{"text_format":"2","workbook":"xlsx","n_sheets":6,"sheets":["765송부","345송부","154송부","한수원","서부","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":18,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":14,"n_cols":16,"rows_kept":14,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2015년도 9월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성S/S #5 M.Tr A-1","신안성S/S #5M.Tr 부싱온라인 모니터링 시스템 설치","신안성S/S 765kV #5M.Tr 부싱온라인 모니터링 시스템 설치","2015-09-12 09:30","2015-09-13 18:00","2015-09-12 09:30","2015-09-13 18:00","연속",null,null,null,201507130119]
[2,"대전충남","서산","당진T/P 신서산-당진TP#1T/L-4호기 1차 CB","2015년 서산P/O 765/345kV GIS 점검공사","○ 당진T/P 765kV 신서산-당진TP#1T/L-4호기 1차GIS(8400) 보통점검","2015-09-21 09:00","2015-09-22 18:00","2015-09-21 09:00","2015-09-22 18:00","연속",null,null,null,201507010092]
[3,"대전충남","서산","당진T/P TIE Tr A","당진T/P 765kV TIE Tr 보통점검 및 보호배전반 대체","○ 당진T/P 765kV TIE Tr 보통점검 및 보호배전반 대체","2015-09-08 09:00","2015-09-11 18:00","취소","취소","연속",null,null,"신뢰도개선",201507090307]
[4,"대전충남","서산","당진T/P 10호기 1차 CB","2015년 서산P/O 765/345kV GIS 점검공사","○ 당진T/P 765kV 10호기 1차 (8971)GIS 초기점검","2015-09-01 09:00","2015-09-02 18:00","2015-09-01 09:00","2015-09-02 18:00","연속",null,null,null,201507010085]
[5,"대전충남","서산","당진T/P 9호기 1차 CB","2015년 서산P/O 765/345kV GIS 점검공사","○ 당진T/P 765kV 9호기 1차 GIS(8972) 보통점검","2015-09-07 09:00","2015-09-08 18:00","2015-09-07 09:00","2015-09-08 18:00","연속",null,null,null,201507010087]
[6,"대전충남","서산","당진T/P 9호기 1차 - 10호기 1차 CB","2015년 서산P/O 765/345kV GIS 점검공사","○ 당진T/P 765kV 9호기 1차 GIS(8900) 보통점검","2015-09-09 09:00","2015-09-10 18:00","2015-09-09 09:00","2015-09-10 18:00","연속",null,null,null,201507010088]
[7,"대전충남","서산","신서산신안성#1 T/L","765kV 신서산-신안성T/L 보호배전반 대체","○ 765kV 신서산-신안성T/L 보호배전반 대체 ○ 765kV 신서산-신안성T/L 선로 정밀점검(아산P/O)","2015-09-14 09:00","2015-09-23 18:00","2015-09-14 09:00","2015-09-23 18:00","연속",null,null,null,201507090308]
[8,"대전충남","서산","신서산신안성#2 T/L","765kV 신서산-신안성 T/L 정밀점검","[송전] 정밀점검 765kV 신서산-신안성 #2T/L : `15.09.07 ~ 13, 07:00 ~ 18:00 [매일] 765kV 신서산-신안성 #1T/L : `15.09.14 ~ 20, 07:00 ~ 18:00 [매일]","2015-09-07 07:00","2015-09-13 18:00","2015-09-07 07:00","2015-09-13 18:00","매일",null,null,null,201507090313]
[9,"경남","함안","북경남신고리NP#1 T/L","765kV 신고리-북경남 송전선로 건설용 자재 운반","식재, 수목 등 철탑복구용 자재 헬기운반","2015-09-01 08:00","2015-09-01 18:00","2015-09-01 08:00","2015-09-01 18:00","당일",null,null,null,201507100042]
[10,"경남","함안","북경남신고리NP#2 T/L","765kV 신고리-북경남 송전선로 건설용 자재 운반","식재, 수목 등 철탑복구용 자재 헬기운반","2015-09-02 08:00","2015-09-02 18:00","2015-09-02 08:00","2015-09-02 18:00","당일",null,null,null,201507100043]

{"sheet":"345송부","index":1,"n_rows":168,"n_cols":16,"rows_kept":168,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2015년도 9월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","양주중부#1 T/L","자기제 피뢰기 교체공사","피뢰기 교체(자기제 -> 폴리머제)","2015-09-17 09:00","2015-09-19 18:00","2015-09-17 09:00","2015-09-19 18:00","연속",null,null,null,201507140154,"-"]
[2,"서울","중부","양주중부#2 T/L","자기제 피뢰기 교체공사","피뢰기 교체(자기제-&gt폴리머제)","2015-09-21 09:00","2015-09-23 18:00","2015-09-21 09:00","2015-09-23 18:00","연속",null,null,null,201507140163,"-"]
[3,"남서울","강남","신양재S/S #1 M.Tr A","신양재S/S #1M.Tr 보호배전반 대체","신양재S/S #1M.Tr 보호배전반 대체","2015-09-21 09:00","2015-09-25 18:00","2015-09-21 09:00","2015-09-25 18:00","연속",null,null,null,201507140001,"-"]
[4,"남서울","영서","영서S/S #1 M.Tr A","불량애자 교체","345kV 및 154kV 불량애자 교체","2015-09-03 09:00","2015-09-03 14:00","2015-09-03 09:00","2015-09-03 14:00","당일",null,null,"신뢰도개선",201507200077,"-"]
[5,"남서울","영서","영서S/S #4 M.Tr A","불량애자 교체","345kV 및 154kV 불량애자 교체","2015-09-03 14:00","2015-09-03 18:00","2015-09-03 14:00","2015-09-03 18:00","당일",null,null,"신뢰도개선",201507200078,"-"]
[6,"남서울","영서","영서S/S #2 M.Tr A","345kV M.Tr 정밀점검","345kV M.Tr 정밀점검","2015-09-14 09:00","2015-09-25 18:00","2015-09-14 09:00","2015-09-25 18:00","연속",null,null,"신뢰도개선",201507210057,"-"]
[7,"인천","김포","345kV신김포S/S #1 M.Tr A","신김포S/S 154kV #61,62M.Tr 증설공사","154kV GIS 2CCT 증설(154kV 모선 증설개소 인접BAY 휴전)","2015-09-07 09:00","2015-09-08 18:00","2015-09-07 09:00","2015-09-08 18:00","연속",null,null,null,201507060138,"-"]
[8,"인천","김포","345kV신김포S/S #1 M.Tr A","신김포S/S 154kV #61,62M.Tr 증설공사","154kV GIS 2CCT 증설(154kV 모선 증설개소 인접BAY 휴전)","2015-09-15 09:00","2015-09-16 18:00","2015-09-15 09:00","2015-09-16 18:00","연속",null,null,null,201507060139,"-"]
[9,"인천","시흥","신시흥#2S/S #5M.Tr A","신시흥#2S/S #5M.Tr 3차 MAIN VCB 보통점검","신시흥#2S/S #5M.Tr 3차 MAIN VCB 보통점검","2015-09-16 09:30","2015-09-16 18:00","2015-09-05 09:30","2015-09-05 18:00","당일",null,null,"신뢰도개선",201507070046,"-"]
[10,"인천","시흥","신시흥#2S/S #6M.Tr A","신시흥#2S/S #6M.Tr 3차 GPT 교체","신시흥#2S/S #6M.Tr 3차 GPT 교체","2015-09-17 09:30","2015-09-17 18:00","2015-09-13 09:30","2015-09-13 18:00","당일",null,null,"신뢰도개선",201507070047,"-"]
[11,"인천","시흥","신시흥신안산 T/L","신시흥#2S/S신시흥신안산 T/L GIS 및 LA보통점검","신시흥#2S/S신시흥신안산 T/L GIS 및 LA보통점검","2015-09-12 09:30","2015-09-12 18:00","2015-09-12 09:30","2015-09-12 18:00","당일",null,null,null,201507070043,"-"]
[12,"인천","시흥","신시흥영흥TP#1 T/L","신시흥-영흥#1T/L 초기점검","신시흥-영흥#1T/L 초기점검(8기)","2015-09-15 09:00","2015-09-15 18:00","2015-09-15 09:00","2015-09-15 18:00","연속",null,null,null,201507020050,"-"]
[13,"인천","시흥","신시흥영흥TP#3 T/L","신시흥-영흥#3T/L 초기점검 및 OPGW 정비","신시흥-영흥#3T/L 초기점검 및 OPGW 정비","2015-09-16 09:00","2015-09-20 18:00","2015-09-16 09:00","2015-09-20 18:00","연속",null,null,null,201507020051,"-"]
[14,"인천","시흥","영흥#2T/P 영흥TP연락#2T/L - TIE CB (7900)","영흥#2T/P 영흥TP연락#2T/L - TIE GIS(7900)","영흥#2T/P 영흥TP연락#2T/L - TIE GIS(7900)","2015-09-23 10:30","2015-09-23 18:00","2015-09-23 10:30","2015-09-23 18:00","당일",null,null,null,201507070044,"-"]
[15,"인천","인천","서인천C/C #3 M.Tr","345kV 서인천C/C 용량부족 GIS 대체공사","- 345kV GIS (7372) 대체 - 기타 부대공사","2015-09-01 09:30","2015-10-02 17:30","2015-09-01 09:30","2015-10-02 17:30","연속",null,null,"신뢰도개선",201507200030,"-"]
[16,"인천","인천","서인천CC신부평#2 T/L","345kV 서인천C/C 용량부족 GIS 대체공사","- 345kV GIS (7371, 7300) 대체 - 기타 부대공사","2015-09-01 09:30","2015-10-02 17:30","2015-09-01 09:30","2015-10-02 17:30","연속",null,null,null,201507200029,"-"]
[17,"인천","인천","서인천C/C 신부평#2T/L Sh.R(#1 Sh.R)","345kV 서인천C/C 용량부족 GIS 대체공사","- #1Sh.R 측 DS 대체","2015-09-01 09:30","2015-10-02 17:30","2015-09-01 09:30","2015-10-02 17:30","연속",null,null,null,201507200032,"-"]
[18,"인천","인천","서인천C/C #1 M.Tr","서인천복합S/Y #1M.Tr 및 LA 보통점검","서인천복합S/Y #1M.Tr 및 LA 보통점검","2015-09-30 09:00","2015-10-01 18:00","2015-09-30 09:00","2015-10-01 18:00","연속",null,null,"신뢰도개선",201507100141,"-"]
[19,"인천","인천","신가좌인천CC#2 T/L","345kV가정루원시티 지중화 정비공사","345kV 가정루원시티 지중화 정비공사 ※금번작업 : #2T/L 건설 및 가압 -신설:3기[4회선(345kV 신가좌-인천CC No.18),2회선 C/H(154kV, 345kV)] -교체:1기[345kV 신가좌-인천CC No.19 Enclosing 공법으로 철탑교체] -철거:20기[345kV 5기, 154kV 15기]","2015-09-07 09:00","2015-10-01 18:00","2015-09-07 09:00","2015-10-01 18:00","연속",null,null,"신뢰도개선",201507130196,"-"]
[20,"인천","인천","신경서S/S #1 M.Tr A","신경서S/S #1M.Tr 휴전 작업","신경서S/S #1M.Tr 휴전 작업 - M.Tr 보통점검 - M.Tr LA 보통점검 - M.Tr 2차 GIS 보통점검 및 보조계전기 교체 - M.Tr 3차 GIS 보통점검","2015-09-02 09:00","2015-09-04 18:00","2015-09-02 09:00","2015-09-04 18:00","연속",null,null,null,201507100133,"-"]
[21,"인천","인천","인천CC S/Y 345kV #76 BUS","인천CC 용량부족 GIS 대체","76 BUS현장개조 75-76-0CB대체, DS45조 대체","2015-09-01 10:00","2015-10-01 17:00","2015-09-01 10:00","2015-10-01 17:00","연속",null,null,null,201507130358,"-"]
[22,"경기북부","구리","동서울미금#1 T/L","2015년 구리전력지사 362kV GIS 정밀점검(7371)","○ 접촉저항, 개폐타임 측정 ○ SF6 SO2, 수분 측정","2015-09-30 08:00","2015-10-02 18:00","2015-09-30 08:00","2015-10-02 18:00","연속",null,null,null,201504300123,"-"]
[23,"경기북부","구리","미금S/S #2 M.Tr A","미금S/S #2M.Tr 주변압기 보통점검 공사","345kV 주변압기 1Bank 보통점검","2015-09-30 09:00","2015-10-01 18:00","2015-09-30 09:00","2015-10-01 18:00","연속",null,null,null,201506170095,"-"]
[24,"경기북부","구리","미금S/S 345kV #4 Sh.R","2015년 구리전력지사 362kV GIS 보통점검","○ 접촉저항, 개폐타임 측정 ○ SF6 SO2, 수분 측정","2015-09-15 10:00","2015-09-15 18:00","2015-09-15 10:00","2015-09-15 18:00","당일",null,null,null,201506120100,"-"]
[25,"경기북부","구리","미금S/S 345kV #6 Sh.R","2015년 구리전력지사 362kV GIS 정밀점검(7272)","○ 접촉저항, 개폐타임 측정 ○ SF6 SO2, 수분 측정","2015-09-21 08:00","2015-09-23 18:00","2015-09-21 08:00","2015-09-23 18:00","연속",null,null,null,201505290012,"-"]
[26,"경기북부","구리","미금S/S 345kV #1 BUS Sh.R MAIN GIS","2015년 362kV GIS 정밀점검(#1,2,5 Sh.R main)","○ 접촉저항, 개폐타임 측정 ○ SF6 SO2, 수분 측정","2015-09-16 08:00","2015-09-18 18:00","2015-09-16 08:00","2015-09-18 18:00","연속",null,null,null,201505290015,"-"]
[27,"경기북부","구리","미금성동#1 T/L","2015년 구리전력지사 362kV GIS 보통점검","○ 접촉저항, 개폐타임 측정 ○ SF6 SO2, 수분 측정","2015-09-24 10:00","2015-09-24 18:00","2015-09-24 10:00","2015-09-24 18:00","당일",null,null,null,201506120099,"-"]
[28,"경기북부","구리","신포천S/S 신포천-동두천CC #2T/L-TIE CB (7600)","345kV 신포천S/S 362kV GIS 설치공사","- 362kV GIS *1 CB 설치 ** 휴전차단기 : 7600 - 무부하 가압(48시간) - 준공시험 - 사용전 검사 -","2015-09-03 09:00","2015-10-13 18:00","2015-09-03 09:00","2015-10-13 18:00","연속",null,null,null,201506120066,"-"]
[29,"경기북부","구리","신포천S/S #3 M.Tr A","신포천S/S 345kV #4M.Tr 증설공사","1. 모선배선을 위한 휴전작업(충전부 유도전압 유기) - 1차 예비모선 연결(기존#3에서 #4M.Tr 연결) - 예비모선 내장 애자련 설치 및 내장모선 설치 - 가공지선 설치 등 2. 휴전신청 사유 : 활선근접 모선배선 작업으로 충전전압 유기에 의한 안전사고 미연방지","2015-09-05 09:00","2015-09-05 18:00","2015-09-05 09:00","2015-09-05 18:00","당일",null,null,null,201506160076,"-"]
[30,"경기북부","구리","신포천S/S 345kV #75 BUS","345kV 신포천S/S 362kV GIS 설치공사","-362kV GIS 1 CB 설치","2015-09-05 09:00","2015-09-06 18:00","2015-09-05 09:00","2015-09-06 18:00","연속",null,null,null,201506120065,"-"]
[31,"경기북부","직할","동두천CC #4TIE 1차 CB (7400)","동두천CC #4TIE 1차 CB","방압변 가스누기 관련 제작사 하자보수","2015-09-18 10:00","2015-09-18 18:00","취소","취소","당일",null,null,null,201507200039,"-"]
[32,"경기북부","직할","동두천CC #3TIE 1차 CB (7300)","동두천CC #3TIE 1차 CB","방압변 가스누기 관련 제작사 하자보수","2015-09-17 10:00","2015-09-17 18:00","취소","취소","당일",null,null,null,201507200038,"-"]
[33,"경기북부","직할","신포천동두천복합#2 T/L","신포천동두천복합#2 T/L","방압변 가스누기 관련 제작사 하자보수","2015-09-14 10:00","2015-09-16 18:00","2015-09-14 10:00","2015-09-16 18:00","연속",null,null,null,201507200036,"-"]
[34,"경기북부","직할","신포천동두천복합#1 T/L","신포천동두천복합#1 T/L","방압변 가스누기 관련 제작사 하자보수","2015-09-09 10:00","2015-09-11 18:00","2015-09-09 10:00","2015-09-11 18:00","연속",null,null,null,201507200035,"-"]
[35,"경기북부","직할","신덕은동두천복합#2 T/L","신덕은동두천복합#2 T/L","방압변 가스누기 관련 제작사 하자보수","2015-09-07 10:00","2015-09-08 18:00","2015-09-07 10:00","2015-09-08 18:00","연속",null,null,null,201507200034,"-"]
[36,"경기북부","직할","신덕은동두천복합#1 T/L","신덕은동두천복합#1 T/L","방압변 가스누기 관련 제작사 하자보수","2015-09-03 10:00","2015-09-04 18:00","2015-09-03 10:00","2015-09-04 18:00","연속",null,null,null,201507200033,"-"]
[37,"경기북부","직할","신의정부S/S #3 M.Tr A","345kV 신의정부S/S 소음저감대책 시행공사","○ 변압기 및 리액터 방음벽 설치 : 6m(높이) × 149m(길이) ○ 변압기 및 리액터 흡음판 설치 : 156개 - 흡음판 : 345kV 의정부S/S 철거자재 재활용 ○ 기타부대공사 1식","2015-09-21 07:30","2015-09-23 18:00","2015-09-21 07:30","2015-09-23 18:00","연속",null,null,null,201507130280,"-"]
[38,"경기북부","직할","신의정부S/S #4 M.Tr A","345kV 신의정부S/S 소음저감대책 시행공사","○ 변압기 및 리액터 방음벽 설치 : 6m(높이) × 149m(길이) ○ 변압기 및 리액터 흡음판 설치 : 156개 - 흡음판 : 345kV 의정부S/S 철거자재 재활용 ○ 기타부대공사 1식","2015-09-14 07:30","2015-09-18 18:00","2015-09-14 07:30","2015-09-18 18:00","연속",null,null,null,201507130278,"-"]
[39,"경기북부","직할","신의정부S/S #2 M.Tr A","345kV 신의정부S/S 소음저감대책 시행공사","○ 변압기 및 리액터 방음벽 설치 : 6m(높이) × 149m(길이) ○ 변압기 및 리액터 흡음판 설치 : 156개 - 흡음판 : 345kV 의정부S/S 철거자재 재활용 ○ 기타부대공사 1식","2015-09-10 07:30","2015-09-12 18:00","2015-09-10 07:30","2015-09-12 18:00","연속",null,null,null,201507130276,"-"]
[40,"경기북부","직할","신의정부S/S #1 M.Tr A","345kV 신의정부S/S 소음저감대책 시행공사","○ 변압기 및 리액터 방음벽 설치 : 6m(높이) × 149m(길이) ○ 변압기 및 리액터 흡음판 설치 : 156개 - 흡음판 : 345kV 의정부S/S 철거자재 재활용 ○ 기타부대공사 1식","2015-09-07 07:30","2015-09-09 18:00","2015-09-07 07:30","2015-09-09 18:00","연속",null,null,null,201507130258,"-"]
[41,"경기북부","직할","신의정부양주#1 T/L","신의정부-양주#1T/L","2015년 경기북부직할 총액공사 - CVT 하자","2015-09-03 10:00","2015-09-03 18:00","2015-09-03 10:00","2015-09-03 18:00","당일",null,null,null,201507140097,"-"]
[42,"경기북부","직할","신의정부S/S 345kV #3 Sh.R","345kV 신의정부S/S 소음저감대책 시행공사","○ 변압기 및 리액터 방음벽 설치 : 6m(높이) × 149m(길이) ○ 변압기 및 리액터 흡음판 설치 : 156개 - 흡음판 : 345kV 의정부S/S 철거자재 재활용 ○ 기타부대공사 1식","2015-09-03 07:30","2015-09-04 18:00","2015-09-03 07:30","2015-09-04 18:00","연속",null,null,null,201507130259,"-"]
[43,"경기북부","직할","신의정부S/S 345kV #2 Sh.R","345kV 신의정부S/S 소음저감대책 시행공사","○ 변압기 및 리액터 방음벽 설치 : 6m(높이) × 149m(길이) ○ 변압기 및 리액터 흡음판 설치 : 156개 - 흡음판 : 345kV 의정부S/S 철거자재 재활용 ○ 기타부대공사 1식","2015-09-01 07:30","2015-09-02 18:00","2015-09-01 07:30","2015-09-02 18:00","연속",null,null,null,201507130256,"-"]
[44,"경기북부","직할","양주S/S SVC M.Tr","14~15년 직할 변전협력회사 총액공사","○ 1차 PT 초기, 2차 모선PT 보통","2015-09-08 10:00","2015-09-08 18:00","2015-09-08 10:00","2015-09-08 18:00","당일",null,null,null,201408180316,"-"]
[45,"경기북부","직할","양주S/S 345kV #4 Sh.R","양주S/S 345kV #4 Sh.R","2015년 경기북부직할 총액공사 - GIS 하자점검","2015-09-03 10:00","2015-09-03 18:00","2015-09-03 10:00","2015-09-03 18:00","당일",null,null,null,201507140079,"-"]
[46,"경기북부","파주","신파주양주#1 T/L","345kV 신파주-양주T/L 전선접속개소 전선교체공사","345kV 신파주-양주T/L 전선접속개소 전선교체공사 No.10~13등 6구간","2015-09-05 07:30","2015-09-14 18:00","2015-09-05 07:30","2015-09-14 18:00","연속",null,null,null,201507140116,"-"]
[47,"경기북부","파주","신파주양주#2 T/L","345kV 신파주-양주T/L 전선접속개소 전선교체공사","345kV 신파주-양주T/L 전선접속개소 전선교체공사 No.10~13등 6구간","2015-09-15 07:30","2015-09-24 18:00","2015-09-15 07:30","2015-09-24 18:00","연속",null,null,null,201507140118,"-"]
[48,"경기","군포","서서울S/S 345kV #1 BUS GIS","345kV 신군포S/S 건설공사","단계별 휴전작업 공정 - 7771CB,7871CB 증설","2015-09-01 09:00","2015-09-12 18:00","2015-09-01 09:00","2015-09-12 18:00","연속",null,null,"신뢰도개선",201507100082,"-"]
[49,"경기","군포","서서울S/S #1 M.Tr A","345kV 신군포S/S 건설공사","단계별 휴전작업 공정 - 모선배선 변경 - 중간 기설철구 1기 철거후 다음철구로 모선배선 변경","2015-09-01 09:00","2015-09-02 18:00","2015-09-01 09:00","2015-09-02 18:00","연속",null,null,null,201507100081,"-"]
[50,"경기","군포","화성서서울#2 T/L","345kV 신군포S/S 건설공사","단계별 휴전작업 공정 - BAY 변경(#2BUS측 77BAY -> #1BUS측 77BAY) - 7771CB 신설 준공시험 - 보호배전반 준공시험 등","2015-09-13 09:00","2015-09-24 18:00","2015-09-13 09:00","2015-09-24 18:00","연속",null,null,"신뢰도개선",201507100089,"-"]
[51,"경기","군포","서서울S/S #3 M.Tr A","345kV 신군포S/S 건설공사","Bay변경(77 #1BUS측 → 77 #2BUS측) 간섭휴전","2015-09-19 09:00","2015-09-20 18:00","2015-09-19 09:00","2015-09-20 18:00","연속",null,null,null,201507130322,"-"]
[52,"경기","군포","화성서서울#1 T/L","345kV 신군포S/S 건설공사","단계별 휴전작업 공정 - BAY 변경(74 → 78) - 7871CB 신설 준공시험 - 보호배전반 준공시험 등","2015-09-30 09:00","2015-10-07 18:00","2015-09-30 09:00","2015-10-07 18:00","연속",null,null,null,201507100110,"-"]
[53,"경기","군포","서서울S/S #3 M.Tr A","345kV 신군포S/S 건설공사","Bay변경(74 → 78) 간섭휴전","2015-09-30 09:00","2015-10-02 18:00","2015-09-30 09:00","2015-10-02 18:00","연속",null,null,null,201507130323,"-"]
[54,"경기","성남","신시흥신성남#1 T/L","신성남-신시흥T/L OPGW 이설공사","임시구성 작업 - No 53 ~54호 OPGW 이설","2015-09-19 09:00","2015-09-20 18:00","2015-09-19 09:00","2015-09-20 18:00","연속",null,null,null,201507100113,"-"]
[55,"경기","성남","신성남신양재#1 T/L","345kV 신성남S/S 신성남신양재#1 T/L PNL대체","345kV 신성남S/S 신성남신양재#1 T/L PNL대체","2015-09-07 09:00","2015-09-11 18:00","2015-09-07 09:00","2015-09-11 18:00","연속",null,null,null,201507130073,"-"]
[56,"경기","성남","신안성신성남#1 T/L","345kV 신안성,신성남/S 신안성신성남#1 T/L 보통점검","345kV 신안성,신성남/S 신안성신성남#1 T/L 보통점검","2015-09-01 09:00","2015-09-01 18:00","2015-09-01 09:00","2015-09-01 18:00","당일",null,null,null,201507130076,"-"]
[57,"경기","성남","신성남신양재#2 T/L","345kV 신성남S/S 신성남신양재#2 T/L PNL대체","345kV 신성남S/S 신성남신양재#2 T/L PNL대체","2015-09-12 09:00","2015-09-16 18:00","2015-09-12 09:00","2015-09-16 18:00","연속",null,null,null,201507130082,"-"]
[58,"경기","성남","신성남S/S #2 M.Tr A","345kV 신성남S/S #2 M.Tr 정밀점검","345kV 신성남S/S #2 M.Tr 정밀점검","2015-09-30 09:00","2015-10-14 18:00","2015-09-30 09:00","2015-10-14 18:00","연속",null,null,null,201507130089,"-"]
[59,"경기","성남","신용인신수원 T/L","345kV 신용인S/S 신용인신수원 T/L BF PNL대체","345kV 신용인S/S 신용인신수원 T/L BF PNL대체","2015-09-07 09:00","2015-09-10 18:00","2015-09-07 09:00","2015-09-10 18:00","연속",null,null,null,201507130086,"-"]
[60,"경기","성남","동서울신용인#2 T/L","345kV 신용인-동서울T/L 지장이설 공사","○ 지 지 물 :4각 철탑 9기, 철거 5기 ○ 전 력 선 : ACSR 480mm2×2B×2C - 설치 : 2C-0.664km - 철거 : 2C-0.892km, 4C-2.427km ○ 공사구간 : 345kV 신용인-동서울T/L No.56-62 ○ 공사목적 : 경기도 광주시 태전택지지구 조성을 위한 지장이설 공사","2015-09-29 06:00","2015-10-04 18:00","2015-09-29 06:00","2015-10-04 18:00","연속",null,null,null,201507130353,"-"]
[61,"경기","성남","신용인S/S #1 M.Tr A","345kV 신용인S/S #1M.Tr B상 초기점검","345kV 신용인S/S #1M.Tr B상 초기점검, TCC PNL대체, #1S.Tr 보통점검, 집중감시반 수용","2015-09-01 09:00","2015-09-04 18:00","2015-09-01 09:00","2015-09-04 18:00","연속",null,null,null,201507130070,"-"]
[62,"경기","성남","동서울신용인#1 T/L","345kV 신용인-동서울T/L 지장이설 공사","○ 지 지 물 :4각 철탑 9기, 철거 5기 ○ 전 력 선 : ACSR 480mm2×2B×2C - 설치 : 2C-0.664km - 철거 : 2C-0.892km, 4C-2.427km ○ 공사구간 : 345kV 신용인-동서울T/L No.56-62 ○ 공사목적 : 경기도 광주시 태전택지지구 조성을 위한 지장이설 공사","2015-09-17 06:00","2015-09-25 18:00","2015-09-17 06:00","2015-09-25 18:00","연속",null,null,null,201507130352,"-"]
[63,"경기","성남","동서울신용인#2 T/L","345kV 신용인-동서울T/L 지장이설 공사","○ 지 지 물 :4각 철탑 9기, 철거 5기 ○ 전 력 선 : ACSR 480mm2×2B×2C - 설치 : 2C-0.664km - 철거 : 2C-0.892km, 4C-2.427km ○ 공사구간 : 345kV 신용인-동서울T/L No.56-62 ○ 공사목적 : 경기도 광주시 태전택지지구 조성을 위한 지장이설 공사","2015-09-11 06:00","2015-09-16 18:00","2015-09-11 06:00","2015-09-16 18:00","연속",null,null,null,201507130349,"-"]
[64,"강원","동해","동해S/S #3 M.Tr A","2015년 동해전력지사 주변압기 정밀점검공사","1. #3M.Tr 주변압기 정밀점검 2. #3M.Tr B상 OLTC 정밀점검 3. #3M.Tr 1차 PT 교체 4. #3M.Tr 1차, 3차 LA 교체 및 보통점검 5. #3M.Tr 3차즉 지지애자 교체 6. #3M.Tr 방호벽 도장","2015-09-10 09:30","2015-09-21 18:00","2015-09-10 09:30","2015-09-21 18:00","연속",null,null,null,201507060176,"-"]
[65,"강원","동해","동해S/S #1 M.Tr A","2015년 동해전력지사 변전협력회사 총액공사","1. #1M.Tr B상 1차 중성점 붓싱(Ho) 누유보수 2. #1M.Tr 3차측 지지애자 교체","2015-09-02 09:30","2015-09-04 18:00","2015-09-02 09:30","2015-09-04 18:00","연속",null,null,null,201507130065,"-"]
[66,"강원","동해","동해S/S #2 M.Tr A","2015년 동해전력지사 변전협력회사 총액공사","1. #2M.Tr 3차측 지지애자 교체","2015-09-07 09:30","2015-09-09 18:00","2015-09-07 09:30","2015-09-09 18:00","연속",null,null,null,201507130068,"-"]
[67,"강원","동해","동해-삼척GP#1T/L T/L","2015년도 가공송전 순시점검 위탁공사","1.소손단선 가공지선 교체공사","2015-09-09 09:00","2015-09-09 18:00","2015-09-09 09:00","2015-09-09 18:00","당일",null,null,null,201507140174,"-"]
[68,"강원","태백","신태백S/S 345kV #3 Sh.R","345kV #3 Sh.R 부싱 교체공사","부싱(GIB) 교체공사","2015-09-07 09:00","2015-09-25 18:00","2015-09-07 09:00","2015-09-25 18:00","연속",null,null,null,201507090057,"-"]
[69,"충북","직할","신제천신충주#1 T/L","2014-15년 직할 송전정비협력회사 총액공사(항공장애구 교체)","항공장애표시구 교체공사","2015-09-01 08:00","2015-09-01 18:00","2015-09-01 08:00","2015-09-01 18:00","당일",null,null,null,201507220058,"-"]
[70,"충북","직할","신제천S/S #1 M.Tr A","345kV 신제천S/S GIS화 공사","신제천S/S 옥외철구 GIS화 (345kV GIS 15CB, 154kV GIS 28CCT) ○ 신제천S/S 345kV FACTS 설비 설치공간 확보 ○ 옥외철구설비 GIS화를 통한 전력공급 신뢰도 제고 - 154kV T-BUS 철거 작업구간(154kV GIS 공사구간) 확보","2015-09-16 09:00","2015-09-16 18:00","2015-09-16 09:00","2015-09-16 18:00","당일",null,null,null,201507200057,"-"]
[71,"충북","직할","신제천S/S #3 M.Tr A","345kV 신제천S/S GIS화 공사","신제천S/S 옥외철구 GIS화 (345kV GIS 15CB, 154kV GIS 28CCT) ○ 신제천S/S 345kV FACTS 설비 설치공간 확보 ○ 옥외철구설비 GIS화를 통한 전력공급 신뢰도 제고 - 154kV T-BUS 철거 작업구간(154kV GIS 공사구간) 확보","2015-09-17 09:00","2015-09-17 18:00","2015-09-17 09:00","2015-09-17 18:00","당일",null,null,null,201507200059,"-"]
[72,"충북","직할","신제천S/S #4 M.Tr A","345kV 신제천S/S GIS화 공사","신제천S/S 옥외철구 GIS화 (345kV GIS 15CB, 154kV GIS 28CCT) ○ 신제천S/S 345kV FACTS 설비 설치공간 확보 ○ 옥외철구설비 GIS화를 통한 전력공급 신뢰도 제고 - 154kV T-BUS 철거 작업구간(154kV GIS 공사구간) 확보","2015-09-18 09:00","2015-09-18 18:00","2015-09-18 09:00","2015-09-18 18:00","당일",null,null,null,201507200060,"-"]
[73,"충북","직할","신제천동해#2 T/L","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 345kV GIS 15CB 설치, 옥외설비 철거 - #2M.TR측 분기모선 철거 (송전선로 휴전기간 최소화 방안)","2015-09-21 09:00","2015-09-21 18:00","2015-09-05 09:00","2015-09-05 18:00","당일",null,null,"신뢰도개선",201507240015,"-"]
[74,"충북","직할","신제천S/S 신제천-동해#2T/L CB (7172)","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 345kV GIS 15CB 설치, 옥외설비 철거 - #2M.TR측 분기모선 철거 (송전선로 휴전기간 최소화 방안)","2015-09-22 09:00","2015-09-22 18:00","2015-09-20 09:00","2015-09-20 18:00","당일",null,null,"신뢰도개선",201507130137,"-"]
[75,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 345kV GIS 15CB 설치, 옥외설비 철거 - #2M.TR측 분기모선 철거 (송전선로 휴전기간 최소화 방안)","2015-09-22 09:00","2015-09-22 18:00","2015-09-20 09:00","2015-09-20 18:00","당일",null,null,"신뢰도개선",201507130139,"-"]
[76,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 345kV GIS 15CB 설치, 옥외설비 철거 - #2M.TR측 분기모선 철거 (송전선로 휴전기간 최소화 방안)","2015-09-21 09:00","2015-09-21 18:00","2015-09-19 09:00","2015-09-19 18:00","당일",null,null,"신뢰도개선",201507130140,"-"]
[77,"충북","직할","신제천S/S 신제천-동해#2T/L-TIE CB (7100)","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 345kV GIS 15CB 설치, 옥외설비 철거 - #2M.TR측 분기모선 철거 (송전선로 휴전기간 최소화 방안)","2015-09-21 09:00","2015-09-21 18:00","2015-09-19 09:00","2015-09-19 18:00","당일",null,null,"신뢰도개선",201507130136,"-"]
[78,"충북","직할","신제천S/S #2 M.Tr A","345kV 신제천S/S GIS화 공사","신제천S/S 옥외철구 GIS화 (345kV GIS 15CB, 154kV GIS 28CCT) ○ 신제천S/S 345kV FACTS 설비 설치공간 확보 ○ 옥외철구설비 GIS화를 통한 전력공급 신뢰도 제고 - 154kV T-BUS 철거 작업구간(154kV GIS 공사구간) 확보 - 345kV GIS 설치공간 확보","2015-09-19 09:00","2016-05-20 18:00","2015-09-19 09:00","2016-05-20 18:00","연속",null,null,null,201507200056,"-"]
[79,"충북","직할","곤지암신충주#1 T/L","2015년 직할 변전협력회사 총액공사","장기사용 배전반 대체","2015-09-07 09:00","2015-09-11 18:00","취소","취소","연속",null,null,"신뢰도개선",201506040123,"-"]
[80,"충북","직할","곤지암신충주#2 T/L","2015년 직할 변전협력회사 총액공사","장기사용 보호배전반 대체","2015-09-14 09:00","2015-09-18 18:00","취소","취소","연속",null,null,"신뢰도개선",201507140212,"-"]
[81,"충북","직할","신충주S/S 신제천-신충주#2 T/L GIS","신충주S/S #3M.Tr 증설공사","차단기실폐보호반용 계전기 설치","2015-09-02 09:00","2015-09-04 18:00","2015-09-02 09:00","2015-09-04 18:00","연속",null,null,null,201506120083,"-"]
[82,"대전충남","아산","신온양S/S #3 M.Tr A","345kV #3M.Tr 2차 GIS 6344 터미널 단자블럭 교체","○단자블럭 불량에 따른 신온양S/S 345kV #3M.Tr 2차 GIS 6344 터미널 단자블럭 교체","2015-09-03 09:00","2015-09-03 18:00","2015-09-03 09:00","2015-09-03 18:00","당일",null,null,null,201507100249,"-"]
[83,"대전충남","아산","신온양S/S #4 M.Tr A","345kV #4M.Tr 2차 GIS 6444 터미널 단자블럭 교체","○단자블럭 불량에 따른 신온양S/S 345kV #4M.Tr 2차 GIS 6444 터미널 단자블럭 교체","2015-09-04 09:00","2015-09-04 18:00","2015-09-04 09:00","2015-09-04 18:00","당일",null,null,null,201507100248,"-"]
[84,"대전충남","아산","아산S/S #2 M.Tr A","아산S/S 345kV #2M.Tr A,B,C상 보통점검","○아산S/S 345kV #2M.Tr A,B,C상 보통점검○345kV #2M.Tr 2차 GIS 6244 보통점검","2015-09-12 09:00","2015-09-12 18:00","2015-09-12 09:00","2015-09-12 18:00","당일",null,null,null,201507100256,"-"]
[85,"대전충남","아산","아산S/S #1 M.Tr A","아산S/S 345kV #1M.Tr 2차 GIS 6144 정밀점검","○345kV #1M.Tr 2차 GIS 6144 정밀점검","2015-09-19 09:00","2015-09-20 18:00","2015-09-19 09:00","2015-09-20 18:00","연속",null,null,null,201507100254,"-"]
[86,"전북","김제","신김제S/S #1 M.Tr A","신김제S/S 345kV #1 M.Tr","345kV #1 M.Tr 1차 차단기 정밀점검","2015-09-07 09:00","2015-09-11 18:00","2015-09-07 09:00","2015-09-11 18:00","연속",null,null,null,201507160078,"-"]
[87,"전북","김제","신김제S/S #2 M.Tr A","신김제S/S 345kV #2 M.Tr","345kV #2 M.Tr 1차 차단기 정밀점검","2015-09-14 09:00","2015-09-18 18:00","2015-09-14 09:00","2015-09-18 18:00","연속",null,null,null,201507160079,"-"]
[88,"광주전남","강진","신강진S/S #2 M.Tr A","345kV 신강진S/S 23kV Sh.R 설치공사","- 23kV Sh.R(건식, 15MVar × 3대) × 2Bank 설치 - 23kV VCB(40kA 3000/2000A)설치 × 3대 설치 - 23kV Sh.R 보호배전반 설치 × 1면 설치 - 23kV S.Tr(150kVA) × 1대 이설","2015-09-02 09:00","2015-09-04 18:00","2015-09-02 09:00","2015-09-04 18:00","연속",null,null,null,201507060207,"-"]
[89,"광주전남","광주","신광주신화순#1 T/L","신광주신화순#1 T/L(신광주S/S 362kV 장기사용GIS 대체)","가. 362kV GIS(40kA 4000A 3CB) × 1식 철거 (#3M.Tr 1차 GIS, 신광주-신화순#1T/L GIS) 나. 362kV GIS(50kA 4000A 3CB) × 1식 설치 (#3M.Tr 1차 GIS, 신광주-신화순#1T/L GIS)","2015-09-01 09:00","2015-09-25 18:00","2015-09-01 09:00","2015-09-25 18:00","연속",null,null,null,201507070016,"-"]
[90,"광주전남","광주","신화순신강진#2 T/L","신화순-신강진#2 T/L (345kV 신강진S/S 노후배전반 정비공사)","345kV 신강진S/S 노후배전반 정비공사 - 신화순-신강진#2T/L 제어케이블 결선","2015-09-30 09:00","2015-10-02 18:00","2015-09-30 09:00","2015-10-02 18:00","연속",null,null,null,201507280073,"-"]
[91,"광주전남","광주","신광주S/S #3 M.Tr A","신광주S/S #3 M.Tr A(신광주S/S 362kV장기사용GIS 대체)","가. 362kV GIS(40kA 4000A 3CB) × 1식 철거 (#3M.Tr 1차 GIS, 신광주-신화순#1T/L GIS) 나. 362kV GIS(50kA 4000A 3CB) × 1식 설치 (#3M.Tr 1차 GIS, 신광주-신화순#1T/L GIS)","2015-09-01 09:00","2015-09-25 18:00","2015-09-01 09:00","2015-09-25 18:00","연속",null,null,null,201507070017,"-"]
[92,"광주전남","순천","광양광양복합#1 T/L","KP복합#1T/L(BF반 86T 램프 성능개선)","BF반 86T 램프 성능개선 - 램프 교체","2015-09-19 09:00","2015-09-20 18:00","2015-09-19 09:00","2015-09-20 18:00","당일",null,null,null,201507100206,"-"]
[93,"광주전남","순천","광양광양제철#1 T/L","광양제철#1T/L(BF반 86T 램프 성능개선)","BF반 86T 램프 성능개선 - 램프 교체","2015-09-07 09:00","2015-09-11 18:00","2015-09-07 09:00","2015-09-11 18:00","당일",null,null,null,201507100209,"-"]
[94,"광주전남","순천","광양광양제철#2 T/L","광양제철#2T/L(BF반 86T 램프 성능개선)","BF반 86T 램프 성능개선 - 램프 교체","2015-09-14 09:00","2015-09-18 18:00","2015-09-14 09:00","2015-09-18 18:00","당일",null,null,null,201507100211,"-"]
[95,"광주전남","순천","광양여수TP T/L","광양S/S 광양-여수TP T/L(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사 - 345kV 74Bay B/F PNL 교체","2015-09-30 09:00","2015-10-02 18:00","2015-09-30 09:00","2015-10-02 18:00","연속",null,null,null,201507140240,"-"]
[96,"광주전남","순천","광양광양복합#2 T/L","KP복합#2T/L(BF반 86T 램프 성능개선)","BF반 86T 램프 성능개선 - 램프 교체","2015-09-05 13:00","2015-09-05 18:00","2015-09-05 13:00","2015-09-05 18:00","당일",null,null,null,201507100210,"-"]
[97,"광주전남","순천","신남원광양#1 T/L","광양S/S 신남원-광양#1T/L(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사(변전) - 345kV 72Bay B/F PNL 교체 345kV 신남원-광양 등 2개T/L 안전이격확보공사(송전) - 철탑교체 : 1기(No.105호)","2015-09-07 09:00","2015-09-11 18:00","2015-09-07 09:00","2015-09-11 18:00","연속",null,null,null,201507140225,"-"]
[98,"광주전남","순천","신남원광양#2 T/L","광양S/S 신남원-광양#2T/L(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사(변전) - 345kV 71Bay B/F PNL 교체 345kV 신남원-광양 등 2개T/L 안전이격확보공사(송전) - 철탑교체 : 1기(No.105호)","2015-09-12 09:00","2015-09-18 18:00","2015-09-12 09:00","2015-09-18 18:00","연속",null,null,null,201507140228,"-"]
[99,"광주전남","순천","광양S/S #2 M.Tr A","광양S/S #2M.Tr A(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사 - 345kV 74Bay B/F PNL 교체","2015-09-30 09:00","2015-10-02 18:00","2015-09-30 09:00","2015-10-02 18:00","연속",null,null,null,201507140241,"-"]
[100,"광주전남","순천","광양율촌CC T/L","광양S/S 광양-율촌CC T/L(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사 - 345kV 73Bay B/F PNL 교체","2015-09-21 09:00","2015-09-25 18:00","2015-09-21 09:00","2015-09-25 18:00","연속",null,null,null,201507140229,"-"]
[101,"광주전남","순천","광양S/S #1 M.Tr A","광양S/S #1M.Tr A(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사 - 345kV 71Bay B/F PNL 교체","2015-09-14 09:00","2015-09-18 18:00","2015-09-14 09:00","2015-09-18 18:00","연속",null,null,null,201507140227,"-"]
[102,"광주전남","순천","율촌CC 여수TP T/L","345kV 광양-율촌CC T/L(피뢰기 설치공사)","송전선로용 피뢰기 설치 105기","2015-09-26 09:00","2015-09-29 18:00","2015-09-26 09:00","2015-09-29 18:00","연속",null,null,null,201507150164,"-"]
[103,"광주전남","직할","한빛2NP-한빛3NP #3 T/L","한빛연락#3 T/L(345kV 피뢰기 설치공사)","발전소 연계설비 피뢰기 설치","2015-09-18 09:00","2015-09-19 18:00","2015-09-18 09:00","2015-09-19 18:00","연속",null,null,null,201507150108,"-"]
[104,"광주전남","직할","신남원한빛NP#1 T/L","신남원한빛NP#1 T/L(인출변경 접속설비 보강공사)","345kV 한빛본부 2,3발전소 인출변경 접속설비 보강공사 1.구간 : 한빛원자력 구내(신남원, 신김제-한빛 NO.1~4호) 2.지지물 : 사각철탑 1기 설치, 3기 철거","2015-09-24 09:00","2015-09-24 18:00","2015-09-24 09:00","2015-09-24 18:00","연속",null,null,null,201507220077,"-"]
[105,"광주전남","직할","신남원한빛NP#2 T/L","신남원한빛NP#2 T/L(인출변경 접속설비 보강공사)","345kV 한빛본부 2,3발전소 인출변경 접속설비 보강공사 1.구간 : 한빛원자력 구내(신남원, 신김제-한빛 NO.1~4호) 2.지지물 : 사각철탑 1기 설치, 3기 철거","2015-09-18 09:00","2015-09-23 18:00","2015-09-18 09:00","2015-09-23 18:00","연속",null,null,null,201507220076,"-"]
[106,"광주전남","직할","신김제한빛NP#2 T/L","신김제한빛NP#2 T/L(인출변경 접속설비 보강공사)","345kV 한빛본부 2,3발전소 인출변경 접속설비 보강공사 1.구간 : 한빛원자력 구내(신남원, 신김제-한빛 NO.1~4호) 2.지지물 : 사각철탑 1기 설치, 3기 철거","2015-09-14 09:00","2015-09-17 18:00","2015-09-14 09:00","2015-09-17 18:00","연속",null,null,null,201507220074,"-"]
[107,"광주전남","직할","한빛3N/P 345kV #2BUS","한빛#3NP 345kV #2BUS","14-15년 직할 변전협력회사 총액공사 345KV #2BUS PRO PNL 대체","2015-09-10 09:00","2015-09-13 18:00","2015-09-10 09:00","2015-09-13 18:00","연속",null,null,null,201507140027,"-"]
[108,"광주전남","직할","신김제한빛NP#1 T/L","신김제한빛NP#1 T/L(인출변경 접속설비 보강공사)","345kV 한빛본부 2,3발전소 인출변경 접속설비 보강공사 1.구간 : 한빛원자력 구내(신남원, 신김제-한빛 NO.1~4호) 2.지지물 : 사각철탑 1기 설치, 3기 철거","2015-09-18 09:00","2015-09-23 18:00","2015-09-18 09:00","2015-09-23 18:00","연속",null,null,null,201507220075,"-"]
[109,"대구경북","경산","신경산S/S #3 M.Tr A","신경산S/S 345kV #3M.Tr 및 관련설비 보통점검","주변압기, 6344, LA, 3차측 GPT 보통점검","2015-09-22 09:00","2015-09-23 18:00","2015-09-22 09:00","2015-09-23 18:00","연속",null,null,null,201507090199,"-"]
[110,"대구경북","달성","고령S/S #3 M.Tr A","변압기 보호반 판넬교체","변압기 보호반판넬교체","2015-09-19 09:00","2015-09-21 18:00","2015-09-19 09:00","2015-09-21 18:00","연속",null,null,null,201507030031,"-"]
[111,"대구경북","영주","신영주S/S #1 M.Tr A","신영주S/S 362kV GIS화 공사","○ 345kV 보호배전반 이설","2015-09-11 09:00","2015-09-24 18:00","2015-09-11 09:00","2015-09-24 18:00","연속",null,null,"신뢰도개선",201507150083,"-"]
[112,"대구경북","영주","신영주한울NP3#2 T/L","신영주S/S 362kV GIS화 공사","○ 345kV 보호배전반 이설 및 6144. 637 GCB 대체","2015-09-11 09:00","2015-09-24 18:00","2015-09-11 09:00","2015-09-24 18:00","연속",null,null,"신뢰도개선",201507150081,"-"]
[113,"대구경북","영주","신영주한울NP3#1 T/L","신영주S/S 362kV GIS화 공사","○ 345kV 보호배전반 이설","2015-09-25 09:00","2015-10-11 18:00","2015-09-25 09:00","2015-10-11 18:00","연속",null,null,"신뢰도개선",201507150084,"-"]
[114,"대구경북","영주","한울3N/P 345kV #2 BUS","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2015-09-11 09:00","2015-09-15 18:00","2015-09-11 09:00","2015-09-15 18:00","연속",null,null,null,201507210041,"-"]
[115,"대구경북","칠곡","서대구S/S #3 M.Tr A","#3M.Tr 누유 하자보수","#3M.Tr 누유 하자보수","2015-09-05 09:30","2015-09-06 18:00","2015-09-05 09:30","2015-09-06 18:00","매일",null,null,null,201507090132,"-"]
[116,"대구경북","포항","신포항S/S #3 M.Tr 1차 CB (7872)","신포항S/S 7872 GIS 휴전작업","7862 DS 전자변 누기보수","2015-09-10 09:00","2015-09-10 18:00","2015-09-10 09:00","2015-09-10 18:00","당일",null,null,null,201507090029,"-"]
[117,"대구경북","포항","신포항S/S 신포항POSCO #2T/L CB (7372)","신포항S/S 신포항-포스코#2T/L 휴전작업","7372CB, 7362,7322DS, PT 보통점검","2015-09-17 09:30","2015-09-17 17:00","2015-09-17 09:30","2015-09-17 17:00","당일",null,null,null,201507090111,"-"]
[118,"대구경북","포항","신포항S/S 신포항POSCO #1T/L CB (7471)","신포항S/S 신포항-포스코#1T/L 휴전작업","7471CB, 7461, 7421 DS, PT 보통점검","2015-09-16 09:30","2015-09-16 17:00","2015-09-16 09:30","2015-09-16 17:00","당일",null,null,null,201507090104,"-"]
[119,"대구경북","포항","월성2N/P F2-#4 SS Tr 1차 CB (7800)","월성S/Y 7800 GIS 휴전작업","7800GIS 보통점검","2015-09-01 10:00","2015-09-01 18:00","2015-09-01 10:00","2015-09-01 18:00","당일",null,null,null,201507090018,"-"]
[120,"대구경북","포항","월성2N/P 75-76-0 SEC CB (75-76-0)","월성S/Y 75-76-0 SEC GIS 휴전작업","75-76-0 SEC GIS 보통점검","2015-09-04 10:00","2015-09-04 18:00","2015-09-04 10:00","2015-09-04 18:00","당일",null,null,null,201507090023,"-"]
[121,"대구경북","포항","월성2N/P 70-71-0 SEC CB (70-71-0)","월성S/Y 70-71-0 SEC GIS 휴전작업","70-71-0 SEC GIS 보통점검","2015-09-03 10:00","2015-09-03 18:00","2015-09-03 10:00","2015-09-03 18:00","당일",null,null,null,201507090026,"○"]
[122,"대구경북","포항","월성2N/P #4 SS Tr 1차 CB (7872)","월성S/Y 7872 휴전작업","7872 GIS 보통점검","2015-09-02 10:00","2015-09-02 18:00","2015-09-02 10:00","2015-09-02 18:00","당일",null,null,null,201507090021,"-"]
[123,"부산울산","동부산","고리N/P S/Y 71-72-0 BUS SEC CB (71-72-0)","고리NP S/Y 362kV GIS 유압설비 보수 - 71-72-0 CB","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 71-72-0 SEC CB (71-72-0 CB)","2015-09-22 09:00","2015-09-22 14:00","2015-09-22 09:00","2015-09-22 14:00","당일",null,null,null,201507100119,"-"]
[124,"부산울산","동부산","고리N/P S/Y 신고리-고리#2T/L CB (7F71)","고리NP S/Y 362kV GIS 유압설비 보수 - 7F71 CB","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 신고리-고리#2T/L CB (7F71 CB)","2015-09-14 13:00","2015-09-14 17:00","2015-09-14 13:00","2015-09-14 17:00","당일",null,null,null,201507100109,"-"]
[125,"부산울산","동부산","고리N/P 신고리#1,2 SAT-고리#4 SUT B CB (7600)","고리NP S/Y 362kV GIS 유압설비 보수 - 7600 CB","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 신고리#1,2 SAT-고리#4 SUT B CB (7600 CB)","2015-09-15 09:00","2015-09-15 13:00","2015-09-15 09:00","2015-09-15 13:00","당일",null,null,null,201507100111,"-"]
[126,"부산울산","동부산","고리N/P S/Y 신고리#1,2 SAT CB (7671)","고리NP S/Y 362kV GIS 유압설비 보수 - 7671 CB","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 신고리#1,2 SAT CB (7671 CB)","2015-09-15 13:00","2015-09-15 17:00","2015-09-15 13:00","2015-09-15 17:00","당일",null,null,null,201507100112,"-"]
[127,"부산울산","동부산","고리N/P S/Y 고리 #4 SUT B CB (7672)","고리NP S/Y 362kV GIS 유압설비 보수 - 7672 CB","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 고리 #4 SUT B CB (7672 CB)","2015-09-16 09:00","2015-09-16 13:00","2015-09-16 09:00","2015-09-16 13:00","당일",null,null,null,201507100114,"-"]
[128,"부산울산","동부산","고리N/P S/Y 7077 BUS SEC CB (7077)","고리NP S/Y 362kV GIS 유압설비 보수 - 7177 CB 점검","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 7177 SEC CB (7177 CB) - 7077, 7177 동시에 휴전되어야 함","2015-09-21 09:00","2015-09-21 14:00","2015-09-21 09:00","2015-09-21 14:00","당일",null,null,null,201507100115,"-"]
[129,"부산울산","동부산","고리N/P S/Y 7177 BUS SEC CB (7177)","고리NP S/Y 362kV GIS 유압설비 보수 - 7177 CB 점검","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 7177 SEC CB (7177 CB) - 7077, 7177 동시에 휴전되어야 함","2015-09-21 09:00","2015-09-21 14:00","2015-09-21 09:00","2015-09-21 14:00","당일",null,null,null,201507100116,"-"]
[130,"부산울산","동부산","고리N/P S/Y 7577 BUS SEC CB (7577)","고리NP S/Y 362kV GIS 유압설비 보수 - 7677 CB 점검","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 7677 SEC CB (7677 CB) - 7577, 7677 동시에 휴전되어야 함","2015-09-21 14:00","2015-09-21 18:00","2015-09-21 14:00","2015-09-21 18:00","당일",null,null,null,201507100117,"-"]
[131,"부산울산","동부산","고리N/P S/Y 76-77-0 BUS SEC CB (76-77-0)","고리NP S/Y 362kV GIS 유압설비 보수 - 76-77-0 CB","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 76-77-0 SEC CB (76-77-0 CB)","2015-09-22 14:00","2015-09-22 18:00","2015-09-22 14:00","2015-09-22 18:00","당일",null,null,null,201507100121,"-"]
[132,"부산울산","동부산","고리N/P S/Y 신고리-고리#2T/L-TIE CB (7F00)","고리NP S/Y 362kV GIS 유압설비 보수 - 7F00 CB","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 신고리-고리#2T/L-TIE CB (7F00 CB)","2015-09-14 09:00","2015-09-14 13:00","2015-09-14 09:00","2015-09-14 13:00","당일",null,null,null,201507100107,"-"]
[133,"부산울산","동부산","고리N/P S/Y 7677 BUS SEC CB (7677)","고리NP S/Y 362kV GIS 유압설비 보수 - 7677 CB 점검","고리NP S/Y 362kV GIS 유압설비 보수 점검설비 : 고리NP S/Y 7677 SEC CB (7677 CB) - 7577, 7677 동시에 휴전되어야 함","2015-09-21 14:00","2015-09-21 18:00","2015-09-21 14:00","2015-09-21 18:00","당일",null,null,null,201507100118,"-"]
[134,"부산울산","북부산","신김해북부산#2 T/L","154kV 호포분기T/L 건설공사","○ 신설 154kV 호포분기T/L No.3~4구간 가공지선 및 OPGW 가선을 위한 안전이격 확보","2015-09-04 07:00","2015-09-04 19:00","2015-09-04 07:00","2015-09-04 19:00","당일",null,null,null,201507060010,"-"]
[135,"부산울산","북부산","북부산S/S #4 M.Tr A","2015년 북부산변전협력회사 총액공사","4-2Sh.R 설치 및 시험가압24시간 (#4M.Tr)","2015-09-01 09:00","2015-09-02 18:00","2015-09-01 09:00","2015-09-02 18:00","연속",null,null,null,201507130266,"-"]
[136,"부산울산","서부산","서부산S/S 서부산-북부산#2T/L CB (7271)","서부산S/S 서부산-북부산#2T/L CB(7271) 보통점검","서부산S/S 서부산-북부산#2T/L GIS(7271) 보통점검","2015-09-23 10:00","2015-09-23 18:00","2015-09-23 10:00","2015-09-23 18:00","당일",null,null,null,201507140134,"-"]
[137,"부산울산","서부산","서부산S/S 서부산#2T/L-#1 M.Tr 1차 CB (7200)","서부산S/S 서부산#2T/L-#1 M.Tr 1차 CB(7200) 보통점검","서부산S/S 서부산#2T/L-#1 M.Tr 1차 GIS(7200) 보통점검","2015-09-21 10:00","2015-09-21 18:00","2015-09-21 10:00","2015-09-21 18:00","당일",null,null,null,201507140133,"-"]
[138,"부산울산","서부산","신김해신녹산#2 T/L","345kV 신녹산S/S #3M.Tr 증설공사","345kV M.Tr 1Bank 증설 시험가압","2015-09-23 16:00","2015-09-25 16:00","2015-09-23 16:00","2015-09-25 16:00","연속",null,null,null,201507140034,"-"]
[139,"부산울산","울산","신울산S/S #3 M.Tr A","2014-15년도 울산전력지사 변전협력회사 총액공사","M.Tr A상 하자점검, 6364 GCB 보통점검, 4384 VCB 보통점검","2015-09-23 08:00","2015-09-24 18:00","2015-09-23 08:00","2015-09-24 18:00","연속",null,null,null,201507130198,"○"]
[140,"부산울산","울산","신울산S/S #1 M.Tr A","주변압기 구조개선 공사","A상 구조개선, 7100,7172 GIS 초기점검","2015-09-08 08:00","2015-09-17 18:00","2015-09-08 08:00","2015-09-17 18:00","연속",null,null,null,201507130062,"-"]
[141,"부산울산","울산","신울산S/S 70-71 SEC CB (2388)","2014-15년도 울산전력지사 변전협력회사 총액공사","70-71-0 GIS 초기점검","2015-09-08 09:00","2015-09-08 18:00","2015-09-08 09:00","2015-09-08 18:00","당일",null,null,null,201507130190,"-"]
[142,"부산울산","울산","신울산S/S 75-76 SEC CB (2388)","2014-15년도 울산전력지사 변전협력회사 총액공사","75-76-0 GIS 초기점검","2015-09-09 09:00","2015-09-09 18:00","2015-09-09 09:00","2015-09-09 18:00","당일",null,null,null,201507130192,"○"]
[143,"부산울산","울산","울산C/C #3 M.Tr A","울산화력S/Y 154kV 보호제어설비 전담운영공사","제어케이블 수용, M.Tr 하자점검","2015-09-30 08:00","2015-10-02 18:00","2015-09-30 08:00","2015-10-02 18:00","연속",null,null,null,201507130207,"-"]
[144,"부산울산","울산","울산C/C 기력6호기 1차 CB (7672)","2014-15년도 울산전력지사 변전협력회사 총액공사","7672 GIS 하자점검","2015-09-11 09:00","2015-09-11 18:00","2015-09-11 09:00","2015-09-11 18:00","당일",null,null,null,201507130338,"-"]
[145,"부산울산","울산","울주월성NP#1 T/L","345kV 울주-월성NP T/L 피뢰기 설치공사","345kV 울주-월성NP T/L 피뢰기 설치공사 (1~79호)","2015-09-14 07:00","2015-09-23 18:00","2015-09-14 07:00","2015-09-23 18:00","연속",null,null,null,201507100047,"-"]
[146,"부산울산","직할","신대연S/S 345kV #1Sh.R","신대연S/S #1Sh.R 냉각팬 교체공사","#1Sh.R 냉각팬 교체","2015-09-02 09:00","2015-09-02 18:00","2015-09-02 09:00","2015-09-02 18:00","당일",null,null,null,201507080003,"-"]
[147,"부산울산","직할","신대연S/S #1M.Tr A","#1M.Tr 누유개소 보수 및 변압기 3차 전압계 회로 변경공사","#1M.Tr 누유개소 보수, 변압기 3차 전압계 회로 변경","2015-09-03 09:00","2015-09-03 18:00","2015-09-03 09:00","2015-09-03 18:00","당일",null,null,null,201507080004,"-"]
[148,"부산울산","직할","신대연S/S #2M.Tr A","신대연S/S #2M.Tr 86T3, 3차측 전압계 회로변경 공사","신대연S/S #2M.Tr 86T3 회로 변경, 3차측 전압계 회로변경","2015-09-04 09:00","2015-09-04 18:00","2015-09-04 09:00","2015-09-04 18:00","당일",null,null,null,201507080005,"-"]
[149,"경남","직할","신김해S/S 345kV #2 BUS","신김해S/S 345kV BUS-PRO PNL 교체","신김해S/S 345kV BUS-PRO PNL 교체(#2BUS용 교체)","2015-09-27 08:00","2015-09-28 17:30","2015-09-27 08:00","2015-09-28 17:30","연속",null,null,null,201507080046,"-"]
[150,"경남","직할","신김해북부산#1 T/L","안전이격확보 관련 휴전(154kV 신김해-주촌#1T/L)","안전이격확보 관련 휴전(154kV 신김해-주촌#1T/L 스페이서 간격조정 및 SB댐퍼 설치)-2014~15년 경남지역본부 직할 송전협력회사 총액공사","2015-09-19 14:00","2015-09-19 18:00","2015-09-19 14:00","2015-09-19 18:00","당일",null,null,null,201507090099,"-"]
[151,"경남","직할","신김해신녹산#1 T/L","안전이격확보 관련 휴전(154kV 신김해-주촌#1T/L)","안전이격확보 관련 휴전(154kV 신김해-주촌#1T/L 스페이서 간격조정 및 SB댐퍼 설치)-2014~15년 경남지역본부 직할 송전협력회사 총액공사","2015-09-19 14:00","2015-09-19 18:00","2015-09-19 14:00","2015-09-19 18:00","당일",null,null,null,201507090098,"-"]
[152,"경남","직할","신김해신녹산#2 T/L","안전이격확보 관련 휴전(154kV 신김해-주촌#1T/L)","안전이격확보 관련 휴전(154kV 신김해-주촌#1T/L 스페이서 간격조정 및 SB댐퍼 설치)-2014~15년 경남지역본부 직할 송전협력회사 총액공사","2015-09-19 08:00","2015-09-19 13:00","2015-09-19 08:00","2015-09-19 13:00","당일",null,null,null,201507090093,"-"]
[153,"경남","직할","신김해북부산#2 T/L","안전이격확보 관련 휴전(154kV 신김해-주촌#1T/L)","안전이격확보 관련 휴전(154kV 신김해-주촌#1T/L 스페이서 간격조정 및 SB댐퍼 설치)-2014~15년 경남지역본부 직할 송전협력회사 총액공사","2015-09-19 08:00","2015-09-19 13:00","2015-09-19 08:00","2015-09-19 13:00","당일",null,null,null,201507090095,"-"]
[154,"경남","통영","삼천포T/P #5 M.Tr 1차 CB (7571)","삼천포T/P #5 GEN 2차 CB(7571) 정밀점검","삼천포T/P #5 GEN 2차 CB(7571) 정밀점검","2015-09-09 09:30","2015-09-10 18:30","2015-09-09 09:30","2015-09-10 18:30","연속",null,null,null,201507070063,"-"]
[155,"경남","통영","삼천포T/P 신김해#1T/L-#5 M.Tr 1차 CB (7500)","삼천포T/P #5 GEN 2차 TIE CB(7500) 정밀점검","삼천포T/P #5 GEN 2차 TIE CB(7500) 정밀점검","2015-09-07 09:30","2015-09-08 18:30","2015-09-07 09:30","2015-09-08 18:30","연속",null,null,null,201507070062,"-"]
[156,"경남","통영","삼천포T/P 신마산#2T/L-#2 M.Tr 1차 CB (7200)","삼천포T/P #2 GEN 2차 TIE CB(7200) 정밀점검","삼천포T/P #2 GEN 2차 TIE CB(7200) 정밀점검","2015-09-14 09:30","2015-09-15 18:30","2015-09-14 09:30","2015-09-15 18:30","연속",null,null,null,201507070066,"-"]
[157,"경남","통영","삼천포T/P #2 M.Tr 1차 CB (7271)","삼천포T/P #2 GEN 2차 CB(7271) 정밀점검","삼천포T/P #2 GEN 2차 CB(7271) 정밀점검","2015-09-16 09:30","2015-09-17 18:30","2015-09-16 09:30","2015-09-17 18:30","연속",null,null,null,201507070067,"-"]
[158,"경남","함안","신마산S/S 의령#2T/L-삼천포화력#2T/L CB (7500)","신마산S/S 345kV 7500 GCB 정밀점검 공사","신마산S/S 345kV 7500 GCB 정밀점검 공사","2015-09-10 08:30","2015-09-12 17:30","2015-09-10 08:30","2015-09-12 17:30","연속",null,null,null,201507090241,"-"]
[159,"경남","함안","신마산S/S 신마산-삼천포화력#2T/L CB (7572)","신마산S/S 345kV 7572 GCB 정밀점검 공사","신마산S/S 345kV 7572 GCB 정밀점검 공사","2015-09-07 08:30","2015-09-09 17:30","2015-09-07 08:30","2015-09-09 17:30","연속",null,null,null,201507090240,"-"]
[160,"경남","함안","신마산S/S 신마산-신김해#2T/L CB (7372)","신마산S/S 345kV 7372 GCB 정밀점검 공사","신마산S/S 345kV 7372 GCB 정밀점검 공사","2015-09-01 09:30","2015-09-04 17:30","2015-09-01 09:30","2015-09-04 17:30","연속",null,null,null,201507090238,"-"]
[161,"경남","함안","신마산S/S 의령-신마산#2T/L CB (7571)","신마산S/S 345kV 7571 GCB 정밀점검 공사","신마산S/S 345kV 7571 GCB 정밀점검 공사","2015-09-14 08:30","2015-09-16 17:30","2015-09-14 08:30","2015-09-16 17:30","연속",null,null,null,201507090242,"-"]
[162,"경남","함안","신마산S/S 의령-신마산#1T/L CB (7472)","신마산S/S 345kV 7472 GCB 정밀점검 공사","신마산S/S 345kV 7472 GCB 정밀점검 공사","2015-09-17 08:30","2015-09-19 17:30","2015-09-17 08:30","2015-09-19 17:30","연속",null,null,null,201507090244,"-"]
[163,"경남","함안","신마산S/S 신김해#1T/L-의령#1T/L CB (7400)","신마산S/S 345kV 7400 GCB 정밀점검 공사","신마산S/S 345kV 7400 GCB 정밀점검 공사, A상 에어링밸브 교체","2015-09-21 08:30","2015-09-23 17:30","2015-09-21 08:30","2015-09-23 17:30","연속",null,null,null,201507090245,"-"]
[164,"경남","함안","신마산S/S 신마산-신김해#1T/L CB (7471)","신마산S/S 345kV 7471 GCB 정밀점검 공사","신마산S/S 345kV 7471 GCB 정밀점검 공사","2015-09-30 08:30","2015-10-02 17:30","2015-09-30 08:30","2015-10-02 17:30","연속",null,null,null,201507090246,"-"]

{"sheet":"154송부","index":2,"n_rows":295,"n_cols":16,"rows_kept":295,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2015년도 9월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","양주쌍문#1 T/L","154kV 양주쌍문T/L C/H PD 진단센서 설치공사","- 154kV 양주쌍문T/L 철탑형 쌍문C/H PD 실시간 진단센서 설치","2015-09-02 09:00","2015-09-02 18:00","2015-09-02 09:00","2015-09-02 18:00","당일",null,null,null,201507100181,"○"]
[2,"서울","성동","창동쌍문#1 T/L","15년 성동P/O 170kV GIS정밀점검(창동S/S 창동쌍문#1T/L)","15년 성동P/O 170kV GIS정밀점검(창동S/S 창동쌍문#1T/L)","2015-09-10 08:00","2015-09-11 18:00","2015-09-10 08:00","2015-09-11 18:00","연속",null,null,null,201507140145,"○"]
[3,"서울","성동","창동쌍문#2 T/L","15년 성동P/O 170kV GIS정밀점검(창동S/S 창동쌍문#2T/L)","15년 성동P/O 170kV GIS정밀점검(창동S/S 창동쌍문#2T/L)","2015-09-21 08:00","2015-09-22 18:00","2015-09-21 08:00","2015-09-22 18:00","연속",null,null,null,201507140147,"-"]
[4,"서울","중부","수색상암#1 T/L","15년 중부전력지사 장기사용 배전반 대체공사","수색(667), 상암(657) 수색상암#1T/L 배전반 대체공사","2015-09-01 10:00","2015-09-04 18:00","2015-09-01 10:00","2015-09-04 18:00","연속",null,null,null,201507080076,"-"]
[5,"서울","중부","수색상암#2 T/L","15년 중부전력지사 장기사용 배전반 대체공사","수색(677), 상암(667) 수색상암#2T/L 배전반 대체공사","2015-09-07 10:00","2015-09-10 18:00","2015-09-07 10:00","2015-09-10 18:00","연속",null,null,null,201507080077,"-"]
[6,"서울","중부","옥인운니#1 T/L","14~15년 중부P/O 변전협력회사 총액공사","옥인S/S 옥인운니#1 T/L (637) GIS 초기점검","2015-09-04 08:30","2015-09-04 17:00","2015-09-04 08:30","2015-09-04 17:00","연속",null,null,"신뢰도개선",201507080060,"-"]
[7,"서울","직할","서소문S/S 154kV #1 BUS","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S #1 M.Tr 1차 GIS 정밀점검","2015-09-10 09:00","2015-09-11 13:00","2015-09-10 09:00","2015-09-11 13:00","연속",null,null,null,201507090180,"-"]
[8,"서울","직할","서소문S/S 154kV #2 BUS","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S 순화서소문#1T/L GIS 정밀점검","2015-09-08 13:00","2015-09-09 18:00","2015-09-08 13:00","2015-09-09 18:00","연속",null,null,null,201507090186,"-"]
[9,"서울","직할","서소문S/S 154kV #1 BUS","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S 순화서소문#1T/L GIS 정밀점검","2015-09-07 09:00","2015-09-08 13:00","2015-09-07 09:00","2015-09-08 13:00","연속",null,null,null,201507090181,"-"]
[10,"서울","직할","서소문S/S 154kV #2 BUS","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S #1 M.Tr 1차 GIS 정밀점검","2015-09-11 13:00","2015-09-12 18:00","2015-09-11 13:00","2015-09-12 18:00","연속",null,null,null,201507090184,"-"]
[11,"서울","직할","서소문S/S 154kV #1 BUS","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S 순화서소문#2T/L GIS 정밀점검","2015-09-14 09:00","2015-09-15 13:00","2015-09-14 09:00","2015-09-15 13:00","연속",null,null,null,201507090179,"-"]
[12,"서울","직할","서소문S/S 154kV #2 BUS","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S 순화서소문#2T/L GIS 정밀점검","2015-09-15 13:00","2015-09-16 18:00","2015-09-15 13:00","2015-09-16 18:00","연속",null,null,null,201507090183,"-"]
[13,"서울","직할","중앙서소문 T/L","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S 중앙서소문T/L GIS 정밀점검","2015-09-17 09:00","2015-09-19 18:00","2015-09-17 09:00","2015-09-19 18:00","연속",null,null,null,201507090172,"-"]
[14,"서울","직할","서소문S/S 154kV #1 BUS","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S 중앙서소문T/L GIS 정밀점검","2015-09-17 09:00","2015-09-18 13:00","2015-09-17 09:00","2015-09-18 13:00","연속",null,null,null,201507090178,"-"]
[15,"서울","직할","서소문S/S 154kV #2 BUS","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S 중앙서소문T/L GIS 정밀점검","2015-09-18 13:00","2015-09-19 18:00","2015-09-18 13:00","2015-09-19 18:00","연속",null,null,null,201507090182,"-"]
[16,"서울","직할","서소문S/S 154kV #1 BUS","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S #1 B/T, #4 M.Tr 1차 GIS 정밀점검","2015-09-20 09:00","2015-09-22 09:00","2015-09-20 09:00","2015-09-22 09:00","연속",null,null,null,201507090176,"-"]
[17,"서울","직할","서소문S/S 154kV #1 BUS TIE CB","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S #1 B/T CB GIS 정밀점검","2015-09-20 09:00","2015-09-23 18:00","2015-09-20 09:00","2015-09-23 18:00","연속",null,null,null,201507090175,"-"]
[18,"서울","직할","서소문S/S 154kV #2 BUS","2015년 직할변전소 170kV GIS 정밀점검","서소문S/S #1 B/T, #4 M.Tr 1차 GIS 정밀점검","2015-09-22 09:00","2015-09-23 18:00","2015-09-22 09:00","2015-09-23 18:00","연속",null,null,null,201507090177,"-"]
[19,"서울","직할","연대신촌 T/L","신촌S/S 154kV 장기사용 GIS 대체","연대신촌T/L GIS 대체","2015-09-13 08:00","2015-10-02 18:00","2015-09-13 08:00","2015-10-02 18:00","연속",null,null,null,201507090028,"-"]
[20,"남서울","강남","신양재S/S 154kV #65 BUS","170kV GIS 정밀점검 (신양재S/S #65BUS 신양재-신사#2)","170kV GIS 정밀점검 (신양재S/S #65BUS 신양재-신사#2) ※ 계통시험팀 보호배전반 점검 병행 - 제어팀 PITR 점검","2015-09-09 08:00","2015-09-09 16:00","2015-09-02 13:00","2015-09-03 12:00","당일",null,null,null,201507080058,"-"]
[21,"남서울","강남","신양재신사#1 T/L","신양재-신사#1T/L 보호배전반 정기점검","신양재-신사#1T/L 보호배전반 정기점검","2015-09-08 09:00","2015-09-08 14:00","2015-09-08 09:00","2015-09-08 14:00","당일",null,null,null,201507140170,"-"]
[22,"남서울","강남","신양재S/S 154kV #60 BUS","170kV GIS 정밀점검 (신양재S/S #60BUS 신양재-신사#2)","170kV GIS 정밀점검 (신양재S/S #60BUS 신양재-신사#2T/L) - 보호배전반 점검 병행 - PITR 점검 병행","2015-09-09 16:00","2015-09-10 18:00","2015-09-03 12:00","2015-09-04 18:00","연속",null,null,null,201507080067,"-"]
[23,"남서울","강남","신양재신사#2 T/L","170kV GIS 정밀점검 (신양재S/S 신양재-신사#2T/L)","170kV GIS 정밀점검 (신양재S/S 신양재-신사#2T/L) ※ 계통시험팀 보호배전반 점검 병행 - 제어팀 PITR 점검","2015-09-08 14:00","2015-09-10 18:00","2015-09-02 10:00","2015-09-04 18:00","연속",null,null,null,201507080055,"-"]
[24,"남서울","강남","신양재S/S 154kV #60 BUS","170kV GIS 정밀점검 (신양재S/S #60BUS 6100 B/T)","170kV GIS 정밀점검 (신양재S/S #60BUS 6100 B/T)","2015-09-10 18:00","2015-09-11 10:00","2015-09-07 08:00","2015-09-08 14:00","연속",null,null,null,201507080059,"-"]
[25,"남서울","강남","신양재S/S 154kV #65 BUS","170kV GIS 정밀점검 (신양재S/S #65BUS 6100 B/T)","170kV GIS 정밀점검 (신양재S/S #65BUS 6100 B/T)","2015-09-11 10:00","2015-09-12 18:00","2015-09-08 14:00","2015-09-09 18:00","연속",null,null,null,201507080070,"-"]
[26,"남서울","강남","역삼대치#2 T/L","역삼S/S 170kV GIS 역삼-대치#2T/L 유압시스템 누유 보수","역삼S/S 170kV GIS 역삼-대치#2T/L 유압시스템 누유 보수 - 병행작업 : 보호배전반 정기점검 (계통시험팀)","2015-09-12 15:00","2015-09-13 18:00","2015-09-09 18:00","2015-09-10 18:00","당일",null,null,null,201507080209,"-"]
[27,"남서울","강남","역삼대치#1 T/L","역삼-대치#1T/L 보호배전반 정기점검","역삼-대치#1T/L 보호배전반 정기점검","2015-09-14 10:00","2015-09-14 14:00","2015-09-14 10:00","2015-09-14 14:00","당일",null,null,null,201507140111,"-"]
[28,"남서울","동서울","강동천호#1 T/L","강동-천호#1T/L 보호배전반 정기점검","강동-천호#1T/L 보호배전반 정기점검","2015-09-15 10:00","2015-09-15 14:00","2015-09-15 10:00","2015-09-15 14:00","당일",null,null,null,201507140101,"-"]
[29,"남서울","동서울","강동천호#2 T/L","강동-천호#2T/L 보호배전반 정기점검","강동-천호#2T/L 보호배전반 정기점검","2015-09-15 14:00","2015-09-15 18:00","2015-09-15 14:00","2015-09-15 18:00","당일",null,null,null,201507140102,"-"]
[30,"남서울","동서울","산성수서#1 T/L","154kV 산성-수서T/L 지중화공사","○ 공사시행 및 휴전요청자 : LH공사 ○ 선로명 : 154kV 산성-수서#1,2T/L ○ 구간 : 신설 C/H.16-1 〜 신설C/H.19 ○ 선종/길이 : 154kV XLPE 1,200㎟ × 2회선(D), 약 1.5km","2015-09-15 10:00","2015-09-24 16:00","2015-09-15 10:00","2015-09-24 16:00","연속",null,null,null,201507130339,"-"]
[31,"남서울","동서울","산성수서#2 T/L","154kV 산성-수서T/L 지중화공사","○ 공사시행 및 휴전요청자 : LH공사 ○ 선로명 : 154kV 산성-수서#1,2T/L ○ 구간 : 신설 C/H.16-1 〜 신설C/H.19 ○ 선종/길이 : 154kV XLPE 1,200㎟ × 2회선(D), 약 1.5km","2015-09-15 10:00","2015-09-24 16:00","2015-09-15 10:00","2015-09-24 16:00","연속",null,null,null,201507130340,"-"]
[32,"남서울","동서울","강동풍납#1 T/L","170KV GIS 정밀점검공사","170KV GIS 정밀점검공사 - 강동-풍납#1T/L","2015-09-07 08:00","2015-09-09 12:00","2015-09-07 08:00","2015-09-09 12:00","연속",null,null,null,201507090277,"-"]
[33,"남서울","동서울","강동풍납#2 T/L","170KV GIS 정밀점검공사","170KV GIS 정밀점검공사 - 강동-풍납#2T/L","2015-09-09 13:00","2015-09-11 17:00","2015-09-09 13:00","2015-09-11 17:00","연속",null,null,null,201507090296,"-"]
[34,"남서울","동서울","풍납석촌#1 T/L","풍납-석촌#1T/L 보호배전반 정기점검","풍납-석촌#1T/L 보호배전반 정기점검","2015-09-22 10:00","2015-09-22 14:00","2015-09-22 10:00","2015-09-22 14:00","당일",null,null,null,201507140166,"-"]
[35,"남서울","동서울","풍납석촌#2 T/L","풍납-석촌#2T/L 보호배전반 정기점검","풍납-석촌#2T/L 보호배전반 정기점검","2015-09-22 14:00","2015-09-22 18:00","2015-09-22 14:00","2015-09-22 18:00","당일",null,null,null,201507140167,"-"]
[36,"남서울","영서","가양등촌#2 T/L","가양S/S 장기사용 170kV GIS 대체공사","170kV GIS 5CCT 대체","2015-09-07 09:00","2015-10-11 18:00","2015-09-07 09:00","2015-10-11 18:00","연속",null,null,null,201507210025,"-"]
[37,"남서울","영서","독산대방#1 T/L","독산-대방#1T/L 보호배전반 정기점검","독산-대방#1T/L 보호배전반 정기점검","2015-09-02 10:00","2015-09-02 14:00","취소","취소","당일",null,null,null,201507140103,"-"]
[38,"남서울","영서","독산대방#2 T/L","독산-대방#2T/L 보호배전반 정기점검","독산-대방#2T/L 보호배전반 정기점검","2015-09-02 14:00","2015-09-02 18:00","취소","취소","당일",null,null,null,201507140106,"-"]
[39,"남서울","영서","사당봉천#1 T/L","사당-봉천#1T/L 보호배전반 정기점검","사당-봉천#1T/L 보호배전반 정기점검","2015-09-01 10:00","2015-09-01 14:00","2015-09-01 10:00","2015-09-01 14:00","당일",null,null,null,201507140164,"-"]
[40,"남서울","영서","사당봉천#2 T/L","사당-봉천#2T/L 보호배전반 정기점검","사당-봉천#2T/L 보호배전반 정기점검","2015-09-01 14:00","2015-09-01 18:00","취소","취소","당일",null,null,null,201507140165,"-"]
[41,"남서울","영서","시흥독산#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2015-09-03 10:00","2015-09-03 18:00","2015-09-03 10:00","2015-09-03 18:00","당일",null,null,null,201507100200,"-"]
[42,"남서울","영서","시흥독산#2 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2015-09-04 09:00","2015-09-04 18:00","2015-09-04 09:00","2015-09-04 18:00","당일",null,null,null,201507100199,"-"]
[43,"남서울","영서","영서시흥#1 T/L","170kV GIS 보통점검","- 시흥S/S 170kV GIS 보통점검 - 시흥S/S 154kV LA 보통점검 - 영서S/S 154kV LA 보통점검","2015-09-05 08:00","2015-09-05 14:00","2015-09-05 08:00","2015-09-05 14:00","당일",null,null,"신뢰도개선",201507200084,"-"]
[44,"남서울","영서","영서시흥#2 T/L","170kV GIS 보통점검","- 시흥S/S 170kV GIS 보통점검 - 시흥S/S 154kV LA 보통점검 - 영서S/S 154kV LA 보통점검 - 영서S/S GCB 초기점검","2015-09-05 14:00","2015-09-06 15:00","2015-09-05 14:00","2015-09-06 15:00","연속",null,null,"신뢰도개선",201507100208,"-"]
[45,"남서울","영서","영서소래 T/L","154kV 소래C/H 종단접속함 자기애관 교체공사","154kV 온수-소래T/L, 영서-소래T/L 소래C/H EBA 6개소 자기애관을 폴리머애관으로 대체","2015-09-07 09:00","2015-09-15 18:00","2015-09-07 09:00","2015-09-15 18:00","연속",null,null,null,201507090279,"-"]
[46,"남서울","영서","온수소래 T/L","154kV 소래C/H 종단접속함 자기애관 교체공사","154kV 온수-소래T/L, 영서-소래T/L 소래C/H EBA 6개소 자기애관을 폴리머애관으로 대체","2015-09-07 09:00","2015-09-15 18:00","2015-09-07 09:00","2015-09-15 18:00","연속",null,null,null,201507090278,"-"]
[47,"남서울","직할","봉천신길#1 T/L","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-09-07 09:00","2015-10-13 18:00","2015-09-07 09:00","2015-10-13 18:00","연속",null,null,null,201507100034,"-"]
[48,"남서울","직할","신길S/S 154kV #2 BUS","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-09-07 09:00","2015-09-13 18:00","2015-09-07 09:00","2015-09-13 18:00","연속",null,null,null,201507100035,"-"]
[49,"남서울","직할","신길S/S 154kV #1 BUS","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-09-14 09:00","2015-09-27 18:00","2015-09-14 09:00","2015-09-27 18:00","연속",null,null,null,201507100036,"-"]
[50,"남서울","직할","신길S/S 154kV #2 BUS","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-09-28 09:00","2015-10-11 18:00","2015-09-28 09:00","2015-10-11 18:00","연속",null,null,null,201507100038,"-"]
[51,"인천","김포","신김포양곡#2 T/L","양곡S/S 170kV 신김포양곡#2 T/L GIS 정밀점검공사","양곡S/S 170kV 신김포양곡#2 T/L GIS 정밀점검공사","2015-09-05 08:00","2015-09-06 18:00","2015-09-05 08:00","2015-09-06 18:00","연속",null,null,null,201507080180,"-"]
[52,"인천","김포","양촌양곡#1 T/L","154kV 양촌양곡T/L No.2 지장철탑 이설공사 (요청자 직접시행)","1. 배경 □ 김포학운4일반산업단지 조성사업에 지장이 되는 154kV 양촌-양곡T/L No.2 철탑 이설요청 2. 공사개요 및 현황 □ 지장물 : 154kV 양촌-양곡T/L No.2 □ 지지물 : 2기신설(관형지지물, 가철탑), 2기 철거 □ 전력선 : HSTACIR/AW 330㎟×S×2C , 0.511km","2015-09-01 07:00","2015-09-02 18:00","2015-09-01 07:00","2015-09-02 18:00","연속",null,null,null,201507100137,"-"]
[53,"인천","김포","양촌양곡#2 T/L","154kV 양촌양곡T/L No.2 지장철탑 이설공사 (요청자 직접시행)","1. 배경 □ 김포학운4일반산업단지 조성사업에 지장이 되는 154kV 양촌-양곡T/L No.2 철탑 이설요청 2. 공사개요 및 현황 □ 지장물 : 154kV 양촌-양곡T/L No.2 □ 지지물 : 2기신설(관형지지물,가철탑), 2기 철거 □ 전력선 : HSTACIR/AW 330㎟×S×2C , 0.511km","2015-09-03 07:00","2015-09-04 18:00","2015-09-03 07:00","2015-09-04 18:00","연속",null,null,null,201507100138,"-"]
[54,"인천","시흥","신시흥#2S/S 154kV #62 BUS","신시흥/S/S 62-63 SEC GIS 정밀점검","신시흥/S/S 62-63 SEC GIS 정밀점검","2015-09-02 09:30","2015-09-03 14:00","2015-09-02 09:30","2015-09-03 14:00","연속",null,null,null,201507070040,"-"]
[55,"인천","시흥","신시흥/S/S 62-63 SEC GIS","신시흥/S/S 62-63 SEC GIS 정밀점검","신시흥/S/S 62-63 SEC GIS 정밀점검","2015-09-02 09:30","2015-09-04 18:00","2015-09-02 09:30","2015-09-04 18:00","연속",null,null,null,201507070038,"-"]
[56,"인천","시흥","신시흥#2S/S 154kV #63 BUS","신시흥/S/S 62-63 SEC GIS 정밀점검","신시흥/S/S 62-63 SEC GIS 정밀점검","2015-09-03 14:00","2015-09-04 18:00","2015-09-03 14:00","2015-09-04 18:00","연속",null,null,null,201507070041,"-"]
[57,"인천","시흥","연수S/S 학익연수#2T/L GIS","연수S/S 학익연수#2T/L GIS 정밀점검","연수S/S 학익연수#2T/L GIS 정밀점검","2015-09-12 09:30","2015-09-14 18:00","2015-09-12 09:30","2015-09-14 18:00","연속",null,null,null,201507070034,"-"]
[58,"인천","시흥","연수S/S 학익연수#1T/L GIS","연수S/S 학익연수#1T/L GIS 정밀점검","연수S/S 학익연수#1T/L GIS 정밀점검","2015-09-09 09:30","2015-09-11 18:00","2015-09-09 09:30","2015-09-11 18:00","연속",null,null,null,201507070031,"-"]
[59,"인천","시흥","신시흥오봉 T/L","154kV 신시흥-오봉T/L 아킹혼 설치공사","154kV 신시흥-오봉T/L 아킹혼 설치공사(29기)","2015-09-01 09:00","2015-09-05 18:00","2015-09-01 09:00","2015-09-05 18:00","연속",null,null,null,201507020048,"-"]
[60,"인천","인천","서인천C/C #1 G.Tr 1차 GIS","서인천복합S/Y #1G.Tr 1차 GIS 보통점검","서인천복합S/Y #1G.Tr 1차 GIS 보통점검","2015-09-30 09:00","2015-09-30 18:00","2015-09-30 09:00","2015-09-30 18:00","당일",null,null,null,201507100142,"-"]
[61,"인천","인천","신가좌인천#2 T/L","154kV 주안-관교 등 4개 T/L 접지선 교체공사","접속함 중 기준이 변경된 접지선 150㎟ → 240㎟ 교체","2015-09-15 09:00","2015-09-23 18:00","2015-09-15 09:00","2015-09-23 18:00","연속",null,null,null,201506150267,"-"]
[62,"인천","직할","계양원창 T/L","345kV가정루원시티 지중화 정비공사","345kV 가정루원시티 지중화 정비공사 ※ 금번작업 : 신가좌-인천CC #2T/L 연긴선 해체 및 설치기간 휴 전(전선 긴선 해체에 따른 선간 단락으로 정전 방지) -신설:3기[4회선(345kV 신가좌-인천CC No.18),2회선 C/H(154kV, 345kV)] -교체:1기[345kV 신가좌-인천CC No.19 Enclosing 공법으로 철탑교체] -철거:20기[345kV 5기, 154kV 15기]","2015-09-09 09:00","2015-09-10 18:00","2015-09-09 09:00","2015-09-10 18:00","연속",null,null,"신뢰도개선",201507130197,"-"]
[63,"인천","직할","부개원미#2 T/L","장기 미동작 차단기 조작시행[부개원미#2T/L]","부개, 원미S/S 양단 부개원미#2T/L 차단기 조작시험 시행","2015-09-02 09:30","2015-09-02 18:00","2015-09-02 09:30","2015-09-02 18:00","당일",null,null,null,201507020082,"-"]
[64,"인천","직할","부개원미#1 T/L","장기 미동작 차단기 조작시행[부개원미#1T/L]","부개, 원미S/S 양단 부개원미#1T/L 차단기 조작시험 시행","2015-09-01 09:30","2015-09-01 18:00","2015-09-01 09:30","2015-09-01 18:00","당일",null,null,null,201507020081,"-"]
[65,"인천","직할","신부평부흥#1 T/L","장기 미동작 차단기 조작시행[신부평부흥#1T/L]","장기 미동작 차단기 조작시행[신부평부흥#1T/L]","2015-09-03 09:30","2015-09-03 14:00","2015-09-03 09:30","2015-09-03 14:00","당일",null,null,null,201507020083,"-"]
[66,"인천","직할","신부평부흥#2 T/L","장기 미동작 차단기 조작시행[신부평부흥#2T/L]","장기 미동작 차단기 조작시행[신부평부흥#2T/L]","2015-09-04 09:30","2015-09-04 14:00","2015-09-04 09:30","2015-09-04 14:00","당일",null,null,null,201507020084,"-"]
[67,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S #62M.Tr 1차 GIS 정밀점검","신부평S/S #62M.Tr 1차 GIS 정밀점검","2015-09-06 09:00","2015-09-06 18:00","2015-09-06 09:00","2015-09-06 18:00","연속",null,null,"신뢰도개선",201507070176,"-"]
[68,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S #62M.Tr 1차 GIS 정밀점검","신부평S/S #62M.Tr 1차 GIS 정밀점검","2015-09-05 09:00","2015-09-05 18:00","2015-09-05 09:00","2015-09-05 18:00","연속",null,null,"신뢰도개선",201507070175,"-"]
[69,"인천","직할","임학계양#2 T/L","임학S/S 170kV 임학-계양#2T/L GIS 정밀점검","임학S/S 170kV 임학-계양#2T/L GIS 정밀점검","2015-09-01 08:00","2015-09-03 18:00","2015-09-01 08:00","2015-09-03 18:00","연속",null,null,null,201507070158,"-"]
[70,"인천","직할","신부평중동#2 T/L","중동S/S 신부평-중동#2T/L GIS 정밀점검","중동S/S 신부평-중동#2T/L GIS 정밀점검","2015-09-17 08:00","2015-09-19 18:00","2015-09-17 08:00","2015-09-19 18:00","연속",null,null,null,201507070177,"-"]
[71,"인천","직할","신부평중동#1 T/L","중동S/S 신부평-중동#1T/L GIS 정밀점검","중동S/S 신부평-중동#1T/L GIS 정밀점검","2015-09-14 08:00","2015-09-16 18:00","2015-09-14 08:00","2015-09-16 18:00","연속",null,null,null,201507130131,"○"]
[72,"인천","직할","중동화곡#2 T/L","15년 가공송전정비 협력회사 총액공사","가공지선 교체공사","2015-09-05 09:00","2015-09-05 18:00","2015-09-05 09:00","2015-09-05 18:00","당일",null,null,"신뢰도개선",201507130304,"-"]
[73,"인천","직할","중동화곡#1 T/L","15년 가공송전정비 협력회사 총액공사","가공지선 교체공사","2015-09-05 09:00","2015-09-05 18:00","2015-09-05 09:00","2015-09-05 18:00","당일",null,null,"신뢰도개선",201507140052,"-"]
[74,"인천","직할","신부평중동#3 T/L","중동S/S 신부평-중동#3T/L GIS 정밀점검","중동S/S 신부평-중동#3T/L GIS 정밀점검","2015-09-21 08:00","2015-09-23 18:00","2015-09-21 08:00","2015-09-23 18:00","연속",null,null,null,201507070185,"-"]
[75,"경기북부","구리","가평춘천HP T/L","가평S/S 170kV 장기사용 GIS 대체공사 (1차 설치분)","170kV GIS × 8Bay (TL 4, M.Tr 2, BT 1, PT 1) 철거 설치","2015-09-01 09:00","2015-09-23 18:00","2015-09-01 09:00","2015-09-23 18:00","연속",null,null,"신뢰도개선",201507070140,"-"]
[76,"경기북부","구리","덕소별내#2 T/L","14-15년도 구리전력지사 변전협력회사 총액공사[170kV GIS]","- 170kV GCB 보통점검 및 주밸브 분해점검","2015-09-25 09:00","2015-09-25 18:00","2015-09-25 09:00","2015-09-25 18:00","당일",null,null,null,201507010033,"○"]
[77,"경기북부","구리","덕소별내#1 T/L","14-15년도 구리전력지사 변전협력회사 총액공사[170kV GIS]","- 170kV GCB 보통점검 및 주밸브 분해점검","2015-09-11 09:00","2015-09-11 18:00","2015-09-11 09:00","2015-09-11 18:00","당일",null,null,null,201507010032,"○"]
[78,"경기북부","직할","도봉방학#1 T/L","15년 직할 170kV GIS/GCB 정밀점검 공사","○ GCB 정밀 ○ LA, CVT 보통","2015-09-14 08:00","2015-09-15 20:00","2015-09-14 08:00","2015-09-15 20:00","연속",null,null,null,201408180319,"-"]
[79,"경기북부","직할","의정부도봉#2 T/L","15년 직할 170kV GIS/GCB 정밀점검 공사","○ GCB 정밀 ○ LA, CVT 보통","2015-09-16 08:00","2015-09-17 20:00","2015-09-16 08:00","2015-09-17 20:00","연속",null,null,null,201408180320,"-"]
[80,"경기북부","직할","별내도봉 T/L","15년 직할 170kV GIS/GCB 정밀점검 공사","○ GCB 정밀 ○ LA, CVT 보통","2015-09-09 08:00","2015-09-10 20:00","2015-09-09 08:00","2015-09-10 20:00","연속",null,null,null,201408180318,"○"]
[81,"경기북부","파주","양주금촌#1 T/L","2015년 하반기 파주전력 170kV GIS 정밀점검공사","금촌S/S 양주-금촌#1T/L GIS 정밀점검","2015-09-09 09:00","2015-09-11 18:00","2015-09-09 09:00","2015-09-11 18:00","당일",null,null,null,201506040093,"-"]
[82,"경기북부","파주","양주금촌#2 T/L","2015년 하반기 파주전력 170kV GIS 정밀점검공사","금촌S/S 양주-금촌#2T/L GIS 정밀점검","2015-09-17 09:00","2015-09-19 18:00","2015-09-17 09:00","2015-09-19 18:00","당일",null,null,null,201506040094,"-"]
[83,"경기북부","파주","신파주문발#1 T/L","154kV 신파주-문발#1T/L 초기점검","154kV 신파주-문발#1 T/L No.5 초기점검","2015-09-01 08:00","2015-09-01 18:00","2015-09-01 08:00","2015-09-01 18:00","당일",null,null,null,201506170051,"-"]
[84,"경기북부","파주","신파주문발#2 T/L","154kV 신파주-문발#2T/L 초기점검","154kV 신파주-문발#2 T/L No.5 초기점검","2015-09-02 08:00","2015-09-02 18:00","2015-09-02 08:00","2015-09-02 18:00","당일",null,null,null,201506170050,"-"]
[85,"경기북부","파주","일산S/S #6G/T GIS","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-09-13 09:00","2015-09-13 18:00","2015-09-13 09:00","2015-09-13 18:00","연속",null,null,null,201506050094,"-"]
[86,"경기북부","파주","일산S/S #2S/T GIS","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-09-12 09:00","2015-09-12 18:00","2015-09-12 09:00","2015-09-12 18:00","연속",null,null,null,201506050093,"-"]
[87,"경기북부","파주","일산S/S 154kV #66 BUS","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-09-09 09:00","2015-09-11 18:00","2015-09-09 09:00","2015-09-11 18:00","연속",null,null,null,201506050090,"-"]
[88,"경기북부","파주","일산S/S 154kV #61 BUS","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-09-07 09:00","2015-09-08 18:00","2015-09-07 09:00","2015-09-08 18:00","연속",null,null,null,201506050088,"-"]
[89,"경기북부","파주","양주일산#1 T/L","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-09-23 09:00","2015-09-24 18:00","2015-09-23 09:00","2015-09-24 18:00","연속",null,null,null,201506050099,"○"]
[90,"경기북부","파주","일산송포#1 T/L","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-09-21 09:00","2015-09-22 18:00","2015-09-21 09:00","2015-09-22 18:00","연속",null,null,null,201506050098,"-"]
[91,"경기북부","파주","일산S/S #5G/T GIS","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-09-19 09:00","2015-09-19 18:00","2015-09-19 09:00","2015-09-19 18:00","연속",null,null,null,201506050097,"-"]
[92,"경기북부","파주","일산송포#2 T/L","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-09-16 09:00","2015-09-17 18:00","2015-09-16 09:00","2015-09-17 18:00","연속",null,null,null,201506050096,"-"]
[93,"경기북부","파주","양주일산#2 T/L","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-09-14 09:00","2015-09-15 18:00","2015-09-14 09:00","2015-09-15 18:00","연속",null,null,null,201506050095,"○"]
[94,"경기","군포","남안산목내#1 T/L","남안산-목내TL 지장송전선로 이설공사","송산그린시티 관련 별망지하차도 건설을 위한 남안산-목내T/L M/H#10~J/B#11구간 지장송전선로 이설","2015-09-11 09:00","2015-09-23 18:00","2015-09-11 09:00","2015-09-23 18:00","연속",null,null,null,201507010091,"-"]
[95,"경기","군포","서안양소래 T/L","서안양S/S 서안양-소래T/L 보호PNL 교체공사","서안양S/S측 서안양-소래T/L 보호PNL 교체","2015-09-18 09:00","2015-09-21 18:00","2015-09-18 09:00","2015-09-21 18:00","연속",null,null,null,201507100071,"-"]
[96,"경기","군포","신시흥시화#1 T/L","15년 군포P/O 변전협력 총액공사_시화 신시흥시화#1","시화변전소 154kV 신시흥시화#1 LA 점검","2015-09-06 09:00","2015-09-06 13:00","2015-09-06 09:00","2015-09-06 13:00","당일",null,null,null,201504140181,"-"]
[97,"경기","군포","일동S/S 154kV #1 BUS","일동S/S 154kV #60Bus","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2, #3MTr 1차 GIS","2015-09-17 09:00","2015-09-17 18:00","2015-09-17 09:00","2015-09-17 18:00","연속",null,null,null,201507080163,"-"]
[98,"경기","군포","서서울일동#2 T/L","154kV 서서울일동#2TL GIS 대체공사","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2T/L GIS","2015-09-01 09:00","2015-09-18 18:00","2015-09-01 09:00","2015-09-18 18:00","연속",null,null,null,201507080149,"-"]
[99,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2, #3MTr 1차 GIS","2015-09-01 09:00","2015-09-03 18:00","2015-09-01 09:00","2015-09-03 18:00","연속",null,null,null,201507080153,"-"]
[100,"경기","군포","일동S/S 154kV #1 BUS","일동S/S 154kV #60Bus","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2, #3MTr 1차 GIS","2015-09-04 09:00","2015-09-10 18:00","2015-09-04 09:00","2015-09-10 18:00","연속",null,null,null,201507080159,"-"]
[101,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2, #3MTr 1차 GIS","2015-09-11 09:00","2015-09-16 18:00","2015-09-11 09:00","2015-09-16 18:00","연속",null,null,null,201507080160,"-"]
[102,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동S/S 154kV 장기사용 GIS교체공사 : 서서울일동#2, #3MTr 1차 GIS","2015-09-18 09:00","2015-09-18 18:00","2015-09-18 09:00","2015-09-18 18:00","연속",null,null,null,201507130321,"-"]
[103,"경기","군포","관양평촌#2 T/L","평촌S/S 154kV 관양평촌#2T/L 1차 GIS 교체공사","관양평촌#2 T/L GIS 교체공사","2015-09-01 09:00","2015-09-18 18:00","2015-09-01 09:00","2015-09-18 18:00","연속",null,null,null,201507060157,"-"]
[104,"경기","직할","서서울남수원#1 T/L","154kV 서서울-남수원T/L 15호 5기 안전이격확보공사","○ 철탑 계탑 5기(15,16,17,18,19호) ○ 전력선교체 : 14~20호간","2015-09-30 07:00","2015-10-09 19:00","2015-09-30 07:00","2015-10-09 19:00","연속",null,null,null,201507060103,"-"]
[105,"경기","직할","서서울남수원#2 T/L","154kV 서서울-남수원T/L 15호 5기 안전이격확보공사","○ 철탑 계탑 5기(15,16,17,18,19호) ○ 전력선교체 : 14~20호간","2015-09-30 07:00","2015-10-09 19:00","2015-09-30 07:00","2015-10-09 19:00","연속",null,null,null,201507060104,"-"]
[106,"경기","직할","율전의왕#2 T/L","154kV 율전의왕#2T/L 자기 피뢰기 교체공사","자기 재질피뢰기 3EA를 폴리머 재질 피뢰기로 교체","2015-09-21 09:00","2015-09-21 18:00","2015-09-21 09:00","2015-09-21 18:00","당일",null,null,"신뢰도개선",201507070061,"-"]
[107,"경기","직할","이의S/S 이의-열병합#2T/L CB","이의S/S 154kV 이의-열병합#2T/L CB","이의S/S 154kV 차단기 조작시험","2015-09-20 15:00","2015-09-20 17:00","2015-09-20 15:00","2015-09-20 17:00","당일",null,null,null,201507130175,"-"]
[108,"경기","직할","이의S/S 이의-열병합#1T/L CB","이의S/S 154kV 이의-열병합#1T/L CB","이의S/S 154kV 차단기 조작시험","2015-09-20 13:00","2015-09-20 15:00","2015-09-20 13:00","2015-09-20 15:00","당일",null,null,null,201507130174,"-"]
[109,"경기","직할","화성조암#1 T/L","154kV 화성조암#1T/L 송전선로 정밀점검(구간 No.1~39)","15년 가공송전선로 순시점검 위탁공사 154kV 화성조암#1T/L 송전선로 정밀점검(구간 No.1~39)","2015-09-12 07:00","2015-09-13 20:00","2015-09-12 07:00","2015-09-13 20:00","매일",null,null,null,201507090188,"-"]
[110,"경기","직할","화성발안#2 T/L","154kV 화성발안T/L 초기점검(구간 No.17~18)","- 공사명 : 154kV 화성발안T/L 초기점검 - 시행자 : 한전KPS 수원출장소","2015-09-06 09:00","2015-09-06 18:00","2015-09-06 09:00","2015-09-06 18:00","매일",null,null,null,201507100060,"-"]
[111,"경기","직할","화성발안#1 T/L","154kV 화성발안T/L 초기점검(구간 No.17~18)","- 공사명 : 154kV 화성발안T/L 초기점검 - 시행자 : 한전KPS 수원출장소","2015-09-05 09:00","2015-09-05 18:00","2015-09-05 09:00","2015-09-05 18:00","매일",null,null,null,201507100057,"-"]
[112,"경기","평택","송탄S/S 송탄-소사벌T/L(687) GIS","송탄S/S 154kV 송탄소사벌T/L GIS 대체 공사","송탄S/S 154kV 송탄소사벌T/L GIS 대체 공사","2015-09-16 09:00","2015-10-04 18:00","2015-09-16 09:00","2015-10-04 18:00","연속",null,null,null,201507090185,"-"]
[113,"경기","평택","청북평택#2 T/L","154kV 청북-평택#2T/L No.24 점퍼소켓 보수 및 안전확보","- 154kV 포승-청북#1T/L No.4,15 가공지선 철거 및 설치(하단 안전확보) - 154kV 포승-청북#1T/L No.9 점퍼소켓균열 보수(하단 안전확보) - 154kV 청북-평택#2T/L No.24 점퍼소켓균열 보수","2015-09-12 08:00","2015-09-13 18:00","2015-09-12 08:00","2015-09-13 18:00","매일",null,null,null,201507100190,"-"]
[114,"경기","평택","포승청북#2 T/L","154kV 포승-청북#2T/L No.33~35 소도체 이도 조정","- 154kV 포승-청북#2T/L No.33~35 소도체 이도불량 보수","2015-09-06 08:00","2015-09-06 18:00","2015-09-06 08:00","2015-09-06 18:00","당일",null,null,null,201507100205,"-"]
[115,"경기","평택","포승청북#1 T/L","154kV 포승-청북#1T/L No.4,15 가공지선 보수","- 154kV 포승-청북#1T/L No.4,15 가공지선 철거 및 설치 - 154kV 포승-청북#1T/L No.9 점퍼소켓균열 보수 - 154kV 청북-평택#2T/L No.24 점퍼소켓균열 보수","2015-09-12 08:00","2015-09-13 18:00","2015-09-12 08:00","2015-09-13 18:00","매일",null,null,null,201507100189,"-"]
[116,"강원","강릉","강릉횡계#1 T/L","154kV 강릉-횡계T/L 용량증대 전선교체공사","전선교체 : 2C-21.9km (ACSR 330㎟ → HSTACIR/AW 330㎟)","2015-09-01 08:00","2015-10-05 18:00","2015-09-01 08:00","2015-10-05 18:00","연속",null,null,null,201507140074,"-"]
[117,"강원","강릉","동해강릉 T/L","154kV 강릉-횡계T/L 용량증대 전선교체공사","전선교체 : 2C-21.9km (ACSR 330㎟ → HSTACIR/AW 330㎟)","2015-09-01 08:00","2015-09-05 18:00","2015-09-01 08:00","2015-09-05 18:00","연속",null,null,null,201507140087,"-"]
[118,"강원","동해","삼척동해TP T/L","2015년도 가공송전 순시점검 위탁공사","1.송전선로 정밀점검","2015-09-07 09:00","2015-09-11 18:00","2015-09-07 09:00","2015-09-11 18:00","매일",null,null,null,201507140182,"-"]
[119,"강원","동해","이원동해TP T/L","2015년도 가공송전 순시점검 위탁공사","1.송전선로 정밀점검","2015-09-14 09:00","2015-09-17 18:00","2015-09-14 09:00","2015-09-17 18:00","매일",null,null,null,201507140179,"-"]
[120,"강원","동해","이원삼척 T/L","2015년도 가공송전 순시점검 위탁공사","1.송전선로 정밀점검","2015-09-21 09:00","2015-09-24 18:00","2015-09-21 09:00","2015-09-24 18:00","매일",null,null,null,201507140178,"-"]
[121,"강원","원주","신제천남원주#2 T/L","154kV 남원주-원주간 OPGW 교체공사","- OPGW(OP-S-L48) : 8.52km 교체","2015-09-07 08:00","2015-09-09 18:00","2015-09-07 08:00","2015-09-09 18:00","연속",null,null,null,201507130334,"-"]
[122,"강원","원주","남원주원주#1 T/L","154kV 남원주-원주간 OPGW 교체공사","-OPGW(OP-S-L48) 8.52km 교체","2015-09-07 08:00","2015-09-13 18:00","2015-09-07 08:00","2015-09-13 18:00","연속",null,null,null,201507130337,"-"]
[123,"강원","원주","원주북원주#1 T/L","원주-횡성구간 천연가스 주배관 볼밸브 교체(가스공사 작업)","작업내용 : 원주~횡성구간 천연가스 주배관 볼밸브 교체 (천연가스 방산작업 시행) 시행주관 : 한국가스공사","2015-09-05 08:00","2015-09-06 20:00","2015-09-05 08:00","2015-09-06 20:00","매일",null,null,null,201507140188,"-"]
[124,"강원","원주","원주북원주#2 T/L","원주-횡성구간 천연가스 주배관 볼밸브 교체(가스공사 작업)","작업내용 : 원주~횡성구간 천연가스 주배관 볼밸브 교체 (천연가스 방산작업 시행) 시행주관 : 한국가스공사","2015-09-05 08:00","2015-09-06 20:00","2015-09-05 08:00","2015-09-06 20:00","매일",null,null,null,201507140194,"-"]
[125,"강원","직할","남춘천청평PP T/L","2015년 가공송전선로 순시점검 위탁공사","정밀점검","2015-09-14 09:00","2015-09-16 18:00","취소","취소","매일",null,null,null,201507140230,"-"]
[126,"강원","직할","남춘천서홍천 T/L","2015년 가공송전선로 순시점검 위탁공사","정밀점검","2015-09-18 09:00","2015-09-20 18:00","2015-09-21 09:00","2015-09-23 18:00","매일",null,null,null,201507140233,"-"]
[127,"강원","직할","북춘천춘천HP T/L","현장기술개발과제 시제품 현장 설치 및 정비대상개소 정비","외물접촉 고장 방지용 전력선 식별용 유도전원형 Multi 전력선 표시등구 설치 및 정비대상개소 정비","2015-09-24 09:00","2015-09-24 18:00","취소","취소","당일",null,null,null,201506160144,"-"]
[128,"강원","직할","서홍천청평PP T/L","2015년 가공송전선로 순시점검 위탁공사","정밀점검","2015-09-17 09:00","2015-09-17 18:00","취소","취소","당일",null,null,null,201507140232,"-"]
[129,"강원","직할","화천화천HP#2 T/L","화천H/P 154kV 화천화천HP #2T/L GCB 대체공사","- 화천화천HP #2T/L GCB 대체","2015-09-21 09:00","2015-09-24 18:00","2015-09-21 09:00","2015-09-24 18:00","연속",null,null,null,201507140226,"-"]
[130,"충북","직할","신제천주진#1 T/L","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 154kV GIS 28CCT 설치, 옥외설비 철거 - 154kV T-BUS 철거 (154kV GIS 설치공간 확보, 철거시 안전거리 확보)","2015-09-24 09:00","2015-09-24 18:00","2015-09-24 09:00","2015-09-24 18:00","당일",null,null,null,201507210059,"-"]
[131,"충북","직할","신제천왕암#1 T/L","2015년 가공송전선로 순시점검 위탁공사","위탁회사 : 송전선로 정밀점검 협력회사 - SB댐퍼 14기 설치 - 조류퇴치방지장치 10기 설치","2015-09-12 08:00","2015-09-13 18:00","2015-09-12 08:00","2015-09-13 18:00","매일",null,null,null,201507090230,"-"]
[132,"충북","직할","신제천-영월CC#2 T/L","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 154kV GIS 28CCT 설치, 옥외설비 철거 - 154kV T-BUS 철거 (154kV GIS 설치공간 확보, 철거시 안전거리 확보)","2015-09-17 09:00","2015-09-17 18:00","2015-09-17 09:00","2015-09-17 18:00","당일",null,null,null,201507200053,"-"]
[133,"충북","직할","신제천-영월CC#1 T/L","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 154kV GIS 28CCT 설치, 옥외설비 철거 - 154kV T-BUS 철거 (154kV GIS 설치공간 확보, 철거시 안전거리 확보)","2015-09-18 09:00","2015-09-18 18:00","2015-09-18 09:00","2015-09-18 18:00","당일",null,null,null,201507200054,"-"]
[134,"충북","직할","신제천주진#2 T/L","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 154kV GIS 28CCT 설치, 옥외설비 철거 - 154kV T-BUS 철거 (154kV GIS 설치공간 확보, 철거시 안전거리 확보)","2015-09-23 09:00","2015-09-23 18:00","2015-09-23 09:00","2015-09-23 18:00","당일",null,null,null,201507210058,"-"]
[135,"충북","직할","신제천남원주#1 T/L","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 154kV GIS 28CCT 설치, 옥외설비 철거 - 154kV T-BUS 철거 (154kV GIS 설치공간 확보, 철거시 안전거리 확보)","2015-09-22 09:00","2015-09-22 18:00","2015-09-22 09:00","2015-09-22 18:00","당일",null,null,null,201507130170,"-"]
[136,"충북","직할","신제천남원주#2 T/L","345kV 신제천S/S GIS화 공사","- 345kV FACAS 설비공간확보, 154kV GIS 28CCT 설치, 옥외설비 철거 - 154kV T-BUS 철거 (154kV GIS 설치공간 확보, 철거시 안전거리 확보)","2015-09-21 09:00","2015-09-21 18:00","2015-09-21 09:00","2015-09-21 18:00","당일",null,null,null,201507130169,"-"]
[137,"충북","직할","신제천왕암#2 T/L","2015년 가공송전선로 순시점검 위탁공사","송전위탁 : 송전선로 정밀점검 송전협력 - SB댐퍼 14기 설치 - 조류퇴치방지장치 10기 설치","2015-09-19 08:00","2015-09-20 18:00","2015-09-19 08:00","2015-09-20 18:00","매일",null,null,null,201507090232,"-"]
[138,"충북","청주","청원죽림#2 T/L","청원S/S 154kV 전류제한리액터 설치공사","○ 154kV GIS(GIB) 설치 × 1식 ○ 보호배전반 설치(대체) × 2면(청원1면, 죽림1면) ○ 기타 부대공사 × 1식 ※ 9/3 ~ 9/6 CLR 설치 안전이격 확보(매일) - 9/3~9/4 : 청원청주#3T/L- 청원죽림#2T/L 동시휴전 - 9/5~9/6 : 청원죽림#2T/L- 청원죽림#1T/L 동시휴전 ※ 9/7~9/13 GIS Docking 및 무부하(48H), 실부하가압(9/13)후 정상운전","2015-09-03 08:00","2015-09-13 18:00","2015-09-03 08:00","2015-09-13 18:00","연속",null,null,null,201507130107,"-"]
[139,"충북","청주","청원죽림#1 T/L","청원S/S 154kV 전류제한리액터 설치공사","○ CLR(2.85Ω, 1695A) 설치 × 1조(154kV 청원-죽림 #1T/L) ○ CLR 1,2차 모선설지(154kV 청원-죽림 #1T/L) ○ 기타 부대공사 × 1식 ※ 9/5~9/6 청원-죽림#2T/L 및 청원-죽림#1T/L 동시휴전(매일)","2015-09-05 08:00","2015-09-06 18:00","2015-09-05 08:00","2015-09-06 18:00","매일",null,null,null,201507130185,"-"]
[140,"충북","청주","청원죽림#1 T/L","청원S/S 154kV 전류제한리액터 설치공사","○ 154kV GIS(GIB) 설치 × 1식 ○ 보호배전반 설치(대체) × 2면(청원1면, 죽림1면) ○ 기타 부대공사 × 1식 ※ 무부하가압(48H) 및 실부하(9/20) 가압후 정상운전","2015-09-14 08:00","2015-09-20 18:00","2015-09-14 08:00","2015-09-20 18:00","연속",null,null,null,201507130109,"-"]
[141,"대전충남","대전","신계룡가수원#2 T/L","○ 154kV 신계룡-가수원 #2T/L CB 보통점검","신계룡-가수원 #2T/L CB 보통점검","2015-09-15 09:00","2015-09-15 18:00","2015-09-15 09:00","2015-09-15 18:00","당일",null,null,null,201507210054,"-"]
[142,"대전충남","대전","신계룡가수원#1 T/L","○ 154kV 신계룡-가수원 #1T/L CB 보통점검 및 누유개소 정비","신계룡-가수원 #1T/L CB 보통점검 및 누유개소 정비","2015-09-14 09:00","2015-09-14 18:00","2015-09-14 09:00","2015-09-14 18:00","당일",null,null,null,201507210053,"-"]
[143,"대전충남","대전","신옥천S/S 154kV #61 BUS","○ 신옥천S/S 장기사용 345kV #1M.Tr 교체공사","○ 신옥천S/S 345kV #1M.Tr 대체공사 - 345kV #1M.TR 철거.설치(단상 x 3대). - 무부하 시험 및 사용전 검사 등","2015-09-21 10:00","2015-09-23 18:00","2015-09-21 10:00","2015-09-23 18:00","연속",null,null,null,201506010039,"-"]
[144,"대전충남","서산","대산석문#1 T/L","154kV 대산-석문T/L 전선접속개소 전력선 교체공사","No.23~27 전선접소개소 전력선 교체[송전]","2015-09-04 07:30","2015-09-07 18:00","취소","취소","연속",null,null,null,201507200044,"-"]
[145,"대전충남","서산","대산석문#2 T/L","154kV 대산-석문T/L 전선접속개소 전력선 교체공사","No.23~27 전선접소개소 전력선 교체[송전]","2015-09-01 07:30","2015-09-03 18:00","취소","취소","연속",null,null,null,201507200042,"-"]
[146,"대전충남","서산","서산태안화력 T/L","154kV 태안T/L 전선접속개소 전력선 교체공사","[송전]태안/T/L 전선접속개소 전력선 교체 -전력선교체 -스페이서철거 및 설치 -SB댐퍼 철거 및 설치","2015-09-08 08:00","2015-09-17 18:00","2015-09-01 08:00","2015-09-09 18:00","연속",null,null,null,201507140046,"-"]
[147,"대전충남","서산","서산태안 T/L","154kV 태안T/L 전선접속개소 전력선 교체공사","[송전]태안/T/L 전선접속개소 전력선 교체 -전력선교체 -스페이서철거 및 설치 -SB댐퍼 철거 및 설치","2015-09-18 08:00","2015-10-02 18:00","2015-09-11 08:00","2015-09-25 18:00","연속",null,null,null,201507140042,"-"]
[148,"대전충남","서산","태안안면#1 T/L","태안S/S 170kV 장기사용 GIS 대체공사","○ 170KV GIS 대체(태안안면#1T/L,#1M.Tr GIS 철거)","2015-09-01 09:00","2015-09-26 18:00","2015-09-01 09:00","2015-09-26 18:00","연속",null,null,null,201507200093,"-"]
[149,"대전충남","아산","신온양한샘#2 T/L","154kV 신온양-한샘#2T/L GIS 터미널 단자블럭 교체","○단자블럭 불량에 따른 신온양,한샘S/S 154kV 신온양-한샘#2T/L GIS 터미널 단자블럭 교체","2015-09-02 09:00","2015-09-02 18:00","2015-09-02 09:00","2015-09-02 18:00","당일",null,null,null,201507100247,"-"]
[150,"대전충남","아산","신온양한샘#1 T/L","154kV 신온양-한샘#1T/L GIS 터미널 단자블럭 교체","○단자블럭 불량에 따른 신온양,한샘S/S 154kV 신온양-한샘#1T/L GIS 터미널 단자블럭 교체","2015-09-01 09:00","2015-09-01 18:00","2015-09-01 09:00","2015-09-01 18:00","당일",null,null,null,201507100246,"-"]
[151,"대전충남","아산","천안전의#2 T/L","154kV 천안-전의#2T/L 영인제 송전선로 보호반 성능개선","○천안,전의S/S 154kV 천안-전의#2T/L 영인제 송전선로 보호반 성능개선","2015-09-08 09:00","2015-09-08 18:00","2015-09-09 09:00","2015-09-09 18:00","당일",null,null,null,201507100252,"-"]
[152,"대전충남","아산","천안전의#1 T/L","154kV 천안-전의#1T/L 영인제 송전선로 보호반 성능개선","○천안,전의S/S 154kV 천안-전의#1T/L 영인제 송전선로 보호반 성능개선","2015-09-07 09:00","2015-09-07 18:00","2015-09-07 09:00","2015-09-07 18:00","당일",null,null,null,201507100251,"-"]
[153,"대전충남","아산","신탕정탕정#2 T/L","탕정S/S 154kV 신탕정-탕정#2T/L GIS 보통점검","○탕정S/S 154kV 신탕정-탕정#2T/L GIS 보통점검","2015-09-18 09:00","2015-09-18 18:00","2015-09-18 09:00","2015-09-18 18:00","당일",null,null,null,201507130144,"-"]
[154,"대전충남","아산","신탕정탕정#1 T/L","탕정S/S 154kV 신탕정-탕정#1T/L GIS 보통점검","○탕정S/S 154kV 신탕정-탕정#1T/L GIS 보통점검","2015-09-17 09:00","2015-09-17 18:00","2015-09-17 09:00","2015-09-17 18:00","당일",null,null,null,201507130142,"-"]
[155,"대전충남","직할","신풍공주#1 T/L","154kV 신풍-공주#1T/L 보호반 교체","○ 154kV 신풍-공주#1T/L 보호배전반 대체","2015-09-08 09:00","2015-09-10 18:00","2015-09-08 09:00","2015-09-10 18:00","연속",null,null,null,201507140036,"-"]
[156,"대전충남","직할","부강월산#1 T/L","154kV부강-월산T/L 애자교체 공사","No.7,24,26,30,35 애자교체","2015-09-01 09:00","2015-09-01 18:00","2015-09-01 09:00","2015-09-01 18:00","당일",null,null,null,201507170005,"○"]
[157,"대전충남","직할","부강월산#2 T/L","154kV부강-월산T/L 애자교체 공사","No.7,24,26,30,35 애자교체","2015-09-02 09:00","2015-09-02 18:00","2015-09-02 09:00","2015-09-02 18:00","당일",null,null,null,201507170006,"-"]
[158,"전북","군산","군산S/S 65-66-0 SEC CB","154kV 군산S/S 65-66-0 SEC CB","군산P/O 노후배전반 대체공사(154kV #60-65BUS 모선보호반 교체) 1. 군산S/S 154kV #60-65BUS 모선보호반 대체","2015-09-14 09:00","2015-09-18 18:00","2015-09-14 09:00","2015-09-18 18:00","연속",null,null,null,201507060090,"-"]
[159,"전북","군산","군산S/S 154kV #1 BUS TIE CB","군산S/S 154kV #1 BUS TIE CB","군산P/O 노후배전반 대체공사(154kV #60-65BUS 모선보호반 교체) 1. 군산S/S 154kV #60-65BUS 모선보호반 대체","2015-09-14 09:00","2015-09-18 18:00","취소","취소","연속",null,null,null,201507060088,"-"]
[160,"전북","군산","군산S/S 60-61-0 SEC CB","154kV 군산S/S 60-61-0 SEC CB","군산P/O 노후배전반 대체공사(154kV #60-65BUS 모선보호반 교체) 1. 군산S/S 154kV #60-65BUS 모선보호반 대체","2015-09-14 09:00","2015-09-18 18:00","2015-09-14 09:00","2015-09-18 18:00","연속",null,null,null,201507060089,"-"]
[161,"전북","군산","이리백산#1 T/L","154kV 이리-백산 #1T/L","154kV 이리-전주 등 2개T/L 지장철탑이설공사 154kV 이리-백산 #1T/L 임시선로 구성 (기설5, 6호→가철탑2기)","2015-09-23 08:00","2015-09-24 18:00","2015-09-23 08:00","2015-09-24 18:00","연속",null,null,null,201505120243,"-"]
[162,"전북","군산","이리백산#2 T/L","154kV 이리-백산 #2T/L","154kV 이리-전주 등 2개T/L 지장철탑이설공사 154kV 이리-전주, 이리-백산 #2T/L 휴전작업 ○ 기설 전력선 철거 : 이리-전주#2 2~7호, 이리-백산#2 2~8호 ○ 신설 철도 건설개소 노반 항타기 작업 : 철도시설관리공단측 작업 ○ 기설 철탑 철거 : 이리-전주 4,5,6호, 이리-백산 4,5,6호 ○ 신설 철탑 설치 : 이리-전주 4,5,6호, 이리-백산 4,5,6호 ○ 신설 전","2015-09-25 08:00","2015-11-23 18:00","2015-09-25 08:00","2015-11-23 18:00","연속",null,null,null,201505120246,"-"]
[163,"전북","군산","이리전주#2 T/L","154kV 이리-전주#2T/L","154kV 이리-전주 등 2개T/L 지장철탑이설공사 154kV 이리-전주, 이리-백산 #2T/L 휴전작업 ○ 기설 전력선 철거 : 이리-전주#2 2~7호, 이리-백산#2 2~8호 ○ 신설 철도 건설개소 노반 항타기 작업 : 철도시설관리공단측 작업 ○ 기설 철탑 철거 : 이리-전주 4,5,6호, 이리-백산 4,5,6호 ○ 신설 철탑 설치 : 이리-전주 4,5,6호, 이리-백산 4,5,6호 ○ 신설 전","2015-09-25 08:00","2015-11-23 18:00","2015-09-25 08:00","2015-11-23 18:00","연속",null,null,null,201505120245,"-"]
[164,"전북","김제","백산김제#2 T/L","154kV 백산-김제#2 T/L","154kV 백산-김제T/L 초기점검 154kV 백산-김제T/L 초기점검 - No.1~15","2015-09-24 09:00","2015-09-24 18:00","2015-09-24 09:00","2015-09-24 18:00","당일",null,null,null,201506260003,"-"]
[165,"전북","김제","백산김제#1 T/L","154kV 백산-김제#1 T/L","154kV 백산-김제T/L 초기점검 154kV 백산-김제T/L 초기점검 - No.1~15","2015-09-25 09:00","2015-09-25 18:00","2015-09-25 09:00","2015-09-25 18:00","당일",null,null,null,201506260002,"-"]
[166,"전북","김제","정공정주#2 T/L","154kV 정공-정주#2 T/L","154kV 정공-정주 등 3개T/L 전선접속개소 해소공사 가. 공사구간 정공-정주T/L No.10~11(4회선병가), 20~30호 정공분기T/L No.10~11(4회선병가), 13~16호 정주부안T/L No.10~11(4회선병가), 18~20, 60~67호 나. 전선교체 ACSR330 x 2B 0.32km, ACSR330xS 3.281km ACSR410xS 2.914km","2015-09-12 08:00","2015-09-18 18:00","2015-09-12 08:00","2015-09-18 18:00","연속",null,null,null,201507160023,"-"]
[167,"전북","김제","정공담양 T/L","154kV 정공-담양 T/L","154kV 정공-정주 등 3개T/L 전선접속개소 해소공사 가. 공사구간 정공-정주T/L No.10~11(4회선병가), 20~30호 정공분기T/L No.10~11(4회선병가), 13~16호 정주부안T/L No.10~11(4회선병가), 18~20, 60~67호 나. 전선교체 ACSR330 x 2B 0.32km, ACSR330xS 3.281km ACSR410xS 2.914km","2015-09-12 08:00","2015-09-15 18:00","2015-09-12 08:00","2015-09-15 18:00","연속",null,null,null,201507160021,"○"]
[168,"전북","김제","정공정주#1 T/L","154kV 정공-정주#1 T/L","154kV 정공-정주 등 3개T/L 전선접속개소 해소공사 가. 공사구간 정공-정주T/L No.10~11(4회선병가), 20~30호 정공분기T/L No.10~11(4회선병가), 13~16호 정주부안T/L No.10~11(4회선병가), 18~20, 60~67호 나. 전선교체 ACSR330 x 2B 0.32km, ACSR330xS 3.281km ACSR410xS 2.914km","2015-09-05 08:00","2015-09-11 18:00","2015-09-05 08:00","2015-09-11 18:00","연속",null,null,null,201507160020,"-"]
[169,"전북","김제","정공섬진강수력 T/L","154kV 정공-섬진강수력 T/L","154kV 정공-정주 등 3개T/L 전선접속개소 해소공사 가. 공사구간 정공-정주T/L No.10~11(4회선병가), 20~30호 정공분기T/L No.10~11(4회선병가), 13~16호 정주부안T/L No.10~11(4회선병가), 18~20, 60~67호 나. 전선교체 ACSR330 x 2B 0.32km, ACSR330xS 3.281km ACSR410xS 2.914km","2015-09-05 08:00","2015-09-06 18:00","2015-09-05 08:00","2015-09-06 18:00","연속",null,null,null,201507160018,"○"]
[170,"전북","김제","정주고창#2 T/L","154kV 정주-고창#2 T/L","154kV 정공-정주 등 3개T/L 전선접속개소 해소공사 정주-부안#2T/L 4회선병가구간 안전이격거리 확보 가. 공사구간 정공-정주T/L No.10~11(4회선병가), 20~30호 정공분기T/L No.10~11(4회선병가), 13~16호 정주부안T/L No.10~11(4회선병가), 18~20, 60~67호","2015-09-02 08:00","2015-09-03 18:00","2015-09-03 08:00","2015-09-04 18:00","연속",null,null,null,201507160049,"-"]
[171,"전북","직할","북전주S/S 154kV #1 BUS","북전주S/S 154kV #1 BUS","북전주S/S 170kV 장기사용 GIS 대체공사 *노후설비 적기보강을 통한 설비 신뢰도 제고를 위한 170kV GIS 대체공사 가. GIS(170kV 50kA 2000A BUS TIE) * 1CCT, 대체 나. GIS(170kV 50kA 2000A T/L) * 2CCT, 대체 다. GIS(170kV BUS P.T) * 1CCT, 대체 라. Bas","2015-09-04 09:00","2015-09-15 18:00","2015-09-04 09:00","2015-09-15 18:00","연속",null,null,null,201507060167,"-"]
[172,"전북","직할","북전주S/S 154kV #2 BUS","북전주S/S 154kV #2 BUS","북전주S/S 170kV 장기사용 GIS 대체공사 *노후설비 적기보강을 통한 설비 신뢰도 제고를 위한 170kV GIS 대체공사 가. GIS(170kV 50kA 2000A BUS TIE) * 1CCT, 대체 나. GIS(170kV 50kA 2000A T/L) * 2CCT, 대체 다. GIS(170kV BUS P.T) * 1CCT, 대체 라. Bas","2015-09-16 09:00","2015-09-25 18:00","2015-09-16 09:00","2015-09-25 18:00","연속",null,null,null,201507060168,"-"]
[173,"전북","직할","북전주S/S #2 M.Tr","북전주S/S #2 M.Tr","북전주S/S 170kV 장기사용 GIS 대체공사 *노후설비 적기보강을 통한 설비 신뢰도 제고를 위한 170kV GIS 대체공사 가. GIS(170kV 50kA 2000A BUS TIE) * 1CCT, 대체 나. GIS(170kV 50kA 2000A T/L) * 2CCT, 대체 다. GIS(170kV BUS P.T) * 1CCT, 대체 라. Base Channel 및 안전점검대 * 1식, 대체","2015-09-04 09:00","2015-09-25 18:00","취소","취소","연속",null,null,null,201507140050,"-"]
[174,"광주전남","강진","진도C/S #1 C.Tr","진도C/S #1C.Tr 교체공사","진도C/S #1C.Tr 교체(서제주 예비C.Tr)","2015-09-20 09:00","2015-11-09 18:00","2015-09-20 09:00","2015-11-09 18:00","연속",null,null,null,201507080261,"-"]
[175,"광주전남","강진","해남진도#1 T/L","154kV 해남진도#1T/L(화원-진도T/L 건설공사)","154kV 화원-진도T/L 건설공사 1. 공사목적 : #2HVDC AC배후계통 보강 및 진도S/S 이중전원 확보 2. 공사개요 가. 철 탑 : 37기 나. 전력선 : ACSR/AW 410㎟ × 2B 14.5km 3. 공사지역 : 해남군 문내면, 진도군 군내면 일원","2015-09-16 08:00","2015-09-20 18:00","2015-09-21 08:00","2015-09-25 18:00","연속",null,null,null,201507150029,"-"]
[176,"광주전남","강진","해남진도#1 T/L","154kV 해남-진도#1 T/L(화원-진도T/L 건설공사)","154kV 화원-진도T/L 건설공사 1. 공사목적 : #2HVDC AC배후계통 보강 및 진도S/S 이중전원 확보 2. 공사개요 가. 철 탑 : 37기 나. 전력선 : ACSR/AW 410㎟ × 2B 14.5km 3. 공사지역 : 해남군 문내면, 진도군 군내면 일원","2015-09-24 08:00","2015-09-25 18:00","2015-10-05 08:00","2015-10-06 18:00","연속",null,null,null,201507150033,"-"]
[177,"광주전남","강진","화원진도 T/L","154kV 화원-진도 T/L(화원-진도T/L 건설공사)","154kV 화원-진도T/L 건설공사 1. 공사목적 : #2HVDC AC배후계통 보강 및 진도S/S 이중전원 확보 2. 공사개요 가. 철 탑 : 37기 나. 전력선 : ACSR/AW 410㎟ × 2B 14.5km 3. 공사지역 : 해남군 문내면, 진도군 군내면 일원","2015-09-21 08:00","2015-09-23 18:00","2015-10-02 08:00","2015-10-04 18:00","연속",null,null,null,201507150027,"-"]
[178,"광주전남","광주","담양S/S 154kV #1 BUS","담양 154kV #1BUS(15년 광주 154kV GIS 정밀점검)","담양S/S #1Sh.C GIS #1DS부 정밀점검","2015-09-01 09:00","2015-09-02 09:00","2015-08-31 09:00","2015-09-01 09:00","연속",null,null,null,201507060216,"-"]
[179,"광주전남","광주","담양S/S 154kV #2 BUS","담양 154kV #2BUS(15년 광주 154kV GIS 정밀점검)","담양S/S #1Sh.C GIS #2DS부 정밀점검","2015-09-02 09:00","2015-09-02 18:00","2015-09-01 09:00","2015-09-01 18:00","당일",null,null,null,201507060217,"-"]
[180,"광주전남","광주","담양김제 T/L","담양-김제T/L(15년 광주 154kV GIS 정밀점검)","담양S/S 담양-김제T/L GIS CB부 정밀점검 담양S/S 피뢰기-카운터 연결선 교체(협력회사총액공사)","2015-09-03 09:00","2015-09-05 18:00","2015-09-02 09:00","2015-09-04 18:00","연속",null,null,"신뢰도개선",201507060218,"-"]
[181,"광주전남","광주","담양S/S 154kV #1 BUS","담양 154kV #1BUS(15년 광주 154kV GIS 정밀점검)","담양S/S 담양-김제T/L GIS #1DS부 정밀점검","2015-09-03 09:00","2015-09-04 09:00","2015-09-02 09:00","2015-09-03 09:00","연속",null,null,null,201507060219,"-"]
[182,"광주전남","광주","담양S/S 154kV #2 BUS","담양 154kV #2BUS(15년 광주 154kV GIS 정밀점검)","담양S/S 담양-김제T/L GIS #2DS부 정밀점검","2015-09-04 09:00","2015-09-05 09:00","2015-09-03 09:00","2015-09-04 09:00","연속",null,null,null,201507060220,"-"]
[183,"광주전남","순천","순천승주#2 T/L","순천-승주#2T/L(안전거리확보공사)","345kV 신남원-광양 등 2개T/L 안전이격확보공사 - 철탑교체 : 2기(No.166,167호)","2015-09-20 09:00","2015-09-22 18:00","2015-08-29 09:00","2015-08-30 18:00","연속",null,null,null,201507140243,"-"]
[184,"광주전남","순천","순천승주#1 T/L","순천-승주#1T/L(안전거리확보공사)","345kV 신남원-광양 등 2개T/L 안전이격확보공사 - 철탑교체 : 2기(No.166,167호)","2015-09-17 09:00","2015-09-19 18:00","2015-08-27 09:00","2015-08-28 18:00","연속",null,null,"신뢰도개선",201507140242,"-"]
[185,"광주전남","순천","여천여수#1 T/L","여수S/S 여천-여수#1T/L(170kV GIS 정밀점검공사)","하반기 순천전력지사 170kV GIS 정밀점검공사 - 여수S/S 여천-여수#1T/L GIS 정밀점검 15년 순천변전협력회사 총액공사 - 여천S/S 여천-여수#1T/L LA 교체","2015-09-10 09:00","2015-09-12 18:00","2015-09-10 09:00","2015-09-12 18:00","연속",null,null,null,201507140177,"-"]
[186,"광주전남","순천","여천S/S 60-61 SEC GIS","여천S/S 60-61SEC GIS(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사 - 여천S/S #60-65 BUS-PRO 교체","2015-09-01 09:00","2015-09-04 18:00","2015-08-31 09:00","2015-09-03 18:00","연속",null,null,null,201507140216,"-"]
[187,"광주전남","순천","여천여수#2 T/L","여천S/S 여천-여수#2T/L(170kV GIS 정밀점검공사)","하반기 순천전력지사 170kV GIS 정밀점검공사 - 여천S/S 여천-여수#2T/L GIS 정밀점검 15년 순천변전협력회사 총액공사 - 여천S/S측 LA 교체 - 여수S/S측 GIS 보통, LA 보통","2015-09-14 09:00","2015-09-16 18:00","2015-09-14 09:00","2015-09-16 18:00","연속",null,null,null,201507140184,"-"]
[188,"광주전남","순천","여천S/S 154kV #60 BUS","여천S/S 154kV #60BUS(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사 - 여천S/S #60-65 BUS-PRO 교체관련 시험","2015-09-04 15:00","2015-09-04 18:00","취소","취소","연속",null,null,null,201507140221,"-"]
[189,"광주전남","순천","여천S/S 154kV #65 BUS","여천S/S 154kV #65BUS(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사 - 여천S/S #60-65 BUS-PRO 교체관련 시험","2015-09-04 15:00","2015-09-04 18:00","취소","취소","연속",null,null,null,201507140222,"-"]
[190,"광주전남","순천","여천S/S 154kV #1 BUS TIE GIS","여천S/S 154kV #1BUS TIE GIS(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사 - 여천S/S #60-65 BUS-PRO 교체","2015-09-01 09:00","2015-09-04 18:00","취소","취소","연속",null,null,null,201507140220,"-"]
[191,"광주전남","순천","여천호남TP#1 T/L","여천-호남TP#1T/L(154kV 조상설비 대체공사)","여천S/S 154kV 조상설비 대체공사 - #1,2Sh.C 교체관련 시험가압","2015-09-07 09:00","2015-09-13 09:00","2015-09-07 09:00","2015-09-13 09:00","연속",null,null,null,201506160183,"-"]
[192,"광주전남","순천","여천S/S 65-66 SEC GIS","여천S/S 65-66SEC GIS(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사 - 여천S/S #60-65 BUS-PRO 교체","2015-09-01 09:00","2015-09-04 18:00","2015-08-31 09:00","2015-09-03 18:00","연속",null,null,null,201507140217,"-"]
[193,"광주전남","순천","율촌-여수산단#2 T/L","율촌-여수산단#2T/L(변전협력회사 총액공사)","15년 변전협력회사 총액공사 - 율촌변전소측 GIS 초기점검, 여수산단측 GIS 초기점검","2015-09-08 14:00","2015-09-09 18:00","2015-09-05 14:00","2015-09-06 18:00","매일",null,null,null,201506150228,"-"]
[194,"광주전남","순천","율촌-여수산단#1 T/L","율촌-여수산단#1T/L(변전협력회사 총액공사)","15년 변전협력회사 총액공사 - 율촌변전소측 GIS 초기점검, 여수산단측 GIS 초기점검","2015-09-07 10:00","2015-09-08 13:00","2015-09-04 10:00","2015-09-05 13:00","매일",null,null,null,201506150227,"-"]
[195,"광주전남","순천","호남TP여수TP#2 T/L","호남화력 ESS용 GIS설치공사(모선연결 및 무부하가압)","1.170kV GIS * 1CCT 2. 인접BAY 감압 및 모선 무부하가압용(9.17~9.19, 9.23~9.25)","2015-09-27 09:00","2015-10-08 18:00","2015-09-27 09:00","2015-10-08 18:00","연속",null,null,null,201507150062,"-"]
[196,"광주전남","순천","호남TP여수TP#2 T/L","호남화력 ESS용 GIS설치공사(안전이격거리확보)","170kV GIS * 1CCT","2015-09-14 09:00","2015-09-21 18:00","2015-09-14 09:00","2015-09-21 18:00","연속",null,null,null,201507150058,"-"]
[197,"광주전남","직할","남광주S/S 154kV #1 BUS TIE CB","남광주S/S 154kV #1BUS TIE CB(6100)","'14-15년 직할 변전협력회사 총액공사 - 남광주S/S 154kV 모선보호반 대체","2015-09-07 09:00","2015-09-10 18:00","2015-09-07 09:00","2015-09-10 18:00","당일",null,null,null,201507140124,"-"]
[198,"대구경북","구미","남인동인동#2 T/L","154kV 남인동-인동T/L 지장송전선로 이설공사","O No. 18 : 철탑 철거, 관형지지물 설치(1기), No.19~22 : 전력선 교체","2015-09-16 09:00","2015-09-20 18:00","2015-09-16 09:00","2015-09-20 18:00","연속",null,null,null,201507090167,"-"]
[199,"대구경북","구미","남인동인동#1 T/L","154kV 남인동-인동T/L 지장송전선로 이설공사","O No.18 : 철탑철거, 관형지지물 설치(1기), No. 19~22 : 전력선 교체","2015-09-21 09:00","2015-09-25 18:00","2015-09-21 09:00","2015-09-25 18:00","연속",null,null,null,201507090171,"-"]
[200,"대구경북","달성","논공유가#2 T/L","154kV현풍분기T/L 건설공사","논공-유가T/L No.18 철거 및 현풍분기T/L No.1 조립 및 가선 현풍, 유가 논공S/S 보호반 설치, 무부하가압(9/22)","2015-09-09 08:00","2015-09-25 18:00","2015-09-09 08:00","2015-09-25 18:00","연속",null,null,null,201507080148,"-"]
[201,"대구경북","달성","고령논공#1 T/L","논공S/S170kV GIS화 공사","O 154kV 송전선로 절체(옥외철구설비 GIS로 대체) - 인출변경(보강용 빔설치, 지중EBA 연결) - 송전선로 보호반 이설 및 시험 - 인출 단로기 철거(옥외철구) - 기타 부대작업","2015-09-05 12:00","2015-09-06 18:00","2015-09-05 12:00","2015-09-06 18:00","연속",null,null,null,201507060117,"-"]
[202,"대구경북","달성","논공달성#1 T/L","논공S/S170kV GIS화 공사","O 154kV 송전선로 절체(옥외철구설비 GIS로 대체) - 인출변경(보강용 빔설치, 지중EBA 연결) - 송전선로 보호반 이설 및 시험 - 인출 단로기 철거(옥외철구) - 기타 부대작업","2015-09-04 08:00","2015-09-05 12:00","2015-09-04 08:00","2015-09-05 12:00","연속",null,null,null,201507060116,"-"]
[203,"대구경북","달성","다산강창#1 T/L","다산 모선보호반교체공사","모선보호반교체공사","2015-09-12 10:00","2015-09-12 10:30","2015-09-12 10:00","2015-09-12 10:30","당일",null,null,null,201507150024,"-"]
[204,"대구경북","달성","고령다산#2 T/L","다산 모선보호반교체공사","모선보호반교체공사","2015-09-12 11:00","2015-09-12 11:30","2015-09-12 11:00","2015-09-12 11:30","당일",null,null,null,201507150025,"-"]
[205,"대구경북","달성","고령다산#1 T/L","다산 모선보호반교체공사","모선보호반교체공사","2015-09-12 13:00","2015-09-12 13:30","2015-09-12 13:00","2015-09-12 13:30","당일",null,null,null,201507150026,"-"]
[206,"대구경북","달성","다산강창#2 T/L","다산 모선보호반교체공사","모선보호반교체공사","2015-09-12 09:00","2015-09-12 09:30","2015-09-12 09:00","2015-09-12 09:30","당일",null,null,null,201507150022,"-"]
[207,"대구경북","달성","두류봉덕#1 T/L","차단기 점검,전자변교체","차단기점검","2015-09-15 09:00","2015-09-15 18:00","2015-09-15 09:00","2015-09-15 18:00","당일",null,null,null,201507060040,"-"]
[208,"대구경북","달성","두류봉덕#2 T/L","차단기 점검,전자변교체","차단기점검","2015-09-16 09:00","2015-09-16 18:00","2015-09-16 09:00","2015-09-16 18:00","당일",null,null,null,201507060041,"-"]
[209,"대구경북","달성","대구봉덕#2 T/L","봉덕S/S 모선보호반교체공사","모선보호반교체공사 1식","2015-09-10 14:30","2015-09-10 15:00","2015-09-10 14:30","2015-09-10 15:00","당일",null,null,null,201507150015,"-"]
[210,"대구경북","달성","두류봉덕#1 T/L","봉덕S/S 모선보호반교체공사","모선보호반교체공사 1식","2015-09-10 13:30","2015-09-10 14:00","2015-09-10 13:30","2015-09-10 14:00","당일",null,null,null,201507150014,"-"]
[211,"대구경북","달성","두류봉덕#2 T/L","봉덕S/S 모선보호반교체공사","모선보호반교체공사 1식","2015-09-10 13:00","2015-09-10 13:30","2015-09-10 13:00","2015-09-10 13:30","당일",null,null,null,201507150013,"-"]
[212,"대구경북","달성","상인봉덕#2 T/L","봉덕S/S 모선보호반교체공사","모선보호반교체공사 1식","2015-09-10 10:30","2015-09-10 11:00","2015-09-10 10:30","2015-09-10 11:00","당일",null,null,null,201507150011,"-"]
[213,"대구경북","달성","상인봉덕#1 T/L","봉덕S/S 모선보호반교체공사","모선보호반교체공사 1식","2015-09-10 10:00","2015-09-10 10:30","2015-09-10 10:00","2015-09-10 10:30","당일",null,null,null,201507150010,"-"]
[214,"대구경북","달성","대구봉덕#1 T/L","봉덕S/S 모선보호반교체공사","모선보호반교체공사 1식","2015-09-10 15:30","2015-09-10 16:00","2015-09-10 15:30","2015-09-10 16:00","당일",null,null,null,201507150016,"-"]
[215,"대구경북","달성","고령쌍림#1 T/L","154kV 고령-쌍림T/L 송전선로 정밀점검공사","정밀점검 52기 고령-다산 병가구간 SB댐퍼 설치","2015-09-07 08:00","2015-09-09 18:00","2015-09-07 08:00","2015-09-09 18:00","매일",null,null,null,201507070121,"-"]
[216,"대구경북","달성","쌍림합천#2 T/L","154kV 쌍림-합천T/L 송전선로 정밀점검","정밀점검 19기","2015-09-23 09:00","2015-09-24 18:00","2015-09-23 09:00","2015-09-24 18:00","연속",null,null,null,201507070124,"-"]
[217,"대구경북","달성","쌍림합천#1 T/L","154kV 쌍림-합천T/L 송전선로 정밀점검","정밀점검 19기","2015-09-21 09:00","2015-09-22 18:00","2015-09-21 09:00","2015-09-22 18:00","연속",null,null,null,201507070123,"-"]
[218,"대구경북","달성","고령쌍림#2 T/L","154kV 고령-쌍림T/L 송전선로 정밀점검 공사","정밀점검 52기 고령다산 병가구간 SB댐퍼 설치","2015-09-10 08:00","2015-09-12 18:00","2015-09-10 08:00","2015-09-12 18:00","매일",null,null,null,201507070122,"-"]
[219,"대구경북","안동","안동안동HP T/L","안동S/S 안동-안동HPT/L 철구철거,보호반 이설공사(GIS화)","- 안동-안동HPT/L 옥외철구 철거 및 임시송전선 철거 - T/L인출철구 ~ GIS측 철구간 가공송전선 배선 - T/L보호PNL 및 LA 이설 등","2015-09-10 08:00","2015-09-12 18:00","2015-09-10 08:00","2015-09-12 18:00","연속",null,null,null,201506270010,"-"]
[220,"대구경북","안동","신영주안동#2 T/L","안동S/S 신영주-안동2T/L 철구철거,보호반 이설공사(GIS화)","- 신영주-안동#2T/L 옥외철구 철거 및 임시송전선 철거 - T/L인출철구 ~ GIS측 철구간 가공송전선 배선 - T/L보호PNL 및 LA 이설 등","2015-09-04 08:00","2015-09-06 18:00","2015-09-04 08:00","2015-09-06 18:00","연속",null,null,null,201506270008,"-"]
[221,"대구경북","안동","신영주안동#1 T/L","안동S/S 신영주-안동1T/L 철구철거,보호반 이설공사 (GIS화)","- 신영주-안동#1T/L 옥외철구 철거 및 임시송전선 철거 - T/L인출철구 ~ GIS측 철구간 가공송전선 배선 - T/L보호PNL 및 LA 이설 등","2015-09-01 08:00","2015-09-03 18:00","2015-09-01 08:00","2015-09-03 18:00","연속",null,null,null,201506270007,"-"]
[222,"대구경북","영주","예천점촌#1 T/L","점촌S/S 예천-점촌#1T/L 장기사용 GIS 대체공사","점촌S/S 예천-점촌#1T/L 장기사용 GIS 대체공사","2015-09-10 08:00","2015-09-24 13:00","2015-09-10 08:00","2015-09-24 13:00","연속",null,null,null,201507070154,"-"]
[223,"대구경북","직할","공평서침산 T/L","공평-서침산T/L 보호반 교체","공평, 서침산S/S 공평-서침산T/L 보호반 교체","2015-09-18 09:00","2015-09-20 18:00","2015-09-18 09:00","2015-09-20 18:00","연속",null,null,null,201507080249,"-"]
[224,"대구경북","칠곡","칠곡S/S 154kV #1 Sh.C","154kV #1Sh.C GIS 대체","154kV #1Sh.C GIS 대체","2015-09-01 09:30","2015-09-14 18:00","2015-09-01 09:30","2015-09-14 18:00","연속",null,null,null,201507090153,"-"]
[225,"대구경북","포항","옥동외동#2 T/L","외동S/S 외동-옥동#2T/L 휴전작업","공기조작부 에어링벨브 누기 보수","2015-09-15 10:00","2015-09-15 14:00","2015-09-15 10:00","2015-09-15 14:00","당일",null,null,null,201507090034,"-"]
[226,"대구경북","포항","외동S/S 154kV #1 BUS TIE CB","외동S/S 6100 BUS TIE GIS 휴전작업","#2DS 전자변 누기보수","2015-09-15 14:00","2015-09-15 18:00","2015-09-15 14:00","2015-09-15 18:00","당일",null,null,null,201507090036,"-"]
[227,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV 6100 GIS 정밀점검 시험가압선로","서창S/S 170kV GIS 정밀점검 시험가압선로 정밀점검 대상 : 서창S/S 6100 GIS #1DS","2015-09-15 17:00","2015-09-15 18:00","2015-09-15 17:00","2015-09-15 18:00","당일",null,null,null,201507100092,"-"]
[228,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV 6100 GIS 정밀점검 시험가압선로","서창S/S 170kV GIS 정밀점검 시험가압선로 정밀점검 대상 : 서창S/S 6100 GIS #2DS","2015-09-16 17:00","2015-09-16 18:00","2015-09-16 17:00","2015-09-16 18:00","당일",null,null,null,201507100094,"-"]
[229,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV 6333 GIS 정밀점검 시험가압선로","서창S/S 170kV GIS 정밀점검 시험가압선로 정밀점검 대상 : 서창S/S #3M.Tr 1차 6333 GIS #1DS","2015-09-18 17:00","2015-09-18 18:00","2015-09-18 17:00","2015-09-18 18:00","당일",null,null,null,201507100095,"-"]
[230,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV 6333 GIS 정밀점검 시험가압선로","서창S/S 170kV GIS 정밀점검 시험가압선로 정밀점검 대상 : 서창S/S #3M.Tr 1차 6333 GIS #2DS","2015-09-19 17:00","2015-09-19 18:00","2015-09-19 17:00","2015-09-19 18:00","당일",null,null,null,201507100096,"-"]
[231,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV 6433 GIS 정밀점검 시험가압선로","서창S/S 170kV GIS 정밀점검 시험가압선로 정밀점검 대상 : 서창S/S #4M.Tr 1차 6433 GIS #1DS","2015-09-22 17:00","2015-09-22 18:00","2015-09-22 17:00","2015-09-22 18:00","당일",null,null,null,201507100099,"-"]
[232,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV 6433 GIS 정밀점검 시험가압선로","서창S/S 170kV GIS 정밀점검 시험가압선로 정밀점검 대상 : 서창S/S #4M.Tr 1차 6433 GIS #2DS","2015-09-23 17:00","2015-09-23 18:00","2015-09-23 17:00","2015-09-23 18:00","당일",null,null,null,201507100100,"-"]
[233,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV 웅촌-서창#1T/L GIS(647) 정밀점검","서창S/S 170kV 647 GIS 정밀점검 정밀점검 대상 : 서창S/S 웅촌-서창#1T/L 647 GIS","2015-09-30 09:00","2015-10-02 18:00","2015-09-30 09:00","2015-10-02 18:00","연속",null,null,null,201507100102,"-"]
[234,"부산울산","동부산","웅촌서창#2 T/L","154kV 웅촌-서창#2T/L 지장철탑이설공사(요청자 시행)","가선로 구성, 14~17.1호, 3기설치, 3기철거","2015-09-24 09:00","2015-09-24 18:00","2015-09-24 09:00","2015-09-24 18:00","당일",null,null,null,201507150180,"-"]
[235,"부산울산","북부산","구포S/S 154kV #2 BUS","구포S/S #2M.Tr 1차 GIS 정밀점검","#2 DS, 정밀점검 및 시험가압","2015-09-11 12:00","2015-09-12 18:00","2015-09-11 12:00","2015-09-12 18:00","연속",null,null,null,201507130282,"○"]
[236,"부산울산","북부산","구포S/S 154kV #1 BUS","구포S/S #2M.Tr 1차 GIS 정밀점검","#2M.Tr #1,6 DS, CB 정밀점검 및 시험가압","2015-09-10 09:00","2015-09-11 12:00","2015-09-10 09:00","2015-09-11 12:00","연속",null,null,null,201507130281,"○"]
[237,"부산울산","북부산","구포S/S 154kV #2 BUS","구포S/S #1M.Tr 1차 GIS 정밀점검","#2 DS, 정밀점검 및 시험가압","2015-09-08 12:00","2015-09-09 18:00","2015-09-08 12:00","2015-09-09 18:00","연속",null,null,null,201507130279,"○"]
[238,"부산울산","북부산","구포S/S 154kV #1 BUS","구포S/S #1M.Tr 1차 GIS 정밀점검","#1M.Tr #1,6 DS, CB 정밀점검 및 시험가압","2015-09-07 09:00","2015-09-08 12:00","2015-09-07 09:00","2015-09-08 12:00","연속",null,null,null,201507130277,"○"]
[239,"부산울산","북부산","북부산구포#1 T/L","2015년도 시스전압제한기(SVL) 교체공사","구형 시스전압제한기(SVL) 신형으로 교체","2015-09-15 09:00","2015-09-15 18:00","2015-09-15 09:00","2015-09-15 18:00","당일",null,null,null,201507080227,"○"]
[240,"부산울산","북부산","북부산호포#1 T/L","154kV 호포분기T/L 건설공사","○ 신설 154kV 호포분기T/L No.1 잠바 설치 - 계통변경 : 북부산-물금, 북부산-호포 #1 → 호포-물금 ○ 신설 154kV 호포분기T/L No.5~6구간 가선작업 ○ 기설 154kV 호포T/L No.8~호포S/S 구간 가선작업","2015-09-05 07:00","2015-09-06 19:00","2015-09-05 07:00","2015-09-06 19:00","연속",null,null,null,201507060012,"-"]
[241,"부산울산","북부산","북부산양산 T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:1호-105호(41기) SB댐퍼 설치:1호-10호(10기)","2015-09-17 07:00","2015-09-19 18:00","2015-09-17 07:00","2015-09-19 18:00","연속",null,null,null,201506220085,"-"]
[242,"부산울산","북부산","북부산물금 T/L","154kV 호포분기T/L 건설공사","○ 신설 154kV 호포분기T/L No.1 잠바 설치 - 계통변경 : 북부산-물금, 북부산-호포 #1 → 호포-물금","2015-09-05 07:00","2015-09-06 19:00","2015-09-05 07:00","2015-09-06 19:00","연속",null,null,null,201507060011,"-"]
[243,"부산울산","북부산","북부산삼랑진PP#2 T/L","154kV 호포분기T/L 건설공사","○ 신설 154kV 호포분기T/L No.1 잠바 설치관련 안전이격","2015-09-05 07:00","2015-09-06 19:00","2015-09-05 07:00","2015-09-06 19:00","연속",null,null,null,201507060013,"-"]
[244,"부산울산","북부산","북부산호포#2 T/L","154kV 호포분기T/L 건설공사","○ 신설 154kV 호포분기T/L No.1 잠바 설치(기설치) - 계통변경 : 북부산-물금(운휴), 북부산-호포 #2 → 북부산-호포 ○ 신설 154kV 호포분기T/L No.5~6구간 가선작업 ○ 기설 154kV 호포T/L No.8~호포S/S 구간 가선작업","2015-09-07 07:00","2015-09-08 19:00","2015-09-07 07:00","2015-09-08 19:00","연속",null,null,null,201507060014,"-"]
[245,"부산울산","북부산","북부산삼랑진PP#1 T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:1호-105호(41기) SB댐퍼 설치:1호-10호(10기) 74호 애자교체","2015-09-14 07:00","2015-09-16 18:00","2015-09-14 07:00","2015-09-16 18:00","연속",null,null,null,201506220084,"○"]
[246,"부산울산","북부산","서창산막#2 T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:1호-72호(40기)","2015-09-12 07:00","2015-09-13 18:00","2015-09-12 07:00","2015-09-13 18:00","연속",null,null,null,201506220038,"-"]
[247,"부산울산","북부산","서창산막#1 T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:1호-72호(40기)","2015-09-05 07:00","2015-09-06 18:00","2015-09-05 07:00","2015-09-06 18:00","연속",null,null,null,201506220037,"-"]
[248,"부산울산","북부산","주촌삼계#2 T/L","삼계S/S 154kV #1,2Sh.C 설치공사","154kV #1,2Sh.C 최초가압","2015-09-21 10:00","2015-09-23 10:00","2015-09-21 10:00","2015-09-23 10:00","연속",null,null,null,201507070113,"-"]
[249,"부산울산","북부산","삼계김해 T/L","삼계-김해T/L PNL 대체","삼계-김해T/L PNL 대체","2015-09-11 09:00","2015-09-13 18:00","2015-09-11 09:00","2015-09-13 18:00","연속",null,null,null,201507130289,"-"]
[250,"부산울산","북부산","양산산막#2 T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:1호-7호(7기) 및 11호 피뢰기 설치","2015-09-09 07:00","2015-09-10 18:00","2015-09-09 07:00","2015-09-10 18:00","연속",null,null,null,201506220044,"-"]
[251,"부산울산","북부산","양산산막#1 T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:1호-7호(7기) 안전이격 확보","2015-09-09 07:00","2015-09-09 18:00","2015-09-09 07:00","2015-09-09 18:00","연속",null,null,null,201506220043,"-"]
[252,"부산울산","북부산","양산삼랑진PP T/L","15년 가공송전 협력업체 공사","조류착지방지장치설치:63호-105호(8기)","2015-09-21 07:00","2015-09-21 18:00","2015-09-21 07:00","2015-09-21 18:00","연속",null,null,null,201506220086,"-"]
[253,"부산울산","서부산","서부산부산 T/L","345kV 서부산-북부산T/L 등 8개T/L 이설공사","154kV XLPE 2000㎟ 케이블 0.177km 이설","2015-09-11 08:00","2015-09-30 18:00","2015-09-11 08:00","2015-09-30 18:00","연속",null,null,null,201507130254,"-"]
[254,"부산울산","울산","용연울산TP#1 T/L","2014~2015 울산전력처 송전정비 협력회사 총액공사","154kV 용연-울산TP#1,2T/L 애자교체 공사","2015-09-22 07:00","2015-09-23 18:00","2015-09-22 07:00","2015-09-23 18:00","연속",null,null,null,201507130387,"-"]
[255,"부산울산","울산","용연울산TP#2 T/L","2014~2015 울산전력처 송전정비 협력회사 총액공사","154kV 용연-울산TP#1,2T/L 애자교체 공사","2015-09-24 07:00","2015-09-25 18:00","2015-09-24 07:00","2015-09-25 18:00","연속",null,null,null,201507130388,"-"]
[256,"부산울산","울산","용연처용#1 T/L","2014~2015 울산전력처 송전정비 협력회사 총액공사","154kV 용연-울산TP#1,2T/L 애자교체 공사 및 가공지선 교체 안전이격","2015-09-25 07:00","2015-09-25 18:00","2015-09-25 07:00","2015-09-25 18:00","당일",null,null,null,201507130389,"-"]
[257,"부산울산","울산","용연울산TP#1 T/L","2014~2015 울산전력처 송전정비 협력회사 총액공사","154kV 용연-울산TP#1,2T/L 애자교체 공사","2015-09-26 07:00","2015-09-26 18:00","2015-09-26 07:00","2015-09-26 18:00","당일",null,null,null,201507300017,"-"]
[258,"부산울산","울산","용연울산TP#2 T/L","2014~2015 울산전력처 송전정비 협력회사 총액공사","154kV 용연-울산TP#1,2T/L 애자교체 공사","2015-09-26 07:00","2015-09-26 18:00","2015-09-26 07:00","2015-09-26 18:00","당일",null,null,null,201507300018,"-"]
[259,"부산울산","울산","울산울산TP#1 T/L","울산화력S/Y 154kV 보호제어설비 전담운영공사","보호배전반 이설, 제어케이블 수용","2015-09-15 08:00","2015-09-18 18:00","2015-09-15 08:00","2015-09-18 18:00","연속",null,null,null,201507130204,"-"]
[260,"부산울산","울산","울산울산TP#2 T/L","울산화력S/Y 154kV 보호제어설비 전담운영공사","보호배전반 대체(울산S/S측 포함), 제어케이블 수용","2015-09-21 08:00","2015-09-25 18:00","2015-09-21 08:00","2015-09-25 18:00","연속",null,null,null,201507130206,"-"]
[261,"경남","직할","신김해주촌#2 T/L","154kV 신김해-주촌 #2T/L 스페이서 간격조정 및 SB댐퍼 설치","154kV 신김해-주촌#2T/L 스페이서 간격조정(1~2,3~5호) 및 SB댐퍼 설치(2호)- 2014~15년 경남지역본부 직할 송전협력회사 총액공사","2015-09-19 14:00","2015-09-19 18:00","2015-09-19 14:00","2015-09-19 18:00","당일",null,null,null,201507090078,"-"]
[262,"경남","직할","신김해주촌#1 T/L","154kV 신김해-주촌 #1T/L 스페이서 간격조정 및 SB댐퍼 설치","154kV 신김해-주촌#1T/L 스페이서 간격조정(1~2,3~5호) 및 SB댐퍼 설치(2호)-2014~15년 경남지역본부 직할 송전협력회사 총액공사","2015-09-19 08:00","2015-09-19 13:00","2015-09-19 08:00","2015-09-19 13:00","당일",null,null,null,201507090073,"-"]
[263,"경남","진주","의령동진주#2 T/L","154kV 의령-산청T/L 피뢰기 설치(안전이격확보)","154kV 의령-산청T/L 피뢰기 설치(안전이격확보)","2015-09-05 08:00","2015-09-05 19:00","2015-09-05 08:00","2015-09-05 19:00","당일",null,null,null,201507060195,"-"]
[264,"경남","진주","의령산청 T/L","154kV 의령-산청T/L 피뢰기 설치 및 철탑정밀점검","154kV 의령-산청T/L 피뢰기 설치(39기) 및 철탑 정밀점검(전 구간)","2015-09-05 08:00","2015-09-06 19:00","2015-09-05 08:00","2015-09-06 19:00","매일",null,null,null,201507060190,"-"]
[265,"경남","진주","하동S/S 154kV #1 BUS","하동-하동화력#1T/L GIS 정밀점검","하동-하동화력#1T/L GIS 정밀점검","2015-09-01 09:30","2015-09-02 12:10","2015-09-01 09:30","2015-09-02 12:10","연속",null,null,null,201507080007,"-"]
[266,"경남","진주","하동하동화력#1 T/L","하동-하동화력#1T/L GIS 정밀점검","하동-하동화력#1T/L GIS 정밀점검","2015-09-01 09:30","2015-09-03 14:00","2015-09-01 09:30","2015-09-03 14:00","연속",null,null,null,201507080006,"-"]
[267,"경남","진주","하동개양#1 T/L","하동-하동화력#1T/L GIS 정밀점검 시험가압","하동-하동화력#1T/L GIS 정밀점검 시험가압","2015-09-02 12:00","2015-09-02 12:10","취소","취소","당일",null,null,null,201507080009,"-"]
[268,"경남","진주","하동S/S 154kV #2 BUS","하동-하동화력#1T/L GIS 정밀점검","하동-하동화력#1T/L GIS 정밀점검","2015-09-02 12:10","2015-09-03 14:00","2015-09-02 12:10","2015-09-03 14:00","연속",null,null,null,201507080008,"-"]
[269,"경남","진주","하동S/S 154kV #1 BUS","하동-하동화력#2T/L GIS 정밀점검","하동-하동화력#2T/L GIS 정밀점검","2015-09-03 14:00","2015-09-04 12:10","2015-09-03 14:00","2015-09-04 12:10","연속",null,null,null,201507080012,"-"]
[270,"경남","진주","하동하동화력#2 T/L","하동-하동화력#2T/L GIS 정밀점검","하동-하동화력#2T/L GIS 정밀점검","2015-09-03 14:00","2015-09-05 18:30","2015-09-03 14:00","2015-09-05 18:30","연속",null,null,null,201507080011,"-"]
[271,"경남","진주","하동개양#2 T/L","하동-하동화력#1T/L GIS 정밀점검 시험가압","하동-하동화력#1T/L GIS 정밀점검 시험가압","2015-09-03 13:50","2015-09-03 14:00","취소","취소","당일",null,null,null,201507080010,"-"]
[272,"경남","진주","하동개양#1 T/L","하동-하동화력#2T/L GIS 정밀점검 시험가압","하동-하동화력#2T/L GIS 정밀점검 시험가압","2015-09-04 12:00","2015-09-04 12:10","취소","취소","당일",null,null,null,201507080014,"-"]
[273,"경남","진주","하동S/S 154kV #2 BUS","하동-하동화력#2T/L GIS 정밀점검","하동-하동화력#2T/L GIS 정밀점검","2015-09-04 12:10","2015-09-05 18:30","2015-09-04 12:10","2015-09-05 18:30","연속",null,null,null,201507080013,"-"]
[274,"경남","진주","하동개양#2 T/L","하동-하동화력#2T/L GIS 정밀점검 시험가압","하동-하동화력#2T/L GIS 정밀점검 시험가압","2015-09-05 18:20","2015-09-05 18:30","취소","취소","당일",null,null,null,201507080015,"-"]
[275,"경남","진주","하동개양#1 T/L","6100 BUS-TIE GIS 정밀점검 시험가압","6100 BUS-TIE GIS 정밀점검 시험가압","2015-09-08 12:00","2015-09-08 12:10","취소","취소","당일",null,null,null,201507080031,"-"]
[276,"경남","진주","하동개양#2 T/L","6100 BUS-TIE GIS 정밀점검 시험가압","6100 BUS-TIE GIS 정밀점검 시험가압","2015-09-09 18:20","2015-09-09 18:30","취소","취소","당일",null,null,null,201507080032,"-"]
[277,"경남","진주","하동개양#1 T/L","하동-남해#1T/L GIS 정밀점검 시험가압","하동-남해#1T/L GIS 정밀점검 시험가압","2015-09-15 12:00","2015-09-15 12:10","취소","취소","당일",null,null,null,201507080020,"-"]
[278,"경남","진주","하동개양#2 T/L","하동-남해#1T/L GIS 정밀점검 시험가압","하동-남해#1T/L GIS 정밀점검 시험가압","2015-09-16 13:50","2015-09-16 14:00","취소","취소","당일",null,null,null,201507080021,"-"]
[279,"경남","진주","하동개양#1 T/L","하동-남해#2T/L GIS 정밀점검 시험가압","하동-남해#2T/L GIS 정밀점검 시험가압","2015-09-17 12:00","2015-09-17 12:10","취소","취소","당일",null,null,null,201507080026,"-"]
[280,"경남","진주","하동개양#2 T/L","하동-남해#2T/L GIS 정밀점검 시험가압","하동-남해#2T/L GIS 정밀점검 시험가압","2015-09-18 18:20","2015-09-18 18:30","취소","취소","당일",null,null,null,201507080027,"-"]
[281,"경남","통영","통영거제#1 T/L","거제S/S 154kV 통영-거제#1T/L 휴전(정밀점검 시험가압)","거제S/S 154kV 통영-거제#1T/L 휴전 - 거제S/S 154kV 삼성조선T/L GIS 시험가압","2015-09-27 17:30","2015-09-27 18:30","2015-09-27 17:30","2015-09-27 18:30","당일",null,null,null,201507070088,"-"]
[282,"경남","통영","통영거제#2 T/L","거제S/S 154kV 통영-거제#2T/L 휴전(정밀점검 시험가압)","거제S/S 154kV 통영-거제#2T/L 휴전 - 거제S/S 154kV 삼성조선T/L GIS 시험가압","2015-09-26 17:30","2015-09-26 18:30","2015-09-26 17:30","2015-09-26 18:30","당일",null,null,null,201507070087,"-"]
[283,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 보호반 성능개선","154kV 신고성-통영T/L 보호반 성능개선 - 영인기술 154kV 송전선로보호반(SEL제) 성능개선","2015-09-19 09:30","2015-09-19 18:30","취소","취소","당일",null,null,null,201507070069,"-"]
[284,"경남","함안","서마산S/S 154kV #1 BUS","서마산S/S 170kV 6100, 6333GIS 교체공사","170kV 6100, 6333GIS #1DS, CB부 교체(GAS회수, 철거, 설치, 진공, GAS주입)","2015-09-04 17:30","2015-09-14 17:30","2015-09-04 17:30","2015-09-14 17:30","연속",null,null,null,201507090212,"-"]
[285,"경남","함안","서마산진동 T/L","서마산S/S 170kV 6100, 6333 GIS 교체공사관련 시험가압","170kV 6100, 6333 GIS 교체관련 #2BUS측 시험가압","2015-09-04 15:30","2015-09-04 17:30","2015-09-04 15:30","2015-09-04 17:30","당일",null,null,null,201507090220,"-"]
[286,"경남","함안","서마산S/S 154kV #1 BUS TIE CB","서마산S/S 170kV 6100, 6333 GIS 교체공사","170kV 6100, 6333GIS #1,2DS, CB, 상부 교체(GAS회수, 철거, 설치, 진공, GAS주입, 시험가압)","2015-09-03 08:30","2015-09-24 17:30","2015-09-03 08:30","2015-09-24 17:30","연속",null,null,null,201507090218,"-"]
[287,"경남","함안","서마산진동 T/L","서마산S/S 170kV 6100, 6333 GIS 교체공사관련 시험가압","170kV 6100, 6333 GIS 교체관련 #1BUS측 시험가압","2015-09-13 17:30","2015-09-14 09:30","2015-09-13 17:30","2015-09-14 09:30","연속",null,null,null,201507090221,"-"]
[288,"경남","함안","서마산진동 T/L","서마산S/S 170kV 6100, 6333 GIS 교체공사관련 시험가압","170kV 6100, 6333 GIS 교체관련 #2BUS측 시험가압","2015-09-20 17:30","2015-09-21 09:30","2015-09-20 17:30","2015-09-21 09:30","연속",null,null,null,201507090223,"-"]
[289,"경남","함안","서마산S/S 154kV #2 BUS","서마산S/S 170kV 6100, 6333 GIS 교체공사","170kV 6100, 6333GIS #2DS, 상부브렌치 교체(GAS회수, 철거, 설치, 진공, GAS주입, 시험가압)","2015-09-14 17:30","2015-09-22 17:30","2015-09-14 17:30","2015-09-22 17:30","연속",null,null,null,201507090215,"-"]
[290,"경남","함안","서마산S/S 154kV #2 BUS","서마산S/S 170kV 6100, 6333GIS 교체공사","#2DS 모선 분리작업","2015-09-03 08:30","2015-09-04 17:30","2015-09-03 08:30","2015-09-04 17:30","연속",null,null,null,201507090203,"-"]
[291,"경남","함안","신마산마산#2 T/L","154kV 신마산-마산#2T/L 보호배전반 교체공사","154kV 신마산-마산#2T/L 보호배전반 교체공사, 신마산S/S GCB,PT,LA보통점검(최병만,김민준)","2015-09-12 08:30","2015-09-13 17:30","2015-09-12 08:30","2015-09-13 17:30","연속",null,null,null,201507090249,"-"]

{"sheet":"한수원","index":3,"n_rows":12,"n_cols":20,"rows_kept":12,"cut":false,"hidden":false,"merged":[[2,19,3,19],[2,13,3,13],[2,14,3,14],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[0,0,0,6],[2,12,3,12],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11]]}
["2015년 9월 월간휴전계획표(한수원)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업\n구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소간","사업소내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한울본부","한울3발","#6 대기보조변압기","6호기 8차 계획예방정비 #6 대기보조변압기 점검\n* 조작차단기 : PCB 7B00, 7B72","○ 스위치야드 'B Bay' 교체공사\n○ 갑종보호반(SAT) 디지털 삼중화\n○ 대기보조변압기 일반점검","2015-09-10T15:00:00","2015-10-11T12:00:00","2015-09-10T15:00:00","2015-10-11T12:00:00","연속","Y"]
[2,"한빛본부","2발전소","#4 주변압기","4호기 15차 계획예방정비\n* 조작차단기 : PCB 7A00, 7A71","○ O/H 관련 #4 주변압기 점검\n○ 보호계전기 개체 및 연동시험","2015-08-06 10:00","2015-11-18 22:30","2015-08-06 10:00","2015-11-18 22:30","연속","Y"]
[3,"한빛본부","2발전소","#4 기동변압기(03XN)","4호기 15차 계획예방정비\n* 조작차단기 : PCB 7900, 7971","○ O/H 관련 #4 기동변압기(03XN) 내부점검\n○ 보호계전기 개체 및 연동시험","2015-08-16 13:00","2015-08-26 12:00","2015-08-16 13:00","2015-08-26 12:00","연속","Y"]
[4,"한빛본부","2발전소","#4 기동변압기(04XN)","4호기 15차 계획예방정비\n* 조작차단기 : PCB 7800, 7871","○ O/H 관련 #4 기동변압기(04XN) 일반점검\n○ 보호계전기 개체 및 연동시험","2015-09-23 19:00","2015-10-03 12:00","2015-09-23 19:00","2015-10-03 12:00","연속","Y",null,null,"휴전시작/종료일 변경됨"]
[5,"한빛본부","한빛3발","연락선로#3 T/L","연락선로#3 T/L 피뢰기 설치\n*조작차단기 : 7C00 7C72","○ 연락선로#3 T/L 피뢰기 설치","2015-09-10T09:00:00","2015-09-11T18:00:00","2015-09-10T09:00:00","2015-09-11T18:00:00","연속","N"]
[6,"한빛본부","한빛3발","모선#2","모선#2 보호반 설치\n*조작차단기 : 7E72  7D72 7C72 7B72","○ 모선#2 보호반 대체","2015-09-12T09:00:00","2015-09-14T18:00:00","2015-09-12T09:00:00","2015-09-14T18:00:00","연속","N"]
[7,"한빛본부","한빛3발","신김제#2 T/L","한빛본부 인출변경 공사\n*조작차단기 : 7E72  7E00","○ 신김제#2 T/L 신규 철탑 N0.4 설치 및 송전선로 연결","2015-09-15T09:00:00","2015-09-21T18:00:00","2015-09-15T09:00:00","2015-09-21T18:00:00","연속","N"]
[8,"한빛본부","한빛3발","신남원#2 T/L","한빛본부 인출변경 공사\n*조작차단기 : 7D72  7D00","○ 신남원#2 T/L 철탑 N0. 1.4, 3, 4 철거 및 송전선로 연결","2015-09-22T09:00:00","2015-10-01T18:00:00","2015-09-22T09:00:00","2015-10-01T18:00:00","연속","N"]

{"sheet":"서부","index":4,"n_rows":6,"n_cols":15,"rows_kept":6,"cut":false,"hidden":false,"merged":[[3,14,4,14],[3,6,3,7],[3,8,3,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,5,4,5],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4]]}
["회사명 : 한국서부발전"]
["2015년도 09월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서인천발전본부","-","제4호기 승압변압기","제4호기 계획예방정비공사\n* 조작차단기 : 6433","- 제4호기 계획예방정비공사 및 법정검사 수검","2015-09-07 09:00","2015-10-05 16:00","2015-09-07 09:00","2015-10-05 16:00","연속",null,null,null," "]

{"sheet":"중부","index":5,"n_rows":10,"n_cols":20,"rows_kept":10,"cut":false,"hidden":false,"merged":[[7,13,8,13],[7,0,8,0],[7,1,8,1],[7,2,8,2],[7,3,8,3],[7,4,8,4],[7,5,8,5],[7,6,7,7],[7,8,7,9],[7,10,8,10],[7,11,8,11],[7,12,8,12],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[2,19,3,19],[6,0,6,1],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,14,3,14],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7]]}
["2015년도 9월 휴전계획표(한국중부발전)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"보령화력","2발전소","기력3호기 Main TR\n(CB7300, CB7371)","간이정비","제3호기 간이정비","2015-09-12","2015-09-18T23:59:00","2015-09-12","2015-09-18T23:59:00","연속","Y"]
[2,"인천화력","복합 3호기","ST #3 주변압기\n(7B72, 7B00)","계획예방정비공사","발전기 차단기\n정밀점검","2015-09-10T09:00:00","2015-09-25T18:00:00","2015-09-10T09:00:00","2015-09-25T18:00:00","연속","Y"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울화력본부","발전소","#5 M. Tr\n(CB 677)","계획예방정비공사","O/H 관련 주변압기 점검","2015-09-30","2015-10-27","2015-09-30","2015-10-27","연속","Y"]