{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["765송부","345송부","154송부","한수원","서부발전"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":15,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":13,"n_cols":16,"rows_kept":13,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2015년도 10월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백S/S TIE-#4 M.Tr 1차 CB","765kV 신태백S/S 800kV GIS 증설공사","8571CB 및 DS 설치, 85BAY 단모선 GIS 철거(8500CB)","2015-10-05 09:00","2015-11-28 18:00","2015-10-05 09:00","2015-11-28 18:00","연속",null,null,null,201508190251]
[2,"강원","태백","신태백S/S 765kV #1 BUS","765kV 신태백S/S 800kV GIS 증설공사","- 800kV GIS * 3CB 설치 - 85BAY 단모선 GIS 철거","2015-10-05 09:00","2015-10-12 18:00","2015-10-05 09:00","2015-10-12 18:00","연속",null,null,null,201508100088]
[3,"대전충남","서산","당진T/P 765kV #1 BUS","15년 서산P/O 장기사용 배전반 교체","○ 765kV 모선보호반 교체 공사","2015-10-12 09:00","2015-10-16 18:00","2015-10-12 09:00","2015-10-16 18:00","연속",null,null,null,201508130111]
[4,"대전충남","서산","당진T/P 765kV #2 BUS","15년 서산P/O 장기사용 배전반 교체","○ 765kV 모선보호반 교체 공사","2015-10-19 09:00","2015-10-23 18:00","2015-10-19 09:00","2015-10-23 18:00","연속",null,null,null,201508130114]
[5,"부산울산","동부산","신고리S/S 북경남#2T/L-#4G T/L TIE CB","신고리S/S 800kV GIS 초기점검공사","신고리S/S 800kV 8300 GIS 초기점검(G4 휴전가능으로 8372GIS와 동시 휴전)","2015-10-19 09:00","2015-10-24 18:00","2015-10-19 09:00","2015-10-24 18:00","연속",null,null,null,201508130208]
[6,"부산울산","동부산","신고리S/S #3 M.Tr A-1","신고리S/S 765kV M.Tr 초기점검공사","1. 신고리S/S 765kV #3M.Tr 초기점검 2. 신고리S/S 800kV 8571,8500 GIS 초기점검 3. 고리N/P S/Y 362kV 7A00, 7A72 GIS 초기점검 4. 고리N/P S/Y 7A02,7A62 GIS 가스누기 보수 5. 고리N/P S/Y 7A72 GIS 유압불량 보수","2015-10-12 09:00","2015-10-17 18:00","2015-10-12 09:00","2015-10-17 18:00","연속",null,null,null,201508130202]
[7,"부산울산","동부산","신고리S/S #3M.Tr 1차 TIE CB","765kV 신고리S/S 81Bay 분리공사(8500CB 휴전)","- 8500CB 휴전(8572CB 설치관련) - 800kV 50kA 8,000A GIS*1CB 신설(8472CB) - 800kV 50kA 8,000A GIS*1CB 이설(8172CB→8572CB)","2015-10-05 09:00","2015-12-16 18:00","2015-10-05 09:00","2015-12-16 18:00","연속",null,null,null,201508040021]
[8,"부산울산","동부산","신고리S/S #1 M.Tr A-1","신고리S/S 765kV M.Tr 초기점검공사","1. 신고리S/S 765kV #1M.Tr 초기점검 2. 신고리S/S 800kV 8471,8400 GIS 초기점검 3. 고리N/P S/Y 362kV 7800, 7872 GIS 초기점검 4. 고리N/P S/Y 7872 GIS 유압불량 보수","2015-10-26 09:00","2015-10-31 18:00","2015-10-26 09:00","2015-10-31 18:00","연속",null,null,null,201508130205]
[9,"부산울산","동부산","신고리S/S #4GEN T/L CB","신고리S/S 800kV GIS 초기점검공사","신고리S/S 800kV 8372 GIS 초기점검(G4 휴전가능으로 8300GIS와 동시 휴전)","2015-10-19 09:00","2015-10-24 18:00","2015-10-19 09:00","2015-10-24 18:00","연속",null,null,null,201508130209]

{"sheet":"345송부","index":1,"n_rows":196,"n_cols":16,"rows_kept":196,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2015년도 10월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr A","성동S/S 345kV 주변압기 및 OLTC 정밀점검공사","주변압기 및 OLTC 정밀점검(#2MTR) x 1Bank","2015-10-12 08:00","2015-10-21 18:00","2015-10-12 08:00","2015-10-21 18:00","연속",null,null,null,201508170264,{"$f":"IF(ISERROR(VLOOKUP(D5,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D5,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[2,"서울","성동","성동S/S 345kV #1 Sh.R","성동S/S 345kV Sh.R 제작사 발췌점검공사","Sh.R 차단기(7179) 내부 성능개선에 따른 제작사 발췌 내부점검","2015-10-15 09:00","2015-10-16 18:00","2015-10-15 09:00","2015-10-16 18:00","연속",null,null,null,201508210121,{"$f":"IF(ISERROR(VLOOKUP(D6,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D6,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[3,"서울","성동","성동S/S #3 M.Tr A","성동S/S 345kV 주변압기 및 OLTC 정밀점검공사","주변압기 및 OLTC 정밀점검(#3MTR) x 1Bank","2015-10-01 08:00","2015-10-08 18:00","2015-10-01 08:00","2015-10-08 18:00","연속",null,null,null,201508170295,{"$f":"IF(ISERROR(VLOOKUP(D7,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D7,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[4,"서울","중부","중부S/S 345kV #2 Sh.R","15년 중부전력지사 장기사용 배전반 대체공사","중부S/S #2Sh.R 배전반 대체공사","2015-10-12 10:00","2015-10-14 18:00","2015-10-12 10:00","2015-10-14 18:00","연속",null,null,null,201508210068,{"$f":"IF(ISERROR(VLOOKUP(D8,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D8,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[5,"서울","중부","중부S/S #3 M.Tr A","15년 중부전력지사 345kV M.Tr 정밀점검 공사","중부S/S 345kV #3M.Tr 누유 보수","2015-10-29 10:00","2015-10-29 18:00","2015-10-29 10:00","2015-10-29 18:00","연속",null,null,null,201508100058,{"$f":"IF(ISERROR(VLOOKUP(D9,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D9,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[6,"서울","중부","중부S/S 345kV #1 Sh.R","15년 중부전력지사 장기사용 배전반 대체공사","중부S/S #1Sh.R 배전반 대체공사","2015-10-05 10:00","2015-10-07 18:00","2015-10-05 10:00","2015-10-07 18:00","연속",null,null,null,201508100045,{"$f":"IF(ISERROR(VLOOKUP(D10,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D10,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[7,"남서울","강남","신양재S/S 345kV #2 BUS","신양재S/S 모선보호반 대체 - 345kV #2BUS","신양재S/S 모선보호반 대체 - 345kV #2BUS - 7172, 7272, 7372, 7472 CB 및 DS 개방","2015-10-26 09:00","2015-10-30 18:00","2015-10-26 09:00","2015-10-30 18:00","연속",null,null,null,201507140015,{"$f":"IF(ISERROR(VLOOKUP(D11,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D11,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[8,"남서울","강남","신양재S/S 345kV #1 BUS","신양재S/S 모선보호반 대체 - 345kV #1BUS","신양재S/S 모선보호반 대체 - 345kV #1BUS - 7171, 7271, 7300, 7471 CB 및 DS 개방","2015-10-19 09:00","2015-10-23 18:00","2015-10-19 09:00","2015-10-23 18:00","연속",null,null,null,201507140014,{"$f":"IF(ISERROR(VLOOKUP(D12,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D12,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[9,"남서울","강남","신양재S/S #3 M.Tr A","신양재S/S #3M.Tr 보호배전반 대체","신양재S/S #3M.Tr 보호배전반 대체 - 병행작업 : #3M.TR 보통점검 (변전협력회사)","2015-10-12 09:00","2015-10-16 18:00","2015-11-23 09:00","2015-11-27 18:00","연속",null,null,null,201507140003,{"$f":"IF(ISERROR(VLOOKUP(D13,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D13,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[10,"남서울","강남","신양재S/S #2 M.Tr A","신양재S/S #2M.Tr 보호배전반 대체","신양재S/S #2M.Tr 보호배전반 대체 - 병행작업 : #2M.Tr 보통점검 (변전협력회사)","2015-10-05 09:00","2015-10-09 18:00","2015-10-12 10:00","2015-10-16 18:00","연속",null,null,null,201507140002,{"$f":"IF(ISERROR(VLOOKUP(D14,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D14,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[11,"남서울","동서울","동서울S/S #4 M.Tr A","동서울S/S 345KV #4M.TR 절연불량 붓싱교체","동서울S/S 345KV #4M.TR 절연불량 붓싱교체(C상:HO,XO)","2015-10-19 08:00","2015-10-20 18:00","2015-10-19 08:00","2015-10-20 18:00","연속",null,null,null,201508110218,{"$f":"IF(ISERROR(VLOOKUP(D15,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D15,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[12,"남서울","동서울","동서울S/S #2 M.Tr A","동서울S/S 345KV #2M.TR 절연불량 붓싱교체","동서울S/S 345KV #2M.TR 절연불량 붓싱교체(B상:HO,XO)","2015-10-15 08:00","2015-10-16 18:00","2015-10-15 08:00","2015-10-16 18:00","연속",null,null,null,201508110217,{"$f":"IF(ISERROR(VLOOKUP(D16,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D16,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[13,"남서울","동서울","동서울S/S #1 M.Tr A","동서울S/S 345KV #1M.TR 절연불량 붓싱교체","동서울S/S 345KV #1M.TR 절연불량 붓싱교체(A상:HO,XO, C상:H1)","2015-10-12 08:00","2015-10-14 18:00","2015-10-12 08:00","2015-10-14 18:00","연속",null,null,null,201508110212,{"$f":"IF(ISERROR(VLOOKUP(D17,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D17,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[14,"남서울","영서","신시흥영서#2 T/L","신시흥-영서#2T/L 보호배전반 정기점검","신시흥-영서#2T/L 보호배전반 정기점검","2015-10-02 10:00","2015-10-02 18:00","2015-10-02 10:00","2015-10-02 18:00","당일",null,null,null,201508170219,{"$f":"IF(ISERROR(VLOOKUP(D18,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D18,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[15,"남서울","영서","신시흥영서#1 T/L","362kV GCB 정밀점검","362kV GCB 정밀점검","2015-10-12 10:00","2015-10-16 18:00","2015-10-12 10:00","2015-10-16 18:00","연속",null,null,null,201508180047,{"$f":"IF(ISERROR(VLOOKUP(D19,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D19,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[16,"남서울","영서","영서S/S 345kV 70-71 SEC CB (70-71-0)","362kV GCB 정밀점검","362kV GCB 정밀점검","2015-10-19 10:00","2015-10-23 18:00","2015-10-19 10:00","2015-10-23 18:00","연속",null,null,null,201508180043,{"$f":"IF(ISERROR(VLOOKUP(D20,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D20,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[17,"남서울","영서","영서S/S 345kV 75-76 SEC CB (75-76-0)","362kV GCB 정밀점검","362kV GCB 정밀점검","2015-10-19 10:00","2015-10-23 18:00","2015-10-19 10:00","2015-10-23 18:00","연속",null,null,null,201508180045,{"$f":"IF(ISERROR(VLOOKUP(D21,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D21,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[18,"남서울","직할","영등포S/S #2 M.Tr A","345kV #2M.Tr 보호배전반 정기점검","345kV #2M.Tr 보호배전반 정기점검","2015-10-09 14:00","2015-10-09 18:00","2015-10-09 14:00","2015-10-09 18:00","당일",null,null,"신뢰도개선",201508170155,{"$f":"IF(ISERROR(VLOOKUP(D22,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D22,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[19,"남서울","직할","영등포S/S #3 M.Tr A","345kV #3M.Tr 보호배전반 정기점검","345kV #3M.Tr 보호배전반 정기점검","2015-10-10 10:00","2015-10-10 18:00","2015-10-10 10:00","2015-10-10 18:00","당일",null,null,"신뢰도개선",201508170161,{"$f":"IF(ISERROR(VLOOKUP(D23,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D23,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[20,"남서울","직할","영등포S/S #1 M.Tr A","345kV #1M.Tr 보호배전반 정기점검","345kV #1M.Tr 보호배전반 정기점검","2015-10-09 09:00","2015-10-09 14:00","2015-10-09 09:00","2015-10-09 14:00","당일",null,null,"신뢰도개선",201508170154,{"$f":"IF(ISERROR(VLOOKUP(D24,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D24,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[21,"인천","시흥","신시흥영흥TP#2 T/L","신시흥-영흥#2T/L 정밀점검","신시흥-영흥#2T/L 정밀점검","2015-10-09 09:00","2015-10-16 18:00","2015-10-21 08:00","2015-10-26 18:00","연속",null,null,"신뢰도개선",201508100169,{"$f":"IF(ISERROR(VLOOKUP(D25,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D25,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[22,"인천","시흥","신시흥영흥TP#4 T/L","신시흥-영흥#4T/L 정밀점검","신시흥-영흥#4T/L 정밀점검","2015-10-01 09:00","2015-10-08 18:00","2015-10-15 08:00","2015-10-20 18:00","연속",null,null,"신뢰도개선",201508100168,{"$f":"IF(ISERROR(VLOOKUP(D26,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D26,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[23,"인천","인천","서인천C/C 345kV #70 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #70BUS 모선 보호용 CT 케이블 분리 및 결선","2015-10-03 09:30","2015-10-03 17:30","2015-10-04 08:00","2015-10-04 13:00","당일",null,null,"신뢰도개선",201508040030,{"$f":"IF(ISERROR(VLOOKUP(D27,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D27,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[24,"인천","인천","서인천C/C 345kV #75 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #75BUS 모선 보호용 CT 케이블 분리 및 결선","2015-10-04 09:30","2015-10-04 17:30","2015-10-04 13:00","2015-10-04 19:00","당일",null,null,"신뢰도개선",201508040032,{"$f":"IF(ISERROR(VLOOKUP(D28,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D28,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[25,"인천","인천","서인천C/C 서인천CC신부평#3T/L #2Sh.R GIS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 서인천C/C 74Bay(7471,7400) GIS 대체","2015-10-05 06:00","2015-11-05 17:30","2015-10-05 06:00","2015-11-05 17:30","연속",null,null,null,201508040034,{"$f":"IF(ISERROR(VLOOKUP(D29,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D29,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[26,"인천","인천","서인천C/C 신부평#3T/L Sh.R(#2 Sh.R)","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #2Sh.R용 GIS 대체","2015-10-05 06:00","2015-11-05 17:30","2015-10-05 06:00","2015-11-05 17:30","연속",null,null,null,201508040042,{"$f":"IF(ISERROR(VLOOKUP(D30,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D30,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[27,"인천","인천","서인천C/C #4 M.Tr 1차 GIS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 서인천c/c 74Bay(7472) GIS 대체","2015-10-05 06:00","2015-11-05 17:30","2015-10-05 06:00","2015-11-05 17:30","연속",null,null,null,201508040035,{"$f":"IF(ISERROR(VLOOKUP(D31,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D31,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[28,"인천","인천","서인천C/C 345kV #70 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #70BUS 모선 보호용 CT 케이블 분리 및 결선","2015-10-27 09:30","2015-10-27 17:30","2015-10-25 08:00","2015-10-25 13:00","당일",null,null,"신뢰도개선",201508040048,{"$f":"IF(ISERROR(VLOOKUP(D32,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D32,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[29,"인천","인천","서인천C/C 345kV #75 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #75BUS 모선 보호용 CT 케이블 분리 및 결선","2015-10-28 09:00","2015-10-28 18:00","2015-10-25 13:00","2015-10-25 19:00","당일",null,null,"신뢰도개선",201508040057,{"$f":"IF(ISERROR(VLOOKUP(D33,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D33,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[30,"인천","인천","신가좌인천CC#1 T/L","345kV가정루원시티 지중화 정비공사","345kV 가정루원시티 지중화 정비공사 -신설:3기[4회선(345kV 신가좌-인천CC No.18),2회선 C/H(154kV, 345kV)] -교체:1기[345kV 신가좌-인천CC No.19 Enclosing 공법으로 철탑교체] -철거:20기[345kV 5기, 154kV 15기]","2015-10-21 09:00","2015-10-31 18:00","2015-10-21 09:00","2015-10-31 18:00","연속",null,null,"신뢰도개선",201508070182,{"$f":"IF(ISERROR(VLOOKUP(D34,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D34,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[31,"인천","인천","신가좌S/S #1 M.Tr 1차 GIS","2015년 인천전력지사 362kV GIS 정밀점검 공사","신가좌S/S #1 M.Tr 1차(7172) GIS 정밀점검","2015-10-21 08:00","2015-10-23 18:00","2015-10-21 08:00","2015-10-23 18:00","연속",null,null,null,201508060142,{"$f":"IF(ISERROR(VLOOKUP(D35,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D35,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[32,"인천","인천","신경서S/S 345kV #1 BUS","345kV 신경서S/S SW증설 및 CLR 설치공사","74Bay 2CB 증설 - #1Bus 모선 GIB 철거, 51DS&GIB 연결","2015-10-29 10:00","2015-11-11 18:00","2015-10-29 10:00","2015-11-11 18:00","연속",null,null,null,201508130349,{"$f":"IF(ISERROR(VLOOKUP(D36,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D36,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[33,"인천","인천","신경서S/S 345kV #2 BUS","345kV 신경서S/S SW증설 및 CLR 설치공사","74Bay 2CB 증설 - #2Bus 모선 GIB 철거, 51DS&GIB 연결","2015-10-15 10:00","2015-10-28 18:00","2015-10-15 10:00","2015-10-28 18:00","연속",null,null,null,201508130351,{"$f":"IF(ISERROR(VLOOKUP(D37,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D37,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[34,"인천","인천","인천CC S/Y #1 M.Tr A","인천CC 용얄부족 GIS 대체공사","CB 2대 대체 및 1대 철거","2015-10-02 10:00","2015-10-30 17:00","2015-10-02 10:00","2015-10-30 17:00","연속",null,null,null,201507270053,{"$f":"IF(ISERROR(VLOOKUP(D38,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D38,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[35,"인천","직할","인천CC S/Y #2 TIE Tr 1차 CB (7172)","인천CC 용량부족 GIS 대체공사","CB 2대 대체 및 1대 철거(7171, 7100 CB 대체,7172 철거) [참고]#2TIe-Tr : 15년 5월 7C Bay로 인출 변경 완료","2015-10-02 10:00","2015-10-30 17:00","2015-10-02 10:00","2015-10-30 17:00","연속",null,null,null,201508270020,{"$f":"IF(ISERROR(VLOOKUP(D39,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D39,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[36,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S #2M.Tr 정밀점검 공사","신부평S/S #2M.Tr 정밀점검","2015-10-12 09:00","2015-10-23 18:00","2015-10-12 09:00","2015-10-23 18:00","연속",null,null,null,201508110161,{"$f":"IF(ISERROR(VLOOKUP(D40,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D40,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[37,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S #3M.Tr 정밀점검 공사","신부평S/S #3M.Tr 정밀점검","2015-10-26 09:00","2015-11-06 18:00","2015-10-26 09:00","2015-11-06 18:00","연속",null,null,null,201508110162,{"$f":"IF(ISERROR(VLOOKUP(D41,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D41,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[38,"경기북부","구리","미금성동#4 T/L","구리전력지사 362kV GIS 보통점검(7772,7700)","362kV GIS 보통점검(7772,7700)","2015-10-20 09:30","2015-10-20 18:00","2015-10-20 09:30","2015-10-20 18:00","당일",null,null,null,201508100178,{"$f":"IF(ISERROR(VLOOKUP(D42,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D42,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[39,"경기북부","구리","미금S/S 345kV #1 BUS","○ 345kV 7651 A상 DS 내부 부분방전 발생 내부 점검","○345kV 7651 A상 DS 내부점검 및 조작링크 교체","2015-10-18 07:30","2015-10-18 20:00","2015-10-18 07:30","2015-10-18 20:00","당일",null,null,null,201505290016,{"$f":"IF(ISERROR(VLOOKUP(D43,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D43,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[40,"경기북부","구리","미금성동#2 T/L","구리전력지사 362kV GIS 보통점검(7271,7200)","362kV GIS 보통점검(7271,7200)","2015-10-19 09:30","2015-10-19 18:00","2015-10-19 09:30","2015-10-19 18:00","당일",null,null,null,201508100177,{"$f":"IF(ISERROR(VLOOKUP(D44,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D44,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[41,"경기북부","구리","신의정부미금#1 T/L","2015년 구리전력지사 362kV GIS 정밀점검(7671,7600)","○ 접촉저항, 개폐타임 측정 ○ SF6 SO2, 수분 측정","2015-10-12 08:00","2015-10-16 18:00","2015-10-05 08:00","2015-10-09 18:00","연속",null,null,null,201506120098,{"$f":"IF(ISERROR(VLOOKUP(D45,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D45,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[42,"경기북부","구리","동서울미금#2 T/L","2015년 구리전력지사 362kV GIS 정밀점검(7471,7400)","○ 접촉저항, 개폐타임 측정 ○ SF6 SO2, 수분 측정","2015-10-05 08:00","2015-10-09 18:00","2015-10-12 08:00","2015-10-16 18:00","연속",null,null,null,201504300124,{"$f":"IF(ISERROR(VLOOKUP(D46,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D46,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[43,"경기북부","구리","신가평신의정부#1 T/L","345kV 신가평-신의정부#1T/L 불량압축인류크램프 교체공사","불량압축인류크램프 교체공사","2015-10-30 09:00","2015-10-30 18:00","2015-10-30 09:00","2015-10-30 18:00","당일",null,null,null,201507090015,{"$f":"IF(ISERROR(VLOOKUP(D47,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D47,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[44,"경기북부","구리","신가평신의정부#2 T/L","345kV 신가평-신의정부#2T/L 전선교체공사","전선소손개소에 대한 전력선 교체공사","2015-10-26 09:00","2015-10-29 18:00","2015-10-26 09:00","2015-10-29 18:00","당일",null,null,null,201507090013,{"$f":"IF(ISERROR(VLOOKUP(D48,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D48,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[45,"경기북부","구리","신가평신포천#1 T/L","345kV 신가평-신포천#1T/L 초기점검","- No.94~175 초기점검","2015-10-12 08:00","2015-10-17 18:00","2015-10-12 08:00","2015-10-17 18:00","연속",null,null,null,201505150019,{"$f":"IF(ISERROR(VLOOKUP(D49,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D49,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[46,"경기북부","구리","신가평미금#2 T/L","345kV 신가평-신의정부#1T/L 불량압축인류크램프 교체공사","불량압축인류크램프 교체공사","2015-10-30 09:00","2015-10-30 18:00","2015-10-30 09:00","2015-10-30 18:00","당일",null,null,null,201507130222,{"$f":"IF(ISERROR(VLOOKUP(D50,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D50,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[47,"경기북부","구리","신가평신포천#2 T/L","345kV 신가평-신포천#2T/L 초기점검","- No.94~175 초기점검","2015-10-19 08:00","2015-10-24 18:00","2015-10-19 08:00","2015-10-24 18:00","연속",null,null,null,201505150020,{"$f":"IF(ISERROR(VLOOKUP(D51,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D51,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[48,"경기북부","구리","신포천S/S #1 M.Tr A","신포천S/S 345kV #1M.Tr 2차 CB 유압계통 누유 보수","신포천S/S 345kV #1M.Tr 2차 CB 유압계통 누유 보수","2015-10-08 09:00","2015-10-08 12:00","2015-10-08 09:00","2015-10-08 12:00","당일",null,null,null,201508110275,{"$f":"IF(ISERROR(VLOOKUP(D52,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D52,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[49,"경기북부","구리","신포천S/S #2 M.Tr A","신포천S/S 345kV #2M.Tr 2차 CB 유압계통 누유 보수","신포천S/S 345kV #2M.Tr 2차 CB 유압계통 누유 보수","2015-10-08 13:00","2015-10-08 14:00","2015-10-08 13:00","2015-10-08 14:00","당일",null,null,null,201508110276,{"$f":"IF(ISERROR(VLOOKUP(D53,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D53,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[50,"경기북부","구리","신포천-포천CC#1 T/L","15년 가공송전 순시점검 위탁공사(초기점검)","345kV 신포천-포천#1T/L 초기점검 : 애자금구류, 전력선점검 - 스페이서 점검 포함","2015-10-17 09:00","2015-10-18 18:00","2015-10-17 09:00","2015-10-18 18:00","매일",null,null,null,201508170138,{"$f":"IF(ISERROR(VLOOKUP(D54,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D54,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[51,"경기북부","구리","신포천-포천CC#2 T/L","15년 가공송전 순시점검 위탁공사(초기점검)","345kV 신포천-포천#1T/L 초기점검 : 애자금구류, 전력선점검 - 스페이서 점검 포함","2015-10-09 09:00","2015-10-11 18:00","2015-10-09 09:00","2015-10-11 18:00","매일",null,null,null,201508170136,{"$f":"IF(ISERROR(VLOOKUP(D55,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D55,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[52,"경기북부","직할","동두천CC #4TIE 1차 CB (7400)","동두천CC 345kV #1BUS","345kV #1BUS 휴전 방압변 가스누기 관련 제작사 하자보수 -설비 미생성으로 인한 변경신청","2015-10-05 10:00","2015-10-07 18:00","2015-10-05 10:00","2015-10-07 18:00","연속",null,null,null,201508130154,{"$f":"IF(ISERROR(VLOOKUP(D56,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D56,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[53,"경기북부","직할","신의정부S/S 345kV #3 Sh.R","345kV 신의정부S/S 소음저감대책 시행공사","○ 변압기 및 리액터 방음벽 설치 : 6m(높이) × 149m(길이) ○ 변압기 및 리액터 흡음판 설치 : 156개 - 흡음판 : 345kV 의정부S/S 철거자재 재활용 ○ 기타부대공사 1식","2015-10-07 07:30","2015-10-07 18:00","2015-10-07 07:30","2015-10-07 18:00","연속",null,null,null,201508180200,{"$f":"IF(ISERROR(VLOOKUP(D57,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D57,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[54,"경기북부","직할","신의정부S/S 345kV #2 Sh.R","345kV 신의정부S/S 소음저감대책 시행공사","○ 변압기 및 리액터 방음벽 설치 : 6m(높이) × 149m(길이) ○ 변압기 및 리액터 흡음판 설치 : 156개 - 흡음판 : 345kV 의정부S/S 철거자재 재활용 ○ 기타부대공사 1식","2015-10-08 07:30","2015-10-08 18:00","2015-10-08 07:30","2015-10-08 18:00","연속",null,null,null,201508180202,{"$f":"IF(ISERROR(VLOOKUP(D58,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D58,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[55,"경기북부","직할","신의정부S/S #1 M.Tr A","345kV 신의정부S/S 소음저감대책 시행공사","○ 변압기 및 리액터 방음벽 설치 : 6m(높이) × 149m(길이) ○ 변압기 및 리액터 흡음판 설치 : 156개 - 흡음판 : 345kV 의정부S/S 철거자재 재활용 ○ 기타부대공사 1식","2015-10-05 07:30","2015-10-06 18:00","2015-10-05 07:30","2015-10-06 18:00","연속",null,null,null,201508180197,{"$f":"IF(ISERROR(VLOOKUP(D59,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D59,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[56,"경기북부","파주","신파주S/S #3 M.Tr A","신파주S/S #3M.Tr 2차 GIS Acc. 교체","#3M.Tr 2차 GIS Accumulator 교체","2015-10-02 09:00","2015-10-02 18:00","2015-10-05 09:00","2015-10-05 18:00","당일",null,null,null,201508180217,{"$f":"IF(ISERROR(VLOOKUP(D60,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D60,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[57,"경기북부","파주","신파주신덕은#1 T/L","345kV 신파주-신덕은#1T/L 항공장애구 교체공사","항공장애구 교체(No.21~22 1EA)-소음발생 민원개소","2015-10-28 08:00","2015-10-28 18:00","2015-10-28 08:00","2015-10-28 18:00","당일",null,null,null,201508180169,{"$f":"IF(ISERROR(VLOOKUP(D61,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D61,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[58,"경기","군포","서서울S/S 345kV #1 BUS GIS","345kV 서서울S/S #1BUS","- #1BUS 모선철거(73bay 우측), - 7100CB,7200CB 철거","2015-10-14 08:00","2015-10-21 18:00","2015-10-14 08:00","2015-10-21 18:00","연속",null,null,"신뢰도개선",201508080006,{"$f":"IF(ISERROR(VLOOKUP(D62,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D62,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[59,"경기","군포","서서울S/S #2 M.Tr A","345kV 서서울S/S #2M.Tr","- Bay 변경(73 → 77)에 따른 간섭휴전","2015-10-08 09:00","2015-10-10 18:00","2015-10-08 09:00","2015-10-10 18:00","연속",null,null,null,201508080003,{"$f":"IF(ISERROR(VLOOKUP(D63,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D63,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[60,"경기","군포","화성서서울#2 T/L","345kV 화성서서울#2T/L 지장철탑이설공사 41~50호","345kV 화성서서울T/L 지장철탑이설공사 41~50호 본철탑기초공사(신설48호)","2015-10-20 09:00","2015-10-22 18:00","2015-10-20 09:00","2015-10-22 18:00","연속",null,null,null,201508170446,{"$f":"IF(ISERROR(VLOOKUP(D64,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D64,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[61,"경기","군포","서서울S/S #1 M.Tr A(2014_대체)","345kV #1M.Tr GIS Bay변경공사","- 362kV GIS Bay변경(71→73) - 모선배선 변경(71↔73) - 제어케이블 포설/ 철거 - 보호배전반 시험","2015-10-17 07:00","2015-10-22 18:00","2015-10-17 07:00","2015-10-22 18:00","연속",null,null,null,201508080007,{"$f":"IF(ISERROR(VLOOKUP(D65,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D65,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[62,"경기","군포","서서울S/S 345kV #2 BUS GIS","345kV 서서울S/S #2BUS","- #2BUS 모선철거(73bay 우측), - 7172CB,7272CB 철거","2015-10-22 08:00","2015-10-28 18:00","2015-10-22 08:00","2015-10-28 18:00","연속",null,null,"신뢰도개선",201508080005,{"$f":"IF(ISERROR(VLOOKUP(D66,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D66,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[63,"경기","군포","신온양서서울#2 T/L","345kV 신온양서서울#2T/L Bay 변경공사","- Bay 변경(73 → 77) - 제어케이블 포설/철거 - 보호배전반 시험 등","2015-10-08 09:00","2015-10-13 18:00","2015-10-08 09:00","2015-10-13 18:00","연속",null,null,null,201508080001,{"$f":"IF(ISERROR(VLOOKUP(D67,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D67,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[64,"경기","군포","서서울S/S #2 M.Tr A","345kV 서서울S/S #2M.Tr","- Bay 변경(72 → 74)에 따른 간섭휴전","2015-10-14 09:00","2015-10-16 18:00","2015-10-14 09:00","2015-10-16 18:00","연속",null,null,null,201508080004,{"$f":"IF(ISERROR(VLOOKUP(D68,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D68,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[65,"경기","군포","신온양서서울#1 T/L","345kV 신온양서서울 #1T/L Bay변경공사","- Bay 변경(72 → 74) - 제어케이블 포설/철거 - 보호배전반 시험 등","2015-10-14 09:00","2015-10-19 18:00","2015-10-14 09:00","2015-10-19 18:00","연속",null,null,null,201508080002,{"$f":"IF(ISERROR(VLOOKUP(D69,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D69,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[66,"경기","군포","서서울S/S #2 M.Tr A","서서울S/S 345kV #2M.Tr 교체공사","345kV #2M.Tr 교체 및 부대공사 1식","2015-10-29 09:00","2015-11-28 18:00","2015-10-29 09:00","2015-11-28 18:00","연속",null,null,null,201508180204,{"$f":"IF(ISERROR(VLOOKUP(D70,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D70,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[67,"경기","군포","신안산S/S #4 M.Tr A","신안산 #4M.Tr 정밀점검공사","4M.Tr 및 OLTC 정밀점검","2015-10-05 09:00","2015-10-22 18:00","2015-10-05 09:00","2015-10-22 18:00","연속",null,null,null,201508120115,{"$f":"IF(ISERROR(VLOOKUP(D71,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D71,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[68,"경기","군포","신시흥신안산 T/L","345kV 화성-신안산T/L 피뢰기 설치공사","- 피뢰기 설치공사 1기(3조)","2015-10-25 07:00","2015-10-25 12:00","2015-10-25 07:00","2015-10-25 12:00","당일",null,null,null,201508130159,{"$f":"IF(ISERROR(VLOOKUP(D72,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D72,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[69,"경기","군포","화성신안산 T/L","2014-2015년 군포전력처 송전정비 협력회사 총액공사 시행","345kV 화성-신안산T/L 49~53호 전력선 교체 - 1.371km × 2가닥(하단 하내외측전선 소선)","2015-10-17 07:00","2015-10-18 18:00","2015-10-17 07:00","2015-10-18 18:00","연속",null,null,null,201508130222,{"$f":"IF(ISERROR(VLOOKUP(D73,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D73,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[70,"경기","동부","곤지암동서울#2 T/L","345kV 곤지암동서울#2T/L OPGW 항공구 정비(No.38-39)","345kV 곤지암동서울#2T/L OPGW 항공구 정비(No.38-39)","2015-10-20 09:00","2015-10-20 18:00","2015-10-20 09:00","2015-10-20 18:00","당일",null,null,null,201508180232,{"$f":"IF(ISERROR(VLOOKUP(D74,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D74,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[71,"경기","성남","서안성신진천#1 T/L","345kV 서안성신진천TL 전력선교체공사","345k서안성신진천#1TL 전력선교체(No.73~81)","2015-10-21 09:00","2015-10-25 18:00","2015-10-21 09:00","2015-10-25 18:00","연속",null,null,null,201508180061,{"$f":"IF(ISERROR(VLOOKUP(D75,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D75,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[72,"경기","성남","서안성신진천#2 T/L","345kV 서안성신진천TL 전력선교체공사","345k서안성신진천#2TL 전력선교체(No.73~81)","2015-10-26 09:00","2015-10-30 18:00","2015-10-26 09:00","2015-10-30 18:00","연속",null,null,null,201508180064,{"$f":"IF(ISERROR(VLOOKUP(D76,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D76,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[73,"경기","성남","신성남S/S #6 M.Tr A","신성남S/S #6M.Tr PCT,NCT이설","신성남S/S #6M.Tr PCT,NCT이설","2015-10-30 09:00","2015-10-30 18:00","2015-10-30 09:00","2015-10-30 18:00","당일",null,null,null,201508180037,{"$f":"IF(ISERROR(VLOOKUP(D77,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D77,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[74,"경기","성남","신성남S/S #5 M.Tr A","신성남S/S #5M.Tr 정밀점검","신성남S/S #5M.Tr 정밀점검","2015-10-15 09:00","2015-10-29 18:00","2015-10-15 09:00","2015-10-29 18:00","연속",null,null,null,201508180031,{"$f":"IF(ISERROR(VLOOKUP(D78,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D78,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[75,"경기","성남","신수원S/S #1 M.Tr A","신수원S/S #1M.Tr 2차 6144 GIS 정밀점검","신수원S/S #1M.Tr 2차 6144 GIS 정밀점검","2015-10-22 09:00","2015-10-24 18:00","2015-10-22 09:00","2015-10-24 18:00","연속",null,null,null,201508180008,{"$f":"IF(ISERROR(VLOOKUP(D79,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D79,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[76,"경기","성남","신수원S/S #2 M.Tr A","신수원S/S #2M.Tr 2차 6244 GIS 정밀점검","신수원S/S #2M.Tr 2차 6244 GIS 정밀점검","2015-10-26 09:00","2015-10-28 18:00","2015-10-26 09:00","2015-10-28 18:00","연속",null,null,null,201508180009,{"$f":"IF(ISERROR(VLOOKUP(D80,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D80,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[77,"경기","성남","신안성신성남#2 T/L","345kV 신안성신성남#2T/L 스페이서댐퍼점검(No.38~56)","345kV 신안성신성남#2T/L 스페이서댐퍼점검(No.38~56)","2015-10-24 08:00","2015-10-24 18:00","2015-10-24 08:00","2015-10-24 18:00","매일",null,null,null,201508170503,{"$f":"IF(ISERROR(VLOOKUP(D81,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D81,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[78,"경기","성남","신안성신성남#1 T/L","345kV 신안성신성남#1T/L 스페이서댐퍼점검(No.38~56)","345kV 신안성신성남#1T/L 스페이서댐퍼점검(No.38~56)","2015-10-31 08:00","2015-10-31 18:00","2015-10-31 08:00","2015-10-31 18:00","매일",null,null,null,201508170505,{"$f":"IF(ISERROR(VLOOKUP(D82,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D82,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[79,"경기","성남","신안성신용인#1 T/L","345kV 신안성신용인#1T/L 스페이서댐퍼점검(No.38~56)","345kV 신안성신용인#1T/L 스페이서댐퍼점검(No.38~56)","2015-10-31 08:00","2015-10-31 18:00","2015-10-31 08:00","2015-10-31 18:00","매일",null,null,null,201508170499,{"$f":"IF(ISERROR(VLOOKUP(D83,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D83,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[80,"경기","성남","신용인S/S 345kV #1 Sh.R","신용인S/S 345kVSh.R 집감반 경보 및 제어 수용","신용인S/S 345kVSh.R 집감반 경보 및 제어 수용","2015-10-29 09:00","2015-10-30 18:00","2015-10-29 09:00","2015-10-30 18:00","연속",null,null,null,201508180003,{"$f":"IF(ISERROR(VLOOKUP(D84,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D84,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[81,"경기","성남","신용인S/S #3 M.Tr A","3MTR 인출변경(76BAY 를 75BAY로)","345kV GIS(40kA 4000A) 재사용 철거 * 17CB 345kV GIS (63kA 6300A)설치 * 16CB GIS 교체에 따른 제어케이블 정비 등 기타부대공사","2015-10-20 09:00","2015-10-28 18:00","2015-10-20 09:00","2015-10-28 18:00","연속",null,null,null,201508060147,{"$f":"IF(ISERROR(VLOOKUP(D85,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D85,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[82,"경기","성남","신안성신용인#2 T/L","신안성신용인 2TL 인출변경(76BAY 를 75BAY로)","345kV GIS(40kA 4000A) 재사용 철거 * 17CB 345kV GIS (63kA 6300A)설치 * 16CB GIS 교체에 따른 제어케이블 정비 등 기타부대공사","2015-10-20 09:00","2015-10-28 18:00","2015-10-20 09:00","2015-10-28 18:00","연속",null,null,null,201508060146,{"$f":"IF(ISERROR(VLOOKUP(D86,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D86,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[83,"경기","직할","화성S/S #3 M.Tr A","화성S/S 345kV #3M.Tr","화성S/S #3M.Tr 3차측 Main CB, DS 보통점검","2015-10-03 10:00","2015-10-03 18:00","2015-10-03 10:00","2015-10-03 18:00","당일",null,null,null,201508170298,{"$f":"IF(ISERROR(VLOOKUP(D87,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D87,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[84,"경기","직할","아산화성#1 T/L","345kV신온양서서울 외 1개T/L 지장철탑이설공사","아산화성 : 철탑 신설 4기, 철거 9기","2015-10-31 07:00","2015-11-05 18:00","2015-10-31 07:00","2015-11-05 18:00","연속",null,null,"신뢰도개선",201508180230,{"$f":"IF(ISERROR(VLOOKUP(D88,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D88,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[85,"경기","평택","평택T/P #3,4 SU Tr 1차-#4 M.Tr 1차 GIS","평택T/P 7200GIS 점검","평택T/P 7200GIS 점검","2015-10-11 09:00","2015-10-11 18:00","2015-10-11 09:00","2015-10-11 18:00","당일",null,null,null,201508130315,{"$f":"IF(ISERROR(VLOOKUP(D89,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D89,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[86,"강원","동해","신제천동해#1 T/L","345kV 신제천-동해 T/L 전선마손 확인점검공사","345kV 신제천-동해#1T/L 전선마손 확인점검공사 (공사구간 : No.9 ~ No.70)","2015-10-01 09:00","2015-10-07 18:00","2015-10-01 09:00","2015-10-07 18:00","매일",null,null,null,201508170232,{"$f":"IF(ISERROR(VLOOKUP(D90,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D90,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[87,"강원","동해","신제천동해#2 T/L","345kV 신제천-동해 T/L 전선마손 확인점검공사","345kV 신제천-동해#2T/L 전선마손 확인점검공사 (공사구간 : No.9 ~ No.70)","2015-10-08 09:00","2015-10-15 18:00","2015-10-08 09:00","2015-10-15 18:00","매일",null,null,null,201508170234,{"$f":"IF(ISERROR(VLOOKUP(D91,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D91,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[88,"충북","청주","청원S/S #2 M.Tr A","15년 청주전력지사 345kV 변압기 정밀점검공사","345kV 변압기 정밀점검공사 및 M.Tr 2차 GIS 정밀점검","2015-10-05 10:00","2015-10-28 18:00","2015-10-05 10:00","2015-10-28 18:00","연속",null,null,null,201508070320,{"$f":"IF(ISERROR(VLOOKUP(D92,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D92,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[89,"충북","청주","청원S/S #3 M.Tr A","15년 하반기 청주전력지사 170kV GIS 정밀점검","345kV #3M.Tr 2차 GIS 정밀점검","2015-10-29 10:00","2015-10-31 18:00","2015-10-29 10:00","2015-10-31 18:00","연속",null,null,null,201508100075,{"$f":"IF(ISERROR(VLOOKUP(D93,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D93,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[90,"충북","충주","신진천S/S #4 M.Tr A","변전정비 협력회사 총액공사","주변압기 및 차단기 초기점검","2015-10-07 10:00","2015-10-09 18:00","2015-10-07 10:00","2015-10-09 18:00","연속",null,null,null,201508070276,{"$f":"IF(ISERROR(VLOOKUP(D94,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D94,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[91,"대전충남","대전","신계룡청양 T/L","345kV 신옥천-청양T/L 접속개소전선교체공사","[송전]신옥천-청양T/L 접속개소전선교체공사 - 청양전력소 작업","2015-10-19 07:00","2015-10-26 19:00","2015-10-19 07:00","2015-10-26 19:00","연속",null,null,null,201508180068,{"$f":"IF(ISERROR(VLOOKUP(D95,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D95,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[92,"대전충남","대전","신계룡S/S #2 M.Tr 1차 CB (7472)","○ 345kV 신계룡S/S 7472 GIS 정밀점검공사","7472GIS CB 정밀점검","2015-10-20 09:00","2015-10-23 18:00","2015-10-20 09:00","2015-10-23 18:00","연속",null,null,null,201508200020,{"$f":"IF(ISERROR(VLOOKUP(D96,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D96,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[93,"대전충남","대전","신계룡S/S #2 M.Tr A","○ 신계룡S/S 345kV GIS 정밀점검 및 #2M.Tr 보통점검","○ 345kV 신계룡S/S #2M.Tr 보통점검(1일) ○ 신계룡S/S 345kV GIS 정밀점검(4일) - 7400GIS CB 정밀점검 - 7402, 7462, 7422 DS 정밀점검","2015-10-26 09:00","2015-10-29 18:00","2015-10-26 09:00","2015-10-29 18:00","연속",null,null,null,201508170320,{"$f":"IF(ISERROR(VLOOKUP(D97,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D97,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[94,"대전충남","대전","신옥천청양 T/L","345kV 신옥천-청양T/L 접속개소전선교체공사","[송전]신옥천-청양T/L 접속개소전선교체공사 - No.56~65","2015-10-27 07:00","2015-11-05 19:00","2015-10-27 07:00","2015-11-05 19:00","연속",null,null,null,201508180072,{"$f":"IF(ISERROR(VLOOKUP(D98,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D98,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[95,"대전충남","서산","신당진S/S #3 M.Tr A","345kV 신당진개폐소 건설공사","- 개폐소 신설에 따른 변전소 구내 철구 가공지선 연결작업 ( 신당진S/S #3M.Tr POST측 ) - 안전 이격거리 확보","2015-10-06 09:30","2015-10-06 17:30","2015-10-06 09:30","2015-10-06 17:30","당일",null,null,null,201508060140,{"$f":"IF(ISERROR(VLOOKUP(D99,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D99,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[96,"대전충남","서산","신당진태안화력#2 T/L","345kV 신당진태안화력T/L 선종교체공사","345kV 신당진태안화력T/L 선종교체공사 관련작업","2015-10-17 07:00","2015-10-23 19:00","2015-10-17 07:00","2015-10-23 19:00","연속",null,null,"신뢰도개선",201508130024,{"$f":"IF(ISERROR(VLOOKUP(D100,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D100,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[97,"대전충남","서산","신당진태안화력#1 T/L","345kV 신당진태안화력T/L 선종교체공사","345kV 신당진태안화력T/L 선종교체공사 관련작업","2015-10-24 07:00","2015-10-30 19:00","2015-10-24 07:00","2015-10-30 19:00","연속",null,null,"신뢰도개선",201508130027,{"$f":"IF(ISERROR(VLOOKUP(D101,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D101,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[98,"대전충남","서산","신서산태안화력#2 T/L","345kV 신당진태안화력TL 선종교체공사","345kV 신당진태안화력TL 선종교체공사 관련작업","2015-10-03 07:00","2015-10-09 19:00","2015-10-03 07:00","2015-10-09 19:00","연속",null,null,"신뢰도개선",201508130020,{"$f":"IF(ISERROR(VLOOKUP(D102,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D102,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[99,"대전충남","서산","신서산태안화력#1 T/L","345kV 신당진태안화력T/L 선종교체공사","345kV 신당진태안화력T/L 선종교체공사 관련작업","2015-10-10 07:00","2015-10-16 19:00","2015-10-10 07:00","2015-10-16 19:00","연속",null,null,"신뢰도개선",201508130022,{"$f":"IF(ISERROR(VLOOKUP(D103,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D103,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[100,"대전충남","서산","신서산태안화력#1 T/L","345kV 신당진태안화력T/L 선종교체공사","345kV 신당진태안화력T/L 선종교체공사 관련작업","2015-10-31 07:00","2015-11-03 19:00","2015-10-31 07:00","2015-11-03 19:00","연속",null,null,"신뢰도개선",201508130029,{"$f":"IF(ISERROR(VLOOKUP(D104,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D104,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[101,"대전충남","서산","태안T/P 345kV #70 BUS","태안화력 362kV 장기사용 GIS 교체공사","○ 345kV GIS 대체 (#70BUS 모선 설치 및 PT 설치)","2015-10-13 09:00","2015-10-23 18:00","2015-10-13 09:00","2015-10-23 18:00","연속",null,null,null,201507100233,{"$f":"IF(ISERROR(VLOOKUP(D105,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D105,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[102,"대전충남","서산","태안T/P 4호기 1차 CB (7472)","태안T/P 345kV 74Bay 차단실패보호반 대체","태안T/P 345kV 73Bay 차단실패보호반 대체","2015-10-01 09:00","2015-10-07 18:00","2015-10-01 09:00","2015-10-07 18:00","연속",null,null,null,201508180042,{"$f":"IF(ISERROR(VLOOKUP(D106,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D106,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[103,"대전충남","서산","태안T/P TIE-4호기 1차 CB (7400)","태안T/P 345kV 74Bay 차단실패보호반 대체","태안T/P 345kV 73Bay 차단실패보호반 대체","2015-10-01 09:00","2015-10-07 18:00","2015-10-01 09:00","2015-10-07 18:00","연속",null,null,null,201508180041,{"$f":"IF(ISERROR(VLOOKUP(D107,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D107,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[104,"대전충남","서산","태안T/P 345kV #75 BUS","태안화력 362kV 장기사용 GIS 교체공사","○ 345kV GIS 대체(#75BUS 및 PT 설치 및 71Bay 차단기 설치)","2015-10-01 09:00","2015-10-12 18:00","2015-10-01 09:00","2015-10-12 18:00","연속",null,null,null,201507100235,{"$f":"IF(ISERROR(VLOOKUP(D108,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D108,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[105,"대전충남","아산","아산보령화력#1 T/L","345kV 아산보령화력T/L 전선교체공사","345kV 아산보령화력T/L 전선교체 No.1~4, 31~41","2015-10-05 07:00","2015-10-14 18:00","2015-10-05 07:00","2015-10-14 18:00","연속",null,null,"신뢰도개선",201508200006,{"$f":"IF(ISERROR(VLOOKUP(D109,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D109,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[106,"대전충남","청양","보령C/C #3 M.Tr 1차 CB (7372)","보령복합 362kV GIS 보통점검","○ 345kV 7372 GIS 보통점검","2015-10-13 09:00","2015-10-13 18:00","2015-10-13 09:00","2015-10-13 18:00","당일",null,null,null,201507100162,{"$f":"IF(ISERROR(VLOOKUP(D110,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D110,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[107,"대전충남","청양","청양보령#4 T/L","345kV 신보령 화력 1,2호기 계통 연계 공사","345kV 보령-청양 #4T/L 신설No.8 전선설치","2015-10-15 07:00","2015-10-22 18:00","2015-10-15 07:00","2015-10-22 18:00","연속",null,null,null,201508200005,{"$f":"IF(ISERROR(VLOOKUP(D111,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D111,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[108,"대전충남","청양","청양보령#1 T/L","345kV 신보령 화력 1,2호기 계통 연계 공사","345kV 청양-보령 #1T/L : 1.419km, ACSR480㎟[C] ⇒ HTACSR/AW480㎟[C]","2015-10-05 07:00","2015-10-14 18:00","2015-10-05 07:00","2015-10-14 18:00","연속",null,null,"신뢰도개선",201508200002,{"$f":"IF(ISERROR(VLOOKUP(D112,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D112,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[109,"전북","군산","군산S/S #3 M.Tr A","345kV 군산S/S #3M.Tr","군산S/S 345kV #3MTR 3차측 회로점검 군산S/S 345kV #3M.Tr","2015-10-01 09:00","2015-10-01 18:00","2015-10-01 09:00","2015-10-01 18:00","당일",null,null,null,201508120001,{"$f":"IF(ISERROR(VLOOKUP(D113,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D113,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[110,"전북","김제","신김제한빛NP#1 T/L","345kV 신김제-한빛#1T/L","345kV 신김제-한빛#1T/L 전선접속개소 해소공사 등 5개 공사 ○ 전선접속개소 해소공사(12일) (42-49호,175-180호) ○ 폴리머 점퍼지지애자 설치 (12일) (28-207호,33기,99SET) ○ 사선애자(26-132호,65기) 청소 (10일) ○ 차단기(7300,7371 CB) 정밀점검(14일) ○ 송전용 피뢰기 설치(196기) 공사(20일)","2015-10-01 08:00","2015-10-14 18:00","2015-10-01 08:00","2015-10-14 18:00","연속",null,null,null,201506050189,{"$f":"IF(ISERROR(VLOOKUP(D114,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D114,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[111,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주#1T/L","345kV 신남원-신광주#1T/L 송전선로 정밀점검 1.송전선로 정밀점검 : No.1~115호간","2015-10-01 09:00","2015-10-08 18:00","2015-10-01 09:00","2015-10-08 18:00","매일",null,null,null,201508180058,{"$f":"IF(ISERROR(VLOOKUP(D115,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D115,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[112,"전북","직할","신남원의령#2 T/L","345kV 신남원-의령#2 T/L","345kV 신남원-의령T/L 지장철탑이설공사 외 2건 1.철탑교체 : 2기(154호, 155호) 2.전선교체 : 147호 - 153호 3.정밀점검 : 136호 - 180호","2015-10-29 08:00","2015-11-05 18:00","2015-10-29 08:00","2015-11-05 18:00","연속",null,null,null,201508130358,{"$f":"IF(ISERROR(VLOOKUP(D116,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D116,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[113,"전북","직할","신남원의령#2 T/L","345kV 신남원-의령#2 T/L","345kV 신남원-의령T/L 지장철탑이설공사 외 2건 1.철탑교체 : 2기(154호, 155호) 2.전선교체 : 147호 - 153호 3.정밀점검 : 136호 - 180호","2015-10-15 08:00","2015-10-17 18:00","2015-10-15 08:00","2015-10-17 18:00","연속",null,null,null,201508130355,{"$f":"IF(ISERROR(VLOOKUP(D117,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D117,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[114,"전북","직할","신남원의령#1 T/L","345kV 신남원-의령#1 T/L","345kV 신남원-의령T/L 지장철탑이설공사 외 2건 1.철탑교체 : 2기(154호, 155호) 2.전선교체 : 147호 - 153호 3.정밀점검 : 136호 - 180호","2015-10-18 08:00","2015-10-28 18:00","2015-10-18 08:00","2015-10-28 18:00","연속",null,null,null,201508130356,{"$f":"IF(ISERROR(VLOOKUP(D118,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D118,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[115,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원#1TL","장기사용 기타설비 대체공사(LA)","2015-10-12 09:00","2015-10-12 18:00","2015-10-12 09:00","2015-10-12 18:00","당일",null,null,null,201508180315,{"$f":"IF(ISERROR(VLOOKUP(D119,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D119,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[116,"광주전남","강진","신화순신강진#1 T/L","신화순-신강진#1T/L(신강진S/S 362kV 장기사용 개폐장치 대체)","72Bay Hybrid GIS화","2015-10-03 09:00","2015-12-02 18:00","2015-10-03 09:00","2015-12-02 18:00","연속",null,null,null,201508100198,{"$f":"IF(ISERROR(VLOOKUP(D120,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D120,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[117,"광주전남","강진","신강진S/S 345kV #1 BUS","신화순-신강진#1T/L(신강진S/S 362kV 장기사용 개폐장치 대체)","362kV Hybrid GIS 대체","2015-10-03 09:00","2015-10-03 18:00","2015-10-03 09:00","2015-10-03 18:00","당일",null,null,null,201508100199,{"$f":"IF(ISERROR(VLOOKUP(D121,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D121,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[118,"광주전남","강진","신강진S/S 345kV #2 BUS","신화순-신강진#1T/L(신강진S/S 362kV 장기사용 개폐장치 대체)","362kV Hybrid GIS 대체","2015-10-04 09:00","2015-10-04 18:00","2015-10-04 09:00","2015-10-04 18:00","당일",null,null,null,201508100200,{"$f":"IF(ISERROR(VLOOKUP(D122,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D122,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[119,"광주전남","강진","신강진광양#1 T/L","신강진-광양#1 T/L (345kV 신강진S/S 노후배전반 정비공사)","345kV 신강진S/S 노후배전반 정비공사 - 신강진-광양 #1T/L 제어케이블 결선","2015-10-05 09:00","2015-10-08 18:00","2015-09-30 09:00","2015-10-02 18:00","연속",null,null,null,201507280061,{"$f":"IF(ISERROR(VLOOKUP(D123,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D123,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[120,"광주전남","강진","신강진S/S #2 M.Tr A","신강진S/S #2 M.Tr (345kV 신강진S/S 노후배전반 정비공사)","345kV 신강진S/S 노후배전반 정비공사 - 신강진S/S #2M.Tr 관련 제어케이블 결선","2015-10-05 09:00","2015-10-08 18:00","2015-10-05 09:00","2015-10-08 18:00","연속",null,null,null,201507280071,{"$f":"IF(ISERROR(VLOOKUP(D124,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D124,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[121,"광주전남","강진","신강진광양#2 T/L","신강진광양#2 T/L (신강진S/S 노후배전반 정비공사)","345kV 신강진S/S 노후배전반 정비공사 - 신강진광양#2 T/L 관련 제어케이블 결선","2015-10-12 09:00","2015-10-16 18:00","2015-10-26 09:00","2015-10-30 18:00","연속",null,null,null,201508170353,{"$f":"IF(ISERROR(VLOOKUP(D125,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D125,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[122,"광주전남","강진","신강진S/S #3 M.Tr A","신강진S/S #3 M.Tr (신강진S/S 노후배전반 정비공사)","345kV 신강진S/S 노후배전반 정비공사 - 신강진S/S #3M.Tr 1,2,3차 관련 제어케이블 결선","2015-10-12 09:00","2015-10-16 18:00","2015-10-12 09:00","2015-10-16 18:00","연속",null,null,null,201508170348,{"$f":"IF(ISERROR(VLOOKUP(D126,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D126,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[123,"광주전남","광주","신화순S/S #3M.Tr A","신화순S/S 345kV #3M.Tr(변전협력공사)","2014~15년 광주전력소 변전정비 협력회사 총액공사, #2S.Tr 보통점검, 4385 DS 보통점검","2015-10-01 09:00","2015-10-01 18:00","2015-10-01 09:00","2015-10-01 18:00","연속",null,null,null,201507130350,{"$f":"IF(ISERROR(VLOOKUP(D127,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D127,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[124,"광주전남","순천","광양하동화력#1 T/L","광양-하동화력#1T/L(전력선 교체공사)","345kV 광양-하동TP T/L 27~29,32~38호 전력선 교체공사 - 전선교체 : 5.388C-km - 스페이서 댐퍼교체 : 342EA","2015-10-11 07:00","2015-10-20 18:00","2015-10-12 07:00","2015-10-19 18:00","연속",null,null,"신뢰도개선",201508130402,{"$f":"IF(ISERROR(VLOOKUP(D128,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D128,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[125,"광주전남","순천","광양하동화력#2 T/L","광양-하동화력#2T/L(전력선 교체공사)","345kV 광양-하동TP T/L 27~29,32~38호 전력선 교체공사 - 전선교체 : 5.388C-km - 스페이서 댐퍼교체 : 342EA","2015-10-02 07:00","2015-10-10 18:00","2015-10-03 07:00","2015-10-11 18:00","연속",null,null,null,201508130401,{"$f":"IF(ISERROR(VLOOKUP(D129,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D129,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[126,"광주전남","순천","광양율촌CC T/L","광양S/S 광양-율촌CC T/L(장기사용 배전반 대체공사)","순천전력지사 장기사용 배전반 대체공사 - 345kV 73Bay B/F PNL 교체","2015-10-19 09:00","2015-10-23 18:00","2015-10-19 09:00","2015-10-23 18:00","연속",null,null,null,201507230009,{"$f":"IF(ISERROR(VLOOKUP(D130,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D130,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[127,"광주전남","직할","신광주한빛NP#2 T/L","신광주한빛NP#2 T/L(345kV 피뢰기 설치공사)","발전소 연계설비 피뢰기 설치","2015-10-12 09:00","2015-10-20 18:00","2015-10-15 09:00","2015-10-23 18:00","연속",null,null,"신뢰도개선",201508120170,{"$f":"IF(ISERROR(VLOOKUP(D131,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D131,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[128,"광주전남","직할","한빛1NP-한빛2NP #2 T/L","2015년 가공송전선로순시점검위탁공사","정밀점검 5기","2015-10-22 13:00","2015-10-22 18:00","2015-10-25 13:00","2015-10-25 18:00","당일",null,null,null,201508100076,{"$f":"IF(ISERROR(VLOOKUP(D132,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D132,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[129,"광주전남","직할","신남원한빛NP#1 T/L","신남원한빛NP#1T/L(345kV 피뢰기 설치공사)","발전소 연계설비 피뢰기 설치","2015-10-26 09:00","2015-10-30 18:00","2015-10-26 09:00","2015-10-30 18:00","연속",null,null,null,201508120169,{"$f":"IF(ISERROR(VLOOKUP(D133,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D133,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[130,"광주전남","직할","한빛2NP-한빛3NP #4 T/L","345kV한빛연락#4T/L","가공송전순시점검위탁공사(345kV한빛연락#4T/L 정밀점검)","2015-10-23 08:00","2015-10-23 18:00","2015-10-31 08:00","2015-10-31 18:00","당일",null,null,null,201508200048,{"$f":"IF(ISERROR(VLOOKUP(D134,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D134,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[131,"광주전남","직할","한빛1NP-한빛2NP #1 T/L","한빛연락#1 T/L(345kV 피뢰기 설치공사)","발전소 연계설비 피뢰기 설치","2015-10-24 09:00","2015-10-24 18:00","2015-10-24 09:00","2015-10-24 18:00","당일",null,null,null,201508120141,{"$f":"IF(ISERROR(VLOOKUP(D135,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D135,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[132,"대구경북","경산","울주신경산#1 T/L","송전선로 정밀점검 및 애자절연저항측정, 피뢰기 설치","- 122기 정밀 점검, 애자 절연저항 측정 - 피뢰기 설치","2015-10-26 08:00","2015-11-05 18:00","2015-10-26 08:00","2015-11-05 18:00","연속",null,null,null,201508110038,{"$f":"IF(ISERROR(VLOOKUP(D136,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D136,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[133,"대구경북","달성","고령S/S #4 M.Tr A","변압기 보호반 판넬교체","변압기 보호반판넬교체","2015-10-17 09:00","2015-10-19 18:00","2015-10-17 09:00","2015-10-19 18:00","연속",null,null,null,201507030032,{"$f":"IF(ISERROR(VLOOKUP(D137,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D137,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[134,"대구경북","영주","신영주S/S #1 M.Tr A","신영주S/S 362kV 옥외철구 GIS화 공사(GIS 기초 PHC 설치)","신영주S/S 362kV 옥외철구 설비 GIS화 공사 - GIS 기초 PHC 설치를 위한 안전이격확보","2015-10-12 09:00","2015-10-15 18:00","2015-10-12 09:00","2015-10-15 18:00","연속",null,null,null,201508130259,{"$f":"IF(ISERROR(VLOOKUP(D138,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D138,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[135,"대구경북","영주","신영주안동CC T/L","신영주S/S 362kV 옥외철구 GIS화 공사(74Bay 보호반 이설)","신영주S/S 362kV 옥외철구 설비 GIS화 공사 - 74Bay 보호반 이설(로컬동 → 임시제어동)","2015-10-31 09:00","2015-11-13 18:00","2015-10-31 09:00","2015-11-13 18:00","연속",null,null,null,201508130256,{"$f":"IF(ISERROR(VLOOKUP(D139,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D139,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[136,"대구경북","영주","신영주S/S #2 M.Tr A","신영주S/S 362kV 옥외철구 GIS화 공사(74Bay 보호반 이설)","신영주S/S 362kV 옥외철구 설비 GIS화 공사 -74Bay 보호반 이설(로컬동 → 임시제어동)","2015-10-31 09:00","2015-11-13 18:00","2015-10-31 09:00","2015-11-13 18:00","연속",null,null,null,201508130260,{"$f":"IF(ISERROR(VLOOKUP(D140,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D140,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[137,"대구경북","영주","신영주청송PP T/L","신영주S/S 362kV 옥외철구 GIS화 공사(73Bay 보호반 이설)","신영주S/S 362kV 옥외철구 설비 GIS화 공사 - 73Bay 보호반 이설(로컬동 → 임시제어동)","2015-10-16 09:00","2015-10-29 18:00","2015-10-16 09:00","2015-10-29 18:00","연속",null,null,null,201508130254,{"$f":"IF(ISERROR(VLOOKUP(D141,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D141,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[138,"대구경북","영주","신태백한울NP2#3 T/L","한울N/P 345kV 송전선로 인출정비공사","- 신태백-한울NP2 #3T/L No.1~No.4구간 경과지변경 - 신태백-한울NP2 #3T/L No.4 보조암철거 4조(기설 765kV No.4) - 신태백-한울NP2 #3T/L No.4-6 전력선교체(345kV 4B→765kV 6B)","2015-10-28 08:00","2015-11-18 19:00","2015-10-28 08:00","2015-11-18 19:00","연속",null,null,"신뢰도개선",201508040121,{"$f":"IF(ISERROR(VLOOKUP(D142,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D142,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[139,"대구경북","영주","신태백한울NP3 T/L","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2015-10-13 09:00","2015-11-22 18:00","2015-10-13 09:00","2015-11-22 18:00","연속",null,null,"신뢰도개선",201508030017,{"$f":"IF(ISERROR(VLOOKUP(D143,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D143,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[140,"대구경북","영주","한울3N/P 345kV #1 BUS","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2015-10-13 09:00","2015-10-24 18:00","2015-10-13 09:00","2015-10-24 18:00","연속",null,null,null,201508030013,{"$f":"IF(ISERROR(VLOOKUP(D144,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D144,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[141,"대구경북","영주","한울3N/P 345kV #2 BUS","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2015-10-06 09:00","2015-10-10 18:00","2015-10-06 09:00","2015-10-10 18:00","연속",null,null,null,201508030012,{"$f":"IF(ISERROR(VLOOKUP(D145,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D145,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[142,"대구경북","영주","한울3N/P 345kV #2 BUS","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2015-10-25 09:00","2015-10-30 18:00","2015-10-25 09:00","2015-10-30 18:00","연속",null,null,null,201508030015,{"$f":"IF(ISERROR(VLOOKUP(D146,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D146,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[143,"대구경북","포항","신포항신월성NP#1 T/L","345kV 신포항-신월성NP#1 등 5개T/L 피뢰기 설치공사","피뢰기 설치 : No.1~75, 전력선교체 : No.53~66","2015-10-30 08:00","2015-11-12 18:00","2015-10-30 08:00","2015-11-12 18:00","연속",null,null,null,201508210120,{"$f":"IF(ISERROR(VLOOKUP(D147,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D147,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[144,"대구경북","포항","신포항신월성NP#2 T/L","345kV 신포항-신월성NP#1,2T/L 전력선 교체공사","345kV 신포항-신월성NP#1,2T/L 전력선 교체(No.53~66)","2015-10-18 08:00","2015-10-29 18:00","2015-10-18 08:00","2015-10-29 18:00","연속",null,null,null,201508050128,{"$f":"IF(ISERROR(VLOOKUP(D148,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D148,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[145,"대구경북","포항","울주월성NP#2 T/L","154kV 입실-양북 송전선로 건설공사","154kV 입실-양북 송전선로 건설공사 인계인수점검","2015-10-02 09:00","2015-10-03 18:00","2015-10-02 09:00","2015-10-03 18:00","연속",null,null,null,201508070072,{"$f":"IF(ISERROR(VLOOKUP(D149,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D149,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[146,"대구경북","포항","월성NP신월성NP#1 T/L","345kV 신포항-신월성 NP#1 등 5개 T/L 피뢰기 설치공사","피뢰기설치 804SET, 268기(345kV 236기, 154kV 32기)중 345kV 월성연락#1 T/L 7기","2015-10-16 08:00","2015-10-17 18:00","2015-10-16 08:00","2015-10-17 18:00","연속",null,null,null,201508040056,{"$f":"IF(ISERROR(VLOOKUP(D150,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D150,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[147,"부산울산","동부산","울주고리NP#2 T/L","345kV 울주-고리NPT/L 피뢰기설치공사","피뢰기설치 145기, 435set","2015-10-04 09:00","2015-10-24 18:00","2015-10-04 09:00","2015-10-24 18:00","연속",null,null,null,201508040080,{"$f":"IF(ISERROR(VLOOKUP(D151,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D151,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[148,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산-신울산T/L 안전이격 확보공사","-No.48 기설철탑 철거 후 본철탑 설치","2015-10-16 08:00","2015-11-14 18:00","2015-10-16 08:00","2015-11-14 18:00","연속",null,null,null,201508070167,{"$f":"IF(ISERROR(VLOOKUP(D152,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D152,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[149,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산T/L 안전이격 확보공사","-가선로 구성(No.46~50)","2015-10-12 08:00","2015-10-15 18:00","2015-10-12 08:00","2015-10-15 18:00","연속",null,null,null,201508070165,{"$f":"IF(ISERROR(VLOOKUP(D153,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D153,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[150,"부산울산","서부산","서부산북부산#1 T/L","345kV 서부산-북부산T/L 등 8개T/L 이설공사","345kV OF 2000㎟ 케이블 0.177km 이설","2015-10-01 08:00","2015-11-05 18:00","2015-10-01 08:00","2015-11-05 18:00","연속",null,null,null,201508170514,{"$f":"IF(ISERROR(VLOOKUP(D154,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D154,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[151,"부산울산","서부산","서부산S/S #2 M.Tr A","서부산S/S 345kV #2M.Tr 냉각탑 교체","[주]서부산S/S 345kV #2M.Tr 냉각탑 교체 [병행]#2M.Tr 보호배전반 대체(김승언)","2015-10-19 10:00","2015-10-30 18:00","2015-10-19 10:00","2015-10-30 18:00","연속",null,null,null,201508130228,{"$f":"IF(ISERROR(VLOOKUP(D155,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D155,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[152,"부산울산","울산","신온산S/S 345kV #1 BUS","신온산S/S #4M.Tr 증설공사","- 주변압기 1상 166.7MVA * 3대 (1Bank) - 362kV GIS 2CB, 170kV GIS 2CCT - 기타 부대공사 * 1식","2015-10-01 09:00","2015-10-09 18:00","2015-10-01 09:00","2015-10-09 18:00","연속",null,null,null,201507070053,{"$f":"IF(ISERROR(VLOOKUP(D156,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D156,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[153,"부산울산","울산","신온산S/S #1 M.Tr A","345kV M.Tr 보통점검 및 OLTC 정밀점검공사","M.Tr 보통점검 및 OLTC 정밀점검, 4184 GCB 보통점검","2015-10-24 08:00","2015-10-25 18:00","2015-10-24 08:00","2015-10-25 18:00","연속",null,null,null,201508070229,{"$f":"IF(ISERROR(VLOOKUP(D157,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D157,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[154,"부산울산","울산","신온산S/S 345kV #2 BUS","신온산S/S #4M.Tr 증설공사","- 주변압기 1상 166.7MVA * 3대 (1Bank) - 362kV GIS 2CB, 170kV GIS 2CCT - 기타 부대공사 * 1식","2015-10-10 09:00","2015-10-19 18:00","2015-10-10 09:00","2015-10-19 18:00","연속",null,null,null,201507070054,{"$f":"IF(ISERROR(VLOOKUP(D158,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D158,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[155,"부산울산","울산","신울산신온산#2 T/L","신온산S/S #4M.Tr 증설공사(362kV GIS 설치)","- 362kV 4000A 50kA * 2CB 설치 - #1BUS 시험가압","2015-10-07 18:00","2015-10-09 18:00","2015-10-07 18:00","2015-10-09 18:00","연속",null,null,null,201508190217,{"$f":"IF(ISERROR(VLOOKUP(D159,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D159,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[156,"부산울산","울산","신울산신온산#2 T/L","신온산S/S #4M.Tr 증설공사(362kV GIS 설치)","- 362kV 4000A 50kA * 2CB 설치 - #2BUS 시험가압","2015-10-17 18:00","2015-10-19 18:00","2015-10-17 18:00","2015-10-19 18:00","연속",null,null,null,201508190218,{"$f":"IF(ISERROR(VLOOKUP(D160,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D160,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[157,"부산울산","울산","신울산S/S #4 M.Tr A","345kV M.Tr 보통점검 및 OLTC 정밀점검공사","M.Tr 보통점검 및 OLTC 정밀점검","2015-10-14 08:00","2015-10-16 18:00","2015-10-14 08:00","2015-10-16 18:00","연속",null,null,null,201508070232,{"$f":"IF(ISERROR(VLOOKUP(D161,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D161,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[158,"부산울산","울산","울산C/C #1 M.Tr A","울산화력S/Y 154kV 보호제어설비 전담운영공사","2차 GIS 관련 제어케이블 수용","2015-10-20 08:00","2015-10-20 14:00","2015-10-20 08:00","2015-10-20 14:00","연속",null,null,null,201508070172,{"$f":"IF(ISERROR(VLOOKUP(D162,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D162,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[159,"부산울산","울산","울산C/C #2 M.Tr A","울산화력S/Y 154kV 보호제어설비 전담운영공사","2차 GIS 관련 제어케이블 수용","2015-10-22 08:00","2015-10-22 14:00","2015-10-22 08:00","2015-10-22 14:00","연속",null,null,null,201508070173,{"$f":"IF(ISERROR(VLOOKUP(D163,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D163,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[160,"부산울산","울산","울주S/S 울주-고리NP#2T/L CB (7571)","2015년 362kV GIS 정밀점검공사","7571 GIS 정밀점검","2015-10-29 08:00","2015-10-31 18:00","2015-10-27 08:00","2015-10-29 18:00","연속",null,null,null,201508070233,{"$f":"IF(ISERROR(VLOOKUP(D164,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D164,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[161,"부산울산","울산","울주S/S #3 M.Tr A","345kV M.Tr 보통점검 및 OLTC 정밀점검공사","M.Tr 보통점검 및 OLTC 정밀점검, 7672 GIS 정밀점검","2015-10-26 08:00","2015-10-28 18:00","취소","취소","연속",null,null,null,201508070231,{"$f":"IF(ISERROR(VLOOKUP(D165,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D165,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[162,"경남","직할","신김해S/S #3 M.Tr A","신김해S/S 345kV #3M.Tr 정밀점검","신김해S/S 345kV #3M.Tr 정밀점검, 보호배전반 교체","2015-10-12 09:30","2015-10-21 17:30","2015-10-12 09:30","2015-10-21 17:30","연속",null,null,null,201507300135,{"$f":"IF(ISERROR(VLOOKUP(D166,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D166,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[163,"경남","직할","신마산신김해#1 T/L","안전이격확보 관련 휴전(조류착지방지장치 설치)","안전이격확보 관련 휴전(신김해-북부산T/L 조류착지방지장치 설치)","2015-10-08 08:30","2015-10-08 13:00","2015-10-08 08:30","2015-10-08 13:00","당일",null,null,null,201508100189,{"$f":"IF(ISERROR(VLOOKUP(D167,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D167,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[164,"경남","직할","신김해북부산#2 T/L","조류착지방지장치 설치","조류착지방지장치 설치(101~106호)","2015-10-08 08:30","2015-10-08 13:00","2015-10-08 08:30","2015-10-08 13:00","당일",null,null,null,201508100187,{"$f":"IF(ISERROR(VLOOKUP(D168,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D168,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[165,"경남","직할","신김해북부산#1 T/L","조류착지방지장치 설치","조류착지방지장치 설치(101~106호)","2015-10-07 08:30","2015-10-07 13:00","2015-10-07 08:30","2015-10-07 13:00","당일",null,null,null,201508100186,{"$f":"IF(ISERROR(VLOOKUP(D169,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D169,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[166,"경남","직할","신마산신김해#2 T/L","안전이격확보 관련 휴전(조류착지방지장치 설치)","안전이격확보 관련 휴전(신김해-북부산T/L 조류착지방지장치 설치)","2015-10-07 08:30","2015-10-07 13:00","2015-10-07 08:30","2015-10-07 13:00","당일",null,null,null,201508100188,{"$f":"IF(ISERROR(VLOOKUP(D170,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D170,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[167,"경남","진주","고령의령#2 T/L","345kV 고령-의령 #2T/L 정밀점검 공사(가공위탁)","고령-의령 #2T/L 1호~116호 정밀점검","2015-10-08 08:30","2015-10-14 18:30","2015-10-08 08:30","2015-10-14 18:30","연속",null,null,null,201508040029,{"$f":"IF(ISERROR(VLOOKUP(D171,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D171,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[168,"경남","진주","의령산청양수#2 T/L","진주전력지사 362kV 개폐장치 정밀점검 공사","의령-산청양수#2T/L CB 7371, DS 7361 정밀점검","2015-10-06 09:30","2015-10-08 20:30","2015-10-06 09:30","2015-10-08 20:30","연속",null,null,null,201508030080,{"$f":"IF(ISERROR(VLOOKUP(D172,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D172,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[169,"경남","진주","의령S/S 345kV #70 BUS","진주전력지사 362kV 개폐장치 정밀점검 공사","의령-산청양수#2T/L #70BUS측 DS 7351 정밀점검","2015-10-05 09:30","2015-10-06 09:30","2015-10-05 09:30","2015-10-06 09:30","연속",null,null,null,201508030079,{"$f":"IF(ISERROR(VLOOKUP(D173,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D173,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[170,"경남","진주","의령S/S 345kV #71 BUS","71 모선 보호반 대체","71 모선 보호반 대체","2015-10-27 09:30","2015-10-30 18:30","2015-10-27 09:30","2015-10-30 18:30","연속",null,null,null,201508070222,{"$f":"IF(ISERROR(VLOOKUP(D174,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D174,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[171,"경남","진주","의령S/S #2 M.Tr A","진주전력지사 362kV 개폐장치 정밀점검 공사","#2M.Tr 1차측 CB 7572, DS 7562 정밀점검","2015-10-27 09:30","2015-10-29 20:30","2015-10-27 09:30","2015-10-29 20:30","연속",null,null,null,201508030083,{"$f":"IF(ISERROR(VLOOKUP(D175,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D175,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[172,"경남","진주","의령S/S 345kV #75 BUS","진주전력지사 362kV 개폐장치 정밀점검 공사","75Bay #75BUS측 7552 DS 정밀점검","2015-10-26 09:30","2015-10-27 09:30","2015-10-26 09:30","2015-10-27 09:30","연속",null,null,null,201508030082,{"$f":"IF(ISERROR(VLOOKUP(D176,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D176,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[173,"경남","진주","의령S/S 345kV #76 BUS","76모선 보호반 대체","76모선 보호반 대체","2015-10-22 09:30","2015-10-25 18:30","2015-10-22 09:30","2015-10-25 18:30","연속",null,null,null,201508070221,{"$f":"IF(ISERROR(VLOOKUP(D177,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D177,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[174,"경남","진주","신남원의령#2 T/L","345kV 고령-의령 #2T/L 정밀점검 공사 관련 안전이격","345kV 고령-의령 #2T/L 정밀점검 공사 관련 안전이격","2015-10-13 08:30","2015-10-13 17:30","2015-10-13 08:30","2015-10-13 17:30","당일",null,null,null,201508040031,{"$f":"IF(ISERROR(VLOOKUP(D178,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D178,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[175,"경남","진주","하동T/P #3 M.Tr 1차 CB (7372)","하동T/P 73Bay B/F PNL 교체(7372)","하동T/P 73Bay B/F PNL 교체(7372)","2015-10-19 09:30","2015-10-22 18:30","2015-10-19 09:30","2015-10-22 18:30","연속",null,null,null,201508100119,{"$f":"IF(ISERROR(VLOOKUP(D179,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D179,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[176,"경남","진주","하동T/P TIE-#4 M.Tr 1차 CB (7400)","하동T/P 74Bay B/F PNL 교체공사(7400)","하동T/P 74Bay B/F PNL 교체(7400)","2015-10-10 09:30","2015-10-13 18:30","2015-10-10 09:30","2015-10-13 18:30","연속",null,null,null,201508100115,{"$f":"IF(ISERROR(VLOOKUP(D180,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D180,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[177,"경남","진주","하동T/P #4 M.Tr 1차 CB (7472)","하동T/P 74Bay B/F PNL 교체공사(7472)","하동T/P 74Bay B/F PNL 교체공사(7472)","2015-10-10 09:30","2015-10-13 18:30","2015-10-10 09:30","2015-10-13 18:30","연속",null,null,null,201508100116,{"$f":"IF(ISERROR(VLOOKUP(D181,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D181,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[178,"경남","통영","신마산삼천포화력#2 T/L","삼천포T/P 신마산-삼천포화력#2T/L GIS 가스누기보수","삼천포T/P 345kV 신마산-삼천포화력#2T/L GIS 인출DS부 가스누기개소 보수작업","2015-10-26 09:30","2015-10-27 18:30","2015-10-26 09:30","2015-10-27 18:30","연속",null,null,null,201508170309,{"$f":"IF(ISERROR(VLOOKUP(D182,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D182,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[179,"경남","통영","신고성S/S #4M.Tr A","신고성S/S #4M.Tr OLTC 정밀점검","신고성S/S #4M.Tr OLTC 정밀점검","2015-10-19 09:30","2015-10-21 18:30","2015-10-19 09:30","2015-10-21 18:30","연속",null,null,null,201508050189,{"$f":"IF(ISERROR(VLOOKUP(D183,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D183,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[180,"경남","통영","신고성삼천포화력#1 T/L","신고성S/S 345kV 7A, 7C Bay B/F 보호반 대체공사","신고성S/S 345kV 7A, 7C Bay B/F 보호반 대체공사","2015-10-17 07:00","2015-10-18 20:00","2015-10-17 07:00","2015-10-18 20:00","연속",null,null,null,201508050180,{"$f":"IF(ISERROR(VLOOKUP(D184,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D184,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[181,"경남","통영","신고성S/S #1 M.Tr A","신고성S/S #1M.Tr 점검 및 7D Bay B/F 보호반 대체","신고성S/S #1M.Tr OLTC 정밀점검 및 7C Bay B/F 보호반 대체공사","2015-10-14 09:30","2015-10-18 18:30","2015-10-14 09:30","2015-10-18 18:30","연속",null,null,null,201508050181,{"$f":"IF(ISERROR(VLOOKUP(D185,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D185,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[182,"경남","통영","신고성삼천포화력#2 T/L","신고성S/S 345kV 7B, 7D Bay B/F 보호반 대체공사","신고성S/S 345kV 7B, 7D Bay B/F 보호반 대체공사","2015-10-09 09:30","2015-10-11 18:30","2015-10-09 09:30","2015-10-11 18:30","연속",null,null,null,201508050179,{"$f":"IF(ISERROR(VLOOKUP(D186,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D186,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[183,"경남","통영","신고성S/S #2 M.Tr A","신고성S/S #2M.Tr 및 7D Bay B/F 보호반 대체공사","신고성S/S #2M.Tr 및 7D Bay B/F 보호반 대체공사","2015-10-05 09:30","2015-10-11 18:30","2015-10-05 09:30","2015-10-11 18:30","연속",null,null,null,201508050178,{"$f":"IF(ISERROR(VLOOKUP(D187,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D187,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[184,"경남","함안","북경남S/S 북경남-고령 #1T/L CB (7872)","북경남S/S 345kV 7872 GIS 초기점검 공사","북경남S/S 345kV 7872 GIS 초기점검 공사","2015-10-22 09:30","2015-10-23 17:30","2015-10-22 09:30","2015-10-23 17:30","연속",null,null,null,201507300052,{"$f":"IF(ISERROR(VLOOKUP(D188,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D188,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[185,"경남","함안","북경남S/S #4 M.Tr 2차-서대구#1T/L CB (7A00)","북경남S/S 345kV 7A00 GIS 초기점검 공사","북경남S/S 345kV 7A00 GIS 초기점검 공사","2015-10-20 09:30","2015-10-21 17:30","2015-10-20 09:30","2015-10-21 17:30","연속",null,null,null,201507090263,{"$f":"IF(ISERROR(VLOOKUP(D189,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D189,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[186,"경남","함안","북경남S/S #3 M.Tr 2차 CB (7871)","북경남S/S 345kV 7871 GIS 초기점검 공사","북경남S/S 345kV 7871 GIS 초기점검 공사","2015-10-07 09:30","2015-10-08 17:30","2015-10-07 09:30","2015-10-08 17:30","연속",null,null,null,201507090258,{"$f":"IF(ISERROR(VLOOKUP(D190,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D190,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[187,"경남","함안","북경남S/S #3M.Tr 2차-북경남고령#1T/L CB (7800)","북경남S/S 345kV 7800 GIS 초기점검 공사","북경남S/S 345kV 7800 GIS 초기점검 공사","2015-10-12 09:30","2015-10-13 17:30","2015-10-12 09:30","2015-10-13 17:30","연속",null,null,null,201507090259,{"$f":"IF(ISERROR(VLOOKUP(D191,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D191,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[188,"경남","함안","북경남S/S #4 M.Tr 2차 CB (7A71)","북경남S/S 345kV 7A71 GIS 초기점검 공사","북경남S/S 345kV 7A71 GIS 초기점검 공사","2015-10-14 09:30","2015-10-15 17:30","2015-10-14 09:30","2015-10-15 17:30","연속",null,null,null,201507090260,{"$f":"IF(ISERROR(VLOOKUP(D192,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D192,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[189,"경남","함안","신마산S/S #1 M.Tr A","신마산S/S 345kV #1M.Tr 변압기 초기점검 공사","신마산S/S 345kV #1M.Tr 변압기 초기점검, 1,2차 LA 보통점검, 3차 LA 초기점검, 6141DS 과열개소 보수, 집유정 청소","2015-10-06 09:30","2015-10-07 17:30","2015-10-06 09:30","2015-10-07 17:30","연속",null,null,null,201507300054,{"$f":"IF(ISERROR(VLOOKUP(D193,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D193,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[190,"경남","함안","신마산S/S #4 M.Tr A","신마산S/S 154kV 6444 GCB 교체공사","신마산S/S 154kV 6444 GCB 교체공사","2015-10-12 09:30","2015-10-15 17:30","2015-10-12 09:30","2015-10-15 17:30","연속",null,null,null,201507300044,{"$f":"IF(ISERROR(VLOOKUP(D194,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D194,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[191,"경남","함안","신마산S/S 신마산-신김해#2T/L CB (7372)","신마산S/S 345kV 7372 GCB 정밀점검 공사","신마산S/S 345kV 7372 GCB 정밀점검 공사","2015-10-12 09:30","2015-10-14 17:30","2015-10-12 09:30","2015-10-14 17:30","연속",null,null,null,201508180229,{"$f":"IF(ISERROR(VLOOKUP(D195,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D195,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[192,"경남","함안","신마산S/S 신마산-신김해#2T/L-TIE CB (7300)","신마산S/S 345kV 7300 GCB 정밀점검 공사","신마산S/S 345kV 7300 GCB 정밀점검 공사","2015-10-05 09:30","2015-10-07 17:30","2015-10-05 09:30","2015-10-07 17:30","연속",null,null,null,201507300043,{"$f":"IF(ISERROR(VLOOKUP(D196,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D196,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]

{"sheet":"154송부","index":2,"n_rows":315,"n_cols":16,"rows_kept":315,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2015년도 10월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","쌍문미아#2 T/L","미아S/S 170KV 장기사용 GIS 교체공사","170KV 장기사용 GIS 철거 및 신규 설치","2015-10-05 09:30","2015-11-02 17:00","2015-10-05 09:30","2015-11-02 17:00","연속",null,null,"신뢰도개선",201508150001,{"$f":"IF(ISERROR(VLOOKUP(D5,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D5,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[2,"서울","성동","휘경종암#2 T/L","휘경S/S 170kV 장기사용 GIS 대체공사","휘경종암#2T/L GIS 대체","2015-10-24 09:00","2015-11-18 18:00","2015-10-24 09:00","2015-11-18 18:00","연속",null,null,"신뢰도개선",201508190164,{"$f":"IF(ISERROR(VLOOKUP(D6,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D6,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[3,"서울","성동","성동휘경#1 T/L","휘경S/S 170kV 장기사용 GIS 대체공사","성동휘경#1T/L GIS 대체","2015-10-24 09:00","2015-11-18 18:00","2015-10-24 09:00","2015-11-18 18:00","연속",null,null,"신뢰도개선",201508190168,{"$f":"IF(ISERROR(VLOOKUP(D7,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D7,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[4,"서울","중부","수색S/S 154kV #2 BUS","14~15년 중부P/O 변전협력회사 총액공사","#1M.Tr LS 보통점검","2015-10-03 14:00","2015-10-03 18:00","2015-10-03 14:00","2015-10-03 18:00","연속",null,null,null,201508100067,{"$f":"IF(ISERROR(VLOOKUP(D8,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D8,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[5,"서울","중부","수색S/S 154kV #1 BUS","14~15년 중부P/O 변전협력회사 총액공사","#4M.Tr LS 보통점검","2015-10-17 08:00","2015-10-17 14:00","2015-10-17 08:00","2015-10-17 14:00","연속",null,null,null,201508100062,{"$f":"IF(ISERROR(VLOOKUP(D9,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D9,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[6,"서울","중부","수색S/S 154kV #2 BUS","14~15년 중부P/O 변전협력회사 총액공사","#4M.Tr LS 보통점검","2015-10-17 14:00","2015-10-17 18:00","2015-10-17 14:00","2015-10-17 18:00","연속",null,null,null,201508100064,{"$f":"IF(ISERROR(VLOOKUP(D10,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D10,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[7,"서울","중부","수색S/S 154kV #1 BUS","14~15년 중부P/O 변전협력회사 총액공사","#1M.Tr LS 보통점검","2015-10-03 08:00","2015-10-03 14:00","2015-10-03 08:00","2015-10-03 14:00","연속",null,null,null,201508100061,{"$f":"IF(ISERROR(VLOOKUP(D11,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D11,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[8,"서울","중부","양주은평#1 T/L","154kV 양주-은평T/L 안전이격거리 확보공사","철탑 11m 상향 * 2기 전력선 교체(인상) 작업 *1.240 c-km","2015-10-12 09:00","2015-10-18 18:00","2015-10-12 09:00","2015-10-18 18:00","연속",null,null,null,201508170343,{"$f":"IF(ISERROR(VLOOKUP(D12,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D12,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[9,"서울","중부","양주은평#2 T/L","154kV 양주-은평T/L 안전이격거리 확보공사","철탑 11m 상향 * 2기 전력선 교체(인상) 작업 *1.240 c-km","2015-10-05 09:00","2015-10-11 18:00","2015-10-05 09:00","2015-10-11 18:00","연속",null,null,null,201508170338,{"$f":"IF(ISERROR(VLOOKUP(D13,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D13,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[10,"서울","직할","마포신촌 T/L","신촌S/S 154kV 장기사용 GIS 대체","마포신촌T/L GIS 대체","2015-10-04 08:00","2015-10-23 18:00","2015-10-04 08:00","2015-10-23 18:00","연속",null,null,null,201507090041,{"$f":"IF(ISERROR(VLOOKUP(D14,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D14,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[11,"서울","직할","신촌순화 T/L","신촌S/S 154kV 장기사용 GIS 대체","신촌순화T/L GIS 교체","2015-10-25 08:00","2015-11-13 18:00","2015-10-25 08:00","2015-11-13 18:00","연속",null,null,null,201507090102,{"$f":"IF(ISERROR(VLOOKUP(D15,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D15,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[12,"서울","직할","방산중앙#1 T/L","중앙S/S 170kV GIS 대체공사","중앙S/S 170kV GIS 대체공사(#2M.Tr 1차, 방산중앙#1T/L)","2015-10-24 09:30","2015-11-14 18:00","2015-10-24 09:30","2015-11-14 18:00","당일",null,null,null,201508190247,{"$f":"IF(ISERROR(VLOOKUP(D16,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D16,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[13,"남서울","강남","신사논현#1 T/L","신사-논현#1T/L 보호배전반 정기점검","신사-논현#1T/L 보호배전반 정기점검","2015-10-12 10:00","2015-10-12 14:00","2015-10-12 10:00","2015-10-12 14:00","당일",null,null,null,201508170198,{"$f":"IF(ISERROR(VLOOKUP(D17,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D17,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[14,"남서울","강남","신사논현#2 T/L","신사-논현#2T/L 보호배전반 정기점검","신사-논현#2T/L 보호배전반 정기점검","2015-10-12 14:00","2015-10-12 18:00","2015-10-12 14:00","2015-10-12 18:00","당일",null,null,null,201508170200,{"$f":"IF(ISERROR(VLOOKUP(D18,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D18,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[15,"남서울","강남","신양재역삼#2 T/L","신양재-역삼#2T/L 보호배전반 정기점검","신양재-역삼#2T/L 보호배전반 정기점검","2015-10-13 12:00","2015-10-13 15:00","취소","취소","당일",null,null,null,201508170208,{"$f":"IF(ISERROR(VLOOKUP(D19,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D19,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[16,"남서울","강남","신양재역삼#1 T/L","신양재-역삼#1T/L 보호배전반 정기점검","신양재-역삼#1T/L 보호배전반 정기점검","2015-10-13 09:00","2015-10-13 12:00","취소","취소","당일",null,null,null,201508170207,{"$f":"IF(ISERROR(VLOOKUP(D20,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D20,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[17,"남서울","강남","신양재역삼#3 T/L","신양재-역삼#3T/L 보호배전반 정기점검","신양재-역삼#3T/L 보호배전반 정기점검","2015-10-13 15:00","2015-10-13 18:00","취소","취소","당일",null,null,null,201508170209,{"$f":"IF(ISERROR(VLOOKUP(D21,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D21,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[18,"남서울","강남","신양재신사#3 T/L","신양재-신사#3T/L 구형 절연통보호장치 교체공사","신양재-신사#3T/L 구형 절연통보호장치 교체공사","2015-10-05 10:00","2015-10-07 14:00","2015-10-05 10:00","2015-10-07 14:00","연속",null,null,null,201508130107,{"$f":"IF(ISERROR(VLOOKUP(D22,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D22,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[19,"남서울","동서울","동서울송파#2 T/L","동서울-송파#2T/L 보호배전반 정기점검","동서울-송파#2T/L 보호배전반 정기점검","2015-10-19 10:00","2015-10-19 13:30","2015-10-19 10:00","2015-10-19 13:30","당일",null,null,null,201508170195,{"$f":"IF(ISERROR(VLOOKUP(D23,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D23,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[20,"남서울","동서울","천호구의#1 T/L","154kV 천호-구의T/L 천호대교 횡간구간 교체공사","ㅇ 공사목적 : 노후 OF케이블 교체로 절연유 누유 및 고장 예방 ㅇ 공사개요 - 구간 : 154kV 천호-구의T/L J/B#5~J/B#8(1-1) - 선종 및 길이 : 154㎸ XLPE 2,000㎟ × 2회선, 1.174㎞ - 케이블 접속 : 보통접속2개소","2015-10-01 10:00","2015-12-30 17:00","2015-10-01 10:00","2015-12-30 17:00","연속",null,null,null,201508170212,{"$f":"IF(ISERROR(VLOOKUP(D24,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D24,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[21,"남서울","동서울","천호구의#2 T/L","천호-구의#2T/L 보호배전반 정기점검","천호-구의#2T/L 보호배전반 정기점검","2015-10-19 14:00","2015-10-19 18:00","2015-10-19 14:00","2015-10-19 18:00","당일",null,null,null,201508170196,{"$f":"IF(ISERROR(VLOOKUP(D25,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D25,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[22,"남서울","영서","가양등촌#1 T/L","가양S/S 장기사용 170kV GIS 대체공사","170kV GIS 5CCT 대체","2015-10-12 09:00","2015-11-16 18:00","2015-10-12 09:00","2015-11-16 18:00","연속",null,null,null,201507210026,{"$f":"IF(ISERROR(VLOOKUP(D26,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D26,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[23,"남서울","영서","광명구공#2 T/L","170kV GIS 정밀점검공사(광명S/S 광명-구공#2T/L)","170kV GIS 정밀점검공사(광명S/S 광명-구공#2T/L)","2015-10-16 09:00","2015-10-18 18:00","2015-10-26 09:00","2015-10-28 18:00","연속",null,null,null,201508190137,{"$f":"IF(ISERROR(VLOOKUP(D27,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D27,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[24,"남서울","영서","독산S/S 154kV #2 BUS","170kV GIS 정밀점검공사(독산S/S 대림-독산T/L)","170kV GIS 정밀점검공사(독산S/S 대림-독산T/L)","2015-10-05 09:00","2015-10-06 14:00","취소","취소","연속",null,null,null,201508190099,{"$f":"IF(ISERROR(VLOOKUP(D28,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D28,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[25,"남서울","영서","독산S/S 154kV #1 BUS","170kV GIS 정밀점검공사(독산S/S 대림-독산T/L)","170kV GIS 정밀점검공사(독산S/S 대림-독산T/L)","2015-10-06 14:00","2015-10-08 18:00","취소","취소","연속",null,null,null,201508190101,{"$f":"IF(ISERROR(VLOOKUP(D29,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D29,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[26,"남서울","영서","독산대방#1 T/L","170kV GIS 정밀점검공사(독산S/S 독산-대방#1T/L)","170kV GIS 정밀점검공사(독산S/S 독산-대방#1T/L)","2015-10-12 09:00","2015-10-13 18:00","2015-10-19 09:00","2015-10-21 18:00","연속",null,null,null,201508190121,{"$f":"IF(ISERROR(VLOOKUP(D30,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D30,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[27,"남서울","영서","독산S/S 154kV #2 BUS","170kV GIS 정밀점검공사(독산S/S 독산-대방#1T/L)","170kV GIS 정밀점검공사(독산S/S 독산-대방#1T/L)","2015-10-12 09:00","2015-10-12 18:00","2015-10-19 09:00","2015-10-20 09:00","연속",null,null,null,201508190127,{"$f":"IF(ISERROR(VLOOKUP(D31,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D31,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[28,"남서울","영서","독산S/S 154kV #1 BUS","170kV GIS 정밀점검공사(독산S/S 독산-대방#1T/L)","170kV GIS 정밀점검공사(독산S/S 독산-대방#1T/L)","2015-10-12 18:00","2015-10-13 18:00","2015-10-20 09:00","2015-10-21 18:00","연속",null,null,null,201508190128,{"$f":"IF(ISERROR(VLOOKUP(D32,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D32,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[29,"남서울","영서","독산대방#2 T/L","170kV GIS 정밀점검공사(독산S/S 독산-대방#2T/L)","170kV GIS 정밀점검공사(독산S/S 독산-대방#2T/L)","2015-10-14 09:00","2015-10-15 18:00","2015-10-22 09:00","2015-10-24 09:00","연속",null,null,null,201508190122,{"$f":"IF(ISERROR(VLOOKUP(D33,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D33,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[30,"남서울","영서","독산S/S 154kV #1 BUS","170kV GIS 정밀점검공사(독산S/S 독산-대방#2T/L)","170kV GIS 정밀점검공사(독산S/S 독산-대방#2T/L)","2015-10-14 18:00","2015-10-15 18:00","2015-10-23 09:00","2015-10-24 18:00","연속",null,null,null,201508190134,{"$f":"IF(ISERROR(VLOOKUP(D34,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D34,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[31,"남서울","영서","독산S/S 154kV #2 BUS","170kV GIS 정밀점검공사(독산S/S 독산-대방#2T/L)","170kV GIS 정밀점검공사(독산S/S 독산-대방#2T/L)","2015-10-14 09:00","2015-10-14 18:00","2015-10-22 09:00","2015-10-23 09:00","연속",null,null,null,201508190133,{"$f":"IF(ISERROR(VLOOKUP(D35,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D35,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[32,"남서울","직할","대방신길#2 T/L","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-10-19 09:00","2015-11-20 18:00","2015-10-29 09:00","2015-11-21 18:00","연속",null,null,null,201508110044,{"$f":"IF(ISERROR(VLOOKUP(D36,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D36,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[33,"남서울","직할","신길S/S 154kV #1 BUS","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-10-25 09:00","2015-11-05 18:00","2015-11-02 15:00","2015-11-13 15:00","연속",null,null,null,201508110047,{"$f":"IF(ISERROR(VLOOKUP(D37,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D37,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[34,"남서울","직할","신길S/S 154kV #2 BUS","신길S/S 170kV 장기사용 GIS 대체공사","신길S/S 170kV 장기사용 GIS 대체공사","2015-10-19 09:00","2015-10-24 18:00","2015-10-29 09:00","2015-11-02 15:00","연속",null,null,null,201508110045,{"$f":"IF(ISERROR(VLOOKUP(D38,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D38,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[35,"인천","김포","양촌양곡#2 T/L","154kV 양촌양곡T/L 지장철탑 이설공사","□ 김포학운4산업단지 및 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.2, 9, 13 이설 - No.2 ,9 본철탑 이설, No.13 가철탑 이설","2015-10-03 08:00","2015-10-07 18:00","2015-10-03 08:00","2015-10-07 18:00","연속",null,null,null,201508110200,{"$f":"IF(ISERROR(VLOOKUP(D39,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D39,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[36,"인천","김포","양촌양곡#1 T/L","154kV 양촌양곡T/L 지장철탑 이설공사","□ 김포학운4산업단지 및 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.2, 9, 13 이설 - No.2 ,9 본철탑 이설, No.13 가철탑 이설","2015-10-08 08:00","2015-10-12 18:00","2015-10-08 08:00","2015-10-12 18:00","연속",null,null,null,201508110201,{"$f":"IF(ISERROR(VLOOKUP(D40,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D40,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[37,"인천","김포","양촌양곡#2 T/L","154kV 양촌양곡T/L 지장철탑 이설공사","□ 김포학운4산업단지 및 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.2, 9, 13 이설 - No.2 ,9 본철탑 이설, No.13 가철탑 이설","2015-10-24 08:00","2015-10-27 18:00","2015-10-24 08:00","2015-10-27 18:00","연속",null,null,null,201508110203,{"$f":"IF(ISERROR(VLOOKUP(D41,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D41,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[38,"인천","시흥","오봉동춘#1 T/L","154kV 고잔분기 지중T/L 건설공사","○ 선종 및 회선수, 길이 : 154kV XLPE 2000SQ, 4회선-1.4km ○ 병행공사 - 신설 154kV 고잔S/S 건설공사","2015-10-30 09:00","2015-11-30 18:00","2015-10-30 09:00","2015-11-30 18:00","연속",null,null,null,201508060045,{"$f":"IF(ISERROR(VLOOKUP(D42,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D42,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[39,"인천","인천","서인천C/C #8 G.Tr 1차 GIS","서인천복합S/Y #8G.Tr 1차 GIS(6833) 보통점검","서인천복합S/Y #8G.Tr 1차 GIS(6833) 보통점검","2015-10-12 09:00","2015-10-12 18:00","취소","취소","당일",null,null,null,201508100043,{"$f":"IF(ISERROR(VLOOKUP(D43,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D43,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[40,"인천","직할","계양원창 T/L","345kV가정루원시티 지중화 정비공사","345kV 가정루원시티 지중화 정비공사 ※ 금번작업 : 신가좌-인천CC #2T/L 연긴선 해체 및 설치기간 휴 전(전선 긴선 해체에 따른 선간 단락으로 정전 방지) -신설:3기[4회선(345kV 신가좌-인천CC No.18),2회선 C/H(154kV, 345kV)] -교체:1기[345kV 신가좌-인천CC No.19 Enclosing 공법으로 철탑교체]","2015-10-02 08:00","2015-10-02 18:00","2015-10-02 08:00","2015-10-02 18:00","연속",null,null,null,201508200063,{"$f":"IF(ISERROR(VLOOKUP(D44,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D44,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[41,"인천","직할","계양원창 T/L","345kV가정루원시티 지중화 정비공사","345kV 가정루원시티 지중화 정비공사 ※ 금번작업 : 신가좌-인천CC #1T/L 연긴선 해체 및 설치기간 휴 전(전선 긴선 해체에 따른 선간 단락으로 정전 방지) -신설:3기[4회선(345kV 신가좌-인천CC No.18),2회선 C/H(154kV, 345kV)] -교체:1기[345kV 신가좌-인천CC No.19 Enclosing 공법으로 철탑교체]","2015-10-28 08:00","2015-10-28 18:00","2015-10-28 08:00","2015-10-28 18:00","연속",null,null,null,201508200059,{"$f":"IF(ISERROR(VLOOKUP(D45,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D45,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[42,"인천","직할","계양원창 T/L","345kV가정루원시티 지중화 정비공사","345kV 가정루원시티 지중화 정비공사 ※ 금번작업 : 신가좌-인천CC #2T/L 연긴선 해체 및 설치기간 휴 전(전선 긴선 해체에 따른 선간 단락으로 정전 방지) -신설:3기[4회선(345kV 신가좌-인천CC No.18),2회선 C/H(154kV, 345kV)] -교체:1기[345kV 신가좌-인천CC No.19 Enclosing 공법으로 철탑교체]","2015-10-14 08:00","2015-10-14 18:00","2015-10-14 08:00","2015-10-14 18:00","연속",null,null,null,201508200061,{"$f":"IF(ISERROR(VLOOKUP(D46,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D46,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[43,"인천","직할","계양원창 T/L","345kV가정루원시티 지중화 정비공사","345kV 가정루원시티 지중화 정비공사 ※ 금번작업 : 신가좌-인천CC #1T/L 연긴선 해체 및 설치기간 휴 전(전선 긴선 해체에 따른 선간 단락으로 정전 방지) -신설:3기[4회선(345kV 신가좌-인천CC No.18),2회선 C/H(154kV, 345kV)] -교체:1기[345kV 신가좌-인천CC No.19 Enclosing 공법으로 철탑교체]","2015-10-23 08:00","2015-10-23 18:00","2015-10-23 08:00","2015-10-23 18:00","연속",null,null,null,201508070183,{"$f":"IF(ISERROR(VLOOKUP(D47,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D47,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[44,"인천","직할","중동S/S #1 G/T GIS","중동S/S G/T #1T/L GIS 정밀점검","중동S/S G/T #1T/L GIS 정밀점검","2015-10-05 08:00","2015-10-07 18:00","취소","취소","연속",null,null,null,201508100239,{"$f":"IF(ISERROR(VLOOKUP(D48,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D48,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[45,"경기북부","구리","가평화천HP T/L","가평S/S 170kV 장기사용 GIS 대체공사 (2차 설치분)","170kV GIS × 8Bay (TL 4, M.Tr 2, BT 1, PT 1) 철거 설치","2015-10-01 09:00","2015-10-20 18:00","2015-10-01 09:00","2015-10-20 18:00","연속",null,null,null,201507070145,{"$f":"IF(ISERROR(VLOOKUP(D49,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D49,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[46,"경기북부","구리","가평청평HP#1 T/L","가평S/S 170kV 장기사용 GIS 대체공사 (3차 설치분)","170kV GIS × 8Bay (TL 4, M.Tr 2, BT 1, PT 1) 철거 설치","2015-10-21 09:00","2015-11-09 18:00","2015-10-21 09:00","2015-11-09 18:00","연속",null,null,null,201507070152,{"$f":"IF(ISERROR(VLOOKUP(D50,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D50,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[47,"경기북부","구리","덕소마석#2 T/L","15년 구리전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(마석S/S 덕소-마석#2T/L GIS)","2015-10-26 08:00","2015-10-28 14:00","2015-10-26 08:00","2015-10-28 14:00","연속",null,null,null,201506160121,"-"]
[48,"경기북부","구리","마석청평HP#2 T/L","15년 구리전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(마석S/S 마석-청평HP#2T/L GIS)","2015-10-15 14:00","2015-10-17 18:00","2015-10-15 14:00","2015-10-17 18:00","연속",null,null,null,201506160124,{"$f":"IF(ISERROR(VLOOKUP(D52,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D52,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[49,"경기북부","구리","미금덕소#1 T/L","15년 구리전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(미금S/S 미금-덕소#1T/L GIS)","2015-10-19 08:00","2015-10-21 14:00","2015-10-19 08:00","2015-10-21 14:00","연속",null,null,null,201506160103,"-"]
[50,"경기북부","구리","미금화양 T/L","154kV 미금-화양T/L 국산지지애자 교체공사","- 국산지지애자 교체공사","2015-10-21 08:00","2015-10-21 14:00","2015-10-21 08:00","2015-10-21 14:00","연속",null,null,null,201507130205,{"$f":"IF(ISERROR(VLOOKUP(D54,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D54,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[51,"경기북부","구리","미금덕소#2 T/L","154kV 미금-덕소#2T/L 국산지지애자교체공사","- 국산지지애자교체공사","2015-10-20 08:00","2015-10-20 14:00","2015-10-20 08:00","2015-10-20 14:00","당일",null,null,null,201507090005,"-"]
[52,"경기북부","구리","미금광장 T/L","15년 구리전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(미금S/S 미금-광장T/L GIS)","2015-10-21 14:00","2015-10-23 18:00","2015-10-21 14:00","2015-10-23 18:00","연속",null,null,null,201506160116,{"$f":"IF(ISERROR(VLOOKUP(D56,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D56,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[53,"경기북부","구리","도봉진접 T/L","154kV 진접분기 등 4개T/L 지장송전선로 이설공사","o 가철탑 1기 설치/철거 o 철탑 1기 설치/철거 o 전력선교체 : No.11-13 o 기타부대공사 1식. 끝.","2015-10-16 08:00","2015-10-17 18:00","2015-10-16 08:00","2015-10-17 18:00","연속",null,null,null,201508170381,"-"]
[54,"경기북부","구리","별내진접 T/L","154kV 진접분기 등 4개T/L 지장송전선로 이설공사","o 가철탑 1기 설치/철거 o 철탑 1기 설치/철거 o 전력선교체 : No.11-13 o 기타부대공사 1식. 끝.","2015-10-13 08:00","2015-10-15 18:00","2015-10-13 08:00","2015-10-15 18:00","연속",null,null,null,201508170379,"-"]
[55,"경기북부","구리","도봉진접 T/L","154kV 진접분기 등 4개T/L 지장송전선로 이설공사","o 가철탑 1기 설치/철거 o 철탑 1기 설치/철거 o 전력선교체 : No.11-13 o 기타부대공사 1식. 끝.","2015-10-12 08:00","2015-10-12 18:00","2015-10-12 08:00","2015-10-12 18:00","연속",null,null,null,201508170366,"-"]
[56,"경기북부","구리","동서울청평PP#2 T/L","154kV 동서울-청평PP T/L No.64, 65 노후취약철탑 보강공사","1) No.64 : 암타이, 주주재, 사재 철거 및 보강 2) No.65 : 보조재 철거 및 보강","2015-10-02 08:00","2015-10-02 18:00","2015-10-02 08:00","2015-10-02 18:00","당일",null,null,null,201508070180,"-"]
[57,"경기북부","구리","동서울청평PP#1 T/L","154kV 동서울-청평PP T/L No.64, 65 노후취약철탑 보강공사","1) No.64 : 암타이, 주주재, 사재 철거 및 보강 2) No.65 : 보조재 철거 및 보강","2015-10-01 08:00","2015-10-01 18:00","2015-10-01 08:00","2015-10-01 18:00","당일",null,null,null,201508070179,{"$f":"IF(ISERROR(VLOOKUP(D61,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D61,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[58,"경기북부","직할","신포천동두천#2 T/L","신포천동두천#2 T/L","동두천S/S SA 시범사업설비 철거공사","2015-10-12 10:00","2015-10-16 18:00","2015-10-12 10:00","2015-10-16 18:00","연속",null,null,null,201508130174,{"$f":"IF(ISERROR(VLOOKUP(D62,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D62,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[59,"경기북부","직할","신의정부의정부#1 T/L","154kV 금오-상계 지중T/L 건설공사","케이블 포설 및 접속","2015-10-21 08:00","2015-11-20 18:00","2015-10-21 08:00","2015-11-20 18:00","연속",null,null,null,201507150066,{"$f":"IF(ISERROR(VLOOKUP(D63,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D63,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[60,"경기북부","직할","양주S/S 154kV #60 BUS","양주S/S 154kV #60 BUS","15년 경기북부직할 변전협력업체 총액공사","2015-10-06 10:00","2015-10-06 18:00","2015-10-06 10:00","2015-10-06 18:00","당일",null,null,null,201508180034,{"$f":"IF(ISERROR(VLOOKUP(D64,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D64,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[61,"경기북부","직할","양주S/S 154kV #65 BUS","양주S/S 154kV #65 BUS","15년 경기북부직할 변전협력업체 총액공사","2015-10-07 10:00","2015-10-07 18:00","2015-10-07 10:00","2015-10-07 18:00","당일",null,null,null,201508180035,{"$f":"IF(ISERROR(VLOOKUP(D65,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D65,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[62,"경기북부","파주","일산S/S 154kV #65 BUS","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-10-30 09:00","2015-10-31 18:00","2015-10-30 09:00","2015-10-31 18:00","연속",null,null,null,201506050102,{"$f":"IF(ISERROR(VLOOKUP(D66,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D66,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[63,"경기북부","파주","양주일산#2 T/L","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-10-12 09:00","2015-10-13 18:00","2015-10-12 09:00","2015-10-13 18:00","연속",null,null,null,201508210131,"-"]
[64,"경기북부","파주","일산S/S 154kV #60 BUS","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-10-28 09:00","2015-10-29 18:00","2015-10-28 09:00","2015-10-29 18:00","연속",null,null,null,201506050100,{"$f":"IF(ISERROR(VLOOKUP(D68,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D68,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[65,"경기북부","파주","양주일산#1 T/L","일산S/S 축소형 Mosaic 배전반 대체공사","축소형 Mosaic 배전반 대체 시행","2015-10-20 09:00","2015-10-21 18:00","2015-10-20 09:00","2015-10-21 18:00","연속",null,null,null,201508210132,{"$f":"IF(ISERROR(VLOOKUP(D69,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D69,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[66,"경기","군포","남안산목내#2 T/L","남안산목내TL 지장송전선로 이설공사","남안산목내TL MH#10~J/B#11 케이블철거 후 교체공사","2015-10-01 08:30","2015-10-13 18:00","2015-10-01 08:30","2015-10-13 18:00","연속",null,null,null,201508130434,{"$f":"IF(ISERROR(VLOOKUP(D70,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D70,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[67,"경기","군포","신시흥시화#1 T/L","시화S/S 154kV 신시흥시화#2T/L LA 교체공사 안전이격거리 확보","1.시화S/S 154kV 신시흥시화#2T/L LA 교체관련 안전이격거리 확보","2015-10-11 09:00","2015-10-11 18:00","2015-10-11 09:00","2015-10-11 18:00","당일",null,null,null,201508180227,{"$f":"IF(ISERROR(VLOOKUP(D71,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D71,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[68,"경기","군포","신시흥시화#2 T/L","시화S/S 154kV 신시흥시화#2T/L LA 교체공사","1.시화S/S 154kV 신시흥시화#2T/L LA 교체","2015-10-11 09:00","2015-10-11 18:00","2015-10-11 09:00","2015-10-11 18:00","당일",null,null,null,201508180226,{"$f":"IF(ISERROR(VLOOKUP(D72,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D72,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[69,"경기","군포","산본안양#2 T/L","안양변전소 154kV 산본안양#2T/L LA 점검 공사","안양변전소 154kV 산본안양#2T/L LA 점검","2015-10-03 09:00","2015-10-03 18:00","2015-10-03 09:00","2015-10-03 18:00","당일",null,null,null,201508180249,{"$f":"IF(ISERROR(VLOOKUP(D73,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D73,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[70,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 6100B/T, 일동원곡#2, #2MTr 1차 GIS 교체공사","2015-10-14 09:00","2015-10-21 18:00","2015-10-14 09:00","2015-10-21 18:00","연속",null,null,null,201508180094,{"$f":"IF(ISERROR(VLOOKUP(D74,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D74,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[71,"경기","군포","일동S/S 154kV #1 BUS","일동S/S 154kV #60Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 서서울일동#1, #1MTr 1차 GIS 교체공사","2015-10-29 09:00","2015-11-04 18:00","2015-10-29 09:00","2015-11-04 18:00","연속",null,null,null,201508180106,{"$f":"IF(ISERROR(VLOOKUP(D75,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D75,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[72,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 서서울일동#1, #1MTr 1차 GIS 교체공사","2015-10-26 09:00","2015-10-28 18:00","2015-10-26 09:00","2015-10-28 18:00","연속",null,null,null,201508180103,{"$f":"IF(ISERROR(VLOOKUP(D76,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D76,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[73,"경기","군포","서서울일동#2 T/L","일동S/S 154kV 서서울일동#2TL GIS","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S #60Bus에서 #65Bus 모선절체를 위한 양단DS투입용","2015-10-14 09:00","2015-10-14 11:00","2015-10-14 09:00","2015-10-14 11:00","당일",null,null,null,201508180143,{"$f":"IF(ISERROR(VLOOKUP(D77,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D77,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[74,"경기","군포","일동S/S 154kV #1 BUS","일동S/S 154kV #60Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 6100B/T, 일동원곡#2, #2MTr 1차 GIS 교체공사","2015-10-05 09:00","2015-10-13 18:00","2015-10-05 09:00","2015-10-13 18:00","연속",null,null,null,201508180092,{"$f":"IF(ISERROR(VLOOKUP(D78,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D78,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[75,"경기","군포","서서울일동#2 T/L","일동S/S 154kV 서서울일동#2TL GIS","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S #65Bus에서 #60Bus 모선절체를 위한 양단DS투입용","2015-10-05 09:00","2015-10-05 11:00","2015-10-05 09:00","2015-10-05 11:00","당일",null,null,null,201508180142,{"$f":"IF(ISERROR(VLOOKUP(D79,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D79,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[76,"경기","군포","일동S/S 154kV #1 BUS TIE GIS","일동S/S 154kV #1 BUS TIE GIS 교체공사","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 6100B/T GIS 교체공사","2015-10-01 09:00","2015-10-23 18:00","2015-10-01 09:00","2015-10-23 18:00","연속",null,null,null,201508180081,{"$f":"IF(ISERROR(VLOOKUP(D80,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D80,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[77,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 6100B/T, 일동원곡#2, #2MTr 1차 GIS 교체공사","2015-10-01 09:00","2015-10-04 18:00","2015-10-01 09:00","2015-10-04 18:00","연속",null,null,null,201508180090,{"$f":"IF(ISERROR(VLOOKUP(D81,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D81,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[78,"경기","군포","일동원곡#2 T/L","일동S/S 154kV 일동원곡#2TL GIS 교체공사","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 일동원곡#2TL GIS 교체공사","2015-10-01 09:00","2015-10-23 18:00","2015-10-01 09:00","2015-10-23 18:00","연속",null,null,null,201508180079,{"$f":"IF(ISERROR(VLOOKUP(D82,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D82,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[79,"경기","군포","서서울일동#1 T/L","일동S/S 154kV 서서울일동#1TL GIS 교체공사","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 서서울일동#1TL GIS 교체공사","2015-10-26 09:00","2015-11-12 18:00","2015-10-26 09:00","2015-11-12 18:00","연속",null,null,null,201508180100,{"$f":"IF(ISERROR(VLOOKUP(D83,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D83,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[80,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 6100B/T, 일동원곡#2, #2MTr 1차 GIS 교체공사","2015-10-23 09:00","2015-10-23 18:00","2015-10-23 09:00","2015-10-23 18:00","연속",null,null,null,201508180096,{"$f":"IF(ISERROR(VLOOKUP(D84,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D84,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[81,"경기","군포","일동S/S 154kV #1 BUS","일동S/S 154kV #60Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 6100B/T, 일동원곡#2, #2MTr 1차 GIS 교체공사","2015-10-22 09:00","2015-10-22 18:00","2015-10-22 09:00","2015-10-22 18:00","연속",null,null,null,201508180095,{"$f":"IF(ISERROR(VLOOKUP(D85,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D85,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[82,"경기","군포","화성조암#2 T/L","154kV 화성조암#2T/L 송전선로 정밀점검(구간 No.1~39)","15년 가공송전선로 순시점검 위탁공사 154kV 화성조암#2T/L 송전선로 정밀점검(구간 No.1~39)","2015-10-24 07:00","2015-10-25 20:00","2015-10-24 07:00","2015-10-25 20:00","매일",null,null,null,201508180119,{"$f":"IF(ISERROR(VLOOKUP(D86,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D86,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[83,"경기","군포","관양평촌#1 T/L","평촌S/S 154kV 관양-평촌#1T/L GIS 교체공사","평촌S/S 154kV GIS 교체공사 - 관양-평촌#1T/L GIS 교체","2015-10-05 09:00","2015-10-22 18:00","2015-10-05 09:00","2015-10-22 18:00","연속",null,null,null,201508090008,{"$f":"IF(ISERROR(VLOOKUP(D87,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D87,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[84,"경기","동부","분당오포#1 T/L","154kV 분당오포T/L 송전선로정밀점검(No.1~31)","154kV 분당오포#1T/L 송전선로정밀점검(No.1~31)","2015-10-10 08:00","2015-10-11 18:00","2015-10-10 08:00","2015-10-11 18:00","매일",null,null,null,201508170474,{"$f":"IF(ISERROR(VLOOKUP(D88,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D88,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[85,"경기","동부","분당오포#2 T/L","154kV 분당오포T/L 송전선로정밀점검(No.1~31)","154kV 분당오포#2T/L 송전선로정밀점검(No.1~31)","2015-10-17 08:00","2015-10-18 18:00","2015-10-17 08:00","2015-10-18 18:00","매일",null,null,null,201508170475,{"$f":"IF(ISERROR(VLOOKUP(D89,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D89,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[86,"경기","동부","오포모현#1 T/L","154kV 오포모현T/L 송전선로정밀점검(No.1~26)","154kV 오포모현#1T/L 송전선로정밀점검(No.1~26)","2015-10-18 08:00","2015-10-19 18:00","2015-10-18 08:00","2015-10-19 18:00","매일",null,null,null,201508170478,{"$f":"IF(ISERROR(VLOOKUP(D90,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D90,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[87,"경기","동부","오포모현#2 T/L","154kV 오포모현T/L 송전선로정밀점검(No.1~26)","154kV 오포모현#2T/L 송전선로정밀점검(No.1~26)","2015-10-11 08:00","2015-10-12 18:00","2015-10-11 08:00","2015-10-12 18:00","매일",null,null,null,201508170477,{"$f":"IF(ISERROR(VLOOKUP(D91,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D91,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[88,"경기","성남","모현용인#1 T/L","154kV 모현용인T/L 송전선로 정밀점검(No.1~37)","154kV 모현용인#1T/L 송전선로 정밀점검(No.1~37)","2015-10-12 08:00","2015-10-13 18:00","2015-10-12 08:00","2015-10-13 18:00","매일",null,null,null,201508170485,{"$f":"IF(ISERROR(VLOOKUP(D92,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D92,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[89,"경기","성남","모현용인#2 T/L","154kV 모현용인T/L 송전선로 정밀점검(No.1~37)","154kV 모현용인#2T/L 송전선로 정밀점검(No.1~37)","2015-10-19 08:00","2015-10-20 18:00","2015-10-19 08:00","2015-10-20 18:00","매일",null,null,null,201508170487,{"$f":"IF(ISERROR(VLOOKUP(D93,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D93,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[90,"경기","직할","안열#2T/L T/L","동안양S/S 154kV 안열#2T/L","동안양S/S 154kV 안열#2T/L 정밀점검 공사","2015-10-04 09:00","2015-10-06 18:00","2015-10-04 09:00","2015-10-06 18:00","연속",null,null,null,201508170437,{"$f":"IF(ISERROR(VLOOKUP(D94,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D94,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[91,"경기","직할","안열#1T/L T/L","동안양S/S 154kV 안열#1T/L","동안양S/S 154kV 안열#1T/L 정밀점검 공사","2015-10-30 09:00","2015-11-01 18:00","2015-10-30 09:00","2015-11-01 18:00","연속",null,null,null,201508170440,{"$f":"IF(ISERROR(VLOOKUP(D95,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D95,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[92,"경기","직할","오산향남#2 T/L","154kV 오산향남T/L 초기점검(향남S/S~오산향남No.2)","154kV 오산향남#2T/L 가공송전선로 초기점검(향남S/S~오산향남No.2)","2015-10-11 13:30","2015-10-11 18:00","2015-10-11 13:30","2015-10-11 18:00","당일",null,null,null,201508170435,{"$f":"IF(ISERROR(VLOOKUP(D96,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D96,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[93,"경기","직할","오산향남#1 T/L","154kV 오산향남T/L 초기점검(향남S/S~오산향남No.2)","154kV 오산향남#1T/L 가공송전선로 초기점검(향남S/S~오산향남No.2)","2015-10-11 09:00","2015-10-11 13:00","2015-10-11 09:00","2015-10-11 13:00","당일",null,null,null,201508170427,{"$f":"IF(ISERROR(VLOOKUP(D97,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D97,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[94,"경기","직할","발안향남#1 T/L","154kV 발안향남T/L 초기점검(발안향남No.20~향남S/S)","154kV 발안향남#1T/L 가공송전선로 초기점검(발안향남No.20~향남S/S)","2015-10-10 09:00","2015-10-10 12:00","2015-10-10 09:00","2015-10-10 12:00","당일",null,null,null,201508170417,{"$f":"IF(ISERROR(VLOOKUP(D98,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D98,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[95,"경기","직할","발안향남#2 T/L","154kV 발안향남T/L 초기점검(발안향남No.20~향남S/S)","154kV 발안향남#2T/L 가공송전선로 초기점검(발안향남No.20~향남S/S)","2015-10-10 13:00","2015-10-10 18:00","2015-10-10 13:00","2015-10-10 18:00","당일",null,null,null,201508170418,{"$f":"IF(ISERROR(VLOOKUP(D99,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D99,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[96,"경기","평택","송탄S/S 송탄-소사벌T/L(687) GIS","송탄S/S 154kV 송탄소사벌T/L GIS 대체 공사","송탄S/S 154kV 송탄소사벌T/L GIS 대체 공사","2015-10-05 09:00","2015-10-19 18:00","2015-10-05 09:00","2015-10-19 18:00","연속",null,null,null,201508130243,{"$f":"IF(ISERROR(VLOOKUP(D100,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D100,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[97,"경기","평택","송탄안성 T/L","154kV 송탄-안성T/L 피뢰기 설치공사","○ 공사대상 : 154kV 송탄-안성T/L No.2~4(3기) ○ 공사내용 : 송전용 피뢰기 9세트 설치","2015-10-25 08:00","2015-10-25 18:00","2015-10-25 08:00","2015-10-25 18:00","당일",null,null,null,201508180099,{"$f":"IF(ISERROR(VLOOKUP(D101,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D101,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[98,"경기","평택","송탄오성CC#1 T/L","154kV 송탄-오성복합#1T/L 전력선 정비공사","○ 공사대상 : 154kV 송탄-오성복합#1T/L No.11~13 ○ 공사내용 : 전력선 이도조정 및 송탄안성 피뢰기설치 안전확보","2015-10-24 08:00","2015-10-25 18:00","2015-10-24 08:00","2015-10-25 18:00","매일",null,null,null,201508180097,{"$f":"IF(ISERROR(VLOOKUP(D102,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D102,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[99,"경기","평택","둔포추팔#2 T/L","154kV 둔포-추팔#2T/L 정밀점검(구간 추팔S/S~둔포S/S)","154kV 둔포-추팔#2TL 가공송전선로 정밀점검(23기)","2015-10-07 09:00","2015-10-08 17:00","2015-10-07 09:00","2015-10-08 17:00","매일",null,null,null,201508110260,{"$f":"IF(ISERROR(VLOOKUP(D103,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D103,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[100,"경기","평택","둔포추팔#1 T/L","154kV 둔포-추팔#1T/L 정밀점검(구간 추팔S/S~둔포S/S)","154kV 둔포-추팔#1TL 가공송전선로 정밀점검(23기)","2015-10-05 09:00","2015-10-06 17:00","2015-10-05 09:00","2015-10-06 17:00","매일",null,null,null,201508110259,{"$f":"IF(ISERROR(VLOOKUP(D104,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D104,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[101,"경기","평택","평택S/S 청북-평택#2T/L CB","평택S/S 청북평택#2T/L 170kV GCB 정밀점검공사","평택S/S 청북평택#2T/L 170kV GCB 정밀점검공사","2015-10-17 08:00","2015-10-18 18:00","2015-10-17 08:00","2015-10-18 18:00","연속",null,null,null,201508130261,{"$f":"IF(ISERROR(VLOOKUP(D105,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D105,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[102,"경기","평택","포승청북#1 T/L","154kV 만호분기T/L 건설공사","154kV 포승-청북#1T/L NO.9 암신설 및 전선이동 설치 관련 안전거리 확보","2015-10-30 08:00","2015-11-15 18:30","2015-10-30 08:00","2015-11-15 18:30","연속",null,null,null,201508180211,{"$f":"IF(ISERROR(VLOOKUP(D106,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D106,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[103,"경기","평택","포승평택TP T/L","154kV 만호분기T/L 건설공사","154kV 포승평택TP T/L NO.9호 4번암 볼트교체","2015-10-29 08:00","2015-10-29 18:30","2015-10-29 08:00","2015-10-29 18:30","당일",null,null,null,201508180208,{"$f":"IF(ISERROR(VLOOKUP(D107,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D107,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[104,"경기","평택","포승청북#2 T/L","154kV 만호분기T/L 건설공사","154kV 포승-청북#1T/L NO.9 암신설 및 전선이동 설치 관련 안전거리 확보","2015-10-31 08:00","2015-11-01 18:30","2015-10-31 08:00","2015-11-01 18:30","연속",null,null,null,201508180212,{"$f":"IF(ISERROR(VLOOKUP(D108,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D108,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[105,"경기","평택","원정포승 T/L","154kV 만호분기T/L 건설공사","154kV 포승-청북#1T/L NO.9 암신설 및 전선이동 설치 관련 안전거리 확보","2015-10-30 08:00","2015-11-15 18:30","2015-10-30 08:00","2015-11-15 18:30","연속",null,null,null,201508180214,{"$f":"IF(ISERROR(VLOOKUP(D109,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D109,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[106,"강원","강릉","영동TP강릉 T/L","154kV 강릉-횡계T/L 용량증대 전선교체공사","전선교체 : 2C-21.9km (ACSR 330㎟ → HSTACIR/AW 330㎟)","2015-10-06 08:00","2015-10-10 18:00","2015-10-06 08:00","2015-10-10 18:00","연속",null,null,null,201507140089,{"$f":"IF(ISERROR(VLOOKUP(D110,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D110,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[107,"강원","강릉","강릉횡계#2 T/L","154kV 강릉-횡계T/L 용량증대 전선교체공사","전선교체 : 2C-21.9km (ACSR 330㎟ → HSTACIR 330㎟)","2015-10-06 08:00","2015-11-09 18:00","2015-10-06 08:00","2015-11-09 18:00","연속",null,null,null,201507140080,{"$f":"IF(ISERROR(VLOOKUP(D111,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D111,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[108,"강원","강릉","강릉횡계#1 T/L","154kV 강릉-횡계T/L 용량증대 전선교체공사","전력선 교체 : 2C-21.9km (ACSR 330㎟ → HSTACIR 330㎟)","2015-10-24 06:00","2015-10-25 18:00","2015-10-10 10:00","2015-10-11 18:00","매일",null,null,null,201508280080,{"$f":"IF(ISERROR(VLOOKUP(D112,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D112,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[109,"강원","강릉","영동T/P 154kV #2 BUS","강릉PO 170kV GIS 정밀점검","○154kV #2M.Tr GIS 정밀점검(#2DS)","2015-10-26 14:00","2015-10-27 18:00","2015-10-26 09:30","2015-10-27 18:00","연속",null,null,null,201508110021,{"$f":"IF(ISERROR(VLOOKUP(D113,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D113,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[110,"강원","강릉","영동T/P 154kV #1 BUS","강릉PO 170kV GIS 정밀점검","○154kV #2M.Tr GIS 정밀점검(#1DS)","2015-10-25 09:30","2015-10-26 14:00","2015-10-23 09:30","2015-10-25 18:00","연속",null,null,null,201508110020,{"$f":"IF(ISERROR(VLOOKUP(D114,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D114,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[111,"강원","강릉","주진평창#2 T/L","2015년 가공송전선로 순시점검 위탁공사(철탑 정밀점검)","154kV 주진평창 T/L 철탑 정밀점검","2015-10-07 09:00","2015-10-13 18:00","취소","취소","매일",null,null,null,201508110146,{"$f":"IF(ISERROR(VLOOKUP(D115,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D115,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[112,"강원","강릉","주진평창#1 T/L","2015년 가공송전선로 순시점검 위탁공사(철탑 정밀점검)","154kV 주진평창 T/L 철탑 정밀점검","2015-10-01 09:00","2015-10-06 18:00","취소","취소","매일",null,null,null,201508110145,{"$f":"IF(ISERROR(VLOOKUP(D116,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D116,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[113,"강원","동해","북평영동TP#1 T/L","154kV 동북, 영동화력T/L 지중화공사","동해북평T/L 지중화 및 북평영동TP TL 일부 지중화","2015-10-15 09:00","2015-10-28 18:00","2015-10-15 09:00","2015-10-28 18:00","연속",null,null,null,201508050157,{"$f":"IF(ISERROR(VLOOKUP(D117,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D117,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[114,"강원","동해","북평영동TP#2 T/L","154kV 동북, 영동화력T/L 지중화공사","동해북평T/L 지중화 및 북평영동TP TL 일부 지중화","2015-10-29 09:00","2015-11-11 18:00","2015-10-29 09:00","2015-11-11 18:00","연속",null,null,null,201508050158,{"$f":"IF(ISERROR(VLOOKUP(D118,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D118,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[115,"강원","원주","남원주원주#2 T/L","2015년 가공송전 순시점검 위탁공사","154kV 남원주-원주#2T/L 정밀점검 (대상기수 31기)","2015-10-12 09:00","2015-10-14 18:00","2015-10-12 09:00","2015-10-14 18:00","매일",null,null,null,201508100109,{"$f":"IF(ISERROR(VLOOKUP(D119,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D119,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[116,"강원","원주","신제천남원주#1 T/L","2015년 가공송전 순시점검 위탁공사","154kV 신제천-남원주#1T/L 정밀점검 (대상기수 60기)","2015-10-05 09:00","2015-10-08 18:00","2015-10-05 09:00","2015-10-08 18:00","매일",null,null,null,201508100105,{"$f":"IF(ISERROR(VLOOKUP(D120,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D120,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[117,"강원","원주","홍천남춘천 T/L","2015년 원주전력지사 변전협력회사 총액공사","170kV GCB 보통점검","2015-10-13 09:00","2015-10-13 18:00","2015-10-13 09:00","2015-10-13 18:00","당일",null,null,null,201508100227,{"$f":"IF(ISERROR(VLOOKUP(D121,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D121,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[118,"강원","원주","홍천상남#1 T/L","장기미동작 차단기 시험","홍천S/S 154kV 홍천상남#1T/L 장기미동작 차단기 시험","2015-10-12 09:00","2015-10-12 18:00","2015-10-12 09:00","2015-10-12 18:00","당일",null,null,null,201508100226,{"$f":"IF(ISERROR(VLOOKUP(D122,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D122,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[119,"강원","직할","남춘천청평PP T/L","2015년 가공송전선로 순시점검 위탁공사","정밀점검(송전철탑, 전력선, 금구류 등)","2015-10-06 09:00","2015-10-08 18:00","2015-10-06 09:00","2015-10-08 18:00","매일",null,null,null,201508110064,{"$f":"IF(ISERROR(VLOOKUP(D123,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D123,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[120,"강원","직할","서홍천청평PP T/L","2015년 가공송전선로 순시점검 위탁공사","정밀점검(철탑, 전력선, 금구류 등)","2015-10-05 09:00","2015-10-05 18:00","2015-10-05 09:00","2015-10-05 18:00","당일",null,null,null,201508110063,{"$f":"IF(ISERROR(VLOOKUP(D124,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D124,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[121,"강원","직할","청평HP의암HP T/L","2015년 강원지역본부 협력회사 총액공사 기기점검","의암HP 청평-의암HP T/L,#1,2M.Tr 2차 GCB 등 3대 하자점검","2015-10-01 09:30","2015-10-02 18:00","2015-10-01 09:30","2015-10-02 18:00","매일",null,null,null,201508100007,{"$f":"IF(ISERROR(VLOOKUP(D125,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D125,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[122,"강원","직할","북춘천춘천HP T/L","춘천H/P 154kV 단로기 성능개선 공사","#1M.Tr 2차 DS(6135) 성능개선 북춘천춘천HP T/L DS(615) 성능개선","2015-10-24 09:00","2015-10-24 18:00","2015-10-24 09:00","2015-10-24 18:00","당일",null,null,null,201508110265,{"$f":"IF(ISERROR(VLOOKUP(D126,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D126,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[123,"강원","직할","춘천H/P 154kV BUS","춘천H/P 154kV 단로기 성능개선 공사","#1M.Tr 2차 DS(6135) 성능개선 북춘천춘천HP T/L DS(615) 성능개선","2015-10-24 09:00","2015-10-24 18:00","2015-10-24 09:00","2015-10-24 18:00","당일",null,null,null,201508110266,{"$f":"IF(ISERROR(VLOOKUP(D127,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D127,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[124,"강원","직할","가평춘천HP T/L","춘천H/P 154kV 단로기 성능개선 공사","#1M.Tr 2차 DS(6135) 성능개선 북춘천춘천HP T/L DS(615) 성능개선","2015-10-24 09:00","2015-10-24 18:00","2015-10-24 09:00","2015-10-24 18:00","당일",null,null,null,201508110264,{"$f":"IF(ISERROR(VLOOKUP(D128,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D128,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[125,"강원","직할","화천H/P 154kV #1 BUS","2015년 강원지역본부 협력회사 총액공사 기기점검","화천HP #4M.Tr 2차측 DS 보통점검","2015-10-06 09:30","2015-10-06 14:00","2015-10-06 09:30","2015-10-06 14:00","당일",null,null,null,201508100041,{"$f":"IF(ISERROR(VLOOKUP(D129,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D129,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[126,"강원","직할","화천H/P 154kV #2 BUS","2015년 강원지역본부 협력회사 총액공사 기기점검","화천HP #3M.Tr 2차측 DS 보통점검","2015-10-08 09:30","2015-10-08 18:00","2015-10-08 09:30","2015-10-08 18:00","당일",null,null,null,201508100072,{"$f":"IF(ISERROR(VLOOKUP(D130,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D130,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[127,"강원","직할","화천H/P 154kV #1 BUS","2015년 강원지역본부 협력회사 총액공사 기기점검","화천HP #3M.Tr 2차측 DS 보통점검","2015-10-07 09:30","2015-10-07 18:00","2015-10-07 09:30","2015-10-07 18:00","당일",null,null,null,201508100044,{"$f":"IF(ISERROR(VLOOKUP(D131,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D131,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[128,"강원","직할","화천H/P 154kV #2 BUS","2015년 강원지역본부 협력회사 총액공사 기기점검","화천HP #4M.Tr 2차측 DS 보통점검","2015-10-06 14:00","2015-10-06 18:00","2015-10-06 14:00","2015-10-06 18:00","당일",null,null,null,201508100042,{"$f":"IF(ISERROR(VLOOKUP(D132,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D132,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[129,"충북","직할","신제천S/S 154kV #60 BUS","2015년 변전협력회사 총액공사","신제천S/S #60BUS LA보통점검","2015-10-14 14:00","2015-10-14 18:00","2015-10-14 14:00","2015-10-14 18:00","당일",null,null,null,201508100024,{"$f":"IF(ISERROR(VLOOKUP(D133,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D133,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[130,"충북","직할","신제천S/S 154kV #67 BUS","2015년 변전협력회사 총액공사","신제천S/S #67BUS CVT, LA보통점검","2015-10-14 09:00","2015-10-14 14:00","2015-10-14 09:00","2015-10-14 14:00","당일",null,null,null,201508100023,{"$f":"IF(ISERROR(VLOOKUP(D134,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D134,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[131,"충북","직할","신제천S/S 154kV #66 BUS","2015년 변전협력회사 총액공사","신제천S/S #66BUS CVT보통점검","2015-10-13 14:00","2015-10-13 18:00","2015-10-13 14:00","2015-10-13 18:00","당일",null,null,null,201508100019,{"$f":"IF(ISERROR(VLOOKUP(D135,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D135,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[132,"충북","직할","신제천S/S 154kV #61 BUS","2015년 변전협력회사 총액공사","신제천S/S #61BUS CVT보통점검","2015-10-13 09:00","2015-10-13 14:00","2015-10-13 09:00","2015-10-13 14:00","당일",null,null,null,201508100016,{"$f":"IF(ISERROR(VLOOKUP(D136,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D136,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[133,"충북","직할","신제천S/S 60-61-0 SEC CB","2015년 하반기 개폐장치 정밀점검 공사","2015년 하반기 개폐장치 정밀점검 공사","2015-10-07 09:00","2015-10-08 18:00","2015-10-07 09:00","2015-10-08 18:00","연속",null,null,null,201508100020,{"$f":"IF(ISERROR(VLOOKUP(D137,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D137,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[134,"충북","직할","신제천S/S 66-67-0 SEC CB","2015년 하반기 개폐장치 정밀점검 공사","2015년 하반기 개폐장치 정밀점검 공사","2015-10-05 09:00","2015-10-06 18:00","2015-10-05 09:00","2015-10-06 18:00","연속",null,null,null,201508100018,{"$f":"IF(ISERROR(VLOOKUP(D138,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D138,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[135,"충북","직할","신제천왕암#1 T/L","2015년 가공송전선로 순시점검 위탁공사","위탁회사 : 송전선로 정밀점검 협력회사 - SB댐퍼 14기 설치 - 조류퇴치방지장치 10기 설치","2015-10-03 08:00","2015-10-04 18:00","2015-10-03 08:00","2015-10-04 18:00","매일",null,null,null,201507090230,{"$f":"IF(ISERROR(VLOOKUP(D139,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D139,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[136,"충북","직할","신제천S/S 65-66-0 SEC CB","2015년 하반기 개폐장치 정밀점검 공사","2015년 하반기 개폐장치 정밀점검 공사","2015-10-01 09:00","2015-10-02 18:00","2015-10-01 09:00","2015-10-02 18:00","연속",null,null,null,201508100017,{"$f":"IF(ISERROR(VLOOKUP(D140,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D140,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[137,"충북","직할","제천영월#2 T/L","154kV 제천-영월T/L 지중 피뢰기 교체공사","ㅇ 공사명 : 154kV 제천-영월T/L 지중 피뢰기 교체공사 ㅇ 내 용 : 자기제 피뢰기 → 폴리머 피뢰기 교체 ㅇ 대 상 : 154kV 제천-영월#1,2T/L 지중피뢰기 6개","2015-10-26 09:00","2015-10-26 18:00","2015-10-26 09:00","2015-10-26 18:00","매일",null,null,null,201508120080,{"$f":"IF(ISERROR(VLOOKUP(D141,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D141,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[138,"충북","직할","제천영월#1 T/L","154kV 제천-영월T/L 지중 피뢰기 교체공사","ㅇ 공사명 : 154kV 제천-영월T/L 지중 피뢰기 교체공사 ㅇ 내 용 : 자기제 피뢰기 -> 폴리머 피뢰기 교체 ㅇ 대 상 : 154kV 제천-영월#1,2T/L 지중피뢰기 6개","2015-10-27 09:00","2015-10-27 18:00","2015-10-27 09:00","2015-10-27 18:00","매일",null,null,null,201508120076,{"$f":"IF(ISERROR(VLOOKUP(D142,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D142,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[139,"충북","청주","청원부강#2 T/L","154kV 청원-부강T/L 정비대상개소 보수","댐퍼 설치","2015-10-13 08:00","2015-10-13 18:00","2015-10-13 08:00","2015-10-13 18:00","매일",null,null,null,201508070251,{"$f":"IF(ISERROR(VLOOKUP(D143,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D143,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[140,"충북","청주","청원부강#1 T/L","154kV 청원-부강T/L 정비대상개소 보수","댐퍼 설치","2015-10-12 08:00","2015-10-12 18:00","2015-10-12 08:00","2015-10-12 18:00","매일",null,null,null,201508070250,{"$f":"IF(ISERROR(VLOOKUP(D144,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D144,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[141,"충북","청주","청원죽림#1 T/L","청원S/S 154kV 전류제한리액터 설치공사","○ 154kV GIS(GIB) 설치 × 1식 ○ 보호배전반 설치(대체) × 2면(청원1면, 죽림1면) ○ 기타 부대공사 × 1식 ※ 무부하가압(48H) 및 실부하(10/23) 가압후 정상운전","2015-10-17 08:00","2015-10-23 18:00","2015-10-17 08:00","2015-10-23 18:00","연속",null,null,null,201508200058,{"$f":"IF(ISERROR(VLOOKUP(D145,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D145,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[142,"충북","청주","청원죽림#2 T/L","청원S/S 154kV 전류제한리액터 설치공사","○ 154kV GIS(GIB) 설치 × 1식 ○ 보호배전반 설치(대체) × 2면(청원1면, 죽림1면) ○ 기타 부대공사 × 1식 ※ CLR C상 설치 안전이격 확보 - 10/10 오전 : 청원죽림#2T/L- 청원죽림#1T/L 동시휴전 ※ 10/10~10/16 GIS Docking, 무부하(48H), 실부하가압(10/16)후 정상운전","2015-10-10 08:00","2015-10-16 18:00","2015-10-10 08:00","2015-10-16 18:00","연속",null,null,null,201508200056,{"$f":"IF(ISERROR(VLOOKUP(D146,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D146,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[143,"충북","청주","청원죽림#1 T/L","청원S/S 154kV 전류제한리액터 설치공사","○ CLR(2.85Ω, 1695A) 설치 × 1조(154kV 청원-죽림 #2T/L) ○ CLR 1,2차 모선설지(154kV 청원-죽림 #2T/L) ○ 기타 부대공사 × 1식 ※ 10/10 08:00~13:00 청원-죽림#2T/L 및 청원-죽림#1T/L 동시휴전 (청원-죽림#2T/L C상 CLR 및 붓싱조립 안전이격 확보)","2015-10-10 08:00","2015-10-10 13:00","2015-10-10 08:00","2015-10-10 13:00","당일",null,null,null,201508200057,{"$f":"IF(ISERROR(VLOOKUP(D147,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D147,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[144,"충북","청주","청원신탄진 T/L","송전선로 정밀점검","송전선로 정밀점검","2015-10-14 09:00","2015-10-19 18:00","2015-10-14 09:00","2015-10-19 18:00","매일",null,null,null,201508070246,{"$f":"IF(ISERROR(VLOOKUP(D148,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D148,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[145,"충북","청주","청주대청HP T/L","송전선로 정밀점검","송전선로 정밀점검","2015-10-20 09:00","2015-10-26 18:00","2015-10-20 09:00","2015-10-26 18:00","매일",null,null,null,201508100004,{"$f":"IF(ISERROR(VLOOKUP(D149,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D149,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[146,"대전충남","대전","신옥천서대전#1 T/L","○ 154kV 신옥천-서대전#1T/L 송전선로보호반 성능개선공사(제작사)","○ 154kV 신옥천-서대전#1T/L 송전선로보호반 성능개선공사(제작사) 영인기술제 154kV 송전선로 보호반 성능개선공사(제작사시행) 제작사 리콜시행 - 모듈교체","2015-10-08 09:00","2015-10-08 13:00","2015-10-08 09:00","2015-10-08 13:00","당일",null,null,null,201507210071,{"$f":"IF(ISERROR(VLOOKUP(D150,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D150,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[147,"대전충남","대전","신옥천서대전#2 T/L","○ 154kV 신옥천-서대전#2T/L 송전선로보호반 성능개선공사(제작사)","○ 154kV 신옥천-서대전#2T/L 송전선로보호반 성능개선공사(제작사) 영인기술제 154kV 송전선로 보호반 성능개선공사(제작사시행) 제작사 리콜시행 - 모듈교체","2015-10-08 13:00","2015-10-08 18:00","2015-10-08 13:00","2015-10-08 18:00","당일",null,null,null,201507210072,{"$f":"IF(ISERROR(VLOOKUP(D151,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D151,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[148,"대전충남","서산","당진T/P 154kV #1 BUS","2015년 서산P/O 170kV GIS 정밀점검","○ 170kV GIS 정밀점검(석문-당진화력#1T/L DS 정밀점검)","2015-10-17 15:00","2015-10-18 18:00","2015-10-17 15:00","2015-10-18 18:00","연속",null,null,null,201508120056,{"$f":"IF(ISERROR(VLOOKUP(D152,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D152,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[149,"대전충남","서산","석문당진TP#1 T/L","2015년 서산P/O 170kV GIS 정밀점검","○ 170kV GIS 정밀점검(내부 정밀점검, 메카니즘점검)","2015-10-16 09:00","2015-10-18 18:00","2015-10-16 09:00","2015-10-18 18:00","연속",null,null,null,201508120052,{"$f":"IF(ISERROR(VLOOKUP(D153,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D153,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[150,"대전충남","서산","당진T/P 154kV #2 BUS","2015년 서산P/O 170kV GIS 정밀점검","○ 170kV GIS 정밀점검(석문-당진화력#1T/L DS 정밀점검)","2015-10-16 09:00","2015-10-17 15:00","2015-10-16 09:00","2015-10-17 15:00","연속",null,null,null,201508120054,{"$f":"IF(ISERROR(VLOOKUP(D154,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D154,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[151,"대전충남","서산","대산석문#1 T/L","154kV 대산-석문T/L 전선접속개소 전력선 교체공사","No.23~27 전선접소개소 전력선 교체[송전] ○ 170kV GIS 정밀점검(내부 정밀점검, 메카니즘점검) (병행)","2015-10-12 07:30","2015-10-15 18:00","2015-10-12 07:30","2015-10-15 18:00","연속",null,null,null,201508120084,{"$f":"IF(ISERROR(VLOOKUP(D155,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D155,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[152,"대전충남","서산","대산석문#2 T/L","2015년 서산P/O 170kV GIS 정밀점검","○ 170kV GIS 정밀점검(내부 정밀점검, 메카니즘점검) (병행)No.23~27 전선접소개소 전력선 교체[송전]","2015-10-09 07:30","2015-10-11 18:00","2015-10-09 07:30","2015-10-11 18:00","연속",null,null,null,201508120012,{"$f":"IF(ISERROR(VLOOKUP(D156,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D156,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[153,"대전충남","서산","태안태안화력 T/L","태안S/S 170kV 장기사용 GIS 대체공사","○ 170KV GIS 대체(BUS TIE, PT) - 안전이격확보","2015-10-08 09:00","2015-10-08 21:00","2015-10-08 09:00","2015-10-08 21:00","연속",null,null,null,201508130365,{"$f":"IF(ISERROR(VLOOKUP(D157,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D157,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[154,"대전충남","서산","태안안면#1 T/L","태안S/S 170kV 장기사용 GIS 대체공사","○ 170KV GIS 대체(태안안면#1T/L,#1M.Tr GIS 철거)","2015-10-19 09:00","2015-11-11 18:00","2015-10-19 09:00","2015-11-11 18:00","연속",null,null,null,201508130374,{"$f":"IF(ISERROR(VLOOKUP(D158,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D158,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[155,"대전충남","아산","아산S/S 154kV #61 BUS","345kV 아산S/S #4M.Tr 증설공사","○ 아산S/S 170kV GIS설치공사 (인터록케이블 포설 및 결선, 보호배전반 설치 등)","2015-10-12 09:30","2015-10-16 16:00","2015-10-12 09:30","2015-10-16 16:00","연속",null,null,null,201507310026,{"$f":"IF(ISERROR(VLOOKUP(D159,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D159,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[156,"대전충남","아산","아산온양#1 T/L","154kV 아산-온양T/L No.32~36간 안전이격확보공사","[송전]아산-온양T/L 안전이격확보공사 ○ 공사 구간 : No.33~36 ○ 철탑 할입 : 1기 (No.34-1) ○ 철탑 계탑 : 1기 (No.33) ○ OPGW 이설(전자제어파트)","2015-10-28 07:00","2015-10-30 18:00","2015-10-28 07:00","2015-10-30 18:00","연속",null,null,null,201505180005,{"$f":"IF(ISERROR(VLOOKUP(D160,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D160,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[157,"대전충남","아산","아산온양#1 T/L","154kV 아산-온양T/L No.32~36간 안전이격확보공사","[송전]아산-온양T/L 안전이격확보공사 ○ 공사 구간 : No.33~36 ○ 철탑 할입 : 1기 (No.34-1) ○ 철탑 계탑 : 1기 (No.33) ○ OPGW 이설(전자제어파트)","2015-10-22 07:00","2015-10-23 18:00","2015-10-22 07:00","2015-10-23 18:00","연속",null,null,null,201505180003,{"$f":"IF(ISERROR(VLOOKUP(D161,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D161,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[158,"대전충남","아산","아산온양#2 T/L","154kV 아산-온양T/L No.32~36간 안전이격확보공사","[송전]아산-온양T/L 안전이격확보공사 ○ 공사 구간 : No.33~36 ○ 철탑 할입 : 1기 (No.34-1) ○ 철탑 계탑 : 1기 (No.33) ○ OPGW 이설(전자제어파트)","2015-10-24 07:00","2015-10-27 18:00","2015-10-24 07:00","2015-10-27 18:00","연속",null,null,null,201505180004,{"$f":"IF(ISERROR(VLOOKUP(D162,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D162,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[159,"대전충남","아산","아산S/S 154kV #66 BUS","345kV 아산S/S #4M.Tr 증설공사","○ 아산S/S 170kV GIS설치공사 (인터록케이블 포설 및 결선, 보호배전반 설치 등)","2015-10-05 09:30","2015-10-08 17:30","2015-10-05 09:30","2015-10-08 17:30","연속",null,null,null,201507310024,{"$f":"IF(ISERROR(VLOOKUP(D163,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D163,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[160,"대전충남","직할","신탄진대청HP T/L","송전선로 정밀점검","송전선로 정밀점검","2015-10-13 09:00","2015-10-14 18:00","2015-10-13 09:00","2015-10-14 18:00","매일",null,null,null,201508070247,{"$f":"IF(ISERROR(VLOOKUP(D164,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D164,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[161,"대전충남","청양","보령C/C 154kV #2 BUS","보령C/C 154kV 보령LNG T/L 신규수용공사","가. GIS(170kV 50kA 1250A) × 1CCT 설치 나.기타 부대작업 × 1식","2015-10-26 10:00","2015-10-30 18:00","2015-10-26 10:00","2015-10-30 18:00","연속",null,null,null,201508130233,{"$f":"IF(ISERROR(VLOOKUP(D165,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D165,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[162,"대전충남","청양","보령C/C 154kV #1 BUS","보령C/C 154kV 보령LNG T/L 신규수용공사","가. GIS(170kV 50kA 1250A) × 1CCT 설치 나.기타 부대작업 × 1식","2015-10-19 10:00","2015-10-23 18:00","2015-10-19 10:00","2015-10-23 18:00","연속",null,null,null,201508130232,{"$f":"IF(ISERROR(VLOOKUP(D166,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D166,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[163,"대전충남","청양","청양신풍#1 T/L","신풍S/S 154kV GIS 불량 DC 컨버터 교체","○ 신풍S/S 154kV GIS 불량 DC 컨버터 교체 (경보창구용 DC 컨버터 불량 교체 및 보조계전기 접점변경)","2015-10-01 09:00","2015-10-01 12:00","2015-10-01 09:00","2015-10-01 12:00","당일",null,null,null,201508130072,{"$f":"IF(ISERROR(VLOOKUP(D167,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D167,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[164,"대전충남","청양","옥산장항#1 T/L","장항S/S 170kV 장기사용 GIS 교체공사","○ 장항S/S 154kV 장기사용 GIS 교체공사 (교체공사로 인한 장기 휴전)","2015-10-12 09:00","2015-10-28 18:00","2015-10-12 09:00","2015-10-28 18:00","연속",null,null,null,201508130067,{"$f":"IF(ISERROR(VLOOKUP(D168,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D168,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[165,"전북","군산","군산영등#2 T/L","154kV 군산-영등#2T/L","군산P/O 154kV LA 점검 공사 영등S/S 154kV 군산-영등#2T/L LA 점검 공사","2015-10-06 09:00","2015-10-06 18:00","2015-10-06 09:00","2015-10-06 18:00","당일",null,null,null,201508030004,{"$f":"IF(ISERROR(VLOOKUP(D169,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D169,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[166,"전북","군산","팔봉봉동#2 T/L","팔봉S/S 154kV 팔봉-봉동#2T/L","팔봉-봉동#2T/L 차단기 보통점검","2015-10-02 10:00","2015-10-02 18:00","2015-10-06 10:00","2015-10-06 18:00","당일",null,null,null,201508170494,{"$f":"IF(ISERROR(VLOOKUP(D170,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D170,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[167,"전북","군산","팔봉봉동#1 T/L","팔봉S/S 154kV 팔봉-봉동#1T/L","팔봉-봉동#1T/L 차단기 보통점검","2015-10-01 10:00","2015-10-01 18:00","2015-10-05 10:00","2015-10-05 18:00","당일",null,null,null,201508170492,{"$f":"IF(ISERROR(VLOOKUP(D171,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D171,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[168,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주 #2T/L 항공장애표시구 설치공사","154kV 신김제-남전주 #1,2T/L 항공장애표시구 설치공사 (국토부) - 신김제-남전주 #1T/L : No15~16호 - 신김제-남전주 #2T/L : No15~16호","2015-10-06 09:00","2015-10-06 18:00","2015-10-06 09:00","2015-10-06 18:00","당일",null,null,null,201508180050,{"$f":"IF(ISERROR(VLOOKUP(D172,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D172,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[169,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주 #1T/L 항공장애표시구 설치공사","154kV 신김제-남전주 #1,2T/L 항공장애표시구 설치공사 (국토부) - 신김제-남전주 #1T/L : No15~16호 - 신김제-남전주 #2T/L : No15~16호","2015-10-05 09:00","2015-10-05 18:00","2015-10-05 09:00","2015-10-05 18:00","당일",null,null,null,201508180049,{"$f":"IF(ISERROR(VLOOKUP(D173,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D173,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[170,"전북","김제","신김제정공#1 T/L","154kV 신김제-정공#1T/L","김제P/O 154KV 차단기 정밀점검공사 - 신김제-정공#1T/L CB정밀점검","2015-10-19 09:00","2015-10-21 18:00","2015-10-19 09:00","2015-10-21 18:00","연속",null,null,null,201508110118,{"$f":"IF(ISERROR(VLOOKUP(D174,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D174,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[171,"전북","김제","신김제정공#2 T/L","154kV 신김제-정공#2T/L","김제P/O 154KV 차단기 정밀점검공사 - 신김제-정공#2T/L CB정밀점검","2015-10-22 09:00","2015-10-24 18:00","2015-10-22 09:00","2015-10-24 18:00","연속",null,null,null,201508110125,{"$f":"IF(ISERROR(VLOOKUP(D175,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D175,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[172,"전북","김제","정공S/S 154kV #1 BUS TIE CB","정공S/S 154kV #1 BUS TIE CB","김제P/O 차단기 보통점검 *. 2014~15년 변전총액공사 -. 154kV 차단기 보통점검","2015-10-01 09:00","2015-10-01 18:00","2015-10-01 09:00","2015-10-01 18:00","당일",null,null,null,201508170185,{"$f":"IF(ISERROR(VLOOKUP(D176,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D176,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[173,"전북","김제","정주고창#1 T/L","154KV 정주-고창#1 T/L","김제P/O 154KV 차단기 정밀점검공사 - 정주-고창#1T/L CB정밀점검","2015-10-13 09:00","2015-10-15 18:00","2015-10-13 09:00","2015-10-15 18:00","연속",null,null,null,201508110128,{"$f":"IF(ISERROR(VLOOKUP(D177,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D177,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[174,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주#1 T/L","154kV 신김제-동전주T/L 송전선로 정밀점검 1.정밀점검 : 1호~11호","2015-10-21 09:00","2015-10-21 18:00","2015-10-21 09:00","2015-10-21 18:00","당일",null,null,null,201508130367,{"$f":"IF(ISERROR(VLOOKUP(D178,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D178,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[175,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주#2 T/L","154kV 신김제-동전주T/L 송전선로 정밀점검 1.정밀점검 : 1호~11호","2015-10-22 09:00","2015-10-22 18:00","2015-10-22 09:00","2015-10-22 18:00","당일",null,null,null,201508130369,{"$f":"IF(ISERROR(VLOOKUP(D179,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D179,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[176,"전북","직할","무주용담수력 T/L","154kV 무주-용담수력T/L","154kV 무주-용담수력T/L 송전선로 정밀점검 송전선로 정밀점검 : 1호-83호","2015-10-12 09:00","2015-10-16 18:00","취소","취소","매일",null,null,null,201508130376,{"$f":"IF(ISERROR(VLOOKUP(D180,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D180,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[177,"전북","직할","북전주진안 T/L","154kV 북전주-진안T/L","북전주S/S 170kV 장기사용 GIS 대체공사(2차분) 가. 170kV 북전주-진안T/L* 1CCT 대체 나. 170kV BusTie(구) * 1CCT 철거 다. Base Channel 및 안전점검대 * 1식 대체 라. 제이케이블 대체공사","2015-10-05 08:00","2015-10-23 18:00","2015-10-05 08:00","2015-10-23 18:00","연속",null,null,null,201508100163,{"$f":"IF(ISERROR(VLOOKUP(D181,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D181,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[178,"광주전남","강진","강진남창#2 T/L","강진남창#2 T/L(변전협력회사 총액공사)","15년 강진전력지사 변전협력회사 총액공사 - 강진S/S 강진-남창#2T/L LA, CVT 보통점검","2015-10-02 14:00","2015-10-02 18:00","2015-10-02 14:00","2015-10-02 18:00","당일",null,null,null,201508170315,{"$f":"IF(ISERROR(VLOOKUP(D182,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D182,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[179,"광주전남","강진","강진남창#1 T/L","강진남창#1 T/L(변전협력회사 총액공사)","15년 강진전력지사 변전협력회사 총액공사 - 강진S/S 강진-남창#1T/L LA, CVT 보통점검","2015-10-02 09:00","2015-10-02 14:00","2015-10-02 09:00","2015-10-02 14:00","당일",null,null,null,201508170314,{"$f":"IF(ISERROR(VLOOKUP(D183,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D183,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[180,"광주전남","강진","나주영암#1 T/L","영암, 대불S/S 170kV 장기사용 GIS대체공사","영암S/S 170kV GIS 3CCT 대체[나주-영암#1,2T/L, BUSTIE), PT&ES포함 - 나주-영암#1T/L GIS, PT&ES대체, (구)BUS-TIE철거","2015-10-01 09:00","2015-10-15 10:00","2015-10-05 09:00","2015-10-19 10:00","연속",null,null,"신뢰도개선",201507150140,{"$f":"IF(ISERROR(VLOOKUP(D184,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D184,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[181,"광주전남","강진","진도S/S 154kV #1 BUS TIE GIS","154kV 화원-진도T/L SW 증설공사","진도S/S 화원-진도#1T/L 677GIS 무부하가압","2015-10-19 11:00","2015-10-21 14:00","2015-10-19 11:00","2015-10-21 14:00","연속",null,null,null,201508120226,{"$f":"IF(ISERROR(VLOOKUP(D185,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D185,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[182,"광주전남","강진","진도S/S 154kV #1 BUS TIE GIS","154kV 화원-진도T/L SW 증설공사","진도S/S 화원-진도#2T/L 687GIS 무부하가압","2015-10-12 11:00","2015-10-14 14:00","2015-10-12 11:00","2015-10-14 14:00","연속",null,null,null,201508120225,{"$f":"IF(ISERROR(VLOOKUP(D186,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D186,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[183,"광주전남","강진","진도S/S 154kV #1 BUS","154kV 화원-진도T/L SW 증설공사","진도S/S 화원-진도#2T/L 687GIS 무부하가압","2015-10-12 11:00","2015-10-14 14:00","2015-10-12 11:00","2015-10-14 14:00","연속",null,null,null,201508120223,{"$f":"IF(ISERROR(VLOOKUP(D187,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D187,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[184,"광주전남","강진","진도S/S 154kV #1 BUS","154kV 화원-진도T/L SW 증설공사","진도S/S 화원-진도#1T/L 677GIS 무부하가압","2015-10-19 11:00","2015-10-21 14:00","2015-10-19 11:00","2015-10-21 14:00","연속",null,null,null,201508120224,{"$f":"IF(ISERROR(VLOOKUP(D188,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D188,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[185,"광주전남","강진","해남진도#1 T/L","154kV 해남진도#1T/L(화원-진도T/L 건설공사)","154kV 화원-진도T/L 건설공사 1. 공사목적 : #2HVDC AC배후계통 보강 및 진도S/S 이중전원 확보 2. 공사개요 가. 철 탑 : 37기 나. 전력선 : ACSR/AW 410㎟ × 2B 14.5km 3. 공사지역 : 해남군 문내면, 진도군 군내면 일원","2015-10-15 08:00","2015-10-21 18:00","2015-10-15 08:00","2015-10-21 18:00","연속",null,null,null,201508130274,{"$f":"IF(ISERROR(VLOOKUP(D189,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D189,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[186,"광주전남","강진","해남화원 T/L","154kV 해남화원T/L(화원-진도T/L 건설공사)","154kV 화원-진도T/L 건설공사 1. 공사목적 : #2HVDC AC배후계통 보강 및 진도S/S 이중전원 확보 2. 공사개요 가. 철 탑 : 37기 나. 전력선 : ACSR/AW 410㎟ × 2B 14.5km 3. 공사지역 : 해남군 문내면, 진도군 군내면 일원","2015-10-22 08:00","2015-10-25 18:00","2015-10-22 08:00","2015-10-25 18:00","연속",null,null,null,201508130287,{"$f":"IF(ISERROR(VLOOKUP(D190,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D190,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[187,"광주전남","강진","해남진도#1 T/L","해남S/S 170kV GIS교체공사(해남-진도T/L GIS교체)","해남S/S 해남-진도T/L GIS 교체공사","2015-10-28 09:00","2015-11-19 18:00","2015-10-28 09:00","2015-11-19 18:00","연속",null,null,null,201508130074,{"$f":"IF(ISERROR(VLOOKUP(D191,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D191,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[188,"광주전남","강진","해남해남CS#1 T/L","해남해남CS#1 T/L(송전정비 협력회사 전선접속개소 해소공사)","14-15년 강진전력지사 송전정비 협력회사 총액공사 - 전선접속개소 해소공사(전선교체)","2015-10-26 08:00","2015-10-29 18:00","2015-10-26 08:00","2015-10-29 18:00","연속",null,null,null,201508170048,{"$f":"IF(ISERROR(VLOOKUP(D192,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D192,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[189,"광주전남","강진","남창해남CS#1 T/L","남창해남CS#1 T/L(송전정비 협력회사 전선접속개소 해소공사)","14-15년 강진전력지사 송전정비 협력회사 총액공사 - 전선접속개소 해소공사(전선교체)","2015-10-26 08:00","2015-10-28 18:00","2015-10-26 08:00","2015-10-28 18:00","연속",null,null,null,201508170051,{"$f":"IF(ISERROR(VLOOKUP(D193,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D193,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[190,"광주전남","강진","남창해남CS#2 T/L","남창해남CS#2 T/L(송전정비 협력회사 전선접속개소 해소공사)","14-15년 강진전력지사 송전정비 협력회사 총액공사 - 전선접속개소 해소공사(전선교체)","2015-10-31 08:00","2015-11-02 18:00","2015-10-31 08:00","2015-11-02 18:00","연속",null,null,null,201508170057,{"$f":"IF(ISERROR(VLOOKUP(D194,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D194,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[191,"광주전남","강진","해남해남CS#2 T/L","해남해남CS#2 T/L(송전정비 협력회사 전선접속개소 해소공사)","14-15년 강진전력지사 송전정비 협력회사 총액공사 - 전선접속개소 해소공사(전선교체)","2015-10-30 08:00","2015-11-02 18:00","2015-10-30 08:00","2015-11-02 18:00","연속",null,null,null,201508170055,{"$f":"IF(ISERROR(VLOOKUP(D195,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D195,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[192,"광주전남","강진","화원진도 T/L","154kV 화원-진도 T/L(화원-진도T/L 건설공사)","154kV 화원-진도T/L 건설공사 1. 공사목적 : #2HVDC AC배후계통 보강 및 진도S/S 이중전원 확보 2. 공사개요 가. 철 탑 : 37기 나. 전력선 : ACSR/AW 410㎟ × 2B 14.5km 3. 공사지역 : 해남군 문내면, 진도군 군내면 일원","2015-10-22 08:00","2015-10-25 18:00","2015-10-22 08:00","2015-10-25 18:00","연속",null,null,null,201508130291,{"$f":"IF(ISERROR(VLOOKUP(D196,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D196,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[193,"광주전남","강진","화원진도 T/L","154kV 화원-진도 T/L(화원-진도T/L 건설공사)","154kV 화원-진도T/L 건설공사 1. 공사목적 : #2HVDC AC배후계통 보강 및 진도S/S 이중전원 확보 2. 공사개요 가. 철 탑 : 37기 나. 전력선 : ACSR/AW 410㎟ × 2B 14.5km 3. 공사지역 : 해남군 문내면, 진도군 군내면 일원","2015-10-08 08:00","2015-10-14 18:00","2015-10-08 08:00","2015-10-14 18:00","연속",null,null,null,201508130268,{"$f":"IF(ISERROR(VLOOKUP(D197,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D197,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[194,"광주전남","광주","계림승주#1(서남권상수도T분기) T/L","154kV 계림-승주T/L 안전이격확보공사","철탑교체 8기 철탑조립 및 전력선 공중이동, 전력선 가선 작업","2015-10-23 07:00","2015-11-06 18:00","2015-10-23 07:00","2015-11-06 18:00","연속",null,null,null,201508170472,{"$f":"IF(ISERROR(VLOOKUP(D198,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D198,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[195,"광주전남","광주","계림승주#2(서남권상수도T분기) T/L","154kV 계림-승주T/L 안전이격확보공사","철탑교체 8기 철탑조립시 안전거리부족으로 철탑 상단 및 하단 안전거리확보 작업","2015-10-15 07:00","2015-10-22 18:00","2015-10-15 07:00","2015-10-22 18:00","연속",null,null,null,201508170471,{"$f":"IF(ISERROR(VLOOKUP(D199,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D199,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[196,"광주전남","광주","신광주일곡#1 T/L","154kV 신광주-일곡 #1T/L","154kV 신광주-일곡T/L 일부구간 지중화공사(요청자시행) 공사구간 : No.4~5 작업내용 : 임시선로 구성","2015-10-15 09:00","2015-10-17 18:00","2015-10-15 09:00","2015-10-17 18:00","연속",null,null,null,201508070206,{"$f":"IF(ISERROR(VLOOKUP(D200,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D200,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[197,"광주전남","광주","신광주일곡#2 T/L","154kV 신광주-일곡 #2T/L","154kV 신광주-일곡T/L 일부구간 지중화공사(요청자시행) 공사구간 : No.4~5 작업내용 : 임시선로 구성","2015-10-12 09:00","2015-10-14 18:00","2015-10-12 09:00","2015-10-14 18:00","연속",null,null,null,201508070202,{"$f":"IF(ISERROR(VLOOKUP(D201,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D201,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[198,"광주전남","순천","여천호남TP#1 T/L","154kV 여천-호남TP#1T/L(조상설비 대체공사)","여천S/S 154kV 조상설비 대체공사 - #1, #2-1, #2-2Sh.C 대체(철거 및 설치)관련 시험가압","2015-10-01 09:00","2015-10-07 18:00","2015-10-01 09:00","2015-10-07 18:00","연속",null,null,null,201508170111,{"$f":"IF(ISERROR(VLOOKUP(D202,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D202,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[199,"광주전남","순천","호남TP여수TP#2 T/L","호남화력 ESS용 GIS설치공사(초기가압)","1. 170kV GIS * 1CCT 2. GIS 초기가압(ESS용 M.Tr, 전력케이블 포함)","2015-10-13 09:00","2015-10-15 18:00","2015-10-13 09:00","2015-10-15 18:00","연속",null,null,null,201507150063,{"$f":"IF(ISERROR(VLOOKUP(D203,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D203,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[200,"광주전남","직할","영광홍농 T/L","영광S/S 영광-홍농T/L(GIS 정밀점검)","영광S/S 영광-홍농T/L GIS 정밀점검","2015-10-05 09:00","2015-10-08 18:00","2015-10-05 09:00","2015-10-08 18:00","연속",null,null,null,201508110174,{"$f":"IF(ISERROR(VLOOKUP(D204,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D204,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[201,"광주전남","직할","비아하남#2(고려시멘트T분기) T/L","하남S/S 비아하남#2(고려시멘트T분기) T/L(안전이격거리 확보)","하남S/S 170kV 장기사용 GIS 대체공사 - 비아-하남#1T/L, BUS-TIE, #3M.Tr 철거 및 대체 휴전사유 : #3M.Tr 및 BUSTIE 작업시 안전이격거리 확보 필요","2015-10-01 09:00","2015-11-16 18:00","2015-10-01 09:00","2015-11-16 18:00","연속",null,null,null,201507030007,{"$f":"IF(ISERROR(VLOOKUP(D205,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D205,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[202,"대구경북","경산","노변효목#2 T/L","노변S/S 모선보호반 교체관련 준공시험(노변-효목#2T/L)","모선보호반 교체 및 준공시험","2015-10-15 11:30","2015-10-15 12:00","2015-10-15 11:30","2015-10-15 12:00","당일",null,null,null,201508060093,{"$f":"IF(ISERROR(VLOOKUP(D206,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D206,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[203,"대구경북","경산","진량노변 T/L","노변S/S 모선보호반 교체관련 준공시험(진량-노변T/L)","모선보호반 교체 및 준공시험","2015-10-15 09:00","2015-10-15 09:30","2015-10-15 09:00","2015-10-15 09:30","당일",null,null,null,201508060088,{"$f":"IF(ISERROR(VLOOKUP(D207,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D207,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[204,"대구경북","경산","신경산노변 T/L","노변S/S 모선보호반 교체관련 준공시험(신경산-노변T/L)","모선보호반 교체 및 준공시험","2015-10-15 09:30","2015-10-15 10:00","2015-10-15 09:30","2015-10-15 10:00","당일",null,null,null,201508060089,{"$f":"IF(ISERROR(VLOOKUP(D208,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D208,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[205,"대구경북","경산","노변효목#1 T/L","노변S/S 모선보호반 교체관련 준공시험(노변-효목#1T/L)","모선보호반 교체 및 준공시험","2015-10-15 10:00","2015-10-15 10:30","2015-10-15 10:00","2015-10-15 10:30","당일",null,null,null,201508060090,{"$f":"IF(ISERROR(VLOOKUP(D209,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D209,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[206,"대구경북","경산","안심신서열병합#1 T/L","안심 및 신서S/Y 154kV 안심-신서열병합#1T/L GIS 초기점검","안심S/S 및 신서S/Y 154kV GIS 초기점검","2015-10-22 09:00","2015-10-22 18:00","2015-10-22 09:00","2015-10-22 18:00","당일",null,null,null,201508060109,{"$f":"IF(ISERROR(VLOOKUP(D210,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D210,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[207,"대구경북","경산","안심신서열병합#2 T/L","안심 및 신서S/Y 154kV 안심-신서열병합#2T/L GIS 초기점검","안심S/S 및 신서S/Y 154kV GIS 초기점검","2015-10-23 09:00","2015-10-23 18:00","2015-10-23 09:00","2015-10-23 18:00","당일",null,null,null,201508060110,{"$f":"IF(ISERROR(VLOOKUP(D211,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D211,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[208,"대구경북","경산","진량노변 T/L","진량S/S 모선보호반 교체관련 준공시험(진량-노변T/L)","진량S/S 모선보호반 교체관련 준공시험(진량-노변T/L)","2015-10-08 09:30","2015-10-08 10:00","2015-10-08 09:30","2015-10-08 10:00","당일",null,null,null,201508060055,{"$f":"IF(ISERROR(VLOOKUP(D212,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D212,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[209,"대구경북","경산","신경산진량 T/L","진량S/S 모선보호반 교체관련 준공시험(신경산-진량T/L)","진량S/S 모선보호반 교체관련 준공시험(신경산-진량T/L)","2015-10-08 09:00","2015-10-08 09:30","2015-10-08 09:00","2015-10-08 09:30","당일",null,null,null,201508060054,{"$f":"IF(ISERROR(VLOOKUP(D213,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D213,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[210,"대구경북","달성","강창성서#1 T/L","송전선로 보호반 판넬교체","송전선로 보호반판넬교체","2015-10-24 09:00","2015-10-25 18:00","2015-10-24 09:00","2015-10-25 18:00","연속",null,null,null,201507030030,{"$f":"IF(ISERROR(VLOOKUP(D214,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D214,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[211,"대구경북","달성","유가구지#1 T/L","154kV 구지S/S #3M.Tr 증설공사","154kV 구지S/S #3M.Tr 증설공사","2015-10-20 09:00","2015-10-30 18:00","2015-10-20 09:00","2015-10-30 18:00","연속",null,null,null,201508040011,{"$f":"IF(ISERROR(VLOOKUP(D215,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D215,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[212,"대구경북","달성","고령논공#2 T/L","논공S/S170kV GIS화 공사","O 154kV 송전선로 절체(옥외철구설비 GIS로 대체) - 인출변경(보강용 빔설치, 지중EBA 연결) - 송전선로 보호반 이설 및 시험 - 인출 단로기 철거(옥외철구) - 기타 부대작업","2015-10-09 08:00","2015-10-10 18:00","2015-10-09 08:00","2015-10-10 18:00","연속",null,null,null,201508100216,{"$f":"IF(ISERROR(VLOOKUP(D216,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D216,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[213,"대구경북","달성","논공유가#1 T/L","154kV현풍분기T/L 건설공사","154kV논공-유가#1/L No.20 - 154kV현풍분기T/L No.1 가선","2015-10-01 09:00","2015-10-08 10:00","2015-10-01 09:00","2015-10-08 10:00","연속",null,null,null,201507080155,{"$f":"IF(ISERROR(VLOOKUP(D217,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D217,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[214,"대구경북","영주","점촌단양 T/L","154kV 점촌-단양 T/L ㅡ 111-118호간 노후취약지지물 교체공사","154kV 점촌-단양 T/L ㅡ 111-118호간 노후취약지지물 교체공사","2015-10-26 09:00","2015-11-04 18:00","2015-10-26 09:00","2015-11-04 18:00","연속",null,null,null,201508100133,{"$f":"IF(ISERROR(VLOOKUP(D218,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D218,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[215,"대구경북","영주","예천점촌#2 T/L","점촌S/S 예천-점촌#2T/L 장기사용 GIS 대체공사","점촌S/S 예천-점촌#2T/L 장기사용 GIS 대체공사","2015-10-02 08:00","2015-10-15 18:00","2015-10-02 08:00","2015-10-15 18:00","연속",null,null,null,201508100135,{"$f":"IF(ISERROR(VLOOKUP(D219,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D219,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[216,"대구경북","영주","상주점촌#1 T/L","점촌S/S 상주-점촌#1T/L 장기사용 GIS 대체공사","점촌S/S 상주-점촌#1T/L 장기사용 GIS 대체공사","2015-10-20 08:00","2015-10-31 17:00","2015-10-20 08:00","2015-10-31 17:00","연속",null,null,null,201508100136,{"$f":"IF(ISERROR(VLOOKUP(D220,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D220,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[217,"대구경북","직할","노변효목#2 T/L","효목S/S GIS(617) 정밀점검","GIS(617) 정밀점검","2015-10-05 09:30","2015-10-08 18:00","2015-10-05 09:30","2015-10-08 18:00","연속",null,null,null,201508060163,{"$f":"IF(ISERROR(VLOOKUP(D221,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D221,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[218,"대구경북","칠곡","서대구칠곡#1 T/L","서대구-칠곡#1T/L GIS 대체","서대구-칠곡#1T/L GIS 대체","2015-10-19 09:30","2015-11-05 18:00","2015-10-19 09:30","2015-11-05 18:00","연속",null,null,null,201508050029,{"$f":"IF(ISERROR(VLOOKUP(D222,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D222,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[219,"대구경북","칠곡","칠곡인동#2 T/L","칠곡-인동#2T/L GIS 대체","칠곡-인동#2T/L GIS 대체","2015-10-01 09:30","2015-10-15 18:00","2015-10-01 09:30","2015-10-15 18:00","연속",null,null,null,201508050019,{"$f":"IF(ISERROR(VLOOKUP(D223,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D223,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[220,"대구경북","포항","대송남포항 T/L","154kV 왕신분기T/L 건설공사","기설 154kV 대송-북포항T/L No.25,26~신설 154kV 왕신S/S 철탑 2기 건설","2015-10-31 09:00","2015-11-06 18:00","2015-10-31 09:00","2015-11-06 18:00","연속",null,null,null,201508050090,{"$f":"IF(ISERROR(VLOOKUP(D224,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D224,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[221,"대구경북","포항","대송북포항 T/L","154kV 왕신분기T/L 건설공사","기설 154kV 대송-북포항T/L No.25,26~신설 154kV 왕신S/S 철탑 2기 건설","2015-10-19 09:00","2015-10-30 18:00","2015-10-19 09:00","2015-10-30 18:00","연속",null,null,null,201508050091,{"$f":"IF(ISERROR(VLOOKUP(D225,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D225,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[222,"대구경북","포항","신포항영일#2 T/L","영일S/S 170kV 장기사용 GIS 대체공사","GIS 대체관련 #1BUS 무부하 가압선로","2015-10-14 20:00","2015-10-17 08:00","2015-10-14 20:00","2015-10-17 08:00","연속",null,null,null,201508070077,{"$f":"IF(ISERROR(VLOOKUP(D226,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D226,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[223,"대구경북","포항","영일S/S 154kV #1 BUS TIE CB","영일S/S 170kV 장기사용 GIS 대체공사","6100 GIS 대체","2015-10-06 08:00","2015-10-25 20:00","2015-10-06 08:00","2015-10-25 20:00","연속",null,null,null,201508070057,{"$f":"IF(ISERROR(VLOOKUP(D227,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D227,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[224,"대구경북","포항","영일포항#1 T/L","영일S/S 170kV 장기사용 GIS 대체공사","637 GIS 대체","2015-10-06 08:00","2015-10-25 20:00","2015-10-06 08:00","2015-10-25 20:00","연속",null,null,null,201508070052,{"$f":"IF(ISERROR(VLOOKUP(D228,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D228,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[225,"대구경북","포항","영일양북#1 T/L","영일S/S 170kV 장기사용 GIS 대체공사","GIS 대체 관련 안전확보(매일)","2015-10-06 08:00","2015-10-23 20:00","2015-10-06 08:00","2015-10-23 20:00","매일",null,null,null,201508070066,{"$f":"IF(ISERROR(VLOOKUP(D229,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D229,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[226,"대구경북","포항","신포항영일#2 T/L","영일S/S 170kV 장기사용 GIS 대체공사","GIS 대체관련 #2BUS 무부하 가압 선로","2015-10-07 18:00","2015-10-08 08:00","2015-10-07 18:00","2015-10-08 08:00","연속",null,null,null,201508070069,{"$f":"IF(ISERROR(VLOOKUP(D230,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D230,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[227,"대구경북","포항","영일포항#2 T/L","영일S/S 170kV 장기사용 GIS 대체공사","GIS 대체 관련 BUS TIE 철거에 따른 154kV BUS 절체용","2015-10-08 08:00","2015-10-08 09:00","2015-10-08 08:00","2015-10-08 09:00","당일",null,null,null,201508070076,{"$f":"IF(ISERROR(VLOOKUP(D231,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D231,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[228,"대구경북","포항","영일포항#2 T/L","영일S/S 170kV 장기사용 GIS 대체공사","GIS 대체관련 BUS TIE 철거에 따른 BUS 절체용","2015-10-17 08:00","2015-10-17 09:00","2015-10-17 08:00","2015-10-17 09:00","당일",null,null,null,201508070082,{"$f":"IF(ISERROR(VLOOKUP(D232,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D232,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[229,"대구경북","포항","신포항영일#2 T/L","영일S/S 170kV 장기사용 GIS 대체공사","GIS 대체관련 #2BUS 무부하가압 선로","2015-10-23 20:00","2015-10-25 20:00","2015-10-23 20:00","2015-10-25 20:00","연속",null,null,null,201508070092,{"$f":"IF(ISERROR(VLOOKUP(D233,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D233,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[230,"대구경북","포항","영일포항#2 T/L","영일S/S 170kV 장기사용 GIS 대체공사","627 GIS 대체","2015-10-26 08:00","2015-11-09 20:00","2015-10-26 08:00","2015-11-09 20:00","연속",null,null,null,201508070095,{"$f":"IF(ISERROR(VLOOKUP(D234,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D234,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[231,"대구경북","포항","신포항영일#2 T/L","영일S/S 170kV 장기사용 GIS 대체공사","GIS 대체관련 #2BUS 무부하 가압선로","2015-10-26 18:00","2015-10-27 08:00","2015-10-26 18:00","2015-10-27 08:00","연속",null,null,null,201508070108,{"$f":"IF(ISERROR(VLOOKUP(D235,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D235,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[232,"대구경북","포항","영일포항#1 T/L","영일S/S 영일-포항#1T/L 휴전작업","GIS 대체관련 안전확보(매일)","2015-10-27 08:00","2015-11-09 20:00","2015-10-27 08:00","2015-11-09 20:00","매일",null,null,null,201508070118,{"$f":"IF(ISERROR(VLOOKUP(D236,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D236,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[233,"대구경북","포항","신포항영일#2 T/L","영일S/S 신포항-영일#2T/L 휴전작업","영일S/S GIS 대체관련 #1BUS 무부하가압용 선로","2015-10-31 20:00","2015-11-03 08:00","2015-10-31 20:00","2015-11-03 08:00","연속",null,null,null,201508170285,{"$f":"IF(ISERROR(VLOOKUP(D237,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D237,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[234,"대구경북","포항","옥동외동#1 T/L","외동S/S 외동-옥동#1T/L 휴전작업","LA 교체","2015-10-06 10:00","2015-10-06 18:00","2015-10-06 10:00","2015-10-06 18:00","당일",null,null,null,201508070015,{"$f":"IF(ISERROR(VLOOKUP(D238,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D238,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[235,"대구경북","포항","건천천북#2 T/L","천북S/S 건천-천북#2T/L 휴전작업","천북S/S 모선보호반 대체 관련 휴전","2015-10-28 16:00","2015-10-28 16:30","2015-10-28 16:00","2015-10-28 16:30","당일",null,null,null,201508070306,{"$f":"IF(ISERROR(VLOOKUP(D239,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D239,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[236,"대구경북","포항","건천천북#1 T/L","천북S/S 건천-천북#1T/L 휴전작업","천북S/S 모선보호반 대체 관련 휴전","2015-10-28 14:30","2015-10-28 15:00","2015-10-28 14:30","2015-10-28 15:00","당일",null,null,null,201508070303,{"$f":"IF(ISERROR(VLOOKUP(D240,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D240,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[237,"대구경북","포항","건천천북#2 T/L","천북S/S 건천-천북#2T/L 휴전작업","보호반 PNL 대체","2015-10-15 09:30","2015-10-17 18:00","2015-10-15 09:30","2015-10-17 18:00","연속",null,null,null,201508070003,{"$f":"IF(ISERROR(VLOOKUP(D241,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D241,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[238,"대구경북","포항","건천천북#1 T/L","천북S/S 건천-천북#1T/L 휴전작업","보호반 PNL 대체","2015-10-12 09:30","2015-10-14 18:00","2015-10-12 09:30","2015-10-14 18:00","연속",null,null,null,201508070002,{"$f":"IF(ISERROR(VLOOKUP(D242,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D242,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[239,"부산울산","동부산","명례정관 T/L","154kV 명례-정관 T/L 정밀점검","154kV 명례-정관 T/L 정밀점검(154kV 정관분기 T/L) -작업구간: 154kV 명례-고리 T/L 4호 ~ 정관 C/H (25기)","2015-10-15 09:00","2015-10-16 18:00","2015-10-15 09:00","2015-10-16 18:00","연속",null,null,null,201508110283,{"$f":"IF(ISERROR(VLOOKUP(D243,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D243,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[240,"부산울산","동부산","명례고리NP T/L","명례S/S 170kV GIS 초기점검","명례S/S 170kV 637 GIS 초기점검(명례-고리T/L)","2015-10-01 09:30","2015-10-01 17:00","2015-10-01 09:30","2015-10-01 17:00","당일",null,null,null,201508130210,{"$f":"IF(ISERROR(VLOOKUP(D244,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D244,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[241,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창T/L 지장철탑이설공사(요청자 직접시행)","지장이설 본선로 구성, 구간: 15 ~ 17.1호","2015-10-19 09:00","2015-10-20 18:00","2015-10-19 09:00","2015-10-20 18:00","연속",null,null,null,201508040081,{"$f":"IF(ISERROR(VLOOKUP(D245,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D245,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[242,"부산울산","동부산","웅촌서창#2 T/L","154kV 웅촌-서창T/L 지장철탑이설공사(요청자 직접시행)","지장이설 본선로 구성, 구간: 15 ~ 17.1호","2015-10-21 09:00","2015-10-22 18:00","2015-10-21 09:00","2015-10-22 18:00","연속",null,null,null,201508040082,{"$f":"IF(ISERROR(VLOOKUP(D246,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D246,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[243,"부산울산","동부산","정관고리NP T/L","154kV 정관-고리NP T/L 정밀점검","154kV 정관-고리NP T/L 정밀점검(154kV 정관분기 T/L) -작업구간: 154kV 명례-고리NP T/L 4호 ~ 정관 C/H(25기)","2015-10-13 09:00","2015-10-14 18:00","2015-10-13 09:00","2015-10-14 18:00","연속",null,null,null,201508110282,{"$f":"IF(ISERROR(VLOOKUP(D247,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D247,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[244,"부산울산","북부산","매리김해#1 T/L","김해S/S 170kV 장기사용 GIS 대체공사","시험가압(#3M.Tr1차 및 신설BUS-TIE #1BUS)","2015-10-19 18:00","2015-10-21 18:00","2015-10-19 18:00","2015-10-21 18:00","연속",null,null,null,201508130038,{"$f":"IF(ISERROR(VLOOKUP(D248,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D248,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[245,"부산울산","북부산","매리김해#1 T/L","김해S/S 170kV 장기사용 GIS 대체공사","시험가압(#3M.Tr 1차 GIS #2BUS 고깔설치부)","2015-10-07 16:00","2015-10-07 18:00","2015-10-07 16:00","2015-10-07 18:00","연속",null,null,null,201508130037,{"$f":"IF(ISERROR(VLOOKUP(D249,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D249,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[246,"부산울산","북부산","매리김해#1 T/L","김해S/S 170kV 장기사용 GIS 대체공사","시험가압(#3M.Tr 1차, 신설BUS-TIE 전부분)","2015-10-28 18:00","2015-10-30 18:00","2015-10-28 18:00","2015-10-30 18:00","연속",null,null,null,201508130039,{"$f":"IF(ISERROR(VLOOKUP(D250,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D250,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[247,"부산울산","북부산","김해S/S 154kV #2 BUS","김해S/S 170kV 장기사용 GIS 대체공사","BUS TIE 설치 및 #3M.Tr 1차 GIS 대체","2015-10-05 09:00","2015-10-07 18:00","2015-10-05 09:00","2015-10-07 18:00","연속",null,null,null,201508130034,{"$f":"IF(ISERROR(VLOOKUP(D251,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D251,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[248,"부산울산","북부산","김해S/S 154kV #1 BUS","김해S/S 170kV 장기사용 GIS 대체공사","BUS TIE 설치 및 #3M.Tr 1차 GIS 대체","2015-10-08 09:00","2015-10-21 18:00","2015-10-08 09:00","2015-10-21 18:00","연속",null,null,null,201508130036,{"$f":"IF(ISERROR(VLOOKUP(D252,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D252,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[249,"부산울산","북부산","김해S/S 154kV #2 BUS","김해S/S 170kV 장기사용 GIS 대체공사","BUS TIE 설치 및 #3M.Tr 1차 GIS 대체","2015-10-22 09:00","2015-10-30 18:00","2015-10-22 09:00","2015-10-30 18:00","연속",null,null,null,201508130035,{"$f":"IF(ISERROR(VLOOKUP(D253,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D253,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[250,"부산울산","북부산","북부산미남#1 T/L","154kV 미남S/S 옥내화 관련 지중화 사업","미남S/S 옥내화에 따른 기설선로 인출정비 - 선로구간 : 154㎸ 미남S/S(옥내) ~ C/H - 선로길이 : 0.10㎞","2015-10-17 09:00","2015-11-16 18:00","2015-10-17 09:00","2015-11-16 18:00","연속",null,null,null,201508120213,{"$f":"IF(ISERROR(VLOOKUP(D254,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D254,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[251,"부산울산","북부산","미남덕포#2 T/L","154kV 미남S/S 옥내화 관련 지중화 사업","미남S/S 옥내화에 따른 기설선로 인출정비 - 선로구간 : 154㎸ 미남S/S(옥내) ~ C/H - 선로길이 : 0.10㎞","2015-10-17 09:00","2015-10-30 18:00","2015-10-17 09:00","2015-10-30 18:00","연속",null,null,null,201508120211,{"$f":"IF(ISERROR(VLOOKUP(D255,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D255,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[252,"부산울산","북부산","북부산미남#2 T/L","154kV 미남S/S 옥내화 관련 지중화 사업","미남S/S 옥내화에 따른 기설선로 인출정비 -선로구간 : 154㎸ 미남S/S(옥내) ~ C/H -선로길이 : 0.10㎞","2015-10-17 09:00","2015-11-16 18:00","2015-10-17 09:00","2015-11-16 18:00","연속",null,null,null,201508120214,{"$f":"IF(ISERROR(VLOOKUP(D256,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D256,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[253,"부산울산","북부산","미남덕포#1 T/L","154kV 미남S/S 옥내화 관련 지중화 사업","미남S/S 옥내화에 따른 기설선로 인출정비 - 선로구간 : 154㎸ 미남S/S(옥내) ~ C/H - 선로길이 : 0.10㎞","2015-10-17 09:00","2015-11-16 18:00","2015-10-17 09:00","2015-11-16 18:00","연속",null,null,null,201508120212,{"$f":"IF(ISERROR(VLOOKUP(D257,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D257,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[254,"부산울산","북부산","언양산막#2 T/L","장기사용 배전반 대체공사","언양-산막#2T/L 보호배전반 대체","2015-10-27 09:00","2015-10-31 18:00","2015-10-27 09:00","2015-10-31 18:00","연속",null,null,null,201508130043,{"$f":"IF(ISERROR(VLOOKUP(D258,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D258,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[255,"부산울산","북부산","신울산언양#1 T/L","154kV 언양S/S #4M.Tr 증설공사","* 154kV GIS 1CCT 설치 ==> #60BUS 시험가압 선로(48시간)","2015-10-09 14:00","2015-10-11 14:00","2015-10-09 14:00","2015-10-11 14:00","연속",null,null,null,201508170305,{"$f":"IF(ISERROR(VLOOKUP(D259,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D259,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[256,"부산울산","북부산","신울산언양#1 T/L","154kV 언양S/S #4M.Tr 증설공사","* 154kV GIS 1CCT 설치 ==> #65BUS 시험가압 선로(48시간)","2015-10-15 14:00","2015-10-17 14:00","2015-10-15 14:00","2015-10-17 14:00","연속",null,null,null,201508170307,{"$f":"IF(ISERROR(VLOOKUP(D260,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D260,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[257,"부산울산","북부산","언양산막#1 T/L","장기사용 배전반 대체공사","언양-산막#1T/L 보호배전반 대체","2015-10-23 09:00","2015-10-26 18:00","2015-10-23 09:00","2015-10-26 18:00","연속",null,null,null,201508130042,{"$f":"IF(ISERROR(VLOOKUP(D261,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D261,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[258,"부산울산","서부산","서부산S/S #2 S/T CB","서부산S/S 154kV #2S/T GIS 정밀점검","서부산S/S 154kV #2S/T GIS(6L7) 정밀점검","2015-10-12 10:00","2015-10-16 18:00","2015-10-12 10:00","2015-10-16 18:00","연속",null,null,null,201508130225,{"$f":"IF(ISERROR(VLOOKUP(D262,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D262,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[259,"부산울산","서부산","서부산엄궁#2 T/L","345kV 서부산-북부산T/L 등 8개T/L 이설공사","154kV XLPE 2000㎟ 케이블 0.177km 이설","2015-10-21 08:00","2015-11-09 18:00","2015-10-21 08:00","2015-11-09 18:00","연속",null,null,null,201508180078,{"$f":"IF(ISERROR(VLOOKUP(D263,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D263,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[260,"부산울산","서부산","서부산엄궁#1 T/L","345kV 서부산-북부산T/L 등 8개T/L 이설공사","154kV XLPE 2000㎟ 케이블 0.177km 이설","2015-10-01 08:00","2015-10-20 18:00","2015-10-01 08:00","2015-10-20 18:00","연속",null,null,null,201508170513,{"$f":"IF(ISERROR(VLOOKUP(D264,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D264,[1]시송전설비!$C$2:$O$130,13,0))","v":"○"}]
[261,"부산울산","울산","신울산웅촌#1 T/L","2014-15년 변전협력 총액공사","송전선로 보호배전반 교체","2015-10-05 09:00","2015-10-06 18:00","2015-10-05 09:00","2015-10-06 18:00","연속",null,null,null,201508190154,{"$f":"IF(ISERROR(VLOOKUP(D265,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D265,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[262,"부산울산","울산","신울산영남TP#2 T/L","2014-15년 울산전력지사 변전협력 총액공사","변전소 양단 보호배전반 교체","2015-10-24 09:00","2015-10-25 18:00","2015-10-24 09:00","2015-10-25 18:00","연속",null,null,null,201508070176,{"$f":"IF(ISERROR(VLOOKUP(D266,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D266,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[263,"부산울산","울산","신울산영남TP#1 T/L","154kV 석지T/L 전력계통 안정화 구축공사","154kV 석지#2T/L 증설","2015-10-26 00:08","2015-10-29 18:00","2015-10-26 00:08","2015-10-29 18:00","매일",null,null,null,201508070177,{"$f":"IF(ISERROR(VLOOKUP(D267,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D267,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[264,"부산울산","울산","신울산울산#1 T/L","154kV 석지T/L 전력계통 안정화 구축공사(안전이격)","154kV 석지#2T/L 증설","2015-10-26 08:00","2015-10-29 18:00","2015-10-26 08:00","2015-10-29 18:00","매일",null,null,null,201508070178,{"$f":"IF(ISERROR(VLOOKUP(D268,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D268,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[265,"부산울산","울산","용연울산TP#3 T/L","울산화력S/Y 154kV 보호제어설비 전담운영공사","보호배전반 이설, 제어케이블 수용","2015-10-29 08:00","2015-11-02 18:00","2015-10-29 08:00","2015-11-02 18:00","연속",null,null,null,201508070170,{"$f":"IF(ISERROR(VLOOKUP(D269,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D269,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[266,"부산울산","직할","부산수정#2 T/L","2015년도 직할 관내 170kV GIS 정밀점검공사","- 170kV GIS 정밀점검","2015-10-29 09:00","2015-10-31 18:00","2015-10-29 09:00","2015-10-31 18:00","연속",null,null,null,201508110095,{"$f":"IF(ISERROR(VLOOKUP(D270,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D270,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[267,"부산울산","직할","부산수정#1 T/L","2015년도 직할 관내 170kV GIS 정밀점검공사","- 170kV GIS 정밀점검","2015-10-26 09:00","2015-10-28 18:00","2015-10-26 09:00","2015-10-28 18:00","연속",null,null,null,201508110093,{"$f":"IF(ISERROR(VLOOKUP(D271,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D271,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[268,"부산울산","직할","수정범일#1 T/L","2015년도 직할 관내 170kV GIS 정밀점검공사","- 시험가압 선로:BUS-TIE 측 #1DS+CB","2015-10-24 16:00","2015-10-24 18:00","2015-10-24 16:00","2015-10-24 18:00","당일",null,null,null,201508110182,{"$f":"IF(ISERROR(VLOOKUP(D272,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D272,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[269,"부산울산","직할","수정범일#1 T/L","2015년도 직할 관내 170kV GIS 정밀점검공사","- 시험가압 선로: BUS-TIE측 #2DS","2015-10-22 18:00","2015-10-22 20:00","2015-10-22 18:00","2015-10-22 20:00","당일",null,null,null,201508110181,{"$f":"IF(ISERROR(VLOOKUP(D273,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D273,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[270,"부산울산","직할","수정범일#1 T/L","2015년도 직할 관내 170kV GIS 정밀점검공사","- 시험가압 대상선로: 항만청 #1T/L(637) 측 #1DS+CB+상부","2015-10-21 16:00","2015-10-21 18:00","2015-10-21 16:00","2015-10-21 18:00","당일",null,null,null,201508110180,{"$f":"IF(ISERROR(VLOOKUP(D274,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D274,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[271,"부산울산","직할","수정범일#1 T/L","2015년도 직할 관내 170kV GIS 정밀점검공사","- 170kV GIS 정밀점검","2015-10-12 09:00","2015-10-14 18:00","2015-10-12 09:00","2015-10-14 18:00","연속",null,null,null,201508110086,{"$f":"IF(ISERROR(VLOOKUP(D275,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D275,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[272,"부산울산","직할","수정범일#1 T/L","2015년도 직할 관내 170kV GIS 정밀점검공사","- 시험가압 대상선로: 항만청 #1T/L(637) 측 #2DS","2015-10-19 18:00","2015-10-19 20:00","2015-10-19 18:00","2015-10-19 20:00","당일",null,null,null,201508110173,{"$f":"IF(ISERROR(VLOOKUP(D276,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D276,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[273,"부산울산","직할","수정범일#2 T/L","2015년도 직할 관내 170kV GIS 정밀점검공사","- 170kV GIS 정밀점검","2015-10-15 09:00","2015-10-17 18:00","2015-10-15 09:00","2015-10-17 18:00","연속",null,null,null,201508110091,{"$f":"IF(ISERROR(VLOOKUP(D277,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D277,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[274,"경남","직할","마천진해#1 T/L","정밀점검(2015 가공송전선로 순시점검 위탁공사)","정밀점검(1~35호, 35기), 주말(17,18일)제외","2015-10-16 08:30","2015-10-21 18:00","2015-10-16 08:30","2015-10-20 18:00","매일",null,null,null,201508100182,{"$f":"IF(ISERROR(VLOOKUP(D278,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D278,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[275,"경남","직할","마천진해#2 T/L","정밀점검(2015 가공송전선로 순시점검 위탁공사)","정밀점검(1~4호, 4기)","2015-10-21 08:30","2015-10-21 13:00","2015-10-17 08:30","2015-10-17 13:00","당일",null,null,null,201508100184,{"$f":"IF(ISERROR(VLOOKUP(D279,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D279,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[276,"경남","직할","차룡창공#1 T/L","창공S/S #4M.Tr 이설공사","창공S/S 154kV 옥외철구설비 GIS화 공사에 따른 GIS 설치장소 확보를 위해 #4M.Tr 임시 이설 - #4M.Tr 모선 LS를 차룡-창공#1T/L과 공용 사용 (LS 설치 부지 없음) - #4M.Tr 시험가압","2015-10-09 09:00","2015-10-11 18:00","2015-10-09 09:00","2015-10-11 18:00","연속",null,null,null,201508030067,{"$f":"IF(ISERROR(VLOOKUP(D280,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D280,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[277,"경남","진주","함양거창#1 T/L","거창-합천#1T/L 차단기 정밀점검 시험가압","거창-합천#1T/L 차단기 정밀점검 #1DS 시험가압","2015-10-20 13:00","2015-10-20 13:30","2015-10-20 13:00","2015-10-20 13:30","당일",null,null,null,201508070212,{"$f":"IF(ISERROR(VLOOKUP(D281,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D281,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[278,"경남","진주","거창S/S 154kV #2 BUS","거창-합천#1T/L 차단기 정밀점검","거창-합천#1T/L 차단기 정밀점검","2015-10-20 13:30","2015-10-21 18:30","2015-10-20 13:30","2015-10-21 18:30","연속",null,null,null,201508070211,{"$f":"IF(ISERROR(VLOOKUP(D282,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D282,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[279,"경남","진주","거창합천#1 T/L","거창-합천#1T/L 차단기 정밀점검","거창-합천#1T/L 차단기 정밀점검","2015-10-19 10:00","2015-10-21 18:30","2015-10-19 10:00","2015-10-21 18:30","연속",null,null,null,201508070209,{"$f":"IF(ISERROR(VLOOKUP(D283,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D283,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[280,"경남","진주","거창S/S 154kV #1 BUS","거창-합천#1T/L 차단기 정밀점검","거창-합천#1T/L 차단기 정밀점검","2015-10-19 10:00","2015-10-20 13:30","2015-10-19 10:00","2015-10-20 13:30","연속",null,null,null,201508070210,{"$f":"IF(ISERROR(VLOOKUP(D284,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D284,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[281,"경남","진주","함양거창#2 T/L","거창-합천#1T/L 차단기 정밀점검 시험가압","거창-합천#1T/L 차단기 정밀점검 시험가압","2015-10-21 18:00","2015-10-21 18:30","2015-10-21 18:00","2015-10-21 18:30","당일",null,null,null,201508070213,{"$f":"IF(ISERROR(VLOOKUP(D285,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D285,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[282,"경남","진주","함양거창#1 T/L","함양-거창#1T/L PNL 대체","함양-거창#1T/L PNL 대체","2015-10-01 09:30","2015-10-02 18:30","2015-10-01 09:30","2015-10-02 18:30","연속",null,null,null,201508070220,{"$f":"IF(ISERROR(VLOOKUP(D286,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D286,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[283,"경남","진주","광양하동#1 T/L","154kV 광양-하동T/L 노후전력선 교체공사","1. 전력선교체구간 : 하동S/T∼37호 10.58km (31∼35호 구간 지장이설 시 교체) ※ ACSR 330㎟×S×2C (교체전, 30년 이상 사용) → HSTACIR/AW 330㎟×S×2C (교체후) 2. 철탑설치 및 철거 : 1기(22호) 3. 철탑계탑 : 2기(27호, 30호) 4. 기타공사 : 금구류교체 등","2015-10-01 08:30","2015-10-16 20:00","2015-10-01 08:30","2015-10-16 20:00","연속",null,null,null,201508040023,{"$f":"IF(ISERROR(VLOOKUP(D287,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D287,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[284,"경남","진주","광양하동#2 T/L","154kV 광양-하동T/L 노후전력선 교체공사","1. 전력선교체구간 : 하동S/T∼37호 10.58km (31∼35호 구간 지장이설 시 교체) ※ ACSR 330㎟×S×2C (교체전, 30년 이상 사용) → HSTACIR/AW 330㎟×S×2C (교체후) 2. 철탑설치 및 철거 : 1기(22호) 3. 철탑계탑 : 2기(27호, 30호) 4. 기타공사 : 금구류교체 등","2015-10-01 08:30","2015-10-16 20:00","2015-10-01 08:30","2015-10-16 20:00","연속",null,null,null,201508040024,{"$f":"IF(ISERROR(VLOOKUP(D288,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D288,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[285,"경남","진주","합천S/S 154kV #1 BUS","합천-합천수력#1T/L 차단기 정밀점검","합천-합천수력#1T/L 차단기 정밀점검","2015-10-12 09:30","2015-10-13 13:30","2015-10-12 09:30","2015-10-13 13:30","연속",null,null,null,201508070198,{"$f":"IF(ISERROR(VLOOKUP(D289,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D289,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[286,"경남","진주","합천수력#1 T/L","합천-합천수력#1T/L 차단기 정밀점검","합천-합천수력#1T/L 차단기 정밀점검","2015-10-12 09:30","2015-10-14 14:00","2015-10-12 09:30","2015-10-14 14:00","연속",null,null,null,201508070197,{"$f":"IF(ISERROR(VLOOKUP(D290,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D290,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[287,"경남","진주","거창합천#1 T/L","합천-합천수력#1T/L 차단기 정밀점검 시험가압","합천-합천수력#1T/L 차단기 정밀점검 시험가압","2015-10-13 13:00","2015-10-13 13:30","2015-10-13 13:00","2015-10-13 13:30","당일",null,null,null,201508070199,{"$f":"IF(ISERROR(VLOOKUP(D291,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D291,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[288,"경남","진주","합천S/S 154kV #2 BUS","합천-합천수력#1T/L 차단기 정밀점검","합천-합천수력#1T/L 차단기 정밀점검","2015-10-13 13:30","2015-10-14 14:00","2015-10-13 13:30","2015-10-14 14:00","연속",null,null,null,201508070201,{"$f":"IF(ISERROR(VLOOKUP(D292,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D292,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[289,"경남","진주","거창합천#2 T/L","합천-합천수력#1T/L 차단기 정밀점검 시험가압","합천-합천수력#1T/L 차단기 정밀점검 시험가압","2015-10-14 13:30","2015-10-14 14:00","2015-10-14 13:30","2015-10-14 14:00","당일",null,null,null,201508070200,{"$f":"IF(ISERROR(VLOOKUP(D293,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D293,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[290,"경남","진주","합천S/S 154kV #1 BUS","합천-합천수력#2T/L 차단기 정밀점검","합천-합천수력#2T/L 차단기 정밀점검","2015-10-14 14:00","2015-10-15 13:30","2015-10-14 14:00","2015-10-15 13:30","연속",null,null,null,201508070204,{"$f":"IF(ISERROR(VLOOKUP(D294,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D294,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[291,"경남","진주","거창합천#2 T/L","합천-합천수력#2T/L 차단기 정밀점검 시험가압","합천-합천수력#2T/L 차단기 정밀점검 시험가압","2015-10-16 18:00","2015-10-16 18:30","2015-10-16 18:00","2015-10-16 18:30","당일",null,null,null,201508070208,{"$f":"IF(ISERROR(VLOOKUP(D295,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D295,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[292,"경남","진주","거창합천#1 T/L","합천-합천수력#2T/L 차단기 정밀점검 시험가압","합천-합천수력#2T/L 차단기 정밀점검 시험가압","2015-10-15 13:00","2015-10-15 13:30","2015-10-15 13:00","2015-10-15 13:30","당일",null,null,null,201508070207,{"$f":"IF(ISERROR(VLOOKUP(D296,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D296,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[293,"경남","진주","합천수력#2 T/L","합천-합천수력#2T/L 차단기 정밀점검","합천-합천수력#2T/L 차단기 정밀점검","2015-10-14 14:00","2015-10-16 18:30","2015-10-14 14:00","2015-10-16 18:30","연속",null,null,null,201508070203,{"$f":"IF(ISERROR(VLOOKUP(D297,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D297,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[294,"경남","진주","합천S/S 154kV #2 BUS","합천-합천수력#2T/L 차단기 정밀점검","합천-합천수력#2T/L 차단기 정밀점검","2015-10-15 13:30","2015-10-16 18:30","2015-10-15 13:30","2015-10-16 18:30","연속",null,null,null,201508070205,{"$f":"IF(ISERROR(VLOOKUP(D298,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D298,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[295,"경남","통영","거제S/S 154kV #1 Sh.C CB","거제S/S 154kV #1-3 Sh.C GIS(6179-3) 정밀점검공사","거제S/S 154kV #1-3 Sh.C GIS(6179-3) 정밀점검공사 및 #1 Sh.C Main GIS(6179) 보통점검","2015-10-01 09:30","2015-10-02 18:30","2015-10-01 09:30","2015-10-02 18:30","연속",null,null,null,201508050164,{"$f":"IF(ISERROR(VLOOKUP(D299,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D299,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[296,"경남","통영","고성통영 T/L","154kV 신고성-통영T/L 96호 지장이설공사","- 가철탑 설치 및 고성-통영T/L 가이설","2015-10-09 07:00","2015-10-09 19:00","2015-10-09 07:00","2015-10-09 19:00","당일",null,null,null,201508070166,{"$f":"IF(ISERROR(VLOOKUP(D300,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D300,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[297,"경남","통영","고성통영 T/L","154kV 신고성-통영T/L 96호 지장이설공사","- 본철탑 설치 및 고성-통영T/L 본이설","2015-10-17 07:00","2015-10-17 19:00","2015-10-17 07:00","2015-10-17 19:00","당일",null,null,null,201508070175,{"$f":"IF(ISERROR(VLOOKUP(D301,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D301,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[298,"경남","통영","고성통영 T/L","고성S/S 154kV 고성-통영T/L GIS UHF 센서교체공사","고성S/S 154kV 고성-통영T/L GIS UHF 센서교체공사 - 병행 : 송전직할 철탑이설 등 2건","2015-10-17 07:00","2015-10-18 18:30","2015-10-17 07:00","2015-10-18 18:30","연속",null,null,null,201508050188,{"$f":"IF(ISERROR(VLOOKUP(D302,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D302,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[299,"경남","통영","삼천포사천#2 T/L","[154kV 삼천포-사천 #2T/L] 위탁회사 정밀점검","안전이격(154kV 신고성-삼천포 #2T/L 정밀점검)","2015-10-07 09:30","2015-10-08 17:30","2015-10-07 09:30","2015-10-08 17:30","매일",null,null,null,201508040079,{"$f":"IF(ISERROR(VLOOKUP(D303,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D303,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[300,"경남","통영","신고성삼천포#2 T/L","[154kV 신고성-삼천포 #2T/L] 위탁회사 정밀점검","154kV 신고성-삼천포 #2T/L 정밀점검","2015-10-07 09:30","2015-10-08 17:30","2015-10-07 09:30","2015-10-08 17:30","매일",null,null,null,201508040077,{"$f":"IF(ISERROR(VLOOKUP(D304,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D304,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[301,"경남","통영","삼천포사천#1 T/L","[154kV 삼천포-사천 #1T/L] 위탁회사 정밀점검","안전이격(154kV 신고성-삼천포 #1T/L 정밀점검)","2015-10-05 09:30","2015-10-06 17:30","2015-10-05 09:30","2015-10-06 17:30","매일",null,null,null,201508040078,{"$f":"IF(ISERROR(VLOOKUP(D305,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D305,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[302,"경남","통영","신고성삼천포#1 T/L","[154kV 신고성-삼천포 #1T/L] 위탁회사 정밀점검","154kV 신고성-삼천포 #1T/L 정밀점검","2015-10-05 09:30","2015-10-06 17:30","2015-10-05 09:30","2015-10-06 17:30","매일",null,null,null,201508040076,{"$f":"IF(ISERROR(VLOOKUP(D306,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D306,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[303,"경남","통영","신고성삼천포#1 T/L","154kV 신고성-삼천포#1T/L 보호반 성능개선","154kV 신고성-삼천포#1T/L 보호반 성능개선 - 영인기술 154kV 송전선로보호반(SEL제) 성능개선","2015-10-05 09:30","2015-10-05 18:30","2015-10-05 09:30","2015-10-05 18:30","당일",null,null,null,201508050172,{"$f":"IF(ISERROR(VLOOKUP(D307,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D307,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[304,"경남","통영","거제아주#1 T/L","아주S/S 154kV 거제-아주#1T/L 휴전(정밀점검 시험가압)","아주S/S 154kV 거제-아주#1T/L 휴전(정밀점검 시험가압) - 아주S/S 154kV BUS TIE GIS(6100) 정밀점검 시험가압","2015-10-27 17:30","2015-10-27 18:30","2015-10-27 17:30","2015-10-27 18:30","연속",null,null,null,201508050193,{"$f":"IF(ISERROR(VLOOKUP(D308,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D308,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[305,"경남","통영","거제아주#2 T/L","아주S/S 154kV 거제-아주#2T/L 휴전(정밀점검 시험가압)","아주S/S 154kV 거제-아주#2T/L 휴전(정밀점검 시험가압) - 아주S/S 154kV BUS TIE GIS(6100) 정밀점검 시험가압","2015-10-28 17:30","2015-10-28 18:30","2015-10-28 17:30","2015-10-28 18:30","연속",null,null,null,201508050194,{"$f":"IF(ISERROR(VLOOKUP(D309,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D309,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[306,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 96호 지장이설공사","- 본철탑 설치 및 신고성-통영T/L 이설","2015-10-10 07:00","2015-10-11 19:00","2015-10-10 07:00","2015-10-11 19:00","연속",null,null,null,201508070174,{"$f":"IF(ISERROR(VLOOKUP(D310,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D310,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[307,"경남","통영","고성통영 T/L","154kV 고성-통영T/L 휴전(정밀점검 시험가압관련)","통영S/S 154kV 통영-거제#1T/L GIS #2 DS 시험가압","2015-10-03 17:30","2015-10-03 18:30","2015-10-03 17:30","2015-10-03 18:30","당일",null,null,null,201508050174,{"$f":"IF(ISERROR(VLOOKUP(D311,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D311,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[308,"경남","통영","통영거제#1 T/L","통영S/S 154kV 통영-거제#1T/L GIS(617) 정밀점검","통영S/S 154kV 통영-거제#1T/L GIS(617) 정밀점검","2015-10-03 09:30","2015-10-04 18:30","2015-10-03 09:30","2015-10-04 18:30","연속",null,null,null,201508050166,{"$f":"IF(ISERROR(VLOOKUP(D312,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D312,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[309,"경남","통영","통영거제#2 T/L","통영S/S 154kV 통영-거제#2T/L GIS(627) 정밀점검","통영S/S 154kV 통영-거제#2T/L GIS(627) 정밀점검","2015-10-31 09:30","2015-11-01 18:30","2015-10-31 09:30","2015-11-01 18:30","연속",null,null,null,201508050167,{"$f":"IF(ISERROR(VLOOKUP(D313,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D313,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[310,"경남","통영","고성통영 T/L","154kV 고성-통영T/L 휴전(정밀점검 시험가압관련)","통영S/S 154kV 통영-거제#2T/L GIS #2 DS 시험가압","2015-10-31 17:30","2015-10-31 18:30","2015-10-31 17:30","2015-10-31 18:30","당일",null,null,null,201508050175,{"$f":"IF(ISERROR(VLOOKUP(D314,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D314,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]
[311,"경남","함안","신마산S/S 154kV #60 BUS","신마산S/S 345kV #1M.Tr 변압기 초기점검 공사","신마산S/S 6141DS 및 #60BUS 과열개소 보수","2015-10-06 09:30","2015-10-06 17:30","2015-10-06 09:30","2015-10-06 17:30","당일",null,null,null,201507300055,{"$f":"IF(ISERROR(VLOOKUP(D315,[1]시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D315,[1]시송전설비!$C$2:$O$130,13,0))","v":"-"}]

{"sheet":"한수원","index":3,"n_rows":18,"n_cols":20,"rows_kept":18,"cut":false,"hidden":false,"merged":[[15,17,16,17],[15,18,16,18],[15,19,16,19],[15,11,16,11],[15,12,16,12],[15,13,16,13],[15,14,16,14],[15,15,16,15],[15,16,16,16],[7,19,8,19],[15,0,16,0],[15,1,16,1],[15,2,16,2],[15,3,16,3],[15,4,16,4],[15,5,16,5],[15,6,15,7],[15,8,15,9],[15,10,16,10],[7,13,8,13],[7,14,8,14],[7,15,8,15],[7,16,8,16],[7,17,8,17],[7,18,8,18],[2,18,3,18],[7,5,8,5],[7,6,7,7],[7,8,7,9],[7,10,8,10],[7,11,8,11],[2,19,3,19],[7,0,8,0],[7,1,8,1],[7,2,8,2],[7,3,8,3],[7,4,8,4],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,14,3,14],[7,12,8,12],[2,15,3,15],[2,16,3,16],[2,17,3,17],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7]]}
["2015년 10월 월간휴전계획표(한수원)"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소간","사업소내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","신고리2발","#4 주변압기","4호기 주변압기 및 소내보조변압기 가동전시험 수행                            *조작차단기 : PCB 8300, 8372","○ 4호기 주변압기 및 소내보조변압기 가동전시험 수행","2015-10-26 09:00","2015-11-06 18:00","2015-10-26 09:00","2015-11-06 18:00","연속","N"]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업\n구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소간","사업소내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","신고리2발","#4 대기보조변압기","4호기 대기보조변압기 가동전시험/154kV SWYD - 4호기 MCR 연동시험\n*조작차단기 : PCB 6500, 6572","○ 대기보조변압기(TR02M/N) 보호신호 확인 시험\n○ 154kV SWYD - 4호기 MCR 연동 시험","2015-10-05 09:00","2015-10-23 18:00","2015-10-05 09:00","2015-10-23 18:00","연속","N"]
[2,"월성본부","1발전소","#2 주변압기","월성 2호기  제15차 계획예방정비관련 주변압기/소내용변압기 점검\n* 조작차단기 : CB7300,7372","- 주변압기/소내용변압기 일반점검\n- 주발전기, 주/소내보조변압기 보호계전기 \n   정기시험(차단기 연동시험 포함)","2015-10-01 09:00","2015-10-11 18:00","2015-10-01 09:00","2015-10-11 18:00","연속","N"]
[3,"월성본부","1발전소","#2 기동용변압기","월성 2호기 제15차 계획예방정비관련 기동용변압기 점검\n*조작차단기 : CB7400, CB7472","- 기동용변압기 일반점검\n- 기동용변압기 보호계전기 정기시험\n   (차단기 연동시험 포함)","2015-10-15 09:00","2015-10-22 18:00","2015-10-15 09:00","2015-10-22 18:00","연속","N",null,null," "]
[4,"한울본부","한울3발","#6 주변압기","6호기 8차 계획예방정비 \n* 조작차단기 : PCB 7C00, 7C72","○ 스위치야드 'C Bay' 교체공사\n○ 갑종보호반(GEN/MTR/UAT) 디지털 삼중화\n○ 주변압기 C상 교체 및 소내보조변압기 정밀점검","2015-10-13T16:00:00","2015-11-20T18:00:00","2015-10-13T16:00:00","2015-11-20T18:00:00","연속","Y"]
[]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소간","사업소내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","신고리2발","#4 대기보조변압기","4호기 대기보조변압기 가동전시험/154kV SWYD - 4호기 MCR 연동시험\n*조작차단기 : PCB 6500, 6572","○ 대기보조변압기(TR02M/N) 보호신호 확인 시험\n○ 154kV SWYD - 4호기 MCR 연동 시험","2015-10-05 09:00","2015-10-23 18:00","2015-10-05 09:00","2015-10-23 18:00","연속","N"]

{"sheet":"서부발전","index":4,"n_rows":6,"n_cols":15,"rows_kept":6,"cut":false,"hidden":false,"merged":[[3,14,4,14],[3,6,3,7],[3,8,3,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,5,4,5],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4]]}
["회사명 : 한국서부발전"]
["2015년도 10월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서인천발전본부","-","제8호기 승압변압기","제8호기 간이정비\n* 조작차단기 : 6833","- 제8호기 간이예방정비공사 및 법정검사 수검","2015-10-10 09:00","2015-10-16 16:00","2015-10-10 09:00","2015-10-16 16:00","연속",null,null,null," "]