{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":8,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"345송부","index":0,"n_rows":103,"n_cols":16,"rows_kept":103,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2015년도 12월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","양주중부#1 T/L","15년 중부전력지사 345kV GIS 정밀점검 공사","중부S/S 345kV 7100 GIS 정밀점검","2015-12-21 10:00","2015-12-24 18:00","2015-12-21 10:00","2015-12-24 18:00","연속",null,null,null,201508130188]
[2,"서울","중부","중부S/S 345kV #2 BUS","15년 중부전력지사 345kV GIS 정밀점검 공사","중부S/S 345kV 7200, 7272 GIS 정밀점검 (#2BUS 병행휴전)","2015-12-14 10:00","2015-12-18 18:00","2015-12-14 10:00","2015-12-18 18:00","연속",null,null,null,201508100057]
[3,"서울","중부","양주중부#2 T/L","15년 중부전력지사 345kV GIS 정밀점검 공사","중부S/S 345kV 7200, 7272 GIS 정밀점검","2015-12-09 10:30","2015-12-13 18:00","2015-12-09 10:30","2015-12-13 18:00","연속",null,null,null,201508130189]
[4,"서울","중부","중부S/S #1 M.Tr A","15년 중부전력지사 345kV GIS 정밀점검 공사","중부S/S 345kV 7100 GIS 정밀점검 (#1M.Tr 2차 6164 GIS 정밀점검 병행)","2015-12-21 10:00","2015-12-24 18:00","2015-12-21 10:00","2015-12-24 18:00","연속",null,null,null,201506300031]
[5,"서울","중부","중부S/S #2 M.Tr A","15년 중부전력지사 345kV GIS 정밀점검 공사","중부S/S 345kV 7200, 7272 GIS 정밀점검 (#2M.Tr 2차 6264 GIS 정밀점검 병행) (#2BUS 병행휴전)","2015-12-09 10:30","2015-12-18 18:00","2015-12-09 10:30","2015-12-18 18:00","연속",null,null,null,201507080050]
[6,"남서울","강남","신양재S/S 345kV #3 Sh.R","변전총액공사 (신양재S/S #3 Sh.R)","변전총액공사 (신양재S/S #3 Sh.R)","2015-12-02 10:00","2015-12-02 18:00","2015-12-02 10:00","2015-12-02 18:00","당일",null,null,null,201510150057]
[7,"남서울","강남","신양재S/S 345kV #4 Sh.R","변전총액공사 (신양재S/S #4 Sh.R)","변전총액공사 (신양재S/S #4 Sh.R)","2015-12-03 10:00","2015-12-03 18:00","2015-12-03 10:00","2015-12-03 18:00","당일",null,null,null,201510150058]
[8,"남서울","동서울","동서울신용인#1 T/L","동서울-신용인#2T/L 피뢰기 점검","동서울-신용인#2T/L 피뢰기 점검","2015-12-02 09:00","2015-12-02 14:00","2015-12-02 09:00","2015-12-02 14:00","당일",null,null,null,201510160076]
[9,"남서울","동서울","동서울신용인#2 T/L","동서울-신용인#2T/L 피뢰기 점검","동서울-신용인#2T/L 피뢰기 점검","2015-12-02 14:00","2015-12-02 18:00","2015-12-02 14:00","2015-12-02 18:00","당일",null,null,null,201510160075]
[10,"인천","인천","신김포서인천CC T/L","345kV 신김포-서인천CCT/L 중간접속함 교체공사","중간접속함 54Set 전량 교체(스트레스콘 재질변경)","2015-12-09 09:00","2016-01-07 18:00","2015-12-09 09:00","2016-01-07 18:00","연속",null,null,null,201510130139]
[11,"인천","인천","신경서S/S 신경서포스코SY#1T/L-TIE CB (7300)","345kV 신경서 SW증설 및 CLR 설치공사","73Bay 1CB(7372) 및 CLR용 GIB 설치","2015-12-01 10:00","2015-12-31 18:00","2015-12-01 10:00","2015-12-31 18:00","연속",null,null,null,201510130076]
[12,"인천","인천","신인천C/C 345kV #71 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #71BUS 모선개조 - SEC-CB(70-71-0) 대체 - 모선용 DS 대체","2015-12-01 09:00","2015-12-24 18:00","2015-12-01 09:00","2015-12-24 18:00","연속",null,null,null,201510080128]
[13,"인천","인천","신경서인천CC T/L","345kV 인천CC 용량부족GIS 대체공사","CB 2대 교체 및 1대 철거","2015-12-09 10:00","2016-01-12 17:00","2015-12-09 10:00","2016-01-12 17:00","연속",null,null,null,201509240069]
[14,"경기북부","구리","신포천S/S 345kV #1 Sh.R","신포천S/S 345kV #1 Sh.R 유사고장 방지조치","345kV Sh.R 방압변 마이크로스위치 교체","2015-12-18 09:00","2015-12-18 18:00","2015-12-18 09:00","2015-12-18 18:00","당일",null,null,null,201510140144]
[15,"경기북부","직할","양주S/S SVC M.Tr","양주S/S SVC M.Tr","2015년 경기북부직할 변전협력회사 총액공사 - 변압기 본체 및 PT,LA 보통","2015-12-03 10:00","2015-12-04 18:00","2015-12-03 10:00","2015-12-04 18:00","연속",null,null,null,201510150002]
[16,"경기북부","파주","신파주S/S #1SVC Tr A","신파주S/S SVC 리액터감시용 열화상 카메라 설치","리액터감시용 열화상 카메라(3개) 설치","2015-12-01 09:00","2015-12-02 18:00","2015-12-01 09:00","2015-12-02 18:00","연속",null,null,null,201510120387]
[17,"경기","군포","화성서서울#1 T/L","345kV 화성서서울T/L 지장철탑이설공사 48호","345kV 화성서서울T/L 지장철탑이설공사 48호 #1T/L 가철탑이설(41~50호)","2015-12-01 07:00","2015-12-04 18:00","2015-12-01 07:00","2015-12-04 18:00","연속",null,null,null,201510080300]
[18,"경기","군포","화성서서울#2 T/L","345kV 화성서서울T/L 지장철탑이설공사 48호","345kV 화성서서울T/L 지장철탑이설공사 48호 본철탑 기초작업 #2T/L 안전이격 확보 (41~50호)","2015-12-05 07:00","2015-12-14 18:00","2015-12-05 07:00","2015-12-14 18:00","연속",null,null,null,201510080301]
[19,"경기","성남","신시흥신성남#2 T/L","345kV 신시흥신성남#2T/L 송전선로 초기점검(44호)","15년 가공송전선로 순시점검 위탁공사 345kV 신시흥신성남#2T/L 송전선로 초기점검(44호)","2015-12-06 08:00","2015-12-06 12:00","2015-12-06 08:00","2015-12-06 12:00","당일",null,null,null,201510070106]
[20,"경기","성남","신안성신용인#1 T/L","신용인S/S 신안성-신용인#1T/L","신용인S/S 345kV신안성-신용인#1T/L 집감반 감시 및 제어 수용","2015-12-01 09:00","2015-12-01 18:00","2015-12-01 09:00","2015-12-01 18:00","당일",null,null,null,201510140189]
[21,"경기","성남","신용인S/S #2 M.Tr A","신용인S/S #2 M.Tr","신용인S/S 345kV #2 M.Tr 집감반 감시 및 제어 수용","2015-12-05 09:00","2015-12-05 18:00","2015-12-05 09:00","2015-12-05 18:00","당일",null,null,null,201510060029]
[22,"경기","직할","아산화성#1T/L","345kV 아산화성T/L지장철탑이설공사","미군부대조성 도로개설 지장철탑이설(NO.65~67) 이설개요 : 철탑신설 10기, 철탑철거 18기","2015-12-01 07:00","2015-12-06 18:00","2015-12-02 07:00","2015-12-07 18:00","연속",null,null,null,"추가예정"]
[23,"경기","직할","아산화성#2T/L","345kV 아산화성T/L지장철탑이설공사","미군부대조성 도로개설 지장철탑이설(NO.65~67) 이설개요 : 철탑신설 10기, 철탑철거 18기","2015-12-07 07:00","2015-12-11 18:00","2015-12-08 07:00","2015-12-12 18:00","연속",null,null,null,"추가예정"]
[24,"강원","태백","신태백S/S #4 M.Tr 2차 CB (7771)","전자변 러버히터 설치[7771]","전자변 러버히터 설치[7771]","2015-12-01 09:00","2015-12-01 13:00","2015-12-01 09:00","2015-12-01 13:00","당일",null,null,null,201510120281]
[25,"강원","태백","신태백S/S 345kV #2 Sh.R","전자변 러버히터 설치[7479]","전자변 러버히터 설치[7479]","2015-12-06 13:00","2015-12-06 18:00","2015-12-06 13:00","2015-12-06 18:00","당일",null,null,null,201510120297]
[26,"강원","태백","신태백S/S 345kV #3 Sh.R","전자변 러버히터 설치[7579]","전자변 러버히터 설치[7579]","2015-12-06 09:00","2015-12-06 13:00","2015-12-06 09:00","2015-12-06 13:00","당일",null,null,null,201510120310]
[27,"강원","태백","신태백S/S #4 M.Tr 2차-TIE CB (7700)","전자변 러버히터 설치[7700]","전자변 러버히터 설치[7700]","2015-12-01 13:00","2015-12-01 18:00","2015-12-01 13:00","2015-12-01 18:00","당일",null,null,null,201510120282]
[28,"강원","태백","신태백S/S #3 M.Tr 2차 CB (7671)","전자변 러버히터 설치[7671]","전자변 러버히터 설치[7671]","2015-12-02 09:00","2015-12-02 13:00","2015-12-02 09:00","2015-12-02 13:00","당일",null,null,null,201510120285]
[29,"강원","태백","신태백#3 M.Tr 2차-신태백-한울NP2#2T/L CB (7600)","전자변 러버히터 설치[7600]","전자변 러버히터 설치[7600]","2015-12-02 13:00","2015-12-02 18:00","2015-12-02 13:00","2015-12-02 18:00","당일",null,null,null,201510120288]
[30,"강원","태백","신태백S/S 신태백-한울NP2#2T/L CB (7672)","전자변 러버히터 설치[7672]","전자변 러버히터 설치[7672]","2015-12-03 09:00","2015-12-03 13:00","2015-12-03 09:00","2015-12-03 13:00","당일",null,null,null,201510120289]
[31,"강원","태백","신태백S/S 345kV #3 Sh.R CB (7571)","전자변 러버히터 설치[7571]","전자변 러버히터 설치[7571]","2015-12-03 13:00","2015-12-03 18:00","2015-12-03 13:00","2015-12-03 18:00","당일",null,null,null,201510120290]
[32,"강원","태백","신태백S/S#3 Sh.R-신태백-한울NP2#1T/L CB (7500)","전자변 러버히터 설치[7500]","전자변 러버히터 설치[7500]","2015-12-04 09:00","2015-12-04 13:00","2015-12-04 09:00","2015-12-04 13:00","당일",null,null,null,201510120293]
[33,"강원","태백","신태백S/S 신태백-한울NP2#1T/L CB (7572)","전자변 러버히터 설치[7572]","전자변 러버히터 설치[7572]","2015-12-04 13:00","2015-12-04 18:00","2015-12-04 13:00","2015-12-04 18:00","당일",null,null,null,201510120295]
[34,"강원","태백","신태백S/S #2 M.Tr 2차 CB (7371)","전자변 러버히터 설치[7471]","전자변 러버히터 설치[7471]","2015-12-05 09:00","2015-12-05 13:00","2015-12-05 09:00","2015-12-05 13:00","당일",null,null,null,201510120309]
[35,"강원","태백","신태백S/S #2 M.Tr 2차 CB (7371)","전자변 러버히터 설치[7371]","전자변 러버히터 설치[7371]","2015-12-05 13:00","2015-12-05 18:00","2015-12-05 13:00","2015-12-05 18:00","당일",null,null,null,201510120298]
[36,"충북","직할","신제천신충주#1 T/L","2014-15년 직할 송전정비 협력회사 총액공사(조류퇴치기 설치)","조류착지방지장치 설치 57기","2015-12-01 08:00","2015-12-03 18:00","2015-12-01 08:00","2015-12-03 18:00","당일",null,null,null,201510080282]
[37,"충북","직할","신제천신충주#2 T/L","2014-15년 직할 송전정비 협력회사 총액공사(조류퇴치기 설치)","조류착지방지장치 설치 57기","2015-12-04 08:00","2015-12-06 18:00","2015-12-04 08:00","2015-12-06 18:00","당일",null,null,null,201510080278]
[38,"충북","충주","신진천S/S #1 M.Tr A","주변압기 정밀점검 공사","주변압기 정밀점검 공사","2015-12-01 08:30","2015-12-15 18:00","2015-12-01 08:30","2015-12-15 18:00","연속",null,null,null,201509080142]
[39,"충북","충주","신진천S/S #4 M.Tr A","주변압기 초기점검","주변압기 초기점검","2015-12-16 10:00","2015-12-18 18:00","2015-12-16 10:00","2015-12-18 18:00","연속",null,null,null,201510190114]
[40,"대전충남","서산","북당진S/S 345kV #1 BUS","당진복합4호기용 345kV SW 증설공사","345kV 63kA 6300A * 4CB 증설 345kV 63kA 8000A Main Bus 증설 * 1식","2015-12-21 09:30","2015-12-25 17:30","2015-12-21 09:30","2015-12-25 17:30","연속",null,null,null,201510070030]
[41,"대전충남","서산","북당진S/S 345kV #2 BUS","당진복합4호기용 345kV SW 증설공사","345kV 63kA 6300A * 4CB 증설 345kV 63kA 8000A Main Bus 증설 * 1식","2015-12-26 09:30","2015-12-30 17:30","2015-12-26 09:30","2015-12-30 17:30","연속",null,null,null,201510070032]
[42,"대전충남","서산","북당진S/S GSEPS #3호기 -TIE CB (7200)","14~15년 변전협력회사 총액공사","○ 북당진S/S 345kV #3M.Tr 1차 - TIE GIS 하자점검","2015-12-02 09:00","2015-12-02 18:00","2015-12-02 09:00","2015-12-02 18:00","당일",null,null,null,201510080136]
[43,"대전충남","서산","신당진S/S #2M.Tr 1차 CB (7672)","신당진S/S 345kV GCB Control Block 2차 성능개선공사","1.차단기 개방시 TRIP VALVE COVER 고무패킹 이탈 AIR 누기 현상 보수 - CONTROL BLOCK 내 기계적인 TRIP VALVE 구조개선(7672)","2015-12-14 09:30","2015-12-15 18:00","2015-12-14 09:30","2015-12-15 18:00","연속",null,null,null,201510060107]
[44,"대전충남","서산","신당진S/S #3M.Tr - TIE CB (7800)","신당진S/S 345kV GCB Control Block 2차 성능개선공사","1.차단기 개방시 TRIP VALVE COVER 고무패킹 이탈 AIR 누기 현상 보수 - CONTROL BLOCK 내 기계적인 TRIP VALVE 구조개선(7800)","2015-12-11 09:30","2015-12-12 18:00","2015-12-11 09:30","2015-12-12 18:00","연속",null,null,null,201510060109]
[45,"대전충남","서산","신당진S/S 신서산-신당진#2T/L CB (7772)","신당진S/S 345kV GCB Control Block 2차 성능개선공사","1.차단기 개방시 TRIP VALVE COVER 고무패킹 이탈 AIR 누기 현상 보수 - CONTROL BLOCK 내 기계적인 TRIP VALVE 구조개선(7772)","2015-12-23 09:30","2015-12-24 18:00","2015-12-23 09:30","2015-12-24 18:00","연속",null,null,null,201510060108]
[46,"대전충남","서산","신당진S/S 신서산-신당진#1T/L CB (7172)","신당진S/S 345kV GCB Control Block 2차 성능개선공사","1.차단기 개방시 TRIP VALVE COVER 고무패킹 이탈 AIR 누기 현상 보수 - CONTROL BLOCK 내 기계적인 TRIP VALVE 구조개선(7172)","2015-12-21 09:30","2015-12-22 18:00","2015-12-21 09:30","2015-12-22 18:00","연속",null,null,null,201510060105]
[47,"대전충남","서산","신당진북당진 T/L","345kV 신당진-북당진 외 1개T/L 용량증대 전력선 교체공사","- 선종교체 : ACSR 480SQ -> HTACSR/AW 480SQ - 공사구간 : 1~35호(잔여구간) 11.239km","2015-12-11 07:00","2015-12-20 18:00","2015-12-11 07:00","2015-12-20 18:00","연속",null,null,null,201510140002]
[48,"대전충남","서산","신당진태안화력#1 T/L","345kV 신당진태안화력T/L 선종교체공사","345kV 신당진태안화력T/L 선종교체공사","2015-12-04 07:00","2015-12-08 19:00","2015-12-04 07:00","2015-12-08 19:00","연속",null,null,null,201510070201]
[49,"대전충남","서산","신당진S/S #2M.Tr - TIE CB (7600)","신당진S/S 345kV GCB Control Block 2차 성능개선공사","1.차단기 개방시 TRIP VALVE COVER 고무패킹 이탈 AIR 누기 현상 보수 - CONTROL BLOCK 내 기계적인 TRIP VALVE 구조개선(7600)","2015-12-16 09:30","2015-12-17 18:00","2015-12-16 09:30","2015-12-17 18:00","연속",null,null,null,201510060106]
[50,"대전충남","서산","신당진현대제철 T/L","345kV 신당진-북당진 외 1개T/L 용량증대 전력선 교체공사","- 선종교체 : ACSR 480SQ -> HTACSR/AW 480SQ - 공사구간 : 1~35호(잔여구간) 11.239km","2015-12-01 07:00","2015-12-10 18:00","2015-12-01 07:00","2015-12-10 18:00","연속",null,null,null,201510140001]
[51,"대전충남","서산","태안T/P TIE-4호기 1차 CB (7400)","15년 서산P/O 장기사용 배전반 대체","태안T/P 74BAY 차단실패 보호반 대체","2015-12-07 09:00","2015-12-11 18:00","2015-12-07 09:00","2015-12-11 18:00","연속",null,null,null,201510120334]
[52,"대전충남","서산","태안T/P 4호기 1차 CB (7472)","15년 서산P/O 장기사용 배전반 대체","태안T/P 74BAY 차단실패 보호반 대체","2015-12-07 09:00","2015-12-11 18:00","2015-12-07 09:00","2015-12-11 18:00","연속",null,null,null,201510120332]
[53,"전북","김제","신김제S/S #4 M.Tr A","신김제S/S #4 M.Tr A","예비M.Tr 절체반 설치","2015-12-09 09:00","2015-12-10 18:00","취소","취소","연속",null,null,null,201510190091]
[54,"전북","김제","신김제한빛NP#2 T/L","345kV 신김제-한빛NP#2 T/L","차단기 정밀점검","2015-12-07 09:00","2015-12-11 18:00","취소","취소","연속",null,null,null,201510060158]
[55,"전북","김제","신김제S/S #2 M.Tr A","신김제S/S #2 M.Tr A","예비M.Tr 절체반 설치","2015-12-04 09:00","2015-12-05 18:00","취소","취소","연속",null,null,null,201510190089]
[56,"전북","김제","신김제S/S #1 M.Tr A","신김제S/S #1 M.Tr A","예비M.Tr 절체반 설치","2015-12-01 09:00","2015-12-03 18:00","취소","취소","연속",null,null,null,201510190088]
[57,"전북","김제","신김제S/S #3 M.Tr A","신김제S/S #3 M.Tr A","예비M.Tr 절체반 설치","2015-12-07 09:00","2015-12-08 18:00","취소","취소","연속",null,null,null,201510190090]
[58,"전북","직할","신남원신광주#1 T/L","345kV 신남원신광주#1T/L 스페이서 정비공사","345kV 신남원신광주#1T/L 스페이서 정비공사 - 스페이셔 불량개소 정비 : No.108호 등 2개소","2015-12-07 09:00","2015-12-07 18:00","2015-12-17 09:00","2015-12-17 18:00","당일",null,null,null,201510210060,"○"]
[59,"광주전남","강진","신강진S/S 345kV #1 BUS","신강진S/S 362kV 장기사용 개폐장치 대체공사","GCB → GIS화","2015-12-01 07:00","2015-12-01 18:00","2015-12-05 07:00","2015-12-05 18:00","당일",null,null,null,201510150083]
[60,"광주전남","강진","신강진S/S 345kV #2 BUS","신강진S/S 362kV 장기사용 개폐장치 대체공사","GCB → GIS화","2015-12-02 07:00","2015-12-02 18:00","2015-12-06 07:00","2015-12-06 18:00","당일",null,null,null,201510150084]
[61,"광주전남","순천","신남원광양#2 T/L","345kV 신남원-광양#2T/L(순천변전협력회사 총액공사)","15년 순천전력지사 변전협력회사 총액공사 - 신남원-광양#2T/L LA,CVT 교체","2015-12-01 09:00","2015-12-01 18:00","취소","취소","당일",null,null,null,201510160009]
[62,"광주전남","순천","광양S/S #1 M.Tr A","345kV 광양S/S #1M.Tr A(순천변전협력회사 총액공사)","15년 순천변전협력회사 총액공사 - M.Tr 보통점검, 3차 GPT 보통점검","2015-12-03 09:00","2015-12-03 18:00","2015-12-03 09:00","2015-12-03 18:00","당일",null,null,null,201510130195]
[63,"광주전남","순천","여수T/P #2 Tie-Tr ","345kV 여수T/P #2M.Tr A(순천변전협력회사 총액공사)","15년 순천변전협력회사 총액공사 - 1차 LA 하자점검","2015-12-02 09:00","2015-12-02 18:00","2015-12-02 09:00","2015-12-02 18:00","당일",null,null,null,201510130206]
[64,"광주전남","직할","신남원한빛NP#2 T/L","신남원한빛NP#2 T/L(인출변경 접속설비 보강공사)","345kV 한빛본부 2,3발전소 인출변경 접속설비 보강공사 1.구간 : 한빛원자력 구내(신남원, 신김제-한빛 NO.1~4호) 2.지지물 : 사각철탑 1기 설치, 3기 철거","2015-12-10 09:00","2015-12-15 18:00","2015-12-05 09:00","2015-12-16 18:00","연속",null,null,null,201510200109]
[65,"광주전남","직할","한빛3N/P 345kV #1BUS","한빛#3S/Y 345kV #1BUS","14-15년 변전협력회사 총액공사 345KV #1BUS PRO PNL 대체","2015-12-07 09:00","2015-12-11 18:00","2015-12-17 09:00","2015-12-21 18:00","연속",null,null,null,201510070086]
[66,"광주전남","직할","신김제한빛NP#1 T/L","신김제한빛NP#1 T/L(인출변경 접속설비 보강공사)","345kV 한빛본부 2,3발전소 인출변경 접속설비 보강공사 1.구간 : 한빛원자력 구내(신남원, 신김제-한빛 NO.1~4호) 2.지지물 : 사각철탑 1기 설치, 3기 철거","2015-12-10 09:00","2015-12-15 18:00","2015-12-05 09:00","2015-12-16 18:00","연속",null,null,null,201510200075]
[67,"광주전남","직할","신김제한빛NP#2 T/L","신김제한빛NP#2 T/L(인출변경 접속설비 보강공사)","345kV 한빛본부 2,3발전소 인출변경 접속설비 보강공사 1.구간 : 한빛원자력 구내(신남원, 신김제-한빛 NO.1~4호) 2.지지물 : 사각철탑 1기 설치, 3기 철거","2015-12-04 09:00","2015-12-09 18:00","2015-11-30 09:00","2015-12-04 18:00","연속",null,null,null,201510200074]
[68,"대구경북","구미","서대구선산#1 T/L","345kV 서대구-선산T/L 송전선로용 피뢰기 설치공사","1. 피뢰기설치 : 79기, 336조 - 2회선 구간 : No.19, 23, 29, 32, 33~73, 107호(46기, 138조) - 4회선 구간 : No. 74~106호(33기, 198조) 2. 아킹혼 철거 : 79기(철거개소 피뢰기설치개소와 동일)","2015-12-01 08:00","2015-12-15 18:00","취소","취소","매일",null,null,null,201510120121]
[69,"대구경북","달성","고령S/S #2 M.Tr A","고령 #2MTR, 6244 정밀점검","고령 #2, 6244정밀","2015-12-04 09:00","2015-12-06 18:00","2015-12-04 09:00","2015-12-06 18:00","연속",null,null,null,201510210076]
[70,"대구경북","포항","신영일S/S #3 M.Tr A","신영일S/S #3M.Tr 휴전작업","소내변압기 지락보호장치 설치","2015-12-08 09:00","2015-12-08 17:00","2015-12-08 09:00","2015-12-08 17:00","당일",null,null,null,201510070195]
[71,"대구경북","포항","신영일S/S #4 M.Tr A","신영일S/S #4M.Tr 휴전작업","소내변압기 지락보호장치 설치","2015-12-09 09:00","2015-12-09 17:00","2015-12-09 09:00","2015-12-09 17:00","당일",null,null,null,201510070197]
[72,"대구경북","포항","신포항S/S #2 M.Tr A","신포항S/S #2M.Tr 휴전작업","소내변압기 지락보호장치 설치","2015-12-05 09:00","2015-12-05 17:00","2015-12-05 09:00","2015-12-05 17:00","당일",null,null,null,201510070200]
[73,"대구경북","포항","신포항신월성NP#3 T/L","345kV 신포항-신월성NP#1 등 5개 T/L 피뢰기 설치공사","피뢰기 설치 : No.1~89","2015-12-07 08:00","2015-12-20 18:00","2015-12-07 08:00","2015-12-20 18:00","연속",null,null,null,201510060074]
[74,"대구경북","포항","신포항S/S 345kV #2 BUS","신포항S/S 345kV #2BUS 휴전작업","CVT 교체","2015-12-21 09:00","2015-12-22 18:00","2015-12-21 09:00","2015-12-22 18:00","연속",null,null,null,201510070192]
[75,"대구경북","포항","신포항S/S #1 M.Tr A","신포항S/S #1M.Tr 휴전작업","소내변압기 지락보호장치 설치","2015-12-04 09:00","2015-12-04 17:00","2015-12-04 09:00","2015-12-04 17:00","당일",null,null,null,201510070199]
[76,"대구경북","포항","신포항S/S #3 M.Tr A","신포항S/S 345kV #3M.Tr 휴전작업","절연유 누유개소 보수","2015-12-03 09:00","2015-12-03 18:00","2015-12-03 09:00","2015-12-03 18:00","당일",null,null,null,201510070193]
[77,"대구경북","포항","동울산월성NP#1 T/L","345kV 신포항-신월성NP#1 등 5개 T/L 피뢰기 설치공사","피뢰기 설치 : No.1~80","2015-12-14 08:00","2015-12-24 18:00","2015-12-14 08:00","2015-12-24 18:00","연속",null,null,null,201510080172]
[78,"부산울산","동부산","고리N/P S/Y 신고리 #3, 4 SAT CB (7D71)","고리NP S/Y 362kV GIS 유압설비보수","고리NP S/Y 362kV 7D71 GIS 유압설비보수(신고리SAT#3,4)","2015-12-01 09:30","2015-12-01 13:00","2015-12-01 09:30","2015-12-01 13:00","당일",null,null,null,201510080255]
[79,"부산울산","동부산","신고리고리NP#3 T/L","신고리S/S 81Bay 분리공사","시험가압 선로","2015-12-21 09:00","2015-12-22 18:00","2015-12-21 09:00","2015-12-22 18:00","연속",null,null,null,201510070053]
[80,"부산울산","동부산","신양산신대연#2 T/L","345kV 신양산-신대연#2 T/L 불량개소 보수","345kV 신양산-신대연#2 T/L 불량개소 보수 -불량개소: 16호, 24호, C/H(3기)","2015-12-07 09:00","2015-12-07 18:00","2015-12-07 09:00","2015-12-07 18:00","당일",null,null,null,201510140203]
[81,"부산울산","동부산","신양산S/S #1 M.Tr A","신양산S/S 23kV #1-1,1-2 Sh.R 대체공사","신양산S/S 23kV #1-1,1-2 Sh.R 대체관련 시험가압(345kV #1M.Tr 사용)","2015-12-10 18:00","2015-12-12 18:00","2015-12-10 18:00","2015-12-12 18:00","연속",null,null,null,201510080258]
[82,"부산울산","서부산","서부산북부산#3 T/L","345kV 서부산-북부산T/L 등 8개T/L 이설공사","345kV OF 2000㎟ 케이블 0.177km 이설","2015-12-11 08:00","2016-01-15 18:00","2015-12-19 08:00","2016-01-25 18:00","연속",null,null,null,201510090001]
[83,"부산울산","울산","동울산신울산#2 T/L","345kV 신포항-신월성NP#1 등 5개 T/L 피뢰기 설치공사","345kV 동울산-월성 47~79 피뢰기 설치공사 구간 안전이격차원","2015-12-14 08:00","2015-12-18 18:00","2015-12-14 08:00","2015-12-18 18:00","연속",null,null,null,201510080186]
[84,"부산울산","울산","동울산S/S #2 M.Tr A","2014-15년 울산전력지사 변전협력 총액공사","권선온도계 불량으로 인한 교체(제작사 작업)","2015-12-08 09:00","2015-12-08 18:00","2015-12-08 09:00","2015-12-08 18:00","당일",null,null,null,201510140271]
[85,"부산울산","울산","동울산S/S #1 M.Tr A","2014-15년 울산전력지사 변전협력 총액공사","방호벽 도장","2015-12-07 09:00","2015-12-07 18:00","2015-12-07 09:00","2015-12-07 18:00","당일",null,null,null,201510140270]
[86,"부산울산","울산","신울산신온산#2 T/L","신온산S/S #4M.Tr 증설공사","7600CB, 7672CB, 7602DS, 7662DS, 7652DS, 7622DS, #4M.Tr, 6446DS, 6444CB, 6442DS, 6302DS, 6300CB 무부하 가압","2015-12-18 18:00","2015-12-20 18:00","2015-12-18 18:00","2015-12-20 18:00","연속",null,null,null,201510080254]
[87,"부산울산","울산","신온산S/S 울산TP#2T/L-#2 M.Tr 1차 CB (7400)","2015년 362kV GIS 정밀점검공사","7400 GIS 정밀점검","2015-12-03 08:00","2015-12-05 18:00","2015-12-01 08:00","2015-12-03 18:00","연속",null,null,null,201510120100]
[88,"부산울산","울산","신온산울산TP T/L","362kV GIS 정밀점검공사","7400 GIS 시험가압(1H)","2015-12-05 17:00","2015-12-05 18:00","2015-12-03 17:00","2015-12-03 18:00","당일",null,null,null,201510140272]
[89,"부산울산","울산","신온산S/S 345kV #2 BUS","신온산S/S #4M.Tr 증설공사","7600CB, 7672CB, 7602DS, 7662DS, 7652DS, 7622DS, #4M.Tr, 6446DS, 6444CB, 6442DS, 6302DS, 6300CB 무부하 가압","2015-12-18 18:00","2015-12-20 18:00","2015-12-18 18:00","2015-12-20 18:00","연속",null,null,null,201510080256]
[90,"부산울산","동부산","신양산고리NP#2 T/L","345kV 고리N/P 통합S/Y 토건공사 ","원자력기술위원회의 사면 추가보강 요청으로 인한 활선근접작업","2015-12-03 09:00","2015-12-05 18:00","2015-12-03 09:00","2015-12-05 18:00","연속",null,null,null,201510120041]
[91,"부산울산","동부산","울주고리NP#1 T/L","345kV 고리N/P 통합S/Y 토건공사 ","원자력기술위원회의 사면 추가보강 요청으로 인한 활선근접작업","2015-12-06 09:00","2015-12-16 18:00","2015-12-06 09:00","2015-12-16 18:00","연속",null,null,null,201510120049]
[92,"경남","진주","의령S/S #1 M.Tr A","345kV #1M.Tr 보통점검","345kV #1M.Tr 보통점검","2015-12-02 09:30","2015-12-03 18:30","2015-12-02 09:30","2015-12-03 18:30","연속",null,null,null,201510200145]
[93,"경남","함안","북경남S/S #7 Sh.R CB (7B71)","북경남S/S 345kV 7B71 GIS 초기점검 공사","북경남S/S 345kV 7B71 GIS 초기점검 공사","2015-12-07 09:30","2015-12-07 17:30","2015-12-07 09:30","2015-12-07 17:30","당일",null,null,null,201510110030]
[94,"경남","함안","북경남S/S #5 Sh.R - 북경남-고령 #2T/L CB (7700)","북경남S/S 345kV 7700 GIS 초기점검 공사","북경남S/S 345kV 7700 GIS 초기점검 공사","2015-12-04 09:30","2015-12-04 17:30","2015-12-04 09:30","2015-12-04 17:30","당일",null,null,null,201510110029]
[95,"경남","함안","북경남S/S #5 Sh.R CB (7779) (7779)","북경남S/S 345kV 7779 GIS 초기점검 공사","북경남S/S 345kV 7779 GIS 초기점검 공사","2015-12-03 09:30","2015-12-03 17:30","2015-12-03 09:30","2015-12-03 17:30","당일",null,null,null,201510110028]
[96,"경남","함안","북경남S/S #5 Sh.R CB (7771)","북경남S/S 345kV 7771 GIS 초기점검 공사","북경남S/S 345kV 7771 GIS 초기점검 공사","2015-12-02 09:30","2015-12-02 17:30","2015-12-02 09:30","2015-12-02 17:30","당일",null,null,null,201510110027]
[97,"경남","함안","북경남S/S #5M.Tr 2차 CB (7C71)","북경남S/S 345kV 7C71 GIS 초기점검 공사","북경남S/S 345kV 7C71 GIS 초기점검 공사","2015-12-01 09:30","2015-12-01 17:30","2015-12-01 09:30","2015-12-01 17:30","당일",null,null,null,201510110023]
[98,"경남","함안","신마산S/S #2 M.Tr A","신마산S/S #2M.Tr 과열개소 보수","신마산S/S #2M.Tr 3차측 A상 Y2, C상 Y1 과열개소 보수","2015-12-06 13:30","2015-12-06 17:30","2015-12-06 13:30","2015-12-06 17:30","당일",null,null,null,201510110033]
[99,"경남","함안","신마산S/S #3 M.Tr A","신마산S/S #3M.Tr 과열개소 보수","신마산S/S #3M.Tr 3차측 EXP금구, 4375 고정자터미널 과열개소 보수","2015-12-06 09:30","2015-12-06 13:30","2015-12-06 09:30","2015-12-06 13:30","당일",null,null,null,201510110032]

{"sheet":"154송부","index":1,"n_rows":140,"n_cols":16,"rows_kept":140,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2015년도 12월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","원남미아#2 T/L","2015년 성동P/O 노후배전반대체공사(미아S/S 원남미아2T/L)","2015년 성동P/O 노후배전반대체공사(미아S/S 원남미아2T/L)","2015-12-22 09:00","2015-12-24 18:00","2015-12-25 09:00","2015-12-27 18:00","연속",null,null,null,201510140187]
[2,"서울","성동","방학창동#2 T/L","2015년 성동P/O 변전협력회사 총액공사(방학S/S방학창동#2T/L)","170kV GIS 하자점검 (방학S/S 154kV 방학창동#2T/L)","2015-12-18 10:00","2015-12-18 18:00","2015-12-18 10:00","2015-12-18 18:00","당일",null,null,null,201510130082]
[3,"서울","성동","방학창동#1 T/L","2015년 성동P/O 변전협력회사 총액공사(방학S/S방학창동#1T/L)","170kV GIS 하자점검 (방학S/S 154kV 방학창동#1T/L)","2015-12-17 10:00","2015-12-17 18:00","2015-12-17 10:00","2015-12-17 18:00","당일",null,null,null,201510130080,"○"]
[4,"서울","성동","도봉방학#1 T/L","2015년 성동P/O 변전협력회사 총액공사(방학S/S도봉방학#1T/L)","170kV GIS 하자점검 (방학S/S 154kV 도봉방학#1T/L)","2015-12-08 10:00","2015-12-08 18:00","2015-12-08 10:00","2015-12-08 18:00","당일",null,null,null,201510130086,"○"]
[5,"서울","성동","도봉방학#2 T/L","2015년 성동P/O 변전협력회사 총액공사(방학S/S도봉방학#2T/L)","170kV GIS 하자점검 (방학S/S 154kV 도봉방학#2T/L)","2015-12-09 10:00","2015-12-09 18:00","2015-12-09 10:00","2015-12-09 18:00","당일",null,null,null,201510130087]
[6,"서울","성동","상봉휘경#2 T/L","15년 변전협력회사 총액공사 (상봉S/S 상봉휘경#2T/L)","170kV GIS 보통점검 (상봉S/S 154kV 상봉휘경#2T/L)","2015-12-15 09:00","2015-12-15 18:00","2015-12-15 09:00","2015-12-15 18:00","당일",null,null,null,201510160113]
[7,"서울","성동","구리신내#2 T/L","154kV 보호배전반 정기점검","154kV 보호배전반 정기점검 -구리신내#2T/L 보호배전반 정기점검","2015-12-16 10:30","2015-12-16 17:30","취소","취소","당일",null,null,null,201510150064]
[8,"서울","중부","수색상암#1 T/L","15년 중부전력지사 장기사용 배전반 대체공사","상암(657), 수색(667) 수색상암#1 T/L 배전반 대체공사","2015-12-08 10:00","2015-12-10 18:00","2015-12-08 10:00","2015-12-10 18:00","연속",null,null,null,201510140141]
[9,"서울","중부","수색상암#2 T/L","15년 중부전력지사 장기사용 배전반 대체공사","상암(667), 수색(677) 수색상암#2 T/L 배전반 대체공사","2015-12-28 10:00","2015-12-30 18:00","2015-12-28 10:00","2015-12-30 18:00","연속",null,null,null,201510140140]
[10,"서울","중부","중부S/S 154kV #60 BUS","15년 중부P/O 170kV GIS 정밀점검 공사","중부S/S #1M.Tr 2차(6164) GIS 정밀점검","2015-12-21 08:00","2015-12-22 14:00","2015-12-21 08:00","2015-12-22 14:00","연속",null,null,null,201508130084]
[11,"서울","중부","중부S/S 154kV #66 BUS","15년 중부P/O 170kV GIS 정밀점검 공사","중부S/S #2M.Tr 2차(6264) GIS 정밀점검","2015-12-10 14:00","2015-12-11 18:00","2015-12-10 14:00","2015-12-11 18:00","연속",null,null,null,201508130186]
[12,"서울","중부","중부S/S 154kV #65 BUS","15년 중부P/O 170kV GIS 정밀점검 공사","중부S/S #1M.Tr 2차(6164) GIS 정밀점검","2015-12-22 14:00","2015-12-23 18:00","2015-12-22 14:00","2015-12-23 18:00","연속",null,null,null,201508130093]
[13,"서울","중부","중부S/S 154kV #61 BUS","15년 중부P/O 170kV GIS 정밀점검 공사","중부S/S #2M.Tr 2차(6264) GIS 정밀점검","2015-12-09 10:30","2015-12-10 14:00","2015-12-09 10:30","2015-12-10 14:00","연속",null,null,null,201508130184]
[14,"서울","직할","원남미아#1 T/L","154kV 보호배전반 정기점검","154kV 보호배전반 정기점검 -원남미아#1T/L 보호배전반 정기점검","2015-12-21 10:30","2015-12-21 17:30","취소","취소","당일",null,null,null,201510150065]
[15,"서울","직할","방산중앙#1 T/L","중앙S/S 170kV GIS 대체공사","중앙S/S 170kV GIS 대체공사(#2M.Tr 1차, 방산중앙#1T/L)","2015-12-03 09:30","2015-12-24 18:00","2015-12-03 09:30","2015-12-24 18:00","연속",null,null,null,201510140038]
[16,"남서울","강남","신양재역삼#3 T/L","지하(복합)변전소 인출구간 OF케이블 선종교체공사","가. 공사구간 ○ 154㎸ 신양재-역삼T/L : 역삼S/S∼J/B#13-1(3C×0.210㎞, 전력구) ○ 154㎸ 역삼-대치T/L : 역삼S/S∼J/B#14 (2C×0.319㎞, 전력구+관로) ○ 154㎸ 역삼-대치T/L : 대치S/S∼J/B#20 (2C×0.625㎞, 전력구+관로) 나. 케이블 포설 : 154㎸ XLPE 1,200㎟ × 2회","2015-12-21 10:00","2016-01-09 10:00","2015-12-21 10:00","2016-01-09 10:00","연속",null,null,null,201509080125]
[17,"남서울","영서","광명구공#2 T/L","170kV GIS 정밀점검공사(광명S/S 광명-구공#2T/L)","170kV GIS 정밀점검공사(광명S/S 광명-구공#2T/L)","2015-12-05 09:00","2015-12-06 18:00","2015-12-05 09:00","2015-12-06 18:00","연속",null,null,null,201508190137]
[18,"남서울","영서","독산대방#2 T/L","170kV GIS 정밀점검공사(독산S/S 독산-대방#2T/L)","170kV GIS 정밀점검공사(독산S/S 독산-대방#2T/L)","2015-12-02 15:00","2015-12-04 18:00","2015-12-02 15:00","2015-12-04 18:00","연속",null,null,null,201508190122]
[19,"남서울","영서","독산S/S 154kV #2 BUS","170kV GIS 정밀점검공사(독산S/S 독산-대방#2T/L)","170kV GIS 정밀점검공사(독산S/S 독산-대방#2T/L)","2015-12-03 09:00","2015-12-04 18:00","2015-12-03 09:00","2015-12-04 18:00","연속",null,null,null,201508190133]
[20,"남서울","영서","독산S/S 154kV #1 BUS","170kV GIS 정밀점검공사(독산S/S 독산-대방#1T/L)","170kV GIS 정밀점검공사(독산S/S 독산-대방#1T/L)","2015-12-01 09:00","2015-12-03 09:00","2015-12-01 09:00","2015-12-03 09:00","연속",null,null,null,201508190128]
[21,"남서울","영서","온수소래 T/L","154kV 온수-소래T/L 정밀점검","철탑 14기 정밀점검","2015-12-03 08:30","2015-12-03 18:00","2015-12-03 08:30","2015-12-03 18:00","당일",null,null,null,201510200045]
[22,"남서울","영서","화곡가양#1 T/L","미동작 차단기 조작시험","미동작 차단기 조작시험","2015-12-11 10:00","2015-12-11 10:30","2015-12-11 10:00","2015-12-11 10:30","당일",null,null,null,201510200029]
[23,"남서울","영서","화곡가양#2 T/L","미동작 차단기 조작시험","미동작 차단기 조작시험","2015-12-11 10:30","2015-12-11 11:00","2015-12-11 10:30","2015-12-11 11:00","당일",null,null,null,201510200030]
[24,"남서울","직할","교대이수#2 T/L","154kV 교대-이수T/L 지중선로 이설공사(방배로 1구간)","배경: 서초구청 시행 하수암거 설치에 따른 지중선로 이설 개요: 154KV 교대-이수T/L J/B#7~8, #9~10 (2구간, 0.66KM) XLPE1200 * 2회선","2015-12-21 09:00","2016-01-22 18:00","2015-12-21 09:00","2016-01-22 18:00","연속",null,null,null,201510140145]
[25,"인천","김포","경서북인천#2 T/L","경서북인천#2 T/L 보호반 대체(양단)","경서북인천#2 T/L 보호반 대체(양단) 및 GIS 기기점검","2015-12-14 09:00","2015-12-18 18:00","2015-12-14 09:00","2015-12-18 18:00","연속",null,null,null,201510210046]
[26,"인천","시흥","신시흥남동#1 T/L","154kV 신시흥-남동#1T/L 절연유 보충","154kV 신시흥-남동#1T/L 절연유 보충 - 남동EBG~남동SJ, 남동SJ~신동C/H","2015-12-04 09:00","2015-12-04 14:00","2015-12-04 09:00","2015-12-04 14:00","당일",null,null,null,201510140169]
[27,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동#2T/L 절연유 시료채취","154kV 신시흥-남동#2T/L 절연유 시료채취(14개소) - 전력구 6개소, 맨홀 8개소","2015-12-02 10:00","2015-12-02 18:00","2015-12-02 10:00","2015-12-02 18:00","당일",null,null,null,201510140168]
[28,"인천","시흥","오봉동춘#2 T/L","154kV 고잔분기 지중T/L 건설공사","○ 선종 및 회선수, 길이 : 154kV XLPE 2000, 4회선-1.4km","2015-12-01 09:00","2015-12-31 18:00","2015-12-01 09:00","2015-12-31 18:00","연속",null,null,null,201508060046]
[29,"인천","인천","주안관교#1 T/L","154kV 주안-관교#1T/L 절연유 보충","154kV 주안-관교#1T/L 절연유 보충 - 관교EBG~관교SJ, 주안TJ~M/H#9","2015-12-04 14:00","2015-12-04 20:00","2015-12-04 14:00","2015-12-04 20:00","당일",null,null,null,201510140170]
[30,"인천","인천","학익연수#2 T/L","154kV 학익-연수#2T/L 절연유 시료채취","154kV 학익-연수#2T/L 절연유 시료채취(6개소) - 전력구 3개소, 맨홀 3개소","2015-12-01 10:00","2015-12-01 18:00","2015-12-01 10:00","2015-12-01 18:00","당일",null,null,null,201510140146]
[31,"인천","직할","중동화곡#1 T/L","No.8~14 철탑 가공지선 교체공사","No.8~14 철탑 가공지선 교체공사","2015-12-11 08:00","2015-12-11 18:00","2015-12-11 08:00","2015-12-11 18:00","당일",null,null,null,201510230037]
[32,"인천","직할","중동화곡#2 T/L","No.8~14 철탑 가공지선 교체공사","No.8~14 철탑 가공지선 교체공사","2015-12-11 08:00","2015-12-11 18:00","2015-12-11 08:00","2015-12-11 18:00","당일",null,null,null,201510230036]
[33,"인천","인천","신경서S/S 154kV #66BUS","신경서-영종S/S SW증설공사","○ 전력계통 신뢰도 및 안정도 향상을 위한 증설공사 \n(신경서S/S~영종S/S 154kV T/L 1회선 증설 공사)","2015-12-01 10:00","2015-12-08 14:00","2015-12-01 10:00","2015-12-08 14:00","연속",null,null,null,201510290046]
[34,"인천","직할","신경서S/S 154kV #61BUS","신경서-영종S/S SW증설공사","○ 전력계통 신뢰도 및 안정도 향상을 위한 증설공사 \n(신경서S/S~영종S/S 154kV T/L 1회선 증설 공사)","2015-12-08 14:00","2015-12-15 18:00","2015-12-08 14:00","2015-12-15 18:00","연속",null,null,null,201510290047]
[35,"인천","직할","영종S/S 154kV #2BUS","신경서-영종S/S SW증설공사","○ 전력계통 신뢰도 및 안정도 향상을 위한 증설공사 \n(신경서S/S~영종S/S 154kV T/L 1회선 증설 공사)","2015-12-16 10:00","2015-12-20 18:00","2015-12-16 10:00","2015-12-20 18:00","연속",null,null,null,201510290045]
[36,"인천","직할","영종S/S 154kV #1BUS","신경서-영종S/S SW증설공사","○ 전력계통 신뢰도 및 안정도 향상을 위한 증설공사 \n(신경서S/S~영종S/S 154kV T/L 1회선 증설 공사)","2015-12-21 10:00","2015-12-25 18:00","2015-12-21 10:00","2015-12-25 18:00","연속",null,null,null,201510290044]
[37,"경기북부","구리","덕소별내#1 T/L","갈매지구 지장철탑 이설공사","철탑 설치1기, 철거5기","2015-12-03 07:00","2015-12-05 18:00","2015-12-03 07:00","2015-12-05 18:00","연속",null,null,null,201509140223,"○"]
[38,"경기북부","구리","동서울청평PP#1 T/L","154kV 서종분기T/L 건설공사","○ 구간 : 154kV 동서울-청평PP T/L No.64, 65 ~ 신설 154kV 서종S/S ○ 설비규모 : 0.283km(C/H 1기) ○ 당해작업내용 : C/H 조립","2015-12-08 08:00","2015-12-09 18:00","2015-12-08 08:00","2015-12-09 18:00","매일",null,null,null,201510150010]
[39,"경기북부","파주","신파주송포#2 T/L","2015~2015년 파주전력 변전협력회사 총액공사","2015~2015년 파주전력 변전협력회사 총액공사 송포S/S 신파주-송포#2T/L 인출DS 전자변 에어누기 보수","2015-12-07 10:00","2015-12-07 15:00","2015-12-07 10:00","2015-12-07 15:00","당일",null,null,null,201510140049]
[40,"경기북부","파주","신파주금촌#1 T/L","154kV 신파주-금촌#1T/L 안전이격확보공사","안전이격확보공사#1T/L 본 선로 구성","2015-12-03 07:00","2015-12-05 18:00","2015-12-24 07:00","2015-12-27 18:00","연속",null,null,null,201509110369]
[41,"경기북부","파주","양주일산#1 T/L","154kV 고양분기T/L 건설공사","○ 사업목적 : 경기도 고양시 풍동, 식사택지지구의 신규 부하공급 및 인근 송포, 일산, 호수변전소의 중부하 해소를 위함 ○ 사업규모 : 0.738km(1기 C/H) ○ 작업내용 : 154kV 양주-일산T/L No.39 → 신설C/H 교체 - 1차휴전 : 가선로 구성(#2T/L : 9/13~15, #1T/L : 9/16~20) - 2차휴전 :","2015-12-08 07:00","2015-12-17 18:00","2015-12-08 07:00","2015-12-17 18:00","연속",null,null,null,201509110433,"○"]
[42,"경기북부","파주","양주일산#2 T/L","154kV 고양분기T/L 건설공사","○ 사업목적 : 경기도 고양시 풍동, 식사택지지구의 신규 부하공급 및 인근 송포, 일산, 호수변전소의 중부하 해소를 위함 ○ 사업규모 : 0.738km(1기 C/H) ○ 작업내용 : 154kV 양주-일산T/L No.39 → 신설C/H 교체 - 1차휴전 : 가선로 구성(#2T/L : 9/13~15, #1T/L : 9/16~20) - 2차휴전 :","2015-12-18 07:00","2015-12-24 18:00","2015-12-18 07:00","2015-12-24 18:00","연속",null,null,null,201509110434]
[43,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 일동원곡#1, #4MTr 1차 GIS 교체공사","2015-12-11 09:00","2015-12-16 18:00","2015-12-11 09:00","2015-12-16 18:00","연속",null,null,null,201510070098]
[44,"경기","군포","일동S/S 154kV #1 BUS","일동S/S 154kV #60Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 일동원곡#1, #4MTr 1차 GIS 교체공사","2015-12-04 09:00","2015-12-10 18:00","2015-12-04 09:00","2015-12-10 18:00","연속",null,null,null,201510070096]
[45,"경기","군포","일동원곡#1 T/L","일동S/S 154kV 일동원곡#1TL GIS 교체공사","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 일동원곡#1TL GIS 교체공사","2015-12-01 09:00","2015-12-17 18:00","2015-12-01 09:00","2015-12-17 18:00","연속",null,null,null,201510070094]
[46,"경기","군포","일동S/S 154kV #2 BUS","일동S/S 154kV #65Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 일동원곡#1, #4MTr 1차 GIS 교체공사","2015-12-01 09:00","2015-12-03 18:00","2015-12-01 09:00","2015-12-03 18:00","연속",null,null,null,201510070095]
[47,"경기","군포","일동S/S 154kV #1 BUS","일동S/S 154kV #60Bus","일동SS 154kV 장기사용 GIS 교체공사 : 일동S/S 일동원곡#1, #4MTr 1차 GIS 교체공사","2015-12-17 09:00","2015-12-17 18:00","2015-12-17 09:00","2015-12-17 18:00","연속",null,null,null,201510070100]
[48,"경기","평택","송탄안성 T/L","평택 동삭2지구 지중화 관련 임시이설공사","송탄안성T/L NO.8~11 임시이설공사 신설 4기(No.9, 10, 10-1, 10-2) 철거 2기(No.9, 10)","2015-12-04 09:00","2015-12-06 18:00","2015-12-04 09:00","2015-12-06 18:00","연속",null,null,null,201510050042,"○"]
[49,"경기","평택","송탄소사벌 T/L","평택 동삭2지구 지중화 관련 임시이설공사","임시이설공사 신설 - 4기(No.9, 10, 10-1, 10-2) 철거 - 2기(No.9, 10)","2015-12-01 07:00","2015-12-03 18:00","2015-12-01 07:00","2015-12-03 18:00","연속",null,null,null,201510050041]
[50,"경기","평택","오산향남#2 T/L","154kV 오산옥내화관련 인출정비공사","오산향남T/L : 154kV XLPE2500 * 2C 0.3km, 오산평택T/L : 154kV XLPE1200 * 2C 0.3km, 모선연계 : 154kV XLPE1200 * 1C 0.2km,","2015-12-14 10:00","2015-12-15 17:00","2015-12-14 10:00","2015-12-15 17:00","연속",null,null,null,201510050023]
[51,"경기","평택","오산평택#2 T/L","154kV 오산옥내화관련 인출정비공사","오산향남T/L : 154kV XLPE2500 * 2C 0.3km, 오산평택T/L : 154kV XLPE1200 * 2C 0.3km, 모선연계 : 154kV XLPE1200 * 1C 0.2km,","2015-12-16 10:00","2015-12-19 17:00","2015-12-16 10:00","2015-12-19 17:00","연속",null,null,null,201510050029]
[52,"강원","강릉","신제천주진#1 T/L","주진S/S 170kV GIS 유압장치 누유 보수","주진S/S 170kV GIS 유압장치 누유 보수","2015-12-01 10:00","2015-12-01 18:00","2015-12-01 10:00","2015-12-01 18:00","당일",null,null,null,201510130008]
[53,"강원","강릉","신제천주진#2 T/L","주진S/S 170kV GIS 유압장치 누유 보수","주진S/S 170kV GIS 유압장치 누유 보수","2015-12-02 10:00","2015-12-02 14:00","2015-12-02 10:00","2015-12-02 14:00","당일",null,null,null,201510130009]
[54,"강원","동해","동해북평#1 T/L","154kV 동북, 영동화력T/L 지중화공사","동해북평T/L 지중화","2015-12-21 09:00","2016-01-15 18:00","2015-12-21 09:00","2016-01-15 18:00","연속",null,null,null,201510120046]
[55,"강원","동해","삼척GP S/S 154KV #67 BUS ((CB))","345kV 삼척GP S/Y 건설공사","1. 154kV 송전선로보호반 이설(2면) 2. 송전선로 - 변전소 붓싱간 연결 3. 피뢰기 인하선 설치","2015-12-04 17:00","2015-12-04 18:00","2015-12-04 17:00","2015-12-04 18:00","당일",null,null,null,201510160094]
[56,"강원","동해","삼척GP S/S 154KV #61 BUS ((CB))","345kV 삼척GP S/Y 건설공사","1. 154kV 송전선로보호반 이설(2면) 2. 송전선로 - 변전소 붓싱간 연결 3. 피뢰기 인하선 설치","2015-12-04 16:00","2015-12-04 17:00","2015-12-04 16:00","2015-12-04 17:00","당일",null,null,null,201510160093]
[57,"강원","원주","홍천소양강HP T/L","154kV 소양T/L 안전이격 확보공사","철탑 철거 12기, 신설 10기","2015-12-09 00:08","2015-12-15 18:00","2015-12-01 00:08","2015-12-03 18:00","연속",null,null,null,201510120296]
[58,"강원","직할","남춘천춘천 T/L","154kV 소양T/L 안전이격 확보공사","철탑 철거 12기, 신설 10기","2015-12-02 00:08","2015-12-08 18:00","2015-12-04 00:08","2015-12-04 18:00","연속",null,null,null,201510120294]
[59,"강원","직할","북춘천화천HP T/L","154kV GIS 유압유 저장탱크 누유관련 점검 및 보수","유압유 누유관련 점검 및 보수","2015-12-08 09:00","2015-12-08 13:00","2015-12-08 09:00","2015-12-08 13:00","당일",null,null,null,201510130069]
[60,"강원","직할","춘천소양강HP T/L","2014~2015년 강원직할 송전정비 협력회사 총액공사","정비대상개소 정비(이도조정, 구형금구류 교체)","2015-12-16 00:08","2015-12-16 18:00","취소","취소","당일",null,null,null,201510120300]
[61,"강원","태백","도계태백 T/L","2015년 태백변전소 배전반 이설공사","도계-태백T/L 보호배전반 이설","2015-12-08 09:00","2015-12-11 18:00","2015-12-01 09:00","2015-12-04 18:00","연속",null,null,null,201510280106]
[62,"강원","태백","이원태백 T/L","이원-태백TL 안전이격확보공사","가철탑 -> 기존철탑 원복작업","2015-12-12 09:00","2015-12-13 18:00","취소","취소","연속",null,null,null,201510300025]
[63,"강원","태백","이원태백 T/L","2015년 태백변전소 배전반 정비공사","이원-태백T/L 보호반 이설","2015-12-01 09:00","2015-12-07 18:00","취소","취소","연속",null,null,null,201510270057]
[64,"충북","직할","왕암북충주#2 T/L","북충주S/S 154kV GIS 불량개소 제작사 점검","유압시스템 누유 관련 제작사 점검","2015-12-11 14:00","2015-12-11 18:00","2015-12-11 14:00","2015-12-11 18:00","당일",null,null,null,201510150050]
[65,"충북","직할","북충주충주#1 T/L","북충주S/S 154kV GIS 불량개소 제작사 점검","유압시스템 누유 관련 제작사 점검","2015-12-11 09:00","2015-12-11 14:00","2015-12-11 09:00","2015-12-11 14:00","당일",null,null,null,201510150049]
[66,"충북","직할","신제천영월CC#1 T/L","345kV 신제천S/S GIS화 공사","154kV GIS 설치 작업안전거리 확보","2015-12-01 08:00","2015-12-01 18:00","2015-12-01 08:00","2015-12-01 18:00","연속",null,null,null,201510190017]
[67,"충북","직할","신제천왕암#2 T/L","345kV 신제천S/S GIS화 공사","154kV GIS 설치 작업안전거리 확보","2015-12-06 08:00","2015-12-06 13:00","2015-12-06 08:00","2015-12-06 13:00","연속",null,null,null,201510190035]
[68,"충북","청주","청원신탄진 T/L","송전선로 정밀점검 및 횡단개소 애자련 보완공사","애자련 보완:2련화, 정밀점검","2015-12-02 09:00","2015-12-02 18:00","2015-12-02 09:00","2015-12-02 18:00","당일",null,null,null,201510130133]
[69,"대전충남","서산","신당진당진#1 T/L","당진S/S 신당진-당진#1T/L GIDS 하자, LA, PT 보통점검","당진S/S 신당진-당진#1T/L GIDS 하자점검 및 LA, PT 보통점검","2015-12-11 09:00","2015-12-11 18:00","2015-12-11 09:00","2015-12-11 18:00","당일",null,null,null,201510130109]
[70,"대전충남","직할","신탄진대청HP T/L","송전선로 정밀점검 및 횡단개소 애자련 보완공사","애자련 보완:2련화, 정밀점검","2015-12-02 09:00","2015-12-02 18:00","2015-12-02 09:00","2015-12-02 18:00","당일",null,null,null,201510130135]
[71,"대전충남","청양","신풍공주#1 T/L","154kV 신풍-공주#1T/L 보호배전반 교체공사","○ 154kV 신풍-공주#1T/L 보호배전반 교체","2015-12-09 09:00","2015-12-11 18:00","2015-12-09 09:00","2015-12-11 18:00","연속",null,null,null,201510080124]
[72,"전북","군산","군산동군산#1 T/L","154kV 동군산-군산T/L 일부구간 지중화","신설 C/H 가선, EBA 접속, 가압","2015-12-12 09:00","2015-12-19 18:00","2015-12-12 09:00","2015-12-19 18:00","연속",null,null,null,201510220004]
[73,"전북","군산","동군산장항#1 T/L","154kV 동군산-장항#1 T/L","154kV 군산-동군산T/L 철탑철거 공사 동군산S/S 인출 동군산-장항T/L 가공지선 철거","2015-12-21 07:30","2015-12-21 13:00","2015-12-21 07:30","2015-12-21 13:00","당일",null,null,null,201510210116]
[74,"전북","군산","동군산군산CC#2 T/L","동군산S/S 154kV 동군산-군산복합#2T/L","공사명 : 군산P/O 차단기 점검공사(345,154kV)","2015-12-09 10:00","2015-12-09 18:00","2015-12-09 10:00","2015-12-09 18:00","당일",null,null,null,201509140017]
[75,"전북","군산","동군산장항#2 T/L","154kV 동군산-장항#2 T/L","154kV 군산-동군산T/L 철탑철거 공사 동군산S/S 인출 동군산-장항T/L 가공지선 철거","2015-12-21 13:00","2015-12-21 18:00","2015-12-21 13:00","2015-12-21 18:00","당일",null,null,null,201510210117]
[76,"전북","군산","군산서군산#2 T/L","154kV 군산-서군산T/L No.37.1 철탑 보강공사","154kV 군산-서군산T/L No.37.1(군산-동군산T/L No.37) 강도 부족 철탑재 보강","2015-12-12 07:00","2015-12-13 18:00","2015-12-12 07:00","2015-12-13 18:00","연속",null,null,null,201510160059]
[77,"전북","군산","이리백산#1 T/L","154kV 이리-백산 #1T/L","154kV 이리-전주 등 2개T/L 지장철탑이설공사 154kV 이리-백산 #1T/L 휴전작업 ○ 전력선 공중이동 : 가철탑 → 신설철탑 (이리-전주, 이리-백산#1) ○ 전력선 교체 : 이리-전주#1 2~7호, 이리-백산#1 2~8호 ○ 용량증대 병행시행 : 이리-백산#1 2~8호(A240→HST/AW240)","2015-12-04 08:00","2015-12-09 18:00","2015-12-04 08:00","2015-12-09 18:00","연속",null,null,null,201505120253]
[78,"전북","김제","담양김제 T/L","154kV 담양-김제T/L","154kV 담양-김제T/L 135,136호 안전이격확보공사 담양-김제(정공-담양)T/L 135,136호 2기 지지물 교체","2015-12-01 07:00","2015-12-03 18:00","2015-12-16 07:00","2015-12-18 18:00","연속",null,null,null,201509100045]
[79,"전북","김제","신김제정공#1 T/L","신김제S/S F/R용 ESS 설치공사","345kV 신김제S/S ESS설치공사 - 신김제S/S #61M.Tr 무부하가압","2015-12-14 09:00","2015-12-14 18:00","2015-12-14 09:00","2015-12-14 18:00","당일",null,null,null,201510060066]
[80,"전북","김제","신김제전주#2 T/L","154kV 신김제-전주#2 T/L","CVT 보통점검","2015-12-03 14:00","2015-12-03 18:00","2015-12-05 14:00","2015-12-05 18:00","당일",null,null,null,201508310024]
[81,"전북","김제","신김제전주#1 T/L","154kV 신김제-전주#1 T/L","CVT 보통점검","2015-12-03 09:00","2015-12-03 14:00","2015-12-05 09:00","2015-12-05 14:00","당일",null,null,null,201508310023]
[82,"전북","김제","정공담양 T/L","154kV 정공-담양T/L","154kV 담양-김제T/L 135,136호 노후취약지지물 교체공사 담양-김제(정공-담양)T/L 135,136호 2기 지지물 교체","2015-12-04 07:00","2015-12-06 18:00","2015-12-19 07:00","2015-12-21 18:00","연속",null,null,null,201509100047,"○"]
[83,"전북","직할","북전주봉동#2 T/L","154kV 북전주-봉동#2 T/L","(주)영인기술 154kV 송전선로 보호반 성능개선 BFI, Trip 및 재폐로 용도로 사용되는 200번대 IGBT 접점과 경보용으로 사용되는 300번대 기계적(Dry) 접점 상호 결선 및 접점 설정 변경","2015-12-08 10:00","2015-12-08 18:00","2015-12-20 10:00","2015-12-20 18:00","당일",null,null,null,201510070012]
[84,"전북","직할","북전주봉동#1 T/L","154kV 북전주-봉동#1 T/L","(주)영인기술 154kV 송전선로 보호반 성능개선 BFI, Trip 및 재폐로 용도로 사용되는 200번대 IGBT 접점과 경보용으로 사용되는 300번대 기계적(Dry) 접점 상호 결선 및 접점 설정 변경","2015-12-07 10:00","2015-12-07 18:00","2015-12-19 10:00","2015-12-19 18:00","당일",null,null,null,201510070011]
[85,"광주전남","광주","담양일곡#2 T/L","154kV 담양-일곡T/L 안전이격확보공사","철탑상향 1기 (173호)","2015-12-01 00:07","2015-12-03 18:00","2015-12-19 00:07","2015-12-19 18:00","연속",null,null,null,201510070130]
[86,"광주전남","광주","담양일곡#1 T/L","154kV 담양-일곡T/L 안전이격확보공사","철탑상향 1기 (173호)","2015-12-04 07:00","2015-12-06 18:00","2015-12-17 07:00","2015-12-18 18:00","연속",null,null,null,201510070129]
[87,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌#1T/L(가공송전선로 순시점검 위탁공사)","2015년 가공송전선로 순시점검 위탁공사 - 초기점검(No.1~10호, 66호)","2015-12-01 09:00","2015-12-02 18:00","2015-12-01 09:00","2015-12-02 18:00","매일",null,null,null,201510130160]
[88,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌#2T/L(가공송전선로 순시점검 위탁공사)","2015년 가공송전선로 순시점검 위탁공사 - 초기점검(No.1~10호, 66호)","2015-12-03 09:00","2015-12-04 18:00","2015-12-03 09:00","2015-12-04 18:00","매일",null,null,null,201510130162]
[89,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주#1T/L(순천변전협력회사 총액공사)","15년 순천변전협력회사 총액공사 - 승주S/S LA 보통점검","2015-12-07 10:00","2015-12-07 18:00","2015-12-07 10:00","2015-12-07 18:00","당일",null,null,null,201510130225]
[90,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP-여수TP#1T/L(송전정비 협력회사 총액공사)","2014~15년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 1~14호, 7기","2015-12-01 07:00","2015-12-01 18:00","2015-12-01 07:00","2015-12-01 18:00","당일",null,null,null,201510130142]
[91,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP-여수TP#2T/L(송전정비 협력회사 총액공사)","2014~15년 송전정비 협력회사 총액공사 - SB댐퍼 설치 : 1~14호, 7기","2015-12-02 07:00","2015-12-02 18:00","2015-12-02 07:00","2015-12-02 18:00","당일",null,null,null,201510130144]
[92,"광주전남","순천","여천여수#2 T/L","여천여수#2 T/L(154kV 여천-여수T/L 송전용량증대 전선교체)","154kV 여천-여수T/L 송전용량증대 전선교체 공사","2015-12-08 07:00","2015-12-22 18:00","2015-12-15 07:00","2015-12-29 18:00","연속",null,null,null,201509160234]
[93,"광주전남","순천","여천호남TP#1 T/L","여천호남TP#1 T/L(154kV 여천-여수T/L 송전용량증대 전선교체)","154kV 여천-여수T/L 송전용량증대 전선교체 공사","2015-12-08 07:00","2015-12-14 18:00","2015-12-15 07:00","2015-12-21 18:00","연속",null,null,null,201509160237]
[94,"광주전남","순천","여천호남TP#2 T/L","여천호남TP#2 T/L(154kV 여천-여수T/L 송전용량증대 전선교체)","154kV 여천-여수T/L 송전용량증대 전선교체 공사","2015-12-15 07:00","2015-12-18 18:00","2015-12-22 07:00","2015-12-25 18:00","연속",null,null,null,201509160236]
[95,"광주전남","직할","고창영광 T/L","154kV 고창-영광T/L","14년-15년 직할 변전협력회사 총액공사 - 영광S/S 고창-영광T/L CVT 대체","2015-12-04 13:00","2015-12-04 18:00","2015-12-06 13:00","2015-12-06 18:00","당일",null,null,null,201510130179]
[96,"광주전남","직할","영광홍농 T/L","154kV 영광-홍농T/L","14년-15년 직할 변전협력회사 총액공사 - 영광S/S 영광-홍농T/L CVT 대체","2015-12-04 09:00","2015-12-04 13:00","2015-12-06 09:00","2015-12-06 13:00","당일",null,null,null,201510130174]
[97,"대구경북","구미","상주영동 T/L","154kV 상주T/L 안전이격확보공사","ㅇ 철탑 7기 철거, 7기 설치 ㅇ 전력선 교체 : No.127 - 133","2015-12-01 08:00","2015-12-20 18:00","2015-12-01 08:00","2015-12-20 18:00","연속",null,null,null,201507080236]
[98,"대구경북","구미","상주보은 T/L","154kV 상주T/L 안전이격확보공사","ㅇ 철탑 7기 철거, 7기 설치 ㅇ 전력선 교체 : No.127 - 133","2015-12-01 08:00","2015-12-20 18:00","2015-12-01 08:00","2015-12-20 18:00","연속",null,null,null,201507080235]
[99,"대구경북","달성","강창성서#1 T/L","안전확보를 위한 휴전(아킹혼 철거작업)","다산-강창#1 작업시 하단 강창-성서#1 휴전","2015-12-08 09:00","2015-12-08 18:00","2015-12-06 09:00","2015-12-06 18:00","당일",null,null,null,201510070043]
[100,"대구경북","달성","고령쌍림#2 T/L","고령 6244 정밀테스트선로","고령 6244테스트선로","2015-12-05 13:00","2015-12-06 18:00","2015-12-05 13:00","2015-12-06 18:00","매일",null,null,null,201510190055]
[101,"대구경북","달성","고령다산#2 T/L","154kV고령-다산T/L 지장철탑 이설공사","No.58~60 구간 지장철탑이설 - 철탑교체 1기(No.59), 가철주 1기설치 - 전력선 교체 : No.58~60","2015-12-05 08:00","2015-12-07 18:00","2015-12-05 08:00","2015-12-07 18:00","연속",null,null,null,201510120191]
[102,"대구경북","달성","고령다산#2 T/L","154kV고령-다산T/L 지장철탑 이설공사","No.58~60 구간 지장철탑이설 - 철탑교체 1기(No.59), 가철주 1기설치 - 전력선 교체 : No.58~60","2015-12-01 08:00","2015-12-01 18:00","2015-12-01 08:00","2015-12-01 18:00","당일",null,null,null,201510120190]
[103,"대구경북","달성","고령다산#1 T/L","154kV고령-다산T/L 지장철탑 이설공사","No.58~60 구간 지장철탑이설 - 철탑교체 1기(No.59), 가철주 1기설치 - 전력선 교체 : No.58~60","2015-12-02 08:00","2015-12-04 18:00","2015-12-02 08:00","2015-12-04 18:00","연속",null,null,null,201510120192]
[104,"대구경북","달성","다산강창#1 T/L","아킹혼 철거작업","복도체 2련내장 피뢰기 설치개소 아킹혼 철거 1-53호","2015-12-08 09:00","2015-12-11 18:00","2015-12-06 09:00","2015-12-13 18:00","매일",null,null,null,201510070042]
[105,"대구경북","달성","다산강창#1 T/L","다산 6144 정밀점검 테스트선로","다산 6144정밀테스트선로","2015-12-13 14:00","2015-12-13 15:00","취소","취소","당일",null,null,null,201510190056]
[106,"대구경북","달성","다산강창#2 T/L","다산 6144 정밀점검 테스트선로","다산 6144정밀테스트서놀","2015-12-20 14:00","2015-12-20 15:00","2015-12-20 14:00","2015-12-20 15:00","당일",null,null,null,201510190057]
[107,"대구경북","달성","달성상인#1 T/L","보호반 판넬교체공사","보호반교체작업","2015-12-01 09:30","2015-12-02 18:00","2015-12-01 09:30","2015-12-02 18:00","연속",null,null,null,201510050064]
[108,"대구경북","달성","대구봉덕#2 T/L","아킹혼 철거작업","복도체 2련내장 피뢰기 설치개소 아킹혼 철거 1-32호","2015-12-02 09:00","2015-12-03 18:00","2015-12-02 09:00","2015-12-03 18:00","연속",null,null,null,201510070038]
[109,"대구경북","달성","쌍림합천#1 T/L","GIS정밀점검","쌍림SS GIS정밀점검","2015-12-09 09:00","2015-12-11 18:00","2015-12-09 09:00","2015-12-11 18:00","연속",null,null,null,201510080041]
[110,"대구경북","안동","신영주안동#1 T/L","안동S/S 154kV #1Sh.C 증설공사","GIS(170kV 50kA 1250A) * 1CCT 설치","2015-12-01 09:00","2015-12-14 18:00","2015-12-01 09:00","2015-12-14 18:00","연속",null,null,null,201510070186]
[111,"대구경북","영주","상주점촌#1 T/L","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","점촌S/S 상주-점촌#2T/L, 6100CB 장기사용 GIS 대체공사","2015-12-03 08:10","2015-12-03 08:15","취소","취소","당일",null,null,null,201509100535]
[112,"대구경북","달성","성서달성#2 T/L","보호계전기 회로보완","보호계전기 회로보완","2015-12-11 09:00","2015-12-11 18:00","2015-12-19 09:00","2015-12-19 18:00","당일",null,null,null,201510280011]
[113,"부산울산","북부산","삼계김해 T/L","장기사용 배전반 대체공사","삼계-김해T/L 보호배전반 대체","2015-12-18 09:00","2015-12-20 18:00","2015-12-18 09:00","2015-12-20 18:00","연속",null,null,null,201510120189]
[114,"부산울산","서부산","서부산부민#2 T/L","서부산S/S 154kV 서부산-부민#2T/L GIS 보통점검","서부산S/S 154kV 서부산-부민#2T/L GIS 보통점검","2015-12-11 10:00","2015-12-11 18:00","2015-12-11 10:00","2015-12-11 18:00","당일",null,null,null,201510120104]
[115,"부산울산","서부산","신녹산용원#1 T/L","154kV 부산신항 예비전력 수급지점 변경공사","- 170kV GIS 50kA 1,250A × 1CCT 설치 - 송전선로 보호배전반 1면 이설 - 기타 부대공사","2015-12-12 08:00","2015-12-14 08:00","2015-12-12 08:00","2015-12-14 08:00","연속",null,null,null,201510070034]
[116,"부산울산","서부산","신녹산용원#1 T/L","154kV 부산신항 예비전력 수급지점 변경공사","- 170kV GIS 50kA 1,250A × 1CCT 설치 - 송전선로 보호배전반 1면 이설 - 기타 부대공사","2015-12-19 08:00","2015-12-21 08:00","2015-12-19 08:00","2015-12-21 08:00","연속",null,null,null,201510070035]
[117,"부산울산","울산","동울산방어진 T/L","2014-15년 울산전력지사 변전협력 총액공사","GIS 초기점검","2015-12-06 09:00","2015-12-06 18:00","2015-12-06 09:00","2015-12-06 18:00","당일",null,null,null,201510260066]
[118,"부산울산","울산","동울산효문#3 T/L","2014-15년 울산전력지사 변전협력 총액공사","GIS 초기점검","2015-12-02 09:00","2015-12-02 18:00","2015-12-02 09:00","2015-12-02 18:00","당일",null,null,null,201510260065]
[119,"부산울산","울산","옥동외동#2 T/L","2014-15년 울산전력지사 변전협력 총액공사","CPD PNL 교체","2015-12-04 10:00","2015-12-04 11:00","2015-12-04 10:00","2015-12-04 11:00","당일",null,null,null,201510120133]
[120,"부산울산","울산","옥동외동#1 T/L","2014-15년 울산전력지사 변전협력 총액공사","CPD PNL 교체","2015-12-04 09:00","2015-12-04 10:00","2015-12-04 09:00","2015-12-04 10:00","당일",null,null,null,201510120132]
[121,"경남","직할","신김해주촌#1 T/L","신김해S/S 신김해-주촌#1T/L CPD 교체공사","신김해S/S 신김해-주촌#1T/L CPD 교체공사","2015-12-06 08:30","2015-12-06 13:30","2015-12-06 08:30","2015-12-06 13:30","당일",null,null,null,201510060018]
[122,"경남","직할","신김해주촌#2 T/L","신김해S/S 신김해-주촌#2T/L CPD 교체공사","신김해S/S 신김해-주촌#2T/L CPD 교체공사","2015-12-06 13:30","2015-12-06 18:30","2015-12-06 13:30","2015-12-06 18:30","당일",null,null,null,201510060019]
[123,"경남","진주","거창합천#2 T/L","거창S/S 거창-합천#2T/L 피뢰기 교체","거창S/S 거창-합천#2T/L 피뢰기 교체","2015-12-12 09:30","2015-12-12 18:30","2015-12-12 09:30","2015-12-12 18:30","당일",null,null,null,201510080160]
[124,"경남","진주","의령동진주#2 T/L","동진주S/S 의령-동진주#2T/L CB 627 초기점검","동진주S/S 의령-동진주#2T/L CB 627 초기점검","2015-12-12 09:30","2015-12-13 18:30","2015-12-12 09:30","2015-12-13 18:30","연속",null,null,null,201507080214]
[125,"경남","진주","동진주진주#2 T/L","진주S/S 동진주-진주#2T/L GCB 대체","진주S/S GCB 대체 동진주S/S 동진주-진주#2T/L CB 637 초기점검","2015-12-05 09:30","2015-12-06 18:30","2015-12-05 09:30","2015-12-06 18:30","연속",null,null,null,201510200144]
[126,"경남","진주","하동하동화력#1 T/L","하동S/S 하동하동화력#1 T/L 피뢰기 교체","하동S/S 하동하동화력#1 T/L 피뢰기 교체","2015-12-02 09:30","2015-12-02 18:30","2015-12-02 09:30","2015-12-02 18:30","당일",null,null,null,201510080159]
[127,"경남","진주","함양거창#1 T/L","함양거창#1 T/L PNL 대체","함양거창#1 T/L PNL 대체","2015-12-05 09:30","2015-12-06 18:30","2015-12-05 09:30","2015-12-06 18:30","연속",null,null,null,201510080166]
[128,"경남","통영","신고성삼천포#2 T/L","신고성S/S 154kV 신고성-삼천포#2T/L GIS 고장예방활동","실리콘 러버 히터 설치","2015-12-12 14:00","2015-12-12 18:30","2015-12-12 14:00","2015-12-12 18:30","당일",null,null,null,201510120185]
[129,"경남","통영","신고성거제#1 T/L","신고성S/S 154kV 신고성-거제#1T/L GIS 고장예방활동","신고성S/S 154kV 신고성-거제#1T/L GIS 고장예방활동(실리콘 러버 히터 설치 등)","2015-12-06 09:30","2015-12-06 14:00","2015-12-06 09:30","2015-12-06 14:00","당일",null,null,null,201510120180]
[130,"경남","통영","신고성거제#2 T/L","신고성S/S 154kV 신고성-거제#2T/L GIS 고장예방활동","신고성S/S 154kV 신고성-거제#2T/L GIS 고장예방활동(실리콘 러버히터 설치)","2015-12-06 14:00","2015-12-06 18:30","2015-12-06 14:00","2015-12-06 18:30","당일",null,null,null,201510120181]
[131,"경남","통영","신고성삼천포#1 T/L","신고성S/S 154kV 신고성-삼천포#1T/L GIS 고장예방활동","신고성S/S 154kV 신고성-삼천포#1T/L GIS 고장예방활동(실리콘 러버 히터 설치 등)","2015-12-12 09:30","2015-12-12 14:00","2015-12-12 09:30","2015-12-12 14:00","당일",null,null,null,201510120183]
[132,"경남","함안","신마산S/S 154kV #61 BUS","신마산S/S #61BUS 과열개소 보수","신마산S/S #61BUS 6200옆 EXP금구 과열보수","2015-12-06 09:30","2015-12-06 17:30","2015-12-06 09:30","2015-12-06 17:30","당일",null,null,null,201510110031]
[133,"경남","함안","신김해진영#2 T/L","154kV 진영변전소 외벽 교체공사","154kV 진영변전소 외벽 교체공사","2015-12-11 09:00","2015-12-12 18:00","2015-12-11 09:00","2015-12-12 18:00","연속",null,null,null,201510140212]
[134,"경남","함안","신김해진영#2 T/L","154kV 진영변전소 외벽 교체공사","154kV 진영변전소 외벽 교체공사","2015-12-05 09:00","2015-12-07 18:00","2015-12-05 09:00","2015-12-07 18:00","연속",null,null,null,201510140211]
[135,"경남","함안","신김해진영#1 T/L","154kV 진영변전소 외벽 교체공사","154kV 진영변전소 외벽 교체공사","2015-12-12 09:00","2015-12-13 18:00","2015-12-12 09:00","2015-12-13 18:00","연속",null,null,null,201510140210]
[136,"경남","함안","신김해진영#1 T/L","154kV 진영변전소 외벽 교체공사","154kV 진영변전소 외벽 교체공사","2015-12-05 09:00","2015-12-06 18:00","2015-12-05 09:00","2015-12-06 18:00","연속",null,null,null,201510140209]

{"sheet":"한수원","index":2,"n_rows":5,"n_cols":20,"rows_kept":5,"cut":false,"hidden":false,"merged":[[0,0,0,6],[2,12,3,12],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,19,3,19],[2,13,3,13],[2,14,3,14],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18]]}
["2015년 12월 월간휴전계획표(한수원)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업\n구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소간","사업소내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"한빛본부","한빛3발","#6 주변압기","6호기 10차 계획예방정비\n#6 주변압기 점검\n* 조작차단기 : PCB 7E00 7E71","○ 주변압기 C상 교체\n○ 주변압기 일반점검\n○ 소내보조변압기 일반점검\n○ 소내보조변압기 AVR 교체","2015-12-10T09:00:00","2015-12-31T18:00:00","2015-12-10T09:00:00","2015-12-31T18:00:00","연속","Y"]