{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","한수원"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":8,"n_cols":16,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 3월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백S/S TIE-#4 M.Tr 1차 CB","신태백S/S 800kV GIS 보통 및 정밀점검공사[8500]","신태백S/S 800kV GIS 보통 및 정밀점검공사[8500]","2016-03-14 09:00","2016-03-30 18:00","취소","취소","연속",null,null,null,201601070140]
[2,"강원","태백","신태백S/S 신태백-신가평#1T/L CB(8571)","신태백S/S 800kV GIS 보통 및 정밀점검공사[8571]","신태백S/S 800kV GIS 보통 및 정밀점검공사[8571]","2016-03-14 09:00","2016-03-30 18:00","취소","취소","연속",null,null,null,201601070141]
[3,"대전충남","서산","당진T/P TIE Tr A","당진T/P 765kV Tie-Tr 보통점검","○당진T/P Tie-Tr 보통점검 및 보호반 교체 / 81Bay, 71Bay 차단실패 보호반 교체","2016-03-02 09:00","2016-03-16 18:00","2016-03-02 09:00","2016-03-16 18:00","연속",null,null,null,201601150051]
[4,"대전충남","서산","신서산S/S #3 M.Tr A-1","신서산S/S #3M.Tr 부싱온라인 모니터링 시스템 설치","○ 신서산S/S #3M.Tr 부싱온라인 모니터링 시스템 설치","2016-03-21 09:00","2016-03-23 18:00","2016-03-21 09:00","2016-03-23 18:00","연속",null,null,null,201601150100]

{"sheet":"345송부","index":1,"n_rows":163,"n_cols":16,"rows_kept":163,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 3월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#2 T/L","2015-16년 성동전력지사 지중송전설비 위탁정비공사","345kV OF케이블 절연유 시료채취","2016-03-16 09:00","2016-03-16 18:00","2016-03-16 09:00","2016-03-16 18:00","당일",null,null,null,201601140154,"-"]
[2,"서울","중부","중부S/S #2 M.Tr A","2016~2017년 중부전력지사 변전협력업체 총액공사","중부S/S #2M.Tr 관련설비 보통점검","2016-03-31 10:00","2016-04-01 18:00","2016-03-31 10:00","2016-04-01 18:00","연속",null,null,null,201601120170,"-"]
[3,"서울","중부","중부S/S #1 M.Tr A","2016~2017년 중부전력지사 변전협력업체 총액공사","중부S/S #1M.Tr 3차측 #1S.Tr 대체관련 연동시험","2016-03-30 10:00","2016-03-30 18:00","2016-03-30 10:00","2016-03-30 18:00","당일",null,null,null,201601120190,"-"]
[4,"남서울","직할","영등포S/S 345kV #1 Sh.R","영등포S/S 362kV #1Sh.R 차단기 정밀점검","ㅇ영등포S/S 362kV #1Sh.R 차단기 정밀점검","2016-03-07 09:00","2016-03-10 18:00","2016-03-07 09:00","2016-03-10 18:00","연속",null,null,null,201601120041,"-"]
[5,"남서울","직할","영등포S/S 345kV #2 Sh.R","영등포S/S 362kV #2Sh.R 차단기 정밀점검","영등포S/S 362kV #2Sh.R 차단기 정밀점검","2016-03-14 09:00","2016-03-18 18:00","2016-03-14 09:00","2016-03-18 18:00","연속",null,null,null,201601120043,"-"]
[6,"인천","시흥","신시흥#1S/S #2 M.Tr A","신시흥#1S/S #2 M.Tr C상 누유보수","신시흥#1S/S #2 M.Tr C상 누유보수","2016-03-09 09:00","2016-03-10 18:00","2016-03-09 09:00","2016-03-10 18:00","연속",null,null,null,201512300025,"-"]
[7,"인천","시흥","영흥T/P #1G/T 1차 CB (7172)","영흥T/P #1G/T 1차 CB(7172) 보통점검","영흥T/P #1G/T 1차 CB(7172) 보통점검","2016-03-17 10:00","2016-03-17 18:00","2016-03-17 10:00","2016-03-17 18:00","당일",null,null,null,201601050150,"-"]
[8,"인천","시흥","신시흥영흥TP#4 T/L","345kV 영흥T/L 피뢰기 설치 및 전력선 교체공사","- 피뢰기 설치 : 53기(159Set)","2016-03-13 08:00","2016-03-25 18:00","2016-03-03 08:00","2016-03-10 18:00","연속",null,null,"신뢰도개선",201512230059,"-"]
[9,"인천","시흥","영흥T/P #2G/T 1차 CB (7272)","영흥T/P #2G/T 1차 CB(7272) 보통점검","영흥T/P #2G/T 1차 CB(7272) 보통점검","2016-03-18 10:00","2016-03-18 18:00","2016-03-18 10:00","2016-03-18 18:00","당일",null,null,null,201601050152,"-"]
[10,"인천","시흥","영흥T/P 영흥TP연락#2T/L-#2G/T 1차 CB (7200)","영흥T/P 영흥TP연락#2T/L-#2G/T 1차 CB(7200) 보통점검","영흥T/P 영흥TP연락#2T/L-#2G/T 1차 CB(7200) 보통점검","2016-03-16 10:00","2016-03-16 18:00","2016-03-16 10:00","2016-03-16 18:00","당일",null,null,null,201601050149,"-"]
[11,"인천","시흥","영흥T/P 영흥TP연락#1T/L-#1 G/T 1차 CB (7100)","영흥T/P 영흥TP연락#1T/L-#1G/T 1차 CB(7100) 보통점검","영흥T/P 영흥TP연락#1T/L-#1G/T 1차 CB(7100) 보통점검","2016-03-15 10:00","2016-03-15 18:00","2016-03-15 10:00","2016-03-15 18:00","당일",null,null,null,201601050148,"-"]
[12,"인천","인천","서인천C/C 345kV #3 Sh.R CB(345kV #1 BUS) (7B79)","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #3 Sh.R CB(7B79) 대체","2016-03-02 09:30","2016-03-15 17:30","2016-03-02 09:30","2016-03-15 17:30","연속",null,null,null,201601130191,"-"]
[13,"인천","인천","서인천C/C 서인천신부평#1 Sh.R CB (7379)","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #1 Sh.R CB(7379) 대체","2016-03-16 09:30","2016-03-31 17:30","2016-03-16 09:30","2016-03-31 17:30","연속",null,null,null,201601130192,"-"]
[14,"인천","인천","신가좌S/S #3 M.Tr A","신가좌S/S #3 M.Tr 정밀점검 공사","신가좌S/S #3 M.Tr 정밀점검 공사 1,2차 LA 보통점검 공사","2016-03-28 08:00","2016-04-08 18:00","2016-03-28 08:00","2016-04-08 18:00","연속",null,null,null,201601130199,"-"]
[15,"인천","인천","신경서인천CC#2 T/L","345kV 신경서-인천CC #2T/L 중간접속함 교체공사","345kV 신경서-인천CC #2T/L 중간접속함 27Set 교체공사","2016-03-19 09:00","2016-04-12 18:00","2016-03-19 09:00","2016-04-12 18:00","연속",null,null,null,201601150050,"-"]
[16,"인천","인천","신인천C/C 345kV #76 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #76BUS 현장 모선개조 - SEC-CB(75-76-0) 대체 - 모선용 DS 대체","2016-03-18 09:30","2016-04-12 17:30","2016-03-18 09:30","2016-04-12 17:30","연속",null,null,null,201601190164,"-"]
[17,"인천","인천","신경서인천CC#1T/L-TIE CB (7200)","인천CC 용량부족GIS 대체공사","7200CB 대체","2016-03-02 10:00","2016-03-16 17:00","2016-03-02 10:00","2016-03-16 17:00","연속",null,null,null,201601120034,"-"]
[18,"인천","직할","서인천CC신부평#1 T/L","절연유 채취(345kV 서인천CC-신부평#1T/L)","시행근거 : 지중송전업무기준(제22차) 대상선로 : 345kV 서인천CC-신부평#1T/L 시행내용 : OF케이블 내 절연유 채취","2016-03-18 09:00","2016-03-19 18:00","2016-03-18 09:00","2016-03-19 18:00","연속",null,null,null,201601080119,"-"]
[19,"경기북부","구리","미금S/S #3 M.Tr A","미금S/S #3 M.Tr(7672)","미금S/S #3 M.Tr(362kV GIS 보통점검 공사)","2016-03-09 09:00","2016-03-09 18:00","2016-03-09 09:00","2016-03-09 18:00","당일",null,null,null,201601120105,"-"]
[20,"경기북부","구리","신의정부미금#2 T/L","미금S/S 신의정부미금#2 T/L(7500,7571)","362kV GIS 보통점검 공사","2016-03-11 09:00","2016-03-11 18:00","2016-03-11 09:00","2016-03-11 18:00","당일",null,null,null,201601120109,"-"]
[21,"경기북부","구리","미금S/S #1 M.Tr A","미금S/S #1 M.Tr(7172)","미금S/S #1 M.Tr(362kV GIS 보통점검 공사)","2016-03-08 09:00","2016-03-08 18:00","2016-03-08 09:00","2016-03-08 18:00","당일",null,null,null,201601120104,"-"]
[22,"경기북부","구리","미금성동#3 T/L","미금S/S 미금성동#3 T/L(7500,7572)","362kV GIS 보통점검 공사","2016-03-10 09:00","2016-03-10 18:00","2016-03-10 09:00","2016-03-10 18:00","당일",null,null,null,201601120107,"-"]
[23,"경기북부","구리","신가평신의정부#2 T/L","전선접속개소 전선교체 및 불량압축인류크램프 교체공사","ㅇ 전선소손개소에 대한 전력선 교체공사 ㅇ 불량압축인류크램프 교체공사","2016-03-22 08:00","2016-03-26 18:00","2016-03-22 08:00","2016-03-26 18:00","연속",null,null,null,201601120336,"-"]
[24,"경기북부","구리","신가평신의정부#1 T/L","345kV 신가평-신의정부#1T/L 불량압축인류크램프 교체공사","불량압축인류크램프 교체공사","2016-03-21 08:00","2016-03-21 18:00","2016-03-21 08:00","2016-03-21 18:00","당일",null,null,null,201601120333,"-"]
[25,"경기북부","구리","신가평미금#2 T/L","345kV 신가평-신의정부#1T/L 불량압축인류크램프 교체공사","불량압축인류크램프 교체공사 병가선로","2016-03-21 08:00","2016-03-21 18:00","2016-03-21 08:00","2016-03-21 18:00","당일",null,null,null,201601120334,"-"]
[26,"경기북부","구리","신가평신포천#1 T/L","신가평신포천T/L 송전선로 계통 병입공사","○ 송전선로 π분기 접속공사 ○ 신포천 변전소 보호반 교체공사 ○ OPGW 광통신 설치공사","2016-03-07 09:00","2016-03-14 18:00","2016-03-07 09:00","2016-03-14 18:00","연속",null,null,null,201601120374,"-"]
[27,"경기북부","구리","신가평신포천#2 T/L","신가평신포천T/L 송전선로 계통 병입공사","○ 송전선로 π분기 접속공사 ○ 신포천 변전소 보호반 교체공사 ○ OPGW 광통신 설치공사","2016-03-12 09:00","2016-03-18 18:00","2016-03-12 09:00","2016-03-18 18:00","연속",null,null,null,201601120375,"-"]
[28,"경기북부","구리","신포천S/S #4 M.Tr A","신포천S/S #4 M.Tr 초기점검","345kV 변압기 1대, 345kV GIS 1CCT, 170kV GIS 1CCT 초기점검","2016-03-04 09:00","2016-03-04 18:00","2016-03-04 09:00","2016-03-04 18:00","연속",null,null,null,201601110506,"-"]
[29,"경기북부","직할","신덕은동두천복합#2 T/L","신덕은동두천복합#2 T/L","2016~17년 직할변전협력회사 총액공사 - 신덕은-동두천C/C#2T/L GIS 하자점검 - 신덕은-동두천C/C#2T/L TIE GIS 하자점검","2016-03-02 10:00","2016-03-02 18:00","2016-03-02 10:00","2016-03-02 18:00","당일",null,null,null,201601130003,"-"]
[30,"경기북부","직할","신덕은동두천복합#1 T/L","신덕은동두천복합#1 T/L","2016~17년 직할변전협력회사 총액공사 - 신덕은-동두천C/C#1T/L GIS 하자점검 - 신덕은-동두천C/C#1T/L TIE GIS 하자점검","2016-03-03 10:00","2016-03-03 18:00","2016-03-03 10:00","2016-03-03 18:00","당일",null,null,null,201601130004,"-"]
[31,"경기북부","직할","신의정부S/S #1 M.Tr A","신의정부S/S #1 M.Tr A","2016~17년 직할변전협력회사 총액공사 - 본체 보통 - 1,2차 GIS 하자 - 7200GIS 하자","2016-03-07 10:00","2016-03-08 18:00","2016-03-07 10:00","2016-03-08 18:00","연속",null,null,null,201601130059,"-"]
[32,"경기북부","직할","신의정부S/S #2 M.Tr A","신의정부S/S #2 M.Tr A","2016~17년 직할변전협력회사 총액공사 - 본체 보통 - 1,2차 GIS 하자 - 7300GIS 하자","2016-03-16 10:00","2016-03-17 18:00","2016-03-16 10:00","2016-03-17 18:00","연속",null,null,null,201601130061,"-"]
[33,"경기북부","직할","신의정부S/S #3 M.Tr A","신의정부S/S #3 M.Tr A","2016~17년 직할변전협력회사 총액공사 - 본체 보통 - 1,2차 GIS 하자 - 7500GIS 하자","2016-03-21 10:00","2016-03-22 18:00","2016-03-21 10:00","2016-03-22 18:00","연속",null,null,null,201601130063,"-"]
[34,"경기북부","직할","신의정부S/S #4 M.Tr A","신의정부S/S #4 M.Tr A","2016~17년 직할변전협력회사 총액공사 - 본체 보통 - 1,2차 GIS 하자 - 7600GIS 하자","2016-03-23 10:00","2016-03-24 18:00","2016-03-23 10:00","2016-03-24 18:00","연속",null,null,null,201601130065,"-"]
[35,"경기북부","직할","양주S/S #4 M.Tr A","양주S/S #4 M.Tr A","2016~17년 직할변전협력회사 총액공사 - 3차절연보강 - 4479 보통 - #4-1Sh.R 하자","2016-03-18 10:00","2016-03-18 18:00","2016-03-18 10:00","2016-03-18 18:00","당일",null,null,null,201601130072,"-"]
[36,"경기북부","직할","양주S/S #3 M.Tr A","345kV 양주S/S #3M.Tr 설치공사","#3M.Tr 설치공사","2016-03-02 09:00","2016-03-11 18:00","2016-03-02 09:00","2016-03-11 18:00","연속",null,null,null,201601130204,"-"]
[37,"경기북부","직할","양주S/S #2 M.Tr C","양주S/S #2 M.Tr C","2016~17년 직할변전협력회사 총액공사 - C상 본체 보통 - 7472,7400GIS 보통 - 1,2차 LA 보통 - 3차 절연보강","2016-03-14 10:00","2016-03-14 18:00","2016-03-14 10:00","2016-03-14 18:00","당일",null,null,null,201601130069,"-"]
[38,"경기북부","직할","신파주양주#2 T/L","신파주양주#2 T/L","- GIS 하자점검","2016-03-04 10:00","2016-03-04 18:00","2016-03-04 10:00","2016-03-04 18:00","당일",null,null,null,201601130052,"-"]
[39,"경기북부","직할","양주S/S #1 M.Tr A","양주S/S #1 M.Tr A","2016~17년 직할변전협력회사 총액공사 - 3차절연보강 - 4179 보통 - 3차 절연보강","2016-03-15 10:00","2016-03-15 18:00","2016-03-15 10:00","2016-03-15 18:00","당일",null,null,null,201601130070,"-"]
[40,"경기북부","파주","신덕은S/S 신덕은-동두천CC#1T/L TIE CB (7500)","345kV 장문복합S/Y 건설공사","O T/L 보호반 설치 및 시험","2016-03-16 09:00","2016-03-25 18:00","2016-03-16 09:00","2016-03-25 18:00","연속",null,null,null,201601120100,"-"]
[41,"경기북부","파주","신덕은S/S TIE-#3 M.Tr 1차 CB (7300)","345kV 장문복합S/Y 건설공사","O T/L 보호반 설치 및 시험","2016-03-16 09:00","2016-03-25 18:00","2016-03-16 09:00","2016-03-25 18:00","연속",null,null,null,201601120088,"-"]
[42,"경기북부","파주","신덕은S/S 신덕은-장문CC #1T/L CB (7572)","345kV 장문복합S/Y 건설공사","O T/L 보호반 설치 및 시험","2016-03-16 09:00","2016-03-25 18:00","2016-03-16 09:00","2016-03-25 18:00","연속",null,null,null,201601120079,"-"]
[43,"경기북부","파주","신덕은S/S 신덕은-장문CC #2T/L CB (7372)","345kV 장문복합S/Y 건설공사","O T/L 보호반 설치 및 시험","2016-03-16 09:00","2016-03-25 18:00","2016-03-16 09:00","2016-03-25 18:00","연속",null,null,null,201601120082,"-"]
[44,"경기북부","파주","신덕은S/S #3 M.Tr A","신덕은S/S #3M.Tr OLTC 누유관련 하자보수","신덕은S/S #3M.Tr OLTC 누유관련 제작사 하자보수(LS산전)","2016-03-03 09:00","2016-03-04 18:00","2016-03-03 09:00","2016-03-04 18:00","연속",null,null,null,201601120367,"-"]
[45,"경기북부","파주","신파주S/S 345kV #71 BUS","신파주S/S #71BUS 부분방전 보수","신파주S/S #71BUS 부분방전 보수","2016-03-07 10:00","2016-03-11 18:00","2016-03-07 10:00","2016-03-11 18:00","연속",null,null,null,201601130245,"-"]
[46,"경기북부","파주","신파주S/S 345kV #75 BUS","2016년 파주전력 362kV #2M.Tr 1차 GIS 정밀점검공사","2016년 파주전력 362kV #2M.Tr 1차 7352DS 정밀점검","2016-03-28 09:00","2016-03-29 18:00","2016-03-28 09:00","2016-03-29 18:00","연속",null,null,null,201601130250,"-"]
[47,"경기북부","파주","신파주S/S #2 M.Tr A","2016년 파주전력 362kV #2M.Tr 1차 GIS 정밀점검공사","2016년 파주전력 362kV #2M.Tr 1차 GIS 정밀점검공사","2016-03-28 09:00","2016-04-01 18:00","2016-03-28 09:00","2016-04-01 18:00","연속",null,null,null,201601130249,"-"]
[48,"경기북부","파주","신파주S/S 345kV #75 BUS","2016년 파주전력 362kV #1M.Tr 1차 GIS 정밀점검공사","2016년 파주전력 362kV #1M.Tr 1차 7252DS 정밀점검","2016-03-25 09:00","2016-03-26 18:00","2016-03-25 09:00","2016-03-26 18:00","연속",null,null,null,201601130251,"-"]
[49,"경기북부","파주","신파주S/S #1 M.Tr A","2016년 파주전력 362kV #1M.Tr 1차 GIS 정밀점검공사","2016년 파주전력 362kV #1M.Tr 1차 GIS 정밀점검공사","2016-03-21 09:00","2016-03-26 18:00","2016-03-21 09:00","2016-03-26 18:00","연속",null,null,null,201601130248,"-"]
[50,"경기북부","파주","신파주S/S 345kV #70 BUS","2016년 파주전력 362kV #1M.Tr 1차 GIS 정밀점검공사","2016년 파주전력 362kV #1M.Tr 1차 7251DS 정밀점검","2016-03-21 09:00","2016-03-22 18:00","2016-03-21 09:00","2016-03-22 18:00","연속",null,null,null,201601130252,"-"]
[51,"경기북부","파주","신파주S/S 345kV #70 BUS","2016년 파주전력 362kV 신파주-신덕은#1T/L GIS 정밀점검공사","2016년 파주전력 362kV 신파주-신덕은#1T/L 7151DS 정밀점검","2016-03-15 09:00","2016-03-16 18:00","2016-03-15 09:00","2016-03-16 18:00","연속",null,null,null,201601130247,"-"]
[52,"경기북부","파주","신파주신덕은#1 T/L","2016년 파주전력 362kV 신파주-신덕은#1T/L GIS 정밀점검공사","2016년 파주전력 362kV 신파주-신덕은#1T/L GIS 정밀점검공사","2016-03-15 09:00","2016-03-18 18:00","2016-03-15 09:00","2016-03-18 18:00","연속",null,null,null,201601130246,"-"]
[53,"경기","군포","화성서서울#2 T/L","345kV 화성서서울T/L 지장철탑이설공사 48호","345kV 화성서서울T/L 지장철탑이설공사 48호 #2T/L 철탑연긴선작업 (41~50호)","2016-03-28 07:00","2016-04-04 18:00","2016-03-28 07:00","2016-04-04 18:00","연속",null,null,null,201601120147,"-"]
[54,"경기","군포","화성서서울#2 T/L","345kV 화성서서울T/L 지장철탑이설공사 48호","345kV 화성서서울T/L 지장철탑이설공사 48호 본철탑 기초작업 #2T/L 안전이격 확보 (41~50호)","2016-03-07 07:00","2016-03-17 18:00","2016-03-07 07:00","2016-03-17 18:00","연속",null,null,null,201601120138,"-"]
[55,"경기","군포","화성서서울#1 T/L","345kV 화성서서울T/L 지장철탑이설공사 48호","345kV 화성서서울T/L 지장철탑이설공사 48호 #1T/L 가철탑이설(41~50호)","2016-03-03 07:00","2016-03-06 18:00","2016-03-03 07:00","2016-03-06 18:00","연속",null,null,null,201601120131,"-"]
[56,"경기","성남","신성남S/S STATCOM Tr","신성남S/S 345kV STATCOM Tr","신성남S/S 345kV STATCOM 1차 7000,7072 GIS, M.Tr 초기점검","2016-03-28 09:30","2016-03-29 18:00","2016-03-28 09:30","2016-03-29 18:00","연속",null,null,null,201601120102,"-"]
[57,"경기","성남","신용인S/S 신용인-동서울#1T/L GIS","신용인S/S 345kV 신용인-동서울#1T/L GIS 7371","신용인S/S 신용인-동서울#1T/L 7371 GIS 초기점검","2016-03-13 09:30","2016-03-13 18:00","2016-03-13 09:30","2016-03-13 18:00","당일",null,null,null,201601110491,"-"]
[58,"경기","성남","신용인S/S 신용인-동서울#1T/L-TIE GIS","신용인S/S 345kV 신용인-동서울#1T/L-TIE GIS 7300","신용인S/S 신용인-동서울#1T/L-TIE 7300 GIS 초기점검","2016-03-12 09:30","2016-03-12 18:00","2016-03-12 09:30","2016-03-12 18:00","당일",null,null,null,201601110492,"-"]
[59,"경기","직할","아산화성#2 T/L","345kV 아산-화성 외 1개T/L 지장철탑 이설공사","- No.59-No.62 관형주 3기 설치 후 3기 철거 병행작업 : 영인-청북간 도로개설공사관련 지장철탑 이설(No.65-71호)","2016-03-01 07:00","2016-03-08 18:00","2016-03-01 07:00","2016-03-08 18:00","연속",null,null,"신뢰도개선",201601130189,"-"]
[60,"경기","평택","평택T/P 평택#2C/C #1 G/T 1차 GIS","평택T/P 평택#2C/C #1 G/T 1차(7771) GIS 하자점검","평택T/P 평택#2C/C #1 G/T 1차(7771) GIS 하자점검","2016-03-19 09:00","2016-03-19 13:00","2016-03-19 09:00","2016-03-19 13:00","당일",null,null,null,201601110123,"-"]
[61,"경기","평택","평택T/P 평택T/P-평택#2C/C #1 G/T 1차 GIS","평택T/P-평택#2C/C #1 G/T 1차(7700) GIS 하자점검","평택T/P-평택#2C/C #1 G/T 1차(7700) GIS 하자점검","2016-03-19 13:00","2016-03-19 18:00","2016-03-19 13:00","2016-03-19 18:00","당일",null,null,null,201601110126,"-"]
[62,"경기","평택","평택T/P 평택#2C/C #2 G/T 1차 GIS","평택T/P 평택#2C/C #2 G/T 1차(7871) GIS 하자점검","평택T/P 평택#2C/C #2 G/T 1차(7871) GIS 하자점검","2016-03-20 09:00","2016-03-20 13:00","2016-03-20 09:00","2016-03-20 13:00","당일",null,null,null,201601110128,"-"]
[63,"경기","평택","평택T/P 평택#2C/C #1 S/T 1차 GIS","평택T/P 평택#2C/C #1 S/T 1차(7872) GIS 하자점검","평택T/P 평택#2C/C #1 S/T 1차(7872) GIS 하자점검","2016-03-26 09:00","2016-03-26 18:00","2016-03-26 09:00","2016-03-26 18:00","당일",null,null,null,201601110148,"-"]
[64,"경기","평택","평택T/P 평택#2C/C #2 G/T-#1 S/T 1차 GIS","평택#2C/C #2 G/T-#1 S/T 1차(7800) GIS 하자점검","평택#2C/C #2 G/T-#1 S/T 1차(7800) GIS 하자점검","2016-03-20 13:00","2016-03-20 18:00","2016-03-20 13:00","2016-03-20 18:00","당일",null,null,null,201601110130,"-"]
[65,"경기","군포","신온양서서울#2 T/L","345kV 아산-화성 등 2개T/L 지장철탑 이설공사","345kV 신온양-서서울T/L 지장철탑 이설 휴전작업 관형주 2기 설치 후 가선로 구성 3기 철거(No.28~No.31)","2016-03-31 07:00","2016-04-05 18:00","2016-03-31 07:00","2016-04-05 18:00","매일",null,null,null,201601280021,"-"]
[66,"강원","동해","동해S/S #2 M.Tr A","동해S/S 취약설비 GIS화 공사","- #2M.Tr 2차측 이설 - 2차측 상모선 철거 및 인출분기모선 설치 - 감시반 이설(신규설비)","2016-03-30 08:00","2016-04-02 18:00","2016-03-30 08:00","2016-04-02 18:00","연속",null,null,null,201601150043,"○"]
[67,"충북","직할","신제천신충주#2 T/L","16년 가공송전선로 순시점검 위탁공사(신제천-신충주#2T/L 정밀점검)","345KV 신제천-신충주#2T/L 정밀점검","2016-03-21 08:00","2016-04-01 18:00","2016-03-21 08:00","2016-04-01 18:00","매일",null,null,null,201601120358,"-"]
[68,"충북","직할","신제천신충주#1 T/L","16년 가공송전선로 순시점검 위탁공사(신제천-신충주#1T/L 정밀점검)","345KV 신제천-신충주#1T/L 정밀점검","2016-03-07 08:00","2016-03-18 18:00","2016-03-07 08:00","2016-03-18 18:00","매일",null,null,null,201601120357,"-"]
[69,"충북","청주","신옥천신남원#1 T/L","2016~17년 가공송전협력회사 총액공사","신계룡두마#2 T/L No.206,206-1,230 현수크람프 및 마로드 교체","2016-03-07 07:00","2016-03-08 18:00","2016-03-07 07:00","2016-03-08 18:00","매일",null,null,null,201601190026,"-"]
[70,"충북","청주","신옥천S/S #1 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-03-28 09:00","2016-03-30 18:00","2016-03-28 09:00","2016-03-30 18:00","연속",null,null,null,201512140043,"-"]
[71,"충북","청주","신옥천신남원#2 T/L","2016~17년 가공송전협력회사 총액공사","신계룡두마#2 T/L No.230,230-1 현수크람프 및 마로드 교체","2016-03-09 07:00","2016-03-10 18:00","2016-03-09 07:00","2016-03-10 18:00","매일",null,null,null,201601190028,"-"]
[72,"충북","청주","신옥천S/S #2 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-03-31 09:00","2016-04-02 18:00","2016-03-31 09:00","2016-04-02 18:00","연속",null,null,null,201512140044,"-"]
[73,"충북","청주","신옥천청원#2 T/L","345kV 세종분기T/L 건설공사","신설선로 연결","2016-03-11 08:00","2016-03-25 17:00","2016-03-11 08:00","2016-03-25 17:00","연속",null,null,null,201601130201,"-"]
[74,"대전충남","서산","북당진S/S 345kV #1 BUS","당진복합4호기용 345kV SW 증설공사","345kV 63kA 6300A * 4CB 증설 345kV 63kA 8000A Main Bus 증설 * 1식","2016-03-02 09:30","2016-03-08 17:30","2016-03-02 09:30","2016-03-08 17:30","연속",null,null,null,201601130205,"-"]
[75,"대전충남","아산","아산화성#1 T/L","345kV북당진-신탕정T/L 건설공사","아산화성#1T/L No.23~35 임시선로구성","2016-03-09 07:00","2016-03-19 18:00","2016-03-09 07:00","2016-03-19 18:00","연속",null,null,null,201601100005,"-"]
[76,"대전충남","아산","아산화성#2 T/L","345kV북당진-신탕정T/L 건설공사","아산화성#2T/L No.23~35 임시선로구성","2016-03-20 07:00","2016-03-30 18:00","2016-03-20 07:00","2016-03-30 18:00","연속",null,null,null,201601190137,"-"]
[77,"전북","군산","군산S/S #2 M.Tr A","345kV 군산S/S #2 M.Tr A","군산S/S M.Tr 3차측 절연보강공사 ○ 군산S/S M.Tr 3차측 절연보강공사 - 절연보강 : 99개소 ○ 군산S/S 주변압기용 43 PD SW 교체공사 - 장기사용 43PD 절체SW 교체 1식","2016-03-14 09:00","2016-03-15 18:00","취소","취소","연속",null,null,null,201512010053,"-"]
[78,"전북","군산","군산새만금3#1 T/L CB","군산S/S 군산-새만금#1T/L","군산P/O 345kV 차단기 정밀점검공사 7772,7700CB 차단기 정밀점검","2016-03-21 09:00","2016-04-01 18:00","2016-03-21 09:00","2016-04-01 18:00","연속",null,null,null,201601130234,"-"]
[79,"전북","군산","군산S/S #4 M.Tr A","345kV 군산S/S #4 M.Tr A","군산S/S M.Tr 3차측 절연보강공사 ○ 군산S/S M.Tr 3차측 절연보강공사 - 절연보강 : 24개소","2016-03-16 09:00","2016-03-17 18:00","2016-04-21 09:00","2016-04-22 18:00","연속",null,null,null,201601190059,"-"]
[80,"전북","군산","군산S/S #1 M.Tr A","345kV 군산S/S #1 M.Tr A","군산S/S M.Tr 3차측 절연보강공사 ○ 군산S/S M.Tr 3차측 절연보강공사 - 절연보강 : 102개소 ○ 군산S/S 주변압기용 43 PD SW 교체공사 - 장기사용 43PD 절체SW 교체 1식","2016-03-10 09:00","2016-03-11 18:00","취소","취소","연속",null,null,null,201512010054,"-"]
[81,"전북","군산","군산S/S #3 M.Tr A","345kV 군산S/S #3 M.Tr A","군산P/O 345kV 차단기 정밀점검공사 7772,7700CB 차단기 정밀점검","2016-03-21 09:00","2016-04-01 18:00","2016-03-21 09:00","2016-04-01 18:00","연속",null,null,null,201601130233,"-"]
[82,"전북","김제","신김제S/S #1 M.Tr A","신김제S/S #1 M.Tr A","변압기 보통점검 및 예비M.Tr 절체반 설치","2016-03-14 09:00","2016-03-16 18:00","취소","취소","연속",null,null,null,201601140090,"-"]
[83,"전북","김제","신김제S/S #3 M.Tr A","신김제S/S #3 M.Tr A","예비M.Tr 절체반 설치","2016-03-21 09:00","2016-03-22 18:00","취소","취소","연속",null,null,null,201601140092,"-"]
[84,"전북","김제","신김제S/S #4 M.Tr A","신김제S/S #4 M.Tr A","예비M.Tr 절체반 설치","2016-03-23 09:00","2016-03-24 18:00","취소","취소","연속",null,null,null,201601140093,"-"]
[85,"전북","김제","신김제S/S #2 M.Tr A","신김제S/S #2 M.Tr A","변압기 보통점검 및 예비M.Tr 절체반 설치","2016-03-17 09:00","2016-03-19 18:00","취소","취소","연속",null,null,null,201601140091,"-"]
[86,"전북","직할","신남원의령#2 T/L","345kV 신남원-의령#2T/L 지장철탑이설공사","전력선교체 : 2.8km (No.153~160호)","2016-03-15 08:00","2016-03-21 18:00","2016-03-15 08:00","2016-03-21 18:00","연속",null,null,null,201601110037,"-"]
[87,"광주전남","광주","신광주S/S #2 M.Tr A","신광주S/S 345kV #2M.Tr(변전총액공사)","- #2M.Tr A상 보통점검 - 4284,4286 VCB 점검 - 4275-1,4275-2 DS 점검 - 1,2,3차 LA, 1,3차 PT 점검","2016-03-10 09:00","2016-03-11 18:00","2016-03-10 09:00","2016-03-11 18:00","당일",null,null,null,201601120330,"-"]
[88,"광주전남","광주","신광주S/S #3 M.Tr A","신광주S/S #3 M.Tr (변전 협력회사공사)","신광주S/S #3 M.Tr 1차 GIS 초기점검, L 보통점검, 3차 DS 및 VCB 보통점검, #2S.Tr 보통점검","2016-03-07 09:00","2016-03-09 18:00","2016-03-07 09:00","2016-03-09 18:00","당일",null,null,null,201601120388,"-"]
[89,"광주전남","광주","신화순신강진#2 T/L","345kV 신화순신강진2T/L(광주변전총액)","신화순S/S 7971 C상 CB 대시포트 교체","2016-03-30 09:00","2016-03-30 18:00","2016-03-30 09:00","2016-03-30 18:00","당일",null,null,null,201601110166,"-"]
[90,"광주전남","광주","신화순신강진#1 T/L","345kV 신화순신강진1T/L(광주변전총액)","신화순S/S 7A71 A상 및 7A00 A상 CB 대시포트 교체","2016-03-29 09:00","2016-03-29 18:00","2016-03-29 09:00","2016-03-29 18:00","당일",null,null,null,201601110165,"-"]
[91,"광주전남","광주","신화순S/S #1 M.Tr A","신화순S/S #1 M.Tr (변전 협력회사공사)","신화순S/S #1M.Tr 2차 GIS 보통점검","2016-03-23 09:00","2016-03-23 18:00","2016-03-23 09:00","2016-03-23 18:00","당일",null,null,null,201601120389,"-"]
[92,"광주전남","순천","광양율촌CC T/L","345kV 광양-율촌CC T/L(송전정비 협력회사 총액공사)","2016~17년 송전정비 협력회사 총액공사 - 전력선 교체 : 77~84호, 2.631C-km","2016-03-28 07:00","2016-03-31 18:00","2016-03-28 07:00","2016-03-31 18:00","연속",null,null,null,201601140126,"-"]
[93,"광주전남","순천","광양S/S #1 M.Tr A","345kV 광양S/S #1M.Tr(순천 변전협력회사 총액공사)","2016년 순천 변전협력회사 총액공사 - 2차 GIS 보통점검 - 1,2,3차 LA 교체","2016-03-07 10:00","2016-03-08 18:00","2016-03-07 10:00","2016-03-08 18:00","연속",null,null,null,201601140138,"-"]
[94,"대구경북","경산","신경산S/S #1 M.Tr A","신경산S/S #1M.Tr 관련설비 보통점검","주변압기, 6144, LA(1, 2, 3차), 3차측 GPT 보통점검","2016-03-14 09:00","2016-03-15 18:00","2016-03-14 09:00","2016-03-15 18:00","연속",null,null,null,201601080078,"-"]
[95,"대구경북","경산","신경산S/S #4 M.Tr A","신경산S/S #4M.Tr 관련설비 보통점검","주변압기, 7600, 7672, 6444, LA, 3차 GPT 보통점검","2016-03-16 09:00","2016-03-17 18:00","2016-03-16 09:00","2016-03-17 18:00","연속",null,null,null,201601080079,"-"]
[96,"대구경북","경산","신경산대구#2 T/L","신경산S/S 신경산-대구#2T/L GIS 정밀점검","7200, 7271 CB 및 7291 EDS부 정밀점검","2016-03-21 09:00","2016-03-26 18:00","2016-03-21 09:00","2016-03-26 18:00","연속",null,null,null,201601080092,"-"]
[97,"대구경북","경산","울주신경산#1 T/L","345kV 울주-신경산#1T/L 송전용 피뢰기 설치","[송전팀]345kV 울주-신경산#1T/L 송전용 피뢰기 설치 [변전팀]관련설비 보통점검(7400, 7471, LA, PT)","2016-03-28 09:00","2016-04-12 18:00","2016-03-28 09:00","2016-04-12 18:00","연속",null,null,null,201601180087,"-"]
[98,"대구경북","경산","울주신경산#2 T/L","신경산S/S 345kV 울주-신경산#2T/L 관련설비 보통점검","7300, 7371 CB 보통점검 및 LA 하자점검, Line PT 보통점검 등","2016-03-10 09:00","2016-03-10 18:00","2016-03-10 09:00","2016-03-10 18:00","당일",null,null,null,201601080077,"-"]
[99,"대구경북","구미","선산S/S 345kV #2 BUS","345kV 선산S/S #4M.Tr 증설공사","345kV M.Tr * 1Bank 362kV GIS *2CCt 이설 362kV GIS *1CCt 설치 154kV GCB 1대 설치","2016-03-02 09:30","2016-03-07 18:00","2016-03-02 09:30","2016-03-07 18:00","연속",null,null,null,201601040080,"-"]
[100,"대구경북","구미","서대구선산#2 T/L","345kV 선산S/S #4M.Tr 증설공사","345kV M.Tr * 1Bank 362kV GIS *2CCt 이설 362kV GIS *1CCt 설치 154kV GCB 1대 설치","2016-03-03 09:30","2016-03-15 18:00","2016-03-03 09:30","2016-03-15 18:00","연속",null,null,null,201601040089,"-"]
[101,"대구경북","구미","선산S/S 345kV #1 BUS","345kV 선산S/S #4M.Tr 증설공사","345kV M.Tr * 1Bank 362kV GIS *2CCt 이설 362kV GIS *1CCt 설치 154kV GCB 1대 설치","2016-03-08 09:30","2016-03-15 18:00","2016-03-08 09:30","2016-03-15 18:00","연속",null,null,null,201601040087,"-"]
[102,"대구경북","구미","서대구선산#1 T/L","345kV 선산S/S #4M.Tr 증설공사","345kV M.Tr * 1Bank 362kV GIS *2CCt 이설 362kV GIS *1CCt 설치 154kV GCB 1대 설치","2016-03-10 09:30","2016-03-22 18:00","2016-03-10 09:30","2016-03-22 18:00","연속",null,null,null,201601040091,"-"]
[103,"대구경북","구미","선산S/S #1 M.Tr 1차 CB (7172)","선산S/S 345kV 7172 GIS 휴전","GIS 보통점검","2016-03-22 09:30","2016-03-22 18:00","2016-03-22 09:30","2016-03-22 18:00","당일",null,null,null,201601110062,"-"]
[104,"대구경북","구미","선산S/S 북대구-선산T/L-TIE CB (7300)","선산S/S 345kV 7300 GIS 휴전","GIS 보통점검","2016-03-23 09:30","2016-03-23 18:00","2016-03-23 09:30","2016-03-23 18:00","당일",null,null,null,201601110066,"-"]
[105,"대구경북","구미","북대구선산 T/L","선산S/S 345kV 7371 GIS 휴전","GIS 초기점검","2016-03-24 09:30","2016-03-24 18:00","2016-03-24 09:30","2016-03-24 18:00","당일",null,null,null,201601110059,"-"]
[106,"대구경북","구미","선산S/S TIE-#2 M.Tr 1차 CB (7400)","선산S/S 345kV 7400 GIS 휴전","GIS 보통점검","2016-03-25 09:30","2016-03-25 18:00","2016-03-25 09:30","2016-03-25 18:00","당일",null,null,null,201601110065,"-"]
[107,"대구경북","구미","선산신포항 T/L","선산S/S 345kV 7471 GIS 휴전","GIS 초기점검","2016-03-28 09:30","2016-03-28 18:00","2016-03-28 09:30","2016-03-28 18:00","당일",null,null,null,201601110060,"-"]
[108,"대구경북","영주","신태백한울NP2#1 T/L","345kV 한울2발S/Y 건설공사","인출단자 접속 및 송전선로 계통변경","2016-03-29 08:00","2016-04-03 18:00","2016-03-29 08:00","2016-04-03 18:00","연속",null,null,"신뢰도개선",201601120313,"-"]
[109,"대구경북","영주","신태백한울NP2#2 T/L","345kV 한울2발S/Y 건설공사","인출단자 접속 및 송전선로 계통변경","2016-03-23 08:00","2016-03-28 18:00","2016-03-23 08:00","2016-03-28 18:00","연속",null,null,"신뢰도개선",201601120311,"-"]
[110,"대구경북","영주","한울1NP-한울2NP#1 T/L","345kV 한울2발S/Y 건설공사","송전선 보호반 이설 및 인출단자 접속 송전선로 계통변경","2016-03-15 08:00","2016-03-22 18:00","2016-03-15 08:00","2016-03-22 18:00","연속",null,null,null,201601120307,"-"]
[111,"대구경북","영주","한울1NP-한울2NP#2 T/L","345kV 한울2발S/Y 건설공사","송전선 보호반 이설 및 인출단자 접속 송전선로 계통변경","2016-03-05 08:00","2016-03-14 18:00","2016-03-05 08:00","2016-03-14 18:00","연속",null,null,null,201601120306,"-"]
[112,"대구경북","영주","한울1NP-한울2NP#1 T/L","345kV 한울2발S/Y 건설공사","한울#6T/L용 일부 GIB 연결작업(안전이격)","2016-03-02 08:00","2016-03-04 18:00","2016-03-02 08:00","2016-03-04 18:00","연속",null,null,null,201601120303,"-"]
[113,"대구경북","칠곡","북대구S/S #1 M.Tr A","북대구S/S #1M.Tr 정밀점검","북대구S/S #1M.Tr 정밀점검","2016-03-07 09:00","2016-03-11 18:00","2016-03-07 09:00","2016-03-11 18:00","연속",null,null,null,201601120179,"-"]
[114,"대구경북","칠곡","북대구S/S #2 M.Tr A","북대구S/S #2M.Tr 정밀점검","북대구S/S #2M.Tr 정밀점검","2016-03-14 09:00","2016-03-18 18:00","2016-03-14 09:00","2016-03-18 18:00","연속",null,null,null,201601120180,"-"]
[115,"대구경북","포항","월성2N/P 월성#2T/L-#1 M.Tr 2차CB (7200)","월성S/Y 7200 CB 정밀점검","7200 CB 정밀점검","2016-03-02 10:00","2016-03-06 18:00","2016-03-02 10:00","2016-03-06 18:00","연속",null,null,null,201601180153,"-"]
[116,"대구경북","포항","월성2N/P #1 SS Tr 1차 CB (7671)","월성S/Y 7671 CB 정밀점검","7671 CB 정밀점검","2016-03-14 10:00","2016-03-17 18:00","2016-03-14 10:00","2016-03-17 18:00","연속",null,null,null,201601180154,"-"]
[117,"대구경북","포항","월성2N/P #1 M.Tr 2차CB (7272)","월성S/Y 7272 CB 정밀점검","7272 CB 정밀점검","2016-03-02 10:00","2016-03-06 18:00","2016-03-02 10:00","2016-03-06 18:00","연속",null,null,null,201601180152,"-"]
[118,"대구경북","영주","신영주S/S #3M.Tr A","신영주S/S 362kV GIS화 공사","○ 362kV GIS(77Bay) 현장 조립","2016-03-03 09:00","2016-03-12 18:00","2016-03-03 09:00","2016-03-12 18:00","연속",null,null,null,201601220126,"-"]
[119,"대구경북","영주","신영주S/S #1 M.Tr A","신영주S/S 362kV GIS화 공사","○ 362kV GIS(71Bay) 현장 조립","2016-03-13 09:00","2016-03-22 18:00","2016-03-13 09:00","2016-03-22 18:00","연속",null,null,null,201601220127,"-"]
[120,"부산울산","동부산","신양산S/S #2 M.Tr A","신양산S/S 6242DS측 과열개소 보수","신양산 6242DS측 과열개소 보수(#2M.Tr+#66BUS 접속부)","2016-03-07 09:30","2016-03-07 17:00","2016-03-07 09:30","2016-03-07 17:00","당일",null,null,null,201601120227,"-"]
[121,"부산울산","북부산","북부산신울산#2 T/L","16년 가공송전 협력업체 정비공사","100-104호 하단 이도조정 및 스페이서 교체공사","2016-03-21 07:30","2016-03-25 18:00","2016-03-21 07:30","2016-03-25 18:00","연속",null,null,null,201601070168,"-"]
[122,"부산울산","북부산","북부산신울산#1 T/L","16년 가공송전 협력업체 정비공사","64-64호 하단 및 100-104호 상중하단 이도조정 및 스페이서 교체 공사","2016-03-08 07:30","2016-03-18 18:00","2016-03-08 07:30","2016-03-18 18:00","연속",null,null,null,201601070167,"-"]
[123,"부산울산","울산","신온산S/S #3 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","C상 2차 부싱 과열개소 해소","2016-03-03 09:00","2016-03-03 18:00","2016-03-03 09:00","2016-03-03 18:00","당일",null,null,null,201601180038,"-"]
[124,"부산울산","울산","신온산S/S 신온산-울산TPT/L CB (7471)","2016-17년 울산전력지사 변전협력회사 총액공사","7471 GIS 보통점검","2016-03-10 09:00","2016-03-10 18:00","2016-03-10 09:00","2016-03-10 18:00","당일",null,null,null,201601110280,"-"]
[125,"부산울산","울산","신울산S/S #1 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","B,C상 초기점검, 7100,7172 GIS 하자점검","2016-03-08 08:00","2016-03-09 18:00","2016-03-08 08:00","2016-03-09 18:00","연속",null,null,null,201601110279,"-"]
[126,"부산울산","울산","신울산S/S #2 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","A상 붓싱 절연유채취","2016-03-02 09:00","2016-03-02 18:00","2016-03-02 09:00","2016-03-02 18:00","당일",null,null,null,201601110276,"-"]
[127,"부산울산","울산","신울산S/S #3 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","B,C상 하자점검, 7500,7571 GIS 하자점검, 437-1,2 GCB 보통점검","2016-03-22 08:00","2016-03-23 18:00","2016-03-22 08:00","2016-03-23 18:00","연속",null,null,null,201601110302,"○"]
[128,"부산울산","울산","신울산S/S 70-71 SEC CB (66-67-0)","2016-17년 울산전력지사 변전협력회사 총액공사","70-71-0 GIS 하자점검","2016-03-24 09:00","2016-03-24 18:00","2016-03-24 09:00","2016-03-24 18:00","당일",null,null,null,201601110286,"-"]
[129,"부산울산","울산","신울산S/S 75-76 SEC CB (66-67-0)","2016-17년 울산전력지사 변전협력회사 총액공사","75-76-0 GIS 하자점검","2016-03-25 09:00","2016-03-25 18:00","2016-03-25 09:00","2016-03-25 18:00","당일",null,null,null,201601110287,"-"]
[130,"부산울산","울산","신울산S/S 신울산-신온산#1T/L CB (7871)","2016-17년 울산전력지사 변전협력회사 총액공사","7871 GIS 하자점검","2016-03-29 09:00","2016-03-29 18:00","2016-03-29 09:00","2016-03-29 18:00","당일",null,null,null,201601110289,"-"]
[131,"부산울산","울산","신울산S/S 신온산-동울산#1T/L TIE CB (7800)","2016-17년 울산전력지사 변전협력회사 총액공사","7800 GIS 하자점검","2016-03-30 09:00","2016-03-30 18:00","2016-03-30 09:00","2016-03-30 18:00","당일",null,null,null,201601110290,"-"]
[132,"부산울산","울산","신울산S/S 동울산-신울산#1T/L CB (7872)","2016-17년 울산전력지사 변전협력회사 총액공사","7872 GIS 하자점검","2016-03-31 09:00","2016-03-31 18:00","2016-03-31 09:00","2016-03-31 18:00","당일",null,null,null,201601110291,"○"]
[133,"부산울산","울산","울주S/S 울주-고리NP#1T/L-TIE CB (7600)","2016-17년 울산전력지사 변전협력회사 총액공사","7600 GIS 보통점검","2016-03-16 09:00","2016-03-16 18:00","2016-03-16 09:00","2016-03-16 18:00","당일",null,null,null,201601110283,"-"]
[134,"부산울산","울산","울주S/S 울주-고리NP#2T/L-TIE CB (7500)","2016-17년 울산전력지사 변전협력회사 총액공사","7500 GIS 보통점검","2016-03-18 09:00","2016-03-18 18:00","2016-03-18 09:00","2016-03-18 18:00","당일",null,null,null,201601110285,"-"]
[135,"부산울산","울산","울주S/S 울주-고리NP#1T/L CB (7671)","2016-17년 울산전력지사 변전협력회사 총액공사","7671 GIS 보통점검","2016-03-15 09:00","2016-03-15 18:00","2016-03-15 09:00","2016-03-15 18:00","당일",null,null,null,201601110282,"-"]
[136,"경남","직할","신마산신김해#2 T/L","신마산신김해#2 T/L 초기점검(2016 가공송전선로 순시점검 위탁공사)","신마산신김해#2 T/L 초기점검(1~5,21,28~29호)","2016-03-16 08:30","2016-03-16 18:00","2016-03-16 08:30","2016-03-16 18:00","당일",null,null,null,201601080045,"-"]
[137,"경남","직할","신마산신김해#1 T/L","신마산신김해#1 T/L 초기점검(2016 가공송전선로 순시점검 위탁공사)","신마산신김해#1 T/L 초기점검(1~5,21,28~29호)","2016-03-14 08:30","2016-03-14 18:00","2016-03-14 08:30","2016-03-14 18:00","당일",null,null,null,201601080040,"-"]
[138,"경남","직할","신김해S/S #1 M.Tr A","신김해S/S #1M.Tr A, B상 누유보수","신김해S/S #1M.Tr A, B상 누유보수","2016-03-10 09:30","2016-03-12 17:30","2016-03-10 09:30","2016-03-12 17:30","연속",null,null,null,201601120040,"-"]
[139,"경남","진주","의령S/S 의령-산청양수#1T/L-TIE CB (7400)","345kV 7400 차단기 정밀점검","345kV 7400 차단기 정밀점검","2016-03-22 09:30","2016-03-24 18:30","2016-03-22 09:30","2016-03-24 18:30","연속",null,null,null,201601080067,"-"]
[140,"경남","진주","의령S/S 고령-의령#2T/L CB (7571)","345kV 7571 차단기 정밀점검","345kV 7571 차단기 정밀점검","2016-03-28 09:30","2016-03-30 18:30","2016-03-28 09:30","2016-03-30 18:30","연속",null,null,null,201601080070,"-"]
[141,"경남","진주","하동T/P 의령-하동TP#1T/L-#1M.Tr 1차 CB (7100)","345kV 7100 차단기 보통점검","345kV 7100 차단기 보통점검","2016-03-09 09:03","2016-03-09 18:30","2016-03-09 09:03","2016-03-09 18:30","당일",null,null,null,201601080064,"-"]
[142,"경남","진주","하동T/P TIE-#4 M.Tr 1차 CB (7400)","345kV 7400 차단기 보통점검","345kV 7400 차단기 보통점검","2016-03-10 09:30","2016-03-10 18:30","취소","취소","당일",null,null,null,201601080065,"-"]
[143,"경남","진주","하동T/P #4 M.Tr 1차 CB (7472)","345kV 7472 차단기 보통점검","345kV 7472 차단기 보통점검","2016-03-11 09:30","2016-03-11 18:30","취소","취소","당일",null,null,null,201601080066,"-"]
[144,"경남","통영","삼천포T/P #4 M.Tr 1차-TIE CB (7400)","삼천포T/P #4M.TR TIE CB(7400) 정밀점검","삼천포T/P #4M.TR TIE CB(7400) 정밀점검 - 삼천포화력 4호기 O/H 기간중 점검","2016-03-30 09:30","2016-03-31 18:30","2016-03-30 09:30","2016-03-31 18:30","연속",null,null,null,201601140055,"-"]
[145,"경남","통영","삼천포T/P #4 M.Tr 1차 CB (7471)","삼천포T/P #4M.TR CB(7471) 정밀점검","삼천포T/P #4M.TR CB(7471) 정밀점검 - 삼천포화력 4호기 O/H 기간중 점검","2016-03-28 09:30","2016-03-29 18:30","2016-03-28 09:30","2016-03-29 18:30","연속",null,null,null,201601140054,"-"]
[146,"경남","통영","신고성S/S #2 M.Tr A","신고성S/S #2M.TR 1차 LA 현수애자 설치 및 피뢰기 점검","신고성S/S #2M.TR 1차 LA 현수애자 설치 및 1,2차 피뢰기 점검 등","2016-03-17 09:30","2016-03-19 18:30","2016-03-17 09:30","2016-03-19 18:30","연속",null,null,null,201601110168,"-"]
[147,"경남","통영","신고성S/S #1 M.Tr A","신고성S/S #1M.TR 1차 LA 현수애자 설치 및 피뢰기 점검","신고성S/S #1M.TR 1차 LA 현수애자 설치 및 1,2차 피뢰기 점검 등","2016-03-14 09:30","2016-03-16 18:30","2016-03-14 09:30","2016-03-16 18:30","연속",null,null,null,201601110167,"-"]
[148,"경남","함안","북경남S/S TIE - 대구#1T/L GIS (7600)","북경남S/S 345kV 7600GIS 하자점검공사","북경남S/S 345kV 7600 GIS 하자점검","2016-03-02 09:30","2016-03-02 17:30","2016-03-02 09:30","2016-03-02 17:30","당일",null,null,null,201601080166,"-"]
[149,"경남","함안","북경남S/S 북경남-대구 #2T/L GIS (7572)","북경남S/S 345kV 7572GIS 하자점검공사","북경남S/S 345kV 7572 GIS 하자점검","2016-03-09 09:30","2016-03-09 17:30","2016-03-09 09:30","2016-03-09 17:30","당일",null,null,null,201601080173,"-"]
[150,"경남","함안","북경남S/S 북경남-대구 #1T/L GIS (7672)","북경남S/S 345kV 7672GIS 하자점검공사","북경남S/S 345kV 7672 GIS 하자점검","2016-03-03 09:30","2016-03-03 17:30","2016-03-03 09:30","2016-03-03 17:30","당일",null,null,null,201601080169,"-"]
[151,"경남","함안","북경남S/S #7 Sh.R","북경남S/S 345kV #7Sh.R 초기점검공사","북경남S/S 345kV #7Sh.R 초기점검","2016-03-15 09:30","2016-03-15 17:30","2016-03-15 09:30","2016-03-15 17:30","당일",null,null,null,201601080180,"-"]
[152,"경남","함안","북경남S/S #6 Sh.R","북경남S/S 345kV #6Sh.R 초기점검공사","북경남S/S 345kV #6Sh.R 초기점검","2016-03-11 09:30","2016-03-11 17:30","2016-03-11 09:30","2016-03-11 17:30","당일",null,null,null,201601080178,"-"]
[153,"경남","함안","북경남S/S TIE - 대구#2T/L GIS (7500)","북경남S/S 345kV 7500GIS 하자점검공사","북경남S/S 345kV 7500 GIS 하자점검","2016-03-08 09:30","2016-03-08 17:30","2016-03-08 09:30","2016-03-08 17:30","당일",null,null,null,201601080171,"-"]
[154,"경남","함안","북경남S/S 북경남-고령 #2T/L GIS (7772)","북경남S/S 345kV 7772GIS 하자점검공사","북경남S/S 345kV 7772 GIS 하자점검","2016-03-04 09:30","2016-03-04 17:30","2016-03-04 09:30","2016-03-04 17:30","당일",null,null,null,201601080170,"-"]
[155,"경남","함안","북경남S/S #5 Sh.R","북경남S/S 345kV #5Sh.R 초기점검공사","북경남S/S 345kV #5Sh.R 초기점검","2016-03-10 09:30","2016-03-10 17:30","2016-03-10 09:30","2016-03-10 17:30","당일",null,null,null,201601080177,"-"]
[156,"경남","함안","신마산S/S #5 M.Tr 1차 CB (7971)","신마산S/S 345kV 7971GCB 보통점검공사","신마산S/S 345kV 7971 GCB 보통점검","2016-03-22 09:30","2016-03-22 17:30","2016-03-22 09:30","2016-03-22 17:30","당일",null,null,null,201601080182,"-"]
[157,"경남","함안","신마산S/S #3 M.Tr 1차 CB (7972)","신마산S/S 345kV 7972GCB 보통점검공사","신마산S/S 345kV 7972 GCB 보통점검","2016-03-23 09:30","2016-03-23 17:30","2016-03-23 09:30","2016-03-23 17:30","당일",null,null,null,201601080183,"-"]
[158,"경남","함안","신마산S/S 의령-신마산#1T/L CB (7472)","신마산S/S 345kV 7472GCB 보통점검공사","신마산S/S 345kV 7472 GCB 보통점검","2016-03-17 09:30","2016-03-17 17:30","2016-03-17 09:30","2016-03-17 17:30","당일",null,null,null,201601080184,"-"]
[159,"경남","함안","신마산S/S 삼천포화력#1T/L-#4 M.Tr 1차 CB (7800)","신마산S/S 345kV 7800GCB 보통점검공사","신마산S/S 345kV 7800 GCB 보통점검","2016-03-18 09:30","2016-03-18 17:30","2016-03-18 09:30","2016-03-18 17:30","당일",null,null,null,201601080185,"-"]

{"sheet":"154송부","index":2,"n_rows":260,"n_cols":16,"rows_kept":260,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 3월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","금오상계#2 T/L","상계C/H 종단접속함 PD진단센서 설치","UWB PD진단센서 설치 12개","2016-03-30 09:00","2016-03-30 18:00","취소","취소","당일",null,null,null,201601130081,"-"]
[2,"서울","성동","금오상계#1 T/L","상계C/H 종단접속함 PD진단센서 설치","UWB PD진단센서 설치 12개","2016-03-29 09:00","2016-03-29 18:00","2016-03-28 09:00","2016-03-31 18:00","당일",null,null,null,201601130080,"-"]
[3,"서울","중부","동빙고반포#2 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","동빙고S/S 동빙고반포#2T/L(637) GIS 보통점검","2016-03-09 10:00","2016-03-09 17:00","취소","취소","당일",null,null,"신뢰도 개선",201601120199,"-"]
[4,"서울","중부","순화동빙고 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","동빙고S/S 순화동빙고T/L(627) GIS 보통점검","2016-03-11 10:00","2016-03-11 17:00","취소","취소","당일",null,null,"신뢰도 개선",201601120158,"-"]
[5,"서울","중부","동빙고반포#1 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","동빙고S/S 동빙고반포#1T/L(647) GIS 보통점검","2016-03-08 10:00","2016-03-08 17:00","취소","취소","당일",null,null,"신뢰도 개선",201601120198,"-"]
[6,"서울","중부","동빙고S/S 154kV #2 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","동빙고S/S 154kV CPD반 대체공사","2016-03-09 10:00","2016-03-09 18:00","취소","취소","당일",null,null,"신뢰도 개선",201601180040,"-"]
[7,"서울","중부","동빙고S/S 154kV #1 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","동빙고S/S 154kV CPD반 대체공사","2016-03-08 10:00","2016-03-08 18:00","취소","취소","당일",null,null,"신뢰도 개선",201601180039,"-"]
[8,"서울","중부","중부용산#1 T/L","2016년 중부전력지사 170kV GIS 정밀점검","용산S/S 중부용산#1T/L GIS(627) 정밀점검","2016-03-21 08:00","2016-03-23 14:00","2016-03-21 08:00","2016-03-23 14:00","연속",null,null,null,201601110407,"-"]
[9,"서울","중부","중부용산#2 T/L","2016년 중부전력지사 170kV GIS 정밀점검","용산S/S 중부용산#2T/L GIS(637) 정밀점검","2016-03-23 14:00","2016-03-25 18:00","2016-03-23 14:00","2016-03-25 18:00","연속",null,null,null,201601110408,"-"]
[10,"서울","중부","용산동빙고 T/L","2016년 중부전력지사 170kV GIS 정밀점검","용산S/S 용산동빙고T/L GIS(617) 정밀점검","2016-03-28 08:00","2016-03-30 14:00","2016-03-28 08:00","2016-03-30 14:00","연속",null,null,null,201601110402,"-"]
[11,"서울","직할","마포신촌 T/L","신촌S/S 154kV 장기사용 GIS 대체","마포신촌T/L GIS 대체","2016-03-03 09:30","2016-03-31 18:00","2016-03-03 09:30","2016-03-31 18:00","연속",null,null,null,201601110115,"-"]
[12,"남서울","강남","역삼대치#2 T/L","지하(복합)변전소 인출구간 OF케이블 선종교체공사","가. 공사구간 ○ 154㎸ 신양재-역삼T/L : 역삼S/S∼J/B#13-1(3C×0.210㎞, 전력구) ○ 154㎸ 역삼-대치T/L : 역삼S/S∼J/B#14 (2C×0.319㎞, 전력구+관로) ○ 154㎸ 역삼-대치T/L : 대치S/S∼J/B#20 (2C×0.625㎞, 전력구+관로) 나. 케이블 포설 : 154㎸ XLPE 1,200㎟ × 2회","2016-03-02 10:00","2016-04-12 10:00","2016-03-07 10:00","2016-04-13 10:00","연속",null,null,null,201601040007,"-"]
[13,"남서울","동서울","동서울가락#2 T/L","동서울-가락#2 T/L 170kV GIS 정밀점검","동서울-가락#2 T/L 170kV GIS 정밀점검","2016-03-14 09:00","2016-03-16 14:00","2016-03-14 09:00","2016-03-16 14:00","연속",null,null,null,201601180102,"-"]
[14,"남서울","동서울","동서울가락#1 T/L","동서울-가락#1 T/L 170kV GIS 정밀점검","동서울-가락#1 T/L 170kV GIS 정밀점검 보호배전반 교체","2016-03-16 14:00","2016-03-18 18:00","2016-03-16 14:00","2016-03-18 18:00","연속",null,null,null,201601180103,"-"]
[15,"남서울","동서울","동서울신장#2 T/L","2016년 정밀점검 및 아킹혼철거","2016년 가공송전선로 순시점검 위탁공사 - 154kV 동서울-신장#2T/L 21기 - 정밀점검 - 내장애자련 아킹혼 철거","2016-03-17 08:00","2016-03-19 18:00","2016-03-17 08:00","2016-03-19 18:00","연속",null,null,null,201601120164,"-"]
[16,"남서울","동서울","동서울신장#1 T/L","2016년 피뢰기 설치 및 정밀점검","2016년 가공송전 협력 및 위탁공사 - 154kV 동서울-신장#1T/L 21기 - 피뢰기 설치공사(협력) - 정밀점검(위탁)","2016-03-10 08:00","2016-03-12 18:00","2016-03-10 08:00","2016-03-12 18:00","연속",null,null,null,201601120134,"-"]
[17,"남서울","동서울","동서울송파#2 T/L","동서울-송파#2 T/L T/L 170kV GCB 교체공사","동서울-송파#2 T/L T/L 170kV GCB 교체공사","2016-03-28 09:00","2016-04-01 18:00","취소","취소","연속",null,null,null,201601120412,"-"]
[18,"남서울","동서울","천호구의#2 T/L","154kV 천호-구의T/L 천호대교 횡단구간 교체공사","○ 공사위치 : 천호대교 교량하부 ○ 공사구간 : 154㎸ 천호-구의T/L J/B#5〜#8(1-1) ○ 선종 및 길이 : 154㎸ XLPE 2,000㎟ × 2회선, 1.174㎞ ○ 케이블 접속 : 보통접속2개소","2016-03-02 09:00","2016-05-31 18:00","2016-03-02 09:00","2016-05-31 18:00","연속",null,null,null,201601080093,"-"]
[19,"남서울","영서","화곡가양#2 T/L","154kV 마곡분기 지중T/L 건설공사","ㅇ 선종/긍장 : 154kV XLPE 2000㎟ , 2C-0.6km ㅇ 공사구간 : 신설 154kV 마곡S/S ~ 기설 M/H#3[화곡-가양 지중T/L] ㅇ 관련공사 : 마곡S/S 및 전력구 건설공사, 화곡-가양 지중T/L 이설공사","2016-03-02 09:00","2016-03-30 18:00","취소","취소","연속",null,null,"신뢰도 개선",201601120118,"-"]
[20,"남서울","영서","대방신길#1 T/L","대방-신길#1T/L 보호배전반 정기점검","대방-신길#1T/L 보호배전반 정기점검","2016-03-31 10:30","2016-03-31 12:00","2016-03-31 10:30","2016-03-31 12:00","당일",null,null,null,201601040086,"-"]
[21,"남서울","영서","대방신길#2 T/L","대방-신길#2T/L 보호배전반 정기점검","대방-신길#2T/L 보호배전반 정기점검","2016-03-31 13:00","2016-03-31 14:30","2016-03-31 13:00","2016-03-31 14:30","당일",null,null,null,201601040088,"-"]
[22,"남서울","영서","독산대방#2 T/L","독산-대방#2T/L 보호배전반 정기점검","독산-대방#2T/L 보호배전반 정기점검","2016-03-24 14:00","2016-03-24 18:00","취소","취소","당일",null,null,"신뢰도 개선",201601040059,"-"]
[23,"남서울","영서","독산대방#1 T/L","독산-대방#1T/L 보호배전반 정기점검","독산-대방#1T/L 보호배전반 정기점검","2016-03-24 10:30","2016-03-24 14:00","취소","취소","당일",null,null,"신뢰도 개선",201601040058,"-"]
[24,"남서울","영서","봉천신길#2 T/L","봉천-신길#2T/L 보호배전반 정기점검","봉천-신길#2T/L 보호배전반 정기점검","2016-03-31 16:30","2016-03-31 18:00","2016-03-31 16:30","2016-03-31 18:00","당일",null,null,null,201601040092,"-"]
[25,"남서울","영서","봉천신길#1 T/L","봉천-신길#1T/L 보호배전반 정기점검","봉천-신길#1T/L 보호배전반 정기점검","2016-03-31 15:00","2016-03-31 16:30","2016-03-31 15:00","2016-03-31 16:30","당일",null,null,null,201601040090,"-"]
[26,"남서울","영서","사당S/S 154kV #2 BUS","170kV GIS 정밀점검(#3M.Tr 1차, 신양재-사당#2T/L)","- 170kV GIS 정밀점검(#3M.Tr 1차, 신양재-사당#2T/L)","2016-03-10 09:00","2016-03-11 13:00","2016-03-10 09:00","2016-03-11 13:00","연속",null,null,null,201601120286,"-"]
[27,"남서울","영서","사당S/S 154kV #1 BUS","170kV GIS 정밀점검(#3M.Tr 1차, 신양재-사당#2T/L)","- 170kV GIS 정밀점검(#3M.Tr 1차, 신양재-사당#2T/L)","2016-03-11 13:00","2016-03-12 18:00","2016-03-11 13:00","2016-03-12 18:00","연속",null,null,null,201601120296,"-"]
[28,"남서울","영서","사당S/S 154kV #2 BUS","170kV GIS 정밀점검(#4M.Tr 1차, 신성남-사당#1T/L)","- 170kV GIS 정밀점검(#4M.Tr 1차, 신성남-사당#1T/L)","2016-03-14 09:00","2016-03-15 13:00","2016-03-14 09:00","2016-03-15 13:00","연속",null,null,null,201601120287,"-"]
[29,"남서울","영서","사당S/S 154kV #1 BUS","170kV GIS 정밀점검(#4M.Tr 1차, 신성남-사당#1T/L)","- 170kV GIS 정밀점검(#4M.Tr 1차, 신성남-사당#1T/L)","2016-03-15 13:00","2016-03-16 18:00","2016-03-15 13:00","2016-03-16 18:00","연속",null,null,null,201601120297,"-"]
[30,"남서울","영서","사당S/S 154kV #2 BUS","170kV GIS 정밀점검(#5M.Tr 1차, 신성남-사당#2T/L)","- 170kV GIS 정밀점검(#5M.Tr 1차, 신성남-사당#2T/L)","2016-03-17 09:00","2016-03-18 13:00","2016-03-17 09:00","2016-03-18 13:00","연속",null,null,null,201601120289,"-"]
[31,"남서울","영서","사당S/S 154kV #1 BUS","170kV GIS 정밀점검(#5M.Tr 1차, 신성남-사당#2T/L)","- 170kV GIS 정밀점검(#5M.Tr 1차, 신성남-사당#2T/L)","2016-03-18 13:00","2016-03-19 18:00","2016-03-18 13:00","2016-03-19 18:00","연속",null,null,null,201601120299,"-"]
[32,"남서울","영서","사당S/S 154kV #2 BUS","170kV GIS 정밀점검(BUS-TIE, 사당-신림T/L)","- 170kV GIS 정밀점검(BUS-TIE, 사당-신림T/L)","2016-03-21 09:00","2016-03-22 13:00","2016-03-21 09:00","2016-03-22 13:00","연속",null,null,null,201601120292,"-"]
[33,"남서울","영서","사당신림 T/L","170kV GIS 정밀점검(BUS-TIE, 사당-신림T/L)","- 170kV GIS 정밀점검(BUS-TIE, 사당-신림T/L)","2016-03-21 09:00","2016-03-23 18:00","2016-03-21 09:00","2016-03-23 18:00","연속",null,null,null,201601120325,"-"]
[34,"남서울","영서","사당S/S 154kV #1 BUS","170kV GIS 정밀점검(BUS-TIE, 사당-신림T/L)","- 170kV GIS 정밀점검(BUS-TIE, 사당-신림T/L)","2016-03-22 13:00","2016-03-23 18:00","2016-03-22 13:00","2016-03-23 18:00","연속",null,null,null,201601120300,"-"]
[35,"남서울","영서","사당S/S 154kV #2 BUS","170kV GIS 정밀점검(#1M.Tr 1차, 사당-봉천#1T/L)","170kV GIS 정밀점검(#1M.Tr 1차, 사당-봉천#1T/L)","2016-03-02 09:00","2016-03-03 13:00","2016-03-28 09:00","2016-03-29 13:00","연속",null,null,null,201601120003,"-"]
[36,"남서울","영서","사당봉천#1 T/L","170kV GIS 정밀점검(#1M.Tr 1차, 사당-봉천#1T/L)","170kV GIS 정밀점검(#1M.Tr 1차, 사당-봉천#1T/L) - 송전선로보호반 교체","2016-03-02 09:00","2016-03-04 18:00","2016-03-28 09:00","2016-03-30 18:00","연속",null,null,null,201601120002,"-"]
[37,"남서울","영서","사당S/S 154kV #2 BUS","170kV GIS 정밀점검(#2M.Tr 1차, 신양재-사당#1T/L)","- 170kV GIS 정밀점검(#2M.Tr 1차, 신양재-사당#1T/L)","2016-03-07 09:00","2016-03-08 13:00","2016-03-07 09:00","2016-03-08 13:00","연속",null,null,null,201601120283,"-"]
[38,"남서울","영서","사당S/S 154kV #1 BUS","170kV GIS 정밀점검(#2M.Tr 1차, 신양재-사당#1T/L)","- 170kV GIS 정밀점검(#2M.Tr 1차, 신양재-사당#1T/L)","2016-03-08 13:00","2016-03-09 18:00","2016-03-08 13:00","2016-03-09 18:00","연속",null,null,null,201601120295,"-"]
[39,"남서울","영서","사당S/S 154kV #1 BUS","170kV GIS 정밀점검(#1M.Tr 1차, 사당-봉천#1T/L)","170kV GIS 정밀점검(#1M.Tr 1차, 사당-봉천#1T/L)","2016-03-03 13:00","2016-03-04 18:00","2016-03-29 13:00","2016-03-30 18:00","연속",null,null,null,201601120005,"-"]
[40,"남서울","직할","교대이수#1 T/L","154kV 교대-이수T/L 지중선로 이설공사(방배로 1구간)","배경: 서초구청 시행 하수암거 설치에 따른 지중선로 이설 개요: 154KV 교대-이수T/L J/B#7~8, #9~10 (2구간, 0.66KM) XLPE1200 * 2회선","2016-03-07 09:00","2016-04-04 18:00","2016-03-07 09:00","2016-04-04 18:00","연속",null,null,null,201601050035,"-"]
[41,"인천","김포","경서S/S 신경서경서#2T/L GIS","경서S/S 신경서경서#2T/L GIS 장기미동작 차단기 점검","경서S/S 신경서경서#2T/L GIS 장기미동작 차단기 점검","2016-03-03 09:00","2016-03-03 18:00","2016-03-03 09:00","2016-03-03 18:00","당일",null,null,null,201601130274,"-"]
[42,"인천","김포","양촌양곡#1 T/L","154kV 양촌-양곡T/L No.13 지장철탑 이설공사","□ 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.13 이설 - No.13 본철탑 이설","2016-03-21 07:00","2016-03-23 18:00","2016-03-21 07:00","2016-03-23 18:00","연속",null,null,"신뢰도 개선",201601180066,"-"]
[43,"인천","김포","양촌양곡#2 T/L","154kV 양촌-양곡T/L No.13 지장철탑 이설공사","□ 제 2외곽순환도로 조성에 따른 지장철탑 이설 □ 공사개요 : 154kV 양촌-양곡T/L No.13 이설 - No.13 본철탑 이설","2016-03-18 07:00","2016-03-20 18:00","2016-03-18 07:00","2016-03-20 18:00","연속",null,null,"신뢰도 개선",201601180065,"-"]
[44,"인천","김포","장기S/S 신김포-장기#2T/L GIS","장기S/S 신김포-장기#2T/L GIS 기기점검","장기S/S 신김포-장기#2T/L GIS 기기점검","2016-03-11 09:00","2016-03-11 18:00","2016-03-11 09:00","2016-03-11 18:00","당일",null,null,"신뢰도 개선",201601130292,"-"]
[45,"인천","김포","장기S/S 김포-장기#1T/L GIS","장기S/S 김포-장기#1T/L GIS 기기점검","장기S/S 김포-장기#1T/L GIS 기기점검","2016-03-08 09:00","2016-03-08 18:00","2016-03-08 09:00","2016-03-08 18:00","당일",null,null,null,201601130286,"-"]
[46,"인천","김포","장기S/S 김포-장기#2T/L GIS","장기S/S 김포-장기#2T/L GIS 기기점검","장기S/S 김포-장기#2T/L GIS 기기점검","2016-03-09 09:00","2016-03-09 18:00","2016-03-09 09:00","2016-03-09 18:00","당일",null,null,null,201601130288,"-"]
[47,"인천","김포","장기S/S 신김포-장기#1T/L GIS","장기S/S 신김포-장기#1T/L GIS 기기점검","장기S/S 신김포-장기#1T/L GIS 기기점검","2016-03-10 09:00","2016-03-10 18:00","2016-03-10 09:00","2016-03-10 18:00","당일",null,null,"신뢰도 개선",201601130290,"-"]
[48,"인천","인천","관교만수 T/L","관교,만수S/S 관교만수T/L 차단기 조작 시험","관교,만수S/S 관교만수T/L 차단기 조작 시험","2016-03-11 09:00","2016-03-11 18:00","2016-03-11 09:00","2016-03-11 18:00","당일",null,null,null,201601180025,"-"]
[49,"인천","인천","남인천학익#1 T/L","남인천S/S 남인천학익#1T/L GIS 보통점검 및 보조계전기 교체","남인천S/S 남인천학익#1T/L GIS 보통점검 및 보조계전기 교체","2016-03-02 09:00","2016-03-02 18:00","2016-03-02 09:00","2016-03-02 18:00","당일",null,null,null,201601180018,"-"]
[50,"인천","인천","남인천학익#2 T/L","남인천S/S 남인천학익#2T/L GIS 보통점검 및 보조계전기 교체","남인천S/S 남인천학익#2T/L GIS 보통점검 및 보조계전기 교체","2016-03-08 09:00","2016-03-08 18:00","2016-03-08 09:00","2016-03-08 18:00","당일",null,null,null,201601180019,"-"]
[51,"인천","인천","인천남인천#1 T/L","남인천S/S 인천남인천#1T/L GIS 보통점검 및 보조계전기 교체","남인천S/S 인천남인천#1T/L GIS 보통점검 및 보조계전기 교체","2016-03-03 09:00","2016-03-03 18:00","2016-03-03 09:00","2016-03-03 18:00","당일",null,null,null,201601180016,"-"]
[52,"인천","인천","인천남인천#2 T/L","남인천S/S 인천남인천#2T/L GIS 보통점검 및 보조계전기 교체","남인천S/S 인천남인천#2T/L GIS 보통점검 및 보조계전기 교체","2016-03-04 09:00","2016-03-04 18:00","2016-03-04 09:00","2016-03-04 18:00","당일",null,null,null,201601180017,"-"]
[53,"인천","인천","경서북인천#1 T/L","북인천S/S 경서북인천#1T/L GIS 하자점검","북인천S/S 경서북인천#1T/L GIS 하자점검","2016-03-25 09:00","2016-03-25 18:00","2016-03-25 09:00","2016-03-25 18:00","당일",null,null,null,201601180020,"-"]
[54,"인천","인천","신가좌인천#3 T/L","신가좌S/S 신가좌인천#3T/L GIS 보통점검 및 보조계전기 교체","신가좌S/S 신가좌인천#3T/L GIS 보통점검 및 보조계전기 교체","2016-03-24 09:00","2016-03-24 18:00","2016-03-24 09:00","2016-03-24 18:00","당일",null,null,null,201601180022,"-"]
[55,"인천","인천","인천CC포스코CC#1 T/L","인천CCS/Y 인천CC포스코CC#1T/L 차단기 조작 시험","인천CCS/Y 인천CC포스코CC#1T/L 차단기 조작 시험","2016-03-29 10:00","2016-03-29 12:00","2016-03-29 10:00","2016-03-29 12:00","당일",null,null,null,201601180028,"-"]
[56,"인천","인천","인천CC포스코CC#2 T/L","인천CCS/Y 인천CC포스코CC#2T/L 차단기 조작 시험","인천CCS/Y 인천CC포스코CC#2T/L 차단기 조작 시험","2016-03-29 13:00","2016-03-29 15:00","2016-03-29 13:00","2016-03-29 15:00","당일",null,null,null,201601180029,"-"]
[57,"인천","인천","인천CC북인천#1 T/L","인천CCS/Y, 북인천S/S 인천CC북인천#1T/L 차단기 조작 시험","인천CCS/Y, 북인천S/S 인천CC북인천#1T/L 차단기 조작 시험","2016-03-30 10:00","2016-03-30 12:00","2016-03-30 10:00","2016-03-30 12:00","당일",null,null,null,201601180030,"-"]
[58,"인천","인천","인천CC북인천#2 T/L","인천CCS/Y, 북인천S/S 인천CC북인천#2T/L 차단기 조작 시험","인천CCS/Y, 북인천S/S 인천CC북인천#2T/L 차단기 조작 시험","2016-03-30 13:00","2016-03-30 15:00","2016-03-30 13:00","2016-03-30 15:00","당일",null,null,null,201601180031,"-"]
[59,"인천","직할","신부평고강#2 T/L","154kV 신부평-고강T/L M/H#9~M/H#10 이설공사","서울특별시에서 시행하는 남부순환로~오정대로 도로개설공사에 지장된는 154kV 신부평-고강T/L 지장이설 필요 - 이설구간 : 154kV 신부평-고강T/L M/H#9~M/H#10 (약 0.3km)","2016-03-21 09:00","2016-04-14 18:00","2016-03-21 09:00","2016-04-14 18:00","연속",null,null,null,201601050180,"-"]
[60,"인천","직할","신가좌부개#1 T/L","절연유 시료채취(154kV 신가좌-부개#1T/L)","시행근거 : 지중송전운영업무기준(제22차) 대상선로 : 154kV 신가좌-부개#1T/L 시행내용 : OF케이블 내 절연유 채취","2016-03-07 09:00","2016-03-08 18:00","2016-03-07 09:00","2016-03-08 18:00","연속",null,null,null,201601080117,"-"]
[61,"인천","직할","신가좌부개#2 T/L","절연유 시료채취(154kV 신가좌-부개#2T/L)","시행근거 : 지중송전운영업무기준(제22차) 대상선로 : 154kV 신가좌-부개#2T/L 시행내용 : OF케이블 내 절연유 채취","2016-03-09 09:00","2016-03-10 18:00","2016-03-09 09:00","2016-03-10 18:00","연속",null,null,null,201601080123,"-"]
[62,"인천","직할","중동화곡#2 T/L","No.8~14 철탑 가공지선 교체공사","No.8~14 철탑 가공지선 교체공사","2016-03-01 09:00","2016-03-01 18:00","2016-03-01 09:00","2016-03-01 18:00","당일",null,null,null,201601150143,"-"]
[63,"인천","직할","중동화곡#1 T/L","No.8~14 철탑 가공지선 교체공사","No.8~14 철탑 가공지선 교체공사","2016-03-01 09:00","2016-03-01 18:00","2016-03-01 09:00","2016-03-01 18:00","당일",null,null,null,201601150142,"-"]
[64,"경기북부","구리","덕소별내#2 T/L","구리갈매지구 송전선로 지중화공사","ㅇ No.31(C/H) 및 No.35(C/H)지중화를 위한 Cable 연결작업 ㅇ No.31 ~ 35호간 기설선로 철거","2016-03-29 09:00","2016-04-18 18:00","2016-03-29 09:00","2016-04-18 18:00","연속",null,null,"신뢰도 개선",201601060088,"○"]
[65,"경기북부","구리","덕소별내#1 T/L","구리갈매지구 송전선로 지중화공사","ㅇ No.31(C/H) 및 No.35(C/H)지중화를 위한 Cable 연결작업 ㅇ No.31 ~ 35호간 기설선로 철거","2016-03-08 09:00","2016-03-28 18:00","2016-03-08 09:00","2016-03-28 18:00","연속",null,null,"신뢰도 개선",201601060087,"○"]
[66,"경기북부","구리","미금화양 T/L","남양주 가운지금지구 지장송전선로 지중화공사","송전선로 지중화 2.2km","2016-03-28 08:00","2016-04-17 18:00","2016-03-28 08:00","2016-04-17 18:00","연속",null,null,"신뢰도 개선",201601130018,"-"]
[67,"경기북부","구리","미금화양 T/L","남양주 가운지금지구 지장송전선로 지중화공사","송전선로 지중화 2.2km","2016-03-04 08:00","2016-03-06 18:00","2016-03-04 08:00","2016-03-06 18:00","연속",null,null,"신뢰도 개선",201601130014,"-"]
[68,"경기북부","구리","미금광장 T/L","남양주 가운지금지구 지장송전선로 지중화공사","송전선로 지중화 2.2km","2016-03-07 08:00","2016-03-27 18:00","2016-03-07 08:00","2016-03-27 18:00","연속",null,null,null,201601130017,"-"]
[69,"경기북부","구리","마석청평HP#1 T/L","청평H/P 154kV 마석-청평HPT/L GIS 유압계통 누유 보수","170kV 마석-청평HP#1T/L GIS 유압계통 누유 보수","2016-03-04 09:00","2016-03-04 14:00","2016-03-04 09:00","2016-03-04 14:00","당일",null,null,null,201601110511,"○"]
[70,"경기북부","구리","마석청평HP#2 T/L","청평H/P 154kV 마석-청평HPT/L GIS 유압계통 누유 보수","170kV 마석-청평HP#2T/L GIS 유압계통 누유 보수","2016-03-04 14:00","2016-03-04 18:00","2016-03-04 14:00","2016-03-04 18:00","당일",null,null,null,201601110514,"○"]
[71,"경기북부","구리","동서울청평PP#1 T/L","154kV 동서울-청평PP #1T/L 불량압축인류크램프 교체공사","ㅇ 불량압축인류크램프 교체공사","2016-03-07 08:00","2016-03-11 18:00","2016-03-07 08:00","2016-03-11 18:00","연속",null,null,null,201601120331,"-"]
[72,"경기북부","구리","동서울청평PP#2 T/L","154kV 동서울-청평PP #2T/L 불량압축인류크램프 교체공사","ㅇ 불량압축인류크램프 교체공사","2016-03-14 08:00","2016-03-16 18:00","2016-03-14 08:00","2016-03-16 18:00","연속",null,null,null,201601120332,"-"]
[73,"경기북부","직할","신포천동두천#2 T/L","신포천동두천#2 T/L","SA시범사업 설비 철거공사 - GIS LCP PNL 교체","2016-03-28 10:00","2016-04-01 18:00","2016-03-28 10:00","2016-04-01 18:00","연속",null,null,null,201601130053,"-"]
[74,"경기북부","직할","신의정부용현#1 T/L","154kV 신의정부-용현#1T/L 보호반 경보회로 개선","- 보호계전기 주보호정지, Com Fail 경보회로 개선","2016-03-08 09:00","2016-03-08 18:00","2016-03-08 09:00","2016-03-08 18:00","당일",null,null,null,201512180148,"-"]
[75,"경기북부","파주","일산지도#2 T/L","고양시 국도대체 우회도로 이설공사","ㅇ 철탑(관형주) 2기 설치 및 철거 ㅇ 전력선교체 : No.11 ~ 13호간","2016-03-22 08:00","2016-03-26 18:00","2016-03-22 08:00","2016-03-26 18:00","연속",null,null,null,201601060089,"-"]
[76,"경기북부","파주","일산S/S 65-66-0 SEC CB","일산S/S 65-66-0CB 보통점검(변전협력회사 총액공사)","일산S/S 65-66-0 SEC CB 실리콘루버히터 설치","2016-03-03 10:00","2016-03-03 18:00","2016-03-03 10:00","2016-03-03 18:00","당일",null,null,null,201601130270,"-"]
[77,"경기북부","파주","일산지도#1 T/L","고양시 국도대체 우회도로 이설공사","ㅇ 철탑(관형주) 2기 설치 및 철거 ㅇ 전력선교체 : No.11 ~ 13호간","2016-03-27 08:00","2016-03-31 18:00","2016-03-27 08:00","2016-03-31 18:00","연속",null,null,null,201601060090,"-"]
[78,"경기","군포","관양평촌#1 T/L","관양,평촌S/S 154kV 관양평촌#1TL 기기점검 공사","관양,평촌S/S 154kV 관양평촌#1TL 기기점검 공사","2016-03-07 09:00","2016-03-07 18:00","2016-03-07 09:00","2016-03-07 18:00","당일",null,null,null,201601060130,"-"]
[79,"경기","군포","관양동안양#2 T/L","관양,평촌S/S 154kV 관양동안양#2TL 기기점검 공사","관양,평촌S/S 154kV 관양동안양#2TL 기기점검 공사","2016-03-05 09:00","2016-03-05 18:00","2016-03-05 09:00","2016-03-05 18:00","당일",null,null,null,201601060128,"-"]
[80,"경기","군포","관양동안양#1 T/L","관양S/S 154kV 관양동안양#1TL 기기점검 공사","관양S/S 154kV 관양동안양#1TL 기기점검 공사","2016-03-04 09:00","2016-03-04 18:00","2016-03-04 09:00","2016-03-04 18:00","당일",null,null,null,201601060126,"-"]
[81,"경기","군포","관양평촌#2 T/L","관양S/S 154kV 관양평촌#2TL 기기점검 공사","관양S/S 154kV 관양평촌#2TL 기기점검 공사","2016-03-08 09:00","2016-03-08 18:00","2016-03-08 09:00","2016-03-08 18:00","당일",null,null,null,201601060133,"-"]
[82,"경기","군포","신안산남안산#2 T/L","남안산S/S 154kV 신안산남안산#2TL 기기점검 공사","남안산S/S 154kV 신안산남안산#2TL 기기점검 공사","2016-03-04 09:00","2016-03-04 18:00","2016-03-04 09:00","2016-03-04 18:00","당일",null,null,null,201601060129,"-"]
[83,"경기","군포","산본안양#1 T/L","산본S/S 154kV 산본안양#1TL 기기점검 공사","산본S/S 154kV 산본안양#1TL 기기점검 공사","2016-03-11 09:00","2016-03-11 18:00","2016-03-11 09:00","2016-03-11 18:00","당일",null,null,"신뢰도개선",201601060141,"-"]
[84,"경기","군포","서서울산본#2 T/L","산본S/S 154kV 서서울산본#2TL 기기점검 공사","산본S/S 154kV 서서울산본#2TL 기기점검 공사","2016-03-14 09:00","2016-03-14 18:00","2016-03-14 09:00","2016-03-14 18:00","당일",null,null,"신뢰도개선",201601060143,"-"]
[85,"경기","군포","서서울남수원#1 T/L","154kV 서서울남수원#1T/L 송전선로 정밀점검(구간 No.1~70)","16년 가공송전선로 순시점검 위탁공사 154kV 서서울남수원#1T/L 송전선로 정밀점검(구간 No.1~70)","2016-03-14 09:00","2016-03-18 18:00","2016-03-14 09:00","2016-03-18 18:00","매일",null,null,null,201601120256,"-"]
[86,"경기","군포","서서울남수원#2 T/L","154kV 서서울남수원#2T/L 송전선로 정밀점검(구간 No.1~70)","16년 가공송전선로 순시점검 위탁공사 154kV 서서울남수원#2T/L 송전선로 정밀점검(구간 No.1~70)","2016-03-21 09:00","2016-03-25 18:00","2016-03-21 09:00","2016-03-25 18:00","매일",null,null,null,201601120258,"-"]
[87,"경기","군포","서서울서안양 T/L","EBA(종단접속) 자기애관 교체공사","EBA(종단접속) 자기애관 교체공사 시행 전 애관사이즈 실측","2016-03-05 15:00","2016-03-05 18:00","2016-03-05 15:00","2016-03-05 18:00","당일",null,null,null,201601070102,"-"]
[88,"경기","군포","서안양소래 T/L","EBA(종단접속) 자기애관 교체공사 및 변전기기 점검","EBA(종단접속) 자기애관 교체공사 시행 전 애관사이즈 실측 서안양S/S 서안양소래T/L GIS 보통점검 및 노후 보조계전기 교체","2016-03-05 08:00","2016-03-05 15:00","2016-03-05 08:00","2016-03-05 15:00","당일",null,null,null,201601070104,"-"]
[89,"경기","군포","신안산성포#3 T/L","성포S/S 154kV 신안산성포#3TL 기기점검 공사","성포S/S 154kV 신안산성포#3TL 기기점검 공사 노후보조계전기 교체 시행","2016-03-30 09:00","2016-03-30 18:00","2016-03-30 09:00","2016-03-30 18:00","당일",null,null,null,201601060132,"-"]
[90,"경기","군포","신안산성포#2 T/L","신안산S/S 154kV 신안산성포안산#2TL 기기점검 공사","신안산S/S 154kV 신안산성포안산#2TL 기기점검 공사 노후보조계전기 교체","2016-03-17 09:00","2016-03-17 18:00","2016-03-17 09:00","2016-03-17 18:00","당일",null,null,null,201601070051,"-"]
[91,"경기","군포","신안산성포#1 T/L","신안산S/S 154kV 신안산성포안산#1TL 기기점검 공사","신안산S/S 154kV 신안산성포안산#1TL 기기점검 공사 노후보조계전기 교체","2016-03-16 09:00","2016-03-16 18:00","2016-03-16 09:00","2016-03-16 18:00","당일",null,null,null,201601070049,"-"]
[92,"경기","동부","왕암가남#1 T/L","16년 동부 변전협력회사 총액공사","가남S/S 왕암-가남#1T/L GIS 보통점검","2016-03-26 10:00","2016-03-26 18:00","2016-03-19 10:00","2016-03-19 18:00","당일",null,null,"신뢰도개선",201601130074,"-"]
[93,"경기","동부","왕암가남#2 T/L","16년 동부 변전협력회사 총액공사","가남S/S 왕암-가남#2T/L GIS 보통점검","2016-03-27 10:00","2016-03-27 18:00","2016-03-20 10:00","2016-03-20 18:00","당일",null,null,"신뢰도개선",201601130076,"-"]
[94,"경기","동부","동판교야탑 T/L","16년 동부 변전협력회사 총액공사","야탑S/S 동판교-야탑T/L GIS 보통점검","2016-03-26 10:00","2016-03-26 18:00","2016-03-26 10:00","2016-03-26 18:00","당일",null,null,null,201601130077,"-"]
[95,"경기","동부","이천가남#1 T/L","이천S/S 이천-가남#1T/L 가스누기개소 보수공사","이천S/S 이천-가남#1T/L #1BUS DS측 구획용 스페이서 교체","2016-03-12 09:00","2016-03-13 18:00","2016-03-12 09:00","2016-03-13 18:00","연속",null,null,null,201601130129,"-"]
[96,"경기","동부","중원야탑 T/L","16년 동부 변전협력회사 총액공사","야탑, 중원S/S 중원-야탑T/L GIS 보통점검","2016-03-19 09:30","2016-03-19 18:00","2016-03-19 09:30","2016-03-19 18:00","당일",null,null,null,201601130073,"-"]
[97,"경기","성남","서안성S/S #61M.Tr(ESS) A","서안성S/S 154kV #61M.Tr(ESS)","서안성S/S #61M.Tr(ESS) 초기점검","2016-03-21 09:30","2016-04-01 18:00","2016-03-21 09:30","2016-04-01 18:00","연속",null,null,null,201601120072,"-"]
[98,"경기","성남","신수원삼미#1 T/L","154kV 북동탄분기 지중T/L 건설공사","신수원-북동탄T/L : 154kV XLPE 2500㎟, 2회선 × 1.4km 북동탄-삼미T/L : 154kV XLPE 2000㎟, 2회선(D) × 0.4km : 154kV XLPE 2500㎟, 2회선 × 1.0km","2016-03-22 10:00","2016-04-18 18:00","2016-03-22 10:00","2016-04-18 18:00","연속",null,null,null,201601120359,"-"]
[99,"경기","성남","신용인S/S #63M.Tr(ESS) A","신용인S/S 154kV #63M.Tr(ESS)","신용인S/S #63M.Tr(ESS), 1차, 2차 GIS 초기점검 #1,2,3,4,5,6 ESS D/L, #3, 4 S.Tr GIS 초기점검","2016-03-07 09:30","2016-03-18 18:00","2016-03-07 09:30","2016-03-18 18:00","연속",null,null,null,201601120046,"-"]
[100,"경기","성남","율현용인#2 T/L","154kV 율현-용인T/L 30호 지장철탑이설공사","-철탑교체 : 154kV 율현-용인T/L No.30(F2-15m), ACSR 330mm2 x S, 1기교체","2016-03-24 09:00","2016-03-26 18:00","2016-03-24 09:00","2016-03-26 18:00","연속",null,null,null,201601120391,"-"]
[101,"경기","성남","율현용인#1 T/L","154kV 율현-용인T/L 30호 지장철탑이설공사","-철탑교체 : 154kV 율현-용인T/L No.30(F2-15m), ACSR 330mm2 x S, 1기교체","2016-03-24 09:00","2016-03-28 18:00","2016-03-24 09:00","2016-03-28 18:00","연속",null,null,null,201601120390,"-"]
[102,"경기","직할","구문천-연료전지 T/L","154kV 구문천-연료전지 T/L","구문천S/S 구문천-연료전지 T/L GIS 하자점검","2016-03-19 10:00","2016-03-19 18:00","2016-03-19 10:00","2016-03-19 18:00","당일",null,null,null,201601070116,"-"]
[103,"경기","직할","발안구문천#2 T/L","154kV 발안구문천#2 T/L","발안S/S 154kV 발안구문천#2 T/L GIS 보통점검 구문천S/S 154kV 발안구문천#2 T/L GIS 보통점검","2016-03-20 10:00","2016-03-20 18:00","2016-03-20 10:00","2016-03-20 18:00","당일",null,null,null,201601070112,"-"]
[104,"경기","직할","발안구문천#1 T/L","154kV 발안구문천#1 T/L","발안S/S 154kV 발안구문천#1 T/L GIS 보통점검 구문천S/S 154kV 발안구문천#1 T/L GIS 보통점검","2016-03-19 10:00","2016-03-19 18:00","2016-03-19 10:00","2016-03-19 18:00","당일",null,null,null,201601070109,"-"]
[105,"경기","직할","남수원발안#1 T/L","154KV 남수원-발안T/L 27호 안전이격확보공사","ㅇ 철탑 1기 철거 및 설치 ㅇ 금구류 교체","2016-03-27 07:00","2016-04-04 20:00","2016-03-27 07:00","2016-04-04 20:00","연속",null,null,null,201601130124,"-"]
[106,"경기","직할","남수원발안#2 T/L","154KV 남수원-발안T/L 27호 안전이격확보공사","ㅇ 철탑 1기 철거 및 설치 ㅇ 금구류 교체","2016-03-27 07:00","2016-04-04 20:00","2016-03-27 07:00","2016-04-04 20:00","연속",null,null,null,201601130125,"-"]
[107,"경기","직할","율전의왕#1 T/L","EBA(종단접속) 자기애관 교체공사","EBA(종단접속) 자기애관 교체공사 시행 전 애관사이즈 실측","2016-03-03 09:00","2016-03-03 14:00","취소","취소","당일",null,null,null,201601070075,"-"]
[108,"경기","직할","율전의왕#2 T/L","EBA(종단접속) 자기애관 교체공사","EBA(종단접속) 자기애관 교체공사 시행 전 애관사이즈 실측","2016-03-03 14:30","2016-03-03 18:00","취소","취소","당일",null,null,null,201601070076,"-"]
[109,"경기","직할","오산향남#1 T/L","154kV 오산향남#1T/L","향남S/S 154kV 오산향남#1T/L GIS 초기점검","2016-03-12 10:00","2016-03-12 18:00","2016-03-12 10:00","2016-03-12 18:00","당일",null,null,null,201601070084,"-"]
[110,"경기","직할","발안향남#2 T/L","154kV 발안향남#2 T/L","향남S/S 발안향남#2 T/L GIS 초기점검","2016-03-23 10:00","2016-03-23 18:00","2016-03-23 10:00","2016-03-23 18:00","당일",null,null,null,201601070115,"-"]
[111,"경기","직할","발안향남#1 T/L","154kV 발안향남#1 T/L","향남S/S 발안향남#1 T/L GIS 초기점검","2016-03-22 10:00","2016-03-22 18:00","2016-03-22 10:00","2016-03-22 18:00","당일",null,null,null,201601070114,"-"]
[112,"경기","직할","오산향남#2 T/L","154kV 오산향남#2T/L","향남S/S 154kV 오산향남#2T/L GIS 초기점검","2016-03-13 10:00","2016-03-13 18:00","2016-03-13 10:00","2016-03-13 18:00","당일",null,null,null,201601070088,"-"]
[113,"경기","평택","송탄S/S 송탄-소사벌T/L(687) GIS","송탄S/S 송탄-소사벌T/L 170kV GIS 대체공사","송탄S/S 송탄-소사벌T/L 170kV GIS 대체공사","2016-03-21 09:00","2016-04-06 18:00","2016-03-21 09:00","2016-04-06 18:00","연속",null,null,null,201601110081,"-"]
[114,"경기","평택","송탄S/S 송탄-안성T/L(657) GIS","송탄S/S 송탄-안성T/L 170kV GIS 대체공사","송탄S/S 송탄-안성T/L 170kV GIS 대체공사","2016-03-02 09:00","2016-03-18 18:00","2016-03-02 09:00","2016-03-18 18:00","연속",null,null,null,201601110076,"○"]
[115,"강원","직할","남춘천청평PP T/L","2016년 강원직할 협력회사 총액공사","스페이샤 교체(4,692개)","2016-03-20 08:00","2016-03-26 18:00","2016-03-14 08:00","2016-03-20 18:00","연속",null,null,null,201601080005,"-"]
[116,"강원","직할","북춘천화천HP T/L","2016년 강원직할 협력회사 총액공사","정밀점검(10기)","2016-03-02 09:00","2016-03-03 18:00","취소","취소","매일",null,null,null,201601080001,"○"]
[117,"강원","직할","서홍천청평PP T/L","2016년 강원직할 협력회사 총액공사","스페이샤 교체(4,692개)","2016-03-27 08:00","2016-03-28 18:00","2016-03-21 08:00","2016-03-22 18:00","연속",null,null,null,201601080006,"-"]
[118,"강원","직할","남춘천춘천 T/L","2016~17년 변전협력회사 총액공사","축소형 고장기록장치 시범적용 × 1식","2016-03-23 09:00","2016-03-24 18:00","2016-03-23 09:00","2016-03-24 18:00","매일",null,null,null,201601080164,"-"]
[119,"강원","직할","가평춘천HP T/L","2016년 강원직할 협력회사 총액공사","정밀점검(10기)","2016-03-04 09:00","2016-03-05 18:00","취소","취소","매일",null,null,null,201601080002,"-"]
[120,"강원","직할","철원화천#2 T/L","2016~17년 변전협력회사 총액공사","축소형 고장기록장치 시범적용 × 1식","2016-03-22 09:00","2016-03-22 18:00","2016-03-22 09:00","2016-03-22 18:00","당일",null,null,null,201601080163,"○"]
[121,"강원","직할","철원화천#1 T/L","2016~17년 변전협력회사 총액공사","축소형 고장기록장치 시범적용 × 1식","2016-03-21 09:00","2016-03-21 18:00","2016-03-21 09:00","2016-03-21 18:00","당일",null,null,null,201601080160,"○"]
[122,"강원","태백","이원태백 T/L","이원-태백, 도계-태백T/L 안전이격확보공사","이원-태백, 도계-태백T/L 안전이격확보공사","2016-03-10 09:00","2016-03-13 18:00","2016-03-10 09:00","2016-03-13 18:00","연속",null,null,null,201601070135,"○"]
[123,"강원","태백","도계태백 T/L","이원-태백, 도계-태백T/L 안전이격확보공사","이원-태백, 도계-태백T/L 안전이격확보공사","2016-03-14 09:00","2016-03-17 18:00","2016-03-14 09:00","2016-03-17 18:00","연속",null,null,null,201601070139,"-"]
[124,"강원","태백","이원태백 T/L","이원-태백, 도계-태백T/L 안전이격확보공사","이원-태백, 도계-태백T/L 안전이격확보공사","2016-03-18 09:00","2016-03-20 18:00","2016-03-18 09:00","2016-03-20 18:00","연속",null,null,null,201601070136,"○"]
[125,"충북","직할","단양영월CC#2 T/L","2016년 변전협력회사 총액공사","피뢰기 보통점검","2016-03-30 09:00","2016-03-30 14:00","2016-03-30 09:00","2016-03-30 14:00","당일",null,null,null,"-","-"]
[126,"충북","직할","신제천남원주#1 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","정밀점검","2016-03-02 07:30","2016-03-03 18:00","2016-03-02 07:30","2016-03-03 18:00","매일",null,null,null,"-","-"]
[127,"충북","직할","신제천남원주#2 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","정밀점검","2016-03-04 07:30","2016-03-05 18:00","2016-03-04 07:30","2016-03-05 18:00","매일",null,null,null,"-","-"]
[128,"충북","청주","서청주사직#1 T/L","16년도 청주전력지사 154kV 개폐장치 정밀점검","사직S/S 서청주-사직#1T/L GIS (617CB, 611,612DS) 정밀점검","2016-03-18 09:00","2016-03-20 18:00","취소","취소","연속",null,null,null,"-","-"]
[129,"충북","청주","청원죽림#2 T/L","16년도 청주전력지사 154kV 개폐장치 정밀점검","죽림S/S 청원-죽림#2T/L GIS (657CB, 651,652DS) 정밀점검","2016-03-25 09:00","2016-03-27 18:00","취소","취소","연속",null,null,null,"-","-"]
[130,"대전충남","대전","신옥천서대전#2 T/L","(송전) 154kV 서대전S/S 지중케이블 계통정비공사","지중송전선로 철거 0.3km, 설치 0.34km 접속 2개소(중간1개소, 종단1개소)","2016-03-28 09:00","2016-04-28 18:00","2016-03-28 09:00","2016-04-28 18:00","연속",null,null,null,201601130157,"-"]
[131,"대전충남","대전","신옥천서대전#1 T/L","154kV 신옥천-서대전T/L 전선교체공사","#1T/L No.87~107호 전선교체 휴전작업","2016-03-16 07:00","2016-03-27 18:00","2016-03-16 07:00","2016-03-27 18:00","연속",null,null,null,201601130005,"-"]
[132,"대전충남","대전","신옥천서대전#2 T/L","154kV 신옥천-서대전TL 전선교체공사","#1T/L휴전작업을 위한 No.107호 안전이격거리 확보 사전작업","2016-03-15 07:00","2016-03-15 18:00","2016-03-15 07:00","2016-03-15 18:00","당일",null,null,null,201601130001,"-"]
[133,"대전충남","대전","은진함열#2 T/L","154kV 은진-함열T/L 취약철탑 교체공사","철탑철거 : 3기 철탑설치 : 2기 전력선교체 : No.49~52","2016-03-02 08:00","2016-04-23 18:00","2016-03-02 08:00","2016-04-23 18:00","연속",null,null,null,201601190001,"-"]
[134,"대전충남","대전","은진함열#1 T/L","154kV 은진-함열T/L 취약철탑교체공사","[송전] 은진-함열T/L 취약철탑교체 - 철탑3기 교체(No.47,48,49호)","2016-03-02 08:00","2016-04-23 18:00","2016-03-02 08:00","2016-04-23 18:00","연속",null,null,null,201601190005,"-"]
[135,"대전충남","서산","석문당진TP#2 T/L","[송전] 154kV 석문-당진화력#2T/L 지장송전선로 이설공사","요청자시행 공사 가공 : 철탑 신설1기, 철거 1기 지중 : 접속 8개소(중간4개소, 종단4개소) (3상/1개소)","2016-03-28 09:00","2016-04-02 18:00","2016-03-28 09:00","2016-04-02 18:00","연속",null,null,null,201601140158,"-"]
[136,"대전충남","서산","석문당진TP#1 T/L","[송전] 154kV 석문-당진화력#1T/L 지장송전선로 이설공사","요청자시행 공사 가공 : 철탑 신설1기, 철거 1기 지중 : 접속 8개소(중간4개소, 종단4개소) (3상/1개소)","2016-03-24 09:00","2016-03-27 18:00","2016-03-24 09:00","2016-03-27 18:00","연속",null,null,null,201601140157,"-"]
[137,"대전충남","서산","대산석문#2 T/L","154kV 대산-석문T/L 전선접속개소 전력선 교체공사","No.23~27 전선접소개소 전력선 교체[송전]","2016-03-17 07:00","2016-03-19 18:00","2016-03-17 07:00","2016-03-19 18:00","연속",null,null,null,201601190121,"-"]
[138,"대전충남","서산","대산석문#1 T/L","154kV 대산-석문T/L 전선접속개소 전력선 교체공사","No.20~27 전선접소개소 전력선 및 가공지선 교체[송전]","2016-03-20 07:00","2016-03-23 18:00","2016-03-20 07:00","2016-03-23 18:00","연속",null,null,null,201601190122,"-"]
[139,"대전충남","서산","태안T/P 154kV #2 BUS","태안화력S/Y 태양광소수력용 154kV GIS 증설공사","태안화력S/Y 태양광소수력용 170kV GIS 1CCT 설치 및 관련 부대공사 1식","2016-03-14 09:00","2016-03-18 18:00","2016-03-14 09:00","2016-03-18 18:00","연속",null,null,null,201601140104,"-"]
[140,"대전충남","서산","태안T/P 154kV #1 BUS","태안화력S/Y 태양광소수력용 154kV GIS 증설공사","태안화력S/Y 태양광소수력용 170kV GIS 1CCT 설치 및 관련 부대공사 1식","2016-03-07 09:00","2016-03-11 18:00","2016-03-07 09:00","2016-03-11 18:00","연속",null,null,null,201601140103,"-"]
[141,"대전충남","세종","신풍공주#2 T/L","154KV 신풍-공주T/L 접속개소제거 전선교체공사","[송전] 신풍-공주T/L 접속개소제거 전선교체 -#2T/L No.19~23 호 중단 내외측","2016-03-04 13:00","2016-03-06 18:00","2016-03-04 13:00","2016-03-06 18:00","연속",null,null,null,201601140017,"-"]
[142,"대전충남","세종","신풍공주#1 T/L","154KV 신풍-공주T/L 접속개소제거 전선교체공사","[송전] 신풍-공주T/L 접속개소제거 전선교체 -#1T/L No.19~23 호 중단 내외측 No.35~37호 상단 내외측","2016-03-02 07:00","2016-03-04 13:00","2016-03-02 07:00","2016-03-04 13:00","연속",null,null,null,201601140016,"-"]
[143,"대전충남","아산","신온양한샘#1 T/L","154kV 신온양-한샘T/L 건설공사","□ 기설 154kV 신온양-한샘T/L 경과지 변경","2016-03-12 06:00","2016-03-18 20:00","2016-03-12 06:00","2016-03-18 20:00","연속",null,null,null,201601110030,"-"]
[144,"대전충남","아산","신온양한샘#2 T/L","154kV 신온양-한샘T/L 건설공사","□ 기설 154kV 신온양-한샘T/L 경과지 변경","2016-03-05 06:00","2016-03-11 20:00","2016-03-05 06:00","2016-03-11 20:00","연속",null,null,null,201601110017,"-"]
[145,"대전충남","아산","아산S/S 154kV #61 BUS","345kV 아산S/S #4M.Tr 증설공사","○ #4MTR 초기가압에 따른 준공시험","2016-03-24 14:00","2016-03-24 15:00","2016-03-24 14:00","2016-03-24 15:00","연속",null,null,null,201601150054,"-"]
[146,"대전충남","아산","아산S/S 154kV #66 BUS","345kV 아산S/S #4M.Tr 증설공사","○ #4MTR 초기가압에 따른 준공시험","2016-03-24 15:00","2016-03-24 16:00","2016-03-24 15:00","2016-03-24 16:00","연속",null,null,null,201601150065,"-"]
[147,"대전충남","아산","장재불당#2 T/L","장재,불당S/S 154kV 장재-불당#2T/L GIS 보통점검","○154kV 장재-불당#2T/L GIS 보통점검","2016-03-20 09:00","2016-03-20 18:00","2016-03-20 09:00","2016-03-20 18:00","당일",null,null,null,201601130044,"-"]
[148,"대전충남","아산","장재불당#1 T/L","장재,불당S/S 154kV 장재-불당#1T/L GIS 보통점검","○154kV 장재-불당#1T/L GIS 보통점검","2016-03-19 09:00","2016-03-19 18:00","2016-03-19 09:00","2016-03-19 18:00","당일",null,null,null,201601130043,"-"]
[149,"대전충남","청양","옥산서천화력#1 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 이설구간 : No.2-6 - 철탑설치 : 2기 - 철탑철거 : 3기","2016-03-11 07:00","2016-03-13 18:00","2016-03-11 07:00","2016-03-13 18:00","연속",null,null,null,201601150007,"-"]
[150,"대전충남","청양","대천서천화력#1 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 이설구간 : No.2-6 - 철탑설치 : 2기 - 철탑철거 : 3기","2016-03-11 07:00","2016-03-13 18:00","2016-03-11 07:00","2016-03-13 18:00","연속",null,null,null,201601150008,"-"]
[151,"대전충남","청양","옥산서천화력#2 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 작업구간 : No.2-6 - 철탑신설 : 2기 - 철탑철거 : 3기","2016-03-14 07:00","2016-03-23 18:00","2016-03-14 07:00","2016-03-23 18:00","연속",null,null,null,201601150017,"-"]
[152,"대전충남","청양","대천서천화력#2 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 작업구간 : No.2-6 - 철탑신설 : 2기 - 철탑철거 : 3기","2016-03-14 07:00","2016-03-23 18:00","2016-03-14 07:00","2016-03-23 18:00","연속",null,null,null,201601150018,"-"]
[153,"대전충남","청양","대천서천화력#1 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 작업구간 : No.2-6 - 철탑신설 : 2기 - 철탑철거 : 3기","2016-03-24 07:00","2016-03-30 18:00","2016-03-24 07:00","2016-03-30 18:00","연속",null,null,null,201601150020,"-"]
[154,"대전충남","청양","옥산서천화력#1 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 작업구간 : No.2-6 - 철탑신설 : 2기 - 철탑철거 : 3기","2016-03-24 07:00","2016-03-30 18:00","2016-03-24 07:00","2016-03-30 18:00","연속",null,null,null,201601150019,"-"]
[155,"전북","군산","서군산S/S 군산-서군산#1T/L CB","서군산S/S 군산-서군산#1T/L CB","차단기 보통점검","2016-03-12 10:00","2016-03-12 18:00","취소","취소","당일",null,null,null,201601180058,"-"]
[156,"전북","군산","서군산S/S 군산-서군산#2T/L CB","서군산S/S 군산-서군산#2T/L CB","차단기 보통점검","2016-03-19 10:00","2016-03-19 18:00","취소","취소","당일",null,null,null,201601180059,"-"]
[157,"전북","군산","서군산S/S 서군산-소룡#1T/L CB","서군산S/S 서군산-소룡#1T/L CB","차단기 보통점검","2016-03-26 10:00","2016-03-26 18:00","2016-03-26 10:00","2016-03-26 18:00","당일",null,null,null,201601180060,"-"]
[158,"전북","김제","고창홍농 T/L","고창S/S 고창-홍농T/L","축소형 고장기록장치 설치","2016-03-04 10:00","2016-03-04 18:00","2016-04-05 10:00","2016-04-05 18:00","당일",null,null,"신뢰도개선",201512160010,"-"]
[159,"전북","김제","고창영광 T/L","고창S/S 고창-영광T/L","축소형 고장기록장치 설치","2016-03-03 10:00","2016-03-03 18:00","2016-04-04 10:00","2016-04-04 18:00","당일",null,null,"신뢰도개선",201512160009,"-"]
[160,"전북","김제","백산김제#1 T/L","백산S/S 백산김제#1 T/L","차단기 보통점검","2016-03-28 09:00","2016-03-28 18:00","2016-03-28 09:00","2016-03-28 18:00","당일",null,null,null,201601140063,"-"]
[161,"전북","김제","백산김제#2 T/L","백산S/S 백산김제#2 T/L","차단기 보통점검","2016-03-29 09:00","2016-03-29 18:00","2016-03-29 09:00","2016-03-29 18:00","당일",null,null,null,201601140066,"-"]
[162,"전북","김제","김제섬진강HP T/L","섬진강수력 김제섬진강HP T/L","통합제어반 및 보호반 연동시험","2016-03-07 09:00","2016-03-08 18:00","2016-03-07 09:00","2016-03-08 18:00","매일",null,null,null,201601140085,"-"]
[163,"전북","김제","정공섬진강수력 T/L","섬진강수력 정공섬진강수력 T/L","통합제어반 및 보호반 연동시험","2016-03-09 09:00","2016-03-10 18:00","2016-03-09 09:00","2016-03-10 18:00","매일",null,null,null,201601140086,"○"]
[164,"전북","김제","섬진강H/P 154kV #1 BUS TIE CB","섬진강H/P 154kV #1 BUS TIE CB","통합제어반 및 보호반 연동시험","2016-03-11 09:00","2016-03-12 18:00","2016-03-11 09:00","2016-03-12 18:00","매일",null,null,null,201601140087,"○"]
[165,"전북","김제","신김제전주#2 T/L","신김제전주#2T/L","장기미동작 차단기 점검","2016-03-02 14:00","2016-03-02 18:00","2016-03-02 14:00","2016-03-02 18:00","당일",null,null,null,201601050092,"-"]
[166,"전북","김제","신김제전주#1 T/L","신김제전주#1 T/L","장기미동작 차단기 점검","2016-03-02 10:00","2016-03-02 14:00","2016-03-02 10:00","2016-03-02 14:00","당일",null,null,null,201601050088,"-"]
[167,"광주전남","강진","화원진도#1 T/L","154kV 화원-진도T/L 인수점검 적출사항 해소","-No.34호 지상고 확보 -전력선 이도조정 등 인수점검 적출사항 해소","2016-03-07 09:00","2016-03-13 18:00","2016-03-07 09:00","2016-03-13 18:00","연속",null,null,null,201601110072,"-"]
[168,"광주전남","강진","화원진도#2 T/L","154kV 화원-진도T/L 인수점검 적출사항 해소","-No.34호 지상고 확보 -전력선 이도조정 등 인수점검 적출사항 해소","2016-03-07 09:00","2016-03-13 18:00","2016-03-07 09:00","2016-03-13 18:00","연속",null,null,null,201601110073,"-"]
[169,"광주전남","강진","해남진도#2 T/L","154kV 해남-진도#2T/L 인수점검 적출사항 해소","-전력선 이도조정 외 적출사항 해소","2016-03-18 07:00","2016-03-22 18:00","2016-03-18 07:00","2016-03-22 18:00","매일",null,null,null,201601110075,"-"]
[170,"광주전남","강진","해남진도#1 T/L","154kV 해남-진도#1T/L 인수점검 적출사항 해소","-전력선 이도조정 외 적출사항 해소","2016-03-14 09:00","2016-03-17 18:00","2016-03-14 09:00","2016-03-17 18:00","매일",null,null,null,201601110074,"-"]
[171,"광주전남","강진","해남해남CS#1 T/L","154kV해남해남CS#1T/L(화원-안좌 등 4개T/L 피뢰기설치공사)","154kV 화원-안좌 등 4개T/L 피뢰기설치공사 - 총 247기 741SET","2016-03-18 07:00","2016-03-22 18:00","2016-03-18 07:00","2016-03-22 18:00","매일",null,null,null,201601140140,"-"]
[172,"광주전남","강진","해남해남CS#2 T/L","154kV 해남해남CS#2 T/L 정밀점검(가공송전 순시점검 위탁공사)","154kV 해남해남CS#2 T/L 정밀점검(가공송전 순시점검 위탁공사)","2016-03-23 09:00","2016-03-27 18:00","2016-03-23 09:00","2016-03-27 18:00","매일",null,null,null,201601190061,"-"]
[173,"광주전남","광주","계림승주#2(서남권상수도T분기) T/L","154kV 계림=승주#2T/L(광주170GIS정밀)","계림S/S 154kV 계림-승주#2T/L GIS 정밀점검 계림S/S 154kV 계림-승주#2T/L 보호반 고장기록장치 설치","2016-03-31 09:00","2016-04-02 18:00","2016-03-31 09:00","2016-04-02 18:00","연속",null,null,null,201601130148,"-"]
[174,"광주전남","광주","계림승주#1(서남권상수도T분기) T/L","154kV 계림=승주#1T/L(광주170GIS정밀)","계림S/S 154kV 계림-승주#1T/L GIS 정밀점검 계림S/S 154kV 계림-승주#1T/L 보호반 고장기록장치 설치","2016-03-28 09:00","2016-03-30 18:00","2016-03-28 09:00","2016-03-30 18:00","연속",null,null,null,201601130147,"-"]
[175,"광주전남","광주","신광주일곡#2 T/L","154kV 신광주-일곡#2T/L(장기미동작차단기 점검)","신광주-일곡#2T/L GIS CB 장기 미동작차단기 점검","2016-03-03 09:00","2016-03-03 18:00","2016-03-03 09:00","2016-03-03 18:00","당일",null,null,"신뢰도개선",201601150107,"-"]
[176,"광주전남","광주","신광주계림#2 T/L","154kV 신광주-계림#2T/L(장기미동작차단기 점검)","신광주-계림#2T/L GIS CB 장기 미동작차단기 점검","2016-03-04 09:00","2016-03-04 18:00","2016-03-04 09:00","2016-03-04 18:00","당일",null,null,null,201601150108,"-"]
[177,"광주전남","광주","담양일곡#1 T/L","154kV 담양-일곡#1T/L(광주170GIS정밀)","일곡S/S 154kV 담양-일곡#1T/L GIS 정밀점검","2016-03-24 09:00","2016-03-26 18:00","2016-03-24 09:00","2016-03-26 18:00","연속",null,null,null,201601130146,"-"]
[178,"광주전남","광주","신광주일곡#1 T/L","신광주-일곡#1T/L(변전 협력회사 총액공사)","일곡S/S 신광주-일곡#1T/L GIS 보통점검","2016-03-02 09:00","2016-03-02 18:00","2016-03-02 09:00","2016-03-02 18:00","당일",null,null,"신뢰도개선",201601120378,"-"]
[179,"광주전남","광주","신광주장성#1 T/L","신광주-장성#1T/L(변전 협력회사 총액공사)","장성S/S 신광주-장성#1T/L GIS 보통점검","2016-03-17 09:00","2016-03-17 18:00","2016-03-17 09:00","2016-03-17 18:00","당일",null,null,null,201601120379,"-"]
[180,"광주전남","광주","장성영광#2 T/L","장성-영광#2T/L(변전 협력회사 총액공사)","장성S/S 장성-영광#2T/L GIS 보통점검","2016-03-18 09:00","2016-03-18 18:00","2016-03-18 09:00","2016-03-18 18:00","당일",null,null,null,201601120380,"-"]
[181,"광주전남","순천","광양순천#1 T/L","154kV 광양-순천#1T/L(순천 변전협력회사 총액공사)","2016년 순천 변전협력회사 총액공사 - 광양S/S측 GIS 보통점검","2016-03-09 10:00","2016-03-09 18:00","2016-03-09 10:00","2016-03-09 18:00","당일",null,null,null,201601140132,"-"]
[182,"광주전남","순천","광양순천#2 T/L","154kV 광양-순천#2T/L(순천 변전협력회사 총액공사)","2016년 순천 변전협력회사 총액공사 - 광양S/S측 GIS 보통점검 - 광양S/S측 LA 보통점검","2016-03-10 10:00","2016-03-10 18:00","2016-03-10 10:00","2016-03-10 18:00","당일",null,null,null,201601140133,"-"]
[183,"광주전남","순천","여수TP화치#1 T/L","154kV 여수TP-화치#1T/L(가공송전선로 순시점검 위탁공사)","2016년 가공송전선로 순시점검 위탁공사 - 정밀점검 : 1~31호, 32기","2016-03-07 08:00","2016-03-09 18:00","2016-03-07 08:00","2016-03-09 18:00","매일",null,null,null,201601140115,"-"]
[184,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP-여수TP#2T/L(가공송전선로 순시점검 위탁공사)","2016년 가공송전선로 순시점검 위탁공사 - 정밀점검 : 1~14호, 16기 2016년 순천 변전협력회사 총액공사 - 여수T/P측 GIS 보통점검","2016-03-16 08:00","2016-03-17 18:00","2016-03-16 08:00","2016-03-17 18:00","매일",null,null,null,201601140118,"-"]
[185,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP-여수TP#1T/L(가공송전선로 순시점검 위탁공사)","2016년 가공송전선로 순시점검 위탁공사 - 정밀점검 : 1~14호, 16기 2016년 순천 변전협력회사 총액공사 - 여수T/P측 GIS 보통점검","2016-03-14 08:00","2016-03-15 18:00","2016-03-14 08:00","2016-03-15 18:00","매일",null,null,null,201601140117,"-"]
[186,"광주전남","순천","여수TP화치#2 T/L","154kV 여수TP-화치#2T/L(가공송전선로 순시점검 위탁공사)","2016년 가공송전선로 순시점검 위탁공사 - 정밀점검 : 1~31호, 32기","2016-03-10 08:00","2016-03-12 18:00","2016-03-10 08:00","2016-03-12 18:00","매일",null,null,null,201601140116,"-"]
[187,"광주전남","순천","여천호남TP#2 T/L","154kV 여천-호남TP #2T/L(가공송전선로 순시점검 위탁공사)","2016년 가공송전선로 순시점검 위탁공사 - 정밀점검 : 1~41호, 41기","2016-03-31 08:00","2016-04-02 18:00","2016-03-31 08:00","2016-04-02 18:00","연속",null,null,null,201601140121,"-"]
[188,"광주전남","순천","여천호남TP#1 T/L","154kV 여천-호남TP #1T/L(가공송전선로 순시점검 위탁공사)","2016년 가공송전선로 순시점검 위탁공사 - 정밀점검 : 1~41호, 41기","2016-03-28 08:00","2016-03-30 18:00","2016-03-28 08:00","2016-03-30 18:00","연속",null,null,null,201601140119,"-"]
[189,"광주전남","순천","율촌화치#1 T/L","154kV 율촌-화치#1T/L(순천 변전협력회사 총액공사)","2016년 순천 변전협력회사 총액공사 - 화치S/S측 GIS 보통점검","2016-03-23 10:00","2016-03-23 18:00","2016-03-23 10:00","2016-03-23 18:00","당일",null,null,null,201601140144,"-"]
[190,"광주전남","순천","율촌화치#2 T/L","154kV 율촌-화치#2T/L(순천 변전협력회사 총액공사)","2016년 순천 변전협력회사 총액공사 - 화치S/S측 GIS 보통점검","2016-03-24 10:00","2016-03-24 18:00","2016-03-24 10:00","2016-03-24 18:00","당일",null,null,null,201601140145,"-"]
[191,"대구경북","달성","대구봉덕#2 T/L","복도체 이련내장 피뢰기 설치개소 아킹혼 철거","No.1~32","2016-03-08 09:00","2016-03-09 18:00","2016-03-08 09:00","2016-03-09 18:00","연속",null,null,null,"-","-"]
[192,"대구경북","달성","성서달성#2 T/L","보호계전기 성능개선","보호계전기 성능개선(계통운영)","2016-03-05 09:00","2016-03-05 13:00","2016-03-05 09:00","2016-03-05 13:00","당일",null,null,null,"-","-"]
[193,"대구경북","영주","점촌문경 T/L","문경S/S 617 GIS 누유개소 보수","문경S/S 617 GIS 누유개소 보수(제작사)","2016-03-08 13:00","2016-03-08 18:00","2016-03-08 13:00","2016-03-08 18:00","당일",null,null,null,"-","-"]
[194,"대구경북","직할","남대구S/S 범물-남대구#2T/L GIS","범물-남대구#2T/L GIS 보통점검","GIS(657) 및 PNL 보통점검","2016-03-11 09:30","2016-03-11 18:00","2016-03-11 09:30","2016-03-11 18:00","당일",null,null,null,"-","-"]
[195,"대구경북","직할","남대구S/S 범물-남대구#1T/L GIS","범물-남대구#1T/L GIS 보통점검","GIS(667) 및 PNL 보통점검","2016-03-10 09:30","2016-03-10 18:00","2016-03-10 09:30","2016-03-10 18:00","당일",null,null,null,"-","-"]
[196,"대구경북","포항","아화건천#1 T/L","건천, 아화S/S 아화-건천#1T/L 장기미동작 차단기 동작시험","장기미동작 차단기 동작시험","2016-03-11 10:00","2016-03-11 11:00","2016-03-11 10:00","2016-03-11 11:00","당일",null,null,null,"-","-"]
[197,"대구경북","포항","옥동외동#1 T/L","외동S/S 외동-옥동#1T/L 휴전작업","687GIS 보통, LA 초기점검","2016-03-09 10:00","2016-03-09 18:00","2016-03-09 10:00","2016-03-09 18:00","당일",null,null,null,"-","-"]
[198,"대구경북","포항","옥동외동#2 T/L","외동S/S 외동-옥동#2T/L 휴전작업","657 GIS 보통, LA 초기점검","2016-03-10 10:00","2016-03-10 18:00","2016-03-10 10:00","2016-03-10 18:00","당일",null,null,null,"-","-"]
[199,"대구경북","포항","건천천북#2 T/L","천북S/S 건천-천북#2T/L 휴전작업","617GIS 보통, PT, LA 하자점검","2016-03-29 09:30","2016-03-29 18:00","2016-03-29 09:30","2016-03-29 18:00","당일",null,null,null,"-","-"]
[200,"대구경북","달성","두류봉덕#2 T/L","두류,봉덕 판넬대체공사","보호반 판넬교체","2016-03-28 09:30","2016-03-29 18:00","2016-03-28 09:30","2016-03-29 18:00","당일",null,null,null,"-","-"]
[201,"대구경북","달성","두류봉덕#1 T/L","두류,봉덕 판넬대체공사","보호반 판넬교체","2016-03-24 09:30","2016-03-25 18:00","2016-03-24 09:30","2016-03-25 18:00","당일",null,null,null,"-","-"]
[202,"부산울산","동부산","신양산S/S 154kV #66 BUS","신양산S/S 6242DS측 과열개소 보수","신양산 6242DS측 과열개소 보수(#2M.Tr+#66BUS 접속부)","2016-03-07 09:30","2016-03-07 17:00","2016-03-07 09:30","2016-03-07 17:00","당일",null,null,null,201601120229,"-"]
[203,"부산울산","동부산","신양산S/S 65-66-0 SEC CB","신양산S/S 154kV ILC PNL 대체","신양산S/S 154kV ILC PNL 대체(65-66-0)","2016-03-08 09:00","2016-03-10 18:00","2016-03-08 09:00","2016-03-10 18:00","연속",null,null,null,201601120221,"-"]
[204,"부산울산","동부산","신양산S/S 60-61-0 SEC CB","신양산S/S 154kV ILC PNL 대체","신양산S/S 154kV ILC PNL 대체(60-61-0)","2016-03-02 09:00","2016-03-04 18:00","2016-03-02 09:00","2016-03-04 18:00","연속",null,null,null,201601120218,"-"]
[205,"부산울산","북부산","삼계김해 T/L","2016년 북부산변전협력회사 총액공사","GIS 보통점검","2016-03-12 10:00","2016-03-12 18:00","2016-03-12 10:00","2016-03-12 18:00","당일",null,null,null,201601120352,"-"]
[206,"부산울산","북부산","매리김해#1 T/L","2016년 김해S/S BUS-TIE 대체공사","최종 시험가압 48시간(#2DS 및 CB)","2016-03-04 18:00","2016-03-06 18:00","2016-03-04 18:00","2016-03-06 18:00","연속",null,null,null,201512120013,"-"]
[207,"부산울산","북부산","매리김해#1 T/L","2016년 김해S/S BUS-TIE 대체공사","#1BUS 자체 시험가압(BUS TIE 철거분으로 모선만 시험가압)","2016-03-09 17:00","2016-03-09 18:00","2016-03-09 17:00","2016-03-09 18:00","연속",null,null,null,201601110555,"-"]
[208,"부산울산","북부산","김해S/S 154kV #2 BUS","2016년 김해S/S BUS-TIE 대체공사","기존 BUS TIE #2DS 철거","2016-03-07 09:00","2016-03-07 18:00","2016-03-07 09:00","2016-03-07 18:00","연속",null,null,null,201512120010,"-"]
[209,"부산울산","북부산","매리김해#1 T/L","2016년 김해S/S BUS-TIE 대체공사","#2BUS 시험가압 1시간(BUS TIE 철거분으로 모선만 시험가압)","2016-03-07 17:00","2016-03-07 18:00","2016-03-07 17:00","2016-03-07 18:00","연속",null,null,null,201601110554,"-"]
[210,"부산울산","북부산","김해S/S 154kV #1 BUS","2016년 김해S/S BUS-TIE 대체공사","기존 BUS TIE #1DS,CB 철거","2016-03-08 09:00","2016-03-09 18:00","2016-03-08 09:00","2016-03-09 18:00","연속",null,null,null,201601110553,"-"]
[211,"부산울산","북부산","모라엄궁#2 T/L","2016년 북부산변전협력회사 총액공사","GIS 보통점검","2016-03-02 10:00","2016-03-02 18:00","2016-03-02 10:00","2016-03-02 18:00","당일",null,null,null,201601120349,"-"]
[212,"부산울산","북부산","양산산막#1 T/L","2016년 북부산변전협력회사 총액공사","GCB 보통점검","2016-03-04 10:00","2016-03-04 18:00","2016-03-04 10:00","2016-03-04 18:00","당일",null,null,null,201601120350,"-"]
[213,"부산울산","북부산","언양산막#1 T/L","16년 가공송전 협력업체 정비공사","언양산막#1T/L14호 상단 애자 9장 섬락 정비","2016-03-03 07:30","2016-03-03 18:00","2016-03-03 07:30","2016-03-03 18:00","당일",null,null,null,201601060091,"-"]
[214,"부산울산","북부산","서부산엄궁#1 T/L","장기사용 배전반 대체공사","서부산-엄궁#1T/L 보호배전반 대체","2016-03-21 09:00","2016-03-23 14:00","2016-03-21 09:00","2016-03-23 14:00","연속",null,null,null,201601120288,"○"]
[215,"부산울산","북부산","서부산엄궁#2 T/L","장기사용 배전반 대체공사","서부산-엄궁#2T/L 보호배전반 대체","2016-03-23 14:00","2016-03-25 18:00","2016-03-23 14:00","2016-03-25 18:00","연속",null,null,null,201601120291,"-"]
[216,"부산울산","북부산","매리호포#2 T/L","장기사용 배전반 대체공사","호포-매리#2T/L 보호배전반 대체","2016-03-26 09:00","2016-03-27 18:00","2016-03-26 09:00","2016-03-27 18:00","연속",null,null,null,201601120231,"-"]
[217,"부산울산","북부산","매리호포#1 T/L","장기사용 배전반 대체공사","호포-매리#1T/L 보호배전반 대체","2016-03-19 09:00","2016-03-20 18:00","2016-03-19 09:00","2016-03-20 18:00","연속",null,null,null,201601120230,"-"]
[218,"부산울산","서부산","서부산다대#2 T/L","154kV 서부산-다대T/L 지장이설공사","천마산터널 민간투자사업 관련 지장이설공사 - 공사구간 : 서부산S/S EBG ~ J/B#2(0.66km)","2016-03-28 09:00","2016-04-22 18:00","취소","취소","연속",null,null,null,201601110180,"-"]
[219,"부산울산","서부산","서부산다대#1 T/L","154kV 서부산-다대T/L 지장이설공사","천마산터널 민간투자사업 관련 지장이설공사 - 공사구간 : 서부산S/S EBG ~ J/B#2 (0.66km)","2016-03-07 09:00","2016-03-25 18:00","취소","취소","연속",null,null,null,201601110175,"-"]
[220,"부산울산","울산","신울산S/S 154kV #2 BUS TIE CB","2016-17년 울산전력지사 변전협력회사 총액공사","#61-66 모선보호반 대체","2016-03-07 09:00","2016-03-10 18:00","2016-03-07 09:00","2016-03-10 18:00","연속",null,null,null,201601110277,"-"]
[221,"부산울산","울산","신울산울산#2 T/L","2016년 가공송전 순시점검 위탁공사(울산전력지사)","송전선로 정밀점검(17기)","2016-03-10 09:00","2016-03-11 18:00","2016-03-11 09:00","2016-03-12 18:00","연속",null,null,null,201601060112,"-"]
[222,"부산울산","울산","신울산울산#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","보호배전반 대체, ILC PNL 대체, 울산측 GIS 보통점검","2016-03-02 09:00","2016-03-04 18:00","2016-03-02 09:00","2016-03-04 18:00","연속",null,null,null,201601110274,"○"]
[223,"부산울산","울산","신울산영남TP#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","보호배전반 대체, ILC PNL 대체, 영남화력측 GIS 보통점검","2016-03-05 08:00","2016-03-06 18:00","2016-03-05 08:00","2016-03-06 18:00","연속",null,null,null,201601110275,"-"]
[224,"부산울산","울산","방어진영남TP#1 T/L","영남화력 170kV GIS 철거공사","6183,6283,6383 철거 후 #2BUS 설치부 시험가압(48H)","2016-03-21 18:00","2016-03-23 18:00","취소","취소","연속",null,null,null,201601110299,"-"]
[225,"부산울산","울산","방어진영남TP#1 T/L","영남화력 170kV GIS 철거공사","6183,6283,6383 철거 후 #1BUS 설치부 시험가압(48H)","2016-03-29 18:00","2016-03-31 18:00","취소","취소","연속",null,null,null,201601110300,"-"]
[226,"부산울산","울산","온산처용#1 T/L","2016년 가공송전 순시점검 위탁공사(울산전력지사)","송전선로 정밀점검(19기)","2016-03-21 09:00","2016-03-22 18:00","2016-03-28 09:00","2016-03-29 18:00","연속",null,null,null,201601060113,"-"]
[227,"부산울산","울산","온산처용#2 T/L","2016년 가공송전 순시점검 위탁공사(울산전력지사)","송전선로 정밀점검(19기)","2016-03-24 09:00","2016-03-25 18:00","2016-03-31 09:00","2016-04-01 18:00","연속",null,null,null,201601060114,"-"]
[228,"부산울산","울산","울산T/P 154kV #66 BUS","울산화력 GIS 철거공사","6332 GIS 철거","2016-03-07 09:00","2016-03-12 18:00","2016-03-14 09:00","2016-03-19 18:00","연속",null,null,null,201601110292,"○"]
[229,"부산울산","울산","용연울산TP#2 T/L","울산화력 GIS 철거공사","6331 GIS 철거부 시험가압(48H)","2016-03-17 18:00","2016-03-19 18:00","2016-03-24 18:00","2016-03-26 18:00","연속",null,null,null,201601110295,"-"]
[230,"부산울산","울산","용연울산TP#2 T/L","울산화력 GIS 철거공사","6332 GIS 철거부 시험가압(48H)","2016-03-10 18:00","2016-03-12 18:00","2016-03-17 18:00","2016-03-19 18:00","연속",null,null,null,201601110294,"-"]
[231,"부산울산","울산","울산T/P 154kV #61 BUS","울산화력 GIS 철거공사","6331 GIS 철거","2016-03-14 09:00","2016-03-19 18:00","2016-03-21 09:00","2016-03-26 18:00","연속",null,null,null,201601110293,"-"]
[232,"부산울산","울산","울산울산TP#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","6432,662 GIS UHF 센서설치 후 시험가압(1H)","2016-03-20 17:00","2016-03-20 18:00","2016-03-20 17:00","2016-03-20 18:00","당일",null,null,null,201601110297,"○"]
[233,"부산울산","울산","울산T/P 154kV #65 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","6432,662 GIS UHF 센서설치","2016-03-20 08:00","2016-03-20 18:00","2016-03-20 08:00","2016-03-20 18:00","당일",null,null,null,201601110298,"○"]
[234,"부산울산","울산","용연울산TP#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","672 GIS UHF 센서설치 후 시험가압(1H)","2016-03-13 17:00","2016-03-13 18:00","2016-03-13 17:00","2016-03-13 18:00","당일",null,null,null,201601110296,"-"]
[235,"부산울산","울산","울산T/P 154kV #66 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","672 GIS UHF 센서설치","2016-03-13 09:00","2016-03-13 18:00","2016-03-13 09:00","2016-03-13 18:00","당일",null,null,null,201601180036,"○"]
[236,"부산울산","직할","정보대연 T/L","2016년 가공송전 순시점검 위탁공사","애자 교체","2016-03-14 09:00","2016-03-14 18:00","2016-03-14 09:00","2016-03-14 18:00","당일",null,null,"신뢰도개선",201601060083,"-"]
[237,"부산울산","직할","우동대연 T/L","2016년 가공송전 순시점검 위탁공사","애자 교체","2016-03-15 09:00","2016-03-15 18:00","2016-03-15 09:00","2016-03-15 18:00","당일",null,null,"신뢰도개선",201601070047,"-"]
[238,"경남","직할","신김해진영#2 T/L","신김해진영#2 T/L 초기점검(2016 가공송전선로 순시점검 위탁공사)","초기점검(2~3,17~33호)","2016-03-16 08:30","2016-03-17 18:00","2016-03-16 08:30","2016-03-17 18:00","매일",null,null,null,201601080046,"-"]
[239,"경남","직할","신김해진영#1 T/L","신김해진영#1 T/L 초기점검(2016 가공송전선로 순시점검 위탁공사)","초기점검(2~3,17~33호)","2016-03-14 08:30","2016-03-15 18:00","2016-03-14 08:30","2016-03-15 18:00","매일",null,null,null,201601080044,"-"]
[240,"경남","직할","신김해진영#1 T/L","신김해S/S 신김해-삼정#2 T/L GIS 정밀점검","신김해S/S 신김해-삼정#2 T/L GIS 정밀점검 시험가압","2016-03-31 16:30","2016-03-31 17:30","2016-03-31 16:30","2016-03-31 17:30","당일",null,null,null,201601070233,"-"]
[241,"경남","직할","신김해진영#2 T/L","신김해S/S 신김해-삼정#2 T/L GIS 정밀점검","신김해S/S 신김해-삼정#2 T/L GIS 정밀점검 시험가압","2016-03-29 16:30","2016-03-29 17:30","2016-03-29 16:30","2016-03-29 17:30","당일",null,null,null,201601070229,"-"]
[242,"경남","직할","수출월림#2 T/L","월림S/S 수출-월림#2 T/L GIS 정밀점검","월림S/S 수출-월림#2 T/L GIS 정밀점검","2016-03-12 08:00","2016-03-13 18:30","2016-03-12 08:00","2016-03-13 18:30","연속",null,null,null,201601070150,"-"]
[243,"경남","직할","신김해주촌#1 T/L","주촌S/S 신김해-주촌#1T/L 하자점검","주촌S/S 신김해-주촌#1T/L 하자점검","2016-03-05 09:30","2016-03-05 17:30","2016-03-05 09:30","2016-03-05 17:30","당일",null,null,null,201601070255,"-"]
[244,"경남","직할","신김해주촌#2 T/L","주촌S/S 신김해-주촌#2T/L 하자점검","주촌S/S 신김해-주촌#2T/L 하자점검","2016-03-12 09:30","2016-03-12 17:30","2016-03-12 09:30","2016-03-12 17:30","당일",null,null,null,201601070258,"-"]
[245,"경남","직할","안민진해#2 T/L","154kV 안민-진해#2T/L 지장송전선로 지중화공사","154kV 안민-진해#2T/L 가공선로 지중 연결(접속) 및 철탑보강","2016-03-24 08:00","2016-03-27 18:00","2016-03-24 08:00","2016-03-27 18:00","연속",null,null,null,201601050165,"-"]
[246,"경남","직할","안민진해#1 T/L","154kV 안민-진해#1T/L 지장송전선로 지중화공사","154kV 안민-진해#1T/L 가공선로 지중 연결(접속) 및 철탑보강","2016-03-24 08:00","2016-03-27 18:00","2016-03-24 08:00","2016-03-27 18:00","연속",null,null,null,201601050164,"-"]
[247,"경남","직할","마천진해#1 T/L","154kV 마천-진해#1T/L 지장송전선로 지중화공사","154kV 마천-진해#1T/L 가공선로 지중 연결(접속)","2016-03-19 08:00","2016-03-20 18:00","2016-03-19 08:00","2016-03-20 18:00","연속",null,null,null,201601050162,"-"]
[248,"경남","직할","마천진해#2 T/L","154kV 마천-진해#2T/L 지장송전선로 지중화공사","154kV 마천-진해#2T/L 가공선로 지중 연결(접속)","2016-03-19 08:00","2016-03-20 18:00","2016-03-19 08:00","2016-03-20 18:00","연속",null,null,null,201601050163,"-"]
[249,"경남","진주","산청함양 T/L","154kV 산청-함양T/L 전선교체","교체구간 : 78~82호, 116~125호","2016-03-19 08:00","2016-03-23 19:00","2016-03-19 08:00","2016-03-23 19:00","연속",null,null,null,201601140079,"-"]
[250,"경남","진주","의령함양 T/L","154kV 의령-함양T/L 전선교체","교체구간 : 116~125호","2016-03-19 08:00","2016-03-20 19:00","2016-03-19 08:00","2016-03-20 19:00","연속",null,null,null,201601140078,"-"]
[251,"경남","진주","의령산청 T/L","154kV 의령-산청T/L 전선교체","교체구간 : 43-47호","2016-03-26 08:00","2016-03-27 19:00","2016-03-26 08:00","2016-03-27 19:00","연속",null,null,null,201601140076,"-"]
[252,"경남","진주","의령함양 T/L","154kV 의령-함양T/L 전선교체","교체구간 : 43~47호, 56~57호","2016-03-26 08:00","2016-03-29 19:00","2016-03-26 08:00","2016-03-29 19:00","연속",null,null,null,201601140077,"-"]
[253,"경남","함안","진영한림정#1 T/L","154kV 진영-한림정#1T/L 정밀점검","154kV 진영-한림정#1T/L 정밀점검 1~13호(13기)","2016-03-26 08:30","2016-03-26 18:00","2016-03-26 08:30","2016-03-26 18:00","당일",null,null,null,201601060098,"-"]
[254,"경남","함안","진영한림정#2 T/L","154kV 진영-한림정#2T/L 정밀점검","154kV 진영-한림정#2T/L 정밀점검 1~13호(13기)","2016-03-27 08:30","2016-03-27 18:00","2016-03-27 08:30","2016-03-27 18:00","당일",null,null,null,201601060094,"-"]
[255,"경남","함안","한림정삼계#2 T/L","154kV한림정-삼계#2T/L 정밀점검 및 진영-한림정#1T/L안전이격","154kV한림정-삼계#2T/L 정밀점검 및 진영-한림정#1T/L안전이격","2016-03-26 08:30","2016-03-26 18:00","2016-03-26 08:30","2016-03-26 18:00","당일",null,null,null,201601060104,"-"]
[256,"경남","함안","한림정삼계#1 T/L","154kV한림정-삼계#1T/L 정밀점검 및 진영-한림정#2T/L안전이격","154kV한림정-삼계#1T/L 정밀점검 및 진영-한림정#2T/L안전이격","2016-03-27 08:30","2016-03-27 18:00","2016-03-27 08:30","2016-03-27 18:00","당일",null,null,null,201601060110,"-"]

{"sheet":"한수원","index":3,"n_rows":14,"n_cols":14,"rows_kept":14,"cut":false,"hidden":false,"merged":[[11,10,12,10],[11,11,12,11],[11,12,12,12],[11,13,12,13],[10,0,10,1],[11,0,12,0],[11,1,12,1],[11,2,12,2],[11,3,12,3],[11,4,12,4],[11,5,12,5],[11,6,11,7],[11,8,11,9],[7,13,8,13],[7,5,8,5],[7,6,7,7],[7,8,7,9],[7,10,8,10],[7,11,8,11],[7,0,8,0],[7,1,8,1],[7,2,8,2],[7,3,8,3],[7,4,8,4],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[7,12,8,12],[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7]]}
["2016년도 3월휴전계획표(한국수력원자력)"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","신고리2발전소","#3 주변압기","신고리3호기 출력상승시험(PAT) 및 간이예방정비 \n* 조작차단기 : CB 8200, 8272","- Load Rejection Test(at 100%)\n- Loss of off-site Power Test\n- 주변압기 정밀점검/일반점검\n- 모선 소내전원 절체시험 등","2016-03-24 09:00\n(※ PAT 일정에 따라 변동)","2016-04-28 18:00","2016-03-24 09:00\n(※ PAT 일정에 따라 변동)","2016-04-28 18:00","연속","N"]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"월성본부","1발전소","#1 주변압기","월성 1호기  제23차 계획예방정비관련 주변압기/소내용변압기 점검\n* 조작차단기 : CB7200,7272","- 주변압기/소내용변압기 일반점검\n- 주발전기, 주/소내보조변압기 보호계전기 \n   정기시험(차단기 연동시험 포함)","2016-03-25 09:00","2016-04-08 18:00","2016-03-25\n09:00","2016-04-08\n18:00","연속","N"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"고리본부","신고리2발전소","#3 SAT","신고리3호기 출력상승시험(PAT) \n* 조작차단기 : CB 6400, 6472","- Loss of off-site Power Test\n","2016-03-24 09:00\n(※ PAT 일정에 따라 변동)","2016-03-25 18:00","2016-03-24 09:00\n(※ PAT 일정에 따라 변동)","2016-03-25 18:00","연속","N"]