{"text_format":"2","workbook":"xlsx","n_sheets":8,"sheets":["765송부","345송부","154송부","중부","동서","서부","수자원","남부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":20,"n_cols":16,"rows_kept":20,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 4월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #2 M.Tr A-1","신가평S/S #2 M.Tr(362kV GIS 정밀점검)","신가평S/S #2 M.Tr(362kV GIS 정밀점검)","2016-04-18 08:00","2016-04-24 18:00","2016-04-18 08:00","2016-04-24 18:00","연속",null,null,null,201602150509]
[2,"경기북부","구리","신가평S/S #3 M.Tr A-1","신가평S/S #3 M.Tr(362kV GIS 정밀점검)","신가평S/S #3 M.Tr(362kV GIS 정밀점검)","2016-04-25 08:00","2016-05-01 18:00","2016-04-25 08:00","2016-05-01 18:00","연속",null,null,null,201602150510]
[3,"경기","성남","신안성S/S #5 M.Tr A-1","신안성S/S 765kV #5 M.Tr","신안성S/S 765kV #5 M.Tr 장경간 GIB 스페이서 구조개선","2016-04-18 10:00","2016-05-30 18:00","2016-04-18 10:00","2016-05-30 18:00","연속",null,null,null,201602020159]
[4,"강원","태백","신태백S/S 신태백-신가평#1T/L CB(8571)","신태백S/S 765kV SW 증설공사","765kV 신태백-신가평#1T/L 가압에 따른 8571CB 휴전","2016-04-28 09:00","2016-05-11 18:00","2016-04-28 09:00","2016-05-11 18:00","연속",null,null,null,201602170024]
[5,"강원","태백","신태백-신가평#2T/L-#3 M.Tr 1차 CB","신태백S/S 800kV GIS 정밀점검공사[8400]","신태백S/S 800kV GIS 정밀점검공사[8400]","2016-04-14 09:00","2016-04-28 18:00","취소","취소","연속",null,null,null,201602120469]
[6,"강원","태백","신태백S/S 신태백-신가평#2T/L CB","신태백S/S 800kV GIS 정밀점검공사[8471]","신태백S/S 800kV GIS 정밀점검공사[8471]","2016-04-14 09:00","2016-04-28 18:00","취소","취소","연속",null,null,null,201602120467]
[7,"강원","태백","신태백신가평#2 T/L","765KV 신태백변전소 송전선로 인출정비공사","1.선로길이 : 1.28km, 철탑 2기 신설, 1기 보강 2.구간 : (기설)신태백-신가평T/L No.2~신태백S/S~(기설)신태백-신한울NP T/L No.86","2016-04-14 09:00","2016-04-27 18:00","2016-04-14 09:00","2016-04-27 18:00","연속",null,null,"신뢰도개선",201601270104]
[8,"강원","태백","신태백신가평#1 T/L","765KV 신태백변전소 송전선로 인출정비공사","1.선로길이 : 1.28km, 철탑 2기 신설, 1기 보강 2.구간 : (기설)신태백-신가평T/L No.2~신태백S/S~(기설)신태백-신한울NP T/L No.86","2016-04-28 09:00","2016-05-11 18:00","2016-04-28 09:00","2016-05-11 18:00","연속",null,null,"신뢰도개선",201601270105]
[9,"강원","태백","신태백S/S TIE-#4 M.Tr 1차 CB","신태백S/S 765kV SW 증설공사","765kV 신태백-신가평#1T/L 이설에 따른 8500CB 휴전","2016-04-28 09:00","2016-05-11 18:00","2016-04-28 09:00","2016-05-11 18:00","연속",null,null,null,201602170023]
[10,"강원","태백","신태백S/S 신태백-신가평#1T/L CB","신태백S/S 800kV GIS 정밀점검공사[8371]","신태백S/S 800kV GIS 정밀점검공사[8371]","2016-04-29 09:00","2016-05-13 18:00","취소","취소","연속",null,null,null,201602120470]
[11,"강원","태백","신태백-신가평#1T/L-#2 M.Tr 1차 CB","신태백S/S 800kV GIS 정밀점검공사[8300]","신태백S/S 800kV GIS 정밀점검공사[8300]","2016-04-29 09:00","2016-05-13 18:00","취소","취소","연속",null,null,null,201602120471]
[12,"대전충남","서산","당진T/P 10호기 1차 CB","2016년 서산P/O 765/345kV GIS 점검공사","○765kV GIS 보통점검","2016-04-14 09:00","2016-04-15 18:00","2016-04-14 09:00","2016-04-15 18:00","연속",null,null,null,201602140089]
[13,"대전충남","서산","신서산S/S 신서산신안성#1T/L-# M.Tr 1차CB","2016년 서산P/O 765/345kV GIS 점검공사","○765kV GIS 보통점검","2016-04-20 09:00","2016-04-21 18:00","2016-04-20 09:00","2016-04-21 18:00","연속",null,null,null,201602140091]
[14,"대전충남","서산","신서산S/S #4 M.Tr 1차 CB","2016년 서산P/O 765/345kV GIS 점검공사","○765kV GIS 보통점검","2016-04-18 09:00","2016-04-19 18:00","2016-04-18 09:00","2016-04-19 18:00","연속",null,null,null,201602140090]
[15,"부산울산","동부산","북경남신고리NP#1 T/L","2016년도 가공송전 위탁공사","□ 765kV 북경남-신고리T/L 초기점검 - 작업구간: 신고리S/S ~ 39호(전원측)","2016-04-11 08:00","2016-04-16 18:00","2016-04-11 08:00","2016-04-16 18:00","연속",null,null,null,201602110069]
[16,"부산울산","동부산","신고리N/P #2Tie-Tr","765kV 신고리S/S #2M.Tr 이설공사","제작사 하자처리 - C상 리액터 유온도계 교체 - 부싱 압력계 모니터 교체 - B상 부흐홀쯔 계전기 가스릴리즈 밸브 누유 처리 - RCP PNL AC, DC FUSE-> NFB 교체","2016-04-21 09:00","2016-04-22 18:00","2016-04-21 09:00","2016-04-22 18:00","연속",null,null,null,201602190001]

{"sheet":"345송부","index":1,"n_rows":147,"n_cols":16,"rows_kept":147,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 4월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","신양재S/S #1 M.Tr A","362kV GIS 정밀점검(신양재S/S #1M.Tr)","362kV GIS 정밀점검(신양재S/S #1M.Tr) - 170kV GIS 정밀점검 병행작업(장도영)","2016-04-18 09:00","2016-04-24 18:00","2016-04-23 09:00","2016-04-24 18:00","연속",null,null,null,201602160408]
[2,"남서울","강남","신양재S/S 345kV #2 BUS","362kV GIS 정밀점검(신양재S/S #2BUS)","362kV GIS 정밀점검(신양재S/S #2BUS) - 170kV GIS 정밀점검 병행작업(장도영)","2016-04-28 09:00","2016-05-01 18:00","취소","취소","연속",null,null,null,201602160411]
[3,"남서울","강남","신양재S/S 345kV #2 BUS","362kV GIS 정밀점검(신양재S/S #2BUS)","362kV GIS 정밀점검(신양재S/S #2BUS) - 170kV GIS 정밀점검 병행작업(장도영)","2016-04-20 09:00","2016-04-24 18:00","취소","취소","연속",null,null,null,201602160409]
[4,"남서울","강남","신양재S/S #2 M.Tr A","362kV GIS 정밀점검(신양재S/S #2M.Tr)","362kV GIS 정밀점검(신양재S/S #2M.Tr) - 170kV GIS 정밀점검 병행작업(장도영)","2016-04-25 09:00","2016-05-01 18:00","2016-04-26 09:00","2016-04-28 18:00","연속",null,null,null,201602160410]
[5,"인천","인천","서인천C/C 345kV #4 Sh.R","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #4Sh.R CB 및 DS 대체","2016-04-25 09:30","2016-06-08 17:30","취소","취소","연속",null,null,null,201602040059]
[6,"인천","인천","서인천C/C 345kV #75 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 345kV #75BUS 현장개조 및 관련 DS 대체","2016-04-25 09:00","2016-06-08 18:00","취소","취소","연속",null,null,null,201602040058]
[7,"인천","인천","서인천C/C 345kV #4 Sh.R","서인천C/C 345kV #4 Sh.R 하자점검","서인천C/C 345kV #4 Sh.R 하자점검","2016-04-11 09:00","2016-04-11 18:00","2016-04-11 09:00","2016-04-11 18:00","당일",null,null,null,201602050100]
[8,"인천","인천","신가좌S/S #4 M.Tr A","신가좌S/S 362kV 장기 사용 GIS 대체 공사","신가좌S/S 362kV 장기 사용 GIS 대체 공사(7600,7672)","2016-04-18 09:00","2016-06-30 18:00","2016-04-18 09:00","2016-06-30 18:00","연속",null,null,null,201602040014]
[9,"인천","인천","신경서신인천CC T/L","345kV신경서-신인천CC T/L 중간접속함 교체공사","○ 교체대상 : J/B#1 (1B,2B) 교체","2016-04-14 09:00","2016-04-23 18:00","2016-04-26 09:00","2016-05-05 18:00","연속",null,null,"신뢰도개선",201602020004]
[10,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S #2M.Tr OFU 필터교체","신부평S/S #2M.Tr OFU 필터교체","2016-04-04 08:00","2016-04-04 18:00","2016-04-04 08:00","2016-04-04 18:00","당일",null,null,null,201602160159]
[11,"인천","직할","서인천CC신부평#2 T/L","절연유 채취(345kV 서인천CC-신부평#2T/L)","시행근거 : 지중송전업무기준(제22차) 대상선로 : 345kV 서인천CC-신부평#2T/L 시행내용 : OF케이블 내 절연유 채취","2016-04-18 09:00","2016-04-19 18:00","2016-04-18 09:00","2016-04-19 18:00","연속",null,null,null,201602040050]
[12,"인천","직할","서인천CC신부평#3 T/L","절연유 채취(345kV 서인천CC-신부평#3T/L)","시행근거 : 지중송전업무기준(제22차) 대상선로 : 345kV 서인천CC-신부평#3T/L 시행내용 : OF케이블 내 절연유 채취","2016-04-20 09:00","2016-04-21 18:00","2016-04-20 09:00","2016-04-21 18:00","연속",null,null,null,201602040051]
[13,"인천","직할","서인천CC신부평#4 T/L","절연유 채취(345kV 서인천CC-신부평#4T/L)","시행근거 : 지중송전업무기준(제22차) 대상선로 : 345kV 서인천CC-신부평#4T/L 시행내용 : OF케이블 내 절연유 채취","2016-04-22 09:00","2016-04-23 18:00","2016-04-22 09:00","2016-04-23 18:00","연속",null,null,null,201602040052]
[14,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S #3M.Tr OFU 필터교체","신부평S/S #3M.Tr OFU 필터교체","2016-04-05 08:00","2016-04-05 18:00","2016-04-05 08:00","2016-04-05 18:00","당일",null,null,null,201602160161]
[15,"경기북부","구리","미금S/S STATCOM <CB>","미금S/S STATCOM 정기점검","○미금S/S STATCOM 정기점검 - 사유 : 주기도래 정기점검 시행","2016-04-04 09:00","2016-04-22 18:00","2016-04-04 09:00","2016-04-22 18:00","연속",null,null,null,201602120575]
[16,"경기북부","구리","신가평미금#1 T/L","345kV 신가평-신의정부#2T/L 정밀점검","- No..1~98 정밀점검","2016-04-25 09:00","2016-04-25 18:00","취소","취소","당일",null,null,null,201601180054]
[17,"경기북부","구리","신가평신의정부#1 T/L","345kV 신가평-신의정부#1T/L 정밀점검","- No..1~98 정밀점검","2016-04-18 09:00","2016-04-23 18:00","2016-04-18 09:00","2016-04-23 18:00","연속",null,null,null,201601130235]
[18,"경기북부","구리","신가평미금#2 T/L","345kV 신가평-신의정부#1T/L 정밀점검","- No..1~98 정밀점검","2016-04-18 09:00","2016-04-18 18:00","2016-04-18 09:00","2016-04-18 18:00","당일",null,null,null,201601180052]
[19,"경기북부","구리","신가평미금#1 T/L","345kV 신가평-신의정부#2T/L 정밀점검","- No..1~98 정밀점검","2016-04-25 09:00","2016-04-25 18:00","2016-04-25 09:00","2016-04-25 18:00","당일",null,null,null,201601180054]
[20,"경기북부","직할","신포천동두천복합#1 T/L","신포천동두천복합#1 T/L","2016~17년도 직할 변전협력회사 총액공사 - GIS 초기점검","2016-04-11 10:00","2016-04-11 18:00","2016-04-11 10:00","2016-04-11 18:00","당일",null,null,null,201602160136]
[21,"경기북부","직할","신포천동두천복합#2 T/L","신포천동두천복합#2 T/L","2016~17년도 직할 변전협력회사 총액공사 - GIS 초기점검","2016-04-12 10:00","2016-04-12 18:00","2016-04-12 10:00","2016-04-12 18:00","당일",null,null,null,201602160137]
[22,"경기북부","파주","신덕은S/S #3 M.Tr A","신덕은S/S #3M.Tr 3차 GPT 교체공사(변전협력회사 총액공사)","신덕은S/S #3M.Tr 3차 GPT 교체","2016-04-14 10:00","2016-04-15 18:00","2016-04-28 10:00","2016-04-29 18:00","연속",null,null,null,201602190025]
[23,"경기북부","파주","신파주신덕은#2 T/L","345kV 신파주-신덕은T/L 항공장애표시구 교체공사","No.22호 항공장애표시구 소음민원 관련 교체공사","2016-04-15 09:00","2016-04-15 18:00","2016-04-15 09:00","2016-04-15 18:00","당일",null,null,null,201602160104]
[24,"경기북부","파주","신덕은동두천복합#2 T/L","2016년 신덕은S/S 362kV 7400GIS 정밀점검공사","2016년 신덕은S/S 362kV 7400GIS 정밀점검공사","2016-04-21 09:00","2016-04-23 18:00","취소","취소","연속",null,null,null,201602160327]
[25,"경기북부","파주","신덕은S/S #4 M.Tr A","2016년 신덕은S/S 362kV #4M.Tr 1차 GIS 정밀점검공사","2016년 신덕은S/S 362kV #4M.Tr 1차 GIS 정밀점검공사","2016-04-18 09:00","2016-04-22 18:00","취소","취소","연속",null,null,null,201601130260]
[26,"경기북부","파주","신덕은S/S 345kV #2 BUS","2016년 신덕은S/S 362kV #4M.Tr 1차 GIS 정밀점검공사","2016년 신덕은S/S 362kV #4M.Tr 1차 7452DS 정밀점검","2016-04-18 09:00","2016-04-19 18:00","취소","취소","연속",null,null,null,201601130262]
[27,"경기북부","파주","신김포신파주#2 T/L","345kV 신김포-신파주T/L 정밀점검","구간 : No.5~36","2016-04-25 08:00","2016-04-29 18:00","취소","취소","매일",null,null,"신뢰도개선",201602160100]
[28,"경기북부","파주","신파주S/S 345kV #70 BUS","2016년 파주전력 362kV 신파주-양주#1T/L GIS 정밀점검공사","2016년 파주전력 362kV 신파주-양주#1T/L 7351DS 정밀점검","2016-04-25 09:00","2016-04-29 18:00","2016-04-25 09:00","2016-04-29 18:00","연속",null,null,null,201601130256]
[29,"경기북부","파주","신파주양주#2 T/L","345kV 신김포-신파주T/L 정밀점검 (하단선로 병행휴전)","신김포-신파주 정밀점검 구간 : No.5~36","2016-04-18 08:00","2016-04-22 18:00","취소","취소","매일",null,null,null,201602160102]
[30,"경기북부","파주","신김포신파주#1 T/L","345kV 신김포-신파주T/L 정밀점검","구간 : No.5~36","2016-04-18 08:00","2016-04-22 18:00","취소","취소","매일",null,null,"신뢰도개선",201602160099]
[31,"경기북부","파주","신김포신파주#1 T/L","345kV 신김포-신파주T/L 정밀점검","구간 : No.5~36","2016-04-18 08:00","2016-04-22 18:00","취소","취소","매일",null,null,null,201602160099]
[32,"경기북부","파주","신파주양주#1 T/L","345kV 신김포-신파주T/L 정밀점검 (하단선로 병행휴전)","신김포-신파주 정밀점검 구간 : No.5~36","2016-04-25 08:00","2016-04-29 18:00","2016-04-25 08:00","2016-04-29 18:00","연속",null,null,null,201602160101]
[33,"경기북부","파주","신파주S/S #3 M.Tr A","신파주S/S 345kV #3M.Tr 정밀점검공사","신파주S/S 345kV #3M.Tr 정밀점검공사","2016-04-18 09:00","2016-04-21 18:00","2016-04-04 09:00","2016-04-07 18:00","연속",null,null,null,201602160392]
[34,"경기북부","구리","신가평신의정부#2 T/L","345kV 신가평-신의정부#2T/L 정밀점검","- No..1~98 정밀점검","2016-04-25 09:00","2016-04-30 18:00","2016-04-25 09:00","2016-04-30 18:00","연속",null,null,null,201601130236]
[35,"경기","군포","화성서서울#2 T/L","345kV 화성-서서울T/L 41호 등 3기 안전이격확보공사","- 대상 : 41, 61, 62호 - 내용 : 철탑상향(인클로징 공법)","2016-04-16 07:00","2016-04-20 19:00","2016-04-25 07:00","2016-04-30 19:00","연속",null,null,null,201602120612]
[36,"경기","군포","신온양서서울#1 T/L","345kV 아산-화성 등 2개T/L 지장철탑 이설공사","345kV 신온양-서서울T/L 지장철탑 이설 휴전작업 관형주 2기 설치 후 가선로 구성 3기 철거(No.28~No.31)","2016-04-06 07:00","2016-04-11 18:00","2016-04-06 07:00","2016-04-11 18:00","연속",null,null,null,201601280022]
[37,"경기","군포","화성서서울#1 T/L","345kV 화성서서울T/L 지장철탑이설공사 48호","345kV 화성서서울T/L 지장철탑이설공사 48호 #1T/L 철탑연긴선작업 (41~50호)","2016-04-05 07:00","2016-04-15 19:00","2016-04-14 07:00","2016-04-24 19:00","연속",null,null,null,201602150277]
[38,"경기","성남","서안성S/S #2 M.Tr A","서안성S/S 345kV #2M.Tr","서안성S/S 345kV #2M.Tr 보통점검 7300,7372,6244 GIS 보통점검 C상 누유점검","2016-04-23 10:00","2016-04-24 18:00","2016-04-23 10:00","2016-04-24 18:00","연속",null,null,null,201602020186]
[39,"경기","성남","서안성S/S #3 M.Tr A","서안성S/S 345kV #3 M.Tr","서안성S/S 345kV #3 M.Tr 보통점검 7472,7400,6344 보통점검","2016-04-02 10:00","2016-04-03 18:00","2016-04-02 10:00","2016-04-03 18:00","연속",null,null,"신뢰도개선",201602020140]
[40,"경기","성남","신시흥신성남#1 T/L","345kV 신시흥-신성남T/L 애자련보강공사","- 대상 : 49, 50호 - 내용 : 1련→2련 현수","2016-04-02 07:00","2016-04-02 19:00","2016-04-02 07:00","2016-04-02 19:00","당일",null,null,null,201602120598]
[41,"경기","성남","신시흥신성남#2 T/L","345kV 신시흥-신성남T/L 애자련보강공사","- 대상 : 49, 50호 - 내용 : 1련→2련 현수","2016-04-03 07:00","2016-04-03 19:00","2016-04-03 07:00","2016-04-03 19:00","당일",null,null,null,201602120600]
[42,"경기","성남","신안성신성남#2 T/L","유사 고장예방 케이블 교체공사(345kV 신안성-신성남#2T/L)","- 공사목적 : 케이블 고장(신김포-신파주, 신김포-신인천CC T/L)관련 유사고장 예방을 위한 규격개정 이전 및 제조불량 동일Lot 케이블 교체 - 대상선로 : 신안성-신성남#2T/L - 교체대상 : 광복합 케이블 1,692m, 일반케이블 449m, 광복합 접속함 6SET, 일반 접속함 2SET - 향후계획 : 제조불량 타 케이블 순차적 교체 시행(","2016-04-06 09:00","2016-05-08 18:00","2016-04-06 09:00","2016-05-08 18:00","연속",null,null,null,201602040064]
[43,"경기","성남","신성남S/S #1M.Tr A","신성남S/S SIS 하자보수건","#1M.Tr 3차 SIS PT 교체(BIL 125kV-&gt150kV)","2016-04-23 09:00","2016-04-23 18:00","2016-04-23 09:00","2016-04-23 18:00","당일",null,null,null,201602150415]
[44,"경기","성남","신성남S/S #4M.Tr A","신성남S/S 345kV #4M.Tr","신성남S/S 345kV #4M.Tr 2,3차 LA 하자점검","2016-04-12 10:00","2016-04-12 18:00","2016-04-12 10:00","2016-04-12 18:00","당일",null,null,null,201602020142]
[45,"경기","성남","동서울신용인#1 T/L","345kV 신용인-동서울#1/L 피뢰기 점검","345kV 신용인-동서울#1/L C/H #67,68 피뢰기 점검(6상)","2016-04-18 09:00","2016-04-19 18:00","2016-04-18 09:00","2016-04-19 18:00","연속",null,null,null,201602120087]
[46,"경기","성남","신용인S/S #1 M.Tr A","345kV 신용인S/S 용량부족 GIS 대체공사","345kV #1M.Tr 인출변경 345kV GIS (63kA 6300A)설치 * 3CB 용량대체","2016-04-09 09:00","2016-04-16 18:00","2016-04-09 09:00","2016-04-16 18:00","연속",null,null,null,201601140108]
[47,"경기","성남","동서울신용인#2 T/L","345kV 신용인S/S 용량부족 GIS 대체공사","345kV 신용인-동서울#2T/L 인출변경 345kV GIS (63kA 6300A)설치 * 3CB 용량대체","2016-04-09 09:00","2016-04-16 18:00","2016-04-09 09:00","2016-04-16 18:00","연속",null,null,null,201601140107]
[48,"경기","성남","신용인S/S #2 M.Tr A","신용인S/S 345kV #2M.Tr","신용인S/S 345kV #2M.Tr 7472 GIS 초기점검 6244 GIS 보통점검, 비상트립장치","2016-04-26 10:00","2016-04-26 18:00","2016-04-26 10:00","2016-04-26 18:00","당일",null,null,null,201602020192]
[49,"경기","직할","화성평택TP#2 T/L","345kV 화성평택T/P#2T/L","화성S/S 345kV 화성평택T/P#2T/L 7671,7600 정밀점검","2016-04-18 09:00","2016-04-22 18:00","2016-04-18 09:00","2016-04-22 18:00","연속",null,null,null,201602120698]
[50,"경기","직할","화성S/S #4 M.Tr A","화성S/S 345kV #4 M.Tr","화성S/S 345kV #4 M.Tr 보통, 1차 GIS 보통, 3차 PT보통","2016-04-09 09:00","2016-04-10 18:00","2016-04-09 09:00","2016-04-10 18:00","연속",null,null,null,201602120722]
[51,"경기","직할","화성신시흥 T/L","345kV 화성신시흥T/L","화성S/S 345kV 화성신시흥T/L 7871,7800 정밀점검","2016-04-23 09:00","2016-04-27 18:00","2016-04-23 09:00","2016-04-27 18:00","연속",null,null,null,201602120710]
[52,"강원","강릉","동해양양PP T/L","2016~17년 송전정비 협력회사 총액공사","○ 345kV 동해-양양PP T/L 피뢰기 설치공사(No.1~218) ○ 345kV 동해-양양PP T/L 전선접속개소 교체공사(No.162~164)","2016-04-21 08:00","2016-05-12 18:00","2016-04-21 08:00","2016-05-12 18:00","연속",null,null,null,201602030049]
[53,"강원","동해","신제천동해#1 T/L","345kV 신제천-동해T/L 스페이서댐퍼 교체","1. No.8~39 스페이서댐퍼교체 2. No.2~6 송전선로용 피뢰기 설치","2016-04-18 07:00","2016-04-23 18:00","2016-04-18 07:00","2016-04-23 18:00","매일",null,null,null,201602110273]
[54,"강원","동해","신제천동해#2 T/L","345kV 신제천-동해T/L 스페이서댐퍼 교체","1. No.8~39 스페이서댐퍼교체 2. No.2~6 송전선로용 피뢰기 설치","2016-04-25 07:00","2016-04-30 18:00","2016-04-25 07:00","2016-04-30 18:00","매일",null,null,null,201602110274]
[55,"충북","직할","신제천S/S 345kV #1 BUS","신제천S/S GIS화 공사","345kV GIS 모선조립 안전공간 확보","2016-04-18 08:00","2016-04-22 18:00","2016-04-25 08:00","2016-04-29 18:00","매일",null,null,null,201602170157]
[56,"충북","직할","신제천S/S #1 M.Tr A","345kV 신제천S/S GIS화 공사","154kV GIS 붓싱 설치 (안전이격 확보)","2016-04-16 09:00","2016-04-16 18:00","2016-04-16 09:00","2016-04-16 18:00","당일",null,null,null,201602260077]
[57,"충북","청주","신옥천S/S #1 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-04-18 09:00","2016-04-20 18:00","2016-04-18 09:00","2016-04-20 18:00","연속",null,null,null,201512140043]
[58,"충북","청주","신옥천S/S #2 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-04-21 09:00","2016-04-23 18:00","2016-04-21 09:00","2016-04-23 18:00","연속",null,null,null,201512140044]
[59,"충북","청주","신옥천S/S #3 M.Tr A","신옥천S/S 345kV 차단기 용량부족대체공사","-345kV CB 18대 철거 18CB 설치 - 기타부대공사","2016-04-24 09:00","2016-04-26 18:00","2016-04-24 09:00","2016-04-26 18:00","연속",null,null,null,201512140045]
[60,"충북","청주","신옥천청원#1 T/L","345kV 세종분기T/L 건설공사","신설선로 연결","2016-04-02 09:00","2016-04-06 17:00","2016-04-02 09:00","2016-04-06 17:00","연속",null,null,null,201601130202]
[61,"충북","청주","청원신진천#1 T/L","16년 청주전력지사 변전협력회사 총액공사","청원S/S 청원-신진천#1 T/L GIS, LA 보통점검","2016-04-12 09:00","2016-04-12 18:00","2016-04-12 09:00","2016-04-12 18:00","당일",null,null,null,201602140063]
[62,"충북","충주","신진천S/S #2 M.Tr A","345kV #2 M.Tr 정밀점검","주기도래 전력설비 정밀점검","2016-04-18 08:30","2016-05-13 18:00","2016-04-18 08:30","2016-05-13 18:00","연속",null,null,null,201602120918]
[63,"대전충남","대전","신계룡S/S #3 M.Tr A","○ 345kV 신계룡S/S #3M.Tr 보통점검","○ 345kV 신계룡S/S #3M.Tr 보통점검 ○ 345kV 신계룡S/S TIE-#3M.Tr 1차 7600 CB 보통점검 및 부분방전센서 설치 ○ 345kV 신계룡S/S #3M.Tr 1차 7672 CB 보통점검 및 부분방전센서 설치 ○ 154kV 신계룡S/S #3M.Tr 2차 6344 CB 보통점검","2016-04-25 09:00","2016-04-27 18:00","2016-04-25 09:00","2016-04-27 18:00","당일",null,null,null,201602190003]
[64,"대전충남","서산","북당진S/S 345kV #2 BUS","당진복합4호기용 345kV SW 증설공사","345kV 63kA 6300A * 4CB 증설 345kV 63kA 8000A Main Bus 증설 * 1식","2016-04-13 09:30","2016-04-16 17:30","2016-04-13 09:30","2016-04-16 17:30","연속",null,null,null,201602030065]
[65,"대전충남","서산","북당진S/S 345kV #1 BUS","당진복합4호기용 345kV SW 증설공사","345kV 63kA 6300A * 4CB 증설 345kV 63kA 8000A Main Bus 증설 * 1식","2016-04-18 09:30","2016-04-21 17:30","2016-04-18 09:30","2016-04-21 17:30","연속",null,null,null,201602030066]
[66,"대전충남","서산","개폐소-현대제철 T/L <CB>","345kV 신당진-태안화력T/L 선종교체공사","345kV 신당진-태안화력T/L OPGW 이설공사","2016-04-04 07:00","2016-04-05 18:00","2016-04-04 07:00","2016-04-05 18:00","연속",null,null,null,201602150319]
[67,"대전충남","서산","신당진S/S 345kV #70 BUS","70-71-1DS 단로기 가스누기보수","70-71-1 DS 구간 가스회수 및 오링교체 진공가스충진","2016-04-12 09:00","2016-04-12 18:00","2016-04-12 09:00","2016-04-12 18:00","당일",null,null,null,201601140105]
[68,"대전충남","서산","신당진S/S 345kV #71BUS","7801DS 단로기 가스누기보수","7801 DS 구간 가스회수 및 오링교체 진공가스충진","2016-04-11 09:00","2016-04-11 18:00","2016-04-11 09:00","2016-04-11 18:00","당일",null,null,null,201601140106]
[69,"대전충남","서산","신당진태안화력#1 T/L","345kV 신당진-태안화력T/L 선종교체공사","345kV 신당진-태안화력 #1T/L 인출변경","2016-04-02 07:00","2016-04-06 18:00","2016-04-02 07:00","2016-04-06 18:00","연속",null,null,null,201602150318]
[70,"대전충남","서산","신당진S/S #3 M.Tr A","16~17년 서산P/O 변전협력총액공사","○ 345kV #3M.Tr, 2차 GIS, 3차 CB 초기 및 3차 AL 모선 절연커버시공","2016-04-19 09:00","2016-04-21 18:00","2016-04-19 09:00","2016-04-21 18:00","연속",null,null,null,201602150451]
[71,"대전충남","서산","신서산S/S #4 M.Tr 2차 CB (7871)","2016년 서산P/O 765/345kV GIS 점검공사","○345kV GIS 정밀점검","2016-04-28 09:00","2016-04-30 18:00","2016-04-28 09:00","2016-04-30 18:00","연속",null,null,null,201602140093]
[72,"대전충남","서산","신서산S/S #3 M.Tr 2차 CB (7671)","2016년 서산P/O 765/345kV GIS 점검공사","○345kV GIS 정밀점검","2016-04-25 09:00","2016-04-27 18:00","2016-04-25 09:00","2016-04-27 18:00","연속",null,null,null,201602140092]
[73,"대전충남","아산","신온양S/S #2 M.Tr A","신온양S/S 345kV #2M.Tr 초기점검","○345kV #2M.Tr 및 기타부대설비 초기점검 ○345kV 7472, 7400 GIS 초기점검 ○154kV 6244 GIS 초기점검","2016-04-25 09:00","2016-04-26 18:00","2016-04-25 09:00","2016-04-26 18:00","연속",null,null,null,201602110139]
[74,"대전충남","아산","신온양S/S 신온양-신탕정 #1T/L - TIE CB (7900)","신온양S/S 345kV 7900 TIE GIS 보통점검","○345kV 7900 TIE GIS 보통점검","2016-04-13 09:00","2016-04-13 18:00","2016-04-13 09:00","2016-04-13 18:00","당일",null,null,null,201602110138]
[75,"대전충남","아산","신온양신탕정#2 T/L","154kV 신온양-한샘T/L 건설공사","□ 기설 154kV 신온양-한샘T/L 가압준비, 인출작업","2016-04-23 06:00","2016-04-23 20:00","2016-04-23 06:00","2016-04-23 20:00","당일",null,null,null,201601110038]
[76,"대전충남","아산","아산보령화력#1 T/L","345kV 아산-보령화력T/L 전선교체공사","345kV 아산보령화력#1T/L 전선교체 68.2km ACSR 480 -> HTACSR/AW","2016-04-08 07:00","2016-05-27 18:00","2016-04-08 07:00","2016-05-27 18:00","연속",null,null,null,201602110076]
[77,"전북","군산","군산S/S #2 M.Tr A","345kV 군산S/S #2M.Tr A","군산P/O 345kV 차단기 정밀점검공사 #2M.Tr 1차(7472) CB 차단기 정밀점검","2016-04-25 09:00","2016-04-29 18:00","2016-04-14 09:00","2016-04-27 18:00","연속",null,null,null,201602120028]
[78,"전북","군산","군산S/S #4 M.Tr A","345kV 군산S/S #4 M.Tr A","군산S/S M.Tr 3차측 절연보강공사 ○ 군산S/S M.Tr 3차측 절연보강공사 - 절연보강 : 24개소","2016-04-21 09:00","2016-04-22 18:00","2016-04-28 09:00","2016-04-29 18:00","연속",null,null,null,201601190059]
[79,"전북","군산","청양군산#1 T/L","345kV 군산S/S 청양군산#1T/L","군산P/O 345kV 차단기 정밀점검공사 청양-군산#1T/L(7371),청양-군산#1T/L-TIE(7300) CB 차단기 정밀점검","2016-04-02 09:00","2016-04-11 18:00","2016-04-02 09:00","2016-04-11 18:00","연속",null,null,null,201602120022]
[80,"전북","군산","청양군산#2 T/L","345kV 군산S/S 청양군산#2T/L","군산P/O 345kV 차단기 정밀점검공사 청양-군산#2T/L(7471),청양-군산#2T/L-#2M.Tr 1차(7400) CB 차단기 정밀점검","2016-04-14 09:00","2016-04-23 18:00","2016-04-14 09:00","2016-04-23 18:00","연속",null,null,null,201602120024]
[81,"전북","김제","신김제S/S #1 M.Tr A","신김제S/S #1 M.Tr A","변압기 보통점검 및 예비M.Tr 절체반 설치","2016-04-18 09:00","2016-04-20 18:00","2016-04-18 09:00","2016-04-20 18:00","연속",null,null,null,201601140090]
[82,"전북","김제","신김제S/S #3 M.Tr A","신김제S/S #3 M.Tr A","예비M.Tr 절체반 설치","2016-04-25 09:00","2016-04-26 18:00","2016-04-25 09:00","2016-04-26 18:00","연속",null,null,null,201601140092]
[83,"전북","김제","신김제S/S #4 M.Tr A","신김제S/S #4 M.Tr A","예비M.Tr 절체반 설치","2016-04-27 09:00","2016-04-28 18:00","2016-04-27 09:00","2016-04-28 18:00","연속",null,null,null,201601140093]
[84,"전북","김제","신김제S/S #2 M.Tr A","신김제S/S #2 M.Tr A","변압기 보통점검 및 예비M.Tr 절체반 설치","2016-04-21 09:00","2016-04-23 18:00","2016-04-21 09:00","2016-04-23 18:00","연속",null,null,null,201601140091]
[85,"광주전남","광주","신광주한빛NP#2 T/L","345kV 신광주-한빛NPT/L 전선접속개소해소공사","전선교체 7.5KM","2016-04-27 07:00","2016-05-08 18:00","취소","취소","연속",null,null,null,201602150707]
[86,"광주전남","광주","신광주한빛NP#1 T/L","345kV 신광주-한빛NPT/L 전선접속개소해소공사","전선교체 7.5KM","2016-04-15 07:00","2016-04-26 18:00","취소","취소","연속",null,null,null,201602150683]
[87,"광주전남","순천","광양여수TP T/L","345kV 광양-여수TP T/L(전선접속개소 해소공사)","345kV 광양-여수TP 등 6개 T/L 전선접속개소 해소공사 - 전력선 교체 : 35~42, 77~84, 90~94호","2016-04-01 07:00","2016-04-07 18:00","2016-04-01 07:00","2016-04-07 18:00","연속",null,null,null,201602120362]
[88,"광주전남","순천","광양율촌CC T/L","345kV 광양-율촌CC T/L(전선접속개소 해소공사)","345kV 광양-여수TP 등 6개 T/L 전선접속개소 해소공사 - 전력선 교체 : 77~84, 90~94, 94~98호","2016-04-08 07:00","2016-04-14 18:00","2016-04-08 07:00","2016-04-14 18:00","연속",null,null,null,201602120369]
[89,"광주전남","순천","율촌CC 여수TP T/L","345kV 율촌CC-여수TP T/L(전선접속개소 해소공사)","345kV 광양-여수TP 등 6개T/L 전선접속개소 해소공사 - 전력선 교체 : 35~42호","2016-04-15 07:00","2016-04-18 18:00","2016-04-15 07:00","2016-04-18 18:00","연속",null,null,null,201602120390]
[90,"광주전남","직할","한빛3N/P 한빛연락#3T/L-#2 SU Tr 1차 GIS","목포전력지사 2분기 362kV GIS 정밀점검","GIS 정밀점검","2016-04-04 09:00","2016-04-08 18:00","2016-04-04 09:00","2016-04-08 18:00","연속",null,null,null,201602160175]
[91,"대구경북","경산","신경산S/S 신경산-대구#1T/L-TIE CB (7100)","16년 경산P/O 362kV GIS 정밀점검(7100)","7100 CB부 정밀점검","2016-04-04 09:00","2016-04-06 18:00","2016-04-04 09:00","2016-04-06 18:00","연속",null,null,null,201602120347]
[92,"대구경북","경산","신경산대구#1 T/L","345kV 신경산-대구#1T/L 휴전(7100 CB 건전도 확인)","7100 CB부 정밀점검관련 건전도 확인용도","2016-04-06 14:00","2016-04-06 15:00","2016-04-06 14:00","2016-04-06 15:00","당일",null,null,null,201602120352]
[93,"대구경북","구미","북대구선산 T/L","345kV 선산S/S #4M.Tr 증설공사","345kV M.Tr * 1Bank 362kV GIS *2CCt 이설 362kV GIS *1CCt 설치 154kV GCB 1대 설치","2016-04-24 15:00","2016-04-30 15:00","2016-04-24 15:00","2016-04-30 15:00","연속",null,null,null,201602160264]
[94,"대구경북","구미","북대구선산 T/L","345kV 선산S/S #4M.Tr 증설공사","345kV M.Tr * 1Bank 362kV GIS *2CCt 이설 362kV GIS *1CCt 설치 154kV GCB 1대 설치","2016-04-15 15:00","2016-04-17 15:00","2016-04-15 15:00","2016-04-17 15:00","연속",null,null,null,201602110349]
[95,"대구경북","구미","선산S/S 345kV #2 BUS","345kV 선산S/S #4M.Tr 증설공사","345kV M.Tr * 1Bank 362kV GIS *2CCt 이설 362kV GIS *1CCt 설치 154kV GCB 1대 설치","2016-04-01 10:00","2016-04-17 18:00","2016-04-01 10:00","2016-04-17 18:00","연속",null,null,null,201602110048]
[96,"대구경북","달성","북경남고령#2 T/L","북경남-고령#2T/L 송전선로용 피뢰기 설치공사","- 북경남-고령#2T/L 송전선로용 피뢰기 설치 (1~39호)","2016-04-25 09:00","2016-05-04 18:00","2016-04-25 09:00","2016-05-04 18:00","연속",null,null,null,201602150043]
[97,"대구경북","달성","북경남대구#2 T/L","북경남-대구#2T/L 송전선로용 피뢰기 설치공사","- 북경남-대구#2T/L 송전선로용 피뢰기 설치 (1~39호)","2016-04-25 09:00","2016-05-04 18:00","2016-04-25 09:00","2016-05-04 18:00","연속",null,null,null,201602150044]
[98,"대구경북","영주","신영주S/S #1 M.Tr A","신영주S/S 362kV GIS화 공사","○ GIS 내압측정을 위한 안전이격 확보","2016-04-22 08:00","2016-04-22 18:00","2016-04-22 08:00","2016-04-22 18:00","당일",null,null,null,201602270003]
[99,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","○ GIS 내압측정을 위한 안전이격확보","2016-04-20 08:00","2016-04-22 18:00","2016-04-20 08:00","2016-04-22 18:00","연속",null,null,null,201602270004]
[100,"대구경북","영주","신영주S/S #3M.Tr A","신영주S/S 362kV GIS화 공사","○ GIS 내압측정을 위한 안전이격 확보","2016-04-20 08:00","2016-04-20 18:00","2016-04-20 08:00","2016-04-20 18:00","당일",null,null,null,201602270001]
[101,"대구경북","영주","신영주S/S #2 M.Tr A","신영주S/S 362kV GIS화 공사","○ GIS 내압측정을 위한 안전이격 확보","2016-04-21 08:00","2016-04-21 18:00","2016-04-21 08:00","2016-04-21 18:00","당일",null,null,null,201602270002]
[102,"대구경북","칠곡","북대구서대구#2 T/L","북대구S/S 345kV 북대구-서대구#2T/L GIS 정밀점검","7271, 7200, 7272 CB 정밀점검","2016-04-25 09:30","2016-05-03 18:00","2016-04-18 09:30","2016-04-23 18:00","연속",null,null,null,201602110255]
[103,"대구경북","칠곡","서대구S/S #1M.Tr A","#1M.Tr 초기점검 6144 하자점검 CVT 교체","#1M.Tr 초기점검 6144 하자점검 CVT 교체","2016-04-05 09:30","2016-04-06 18:00","2016-04-05 09:30","2016-04-06 18:00","연속",null,null,null,201602120466]
[104,"대구경북","포항","신포항청송PP T/L","345kV 영포T/L 전선접속개소 제거공사","No. 210~253, 259~267, 353~355 전선교체 : ACSR 480㎟(R) × 4B × 2C, 38.35C-km","2016-04-18 09:00","2016-05-08 18:00","2016-04-18 09:00","2016-05-08 18:00","연속",null,null,null,201602120828]
[105,"대구경북","포항","신포항신월성NP#1 T/L","345kV 신포항-신월성NP#1,2T/L 전력선교체공사","전력선교체:No.53~66, 철탑이설:No.56, 61","2016-04-16 08:00","2016-04-30 18:00","2016-04-16 08:00","2016-04-30 18:00","연속",null,null,null,201602110398]
[106,"대구경북","포항","신포항S/S #1 M.Tr A","신포항S/S #1M.Tr 관련설비 점검","M.Tr, 1,3차 PT, 1,2차 LA, 6144, 4179 CB 보통점검","2016-04-11 09:00","2016-04-12 18:00","2016-04-11 09:00","2016-04-12 18:00","연속",null,null,null,201602120864]
[107,"대구경북","포항","신포항신월성NP#2 T/L","345kV 신포항-신월성NP#1,2T/L 전력선교체공사","전력선교체:No.53~66, 철탑이설:No.56,61","2016-04-04 08:00","2016-04-18 18:00","2016-04-04 08:00","2016-04-18 18:00","연속",null,null,null,201602110394]
[108,"부산울산","동부산","신양산S/S 신양산-신대연#1T/L CB (7271)","신양산S/S 362kV 7271GIS 하자점검","신양산S/S 362kV 7271GIS 하자점검","2016-04-05 09:30","2016-04-05 17:00","2016-04-05 09:30","2016-04-05 17:00","당일",null,null,null,201602180184]
[109,"부산울산","동부산","신양산S/S 신양산-신대연#2T/L CB (7171)","신양산S/S 362kV 7171 GIS 보통점검","신양산S/S 362kV 7171 GIS 보통점검(신양산-신대연#2T/L CB)","2016-04-04 09:30","2016-04-04 17:00","2016-04-04 09:30","2016-04-04 17:00","당일",null,null,null,201602120613]
[110,"부산울산","동부산","신양산S/S 신양산-신대연#1T/L-TIE CB (7200)","신양산S/S 362kV 7200GIS 하자점검","신양산S/S 362kV 7200GIS 하자점검","2016-04-06 09:30","2016-04-06 17:00","2016-04-06 09:30","2016-04-06 17:00","당일",null,null,null,201602180186]
[111,"부산울산","북부산","북부산S/S 345kV #4 Sh.R <CB>","2016년 북부산변전협력회사 총액공사","#4Sh.R 및 7079 GIS하자점검","2016-04-11 09:00","2016-04-11 18:00","2016-04-11 09:00","2016-04-11 18:00","당일",null,null,null,201602160011]
[112,"부산울산","북부산","북부산S/S 북부산#1T/L-북신양#1T/L CB (7100)","2016년 북부산변전협력회사 총액공사","7100 GCB 보통점검","2016-04-07 10:00","2016-04-07 18:00","2016-04-07 10:00","2016-04-07 18:00","당일",null,null,null,201602160006,"○"]
[113,"부산울산","북부산","북부산S/S 신김해-북부산#2T/L(#2CLR) CB (7478)","2016년 북부산변전협력회사 총액공사","7478 GIS 보통점검","2016-04-22 09:00","2016-04-22 18:00","2016-04-22 09:00","2016-04-22 18:00","당일",null,null,null,201602160015]
[114,"부산울산","북부산","북부산S/S 서부산#3T/L-서부산#2T/L CB (7800)","2016년 북부산변전협력회사 총액공사","7800 GIS 보통점검","2016-04-06 10:00","2016-04-06 18:00","2016-04-06 10:00","2016-04-06 18:00","당일",null,null,null,201602160005]
[115,"부산울산","북부산","북부산S/S 70-71 BUS-SEC CB (70-71-0)","2016년 북부산변전협력회사 총액공사","GIS 하자점검","2016-04-14 09:00","2016-04-14 18:00","2016-04-14 09:00","2016-04-14 18:00","당일",null,null,null,201602160012]
[116,"부산울산","북부산","신김해북부산#1 T/L","345kV 북부산-울산TP 등 2개T/L 피뢰기 설치공사","345kV 신김해-해북T/L 피뢰기 설치공사 (1호~57호, 62기)","2016-04-18 08:00","2016-04-29 18:00","2016-04-18 08:00","2016-04-29 18:00","연속",null,null,null,201602120124]
[117,"부산울산","북부산","북부산S/S 75-76 BUS-SEC CB (75-76-0)","2016년 북부산변전협력회사 총액공사","GIS 하자점검","2016-04-15 09:00","2016-04-15 18:00","2016-04-15 09:00","2016-04-15 18:00","당일",null,null,null,201602160013]
[118,"부산울산","북부산","북부산S/S 서부산-북부산#3T/L Sh.R <CB>","2016년 북부산변전협력회사 총액공사","#3Sh.R 및 7977 GIS하자점검","2016-04-12 09:00","2016-04-12 18:00","2016-04-12 09:00","2016-04-12 18:00","당일",null,null,null,201602160008]
[119,"부산울산","북부산","북부산S/S 신김해-북부산#1T/L(#1CLR) CB (7378)","2016년 북부산변전협력회사 총액공사","7378 GIS 보통점검","2016-04-21 09:00","2016-04-21 18:00","2016-04-21 09:00","2016-04-21 18:00","당일",null,null,null,201602160014]
[120,"부산울산","울산","신온산S/S 신온산-울산TPT/L CB (7471)","2016-17년 울산전력지사 변전협력회사 총액공사","7471 GIS 보통점검","2016-04-12 09:00","2016-04-12 18:00","2016-04-12 09:00","2016-04-12 18:00","당일",null,null,null,201602150104]
[121,"부산울산","울산","신온산S/S 신온산T/L-TIE CB (7300)","2016-17년 울산전력지사 변전협력회사 총액공사","7300 GIS 보통점검","2016-04-11 09:00","2016-04-11 18:00","2016-04-11 09:00","2016-04-11 18:00","당일",null,null,null,201602150102]
[122,"부산울산","울산","신울산신온산#2 T/L","2016년 가공송전 순시점검 위탁공사(울산전력지사)","송전선로 초기점검 : 22기","2016-04-21 09:00","2016-04-22 18:00","2016-04-21 09:00","2016-04-22 18:00","연속",null,null,null,201602150379]
[123,"부산울산","울산","신울산신온산#1 T/L","345kV 신울산-신온산T/L 송전용 피뢰기 설치공사","345kV 신울산-신온산T/L 송전용 피뢰기 설치(1~22호), 66SET 설치","2016-04-26 09:00","2016-04-28 18:00","2016-04-26 09:00","2016-04-28 18:00","연속",null,null,null,201602030051]
[124,"부산울산","울산","신울산신온산#1 T/L","345kV 신울산-신온산T/L 송전용 피뢰기 설치공사","345kV 신울산-신온산T/L 송전용 피뢰기 설치(1~22호), 66SET 설치","2016-04-26 09:00","2016-04-28 18:00","취소","취소","연속",null,null,null,201602030051]
[125,"부산울산","울산","신울산S/S 동울산-신울산#2T/L CB (7972)","2016-17년 울산전력지사 변전협력회사 총액공사","7972 GIS 하자점검","2016-04-18 09:00","2016-04-18 18:00","2016-04-18 09:00","2016-04-18 18:00","당일",null,null,null,201602150113]
[126,"경남","직할","신김해S/S #4 M.Tr A","신김해S/S 진례전철 #1T/L GIS 정밀점검","신김해S/S 진례전철 #1T/L GIS 정밀점검 시험가압","2016-04-21 16:30","2016-04-21 17:30","2016-04-21 16:30","2016-04-21 17:30","당일",null,null,null,201602170148]
[127,"경남","직할","신김해S/S #4 M.Tr A","신김해S/S 진례전철 #1T/L GIS 정밀점검","신김해S/S 진례전철 #1T/L GIS 정밀점검 시험가압","2016-04-23 16:30","2016-04-23 17:30","2016-04-23 16:30","2016-04-23 17:30","당일",null,null,null,201602170149]
[128,"경남","직할","신김해S/S #4 M.Tr A","신김해S/S 진례전철 #2T/L GIS 정밀점검","신김해S/S 진례전철 #2T/L GIS 정밀점검 시험가압","2016-04-25 16:30","2016-04-25 17:30","2016-04-25 16:30","2016-04-25 17:30","당일",null,null,null,201602170150]
[129,"경남","직할","신김해S/S #4 M.Tr A","신김해S/S 진례전철 #2T/L GIS 정밀점검","신김해S/S 진례전철 #2T/L GIS 정밀점검 시험가압","2016-04-27 16:30","2016-04-27 17:30","2016-04-27 16:30","2016-04-27 17:30","당일",null,null,null,201602170151]
[130,"경남","직할","신김해삼천포화력#2 T/L","345kV 신김해-삼천포화력T/L 전력선교체공사","345kV 신김해-삼천포화력T/L 전력선 교체공사(105~108, 159~160, 181~183, 201~202,207~208)","2016-04-14 08:00","2016-04-30 18:00","2016-04-14 08:00","2016-04-30 18:00","연속",null,null,null,201602120057]
[131,"경남","진주","의령S/S 신남원-의령#2T/L CB (7771)","신남원-의령#2T/L 7771 CB 정밀점검","신남원-의령#2T/L 7771 CB 정밀점검","2016-04-04 09:30","2016-04-06 18:30","2016-04-04 09:30","2016-04-06 18:30","연속",null,null,null,201602120116]
[132,"경남","진주","의령산청양수#2 T/L","345kV 의령-하동화력 등 3개T/L 송전선로용 피뢰기설치공사","345kV 의령-산청양수#2T/L 송전선로용 피뢰기설치공사 : 130기 / 390Set","2016-04-05 07:00","2016-04-30 20:00","2016-04-05 07:00","2016-04-30 20:00","연속",null,null,null,201602030014]
[133,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력 등 3개T/L 송전선로용 피뢰기설치공사","345kV 의령-하동화력T/L 송전선로용 피뢰기설치공사 : 152기 /456Set","2016-04-30 07:00","2016-05-01 20:00","2016-04-30 07:00","2016-05-01 20:00","연속",null,null,null,201602030013]
[134,"경남","진주","의령S/S 고령-의령#1T/L CB (7671)","고령-의령#1T/L 7671 CB 정밀점검","고령-의령#1T/L 7671 CB 정밀점검","2016-04-25 09:30","2016-04-27 18:30","2016-04-25 09:30","2016-04-27 18:30","연속",null,null,null,201602120128]
[135,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력 등 3개T/L 송전선로용 피뢰기설치공사","345kV 의령-하동화력T/L 송전선로용 피뢰기설치공사 : 152기 /456Set","2016-04-06 07:00","2016-04-12 20:00","2016-04-06 07:00","2016-04-12 20:00","연속",null,null,null,201602030011]
[136,"경남","진주","의령S/S 신남원-의령#2T/L-TIE CB (7700)","신남원-의령#2T/L 7700 CB 정밀점검","신남원-의령#2T/L 7700 CB 정밀점검","2016-04-11 09:30","2016-04-13 18:30","2016-04-11 09:30","2016-04-13 18:30","연속",null,null,null,201602120118]
[137,"경남","진주","의령S/S 의령-신마산#1T/L-TIE CB (7900)","의령-신마산#1T/L 7900 CB 정밀점검","의령-신마산#1T/L 7900 CB 정밀점검","2016-04-18 09:30","2016-04-20 18:30","2016-04-18 09:30","2016-04-20 18:30","연속",null,null,null,201602120122]
[138,"경남","진주","의령S/S 의령-신마산#1T/L CB (7971)","의령-신마산#1T/L 7971 CB 정밀점검","의령-신마산#1T/L 7971 CB 정밀점검","2016-04-21 09:30","2016-04-23 18:30","2016-04-21 09:30","2016-04-23 18:30","연속",null,null,null,201602120125]
[139,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력 등 3개T/L 송전선로용 피뢰기설치공사","345kV 의령-하동화력T/L 송전선로용 피뢰기설치공사 : 152기 /456Set","2016-04-24 07:00","2016-04-26 20:00","2016-04-24 07:00","2016-04-26 20:00","연속",null,null,null,201602030012]
[140,"경남","진주","하동T/P #4 M.Tr 1차 CB (7472)","하동T/P 74BF PNL 대체","하동T/P 74BF PNL 대체(4호기 Overhaul 기간 시행)","2016-04-18 09:30","2016-04-22 18:30","2016-04-18 09:30","2016-04-22 18:30","연속",null,null,null,201602160362]
[141,"경남","진주","의령하동화력#2 T/L","의령-하동T/P #2T/L CPD, LA 교체공사","의령-하동T/P #2T/L CPD, LA 교체공사","2016-04-05 09:30","2016-04-05 18:30","2016-04-05 09:30","2016-04-05 18:30","당일",null,null,null,201602120077]
[142,"경남","진주","하동T/P TIE-#4 M.Tr 1차 CB (7400)","하동T/P 74BF PNL 대체","하동T/P 74BF PNL 대체(4호기 Overhaul 기간 시행)","2016-04-18 09:30","2016-04-22 18:30","2016-04-18 09:30","2016-04-22 18:30","연속",null,null,null,201602160363]
["추가\n1","경남","진주","광양하동화력#1T/L","345kV 광양-하동화력 등 3개T/L 송전선로용 피뢰기설치공사","345kV 광양-하동화력T/L 송전선로용 피뢰기설치공사","2016-04-17 07:00","2016-04-18 20:00","2016-04-17 07:00","2016-04-18 20:00","연속"]

{"sheet":"154송부","index":2,"n_rows":287,"n_cols":16,"rows_kept":287,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 4월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성수뚝도#2 T/L","16년 성동 변전협력회사 총액공사 (뚝도S/S 성수뚝도#2T/L)","170kV GIS 보통점검 (뚝도S/S 성수뚝도#2T/L)","2016-04-15 10:00","2016-04-15 18:00","취소","취소","당일",null,null,"신뢰도 개선",201602150516,"-"]
[2,"서울","성동","금오상계#2 T/L","2016-17년 가공송전정비 협력회사 총액공사","스페이서 간격조정 : 등간격에서 이간격으로 조정","2016-04-01 09:00","2016-04-02 18:00","2016-04-01 09:00","2016-04-02 18:00","연속",null,null,null,201602180017,"-"]
[3,"서울","성동","휘경종암#2 T/L","16년 성동 변전협력회사 총액공사 (종암S/S 휘경종암#2T/L)","170kV GIS 초기점검 (종암S/S 휘경종암#2T/L)","2016-04-06 10:00","2016-04-06 18:00","2016-04-06 10:00","2016-04-06 18:00","당일",null,null,null,201602150810,"-"]
[4,"서울","성동","휘경종암#1 T/L","16년 성동 변전협력회사 총액공사 (종암S/S 휘경종암#1T/L)","170kV GIS 초기점검 (종암S/S 휘경종암#1T/L)","2016-04-05 10:00","2016-04-05 18:00","2016-04-05 10:00","2016-04-05 18:00","당일",null,null,null,201602150809,"-"]
[5,"서울","성동","방학창동#2 T/L","16년 성동 변전협력회사 총액공사 (창동S/S 방학창동#2T/L)","170kV GIS 하자점검 (창동S/S 방학창동#2T/L)","2016-04-08 10:00","2016-04-08 18:00","2016-04-08 10:00","2016-04-08 18:00","당일",null,null,null,201602150512,"-"]
[6,"서울","성동","방학창동#1 T/L","16년 성동 변전협력회사 총액공사 (창동S/S 방학창동#1T/L)","170kV GIS 하자점검 (창동S/S 방학창동#1T/L)","2016-04-07 10:00","2016-04-07 18:00","2016-04-07 10:00","2016-04-07 18:00","당일",null,null,null,201602150511,"○"]
[7,"서울","성동","창동돈암 T/L","16년 성동 변전협력회사 총액공사 (창동S/S 창동돈암T/L)","170kV GIS 하자점검 (창동S/S 창동돈암T/L)","2016-04-11 10:00","2016-04-11 18:00","2016-04-06 10:00","2016-04-06 18:00","당일",null,null,null,201602150813,"-"]
[8,"서울","직할","불광서대문#1 T/L","2016년 직할 변전협력회사 총액공사","불광서대문#1T/L GIS 및 PT 보통점검","2016-04-22 10:00","2016-04-22 18:00","2016-04-22 10:00","2016-04-22 18:00","당일",null,null,null,201602150706,"-"]
[9,"서울","직할","서소문S/S 154kV #1 BUS","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (순화서소문#2T/L, 종로서소문T/L GIS)","2016-04-27 10:00","2016-05-05 10:00","2016-04-27 10:00","2016-05-05 10:00","연속",null,null,null,201602150727,"-"]
[10,"서울","직할","서소문S/S 154kV #2 BUS","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (순화서소문#2T/L, 종로서소문T/L GIS)","2016-04-25 09:00","2016-04-27 10:00","2016-04-25 09:00","2016-04-27 10:00","연속",null,null,null,201602150726,"-"]
[11,"서울","직할","종로서소문 T/L","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (순화서소문#2T/L, 종로서소문T/L GIS)","2016-04-25 09:00","2016-05-14 18:00","2016-04-25 09:00","2016-05-14 18:00","연속",null,null,null,201602120392,"-"]
[12,"서울","직할","순화서소문#2 T/L","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (순화서소문#2T/L, 종로서소문T/L GIS)","2016-04-25 09:00","2016-05-14 18:00","2016-04-25 09:00","2016-05-14 18:00","연속",null,null,null,201602120389,"-"]
[13,"서울","직할","서소문S/S 154kV #2 BUS","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (154kV BUSTIE, 중앙서소문T/L GIS)","2016-04-14 10:00","2016-04-23 18:00","2016-04-14 10:00","2016-04-23 18:00","연속",null,null,null,201602150719,"-"]
[14,"서울","직할","서소문S/S 154kV #1 BUS","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (154kV BUSTIE, 중앙서소문T/L GIS)","2016-04-06 10:00","2016-04-14 10:00","2016-04-06 10:00","2016-04-14 10:00","연속",null,null,null,201602150717,"-"]
[15,"서울","직할","서소문S/S 154kV #1 BUS TIE CB","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (154kV BUSTIE, 중앙서소문T/L GIS)","2016-04-04 09:00","2016-04-23 18:00","2016-04-04 09:00","2016-04-23 18:00","연속",null,null,null,201602120380,"-"]
[16,"서울","직할","서소문S/S 154kV #2 BUS","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (154kV BUSTIE, 중앙서소문T/L GIS)","2016-04-04 09:00","2016-04-06 10:00","2016-04-04 09:00","2016-04-06 10:00","연속",null,null,null,201602150714,"-"]
[17,"서울","직할","중앙서소문 T/L","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (154kV BUSTIE, 중앙서소문T/L GIS)","2016-04-04 09:00","2016-04-23 18:00","2016-04-04 09:00","2016-04-23 18:00","연속",null,null,null,201602120385,"-"]
[18,"남서울","강남","신양재S/S 154kV #60 BUS","170kV GIS 정밀점검(신양재S/S #60BUS-#1M.Tr)","170kV GIS 정밀점검(신양재S/S #60BUS-#1M.Tr)","2016-04-19 18:00","2016-04-21 18:00","2016-04-23 17:00","2016-04-24 18:00","연속",null,null,null,201602160413,"-"]
[19,"남서울","강남","신양재S/S 154kV #65 BUS","170kV GIS 정밀점검(신양재S/S #65BUS-#1M.Tr)","170kV GIS 정밀점검(신양재S/S #65BUS-#1M.Tr)","2016-04-18 09:00","2016-04-19 18:00","2016-04-23 09:00","2016-04-23 17:00","연속",null,null,null,201602160412,"-"]
[20,"남서울","강남","역삼대치#1 T/L","지하(복합)변전소 인출구간 OF케이블 선종교체공사","가. 공사구간 ○ 154㎸ 신양재-역삼T/L : 역삼S/S∼J/B#13-1(3C×0.210㎞, 전력구) ○ 154㎸ 역삼-대치T/L : 역삼S/S∼J/B#14 (2C×0.319㎞, 전력구+관로) ○ 154㎸ 역삼-대치T/L : 대치S/S∼J/B#20 (2C×0.625㎞, 전력구+관로) 나. 케이블 포설 : 154㎸ XLPE 1,200㎟ × 2회","2016-04-13 10:00","2016-05-19 10:00","2016-04-13 10:00","2016-05-19 10:00","연속",null,null,null,201601040054,"-"]
[21,"남서울","강남","신양재역삼#3 T/L","역삼S/S 신양재-역삼#3T/L 누유 보수","역삼S/S 신양재-역삼#3T/L 누유 보수","2016-04-01 10:00","2016-04-01 18:00","2016-04-01 10:00","2016-04-01 18:00","당일",null,null,null,201602160407,"-"]
[22,"남서울","동서울","잠실삼성#2 T/L","잠실-삼성#2T/L 170kV GIS 정밀점검","잠실-삼성#2T/L 170kV GIS 정밀점검","2016-04-27 14:00","2016-04-29 18:00","취소","취소","연속",null,null,"신뢰도 개선",201602120897,"-"]
[23,"남서울","동서울","잠실삼성#1 T/L","잠실-삼성#1T/L 170kV GIS 정밀점검","잠실-삼성#1T/L 170kV GIS 정밀점검","2016-04-25 09:00","2016-04-27 14:00","취소","취소","연속",null,null,"신뢰도 개선",201602120896,"-"]
[24,"남서울","영서","화곡가양#2 T/L","154kV 마곡분기 지중T/L 건설공사","ㅇ 선종/긍장 : 154kV XLPE 2000㎟ , 2C-0.6km ㅇ 공사구간 : 신설 154kV 마곡S/S ~ 기설 M/H#3[화곡-가양 지중T/L] ㅇ 관련공사 : 마곡S/S 및 전력구 건설공사, 화곡-가양 지중T/L 이설공사","2016-04-01 09:00","2016-04-29 18:00","2016-04-01 09:00","2016-04-29 18:00","연속",null,null,"신뢰도 개선",201601120118,"-"]
[25,"남서울","영서","광명구공#1 T/L","영서P/O 170kV GIS 정밀점검( 광명-구공#1 및 구철T/L)","- 광명-구공#1T/L GIS 정밀점검 - 구철T/L GIS 정밀점검","2016-04-25 09:00","2016-04-27 18:00","2016-04-25 09:00","2016-04-27 18:00","연속",null,null,null,201602110390,"-"]
[26,"남서울","영서","광명구공#2 T/L","영서P/O 170kV GIS 정밀점검( 광명-구공#2T/L)","- 광명-구공#2T/L GIS 정밀점검","2016-04-28 09:00","2016-04-29 18:00","2016-04-28 09:00","2016-04-29 18:00","연속",null,null,null,201602110392,"-"]
[27,"남서울","영서","영서광명#2 T/L","154kV 영서-광명#2T/L 정밀점검 및 아킹혼 철거(부하측)","철탑 6기, 긍장 1.369km","2016-04-05 09:00","2016-04-05 18:00","2016-04-10 09:00","2016-04-10 18:00","당일",null,null,"신뢰도 개선",201602170084,"-"]
[28,"남서울","영서","영서광명#1 T/L","154kV 영서-광명#1T/L 정밀점검","철탑 6기, 긍장 1.369km","2016-04-04 09:00","2016-04-04 18:00","2016-04-09 09:00","2016-04-09 18:00","당일",null,null,"신뢰도 개선",201602170083,"-"]
[29,"남서울","영서","고강화곡#2 T/L","영서P/O 170kV GIS 정밀점검(고강-화곡#2T/L 등)","- 고강-화곡#2T/L GIS 정밀점검 - BUS TIE 6100 GIS 정밀점검","2016-04-18 09:00","2016-04-20 18:00","2016-04-18 09:00","2016-04-20 18:00","연속",null,null,null,201602110375,"-"]
[30,"남서울","영서","화곡S/S 154kV #2 BUS","영서P/O 170kV GIS 정밀점검(고강-화곡#2T/L 등)","- 고강-화곡#2T/L GIS 정밀점검 - BUS-TIE 6100 GIS 정밀점검","2016-04-18 09:00","2016-04-19 13:00","2016-04-18 09:00","2016-04-19 13:00","연속",null,null,null,201602110341,"-"]
[31,"남서울","영서","화곡S/S 154kV #1 BUS","영서P/O 170kV GIS 정밀점검(고강-화곡#2T/L 등)","- 고강-화곡#2T/L GIS 정밀점검 - BUS TIE 6100 GIS 정밀점검","2016-04-19 13:00","2016-04-20 18:00","2016-04-19 13:00","2016-04-20 18:00","연속",null,null,null,201602110354,"-"]
[32,"남서울","영서","화곡S/S 154kV #1 BUS","영서P/O 170kV GIS 정밀점검(고강-화곡#1T/L 등)","- 고강-화곡#1T/L GIS 정밀점검 - #4M.Tr 1차 GIS 정밀점검","2016-04-15 13:00","2016-04-16 18:00","2016-04-15 13:00","2016-04-16 18:00","연속",null,null,null,201602110346,"-"]
[33,"남서울","영서","화곡S/S 154kV #2 BUS","영서P/O 170kV GIS 정밀점검(고강-화곡#1T/L 등)","- 고강-화곡#1T/L GIS 정밀점검 - #4M.Tr 1차 GIS 정밀점검","2016-04-14 09:00","2016-04-15 13:00","2016-04-14 09:00","2016-04-15 13:00","연속",null,null,null,201602110331,"-"]
[34,"남서울","영서","고강화곡#1 T/L","영서P/O 170kV GIS 정밀점검(고강-화곡#1T/L 등)","- 고강-화곡#1T/L GIS 정밀점검 - #4M.Tr 1차 GIS 정밀점검","2016-04-14 09:00","2016-04-16 18:00","2016-04-14 09:00","2016-04-16 18:00","연속",null,null,null,201602110374,"-"]
[35,"남서울","영서","화곡S/S 154kV #1 BUS","영서P/O 170kV GIS 정밀점검(중동-화곡#2T/L 등)","- 중동-화곡#2T/L GIS 정밀점검","2016-04-12 10:00","2016-04-12 18:00","2016-04-12 10:00","2016-04-12 18:00","연속",null,null,null,201602110345,"-"]
[36,"남서울","영서","화곡S/S 154kV #2 BUS","영서P/O 170kV GIS 정밀점검(중동-화곡#2T/L 등)","- 중동-화곡#2T/L GIS 정밀점검","2016-04-11 09:00","2016-04-12 10:00","2016-04-11 09:00","2016-04-12 10:00","연속",null,null,null,201602110327,"-"]
[37,"남서울","영서","중동화곡#2 T/L","영서P/O 170kV GIS 정밀점검(중동-화곡#2T/L 등)","- 중동-화곡#2T/L GIS 정밀점검","2016-04-11 09:00","2016-04-12 18:00","2016-04-11 09:00","2016-04-12 18:00","연속",null,null,null,201602110373,"-"]
[38,"남서울","영서","화곡S/S 154kV #1 BUS","영서P/O 170kV GIS 정밀점검(중동-화곡#1T/L 등)","- 중동-화곡#1T/L GIS 정밀점검 - #3M.Tr 1차 GIS 정밀점검","2016-04-08 13:00","2016-04-09 18:00","2016-04-08 13:00","2016-04-09 18:00","연속",null,null,null,201602110344,"-"]
[39,"남서울","영서","중동화곡#1 T/L","영서P/O 170kV GIS 정밀점검(중동-화곡#1T/L 등)","- 중동-화곡#1T/L GIS 정밀점검 - #3M.Tr 1차 GIS 정밀점검","2016-04-07 09:00","2016-04-09 18:00","2016-04-07 09:00","2016-04-09 18:00","연속",null,null,null,201602110370,"-"]
[40,"남서울","영서","화곡S/S 154kV #2 BUS","영서P/O 170kV GIS 정밀점검(중동-화곡#1T/L 등)","- 중동-화곡#1T/L GIS 정밀점검 - #3M.Tr 1차 GIS 정밀점검","2016-04-07 09:00","2016-04-08 13:00","2016-04-07 09:00","2016-04-08 13:00","연속",null,null,null,201602110326,"-"]
[41,"남서울","영서","화곡S/S 154kV #1 BUS","영서P/O 170kV GIS 정밀점검(화곡-가양#2T/L 등)","- 화곡-가양#2T/L GIS 정밀점검 - #2M.Tr 1차 GIS 정밀점검","2016-04-05 13:00","2016-04-06 18:00","2016-04-05 13:00","2016-04-06 18:00","연속",null,null,null,201602110299,"-"]
[42,"남서울","영서","화곡S/S 154kV #2 BUS","영서P/O 170kV GIS 정밀점검(화곡-가양#2T/L 등)","- 화곡-가양#2T/L GIS 정밀점검 - #2M.Tr 1차 GIS 정밀점검","2016-04-04 09:00","2016-04-05 13:00","2016-04-04 09:00","2016-04-05 13:00","연속",null,null,null,201602110285,"-"]
[43,"남서울","영서","화곡S/S 154kV #1 BUS","영서 관내S/S 170kV GIS 정밀점검","- #1M.Tr 1차 GIS 정밀점검","2016-04-01 13:00","2016-04-02 18:00","2016-04-01 13:00","2016-04-02 18:00","연속",null,null,null,201601150053,"-"]
[44,"남서울","직할","교대이수#2 T/L","154kV 교대-이수T/L 지중선로 이설공사(방배로 1구간)","배경: 서초구청 시행 하수암거 설치에 따른 지중선로 이설 개요: 154KV 교대-이수T/L J/B#7~8, #9~10 (2구간, 0.66KM) XLPE1200 * 2회선","2016-04-11 09:00","2016-05-09 18:00","2016-04-11 09:00","2016-05-09 18:00","연속",null,null,null,201602180066,"-"]
[45,"인천","김포","신경서경서#1 T/L","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(1차) - 경서양촌#1T/L, #1M.Tr 1차, BUS-TIE GIS 3CCT - 신경서경서#1T/L 휴전 : BUS-TIE 작업에 따른 모선절체용","2016-04-22 08:00","2016-04-22 11:00","2016-04-22 08:00","2016-04-22 11:00","당일",null,null,null,201602110323,"-"]
[46,"인천","김포","경서S/S 154kV #1 BUS TIE GIS","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(1차) - 경서양촌#1T/L, #1M.Tr 1차, BUS-TIE GIS 3CCT - 신경서경서#1T/L 휴전 : BUS-TIE 작업에 따른 모선절체용","2016-04-20 08:00","2016-05-20 18:00","2016-04-20 08:00","2016-05-20 18:00","연속",null,null,null,201602110325,"-"]
[47,"인천","김포","경서S/S 154kV #2 BUS","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(1차) - 경서양촌#1T/L, #1M.Tr 1차, BUS-TIE GIS 3CCT","2016-04-20 08:00","2016-04-22 08:00","2016-04-20 08:00","2016-04-22 08:00","연속",null,null,null,201602110335,"-"]
[48,"인천","김포","경서양촌#1 T/L","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(1차) - 경서양촌#1T/L, #1M.Tr 1차, BUS-TIE GIS 3CCT","2016-04-20 08:00","2016-05-20 18:00","2016-04-20 08:00","2016-05-20 18:00","연속",null,null,"신뢰도 개선",201602110310,"-"]
[49,"인천","김포","경서S/S 154kV #1 BUS","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(1차) - 경서양촌#1T/L, #1M.Tr 1차, BUS-TIE GIS 3CCT","2016-04-22 08:00","2016-05-05 18:00","2016-04-22 08:00","2016-05-05 18:00","연속",null,null,null,201602110338,"-"]
[50,"인천","시흥","동시화서시화 T/L","동시화S/S 동시화서시화 T/L GIS 미동작점검","동시화S/S 동시화서시화 T/L GIS 미동작점검","2016-04-12 09:30","2016-04-12 18:00","2016-04-12 09:30","2016-04-12 18:00","당일",null,null,"신뢰도 개선",201602030062,"-"]
[51,"인천","시흥","서서울소래 T/L","154kV 서서울소래T/L 정밀점검","154kV 서서울소래T/L 정밀점검","2016-04-04 08:00","2016-04-08 18:00","2016-04-04 08:00","2016-04-08 18:00","연속",null,null,null,201602050159,"-"]
[52,"인천","시흥","남동연수#1 T/L","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 남동연수#1T/L GIS 1CCT 대체 - 154kV #1M.Tr 1차 GIS 1CCT 대체","2016-04-19 08:00","2016-05-03 18:00","2016-04-28 08:00","2016-05-12 18:00","연속",null,null,null,201602120289,"-"]
[53,"인천","인천","신현송현#2 T/L","송현S/S 신현송현#2 T/L 차단기 조작시험","송현S/S 신현송현#2 T/L 차단기 조작시험","2016-04-15 09:00","2016-04-15 18:00","2016-04-15 09:00","2016-04-15 18:00","당일",null,null,"신뢰도 개선",201602050099,"-"]
[54,"인천","인천","신경서영종 T/L","영종S/S 신경서영종T/L GIS 보통점검 및 보조계전기 교체","영종S/S 신경서영종T/L GIS 보통점검 및 보조계전기 교체","2016-04-06 09:00","2016-04-06 18:00","2016-04-06 09:00","2016-04-06 18:00","당일",null,null,null,201602050097,"-"]
[55,"인천","인천","신가좌인천#2 T/L","154kV 신가좌-인천#2T/L 절연유 시료채취","154kV 신가좌-인천#2T/L 절연유 시료채취(5개소) - 인천EBG, 인천SJ, M/H#15, M/H#21, M/H#26","2016-04-14 10:00","2016-04-14 18:00","2016-04-14 10:00","2016-04-14 18:00","당일",null,null,null,201602110075,"-"]
[56,"인천","직할","계양S/S 154kV #1 BUS TIE GIS","계양S/S 모선보호반 대체공사","계양S/S 모선보호반 대체공사","2016-04-04 09:00","2016-04-08 18:00","2016-04-04 09:00","2016-04-08 18:00","연속",null,null,null,201602170090,"-"]
[57,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강T/L M/H#9~M/H#10 이설공사","서울특별시에서 시행하는 남부순환로~오정대로 도로개설공사에 지장된는 154kV 신부평-고강T/L 지장이설 필요 - 이설구간 : 154kV 신부평-고강T/L M/H#9~M/H#10 (약 0.3km)","2016-04-15 09:00","2016-05-09 18:00","2016-04-15 09:00","2016-05-09 18:00","연속",null,null,null,201601050181,"-"]
[58,"인천","직할","부흥부개#1 T/L","부흥S/S 부흥-부개#1T/L GIS 정밀점검","부흥S/S 부흥-부개#1T/L GIS 정밀점검","2016-04-14 08:00","2016-04-16 18:00","2016-04-14 08:00","2016-04-16 18:00","연속",null,null,null,201602160244,"-"]
[59,"인천","직할","신부평부흥#1 T/L","부흥S/S 신부평-부흥#1T/L GIS 정밀점검","부흥S/S 신부평-부흥#1T/L GIS 정밀점검","2016-04-21 08:00","2016-04-23 18:00","2016-04-21 08:00","2016-04-23 18:00","연속",null,null,null,201602160247,"-"]
[60,"인천","직할","신부평부흥#2 T/L","부흥S/S 신부평-부흥#2T/L GIS 정밀점검","부흥S/S 신부평-부흥#2T/L GIS 정밀점검","2016-04-25 08:00","2016-04-27 18:00","2016-04-25 08:00","2016-04-27 18:00","연속",null,null,null,201602160249,"-"]
[61,"인천","직할","부흥부개#2 T/L","부흥S/S 부흥-부개#2T/L GIS 정밀점검","부흥S/S 부흥-부개#2T/L GIS 정밀점검","2016-04-18 08:00","2016-04-20 18:00","2016-04-18 08:00","2016-04-20 18:00","연속",null,null,null,201602160245,"-"]
[62,"경기북부","구리","마석청평HP#1 T/L","154kV 마석-청평HP #1T/L 피뢰기 설치공사","ㅇ 송전선로용 피뢰기 설치공사","2016-04-12 08:00","2016-04-18 18:00","2016-04-12 08:00","2016-04-18 18:00","연속",null,null,null,201602150581,"○"]
[63,"경기북부","구리","마석청평HP#2 T/L","154kV 마석-청평HP #2T/L 피뢰기 설치공사","ㅇ 송전선로용 피뢰기 설치공사","2016-04-19 08:00","2016-04-25 18:00","2016-04-19 08:00","2016-04-25 18:00","연속",null,null,null,201602150584,"○"]
[64,"경기북부","구리","미금덕소#1 T/L","154kV 미금-화양T/L 철탑이설공사","ㅇ 가운,지금지구 택지조성 철탑이설공사 - 인출정비 : 미금-덕소","2016-04-04 08:00","2016-04-04 14:00","취소","취소","연속",null,null,null,201602160193,"-"]
[65,"경기북부","구리","미금덕소#1 T/L","154kV 미금-화양T/L 철탑이설공사","ㅇ 가운,지금지구 택지조성 철탑이설공사 - 인출정비 : 미금-덕소","2016-04-07 08:00","2016-04-09 18:00","취소","취소","연속",null,null,null,201602160197,"-"]
[66,"경기북부","구리","미금덕소#2 T/L","154kV 미금-화양T/L 철탑이설공사","ㅇ 가운,지금지구 택지조성 철탑이설공사 - 인출정비 : 미금-덕소","2016-04-04 08:00","2016-04-06 18:00","취소","취소","연속",null,null,null,201602160195,"-"]
[67,"경기북부","구리","지제용문 T/L","154kV 지제-용문T/L 불량애자교체공사","불량애자교체공사","2016-04-28 08:00","2016-04-28 18:00","2016-04-28 08:00","2016-04-28 18:00","매일",null,null,null,201602150594,"-"]
[68,"경기북부","구리","문막지제 T/L","154kV 문막-지제T/L 피뢰기 설치공사","송전선로용 피뢰기 설치공사","2016-04-04 08:00","2016-04-08 19:00","2016-04-04 08:00","2016-04-08 19:00","매일",null,null,null,201602150575,"-"]
[69,"경기북부","구리","철원화천#1 T/L","154kV 철원S/S 철원화천#1T/L SFR 설치","송전선로 보호반에 SFR(Smart Fault Recorder) 설치","2016-04-05 10:00","2016-04-05 18:00","2016-04-05 10:00","2016-04-05 18:00","연속",null,null,null,201602010004,"○"]
[70,"경기북부","구리","철원화천#2 T/L","154kV 철원S/S 철원화천#2T/L SFR 설치","송전선로 보호반에 SFR(Smart Fault Recorder) 설치","2016-04-06 10:00","2016-04-06 18:00","2016-04-06 10:00","2016-04-06 18:00","연속",null,null,null,201602010005,"○"]
[71,"경기북부","직할","신의정부의정부#2 T/L","신의정부의정부#2 T/L","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-05 10:00","2016-04-05 18:00","2016-04-05 10:00","2016-04-05 18:00","당일",null,null,null,201602160126,"-"]
[72,"경기북부","직할","신의정부의정부#1 T/L","신의정부의정부#1 T/L","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-04 10:00","2016-04-04 18:00","2016-04-04 10:00","2016-04-04 18:00","당일",null,null,null,201602160125,"-"]
[73,"경기북부","직할","신의정부S/S 154kV #3 BUS TIE CB","신의정부S/S 154kV #3 BUS TIE CB","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-20 10:00","2016-04-20 18:00","2016-04-20 10:00","2016-04-20 18:00","당일",null,null,null,201602160135,"-"]
[74,"경기북부","직할","신의정부S/S 66-67-0 SEC CB","신의정부S/S 66-67-0 SEC CB","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-19 10:00","2016-04-19 18:00","2016-04-19 10:00","2016-04-19 18:00","당일",null,null,null,201602160134,"-"]
[75,"경기북부","직할","신의정부S/S 61-62-0 SEC CB","신의정부S/S 61-62-0 SEC CB","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-18 10:00","2016-04-18 18:00","2016-04-18 10:00","2016-04-18 18:00","당일",null,null,null,201602160133,"-"]
[76,"경기북부","직할","신의정부S/S 154kV #2 BUS TIE CB","신의정부S/S 154kV #2 BUS TIE CB","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-15 10:00","2016-04-15 18:00","2016-04-15 10:00","2016-04-15 18:00","당일",null,null,null,201602160132,"-"]
[77,"경기북부","직할","신의정부S/S 65-66-0 SEC CB","신의정부S/S 65-66-0 SEC CB","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-14 10:00","2016-04-14 18:00","2016-04-14 10:00","2016-04-14 18:00","당일",null,null,null,201602160131,"-"]
[78,"경기북부","직할","신의정부S/S 60-61-0 SEC CB","신의정부S/S 60-61-0 SEC CB","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-13 10:00","2016-04-13 18:00","2016-04-13 10:00","2016-04-13 18:00","당일",null,null,null,201602160130,"-"]
[79,"경기북부","직할","신의정부S/S 154kV #1 BUS TIE CB","신의정부S/S 154kV #1 BUS TIE CB","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-08 10:00","2016-04-08 18:00","2016-04-08 10:00","2016-04-08 18:00","당일",null,null,null,201602160129,"-"]
[80,"경기북부","직할","신의정부금오#2 T/L","신의정부금오#2 T/L","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-07 10:00","2016-04-07 18:00","2016-04-07 10:00","2016-04-07 18:00","당일",null,null,null,201602160128,"-"]
[81,"경기북부","직할","신의정부금오#1 T/L","신의정부금오#1 T/L","2016~17년도 직할 변전협력회사 총액공사 - GIS 보통점검","2016-04-06 10:00","2016-04-06 18:00","2016-04-06 10:00","2016-04-06 18:00","당일",null,null,null,201602160127,"-"]
[82,"경기북부","직할","양주불광#2 T/L","154kV 양주-불광#2T/L 전선교체공사","접속개소 전선교체 (No.2-4, 5-6, 6-8, 8-10)","2016-04-08 07:00","2016-04-14 18:00","2016-04-08 07:00","2016-04-14 18:00","연속",null,null,null,201602150647,"-"]
[83,"경기북부","직할","양주은평#1 T/L","154kV 양주-은평#1T/L 전선교체공사","접속개소전선교체 (양주-No.1,2-4,5-6,8-10,10-11)","2016-04-08 07:00","2016-04-14 18:00","2016-04-08 07:00","2016-04-14 18:00","연속",null,null,null,201602150652,"-"]
[84,"경기북부","직할","양주불광#1 T/L","154kV 양주-불광#1T/L 전선교체공사","접속개소 전선교체 (No.6-8,14-17)","2016-04-01 07:00","2016-04-07 18:00","2016-04-01 07:00","2016-04-07 18:00","연속",null,null,null,201602150644,"-"]
[85,"경기북부","직할","양주은평#2 T/L","154kV 양주-은평#2T/L 전선교체공사","접속개소 전선교체 (양주-No.1,2-4,5-6,8-10,10-11)","2016-04-01 07:00","2016-04-07 18:00","2016-04-01 07:00","2016-04-07 18:00","연속",null,null,null,201602150649,"-"]
[86,"경기북부","파주","일산송포#2 T/L","일산S/S 일산-송포#2T/L GIS Air 누기 보수","일산S/S 일산-송포#2T/L GIS Air 누기 보수","2016-04-08 09:00","2016-04-08 18:00","2016-04-08 09:00","2016-04-08 18:00","당일",null,null,null,201602170061,"-"]
[87,"경기북부","파주","고양일산#1 T/L","일산S/S 고양-일산#1T/L GIS 초기점검(변전협력회사 총액공사)","일산S/S 고양-일산#1T/L GIS 초기점검(변전협력회사 총액공사)","2016-04-11 10:00","2016-04-11 18:00","2016-04-11 10:00","2016-04-11 18:00","당일",null,null,null,201602160389,"○"]
[88,"경기북부","파주","고양일산#2 T/L","일산S/S 고양-일산#2T/L GIS 초기점검(변전협력회사 총액공사)","일산S/S 고양-일산#2T/L GIS 초기점검(변전협력회사 총액공사)","2016-04-14 10:00","2016-04-14 18:00","2016-04-14 10:00","2016-04-14 18:00","당일",null,null,null,201602160390,"○"]
[89,"경기","군포","조암구문천#1 T/L","154kV 조암구문천#1T/L 송전선로 정밀점검(구간 No.1~20)","16년 가공송전선로 순시점검 위탁공사 154kV 조암구문천#1T/L 송전선로 정밀점검(구간 No.1~20)","2016-04-16 09:30","2016-04-17 18:00","2016-04-16 09:30","2016-04-17 18:00","매일",null,null,null,201602150138,"-"]
[90,"경기","군포","조암구문천#2 T/L","154kV 조암구문천#2T/L 송전선로 정밀점검(구간 No.1~20)","16년 가공송전선로 순시점검 위탁공사 154kV 조암구문천#2T/L 송전선로 정밀점검(구간 No.1~20)","2016-04-23 09:30","2016-04-24 18:00","2016-04-23 09:30","2016-04-24 18:00","매일",null,null,null,201602150141,"-"]
[91,"경기","군포","화성조암#2 T/L","조암S/S 154kV 화성조암#2T/L GIS 정밀점검공사","조암S/S 154kV 화성조암#2T/L GIS 정밀점검공사","2016-04-29 09:00","2016-05-01 18:00","2016-04-29 09:00","2016-05-01 18:00","연속",null,null,null,201602150592,"-"]
[92,"경기","동부","분당오포#1 T/L","154kV 분당오포#1T/L 송전선로 정밀점검(구간 No.10~31)","154kV 분당오포#1T/L 송전선로 정밀점검(구간 No.10~31)","2016-04-15 09:00","2016-04-16 18:00","2016-04-15 09:00","2016-04-16 18:00","매일",null,null,null,201602150068,"-"]
[93,"경기","동부","오포모현#2 T/L","154kV 오포모현#2T/L 송전선로 정밀점검(구간 No.1~24)","154kV 오포모현#2T/L 송전선로 정밀점검(구간 No.1~24)","2016-04-16 09:00","2016-04-17 18:00","2016-04-16 09:00","2016-04-17 18:00","매일",null,null,null,201602150073,"-"]
[94,"경기","성남","신성남서판교#2 T/L","신성남S/S 154kV 신성남-서판교#2T/L","신성남S/S 154kV 신성남-서판교#2T/L GIS 보통점검 비상트립장치","2016-04-16 09:00","2016-04-16 18:00","2016-04-16 09:00","2016-04-16 18:00","당일",null,null,"신뢰도개선",201602020166,"-"]
[95,"경기","성남","신성남정자#1 T/L","154kV 신성남-정자#1T/L PNL대체","154kV 신성남-정자#1T/L PNL대체","2016-04-27 09:00","2016-04-29 18:00","2016-04-27 09:00","2016-04-29 18:00","연속",null,null,"신뢰도개선",201602040075,"-"]
[96,"경기","성남","신수원삼미#2 T/L","154kV 북동탄분기 지중T/L 건설공사","신수원-북동탄T/L : 154kV XLPE 2500㎟, 2회선 × 1.4km 북동탄-삼미T/L : 154kV XLPE 2000㎟, 2회선(D) × 0.4km : 154kV XLPE 2500㎟, 2회선 × 1.0km","2016-04-22 10:00","2016-05-18 18:00","2016-04-25 10:00","2016-05-24 18:00","연속",null,null,null,201602160205,"-"]
[97,"경기","성남","용인남사#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식 ○ 옥외설비(옥외용 단로기, 모선 등) 철거 × 1식 ○ 전력케이블 및 제어케이블 철거, 설치 × 1식 ○ 디지털 축소형모자익반 등 각종 보호반 철거, 설치 × 1식 ○ 기기기초 및 접지공사 설치 등 × 1식","2016-04-05 09:00","2016-04-11 18:00","2016-04-05 09:00","2016-04-11 18:00","연속",null,null,null,201602150184,"-"]
[98,"경기","성남","용인남사#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","안전이격 확보","2016-04-26 09:00","2016-04-26 14:00","2016-04-26 09:00","2016-04-26 14:00","당일",null,null,null,201602150729,"-"]
[99,"경기","평택","서운안성#2 T/L","154kV 서운-안성T/L No.17~21 이도조정공사","○ 공사구간 : 154kV 서운-안성T/L No.17~21 ○ 공사내용 : #1,2T/L 전력선 및 가공지선 이도조정","2016-04-20 08:00","2016-04-21 18:00","2016-04-20 08:00","2016-04-21 18:00","연속",null,null,null,201602160041,"-"]
[100,"경기","평택","서운안성#1 T/L","154kV 서운-안성T/L No.17~21 이도조정공사","○ 공사구간 : 154kV 서운-안성T/L No.17~21 ○ 공사내용 : #1,2T/L 전력선 및 광통신선 이도조정","2016-04-18 08:00","2016-04-19 18:00","2016-04-18 08:00","2016-04-19 18:00","연속",null,null,null,201602160034,"○"]
[101,"경기","평택","송탄S/S 송탄-오성복합#1T/L(627) GIS","송탄S/S 송탄-오성복합T/L GIS(627) 노후대체","송탄S/S 송탄-오성복합T/L GIS(627) 노후대체","2016-04-25 09:00","2016-05-17 18:00","2016-04-25 09:00","2016-05-17 18:00","연속",null,null,"신뢰도개선",201602150028,"○"]
[102,"경기","평택","오산S/S 오산-평택#1T/L GIS","오산S/S 오산-평택#1T/L GIS 초기점검","오산S/S 오산-평택#1T/L GIS 초기점검","2016-04-10 09:00","2016-04-10 18:00","2016-04-10 09:00","2016-04-10 18:00","당일",null,null,"신뢰도개선",201602150285,"-"]
[103,"강원","강릉","영동TP강릉 T/L","154kV 강릉T/L 피뢰기 설치공사","○ 발전소 연계선로 피뢰기 및 아킹혼 설치공사(No.1~8)","2016-04-01 08:00","2016-04-01 18:00","2016-04-01 08:00","2016-04-01 18:00","당일",null,null,null,201602030041,"-"]
[104,"강원","강릉","주진평창#2 T/L","2016~17년 송전정비 협력회사 총액공사","○ 주진-평창 #2T/L 전선접속개소 제거공사(No.6~13, 23~26, 53~56)","2016-04-11 08:00","2016-04-17 18:00","2016-04-11 08:00","2016-04-17 18:00","연속",null,null,null,201602030046,"-"]
[105,"강원","강릉","주진평창#1 T/L","2016~17년 송전정비 협력회사 총액공사","○ 주진-평창 #1T/L 전선접속개소 제거공사(No.6~13, 23~26, 53~56)","2016-04-02 08:00","2016-04-07 18:00","2016-04-02 08:00","2016-04-07 18:00","연속",null,null,null,201602030045,"-"]
[106,"강원","동해","이원동해TP T/L","345kV 신제천-동해 등 7개T/L 송전선로용 피뢰기 설치공사","이원-동해TPT/L No.1~No.32 송전선로용 피뢰기 설치","2016-04-04 07:00","2016-04-06 18:00","2016-04-04 07:00","2016-04-06 18:00","매일",null,null,null,201602110268,"-"]
[107,"강원","동해","삼척동해TP T/L","345kV 신제천-동해 등 7개T/L 송전선로용 피뢰기 설치공사","삼척-동해TPT/L No.1~No.39 송전선로용 피뢰기 설치","2016-04-07 07:00","2016-04-12 18:00","2016-04-07 07:00","2016-04-12 18:00","매일",null,null,null,201602110269,"-"]
[108,"강원","동해","이원도계 T/L","345kV 신제천-동해 등 7개T/L 송전선로용 피뢰기 설치공사","이원-도계T/L No.31~124 피뢰기설치","2016-04-11 07:00","2016-04-18 18:00","2016-04-11 07:00","2016-04-18 18:00","매일",null,null,null,201602110270,"-"]
[109,"강원","원주","홍천소양강HP T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 10기 및 전력선 교체","2016-04-27 07:30","2016-05-02 18:00","2016-04-27 07:30","2016-05-02 18:00","연속",null,null,null,201602150709,"-"]
[110,"강원","원주","홍천소양강HP T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 10기 및 전력선 교체","2016-04-04 07:30","2016-04-05 18:00","2016-04-04 07:30","2016-04-05 18:00","연속",null,null,null,201602150708,"-"]
[111,"강원","직할","홍천남춘천 T/L","2016년 관내변전소 154kV GCB ,GIS 정밀점검공사 시행","154kV 홍천남춘천T/L CB, #1,2DS, LDS 등 내부점검 조작메카니즘부 점검","2016-04-14 08:00","2016-04-16 18:00","2016-04-14 08:00","2016-04-16 18:00","연속",null,null,null,201602150078,"-"]
[112,"강원","직할","남춘천춘천 T/L","154kV 소양T/L 안전이격 확보공사","철탑교체 10기 및 전력선 교체","2016-04-06 07:30","2016-04-07 18:00","2016-04-06 07:30","2016-04-07 18:00","연속",null,null,null,201602150710,"-"]
[113,"강원","직할","북춘천춘천HP T/L","2016년 상반기 장기미동작 차단기 조작시험","2016년 상반기 장기미동작 차단기 조작시험 시행","2016-04-06 10:00","2016-04-06 13:00","2016-04-06 10:00","2016-04-06 13:00","당일",null,null,null,201602150120,"-"]
[114,"강원","직할","화천화천HP#1 T/L","2016년 상반기 장기미동작 차단기 조작시험","2016년 상반기 장기미동작 차단기 조작시험 시행","2016-04-06 14:00","2016-04-06 18:00","2016-04-06 14:00","2016-04-06 18:00","당일",null,null,null,201602150121,"-"]
[115,"강원","태백","동해동영월 T/L","154kV 태백-영월 등 3개T/L 피뢰기설치 공사","154kV 동해-동영월T/L No1~6호, 피뢰기 설치공사","2016-04-29 08:30","2016-04-29 18:00","2016-04-29 08:30","2016-04-29 18:00","당일",null,null,null,201602150088,"-"]
[116,"강원","태백","영월CC S/Y 154kV #2 BUS","2016년 태백전력지사 GIS 정밀점검공사","영월CC G/T #2 Bay 정밀점검(2DS측)","2016-04-05 10:00","2016-04-06 18:00","2016-04-05 10:00","2016-04-06 18:00","연속",null,null,null,201602150201,"-"]
[117,"강원","태백","단양영월CC#2 T/L","2016년 태백전력지사 GIS 정밀점검공사","단양-영월CC #2 T/L Bay 정밀점검","2016-04-10 09:00","2016-04-12 18:00","2016-04-10 09:00","2016-04-12 18:00","연속",null,null,null,201602120505,"-"]
[118,"강원","태백","영월CC S/Y 154kV #1 BUS","2016년 태백전력지사 GIS 정밀점검공사","단양-영월CC #2 T/L Bay 정밀점검(1DS)","2016-04-10 10:00","2016-04-11 10:00","2016-04-10 10:00","2016-04-11 10:00","연속",null,null,null,201602150202,"-"]
[119,"강원","태백","영월CC S/Y 154kV #2 BUS","2016년 태백전력지사 GIS 정밀점검공사","단양-영월CC #2 T/L Bay 정밀점검(2DS)","2016-04-11 10:00","2016-04-12 18:00","2016-04-11 10:00","2016-04-12 18:00","연속",null,null,null,201602150203,"-"]
[120,"강원","태백","정선영월CC T/L","2016년 태백전력지사 GIS 정밀점검공사","정선-영월CC T/L Bay 정밀점검","2016-04-18 09:00","2016-04-20 18:00","2016-04-18 09:00","2016-04-20 18:00","연속",null,null,null,201602150162,"-"]
[121,"강원","태백","영월CC S/Y 154kV #1 BUS","2016년 태백전력지사 GIS 정밀점검공사","정선-영월CC T/L Bay 정밀점검(1DS)","2016-04-18 10:00","2016-04-19 10:00","2016-04-18 10:00","2016-04-19 10:00","연속",null,null,null,201602150206,"-"]
[122,"강원","태백","영월CC S/Y 154kV #2 BUS","2016년 태백전력지사 GIS 정밀점검공사","정선-영월CC T/L Bay 정밀점검(2DS)","2016-04-19 10:00","2016-04-20 18:00","2016-04-19 10:00","2016-04-20 18:00","연속",null,null,null,201602150208,"-"]
[123,"강원","태백","동영월영월CC T/L","2016년 태백전력지사 GIS 정밀점검공사","동영월-영월CC T/L Bay GIS 정밀점검","2016-04-21 09:00","2016-04-23 18:00","2016-04-21 09:00","2016-04-23 18:00","연속",null,null,null,201602150163,"-"]
[124,"강원","태백","영월CC S/Y 154kV #1 BUS","2016년 태백전력지사 GIS 정밀점검공사","동영월-영월CC T/L Bay GIS 정밀점검(1DS)","2016-04-21 10:00","2016-04-22 10:00","2016-04-21 10:00","2016-04-22 10:00","연속",null,null,null,201602150210,"-"]
[125,"강원","태백","영월CC S/Y 154kV #2 BUS","2016년 태백전력지사 GIS 정밀점검공사","동영월-영월CC T/L Bay GIS 정밀점검(2DS)","2016-04-22 10:00","2016-04-23 18:00","2016-04-22 10:00","2016-04-23 18:00","연속",null,null,null,201602150211,"-"]
[126,"강원","태백","영월CC S/Y 154kV #1 BUS","2016년 태백전력지사 GIS 정밀점검공사","영월G/T #3 Bay GIS 정밀점검(1DS)","2016-04-25 10:00","2016-04-26 10:00","2016-04-25 10:00","2016-04-26 10:00","연속",null,null,null,201602150212,"-"]
[127,"강원","태백","영월CC S/Y 154kV #2 BUS","2016년 태백전력지사 GIS 정밀점검공사","영월G/T #3 Bay GIS 정밀점검(2DS)","2016-04-26 10:00","2016-04-27 18:00","2016-04-26 10:00","2016-04-27 18:00","연속",null,null,null,201602150213,"-"]
[128,"강원","태백","영월CC S/Y 154kV #1 BUS","2016년 태백전력지사 GIS 정밀점검공사","영월S/T #1 Bay GIS 정밀점검(1DS)","2016-04-28 10:00","2016-04-29 10:00","2016-04-28 10:00","2016-04-29 10:00","연속",null,null,null,201602150215,"-"]
[129,"강원","태백","영월CC S/Y 154kV #2 BUS","2016년 태백전력지사 GIS 정밀점검공사","영월S/T #1 Bay GIS 정밀점검(2DS)","2016-04-29 10:00","2016-04-30 18:00","2016-04-29 10:00","2016-04-30 18:00","연속",null,null,null,201602150219,"-"]
[130,"강원","태백","영월CC S/Y 154kV #1 BUS","2016년 태백전력지사 GIS 정밀점검공사","영월CC G/T #2 Bay 정밀점검(1DS측)","2016-04-04 10:00","2016-04-05 10:00","2016-04-04 10:00","2016-04-05 10:00","연속",null,null,null,201602150192,"-"]
[131,"강원","태백","고한영월 T/L","154kV 태백-영월 등 3개T/L 피뢰기 설치공사","고한-영월T/L No.1~33호","2016-04-25 08:30","2016-04-28 18:00","2016-04-25 08:30","2016-04-28 18:00","매일",null,null,null,201602150081,"-"]
[132,"충북","직할","금왕남음성#1 T/L","16년 직할 변전협력회사 총액공사","금왕남음성#1T/L 차단기 보통점검","2016-04-04 10:00","2016-04-04 18:00","2016-04-04 10:00","2016-04-04 18:00","당일",null,null,null,201602020052,"○"]
[133,"충북","직할","점촌단양 T/L","16년 직할 변전협력회사 총액공사","점촌단양T/L 차단기 보통점검","2016-04-06 10:00","2016-04-06 18:00","취소","취소","당일",null,null,null,201602020065,"-"]
[134,"충북","직할","문경단양 T/L","16년 직할 변전협력회사 총액공사","문경단양T/L 차단기 보통점검","2016-04-01 10:00","2016-04-01 18:00","2016-04-01 10:00","2016-04-01 18:00","당일",null,null,null,201602020066,"-"]
[135,"충북","직할","신제천영월CC#2 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","피뢰기 설치, 아킹혼 철거, 조류착지방지장치 설치","2016-04-18 07:30","2016-04-23 18:00","2016-04-18 07:30","2016-04-23 18:00","매일",null,null,null,201602150066,"-"]
[136,"충북","직할","신제천왕암#1 T/L","345kV 신제천S/S GIS화 공사","154kV GIS 붓싱 설치 (안전이격 확보)","2016-04-16 09:00","2016-04-16 18:00","2016-04-16 09:00","2016-04-16 18:00","매일",null,null,null,201602260075,"-"]
[137,"충북","직할","신제천왕암#2 T/L","345kV 신제천S/S GIS화 공사","154kV GIS 붓싱 설치 (안전이격 확보)","2016-04-17 09:00","2016-04-17 13:00","2016-04-17 09:00","2016-04-17 13:00","매일",null,null,null,201602260073,"-"]
[138,"충북","직할","신제천영월CC#1 T/L","345kV 신제천S/S GIS화 공사","154kV GIS 붓싱 설치 (안전이격 확보)","2016-04-17 13:00","2016-04-17 18:00","2016-04-17 13:00","2016-04-17 18:00","매일",null,null,null,201602260074,"-"]
[139,"충북","직할","풍동음성#2 T/L","16년 직할 변전협력회사 총액공사","풍동음성#2T/L 차단기 하자점검","2016-04-12 10:00","2016-04-12 18:00","2016-04-12 10:00","2016-04-12 18:00","당일",null,null,null,201602020063,"○"]
[140,"충북","직할","음성금왕#2 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","154kV 신충주-음성#2T/L 4회선 구간 상단회선 작업에 따른 안전조치 (64~70호)","2016-04-07 07:30","2016-04-07 18:00","2016-04-07 07:30","2016-04-07 18:00","당일",null,null,null,201602160042,"○"]
[141,"충북","직할","음성금왕#1 T/L","16년 직할 변전협력회사 총액공사","음성금왕#1T/L 차단기 하자점검","2016-04-05 10:00","2016-04-05 18:00","2016-04-05 10:00","2016-04-05 18:00","당일",null,null,null,201602020053,"○"]
[142,"충북","직할","풍동음성#1 T/L","16년 직할 변전협력회사 총액공사","풍동음성#1T/L 차단기 하자점검","2016-04-20 10:00","2016-04-20 18:00","2016-04-20 10:00","2016-04-20 18:00","당일",null,null,null,201602020062,"○"]
[143,"충북","직할","제천영월#1 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","애자련 보강 (68~71호)","2016-04-25 07:30","2016-04-25 18:00","2016-04-25 07:30","2016-04-25 18:00","당일",null,null,null,201602160052,"-"]
[144,"충북","직할","제천영월#2 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","애자련 보강 (68~71호)","2016-04-26 07:30","2016-04-26 18:00","2016-04-26 07:30","2016-04-26 18:00","당일",null,null,null,201602160054,"-"]
[145,"충북","직할","제천영월#1 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","154kV 신제천-영월CC #2T/L 4회선구간 하단회선 작업에 따른 안전조치 (34호)","2016-04-19 07:30","2016-04-19 18:00","2016-04-19 07:30","2016-04-19 18:00","당일",null,null,null,201602150091,"-"]
[146,"충북","청주","서청주사직#1 T/L","16년도 청주전력지사 154kV 개폐장치 정밀점검","사직S/S 서청주-사직#1T/L GIS (617CB, 611,612DS) 정밀점검","2016-04-01 09:00","2016-04-03 18:00","2016-04-01 09:00","2016-04-03 18:00","연속",null,null,null,201602140054,"-"]
[147,"충북","청주","신옥천남대전#3 T/L","16년 청주 변전협력회사 총액공사","신옥천S/S 신옥천남대전#3 T/L GCB 하자점검 및 PT 보통점검","2016-04-14 09:00","2016-04-14 18:00","2016-04-14 09:00","2016-04-14 18:00","당일",null,null,null,201602180091,"-"]
[148,"충북","청주","신옥천남대전#4 T/L","16년 청주 변전협력회사 총액공사","신옥천S/S 신옥천남대전#4 T/L GCB, PT, LA 보통점검","2016-04-15 09:00","2016-04-15 18:00","2016-04-15 09:00","2016-04-15 18:00","당일",null,null,null,201602180092,"-"]
[149,"충북","청주","신옥천남대전#1 T/L","16년 청주 변전협력회사 총액공사","신옥천S/S 신옥천남대전#1 T/L GCB 하자점검 및 PT 보통점검","2016-04-11 09:00","2016-04-11 18:00","2016-04-11 09:00","2016-04-11 18:00","당일",null,null,null,201602180089,"-"]
[150,"충북","청주","신옥천남대전#2 T/L","16년 청주 변전협력회사 총액공사","신옥천S/S 신옥천남대전#2 T/L GCB, PT ,LA보통점검","2016-04-12 09:00","2016-04-12 18:00","2016-04-12 09:00","2016-04-12 18:00","당일",null,null,null,201602180090,"-"]
[151,"충북","청주","청원죽림#2 T/L","16년도 청주전력지사 154kV 개폐장치 정밀점검","죽림S/S 청원-죽림#2T/L GIS (657CB, 651,652DS) 정밀점검","2016-04-22 09:00","2016-04-24 18:00","2016-04-22 09:00","2016-04-24 18:00","연속",null,null,null,201602140055,"-"]
[152,"충북","청주","청원부강#1 T/L","16년도 청주전력지사 154kV 개폐장치 정밀점검","청원S/S 청원-부강#1T/L GIS (6B7CB, 6B1,6B2DS) 정밀점검","2016-04-26 09:00","2016-04-28 18:00","2016-04-26 09:00","2016-04-28 18:00","연속",null,null,null,201602140058,"○"]
[153,"충북","청주","청원청주#3 T/L","154kV 청원청주T/L 전선접속개소 해소공사","전력선 교체","2016-04-16 09:00","2016-05-10 18:00","2016-04-16 09:00","2016-05-10 18:00","연속",null,null,null,201602150631,"-"]
[154,"충북","청주","청원청주#1 T/L","154kV 청원청주T/L 전선접속개소 해소공사","전력선 교체","2016-04-16 09:00","2016-05-10 18:00","2016-04-16 09:00","2016-05-10 18:00","연속",null,null,null,201602150629,"-"]
[155,"충북","충주","진천덕산#1 T/L","154kV GIS 하자점검","주기도래에 따른 해당 차단기 하자점검","2016-04-04 10:00","2016-04-04 18:00","2016-04-04 10:00","2016-04-04 18:00","당일",null,null,null,201602120902,"○"]
[156,"충북","충주","진천덕산#2 T/L","154kV GIS 하자점검","주기도래에 따른 해당 차단기 하자점검","2016-04-05 10:00","2016-04-05 18:00","2016-04-05 10:00","2016-04-05 18:00","당일",null,null,null,201602120903,"○"]
[157,"충북","충주","남음성덕산#1 T/L","154kV GIS 하자점검","주기도래에 따른 해당 차단기 하자점검","2016-04-06 10:00","2016-04-07 18:00","2016-04-06 10:00","2016-04-07 18:00","매일",null,null,null,201602120904,"○"]
[158,"대전충남","서산","석문당진TP#2 T/L","[송전] 154kV 석문-당진화력#2T/L 지장송전선로 이설공사","요청자시행 공사 가공 : 철탑 신설1기, 철거 1기 지중 : 접속 8개소(중간4개소, 종단4개소) (3상/1개소)","2016-04-21 09:00","2016-05-08 18:00","2016-04-21 09:00","2016-05-08 18:00","연속",null,null,"신뢰도 개선",201602120031,"-"]
[159,"대전충남","서산","석문당진TP#1 T/L","[송전] 154kV 석문-당진화력#1T/L 지장송전선로 이설공사","요청자시행 공사 가공 : 철탑 신설1기, 철거 1기 지중 : 접속 8개소(중간4개소, 종단4개소) (3상/1개소)","2016-04-03 09:00","2016-04-20 18:00","2016-04-02 07:00","2016-04-20 18:00","연속",null,null,null,201602120029,"-"]
[160,"대전충남","아산","신온양한샘#1 T/L","154kV 신온양-한샘T/L 건설공사","□ 기설 154kV 신온양-한샘T/L 경과지 변경","2016-04-18 06:00","2016-04-23 20:00","2016-04-18 06:00","2016-04-23 20:00","연속",null,null,null,201601110036,"-"]
[161,"대전충남","아산","신온양한샘#2 T/L","154kV 신온양-한샘T/L 건설공사","□ 기설 154kV 신온양-한샘T/L 가압준비, 인출작업","2016-04-18 06:00","2016-04-23 20:00","2016-04-18 06:00","2016-04-23 20:00","연속",null,null,null,201601110035,"-"]
[162,"대전충남","아산","신탕정탕정#1 T/L","신탕정S/S 154kV 신탕정-탕정#1T/L GIS 보통점검","○154kV 신탕정-탕정#1T/L GIS 보통점검","2016-04-07 09:00","2016-04-07 18:00","2016-04-07 09:00","2016-04-07 18:00","당일",null,null,null,201602110124,"-"]
[163,"대전충남","아산","신탕정탕정#2 T/L","신탕정S/S 154kV 신탕정-탕정#2T/L GIS 보통점검","○154kV 신탕정-탕정#2T/L GIS 보통점검","2016-04-08 09:00","2016-04-08 18:00","2016-04-08 09:00","2016-04-08 18:00","당일",null,null,null,201602110130,"-"]
[164,"대전충남","아산","온양풍세#1 T/L","풍세S/S 154kV 온양-풍세#1T/L GIS 하자점검","○154kV 온양-풍세#1T/L GIS 하자점검","2016-04-11 09:00","2016-04-11 18:00","2016-04-11 09:00","2016-04-11 18:00","당일",null,null,null,201602110133,"-"]
[165,"대전충남","아산","온양풍세#2 T/L","풍세S/S 154kV 온양-풍세#2T/L GIS 하자점검","○154kV 온양-풍세#2T/L GIS 하자점검","2016-04-12 09:00","2016-04-12 18:00","2016-04-12 09:00","2016-04-12 18:00","당일",null,null,null,201602110136,"-"]
[166,"전북","군산","군산동군산#2 T/L","154kV 군산-동군산#2T/L 정밀점검","송전선로 정밀점검 : No.2~38","2016-04-19 07:30","2016-04-21 18:00","2016-04-19 07:30","2016-04-21 18:00","매일",null,null,null,201602120618,"-"]
[167,"전북","군산","군산동군산#2 T/L","154kV 군산-동군산#2T/L 피뢰기 설치공사","피뢰기 설치 : No.2~6","2016-04-30 07:30","2016-04-30 18:00","2016-04-30 07:30","2016-04-30 18:00","당일",null,null,null,201602120676,"-"]
[168,"전북","군산","군산동군산#1 T/L","154kV 군산-동군산#1T/L 피뢰기 설치 등 2개 공사","1. 피뢰기 설치 : No.2~38 2. 송전선로 정밀점검 : No.2~38","2016-04-22 07:30","2016-04-24 18:00","2016-04-22 07:30","2016-04-24 18:00","매일",null,null,null,201602120621,"-"]
[169,"전북","군산","군산서군산#1 T/L","154kV 군산-서군산#1T/L 피뢰기 설치 등 2개공사","1. 피뢰기 설치공사 : No.2~70 2. 4회선 정밀점검 및 피뢰기 설치를 위한 안전이격거리 확보","2016-04-24 07:30","2016-04-29 18:00","2016-04-24 07:30","2016-04-29 18:00","매일",null,null,null,201602120641,"-"]
[170,"전북","군산","군산서군산#2 T/L","154kV 군산-서군산#2T/L 피뢰기설치 등2개공사 관련 안전이격확보","군산-동군산 및 군산-서군산T/L 4회선 구간 작업을 위한 안전이격거리 확보","2016-04-30 07:30","2016-04-30 18:00","2016-04-30 07:30","2016-04-30 18:00","당일",null,null,null,201602120637,"-"]
[171,"전북","군산","이리S/S 154kV #1 BUS TIE CB","차단기 보통점검공사","- 메카니즘점검 및 경보시험 - 타임측정, 절연열화측정, CT포화시험 등","2016-04-06 10:00","2016-04-06 17:00","2016-04-06 10:00","2016-04-06 17:00","당일",null,null,null,201602170059,"-"]
[172,"전북","군산","이리백산#2 T/L","154kV 이리-백산#2T/L 선종교체공사","가. 공사구간 : 154kV 이리-백산T/L No.8 ～ 35호 나. 공사내용 1) 선종교체 : 19.226 C-km (ACSR 240㎟ → HSTACIR 240㎟) 2) 철탑교체 : 신설 6기, 철거 5기 [No.11, 19, 25, 28.1(신설), 32, 33호] 3) 임시선로 구성 및 기타 부대공사","2016-04-29 08:00","2016-05-05 18:00","취소","취소","연속",null,null,null,201602110062,"-"]
[173,"전북","군산","이리백산#1 T/L","154kV 이리-백산#1T/L 선종교체공사","가. 공사구간 : 154kV 이리-백산T/L No.8 ～ 35호 나. 공사내용 1) 선종교체 : 19.226 C-km (ACSR 240㎟ → HSTACIR 240㎟) 2) 철탑교체 : 신설 6기, 철거 5기 [No.11, 19, 25, 28.1(신설), 32, 33호] 3) 임시선로 구성 및 기타 부대공사","2016-04-22 08:00","2016-04-28 18:00","2016-04-04 08:00","2016-04-04 18:00","연속",null,null,null,201602110059,"-"]
[174,"전북","군산","이리백산#2 T/L","154kV 이리-백산#2T/L 선종교체공사","가. 공사구간 : 154kV 이리-백산T/L No.8 ～ 35호 나. 공사내용 1) 선종교체 : 19.226 C-km (ACSR 240㎟ → HSTACIR 240㎟) 2) 철탑교체 : 신설 6기, 철거 5기 [No.11, 19, 25, 28.1(신설), 32, 33호] 3) 임시선로 구성 및 기타 부대공사","2016-04-18 08:00","2016-04-21 18:00","2016-04-05 08:00","2016-04-05 18:00","연속",null,null,null,201602110054,"-"]
[175,"전북","군산","이리S/S 154kV #1 BUS","이리S/S 154kV #1 BUS","이리S/S 차단기 보통점검공사 - 메카니즘점검 및 경보시험 - 타임측정, 절연열화측정, CT포화시험 등","2016-04-07 10:00","2016-04-07 18:00","2016-04-07 10:00","2016-04-07 18:00","당일",null,null,null,201602120115,"-"]
[176,"전북","군산","팔봉영등#1 T/L","154kV 팔봉-영등#1T/L 정밀점검","No.1~14 구간 송전선로 정밀점검","2016-04-04 09:00","2016-04-04 18:00","취소","취소","당일",null,null,"신뢰도개선",201602110250,"-"]
[177,"전북","군산","팔봉영등#2 T/L","154kV 팔봉-영등#2T/L 정밀점검","No.1~14 구간 송전선로 정밀점검","2016-04-05 09:00","2016-04-05 18:00","취소","취소","당일",null,null,"신뢰도개선",201602110251,"-"]
[178,"전북","김제","고창홍농 T/L","고창S/S 고창-홍농T/L","축소형 고장기록장치 설치","2016-04-05 10:00","2016-04-05 18:00","2016-04-05 10:00","2016-04-05 18:00","당일",null,null,null,201512160010,"-"]
[179,"전북","김제","고창영광 T/L","고창S/S 고창-영광T/L","축소형 고장기록장치 설치","2016-04-04 10:00","2016-04-04 18:00","2016-04-04 10:00","2016-04-04 18:00","당일",null,null,null,201512160009,"-"]
[180,"전북","직할","무주용담수력 T/L","154kV 무주용담수력T/L 정밀점검","내용 : 정밀점검 구간 : No.1~83호","2016-04-18 09:00","2016-04-22 18:00","2016-04-18 09:00","2016-04-22 18:00","매일",null,null,null,201602110208,"-"]
[181,"전북","직할","북전주S/S 북전주-봉동#1T/L GIS","북전주S/S 154kV 북전주-봉동#1T/L","북전주S/S 170kV 북전주-봉동#1T/L GIS 보통점검","2016-04-01 09:30","2016-04-01 18:00","취소","취소","당일",null,null,"신뢰도개선",201602160279,"-"]
[182,"광주전남","강진","강진남창#1 T/L","154kV 강진-남창 등 3개T/L 접속개소 해소공사","○ 교체구간 - 강진-남창 #1 61~63, 79~82, 122~126호간 2.637km - 강진-남창 #2 52~54호간 0.695km","2016-04-04 08:00","2016-04-09 18:00","2016-04-04 08:00","2016-04-09 18:00","연속",null,null,null,201602160194,"-"]
[183,"광주전남","강진","강진남창#2 T/L","154kV 강진-남창 등 3개T/L 접속개소 해소공사","○ 교체구간 - 강진-남창 #1 61~63, 79~82, 122~126호간 2.637km - 강진-남창 #2 52~54호간 0.695km","2016-04-11 08:00","2016-04-12 18:00","2016-04-11 08:00","2016-04-12 18:00","연속",null,null,null,201602160199,"-"]
[184,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌#2T/L(전선접속개소 전력선교체공사)","345kV 광양-여수TP T/L 전선접속개소 전력선교체공사 - 77~84호 전력선 교체 관련 교차구간 안전이격거리 확보","2016-04-02 07:00","2016-04-12 18:00","2016-04-02 07:00","2016-04-12 18:00","연속",null,null,null,201602150521,"-"]
[185,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌#1T/L(전선접속개소 전력선교체공사)","345kV 광양-여수TP T/L 전선접속개소 전력선교체공사 - 77~84호 전력선 교체 관련 교차구간 안전이격거리 확보","2016-04-02 07:00","2016-04-12 18:00","2016-04-02 07:00","2016-04-12 18:00","연속",null,null,null,201602150520,"-"]
[186,"광주전남","순천","여수T/P 154kV #65 BUS","여수TP 154kV #65BUS(상반기 GIS 정밀점검공사)","2016년 상반기 순천전력지사 GIS 정밀점검공사 - GS Caltex GIS 정밀점검(CB,#2DS,상부BUS)","2016-04-08 13:00","2016-04-09 18:00","2016-04-08 13:00","2016-04-09 18:00","연속",null,null,null,201602150269,"-"]
[187,"광주전남","순천","여수T/P 154kV #60 BUS","여수TP 154kV #60BUS(상반기 GIS 정밀점검공사)","2016년 상반기 순천전력지사 GIS 정밀점검공사 - GS Caltex GIS 정밀점검(CB,#1DS,상부BUS)","2016-04-07 09:00","2016-04-08 13:00","2016-04-07 09:00","2016-04-08 13:00","연속",null,null,null,201602150268,"-"]
[188,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성#1TL(송전선로 보호반 성능개선)","영인기술(SEL-311) 154kV 송전선로 보호반 성능개선 내용:BFI,Trip 및 재폐로 용도 접점 변경(송운(계통)-419)","2016-04-20 10:00","2016-04-20 18:00","취소","취소","당일",null,null,null,201602120339,"-"]
[189,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성#2T/L(송전선로 보호반 성능개선)","영인기술(SEL-311) 154kV 송전선로 보호반 성능개선 내용:BFI,Trip 및 재폐로 용도 접점 변경(송운(계통)-419)","2016-04-21 10:00","2016-04-21 18:00","취소","취소","당일",null,null,null,201602120341,"-"]
[190,"광주전남","순천","여수산단여천#2 T/L","154kV 여수산단-여천#2T/L(송전선로 보호반 성능개선)","영인기술(SEL-311) 154kV 송전선로 보호반 성능개선 내용:BFI,Trip 및 재폐로 용도 접점 변경(송운(계통)-419)","2016-04-19 10:00","2016-04-19 18:00","취소","취소","당일",null,null,null,201602120334,"-"]
[191,"광주전남","순천","여수산단여천#1 T/L","154kV 여수산단-여천#1T/L(송전선로 보호반 성능개선)","영인기술(SEL-311) 154kV 송전선로 보호반 성능개선 내용:BFI,Trip 및 재폐로 용도 접점 변경(송운(계통)-419)","2016-04-18 10:00","2016-04-18 18:00","취소","취소","당일",null,null,null,201602120332,"-"]
[192,"대구경북","경산","진량노변 T/L","진량S/S 154kV 진량-노변T/L 휴전(6279 CB 건전도 확인)","6279 CB 정밀점검관련 건전도 확인","2016-04-15 15:00","2016-04-15 16:00","2016-04-15 15:00","2016-04-15 16:00","당일",null,null,null,201602120386,"-"]
[193,"대구경북","경산","신경산진량 T/L","진량S/S 154kV 신경산-진량T/L 휴전(6179 CB 건전도 확인)","6179 CB 건전도 확인용도","2016-04-12 15:00","2016-04-12 16:00","2016-04-12 15:00","2016-04-12 16:00","당일",null,null,null,201602120374,"-"]
[194,"대구경북","구미","구미고아#1 T/L","154kV 구미-고아T/L 지장송전선로 이설공사","철탑 : 5기 신설(No.10,11,17,18,19), 5기 철거 전력선교체 : 2.194km(HSTACIR/AW 330mm2 X S X 2C)","2016-04-16 08:00","2016-04-18 18:00","2016-04-16 08:00","2016-04-18 18:00","연속",null,null,null,201602150010,"-"]
[195,"대구경북","구미","구미고아#2 T/L","154kV 구미-고아T/L 지장송전선로 이설공사","철탑 : 5기 신설(No.10,11,17,18,19), 5기 철거 전력선교체 : 2.194km(HSTACIR/AW 330mm2 X S X 2C)","2016-04-16 08:00","2016-04-18 18:00","2016-04-16 08:00","2016-04-18 18:00","연속",null,null,null,201602150011,"-"]
[196,"대구경북","안동","안동안동HP T/L","154kV 안동-안동HP T/L 송전용 접속설비 대체공사","안동수력발전소 전기설비 현대화에 따른 No.1 이설","2016-04-25 09:00","2016-05-05 18:00","2016-04-25 09:00","2016-05-05 18:00","연속",null,null,null,201602190097,"-"]
[197,"대구경북","안동","신영주안동#1 T/L","안동S/S 신영주-안동#1T/L 관련기기 점검","안동S/S 신영주-안동#1T/L GIS 초기, LA 보통점검","2016-04-25 09:00","2016-04-25 18:00","2016-04-25 09:00","2016-04-25 18:00","당일",null,null,null,201602140173,"-"]
[198,"대구경북","안동","신영주안동#2 T/L","안동S/S 신영주-안동#2T/L 관련기기 점검","안동S/S 신영주-안동#2T/L GIS 초기, LA 보통점검","2016-04-29 09:00","2016-04-29 18:00","2016-04-29 09:00","2016-04-29 18:00","당일",null,null,null,201602140174,"-"]
[199,"대구경북","칠곡","칠곡인동#1 T/L","송전선로 정밀점검","- 구간 : No.1~128","2016-04-11 09:00","2016-04-15 18:00","2016-04-11 09:00","2016-04-15 18:00","연속",null,null,null,201602150296,"-"]
[200,"대구경북","칠곡","칠곡인동#2 T/L","칠곡-인동T/L 정밀점검간 안전확보 및 정밀점검","- 병가구간 : No.9~16(#1,2T/L 수직배열)","2016-04-12 09:00","2016-04-12 18:00","2016-04-12 09:00","2016-04-12 18:00","당일",null,null,null,201602150301,"-"]
[201,"대구경북","포항","신포항영일#1 T/L","신포항-영일#1T/L 관련설비 점검","신포항S/S 6A7 CB, LA 보통, PT 초기점검 영일S/S 697 GIS 초기, PT, LA 보통점검","2016-04-07 09:00","2016-04-07 18:00","2016-04-07 09:00","2016-04-07 18:00","당일",null,null,null,201602120855,"-"]
[202,"대구경북","포항","신포항영일#2 T/L","신포항-영일#2T/L 관련설비 점검","신포항S/S 697 CB, LA 보통, PT 초기점검 영일S/S 6A7 GIS 초기, PT, LA 보통점검","2016-04-08 09:00","2016-04-08 18:00","2016-04-08 09:00","2016-04-08 18:00","당일",null,null,null,201602120858,"-"]
[203,"부산울산","동부산","웅촌서창#2 T/L","154kV 웅촌-서창#2T/L 안전이격(교각상판작업)","18~19호 간 선하지 안전이격(교각상판작업) 발주청: 부산국토개발청, 시공사 : 코오롱 글로벌","2016-04-10 08:00","2016-04-10 17:00","2016-04-10 08:00","2016-04-10 17:00","당일",null,null,null,201602040061,"-"]
[204,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창#1T/L 안전이격(교각상판작업)","18~19호 간 선하지 안전이격(교각상판작업) 발주청: 부산국토개발청, 시공사 : 코오롱 글로벌","2016-04-09 08:00","2016-04-10 17:00","2016-04-09 08:00","2016-04-10 17:00","매일",null,null,null,201602040062,"-"]
[205,"부산울산","북부산","북부산삼랑진PP#1 T/L","154kV 북부산-삼랑진양수T/L 접속개소 전선교체공사","154kV 북부산-삼랑진양수#1T/L 접속개소 전선교체공사 (25호~45호)","2016-04-25 08:00","2016-05-09 18:00","2016-04-25 08:00","2016-05-09 18:00","연속",null,null,null,201602120134,"○"]
[206,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진양수T/L 접속개소 전선교체공사","154kV 북부산-삼랑진양수#1T/L 접속개소 전선교체공사 (4회선 구간 작업시 작업자 안전거리 확보)","2016-04-25 08:00","2016-05-09 18:00","2016-04-25 08:00","2016-05-09 18:00","연속",null,null,null,201602120151,"-"]
[207,"부산울산","북부산","삼계어방 T/L","장기사용 보호배전반 대체","장기사용 보호배전반 대체","2016-04-09 09:00","2016-04-10 18:00","2016-04-09 09:00","2016-04-10 18:00","연속",null,null,null,201602160007,"-"]
[208,"부산울산","북부산","서부산엄궁#2 T/L","장기사용 배전반 대체공사","서부산-엄궁#2T/L 보호배전반 대체","2016-04-07 09:00","2016-04-09 18:00","2016-04-07 09:00","2016-04-09 18:00","연속",null,null,null,201602160183,"-"]
[209,"부산울산","북부산","서부산엄궁#1 T/L","장기사용 배전반 대체공사","서부산-엄궁#1T/L 보호배전반 대체","2016-04-04 09:00","2016-04-06 18:00","2016-04-04 09:00","2016-04-06 18:00","연속",null,null,null,201602160162,"○"]
[210,"부산울산","북부산","모라엄궁#1 T/L","2016년 북부산변전협력회사 총액공사","GIS 보통점검","2016-04-01 10:00","2016-04-01 18:00","2016-04-01 10:00","2016-04-01 18:00","당일",null,null,null,201602160004,"○"]
[211,"부산울산","북부산","학장개금#1 T/L","학장S/S 170kV 장기사용 GIS 대체","#4M.Tr 1차 GIS #2DS 철거에 따른 #2BUS 시험가압","2016-04-19 18:00","2016-04-19 20:00","2016-04-19 18:00","2016-04-19 20:00","당일",null,null,null,201602160016,"-"]
[212,"부산울산","북부산","학장개금#1 T/L","학장S/S 170kV 장기사용 GIS 대체","#4M.Tr 1차 GIS #1DS 설치에 따른 #1BUS 시험가압","2016-04-29 10:00","2016-05-01 10:00","2016-04-29 10:00","2016-05-01 10:00","연속",null,null,null,201602160017,"-"]
[213,"부산울산","서부산","서부산다대#2 T/L","154kV 서부산-다대T/L 지장이설공사","천마산터널 민간투자사업 지장송전선로 이설공사(서부산S/S ~ J/B#2 지중송전케이블 및 접속함 이설)","2016-04-18 13:00","2016-04-30 18:00","2016-04-18 13:00","2016-04-30 18:00","연속",null,null,null,201602110027,"-"]
[214,"부산울산","서부산","서부산다대#1 T/L","154kV 서부산-다대T/L 지장이설공사","천마산터널 민간투자사업 지장송전선로 이설(서부산S/S ~ J/B#2 지중송전케이블 및 접속함 이설)","2016-04-06 09:00","2016-04-18 12:00","2016-04-06 09:00","2016-04-18 12:00","연속",null,null,null,201602110022,"-"]
[215,"부산울산","울산","신울산영남TP#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","양단 보호배전반 대체, 신울산측 ILC PNL 대체, 영남화력측 617 GIS 보통점검","2016-04-02 08:00","2016-04-03 18:00","2016-04-02 08:00","2016-04-03 18:00","연속",null,null,null,201602120353,"-"]
[216,"부산울산","울산","방어진영남TP#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","양단 보호배전반 대체","2016-04-16 08:00","2016-04-17 18:00","2016-04-16 08:00","2016-04-17 18:00","연속",null,null,null,201602120349,"-"]
[217,"부산울산","울산","방어진영남TP#1 T/L","영남화력 170kV GIS 철거공사","6183,6283,6383 철거 후 #2BUS 설치부 시험가압(48H)","2016-04-22 18:00","2016-04-24 18:00","2016-04-22 18:00","2016-04-24 18:00","연속",null,null,null,201602050233,"-"]
[218,"부산울산","울산","방어진영남TP#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","양단 보호배전반 대체","2016-04-09 08:00","2016-04-10 18:00","2016-04-09 08:00","2016-04-10 18:00","연속",null,null,null,201602120348,"-"]
[219,"부산울산","울산","방어진영남TP#1 T/L","영남화력 170kV GIS 철거공사","6183,6283,6383 철거 후 #1BUS 설치부 시험가압(48H)","2016-04-30 09:00","2016-05-02 09:00","2016-04-30 09:00","2016-05-02 09:00","연속",null,null,null,201602050235,"-"]
[220,"부산울산","울산","용연처용#1 T/L","2016년 가공송전 순시점검 위탁공사(울산전력지사)","송전선로 정밀점검 : 24기","2016-04-11 09:00","2016-04-12 18:00","2016-04-11 09:00","2016-04-12 18:00","연속",null,null,null,201602150384,"-"]
[221,"부산울산","울산","용연처용#2 T/L","2016년 가공송전 순시점검 위탁공사(울산전력지사)","송전선로 정밀점검 : 24기","2016-04-14 09:00","2016-04-15 18:00","2016-04-14 09:00","2016-04-15 18:00","연속",null,null,null,201602150385,"-"]
[222,"부산울산","울산","울산T/P 154kV #65 BUS","2016년 170kV 개폐장치 정밀점검공사","65-66-1,65-66-0 정밀점검","2016-04-27 08:00","2016-04-28 18:00","2016-04-27 08:00","2016-04-28 18:00","연속",null,null,null,201602120331,"○"]
[223,"부산울산","울산","울산T/P 154kV #1 BUS TIE CB","2016년 170kV 개폐장치 정밀점검공사","6100 GIS 정밀점검","2016-04-18 08:00","2016-04-20 18:00","2016-04-18 08:00","2016-04-20 18:00","연속",null,null,null,201602120284,"○"]
[224,"부산울산","울산","울산T/P 154kV #60 BUS","2016년 170kV 개폐장치 정밀점검공사","6101,6100 정밀점검","2016-04-19 08:00","2016-04-20 18:00","2016-04-19 08:00","2016-04-20 18:00","연속",null,null,null,201602120256,"○"]
[225,"부산울산","울산","울산울산TP#1 T/L","2016년 170kV 개폐장치 정밀점검공사","617 GIS 정밀점검, 울산측 6A7 GIS 보통점검","2016-04-04 08:00","2016-04-06 18:00","2016-04-04 08:00","2016-04-06 18:00","연속",null,null,null,201602120246,"○"]
[226,"부산울산","울산","울산T/P 154kV #60 BUS","2016년 170kV 개폐장치 정밀점검공사","611,617,616 정밀점검","2016-04-05 08:00","2016-04-06 18:00","2016-04-05 08:00","2016-04-06 18:00","연속",null,null,null,201602120254,"○"]
[227,"부산울산","울산","울산T/P 60-61-0 SEC CB","2016년 170kV 개폐장치 정밀점검공사","60-61-0 GIS 정밀점검","2016-04-21 08:00","2016-04-23 18:00","2016-04-21 08:00","2016-04-23 18:00","연속",null,null,null,201602120338,"-"]
[228,"부산울산","울산","울산T/P 154kV #60 BUS","2016년 170kV 개폐장치 정밀점검공사","60-61-1,60-61-0 정밀점검","2016-04-23 08:00","2016-04-24 18:00","2016-04-23 08:00","2016-04-24 18:00","연속",null,null,null,201602120327,"○"]
[229,"부산울산","울산","울산T/P 65-66-0 SEC CB","2016년 170kV 개폐장치 정밀점검공사","65-66-0 GIS 정밀점검","2016-04-25 08:00","2016-04-27 18:00","2016-04-25 08:00","2016-04-27 18:00","연속",null,null,null,201602120340,"○"]
[230,"부산울산","울산","울산T/P 154kV #61 BUS","2016년 170kV 개폐장치 정밀점검공사","641,647,646 정밀점검","2016-04-29 08:00","2016-04-30 18:00","2016-04-29 08:00","2016-04-30 18:00","연속",null,null,null,201602120263,"-"]
[231,"부산울산","울산","용연울산TP#1 T/L","2016년 170kV 개폐장치 정밀점검공사","647 GIS 정밀점검","2016-04-28 08:00","2016-04-30 18:00","2016-04-28 08:00","2016-04-30 18:00","연속",null,null,null,201602120268,"-"]
[232,"부산울산","울산","울산T/P 154kV #61 BUS","2016년 170kV 개폐장치 정밀점검공사","651,657,656 정밀점검","2016-04-15 08:00","2016-04-16 18:00","2016-04-15 08:00","2016-04-16 18:00","연속",null,null,null,201602120265,"-"]
[233,"부산울산","울산","용연울산TP#2 T/L","2016년 170kV 개폐장치 정밀점검공사","657 GIS 정밀점검","2016-04-14 08:00","2016-04-16 18:00","2016-04-14 08:00","2016-04-16 18:00","연속",null,null,null,201602120267,"-"]
[234,"부산울산","울산","울산T/P 154kV #60 BUS","2016년 170kV 개폐장치 정밀점검공사","621,627,626 정밀점검","2016-04-08 08:00","2016-04-09 18:00","2016-04-08 08:00","2016-04-09 18:00","연속",null,null,null,201602120252,"○"]
[235,"부산울산","울산","울산울산TP#2 T/L","2016년 170kV 개폐장치 정밀점검공사","627 GIS 정밀점검, 울산측 687 GIS 보통점검","2016-04-07 08:00","2016-04-09 18:00","2016-04-07 08:00","2016-04-09 18:00","연속",null,null,null,201602120248,"-"]
[236,"부산울산","울산","울산울산TP#2 T/L","2016년 170kV 개폐장치 정밀점검공사","60-61-1,60-61-0 시험가압(1H)","2016-04-23 17:00","2016-04-23 18:00","2016-04-23 17:00","2016-04-23 18:00","당일",null,null,null,201602120274,"-"]
[237,"부산울산","울산","울산T/P 154kV #61 BUS","2016년 170kV 개폐장치 정밀점검공사","60-61-2 정밀점검","2016-04-21 08:00","2016-04-22 18:00","2016-04-21 08:00","2016-04-22 18:00","연속",null,null,null,201602120300,"-"]
[238,"부산울산","울산","울산T/P 154kV #65 BUS","2016년 170kV 개폐장치 정밀점검공사","612 정밀점검","2016-04-04 08:00","2016-04-04 18:00","2016-04-04 08:00","2016-04-04 18:00","당일",null,null,null,201602120250,"○"]
[239,"부산울산","울산","울산울산TP#2 T/L","2016년 170kV 개폐장치 정밀점검공사","6101,6100 시험가압(1H)","2016-04-20 17:00","2016-04-20 18:00","2016-04-20 17:00","2016-04-20 18:00","당일",null,null,null,201602120273,"-"]
[240,"부산울산","울산","울산울산TP#2 T/L","2016년 170kV 개폐장치 정밀점검공사","6102 시험가압(1H)","2016-04-18 17:00","2016-04-18 18:00","2016-04-18 17:00","2016-04-18 18:00","당일",null,null,null,201602120272,"-"]
[241,"부산울산","울산","울산T/P 154kV #65 BUS","2016년 170kV 개폐장치 정밀점검공사","6102 정밀점검","2016-04-18 08:00","2016-04-18 18:00","2016-04-18 08:00","2016-04-18 18:00","당일",null,null,null,201602120257,"○"]
[242,"부산울산","울산","울산울산TP#2 T/L","2016년 170kV 개폐장치 정밀점검공사","65-66-1,65-66-0 시험가압(1H)","2016-04-27 17:00","2016-04-27 18:00","2016-04-27 17:00","2016-04-27 18:00","당일",null,null,null,201602120279,"-"]
[243,"부산울산","울산","용연울산TP#1 T/L","2016년 170kV 개폐장치 정밀점검공사","65-66-2 시험가압(1H)","2016-04-25 17:00","2016-04-25 18:00","2016-04-25 17:00","2016-04-25 18:00","당일",null,null,null,201602120281,"-"]
[244,"부산울산","울산","울산T/P 154kV #66 BUS","2016년 170kV 개폐장치 정밀점검공사","65-66-2 정밀점검","2016-04-25 08:00","2016-04-26 18:00","2016-04-25 08:00","2016-04-26 18:00","당일",null,null,null,201602120333,"○"]
[245,"부산울산","울산","울산T/P 154kV #66 BUS","2016년 170kV 개폐장치 정밀점검공사","642 정밀점검","2016-04-28 08:00","2016-04-28 18:00","2016-04-28 08:00","2016-04-28 18:00","당일",null,null,null,201602120261,"○"]
[246,"부산울산","울산","울산T/P 154kV #66 BUS","2016년 170kV 개폐장치 정밀점검공사","652 정밀점검","2016-04-14 08:00","2016-04-14 18:00","2016-04-14 08:00","2016-04-14 18:00","당일",null,null,null,201602120260,"○"]
[247,"부산울산","울산","울산T/P 154kV #65 BUS","2016년 170kV 개폐장치 정밀점검공사","622 정밀점검","2016-04-07 08:00","2016-04-07 18:00","2016-04-07 08:00","2016-04-07 18:00","당일",null,null,null,201602120251,"○"]
[248,"부산울산","울산","용연울산TP#1 T/L","2016년 170kV 개폐장치 정밀점검공사","60-61-2 시험가압(1H)","2016-04-21 17:00","2016-04-21 18:00","2016-04-21 17:00","2016-04-21 18:00","당일",null,null,null,201602120283,"-"]
[249,"부산울산","직할","부산S/S 154kV #1 BUS TIE CB","16년 직할 상반기 170kV GIS 정밀점검","6100 GIS 정밀점검","2016-04-14 08:00","2016-04-16 18:00","2016-04-14 08:00","2016-04-16 18:00","연속",null,null,null,201602130002,"-"]
[250,"부산울산","직할","서부산부산 T/L","154kV 부산-영도T/L등 3개T/L 임시이설공사","부산S/S배전 인출정비 전력구 공사에 따른 154kV 부산-영도#1,2T/L, 서부산-부산T/L을 전력구 중앙측으로 20cm 임시이설","2016-04-01 09:00","2016-04-02 18:00","2016-04-01 09:00","2016-04-02 18:00","연속",null,null,null,201602150225,"-"]
[251,"부산울산","직할","부산수정#2 T/L","16년 직할 상반기 170kV GIS 정밀점검","부산-수정#2T/L GIS 정밀점검","2016-04-28 08:00","2016-04-30 18:00","2016-04-28 08:00","2016-04-30 18:00","연속",null,null,null,201602130012,"-"]
[252,"부산울산","직할","부산수정#1 T/L","16년 직할 상반기 170kV GIS 정밀점검","부산-수정#1T/L GIS 정밀점검","2016-04-25 08:00","2016-04-27 18:00","2016-04-25 08:00","2016-04-27 18:00","연속",null,null,null,201602130011,"-"]
[253,"부산울산","직할","부산S/S 154kV #1 BUS","16년 직할 상반기 170kV GIS 정밀점검","#3M.Tr 1차 GIS CB, 1DS 정밀점검","2016-04-22 09:00","2016-04-23 18:00","2016-04-22 09:00","2016-04-23 18:00","연속",null,null,null,201602150317,"-"]
[254,"부산울산","직할","부산S/S 154kV #1 BUS","16년 직할 상반기 170kV GIS 정밀점검","#2M.Tr 1차 GIS CB, 1DS 정밀점검","2016-04-19 09:00","2016-04-20 18:00","2016-04-19 09:00","2016-04-20 18:00","연속",null,null,null,201602150314,"-"]
[255,"부산울산","직할","부산S/S 154kV #2 BUS","16년 직할 상반기 170kV GIS 정밀점검","#2M.Tr 1차 GIS 2DS 정밀점검","2016-04-18 08:00","2016-04-18 19:00","2016-04-18 08:00","2016-04-18 19:00","당일",null,null,null,201602150312,"-"]
[256,"부산울산","직할","부산S/S 154kV #2 BUS","16년 직할 상반기 170kV GIS 정밀점검","#3M.Tr 1차 GIS 2DS 정밀점검","2016-04-21 08:00","2016-04-21 19:00","2016-04-21 08:00","2016-04-21 19:00","당일",null,null,null,201602150316,"-"]
[257,"부산울산","직할","부산영도#1 T/L","16년 직할 상반기 170kV GIS 정밀점검","부산-영도#1T/L GIS 정밀점검","2016-04-10 08:00","2016-04-12 18:00","2016-04-10 08:00","2016-04-12 18:00","연속",null,null,null,201602130001,"-"]
[258,"부산울산","직할","신대연양정#2 T/L","신대연S/S 신대연-양정#2T/L(647) GIS 보통점검","신대연S/S 신대연-양정#2T/L(647) GIS 보통점검","2016-04-07 10:00","2016-04-07 18:00","2016-04-07 10:00","2016-04-07 18:00","당일",null,null,null,201602150306,"-"]
[259,"부산울산","직할","신대연양정#1 T/L","신대연S/S 신대연-양정#1T/L(637) GIS 보통점검","신대연S/S 신대연-양정#1T/L(637) GIS 보통점검","2016-04-06 10:00","2016-04-06 18:00","2016-04-06 10:00","2016-04-06 18:00","당일",null,null,null,201602150305,"-"]
[260,"부산울산","직할","부산영도#2 T/L","16년 직할 상반기 170kV GIS 정밀점검","영도,부산S/S 부산-영도#2T/L GIS 정밀점검","2016-04-03 08:00","2016-04-08 18:00","2016-04-03 08:00","2016-04-08 18:00","연속",null,null,null,201602110408,"-"]
[261,"경남","직할","신김해진영#1 T/L","154kV 신김해-진영T/L 건설공사(불량설비 교체)","154kV 신김해-진영T/L 건설공사-불량설비(압축인류크램프) 교체(S/T)","2016-04-09 08:00","2016-04-09 12:00","2016-04-09 08:00","2016-04-09 12:00","당일",null,null,null,201602120069,"-"]
[262,"경남","진주","거창합천#2 T/L","154kV 의령-이현 등 8개T/L 피뢰기설치 및 전선교체공사","154kV 거창-합천T/L 59~63호","2016-04-28 07:00","2016-04-30 20:00","2016-04-28 07:00","2016-04-30 20:00","연속",null,null,null,201602120047,"-"]
[263,"경남","진주","거창합천#1 T/L","154kV 의령-이현 등 8개T/L 피뢰기설치 및 전선교체공사","154kV 거창-합천T/L 59~63호","2016-04-25 07:00","2016-04-27 20:00","2016-04-25 07:00","2016-04-27 20:00","연속",null,null,null,201602120045,"-"]
[264,"경남","진주","함양거창#2 T/L","함양-거창#2T/L 변전설비 점검","함양-거창#2T/L 변전설비 보통점검(GCB,LA,CPD)","2016-04-15 09:30","2016-04-15 18:30","2016-04-15 09:30","2016-04-15 18:30","당일",null,null,null,201602180016,"-"]
[265,"경남","진주","함양거창#1 T/L","함양-거창#1T/L 변전설비 점검","함양-거창#1T/L 변전설비 보통점검(GCB,LA,CPD)","2016-04-14 09:30","2016-04-14 18:30","2016-04-14 09:30","2016-04-14 18:30","당일",null,null,null,201602180015,"-"]
[266,"경남","진주","거창합천#2 T/L","합천S/S BUS TIE 6100 정밀점검_시험가압","합천S/S BUS TIE 6100 정밀점검(시험가압)","2016-04-22 16:00","2016-04-22 17:00","2016-04-22 16:00","2016-04-22 17:00","연속",null,null,null,201602120774,"-"]
[267,"경남","진주","거창합천#1 T/L","합천S/S BUS TIE 6100 정밀점검_시험가압","합천S/S BUS TIE 6100 정밀점검(시험가압)","2016-04-21 11:00","2016-04-21 12:00","2016-04-21 11:00","2016-04-21 12:00","연속",null,null,null,201602120765,"-"]
[268,"경남","통영","고성S/S 154kV #1 BUS","고성S/S 170kV GIS대체공사관련 154kV #1 BUS 휴전","고성S/S 고성-통영T/L 및 154kV PT GIS 대체공사관련 154kV #1 BUS 휴전","2016-04-25 09:30","2016-05-05 18:30","2016-04-25 09:30","2016-05-05 18:30","연속",null,null,null,201602040025,"-"]
[269,"경남","통영","고성통영 T/L","고성S/S 고성-통영T/L 및 154kV PT GIS 대체공사","고성S/S 고성-통영T/L 및 154kV PT GIS 대체공사","2016-04-18 09:30","2016-05-05 18:30","2016-04-18 09:30","2016-05-05 18:30","연속",null,null,null,201602040019,"-"]
[270,"경남","통영","신고성삼천포#1 T/L","삼천포S/S 154kV 신고성-삼천포#1T/L GIS 정밀점검","삼천포S/S 154kV 신고성-삼천포#1T/L GIS 정밀점검","2016-04-25 09:30","2016-04-27 18:30","2016-04-25 09:30","2016-04-27 18:30","연속",null,null,null,201602020015,"-"]
[271,"경남","통영","신고성삼천포#2 T/L","삼천포S/S 154kV 신고성-삼천포#2T/L GIS 정밀점검","삼천포S/S 154kV 신고성-삼천포#2T/L GIS 정밀점검","2016-04-28 09:30","2016-04-30 18:30","2016-04-28 09:30","2016-04-30 18:30","연속",null,null,null,201602020016,"-"]
[272,"경남","통영","삼천포사천#2 T/L","삼천포S/S 신고성-삼천포#2T/L GIS 정밀점검관련 시험가압","삼천포S/S 신고성-삼천포#2T/L GIS 정밀점검관련 #2 BUS 시험가압","2016-04-28 17:30","2016-04-28 18:30","2016-04-28 17:30","2016-04-28 18:30","당일",null,null,null,201602020020,"-"]
[273,"경남","통영","삼천포사천#2 T/L","삼천포S/S 신고성-삼천포#1T/L GIS 정밀점검관련 시험가압","삼천포S/S 신고성-삼천포#1T/L GIS 정밀점검관련 #2 BUS 시험가압","2016-04-25 17:30","2016-04-25 18:30","2016-04-25 17:30","2016-04-25 18:30","당일",null,null,null,201602020018,"-"]
[274,"경남","통영","통영거제#2 T/L","154kV 고성-통영T/L 송전용 피뢰기 설치공사 안전이격","154kV 고성-통영T/L 송전용 피뢰기 설치공사 안전이격","2016-04-30 08:30","2016-05-01 17:30","2016-04-30 08:30","2016-05-01 17:30","매일",null,null,null,201601110029,"-"]
[275,"경남","함안","청도밀양#1 T/L","밀양SS 170kV GIS 교체공사","170kV 청도-밀양#1T/L 대체(철거 및 설치)","2016-04-14 08:00","2016-05-03 17:30","2016-04-14 08:00","2016-05-03 17:30","연속",null,null,null,201602120656,"-"]
[276,"경남","함안","신마산S/S 154kV #65 BUS","신마산 170kV GIS 정밀점검공사","신마산 170kV #2Sh.C 6279 GIS Bay 정밀점검 6279,6276,6271GIS부 정밀점검","2016-04-07 19:30","2016-04-09 18:30","2016-04-07 19:30","2016-04-09 18:30","연속",null,null,null,201602120211,"-"]
[277,"경남","함안","신마산차룡#2 T/L","신마산-차룡 #2 T/L 이도조정 및 스페이서 간격조정","신마산-차룡 #2 T/L 이도조정 : 28~31호 구간 스페이서 간격조정 : S/T ~ 46호","2016-04-09 08:30","2016-04-10 17:30","2016-04-09 08:30","2016-04-10 17:30","연속",null,null,null,201602160297,"-"]
[278,"경남","함안","신마산S/S 154kV #60 BUS","신마산 170kV GIS 정밀점검공사","신마산 170kV #1Sh.C 6179 GIS Bay 정밀점검 6179,6176,6171GIS부 정밀점검","2016-04-04 19:30","2016-04-06 18:30","2016-04-04 19:30","2016-04-06 18:30","연속",null,null,null,201602120078,"-"]
[279,"경남","함안","신마산차룡#2 T/L","신마산-차룡 #2 T/L 이도조정 및 스페이서 간격조정","신마산-차룡 #2 T/L 이도조정 : 28~31호 구간 스페이서 간격조정 : S/T ~ 46호","2016-04-02 08:30","2016-04-03 17:30","2016-04-02 08:30","2016-04-03 17:30","연속",null,null,null,201602050051,"-"]
[280,"경남","함안","신마산중리#2 T/L","중리SS 170kV GIS 정밀점검공사","중리SS 중리-가야#2T/L 617 GIS 정밀점검 -612 DS부 시험가압","2016-04-18 18:30","2016-04-18 19:30","2016-04-18 18:30","2016-04-18 19:30","당일",null,null,null,201602120156,"-"]
[281,"경남","함안","신마산중리#2 T/L","중리SS 170kV GIS 정밀점검공사","중리SS 중리-가야#2T/L 617 GIS 정밀점검 -611,617,616부 시험가압","2016-04-20 18:30","2016-04-20 19:30","2016-04-20 18:30","2016-04-20 19:30","당일",null,null,null,201602120157,"-"]
[282,"경남","함안","신마산중리#1 T/L","중리SS 170kV GIS 정밀점검공사","중리SS 중리-가야#1T/L 627 GIS 정밀점검 -622 DS부 시험가압","2016-04-21 18:30","2016-04-21 19:30","2016-04-21 18:30","2016-04-21 19:30","당일",null,null,null,201602120167,"-"]
[283,"경남","함안","신마산중리#1 T/L","중리SS 170kV GIS 정밀점검공사","중리SS 중리-가야#1T/L 627 GIS 정밀점검 -621,626,627 시험가압","2016-04-23 18:30","2016-04-23 19:30","2016-04-23 18:30","2016-04-23 19:30","당일",null,null,null,201602120169,"-"]

{"sheet":"중부","index":3,"n_rows":9,"n_cols":16,"rows_kept":9,"cut":false,"hidden":false,"merged":[[4,15,5,15],[4,10,5,10],[4,11,5,11],[4,12,5,12],[4,13,5,13],[4,14,5,14],[1,0,1,4],[4,6,4,7],[4,8,4,9],[4,0,5,0],[4,1,5,1],[4,2,5,2],[4,3,5,3],[4,4,5,4],[4,5,5,5]]}
["회사명 : 한국중부발전㈜"]
["2016년 04월 월간 휴전계획표"]
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[2,"보령화력","복합발전소","GT #1,2 M-TR\n(7100, 7172)","GT #1,2 주변압기(MT0001)점검","상분리모선(IPB) 및 지지애자 점검\n갑종보호계전기 시험","2016-04-09\n08:00","2016-04-10\n23:00","2016-04-09\n08:00","2016-04-10\n23:00"]
[3,"보령화력","복합발전소","ST #1 M-TR\n(7200, 7272)","ST #1 주변압기(MT0002)점검","상분리모선(IPB) 및 지지애자 점검\n갑종보호계전기 시험","2016-04-14\n09:00","2016-04-25\n23:00","2016-04-14\n09:00","2016-04-25\n23:00"]
[4,"보령화력","복합발전소","GT #1,2 M-TR\n(7100, 7172)","GT #1,2 주변압기(MT0001)점검","상분리모선(IPB) 및 지지애자 점검\n갑종보호계전기 시험","2016-04-16\n08:00","2016-04-17\n23:00","2016-04-16\n08:00","2016-04-17\n23:00"]

{"sheet":"동서","index":4,"n_rows":11,"n_cols":14,"rows_kept":11,"cut":false,"hidden":false,"merged":[[3,13,4,13],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,3,7],[3,8,3,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[8,13,9,13],[8,0,9,0],[8,1,9,1],[8,2,9,2],[8,3,9,3],[8,4,9,4],[8,5,9,5],[8,6,8,7],[8,8,8,9],[8,10,9,10],[8,11,9,11],[8,12,9,12]]}
["회사명 : 한국동서발전㈜"]
["2016년도 04월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"당진화력","당진화력","#8","계획예방정비공사","전력용변압기 및 법정검사\n(CB 8700/8771 OPEN)","2016-04-02 10:00","2016-05-21 24:00","2016-04-02 10:00","2016-05-21 24:00","연속","Y"]
[]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"울산화력","울산화력","GT #1,2 & ST #1","정기검사","갑종보호계전기 개체시험\n(CB 6533/6433 OPEN)","2016-04-07 09:00","2016-04-10 18:00","승인대상 아님","승인대상 아님","연속","Y"]

{"sheet":"서부","index":5,"n_rows":8,"n_cols":14,"rows_kept":8,"cut":false,"hidden":false,"merged":[[3,13,4,13],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,3,7],[3,8,3,9],[3,10,4,10],[3,11,4,11],[3,12,4,12]]}
["회사명 : 한국서부발전"]
["2016년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서인천발전본부","-","제1호기 승압변압기","제1호기 간이정비\n* 조작차단기 : 6133","- 제1호기 간이예방정비공사 및 법정검사 수검","2016-04-04 10:00","2016-04-07 16:00","2016-04-04 10:00","2016-04-07 16:00","연속"]
[2,"서인천발전본부","-","제2호기 승압변압기","제2호기 간이정비\n* 조작차단기 : 6233","- 제2호기 간이예방정비공사 및 법정검사 수검","2016-04-12 10:00","2016-04-20 16:00","2016-04-12 10:00","2016-04-20 16:00","연속"]
[3,"서인천발전본부","-","제6호기 승압변압기","제6호기 A급 계획예방정비공사\n* 조작차단기 : 6633","- 제6호기 A급 계획예방정비공사 및 법정검사 수검","2016-04-29 10:00","2016-05-31 16:00","2016-04-29 10:00","2016-05-31 16:00","연속"]

{"sheet":"수자원","index":6,"n_rows":8,"n_cols":16,"rows_kept":8,"cut":false,"hidden":false,"merged":[[3,14,4,14],[3,15,4,15],[3,6,3,7],[3,8,3,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,5,4,5],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4]]}
["회사명 : 한국수자원공사"]
["2016년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"주암H/P",null,"주암수력#1T/L","옥외변전소 애자청소 및 금구류 조임공사","옥외변전소 애자청소 및 금구류 조임공사","2016-04-25 09:00","2016-04-28 18:00","2016-04-25 09:00","2016-04-28 18:00","매일"]
[2,"주암H/P",null,"주암수력#2T/L","옥외변전소 애자청소 및 금구류 조임공사","옥외변전소 애자청소 및 금구류 조임공사","2016-04-25 09:00","2016-04-28 18:00","2016-04-25 09:00","2016-04-28 18:00","매일"]
[3,"안동H/P",null,"안동T/L","옥외변젼설비 현대화작업","옥외변젼설비 현대화작업","2016-04-25 06:00","2016-05-04 18:00","2016-04-25 06:00","2016-05-04 18:00","연속"]

{"sheet":"남부","index":7,"n_rows":15,"n_cols":16,"rows_kept":15,"cut":false,"hidden":false,"merged":[[10,14,11,14],[10,15,11,15],[10,6,10,7],[10,8,10,9],[10,10,11,10],[10,11,11,11],[10,12,11,12],[10,13,11,13],[10,0,11,0],[10,1,11,1],[10,2,11,2],[10,3,11,3],[10,4,11,4],[10,5,11,5],[3,10,4,10],[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,14,4,14],[3,15,4,15],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,3,7],[3,8,3,9]]}
["회사명 : 한국남부발전㈜"]
["2016년도 4월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"부산복합",null,"1MTG001 주변압기(#1,2GT용)","정기검사(법정검사) 수검(CB 7400, 7471)","정기검사(법정검사) 수검","2016-04-02 10:00","2016-04-08 18:00","2016-04-02 10:00","2016-04-08 18:00","연속"]
[2,"부산복합",null,"21MTG001 주변압기(#3,4GT용)","정기검사(법정검사) 수검(CB 7400, 7472)","정기검사(법정검사) 수검","2016-04-23 10:00","2016-04-29 18:00","2016-04-23 10:00","2016-04-29 18:00","연속"]
[3,"부산복합",null,"3MTG001 주변압기(#5,6GT용)","정기검사(법정검사) 수검(CB 7500, 7571)","정기검사(법정검사) 수검","2016-04-16 10:00","2016-04-22 18:00","2016-04-16 10:00","2016-04-22 18:00","연속"]
[]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"부산복합",null,"1MTS101 주변압기(#1ST용)","정기검사(법정검사) 수검(CB 687)","정기검사(법정검사) 수검","2016-04-02 10:00","2016-04-08 18:00","승인대상 아님","승인대상 아님","연속"]
[2,"부산복합",null,"21MTS201 주변압기(#2ST용)","정기검사(법정검사) 수검(CB 6L7)","정기검사(법정검사) 수검","2016-04-23 10:00","2016-04-29 18:00","승인대상 아님","승인대상 아님","연속"]
[3,"부산복합",null,"3MTS301 주변압기(#3ST용)","정기검사(법정검사) 수검(CB 657)","정기검사(법정검사) 수검","2016-04-16 10:00","2016-04-22 18:00","승인대상 아님","승인대상 아님","연속"]