{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":17,"n_cols":16,"rows_kept":17,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2016년도 6월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성신가평 T/L","765kV 신안성신가평T/L 철탑도장공사(No.37~38)","765kV 신안성신가평T/L 철탑도장공사(No.37~38) - 민원개소 환경친화도장 실시","2016-06-27 08:00","2016-06-30 18:00","2016-06-27 08:00","2016-06-30 18:00","연속",null,null,null,201604100061]
[2,"강원","태백","신태백-신가평#2T/L-#3 M.Tr 1차 CB","765kV 신태백S/S SW 증설공사","신태백-신한울N/P 보호배전반 설치 신태박-신기평T/L 연동시험","2016-06-01 10:00","2016-06-10 18:00","2016-06-01 10:00","2016-06-10 18:00","연속",null,null,null,201604150045]
[3,"강원","태백","신태백S/S 신태백-신가평#2T/L CB","765kV 신태백S/S SW 증설공사","신태백-신한울N/P 보호배전반 설치 신태박-신기평T/L 연동시험","2016-06-01 10:00","2016-06-10 18:00","2016-06-01 10:00","2016-06-10 18:00","연속",null,null,null,201604150049]
[4,"강원","태백","신태백-신가평#1T/L-#2 M.Tr 1차 CB","신태백S/S 800kV GIS 정밀점검공사[8300]","신태백S/S 800kV GIS 정밀점검공사[8300]","2016-06-20 09:00","2016-07-03 18:00","2016-06-20 09:00","2016-07-03 18:00","연속",null,null,null,201604170013]
[5,"강원","태백","신태백S/S 신태백-신가평#1T/L CB","신태백S/S 800kV GIS 정밀점검공사[8371]","신태백S/S 800kV GIS 정밀점검공사[8371]","2016-06-20 09:00","2016-07-03 18:00","2016-06-20 09:00","2016-07-03 18:00","연속",null,null,null,201604170014]
[6,"대전충남","서산","당진T/P 3호기 1차 CB","2016년 서산P/O 765/345kV GIS 점검공사","○765kV GIS 보통점검","2016-06-08 09:00","2016-06-09 18:00","2016-06-08 09:00","2016-06-09 18:00","연속",null,null,null,201602140084]
[7,"대전충남","서산","신서산S/S #3 M.Tr","신서산S/S #3M.Tr 1차 붓싱압력계 교체","○ 신서산S/S #3M.Tr 1차 붓싱압력계 교체","2016-06-27 09:00","2016-06-28 18:00","2016-06-27 09:00","2016-06-28 18:00","연속",null,null,null,201604180019]
[8,"대전충남","서산","신서산S/S #4 M.Tr","신서산S/S #4M.Tr PAN 전원 교체","○ 신서산S/S #4M.Tr PAN 전원 MCCB → ELCB 교체","2016-06-29 09:00","2016-06-30 18:00","2016-06-29 09:00","2016-06-30 18:00","연속",null,null,null,201604180022]
[9,"부산울산","동부산","신고리S/S #3M.Tr 1차-#5G TIE CB","신고리S/S 800kV GIS 보통점검공사","신고리S/S 800kV 8500 GIS 보통점검(#3M.Tr-G5-TIE)","2016-06-07 09:00","2016-06-10 18:00","2016-06-07 09:00","2016-06-10 18:00","연속",null,null,null,201604120348]
[10,"부산울산","동부산","신고리S/S #5GEN T/L CB","신고리S/S 800kV GIS 보통점검공사","신고리S/S 800kV 8572 GIS 보통점검(G5)","2016-06-07 09:00","2016-06-10 18:00","2016-06-07 09:00","2016-06-10 18:00","연속",null,null,null,201604120354]
[11,"경남","함안","북경남S/S #4 M.Tr","북경남S/S 765kV GIS 초기점검공사","- 북경남S/S 765kV #4 M.TR 휴전","2016-06-20 09:00","2016-06-21 18:00","2016-06-20 09:00","2016-06-21 18:00","연속",null,null,null,201604080085]
[12,"경남","함안","북경남S/S #3 M.Tr","북경남S/S 765kV GIS 초기점검공사","- 북경남S/S 765kV #3 M.TR 휴전","2016-06-22 09:00","2016-06-23 18:00","2016-06-22 09:00","2016-06-23 18:00","연속",null,null,null,201604080089]
[13,"경남","함안","북경남S/S #5 M.Tr","북경남S/S 765kV GIS 초기점검공사","- 북경남S/S 765kV #5 M.TR 휴전","2016-06-13 09:00","2016-06-15 18:00","2016-06-13 09:00","2016-06-15 18:00","연속",null,null,null,201604080092]

{"sheet":"345송부","index":1,"n_rows":171,"n_cols":16,"rows_kept":171,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"'765송부'!A1","v":"2016년도 6월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","신성남신양재 #1 T/L","신성남-신양재#1(D)T/L 구형 절연통보호장치 교체공사","신성남-신양재#1(D)T/L 구형 절연통보호장치 교체공사","2016-06-13 10:00","2016-06-17 10:00","2016-06-13 10:00","2016-06-17 10:00","연속",null,null,null,201603130012,"-"]
[2,"남서울","강남","신성남신양재#2 T/L","신성남-신양재#2(D)T/L 구형 절연통보호장치 교체공사","신성남-신양재#2(D)T/L 구형 절연통보호장치 교체공사","2016-06-20 10:00","2016-06-24 10:00","2016-06-20 10:00","2016-06-24 10:00","연속",null,null,null,201603130013,"-"]
[3,"남서울","동서울","동서울S/S #1 M.Tr A","동서울 #1M.Tr 보호반 교체공사","동서울 #1M.Tr 보호반 교체공사 냉각배관 점검 소내변압기 회로보완","2016-06-07 09:00","2016-06-10 18:00","2016-06-07 09:00","2016-06-10 18:00","연속",null,null,null,201604150369,"-"]
[4,"남서울","동서울","동서울S/S #2 M.Tr A","동서울 #2M.Tr 보호반 교체공사","동서울 #2M.Tr 보호반 교체공사 냉각배관 점검 소내변압기 회로보완","2016-06-13 09:00","2016-06-16 18:00","2016-06-13 09:00","2016-06-16 18:00","연속",null,null,null,201604150372,"-"]
[5,"남서울","동서울","동서울S/S #3 M.Tr A","동서울 #3M.Tr 냉각배관 점검","동서울 #3M.Tr 냉각배관 점검 소내변압기 회로보완","2016-06-20 09:00","2016-06-21 18:00","2016-06-20 09:00","2016-06-21 18:00","연속",null,null,null,201604150387,"-"]
[6,"남서울","동서울","동서울미금#1 T/L","동서울변전소 구내 EBA 비산방지장치 설치공사","동서울미금#1,2 EBA 비산방지장치 설치 공사","2016-06-13 09:00","2016-06-15 18:00","2016-06-13 09:00","2016-06-15 18:00","연속",null,null,null,201604190221,"-"]
[7,"남서울","동서울","동서울미금#2 T/L","동서울변전소 구내 EBA 비산방지장치 설치공사","동서울미금#1,2 EBA 비산방지장치 설치 공사","2016-06-16 09:00","2016-06-18 18:00","2016-06-16 09:00","2016-06-18 18:00","연속",null,null,null,201604190229,"-"]
[8,"남서울","동서울","동서울S/S #4 M.Tr A","동서울 #4M.Tr 냉각배관 점검","동서울 #4M.Tr 냉각배관 점검 EBG 비산방지 격벽 설치","2016-06-22 09:00","2016-06-23 18:00","2016-06-22 09:00","2016-06-23 18:00","연속",null,null,null,201604190244,"-"]
[9,"남서울","영서","영서S/S #3 M.Tr A","2016년 변전협력회사 총액공사_계획점검","- 영서S/S #3 M.Tr 초기 및 보통점검 - 영서S/S #3 M.Tr 1차 및 3차 LA 보통점검 - 영서S/S #3 M.Tr 3차 PT 보통점검 - 영서S/S #3 M.Tr 누유보수","2016-06-13 10:00","2016-06-17 18:00","2016-06-13 10:00","2016-06-17 18:00","연속",null,null,null,201604080244,"-"]
[10,"남서울","영서","영서S/S #4 M.Tr A","2016년 변전협력회사 총액공사_계획점검","- 영서S/S #4 M.Tr 보통점검 - 영서S/S #4 M.Tr 3차 LA 보통점검 - 영서S/S #4 M.Tr 3차 PT 보통점검","2016-06-07 10:00","2016-06-09 18:00","2016-06-07 10:00","2016-06-09 18:00","연속",null,null,null,201604080245,"-"]
[11,"인천","김포","345kV 신김포S/S #4Sh.R 1차 CB (7272)","345kV 신김포S/S #4Sh.R 1차 CB 기기점검","345kV 신김포S/S #4Sh.R 1차 7272CB 기기점검","2016-06-17 09:00","2016-06-17 18:00","2016-06-17 09:00","2016-06-17 18:00","당일",null,null,null,201603300205,"-"]
[12,"인천","김포","신김포S/S 345kV #4Sh.R","신김포S/S 345kV #4 Sh.R 기기점검","신김포S/S 345kV #4 Sh.R 기기점검","2016-06-17 09:00","2016-06-17 18:00","2016-06-17 09:00","2016-06-17 18:00","당일",null,null,null,201604130186,"-"]
[13,"인천","인천","서인천C/C #1 M.Tr","2016년 인천전력지사 170kV GIS 정밀점검 공사","서인천복합S/Y 345kV #1M.Tr 2차 GIS(6144) 정밀점검","2016-06-04 09:00","2016-06-06 18:00","2016-06-04 09:00","2016-06-06 18:00","연속",null,null,null,201604060009,"-"]
[14,"인천","인천","신경서S/S #2 M.Tr A","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S #2M.Tr 2차 GIS 정밀점검 공사","2016-06-16 09:00","2016-06-18 18:00","2016-06-16 09:00","2016-06-18 18:00","연속",null,null,null,201604060018,"-"]
[15,"인천","인천","서인천C/C 345kV #4 Sh.R","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #4Sh.R용 CB(7A79) 대체 및 DS 대체 - 기타 부대공사","2016-06-01 10:00","2016-06-15 17:00","2016-06-01 10:00","2016-06-15 17:00","연속",null,null,null,201604070055,"-"]
[16,"인천","인천","신인천C/C 345kV #72 BUS","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- #72BUS 모선개조 및 모선용 DS 대체 - CB(71-72-0) 대체","2016-06-01 10:00","2016-06-30 17:00","2016-06-01 10:00","2016-06-30 17:00","연속",null,null,null,201604070058,"-"]
[17,"인천","인천","서인천C/C 서인천신부평#3T/L-#4 M.Tr 1차 CB (7400)","서인천C/C #4 M.Tr 1차 GIS(7400) 초기점검","서인천C/C #4 M.Tr 1차 GIS(7400) 초기점검","2016-06-01 09:00","2016-06-01 18:00","2016-06-01 09:00","2016-06-01 18:00","당일",null,null,null,201604130183,"-"]
[18,"인천","인천","서인천C/C #4 M.Tr 1차 CB (7472)","서인천C/C #4 M.Tr 1차 GIS(7472) 초기점검","서인천C/C #4 M.Tr 1차 GIS(7472) 초기점검","2016-06-02 09:00","2016-06-02 18:00","2016-06-02 09:00","2016-06-02 18:00","당일",null,null,null,201604130184,"-"]
[19,"인천","인천","신인천C/C 4MT101 CB (7772)","신인천C/C #4MT101 GIS(7772) 초기점검","신인천C/C #4MT101 GIS(7772) 초기점검","2016-06-03 09:00","2016-06-03 18:00","2016-06-03 09:00","2016-06-03 18:00","당일",null,null,null,201604130187,"-"]
[20,"인천","인천","신인천C/C 70-71-0 SEC CB (70-71-0)","신인천C/C #70-71-0 SEC GIS(70-71) 초기점검","신인천C/C #70-71-0 SEC GIS(70-71) 초기점검","2016-06-07 09:00","2016-06-07 18:00","2016-06-07 09:00","2016-06-07 18:00","당일",null,null,null,201604130188,"-"]
[21,"인천","인천","신가좌S/S 345kV #1 BUS","신가좌S/S 345㎸ 용량부족 GIS 대체공사","신가좌S/S 345㎸ 용량부족 GIS 대체공사 - #1BUS 모선 교체 및 개조","2016-06-01 09:00","2016-06-20 18:00","2016-06-01 09:00","2016-06-20 18:00","연속",null,null,null,201604130191,"-"]
[22,"인천","인천","신가좌S/S 345kV #2 BUS","신가좌S/S 345㎸ 용량부족 GIS 대체공사","신가좌S/S 345㎸ 용량부족 GIS 대체공사 - #2BUS 모선 교체 및 개조","2016-06-21 09:00","2016-07-11 18:00","2016-06-21 09:00","2016-07-11 18:00","연속",null,null,null,201604130192,"-"]
[23,"인천","인천","인천CC S/Y #1TIE.Tr 1차 CB (7171)","인천CC S/Y #1TIE-Tr 1차 GIS(7171) 초기점검","인천CC S/Y #1TIE-Tr 1차 GIS(7171) 초기점검","2016-06-10 09:00","2016-06-10 18:00","2016-06-10 09:00","2016-06-10 18:00","당일",null,null,null,201604140001,"-"]
[24,"인천","인천","인천CC S/Y #1TIE.Tr 1차 - TIE CB (7100)","인천CC S/Y #1TIE-Tr 1차 GIS(7100) 초기점검","인천CC S/Y #1TIE-Tr 1차 GIS(7100) 초기점검","2016-06-13 09:00","2016-06-13 18:00","2016-06-13 09:00","2016-06-13 18:00","당일",null,null,null,201604140003,"-"]
[25,"인천","인천","인천CC S/Y 신경서인천CC#2T/L CB (7471)","인천CC S/Y 신경서인천CC#2T/L GIS(7471) 초기점검","인천CC S/Y 신경서인천CC#2T/L GIS(7471) 초기점검","2016-06-14 09:00","2016-06-14 18:00","2016-06-14 09:00","2016-06-14 18:00","당일",null,null,null,201604140004,"-"]
[26,"인천","인천","인천CC S/Y 70-71-0 SEC CB (70-71-0-9)","인천CC S/Y #70-71 SEC GIS(70-71) 초기점검","인천CC S/Y #70-71 SEC GIS(70-71) 초기점검","2016-06-15 09:00","2016-06-15 18:00","2016-06-15 09:00","2016-06-15 18:00","당일",null,null,null,201604140005,"-"]
[27,"인천","인천","인천CC S/Y 75-76-0 SEC CB (75-76-0)","인천CC S/Y #75-76 SEC GIS(75-76) 초기점검","인천CC S/Y #75-76 SEC GIS(75-76) 초기점검","2016-06-16 09:00","2016-06-16 18:00","2016-06-16 09:00","2016-06-16 18:00","당일",null,null,null,201604140006,"-"]
[28,"인천","인천","인천CC S/Y 가정인천#2T/L CB (7C71)","인천CC S/Y 가정인천#2T/L GIS(7C71) 초기점검","인천CC S/Y 가정인천#2T/L GIS(7C71) 초기점검","2016-06-17 09:00","2016-06-17 18:00","2016-06-17 09:00","2016-06-17 18:00","당일",null,null,null,201604140007,"-"]
[29,"인천","인천","인천CC S/Y 가정인천#2 - #2TIE Tr 1차 CB (7C00)","인천CC S/Y #2Tie-Tr 1차 GIS(7C00) 초기점검","인천CC S/Y #2Tie-Tr 1차 GIS(7C00) 초기점검","2016-06-20 09:00","2016-06-20 18:00","2016-06-20 09:00","2016-06-20 18:00","당일",null,null,null,201604140008,"-"]
[30,"인천","인천","인천CC S/Y #2 TIE Tr 1차 CB (7C72)","인천CC S/Y #2Tie-Tr 1차 GIS(7C72) 초기점검","인천CC S/Y #2Tie-Tr 1차 GIS(7C72) 초기점검","2016-06-21 09:00","2016-06-21 18:00","2016-06-21 09:00","2016-06-21 18:00","당일",null,null,null,201604140009,"-"]
[31,"인천","인천","신경서S/S 서인천인천CC#2T/L CB (7372)","신경서S/S 신경서인천CC#2T/L GIS(7372) 초기점검","신경서S/S 신경서인천CC#2T/L GIS(7372) 초기점검","2016-06-22 09:00","2016-06-22 18:00","2016-06-22 09:00","2016-06-22 18:00","당일",null,null,null,201604140010,"-"]
[32,"인천","인천","신경서S/S 신경서서인천CCT/L-TIE CB (7400)","신경서S/S 신경서서인천CCT/L GIS(7400) 초기점검","신경서S/S 신경서서인천CCT/L GIS(7400) 초기점검","2016-06-23 09:00","2016-06-23 18:00","2016-06-23 09:00","2016-06-23 18:00","당일",null,null,null,201604140011,"-"]
[33,"인천","인천","신경서S/S 서인천서인천CCT/L CB (7472)","신경서S/S 신경서서인천CCT/L GIS(7472) 초기점검","신경서S/S 신경서서인천CCT/L GIS(7472) 초기점검","2016-06-24 09:00","2016-06-24 18:00","2016-06-24 09:00","2016-06-24 18:00","당일",null,null,null,201604140012,"-"]
[34,"인천","인천","신경서S/S 345kV #1 Sh.R","신경서S/S #1Sh.R 제작사 점검","신경서S/S #1Sh.R 제작사 점검 - #1Sh.R 소음 및 진동 방지 보강 공사 - 유중가스 분석결과 3회이상 이상 발생 관련 점검","2016-06-20 09:00","2016-06-25 18:00","2016-06-20 09:00","2016-06-25 18:00","연속",null,null,null,201604250114,"-"]
[35,"인천","직할","신부평S/S #1 M.Tr A","신부평S/S #1M.Tr 보호반 대체","신부평S/S #1M.Tr 보호반 대체","2016-06-13 09:30","2016-06-17 18:00","2016-06-13 09:30","2016-06-17 18:00","연속",null,null,null,201604140241,"-"]
[36,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S #2M.Tr 보호반 대체","신부평S/S #2M.Tr 보호반 대체","2016-06-20 09:30","2016-06-24 18:00","2016-06-20 09:30","2016-06-24 18:00","연속",null,null,null,201604140242,"-"]
[37,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S #3M.Tr 보호반 대체","신부평S/S #3M.Tr 보호반 대체","2016-06-27 09:30","2016-07-01 18:00","2016-06-27 09:30","2016-07-01 18:00","연속",null,null,null,201604140243,"-"]
[38,"경기북부","구리","신포천동두천복합#1 T/L","'2016년도 피뢰기 설치공사","피뢰기 설치기수 :22기(4회선 17기 설치, 2회선 5기 설치) 구간 : 1~22","2016-06-07 08:00","2016-06-13 18:00","2016-06-07 08:00","2016-06-13 18:00","연속",null,null,null,201603170088,"-"]
[39,"경기북부","구리","신포천포천CC#2 T/L","'2016년도 피뢰기 설치공사","공사구간 : 345kV 신포천-포천CC #2T/L No.1~13 공사내역 : 피뢰기 13기 39set 설치","2016-06-28 08:00","2016-06-30 18:00","2016-06-28 08:00","2016-06-30 18:00","연속",null,null,null,201603170094,"-"]
[40,"경기북부","구리","신가평신의정부#2 T/L","362kV 신가평신의정부 #2T/L GIS 정밀점검 공사(7572)","362kV 신가평신의정부 #2T/L GIS 정밀점검 공사(7572)","2016-06-07 09:00","2016-06-11 18:00","2016-06-07 09:00","2016-06-11 18:00","연속",null,null,null,201604180392,"-"]
[41,"경기북부","구리","신가평신의정부#1 T/L","362kV 신가평신의정부 #1T/L GIS 정밀점검 공사(7672)","362kV신가평신의정부 #1T/L GIS 정밀점검 공사(7672)","2016-06-13 09:00","2016-06-17 18:00","2016-06-13 09:00","2016-06-17 18:00","연속",null,null,null,201604180393,"-"]
[42,"경기북부","구리","신가평미금#1 T/L","362kV 신가평미금 #1T/L GIS 정밀점검 공사(7772)","362kV 신가평미금 #1T/L GIS 정밀점검 공사(7772)","2016-06-20 09:00","2016-06-23 18:00","2016-06-20 09:00","2016-06-23 18:00","연속",null,null,null,201604180394,"-"]
[43,"경기북부","구리","신가평미금#2 T/L","362kV 신가평미금 #2T/L GIS 정밀점검 공사(7872)","362kV 신가평미금 #2T/L GIS 정밀점검 공사(7872)","2016-06-27 09:00","2016-06-30 18:00","2016-06-27 09:00","2016-06-30 18:00","연속",null,null,null,201604190005,"-"]
[44,"경기북부","구리","미금S/S 345kV #1 BUS Sh.R MAIN CB (7079)","미금S/S 345kV #1 Sh.R 하자점검","345kV 분로리액터 1대 하자점검","2016-06-07 09:00","2016-06-08 18:00","2016-06-07 09:00","2016-06-08 18:00","연속",null,null,null,201604290051,"-"]
[45,"경기북부","파주","신덕은동두천복합#2 T/L","'2016년도 피뢰기 설치공사","공사구간 : 345kV 신덕은-동두천CC #2T/L No.18~76 공사내역 : 피뢰기 59기 177set 설치","2016-06-07 08:00","2016-06-27 18:00","2016-06-07 08:00","2016-06-27 18:00","연속",null,null,null,201603170090,"-"]
[46,"경기북부","파주","신파주S/S #1SVC Tr <CB>","신파주S/S 345kV SVC 점검","신파주S/S SVC 과거 누수개소 재조임(현재 양호) - 하자보수 진행 기타 사항 점검","2016-06-08 09:00","2016-06-10 18:00","2016-06-08 09:00","2016-06-10 18:00","연속",null,null,null,201604070002,"-"]
[47,"경기북부","파주","신파주신덕은#2 T/L","345kV 신파주-신덕은#2T/L 항공구 교체공사","345kV 신파주-신덕은#2T/L No.21-22 소음민원해소목적 항공장애구 교체","2016-06-24 08:00","2016-06-24 18:00","2016-06-24 08:00","2016-06-24 18:00","당일",null,null,null,201604180256,"-"]
[48,"경기북부","파주","신파주신덕은#1 T/L","345kV 신파주-신덕은#1T/L 항공구 교체공사","345kV 신파주-신덕은#1T/L No.21-22 소음민원해소목적 항공장애구 교체","2016-06-23 08:00","2016-06-23 18:00","2016-06-23 08:00","2016-06-23 18:00","당일",null,null,null,201604180257,"-"]
[49,"경기북부","파주","신파주양주#1 T/L","345kV 신파주-양주#1T/L 정밀점검","345kV 신파주-양주#1T/L No.1-9 정밀점검","2016-06-01 08:00","2016-06-03 18:00","2016-06-01 08:00","2016-06-03 18:00","연속",null,null,null,201604180259,"-"]
[50,"경기북부","파주","신파주S/S #1 M.Tr A","345kV M.Tr 3차측 GPT 교체공사","345kV M.Tr 3차측 GPT 교체공사","2016-06-13 10:00","2016-06-17 18:00","2016-06-13 10:00","2016-06-17 18:00","연속",null,null,null,201604180375,"-"]
[51,"경기북부","파주","신파주S/S #2 M.Tr A","345kV M.Tr 3차측 GPT 교체공사","345kV M.Tr 3차측 GPT 교체공사","2016-06-20 10:00","2016-06-24 18:00","2016-06-20 10:00","2016-06-24 18:00","연속",null,null,null,201604180377,"-"]
[52,"경기북부","파주","신덕은S/S #3 M.Tr A","345kV M.Tr 3차측 GPT 교체공사","345kV M.Tr 3차측 GPT 교체공사","2016-06-27 10:00","2016-06-30 18:00","2016-06-27 10:00","2016-06-30 18:00","연속",null,null,null,201604180378,"-"]
[53,"경기북부","파주","신파주S/S 345kV #76 BUS","345kV 신김포신파주 #2T/L GIS 정밀점검","2016년 파주전력지사 362kV GIS 정밀점검공사 (345kV 신김포신파주 #2T/L GIS 정밀점검)","2016-06-01 08:00","2016-06-02 18:00","2016-06-01 08:00","2016-06-02 18:00","연속",null,null,null,201604270010,"-"]
[54,"경기","군포","서서울S/S #1 M.Tr A","서서울S/S #1M.Tr 1차 GIS 보통점검 공사","서서울S/S #1M.Tr 1차 GIS 보통점검 공사","2016-06-13 09:00","2016-06-13 18:00","2016-06-13 09:00","2016-06-13 18:00","당일",null,null,null,201604110181,"-"]
[55,"경기","군포","서서울S/S #3 M.Tr A","서서울S/S #3M.Tr 1차 GIS 보통점검 공사","서서울S/S #3M.Tr 1차 GIS 보통점검 공사","2016-06-14 09:00","2016-06-14 18:00","2016-06-14 09:00","2016-06-14 18:00","당일",null,null,null,201604110182,"-"]
[56,"경기","군포","서서울S/S #4 M.Tr A","서서울S/S #4M.Tr 1차 GIS 보통점검 공사","서서울S/S #4M.Tr 1차 GIS 보통점검 공사","2016-06-15 09:00","2016-06-15 18:00","2016-06-15 09:00","2016-06-15 18:00","당일",null,null,null,201604110184,"-"]
[57,"경기","성남","신용인S/S 345kV #1 Sh.R","345kV 신용인S/S 용량부족 GIS 대체공사","345kV #1Sh.R 1차 GIS 용량대체 345kV GIS (63kA 6300A)설치 * 3CB 용량대체","2016-06-01 09:00","2016-09-08 18:00","2016-06-01 09:00","2016-09-08 18:00","연속",null,null,null,201601140111,"-"]
[58,"경기","성남","신안성신성남#1 T/L","유사고장예방 345kV 신안성-신성남#1T/L 케이블 교체공사","유사고장 예방 케이블 교체 - 케이블 5개 경간, 9개 접속함","2016-06-14 08:30","2016-07-18 18:00","2016-06-14 08:30","2016-07-18 18:00","연속",null,null,null,201604070210,"-"]
[59,"경기","성남","신성남S/S #4M.Tr A","신성남S/S #4M.Tr 2,3차 LA 초기점검,벽체도장","신성남S/S #4M.Tr 2,3차 LA 초기점검,벽체도장","2016-06-06 09:30","2016-06-08 18:00","2016-06-06 09:30","2016-06-08 18:00","연속",null,null,null,201604080205,"-"]
[60,"경기","성남","신성남S/S #3 M.Tr A","신성남S/S #3M.Tr 154kV GIS 정밀점검","신성남S/S #3M.Tr 154kV GIS 정밀점검,벽체도장","2016-06-02 09:30","2016-06-04 18:00","2016-06-02 09:30","2016-06-04 18:00","연속",null,null,null,201604080206,"-"]
[61,"경기","성남","신성남S/S #5 M.Tr A","신성남S/S #5M.Tr 154kV GIS 정밀점검","신성남S/S #5M.Tr 154kV GIS 정밀점검,벽체도장","2016-06-20 09:30","2016-06-22 18:00","2016-06-20 09:30","2016-06-22 18:00","연속",null,null,null,201604080207,"-"]
[62,"경기","성남","신성남S/S #6 M.Tr A","신성남S/S #6M.Tr 비상트립장치, 벽체도장","신성남S/S #6M.Tr 비상트립장치, 벽체도장","2016-06-09 09:30","2016-06-11 18:00","2016-06-09 09:30","2016-06-11 18:00","연속",null,null,null,201604080228,"-"]
[63,"경기","성남","신안성신용인#1 T/L","345kV 신안성-신용인#1T/L 전력선교체 및 스페이서댐퍼 정비공사","345kV 신안성-신용인#1T/L 전력선교체 및 스페이서댐퍼 정비(증설) 1. 전력선교체 : 345kV 신안성-신용인#1T/L No.54~55 3가닥 2. 스페이서댐퍼수량 일반지역에서 특수지역 조건으로 변경설치 No.38~56(10경간)","2016-06-20 08:00","2016-06-24 18:00","2016-06-20 08:00","2016-06-24 18:00","연속",null,null,null,201604100058,"-"]
[64,"경기","성남","신성남S/S #1M.Tr A","신성남S/S #1M.Tr 비상트립장치, 벽체도장","신성남S/S #1M.Tr 비상트립장치, 벽체도장","2016-06-30 09:30","2016-07-02 18:00","2016-06-30 09:30","2016-07-02 18:00","연속",null,null,null,201604120599,"-"]
[65,"경기","성남","신수원S/S #1 M.Tr A","신수원S/S 노후 전력계통반 교체공사","신수원S/S 노후 전력계통반 교체공사 ㅇ 노후전력계통반 철거 및 디지털축소형모자익 설치","2016-06-01 09:00","2016-06-03 18:00","2016-06-01 09:00","2016-06-03 18:00","연속",null,null,null,201604140105,"-"]
[66,"경기","성남","신수원S/S #2 M.Tr A","신수원S/S 노후 전력계통반 교체공사","신수원S/S 노후 전력계통반 교체공사 ㅇ 노후전력계통반 철거 및 디지털축소형모자익 설치","2016-06-07 09:00","2016-06-09 18:00","2016-06-07 09:00","2016-06-09 18:00","연속",null,null,null,201604140106,"-"]
[67,"경기","성남","신수원S/S #3 M.Tr A","신수원S/S 노후 전력계통반 교체공사","신수원S/S 노후 전력계통반 교체공사 ㅇ 노후전력계통반 철거 및 디지털축소형모자익 설치","2016-06-20 09:00","2016-06-22 18:00","2016-06-20 09:00","2016-06-22 18:00","연속",null,null,null,201604140107,"-"]
[68,"경기","성남","신수원S/S #4 M.Tr A","신수원S/S 노후 전력계통반 교체공사","신수원S/S 노후 전력계통반 교체공사 ㅇ 노후전력계통반 철거 및 디지털축소형모자익 설치","2016-06-23 09:00","2016-06-25 18:00","2016-06-23 09:00","2016-06-25 18:00","연속",null,null,null,201604140108,"-"]
[69,"경기","성남","신성남S/S #2 M.Tr A","신성남S/S #2M.Tr 154kV GIS 정밀점검","신성남S/S #2M.Tr 154kV GIS 정밀점검,벽체도장","2016-06-27 09:30","2016-06-29 18:00","2016-06-27 09:30","2016-06-29 18:00","연속",null,null,null,201604140181,"-"]
[70,"경기","직할","화성서서울#1 T/L","154kV 화성서서울#1T/L 안전이격거리확보","- 345kV 화성-평택TP#2T/L 송전선로용 피뢰기 설치 관련 안전이격거리확보(69호)","2016-06-04 13:00","2016-06-04 19:00","2016-06-04 13:00","2016-06-04 19:00","당일",null,null,null,201603140057,"-"]
[71,"강원","동해","삼척GP한울NP1#1T/L","345kV 삼척GP-한울NP1T/L 전선접속개소 전선교체공사","No.12~20 전선접속개소 전선교체","2016-06-02 07:00","2016-06-09 18:00","2016-06-02 07:00","2016-06-09 18:00","연속",null,null,null,201604170002,"-"]
[72,"충북","직할","신제천동해#2 T/L","345kV 신제천S/S GIS화 공사","신제천-동해#2T/L 인출변경 345KV 옥외철구 설비 철거","2016-06-21 09:00","2016-07-11 18:00","2016-06-21 09:00","2016-07-11 18:00","연속",null,null,null,201604070132,"-"]
[73,"충북","직할","신제천S/S 345kV #1 BUS","345kV 신제천S/S GIS화 공사","신제천-동해#2T/L 인출변경 345KV 옥외철구 설비 철거","2016-06-20 09:00","2016-06-20 18:00","2016-06-20 09:00","2016-06-20 18:00","당일",null,null,null,201604070134,"-"]
[74,"충북","직할","신제천S/S 345kV #2 BUS","345kV 신제천S/S GIS화 공사","신제천-동해#2T/L 인출변경 345KV 옥외철구 설비 철거","2016-06-21 09:00","2016-06-21 13:00","2016-06-21 09:00","2016-06-21 13:00","당일",null,null,null,201604070137,"-"]
[75,"충북","청주","청원신진천#2 T/L","새롬프로텍 성능개선","새롬프로텍 성능개선","2016-06-21 09:00","2016-06-22 18:00","2016-06-21 09:00","2016-06-22 18:00","연속",null,null,null,201604120013,"-"]
[76,"충북","충주","신진천S/S #1 M.Tr A","1,2차 차단기 보통점검","1,2차 차단기 보통점검","2016-06-13 10:00","2016-06-14 18:00","2016-06-13 10:00","2016-06-14 18:00","매일",null,null,null,201604100026,"-"]
[77,"충북","충주","신진천S/S #3 M.Tr A","1,2차 차단기 보통점검","1,2차 차단기 보통점검","2016-06-15 10:00","2016-06-16 18:00","2016-06-15 10:00","2016-06-16 18:00","매일",null,null,null,201604100027,"-"]
[78,"대전충남","서산","신당진S/S #1 M.Tr A","345kV 신당진S/S CLR 설치공사","- #1M.Tr 3차측 이설(#1->#3)","2016-06-01 09:00","2016-06-08 18:00","2016-06-01 09:00","2016-06-08 18:00","연속",null,null,null,201604100068,"-"]
[79,"대전충남","서산","신당진S/S #3 M.Tr A","345kV 신당진S/S CLR 설치공사","- #1M.Tr 3차측 이설(#1->#3)에 따른 접속","2016-06-18 09:00","2016-06-30 18:00","2016-06-18 09:00","2016-06-30 18:00","연속",null,null,null,201604100069,"-"]
[80,"대전충남","서산","태안T/P #1 M.Tr 1차 CB (7871)","태안T/P 345kV GIS 보통점검(7871)","○ 345kV #1M.Tr 1차(7871) GIS 보통점검 ○ 2차 실리콘러버 설치","2016-06-10 09:00","2016-06-10 18:00","2016-06-10 09:00","2016-06-10 18:00","당일",null,null,null,201604150006,"-"]
[81,"대전충남","서산","태안T/P 1호기 1차 CB (7172)","태안T/P 345kV GIS 초기점검(7172)","○ 345kV 1호기 1차(7172) GIS 초기점검","2016-06-02 09:00","2016-06-02 16:00","2016-06-02 09:00","2016-06-02 16:00","당일",null,null,null,201604150011,"-"]
[82,"대전충남","서산","태안T/P 8호기 1차 CB (7872)","태안T/P 345kV GIS 초기점검(7872)","○ 345kV 8호기 1차(7872) GIS 초기점검","2016-06-03 11:00","2016-06-03 18:00","2016-06-03 11:00","2016-06-03 18:00","당일",null,null,null,201604150012,"-"]
[83,"대전충남","서산","태안T/P TIE-1호기 1차CB(신) (7100)","태안T/P 345kV GIS 초기점검(7100)","○ 345kV TIE-1호기 1차(7100) GIS 초기점검","2016-06-01 09:00","2016-06-01 18:00","2016-06-01 09:00","2016-06-01 18:00","당일",null,null,null,201604150013,"-"]
[84,"대전충남","서산","태안T/P #1M.Tr-8호기 1차 CB (7800)","태안T/P 345kV GIS 초기점검(7800)","○ 345kV TIE-8호기 1차(7800) GIS 초기점검","2016-06-02 16:00","2016-06-03 11:00","2016-06-02 16:00","2016-06-03 11:00","연속",null,null,null,201604150014,"-"]
[85,"대전충남","서산","북당진현대제철T/L","345kV 북당진-현대제철 등 2개T/L 점퍼련 횡징방지 장치 설치공사","- 북당진S/S S/T 점퍼련 횡진방지 장치 3 SET 설치","2016-06-14 08:00","2016-06-14 18:00","2016-06-14 08:00","2016-06-14 18:00","당일",null,null,null,201604250030,"-"]
[86,"대전충남","서산","신당진개폐소-북당진 T/L","345kV 북당진-현대제철 등 2개T/L 점퍼련 횡징방지 장치 설치공사","- 북당진S/S S/T 점퍼련 횡진방지 장치 3 SET 설치","2016-06-15 08:00","2016-06-15 18:00","2016-06-15 08:00","2016-06-15 18:00","당일",null,null,null,201604250031,"-"]
[87,"대전충남","아산","아산화성#1 T/L","[송전] 345kV 아산-화성T/L 48호 안전이격확보공사","ㅇ 철탑교체 1기 : No.48 ㅇ 전선교체 : No.44~49 ㅇ OPGW 이설 ㅇ 기타 부대작업","2016-06-01 08:00","2016-06-12 18:00","2016-06-06 08:00","2016-06-16 18:00","연속",null,null,null,201603110001,"-"]
[88,"대전충남","아산","아산화성#2 T/L","[송전] 345kV 아산-화성T/L 48호 안전이격확보공사","ㅇ 철탑교체 1기 : No.48 ㅇ 전선교체 : No.44~49 ㅇ OPGW 이설 ㅇ 기타 부대작업","2016-06-13 08:00","2016-06-25 18:00","2016-06-17 08:00","2016-06-28 18:00","연속",null,null,null,201603110002,"-"]
[89,"대전충남","아산","신탕정S/S #3 M.Tr A","신탕정S/S 345kV #3M.Tr 및 3차 PT 하자 점검","○ 345kV #3M.Tr 및 3차 PT 하자 점검 ○ 병행) 154kV #3M.Tr 2차 6344 GIS 하자점검","2016-06-09 09:00","2016-06-09 18:00","2016-06-09 09:00","2016-06-09 18:00","당일",null,null,null,201604140182,"-"]
[90,"대전충남","청양","보령TP보령CC T/L","345kV 보령연락#1T/L 보호배전반 교체공사","○ 345kV 보령연락#1T/L 보호배전반 교체","2016-06-20 09:00","2016-06-24 18:00","2016-06-20 09:00","2016-06-24 18:00","연속",null,null,null,201604130090,"-"]
[91,"대전충남","청양","청양S/S #2 M.Tr A","청양S/S #62M.Tr 1차 GIS 교체공사","○ 154kV #62M.Tr 1차 GIS 교체 안전이격","2016-06-13 09:00","2016-06-17 18:00","2016-06-13 09:00","2016-06-17 18:00","매일",null,null,null,201604140129,"-"]
[92,"대전충남","청양","청양S/S #2 M.Tr A","청양S/S #62M.Tr 1차 GIS 교체공사","○ 154kV #62M.Tr 1차 GIS 교체 안전이격","2016-06-20 08:00","2016-06-24 18:00","2016-06-20 08:00","2016-06-24 18:00","매일",null,null,null,201604150243,"-"]
[93,"전북","군산","군산신김제#2 T/L","345kV 군산S/S 군산-신김제#2T/L","군산P/O 345kV 차단기 정밀점검공사 군산-신김제#2T/L(7171), 군산-신김제#1T/L-TIE(7100) CB 차단기 정밀점검","2016-06-07 09:00","2016-06-17 18:00","2016-06-07 09:00","2016-06-17 18:00","연속",null,null,null,201602120050,"-"]
[94,"전북","군산","군산S/S 345kV #1 BUS","군산S/S 345kV #1BUS","군산P/O 노후배전반 대체공사","2016-06-03 09:00","2016-06-03 13:00","2016-06-02 14:00","2016-06-02 16:00","당일",null,null,null,201604150052,"-"]
[95,"전북","군산","군산S/S 345kV #2 BUS","군산S/S 345kV #2BUS","군산P/O 노후배전반 대체공사","2016-06-03 13:00","2016-06-03 18:00","2016-06-10 14:00","2016-06-10 16:00","당일",null,null,null,201604150054,"-"]
[96,"전북","김제","신김제S/S #1 M.Tr A","신김제S/S #1 M.Tr A","71Bay B/F 보호반 교체, 7100 CB 정밀점검","2016-06-07 09:00","2016-06-10 18:00","2016-06-07 09:00","2016-06-10 18:00","연속",null,null,null,201604180396,"-"]
[97,"전북","직할","신남원의령#2 T/L","345kV 신남원-의령 #2T/L 안전이격거리 확보공사","1.철탑교체 (No.163~164) 2.전력선교체(No.160~164, 164~179)","2016-06-10 08:00","2016-06-17 18:00","2016-06-08 08:00","2016-06-19 18:00","연속",null,null,null,201603160174,"-"]
[98,"전북","직할","신옥천신남원#1 T/L","신남원S/S 345kV 신옥천-신남원#1T/L GIS 정밀분석점검","신남원S/S 345kV 신옥천-신남원#1T/L GIS 정밀분석점검","2016-06-21 09:30","2016-07-10 18:00","2016-06-30 09:30","2016-07-19 18:00","연속",null,null,null,201604180217,"-"]
[99,"전북","직할","신남원S/S 345kV #1 BUS","신남원S/S 345kV #1BUS 휴전","신남원S/S 345kV 신옥천-신남원#1T/L GIS 정밀분석점검관련 병행휴전","2016-06-21 09:30","2016-07-10 18:00","2016-06-30 09:30","2016-07-19 18:00","연속",null,null,null,201604180219,"-"]
[100,"광주전남","광주","신광주S/S #1 M.Tr A","신광주S/S #1 M.Tr (취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-27 07:30","2016-06-27 18:00","2016-06-14 07:30","2016-06-14 18:00","연속",null,null,null,201604010117,"-"]
[101,"광주전남","광주","신광주S/S #2 M.Tr A","신광주S/S #2 M.Tr (취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-28 07:30","2016-06-28 18:00","2016-06-15 07:30","2016-06-15 18:00","연속",null,null,null,201604010118,"-"]
[102,"광주전남","광주","신광주S/S #3 M.Tr A","신광주S/S #3M.Tr (취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-29 07:30","2016-06-30 18:00","2016-06-16 07:30","2016-06-16 18:00","연속",null,null,null,201604010119,"-"]
[103,"광주전남","광주","신광주S/S #4 M.Tr A","신광주S/S #4M.Tr (취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-30 07:30","2016-07-01 18:00","2016-06-17 07:30","2016-06-17 18:00","연속",null,null,null,201604010120,"-"]
[104,"광주전남","광주","신광주신화순#1 T/L","345kV 신광주-신화순T/L 지상고확보 및 전선교체","지상고확보 2기 (6,7호) 전선교체 4경간 (11-14호)","2016-06-18 07:00","2016-06-24 18:00","2016-06-18 07:00","2016-06-24 18:00","연속",null,null,null,201604060124,"-"]
[105,"광주전남","광주","신광주신화순#2 T/L","345kV 신광주-신화순T/L 지상고확보 및 전선교체","지상고확보 2기 (6,7호) 전선교체 4경간 (11-14호)","2016-06-25 07:00","2016-06-29 18:00","2016-06-25 07:00","2016-06-29 18:00","연속",null,null,null,201604060125,"-"]
[106,"광주전남","목포","한빛1NP-한빛2NP #2T/L","16년 변전협력회사 총액공사","한빛연락#2T/L GIS 점검","2016-06-01 09:00","2016-06-13 18:00","2016-06-01 09:00","2016-06-13 18:00","연속",null,null,null,201603240065,"-"]
[107,"광주전남","순천","신남원광양#1 T/L","345kV 신남원-광양#1T/L(가공송전선로 순시점검 위탁공사)","345kV 신남원-광양#1T/L 정밀점검 - 점검구간 : 1 ~ 125호(64기)","2016-06-13 09:00","2016-06-16 18:00","2016-06-20 09:00","2016-06-23 18:00","매일",null,null,null,201604110352,"-"]
[108,"광주전남","순천","신남원광양#2 T/L","345kV 신남원-광양#2T/L(가공송전선로 순시점검 위탁공사)","345kV 신남원-광양#2T/L 정밀점검 - 점검구간 : 1 ~ 125호(64기)","2016-06-20 09:00","2016-06-23 18:00","2016-06-27 09:00","2016-06-30 18:00","매일",null,null,null,201604110354,"-"]
[109,"광주전남","순천","광양S/S #2 M.Tr A","345kV 광양S/S #2M.Tr(2차 GIS 보통점검)","2016년 순천전력지사 변전협력회사 총액공사 - GIS 보통점검","2016-06-14 10:00","2016-06-14 18:00","2016-06-02 10:00","2016-06-02 18:00","당일",null,null,null,201604120510,"-"]
[110,"광주전남","순천","광양S/S #3 M.Tr A","345kV 광양S/S #3M.Tr(2차 GIS 보통점검)","2016년 순천전력지사 변전협력회사 총액공사 - GIS 보통점검","2016-06-21 10:00","2016-06-21 18:00","2016-06-09 10:00","2016-06-09 18:00","당일",null,null,null,201604120511,"-"]
[111,"광주전남","강진","신강진광양#1 T/L","345kV 신강진-광양#1T/L(신강진 7300, 7372 CB점검)","2016~17년도 강진전력지사 변전협력회사 총액공사 - 6. 7 : 신강진S/S 7300, 7372 CB 보통점검","2016-06-07 09:00","2016-06-08 18:00","2016-06-07 09:00","2016-06-08 18:00","연속",null,null,null,201604290095,"-"]
[112,"광주전남","강진","신강진광양#2 T/L","345kV 신강진-광양#2T/L(신강진 7400, 7471 CB점검)","2016~17년도 강진전력지사 변전협력회사 총액공사 - 6. 9 ~ 6. 10 : 신강진S/S 7400, 7471 CB 보통점검","2016-06-09 09:00","2016-06-10 18:00","2016-06-09 09:00","2016-06-10 18:00","연속",null,null,null,201604290094,"-"]
[113,"대구경북","경산","신경산대구#1 T/L","154kV 경산-자인#2T/L 정밀점검 관련 안전이격","154kV 경산-자인#2T/L 정밀점검 30기 관련 안전이격","2016-06-07 08:00","2016-06-10 18:00","2016-06-07 08:00","2016-06-07 18:00","연속",null,null,null,201604070027,"-"]
[114,"대구경북","경산","신경산S/S #4 M.Tr A","신경산S/S 345kV #4M.Tr 및 관련설비 보통점검","주변압기, 7600, 7672 CB 및 6444 GIS 보통점검, 1차 LA(하자점검) 3차 LA, 3차 GPT 보통점검, #2S.Tr 및 4289 VCB 보통점검","2016-06-02 09:00","2016-06-03 18:00","2016-06-02 09:00","2016-06-03 18:00","연속",null,null,null,201604090092,"-"]
[115,"대구경북","영주","한울3N/P 345kV #2 BUS","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2016-06-21 09:00","2016-06-23 18:00","2016-06-21 09:00","2016-06-23 18:00","연속",null,null,null,201602110012,"-"]
[116,"대구경북","영주","한울3N/P 345kV #1 BUS","한울 3발 362kV 용량부족 GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2016-06-29 09:00","2016-07-01 18:00","2016-06-29 09:00","2016-07-01 18:00","매일",null,null,null,201602110013,"-"]
[117,"대구경북","영주","신영주S/S #1 M.Tr A","#1M.Tr 정밀점검, 6144 CB 초기점검, 4179CB 점검 등","#1M.Tr 정밀점검, 6144 CB 초기점검, 4179, 4189 CB 보통점검, 6141, 6142 DS 보통점검, 3차 PT 보통점검, 2,3차 LA 보통점검, #1S.Tr 보통점검","2016-06-07 09:00","2016-06-13 18:00","2016-06-07 09:00","2016-06-13 18:00","연속",null,null,null,201604110378,"-"]
[118,"대구경북","영주","한울1NP-한울2NP #1T/L","한울1발 S/Y 72BAY 감시제어회로 이설 및 추가","한울2발 통합감시시스템 구성관련 1발 S/Y 72BAY 감시제어회로 이설 및 추가설치","2016-06-04 09:00","2016-06-06 18:00","2016-06-02 09:00","2016-06-04 18:00","연속",null,null,null,201604110379,"-"]
[119,"대구경북","영주","신영주예천PP#1 T/L","신영주S/S 362kV GIS화 공사","○ 부하전환(옥외철구 → GIS) - 보호반 이설, 송전선로 인출 리드 연장, 옥외철구설비 철거","2016-06-01 08:00","2016-06-11 18:00","2016-06-01 08:00","2016-06-11 18:00","연속",null,null,null,201604150050,"-"]
[120,"대구경북","영주","신영주예천PP#2 T/L","신영주S/S 362kV GIS화 공사","○ 부하전환(옥외철구 → GIS) - 보호반 이설, 송전선로 인출 리드 연장, 옥외철구설비 철거","2016-06-12 08:00","2016-06-22 18:00","2016-06-12 08:00","2016-06-22 18:00","연속",null,null,null,201604150051,"-"]
[121,"대구경북","영주","신영주안동CC T/L","신영주S/S 362kV GIS화 공사","○ 부하전환(옥외철구 → GIS) - 보호반 이설, 송전선로 인출 리드 연장, 옥외철구설비 철거","2016-06-23 08:00","2016-07-03 18:00","취소","취소","연속",null,null,null,201604150053,"-"]
[122,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","○ 송전선로 및 가공지선 신규 설치를 위한 안전이격 확보","2016-06-03 08:00","2016-06-07 18:00","2016-06-03 08:00","2016-06-07 18:00","연속",null,null,null,201604150055,"-"]
[123,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","○ 송전선로 및 가공지선 신규 설치를 위한 안전이격 확보","2016-06-14 08:00","2016-06-18 18:00","2016-06-14 08:00","2016-06-18 18:00","연속",null,null,null,201604150056,"-"]
[124,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","○ 송전선로 및 가공지선 신규 설치를 위한 안전이격 확보","2016-06-25 08:00","2016-06-29 18:00","2016-06-25 08:00","2016-06-29 18:00","연속",null,null,null,201604150057,"-"]
[125,"대구경북","영주","신영주S/S #2 M.Tr A","신영주S/S 362kV GIS화 공사","○ 부하전환(옥외철구 → GIS) - 보호반 이설, 송전선로 인출 리드 연장, 옥외철구설비 철거","2016-06-23 08:00","2016-07-03 18:00","2016-06-23 08:00","2016-07-03 18:00","연속",null,null,null,201604150058,"-"]
[126,"대구경북","영주","신영주S/S 345kV #1 BUS","신영주S/S 362kV GIS화 공사","○ 송전선로 및 가공지선 신규 설치를 위한 안전이격 확보","2016-06-08 09:00","2016-06-11 18:00","2016-06-08 09:00","2016-06-11 18:00","연속",null,null,null,201604150059,"-"]
[127,"대구경북","칠곡","서대구S/S #4 M.Tr A","6444 GCB 초기점검","6444 GCB 초기점검","2016-06-07 09:30","2016-06-07 18:00","2016-06-07 09:30","2016-06-07 18:00","당일",null,null,null,201604080094,"-"]
[128,"대구경북","칠곡","서대구S/S 345kV #1 BUS","LA,PT 보통점검","LA,PT 보통점검","2016-06-15 09:30","2016-06-15 18:00","2016-06-15 09:30","2016-06-15 18:00","당일",null,null,null,201604080097,"-"]
[129,"대구경북","칠곡","북경남서대구#1 T/L","PT교체","PT교체","2016-06-27 09:30","2016-06-28 18:00","2016-06-27 09:30","2016-06-28 18:00","연속",null,null,null,201604080102,"-"]
[130,"대구경북","칠곡","신포항북대구 T/L","북대구S/S 362kV #1BUS GIS 정밀점검 Test 선로","북대구S/S 362kV #1BUS GIS 정밀점검 Test 선로","2016-06-08 14:00","2016-06-08 18:00","2016-06-01 14:00","2016-06-03 18:00","매일",null,null,null,201604080105,"-"]
[131,"대구경북","칠곡","북대구S/S 345kV #1 BUS","GIS 정밀점검, UHF 센서설치","GIS 정밀점검, UHF 센서설치","2016-06-07 09:30","2016-06-08 18:00","취소","취소","연속",null,null,null,201604080107,"-"]
[132,"대구경북","칠곡","북대구S/S 345kV #2 BUS","GIS 정밀점검, UHF 센서설치","GIS 정밀점검, UHF 센서설치","2016-06-09 09:30","2016-06-10 18:00","취소","취소","연속",null,null,null,201604080108,"-"]
[133,"대구경북","칠곡","북경남서대구#2 T/L","345kV 북경남-서대구#2T/L 피뢰기 설치공사","345kV 북경남-서대구#2T/L 피뢰기 설치 - 공사구간 : 1~113호 - 피뢰기설치 : 113기","2016-06-02 09:00","2016-06-21 18:00","2016-06-02 09:00","2016-06-21 18:00","연속",null,null,null,201604110082,"-"]
[134,"대구경북","포항","신포항신월성NP#3 T/L","345kV 신포항-신월성NP#3,4 전력선교체공사","345kV 신포항-신월성NP#3,4 T/L 전력선 교체 No.59~71호 ACSR 480㎟*4B*2C 2.743km","2016-06-08 08:00","2016-06-17 18:00","2016-06-21 08:00","2016-06-30 18:00","연속",null,null,null,201604110050,"-"]
[135,"대구경북","포항","신포항신월성NP#4 T/L","345kV 신포항-신월성NP#3,4 전력선교체공사","345kV 신포항-신월성NP#3,4 T/L 전력선 교체 No.59~71호 ACSR 480㎟*4B*2C 2.743km","2016-06-18 08:00","2016-06-29 18:00","2016-06-09 08:00","2016-06-20 18:00","연속",null,null,null,201604110052,"-"]
[136,"대구경북","포항","신영일안동CC T/L","345kV 영포T/L 전선접속개소 제거공사","영포T/L No.210~253, 259~267 전선교체 : ACSR 480㎟(R) × 4B × 2C, 38.35C-km 가공지선교체 : ACSR120㎟ × S ×1C, 19.2C-km","2016-06-04 09:00","2016-06-17 18:00","2016-06-04 09:00","2016-06-17 18:00","연속",null,null,null,201604110183,"-"]
[137,"부산울산","동부산","신울산고리NP#1 T/L","345kV 신울산-고리NP T/L 9~12호 지장철탑이설공사","○ 장안-온산1 국도건설공사에 지장이 되는 송전철탑 이설공사 ○ 이설철탑 : 본철탑 10호 및 가철탑 11호 설치(가선로 구성) ○ 9, 12호 애자장치 보강","2016-06-26 09:00","2016-07-05 18:00","2016-06-26 09:00","2016-07-05 18:00","연속",null,null,null,201604120251,"○"]
[138,"부산울산","동부산","신울산고리NP#2 T/L","345kV 신울산-고리NP T/L 9~12호 지장철탑이설공사","○ 장안-온산1 국도건설공사에 지장이 되는 송전철탑의 이설공사 ○ 이설철탑 : 본철탑 10호 및 가철탑 11호 설치(가선로 구성) ○ 9, 12호 애자장치 보강","2016-06-26 09:00","2016-07-05 18:00","2016-06-26 09:00","2016-07-05 18:00","연속",null,null,null,201604120260,"-"]
[139,"부산울산","동부산","울주고리NP#2 T/L","345kV 울주-고리NP #2T/L 전선접속개소 전선교체공사","전선접속개소 해소, 30~68호, 9.406km","2016-06-09 08:00","2016-06-25 18:00","2016-06-09 08:00","2016-06-25 18:00","연속",null,null,null,201604150172,"-"]
[140,"부산울산","동부산","신양산S/S #3 M.Tr A","신양산S/S 소내변압기 보호회로 보완","신양산S/S 소내변압기 보호회로 보완(#3M.Tr)","2016-06-02 09:30","2016-06-02 17:00","2016-06-02 09:30","2016-06-02 17:00","당일",null,null,null,201604180244,"-"]
[141,"부산울산","동부산","신양산S/S #4 M.Tr A","신양산S/S 소내변압기 보호회로 보완","신양산S/S 소내변압기 보호회로 보완(#4M.Tr)","2016-06-03 09:30","2016-06-03 17:00","2016-06-03 09:30","2016-06-03 17:00","당일",null,null,null,201604180246,"-"]
[142,"부산울산","북부산","서부산북부산#3 T/L","2016년 북부산변전협력회사 총액공사","7871CB Air 게이지 교체","2016-06-11 09:00","2016-06-11 18:00","2016-06-11 09:00","2016-06-11 18:00","당일",null,null,null,201604120362,"-"]
[143,"부산울산","북부산","북부산S/S #4 M.Tr A","북부산S/S 154kV 취약설비 GIS화공사","T-BUS 및 6448DS 철거","2016-06-25 09:00","2016-06-26 18:00","2016-06-25 09:00","2016-06-26 18:00","연속",null,null,null,201604120368,"-"]
[144,"부산울산","북부산","북부산S/S #1 M.Tr A","북부산S/S 154kV 취약설비 GIS화공사","T-BUS 및 6148DS 철거","2016-06-27 09:00","2016-06-28 18:00","2016-06-27 09:00","2016-06-28 18:00","연속",null,null,null,201604120380,"-"]
[145,"부산울산","북부산","북부산S/S #2 M.Tr A","북부산S/S 154kV 취약설비 GIS화공사","T-BUS 및 6248DS 철거","2016-06-29 09:00","2016-06-30 18:00","2016-06-29 09:00","2016-06-30 18:00","연속",null,null,null,201604120416,"-"]
[146,"부산울산","서부산","서부산S/S #2 M.Tr A","서부산S/S #2M.Tr 정밀점검","서부산S/S #2M.Tr 정밀점검","2016-06-13 10:00","2016-06-24 18:00","2016-06-13 10:00","2016-06-24 18:00","연속",null,null,null,201604110227,"-"]
[147,"부산울산","서부산","서부산S/S #1 M.Tr A","서부산S/S #1M.Tr 정밀점검","서부산S/S #1M.Tr 정밀점검 [병행작업]#1M.Tr PNL 대체(전성식)","2016-06-27 10:00","2016-07-08 18:00","2016-06-27 10:00","2016-07-08 18:00","연속",null,null,null,201604110228,"-"]
[148,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S #71Bay B/F PNL 대체공사","서부산S/S #71Bay B/F PNL 대체공사 (7171, 7100, 7172 휴전)","2016-06-20 09:00","2016-06-24 18:00","2016-06-20 09:00","2016-06-24 18:00","연속",null,null,null,201604110237,"-"]
[149,"부산울산","울산","신온산울산TP T/L","345kV 북부산-울산TP 등 4개T/L 전선교체공사","회선명 : 345kV 신온산-울산TP T/L 작업내용: 전선교체공사 구간 : No.8~No.09(상단 1가닥)","2016-06-07 08:00","2016-06-08 18:00","2016-06-07 08:00","2016-06-08 18:00","연속",null,null,null,201604070001,"-"]
[150,"부산울산","울산","북부산신울산#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 북부산-신울산#1 T/L 측 345kV 모선 교체","2016-06-27 09:00","2016-06-28 18:00","2016-06-27 09:00","2016-06-28 18:00","연속",null,null,null,201604130071,"-"]
[151,"부산울산","울산","신울산S/S 345kV #70BUS","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 345kV #70BUS 모선보호반, 모선 CPD, 모선 교체","2016-06-13 09:00","2016-06-17 18:00","2016-06-13 09:00","2016-06-17 18:00","연속",null,null,null,201604130072,"-"]
[152,"부산울산","울산","동울산S/S 동울산-월성NP#1T/L CB (7171)","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S 7171 GIS 하자점검","2016-06-15 09:00","2016-06-15 18:00","2016-06-15 09:00","2016-06-15 18:00","당일",null,null,null,201604130108,"○"]
[153,"부산울산","울산","동울산S/S TIE-#1M.Tr 1차 CB (7100)","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S 7100 GIS 하자점검","2016-06-16 09:00","2016-06-16 18:00","2016-06-16 09:00","2016-06-16 18:00","당일",null,null,null,201604130109,"-"]
[154,"부산울산","울산","동울산S/S TIE-#2M.Tr 1차 CB (7200)","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S 7200 GIS 하자점검","2016-06-23 09:00","2016-06-23 18:00","2016-06-23 09:00","2016-06-23 18:00","당일",null,null,null,201604130112,"-"]
[155,"부산울산","울산","동울산S/S 동울산-월성NP#2T/L CB (7271)","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S 7271 GIS 하자점검","2016-06-22 09:00","2016-06-22 18:00","2016-06-22 09:00","2016-06-22 18:00","당일",null,null,null,201604130115,"-"]
[156,"부산울산","울산","신울산S/S #2 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S #2M.Tr 1차측 345kV 모선 교체","2016-06-29 09:00","2016-06-29 18:00","2016-06-29 09:00","2016-06-29 18:00","연속",null,null,null,201604130131,"-"]
[157,"부산울산","울산","신울산S/S 345kV #75BUS","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 345kV #75BUS 모선보호반, 모선 CPD, 모선 교체","2016-06-20 09:00","2016-06-24 18:00","2016-06-20 09:00","2016-06-24 18:00","연속",null,null,null,201604140022,"○"]
[158,"경남","직할","신김해북부산#2 T/L","안전이격확보(154kV 신김해-주촌#1T/L 피뢰기 설치관련)","신김해-주촌#1T/L 피뢰기 설치(1~18호, 18기)관련 안전이격확보","2016-06-06 08:00","2016-06-06 12:00","2016-06-06 08:00","2016-06-06 12:00","당일",null,null,null,201604150440,"-"]
[159,"경남","통영","신고성S/S #2 M.Tr A","신고성S/S 7B, 7D Bay B/F 보호반 대체 등","- 신고성S/S 7B, 7D Bay B/F 보호반 대체 - 신고성-삼천포화력#2T/L 보호반 대체 - 기타 #2M.Tr 휴전작업(1차 LA초기, 2차 LA하자, 3차 작업등)","2016-06-01 09:30","2016-06-02 18:30","2016-06-01 09:30","2016-06-02 18:30","연속",null,null,null,201604110004,"-"]
[160,"경남","통영","삼천포T/P 신마산#1T/L-#3 M.Tr 1차 CB (7300)","삼천포T/P 신마산#1T/L-#3M.Tr 1차 CB(7300) 정밀점검","삼천포T/P 345kV 7300 CB 정밀점검","2016-06-16 09:30","2016-06-18 18:30","2016-06-16 09:30","2016-06-18 18:30","연속",null,null,null,201604110011,"-"]
[161,"경남","통영","신고성S/S 345kV #1 BUS","신고성S/S 345kV #1BUS-PRO PNL 대체","신고성S/S 345kV #1BUS-PRO PNL 대체","2016-06-04 09:30","2016-06-06 18:30","2016-06-04 09:30","2016-06-06 18:30","연속",null,null,null,201604110012,"-"]
[162,"경남","통영","신고성S/S 345kV #2 BUS","신고성S/S 345kV #2BUS-PRO PNL 대체","신고성S/S 345kV #2BUS-PRO PNL 대체","2016-06-10 09:30","2016-06-12 18:30","2016-06-10 09:30","2016-06-12 18:30","연속",null,null,null,201604110013,"-"]
[163,"경남","통영","삼천포T/P #3 M.Tr 1차 CB (7371)","삼천포T/P #3M.Tr 1차 CB(7371) 정밀점검","삼천포T/P 345kV 7371 CB 정밀점검","2016-06-13 09:30","2016-06-15 18:30","2016-06-13 09:30","2016-06-15 18:30","연속",null,null,null,201604110014,"-"]
[164,"경남","통영","삼천포T/P 신김해#2T/L-#6 M.Tr 1차 CB (7600)","삼천포T/P 7600CB 기계적접점 교체","7600 CB 기계적접점 교체작업","2016-06-01 09:30","2016-06-01 18:00","2016-06-01 09:30","2016-06-01 18:00","당일",null,null,null,201604220075,"-"]
[165,"경남","함안","신옥천북경남 T/L","345kV 신옥천-북경남T/L 피뢰기 설치공사","345kV 신옥천-북경남T/L 피뢰기 설치공사 - 공사구간 : 신옥천-북경남T/L 1~113호(북경남2분기) - 피뢰기설치 : 113기","2016-06-02 09:00","2016-06-21 18:00","2016-06-02 09:00","2016-06-21 18:00","연속",null,null,null,201604110096,"-"]
["추가1","대구경북",null,"신영주청송PPT/L","신영주S/S 362kV GIS화 공사","○ 송전선로 및 가공지선 신규 설치를 위한 안전이격 확보","2016-06-23 08:00","2016-07-03 18:00","2016-06-23 08:00","2016-07-03 18:00","연속"]
["추가2","대구경북",null,"신영주S/S #2BUS","신영주S/S 362kV GIS화 공사","○ 송전선로 및 가공지선 신규 설치를 위한 안전이격 확보","2016-06-25 08:00","2016-06-29 18:00","2016-06-25 08:00","2016-06-29 18:00","연속"]

{"sheet":"154송부","index":2,"n_rows":357,"n_cols":16,"rows_kept":357,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
[{"$f":"'765송부'!A1","v":"2016년도 6월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","군자화양#1 T/L","화양 및 세종로S/S 인출선로 선종교체공사","1. 사 업 명 : 화양 및 세종로S/S 인출선로 선종교체공사 2. 사업목적 : 지하복합변전소 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 화양S/S ∼ 인출전력구, 세종로S/S ∼ 인출전력구 ○ 사업내용 : 154kV 6회선 0.6km 선종교체","2016-06-28 09:00","2016-07-27 18:00","2016-06-28 09:00","2016-07-27 18:00","연속",null,null,null,201604140053,"-"]
[2,"서울","성동","신내중계#1 T/L","154㎸ 중계상봉T/L 직결공사","중계S/S 방사상망 해소를 위한 계통보강공사","2016-06-01 09:00","2016-06-30 18:00","2016-06-01 09:00","2016-06-30 18:00","연속",null,null,null,201604180317,"-"]
[3,"서울","성동","신내상봉#2 T/L","154㎸ 중계상봉T/L 직결공사","중계S/S 방사상망 해소를 위한 계통보강공사","2016-06-01 09:00","2016-06-30 18:00","2016-06-01 09:00","2016-06-30 18:00","연속",null,null,null,201604180320,"-"]
[4,"서울","성동","양주쌍문#2 T/L","16년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검 (쌍문S/S 양주쌍문#2T/L)","2016-06-16 08:00","2016-06-17 20:00","2016-06-16 08:00","2016-06-17 20:00","연속",null,null,null,201604190154,"-"]
[5,"서울","성동","양주쌍문#1 T/L","154kV 양주쌍문#1T/L 종단접속함 자기애관 실측","종단접속함 자기애관 교체공사전 실측","2016-06-23 09:00","2016-06-23 18:00","2016-06-23 09:00","2016-06-23 18:00","당일",null,null,null,201604190192,"○"]
[6,"서울","직할","서소문S/S 154kV #2 BUS","서소문S/S 170kV GIS 대체공사_3차","서소문S/S 170kV GIS 대체공사 (#2M.Tr 1차 GIS, 아현서소문T/L GIS)","2016-06-02 10:00","2016-06-13 10:00","2016-05-30 10:00","2016-06-10 10:00","연속",null,null,null,201604150195,"-"]
[7,"서울","직할","서소문S/S 154kV #2 BUS","서소문S/S 170kV GIS 대체공사_4차","서소문S/S 170kV GIS 대체공사 (서소문서대문#1T/L, 154kV PT, 순화서소문#1T/L)","2016-06-13 10:00","2016-06-15 09:00","2016-06-10 10:00","2016-06-11 10:00","연속",null,null,null,201604150197,"-"]
[8,"서울","직할","서소문S/S 154kV #1 BUS","서소문S/S 170kV GIS 대체공사_4차","서소문S/S 170kV GIS 대체공사 (서소문서대문#2 T/L, 154kV PT, 순화서소문#1T/L GIS)","2016-06-15 09:00","2016-06-23 09:00","2016-06-11 10:00","2016-06-18 10:00","연속",null,null,null,201604150198,"-"]
[9,"서울","직할","서소문S/S 154kV #2 BUS","서소문S/S 170kV GIS 대체공사_4차","서소문S/S 170kV GIS 대체공사 (서소문서대문#2T/L, 154kV PT, 순화서소문#1T/L)","2016-06-23 09:00","2016-07-04 09:00","2016-06-18 10:00","2016-06-30 10:00","연속",null,null,null,201604150199,"-"]
[10,"서울","직할","서소문서대문#2 T/L","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (서소문서대문#2T/L, 154kV PT, 순화서소문#1T/L GIS)","2016-06-13 10:00","2016-07-04 09:00","2016-06-10 10:00","2016-06-30 10:00","연속",null,null,"신뢰도개선",201604150202,"-"]
[11,"서울","직할","순화서소문#1 T/L","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (서소문서대문#2T/L, 154kV PT, 순화서소문#1T/L GIS)","2016-06-13 10:00","2016-07-04 09:00","2016-06-10 10:00","2016-06-30 10:00","연속",null,null,null,201604150203,"-"]
[12,"서울","직할","운니S/S 154kV #1 BUS","2016년 직할변전소 170kV GIS 정밀점검","운니S/S 6100 B/T GIS 정밀점검","2016-06-01 10:00","2016-06-02 11:00","2016-06-01 10:00","2016-06-02 11:00","연속",null,null,null,201604210037,"-"]
[13,"서울","직할","운니S/S 154kV #2 BUS","2016년 직할변전소 170kV GIS 정밀점검","운니S/S 운니원남#2T/L GIS 정밀점검","2016-06-02 11:00","2016-06-03 18:00","2016-06-02 11:00","2016-06-03 18:00","연속",null,null,null,201604210038,"-"]
[14,"남서울","강남","신사S/S 154kV #2 BUS","신사S/S 170kV GIS 정밀점검 - 변전전문회사","신사S/S 170kV GIS 정밀점검 - 변전전문회사 -6333 GIS 정밀점검, #3M.Tr 본체 및 4344 GIS 보통점검, 계전기 시험","2016-06-06 10:00","2016-06-07 10:00","2016-06-06 10:00","2016-06-07 10:00","연속",null,null,null,201604130148,"-"]
[15,"남서울","강남","신사S/S 154kV #1 BUS","신사S/S 170kV GIS 정밀점검 - 변전전문회사","신사S/S 170kV GIS 정밀점검 - 변전전문회사 -6333 GIS 정밀점검, #3M.Tr 본체 및 4344 GIS 보통점검, 계전기 시험","2016-06-07 10:00","2016-06-08 18:00","2016-06-07 10:00","2016-06-08 18:00","연속",null,null,null,201604130149,"-"]
[16,"남서울","강남","신사S/S 154kV #1 BUS","신사S/S 170kV GIS 정밀점검 - 변전전문회사","신사S/S 170kV GIS 정밀점검 - 변전전문회사 -6433 GIS 정밀점검, #4M.Tr 본체 및 4444 GIS 보통점검, 계전기 시험","2016-06-10 10:00","2016-06-11 18:00","2016-06-10 10:00","2016-06-11 18:00","연속",null,null,null,201604130150,"-"]
[17,"남서울","강남","신사S/S 154kV #2 BUS","신사S/S 170kV GIS 정밀점검 - 변전전문회사","신사S/S 170kV GIS 정밀점검 - 변전전문회사 -6433 GIS 정밀점검, #4M.Tr 본체 및 4444 GIS 보통점검, 계전기 시험","2016-06-09 10:00","2016-06-10 10:00","2016-06-09 10:00","2016-06-10 10:00","연속",null,null,null,201604130151,"-"]
[18,"남서울","동서울","강동천호#1 T/L","154kV 강동-천호#1T/L 천호S/S측 인출구간 선종교체공사","천호S/S 강동-천호#1T/L EBG ~ 신설T/J 구간 OF케이블 -> XLPE케이블 교체","2016-06-01 09:30","2016-07-31 18:00","2016-06-01 09:30","2016-07-31 18:00","연속",null,null,null,201604120401,"-"]
[19,"남서울","동서울","가락수서#1 T/L","154kV 가락-수서#1T/L 가락S/S측 인출구간 선종교체공사","가락S/S 가락-수서#1T/L EBG ~ J/B#6구간 OF케이블 -> XLPE케이블 교체","2016-06-01 09:30","2016-06-30 18:00","2016-06-01 09:30","2016-06-30 18:00","연속",null,null,null,201604120417,"-"]
[20,"남서울","동서울","상일하남열병합#1 T/L","상일S/S 170kV GIS 초기점검","상일S/S 170kV GIS 초기점검","2016-06-12 09:00","2016-06-12 16:00","2016-06-12 09:00","2016-06-12 16:00","당일",null,null,null,201604150389,"-"]
[21,"남서울","동서울","상일하남열병합#2 T/L","상일S/S 170kV GIS 초기점검","상일S/S 170kV GIS 초기점검","2016-06-19 09:00","2016-06-19 16:00","2016-06-19 09:00","2016-06-19 16:00","당일",null,null,null,201604150390,"-"]
[22,"남서울","동서울","잠실삼성#1 T/L","154kV 삼성#2S/S 건설관련 삼성#2-잠실 분기구 시공","154kV 삼성#2-잠실 분기구 시공을 위한 기존 154kV 잠실-삼성T/L 접속맨홀 매달기 작업","2016-06-01 09:00","2016-06-30 18:00","2016-06-01 09:00","2016-06-30 18:00","연속",null,null,null,201604210125,"-"]
[23,"남서울","동서울","잠실삼성#2 T/L","154kV 삼성#2S/S 건설관련 삼성#2-잠실 분기구 시공","154kV 삼성#2-잠실 분기구 시공을 위한 기존 154kV 잠실-삼성T/L 접속맨홀 매달기 작업","2016-06-01 09:00","2016-06-30 18:00","2016-06-01 09:00","2016-06-30 18:00","연속",null,null,null,201604210129,"-"]
[24,"남서울","영서","화곡S/S 154kV #2 BUS","영서P/O 170kV GIS 정밀점검(공항#1T/L)","- 공항#1T/L GIS 정밀점검","2016-06-01 09:00","2016-06-02 13:00","2016-06-01 09:00","2016-06-02 13:00","연속",null,null,null,201604070176,"-"]
[25,"남서울","영서","화곡S/S 154kV #1 BUS","영서P/O 170kV GIS 정밀점검(공항#1T/L)","- 공항#1T/L GIS 정밀점검","2016-06-02 09:00","2016-06-03 13:00","2016-06-02 09:00","2016-06-03 13:00","연속",null,null,null,201604070178,"-"]
[26,"인천","김포","경서S/S 154kV #2 BUS","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(2차) - 154kV #2M.Tr 1차 GIS 1CCT","2016-06-30 08:00","2016-06-30 18:00","2016-06-30 08:00","2016-06-30 18:00","연속",null,null,null,201604150016,"-"]
[27,"인천","김포","계양김포#1 T/L","스페이서 간격조정 공사(가공송전정비 협력회사 총액공사)","전력선 스페이서 간격조정","2016-06-04 08:00","2016-06-05 18:00","2016-06-04 08:00","2016-06-05 18:00","매일",null,null,null,201604190147,"-"]
[28,"인천","김포","계양김포#2 T/L","피뢰기 설치 및 스페이서 간격조정 공사(가공송전정비 협력회사 총액공사)","송전철탑 피뢰기 설치 및 전력선 스페이서 간격조정","2016-06-06 08:00","2016-06-07 18:00","2016-06-06 08:00","2016-06-07 18:00","매일",null,null,null,201604190149,"-"]
[29,"인천","시흥","오봉논현열병합 T/L<CB>","오봉S/S 미래엔인천에너지T/L Line EDS 점검(유사)","오봉S/S 미래엔인천에너지T/L Line EDS 점검(유사)","2016-06-09 10:30","2016-06-10 18:00","2016-06-09 10:30","2016-06-10 18:00","연속",null,null,null,201603070032,"-"]
[30,"인천","시흥","오봉S/S 154kV #1 BUS","오봉S/S 오봉남동#2T/L GIS 정밀점검","오봉S/S 오봉남동#2T/L GIS 정밀점검","2016-06-02 09:30","2016-06-03 14:00","2016-06-02 09:30","2016-06-03 14:00","연속",null,null,null,201604110260,"-"]
[31,"인천","시흥","오봉S/S 154kV #2 BUS","오봉S/S 오봉남동#2T/L GIS 정밀점검","오봉S/S 오봉남동#2T/L GIS 정밀점검","2016-06-03 14:00","2016-06-04 18:00","2016-06-03 14:00","2016-06-04 18:00","연속",null,null,null,201604110261,"-"]
[32,"인천","시흥","신시흥도림 T/L","154kV 신시흥-도림T/L 피뢰기 설치공사","송전선로용 피뢰기 설치","2016-06-27 00:08","2016-06-30 18:00","2016-06-27 00:08","2016-06-30 18:00","연속",null,null,null,201604110265,"-"]
[33,"인천","시흥","오봉S/S 154kV #1 BUS","오봉S/S 154kV BUS-TIE GIS 정밀점검","오봉S/S 154kV BUS-TIE GIS 정밀점검","2016-06-05 09:30","2016-06-05 18:00","2016-06-05 09:30","2016-06-05 18:00","연속",null,null,null,201604120284,"-"]
[34,"인천","시흥","오봉S/S 154kV #2 BUS","오봉S/S 154kV BUS-TIE GIS정밀점검","오봉S/S 154kV BUS-TIE GIS정밀점검","2016-06-06 09:00","2016-06-06 18:00","2016-06-06 09:00","2016-06-06 18:00","연속",null,null,null,201604120286,"-"]
[35,"인천","시흥","오봉S/S 154kV #1 BUS","오봉S/S 154kV 오봉남동#1T/L GIS 정밀점검","오봉S/S 154kV 오봉남동#1T/L GIS 정밀점검","2016-06-13 09:30","2016-06-14 14:00","2016-06-13 09:30","2016-06-14 14:00","연속",null,null,null,201604120310,"-"]
[36,"인천","시흥","오봉S/S 154kV #2 BUS","오봉S/S 154kV 오봉남동#1T/L GIS 정밀점검","오봉S/S 154kV 오봉남동#1T/L GIS 정밀점검","2016-06-14 14:00","2016-06-15 18:00","2016-06-14 14:00","2016-06-15 18:00","연속",null,null,null,201604120313,"-"]
[37,"인천","시흥","신시흥남동#1 T/L","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","2016-06-16 09:30","2016-06-18 18:00","2016-06-16 09:30","2016-06-18 18:00","연속",null,null,null,201604120321,"-"]
[38,"인천","시흥","남동S/S 154kV #1 BUS","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","2016-06-16 09:30","2016-06-17 14:00","2016-06-16 09:30","2016-06-17 14:00","연속",null,null,null,201604120326,"-"]
[39,"인천","시흥","남동S/S 154kV #2 BUS","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","남동S/S 신시흥남동#1 T/L GIS 정밀점검공사","2016-06-17 14:00","2016-06-18 18:00","2016-06-17 14:00","2016-06-18 18:00","연속",null,null,null,201604120327,"-"]
[40,"인천","시흥","남동S/S 154kV #1 BUS","남동S/S 154kV 남동연수#1T/L GIS 정밀점검 공사","남동S/S 154kV 남동연수#1T/L GIS 정밀점검 공사","2016-06-20 09:30","2016-06-21 14:00","2016-06-20 09:30","2016-06-21 14:00","연속",null,null,null,201604120332,"-"]
[41,"인천","시흥","남동S/S 154kV #2 BUS","남동S/S 154kV 남동연수#1T/L GIS 정밀점검 공사","남동S/S 154kV 남동연수#1T/L GIS 정밀점검 공사","2016-06-21 14:00","2016-06-22 18:00","2016-06-21 14:00","2016-06-22 18:00","연속",null,null,null,201604120333,"-"]
[42,"인천","시흥","남동S/S 154kV #1 BUS","남동S/S 154kV 남동연수#2T/L GIS 정밀점검 공사","남동S/S 154kV 남동연수#2T/L GIS 정밀점검 공사","2016-06-23 09:30","2016-06-24 14:00","2016-06-23 09:30","2016-06-24 14:00","연속",null,null,null,201604120343,"-"]
[43,"인천","시흥","남동S/S 154kV #2 BUS","남동S/S 154kV 남동연수#2T/L GIS 정밀점검 공사","남동S/S 154kV 남동연수#2T/L GIS 정밀점검 공사","2016-06-24 14:00","2016-06-25 18:00","2016-06-24 14:00","2016-06-25 18:00","연속",null,null,null,201604120345,"-"]
[44,"인천","시흥","남동S/S 신시흥남동#2T/L GIS","신시흥. 남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","신시흥. 남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","2016-06-27 09:30","2016-07-02 18:00","2016-06-27 09:30","2016-07-02 18:00","연속",null,null,null,201604120355,"-"]
[45,"인천","시흥","남동S/S 154kV #1 BUS","남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","신시흥. 남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","2016-06-27 09:30","2016-06-28 14:00","2016-06-27 09:30","2016-06-28 14:00","연속",null,null,null,201604120356,"-"]
[46,"인천","시흥","남동S/S 154kV #2 BUS","남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","남동S/S 신시흥남동#2 T/L GIS 정밀점검공사","2016-06-28 14:00","2016-06-29 18:00","2016-06-28 14:00","2016-06-29 18:00","연속",null,null,null,201604120357,"-"]
[47,"인천","시흥","신시흥#1S/S 154kV #61 BUS","신시흥/S/S 신시흥남동#2T/L GIS 정밀점검","신시흥/S/S 신시흥남동#2T/L GIS 정밀점검","2016-06-30 09:30","2016-07-01 14:00","2016-06-30 09:30","2016-07-01 14:00","연속",null,null,null,201604120359,"-"]
[48,"인천","인천","신경서S/S 60-61 SEC GIS","신경서S/S #60-65 모선보호반 대체공사(6061휴전)","신경서S/S #60-65 모선보호반 대체공사(6061휴전)","2016-06-27 09:00","2016-07-01 18:00","2016-06-27 09:00","2016-07-01 18:00","연속",null,null,null,201603290112,"-"]
[49,"인천","인천","신경서S/S 65-66 SEC GIS","신경서S/S #60-65 모선보호반 대체공사(6566휴전)","신경서S/S #60-65 모선보호반 대체공사(6566휴전)","2016-06-27 09:00","2016-07-01 18:00","2016-06-27 09:00","2016-07-01 18:00","연속",null,null,null,201603290113,"-"]
[50,"인천","인천","신경서S/S 154kV #60-65 BUS TIE GIS","신경서S/S #60-65 모선보호반 대체공사(6100휴전)","신경서S/S #60-65 모선보호반 대체공사(6100휴전)","2016-06-27 09:00","2016-07-01 18:00","2016-06-27 09:00","2016-07-01 18:00","연속",null,null,null,201603290114,"-"]
[51,"인천","인천","서인천C/C 154kV #60 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","서인천복합S/Y 345kV #1M.Tr 2차 GIS(6144) 정밀점검","2016-06-04 09:00","2016-06-05 10:00","2016-06-04 09:00","2016-06-05 10:00","연속",null,null,null,201604060010,"-"]
[52,"인천","인천","서인천C/C 154kV #65 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","서인천복합S/Y 345kV #1M.Tr 2차 GIS(6144) 정밀점검","2016-06-05 10:00","2016-06-06 18:00","2016-06-05 10:00","2016-06-06 18:00","연속",null,null,null,201604060011,"-"]
[53,"인천","인천","신경서S/S 신경서경서#1T/L GIS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S 신경서경서#1T/L GIS 정밀점검 공사","2016-06-08 09:00","2016-06-10 18:00","2016-06-08 09:00","2016-06-10 18:00","연속",null,null,null,201604060012,"-"]
[54,"인천","인천","신경서S/S 154kV #61 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S 신경서경서#1T/L GIS 정밀점검 공사","2016-06-08 09:00","2016-06-09 10:00","2016-06-08 09:00","2016-06-09 10:00","연속",null,null,null,201604060013,"-"]
[55,"인천","인천","신경서S/S 154kV #66 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S 신경서경서#1T/L GIS 정밀점검 공사","2016-06-09 10:00","2016-06-10 18:00","2016-06-09 10:00","2016-06-10 18:00","연속",null,null,null,201604060014,"-"]
[56,"인천","인천","신경서S/S 신경서경서#2T/L GIS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S 신경서경서#2T/L GIS 정밀점검 공사","2016-06-13 09:00","2016-06-15 18:00","2016-06-13 09:00","2016-06-15 18:00","연속",null,null,null,201604060015,"-"]
[57,"인천","인천","신경서S/S 154kV #61 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S 신경서경서#2T/L GIS 정밀점검 공사","2016-06-13 09:00","2016-06-14 10:00","2016-06-13 09:00","2016-06-14 10:00","연속",null,null,null,201604060016,"-"]
[58,"인천","인천","신경서S/S 154kV #66 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S 신경서경서#2T/L GIS 정밀점검 공사","2016-06-14 10:00","2016-06-15 18:00","2016-06-14 10:00","2016-06-15 18:00","연속",null,null,null,201604060017,"-"]
[59,"인천","인천","신경서S/S 154kV #61 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S #2M.Tr 2차 GIS 정밀점검 공사","2016-06-16 09:00","2016-06-17 10:00","2016-06-16 09:00","2016-06-17 10:00","연속",null,null,null,201604060019,"-"]
[60,"인천","인천","신경서S/S 154kV #66 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S #2M.Tr 2차 GIS 정밀점검 공사","2016-06-17 10:00","2016-06-18 18:00","2016-06-17 10:00","2016-06-18 18:00","연속",null,null,null,201604060020,"-"]
[61,"인천","인천","신경서S/S 154kV #61-66 BUS TIE GIS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S #61-66 BUS TIE GIS 정밀점검 공사","2016-06-20 09:00","2016-06-22 18:00","2016-06-20 09:00","2016-06-22 18:00","연속",null,null,null,201604060022,"-"]
[62,"인천","인천","신경서S/S 154kV #61 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S #61-66 BUS TIE GIS 정밀점검 공사","2016-06-20 09:00","2016-06-21 10:00","2016-06-20 09:00","2016-06-21 10:00","연속",null,null,null,201604060023,"-"]
[63,"인천","인천","신경서S/S 154kV #66 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","신경서S/S #61-66 BUS TIE GIS 정밀점검 공사","2016-06-21 10:00","2016-06-22 18:00","2016-06-21 10:00","2016-06-22 18:00","연속",null,null,null,201604060024,"-"]
[64,"인천","인천","원창S/S 북인천원창T/L GIS","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 북인천원창T/L GIS 정밀점검","2016-06-27 09:00","2016-06-29 18:00","2016-06-27 09:00","2016-06-29 18:00","연속",null,null,null,201604070097,"-"]
[65,"인천","인천","원창S/S 154kV #1 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 북인천원창T/L GIS 정밀점검","2016-06-27 09:00","2016-06-28 10:00","2016-06-27 09:00","2016-06-28 10:00","연속",null,null,null,201604070098,"-"]
[66,"인천","인천","원창S/S 154kV #2 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 북인천원창T/L GIS 정밀점검","2016-06-28 10:00","2016-06-29 18:00","2016-06-28 10:00","2016-06-29 18:00","연속",null,null,null,201604070101,"-"]
[67,"인천","인천","원창S/S 계양원창T/L GIS","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 계양원창T/L GIS 정밀점검","2016-06-23 09:00","2016-06-26 18:00","2016-06-23 09:00","2016-06-26 18:00","연속",null,null,null,201604070103,"-"]
[68,"인천","인천","원창S/S 154kV #1 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 계양원창T/L GIS 정밀점검","2016-06-23 09:00","2016-06-24 10:00","2016-06-23 09:00","2016-06-24 10:00","연속",null,null,null,201604070104,"-"]
[69,"인천","인천","원창S/S 154kV #2 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 계양원창T/L GIS 정밀점검","2016-06-24 10:00","2016-06-25 18:00","2016-06-24 10:00","2016-06-25 18:00","연속",null,null,null,201604070105,"-"]
[70,"인천","인천","영종S/S 154kV #2 BUS","154kV 신경서-영종S/S SW증설공사","1. 154kV 영종S/S GIS 2CCT 설치 2. 기타 부대작업 1식","2016-06-22 10:00","2016-06-24 18:00","2016-06-22 10:00","2016-06-24 18:00","연속",null,null,null,201604110189,"-"]
[71,"인천","인천","영종S/S 154kV #1 BUS","154kV 신경서-영종S/S SW증설공사","1. 154kV 영종S/S GIS 2CCT 설치 2. 기타 부대작업 1식","2016-06-15 10:00","2016-06-22 10:00","2016-06-15 10:00","2016-06-22 10:00","연속",null,null,null,201604110190,"-"]
[72,"인천","인천","송월남인천#1 T/L","154kV 송월-남인천T/L J/B#1~M/H#2 지장이설공사","한국도로공사에서 시행하는 제2외곽 순환고속도로 건설 구간에 지장되는 154kV 송월-남인천T/L J/B#1~M/H#2 지장이설공사 시행","2016-06-01 09:00","2016-06-20 18:00","2016-06-01 09:00","2016-06-20 18:00","연속",null,null,null,201604120403,"-"]
[73,"인천","인천","송월남인천#2 T/L","154kV 송월-남인천T/L J/B#1~M/H#2 지장이설공사","한국도로공사에서 시행하는 제2외곽 순환고속도로 건설구간에 지장되는 154kV 송월-남인천T/L J/B#1~M/H#2 지장이설공사 시행","2016-06-21 09:00","2016-07-10 18:00","2016-06-21 09:00","2016-07-10 18:00","연속",null,null,null,201604120415,"-"]
[74,"인천","직할","중동화곡#1 T/L","중동S/S 부천하수#2T/L GIS 정밀점검[인접선로위험]","중동S/S 부천하수#2T/L GIS 정밀점검[인접선로위험]","2016-06-03 08:00","2016-06-03 18:00","2016-06-03 08:00","2016-06-03 18:00","당일",null,null,null,201604140238,"-"]
[75,"인천","직할","신부평임학#1 T/L","154kV 신부평-임학#1T/L 접속함 접지선 교체공사","○ 공사목적 : 지중송전 케이블 고장예방을 위해 관내 접속함 중 기준이 변경된 접지선을 교체하여 지중설비 운영에 만전을 기하고자 함. ○ 시공방법 : 접지선 150㎟ → 240㎟ 규격 교체 ○ 시공대상 - 154㎸ 신부평-임학#1T/L(J/B#3,6,9,12,15)","2016-06-27 09:00","2016-06-29 18:00","2016-06-27 09:00","2016-06-29 18:00","연속",null,null,null,201604150245,"-"]
[76,"인천","직할","신가좌부개#1 T/L","154kV 신가좌-부개1T/L 접속함 접지선 교체공사","○ 공사목적 : 지중송전 케이블 고장예방을 위해 관내 접속함 중 기준이 변경된 접지선을 교체하여 지중설비 운영에 만전을 기하고자 함. ○ 시공방법 : 접지선 150㎟ → 240㎟ 규격 교체 ○ 시공대상 - 154㎸ 신가좌-부개#1T/L(J/B#3,6,9,12,15)","2016-06-06 09:00","2016-06-09 18:00","2016-06-06 09:00","2016-06-09 18:00","연속",null,null,null,201604150249,"-"]
[77,"인천","직할","신부평임학#2 T/L","154kV 신부평-임학#2T/L 접속함 접지선 교체공사","○ 공사목적 : 지중송전 케이블 고장예방을 위해 관내 접속함 중 기준이 변경된 접지선을 교체하여 지중설비 운영에 만전을 기하고자 함. ○ 시공방법 : 접지선 150㎟ → 240㎟ 규격 교체 ○ 시공대상 - 154㎸ 신부평-임학#2T/L(J/B#3,6,9,12,15)","2016-06-30 09:00","2016-07-02 18:00","2016-06-30 09:00","2016-07-02 18:00","연속",null,null,null,201604150254,"-"]
[78,"인천","직할","신부평부천#1 T/L","154kV 신부평-부천#1T/L 접속함 접지선 교체공사","○ 공사목적 : 지중송전 케이블 고장예방을 위해 관내 접속함 중 기준이 변경된 접지선을 교체하여 지중설비 운영에 만전을 기하고자 함. ○ 시공방법 : 접지선 150㎟ → 240㎟ 규격 교체 ○ 시공대상 - 154㎸ 신부평-부천#1T/L(J/B#3,6,9,13,16)","2016-06-13 09:00","2016-06-15 18:00","2016-06-13 09:00","2016-06-15 18:00","연속",null,null,null,201604150435,"-"]
[79,"인천","직할","신부평부천#2 T/L","154kV 신부평-부천#2T/L 접속함 접지선 교체공사","○ 공사목적 : 지중송전 케이블 고장예방을 위해 관내 접속함 중 기준이 변경된 접지선을 교체하여 지중설비 운영에 만전을 기하고자 함. ○ 시공방법 : 접지선 150㎟ → 240㎟ 규격 교체 ○ 시공대상 - 154㎸ 신부평-부천#2T/L(J/B#3,6,9,13,16)","2016-06-16 09:00","2016-06-18 18:00","2016-06-16 09:00","2016-06-18 18:00","연속",null,null,null,201604150436,"-"]
[80,"인천","직할","임학계양#1 T/L","스페이서 간격조정 공사(가공송전정비 협력회사 총액공사)","전력선 스페이서 간격조정","2016-06-23 09:00","2016-06-26 18:00","2016-06-23 09:00","2016-06-26 18:00","매일",null,null,null,201604190162,"-"]
[81,"인천","직할","신부평중동#1 T/L","신부평S/S 154kV 신부평-중동 #1T/L GIS 정밀점검","신부평S/S 154kV 신부평-중동 #1T/L GIS 정밀점검","2016-06-20 08:00","2016-06-22 18:00","2016-06-20 08:00","2016-06-22 18:00","연속",null,null,null,201604200185,"-"]
[82,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 신부평-중동 #1T/L GIS 정밀점검","신부평S/S 154kV 신부평-중동 #1T/L GIS 정밀점검","2016-06-20 08:00","2016-06-21 14:00","2016-06-20 08:00","2016-06-21 14:00","연속",null,null,"신뢰도개선",201604200186,"-"]
[83,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 신부평-중동 #1T/L GIS 정밀점검","신부평S/S 154kV 신부평-중동 #1T/L GIS 정밀점검","2016-06-21 14:00","2016-06-22 18:00","2016-06-21 14:00","2016-06-22 18:00","연속",null,null,"신뢰도개선",201604200187,"-"]
[84,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV #62M.Tr 정밀점검","신부평S/S 154kV #62M.Tr 정밀점검","2016-06-23 08:00","2016-06-24 14:00","2016-06-23 08:00","2016-06-24 14:00","연속",null,null,"신뢰도개선",201604200188,"-"]
[85,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV #62M.Tr 정밀점검","신부평S/S 154kV #62M.Tr 정밀점검","2016-06-24 14:00","2016-06-25 18:00","2016-06-24 14:00","2016-06-25 18:00","연속",null,null,"신뢰도개선",201604200189,"-"]
[86,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 신부평-부천 #1T/L GIS 정밀점검","신부평S/S 154kV 신부평-부천 #1T/L GIS 정밀점검","2016-06-13 08:00","2016-06-14 14:00","2016-06-13 08:00","2016-06-14 14:00","연속",null,null,"신뢰도개선",201604220032,"-"]
[87,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 신부평-부천 #1T/L GIS 정밀점검","신부평S/S 154kV 신부평-부천 #1T/L GIS 정밀점검","2016-06-14 14:00","2016-06-15 18:00","2016-06-14 14:00","2016-06-15 18:00","연속",null,null,"신뢰도개선",201604220033,"-"]
[88,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 신부평-부천 #2T/L GIS 정밀점검","신부평S/S 154kV 신부평-부천 #2T/L GIS 정밀점검","2016-06-16 08:00","2016-06-17 14:00","2016-06-16 08:00","2016-06-17 14:00","연속",null,null,"신뢰도개선",201604220034,"-"]
[89,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 신부평-부천 #2T/L GIS 정밀점검","신부평S/S 154kV 신부평-부천 #2T/L GIS 정밀점검","2016-06-17 14:00","2016-06-18 18:00","2016-06-17 14:00","2016-06-18 18:00","연속",null,null,"신뢰도개선",201604220035,"-"]
[90,"경기북부","구리","덕소팔당HP청평HP T/L","청평H/P 덕소팔당청평T/L GCB 정밀점검공사(667CB)","청평H/P 154kV 덕소팔당청평T/L GCB 정밀점검공사(667CB)","2016-06-23 09:00","2016-06-24 18:00","2016-06-23 09:00","2016-06-24 18:00","연속",null,null,null,201604070215,"-"]
[91,"경기북부","구리","별내도봉 T/L","154kV 별내-도봉T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체공사 - 구간 : No.11~12","2016-06-24 08:00","2016-06-24 18:00","2016-06-24 08:00","2016-06-24 18:00","당일",null,null,null,201604150086,"○"]
[92,"경기북부","구리","도봉진접 T/L","154kV 도봉-진접T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체공사 - 구간 : No.11~12","2016-06-25 08:00","2016-06-25 18:00","2016-06-25 08:00","2016-06-25 18:00","당일",null,null,null,201604150090,"-"]
[93,"경기북부","구리","미금화양 T/L","154kV 미금-화양T/L 지장송전선로 이설공사","154kV 미금-화양T/L 지장송전선로 이설공사 ㅇ 가공분야 - 신설 : No.15(CH), No.16 설치 - 철거 : No.3 ~ 16호간 철거 ㅇ 지중 - No.15(CH) ~ 미금S/S","2016-06-01 08:00","2016-06-20 18:00","2016-06-01 08:00","2016-06-20 18:00","연속",null,null,null,201604150323,"-"]
[94,"경기북부","구리","동서울청평PP#1 T/L","154kV 서종S/S 및 분기T/L 건설공사","○ 구간 : 154kV 동서울-청평양수 T/L No.64,65~(신설)서종S/S ○ 선로규모 : 4C-0.283km, C/H 1기 신설 ○ (변전)변전소 보호배전반 대체","2016-06-18 07:00","2016-06-29 19:00","2016-06-18 07:00","2016-06-29 19:00","연속",null,null,null,201604180224,"-"]
[95,"경기북부","구리","동서울청평PP#2 T/L","154kV 서종S/S 및 분기T/L 건설공사","○ 구간 : 154kV 동서울-청평양수 T/L No.64,65~(신설)서종S/S ○ 선로규모 : 4C-0.283km, C/H 1기 신설 ○ (변전)변전소 보호배전반 대체","2016-06-18 07:00","2016-06-19 19:00","2016-06-18 07:00","2016-06-19 19:00","연속",null,null,null,201604180232,"-"]
[96,"경기북부","구리","동서울청평PP#2 T/L","154kV 서종S/S 및 분기T/L 건설공사","○ 구간 : 154kV 동서울-청평양수 T/L No.64,65~(신설)서종S/S ○ 선로규모 : 4C-0.283km, C/H 1기 신설 ○ (변전)변전소 보호배전반 대체","2016-06-30 07:00","2016-07-08 19:00","2016-06-30 07:00","2016-07-08 19:00","연속",null,null,null,201604180235,"-"]
[97,"경기북부","직할","양주S/S 154kV #1 BUS TIE CB","양주S/S 154kV #1 BUS TIE CB","2016년 직할 변전협력회사 총액공사 - #60-65BUS 모선보호반 대체","2016-06-13 10:00","2016-06-17 18:00","2016-06-13 10:00","2016-06-17 18:00","연속",null,null,null,201604120315,"○"]
[98,"경기북부","직할","양주S/S 60-61-0 SEC CB","양주S/S 60-61-0 SEC CB","2016년 직할 변전협력회사 총액공사 - #60-65BUS 모선보호반 대체","2016-06-13 10:00","2016-06-17 18:00","2016-06-13 10:00","2016-06-17 18:00","연속",null,null,null,201604120316,"○"]
[99,"경기북부","직할","양주S/S 154kV #2 BUS TIE CB","양주S/S 154kV #2 BUS TIE CB","2016년 직할 변전협력회사 총액공사 - #61-66BUS 모선보호반 대체","2016-06-20 10:00","2016-06-24 18:00","2016-06-20 10:00","2016-06-24 18:00","연속",null,null,null,201604120319,"○"]
[100,"경기북부","직할","양주S/S 61-62-0 SEC CB","양주S/S 61-62-0 SEC CB","2016년 직할 변전협력회사 총액공사 - #61-66BUS 모선보호반 대체","2016-06-20 10:00","2016-06-24 18:00","2016-06-20 10:00","2016-06-24 18:00","연속",null,null,null,201604120320,"-"]
[101,"경기북부","파주","신파주금촌#1 T/L","신파주S/S 신파주-금촌#1T/L GIS 정밀점검공사","신파주S/S 신파주-금촌#1T/L GIS 정밀점검","2016-06-02 09:30","2016-06-04 18:00","2016-06-02 09:30","2016-06-04 18:00","연속",null,null,null,201603180198,"-"]
[102,"경기북부","파주","신파주금촌#2 T/L","금촌S/S 신파주-금촌#2T/L GIS 정밀점검공사","금촌S/S 신파주-금촌#2T/L GIS 정밀점검","2016-06-13 09:30","2016-06-15 18:00","2016-06-13 09:30","2016-06-15 18:00","연속",null,null,null,201603180204,"-"]
[103,"경기북부","파주","일산S/S 65-66-0 SEC CB","일산S/S 65-66BUS-SEC GIS 정밀점검공사","일산S/S 65-66BUS-SEC GIS 정밀점검","2016-06-27 09:00","2016-06-29 18:00","2016-06-27 09:00","2016-06-29 18:00","연속",null,null,null,201603180206,"-"]
[104,"경기북부","파주","일산S/S 60-61-0 SEC CB","일산S/S 60-61BUS-SEC GIS 정밀점검공사","일산S/S 60-61BUS-SEC GIS 정밀점검","2016-06-30 09:00","2016-07-02 18:00","2016-06-30 09:00","2016-07-02 18:00","연속",null,null,null,201603180208,"○"]
[105,"경기북부","파주","문산월롱#1 T/L","월롱S/S 문산-월롱#1T/L GIS 정밀점검공사","월롱S/S 문산-월롱#1T/L GIS 정밀점검","2016-06-20 09:30","2016-06-22 18:00","2016-06-20 09:30","2016-06-22 18:00","연속",null,null,null,201603180211,"-"]
[106,"경기북부","파주","문산월롱#2 T/L","월롱S/S 문산-월롱#2T/L GIS 정밀점검공사","월롱S/S 문산-월롱#2T/L GIS 정밀점검","2016-06-23 09:30","2016-06-25 18:00","2016-06-23 09:30","2016-06-25 18:00","연속",null,null,null,201603180214,"-"]
[107,"경기북부","파주","일산지도#1 T/L","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(2CCT + PT Bay) 1. 154kV 일산S/S 일산-지도#1,2T/L 2. 154kV #61-66 BUS PT Bay","2016-06-07 08:00","2016-06-26 18:00","2016-06-07 08:00","2016-06-26 18:00","연속",null,null,null,201604080256,"-"]
[108,"경기북부","파주","일산S/S 154kV #65 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(2CCT + PT Bay) 1. 154kV 일산S/S 일산-지도#1,2T/L 2. 154kV #61-66 BUS PT Bay","2016-06-07 08:00","2016-06-09 18:00","2016-06-07 08:00","2016-06-09 18:00","연속",null,null,null,201604080257,"-"]
[109,"경기북부","파주","일산S/S 154kV #60 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(2CCT + PT Bay) 1. 154kV 일산S/S 일산-지도#1,2T/L 2. 154kV #61-66 BUS PT Bay","2016-06-10 08:00","2016-06-19 18:00","2016-06-10 08:00","2016-06-19 18:00","연속",null,null,null,201604080258,"-"]
[110,"경기북부","파주","일산S/S 154kV #65 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S 장기사용 170kV GIS 교체공사(2CCT + PT Bay) 1. 154kV 일산S/S 일산-지도#1,2T/L 2. 154kV #61-66 BUS PT Bay","2016-06-20 08:00","2016-06-26 18:00","2016-06-20 08:00","2016-06-26 18:00","연속",null,null,null,201604080259,"-"]
[111,"경기북부","파주","지도능곡#1 T/L","지도-능곡#1T/L 구형 SVL 교체 공사 J/B 6개소","154kV 지도-능곡T/L 구형 SVL 교체 공사(J/B5,6,8,9,11,12)","2016-06-28 09:00","2016-07-01 18:00","2016-06-28 09:00","2016-07-01 18:00","연속",null,null,null,201604120569,"-"]
[112,"경기북부","파주","신덕은원흥#1 T/L","154kV 신덕은-원흥T/L 장기사용 전력선교체공사","No.12 ~ 17, No.30~39호간 4.319km 전력선교체","2016-06-15 08:00","2016-06-23 18:00","2016-06-15 08:00","2016-06-23 18:00","연속",null,null,null,201604150316,"-"]
[113,"경기북부","파주","신덕은원흥#2 T/L","154kV 신덕은-원흥T/L 장기사용 전력선교체공사","No.12 ~ 17, No.30~39호간 4.319km 전력선교체","2016-06-24 08:00","2016-07-02 18:00","2016-06-24 08:00","2016-07-02 18:00","연속",null,null,null,201604150317,"-"]
[114,"경기북부","파주","월롱금촌#1 T/L","금촌C/H 노후피뢰기 교체공사","월롱-금촌#1T/L 금촌C/H 노후피뢰기 A,B,C상 교체","2016-06-07 09:00","2016-06-08 18:00","2016-06-07 09:00","2016-06-08 18:00","연속",null,null,null,201604180158,"-"]
[115,"경기북부","파주","월롱금촌#2 T/L","금촌C/H 노후피뢰기 교체","월롱-금촌#1T/L 금촌C/H 노후피뢰기 A,B,C상 교체","2016-06-09 09:00","2016-06-10 18:00","2016-06-09 09:00","2016-06-10 18:00","연속",null,null,null,201604180159,"-"]
[116,"경기북부","파주","양주고양#2 T/L","154kV 양주-고양#2T/L 정밀점검","154kV 양주-금촌#2T/L No.1-59 정밀점검관련 4회선구간 안전확보목적 병행휴전","2016-06-20 08:00","2016-06-21 18:00","2016-06-20 08:00","2016-06-21 18:00","연속",null,null,null,201604180295,"○"]
[117,"경기북부","파주","양주고양#1 T/L","154kV 양주-고양#1T/L 정밀점검","154kV 양주-금촌#1T/L No.1-59 정밀점검관련 4회선구간 안전확보목적 병행휴전","2016-06-13 08:00","2016-06-14 18:00","2016-06-13 08:00","2016-06-14 18:00","연속",null,null,null,201604180298,"○"]
[118,"경기북부","파주","일산S/S 154kV #60 BUS","일산S/S 60-61BUS-SEC GIS 정밀점검공사","일산S/S 60-61BUS-SEC #1DS GIS 정밀점검","2016-06-30 09:00","2016-07-01 12:00","2016-06-30 09:00","2016-07-01 12:00","연속",null,null,null,201604190173,"-"]
[119,"경기북부","파주","일산S/S 154kV #65 BUS","일산S/S 65-66BUS-SEC GIS 정밀점검공사","일산S/S 65-66BUS-SEC #1DS GIS 정밀점검","2016-06-27 09:00","2016-06-28 12:00","2016-06-27 09:00","2016-06-28 12:00","연속",null,null,null,201604190186,"-"]
[120,"경기북부","파주","일산S/S 154kV #66 BUS","일산S/S 65-66BUS-SEC GIS 정밀점검공사","일산S/S 65-66BUS-SEC #2DS GIS 정밀점검","2016-06-28 12:00","2016-06-29 18:00","2016-06-28 12:00","2016-06-29 18:00","연속",null,null,null,201604190188,"-"]
[121,"경기북부","파주","고양일산#1 T/L","일산S/S 65-66BUS-SEC GIS 정밀점검공사 안전이격확보","일산S/S 65-66BUS-SEC #2DS GIS 정밀점검","2016-06-28 12:00","2016-06-29 18:00","2016-06-28 12:00","2016-06-29 18:00","연속",null,null,null,201604190234,"○"]
[122,"경기","군포","서서울S/S 154kV #61 BUS","서서울S/S 170kV GCB(61-62-0) 정밀점검공사","서서울S/S 170kV GCB(61-62-0) 정밀점검","2016-06-01 09:00","2016-06-02 18:00","2016-06-01 09:00","2016-06-02 18:00","연속",null,null,"신뢰도개선",201604060164,"-"]
[123,"경기","군포","서서울S/S 154kV #66 BUS","서서울S/S 170kV GCB(66-67-0) 정밀점검공사","서서울S/S 170kV GCB(66-67-0) 정밀점검","2016-06-03 09:00","2016-06-04 18:00","2016-06-03 09:00","2016-06-04 18:00","연속",null,null,"신뢰도개선",201604060165,"-"]
[124,"경기","군포","서서울S/S 154kV #67 BUS","서서울S/S 170kV GCB(66-67-0) 정밀점검공사","- 서서울S/S 170kV GCB(66-67-0) 정밀점검 - 서서울S/S 154kV #67BUS LA, PT 보통점검","2016-06-03 09:00","2016-06-04 18:00","2016-06-03 09:00","2016-06-04 18:00","연속",null,null,"신뢰도개선",201604060166,"-"]
[125,"경기","군포","서서울S/S 154kV #62 BUS","서서울S/S 170kV GCB(61-62-0) 정밀점검공사","- 서서울S/S 170kV GCB(61-62-0) 정밀점검 - 서서울S/S 154kV #62BUS LA, PT 보통점검","2016-06-01 09:00","2016-06-02 18:00","2016-06-01 09:00","2016-06-02 18:00","연속",null,null,"신뢰도개선",201604060167,"-"]
[126,"경기","군포","신시흥시화#2 T/L","시화S/S 신시흥-시화#2T/L 변전기기 점검공사","시화S/S 신시흥-시화#2T/L LA 초기점검","2016-06-23 09:00","2016-06-23 18:00","2016-06-23 09:00","2016-06-23 18:00","당일",null,null,"신뢰도개선",201604070108,"-"]
[127,"경기","군포","서서울산본#1 T/L","154kV 시화,산본S/S 장기사용 GIS 대체공사","산본S/S 산본안양#2, 서서울산본#1T/L GIS 대체","2016-06-20 09:00","2016-07-04 18:00","2016-06-20 09:00","2016-07-04 18:00","연속",null,null,"신뢰도개선",201604110161,"-"]
[128,"경기","군포","시화성곡 T/L","시화,성곡S/S 시화성곡T/L 보호배전반 대체 공사","시화,성곡S/S 시화성곡T/L 보호배전반 대체 공사","2016-06-20 09:00","2016-06-22 18:00","2016-06-20 09:00","2016-06-22 18:00","연속",null,null,null,201604110177,"-"]
[129,"경기","동부","산성성현#1 T/L","동부전력 170kV GIS 정밀점검","성현S/S 170kV 산성-성현#1T/L GIS 정밀점검","2016-06-04 09:00","2016-06-06 18:00","2016-06-04 09:00","2016-06-06 18:00","연속",null,null,null,201604100031,"○"]
[130,"경기","동부","성현분당#1 T/L","동부전력 170kV GIS 정밀점검","분당S/S 170kV 성현-분당#1T/L GIS 정밀점검","2016-06-24 09:00","2016-06-26 18:00","2016-06-24 09:00","2016-06-26 18:00","연속",null,null,null,201604100033,"○"]
[131,"경기","동부","이천율현#2 T/L","154kV 율현S/S SW 증설공사","고객(SK하이닉스) 수전선로 구축에 따른 154kV GIS 설치 - 154kV GIS 2CCT #1BUS측 설치","2016-06-18 09:00","2016-06-19 18:00","2016-06-18 09:00","2016-06-19 18:00","연속",null,null,null,201604120111,"-"]
[132,"경기","동부","이천율현#2 T/L","154kV 율현S/S SW 증설공사","고객(SK하이닉스) 수전선로 구축에 따른 154kV GIS 설치 - 154kV GIS 2CCT #2BUS측 설치","2016-06-25 09:00","2016-06-26 18:00","2016-06-25 09:00","2016-06-26 18:00","연속",null,null,null,201604120120,"-"]
[133,"경기","성남","서안성안성#2 T/L","서안성S/S 서안성안성#2T/L 보호배전반 대체","서안성S/S 서안성안성#2T/L 보호배전반 대체 GIS 보통점검","2016-06-01 09:00","2016-06-03 18:00","2016-06-01 09:00","2016-06-03 18:00","연속",null,null,null,201604080062,"-"]
[134,"경기","성남","용인남사#2 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식","2016-06-01 09:00","2016-06-01 18:00","2016-06-01 09:00","2016-06-01 18:00","당일",null,null,null,201604150023,"-"]
[135,"경기","성남","모현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식","2016-06-15 09:00","2016-06-22 18:00","2016-06-15 09:00","2016-06-22 18:00","연속",null,null,null,201604150032,"-"]
[136,"경기","성남","율현용인#1 T/L","154kV 율현-용인T/L No.30 지장철탑이설","철탑 1기 교체 전력선 교체 : No.29-32","2016-06-01 08:00","2016-06-03 18:00","2016-06-01 08:00","2016-06-03 18:00","연속",null,null,null,201604260063,"-"]
[137,"경기","성남","율현용인#2 T/L","154kV 율현-용인T/L No.30 지장철탑이설","철탑 1기 교체 전력선 교체 : No.29-32","2016-06-04 08:00","2016-06-06 18:00","2016-06-04 08:00","2016-06-06 18:00","연속",null,null,null,201604260065,"-"]
[138,"경기","성남","모현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식","2016-06-30 09:00","2016-06-30 18:00","2016-06-30 09:00","2016-06-30 18:00","당일",null,null,null,201604290050,"-"]
[139,"경기","성남","신용인용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식","2016-06-12 09:00","2016-06-14 18:00","2016-06-12 09:00","2016-06-14 18:00","연속",null,null,null,201604260066,"-"]
[140,"경기","성남","신용인용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식","2016-06-08 09:00","2016-06-10 18:00","2016-06-08 09:00","2016-06-10 18:00","연속",null,null,null,201604260061,"-"]
[141,"경기","직할","조암구문천#2 T/L","154kV 조암구문천#2T/L 안전이격거리확보","345kV 화성-평택TP#2T/L 송전선로용 피뢰기 설치 관련 안전이격거리확보(42~47호)","2016-06-06 07:00","2016-06-06 19:00","2016-06-06 07:00","2016-06-06 19:00","당일",null,null,null,201603140054,"-"]
[142,"경기","직할","화성조암#1 T/L","154kV 화성조암#1T/L 안전이격거리확보","- 345kV 화성-평택TP#2T/L 송전선로용 피뢰기 설치 관련 안전이격거리확보(51~54호)","2016-06-04 07:00","2016-06-04 19:00","2016-06-04 07:00","2016-06-04 19:00","당일",null,null,null,201603140055,"-"]
[143,"경기","직할","남수원발안#1 T/L","154kV 남수원-발안T/L No.27 안전이격확보공사","- 공사내용 : 154kV 남수원-발안T/L No.27 안전이격확보공사 - 시공사 : (주)썬일렉컴","2016-06-20 08:00","2016-06-28 18:00","2016-06-20 08:00","2016-06-28 18:00","연속",null,null,null,201604120051,"-"]
[144,"경기","직할","남수원발안#2 T/L","154kV 남수원-발안T/L No.27 안전이격확보공사","- 공사내용 : 154kV 남수원-발안T/L No.27 안전이격확보공사 - 시공사 : (주)썬일렉컴","2016-06-20 08:00","2016-06-28 18:00","2016-06-20 08:00","2016-06-28 18:00","연속",null,null,null,201604120052,"-"]
[145,"경기","직할","율전의왕#2 T/L","154kV 율전의왕#2 T/L","의왕S/S 154kV 율전의왕#2 T/L 정밀점검공사","2016-06-03 09:00","2016-06-05 18:00","2016-06-03 09:00","2016-06-05 18:00","연속",null,null,"신뢰도개선",201604120246,"-"]
[146,"경기","직할","의왕동안양#2 T/L","154kV 의왕동안양#2 T/L","의왕S/S 154kV 의왕동안양#2 T/L 조향와이어 설치 동안양S/S 154kV 의왕동안양#2 T/L 전자변 히터설치","2016-06-18 10:00","2016-06-18 18:00","2016-06-18 10:00","2016-06-18 18:00","당일",null,null,null,201604120290,"-"]
[147,"경기","평택","오산평택#1 T/L","154kV 오산-평택T/L 전선접속개소 보강공사","전선접속개소 전력선 교체 5개소 10가닥 교체","2016-06-11 08:00","2016-06-15 18:00","2016-06-11 08:00","2016-06-15 18:00","연속",null,null,"신뢰도개선",201604110069,"-"]
[148,"경기","평택","오산평택#2 T/L","154kV 오산-평택T/L 전선접속개소 보강공사","전선접속개소 전력선 교체 5개소 10가닥 교체","2016-06-16 08:00","2016-06-19 18:00","2016-06-16 08:00","2016-06-19 18:00","연속",null,null,"신뢰도개선",201604110070,"-"]
[149,"경기","평택","오산향남#1 T/L","오산-평택T/L 전선접속개소 보강공사에 따른 안전확보(4회선 구간)","전선접속개소 전력선 교체 5개소 10가닥 교체","2016-06-11 08:00","2016-06-12 18:00","2016-06-11 08:00","2016-06-12 18:00","연속",null,null,null,201604110071,"-"]
[150,"경기","평택","오산향남#2 T/L","오산-평택T/L 전선접속개소 보강공사에 따른 안전확보(4회선 구간)","전선접속개소 전력선 교체 5개소 10가닥 교체","2016-06-18 08:00","2016-06-19 18:00","2016-06-18 08:00","2016-06-19 18:00","연속",null,null,null,201604110072,"-"]
[151,"경기","평택","포승평택TP T/L","154kV 포승평택TP T/L 안전이격거리확보","345kV 화성-평택T/P#2T/L 송전선로용 피뢰기 설치 관련 안전이격거리확보(2~5호)","2016-06-05 07:00","2016-06-05 19:00","2016-06-05 07:00","2016-06-05 19:00","당일",null,null,null,201604110367,"-"]
[152,"경기","평택","평택오성CC#2 T/L","평택S/S 평택오성CC#2T/L GCB 정밀점검","-공사명 :'16년 평택전력 170kV GIS 정밀점검 평택S/S 평택오성CC#2T/L GCB 정밀점검","2016-06-25 09:00","2016-06-26 18:00","2016-06-25 09:00","2016-06-26 18:00","연속",null,null,null,201604120104,"-"]
[153,"경기","평택","평택추팔#2 T/L","154kV 추팔S/S #4M.Tr 증설공사","M.Tr(15/20MVA*3)*1BANK 설치 154kV GIS 1CCT 설치 23kV GIS 3CCT 설치(GIB*5포함)","2016-06-24 16:00","2016-06-27 08:30","2016-06-24 16:00","2016-06-27 08:30","연속",null,null,null,201604150361,"-"]
[154,"강원","강릉","신양양_양양#2 T/L","양양변전소 외장재 교체공사","○ 공 사 명 : 양양변전소 외장재 교체공사 ○ 공사목적 : 재해에 취약한 드라이비트 철거 및 메탈판넬 교체공사 ○ 공사내용 - 드라이비트 철거 - 벽체, 난간 지지철물 및 메탈판넬 설치","2016-06-21 09:00","2016-06-29 18:00","2016-06-21 09:00","2016-06-29 18:00","연속",null,null,null,201604150291,"-"]
[155,"강원","강릉","신양양_양양#1 T/L","2016년 가공송전 순시점검 위탁공사","○154kV 신양양-양양#1T/L No.1~62 정밀점검","2016-06-13 09:00","2016-06-17 18:00","2016-06-13 09:00","2016-06-17 18:00","매일",null,null,null,201604160037,"-"]
[156,"강원","동해","이원삼척 T/L","2016~17년도 동해전력지사 송전정비협력회사 총액공사","불량정비개소(불량애자교체)","2016-06-13 08:00","2016-06-14 18:00","2016-06-13 08:00","2016-06-14 18:00","매일",null,null,null,201604140222,"-"]
[157,"강원","동해","정선영월CC T/L","2016년도 가공송전선로 위탁공사","154kV 정선-영월CCT/L 정밀점검","2016-06-01 09:00","2016-06-03 18:00","2016-06-01 09:00","2016-06-03 18:00","매일",null,null,null,201604140223,"-"]
[158,"강원","원주","홍천소양강HP T/L","154kV 소양T/L 안전이격 확보공사","철탑신설 10기, 철탑철거 12기","2016-06-09 07:30","2016-06-13 18:00","2016-06-09 07:30","2016-06-13 18:00","연속",null,null,null,201604130161,"-"]
[159,"강원","원주","원주문막#2 T/L","154kV 서원주S/S 건설공사","154kV 원주-문막#2T/L 보호배전반 철거 154kV 원주-서원주#2T/L 보호배전반 설치 및 준공시험 154kV 서원주분기T/L 건설","2016-06-21 09:00","2016-07-01 18:00","2016-06-21 09:00","2016-07-01 18:00","연속",null,null,null,201604150071,"-"]
[160,"강원","원주","남원주원주#2 T/L","16-17년 송전정비 협력회사 총액공사","남원주-원주 #2T/L 암조재 및 주주재 보강","2016-06-20 09:00","2016-06-20 18:00","2016-06-20 09:00","2016-06-20 18:00","당일",null,null,null,201604150085,"-"]
[161,"강원","원주","신제천남원주#1 T/L","154kV 신제천-남원주#1T/L OPGW 항공장애표시구 교체공사","154kV 신제천-남원주T/L No.37~38호 항공장애표시구 6개 교체","2016-06-15 09:00","2016-06-15 18:00","2016-06-15 09:00","2016-06-15 18:00","당일",null,null,null,201604280087,"-"]
[162,"강원","직할","춘천소양강HP T/L","춘천S/S 170kV 취약설비 GIS화 공사","- 송전선로 인출변경(송전운영부) - GIS 무부하 가압","2016-06-08 09:00","2016-06-16 18:00","2016-06-08 09:00","2016-06-16 18:00","연속",null,null,null,201604110049,"-"]
[163,"강원","직할","서홍천청평PP T/L","2016년 가공송전선로 순시점검 위탁공사","정밀점검","2016-06-13 08:30","2016-06-14 18:00","2016-06-13 08:30","2016-06-14 18:00","매일",null,null,null,201604110062,"-"]
[164,"강원","직할","북춘천화천HP T/L","16년 직할 관내 발,변전소 154kV GCB,GIS 정밀점검공사","화천H/P 북춘천화천HP T/L GCB 내부점검 및 조작메카니즘 점검","2016-06-01 08:00","2016-06-02 18:00","2016-06-01 08:00","2016-06-02 18:00","연속",null,null,null,201604110113,"-"]
[165,"강원","직할","화천화천HP#1 T/L","16년 직할 관내 발,변전소 154kV GCB,GIS 정밀점검공사","화천H/P 화천화천HP #1T/L 차단기 내부점검 및 조작메카니즘 점검","2016-06-09 08:00","2016-06-11 18:00","2016-06-09 08:00","2016-06-11 18:00","연속",null,null,null,201604110121,"-"]
[166,"강원","직할","남춘천춘천 T/L","154kV 소양T/L 안전이격 확보공사","철탑신설 10기, 철탑철거 12기","2016-06-05 07:30","2016-06-08 18:00","2016-06-05 07:30","2016-06-08 18:00","연속",null,null,null,201604110139,"-"]
[167,"강원","직할","화천화천HP#2 T/L","16년 직할 관내 발,변전소 154kV GCB,GIS 정밀점검공사","화천H/P 화천화천HP #2T/L 차단기 내부점검 및 조작메카니즘 점검","2016-06-13 08:00","2016-06-15 18:00","2016-06-13 08:00","2016-06-15 18:00","연속",null,null,null,201604110186,"-"]
[168,"강원","직할","가평춘천HP T/L","16년 상반기 장기 미동작 차단기 조작시험","차단기 동작시험","2016-06-02 10:00","2016-06-02 13:00","2016-06-02 10:00","2016-06-02 13:00","당일",null,null,null,201604120068,"-"]
[169,"강원","직할","남춘천춘천 T/L","154kV 소양T/L 안전이격 확보공사","철탑신설 10기, 철탑철거 12기","2016-06-14 07:30","2016-06-15 18:00","2016-06-14 07:30","2016-06-15 18:00","연속",null,null,null,201604130160,"-"]
[170,"강원","직할","화천H/P 154kV #1 BUS","2016년 강원본부 직할 총액공사 기기점검","2016년 강원본부 직할 총액공사 기기점검 1. 북춘천-화천HP T/L DS A 2. 154kV BUSTIE DS A","2016-06-01 09:00","2016-06-01 14:00","2016-06-01 09:00","2016-06-01 14:00","당일",null,null,null,201604140184,"-"]
[171,"강원","직할","화천H/P 154kV #2 BUS","2016년 강원본부 직할 총액공사 기기점검","2016년 강원본부 직할 총액공사 기기점검 1. 북춘천-화천HP T/L DS B 2. 154kV BUSTIE DS B","2016-06-01 14:00","2016-06-01 18:00","2016-06-01 14:00","2016-06-01 18:00","당일",null,null,null,201604140185,"-"]
[172,"강원","직할","화천H/P 154kV BUS TIE CB","2016년 강원본부 직할 총액공사 기기점검","2016년 강원본부 직할 총액공사 기기점검 1. 154kV BUSTIE DS A 2. 154kV BUSTIE DS B","2016-06-01 09:00","2016-06-01 18:00","2016-06-01 09:00","2016-06-01 18:00","당일",null,null,null,201604140200,"-"]
[173,"강원","직할","화천H/P 154kV #1 BUS","2016년 강원본부 직할 총액공사 기기점검","2016년 강원본부 직할 총액공사 기기점검 1. #2M.Tr 2차 DS A","2016-06-08 09:00","2016-06-08 14:00","2016-06-08 09:00","2016-06-08 14:00","당일",null,null,null,201604140206,"-"]
[174,"강원","직할","화천H/P 154kV #2 BUS","2016년 강원본부 직할 총액공사 기기점검","2016년 강원본부 직할 총액공사 기기점검 1. #2M.Tr 2차 DS B","2016-06-08 14:00","2016-06-08 18:00","2016-06-08 14:00","2016-06-08 18:00","당일",null,null,null,201604140211,"-"]
[175,"강원","태백","태백영월 T/L","154kV 영월화력 등 2개T/L 전선교체공사","154kV 태백-영월T/L No. 91.3~91.4/103~109/111~113 접속개소해소 전선교체공사","2016-06-01 08:00","2016-06-05 18:00","2016-06-01 08:00","2016-06-05 18:00","연속",null,null,null,201604140091,"-"]
[176,"강원","태백","태백삼척GP#1 T/L","'16~'17년 태백전력지사 변전회사 총액공사","태백S/S 154kV 태백-삼척GP#1T/L GIS 하자점검","2016-06-08 09:00","2016-06-08 18:00","2016-06-08 09:00","2016-06-08 18:00","당일",null,null,null,201604180017,"-"]
[177,"강원","태백","태백삼척GP#2 T/L","'16~'17년 태백전력지사 변전회사 총액공사","태백S/S 154kV 태백-삼척GP#2T/L GIS 하자점검","2016-06-09 09:00","2016-06-09 18:00","2016-06-09 09:00","2016-06-09 18:00","당일",null,null,null,201604180018,"-"]
[178,"충북","직할","단양영월CC#2 T/L","154kV 단양-영월CC T/L 송전선로용 피뢰기 설치공사","ㅇ #2T/L 피뢰기 설치 (79기)","2016-06-13 07:30","2016-06-18 18:00","2016-06-13 07:30","2016-06-18 18:00","매일",null,null,null,201604070030,"-"]
[179,"충북","청주","청원신탄진 T/L","16년 청주전력지사 변전협력회사 총액공사","청원S/S 청원-신탄진T/L 보호배전반 대체","2016-06-01 09:00","2016-06-03 18:00","2016-06-01 09:00","2016-06-03 18:00","연속",null,null,null,201604150107,"-"]
[180,"충북","청주","서청주사직#1 T/L","16년 청주전력지사 변전협력회사 총액공사","서청주,사직S/S 서청주-사직#1 T/L 보호배전반 대체","2016-06-10 09:00","2016-06-12 18:00","2016-06-10 09:00","2016-06-12 18:00","연속",null,null,null,201604150108,"-"]
[181,"충북","충주","충주풍동 T/L","차단기 보통점검","차단기 보통점검","2016-06-29 10:00","2016-06-29 18:00","2016-06-29 10:00","2016-06-29 18:00","매일",null,null,null,201604100029,"-"]
[182,"충북","충주","풍동음성#1 T/L","2016~17년 충주 송전정비 협력회사 총액공사","피뢰기 설치","2016-06-15 09:00","2016-06-23 18:00","2016-06-15 09:00","2016-06-23 18:00","매일",null,null,null,201604110095,"○"]
[183,"충북","충주","신진천S/S 61-62-0 SEC CB","154kV 개폐장치 정밀점검 공사","61-62-0 SEC GIS 정밀점검","2016-06-07 08:30","2016-06-09 18:00","2016-06-07 08:30","2016-06-09 18:00","연속",null,null,null,201604120169,"-"]
[184,"충북","충주","신진천S/S 66-67-0 SEC CB","154kV 개폐장치 정밀점검 공사","66-67-0 SEC GIS 정밀점검","2016-06-13 08:30","2016-06-15 18:00","2016-06-13 08:30","2016-06-15 18:00","연속",null,null,null,201604120172,"-"]
[185,"대전충남","대전","신계룡가수원#1 T/L","154kV 신계룡-가수원 등 2개T/L 정밀점검","정밀점검 및 현수애자련(7기) 분해점검 (신계룡S/T ~ No.27)","2016-06-20 07:00","2016-06-24 18:00","2016-06-20 07:00","2016-06-24 18:00","매일",null,null,null,201604140087,"-"]
[186,"대전충남","대전","신계룡가수원#2 T/L","154kV 신계룡-가수원 등 2개T/L 정밀점검","정밀점검 및 현수애자련(7기) 분해점검 (신계룡S/T ~ No.27)","2016-06-27 07:00","2016-07-01 18:00","2016-06-27 07:00","2016-07-01 18:00","매일",null,null,null,201604140090,"-"]
[187,"대전충남","서산","대산석문#1 T/L","대산S/S 154kV GIS 정밀점검(대산석문#1T/L)","○ 154kV GIS 정밀점검(대산석문#1T/L)","2016-06-01 09:00","2016-06-03 18:00","2016-06-01 09:00","2016-06-03 18:00","연속",null,null,null,201604110267,"-"]
[188,"대전충남","서산","대산석문#2 T/L","대산S/S 154kV GIS 정밀점검(대산석문#2T/L)","○ 154kV GIS 정밀점검(대산석문#2T/L)","2016-06-07 09:00","2016-06-09 18:00","2016-06-07 09:00","2016-06-09 18:00","연속",null,null,null,201604110270,"-"]
[189,"대전충남","서산","신당진당진#1 T/L","154kV 아산-송악#1T/L 정밀점검(4회선 병가구간)","[송전] 154kV 아산송악#1T/L No.103~110 (모선로) 정밀점검 -154kV 신당진-당진#1T/L No.36~43","2016-06-13 08:00","2016-06-13 18:00","2016-06-13 08:00","2016-06-13 18:00","당일",null,null,null,201604150105,"-"]
[190,"대전충남","세종","월산서세종 T/L","세종P/O 변전협력회사 총액공사 및 성능개선","○ LA 초기점검(도블측정) ○ 장기 미동작 차단기 부·지연동작 예방 조작시험 ○ 성능개선","2016-06-10 09:30","2016-06-10 18:00","2016-06-10 09:30","2016-06-10 18:00","당일",null,null,null,201604130126,"-"]
[191,"대전충남","아산","둔포한샘#1 T/L","둔포S/S 154kV 한샘-둔포#1T/L GIS 정밀점검 공사","○ 154kV 한샘-둔포#1T/L GIS 정밀점검 및 LA 초기점검 ○ 병행) 한샘S/S 한샘-둔포#1T/L GIS 보통점검","2016-06-22 09:00","2016-06-24 18:00","2016-06-22 09:00","2016-06-24 18:00","연속",null,null,null,201604140196,"-"]
[192,"대전충남","아산","둔포한샘#2 T/L","둔포S/S 154kV 한샘-둔포#2T/L GIS 정밀점검 공사","○ 154kV 한샘-둔포#2T/L GIS 정밀점검 및 LA 초기점검 ○ 병행) 한샘S/S 한샘-둔포#2T/L GIS 보통점검","2016-06-27 09:00","2016-06-29 18:00","2016-06-27 09:00","2016-06-29 18:00","연속",null,null,null,201604140199,"-"]
[193,"대전충남","청양","보령TP보령CC T/L","154kV 보령복합T/L 보호배전반 교체공사","○ 154kV 보령복합T/L 보호배전반 교체","2016-06-01 09:00","2016-06-03 18:00","2016-06-01 09:00","2016-06-03 18:00","연속",null,null,null,201604130089,"-"]
[194,"대전충남","청양","보령C/C 154kV #1 BUS TIE CB","보령복합 154kV 모선 보호배전반 교체공사","○ 154kV 모선 보호배전반 교체","2016-06-07 09:00","2016-06-09 18:00","2016-06-07 09:00","2016-06-09 18:00","연속",null,null,null,201604130091,"-"]
[195,"대전충남","청양","옥산서천화력#1 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 이설구간 : No.2-6 - 철탑설치 : 2기, 가철탑 1기 - 철탑철거 : 3기","2016-06-01 07:00","2016-06-04 18:00","2016-06-01 07:00","2016-06-04 18:00","연속",null,null,null,201604150300,"-"]
[196,"대전충남","청양","대천서천화력#1 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 이설구간 : No.2-6 - 철탑설치 : 2기, 가철탑 1기 - 철탑철거 : 3기","2016-06-01 07:00","2016-06-04 18:00","2016-06-01 07:00","2016-06-04 18:00","연속",null,null,null,201604150305,"-"]
[197,"대전충남","청양","옥산서천화력#2 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 이설구간 : No.2-6 - 철탑설치 : 2기, 가철탑 1기 - 철탑철거 : 3기","2016-06-05 07:00","2016-06-17 18:00","2016-06-05 07:00","2016-06-17 18:00","연속",null,null,null,201604150307,"-"]
[198,"대전충남","청양","대천서천화력#2 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 이설구간 : No.2-6 - 철탑설치 : 2기, 가철탑 1기 - 철탑철거 : 3기","2016-06-05 07:00","2016-06-17 18:00","2016-06-05 07:00","2016-06-17 18:00","연속",null,null,null,201604150309,"-"]
[199,"대전충남","청양","옥산서천화력#1 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 이설구간 : No.2-6 - 철탑설치 : 2기, 가철탑 1기 - 철탑철거 : 3기","2016-06-18 07:00","2016-06-28 18:00","2016-06-18 07:00","2016-06-28 18:00","연속",null,null,null,201604150311,"-"]
[200,"대전충남","청양","대천서천화력#1 T/L","154kV 옥산-서천화력 등 2개T/L 지장송전선로 이설공사","- 이설구간 : No.2-6 - 철탑설치 : 2기, 가철탑 1기 - 철탑철거 : 3기","2016-06-18 07:00","2016-06-28 18:00","2016-06-18 07:00","2016-06-28 18:00","연속",null,null,null,201604150313,"-"]
[201,"대전충남","청양","청양신풍#1 T/L","청양신풍#1 T/L 정밀점검","정밀점검","2016-06-07 08:00","2016-06-10 18:00","2016-06-07 08:00","2016-06-10 18:00","당일",null,null,null,201604200164,"-"]
[202,"전북","군산","군산동군산#1 T/L","군산동군산#1 T/L","-정밀점검 : 37기 -현수애자련 분해점검 : 20기","2016-06-07 08:00","2016-06-11 18:00","2016-06-06 08:00","2016-06-08 18:00","매일",null,null,null,201604110040,"-"]
[203,"전북","군산","군산동군산#2 T/L","군산동군산#2 T/L","154kV 군산-동군산T/L 정밀점검 공사 -정밀점검 : 37기 -현수애자련 분해점검 : 20기","2016-06-12 08:00","2016-06-16 18:00","2016-06-09 08:00","2016-06-11 18:00","매일",null,null,null,201604110042,"-"]
[204,"전북","군산","군산서군산#1 T/L","군산서군산#1 T/L","154kV 군산-동군산T/L 정밀점검 공사 4회선구간 안전이격확보 -정밀점검 : 37기 -현수애자련 분해점검 : 20기","2016-06-11 08:00","2016-06-11 18:00","2016-06-06 08:00","2016-06-06 18:00","매일",null,null,null,201604110045,"-"]
[205,"전북","군산","군산서군산#2 T/L","군산서군산#2 T/L","154kV 군산-동군산T/L 정밀점검 공사 4회선구간 안전이격확보 -정밀점검 : 37기 -현수애자련 분해점검 : 20기","2016-06-12 08:00","2016-06-12 18:00","2016-06-11 08:00","2016-06-11 18:00","매일",null,null,null,201604110046,"-"]
[206,"전북","군산","군공군산CC#1 T/L","154kV군공-군산복합T/L 지중선로 이설공사","154kV 군공-군산복합T/L M/H#10~12번 구간 군장대고 건설관련 지장이설 신청으로 선로 이설","2016-06-27 09:00","2016-07-16 18:00","취소","취소","연속",null,null,null,201604120560,"-"]
[207,"전북","군산","동군산군산복합#2 T/L","동군산군산복합#2 T/L","1. 동군산S/S 154kV 동군산-군산CC#2T/L 접지발생 가스압력계교체","2016-06-01 09:00","2016-06-01 18:00","2016-06-01 09:00","2016-06-01 18:00","당일",null,null,null,201604210001,"-"]
[208,"전북","김제","백산김제#1 T/L","백산김제#1 T/L","차단기 정밀점검","2016-06-02 09:00","2016-06-04 18:00","2016-06-02 09:00","2016-06-04 18:00","연속",null,null,null,201603090290,"-"]
[209,"전북","김제","백산김제#2 T/L","백산김제#2 T/L","차단기 정밀점검","2016-06-13 09:00","2016-06-15 18:00","2016-06-05 09:00","2016-06-07 18:00","연속",null,null,null,201603090291,"-"]
[210,"전북","김제","섬진강H/P 154kV #1 BUS TIE CB","섬진강H/P 154kV #1 BUS TIE CB","모선보호배전반 보조계전기 교체","2016-06-01 10:00","2016-06-01 18:00","2016-06-01 10:00","2016-06-01 18:00","당일",null,null,null,201604060147,"○"]
[211,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주#1T/L 전선접속개소 해소공사","공사명 : 154kV 신김제-남전주#1T/L 전선접속개소 해소공사 공사구간 : No.0.11~36호 공사내용 : 전력선 교체","2016-06-08 08:00","2016-06-13 18:00","2016-06-08 08:00","2016-06-13 18:00","연속",null,null,null,201604150368,"-"]
[212,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주#2T/L 전선접속개소 해소공사","공사명 : 154kV 신김제-남전주#2T/L 전선접속개소 해소공사 공사구간 : No10~36호 공사내용 : 전선접속개소 해소를 위한 전력선 교체","2016-06-20 08:00","2016-06-25 18:00","2016-06-20 08:00","2016-06-25 18:00","연속",null,null,null,201604150373,"-"]
[213,"전북","김제","고창시험#1 T/L","서고창S/S 154kV 초전도용 S.W 증설공사","170kV GIS x 1CCT","2016-06-01 09:00","2016-06-03 18:00","2016-06-01 09:00","2016-06-03 18:00","연속",null,null,null,201604150403,"-"]
[214,"전북","김제","고창시험#2 T/L","서고창S/S 154kV 초전도용 S.W 증설공사","170kV GIS x 1CCT","2016-06-01 09:00","2016-06-03 18:00","2016-06-01 09:00","2016-06-03 18:00","연속",null,null,null,201604150404,"-"]
[215,"전북","김제","백산김제#1 T/L","백산김제#1 T/L","#1 BUS 시험가압","2016-06-20 13:00","2016-06-20 15:00","2016-06-07 13:00","2016-06-07 15:00","당일",null,null,null,201604180397,"-"]
[216,"전북","김제","백산김제#1 T/L","백산김제#1 T/L","#2 BUS 시험가압","2016-06-22 10:00","2016-06-22 12:00","2016-06-09 10:00","2016-06-09 12:00","당일",null,null,null,201604180398,"-"]
[217,"전북","김제","신김제전주#2 T/L","신김제전주#2 T/L","차단기 정밀점검","2016-06-27 09:00","2016-06-29 18:00","2016-06-27 09:00","2016-06-29 18:00","연속",null,null,null,201604180399,"-"]
[218,"전북","김제","신김제전주#1 T/L","신김제전주#1 T/L","차단기 정밀점검","2016-06-30 09:00","2016-07-02 18:00","2016-06-30 09:00","2016-07-02 18:00","연속",null,null,null,201604180400,"-"]
[219,"전북","직할","신김제동전주#1 T/L","동전주S/S 154kV 신김제-동전주#1T/L 장기사용배전반 대체공사","동전주S/S 154kV 신김제-동전주#1T/L 장기사용배전반 대체공사","2016-06-01 09:30","2016-06-03 18:00","2016-06-01 09:30","2016-06-03 18:00","연속",null,null,null,201604180168,"-"]
[220,"전북","직할","무주용담수력 T/L","154kV 무주용담수력T/L 정밀점검","내용 : 정밀점검 구간 : No.1~83호","2016-06-16 09:00","2016-06-18 18:00","2016-06-16 09:00","2016-06-18 18:00","매일",null,null,null,201604190059,"-"]
[221,"광주전남","강진","해남C/S #1 C.Tr <CB>","'16~'17년 #1HVDC 변환설비 위탁정비공사","#1HVDC 변환설비 연차점검","2016-06-03 09:00","2016-06-16 18:00","2016-06-03 09:00","2016-06-16 18:00","연속",null,null,null,201604140109,"-"]
[222,"광주전남","강진","해남C/S #2 C.Tr <CB>","'16~'17년 #1HVDC 변환설비 위탁정비공사","#1 HVDC 변환설비 연차점검","2016-06-10 09:00","2016-06-23 18:00","2016-06-10 09:00","2016-06-23 18:00","연속",null,null,null,201604140110,"-"]
[223,"광주전남","광주","신광주장성#1 T/L","신광주장성#1 T/L(취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-07 09:00","2016-06-07 18:00","2016-06-07 09:00","2016-06-07 18:00","연속",null,null,null,201604010108,"-"]
[224,"광주전남","광주","신광주장성#2 T/L","신광주장성#2 T/L(취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-08 09:00","2016-06-08 18:00","2016-06-08 09:00","2016-06-08 18:00","연속",null,null,null,201604010109,"-"]
[225,"광주전남","광주","신광주일곡#1 T/L","신광주일곡#1T/L(취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-05 09:00","2016-06-05 18:00","2016-06-05 09:00","2016-06-05 18:00","연속",null,null,null,201604010110,"-"]
[226,"광주전남","광주","신광주일곡#2 T/L","신광주일곡#2T/L(취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-12 07:30","2016-06-12 18:00","2016-06-12 07:30","2016-06-12 18:00","연속",null,null,null,201604010112,"-"]
[227,"광주전남","광주","신광주계림#1 T/L","신광주계림#1T/L(취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-01 07:30","2016-06-01 18:00","2016-06-01 07:30","2016-06-01 18:00","연속",null,null,null,201604010113,"-"]
[228,"광주전남","광주","신광주계림#2 T/L","신광주계림#2T/L(취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-02 07:30","2016-06-02 18:00","2016-06-02 07:30","2016-06-02 18:00","연속",null,null,null,201604010114,"-"]
[229,"광주전남","광주","신광주곡성#1 T/L","신광주곡성#1T/L(취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-03 07:30","2016-06-03 18:00","2016-06-10 07:30","2016-06-10 18:00","연속",null,null,null,201604010115,"-"]
[230,"광주전남","광주","신광주곡성#2 T/L","신광주곡성#2T/L(취약설비 GIS화 공사)","T-BUS 철거 및 인출정비","2016-06-09 07:30","2016-06-09 18:00","2016-06-09 07:30","2016-06-09 18:00","연속",null,null,null,201604010116,"-"]
[231,"광주전남","광주","정공담양 T/L","154kV 김제-담양T/L 전선접속개소해소공사","전선교체 No.176-185","2016-06-07 07:00","2016-06-11 18:00","2016-06-07 07:00","2016-06-11 18:00","연속",null,null,null,201604060132,"-"]
[232,"광주전남","광주","담양일곡#2 T/L","154kV 담양-일곡T/L 전선접속개소해소공사","전선교체 No.7-11","2016-06-07 07:00","2016-06-11 18:00","2016-06-07 07:00","2016-06-11 18:00","연속",null,null,null,201604060133,"-"]
[233,"광주전남","광주","장성영광#1 T/L","154kV 장성-영광T/L 전선접속개소해소공사","전선교체 No.38-64","2016-06-09 07:00","2016-06-17 18:00","2016-06-13 07:00","2016-06-17 18:00","연속",null,null,null,201604070024,"-"]
[234,"광주전남","광주","장성영광#2 T/L","154kV 장성-영광T/L 전선접속개소해소공사","전선교체 No.38-64","2016-06-18 07:00","2016-06-26 18:00","2016-06-20 07:00","2016-06-24 18:00","연속",null,null,null,201604070025,"-"]
[235,"광주전남","광주","계림승주#1(서남권상수도T분기) T/L","계림S/S 154kV 계림-승주#1T/L GIS 정밀점검","계림S/S 154kV 계림-승주#1T/L GIS 정밀점검","2016-06-13 09:00","2016-06-15 18:00","2016-06-13 09:00","2016-06-15 18:00","연속",null,null,null,201604120352,"-"]
[236,"광주전남","광주","북광주계림#2 T/L","계림S/S 154kV 북광주-계림#2T/L GIS 정밀점검","계림S/S 154kV 북광주-계림#2T/L GIS 정밀점검","2016-06-30 09:00","2016-07-02 18:00","2016-06-30 09:00","2016-07-02 18:00","연속",null,null,null,201604120353,"-"]
[237,"광주전남","광주","담양S/S 154kV #1 BUS","담양S/S 담양-일곡#2T/L GIS 정밀점검","담양S/S 담양-일곡#2T/L GIS 정밀점검","2016-06-08 09:00","2016-06-09 13:00","2016-06-08 09:00","2016-06-09 13:00","연속",null,null,null,201604190315,"-"]
[238,"광주전남","광주","담양S/S 154kV #2 BUS","담양S/S 담양-일곡#2T/L GIS 정밀점검","담양S/S 담양-일곡#2T/L GIS 정밀점검","2016-06-09 13:00","2016-06-10 18:00","2016-06-09 13:00","2016-06-10 18:00","연속",null,null,null,201604190316,"-"]
[239,"광주전남","목포","고창홍농 T/L","154kV 홍농분기 등 2개T/L 전선접속개소 전선교체공사","154kV 고창-홍농T/L No.42~46, 61~63전선교체 154kV 고창-홍농T/L No.42~46, 61~63전선교체 154kV 고창-홍농T/L No.42~68 피뢰기 설치","2016-06-27 07:00","2016-07-01 18:00","2016-06-27 07:00","2016-07-01 18:00","연속",null,null,null,201604080067,"-"]
[240,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성#2T/L(송전선로 보호반 성능개선)","-영인기술(SEL-311) 154kV 송전선로 보호반 성능개선 내용:BFI,Trip 및 재폐로 용도 접점 변경(송운(계통)-419) -16-17 순천전력지사 변전총액공사 내용 : 154kV GIS 보통점검","2016-06-01 10:00","2016-06-01 18:00","2016-06-01 10:00","2016-06-01 18:00","당일",null,null,null,201603110068,"-"]
[241,"광주전남","순천","용성여수산단#2 T/L","154kV 용성S/S 롯데케미칼 신규수용공사","1. 안전이격거리 확보 및 무부하 가압(154kV #2,1BUS)","2016-06-21 10:00","2016-07-02 17:00","2016-06-21 10:00","2016-07-02 17:00","연속",null,null,null,201604040076,"-"]
[242,"광주전남","순천","율촌화치#1 T/L","345kV 광양-여수TP 등 6개T/L 전선접속개소 해소공사","154kV 율촌-화치#1T/L 전선접속개소 해소 - 전력선 교체 : 23~26호 등 3경간","2016-06-22 07:00","2016-06-25 18:00","2016-06-22 07:00","2016-06-25 18:00","연속",null,null,null,201604110356,"-"]
[243,"광주전남","순천","율촌화치#2 T/L","345kV 광양-여수TP 등 6개T/L 전선접속개소 해소공사","154kV 율촌-화치#2T/L 전선접속개소 해소 - 전력선 교체 : 23~26호 등 3경간","2016-06-26 07:00","2016-06-29 18:00","2016-06-26 07:00","2016-06-29 18:00","연속",null,null,null,201604110357,"-"]
[244,"광주전남","순천","여수TP화치#1 T/L","345kV 광양-여수TP 등 6개T/L 전선접속개소 해소공사","154kV 여수TP-화치#1T/L 전선접속개소 해소 - 전력선 교체 : 23~26호 등 3경간","2016-06-20 07:00","2016-06-21 18:00","2016-06-20 07:00","2016-06-21 18:00","연속",null,null,null,201604110358,"-"]
[245,"광주전남","순천","여수TP화치#2 T/L","345kV 광양-여수TP 등 6개T/L 전선접속개소 해소공사","154kV 여수TP-화치#2T/L 전선접속개소 해소 - 전력선 교체 : 23~26호 등 3경간","2016-06-18 07:00","2016-06-19 18:00","2016-06-18 07:00","2016-06-19 18:00","연속",null,null,null,201604110359,"-"]
[246,"광주전남","순천","호남TP여수TP#1 T/L","345kV 신남원-광양 등 16개T/L 피뢰기 설치공사","154kV 호남TP-여수TP #1T/L 피뢰기 설치 - 피뢰기 설치 : 1~14호, 16기","2016-06-02 07:00","2016-06-03 18:00","2016-06-02 07:00","2016-06-03 18:00","매일",null,null,null,201604110360,"-"]
[247,"광주전남","순천","여천호남TP#1 T/L","345kV 신남원-광양 등 16개T/L 피뢰기 설치공사","154kV 여천-호남TP #1T/L 피뢰기 설치 - 피뢰기 설치 : 1~41호, 41기","2016-06-03 07:00","2016-06-06 18:00","2016-06-03 07:00","2016-06-06 18:00","매일",null,null,null,201604110361,"-"]
[248,"광주전남","순천","여천호남TP#2 T/L","345kV 신남원-광양 등 16개T/L 피뢰기 설치공사","154kV 여천-호남TP #2T/L 피뢰기 설치 - 피뢰기 설치 : 32~41호, 10기","2016-06-07 07:00","2016-06-07 18:00","2016-06-07 07:00","2016-06-07 18:00","당일",null,null,null,201604110362,"-"]
[249,"광주전남","순천","율촌민자#2 T/L","345kV 신남원-광양 등 16개T/L 피뢰기 설치공사","154kV 율촌민자 #2T/L 피뢰기 설치 - 피뢰기 설치 : 1~9호, 9기","2016-06-08 07:00","2016-06-08 18:00","2016-06-08 07:00","2016-06-08 18:00","당일",null,null,null,201604110364,"-"]
[250,"광주전남","순천","순천율촌#2 T/L","345kV 신남원-광양 등 16개T/L 피뢰기 설치공사","154kV 순천-율촌 #2T/L 피뢰기 설치 - 피뢰기 설치 : 57~67호, 11기","2016-06-09 07:00","2016-06-09 18:00","2016-06-09 07:00","2016-06-09 18:00","당일",null,null,null,201604110365,"-"]
[251,"광주전남","순천","서순천주암HP T/L","345kV 신남원-광양 등 16개T/L 피뢰기 설치공사","154kV 소라-서순천 #2T/L 피뢰기 설치 - 4회선 병가개소 휴전","2016-06-14 07:00","2016-06-17 18:00","2016-06-14 07:00","2016-06-17 18:00","매일",null,null,null,201604140047,"-"]
[252,"광주전남","순천","용성여수산단#2 T/L","345kV 신남원-광양 등 16개T/L 피뢰기 설치공사","154kV 여수TP-용성 #2T/L 피뢰기 설치 - 4회선 병가개소 휴전","2016-06-01 07:00","2016-06-01 18:00","2016-06-01 07:00","2016-06-01 18:00","당일",null,null,null,201604140048,"-"]
[253,"광주전남","순천","여천여수#2 T/L","345kV 신남원-광양 등 16개T/L 피뢰기 설치공사","154kV 여천-호남TP #1T/L 피뢰기 설치 - 4회선 병가개소 휴전","2016-06-06 07:00","2016-06-06 18:00","2016-06-06 07:00","2016-06-06 18:00","당일",null,null,null,201604140050,"-"]
[254,"광주전남","순천","여천여수#1 T/L","345kV 신남원-광양 등 16개T/L 피뢰기 설치공사","154kV 여천-호남TP #2T/L 피뢰기 설치 - 4회선 병가개소 휴전","2016-06-07 07:00","2016-06-07 18:00","2016-06-07 07:00","2016-06-07 18:00","당일",null,null,null,201604140051,"-"]
[255,"광주전남","순천","화치S/S 154kV #2 BUS TIE CB","154kV 화치S/S 신규수용공사(금호미쓰이화학)","화치S/S #61,66BUS 모선보호반 F/D 증설","2016-06-13 10:00","2016-06-14 18:00","2016-06-13 10:00","2016-06-14 18:00","연속",null,null,null,201604200054,"-"]
[256,"광주전남","순천","화치S/S 60-61 SEC CB","154kV 화치S/S 신규수용공사(금호미쓰이화학)","화치S/S #61,66BUS 모선보호반 F/D 증설","2016-06-13 10:00","2016-06-14 18:00","2016-06-13 10:00","2016-06-14 18:00","연속",null,null,null,201604200055,"-"]
[257,"광주전남","순천","화치S/S 65-66 CB CB","154kV 화치S/S 신규수용공사(금호미쓰이화학)","화치S/S #61,66BUS 모선보호반 F/D 증설","2016-06-13 10:00","2016-06-14 18:00","2016-06-13 10:00","2016-06-14 18:00","연속",null,null,null,201604200056,"-"]
[258,"대구경북","경산","신경산아화#1 T/L","154kV 금호분기T/L 건설공사","No.1 철탑조립, No.1~9구간 전력선 설치","2016-06-13 08:00","2016-06-24 18:00","2016-06-13 08:00","2016-06-24 18:00","연속",null,null,null,201604070053,"-"]
[259,"대구경북","경산","신경산아화#2 T/L","154kV 금호분기T/L 건설공사","No.1 철탑조립, No.1~9구간 전력선 설치","2016-06-13 08:00","2016-06-24 18:00","2016-06-13 08:00","2016-06-24 18:00","연속",null,null,null,201604070056,"-"]
[260,"대구경북","구미","선산청리#1 T/L","154kV 청리-상주 등 6개T/L 송전선로용 피뢰기 설치공사","154kV 선산-청리#1T/L No.1~No.133호 구간 송전선로용 피뢰기 설치","2016-06-13 08:00","2016-06-26 18:00","2016-06-22 08:00","2016-07-05 18:00","연속",null,null,null,201604130059,"-"]
[261,"대구경북","달성","강창성서#1 T/L","667 GIS 정밀점검 테스트가압","667 GIS 정밀점검 테스트가압","2016-06-10 14:00","2016-06-10 15:00","2016-06-09 14:00","2016-06-09 15:00","당일",null,null,null,201604050083,"-"]
[262,"대구경북","달성","고령논공#1 T/L","154KV 고령-논공#1T/L 정밀점검","154KV 고령-논공#1T/L NO.1-22 정밀점검, 22기","2016-06-11 09:00","2016-06-12 18:00","2016-06-11 09:00","2016-06-12 18:00","연속",null,null,null,201604110235,"-"]
[263,"대구경북","달성","고령논공#2 T/L","154KV 고령-논공#2T/L 정밀점검","154KV 고령-논공#2T/L NO.1-22 정밀점검, 22기","2016-06-18 09:00","2016-06-19 18:00","2016-06-18 09:00","2016-06-19 18:00","연속",null,null,null,201604110236,"-"]
[264,"대구경북","달성","논공달성#1 T/L","EBA 종단접속함 교체관련 애관 실측","자기애관을 폴리머 애관으로 교체","2016-06-04 08:00","2016-06-04 11:00","2016-06-04 08:00","2016-06-04 11:00","당일",null,null,null,201604120043,"-"]
[265,"대구경북","달성","논공달성#2 T/L","EBA 종단접속함 교체관련 애관 실측","자기애관을 폴리머 애관으로 교체","2016-06-04 11:00","2016-06-04 13:00","2016-06-04 11:00","2016-06-04 13:00","당일",null,null,null,201604120046,"-"]
[266,"대구경북","달성","성서달성#1 T/L","EBA 종단접속함 교체관련 애관 실측","자기애관을 폴리머 애관으로 교체","2016-06-04 13:00","2016-06-04 15:00","2016-06-04 13:00","2016-06-04 15:00","당일",null,null,null,201604120063,"-"]
[267,"대구경북","달성","성서달성#2 T/L","EBA 종단접속함 교체관련 애관 실측","자기애관을 폴리머 애관으로 교체","2016-06-04 15:00","2016-06-04 19:00","2016-06-04 15:00","2016-06-04 19:00","당일",null,null,null,201604120065,"-"]
[268,"대구경북","달성","대구범물#1 T/L","2016년 가공송전 순시점검 위탁공사","- 정밀점검 : 대구-범물T/L 정밀점검","2016-06-23 09:00","2016-06-27 18:00","2016-06-24 09:00","2016-06-28 18:00","연속",null,null,null,201604120375,"-"]
[269,"대구경북","달성","대구범물#2 T/L","2016년 가공송전 순시점검 위탁공사","- 정밀점검 : 대구-범물T/L 정밀점검","2016-06-28 09:00","2016-07-01 18:00","2016-06-29 09:00","2016-07-02 18:00","연속",null,null,null,201604120377,"-"]
[270,"대구경북","안동","울진삼척GP#1 T/L","울진S/S 울진-삼척GP #1T/L 정밀점검","울진S/S 울진-삼척GP #1T/L 정밀점검","2016-06-13 09:00","2016-06-15 18:00","2016-06-13 09:00","2016-06-15 18:00","연속",null,null,null,201604120574,"-"]
[271,"대구경북","안동","울진삼척GP#2 T/L","울진S/S 울진-삼척GP #2T/L 정밀점검","울진S/S 울진-삼척GP #2T/L 정밀점검","2016-06-16 09:00","2016-06-18 18:00","2016-06-16 09:00","2016-06-18 18:00","연속",null,null,null,201604120575,"-"]
[272,"대구경북","영주","신영주안동#1 T/L","345kV 신영주-한울NP3T/L 전선접속개소 교체공사","공사구간 : 231~236호간 전선교체관련 하단선로 양회선 동시휴전 필요","2016-06-04 09:00","2016-06-05 18:00","2016-06-04 09:00","2016-06-05 18:00","매일",null,null,null,201604110192,"-"]
[273,"대구경북","영주","신영주안동#2 T/L","345kV 신영주-한울NP3T/L 전선접속개소 교체공사","공사구간 : 231~236호간 전선교체관련 하단선로 양회선 동시휴전 필요","2016-06-04 09:00","2016-06-05 18:00","2016-06-04 09:00","2016-06-05 18:00","매일",null,null,null,201604110193,"-"]
[274,"대구경북","영주","점촌문경 T/L","문경S/S #1M.Tr 6133 GIS 정밀점검(테스트 T/L)","문경S/S 154kV #1M.Tr 6133 GIS 정밀점검(테스트 T/L)","2016-06-24 13:00","2016-06-25 18:00","취소","취소","연속",null,null,null,201604280264,"-"]
[275,"대구경북","영주","점촌문경 T/L","문경S/S 617 GIS 정밀점검, 617 GIS 누유개소 보수(제작사)","문경S/S 617 GIS 정밀점검, 617 GIS 누유개소 보수(제작사)","2016-06-10 09:00","2016-06-25 18:00","취소","취소","연속",null,null,null,201604190052,"-"]
[276,"대구경북","영주","점촌문경 T/L","문경S/S #1BUS TIE 6100 GIS 정밀점검(테스트 T/L)","문경S/S 154kV #1BUS TIE 6100 GIS 정밀점검(테스트 T/L)","2016-06-14 13:00","2016-06-15 18:00","취소","취소","연속",null,null,null,201604280262,"-"]
[277,"대구경북","영주","점촌문경 T/L","문경S/S #2M.Tr 6233 GIS 정밀점검(테스트 T/L)","문경S/S 154kV #2M.Tr 6233 GIS 정밀점검(테스트 T/L)","2016-06-21 13:00","2016-06-22 18:00","취소","취소","연속",null,null,null,201604280263,"-"]
[278,"대구경북","포항","신포항포항#2 T/L","포항S/S 6333 GIS 정밀점검","포항S/S 6333 GIS 정밀점검","2016-06-02 14:00","2016-06-03 18:00","2016-06-02 14:00","2016-06-03 18:00","연속",null,null,null,201604110127,"-"]
[279,"부산울산","동부산","명례고리NP T/L","154kV 명례-고리NPT/L 전선접속개소 전선교체공사","전선접속개소 해소, 구간: 13~17호, 1.072km","2016-06-26 08:00","2016-06-28 18:00","2016-06-26 08:00","2016-06-28 18:00","연속",null,null,null,201604060106,"-"]
[280,"부산울산","동부산","수영정보 T/L","154kV 수영-정보T/L 선로분리공사","정보S/S 수영-정보#2T/L #2BUS측 시험가압","2016-06-03 18:00","2016-06-03 19:00","2016-06-03 18:00","2016-06-03 19:00","당일",null,null,null,201604080128,"-"]
[281,"부산울산","동부산","정관고리NP T/L","154kV 정관-고리NPT/L 전선접속개소 전선교체공사","전선접속개소해소, 정관분기 8~24호, 8.25km","2016-06-29 08:00","2016-07-08 18:00","2016-06-29 08:00","2016-07-08 18:00","연속",null,null,null,201604120026,"-"]
[282,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 170kV GIS 정밀점검공사","서창 170kV 6102DS 정밀점검관련 시험가압(웅촌-서창#1T/L)","2016-06-01 18:00","2016-06-01 19:00","2016-06-01 18:00","2016-06-01 19:00","당일",null,null,null,201604120291,"-"]
[283,"부산울산","동부산","노포정관#2 T/L","정관S/S 170kV GIS 유압계통 보수","정관S/S 170kV 637 GIS 유압계통 보수(노포-정관#2T/L)","2016-06-27 09:00","2016-06-27 10:30","2016-06-27 09:00","2016-06-27 10:30","당일",null,null,null,201604120363,"-"]
[284,"부산울산","동부산","노포정관#1 T/L","정관S/S 170kV GIS 유압계통 보수","정관S/S 170kV 647 GIS 유압계통 보수(노포-정관#2T/L)","2016-06-24 09:00","2016-06-24 10:30","2016-06-24 09:00","2016-06-24 10:30","당일",null,null,null,201604120367,"-"]
[285,"부산울산","동부산","수영정보 T/L","154kV 수영-정보T/L 선로분리공사","1. 수영, 정보S/S 케이블 챔버 분리 - 케이블 챔버 분리에 따른 시험가압 2시간후 - 시험가압선로 : 수영-정보T/L( 6/12 16시~18시) 2. 수영-정보T/L 송전선로 보호반 대체 3. 수영S/S 선로측 PT 이설","2016-06-07 18:00","2016-06-12 19:00","2016-06-07 18:00","2016-06-12 19:00","연속",null,null,null,201604140214,"-"]
[286,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진양수T/L 전선접속개소 전선교체공사","154kV 북부산-삼랑진양수T/L 전선접속개소 전선교체공사 (No.25~46, 7.734km)","2016-06-03 08:00","2016-06-13 18:00","2016-06-03 08:00","2016-06-13 18:00","연속",null,null,null,201604110275,"-"]
[287,"부산울산","북부산","북부산삼랑진PP#1 T/L","154kV 북부산-삼랑진양수T/L 전선접속개소 전선교체공사","154kV 북부산-삼랑진양수T/L 전선접속개소 전선교체공사에 따른 작업자 안전거리확보","2016-06-03 08:00","2016-06-13 18:00","2016-06-03 08:00","2016-06-13 18:00","매일",null,null,null,201604110276,"○"]
[288,"부산울산","북부산","학장개금#1 T/L","학장S/S 170kV 장기사용 GIS 대체(2차)","학장-개금#2T/L, #3M.Tr 1차 GIS 대체(#2DS 및 차단부 시험가압48시간, #1DS 2시간)","2016-06-08 18:00","2016-06-10 20:00","2016-06-08 18:00","2016-06-10 20:00","연속",null,null,null,201604120309,"-"]
[289,"부산울산","북부산","학장개금#1 T/L","학장S/S 170kV 장기사용 GIS 대체(3차)","학장-개금#1T/L, #2M.Tr 1차 GIS 대체, BUS TIE 철거","2016-06-13 09:00","2016-07-08 18:00","2016-06-13 09:00","2016-07-08 18:00","연속",null,null,null,201604120317,"-"]
[290,"부산울산","북부산","학장개금#2 T/L","학장S/S 170kV 장기사용 GIS 대체(3차)","학장-개금#1T/L, #2M.Tr 1차 GIS 대체, BUS TIE 철거(#2BUS측 시험가압)","2016-06-15 16:00","2016-06-15 18:00","2016-06-15 16:00","2016-06-15 18:00","당일",null,null,null,201604120318,"-"]
[291,"부산울산","북부산","학장S/S 154kV #1 BUS","학장S/S 170kV 장기사용 GIS 대체(3차)","학장-개금#1T/L, #2M.Tr 1차 GIS 대체, BUS TIE 철거 (학장-개금#1T/L, #2M.Tr 1차 측 #1DS, CB설치)","2016-06-15 18:00","2016-06-27 18:00","2016-06-15 18:00","2016-06-27 18:00","연속",null,null,null,201604120322,"-"]
[292,"부산울산","북부산","학장S/S 154kV #2 BUS","학장S/S 170kV 장기사용 GIS 대체(3차)","학장-개금#1T/L, #2M.Tr 1차 GIS 대체, BUS TIE 철거 (#2DS측 설치)","2016-06-27 18:00","2016-07-08 18:00","2016-06-27 18:00","2016-07-08 18:00","연속",null,null,null,201604120324,"-"]
[293,"부산울산","북부산","학장개금#2 T/L","학장S/S 170kV 장기사용 GIS 대체(3차)","학장-개금#1T/L, #2M.Tr 1차 GIS 대체, BUS TIE 철거(#1BUS측 시험가압)","2016-06-25 18:00","2016-06-27 18:00","2016-06-25 18:00","2016-06-27 18:00","연속",null,null,null,201604120336,"-"]
[294,"부산울산","북부산","북부산구포#1 T/L","북부산S/S 154kV 취약설비 GIS화공사","T-BUS 및 6C8DS 철거","2016-06-29 09:00","2016-06-30 18:00","2016-06-29 09:00","2016-06-30 18:00","연속",null,null,null,201604120389,"-"]
[295,"부산울산","북부산","양산산막#1 T/L","2016년 북부산변전협력회사 총액공사","양산-산막#1T/L 622DS 조작불량 점검","2016-06-17 10:00","2016-06-17 18:00","2016-06-27 10:00","2016-06-29 18:00","당일",null,null,null,201604120421,"-"]
[296,"부산울산","북부산","양산삼랑진PP T/L","2016년 양산S/S 154kV Sh.C 이설공사","양산S/S 154kV 6179-1,2 Sh.C 이설(Sh.C 이설관련 안전확보)","2016-06-01 09:00","2016-06-02 18:00","2016-06-16 09:00","2016-06-17 18:00","매일",null,null,null,201604120424,"-"]
[297,"부산울산","북부산","북부산양산 T/L","2016년 양산S/S 154kV Sh.C 이설공사","양산S/S 154kV 6179-1,2 Sh.C 이설(Sh.C 이설관련 안전확보)","2016-06-01 09:00","2016-06-02 18:00","2016-06-16 09:00","2016-06-17 18:00","매일",null,null,null,201604120425,"-"]
[298,"부산울산","북부산","북부산S/S 154kV #61 T BUS","북부산S/S 154kV 취약설비 GIS화공사","61T-BUS 철거","2016-06-29 09:00","2016-07-12 18:00","2016-06-29 09:00","2016-07-12 18:00","연속",null,null,null,201604120439,"-"]
[299,"부산울산","북부산","양산S/S 154kV #1-1 SC","2016년 양산S/S 154kV Sh.C 이설공사","양산S/S 154kV 6179-1,2 Sh.C 이설","2016-06-01 09:00","2016-06-14 18:00","2016-06-16 09:00","2016-06-29 18:00","연속",null,null,null,201604120446,"-"]
[300,"부산울산","북부산","양산S/S 154kV #1-2 SC","2016년 양산S/S 154kV Sh.C 이설공사","양산S/S 154kV 6179-1,2 Sh.C 이설","2016-06-01 09:00","2016-06-14 18:00","2016-06-16 09:00","2016-06-29 18:00","연속",null,null,null,201604120451,"-"]
[301,"부산울산","북부산","양산S/S 154kV #1 SC MAIN CB","2016년 양산S/S 154kV Sh.C 이설공사","양산S/S 154kV 6179-1,2 Sh.C 이설","2016-06-01 09:00","2016-06-14 18:00","2016-06-27 09:00","2016-06-29 18:00","연속",null,null,null,201604120454,"-"]
[302,"부산울산","북부산","삼계어방 T/L","2016년 북부산변전협력회사 총액공사","장기사용 보호반 대체(삼계,어방 양측)","2016-06-11 09:00","2016-06-12 18:00","2016-06-11 09:00","2016-06-12 18:00","연속",null,null,null,201604190171,"-"]
[303,"부산울산","울산","온산처용#2 T/L","345kV 신온산분기 등 6개T/L 피뢰기 설치공사","회선명 : 154kV 온산-처용#2 T/L 작업내용: 345kV 신온산-울산TP 송전선로용 피뢰기 설치공사 안전이격 확보(하단 병가구간) 해당구간 : No.1~No.8","2016-06-07 08:00","2016-06-08 18:00","2016-06-07 08:00","2016-06-08 18:00","매일",null,null,null,201604060173,"-"]
[304,"부산울산","울산","신울산언양#1 T/L","154㎸ 신울산-언양T/L OPGW 교체공사","1. OPGW 시설 및 철거 가. OPGW 시설(70SQ 48C) : 신울산변전소 S/T～언양변전소 C/H철탑(22.091 ㎞), 연선 및 긴선작업 - 신울산변전소 S/T～언양변전소 C/H철탑(69기) 나. OPGW 철거 (70SQ 24C) : 신울산변전소 S/T～언양변전소 C/H철탑(21.492 ㎞), 연선 및 긴선 철거작업(69기)","2016-06-08 08:00","2016-06-24 18:00","2016-06-08 08:00","2016-06-24 18:00","연속",null,null,null,201604110180,"-"]
[305,"부산울산","울산","신울산옥동#1 T/L","154㎸ 신울산-언양T/L OPGW 교체공사","1. OPGW 시설 및 철거 가. OPGW 시설(70SQ 48C) : 신울산변전소 S/T～언양변전소 C/H철탑(22.091 ㎞), 연선 및 긴선작업 - 신울산변전소 S/T～언양변전소 C/H철탑(69기) 나. OPGW 철거 (70SQ 24C) : 신울산변전소 S/T～언양변전소 C/H철탑(21.492 ㎞), 연선 및 긴선 철거작업(69기)","2016-06-08 08:00","2016-06-09 18:00","2016-06-08 08:00","2016-06-09 18:00","연속",null,null,null,201604110212,"-"]
[306,"부산울산","울산","신울산옥동#2 T/L","154㎸ 신울산-언양T/L OPGW 교체공사","1. OPGW 시설 및 철거 가. OPGW 시설(70SQ 48C) : 신울산변전소 S/T～언양변전소 C/H철탑(22.091 ㎞), 연선 및 긴선작업 - 신울산변전소 S/T～언양변전소 C/H철탑(69기) 나. OPGW 철거 (70SQ 24C) : 신울산변전소 S/T～언양변전소 C/H철탑(21.492 ㎞), 연선 및 긴선 철거작업(69기)","2016-06-25 08:00","2016-06-26 18:00","2016-06-25 08:00","2016-06-26 18:00","연속",null,null,null,201604110218,"-"]
[307,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양T/L 전선접속개소 전선교체공사","ㅁ 전력선 교체 : 154kV 신울산-언양#2 T/L No.21~27,34~36,56~59","2016-06-24 07:00","2016-06-28 19:00","2016-06-24 07:00","2016-06-28 19:00","연속",null,null,null,201604120522,"-"]
[308,"부산울산","울산","울산울산TP#1 T/L","2016년 170kV 개폐장치 정밀점검공사","울산T/P 617 GIS 정밀점검, 울산S/S 6A7 GIS 보통점검","2016-06-07 08:00","2016-06-09 18:00","2016-06-07 08:00","2016-06-09 18:00","연속",null,null,null,201604130022,"○"]
[309,"부산울산","울산","울산T/P 154kV #65 BUS","2016년 170kV 개폐장치 정밀점검공사","울산T/P 612 GIS 정밀점검","2016-06-07 08:00","2016-06-07 18:00","2016-06-07 08:00","2016-06-07 18:00","당일",null,null,null,201604130023,"○"]
[310,"부산울산","울산","울산T/P 154kV #60 BUS","2016년 170kV 개폐장치 정밀점검공사","울산T/P 611,617,616 GIS 정밀점검","2016-06-08 08:00","2016-06-09 18:00","2016-06-08 08:00","2016-06-09 18:00","연속",null,null,null,201604130024,"○"]
[311,"부산울산","울산","효문방어진 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","효문, 방어진S/S 효문-방어진T/L 선로보호반 교체","2016-06-11 09:00","2016-06-12 18:00","2016-06-11 09:00","2016-06-12 18:00","연속",null,null,null,201604130067,"-"]
[312,"부산울산","울산","온산처용#1 T/L","2016년 170kV 개폐장치 정밀점검공사","온산S/S 677 GIS 정밀점검","2016-06-29 08:00","2016-07-01 18:00","2016-06-29 08:00","2016-07-01 18:00","연속",null,null,null,201604130158,"-"]
[313,"부산울산","울산","방어진영남TP#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","선로보호반 교체","2016-06-04 09:00","2016-06-05 18:00","2016-06-04 09:00","2016-06-05 18:00","연속",null,null,null,201604260215,"-"]
[314,"부산울산","직할","정보대연 T/L","2016-2017년도 서부산전력지사 송전정비협력회사 총액공사","스페이서 간격조정(1~13호)","2016-06-27 09:00","2016-06-28 18:00","2016-06-27 09:00","2016-06-28 18:00","매일",null,null,null,201604080033,"-"]
[315,"부산울산","직할","우동대연 T/L","2016-2017년도 서부산전력지사 송전정비협력회사 총액공사","스페이서 간격조정(1~13호)","2016-06-29 09:00","2016-06-30 18:00","2016-06-29 09:00","2016-06-30 18:00","매일",null,null,null,201604080034,"-"]
[316,"부산울산","직할","서부산부산 T/L","154kV 부산-영도T/L등 3개T/L 이설공사","부산S/S배전 인출 정비 전력구 공사에 지장되어 임시이설한 지중송전선로 본 복구 및 배전,통신 이설 작업을 위한 케이블 인하","2016-06-09 09:00","2016-06-10 18:00","2016-06-09 09:00","2016-06-10 18:00","연속",null,null,null,201604190289,"-"]
[317,"경남","직할","마천진해#2 T/L","마천S/S 장유-마천#1T/L GIS 정밀점검","마천S/S 장유-마천#1T/L GIS 정밀점검 시험가압용","2016-06-20 16:30","2016-06-20 17:30","2016-06-20 16:30","2016-06-20 17:30","당일",null,null,null,201604060112,"-"]
[318,"경남","직할","마천진해#1 T/L","마천S/S 장유-마천#1T/L GIS 정밀점검","마천S/S 장유-마천#1T/L GIS 정밀점검 시험가압용","2016-06-22 16:30","2016-06-22 17:30","2016-06-22 16:30","2016-06-22 17:30","당일",null,null,null,201604060114,"-"]
[319,"경남","직할","마천진해#2 T/L","마천S/S 장유-마천#2T/L GIS 정밀점검","마천S/S 장유-마천#2T/L GIS 정밀점검 시험가압용","2016-06-23 16:30","2016-06-23 17:30","2016-06-23 16:30","2016-06-23 17:30","당일",null,null,null,201604060118,"-"]
[320,"경남","직할","마천진해#1 T/L","마천S/S 장유-마천#2T/L GIS 정밀점검","마천S/S 장유-마천#2T/L GIS 정밀점검 시험가압용","2016-06-25 16:30","2016-06-25 17:30","2016-06-25 16:30","2016-06-25 17:30","당일",null,null,null,201604060122,"-"]
[321,"경남","직할","신김해주촌#1 T/L","154kV 신김해-주촌#1T/L 피뢰기 설치(협력회사공사)","피뢰기 설치(1~18호, 18기)","2016-06-05 08:00","2016-06-06 18:00","2016-06-05 08:00","2016-06-06 18:00","매일",null,null,null,201604070194,"-"]
[322,"경남","직할","신월동읍#1 T/L","154kV 신월-동읍#1T/L 피뢰기 설치(협력회사공사)","피뢰기 설치(1~45호, 45기)","2016-06-11 08:00","2016-06-12 18:00","2016-06-11 08:00","2016-06-12 18:00","매일",null,null,null,201604070196,"-"]
[323,"경남","직할","완암안민#1 T/L","154kV 완암-안민#1T/L 피뢰기 설치,애자련보강(협력공사)","154kV 완암-안민#1T/L 피뢰기 설치(1~7, 12~17, 19~22호, 17기) 애자련보강 : 6~7호 구간","2016-06-26 08:00","2016-06-29 18:00","2016-06-26 08:00","2016-06-29 18:00","매일",null,null,null,201604080053,"-"]
[324,"경남","직할","완암안민#2 T/L","완암-안민#2T/L 애자련보강 및 #1T/L안전이격확보(협력)","애자련보강 공사(6,7호) 154kV 완암-안민#1T/L 피뢰기 설치관련 안전이격확보","2016-06-26 08:00","2016-06-26 18:00","2016-06-26 08:00","2016-06-26 18:00","당일",null,null,null,201604080058,"-"]
[325,"경남","진주","쌍림합천#1 T/L","거창-합천#1T/L GIS 정밀점검","거창-합천#1T/L GIS #1DS 시험가압","2016-06-01 16:00","2016-06-01 17:00","2016-06-01 16:00","2016-06-01 17:00","당일",null,null,null,201603100187,"-"]
[326,"경남","진주","거창합천#2 T/L","거창-합천#2T/L GIS 정밀점검","거창-합천#2T/L GIS 정밀점검, 합천(13~15), 거창(15~17)","2016-06-13 09:30","2016-06-17 18:30","2016-06-13 09:30","2016-06-17 18:30","연속",null,null,null,201604070122,"-"]
[327,"경남","진주","쌍림합천#2 T/L","거창-합천#2T/L GIS 정밀점검 시험가압","합천S/S 거창-합천#2T/L GIS 정밀점검 시험가압","2016-06-14 13:00","2016-06-14 14:00","2016-06-14 13:00","2016-06-14 14:00","연속",null,null,null,201604070125,"-"]
[328,"경남","진주","쌍림합천#1 T/L","합천S/S 거창-합천#2T/L GIS 정밀점검 시험가압","합천S/S 거창-합천#2T/L GIS 정밀점검 시험가압","2016-06-15 13:00","2016-06-15 14:00","2016-06-15 13:00","2016-06-15 14:00","연속",null,null,null,201604070126,"-"]
[329,"경남","진주","함양거창#2 T/L","거창S/S 거창-합천#2T/L GIS 정밀점검 시험가압","거창S/S 거창-합천#2T/L GIS 정밀점검 시험가압","2016-06-16 13:00","2016-06-16 14:00","2016-06-16 13:00","2016-06-16 14:00","연속",null,null,null,201604070129,"-"]
[330,"경남","진주","함양거창#1 T/L","거창-합천#2T/L GIS 정밀점검 시험가압","거창-합천#2T/L GIS 정밀점검 시험가압","2016-06-17 17:30","2016-06-17 18:30","2016-06-17 17:30","2016-06-17 18:30","연속",null,null,null,201604070130,"-"]
[331,"경남","진주","산청함양 T/L","#3M.Tr 1차 GIS 정밀점검 시험가압","#3M.Tr 1차 GIS 정밀점검 시험가압","2016-06-25 13:00","2016-06-26 18:30","2016-06-25 13:00","2016-06-26 18:30","매일",null,null,null,201604070162,"-"]
[332,"경남","진주","하동하동화력#1 T/L","#1M.Tr 1차 GIS 정밀점검 시험가압","#1M.Tr 1차 GIS 정밀점검 시험가압","2016-06-29 13:00","2016-06-30 18:30","2016-06-29 13:00","2016-06-30 18:30","매일",null,null,null,201604070172,"-"]
[333,"경남","진주","동진주진주#2 T/L","동진주-진주#2T/L GIS 보통점검","동진주-진주#2T/L GIS 보통점검","2016-06-11 09:30","2016-06-11 18:30","2016-06-11 09:30","2016-06-11 18:30","당일",null,null,null,201604070179,"-"]
[334,"경남","진주","거창합천#2 T/L","거창합천#2T/L #1BUS-TIE(6100)정밀점검 #BUS 시험가압","#1BUS-TIE(6100)정밀점검 #BUS 시험가압","2016-06-03 12:00","2016-06-03 13:00","2016-06-03 12:00","2016-06-03 13:00","당일",null,null,null,201604210177,"-"]
[335,"경남","진주","거창합천#1 T/L","#1BUS-TIE(6100) 정밀점검 시험가압","#1BUS-TIE(6100) 정밀점검 시험가압","2016-06-04 16:00","2016-06-04 17:00","2016-06-04 16:00","2016-06-04 17:00","당일",null,null,null,201604210179,"-"]
[336,"경남","진주","쌍림합천#1 T/L","쌍림-합천#1T/L GIS CB 정밀점검","쌍림-합천#1T/L GIS CB 정밀점검","2016-06-06 09:00","2016-06-08 18:00","2016-06-06 09:00","2016-06-08 18:00","당일",null,null,null,201604210181,"-"]
[337,"경남","진주","거창합천#2 T/L","쌍림-합천#1T/L GIS #2DS 시험가압","쌍림-합천#1T/L GIS #2DS 시험가압","2016-06-07 12:00","2016-06-07 13:00","2016-06-07 12:00","2016-06-07 13:00","당일",null,null,null,201604210185,"-"]
[338,"경남","진주","쌍림합천#2 T/L","쌍림-합천#2T/L GIS 정밀점검","쌍림-합천#2T/L GIS 정밀점검","2016-06-09 09:00","2016-06-11 18:00","2016-06-09 09:00","2016-06-11 18:00","연속",null,null,null,201604210186,"-"]
[339,"경남","진주","거창합천#1 T/L","쌍림-합천#1T/L GIS #1DS 시험가압","쌍림-합천#1T/L GIS #1DS 시험가압","2016-06-08 16:00","2016-06-08 17:00","2016-06-08 16:00","2016-06-08 17:00","당일",null,null,null,201604210188,"-"]
[340,"경남","진주","거창합천#2 T/L","쌍림-합천#2T/L GIS #2DS 시험가압","쌍림-합천#2T/L GIS #2DS 시험가압","2016-06-10 12:00","2016-06-10 13:00","2016-06-10 12:00","2016-06-10 13:00","당일",null,null,null,201604210189,"-"]
[341,"경남","진주","거창합천#1 T/L","쌍림-합천#2T/L GIS #1DS 시험가압","쌍림-합천#2T/L GIS #1DS 시험가압","2016-06-11 16:00","2016-06-11 17:00","2016-06-11 16:00","2016-06-11 17:00","당일",null,null,null,201604210190,"-"]
[342,"경남","통영","신고성거제#1 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-거제T/L 가철탑 설치 및 전선이설","2016-06-18 07:00","2016-06-18 19:00","2016-06-18 07:00","2016-06-18 19:00","당일",null,null,null,201604070016,"-"]
[343,"경남","통영","신고성거제#2 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-거제T/L 가철탑 설치 및 전선이설","2016-06-19 07:00","2016-06-19 19:00","2016-06-19 07:00","2016-06-19 19:00","당일",null,null,null,201604070018,"-"]
[344,"경남","통영","신고성통영 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 가철탑 설치 및 전선이설","2016-06-25 07:00","2016-06-25 19:00","2016-06-25 07:00","2016-06-25 19:00","당일",null,null,null,201604070019,"-"]
[345,"경남","통영","신고성고성 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 가철탑 설치 및 전선이설","2016-06-26 07:00","2016-06-26 19:00","2016-06-26 07:00","2016-06-26 19:00","당일",null,null,null,201604070020,"-"]
[346,"경남","함안","신마산중리#1 T/L","중리SS 170kV GIS 정밀점검공사","중리SS 중리-가야#1T/L 627 GIS 정밀점검 -621,626,627 시험가압","2016-04-23 18:30","2016-04-23 19:30","2016-06-01 18:30","2016-06-01 19:30","당일",null,null,null,201602120169,"-"]
[347,"경남","함안","신마산S/S 154kV #61 BUS","신마산 154kV #61BUS 점검공사","신마산 154kV #61BUS 점검 - 모선 PT 및 LA 절연열화측정","2016-06-19 09:00","2016-06-19 13:00","2016-06-19 09:00","2016-06-19 13:00","당일",null,null,null,201604070198,"-"]
[348,"경남","함안","신마산S/S 154kV #66 BUS","신마산 154kV #66BUS 점검공사","신마산 154kV #66BUS 점검 - 모선 PT 및 LA 절연열화측정","2016-06-19 13:00","2016-06-19 18:00","2016-06-19 13:00","2016-06-19 18:00","당일",null,null,null,201604070200,"-"]
[349,"경남","함안","초동밀양#2 T/L","밀양SS 초동-밀양#2 GIS대체공사","밀양SS 초동-밀양#2T/L GIS대체 -철거 및 설치","2016-06-03 08:00","2016-06-23 17:30","2016-06-03 08:00","2016-06-23 17:30","연속",null,null,null,201604080118,"-"]
[350,"경남","함안","청도밀양#2 T/L","밀양SS 청도-밀양#2GIS 대체공사","밀양SS 청도-밀양#2GIS 대체 -철거 및 설치 -보호배전반교체","2016-06-24 08:00","2016-07-10 17:30","2016-06-24 08:00","2016-07-10 17:30","연속",null,null,null,201604080130,"-"]
[351,"경남","함안","신마산마산#1 T/L","신마산-마산#1T/L 공압식CB 차단부 히터설치공사","신마산-마산#1T/L 공압식CB 차단부 히터설치","2016-06-25 10:00","2016-06-25 11:00","2016-06-25 10:00","2016-06-25 11:00","당일",null,null,null,201604110103,"-"]
[352,"경남","함안","신마산마산#2 T/L","신마산-마산#2T/L 공압식CB 차단부 히터설치공사","신마산-마산#2T/L 공압식CB 차단부 히터설치 (유사고장)","2016-06-25 11:00","2016-06-25 12:00","2016-06-25 11:00","2016-06-25 12:00","당일",null,null,null,201604110104,"-"]
[353,"경남","함안","신마산차룡#1 T/L","신마산-차룡#1T/L 공압식CB 차단부 히터설치공사","신마산-차룡#1T/L 공압식CB 차단부 히터설치 (유사고장)","2016-06-25 12:00","2016-06-25 13:00","2016-06-25 12:00","2016-06-25 13:00","당일",null,null,null,201604110105,"-"]

{"sheet":"중부","index":3,"n_rows":12,"n_cols":20,"rows_kept":12,"cut":false,"hidden":false,"merged":[[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,19,3,19],[7,0,8,0],[7,1,8,1],[7,2,8,2],[7,3,8,3],[7,4,8,4],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,14,3,14],[7,12,8,12],[2,15,3,15],[2,16,3,16],[2,17,3,17],[2,18,3,18],[7,5,8,5],[7,6,7,7],[7,8,7,9],[7,10,8,10],[7,11,8,11],[7,19,8,19],[7,13,8,13],[7,14,8,14],[7,15,8,15],[7,16,8,16],[7,17,8,17],[7,18,8,18]]}
["2016년도 6월 휴전계획표(한국중부발전)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"보령복합","신보령","신보령 연락 T/L\n신보령(CB7171, CB7100)\n보령복합(CB7471, CB7400)","송전선로 전선\n교체공사","지락사고로 일부 \n소손된 송전선로 \n교체공사","2016-06-16\n9:00:00 AM","2016-06-17  18:00:00 PM","2016-06-16\n9:00:00 AM","2016-06-17  18:00:00 PM","연속"]
[]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","북상\n선로","수도권\n환상망","발전\n연계","사업소\n간","사업소\n내"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서천화력본부","서천화력","서천화력 탈황 #62\n(CB6383)","법정검사","법정검사","2016-05-28","2016-05-31T23:59:00","2016-05-28","2016-05-31T23:59:00","연속",null,null,"일정변경"]
[2,"서천화력본부","서천화력","서천화력 탈황 #61\n(CB6283)","법정검사","법정검사","2016-06-02","2016-06-06T23:59:00","2016-06-02","2016-06-06T23:59:00","연속",null,null,"추가요청"]
[3,"서천화력본부","서천화력","서천화력 제2호기\n(CB6233)","계획예방정비공사(간이)","계획예방정비공사\n(간이)","2016-05-28","2016-06-06T23:59:00","2016-05-28","2016-06-06T23:59:00","연속",null,null,"일정변경"]