{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","중부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":7,"n_cols":16,"rows_kept":7,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 7월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백S/S #2 M.Tr 1차 CB","신태백S/S 800kV GIS 정밀점검공사[8372]","신태백S/S 800kV GIS 정밀점검공사[8372]","2016-07-18 09:00","2016-08-02 18:00","취소","취소","연속",null,null,null,201605120004]
[2,"강원","태백","신태백-신한울NP#2T/L-#2M.Tr1차 GIS(8300)","765kV 신태백S/S SW 증설공사","765kV 신태백-신한울N/P #2T/L 보호배전반 설치 및 연동시험","2016-07-16 09:00","2016-07-25 18:00","취소","취소","연속",null,null,null,201605110151]
[3,"강원","태백","신태백S/S 신태백-신한울NP#2T/L GIS(8371)","765kV 신태백S/S SW 증설공사","765kV 신태백-신한울N/P #2T/L 보호배전반 설치 및 연동시험","2016-07-16 09:00","2016-07-25 18:00","취소","취소","연속",null,null,null,201605110150]

{"sheet":"345송부","index":1,"n_rows":103,"n_cols":16,"rows_kept":103,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 7월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","김포","345kV 가정개폐소 #2 Sh.R 1차 CB (7171)","345KV 가정개폐소 7171CB 정밀점검 공사","- 7171CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-04 10:00","2016-07-06 14:00","2016-07-04 10:00","2016-07-06 14:00","연속",null,null,null,201605180014]
[2,"인천","김포","가정개폐소 가정 - 인천CC#2T/L CB (7271)","345KV 가정개폐소 7271CB 정밀점검 공사","- 7271CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-04 10:00","2016-07-06 14:00","2016-07-04 10:00","2016-07-06 14:00","연속",null,null,null,201605180016]
[3,"인천","김포","가정인천CC#2 -가정신부평 #3 TIE CB (7200)","345KV 가정개폐소 7200CB 정밀점검 공사","- 7200CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-06 14:00","2016-07-08 18:00","2016-07-06 14:00","2016-07-08 18:00","연속",null,null,null,201605180018]
[4,"인천","김포","가정개폐소 345KV #2,3Sh.R - TIE CB (7100)","345KV 가정개폐소 7100CB 정밀점검 공사","- 7100CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-06 14:00","2016-07-08 18:00","2016-07-06 14:00","2016-07-08 18:00","연속",null,null,null,201605180017]
[5,"인천","김포","가정개폐소 가정 - 신부평#3T/L CB (7272)","345KV 가정개폐소 7272CB 정밀점검 공사","- 7272CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-11 10:00","2016-07-13 14:00","2016-07-11 10:00","2016-07-13 14:00","연속",null,null,null,201605180020]
[6,"인천","김포","345kV 가정개폐 #3Sh.R 1차 CB (7172)","345KV 가정개폐소 7172CB 정밀점검 공사","- 7172CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-11 10:00","2016-07-13 14:00","2016-07-11 10:00","2016-07-13 14:00","연속",null,null,null,201605180019]
[7,"인천","김포","가정개폐소 345KV 75-76 SEC CB (75-76-0)","345KV 가정개폐소75-76-0CB 정밀점검 공사","- 75-76-0CB - 345KV GIS 13CB 점검","2016-07-25 10:00","2016-07-27 14:00","2016-07-25 10:00","2016-07-27 14:00","연속",null,null,null,201605180027]
[8,"인천","김포","가정개폐소 가정 - 인천CC#1T/L CB (7471)","345KV 가정개폐소 7471CB 정밀점검 공사","- 7471CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-13 14:00","2016-07-15 18:00","2016-07-13 14:00","2016-07-15 18:00","연속",null,null,null,201605180021]
[9,"인천","김포","가정개폐소 345KV #1Sh.R - TIE CB (7600)","345KV 가정개폐소 7600CB 정밀점검 공사","- 7600CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-18 10:00","2016-07-20 14:00","2016-07-18 10:00","2016-07-20 14:00","연속",null,null,null,201605180024]
[10,"인천","김포","가정인천CC#1 -가정신부평 #1 TIE CB (7400)","345KV 가정개폐소 7400CB 정밀점검 공사","- 7400CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-18 10:00","2016-07-20 14:00","2016-07-18 10:00","2016-07-20 14:00","연속",null,null,null,201605180023]
[11,"인천","김포","가정개폐소 가정 - 신부평#1T/L CB (7600)","345KV 가정개폐소7472CB 정밀점검 공사","- 7472 CB - 345KV GIS 13CB 점검","2016-07-20 14:00","2016-07-22 18:00","2016-07-20 14:00","2016-07-22 18:00","연속",null,null,null,201605180025]
[12,"인천","김포","가정개폐소 345KV 70-71 SEC CB (70-71-0)","345KV 가정개폐소 70-71-0CB 정밀점검 공사","-70-71-0CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-20 14:00","2016-07-22 18:00","2016-07-20 14:00","2016-07-22 18:00","연속",null,null,null,201605180026]
[13,"인천","김포","345kV 가정개폐소 #1 Sh.R 1차 CB (7671)","345KV 가정개폐소 7671CB 정밀점검 공사","- 7671CB 정밀점검 - 345KV GIS 13CB 점검","2016-07-13 14:00","2016-07-15 18:00","2016-07-13 14:00","2016-07-15 18:00","연속",null,null,null,201605180022]
[14,"인천","시흥","신시흥영서#1 T/L","345kV 신시흥영서T/L 정밀점검","345kV 신시흥영서T/L 정밀점검(신가좌신시흥 병행)","2016-07-11 08:00","2016-07-16 18:00","2016-07-11 08:00","2016-07-16 18:00","매일",null,null,null,201605160097]
[15,"인천","시흥","신가좌신시흥#1 T/L","345kV 신가좌신시흥T/L 정밀점검","345kV 신가좌신시흥T/L 정밀점검(신시흥영서 병행)","2016-07-11 08:00","2016-07-16 18:00","2016-07-11 08:00","2016-07-16 18:00","매일",null,null,null,201605160098]
[16,"인천","인천","서인천C/C 서인천신부평#2T/L-#3 M.Tr 1차 CB (7300)","서인천CC #3M.Tr 1차 7300CB 초기점검","서인천CC #3M.Tr 1차 7300CB 초기점검","2016-07-08 09:00","2016-07-08 18:00","2016-07-08 09:00","2016-07-08 18:00","당일",null,null,null,201605170101]
[17,"인천","인천","서인천C/C 서인천신부평#3T/L CB (7471)","서인천CC 서인천신부평#3T/L 7471CB 초기점검","서인천CC 서인천신부평#3T/L 7471CB 초기점검","2016-07-11 09:00","2016-07-11 18:00","2016-07-11 09:00","2016-07-11 18:00","당일",null,null,null,201605170102]
[18,"인천","인천","서인천C/C 서인천신부평#2T/L CB (7371)","서인천CC 서인천신부평#2T/L 7371CB 초기점검","서인천CC 서인천신부평#2T/L 7371CB 초기점검","2016-07-07 09:00","2016-07-07 18:00","2016-07-07 09:00","2016-07-07 18:00","당일",null,null,null,201605170100]
[19,"인천","인천","서인천C/C 345kV #70 BUS","345kV 서인천CC 용량부족 GIS 대체공사","- #70BUS 모선개조 및 모선용 DS 대체","2016-07-01 09:00","2016-08-04 18:00","취소","취소","연속",null,null,null,201605160018]
[20,"인천","인천","신경서S/S #2 M.Tr A","신경서S/S #2 M.Tr 2차 과열보수 공사","신경서S/S #2 M.Tr 2차 과열보수 공사","2016-07-05 09:00","2016-07-05 18:00","2016-07-05 09:00","2016-07-05 18:00","당일",null,null,null,201605160302]
[21,"인천","인천","인천T/P 인천복합 #3,4 G/T CB (7571)","인천복합S/Y 7551DS B상 이음발생관련 보수공사","-휴전설비 : 7571CB -인천복합S/Y 7551DS B상 이음발생관련 보수공사","2016-07-05 09:00","2016-07-06 18:00","2016-07-05 09:00","2016-07-06 18:00","연속",null,null,null,201605180001]
[22,"인천","인천","인천T/P 인천복합 #2 S/T CB (7671)","인천복합S/Y 7651DS C상 이음발생관련 보수공사","-휴전설비 : 7671CB -인천복합S/Y 7651DS C상 이음발생관련 보수공사","2016-07-11 09:00","2016-07-14 18:00","2016-07-11 09:00","2016-07-14 18:00","연속",null,null,null,201605180002]
[23,"인천","인천","인천CC S/Y 345kV #71 BUS","인천복합S/Y 7651DS C상 이음발생관련 보수공사","인천복합S/Y 7651DS C상 이음발생관련 보수공사","2016-07-11 09:00","2016-07-14 18:00","2016-07-11 09:00","2016-07-14 18:00","연속",null,null,null,201605180003]
[24,"인천","인천","인천CC S/Y #1Tie-Tr A","인천CC S/Y #1Tie-Tr 2차 과열보수 공사","인천CC S/Y #1Tie-Tr 2차 과열보수 공사","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605160301]
[25,"경기북부","파주","신덕은S/S #2 M.Tr A","신덕은S/S #2M.Tr 3차 GPT 점검","- #2M.Tr 3차 GPT 점검 (포화전압특성시험) - 접지패드 보강","2016-07-06 10:00","2016-07-06 18:00","2016-07-06 10:00","2016-07-08 18:00","당일",null,null,null,201605100010]
[26,"경기북부","파주","신덕은S/S #1 M.Tr A","신덕은S/S #1M.Tr 3차 GPT 점검","- #1M.Tr 3차 GPT 점검 (포화전압특성시험) - 접지패드 보강","2016-07-05 10:00","2016-07-05 18:00","2016-07-05 10:00","2016-07-05 18:00","당일",null,null,null,201605100008]
[27,"경기북부","파주","신덕은장문CC#1 T/L","345kV 장문C/C-신덕은 지중T/L 건설공사","신설 No.5 C/H 피뢰기 정밀점검","2016-07-04 10:00","2016-07-04 14:00","2016-07-04 10:00","2016-07-04 14:00","당일",null,null,null,201605160020]
[28,"경기북부","파주","신덕은장문CC#2 T/L","345kV 장문C/C-신덕은 지중T/L 건설공사","신설 No.5 C/H 피뢰기 정밀점검","2016-07-04 14:00","2016-07-04 18:00","2016-07-04 14:00","2016-07-04 18:00","당일",null,null,null,201605160021]
[29,"경기","성남","신용인S/S #3 M.Tr A","신용인S/S 154kV #3M.Tr 2차 GIS 정밀점검","신용인S/S 154kV #3M.Tr 2차 GIS 정밀점검","2016-07-07 08:30","2016-07-09 18:00","2016-07-07 08:30","2016-07-09 18:00","연속",null,null,null,201605100194]
[30,"경기","직할","화성S/S 75-76 SEC GIS","화성S/S 75-76 SEC GIS","화성S/S 75-76 SEC GIS 전자변 히터설치","2016-07-11 14:00","2016-07-11 18:00","2016-07-11 14:00","2016-07-11 18:00","당일",null,null,null,201605090173]
[31,"경기","직할","화성S/S 70-71 SEC GIS","화성S/S 70-71 SEC GIS","화성S/S 70-71 SEC GIS 전자변 히터설치","2016-07-11 10:00","2016-07-11 14:00","2016-07-11 10:00","2016-07-11 14:00","당일",null,null,null,201605090172]
[32,"강원","동해","북평T/P #2STEP-UP Tr 1차 CB (7272)","동해전력지사 북평TP 누유개소 보수공사","1. 7272 CB 누유개소 보수(프레샤S/W 교체 등)","2016-07-06 09:30","2016-07-06 18:00","2016-07-06 09:30","2016-07-06 18:00","당일",null,null,null,201605180032]
[33,"강원","동해","삼척GP 동해-삼척GP #2T/L CB (7771)","동해전력지사 삼척GP 누유개소 보수공사","1. 7771 CB 누유개소 보수(프레샤S/W 교체 등)","2016-07-05 09:30","2016-07-05 18:00","2016-07-05 09:30","2016-07-05 18:00","당일",null,null,null,201605180031]
[34,"충북","직할","신제천신충주#2 T/L","2016년 가공송전선로 순시점검 위탁공사","지장수목벌채","2016-07-01 08:00","2016-07-01 18:00","2016-07-01 08:00","2016-07-01 18:00","당일",null,null,null,201605250032]
[35,"충북","직할","신제천S/S #1 M.Tr A","신제천S/S 345kV GIS화 공사","345kV #1M.TR 1차측 차단기 철거 345kV GIS 설치","2016-07-11 08:00","2016-11-10 18:00","2016-07-11 08:00","2016-11-10 18:00","연속",null,null,null,201605230020]
[36,"충북","직할","신제천S/S 345kV #1 BUS","신제천S/S 345kV GIS 설치공사","345KV GIS 설치","2016-07-04 08:00","2016-07-06 18:00","2016-07-04 08:00","2016-07-06 18:00","매일",null,null,null,201605300048]
[37,"대전충남","서산","북당진S/S GSEPS #3호기 CB (7272)","북당진S/S 345kV GIS 하자점검(7272)","○ 345kV GIS 하자점검(7272)","2016-07-14 09:00","2016-07-14 18:00","2016-07-14 09:00","2016-07-14 18:00","당일",null,null,null,201605130015]
[38,"대전충남","서산","북당진S/S GSEPS #2호기 CB (7472)","북당진S/S 345kV GIS 하자점검(7472)","○ 345kV GIS 하자점검(7472)","2016-07-15 09:00","2016-07-15 18:00","2016-07-15 09:00","2016-07-15 18:00","당일",null,null,null,201605120112]
[39,"대전충남","서산","북당진S/S GSEPS #3호기 -TIE CB (7200)","북당진S/S 345kV GIS 하자점검(7200)","○ 345kV GIS 하자점검(7200)","2016-07-13 09:00","2016-07-13 18:00","2016-07-13 09:00","2016-07-13 18:00","당일",null,null,null,201605120110]
[40,"대전충남","서산","북당진S/S GSEPS #2호기 -TIE CB (7400)","북당진S/S 345kV GIS 하자점검(7400)","○ 345kV GIS 하자점검(7400)","2016-07-12 09:00","2016-07-12 18:00","2016-07-12 09:00","2016-07-12 18:00","당일",null,null,null,201605120109]
[41,"대전충남","서산","북당진S/S 신당진-북당진T/L CB (7171)","북당진S/S 345kV GIS 하자점검(7171)","○ 345kV GIS 하자점검(7171)","2016-07-11 09:00","2016-07-11 18:00","2016-07-11 09:00","2016-07-11 18:00","당일",null,null,null,201605120108]
[42,"대전충남","서산","북당진S/S 신당진북당진-북당진현대T/L CB (7100)","북당진S/S 345kV GIS 하자점검(7100)","○ 345kV GIS 하자점검(7100)","2016-07-08 09:00","2016-07-08 18:00","2016-07-08 09:00","2016-07-08 18:00","당일",null,null,null,201605120106]
[43,"대전충남","서산","신당진개폐소 7A-7B SECTION CB (7A-7B-0)","개폐소 345kV GIS 초기점검(7A-7B-0)","○ 345kV GIS 초기점검(7A-7B-0)","2016-07-06 09:00","2016-07-06 18:00","2016-07-06 09:00","2016-07-06 18:00","당일",null,null,null,201605120102]
[44,"대전충남","서산","신당진 개폐소태안TP#1T/L CB (7A71)","개폐소 345kV GIS 초기점검(7A71)","○ 345kV GIS 초기점검(7A71)","2016-07-20 09:00","2016-07-20 18:00","2016-07-20 09:00","2016-07-20 18:00","당일",null,null,null,201605120123]
[45,"대전충남","서산","신당진개폐소 신당진연락#1T/L CB (E013)","개폐소 345kV GIS 초기점검(7A72)","○ 345kV GIS 초기점검(7A72)","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605130017]
[46,"대전충남","서산","신당진개폐소 신당진연락#2T/L CB (E013)","개폐소 345kV GIS 초기점검(7C72)","○ 345kV GIS 초기점검(7C72)","2016-07-01 09:00","2016-07-01 18:00","2016-07-01 09:00","2016-07-01 18:00","당일",null,null,null,201605130018]
[47,"대전충남","서산","신당진 개폐소태안TP#1-연락#1T/L CB (E013)","개폐소 345kV GIS 초기점검(7A00)","○ 345kV GIS 초기점검(7A00)","2016-07-05 09:00","2016-07-05 18:00","2016-07-05 09:00","2016-07-05 18:00","당일",null,null,null,201605120103]
[48,"대전충남","서산","신당진 개폐소북당진#1T/L CB (7D71)","개폐소 345kV GIS 초기점검(7D01)","○ 345kV GIS 초기점검(7D01)","2016-07-21 09:00","2016-07-21 18:00","2016-07-21 09:00","2016-07-21 18:00","당일",null,null,null,201605120124]
[49,"대전충남","서산","신당진 개폐소북당진#1T/L-TIE CB (7D71)","개폐소 345kV GIS 초기점검(7D00)","○ 345kV GIS 초기점검(7D00)","2016-07-22 09:00","2016-07-22 18:00","2016-07-22 09:00","2016-07-22 18:00","당일",null,null,null,201605120125]
[50,"대전충남","서산","신당진 개폐소태안TP#2T/L CB (7C71)","개폐소 345kV GIS 초기점검(7C71)","○ 345kV GIS 초기점검(7C71)","2016-07-26 09:00","2016-07-26 18:00","2016-07-26 09:00","2016-07-26 18:00","당일",null,null,null,201605120126]
[51,"대전충남","서산","신당진 개폐소태안TP#2-연락#2T/L CB (E013)","개폐소 345kV GIS 초기점검(7C00)","○ 345kV GIS 초기점검(7C00)","2016-07-19 09:00","2016-07-19 18:00","2016-07-19 09:00","2016-07-19 18:00","당일",null,null,null,201605120122]
[52,"대전충남","서산","신당진개폐소 7C-7D SECTION CB (7C-7D-0)","개폐소 345kV GIS 초기점검(7C-7D-0)","○ 345kV GIS 초기점검(7C-7D-0)","2016-07-07 09:00","2016-07-07 18:00","2016-07-07 09:00","2016-07-07 18:00","당일",null,null,null,201605120101]
[53,"대전충남","청양","보령C/C 345kV #70 BUS","보령C/C 345kV #70BUS 보호반 교체","○ 345kV #70BUS 보호반 교체","2016-07-04 09:30","2016-07-05 18:00","2016-07-04 09:30","2016-07-05 18:00","연속",null,null,null,201605040019]
[54,"대전충남","청양","보령C/C 345kV #75 BUS","보령C/C 345kV #75BUS 보호반 교체","○ 345kV #70BUS 보호반 교체","2016-07-06 09:30","2016-07-07 18:00","2016-07-06 09:30","2016-07-07 18:00","연속",null,null,null,201605040020]
[55,"대전충남","청양","보령C/C #4 M.Tr 1차-신보령연락T/L CB (7400)","보령복합 362kV GIS 보통점검","○ 345kV 7400 GIS 보통점검","2016-07-08 09:00","2016-07-08 18:00","2016-07-08 09:00","2016-07-08 18:00","당일",null,null,null,201604220017]
[56,"대전충남","청양","보령C/C #4 M.Tr 1차 CB (7472)","보령복합 362kV GIS 보통점검","○ 345kV 7472 GIS 보통점검","2016-07-12 09:00","2016-07-12 18:00","2016-07-12 09:00","2016-07-12 18:00","당일",null,null,null,201604220018]
[57,"대전충남","청양","보령C/C 신보령연락T/L CB (7471)","보령복합 362kV GIS 보통점검","○ 345kV 7471 GIS 보통점검","2016-07-13 09:00","2016-07-13 18:00","2016-07-13 09:00","2016-07-13 18:00","당일",null,null,null,201604220016]
[58,"전북","군산","군산S/S #2 M.Tr A","군산S/S 345kV #2M.Tr","1. 345kV #2M.Tr 예비변압기 절체반 설치","2016-07-20 09:00","2016-07-21 18:00","2016-07-20 09:00","2016-07-21 18:00","연속",null,null,null,201605190003]
[59,"전북","군산","군산S/S #1 M.Tr A","군산S/S 345kV #1M.Tr","1. 345kV #1M.Tr 예비변압기 절체반 설치","2016-07-18 09:00","2016-07-19 18:00","2016-07-18 09:00","2016-07-19 18:00","연속",null,null,null,201605190002]
[60,"전북","군산","군산S/S 345kV #2 BUS","군산S/S 345k #2BUS","군산P/O 345kV 차단기 정밀점검 공사","2016-07-09 09:00","2016-07-10 18:00","2016-07-09 09:00","2016-07-10 18:00","연속",null,null,null,201605170172]
[61,"전북","군산","군산S/S #3 M.Tr A","군산S/S 345kV #3M.Tr","군산S/S 345kV 77Bay B/F반 대체","2016-07-04 09:00","2016-07-08 18:00","2016-07-04 09:00","2016-07-08 18:00","연속",null,null,null,201605110018]
[62,"전북","군산","군산새만금#1 T/L","군산S/S 345kV 군산-새만금#1T/L","군산S/S 345kV 77Bay B/F반 대체","2016-07-04 09:00","2016-07-08 18:00","2016-07-04 09:00","2016-07-08 18:00","연속",null,null,null,201605110017]
[63,"전북","군산","군산S/S 345kV #1 BUS","군산S/S 345k #1BUS","군산P/O 345kV 차단기 정밀점검 공사","2016-07-02 09:00","2016-07-03 18:00","2016-07-02 09:00","2016-07-03 18:00","연속",null,null,null,201605170168]
[64,"전북","군산","군산S/S #4 M.Tr A","군산S/S 345kV #4M.Tr","1. 345kV #4M.Tr 예비변압기 절체반 설치","2016-07-22 09:00","2016-07-23 18:00","2016-07-22 09:00","2016-07-23 18:00","연속",null,null,null,201605190006]
[65,"광주전남","강진","신화순신강진#2 T/L","345kV신화순-신강진#2T/L(신강진 7371 CB 보통점검)","2016~2017년도 강진전력지사 변전협력회사 총액공사 - 7. 4 : 신강진S/S 신화순-신강진#2T/L CB, PT A,B,C LA A,B,C 보통","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605200108]
[66,"광주전남","강진","신강진광양#2 T/L","345kV신강진-광양#2T/L(신강진7400,7471 CB 보통점검)","2016~2017년도 강진전력지사 변전협력회사 총액공사 - 7. 7 : 신강진S/S 7400 CB 보통점검 - 7. 8 : 신강진S/S 7471 CB 보통점검 신강진S/S 신강진-광양#1T/L PT A,B,C LA A,B,C 보통점검","2016-07-07 09:00","2016-07-08 18:00","2016-07-07 09:00","2016-07-08 18:00","당일",null,null,null,201605200105]
[67,"광주전남","강진","신강진광양#1 T/L","345kV신강진-광양#1T/L(신강진7300,7372 CB 보통점검)","2016~2017년도 강진전력지사 변전협력회사 총액공사 - 7. 5 : 신강진S/S 7300 CB 보통점검 - 7. 6 : 신강진S/S 7372 CB 보통점검, 신강진S/S 신강진-광양#1T/L PT A,B,C LA A,B,C 보통점검","2016-07-05 09:00","2016-07-06 18:00","2016-07-05 09:00","2016-07-06 18:00","당일",null,null,null,201605200104]
[68,"대구경북","달성","서대구고령#2 T/L","서대구-고령T/L 송전선로 정밀점검","서대구-고령 No.1-100호간 송전선로 정밀점검(100기)","2016-07-11 09:00","2016-07-15 18:00","2016-07-11 09:00","2016-07-15 18:00","연속",null,null,null,201605110207]
[69,"대구경북","달성","서대구고령#1 T/L","서대구-고령T/L 송전선로 정밀점검","서대구-고령 No.1-100호간 송전선로 정밀점검(100기)","2016-07-04 09:00","2016-07-08 18:00","2016-07-04 09:00","2016-07-08 18:00","연속",null,null,null,201605110205]
[70,"대구경북","달성","고령의령#1 T/L","안전확보휴전","서대구-고령 No.1-100호간 송전선로 정밀점검시 병가구간 안전확보","2016-07-11 09:00","2016-07-11 18:00","2016-07-11 09:00","2016-07-11 18:00","당일",null,null,null,201605110210]
[71,"대구경북","달성","고령의령#2 T/L","안전확보휴전","서대구-고령 No.1-100호간 송전선로 정밀점검시 병가구간 안전확보","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605110212]
[72,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","○ 송전선로 및 가공지선 신규 설치를 위한 안전이격 확보","2016-07-13 08:00","2016-07-23 18:00","2016-07-15 08:00","2016-07-19 18:00","연속",null,null,null,201604150057]
[73,"대구경북","영주","신영주안동CC T/L","신영주S/S 362kV GIS화 공사","○ 부하전환(옥외철구 → GIS) - 보호반 이설, 송전선로 인출 리드 연장, 옥외철구설비 철거","2016-07-13 08:00","2016-07-23 18:00","2016-07-13 08:00","2016-07-23 18:00","연속",null,null,null,201604150053,"○"]
[74,"대구경북","영주","신영주S/S #2 M.Tr A","신영주S/S 362kV GIS화 공사","○ 부하전환(옥외철구 → GIS) - 보호반 이설, 송전선로 인출 리드 연장, 옥외철구설비 철거","2016-07-13 08:00","2016-07-23 18:00","2016-07-13 08:00","2016-07-23 18:00","연속",null,null,null,201604150058]
[75,"대구경북","영주","신태백한울NP3 T/L","한울 3발 362kV GIS 대체공사","362kV GIS 용량부족 GIS(40kA-&gt50kA)12CB 대체공사 전담운영체계공사","2016-07-11 09:00","2016-07-14 18:00","2016-07-11 09:00","2016-07-14 18:00","당일",null,null,null,201605180015]
[76,"대구경북","포항","신월성N/P 월성연락#2T/L-#2SA.Tr 1차 CB (7200)","신월성N/P 362kV 차단기 정밀점검 공사","신월성N/P 7200, 7272 CB 정밀점검","2016-07-18 10:00","2016-07-22 18:00","2016-07-18 10:00","2016-07-22 18:00","연속",null,null,null,201605160084]
[77,"대구경북","포항","신월성N/P #2SA.Tr 1차 CB (7272)","신월성N/P 362kV 차단기 정밀점검 공사","신월성N/P 7200, 7272 CB 정밀점검","2016-07-18 10:00","2016-07-22 18:00","2016-07-18 10:00","2016-07-22 18:00","연속",null,null,null,201605160085]
[78,"대구경북","포항","월성연락#2 T/L","신월성N/P 월성연락 #2T/L 애자코팅작업","신월성N/P 월성연락 #2T/L 애자코팅작업","2016-07-13 10:00","2016-07-26 18:00","2016-07-13 10:00","2016-07-26 18:00","연속",null,null,null,201605160132]
[79,"대구경북","포항","신포항S/S 345kV #1 BUS","신포항S/S 345kV 7751 DS 점검","신포항S/S 7751 DS C상 불량에 따른 보수","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605230111]
[80,"부산울산","동부산","신울산고리NP#1 T/L","345kV 신울산-고리NP T/L 9~12호 지장철탑이설공사","○ 장안-온산1 국도건설공사에 지장이 되는 송전철탑 이설공사 ○ 이설철탑 : 본철탑 10호 및 가철탑 11호 설치(가선로 구성) ○ 9, 12호 애자장치 보강","2016-07-27 09:00","2016-08-09 18:00","2016-07-27 09:00","2016-08-09 18:00","연속",null,null,"신뢰도개선",201605230065]
[81,"부산울산","동부산","신울산고리NP#2 T/L","345kV 신울산-고리NP T/L 9~12호 지장철탑이설공사","○ 장안-온산1 국도건설공사에 지장이 되는 송전철탑 이설공사 ○ 이설철탑 : 본철탑 10호 및 가철탑 11호 설치(가선로 구성) ○ 9, 12호 애자장치 보강","2016-07-27 09:00","2016-08-09 18:00","2016-07-27 09:00","2016-08-09 18:00","연속",null,null,"신뢰도개선",201605230066]
[82,"부산울산","북부산","북부산신울산#2 T/L","16년 가공송전 협력업체 공사","81, 84호 지지애자 설치","2016-07-06 07:30","2016-07-06 18:00","2016-07-06 07:30","2016-07-06 18:00","연속",null,null,null,201605110077]
[83,"부산울산","북부산","북부산S/S #3 M.Tr A","북부산S/S 154kV 취약설비 GIS화공사","T-BUS 및 6348DS 철거","2016-07-07 09:00","2016-07-08 18:00","2016-07-07 09:00","2016-07-08 18:00","연속",null,null,null,201605100334]
[84,"부산울산","울산","동울산S/S 동울산-신울산#2T/L CB (7371)","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S 7371 GIS 하자점검","2016-07-11 09:00","2016-07-11 18:00","2016-07-11 09:00","2016-07-11 18:00","당일",null,null,null,201605100217]
[85,"부산울산","울산","동울산S/S 동울산-신울산#1T/L CB (7471)","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S 7471 GIS 하자점검","2016-07-13 09:00","2016-07-13 18:00","2016-07-13 09:00","2016-07-13 18:00","당일",null,null,null,201605100219,"○"]
[86,"부산울산","울산","동울산S/S 동울산-신울산#2T/L-TIE CB (7300)","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S 7300 GIS 하자점검","2016-07-12 09:00","2016-07-12 18:00","2016-07-12 09:00","2016-07-12 18:00","당일",null,null,null,201605100218]
[87,"부산울산","울산","동울산S/S #1 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S M.Tr 및 1, 2차 GIS 하자점검","2016-07-05 09:00","2016-07-06 18:00","2016-07-05 09:00","2016-07-06 18:00","연속",null,null,null,201605100222]
[88,"부산울산","울산","동울산S/S TIE-#3M.Tr 1차 CB (7400)","2016-17년 울산전력지사 변전협력회사 총액공사","동울산S/S 7400 GIS 하자점검","2016-07-14 09:00","2016-07-14 18:00","2016-07-14 09:00","2016-07-14 18:00","당일",null,null,null,201605100220]
[89,"부산울산","울산","울산C/C #5,6 G/T 1차 CB (7872)","2016-17년 울산전력지사 변전협력회사 총액공사","울산C/C 7872 GIS 하자점검","2016-07-01 09:00","2016-07-01 18:00","2016-07-01 09:00","2016-07-01 18:00","당일",null,null,null,201605100214]
[90,"부산울산","울산","울산C/C 4복합 #4S/T 1차-TIE CB (7A00)","2016-17년 울산전력지사 변전협력회사 총액공사","울산C/C 7A00 GIS 하자점검","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605100215]
[91,"부산울산","울산","울산C/C 4복합 #4S/T 1차 CB (7A72)","2016-17년 울산전력지사 변전협력회사 총액공사","울산C/C 7A72 GIS 하자점검","2016-07-07 09:00","2016-07-07 18:00","2016-07-07 09:00","2016-07-07 18:00","당일",null,null,null,201605100216]
[92,"경남","직할","신김해삼천포화력#2 T/L","345kV 신김해-삼천포화력#2T/L 점퍼선 불량개소 조치 시행","345kV 신김해-삼천포화력#2T/L 207호 등 점퍼선 불량개소 조치 시행","2016-07-03 08:00","2016-07-03 18:00","2016-07-03 08:00","2016-07-03 18:00","당일",null,null,"신뢰도개선",201605160062]
[93,"경남","진주","산청P/P 의령-산청PP#1T/L-#1 M.Tr 1차 CB (7100)","의령-산청PP#1T/L-#1M.Tr 1차(7100) 보통점검","의령-산청PP#1T/L-#1M.Tr 1차(7100) 보통점검","2016-07-05 09:00","2016-07-05 18:00","2016-07-05 09:00","2016-07-05 18:00","당일",null,null,null,201605120032]
[94,"경남","진주","산청P/P 의령-산청PP#1T/L-#2 M.Tr 1차 CB (7271)","의령-산청PP#1T/L-#2M.Tr 1차(7271) 보통점검","의령-산청PP#1T/L-#2M.Tr 1차(7271) 보통점검","2016-07-06 09:00","2016-07-06 18:00","2016-07-06 09:00","2016-07-06 18:00","당일",null,null,null,201605120033]
[95,"경남","진주","산청P/P 의령-산청PP#2T/L-#1 M.Tr 1차 CB (7172)","의령-산청PP#2T/L-#1M.Tr 1차(7172) 보통점검","의령-산청PP#2T/L-#1M.Tr 1차(7172) 보통점검","2016-07-07 09:00","2016-07-07 18:00","2016-07-07 09:00","2016-07-07 18:00","당일",null,null,null,201605120035]
[96,"경남","진주","산청P/P 의령-산청PP#2T/L-#2 M.Tr 1차 CB (7200)","의령-산청PP#2T/L-#2M.Tr 1차(7200) 보통점검","의령-산청PP#2T/L-#2M.Tr 1차(7200) 보통점검","2016-07-08 09:00","2016-07-08 18:00","2016-07-08 09:00","2016-07-08 18:00","당일",null,null,null,201605120037]
[97,"경남","진주","의령S/S 의령-산청양수#2T/L-#1M.Tr 1차 CB (7300)","유압조작기 메인밸브교체","유압조작기 메인밸브교체","2016-07-11 09:30","2016-07-11 18:30","2016-07-11 09:30","2016-07-11 18:30","당일",null,null,null,201605120044]
[98,"경남","진주","하동T/P #1 M.Tr 1차 CB (7172)","하동화력#1M.Tr 1차 GIS(7172) 보통점검","하동화력#1M.Tr 1차 GIS(7172) 보통점검","2016-07-01 09:00","2016-07-01 18:00","2016-07-01 09:00","2016-07-01 18:00","당일",null,null,null,201605120029]
[99,"경남","진주","하동T/P #4 M.Tr 1차 CB (7472)","하동화력 #4M.Tr 1차(7472) 보통점검","하동화력 #4M.Tr 1차(7472) 보통점검","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605120031]

{"sheet":"154송부","index":2,"n_rows":143,"n_cols":16,"rows_kept":143,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 7월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구리신내#1 T/L","16년 성동P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검 (신내S/S 구리신내#1T/L)","2016-07-06 08:00","2016-07-08 20:00","2016-07-06 08:00","2016-07-08 20:00","연속",null,null,null,201604190146]
[2,"서울","직할","서소문S/S 154kV #2 BUS","서소문S/S 170kV GIS 대체공사_3차","서소문S/S 170kV GIS 대체공사 (서소문서대문#1 T/L, #1M.Tr 1차)","2016-07-11 10:00","2016-07-21 18:00","2016-07-11 10:00","2016-07-21 18:00","연속",null,null,null,201605170095]
[3,"서울","직할","서소문S/S 154kV #2 BUS","서소문S/S 170kV GIS 대체공사_5차","서소문S/S 170kV GIS 대체공사 (서소문서대문#1T/L, #1M.Tr 1차)","2016-07-01 09:00","2016-07-02 09:00","2016-07-01 09:00","2016-07-02 09:00","연속",null,null,null,201605170093]
[4,"서울","직할","서소문서대문#1 T/L","서소문S/S 170kV GIS 대체공사","서소문S/S 170kV GIS 대체공사 (서소문서대문#1 T/L, #1M.Tr 1차)","2016-07-01 09:00","2016-07-21 09:00","2016-07-01 09:00","2016-07-21 09:00","연속",null,null,null,201605170099]
[5,"서울","직할","서소문S/S 154kV #1 BUS","서소문S/S 170kV GIS 대체공사_4차","서소문S/S 170kV GIS 대체공사 (서소문서대문#1 T/L, #1M.Tr 1차)","2016-07-02 09:00","2016-07-11 09:00","2016-07-02 09:00","2016-07-11 09:00","연속",null,null,null,201605170094]
[6,"인천","김포","경서S/S 154kV #1 BUS","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(2차) - 154kV #2M.Tr 1차 GIS 1CCT","2016-07-01 08:00","2016-07-06 08:00","2016-07-01 08:00","2016-07-06 08:00","연속",null,null,null,201604150017]
[7,"인천","김포","경서S/S 154kV #1 BUS","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(2차) - 154kV #2M.Tr 1차 GIS 1CCT","2016-07-10 11:00","2016-07-10 18:00","2016-07-10 11:00","2016-07-10 18:00","연속",null,null,null,201606020025]
[8,"인천","김포","경서S/S 154kV #2 BUS","경서S/S 170kV 장기사용 GIS 대체공사","경서S/S 170kV 장기사용 GIS 대체공사(2차) - 154kV #2M.Tr 1차 GIS 1CCT","2016-07-06 08:00","2016-07-10 11:00","2016-07-06 08:00","2016-07-10 11:00","연속",null,null,null,201604150018]
[9,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","2016-07-04 09:30","2016-07-05 14:00","2016-07-04 09:30","2016-07-05 14:00","연속",null,null,null,201605120133]
[10,"인천","시흥","신시흥#1S/S 154kV #61 BUS","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","2016-07-05 14:00","2016-07-06 18:00","2016-07-05 14:00","2016-07-06 18:00","연속",null,null,null,201605120135]
[11,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥/S/S 신시흥남동#2T/L GIS 정밀점검","신시흥/S/S 신시흥남동#2T/L GIS 정밀점검","2016-07-01 14:00","2016-07-02 18:00","2016-07-01 14:00","2016-07-02 18:00","연속",null,null,null,201604120361]
[12,"인천","시흥","신시흥#1S/S 154kV #2 BUS TIE GIS","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","신시흥#1S/S 154kV #2 BUS TIE GIS 정밀점검공사","2016-07-04 09:30","2016-07-06 18:00","2016-07-04 09:30","2016-07-06 18:00","연속",null,null,null,201605120131]
[13,"인천","시흥","북송도연수#2 T/L","154kV 북송도-연수#2 T/L 케이블 및 관로 복구공사","연수EBG~J/B#1 구간 B상 케이블 및 관로 교체","2016-07-29 09:30","2016-08-05 18:00","2016-07-29 09:30","2016-08-05 18:00","연속",null,null,null,201605110010]
[14,"인천","시흥","북송도연수#1 T/L","154kV 북송도-연수#1 T/L 케이블 및 관로 복구공사","연수EBG~J/B#1 구간 A,B,C상 케이블 및 관로 교체","2016-07-18 09:30","2016-07-28 18:00","2016-07-18 09:30","2016-07-28 18:00","연속",null,null,null,201605110008]
[15,"인천","시흥","오봉S/S 154kV #2 BUS","오봉S/S 154kV 오봉가스공사T/L GIS 정밀점검","오봉S/S 154kV 오봉가스공사T/L GIS 정밀점검","2016-07-07 09:30","2016-07-08 14:00","2016-07-07 09:30","2016-07-08 14:00","연속",null,null,null,201605120137]
[16,"인천","시흥","오봉S/S 154kV #1 BUS","오봉S/S 154kV 오봉가스공사T/L GIS 정밀점검","오봉S/S 154kV 오봉가스공사T/L GIS 정밀점검","2016-07-08 14:00","2016-07-09 18:00","2016-07-08 14:00","2016-07-09 18:00","연속",null,null,null,201605120138]
[17,"인천","인천","관교만수 T/L","154kV 관교-만수 T/L 접지선 교체공사","접지선 기준개정 관련 구형 접지선 교체","2016-07-09 09:00","2016-07-09 18:00","2016-07-09 09:00","2016-07-09 18:00","당일",null,null,null,201605130154]
[18,"인천","인천","남인천학익#1 T/L","154kV 남인천-학익 #1T/L 접지선 교체공사","접지선 기준개정 관련 구형 접지선 교체","2016-07-12 09:00","2016-07-13 18:00","2016-07-12 09:00","2016-07-13 18:00","연속",null,null,null,201605130151]
[19,"인천","인천","남인천학익#2 T/L","154kV 남인천-학익 #2T/L 접지선 교체공사","접지선 기준개정 관련 구형 접지선 교체","2016-07-14 09:00","2016-07-15 18:00","2016-07-14 09:00","2016-07-15 18:00","연속",null,null,null,201605130152]
[20,"인천","인천","신가좌인천#3 T/L","154kV 신가좌-인천 #3T/L 접지선 교체공사","접지선 기준개정 관련 구형 접지선 교체","2016-07-31 09:00","2016-08-01 18:00","2016-07-31 09:00","2016-08-01 18:00","연속",null,null,null,201605130157]
[21,"인천","인천","신가좌신현#2 T/L","154kV 신가좌-신현#2T/L SVL 교체공사","케이블 접속함에 설치된 구형 SVL (난연성 미확보) 제품을 현 규격품으로 교체","2016-07-25 09:30","2016-07-30 18:00","2016-07-25 09:30","2016-07-30 18:00","연속",null,null,null,201605110006]
[22,"인천","인천","신가좌신현#1 T/L","154kV 신가좌-신현#1T/L SVL 교체공사","케이블 접속함에 설치된 구형 SVL (난연성 미확보) 제품을 현 규격품으로 교체","2016-07-19 09:30","2016-07-24 18:00","2016-07-19 09:30","2016-07-24 18:00","연속",null,null,null,201605110005]
[23,"인천","인천","원창S/S 154kV #2 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 원창포스코CC#1T/L GIS 정밀점검","2016-07-12 10:00","2016-07-12 22:00","2016-07-12 10:00","2016-07-12 22:00","당일",null,null,null,201605090014]
[24,"인천","인천","원창S/S 154kV #2 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 원창포스코CC#2T/L GIS 정밀점검","2016-07-14 10:00","2016-07-14 22:00","2016-07-14 10:00","2016-07-14 22:00","당일",null,null,null,201605090017]
[25,"인천","인천","원창S/S 154kV #1 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 원창포스코CC#1T/L GIS 정밀점검","2016-07-11 08:00","2016-07-12 10:00","2016-07-11 08:00","2016-07-12 10:00","연속",null,null,null,201605090013]
[26,"인천","인천","원창S/S 154kV #1 BUS","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 원창포스코CC#2T/L GIS 정밀점검","2016-07-13 08:00","2016-07-14 10:00","2016-07-13 08:00","2016-07-14 10:00","연속",null,null,null,201605090016]
[27,"인천","인천","원창포스코CC#2 T/L","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 원창포스코CC#2T/L GIS 정밀점검","2016-07-13 08:00","2016-07-14 22:00","2016-07-13 08:00","2016-07-14 22:00","연속",null,null,null,201605090015]
[28,"인천","인천","원창포스코CC#1 T/L","2016년 인천전력지사 170kV GIS 정밀점검 공사","원창S/S 170kV 원창포스코CC#1T/L GIS 정밀점검","2016-07-11 08:00","2016-07-12 22:00","2016-07-11 08:00","2016-07-12 22:00","연속",null,null,null,201605090012]
[29,"인천","인천","학익연수#2 T/L","154kV 학익-연수 T/L 접지선 교체공사","접지선 기준개정 관련 구형 접지선 교체","2016-07-11 09:00","2016-07-11 19:00","2016-07-11 09:00","2016-07-11 19:00","당일",null,null,null,201605130148]
[30,"인천","인천","학익연수#1 T/L","154kV 학익-연수 T/L 접지선 교체공사","접지선 기준개정 관련 구형 접지선 교체","2016-07-10 09:00","2016-07-10 19:00","2016-07-10 09:00","2016-07-10 19:00","당일",null,null,null,201605130147]
[31,"인천","직할","신가좌부개#2 T/L","신가좌-부개#2T/L 보호반 대체공사","신가좌-부개#2T/L 보호반 대체공사","2016-07-04 09:00","2016-07-08 18:00","2016-07-04 09:00","2016-07-08 18:00","연속",null,null,null,201605170054]
[32,"인천","직할","신부평중동#3 T/L","신부평-중동#3T/L 보호반 대체공사","신부평-중동#3T/L 보호반 대체공사","2016-07-11 09:30","2016-07-15 18:00","2016-07-11 09:30","2016-07-15 18:00","연속",null,null,null,201605190056]
[33,"경기북부","구리","덕소별내#1 T/L","154kV 덕소-별내T/L 지장철탑이설공사","구리갈매지구 지장철탑이설공사 - 철탑도장(No.30)","2016-07-04 08:00","2016-07-05 12:00","2016-07-04 08:00","2016-07-05 12:00","연속",null,null,null,201605160303,"○"]
[34,"경기북부","구리","덕소별내#2 T/L","154kV 덕소-별내T/L 지장철탑이설공사","구리갈매지구 지장철탑이설공사 - 철탑도장(No.30)","2016-07-05 12:00","2016-07-06 18:00","2016-07-05 12:00","2016-07-06 18:00","연속",null,null,null,201605160304,"○"]
[35,"경기북부","직할","신포천동두천#2 T/L","신포천동두천#2 T/L","2016년 직할 변전협력회사 총액공사 - SA 시범사업 철거","2016-07-04 10:00","2016-07-08 18:00","2016-07-04 10:00","2016-07-08 18:00","연속",null,null,null,201605130142]
[36,"경기북부","직할","백석덕계#2 T/L","백석-덕계#1,2T/L 정밀점검","- No.1~9 백석덕계 #1,2T/L 정밀점검 - 4회선 수평배열로 인한 작업안전거리 확보불가로 #1,2T/L 동시휴전","2016-07-07 08:00","2016-07-07 18:00","2016-07-07 08:00","2016-07-07 18:00","당일",null,null,null,201605170053]
[37,"경기북부","직할","백석덕계#1 T/L","백석-덕계#1,2T/L 정밀점검","- No.1~9 백석덕계 #1,2T/L 정밀점검 - 4회선 수평배열로 인한 작업안전거리 확보불가로 #1,2T/L 동시휴전","2016-07-07 08:00","2016-07-07 18:00","2016-07-07 08:00","2016-07-07 18:00","당일",null,null,null,201605170052]
[38,"경기북부","파주","지도능곡#2 T/L","지도-능곡#2T/L 구형 SVL 교체 공사 J/B 6개소","지도-능곡#2T/L 구형 SVL 교체 공사(J/B5,6,8,9,11,12)","2016-07-04 09:00","2016-07-08 18:00","2016-07-04 09:00","2016-07-08 18:00","연속",null,null,null,201605130016]
[39,"경기북부","파주","일산S/S 154kV #61 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S #61-66BUS PT Bay 교체","2016-07-04 08:00","2016-07-05 18:00","2016-07-04 08:00","2016-07-05 18:00","연속",null,null,null,201605120018]
[40,"경기북부","파주","일산S/S 154kV #66 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","일산S/S #61-66BUS PT Bay 교체","2016-07-06 08:00","2016-07-09 18:00","2016-07-06 08:00","2016-07-09 18:00","연속",null,null,null,201605120016]
[41,"경기북부","파주","일산S/S 154kV #61 BUS","일산S/S 60-61BUS-SEC GIS 정밀점검공사","일산S/S 60-61BUS-SEC #2DS GIS 정밀점검","2016-07-01 12:00","2016-07-02 18:00","2016-07-01 12:00","2016-07-02 18:00","연속",null,null,null,201604190174]
[42,"경기북부","파주","일산지도#2 T/L","고양시 국도대체우회도로 지장철탑이설공사(일산-지도T/L)","철탑 설치 : 2기 철탑 철거 : 2기","2016-07-07 07:00","2016-07-11 18:00","2016-07-07 07:00","2016-07-11 18:00","연속",null,null,null,201605200075]
[43,"경기북부","파주","일산지도#1 T/L","고양시 국도대체우회도로 지장철탑이설공사(일산-지도T/L)","철탑 설치 : 2기 철탑 철거 : 2기","2016-07-12 07:00","2016-07-16 18:00","2016-07-12 07:00","2016-07-16 18:00","연속",null,null,null,201605200076]
[44,"경기","군포","서서울산본#1 T/L","154kV 시화,산본S/S 장기사용 GIS 대체공사","산본S/S 산본안양#2, 서서울산본#1T/L GIS 대체","2016-07-07 08:00","2016-07-08 18:00","2016-07-07 08:00","2016-07-08 18:00","연속",null,null,"신뢰도개선",201605110156]
[45,"경기","군포","산본안양#2 T/L","154kV 시화,산본S/S 장기사용 GIS 대체공사","산본S/S 산본안양#2, 서서울산본#1T/L GIS 대체","2016-07-04 08:00","2016-07-15 18:00","2016-07-04 08:00","2016-07-15 18:00","연속",null,null,"신뢰도개선",201605110157]
[46,"경기","군포","산본안양#2 T/L","154kV 시화,산본S/S 장기사용 GIS 대체공사","산본 154kV #1Bus 휴전 - 서서울산본#1TL 무부하가압","2016-07-01 08:00","2016-07-03 18:00","2016-07-01 08:00","2016-07-03 18:00","연속",null,null,null,201605240135]
[47,"경기","군포","서서울산본#1 T/L","154kV 시화,산본S/S 장기사용 GIS 대체공사","산본S/S 산본안양#2T/L GIS로 선로 무부하 가압 시행","2016-07-13 08:00","2016-07-15 18:00","2016-07-13 08:00","2016-07-15 18:00","연속",null,null,null,201605120315]
[48,"경기","군포","시화성곡 T/L","시화, 성곡S/S 시화성곡T/L 보호배전반 대체공사","시화, 성곡S/S 시화성곡T/L 보호배전반 대체공사","2016-07-04 09:00","2016-07-06 18:00","2016-07-04 09:00","2016-07-06 18:00","연속",null,null,null,201605230129]
[49,"경기","군포","조암구문천#1 T/L","154kV 조암구문천#1T/L 송전선로 정밀점검(구간 No.10~20)","16년 가공송전선로 순시점검 위탁공사 154kV 조암구문천#1T/L 송전선로 정밀점검(구간 No.10~20)","2016-07-02 09:00","2016-07-02 18:00","2016-07-02 09:00","2016-07-02 18:00","당일",null,null,null,201605110023]
[50,"경기","동부","성현분당#2 T/L","동부전력 170kV GIS 정밀점검","분당S/S 170kV 성현-분당#2T/L GIS 정밀점검","2016-07-01 09:00","2016-07-03 18:00","2016-07-01 09:00","2016-07-03 18:00","연속",null,null,null,201605110073]
[51,"경기","성남","신용인용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식","2016-07-05 09:00","2016-07-06 18:00","2016-07-05 09:00","2016-07-06 18:00","연속",null,null,null,201605120263]
[52,"경기","성남","신용인용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식","2016-07-02 09:00","2016-07-03 18:00","2016-07-02 09:00","2016-07-03 18:00","연속",null,null,null,201605120257]
[53,"경기","성남","모현용인#2 T/L","154kV 용인S/S 무인화대비 설비보강공사","○ GIS(170kV 1250/2000A 50kA 17CCT, P.T 포함) 설치 × 1식","2016-07-07 09:00","2016-07-15 18:00","2016-07-07 09:00","2016-07-15 18:00","연속",null,null,"신뢰도개선",201605120266]
[54,"경기","직할","발안향남#2 T/L","발안변전소 누수 보수공사","건물배면 창호, 유리코킹 보수 (T/L 월부싱 인근)","2016-07-05 09:00","2016-07-05 18:00","2016-07-05 09:00","2016-07-05 18:00","당일",null,null,null,201605130146]
[55,"경기","직할","발안향남#1 T/L","발안변전소 누수 보수공사","건물배면 창호, 유리코킹 보수 (T/L 월부싱 인근)","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605130143]
[56,"경기","직할","화성S/S 65-66 SEC GIS","화성S/S 65-66 SEC GIS","화성S/S 65-66 SEC GIS 트립와이어 설치 및 전자변 히터설치","2016-07-13 10:00","2016-07-13 14:00","2016-07-13 10:00","2016-07-13 14:00","당일",null,null,null,201605090170]
[57,"경기","직할","화성S/S 66-67 SEC GIS","화성S/S 66-67 SEC GIS","화성S/S 66-67 SEC GIS 트립와이어 설치 및 전자변 히터설치","2016-07-13 14:00","2016-07-13 18:00","2016-07-13 14:00","2016-07-13 18:00","당일",null,null,null,201605090171]
[58,"경기","직할","화성S/S 60-61 SEC GIS","화성S/S 60-61 SEC GIS","화성S/S 60-61 SEC GIS 트립와이어 설치 및 전자변 히터설치","2016-07-12 10:00","2016-07-12 14:00","2016-07-12 10:00","2016-07-12 14:00","당일",null,null,null,201605090166]
[59,"경기","직할","화성S/S 61-62 SEC GIS","화성S/S 61-62 SEC GIS","화성S/S 61-62 SEC GIS 트립와이어 설치 및 전자변 히터설치","2016-07-12 14:00","2016-07-12 18:00","2016-07-12 14:00","2016-07-12 18:00","당일",null,null,null,201605090168]
[60,"경기","직할","화성발안#2 T/L","화성S/S 154kV 화성발안#2T/L","화성S/S 154kV 화성발안#2T/L GIS 트립와이어 설치 및 전자변 히터설치","2016-07-09 14:00","2016-07-09 18:00","2016-07-09 14:00","2016-07-09 18:00","당일",null,null,null,201605090150]
[61,"경기","직할","화성발안#1 T/L","화성S/S 154kV 화성발안#1T/L","화성S/S 154kV 화성발안#1T/L GIS 트립와이어 설치 및 전자변 히터설치","2016-07-09 10:00","2016-07-09 14:00","2016-07-09 10:00","2016-07-09 14:00","당일",null,null,null,201605090148]
[62,"경기","평택","평택오성CC#1 T/L","154kV평택오성CC 등 2개 T/L 지장철탑이설공사(구간 No.2~5)","○ 구간 : 154kV 평택오성CCT/L No.2~No.5호 ○ 선로길이 : 4C, 0.995 km ○ 지지물 : 4회선 2기 ○ 전력선 : ACSR 410㎟ × 2B x 4C ○ 가공지선 : ACSR 97㎟ × 1조, OPGW 100㎟ × 1조","2016-07-13 07:00","2016-07-17 18:00","2016-07-13 07:00","2016-07-17 18:00","연속",null,null,"신뢰도개선",201605160165]
[63,"경기","평택","송탄오성CC#2 T/L","154kV평택오성CC 등 2개 T/L 지장철탑이설공사(구간 No.2~5)","○ 구간 : 154kV 평택오성CCT/L No.2~No.5호 ○ 선로길이 : 4C, 0.995 km ○ 지지물 : 4회선 2기 ○ 전력선 : ACSR 410㎟ × 2B x 4C ○ 가공지선 : ACSR 97㎟ × 1조, OPGW 100㎟ × 1조","2016-07-13 07:00","2016-07-17 18:00","2016-07-13 07:00","2016-07-17 18:00","연속",null,null,"신뢰도개선",201605160164]
[64,"경기","평택","평택오성CC#2 T/L","154kV평택오성CC 등 2개 T/L 지장철탑이설공사(구간 No.2~5)","○ 구간 : 154kV 평택오성CCT/L No.2~No.5호 ○ 선로길이 : 4C, 0.995 km ○ 지지물 : 4회선 2기 ○ 전력선 : ACSR 410㎟ × 2B x 4C ○ 가공지선 : ACSR 97㎟ × 1조, OPGW 100㎟ × 1조","2016-07-08 07:00","2016-07-12 18:00","2016-07-08 07:00","2016-07-12 18:00","연속",null,null,"신뢰도개선",201605160163]
[65,"경기","평택","송탄오성CC#1 T/L","154kV평택오성CC 등 2개 T/L 지장철탑이설공사(구간 No.2~5)","○ 구간 : 154kV 평택오성CCT/L No.2~No.5호 ○ 선로길이 : 4C, 0.995 km ○ 지지물 : 4회선 2기 ○ 전력선 : ACSR 410㎟ × 2B x 4C ○ 가공지선 : ACSR 97㎟ × 1조, OPGW 100㎟ × 1조","2016-07-08 07:00","2016-07-12 18:00","2016-07-08 07:00","2016-07-12 18:00","연속",null,null,"신뢰도개선",201605160162,"○"]
[66,"경기","평택","평택추팔#1 T/L","154kV 추팔S/S #4M.Tr 증설공사","M.Tr(15/20MVA*3)*1BANK 설치 154kV GIS 1CCT 설치 23kV GIS 3CCT 설치(GIB*5포함)","2016-07-01 16:00","2016-07-04 10:00","2016-07-01 16:00","2016-07-04 10:00","연속",null,null,null,201604150350]
[67,"강원","원주","원주문막#1 T/L","154kV 서원주S/S 건설공사","154kV 원주-문막#1T/L 보호배전반 철거 154kV 원주-서원주#1T/L 보호배전반 설치 및 준공시험 154kV 서원주분기T/L 건설","2016-07-04 09:00","2016-07-11 18:00","2016-07-04 09:00","2016-07-11 18:00","연속",null,null,null,201604150072]
[68,"강원","직할","남춘천청평PP T/L","춘천집단에너지 154kV 송전선로 건설공사","청평양수#3,4T/L 71호 철거, 가철탑 71호 신설","2016-07-05 09:00","2016-07-12 18:00","2016-07-05 09:00","2016-07-12 18:00","연속",null,null,null,201605100209]
[69,"강원","직할","남춘천서홍천 T/L","춘천집단에너지 154kV 송전선로 건설공사","청평양수#3,4T/L 71호 철거, 가철탑 71호 신설","2016-07-13 09:00","2016-07-18 18:00","2016-07-13 09:00","2016-07-18 18:00","연속",null,null,null,201605100210]
[70,"강원","직할","남춘천춘천 T/L","춘천S/S 170kV GIS 설치공사","- 송전선로 인출변경 - GIS 설치 및 초기가압 - 송전선로 보호배전반 설치","2016-07-13 08:00","2016-07-18 18:00","2016-07-13 08:00","2016-07-18 18:00","연속",null,null,null,201605020034]
[71,"충북","직할","왕암가남#2 T/L","변전설비 취약개소 설비보강","154kV 왕암가남#2T/L 유압실린더 연결부 볼트파손 제작사 수리(LS산전)","2016-07-16 09:00","2016-07-16 18:00","2016-07-16 09:00","2016-07-16 18:00","당일",null,null,null,201604100067]
[72,"충북","직할","음성금왕#1 T/L","154kV 효성제 GIS 제작사 하자 점검","154kV 음성금왕#1T/L GIS 제작사 하자 점검(효성)","2016-07-15 10:00","2016-07-15 18:00","2016-07-15 10:00","2016-07-15 18:00","당일",null,null,null,201604100066,"○"]
[73,"충북","청주","상주보은 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","전력선교체 - 상주TL No.61~64, 75~79 보은분기TL No.6~9, 10~11, 12~13, 27~28,","2016-07-01 08:00","2016-07-05 19:00","2016-07-01 08:00","2016-07-05 19:00","연속",null,null,null,201604080150]
[74,"충북","청주","신옥천서대전#2 T/L","16년 청주 변전협력회사 총액공사","신옥천S/S 신옥천-서대전#2 T/L #2BUS DS(602) 과열개소 보수","2016-07-01 10:00","2016-07-01 18:00","취소","취소","당일",null,null,null,201605160150]
[75,"충북","충주","금왕남음성#2 T/L","2016년 충주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 금왕-남음성 #2T/L 정밀점검","2016-07-06 09:00","2016-07-07 18:00","2016-07-06 09:00","2016-07-07 18:00","매일",null,null,null,201605160308,"○"]
[76,"충북","충주","금왕남음성#1 T/L","2016년 충주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 금왕-남음성 #1T/L 정밀점검","2016-07-04 09:00","2016-07-05 18:00","2016-07-04 09:00","2016-07-05 18:00","매일",null,null,null,201605160307,"○"]
[77,"충북","충주","남음성덕산#2 T/L","2016년 충주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 남음성-덕산 #2T/L 정밀점검","2016-07-13 09:00","2016-07-14 18:00","2016-07-13 09:00","2016-07-14 18:00","매일",null,null,null,201605160311,"○"]
[78,"충북","충주","남음성덕산#1 T/L","2016년 충주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 남음성-덕산 #1T/L 정밀점검","2016-07-11 09:00","2016-07-12 18:00","2016-07-11 09:00","2016-07-12 18:00","매일",null,null,null,201605160310,"○"]
[79,"충북","충주","신진천S/S 154kV #61 BUS","지반침하에 따른 모선 정밀점검","지반침하에 따른 모선(#61,62,66,67) 정밀점검","2016-07-01 09:00","2016-07-07 18:00","2016-07-01 09:00","2016-07-07 18:00","연속",null,null,null,201605170115]
[80,"충북","충주","신진천S/S 154kV #67 BUS","지반침하에 따른 모선 정밀점검","지반침하에 따른 모선(#61,62,66,67) 정밀점검","2016-07-08 09:00","2016-07-14 18:00","2016-07-08 09:00","2016-07-14 18:00","연속",null,null,null,201605170118]
[81,"충북","충주","신진천S/S 154kV #66 BUS","지반침하에 따른 모선 정밀점검","지반침하에 따른 모선(#61,62,66,67) 정밀점검","2016-07-08 09:00","2016-07-14 18:00","2016-07-08 09:00","2016-07-14 18:00","연속",null,null,null,201605170117]
[82,"대전충남","서산","송악GSEPS#1 T/L","송악S/S 154kV GSEPS#1T/L 정밀점검","○ 154kV GIS 정밀점검(GSEPS#1T/L)","2016-07-05 09:00","2016-07-07 18:00","2016-07-05 09:00","2016-07-07 18:00","연속",null,null,null,201605110262]
[83,"대전충남","서산","서산태안 T/L","태안S/S 154kV 서산태안T/L 보통점검","○ 태안S/S 154kV 서산태안T/L 보통점검 ○ LA 보통점검","2016-07-01 09:00","2016-07-01 18:00","2016-07-01 09:00","2016-07-01 18:00","당일",null,null,null,201605110246]
[84,"대전충남","서산","서산태안화력 T/L","태안T/P 154kV GIS 초기점검","○154kV 서산태안화력T/L 초기점검 ○ LA 및 CVT 보통점검","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605110292]
[85,"대전충남","세종","부강월산#2 T/L","[변전] 세종P/O 변전협력회사 총액공사","○ LA초기점검","2016-07-04 09:30","2016-07-04 18:00","2016-07-04 09:30","2016-07-04 18:00","당일",null,null,null,201605100178]
[86,"대전충남","세종","천안전의#2 T/L","[변전] 세종P/O 변전협력회사 총액공사","○ 천안-전의#2T/L GIS보통점검","2016-07-11 09:30","2016-07-11 18:00","2016-07-11 09:30","2016-07-11 18:00","당일",null,null,null,201605100180]
[87,"대전충남","청양","청양신풍#2 T/L","관내S/S 차단기 부동작 예방 조작시험","○ 신풍S/S 154kV CB 부동작 예방 조작시험","2016-07-14 10:00","2016-07-14 12:00","2016-07-14 10:00","2016-07-14 12:00","당일",null,null,null,201604260152]
[88,"전북","군산","군공군산CC#2 T/L","154kV군공-군산복합T/L 지중선로 이설공사","154kV 군공-군산복합T/L M/H#10~12번 구간 군장대고 건설관련 지장이설 신청으로 선로 이설","2016-07-25 09:00","2016-08-14 18:00","취소","취소","연속",null,null,null,201604140079]
[89,"전북","군산","군산S/S 61-62-0 SEC CB","군산S/S 154kV 61-62-0 SEC CB","군산S/S 154kV 62-67 모선보호반 대체","2016-07-25 09:00","2016-07-29 18:00","2016-07-25 09:00","2016-07-29 18:00","연속",null,null,null,201605100233]
[90,"전북","군산","군산영등#2 T/L","군산영등#2 T/L 피뢰기설치 공사","피뢰기설치 56기","2016-07-04 07:00","2016-07-07 18:00","2016-07-04 07:00","2016-07-08 18:00","매일",null,null,null,201605240163]
[91,"전북","군산","군산S/S 66-67-0 SEC CB","군산S/S 154kV 66-67-0 SEC CB","군산S/S 154kV 62-67 모선보호반 대체","2016-07-25 09:00","2016-07-29 18:00","2016-07-25 09:00","2016-07-29 18:00","연속",null,null,null,201605110019]
[92,"전북","군산","군산S/S 154kV #3 BUS TIE CB","군산S/S 154kV #3 BUSTIE CB","군산S/S 154kV 62-67 모선보호반 대체","2016-07-25 09:00","2016-07-29 18:00","2016-07-25 09:00","2016-07-29 18:00","연속",null,null,null,201605110020]
[93,"전북","군산","동군산장항#2 T/L","동군산장항#2 T/L 피뢰기설치 공사","피뢰기설치 13기","2016-07-15 07:00","2016-07-16 18:00","2016-07-16 07:00","2016-07-17 18:00","매일",null,null,null,201605240168]
[94,"전북","군산","팔봉영등#2 T/L","팔봉영등#2 T/L 피뢰기설치 공사","피뢰기설치 14기","2016-07-13 07:00","2016-07-14 18:00","취소","취소","매일",null,null,"신뢰도개선",201605240167]
[95,"전북","김제","고창홍농 T/L","고창홍농 T/L","차단기 유압조작기 점검(누유)","2016-07-01 10:00","2016-07-01 12:00","취소","취소","당일",null,null,null,201605200177]
[96,"전북","김제","신김제정공#1 T/L","신김제정공#1 T/L","송전선로 보호반 교체","2016-07-04 09:00","2016-07-07 18:00","2016-07-04 09:00","2016-07-07 18:00","연속",null,null,null,201605170206]
[97,"광주전남","광주","신광주일곡#1 T/L","154kV 신광주-일곡T/L 지중화공사","154kV 신광주-일곡T/L No.4~5 지중화공사 케이블헤드 2기 신설, 철탑2기 철거, 지중화 533m","2016-07-11 09:00","2016-08-05 18:00","취소","취소","연속",null,null,"신뢰도개선",201605250029]
[98,"광주전남","목포","장성영광#1 T/L","장성-영광T/L 146-150호간 OPGW 교체공사","154kV 장성-영광#1T/L No.146-150호 OPGW 교체 : 2.1km","2016-07-09 08:00","2016-07-10 18:00","취소","취소","연속",null,null,"신뢰도개선",201605240102]
[99,"광주전남","목포","영광홍농 T/L","장성-영광T/L 146-150호간 OPGW 교체공사","154kV 장성-영광#1T/L No.146-150호 OPGW 교체 : 2.1km - 하단 영광-홍농T/L 안전이격 확보","2016-07-09 08:00","2016-07-10 18:00","취소","취소","연속",null,null,"신뢰도개선",201605240107]
[100,"광주전남","순천","광양순천#2 T/L","154kV 광양T/L C/H 건설공사","철탑 : 1기(C/H) 전력선 : 0.5km","2016-07-25 07:00","2016-07-25 18:00","2016-07-25 07:00","2016-07-25 18:00","당일",null,null,null,201605230136]
[101,"광주전남","순천","광양순천#2 T/L","154kV 광양T/L C/H 건설공사","철탑 : 1기(C/H) 전력선 : 0.5km","2016-07-29 07:00","2016-07-29 18:00","2016-07-29 07:00","2016-07-29 18:00","당일",null,null,null,201605230137]
[102,"광주전남","순천","광양순천#1 T/L","154kV 광양T/L C/H 건설공사","철탑 : 1기(C/H) 전력선 : 0.5km","2016-07-26 07:00","2016-07-28 18:00","2016-07-26 07:00","2016-07-28 18:00","연속",null,null,null,201605230138]
[103,"광주전남","순천","여수TP화치#2 T/L","154kV 화치S/S 금호미쓰이화학T/L 신규수용공사","#65BUS측 모선 및 DS 증설구간 여수TP-화치#2T/L을 통한 48시간 무부하가압","2016-07-01 15:00","2016-07-03 15:00","2016-07-01 15:00","2016-07-03 15:00","연속",null,null,null,201605270009]
[104,"광주전남","순천","여수TP화치#2 T/L","154kV 화치S/S 금호미쓰이화학T/L 신규수용공사","#60BUS측 모선, DS, CB, C/H 챔버 증설구간 여수TP-화치#2T/L을 통한 48시간 무부하가압","2016-07-06 15:00","2016-07-08 15:00","2016-07-06 15:00","2016-07-08 15:00","연속",null,null,null,201605270010]
[105,"대구경북","경산","신경산아화#1 T/L","154kV 금호변전소 건설공사","신경산-아화T/L 분기철탑 점퍼선 분리(송전) 신경산-아화T/L 송전선로 보호반 교체(변전)","2016-07-26 09:00","2016-07-29 18:00","2016-07-26 09:00","2016-07-29 18:00","연속",null,null,null,201605130010]
[106,"대구경북","경산","신경산아화#2 T/L","154kV 금호변전소 건설공사","신경산-아화T/L 분기철탑 점퍼선 분리(송전) 신경산-아화T/L 송전선로 보호반 교체(변전)","2016-07-26 09:00","2016-07-29 18:00","2016-07-26 09:00","2016-07-29 18:00","연속",null,null,null,201605130011]
[107,"대구경북","경산","안심대구그린파워#2 T/L","안심-신서열병합#2T/L 초기점검","1. 신서S/Y측 안심-신서열병합#2T/L 초기점검 2. 안심S/S측 안심-신서열병합#2T/L 초기점검","2016-07-05 09:00","2016-07-05 18:00","2016-07-05 09:00","2016-07-05 18:00","당일",null,null,null,201605090122]
[108,"대구경북","경산","안심대구그린파워#1 T/L","안심-신서열병합#1T/L 초기점검","1. 신서S/Y측 안심-신서열병합#1T/L 초기점검 2. 안심S/S측 안심-신서열병합#1T/L 초기점검","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605090120]
[109,"대구경북","구미","청리상주#1 T/L","154kV 청리-상주 등 6개T/L 송전선로용 피뢰기 설치공사","154kV 청리-상주#2T/L No.61~63, 69~72 송전선로용 피뢰기 설치(1차)","2016-07-12 08:00","2016-07-13 18:00","2016-07-12 08:00","2016-07-13 18:00","매일",null,null,null,201605230052]
[110,"대구경북","구미","청리상주#2 T/L","154kV 청리-상주 등 6개T/L 송전선로용 피뢰기 설치공사","154kV 청리-상주#2T/L No.61~63, 69~72 송전선로용 피뢰기 설치(1차)","2016-07-12 08:00","2016-07-13 18:00","2016-07-12 08:00","2016-07-13 18:00","매일",null,null,null,201604130062]
[111,"대구경북","달성","달성상인#2 T/L","모선보호반교체","모선보호반교체","2016-07-06 14:00","2016-07-06 14:30","2016-07-07 14:00","2016-07-07 14:30","당일",null,null,null,201605190027]
[112,"대구경북","달성","달성상인#1 T/L","모선보호반교체","모선보호반교체","2016-07-06 13:30","2016-07-06 14:00","2016-07-07 13:30","2016-07-07 14:00","당일",null,null,null,201605190026]
[113,"대구경북","포항","아화건천#1 T/L","2016년 가공송전 협력회사 총액공사","전력선교체(No.32~34)","2016-07-01 08:00","2016-07-02 18:00","2016-07-01 08:00","2016-07-02 18:00","연속",null,null,null,201605120274]
[114,"부산울산","동부산","명례정관 T/L","154kV 명례-정관T/L 전선접속개소 전선교체공사","전선접속개소해소, 정관분기 8~24호, 8.25km","2016-07-09 08:00","2016-07-16 18:00","2016-07-09 08:00","2016-07-16 18:00","연속",null,null,null,201605120099]
[115,"부산울산","동부산","정관S/S 154KV#1 BUS TIE CB","정관S/S 170kV GIS 유압계통 보수","정관S/S 170kV 6100 GIS 유압계통 보수","2016-07-01 09:30","2016-07-01 11:00","2016-07-01 09:30","2016-07-01 11:00","당일",null,null,null,201605180102]
[116,"부산울산","북부산","북부산호포 T/L","북부산S/S 154kV 취약설비 GIS화공사","T-BUS 및 6J8DS 철거","2016-07-09 09:00","2016-07-10 18:00","2016-07-09 09:00","2016-07-10 18:00","연속",null,null,null,201605100336]
[117,"부산울산","북부산","양산산막#2 T/L","16년 가공송전 협력업체 총액공사","양산산막#2T/L 4호 애자련 교체공사","2016-07-12 09:00","2016-07-12 18:00","2016-07-12 09:00","2016-07-12 18:00","당일",null,null,null,201605130161]
[118,"부산울산","북부산","학장개금#2 T/L","학장S/S 170kV 장기사용 GIS 대체(3차)","학장-개금#1T/L, #2M.Tr 1차 GIS 대체, BUS TIE 철거(#2DS 및 차단부 시험가압)","2016-07-06 18:00","2016-07-08 18:00","2016-07-06 18:00","2016-07-08 18:00","연속",null,null,null,201605110003]
[119,"부산울산","북부산","매리호포#1 T/L","16년 가공송전 협력업체 공사","13, 14호 앵카쇄클 금구류 교체","2016-07-16 09:00","2016-07-16 18:00","2016-07-16 09:00","2016-07-16 18:00","연속",null,null,null,201605110063]
[120,"부산울산","서부산","서부산S/S 154kV #1 BUS TIE CB","서부산S/S 154kV #60-65Bus Pro 성능개선","서부산S/S 154kV #60-65Bus Pro 성능개선(6100 CB 휴전, 영인제)","2016-07-01 10:00","2016-07-01 18:00","2016-07-01 10:00","2016-07-01 18:00","당일",null,null,null,201605100140]
[121,"부산울산","울산","신울산S/S 67-68-0 SEC CB","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 67-68-0 GIS 보통점검","2016-07-04 09:00","2016-07-04 18:00","2016-07-04 09:00","2016-07-04 18:00","당일",null,null,null,201605110291]
[122,"부산울산","울산","신울산S/S 62-63-0 SEC CB","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S 62-63-0 GIS 보통점검","2016-07-01 09:00","2016-07-01 18:00","2016-07-01 09:00","2016-07-01 18:00","당일",null,null,null,201605110290]
[123,"부산울산","울산","신울산울산#2 T/L","2016년 가공송전 순시점검 위탁공사","송전선로 정밀점검(17기)","2016-07-04 09:00","2016-07-05 18:00","2016-07-04 09:00","2016-07-05 18:00","연속",null,null,null,201605110236]
[124,"부산울산","울산","방어진영남TP#1 T/L","영남화력S/Y 154kV GIS대체공사","○ 영남화력S/Y 154kV #1BUS/ 6131DS 시험가압 ==> 가압선로(48시간) ○ 154kV 50kA 2,000A GIS × 1CCT 재사용철거 ○ 154kV 50kA 4,000A GIS × 1CCT 설치 ○ 기타 부대공사 × 1식","2016-07-16 15:00","2016-07-18 15:00","2016-07-16 15:00","2016-07-18 15:00","연속",null,null,null,201605100197]
[125,"부산울산","울산","방어진영남TP#1 T/L","영남화력S/Y 154kV GIS대체공사","○ 영남화력S/Y 154kV #2BUS 시험가압 - 시험가압선로(48시간) ○ 154kV 50kA 2,000A GIS × 1CCT 재사용철거 ○ 154kV 50kA 4,000A GIS × 1CCT 설치 ○ 기타 부대공사 × 1식","2016-07-08 15:00","2016-07-10 15:00","2016-07-08 15:00","2016-07-10 15:00","연속",null,null,null,201605100185]
[126,"부산울산","울산","방어진영남TP#1 T/L","영남화력S/Y 154kV GIS대체공사","○ 영남화력S/Y 154kV #2BUS/ 6132DS,6133BAY 시험가압 ==> 가압선로(48시간) ○ 154kV 50kA 2,000A GIS × 1CCT 재사용철거 ○ 154kV 50kA 2,000A GIS × 1CCT 재사용철거 ○ 154kV 50kA 4,000A GIS × 1CCT 설치 ○ 기타 부대공사 × 1식","2016-07-20 15:00","2016-07-22 15:00","2016-07-20 15:00","2016-07-22 15:00","연속",null,null,null,201605100190]
[127,"부산울산","울산","방어진영남TP#1 T/L","영남화력S/Y 154kV GIS대체공사","○ 영남화력S/Y 154kV 6131DS,6133CB, 상부부스 BAY 시험가압 ==> 가압선로(48시간)","2016-07-22 15:00","2016-07-24 15:00","2016-07-22 15:00","2016-07-24 15:00","연속",null,null,null,201605240151]
[128,"부산울산","직할","범일S/S 154kV #1 BUS TIE CB","범일S/S 154kV 6100 CB 장기 미동작차단기 점검","범일S/S 154kV 6100 CB 장기 미동작차단기 점검","2016-07-04 10:00","2016-07-04 14:00","2016-07-04 10:00","2016-07-04 14:00","당일",null,null,null,201605190019]
[129,"경남","진주","거창합천#2 T/L","거창S/S 154kV #1BUS TIE CB(6100) 정밀 시험가압","거창S/S 154kV #1BUS TIE CB(6100) 정밀 #2BUS 시험가압","2016-07-02 12:00","2016-07-02 13:00","2016-07-02 12:00","2016-07-02 13:00","당일",null,null,null,201605120060]
[130,"경남","진주","거창합천#1 T/L","거창S/S 154kV #1BUS TIE CB(6100) 시험가압","거창S/S 154kV #1BUS TIE CB(6100) 시험가압","2016-07-03 16:00","2016-07-03 17:00","2016-07-03 16:00","2016-07-03 17:00","당일",null,null,null,201605120063]
[131,"경남","함안","신마산S/S 154kV #2 BUS TIE CB","신마산SS 154kV 61-66BUS 모선보호반 대체공사","신마산SS 154kV 61-66BUS 모선보호반 대체 - 모선보호반 철거 및 설치","2016-07-01 09:00","2016-07-03 18:00","2016-07-01 09:00","2016-07-03 18:00","연속",null,null,null,201605130112]
[132,"경남","함안","신마산S/S 154kV #1 BUS TIE CB","신마산SS 154kV 60-65BUS 모선보호반 대체공사","신마산SS 154kV 60-65BUS 모선보호반 대체 - 모선보호반 철거 및 설치","2016-07-08 09:00","2016-07-10 18:00","2016-07-08 09:00","2016-07-10 18:00","연속",null,null,null,201605130128]
[133,"경남","함안","동읍진영#1 T/L","154kV 동읍-진영T/L 33-35호 지장송전선로 이설공사","154kV 동읍-진영T/L 33-35호 임시선로구성(기설33호-임시34호-기설35호)","2016-07-09 07:00","2016-07-10 18:00","2016-07-09 07:00","2016-07-10 18:00","연속",null,null,null,201605110036]
[134,"경남","함안","동읍진영#2 T/L","154kV 동읍-진영T/L 33-35호 지장송전선로 이설공사","154kV 동읍-진영T/L 33-35호 임시선로구성(기설33호-임시34호-기설35호)","2016-07-02 07:00","2016-07-03 18:00","2016-07-02 07:00","2016-07-03 18:00","연속",null,null,null,201605110034]
[135,"경남","함안","진영초동#2 T/L","154kV 동읍-진영T/L 33-35호 지장송전선로 이설공사","154kV 동읍-진영T/L 33-35호 임시선로구성(기설33호-임시34호-기설35호)","2016-07-02 07:00","2016-07-03 18:00","2016-07-02 07:00","2016-07-03 18:00","연속",null,null,null,201605110035]
[136,"경남","함안","진영초동#1 T/L","154kV 동읍-진영T/L 33-35호 지장송전선로 이설공사","154kV 동읍-진영T/L 33-35호 임시선로구성(기설33호-임시34호-기설35호)","2016-07-09 07:00","2016-07-10 18:00","2016-07-09 07:00","2016-07-10 18:00","연속",null,null,null,201605110037]
[137,"경남","함안","창공S/S 154kV #1 BUS","옥외철구설비 GIS화 공사","옥외철구설비,GIS설비 모선연결작업","2016-07-31 09:00","2016-08-15 18:00","2016-07-31 09:00","2016-08-15 18:00","연속"]
[138,"경남","함안","창공S/S 154kV #2 BUS","옥외철구설비 GIS화 공사","옥외철구설비,GIS설비 모선연결작업","2016-07-18 :09:00","2016-07-30 18:00","2016-07-18 :09:00","2016-07-30 18:00","연속"]
[139,"대구경북","달성","다산강창#1T/L","무부하 가압","무부하 가압","2016-07-05 12:00","2016-07-06 18:00","2016-07-05 12:00","2016-07-06 18:00","매일"]

{"sheet":"중부","index":3,"n_rows":5,"n_cols":14,"rows_kept":5,"cut":false,"hidden":false,"merged":[[0,0,0,6],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 07월 휴전계획(신보령화력건설본부)"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간\n(Y/N)","처리결과\n(Y/N)","처리사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"신보령","신보령","1호기 주변압기\n(CB 7172, CB 7100)","신보령 1호기 주변압기  \n 냉각팬 운전회로 설비 개선","신보령 1호기 주변압기  \n 냉각팬 운전회로 설비 개선","2016-07-04T09:00:00","2016-07-06T18:00:00","2016-07-04T09:00:00","2016-07-06T18:00:00","연속"]