{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["765송부","345송부","154송부","Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":11,"n_cols":16,"rows_kept":11,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 10월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신서산신안성#1 T/L","신안성S/S 신서산신안성#1T/L PNL 대체시험","신안성S/S 신서산신안성#1T/L PNL 대체시험","2016-10-28 09:30","2016-10-28 18:00","2016-10-19 09:30","2016-10-19 18:00","당일",null,null,"일정변경",201608010077]
[2,"강원","태백","신태백S/S 765kV #1 BUS","2016 신태백S/S 800kV GIS 정밀점검 공사","ㅇ 신태백S/S 800kV GIS 정밀점검공사(83BAY CB,DS) ㅇ 8351 #1BUS DS 정밀점검","2016-10-04 08:00","2016-10-10 18:00","2016-10-04 08:00","2016-10-10 18:00","연속",null,null,null,201608090278]
[3,"강원","태백","신태백S/S 765kV #2 BUS","2016 신태백S/S 800kV GIS 정밀점검 공사","ㅇ 신태백S/S 800kV GIS 정밀점검공사(83BAY CB,DS) ㅇ 8352 #2BUS DS 정밀점검 ㅇ 8472CB 조작시험","2016-10-11 08:00","2016-10-17 18:00","2016-10-11 08:00","2016-10-17 18:00","연속",null,null,null,201608090281]
[4,"대전충남","서산","신서산당진TP#1 T/L","765kV 신서산-당진화력#1T/L 정밀점검","[송전] 765kV 신서산-당진화력#1T/L 정밀점검 No.1~90","2016-10-26 07:30","2016-10-30 18:00","2016-10-26 07:30","2016-10-30 18:00","매일",null,null,null,201608110315]
[5,"대전충남","서산","신서산당진TP#2 T/L","765kV 신서산-당진화력#2T/L 정밀점검","[송전] 765kV 신서산-당진화력#2T/L 정밀점검 No.1~90","2016-10-31 07:30","2016-11-04 18:00","2016-10-31 07:30","2016-11-04 18:00","매일",null,null,null,201608110316]
[6,"경남","함안","북경남S/S 765kV #1 BUS","북경남S/S 800kV 스페이서 교체공사","- 765kV 북경남-신고리NP #1 T/L 인출측 GIS SPACER교체에 따른 내전압시험","2016-10-24 08:00","2016-10-25 18:00","2016-10-24 08:00","2016-10-25 18:00","연속",null,null,null,201607290101]
[7,"경남","함안","북경남S/S #4 M.Tr","북경남S/S 765kV M.TR 초기점검공사 및 차단부 이너노즐교체","- 북경남S/S 765kV M.TR 초기점검공사 및 차단부 이너노즐교체","2016-10-23 08:00","2016-10-29 18:00","2016-10-23 08:00","2016-10-29 18:00","연속",null,null,null,201607290099]

{"sheet":"345송부","index":1,"n_rows":281,"n_cols":16,"rows_kept":281,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 10월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#4 T/L","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-10-10 09:00","2016-10-18 18:00","2016-10-10 09:00","2016-10-18 18:00","연속",null,null,null,201608170077]
[2,"서울","성동","성동S/S #2 M.Tr A","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-10-19 09:00","2016-10-25 18:00","2016-10-19 09:00","2016-10-25 18:00","연속",null,null,null,201608170082]
[3,"서울","성동","성동S/S #3 M.Tr A","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-10-10 09:00","2016-10-18 18:00","2016-10-10 09:00","2016-10-18 18:00","연속",null,null,null,201608170079]
[4,"서울","성동","성동S/S #1 M.Tr A","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-10-26 09:00","2016-10-27 18:00","2016-10-26 09:00","2016-10-27 18:00","연속",null,null,null,201608170084]
[5,"서울","성동","성동S/S 345kV #2Sh.R","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-10-04 09:00","2016-10-07 18:00","2016-10-04 09:00","2016-10-07 18:00","연속",null,null,null,201608170057]
[6,"서울","성동","미금성동#2 T/L","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-10-19 09:00","2016-10-25 18:00","2016-10-19 09:00","2016-10-25 18:00","연속",null,null,null,201608170083]
[7,"서울","중부","양주중부#1 T/L","345kV 중부S/S #1,2Sh.R용 GIS 복구공사","중부S/S 345kV #1 Sh.R GIS CB (7179) 대체공사","2016-10-10 08:00","2016-10-18 18:00","2016-10-10 08:00","2016-10-18 18:00","연속",null,null,null,201608100035]
[8,"서울","중부","양주중부#2 T/L","345kV 중부S/S #1,2Sh.R용 GIS 복구공사","중부S/S 345kV #2 Sh.R GIS CB (7279) 대체공사","2016-10-19 08:00","2016-10-28 18:00","2016-10-19 08:00","2016-10-28 18:00","연속",null,null,null,201607190038]
[9,"서울","중부","중부S/S 345kV #2 Sh.R","345kV 중부S/S #1,2Sh.R용 GIS 복구공사","중부S/S 345kV #2 Sh.R GIS CB (7279) 대체공사","2016-10-19 08:00","2016-10-31 18:00","2016-10-19 08:00","2016-10-31 18:00","연속",null,null,null,201608100036]
[10,"남서울","강남","신양재S/S #1 M.Tr A","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-10-04 09:00","2016-10-06 18:00","2016-10-04 09:00","2016-10-06 18:00","연속",null,null,null,201607110049]
[11,"남서울","강남","신양재S/S #3 M.Tr A","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-10-26 09:00","2016-10-29 18:00","2016-10-26 09:00","2016-10-29 18:00","연속",null,null,null,201607110061]
[12,"남서울","강남","신양재S/S 신성남-신양재#1T/L#1 M.Tr1차CB (7100)","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-10-10 09:00","2016-10-13 18:00","2016-10-10 09:00","2016-10-13 18:00","연속",null,null,null,201607110052]
[13,"남서울","강남","신양재S/S 345kV #1 BUS","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-10-19 09:00","2016-10-21 18:00","2016-10-19 09:00","2016-10-21 18:00","연속",null,null,null,201607110056]
[14,"남서울","강남","신양재S/S 신성남-신양재#1T/L CB (7171)","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-10-17 09:00","2016-10-19 18:00","2016-10-17 09:00","2016-10-19 18:00","연속",null,null,null,201607110055]
[15,"남서울","강남","신성남신양재#1 T/L","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-10-12 09:00","2016-10-15 18:00","2016-10-12 09:00","2016-10-15 18:00","연속",null,null,null,201607110054]
[16,"남서울","강남","신양재S/S #3 M.Tr 1차 CB (7372)","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-10-31 09:00","2016-11-02 18:00","2016-10-31 09:00","2016-11-02 18:00","연속",null,null,null,201607110062]
[17,"남서울","강남","신양재S/S 7300 CB (7300)","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","강남전력지사 362kV GIS 정밀점검 공사 - 변전전문회사","2016-10-24 09:00","2016-10-26 18:00","2016-10-24 09:00","2016-10-26 18:00","연속",null,null,null,201607110058]
[18,"남서울","동서울","동서울S/S 345kV #71 BUS","345kV GIS 정밀점검","345kV GIS 정밀점검 - 신성남-동서울#2T/L 모선측 DS(7451DS) 점검","2016-10-16 09:00","2016-10-17 18:00","2016-10-16 09:00","2016-10-17 18:00","연속",null,null,null,201608180135]
[19,"남서울","동서울","신성남-동서울#2T/L-#2M.Tr 1차 CB (7400)","345kV GIS 정밀점검","345kV GIS 정밀점검 - 7400 BUS-TIE - 차단기 점검(10/14~15)","2016-10-09 09:00","2016-10-20 18:00","2016-10-09 09:00","2016-10-20 18:00","연속",null,null,null,201608180141]
[20,"남서울","동서울","동서울S/S #2 M.Tr A","345kV GIS 정밀점검","345kV GIS 정밀점검 - 동서울S/S #2M.Tr 1차","2016-10-09 09:00","2016-10-13 18:00","2016-10-09 09:00","2016-10-13 18:00","연속",null,null,null,201608180133]
[21,"남서울","동서울","동서울S/S 345kV #76 BUS","345kV GIS 정밀점검","345kV GIS 정밀점검 - 10/7~10/8 : #1M.Tr 모선측 DS(7352DS) 점검 - 10/9~10/10 : #2M.Tr 모선측 DS(7452DS) 점검","2016-10-07 09:00","2016-10-10 18:00","2016-10-07 09:00","2016-10-10 18:00","연속",null,null,null,201608180131]
[22,"남서울","동서울","신용인-동서울#1T/L-#1M.Tr 1차 CB (7300)","345kV GIS 정밀점검","345kV GIS 정밀점검 - #1M.Tr 1차","2016-10-04 09:00","2016-10-08 18:00","2016-10-04 09:00","2016-10-08 18:00","연속",null,null,null,201608180216]
[23,"남서울","동서울","동서울S/S #1 M.Tr A","345kV GIS 정밀점검","345kV GIS 정밀점검 - 동서울S/S #1M.Tr 1차","2016-10-04 09:00","2016-10-08 18:00","2016-10-04 09:00","2016-10-08 18:00","연속",null,null,null,201608180130]
[24,"남서울","동서울","동서울S/S #4 M.Tr A","170kV GCB 교체공사","동서울S/S #4 M.Tr 2차 GCB 교체공사","2016-10-17 09:00","2016-10-21 18:00","2016-10-17 09:00","2016-10-21 18:00","연속",null,null,null,201608180150]
[25,"남서울","동서울","동서울S/S #3 M.Tr A","170kV GCB 교체공사","동서울S/S #3 M.Tr 2차 GCB 교체공사","2016-10-24 09:00","2016-10-28 18:00","2016-10-24 09:00","2016-10-28 18:00","연속",null,null,null,201608180147]
[26,"남서울","동서울","신성남동서울#2 T/L","345kV GIS 정밀점검","345kV GIS 정밀점검 - 신성남-동서울#2 T/L","2016-10-16 09:00","2016-10-20 18:00","2016-10-16 09:00","2016-10-20 18:00","연속",null,null,null,201608180134]
[27,"남서울","영서","영서S/S #3 M.Tr A","2016년 변전협력회사 총액공사_보통점검","- MTR 초기 및 보통점검 - MTR 주변기기(LA, PT 등) 보통점검 - MTR 누유보수","2016-10-31 09:00","2016-11-04 18:00","2016-10-31 09:00","2016-11-04 18:00","연속",null,null,null,201608110231]
[28,"남서울","영서","영서S/S #2 M.Tr A","2016년 변전협력회사 총액공사_보통점검","- MTR 1,2,3차 피뢰기 점검 - MTR 3차측 PT 및 모선 점검","2016-10-06 09:00","2016-10-06 18:00","2016-10-06 09:00","2016-10-06 18:00","당일",null,null,null,201608110191]
[29,"남서울","영서","신시흥영서#2 T/L","2016년 변전협력회사 총액공사_보통점검","- 345kV 전위변성기 보통점검 - 345kV 피뢰기 보통점검 - 선로 인출DS 과열보수 - 송전부 병행작업(인류크램프 교체_정윤환)","2016-10-13 09:00","2016-10-13 18:00","2016-10-13 09:00","2016-10-13 18:00","당일",null,null,null,201608180061]
[30,"남서울","영서","신시흥영서#1 T/L","16년 가공송전협력총액공사(압축인류클램프 교체공사)","압축인류클램프 교체 공사","2016-10-12 09:00","2016-10-12 18:00","2016-10-12 09:00","2016-10-12 18:00","당일",null,null,null,201608190030]
[31,"남서울","영서","서서울영서#2 T/L","2016년 변전협력회사 총액공사_보통점검","- 345kV 전위변성기 보통점검 - 345kV 피뢰기 보통점검","2016-10-07 09:00","2016-10-07 18:00","2016-10-07 09:00","2016-10-07 18:00","당일",null,null,null,201608180042]
[32,"인천","김포","가정개폐소 345KV #2,3Sh.R - TIE GIS CB","가정개폐소 345KV #2,3Sh.R - TIE GIS 기기점검","가정개폐소 345KV #2,3Sh.R - TIE GIS(7100)기기점검","2016-10-06 09:00","2016-10-06 18:00","2016-10-06 09:00","2016-10-06 18:00","당일",null,null,null,201608100163]
[33,"인천","김포","가정개폐소 345KV 75-76 SEC CB","가정개폐소 345KV 75-76 SEC 기기점검","가정개폐소 345KV 75-76 SEC 기기점검","2016-10-27 09:00","2016-10-27 18:00","2016-10-27 09:00","2016-10-27 18:00","당일",null,null,null,201608110114]
[34,"인천","김포","345kV 가정개폐소 #3Sh.R 1차 GIS CB","345kV 가정개폐소 #3Sh.R 1차 GIS(7172) 기기점검","345kV 가정개폐소 #3Sh.R 1차 GIS(7172) 기기점검","2016-10-07 09:00","2016-10-07 18:00","2016-10-07 09:00","2016-10-07 18:00","당일",null,null,null,201608100164]
[35,"인천","김포","345kV가정 - 인천CC #2T/L GIS CB","345kV가정 인천CC #2T/L GIS(7271) 기기점검","345kV가정 인천CC #2T/L GIS(7271) 기기점검","2016-10-17 09:00","2016-10-17 18:00","2016-10-17 09:00","2016-10-17 18:00","당일",null,null,null,201608100165]
[36,"인천","김포","가정인천CC# - 가정신부평#3 TIE GIS CB","가정인천CC#2 - 가정신부평#3 TIE GIS 기기점검","가정인천CC#2 - 가정신부평#3 TIE GIS(7200) 기기점검","2016-10-13 09:00","2016-10-13 18:00","2016-10-13 09:00","2016-10-13 18:00","당일",null,null,null,201608110088]
[37,"인천","김포","345kV신가좌 - 가정 #2T/L GIS CB","345kV신가좌 - 가정 #2T/L GIS(7371)기기점검","345kV신가좌 - 가정 #2T/L GIS(7371)기기점검","2016-10-18 09:00","2016-10-18 18:00","2016-10-18 09:00","2016-10-18 18:00","당일",null,null,null,201608110090]
[38,"인천","김포","345kV가정 - 신부평 #3T/L GIS CB","345kV가정 - 신부평 #3T/L GIS(7272)기기점검","345kV가정 - 신부평 #3T/L GIS(7272)기기점검","2016-10-12 09:00","2016-10-12 18:00","2016-10-12 09:00","2016-10-12 18:00","당일",null,null,null,201608110089]
[39,"인천","김포","신가좌 -가정#2 TIE GIS CB","신가좌 -가정#2 TIE GIS(7300) 기기점검","신가좌 -가정#2 TIE GIS(7300) 기기점검","2016-10-19 09:00","2016-10-19 18:00","2016-10-19 09:00","2016-10-19 18:00","당일",null,null,null,201608110093]
[40,"인천","김포","345kV가정 - 인천CC #1T/L GIS CB","345kV가정 - 인천CC #1T/L GIS(7471) 기기점검","345kV가정 - 인천CC #1T/L GIS(7471) 기기점검","2016-10-10 09:00","2016-10-10 18:00","2016-10-10 09:00","2016-10-10 18:00","당일",null,null,null,201608110095]
[41,"인천","김포","가정인천CC#1 - 가정신부평#1 TIE GIS CB","가정인천CC#1-가정신부평#1 TIE GIS(7400)기기점검","가정인천CC#1-가정신부평#1 TIE GIS(7400)기기점검","2016-10-11 09:00","2016-10-11 18:00","2016-10-11 09:00","2016-10-11 18:00","당일",null,null,null,201608110096]
[42,"인천","김포","345kV가정개폐 #2Sh.R 1차 GIS CB","345kV가정개폐 #2Sh.R 1차 GIS (7171)","345kV가정개폐 #2Sh.R 1차 GIS (7171) 기기점검","2016-10-05 09:00","2016-10-05 18:00","2016-10-05 09:00","2016-10-05 18:00","당일",null,null,null,201608100160]
[43,"인천","김포","가정개폐소 345KV 70-71 SEC CB","가정개폐소 345KV 70-71 SEC 기기점검","가정개폐소 345KV 70-71 SEC 기기점검","2016-10-26 09:00","2016-10-26 18:00","2016-10-26 09:00","2016-10-26 18:00","당일",null,null,null,201608110113]
[44,"인천","김포","345kV가정 - 신부평 #1T/L GIS CB","345kV가정 - 신부평 #1T/L GIS(7472)기기점검","345kV가정 - 신부평 #1T/L GIS(7472)기기점검","2016-10-14 09:00","2016-10-14 18:00","2016-10-14 09:00","2016-10-14 18:00","당일",null,null,null,201608110100]
[45,"인천","김포","345kV신가좌 - 가정 #1T/L GIS CB","345kV신가좌 - 가정 #1T/L GIS(7571)기기점검","345kV신가좌 - 가정 #1T/L GIS(7571)기기점검","2016-10-20 09:00","2016-10-20 18:00","2016-10-20 09:00","2016-10-20 18:00","당일",null,null,null,201608110108]
[46,"인천","김포","신가좌 -가정#1 TIE GIS CB","신가좌 -가정#1 TIE GIS(7500)기기점검","신가좌 -가정#1 TIE GIS(7500)기기점검","2016-10-21 09:00","2016-10-21 18:00","2016-10-21 09:00","2016-10-21 18:00","당일",null,null,null,201608110109]
[47,"인천","김포","345kV가정개폐 #1Sh.R 1차 GIS CB","345kV가정개폐 #1Sh.R 1차 GIS(7671) 기기점검","345kV가정개폐 #1Sh.R 1차 GIS(7671) 기기점검","2016-10-24 09:00","2016-10-24 18:00","2016-10-24 09:00","2016-10-24 18:00","당일",null,null,null,201608110111]
[48,"인천","김포","가정개폐소 345KV #1Sh.R - TIE GIS CB","가정개폐소 345KV #1Sh.R - TIE GIS 기기점검","가정개폐소 345KV #1Sh.R - TIE GIS(7600) 기기점검","2016-10-25 09:00","2016-10-25 18:00","2016-10-25 09:00","2016-10-25 18:00","당일",null,null,null,201608110112]
[49,"인천","김포","345kV신김포S/S 신김포 - 신파주#2T/L GIS CB","345kV신김포S/S 7571 GIS Accumulator 교체 공사","345kV신김포S/S GIS(7571) Accumulator 교체 공사","2016-10-11 09:00","2016-10-12 18:00","2016-10-11 09:00","2016-10-12 18:00","연속",null,null,null,201608110127]
[50,"인천","김포","345kV신김포S/S 신김포 - 서인천#T/L GIS CB","345kV신김포S/S 신김포-서인천T/L Accumulator 교체 공사","345kV신김포S/S 신김포-서인천T/L Accumulator(7572) 교체 공사","2016-10-13 09:00","2016-10-14 18:00","2016-10-13 09:00","2016-10-14 18:00","연속",null,null,null,201608110129]
[51,"인천","시흥","신시흥영흥TP#4 T/L","354kV 신시흥-신안산T/L 피뢰기 설치공사","- 신시흥-신안산T/L 피뢰기 설치 관련 안전이격거리확보(1기)","2016-10-01 07:00","2016-10-01 12:00","취소","취소","당일",null,null,null,201608040107]
[52,"인천","시흥","신시흥#1S/S #1 M.Tr 1차 CB (7B72)","신시흥#1S/S #1 M.Tr 1차 GIS(7B72) 정밀점검","신시흥#1S/S #1 M.Tr 1차 GIS(7B72) 정밀점검","2016-10-03 09:30","2016-10-07 18:00","2016-10-03 09:30","2016-10-07 18:00","연속",null,null,null,201608080155]
[53,"인천","시흥","신시흥#2S/S 화성신시흥T/L-TIE CB (7400)","신시흥#2S/S 화성신시흥T/L-TIE CB(7400) 누기개소 보수","신시흥#2S/S 화성신시흥T/L-TIE CB(7400) 누기개소 보수","2016-10-10 09:30","2016-10-12 18:00","2016-10-10 09:30","2016-10-12 18:00","연속",null,null,null,201608080156]
[54,"인천","시흥","신시흥#2S/S 화성신시흥T/L CB (7471)","신시흥#2S/S 화성신시흥T/L CB(7471) 누기개소 보수","신시흥#2S/S 화성신시흥T/L CB(7471) 누기개소 보수","2016-10-13 09:30","2016-10-15 18:00","2016-10-13 09:30","2016-10-15 18:00","연속",null,null,null,201608080157]
[55,"인천","시흥","영흥T/P 신시흥영흥TP#2T/L-#3G/T 1차 CB (7400)","영흥T/P 신시흥영흥TP#2T/L-#3G/T 1차 (7400) 정밀점검","영흥T/P 신시흥영흥TP#2T/L-#3G/T 1차 (7400) 정밀점검","2016-10-17 09:00","2016-10-19 18:00","2016-10-17 09:00","2016-10-19 18:00","연속",null,null,null,201608190054]
[56,"인천","시흥","영흥T/P #3 M.Tr(G.T) 1차 CB (7472)","영흥T/P #3 M.Tr(G.T) 1차 CB (7472) 정밀점검","영흥T/P #3 M.Tr(G.T) 1차 CB (7472) 정밀점검","2016-10-20 09:00","2016-10-22 18:00","2016-10-20 09:00","2016-10-22 18:00","연속",null,null,null,201608190055]
[57,"인천","인천","서인천C/C #2 M.Tr","서인천C/C #2 M.Tr 주변압기 정밀점검","서인천C/C #2 M.Tr 주변압기 정밀점검","2016-10-10 09:00","2016-10-20 18:00","2016-10-10 09:00","2016-10-20 18:00","연속",null,null,null,201608010130]
[58,"인천","인천","신가좌가정#2 T/L","'16-17년 가공송전정비 협력회사 총액공사","송전용 피뢰기 설치공사(3기)","2016-10-18 08:00","2016-10-20 18:00","2016-10-18 08:00","2016-10-20 18:00","당일",null,null,null,201608160174]
[59,"인천","인천","신가좌S/S #3 M.Tr A","신가좌S/S #3 M.Tr 주변압기 정밀점검","신가좌S/S #3 M.Tr 주변압기 정밀점검","2016-10-24 09:00","2016-11-05 18:00","2016-10-24 09:00","2016-11-05 18:00","연속",null,null,null,201608010128]
[60,"인천","인천","신가좌신시흥#2 T/L","'16-17년 가공송전정비 협력회사 총액공사","송전용 피뢰기 설치공사(39기)","2016-10-21 08:00","2016-10-26 18:00","2016-10-21 08:00","2016-10-26 18:00","매일",null,null,null,201608170188]
[61,"인천","인천","신경서S/S #1 M.Tr A","신경서S/S #1M.Tr 보호반 대체공사","신경서S/S #1M.Tr 보호반 대체공사","2016-10-17 09:00","2016-10-21 18:00","2016-10-17 09:00","2016-10-21 18:00","연속",null,null,null,201608250047]
[62,"인천","인천","신경서S/S 신경서포스코SY#1T/L GIS","2016년 인천전력지사 362kV GIS 정밀점검 공사","신경서S/S 신경서포스코SY#1T/L(7371) GIS 정밀점검","2016-10-05 08:00","2016-10-07 18:00","2016-10-05 08:00","2016-10-07 18:00","연속",null,null,null,201608010008]
[63,"인천","인천","신경서S/S 신경서포스코SY#1T/L-TIE GIS","2016년 인천전력지사 362kV GIS 정밀점검 공사","신경서S/S 신경서포스코SY#1T/L-신경서인천CC#2T/L TIE(7300) GIS 정밀점검","2016-10-10 08:00","2016-10-12 18:00","2016-10-10 08:00","2016-10-12 18:00","연속",null,null,null,201608010009]
[64,"인천","인천","신경서S/S 신경서포스코SY#2T/L GIS","2016년 인천전력지사 362kV GIS 정밀점검 공사","신경서S/S 신경서포스코SY#2T/L(7571) GIS 정밀점검","2016-10-13 08:00","2016-10-15 18:00","2016-10-13 08:00","2016-10-15 18:00","연속",null,null,null,201608010010]
[65,"인천","인천","신인천C/C 4MT001 CB (7972)","345kV 서(신)인천C/C 용량부족 GIS 대체공사","79Bay : 7972CB 대체","2016-10-20 10:00","2016-10-26 17:00","2016-10-20 10:00","2016-10-26 17:00","연속",null,null,null,201608010115]
[66,"인천","인천","신인천C/C TIE-4MT001 CB (7900)","345kV 서(신)인천C/C 용량부족 GIS 대체공사","79Bay : 7900CB 대체","2016-10-05 10:00","2016-10-18 17:00","2016-10-05 10:00","2016-10-18 17:00","연속",null,null,null,201608010114]
[67,"인천","인천","신인천C/C 70-71-0 SEC CB (70-71-0)","신인천C/C 70-71-0 SEC GIS(70-71-0) 초기점검","신인천C/C 70-71-0 SEC GIS(70-71-0) 초기점검","2016-10-04 09:00","2016-10-04 18:00","2016-10-04 09:00","2016-10-04 18:00","당일",null,null,null,201608010124]
[68,"인천","인천","인천CC S/Y 인천복합 #1,2 G/T CB (7572)","인천복합S/Y 7552DS A상 이음발생관련 보수공사","-휴전설비 : 7572CB -인천복합S/Y 7552DS A상 이음발생관련 보수공사","2016-10-04 09:00","2016-10-06 18:00","2016-10-04 09:00","2016-10-06 18:00","연속",null,null,null,201608020118]
[69,"인천","인천","인천CC S/Y 345kV #76 BUS","인천복합S/Y 7552DS A상 이음발생관련 보수공사","인천복합S/Y 7552DS A상 이음발생관련 보수공사","2016-10-04 09:00","2016-10-06 18:00","2016-10-04 09:00","2016-10-06 18:00","연속",null,null,null,201608020124]
[70,"인천","인천","가정인천CC#1 T/L","인천T/P 가정인천C/C#1T/L CLR 이음 확인 및 미사용 철구 철거","인천T/P 가정인천C/C#1T/L CLR 이음 확인 및 미사용 철구 철거","2016-10-10 09:00","2016-10-11 18:00","2016-10-10 09:00","2016-10-11 18:00","연속",null,null,null,201608180108]
[71,"인천","직할","신부평S/S 345kV #2 BUS","신부평S/S 345kV 모선보호반 대체(#2BUS휴전)","신부평S/S 345kV 모선보호반 대체(#2BUS휴전)","2016-10-03 09:30","2016-10-07 18:00","2016-10-03 09:30","2016-10-07 18:00","연속",null,null,null,201608090118]
[72,"경기북부","구리","신가평신의정부#2 T/L","신가평S/S 345kV 신가평신의정부#2T/L GIS 정밀점검","신가평S/S 345kV 신가평신의정부#2T/L GIS 정밀점검 * 7502,7562,7522DS 및 7572CB","2016-10-10 08:00","2016-10-13 18:00","2016-10-10 08:00","2016-10-13 18:00","연속",null,null,null,201606200064]
[73,"경기북부","구리","신가평신의정부#1 T/L","신가평S/S 345kV 신가평신의정부#1T/L GIS 정밀점검","신가평S/S 345kV 신가평신의정부#1T/L GIS 정밀점검 * 7602,7662,7622DS 및 7600, 7672CB","2016-10-17 08:00","2016-10-21 17:00","2016-10-17 08:00","2016-10-21 17:00","연속",null,null,null,201606200065]
[74,"경기북부","구리","미금S/S 345kV #6 Sh.R","미금S/S 345kV #6 Sh.R 냉각장치 팬 청소","345kV Sh.R 1대 냉각장치 팬 청소","2016-10-04 09:00","2016-10-04 18:00","2016-10-04 09:00","2016-10-04 18:00","연속",null,null,null,201608290039]
[75,"경기북부","구리","미금S/S 345kV #1 BUS Sh.R MAIN CB (7079)","미금S/S 345kV #1 Sh.R 하자점검","345kV 분로리액터 1대 하자점검 냉각장치 팬 청소","2016-10-03 09:00","2016-10-03 18:00","2016-10-03 09:00","2016-10-03 18:00","연속",null,null,null,201608290038]
[76,"경기북부","직할","신의정부S/S #1 M.Tr A","신의정부S/S #1 M.Tr A","2016년 경기북부지역본부 직할 345kV 본체 정밀점검 공사 - #1M.Tr A상","2016-10-24 09:30","2016-10-28 18:00","2016-10-24 09:30","2016-10-28 18:00","연속",null,null,null,201608160014]
[77,"경기북부","직할","양주S/S #2 M.Tr","양주S/S #2 M.Tr B","2016년 경기북부지역본부 직할 345kV 본체 정밀점검 공사 - #2M.Tr B,C상","2016-10-10 09:30","2016-10-14 18:00","2016-10-10 09:30","2016-10-14 18:00","연속",null,null,null,201608160012]
[78,"경기북부","직할","양주S/S #4 M.Tr A","양주S/S #4 M.Tr A","2016년 경기북부지역본부 직할 345kV 본체 정밀점검 공사 - #4M.Tr A상","2016-10-17 09:30","2016-10-21 18:00","2016-10-17 09:30","2016-10-21 18:00","연속",null,null,null,201608160013]
[79,"경기북부","직할","양주S/S SVC M.Tr CB","양주S/S SVC M.Tr","2016년 양주S/S SVC 보통점검 공사","2016-10-04 09:30","2016-10-14 18:00","2016-10-04 09:30","2016-10-14 18:00","연속",null,null,null,201608160015]
[80,"경기북부","파주","신파주S/S #1SVC Tr CB","2016년 신파주S/S SVC 하자점검","- M.Tr, GIS 포함 SVC 부속설비 점검 - Thyristor 및 Cooling System 점검","2016-10-31 09:00","2016-11-11 18:00","2016-10-31 09:00","2016-11-11 18:00","연속",null,null,null,201607290065]
[81,"경기","군포","서서울S/S #4 M.Tr A","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로,모선보호 PNL 이설","2016-10-05 07:00","2016-10-20 07:00","2016-10-05 07:00","2016-10-20 07:00","연속",null,null,null,201608050027]
[82,"경기","군포","서서울S/S 345kV #2 BUS GIS","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로,모선보호 PNL 이설 - 7472CB 교체(투입저항부 설치)","2016-10-19 13:00","2016-11-12 18:00","2016-10-19 13:00","2016-11-12 18:00","연속",null,null,"신뢰도개선",201608050028]
[83,"경기","군포","화성서서울#1 T/L","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로,모선보호 PNL 이설","2016-10-10 07:00","2016-10-19 13:00","2016-10-10 07:00","2016-10-19 13:00","연속",null,null,null,201608050026]
[84,"경기","군포","화성서서울#2 T/L","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로,모선보호 PNL 이설","2016-10-04 13:00","2016-10-10 07:00","2016-10-04 13:00","2016-10-10 07:00","연속",null,null,null,201608050024]
[85,"경기","군포","서서울S/S 345kV #1 BUS GIS","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로,모선보호 PNL 이설","2016-10-04 07:00","2016-10-04 13:00","2016-10-04 07:00","2016-10-04 13:00","연속",null,null,"신뢰도개선",201608050025]
[86,"경기","군포","신온양서서울#1 T/L","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로보호 PNL 신설 - 7472CB 교체(투입저항부 설치)","2016-10-20 07:00","2016-10-26 18:00","2016-10-20 07:00","2016-10-26 18:00","연속",null,null,null,201608050029]
[87,"경기","군포","서서울S/S #3 M.Tr A","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로보호 PNL 이설 - 7672CB 교체(투입저항부 설치)","2016-10-27 07:00","2016-11-05 18:00","2016-10-27 07:00","2016-11-05 18:00","연속",null,null,null,201608050030]
[88,"경기","군포","서서울영서#2 T/L","서서울S/S Local House 전력설비 이설공사","서서울S/S Local House 전력설비 이설공사 - 송전선로보호 PNL 이설 - 7672CB 교체(투입저항부 설치)","2016-10-27 07:00","2016-11-05 18:00","2016-10-27 07:00","2016-11-05 18:00","연속",null,null,null,201608050031]
[89,"경기","군포","신시흥신안산 T/L","345kV 신시흥-신안산T/L 피뢰기 설치공사","- No.56.2~101호간 피뢰기 설치(141set)","2016-10-01 07:00","2016-10-06 18:00","2016-10-01 07:00","2016-10-06 18:00","연속",null,null,null,201608020099]
[90,"경기","동부","곤지암S/S #1 M.Tr A","16년 동부 변전협력회사 총액공사","곤지암S/S #1M.Tr OFU 필터교체","2016-10-04 09:30","2016-10-04 18:00","2016-10-04 09:30","2016-10-04 18:00","당일",null,null,null,201608080079]
[91,"경기","동부","곤지암S/S #3 M.Tr A","16년 동부 변전협력회사 총액공사","곤지암S/S #3M.Tr 붓싱도블 측정 및 절연유 채유","2016-10-05 09:30","2016-10-05 18:00","2016-10-05 09:30","2016-10-05 18:00","당일",null,null,null,201608080081]
[92,"경기","성남","서안성신진천#1 T/L","345kV 서안성-신진천#1T/L 송전용피뢰기 설치공사","- 송전용피뢰기 63기(189set) 설치","2016-10-02 08:00","2016-10-09 18:00","2016-10-02 08:00","2016-10-09 18:00","연속",null,null,null,201608030070]
[93,"경기","성남","서안성S/S #3 M.Tr A","서안성S/S 345kV GIS 설치공사","345kV GIS 2CB 신설","2016-10-01 09:00","2016-10-03 18:00","2016-10-01 09:00","2016-10-03 18:00","연속",null,null,null,201608040012]
[94,"경기","성남","신안성신성남#2 T/L","345kV 신용인-동서울T/L(태전) OPGW 증설공사","345kV 신용인-동서울T/L(태전) OPGW 증설공사 OPGW 120SQ 15km , 70SQ 30km 교체 및 증설","2016-10-20 09:00","2016-10-23 18:00","2016-10-20 09:00","2016-10-23 18:00","연속",null,null,null,201608250063]
[95,"경기","성남","신시흥신성남#1 T/L","354kV 신시흥-신안산T/L 피뢰기 설치공사","- 신시흥-신안산T/L 피뢰기 설치 관련 안전이격거리확보(28기)","2016-10-01 07:00","2016-10-04 18:00","2016-10-01 07:00","2016-10-04 18:00","연속",null,null,null,201608040108]
[96,"경기","성남","신성남신양재#1 T/L","345kV 신성남-신양재T/L 송전선로용 피뢰기 설치공사","대상 : No.1~22","2016-10-12 08:00","2016-10-16 18:00","2016-10-12 08:00","2016-10-16 18:00","연속",null,null,null,201608190037]
[97,"경기","성남","신수원S/S #1 M.Tr A","신수원S/S 345kV #1M.Tr 정밀점검","신수원S/S 345kV #1M.Tr 정밀점검","2016-10-10 09:00","2016-10-23 18:00","2016-10-10 09:00","2016-10-23 18:00","연속",null,null,null,201608010083]
[98,"경기","성남","신안성S/S 신안성-신수원#2T/L CB (7A72)","신안성S/S 345kV 7A72 GIS 정밀점검","신안성S/S 345kV 7A72 GIS 정밀점검, 보조계전기교체","2016-10-27 09:00","2016-10-29 18:00","2016-10-27 09:00","2016-10-29 18:00","연속",null,null,null,201608010069]
[99,"경기","성남","신안성S/S#4M.Tr 2차-신안성-신수원#2TL CB (7A00)","신안성S/S 345kV 7A00 GIS 정밀점검","신안성S/S 345kV 7A00 GIS 정밀점검, 보조계전기교체","2016-10-24 09:00","2016-10-26 18:00","2016-10-24 09:00","2016-10-26 18:00","연속",null,null,null,201608010065]
[100,"경기","성남","신안성S/S 신안성-서안성#2T/L CB (7B72)","신안성S/S 345kV 7B72 GIS 정밀점검","신안성S/S 345kV 7B72 GIS 정밀점검, 보조계전기교체","2016-10-20 09:00","2016-10-22 18:00","2016-10-20 09:00","2016-10-22 18:00","연속",null,null,null,201608010064]
[101,"경기","성남","신안성S/S#7 Sh.R-신안성-서안성#2T/L CB (7B00)","신안성S/S 345kV 7B00 GIS 정밀점검","신안성S/S 345kV 7B00 GIS 정밀점검, 보조계전기교체","2016-10-17 09:00","2016-10-19 18:00","2016-10-17 09:00","2016-10-19 18:00","연속",null,null,null,201608010063]
[102,"경기","성남","신안성S/S #7 Sh.R CB (7B71) (7B71)","신안성S/S 345kV 7B71 GIS 정밀점검","신안성S/S 345kV 7B71 GIS 정밀점검, 보조계전기교체","2016-10-13 09:00","2016-10-15 18:00","2016-10-13 09:00","2016-10-15 18:00","연속",null,null,null,201608010062]
[103,"경기","성남","신안성S/S#5M.Tr 2차-신안성-서안성#1TL CB (7C00)","신안성S/S 345kV 7C00 GIS 정밀점검","신안성S/S 345kV 7C00 GIS 정밀점검, 보조계전기교체","2016-10-05 09:00","2016-10-07 18:00","2016-10-05 09:00","2016-10-07 18:00","연속",null,null,null,201608010060]
[104,"경기","성남","신안성S/S 신안성-서안성#1T/L CB (7C72)","신안성S/S 345kV 7C72 GIS 정밀점검","신안성S/S 345kV 7C72 GIS 정밀점검, 보조계전기교체","2016-10-10 09:00","2016-10-12 18:00","2016-10-10 09:00","2016-10-12 18:00","연속",null,null,null,201608010061]
[105,"경기","성남","신용인S/S 345kV #1 BUS","345kV 신용인S/S 용량부족 GIS 대체공사","345kV 모선 및 모선DS GIS 용량대체","2016-10-05 09:00","2016-11-13 18:00","2016-10-05 09:00","2016-11-13 18:00","연속",null,null,null,201608110085]
[106,"경기","성남","동서울신용인#2 T/L","345kV 신용인-동서울T/L(태전) OPGW 증설공사","345kV 신용인-동서울T/L(태전) OPGW 증설공사 OPGW 120SQ 15km , 70SQ 30km 교체 및 증설","2016-10-17 07:00","2016-11-05 18:00","2016-10-17 07:00","2016-11-05 18:00","연속",null,null,null,201608030090]
[107,"경기","성남","신안성서안성#2 T/L","345kV 서안성-신진천T/L 피뢰기 설치공사","- 공사구간 : 서안성-신진천T/L No.36-98(63기) - 기타사항 : No.93-98 병가구간 신안성-서안성#2T/L 안전확보 휴전","2016-10-08 08:00","2016-10-08 18:00","2016-10-08 08:00","2016-10-08 18:00","연속",null,null,null,201609010044]
[108,"경기","성남","서안성S/S #3 M.Tr A","서안성S/S 345kV GIS 설치공사","345kV GIS 2CB 신설","2016-10-01 09:00","2016-10-03 18:00","2016-10-01 09:00","2016-10-03 18:00","연속",null,null,null,201608040012]
[109,"강원","강릉","동해신양양 T/L","2016년 가공송전 순시점검 위탁공사","○ 154kV 신양양-인제T/L 정밀점검 공사시 4회선 철탑 (4회선 철탑 정밀점검시 도급자 유도로 인한 휴전 요청)","2016-10-20 09:00","2016-10-20 18:00","2016-10-20 09:00","2016-10-20 18:00","당일",null,null,null,201608100356]
[110,"강원","강릉","신양양_양양PP T/L","2016년 가공송전 순시점검 위탁공사","○ 154kV 신양양-인제T/L 정밀점검 공사시 4회선 철탑 (4회선 철탑 정밀점검시 도급자 유도로 인한 휴전 요청)","2016-10-17 09:00","2016-10-17 18:00","2016-10-17 09:00","2016-10-17 18:00","당일",null,null,null,201608100355]
[111,"강원","동해","신제천동해#2 T/L","2016~17년도 동해전력지사 송전정비 협력회사 총액공사","1. 전선접속개소 전선교체(No.81~85, 155~157) 2. 송전선로용 피뢰기설치","2016-10-29 07:00","2016-11-18 18:00","2016-10-29 07:00","2016-11-18 18:00","연속",null,null,null,201608220141]
[112,"강원","동해","동해S/S 동해-북평TP#2T/L CB (7372)","2016년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해북평TP#2T/L GIS 초기점검(7372) 2. 동해S/S 동해북평TP#2T/L PT 초기점검 3. 동해S/S 동해북평TP#2T/L LS 초기점검","2016-10-11 09:30","2016-10-11 18:00","2016-10-11 09:30","2016-10-11 18:00","당일",null,null,null,201608120118]
[113,"강원","동해","신제천동해#1 T/L","2016~17년도 동해전력지사 송전정비 협력회사 총액공사","1. 전선접속개소 전선교체(No.81~85, 155~157)","2016-10-22 07:00","2016-10-28 18:00","2016-10-22 07:00","2016-10-28 18:00","연속",null,null,null,201608220138]
[114,"강원","동해","동해S/S 345kV #1 BUS","2016년 동해전력지사 변전협력회사 총액공사","1. 동해변전소 345kV #1 BUS PT 보통점검 2. 동해변전소 345kV #1 BUS 모선보호반 점검","2016-10-04 09:30","2016-10-04 13:30","2016-10-04 09:30","2016-10-04 13:30","당일",null,null,null,201608120101]
[115,"강원","동해","동해S/S 345kV #2 BUS","2016년 동해전력지사 변전협력회사 총액공사","1. 동해변전소 345kV #2 BUS 모선보호반 점검","2016-10-04 14:00","2016-10-04 18:00","2016-10-04 14:00","2016-10-04 18:00","당일",null,null,null,201608170156]
[116,"강원","동해","동해S/S 동해-북평TP#1T/L CB (7272)","2016년 동해전력지사 변전협력회사 총액공사","1. 동해S/S 동해북평TP#1T/L GIS 초기점검(7272) 2. 동해S/S 동해북평TP#1T/L PT 초기점검 3. 동해S/S 동해북평TP#1T/L LS 초기점검","2016-10-10 09:30","2016-10-10 18:00","2016-10-10 09:30","2016-10-10 18:00","당일",null,null,null,201608120117]
[117,"강원","동해","북평T/P 345kV #70 BUS","2016년 동해전력지사 변전협력회사 총액공사","1. 북평T/P 345kV #70 BUS PT 초기점검","2016-10-17 09:30","2016-10-17 13:00","2016-10-17 09:30","2016-10-17 13:00","당일",null,null,null,201608120157]
[118,"강원","동해","북평T/P 동해-북평TP #3T/L-TIE CB (7300)","동해P/O 관내 유압동작유 누유개소 제작사 보수","1. 북평TP 7300 CB부 유압동작유 누유개소 보수","2016-10-07 09:30","2016-10-07 16:00","2016-10-07 09:30","2016-10-07 16:00","당일",null,null,null,201608120114]
[119,"강원","동해","북평T/P 동해-북평TP #1T/L CB (7171)","2016년 동해전력지사 변전협력회사 총액공사","1. 북평T/P 동해북평TP#1T/L GIS 초기점검(7171) 2. 북평T/P 동해북평TP#1T/L PT 초기점검 3. 북평T/P 동해북평TP#1T/L LA 초기점검","2016-10-12 09:30","2016-10-12 18:00","2016-10-12 09:30","2016-10-12 18:00","당일",null,null,null,201608120121]
[120,"강원","동해","북평T/P 동해-북평TP #1T/L-#1STEP-UP CB (7100)","2016년 동해전력지사 변전협력회사 총액공사","1. 북평T/P 71BAY GIS 초기점검(7100)","2016-10-13 09:30","2016-10-13 18:00","2016-10-13 09:30","2016-10-13 18:00","당일",null,null,null,201608120122]
[121,"강원","동해","북평T/P 345kV #75 BUS","2016년 동해전력지사 변전협력회사 총액공사","1. 북평T/P 345kV #75 BUS PT 초기점검","2016-10-17 13:30","2016-10-17 18:00","2016-10-17 13:30","2016-10-17 18:00","당일",null,null,null,201608120130]
[122,"강원","동해","북평T/P #1STEP-UP Tr 1차 CB (7172)","2016년 동해전력지사 변전협력회사 총액공사","1. 북평T/P #1STEP-UP Tr 1차 GIS 초기점검(7172) 2. 북평T/P #1STEP-UP Tr 1차 PT 초기점검 3. 북평T/P #1STEP-UP Tr 1차 LA 초기점검","2016-10-14 09:30","2016-10-14 18:00","2016-10-14 09:30","2016-10-14 18:00","당일",null,null,null,201608120125]
[123,"강원","동해","삼척G/P 삼척GP-한울NP1 #1T/L CB (7571)","동해P/O 관내 유압동작유 누유개소 제작사 보수","1. 삼척G/P 7571 CB부 유압동작유 누유개소 보수","2016-10-06 09:30","2016-10-06 16:00","2016-10-06 09:30","2016-10-06 16:00","당일",null,null,null,201608120110]
[124,"강원","동해","삼척GP-한울NP1 #2T/L-#2M.Tr 1차 CB (7400)","동해P/O 관내 유압동작유 누유개소 제작사 보수","1. 삼척G/P 7400 CB부 유압동작유 누유개소 보수","2016-10-05 13:30","2016-10-05 18:00","2016-10-05 13:30","2016-10-05 18:00","당일",null,null,null,201608120109]
[125,"강원","동해","삼척G/P 삼척GP-한울NP1 #2T/L CB (7471)","동해P/O 관내 유압동작유 누유개소 제작사 보수","1. 삼척G/P 7471 CB부 유압동작유 누유개소 보수","2016-10-05 09:30","2016-10-05 13:00","2016-10-05 09:30","2016-10-05 13:00","당일",null,null,null,201608120108]
[126,"강원","태백","신태백S/S 345kV #3 Sh.R CB (7571)","신태백S/S 362kV GIS 정밀점검공사","7571CB 정밀점검","2016-10-13 09:00","2016-10-18 18:00","2016-10-13 09:00","2016-10-18 18:00","연속",null,null,null,201607150145]
[127,"강원","태백","신태백S/S 345kV #2 Sh.R","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","신태백S/S #2Sh.R 초기점검","2016-10-13 09:30","2016-10-13 18:00","2016-10-13 09:30","2016-10-13 18:00","당일",null,null,null,201608100124]
[128,"강원","태백","신태백S/S 345kV #1 BUS","신태백S/S 362kV GIS 정밀점검공사","7551DS 정밀점검","2016-10-18 09:00","2016-10-19 18:00","2016-10-18 09:00","2016-10-19 18:00","연속",null,null,null,201607060101]
[129,"강원","태백","신태백S/S 345kV #3 Sh.R","신태백S/S 362kV GIS 정밀점검공사","7579CB, 7561DS, 7501DS, 7521DS 정밀점검","2016-10-04 09:00","2016-10-12 18:00","2016-10-04 09:00","2016-10-12 18:00","연속",null,null,null,201607060102]
[130,"충북","직할","신제천신충주#1 T/L","2016년 가공송전선로 순시점검 위탁공사","정밀점검, 스페이서 점검","2016-10-11 08:00","2016-10-15 18:00","취소","취소","매일",null,null,null,201608090149]
[131,"충북","직할","신제천신충주#2 T/L","2016년 가공송전선로 순시점검 위탁공사","정밀점검, 스페이서 점검","2016-10-16 08:00","2016-10-20 18:00","취소","취소","매일",null,null,null,201608090150]
[132,"충북","직할","곤지암신충주#2 T/L","2016년 가공송전선로 순시점검 위탁공사","정밀점검, 스페이서 점검","2016-10-11 08:00","2016-10-15 18:00","취소","취소","매일",null,null,null,201608090162]
[133,"충북","직할","곤지암신충주#1 T/L","2016년 가공송전선로 순시점검 위탁공사","정밀점검, 스페이서 점검","2016-10-16 08:00","2016-10-20 18:00","취소","취소","매일",null,null,null,201608090163]
[134,"충북","청주","신옥천세종#2 T/L","345kV 신옥천-세종 #2T/L 피뢰기설치공사","피뢰기 설치(54기)","2016-10-05 07:00","2016-10-12 18:00","취소","취소","연속",null,null,null,201608040088]
[135,"충북","청주","세종청원#1 T/L","345kV 신옥천-세종 등 3개T/L 송전선로 피뢰기 설치공사","피뢰기 설치(26기)","2016-10-13 09:00","2016-10-18 18:00","2016-10-13 09:00","2016-10-18 18:00","연속",null,null,null,201608040092]
[136,"대전충남","서산","당진T/P #2M.Tr 1차 CB (7371)","당진T/P 345kV GIS 보통점검(7371)","○ 당진T/P 345kV GIS 보통점검(7371)","2016-10-12 09:00","2016-10-12 18:00","2016-10-12 09:00","2016-10-12 18:00","당일",null,null,null,201608120158]
[137,"대전충남","서산","당진T/P #2M.Tr 1차 - TIE CB (7300)","당진T/P 345kV GIS 보통점검(7300)","○ 당진T/P 345kV GIS 보통점검(7300)","2016-10-13 09:00","2016-10-13 18:00","2016-10-13 09:00","2016-10-13 18:00","당일",null,null,null,201608120159]
[138,"대전충남","서산","신당진개폐소 신당진연락#2T/L CB (7C72)","신당진개폐소 345kV GIS 초기점검(7C72)","○ 신당진개폐소 345kV GIS 초기점검(7C72)","2016-10-11 09:00","2016-10-11 18:00","2016-10-11 09:00","2016-10-11 18:00","당일",null,null,null,201608120156]
[139,"대전충남","서산","신당진S/S #3 M.Tr A","345kV 신당진S/S CLR 설치공사","- CLR 설치에 따른 Sh.R 이설작업","2016-10-17 09:00","2016-11-04 18:00","2016-10-17 09:00","2016-11-04 18:00","연속",null,null,null,201608040100]
[140,"대전충남","서산","신당진S/S #1 M.Tr A","345kV 신당진S/S CLR 설치공사","- CLR 설치에 따른 S.Tr 이설작업","2016-10-10 09:00","2016-10-14 18:00","2016-10-10 09:00","2016-10-14 18:00","연속",null,null,null,201608040099]
[141,"대전충남","서산","신서산신당진#2 T/L","345kV 신서산-신당진#2T/L 정밀점검","[송전] 345kV 신서산-신당진#2T/L 정밀점검 No.1~42 (No.2~32, 345kV신서산-아산 병가구간)","2016-10-17 07:30","2016-10-18 18:00","2016-10-17 07:30","2016-10-18 18:00","매일",null,null,null,201608110310]
[142,"대전충남","서산","신서산S/S 345kV #4 Sh.R","신서산S/S 345kV #4Sh.R 보통점검","○ 신서산S/S 345kV #4Sh.R 보통점검","2016-10-12 09:00","2016-10-12 18:00","2016-10-12 09:00","2016-10-12 18:00","당일",null,null,null,201608120170]
[143,"대전충남","서산","신서산S/S 345kV #5 Sh.R","신서산S/S 345kV #5Sh.R 보통점검","○ 신서산S/S 345kV #5Sh.R 보통점검","2016-10-13 09:00","2016-10-13 18:00","2016-10-13 09:00","2016-10-13 18:00","당일",null,null,null,201608120176]
[144,"대전충남","서산","신서산신당진#1 T/L","345kV 신서산-신당진#1T/L 정밀점검","[송전] 345kV 신서산-신당진#1T/L 정밀점검 No.1~42 (No.2~32, 345kV신서산-아산 병가구간)","2016-10-19 07:30","2016-10-20 18:00","2016-10-19 07:30","2016-10-20 18:00","매일",null,null,null,201608110309]
[145,"대전충남","서산","신서산S/S #3 Sh.R-신서산태안TP#2T/L CB (7500)","신서산S/S 345kV GIS 보통점검(7500)","○ 신서산S/S 345kV GIS 보통점검(7500)","2016-10-18 09:00","2016-10-18 18:00","2016-10-18 09:00","2016-10-18 18:00","당일",null,null,null,201608120162]
[146,"대전충남","서산","태안T/P 4호기 1차 CB (7472)","태안화력 345kV 장기사용 GIS 교체공사","1.74BAY GIS (7472,7400) 철거(40KA 4000A) 2.74BAY GIS (7472,7400) 신품설치 (63KA 6300A)","2016-10-21 08:00","2016-12-04 18:00","2016-10-21 08:00","2016-12-04 18:00","연속",null,null,null,201607070123]
[147,"대전충남","서산","태안T/P TIE-4호기 1차 CB (7400)","태안화력 345kV 장기사용 GIS 교체공사","1. 74BAY GIS(7472,7400) 철거(40KA, 4000A) 2. 74BAY GIS(7472,7400) 신품설치(63KA 6300A)","2016-10-21 08:00","2016-12-04 18:00","2016-10-21 08:00","2016-12-04 18:00","연속",null,null,null,201608160170]
[148,"대전충남","서산","태안T/P 7호기 1차 CB (7772)","태안T/P 345kV GIS 보통점검(7772)","○ 태안T/P 345kV GIS 보통점검(7772)","2016-10-04 09:00","2016-10-04 18:00","2016-10-04 09:00","2016-10-04 18:00","당일",null,null,null,201608120167]
[149,"대전충남","서산","태안T/P TIE-7호기 1차 CB (7700)","태안T/P 345kV GIS 보통점검(7700)","○ 태안T/P 345kV GIS 보통점검(7700)","2016-10-05 09:00","2016-10-05 18:00","2016-10-05 09:00","2016-10-05 18:00","당일",null,null,null,201608120168]
[150,"대전충남","서산","태안T/P 345kV #70 BUS","태안화력 345kV 장기사용 GIS 교체공사","1.72BAY GIS(7272,7200,7271) 철거(40KA, 4000A) 2 72BAY GIS(7272,7200) 설치(60kA, 6000A) 3 72BAY GIS(70BUS)철거,설치 4 72BAY GIS(75BUS)철거,설치","2016-10-12 14:00","2016-10-14 14:00","2016-10-12 14:00","2016-10-14 14:00","연속",null,null,null,201607210034]
[151,"대전충남","서산","태안T/P 345kV #75 BUS","태안화력 345kV 장기사용 GIS 교체공사","1.74BAY GIS(7472,7400) 철거(40KA, 4000A) 2 74BAY GIS(7472,7400) 설치(60kA, 6000A) 3 74BAY GIS(70BUS)철거,설치 4 74BAY GIS(75BUS)철거,설치","2016-10-30 09:00","2016-11-11 18:00","2016-10-30 09:00","2016-11-11 18:00","연속",null,null,null,201607120101]
[152,"대전충남","서산","태안T/P #1M.Tr-8호기 1차 CB (7800)","태안T/P 345kV GIS 보통점검(7800)","○ 태안T/P 345kV GIS 보통점검(7800)","2016-10-25 09:00","2016-10-25 18:00","2016-10-25 09:00","2016-10-25 18:00","당일",null,null,null,201608120163]
[153,"대전충남","서산","태안T/P 8호기 1차 CB (7872)","태안T/P 345kV GIS 보통점검(7872)","○ 태안T/P 345kV GIS 보통점검(7872)","2016-10-24 09:00","2016-10-24 18:00","2016-10-24 09:00","2016-10-24 18:00","당일",null,null,null,201608120165]
[154,"대전충남","아산","청양신온양#1 T/L","[송전] 345kV 청양-신온양T/L 전선교체공사","[송전] 345kV 청양-신온양T/L 전선교체공사 - No.64~68 15가닥 전선교체(#1T/L 11가닥, #2T/L 4가닥) - No.79~84 2가닥 전선교체(#1T/L 2가닥)","2016-10-04 07:00","2016-10-12 18:00","2016-10-04 07:00","2016-10-12 18:00","연속",null,null,null,201607200012]
[155,"대전충남","아산","청양신온양#2 T/L","[송전] 345kV 청양-신온양T/L 전선교체공사","[송전] 345kV 청양-신온양T/L 전선교체공사 - No.64~68 12가닥 전선교체(#1T/L 11가닥, #2T/L 4가닥) - No.79~84 2가닥 전선교체(#1T/L 2가닥)","2016-10-13 07:00","2016-10-17 18:00","2016-10-13 07:00","2016-10-17 18:00","연속",null,null,null,201608110165]
[156,"대전충남","아산","아산보령화력#1 T/L","345kV 아산보령화력T/L 전선교체공사","점퍼선 혼촉개소 정비 : 37,89,104호 이도 조정 : 39~40, 185~186","2016-10-01 07:00","2016-10-02 18:00","2016-10-01 07:00","2016-10-02 18:00","매일",null,null,null,201608040040]
[157,"대전충남","아산","아산보령화력#2 T/L","345kV 아산보령화력T/L 전선교체공사","이도 조정 : 153~54,185~186","2016-10-03 07:00","2016-10-04 18:00","2016-10-03 07:00","2016-10-04 18:00","매일",null,null,null,201608110458]
[158,"대전충남","아산","신서산아산#2 T/L","[송전] 345kV 신서산-아산#2T/L 정밀점검","345kV 신서산-아산#2T/L 정밀점검 - 구간 : 6~31호","2016-10-19 07:00","2016-10-20 18:00","2016-10-19 07:00","2016-10-20 18:00","매일",null,null,null,201608110313]
[159,"대전충남","아산","신서산아산#1 T/L","[송전] 345kV 신서산-아산#1T/L 정밀점검","345kV 신서산-아산#1T/L 정밀점검 - 구간 : 6~31호","2016-10-12 07:00","2016-10-18 18:00","2016-10-12 07:00","2016-10-18 18:00","매일",null,null,null,201608110314]
[160,"대전충남","청양","보령T/P 345kV #75 BUS","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 75-76-0 GIS 교체","2016-10-28 09:00","2016-11-09 18:00","2016-10-28 09:00","2016-11-09 18:00","연속",null,null,null,201608120037]
[161,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 75-76-0 GIS 교체","2016-10-05 09:00","2016-10-07 18:00","2016-10-05 09:00","2016-10-07 18:00","연속",null,null,null,201608120025]
[162,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 75-76-0 GIS 교체","2016-10-28 09:00","2016-11-09 18:00","2016-10-28 09:00","2016-11-09 18:00","연속",null,null,null,201608120036]
[163,"대전충남","청양","보령T/P 345kV #75 BUS","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 75-76-0 GIS 교체","2016-10-05 09:00","2016-10-07 18:00","2016-10-05 09:00","2016-10-07 18:00","연속",null,null,null,201608120023]
[164,"대전충남","청양","보령T/P 75-76-0 SEC CB (75-76-0)","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 75-76-0 GIS 교체","2016-10-05 09:00","2016-11-09 18:00","2016-10-05 09:00","2016-11-09 18:00","연속",null,null,null,201608120031]
[165,"대전충남","청양","청양S/S #1 M.Tr A","청양S/S 345kV 76BAY BF 보호배전반 교체","○ 345kV 76BAY BF 보호배전반 교체","2016-10-24 09:00","2016-10-27 18:00","2016-10-24 09:00","2016-10-27 18:00","연속",null,null,null,201607050078]
[166,"대전충남","청양","청양보령TP#2 T/L","청양S/S 345kV 76BAY BF 보호배전반 교체","○ 345kV 76BAY BF 보호배전반 교체","2016-10-24 09:00","2016-10-27 18:00","2016-10-24 09:00","2016-10-27 18:00","연속",null,null,null,201607050079]
[167,"전북","군산","군산S/S 군산-새만금#1T/L CB (7771)","345kV 군산S/S S/W증설공사","송전선로 인출 압축인류클램프 시공 및 CVT_LA 배선","2016-10-25 09:00","2016-10-25 18:00","2016-10-25 09:00","2016-10-25 18:00","당일",null,null,null,201608170189]
[168,"전북","군산","군산S/S #3 M.Tr 1차-TIE CB (7700)","345kV 군산S/S S/W증설공사","송전선로 인출 압축인류클램프 시공 및 CVT_LA 배선","2016-10-25 09:00","2016-10-25 18:00","2016-10-25 09:00","2016-10-25 18:00","당일",null,null,null,201608170187]
[169,"전북","군산","군산S/S 군산-새만금#2T/L CB (7871)","345kV 군산S/S S/W증설공사","송전선로 인출 압축인류클램프 시공 및 CVT_LA 배선","2016-10-26 09:00","2016-10-26 18:00","2016-10-26 09:00","2016-10-26 18:00","당일",null,null,null,201608170190]
[170,"전북","군산","군산S/S #4 M.Tr 1차-TIE CB (7800)","345kV 군산S/S S/W증설공사","송전선로 인출 압축인류클램프 시공 및 CVT_LA 배선","2016-10-26 09:00","2016-10-26 18:00","2016-10-26 09:00","2016-10-26 18:00","당일",null,null,null,201608170191]
[171,"전북","군산","군산S/S #1 M.Tr A","군산S/S #1 M.Tr A","1. 345kV 예비변압기 절제보호반 설치","2016-10-04 09:00","2016-10-05 18:00","2016-10-04 09:00","2016-10-05 18:00","연속",null,null,null,201608160106]
[172,"전북","군산","군산S/S #2 M.Tr A","군산S/S #2 M.Tr A","1. 345kV 예비변압기 절제보호반 설치","2016-10-06 09:00","2016-10-07 18:00","2016-10-06 09:00","2016-10-07 18:00","연속",null,null,null,201608160107]
[173,"전북","군산","군산S/S #3 M.Tr A","군산S/S #3 M.Tr A","1. 345kV 예비변압기 절제보호반 설치","2016-10-10 09:00","2016-10-11 18:00","2016-10-10 09:00","2016-10-11 18:00","연속",null,null,null,201608160108]
[174,"전북","군산","군산S/S #4 M.Tr A","군산S/S #4 M.Tr A","1. 345kV 예비변압기 절제보호반 설치","2016-10-12 09:00","2016-10-13 18:00","2016-10-12 09:00","2016-10-13 18:00","연속",null,null,null,201608160109]
[175,"전북","김제","신김제S/S #3 M.Tr A","신김제S/S #3 M.Tr A","변압기 정밀점검","2016-10-31 09:00","2016-11-04 18:00","2016-10-31 09:00","2016-11-04 18:00","연속",null,null,null,201608170101]
[176,"전북","김제","신김제S/S CB 7372","신김제S/S M.Tr(예비)","변압기 누유보수","2016-10-17 09:00","2016-10-21 18:00","2016-10-17 09:00","2016-10-21 18:00","연속",null,null,null,201608100062]
[177,"전북","김제","신김제S/S #2 M.Tr A","신김제S/S #2 M.Tr A","변압기 보호반 교체 및 변압기 보통점검","2016-10-17 09:00","2016-10-21 18:00","2016-10-17 09:00","2016-10-21 18:00","연속",null,null,null,201608170094]
[178,"전북","김제","신김제S/S #1 M.Tr A","신김제S/S #1 M.Tr A","변압기 보통점검","2016-10-04 09:00","2016-10-05 18:00","2016-10-04 09:00","2016-10-05 18:00","연속",null,null,null,201608170091]
[179,"전북","직할","신남원S/S CB 7200","2016년 전북직할 345kV 차단기 정밀점검(7200)공사","-. 345kV GIS(차단기) 정밀점검공사","2016-10-10 09:30","2016-10-13 18:00","2016-10-10 09:30","2016-10-13 18:00","연속",null,null,null,201608160094]
[180,"전북","직할","신옥천신남원#1 T/L","2016년 전북직할 345kV 차단기 정밀점검공사","-. 345kV GIS(차단기) 정밀점검공사 관련 무부하 시험가압","2016-10-13 10:00","2016-10-13 14:00","2016-10-13 10:00","2016-10-13 14:00","당일",null,null,null,201608160095]
[181,"전북","직할","신남원S/S CB 7272","2016년 전북직할 345kV 차단기 정밀점검(7272)공사","-. 345kV GIS(차단기) 정밀점검공사","2016-10-17 09:30","2016-10-20 18:00","2016-10-17 09:30","2016-10-20 18:00","연속",null,null,null,201608160110]
[182,"전북","직할","신옥천신남원#1 T/L","2016년 전북직할 345kV 차단기 정밀점검공사","-. 345kV GIS(차단기) 정밀점검공사 관련 무부하 시험가압","2016-10-20 10:00","2016-10-20 14:00","2016-10-20 10:00","2016-10-20 14:00","당일",null,null,null,201608160111]
[183,"전북","직할","신남원S/S 신남원-의 령#2 - TIE GIS","2016년 전북직할 345kV 차단기 정밀점검(7400)공사","-. 345kV GIS(차단기) 정밀점검공사","2016-10-24 09:30","2016-10-27 18:00","취소","취소","연속",null,null,null,201608160113]
[184,"전북","직할","신남원의령#1 T/L","2016년 전북직할 345kV 차단기 정밀점검공사","-. 345kV GIS(차단기) 정밀점검공사 관련 무부하 시험가압","2016-10-07 10:00","2016-10-07 14:00","2016-10-07 10:00","2016-10-07 14:00","당일",null,null,null,201608160091]
[185,"전북","직할","신남원의령#2 T/L","2016년 전북직할 345kV 차단기 정밀점검(7471)공사","-. 345kV GIS(차단기) 정밀점검공사","2016-10-31 09:30","2016-11-03 18:00","2016-10-31 09:30","2016-11-03 18:00","연속",null,null,null,201608160120]
[186,"전북","직할","신남원한빛NP#1 T/L","345kV 신남원-한빛#1T/L 전선교체 등 3개 공사","전선교체 : 20~58호 6.971C-km 사선애자청소 : 21~81호 61기 항공장애표시구 교체 : 87~163호 31개 경간","2016-10-31 07:00","2016-11-17 18:00","2016-10-31 07:00","2016-11-17 18:00","연속",null,null,null,201608110148]
[187,"전북","직할","신남원의령#2 T/L","2016년 전북직할 345kV 차단기 정밀점검공사","-. 345kV GIS(차단기) 정밀점검공사 관련 무부하 시험가압","2016-10-27 10:00","2016-10-27 14:00","취소","취소","당일",null,null,null,201608160115]
[188,"전북","직할","신남원S/S CB 7300","2016년 전북직할 345kV 차단기 정밀점검(7300)공사","-. 345kV GIS(차단기) 정밀점검공사","2016-10-04 09:30","2016-10-07 18:00","2016-10-04 09:30","2016-10-07 18:00","연속",null,null,null,201608160087,"○"]
[189,"광주전남","광주","신광주S/S #1 M.Tr A","신광주S/S #1M.Tr(3차 DS,VCB 점검등)","VCB 4189 보통점검 DS 4175-1,2, 4185, 4186 보통점검 #1M.Tr 3차 LA 대체","2016-10-24 09:00","2016-10-25 18:00","취소","취소","연속",null,null,null,201608030037]
[190,"광주전남","목포","한빛1N/P 한빛연락#1T/L","345kV 한빛연락#1T/L(362kV GIS 보통점검)","362kV GIS 보통점검","2016-10-20 09:00","2016-10-26 18:00","2016-10-20 09:00","2016-10-21 18:00","연속",null,null,null,201608160006]
[191,"광주전남","목포","신남원-한빛#2T/L","345kV 신남원-한빛#2T/L(보호배전반 대체공사)","- 345kV 송전선로 보호배전반 대체(2면) - 기타 GIS 보통점검","2016-10-24 09:00","2016-11-04 18:00","2016-10-24 09:00","2016-11-04 18:00","연속",null,null,null,201608160003]
[192,"광주전남","목포","신남원-한빛#1T/L","345kV 신남원-한빛#1T/L(보호배전반 대체공사)","345kV 송전선로 보호배전반 대체(2면)","2016-10-10 09:00","2016-10-21 18:00","2016-10-10 09:00","2016-10-19 18:00","연속",null,null,null,201608160002]
[193,"광주전남","순천","광양하동화력#1 T/L","345kV 광양-하동TP#1T/L(송전선로 피뢰기 설치)","피뢰기 설치 : 26~73호, 48기","2016-10-30 07:00","2016-10-31 18:00","2016-10-30 07:00","2016-10-31 18:00","연속",null,null,null,201608120129]
[194,"광주전남","순천","신강진광양#2 T/L","345kV 신강진-광양#2T/L(광양-하동TP#1T/L 4회선 병가구간)","광양-하동TP#1T/L 4회선 병가구간","2016-10-30 07:00","2016-10-30 18:00","2016-10-30 07:00","2016-10-30 18:00","당일",null,null,null,201608120132]
[195,"광주전남","순천","광양S/S 345kV #75 BUS","345kV 광양S/S 362kV GIS 대체공사","가. GIS(345kV 50kA 4000A) ×27 CB 철거 나. GIS(345kV 63kA 6300A) ×27 CB 설치 다. 기타 부대작업 × 1식","2016-10-17 09:00","2016-10-20 18:00","2016-10-17 09:00","2016-10-20 18:00","연속",null,null,null,201608170169]
[196,"광주전남","순천","광양율촌CC T/L","345kV 광양S/S 362kV GIS 대체공사","가. GIS(345kV 50kA 4000A) ×27 CB 철거 나. GIS(345kV 63kA 6300A) ×27 CB 설치 다. 기타 부대작업 × 1식","2016-10-21 09:00","2017-01-20 18:00","2016-10-21 09:00","2017-01-20 18:00","연속",null,null,null,201608170170]
[197,"광주전남","순천","여수T/P #3 Tie-Tr","여수T/P 345kV #3M.Tr(1차 GIS 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 1차 GIS(7300,7372 GIS 보통점검)","2016-10-24 10:00","2016-10-25 18:00","2016-10-24 10:00","2016-10-25 18:00","연속",null,null,null,201608120086]
[198,"대구경북","경산","신경산S/S 345kV #2 BUS","신경산S/S 노후배전반 대체공사","모자익판넬 대체","2016-10-12 09:00","2016-10-12 18:00","2016-10-12 09:00","2016-10-12 18:00","당일",null,null,null,201608080190]
[199,"대구경북","경산","신경산S/S 345kV #1 BUS","신경산S/S 노후배전반 대체공사","모자익판넬 대체","2016-10-11 09:00","2016-10-11 18:00","2016-10-11 09:00","2016-10-11 18:00","당일",null,null,null,201608080189]
[200,"대구경북","구미","서대구선산#1 T/L","2016년 가공송전설비 순시점검 위탁공사","345kV 서대구-선산T/L 초기점검 o No.28~60 2회선 o No.61~64 4회선(칠곡-인동 병가) o No.65~71 4회선(산동-군위 병가) o No.74~106 4회선(선산분기 병가)","2016-10-04 09:00","2016-10-08 18:00","2016-10-04 09:00","2016-10-08 18:00","매일",null,null,null,201607110170]
[201,"대구경북","구미","북대구선산 T/L","2016년 가공송전설비 순시점검 위탁공사","345kV 서대구-선산T/L 초기점검 o No.28~60 2회선 o No.61~64 4회선(칠곡-인동 병가) o No.65~71 4회선(산동-군위 병가) o No.74~106 4회선(선산분기 병가, 하단)","2016-10-04 09:00","2016-10-06 18:00","2016-10-04 09:00","2016-10-06 18:00","매일",null,null,null,201607110180]
[202,"대구경북","구미","서대구선산#2 T/L","2016년 가공송전설비 순시점검 위탁공사","345kV 서대구-선산T/L 초기점검 o No.28~60 2회선 o No.61~64 4회선(칠곡-인동 병가) o No.65~71 4회선(산동-군위 병가) o No.74~106 4회선(선산분기 병가)","2016-10-10 09:00","2016-10-14 18:00","2016-10-10 09:00","2016-10-14 18:00","매일",null,null,null,201607110171]
[203,"대구경북","구미","선산신포항 T/L","2016년 가공송전설비 순시점검 위탁공사","345kV 서대구-선산T/L 초기점검 o No.28~60 2회선 o No.61~64 4회선(칠곡-인동 병가) o No.65~71 4회선(산동-군위 병가) o No.74~106 4회선(선산분기 병가, 하단)","2016-10-10 09:00","2016-10-12 18:00","2016-10-10 09:00","2016-10-12 18:00","매일",null,null,null,201607110183]
[204,"대구경북","구미","선산S/S #3 M.Tr A","선산S/S 345kV #3 M.TR","- 7472GIS 보통점검 - 3차 LA 하자점검","2016-10-24 09:00","2016-10-24 18:00","2016-10-24 09:00","2016-10-24 18:00","당일",null,null,null,201608020007]
[205,"대구경북","구미","선산S/S #4 M.Tr A","선산S/S 345kV #4 M.TR","- 7700,7772GIS 보통점검","2016-10-25 09:00","2016-10-26 18:00","2016-10-25 09:00","2016-10-26 18:00","연속",null,null,null,201608030035]
[206,"대구경북","달성","고령S/S #2 M.Tr A","변압기 보호반대체 및 누유개소보수","보호반대체 및 누유개소보수","2016-10-07 09:00","2016-10-09 18:00","2016-10-07 09:00","2016-10-09 18:00","연속",null,null,null,201608080027]
[207,"대구경북","달성","대구S/S 345kV #1 Sh.R","대구S/S #1Sh.R 휴전","#1Sh.R 및 GIS보통점검","2016-10-10 09:30","2016-10-10 18:00","2016-10-10 09:30","2016-10-10 18:00","당일",null,null,null,201608080025]
[208,"대구경북","안동","안동복합S/Y 345kV #1 BUS","안동CC BUS PT GIS 하자점검","안동CC BUS PT GIS 하자점검","2016-10-28 09:00","2016-10-28 14:00","2016-10-28 09:00","2016-10-28 14:00","당일",null,null,null,201608100159]
[209,"대구경북","안동","안동복합S/Y 345kV #2 BUS","안동CC BUS PT GIS 하자점검","안동CC BUS PT GIS 하자점검","2016-10-28 14:00","2016-10-28 18:00","2016-10-28 14:00","2016-10-28 18:00","당일",null,null,null,201608100161]
[210,"대구경북","영주","신영주한울NP2#1 T/L","신영주S/S 362kV GIS화 공사","○ 임시제어동 철거를 위한 안전이격 확보","2016-10-28 08:00","2016-10-29 18:00","2016-10-28 08:00","2016-10-29 18:00","연속",null,null,null,201608040030]
[211,"대구경북","영주","신영주청송PP T/L","신영주S/S 362kV GIS화 공사","○ 임시제어동 철거를 위한 안전이격 확보","2016-10-26 08:00","2016-10-27 18:00","2016-10-26 08:00","2016-10-27 18:00","연속",null,null,"조건부 승인",201608040029]
[212,"대구경북","영주","신영주예천PP#2 T/L","신영주S/S 362kV GIS화 공사","○ 임시제어동 철거를 위한 안전이격확보","2016-10-24 09:00","2016-10-25 18:00","2016-10-24 09:00","2016-10-25 18:00","연속",null,null,null,201608160001]
[213,"대구경북","영주","신영주S/S 345kV #1 BUS","신영주S/S 362kV GIS화 공사","○ 인출 DS 리드철거를 위한 안전이격 확보","2016-10-02 08:00","2016-10-02 18:00","2016-10-02 08:00","2016-10-02 18:00","연속",null,null,null,201608040036]
[214,"대구경북","영주","신영주한울NP2#2 T/L","신영주S/S 362kV GIS화 공사","○ 부하전환(옥외철구 → GIS) - 보호반 이설, 송전선로 인출 리드 연장, 옥외철구설비 철거","2016-10-02 08:00","2016-10-12 18:00","2016-10-02 08:00","2016-10-12 18:00","연속",null,null,null,201608040033]
[215,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","○ #2BUS 모선연계용 ACSR 및 옥외철구 #2BUS 철거 ○ GIS 모선보호반 단독운전을 위한 CT비 변경(4000/5 → 6000/5)","2016-10-16 08:00","2016-10-18 18:00","2016-10-16 08:00","2016-10-18 18:00","연속",null,null,null,201606120019]
[216,"대구경북","영주","신제천신영주#1 T/L","신영주S/S 362kV GIS화 공사","부하전환(보호반 이설)","2016-10-13 08:00","2016-10-23 18:00","2016-10-13 08:00","2016-10-23 18:00","연속",null,null,null,201606120017]
[217,"대구경북","영주","신영주S/S 345kV #1 BUS","신영주S/S 362kV GIS화 공사","○ #1BUS 모선연계용 ACSR 및 POST. 옥외철구 #1BUS 철거 ○ GIS 모선보호반 단독운전을 위한 CT비 변경(4000/5 → 6000/5)","2016-10-13 08:00","2016-10-15 18:00","2016-10-13 08:00","2016-10-15 18:00","연속",null,null,null,201606120018]
[218,"대구경북","영주","신영주S/S 345kV #2 BUS","신영주S/S 362kV GIS화 공사","송전선로 연장 및 가공지선 신규 설치","2016-10-04 08:00","2016-10-08 18:00","2016-10-04 08:00","2016-10-08 18:00","연속",null,null,null,201606120015]
[219,"대구경북","영주","신영주한울NP2#2 T/L","신영주S/S 362kV GIS화 공사","부하전환 및 송전선로 인출변경","2016-10-02 08:00","2016-10-12 18:00","취소","취소","연속",null,null,"한전요청",201606120013]
[220,"대구경북","영주","신영주S/S #1 M.Tr A","신영주S/S 362kV GIS화 공사","부하전환(보호반 이설)","2016-10-02 08:00","2016-10-12 18:00","2016-10-02 08:00","2016-10-12 18:00","연속",null,null,null,201606120016]
[221,"대구경북","칠곡","신포항북대구 T/L","신포항-북대구T/L 보호반 대체","신포항-북대구T/L 보호반 대체","2016-10-30 09:30","2016-11-04 18:00","2016-10-30 09:30","2016-11-04 18:00","연속",null,null,null,201608090085]
[222,"대구경북","칠곡","서대구S/S 345kV #1 BUS","서대구S/S #1BUS LA,PT 초기점검","서대구S/S #1BUS LA,PT 초기점검","2016-10-13 09:00","2016-10-13 18:00","2016-10-13 09:00","2016-10-13 18:00","당일",null,null,null,201608090082]
[223,"대구경북","칠곡","북대구서대구#1 T/L","서대구S/S 북대구-서대구#1T/L PT교체","서대구S/S 북대구-서대구#1T/L PT교체","2016-10-17 09:30","2016-10-17 18:00","2016-10-17 09:30","2016-10-17 18:00","당일",null,null,null,201608090079]
[224,"대구경북","칠곡","서대구S/S #1M.Tr A","#1M.Tr C상 가스 발생관련 내부점검","#1M.Tr C상 가스 발생관련 내부점검","2016-10-17 09:30","2016-10-20 18:00","2016-10-17 09:30","2016-10-20 18:00","연속",null,null,null,201608250046]
[225,"대구경북","포항","신포항신월성NP#2 T/L","신월성S/Y 신포항-신월성#2T/L 휴전작업","7571 GIS, PT 보통점검","2016-10-26 09:30","2016-10-26 18:00","2016-10-26 09:30","2016-10-26 18:00","당일",null,null,"조건부 승인",201608100287]
[226,"대구경북","포항","신포항신월성NP#1 T/L","신월성S/Y 신포항-신월성#1T/L 휴전작업","7500, 7572 GIS, PT 보통점검","2016-10-25 09:30","2016-10-25 18:00","2016-10-25 09:30","2016-10-25 18:00","당일",null,null,"조건부 승인",201608100284,"○"]
[227,"대구경북","포항","신포항신영일 T/L","신포항S/S 신포항-신영일T/L 휴전작업","7171 CB, PT, LA A,B,C 보통점검","2016-10-19 09:00","2016-10-19 18:00","2016-10-19 09:00","2016-10-19 18:00","당일",null,null,"조건부 승인",201608100282]
[228,"대구경북","포항","신포항S/S #4 M.Tr A","신포항S/S #4M.Tr 휴전작업","7772, 6444 CB 보통점검","2016-10-18 09:00","2016-10-18 18:00","2016-10-18 09:00","2016-10-18 18:00","당일",null,null,null,201608100280]
[229,"부산울산","동부산","신양산S/S #4 M.Tr A","신양산S/S 345kV #4M.Tr 누유개소 보수","신양산S/S 345kV #4M.Tr 누유개소 보수(C상 상부)","2016-10-12 09:00","2016-10-14 18:00","2016-10-12 09:00","2016-10-14 18:00","연속",null,null,null,201608110412]
[230,"부산울산","북부산","북부산S/S 75-76 BUS-SEC CB (75-76-0)","2016년 북부산변전협력회사 총액공사","75-76-0 GIS 하자점검","2016-10-04 14:00","2016-10-04 18:00","2016-10-04 14:00","2016-10-04 18:00","당일",null,null,null,201608110246]
[231,"부산울산","북부산","북부산S/S 70-71 BUS-SEC CB (70-71-0)","2016년 북부산변전협력회사 총액공사","70-71-0 GIS 하자점검","2016-10-04 09:30","2016-10-04 14:00","2016-10-04 09:30","2016-10-04 14:00","당일",null,null,null,201608110244]
[232,"부산울산","북부산","북부산신온산 T/L","345kV 북부산-울산화력 등 2개T/L 전선접속개소 전선교체공사","70-71-0 GIS 하자점검","2016-10-04 08:00","2016-10-18 18:00","2016-10-04 08:00","2016-10-18 18:00","연속",null,null,null,201608080173]
[233,"부산울산","북부산","신김해북부산#2 T/L","16년 가공송전설비 위탁업체 공사","ㅇ 초기점검 - 구간 : No.16~19호(4기)","2016-10-03 08:00","2016-10-03 18:00","2016-10-03 08:00","2016-10-03 18:00","당일",null,null,null,201608050076]
[234,"부산울산","북부산","북부산S/S #4 M.Tr A","345kV 북부산S/S 차단기용량대체 공사","345kV GIS 기초보강 PHC파일 작업 안전이격확보","2016-10-20 09:00","2016-10-26 18:00","2016-10-20 09:00","2016-10-26 18:00","연속",null,null,null,201608100032]
[235,"부산울산","서부산","서부산S/S #2 M.Tr A","서부산s/s #71Bay B/F PNL 대체","서부산s/s #71Bay B/F PNL 대체 (#2M.Tr, 서부산-북부산#1T/L 휴전)","2016-10-05 10:00","2016-10-10 18:00","2016-10-05 10:00","2016-10-10 18:00","연속",null,null,null,201608100119]
[236,"부산울산","서부산","서부산북부산#2 T/L","서부산s/s #72Bay B/F PNL 대체","서부산s/s #72Bay B/F PNL 대체 (서부산s/s #1M.Tr PNL 대체 병행 진행)","2016-10-11 10:00","2016-10-18 18:00","2016-10-11 10:00","2016-10-18 18:00","연속",null,null,null,201608100129]
[237,"부산울산","서부산","서부산S/S #1 M.Tr A","서부산s/s #72Bay B/F PNL 대체","서부산s/s #72Bay B/F PNL 대체 (서부산s/s #1M.Tr PNL 대체 병행 진행)","2016-10-11 10:00","2016-10-18 18:00","2016-10-11 10:00","2016-10-18 18:00","연속",null,null,null,201608100128]
[238,"부산울산","서부산","서부산북부산#1 T/L","서부산s/s #71Bay B/F PNL 대체","서부산s/s #71Bay B/F PNL 대체 (#2M.Tr, 서부산-북부산#1T/L 휴전)","2016-10-05 10:00","2016-10-10 18:00","2016-10-05 10:00","2016-10-10 18:00","연속",null,null,null,201608100115]
[239,"부산울산","울산","신온산S/S #3 M.Tr A","신온산S/S 154kV #2Sh.C 고장 복구","#2Sh.C 전력케이블 C/H 설치관련 안전이격거리 확보차","2016-10-04 09:00","2016-10-04 18:00","2016-10-04 09:00","2016-10-04 18:00","당일",null,null,null,201608100388]
[240,"부산울산","울산","신울산S/S 345kV #75BUS","2016년 362kV 개폐장치 정밀점검 공사","신울산S/S 7572 CB 시험가압","2016-10-12 17:00","2016-10-12 18:00","2016-10-12 17:00","2016-10-12 18:00","당일",null,null,null,201608090401]
[241,"부산울산","울산","신울산S/S 345kV #75BUS","2016년 362kV 개폐장치 정밀점검 공사","신울산S/S 7672 CB 시험가압","2016-10-01 17:00","2016-10-01 18:00","2016-10-01 17:00","2016-10-01 18:00","당일",null,null,null,201608090400]
[242,"부산울산","울산","북부산신울산#1 T/L","2016년 362kV 개폐장치 정밀점검 공사","신울산 7672 CB 시험가압","2016-10-01 17:00","2016-10-01 18:00","2016-10-01 17:00","2016-10-01 18:00","당일",null,null,null,201608090402,"○"]
[243,"부산울산","울산","북부산신울산#1 T/L","2016년 362kV 개폐장치 정밀점검 공사","신울산 7572 GCB 시험가압","2016-10-12 17:00","2016-10-12 18:00","2016-10-12 17:00","2016-10-12 18:00","당일",null,null,null,201608090398]
[244,"부산울산","울산","신울산S/S 신울산-고리NP#1T/L CB (7572)","2016년 362kV 개폐장치 정밀점검 공사","신울산 7572 GCB 정밀점검","2016-10-10 08:00","2016-10-12 18:00","2016-10-10 08:00","2016-10-12 18:00","연속",null,null,null,201608090392]
[245,"부산울산","울산","북부산신울산#1 T/L","2016년 362kV 개폐장치 정밀점검 공사","신울산 7400 GCB 시험가압","2016-10-06 17:00","2016-10-06 18:00","2016-10-06 17:00","2016-10-06 18:00","당일",null,null,null,201608090396]
[246,"부산울산","울산","신울산S/S 북부산-신울산#1T/L TIE CB (7400)","2016년 362kV 개폐장치 정밀점검 공사","신울산 7400 GCB 정밀점검","2016-10-04 08:00","2016-10-06 18:00","2016-10-04 08:00","2016-10-06 18:00","연속",null,null,null,201608090388]
[247,"부산울산","울산","울산C/C #1 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 #1M.Tr 보통점검, 7400,7471,6144,4184 GIS 보통점검","2016-10-19 09:00","2016-10-20 18:00","2016-10-19 09:00","2016-10-20 18:00","연속",null,null,null,201608180137]
[248,"부산울산","울산","울산C/C #2 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 #2M.Tr 보통점검, 7871,6244,4284 GIS 보통점검","2016-10-26 09:00","2016-10-27 18:00","2016-10-26 09:00","2016-10-27 18:00","연속",null,null,null,201608180138]
[249,"부산울산","울산","울주S/S #4 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","울주S/S 78Bay B/F PNL 대체","2016-10-17 09:00","2016-10-23 18:00","2016-10-17 09:00","2016-10-23 18:00","연속",null,null,null,201608100011]
[250,"부산울산","울산","울주신경산#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","울주S/S 78Bay B/F PNL 대체","2016-10-17 09:00","2016-10-23 18:00","2016-10-17 09:00","2016-10-23 18:00","연속",null,null,null,201608100010]
[251,"부산울산","울산","울주S/S 울주-월성NP#1T/L CB (7971)","2016년 362kV 개폐장치 정밀점검 공사","울주 7971 CB 정밀점검","2016-10-13 08:00","2016-10-15 18:00","2016-10-13 08:00","2016-10-15 18:00","연속",null,null,null,201608100008]
[252,"부산울산","울산","울주월성NP#1 T/L","2016년 362kV 개폐장치 정밀점검 공사","울주 7971 CB 시험가압","2016-10-15 17:00","2016-10-15 18:00","2016-10-15 17:00","2016-10-15 18:00","당일",null,null,null,201608100009]
[253,"부산울산","울산","울주S/S 345kV #2 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","울주S/S #2BUS 보호반 대체","2016-10-04 09:00","2016-10-07 18:00","2016-10-04 09:00","2016-10-07 18:00","연속",null,null,null,201608110353]
[254,"부산울산","울산","신울산신온산#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","신온산S/S 345kV 7209-1, 7509-1 ES 스페이서 교체관련 시험가압","2016-10-24 17:00","2016-10-24 18:00","2016-10-24 17:00","2016-10-24 18:00","연속",null,null,null,201608290179]
[255,"부산울산","울산","신울산신온산#2 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","신온산S/S 345kV 7209-6 ES 스페이서 교체관련 시험가압","2016-10-25 17:00","2016-10-25 18:00","2016-10-25 17:00","2016-10-25 18:00","연속",null,null,null,201608290176]
[256,"부산울산","울산","신온산S/S 345kV #2 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","신온산S/S 345kV 7209-6 ES 스페이서 교체","2016-10-25 08:00","2016-10-25 18:00","2016-10-25 08:00","2016-10-25 18:00","당일",null,null,null,201608290172]
[257,"부산울산","울산","신온산S/S 345kV #1 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","신온산S/S 345kV 7209-1, 7509-1 ES 스페이서 교체","2016-10-24 08:00","2016-10-24 18:00","2016-10-24 08:00","2016-10-24 18:00","연속",null,null,null,201608290169]
[258,"경남","직할","신김해신녹산#2 T/L","안전이격확보휴전(신김해삼정#1T/L정밀점검)","안전이격확보휴전(신김해삼정#1T/L정밀점검)","2016-10-13 08:00","2016-10-13 18:00","2016-10-13 08:00","2016-10-13 18:00","당일",null,null,null,201608120341]
[259,"경남","직할","신김해S/S #2 M.Tr A","신김해S/S #2M.Tr 정밀점검","신김해S/S #2M.Tr 정밀점검, 1,2차 CB 보통점검, 3차 PT 보통점검, 1,2,3차 LA 보통점검, 실리콘 러버히터 설치","2016-10-10 09:30","2016-10-18 17:30","2016-10-10 09:30","2016-10-18 17:30","연속",null,null,null,201608100327]
[260,"경남","직할","신김해북부산#2 T/L","안전이격확보휴전(신마산신김해#1 T/L 과열개소 정비)","안전이격확보휴전(신마산신김해#1 T/L 과열개소 정비)","2016-10-04 08:00","2016-10-04 18:00","2016-10-04 08:00","2016-10-04 18:00","당일",null,null,null,201608120343]
[261,"경남","직할","신마산신김해#1 T/L","과열개소 정비","과열개소 정비(22,23호)","2016-10-04 08:00","2016-10-04 18:00","2016-10-04 08:00","2016-10-04 18:00","당일",null,null,null,201608120342]
[262,"경남","직할","신김해S/S #5 M.Tr A","신김해S/S #5M.Tr 보통점검","신김해S/S #5M.Tr 보통점검, 2차 LA A,B,C상 보통점검, 실리콘 러버히터 설치","2016-10-26 09:30","2016-10-28 17:30","2016-10-26 09:30","2016-10-28 17:30","연속",null,null,null,201608100363]
[263,"경남","직할","신김해신녹산#1 T/L","안전이격확보(154kV 신김해-삼정#2T/L 정밀점검)","154kV 신김해-삼정#2T/L 정밀점검 관련 안전이격확보 휴전","2016-10-20 08:00","2016-10-20 18:00","2016-10-20 08:00","2016-10-20 18:00","당일",null,null,null,201608190100]
[264,"경남","진주","신남원의령#1 T/L","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치)","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치) -78Bay BF반 대체 및 #3M.Tr 최초가압","2016-10-18 08:30","2016-10-26 17:00","2016-10-18 08:30","2016-10-26 17:00","연속",null,null,null,201608100395]
[265,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 6-8호 지장이설공사(요청자시행)","신설7호 설치 및 기설 7호 철거","2016-10-22 07:00","2016-10-26 19:00","취소","취소","연속",null,null,null,201608090095]
[266,"경남","진주","고령의령#1 T/L","345kV 신남원-의령T/L 송전선로용 피뢰기설치공사","345kV 신남원-의령#1T/L 피뢰기 설치 안전작업 거리확보 - 345kV 신남원-의령T/L 2∼4호 구간에 345kV 의령-고령T/L 2∼4호 병가","2016-10-22 08:30","2016-10-23 18:00","2016-10-22 08:30","2016-10-23 18:00","매일",null,null,null,201608040090]
[267,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 6-8호 지장이설공사(요청자시행)","신설7호 설치 및 기설 7호 철거","2016-10-27 07:00","2016-10-31 19:00","취소","취소","연속",null,null,null,201608090098]
[268,"경남","진주","의령산청양수#2 T/L","현수애자교체","현수애자교체 114, 125호","2016-10-07 09:00","2016-10-07 18:00","2016-10-07 09:00","2016-10-07 18:00","매일",null,null,null,201608020129]
[269,"경남","진주","신남원의령#1 T/L","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치)","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치) -345kV #76BUS(상체크) 및 7872CB 시험가압","2016-10-07 10:00","2016-10-13 17:00","2016-10-07 10:00","2016-10-13 17:00","연속",null,null,null,201608100393]
[270,"경남","진주","의령S/S 345kV #76 BUS","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치)","345kV 의령S/S #3M.Tr 증설공사(345kV GIS 설치) -345kV #76BUS(상체크) 및 7852DS연결부 시험가압","2016-10-11 17:00","2016-10-13 17:00","2016-10-11 17:00","2016-10-13 17:00","연속",null,null,null,201608100389]
[271,"경남","진주","광양하동화력#1 T/L","하동T/P 광양-하동T/P#1T/L PNL 대체공사","하동T/P 광양-하동T/P#1T/L PNL 대체공사 - 작업 : 광양-하동T/P#1T/L PNL, 73B/F PNL 대체 - 병행작업 : 광양-하동#1T/L LA(A,B,C) 대체 광양-하동#1T/L CPD(A,B,C) 하자점검","2016-10-10 09:30","2016-10-15 18:30","취소","취소","연속",null,null,null,201608100368]
[272,"경남","진주","하동T/P #1 M.Tr 1차 CB (7172)","하동T/P #1 M.Tr 1차 GIS(7172) 보통점검","하동T/P #1 M.Tr 1차 GIS(7172) 보통점검 - 하동T/P 1호기 OVERHAUL 기간 : 10.9~11.27","2016-10-24 09:30","2016-10-24 18:30","2016-10-24 09:30","2016-10-24 18:30","당일",null,null,null,201608100362]
[273,"경남","진주","하동T/P #4 M.Tr 1차 CB (7472)","하동T/P #4 M.Tr 1차 GIS(7472) 보통점검","하동T/P #4 M.Tr 1차 GIS(7472) 보통점검","2016-10-25 09:30","2016-10-25 18:30","2016-10-25 09:30","2016-10-25 18:30","당일",null,null,null,201608100364]
[274,"경남","통영","신고성S/S #3 M.Tr A","신고성S/S 345kV #3M.Tr 및 OLTC 정밀점검","신고성S/S 345kV #3M.Tr 및 OLTC 정밀점검","2016-10-10 09:30","2016-10-15 18:30","2016-10-10 09:30","2016-10-15 18:30","연속",null,null,null,201608130030]
[275,"경남","통영","신고성S/S #1 M.Tr A","신고성S/S 345kV #1M.Tr B상 중성선 부싱단자 과열개소 보수","신고성S/S 345kV #1M.Tr B상 중성선 부싱단자 과열개소 보수","2016-10-05 09:30","2016-10-05 18:30","2016-10-05 09:30","2016-10-05 18:30","당일",null,null,null,201608130028]
[276,"경남","함안","신마산S/S #2 M.Tr A","신마산 #2M.Tr 2차 GCB(6244) 보통점검공사","신마산 #2M.Tr 2차 GCB(6244) 보통점검 -3차측 LA 초기점검","2016-10-06 09:30","2016-10-06 17:30","2016-10-06 09:30","2016-10-06 17:30","당일",null,null,null,201608050187]
[277,"경남","함안","신마산S/S #4 M.Tr A","신마산 #4M.Tr 2차 GCB(6444) 초기점검공사","신마산 #4M.Tr 2차 GCB(6444) 초기점검사 - 병행: 3차측 PT 및 LA 보통점검","2016-10-07 09:30","2016-10-07 17:30","2016-10-07 09:30","2016-10-07 17:30","당일",null,null,null,201608050184]

{"sheet":"154송부","index":2,"n_rows":428,"n_cols":15,"rows_kept":428,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
[{"$f":"'765송부'!A1","v":"2016년도 10월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#2 T/L","154㎸ 구의광장T/L 일부구간 선종교체공사","1. 배 경 □ 구의S/S(테크노마트) 화재 및 설비피해시 대형 인명 피해 예방 2. 구의변전소 현황 □ 수용선로 : 154kV OF 4회선, 배전 총 13회선 □ 형 태 : 주상복합형 지하변전소(지하4∼6층) ※ 테크노마트 : 지하6층∼지상 39층(상가, 주택 등 1,000여명 거주중) 3. 시행계획 : 154㎸","2016-10-01 09:00","2016-10-31 18:00","2016-10-01T09:00:00","2016-10-31T18:00:00","연속",null,null,null,"-"]
[2,"서울","성동","성동휘경#1 T/L","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-10-11 09:00","2016-10-12 18:00","2016-10-11T09:00:00","2016-10-12T18:00:00","연속",null,null,null,"-"]
[3,"서울","성동","성동휘경#2 T/L","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사","2016-10-13 09:00","2016-10-14 18:00","2016-10-13T09:00:00","2016-10-14T18:00:00","연속",null,null,null,"-"]
[4,"서울","성동","중랑하수#2 T/L CB","화양 및 세종로S/S 인출선로 선종교체공사","1. 사 업 명 : 화양 및 세종로S/S 인출선로 선종교체공사 2. 사업목적 : 지하복합변전소 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 화양S/S ∼ 인출전력구, 세종로S/S ∼ 인출전력구 ○ 사업내용 : 154kV 6회선 0.6km 선종교체","2016-10-10 09:00","2016-11-30 18:00","취소","취소","연속",null,null,"고객선로_통보분으로 변경신청","-"]
[5,"서울","중부","수색S/S 154kV #1 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV LS 보통점검(#2 M.Tr 1차, 수색중부#2T/L)","2016-10-01 08:00","2016-10-01 14:00","2016-10-01T08:00:00","2016-10-01T14:00:00","당일",null,null,null,"-"]
[6,"서울","중부","수색S/S 154kV #2 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV LS 보통점검(#2 M.Tr 1차, 수색중부#2T/L)","2016-10-01 14:00","2016-10-01 18:00","2016-10-01T14:00:00","2016-10-01T18:00:00","당일",null,null,null,"-"]
[7,"서울","중부","수색S/S 154kV #1 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV LS 보통점검(원흥수색#1, 수색중부#1T/L)","2016-10-08 08:00","2016-10-08 14:00","2016-10-08T08:00:00","2016-10-08T14:00:00","당일",null,null,null,"-"]
[8,"서울","중부","수색S/S 154kV #2 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","수색S/S 154kV LS 보통점검(원흥수색#1, 수색중부#1T/L)","2016-10-08 14:00","2016-10-08 18:00","2016-10-08T14:00:00","2016-10-08T18:00:00","당일",null,null,null,"-"]
[9,"서울","중부","용산동빙고 T/L","2016년 중부전력지사 170kV GIS 정밀점검","용산S/S 용산동빙고T/L GIS(617) 정밀점검","2016-10-12 08:00","2016-10-14 18:00","2016-10-12T08:00:00","2016-10-14T18:00:00","연속",null,null,null,"-"]
[10,"서울","직할","신당방산#1 T/L","신당S/S 170kV 장기사용 GIS 대체공사(3차)","신당S/S 170kV 장기사용 GIS 대체공사(3차) - 신당방산#1T/L, #2M.Tr, 627CB GIS 대체","2016-10-27 14:00","2016-11-22 18:00","2016-10-27T14:00:00","2016-11-22T18:00:00","연속",null,null,null,"-"]
[11,"서울","직할","신당방산#2 T/L","신당S/S 170kV 장기사용 GIS 대체공사(2차)","신당S/S 170kV 장기사용 GIS 대체공사(2차) - #3M.Tr 1차, BUS TIE, 신당방산#2T/L GIS 대체","2016-10-01 09:30","2016-10-27 14:00","2016-10-01T09:30:00","2016-10-27T14:00:00","연속",null,null,null,"-"]
[12,"서울","직할","신당방산#1 T/L","신당S/S 170kV 장기사용 GIS 대체공사(2차)","신당S/S 170kV 장기사용 GIS 대체공사(2차) - #3M.Tr 1차, BUS TIE, 신당방산#2T/L GIS 대체 - 모선분리시 인접Bay 신당방산#1T/L 휴전","2016-10-08 08:00","2016-10-09 18:00","2016-10-08T08:00:00","2016-10-09T18:00:00","연속",null,null,null,"-"]
[13,"서울","직할","신당S/S 154kV #1 BUS TIE CB","신당S/S 170kV 장기사용 GIS 대체공사(2차)","신당S/S 170kV 장기사용 GIS 대체공사(2차) - #3M.Tr 1차, BUS TIE, 신당방산#2T/L GIS 대체","2016-10-01 09:30","2016-10-27 18:00","2016-10-01T09:30:00","2016-10-27T18:00:00","연속",null,null,null,"-"]
[14,"남서울","강남","동빙고반포#2 T/L","16년 가공송전협력총액공사(피뢰기 설치공사)","송전선로용 피뢰기 설치공사","2016-10-25 09:00","2016-10-25 18:00","2016-10-25T09:00:00","2016-10-25T18:00:00","당일",null,null,null,"-"]
[15,"남서울","강남","신성남염곡#2 T/L","154KV 신성남-염곡T/L 이설공사(양재대로)","강남순환도시고속도로 건설에 따른 지장 송전선로 이설 154kV 신성남-염곡T/L J/B#17~18","2016-10-17 14:00","2016-11-14 10:00","2016-11-01T10:00:00","2016-11-25T10:00:00","연속",null,null,"한전요청","-"]
[16,"남서울","동서울","동서울가락#2 T/L","170kV ILC반 교체공사","동서울-가락#2T/L 170kV ILC반 교체공사","2016-10-17 09:00","2016-10-21 18:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[17,"남서울","동서울","동서울S/S 154kV #67 BUS","170kV GCB 교체공사","170kV GCB 교체공사 - 동서울S/S #4M.Tr GCB 교체공사","2016-10-17 09:00","2016-10-21 18:00","취소","취소","연속",null,null,"신뢰도개선","○"]
[18,"남서울","동서울","동서울신장#2 T/L","170kV ILC반 교체공사","동서울-신장#2T/L ILC반 교체공사","2016-10-10 09:00","2016-10-12 18:00","2016-10-10T09:00:00","2016-10-12T18:00:00","연속",null,null,null,"-"]
[19,"남서울","동서울","동서울신장#1 T/L","170kV ILC반 교체공사","동서울-신장#1T/L 170kV ILC반 교체공사","2016-10-04 09:00","2016-10-06 18:00","2016-10-04T09:00:00","2016-10-06T18:00:00","연속",null,null,null,"-"]
[20,"남서울","동서울","동서울S/S 154kV #67 BUS","170kV GCB 교체공사","170kV GCB 교체공사 - 동서울S/S #3M.Tr, 동서울-송파#1T/L GCB 교체공사","2016-10-24 09:00","2016-10-28 18:00","취소","취소","연속",null,null,"신뢰도개선","○"]
[21,"남서울","동서울","동서울송파#1 T/L","170kV GCB 교체공사","- 동서울S/S 동서울-송파#1T/L GCB 교체공사 - ILC반 교체공사","2016-10-24 09:00","2016-10-28 18:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[22,"남서울","동서울","동서울송파#2 T/L","170kV ILC반 교체공사","동서울-송파#2T/L 170kV ILC반 교체공사","2016-10-31 09:00","2016-11-02 18:00","2016-10-31T09:00:00","2016-11-02T18:00:00","연속",null,null,null,"-"]
[23,"남서울","동서울","삼성선릉#1 T/L","154kV 삼성-선릉 지중T/L 이설공사","삼성동 (구)본사부지 내 현대차 글로벌 비지니스센터(GBC)건설에 따른 부지 내 전력설비 이전필요에 따른 케이블이설공사","2016-10-10 10:00","2016-11-30 18:00","2016-10-10T10:00:00","2016-11-30T18:00:00","연속",null,null,null,"-"]
[24,"남서울","동서울","강동상일#1 T/L","170kV GIS 유압장치 보수","170kV GIS 유압장치 보수","2016-10-09 09:00","2016-10-09 18:00","2016-10-09T09:00:00","2016-10-09T18:00:00","당일",null,null,null,"-"]
[25,"남서울","동서울","강동상일#2 T/L","170kV GIS 유압장치 보수","170kV GIS 유압장치 보수","2016-10-16 09:00","2016-10-16 18:00","2016-10-16T09:00:00","2016-10-16T18:00:00","당일",null,null,null,"-"]
[26,"남서울","영서","가양S/S 154kV #1 BUS","2016년 변전협력회사 총액공사_보통점검","- 154kV GIS PT 보통점검","2016-10-06 09:00","2016-10-06 14:00","2016-10-06T09:00:00","2016-10-06T14:00:00","당일",null,null,null,"-"]
[27,"남서울","영서","가양S/S 154kV #2 BUS","2016년 변전협력회사 총액공사_보통점검","- 154kV GIS PT 보통점검","2016-10-06 14:00","2016-10-06 18:00","2016-10-06T14:00:00","2016-10-06T18:00:00","당일",null,null,null,"-"]
[28,"남서울","영서","대방S/S 154kV #1 BUS","2016년 변전협력회사 총액공사_보통점검","- 154kV GIS PT 보통점검","2016-10-14 09:00","2016-10-14 14:00","2016-10-14T09:00:00","2016-10-14T14:00:00","당일",null,null,null,"-"]
[29,"남서울","영서","대방S/S 154kV #2 BUS","2016년 변전협력회사 총액공사_보통점검","- 154kV GIS PT 보통점검","2016-10-14 14:00","2016-10-14 18:00","2016-10-14T14:00:00","2016-10-14T18:00:00","당일",null,null,null,"-"]
[30,"남서울","영서","영서시흥#2 T/L","16년 가공송전협력총액공사(송전선로용 피뢰기 설치공사)","송전선로용 피뢰기 설치공사","2016-10-24 09:00","2016-10-24 18:00","2016-10-24T09:00:00","2016-10-24T18:00:00","당일",null,null,null,"-"]
[31,"남서울","영서","영서소래 T/L","2016년 변전협력회사 총액공사_보통점검","- 154kV 전위변성기 보통점검 - 154kV 피뢰기 보통점검","2016-10-18 09:00","2016-10-18 18:00","2016-10-18T09:00:00","2016-10-18T18:00:00","당일",null,null,null,"-"]
[32,"남서울","영서","영서광명#2 T/L","16년 가공송전협력회사 총액공사(압축인류크램프 교체)","압축인류클램프 교체","2016-10-16 09:00","2016-10-16 18:00","2016-10-16T09:00:00","2016-10-16T18:00:00","당일",null,null,null,"-"]
[33,"남서울","영서","영서광명#1 T/L","16년 가공송전협력회사 총액공사(압축인류크램프 교체)","압축인류클램프 교체","2016-10-15 09:00","2016-10-15 18:00","2016-10-15T09:00:00","2016-10-15T18:00:00","당일",null,null,null,"-"]
[34,"남서울","영서","온수소래 T/L","16년 가공송전협력총액공사(송전선로용 피뢰기 설치공사)","송전선로용 피뢰기 설치공사","2016-10-18 09:00","2016-10-21 18:00","2016-10-18T09:00:00","2016-10-21T18:00:00","당일",null,null,null,"-"]
[35,"남서울","직할","사당봉천#1 T/L","봉천,노들변전소 OF케이블 선종교체공사","케이블철거 및 설치 : OF케이블에서 XLPE로 교체(260m X 3상) 이종 및 종단 접속 : 2개소 X 3상 PT 이설 및 기타 부대작업","2016-10-04 09:00","2016-10-31 18:00","2016-10-04T09:00:00","2016-10-31T18:00:00","연속",null,null,null,"-"]
[36,"남서울","직할","교대이수#2 T/L","154kV 교대-이수T/L 이설공사","J/B#7~#8, J/B#9~#10구간 이설","2016-10-27 09:00","2016-12-02 18:00","2016-10-27T09:00:00","2016-12-02T18:00:00","연속",null,null,null,"-"]
[37,"인천","시흥","신시흥남동#2 T/L","154kV 남동T/L 아킹혼설치 및 오봉T/L 피뢰기 설치공사","154kV 남동T/L 아킹혼설치(30기) 및 오봉T/L 피뢰기 설치(34기)","2016-10-02 09:00","2016-10-03 18:00","2016-10-02T09:00:00","2016-10-03T18:00:00","매일",null,null,null,"-"]
[38,"인천","시흥","도림오봉 T/L","154kV 남동T/L 아킹혼설치 및 오봉T/L 피뢰기 설치공사","154kV 남동T/L 아킹혼설치(30기) 및 오봉T/L 피뢰기 설치(34기)","2016-10-03 13:00","2016-10-03 18:00","2016-10-03T13:00:00","2016-10-03T18:00:00","당일",null,null,null,"-"]
[39,"인천","시흥","신시흥도림 T/L","154kV 남동T/L 아킹혼설치 및 오봉T/L 피뢰기 설치공사","154kV 남동T/L 아킹혼설치(30기) 및 오봉T/L 피뢰기 설치(34기)","2016-10-02 09:00","2016-10-03 13:00","2016-10-02T09:00:00","2016-10-03T13:00:00","매일",null,null,null,"-"]
[40,"인천","시흥","서안양소래 T/L","154kV 서안양소래T/L 정밀점검","154kV 서안양소래T/L 정밀점검","2016-10-26 08:00","2016-10-28 18:00","2016-10-26T08:00:00","2016-10-28T18:00:00","연속",null,null,null,"-"]
[41,"인천","시흥","연수S/S 154kV #1 BUS","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 학익연수#2T/L GIS 1CCT 대체","2016-10-21 08:00","2016-10-27 14:00","2016-10-21T08:00:00","2016-10-27T14:00:00","연속",null,null,null,"-"]
[42,"인천","시흥","학익연수#2 T/L","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 학익연수#2T/L GIS 1CCT 대체","2016-10-20 08:00","2016-11-04 18:00","2016-10-20T08:00:00","2016-11-04T18:00:00","연속",null,null,null,"-"]
[43,"인천","시흥","연수S/S 154kV #1 BUS","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 남동연수#2T/L GIS 1CCT 대체 - 154kV #2M.Tr 1차 GIS 1CCT 대체 - 154kV 학익연수#1T/L GIS 1CCT 대체","2016-10-14 10:00","2016-10-14 18:00","2016-10-14T10:00:00","2016-10-14T18:00:00","연속",null,null,null,"-"]
[44,"인천","시흥","연수S/S 154kV #2 BUS","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 남동연수#2T/L GIS 1CCT 대체 - 154kV #2M.Tr 1차 GIS 1CCT 대체 - 154kV 학익연수#1T/L GIS 1CCT 대체","2016-10-04 08:00","2016-10-14 10:00","2016-10-04T08:00:00","2016-10-14T10:00:00","연속",null,null,null,"-"]
[45,"인천","시흥","연수S/S 154kV #2 BUS","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 학익연수#2T/L GIS 1CCT 대체","2016-10-20 08:00","2016-10-20 18:00","2016-10-20T08:00:00","2016-10-20T18:00:00","연속",null,null,null,"-"]
[46,"인천","시흥","연수S/S 154kV #2 BUS","연수S/S 170kV 장기사용 GIS 대체공사","- 154kV 학익연수#2T/L GIS 1CCT 대체","2016-10-27 14:00","2016-11-04 10:00","2016-10-27T14:00:00","2016-11-04T10:00:00","연속",null,null,null,"-"]
[47,"인천","인천","남동관교#2 T/L","'16-17년 가공송전정비 협력회사 총액공사","송전용 피뢰기 설치공사(11기)","2016-10-19 08:00","2016-10-19 18:00","2016-10-19T08:00:00","2016-10-19T18:00:00","매일",null,null,null,"-"]
[48,"인천","인천","서인천C/C #3 G.Tr 1차 GIS","서인천복합S/Y #3G.Tr 1차 GIS 보통점검 및 보조계전기 교체","서인천복합S/Y #3G.Tr 1차 GIS 보통점검 및 보조계전기 교체","2016-10-11 09:00","2016-10-11 18:00","2016-10-11T09:00:00","2016-10-11T18:00:00","당일",null,null,null,"-"]
[49,"인천","인천","신가좌신현#2 T/L","'16-17년 가공송전정비 협력회사 총액공사","스페이서 간격조정 공사","2016-10-17 08:00","2016-10-18 18:00","2016-10-17T08:00:00","2016-10-18T18:00:00","매일",null,null,null,"-"]
[50,"인천","인천","신가좌신현#1 T/L","'16-17년 가공송전정비 협력회사 총액공사","송전용 피뢰기 설치공사(3기) 및 스페이서 간격조정 공사","2016-10-15 08:00","2016-10-16 18:00","2016-10-15T08:00:00","2016-10-16T18:00:00","매일",null,null,null,"-"]
[51,"인천","인천","계양원창 T/L","'16-17년 가공송전정비 협력회사 총액공사","송전용 피뢰기 설치공사(4기)","2016-10-18 08:00","2016-10-20 18:00","2016-10-18T08:00:00","2016-10-20T18:00:00","당일",null,null,null,"-"]
[52,"인천","인천","신가좌주안#2 T/L","'16-17년 가공송전정비 협력회사 총액공사","송전용 피뢰기 설치공사(1기) 및 스페이서 간격조정 공사","2016-10-15 08:00","2016-10-16 18:00","2016-10-15T08:00:00","2016-10-16T18:00:00","매일",null,null,null,"-"]
[53,"인천","인천","신가좌주안#1 T/L","'16-17년 가공송전정비 협력회사 총액공사","스페이서 간격조정 공사","2016-10-17 08:00","2016-10-18 18:00","2016-10-17T08:00:00","2016-10-18T18:00:00","매일",null,null,null,"-"]
[54,"인천","인천","송현포스코CC#1 T/L","송현S/S 송현포스코#1T/L GIS 유압 불량보수","송현S/S 송현포스코#1T/L GIS 유압 불량보수","2016-10-07 09:00","2016-10-07 18:00","2016-10-07T09:00:00","2016-10-07T18:00:00","당일",null,null,null,"-"]
[55,"인천","직할","신부평부흥#1 T/L","부흥S/S 154kV M.Tr 대체공사(#1M.Tr)","1. 변압기 1Bank 철거 및 설치(FOW → GWFW) 2. 변압기 2차케이블 선종교체(FR-CV → FR-CNCO-W) 3. 기타 부대공사 1식","2016-10-16 09:00","2016-10-18 09:00","2016-10-16T09:00:00","2016-10-18T09:00:00","연속",null,null,null,"-"]
[56,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 6100GIS 정밀점검","신부평S/S 154kV 6100GIS 정밀점검","2016-10-25 08:00","2016-10-26 10:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[57,"인천","직할","신부평S/S 65-66 SEC GIS","신부평S/S 154kV 65-66SEC GIS 정밀점검","신부평S/S 154kV 65-66SEC GIS 정밀점검","2016-10-21 08:00","2016-10-22 18:00","2016-10-21T08:00:00","2016-10-22T18:00:00","연속",null,null,null,"-"]
[58,"인천","직할","신부평S/S 154kV #61 BUS","신부평S/S 154kV 60-61SEC GIS 정밀점검","신부평S/S 154kV 60-61SEC GIS 정밀점검","2016-10-20 10:00","2016-10-20 18:00","2016-10-20T10:00:00","2016-10-20T18:00:00","연속",null,null,null,"-"]
[59,"인천","직할","신부평S/S 60-61 SEC GIS","신부평S/S 154kV 60-61SEC GIS 정밀점검","신부평S/S 154kV 60-61SEC GIS 정밀점검","2016-10-19 08:00","2016-10-20 18:00","2016-10-19T08:00:00","2016-10-20T18:00:00","연속",null,null,null,"-"]
[60,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV #62M.Tr 정밀점검","신부평S/S 154kV #62M.Tr 정밀점검","2016-10-14 14:00","2016-10-15 18:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[61,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","2016-10-04 14:00","2016-10-05 18:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[62,"인천","직할","신부평S/S 154kV #2 BUS TIE GIS","신부평S/S 154kV 6200GIS 정밀점검","신부평S/S 154kV 6200GIS 정밀점검","2016-10-27 08:00","2016-10-28 18:00","2016-10-27T08:00:00","2016-10-28T18:00:00","연속",null,null,null,"-"]
[63,"인천","직할","신부평S/S 154kV #61 BUS","신부평S/S 154kV 6200GIS 정밀점검","신부평S/S 154kV 6200GIS 정밀점검","2016-10-27 08:00","2016-10-28 10:00","2016-10-27T08:00:00","2016-10-28T10:00:00","연속",null,null,null,"-"]
[64,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 6100GIS 정밀점검","신부평S/S 154kV 6100GIS 정밀점검","2016-10-26 10:00","2016-10-26 18:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[65,"인천","직할","신부평S/S 154kV #66 BUS","신부평S/S 154kV 65-66SEC GIS 정밀점검","신부평S/S 154kV 65-66SEC GIS 정밀점검","2016-10-22 10:00","2016-10-22 18:00","2016-10-22T10:00:00","2016-10-22T18:00:00","연속",null,null,null,"-"]
[66,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 65-66SEC GIS 정밀점검","신부평S/S 154kV 65-66SEC GIS 정밀점검","2016-10-21 08:00","2016-10-22 10:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[67,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 60-61SEC GIS 정밀점검","신부평S/S 154kV 60-61SEC GIS 정밀점검","2016-10-19 08:00","2016-10-20 10:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[68,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV #62M.Tr 정밀점검","신부평S/S 154kV #62M.Tr 정밀점검","2016-10-13 08:00","2016-10-14 14:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[69,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","2016-10-11 14:00","2016-10-12 18:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[70,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","2016-10-10 08:00","2016-10-11 14:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[71,"인천","직할","신부평부천#2 T/L","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","신부평S/S 154kV 신부평-부천#2T/L 정밀점검","2016-10-10 08:00","2016-10-12 18:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[72,"인천","직할","신부평S/S 154kV #65 BUS","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","2016-10-07 14:00","2016-10-08 18:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[73,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","2016-10-06 08:00","2016-10-07 14:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[74,"인천","직할","신부평부천#1 T/L","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","신부평S/S 154kV 신부평-부천#1T/L 정밀점검","2016-10-06 08:00","2016-10-08 18:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[75,"인천","직할","신부평S/S 154kV #60 BUS","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","2016-10-03 08:00","2016-10-04 14:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[76,"인천","직할","신부평중동#1 T/L","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","신부평S/S 154kV 신부평-중동#1T/L 정밀점검","2016-10-03 08:00","2016-10-05 18:00","취소","취소","연속",null,null,"신뢰도개선","-"]
[77,"인천","직할","신부평중동#3 T/L","신부평-중동#3T/L 보호반 대체공사","신부평-중동#3T/L 보호반 대체공사","2016-10-10 09:30","2016-10-14 18:00","2016-10-17T09:30:00","2016-10-21T18:00:00","연속",null,null,"한전요청","-"]
[78,"인천","직할","신부평S/S 154kV #66 BUS","신부평S/S 154kV 6200GIS 정밀점검","신부평S/S 154kV 6200GIS 정밀점검","2016-10-28 10:00","2016-10-28 18:00","2016-10-28T10:00:00","2016-10-28T18:00:00","연속",null,null,null,"-"]
[79,"인천","직할","신부평S/S 154kV #1 BUS TIE GIS","신부평S/S 154kV 6100GIS 정밀점검","신부평S/S 154kV 6100GIS 정밀점검","2016-10-25 08:00","2016-10-26 18:00","2016-10-25T08:00:00","2016-10-26T18:00:00","연속",null,null,null,"-"]
[80,"인천","직할","중동화곡#2 T/L","'16-17년 가공송전정비 협력회사 총액공사","송전용 피뢰기 설치공사(6기)","2016-10-30 08:00","2016-10-30 18:00","2016-10-30T08:00:00","2016-10-30T18:00:00","당일",null,null,null,"-"]
[81,"경기북부","구리","가평춘천HP T/L","가평변전소 모자익배전반 교체공사","가평춘천HPT/L GIS,보호배전반 결선교체 및 조작,경보시험","2016-10-07 09:00","2016-10-10 18:00","2016-10-07T09:00:00","2016-10-10T18:00:00","연속",null,null,null,"-"]
[82,"경기북부","구리","덕소팔당HP청평HP T/L","154kV 덕소-팔당HP-청평HP T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체공사 - 구간 : No.6~9,9~11,11~14,14~18,30~33,50~52,54~56","2016-10-06 08:00","2016-10-20 18:00","2016-10-06T08:00:00","2016-10-20T18:00:00","연속",null,null,null,"-"]
[83,"경기북부","구리","마석청평HP#2 T/L","154kV 마석-청평HP #2T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체공사 - 구간 : No.2~3,7~10,14~23","2016-10-27 08:00","2016-11-01 18:00","2016-10-27T08:00:00","2016-11-01T18:00:00","연속",null,null,null,"○"]
[84,"경기북부","구리","마석청평HP#1 T/L","154kV 마석-청평HP #1T/L 전선접속개소 전선교체공사","ㅇ 전선접속개소 전선교체공사 - 구간 : No.2~3,7~10,14~23","2016-10-21 08:00","2016-10-26 18:00","2016-10-21T08:00:00","2016-10-26T18:00:00","연속",null,null,null,"○"]
[85,"경기북부","구리","미금화양 T/L","가운지금지구 지장송전선로 지중화공사","ㅇ 철탑 2기 설치 및 철탑 11철거 ㅇ 지중케이블 포설 : 2.2km","2016-10-07 08:00","2016-10-25 18:00","2016-10-07T08:00:00","2016-10-25T18:00:00","연속",null,null,null,"-"]
[86,"경기북부","구리","지제S/S 154kV #1 BUS TIE CB","지제S/S 154kV #1 BUS TIE CB 보통점검 (6100)","지제S/S 154kV #1 BUS TIE CB 보통점검 (6100)","2016-10-25 10:00","2016-10-25 18:00","2016-10-25T10:00:00","2016-10-25T18:00:00","당일",null,null,null,"-"]
[87,"경기북부","구리","철원화천#1 T/L","철원S/S 154kV 철원-화천#1T/L GIS 초기점검 (637)","철원S/S 154kV 철원-화천#1T/L GIS 초기점검 (637)","2016-10-11 10:00","2016-10-11 18:00","2016-10-11T10:00:00","2016-10-11T18:00:00","당일",null,null,null,"○"]
[88,"경기북부","구리","철원화천#2 T/L","철원S/S 154kV 철원-화천#2T/L GIS 초기점검 (647)","철원S/S 154kV 철원-화천#2T/L GIS 초기점검 (647)","2016-10-12 10:00","2016-10-12 18:00","2016-10-12T10:00:00","2016-10-12T18:00:00","당일",null,null,null,"○"]
[89,"경기북부","구리","서종청평PP#2 T/L","청평PP 170kV 서종청평PP #2T/L GIS 정밀점검(627CB)","청평P/P 170kV 서종청평PP #2T/L GIS 정밀점검공사(627CB)","2016-10-10 09:00","2016-10-12 18:00","2016-10-10T09:00:00","2016-10-12T18:00:00","연속",null,null,null,"○"]
[90,"경기북부","구리","서종청평PP#1 T/L","청평PP 170kV 서종청평PP #1T/L GIS 정밀점검(617CB)","청평P/P 170kV 서종청평PP #1T/L GIS 정밀점검공사(617CB)","2016-10-04 09:00","2016-10-06 18:00","2016-10-04T09:00:00","2016-10-06T18:00:00","연속",null,null,null,"○"]
[91,"경기북부","직할","양주은평#2 T/L","양주은평#2 T/L","2016년 직할 변전협력회사 총액공사 - GIS, LA, CVT 보통","2016-10-13 10:00","2016-10-13 18:00","2016-10-13T10:00:00","2016-10-13T18:00:00","당일",null,null,null,"-"]
[92,"경기북부","직할","양주은평#1 T/L","양주은평#1 T/L","2016년 직할 변전협력회사 총액공사 - GIS, LA, CVT 보통","2016-10-12 10:00","2016-10-12 18:00","2016-10-12T10:00:00","2016-10-12T18:00:00","당일",null,null,null,"-"]
[93,"경기북부","직할","신포천전곡#1 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-&gt메탈판넬) 교체","2016-10-17 09:00","2016-10-19 18:00","2016-10-17T09:00:00","2016-10-19T18:00:00","연속",null,null,null,"○"]
[94,"경기북부","직할","운천전곡#1 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-&gt메탈판넬) 교체","2016-10-26 09:00","2016-10-28 18:00","2016-10-26T09:00:00","2016-10-28T18:00:00","연속",null,null,null,"○"]
[95,"경기북부","직할","신포천전곡#2 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-메탈판넬) 교체","2016-10-26 09:00","2016-10-28 18:00","2016-10-26T09:00:00","2016-10-28T18:00:00","연속",null,null,null,"○"]
[96,"경기북부","직할","운천전곡#2 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-&gt메탈판넬) 교체","2016-10-17 09:00","2016-10-19 18:00","2016-10-17T09:00:00","2016-10-19T18:00:00","연속",null,null,null,"○"]
[97,"경기북부","파주","양주고양#1 T/L","154kV 양주-고양#1T/L 피뢰기 설치공사","154kV 양주-고양#1T/L 피뢰기 설치공사(No.1~38)","2016-10-19 07:00","2016-10-25 18:00","2016-10-19T07:00:00","2016-10-25T18:00:00","연속",null,null,null,"○"]
[98,"경기북부","파주","양주고양#2 T/L","154kV 양주-고양#2T/L 정밀점검","154kV 양주-고양#2T/L 정밀점검(No.1~38)","2016-10-12 07:00","2016-10-18 18:00","2016-10-12T07:00:00","2016-10-18T18:00:00","연속",null,null,null,"○"]
[99,"경기북부","파주","신파주금촌#1 T/L","154kV 신파주-금촌#1T/L 4회선 병가선로 병행휴전","154kV 양주-금촌#2T/L No.59 정밀점검 작업관련 병가선로 154kV 신파주-금촌#1T/L 병행휴전","2016-10-10 07:00","2016-10-10 18:00","2016-10-10T07:00:00","2016-10-10T18:00:00","당일",null,null,null,"-"]
[100,"경기북부","파주","능곡상암#2 T/L","능곡S/S 능곡-상암#2T/L GIS 정밀점검공사","능곡S/S 능곡-상암#2T/L GIS 정밀점검공사","2016-10-31 09:00","2016-11-02 18:00","2016-10-31T09:00:00","2016-11-02T18:00:00","연속",null,null,null,"-"]
[101,"경기북부","파주","능곡상암#1 T/L","능곡S/S 능곡-상암#1T/L GIS 정밀점검공사","능곡S/S 능곡-상암#1T/L GIS 정밀점검공사","2016-10-24 09:00","2016-10-26 18:00","2016-10-24T09:00:00","2016-10-26T18:00:00","연속",null,null,null,"-"]
[102,"경기북부","파주","신덕은문산#2 T/L","문산,신덕은S/S 신덕은-문산#2T/L GIS 조작시험","GIS 성능(개폐타임) 측정시험","2016-10-25 10:00","2016-10-25 17:00","2016-10-25T10:00:00","2016-10-25T17:00:00","당일",null,null,null,"-"]
[103,"경기북부","파주","문산월롱#2 T/L","문산,월롱S/S 문산-월롱#2T/L GIS 조작시험","GIS 성능(개폐타임) 측정시험","2016-10-18 10:00","2016-10-18 17:00","2016-10-18T10:00:00","2016-10-18T17:00:00","당일",null,null,null,"-"]
[104,"경기북부","파주","신파주송포#1 T/L","154kV 송전선로 보호반 교체공사","송전선로 보호반 교체","2016-10-30 09:00","2016-11-01 18:00","2016-10-30T09:00:00","2016-11-01T18:00:00","연속",null,null,null,"-"]
[105,"경기북부","파주","신파주금촌#2 T/L","신파주S/S 신파주-금촌#2T/L GIS 정밀점검공사","신파주S/S 신파주-금촌#2T/L GIS 정밀점검공사","2016-10-05 09:00","2016-10-07 18:00","2016-10-05T09:00:00","2016-10-07T18:00:00","연속",null,null,null,"-"]
[106,"경기북부","파주","원흥수색#1 T/L","154kV 원흥수색T/L No.13 지장송전선로 이설공사","#2T/L : 10.10~11(2일), #1T/L : 10.12~10.14(3일), #2T/L : 10.15~16(2일) 1. 구 간 : 154kV 원흥-수색T/L No.12∼14 2. 지지물 : 설치 1기(관형주) / 철거 1기(4각철탑) 3. 전력선 교체(용량증대) : HSTACIR 330㎟ (0.752km)","2016-10-12 07:00","2016-10-14 18:00","2016-10-12T07:00:00","2016-10-14T18:00:00","연속",null,null,"신뢰도 개선","-"]
[107,"경기북부","파주","원흥수색#2 T/L","154kV 원흥수색T/L No.13 지장송전선로 이설공사","#2T/L : 10.10~11(2일), #1T/L : 10.12~10.14(3일), #2T/L : 10.15~16(2일) 1. 구 간 : 154kV 원흥-수색T/L No.12∼14 2. 지지물 : 설치 1기(관형주) / 철거 1기(4각철탑) 3. 전력선 교체(용량증대) : HSTACIR 330㎟ (0.752km)","2016-10-15 07:00","2016-10-16 18:00","2016-10-15T07:00:00","2016-10-16T18:00:00","연속",null,null,"신뢰도 개선","-"]
[108,"경기북부","파주","원흥수색#2 T/L","154kV 원흥수색T/L No.13 지장송전선로 이설공사","#2T/L : 10.10~11(2일), #1T/L : 10.12~10.14(3일), #2T/L : 10.15~16(2일) 1. 구 간 : 154kV 원흥-수색T/L No.12∼14 2. 지지물 : 설치 1기(관형주) / 철거 1기(4각철탑) 3. 전력선 교체(용량증대) : HSTACIR 330㎟ (0.752km)","2016-10-10 07:00","2016-10-11 18:00","2016-10-10T07:00:00","2016-10-11T18:00:00","연속",null,null,"신뢰도 개선","-"]
[109,"경기북부","파주","일산송포#2 T/L","백마지하차도 지장송전선로 이설공사","지중송전선로 이설 : 일산-송포 관로 #2~3","2016-10-01 08:00","2016-10-28 18:00","2016-10-01T08:00:00","2016-10-28T18:00:00","연속",null,null,null,"-"]
[110,"경기북부","파주","일산호수#2 T/L","백마지하차도 지장송전선로 이설공사","지중송전선로 이설 : 일산-호수 관로 #2~3","2016-10-29 08:00","2016-11-14 18:00","2016-10-29T08:00:00","2016-11-14T18:00:00","연속",null,null,null,"-"]
[111,"경기북부","파주","일산지도#1 T/L","2016년 파주전력지사 장기사용 170kV GIS 교체공사","지도S/S 장기사용 170kV GIS 교체공사 - 일산지도#1T/L, #2M.Tr, PT&ES 철거, 설치","2016-10-31 08:00","2016-11-27 18:00","2016-10-31T08:00:00","2016-11-27T18:00:00","연속",null,null,null,"-"]
[112,"경기북부","파주","지도S/S 154kV #1 BUS","2016년 파주전력지사 장기사용 170kV GIS 교체공사","지도S/S 장기사용 170kV GIS 교체공사 - 일산지도#1T/L, #2M.Tr, PT&ES 철거, 설치","2016-10-31 08:00","2016-11-06 18:00","2016-10-31T08:00:00","2016-11-06T18:00:00","연속",null,null,null,"-"]
[113,"경기","군포","관양평촌#2 T/L","154kV 관양S/S #3M.Tr용 GIS 설치공사","-170kV GIS(50kA 1250A) × 1CCT 설치 -25.8kV GIS(25kA 2000A) × 4CCT 설치(GIB포함)","2016-10-26 09:00","2016-10-28 18:00","2016-10-26 09:00","2016-10-28 18:00","연속",null,null,null,"-"]
[114,"경기","군포","관양평촌#2 T/L","154kV 관양S/S #3M.Tr용 GIS 설치공사","-170kV GIS(50kA 1250A) × 1CCT 설치 -25.8kV GIS(25kA 2000A) × 4CCT 설치(GIB포함)","2016-10-19 09:00","2016-10-21 18:00","2016-10-19 09:00","2016-10-21 18:00","연속",null,null,null,"-"]
[115,"경기","군포","서서울일동#1 T/L","서서울S/S CVT,LA 이설공사","서서울S/S CVT,LA 이설공사 - 기기기초 및 CVT,LA 이설","2016-10-21 07:00","2016-10-24 18:00","2016-10-21 07:00","2016-10-24 18:00","연속",null,null,null,"-"]
[116,"경기","군포","서서울일동#2 T/L","서서울S/S CVT,LA 이설공사","서서울S/S CVT,LA 이설공사 - 기기기초 및 CVT,LA 이설","2016-10-17 07:00","2016-10-21 07:00","2016-10-17 07:00","2016-10-21 07:00","연속",null,null,null,"-"]
[117,"경기","군포","서서울산본#1 T/L","서서울S/S CVT,LA 이설공사","서서울S/S CVT,LA 이설공사 - 기기기초 및 CVT,LA 이설","2016-10-13 07:00","2016-10-17 07:00","2016-10-13 07:00","2016-10-17 07:00","연속",null,null,"신뢰도개선","-"]
[118,"경기","군포","서서울산본#2 T/L","서서울S/S CVT,LA 이설공사","서서울S/S CVT,LA 이설공사 - 기기기초 및 CVT,LA 이설","2016-10-09 07:00","2016-10-13 07:00","2016-10-09 07:00","2016-10-13 07:00","연속",null,null,"신뢰도개선","-"]
[119,"경기","군포","서서울서안양 T/L","서서울S/S CVT,LA 이설공사","서서울S/S CVT,LA 이설공사 - 기기기초 및 CVT,LA 이설","2016-10-05 07:00","2016-10-09 07:00","2016-10-01 07:00","2016-10-05 07:00","연속",null,null,"한전요청","-"]
[120,"경기","군포","서서울소래 T/L","서서울S/S CVT,LA 이설공사","서서울S/S CVT,LA 이설공사 - 기기기초 및 CVT,LA 이설","2016-10-01 07:00","2016-10-05 07:00","2016-09-27 07:00","2016-10-01 07:00","연속",null,null,"한전요청","-"]
[121,"경기","동부","분당오포#2 T/L","154kV 분당-오포#2T/L 낙뢰소산장치 철거공사","154kV 분당-오포#2T/L 가공지선 및 OPGW 1~28호 구간 낙뢰소산장치 철거(분당-오포#2T/L 및 성현-분당#1T/L 2~18호 4회선 병가)","2016-10-10 07:00","2016-10-15 18:00","2016-10-10 07:00","2016-10-15 18:00","연속",null,null,null,"-"]
[122,"경기","동부","성현분당#1 T/L","154kV 분당-오포#2T/L 낙뢰소산장치 철거공사","154kV 분당-오포#2T/L 가공지선 및 OPGW 1~28호 구간 낙뢰소산장치 철거(분당-오포#2T/L 및 성현-분당#1T/L 2~18호 4회선 병가)","2016-10-10 07:00","2016-10-15 18:00","2016-10-10 07:00","2016-10-15 18:00","연속",null,null,null,"○"]
[123,"경기","동부","야탑성현#2 T/L","16년 동부 변전협력회사 총액공사","야탑-성현#2T/L GIS 보통점검(양단)","2016-10-18 09:30","2016-10-18 18:00","2016-10-18 09:30","2016-10-18 18:00","당일",null,null,null,"-"]
[124,"경기","동부","야탑성현#1 T/L","16년 동부 변전협력회사 총액공사","야탑-성현#1T/L GIS 보통점검(양단)","2016-10-17 09:30","2016-10-17 18:00","2016-10-17 09:30","2016-10-17 18:00","당일",null,null,null,"-"]
[125,"경기","동부","이천율현#1 T/L","154kV 이천S/S #2Sh.C 설치공사","- 170kV GIS #60-65BUS PT BAY 설치 - 170kV GIS 6100 BUS-TIE BAY 설치 - 170kV GIS BUS-SEC 설치 - 170kV GIS #61-66BUS PT 이설 설치 - 170kV GIS #2Sh.C BAY 설치 - 154kV #2Sh.C 1대 설치 - 모선보호반, CPD반, Sh.C 보호반 등 관련","2016-10-07 09:30","2016-10-10 18:00","2016-10-07 09:30","2016-10-10 18:00","연속",null,null,null,"-"]
[126,"경기","동부","이천율현#2 T/L","154kV 이천S/S #2Sh.C 설치공사","- 170kV GIS #60-65BUS PT BAY 설치 - 170kV GIS 6100 BUS-TIE BAY 설치 - 170kV GIS BUS-SEC 설치 - 170kV GIS #61-66BUS PT 이설 설치 - 170kV GIS #2Sh.C BAY 설치 - 154kV #2Sh.C 1대 설치 - 모선보호반, CPD반, Sh.C 보호반 등 관련","2016-10-11 09:30","2016-10-15 18:00","2016-10-11 09:30","2016-10-15 18:00","연속",null,null,null,"-"]
[127,"경기","동부","이천율현#1 T/L","154kV 이천S/S #2Sh.C 설치공사","- 170kV GIS #60-65BUS PT BAY 설치 - 170kV GIS 6100 BUS-TIE BAY 설치 - 170kV GIS BUS-SEC 설치 - 170kV GIS #61-66BUS PT 이설 설치 - 170kV GIS #2Sh.C BAY 설치 - 154kV #2Sh.C 1대 설치 - 모선보호반, CPD반, Sh.C 보호반 등 관련","2016-10-23 09:30","2016-10-26 18:00","2016-10-23 09:30","2016-10-26 18:00","연속",null,null,null,"-"]
[128,"경기","동부","이천율현#2 T/L","154kV 이천S/S #2Sh.C 설치공사","- 170kV GIS #60-65BUS PT BAY 설치 - 170kV GIS 6100 BUS-TIE BAY 설치 - 170kV GIS BUS-SEC 설치 - 170kV GIS #61-66BUS PT 이설 설치 - 170kV GIS #2Sh.C BAY 설치 - 154kV #2Sh.C 1대 설치 - 모선보호반, CPD반, Sh.C 보호반 등 관련","2016-10-27 09:30","2016-10-31 18:00","2016-10-27 09:30","2016-10-31 18:00","연속",null,null,null,"-"]
[129,"경기","동부","동판교야탑 T/L","성남-장호원 도로개설에 따른 지장송전선로 이설공사","케이블 철거 및 신규포설 2구간 케이블 접속 3개소(NJ2, IJ1)","2016-10-28 09:00","2016-11-14 18:00","2016-10-28 09:00","2016-11-14 18:00","연속",null,null,null,"-"]
[130,"경기","성남","서판교중원#1 T/L","성남-장호원 도로개설에 따른 지장송전선로 이설공사","케이블 철거 및 신규포설 2구간 케이블 접속 3개소(NJ2, IJ1)","2016-10-09 09:00","2016-10-26 18:00","2016-10-09 09:00","2016-10-26 18:00","연속",null,null,null,"-"]
[131,"경기","성남","신용인용인#1 T/L","용인S/S 신용인용인#1T/L GIS 초기점검","용인S/S 신용인용인#1T/L GIS 초기점검","2016-10-03 09:30","2016-10-03 18:00","2016-10-03 09:30","2016-10-03 18:00","당일",null,null,"신뢰도개선","-"]
[132,"경기","성남","율현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S #3M.Tr GIS 설치공사 무부하 가압","2016-10-12 09:00","2016-10-14 18:00","2016-10-12 09:00","2016-10-14 18:00","연속",null,null,null,"-"]
[133,"경기","성남","모현용인#1 T/L","154kV 모현-용인T/L 안전이격거리 확보공사(가선로 구성)","0 지지물 교체 : 1기(No.19) 0 가철탑 설치 및 철거 : 1기 0 전선교체 : 1.214km 0 기타공사 1식","2016-10-22 07:00","2016-10-23 18:00","2016-10-22 07:00","2016-10-23 18:00","연속",null,null,null,"-"]
[134,"경기","성남","율현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S #4M.Tr GIS 설치공사 무부하 가압","2016-10-19 09:00","2016-10-21 18:00","2016-10-19 09:00","2016-10-21 18:00","연속",null,null,null,"-"]
[135,"경기","성남","율현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S #2M.Tr GIS 설치공사 무부하 가압","2016-10-06 09:00","2016-10-08 18:00","2016-10-06 09:00","2016-10-08 18:00","연속",null,null,null,"-"]
[136,"경기","성남","모현용인#2 T/L","154kV 모현-용인T/L 안전이격거리 확보공사(가선로 구성)","0 지지물 교체 : 1기(No.19) 0 가철탑 설치 및 철거 : 1기 0 전선교체 : 1.214km 0 기타공사 1식","2016-10-24 07:00","2016-10-25 18:00","2016-10-24 07:00","2016-10-25 18:00","연속",null,null,null,"-"]
[137,"경기","성남","율현용인#1 T/L","154kV 용인S/S 무인화대비 설비보강공사","154kV 용인S/S #5M.Tr GIS 설치공사","2016-10-26 09:00","2016-10-28 18:00","2016-10-26 09:00","2016-10-28 18:00","연속",null,null,null,"-"]
[138,"경기","성남","서안성안성#1 T/L","서안성S/S 154kV GIS 설치공사","154kV GIS 4CCT 설치","2016-10-07 09:00","2016-10-09 18:00","2016-10-07 09:00","2016-10-09 18:00","연속",null,null,null,"-"]
[139,"경기","성남","서안성S/S #61M.Tr(ESS) CB","345kV 서안성S/S #4M.Tr 증설공사","345kV M.Tr 1Bank, 345kV GIS 2CB, 154kV GIS 4CCT 증설관련 모선보호반 변경(#61,66->#62,67)시험","2016-10-18 13:00","2016-10-18 17:00","2016-10-18 13:00","2016-10-18 17:00","연속",null,null,null,"-"]
[140,"경기","직할","발안향남#2 T/L","발안변전소 창호누수 보수공사","- 건물배면 창호, 유리코킹 보수","2016-10-06 08:00","2016-10-06 18:00","2016-10-06 08:00","2016-10-06 18:00","당일",null,null,null,"-"]
[141,"경기","직할","발안향남#1 T/L","발안변전소 창호누수 보수공사","- 건물배면 창호, 유리코킹 보수","2016-10-05 08:00","2016-10-05 18:00","2016-10-05 08:00","2016-10-05 18:00","당일",null,null,null,"-"]
[142,"경기","직할","율전의왕#1 T/L","154kV 율전의왕#1T/L 피뢰기 설치공사","1~11호간 피뢰기 설치(11기)","2016-10-15 07:00","2016-10-16 18:00","2016-10-15 07:00","2016-10-16 18:00","연속",null,null,null,"-"]
[143,"경기","직할","화성조암#1 T/L","화성S/S 154kV 화성조암#1T/L 전자변히터, 트립와이어 설치","화성S/S 154kV 화성조암#1T/L 전자변히터, 트립와이어 설치","2016-10-01 09:00","2016-10-01 18:00","2016-10-01 09:00","2016-10-01 18:00","당일",null,null,null,"-"]
[144,"경기","평택","송탄소사벌 T/L","평택동삭2지구 지중화","154kV 송탄-안성(소사벌) No.8~11 지중화","2016-10-27 08:00","2016-10-28 18:00","2016-10-27 08:00","2016-10-28 18:00","연속",null,null,null,"-"]
[145,"경기","평택","송탄S/S 송탄-오성복합#2T/L(617) GIS","송탄S/S 송탄-오성복합#2T/L 장기사용 GIS 대체공사","송탄S/S 송탄-오성복합#2T/L 장기사용 GIS 대체공사","2016-10-08 09:00","2016-10-26 18:00","2016-10-08 09:00","2016-10-26 18:00","연속",null,null,null,"-"]
[146,"경기","평택","송탄안성 T/L","평택동삭2지구 지중화","154kV 송탄-안성(소사벌) No.8~11 지중화","2016-10-29 08:00","2016-11-05 18:00","2016-10-29 08:00","2016-11-05 18:00","연속",null,null,null,"○"]
[147,"경기","평택","오산향남#1 T/L","154kV 오산-향남#1T/L 초기점검(구간 향남S/S~No.2)","154kV 오산-향남#1T/L 초기점검(구간 향남S/S~No.2) - 신설철탑 초기점검","2016-10-14 09:00","2016-10-14 12:00","2016-10-14 09:00","2016-10-14 12:00","당일",null,null,null,"-"]
[148,"경기","평택","오산향남#2 T/L","154kV 오산-향남#2T/L 초기점검(구간 향남S/S~No.2)","154kV 오산-향남#2T/L 초기점검(구간 향남S/S~No.2) - 신설철탑 초기점검","2016-10-14 13:00","2016-10-14 16:00","2016-10-14 13:00","2016-10-14 16:00","당일",null,null,null,"-"]
[149,"경기","평택","청북평택#2 T/L","154kV 청북-평택T/L 피뢰기 설치공사","- 청북S/S 인출 4회선구간 상간스페이서 설치(3경간) - 청북평택#2T/L 송전용피뢰기 설치(26기) - 만호분기T/L 송전용피뢰기 설치(4기)","2016-10-01 08:00","2016-10-03 18:00","2016-10-01 08:00","2016-10-03 18:00","매일",null,null,null,"-"]
[150,"경기","평택","만호청북#1 T/L","154kV 만호-청북T/L 상간스페이서설치공사","- 청북S/S 인출 4회선구간 상간스페이서 설치(3경간) - 만호분기T/L 송전용피뢰기 설치(4기)","2016-10-01 08:00","2016-10-03 18:00","2016-10-01 08:00","2016-10-03 18:00","매일",null,null,null,"-"]
[151,"경기","평택","둔포추팔#2 T/L","추팔S/S 둔포추팔#2T/L GIS 정밀점검","추팔S/S 둔포추팔#2T/L GIS 정밀점검","2016-10-20 09:00","2016-10-22 18:00","2016-10-20 09:00","2016-10-22 18:00","연속",null,null,null,"-"]
[152,"경기","평택","평택추팔#1 T/L","추팔S/S 6100 GIS 정밀점검","추팔S/S 6100 GIS 정밀점검간 모선 무부하가압 조작시 휴전","2016-10-13 09:00","2016-10-15 18:00","2016-10-13 09:00","2016-10-15 18:00","매일",null,null,null,"-"]
[153,"경기","평택","둔포추팔#1 T/L","추팔S/S 둔포추팔#1T/L GIS 정밀점검","추팔S/S 둔포추팔#1T/L GIS 정밀점검","2016-10-07 09:00","2016-10-09 18:00","2016-10-07 09:00","2016-10-09 18:00","연속",null,null,null,"-"]
[154,"경기","평택","평택추팔#1 T/L","154kV 추팔S/S #4M.Tr증설공사","M.Tr(15/20MVA*3)*1BANK 설치 154kV GIS 1CCT 설치 23kV GIS 3CCT 설치(GIB*5포함)","2016-10-25 10:30","2016-10-27 11:00","2016-10-25 10:30","2016-10-27 11:00","연속",null,null,null,"-"]
[155,"강원","강릉","신양양_양양#2 T/L","양양S/S 외장재 교체공사","드라이비트 철거 및 메탈판넬 설치","2016-10-22 09:00","2016-10-28 18:00","2016-10-22 09:00","2016-10-28 18:00","매일",null,null,null,"-"]
[156,"강원","강릉","신양양_양양#1 T/L","양양S/S 외장재 교체공사","드라이비트 철거 및 메탈판넬 설치","2016-10-26 09:00","2016-11-01 18:00","2016-10-26 09:00","2016-11-01 18:00","매일",null,null,null,"-"]
[157,"강원","강릉","북평영동TP#1 T/L","2016년 가공송전 순시점검 위탁공사","○ 154kV 북평영동TP 정밀점검(영동TP-No.47)","2016-10-10 09:00","2016-10-12 18:00","2016-10-10 09:00","2016-10-12 18:00","매일",null,null,null,"-"]
[158,"강원","강릉","북평영동TP#2 T/L","2016년 가공송전 순시점검 위탁공사","○ 154kV 북평영동TP 정밀점검(영동TP-No.47)","2016-10-13 09:00","2016-10-17 18:00","2016-10-13 09:00","2016-10-17 18:00","매일",null,null,null,"-"]
[159,"강원","강릉","주진평창#2 T/L","154kV 주진평창T/L 안전이격거리 확보공사","○ 철탑이설 No.18~20 (No.18, 19, 20호의 철탑 위치가 기설철탑의 지그재그로 이루어져 1회선씩 휴전시 #1, #2, #1 순서로 8일씩 총 24일 소요 예정 및 철탑이설 위치가 산악지, 급경사지로 인해 안전을 위해 2회선 동시휴전 요청)","2016-10-01 09:00","2016-10-10 18:00","2016-10-01 09:00","2016-10-10 18:00","연속",null,null,null,"-"]
[160,"강원","강릉","주진평창#1 T/L","154kV 주진평창T/L 안전이격거리 확보공사","○ 철탑이설 No.18~20 (No.18, 19, 20호의 철탑 위치가 기설철탑의 지그재그로 이루어져 1회선씩 휴전시 #1, #2, #1 순서로 8일씩 총 24일 소요 예정 및 철탑이설 위치가 산악지, 급경사지로 인해 안전을 위해 2회선 동시휴전 요청)","2016-10-01 09:00","2016-10-10 18:00","2016-10-01 09:00","2016-10-10 18:00","연속",null,null,null,"-"]
[161,"강원","강릉","강릉횡계#1 T/L","횡계S/S 외장재 교체공사","드라이비트 철거 및 메탈판넬 설치공사","2016-10-18 09:00","2016-10-24 18:00","2016-10-18 09:00","2016-10-24 18:00","매일",null,null,null,"-"]
[162,"강원","강릉","강릉횡계#2 T/L","횡계S/S 외장재 교체공사","드라이비트 철거 및 메탈판넬 설치공사","2016-10-14 09:00","2016-10-20 18:00","2016-10-14 09:00","2016-10-20 18:00","매일",null,null,null,"-"]
[163,"강원","강릉","주문진양양#2 T/L","양양변전소 외장재 교체공사","외장재 철거 및 교체","2016-10-15 09:00","2016-10-21 18:00","2016-10-15 09:00","2016-10-21 18:00","매일",null,null,null,"-"]
[164,"강원","강릉","주문진양양#1 T/L","양양변전소 외장재 교체공사","외장재 철거 및 교체","2016-10-11 09:00","2016-10-17 18:00","2016-10-11 09:00","2016-10-17 18:00","매일",null,null,null,"-"]
[165,"강원","동해","이원도계 T/L","2016년도 가공송전선로 순시점검 위탁공사","1. 도계분기T/L 정밀점검(1기)","2016-10-07 14:00","2016-10-07 18:00","2016-10-07 14:00","2016-10-07 18:00","매일",null,null,null,"-"]
[166,"강원","동해","도계태백 T/L","2016년도 가공송전선로 순시점검 위탁공사","1. 도계분기T/L 정밀점검(1기)","2016-10-07 09:00","2016-10-07 12:00","2016-10-07 09:00","2016-10-07 12:00","매일",null,null,null,"-"]
[167,"강원","동해","동해정선 T/L","2016~17년도 동해전력지사 송전정비 협력회사 총액공사","섬락애자교체('16.8.7 낙뢰)","2016-10-10 09:00","2016-10-10 18:00","2016-10-10 09:00","2016-10-10 18:00","당일",null,null,null,"-"]
[168,"강원","동해","태백삼척GP#2 T/L","2016년 동해전력지사 변전협력회사 총액공사","1. 삼척G/P 태백삼척GP#2T/L GIS 초기점검 2. 삼척G/P 태백삼척GP#2T/L PT 초기점검 3. 삼척G/P 태백삼척GP#2T/L LA 초기점검","2016-10-19 09:30","2016-10-19 18:00","2016-10-19 09:30","2016-10-19 18:00","당일",null,null,null,"-"]
[169,"강원","동해","태백삼척GP#1 T/L","2016년 동해전력지사 변전협력회사 총액공사","1. 삼척G/P 태백삼척GP#1T/L GIS 초기점검 2. 삼척G/P 태백삼척GP#1T/L PT 초기점검 3. 삼척G/P 태백삼척GP#1T/L LA 초기점검","2016-10-18 09:30","2016-10-18 18:00","2016-10-18 09:30","2016-10-18 18:00","당일",null,null,null,"-"]
[170,"강원","동해","삼척동해TP T/L","2016년 동해전력지사 변전협력회사 총액공사","1. 삼척S/S 삼척-동해TP T/L LA 교체 2. 장기미동작차단기 조작시험","2016-10-05 09:30","2016-10-05 18:00","2016-10-05 09:30","2016-10-05 18:00","당일",null,null,null,"-"]
[171,"강원","동해","동해이원#1 T/L","2016년 동해전력지사 변전협력회사 총액공사","1. 이원S/S 동해-이원#1T/L LA 교체","2016-10-06 09:30","2016-10-06 18:00","2016-10-06 09:30","2016-10-06 18:00","당일",null,null,null,"-"]
[172,"강원","원주","남원주원주#2 T/L","154kV 남원주-원주T/L 철탑 만곡개소 보강공사","- 공사대상 : 154kV 남원주-원주T/L No.9, 17, 20 - 공사내용 : 철탑 만곡개소(Arm) 보강","2016-10-19 08:00","2016-10-19 18:00","2016-10-19 08:00","2016-10-19 18:00","당일",null,null,null,"-"]
[173,"강원","원주","남원주원주#1 T/L","154kV 남원주-원주T/L 철탑 만곡개소 보강공사","- 공사대상 : 154kV 남원주-원주T/L No.26, 30 - 공사내용 : 철탑 만곡개소(Arm) 보강","2016-10-13 08:00","2016-10-13 18:00","2016-10-13 08:00","2016-10-13 18:00","당일",null,null,null,"-"]
[174,"강원","원주","홍천남춘천 T/L","장기미동작 차단기 시험","홍천S/S 홍천-남춘천T/L 장기미동작 차단기 시험","2016-10-05 10:00","2016-10-05 18:00","2016-10-05 10:00","2016-10-05 18:00","당일",null,null,null,"-"]
[175,"강원","원주","홍천상남#1 T/L","154kV 홍천-상남T/L 전선접속개소 해소공사","- 공사구간 : 홍천-상남#1T/L No.32~33 등 5구간 - 공사내용 : 전선접속개소 해소 전력선 교체","2016-10-01 08:00","2016-10-07 18:00","2016-10-01 08:00","2016-10-07 18:00","연속",null,null,null,"-"]
[176,"강원","원주","홍천상남#2 T/L","154kV 홍천-상남T/L 전선접속개소 해소공사","- 공사구간 : 홍천-상남#2T/L No.32~33 등 4구간 - 공사내용 : 전선접속개소 해소 전력선 및 가공지선 교체","2016-10-08 08:00","2016-10-14 18:00","2016-10-08 08:00","2016-10-14 18:00","연속",null,null,null,"-"]
[177,"강원","직할","남춘천청평PP T/L","춘천집단에너지 송전선로 건설공사","청평양수 #3,4T/L 70호 보강 및 계통연계","2016-10-05 09:00","2016-10-17 18:00","2016-10-05 09:00","2016-10-17 18:00","연속",null,null,null,"-"]
[178,"강원","직할","의암H/P 154kV BUS","2016-17 강원지역본부 직할 협력회사 총액공사 기기점검","154kV #1 BUS PT A, B, C상 보통점검","2016-10-06 09:00","2016-10-06 18:00","2016-10-06 09:00","2016-10-06 18:00","당일",null,null,null,"-"]
[179,"강원","직할","청평HP의암HP T/L","2016~2017년 강원직할 송전정비 협력회사 총액공사","항공도장 2기","2016-10-06 09:00","2016-10-07 18:00","2016-10-06 09:00","2016-10-07 18:00","매일",null,null,null,"-"]
[180,"강원","직할","상남인제#2 T/L","154kV 인제-양구T/L 용량증대 전력선 교체공사 안전확보","인제S/S ~ No.125구간 전력선 교체구간 안전확보","2016-10-17 09:00","2016-10-20 18:00","2016-10-17 09:00","2016-10-20 18:00","연속",null,null,null,"-"]
[181,"강원","직할","북춘천화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ 철탑신설 : 6기 ○ 전선교체 : 2C-2.925km ○ 정밀점검 시행","2016-10-24 08:00","2016-10-25 18:00","2016-10-24 08:00","2016-10-25 18:00","연속",null,null,null,"-"]
[182,"강원","직할","가평화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ 철탑신설 : 6기 ○ 전선교체 : 2C-2.925km ○ 정밀점검 시행","2016-10-26 08:00","2016-10-31 18:00","2016-10-26 08:00","2016-10-31 18:00","연속",null,null,null,"-"]
[183,"강원","직할","가평화천HP T/L","154kV 화천T/L 안전이격 확보공사","○ 철탑신설 : 6기 ○ 전선교체 : 2C-2.925km ○ 정밀점검 시행","2016-10-22 08:00","2016-10-23 18:00","2016-10-22 08:00","2016-10-23 18:00","연속",null,null,null,"-"]
[184,"강원","직할","화천H/P 154kV BUS TIE CB","2016-17 강원지역본부 직할 협력회사 총액공사 기기점검","154kV BUS-TIE GCB 보통점검","2016-10-05 09:00","2016-10-05 18:00","2016-10-05 09:00","2016-10-05 18:00","연속",null,null,null,"-"]
[185,"강원","태백","동해동영월 T/L","2016년 가공송전선로 순시점검 위탁공사","154kV 동해-동영월T/L 정밀점검","2016-10-22 09:00","2016-10-26 18:00","2016-10-22 09:00","2016-10-26 18:00","매일",null,null,null,"-"]
[186,"강원","태백","정선영월CC T/L","154kV 영월화력T/L 안전이격확보공사","정선영월CCTL No.4~6호 가선공사","2016-10-27 09:00","2016-11-02 18:00","2016-10-27 09:00","2016-11-02 18:00","연속",null,null,null,"-"]
[187,"강원","태백","제천영월#2 T/L","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","영월S/S 제천-영월#2T/L CB 조작시험","2016-10-05 14:00","2016-10-05 18:00","2016-10-05 14:00","2016-10-05 18:00","당일",null,null,null,"-"]
[188,"강원","태백","제천영월#1 T/L","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","영월S/S 제천-영월#1T/L CB 조작시험","2016-10-05 10:00","2016-10-05 14:00","2016-10-05 10:00","2016-10-05 14:00","당일",null,null,null,"-"]
[189,"충북","직할","금왕S/S 154kV #1 BUS TIE GIS","16년도 직할 154kV 개폐장치 정밀점검 공사","금왕S/S 154kV #1BUS TIE GIS(6101DS,6102DS,6100CB) 정밀점검","2016-10-24 09:00","2016-10-25 18:00","2016-10-24 09:00","2016-10-25 18:00","연속",null,null,null,"○"]
[190,"충북","직할","단양영월CC#2 T/L","154kV 단양-영월CCT/L 안전이격확보공사","○ 공사구간 : 154kV 단양-영월CC T/L 34 ∼ 36호, 42 ∼ 45호간 ○ 철탑교체 : 154kV 2회선용 6기 (35, 36, 42, 43, 44, 45호), 상부재교체 (34, 46호) ○ 전력선교체 : HSTACIR/AW 330㎟(S) × 2회선 (2.129km) ○ 가공지선교체 : OPGW 70㎟ × 1조","2016-10-22 08:00","2016-10-23 18:00","2016-10-22 08:00","2016-10-23 18:00","연속",null,null,null,"-"]
[191,"충북","직할","단양영월CC#2 T/L","154kV 단양-영월CCT/L 안전이격확보공사","○ 공사구간 : 154kV 단양-영월CC T/L 34 ∼ 36호, 42 ∼ 45호간 ○ 철탑교체 : 154kV 2회선용 6기 (35, 36, 42, 43, 44, 45호), 상부재교체 (34, 46호) ○ 전력선교체 : HSTACIR/AW 330㎟(S) × 2회선 (2.129km) ○ 가공지선교체 : OPGW 70㎟ × 1조","2016-10-14 08:00","2016-10-19 18:00","2016-10-14 08:00","2016-10-19 18:00","연속",null,null,null,"-"]
[192,"충북","직할","단양영월CC#1 T/L","154kV 단양-영월CCT/L 안전이격확보공사","○ 공사구간 : 154kV 단양-영월CC T/L 34 ∼ 36호, 42 ∼ 45호간 ○ 철탑교체 : 154kV 2회선용 6기 (35, 36, 42, 43, 44, 45호), 상부재교체 (34, 46호) ○ 전력선교체 : HSTACIR/AW 330㎟(S) × 2회선 (2.129km) ○ 가공지선교체 : OPGW 70㎟ × 1조","2016-10-20 08:00","2016-11-04 18:00","2016-10-20 08:00","2016-11-04 18:00","연속",null,null,null,"-"]
[193,"충북","직할","신제천왕암#1 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","4회선 구간 휴전에 따른 안전조치, SB댐퍼 설치","2016-10-04 07:30","2016-10-13 18:00","2016-10-04 07:30","2016-10-13 18:00","매일",null,null,null,"-"]
[194,"충북","직할","신제천제천#1 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","전력선 교체, 애자련 보강, 조류착지방지장치 설치","2016-10-04 07:30","2016-10-13 18:00","2016-10-04 07:30","2016-10-13 18:00","연속",null,null,null,"-"]
[195,"충북","직할","신제천왕암#2 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","4회선 구간 휴전에 따른 안전조치, 피뢰기 설치, SB댐퍼 설치","2016-10-14 07:30","2016-10-27 18:00","2016-10-14 07:30","2016-10-27 18:00","매일",null,null,null,"-"]
[196,"충북","직할","신제천제천#2 T/L","2016~17년 충북지역본부 직할 송전정비 협력회사 총액공사","전력선 교체, 피뢰기 설치, 애자련 보강, 조류착지방지장치 설치","2016-10-14 07:30","2016-10-27 18:00","2016-10-14 07:30","2016-10-27 18:00","연속",null,null,null,"-"]
[197,"충북","직할","왕암가남#2 T/L","154kV 왕암-가남T/L 132호 안전이격확보공사","철탑설치 1기, 철탑보강 1기, 철탑철거 1기, 전력선 교체 0.799km","2016-10-22 08:00","2016-10-28 18:00","취소","취소","연속",null,null,null,"-"]
[198,"충북","직할","왕암가남#1 T/L","154kV 왕암-가남T/L 132호 안전이격확보공사","철탑설치 1기, 철탑보강 1기, 철탑철거 1기, 전력선 교체 0.799km","2016-10-20 08:00","2016-10-28 18:00","취소","취소","연속",null,null,null,"-"]
[199,"충북","직할","풍동음성#1 T/L","음성S/S 풍동음성#1 T/L LA 대체","풍동음성#1 T/L LA 대체 작업","2016-10-10 09:00","2016-10-10 18:00","2016-10-10 09:00","2016-10-10 18:00","당일",null,null,null,"○"]
[200,"충북","청주","봉명상당#1 T/L","154kV 봉명-상당 T/L 접속함 Recall 공사","일진제 PMJ 접속함 42개소 Recall 공사","2016-10-17 09:00","2016-11-02 18:00","2016-10-17 09:00","2016-11-02 18:00","연속",null,null,null,"-"]
[201,"충북","청주","부강월산#1 T/L","2016년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 청원-부강T/L 정밀점검시 안전상 휴전","2016-10-05 09:00","2016-10-05 18:00","2016-10-05 09:00","2016-10-05 18:00","당일",null,null,null,"○"]
[202,"충북","청주","청원부강#2 T/L","2016년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 청원-부강T/L 정밀점검","2016-10-05 09:00","2016-10-05 18:00","2016-10-05 09:00","2016-10-05 18:00","당일",null,null,null,"-"]
[203,"충북","청주","청원부강#1 T/L","2016년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 청원-부강T/L 정밀점검","2016-10-04 09:00","2016-10-04 18:00","2016-10-04 09:00","2016-10-04 18:00","당일",null,null,null,"○"]
[204,"충북","청주","부강월산#2 T/L","2016년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 청원-부강T/L 정밀점검시 안전상 휴전","2016-10-04 09:00","2016-10-04 18:00","2016-10-04 09:00","2016-10-04 18:00","당일",null,null,null,"-"]
[205,"충북","청주","신옥천남대전#2 T/L","16년 청주전력지사 변전협력회사 총액공사","신옥천S/S 신옥천남대전#2 T/L 컴프레샤 보수","2016-10-05 09:30","2016-10-05 18:00","2016-10-05 09:30","2016-10-05 18:00","당일",null,null,null,"-"]
[206,"충북","청주","청원부강#2 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","4회선 병가선로 안전상 휴전(이격거리 확보)","2016-10-03 08:00","2016-10-03 19:00","2016-10-03 08:00","2016-10-03 19:00","매일",null,null,null,"-"]
[207,"충북","청주","청원죽림#1 T/L","16년 하반기 청주전력지사 170kV GIS 정밀점검공사","청원S/S 청원-죽림#1 T/L (637CB, 631, 632DS) 정밀점검","2016-10-07 09:30","2016-10-09 18:00","2016-10-07 09:30","2016-10-09 18:00","연속",null,null,null,"-"]
[208,"충북","청주","청원죽림#2 T/L","16년 하반기 청주전력지사 170kV GIS 정밀점검공사","청원S/S 청원죽림#2 T/L GIS (647 CB, 641,642DS)정밀점검","2016-10-14 09:30","2016-10-16 18:00","2016-10-14 09:30","2016-10-16 18:00","연속",null,null,null,"-"]
[209,"충북","충주","신진천S/S 154kV #67 BUS","신진천S/S 170GIS 정밀점검 및 지반침하 관련 점검","신진천S/S 170GIS 정밀점검 및 지반침하 관련 점검","2016-10-05 09:00","2016-10-08 18:00","2016-10-05 09:00","2016-10-08 18:00","연속",null,null,null,"-"]
[210,"충북","충주","신진천S/S 154kV #66 BUS","신진천S/S 170GIS 정밀점검 및 지반침하 관련 점검","신진천S/S 170GIS 정밀점검 및 지반침하 관련 점검","2016-10-05 09:00","2016-10-08 18:00","2016-10-05 09:00","2016-10-08 18:00","연속",null,null,null,"-"]
[211,"충북","충주","신진천S/S 154kV #61 BUS","신진천S/S 170GIS 정밀점검 및 지반침하 관련 점검","신진천S/S 170GIS 정밀점검 및 지반침하 관련 점검","2016-10-09 09:00","2016-10-13 18:00","2016-10-09 09:00","2016-10-13 18:00","연속",null,null,null,"-"]
[212,"충북","충주","신진천S/S 154kV #62 BUS","신진천S/S 170GIS 정밀점검 및 지반침하 관련 점검","신진천S/S 170GIS 정밀점검 및 지반침하 관련 점검","2016-10-09 09:00","2016-10-13 18:00","2016-10-09 09:00","2016-10-13 18:00","연속",null,null,null,"-"]
[213,"충북","충주","진천덕산#1 T/L","2016년도 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.1~27)","2016-10-04 09:00","2016-10-05 18:00","2016-10-04 09:00","2016-10-05 18:00","매일",null,null,null,"○"]
[214,"충북","충주","진천덕산#2 T/L","2016년도 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 (No.1~27)","2016-10-06 09:00","2016-10-07 18:00","2016-10-06 09:00","2016-10-07 18:00","매일",null,null,null,"-"]
[215,"충북","충주","충주S/S 154kV #65-66 BUS SEC GIS","GIS 보통점검","GIS 보통점검","2016-10-13 10:00","2016-10-13 18:00","2016-10-13 10:00","2016-10-13 18:00","당일",null,null,null,"-"]
[216,"충북","충주","충주S/S 154kV #60-61 BUS SEC GIS","GIS 보통점검","GIS 보통점검","2016-10-13 10:00","2016-10-13 18:00","2016-10-13 10:00","2016-10-13 18:00","당일",null,null,null,"-"]
[217,"충북","충주","충주S/S 154kV #2 BUS TIE GIS","GIS 보통점검","GIS 보통점검","2016-10-12 10:00","2016-10-12 18:00","2016-10-12 10:00","2016-10-12 18:00","당일",null,null,null,"-"]
[218,"대전충남","대전","가수원S/S LH열병합 T/L CB","○ 154kV 가수원S/S LH열병합T/L GIS 보통점검","○ 154kV 가수원S/S LH열병합T/L GIS 보통점검","2016-10-06 09:00","2016-10-06 18:00","2016-10-06T09:00:00","2016-10-06T18:00:00","당일",null,null,null,"-"]
[219,"대전충남","대전","신계룡은진#2 T/L","154kV 신계룡-은진T/L 안전이격확보공사","안전이격확보공사 : 3기 철거 및 설치 (No.46,47,59)","2016-10-31 07:00","2016-11-10 18:00","2016-10-31T07:00:00","2016-11-10T18:00:00","연속",null,null,null,"-"]
[220,"대전충남","대전","신계룡가수원#1 T/L","154kV 신계룡-유성#1T/L 피뢰기 설치공사 (안전이격거리확보)","No1~18간 안전이격확보","2016-10-06 07:00","2016-10-07 18:00","2016-10-06T07:00:00","2016-10-07T18:00:00","매일",null,null,null,"-"]
[221,"대전충남","대전","신계룡은진#1 T/L","154kV 신계룡-은진T/L 안전이격확보공사","안전이격확보공사 : 3기 철거 및 설치 (No.46,47,59)","2016-10-01 07:00","2016-10-30 18:00","2016-10-01T07:00:00","2016-10-30T18:00:00","연속",null,null,null,"-"]
[222,"대전충남","세종","천안전의#2 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS보통점검","2016-10-07 09:30","2016-10-07 18:00","2016-10-07T09:30:00","2016-10-07T18:00:00","당일",null,null,null,"-"]
[223,"대전충남","아산","신온양한샘#1 T/L","신온양S/S 154kV 신온양-한샘#1T/L 보호배전반 교체","○ 154kV 신온양-한샘#1T/L 보호배전반 교체 ○ 병행) 한샘S/S 154kV 신온양-한샘#1T/L 보호배전반 교체","2016-10-10 09:00","2016-10-13 18:00","2016-10-10T09:00:00","2016-10-13T18:00:00","연속",null,null,null,"-"]
[224,"대전충남","아산","아산온양#2 T/L","[송전] 154kV 아산-온양#2T/L 정밀점검","154kV 아산-온양#2T/L 정밀점검 - 구간 : 1~56호","2016-10-29 07:00","2016-10-31 18:00","2016-10-29T07:00:00","2016-10-31T18:00:00","매일",null,null,null,"-"]
[225,"대전충남","아산","아산S/S 154kV #61 BUS","아산S/S 154kV 아산-예산#2T/L GIS 정밀점검","○ 154kV 아산-예산#2T/L GIS 정밀점검, LA 보통점검 ○ 병행) 예산S/S 154kV 아산-예산#2T/L GIS, LA 보통점검","2016-10-27 15:00","2016-10-28 18:00","2016-10-27T15:00:00","2016-10-28T18:00:00","연속",null,null,null,"-"]
[226,"대전충남","아산","아산S/S 154kV #66 BUS","아산S/S 154kV 아산-예산#1T/L GIS 정밀점검","○ 154kV 아산-예산#1T/L GIS 정밀점검, LA 보통점검 ○ 병행) 예산S/S 154kV 아산-예산#1T/L GIS, LA 보통점검","2016-10-19 09:00","2016-10-20 15:00","2016-10-19T09:00:00","2016-10-20T15:00:00","연속",null,null,null,"-"]
[227,"대전충남","아산","아산S/S 154kV #61 BUS","아산S/S 154kV 아산-예산#1T/L GIS 정밀점검","○ 154kV 아산-예산#1T/L GIS 정밀점검, LA 보통점검 ○ 병행) 예산S/S 154kV 아산-예산#1T/L GIS, LA 보통점검","2016-10-20 15:00","2016-10-21 18:00","2016-10-20T15:00:00","2016-10-21T18:00:00","연속",null,null,null,"-"]
[228,"대전충남","아산","아산S/S 154kV #66 BUS","아산S/S 154kV 아산-예산#2T/L GIS 정밀점검","○ 154kV 아산-예산#2T/L GIS 정밀점검, LA 보통점검 ○ 병행) 예산S/S 154kV 아산-예산#2T/L GIS, LA 보통점검","2016-10-26 09:00","2016-10-27 15:00","2016-10-26T09:00:00","2016-10-27T15:00:00","연속",null,null,null,"-"]
[229,"대전충남","아산","아산온양#1 T/L","[송전] 154kV 아산-온양#1T/L 정밀점검","154kV 아산-온양#1T/L 정밀점검 - 구간 : 1~56호","2016-10-21 07:00","2016-10-23 18:00","2016-10-21T07:00:00","2016-10-23T18:00:00","매일",null,null,null,"-"]
[230,"대전충남","아산","온양풍세#2 T/L","[송전] 154kV 온양-풍세#2T/L 정밀점검","154kV 온양-풍세#2T/L 정밀점검 - 구간 : 1~56호","2016-10-31 07:00","2016-10-31 18:00","2016-10-31T07:00:00","2016-10-31T18:00:00","매일",null,null,null,"-"]
[231,"대전충남","아산","온양풍세#1 T/L","[송전] 154kV 온양-풍세#1T/L 정밀점검","154kV 온양-풍세#1T/L 정밀점검 - 구간 : 1~56호","2016-10-23 07:00","2016-10-23 18:00","2016-10-23T07:00:00","2016-10-23T18:00:00","매일",null,null,null,"-"]
[232,"대전충남","아산","온양풍세#1 T/L","온양S/S 170kV 장기사용 GIS 보강공사","○170kV 장기사용 GIS 보강공사","2016-10-01 09:00","2016-10-01 18:00","2016-10-01T09:00:00","2016-10-01T18:00:00","연속",null,null,null,"-"]
[233,"대전충남","아산","둔포한샘#2 T/L","[송전] 154kV 한샘-둔포T/L 19호 안전이격확보공사","ㅇ철탑계탑 : 1기 (No.19) ㅇOPGW 이설 : 1식(전자제어파트) ㅇ기타 부대공사","2016-10-24 08:00","2016-10-28 18:00","2016-10-24T08:00:00","2016-10-28T18:00:00","연속",null,null,null,"-"]
[234,"대전충남","아산","둔포한샘#1 T/L","[송전] 154kV 한샘-둔포T/L 19호 안전이격확보공사","ㅇ철탑계탑 : 1기 (No.19) ㅇOPGW 이설 : 1식(전자제어파트) ㅇ기타 부대공사","2016-10-24 08:00","2016-10-28 18:00","2016-10-24T08:00:00","2016-10-28T18:00:00","연속",null,null,null,"-"]
[235,"대전충남","직할","용운대화#2 T/L","154kV 용운-대화T/L 안전거리 확보공사","- 철탑설치(No.19,20,21) - 철탑철거(No.19,20,21,22) - 철탑보강(No.18,23) - 전선교체 No.18~23(1.58km) - 기타부대공사","2016-10-10 07:00","2016-10-19 18:00","2016-10-10T07:00:00","2016-10-19T18:00:00","연속",null,null,null,"-"]
[236,"대전충남","직할","용운대화#1 T/L","154kV 용운-대화T/L 안전거리 확보공사","- 철탑설치(No.19,20,21) - 철탑철거(No.19,20,21,22) - 철탑보강(No.18,23) - 전선교체 No.18~23(1.58km) - 기타부대공사","2016-10-10 07:00","2016-10-14 18:00","2016-10-10T07:00:00","2016-10-14T18:00:00","연속",null,null,null,"-"]
[237,"대전충남","직할","신탄진S/S 154kV #1 BUS TIE CB","신탄진S/S 154kV B/T(6100) 차단기 보통점검","O 154kV B/T 차단기(6100) 보통점검","2016-10-19 09:00","2016-10-19 18:00","2016-10-19T09:00:00","2016-10-19T18:00:00","당일",null,null,null,"-"]
[238,"대전충남","청양","관창보령복합 T/L","154kV 보관T/L 안전이격확보공사","작업구간 : No.15~19 작업내용 : 철탑 3기(15,16,17)설치, 철거/ 전력선 신설","2016-10-13 08:00","2016-11-18 18:00","2016-10-13T08:00:00","2016-11-18T18:00:00","연속",null,null,null,"-"]
[239,"대전충남","청양","관창보령화력 T/L","154kV 보관T/L 안전이격확보공사","작업구간 :관창-보령화력 No.15~19 작업내용 : 가수전선로 구성(가철주 3기)","2016-10-08 08:00","2016-10-12 18:00","2016-10-08T08:00:00","2016-10-12T18:00:00","연속",null,null,null,"-"]
[240,"전북","군산","군공군산CC#2 T/L","154kV 군공-군산복합 지장 지중선로 이설공사","군장대교 건선관련 지장물 이설","2016-10-26 08:00","2016-11-09 18:00","2016-10-26 08:00","2016-11-09 18:00","연속",null,null,"345k 새만금T/L 준공 조건부 시행","-"]
[241,"전북","군산","군공군산CC#1 T/L","154kV 군공-군산복합 지장 지중선로 이설공사","군장대교 건설관련 지장 송전선로 이설","2016-10-04 08:00","2016-10-25 18:00","2016-10-04 08:00","2016-10-25 18:00","연속",null,null,"345k 새만금T/L 준공 조건부 시행","-"]
[242,"전북","군산","군산이리#2 T/L","154㎸ 군산-이리T/L 안전이격확보공사","- 15호 가철탑철거 및 전력선공중이동 - 전력선교체(12~13호간)","2016-10-02 07:00","2016-10-09 18:00","2016-10-02 07:00","2016-10-09 18:00","연속",null,null,null,"-"]
[243,"전북","군산","군산영등#2 T/L","154㎸ 군산-이리T/L 안전이격확보공사","- 15호 가철탑철거 및 전력선공중이동, 전력선교체(12~13호간)관련 상단(군산-영등T/L)안전이격거리 확보 휴전","2016-10-02 07:00","2016-10-06 18:00","2016-10-02 07:00","2016-10-06 18:00","연속",null,null,null,"-"]
[244,"전북","군산","동군산장항#2 T/L","동군산장항#2 T/L","피뢰기설치 : 13기","2016-10-01 07:00","2016-10-01 18:00","2016-10-01 07:00","2016-10-01 18:00","당일",null,null,null,"-"]
[245,"전북","군산","군산동군산#1 T/L","군산동군산#1 T/L","○ 경보회로 보완 - LCP PNL의 Reset 회로에 역저지용 Diode 취부 후 경보시험","2016-10-07 09:00","2016-10-07 13:00","2016-10-07 09:00","2016-10-07 13:00","당일",null,null,null,"-"]
[246,"전북","군산","군산동군산#2 T/L","군산동군산#2 T/L","○ 경보회로 보완 - LCP PNL의 Reset 회로에 역저지용 Diode 취부 후 경보시험","2016-10-07 13:00","2016-10-07 18:00","2016-10-07 13:00","2016-10-07 18:00","당일",null,null,null,"-"]
[247,"전북","군산","동군산군산CC#1 T/L","동군산군산CC#1 T/L","○ 경보회로 보완 - LCP PNL의 Reset 회로에 역저지용 Diode 취부 후 경보시험","2016-10-13 09:00","2016-10-13 18:00","2016-10-13 09:00","2016-10-13 18:00","당일",null,null,null,"-"]
[248,"전북","군산","동군산군산CC#2 T/L","동군산군산CC#2 T/L","○ 경보회로 보완 - LCP PNL의 Reset 회로에 역저지용 Diode 취부 후 경보시험","2016-10-14 09:00","2016-10-14 18:00","2016-10-14 09:00","2016-10-14 18:00","당일",null,null,null,"-"]
[249,"전북","군산","팔봉영등#2 T/L","팔봉영등#2 T/L","#1T/L 피뢰기설치시 안전이격확보휴전","2016-10-02 07:00","2016-10-02 18:00","2016-10-02 07:00","2016-10-02 18:00","당일",null,null,null,"-"]
[250,"전북","군산","팔봉영등#1 T/L","팔봉영등#1 T/L","피뢰기설치 : 14기","2016-10-02 07:00","2016-10-02 18:00","2016-10-02 07:00","2016-10-02 18:00","당일",null,null,null,"-"]
[251,"전북","군산","이리S/S 154kV #2 BUS","이리S/S 154kV #2 BUS","1. 이리S/S 154kV 단로기 과열발생 특별점검","2016-10-17 14:00","2016-10-17 18:00","2016-10-17 14:00","2016-10-17 18:00","당일",null,null,null,"-"]
[252,"전북","군산","이리백산#2 T/L","154kV 이리-백산T/L 선종교체공사","선종 교체 : No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) 철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-10-04 08:00","2016-10-14 18:00","2016-10-04 08:00","2016-10-14 18:00","연속",null,null,null,"-"]
[253,"전북","군산","이리백산#1 T/L","154kV 이리-백산T/L 선종교체공사","선종 교체 : No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) 철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-10-15 08:00","2016-10-18 18:00","2016-10-15 08:00","2016-10-18 18:00","연속",null,null,null,"-"]
[254,"전북","군산","이리백산#2 T/L","154kV 이리-백산T/L 선종교체공사","선종 교체 : No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) 철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-10-19 08:00","2016-10-26 18:00","2016-10-19 08:00","2016-10-26 18:00","연속",null,null,null,"-"]
[255,"전북","군산","이리백산#1 T/L","154kV 이리-백산T/L 선종교체공사","선종 교체 : No.8~No.35호간 HSTACIR/AW 240㎟ (19.22 C-km) 철탑 신설·철거 : 설치 6기, 철거 5기 (No.11,19,25,28.1,32,33)","2016-10-27 08:00","2016-11-05 18:00","2016-10-27 08:00","2016-11-05 18:00","연속",null,null,null,"-"]
[256,"전북","군산","군산이리#1 T/L","154kV 군산-이리#1T/L","지중화 관련 26호 C/H 신설","2016-10-10 08:00","2016-10-13 18:00","2016-10-10 08:00","2016-10-13 18:00","연속",null,null,null,"-"]
[257,"전북","군산","군산이리#2 T/L","154kV 군산-이리#2T/L","지중화 관련 26호 C/H 신설","2016-10-14 08:00","2016-10-15 18:00","2016-10-14 08:00","2016-10-15 18:00","연속",null,null,null,"-"]
[258,"전북","군산","이리S/S 154kV #1 BUS","이리S/S 154kV #1 BUS","1. 이리S/S 154kV 단로기 과열발생 특별점검","2016-10-17 09:00","2016-10-17 14:00","2016-10-17 09:00","2016-10-17 14:00","당일",null,null,null,"-"]
[259,"전북","군산","이리S/S 154kV #1 BUS TIE CB","이리S/S 154kV #1 BUS TIE CB","1. 이리S/S 154kV 단로기 과열발생 특별점검","2016-10-17 09:00","2016-10-17 18:00","2016-10-17 09:00","2016-10-17 18:00","당일",null,null,null,"-"]
[260,"전북","군산","군산이리#1 T/L","군산이리#1 T/L","1. 이리S/S 154kV 단로기 과열발생 특별점검","2016-10-17 09:00","2016-10-17 14:00","2016-10-17 09:00","2016-10-17 14:00","당일",null,null,null,"-"]
[261,"전북","군산","군산이리#2 T/L","군산이리#2 T/L","1. 이리S/S 154kV 단로기 과열발생 특별점검","2016-10-17 14:00","2016-10-17 18:00","2016-10-17 14:00","2016-10-17 18:00","당일",null,null,null,"-"]
[262,"전북","군산","이리S/S 154kV #1 BUS TIE CB","이리S/S 154kV #1 BUS TIE CB","1. 이리S/S 154kV 단로기 과열발생 특별점검","2016-10-18 09:00","2016-10-18 18:00","2016-10-18 09:00","2016-10-18 18:00","당일",null,null,null,"-"]
[263,"전북","군산","이리S/S 154kV #1 BUS","이리S/S 154kV #1 BUS","1. 이리S/S 154kV 단로기 과열발생 특별점검","2016-10-18 09:00","2016-10-18 14:00","2016-10-18 09:00","2016-10-18 14:00","당일",null,null,null,"-"]
[264,"전북","군산","이리S/S 154kV #2 BUS","이리S/S 154kV #2 BUS","1. 이리S/S 154kV 단로기 과열발생 특별점검","2016-10-18 14:00","2016-10-18 18:00","2016-10-18 14:00","2016-10-18 18:00","당일",null,null,null,"-"]
[265,"전북","군산","팔봉두마#1 T/L","154kV 팔봉-두마T/L 안전이격확보공사","- 신설 철탑조립(27~30호) 및 전력선공중이동 - 28호 인클로징 철탑교체 시행","2016-10-17 07:00","2016-10-21 18:00","2016-10-17 07:00","2016-10-21 18:00","연속",null,null,null,"-"]
[266,"전북","군산","팔봉두마#2 T/L","154kV 팔봉-두마T/L 안전이격확보공사","- 신설 철탑조립(27~30호) 및 전력선공중이동 - 28호 인클로징 철탑교체 시행","2016-10-17 07:00","2016-10-21 18:00","2016-10-17 07:00","2016-10-21 18:00","연속",null,null,null,"-"]
[267,"전북","김제","고창영광 T/L","154kV 고창-영광T/L 전선교체 등 2개 공사","전선교체 : 61~108호 10.627C-km 피뢰기 설치 : 46~155호 110기 330set","2016-10-31 07:00","2016-11-19 18:00","2016-10-31 07:00","2016-11-19 18:00","연속",null,null,null,"-"]
[268,"전북","김제","정주고창#1 T/L","정주-고창#1T/L","정주S/S #3M.TR 1차 CB정밀점검 - 시험가압","2016-10-21 13:00","2016-10-22 18:00","2016-10-21 13:00","2016-10-22 18:00","연속",null,null,null,"-"]
[269,"전북","김제","고창영광 T/L","154kV 고창-영광T/L 전선교체 등 2개 공사","전선교체 : 61~108호 10.627C-km 피뢰기 설치 : 46~155호 110기 330set","2016-10-10 07:00","2016-10-21 18:00","2016-10-10 07:00","2016-10-21 18:00","연속",null,null,null,"-"]
[270,"전북","김제","백산김제#1 T/L","백산-김제#1T/L","김제S/S 154KV BUS TIE GIS정밀점검 - 시험가압","2016-10-28 13:00","2016-10-29 18:00","2016-10-28 13:00","2016-10-29 18:00","연속",null,null,null,"-"]
[271,"전북","김제","신김제S/S 60-61-0 SEC CB","신김제S/S 60-61-0 SEC CB","모선보호반 교체 및 차단기 보통점검","2016-10-17 10:00","2016-10-21 18:00","2016-10-17 10:00","2016-10-21 18:00","연속",null,null,null,"-"]
[272,"전북","김제","신김제전주#1 T/L","신김제-전주#1T/L","신김제S/S 신김제-전주#1T/L GIS정밀점검","2016-10-24 09:00","2016-10-26 18:00","2016-10-24 09:00","2016-10-26 18:00","연속",null,null,null,"-"]
[273,"전북","김제","신김제S/S 65-66-0 SEC CB","신김제S/S 65-66-0 SEC CB","모선보호반 교체 및 차단기 보통점검","2016-10-17 10:00","2016-10-21 18:00","2016-10-17 10:00","2016-10-21 18:00","연속",null,null,null,"-"]
[274,"전북","김제","신김제정공#2 T/L","154kV 신김제-동전주T/L 피뢰기 설치공사 안전이격 확보","154kV 신김제-동전주T/L 피뢰기 설치공사 관련 4회선 병가구간 안전이격 확보를 위해 휴전 필요","2016-10-10 07:30","2016-10-11 18:00","2016-10-10 07:30","2016-10-11 18:00","당일",null,null,null,"-"]
[275,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 #2T/L 피뢰기 설치공사","작업구간 : 1~83호간","2016-10-10 07:30","2016-10-16 18:00","2016-10-10 07:30","2016-10-16 18:00","매일",null,null,null,"-"]
[276,"전북","직할","북전주봉동#2 T/L","154kV 북전주-봉동T/L 정밀점검","내용 : 정밀점검 구간 : 1~9호","2016-10-31 09:00","2016-10-31 18:00","2016-10-31 09:00","2016-10-31 18:00","당일",null,null,null,"-"]
[277,"전북","직할","북전주봉동#2 T/L","154kV 북전주-봉동#2T/L 피뢰기 설치공사","작업구간 : 1~9호간","2016-10-28 07:30","2016-10-28 18:00","2016-10-28 07:30","2016-10-28 18:00","당일",null,null,null,"-"]
[278,"전북","직할","북전주용담수력 T/L","154kV 북전주-용담수력T/L 피뢰기 설치공사","작업구간 : 1, 5~51호간","2016-10-24 07:30","2016-10-27 18:00","2016-10-24 07:30","2016-10-27 18:00","매일",null,null,null,"-"]
[279,"광주전남","강진","진도C/S #1Pole C.Tr CB","'16~'17년 #2HVDC 변환설비 위탁정비공사","#2HVDC 변환설비 연차점검","2016-10-30 09:00","2016-11-10 18:00","2016-10-30 09:00","2016-11-10 18:00","연속",null,null,null,"-"]
[280,"광주전남","강진","진도진도CS#2 T/L","진도-진도CS#2 T/L(변전협력회사 총액공사)","강진전력지사 변전협력회사 총액공사 - 진도-진도C/S#2T/L 송전선로 보호반 대체","2016-10-31 09:00","2016-11-03 18:00","2016-10-31 09:00","2016-11-03 18:00","연속",null,null,null,"-"]
[281,"광주전남","광주","계림승주#1(서남권상수도T분기) T/L","2016년 송전 협력회사 총액공사","불량애자교체 작업자 충전부 안전거리확보","2016-10-05 07:00","2016-10-06 18:00","2016-10-05 07:00","2016-10-06 18:00","당일",null,null,null,"-"]
[282,"광주전남","광주","담양일곡#1 T/L","담양-일곡#1T/L 보호배전반 교체","담양-일곡#1T/L 보호배전반 교체","2016-10-17 09:00","2016-10-19 18:00","취소","취소","연속",null,null,"계통안정","-"]
[283,"광주전남","광주","담양일곡#2 T/L","담양-일곡#2T/L 보호배전반 교체","담양-일곡#2T/L 보호배전반 교체","2016-10-24 09:00","2016-10-26 18:00","취소","취소","연속",null,null,"계통안정","-"]
[284,"광주전남","광주","신광주곡성#1 T/L","154kV신광주-곡성T/L 정밀점검공사 등 2건","1.정밀점검 115기 2.안전이격확보 1기(115호) 3.피뢰기 설치 115기","2016-10-10 07:00","2016-10-16 18:00","2016-10-10 07:00","2016-10-16 18:00","연속",null,null,null,"-"]
[285,"광주전남","광주","신광주계림#1 T/L","2016년 송전 협력회사 총액공사","불량애자교체69개","2016-10-05 07:00","2016-10-05 18:00","2016-10-05 07:00","2016-10-05 18:00","당일",null,null,null,"-"]
[286,"광주전남","광주","신광주계림#2 T/L","2016년 송전 협력회사 총액공사","불량애자교체69개","2016-10-06 07:00","2016-10-06 18:00","2016-10-06 07:00","2016-10-06 18:00","당일",null,null,null,"-"]
[287,"광주전남","광주","신광주곡성#2 T/L","154kV신광주-곡성T/L 정밀점검공사 등 2건","1.정밀점검 115기 2.안전이격확보 1기(115호)","2016-10-17 07:00","2016-10-21 18:00","2016-10-17 07:00","2016-10-21 18:00","연속",null,null,null,"-"]
[288,"광주전남","목포","영광홍농 T/L","154kV 영광-홍농T/L(보호배전반 대체공사)","154kV 송전선로보호반 대체","2016-10-24 09:00","2016-10-28 18:00","취소","취소","연속",null,null,"계통안정","-"]
[289,"광주전남","순천","광양순천#1 T/L","154kV 광양-순천T/L C/H 건설공사","C/H 1기 설치, 전력선 가선 0.5km","2016-10-04 09:00","2016-10-07 18:00","2016-10-04 09:00","2016-10-07 18:00","연속",null,null,null,"-"]
[290,"광주전남","순천","광양하동#2 T/L","154kV 광양-하동#2T/L(노후전력선 및 철탑 교체)","노후전력선 교체 : 37~92호 철탑교체 : 59,61,77,81호(4기)","2016-10-09 07:00","2016-10-15 18:00","2016-10-09 07:00","2016-10-15 18:00","연속",null,null,null,"-"]
[291,"광주전남","순천","광양하동#1 T/L","154kV 광양-하동#1T/L(노후전력선 및 철탑 교체)","노후전력선 교체 : 37~92호 철탑교체 : 59,61,77,81호(4기)","2016-10-09 07:00","2016-10-15 18:00","2016-10-09 07:00","2016-10-15 18:00","연속",null,null,null,"-"]
[292,"광주전남","순천","광양하동#1 T/L","154kV 광양-하동#1T/L(노후전력선 및 철탑 교체)","노후전력선 교체 : 37~92호 철탑교체 : 59,61,77,81호(4기)","2016-10-22 07:00","2016-10-29 18:00","2016-10-22 07:00","2016-10-29 18:00","연속",null,null,null,"-"]
[293,"광주전남","순천","광양하동#2 T/L","154kV 광양-하동#2T/L(노후전력선 및 철탑 교체)","노후전력선 교체 : 37~92호 철탑교체 : 59,61,77,81호(4기)","2016-10-22 07:00","2016-10-29 18:00","2016-10-22 07:00","2016-10-29 18:00","연속",null,null,null,"-"]
[294,"광주전남","순천","서순천주암HP T/L","154kV 서순천-주암HP T/L(철탑 지상고 상향)","철탑 지상고 상향 : 22,23,24호(3기)","2016-10-24 07:00","2016-10-28 18:00","2016-10-24 07:00","2016-10-28 18:00","연속",null,null,null,"-"]
[295,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주T/L C/H 건설공사","C/H 1기 설치, 전력선 가선 0.5km","2016-10-11 09:00","2016-10-14 18:00","2016-10-11 09:00","2016-10-14 18:00","연속",null,null,null,"-"]
[296,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌#1T/L(송전선로 보호배전반 대체)","순천-율촌#1T/L 송전선로 보호배전반 대체","2016-10-08 09:00","2016-10-10 18:00","2016-10-08 09:00","2016-10-10 18:00","연속",null,null,null,"-"]
[297,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단#1T/L(송전선로 초기점검)","율촌-여수산단#1T/L 송전선로 초기점검 - 28~50호, 51기","2016-10-04 08:00","2016-10-07 18:00","2016-10-04 08:00","2016-10-07 18:00","매일",null,null,null,"-"]
[298,"광주전남","순천","율촌화치#2 T/L","154kV 율촌-화치#2T/L(송전선로 초기점검)","율촌-화치#2T/L 송전선로 초기점검 - 45~67호, 24기","2016-10-06 08:00","2016-10-07 18:00","2016-10-06 08:00","2016-10-07 18:00","매일",null,null,null,"-"]
[299,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단#2T/L(송전선로 초기점검)","율촌-여수산단#2T/L 송전선로 초기점검 - 28~50호, 51기","2016-10-10 08:00","2016-10-13 18:00","2016-10-10 08:00","2016-10-13 18:00","매일",null,null,null,"-"]
[300,"광주전남","순천","율촌화치#1 T/L","154kV 율촌-화치#1T/L(송전선로 초기점검)","율촌-화치#1T/L 송전선로 초기점검 - 45~67호, 24기","2016-10-12 08:00","2016-10-13 18:00","2016-10-12 08:00","2016-10-13 18:00","매일",null,null,null,"-"]
[301,"광주전남","직할","신화순평동(구,신화순나주#1) CB T/L","154kV 신화순-나주T/L No.43-48호 지장철탑 이설공사","송현-남평간 지방도 확포장 공사에 지장이 되는 154kV 신화순-나주T/L No.43-48호간 지장철탑 이설공사","2016-10-27 08:00","2016-11-02 18:00","2016-10-27 08:00","2016-11-02 18:00","연속",null,null,null,"-"]
[302,"광주전남","직할","신화순나주#2 T/L","154kV 신화순-나주T/L No.43-48호 지장철탑 이설공사","송현-남평간 지방도 확포장 공사에 지장이 되는 154kV 신화순-나주T/L No.43-48호간 지장철탑 이설공사","2016-10-20 08:00","2016-10-26 18:00","2016-10-20 08:00","2016-10-26 18:00","연속",null,null,null,"-"]
[303,"광주전남","직할","신화순평동(구,나주평동#1) CB T/L","154kV 신화순-평동#1T/L 피뢰기 설치공사","154kV 나주-평동#1T/L 피뢰기 설치공사(16년 광주전남 직할 송전협력공사)","2016-10-17 08:00","2016-10-19 18:00","2016-10-17 08:00","2016-10-19 18:00","매일",null,null,null,"-"]
[304,"대구경북","경산","신경산노변 T/L","'16년 신경산S/S 170kV 장기사용 GIS 대체","1. 신경산-노변T/L GIS 대체 2. 진량S/S 장기간 RADIAL 운전대비 선로보강 사전작업","2016-10-30 09:00","2016-11-28 18:00","2016-10-30 09:00","2016-11-28 18:00","연속",null,null,null,"-"]
[305,"대구경북","경산","신경산진량 T/L","'16년 신경산S/S 170kV 장기사용 GIS 대체","1. 신경산-진량T/L GIS 대체 2. 진량S/S 장기간 RADIAL 운전대비 선로보강 사전작업","2016-10-30 09:00","2016-11-28 18:00","2016-10-30 09:00","2016-11-28 18:00","연속",null,null,null,"-"]
[306,"대구경북","경산","신경산경산#2 T/L","'16년 신경산S/S 170kV 장기사용 GIS 대체공사","신경산-경산#2T/L GIS 대체","2016-10-04 09:00","2016-10-26 18:00","2016-10-04 09:00","2016-10-26 18:00","연속",null,null,null,"-"]
[307,"대구경북","경산","아화영천#2 T/L","2016년 경산전력 가공송전 협력회사 총액공사","청통영천#1 T/L 전력선교체에 따른 안전이격거리 확보","2016-10-20 08:00","2016-10-27 18:00","2016-10-20 08:00","2016-10-27 18:00","연속",null,null,null,"-"]
[308,"대구경북","경산","아화영천#1 T/L","2016년 경산전력 가공송전 협력회사 총액공사","청통영천#1 T/L 전력선교체에 따른 안전이격거리 확보","2016-10-20 08:00","2016-10-23 18:00","2016-10-20 08:00","2016-10-23 18:00","연속",null,null,null,"-"]
[309,"대구경북","구미","상주보은 T/L","154kV상주T/L 노후취약지지물교체공사","ㅇ 공사목적 : 수목밀집 지역에 설치되어 있는 1937년도 건설 노후취약지지물 및 전력선 교체를 통한 설비고장 요인을 사전에 제거하고, 경북 상주, 충북보은 및 영동지역의 전력공급 신뢰도를 향상시키고자 함. ㅇ 공사구간 : 154kV 상주T/L 118-127호간 ㅇ 공사수량 1. 지지물 : 철거 5기, 설치 5기 2. 전력선 : ACSR240SQ x S x 2C 1.793km 3. 가공지선 : ACSR97SQ x 1조 (OPGW 100SQ 전자제어팀 별도 시행) 4. 기타 부대공사 1식 끝.","2016-10-10 08:00","2016-10-24 18:00","2016-10-10 08:00","2016-10-24 18:00","연속",null,null,"조건부 승인","-"]
[310,"대구경북","구미","상주영동 T/L","154kV상주T/L 노후취약지지물교체공사","ㅇ 공사목적 : 수목밀집 지역에 설치되어 있는 1937년도 건설 노후취약지지물 및 전력선 교체를 통한 설비고장 요인을 사전에 제거하고, 경북 상주, 충북보은 및 영동지역의 전력공급 신뢰도를 향상시키고자 함. ㅇ 공사구간 : 154kV 상주T/L 118-127호간 ㅇ 공사수량 1. 지지물 : 철거 5기, 설치 5기 2. 전력선 : ACSR","2016-10-10 08:00","2016-10-18 18:00","2016-10-10 08:00","2016-10-18 18:00","연속",null,null,"조건부 승인","-"]
[311,"대구경북","구미","상주영동 T/L","154kV상주T/L 노후취약지지물교체공사","ㅇ 공사목적 : 수목밀집 지역에 설치되어 있는 1937년도 건설 노후취약지지물 및 전력선 교체를 통한 설비고장 요인을 사전에 제거하고, 경북 상주, 충북보은 및 영동지역의 전력공급 신뢰도를 향상시키고자 함. ㅇ 공사구간 : 154kV 상주T/L 118-127호간 ㅇ 공사수량 1. 지지물 : 철거 5기, 설치 5기 2. 전력선 : ACSR","2016-10-25 08:00","2016-10-30 18:00","2016-10-25 08:00","2016-10-30 18:00","연속",null,null,"조건부 승인","-"]
[312,"대구경북","구미","선산안계#1 T/L","154kV 선산-안계 등 2개T/L 지장선로 이설공사","ㅇ 개요 : 한국수자원공사측 시행 산업단지 조성사업관련 송전선로 이설 ㅇ구간 : 154㎸ 선산-안계T/L S/T∼No.10, 선산-고아T/L No.1∼4 ㅇ지지물 : 설치 8기(4회선용 2기, 2회선용 4기, C/H 2기), 철거 10기","2016-10-20 07:00","2016-11-07 18:00","2016-10-20 07:00","2016-11-07 18:00","연속",null,null,null,"-"]
[313,"대구경북","구미","선산고아#2 T/L","154kV 선산-안계 등 2개T/L 지장선로 이설공사","ㅇ 개요 : 한국수자원공사측 시행 산업단지 조성사업관련 송전선로 이설 ㅇ구간 : 154㎸ 선산-안계T/L S/T∼No.10, 선산-고아T/L No.1∼4 ㅇ지지물 : 설치 8기(4회선용 2기, 2회선용 4기, C/H 2기), 철거 10기","2016-10-24 07:00","2016-11-12 18:00","2016-10-24 07:00","2016-11-12 18:00","연속",null,null,null,"-"]
[314,"대구경북","구미","선산고아#1 T/L","154kV 선산-안계 등 2개T/L 지장선로 이설공사","ㅇ 개요 : 한국수자원공사측 시행 산업단지 조성사업관련 송전선로 이설 ㅇ구간 : 154㎸ 선산-안계T/L S/T∼No.10, 선산-고아T/L No.1∼4 ㅇ지지물 : 설치 8기(4회선용 2기, 2회선용 4기, C/H 2기), 철거 10기","2016-10-30 07:00","2016-11-05 18:00","2016-10-30 07:00","2016-11-05 18:00","연속",null,null,null,"-"]
[315,"대구경북","구미","선산안계#2 T/L","154kV 선산-안계 등 2개T/L 지장선로 이설공사","ㅇ 개요 : 한국수자원공사측 시행 산업단지 조성사업관련 송전선로 이설 ㅇ구간 : 154㎸ 선산-안계T/L S/T∼No.10, 선산-고아T/L No.1∼4 ㅇ지지물 : 설치 8기(4회선용 2기, 2회선용 4기, C/H 2기), 철거 10기","2016-10-30 13:00","2016-10-30 17:00","2016-10-30 13:00","2016-10-30 17:00","연속",null,null,null,"-"]
[316,"대구경북","구미","칠곡인동#2 T/L","2016년 가공송전설비 순시점검 위탁공사","345kV 서대구-선산T/L 초기점검 o No.28~60 2회선 o No.61~64 4회선(칠곡-인동 병가, 하단) o No.65~71 4회선(산동-군위 병가) o No.74~106 4회선(선산분기 병가)","2016-10-08 09:00","2016-10-09 18:00","2016-10-08 09:00","2016-10-09 18:00","당일",null,null,null,"-"]
[317,"대구경북","구미","칠곡인동#1 T/L","2016년 가공송전설비 순시점검 위탁공사","345kV 서대구-선산T/L 초기점검 o No.28~60 2회선 o No.61~64 4회선(칠곡-인동 병가, 하단) o No.65~71 4회선(산동-군위 병가) o No.74~106 4회선(선산분기 병가)","2016-10-09 09:00","2016-10-09 18:00","2016-10-09 09:00","2016-10-09 18:00","당일",null,null,null,"-"]
[318,"대구경북","달성","다산강창#2 T/L","안전확보 휴전","강창-성서#2(하단) No.1-4 송전선로 정밀점검시 다산-강창#2(상단) 안전확보 휴전","2016-10-24 08:30","2016-10-24 18:00","2016-10-16 09:00","2016-10-16 18:00","당일",null,null,null,"-"]
[319,"대구경북","달성","강창성서#2 T/L","송전선로 정밀점검","강창-성서 No.1-14 송전선로 정밀점검(14기)","2016-10-24 08:30","2016-10-25 18:00","취소","취소","당일",null,null,null,"-"]
[320,"대구경북","달성","강창성서#1 T/L","피뢰기설치 및 송전선로 정밀점검","강창성서 #1 T/L No.2~12,14, 12기 피뢰기 설치 강창-성서 No.1-14 송전선로 정밀점검(14기)","2016-10-17 08:30","2016-10-19 18:00","취소","취소","당일",null,null,null,"-"]
[321,"대구경북","달성","다산강창#1 T/L","안전확보 휴전","강창-성서#1(하단) No.1-4 송전선로 정밀점검시 다산-강창#2(상단) 안전확보 휴전","2016-10-17 08:30","2016-10-17 18:00","2016-10-15 09:00","2016-10-15 18:00","당일",null,null,null,"-"]
[322,"대구경북","달성","고령논공#2 T/L","고령-논공T/L 송전선로 정밀점검","고령-논공 No.1-22 송전선로 정밀점검(22기)","2016-10-22 08:30","2016-10-22 18:00","2016-10-22 08:30","2016-10-22 18:00","당일",null,null,null,"-"]
[323,"대구경북","달성","고령논공#1 T/L","고령-논공T/L 송전선로 정밀점검","고령-논공 No.1-22 송전선로 정밀점검(22기)","2016-10-15 08:30","2016-10-15 18:00","2016-10-15 08:30","2016-10-15 18:00","당일",null,null,null,"-"]
[324,"대구경북","달성","논공달성#2 T/L","2016년 달성변전협력 총액공사","GIS 보통점검","2016-10-07 09:30","2016-10-07 18:00","2016-10-07 09:30","2016-10-07 18:00","당일",null,null,null,"-"]
[325,"대구경북","달성","논공달성#1 T/L","2016년 달성변전협력 총액공사","GIS 보통점검","2016-10-06 09:30","2016-10-06 18:00","2016-10-06 09:30","2016-10-06 18:00","당일",null,null,null,"-"]
[326,"대구경북","달성","성서달성#2 T/L","피뢰기설치 및 안전확보 휴전","성서달성 #2T/L No.1~20(결번 13) 19기 피뢰기 설치 강창-성서#1(상단) No.13 송전선로 정밀점검시 성서-달성#2(하단) 안전확보 휴전","2016-10-18 08:30","2016-10-20 18:00","취소","취소","당일",null,null,"계통안정","-"]
[327,"대구경북","달성","성서달성#1 T/L","안전확보 휴전","강창-성서#2(상단) No.13 송전선로 정밀점검시 성서-달성#1(하단) 안전확보 휴전","2016-10-25 08:30","2016-10-25 13:00","취소","취소","당일",null,null,"계통안정","-"]
[328,"대구경북","안동","동안동임하HP T/L","동안동S/S 모선보호반 교체공사","동안동S/S 모선보호반 교체공사","2016-10-07 10:30","2016-10-07 11:00","2016-10-07 10:30","2016-10-07 11:00","당일",null,null,null,"-"]
[329,"대구경북","안동","안계의성#1 T/L","의성S/S 옥외철구 설비 GIS화 공사","- 기초 터파기 중장비 안전이격 확보","2016-10-24 08:00","2016-10-26 18:00","2016-10-24 08:00","2016-10-26 18:00","매일",null,null,null,"-"]
[330,"부산울산","동부산","구서노포#2 T/L","구서S/S 170kV GIS 정밀점검공사","구서 170kV 617 GIS 정밀점검(구서-노포#2T/L)","2016-10-07 09:00","2016-10-09 18:00","2016-10-07 09:00","2016-10-09 18:00","연속",null,null,null,"-"]
[331,"부산울산","동부산","구서노포#1 T/L","구서S/S 170kV GIS 정밀점검공사","구서 170kV 627 GIS 정밀점검(구서-노포#1T/L)","2016-10-15 09:00","2016-10-17 18:00","2016-10-15 09:00","2016-10-17 18:00","연속",null,null,null,"-"]
[332,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창T/L 지장철탑이설공사","구간:8-12호, 17.1-20호 철탑교체:9,10,11,18호","2016-10-28 09:00","2016-11-27 18:00","2016-10-28 09:00","2016-11-27 18:00","연속",null,null,null,"-"]
[333,"부산울산","동부산","웅촌서창#2 T/L","154kV 웅촌-서창T/L 지장철탑이설공사","구간:8-12호, 17.1-20호 철탑교체:9,10,11,18호","2016-10-24 09:00","2016-10-27 18:00","2016-10-24 09:00","2016-10-27 18:00","연속",null,null,null,"-"]
[334,"부산울산","북부산","서창산막#1 T/L","154kV 삼랑진 양수 등 3개T/L 피뢰기 설치공사","154kV 서창-산막#2T/L 피뢰기 설치에 따른 작업자 안전거리확보 : 4회선(73~80), 6회선(81~86)","2016-10-01 08:00","2016-10-02 18:00","2016-10-01 08:00","2016-10-02 18:00","매일",null,null,null,"-"]
[335,"부산울산","북부산","언양산막#2 T/L","154kV 삼랑진 양수 등 3개T/L 피뢰기 설치공사","154kV 서창-산막#2T/L 피뢰기 설치에 따른 작업자 안전거리확보 : 6회선(81~86)","2016-10-02 08:00","2016-10-02 18:00","2016-10-02 08:00","2016-10-02 18:00","당일",null,null,null,"-"]
[336,"부산울산","북부산","한림정삼계#2 T/L","2016년 북부산 170kV GIS 정밀점검","삼계S/S 한림정-삼계#2T/L 627 GIS 정밀점검 (자기선로로 시험가압: 10/15 11~12, 10/16 17~18)","2016-10-14 09:00","2016-10-16 18:00","2016-10-14 09:00","2016-10-16 18:00","연속",null,null,null,"-"]
[337,"부산울산","북부산","한림정삼계#1 T/L","2016년 북부산 170kV GIS 정밀점검","삼계S/S 한림정-삼계#1T/L 617 GIS 정밀점검 (자기선로로 시험가압: 10/8 11~12, 10/9 17~18)","2016-10-21 09:00","2016-10-23 18:00","2016-10-21 09:00","2016-10-23 18:00","연속",null,null,null,"-"]
[338,"부산울산","북부산","주촌삼계#1 T/L","2016년 북부산 170kV GIS 정밀점검","삼계S/S 주촌-삼계#1T/L 657 GIS 정밀점검 (자기선로로 시험가압: 10/22 11~12, 10/23 17~18)","2016-10-07 09:00","2016-10-09 18:00","2016-10-07 09:00","2016-10-09 18:00","연속",null,null,null,"-"]
[339,"부산울산","북부산","주촌삼계#2 T/L","2016년 북부산 170kV GIS 정밀점검","삼계S/S 주촌-삼계#2T/L 687 GIS 정밀점검 (자기선로로 시험가압: 10/29 11~12, 10/30 17~18)","2016-10-28 09:00","2016-10-30 18:00","2016-10-28 09:00","2016-10-30 18:00","연속",null,null,null,"-"]
[340,"부산울산","북부산","양산삼랑진PP T/L","154kV 삼랑진양수T/L 접속설비 전선접속개소 전선교체공사","154kV 양산-삼랑진T/L 접속설비 전선접속개소 전선교체공사(No.67~87,91~105)","2016-10-27 08:00","2016-11-25 18:00","2016-10-27 08:00","2016-11-25 18:00","연속",null,null,null,"-"]
[341,"부산울산","북부산","학장S/S 154kV #2 BUS","학장S/S 170kV 장기사용 GIS 대체(4차)","학장S/S 엄궁-학장#2T/L, #1M.Tr 1차 GIS 대체(#2DS측 설치)","2016-10-03 08:00","2016-10-13 16:00","2016-10-03 08:00","2016-10-13 16:00","연속",null,null,null,"-"]
[342,"부산울산","북부산","엄궁학장#1 T/L","학장S/S 170kV 장기사용 GIS 대체(4차)","학장S/S 엄궁-학장#2T/L, #1M.Tr 1차 GIS 대체(#2DS 및 차단부 시험가압)","2016-10-11 16:00","2016-10-13 18:00","2016-10-11 16:00","2016-10-13 18:00","연속",null,null,null,"-"]
[343,"부산울산","북부산","엄궁학장#2 T/L","학장S/S 170kV 장기사용 GIS 대체(4차)","학장S/S 엄궁-학장#1T/L 대체(#2DS 및 차단부 시험가압)","2016-10-31 16:00","2016-11-02 18:00","2016-10-31 16:00","2016-11-02 18:00","연속",null,null,null,"-"]
[344,"부산울산","북부산","엄궁학장#2 T/L","학장S/S 170kV 장기사용 GIS 대체(5차)","학장S/S 엄궁-학장#1T/L 대체(#1BUS측 시험가압)","2016-10-22 18:00","2016-10-24 18:00","2016-10-22 18:00","2016-10-24 18:00","연속",null,null,null,"-"]
[345,"부산울산","북부산","엄궁학장#1 T/L","학장S/S 170kV 장기사용 GIS 대체(5차)","학장S/S 엄궁-학장#1T/L 대체","2016-10-17 08:00","2016-11-02 18:00","2016-10-17 08:00","2016-11-02 18:00","연속",null,null,null,"-"]
[346,"부산울산","북부산","엄궁학장#2 T/L","학장S/S 170kV 장기사용 GIS 대체(4차)","학장S/S 엄궁-학장#1T/L 대체(#2BUS측 시험가압)","2016-10-18 11:00","2016-10-18 13:00","2016-10-18 11:00","2016-10-18 13:00","당일",null,null,null,"-"]
[347,"부산울산","북부산","북부산호포 T/L","154kV 호포S/S #3M.Tr 증설공사","호포S/S 23kV GIS 설치 관련 시험가압(#41,42,47 BUS) -23kV GIS 5CCT 설치(4k2 DS 제외) 후 무부하시험가압","2016-10-14 18:00","2016-10-16 18:00","2016-10-14 18:00","2016-10-16 18:00","연속",null,null,null,"-"]
[348,"부산울산","서부산","서부산S/S 154kV #1 BUS TIE CB","6100 GIS 정밀점검","6100 GIS 정밀점검 (6100 CB 정밀점검)","2016-10-31 10:00","2016-11-02 18:00","2016-10-31 10:00","2016-11-02 18:00","연속",null,null,null,"-"]
[349,"부산울산","서부산","서부산엄궁#2 T/L","65-66-0 GIS 정밀점검","65-66-0 GIS 정밀점검 (65-66-0 2DS 정밀점검관련 시험가압)","2016-10-29 18:00","2016-10-29 20:00","2016-10-29 18:00","2016-10-29 20:00","당일",null,null,null,"-"]
[350,"부산울산","서부산","서부산S/S 154kV #66 BUS","65-66-0 GIS 정밀점검","65-66-0 GIS 정밀점검 (65-66-0 CB + 65-66-2DS 정밀점검)","2016-10-28 08:00","2016-10-29 20:00","2016-10-28 08:00","2016-10-29 20:00","연속",null,null,null,"-"]
[351,"부산울산","서부산","서부산S/S 154kV #65 BUS","65-66-0 GIS 정밀점검","65-66-0 GIS 정밀점검 (65-66-1 DS 정밀점검)","2016-10-27 08:00","2016-10-27 20:00","2016-10-27 08:00","2016-10-27 20:00","당일",null,null,null,"-"]
[352,"부산울산","서부산","서부산S/S 65-66-0 SEC CB","65-66-0 GIS 정밀점검","65-66-0 GIS 정밀점검 (65-66-0 CB 정밀점검)","2016-10-27 08:00","2016-10-29 20:00","2016-10-27 08:00","2016-10-29 20:00","연속",null,null,null,"-"]
[353,"부산울산","서부산","서부산엄궁#1 T/L","60-61-0 GIS 정밀점검","60-61-0 GIS 정밀점검 (60-61-0 2DS 정밀점검관련 시험가압)","2016-10-26 18:00","2016-10-26 20:00","2016-10-26 18:00","2016-10-26 20:00","당일",null,null,null,"○"]
[354,"부산울산","서부산","서부산S/S 154kV #61 BUS","60-61-0 GIS 정밀점검","60-61-0 GIS 정밀점검 (60-61-0 CB + 60-61-2 DS 정밀점검)","2016-10-25 08:00","2016-10-26 20:00","2016-10-25 08:00","2016-10-26 20:00","연속",null,null,null,"-"]
[355,"부산울산","서부산","서부산S/S 60-61-0 SEC CB","60-61-0 GIS 정밀점검","60-61-0 GIS 정밀점검 (60-61-0 CB 정밀점검)","2016-10-24 08:00","2016-10-26 20:00","2016-10-24 08:00","2016-10-26 20:00","연속",null,null,null,"-"]
[356,"부산울산","서부산","서부산S/S 154kV #60 BUS","60-61-0 GIS 정밀점검","60-61-0 GIS 정밀점검 (60-61-1 DS 정밀점검)","2016-10-24 08:00","2016-10-24 20:00","2016-10-24 08:00","2016-10-24 20:00","당일",null,null,null,"-"]
[357,"부산울산","서부산","서부산S/S 154kV #65 BUS","#1S/T GIS 정밀점검","#1S/T GIS 정밀점검 (#1S/T CB(687) + 2DS(682) 정밀점검)","2016-10-20 08:00","2016-10-21 20:00","2016-10-20 08:00","2016-10-21 20:00","연속",null,null,null,"-"]
[358,"부산울산","서부산","서부산S/S 154kV #60 BUS","#1S/T GIS 정밀점검","#1S/T GIS 정밀점검 (#1S/T 1DS(681) 정밀점검)","2016-10-19 08:00","2016-10-19 20:00","2016-10-19 08:00","2016-10-19 20:00","당일",null,null,null,"-"]
[359,"부산울산","서부산","서부산S/S #1 S/T CB","#1S/T GIS 정밀점검","#1S/T GIS 정밀점검 (#1S/T CB(687) 정밀점검)","2016-10-19 08:00","2016-10-21 20:00","2016-10-19 08:00","2016-10-21 20:00","연속",null,null,null,"-"]
[360,"부산울산","서부산","서부산S/S 154kV #60 BUS","6100 GIS 정밀점검","6100 GIS 정밀점검 (6101 DS 정밀점검)","2016-10-31 08:00","2016-10-31 20:00","2016-10-31 08:00","2016-10-31 20:00","당일",null,null,null,"-"]
[361,"부산울산","울산","동울산효문#2 T/L","2016년 가공송전 순시점검 위탁공사","동울산효문#2T/L 송전선로 초기점검(1~22) 정밀점검(23~43)","2016-10-31 09:00","2016-11-04 18:00","2016-10-31 09:00","2016-11-04 18:00","연속",null,null,null,"-"]
[362,"부산울산","울산","동울산효문#1 T/L","2016년 가공송전 순시점검 위탁공사","동울산효문#1 T/L 송전선로 초기점검(1~22) 정밀점검(23~43)","2016-10-24 09:00","2016-10-28 18:00","2016-10-24 09:00","2016-10-28 18:00","연속",null,null,null,"-"]
[363,"부산울산","울산","효문방어진 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S #2BUS 단로기 설치관련 안전이격 확보","2016-10-11 09:00","2016-10-11 13:00","2016-10-11 09:00","2016-10-11 13:00","당일",null,null,null,"-"]
[364,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S 방어진-영남T/P #1T/L GIS 대체시행","2016-10-05 09:00","2016-10-20 20:00","2016-10-05 09:00","2016-10-20 20:00","연속",null,null,null,"-"]
[365,"부산울산","울산","효문방어진 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S #1BUS 임시모선 설치관련 안전이격 확보","2016-10-07 09:00","2016-10-07 13:00","2016-10-07 09:00","2016-10-07 13:00","당일",null,null,null,"-"]
[366,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S #1BUS 임시모선 설치관련 안전이격 확보","2016-10-07 13:00","2016-10-07 18:00","2016-10-07 13:00","2016-10-07 18:00","당일",null,null,null,"-"]
[367,"부산울산","울산","동울산방어진 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S #1BUS 임시모선 예비가압 (48h) 선로","2016-10-09 08:00","2016-10-11 08:00","2016-10-09 08:00","2016-10-11 08:00","연속",null,null,null,"-"]
[368,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S #2BUS 단로기 설치관련 안전이격 확보","2016-10-11 13:00","2016-10-11 18:00","2016-10-11 13:00","2016-10-11 18:00","당일",null,null,null,"-"]
[369,"부산울산","울산","동울산방어진 T/L","154kV 방어진S/S 용량부족 차단기 대체공사","154kV 방어진S/S 용량부족 차단기 대체공사 - 방어진S/S #2BUS (DS) 예비가압 선로","2016-10-13 08:00","2016-10-15 18:00","2016-10-13 08:00","2016-10-15 18:00","연속",null,null,null,"-"]
[370,"부산울산","울산","동울산방어진 T/L","154kV 현대#1T/L 전선교체공사(이격거리 확보)","ㅁ 154kV 현대#1T/L 전선접속개소 전선교체공사 관련 병가구간 이격거리 확보","2016-10-23 06:00","2016-10-23 14:00","2016-10-23 06:00","2016-10-23 14:00","당일",null,null,null,"-"]
[371,"부산울산","울산","신온산온산#2 T/L","2016년 상반기 170kV 개폐장치 정밀점검","신온산S/S 631, 641 DS 시험가압","2016-10-07 17:00","2016-10-07 18:00","2016-10-07 17:00","2016-10-07 18:00","당일",null,null,null,"-"]
[372,"부산울산","울산","신온산온산#2 T/L","2016년 상반기 170kV 개폐장치 정밀점검","신온산S/S 632, 642 DS 시험가압","2016-10-06 17:00","2016-10-06 18:00","2016-10-06 17:00","2016-10-06 18:00","당일",null,null,null,"-"]
[373,"부산울산","울산","신울산S/S 67-68-0 SEC CB","2016-17년 울산전력지사 변전협력회사 총액공사","신울산 67-68-0 GIS 보통점검","2016-10-07 09:00","2016-10-07 18:00","2016-10-07 09:00","2016-10-07 18:00","당일",null,null,null,"-"]
[374,"부산울산","울산","신울산S/S 62-63-0 SEC CB","2016-17년 울산전력지사 변전협력회사 총액공사","신울산 62-63-0 GIS 보통점검","2016-10-06 09:00","2016-10-06 18:00","2016-10-06 09:00","2016-10-06 18:00","당일",null,null,null,"-"]
[375,"부산울산","울산","신울산S/S 154kV #66 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","신울산S/S SK에너지Polymer T/L #66BUS측 단로기 접촉자 교체 및 GCB 시험가압","2016-10-04 09:00","2016-10-05 18:00","2016-10-04 09:00","2016-10-05 18:00","연속",null,null,null,"-"]
[376,"부산울산","울산","방어진영남TP#2 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","영남화력 6102 DS 시험가압","2016-10-26 17:00","2016-10-26 18:00","2016-10-26 17:00","2016-10-26 18:00","당일",null,null,null,"-"]
[377,"부산울산","울산","방어진영남TP#1 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","영남화력 6101 DS 시험가압","2016-10-24 17:00","2016-10-24 18:00","2016-10-24 17:00","2016-10-24 18:00","당일",null,null,null,"-"]
[378,"부산울산","울산","온산처용#1 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","10/10~12 : 온산S/S 677 GIS 정밀점검 10/13~15 : 처용S/S 687 GIS 정밀점검","2016-10-10 08:00","2016-10-15 18:00","2016-10-10 08:00","2016-10-15 18:00","연속",null,null,null,"-"]
[379,"부산울산","울산","용연처용#1 T/L","154kV 신온산-성암T/L 계통정비공사","○ 구간 : (기설)154kV 용연분기T/L No.10~(신설)154kV 성암S/S ○ 지지물 : 철탑 4기 ○ 휴잔사유 : (신설)154kV 신온산-성암T/L No.12~13구간 가선작업을 위한 안전이격확보","2016-10-25 07:00","2016-10-28 19:00","2016-10-25 07:00","2016-10-28 19:00","연속",null,null,null,"-"]
[380,"부산울산","울산","온산처용#2 T/L","2016년 하반기 170kV 개폐장치 정밀점검 공사","처용S/S 657 GIS 정밀점검","2016-10-17 08:00","2016-10-19 18:00","2016-10-17 08:00","2016-10-19 18:00","연속",null,null,null,"-"]
[381,"부산울산","직할","서부산부산 T/L","부산S/S 서부산-부산T/L PNL 대체공사","부산S/S 서부산-부산T/L PNL 대체공사","2016-10-12 10:00","2016-10-14 18:00","2016-10-12 10:00","2016-10-14 18:00","연속",null,null,null,"-"]
[382,"부산울산","직할","부민영도 T/L","154kV 부민-영도T/L S.W 증설공사","영도S/S 154kV 부민영도T/L GIS 대체(가공-> 지중)","2016-10-31 09:00","2016-12-02 18:00","2016-10-31 09:00","2016-12-02 18:00","연속",null,null,null,"-"]
[383,"경남","직할","마천진해#1 T/L","안전이격확보휴전(진해변전소 인출송전선로 지중화 공사 관련)","마천-진해#2T/L 표준절연 간격 부족 및 애자(일반→내무) 교체","2016-10-09 10:00","2016-10-09 18:00","2016-10-09 10:00","2016-10-09 18:00","당일",null,null,null,"-"]
[384,"경남","직할","마천진해#2 T/L","진해변전소 인출송전선로 지중화 공사 관련(지장이설)","마천-진해#2T/L 표준절연 간격 부족 및 애자(일반→내무) 교체","2016-10-09 10:00","2016-10-09 18:00","2016-10-09 10:00","2016-10-09 18:00","당일",null,null,null,"-"]
[385,"경남","직할","신월동읍#2 T/L","안전이격확보(154kV 신월-삼정#2T/L 정밀점검)","154kV 신월-삼정#2T/L 정밀점검 관련 안전이격확보 휴전","2016-10-16 08:00","2016-10-16 18:00","2016-10-16 08:00","2016-10-16 18:00","당일",null,null,null,"-"]
[386,"경남","직할","신월동읍#1 T/L","안전이격확보(154kV 신월-삼정#1T/L 정밀점검)","154kV 신워-삼정#1T/L 정밀점검 관련 안전이격확보 휴전","2016-10-23 08:00","2016-10-23 18:00","2016-10-23 08:00","2016-10-23 18:00","당일",null,null,null,"-"]
[387,"경남","직할","안민진해#2 T/L","진해변전소 인출송전선로 지중화 공사 관련(지장이설)","안민-진해#2T/L 표준절연 간격 부족 및 애자(일반→내무) 교체","2016-10-30 08:00","2016-10-30 18:00","2016-10-30 08:00","2016-10-30 18:00","당일",null,null,null,"-"]
[388,"경남","직할","안민진해#1 T/L","안전이격확보휴전(진해변전소 인출송전선로 지중화 공사 관련)","안민-진해#2T/L 표준절연 간격 부족 및 애자(일반→내무) 교체","2016-10-30 08:00","2016-10-30 18:00","2016-10-30 08:00","2016-10-30 18:00","당일",null,null,null,"-"]
[389,"경남","직할","창공완암#2 T/L","창공-완암#1,2T/L 전력선 교체 및 애자련 보강","창공-완암#2T/L 전력선교체(11~12호),창공-완암#1T/L전력선교체 안전이격(14~15호), 애자련보강(15~16호)","2016-10-03 07:00","2016-10-07 18:00","2016-10-03 07:00","2016-10-07 18:00","연속",null,null,null,"-"]
[390,"경남","진주","사봉개양 T/L","154kV 사봉-개양 정밀점검","154kV 사봉-개양 정밀점검(44~개양S/T)","2016-10-16 09:00","2016-10-19 18:00","2016-10-16 09:00","2016-10-19 18:00","매일",null,null,null,"-"]
[391,"경남","진주","의령동진주#1 T/L","의령-동진주#1T/L CPD 대체공사","의령-동진주#1T/L CPD 대체공사","2016-10-01 09:30","2016-10-01 18:30","2016-10-01 09:30","2016-10-01 18:30","당일",null,null,null,"-"]
[392,"경남","진주","의령동진주#2 T/L","의령-동진주#2T/L CPD 대체공사","의령-동진주#2T/L CPD 대체공사","2016-10-08 09:30","2016-10-08 18:30","2016-10-08 09:30","2016-10-08 18:30","당일",null,null,null,"-"]
[393,"경남","진주","의령S/S #61 M.Tr CB","의령S/S #61 M.Tr 초기점검","의령S/S #61 M.Tr 초기점검 - 병행작점 : #61M.Tr 1,2차(6133,4144) 초기점검 병행작업 : #1~6EES 시스템 업그레이드(LG CNS)","2016-10-10 09:30","2016-10-10 18:30","2016-10-10 09:30","2016-10-10 18:30","당일",null,null,null,"-"]
[394,"경남","진주","진주S/S 154kV #2 BUS","진주S/S 154kV #2 BUS 보통점검","진주S/S 154kV #2 BUS 보통점검 - 황색차단기 154kV BUS TIE CB(6100) 조작예정","2016-10-17 14:30","2016-10-17 18:30","2016-10-17 14:30","2016-10-17 18:30","당일",null,null,null,"-"]
[395,"경남","진주","진주S/S 154kV #1 BUS","진주S/S 154kV #1 BUS 보통점검","진주S/S 154kV #1 BUS 보통점검 - 황색차단기 154kV BUS TIE CB(6100) 조작예정","2016-10-17 09:30","2016-10-17 14:30","2016-10-17 09:30","2016-10-17 14:30","당일",null,null,null,"-"]
[396,"경남","진주","의령함양 T/L","의령-함양T/L GIS(667) 장기미동작 점검","의령-함양T/L GIS(667) 장기미동작 점검","2016-10-15 09:30","2016-10-15 13:30","2016-10-15 09:30","2016-10-15 13:30","당일",null,null,null,"-"]
[397,"경남","진주","산청함양 T/L","산청-함양T/L GIS(657) 장기미동작 점검","산청-함양T/L GIS(657) 장기미동작 점검","2016-10-15 13:30","2016-10-15 17:30","2016-10-15 13:30","2016-10-15 17:30","당일",null,null,null,"-"]
[398,"경남","진주","쌍림합천#2 T/L","합천S/S 모자익 대체공사","합천S/S 모자익 대체공사 - 작업내용 : 쌍림합천#2T/L관련 케이블결선","2016-10-13 09:30","2016-10-14 18:30","2016-10-13 09:30","2016-10-14 18:30","연속",null,null,null,"-"]
[399,"경남","진주","쌍림합천#1 T/L","쌍림-합천#1T/L GIS 정밀점검공사","쌍림-합천#1T/L GIS 정밀점검공사","2016-10-04 09:30","2016-10-06 18:30","2016-10-04 09:30","2016-10-06 18:30","연속",null,null,null,"-"]
[400,"경남","진주","거창합천#2 T/L","쌍림-합천#1T/L GIS 정밀점검공사","쌍림-합천#1T/L GIS 정밀점검공사","2016-10-05 12:00","2016-10-05 13:00","2016-10-05 12:00","2016-10-05 13:00","당일",null,null,null,"-"]
[401,"경남","진주","거창합천#1 T/L","쌍림-합천#1T/L GIS 정밀점검공사","쌍림-합천#1T/L GIS 정밀점검공사","2016-10-06 16:00","2016-10-06 18:30","2016-10-06 16:00","2016-10-06 18:30","당일",null,null,null,"-"]
[402,"경남","통영","삼천포사천#2 T/L","삼천포S/S 154kV 삼천포-사천#2T/L CVT 대체공사","삼천포S/S 154kV 삼천포-사천#2T/L CVT 대체공사","2016-10-07 09:30","2016-10-07 18:30","2016-10-07 09:30","2016-10-07 18:30","당일",null,null,null,"-"]
[403,"경남","통영","삼천포사천#1 T/L","삼천포S/S 154kV 삼천포-사천#1T/L CVT 대체공사","삼천포S/S 154kV 삼천포-사천#1T/L CVT 대체공사","2016-10-06 09:30","2016-10-06 18:30","2016-10-06 09:30","2016-10-06 18:30","당일",null,null,null,"-"]
[404,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제#1T/L 피뢰기 설치공사","154kV 신고성-거제#1T/L 피뢰기 및 SB Damper 설치공사 - 공사구간 : No.87~117 / 피뢰기 - 진동-안정#1T/L : No.54~85","2016-10-02 07:00","2016-10-02 19:00","2016-10-02 07:00","2016-10-02 19:00","매일",null,null,null,"-"]
[405,"경남","통영","신고성거제#2 T/L","154kV 진동-안정#2T/L 안전이격","154kV 진동-안정#2T/L 피뢰기 설치공사 - 공사구간 : No.55~85","2016-10-03 07:00","2016-10-03 19:00","2016-10-03 07:00","2016-10-03 19:00","매일",null,null,null,"-"]
[406,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제#1T/L 피뢰기 설치공사","154kV 신고성-거제#1T/L 피뢰기 및 SB Damper 설치공사 - 공사구간 : No.87~117 / 피뢰기 - 진동-안정#1T/L : No.54~85","2016-10-09 07:00","2016-10-09 19:00","2016-10-09 07:00","2016-10-09 19:00","매일",null,null,null,"-"]
[407,"경남","통영","신마산진동 T/L","154kV 진동-안정#2T/L 안전이격","154kV 진동-안정#2T/L 안전이격 - 공사구간 : No.1~85","2016-10-08 07:00","2016-10-08 19:00","2016-10-08 07:00","2016-10-08 19:00","매일",null,null,null,"-"]
[408,"경남","통영","통영거제#2 T/L","통영S/S 154kV 신고성-통영T/L GIS 정밀점검 시험가압 선로","통영S/S 154kV 신고성-통영T/L GIS 정밀점검 시험가압 선로","2016-10-22 17:30","2016-10-22 18:30","2016-10-22 17:30","2016-10-22 18:30","당일",null,null,null,"-"]
[409,"경남","통영","신고성통영 T/L","통영S/S 154kV 신고성-통영T/L GIS 정밀점검","통영S/S 154kV 신고성-통영T/L GIS 정밀점검 [병행] 통영S/S 신고성-통영T/L 월부싱 단자과열개소 보수","2016-10-22 09:30","2016-10-23 18:30","2016-10-22 09:30","2016-10-23 18:30","연속",null,null,null,"-"]
[410,"경남","통영","고성통영 T/L","통영S/S 154kV 고성-통영T/L GIS 정밀점검공사","통영S/S 154kV 고성-통영T/L GIS 정밀점검공사","2016-10-15 09:30","2016-10-16 18:30","2016-10-15 09:30","2016-10-16 18:30","연속",null,null,null,"-"]
[411,"경남","통영","통영거제#2 T/L","통영S/S 154kV 고성-통영T/L GIS 정밀점검 시험가압선로","통영S/S 154kV 고성-통영T/L GIS 정밀점검 시험가압선로","2016-10-15 17:30","2016-10-15 18:30","2016-10-15 17:30","2016-10-15 18:30","당일",null,null,null,"-"]
[412,"경남","함안","신마산마산#1 T/L","마산 신마산-마산#1T/L GIS 정밀점검공사","신마산-마산#1T/L GIS 정밀점검 - 627 GIS 분해점검","2016-10-01 08:30","2016-10-03 18:30","2016-10-01 08:30","2016-10-03 18:30","연속",null,null,null,"-"]
[413,"경남","함안","마산수출#2 T/L","154kV마산-수출#2T/L 송전선로 보호반대체공사","154kV마산-수출#2T/L 송전선로 보호반대체공사 - 보호반 철거 및 설치 : 1면 - 제어케이블 포설 및 결선","2016-10-08 09:00","2016-10-09 18:00","2016-10-08 09:00","2016-10-09 18:00","연속",null,null,null,"-"]
[414,"경남","함안","마산수출#1 T/L","마산 신마산-마산#1/L GIS 정밀점검공사","마산 신마산-마산#1T/L GIS 정밀점검 - 1DS,CB 및 상부 시험가압","2016-10-03 18:30","2016-10-03 19:30","2016-10-03 18:30","2016-10-03 19:30","당일",null,null,null,"-"]
[415,"경남","함안","마산수출#1 T/L","마산 신마산-마산#1/L GIS 정밀점검공사","마산 신마산-마산#1T/L GIS 정밀점검 - 2DS 시험가압","2016-10-01 18:30","2016-10-01 19:30","2016-10-01 18:30","2016-10-01 19:30","당일",null,null,null,"-"]
[416,"경남","함안","초동밀양#1 T/L","154kV 초동-밀양#1,2T/L 전선교체공사","154kV 초동-밀양T/L 전선교체공사 (16~17, 31~33호)","2016-10-10 08:30","2016-10-14 18:30","2016-10-10 08:30","2016-10-14 18:30","연속",null,null,null,"-"]
[417,"경남","함안","초동밀양#2 T/L","154kV 초동-밀양#1,2T/L 전선교체공사","154kV 초동-밀양T/L 전선교체공사 (16~17, 31~33호)","2016-10-10 08:30","2016-10-14 18:30","2016-10-10 08:30","2016-10-14 18:30","연속",null,null,null,"-"]
[418,"경남","함안","청도밀양#1 T/L","154kV 청도-밀양 #1,2T/L 전선교체공사","154kV 청도-밀양 T/L 전선교체공사 (48~50, 57~58, 72~74호)","2016-10-02 08:30","2016-10-08 18:30","2016-10-02 08:30","2016-10-08 18:30","연속",null,null,null,"-"]
[419,"경남","함안","청도밀양#2 T/L","154kV 청도-밀양 #1,2T/L 전선교체공사","154kV 청도-밀양 T/L 전선교체공사 (48~50, 57~58, 72~74호)","2016-10-02 08:30","2016-10-08 18:30","2016-10-02 08:30","2016-10-08 18:30","연속",null,null,null,"-"]
[420,"경남","함안","서마산진동 T/L","154kV 진동-안정#1T/L 안전이격확보","154kV 진동-안정#1T/L 안전이격확보","2016-10-10 07:00","2016-10-12 19:00","2016-10-10 07:00","2016-10-12 19:00","매일",null,null,null,"-"]
[421,"경남","함안","신마산S/S 154kV #2 BUS TIE CB","신마산 154kV 61-66BUS 모선보호반 교체공사","신마산 154kV 61-66BUS 모선보호반 교체 - 보호반 철거 및 설치 : 2면 - 제어케이블 포설 및 결선","2016-10-22 09:00","2016-10-24 18:00","2016-10-22 09:00","2016-10-24 18:00","연속",null,null,null,"-"]
[422,"경남","함안","신마산S/S 154kV #1 BUS TIE CB","신마산 154kV 60-65BUS 모선보호반 교체공사","신마산 154kV 60-65BUS 모선보호반 교체 - 보호반 철거 및 설치 : 2면 - 제어케이블 포설 및 결선","2016-10-15 09:00","2016-10-17 18:00","2016-10-15 09:00","2016-10-17 18:00","연속",null,null,null,"-"]
[423,"경남","함안","신김해진영#1 T/L","진영 신김해-진영#1T/L GIS UHF센서철치","진영 신김해-진영#1T/L GIS UHF센서철치 - 617GIS 상부브랜치 UHF센서 *1개소 설치","2016-10-04 13:00","2016-10-05 15:00","2016-10-04 13:00","2016-10-05 15:00","연속",null,null,null,"-"]
[424,"경남","함안","신김해진영#2 T/L","진영S/S 170kV GIS 하자점검공사","진영S/S 신김해-진영#2T/L GIS 하자점검","2016-10-27 09:30","2016-10-27 17:30","2016-10-27 09:30","2016-10-27 17:30","당일",null,null,null,"-"]

{"sheet":"Sheet1","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}