{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":16,"n_cols":16,"rows_kept":16,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 12월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #4 M.Tr A-1","신가평S/S #4 M.Tr 냉각장치 회로보완 공사","765kV M.Tr 냉각장치 회로보완 × 1식","2016-12-15 09:00","2016-12-17 18:00","2016-12-15 09:00","2016-12-17 18:00","연속",null,null,null,201610130025]
[2,"경기","성남","신안성S/S #5 M.Tr A-1","부싱 온라인 모니터링 시스템 점검","시스템 경보 발생 관련 점검","2016-12-09 09:00","2016-12-09 18:00","2016-12-05 09:00","2016-12-05 18:00","당일",null,null,null,201610140107]
[3,"경기","성남","신안성S/S #5 M.Tr A-1","부싱 온라인 모니터링 시스템 점검(2차)","시스템 경보 발생 관련 점검","2016-12-16 09:00","2016-12-16 18:00","2016-12-12 09:00","2016-12-12 18:00","당일",null,null,null,201610140108]
[4,"경기","성남","신안성S/S #3 M.Tr A-1","16~17년 변전협력회사 총액공사","AC 전원 상실 관련 Trip 회로 변경","2016-12-05 09:00","2016-12-08 18:00","취소","취소","연속",null,null,null,201610170102]
[5,"경기","성남","신안성S/S #2 M.Tr A-1","16~17년 변전협력회사 총액공사","AC 전원 상실 관련 Trip 회로 변경","2016-12-12 09:00","2016-12-15 18:00","취소","취소","연속",null,null,null,201610170104]
[6,"강원","태백","신태백신가평#2 T/L","765KV 신태백변전소 송전선로 인출정비공사","1.선로길이 : 1.28km, 철탑 2기 신설, 1기 보강 2.구간 : (기설)신태백-신가평T/L No.2~신태백S/S~(기설)신태백-신한울NP T/L No.86","2016-12-03 09:00","2016-12-04 18:00","2016-12-03 09:00","2016-12-04 18:00","연속",null,null,null,201610120095]
[7,"강원","태백","신태백신가평#1 T/L","765KV 신태백변전소 송전선로 인출정비공사","1.선로길이 : 1.28km, 철탑 2기 신설, 1기 보강 2.구간 : (기설)신태백-신가평T/L No.2~신태백S/S~(기설)신태백-신한울NP T/L No.86","2016-12-01 09:00","2016-12-02 18:00","2016-12-01 09:00","2016-12-02 18:00","연속",null,null,null,201610120104]
[8,"강원","태백","신태백S/S #3 M.Tr 1차 CB","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","장기미동작 차단기 조작시험(8472CB)","2016-12-14 10:00","2016-12-14 18:00","2016-12-14 10:00","2016-12-14 18:00","당일",null,null,null,201610120154]
[9,"부산울산","동부산","신고리S/S #2 M.Tr A-1","신고리S/S 800kV GIS 보통점검공사","신고리S/S 800kV 8671, 8600 GIS 보통점검(#2M.Tr 휴전)","2016-12-05 09:00","2016-12-09 18:00","2016-12-05 09:00","2016-12-09 18:00","연속",null,null,null,201610060233]
[10,"경남","함안","북경남신고리NP#1 T/L","765kV 북경남-신고리#1T/L 착설방지링 설치작업","765kV 북경남-신고리#1T/L 착설방지링 설치작업 (본사문서 송운(송전)-1386 시행지시)","2016-12-19 08:00","2016-12-24 18:00","2016-12-19 08:00","2016-12-24 18:00","연속",null,null,null,201610100131]
[11,"경남","함안","북경남신고리NP#2 T/L","765kV 북경남-신고리#2T/L 착설방지링 설치작업","765kV 북경남-신고리#2T/L 착설방지링 설치작업 (본사문서 송운(송전)-1386 시행지시)","2016-12-26 08:00","2016-12-31 18:00","2016-12-26 08:00","2016-12-31 18:00","연속",null,null,null,201610100132]
[12,"경남","함안","북경남S/S #5 M.Tr A-1","345kV 무주양수S/Y 접속설비 대체공사","362kV GIS(6CB, 링모선-&gt이중모선) 대체관련 무부하시험가압","2016-12-01 09:00","2016-12-05 18:00","2016-12-01 09:00","2016-12-05 18:00","연속",null,null,null,201610240023]

{"sheet":"345송부","index":1,"n_rows":119,"n_cols":16,"rows_kept":119,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 12월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr A","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사 (345kV #2M.Tr)","2016-12-01 09:30","2016-12-07 18:00","2016-12-01 09:30","2016-12-07 18:00","연속",null,null,null,201610170224]
[2,"서울","성동","성동S/S #1 M.Tr A","345kV 성동S/S 장기사용 모자익반 교체공사","345kV 성동S/S 장기사용 모자익반 교체공사 (345kV #1M.Tr)","2016-12-08 09:30","2016-12-15 18:00","2016-12-08 09:30","2016-12-15 18:00","연속",null,null,null,201610170225]
[3,"남서울","강남","신성남신양재 #2 T/L","345kV GIS 보통점검 - 변전총액공사","345kV GIS 보통점검 - 변전총액공사 - 신양재S/S 신성남-신양재#2T/L 보통점검","2016-12-01 10:00","2016-12-01 18:00","2016-12-01 10:00","2016-12-01 18:00","당일",null,null,null,201609300122]
[4,"남서울","영서","영서S/S 신시흥-영서#1T/L CB (7172)","345kV 미동작차단기 조작시험","- 영서S/S 신시흥-영서#1T/L 미동작차단기 조작시험","2016-12-05 14:00","2016-12-05 15:00","2016-12-05 14:00","2016-12-05 15:00","당일",null,null,null,201610140196]
[5,"남서울","영서","영서S/S 영서-영등포#1T/L CB (7572)","345kV 미동작차단기 조작시험","- 영서S/S 영서-영등포#1T/L 미동작차단기 조작시험","2016-12-05 13:00","2016-12-05 14:00","2016-12-05 13:00","2016-12-05 14:00","당일",null,null,null,201610140197]
[6,"남서울","동서울","신성남동서울#2 T/L","345kV 신성남-동서울T/L 정밀점검","대상 : No.1~No.22 (21기) 내용 : 철탑 기별 및 전선 충전부 점검","2016-12-05 09:00","2016-12-09 18:00","2016-12-05 09:00","2016-12-09 18:00","연속",null,null,null,201610160005]
[7,"인천","인천","신경서신인천CC T/L","345kV 서(신)인천C/C 용량부족 GIS 대체공사","- 345kV 신인천C/C 78Bay GIS 대체(7871,7800CB)","2016-12-03 10:00","2016-12-29 17:00","취소","취소","연속",null,null,null,201610120200]
[8,"인천","인천","신가좌신시흥#1 T/L","345kV 신가좌신시흥T/L 태풍취약철탑 보강공사","철탑 상부재 보강","2016-12-01 08:00","2016-12-01 18:00","2016-12-01 08:00","2016-12-01 18:00","당일",null,null,null,201610140198]
[9,"인천","인천","신가좌신시흥#2 T/L","345kV 신가좌신시흥T/L 태풍취약철탑 보강공사","철탑 상부재 보강","2016-12-02 08:00","2016-12-02 18:00","2016-12-02 08:00","2016-12-02 18:00","당일",null,null,null,201610140199]
[10,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S 345kV #2M.Tr 보호반 대체","신부평S/S 345kV #2M.Tr 보호반 대체","2016-12-05 09:30","2016-12-09 18:00","2016-12-05 09:30","2016-12-09 18:00","연속",null,null,null,201610140202]
[11,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S 345kV #3M.Tr 보호반 대체","신부평S/S 345kV #3M.Tr 보호반 대체","2016-12-12 09:30","2016-12-16 18:00","2016-12-12 09:30","2016-12-16 18:00","연속",null,null,null,201610140203]
[12,"인천","인천","신경서S/S 345kV #1 BUS","신경서S/S #1Sh.R 대체공사","신경서S/S #1Sh.R 대체공사 - 345㎸ #1Sh.R 대체 × 1대 - 제어케이블 결선 및 분리 × 1식 - 각종 시험 및 연동시험 등 × 1식 - 기타 부대작업 × 1식","2016-12-01 09:00","2016-12-04 18:00","2016-12-08 09:00","2016-12-11 18:00","연속",null,null,null,201610170187]
[13,"인천","인천","인천CC포스코CC#2 T/L","포스코S/Y 포스코SY인천CC#2 T/L C상 과열보수 공사","포스코S/Y 포스코S/Y인천CC #2T/L CLR 2차 인입붓싱 C상 과열 보수","2016-12-05 09:00","2016-12-05 18:00","2016-12-05 09:00","2016-12-05 18:00","당일",null,null,null,201610190050]
[14,"인천","시흥","영흥T/P #3 M.Tr(G.T) 1차 CB (7472)","영흥T/P #3 M.Tr(G.T) 1차 CB (7472) 정밀점검","영흥T/P #3 M.Tr(G.T) 1차 CB (7472) 정밀점검","2016-12-12 08:00","2016-12-14 18:00","2016-12-12 08:00","2016-12-14 18:00","연속",null,null,null,201610200003]
[15,"경기북부","구리","신의정부미금#1 T/L","전선접속개소 교체공사","o No.23-25간 상단 2가닥 전선접속개소 교체공사","2016-12-02 08:00","2016-12-02 18:00","2016-12-02 14:00","2016-12-03 18:00","당일",null,null,null,201608120189]
[16,"경기북부","구리","신의정부미금#2 T/L","전선접속개소 교체공사","o No.23-25간 상단 2가닥 전선접속개소 교체공사","2016-12-01 08:00","2016-12-01 18:00","2016-12-01 08:00","2016-12-02 14:00","당일",null,null,null,201608170131]
[17,"경기북부","구리","신가평S/S 345kV #1 BUS","765kV 신가평S/S #1M.Tr 증설공사","○ 변압기 : 765kV 1,000MVA X 1Bank ○ 개폐장치 : 800kV X 2CB(1BAY), 362kV X 2CB(1BAY) ○ 보호배전반 설치 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기초 및 접지시공 × 1식 ○ 기타 부대공사 × 1식","2016-12-01 09:00","2016-12-07 18:00","2016-12-01 09:00","2016-12-07 18:00","연속",null,null,null,201609050163]
[18,"경기북부","구리","신가평S/S 345kV #2 BUS","765kV 신가평S/S #1M.Tr 증설공사","○ 변압기 : 765kV 1,000MVA X 1Bank ○ 개폐장치 : 800kV X 2CB(1BAY), 362kV X 2CB(1BAY) ○ 보호배전반 설치 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기초 및 접지시공 × 1식 ○ 기타 부대공사 × 1식","2016-12-08 09:00","2016-12-14 18:00","2016-12-08 09:00","2016-12-14 18:00","연속",null,null,null,201609050164]
[19,"경기북부","구리","미금S/S #1 M.Tr A","구리전력지사 변전협력회사 총액공사","미금S/S 345kV GIS #1M.Tr 1차 7172 보통점검","2016-12-05 09:30","2016-12-05 16:00","취소","취소","당일",null,null,null,201610050138]
[20,"경기북부","구리","미금S/S #3 M.Tr A","구리전력지사 변전협력회사 총액공사","미금S/S 345kV GIS #3M.Tr 1차 7672 보통점검","2016-12-06 09:30","2016-12-06 16:00","취소","취소","당일",null,null,null,201610050139]
[21,"경기북부","구리","신가평S/S 345kV #2 Sh.R","2016년 구리전력지사 362kV GIS 정밀점검 공사","신가평S/S 345kV #2Sh.R GIS 보통점검 ㅇ 7300, 7371 CB","2016-12-02 09:00","2016-12-02 17:00","2016-12-02 09:00","2016-12-02 17:00","당일",null,null,null,201610050142]
[22,"경기북부","파주","신김포신파주#1 T/L","345kV 신파주S/S CLR 설치공사","1. 362kV GIB 일부 철거 및 설치 2. 345kV CLR 설치 및 모선배선","2016-12-01 09:00","2016-12-17 18:00","취소","취소","연속",null,null,null,201610120119]
[23,"경기북부","파주","신파주양주#2 T/L","345kV 신파주S/S CLR 설치공사","1. 신김포-신파주#1T/L 3상 GIB 설치 및 기타작업(근접 안전작업) 2. CLR 설치시 장비 활선 근접관련 안전 작업","2016-12-08 09:00","2016-12-12 18:00","취소","취소","연속",null,null,null,201610120121]
[24,"경기북부","구리","신포천S/S 345kV #1 Sh.R","신포천S/S 345kV #1 Sh.R 냉각장치 세정공사","345kV Sh.R 냉각장치 세정 × 1대 (7300, 7372 CB 개방)","2016-12-01 09:00","2016-12-01 18:00","2016-12-01 09:00","2016-12-01 18:00","당일",null,null,null,201610130024]
[25,"경기북부","직할","양주S/S 신파주-양주#2T/L GIS","`16-17년 직할변전총액(양주S/S 345kV 신파주-양주#2T/L)","양주S/S 345kV 신파주-양주#2T/L CVT 보통점검","2016-12-02 09:00","2016-12-02 18:00","2016-12-02 09:00","2016-12-02 18:00","당일",null,null,null,201610140009]
[26,"경기북부","구리","미금S/S STATCOM CB","STATCOM 내부 에어컨 보수","STATCOM 내부 에어컨 보수","2016-12-15 09:00","2016-12-15 18:00","2016-12-15 09:00","2016-12-15 18:00","당일",null,null,null,201610140051]
[27,"경기","성남","신안성S/S#5M.Tr 2차-신안성-서안성#1TL CB (7C00)","신안성S/S 345kV 7C00 GIS 정밀점검","신안성S/S 345kV 7C00 GIS 정밀점검, 보조계전기교체","2016-12-01 09:00","2016-12-03 18:00","2016-12-01 09:00","2016-12-03 18:00","연속",null,null,null,201610100188]
[28,"경기","성남","신성남S/S #5 M.Tr A","신성남S/S 모자익 대체공사(#5M.Tr TCC PNL)","신성남S/S 모자익 대체공사(#5M.Tr TCC PNL) #5M.Tr 2차 GIS 정밀점검공사","2016-12-05 09:00","2016-12-10 18:00","2016-12-05 09:00","2016-12-17 18:00","연속",null,null,null,201610100191]
[29,"경기","성남","신안성신성남#1 T/L","신성남S/S B/F PNL대체공사","B/F PNL대체공사, 345kV 피뢰기대체공사","2016-12-05 09:00","2016-12-10 18:00","2016-12-05 09:00","2016-12-10 18:00","연속",null,null,null,201610100201]
[30,"경기","성남","신성남S/S #6 M.Tr A","신성남S/S 모자익 대체공사(#6M.Tr TCC PNL)","신성남S/S 모자익 대체공사(#6M.Tr TCC PNL)","2016-12-12 09:00","2016-12-17 18:00","취소","취소","연속",null,null,null,201610100208]
[31,"경기","성남","신성남동서울#1 T/L","신성남S/S B/F PNL대체공사","75Bay B/F PNL대체공사, 345kV 피뢰기대체공사","2016-12-12 09:00","2016-12-17 18:00","2016-12-12 09:00","2016-12-17 18:00","연속",null,null,null,201610100211]
[32,"경기","성남","신수원S/S #3 M.Tr 1차 CB (7572)","신수원S/S 7572차단기 휴전 및 7576 DS 결상점검","신수원S/S 7576 DS 결상점검(단자대불량)","2016-12-01 09:00","2016-12-02 18:00","2016-12-01 09:00","2016-12-02 18:00","연속",null,null,null,201610120172]
[33,"경기","군포","화성서서울#1 T/L","화성-서서울#1T/L LA,CVT 이설","- 화성-서서울#1T/L LA,CVT 이설","2016-12-04 07:00","2016-12-04 18:00","2016-12-04 07:00","2016-12-04 18:00","당일",null,null,null,201610140018]
[34,"강원","동해","동해S/S #3 M.Tr A","2016년 동해전력지사 변전협력회사 총액공사","1. 동해변전소 #3M.Tr 상부 누유개소 보수 2. 동해변전소 #3M.Tr 과열개소 보수 3. 동해변전소 #3M.Tr 3차 LA 교체","2016-12-05 09:30","2016-12-05 18:00","2016-12-05 09:30","2016-12-05 18:00","당일",null,null,null,201610110016]
[35,"강원","동해","북평T/P #2STEP-UP Tr 1차 CB (7272)","북평화력 누유개소 보수작업(제작사)","1. 북평화력 7272 CB A상 누유개소보수","2016-12-06 09:30","2016-12-06 13:00","2016-12-06 09:30","2016-12-06 13:00","당일",null,null,null,201610110018]
[36,"강원","동해","북평T/P 동해-북평TP #2T/L-#2STEP-UP CB (7200)","DS 상태표시기 불량개소 보수작업(제작사)","1. 북평화력 7202 DS 인디케이터 구조개선","2016-12-06 13:30","2016-12-06 18:00","2016-12-06 13:30","2016-12-06 18:00","당일",null,null,null,201610110019]
[37,"강원","동해","삼척GP-한울NP1 #2T/L-#2M.Tr 1차 CB (7400)","DS 상태표시기 불량개소 보수작업(제작사)","1. 삼척GP S/Y 7402 DS 인디케이터 구조개선","2016-12-07 09:30","2016-12-07 13:00","2016-12-07 09:30","2016-12-07 13:00","당일",null,null,null,201610110020]
[38,"강원","동해","삼척GP-한울NP #1T/L - #2기동 Tr CB (7500)","DS 상태표시기 불량개소 보수작업(제작사)","1. 삼척GP S/Y 7502 DS 인디케이터 구조개선","2016-12-07 13:30","2016-12-07 18:00","2016-12-07 13:30","2016-12-07 18:00","당일",null,null,null,201610110021]
[39,"강원","동해","동해삼척GP#1T/L","삼척GP S/Y GIS 불량개소 보수작업(제작사)","1. 삼척GP S/Y DS 상간로드핀 발청개소 보수(7621) 2. 삼척GP S/Y DS 상간로드핀 발청개소 보수(7651) 3. 삼척GP S/Y DS 상간로드핀 발청개소 보수(7661) 4. 삼척GP S/Y DS 상간로드핀 발청개소 보수(7601) 5. 삼척GP S/Y 7602 DS 인디케이터 구조개선","2016-12-08 09:30","2016-12-08 18:00","2016-12-08 09:30","2016-12-08 18:00","당일",null,null,null,201610110023]
[40,"강원","동해","동해삼척GP#2T/L","삼척GP S/Y GIS 불량개소 보수작업(제작사)","1. 삼척GP S/Y DS 상간로드핀 발청개소 보수(7721) 2. 삼척GP S/Y DS 상간로드핀 발청개소 보수(7751) 3. 삼척GP S/Y DS 상간로드핀 발청개소 보수(7761) 4. 삼척GP S/Y DS 상간로드핀 발청개소 보수(7701) 5. 삼척GP S/Y 7702 DS 인디케이터 구조개선","2016-12-09 09:30","2016-12-09 18:00","2016-12-09 09:30","2016-12-09 18:00","당일",null,null,null,201610110024]
[41,"강원","동해","북평T/P 동해-북평TP #1T/L-#1STEP-UP CB (7100)","DS 상태표시기 불량개소 보수작업(제작사)","1. 북평화력 7102 DS 인디케이터 구조개선","2016-12-05 13:00","2016-12-05 18:00","2016-12-05 13:00","2016-12-05 18:00","당일",null,null,null,201610110026]
[42,"강원","태백","신태백S/S 345kV #3 Sh.R","신태백S/S 362kV GIS 정밀점검공사","7561DS, 7501DS, 7521DS 정밀점검","2016-12-05 08:00","2016-12-08 18:00","2016-12-05 08:00","2016-12-08 18:00","연속",null,null,null,201610120130]
[43,"강원","태백","신태백S/S 345kV #3 Sh.R CB (7571)","신태백S/S 362kV GIS 정밀점검공사","7561DS, 7501DS, 7521DS 정밀점검","2016-12-05 08:00","2016-12-08 18:00","2016-12-05 08:00","2016-12-08 18:00","연속",null,null,null,201610120131]
[44,"강원","태백","신태백S/S#3 Sh.R-신태백-한울NP2#1T/L CB (7500)","신태백S/S 362kV GIS 정밀점검공사","7561DS, 7501DS, 7521DS 정밀점검","2016-12-05 08:00","2016-12-08 18:00","2016-12-05 08:00","2016-12-08 18:00","연속",null,null,null,201610120134]
[45,"강원","태백","신태백한울NP2#1 T/L","신태백S/S 362kV GIS 정밀점검공사","7502DS 정밀점검","2016-12-09 08:00","2016-12-10 18:00","2016-12-09 08:00","2016-12-10 18:00","연속",null,null,null,201610120135]
[46,"강원","태백","신태백S/S 345kV #1 BUS","신태백S/S 362kV GIS 정밀점검공사","7551DS, 7751DS 정밀점검","2016-12-11 08:00","2016-12-14 18:00","2016-12-11 08:00","2016-12-14 18:00","연속",null,null,null,201610120137]
[47,"강원","태백","신태백S/S 345kV #2 BUS","신태백S/S 362kV GIS 정밀점검공사","7752DS 정밀점검","2016-12-15 08:00","2016-12-16 18:00","2016-12-15 08:00","2016-12-16 18:00","연속",null,null,null,201610120139]
[48,"강원","태백","신태백S/S 345kV #2 Sh.R","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","신태백S/S #2Sh.R 초기점검","2016-12-13 10:00","2016-12-13 18:00","2016-12-13 10:00","2016-12-13 18:00","당일",null,null,null,201610120150]
[49,"강원","태백","신태백S/S#2 Sh.R-신태백-한울NP3T/L CB (7400)","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","신태백S/S #2Sh.R 초기점검","2016-12-13 10:00","2016-12-13 18:00","2016-12-13 10:00","2016-12-13 18:00","당일",null,null,null,201610120152]
[50,"강원","강릉","신양양S/S #3 M.Tr A","신양양S/S 주변압기 누유 하자보수","#3MTr 주변압기 누유관련 하자보수","2016-12-01 09:00","2016-12-01 18:00","2016-12-01 09:00","2016-12-01 18:00","당일",null,null,null,201610120239]
[51,"충북","청주","신옥천신계룡 T/L","345kV 신옥천S/S 용량부족차단기 대체공사","1.신설GIS 345KV 모선연결 안전이격확보 2.기타부대공사","2016-12-20 09:00","2016-12-29 18:00","2016-12-12 09:00","2016-12-22 18:00","매일",null,null,null,201609070031]
[52,"충북","청주","청원신진천#2 T/L","345kV 청원-신진천T/L 피뢰기설치공사","345kV 송전선로용 피뢰기 설치","2016-12-08 07:00","2016-12-20 18:00","2016-12-08 07:00","2016-12-20 18:00","연속",null,null,null,201610110130]
[53,"충북","청주","청원신진천#1 T/L","16년 청주 변전협력회사 총액공사","청원S/S 청원신진천#1 T/L CVT 대체","2016-12-06 09:30","2016-12-06 18:00","2016-12-06 09:30","2016-12-06 18:00","당일",null,null,null,201610140169]
[54,"충북","직할","신충주S/S #2 M.Tr A","신충주S/S #2M.Tr A상 방열기 교체 공사","누유개소(방열기) 교체","2016-12-19 09:00","2016-12-23 18:00","2016-12-19 09:00","2016-12-23 18:00","연속",null,null,null,201610180187]
[55,"충북","직할","신충주S/S #3 M.Tr A","'16년 직할 변전협력회사 총액공사","- #3M.Tr 초기점검. - 7472, 6344 GIS 초기점검.","2016-12-05 09:00","2016-12-06 18:00","2016-12-05 09:00","2016-12-06 18:00","연속",null,null,null,201610260172]
[56,"충북","청주","신옥천청양 T/L","345kV 신옥천S/S 용량부족차단기 대체공사","1.POST 및 BEAM 조립 2.기타부대공사","2016-12-20 09:00","2016-12-23 18:00","2016-12-12 09:00","2016-12-15 18:00","연속",null,null,null,201610210097]
[57,"충북","청주","신옥천S/S 345kV #1 BUS","345kV 신옥천S/S 용량부족차단기 대체공사","1.신설 GIS 가압을 위한 모선연결 2.기타부대공사","2016-12-24 09:00","2016-12-26 18:00","2016-12-16 09:00","2016-12-18 18:00","연속",null,null,null,201610210114]
[58,"충북","청주","신옥천S/S 345kV #2 BUS","345kV 신옥천S/S 용량부족차단기 대체공사","1.POST 및 BEAM 조립, 초기가압 2.기타부대공사","2016-12-29 09:00","2016-12-29 18:00","2016-12-21 09:00","2016-12-22 18:00","당일",null,null,null,201610210116]
[59,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 70-71-0 GIS 교체","2016-12-07 09:00","2016-12-17 18:00","2016-12-07 09:00","2016-12-17 18:00","연속",null,null,null,201608120044]
[60,"대전충남","청양","보령T/P 345kV #70 BUS","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 70-71-0 GIS 교체","2016-12-07 09:00","2016-12-17 18:00","2016-12-07 09:00","2016-12-17 18:00","연속",null,null,null,201608120045]
[61,"대전충남","청양","보령T/P 75-76-0 SEC CB (75-76-0)","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV SEC B/F 보호배전반 교체","2016-12-01 09:00","2016-12-06 18:00","2016-12-01 09:00","2016-12-06 18:00","연속",null,null,null,201608170196]
[62,"대전충남","아산","아산화성#1 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-12-02 07:00","2016-12-12 18:00","취소","취소","연속",null,null,null,201609070093]
[63,"대전충남","청양","보령T/P #5,6 SU Tr 1차 CB (7471)","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 70-71-0 GIS 교체(무부하가압)","2016-12-15 09:00","2016-12-17 18:00","2016-12-15 09:00","2016-12-17 18:00","연속",null,null,null,201609130249]
[64,"대전충남","청양","보령T/P #5,6 SU Tr 1차-#4 M.Tr 1차 CB (7400)","보령화력 제2발전소 362kV GIS 교체공사","○ 보령화력 345kV 70-71-0 GIS 교체(무부하가압)","2016-12-15 09:00","2016-12-17 18:00","2016-12-15 09:00","2016-12-17 18:00","연속",null,null,null,201609130250]
[65,"대전충남","서산","신당진개폐소 태안TP#2T/L CB (7C71)","신당진개폐소 362kV GIS 모선진동 저감대책","- 362kV GIS 모선진동 저감대책관련 PAD 시공","2016-12-12 13:00","2016-12-12 18:00","2016-12-12 13:00","2016-12-12 18:00","당일",null,null,null,201610050009]
[66,"대전충남","서산","신당진개폐소 북당진#1T/L-TIE CB (7D00)","신당진개폐소 362kV GIS 모선진동 저감대책","- 362kV GIS 모선진동 저감대책관련 PAD 시공","2016-12-12 09:00","2016-12-12 13:00","2016-12-12 09:00","2016-12-12 13:00","당일",null,null,null,201610050010]
[67,"대전충남","서산","신당진개폐소 태안TP#1T/L CB (7A71)","신당진개폐소 362kV GIS 모선진동 저감대책","- 362kV GIS 모선진동 저감대책관련 PAD 시공","2016-12-13 09:00","2016-12-13 13:00","2016-12-13 09:00","2016-12-13 13:00","당일",null,null,null,201610050011]
[68,"대전충남","서산","신당진개폐소 태안TP#1-연락#1T/L CB (7A00)","신당진개폐소 362kV GIS 모선진동 저감대책","- 362kV GIS 모선진동 저감대책관련 PAD 시공","2016-12-13 13:00","2016-12-13 18:00","2016-12-13 13:00","2016-12-13 18:00","당일",null,null,null,201610050012]
[69,"대전충남","서산","신당진개폐소 현대제철-TIE CB (7B00)","신당진개폐소 362kV GIS 모선진동 저감대책","- 362kV GIS 모선진동 저감대책관련 PAD 시공","2016-12-14 09:00","2016-12-14 13:00","2016-12-14 09:00","2016-12-14 13:00","당일",null,null,null,201610050013]
[70,"대전충남","서산","신당진개폐소 북당진#1T/L CB (7D71)","신당진개폐소 362kV GIS 모선진동 저감대책","- 362kV GIS 모선진동 저감대책관련 PAD 시공","2016-12-14 13:00","2016-12-14 18:00","2016-12-14 13:00","2016-12-14 18:00","당일",null,null,null,201610050014]
[71,"대전충남","서산","신당진개폐소 7A-7B SECTION CB (7A-7B-0)","신당진개폐소 362kV GIS 모선진동 저감대책","- 362kV GIS 모선진동 저감대책관련 PAD 시공","2016-12-15 09:00","2016-12-15 13:00","2016-12-15 09:00","2016-12-15 13:00","당일",null,null,null,201610050015]
[72,"대전충남","서산","신당진개폐소 7C-7D SECTION CB (7C-7D-0)","신당진개폐소 362kV GIS 모선진동 저감대책","- 362kV GIS 모선진동 저감대책관련 PAD 시공","2016-12-15 13:00","2016-12-15 18:00","2016-12-15 13:00","2016-12-15 18:00","당일",null,null,null,201610050016]
[73,"대전충남","서산","신당진개폐소 태안TP#2-연락#2T/L CB (7C00)","신당진개폐소 362kV GIS 모선진동 저감대책","- 362kV GIS 모선진동 저감대책관련 PAD 시공","2016-12-16 09:00","2016-12-16 13:00","2016-12-16 09:00","2016-12-16 13:00","당일",null,null,null,201610050017]
[74,"대전충남","서산","신당진개폐소 신당진연락#2T/L CB (7C72)","신당진개폐소 362kV GIS 모선진동 저감대책","- 362kV GIS 모선진동 저감대책관련 PAD 시공","2016-12-16 13:00","2016-12-16 18:00","2016-12-16 13:00","2016-12-16 18:00","당일",null,null,null,201610050018]
[75,"대전충남","아산","신탕정S/S 345kV #1 BUS","신탕정S/S 345kV 북당진-신탕정T/L용 GIS 설치공사","- 362kV GIS(63kA 6,300A)×4CB 설치(2CB×2BAY)","2016-12-20 09:00","2016-12-24 18:00","2016-12-20 09:00","2016-12-24 18:00","연속",null,null,null,201610100062]
[76,"대전충남","아산","신탕정S/S 345kV #2 BUS","신탕정S/S 345kV 북당진-신탕정T/L용 GIS 설치공사","- 362kV GIS(63kA 6,300A)×4CB 설치(2CB×2BAY)","2016-12-26 09:00","2016-12-30 18:00","2016-12-26 09:00","2016-12-30 18:00","연속",null,null,null,201610100074]
[77,"전북","군산","군산신김제#2 T/L","군산신김제#2 T/L 전선접속개소교체공사","○ 전선교체 - 구간 : No.90 ~ 93 , No.106 ~ 109 114~115, 127 ~ 128","2016-12-11 07:00","2016-12-13 18:00","2016-12-04 07:00","2016-12-16 18:00","연속",null,null,null,201609190149]
[78,"전북","김제","신김제S/S 345kV #2 BUS","신김제S/S 345kV #2 BUS","가스누기 보수","2016-12-05 09:00","2016-12-10 18:00","2016-12-05 09:00","2016-12-10 18:00","연속",null,null,"신뢰도개선",201610070443]
[79,"전북","김제","군산신김제#1 T/L","군산신김제#1 T/L","신김제S/S 345kV #2 BUS 시험가압","2016-12-10 09:00","2016-12-10 18:00","2016-12-10 09:00","2016-12-10 18:00","당일",null,null,null,201610070444]
[80,"전북","군산","군산S/S #2 M.Tr A","군산S/S #2 M.Tr A","1. 불량 유량온도계교체 및 보조계전기 교체","2016-12-12 09:00","2016-12-14 18:00","2016-12-12 09:00","2016-12-14 18:00","연속",null,null,null,201610110011]
[81,"전북","직할","신남원신광주#1 T/L","345kV 신남원S/S M.Tr 설치","362kV GIS CB(7772)×1대 증설, 77B/F개조 및 CB(7772)무부하가압","2016-12-13 09:00","2016-12-19 12:00","2016-12-12 07:00","2016-12-19 18:00","연속",null,null,null,201610120249]
[82,"전북","군산","군산S/S #1 M.Tr A","군산S/S #1 M.Tr A","1. 예비변압기 절체반 설치공사","2016-12-05 09:00","2016-12-07 18:00","2016-12-05 09:00","2016-12-07 18:00","연속",null,null,null,201610170042]
[83,"전북","군산","군산S/S #4 M.Tr A","군산S/S #4 M.Tr A","1. 예비변압기 절체반 설치공사","2016-12-08 09:00","2016-12-10 18:00","2016-12-08 09:00","2016-12-10 18:00","연속",null,null,null,201610170043]
[84,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주T/L 전선접속개소 전력선교체공사","전선접속개소 전력선 교체(ACSR480㎟ × 4B : 2.679C-km) 가공지선 교체 : 2.679km 스페이서댐퍼 교체 : 172개","2016-12-07 07:00","2016-12-12 18:00","2016-12-06 07:00","2016-12-11 18:00","연속",null,null,null,201610190010]
[85,"광주전남","순천","광양S/S #2 M.Tr A","345kV 광양S/S #2M.Tr(변압기 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - M.Tr 보통점검, 74Bay 현수애자 교체","2016-12-05 10:00","2016-12-07 18:00","2016-12-05 10:00","2016-12-07 18:00","연속",null,null,null,201610050119]
[86,"광주전남","순천","광양S/S #3 M.Tr A","345kV 광양S/S #3M.Tr(변압기 누유개소 보수)","2016~17년 순천전력지사 변전협력회사 총액공사 - M.Tr 누유개소 보수","2016-12-08 10:00","2016-12-08 18:00","2016-12-01 10:00","2016-12-01 18:00","당일",null,null,null,201610050120]
[87,"광주전남","순천","신강진광양#2 T/L","345kV 신강진-광양#2T/L(광양S/S GIS,CVT 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 7771,7700 GIS 보통점검 - CVT 보통점검","2016-12-01 10:00","2016-12-02 18:00","2016-12-01 10:00","2016-12-02 18:00","연속",null,null,null,201610050123]
[88,"광주전남","순천","신강진광양#1 T/L","345kV 신강진-광양#1T/L(광양S/S GIS 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 7871,7800 GIS 보통점검","2016-12-05 10:00","2016-12-06 18:00","2016-12-05 10:00","2016-12-06 18:00","연속",null,null,null,201610050124]
[89,"광주전남","순천","신남원광양#1 T/L","345kV 신남원-광양T/L 지상고확보공사","철탑교체 6기","2016-12-15 07:00","2016-12-20 18:00","2016-12-15 07:00","2016-12-20 18:00","연속",null,null,"신뢰도개선",201610110135]
[90,"광주전남","순천","신남원광양#2 T/L","345kV 신남원-광양T/L 지상고확보공사","철탑교체 6기","2016-12-08 07:00","2016-12-14 18:00","2016-12-08 07:00","2016-12-14 18:00","연속",null,null,"신뢰도개선",201610110136]
[91,"광주전남","광주","신광주신화순#2 T/L","345kV 신광주-신화순T/L 지상고확보공사","철탑교체 2기 전선교체 2경간","2016-12-08 07:00","2016-12-13 18:00","2016-12-08 07:00","2016-12-15 18:00","연속",null,null,null,201610110137]
[92,"광주전남","광주","신광주신화순#1 T/L","345kV 신광주-신화순T/L 지상고확보공사","철탑교체 2기 전선교체 2경간","2016-12-14 07:00","2016-12-19 18:00","2016-12-16 07:00","2016-12-21 18:00","연속",null,null,null,201610110138]
[93,"광주전남","순천","광양율촌CC T/L","345kV 광양S/S 362kV GIS 대체공사","가. GIS(345kV 50kA 4000A) ×27 CB 철거 나. GIS(345kV 63kA 6300A) ×27 CB 설치 다. 기타 부대작업 × 1식","2016-12-02 09:00","2017-03-02 18:00","2016-12-02 09:00","2017-03-02 18:00","연속",null,null,null,201610130171]
[94,"대구경북","영주","한울2NP-한울2NP #6T/L","한울N/P 345kV 송전선로 인출정비공사","한울연락#3T/L(3발-기2발) 및 한울연락#6T/L(기2발-신2발) 휴전 후 한울연락#3T/L(3발-신2발)로 계통변경","2016-12-10 08:00","2016-12-16 18:00","2016-12-10 08:00","2016-12-16 18:00","연속",null,null,null,201610050038]
[95,"대구경북","영주","한울2NP-한울3NP #3T/L","한울N/P 345kV 송전선로 인출정비공사","한울연락#3T/L(3발-기2발) 및 한울연락#6T/L(기2발-신2발) 휴전 후 한울연락#3T/L(3발-신2발)로 계통변경","2016-12-10 08:00","2016-12-16 18:00","2016-12-10 08:00","2016-12-16 18:00","연속",null,null,null,201610050064]
[96,"대구경북","구미","선산S/S #4 M.Tr A","선산S/S 345kV #4M.Tr 휴전","- 변압기 보호반 대체 - 7772,7700 GIS 보통점검","2016-12-05 09:00","2016-12-09 18:00","2016-12-05 09:00","2016-12-09 18:00","연속",null,null,null,201610060142]
[97,"대구경북","칠곡","서대구S/S #3 M.Tr A","서대구S/S #3M.Tr 보호반 교체","서대구S/S #3M.Tr 보호반 교체","2016-12-19 09:30","2016-12-23 18:00","2016-12-19 09:30","2016-12-23 18:00","연속",null,null,null,201610060160]
[98,"대구경북","달성","대구S/S #1 M.Tr A","2016년 하반기 주변압기정밀점검","주변압기 정밀점검","2016-12-01 09:00","2016-12-10 18:00","2016-12-01 09:00","2016-12-10 18:00","연속",null,null,null,201610070067]
[99,"대구경북","영주","삼척GP한울NP1 #1T/L","한울1발 B/F 계전기 교체, 통합감시제어 결선(O/H 병행)","한울1발 B/F 계전기 교체, 통합감시제어 결선(O/H 병행)","2016-12-01 09:00","2016-12-05 18:00","2016-12-01 09:00","2016-12-05 18:00","연속",null,null,null,201610070207]
[100,"대구경북","포항","신영일S/S #3 M.Tr","신영일S/S 예비M.Tr, 3차 LA 보통점검","신영일S/S 예비M.Tr, 3차 LA 보통점검","2016-12-13 09:00","2016-12-13 18:00","2016-12-13 09:00","2016-12-13 18:00","당일",null,null,null,201610070313]
[101,"대구경북","포항","월성2N/P #2 M.Tr 2차 CB (7372)","월성S/Y 7372 CB 보통점검","월성S/Y 7372 CB 보통점검","2016-12-28 09:30","2016-12-28 18:00","2016-12-28 09:30","2016-12-28 18:00","당일",null,null,null,201610070337]
[102,"대구경북","달성","대구S/S 345kV #1 Sh.R","대구S/S #1Sh.R 휴전","#1Sh.R 및 GIS정밀점검","2016-12-19 09:30","2016-12-21 18:00","2016-12-19 09:30","2016-12-21 18:00","연속",null,null,null,201610100019]
[103,"대구경북","달성","대구S/S 345kV #2 Sh.R","대구S/S #2Sh.R 휴전","#2Sh.R 및 GIS정밀점검","2016-12-22 09:30","2016-12-24 18:00","2016-12-22 09:30","2016-12-24 18:00","연속",null,null,null,201610100020]
[104,"대구경북","달성","서대구고령#2 T/L","345kV 서대구-고령T/L 안전이격 확보공사","- 16,18호 철탑교체 - 12~17호 전선이동, 17~19호 전선교체","2016-12-08 08:00","2016-12-15 18:00","2016-12-08 08:00","2016-12-15 18:00","연속",null,null,null,201610100159]
[105,"대구경북","영주","(신)신영주S/S 345kV #1 BUS CB","신영주S/S STATCOM 설치공사","신영주S/S STATCOM 설치공사(362kV GIS 설치)","2016-12-06 09:00","2016-12-09 18:00","2016-12-06 09:00","2016-12-09 18:00","연속",null,null,null,201610100272]
[106,"대구경북","포항","신포항S/S #4 M.Tr A","신포항S/S #4M.Tr 휴전작업","#4M.Tr A,C상 누유추이 확인 후 정밀점검, 정상시 7772, 6444 CB 보통점검","2016-12-12 09:00","2016-12-15 18:00","2016-12-12 09:00","2016-12-15 18:00","연속",null,null,null,201610130172]
[107,"대구경북","경산","신경산S/S #3 M.Tr A","'16년 신경산S/S 170kV 장기사용 GIS 대체공사","#61-66PT 대체관련 안전이격 확보","2016-12-15 09:00","2016-12-22 18:00","2016-12-15 09:00","2016-12-22 18:00","연속",null,null,null,201610160019]
[108,"대구경북","달성","고령S/S 북경남-고령#2T/L CB (7771)","2016년 하반기 주변압기정밀점검(7771)","하반기 GIS정밀점검(7771)","2016-12-05 09:00","2016-12-07 18:00","2016-12-05 09:00","2016-12-07 18:00","연속",null,null,null,201610190125]
[109,"대구경북","달성","고령S/S 북경남-고령#2T/L-TIE CB (7700)","2016년 하반기 주변압기정밀점검(7700)","하반기 GIS정밀점검(7700)","2016-12-15 09:00","2016-12-17 18:00","2016-12-15 09:00","2016-12-17 18:00","연속",null,null,null,201610190126]
[110,"부산울산","울산","울산C/C 기력4호기 1차 CB (7472)","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 345kV 7472 GIS 하자점검","2016-12-02 09:00","2016-12-02 18:00","2016-12-02 09:00","2016-12-02 18:00","당일",null,null,null,201610100332]
[111,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S 345kV #1Sh.R 대체공사(시험가압)","서부산S/S 345kV #1Sh.R 대체공사(시험가압-48H)","2016-12-16 18:00","2016-12-18 18:00","2016-12-16 18:00","2016-12-18 18:00","연속",null,null,null,201610130174]
[112,"부산울산","울산","울산C/C #1 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 #1M.Tr 보통점검, 7400,7471,6144,4184 GIS 보통점검","2016-12-03 09:00","2016-12-04 18:00","취소","취소","연속",null,null,null,201610140204]
[113,"부산울산","울산","울산C/C #2 M.Tr A","2016-17년 울산전력지사 변전협력회사 총액공사","울산복합 #2M.Tr 보통점검, 7871,6244,4284 GIS 보통점검","2016-12-17 09:00","2016-12-18 18:00","취소","취소","연속",null,null,null,201610140205]
[114,"경남","직할","신김해삼천포화력#1 T/L","신김해-삼천포화력#1 초기점검(2016 가공송전 순시점검 위탁공사)","345kV 신김해-삼천포화력#1 초기점검(229~S/T)","2016-12-11 08:00","2016-12-11 11:00","2016-12-11 08:00","2016-12-11 11:00","당일",null,null,"신뢰도개선",201610070319]
[115,"경남","직할","신김해삼천포화력#2 T/L","신김해-삼천포화력#2 초기점검(2016 가공송전 순시점검 위탁공사)","345kV 신김해-삼천포화력#2 초기점검(229~S/T)","2016-12-11 11:00","2016-12-11 14:00","2016-12-11 11:00","2016-12-11 14:00","당일",null,null,"신뢰도개선",201610070321]

{"sheet":"154송부","index":2,"n_rows":213,"n_cols":16,"rows_kept":213,"cut":false,"hidden":false,"merged":[[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13]]}
["2016년도 12월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부용산#2 T/L","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 중부용산#2T/L(6G7) GIS 정밀점검","2016-12-01 08:00","2016-12-03 18:00","2016-12-01T08:00:00","2016-12-03T18:00:00","연속",null,null,null,201607140149]
[2,"서울","중부","중부S/S 154kV #66 BUS","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 중부용산#2T/L GIS(6G7) #2DS 정밀점검","2016-12-02 14:00","2016-12-03 18:00","2016-12-02T14:00:00","2016-12-03T18:00:00","연속",null,null,null,201607140157]
[3,"서울","중부","중부S/S 154kV #61 BUS","2016년 중부전력지사 170kV GIS 정밀점검 공사","중부S/S 중부용산#2T/L GIS(6G7) #1DS 정밀점검","2016-12-01 08:00","2016-12-02 14:00","2016-12-01T08:00:00","2016-12-02T14:00:00","연속",null,null,null,201607140158]
[4,"서울","중부","중부S/S 154kV #61 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","중부S/S 154kV PT반 교체공사","2016-12-05 10:00","2016-12-05 18:00","2016-12-05T10:00:00","2016-12-05T18:00:00","당일",null,null,null,201610120066]
[5,"서울","중부","중부S/S 154kV #60 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","중부S/S 154kV PT반 교체공사","2016-12-06 10:00","2016-12-06 18:00","2016-12-06T10:00:00","2016-12-06T18:00:00","당일",null,null,null,201610120068]
[6,"서울","중부","중부S/S 154kV #65 BUS","2016~2017년 중부전력지사 변전협력업체 총액공사","중부S/S 154kV PT반 교체공사","2016-12-07 10:00","2016-12-07 18:00","2016-12-07T10:00:00","2016-12-07T18:00:00","당일",null,null,null,201610120070]
[7,"서울","중부","양주은평#2 T/L","2016~2017년 중부전력지사 변전협력업체 총액공사","은평S/S 154kV 양주은평#2T/L 보호배전반 교체공사 (627)","2016-12-15 10:00","2016-12-16 18:00","2016-12-15T10:00:00","2016-12-16T18:00:00","연속",null,null,null,201610120071]
[8,"서울","성동","창동돈암 T/L","16년 성동 변전협력회사 총액공사 (돈암S/S 창동돈암T/L)","170kV GIS 보통점검 (돈암S/S 창동돈암T/L)","2016-12-09 10:00","2016-12-09 17:00","2016-12-09T10:00:00","2016-12-09T17:00:00","당일",null,null,null,201610130231]
[9,"서울","직할","세종로옥인#2 T/L","화양 및 세종로S/S 인출선로 선종교체공사","1. 사 업 명 : 화양 및 세종로S/S 인출선로 선종교체공사 2. 사업목적 : 지하복합변전소 화재 및 대형 재난사고 예방 3. 사업개요 ○ 사업구간 : 화양S/S ∼ 인출전력구, 세종로S/S ∼ 인출전력구 ○ 사업내용 : 154kV 6회선 0.6km 선종교체","2016-12-01 10:00","2016-12-30 17:00","2016-11-28T10:00:00","2016-12-27T17:00:00","연속",null,null,null,201610170195]
[10,"남서울","직할","봉천신길#1 T/L","변전총액공사(신길S/S 봉천-신길#1T/L GIS 초기)","변전총액공사(신길S/S 봉천-신길#1T/L GIS 초기)","2016-12-05 09:30","2016-12-05 14:00","2016-12-05T09:30:00","2016-12-05T14:00:00","연속",null,null,null,201608170110]
[11,"남서울","동서울","잠실삼성#1 T/L","삼성S/S OF 송전선로 이설 및 선종교체공사","삼성#2S/S 건설로 인한 송전선로 이설 및 OF 케이블 선종교체 공사","2016-12-01 10:00","2016-12-30 18:00","2016-12-01T10:00:00","2016-12-30T18:00:00","연속",null,null,null,201609220006]
[12,"남서울","강남","신양재역삼#2 T/L","송전선로 미동작차단기 시험 - 직영","송전선로 미동작차단기 시험 - 직영 -신양재-역삼#2T/L","2016-12-02 10:00","2016-12-02 18:00","취소","취소","당일",null,null,"신뢰도개선",201609300110]
[13,"남서울","동서울","강동천호#2 T/L","154kV 강동-천호T/L 천호S/S 인출구간 선종교체공사","천호S/S 인출구간 OF케이블을 XLPE케이블로 교체","2016-12-01 09:00","2016-12-30 18:00","2016-12-01T09:00:00","2016-12-30T18:00:00","연속",null,null,null,201610040038]
[14,"남서울","영서","독산대방#1 T/L","154kV 미동작 차단기 조작시험","- 독산,대방S/S 154kV 독산-대방#1,2T/L 조작시험","2016-12-06 10:00","2016-12-06 11:00","2016-12-06T10:00:00","2016-12-06T11:00:00","당일",null,null,null,201610170076]
[15,"남서울","영서","독산대방#2 T/L","154kV 미동작 차단기 조작시험","- 독산,대방S/S 154kV 독산-대방#1,2T/L 조작시험","2016-12-06 11:00","2016-12-06 12:00","2016-12-06T11:00:00","2016-12-06T12:00:00","당일",null,null,null,201610170077]
[16,"남서울","영서","시흥독산#1 T/L","154kV 미동작 차단기 조작시험","- 독산,시흥S/S 154kV 시흥-독산#1,2T/L 조작시험","2016-12-07 10:00","2016-12-07 11:00","2016-12-07T10:00:00","2016-12-07T11:00:00","당일",null,null,null,201610170081]
[17,"남서울","영서","시흥독산#2 T/L","154kV 미동작 차단기 조작시험","- 독산,시흥S/S 154kV 시흥-독산#1,2T/L 조작시험","2016-12-07 11:00","2016-12-07 12:00","2016-12-07T11:00:00","2016-12-07T12:00:00","당일",null,null,null,201610170083]
[18,"남서울","영서","온수소래 T/L","154kV 미동작 차단기 조작시험","- 온수S/S 154kV 온수-소래T/L 조작시험","2016-12-07 14:00","2016-12-07 15:00","2016-12-07T14:00:00","2016-12-07T15:00:00","당일",null,null,null,201610170084]
[19,"남서울","영서","신정목동#1 T/L","154kV 미동작 차단기 조작시험","- 목동,신정S/S 154kV 신정-목동#1,2T/L 조작시험","2016-12-08 10:00","2016-12-08 11:00","2016-12-08T10:00:00","2016-12-08T11:00:00","당일",null,null,null,201610170087]
[20,"남서울","영서","신정목동#2 T/L","154kV 미동작 차단기 조작시험","- 목동,신정S/S 154kV 신정-목동#1,2T/L 조작시험","2016-12-08 11:00","2016-12-08 12:00","2016-12-08T11:00:00","2016-12-08T12:00:00","당일",null,null,null,201610170088]
[21,"남서울","영서","부천신정#1 T/L","154kV 미동작 차단기 조작시험","- 신정S/S 154kV 부천-신정#1,2T/L 조작시험","2016-12-08 13:30","2016-12-08 14:30","2016-12-08T13:30:00","2016-12-08T14:30:00","당일",null,null,null,201610170089]
[22,"남서울","영서","부천신정#2 T/L","154kV 미동작 차단기 조작시험","- 신정S/S 154kV 부천-신정#1,2T/L 조작시험","2016-12-08 14:30","2016-12-08 15:30","2016-12-08T14:30:00","2016-12-08T15:30:00","당일",null,null,null,201610170091]
[23,"남서울","동서울","삼성선릉#1 T/L","154kV 삼성-선릉 지중T/L 이설공사","삼성동 (구)본사부지 내 현대차 글로벌 비지니스센터(GBC)건설에 따른 부지 내 전력설비 이전필요에 따른 케이블이설공사(EBG~J/B#2)","2016-12-27 10:00","2017-02-10 18:00","2016-12-27T10:00:00","2017-02-10T18:00:00","연속",null,null,null,201610170129]
[24,"남서울","영서","신림봉천 T/L","봉천,노들변전소 OF케이블 선종교체공사","케이블철거 및 설치 : OF케이블에서 XLPE로 교체(264m X 3상) 이종 및 종단 접속 : 2개소 X 3상 PT 이설 및 기타 부대작업","2016-12-02 09:00","2016-12-30 18:00","2016-12-02T09:00:00","2016-12-30T18:00:00","연속",null,null,null,201610180004]
[25,"남서울","직할","영등포노량진 T/L","영등포-노량진T/L 누유개소 보수작업","OF케이블 급유관 연결 절연 컨넥터 1개 교체","2016-12-08 10:00","2016-12-08 16:00","2016-12-08T10:00:00","2016-12-08T16:00:00","당일",null,null,null,201610180005]
[26,"남서울","직할","노들노량진 T/L","노들-노량진T/L 절연유 체유","절연유 체유 3개소","2016-12-07 10:00","2016-12-07 15:00","2016-12-07T10:00:00","2016-12-07T15:00:00","당일",null,null,null,201610180006]
[27,"남서울","영서","온수소래 T/L","16년 영서P/O 가공송전협력회사공사(송전선로용 피뢰기 설치)","16년 영서P/O 가공송전협력회사공사(송전선로용 피뢰기 설치)","2016-12-05 09:00","2016-12-07 18:00","2016-12-05T09:00:00","2016-12-07T18:00:00","연속",null,null,null,201610190021]
[28,"남서울","동서울","강동풍납#1 T/L","미동작 차단기 점검","미동작 차단기 점검","2016-12-01 13:00","2016-12-01 14:00","2016-12-01T13:00:00","2016-12-01T14:00:00","당일",null,null,null,201610190146]
[30,"남서울","동서울","강동풍납#2 T/L","미동작 차단기 점검","미동작 차단기 점검","2016-12-01 13:00","2016-12-01 14:00","2016-12-01T13:00:00","2016-12-01T14:00:00","당일",null,null,null,201610190149]
[31,"남서울","동서울","풍납석촌#1 T/L","미동작 차단기 점검","미동작 차단기 점검","2016-12-02 10:00","2016-12-02 11:00","2016-12-02T10:00:00","2016-12-02T11:00:00","당일",null,null,null,201610190151]
[32,"남서울","동서울","풍납석촌#2 T/L","미동작 차단기 점검","미동작 차단기 점검","2016-12-02 10:00","2016-12-02 11:00","2016-12-02T10:00:00","2016-12-02T11:00:00","당일",null,null,null,201610190152]
[33,"남서울","영서","영서소래 T/L","16년 가공송전위탁공사(위험표지판 전력선 설치)","16년 가공송전위탁공사(위험표지판 전력선 설치)","2016-12-08 09:00","2016-12-08 13:00","2016-12-08T09:00:00","2016-12-08T13:00:00","당일",null,null,null,201610200015]
[34,"남서울","영서","영서온수 T/L","16년 가공송전위탁공사(위험표지판 전력선 설치 시행)","16년 가공송전위탁공사(위험표지판 전력선 설치 시행)","2016-12-08 13:00","2016-12-08 18:00","2016-12-08T13:00:00","2016-12-08T18:00:00","당일",null,null,null,201610200016]
[35,"남서울","영서","영서시흥#1 T/L","16년 가공송전위탁공사(위험표지판 전력선 설치)","16년 가공송전위탁공사(위험표지판 전력선 설치)","2016-12-12 09:00","2016-12-12 13:00","2016-12-12T09:00:00","2016-12-12T13:00:00","당일",null,null,null,201610200017]
[36,"남서울","영서","영서시흥#2 T/L","16년 가공송전위탁공사(위험표지판 전력선 설치)","16년 가공송전위탁공사(위험표지판 전력선 설치)","2016-12-12 13:00","2016-12-12 18:00","2016-12-12T13:00:00","2016-12-12T18:00:00","당일",null,null,null,201610200018]
[37,"남서울","영서","화곡S/S 154kV #1 BUS","2016년 변전협력회사 총액공사-보통점검","- 화곡S/S 154kV GIS PT 보통점검","2016-12-02 10:00","2016-12-02 13:00","2016-12-02T10:00:00","2016-12-02T13:00:00","당일",null,null,null,201610200055]
[38,"남서울","영서","화곡S/S 154kV #2 BUS","2016년 변전협력회사 총액공사-보통점검","- 화곡S/S 154kV GIS PT 보통점검","2016-12-02 13:00","2016-12-02 17:00","2016-12-02T13:00:00","2016-12-02T17:00:00","당일",null,null,null,201610200056]
[39,"남서울","영서","광명구공#2 T/L","(주)영인기술 154kV 송전선로 보호반 성능개선","(주)영인기술 154kV 송전선로 보호반 성능개선","2016-12-03 09:00","2016-12-03 18:00","2016-12-03T09:00:00","2016-12-03T18:00:00","당일",null,null,null,201610210044]
[40,"인천","인천","신현포스코CC#2 T/L","154kV 신현포스코CCT/L 지장송전선로 이설 공사","한진중공업에서 시행하는 인천북항 배후부지 항만구역 조성공사에 지장되는 154kV 신현-포스코CC T/L 지장이설 필요 - 이설구간 : 154kV 신현-포스코CC #2T/L M/H #4~M/H #5 (약313m)","2016-12-20T09:00:00","2017-01-04T18:00:00","2016-12-20T09:00:00","2017-01-04T18:00:00","연속",null,null,null,201610130167]
[41,"인천","인천","신현포스코CC#1 T/L","154kV 신현포스코CCT/L 지장송전선로 이설 공사","한진중공업에서 시행하는 인천북항 배후부지 항만구역 조성공사에 지장되는 154kV 신현-포스코CC T/L 지장이설 필요 - 이설구간 : 154kV 신현-포스코CC #2T/L M/H #4~M/H #5 (약313m)","2016-12-04T09:00:00","2016-12-19T18:00:00","2016-12-04T09:00:00","2016-12-19T18:00:00","연속",null,null,null,201610310013]
[42,"인천","시흥","신시흥#1S/S 154kV #2 BUS TIE GIS","신시흥#1S/S 154kV 6200 GIS 정밀점검공사","신시흥#1S/S 154kV 6200 GIS 정밀점검공사","2016-12-01 08:00","2016-12-03 18:00","2016-12-01T08:00:00","2016-12-03T18:00:00","연속",null,null,null,201610170009]
[43,"인천","시흥","신시흥#1S/S 154kV #66 BUS","신시흥#1S/S 154kV 6200 GIS 정밀점검공사","신시흥#1S/S 154kV 6200 GIS 정밀점검공사","2016-12-01 08:00","2016-12-02 14:00","2016-12-01T08:00:00","2016-12-02T14:00:00","연속",null,null,null,201610170011]
[44,"인천","시흥","신시흥#1S/S 154kV #61 BUS","신시흥#1S/S 154kV 6200 GIS 정밀점검공사","신시흥#1S/S 154kV 6200 GIS 정밀점검공사","2016-12-02 14:00","2016-12-03 18:00","2016-12-02T14:00:00","2016-12-03T18:00:00","연속",null,null,null,201610170012]
[45,"인천","인천","신가좌인천#1 T/L","신가좌S/S 신가좌인천#1T/L GIS 접지개폐기 불량 보수","신가좌S/S 신가좌인천#1T/L GIS 접지개폐기 불량 보수","2016-12-02 09:00","2016-12-02 18:00","2016-12-02T09:00:00","2016-12-02T18:00:00","당일",null,null,null,201610170201]
[46,"인천","인천","신현S/S 154kV #2 BUS","154kV 신현-포스코CC #2T/L M/H#4~#5 지장이설공사","154kV 신현-포스코CC #2T/L 지장이설관련 상체크시험","2016-12-18 13:00","2016-12-18 18:00","2016-12-18T13:00:00","2016-12-18T18:00:00","당일",null,null,null,201610180118]
[47,"인천","인천","남동관교#2 T/L","'16-17년 가공송전정비 협력회사 총액공사","송전용 피뢰기 설치공사(11기)","2016-12-03 08:00","2016-12-03 18:00","2016-12-03T08:00:00","2016-12-03T18:00:00","매일",null,null,null,201610200011]
[48,"경기북부","직할","운천전곡#2 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-&gt메탈판넬) 교체","2016-12-12 09:00","2016-12-16 18:00","2016-12-12T09:00:00","2016-12-16T18:00:00","연속",null,null,null,201607130079]
[49,"경기북부","직할","신포천전곡#1 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-&gt메탈판넬) 교체","2016-12-12 09:00","2016-12-16 18:00","2016-12-12T09:00:00","2016-12-16T18:00:00","연속",null,null,null,201607130082]
[50,"경기북부","파주","고양일산#2 T/L","154kV 고양-일산#2T/L 정밀점검","- 내용 : 154kV 고양-일산#2T/L No.1,2,3,4,11(2회선철탑) 정밀점검 - 시행업체 : 한전KPS(주)","2016-12-01 09:00","2016-12-01 18:00","2016-12-01T09:00:00","2016-12-01T18:00:00","당일",null,null,null,201610120024]
[51,"경기북부","구리","덕소마석#1 T/L","154kV 덕소-마석#1T/L 피뢰기 설치공사","ㅇ 피뢰기설치 - 대상 : No.1,2,3","2016-12-03 08:00","2016-12-03 14:00","2016-12-03T08:00:00","2016-12-03T14:00:00","당일",null,null,null,201610120240]
[52,"경기북부","구리","마석청평HP#2 T/L","154kV 덕소-마석#1T/L 피뢰기 설치공사 병가선로","ㅇ 피뢰기설치 - 대상 : 덕소-마석T/L No.1,2,3","2016-12-03 08:00","2016-12-03 14:00","2016-12-03T08:00:00","2016-12-03T14:00:00","당일",null,null,null,201610120241]
[53,"경기북부","구리","마석청평HP#1 T/L","154kV 마석-청평HP#1T/L 피뢰기 설치공사","ㅇ 피뢰기설치 - 대상 : No.33,34,35","2016-12-03 14:00","2016-12-03 18:00","2016-12-03T14:00:00","2016-12-03T18:00:00","당일",null,null,null,201610120242]
[54,"경기북부","구리","덕소마석#2 T/L","154kV 마석-청평HP#1T/L 피뢰기 설치공사 병가선로","ㅇ 피뢰기설치 - 대상 : 마석-청평HP#1T/L No.33,34,35","2016-12-03 14:00","2016-12-03 18:00","2016-12-03T14:00:00","2016-12-03T18:00:00","당일",null,null,null,201610120243]
[55,"경기북부","구리","신장덕소#1 T/L","154kV 신장-덕소#1T/L 압축인류크램프 교체공사","ㅇ 압축인류크램프 교체공사 - No.11,12,13,16,24","2016-12-04 08:00","2016-12-04 18:00","2016-12-04T08:00:00","2016-12-04T18:00:00","당일",null,null,null,201610120244]
[56,"경기북부","구리","신장덕소#2 T/L","154kV 신장-덕소#2T/L 압축인류크램프 교체공사","ㅇ 압축인류크램프 교체공사 - No.8,11,13,16","2016-12-05 08:00","2016-12-06 18:00","2016-12-05T08:00:00","2016-12-06T18:00:00","연속",null,null,null,201610120245]
[57,"경기북부","직할","신포천전곡#2 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-메탈판넬) 교체","2016-12-05 09:00","2016-12-09 18:00","2016-12-05T09:00:00","2016-12-09T18:00:00","연속",null,null,null,201610130065]
[58,"경기북부","직할","운천전곡#1 T/L","전곡변전소 외장재 전면교체공사","- 건물 외부 마감재(드라이비트-&gt메탈판넬) 교체","2016-12-05 09:00","2016-12-09 18:00","2016-12-05T09:00:00","2016-12-09T18:00:00","연속",null,null,null,201610130066]
[59,"경기북부","직할","신의정부용현#1 T/L","신의정부용현#1 T/L","2016년 직할 변전협력회사 총액공사 - GIS 초기","2016-12-01 10:00","2016-12-01 18:00","2016-12-01T10:00:00","2016-12-01T18:00:00","당일",null,null,null,201610130140]
[60,"경기북부","직할","신의정부용현#2 T/L","신의정부용현#2T/L","2016년 직할 변전협력회사 총액공사 - GIS 초기","2016-12-02 10:00","2016-12-02 18:00","2016-12-02T10:00:00","2016-12-02T18:00:00","당일",null,null,null,201610130141]
[61,"경기북부","직할","옥정동두천#1 T/L","옥정동두천#1 T/L","2016년 직할 변전협력회사 총액공사 - GIS 하자","2016-12-05 10:00","2016-12-05 18:00","2016-12-05T10:00:00","2016-12-05T18:00:00","당일",null,null,null,201610130146]
[62,"경기북부","파주","일산호수#2 T/L","백마지하차도 지장송전선로 이설공사","지중송전선로 이설 : 일산-호수 관로 #2~3","2016-12-03 08:00","2016-12-19 18:00","2016-12-03T08:00:00","2016-12-19T18:00:00","연속",null,null,null,201610170126]
[63,"경기북부","구리","미금구리#2 T/L","170kV 미금구리 #2T/L GIS 정밀점검공사","구리S/S 170kV 미금구리 #2T/L GIS 정밀점검공사(647CB) 12.5~7 미금S/S 170kV 미금구리 #2T/L GIS 정밀점검공사(627CB) 12.8~10","2016-12-05 09:00","2016-12-10 18:00","취소","취소","연속",null,null,"신뢰도개선",201610180181]
[64,"경기북부","파주","신파주금촌#1 T/L","16년 파주전력지사 변전협력회사 총액공사(전자변 교체)","금촌S/S 신파주금촌#1T/L GIS 전자변 교체","2016-12-05 10:00","2016-12-05 17:00","2016-12-05T10:00:00","2016-12-05T17:00:00","당일",null,null,null,201610210194]
[65,"경기","평택","평택추팔#1 T/L","154kV 평택-추팔T/L No.14, 15 안전이격 확보공사","철탑교체 2기(No.14, 15), 가철주 2기 전력선교체(접속개소 제거)","2016-12-05 08:00","2016-12-09 18:00","2016-12-05T08:00:00","2016-12-09T18:00:00","연속",null,null,null,201609050202]
[66,"경기","평택","송탄오성CC#1 T/L","154kV 평택-추팔T/L No.14, 15 안전이격 확보공사","No.13 병가선로 opgw 작업시 안전거리 확보","2016-12-03 09:00","2016-12-03 18:00","2016-12-03T09:00:00","2016-12-03T18:00:00","당일",null,null,null,201609070001]
[67,"경기","군포","신안산성포#2 T/L","신안산SS 감시제어반 교체 공사","신안산SS 감시제어반 교체 공사 -신안산성포#2 T/L 감시, 조작회로 이설","2016-12-08 09:00","2016-12-10 18:00","2016-12-08T09:00:00","2016-12-10T18:00:00","연속",null,null,null,201609070061]
[68,"경기","군포","신안산성포#1 T/L","신안산SS 감시제어반 교체 공사","신안산SS 감시제어반 교체 공사 -신안산성포#1T/L 감시, 조작회로 이설","2016-12-12 09:00","2016-12-14 18:00","2016-12-12T09:00:00","2016-12-14T18:00:00","연속",null,null,null,201609090116]
[69,"경기","평택","청북평택#1 T/L","포승-청북 등 2개T/L 상간스페이서 설치공사","○ 154kV 청북-평택#1T/L, 포승-청북#2T/L 3경간 상간스페이서설치 ○ 이도조정","2016-12-10 08:00","2016-12-11 18:00","2016-12-10T08:00:00","2016-12-11T18:00:00","매일",null,null,null,201609290040]
[70,"경기","평택","포승청북#2 T/L","포승-청북 등 2개T/L 상간스페이서 설치공사","○ 154kV 청북-평택#1T/L, 포승-청북#2T/L 3경간 상간스페이서설치 ○ 이도조정","2016-12-10 08:00","2016-12-11 18:00","2016-12-10T08:00:00","2016-12-11T18:00:00","매일",null,null,null,201609290041]
[71,"경기","군포","신안산남안산#2 T/L","신안산SS 감시제어반 교체 공사","신안산SS 감시제어반 교체 공사 -신안산 남안산#2 T/L 감시, 조작회로 이설","2016-12-05 08:00","2016-12-07 18:00","2016-12-05T08:00:00","2016-12-07T18:00:00","연속",null,null,null,201610100075]
[72,"경기","평택","서운안성#1 T/L","154kV 서운-안성T/L OPGW 증설","No.24~29 OPGW 증설(6기)","2016-12-01 08:00","2016-12-07 18:00","2016-12-01T08:00:00","2016-12-07T18:00:00","연속",null,null,null,201610100157]
[73,"경기","평택","서운삼죽 T/L","154kV 서운-안성T/L OPGW 증설","No.39~43 OPGW 증설(5기)","2016-12-03 08:00","2016-12-04 18:00","취소","취소","연속",null,null,null,201610100176]
[74,"경기","군포","서서울소래 T/L","154kV 서서울-소래T/L 37호 안전이격확보공사","154kV 서서울-소래T/L 37호 지지물 교체 : 관형주(A2-26)신설, 철탑(A2-15)철거","2016-12-10 07:00","2016-12-11 18:00","2016-12-10T07:00:00","2016-12-11T18:00:00","연속",null,null,null,201610110182]
[75,"경기","군포","서서울서안양 T/L","154kV 서서울-소래T/L 37호 안전이격확보공사","154kV 서서울-소래T/L 37호 지지물 교체 : 관형주(A2-26)신설, 철탑(A2-15)철거","2016-12-10 07:00","2016-12-11 18:00","2016-12-10T07:00:00","2016-12-11T18:00:00","연속",null,null,null,201610110183]
[76,"경기","직할","조암구문천#1 T/L","154kV 구문천S/S #4M.Tr 증설공사","구문천S/S #4M.Tr 증설공사관련 무부하가압","2016-12-16 09:00","2016-12-18 18:00","2016-12-16T09:00:00","2016-12-18T18:00:00","연속",null,null,null,201610120009]
[77,"경기","평택","삼죽만승 T/L","154kV 삼죽-만승T/L 피뢰기 및 상간스페이서 설치공사","- 송전용피뢰기 39기 설치 - 상간스페이서 3경간 설치","2016-12-12 08:00","2016-12-16 18:00","2016-12-12T08:00:00","2016-12-14T18:00:00","매일",null,null,null,201610130081]
[78,"경기","평택","송탄오성CC#1 T/L","154kV 송탄-소사벌T/L 피뢰기설치공사(안전확보)","- 송전용피뢰기 8기 설치(4회선병가구간 안전확보 휴전)","2016-12-17 09:00","2016-12-17 18:00","취소","취소","당일",null,null,null,201610130082]
[79,"경기","군포","관양평촌#2 T/L","154kV 관양S/S #3M.Tr 증설공사","-154/23kV M.Tr 1Bank 증설 -170kV GIS 1CCT 증설 -수냉각장치 1식 설치 -25.8kV GIS 4CCT 증설 -변압기 보호반 1식 설치 -제어케이블 1식 설치 -기타부대공사 1식","2016-12-13 13:00","2016-12-15 13:00","2016-12-13T13:00:00","2016-12-15T13:00:00","연속",null,null,null,201610130096]
[80,"강원","태백","태백삼척GP#2T/L","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","태백-삼척GP#2T/L GIS LCP 내부 단자대 불량 보수 및 LA점검","2016-12-22 10:00","2016-12-22 18:00","2016-12-22 10:00","2016-12-22 18:00","당일",null,null,null,201610120145]
[81,"강원","태백","태백삼척GP#1T/L","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","태백-삼척GP#1T/L GIS LCP 내부 단자대 불량 보수","2016-12-21 10:00","2016-12-21 18:00","2016-12-21 10:00","2016-12-21 18:00","당일",null,null,null,201610120188]
[82,"강원","태백","태백고한 T/L","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","태백고한T/L 인출측 피뢰기 교체","2016-12-08 10:00","2016-12-08 18:00","2016-12-08 10:00","2016-12-08 18:00","당일",null,null,null,201610120189]
[83,"강원","태백","태백영월 T/L","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","태백영월T/L 인출측 피뢰기 교체","2016-12-09 10:00","2016-12-09 18:00","2016-12-09 10:00","2016-12-09 18:00","당일",null,null,null,201610120190]
[84,"강원","태백","고한영월 T/L","2016~2017년 태백전력지사 변전정비 협력회사 총액공사","고한영월T/L 인출측 벽면 물받이 잡초제거","2016-12-05 10:00","2016-12-05 18:00","2016-12-05 10:00","2016-12-05 18:00","당일",null,null,null,201610120193]
[85,"강원","직할","춘천소양강HP T/L","2016~2017년 강원직할 송전정비 협력회사 총액공사","154kV 춘천분기T/L No.19~23간 전선접속개소 해소","2016-12-05 09:00","2016-12-06 18:00","2016-12-05 09:00","2016-12-06 18:00","연속",null,null,null,201610130004]
[86,"강원","직할","남춘천춘천 T/L","2016~2017년 강원직할 송전정비 협력회사 총액공사","154kV 춘천분기T/L No.19~23간 전선접속개소 해소","2016-12-07 09:00","2016-12-08 18:00","2016-12-07 09:00","2016-12-08 18:00","연속",null,null,null,201610130006]
[87,"강원","강릉","영동T/P 154kV #1 BUS","2016년 변전협력회사 총액공사","영동화력S/Y 탈황측 BUS PT 점검","2016-12-05 09:00","2016-12-05 14:00","2016-12-05 09:00","2016-12-05 14:00","당일",null,null,null,201610250041]
[88,"강원","강릉","영동T/P 154kV #2 BUS","2016년 변전협력회사 총액공사","영동화력S/Y 탈황측 BUS PT 점검","2016-12-05 14:00","2016-12-05 18:00","2016-12-05 14:00","2016-12-05 18:00","당일",null,null,null,201610250042]
[89,"강원","강릉","신양양_양양#1 T/L","2016~17년 송전정비 협력회사 총액공사","○상간스페이서 보수작업","2016-12-05 09:00","2016-12-08 18:00","2016-12-05 09:00","2016-12-08 18:00","매일",null,null,null,201610250044]
[90,"충북","충주","만승S/S 154kV #1 BUS TIE CB","154kV 개폐장치 정밀점검","154kV 개폐장치 정밀점검","2016-12-05 09:00","2016-12-07 18:00","2016-12-05 09:00","2016-12-07 18:00","연속",null,null,null,201609090135]
[91,"충북","직할","신제천왕암#1 T/L","345kV 신제천S/S GIS화 공사","신제천-왕암#1T/L 옥외철구→GIS 이설","2016-12-12 08:00","2016-12-16 18:00","2016-12-12 08:00","2016-12-16 18:00","연속",null,null,null,201610130166]
[92,"충북","청주","청주대청HP T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","송전용 피뢰기설치(청주-대청HP) No.18~88(71기)","2016-12-21 09:00","2016-12-22 18:00","2016-12-21 09:00","2016-12-22 18:00","매일",null,null,null,201610170062]
[93,"충북","청주","청원부강#2 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","4회선 병가선로 안전상 휴전(이격거리 확보)","2016-12-18 08:00","2016-12-18 19:00","2016-12-18 08:00","2016-12-18 19:00","당일",null,null,null,201610170072]
[94,"충북","청주","청원부강#1 T/L","16-17년 송전정비 협력회사 총액공사(청주전력)","불량애자 교체 No.20, 26 (20EA)","2016-12-19 08:00","2016-12-19 19:00","2016-12-19 08:00","2016-12-19 19:00","당일",null,null,null,201610170073]
[95,"충북","청주","청원신탄진 T/L","16-17년 청주송전협력회사 총액공사(피뢰기설치)","피뢰기설치 No.1~17호 (17기, 51set)","2016-12-20 08:00","2016-12-20 18:00","2016-12-20 08:00","2016-12-20 18:00","당일",null,null,null,201610170074]
[96,"충북","직할","풍동음성#2 T/L","음성S/S 풍동음성#2T/L CVT 대체","풍동음성#2T/L CVT 대체 작업","2016-12-01 09:00","2016-12-01 18:00","2016-12-01 09:00","2016-12-01 18:00","당일",null,null,null,201610180203]
[97,"대전충남","아산","인주탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-12-03 07:00","2016-12-04 19:00","2016-12-03 07:00","2016-12-04 19:00","매일",null,null,null,201609070098]
[98,"대전충남","아산","인주탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-12-10 07:00","2016-12-11 19:00","2016-12-10 07:00","2016-12-11 19:00","매일",null,null,null,201609070105]
[99,"대전충남","아산","인주탕정#2 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-12-10 07:00","2016-12-11 19:00","2016-12-10 07:00","2016-12-11 19:00","매일",null,null,null,201609070109]
[100,"대전충남","아산","인주탕정#2 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L, 345kV 아산-화성T/L 병가구간 가선작업 신설18호~기설28호 구간 전선 가선작업 기설18호~기설28호 구간 전선 철거작업 발받침 철탑 4기 및 보호망 2개소 설치(154kV 인주-탕정T/L 31~32호)","2016-12-03 07:00","2016-12-04 19:00","2016-12-03 07:00","2016-12-04 19:00","매일",null,null,null,201609070112]
[101,"대전충남","세종","조치원전의#1 T/L","[변전] 세종P/O 협력회사 총액공사","○ GIS보통점검(15년 미시행분)","2016-12-04 09:00","2016-12-04 18:00","2016-12-04 09:00","2016-12-04 18:00","당일",null,null,null,201610070295]
[102,"대전충남","아산","온양풍세#2 T/L","154kV 온양-풍세#2T/L 정밀점검","정밀점검 구간 : 온양S/S ~ 풍세S/S 31기 9.113kM 투입인력 : 3개조 9명투입(3명 지상감시자)","2016-12-08 08:00","2016-12-09 18:00","2016-12-08 08:00","2016-12-09 18:00","당일",null,null,null,201610130059]
[103,"대전충남","아산","풍세장재#1 T/L","154kV 온양-풍세#2T/L 정밀점검 관련 4회선 구간 안전이격","정밀점검 구간 : 온양S/S ~ 풍세S/S 31기 9.113kM 투입인력 : 3개조 9명투입(3명 지상감시자)","2016-12-09 08:00","2016-12-09 18:00","2016-12-09 08:00","2016-12-09 18:00","당일",null,null,null,201610130068]
[104,"전북","김제","섬진강H/P 154kV #1 BUS TIE CB","섬진강H/P 154kV #1 BUS TIE CB","전담운영 대비 SCADA 제어회로 구성","2016-12-05 09:00","2016-12-10 18:00","취소","취소","연속",null,null,null,201607180132,"○"]
[105,"전북","김제","섬진강H/P #2 M.Tr 1차 CB","섬진강H/P 154kV #1 BUS TIE CB","전담운영 대비 SCADA 제어회로 구성","2016-12-14 09:00","2016-12-15 18:00","취소","취소","연속",null,null,null,201607180133]
[106,"전북","김제","섬진강H/P #1 M.Tr 1차 CB","섬진강H/P #1 M.Tr 1차 CB","전담운영 대비 SCADA 제어회로 구성","2016-12-12 09:00","2016-12-13 18:00","취소","취소","연속",null,null,null,201607180134,"○"]
[107,"전북","김제","정공정주#1 T/L","정공-정주#1T/L LA","정공S/S 정공-정주#1T/L LA 보통점검","2016-12-05 09:00","2016-12-05 18:00","2016-12-03 09:00","2016-12-03 18:00","당일",null,null,null,201608290006]
[108,"전북","김제","정공정주#2 T/L","정공-정주#2T/L LA","정공S/S 정공-정주#2T/L LA 보통점검","2016-12-01 09:00","2016-12-01 18:00","취소","취소","당일",null,null,null,201608290007]
[109,"전북","군산","팔봉두마#2 T/L","군산신김제#1,2 T/L 전선접속개소교체공사","○ 전선교체구간 안전이격거리 확보 - 군산신김제#1,2 T/L No.90 ~ 93 간 직하에 154㎸ 팔봉-두마T/L 횡단","2016-12-07 07:00","2016-12-14 18:00","2016-12-01 07:00","2016-12-08 18:00","연속",null,null,null,201609190148]
[110,"전북","군산","팔봉두마#1 T/L","군산신김제#1,2 T/L 전선접속개소교체공사","○ 전선교체구간 안전이격거리 확보 - 군산신김제#1,2 T/L No.90 ~ 93 간 직하에 154㎸ 팔봉-두마T/L 횡단","2016-12-07 07:00","2016-12-14 18:00","2016-12-01 07:00","2016-12-08 18:00","연속",null,null,null,201609190151]
[111,"전북","군산","동군산장항#1 T/L","군산P/O LA, CVT 점검공사","동군산S/S 154kV 동군산-장항#1T/L CVT(A상) 점검","2016-12-09 09:00","2016-12-09 18:00","2016-12-09 09:00","2016-12-09 18:00","당일",null,null,null,201609300211]
[112,"전북","군산","이리백산#2 T/L","154kV 이리-백산#2T/L (C/H설치공사)","케이블헤드 조립, 긴선 및 기설전선 철거","2016-12-10 08:00","2016-12-18 18:00","2016-12-10 08:00","2016-12-18 18:00","연속",null,null,null,201610130129]
[113,"전북","군산","이리전주#2 T/L","154kV 이리-전주#2T/L (C/H설치공사)","케이블헤드 조립, 긴선 및 기설전선 철거","2016-12-10 08:00","2016-12-18 18:00","2016-12-10 08:00","2016-12-18 18:00","연속",null,null,null,201610130130]
[114,"전북","군산","군산서군산#1 T/L","군산서군산#1 T/L 점퍼지지애자교체","점퍼지지애자교체 : 3기","2016-12-01 07:00","2016-12-01 18:00","2016-12-01 07:00","2016-12-01 18:00","당일",null,null,null,201610140068]
[115,"전북","군산","군산서군산#2 T/L","군산서군산#2 T/L 점퍼지지애자교체","점퍼지지애자교체 : 3기","2016-12-02 07:00","2016-12-02 18:00","2016-12-02 07:00","2016-12-02 18:00","당일",null,null,null,201610140070]
[116,"전북","김제","신김제남전주#2 T/L","154kV 임실-남전주#1T/L 피뢰기 설치공사 안전거리 확보","154kV 임실-남전주#1T/L 피뢰기 설치 No.1~105","2016-12-05 09:00","2016-12-07 18:00","취소","취소","매일",null,null,null,201610140102]
[117,"전북","김제","신김제동전주#1 T/L","154kV 임실-남전주#1T/L 피뢰기 설치공사 안전거리 확보","154kV 임실-남전주#1T/L 피뢰기 설치 No.1~105","2016-12-08 09:00","2016-12-09 18:00","2016-12-09 09:00","2016-12-10 18:00","매일",null,null,null,201610140105]
[118,"전북","김제","정공섬진강수력 T/L","154kV 정공-섬진강T/L 송전선로 정밀점검","154kV 담양(정공-섬진강)T/L 정밀점검 No.117~126","2016-12-12 09:00","2016-12-13 18:00","2016-12-12 09:00","2016-12-13 18:00","매일",null,null,null,201610140110,"○"]
[119,"전북","김제","김제섬진강HP T/L","154kV 담양T/L 65호 안전이격거리 확보공사","65호 인클로징 공법 이용한 철탑 철거, 설치","2016-12-05 07:00","2016-12-07 18:00","2016-12-05 07:00","2016-12-07 18:00","연속",null,null,null,201610160012]
[120,"전북","김제","담양김제 T/L","154kV 담양T/L 65호 안전이격거리 확보공사","65호 인클로징 공법 이용한 철탑 철거, 설치","2016-12-08 07:00","2016-12-10 18:00","2016-12-08 07:00","2016-12-10 18:00","연속",null,null,null,201610160014]
[121,"전북","군산","군공군산CC#1 T/L","154kV 군공-군산복합T/L 지장 지중선로 이설공사","군장대교 건설관련 지장 송전설로 이설","2016-12-02 09:00","2016-12-23 18:00","2016-12-02 09:00","2016-12-23 18:00","연속",null,null,null,201610170202]
[122,"전북","군산","군공군산CC#2 T/L","154kV 군공-군산복합T/L 지장 지중선로 이설공사","군장대교 건설관련 지장 송전설로 이설","2016-12-26 08:00","2017-02-05 18:00","2016-12-26 08:00","2017-02-05 18:00","연속",null,null,null,201610170203]
[123,"전북","김제","신김제정공#2 T/L","154kV 신김제-정공#2T/L 항공장애표시구 설치공사","항공장애표시구 설치","2016-12-05 07:00","2016-12-05 18:00","2016-12-05 07:00","2016-12-05 18:00","당일",null,null,null,201610170222]
[124,"전북","군산","군산이리#2 T/L","154kV 군산-이리#2T/L (C/H설치공사)","인하선 설치 및 지중가압","2016-12-25 08:00","2016-12-26 18:00","2016-12-25 08:00","2016-12-26 18:00","연속",null,null,null,201610180122]
[125,"전북","군산","군산이리#1 T/L","154kV 군산-이리#1T/L (C/H설치공사)","인하선 설치 및 지중가압(#2T/L 가압불가시 작업예정)","2016-12-27 08:00","2016-12-28 18:00","2016-12-27 08:00","2016-12-28 18:00","연속",null,null,null,201610180123]
[126,"전북","김제","신김제S/S 65-66-0 SEC CB","신김제S/S 65-66-0 SEC CB","#60,65 BUS모선보호반 교체","2016-12-12 09:00","2016-12-16 18:00","취소","취소","연속",null,null,null,201610200004]
[127,"전북","김제","신김제S/S 60-61-0 SEC CB","신김제S/S 60-61-0 SEC CB","#60,65 BUS모선보호반 교체","2016-12-12 09:00","2016-12-16 18:00","취소","취소","연속",null,null,null,201610200006]
[128,"광주전남","순천","여천호남TP#1 T/L","154kV 여천-호남TP#1T/L(호남T/P GIS 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - GIS 보통점검","2016-12-20 10:00","2016-12-20 18:00","2016-12-20 10:00","2016-12-20 18:00","당일",null,null,null,201610050128]
[129,"광주전남","광주","신광주S/S 신광주-곡성#2T/L CB","신광주S/S 154kV취약설비 GIS설치 공사","신설 GIS 19 CCT 초기가압 시험","2016-12-12 08:00","2016-12-15 18:00","2016-12-12 08:00","2016-12-15 18:00","연속",null,null,null,201610060127]
[130,"광주전남","순천","여수산단개폐소 154kV #2 BUS TIE GIS","154kV 전력설비 보호반(새롬프로텍) 성능개선","154kV 전력설비 보호반(새롬프로텍) 성능개선","2016-12-06 09:00","2016-12-06 18:00","2016-12-03 09:00","2016-12-03 18:00","당일",null,null,null,201610070409]
[131,"광주전남","순천","여수산단개폐소 60-61 SEC GIS","154kV 전력설비 보호반(새롬프로텍) 성능개선","154kV 전력설비 보호반(새롬프로텍) 성능개선","2016-12-06 09:00","2016-12-06 18:00","2016-12-03 09:00","2016-12-03 18:00","당일",null,null,null,201610070410]
[132,"광주전남","순천","여수산단개폐소 65-66 SEC GIS","154kV 전력설비 보호반(새롬프로텍) 성능개선","154kV 전력설비 보호반(새롬프로텍) 성능개선","2016-12-06 09:00","2016-12-06 18:00","2016-12-03 09:00","2016-12-03 18:00","당일",null,null,null,201610070411]
[133,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP-여수TP#1T/L(송전선로 정밀점검)","송전선로 정밀점검 : 1~14호, 16기","2016-12-09 09:00","2016-12-09 18:00","2016-12-05 09:00","2016-12-07 18:00","매일",null,null,null,201610100051]
[134,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP-여수TP#2T/L(송전선로 정밀점검)","송전선로 정밀점검 : 1~14호, 16기","2016-12-09 09:00","2016-12-09 18:00","2016-12-08 09:00","2016-12-10 18:00","매일",null,null,null,201610100052]
[135,"광주전남","순천","여천여수#1 T/L","154kV 여천-여수#1T/L(점퍼지지애가 교체)","점퍼지지애자 교체 : 12호(1기)","2016-12-09 09:00","2016-12-09 18:00","2016-12-10 09:00","2016-12-10 18:00","당일",null,null,null,201610100057]
[136,"광주전남","순천","여천호남TP#2 T/L","154kV 여천-호남TP#2T/L(여천-여수#1T/L 안전이격 확보)","여천-여수#1T/L 휴전관련 안전이격 확보","2016-12-12 13:00","2016-12-12 18:00","2016-12-12 13:00","2016-12-12 18:00","당일",null,null,null,201610100061]
[137,"광주전남","광주","북광주일곡#1 T/L","북광주-일곡#1T/L(광주 장기 미동작차단기 점검)","북광주S/S 북광주-일곡#1T/L GIS CB 장기 미동작차단기 점검","2016-12-13 09:00","2016-12-13 13:00","2016-12-13 09:00","2016-12-13 13:00","당일",null,null,null,201610110121]
[138,"광주전남","광주","북광주일곡#2 T/L","북광주-일곡#2T/L(광주 장기 미동작차단기 점검)","북광주S/S 북광주-일곡#2T/L GIS CB 장기 미동작차단기 점검","2016-12-13 13:00","2016-12-13 18:00","2016-12-13 13:00","2016-12-13 18:00","당일",null,null,null,201610110122]
[139,"광주전남","광주","신광주장성#2 T/L","신광주-장성#2T/L(광주 장기 미동작차단기 점검)","장성S/S 신광주-장성#2T/L GIS CB 장기 미동작차단기 점검","2016-12-14 09:00","2016-12-14 13:00","2016-12-17 09:00","2016-12-17 13:00","당일",null,null,null,201610110123]
[140,"광주전남","광주","계림승주#1(서남권상수도T분기) T/L","154kV 계림-승주T/L 지상고확보공사","철탑교체 14기 전선교체 4.656km","2016-12-07 07:00","2016-12-17 18:00","2016-12-07 07:00","2016-12-17 18:00","연속",null,null,null,201610110133]
[141,"광주전남","광주","계림승주#2(서남권상수도T분기) T/L","154kV 계림-승주T/L 지상고확보공사","철탑교체 14기 전선교체 4.656km","2016-12-18 07:00","2016-12-22 18:00","2016-12-18 07:00","2016-12-22 18:00","연속",null,null,null,201610110134]
[142,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주#1T/L(순천S/S GCB 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 순천S/S GCB 보통점검","2016-12-27 09:00","2016-12-27 18:00","2016-12-10 09:00","2016-12-10 18:00","당일",null,null,null,201610140069]
[143,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주#2T/L(순천S/S GCB 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 순천S/S GCB 보통점검","2016-12-28 09:00","2016-12-28 18:00","2016-12-11 09:00","2016-12-11 18:00","당일",null,null,null,201610140071]
[144,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌#1T/L(순천S/S GCB 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 순천S/S GCB 보통점검","2016-12-29 09:00","2016-12-29 18:00","2016-12-17 09:00","2016-12-17 18:00","당일",null,null,null,201610140072]
[145,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌#2T/L(순천S/S GCB 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 순천S/S GCB 보통점검","2016-12-30 09:00","2016-12-30 18:00","2016-12-18 09:00","2016-12-18 18:00","당일",null,null,null,201610140073]
[146,"광주전남","순천","순천S/S 154kV #1 BUS TIE CB","154kV 순천S/S #1BUS-TIE(GCB 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 순천S/S GCB 보통점검","2016-12-26 09:00","2016-12-26 18:00","2016-12-26 09:00","2016-12-26 18:00","당일",null,null,null,201610140074]
[147,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천#1T/L(여천측 LA 보통점검)","2016~17년 순천전력지사 변전협력회사 총액공사 - 여천S/S LA 보통점검","2016-12-07 10:00","2016-12-07 18:00","2016-12-07 10:00","2016-12-07 18:00","당일",null,null,null,201610190020]
[148,"광주전남","순천","광양순천#1 T/L","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2016-12-01 09:00","2016-12-14 18:00","2016-12-01 09:00","2016-12-14 18:00","연속",null,null,null,201610210176]
[149,"광주전남","순천","순천승주#2 T/L","154kV 순천,광양,율촌T/L 시가지 지중화사업","가. 154kV 순천-승주T/L : XLPE 2,000㎟ 2회선 1.9㎞ 나. 154kV 순천-광양T/L : XLPE 1,200㎟ 2회선(D) 2.8㎞ 다. 154kV 순천-율촌T/L : XLPE 1,200㎟ 2회선 0.1㎞","2016-12-19 09:00","2016-12-22 18:00","2016-12-24 09:00","2016-12-24 18:00","연속",null,null,null,201610210177]
[150,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌#1T/L 보호배전반 대체공사","- 154kV 율촌S/S 순천-율촌#1T/L 보호배전반 1면 대체 - 154kV 순천S/S 순천-율촌#1T/L 보호배전반 1면 신설","2016-12-15 09:00","2016-12-17 18:00","2016-12-25 09:00","2016-12-25 18:00","연속",null,null,null,201610210178]
[151,"대구경북","영주","점촌단양 T/L","154kV단양T/L 노후취약지지물 교체공사","154kV단양T/L 노후취약지지물 교체공사","2016-12-03 07:00","2016-12-04 18:00","2016-12-03 07:00","2016-12-04 18:00","연속",null,null,null,201607080225]
[152,"대구경북","포항","영일양북 T/L","154kV 상정-양북T/L 건설공사","목적 : 포항 블루밸리산업단지 전력수요 대비 및 상정S/S 단일계통 해소 구간 : 기설 154kV 영일-양북T/L No.29,31~기설 154kV 상정S/S 개요 : 철탑 39기, 14.725km","2016-12-05 08:00","2016-12-19 18:00","2016-12-05 08:00","2016-12-19 18:00","연속",null,null,null,201609010050]
[153,"대구경북","포항","영일입실 T/L","154kV 상정-양북T/L 건설공사","목적 : 포항 블루밸리산업단지 전력수요 대비 및 상정S/S 단일계통 해소 구간 : 기설 154kV 영일-양북T/L No.29,31~기설 154kV 상정S/S 개요 : 철탑 39기, 14.725km","2016-12-05 08:00","2016-12-19 18:00","2016-12-05 08:00","2016-12-19 18:00","연속",null,null,null,201609010051]
[154,"대구경북","직할","범물남대구#2 T/L","남대구S/S 모선보호반 교체","모선보호반 교체","2016-12-08 07:00","2016-12-08 11:00","취소","취소","당일",null,null,null,201609070189]
[155,"대구경북","직할","범물남대구#1 T/L","남대구S/S 모선보호반 교체","모선보호반 교체","2016-12-08 11:00","2016-12-08 11:30","취소","취소","당일",null,null,null,201609070190]
[156,"대구경북","경산","신경산진량 T/L","신경산S/S 170kV 장기사용 GIS 대체공사","신경산-진량T/L GIS 대체시 진량S/S 장기간 RADIAL 운전관련 계통보강사전작업 환원","2016-12-13 09:00","2016-12-14 18:00","2016-12-13 09:00","2016-12-14 18:00","연속",null,null,null,201609170013]
[157,"대구경북","경산","신경산노변 T/L","154kV 신경산-노변T/L 취약송전철탑 교체공사","- 154kV 신경산-노변T/L 41,43호(2기) 교체","2016-12-15 08:00","2016-12-18 18:00","2016-12-15 08:00","2016-12-18 18:00","연속",null,null,null,201610050001]
[158,"대구경북","경산","진량노변 T/L","154kV 신경산-노변T/L 취약송전철탑 교체공사","- 154kV 신경산-노변T/L 41,43호(2기) 교체","2016-12-15 08:00","2016-12-18 18:00","2016-12-15 08:00","2016-12-18 18:00","연속",null,null,null,201610050002]
[159,"대구경북","직할","노변효목#1 T/L","효목S/S 송전선로 보호반 보통점검","송전선로 보호반 보통점검","2016-12-01 14:00","2016-12-01 18:00","취소","취소","당일",null,null,null,201610070308]
[160,"대구경북","경산","대구범물#1 T/L","17년 직할 가공송전협력회사 총액공사","- 대구-범물T/L 불량 압축인류크램프 교체(13개소)","2016-12-19 08:00","2016-12-21 18:00","2016-12-19 08:00","2016-12-21 18:00","연속",null,null,null,201610180136]
[161,"대구경북","경산","대구범물#2 T/L","17년 직할 가공송전협력회사 총액공사","- 대구-범물T/L 불량 압축인류크램프 교체(9소)","2016-12-22 08:00","2016-12-23 18:00","2016-12-22 08:00","2016-12-23 18:00","연속",null,null,null,201610180139]
[162,"대구경북","포항","건천천북#2 T/L","154kV 건천-천북#2T/L 피뢰기 설치","○작업구간 : No.21~96","2016-12-01 08:00","2016-12-08 18:00","취소","취소","연속",null,null,null,201610240058]
[163,"대구경북","칠곡","구미광평#2 T/L","광평S/S 구미-광평#2T/L GIS 정밀점검","GIS 정밀점검","2016-12-04 09:30","2016-12-06 18:00","2016-12-04 09:30","2016-12-06 18:00","연속",null,null,null,201611020029]
[164,"대구경북","칠곡","남구미광평#1 T/L","광평S/S 154kV #1Sh.C GIS 정밀점검","GIS 정밀점검","2016-12-02 14:00","2016-12-03 18:00","2016-12-02 14:00","2016-12-03 18:00","연속",null,null,null,201611020028]
[165,"부산울산","동부산","노포정관#2 T/L","154kV 노포-정관T/L 지장철탑이설공사","지장철탑이설, 노포-정관T/L 8호, 작업구간 6~9호","2016-12-10 09:00","2016-12-12 18:00","2016-12-26 09:00","2016-12-28 18:00","연속",null,null,null,201609090108]
[166,"부산울산","북부산","매리호포#2 T/L","16년 가공송전 협력업체 공사","13호 앵카쇄클 금구류 교체","2016-12-03 09:00","2016-12-03 18:00","2016-12-03 09:00","2016-12-03 18:00","연속",null,null,null,201609260086]
[167,"부산울산","울산","용연처용#2 T/L","154kV 용연-울산TP #2T/L 송전선로용 피뢰기 설치공사","ㅁ 154kV 용연-울산TP #2T/L 피뢰기 설치작업 관련 이격거리 확보 [No.9, 9-1호]","2016-12-10 08:00","2016-12-10 13:00","2016-12-10 08:00","2016-12-10 13:00","당일",null,null,null,201610040036]
[168,"부산울산","울산","용연울산TP#2 T/L","154kV 용연-울산TP #2T/L 송전선로용 피뢰기 설치공사","ㅁ 피뢰기 설치 ㅇ 구간 : 154kV 용연-울산TP #2T/L No.9~9.2호(3기)","2016-12-10 08:00","2016-12-10 18:00","2016-12-10 08:00","2016-12-10 18:00","당일",null,null,null,201610040037]
[169,"부산울산","직할","수정범일#2 T/L","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S #2M.Tr 1차 GIS 정밀점검 2DS 시험가압선로","2016-12-01 18:00","2016-12-01 19:00","2016-12-01 18:00","2016-12-01 19:00","당일",null,null,null,201610070052]
[170,"부산울산","직할","수정범일#1 T/L","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S #2M.Tr 1차 GIS 정밀점검 1DS,CB 시험가압선로","2016-12-03 17:00","2016-12-03 18:00","2016-12-03 17:00","2016-12-03 18:00","당일",null,null,null,201610070053]
[171,"부산울산","직할","수정범일#2 T/L","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S 수정-범일#2T/L GIS 정밀점검","2016-12-05 08:00","2016-12-07 18:00","2016-12-05 08:00","2016-12-07 18:00","연속",null,null,null,201610070054]
[172,"부산울산","직할","수정범일#1 T/L","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S 수정-범일#1T/L GIS 정밀점검","2016-12-19 08:00","2016-12-21 18:00","2016-12-19 08:00","2016-12-21 18:00","연속",null,null,null,201610070056]
[173,"부산울산","직할","범일서면#1 T/L","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S 범일-서면#1T/L GIS 정밀점검","2016-12-12 08:00","2016-12-14 18:00","2016-12-11 08:00","2016-12-14 18:00","연속",null,null,null,201610070057]
[174,"부산울산","직할","범일서면#2 T/L","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S 범일-서면#2T/L GIS 정밀점검","2016-12-15 08:00","2016-12-17 18:00","2016-12-15 08:00","2016-12-17 18:00","연속",null,null,null,201610070058]
[175,"부산울산","직할","범일S/S 154kV #1 BUS TIE CB","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S 6100 BUS-TIE GIS 정밀점검","2016-12-08 08:00","2016-12-10 18:00","2016-12-08 08:00","2016-12-10 18:00","연속",null,null,null,201610070060]
[176,"부산울산","직할","수정범일#1 T/L","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S 6100 BUS-TIE GIS 정밀점검 1DS 시험가압선로","2016-12-08 18:00","2016-12-08 19:00","2016-12-08 18:00","2016-12-08 19:00","당일",null,null,null,201610070061]
[177,"부산울산","직할","수정범일#2 T/L","16년도 직할 하반기 170kV GIS 정밀점검","범일S/S 6100 BUS-TIE GIS 정밀점검 2DS,CB 시험가압선로","2016-12-10 17:00","2016-12-10 18:00","2016-12-10 17:00","2016-12-10 18:00","당일",null,null,null,201610070062]
[178,"부산울산","직할","서부산부산 T/L","서부산-부산T/L 보호배전반 대체공사","서부산-부산T/L 보호배전반 대체공사","2016-12-07 09:00","2016-12-09 18:00","2016-12-07 09:00","2016-12-09 18:00","연속",null,null,null,201610070095]
[179,"부산울산","울산","울산울산TP#2 T/L","울산S/S ESS설치공사","▢ 개폐장치 설치공사 ❍ 170kV 50kA 케이블헤드 × 1Bay 개조 ❍ 170kV 50kA 케이블헤드+Bushing × 1Bay 설치 ❍ 25.8kV 25kA GIS × 1CCT 설치 ❍ 25.8kV 25kA SIS(친환경개폐장치) × 11CCT 설치 ▢ M.Tr 설치공사 : 154kV 45/60MVA × 1BANK 설치","2016-12-12 13:00","2016-12-14 13:00","2016-12-12 13:00","2016-12-14 13:00","연속",null,null,null,201610070138]
[180,"부산울산","울산","신울산울산#2 T/L","2016년 가공송전 순시점검 위탁공사","송전선로 정밀점검 : 신울산S/S~No.17(C/H) 병행: 5호 보강철탑 현장실측(고명진)","2016-12-07 09:00","2016-12-08 18:00","2016-12-07 09:00","2016-12-08 18:00","연속",null,null,null,201610100030]
[181,"부산울산","북부산","북부산삼랑진PP#2 T/L","2016년도 가공송전설비 위탁업체 공사","154kV 북부산-삼랑진PP#2T/L 정밀점검","2016-12-01 08:00","2016-12-02 18:00","2016-12-01 08:00","2016-12-02 18:00","연속",null,null,null,201610100148]
[182,"부산울산","울산","신온산온산#1 T/L","2016-17년 울산전력지사 변전협력회사 총액공사","신온산 154kV 신온산-온산#1T/L GIS 보통점검","2016-12-06 09:00","2016-12-06 18:00","2016-12-06 09:00","2016-12-06 18:00","당일",null,null,null,201610100333]
[183,"부산울산","울산","울산T/P 154kV #60 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","울산화력 154kV #60BUS 전담운영공사 - 보호/감시용 모선전압 제어케이블 철거","2016-12-01 09:00","2016-12-01 12:00","2016-12-01 09:00","2016-12-01 12:00","당일",null,null,null,201610100334,"○"]
[184,"부산울산","울산","울산T/P 154kV #65 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","울산화력 154kV #65BUS 전담운영공사 - 보호/감시용 모선전압 제어케이블 철거","2016-12-01 13:00","2016-12-01 16:00","2016-12-01 13:00","2016-12-01 16:00","당일",null,null,null,201610100335,"○"]
[185,"부산울산","울산","울산T/P 154kV #61 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","울산화력 154kV #61BUS 전담운영공사 - 보호/감시용 모선전압 제어케이블 철거","2016-12-02 09:00","2016-12-02 12:00","2016-12-02 09:00","2016-12-02 12:00","당일",null,null,null,201610100337]
[186,"부산울산","울산","울산T/P 154kV #66 BUS","2016-17년 울산전력지사 변전협력회사 총액공사","울산화력 154kV #66BUS 전담운영공사 - 보호/감시용 모선전압 제어케이블 철거","2016-12-02 13:00","2016-12-02 16:00","2016-12-02 13:00","2016-12-02 16:00","당일",null,null,null,201610100338,"○"]
[187,"부산울산","울산","신울산울산#1 T/L","보강철탑 현장실측 용역","154kV 신울산-울산T/L No.5 현장실측 용역","2016-12-06 09:00","2016-12-06 18:00","2016-12-06 09:00","2016-12-06 18:00","당일",null,null,null,201610100399,"○"]
[188,"부산울산","직할","신대연S/S 154kV #1 BUS","154kV 신대연-용호T/L SW 증설공사","154kV 신대연-용호T/L Angle측정","2016-12-09 10:00","2016-12-09 11:00","2016-12-09 10:00","2016-12-09 11:00","당일",null,null,null,201610130075]
[189,"부산울산","직할","신대연S/S 154kV #2 BUS","154kV 신대연-용호T/L SW 증설공사","154kV 신대연-용호T/L Angle측정 및 시험가압","2016-12-09 11:00","2016-12-11 11:00","2016-12-09 11:00","2016-12-11 11:00","연속",null,null,null,201610130077]
[190,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창T/L 지장철탑이설공사","구간:8-12호, 17.1-20호 철탑교체:9,10,11,18호","2016-12-19 08:00","2016-12-22 18:00","2016-12-19 08:00","2016-12-22 18:00","연속",null,null,null,201610170048]
[191,"부산울산","동부산","웅촌서창#2 T/L","154kV 웅촌-서창T/L 지장철탑이설공사","구간:8-12호, 17.1-20호 철탑교체:9,10,11,18호","2016-12-23 08:00","2016-12-28 18:00","2016-12-23 08:00","2016-12-28 18:00","연속",null,null,null,201610170050]
[192,"부산울산","동부산","웅촌서창#1 T/L","154kV 웅촌-서창T/L 지장철탑이설공사","구간:8-12호, 17.1-20호 철탑교체:9,10,11,18호","2016-12-29 08:00","2016-12-31 18:00","2016-12-29 08:00","2016-12-31 18:00","연속",null,null,null,201610170051]
[193,"경남","통영","삼천포사천#2 T/L","154kV 삼천포-사천#2T/L 전력선 교체공사","154kV 삼천포-사천#2T/L 전력선 교체공사 - 공사구간 : No.15~20, 41~45","2016-12-01 07:00","2016-12-08 18:00","2016-12-01 07:00","2016-12-08 18:00","연속",null,null,null,201609050108]
[194,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제#1T/L 피뢰기 설치공사","154kV 신고성-거제#1T/L 피뢰기 및 SB Damper 설치공사 - 공사구간 : No.118~120 / 피뢰기 - 고성-안정#1T/L TLA : No.10~20 및 SB Damper","2016-12-04 07:00","2016-12-04 19:00","2016-12-04 07:00","2016-12-04 19:00","매일",null,null,null,201610060057]
[195,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제#1T/L 피뢰기 설치공사","154kV 신고성-거제#1T/L 피뢰기 및 SB Damper 설치공사 - 공사구간 : No.87~117 / 피뢰기 - 진동-안정#1T/L : No.54~85","2016-12-11 07:30","2016-12-11 18:00","2016-12-11 07:30","2016-12-11 18:00","매일",null,null,null,201610060062]
[196,"경남","직할","신김해진영#1 T/L","안전이격확보휴전(신김해-삼천포화력#1 초기점검)","안전이격확보휴전(신김해-삼천포화력#1 초기점검)","2016-12-11 08:00","2016-12-11 11:00","2016-12-11 08:00","2016-12-11 11:00","당일",null,null,null,201610070323]
[197,"경남","직할","신김해진영#2 T/L","안전이격확보휴전(신김해-삼천포화력#2 초기점검)","안전이격확보휴전(신김해-삼천포화력#2 초기점검)","2016-12-11 11:00","2016-12-11 14:00","2016-12-11 11:00","2016-12-11 14:00","당일",null,null,null,201610070325]
[198,"경남","직할","신월삼정#1 T/L","피뢰기 설치 및 가공지선 교체(2016~17 직할 송전협력 총액공사)","피뢰기 설치(3~28호) 및 가공지선 교체(6~14호)","2016-12-01 07:30","2016-12-06 18:00","2016-12-01 07:30","2016-12-06 18:00","연속",null,null,null,201610070335]
[199,"경남","직할","신월동읍#1 T/L","피뢰기 설치(2016~17 직할 송전협력 총액공사)","피뢰기 설치(1~2호)","2016-12-04 07:30","2016-12-04 12:00","2016-12-04 07:30","2016-12-04 12:00","당일",null,null,null,201610070347]
[200,"경남","직할","신김해삼정#2 T/L","안전이격확보휴전(신월-삼정#1T/L 피뢰기 설치)","안전이격확보휴전(신월-삼정#1T/L 피뢰기 설치)","2016-12-03 07:30","2016-12-03 18:00","2016-12-03 07:30","2016-12-03 18:00","당일",null,null,null,201610070366]
[201,"경남","진주","합천합천수력#1T/L","합천S/S 모자익 교체공사","합천S/S 모자익 교체","2016-12-05 09:30","2016-12-06 18:30","2016-12-05 09:30","2016-12-06 18:30","당일",null,null,null,201610070379]
[202,"경남","진주","합천합천수력#2T/L","합천S/S 모자익 교체공사","합천S/S 모자익 교체","2016-12-07 09:30","2016-12-08 18:30","2016-12-07 09:30","2016-12-08 18:30","당일",null,null,null,201610070382]
[203,"경남","진주","거창합천#1 T/L","합천S/S 모자익 교체공사","합천S/S 모자익 교체","2016-12-03 09:30","2016-12-04 18:30","2016-12-03 09:30","2016-12-04 18:30","당일",null,null,null,201610070384]
[204,"경남","진주","거창합천#2 T/L","합천S/S 모자익 교체공사","합천S/S 모자익 교체","2016-12-10 09:30","2016-12-11 18:30","2016-12-10 09:30","2016-12-11 18:30","당일",null,null,null,201610070385]
[205,"경남","직할","주촌삼계#2 T/L","피뢰기 설치(2016~17 직할 송전협력 총액공사)","피뢰기 설치(20~30호)","2016-12-10 07:30","2016-12-10 18:00","2016-12-10 07:30","2016-12-10 18:00","당일",null,null,null,201610070436]
[206,"경남","진주","개양S/S 154KV #1 BUS","154kV 개양S/S #4M.Tr 증설공사","154kV #4M.Tr 시험가압관련 모선휴전 154kV 가야-개양T/L 로 가압","2016-12-09 18:00","2016-12-11 18:00","2016-12-09 18:00","2016-12-11 18:00","연속",null,null,null,201610120201]
[207,"경남","진주","산청함양 T/L","산청S/S 건물누수공사 안전이격","산청S/S 건물누수공사 안전이격","2016-12-18 08:00","2016-12-18 13:00","2016-12-18 08:00","2016-12-18 13:00","당일",null,null,null,201610180047]
[208,"경남","진주","의령산청 T/L","산청S/S 건물누수공사 안전이격","산청S/S 건물누수공사 안전이격","2016-12-18 13:00","2016-12-18 18:00","2016-12-18 13:00","2016-12-18 18:00","당일",null,null,null,201610180049]
[209,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 이도조정공사","154kV 하동-개양#1,2T/L 101~104호 송전선로 이도조정","2016-12-03 08:00","2016-12-04 17:30","2016-12-03 08:00","2016-12-04 17:30","연속",null,null,null,201610180177]
[210,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 이도조정공사","154kV 하동-개양#1,2T/L 101~104호 송전선로 이도조정","2016-12-03 08:00","2016-12-04 17:30","2016-12-03 08:00","2016-12-04 17:30","연속",null,null,null,201610180178]