{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":5,"n_cols":16,"rows_kept":5,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 1월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[null,null,null,"해당사항 없음"]

{"sheet":"345송부","index":1,"n_rows":22,"n_cols":16,"rows_kept":22,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 1월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","직할","신부평S/S #2 M.Tr A","신부평S/S 345kV #2M.Tr 보호반 대체","신부평S/S 345kV #2M.Tr 보호반 대체","2017-01-09 09:30","2017-01-13 18:00","2017-01-09 09:30","2017-01-13 18:00","연속",null,null,null,201611160061]
[2,"인천","직할","신부평S/S #3 M.Tr A","신부평S/S 345kV #3M.Tr 보호반 대체","신부평S/S 345kV #3M.Tr 보호반 대체","2017-01-16 09:30","2017-01-20 18:00","2017-01-16 09:30","2017-01-20 18:00","연속",null,null,null,201611160062]
[3,"충북","청주","신옥천S/S 345kV #2 BUS","345kV 신옥천S/S 차단기 용량대체공사","기설 77Bay #2BUS 철거작업","2017-01-10 09:00","2017-01-10 18:00","취소","취소","당일",null,null,null,201611140179]
[4,"충북","청주","신옥천S/S #3 M.Tr A","장기미동작 차단기 조작시험","#3M.Tr 2차 차단기 개폐Time 측정","2017-01-18 14:00","2017-01-18 18:00","취소","취소","당일",null,null,null,201611140025]
[5,"충북","청주","신옥천세종#1 T/L","345kV 신옥천S/S 차단기 용량대체공사","- 기설 인출GIB 철거 및 신설 인출GIB 설치 - 가선(가공인출 및 인하선 연결) - 송전선로 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험,사용전검사 - 기설 Bay 철거 및 신설Bay 가압","2017-01-09 09:00","2017-01-18 18:00","취소","취소","연속",null,null,null,201611140185]
[6,"충북","청주","신옥천S/S #3 M.Tr A","345kV 신옥천S/S 차단기 용량대체공사","- 가선(인하선 연결) - 변압기 보호반 기설 케이블 철거 및 신설 케이블 결선 - 보호반관련 시험 및 연동시험 - 기설 Bay철거 및 신설 Bay 가압","2017-01-09 09:00","2017-01-18 18:00","취소","취소","연속",null,null,null,201611140173]
[7,"충북","청주","신옥천S/S 345kV #1 BUS","345kV 신옥천S/S 차단기 용량대체공사","기설 77Bay #1BUS 철거작업","2017-01-09 09:00","2017-01-09 18:00","취소","취소","당일",null,null,null,201611140176]
[8,"충북","청주","청원S/S #4 M.Tr A","장기미동작 차단기 조작시험","#4M.Tr 2차 차단기 개폐Time 측정","2017-01-17 10:00","2017-01-17 18:00","취소","취소","당일",null,null,null,201611140024]
[9,"충북","청주","청원S/S #3 M.Tr A","16~17년 청주 변전협력회사 총액공사","청원S/S #3 M.Tr A상 2차 부싱단자 과열 보수","2017-01-09 09:00","2017-01-09 18:00","취소","취소","당일",null,null,null,201611180020]
[10,"대전충남","아산","신탕정S/S #3 M.Tr A","신탕정S/S 345kV 용량부족 GIS대체공사","○ 345kV 73BAY GIS 용량부족 대체 ○ 기타 부대작업- (50kA 4,000A)×2CB 철거 및 362kV GIS(63kA 6,300A)×2CB 설치공사","2017-01-09 09:00","2017-02-22 18:00","2017-01-09 09:00","2017-02-22 18:00","연속",null,null,null,201611110211]
[11,"대전충남","아산","신탕정S/S 345kV #2 BUS","신탕정S/S 345kV 용량부족 GIS대체공사","○ 345kV 73Bay #2BUS 측 모선부 용량부족 대체 ○ 기타 부대작업- 모선부 철거 및 설치작업","2017-01-09 09:00","2017-01-15 18:00","2017-01-09 09:00","2017-01-15 18:00","연속",null,null,null,201611110206]
[12,"대전충남","아산","신탕정S/S 345kV #1 BUS","신탕정S/S 345kV 용량부족 GIS대체공사","○ 345kV 73Bay #1BUS 측 모선부 용량부족 대체 ○ 기타 부대작업- 모선부 철거 및 설치작업","2017-01-16 09:00","2017-01-22 18:00","2017-01-16 09:00","2017-01-22 18:00","연속",null,null,null,201611110208]
[13,"전북","김제","군산신김제#2 T/L","345kV 군산-신김제T/L 불량접속함 교체공사","LS제 불량 중간접속함 교체공사(PJ- PMJ 접속함 ) LS전선 하자처리","2017-01-24 08:00","2017-02-11 18:00","취소","취소","연속",null,null,null,201611150135]
[14,"전북","김제","신김제S/S #3 M.Tr A","신김제S/S #3 M.Tr A","76Bay B/F 보호반 교체","2017-01-31 09:00","2017-02-03 18:00","2017-01-31 09:00","2017-02-03 18:00","연속",null,null,null,201611160101]
[15,"전북","김제","신김제S/S #2 M.Tr A","신김제S/S #2 M.Tr A","보호배전반 교체","2017-01-16 09:00","2017-01-20 18:00","2017-01-16 09:00","2017-01-20 18:00","연속",null,null,null,201611160096]
[16,"전북","김제","군산신김제#1 T/L","345kV 군산-신김제T/L 불량접속함 교체공사","LS제 불량 중간접속함 교체공사(PJ- PMJ 접속함 ) LS전선 하자처리","2017-01-05 08:00","2017-01-23 18:00","취소","취소","연속",null,null,null,201611150132]
[17,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S 345kV #1M.Tr(과부하경보설비 구축)","2016~17년도 강진전력지사 변전협력회사 총액공사 - 17. 1. 30 : 신강진S/S 75BAY 과부하경보설비 구축","2017-01-30 09:00","2017-01-30 18:00","2017-01-30 09:00","2017-01-30 18:00","당일",null,null,null,201611170094]
[18,"대구경북","포항","월성NP신월성NP#1T/L","월성S/Y 월성연락#1T/L 휴전작업","월성S/Y 월성연락#1T/L 애자코팅 월성S/Y 7400, 7471, 7472 CB, PT 보통점검 월성S/Y 7421-2,3,4 DS, CLR A,B,C, #1S.Tr 보통점검","2017-01-04 09:00","2017-01-09 18:00","2017-01-04 09:00","2017-01-09 18:00","연속",null,null,null,201611080109]

{"sheet":"154송부","index":2,"n_rows":37,"n_cols":16,"rows_kept":37,"cut":false,"hidden":false,"merged":[[2,14,3,14],[2,15,3,15],[2,6,2,7],[2,8,2,9],[2,10,3,10],[2,11,3,11],[2,12,3,12],[2,13,3,13],[2,5,3,5],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4]]}
["2017년도 1월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","영서","가양등촌#2 T/L","2017년 변전협력회사 총액공사_계획보수","가양,등촌S/S 가양-등촌#1,2T/L 인출접지 PITR 인터록회로 구성","2017-01-10 10:00","2017-01-10 15:00","2017-01-10T10:00:00","2017-01-10T15:00:00","당일",null,null,null,201611180042]
[2,"남서울","영서","가양등촌#1 T/L","2017년 변전협력회사 총액공사_계획보수","가양,등촌S/S 가양-등촌#1,2T/L 인출접지 PITR 인터록회로 구성","2017-01-10 10:00","2017-01-10 15:00","2017-01-10T10:00:00","2017-01-10T15:00:00","당일",null,null,null,201611180037]
[3,"인천","인천","신현S/S 154kV #1 BUS","154kV 신현-포스코CC #1T/L M/H#4~#5 지장이설공사","154kV 신현-포스코CC #1T/L 지장이설관련 상체크시험","2017-01-03 13:00","2017-01-03 18:00","취소","취소","당일",null,null,null,201610310014]
[4,"경기북부","파주","일산호수#1 T/L","백마지하차도 지장송전선로 이설공사","지중송전선로 이설 : 일산-호수 관로 #2~3","2017-01-17 08:00","2017-02-02 18:00","2017-01-17T08:00:00","2017-02-02T18:00:00","연속",null,null,null,201610170128]
[5,"강원","원주","신제천남원주#2 T/L","남원주S/S 외장재 교체공사","남원주S/S 배면부 외장재 교체 (신제천-남원주#2T/L)","2017-01-07 08:00","2017-01-10 18:00","2017-01-07 08:00","2017-01-10 18:00","매일",null,null,null,201611150003]
[6,"강원","원주","남원주원주#2 T/L","남원주S/S 외장재 교체공사","남원주S/S 배면부 외장재 교체 (남원주-원주#2T/L)","2017-01-05 08:00","2017-01-08 18:00","2017-01-05 08:00","2017-01-08 18:00","매일",null,null,null,201611150002]
[7,"강원","원주","남원주원주#1 T/L","남원주S/S 외장재 교체공사","남원주S/S 배면부 외장재 교체 (남원주-원주#1T/L)","2017-01-03 08:00","2017-01-06 18:00","2017-01-03 08:00","2017-01-06 18:00","매일",null,null,null,201611150001]
[8,"강원","원주","신제천남원주#1 T/L","남원주S/S 외장재 교체공사","남원주S/S 배면부 외장재 교체 (신제천-남원주#1T/L)","2017-01-09 08:00","2017-01-11 18:00","2017-01-09 08:00","2017-01-11 18:00","매일",null,null,null,201611150004]
[9,"강원","직할","남춘천춘천열병합#2 T/L","154kV 춘천열병합S/Y 인출 POST 주자재 보강공사","- 춘천열병합S/Y 송전선로 인출 POST(Gantry Tower) 안전성 검토 결과 주자재 보강 필요에 따른 보강 시행 - 주자재 보강 및 교체, 볼트 교체","2017-01-17 09:00","2017-01-17 17:00","2017-01-17 09:00","2017-01-17 17:00","당일",null,null,null,201611170039]
[10,"강원","직할","남춘천춘천열병합#1 T/L","154kV 춘천열병합S/Y 인출 POST 주자재 보강공사","- 춘천열병합S/Y 송전선로 인출 POST(Gantry Tower) 안전성 검토 결과 주자재 보강 필요에 따른 보강 시행 - 주자재 보강 및 교체, 볼트 교체","2017-01-17 09:00","2017-01-17 17:00","2017-01-17 09:00","2017-01-17 17:00","당일",null,null,null,201611170038]
[11,"강원","직할","청평PP춘천열병합 T/L","154kV 춘천열병합S/Y 인출 POST 주자재 보강공사","- 춘천열병합S/Y 송전선로 인출 POST(Gantry Tower) 안전성 검토 결과 주자재 보강 필요에 따른 보강 시행 - 주자재 보강 및 교체, 볼트 교체","2017-01-18 09:00","2017-01-18 17:00","2017-01-18 09:00","2017-01-18 17:00","당일",null,null,null,201611170040]
[12,"강원","직할","서홍천춘천열병합 T/L","154kV 춘천열병합S/Y 인출 POST 주자재 보강공사","- 춘천열병합S/Y 송전선로 인출 POST(Gantry Tower) 안전성 검토 결과 주자재 보강 필요에 따른 보강 시행 - 주자재 보강 및 교체, 볼트 교체","2017-01-16 09:00","2017-01-16 17:00","2017-01-16 09:00","2017-01-16 17:00","당일",null,null,null,201611170037]
[13,"충북","직할","왕암가남#2 T/L","154kV 왕암-가남T/L 10~12호 안전이격확보공사","철탑신설 2기, 철탑철거 1기","2017-01-16 08:00","2017-01-20 18:00","2017-01-16 08:00","2017-01-20 18:00","연속",null,null,null,201611170136]
[14,"충북","직할","왕암가남#1 T/L","154kV 왕암-가남T/L 10~12호 안전이격확보공사","철탑신설 2기, 철탑철거 1기","2017-01-16 08:00","2017-01-20 18:00","2017-01-16 08:00","2017-01-20 18:00","연속",null,null,null,201611170135]
[15,"충북","직할","신제천주진#1 T/L","직할 변전협력회사 총액공사","- 신제천S/S 신제천주진#1T/L #2BUS DS(612) 조작불량 점검.","2017-01-10 09:00","2017-01-10 18:00","2017-01-10 09:00","2017-01-10 18:00","당일",null,null,null,201611290099]
[16,"충북","충주","삼죽만승 T/L","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험","2017-01-03 15:00","2017-01-03 16:00","2017-01-03 15:00","2017-01-03 16:00","당일",null,null,null,201611090022]
[17,"충북","충주","진천만승#2 T/L","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험","2017-01-03 13:00","2017-01-03 14:00","2017-01-03 13:00","2017-01-03 14:00","당일",null,null,null,201611090024]
[18,"충북","충주","만승S/S 154kV #1 BUS TIE GIS","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험","2017-01-03 14:00","2017-01-03 15:00","2017-01-03 14:00","2017-01-03 15:00","당일",null,null,null,201611090026]
[19,"충북","충주","풍동S/S 154kV #1 BUS TIE GIS","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험","2017-01-06 14:00","2017-01-06 18:00","2017-01-06 14:00","2017-01-06 18:00","당일",null,null,null,201611110082]
[20,"대전충남","아산","아산온양#1 T/L","[송전] 154kV 아산-온양T/L 23호 안전이격확보공사","ㅇ 철탑교체 : 1기 ㅇ OPGW 이설 : 1기 ㅇ 기타 부대공사","2017-01-21 08:00","2017-01-22 18:00","2017-01-21T08:00:00","2017-01-22T18:00:00","연속",null,null,null,201611240109]
[21,"대전충남","아산","아산온양#2 T/L","[송전] 154kV 아산-온양T/L 23호 안전이격확보공사","ㅇ 철탑교체 : 1기 ㅇ OPGW 이설 : 1기 ㅇ 기타 부대공사","2017-01-27 08:00","2017-01-30 18:00","2017-01-27T08:00:00","2017-01-30T18:00:00","연속",null,null,null,201611230026]
[22,"전북","군산","군공군산CC#2 T/L","154kV 군공-군산복합 지장 지중선로 이설공사","군장대교 건설관련 지장 송전설로 이설","2017-01-18 08:00","2017-03-04 18:00","2017-01-18 08:00","2017-03-04 18:00","연속",null,null,null,201610170205]
[23,"대구경북","포항","영일입실 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사(안전확보)","345kV 동울산-월성NP T/L 39~40호 가선작업 안전확보(철탑 발받침 철거)","2017-01-04 08:00","2017-01-06 18:00","2017-01-04 08:00","2017-01-06 18:00","연속",null,null,null,201611200015]
[24,"대구경북","포항","입실양북 T/L","345kV 동울산-월성NP 등 2개T/L 계통변경공사(안전확보)","345kV 동울산-월성NP T/L 39~40호 가선작업 안전확보(철탑 발받침 철거)","2017-01-04 08:00","2017-01-06 18:00","2017-01-04 08:00","2017-01-06 18:00","연속",null,null,null,201611200016]
[25,"부산울산","북부산","북부산삼랑진PP#1 T/L","북부산S/S 154kV 취약설비 GIS화 공사","154kV GIS 반입관련 안전이격","2017-01-21 09:00","2017-01-22 18:00","2017-01-21 09:00","2017-01-22 18:00","연속",null,null,null,201611100079]
[26,"경남","직할","창공월림#1 T/L","345kV 창원분기T/L 건설 공사","345kV 창원분기T/L 건설 공사 4-5호 가선 구간 154kV 창공-월림#1,2T/L 9-10호 교차에 따른 안전 보호망 설치 관련 안전 확보","2017-01-01 09:00","2017-01-01 18:00","2017-01-01 09:00","2017-01-01 18:00","당일",null,null,null,201609120447]
[27,"경남","직할","창공월림#2 T/L","345kV 창원분기T/L 건설 공사","345kV 창원분기T/L 건설 공사 4-5호 가선 구간 154kV 창공-월림#1,2T/L 9-10호 교차에 따른 안전 보호망 설치 관련 안전 확보","2017-01-01 09:00","2017-01-01 18:00","2017-01-01 09:00","2017-01-01 18:00","당일",null,null,null,201609120449]
[28,"경남","직할","창공월림#1 T/L","345kV 창원분기T/L 건설 공사","345kV 창원분기T/L 건설 공사 4-5호 가선 구간 154kV 창공-월림#1,2T/L 9-10호 교차에 따른 안전 보호망 철거 관련 안전 확보","2017-01-30 08:00","2017-01-30 18:00","2017-01-30 08:00","2017-01-30 18:00","당일",null,null,null,201611070104]
[29,"경남","직할","창공월림#2 T/L","345kV 창원분기T/L 건설 공사","345kV 창원분기T/L 건설 공사 4-5호 가선 구간 154kV 창공-월림#1,2T/L 9-10호 교차에 따른 안전 보호망 철거 관련 안전 확보","2017-01-30 08:00","2017-01-30 18:00","2017-01-30 08:00","2017-01-30 18:00","당일",null,null,null,201611070103]
[30,"경남","통영","신고성거제#2 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-거제T/L 철탑 설치 및 전선이설","2017-01-30 09:00","2017-01-30 18:00","2017-01-30 09:00","2017-01-30 18:00","당일",null,null,null,201611110130]
[31,"경남","통영","신고성거제#1 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-거제T/L 철탑 설치 및 전선이설","2017-01-29 09:00","2017-01-29 18:00","2017-01-29 09:00","2017-01-29 18:00","당일",null,null,null,201611110129]
[32,"경남","통영","신고성고성 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 철탑 설치 및 전선이설","2017-01-28 09:00","2017-01-28 18:00","2017-01-28 09:00","2017-01-28 18:00","당일",null,null,null,201611110128]
[33,"경남","통영","신고성통영 T/L","345kV 삼천포 등 4개T/L 지장송전선로 이설공사","고성하이화력발전소 건설에 의한 지장이설 - 154kV 신고성-통영T/L 철탑 설치 및 전선이설","2017-01-27 09:00","2017-01-27 18:00","2017-01-27 09:00","2017-01-27 18:00","당일",null,null,null,201611110127]