{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":11,"n_cols":16,"rows_kept":11,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
["2018년도 12월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성S/S #2 M.Tr A-1","신안성S/S #2M.Tr AC 상실관련 경보분리","신안성S/S #2M.Tr AC 상실관련 경보분리","2018-12-08 09:00","2018-12-08 18:00","2018-12-08 09:00","2018-12-08 18:00","당일",null,null,null,201810080114]
[2,"경기","성남","신안성S/S #3 M.Tr A-1","신안성S/S #2M.Tr AC 상실관련 경보분리","신안성S/S #2M.Tr AC 상실관련 경보분리","2018-12-15 09:00","2018-12-15 18:00","2018-12-15 09:00","2018-12-15 18:00","당일",null,null,null,201810080115]
[3,"강원","태백","신태백S/S #4 M.Tr 1차 CB","18~19 태백전력지사 변전정비회사 총액공사","18~19 태백전력지사 변전정비회사 총액공사","2018-12-03 10:00","2018-12-03 18:00","취소","취소","당일",null,null,null,201810110088]
[4,"대전충남","서산","당진T/P 9호기 1차 CB(8972)","18년 변전협력회사 총액공사","18년 변전협력회사 총액공사","2018-12-03 09:00","2018-12-03 18:00","2018-12-03 09:00","2018-12-03 18:00","당일",null,null,null,201810160059]
[5,"대전충남","서산","당진T/P 3호기 1차 CB(8372)","당진화력 3,4호기 주변압기 역가압 관련 조작요청(발전소요청)","당진화력 3,4호기 주변압기 역가압 관련 조작요청(발전소요청)","2018-12-14 13:30","2018-12-14 18:00","2018-12-14 13:30","2018-12-14 18:00","당일",null,null,null,201810170045]
[6,"대전충남","서산","당진T/P 신서산-당진TP#1T/L-3호기 1차 CB(8300)","당진화력 3,4호기 주변압기 역가압 관련 조작요청(발전소요청)","당진화력 3,4호기 주변압기 역가압 관련 조작요청(발전소요청)","2018-12-14 13:30","2018-12-14 18:00","2018-12-14 13:30","2018-12-14 18:00","당일",null,null,null,201810170044]
[7,"경남","함안","북경남신고리NP#2 T/L","북경남s/s 765kV 스페이서 교체공사","북경남s/s 765kV 스페이서 교체공사","2018-12-03 09:30","2018-12-10 18:00","2018-12-03 09:30","2018-12-10 18:00","연속",null,null,null,201810110288]

{"sheet":"345송부","index":1,"n_rows":161,"n_cols":16,"rows_kept":161,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,14,3,14],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
["2018년도 12월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","동서울","동서울S/S #1Sh.R 1차-TIE CB (7A00)","345kV 동서울S/S #2 Sh.R GIS 설치공사","345kV GIS(50kA 4000A × 2CB) × 1조 설치","2018-12-04 09:30","2018-12-19 17:00","2018-12-04 09:30","2018-12-19 17:00","연속"]
[2,"인천","시흥","서서울#2신시흥#1 T/L","신시흥#2S/S 옥외분전반(LA3) 대체공사 이격거리 확보","신시흥#2S/S 옥외분전반(LA3) 대체공사 이격거리 확보","2018-12-05 13:00","2018-12-05 17:00","2018-12-05 13:00","2018-12-05 17:00","당일"]
[3,"인천","시흥","신시흥신안산 T/L","신시흥#2S/S 옥외분전반(LA2) 대체공사 이격거리 확보","신시흥#2S/S 옥외분전반(LA2) 대체공사 이격거리 확보","2018-12-03 13:00","2018-12-03 17:00","취소","취소","당일"]
[4,"인천","인천","신김포신인천CC T/L","345kV신김포-신인천CCT/L 발열개소 보강공사 ","○ J/B#3 B상(2B) 발열개소 보강시행 ","2018-12-10 09:00","2018-12-10 18:00","취소","취소","연속"]
[5,"인천","인천","(신)서인천C/C 서인천신부평#4T/L CB (7A72)","서인천복합S/Y 7A72 GIS 초기점검","서인천복합S/Y 7A72 GIS 초기점검","2018-12-04 09:00","2018-12-04 18:00","2018-12-09 09:00","2018-12-09 18:00","당일"]
[6,"인천","인천","(신)서인천C/C #2 M.Tr 1차 CB (7272)","서인천복합S/Y 7272 GIS 하자점검","서인천복합S/Y 7272 GIS 하자점검","2018-12-11 09:00","2018-12-11 18:00","2018-12-11 09:00","2018-12-11 18:00","당일"]
[7,"인천","인천","신경서서인천CC T/L","서인천복합S/Y 신경서서인천CCT/L 철공진방지장치 설치공사","서인천복합S/Y 신경서서인천CCT/L 철공진방지장치 설치공사 서인천복합S/Y 7271, 7200 GIS 하자점검","2018-12-05 09:00","2018-12-06 18:00","2018-12-05 09:00","2018-12-06 18:00","연속"]
[8,"인천","인천","신가좌가정#1 T/L","345kV신가좌가정#1T/L 항공구 설치공사","18-19 가공송전선로 협력회사 총액공사","2018-12-03 08:00","2018-12-04 18:00","2018-12-08 08:00","2018-12-09 18:00","연속"]
[9,"인천","인천","신가좌S/S #4 M.Tr A","신가좌S/S #4M.Tr 보통점검","#4M.Tr 보통점검 #4M.Tr 1,2,3차 LA 대체 76BAY B/F PNL 대체 6444 GIS 초기점검 #4-2Sh.R 초기점검","2018-12-06 09:00","2018-12-11 18:00","2018-12-06 09:00","2018-12-11 18:00","연속"]
[10,"인천","인천","(신)신인천C/C 70-71 SEC GIS","서인천복합S/Y 70-71-0 GIS 하자점검","서인천복합S/Y 70-71-0 GIS 하자점검","2018-12-03 09:00","2018-12-03 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[11,"인천","인천","신경서신인천CC T/L","신김포-신경서간 광케이블 시설공사","신김포-신경서간 광케이블 시설(OPGW : 13.4Km 시설)","2018-12-03 06:00","2018-12-16 18:00","취소","취소","연속"]
[12,"인천","직할","신부평S/S 서인천CC-신부평#2T/L CB (7271)","신부평S/S 7271CB 대쉬포트 누유보수","신부평S/S 7271CB 대쉬포트 누유보수(C상)","2018-12-03 09:00","2018-12-03 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[13,"인천","직할","서인천CC-신부평#2T/L-#2 M.Tr 1차 CB (7200)","신부평S/S 7200CB 대쉬포트 누유보수","신부평S/S 7200CB 대쉬포트 누유보수(A,B상)","2018-12-04 09:00","2018-12-04 18:00","2018-12-04 09:00","2018-12-04 18:00","당일"]
[14,"경기북부","구리","미금S/S #1 M.Tr A","구리전력 345kV #1M.Tr 3차 VCB 교체공사","#1M.Tr 3차 VCB 교체공사","2018-12-04 09:00","2018-12-05 18:00","2018-12-04 09:00","2018-12-05 18:00","연속"]
[15,"경기북부","구리","신가평S/S 345kV #2 Sh.R","신가평S/S 7379GIS 초기점검","신가평S/S 7379GIS 초기점검","2018-12-03 09:00","2018-12-03 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[16,"경기북부","구리","신포천S/S #3 M.Tr A","YPP제 345kV 변압기 보호배전반 보호계전기(T60) 리콜 시행","○ DSP 오류 검출 방식이 개선된 펌웨어로 업그레이드 ○ 노이즈 필터링 기능이 강화된 DSP 모듈로 교체","2018-12-03 09:00","2018-12-03 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[17,"경기북부","직할","신의정부S/S #1 M.Tr A","YPP제 345kV 변압기 보호배전반 보호계전기(T60) 리콜 시행","○ DSP 오류 검출 방식이 개선된 펌웨어로 업그레이드 ○ 노이즈 필터링 기능이 강화된 DSP 모듈로 교체","2018-12-04 09:00","2018-12-04 18:00","2018-12-04 09:00","2018-12-04 18:00","당일"]
[18,"경기북부","직할","신의정부S/S 345kV #3 Sh.R","18~19 변전정비 총액공사","345kV #3Sh.R 보통점검","2018-12-13 10:00","2018-12-13 18:00","2018-12-13 10:00","2018-12-13 18:00","당일"]
[19,"경기북부","직할","양주S/S #4 M.Tr A","양주변전소 옥외철구 GIS화 공사","M.Tr 3차측 GIS 및 기초 설치","2018-12-24 09:00","2018-12-28 18:00","2018-12-24 09:00","2018-12-28 18:00","연속"]
[20,"경기북부","직할","양주S/S #1 M.Tr A","양주변전소 옥외철구 GIS화 공사","M.Tr 3차측 GIS 및 기초 설치","2018-12-17 09:00","2018-12-21 18:00","2018-12-17 09:00","2018-12-21 18:00","연속"]
[21,"경기북부","직할","양주S/S #2 M.Tr A","양주변전소 옥외철구 GIS화 공사","M.Tr 3차측 GIS 및 기초 설치","2018-12-10 09:00","2018-12-14 18:00","2018-12-10 09:00","2018-12-14 18:00","연속"]
[22,"경기북부","직할","양주S/S #3 M.Tr A","양주변전소 옥외철구 GIS화 공사","M.Tr 3차측 GIS 및 기초 설치","2018-12-03 09:00","2018-12-07 18:00","2018-12-03 09:00","2018-12-07 18:00","연속"]
[23,"경기","군포","서서울S/S #3 M.Tr A","서서울S/S 345kV 3M.Tr A상 1차 불량 부싱 교체공사","서서울S/S 345kV 3M.Tr A상 1차 불량 부싱 교체 및 3차측 S.Tr, 차단기 점검","2018-12-03 09:00","2018-12-07 18:00","2018-12-03 09:00","2018-12-07 18:00","연속"]
[24,"경기","군포","서서울신광명#2 T/L","서서울-신광명 #2T/L 차단기 조작시험","서서울-신광명 #2T/L 차단기 조작시험","2018-12-03 13:00","2018-12-03 17:00","2018-12-03 13:00","2018-12-03 17:00","당일"]
[25,"경기","군포","서서울신광명#1 T/L","서서울-신광명 #1T/L 차단기 조작시험","서서울-신광명 #1T/L 차단기 조작시험","2018-12-03 09:00","2018-12-03 13:00","2018-12-03 09:00","2018-12-03 13:00","당일"]
[26,"경기","군포","신안산S/S #1 M.Tr A","18년 군포P/O 변전정비 총액공사","○ 7100, 7172CB 조작시험","2018-12-03 10:00","2018-12-03 14:00","2018-12-04 10:00","2018-12-04 14:00","당일"]
[27,"경기","군포","신안산S/S 345kV #70 BUS","345kV 신안산S/S 용량부족 GIS 대체 및 SW 증설공사","- 화성-신안산T/L GIS #70BUS 기기도킹","2018-12-04 09:00","2018-12-07 18:00","취소","취소","연속"]
[28,"경기","군포","화성신안산 T/L","345kV 신안산S/S 용량부족 GIS 대체 및 SW 증설공사","- 화성-신안산T/L GIS 및 #70BUS 무부하가압","2018-12-06 09:00","2018-12-07 18:00","취소","취소","연속"]
[29,"경기","군포","신안산S/S #1 M.Tr A","345kV 신안산S/S 용량부족 GIS 대체 및 SW 증설공사","- 화성-신안산T/L GIS 및 #75BUS 무부하가압","2018-12-12 09:00","2018-12-13 18:00","취소","취소","연속"]
[30,"경기","군포","화성신안산 T/L","345kV 신안산S/S 용량부족 GIS 대체 및 SW 증설공사","- 화성-신안산T/L GIS 및 #75BUS 무부하가압","2018-12-12 09:00","2018-12-13 18:00","취소","취소","연속"]
[31,"경기","군포","신안산S/S 345kV #75 BUS","345kV 신안산S/S 용량부족 GIS 대체 및 SW 증설공사","- 화성-신안산T/L GIS #75BUS 기기도킹","2018-12-10 09:00","2018-12-13 18:00","취소","취소","연속"]
[32,"경기","동부","곤지암S/S #1 M.Tr 1차 GIS(7172)","18년 동부변전협력회사 총액공사","곤지암:7172.7100 GIS (개폐타임)","2018-12-03 09:00","2018-12-03 14:00","2018-12-03 09:00","2018-12-03 14:00","당일"]
[33,"경기","동부","곤지암S/S 곤지암-신충주#1T/L GIS(7271)","18년 동부변전협력회사 총액공사","곤지암:7271.7200 GIS (개폐타임)","2018-12-04 09:00","2018-12-04 14:00","2018-12-04 09:00","2018-12-04 14:00","당일"]
[34,"경기","동부","곤지암S/S 곤지암-신충주#1T/L-TIE GIS(7200)","18년 동부변전협력회사 총액공사","곤지암:7271.7200 GIS (개폐타임)","2018-12-04 14:00","2018-12-04 18:00","2018-12-04 14:00","2018-12-04 18:00","당일"]
[35,"경기","동부","곤지암S/S 곤지암-신충주#2T/L GIS(7171)","18년 동부변전협력회사 총액공사","곤지암: 7171 GIS (개폐타임)","2018-12-05 09:00","2018-12-05 18:00","2018-12-05 09:00","2018-12-05 18:00","당일"]
[36,"경기","동부","곤지암-신충주#2T/L-#1 M.Tr 1차 GIS(7100)","18년 동부변전협력회사 총액공사","곤지암:7172.7100 GIS (개폐타임)","2018-12-03 14:00","2018-12-03 18:00","2018-12-03 14:00","2018-12-03 18:00","당일"]
[37,"경기","동부","곤지암S/S #3 M.Tr 1차-TIE GIS(7500)","18년 동부변전협력회사 총액공사","곤지암:7572,7500 GIS (개폐타임)","2018-12-06 14:00","2018-12-06 18:00","2018-12-06 14:00","2018-12-06 18:00","당일"]
[38,"경기","동부","곤지암S/S 345kV #1Sh.R GIS(7179)","18년 동부변전협력회사 총액공사","곤지암:7179 GIS (개폐타임)","2018-12-07 09:00","2018-12-07 18:00","2018-12-07 09:00","2018-12-07 18:00","당일"]
[39,"경기","동부","곤지암동서울#2 T/L","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS 무부하가압용 수전선로 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2018-11-17 17:30","2018-11-18 17:30","취소","취소","연속"]
[40,"경기","동부","곤지암S/S #3 M.Tr 1차 GIS(7572)","18년 동부변전협력회사 총액공사","곤지암:7572,7500 GIS (개폐타임)","2018-12-06 09:00","2018-12-06 14:00","2018-12-06 09:00","2018-12-06 14:00","당일"]
[41,"경기","성남","신성남동서울#2 T/L","신성남-동서울TL OPGW시설공사(대장지구)","신성남동서울T/L 머내C/H~동서울 구간 OPGW 증설","2018-12-08 09:00","2018-12-09 18:00","2018-12-08 09:00","2018-12-09 18:00","연속"]
[42,"경기","성남","신성남동서울#2 T/L","신성남-동서울TL OPGW시설공사(대장지구)","신성남동서울T/L 머내C/H~동서울 구간 OPGW 증설","2018-12-01 09:00","2018-12-02 18:00","2018-12-01 09:00","2018-12-02 18:00","연속"]
[43,"경기","성남","신성남신양재#2 T/L","신안성신가평 등 4개T/L 항공구 정비공사","345kV 신성남-신양재T/L : NO.7~10호 백색 18개 설치, 13개철거","2018-12-13 09:00","2018-12-14 18:00","2018-12-13 09:00","2018-12-14 18:00","연속"]
[44,"경기","직할","화성S/S 345kV #70 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 #75모선 분리","2018-12-01 09:00","2018-12-10 18:00","2018-12-01 09:00","2018-12-10 18:00","연속"]
[45,"경기","직할","화성S/S 345kV #1LCR 70BUS CB (7077)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-12-01 09:00","2019-04-30 18:00","2018-12-01 09:00","2019-04-30 18:00","연속"]
[46,"경기","직할","화성S/S 70-71-0 SEC CB (70-71-0)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-12-01 09:00","2019-04-30 18:00","2018-12-01 09:00","2019-04-30 18:00","연속"]
[47,"경기","직할","화성S/S 345kV #1LCR 71BUS CB (7177)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-12-01 09:00","2019-04-30 18:00","2018-12-01 09:00","2019-04-30 18:00","연속"]
[48,"경기","직할","화성S/S 345kV #2LCR 76BUS GIS CB (7677)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-12-03 09:00","2018-12-07 18:00","2018-12-03 09:00","2018-12-07 18:00","연속"]
[49,"경기","직할","화성S/S 345kV #71 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 #75모선 분리","2018-12-11 09:00","2018-12-25 18:00","2018-12-11 09:00","2018-12-25 18:00","연속"]
[50,"경기","직할","화성S/S 345kV #2LCR 75BUS GIS CB (7577)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB) - 한류리액터 이설관련 철거시행","2018-12-03 09:00","2018-12-07 18:00","2018-12-03 09:00","2018-12-07 18:00","연속"]
[51,"강원","동해","동해S/S 345kV #1 BUS","동해S/S STATCOM용 GIS 설치공사","○ 362kV 6300A 63kA GIS × 2CB ○ 기타부대공사 1식","2018-12-06 09:00","2018-12-06 13:30","취소","취소","당일"]
[52,"강원","동해","동해S/S 345kV #2 BUS","동해S/S STATCOM용 GIS 설치공사","○ 362kV 6300A 63kA GIS × 2CB ○ 기타부대공사 1식","2018-12-06 14:00","2018-12-06 18:00","취소","취소","당일"]
[53,"강원","동해","동해S/S #3 M.Tr","동해S/S STATCOM용 GIS 설치공사","○ 362kV 6300A 63kA GIS × 2CB ○ 기타부대공사 1식","2018-12-11 09:00","2018-12-11 18:00","2018-12-22 09:00","2018-12-22 18:00","당일"]
[54,"충북","직할","신제천S/S #2 M.Tr A","신제천S/S 345kV DS 하자대체 및 GIS 초기점검차","- 신제천S/S 345kV DS(7302,7362) 제작사(LS) 하자대체 - 362kV GIS 초기점검","2018-12-05 09:00","2018-12-08 18:00","2018-12-05 08:00","2018-12-07 18:00","연속"]
[55,"충북","직할","신제천신충주#2 T/L","신제천S/S 신제천-신충주#2T/L 345kV DS 하자대체","- 345kV DS(7361, 7301) 제작사(LS) 하자대체","2018-12-02 09:00","2018-12-05 18:00","2018-12-05 09:00","2018-12-05 12:00","연속"]
[56,"충북","충주","신진천S/S #2 M.Tr A","신진천S/S #2M.Tr 보호반 대체","신진천S/S #2M.Tr 보호반 대체","2018-12-03 10:00","2018-12-07 18:00","취소","취소","연속"]
[57,"충북","직할","신제천동해#1 T/L","345kV 신제천S/S TCSC용 GIB 설치공사","GIB 362kV 6300A 63kA 1식","2018-12-15 09:00","2018-12-31 18:00","2018-12-15 09:00","2018-12-31 18:00","연속"]
[58,"대전충남","서산","태안T/P 신서산-태안TP#2T/L CB (7A71)","18년 변전협력회사 총액공사","765kV 8962 DS A상 결상발생 관련 조치 작업","2018-12-04 09:00","2018-12-04 18:00","취소","취소","당일"]
[59,"대전충남","아산","신온양-서서울 #2 T/L - #4 M.Tr 1차 CB (7700)","신온양S/S 345kV 7700,7771,7871 CB 개폐타임 측정","신온양S/S 345kV 7700,7771,7871 CB 개폐타임 측정","2018-12-05 09:00","2018-12-05 12:00","2018-12-05 09:00","2018-12-05 12:00","당일"]
[60,"대전충남","아산","신온양S/S 신온양-서서울 #2 T/L CB (7771)","신온양S/S 345kV 7700,7771,7871 CB 개폐타임 측정","신온양S/S 345kV 7700,7771,7871 CB 개폐타임 측정","2018-12-05 12:00","2018-12-05 15:00","2018-12-05 12:00","2018-12-05 15:00","당일"]
[61,"대전충남","아산","신온양S/S 신온양-서서울 #1 T/L CB (7871)","신온양S/S 345kV 7700,7771,7871 CB 개폐타임 측정","신온양S/S 345kV 7700,7771,7871 CB 개폐타임 측정","2018-12-05 15:00","2018-12-05 18:00","2018-12-05 15:00","2018-12-05 18:00","당일"]
[62,"대전충남","아산","신탕정S/S #3 M.Tr 1차 CB (7371)","신탕정S/S 345kV 7371 CB 개폐타임 측정","신탕정S/S 345kV 7371 CB 개폐타임 측정","2018-12-06 09:00","2018-12-06 12:00","2018-12-06 09:00","2018-12-06 12:00","당일"]
[63,"대전충남","아산","아산S/S 신서산-아산#1T/L CB (7171)","아산S/S 345kV 7171,7172,7271 CB 개폐타임 측정","아산S/S 345kV 7171,7172,7271 CB 개폐타임 측정","2018-12-03 09:00","2018-12-03 12:00","2018-12-03 09:00","2018-12-03 12:00","당일"]
[64,"대전충남","아산","아산S/S 아산-보령화력#2T/L CB (7172)","아산S/S 345kV 7171,7172,7271 CB 개폐타임 측정","아산S/S 345kV 7171,7172,7271 CB 개폐타임 측정","2018-12-03 12:00","2018-12-03 15:00","2018-12-03 12:00","2018-12-03 15:00","당일"]
[65,"대전충남","아산","아산S/S 아산-화성#2T/L CB (7271)","아산S/S 345kV 7171,7172,7271 CB 개폐타임 측정","아산S/S 345kV 7171,7172,7271 CB 개폐타임 측정","2018-12-03 15:00","2018-12-03 18:00","2018-12-03 15:00","2018-12-03 18:00","당일"]
[66,"대전충남","아산","아산S/S TIE-#4 M.Tr 1차 CB (7800)","아산S/S 345kV 7800,7700,7371 CB 개폐타임 측정","아산S/S 345kV 7800,7700,7371 CB 개폐타임 측정","2018-12-04 09:00","2018-12-04 12:00","2018-12-04 09:00","2018-12-04 12:00","당일"]
[67,"대전충남","아산","아산S/S #4 M.Tr 1차 CB (7872)","아산S/S 345kV 7800,7872,7371 CB 개폐타임 측정","아산S/S 345kV 7800,7872,7371 CB 개폐타임 측정","2018-12-04 12:00","2018-12-04 15:00","2018-12-04 12:00","2018-12-04 15:00","당일"]
[68,"대전충남","아산","아산S/S 신서산-아산#2T/L CB (7371)","아산S/S 345kV 7800,7872,7371 CB 개폐타임 측정","아산S/S 345kV 7800,7872,7371 CB 개폐타임 측정","2018-12-04 15:00","2018-12-04 18:00","2018-12-04 15:00","2018-12-04 18:00","당일"]
[69,"대전충남","청양","신보령TP보령CC T/L","(주)와이피피제 보호계전기 성능개선","○345kV신보령연락T/L 송전선로 보호반 성능개선(양단)","2018-12-05 09:00","2018-12-05 18:00","2018-12-05 09:00","2018-12-05 18:00","당일"]
[70,"대전충남","청양","보령TP보령CC#2 T/L","(주)와이피피제 보호계전기 성능개선","○345kV보령연락#2T/L 송전선로 보호반 성능개선(양단)","2018-12-06 09:00","2018-12-06 18:00","2018-12-06 09:00","2018-12-06 18:00","당일"]
[71,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7471 GIS 교체 ○ 보령화력 345kV 7400 GIS 교체 ○ 보령화력 345kV 7472 GIS 교체","2018-12-11 09:00","2018-12-11 14:00","2018-12-11 09:00","2018-12-11 14:00","당일"]
[72,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7471 GIS 교체 ○ 보령화력 345kV 7400 GIS 교체 ○ 보령화력 345kV 7472 GIS 교체","2018-12-11 14:00","2018-12-14 18:00","2018-12-11 14:00","2018-12-14 18:00","연속"]
[73,"대전충남","청양","아산보령화력#2 T/L","(주)와이피피제 보호계전기 성능개선","○345kV아산-보령화력#2T/L 송전선로 보호반 성능개선(양단)","2018-12-04 09:00","2018-12-04 18:00","2018-12-04 09:00","2018-12-04 18:00","당일"]
[74,"대전충남","청양","청양보령화력#1 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7471 GIS 교체 ○ 보령화력 345kV 7400 GIS 교체 ○ 보령화력 345kV 7472 GIS 교체","2018-12-11 16:00","2018-12-14 18:00","2018-12-11 16:00","2018-12-14 18:00","연속"]
[75,"대전충남","청양","청양S/S #1 M.Tr 1차 CB (7671)","청양S/S 362kV GIS 러버히터 설치","청양S/S 362kV GIS 러버히터 설치(7671 CB)","2018-12-03 09:00","2018-12-03 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[76,"대전충남","청양","청양S/S #1M.Tr 1차-청양-보령#2T/L CB (7600)","청양S/S 362kV GIS 러버히터 설치","청양S/S 362kV GIS 러버히터 설치(7600 CB)","2018-12-04 09:00","2018-12-04 18:00","2018-12-04 09:00","2018-12-04 18:00","당일"]
[77,"대전충남","청양","청양보령복합 T/L","(주)와이피피제 보호계전기 성능개선","○345kV청양-보령복합T/L 송전선로 보호반 성능개선(양단)","2018-12-07 09:00","2018-12-07 18:00","2018-12-07 09:00","2018-12-07 18:00","당일"]
[78,"대전충남","청양","청양S/S #2 M.Tr A","청양S/S #2M.Tr 관련 보호배전반 성능개선","○청양S/S #2M.Tr 관련 보호배전반 성능개선","2018-12-03 09:00","2018-12-03 18:00","2018-12-03 09:00","2018-12-03 18:00","연속"]
[79,"전북","군산","군산S/S #4 M.Tr A","군산S/S #4 M.Tr A","군산 345kV 모자익 대체공사 #4M.Tr PNL T3 개조 시행 및 제어,감시,CT 등 이설","2018-12-17 09:00","2018-12-28 18:00","2018-12-17 09:00","2018-12-28 18:00","연속"]
[80,"전북","군산","군산S/S #3 M.Tr A","군산P/O 기타설비대체공사","군산S/S 345kV #3M.Tr 1차, 3차 피뢰기 교체","2018-12-03 09:00","2018-12-03 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[81,"전북","김제","신김제한빛NP#1 T/L","신김제 모자익배전반 교체공사","-. 제어라인 집감반 구성을 위한 73BAY휴전","2018-12-04 09:00","2018-12-08 18:00","2018-12-04 09:00","2018-12-08 18:00","연속"]
[82,"전북","김제","신김제S/S #2 M.Tr A","신김제 모자익배전반 교체공사","-. 제어라인 집감반 구성을 위한 73BAY휴전","2018-12-04 09:00","2018-12-08 18:00","2018-12-04 09:00","2018-12-08 18:00","연속"]
[83,"전북","김제","신김제한빛NP#2 T/L","모자익배전반 교체공사","-. 345kV 차단기 제어케이블 결선 및 시험","2018-12-10 09:00","2018-12-14 18:00","2018-12-10 09:00","2018-12-14 18:00","연속"]
[84,"전북","김제","신김제S/S #4 M.Tr A","모자익배전반 교체공사","-. 345kV 차단기 제어케이블 결선 및 시험","2018-12-24 09:00","2018-12-28 18:00","2018-12-24 09:00","2018-12-28 18:00","연속"]
[85,"전북","김제","신김제S/S #3 M.Tr A","모자익배전반 교체공사","-. 345kV 차단기 제어케이블 결선 및 시험","2018-12-17 09:00","2018-12-21 18:00","2018-12-17 09:00","2018-12-21 18:00","연속"]
[86,"전북","직할","신옥천신남원#2 T/L","신남원S/S 345kV 차단기 가스 누기개소 점검공사","○ 7100, 7200, 7300 CB 가스 누기개소 점검","2018-12-01 09:00","2018-12-03 18:00","2018-12-01 09:00","2018-12-03 18:00","연속"]
[87,"전북","직할","신남원한빛NP#2 T/L","신남원S/S 345kV 차단기 가스 누기개소 점검공사","○ 7100, 7200, 7300 CB 가스 누기개소 점검","2018-12-01 09:00","2018-12-03 18:00","2018-12-01 09:00","2018-12-03 18:00","연속"]
[88,"전북","직할","신남원광양#2 T/L","345kV 신남원-광양T/L 안전이격 확보공사","가. 철탑철거 : 2기 [No.214(T-14), No.216(F-21)] 나. 철탑설치 : 2기 [No.214(C2-26), No.216(SF-36)] 다. 전력선 교체 : 1.790km [ACSR 480㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기 (No.216","2018-12-01 09:00","2018-12-10 18:00","취소","취소","연속"]
[89,"전북","직할","신남원광양#1 T/L","345kV 신남원-광양T/L 안전이격 확보공사","가. 철탑철거 : 2기 [No.214(T-14), No.216(F-21)] 나. 철탑설치 : 2기 [No.214(C2-26), No.216(SF-36)] 다. 전력선 교체 : 1.790km [ACSR 480㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기 (No.216","2018-12-11 09:00","2018-12-16 18:00","취소","취소","연속"]
[90,"광주전남","광주","신광주S/S #2 M.Tr A","18년 광주 변전총액공사(신광주S/S #2 M.Tr)","#2M.Tr 1,2차 LA 교체, 부싱절연열화측정","2018-12-13 09:00","2018-12-14 18:00","2018-12-13 09:00","2018-12-14 18:00","연속"]
[91,"광주전남","광주","신남원신광주#2 T/L","18년 광주 변전총액공사(신남원신광주#2T/L)","신광주S/S 345kV 신남원신광주#2T/L LA 교체","2018-12-06 09:00","2018-12-07 18:00","2018-12-06 09:00","2018-12-07 18:00","연속"]
[92,"광주전남","광주","신광주S/S #3 M.Tr A","18년 광주 변전총액공사(신광주S/S #3 M.Tr)","#3 M.Tr 부싱절연열화측정","2018-12-05 09:00","2018-12-05 18:00","2018-12-05 09:00","2018-12-05 18:00","당일"]
[93,"광주전남","광주","신남원신광주#1 T/L","18년 광주 변전총액공사(신남원신광주#1T/L)","신광주S/S 345kV 신남원신광주#1T/L LA 교체","2018-12-04 09:00","2018-12-05 18:00","2018-12-04 09:00","2018-12-05 18:00","연속"]
[94,"광주전남","광주","신광주S/S #4 M.Tr A","18년 광주 변전총액공사(신광주S/S #4 M.Tr)","파급고장 방지 방압변 트립 Blocking 회로 구성(시험팀)","2018-12-03 09:00","2018-12-03 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[95,"광주전남","순천","광양S/S #2 M.Tr A","변압기 부싱 절연유 채유","광양S/S #2M.Tr 1,2차 부싱 절연유 채유","2018-12-27 10:00","2018-12-27 17:00","2018-12-27 10:00","2018-12-27 17:00","당일"]
[96,"광주전남","순천","광양S/S #1 M.Tr A","와이피피제 보호계전기 성능개선","와이피피제(L90,D60,F35) 보호계전기 모듈교체","2018-12-26 10:00","2018-12-26 18:00","2018-12-26 10:00","2018-12-26 18:00","당일"]
[97,"광주전남","강진","신화순신강진#2T/L","2018년 변전설비 차단기 및 개폐장치 조작시험","현장조작, 원방조작, 계전기 Trip 시험, 개폐타임 측정","2018-12-10 10:30","2018-12-11 12:00","2018-12-10 10:30","2018-12-11 12:00","연속"]
[98,"광주전남","강진","신강진광양#1T/L","2018년 변전설비 차단기 및 개폐장치 조작시험","현장조작, 원방조작, 계전기 Trip 시험, 개폐타임 측정","2018-12-28 09:30","2018-12-28 18:00","2018-12-28 09:30","2018-12-28 18:00","연속"]
[99,"광주전남","목포","한빛2NP한빛3NP #3T/L ","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","○ 362kV GIS(4000A,40kA) X 9CCT 철거\n○ 362kV GIS(6300A,63kA) X 9CCT 설치\n○ 기타부대공사 X 1식 ","2018-12-20 09:00 ","2019-02-13 18:00","2018-12-21 09:00 ","2019-02-13 18:00","연속"]
[100,"대구","달성","고령의령#1 T/L","달성전력지사 고령S/S 차단기동작특성시험","달성전력지사 고령S/S 차단기동작특성시험","2018-12-04 09:00","2018-12-04 18:00","2018-12-07 09:00","2018-12-07 18:00","당일"]
[101,"대구","달성","대구S/S #1 M.Tr A","달성전력지사 대구S/S 1차 차단기동작특성시험","달성전력지사 대구S/S 1차 차단기동작특성시험","2018-12-06 09:00","2018-12-06 12:00","2018-12-09 09:00","2018-12-09 13:00","당일"]
[102,"대구","달성","북경남대구#2 T/L","154kV 고령-다산 등 17개T/L 피뢰기 설치공사","피뢰기 설치공사 안전확보","2018-12-02 07:00","2018-12-02 18:00","2018-12-02 07:00","2018-12-02 18:00","당일"]
[103,"대구","달성","대구S/S 345kV #2 Sh.R CB (7279)","달성전력지사 대구S/S 차단기동작특성시험","달성전력지사 대구S/S 차단기동작특성시험","2018-12-06 15:00","2018-12-06 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[104,"대구","달성","대구S/S #2 M.Tr A","달성전력지사 대구S/S 1차 차단기동작특성시험","달성전력지사 대구S/S 1차 차단기동작특성시험","2018-12-06 12:00","2018-12-06 15:00","2018-12-09 13:00","2018-12-09 18:00","당일"]
[105,"대구","칠곡","북대구S/S #1 Sh.R CB","북대구S/S 345kV #1Sh.R 7679,7671 GIS 초기점검","북대구S/S 345kV #1Sh.R 7679,7671 GIS 초기점검","2018-12-14 09:30","2018-12-14 18:00","2018-12-13 09:30","2018-12-13 18:00","당일"]
[106,"대구","칠곡","북대구서대구#1 T/L","북대구S/S 362kV GIS 인출조정 공사","북대구-서대구#1↔#2T/L 인출 변경","2018-12-03 09:30","2018-12-09 18:00","2018-12-03 09:30","2018-12-11 18:00","연속"]
[107,"대구","칠곡","서대구고령#1 T/L","154kV 서대구-남구미#1T/L 피뢰기 설치공사 안전확보 휴전","154kV 서대구-남구미#1T/L 피뢰기 설치공사 안전확보 휴전 서대구-남구미 No9 병가구간","2018-12-03 08:00","2018-12-03 18:00","취소","취소","당일"]
[108,"대구","칠곡","서대구S/S #2 M.Tr A","서대구S/S #2M.Tr 부싱절연유 채유","서대구S/S #2M.Tr 부싱절연유 채유","2018-12-03 09:30","2018-12-03 14:00","2018-12-05 09:30","2018-12-05 14:00","당일"]
[109,"대구","칠곡","서대구S/S #1 M.Tr 1차 CB (7171)","서대구S/S #1M.Tr 1차 7171CB 장기미동작점검","서대구S/S #1M.Tr 1차 7171CB 장기미동작점검","2018-12-17 09:30","2018-12-17 15:00","2018-12-14 09:30","2018-12-14 15:00","당일"]
[110,"대구","칠곡","서대구S/S #4 M.Tr A","서대구S/S 345kV #4M.Tr 부싱절연유 채유","서대구S/S 345kV #4M.Tr 부싱절연유 채유","2018-12-04 09:30","2018-12-04 14:00","2018-12-04 09:30","2018-12-04 14:00","당일"]
[111,"대구","칠곡","서대구S/S #3 M.Tr A","서대구S/S #3M.Tr 부싱절연유 채유","서대구S/S #3M.Tr 부싱절연유 채유","2018-12-03 14:00","2018-12-03 18:00","2018-12-05 14:00","2018-12-05 18:00","당일"]
[112,"대구","포항","신영일S/S #3 M.Tr A","신영일S/S #3M.Tr 보호반 대체","신영일S/S #3M.Tr 보호반 대체","2018-12-01 09:00","2018-12-04 18:00","2018-12-01 09:00","2018-12-04 18:00","연속"]
[113,"대구","포항","신포항S/S 신포항-청송T/L CB (7771)","신포항S/S 7771 CB 조작시험","신포항S/S 7771 CB 조작시험","2018-12-11 09:00","2018-12-11 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[114,"대구","포항","신포항S/S 신포항-신월성NP#4T/L CB (7272)","신포항S/S 7272 CB 조작시험","신포항S/S 7272 CB 조작시험","2018-12-10 09:00","2018-12-10 18:00","2018-12-06 09:00","2018-12-06 18:00","당일"]
[115,"대구","포항","신포항신월성NP#2 T/L","신포항신월성NP#2 T/L YPP제 성능개선","신포항신월성NP#2 T/L YPP제 성능개선","2018-12-05 10:00","2018-12-06 18:00","2018-12-05 10:00","2018-12-06 18:00","매일"]
[116,"대구","포항","신포항S/S #1 M.Tr A","신포항S/S 154kV 옥외철구 설비 GIS화 공사","- 전력구 기초 가시설 설치관련 안전이격거리 확보","2018-12-05 08:00","2018-12-07 18:00","2018-12-14 08:00","2018-12-15 18:00","연속"]
[117,"경북","구미","선산신포항 T/L","345kV 선산분기 등 12개T/L 송전선로용 피뢰기 설치공사","345kV 선산-신포항 T/L 송전선로용 피뢰기 설치공사","2018-12-03 09:00","2018-12-03 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[118,"경북","영주","신영주한울NP2#2 T/L","신영주S/S TCSC 건설공사","- 345kV GIS(63kA 6,300A) DS 및 GIB * 1식 설치","2018-12-17 09:00","2018-12-21 18:00","취소","취소","연속"]
[119,"경북","영주","신영주한울NP2#1 T/L","신영주S/S TCSC 건설공사","- 345kV GIS(63kA 6,300A) DS 및 GIB * 1식 설치","2018-12-03 09:00","2018-12-14 18:00","취소","취소","연속"]
[120,"경북","영주","삼척GP한울NP1#1 T/L","YPP제 계전기 성능개선 공사","YPP제 계전기 성능개선 공사","2018-12-11 09:00","2018-12-11 18:00","2018-12-11 09:00","2018-12-11 18:00","당일"]
[121,"부산울산","동부산","신양산S/S #3 M.Tr A","345kV 신양산S/S 현대화 공사","154kV GIS 붓싱설치 및 기태부대작업(안전이격)","2018-12-13 09:00","2018-12-13 18:00","취소","취소","당일"]
[122,"부산울산","동부산","신양산S/S #1 M.Tr A","345kV 신양산S/S 현대화 공사","154kV GIS 붓싱설치 및 기태부대작업(안전이격)","2018-12-11 09:00","2018-12-11 18:00","취소","취소","당일"]
[123,"부산울산","동부산","신양산S/S #4 M.Tr A","345kV 신양산S/S 현대화 공사","154kV GIS 붓싱설치 및 기태부대작업(안전이격)","2018-12-14 09:00","2018-12-14 18:00","취소","취소","당일"]
[124,"부산울산","동부산","신양산S/S #2 M.Tr A","345kV 신양산S/S 현대화 공사","154kV GIS 붓싱설치 및 기태부대작업(안전이격)","2018-12-12 09:00","2018-12-12 18:00","취소","취소","당일"]
[125,"부산울산","북부산","신김해북부산#1 T/L","345kV 북부산S/S 차단기용량대체공사","북부산S/S 구내 가공지선 철거(신김해-북부산#1,2 T/L 횡단개소)","2018-12-03 07:00","2018-12-12 18:00","취소","취소","연속"]
[126,"부산울산","북부산","신김해북부산#2 T/L","345kV 북부산S/S 차단기용량대체공사","북부산S/S 구내 가공지선 철거(신김해-북부산#1,2 T/L 횡단개소)","2018-12-09 09:00","2018-12-09 12:00","취소","취소","당일"]
[127,"부산울산","서부산","서부산S/S 서부산-북부산#3T/L CB (7371)","서부산S/S 서부산-북부산#3T/L CB(7371) 개폐타임","서부산S/S 서부산-북부산#3T/L CB(7371) 개폐타임","2018-12-03 10:00","2018-12-03 14:00","2018-12-03 10:00","2018-12-03 14:00","당일"]
[128,"부산울산","서부산","신녹산S/S 신김해#2T/L-#3 M.Tr 1차 CB (7300)","신녹산S/S 신김해#2T/L-#3M.Tr1차 CB(7300) 타임측정","신녹산S/S 신김해#2T/L-#3M.Tr1차 CB(7300) 타임측정","2018-12-05 14:00","2018-12-05 18:00","2018-12-05 14:00","2018-12-05 18:00","당일"]
[129,"부산울산","서부산","신녹산S/S 신김해-신녹산#2T/L CB (7371)","신녹산S/S 신김해-신녹산#2T/L GIS(7371) 개폐타임 측정","신녹산S/S 신김해-신녹산#2T/L GIS(7371) 개폐타임 측정","2018-12-05 10:00","2018-12-05 14:00","2018-12-05 10:00","2018-12-05 14:00","당일"]
[130,"부산울산","울산","신온산S/S #1 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","신온산S/S 345kV #1M.Tr 보통점검 신온산S/S 345kV 7200,7272 차단기 동작시험 신온산S/S 154kV 6144 GIS, 23kV 6484 CB 보통점검","2018-12-05 09:00","2018-12-06 18:00","2018-12-05 13:00","2018-12-06 18:00","연속"]
[131,"부산울산","울산","신온산S/S #4 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","신온산S/S 345kV #4M.Tr A,B상 하자점검 신온산S/S 362kV 7672,7600 GIS, 154kV 6444 GIS 하자점검","2018-12-04 09:00","2018-12-05 18:00","2018-12-04 09:00","2018-12-05 13:00","연속"]
[132,"부산울산","울산","신울산S/S #5 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","1.신울산S/S 345kV #5M.Tr 보통점검 2.신울산S/S 154kV 6564 GIS 보통점검","2018-12-03 09:00","2018-12-04 18:00","2018-12-03 09:00","2018-12-04 18:00","연속"]
[133,"부산울산","울산","북부산울산TP T/L","2018-19년 울산전력지사 변전협력회사 총액공사","울산복합 345kV 75Bay B/F PNL 대체(발전기 정지관련 병행작업)","2018-12-03 09:00","2018-12-07 18:00","2018-12-03 09:00","2018-12-07 18:00","연속"]
[134,"부산울산","울산","울산C/C 기력5호기 1차 CB (7572)","2018-19년 울산전력지사 변전협력회사 총액공사","울산복합 345kV 75Bay B/F PNL 대체(발전기 정지관련 병행작업)","2018-12-03 09:00","2018-12-07 18:00","2018-12-03 09:00","2018-12-07 18:00","연속"]
[135,"부산울산","울산","울산C/C #3 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","울산C/C 345kV #3M.Tr 보통점검 및 2차 차단기 동작시험","2018-12-01 09:00","2018-12-02 18:00","2018-12-01 09:00","2018-12-02 18:00","연속"]
[136,"부산울산","울산","울주월성NP#1 T/L","2018-19년 울산전력지사 변전협력회사 총액공사","1.울주S/S 345kV 7900 GIS 보통점검 및 7971 차단기 동작시험 2.울주S/S 345kV 울주-월성NP#1T/L CVT,LA 대체","2018-12-03 09:00","2018-12-04 14:00","2018-12-03 09:00","2018-12-04 14:00","연속"]
[137,"부산울산","울산","울주S/S #4 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","1.울주S/S 345kV #4M.Tr ABB 부싱절연유 채유 2.울주S/S 345kV 7872 차단기 동작시험","2018-12-08 09:00","2018-12-08 18:00","2018-12-08 09:00","2018-12-08 18:00","당일"]
[138,"부산울산","울산","울주S/S #2 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사","울주S/S 345kV #2M.Tr, 7472,7400 GIS 및 154kV 6244 GIS 초기점검","2018-12-06 09:00","2018-12-07 18:00","2018-12-06 09:00","2018-12-07 18:00","연속"]
[139,"부산울산","울산","울주월성NP#2 T/L","2018-19년 울산전력지사 변전협력회사 총액공사","1.울주S/S 345kV 7A71 GIS 보통점검 및 7A00 차단기 동작시험 2.울주S/S 345kV 울주-월성NP#2T/L CVT,LA 대체","2018-12-04 14:00","2018-12-05 18:00","2018-12-04 14:00","2018-12-05 18:00","연속"]
[140,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산T/L 78호 지장송전선로 이설공사","345kV 신김해-북부산T/L 77~81호 간 지장이설공사[가탑 1기]","2018-12-10 08:00","2018-12-13 18:00","취소","취소","연속"]
[141,"경남","직할","신김해북부산#1 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신김해-주촌#2T/L LA설치 안전이격확보","2018-12-29 12:00","2018-12-29 18:00","2018-12-29 12:00","2018-12-29 18:00","당일"]
[142,"경남","직할","신김해북부산#1 T/L","신김해S/S 170kV 장기사용GIS 대체공사","신김해S/S 170kV 장기사용GIS 대체공사(시험가압선로) 7371CB 개방으로 B/F 동작 방지","2018-12-07 17:30","2018-12-08 17:30","2018-12-07 17:30","2018-12-08 17:30","연속"]
[143,"경남","직할","신김해신녹산#1 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신김해-주촌#2T/L LA설치 안전이격 확보","2018-12-29 08:00","2018-12-29 12:00","2018-12-29 08:00","2018-12-29 12:00","당일"]
[144,"경남","직할","신김해창원#2 T/L","345kV 창원S/S 예비M.Tr 시험가압 및 사용전검사","345kV 창원S/S 예비M.Tr 절체 및 시험가압","2018-12-01 09:30","2018-12-02 09:30","2018-12-01 09:30","2018-12-02 09:30","연속"]
[146,"경남","직할","창원S/S 345kV #2 BUS","345kV 창원S/S 예비M.Tr 시험가압 및 사용전검사","345kV 창원S/S 예비M.Tr 절체 및 시험가압","2018-12-01 09:30","2018-12-02 09:30","2018-12-01 09:30","2018-12-02 09:30","연속"]
[147,"경남","진주","의령산청양수#1 T/L","의령S/S 의령산청양수#1 T/L PT(3상) 보통점검","의령S/S 의령산청양수#1 T/L PT(3상) 보통점검","2018-12-19 09:30","2018-12-19 18:30","취소","취소","당일"]
[148,"경남","진주","의령산청양수#2 T/L","의령S/S 의령산청양수#2 T/L PT(3상) 보통점검","의령S/S 의령산청양수#2 T/L PT(3상) 보통점검","2018-12-20 09:30","2018-12-20 18:30","취소","취소","당일"]
[149,"경남","진주","하동T/P 75-76-0 SEC CB (75-76-0)","하동T/P 70-71, 75-76 B/F PNL 대체","하동T/P 70-71, 75-76 B/F PNL 대체","2018-12-03 09:30","2018-12-09 18:30","취소","취소","연속"]
[150,"경남","진주","하동T/P 70-71-0 SEC CB (70-71-0)","하동T/P 70-71, 75-76 B/F PNL 대체","하동T/P 70-71, 75-76 B/F PNL 대체","2018-12-03 09:30","2018-12-09 18:30","취소","취소","연속"]
[151,"경남","함안","신마산삼천포화력#2 T/L","345kV 신마산S/S 차단기 대체관련 가공송전선로 인출변경공사","○ 신설 345kV 신마산-삼천포화력T/L 176호 철탑 조립을 위한 안전이격확보","2018-12-01 07:00","2018-12-04 19:00","2018-12-01 07:00","2018-12-04 19:00","연속"]
[152,"경남","함안","신마산S/S #4 M.Tr A","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 인출변경 - #4M.Tr 1차 인출변경 작업","2018-12-06 07:00","2018-12-22 18:00","2018-12-06 07:00","2018-12-22 18:00","연속"]
[153,"경남","함안","의령신마산#1 T/L","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 인출변경 - 의령-신마산#1T/L 인출 변경","2018-12-12 06:30","2018-12-17 18:00","취소","취소","연속"]
[154,"경남","함안","의령신마산#2 T/L","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 인출변경 - 의령-신마산#1T/L 인출 변경","2018-12-18 06:30","2018-12-23 18:00","취소","취소","연속"]
[155,"경남","함안","신마산삼천포화력#2 T/L","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 인출변경 - 신마산-삼천포#2T/L 인출 변경","2018-12-24 06:30","2018-12-29 18:00","취소","취소","연속"]
[156,"경남","함안","신마산삼천포화력#1 T/L","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 인출변경 - 신마산-삼천포#1T/L 인출 변경","2018-12-30 06:30","2019-01-04 18:00","취소","취소","연속"]
[157,"경남","함안","신마산S/S #5M.Tr A","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산S/S 용량부족 차단기 대체공사 인출변경 - #5M.Tr 1차 인출변경 작업","2018-12-23 07:00","2019-01-08 18:00","2018-12-23 07:00","2019-01-08 18:00","연속"]
[158,"경북","한울본부","한울NP6호기 주변압기 CB(7C00,7C72)","○ 주변압기 B상 교체\n○ 주/소내보조/여자변압기 일반점검","○ 주변압기 B상 교체\n○ 주/소내보조/여자변압기 일반점검","2018-12-02 09:00","2019-01-01 17:00","2018-12-02 09:00","2019-01-01 17:00","연속"]

{"sheet":"154송부","index":2,"n_rows":325,"n_cols":16,"rows_kept":325,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
["2018년도 12월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","금오상계#1 T/L","2018년 성동P/O 변전협력회사 총액공사","LA 보통점검 (상계S/S 금오상계#1T/L)","2018-12-06 09:30","2018-12-06 17:00","2018-12-06 09:30","2018-12-06 17:00","당일"]
[2,"서울","직할","서소문S/S 154kV #1 BUS TIE CB","18년 직할 변전협력 총액공사","조작시험, 170kV SPRING DISCHARGED 경보 회로 보강","2018-12-10 09:00","2018-12-10 18:00","2018-12-03 09:00","2018-12-03 18:00","당일"]
[3,"서울","직할","종로서소문 T/L","18년 직할 변전협력 총액공사","송전선로 보호반 대체","2018-12-11 09:00","2018-12-14 18:00","취소","취소","연속"]
[4,"서울","직할","중앙서소문 T/L","18년 직할 변전협력 총액공사","송전선로 보호반 대체","2018-12-03 09:00","2018-12-06 18:00","2018-12-04 09:00","2018-12-11 18:00","연속"]
[5,"남서울","강남","대치S/S 154kV #1 BUS","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#1T/L, #1M.Tr 1차, 6100 BUS TIE GIS #1DS 철거","2018-12-17 10:00","2018-12-20 18:00","2018-12-17 10:00","2018-12-20 18:00","연속"]
[6,"남서울","강남","대치S/S 154kV #1 BUS","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#2T/L, BUS PT #1BUS 철거 및 설치","2018-12-03 10:00","2018-12-07 18:00","2018-12-03 10:00","2018-12-07 18:00","연속"]
[7,"남서울","강남","강남대치#1 T/L","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#2T/L, BUS PT #1BUS 무부하가압","2018-12-07 16:00","2018-12-07 18:00","2018-12-07 16:00","2018-12-07 18:00","당일"]
[8,"남서울","강남","대치S/S 154kV #2 BUS","대치S/S 장기사용GIS 대체공사","154kV #2BUS PT 케이블 이설(임시분전반 → PT LCP)","2018-12-08 10:00","2018-12-09 18:00","2018-12-08 10:00","2018-12-09 18:00","연속"]
[9,"남서울","강남","대치S/S 154kV #2 BUS","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#2T/L 무부하가압","2018-12-11 18:00","2018-12-12 18:00","2018-12-11 18:00","2018-12-12 18:00","연속"]
[10,"남서울","강남","대치S/S 154kV #1 BUS TIE CB","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#1T/L, #1M.Tr 1차, 6100 BUS TIE GIS 대체공사","2018-12-13 10:00","2019-01-19 18:00","2018-12-13 10:00","2019-01-19 18:00","연속"]
[11,"남서울","강남","강남대치#1 T/L","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#1T/L, #1M.Tr 1차, 6100 BUS TIE GIS 대체공사","2018-12-13 10:00","2019-01-19 18:00","2018-12-13 10:00","2019-01-19 18:00","연속"]
[12,"남서울","강남","대치S/S 154kV #2 BUS","대치S/S 장기사용GIS 대체공사","154kV 대치-강남#1T/L, #1M.Tr 1차, 6100 BUS TIE GIS #2DS 철거","2018-12-13 10:00","2018-12-15 18:00","2018-12-13 10:00","2018-12-15 18:00","연속"]
[13,"남서울","강남","강남대치#2 T/L","대치S/S 장기사용GIS 대체공사","154kV #1BUS 무부하가압","2018-12-20 16:00","2018-12-20 18:00","2018-12-20 16:00","2018-12-20 18:00","당일"]
[14,"남서울","강남","강남대치#1 T/L","대치S/S 장기사용GIS 대체공사","154kV #1BUS PT 및 대치-강남#2T/L #1DS 무부하가압","2018-12-01 16:00","2018-12-01 18:00","2018-12-01 16:00","2018-12-01 18:00","당일"]
[15,"남서울","강남","강남대치#2 T/L","대치S/S 장기사용GIS 대체공사","154kV #2BUS 무부하가압","2018-12-15 16:00","2018-12-15 18:00","2018-12-15 16:00","2018-12-15 18:00","당일"]
[16,"남서울","동서울","강동천호#1 T/L","송전선로 보호반 교체공사","송전선로 보호반 교체공사","2018-12-03 09:00","2018-12-05 14:00","2018-12-03 09:00","2018-12-05 14:00","연속"]
[17,"남서울","동서울","강동천호#2 T/L","송전선로 보호반 교체공사","송전선로 보호반 교체공사","2018-12-05 14:00","2018-12-07 18:00","2018-12-05 14:00","2018-12-07 18:00","연속"]
[18,"인천","김포","신경서왕길#2 T/L","154kV신경서-왕길#2T/L 정밀점검","154kV신경서-왕길#2T/L 정밀점검","2018-12-10 08:00","2018-12-11 18:00","2018-12-10 08:00","2018-12-11 18:00","연속"]
[19,"인천","시흥","도림오봉 T/L","154kV 도림S/S #3M.Tr 증설사업","도림S/S TR용 GIS 1CCT 가압","2018-12-04 09:00","2018-12-05 18:00","2018-12-21 09:00","2018-12-22 18:00","연속"]
[20,"인천","시흥","도림S/S 154kV #1 BUS","154kV 도림S/S #3M.Tr 증설사업","154kV GIS 1CCT 설치(TR용)","2018-12-01 18:00","2018-12-05 18:00","2018-12-17 09:00","2018-12-22 14:00","연속"]
[21,"인천","시흥","북시화서시화#1 T/L","선도전기 154kV 송전선로 보호반 성능개선","보호계전기 ROM & 소프트웨어 업데이트 작업","2018-12-03 10:30","2018-12-03 18:00","2018-12-15 10:30","2018-12-15 18:00","당일"]
[22,"인천","시흥","북시화서시화#2 T/L","선도전기 154kV 송전선로 보호반 성능개선","보호계전기 ROM & 소프트웨어 업데이트 작업","2018-12-04 10:30","2018-12-04 18:00","2018-12-16 10:30","2018-12-16 18:00","당일"]
[23,"인천","시흥","서서울#2소래 T/L","154kV 서서울소래T/L(OPGW) 항공장애표시구 설치공사","154kV 서서울소래T/L(OPGW) 항공장애표시구 설치공사 - 설치구간 OPGW 1조 이므로 양회선 동시휴전 필요 - 서서울2소래(좌)-서서울2서안양(우), 서서울2소래(좌)-서안양소래(우)","2018-12-03 08:00","2018-12-04 18:00","2018-12-03 08:00","2018-12-04 18:00","연속"]
[24,"인천","시흥","서안양소래 T/L","154kV 서서울소래T/L(OPGW) 항공장애표시구 설치공사","154kV 서서울소래T/L(OPGW) 항공장애표시구 설치공사 - 설치구간 OPGW 1조 이므로 양회선 동시휴전 필요 - 서서울2소래(좌)-서서울2서안양(우), 서서울2소래(좌)-서안양소래(우)","2018-12-04 14:00","2018-12-04 18:00","2018-12-04 14:00","2018-12-04 18:00","당일"]
[25,"인천","시흥","도림오봉 T/L","154kV 도림-오봉T/L 자기애관 교체공사","자기애관 교체공사(6상)","2018-12-06 09:00","2018-12-08 18:00","2018-12-06 09:00","2018-12-08 18:00","연속"]
[26,"인천","시흥","신시흥오봉 T/L","154kV 신시흥-오봉T/L 자기애관 교체공사","자기애관 교체공사(6상)","2018-12-03 09:00","2018-12-05 18:00","취소","취소","연속"]
[27,"인천","인천","신가좌주안#2 T/L","154kV신가좌-주안T/L 태풍취약철탑 보강공사","154kV신가좌-주안T/L No.5 태풍취약철탑 보강공사","2018-12-06 08:00","2018-12-08 18:00","취소","취소","연속"]
[28,"인천","인천","신가좌주안#1 T/L","154kV신가좌-주안T/L 태풍취약철탑 보강공사","154kV신가좌-주안T/L No.5 태풍취약철탑 보강공사","2018-12-03 08:00","2018-12-05 18:00","취소","취소","연속"]
[29,"인천","인천","신가좌신현#2 T/L","신현,신가좌S/S 신가좌신현#2T/L GIS 초기점검 및 조작시험","신현S/S 신가좌신현#2T/L GIS 초기점검 신가좌S/S 신가좌신현#2T/L GIS 조작시험","2018-12-13 09:00","2018-12-13 18:00","2018-12-13 09:00","2018-12-13 18:00","연속"]
[30,"인천","인천","신가좌신현#1 T/L","신현,신가좌S/S 신가좌신현#1T/L GIS 초기점검 및 조작시험","신현S/S 신가좌신현#1T/L GIS 초기점검 신가좌S/S 신가좌신현#1T/L GIS 조작시험","2018-12-10 09:00","2018-12-10 18:00","2018-12-10 09:00","2018-12-10 18:00","당일"]
[31,"경기북부","고양","지도능곡#2 T/L","2018년도 고양전력지사 변전협력회사 총액공사","능곡 지도능곡#2T/L 차단기 조작시험","2018-12-05 10:00","2018-12-05 14:00","2018-12-05 10:00","2018-12-05 14:00","당일"]
[32,"경기북부","고양","신파주금촌#2 T/L","154kV 신파주#64D.Tr 증설공사","- 154kV M.Tr 1Bank 개조 설치 - 170kV GIS 1CCT 설치 - 25.8kV GIS 3CCT 설치","2018-12-06 10:00","2018-12-07 17:00","2018-12-06 10:00","2018-12-07 17:00","연속"]
[33,"경기북부","고양","신파주S/S 154kV #66 BUS","154kV 신파주#64D.Tr 증설공사","- 154kV M.Tr 1Bank 개조 설치 - 170kV GIS 1CCT 설치 - 25.8kV GIS 3CCT 설치","2018-12-03 10:00","2018-12-07 17:00","2018-12-03 10:00","2018-12-07 17:00","연속"]
[34,"경기북부","고양","원흥수색#2 T/L","154kV 원흥-수색T/L 지중화 정비공사","154kV C/H철탑 2기 설치 No.4~C/H1, No.8~C/H2 구간 전력선 공중이동 임시철탑 2기 철거","2018-12-08 08:00","2018-12-09 18:00","취소","취소","연속"]
[35,"경기북부","고양","원흥수색#1 T/L","154kV 원흥-수색T/L 지중화 정비공사","154kV C/H철탑 2기 설치 No.4~C/H1, No.8~C/H2 구간 전력선 공중이동 임시철탑 2기 철거","2018-12-01 08:00","2018-12-02 18:00","취소","취소","연속"]
[36,"경기북부","고양","일산S/S 60-61-0 SEC CB","2018년도 고양전력지사 변전협력회사 총액공사","일산 60-61 SEC 차단기 조작시험","2018-12-06 10:00","2018-12-06 14:00","2018-12-06 10:00","2018-12-06 14:00","당일"]
[37,"경기북부","고양","일산S/S 65-66-0 SEC CB","2018년도 고양전력지사 변전협력회사 총액공사","일산 65-66 SEC 차단기 조작시험","2018-12-07 10:00","2018-12-07 14:00","2018-12-07 10:00","2018-12-07 14:00","당일"]
[38,"경기북부","고양","일산S/S 154kV #1 BUS TIE GIS","18년 고양전력지사 변전협력총액공사","170kV GIS 보통점검","2018-12-04 10:00","2018-12-04 18:00","2018-12-04 10:00","2018-12-04 18:00","당일"]
[39,"경기북부","고양","일산S/S 일산-호수#2T/L GIS","2018년 고양P/O 변전정비회사 총액공사","GIS 조작시험","2018-12-04 09:00","2018-12-04 18:00","2018-12-04 09:00","2018-12-04 18:00","당일"]
[40,"경기북부","구리","미금구리#2 T/L","보호계전기(가보제) 내부 캐패시터 Recall에 따른 성능개선","- 송전선로 보호반(7SD86:87) 확장형 모듈 교체 등","2018-12-01 09:30","2018-12-01 12:00","2018-12-01 09:30","2018-12-01 12:00","당일"]
[41,"경기북부","구리","미금구리#1 T/L","구리전력 154kV GIS 장기무동작 점검","구리전력 154kV GIS 장기무동작 점검","2018-12-02 09:00","2018-12-02 18:00","2018-12-02 09:00","2018-12-02 18:00","당일"]
[42,"경기북부","구리","진건별내#1 T/L","지중송전선로 조립식 중간접속함(PMJ) 전량교체공사","일진제 조립식 중간접속함 9상 교체","2018-12-22 08:00","2018-12-28 18:00","취소","취소","연속"]
[43,"경기북부","구리","신포천포천#2 T/L","2018~2019년 경기북부직할 가공송전정비 협력회사 총액공사","154kV 신포천-포천#2T/L No.1-5 피뢰기 설치공사","2018-12-03 08:00","2018-12-04 18:00","2018-12-07 08:00","2018-12-08 18:00","연속"]
[44,"경기북부","구리","포천S/S 154kV #1 BUS TIE CB","포천S/S 모선보호반 교체공사","장기사용 보호반 교체공사","2018-12-03 09:00","2018-12-07 18:00","2018-12-03 09:00","2018-12-07 18:00","연속"]
[45,"경기북부","직할","신의정부내촌#1 T/L","2018~2019년 경기북부직할 가공송전정비 협력회사 총액공사","154kV 신의정부-내촌#1T/L No.1-4 피뢰기 설치공사","2018-12-05 08:00","2018-12-06 18:00","2018-12-05 08:00","2018-12-06 18:00","연속"]
[46,"경기북부","직할","신의정부송우#2 T/L","2018~2019년 경기북부직할 가공송전정비 협력회사 총액공사","154kV 신의정부-송우#2T/L No.1-4 피뢰기 설치공사","2018-12-05 08:00","2018-12-06 18:00","2018-12-05 08:00","2018-12-06 18:00","연속"]
[47,"경기북부","직할","양주금촌#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주금촌#1T/L 인출측 전력구공사","2018-12-01 07:30","2018-12-05 18:00","2018-12-01 07:30","2018-12-05 18:00","연속"]
[48,"경기북부","직할","양주불광#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주불광#2T/L 인출측 전력구공사","2018-12-06 07:30","2018-12-10 18:00","취소","취소","연속"]
[49,"경기북부","직할","양주고양#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주고양#1 T/L 인출측 전력구공사","2018-12-06 07:30","2018-12-10 18:00","2018-12-06 07:30","2018-12-10 18:00","연속"]
[50,"경기북부","직할","양주고양#2 T/L","양주 S/S 옥외철구 GIS화 전력구공사","양주고양#2T/L 인출측 전력구공사","2018-12-01 07:30","2018-12-05 18:00","2018-12-01 07:30","2018-12-05 18:00","연속"]
[51,"경기","군포","관양동안양#1 T/L","관양-동안양 #1T/L 조작시험","관양-동안양 #1T/L 조작시험","2018-12-04 09:00","2018-12-04 13:00","2018-12-04 09:00","2018-12-04 13:00","당일"]
[52,"경기","군포","관양동안양#2 T/L","관양-동안양 #2T/L 조작시험","관양-동안양 #2T/L 조작시험","2018-12-04 13:00","2018-12-04 18:00","2018-12-04 13:00","2018-12-04 18:00","당일"]
[53,"경기","군포","마도사강#2 T/L","제어IED 성능개선 작업","개폐시간 측정관련 기능 보강","2018-12-01 09:00","2018-12-01 14:00","2018-12-01 09:00","2018-12-01 14:00","당일"]
[54,"경기","군포","화성마도 T/L","제어IED 성능개선 작업","개폐시간 측정관련 기능 보강","2018-12-01 14:00","2018-12-01 18:00","2018-12-01 14:00","2018-12-01 18:00","당일"]
[55,"경기","군포","반월시화#1 T/L","반월시화1TL 불량보호반 대체공사","반월 및 시화변전소 반월시화1TL 보호계전기 불량발생으로 보호반 대체","2018-12-10 09:00","2018-12-13 18:00","취소","취소","연속"]
[56,"경기","군포","반월시화#2 T/L","2018~19년도 송전정비회사 총액공사","전선교체, 금구류 교체","2018-12-08 07:00","2018-12-10 18:00","2018-12-08 07:00","2018-12-10 18:00","연속"]
[57,"경기","군포","반월시화#1 T/L","2018~19년도 송전정비회사 총액공사","전선교체, 금구류 교체","2018-12-03 07:00","2018-12-07 18:00","2018-12-03 07:00","2018-12-07 18:00","연속"]
[58,"경기","군포","산본안양#2 T/L","154kV 남군포S/S 건설공사","- 주요 변전설비 실부하 가압 및 사용전검사","2018-12-26 10:00","2018-12-28 17:00","2018-12-26 10:00","2018-12-28 17:00","연속"]
[59,"경기","군포","산본안양#2 T/L","154kV 남군포S/S 건설공사","- 주요 변전설비 무부하가압","2018-12-20 10:00","2018-12-21 17:00","2018-12-20 10:00","2018-12-21 17:00","연속"]
[60,"경기","군포","서서울서수원#2 T/L","2018-2019년 송전정비회사 총액공사","1~3호 1가닥 전선 교체","2018-12-02 07:00","2018-12-02 14:00","2018-12-02 07:00","2018-12-02 14:00","당일"]
[61,"경기","군포","서서울율전#1 T/L","가공송전위탁공사 초기점검","154kV서서울-율전#1T/L No.6~15 초기점검","2018-12-05 09:00","2018-12-05 18:00","2018-12-05 09:00","2018-12-05 18:00","당일"]
[62,"경기","군포","서서울율전#2 T/L","2018-2019년 송전정비회사 총액공사","피뢰기 설치 : 1~5호","2018-12-02 14:00","2018-12-03 18:00","2018-12-02 14:00","2018-12-03 18:00","연속"]
[63,"경기","군포","서서울#2서안양 T/L","154kV 서서울소래T/L(OPGW) 항공장애표시구 설치공사","154kV 서서울소래T/L(OPGW) 항공장애표시구 설치공사 - 설치구간 OPGW 1조 이므로 양회선 동시휴전 필요 - 서서울2소래(좌)-서서울2서안양(우), 서서울2소래(좌)-서안양소래(우)","2018-12-03 08:00","2018-12-04 14:00","2018-12-03 08:00","2018-12-04 14:00","연속"]
[64,"경기","군포","서안양S/S 삼천리#2T/L GIS","18년 군포변전 총액- 서안양SS 삼천리 #2TL","서안양SS 삼천리 #2TL 조작시험","2018-12-11 10:00","2018-12-11 18:00","2018-12-11 10:00","2018-12-11 18:00","당일"]
[65,"경기","군포","서안양S/S 삼천리#1T/L GIS","18년 군포변전 총액- 서안양SS 삼천리 #1TL","서안양SS 삼천리 #1TL 조작시험","2018-12-10 10:00","2018-12-10 18:00","2018-12-10 10:00","2018-12-10 18:00","당일"]
[66,"경기","군포","신시흥시화#2 T/L","2018~19년도 송전정비회사 총액공사 관련 안전이격거리확보","전선교체, 피뢰기설치, 금구류 교체 관련 안전이격거리확보","2018-12-03 07:00","2018-12-07 18:00","2018-12-03 07:00","2018-12-07 18:00","연속"]
[67,"경기","군포","신시흥시화#1 T/L","2018~19년도 송전정비회사 총액공사 관련 안전이격거리확보","전선교체, 금구류 교체 관련 안전이격거리확보","2018-12-08 07:00","2018-12-10 18:00","2018-12-08 07:00","2018-12-10 18:00","연속"]
[68,"경기","군포","산본안양#1 T/L","154kV 안양S/S 철거공사","O. 154kV 산본-안양#1,2T/L 인출 포스트 보강","2018-12-01 09:00","2018-12-02 18:00","2018-12-01 09:00","2018-12-02 18:00","연속"]
[69,"경기","군포","산본안양#2 T/L","154kV 안양S/S 철거공사","O. 154kV 산본-안양#1,2T/L 인출 포스트 보강","2018-12-03 08:00","2018-12-03 20:00","2018-12-03 08:00","2018-12-03 20:00","당일"]
[70,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-이천 등 4개 T/L 송전선로용 피뢰기 설치공사","곤지암-이천 #2 T/L 1~5호 송전선로용 피뢰기 설치 곤지암-율현 #2 T/L 1~5호 송전선로용 피뢰기 설치","2018-12-02 08:00","2018-12-02 18:00","취소","취소","당일"]
[71,"경기","동부","곤지암초월#1 T/L","154kV 곤지암-초월 등 2개 T/L 상간스페이서 점검","12년 이상 장기사용 상간 스페이서 내부 전선 정밀점검 -곤지암-초월T/L 16~17호, 55~56호 -초월-성현T/L 8~9호, 19~20호, 55~56호","2018-12-01 08:00","2018-12-01 18:00","2018-12-01 08:00","2018-12-01 18:00","당일"]
[72,"경기","동부","분당S/S #3 G/T GIS","18년 동부변전협력회사 총액공사","분당: #3 G/T GIS (개폐타임)","2018-12-10 09:00","2018-12-10 18:00","2018-12-10 09:00","2018-12-10 18:00","당일"]
[73,"경기","동부","분당오포#2 T/L","154kV 모현-용인 등6개 T/L 송전선로용 피뢰기 설치공사","154kV 모현-용인 등6개 T/L 송전선로용 피뢰기 설치공사(122기)","2018-12-09 08:00","2018-12-10 18:00","2018-12-09 08:00","2018-12-10 18:00","연속"]
[74,"경기","동부","분당오포#1 T/L","154kV 모현-용인 등6개 T/L 송전선로용 피뢰기 설치공사","154kV 모현-용인 등6개 T/L 송전선로용 피뢰기 설치공사(안전이격확보 포함)","2018-12-11 08:00","2018-12-13 18:00","2018-12-11 08:00","2018-12-13 18:00","연속"]
[75,"경기","동부","분당S/S #6 G/T GIS","18년 동부변전협력회사 총액공사","분당: #6,7 G/T GIS (개폐타임)","2018-12-11 09:00","2018-12-11 14:00","2018-12-11 09:00","2018-12-11 14:00","당일"]
[76,"경기","동부","분당S/S #7 G/T GIS","18년 동부변전협력회사 총액공사","분당: #6,7 G/T GIS (개폐타임)","2018-12-11 14:00","2018-12-11 18:00","2018-12-11 14:00","2018-12-11 18:00","당일"]
[77,"경기","동부","성현S/S 성현-분당#1T/L GIS","18년 동부변전협력회사 총액공사","성현,분당:성현-분당 #1T/L보호반대체(~5)","2018-12-03 09:00","2018-12-05 18:00","2018-12-03 09:00","2018-12-05 18:00","연속"]
[78,"경기","동부","성현S/S 성현-분당#2T/L GIS","18년 동부변전협력회사 총액공사","성현,분당:성현-분당 #2T/L보호반대체(~12)","2018-12-06 09:00","2018-12-08 18:00","2018-12-06 09:00","2018-12-08 18:00","연속"]
[79,"경기","성남","남사진위#1 T/L","남사S/S 남사-진위#1T/L 하자점검","남사S/S 남사-진위#1T/L 하자점검","2018-12-14 09:00","2018-12-14 18:00","2018-12-13 09:00","2018-12-13 18:00","당일"]
[80,"경기","성남","오포모현#2 T/L","154kV 모현-용인 등6개 T/L 송전선로용 피뢰기 설치공사","154kV 모현-용인 등6개 T/L 송전선로용 피뢰기 설치공사","2018-12-12 08:00","2018-12-13 18:00","2018-12-12 08:00","2018-12-13 18:00","연속"]
[81,"경기","성남","모현용인#2 T/L","154kV 모현-용인 등6개 T/L 송전선로용 피뢰기 설치공사","154kV 모현-용인 등6개 T/L 송전선로용 피뢰기 설치공사","2018-12-14 08:00","2018-12-15 18:00","2018-12-14 08:00","2018-12-15 18:00","연속"]
[82,"경기","직할","남수원S/S 154kV #1 BUS","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(서서울2-남수원#2T/L,#1M.Tr)","2018-12-02 09:00","2018-12-12 18:00","취소","취소","연속"]
[83,"경기","직할","서서울#2남수원 #2T/L","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(서서울2-남수원#2T/L,#1M.Tr)","2018-12-01 09:00","2018-12-22 18:00","취소","취소","연속"]
[84,"경기","직할","남수원S/S 154kV #2 BUS","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(서서울2-남수원#2T/L,#1M.Tr)","2018-12-03 09:00","2018-12-13 09:00","취소","취소","연속"]
[85,"경기","직할","발안향남#1 T/L","경기직할 OPGW 항공장애표시구 보강공사(신항공법)","No.10-11-12간 백색 10개 취부","2018-12-04 08:00","2018-12-04 18:00","2018-12-04 08:00","2018-12-04 18:00","당일"]
[86,"경기","직할","의왕동안양#2 T/L","의왕S/S 170kV GIS 대체공사","의왕S/S 율전의왕#2T/L, #1M.Tr 1차 GIS 대체(#1BUS 무부하가압용)","2018-12-16 18:00","2018-12-17 18:00","2018-12-16 18:00","2018-12-17 18:00","연속"]
[87,"경기","직할","의왕동안양#1 T/L","154kV 의왕-동안양T/L 지중화공사","본선로 구성 : C/H 2기, 교체 1기","2018-12-14 07:00","2018-12-15 18:00","2018-12-14 07:00","2018-12-15 18:00","연속"]
[88,"경기","직할","의왕동안양#2 T/L","154kV 의왕-동안양T/L 지중화공사","본선로 구성 : C/H 2기, 교체 1기","2018-12-12 07:00","2018-12-13 18:00","2018-12-12 07:00","2018-12-13 18:00","연속"]
[89,"경기","직할","율전의왕#2 T/L","의왕S/S 170kV GIS 대체공사","의왕S/S 율전의왕#2T/L, #1M.Tr 1차 GIS 대체","2018-12-04 09:00","2018-12-26 18:00","2018-12-04 09:00","2018-12-26 18:00","연속"]
[90,"경기","직할","의왕S/S 154kV #1 BUS","의왕S/S 170kV GIS 대체공사","의왕S/S 율전의왕#2T/L, #1M.Tr 1차 GIS 대체(#1DS 철거 및 설치)","2018-12-07 09:00","2018-12-17 18:00","2018-12-07 09:00","2018-12-17 18:00","연속"]
[91,"경기","평택","고덕S/S 고덕-평택#1T/L GIS","345kV 고덕S/S 건설공사","154kV 고덕-삼성전자 #3T/L 무부하 가압","2018-12-26 10:00","2018-12-27 10:00","취소","취소","연속"]
[92,"경기","평택","고덕S/S 고덕-평택#1T/L GIS","345kV 고덕S/S 건설공사","154kV 고덕-삼성전자 #3T/L용 GIS 1CCT 증설 #60 BUS 무부하 가압","2018-12-13 15:00","2018-12-14 15:00","취소","취소","연속"]
[93,"경기","평택","고덕S/S 고덕-평택#1T/L GIS","345kV 고덕S/S 건설공사","154kV 고덕-삼성전자 #3T/L용 GIS 1CCT 증설 #65 BUS 무부하 가압","2018-12-20 15:00","2018-12-21 15:00","취소","취소","연속"]
[94,"경기","평택","소사벌안성 T/L","안성S/S 154kV 소사벌-안성T/L GIS 조작시험","안성S/S 154kV 소사벌-안성T/L GIS 조작시험 / 소사벌S/S 154kV 소사벌-안성T/L GIS 보통점검","2018-12-11 10:00","2018-12-11 18:00","취소","취소","당일"]
[95,"경기","평택","서안성안성#2 T/L","안성S/S 154kV 서안성-안성#2T/L GIS 조작시험","안성S/S 154kV 서안성-안성#2T/L GIS 조작시험","2018-12-10 14:00","2018-12-10 18:00","취소","취소","당일"]
[96,"경기","평택","서안성안성#1 T/L","안성S/S 154kV 서안성-안성#1T/L GIS 조작시험","안성S/S 154kV 서안성-안성#1T/L GIS 조작시험","2018-12-10 10:00","2018-12-10 14:00","취소","취소","당일"]
[97,"경기","평택","송탄안성 T/L","안성S/S 154kV 송탄-안성T/L GIS 조작시험","안성S/S 154kV 송탄-안성T/L GIS 조작시험","2018-12-12 10:00","2018-12-12 18:00","취소","취소","당일"]
[98,"경기","평택","진위동탄#1 T/L","진위S/S 동탄-진위#1T/L GIS 하자점검","진위S/S 동탄-진위#1T/L GIS 하자점검","2018-12-14 10:00","2018-12-14 18:00","2018-12-14 10:00","2018-12-14 18:00","당일"]
[99,"경기","평택","청북평택#2 T/L","평택S/S 154kV 청북-평택#2T/L GCB 보통점검","평택S/S 154kV 청북-평택#2T/L GCB 보통점검","2018-12-10 10:00","2018-12-10 18:00","취소","취소","당일"]
[100,"경기","평택","청북평택#2 T/L","154kV 청북S/S #5M.Tr 증설용 GIS 설치공사","ㅇ 증설설비 무부하 가압","2018-12-29 09:00","2018-12-31 09:00","취소","취소","연속"]
[101,"경기","평택","청북평택#2 T/L","154kV 청북S/S #5M.Tr 증설용 GIS 설치공사","ㅇ 154kV #2BUS 무부하 가압","2018-12-14 18:00","2018-12-15 18:00","취소","취소","연속"]
[102,"경기","평택","청북평택#2 T/L","154kV 청북S/S #5M.Tr 증설용 GIS 설치공사","ㅇ 154kV #1BUS 무부하 가압","2018-12-07 18:00","2018-12-08 18:00","취소","취소","연속"]
[103,"경기","평택","평택추팔#2 T/L","추팔S/S 노후 축소형 모자익 대체공사","추팔S/S 노후 축소형 모자익 대체공사 / 154kV 평택-추팔#2T/L 경보시험","2018-12-13 09:00","2018-12-14 18:00","취소","취소","연속"]
[104,"경기","평택","평택추팔#1 T/L","추팔S/S 노후 축소형 모자익 대체공사","추팔S/S 노후 축소형 모자익 대체공사 / 154kV 평택-추팔#1T/L 경보시험","2018-12-06 09:00","2018-12-07 18:00","취소","취소","연속"]
[105,"경기","평택","평택추팔#1 T/L","154kV 평택-추팔T/L 안전이격확보공사","철탑교체 3기(No.34, 35, 38), 임시선로 2기(No.34, 38)","2018-12-04 08:00","2018-12-07 18:00","취소","취소","연속"]
[106,"강원","강릉","강릉횡계#2 T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","No.35, 36[CH철탑] 항공장애등 설치","2018-12-05 09:00","2018-12-06 18:00","2018-12-05 09:00","2018-12-06 18:00","매일"]
[107,"강원","강릉","강릉영동TP T/L","154kV 강릉 등 3개T.L CH철탑 설치공사","No.35, 36[CH철탑] 항공장애등 설치","2018-12-05 09:00","2018-12-06 18:00","2018-12-05 09:00","2018-12-06 18:00","매일"]
[108,"강원","강릉","북평영동TP#2 T/L","154kV 횡계평창 등 5개 T/L 피뢰기 설치공사","○피뢰기 설치공사 154kV 영동화력T/L No. 47~92","2018-12-03 07:00","2018-12-07 18:00","취소","취소","매일"]
[109,"강원","강릉","주진평창#1T/L","  2018년 강릉전력지사 170kV GIS 정밀점검 ","주진평창#1T/L 정밀점검","2018-12-13 10:00","2018-12-13 18:00","취소","취소","당일"]
[110,"강원","강릉","주진평창#2T/L","  2018년 강릉전력지사 170kV GIS 정밀점검 ","주진평창#2T/L 정밀점검","2018-12-14 10:00","2018-12-14 18:00","취소","취소","당일"]
[111,"강원","직할","양구화천HP#1T/L","'18~19년 강원직할 송전정비회사 총액공사","상간스페이서 설치공사(10경간)","2018-12-04 09:00","2018-12-05 18:00","2018-12-04 09:00","2018-12-05 18:00","연속"]
[112,"강원","직할","양구화천HP#2T/L","'18~19년 강원직할 송전정비회사 총액공사","상간스페이서 설치공사(10경간)","2018-12-06 09:00","2018-12-07 18:00","2018-12-06 09:00","2018-12-07 18:00","연속"]
[113,"강원","강릉","속초S/S #EM.Tr CB","보호계전기 점검","보호계전기 점검(#1EM.Tr)","2018-12-05 10:00","2018-12-05 18:00","2018-12-05 10:00","2018-12-05 18:00","당일"]
[114,"충북","직할","단양영월CC#1 T/L","2018~2019년 직할 송전정비회사 총액공사","불량애자 교체 (#1T/L 1호)","2018-12-04 14:30","2018-12-04 18:00","취소","취소","당일"]
[115,"충북","직할","단양영월CC#2 T/L","2018~2019년 직할 송전정비회사 총액공사","불량애자 교체 (#2T/L 1호)","2018-12-04 08:00","2018-12-04 14:00","취소","취소","당일"]
[116,"충북","직할","제천영월#1 T/L","2018~2019년 직할 송전정비회사 총액공사","154kV 단양-영월CCT/L No.1 불량애자 교체 안전조치","2018-12-04 14:30","2018-12-04 18:00","취소","취소","당일"]
[117,"충북","직할","제천영월#2 T/L","2018~2019년 직할 송전정비회사 총액공사","154kV 단양-영월CCT/L No.1 불량애자 교체 안전조치","2018-12-04 08:00","2018-12-04 14:00","취소","취소","당일"]
[118,"충북","청주","오송북청주#2 T/L","2018년 하반기 청주전력지사 170kV GIS 정밀점검공사","북청주S/S 170kV 오송북청주#2T/L GIS 정밀점검","2018-12-15 09:00","2018-12-16 18:00","취소","취소","연속"]
[119,"충북","청주","사직북청주#2 T/L","2018년 하반기 청주전력지사 170kV GIS 정밀점검공사","북청주S/S 170kV 사직북청주#2T/L GIS 정밀점검","2018-12-01 09:00","2018-12-02 18:00","2018-12-01 09:00","2018-12-02 18:00","연속"]
[120,"충북","청주","청원오송#2 T/L","2018년 하반기 청주전력지사 170kV GIS 정밀점검공사","오송S/S 170kV 청원오송#2T/L GIS 정밀점검","2018-12-08 09:00","2018-12-09 18:00","취소","취소","연속"]
[121,"충북","충주","진천만승#1 T/L","18-19년 충주전력지사 변전 정비회사 총액공사","LA 초기점검 등","2018-12-07 09:00","2018-12-07 18:00","2018-12-08 09:00","2018-12-08 18:00","당일"]
[122,"충북","충주","서운만승 T/L","18-19년 충주전력 변전 정비회사 총액공사","CVT, LA 교체 등","2018-12-02 09:00","2018-12-02 18:00","2018-12-02 09:00","2018-12-02 18:00","당일"]
[123,"충북","충주","진천만승#2 T/L","18-19년 충주전력지사 변전 정비회사 총액공사","LA 초기점검 등","2018-12-08 09:00","2018-12-08 18:00","취소","취소","당일"]
[124,"충북","충주","충주충주HP#1 T/L","2018-2019년 송전정비회사 총액공사","가공지선 교체 (No.39-44)","2018-12-03 09:00","2018-12-05 14:00","2018-12-03 09:00","2018-12-05 14:00","연속"]
[125,"충북","충주","충주충주HP#2 T/L","2018-2019년 송전정비회사 총액공사","송전선 보호계전기 정정 및 시험","2018-12-05 14:00","2018-12-05 18:00","2018-12-05 14:00","2018-12-05 18:00","당일"]
[126,"충북","충주","남음성덕산#2 T/L","154kV 남음성S/S #2M.Tr 증설공사","○ M.Tr 1Bank 설치 ○ 170kV GIS 1CCT 설치 ○ 25.8kV SIS 4CCT 설치 ○ 기타 부속기기(NGR, 변압기 보호 IED반 등) 설치","2018-12-03 10:00","2018-12-04 10:00","2018-12-03 10:00","2018-12-04 10:00","연속"]
[127,"대전충남","서산","합덕송악#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","154kV 합덕-송악#2T/L 피뢰기설치공사 - 27기분, 841set","2018-12-03 09:00","2018-12-07 18:00","2018-12-03 09:00","2018-12-07 18:00","매일"]
[128,"대전충남","세종","전의동천안#2 T/L","[송전]154kV 전의-동천안 #2T/L 피뢰기 설치공사","60기 피뢰기 설치","2018-12-03 07:00","2018-12-11 18:00","2018-12-03 07:00","2018-12-11 18:00","연속"]
[129,"대전충남","청양","신풍공주#2 T/L","(주)와이피피제 보호계전기 성능개선","○154kV신풍-공주#2T/L 송전선로 보호반 성능개선","2018-12-03 09:00","2018-12-03 18:00","2018-12-02 09:00","2018-12-02 18:00","당일"]
[130,"전북","군산","군공군산CC#1 T/L","군공S/S 154kV 군공-군산복합#1T/L 접지불량 해소공사","군공S/S 154kV 군공-군산복합#1T/L 선로접지 고정 접촉자 교체","2018-12-10 09:00","2018-12-11 18:00","2018-12-10 09:00","2018-12-11 18:00","연속"]
[131,"전북","군산","군산영등#2 T/L","군산P/O 154kV이상 차단기 조작시험","차단기 조작시험","2018-12-01 09:00","2018-12-01 12:00","2018-12-01 09:00","2018-12-01 12:00","당일"]
[132,"전북","군산","군산S/S 154kV #1 BUS TIE CB","군산P/O 154kV이상 차단기 조작시험","차단기 조작시험","2018-12-05 09:00","2018-12-05 12:00","2018-12-05 09:00","2018-12-05 12:00","당일"]
[133,"전북","군산","군산S/S 154kV #3 BUS TIE CB","군산P/O 154kV이상 차단기 조작시험","차단기 조작시험","2018-12-05 09:00","2018-12-05 12:00","2018-12-05 09:00","2018-12-05 12:00","당일"]
[134,"전북","김제","고창홍농 T/L","154kV 고창-홍농 등 7개T/L 피뢰기설치공사","154kV 고창-홍농T/L 110기, 피뢰기 330Set 설치","2018-12-01 08:00","2018-12-01 18:00","2018-12-02 08:00","2018-12-02 18:00","당일"]
[135,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격확보공사","정주-고창#1T/L 철탑 이설 및 전력선 교체 철탑교체 : No.66,69,70,72호 전력선 교체 : No.65~74호","2018-12-04 09:00","2018-12-06 18:00","츼소","취소","연속"]
[136,"전북","김제","백산김제#1 T/L","154kV 고창-홍능 등 7개T/L 피뢰기설치공사","154kV 김제-섬진강T/L 병가구간 설치 공사 김제-섬진강 No.2~12 구간","2018-12-08 08:00","2018-12-09 18:00","2018-12-08 08:00","2018-12-09 18:00","매일"]
[137,"전북","김제","김제섬진강HP T/L","154kV 고창-홍농 등 7개T/L 피뢰기 설치공사","154kV 김제-섬진강T/L 82기, 피뢰기 246Set 설치","2018-12-08 08:00","2018-12-15 18:00","츼소","취소","매일"]
[138,"전북","김제","백산김제#2 T/L","154kV 김제-부안T/L 최초가압 관련","154kV 김제-부안T/L 최초가압 관련 무부하 회선 신청","2018-12-17 09:00","2018-12-21 18:00","2018-12-17 09:00","2018-12-21 18:00","연속"]
[139,"전북","김제","신김제남전주#2 T/L","남전주S/S 장기사용 GIS 교체공사(#4M.Tr 1차)","남전주S/S 장기사용 GIS 교체공사(#4M.Tr 1차) -안전이격","2018-12-01 09:00","2018-12-07 18:00","츼소","취소","매일"]
[140,"전북","김제","섬진강H/P #1 M.Tr 1차 GIS","차단기 조작시험","차단기 조작시험","2018-12-10 10:00","2018-12-10 14:00","2018-12-10 10:00","2018-12-10 14:00","당일"]
[141,"전북","김제","섬진강H/P #2 M.Tr 1차 GIS","GIS 보통점검","GIS 보통점검","2018-12-11 10:00","2018-12-11 18:00","2018-12-11 10:00","2018-12-11 18:00","당일"]
[142,"전북","김제","신김제S/S #61EM.Tr CB","신김제ESS 정밀점검","#EM.Tr 초기점검, EGIS 초기점검, ESS정밀점검","2018-12-03 09:00","2018-12-14 18:00","2018-12-03 09:00","2018-12-14 18:00","연속"]
[143,"전북","직할","무주용담수력 T/L","154kV 무주-용담수력T/L 송전선로 정밀점검","○ 송전선로 정밀점검 No.51~103 (53기)","2018-12-03 08:00","2018-12-07 18:00","츼소","취소","매일"]
[144,"전북","직할","무주진안 T/L","154kV 무주-진안T/L 송전선로 정밀점검","○ 송전선로 정밀점검 No.104~175 (72기)","2018-12-10 08:00","2018-12-19 18:00","츼소","취소","매일"]
[145,"전북","직할","북전주진안 T/L","154kV 동전주-북전주#1T/L 피뢰기 설치공사","○ 병가구간 작업 無","2018-12-01 07:00","2018-12-02 18:00","2018-12-01 07:00","2018-12-02 18:00","매일"]
[146,"광주전남","강진","진도S/S 154kV #2 BUS","#1M.Tr 1차 GIS 정밀점검공사","CB부,상부,모선부 정밀점검","2018-12-06 09:00","2018-12-07 18:00","취소","취소","연속"]
[147,"광주전남","강진","진도S/S 154kV #1 BUS","#1BUSTIE GIS 정밀저검공사","모선부,CB부 정밀점검","2018-12-03 09:00","2018-12-04 18:00","취소","취소","연속"]
[148,"광주전남","강진","진도S/S 154kV #2 BUS","#1BUSTIE GIS 정밀점검공사","모선부,CB부 정밀점검","2018-12-04 09:00","2018-12-05 18:00","취소","취소","연속"]
[149,"광주전남","강진","진도S/S 154kV #1 BUS","#1M.Tr 1차 GIS 정밀점검공사","CB부,모선부,상부 정밀점검","2018-12-05 09:00","2018-12-06 18:00","취소","취소","연속"]
[150,"광주전남","강진","진도S/S 154kV #2 BUS","#2M.Tr 1차 GIS 정밀점검공사","CB부,모선부,상부 정밀점검","2018-12-11 09:00","2018-12-12 18:00","취소","취소","연속"]
[151,"광주전남","강진","진도S/S 154kV #1 BUS","#2M.Tr 1차 GIS 정밀점검공사","CB부,모선부,상부 정밀점검","2018-12-10 09:00","2018-12-11 18:00","취소","취소","연속"]
[152,"광주전남","강진","진도진도CS#2 T/L","진도C/S 154kV 진도-진도C/S #2T/L (87Ry 교체)","87Ry 오동작에 따른 교체 및 시험 (계통운영부 입회)","2018-12-04 09:00","2018-12-04 18:00","2018-12-07 09:00","2018-12-07 18:00","당일"]
[153,"광주전남","강진","진도진도CS#1 T/L","진도C/S 154kV 진도-진도C/S #1T/L (87Ry 교체)","87Ry 오동작에 따른 교체 및 시험 (계통운영부 입회)","2018-12-03 09:00","2018-12-03 18:00","2018-12-06 09:00","2018-12-06 18:00","당일"]
[154,"광주전남","강진","해남C/S 해남-해남CS#1T/L GIS(신규)","#1HVDC 노후 변환설비 정비공사","T/L PNL 대체 및 RTU 수용","2018-12-03 09:00","2018-12-05 18:00","2018-12-03 09:00","2018-12-05 18:00","연속"]
[155,"광주전남","강진","해남C/S 해남-해남CS#2T/L GIS(신규)","#1HVDC 노후 변환설비 정비공사","T/L PNL 대체 및 RTU 수용","2018-12-06 09:00","2018-12-08 18:00","2018-12-06 09:00","2018-12-08 18:00","연속"]
[156,"광주전남","광주","북광주계림#2 T/L","18년 광주 변전총액공사 (북광주-계림2T/L)","북광주-계림#2T/L 양단 보호반 교체, 계림S/S 장기미동작 CB점검","2018-12-26 09:00","2018-12-28 18:00","2018-12-26 09:00","2018-12-28 18:00","연속"]
[157,"광주전남","광주","계림충장#2 T/L","18년 광주 변전정비회사 총액공사 (계림-충장2T/L)","계림-충장#2T/L 양단 보호반 교체, 장기미동작 CB점검","2018-12-17 09:00","2018-12-19 18:00","취소","취소","연속"]
[158,"광주전남","광주","북광주계림#1 T/L","18년 광주 변전총액공사 (북광주-계림#1T/L)","북광주-계림#1T/L 양단 보호반 교체, 계림S/S 장기미동작 CB점검","2018-12-17 09:00","2018-12-19 18:00","2018-12-17 09:00","2018-12-19 18:00","연속"]
[159,"광주전남","광주","계림충장#3 T/L","18년 광주 변전총액공사(계림충장#3T/L)","[계림,충장S/S]계림충장#3T/L 양단 보호배전반 교체 [계림S/S]계림충장#3T/L GIS 보통점검 [충장S/S]계림충장#3T/L 장기미동작 CB 점검","2018-12-10 09:00","2018-12-12 18:00","취소","취소","연속"]
[160,"광주전남","광주","담양일곡#1 T/L","18년 광주변전총액공사(담양S/S 담양-일곡#1T/L GIS 보통점검)","담양S/S 담양-일곡#1T/L GIS 보통점검","2018-12-07 09:00","2018-12-07 18:00","2018-12-07 09:00","2018-12-07 18:00","당일"]
[161,"광주전남","광주","신광주장성#2 T/L","154kV 담양-일곡 등6개T/L 피뢰기설치공사","신광주일곡#2 T/L No.1~21호간 피뢰기 설치(4회선 병가구간)","2018-12-01 08:00","2018-12-01 18:00","2018-12-01 08:00","2018-12-01 18:00","당일"]
[162,"광주전남","광주","장성영광#2 T/L","154kV 장성-영광#1T/L 비표준 EB-A 자기애관 교체공사","154kV 장성-영광#1T/L 비표준 EB-A 자기애관 교체공사 ○ EB-A 부분방전 진단 UWB센서 설치(#2T/L)","2018-12-26 09:00","2018-12-26 15:00","2018-12-26 09:00","2018-12-26 15:00","당일"]
[163,"광주전남","광주","장성영광#1 T/L","154kV 장성-영광#1T/L 비표준 EB-A 자기애관 교체공사","154kV 장성-영광#1T/L 비표준 EB-A 자기애관 교체공사 ○ EB-A 교체 #1T/L A,B상 ○ 케이블 포설 #1T/L A,B상 114m ○ 무접지 PMNJ #1T/L A,B상 ○ 기타 부대공사 2식","2018-12-17 09:00","2018-12-24 18:00","2018-12-17 09:00","2018-12-24 18:00","연속"]
[164,"광주전남","광주","장성영광#2 T/L","18년 광주변전총액공사(장성-영광#2T/L)","장성S/S 장성-영광#2T/L GIS 장기미동작 차단기 점검","2018-12-17 09:00","2018-12-17 18:00","2018-12-27 09:00","2018-12-27 18:00","당일"]
[165,"광주전남","목포","고창홍농 T/L","154kV 홍농분기T/L 안전이격확보공사","154kV 홍농분기T/L 안전이격확보공사 ○ 54,56호 보조암 설치","2018-12-26 08:00","2018-12-26 18:00","2018-12-26 08:00","2018-12-26 18:00","당일"]
[166,"광주전남","목포","영광홍농 T/L","154kV 홍농분기T/L 안전이격확보공사","154kV 홍농분기T/L 안전이격확보공사 ○ 54,56호 보조암 설치","2018-12-27 08:00","2018-12-27 18:00","2018-12-27 08:00","2018-12-27 18:00","당일"]
[167,"광주전남","순천","광양순천#2 T/L","345kV 광양-율촌CC등 12개T/L 피뢰기 설치공사","154kV 광양-순천T/L 피뢰기 설치 - 피뢰기 설치 (1~177호, 34기)","2018-12-18 07:00","2018-12-19 18:00","2018-12-06 07:00","2018-12-07 18:00","매일"]
[168,"광주전남","순천","광양하동#1 T/L","345kV 광양-율촌CC등 12개T/L 피뢰기 설치공사","154kV 광양-하동T/L 피뢰기 설치 - 피뢰기 설치 (38~91호, 53기)","2018-12-12 07:00","2018-12-14 18:00","2018-12-03 07:00","2018-12-05 18:00","매일"]
[169,"광주전남","순천","승주서순천 T/L","345kV 광양-율촌CC등 12개T/L 피뢰기 설치공사","154kV 승주-서순천T/L 피뢰기 설치 - 피뢰기 설치 (1~96호, 96기)","2018-12-01 07:00","2018-12-05 18:00","취소","취소","매일"]
[170,"광주전남","순천","여천여수#1 T/L","여천,여수S/S 차단기 전자변 교체","여천,여수S/S 여천-여수#1T/L 차단기 전자변 교체","2018-12-05 10:00","2018-12-05 18:00","2018-12-01 10:00","2018-12-01 18:00","당일"]
[171,"광주전남","순천","여천여수#2 T/L","345kV 광양-율촌CC등 12개T/L 피뢰기 설치공사","154kV 여천-여수T/L 피뢰기 설치 - 피뢰기 설치 (1~22호, 22기)","2018-12-15 07:00","2018-12-16 18:00","2018-12-08 07:00","2018-12-09 18:00","매일"]
[172,"광주전남","순천","여천호남TP#1 T/L","345kV 광양-율촌CC등 12개T/L 피뢰기 설치공사","154kV 여천-여수T/L 피뢰기 설치관련 병가선로 휴전","2018-12-16 07:00","2018-12-16 18:00","2018-12-09 07:00","2018-12-09 18:00","당일"]
[173,"광주전남","순천","율촌여수산단#1 T/L","345kV 광양-율촌CC등 12개T/L 피뢰기 설치공사","154kV 율촌-여수산단T/L 피뢰기 설치 - 피뢰기 설치 (1~51호, 51기)","2018-12-09 07:00","2018-12-11 18:00","취소","취소","매일"]
[174,"광주전남","순천","율촌화치#2 T/L","345kV 광양-율촌CC등 12개T/L 피뢰기 설치공사","154kV 율촌-화치T/L 피뢰기 설치 - 피뢰기 설치 (1~68호, 64기)","2018-12-06 07:00","2018-12-09 18:00","취소","취소","매일"]
[175,"광주전남","순천","율촌화치#1 T/L","345kV 광양-율촌CC등 12개T/L 피뢰기 설치공사","154kV 율촌-화치T/L 피뢰기 설치 - 피뢰기 설치 (31호, 1기)","2018-12-05 07:00","2018-12-05 18:00","2018-12-05 07:00","2018-12-05 18:00","당일"]
[176,"광주전남","순천","여수TP화치#1 T/L","화치S/S 장기미동작 차단기 타임 측정","화치 여수TP-화치#1T/L #1,2DS 댐퍼교체,장기미동작 차단기 타임 측정","2018-12-04 10:00","2018-12-04 16:00","2018-12-04 10:00","2018-12-04 16:00","당일"]
[177,"광주전남","순천","여수TP화치#2 T/L","화치S/S 장기미동작 차단기 타임 측정","화치 여수TP-화치#2T/L #1,2DS 댐퍼교체,장기미동작 차단기 타임 측정","2018-12-04 16:00","2018-12-04 18:00","2018-12-04 16:00","2018-12-04 18:00","당일"]
[178,"광주전남","직할","신화순나주#2 T/L","나주S/S 옥내화 관련 인출정비 C/H 설치공사","C/H 6기, LA/LP 11기 설치","2018-12-03 08:00","2018-12-04 18:00","2018-12-08 08:00","2018-12-09 18:00","당일"]
[179,"광주전남","직할","나주엄다#1 T/L","나주S/S 옥내화 관련 인출정비 C/H 설치공사","C/H 6기, LA/LP 11기 설치","2018-12-11 08:00","2018-12-11 18:00","2018-12-11 08:00","2018-12-11 18:00","당일"]
[180,"광주전남","직할","나주엄다#2 T/L","나주S/S 옥내화 관련 인출정비 C/H 설치공사","암부착, 가선, 가압","2018-12-30 08:00","2018-12-30 18:00","2018-12-30 08:00","2018-12-30 18:00","당일"]
[181,"광주전남","직할","나주엄다#1 T/L","나주S/S 옥내화 관련 인출정비 C/H 설치공사","C/H 조립, 가선, 가압","2018-12-29 08:00","2018-12-31 18:00","2018-12-29 08:00","2018-12-31 18:00","연속"]
[182,"광주전남","직할","농성S/S 충장-농성#1T/L GIS","18-19년 직할 변전정비회사 총액공사","170kV GIS(공기압방식) 장기미동작 점검","2018-12-07 09:00","2018-12-07 18:00","취소","취소","당일"]
[183,"광주전남","직할","농성S/S 충장-농성#2T/L GIS","18-19년 직할 변전정비회사 총액공사","170kV GIS(공기압방식) 장기미동작 점검","2018-12-06 09:00","2018-12-06 18:00","취소","취소","당일"]
[184,"광주전남","직할","하남S/S 하남-장성#2T/L GIS","18-19년 직할 변전정비회사 총액공사","170kV GIS(공기압방식) 장기미동작 점검","2018-12-04 09:00","2018-12-04 18:00","취소","취소","당일"]
[185,"광주전남","직할","하남S/S 하남-장성#1T/L GIS","18-19년 직할 변전정비회사 총액공사","170kV GIS(공기압방식) 장기미동작 점검","2018-12-03 09:00","2018-12-03 18:00","취소","취소","당일"]
[186,"광주전남","직할","수완흑석#2 T/L","18년 직할 170kV GIS 정밀점검공사","흑석S/S 수완-흑석#2T/L GIS 정밀점검","2018-12-05 09:00","2018-12-06 18:00","2018-12-05 09:00","2018-12-06 18:00","연속"]
[187,"광주전남","직할","수완흑석#1 T/L","18년 직할 170kV GIS 정밀점검공사","흑석S/S 수완-흑석#1T/L GIS 정밀점검","2018-12-03 09:00","2018-12-04 18:00","2018-12-03 09:00","2018-12-04 18:00","연속"]
[188,"광주전남","직할","신광주일곡 #2T/L","154kV 담양-일곡 등6개T/L 피뢰기설치공사","피뢰기 설치","2018-12-01 08:00","2018-12-02 18:00","2018-12-01 08:00","2018-12-02 18:00","매일"]
[189,"대구","달성","다산강창#2 T/L","달성전력지사 변전총액공사(모선보호반 대체)","달성전력지사 변전총액공사(모선보호반 대체 TEST)","2018-12-16 16:00","2018-12-16 16:30","2018-12-16 16:00","2018-12-16 16:30","당일"]
[190,"대구","달성","강창성서#2 T/L","달성전력지사 변전총액공사(모선보호반 대체)","달성전력지사 변전총액공사(모선보호반 대체 TEST)","2018-12-16 15:30","2018-12-16 16:00","2018-12-16 15:30","2018-12-16 16:00","당일"]
[191,"대구","달성","강창성서#1 T/L","달성전력지사 변전총액공사(모선보호반 대체)","달성전력지사 변전총액공사(모선보호반 대체 TEST)","2018-12-16 15:00","2018-12-16 15:30","2018-12-16 15:00","2018-12-16 15:30","당일"]
[192,"대구","달성","다산강창#1 T/L","달성전력지사 변전총액공사(모선보호반 대체)","달성전력지사 변전총액공사(모선보호반 대체 TEST)","2018-12-16 17:00","2018-12-16 17:30","2018-12-16 17:00","2018-12-16 17:30","당일"]
[193,"대구","달성","고령S/S 154kV #2 BUS TIE CB","달성전력지사 고령S/S 차단기동작특성시험","달성전력지사 고령S/S 차단기동작특성시험","2018-12-05 14:00","2018-12-05 16:00","2018-12-05 14:00","2018-12-05 16:00","당일"]
[194,"대구","달성","고령다산#2 T/L","'18~'19년 달성 송전정비 협력회사 총액공사","항공장애구 설치공사","2018-12-09 07:00","2018-12-09 18:00","2018-12-09 07:00","2018-12-09 18:00","당일"]
[195,"대구","달성","고령다산#1 T/L","'18~'19년 달성 송전정비 협력회사 총액공사","항공장애구 설치공사","2018-12-08 07:00","2018-12-08 18:00","2018-12-08 07:00","2018-12-08 18:00","당일"]
[196,"대구","달성","창녕구지#1 T/L","154kV 서구지-구지T/L SW증설공사","154kV 서구지-구지T/L SW증설공사","2018-12-10 09:00","2018-12-22 18:00","취소","취소","연속"]
[197,"대구","달성","유가구지#1 T/L","154kV 서구지-구지T/L SW증설공사","154kV 서구지-구지T/L SW증설공사","2018-12-10 09:00","2018-12-22 18:00","취소","취소","연속"]
[198,"대구","달성","구지S/S 154kV #2 BUS","154kV 서구지-구지T/L SW증설공사","154kV 서구지-구지T/L SW증설공사","2018-12-10 09:00","2018-12-22 18:00","취소","취소","연속"]
[199,"대구","달성","구지S/S 154kV #1 BUS","154kV 서구지-구지T/L SW증설공사","154kV 서구지-구지T/L SW증설공사","2018-12-23 09:00","2019-01-07 18:00","취소","취소","연속"]
[200,"대구","달성","유가구지#1 T/L","154kV 서구지-구지T/L SW증설공사","154kV 서구지-구지T/L SW증설공사","2018-12-23 09:00","2019-01-07 18:00","취소","취소","연속"]
[201,"대구","달성","창녕구지#1 T/L","154kV 서구지-구지T/L SW증설공사","154kV 서구지-구지T/L SW증설공사","2018-12-23 09:00","2019-01-07 18:00","취소","취소","연속"]
[202,"대구","달성","논공S/S #1 EM.Tr CB","23kV - ESS모선연계","23kV - ESS모선연계","2018-12-17 09:00","2018-12-20 18:00","2018-12-17 09:00","2018-12-20 18:00","연속"]
[203,"대구","달성","다산강창#1 T/L","154kV 다산-강창T/L 지장송전선로 이설공사","월성산단 조성관련 다산-강창T/L 지장송전선로 이설 1기 철거(기설36호), 3기 설치(35-1,35-3,36호)","2018-12-07 08:00","2018-12-09 18:00","2018-12-08 08:00","2018-12-10 18:00","연속"]
[204,"대구","달성","다산강창#2 T/L","154kV 다산-강창T/L 지장송전선로 이설공사","월성산단 조성관련 다산-강창T/L 지장송전선로 이설 1기 철거(기설36호), 3기 설치(35-1,35-3,36호)","2018-12-01 08:00","2018-12-06 18:00","2018-12-01 08:00","2018-12-07 18:00","연속"]
[205,"대구","달성","대구청도#1 T/L","154kV 고령-다산 등 17개T/L 피뢰기 설치공사","피뢰기 설치공사","2018-12-02 07:00","2018-12-02 18:00","2018-12-02 07:00","2018-12-02 18:00","당일"]
[206,"대구","달성","성서달성#2 T/L","2018년 가공송전 순시점검 위탁공사","154kV 성서-팔달T/L 정밀점검","2018-12-08 08:00","2018-12-09 18:00","2018-12-08 08:00","2018-12-09 18:00","연속"]
[207,"대구","달성","강창성서#1 T/L","2018년 가공송전 순시점검 위탁공사","154kV 성서-팔달T/L 정밀점검 안전확보","2018-12-08 08:00","2018-12-08 18:00","2018-12-08 08:00","2018-12-08 18:00","당일"]
[208,"대구","포항","북포항남포항 T/L","154kV 영일-양북 등 19개 T/L 피뢰기 설치공사","154kV 북포항남포항 T/L 6~15호 (10기) 피뢰기 설치","2018-12-09 08:00","2018-12-09 18:00","2018-12-09 08:00","2018-12-09 18:00","당일"]
[209,"대구","포항","신포항S/S 154kV #4 BUS TIE CB","신포항S/S 154kV #4 BUS TIE CB 조작시험","신포항S/S 6000 CB 조작시험","2018-12-05 09:00","2018-12-05 12:00","2018-12-05 09:00","2018-12-05 12:00","당일"]
[210,"대구","포항","신포항S/S 154kV #1 BUS TIE CB","신포항S/S 154kV #1 BUS TIE CB 조작시험","신포항S/S 6100 CB 조작시험","2018-12-05 13:00","2018-12-05 18:00","2018-12-05 13:00","2018-12-05 18:00","당일"]
[211,"대구","포항","신포항S/S 65-66-0 SEC CB","신포항S/S 65-66-0 SEC CB 조작시험","신포항S/S 65-66-0 SEC CB 조작시험","2018-12-04 15:00","2018-12-04 18:00","2018-12-04 15:00","2018-12-04 18:00","당일"]
[212,"대구","포항","신포항S/S 60-61-0 SEC CB","신포항S/S 60-61-0 SEC CB 조작시험","신포항S/S 60-61-0 SEC CB 조작시험","2018-12-04 12:00","2018-12-04 15:00","2018-12-04 12:00","2018-12-04 15:00","당일"]
[213,"경북","구미","남인동인동#1 T/L","2018년도 구미전력지사 변전정비업체 총액공사","- 공기조작부 점검 및 전자변 교체","2018-12-21 09:00","2018-12-21 14:00","2018-12-21 09:00","2018-12-21 14:00","당일"]
[214,"경북","구미","남인동인동#2 T/L","2018년도 구미전력지사 변전정비업체 총액공사","- 공기조작부 점검 및 전자변 교체","2018-12-21 14:00","2018-12-21 18:00","2018-12-21 14:00","2018-12-21 18:00","당일"]
[215,"경북","구미","청리상주#2 T/L","2018년도 구미전력지사 변전정비업체 총액공사","LA대체공사","2018-12-11 14:00","2018-12-11 18:00","취소","취소","당일"]
[216,"경북","구미","청리상주#1 T/L","2018년도 구미전력지사 변전정비업체 총액공사","LA대체공사","2018-12-11 09:00","2018-12-11 14:00","취소","취소","당일"]
[217,"경북","구미","상주S/S 154kV #2 BUS","상주S/S #4M.Tr 증설공사(GIS)","- 170kV 1,250A 50kA 1CCT설치 - 기타부대공사","2018-12-17 09:00","2018-12-18 13:00","취소","취소","연속"]
[218,"경북","구미","상주S/S 154kV #1 BUS","상주S/S #4M.Tr 증설공사","- 154kV 15/20Mvar * 3대 변압기 설치 - 170kV 1,250A 50kA 1CCT설치 - 25.8kV 2,000A 3CCT설치 - 25.8kV 600A 5CCT설치 - 기타부대공사","2018-12-18 13:00","2018-12-19 18:00","취소","취소","연속"]
[219,"경북","구미","선산청리#1 T/L","2018-19년도 구미전력지사 가공송전협력회사 총액공사","ㅇ 항공장애표시구 설치 : 99경간, 350개","2018-12-01 07:00","2018-12-02 13:00","취소","취소","매일"]
[220,"경북","구미","선산청리#2 T/L","2018-19년도 구미전력지사 가공송전협력회사 총액공사","ㅇ 항공장애표시구 설치 : 99경간, 350개","2018-12-02 13:00","2018-12-03 18:00","취소","취소","매일"]
[221,"경북","구미","청리S/S 154kV #1 BUS","154kV 청리S/S #3M.Tr 증설공사","154/23kV M.Tr * 1Bank 170kV GIS *1CCT 25.8kV GIS * 7CCT","2018-12-01 10:00","2018-12-01 16:00","취소","취소","당일"]
[222,"경북","구미","청리S/S 154kV #2 BUS","154kV 청리S/S #3M.Tr 증설공사","154/23kV M.Tr * 1Bank 170kV GIS *1CCT 25.8kV GIS * 7CCT","2018-12-17 10:00","2018-12-17 11:00","취소","취소","당일"]
[223,"경북","구미","청리S/S 154kV #1 BUS","154kV 청리S/S #3M.Tr 증설공사","154/23kV M.Tr * 1Bank 170kV GIS *1CCT 25.8kV GIS * 7CCT","2018-12-17 11:00","2018-12-18 11:00","취소","취소","연속"]
[224,"경북","구미","청리S/S 154kV #2 BUS","154kV 청리S/S #3M.Tr 증설공사","154/23kV M.Tr * 1Bank 170kV GIS *1CCT 25.8kV GIS * 7CCT","2018-12-02 10:00","2018-12-05 16:00","취소","취소","연속"]
[225,"경북","구미","선산청리#1 T/L","154kV 청리S/S #3M.Tr 증설공사","154/23kV M.Tr * 1Bank 170kV GIS *1CCT 25.8kV GIS * 7CCT","2018-12-04 16:00","2018-12-05 16:00","취소","취소","연속"]
[226,"경북","구미","선산청리#1 T/L","154kV 청리S/S #3M.Tr 증설공사","154/23kV M.Tr * 1Bank 170kV GIS *1CCT 25.8kV GIS * 7CCT","2018-12-17 10:00","2018-12-18 12:00","취소","취소","연속"]
[227,"경북","영주","봉화울진 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","봉화S/S 노후 모선보호반 교체공사 후 시험","2018-12-27 13:00","2018-12-27 15:00","2018-12-20 12:00","2018-12-20 12:30","당일"]
[228,"경북","영주","봉화현종산풍력#1 T/L CB","2018-19년도 영주전력지사 변전협력업체 총액공사","봉화S/S 노후 모선보호반 교체공사 후 시험","2018-12-27 11:00","2018-12-27 13:00","2018-12-20 12:30","2018-12-20 13:00","당일"]
[229,"경북","직할","울진삼척GP#2 T/L","18~19년 경북직할 변전정비회사 총액공사","울진S/S 울진-삼척GP#2T/L PT초기점검","2018-12-17 13:00","2018-12-17 18:00","취소","취소","당일"]
[230,"경북","직할","울진삼척GP#1 T/L","18~19년 경북직할 변전정비회사 총액공사","울진S/S 울진-삼척GP#1T/L PT초기점검","2018-12-17 09:00","2018-12-17 13:00","취소","취소","당일"]
[231,"경북","직할","울진평해 T/L","154kV 울진 현종산 풍력발전단지 송전선로 건설공사","No.14 전력선이동, 긴선(하단→상단) 및 평해 변전소 보호계전기 철거,신설,TEST","2018-12-01 07:00","2018-12-07 18:00","취소","취소","연속"]
[232,"경북","구미","남인동인동#1T/L","154kV 칠곡-인동T/L 피뢰기 설치공사","피뢰기 설치공사 병가구간 안전확보 154kV 남인동-인동T/L No.32-33(병가)","2018-12-08 09:00","2018-12-08 18:00","2018-12-08 09:00","2018-12-08 18:00","당일"]
[233,"부산울산","동부산","구서노포#1 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 작업내용 : 154kV 노포-정관#2T/L 피뢰기 설치관련 안전이격확보","2018-12-03 08:00","2018-12-03 18:00","취소","취소","당일"]
[234,"부산울산","동부산","노포정관#2 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 작업내용 : 154kV 노포-정관#2T/L 피뢰기 설치 2. 설치수량 : 31기, 93set","2018-12-02 08:00","2018-12-05 18:00","취소","취소","연속"]
[235,"부산울산","동부산","신울산명례#2 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 대상선로/작업내용 : 154kV 신울산-명례#2T/L/송전선로용 피뢰기 설치(No.1 ~43, 43기)","2018-12-06 08:00","2018-12-10 18:00","취소","취소","연속"]
[236,"부산울산","동부산","신양산S/S 65-66-0 SEC CB","신양산S/S 170kV GCB 조작시험","신양산S/S 170kV GCB 조작시험(65-66-0)","2018-12-03 09:30","2018-12-03 11:00","2018-12-03 09:30","2018-12-03 11:00","당일"]
[237,"부산울산","동부산","신양산S/S 66-67-0 SEC CB","신양산S/S 170kV GCB 조작시험","신양산S/S 170kV GCB 조작시험(66-67-0)","2018-12-03 11:00","2018-12-03 13:00","2018-12-03 11:00","2018-12-03 13:00","당일"]
[238,"부산울산","동부산","신양산S/S 154kV #2 BUS TIE CB","신양산S/S 170kV GCB 조작시험","신양산S/S 170kV GCB 조작시험(6200)","2018-12-04 14:00","2018-12-04 18:00","2018-12-04 14:00","2018-12-04 18:00","당일"]
[239,"부산울산","동부산","신양산S/S 154kV #1 BUS TIE CB","신양산S/S 170kV GCB 조작시험","신양산S/S 170kV GCB 조작시험(6100)","2018-12-04 09:30","2018-12-04 14:00","2018-12-04 09:30","2018-12-04 14:00","당일"]
[240,"부산울산","북부산","매리김해#2 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","피뢰기 설치공사관련 선로 안전이격 - 피뢰기 설치공사 : 호포-매리#2T/L NO.1~25호 15기","2018-12-08 07:00","2018-12-08 18:00","2018-12-08 07:00","2018-12-08 18:00","당일"]
[241,"부산울산","북부산","호포매리#2 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","- 피뢰기 설치공사 : 호포-매리#2T/L NO.1~25호 15기","2018-12-08 07:00","2018-12-09 18:00","2018-12-08 07:00","2018-12-09 18:00","매일"]
[242,"부산울산","북부산","북부산S/S 60-61-0 SEC CB","2018년 북부산 변전협력회사 총액공사","북부산S/S 154kV 60-61 Bus-Section GIS 초기점검","2018-12-03 10:00","2018-12-03 18:00","2018-12-03 10:00","2018-12-03 18:00","당일"]
[243,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막T/L 60~63호 지장송전선로 이설공사","양산사송 공공주택지구 내 지장철탑 이설","2018-12-07 07:00","2018-12-09 18:00","2018-12-08 07:00","2018-12-09 18:00","연속"]
[244,"부산울산","북부산","삼계어방#2 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","피뢰기 설치공사관련 선로 안전이격 - 피뢰기 설치공사 : 주촌-삼계#1T/L NO.31~38호 8기","2018-12-01 07:00","2018-12-01 18:00","취소","취소","당일"]
[245,"부산울산","북부산","주촌삼계#1 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","- 피뢰기 설치공사 : 주촌-삼계#1T/L NO.31~38호 8기","2018-12-01 07:00","2018-12-01 18:00","취소","취소","당일"]
[246,"부산울산","북부산","한림정삼계#1 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","피뢰기 설치공사관련 선로 안전이격 - 피뢰기 설치공사 : 주촌-삼계#1T/L NO.31~38호 8기","2018-12-01 07:00","2018-12-01 18:00","취소","취소","당일"]
[247,"부산울산","북부산","양산S/S 154kV #1 BUS TIE CB","2018년 북부산 변전협력회사 총액공사","양산S/S 154kV 6100 Bus-Tie GIS 미동작 점검","2018-12-04 10:00","2018-12-04 18:00","2018-12-10 10:00","2018-12-10 18:00","당일"]
[248,"부산울산","북부산","엄궁학장#1 T/L","2018년 북부산 변전협력회사 총액공사","엄궁S/S 154kV 엄궁-학장 #1T/L GIS 미동작 점검","2018-12-06 10:00","2018-12-06 18:00","2018-12-06 10:00","2018-12-06 18:00","당일"]
[249,"부산울산","북부산","엄궁학장#2 T/L","2018년 북부산 변전협력회사 총액공사","엄궁S/S 154kV 엄궁-학장 #2T/L GIS 미동작 점검","2018-12-07 10:00","2018-12-07 18:00","2018-12-07 10:00","2018-12-07 18:00","당일"]
[250,"부산울산","북부산","학장S/S 154kV #1 BUS TIE CB","2018년 북부산 변전협력회사 총액공사","학장S/S 154kV 6100 Bus-Tie GIS 미동작 점검","2018-12-05 10:00","2018-12-05 18:00","2018-12-05 10:00","2018-12-05 18:00","당일"]
[251,"부산울산","서부산","서부산부민#2 T/L","서부산S/S 서부산-부민#2TL(6A7) 조작점검","서부산S/S 서부산-부민#2TL(6A7) 조작점검","2018-12-06 10:00","2018-12-06 18:00","2018-12-06 10:00","2018-12-06 18:00","당일"]
[252,"부산울산","서부산","서부산부민#1 T/L","154kV 서부산-신평, YK T/L 지중화사업","공사개요 ○ 공사구간 154kV 서부산S/S YK스틸 구내 C/H ○ 회선 및 길이 : 154kV XLPE 2,000/1,200㎟ 3C×1.2㎞ ○ 케이블 포설 : 9구간(3구간×3회선) ○ 케이블 접속 : 12개소 ○ 공사기간 : ’18.08.10∼ ’19.08.04(공기360일) / 시공사 : 공영씨엔이, 태유전력","2018-12-18 12:00","2018-12-18 13:00","2018-12-18 12:00","2018-12-18 13:00","당일"]
[253,"부산울산","서부산","서부산S/S 154kV #65 BUS","154kV 서부산-신평,YK T/L 지중화사업","변전 : 서부산S/S내 YK T/L 선로측 GIS 시험가압 지중 : ○ 공사구간 : 154kV 서부산S/S ∼ YK스틸 구내 C/H ○ 회선 및 길이 : 154kV XLPE 2,000/1,200㎟ 3C×1.2㎞ ○ 공사기간 : ’18.08.10∼ ’19.08.04(공기360일)","2018-12-18 12:00","2018-12-18 13:00","2018-12-18 12:00","2018-12-18 13:00","당일"]
[254,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진-영남TP#2T/L 송전선로용 피뢰기 설치공사","ㅁ 작업내용 : 송전선로용 피뢰기설치 ㅁ 선로명 : 154kV 방어진-영남TP#2T/L ㅁ 구간 : No.2~4(3기)","2018-12-02 07:00","2018-12-02 18:00","2018-12-02 07:00","2018-12-02 18:00","당일"]
[255,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진-영남TP#1T/L 송전선로용 피뢰기 설치공사","ㅁ 작업내용 : 송전선로용 피뢰기설치 ㅁ 선로명 : 154kV 방어진-영남TP#1T/L ㅁ 구간 : No.2~6(5기)","2018-12-01 07:00","2018-12-01 18:00","2018-12-01 07:00","2018-12-01 18:00","당일"]
[256,"부산울산","울산","신울산S/S 154kV #3 BUS TIE CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 6300 GCB 보통점검","2018-12-10 09:00","2018-12-10 18:00","2018-12-10 09:00","2018-12-10 18:00","당일"]
[257,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양#2T/L 송전선로용 피뢰기 설치공사","ㅁ 작업내용 : 송전선로용 피뢰기설치 ㅁ 선로명 : 154kV 신울산-언양#2T/L ㅁ 구간 : No.1~67(68기)","2018-12-03 07:00","2018-12-08 18:00","2018-12-03 07:00","2018-12-08 18:00","연속"]
[258,"부산울산","울산","신울산S/S 154kV #63 BUS","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 신울산-울산#1T/L 6M1DS 접촉자 과열보수 신울산S/S 154kV #63BUS PT 대체","2018-12-01 09:00","2018-12-01 18:00","2018-12-01 09:00","2018-12-01 18:00","당일"]
[259,"부산울산","울산","신울산S/S 154kV #68 BUS","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV #68BUS PT 보통점검","2018-12-07 09:00","2018-12-07 12:00","2018-12-08 09:00","2018-12-08 12:00","당일"]
[260,"부산울산","울산","신울산S/S 60-61-0 SEC CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 60-61-0 GIS 차단기 동작시험","2018-12-12 09:00","2018-12-12 14:00","2018-12-12 09:00","2018-12-12 14:00","당일"]
[261,"부산울산","울산","신울산S/S 154kV #2 BUS TIE CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 6200 GIS 차단기 동작시험","2018-12-11 14:00","2018-12-11 18:00","2018-12-11 14:00","2018-12-11 18:00","당일"]
[262,"부산울산","울산","신울산S/S 154kV #1 BUS TIE CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 6100 GIS 차단기 동작시험","2018-12-11 09:00","2018-12-11 14:00","2018-12-11 09:00","2018-12-11 14:00","당일"]
[263,"부산울산","울산","신울산S/S 67-68-0 SEC CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 67-68-0 GIS 차단기 동작시험","2018-12-14 14:00","2018-12-14 18:00","2018-12-14 14:00","2018-12-14 18:00","당일"]
[264,"부산울산","울산","신울산S/S 62-63-0 SEC CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 62-63-0 GIS 차단기 동작시험","2018-12-14 09:00","2018-12-14 14:00","2018-12-14 09:00","2018-12-14 14:00","당일"]
[265,"부산울산","울산","신울산S/S 66-67-0 SEC CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 66-67-0 GIS 차단기 동작시험","2018-12-13 14:00","2018-12-13 18:00","2018-12-13 14:00","2018-12-13 18:00","당일"]
[266,"부산울산","울산","신울산S/S 65-66-0 SEC CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 65-66-0 GIS 차단기 동작시험","2018-12-12 14:00","2018-12-12 18:00","2018-12-12 14:00","2018-12-12 18:00","당일"]
[267,"부산울산","울산","신울산S/S 61-62-0 SEC CB","2018-19년 울산전력지사 변전협력회사 총액공사","신울산S/S 154kV 61-62-0 GIS 차단기 동작시험","2018-12-13 09:00","2018-12-13 14:00","2018-12-13 09:00","2018-12-13 14:00","당일"]
[268,"부산울산","울산","신온산온산#3 T/L","2018년 울산P/O 170kV 개폐장치 정밀점검공사","온산S/S 170kV 6233 정밀점검관련 시험가압","2018-12-02 17:00","2018-12-02 18:00","2018-12-02 17:00","2018-12-02 18:00","당일"]
[269,"부산울산","울산","웅촌서창#2 T/L","2018-19년 울산저력지사 변전협력회사","웅촌S/S 154kV 웅촌-서창#2T/L GIS 차단기 동작시험","2018-12-06 14:00","2018-12-06 18:00","2018-12-08 14:00","2018-12-08 18:00","당일"]
[270,"부산울산","울산","온산처용#1 T/L","2018-19년 울산저력지사 변전협력회사","1.처용S/S 154kV 온산-처용#1T/L 보호반 대체 2.처용,용연S/S 170kV GIS 차단기 동작시험","2018-12-05 09:00","2018-12-06 18:00","2018-12-05 09:00","2018-12-06 18:00","연속"]
[271,"부산울산","직할","범일서면#2 T/L","154kV 범일 등 3개S/S 지중송전케이블 선종교체공사","154kV 범일-서면#1T/L 시험가압","2018-12-26 15:00","2018-12-27 16:00","2018-12-26 15:00","2018-12-27 16:00","연속"]
[272,"부산울산","직할","서면S/S 154kV #1 BUS","2018년 직할 관내 170kV GIS 정밀점검","서면S/S 6100 GIS #1DS 정밀점검","2018-12-04 09:00","2018-12-05 18:00","2018-12-04 09:00","2018-12-05 18:00","연속"]
[273,"부산울산","직할","서면S/S 154kV #2 BUS","2018년 직할 관내 170kV GIS 정밀점검","서면S/S 신대연-서면#1T/L GIS #2DS 정밀점검","2018-12-06 09:00","2018-12-06 20:00","2018-12-06 09:00","2018-12-06 20:00","당일"]
[274,"부산울산","직할","서면S/S 154kV #1 BUS","2018년 직할 관내 170kV GIS 정밀점검","서면S/S 신대연-서면#1T/L GIS #1DS 정밀점검","2018-12-07 09:00","2018-12-08 18:00","2018-12-07 09:00","2018-12-08 18:00","연속"]
[275,"부산울산","직할","서면S/S 154kV #1 BUS","2018년 직할 관내 170kV GIS 정밀점검","서면S/S 신대연-서면#2T/L GIS #1DS 정밀점검","2018-12-11 09:00","2018-12-12 18:00","2018-12-11 09:00","2018-12-12 18:00","연속"]
[276,"부산울산","직할","서면S/S 154kV #2 BUS","2018년 직할 관내 170kV GIS 정밀점검","서면S/S 6100 GIS #2DS 정밀점검","2018-12-03 09:00","2018-12-03 20:00","2018-12-03 09:00","2018-12-03 20:00","당일"]
[277,"부산울산","직할","서면S/S 154kV #2 BUS","2018년 직할 관내 170kV GIS 정밀점검","서면S/S 신대연-서면#2T/L GIS #2DS 정밀점검","2018-12-10 09:00","2018-12-10 20:00","2018-12-10 09:00","2018-12-10 20:00","당일"]
[278,"부산울산","직할","명장연산#1 T/L","154kV 연산S/S #3M.Tr 증설공사","신설 #3M.Tr 시험가압 24시간 - 시험가압 선로 : 명장-연산 #1T/L","2018-12-13 10:30","2018-12-14 10:30","2018-12-13 10:30","2018-12-14 10:30","연속"]
[279,"경남","통영","신고성고성 T/L","154kV 신고성-통영T/L 안전이격확보공사","154kV 신고성-통영T/L 안전이격확보공사(암조립 및 전선이설)","2018-12-01 07:00","2018-12-02 18:30","2018-12-01 07:00","2018-12-02 18:30","연속"]
[280,"경남","함안","진영한림정#1 T/L","154kV 진영-한림정T/L 4호 지장송전선로 이설공사","1. 사업구간 : 3~5호 (0.62km) 2. 사업위치 : 경남 김해시 진영읍 설창리 산1-4번지 일원 3. 송전선로 : 154kV 410㎟ Ｘ S, 2회선, 전선교체 0.62km 4. 지 지 물 : 1기 교체(사각철탑 C2-30m ⇒ 관형주 SPC2-36m)","2018-12-01 07:00","2018-12-02 18:00","2018-12-15 07:00","2018-12-16 18:00","연속"]
[281,"경남","직할","창원S/S 154kV #61 BUS","345kV 창원S/S 예비M.Tr 시험가압 및 사용전검사","345kV 창원S/S 예비M.Tr 절체 및 시험가압","2018-12-01 09:30","2018-12-02 09:30","2018-12-01 09:30","2018-12-02 09:30","연속"]
[282,"경남","진주","광양하동#1 T/L","154kV 하동S/S #4M.Tr 증설공사","154kV 하동S/S #4M.Tr 1차 GIS 설치 및 모선 시험가압","2018-12-01 15:00","2018-12-02 15:00","2018-12-01 15:00","2018-12-02 15:00","연속"]
[283,"경남","함안","신마산동읍#1 T/L","154kV 신마산-동읍#1T/L 피뢰기 설치공사","ㅇ1~5호 피뢰기 설치","2018-12-03 07:30","2018-12-03 18:00","2018-12-09 07:30","2018-12-09 18:00","당일"]
[284,"경남","함안","신마산차룡#2 T/L","154kV 신마산-차룡#2T/L 피뢰기 설치공사","154kV 신마산-차룡#2T/L 피뢰기 설치공사","2018-12-03 07:30","2018-12-03 18:00","2018-12-10 07:30","2018-12-10 18:30","당일"]
[285,"경남","진주","하동하동화력#2 T/L"," 154kV 하동S/S #4M.Tr 증설공사","154kV 하동S/S #4M.Tr 증설공사 GIS 설치 안전이격 확보","2018-12-04 09:00","2018-12-04 18:00","2018-12-04 09:00","2018-12-04 18:00"," 당일"]
[286,"경남","직할","장유마천#1 T/L","장유S/S 장유-마천#1T/L PNL 대체","장유S/S 장유-마천#1T/L PNL 대체 (병행)마천S/S 장유-마천#1T/L PNL 대체","2018-12-04 09:30","2018-12-06 17:30","2018-12-04 09:30","2018-12-06 17:30","연속"]
[287,"경남","직할","차룡창공#2 T/L","차룡S/S 차룡-창공#2T/L 장기미동작, LA 하자점검","차룡S/S 차룡-창공#2T/L 장기미동작, LA 하자점검 (병행)창공S/S 차룡-창공#2T/L 장기미동작","2018-12-04 09:30","2018-12-04 17:30","2018-12-04 09:30","2018-12-04 17:30","당일"]
[288,"경남","진주","의령S/S #1 EM.Tr CB","의령S/S #1 EM.Tr 하자점검","의령S/S #1 EM.Tr 하자점검 병행: E6133 하자점검","2018-12-05 09:00","2018-12-06 18:30","2018-12-05 09:00","2018-12-06 18:30","당일"]
[289,"경남","함안","신마산S/S 154kV #61 BUS","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산 용량부족 차단기 대체공사 M.Tr 상체크 시행 - #3M.Tr 인출변경에 따른 상체크 시행모선","2018-12-05 15:00","2018-12-05 18:00","2018-12-05 15:00","2018-12-05 18:00","당일"]
[290,"경남","함안","신마산S/S 154kV #60 BUS","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산 용량부족 차단기 대체공사 M.Tr 상체크 시행 - #3M.Tr 인출변경에 따른 상체크 시행모선","2018-12-05 15:00","2018-12-05 18:00","2018-12-05 15:00","2018-12-05 18:00","당일"]
[291,"경남","진주","광양하동#1 T/L","154kV 하동S/S #4M.Tr 증설공사","154kV 하동S/S #4M.Tr 1차 GIS #2BUS 시험가압","2018-12-07 15:00","2018-12-08 15:00","2018-12-07 15:00","2018-12-08 15:00","연속"]
[292,"경남","통영","신고성고성 T/L","154kV 신고성-통영T/L 안전이격확보공사","154kV 신고성-통영T/L 안전이격확보공사(철탑 암 취부 및 전선이설)","2018-12-08 07:00","2018-12-09 18:00","2018-12-08 07:00","2018-12-09 18:00","연속"]
[293,"경남","함안","진영한림정#2 T/L","154kV 진영-한림정T/L 4호 지장송전선로 이설공사","1. 사업구간 : 3~5호 (0.62km) 2. 사업위치 : 경남 김해시 진영읍 설창리 산1-4번지 일원 3. 송전선로 : 154kV 410㎟ Ｘ S, 2회선, 전선교체 0.62km 4. 지 지 물 : 1기 교체(사각철탑 C2-30m ⇒ 관형주 SPC2-36m)","2018-12-08 07:00","2018-12-09 18:00","2018-12-22 07:00","2018-12-23 18:00","연속"]
[294,"경남","진주","하동개양#2 T/L","154kV 하동-남해 등 2개T/L 안전이격확보 및 송전설비보강공사","154kV 하동-개양T/L 30~33호 안전이격확보 본선로구성","2018-12-09 06:00","2018-12-09 19:00","2018-12-09 06:00","2018-12-09 19:00","당일"]
[295,"경남","직할","녹공마천#2 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","녹공-마천#2 LA설치","2018-12-10 08:00","2018-12-11 18:00","2018-12-10 08:00","2018-12-11 18:00","매일"]
[296,"경남","진주","하동하동화력#2 T/L"," 154kV 하동S/S #4M.Tr 증설공사","154kV 하동S/S #4M.Tr 증설공사 모선배선 안전이격 확보","2018-12-10 09:00","2018-12-10 18:00","2018-12-10 09:00","2018-12-10 18:00"," 당일"]
[297,"경남","진주","광양하동#1 T/L","154kV 하동S/S #4M.Tr 증설공사 (최초 가압)","154kV 하동S/S #4M.Tr 최초가압 선로","2018-12-14 15:00","2018-12-15 15:00","2018-12-14 15:00","2018-12-15 15:00","연속"]
[298,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 안전이격확보공사","154kV 신고성-통영T/L 안전이격확보공사(철탑 암 취부 및 전선이설)","2018-12-15 07:00","2018-12-16 18:00","2018-12-15 07:00","2018-12-16 18:00","연속"]
[299,"경남","직할","신김해주촌#2 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신김해-주촌#2 LA설치 및 주촌-삼계#1 LA설치 안전거리확보","2018-12-15 08:00","2018-12-16 18:00","2018-12-08 08:00","2018-12-09 18:00","매일"]
[300,"경남","직할","주촌삼계#1 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","주촌-삼계#1 LA설치 및 신김해-주촌#2 LA설치 안전거리확보","2018-12-15 08:00","2018-12-16 18:00","2018-12-08 08:00","2018-12-09 18:00","매일"]
[301,"경남","통영","진동S/S 154kV #1 BUS TIE CB","진동S/S 154kV B/T GIS, PT&ES 대체공사","1. 진동S/S 154kV B/T GIS, PT&ES 철거 및 설치","2018-12-15 08:30","2018-12-31 17:00","2018-12-15 08:30","2018-12-31 17:00","연속"]
[302,"경남","진주","하동개양#1 T/L","154kV 하동-남해 등 2개T/L 안전이격확보 및 송전설비보강공사","154kV 하동-개양#1T/L 88~108호 송전선로용 피뢰기설치 안전거리확보","2018-12-09 06:00","2018-12-09 19:00","2018-12-09 06:00","2018-12-09 19:00","당일"]
[303,"경남","통영","진동S/S 154kV #2 BUS","진동S/S 154kV B/T GIS, PT&ES 대체공사","1. 진동S/S 154kV B/T GIS, PT&ES 철거 및 설치","2018-12-20 08:30","2018-12-31 10:00","2018-12-20 08:30","2018-12-31 10:00","연속"]
[304,"경남","직할","주촌삼계#1 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","주촌-삼계#1 LA설치 및 신김해-주촌#2 LA설치 안전거리확보","2018-12-22 07:00","2018-12-22 18:00","취소","취소","당일"]
[305,"경남","통영","신고성거제#1 T/L","154kV 진동-안정#1T/L 피뢰기 설치 안전확보차","154kV 진동-안정#1T/L 피뢰기 설치 안전확보차","2018-12-22 07:00","2018-12-23 18:00","2018-12-22 07:00","2018-12-23 18:00","매일"]
[306,"경남","직할","신김해주촌#2 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신김해-주촌#2 LA설치","2018-12-22 08:00","2018-12-22 18:00","취소","취소","매일"]
[307,"경남","함안","신마산S/S 154kV #60 BUS","345kV 신마산S/S 용량부족 차단기 대체공사","345kV 신마산 용량부족 차단기 대체공사 M.Tr 상체크 시행 - #4M.Tr 인출변경에 따른 상체크 시행모선","2018-12-22 15:00","2018-12-22 18:00","2018-12-22 15:00","2018-12-22 18:00","당일"]
[308,"경남","함안","초동밀양#1 T/L","154kV 초동-밀양T/L 13-14호 OPGW 이도조정 공사","154kV 초동-밀양T/L 12(여장철탑)-14호간 이도조정","2018-12-23 09:00","2018-12-23 18:00","2018-12-09 09:00","2018-12-09 18:00","당일"]
[309,"경남","함안","초동밀양#2 T/L","154kV 초동-밀양T/L 13-14호 OPGW 이도조정 공사","154kV 초동-밀양T/L 12(여장철탑)-14호간 이도조정","2018-12-23 09:00","2018-12-23 18:00","2018-12-09 09:00","2018-12-09 18:00","당일"]
[310,"경남","함안","신마산칠서#2 T/L","345kV 신마산S/S 차단기 대체관련 가공송전선로 인출변경공사","○ 345kV 신마산-삼천포화력T/L 175~176호 전력선 가선을 위한 안전이격확보","2018-12-25 07:00","2018-12-25 19:00","2018-12-25 07:00","2018-12-25 19:00","당일"]
[311,"경남","함안","신마산칠서#1 T/L","345kV 신마산S/S 차단기 대체관련 가공송전선로 인출변경공사","○ 345kV 신마산-삼천포화력T/L 175~176호 전력선 가선을 위한 안전이격확보","2018-12-25 07:00","2018-12-25 19:00","2018-12-25 07:00","2018-12-25 19:00","당일"]
[312,"경남","통영","신고성거제#2 T/L","거제S/S 154kV 신고성-거제#2T/L GIS 보통점검","1. 거제S/S 154kV 신고성-거제#2T/L GIS 보통점검 2. 신고성S/S 154kV 신고성-거제#2T/L GIS 개폐장치 조작시험","2018-12-25 09:30","2018-12-25 18:30","2018-12-25 09:30","2018-12-25 18:30","당일"]
[313,"경남","직할","신김해진영#2 T/L","345kV 및 154kV 송전선로 항공장애표지 설치공사","○ 154kV 신김해-진영T/L 28~30호 구간 항공장애표시구 설치","2018-12-29 07:00","2018-12-29 19:00","2018-12-29 07:00","2018-12-29 19:00","당일"]
[314,"경남","통영","통영거제#2 T/L","154kV 통영-거제#2T/L 피뢰기 설치","154kV 통영-거제#2T/L 피뢰기 설치","2018-12-29 07:00","2018-12-30 18:00","2018-12-29 07:00","2018-12-30 18:00","매일"]
[315,"경남","직할","신김해주촌#2 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신김해-주촌#2 LA설치","2018-12-29 08:00","2018-12-29 18:00","2018-12-29 08:00","2018-12-29 18:00","당일"]
[316,"경남","통영","고성통영 T/L","154kV 통영-거제#2T/L 피뢰기 설치 안전확보차","154kV 통영-거제#2T/L 피뢰기 설치 안전확보차","2018-12-29 09:00","2018-12-29 18:00","2018-12-29 09:00","2018-12-29 18:00","당일"]
[317,"경남","통영","신고성거제#1 T/L","154kV 통영-거제#2T/L 피뢰기 설치 안전확보차","154kV 통영-거제#2T/L 피뢰기 설치 안전확보차","2018-12-30 07:00","2018-12-30 18:00","2018-12-30 07:00","2018-12-30 18:00","당일"]
[318,"경남","함안","한림정삼계#2 T/L","항공장애표시구 시설공사","한림정-삼계T/L 12~13호 항공장애표시구 2EA 설치","2018-12-30 09:00","2018-12-30 18:00","2018-12-30 09:00","2018-12-30 18:00","당일"]
[319,"경남","함안","한림정삼계#1 T/L","항공장애표시구 시설공사","154kV 한림정-삼계T/L 12~13호 항공장애표시구 2EA 시설","2018-12-30 09:00","2018-12-30 18:00","2018-12-30 09:00","2018-12-30 18:00","당일"]
[320,"남서울","강남","신성남사당#1 T/L","154kV 동빙고반포 등 2개T/L 자기애관 교체공사","자기애관을 폴리머 애관으로 교체(6상)","2018-12-03 09:00","2018-12-05 18:00","2018-12-03 09:00","2018-12-05 18:00","연속"]
[321,"남서울","강남","신성남사당#2 T/L","154kV 동빙고반포 등 2개T/L 자기애관 교체공사","자기애관을 폴리머 애관으로 교체(6상)","2018-12-06 09:00","2018-12-08 18:00","2018-12-06 09:00","2018-12-08 18:00","연속"]