{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":9,"n_cols":16,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
["2019년도 3월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #4 M.Tr A-1","765kV #4M.Tr 보호반 교체공사","765kV #4M.Tr 보호반 교체","2019-03-18 08:00","2019-03-29 18:00","2019-03-18 08:00","2019-03-29 18:00","연속",null,null,null,201812170029]
[2,"경기북부","구리","신가평S/S #2 M.Tr A-1","765kV #2M.Tr 보호반 교체공사","765kV #2M.Tr 보호반 교체","2019-03-04 08:00","2019-03-15 18:00","2019-03-04 08:00","2019-03-15 18:00","연속",null,null,null,201812170027]
[3,"경기","성남","신안성신가평 T/L","2018-2019년 성남전력지사 송전정비회사 총액공사","- 765kV 신안성-신가평T/L 항공장애표시도장(20기)","2019-03-04 07:00","2019-03-22 18:00","취소","취소","연속",null,null,null,201901090094]
[4,"강원","태백","신태백신가평#1 T/L","항공장애표시구 설치","765kV 신태백-신가평#1T/L 항공장애표시구 설치","2019-03-04 10:00","2019-03-07 18:00","취소","취소","연속",null,null,null,201901070026]
[5,"대전충남","서산","당진T/P 765kV #2 BUS","당진화력 765kV #2BUS 가공모선 C상 인하선 장력해소 공사","당진화력 765kV #2BUS 가공모선 C상 인하선 장력해소 공사 (#4,5,6GEN O/H)","2019-03-20 09:00","2019-03-22 18:00","2019-03-20 09:00","2019-03-22 18:00","연속",null,null,null,201901100052]

{"sheet":"345송부","index":1,"n_rows":236,"n_cols":16,"rows_kept":236,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,14,3,14],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
["2019년도 3월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #4 M.Tr A","19년 성동P/O 변전협력회사 총액공사","#4M.Tr보호반, B/F반 교체(성동S/S #4M.Tr)","2019-03-20 09:30","2019-03-29 17:00","2019-03-20 09:30","2019-03-29 17:00","연속",null,null,null,201901150243]
[2,"서울","성동","미금성동#3 T/L","19년 성동P/O 변전협력회사 총액공사","#4M.Tr보호반, B/F반 교체","2019-03-20 09:30","2019-03-29 17:00","2019-03-20 09:30","2019-03-29 17:00","연속",null,null,null,201901150246]
[3,"남서울","강남","신양재S/S #3 M.Tr A","신양재S/S #3M.Tr 2차측 170kV GIS 에어 누기개소 보수","신양재S/S #3M.Tr 2차측 170kV GIS 에어 누기개소 보수","2019-03-12 09:00","2019-03-12 18:00","2019-03-12 09:00","2019-03-12 18:00","당일",null,null,null,201901180122]
[4,"남서울","동서울","동서울미금#1 T/L","345kV 동서울-미금#1,2T/L 자기애관 교체공사","대상설비 : 345kV 동서울-미금#1,2T/L No.18C/H 6상 공사내용 : 자기애관 교체 (폴리머애관)","2019-03-09 09:00","2019-03-13 18:00","2019-03-09 09:00","2019-03-13 18:00","연속",null,null,null,201901150179]
[5,"남서울","영등포","신광명S/S #73Bay TIE CB (7300)","신광명S/S 345kV 차단기 보통점검","신광명S/S 345kV 차단기 보통점검","2019-03-14 09:00","2019-03-14 18:00","2019-03-14 09:00","2019-03-14 18:00","연속",null,null,null,201901150059]
[6,"남서울","영등포","신광명S/S 345kV 70-71 SEC CB (70-71-0)","신광명S/S 345kV 차단기 보통점검","신광명S/S 345kV 차단기 보통점검","2019-03-11 09:00","2019-03-11 18:00","2019-03-11 09:00","2019-03-11 18:00","당일",null,null,null,201901150054]
[7,"남서울","영등포","신광명S/S 신시흥-신광명#1T/L CB (7172)","신광명S/S 345kV 차단기 보통점검","신광명S/S 345kV 차단기 보통점검","2019-03-13 09:00","2019-03-13 18:00","2019-03-13 09:00","2019-03-13 18:00","당일",null,null,null,201901150057]
[8,"남서울","영등포","신광명S/S 345kV 75-76 SEC CB (75-76-0)","신광명S/S 345kV 차단기 보통점검","신광명S/S 345kV 차단기 보통점검","2019-03-12 09:00","2019-03-12 18:00","2019-03-12 09:00","2019-03-12 18:00","연속",null,null,null,201901150056]
[9,"남서울","직할","영등포S/S 영서-영등포#2T/L CB (7271)","영등포S/S 345kV 신광명-영등포#2T/L(7271)CB 정밀점검공사","영등포S/S 345kV 신광명-영등포#2T/L(7271)CB 정밀점검공사","2019-03-25 09:00","2019-03-28 18:00","취소","취소","연속",null,null,null,201901170003]
[10,"남서울","직할","영등포S/S 영서-영등포#1T/L CB (7171)","영등포S/S 345kV 신광명-영등포#1T/L(7171)CB 정밀점검공사","영등포S/S 345kV 신광명-영등포#1T/L(7171)CB 정밀점검공사","2019-03-18 09:00","2019-03-21 18:00","취소","취소","연속",null,null,null,201901170002]
[11,"인천","인천","서인천C/C #2 M.Tr","서인천복합S/Y 72BAY B/F 보호반 대체공사","서인천복합S/Y 72BAY B/F 보호반 대체공사 서인천복합S/Y 7271, 7200, 7272 GIS 조작시험 서인천복합S/Y #2M.Tr 1차 LA 대체","2019-03-11 09:00","2019-03-15 18:00","2019-03-11 09:00","2019-03-15 18:00","연속",null,null,null,201901090103]
[12,"인천","인천","신경서서인천CC T/L","서인천복합S/Y 72BAY B/F 보호반 대체공사","서인천복합S/Y 72BAY B/F 보호반 대체공사 서인천복합S/Y 7271, 7200, 7272 GIS 조작시험 서인천복합S/Y #2M.Tr 1차 LA 대체","2019-03-11 09:00","2019-03-15 18:00","2019-03-11 09:00","2019-03-15 18:00","연속",null,null,null,201901090104]
[13,"인천","인천","신가좌신시흥#1 T/L","신가좌신시흥#1 T/L 보호배전반 성능개선","GE제 보호계전기 성능개선","2019-03-04 09:00","2019-03-04 18:00","2019-03-04 09:00","2019-03-04 18:00","연속",null,null,null,201901150250]
[14,"인천","인천","신가좌S/S #4 M.Tr A","신가좌S/S #4M.Tr 휴전","신가좌S/S 7600, 7672 GIS 하자점검 신가좌S/S 4479, 4479-1 VCB 조작시험 신가좌S/S 4479-2 VCB 보통점검 신가좌S/S 7622DS 제작사 하자 보수","2019-03-11 09:00","2019-03-13 18:00","2019-03-11 09:00","2019-03-13 18:00","연속",null,null,null,201901070164]
[15,"인천","인천","신가좌신시흥#2 T/L","신가좌신시흥#2 T/L 보호배전반 성능개선","GE제 보호계전기 성능개선","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","연속",null,null,null,201901150251]
[16,"인천","인천","(신)신인천C/C 신경서신인천T/L-4MT201 CB (7800(신))","신인천복합S/Y 7800 GIS 조작시험","신인천복합S/Y 7800 GIS 조작시험","2019-03-06 13:00","2019-03-06 18:00","2019-03-06 13:00","2019-03-06 18:00","당일",null,null,null,201901070351]
[17,"인천","인천","(신)신인천C/C 71-72 SEC GIS","신인천복합S/Y 71-72-0 GIS 하자점검","신인천복합S/Y 71-72-0 GIS 하자점검","2019-03-07 09:00","2019-03-07 18:00","2019-03-07 09:00","2019-03-07 18:00","연속",null,null,null,201901070354]
[18,"인천","인천","(신)신인천C/C 75-76 SEC GIS","신인천복합S/Y 75-76-0 GIS 하자점검","신인천복합S/Y 75-76-0 GIS 하자점검","2019-03-08 09:00","2019-03-08 18:00","2019-03-08 09:00","2019-03-08 18:00","당일",null,null,null,201901070355]
[19,"인천","인천","(신)신인천C/C 3MT201 CB (7672(신))","신인천복합S/Y 7672 GIS 조작시험","신인천복합S/Y 7672 GIS 조작시험","2019-03-05 13:00","2019-03-05 18:00","2019-03-05 13:00","2019-03-05 18:00","연속",null,null,null,201901070348]
[20,"인천","인천","(신)신인천C/C 신경서신인천CCT/L CB (7871(신))","신인천복합S/Y 7871 GIS 조작시험","신인천복합S/Y 7871 GIS 조작시험","2019-03-06 09:00","2019-03-06 13:00","2019-03-06 09:00","2019-03-06 13:00","연속",null,null,null,201901070350]
[21,"인천","인천","(신)신인천C/C 3MT101 CB (7572(신))","신인천복합S/Y 7572 GIS 조작시험","신인천복합S/Y 7572 GIS 조작시험","2019-03-04 13:00","2019-03-04 18:00","2019-03-04 13:00","2019-03-04 18:00","연속",null,null,null,201901070276]
[22,"인천","인천","(신)신인천C/C TIE-3MT101 CB (7500(신))","신인천복합S/Y 7500 GIS 조작시험","신인천복합S/Y 7500 GIS 조작시험","2019-03-04 09:00","2019-03-04 13:00","2019-03-04 09:00","2019-03-04 13:00","연속",null,null,null,201901070182]
[23,"인천","인천","신김포신인천CC T/L","신김포-신경서간 광케이블 시설공사","신김포-신경서간 광케이블 시설(OPGW : 13.4Km 시설)","2019-03-18 07:00","2019-03-31 18:00","2019-03-18 07:00","2019-03-31 18:00","연속",null,null,null,201812030088]
[24,"인천","인천","(신)신인천C/C 3MT001-3MT201 CB (7600(신))","신인천복합S/Y 7600 GIS 조작시험","신인천복합S/Y 7600 GIS 조작시험","2019-03-05 09:00","2019-03-05 13:00","2019-03-05 09:00","2019-03-05 13:00","연속",null,null,null,201901070346]
[25,"인천","직할","서인천CC-신부평#2T/L-#2 M.Tr 1차 CB (7200)","신부평S/S 7200CB 362kV GIS 정밀점검","신부평S/S 7200CB 362kV GIS 정밀점검","2019-03-13 09:00","2019-03-15 18:00","2019-03-13 09:00","2019-03-15 18:00","연속",null,null,null,201901150168]
[26,"인천","직할","신부평S/S 345kV #4Sh.R CB (7479)","신부평S/S 7479CB 362kV GIS 정밀점검","신부평S/S 7479CB 362kV GIS 정밀점검(#4Sh.R)","2019-03-18 09:00","2019-03-20 18:00","2019-03-18 09:00","2019-03-20 18:00","연속",null,null,null,201901150164]
[27,"인천","직할","신부평S/S 서인천CC-신부평#2T/L CB (7271)","신부평S/S 7271CB 362kV GIS 정밀점검","신부평S/S 7271CB 362kV GIS 정밀점검","2019-03-21 09:00","2019-03-23 18:00","2019-03-21 09:00","2019-03-23 18:00","연속",null,null,null,201901150169]
[28,"인천","직할","서인천CC신부평#3 T/L","신부평S/S 서인천신부평#3T/L 보호반 대체","신부평S/S 서인천신부평#3T/L 보호반 대체","2019-03-25 09:00","2019-03-29 18:00","2019-03-25 09:00","2019-03-29 18:00","연속",null,null,null,201901090243]
[29,"경기북부","고양","신덕은S/S #4 M.Tr A","154kV 신덕은S/S #64D.Tr 증설공사","154kV M.Tr 1bank 설치 170kV GIS 1CCT 설치 25.8kV GIS 4CCT 설치","2019-03-20 12:00","2019-03-20 16:00","2019-03-20 12:00","2019-03-20 16:00","매일",null,null,null,201901090001]
[30,"경기북부","고양","신덕은S/S #3 M.Tr A","345kV 신덕은S/S #3M.Tr B상 가스발생관련 내부정밀점검","345kV 신덕은S/S #3M.Tr B상 가스발생관련 내부정밀점검","2019-03-25 09:00","2019-03-29 18:00","2019-03-11 09:00","2019-03-15 18:00","연속",null,null,null,201901150209]
[31,"경기북부","고양","신덕은동두천CC#2 T/L","신덕은변전소 외 3개소 내진보강공사","신덕은변전소 외 3개소 내진보강공사","2019-03-25 07:00","2019-03-29 18:00","2019-03-25 07:00","2019-03-29 18:00","매일",null,null,null,201901150218]
[32,"경기북부","고양","신파주S/S #1 M.Tr A","19년도 고양전력지사 변전협력회사 총액공사(M.Tr 보통점검)","#1M.Tr 및 부속설비(GIS, LA등)보통점검","2019-03-11 10:00","2019-03-12 18:00","2019-03-11 10:00","2019-03-12 18:00","당일",null,null,null,201901150244]
[33,"경기북부","고양","신파주S/S #2 M.Tr A","19년도 고양전력지사 변전협력회사 총액공사(M.Tr 보통점검)","#2M.Tr 및 부속설비(GIS, LA등)보통점검","2019-03-14 10:00","2019-03-15 18:00","2019-03-14 10:00","2019-03-15 18:00","당일",null,null,null,201901150245]
[34,"경기북부","고양","신파주S/S #3 M.Tr A","19년도 고양전력지사 변전협력회사 총액공사(M.Tr 보통점검)","#3M.Tr 및 부속설비(GIS, LA등)보통점검","2019-03-18 10:00","2019-03-19 18:00","2019-03-18 10:00","2019-03-19 18:00","연속",null,null,null,201901150247]
[35,"경기북부","고양","신덕은파주문산CC#1 T/L","19년도 고양전력지사 변전협력회사 총액공사(GIS 하자점검)","파주문산CC 신덕은SS 신덕은-파주문산#1T/L GIS 하자점검 파주문산CC 개폐써지 측정 센서 철거","2019-03-04 10:00","2019-03-06 18:00","2019-03-04 10:00","2019-03-06 18:00","연속",null,null,null,201901150236]
[36,"경기북부","고양","신덕은파주문산CC#2 T/L","19년도 고양전력지사 변전협력회사 총액공사(GIS 하자점검)","파주문산CC 신덕은SS 신덕은-파주문산#2T/L GIS 하자점검","2019-03-07 10:00","2019-03-08 18:00","2019-03-07 10:00","2019-03-08 18:00","당일",null,null,null,201901150238]
[37,"경기북부","구리","미금성동#1 T/L","345kV GIS 정밀점검 공사(18년 계약분)","345kV GIS 정밀점검 공사(18년 계약분) - 7171, 7100 GIS 정밀점검","2019-03-09 09:00","2019-03-14 18:00","2019-03-09 09:00","2019-03-14 18:00","당일",null,null,null,201812170076]
[38,"경기북부","구리","신가평미금#1 T/L","154kV 신가평-미금#1T/L 불량압축인류크램프 교체공사","ㅇ 불량압축인류크램프 교체 - 대상 : No.81호","2019-03-15 07:00","2019-03-15 18:00","2019-03-15 07:00","2019-03-15 18:00","연속",null,null,null,201811150112]
[39,"경기북부","구리","신가평미금#2 T/L","345kV 신가평-미금#2T/L 항공장애표시구 설치공사","ㅇ 항공장애표시구 설치 - 대상 : No.94~95호","2019-03-14 07:00","2019-03-14 18:00","2019-03-14 07:00","2019-03-14 18:00","당일",null,null,null,201901140110]
[40,"경기북부","구리","동서울미금#2 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33,No.34~38 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2019-03-24 09:00","2019-03-25 18:00","2019-03-24 09:00","2019-03-25 18:00","연속",null,null,null,201812310027]
[41,"경기북부","구리","미금S/S STATCOM CB","미금S/S 345kV STATCOM 보통점검공사","미금S/S 345kV STATCOM 보통점검공사","2019-03-18 09:00","2019-04-05 18:00","2019-03-18 09:00","2019-04-05 18:00","연속",null,null,null,201901150137]
[42,"경기북부","구리","동서울미금#2 T/L","미금S/S 345kV #74BAY B/F반 교체공사","미금S/S 345kV #74BAY B/F반 교체","2019-03-16 09:00","2019-03-20 18:00","2019-03-16 09:00","2019-03-20 18:00","연속",null,null,null,201812170077]
[43,"경기북부","구리","신포천S/S 345kV #1 Sh.R","345kV GIS 정밀점검 공사(18년 계약분)","345kV GIS 정밀점검 공사(18년 계약분) - 7379 GIS 정밀점검","2019-03-04 09:00","2019-03-06 18:00","2019-03-04 09:00","2019-03-06 18:00","연속",null,null,null,201812170088]
[44,"경기북부","직할","신의정부미금#1 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33,No.34~38","2019-03-16 09:00","2019-03-21 18:00","2019-03-16 09:00","2019-03-21 18:00","연속",null,null,null,201812310022]
[45,"경기북부","직할","신의정부미금#2 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33,No.34~38","2019-03-22 09:00","2019-04-01 18:00","2019-03-22 09:00","2019-04-01 18:00","연속",null,null,null,201812310024]
[46,"경기북부","직할","양주S/S #1 M.Tr A","양주S/S 345kV M.Tr 3차측 SIS화 공사","1. 양주S/S 170kV GIS화 공사 관련 345kV M.Tr 3차측 SIS화 공사 2. 23kV VCB 철거 및 SIS 40kA 설치","2019-03-18 09:00","2019-03-27 18:00","2019-03-18 09:00","2019-03-27 18:00","연속",null,null,null,201901150257]
[47,"경기북부","직할","양주S/S #3 M.Tr A","양주S/S 345kV M.Tr 3차측 SIS화 공사","1. 양주S/S 170kV GIS화 공사 관련 345kV M.Tr 3차측 SIS화 공사 2. 23kV VCB 철거 및 SIS 40kA 설치","2019-03-07 09:00","2019-03-16 18:00","2019-03-07 09:00","2019-03-16 18:00","당일",null,null,null,201901150256]
[48,"경기","군포","서서울#2S/S #6 M.Tr A","19년 군포변전정비회사 총액공사","주변압기/붓싱 하자점검 345kV GIS 하자점검(7B72, 7B00), 154kV GIS 하자점검(6644) 3차 Main VCB(4679), #2S.Tr VCB(4689), Sh.R VCB(4679-1,2)하자점검","2019-03-27 09:00","2019-03-29 18:00","2019-03-27 09:00","2019-03-29 18:00","연속",null,null,null,201901080048]
[49,"경기","군포","서서울#2S/S #5 M.Tr A","19년 군포변전정비회사 총액공사","주변압기/붓싱 하자점검 345kV GIS 하자점검(7A72, 7A00), 154kV GIS 하자점검(6544) 23kV GIS #1S.Tr CB(4589) 하자점검","2019-03-25 09:00","2019-03-26 18:00","2019-03-25 09:00","2019-03-26 18:00","연속",null,null,null,201901080047]
[50,"경기","군포","화성서서울#2 T/L","345kV화성-서서울#2T/L정밀점검(19년 가공송전 위탁공사)","345kV화성-서서울#2T/L 1호~69호 정밀점검","2019-03-18 09:00","2019-03-22 18:00","취소","취소","연속",null,null,null,201901070456]
[51,"경기","군포","서서울S/S #3 M.Tr","154kV 남군포S/S 건설사업","o서서울S/S~남군포S/S간 신설 변전설비 무부하 가압 - 서서울~남군포#1.2T/L","2019-03-26 09:00","2019-03-29 18:00","취소","취소","연속",null,null,null,201901180035]
[52,"경기","군포","화성서서울#1 T/L","345kV화성-서서울#1T/L정밀점검(19년 가공송전 위탁공사)","345kV화성-서서울#1T/L 1호~69호 정밀점검","2019-03-11 09:00","2019-03-15 18:00","취소","취소","연속",null,null,null,201901070455]
[53,"경기","군포","서서울S/S #1 M.Tr A","'19년 군포P/O 변전정비회사 총액공사","- 345kV 7300, 7372 GIS 보통점검, 154kV 6144 GIS 초기점검","2019-03-25 09:00","2019-03-25 18:00","2019-03-25 09:00","2019-03-25 18:00","연속",null,null,null,201901080111]
[54,"경기","군포","서서울S/S #2 M.Tr A","'19년 군포P/O 변전정비회사 총액공사","- 345kV 7572,7500 GIS 보통점검, 154kV 6244 GIS 초기점검","2019-03-26 09:30","2019-03-26 18:00","2019-03-26 09:30","2019-03-26 18:00","연속",null,null,null,201901080121]
[55,"경기","군포","신온양서서울#2 T/L","345kV 신온양-서서울 T/L 전선접속개소 전선교체공사","0 전선교체 : No.169-174","2019-03-05 07:00","2019-03-08 18:00","2019-03-08 07:00","2019-03-11 18:00","연속",null,null,null,201901100125]
[56,"경기","군포","신온양서서울#1 T/L","345kV 신온양-서서울 T/L 전선접속개소 전선교체공사","0 전선교체 : No.169-174","2019-03-01 09:00","2019-03-04 18:00","2019-03-04 09:00","2019-03-07 18:00","연속",null,null,null,201901100123]
[57,"경기","군포","신안산S/S #1 M.Tr A","345kV 신안산S/S 용량부족 GIS 대체공사","○ 362kV 40kA 8CB 철거, 63kA 11CB 설치 - F/R 입력요소 변경에 따른 #1M.Tr 휴전","2019-03-18 09:00","2019-03-18 18:00","2019-03-18 09:00","2019-03-18 18:00","당일",null,null,null,201901100142]
[58,"경기","군포","신시흥신안산 T/L","345kV 신안산S/S 용량부족 GIS 대체공사","○ 362kV 40kA 8CB 철거, 63kA 11CB 설치 - F/R 입력요소 변경에 따른 신시흥-신안산T/L 휴전","2019-03-17 09:00","2019-03-17 18:00","2019-03-20 09:00","2019-03-20 18:00","당일",null,null,null,201901100138]
[59,"경기","동부","곤지암신충주#1 T/L","345kV 곤지암-신충주 #1T/L 송전선로 정밀점검","345kV 곤지암-신충주 #1T/L 1~140호 송전선로 정밀점검","2019-03-11 09:00","2019-03-16 18:00","2019-03-12 09:00","2019-03-17 18:00","당일",null,null,null,201901100075]
[60,"경기","동부","곤지암신충주#2 T/L","345kV 곤지암-신충주 #2T/L 송전선로 정밀점검","345kV 곤지암-신충주 #2T/L 1~140호 송전선로 정밀점검","2019-03-18 09:00","2019-03-22 18:00","2019-03-18 09:00","2019-03-22 18:00","당일",null,null,null,201901100078]
[61,"경기","동부","곤지암S/S 345kV #1Sh.R GIS","19년 동부변전협력회사 총액공사","곤지암:7179 GIS (보통)","2019-03-07 09:00","2019-03-07 18:00","2019-03-07 09:00","2019-03-07 18:00","당일",null,null,null,201901070467]
[62,"경기","성남","서안성S/S #4 M.Tr A","서안성S/S #4M.Tr 보통점검 등","서안성S/S #4M.Tr 보통점검, 7672,7600 하자점검","2019-03-19 09:00","2019-03-20 18:00","2019-03-19 09:00","2019-03-20 18:00","매일",null,null,null,201901110170]
[63,"경기","성남","신수원S/S #2 M.Tr A","신수원S/S #2M.TR 보통점검 등","신수원S/S #2M.TR 보통점검, 1,2,3차 LA 보통점검, #2S.Tr 보통점검, #2S.Tr GIS 4279 보통점검, 6244 조작시험","2019-03-16 09:00","2019-03-17 18:00","2019-03-16 09:00","2019-03-17 18:00","연속",null,null,null,201901110153]
[64,"경기","성남","신수원S/S #1 M.Tr A","신수원S/S #1M.Tr 보통점검 등","신수원S/S #1M.Tr 보통점검, 1,3차 LA 보통점검, #1S.Tr 보통점검, 4179 GIS 보통점검, 6144 조작시험","2019-03-09 09:00","2019-03-10 18:00","2019-03-09 09:00","2019-03-10 18:00","연속",null,null,null,201901110164]
[65,"경기","성남","신용인S/S #3 M.Tr A","#3M.Tr 누유보수","#3M.Tr 누유보수","2019-03-23 09:00","2019-03-24 18:00","2019-03-23 09:00","2019-03-24 18:00","당일",null,null,null,201901180131]
[66,"경기","성남","신용인신수원 T/L","신용인S/S 신용인-신수원T/L 7771,7770 GIS 하자점검","신용인S/S 신용인-신수원T/L 7771,7770 GIS 하자점검 LA, CVT 하자점검","2019-03-13 09:00","2019-03-13 18:00","취소","취소","연속",null,null,null,201901110150]
[67,"경기","성남","신용인S/S 345kV #1 BUS","신용인S/S #4M.Tr 증설용 362kV GIS 설치공사","362kV GIS x 2CB 설치 기타 부대작업 x 1식","2019-03-18 09:00","2019-03-22 18:00","2019-03-18 09:00","2019-03-22 18:00","당일",null,null,null,201901100105]
[68,"경기","성남","신용인S/S 345kV #2 BUS","신용인S/S #4M.Tr 증설용 362kV GIS 설치공사","362kV GIS x 2CB 설치 기타 부대작업 x 1식","2019-03-25 09:00","2019-03-29 18:00","2019-03-25 09:00","2019-03-29 18:00","연속",null,null,null,201901100115]
[69,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울T/L EBA 애관 교체공사","자기애관 시범교체 6상(1T/L : 3상, 2T/L : 3상)","2019-03-30 08:00","2019-04-01 18:00","2019-03-30 08:00","2019-04-01 18:00","연속",null,null,null,201901080031]
[70,"경기","성남","신용인S/S 345kV #1 Sh.R","신용인S/S #1Sh.R 보통점검 등","신용인S/S #1Sh.R 보통점검, 7772, 7779 하자점검","2019-03-28 09:00","2019-03-29 18:00","2019-03-28 09:00","2019-03-29 18:00","연속",null,null,null,201901110161]
[71,"경기","성남","신용인동서울#1 T/L","신용인S/S #4M.Tr 증설용 362kV GIS 설치공사","362kV GIS x 2CB 설치관련 무부하가압","2019-03-21 18:00","2019-03-22 18:00","2019-03-21 18:00","2019-03-22 18:00","연속"]
[72,"경기","성남","신용인동서울#1 T/L","신용인S/S #4M.Tr 증설용 362kV GIS 설치공사","362kV GIS x 2CB 설치관련 무부하가압","2019-03-28 18:00","2019-03-29 18:00","2019-03-28 18:00","2019-03-29 18:00","연속"]
[73,"경기","직할","화성신안산 T/L","화성S/S 용량부족 차단기대체 및 SW증설 공사","- 휴전작업내용 : #70-71 SEC GIS 71모선 연결후 무부하가압 *공사개요 ○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB)","2019-03-18 11:00","2019-03-19 11:00","2019-03-18 11:00","2019-03-19 11:00","연속",null,null,null,201901140123]
[74,"경기","직할","아산화성#1 T/L","345kV 신평택-화성T/L 건설관련 안전이격 확보공사","아산화성 No.128 인클로징공사 (19m → 25m)","2019-03-24 07:00","2019-04-01 18:00","2019-03-24 07:00","2019-04-01 18:00","연속",null,null,null,201901100194]
[75,"경기","직할","화성S/S 345kV #2LCR 75BUS GIS CB (7577)","화성S/S 용량부족 차단기대체 및 SW증설 공사","- 휴전작업내용 : 한류리액터 이설관련 #1CLR 설치관련 안전이격확보 *공사개요 ○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB)","2019-03-11 09:00","2019-03-12 18:00","2019-03-11 09:00","2019-03-12 18:00","당일",null,null,null,201901140119]
[76,"경기","직할","화성S/S 345kV #2LCR 76BUS GIS CB (7677)","화성S/S 용량부족 차단기대체 및 SW증설 공사","- 휴전작업내용 : 한류리액터 이설관련 #1CLR 설치관련 안전이격확보 *공사개요 ○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB)","2019-03-11 09:00","2019-03-12 18:00","2019-03-11 09:00","2019-03-12 18:00","매일",null,null,null,201901140121]
[77,"경기","직할","화성S/S 345kV #71 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","- 휴전작업내용 : #70-71 SEC GIS #71모선 연결 *공사개요 ○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ 신평택발전T/L SW증설(4CB)","2019-03-04 09:00","2019-03-19 18:00","2019-03-04 09:00","2019-03-19 18:00","매일",null,null,null,201901140124]
[78,"경기","평택","평택T/P 평택#2C/C #1 S/T 1차 GIS","평택T/P 345kV 7872CB GIS 보통점검","평택T/P 345kV 7872CB GIS 보통점검","2019-03-29 10:00","2019-03-29 18:00","2019-03-29 10:00","2019-03-29 18:00","당일",null,null,null,201901100055]
[79,"경기","평택","평택T/P 평택T/P-평택#2C/C #1 G/T 1차 GIS","평택T/P 345kV 7700CB GIS 보통점검","평택T/P 345kV 7700CB GIS 보통점검","2019-03-26 10:00","2019-03-26 18:00","2019-03-26 10:00","2019-03-26 18:00","연속",null,null,null,201901100051]
[80,"경기","평택","평택T/P 평택#2C/C #1 G/T 1차 GIS","평택T/P 345kV 7771CB GIS 보통점검","평택T/P 345kV 7771CB GIS 보통점검","2019-03-25 10:00","2019-03-25 18:00","2019-03-25 10:00","2019-03-25 18:00","연속",null,null,null,201901100050]
[81,"경기","평택","평택T/P 평택#2C/C #2 G/T-#1 S/T 1차 GIS","평택T/P 345kV 7800CB GIS 보통점검","평택T/P 345kV 7800CB GIS 보통점검","2019-03-28 10:00","2019-03-28 18:00","2019-03-28 10:00","2019-03-28 18:00","연속",null,null,null,201901100054]
[82,"경기","평택","평택T/P 평택#2C/C #2 G/T 1차 GIS","평택T/P 345kV 7871CB GIS 보통점검","평택T/P 345kV 7871CB GIS 보통점검","2019-03-27 10:00","2019-03-27 18:00","2019-03-27 10:00","2019-03-27 18:00","당일",null,null,null,201901100053]
[83,"강원","동해","동해북평TP#3 T/L","345kV 동해-북평TPT/L 광통신케이블 보수공사","345kV 동해-북평TPT/L 광통신케이블 보수","2019-03-08 09:00","2019-03-09 18:00","2019-03-22 09:00","2019-03-23 18:00","당일",null,null,null,201901090214]
[4,"강원","동해","동해S/S 345kV #2 BUS","동해S/S STATCOM용 GIS 설치공사","○ 362kV 6300A 63kA GIS × 2CB ○ 기타부대공사 1식","2019-03-04 14:00","2019-03-05 18:00","2019-03-27 09:00","2019-03-28 18:00","연속",null,null,null,201812170084]
[85,"강원","동해","동해S/S 345kV #1 BUS","동해S/S STATCOM용 GIS 설치공사","○ 362kV 6300A 63kA GIS × 2CB ○ 기타부대공사 1식","2019-03-04 09:00","2019-03-04 13:00","2019-03-25 09:00","2019-03-26 18:00","연속",null,null,null,201812170083]
[86,"강원","동해","동해북평TP#1 T/L","345kV 동해-북평TPT/L 광통신케이블 보수공사","345kV 동해-북평TPT/L 광통신케이블 보수","2019-03-04 09:00","2019-03-05 18:00","2019-03-18 09:00","2019-03-19 18:00","연속",null,null,null,201901090212]
[87,"강원","동해","동해북평TP#2 T/L","345kV 동해-북평TPT/L 광통신케이블 보수공사","345kV 동해-북평TPT/L 광통신케이블 보수","2019-03-06 09:00","2019-03-07 18:00","2019-03-20 09:00","2019-03-21 18:00","당일",null,null,null,201901090213]
[88,"강원","동해","동해S/S #3 M.Tr A","동해S/S STATCOM 설치공사","○ #3M.Tr 3차 VCB 부품 교체작업","2019-03-05 09:00","2019-03-06 18:00","2019-03-05 09:00","2019-03-06 18:00","연속",null,null,null,201901080006]
[89,"강원","동해","삼척GP 동해-삼척GP #1/L-#3M.Tr 1차 CB (7600)","삼척GP 362kV GIS 유압계통 제작사 합동점검","1. 유압계통 점검","2019-03-26 10:00","2019-03-26 18:00","2019-03-26 10:00","2019-03-26 18:00","연속",null,null,null,201901160015]
[90,"충북","직할","신제천신충주#2 T/L","345kV 신제천-신충주 등 2개T/L 스페이서 교체공사","345kV 신제천-신충주T/L, 곤지암-신충주T/L 스페이서 댐퍼 778개 교체","2019-03-11 08:00","2019-03-16 18:00","2019-03-12 08:00","2019-03-17 18:00","연속",null,null,null,201901100135]
[91,"충북","직할","신제천S/S #2 M.Tr A","345kV 신제천S/S TCSC 설치공사(일반)","- STr용 23kV VCB 3000A 설치 1식 - STr용 23kV VCB 600A 설치 1식 - 23kV 3000A DS 설치 1식 - 23kV 600A DS 설치 1식 - 전력케이블 설치 1식 - 기타 부대공사","2019-03-11 09:00","2019-03-15 18:00","2019-03-04 09:00","2019-03-08 18:00","연속",null,null,null,201901090252]
[92,"충북","직할","신제천신충주#1 T/L","345kV 신제천-신충주 등 2개T/L 스페이서 교체공사","345kV 신제천-신충주T/L, 곤지암-신충주T/L 스페이서 댐퍼 778개 교체","2019-03-17 08:00","2019-03-22 18:00","2019-03-18 08:00","2019-03-23 18:00","매일",null,null,null,201901100134]
[93,"충북","직할","신제천S/S 345kV #2 BUS","신제천S/S 345kV #2BUS부 DS 제작사(LS) 하자대체","- 345kV 수평 EDS 제작사 하자대체 - 대상 : 7352,7452,7A52DS","2019-03-18 09:00","2019-03-23 18:00","취소","취소","연속",null,null,null,201901090251]
[94,"충북","직할","신제천S/S 345kV #1 BUS","신제천S/S 345kV #1BUS부 DS 제작사(LS) 하자대체","- 345kV 수평 EDS 제작사 하자대체 - 대상 : 73351,7451,7651,7751,7951,7A51","2019-03-25 09:00","2019-04-06 18:00","취소","취소","연속",null,null,null,201901100042]
[95,"충북","직할","신제천S/S #4 M.Tr A","345kV 신제천S/S TCSC 설치공사(일반)","- STr용 23kV VCB 3000A 설치 1식 - STr용 23kV VCB 600A 설치 1식 - 23kV 3000A DS 설치 1식 - 23kV 600A DS 설치 1식 - 전력케이블 설치 1식 - 기타 부대공사","2019-03-18 09:00","2019-03-22 18:00","2019-03-25 09:00","2019-03-29 18:00","연속",null,null,null,201901090253]
[96,"충북","직할","곤지암신충주#2 T/L","345kV 신제천-신충주 등 2개T/L 스페이서 교체공사","345kV 신제천-신충주T/L, 곤지암-신충주T/L 스페이서 댐퍼 778개 교체","2019-03-17 08:00","2019-03-22 18:00","2019-03-18 08:00","2019-03-23 18:00","매일",null,null,null,201901100137]
[97,"충북","직할","신충주S/S #2 M.Tr A","345kV 신충주S/S #4M.Tr 증설공사","345kV M.Tr 설치 345kV GIS CB 설치 154kV GIS 4CCT 설치 기기기초 및 기타 부대공사","2019-03-18 16:00","2019-03-18 18:00","2019-03-29 15:00","2019-03-29 17:00","연속",null,null,null,201901100070]
[98,"충북","직할","신충주S/S #3 M.Tr A","345kV 신충주S/S #4M.Tr 증설공사","345kV M.Tr 설치 345kV GIS CB 설치 154kV GIS 4CCT 설치 기기기초 및 기타 부대공사","2019-03-20 10:00","2019-03-20 13:00","2019-03-27 09:00","2019-03-27 18:00","연속",null,null,null,201901100092]
[99,"충북","직할","곤지암신충주#1 T/L","345kV 신제천-신충주 등 2개T/L 스페이서 교체공사","345kV 신제천-신충주T/L, 곤지암-신충주T/L 스페이서 댐퍼 778개 교체","2019-03-11 08:00","2019-03-16 18:00","2019-03-12 08:00","2019-03-17 18:00","매일",null,null,null,201901100136]
[100,"충북","청주","청원신진천#1 T/L","345kV 신중부분기T/L 건설공사","○ 사업규모 : HSTACIR/AW 410(2B)×4C×3.408km ○ 지 지 물 : 설치8기, 철거 2기 ○ 기타 신중부변전소 건설후 환원시 T/L변경 복구","2019-03-11 07:00","2019-03-19 18:00","2019-03-11 07:00","2019-03-19 18:00","연속",null,null,null,201807110012]
[101,"대전충남","서산","신서산S/S 345kV #2 BUS","신서산S/S 345kV 7952 DS 가스누기 보수작업","신서산S/S 345kV 7952 DS 가스누기 보수작업","2019-03-04 09:00","2019-03-06 18:00","2019-03-04 09:00","2019-03-06 18:00","연속",null,null,null,201901100200]
[102,"대전충남","서산","신서산S/S 신서산-아산#1T/L CB (7972)","신서산S/S 345kV 7952 DS 가스누기 보수작업","신서산S/S 345kV 7952 DS 가스누기 보수작업","2019-03-04 09:00","2019-03-06 18:00","2019-03-04 09:00","2019-03-06 18:00","연속",null,null,null,201901100201]
[103,"대전충남","청양","청양S/S 345kV #71 BUS","청양S/S 345kV PT집합반 설치공사","청양S/S 345kV PT집합반 설치(71BUS)","2019-03-04 09:00","2019-03-04 18:00","2019-03-04 09:00","2019-03-04 18:00","당일",null,null,null,201901080081]
[104,"대전충남","세종","세종S/S #2M.Tr A","[변전]YPP제 보호계전기 성능개선 시행","○ YPP제 보호계전기 성능개선 시행 ○ 송운(계통)-1533(18.10.15) 관련","2019-03-04 09:30","2019-03-04 18:00","2019-03-04 09:30","2019-03-04 18:00","당일",null,null,null,201901080109]
[105,"대전충남","청양","청양S/S 345kV #76 BUS","청양S/S 345kV PT집합반 설치공사","청양S/S 345kV PT집합반 설치(76BUS)","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901080083]
[106,"대전충남","세종","세종S/S #3M.Tr A","[변전]YPP제 보호계전기 성능개선 시행","○ YPP제 보호계전기 성능개선 시행 ○ 송운(계통)-1533(18.10.15) 관련","2019-03-05 09:30","2019-03-05 18:00","2019-03-05 09:30","2019-03-05 18:00","당일",null,null,null,201901080110]
[107,"대전충남","청양","청양S/S 345kV #70 BUS","청양S/S 345kV PT집합반 설치공사","청양S/S 345kV PT집합반 설치(70BUS)","2019-03-06 08:00","2019-03-06 12:00","취소","취소","당일",null,null,null,201901080087]
[108,"대전충남","청양","청양S/S 345kV #75 BUS","청양S/S 345kV PT집합반 설치공사","청양S/S 345kV PT집합반 설치(75BUS)","2019-03-06 13:00","2019-03-06 18:00","취소","취소","당일",null,null,null,201901080090]
[109,"대전충남","청양","청양S/S #1 M.Tr 1차 CB (7671)","청양S/S 345kV 차단기 러버히터 설치","청양S/S 345kV 차단기 러버히터 설치(7671 CB)","2019-03-07 09:00","2019-03-07 18:00","2019-03-07 09:00","2019-03-07 18:00","당일",null,null,null,201901090032]
[110,"대전충남","세종","신옥천세종#1 T/L","[변전]YPP제 보호계전기 성능개선 시행","○ YPP제 보호계전기 성능개선 시행 ○ 송운(계통)-1533(18.10.15) 관련","2019-03-11 09:30","2019-03-11 18:00","2019-03-11 09:30","2019-03-11 18:00","당일",null,null,null,201901290116]
[111,"대전충남","서산","신당진개폐소태안화력#2 T/L","345kV 신당진개폐소-태안화력#2T/L 정밀점검","345kV 신당진개폐소-태안화력#2T/L 정밀점검 - No.0-1-127(128기)","2019-03-13 08:00","2019-03-20 18:00","2019-03-13 08:00","2019-03-20 18:00","매일",null,null,null,201901090201]
[112,"대전충남","세종","세종청원#1 T/L","[변전]YPP제 보호계전기 성능개선 시행","○ YPP제 보호계전기 성능개선 시행 ○ 송운(계통)-1533(18.10.15) 관련","2019-03-13 09:30","2019-03-13 18:00","2019-03-20 09:30","2019-03-20 18:00","당일",null,null,null,201901290117]
[113,"대전충남","청양","청양S/S 신계룡-청양T/L-청양-보령#1T/L CB (7100)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7100 CB","2019-03-18 09:00","2019-03-18 13:00","2019-03-18 09:00","2019-03-18 13:00","당일",null,null,null,201901070005]
[114,"대전충남","세종","신옥천세종#2 T/L","[변전]YPP제 보호계전기 성능개선 시행","○ YPP제 보호계전기 성능개선 시행 ○ 송운(계통)-1533(18.10.15) 관련","2019-03-12 09:30","2019-03-12 18:00","2019-03-12 09:30","2019-03-12 18:00","당일",null,null,null,201901080074]
[115,"대전충남","청양","청양S/S 신계룡-청양T/L CB (7171)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7171 CB","2019-03-18 13:00","2019-03-18 16:00","2019-03-18 13:00","2019-03-18 16:00","당일",null,null,null,201901070007]
[116,"대전충남","청양","청양S/S 청양-보령화력#1T/L CB (7172)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7172 CB","2019-03-18 16:00","2019-03-18 18:00","2019-03-18 16:00","2019-03-18 18:00","당일",null,null,null,201901070008]
[117,"대전충남","청양","청양S/S 청양-신보령T/L-청양보령복합TL CB (7200)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7200 CB","2019-03-19 09:00","2019-03-19 13:00","2019-03-19 09:00","2019-03-19 13:00","당일",null,null,null,201901070010]
[118,"대전충남","세종","세종청원#2 T/L","[변전]YPP제 보호계전기 성능개선 시행","○ YPP제 보호계전기 성능개선 시행 ○ 송운(계통)-1533(18.10.15) 관련","2019-03-14 09:30","2019-03-14 18:00","2019-03-21 09:30","2019-03-21 18:00","당일",null,null,null,201901080068]
[119,"대전충남","청양","청양S/S 청양-신보령T/L CB (7271)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7271 CB","2019-03-19 13:00","2019-03-19 16:00","2019-03-19 13:00","2019-03-19 16:00","당일",null,null,null,201901070011]
[120,"대전충남","청양","청양S/S 청양-보령복합T/L CB (7272)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7272 CB","2019-03-19 16:00","2019-03-19 18:00","2019-03-19 16:00","2019-03-19 18:00","당일",null,null,null,201901070013]
[121,"대전충남","서산","신당진개폐소북당진 T/L","345kV 신당진개폐소-태안화력#2T/L 정밀점검(4회선병가)","345kV 신당진개폐소-태안화력#2T/L 정밀점검 4회선 병가 - No.126,127(2기)","2019-03-20 08:00","2019-03-20 18:00","2019-03-20 08:00","2019-03-20 18:00","당일",null,null,null,201901090200]
[122,"대전충남","서산","신당진S/S #1 M.Tr A","19년 서산PO 변전협력회사 총액공사","신당진S/S 345kV #1M.Tr TAP상태 거래소 표기작업","2019-03-20 09:00","2019-03-20 18:00","2019-03-20 09:00","2019-03-20 18:00","당일",null,null,null,201901100072]
[123,"대전충남","아산","아산S/S #2 M.Tr","345kV #2M.Tr A상 불량부싱 교체 후 결선 조정","345kV #2M.Tr A상 불량부싱 교체 후 결선 조정","2019-03-20 09:00","2019-03-22 18:00","2019-03-20 09:00","2019-03-22 18:00","연속",null,null,null,201901110057]
[124,"대전충남","청양","청양S/S 청양신온양#1T/L-청양군산#2T/L CB (7300)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7300 CB","2019-03-20 09:00","2019-03-20 13:00","2019-03-20 09:00","2019-03-20 13:00","당일",null,null,null,201901070015]
[125,"대전충남","청양","청양S/S 청양-신온양#1T/L CB (7371)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7371 CB","2019-03-20 13:00","2019-03-20 16:00","2019-03-20 13:00","2019-03-20 16:00","당일",null,null,null,201901070016]
[126,"대전충남","청양","청양S/S 청양-군산#2T/L CB (7372)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7372 CB","2019-03-20 16:00","2019-03-20 18:00","2019-03-20 16:00","2019-03-20 18:00","당일",null,null,null,201901070017]
[127,"대전충남","서산","신당진S/S #2 M.Tr A","19년 서산PO 변전협력회사 총액공사","신당진S/S 345kV #2M.Tr TAP상태 거래소 표기작업","2019-03-21 09:00","2019-03-21 18:00","2019-03-21 09:00","2019-03-21 18:00","당일",null,null,null,201901100073]
[128,"대전충남","청양","청양S/S 신옥천-청양T/L-청양-군산#1T/L CB (7400)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7400 CB","2019-03-21 09:00","2019-03-21 13:00","2019-03-21 09:00","2019-03-21 13:00","당일",null,null,null,201901070018]
[129,"대전충남","청양","청양S/S 신옥천-청양T/L CB (7471)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7471 CB","2019-03-21 13:00","2019-03-21 16:00","2019-03-21 13:00","2019-03-21 16:00","당일",null,null,null,201901070019]
[130,"대전충남","청양","청양S/S 청양-군산#1T/L CB (7472)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7472 CB","2019-03-21 16:00","2019-03-21 18:00","2019-03-21 16:00","2019-03-21 18:00","당일",null,null,null,201901070021]
[131,"대전충남","서산","신당진개폐소태안화력#1 T/L","345kV 신당진개폐소-태안화력#1T/L 정밀점검","345kV 신당진개폐소-태안화력#1T/L 정밀점검 - No.0-1-127(128기)","2019-03-22 08:00","2019-03-29 18:00","2019-03-22 08:00","2019-03-29 18:00","매일",null,null,null,201901090182]
[132,"대전충남","청양","청양S/S 청양신온양#2T/L-TIE CB (7500)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7500 CB","2019-03-22 09:00","2019-03-22 13:00","2019-03-22 09:00","2019-03-22 13:00","당일",null,null,null,201901070023]
[133,"대전충남","청양","청양S/S 청양-신온양#2T/L CB (7571)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7571 CB","2019-03-22 13:00","2019-03-22 16:00","2019-03-22 13:00","2019-03-22 16:00","당일",null,null,null,201901070024]
[134,"대전충남","청양","청양S/S 청양-보령화력#2T/L CB (7672)","청양S/S 345kV 차단기 조작시험","청양S/S 345kV 차단기 조작시험 - 개소 : 청양S/S 7672 CB","2019-03-22 16:00","2019-03-22 18:00","2019-03-22 16:00","2019-03-22 18:00","당일",null,null,null,201901070025]
[135,"대전충남","청양","보령T/P 70-71-0 SEC CB (70-71-0)","보령T/P 70-71-0 SEC AC,DC전원 교체","보령T/P 70-71-0 SEC AC,DC전원 교체(경로 변경)","2019-03-25 09:00","2019-03-25 18:00","2019-03-25 09:00","2019-03-25 18:00","당일",null,null,null,201901090022]
[136,"대전충남","청양","보령T/P 75-76-0 SEC CB (75-76-0)","보령T/P 75-76-0 SEC AC,DC전원 교체","보령T/P 75-76-0 SEC AC,DC전원 교체(경로 변경)","2019-03-26 09:00","2019-03-26 18:00","2019-03-26 09:00","2019-03-26 18:00","당일",null,null,null,201901090024]
[137,"대전충남","청양","청양S/S #1 M.Tr A","2019년 청양S/S #1M.Tr 및 OLTC 정밀점검 공사","#1M.Tr 및 OLTC 정밀점검","2019-03-26 09:00","2019-04-12 18:00","2019-03-26 09:00","2019-04-12 18:00","연속",null,null,null,201901030151]
[138,"대전충남","서산","신당진개폐소현대제철 T/L","345kV 신당진개폐소-태안화력#1T/L 정밀점검(4회선병가)","345kV 신당진개폐소-태안화력#1T/L 정밀점검 4회선 병가 - No.126,127(2기)","2019-03-29 08:00","2019-03-29 18:00","2019-03-29 08:00","2019-03-29 18:00","당일",null,null,null,201901090204]
[139,"전북","군산","청양군산#2 T/L","청양-군산 2TL 송전선로 보호반 성능개선","청양-군산 2TL 송전선로 보호반 성능개선","2019-03-19 10:00","2019-03-19 18:00","2019-03-11 09:00","2019-04-12 18:00","연속",null,null,null,201812310040]
[140,"전북","군산","군산신김제#1 T/L","군산-신김제#1T/L 정밀점검공사","송전선로 정밀점검 : 137기","2019-03-04 08:00","2019-03-08 18:00","2019-03-04 08:00","2019-03-08 18:00","당일",null,null,null,201901070056]
[141,"전북","군산","군산S/S #4 M.Tr A","군산S/S #4 M.Tr A","군산S/S 345kV 모자익 대체공사","2019-03-04 09:00","2019-03-08 18:00","2019-03-04 09:00","2019-03-08 18:00","당일",null,null,null,201811300157]
[142,"전북","군산","청양군산#1 T/L","청양-군산 1TL 송전선로 보호반 성능개선","청양-군산 1TL 송전선로 보호반 성능개선","2019-03-18 10:00","2019-03-18 18:00","2019-03-25 10:00","2019-03-25 18:00","매일",null,null,null,201812310039]
[143,"전북","군산","군산신김제#2 T/L","군산-신김제#2T/L 정밀점검공사","송전선로 정밀점검 : 137기","2019-03-11 08:00","2019-03-15 18:00","2019-03-11 08:00","2019-03-15 18:00","매일",null,null,null,201901070058]
[144,"전북","군산","새만금S/S #3 M.Tr A","관내주변압기 점검공사","1. 주변압기 물청소 및 보통점검 2. 345, 154kV GIS 초기점검 3 23kV GIS 조작시험","2019-03-07 09:30","2019-03-08 18:00","2019-03-07 09:30","2019-03-08 18:00","당일",null,null,null,201901180111]
[145,"전북","군산","새만금S/S #2 M.Tr A","관내주변압기 점검공사","1. 주변압기 물청소 및 보통점검 2. 345, 154kV GIS 초기점검 3 23kV GIS 조작시험","2019-03-05 09:30","2019-03-06 18:00","2019-03-05 09:30","2019-03-06 18:00","당일",null,null,null,201901180110]
[146,"전북","김제","신김제S/S #3 M.Tr A","신김제 #3 M.Tr 보호배전반 성능개선","신김제 #3 M.Tr 보호배전반 성능개선","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201812310036]
[147,"전북","직할","북경남무주양수 T/L","345kV 북경남-무주양수T/L 피뢰기 설치공사","345kV 북경남-무주양수T/L 피뢰기 설치공사","2019-03-04 07:30","2019-03-19 18:00","2019-03-04 07:30","2019-03-19 18:00","연속",null,null,null,201901070057]
[148,"전북","직할","신남원광양#2 T/L","345kV 신남원-광양T/L 안전이격 확보공사","가. 철탑철거 : 2기 [No.214(T-14), No.216(F-21)] 나. 철탑설치 : 2기 [No.214(C2-26), No.216(SF-36)] 다. 전력선 교체 : 1.790km [ACSR 480㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기 (No.216","2019-03-26 08:00","2019-04-05 18:00","2019-03-31 08:00","2019-04-12 18:00","연속",null,null,null,201810310060]
[149,"전북","직할","신남원광양#2 T/L","345kV 신남원-광양T/L 안전이격 확보공사","가. 철탑철거 : 2기 [No.214(T-14), No.216(F-21)] 나. 철탑설치 : 2기 [No.214(C2-26), No.216(SF-36)] 다. 전력선 교체 : 1.790km [ACSR 480㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기 (No.216","2019-03-03 08:00","2019-03-07 18:00","2019-03-03 08:00","2019-03-07 18:00","매일",null,null,null,201810310059]
[150,"광주전남","강진","신강진S/S 345kV #1 BUS","신강진S/S 345kV 취약설비 GIS화 공사","- 345kV 옥외철구 -> GIS화","2019-03-01 09:00","2019-03-01 18:00","2019-03-01 09:00","2019-03-01 18:00","당일",null,null,null,201901170087]
[151,"광주전남","강진","신강진S/S #2 M.Tr A","신강진S/S 345kV 취약설비 GIS화 공사","- 345kV 옥외철구 -> GIS화","2019-03-01 09:00","2019-06-28 18:00","2019-03-01 09:00","2019-06-28 18:00","연속",null,null,null,201901170086]
[152,"광주전남","강진","신강진S/S 345kV #2 BUS","신강진S/S 345kV 취약설비 GIS화 공사","- 345kV 옥외철구 -> GIS화","2019-03-02 09:00","2019-03-02 18:00","2019-03-02 09:00","2019-03-02 18:00","당일",null,null,null,201901170088]
[153,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S 345kV #1 M.Tr 부싱 절연열화 측정","- 신강진S/S 345kV #1 M.Tr 부싱 절연열화 측정","2019-03-27 09:00","2019-03-27 18:00","2019-03-27 09:00","2019-03-27 18:00","당일",null,null,null,201901080072]
[154,"광주전남","목포","한빛1NP한빛2NP #1T/L","한빛2발 362kV GIS 대체공사","○ 362kV GIS(4000A,40kA) X 9CCT 철거 ○ 362kV GIS(6300A,63kA) X 9CCT 설치 ○ 기타부대공사 X 1식","2019-03-12 09:00","2019-06-04 18:00","2019-03-12 09:00","2019-06-04 18:00","연속",null,null,null,201901180010]
[155,"광주전남","목포","신남원한빛NP#1 T/L","한빛2발 362kV GIS 대체공사","○ 362kV GIS(4000A,40kA) X 9CCT 철거 ○ 362kV GIS(6300A,63kA) X 9CCT 설치 ○ 기타부대공사 X 1식","2019-03-12 09:00","2019-05-16 18:00","2019-03-12 09:00","2019-05-16 18:00","연속",null,null,null,201901180009]
[156,"광주전남","순천","광양S/S #1 M.Tr A","‘18-19년도 순천전력지사 변전협력회사 총액공사","7100, 7172 GIS 초기, LA 하자 , 부싱절연유 채유","2019-03-25 09:00","2019-03-26 18:00","2019-03-25 09:00","2019-03-26 18:00","연속",null,null,null,201901140151]
[157,"광주전남","순천","광양S/S #2 M.Tr A","‘18-19년도 순천전력지사 변전협력회사 총액공사","7400, 7472 GIS 초기, LA 하자 , 부싱절연유 채유","2019-03-27 09:00","2019-03-28 18:00","2019-03-27 09:00","2019-03-28 18:00","연속",null,null,null,201901140152]
[158,"광주전남","순천","광양S/S 신강진-광양#1T/L-TIE GIS","광양 362kV GIS 용량대체 공사","신강진 광양 #1T/L BAY GIS 용량대체 - 50kA →63kA (7871,7800CB)","2019-03-01 09:00","2019-06-28 18:00","취소","취소","연속",null,null,null,201901150039]
[159,"광주전남","순천","신강진광양#1 T/L","광양 362kV GIS 용량대체 공사","신강진 광양 #1T/L BAY GIS 용량대체 - 50kA →63kA (7871,7800CB)","2019-03-01 09:00","2019-06-28 18:00","2019-03-01 09:00","2019-06-28 18:00","연속",null,null,null,201901150038]
[160,"광주전남","순천","광양여수TP T/L","‘18-19년도 순천전력지사 변전협력회사 총액공사","여수화력 7171 GIS, LA,CVT(A,C)/CVT(B)대체,광양 7471 GIS초기, LA,CVT 하자","2019-03-21 09:00","2019-03-22 18:00","2019-03-21 09:00","2019-03-22 18:00","연속",null,null,null,201901140160]
[161,"광주전남","순천","율촌CC 여수TP T/L","‘18-19년도 순천전력지사 변전협력회사 총액공사","7271 GIS 보통, LA 보통, CVT 하자","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901140157]
[162,"광주전남","순천","여수T/P #1 Tie-Tr","‘18-19년도 순천전력지사 변전협력회사 총액공사","#1M.Tr 보통,7172,7100 GIS 보통, 6144 GIS 보통, 3차 VCB, 1,2,3차 LA 보통, 3차 GPT 보통","2019-03-11 09:00","2019-03-15 18:00","2019-02-25 09:00","2019-02-28 18:00","당일",null,null,null,201901140164]
[163,"광주전남","순천","광양율촌CC T/L","‘18-19년도 순천전력지사 변전협력회사 총액공사","율촌CC 7171, 7100 GIS 보통","2019-03-18 09:00","2019-03-18 18:00","2019-03-18 09:00","2019-03-18 18:00","당일",null,null,null,201901140162]
[164,"대구","경산","신경산S/S #3 M.Tr A","신경산S/S #3M.Tr 휴전","#2BUS 철거, 설치 안전이격","2019-03-10 09:00","2019-03-10 18:00","2019-03-06 09:00","2019-03-07 18:00","당일",null,null,null,201901150026]
[165,"대구","경산","울주신경산#1 T/L","신경산S/S 울주-신경산#1T/L 휴전","○ 울주-신경산#1T/L 관련 CB, DS, PT, LA 철거, 설치 ○ 자체시험 ○ 준공시험 ○ 사용전검사, 실부하 가압","2019-03-05 09:00","2019-04-16 18:00","2019-03-05 09:00","2019-04-16 18:00","당일",null,null,null,201901070131]
[166,"대구","경산","신경산S/S 345kV #2 BUS","신경산S/S 345kV #2BUS 휴전","○ 모선 및 CB, DS 철거, 설치 (#2BUS, 7402DS, 7400CB)","2019-03-05 09:00","2019-03-12 09:00","2019-03-05 09:00","2019-03-12 09:00","당일",null,null,null,201901070136]
[167,"대구","경산","신경산대구#2 T/L","신경산S/S 신경산-대구#2T/L 휴전","#2BUS 무부하가압 (모선 접속개소 건전성 확인)","2019-03-11 18:00","2019-03-12 09:00","2019-03-11 18:00","2019-03-12 09:00","연속",null,null,null,201901150027]
[168,"대구","경산","신경산S/S 345kV #1 BUS","신경산S/S 345kV #1BUS 휴전","○ 모선 및 CB, DS 철거, 설치 (#1BUS, 7451DS, 7471CB)","2019-03-12 09:00","2019-03-19 09:00","2019-03-12 09:00","2019-03-19 09:00","연속",null,null,null,201901070133]
[169,"대구","경산","울주신경산#2 T/L","신경산S/S 울주-신경산#2T/L 휴전","#1BUS 철거, 설치 안전이격","2019-03-17 09:00","2019-03-17 18:00","2019-03-13 09:00","2019-03-14 18:00","연속",null,null,null,201901150029]
[170,"대구","경산","신경산S/S 345kV #2 BUS","신경산S/S 345kV #2BUS 휴전","7400CB 연결용 단상 모선 설치(3상)","2019-03-19 09:00","2019-03-19 18:00","2019-03-19 09:00","2019-03-19 18:00","당일",null,null,null,201901150032]
[171,"대구","경산","신경산대구#2 T/L","신경산S/S 신경산-대구#2T/L 휴전","#1BUS 무부하 가압 (모선 접속개소 건전성 확인)","2019-03-18 18:00","2019-03-19 09:00","2019-03-18 18:00","2019-03-19 09:00","연속",null,null,null,201901150030]
[172,"대구","달성","고령S/S 345kV #1 BUS","345kV 고령S/S #1M.Tr 증설공사","345kV 고령S/S #1M.Tr 증설공사","2019-03-04 09:00","2019-03-14 18:00","취소","취소","연속",null,null,null,201901100207]
[173,"대구","달성","고령S/S 345kV #2 BUS","345kV 고령S/S #1M.Tr 증설공사","345kV 고령S/S #1M.Tr 증설공사","2019-03-15 09:00","2019-03-25 18:00","취소","취소","연속",null,null,null,201901100208]
[174,"대구","달성","서대구고령#2 T/L","345kV 고령S/S #1M.Tr 증설공사","345kV 고령S/S #1M.Tr 증설공사","2019-03-13 18:00","2019-03-14 18:00","취소","취소","연속",null,null,null,201901100205]
[175,"대구","달성","서대구고령#2 T/L","345kV 고령S/S #1M.Tr 증설공사","345kV 고령S/S #1M.Tr 증설공사","2019-03-24 18:00","2019-03-25 18:00","취소","취소","연속",null,null,null,201901100206]
[176,"대구","칠곡","북경남서대구#2 T/L","가공송전선로 순시점검 위탁공사","345kV 북경남-서대구#2T/L 정밀점검","2019-03-11 09:00","2019-03-14 18:00","2019-03-25 09:00","2019-03-28 18:00","연속",null,null,null,201901070215]
[177,"대구","칠곡","서대구고령#2 T/L","154kV 서대구-남구미#1T/L 피뢰기 설치공사","154kV 서대구-남구미#1T/L 피뢰기 설치공사 안전확보","2019-03-05 07:30","2019-03-05 18:00","2019-03-04 07:30","2019-03-04 18:00","연속",null,null,null,201901070311]
[178,"대구","칠곡","북경남서대구#1 T/L","가공송전선로 순시점검 위탁공사","345kV 북경남-서대구#1T/L 정밀점검","2019-03-04 09:00","2019-03-07 18:00","2019-03-18 09:00","2019-03-21 18:00","연속",null,null,null,201901070213]
[179,"대구","칠곡","서대구S/S TIE-북경남-서대구#2T/L-TIE CB (7300)","서대구S/S 북경남-서대구#2T/L TIE 7300 GCB 장기미동작점검","서대구S/S 북경남-서대구#2T/L TIE 7300 GCB 장기미동작점검","2019-03-28 09:30","2019-03-28 12:00","2019-03-28 09:30","2019-03-28 12:00","연속",null,null,null,201901030179]
[180,"대구","칠곡","서대구S/S 북경남-서대구#2T/L CB (7372)","서대구S/S 북경남-서대구#2T/L 7372 GCB 장기미동작점검","서대구S/S 북경남-서대구#2T/L 7372 GCB 장기미동작점검","2019-03-28 13:00","2019-03-28 16:00","2019-03-28 13:00","2019-03-28 16:00","연속",null,null,null,201901030180]
[181,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구 T/L 안전이격확보공사","345kV 신포항-북대구T/L 안전이격확보공사 ○ 임시선로 구성","2019-03-04 08:00","2019-03-12 18:00","2019-03-18 08:00","2019-03-24 18:00","연속",null,null,null,201901070039]
[182,"대구","포항","신포항신영일 T/L","154kV 영일-양북 등 19개 T/L 피뢰기설치공사","154kV 신포항-영일#1 T/L 피뢰기설치공사에 따른 작업자 안전확보 휴전","2019-03-08 08:00","2019-03-08 18:00","2019-03-08 08:00","2019-03-08 18:00","당일",null,null,null,201812270173]
[183,"대구","포항","선산신포항 T/L","345kV 신포항-북대구 T/L 안전이격확보공사","345kV 신포항-북대구T/L 안전이격확보공사 ○ 임시선로 구성","2019-03-13 08:00","2019-03-21 18:00","2019-03-25 08:00","2019-03-29 18:00","당일",null,null,null,201901070036]
[184,"대구","포항","월성2N/P 70-71-0 SEC CB (70-71-0)","월성2N/P 70-71-0 SEC GIS 보통점검","월성2N/P 70-71-0 SEC GIS 보통점검","2019-03-12 10:00","2019-03-12 18:00","2019-03-12 10:00","2019-03-12 18:00","연속",null,null,null,201901070453]
[185,"대구","포항","월성2N/P 75-76-0 SEC CB (75-76-0)","월성2N/P 75-76-0 SEC GIS 보통점검","월성2N/P 75-76-0 SEC GIS 보통점검","2019-03-13 10:00","2019-03-13 18:00","2019-03-11 10:00","2019-03-11 18:00","연속",null,null,null,201901070454]
[186,"대구","포항","울주월성NP#2 T/L","2019년도 가공송전선로 순시점검 위탁공사","154kV 입실-양북 T/L 정밀점검 안전확보차","2019-03-25 08:00","2019-03-26 18:00","2019-03-25 08:00","2019-03-26 18:00","당일",null,null,null,201901070004]
[187,"경북","구미","북대구선산 T/L","가보제 송전선로보호반 로직개선(선산S/S)","-수전단 재폐로 조건 로직 개선","2019-03-06 09:00","2019-03-06 18:00","2019-03-06 09:00","2019-03-06 18:00","연속",null,null,null,201901080104]
[188,"경북","구미","서대구선산#2 T/L","2018-19년도 구미전력지사 가공송전협력회사 총액공사","ㅇ 항공장애표시구 설치 : 8경간, 23개","2019-03-30 07:00","2019-03-31 18:00","2019-03-30 07:00","2019-03-31 18:00","연속",null,null,null,201901080128]
[189,"경북","구미","서대구선산#1 T/L","2018-19년도 구미전력지사 가공송전협력회사 총액공사","ㅇ 항공장애표시구 설치 : 8경간, 23개","2019-03-28 07:00","2019-03-29 18:00","2019-03-28 07:00","2019-03-29 18:00","연속",null,null,null,201901080127]
[190,"부산울산","동부산","고리N/P S/Y 76-77-0 BUS SEC CB (76-77-0)","고리NP S/Y 362kV GIS 보통점검","고리NP S/Y 362kV GIS 보통점검(76-77-0)","2019-03-21 14:00","2019-03-22 18:00","2019-03-21 14:00","2019-03-22 18:00","연속",null,null,null,201901210002]
[191,"부산울산","동부산","고리N/P S/Y 71-72-0 BUS SEC CB (71-72-0)","고리NP S/Y 362kV GIS 보통점검","고리NP S/Y 362kV GIS 보통점검(71-72-0)","2019-03-20 09:30","2019-03-21 14:00","2019-03-20 09:30","2019-03-21 14:00","연속",null,null,null,201901210001]
[192,"부산울산","동부산","신양산북부산#2 T/L","345kV 신양산-북부산 등 2개T/L 안전이격확보공사","철탑설치 : 42호(신설 4회선), 철탑철거 : 42호(기설) 전선교체 : 41-43호","2019-03-25 09:00","2019-03-27 18:00","취소","취소","연속",null,null,null,201901110050]
[193,"부산울산","동부산","신양산북부산#1 T/L","신양산S/S 345kV CVT 초기점검","1.신양산S/S 345kV CVT 초기점검(신양산-북부산#1T/L) 2.신양산S/S 362kV 7471,7400GIS 조작시험","2019-03-28 09:30","2019-03-28 17:00","취소","취소","당일",null,null,null,201901110318]
[194,"부산울산","동부산","신양산신대연#2 T/L","154㎸ 신양산-좌동T/L OPGW 증설공사","154㎸ 신양산-좌동#1T/L OPGW 5.031㎞(120SQ/48C) 증설, 기타 부대설비 1식","2019-03-01 07:00","2019-03-05 18:00","2019-03-01 07:00","2019-03-05 18:00","당일",null,null,null,201901040162]
[195,"부산울산","동부산","신양산S/S #1 M.Tr A","신양산S/S 362kV GIS 보통점검","1.신양산S/S 362kV 7100,7172GIS 보통점검(#1M.Tr) 2.170kV 6144GCB 조작시험 3.#1,2Sh.R 하자점검 4. 23kV 4179VCB 조작시험 5. 23kV 417-1,2,3VCB 보통점검 6. M.Tr 1,2차 부싱절연유 채유","2019-03-18 09:30","2019-03-19 17:00","2019-03-18 09:30","2019-03-19 17:00","당일",null,null,null,201901110304]
[196,"부산울산","북부산","북부산S/S #2 M.Tr A","북부산S/S 345kV #2M.Tr YPP 보호반 성능개선 공사","북부산S/S 345kV #2M.Tr YPP 보호반 성능개선 공사","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901030086]
[197,"부산울산","북부산","북부산S/S #3 M.Tr A","북부산S/S 345kV #3M.Tr 정밀점검 공사","북부산S/S 345kV #3M.Tr 정밀점검 공사","2019-03-28 09:00","2019-04-13 18:00","취소","취소","당일",null,null,null,201901100145]
[198,"부산울산","서부산","서부산S/S #2 M.Tr A","서부산S/S #2M.Tr 보통점검","서부산S/S #2M.Tr 보통점검","2019-03-26 10:00","2019-03-28 18:00","2019-03-26 10:00","2019-03-28 18:00","당일",null,null,null,201901080017]
[199,"부산울산","서부산","서부산S/S #1 M.Tr A","서부산S/S #1M.Tr 보통점검","서부산S/S #1M.Tr 보통점검","2019-03-19 10:00","2019-03-21 18:00","2019-03-19 10:00","2019-03-21 18:00","당일",null,null,null,201901080016]
[200,"부산울산","울산","신울산고리NP#1 T/L","18-19년 동부산전력지사 송전정비 협력회사 총액공사","1. 만곡개소 정비 : 34호, 2. 노후 금구류 교체 : 15, 15-1, 16호, 3. 피뢰기 설치 : 5-1, 50호","2019-03-18 08:00","2019-03-23 18:00","2019-03-11 08:00","2019-03-16 18:00","연속",null,null,null,201901080165]
[201,"부산울산","울산","신울산고리NP#2 T/L","18-19년 동부산전력지사 송전정비 협력회사 총액공사","노후 금구류 교체 : 15, 15-1, 16호","2019-03-25 08:00","2019-03-26 18:00","2019-04-04 08:00","2019-04-05 18:00","연속",null,null,null,201901080166]
[202,"부산울산","울산","울산C/C #2 M.Tr A","2018~19년 변전협력회사 총액공사","1. ERA폴리머타입 교체관련 애관길이 측정 2. 1차GIS 보통점검(박범용) 3. 2차GIS 차단기 조작시험(안정모)","2019-03-23 09:00","2019-03-24 18:00","2019-03-23 09:00","2019-03-24 18:00","연속",null,null,null,201901100181]
[203,"부산울산","울산","울산C/C #3 M.Tr A","2018~19년 변전협력회사 총액공사","1. ERA폴리머타입 교체관련 애관길이 측정 2. 1,2차GIS 보통점검(강명주)","2019-03-30 09:00","2019-03-31 18:00","2019-03-30 09:00","2019-03-31 18:00","연속",null,null,null,201901100182]
[204,"부산울산","울산","울산C/C 345kV #2 BUS","2018~19년 변전협력회사 총액공사","1. 모선보호반 대체","2019-03-25 09:00","2019-03-29 18:00","2019-03-25 09:00","2019-03-29 18:00","연속",null,null,null,201901100185]
[205,"부산울산","울산","울산C/C 345kV #1 BUS","2018~19년 변전협력회사 총액공사","1. 모선보호반 대체","2019-03-18 09:00","2019-03-22 18:00","2019-03-18 09:00","2019-03-22 18:00","연속",null,null,null,201901100180]
[206,"부산울산","직할","신대연S/S #2M.Tr A","신대연S/S 362kV GIS 정밀점검공사(7272) 정밀점검관련 휴전","신대연S/S 362kV GIS 정밀점검공사(7272) 정밀점검관련 휴전(시험가압)","2019-03-28 17:00","2019-03-28 18:00","2019-03-28 17:00","2019-03-28 18:00","당일",null,null,null,201901130009]
[207,"부산울산","직할","신양산신대연#2 T/L","신대연S/S 362kV GIS 정밀점검공사(7272) 시험가압선로","신대연S/S 362kV GIS 정밀점검공사(7272) 시험가압선로","2019-03-28 17:00","2019-03-28 18:00","2019-03-28 17:00","2019-03-28 18:00","연속",null,null,null,201901130008]
[208,"부산울산","직할","신양산신대연#1 T/L","신대연S/S 362kV GIS 정밀점검공사(7172) 시험가압선로","신대연S/S 362kV GIS 정밀점검공사(7172) 시험가압선로","2019-03-21 17:00","2019-03-21 18:00","2019-03-21 17:00","2019-03-21 18:00","당일",null,null,null,201901130006]
[209,"부산울산","직할","신대연S/S #1M.Tr A","신대연S/S 362kV GIS 정밀점검공사(7172) 정밀점검관련 휴전","신대연S/S 362kV GIS 정밀점검공사(7172) 정밀점검관련 휴전(시험가압)","2019-03-21 17:00","2019-03-21 18:00","2019-03-21 17:00","2019-03-21 18:00","당일",null,null,null,201901140035]
[210,"부산울산","직할","신양산신대연#1 T/L","신대연S/S 362kV GIS 정밀점검공사(7079) 시험가압선로","신대연S/S 362kV GIS 정밀점검공사(7079) 시험가압선로","2019-03-15 17:00","2019-03-15 18:00","2019-03-15 17:00","2019-03-15 18:00","연속",null,null,null,201901130011]
[211,"부산울산","직할","신대연S/S 345kV #1 BUS","신대연S/S 362kV GIS 정밀점검공사(7079) 정밀점검관련 휴전","신대연S/S 362kV GIS 정밀점검공사(7079) 정밀점검관련 휴전(시험가압)","2019-03-15 17:00","2019-03-15 18:00","2019-03-15 17:00","2019-03-15 18:00","당일",null,null,null,201901130012]
[212,"부산울산","직할","신대연S/S #1Sh.R CB","신대연S/S 362kV GIS 정밀점검공사(7079)","신대연S/S 362kV GIS 정밀점검공사(7079)","2019-03-12 09:00","2019-03-15 18:00","2019-03-12 09:00","2019-03-15 18:00","연속",null,null,null,201901130010]
[213,"부산울산","직할","신양산신대연#1 T/L","345kV 신양산-신대연#1T/L 이음,진동 발생 접속함 재접속 공사","345kV 신양산-신대연#1T/L EB-G(신양산S/S측) A상 해체 후 재접속","2019-03-06 09:00","2019-03-09 18:00","2019-03-06 09:00","2019-03-09 18:00","연속",null,null,null,201901110200]
[214,"부산울산","직할","신대연S/S #1M.Tr 1차 CB","신대연S/S 362kV GIS 정밀점검공사(7172)","신대연S/S 362kV GIS 정밀점검공사(7172)","2019-03-18 09:00","2019-03-21 18:00","2019-03-18 09:00","2019-03-21 18:00","연속"]
[215,"부산울산","직할","신대연S/S #2M.Tr 1차 CB","신대연S/S 362kV GIS 정밀점검공사(7272)","신대연S/S 362kV GIS 정밀점검공사(7272)","2019-03-25 09:00","2019-03-28 18:00","2019-03-25 09:00","2019-03-28 18:00","연속"]
[216,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산T/L 78호 지장송전선로 이설공사","345kV 신김해-북부산T/L 77~81호 간 지장이설공사[가탑 1기, 계탑 1기]","2019-03-22 08:00","2019-03-27 18:00","2019-03-22 08:00","2019-03-27 18:00","연속",null,null,null,201901030020]
[217,"경남","직할","신김해신녹산#2 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","345kV 신김해-신녹산#2T/L 정밀점검(1호~22호)","2019-03-17 09:00","2019-03-20 18:00","2019-03-18 09:00","2019-03-21 18:00","매일",null,null,null,201812060082]
[218,"경남","직할","신마산신김해#1 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신김해-진영#1T/L 피뢰기 설치관련 안전이격 확보","2019-03-16 07:00","2019-03-16 18:00","2019-03-16 07:00","2019-03-16 18:00","당일",null,null,null,201812280022]
[219,"경남","직할","신김해창원#1 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신김해-진영#1T/L 피뢰기 설치관련 안전이격 확보","2019-03-03 07:00","2019-03-03 18:00","2019-03-03 07:00","2019-03-03 18:00","당일",null,null,null,201812280025]
[220,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산T/L 78호 지장송전선로 이설공사","345kV 신김해-북부산T/L 77~81호 간 지장이설공사[가탑 1기, 계탑 1기]","2019-03-28 08:00","2019-04-01 18:00","2019-03-28 08:00","2019-04-01 18:00","연속",null,null,null,201901180085]
[221,"경남","직할","창원S/S #2 M.Tr A","창원S/S #2M.Tr 초기점검","창원S/S #2M.Tr 초기점검 (병행) 창원S/S #2M.Tr 1,2,3차 CB / #2S.Tr 초기점검","2019-03-13 09:30","2019-03-15 17:30","2019-03-13 09:30","2019-03-15 17:30","연속",null,null,null,201812310103]
[222,"경남","직할","신김해창원#2 T/L","신김해,창원S/S 신김해-창원#2T/L 87,21 Ry 성능개선","신김해,창원S/S 신김해-창원#2T/L 87,21 Ry 성능개선 (제작사 입회)","2019-03-15 09:30","2019-03-15 13:30","2019-03-15 09:30","2019-03-15 17:30","당일",null,null,null,201901220075]
[223,"경남","직할","창원S/S #1 M.Tr A","창원S/S #1M.Tr 초기점검","창원S/S #1M.Tr 초기점검 (병행) 창원S/S #1M.Tr 1,2,3차 CB / #1S.Tr 초기점검","2019-03-06 09:30","2019-03-08 17:30","2019-03-06 09:30","2019-03-08 17:30","연속",null,null,null,201812310102]
[224,"경남","진주","고령의령#2 T/L","345kV 고령의령#2 T/L PT 보통점검","345kV 고령의령#2 T/L PT 보통점검 7571CB 보통점검","2019-03-08 09:30","2019-03-08 18:00","취소","취소","연속",null,null,null,201901030003]
[225,"경남","진주","고령의령#1 T/L","345kV 고령의령#1 T/L 송전선로 보호반 대체","345kV 고령의령#1 T/L 송전선로 보호반 대체 병행) 7671CB 보통점검 PT,LA 보통점검","2019-03-18 09:00","2019-03-22 18:00","취소","취소","연속",null,null,null,201901030009,"O"]
[226,"경남","통영","(신)삼천포TP G3호기 1차 GIS(7371)","삼천포,신고성S/S 용량부족차단기 대체공사","삼천포화력 3호기 인출변경 관련 3호기측 PT, LA, 전력케이블 시험 가압","2019-03-16 10:00","2019-03-17 10:00","2019-03-16 10:00","2019-03-17 10:00","연속",null,null,null,201901180056]
[227,"경남","통영","(신)삼천포TP 345kV #70 BUS CB","삼천포,신고성S/S 용량부족차단기 대체공사","삼천포화력 3호기 인출변경 관련 3호기측 PT, LA, 전력케이블 시험 가압","2019-03-16 10:00","2019-03-17 10:00","2019-03-16 10:00","2019-03-17 10:00","연속",null,null,null,201901180052]
[228,"경남","통영","신고성S/S 345kV #1 BUS","삼천포,신고성S/S 용량부족차단기 대체공사","신고성S/S #1M.Tr 1차 인출변경 작업에 따른 동일 BAY 신고성-삼천포화력#2T/L 양모선운전을 위한 모선보호구간 확장 작업","2019-03-09 13:00","2019-03-09 18:00","2019-03-09 13:00","2019-03-09 18:00","연속",null,null,null,201812130040]
[229,"경남","통영","신고성S/S #2 M.Tr A","삼천포,신고성S/S 용량부족차단기 대체공사","신고성S/S #2M.Tr 1차 인출변경(구GIS-&gt신GIS)","2019-03-09 09:00","2019-03-30 18:00","2019-03-09 09:00","2019-03-30 18:00","연속",null,null,null,201812210002]
[229,"인천",null,"신인천복합#3,4GT 주변압기 CB(7672,7600)","계획예방정비","계획예방정비","2019-03-11 09:00","2019-04-12 18:00","2019-03-11 09:00","2019-04-12 18:00","연속"]
[229,"부산울산",null,"부산복합#7,8GT 주변압기 CB(7572,7500)","계획예방정비","계획예방정비","2019-03-18 09:00","2019-05-24 18:00","2019-03-18 09:00","2019-05-24 18:00","연속"]
[230,"경북",null,"청송양수1호기 주변압기 CB(7100,7172)","계획예방정비","계획예방정비","2019-03-07 09:00","2019-03-26 18:00","2019-03-07 09:00","2019-03-26 18:00","연속"]

{"sheet":"154송부","index":2,"n_rows":466,"n_cols":16,"rows_kept":466,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
["2019년도 3월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","천호구의#1 T/L","19년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2019-03-28 13:00","2019-03-28 15:00","2019-03-28 13:00","2019-03-28 15:00","당일",null,null,null,201901140125]
[2,"서울","성동","마장용두 T/L","19년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2019-03-13 13:00","2019-03-13 15:00","2019-03-13 13:00","2019-03-13 15:00","당일",null,null,null,201901140127]
[3,"서울","성동","성동S/S 154kV #66 BUS","19년 성동P/O 변전협력회사 총액공사","154kV PT배전반 교체","2019-03-14 09:30","2019-03-16 18:00","2019-03-14 09:30","2019-03-16 18:00","연속",null,null,null,201901150242]
[4,"서울","성동","성동S/S 154kV #65 BUS","19년 성동P/O 변전협력회사 총액공사","154kV PT배전반 교체","2019-03-07 11:00","2019-03-09 18:00","2019-03-07 11:00","2019-03-09 18:00","연속",null,null,null,201901150240]
[5,"서울","성동","성동S/S 154kV #61 BUS","19년 성동P/O 변전협력회사 총액공사","154kV PT배전반 교체","2019-03-11 09:30","2019-03-13 18:00","2019-03-11 09:30","2019-03-13 18:00","연속",null,null,null,201901150241]
[6,"서울","성동","성동S/S 154kV #60 BUS","19년 성동P/O 변전협력회사 총액공사","154kV PT배전반 교체","2019-03-04 11:00","2019-03-06 18:00","2019-03-04 11:00","2019-03-06 18:00","연속",null,null,null,201901150237]
[7,"서울","성동","성동S/S 65-66 SEC GIS","19년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2019-03-07 09:00","2019-03-07 11:00","2019-03-07 09:00","2019-03-07 11:00","당일",null,null,null,201901140113]
[8,"서울","성동","성동휘경#1 T/L","19년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2019-03-26 10:00","2019-03-26 15:00","2019-03-26 10:00","2019-03-26 15:00","당일",null,null,null,201901140154]
[9,"서울","성동","성동S/S 60-61 SEC GIS","19년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2019-03-04 09:00","2019-03-04 11:00","2019-03-04 09:00","2019-03-04 11:00","당일",null,null,null,201901140112]
[10,"서울","중부","당인리S/S 154kV #1 BUS TIE CB","19년 중부전력지사 변전협력회사 총액공사","모선보호반 대체","2019-03-04 10:00","2019-03-08 18:00","2019-03-04 10:00","2019-03-08 18:00","연속",null,null,null,201901150033]
[11,"서울","중부","당인리S/S 154kV #2 BUS TIE CB","19년 중부전력지사 변전협력회사 총액공사","모선보호반 대체","2019-03-11 10:00","2019-03-15 18:00","2019-03-11 10:00","2019-03-15 18:00","연속",null,null,null,201901150035]
[12,"서울","중부","동빙고반포#1 T/L","154kV 동빙고S/S 인출T/L 교체공사","154kV 동빙고-반포#1T/L 인출측 OF -> XLPE 선종교체","2019-03-11 09:00","2019-05-03 18:00","2019-03-11 09:00","2019-05-03 18:00","연속",null,null,null,201901220015]
[13,"서울","직할","종로서소문 T/L","19년 직할 변전협력 총액공사","송전선로 보호반 대체, 하자점검","2019-03-11 09:00","2019-03-18 18:00","2019-03-11 09:00","2019-03-18 18:00","연속",null,null,null,201901150111]
[14,"서울","직할","서소문S/S 154kV #1 BUS TIE CB","19년 직할 변전협력 총액공사","하자점검","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901150109]
[15,"서울","직할","아현서소문 T/L","19년 변전협력 총액공사","하자점검","2019-03-04 09:00","2019-03-04 18:00","2019-03-04 09:00","2019-03-04 18:00","당일",null,null,null,201901140205]
[16,"서울","직할","중앙서소문 T/L","19년 직할 변전협력 총액공사","하자점검","2019-03-14 09:00","2019-03-14 18:00","2019-03-14 09:00","2019-03-14 18:00","당일",null,null,null,201901150110]
[17,"서울","직할","신촌순화 T/L","19년 직할 변전협력 총액공사","조작시험","2019-03-26 09:00","2019-03-26 18:00","2019-03-26 09:00","2019-03-26 18:00","당일",null,null,null,201901150112]
[18,"남서울","강남","반포S/S 154kV #1 BUS TIE CB","170kV GIS 보통점검 및 에어 누기개소 보수","보통점검 시행, 에어 누기개소 보수","2019-03-04 09:00","2019-03-05 18:00","2019-03-12 09:00","2019-03-13 18:00","연속",null,null,null,201901180095]
[19,"남서울","강남","신양재신사#3 T/L","170kV GIS 개폐타임 측정 및 에어 누기개소 보수","신양재S/S_신양재-신사#3T/L GIS 개폐타임 측정, 에어 누기개소 보수 신사S/S_신양재-신사#3T/L GIS 보통점검","2019-03-06 09:00","2019-03-06 18:00","2019-03-09 09:00","2019-03-09 18:00","당일",null,null,null,201901180119]
[20,"남서울","동서울","강동천호#2 T/L","송전선로 보호반 교체공사","송전선로 보호반 교체공사","2019-03-11 09:00","2019-03-13 18:00","2019-03-25 09:00","2019-03-27 18:00","연속",null,null,null,201901180014]
[21,"남서울","동서울","강동천호#1 T/L","송전선로 보호반 교체공사","송전선로 보호반 교체공사","2019-03-06 09:00","2019-03-08 18:00","2019-03-18 09:00","2019-03-20 18:00","연속",null,null,null,201901180012]
[22,"남서울","동서울","풍납석촌#1 T/L","풍납-석촌#1T/L 보호배전반 성능개선","풍납-석촌#1T/L 보호배전반 성능개선","2019-03-05 09:00","2019-03-05 14:00","2019-03-05 09:00","2019-03-05 14:00","당일",null,null,null,201901180002]
[23,"남서울","동서울","풍납석촌#2 T/L","풍납-석촌#2T/L 보호배전반 성능개선","풍납-석촌#2T/L 보호배전반 성능개선","2019-03-05 14:00","2019-03-05 18:00","2019-03-05 14:00","2019-03-05 18:00","당일",null,null,null,201901180004]
[24,"남서울","영등포","독산대방#1 T/L","독산,대방S/S 170kV GIS 조작시험","-독산대방#1","2019-03-07 09:00","2019-03-07 14:00","2019-03-09 09:00","2019-03-09 14:00","당일",null,null,null,201901150071]
[25,"남서울","영등포","독산대방#2 T/L","독산,대방S/S 170kV GIS 조작시험","-독산대방#2","2019-03-07 14:00","2019-03-07 18:00","2019-03-09 14:00","2019-03-09 18:00","당일",null,null,null,201901150072]
[26,"남서울","영등포","등촌S/S 154kV #1 BUS TIE CB","등촌S/S 모선보호반 교체",-6100,"2019-03-18 09:00","2019-03-22 18:00","2019-03-18 09:00","2019-03-22 18:00","연속",null,null,null,201901150083]
[27,"남서울","영등포","마곡S/S 154kV #1 BUS","154kV 마곡S/S #4M.Tr 증설공사","154kV M.Tr x 1 bank 170kV GIS x 1 cct 25.8kV SIS x 3 cct","2019-03-01 09:00","2019-03-02 09:00","2019-03-02 09:00","2019-03-03 09:00","연속",null,null,null,201901030068]
[28,"남서울","영등포","화곡마곡#2 T/L","154kV 마곡S/S #4M.Tr 증설공사","170kV GIS 1CCT 증설 - 무부하가압(12H)","2019-03-01 18:00","2019-03-02 09:00","2019-03-02 09:00","2019-03-03 09:00","연속",null,null,null,201901030073]
[29,"남서울","영등포","마곡S/S 154kV #2 BUS","154kV 마곡S/S #4M.Tr 증설공사","154kV M.Tr x 1 bank 170kV GIS x 1 cct 25.8kV SIS x 3 cct","2019-03-02 09:00","2019-03-03 14:00","2019-03-03 09:00","2019-03-03 18:00","연속",null,null,null,201901030070]
[30,"남서울","영등포","화곡마곡#2 T/L","154kV 마곡S/S #4M.Tr 증설공사","170kV GIS 1CCT 증설 - 무부하가압(12H)","2019-03-02 18:00","2019-03-03 18:00","2019-03-03 09:00","2019-03-03 18:00","연속",null,null,null,201901030074]
[31,"남서울","영등포","마곡S/S 154kV #2 BUS","154kV 마곡S/S #4M.Tr 증설공사","#4M.Tr 무부하가압","2019-03-09 10:00","2019-03-10 12:00","2019-03-09 10:00","2019-03-10 12:00","연속",null,null,null,201901220107]
[32,"남서울","영등포","화곡마곡#1 T/L","154kV 마곡S/S #4M.Tr 증설공사","#4M.Tr 무부하가압","2019-03-09 09:00","2019-03-10 18:00","2019-03-09 09:00","2019-03-10 18:00","연속",null,null,null,201901220108]
[33,"남서울","영등포","마곡가양#2 T/L","마곡,가양S/S 170kV GIS 보통점검","-마곡 : 마곡가양#2 초기점검 -가양 : 마곡가양#2 조작시험","2019-03-29 09:00","2019-03-29 18:00","2019-03-29 09:00","2019-03-29 18:00","당일",null,null,null,201901150092]
[34,"남서울","영등포","마곡가양#1 T/L","마곡,가양S/S 170kV GIS 보통점검","-마곡 : 마곡가양#1 초기점검 -가양 : 마곡가양#1 조작시험","2019-03-28 09:00","2019-03-28 18:00","2019-03-28 09:00","2019-03-28 18:00","당일",null,null,null,201901150091]
[35,"남서울","영등포","당인리목동#1 T/L","154kV 당인리-목동T/L 선종교체공사","1. 공사목적 : 공동구내 OF케이블 노후화에 따른 화재 및 설비고장 방지 2. 구간 : 목동S/S ~ 목동C/H 3. 선종 및 길이 : 154kV XLPE 2000SQ / 3.7km 4. 포설 : 6구간 * 2회선 5. 접속개소 : 7개소 * 2회선(EBG, EBA, IJ, NJ)","2019-03-25 09:00","2019-07-01 18:00","2019-03-25 09:00","2019-07-01 18:00","연속",null,null,null,201901070054]
[36,"남서울","영등포","시흥독산#2 T/L","시흥, 독산S/S 170kV GIS 조작시험","-시흥독산#2","2019-03-08 14:00","2019-03-08 18:00","2019-03-08 14:00","2019-03-08 18:00","당일",null,null,null,201901150061]
[37,"남서울","영등포","시흥독산#1 T/L","시흥, 독산S/S 170kV GIS 조작시험","-시흥독산#1","2019-03-08 09:00","2019-03-08 14:00","2019-03-08 09:00","2019-03-08 14:00","당일",null,null,null,201901150060]
[38,"남서울","영등포","신광명광명#2 T/L","신광명, 광명S/S 170kV GIS 보통점검","-신광명광명#2","2019-03-04 09:00","2019-03-04 18:00","2019-03-04 09:00","2019-03-04 18:00","당일",null,null,null,201901150075]
[39,"남서울","영등포","고강화곡#2 T/L","화곡S/S 170kV GIS 초기점검","-고강화곡#2","2019-03-16 14:00","2019-03-16 18:00","2019-03-16 14:00","2019-03-16 18:00","당일",null,null,null,201901150087]
[40,"남서울","영등포","중동화곡#2 T/L","화곡S/S 170kV GIS 보통점검","-중동화곡#2","2019-03-23 09:00","2019-03-23 18:00","취소","취소","당일",null,null,null,201901150090]
[41,"남서울","영등포","고강화곡#1 T/L","화곡S/S 170kV GIS 초기점검","-고강화곡#1","2019-03-16 09:00","2019-03-16 14:00","2019-03-16 09:00","2019-03-16 14:00","당일",null,null,null,201901150086]
[42,"남서울","직할","대방신길#2 T/L","154kV 신길인출전력구 OF케이블 선종교체공사","154kV 신길인출전력구 내 154kV 대방-신길#2T/L 선종교체공사 교체선종 : OF 1200 -> XLPE 1200 접속함교체 등","2019-03-11 09:00","2019-04-30 18:00","2019-03-11 09:00","2019-04-30 18:00","연속",null,null,null,201901090221]
[43,"남서울","영등포","마곡S/S 154kV #1 BUS","154kV 마곡S/S #4M.Tr 증설공사","#4M.Tr 무부하가압","2019-03-09 09:00","2019-03-09 10:00","2019-03-09 09:00","2019-03-09 10:00","당일"]
[44,"인천","김포","계양김포#1 T/L","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사 - 사유 : 불로지구 공동주택 신축공사 지장 - 공사시행 : 대광에이엠씨(요청자). 끝.","2019-03-25 09:00","2019-04-11 18:00","취소","취소","연속",null,null,null,201901150180]
[45,"인천","김포","계양김포#2 T/L","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사 - 사유 : 불로지구 공동주택 신축공사 지장 - 공사시행 : 대광에이엠씨(요청자). 끝.","2019-03-04 09:00","2019-03-21 18:00","취소","취소","연속",null,null,null,201901150178]
[46,"인천","시흥","북시화서시화#2 T/L","서시화S/S 북시화서시화#2 T/L GIS CB 보통점검","서시화S/S 북시화서시화#2 T/L GIS CB 보통점검 북시화S/S 북시화서시화#2 T/L GIS CB 동작시험","2019-03-06 10:00","2019-03-06 18:00","2019-03-10 10:00","2019-03-10 18:00","당일",null,null,null,201901110205]
[47,"인천","시흥","북시화서시화#1 T/L","서시화S/S 북시화서시화#1 T/L GIS CB 보통점검","서시화S/S 북시화서시화#1 T/L GIS CB 보통점검 북시화S/S 북시화서시화#1 T/L GIS CB 동작시험","2019-03-05 10:00","2019-03-05 18:00","2019-03-09 10:00","2019-03-09 18:00","당일",null,null,null,201901110203]
[48,"인천","시흥","신광명소래 T/L","소래S/S 영서소래 T/L GIS 동작점검","소래S/S 영서소래 T/L GIS 동작점검","2019-03-26 10:00","2019-03-26 18:00","2019-03-26 10:00","2019-03-26 18:00","당일",null,null,null,201901140150]
[49,"인천","시흥","온수소래 T/L","소래S/S 170kV 온수소래 T/L GIS 동작점검","소래S/S 170kV 온수소래 T/L GIS 동작점검","2019-03-08 10:00","2019-03-08 18:00","2019-03-08 10:00","2019-03-08 18:00","당일",null,null,null,201901140147]
[50,"인천","시흥","소래S/S 154kV #1 BUS TIE GIS","소래S/S 154kV #1 BUS TIE GIS CB 보통점검","소래S/S 154kV #1 BUS TIE GIS CB 보통점검","2019-03-15 10:00","2019-03-15 18:00","2019-03-15 10:00","2019-03-15 18:00","당일",null,null,null,201901110218]
[51,"인천","시흥","신시흥시화#1 T/L","154kV 신시흥-시화#1T/L 애자교체공사","154kV 신시흥-시화#1T/L 애자교체공사 -병가구간/(상단)반월-시화#2, (하단)신시흥-시화#1","2019-03-11 08:00","2019-03-11 18:00","2019-03-11 08:00","2019-03-11 18:00","당일",null,null,null,201901220023]
[52,"인천","시흥","신시흥시화#2 T/L","154kV 신시흥-시화#2T/L 애자교체공사","154kV 신시흥-시화#2T/L 애자교체공사 -병가구간(No.1~6)/(상단)신시흥-북시화#2, (하단)신시흥-시화#2 -병가구간(No.18~25)/(상단)반월-시화#1, (하단)신시흥-시화#2 -&gt안전이격거리 확보,반월-시화#1T/L 작업없음","2019-03-12 08:00","2019-03-13 18:00","2019-03-12 08:00","2019-03-13 18:00","연속",null,null,null,201901220033]
[53,"인천","시흥","신시흥#1S/S 154kV #2 BUS TIE GIS(2017)","신시흥#1S/S 154kV #2 BUS TIE GIS 초기점검","신시흥#1S/S 154kV #2 BUS TIE GIS 초기점검","2019-03-13 14:00","2019-03-13 18:00","2019-03-13 14:00","2019-03-13 18:00","당일",null,null,null,201901110217]
[54,"인천","시흥","신시흥북시화#2 T/L","154kV 신시흥-북시화#2T/L 애자교체공사","154kV 신시흥-북시화#2T/L 애자교체공사 -병가구간/(상단)신시흥-북시화#2, (하단)신시흥-시화#2","2019-03-12 08:00","2019-03-12 18:00","2019-03-12 08:00","2019-03-12 18:00","당일",null,null,null,201901220029]
[55,"인천","시흥","신시흥시화#2 T/L","신시흥#2S/S #62-63SEC GIS 대체공사[무부하용]","신시흥#2S/S #62-63SEC GIS 대체공사[무부하용]","2019-03-22 08:00","2019-03-23 08:00","2019-03-22 08:00","2019-03-23 08:00","연속",null,null,null,201901110233]
[56,"인천","시흥","신시흥#2S/S 154kV #62 BUS","신시흥#2S/S #62-63SEC GIS 대체공사","신시흥#2S/S #62-63SEC GIS 대체공사","2019-03-19 08:00","2019-03-23 08:00","2019-03-19 08:00","2019-03-23 08:00","연속",null,null,null,201901110231]
[57,"인천","시흥","신시흥#2S/S 154kV #63 BUS","신시흥#2S/S 154kV #62-63 SEC GIS 대체공사","신시흥#2S/S 154kV #62-63 SEC GIS 대체공사","2019-03-18 08:00","2019-03-19 08:00","2019-03-18 08:00","2019-03-19 08:00","연속",null,null,null,201901110221]
[58,"인천","시흥","신시흥#2S/S 62-63-0 SEC CB","신시흥#2S/S 154kV #62-63 SEC GIS 대체공사","신시흥#2S/S 154kV #62-63 SEC GIS 대체공사","2019-03-18 08:00","2019-03-29 18:00","2019-03-18 08:00","2019-03-29 18:00","연속",null,null,null,201901110225]
[59,"인천","시흥","신시흥북시화#1 T/L","신시흥#2S/S #62-63SEC GIS 대체공사[이격거리]","신시흥#2S/S #62-63SEC GIS 대체공사[이격거리]","2019-03-18 08:00","2019-03-20 18:00","2019-03-15 08:00","2019-03-17 18:00","연속",null,null,null,201901110229]
[60,"인천","시흥","신시흥시화#2 T/L","신시흥#2S/S #62-63SEC GIS 대체공사[이격거리]","신시흥#2S/S #62-63SEC GIS 대체공사[이격거리]","2019-03-25 08:00","2019-03-26 18:00","2019-03-25 08:00","2019-03-26 18:00","연속",null,null,null,201901170071]
[61,"인천","시흥","신시흥#2S/S 154kV #3 BUS TIE GIS","신시흥#2S/S 154kV #3 BUS TIE(6300)GIS 동작시험","신시흥#2S/S 154kV #3 BUS TIE(6300)GIS 동작시험","2019-03-13 10:00","2019-03-13 18:00","2019-03-13 10:00","2019-03-13 18:00","당일",null,null,null,201901110212]
[62,"인천","시흥","신시흥#2S/S 154kV #63 BUS","신시흥#2S/S #62-63SEC GIS 대체공사","신시흥#2S/S #62-63SEC GIS 대체공사","2019-03-25 08:00","2019-03-29 08:00","2019-03-25 08:00","2019-03-29 08:00","연속",null,null,null,201901110240]
[63,"인천","시흥","신시흥북시화#1 T/L","신시흥#2S/S #62-63SEC GIS 대체공사[이격거리]","신시흥#2S/S #62-63SEC GIS 대체공사[이격거리]","2019-03-25 08:00","2019-03-26 18:00","2019-03-25 08:00","2019-03-26 18:00","연속",null,null,null,201901170072]
[64,"인천","시흥","신시흥북시화#1 T/L","신시흥#2S/S #62-63SEC GIS 대체공사[무부하용]","신시흥#2S/S #62-63SEC GIS 대체공사[무부하용]","2019-03-28 08:00","2019-03-29 08:00","2019-03-28 08:00","2019-03-29 08:00","연속",null,null,null,201901110244]
[65,"인천","시흥","신시흥#2S/S 154kV #62 BUS","신시흥#2S/S #62-63SEC GIS 대체공사","신시흥#2S/S #62-63SEC GIS 대체공사","2019-03-29 08:00","2019-03-29 18:00","2019-03-29 08:00","2019-03-29 18:00","연속",null,null,null,201901110253]
[66,"인천","시흥","신시흥시화#2 T/L","신시흥#2S/S #62-63SEC GIS 대체공사[이격거리]","신시흥#2S/S #62-63SEC GIS 대체공사[이격거리]","2019-03-18 08:00","2019-03-20 18:00","2019-03-15 08:00","2019-03-17 18:00","연속",null,null,null,201901110228]
[67,"인천","시흥","학익연수#1 T/L","연수S/S 학익연수#1 T/L GIS 하자점검","연수S/S 학익연수#1 T/L GIS 하자점검","2019-03-19 10:00","2019-03-19 18:00","2019-03-19 10:00","2019-03-19 18:00","당일",null,null,null,201901140167]
[68,"인천","인천","남동관교#1 T/L","절연유 시료분석","주기도래 절연유 시료분석","2019-03-15 09:00","2019-03-15 18:00","2019-03-15 09:00","2019-03-15 18:00","당일",null,null,null,201812280016]
[69,"인천","인천","인천남인천#2 T/L","절연유 시료분석","주기도래 절연유 시료분석","2019-03-21 09:00","2019-03-21 18:00","2019-03-21 09:00","2019-03-21 18:00","당일",null,null,null,201812280009]
[70,"인천","인천","남인천학익#2 T/L","절연유 시료분석","주기도래 절연유 시료분석","2019-03-08 09:00","2019-03-08 18:00","2019-03-10 10:00","2019-03-10 18:00","당일",null,null,null,201812280011]
[71,"인천","인천","남인천학익#1 T/L","절연유 시료분석","주기도래 절연유 시료분석","2019-03-07 09:00","2019-03-07 18:00","2019-03-09 10:00","2019-03-09 18:00","당일",null,null,null,201812280010]
[72,"인천","인천","주안만수 T/L","절연유 시료분석","주기도래 절연유 시료분석","2019-03-13 09:00","2019-03-13 18:00","2019-03-13 09:00","2019-03-13 18:00","당일",null,null,null,201812280014]
[73,"인천","인천","송월남인천#2 T/L","송월,남인천S/S 송월남인천#1T/L 보호반 대체공사","송월남인천#1T/L 보호반 대체 관련 #2T/L 휴전","2019-03-18 09:00","2019-03-18 12:00","2019-03-18 09:00","2019-03-18 12:00","당일",null,null,null,201901070160]
[74,"인천","인천","송월남인천#2 T/L","송월,남인천S/S 송월남인천#2T/L 보호반 대체공사","송월S/S 송월남인천#2T/L 보호반 대체공사 남인천S/S 송월남인천#2T/L 보호반 대체공사 송월S/S 송월남인천#2T/L GIS 보통점검 및 보조계전기 교체","2019-03-25 09:00","2019-03-29 18:00","2019-03-25 09:00","2019-03-29 18:00","연속",null,null,null,201901070161]
[75,"인천","인천","송월남인천#1 T/L","송월,남인천S/S 송월남인천#1T/L 보호반 대체공사","송월S/S 송월남인천#1T/L 보호반 대체공사 남인천S/S 송월남인천#1T/L 보호반 대체공사 송월S/S 송월남인천#1T/L GIS 보통점검 및 보조계전기 교체","2019-03-18 09:00","2019-03-22 18:00","2019-03-18 09:00","2019-03-22 18:00","연속",null,null,null,201901070158]
[76,"인천","인천","신가좌주안#1 T/L","신가좌주안#1 T/L 보호배전반 성능개선","87Ry GRL100 성능개선","2019-03-08 10:00","2019-03-08 12:00","2019-03-10 10:00","2019-03-10 12:00","당일",null,null,null,201901160001]
[77,"인천","인천","신가좌주안#2 T/L","신가좌주안#2 T/L 보호배전반 성능개선","GRL100 87 Ry 성능개선","2019-03-08 13:00","2019-03-08 15:00","2019-03-10 13:00","2019-03-10 15:00","당일",null,null,null,201901160002]
[78,"인천","인천","신현포스코CC#2 T/L","SVL 교체공사","구형 SVL을 신형SVL로 교체(난연성 확보)","2019-03-19 09:00","2019-03-22 18:00","취소","취소","연속",null,null,null,201901150079]
[79,"인천","인천","신현포스코CC#1 T/L","SVL 교체공사","구형 SVL을 신형 SVL로 교체(난연성 확보)","2019-03-12 09:00","2019-03-15 18:00","취소","취소","연속",null,null,null,201901150076]
[80,"인천","인천","신가좌신현#2 T/L","154kV신가좌-신현#2T/L 피뢰기 설치공사","송전선로용 피뢰기 설치","2019-03-04 08:00","2019-03-06 18:00","2019-03-04 08:00","2019-03-06 18:00","연속",null,null,null,201901150031]
[81,"인천","인천","계양원창 T/L","원창S/S 계양원창T/L GIS 보통점검 및 보조계전기 교체","원창S/S 계양원창T/L GIS 보통점검 및 보조계전기 교체","2019-03-21 09:00","2019-03-21 18:00","2019-03-21 09:00","2019-03-21 18:00","당일",null,null,null,201901070365]
[82,"인천","인천","북인천원창 T/L","원창S/S 북인천원창T/L GIS 보통점검 및 보조계전기 교체","원창S/S 북인천원창T/L GIS 보통점검 및 보조계전기 교체","2019-03-20 09:00","2019-03-20 18:00","2019-03-20 09:00","2019-03-20 18:00","당일",null,null,null,201901070363]
[83,"인천","인천","신가좌인천#1 T/L","절연유 시료분석","주기도래 절연유 시료분석","2019-03-11 09:00","2019-03-11 18:00","2019-03-11 09:00","2019-03-11 18:00","당일",null,null,null,201812280012]
[84,"인천","인천","신가좌인천#3 T/L","절연유 시료분석","주기도래 절연유 시료분석","2019-03-12 09:00","2019-03-12 18:00","2019-03-12 09:00","2019-03-12 18:00","당일",null,null,null,201812280013]
[85,"인천","인천","신가좌주안#1 T/L","154kV신가좌-주안T/L 태풍취약철탑 보강공사","No.5 철탑 상부재 보강","2019-03-04 08:00","2019-03-06 18:00","2019-03-09 08:00","2019-03-10 18:00","연속",null,null,null,201901150028]
[86,"인천","인천","신가좌주안#2 T/L","154kV신가좌-주안T/L 태풍취약철탑 보강공사","No.5 철탑 상부재 보강","2019-03-07 08:00","2019-03-09 18:00","2019-03-16 08:00","2019-03-17 18:00","연속",null,null,null,201901150034]
[87,"인천","인천","학익연수#2 T/L","절연유 시료분석","주기도래 절연유 시료분석","2019-03-14 09:00","2019-03-14 18:00","2019-03-14 09:00","2019-03-14 18:00","당일",null,null,null,201812280015]
[88,"인천","직할","신부평고강#2 T/L","154kV신부평-고강T/L 태풍취약철탑 보강공사","No.3,4 철탑 상부재 보강","2019-03-17 08:00","2019-03-17 18:00","2019-03-17 08:00","2019-03-17 18:00","당일",null,null,null,201901150037]
[89,"인천","직할","신부평고강#1 T/L","154kV신부평-고강T/L 태풍취약철탑 보강공사","No.3,4 철탑 상부재 보강","2019-03-16 08:00","2019-03-16 18:00","2019-03-16 08:00","2019-03-16 18:00","당일",null,null,null,201901150036]
[90,"인천","직할","부흥부개#1 T/L","부흥S/S 부흥부개#1T/L 170kV GIS 보통점검","부흥S/S 부흥부개#1T/L 170kV GIS 보통점검","2019-03-15 09:00","2019-03-15 18:00","2019-03-15 09:00","2019-03-15 18:00","당일",null,null,null,201901090236]
[91,"인천","직할","부흥부개#2 T/L","부흥S/S 부흥부개#2T/L 170kV GIS 보통점검","부흥S/S 부흥부개#2T/L 170kV GIS 보통점검","2019-03-22 09:00","2019-03-22 18:00","2019-03-22 09:00","2019-03-22 18:00","당일",null,null,null,201901090237]
[92,"인천","직할","신부평S/S 154kV #65 BUS","신부평-청천S/S SW증설","신부평S/S측 1CCT 증설","2019-03-04 09:00","2019-03-07 18:00","2019-03-04 09:00","2019-03-07 18:00","연속",null,null,null,201901020023]
[93,"인천","직할","신부평중동#2 T/L","신부평-청천S/S SW증설","신부평S/S측 1CCT 증설관련하여 모선 무부하 가압용","2019-03-06 18:00","2019-03-07 18:00","2019-03-06 18:00","2019-03-07 18:00","연속",null,null,null,201901020027]
[94,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV #5M.Tr 인출GIS 정비공사 - #60BUS 휴전 - 기설 #1DS,CB,상부BUS,붓싱,LCP 철거 - 신설 부싱 ~ 케이블 연결 - 진공 및 가스주입 -무부하가압 및 가압","2019-03-15 14:00","2019-03-20 18:00","2019-03-15 14:00","2019-03-20 18:00","연속",null,null,null,201901160047]
[95,"인천","직할","중동화곡#1 T/L","154kV중동화곡T/L 태풍취약철탑 보강공사","No.2 철탑 상부재 보강(양회선 휴전)","2019-03-11 08:00","2019-03-14 18:00","취소","취소","연속",null,null,null,201901140090]
[96,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV #4M.Tr 인출GIS 정비공사 - #60BUS 휴전 - 기설 #2DS - 진공 및 가스주입 - 무부하가압 및 가압","2019-03-25 09:00","2019-03-26 14:00","2019-03-25 09:00","2019-03-26 14:00","연속",null,null,null,201901160053]
[97,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV #4M.Tr 인출GIS 정비공사 - #60BUS 휴전 - 기설 #1DS,CB,상부BUS,붓싱,LCP 철거 - 신설 부싱 ~ 케이블 연결 - 진공 및 가스주입 -무부하가압 및 가압","2019-03-26 14:00","2019-03-29 18:00","2019-03-26 14:00","2019-03-29 18:00","연속",null,null,null,201901160054]
[98,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV #5M.Tr 인출GIS 정비공사 - #60BUS 휴전 - 기설 #2DS - 진공 및 가스주입 - 무부하가압 및 가압","2019-03-14 09:00","2019-03-15 14:00","2019-03-14 09:00","2019-03-15 14:00","연속",null,null,null,201901160051]
[99,"경기북부","고양","능곡상암#2 T/L","2019 변전정비회사 총액공사(능곡-상암#2T/L)","170kV GIS 보통점검","2019-03-06 09:00","2019-03-06 18:00","2019-03-06 09:00","2019-03-06 18:00","당일",null,null,null,201901080197]
[100,"경기북부","고양","능곡상암#1 T/L","2019 변전정비회사 총액공사(능곡-상암#1T/L)","170kV GIS 보통점검","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901080195]
[101,"경기북부","고양","불광서대문#2 T/L","154kV양주-불광-서대문T/L 정비공사","154kV불광-서대문T/L C/H 조립작업 안전확보(활선 근접)","2019-03-08 07:00","2019-03-08 18:00","2019-03-08 07:00","2019-03-08 18:00","당일",null,null,null,201901150019]
[102,"경기북부","고양","양주불광#1 T/L","154kV양주-불광-서대문T/L 정비공사","154kV불광-서대문T/L C/H 조립작업 안전확보(활선 근접)","2019-03-09 07:00","2019-03-09 18:00","2019-03-09 07:00","2019-03-09 18:00","연속",null,null,null,201901150015]
[103,"경기북부","고양","신덕은S/S 154kV #66 BUS","신덕은S/S #64D.Tr 증설공사","154kV M.Tr 1bank 설치 170kV GIS 1CCT 설치 25.8kV GIS 4CCT 설치","2019-03-20 14:00","2019-03-20 16:00","2019-03-20 14:00","2019-03-20 16:00","당일",null,null,null,201901090004]
[104,"경기북부","고양","신덕은S/S 154kV #61 BUS","신덕은S/S #64D.Tr 증설공사","154kV M.Tr 1bank 설치 170kV GIS 1CCT 설치 25.8kV GIS 4CCT 설치","2019-03-20 12:00","2019-03-20 14:00","2019-03-20 12:00","2019-03-20 14:00","당일",null,null,null,201901090003]
[105,"경기북부","고양","일산지도#2 T/L","2019 변전정비회사 총액공사(일산-지도#2T/L)","170kV GIS 하자점검","2019-03-25 10:00","2019-03-26 18:00","2019-03-25 10:00","2019-03-26 18:00","연속",null,null,null,201901080201]
[106,"경기북부","고양","일산지도#1 T/L","2019 변전정비회사 총액공사(일산-지도#1T/L)","170kV GIS 하자점검","2019-03-18 10:00","2019-03-19 18:00","2019-03-18 10:00","2019-03-19 18:00","연속",null,null,null,201901080200]
[107,"경기북부","구리","미금구리#1 T/L","19년도 구리전력 154kV GIS 보통점검","19년도 구리전력 154kV GIS 보통점검","2019-03-25 09:00","2019-03-25 18:00","취소","취소","당일",null,null,null,201901150113]
[108,"경기북부","구리","미금구리#2 T/L","19년도 구리전력 154kV 장기무동작 차단기점검","19년도 구리전력 154kV 장기무동작 차단기점검","2019-03-26 09:00","2019-03-26 18:00","취소","취소","당일",null,null,null,201901150175]
[109,"경기북부","구리","동서울서종#1 T/L","19년도 구리전력 154kV GIS 보통점검","19년도 구리전력 154kV GIS 보통점검","2019-03-20 09:00","2019-03-20 14:00","2019-03-20 09:00","2019-03-20 14:00","당일",null,null,null,201901150144,"O"]
[110,"경기북부","구리","서종청평PP#2 T/L","19년도 구리전력 154kV GIS 보통점검","19년도 구리전력 154kV GIS 보통점검","2019-03-19 14:00","2019-03-19 18:00","2019-03-19 14:00","2019-03-19 18:00","당일",null,null,null,201901150142]
[111,"경기북부","구리","서종청평PP#1 T/L","19년도 구리전력 154kV GIS 보통점검","19년도 구리전력 154kV GIS 보통점검","2019-03-18 14:00","2019-03-18 18:00","2019-03-18 14:00","2019-03-18 18:00","당일",null,null,null,201901150140,"O"]
[112,"경기북부","구리","동서울서종#2 T/L","19년도 구리전력 154kV GIS 보통점검","19년도 구리전력 154kV GIS 보통점검","2019-03-21 10:00","2019-03-21 18:00","2019-03-21 10:00","2019-03-21 18:00","당일",null,null,null,201901150149]
[113,"경기북부","구리","덕소진건#1 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33,No.34~38 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2019-03-29 09:00","2019-04-01 18:00","2019-03-29 09:00","2019-04-01 18:00","연속",null,null,null,201812310030]
[114,"경기북부","구리","덕소진건#2 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33,No.34~38 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2019-03-29 09:00","2019-04-01 18:00","2019-03-29 09:00","2019-04-01 18:00","연속",null,null,null,201812310032]
[115,"경기북부","구리","별내진접 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33,No.34~38 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2019-03-19 09:00","2019-03-23 18:00","2019-03-23 09:00","2019-03-27 18:00","연속",null,null,null,201812310029]
[116,"경기북부","직할","백석덕계#1 T/L","'19년 변전협력회사 총액공사(덕계S/S 백석-덕계#1T/L )","GIS 보통점검","2019-03-15 10:00","2019-03-15 18:00","2019-03-16 10:00","2019-03-16 18:00","당일",null,null,null,201901090090]
[117,"경기북부","직할","양주쌍문#2 T/L","양주S/S옥외철구 GIS화 전력구공사","양주쌍문#2 T/L 인출측 전력구공사","2019-03-16 09:00","2019-03-18 18:00","2019-03-16 09:00","2019-03-17 18:00","연속",null,null,null,201901110054]
[118,"경기북부","직할","양주쌍문#1 T/L","양주S/S옥외철구 GIS화 전력구공사","양주쌍문#1 T/L 인출측 전력구공사","2019-03-19 09:00","2019-03-21 18:00","2019-03-23 09:00","2019-03-24 18:00","연속",null,null,null,201901110060,"O"]
[119,"경기북부","직할","양주녹양#2 T/L","양주S/S옥외철구 GIS화 전력구공사","양주녹양#2 T/L 인출측 전력구공사","2019-03-14 09:00","2019-03-15 18:00","2019-03-14 09:00","2019-03-15 18:00","연속",null,null,null,201901110064]
[120,"경기북부","직할","양주녹양#1 T/L","양주S/S옥외철구 GIS화 전력구공사","양주녹양#1 T/L 인출측 전력구공사","2019-03-11 09:00","2019-03-13 18:00","2019-03-11 09:00","2019-03-13 18:00","연속",null,null,null,201901110062]
[121,"경기북부","구리","지제용문 T/L","154kV 지제분기T/L 건설공사","○ 구간 : 기설 154kV 용문T/L No.80,81 ~ 지제S/S ○ 지지물 : 신설 철탑 2기(No.81, 2) \n○ 전력선 : ACSR 410㎡ * 2B * 2C, 0.5km ○ 공정 : 1차휴전 - 철탑 No.2 조립 및 문막-용문T/L No.80~신설2~81 가선","2019-03-25 07:00","2019-03-26 18:00","2019-03-25 07:00","2019-03-26 18:00","연속"]
[122,"경기북부","구리","문막용문 T/L","154kV 지제분기T/L 건설공사","○ 구간 : 기설 154kV 용문T/L No.80,81 ~ 지제S/S ○ 지지물 : 신설 철탑 2기(No.81, 2) \n○ 전력선 : ACSR 410㎡ * 2B * 2C, 0.5km ○ 공정 : 1차휴전 - 철탑 No.2 조립 및 문막-용문T/L No.80~신설2~81 가선","2019-03-25 07:00","2019-03-28 18:00","2019-03-25 07:00","2019-03-28 18:00","연속"]
[123,"경기","군포","마도사강#1 T/L","18-19 송전정비회사 총액공사(군포)","154kV 마도-사강#1T/L 압축인류클램프 균열개소 정비","2019-03-14 08:00","2019-03-15 18:00","2019-03-14 08:00","2019-03-15 18:00","연속",null,null,null,201901070079]
[124,"경기","군포","반월시화#2 T/L","154kV 신시흥-시화#1T/L 애자교체공사","154kV 신시흥-시화#1T/L 애자교체공사 -병가구간/(상단)반월-시화#2, (하단)신시흥-시화#1 -안전이격거리 확보로 휴전신청(시월T/L 작업없음)","2019-03-11 08:00","2019-03-11 18:00","2019-03-11 08:00","2019-03-11 18:00","당일",null,null,null,201901220026]
[125,"경기","군포","반월시화#1 T/L","154kV 신시흥-시화#2T/L 애자교체공사","154kV 신시흥-시화#2T/L 애자교체공사 -병가구간(No.18~25)/(상단)반월-시화#1, (하단)신시흥-시화#2 -&gt안전이격거리 확보,반월-시화#1T/L 작업없음","2019-03-13 08:00","2019-03-13 18:00","2019-03-13 08:00","2019-03-13 18:00","당일",null,null,null,201901220034]
[126,"경기","군포","서서울#2남수원 #2T/L","345kV 신온양-서서울 T/L 전선접속개소 전선교체공사","전선교체 관련 안전이격거리확보","2019-03-01 09:00","2019-03-08 18:00","2019-03-01 09:00","2019-03-08 18:00","연속",null,null,null,201901100235]
[127,"경기","군포","서서울#2남수원 #1T/L","345kV 신온양-서서울 T/L 전선접속개소 전선교체공사","전선교체 관련 안전이격거리확보","2019-03-01 09:00","2019-03-08 18:00","2019-03-01 09:00","2019-03-08 18:00","연속",null,null,null,201901100236]
[128,"경기","군포","서서울S/S 66-67 SEC GIS","'19년 군포P/O 변전정비회사 총액공사","- GIS 초기점검","2019-03-08 09:30","2019-03-08 18:00","2019-03-08 09:30","2019-03-08 18:00","연속",null,null,null,201901080136]
[129,"경기","군포","서서울산본#1 T/L","'19년 군포P/O 변전정비회사 총액공사","- 서서울 : GIS 초기점검, 산본 : GIS 하자점검","2019-03-25 09:30","2019-03-25 18:00","2019-03-25 09:30","2019-03-25 18:00","당일",null,null,null,201901080132]
[130,"경기","군포","서서울S/S 154kV #61-66 BUS TIE GIS","'19년 군포P/O 변전정비회사 총액공사","- GIS 초기점검","2019-03-04 09:30","2019-03-04 18:00","2019-03-04 09:30","2019-03-04 18:00","당일",null,null,null,201901080129]
[131,"경기","군포","서서울S/S 154kV #60-65 BUS TIE GIS","'19년 군포P/O 변전정비회사 총액공사","- GIS 초기점검","2019-03-04 09:30","2019-03-04 18:00","2019-03-04 09:30","2019-03-04 18:00","당일",null,null,null,201901080122]
[132,"경기","군포","서서울S/S 154kV #62-67 BUS TIE GIS","'19년 군포P/O 변전정비회사 총액공사","- GIS 초기점검","2019-03-06 09:30","2019-03-06 18:00","2019-03-06 09:30","2019-03-06 18:00","당일",null,null,null,201901080131]
[133,"경기","군포","서서울S/S 60-61 SEC GIS","'19년 군포P/O 변전정비회사 총액공사","- GIS 초기점검","2019-03-07 09:30","2019-03-07 18:00","2019-03-07 09:30","2019-03-07 18:00","연속",null,null,null,201901080133]
[134,"경기","군포","서서울S/S 61-62 SEC GIS","'19년 군포P/O 변전정비회사 총액공사","- GIS 초기점검","2019-03-07 09:30","2019-03-07 18:00","2019-03-07 09:30","2019-03-07 18:00","연속",null,null,null,201901080134]
[135,"경기","군포","서서울S/S 65-66 SEC GIS","'19년 군포P/O 변전정비회사 총액공사","- GIS 초기점검","2019-03-08 09:30","2019-03-08 18:00","2019-03-08 09:30","2019-03-08 18:00","연속",null,null,null,201901080135]
[136,"경기","군포","화성장덕 T/L","19년 군포P/O 변전정비회사 총액공사(조작)","1. GIS 조작시험(유압)","2019-03-05 14:00","2019-03-05 17:00","2019-03-10 14:00","2019-03-10 17:00","당일",null,null,null,201901080078]
[137,"경기","군포","장덕마도 T/L","19년 군포P/O 변전정비회사 총액공사(조작)","1. GIS 조작시험(유압)","2019-03-05 10:00","2019-03-05 13:00","2019-03-05 10:00","2019-03-05 13:00","당일",null,null,null,201901080077]
[138,"경기","군포","조암구문천#2 T/L","345kV 신온양서서울#1T/L 97호 피뢰기 설치 관련 안전확보차","345kV 신온양서서울#1T/L 97호 피뢰기 설치 관련 안전확보차","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901110065]
[139,"경기","군포","시화중시화 T/L","19년 군포P/O 변전정비회사 총액공사","중시화 및 시화변전소 시화-중시화T/L GIS 조작시험","2019-03-15 09:00","2019-03-15 18:00","2019-03-15 09:00","2019-03-15 18:00","당일",null,null,null,201901100171]
[140,"경기","군포","성곡중시화 T/L","19년 군포P/O 변전정비회사 총액공사","중시화 및 성곡변전소 성곡-중시화T/L GIS 조작시험","2019-03-12 09:00","2019-03-12 18:00","2019-03-12 09:00","2019-03-12 18:00","당일",null,null,null,201901100169]
[141,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-14 08:30","2019-03-16 17:30","취소","취소","연속",null,null,null,201901080214]
[142,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-11 08:30","2019-03-13 17:30","취소","취소","연속",null,null,null,201901080212]
[143,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-07 08:30","2019-03-10 17:30","취소","취소","연속",null,null,null,201901080208]
[144,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-04 08:30","2019-03-06 17:30","취소","취소","연속",null,null,null,201901080210]
[145,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-20 08:30","2019-03-23 17:30","취소","취소","연속",null,null,null,201901080217]
[146,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-17 08:30","2019-03-19 17:30","취소","취소","연속",null,null,null,201901080216]
[147,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-20 08:30","2019-03-24 17:30","취소","취소","연속",null,null,null,201901080218]
[148,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-25 08:30","2019-03-27 17:30","취소","취소","연속",null,null,null,201901080220]
[149,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-28 08:30","2019-03-31 17:30","취소","취소","연속",null,null,null,201901080222]
[150,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-17 08:30","2019-03-19 17:30","취소","취소","연속",null,null,null,201901080215]
[151,"경기","동부","곤지암S/S 154kV #2 BUS TIE GIS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 6200 B/T 장기휴전 필요 - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-03-04 08:30","2019-04-21 17:30","취소","취소","연속",null,null,null,201901070059]
[152,"경기","동부","곤지암S/S 154kV #1 Sh.C CB","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 Sh.C 장기휴전 - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-03-04 08:30","2019-04-21 17:30","취소","취소","연속",null,null,null,201901070052]
[153,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-14 08:30","2019-03-16 17:30","취소","취소","연속",null,null,null,201901080213]
[154,"경기","동부","곤지암S/S 154kV #61 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설(2차작업) - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-03-11 08:30","2019-03-24 17:30","취소","취소","연속",null,null,null,201901080118]
[155,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-11 08:30","2019-03-13 17:30","취소","취소","연속",null,null,null,201901080211]
[156,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-07 08:30","2019-03-09 17:30","취소","취소","연속",null,null,null,201901080207]
[157,"경기","동부","곤지암S/S 154kV #66 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설(1차작업) - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-03-04 08:30","2019-03-10 17:30","취소","취소","연속",null,null,null,201901080116]
[158,"경기","동부","곤지암S/S 154kV #2 Sh.C CB","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 Sh.C 장기휴전 - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-03-04 08:30","2019-04-21 17:30","취소","취소","연속",null,null,null,201901070053]
[159,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-04 08:30","2019-03-06 17:30","취소","취소","연속",null,null,null,201901080209]
[160,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-25 08:30","2019-03-27 17:30","취소","취소","연속",null,null,null,201901080219]
[161,"경기","동부","곤지암S/S 154kV #66 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설(3차작업) - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-03-25 08:30","2019-04-07 17:30","취소","취소","연속",null,null,null,201901080202]
[162,"경기","동부","곤지암초월#2 T/L","154kV 곤지암-초월T/L OPGW 증설공사","* 곤지암S/S S/T ~ No.12 OPGW 신설 3.383km * No.12 ~ No.44 OPGW 교체(24→48C) 8.323km * 곤지암S/S ICT실 ~ S/T FOFC-S-24 시설 0.200km * 접속, 최종시험 및 기타 부대공사 1식","2019-03-11 09:00","2019-03-13 18:00","2019-03-11 09:00","2019-03-13 18:00","연속",null,null,null,201901110024]
[163,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-03-28 08:30","2019-03-31 17:30","취소","취소","연속",null,null,null,201901080221]
[164,"경기","동부","곤지암초월#1 T/L","154kV 곤지암-초월T/L OPGW 증설공사","* 곤지암S/S S/T ~ No.12 OPGW 신설 3.383km * No.12 ~ No.44 OPGW 교체(24→48C) 8.323km * 곤지암S/S ICT실 ~ S/T FOFC-S-24 시설 0.200km * 접속, 최종시험 및 기타 부대공사 1식","2019-03-14 09:00","2019-03-23 18:00","2019-03-14 09:00","2019-03-23 18:00","연속",null,null,null,201901110033]
[165,"경기","동부","분당S/S 65-66 SEC GIS","19년 동부변전협력회사 총액공사","분당: 65-66GIS (개폐타임) -43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-03-29 09:00","2019-03-29 18:00","2019-03-29 09:00","2019-03-29 18:00","당일",null,null,null,201901070480]
[166,"경기","동부","분당S/S 60-61 SEC GIS","19년 동부변전협력회사 총액공사","분당: 60-61GIS (개폐타임) -43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-03-06 09:00","2019-03-06 18:00","2019-03-06 09:00","2019-03-06 18:00","당일",null,null,null,201901070448]
[167,"경기","동부","분당S/S 154kV #1 BUS TIE GIS","19년 동부변전협력회사 총액공사","분당: 6100 GIS(개폐타임) -43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-03-21 09:00","2019-03-21 18:00","2019-03-21 09:00","2019-03-21 18:00","당일",null,null,null,201901070471]
[168,"경기","동부","분당S/S 분당-오포#2T/L GIS(2018)","19년 동부변전협력회사 총액공사","분당: 분당-오포#2T/L GIS(초기),43L/R 회로보완 확인 오포: 분당-오포#2T/L GIS(보통),43L/R 회로보완 확인","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901070482]
[169,"경기","동부","분당S/S 분당-오포#1T/L GIS(2018)","19년 동부변전협력회사 총액공사","분당: 분당-오포#1T/L GIS(초기),43L/R 회로보완 확인 오포: 분당-오포#1T/L GIS(보통),43L/R 회로보완 확인","2019-03-04 09:00","2019-03-04 18:00","2019-03-04 09:00","2019-03-04 18:00","당일",null,null,null,201901070481]
[170,"경기","동부","야탑성현#2 T/L","154kV 야탑-성현T/L OPGW 증설공사","* 성현S/S G/T ~ No.9 OPGW 교체(24→48C) 2.320km * No.9 ~ 야탑S/S G/T OP-S-L24 증설 2.440km * 성현S/S ICT실 ~ G/T FOFC-S-48 시설 0.100km * 야탑S/S ICT실 ~ G/T FOFC-S-24 시설 0.100km * 접속, 최종시험 및 기타 부대공사 1식","2019-03-27 09:00","2019-03-29 18:00","2019-03-27 09:00","2019-03-29 18:00","연속",null,null,null,201901110066]
[171,"경기","동부","성현분당#1 T/L","154kV 야탑-성현T/L OPGW 증설공사","* 성현S/S G/T ~ No.9 OPGW 교체(24→48C) 2.320km * No.9 ~ 야탑S/S G/T OP-S-L24 증설 2.440km * 성현S/S ICT실 ~ G/T FOFC-S-48 시설 0.100km * 야탑S/S ICT실 ~ G/T FOFC-S-24 시설 0.100km * 접속, 최종시험 및 기타 부대공사 1식","2019-03-27 09:00","2019-03-29 18:00","2019-03-27 09:00","2019-03-29 18:00","연속",null,null,null,201901110068]
[172,"경기","동부","성현분당#2 T/L","154kV 야탑-성현T/L OPGW 증설공사","* 성현S/S G/T ~ No.9 OPGW 교체(24→48C) 2.320km * No.9 ~ 야탑S/S G/T OP-S-L24 증설 2.440km * 성현S/S ICT실 ~ G/T FOFC-S-48 시설 0.100km * 야탑S/S ICT실 ~ G/T FOFC-S-24 시설 0.100km * 접속, 최종시험 및 기타 부대공사 1식","2019-03-24 09:00","2019-03-26 18:00","2019-03-24 09:00","2019-03-26 18:00","연속",null,null,null,201901170035]
[173,"경기","동부","야탑성현#1 T/L","154kV 야탑-성현T/L OPGW 증설공사","* 성현S/S G/T ~ No.9 OPGW 교체(24→48C) 2.320km * No.9 ~ 야탑S/S G/T OP-S-L24 증설 2.440km * 성현S/S ICT실 ~ G/T FOFC-S-48 시설 0.100km * 야탑S/S ICT실 ~ G/T FOFC-S-24 시설 0.100km * 접속, 최종시험 및 기타 부대공사 1식","2019-03-24 09:00","2019-03-26 18:00","2019-03-24 09:00","2019-03-26 18:00","연속",null,null,null,201901170037]
[174,"경기","동부","중원S/S 중원-야탑T/L GIS","19년 동부변전협력회사 총액공사","중원,야탑:중원-야탑#1T/L 보호반대체(~20)","2019-03-18 09:00","2019-03-20 18:00","2019-03-18 09:00","2019-03-20 18:00","연속",null,null,null,201901140034]
[175,"경기","동부","초월성현#1 T/L","154kV 곤지암-초월T/L OPGW 증설공사","* 곤지암S/S S/T ~ No.12 OPGW 신설 3.383km * No.12 ~ No.44 OPGW 교체(24→48C) 8.323km * 곤지암S/S ICT실 ~ S/T FOFC-S-24 시설 0.200km * 접속, 최종시험 및 기타 부대공사 1식","2019-03-22 09:00","2019-03-23 18:00","2019-03-22 09:00","2019-03-23 18:00","연속",null,null,null,201901110056]
[176,"경기","성남","용인남사#2 T/L","남사S/S 용인-남사#2T/L GIS 보통점검","남사S/S 용인-남사#2T/L GIS 보통점검","2019-03-06 09:00","2019-03-06 18:00","취소","취소","당일",null,null,null,201901110147]
[177,"경기","성남","용인남사#1 T/L","남사S/S 용인-남사#1T/L 보통점검 등","남사S/S 용인-남사#1T/L 보통점검 용인S/S 용인-남사#1T/L CVT 하자점검","2019-03-04 09:00","2019-03-04 18:00","취소","취소","연속",null,null,null,201901110162]
[178,"경기","성남","남사진위#2 T/L","남사S/S 남사-진위#2T/L 하자보수(ES관련)","남사S/S 남사-진위#2T/L 하자보수(ES관련)","2019-03-06 09:00","2019-03-08 18:00","취소","취소","연속",null,null,null,201901110149]
[179,"경기","성남","남사진위#1 T/L","154kV 동탄S/S GIS 및 SIS 설치공사","1.남사-동탄#1TL , 동탄-진위#1TL 건설(병행작업) 2.동탄S/S GIS C/H Chamber 조립 3.진위S/S 동탄-진위#1TL Line PT 설치","2019-03-11 09:00","2019-03-29 18:00","2019-03-11 09:00","2019-03-29 18:00","연속",null,null,null,201901110025]
[180,"경기","성남","서안성S/S 66-67 SEC(66-67-0) GIS","서안성S/S 66-67 GIS 하자점검","서안성S/S 66-67 GIS 하자점검","2019-03-04 14:00","2019-03-04 18:00","2019-03-04 14:00","2019-03-04 18:00","당일",null,null,null,201901110160]
[181,"경기","성남","서안성S/S 61-62 SEC(61-62-0) GIS","서안성S/S 61-62 GIS 하자점검","서안성S/S 61-62 GIS 하자점검","2019-03-04 09:00","2019-03-04 14:00","2019-03-04 09:00","2019-03-04 14:00","당일",null,null,null,201901110159]
[182,"경기","성남","서안성S/S 154kV #3BUS-TIE(6300) GIS","서안성S/S 6300 BUS TIE 하자점검","서안성S/S 6300 BUS TIE 하자점검","2019-03-21 09:00","2019-03-21 18:00","2019-03-21 09:00","2019-03-21 18:00","당일",null,null,null,201901110157]
[183,"경기","성남","신성남서판교 #3 T/L","신성남S/S 신성남-서판교#3T/L 하자점검","신성남S/S 신성남-서판교#3T/L 하자점검","2019-03-20 09:00","2019-03-20 18:00","2019-03-20 09:00","2019-03-20 18:00","당일",null,null,null,201901110155]
[184,"경기","성남","신수원S/S 154kV #61 BUS","신수원S/S 154kV GIS 인출 BAY 조정공사","신수원S/S 154kV GIS 인출 BAY 조정공사","2019-03-11 09:00","2019-03-16 18:00","취소","취소","연속",null,null,null,201901110175]
[185,"경기","성남","신수원S/S 154kV #66 BUS","신수원S/S 154kV GIS 인출 BAY 조정공사","신수원S/S 154kV GIS 인출 BAY 조정공사","2019-03-17 09:00","2019-03-23 18:00","취소","취소","연속",null,null,null,201901110176]
[186,"경기","성남","신수원S/S 154kV #61 BUS","신수원S/S 154kV GIS 인출 BAY 조정공사","신수원S/S 154kV GIS 인출 BAY 조정공사","2019-03-24 09:00","2019-03-30 18:00","취소","취소","연속",null,null,null,201901110177]
[187,"경기","성남","신용인용인#2 T/L","154kV 신용인-용인#2T/L 정밀점검","154kV 신용인-용인#2T/L No.1-27 정밀점검 시행","2019-03-27 08:00","2019-03-28 18:00","취소","취소","매일",null,null,null,201901100233]
[188,"경기","성남","신용인용인#1 T/L","154kV 신용인-용인#1T/L 정밀점검","154kV 신용인-용인#1T/L No.1-27 정밀점검 시행","2019-03-25 08:00","2019-03-26 18:00","취소","취소","매일",null,null,null,201901100232]
[189,"경기","성남","신성남정자 #3 T/L","신성남S/S 신성남-정자#3T/L 하자점검 등","신성남S/S 신성남-정자#3T/L 하자점검 정 자S/S 신성남-정자#3T/L 하자점검","2019-03-18 09:00","2019-03-18 18:00","2019-03-18 09:00","2019-03-18 18:00","당일",null,null,null,201901110168]
[190,"경기","성남","신용인S/S 154kV #62BUS","신용인S/S #4M.Tr 증설용 170kV GIS 설치공사","170kV GIS × 4CCT 설치 기타부대작업 1식","2019-03-04 09:00","2019-03-10 18:00","취소","취소","연속"]
[191,"경기","성남","신용인S/S 154kV #67BUS","신용인S/S #4M.Tr 증설용 170kV GIS 설치공사","170kV GIS × 4CCT 설치 기타부대작업 1식","2019-03-11 09:00","2019-03-17 18:00","취소","취소","연속"]
[192,"경기","직할","남수원S/S 154kV #2 BUS","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(서서울2-남수원#2T/L,#1M.Tr)","2019-03-25 09:00","2019-04-04 09:00","2019-03-25 09:00","2019-04-04 09:00","연속",null,null,null,201901070298]
[193,"경기","직할","서서울#2남수원 #2T/L","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(서서울2-남수원#2T/L,#1M.Tr)","2019-03-04 09:00","2019-04-04 18:00","2019-03-04 09:00","2019-04-04 18:00","연속",null,null,null,201901070293]
[194,"경기","직할","남수원S/S 154kV #1 BUS","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(서서울2-남수원#2T/L,#1M.Tr)","2019-03-11 09:00","2019-03-23 18:00","2019-03-11 09:00","2019-03-23 18:00","연속",null,null,null,201901070295]
[195,"경기","직할","서서울#2남수원 #1T/L","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(서서울2-남수원#2T/L,#1M.Tr 무부하 가압 선로)","2019-03-22 14:00","2019-03-23 14:00","2019-03-22 14:00","2019-03-23 14:00","연속",null,null,null,201901070297]
[196,"경기","직할","남수원S/S 154kV #2 BUS","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(서서울2-남수원#2T/L,#1M.Tr)","2019-03-04 09:00","2019-03-09 18:00","2019-03-04 09:00","2019-03-09 18:00","연속",null,null,null,201901070294]
[197,"경기","직할","화성발안#1 T/L","일진제 PMJ 접속함(리콜분) 교체공사","화성-발안#1T/L J/B#1-4 접속함 교체 - R형 접속함을 Flat형 접속함으로 교체","2019-03-11 09:00","2019-03-24 18:00","2019-03-11 09:00","2019-03-24 18:00","연속",null,null,null,201901020131]
[198,"경기","직할","화성발안#2 T/L","일진제 PMJ 접속함(리콜분) 교체공사","화성-발안#2T/L J/B#1-4 접속함 교체 - R형 접속함을 Flat형 접속함으로 교체","2019-03-25 09:00","2019-04-07 18:00","2019-03-25 09:00","2019-04-07 18:00","연속",null,null,null,201901020134]
[199,"경기","직할","율전의왕#1 T/L","의왕S/S 154kV 장기사용 GIS 교체공사","의왕S/S 율전의왕#1T/L GIS 대체","2019-03-04 09:00","2019-03-24 18:00","2019-03-04 09:00","2019-03-24 18:00","연속",null,null,null,201901070132]
[200,"경기","직할","의왕동안양#2 T/L","154kV 의왕S/S SW 증설공사(금정-전철 #1T/L)","ㅇ의왕S/S SW 증설설비 (#2BUS) 무부하 가압","2019-03-15 09:00","2019-03-16 18:00","2019-03-15 09:00","2019-03-16 18:00","연속",null,null,null,201901070050]
[201,"경기","직할","의왕동안양#2 T/L","154kV 의왕S/S SW 증설공사(금정-전철 #1T/L)","ㅇ 의왕S/S SW증설설비(#1BUS) 무부하 가압","2019-03-08 09:00","2019-03-09 18:00","2019-03-08 09:00","2019-03-09 18:00","연속",null,null,null,201901070048]
[202,"경기","직할","화성마도 T/L","19년 변전협력회사 총액공사","화성S/S 화성마도T/L GIS 조작시험","2019-03-04 09:00","2019-03-04 18:00","2019-03-09 09:00","2019-03-09 18:00","당일",null,null,null,201901080187]
[203,"경기","직할","화성조암#1 T/L","19년 변전협력회사 총액공사","화성S/S 화성조암#1T/L GIS 조작시험 및 CVT 하자점검","2019-03-26 09:00","2019-03-26 18:00","2019-03-26 09:00","2019-03-26 18:00","당일",null,null,null,201901080188]
[204,"경기","직할","화성조암#2 T/L","19년 변전협력회사 총액공사","화성S/S 화성조암#2T/L GIS 조작시험 및 CVT 하자점검","2019-03-27 09:00","2019-03-27 18:00","2019-03-27 09:00","2019-03-27 18:00","당일",null,null,null,201901080189]
[205,"경기","평택","고덕S/S 고덕-평택#1T/L CB","345kV 고덕E/C 154kV 고덕-삼성전자 T/L용 S.W 증설","170kV GIS 2CCT 설치 #60BUS 무부하 가압","2019-03-18 14:00","2019-03-19 14:00","2019-03-18 14:00","2019-03-19 14:00","연속",null,null,null,201901030001]
[206,"경기","평택","고덕S/S 고덕-평택#2T/L CB","345kV 고덕E/C 154kV 고덕-삼성전자 T/L용 S.W 증설","170kV GIS 2CCT 설치 #65BUS 무부하 가압, 고덕-삼성전자#4T/L 무부하 가압","2019-03-26 14:00","2019-03-27 14:00","2019-03-26 14:00","2019-03-27 14:00","연속",null,null,null,201901030002]
[207,"경기","평택","서운안성#2 T/L","154kV 서운안성T/L 정밀점검","154kV 서운안성T/L 정밀점검 시행 1. 작업구간 : 안성S/S~서운S/S 2. 작업물량 : 철탑 61기, 18.706km","2019-03-06 09:00","2019-03-10 18:00","2019-03-06 09:00","2019-03-10 18:00","연속",null,null,null,201812280041]
[208,"경기","평택","서운안성#1 T/L","154kV 서운안성T/L 정밀점검","154kV 서운안성T/L 정밀점검 시행 1. 작업구간 : 안성S/S~서운S/S 2. 작업물량 : 철탑 61기, 18.706km","2019-03-01 09:00","2019-03-05 18:00","2019-03-01 09:00","2019-03-05 18:00","연속",null,null,null,201812280040,"O"]
[209,"경기","평택","서운만승 T/L","154kV 서운만승T/L 정밀점검","154kV 서운만승T/L 정밀점검 시행 1. 작업구간 : 서운S/S~No.28 2. 작업물량 : 철탑 28기, 8.690km","2019-03-01 09:00","2019-03-02 18:00","2019-03-01 09:00","2019-03-02 18:00","연속",null,null,null,201812280043,"O"]
[210,"경기","평택","서운삼죽 T/L","154kV 서운만승T/L 정밀점검","154kV 서운만승T/L 정밀점검 시행 1. 작업구간 : 서운S/S~No.28 2. 작업물량 : 철탑 28기, 8.690km","2019-03-09 09:00","2019-03-10 18:00","2019-03-09 09:00","2019-03-10 18:00","연속",null,null,null,201812280044]
[211,"경기","평택","안성S/S 154kV #1 BUS TIE CB","안성S/S 170kV GIS 용량대체공사","서안성-안성#1T/L GIS 철거 및 설치 6100B/T GIS 철거 및 설치 #2M.Tr GIS 철거 및 설치","2019-03-30 08:00","2019-04-19 18:00","2019-03-30 08:00","2019-04-19 18:00","연속",null,null,null,201901020037]
[212,"경기","평택","안성S/S 154kV #65 BUS","안성S/S 170kV GIS 용량대체공사","서안성-안성#1T/L GIS 철거 및 설치 6100B/T GIS 철거 및 설치 #2M.Tr GIS 철거 및 설치 - #2BUS 철거 및 설치","2019-03-30 08:00","2019-04-02 18:00","2019-03-30 08:00","2019-04-02 18:00","연속",null,null,null,201901020038]
[213,"경기","평택","서안성안성#1 T/L","안성S/S 170kV GIS 용량대체공사","서안성-안성#1T/L GIS 철거 및 설치 6100B/T GIS 철거 및 설치 #2M.Tr GIS 철거 및 설치","2019-03-30 08:00","2019-04-19 18:00","2019-03-30 08:00","2019-04-19 18:00","연속",null,null,null,201901020036]
[214,"경기","평택","청북평택#2 T/L","154kV 청북S/S #5M.Tr 증설용 GIS 설치공사","ㅇ #5M.Tr 증설설비(CB, #2BUS) 무부하 가압","2019-03-15 14:00","2019-03-16 18:00","2019-03-15 14:00","2019-03-16 18:00","연속",null,null,null,201812310047]
[215,"경기","평택","청북평택#2 T/L","154kV 청북S/S #5M.Tr 증설용 GIS 설치공사","ㅇ #5M.TR증설설비(#1BUS) 무부하 가압","2019-03-08 14:00","2019-03-09 18:00","2019-03-08 14:00","2019-03-09 18:00","연속",null,null,null,201812310046]
[216,"경기","평택","평택추팔#1 T/L","154kV 평택추팔 34-38 안전이격확보공사","지지물 교체 3기, 임시선로 2기, 인클로징 1기","2019-03-11 08:00","2019-03-14 18:00","2019-03-11 08:00","2019-03-14 18:00","연속",null,null,null,201901030083]
[217,"경기","평택","평택추팔#2 T/L","154kV 평택추팔 34-38 안전이격확보공사","지지물 교체 3기, 임시선로 2기, 인클로징 1기","2019-03-15 08:00","2019-03-18 18:00","2019-03-15 08:00","2019-03-18 18:00","연속",null,null,null,201901030084]
[218,"경기","평택","포승평택TP#1 T/L","포승S/S 포승-평택T/P#1T/L 보호반 대체","포승S/S 포승-평택T/P#1T/L 보호반 대체 / GIS 조작시험 / 평택T/P 포승-평택T/P#1T/L 보호반 대체","2019-03-25 10:00","2019-03-28 18:00","2019-03-25 10:00","2019-03-28 18:00","연속",null,null,null,201901100056]
[219,"강원","강릉","강릉영동TP T/L","154kV 강릉T/L No.7~7.1간 지장송전선로 지중화공사","154kV 강릉T/L No.7~7.1간 가선로 구성 - 가철탑 설치 2기, 철거 1기","2019-03-26 09:00","2019-03-29 18:00","2019-03-26 09:00","2019-03-29 18:00","연속",null,null,null,201901090012]
[220,"강원","강릉","동해영동TP T/L","154kV 강릉T/L No.7~7.1간 지장송전선로 지중화공사","154kV 강릉T/L No.7~7.1간 가선로 구성 - 가철탑 설치 2기, 철거 1기","2019-03-21 09:00","2019-03-25 18:00","2019-03-21 09:00","2019-03-25 18:00","연속",null,null,null,201901090009]
[221,"강원","강릉","주진평창#2 T/L","2019년 가공송전 순시점검 위탁공사","○ 154kV 주진평창T/L 초기점검 - 구간 : 154kV 주진평창#2T/L No.16~20","2019-03-12 08:00","2019-03-12 18:00","2019-03-12 08:00","2019-03-12 18:00","당일",null,null,null,201901100124]
[222,"강원","강릉","주진평창#1 T/L","2019 가공송전 순시점검 위탁공사","○ 154kV 주진평창T/L 초기점검 - 구간 : 154kV 주진평창 #1T/L No.16~20","2019-03-11 08:00","2019-03-11 18:00","2019-03-11 08:00","2019-03-11 18:00","당일",null,null,null,201901100122]
[223,"강원","동해","울진삼척GP#1 T/L","울진-삼척GP #1T/L 피뢰기 설치공사","울진-삼척GP #1T/L 피뢰기 설치공사","2019-03-18 09:00","2019-03-22 18:00","2019-03-20 09:00","2019-03-22 18:00","매일",null,null,null,201901090071]
[224,"강원","동해","이원태백 T/L","154kV 태원T/L 안전이격확보공사","철탑 인클로징공법 2기 : 96~97호","2019-03-05 08:00","2019-03-10 18:00","2019-03-05 08:00","2019-03-10 18:00","연속",null,null,null,201901090209,"O"]
[225,"강원","동해","이원도계 T/L","154kV 태원T/L 안전이격확보공사","철탑 인클로징공법 2기 : 96~97호","2019-03-11 08:00","2019-03-15 18:00","2019-03-11 08:00","2019-03-15 18:00","연속",null,null,null,201901090210]
[226,"강원","원주","홍천소양강HP T/L","154kV 소양t/L No.84~89간 안전이격 확보공사","철탑철거 4기, 신설 3기","2019-03-13 09:00","2019-03-15 18:00","2019-03-13 09:00","2019-03-15 18:00","연속",null,null,null,201901020021]
[227,"강원","직할","홍천남춘천 T/L","154kV 소양t/L No.84~89간 안전이격 확보공사","철탑철거 4기, 신설 3기","2019-03-10 08:00","2019-03-12 18:00","2019-03-10 08:00","2019-03-12 18:00","연속",null,null,null,201901020020]
[228,"강원","직할","춘천소양강HP T/L","19년 가공송전선로 순시점검 위탁공사","정밀점검","2019-03-25 09:00","2019-03-26 18:00","2019-03-25 09:00","2019-03-26 18:00","연속",null,null,null,201901160010]
[229,"강원","태백","동영월영월CC T/L","18~19 변전정비 총액공사","동영월-영월CC GIS 보통점검","2019-03-20 10:00","2019-03-20 18:00","2019-03-20 10:00","2019-03-20 18:00","당일",null,null,null,201901090068]
[230,"강원","태백","단양영월CC#1 T/L","18~19 변전정비 총액공사","단양-영월CC GIS 보통점검","2019-03-19 10:00","2019-03-19 18:00","2019-03-19 10:00","2019-03-19 18:00","당일",null,null,null,201901090066]
[231,"강원","태백","정선영월CC T/L","정선-영월CC T/L 피뢰기 설치공사","정선-영월CC T/L 피뢰기 설치공사","2019-03-11 09:00","2019-03-15 18:00","2019-03-04 09:00","2019-03-08 18:00","매일",null,null,null,201901090062]
[232,"강원","태백","단양영월CC#2 T/L","18~19 변전정비 총액공사","단양-영월CC GIS 보통점검","2019-03-21 10:00","2019-03-21 18:00","2019-03-21 10:00","2019-03-21 18:00","당일",null,null,null,201901090069]
[233,"강원","태백","영월_영월CC T/L","18~19년 변전정비 총액공사","영월-영월CC GIS 조작시험","2019-03-04 10:00","2019-03-04 18:00","2019-03-04 10:00","2019-03-04 18:00","당일",null,null,null,201901090060]
[234,"강원","태백","태백삼척GP#1 T/L","태백-삼척GP #1T/L 피뢰기 설치공사","태백-삼척GP #1T/L 피뢰기 설치공사","2019-03-25 09:00","2019-04-05 18:00","2019-03-11 09:00","2019-03-19 18:00","매일",null,null,null,201901090073]
[235,"강원","직할 ","화천H/P 154kV #1 BUS","18-19년 직할 변전정비 총액공사","#1M,Tr 및 #2M.Tr 1,2 DS 보통점검","2019-03-07 10:00","2019-03-07 13:00","2019-03-07 10:00","2019-03-07 13:00","당일"]
[236,"강원","직할 ","화천H/P 154kV #1 BUS","18-19년 직할 변전정비 총액공사","#1M,Tr 및 #2M.Tr 1,2 DS 보통점검","2019-03-07 13:00","2019-03-07 18:00","2019-03-07 13:00","2019-03-07 18:00","당일"]
[237,"충북","직할","신충주S/S 154kV #60 BUS","345kV 신충주S/S #4M.Tr 증설공사","345kV M.Tr 설치 345kV GIS CB 설치 154kV GIS 4CCT 설치 기기기초 및 기타 부대공사","2019-03-05 09:00","2019-03-14 18:00","2019-03-05 09:00","2019-03-14 18:00","연속",null,null,null,201901100062]
[238,"충북","직할","왕암가남#1 T/L","왕암S/S 154kV SW 증설공사(봉양전철)","증설 GIS 초기 가압 전원 확보 170kV GIS 50kA 1250A x 1CCT 설치","2019-03-06 09:00","2019-03-07 09:00","2019-03-06 09:00","2019-03-07 09:00","연속",null,null,null,201812050175]
[239,"충북","직할","왕암가남#2 T/L","왕암S/S 154kV SW 증설공사(봉양전철)","증설 GIS 초기 가압 전원 확보 170kV GIS 50kA 1250A x 1CCT 설치","2019-03-01 09:00","2019-03-02 09:00","2019-03-01 09:00","2019-03-02 09:00","연속",null,null,null,201812050173]
[240,"충북","직할","제천영월#1 T/L","2018~2019년 직할 송전정비회사 총액공사","154kV 단양-영월CCT/L No.1 불량애자 교체 안전조치","2019-03-19 10:00","2019-03-19 18:00","2019-03-19 10:00","2019-03-19 18:00","당일",null,null,null,201901090179]
[241,"충북","직할","제천영월#2 T/L","2018~2019년 직할 송전정비회사 총액공사","154kV 단양-영월CCT/L No.1 불량애자 교체 안전조치","2019-03-21 10:00","2019-03-21 18:00","2019-03-21 10:00","2019-03-21 18:00","당일",null,null,null,201901090178]
[242,"충북","청주","상주보은 T/L","154kV 상주T/L 안전이격거리 확보공사","철탑 2기 교체, 전력선 0.795km 교체 / 회선직결","2019-03-19 07:00","2019-04-14 19:00","2019-03-19 07:00","2019-04-14 19:00","연속",null,null,null,201901100275]
[243,"충북","청주","부강월산#1 T/L","2019년 청주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 부강-대청H/P T/L 정밀점검 병가구간 작업자 안전상 휴전","2019-03-13 09:00","2019-03-13 18:00","2019-03-13 09:00","2019-03-13 18:00","당일",null,null,null,201901110116,"O"]
[244,"충북","청주","부강신탄진 T/L","2019년 청주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 부강-신탄진/L 부강S/S~신탄진S/S 정밀점검","2019-03-04 09:00","2019-03-12 18:00","2019-03-04 09:00","2019-03-12 18:00","매일",null,null,null,201901100176]
[245,"충북","청주","부강월산#2 T/L","2019년 청주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 부강-신탄진 T/L 정밀점검 병가구간 작업자 안전상 휴전","2019-03-04 09:00","2019-03-04 18:00","2019-03-04 09:00","2019-03-04 18:00","당일",null,null,null,201901110118]
[246,"충북","청주","부강대청HP T/L","2019년 청주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 부강-대청H/P T/L 부강S/S~대청H/P 정밀점검","2019-03-13 09:00","2019-03-15 18:00","2019-03-13 09:00","2019-03-15 18:00","매일",null,null,null,201901100178]
[247,"충북","청주","상주영동 T/L","154kV 상주T/L 안전이격거리 확보공사","철탑 2기 교체, 전력선 0.795km 교체 / 회선직결","2019-03-19 07:00","2019-04-14 19:00","2019-03-19 07:00","2019-04-14 19:00","연속",null,null,null,201901100276]
[248,"충북","청주","오송북청주#1 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","154kV 오송-북청주#1T/L - 불량애자교체 : No.9,38 - 아킹혼철거 : No.20~28,31(10기)","2019-03-14 07:30","2019-03-18 19:00","2019-03-14 07:30","2019-03-18 19:00","연속",null,null,null,201901100265]
[249,"충북","청주","신진천오창#1 T/L","18~19년 청주전력 변전협력회사 총액공사","신진천오창#1T/L 송전선로보호반 대체","2019-03-30 09:30","2019-03-31 18:00","2019-03-30 09:30","2019-03-31 18:00","연속",null,null,null,201901080142]
[250,"충북","청주","신진천오창#2 T/L","18~19년 청주전력 변전협력회사 총액공사","신진천오창#2T/L 송전선로보호반 대체","2019-03-23 09:30","2019-03-24 18:00","2019-03-23 09:30","2019-03-24 18:00","연속",null,null,null,201901080140]
[251,"충북","청주","청원청주#1 T/L","청주S/S 154kV GIS화 공사","옥외철구 GIS화 공사","2019-03-01 09:00","2019-03-05 18:00","2019-03-16 09:00","2019-03-20 18:00","연속",null,null,null,201901160031]
[252,"충북","청주","청원청주#3 T/L","청주S/S 154kV GIS화 공사","옥외철구 GIS화 공사","2019-03-01 09:00","2019-03-05 18:00","2019-03-16 09:00","2019-03-20 18:00","연속",null,null,null,201901160032]
[253,"충북","충주","왕암충주 T/L","2018-2019년 송전정비회사 총액공사","미소균열 압축인류클램프 교체 (No.105)","2019-03-28 08:00","2019-03-28 18:00","2019-03-28 08:00","2019-03-28 18:00","당일",null,null,null,201901150005]
[254,"충북","청주","청주S/S 154kV #2 BUS","청주S/S 154kV GIS화 공사","옥외철구 GIS화 공사","2019-03-06 09:00","2019-03-08 18:00","2019-03-21 09:00","2019-03-23 18:00","연속"]
[255,"대전충남","아산","아산온양#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","[송전] 154kV 신온양-석곡 등 10개T/L 피뢰기설치공사 가. 휴전선로 : 154kV 아산-온양 #2T/L 나. 공사내용 : 피뢰기설치 58기 (No.1~57), 174set","2019-03-02 07:00","2019-03-03 18:00","2019-03-02 07:00","2019-03-03 18:00","매일",null,null,null,201901090087]
[256,"대전충남","세종","서세종조치원 T/L","[송전]154kV 조치원-월산T/L 안전이격확보공사","[송전]154kV 조치원-월산T/L No.13~18 안전이격확보공사","2019-03-03 07:00","2019-03-03 13:00","2019-03-03 07:00","2019-03-03 13:00","당일",null,null,null,201901240001]
[257,"대전충남","세종","조치원월산 T/L","[송전]154kV 조치원-월산T/L 안전이격확보공사","[송전]154kV 조치원-월산T/L No.13~18 안전이격확보공사","2019-03-03 09:00","2019-03-06 18:00","2019-03-03 09:00","2019-03-06 18:00","연속",null,null,null,201901100221]
[258,"대전충남","서산","서산태안 T/L","154kV서산-대산T/L 피뢰기 설치공사","154kV서산-대산T/L 피뢰기 설치공사 안전이격 확보","2019-03-04 07:30","2019-03-05 18:00","2019-03-04 07:30","2019-03-05 18:00","매일",null,null,null,201901090222]
[259,"대전충남","서산","태안T/P 154kV #1 BUS","태안화력 154kV 노후사용 GIS 대체 공사","태안화력 154kV 노후사용 GIS 대체 공사","2019-03-04 09:00","2019-03-06 18:00","2019-03-06 09:00","2019-03-08 18:00","연속",null,null,null,201901100033]
[260,"대전충남","서산","태안T/P 4호기 S/U Tr 1차 CB","태안화력 154kV 노후사용 GIS 대체 공사","태안화력 154kV 노후사용 GIS 대체 공사","2019-03-04 09:00","2019-03-22 18:00","2019-03-04 09:00","2019-03-22 18:00","연속",null,null,null,201901100027]
[261,"대전충남","아산","장재천안#2 T/L","154kV 장재-천안 등 4개T/L 일진제 PMJ 교체공사","일진제 R-Type 조립식접속함(PMJ) 교체","2019-03-04 09:00","2019-03-10 18:00","2019-03-04 09:00","2019-03-10 18:00","연속",null,null,null,201812130057]
[262,"대전충남","서산","태안태안화력 T/L","태안화력 154kV 노후사용 GIS 대체 공사","태안화력 154kV 노후사용 GIS 대체 공사","2019-03-06 15:00","2019-03-07 18:00","2019-03-06 15:00","2019-03-07 18:00","연속",null,null,null,201901100039]
[263,"대전충남","서산","해미홍성 T/L","154kV 해미분기T/L 정밀점검","154kV해미분기(#해미-홍성T/L) : No.1~30 정밀점검","2019-03-07 08:00","2019-03-08 18:00","2019-03-07 08:00","2019-03-08 18:00","매일",null,null,null,201901090206]
[264,"대전충남","서산","태안T/P 154kV #2 BUS","태안화력 154kV 노후사용 GIS 대체 공사","태안화력 154kV 노후사용 GIS 대체 공사","2019-03-07 09:00","2019-03-12 18:00","2019-03-09 09:00","2019-03-14 18:00","연속",null,null,null,201901100036]
[265,"대전충남","세종","서세종조치원 T/L","[송전]154kV 조치원-월산T/L 안전이격확보공사","[송전]154kV 조치원-월산T/L No.13~18 안전이격확보공사","2019-03-07 09:00","2019-03-27 18:00","2019-03-07 09:00","2019-03-27 18:00","연속",null,null,null,201901100225]
[266,"대전충남","직할","신탄진대청HP T/L","2019년 청주 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 신탄진-대청H/P T/L 신탄진S/S~대청H/P 정밀점검 (주말제외)","2019-03-07 09:00","2019-03-12 18:00","2019-03-07 09:00","2019-03-12 18:00","매일",null,null,null,201901110111]
[267,"대전충남","아산","아산온양#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","[송전] 154kV 신온양-석곡 등 10개T/L 피뢰기설치공사 가. 휴전선로 : 154kV 아산-온양 #2T/L 나. 공사내용 : 피뢰기설치 58기 (No.1~57), 174set","2019-03-09 07:00","2019-03-10 18:00","2019-03-09 07:00","2019-03-10 18:00","매일",null,null,null,201901090091]
[268,"대전충남","대전","신계룡은진#2 T/L","[송전] 154kV 신계룡-은진T/L 안전이격거리확보공사","[송전] 154kV 신계룡-은진T/L 철탑 철거/설치 및 전선 교체","2019-03-11 07:00","2019-03-30 18:00","2019-03-11 07:00","2019-03-30 18:00","연속",null,null,null,201901090264]
[269,"대전충남","대전","신계룡은진#1 T/L","[송전] 154kV 신계룡-은진T/L 안전이격거리확보공사","[송전] 154kV 신계룡-은진T/L 철탑 철거/설치 및 전선 교체","2019-03-11 07:00","2019-03-30 18:00","2019-03-11 07:00","2019-03-30 18:00","연속",null,null,null,201901090263]
[270,"대전충남","서산","서산해미 T/L","154kV 해미분기T/L 정밀점검","154kV해미분기(#서산-해미T/L) : No.1~30 정밀점검","2019-03-11 08:00","2019-03-12 18:00","2019-03-11 08:00","2019-03-12 18:00","매일",null,null,null,201901090207]
[271,"대전충남","아산","둔포추팔#1 T/L","둔포S/S 154kV 둔포-추팔#1,2T/L CB 개페타임 측정","둔포S/S 154kV 둔포-추팔#1,2T/L CB 개페타임 측정","2019-03-12 09:00","2019-03-12 13:00","2019-03-12 09:00","2019-03-12 13:00","당일",null,null,null,201901110026]
[272,"대전충남","아산","둔포추팔#2 T/L","둔포S/S 154kV 둔포-추팔#1,2T/L CB 개페타임 측정","둔포S/S 154kV 둔포-추팔#1,2T/L CB 개페타임 측정","2019-03-12 13:00","2019-03-12 18:00","2019-03-12 13:00","2019-03-12 18:00","당일",null,null,null,201901110027]
[273,"대전충남","서산","태안태안화력 T/L","태안화력 154kV 노후사용 GIS 대체 공사","태안화력 154kV 노후사용 GIS 대체 공사","2019-03-12 15:00","2019-03-13 09:00","2019-03-11 15:00","2019-03-12 09:00","연속",null,null,null,201901100040]
[274,"대전충남","서산","서산태안화력 T/L","154kV태안화력T/L 전력선 교체공사","154kV서산-태안화력T/L 전력선 교체공사 No.2~6,8~10,30~33 36~37,49~51,51~51.1","2019-03-13 09:00","2019-03-20 18:00","2019-03-13 09:00","2019-03-20 18:00","연속",null,null,null,201901090219]
[275,"대전충남","서산","태안T/P 154kV #1 BUS","태안화력 154kV 노후사용 GIS 대체 공사","태안화력 154kV 노후사용 GIS 대체 공사","2019-03-13 09:00","2019-03-22 18:00","2019-03-13 09:00","2019-03-22 18:00","연속",null,null,null,201901100045]
[276,"대전충남","아산","서천안탕정#1 T/L","탕정S/S 154kV 서천안-탕정#1,2T/L CB 개페타임 측정","탕정S/S 154kV 서천안-탕정#1,2T/L CB 개페타임 측정","2019-03-13 09:00","2019-03-13 13:00","2019-03-10 09:00","2019-03-10 13:00","당일",null,null,null,201901110028]
[277,"대전충남","아산","서천안탕정#2 T/L","탕정S/S 154kV 서천안-탕정#1,2T/L CB 개페타임 측정","탕정S/S 154kV 서천안-탕정#1,2T/L CB 개페타임 측정","2019-03-13 13:00","2019-03-13 18:00","2019-03-10 13:00","2019-03-10 18:00","당일",null,null,null,201901110030]
[278,"대전충남","아산","인주탕정#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","[안전이격]154kV 아산-인주#1T/L","2019-03-16 07:00","2019-03-17 18:00","2019-03-16 07:00","2019-03-17 18:00","매일",null,null,null,201901110119]
[279,"대전충남","아산","아산인주#1 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","[송전] 154kV 신온양-석곡 등 10개T/L 피뢰기설치공사 가. 휴전선로 : 154kV 아산-인주 #1T/L 나. 공사내용 : 피뢰기설치 35기 (No.1~35), 105set","2019-03-16 07:00","2019-03-17 18:00","2019-03-16 07:00","2019-03-17 18:00","매일",null,null,null,201901090081]
[280,"대전충남","세종","신풍공주#1 T/L","[변전]YPP제 보호계전기 성능개선 시행","○ YPP제 보호계전기 성능개선 시행 ○ 송운(계통)-1533(18.10.15) 관련","2019-03-18 09:30","2019-03-18 18:00","2019-03-18 09:30","2019-03-18 18:00","당일",null,null,null,201901080067]
[281,"대전충남","세종","신풍공주#2 T/L","[변전]YPP제 보호계전기 성능개선 시행","○ YPP제 보호계전기 성능개선 시행 ○ 송운(계통)-1533(18.10.15) 관련","2019-03-19 09:30","2019-03-19 18:00","2019-03-19 09:30","2019-03-19 18:00","당일",null,null,null,201901080079]
[282,"대전충남","서산","태안태안화력 T/L","154kV태안화력T/L 전력선 교체공사","154kV태안화력T/L 전력선 교체공사 No.2~6,8~10,30~33 36~37,49~51,51~51.1","2019-03-21 07:00","2019-03-28 18:00","2019-03-21 07:00","2019-03-28 18:00","연속",null,null,null,201901090220]
[283,"대전충남","아산","아산온양#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","[송전] 154kV 신온양-석곡 등 10개T/L 피뢰기설치공사 가. 휴전선로 : 154kV 아산-온양 #2T/L 나. 공사내용 : 피뢰기설치 58기 (No.1~57), 174set","2019-03-23 07:00","2019-03-23 18:00","2019-03-23 07:00","2019-03-23 18:00","당일",null,null,null,201901110128]
[284,"대전충남","아산","온양풍세#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","[안전이격]154kV 아산-온양#2T/L","2019-03-23 07:00","2019-03-23 18:00","2019-03-23 07:00","2019-03-23 18:00","당일",null,null,null,201901110122]
[285,"대전충남","아산","아산합덕#1 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-03-25 07:00","2019-04-03 18:00","2019-03-25 07:00","2019-04-03 18:00","연속",null,null,null,201901090238]
[286,"대전충남","아산","한샘둔포#1 T/L","둔포S/S 154kV 한샘-둔포#1T/L GIS 보통점검","둔포S/S 154kV 한샘-둔포#1T/L GIS 보통점검","2019-03-26 09:00","2019-03-26 18:00","2019-03-26 09:00","2019-03-26 18:00","당일",null,null,null,201901110040]
[287,"대전충남","아산","한샘둔포#2 T/L","둔포S/S 154kV 한샘-둔포#2T/L GIS 보통점검","둔포S/S 154kV 한샘-둔포#2T/L GIS 보통점검","2019-03-27 09:00","2019-03-27 18:00","2019-03-27 09:00","2019-03-27 18:00","당일",null,null,null,201901110042]
[288,"대전충남","세종","조치원월산 T/L","[송전]154kV 조치원-월산T/L 안전이격확보공사","[송전]154kV 조치원-월산T/L No.13~18 안전이격확보공사","2019-03-28 09:00","2019-04-03 18:00","2019-03-28 09:00","2019-04-03 18:00","연속",null,null,null,201901100223]
[289,"전북","군산","군공군산CC#1 T/L","선로측 접지개폐기 보수공사 시행","선로측 접지개폐기 보수공사","2019-03-04 09:00","2019-03-05 18:00","2019-03-04 09:00","2019-03-05 18:00","연속",null,null,null,201901040075]
[290,"전북","군산","군산영등#1 T/L","군산-영등 1TL 보호배전반 성능개선","가보제 송전선로 보호반 성능개선","2019-03-20 09:00","2019-03-20 18:00","2019-03-20 09:00","2019-03-20 18:00","당일",null,null,null,201812310034]
[291,"전북","군산","군산동군산#2 T/L","군산동군산T/L 노후금구류교체공사","-금구류교체 : 33~37","2019-03-13 07:00","2019-03-13 18:00","2019-03-13 07:00","2019-03-13 18:00","당일",null,null,null,201901070225]
[292,"전북","군산","군산동군산#1 T/L","군산동군산T/L 노후금구류교체공사","-금구류교체 : 33~37","2019-03-12 07:00","2019-03-12 18:00","2019-03-12 07:00","2019-03-12 18:00","당일",null,null,null,201901070224]
[293,"전북","군산","군장S/S 한화에너지#1T/L GIS","군장- 한화에너지#1 TL 송전선로 보호반 성능개선","군장- 한화에너지#1 TL 송전선로 보호반 성능개선","2019-03-04 09:00","2019-03-04 18:00","2019-03-04 09:00","2019-03-04 18:00","당일",null,null,null,201812310041]
[294,"전북","군산","팔봉두마#2 T/L","팔봉두마T/L 국산애자교체공사","- 국산애자(지지애자)교체 : 2~7","2019-03-09 07:00","2019-03-09 18:00","2019-03-09 07:00","2019-03-09 18:00","당일",null,null,null,201901070228]
[295,"전북","군산","팔봉두마#1 T/L","팔봉두마T/L 국산애자교체공사","- 국산애자(지지애자)교체 : 2~7","2019-03-09 07:00","2019-03-09 18:00","2019-03-09 07:00","2019-03-09 18:00","당일",null,null,null,201901070227]
[296,"전북","김제","정주고창#2 T/L","154kV 정주-고창 안전이격확보공사","정주-고창#1T/L 철탑 이설 및 전력선 교체 철탑교체 : No.69,70,72호 전력선 교체 : No.67~74호","2019-03-18 08:00","2019-03-25 18:00","2019-03-18 08:00","2019-03-25 18:00","연속",null,null,null,201811120044]
[297,"전북","김제","김제칠보HP T/L","154kV 고창-홍농 등7개T/L 피뢰기 설치공사","154kV 김제-칠보수력T/L 82기, 피뢰기 246Set 설치","2019-03-08 08:00","2019-03-17 18:00","2019-03-08 08:00","2019-03-17 18:00","매일",null,null,null,201812210120]
[298,"전북","김제","백산김제#1 T/L","154kV 고창-홍농 등7개T/L 피뢰기 설치공사","작업없음.(154kV 김제-칠보수력T/L 피뢰기 설치 병가철탑 휴전)","2019-03-08 08:00","2019-03-17 18:00","2019-03-08 08:00","2019-03-17 18:00","매일",null,null,null,201901150018]
[299,"전북","김제","신김제남전주#2 T/L","남전주S/S #4M.Tr 1차 GIS 교체공사","남전주S/S #4M.Tr 1차 GIS 교체공사","2019-03-25 09:00","2019-04-05 18:00","2019-03-25 09:00","2019-04-05 18:00","매일",null,null,null,201901180086]
[300,"전북","김제","정주고창#1 T/L","정주S/S 170kV GIS 설치공사","정주S/S 정주-고창#1T/L 차단기 이설 고창S/S 송전선로 보호배전반 교체","2019-03-26 09:00","2019-04-02 18:00","2019-03-26 09:00","2019-04-02 18:00","연속",null,null,null,201811150188]
[301,"전북","직할","무주진안 T/L","154kV 무주-진안T/L 정밀점검","154kV 무주-진안T/L No.104-175호 정밀점검(점검 수량 71기)","2019-03-04 09:00","2019-03-12 18:00","2019-03-04 09:00","2019-03-12 18:00","매일",null,null,null,201901150012]
[302,"전북","직할","무주용담수력 T/L","154kV 무주-용담수력T/L 정밀점검","154kV 무주-용담수력T/L No.51-103호 정밀점검(점검 수량 53기)","2019-03-13 09:00","2019-03-15 18:00","취소","취소","매일",null,null,null,201901150013]
[303,"전북","직할","북전주용담수력 T/L","154kV 북전주-용담수력T/L 정밀점검","154kV 북전주-용담수력T/L 송전선로 정밀점검","2019-03-18 07:00","2019-03-19 18:00","취소","취소","매일",null,null,null,201901180057]
[304,"전북","직할","북전주진안 T/L","154kV 북전주-진안T/L 정밀점검","154kV 북전주-진안T/L No.14-175호 정밀점검(점검 수량 162기)","2019-03-20 09:00","2019-04-05 18:00","2019-03-20 09:00","2019-04-05 18:00","매일",null,null,null,201901150017]
[305,"광주전남","강진","신강진강진#2 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,신강진,남창S/S 보호배전반 대체, 시험 강진-남창#2T/L, 신강진-강진#2T/L 직결","2019-03-04 09:00","2019-03-15 18:00","2019-03-04 09:00","2019-03-15 18:00","연속",null,null,null,201901210049]
[306,"광주전남","강진","강진남창#2 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,신강진,남창S/S 보호배전반 대체, 시험 강진-남창#2T/L, 신강진-강진#2T/L 직결","2019-03-04 09:00","2019-03-15 18:00","2019-03-04 09:00","2019-03-15 18:00","연속",null,null,null,201901210048]
[307,"광주전남","강진","강진남창#1 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,남창S/S 보호배전반 대체, 시험, LA, CVT 이설 송전선로 철거 및 가선, 선로접속, 모선POST 철거 OPGW 설치 및 시험","2019-03-18 09:00","2019-03-29 18:00","2019-03-18 09:00","2019-03-29 18:00","연속",null,null,null,201901210053]
[308,"광주전남","강진","강진남창#2 T/L","남창S/S 154kV 강진-남창#2T/L PT 하자점검","- 남창S/S 154kV 강진-남창#2T/L PT 하자점검 - 남창S/S 154kV 강진-남창#2T/L LA 초기점검","2019-03-04 09:00","2019-03-04 18:00","2019-03-04 09:00","2019-03-04 18:00","당일",null,null,null,201901070343]
[309,"광주전남","강진","신강진대불#2 T/L","대불S/S 154kV 신강진-대불#2T/L LA 보통점검","- 대불S/S 154kV 신강진-대불#2T/L LA 보통점검","2019-03-06 09:00","2019-03-06 18:00","2019-03-06 09:00","2019-03-06 18:00","당일",null,null,null,201901070352]
[310,"광주전남","강진","신강진대불#1 T/L","대불S/S 154kV 신강진-대불#1T/L LA 보통점검","- 대불S/S 154kV 신강진-대불#1T/L LA 보통점검","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901070349]
[311,"광주전남","강진","진도진도CS#2 T/L","154kV 보호배전반 계전기 제작사 교체","154kV 보호배전반 계전기 제작사 교체","2019-03-05 09:00","2019-03-05 18:00","2019-03-03 09:00","2019-03-03 18:00","당일",null,null,null,201901140195]
[312,"광주전남","강진","진도진도CS#1 T/L","154kV 보호배전반 계전기 제작사 교체","154kV 보호배전반 계전기 제작사 교체","2019-03-04 09:00","2019-03-04 18:00","2019-03-02 09:00","2019-03-02 18:00","당일",null,null,null,201901140193]
[313,"광주전남","강진","해남C/S #2 C.Tr 1차 CB(신규)","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2019-03-01 09:00","2019-08-31 18:00","2019-03-01 09:00","2019-08-31 18:00","연속",null,null,null,201901170112]
[314,"광주전남","강진","해남C/S 154kV #1 HPF CB","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2019-03-01 09:00","2019-08-31 18:00","2019-03-01 09:00","2019-08-31 18:00","연속",null,null,null,201901170108]
[315,"광주전남","강진","제주1연계선#2 T/L CB","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2019-03-01 09:00","2019-08-31 18:00","2019-03-01 09:00","2019-08-31 18:00","연속",null,null,null,201901170121]
[316,"광주전남","강진","해남C/S 154kV #1 DTF CB","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2019-03-01 09:00","2019-08-31 18:00","2019-03-01 09:00","2019-08-31 18:00","연속",null,null,null,201901170109]
[317,"광주전남","강진","해남C/S #1 C.Tr 1차 CB","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2019-03-01 09:00","2019-08-31 18:00","2019-03-01 09:00","2019-08-31 18:00","연속",null,null,null,201901170111]
[318,"광주전남","강진","해남C/S 154kV #2 Sh.C CB(신규)","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2019-03-01 09:00","2019-08-31 18:00","2019-03-01 09:00","2019-08-31 18:00","연속",null,null,null,201901170113]
[319,"광주전남","강진","해남C/S 154kV #2 HPF CB(신규)","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2019-03-01 09:00","2019-08-31 18:00","2019-03-01 09:00","2019-08-31 18:00","연속",null,null,null,201901170114]
[320,"광주전남","강진","해남C/S 154kV #2 DTF CB(신규)","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2019-03-01 09:00","2019-08-31 18:00","2019-03-01 09:00","2019-08-31 18:00","연속",null,null,null,201901170115]
[321,"광주전남","강진","해남C/S 154kV #1 Sh.C CB","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2019-03-01 09:00","2019-08-31 18:00","2019-03-01 09:00","2019-08-31 18:00","연속",null,null,null,201901170110]
[322,"광주전남","강진","제주1연계선#1 T/L CB","#1HVDC 노후변환설비 교체사업","밸브, 냉각설비, 제어기, 관련 제어케이블 교체 및 시운전 C.Tr, 필터, VBE 등 PNL 교체","2019-03-01 09:00","2019-08-31 18:00","2019-03-01 09:00","2019-08-31 18:00","연속",null,null,null,201901170120]
[323,"광주전남","광주","신광주계림#2 T/L","154kV 신광주-계림#2T/L(변전총액공사)","154kV 신광주-계림#2T/L LA 교체","2019-03-07 09:00","2019-03-07 18:00","취소","취소","당일",null,null,null,201901150089]
[324,"광주전남","목포","엄다S/S 나주-엄다#2T/L GIS","`19년 변전협력회사 총액공사","`19년 변전협력회사 총액공사 - 나주-엄다#2T/L GIS 보통점검","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901150210]
[325,"광주전남","목포","장성영광#1 T/L","154kV장성-영광T/L전선접속개소전선교체공사","전선 및 금구류 교체 : No.125~160호","2019-03-06 07:00","2019-03-15 18:00","2019-03-03 07:00","2019-03-13 18:00","연속",null,null,null,201901140005]
[326,"광주전남","목포","장성영광#2 T/L","154kV장성-영광T/L전선접속개소전선교체공사","전선 및 금구류 교체 : No.125~160호","2019-03-27 07:00","2019-04-03 18:00","2019-03-21 07:00","2019-03-27 18:00","연속",null,null,null,201901140006]
[327,"광주전남","목포","고창영광 T/L","154kV 장성-영광T/L전선접속개소전선교체공사","장성-영광#2T/L 전선교체공사 관련 4회선 구간 안전이격거리 확보차","2019-03-27 07:00","2019-04-02 18:00","2019-03-21 07:00","2019-04-01 18:00","연속",null,null,null,201901140007]
[328,"광주전남","목포","고창홍농 T/L","345kV 신김제-한빛NP 등 4개T/L 지장송전선로 이설공사","154kV 홍농분기T/L 51, 52호 철탑이설 - 51, 52호 철탑 교체 및 46-52호 구간 전력선 교체","2019-03-17 09:00","2019-03-26 18:00","2019-03-14 09:00","2019-03-20 18:00","연속",null,null,null,201812180080]
[329,"광주전남","목포","영광홍농 T/L","345kV 신김제-한빛NP 등 4개T/L 지장송전선로 이설공사","154kV 홍농분기T/L 51, 52호 철탑이설 - 51, 52호 철탑 교체 및 46-52호 구간 전력선 교체","2019-03-07 09:00","2019-03-16 18:00","2019-03-04 09:00","2019-03-13 18:00","연속",null,null,null,201812180079]
[330,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌T/L 안전이격확보공사","공 사 개 요 가. 작업구간 : 154kV 순천-율촌T/L No.57~65호 나. 작업내용 ○ 154kV 순천-율촌T/L 철탑상향 : 2기 - 61호(15 → 42m) : 27m 상향 - 63호(17 → 30m) : 13m 상향 ※ 관형지지물 활용 선하지 내 철탑이설","2019-03-30 07:00","2019-03-31 18:00","취소","취소","연속",null,null,null,201901180007]
[331,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌T/L 안전이격확보공사","공 사 개 요 가. 작업구간 : 154kV 순천-율촌T/L No.57~65호 나. 작업내용 ○ 154kV 순천-율촌T/L 철탑상향 : 2기 - 61호(15 → 42m) : 27m 상향 - 63호(17 → 30m) : 13m 상향 ※ 관형지지물 활용 선하지 내 철탑이설","2019-03-30 07:00","2019-03-31 18:00","취소","취소","연속",null,null,null,201901180005]
[332,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌T/L 지중화공사","가. 공사구간 : 순천S/S ~ M/H#1, M/H#8 나. 휴전선로 : 154kV 순천-율촌#1T/L 다. 작업내용 - 154kV XLPE 2000SQ 케이블 포설 및 접속 - 접속 : EBG 1개소, 중간접속 1개소, EB-A 1개소","2019-03-02 07:00","2019-03-24 18:00","2019-03-08 07:00","2019-04-01 18:00","연속",null,null,null,201901030100]
[333,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌T/L 지중화공사","가. 공사구간 : 순천S/S ~ M/H#1, M/H#8 나. 휴전선로 : 154kV 순천-율촌#2T/L 다. 작업내용 - 154kV XLPE 2000SQ 케이블 포설 및 접속 - 접속 : EBG 1개소, 중간접속 1개소, EB-A 1개소","2019-03-02 07:00","2019-03-24 18:00","2019-03-08 07:00","2019-04-01 18:00","연속",null,null,null,201901030101]
[334,"광주전남","순천","승주S/S 154kV #2 BUS","승주 #3M.Tr 증설 사업","승주 #3M.Tr 170kV GIS 설치 - #2BUS DS 설치","2019-03-25 09:00","2019-03-29 18:00","2019-03-25 09:00","2019-03-29 18:00","연속",null,null,null,201901150127]
[335,"광주전남","순천","승주S/S 154kV #1 BUS","승주 #3M.Tr 증설 사업","승주 #3M.Tr 170kV GIS 설치 - #1BUS DS 설치","2019-03-19 09:00","2019-03-22 18:00","2019-03-19 09:00","2019-03-22 18:00","연속",null,null,null,201901150126]
[336,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성 #1T/L(자기애관 교체공사)","○ 154kV 여수TP-용성 #1T/L 자기애관을 폴리머애관으로 교체(6대)","2019-03-29 07:00","2019-03-30 18:00","2019-03-06 07:00","2019-03-07 18:00","연속",null,null,null,201901040090]
[337,"광주전남","순천","용성여수산단#2 T/L","154kV 용성여수산단#2T/L(전선접속개소해소공사)","전력선 교체 - 7호~10호, 13~14호","2019-03-25 00:07","2019-03-26 18:00","2019-03-04 07:00","2019-03-05 18:00","연속",null,null,null,201901100271]
[338,"광주전남","순천","여천호남TP#1 T/L","154kV 여천-호남T/P #1T/L 자기애관 교체공사","○ 154kV 여천-호남T/P #1T/L 자기애관을 폴리머애관으로 교체(3대)","2019-03-27 07:00","2019-03-28 18:00","취소","취소","연속",null,null,null,201901040088]
[339,"광주전남","직할","나주영암#1 T/L","154kV 나주S/S 옥내화 인출지중화 공사","변전 : 보호반대체, 통신, 계통시험, 무부하, 사용전검사 송전 : 송전선로 가선 및 LA 설치, EBA 선로접속","2019-03-04 06:00","2019-03-13 18:00","2019-03-04 06:00","2019-03-13 18:00","연속",null,null,null,201901220094]
[340,"광주전남","직할","나주평동#2 T/L","154kV 나주S/S 옥내화 인출지중화 공사","변전 : 보호반대체, 통신, 계통시험 송전 : 송전선로 가선 및 LA 설치, EBA 선로접속 통신 : OPGW 설치 및 시험","2019-03-04 06:00","2019-03-13 18:00","2019-03-04 06:00","2019-03-13 18:00","연속",null,null,null,201901220095]
[341,"광주전남","직할","나주영암#2 T/L","154kV 나주S/S 옥내화 인출지중화 공사","변전 : 보호반대체, 통신, 계통시험 송전 : 송전선로 가선 및 LA 설치, EBA 선로접속","2019-03-15 06:00","2019-03-22 18:00","2019-03-15 06:00","2019-03-22 18:00","연속",null,null,null,201901220096]
[342,"광주전남","직할","나주엄다#1 T/L","154kV 나주S/S 옥내화 인출지중화 공사","변전 : 보호반대체, 통신, 계통시험 송전 : 송전선로 가선 및 LA 설치, EBA 선로접속","2019-03-25 06:00","2019-04-01 18:00","2019-03-25 06:00","2019-04-01 18:00","연속",null,null,null,201901220097]
[343,"광주전남","직할","나주영암#2 T/L","154kV 나주S/S 옥내화 인출지중화 공사","병행선로 안전이격","2019-03-31 06:00","2019-03-31 18:00","2019-03-31 06:00","2019-03-31 18:00","당일",null,null,null,201901220098]
[344,"광주전남","직할","신화순나주#2 T/L","154kV 나주S/S 옥내화 인출지중화 공사","병행선로 안전이격","2019-03-31 06:00","2019-04-01 18:00","2019-03-30 06:00","2019-03-31 18:00","연속",null,null,null,201901220102]
[345,"광주전남","직할","하남장성#1 T/L","2019년도 가공송전선로 순시점검 위탁공사","154kV 하남-장성#1T/L 정밀점검","2019-03-25 08:00","2019-03-29 18:00","취소","취소","매일",null,null,null,201901210059]
[346,"광주전남","직할","하남장성#2 T/L","2019년도 가공송전선로 순시점검 위탁공사","154kV 하남-장성#2T/L 정밀점검","2019-03-11 08:00","2019-03-15 18:00","취소","취소","매일",null,null,null,201901210058]
[347,"대구","경산","청통하양#2 T/L","154kV 와촌E/C 건설공사","170kV GIS * 10CCT, 154kV M.Tr * 2Bank, 25.8kV SIS * 10CCT 설치","2019-03-18 09:00","2019-03-29 18:00","2019-03-18 09:00","2019-03-29 18:00","연속",null,null,null,201812130008]
[348,"대구","경산","청통하양#1 T/L","154kV 와촌E/C 건설공사","170kV GIS * 10CCT, 154kV M.Tr * 2Bank, 25.8kV SIS * 10CCT 설치","2019-03-18 09:00","2019-03-29 18:00","2019-03-18 09:00","2019-03-29 18:00","연속",null,null,null,201812130007]
[349,"대구","달성","다산강창#1 T/L","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사","2019-03-04 09:00","2019-03-05 18:00","취소","취소","연속",null,null,null,201901070104]
[350,"대구","달성","다산강창#2 T/L","154kV 고령-다산 등 17개T/L 피뢰기설치공사","피뢰기 설치","2019-03-09 07:00","2019-03-09 18:00","2019-03-09 07:00","2019-03-09 18:00","당일",null,null,null,201901080095]
[351,"대구","달성","강창성서#2 T/L","154kV 고령-다산 등 17개T/L 피뢰기설치공사","피뢰기 설치","2019-03-09 07:00","2019-03-09 18:00","2019-03-09 07:00","2019-03-09 18:00","당일",null,null,null,201901080096]
[352,"대구","달성","고령S/S 154kV #65 BUS","345kV 고령S/S #1M.Tr 증설공사","345kV 고령S/S #1M.Tr 증설공사","2019-03-24 18:00","2019-03-25 18:00","2019-03-24 18:00","2019-03-25 18:00","연속",null,null,null,201901100210]
[353,"대구","달성","고령쌍림#2 T/L","154kV 고령-서구지T/L SW증설공사","154kV 고령-서구지T/L SW증설공사","2019-03-07 18:00","2019-03-08 18:00","2019-03-07 18:00","2019-03-08 18:00","연속",null,null,null,201812130029]
[354,"대구","달성","고령쌍림#1 T/L","154kV 고령-다산 등 17개T/L 피뢰기 설치공사","안전확보","2019-03-04 07:00","2019-03-04 18:00","2019-03-04 07:00","2019-03-04 18:00","당일",null,null,null,201901080082,"O"]
[355,"대구","달성","고령다산#1 T/L","154kV 고령-다산 등 17개T/L 피뢰기 설치공사","피뢰기 설치","2019-03-04 07:00","2019-03-07 18:00","2019-03-04 07:00","2019-03-07 18:00","연속",null,null,null,201901080080]
[356,"대구","달성","고령S/S 154kV #65 BUS","154kV 고령-서구지T/L SW증설공사","154kV 고령-서구지T/L SW증설공사","2019-03-04 09:00","2019-03-08 18:00","2019-03-04 09:00","2019-03-08 18:00","연속",null,null,null,201812130032]
[357,"대구","달성","논공달성#1 T/L","154kV 고령-다산 등 17개T/L 피뢰기설치공사","피뢰기 설치","2019-03-11 07:00","2019-03-13 18:00","2019-03-11 07:00","2019-03-13 18:00","연속",null,null,null,201901080086]
[358,"대구","달성","고령쌍림#2 T/L","달성전력지사 정밀점검공사(TEST선로)","달성전력지사 정밀점검공사(TEST선로)","2019-03-26 13:00","2019-03-28 18:00","취소","취소","매일",null,null,null,201901070121]
[359,"대구","달성","고령쌍림#2 T/L","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사","2019-03-18 09:00","2019-03-21 18:00","취소","취소","연속",null,null,null,201901070114]
[360,"대구","직할","노변효목#1 T/L","차단기 개폐타임 측정","차단기 개폐타임 측정","2019-03-26 09:30","2019-03-26 11:00","2019-03-26 09:30","2019-03-26 11:00","당일",null,null,null,201901070379]
[361,"대구","직할","노변효목#2 T/L","차단기 개폐타임 측정","차단기 개폐타임 측정","2019-03-26 11:00","2019-03-26 14:00","2019-03-26 11:00","2019-03-26 14:00","당일",null,null,null,201901070381]
[362,"대구","칠곡","구미광평#1 T/L","광평S/S 구미-광평#1T/L GIS정밀점검","광평S/S 구미-광평#1T/L GIS정밀점검","2019-03-18 09:30","2019-03-20 18:00","2019-03-27 09:30","2019-03-29 18:00","연속",null,null,null,201901040053]
[363,"경북","구미","상주풍산 T/L","154kV 동상주개폐소 지중T/L 건설공사","O 구간 : 154kV 상주S/S ∼ 154kV 동상주개폐소 154kV 동상주 개폐소 ∼ 접속맨홀J/B#1 O 선 종 : 154kV XLPE 1200㎟ * 5회선 O 회선수 및 길이 - 154kV 상주S/S∼154kV 동상주개폐소 2C-0.1㎞ - 154kV 동상주개폐소∼접속맨홀J/B#1 2C-0.15㎞ - 154kV 동상주개폐소∼접속맨홀J/B#1 2C-0.15㎞","2019-03-27 09:00","2019-04-10 18:00","2019-03-27 09:00","2019-04-10 18:00","연속",null,null,null,201901220109]
[364,"경북","구미","상주점촌#2 T/L","154kV 동상주개폐소 지중T/L 건설공사","O 구간 : 154kV 상주S/S ∼ 154kV 동상주개폐소 154kV 동상주 개폐소 ∼ 접속맨홀J/B#1 O 선 종 : 154kV XLPE 1200㎟ * 5회선 O 회선수 및 길이 - 154kV 상주S/S∼154kV 동상주개폐소 2C-0.1㎞ - 154kV 동상주개폐소∼접속맨홀J/B#1 2C-0.15㎞ - 154kV 동상주개폐소∼접속맨홀J/B#1 2C-0.15㎞","2019-03-12 09:00","2019-03-26 18:00","2019-03-12 09:00","2019-03-26 18:00","연속",null,null,null,201901150184]
[365,"경북","구미","상주점촌#1 T/L","154kV 동상주개폐소 지중T/L 건설공사","O 구간 : 154kV 상주S/S ∼ 154kV 동상주개폐소 154kV 동상주 개폐소 ∼ 접속맨홀J/B#1 O 선 종 : 154kV XLPE 1200㎟ * 5회선 O 회선수 및 길이 - 154kV 상주S/S∼154kV 동상주개폐소 2C-0.1㎞ - 154kV 동상주개폐소∼접속맨홀J/B#1 2C-0.15㎞ - 154kV 동상주개폐소∼접속맨홀J/B#1 2C-0.15㎞","2019-03-04 09:00","2019-03-26 18:00","2019-03-04 09:00","2019-03-26 18:00","연속",null,null,null,201901150183]
[366,"경북","구미","선산안계#2 T/L","154kV 해평분기 지중T/L 건설공사","O 구 간 : 154kV 해평E/C ~ 분기맨홀(선산-안계T/L 2파이 분기)&ltbr&gtO 선 종 : 154kV XLPE 2000㎟ 4회선- 0.1㎞","2019-03-25 09:00","2019-04-11 18:00","2019-03-25 09:00","2019-04-11 18:00","연속",null,null,null,201901170118]
[367,"경북","구미","선산청리#1 T/L","2018-19년도 구미전력지사 가공송전협력회사 총액공사","ㅇ 항공장애표시구 설치 : 1경간, 6개","2019-03-29 07:00","2019-03-29 18:00","2019-03-29 07:00","2019-03-29 18:00","당일",null,null,null,201901080124]
[368,"경북","구미","선산청리#2 T/L","345kV 선산분기 등 12개T/L 송전선로용 피뢰기 설치공사","154kV 선산-청리T/L 송전선로용 피뢰기 설치공사","2019-03-28 07:00","2019-03-28 18:00","2019-03-28 07:00","2019-03-28 18:00","당일",null,null,null,201901020046]
[369,"경북","구미","청리상주#2 T/L","2018-19년도 구미전력지사 가공송전협력회사 총액공사","ㅇ 항공장애표시구 설치 : 1경간, 2개","2019-03-27 13:00","2019-03-27 18:00","2019-03-27 13:00","2019-03-27 18:00","당일",null,null,null,201901080126]
[370,"경북","구미","청리상주#1 T/L","2018-19년도 구미전력지사 가공송전협력회사 총액공사","ㅇ 항공장애표시구 설치 : 1경간, 2개","2019-03-27 07:00","2019-03-27 12:00","2019-03-27 07:00","2019-03-27 12:00","당일",null,null,null,201901080125]
[371,"경북","영주","봉화현종산 T/L","항공구 설치공사(OPGW)","154kV 봉화-현종산풍력T/L 항공구설치공사(OPGW)","2019-03-04 08:00","2019-03-04 18:00","2019-03-04 08:00","2019-03-04 18:00","당일",null,null,null,201901080153]
[372,"경북","영주","봉화울진 T/L","항공구 설치공사(가공지선)","154kV 봉화-울진T/L 항공구설치공사(가공지선)","2019-03-05 08:00","2019-03-05 18:00","2019-03-05 08:00","2019-03-05 18:00","당일",null,null,null,201901160009]
[373,"부산울산","동부산","노포정관#1 T/L","19년 가공송전 순시점검 위탁공사(동부산전력지사)","154kV 노포-정관#1T/L 정밀점검 ㅇ 구간 : 노포S/T~정관C/H(36기)","2019-03-25 08:00","2019-03-27 18:00","취소","취소","매일",null,null,null,201901110120]
[374,"부산울산","동부산","노포정관#2 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 작업내용 : 154kV 노포-정관#2T/L 피뢰기 설치 2. 설치수량 : 31기, 93set","2019-03-22 08:00","2019-03-24 18:00","취소","취소","연속",null,null,null,201901080011]
[375,"부산울산","동부산","구서노포#1 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 작업내용 : 154kV 노포-정관#2T/L 피뢰기 설치관련 안전이격확보","2019-03-23 08:00","2019-03-23 18:00","취소","취소","당일",null,null,null,201901080008]
[376,"부산울산","동부산","구서명장#2 T/L","명장S/S 170kV 667GIS 공기압력계 교체","1.명장S/S 667GIS 공기압력계 교체(구서-명장#2T/L) 2.명장S/S 667GIS 조작시험 3.구서S/S 667GIS 조작시험","2019-03-29 09:30","2019-03-29 14:00","2019-03-29 09:30","2019-03-29 14:00","당일",null,null,null,201901110307]
[377,"부산울산","동부산","구서명장#1 T/L","명장S/S 170kV 657GIS 공기압력계 교체","1.명장S/S 170kV 657GIS 공기압력계 교체(구서-명장#1T/L) 2. 명장S/S 657GIS 조작시험 3.구서S/S 657GIS 조작시험","2019-03-29 14:00","2019-03-29 18:00","2019-03-29 14:00","2019-03-29 18:00","당일",null,null,null,201901110308]
[378,"부산울산","동부산","서창산막#2 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 작업내용 : 154kV 노포-정관#2T/L 피뢰기 설치관련 안전이격확보(23호)","2019-03-24 09:00","2019-03-24 18:00","2019-03-24 09:00","2019-03-24 18:00","당일",null,null,null,201901080012]
[379,"부산울산","동부산","서창산막#2 T/L","서창S/S 170kV GIS 보통점검","서창S/S 170kV 687GIS 보통점검(서창-산막#2T/L)","2019-03-09 09:30","2019-03-09 17:00","2019-03-09 09:30","2019-03-09 17:00","당일",null,null,null,201901110302]
[380,"부산울산","북부산","매리김해#2 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","피뢰기 설치공사 관련 안전이격 - 피뢰기 설치공사 : 매리-김해#1T/L NO.1~50호 49기","2019-03-26 07:00","2019-03-29 18:00","취소","취소","매일",null,null,null,201812240082]
[381,"부산울산","북부산","호포매리#1 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","피뢰기 설치공사 관련 안전이격 - 피뢰기 설치공사 : 매리-김해#1T/L NO.1~50호 49기","2019-03-25 07:00","2019-03-25 18:00","취소","취소","당일",null,null,null,201812240081]
[382,"부산울산","북부산","매리김해#1 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","- 피뢰기 설치공사 : 매리-김해#1T/L NO.1~50호 49기","2019-03-25 07:00","2019-03-29 18:00","취소","취소","연속",null,null,null,201812240080]
[383,"부산울산","북부산","언양산막#1 T/L","19년 가공송전 순시점검 위탁공사","154kV 언양-산막#1T/L 정밀점검 시행(1-73호, 67기)","2019-03-11 09:00","2019-03-15 18:00","2019-03-11 09:00","2019-03-15 18:00","매일",null,null,null,201901100214]
[384,"부산울산","북부산","언양산막#2 T/L","19년 가공송전 순시점검 위탁공사","154kV 언양-산막#2T/L 정밀점검 시행(1-73호, 67기)","2019-03-18 09:00","2019-03-22 18:00","2019-03-18 09:00","2019-03-22 18:00","매일",null,null,null,201901100215]
[385,"부산울산","북부산","주촌삼계#1 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","- 피뢰기 설치공사 : 주촌-삼계#1/L NO.31~38호 8기","2019-03-23 07:00","2019-03-23 18:00","2019-03-23 07:00","2019-03-23 18:00","당일",null,null,null,201812240085]
[386,"부산울산","북부산","삼계어방#2 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","피뢰기 설치공사관련 선로 안전이격 - 피뢰기 설치공사 : 주촌-삼계#1/L NO.31~38호 8기","2019-03-23 07:00","2019-03-23 18:00","2019-03-23 07:00","2019-03-23 18:00","당일",null,null,null,201812240087]
[387,"부산울산","북부산","한림정삼계#1 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","피뢰기 설치공사관련 선로 안전이격 - 피뢰기 설치공사 : 주촌-삼계#1/L NO.31~38호 8기","2019-03-23 07:00","2019-03-23 18:00","2019-03-23 07:00","2019-03-23 18:00","당일",null,null,null,201812240086]
[388,"부산울산","북부산","한림정삼계#1 T/L","2019년 북부산 변전협력회사 총액공사","삼계S/S 154kV 한림정-삼계#1T/L 보통점검","2019-03-19 10:00","2019-03-19 18:00","2019-03-16 10:00","2019-03-16 18:00","당일",null,null,null,201901030069]
[389,"부산울산","북부산","한림정삼계#2 T/L","2019년 북부산 변전협력회사 총액공사","삼계S/S 154kV 한림정-삼계#2T/L 보통점검","2019-03-20 10:00","2019-03-20 18:00","2019-03-17 10:00","2019-03-17 18:00","당일",null,null,null,201901030072]
[390,"부산울산","북부산","주촌삼계#2 T/L","2019년 북부산 변전협력회사 총액공사","삼계S/S 154kV 주촌-삼계#2T/L 보통점검","2019-03-14 10:00","2019-03-14 18:00","2019-03-14 10:00","2019-03-14 18:00","당일",null,null,null,201901020071]
[391,"부산울산","북부산","양산S/S 154kV #1 BUS TIE CB","양산S/S 154kV 모선보호반 벨,알람 보수","양산S/S 154kV 모선보호반 벨,알람 보수","2019-03-08 09:00","2019-03-08 18:00","2019-03-08 09:00","2019-03-08 18:00","당일",null,null,null,201901030087]
[392,"부산울산","북부산","학장S/S 154kV #1 BUS TIE CB","2019년 북부산 변전협력회사 총액공사","학장S/S 154kV 6100 Bus-Tie 하자점검","2019-03-26 10:00","2019-03-26 18:00","2019-03-26 10:00","2019-03-26 18:00","당일",null,null,null,201901030079]
[393,"부산울산","서부산","녹공마천#1 T/L","녹공S/S 녹공-마천#1T/L GIS 개폐타임 측정","녹공S/S 녹공-마천#1T/L GIS 개폐타임 측정","2019-03-05 10:00","2019-03-05 14:00","2019-03-05 10:00","2019-03-05 14:00","당일",null,null,null,201901080020]
[394,"부산울산","서부산","용원녹공#2 T/L","녹공S/S 용원-녹공#2T/L GIS 개폐타임 측정","녹공S/S 용원-녹공#2T/L GIS 개폐타임 측정","2019-03-04 14:00","2019-03-04 18:00","2019-03-04 14:00","2019-03-04 18:00","당일",null,null,null,201901080023]
[395,"부산울산","서부산","용원녹공#1 T/L","녹공S/S 용원-녹공#1T/L GIS 개폐타임 측정","녹공S/S 용원-녹공#1T/L GIS 개폐타임 측정","2019-03-04 10:00","2019-03-04 14:00","2019-03-04 10:00","2019-03-04 14:00","당일",null,null,null,201901080022]
[396,"부산울산","서부산","서부산S/S 65-66-0 SEC CB","서부산S/S 65-66-0 SEC 보통점검","서부산S/S 65-66-0 SEC 보통점검","2019-03-22 10:00","2019-03-22 18:00","2019-03-22 10:00","2019-03-22 18:00","당일",null,null,null,201901080019]
[397,"부산울산","서부산","서부산S/S 60-61-0 SEC CB","서부산S/S 60-61-0 SEC 보통점검","서부산S/S 60-61-0 SEC 보통점검","2019-03-25 10:00","2019-03-25 18:00","2019-03-25 10:00","2019-03-25 18:00","당일",null,null,null,201901080018]
[398,"부산울산","울산","동울산효문#1 T/L","2018~2018년 울산전력지사 송전정비 협력회사 총액공사","애자련보강 : 40호 부하측, 41호 전원측 국산애자련 교체 : 42호","2019-03-13 08:00","2019-03-14 18:00","2019-03-13 08:00","2019-03-14 18:00","연속",null,null,null,201901100218]
[399,"부산울산","울산","동울산효문#2 T/L","2018~2018년 울산전력지사 송전정비 협력회사 총액공사","애자련보강 : 40호 부하측, 41호 전원측 국산애자련 교체 : 42호","2019-03-13 08:00","2019-03-14 18:00","2019-03-13 08:00","2019-03-14 18:00","연속",null,null,null,201901100220]
[400,"부산울산","울산","동울산방어진 T/L","2018~19년 변전협력회사 총액공사","- 154kV 동울산-방어진T/L 6A7 보통점검","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901100161]
[401,"부산울산","울산","방어진영남TP#1 T/L","2018~19년 변전협력회사 총액공사","- 154kV 6A7 GIS 하자점검","2019-03-06 09:00","2019-03-06 18:00","2019-03-06 09:00","2019-03-06 18:00","당일",null,null,null,201901100165]
[402,"부산울산","울산","방어진영남TP#2 T/L","2018년~19년 변전협력회사 총액공사","- 154kV 방어진-영남TP#2T/L 637GIS 하자점검","2019-03-07 09:00","2019-03-07 18:00","2019-03-07 09:00","2019-03-07 18:00","당일",null,null,null,201901100166]
[403,"부산울산","울산","신울산S/S 154kV #67 BUS","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","GIS 정밀점검","2019-03-29 17:00","2019-03-29 18:00","2019-03-29 17:00","2019-03-29 18:00","당일",null,null,null,201901140186]
[404,"부산울산","울산","신울산S/S 66-67-0 SEC CB","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","- GIS 정밀점검","2019-03-27 09:00","2019-03-29 18:00","2019-03-27 09:00","2019-03-29 18:00","연속",null,null,null,201901100173]
[405,"부산울산","울산","신울산S/S 154kV #62 BUS","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","GIS 정밀점검","2019-03-22 17:00","2019-03-22 18:00","2019-03-22 17:00","2019-03-22 18:00","당일",null,null,null,201901140185]
[406,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양#2T/L 현수애자 제원 확인","ㅁ 작업내용 : 현수애자 제원확인 ㅁ 선로명 : 154kV 신울산-언양#2T/L ㅁ 대상철탑 : No.S/T,1,2,5(4기)","2019-03-28 09:00","2019-03-28 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901210055]
[407,"부산울산","울산","신울산S/S 61-62-0 SEC CB","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","GIS 정밀점검","2019-03-21 09:00","2019-03-22 18:00","2019-03-21 09:00","2019-03-22 18:00","연속",null,null,null,201901100168]
[408,"부산울산","울산","신울산언양#1 T/L","154kV 신울산-언양#1T/L 현수애자 제원 확인","ㅁ 작업내용 : 현수애자 제원확인 ㅁ 선로명 : 154kV 신울산-언양#1T/L ㅁ 대상철탑 : No.7,9,13,14(4기)","2019-03-27 09:00","2019-03-27 18:00","2019-03-04 09:00","2019-03-04 18:00","당일",null,null,null,201901210054]
[409,"부산울산","울산","옥동외동#1 T/L","2018~2018년 울산전력지사 송전정비 협력회사 총액공사","신울산-태화#1T/L 애자련교체작업간 안전이격확보","2019-03-20 08:00","2019-03-20 18:00","2019-03-20 08:00","2019-03-20 18:00","당일",null,null,null,201901100240]
[410,"부산울산","울산","옥동외동#2 T/L","2018~2018년 울산전력지사 송전정비 협력회사 총액공사","신울산태화#2T/L 애자련교체작업간 안전이격확보","2019-03-21 08:00","2019-03-22 18:00","2019-03-21 08:00","2019-03-22 18:00","연속",null,null,null,201901100241]
[411,"부산울산","울산","울산T/P 154kV #60 BUS","2019년 관내 170kV 장기사용GIS 대체공사","1. 울산화력S/Y 170kV SK케미칼T/L GIS 1CCT 설치 2. CB, 1DS설치","2019-03-04 09:00","2019-03-09 18:00","2019-03-04 09:00","2019-03-09 18:00","연속",null,null,null,201901100160]
[412,"부산울산","울산","울산T/P 154kV #65 BUS","2019년 관내 170kV 장기사용GIS 대체공사","1. 2BUS, 2DS, 상부모선, C/H 설치","2019-03-10 09:00","2019-03-15 16:00","2019-03-10 09:00","2019-03-15 16:00","연속",null,null,null,201901100213]
[413,"부산울산","울산","울산T/P 154kV #60 BUS","2019년 관내 170kV 장기사용GIS 대체공사","- #1DS 시험가압(1H)","2019-03-15 16:00","2019-03-15 17:00","2019-03-15 16:00","2019-03-15 17:00","당일",null,null,null,201901100175]
[414,"부산울산","울산","울산울산TP#2 T/L","2019년 관내 170kV 장기사용GIS 대체공사","1. 울산화력S/Y 170kV SK케미칼T/L GIS 1CCT 설치 2. 장기사용GIS 반입관련 안전이격","2019-03-01 09:00","2019-03-01 12:00","취소","취소","당일",null,null,null,201901100158]
[415,"부산울산","울산","울산울산TP#1 T/L","2019년 관내 170kV 장기사용GIS 대체공사","1. 울산화력S/Y 170kV SK케미칼T/L GIS 1CCT설치 - 안전이격 : 3/4~3/15 매일 (연속휴전일 제외) - 정밀점검 : 3/7 09:00 ~ 3/8 18:00 (연속) - 시험가압1 : 3/8 18:00 ~ 3/9 18:00 (24h) #60BUS, 617,616, 611 - 시험가압2 : 3/14 16:00 ~ 3/15 16:00 (24h) #65bus, 697,692,696 - 시험가압3 : 3/15 16:00 ~ 3/15 17:00 (1h) 691투입","2019-03-04 09:00","2019-03-15 18:00","2019-03-04 09:00","2019-03-15 18:00","매일",null,null,null,201901100159]
[416,"부산울산","울산","울산울산TP#1 T/L","2019년 관내 170kV 장기사용GIS 대체공사","1. 울산화력S/Y 170kV SK케미칼T/L GIS 1CCT 설치 2. 장기사용GIS 반입관련 안전이격","2019-03-01 13:00","2019-03-01 18:00","2019-03-01 09:00","2019-03-01 18:00","당일",null,null,null,201901170063]
[417,"부산울산","울산","울산S/S #1 EM.Tr CB","2018~19년 변전협력회사 총액공사","1. M.Tr 하자점검(안정모) 2. 1, 2차 GIS 하자점검(안진일)","2019-03-12 09:00","2019-03-12 18:00","2019-03-12 09:00","2019-03-12 18:00","당일",null,null,null,201901100170]
[418,"부산울산","울산","울주S/S #1 EM.Tr CB","2018~19년 변전협력회사 총액공사","1. E462DS 불량점검","2019-03-05 09:00","2019-03-05 18:00","2019-03-05 09:00","2019-03-05 18:00","당일",null,null,null,201901100162]
[419,"부산울산","울산","용연처용#2 T/L","2019년 관내 170kV 장기사용GIS 대체공사","1. 처용S/S 154kV S-OIL#3T/L #2BUS, CB, 상부, C/H시험가압(24H) 2. 시험가압선로","2019-03-27 16:00","2019-03-28 16:00","2019-03-27 16:00","2019-03-28 16:00","연속",null,null,null,201901100186]
[420,"부산울산","울산","용연처용#2 T/L","2019년 관내 170kV 장기사용GIS 대체공사","1. 처용S/S 154kV S-OIL#3T/L 장기사용GIS 대체공사 2. #2BUS 시험가압(1H)","2019-03-16 18:00","2019-03-16 19:00","2019-03-16 18:00","2019-03-16 19:00","당일",null,null,null,201901100177]
[421,"부산울산","울산","용연처용#1 T/L","2019년 관내 170kV 장기사용GIS 대체공사","1. 처용S/S 154kV S-OIL#3T/L CB, 1DS 시험가압(24H) 2. #1BUS시험가압(24H)","2019-03-21 18:00","2019-03-22 18:00","2019-03-21 18:00","2019-03-22 18:00","연속",null,null,null,201901100184]
[422,"부산울산","울산","용연처용#1 T/L","2019년 관내 170kV 장기사용GIS 대체공사","1. 처용S/S 154kV S-OIL#3T/L #1DS 시험가압(1H) 2. 시험가압선로","2019-03-28 16:00","2019-03-28 17:00","2019-03-28 16:00","2019-03-28 17:00","당일",null,null,null,201901100187]
[423,"부산울산","직할","범일S/S 154kV #1 BUS TIE CB","2019년 직할 변전협력회사 총액공사","- B/P PNL 대체","2019-03-04 10:00","2019-03-07 18:00","취소","취소","연속",null,null,null,201901110211]
[424,"부산울산","직할","범일서면#1 T/L","범일,서면S/S 범일-서면#1T/L 보호배전반 성능개선(제작사 가보)","범일,서면S/S 범일-서면#1T/L 보호배전반 성능개선(제작사 가보)","2019-03-11 10:00","2019-03-11 18:00","2019-03-11 10:00","2019-03-11 18:00","당일",null,null,null,201901110216]
[425,"부산울산","직할","수정범일#1 T/L","수정,범일/S 수정-범일#1T/L 보호배전반 성능개선(제작사 세니온)","수정,범일/S 수정-범일#1T/L 보호배전반 성능개선(제작사 세니온)","2019-03-14 10:00","2019-03-14 18:00","2019-03-14 10:00","2019-03-14 18:00","당일",null,null,null,201901110219]
[426,"부산울산","직할","수정범일#2 T/L","수정,범일/S 수정-범일#2T/L 보호배전반 성능개선(제작사 세니온)","수정,범일/S 수정-범일#2T/L 보호배전반 성능개선(제작사 세니온)","2019-03-15 10:00","2019-03-15 18:00","2019-03-15 10:00","2019-03-15 18:00","당일",null,null,null,201901110220]
[427,"경남","직할","녹공마천#2 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","녹공-마천#2T/L 피뢰기 설치(1-9호)","2019-03-07 07:00","2019-03-08 18:00","2019-03-07 07:00","2019-03-08 18:00","매일",null,null,null,201812280028]
[428,"경남","직할","신김해주촌#1 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","345kV 신김해-신녹산#2T/L 정밀점검관련 안전거리확보, 154kV 신김해-주촌#1(2호) 병가","2019-03-17 09:00","2019-03-17 18:00","2019-03-01 09:00","2019-03-01 18:00","당일",null,null,null,201812060087]
[429,"경남","직할","신김해진영#1 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신김해-진영#1T/L 피뢰기 설치(9-14호)","2019-03-31 07:00","2019-03-31 18:00","2019-03-31 07:00","2019-03-31 18:00","당일",null,null,null,201812280026]
[430,"경남","직할","신김해진영#1 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신김해-진영#1T/L 피뢰기 설치 (15-29호,1-3호)","2019-03-02 07:00","2019-03-03 18:00","2019-03-02 07:00","2019-03-03 18:00","매일",null,null,null,201812280024]
[431,"경남","직할","신김해진영#1 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","신김해-진영#1T/L 피뢰기설치(4-8,30-33호)","2019-03-16 07:00","2019-03-16 18:00","2019-03-16 07:00","2019-03-16 18:00","당일",null,null,null,201812280021]
[432,"경남","직할","신김해삼정#1 T/L","신김해S/S 170kV GIS 대체공사(5차공정)","신김해S/S 170kV GIS 대체공사(5차공정) : 안전이격거리 확보 및 시험가압선로","2019-03-18 08:00","2019-03-30 17:30","2019-03-18 08:00","2019-03-30 17:30","연속",null,null,null,201901030078]
[433,"경남","직할","신월삼정#1 T/L","154kV 신월-동읍 등 2개T/L OF케이블 교체공사","신월EBG~#1M/H 구간 154kV 신월-삼정#1T/L 케이블 교체(OF1200㎟ → XLPE1200㎟)","2019-03-04 08:00","2019-04-02 18:00","2019-03-04 08:00","2019-04-02 18:00","연속",null,null,null,201901030008]
[434,"경남","직할","주촌삼계#1 T/L","154kV 녹공-마천 등 17개 T/L 피뢰기 설치공사","주촌-삼계#1T/L 피뢰기설치(20-30호)","2019-03-09 07:00","2019-03-09 18:00","2019-03-09 07:00","2019-03-09 18:00","당일",null,null,null,201812280019]
[435,"경남","진주","사천개양#1 T/L","154kV 삼천포-사천#1T/L 피뢰기 설치공사","154kV 삼천포-사천#1T/L 피뢰기 설치공사 안전확보차","2019-03-24 07:00","2019-03-24 09:00","2019-03-24 07:00","2019-03-24 09:00","당일",null,null,null,201901070071]
[436,"경남","진주","하동하동화력#1 T/L","하동S/S 하동하동화력#1 T/L(637) CB 조작시험","하동S/S 하동하동화력#1 T/L(637) CB 조작시험","2019-03-08 10:00","2019-03-08 14:00","2019-03-08 10:00","2019-03-08 14:00","당일",null,null,null,201901070211]
[437,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 안전이격확보공사","154kV 하동-개양#1,2T/L 19,20호 안전이격확보공사","2019-03-01 07:00","2019-03-04 19:00","취소","취소","연속",null,null,null,201812170092]
[438,"경남","진주","하동하동화력#2 T/L","하동S/S 하동하동화력#2 T/L(647) CB 조작시험","하동S/S 하동하동화력#2 T/L(647) CB 조작시험","2019-03-08 14:00","2019-03-08 18:00","2019-03-08 14:00","2019-03-08 18:00","당일",null,null,null,201901070212]
[439,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 안전이격확보공사","154kV 하동-개양#1,2T/L 19,20호 안전이격확보공사","2019-03-09 07:00","2019-03-11 19:00","취소","취소","연속",null,null,null,201812170093]
[440,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 안전이격확보공사","154kV 하동-개양#1,2T/L 19,20호 안전이격확보공사","2019-03-09 07:00","2019-03-11 19:00","취소","취소","연속",null,null,null,201812170094]
[441,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 안전이격확보공사","154kV 하동-개양#1,2T/L 19,20호 안전이격확보공사","2019-03-01 07:00","2019-03-04 19:00","취소","취소","연속",null,null,null,201812170091]
[442,"경남","진주","합천수력#1 T/L","합천S/S 합천수력#1T/L CB(637) 조작시험","합천S/S 합천수력#1T/L CB(637) 조작시험","2019-03-14 10:00","2019-03-14 14:00","2019-03-14 10:00","2019-03-14 14:00","당일",null,null,null,201901070221]
[443,"경남","진주","합천수력#2 T/L","합천S/S 합천수력#2T/L CB(647) 조작시험","합천S/S 합천수력#2T/L CB(647) 조작시험","2019-03-14 14:00","2019-03-14 18:00","2019-03-14 14:00","2019-03-14 18:00","당일",null,null,null,201901070222]
[444,"경남","통영","고성통영 T/L","154kV 고성-안정#2T/L 피뢰기 설치공사","154kV 고성-안정#2T/L 피뢰기 설치공사 안전확보차","2019-03-17 07:00","2019-03-17 18:00","2019-03-17 07:00","2019-03-17 18:00","당일",null,null,null,201901070085]
[445,"경남","통영","삼천포사천#2 T/L","154kV 삼천포-사천#1T/L 피뢰기 설치공사","154kV 삼천포-사천#1T/L 피뢰기 설치공사 안전확보차","2019-03-23 07:00","2019-03-24 18:00","2019-03-23 07:00","2019-03-24 18:00","매일",null,null,null,201901070068]
[446,"경남","통영","삼천포사천#1 T/L","154kV 삼천포-사천T/L 피뢰기 설치공사","154kV 삼천포-사천#1T/L 60~72호 피뢰기 설치공사","2019-03-23 07:00","2019-03-24 18:00","2019-03-23 07:00","2019-03-24 18:00","매일",null,null,null,201901070067]
[447,"경남","통영","신고성고성 T/L","154kV 신고성-통영T/L 안전이격 확보공사","154kV 신고성-통영T/L 56~58호, 91~93호 안전이격 확보공사","2019-03-01 09:00","2019-03-02 12:00","2019-03-01 09:00","2019-03-02 12:00","연속",null,null,null,201901070065]
[448,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 안전이격 확보공사","154kV 신고성-통영T/L 56~58호, 91~93호 안전이격 확보공사","2019-03-02 12:00","2019-03-03 18:00","2019-03-02 12:00","2019-03-03 18:00","연속",null,null,null,201901070066]
[449,"경남","통영","진동S/S 154kV #2 BUS","진동S/S 170kV GIS(서마산T/L,#1M.Tr 1차) 대체","1. 진동S/S 170kV GIS(서마산-진동T/L,#1M.Tr 1차) 대체공사","2019-03-30 09:00","2019-04-09 16:00","2019-03-30 09:00","2019-04-09 16:00","연속",null,null,null,201811210098]
[450,"경남","통영","신마산진동 T/L","진동S/S 170kV GIS(서마산T/L,#1M.Tr 1차) 대체","진동S/S 170kV GIS(서마산-진동T/L,#1M.Tr 1차) 대체공사 진동S/S 서마산-진동T/L GIS 대체관련 임시선로 구성(3/23~24)","2019-03-23 08:30","2019-04-09 19:00","2019-03-23 08:30","2019-04-09 19:00","연속",null,null,null,201811210106]
[451,"경남","통영","통영거제#2 T/L","154kV 통영-거제#2T/L 피뢰기 설치공사","154kV 통영-거제#2T/L 41~52호, 57~69호 피뢰기 설치공사","2019-03-23 07:00","2019-03-24 18:00","2019-03-23 07:00","2019-03-24 18:00","매일",null,null,null,201901070076]
[452,"경남","함안","신마산마산#1 T/L","154kV 신마산-마산#1T/L 피뢰기 설치","154kV 신마산-마산#1T/L 1-5호 피뢰기 설치","2019-03-09 09:00","2019-03-09 18:00","2019-03-09 09:00","2019-03-09 18:00","당일",null,null,null,201901040138]
[453,"경남","함안","신마산마산#2 T/L","154kV 신마산-진동T/L 9-23호 피뢰기 설치작업","피뢰기설치작업 4회선구간 안전이격차","2019-03-28 07:00","2019-03-28 18:00","2019-03-28 07:00","2019-03-28 18:00","당일",null,null,null,201901180136]
[454,"경남","함안","신마산마산#2 T/L","154kV 신마산-마산#1T/L 피뢰기 설치 안전이격","154kV 신마산-마산#1T/L 1-5호 피뢰기 설치","2019-03-09 09:00","2019-03-09 18:00","2019-03-09 09:00","2019-03-09 18:00","당일",null,null,null,201901040140]
[455,"경남","함안","신마산중리#1 T/L","154kV 신마산-진동T/L 1-8호 피뢰기 설치작업","피뢰기설치작업 6회선구간 안전이격차","2019-03-31 07:00","2019-03-31 15:00","2019-03-31 07:00","2019-03-31 15:00","당일",null,null,null,201901180137]
[456,"경남","함안","중리가야#1 T/L","중리S/S 154kV 중리-가야 #1T/L GIS 보통점검","중리S/S 154kV 중리-가야 #1T/L GIS 보통점검","2019-03-26 09:30","2019-03-26 17:30","2019-03-26 09:30","2019-03-26 17:30","당일",null,null,null,201901040025]
[457,"경남","함안","중리가야#2 T/L","중리,가야S/S 154kV 중리-가야#2T/L GIS 보통점검","중리,가야S/S 154kV 중리-가야#2T/L GIS 보통점검","2019-03-27 09:30","2019-03-27 17:30","2019-03-27 09:30","2019-03-27 17:30","당일",null,null,null,201901040016]
[458,"경남","함안","신마산중리#2 T/L","154kV 신마산-진동T/L 1-8호 피뢰기 설치작업","피뢰기설치작업 6회선구간 안전이격차","2019-03-31 07:00","2019-03-31 15:00","2019-03-31 07:00","2019-03-31 15:00","당일",null,null,null,201901180138]
[459,"경남","함안","진영수산#1 T/L","154kV 진영-수산T/L 44~50호 안전이격확보공사","철탑교체(계탑 5기)","2019-03-11 07:00","2019-03-20 18:30","2019-03-11 07:00","2019-03-20 18:30","연속",null,null,null,201901040003]
[460,"경남","함안","진영수산#2 T/L","154kV 진영-수산T/L 44~50호 안전이격확보공사","철탑교체(계탑 5기)","2019-03-11 07:00","2019-03-20 18:30","2019-03-11 07:00","2019-03-20 18:30","연속",null,null,null,201901040004]
[461,"광주전남","순천","호남TP여수TP#1T/L","18~19년도 순천전력지사 변전협력회사 총액공사","호남화력 CB타임 측정, 여수화력 GIS 보통","2019-03-26 09:00","2019-03-26 18:00","2019-03-11 09:00","2019-03-11 18:00","당일"]
[462,"광주전남","순천","호남TP여수TP#1T/L","18~19년도 순천전력지사 변전협력회사 총액공사","호남화력 CB타임 측정, 여수화력 GIS 보통","2019-03-26 09:00","2019-03-26 18:00","2019-03-12 09:00","2019-03-12 18:00","당일"]