{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":11,"n_cols":16,"rows_kept":11,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
["2019년도 4월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #3 M.Tr A-1","19년도 신가평변전소 765kV GIS 점검공사","8472CB,8400CB,8402DS,8422DS,8462DS,8452DS정밀점검/#3MTr 정밀점검","2019-04-22 09:00","2019-06-14 18:00","2019-04-22 09:00","2019-06-14 18:00","연속",null,null,null,201902120207]
[2,"경기북부","구리","신가평S/S 765kV #1 BUS","765kV #80BUS 보호반 교체공사","765kV #80BUS 보호반 교체","2019-04-01 08:00","2019-04-12 18:00","취소","취소","연속",null,null,null,201812170030]
[3,"경기북부","구리","신가평S/S #1 M.Tr A-1","19년도 신가평변전소 765kV GIS 점검공사","82Bay(8200CB,8272CB) GIS 하자점검/#1MTr 하자점검(모장순)","2019-04-08 09:00","2019-04-10 18:00","취소","취소","연속"]
[4,"경기","성남","신안성신가평 T/L","2018-2019년 성남전력지사 송전정비회사 총액공사","- 765kV 신안성-신가평T/L 항공장애표시도장(10기)","2019-04-08 07:00","2019-04-26 18:00","취소","취소","연속",null,null,null,201902190212]
[5,"강원","태백","신태백신가평#1 T/L","항공장애표시구 설치","765kV 신태백-신가평#1T/L 항공장애표시구 설치","2019-04-08 10:00","2019-04-12 18:00","2019-04-15 09:00","2019-04-19 18:00","연속",null,null,null,201902130415]
[6,"대전충남","서산","신서산S/S #3 M.Tr A-1","19년도 서산P/O 765kV M.Tr 정밀점검공사","신서산S/S 765kV #3M.Tr 정밀점검공사","2019-04-01 09:00","2019-06-05 18:00","2019-04-01 09:00","2019-06-05 18:00","연속",null,null,null,201902120104]
[7,"경남","함안","북경남S/S #3 M.Tr A-1","북경남S/S #3M.Tr 1차측 Spacer 교체공사","북경남S/S #3M.Tr 1차측 Spacer 교체공사","2019-04-15 09:30","2019-06-20 18:00","2019-04-15 13:30","2019-06-20 18:00","연속"]

{"sheet":"345송부","index":1,"n_rows":336,"n_cols":16,"rows_kept":336,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,14,3,14],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
["2019년도 4월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S 345kV #1 BUS","19년 성동P/O 변전협력회사 총액공사","362kV 모선보호반 교체","2019-04-08 09:30","2019-04-12 17:00","2019-04-08 09:30","2019-04-12 17:00","연속",null,null,null,201901150248]
[2,"서울","성동","성동S/S 345kV #2 BUS","19년 성동P/O 변전협력회사 총액공사","362kV 모선보호반 교체","2019-04-15 09:30","2019-04-19 17:00","2019-04-15 09:30","2019-04-19 17:00","연속",null,null,null,201901150249]
[3,"남서울","동서울","동서울S/S #3 M.Tr A","#3M.Tr 1차 피뢰기 교체공사","#3M.Tr 1차 피뢰기 교체공사 1,3차 조작시험, 2차 초기점검","2019-04-01 09:00","2019-04-03 14:00","2019-04-01 09:00","2019-04-03 14:00","연속",null,null,null,201902130623]
[4,"남서울","동서울","동서울S/S #4 M.Tr A","#3M.Tr 1차 피뢰기 교체공사","#3M.Tr 1차 피뢰기 교체공사 1차 조작시험, 2차 초기점검","2019-04-03 14:00","2019-04-05 18:00","2019-04-03 14:00","2019-04-05 18:00","연속",null,null,null,201902130625]
[5,"남서울","영등포","신광명S/S #3 M.Tr A","신광명S/S #`3M.Tr 점검","1,2,3차 LA 점검 1,3차 PT 점검 2차 GIS 초기점검 3차 CB 조작시험","2019-04-04 09:00","2019-04-04 18:00","2019-04-04 09:00","2019-04-04 18:00","당일",null,null,null,201902110314]
[6,"남서울","영등포","신광명S/S #1 M.Tr A","신광명S/S #`1M.Tr 점검","1,2,3차 LA 점검 1,3차 PT 점검 2차 GIS 초기점검 3차 CB 조작시험","2019-04-03 09:00","2019-04-03 18:00","2019-04-03 09:00","2019-04-03 18:00","당일",null,null,null,201902110313]
[7,"남서울","영등포","신광명S/S #4 M.Tr A","신광명S/S #`4M.Tr 점검","1,2,3차 LA 점검 1,3차 PT 점검 2차 GIS 초기점검 3차 CB 조작시험","2019-04-05 09:00","2019-04-05 18:00","2019-04-05 09:00","2019-04-05 18:00","당일",null,null,null,201902110316]
[8,"남서울","영등포","서서울신광명#1 T/L","신광명S/S 345kV LA,PT 점검","신광명-서서울#1T/L","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902110472]
[9,"남서울","영등포","서서울신광명#2 T/L","신광명S/S 345kV LA,PT점검","신광명-서서울#2T/L","2019-04-09 09:00","2019-04-09 18:00","2019-04-09 09:00","2019-04-09 18:00","당일",null,null,null,201902110515]
[10,"남서울","영등포","신시흥신광명#1 T/L","신광명S/S 345kV LA,PT점검","신시흥-신광명#1T/L GIS 점검","2019-04-10 09:00","2019-04-10 18:00","2019-04-10 09:00","2019-04-10 18:00","당일",null,null,null,201902110537]
[11,"남서울","영등포","신시흥신광명#2 T/L","신광명S/S 345kV LA,PT점검","신시흥-신광명#2T/L GIS 점검","2019-04-11 09:00","2019-04-11 18:00","2019-04-11 09:00","2019-04-11 18:00","당일",null,null,null,201902110542]
[12,"남서울","직할","영등포S/S 영서-영등포#2T/L-#2M.Tr 1차CB","영등포S/S 345kV 7200 GIS 정밀점검 공사","영등포S/S 345kV 7200 GIS 정밀점검 공사","2019-04-29 09:00","2019-05-02 18:00","취소","취소","연속",null,null,null,201902130107]
[13,"남서울","직할","영등포S/S #2 M.Tr A","영등포S/S 345kV 7200,7272 GIS 정밀점검 공사","영등포S/S 345kV 7200,7272 GIS 정밀점검 공사","2019-04-29 09:00","2019-05-10 18:00","2019-04-29 09:00","2019-05-10 18:00","연속",null,null,null,201902130104]
[14,"남서울","직할","영등포S/S 영서-영등포#1T/L CB (7171)","영등포S/S 345kV 신광명-영등포#1T/L(7171)CB 정밀점검공사","영등포S/S 345kV 신광명-영등포#1T/L(7171)CB 정밀점검공사","2019-04-01 09:00","2019-04-04 18:00","2019-04-01 09:00","2019-04-04 18:00","연속",null,null,null,201902180117]
[15,"남서울","직할","영등포S/S 영서-영등포#2T/L CB (7271)","영등포S/S 345kV 신광명-영등포#2T/L(7271)CB 정밀점검공사","영등포S/S 345kV 신광명-영등포#2T/L(7271)CB 정밀점검공사","2019-04-08 09:00","2019-04-11 18:00","2019-04-08 09:00","2019-04-11 18:00","연속",null,null,null,201902180119]
[16,"남서울","직할","영등포S/S 영서-영등포#1T/L-#1M.Tr 1차CB","영등포S/S 345kV 7100GIS 정밀점검 공사","영등포S/S 345kV 7100 GIS 정밀점검 공사","2019-04-15 09:00","2019-04-18 18:00","취소","취소","연속",null,null,null,201902130097]
[17,"남서울","직할","영등포S/S #1 M.Tr A","영등포S/S 345kV 7100,7172 GIS 정밀점검 공사","영등포S/S 345kV 7100, 7172 및 연관 DS GIS 정밀점검 공사","2019-04-15 09:00","2019-04-26 18:00","2019-04-15 09:00","2019-04-26 18:00","연속",null,null,null,201902130096]
[18,"남서울","직할","영등포S/S #1 M.Tr 1차 CB","영등포S/S 345kV 7172 GIS 정밀점검 공사","영등포S/S 345kV 7172 GIS 정밀점검 공사","2019-04-22 09:00","2019-04-25 18:00","취소","취소","연속",null,null,null,201902130099]
[19,"남서울","직할","신광명영등포#2 T/L","영등포S/S 신광명-영등포#2T/L 보호배전반 교체공사","영등포S/S 신광명-영등포#2T/L 보호배전반 교체공사","2019-04-26 18:00","2019-04-29 09:00","취소","취소","연속",null,null,null,201902130115]
[20,"인천","인천","인천CC S/Y 75-76 SEC GIS","인천화력S/Y 75-76 GIS 조작시험","인천화력S/Y 75-76 GIS 조작시험","2019-04-29 13:00","2019-04-29 18:00","2019-04-29 13:00","2019-04-29 18:00","당일",null,null,null,201902080197]
[21,"인천","시흥","신시흥#1S/S #1 M.Tr A","신시흥#1S/S #1M.Tr, 1차GIS 보통점검, 2차GIS 동작점검","신시흥#1S/S #1M.Tr, 1차GIS 보통점검, 2차GIS 동작점검","2019-04-29 10:00","2019-05-02 18:00","2019-04-29 10:00","2019-05-02 18:00","연속",null,null,null,201902140132]
[22,"인천","인천","신경서포스코SY#2T/L-#3M.Tr 1차 CB (7500)","2019년 부평전력지사 362kV GIS 정밀점검","신경서포스코SY#2T/L-#3M.Tr 1차 7500 GIS 정밀점검","2019-04-29 09:00","2019-05-01 18:00","2019-04-29 09:00","2019-05-01 18:00","연속",null,null,null,201902180114]
[23,"인천","인천","인천CC S/Y 70-71 SEC GIS","인천화력S/Y 70-71 GIS 조작시험","인천화력S/Y 70-71 GIS 조작시험","2019-04-29 09:00","2019-04-29 13:00","2019-04-29 09:00","2019-04-29 13:00","당일",null,null,null,201902080196]
[24,"인천","인천","서인천C/C 345kV #4 Sh.R","서인천복합S/Y #4Sh.R 보통점검 및 7A79 GIS 하자점검","서인천복합S/Y #4Sh.R 보통점검 서인천복합S/Y 7A79 GIS 하자점검","2019-04-24 09:00","2019-04-25 18:00","취소","취소","연속",null,null,null,201902080204]
[25,"인천","김포","345kV가정개폐 #1Sh.R 1차 GIS","가정개폐소 345kV #1Sh.R 1차 GIS 보통점검","가정개폐소 345kV #1Sh.R 1차 7671 GIS 보통점검","2019-04-23 10:00","2019-04-23 18:00","2019-04-23 10:00","2019-04-23 18:00","당일",null,null,null,201902140105]
[26,"인천","김포","가정개폐소 345KV 75-76 SEC CB","가정개폐소 345kV 75-76 SEC GIS 보통점검","가정개폐소 345kV 75-76 SEC GIS 보통점검","2019-04-22 10:00","2019-04-22 18:00","2019-04-22 10:00","2019-04-22 18:00","당일",null,null,null,201902140104]
[27,"인천","시흥","신시흥#1S/S #3 M.Tr A","신시흥#1S/S #3 M.Tr, 1차 GIS 보통점검,2차GIS동작점검","신시흥#1S/S #3 M.Tr, 1차 GIS 보통점검,2차GIS동작점검","2019-04-22 10:00","2019-04-25 18:00","2019-04-22 10:00","2019-04-25 18:00","연속",null,null,null,201902140134]
[28,"인천","인천","신경서S/S #2 M.Tr 1차 CB (7272)","2019년 부평전력지사 362kV 7272 GIS 정밀점검","신경서S/S #2 M.Tr 1차 GIS 정밀점검","2019-04-22 09:00","2019-04-24 18:00","2019-04-22 09:00","2019-04-24 18:00","연속",null,null,null,201902180113]
[29,"인천","김포","가정개폐소 345KV 70-71 SEC CB","가정개폐소 345kV 70-71 SEC GIS 보통점검","가정개폐소 345kV 70-71 SEC GIS 보통점검","2019-04-19 10:00","2019-04-19 18:00","2019-04-19 10:00","2019-04-19 18:00","당일",null,null,null,201902140103]
[30,"인천","시흥","영흥1TP영흥2TP #1T/L","영흥화력#1S/Y 영흥TP연락#1T/L 보호반 접지개소 보완","영흥화력#1S/Y 영흥TP연락#1T/L 보호반 접지개소 보완","2019-04-18 10:30","2019-04-18 18:00","2019-04-18 10:30","2019-04-18 18:00","당일",null,null,null,201902150047]
[31,"인천","김포","345kV 가정개폐소 #3Sh.R 1차 GIS","가정개폐소 345kV #3Sh.R 1차 GIS 보통점검","가정개폐소 345kV #3Sh.R 1차 7172 GIS 보통점검","2019-04-18 10:00","2019-04-18 18:00","2019-04-18 10:00","2019-04-18 18:00","당일",null,null,null,201902140102]
[32,"인천","인천","(신)서인천C/C 신김포서인천CC T/L CB (7171)","서인천C/C 7171 GIS 조작시험","서인천C/C 7171 GIS 조작시험","2019-04-18 09:00","2019-04-18 13:00","2019-04-18 09:00","2019-04-18 13:00","당일",null,null,null,201902080199]
[33,"인천","김포","가정개폐소 345KV #2,3Sh.R - TIE GIS","가정개폐소 345kV #2Sh.R TIE GIS 보통점검","가정개폐소 345kV #2Sh.R TIE 7100 GIS 보통점검","2019-04-17 10:00","2019-04-17 18:00","2019-04-17 10:00","2019-04-17 18:00","당일",null,null,null,201902140101]
[34,"인천","김포","345kV가정개폐 #2Sh.R 1차 GIS","가정개폐소 345kV #2Sh.R 1차 GIS 보통점검","가정개폐소 345kV #2Sh.R 1차 7171 GIS 보통점검","2019-04-16 10:00","2019-04-16 18:00","2019-04-16 10:00","2019-04-16 18:00","당일",null,null,null,201902140100]
[35,"인천","인천","(신)서인천C/C #4 M.Tr 1차 CB (7472)","서인천C/C 7472 GIS 조작시험","서인천C/C 7472 GIS 조작시험","2019-04-16 09:00","2019-04-16 18:00","2019-04-16 09:00","2019-04-16 18:00","당일",null,null,null,201902080193]
[36,"인천","인천","(신)서인천C/C #3 M.Tr 1차 CB (7372)","서인천C/C 7372 GIS 조작시험","서인천C/C 7372 GIS 조작시험","2019-04-15 09:00","2019-04-15 18:00","2019-04-15 09:00","2019-04-15 18:00","당일",null,null,null,201902080134]
[37,"인천","인천","인천CC S/Y 인천복합 #3S/T CB (7B72)","2019년 부평전력지사 362kV 7B72 GIS 정밀점검","인천CC S/Y 인천복합 #3S/T GIS 정밀점검","2019-04-15 09:00","2019-04-17 18:00","2019-04-15 09:00","2019-04-17 18:00","연속",null,null,null,201902180112]
[38,"인천","시흥","신시흥#2S/S #5M.Tr A","신시흥#2S/S 신시흥북시화#1T/L 부싱 이격거리 확보 공사[이격거리]","신시흥#2S/S 신시흥북시화#1T/L 부싱 이격거리 확보 공사[이격거리]","2019-04-15 08:30","2019-04-15 18:00","2019-04-15 08:30","2019-04-15 18:00","연속",null,null,null,201902140168]
[39,"인천","인천","(신)서인천C/C #2 M.Tr 1차 CB (7272)","서인천C/C 7272 GIS 조작시험","서인천C/C 7272 GIS 조작시험","2019-04-12 13:00","2019-04-12 18:00","2019-04-12 13:00","2019-04-12 18:00","당일",null,null,null,201902080124]
[40,"인천","인천","(신)서인천C/C 서인천신부평#3T/L-#4MTr CB (7400)","서인천C/C 7400 GIS 조작시험","서인천C/C 7400 GIS 조작시험","2019-04-11 13:00","2019-04-11 18:00","2019-04-11 13:00","2019-04-11 18:00","당일",null,null,null,201902080123]
[41,"인천","인천","인천CC S/Y #1Tie-Tr A","인천복합S/Y #1Tie-Tr 1_2_3차 GIS 조작시험","- #1Tie-Tr 1, 2, 3차 GIS 조작시험공사 - #1Tie-Tr 2차 EBA 현장 확인 (치수 측정 및 외관 점검 등)","2019-04-11 10:00","2019-04-11 18:00","2019-04-11 10:00","2019-04-11 18:00","당일",null,null,null,201902080034]
[42,"인천","인천","(신)서인천C/C 서인천CC신부평#3T/L CB (7471)","서인천C/C 7471 GIS 조작시험","서인천C/C 7471 GIS 조작시험","2019-04-11 09:00","2019-04-11 13:00","2019-04-11 09:00","2019-04-11 13:00","당일",null,null,null,201902080122]
[43,"인천","인천","(신)서인천C/C 서인천신부평#2T/L-#3MTr CB (7300)","서인천C/C 7300 GIS 조작시험","서인천C/C 7300 GIS 조작시험","2019-04-10 13:00","2019-04-10 18:00","2019-04-10 13:00","2019-04-10 18:00","당일",null,null,null,201902080120]
[44,"인천","인천","(신)서인천C/C 서인천CC신부평#2T/L CB (7371)","서인천C/C 7371 GIS 조작시험","서인천C/C 7371 GIS 조작시험","2019-04-10 09:00","2019-04-10 13:00","2019-04-10 09:00","2019-04-10 13:00","당일",null,null,null,201902080119]
[45,"인천","인천","(신)서인천C/C 신경서서인천T/L-1M.Tr CB (7200)","서인천C/C 7200 GIS 조작시험","서인천C/C 7200 GIS 조작시험","2019-04-09 13:00","2019-04-09 18:00","2019-04-09 13:00","2019-04-09 18:00","당일",null,null,null,201902080102]
[46,"인천","인천","(신)서인천C/C 신경서서인천CC T/L CB (7271)","서인천C/C 7271 GIS 조작시험","서인천C/C 7271 GIS 조작시험","2019-04-09 09:00","2019-04-09 13:00","2019-04-09 09:00","2019-04-09 13:00","당일",null,null,null,201902080095]
[47,"인천","인천","신경서S/S #1 M.Tr A","신경서S/S #1M.Tr 휴전작업","신경서S/S #1M.Tr 휴전작업 - 2차 GIS(6144) 정밀점검 - 7100, 7172GIS 조작시험","2019-04-08 09:00","2019-04-10 18:00","2019-04-08 09:00","2019-04-10 18:00","연속",null,null,null,201902210063]
[48,"인천","인천","인천CC S/Y 인천복합 #5,6G/T-#3S/T CB (7B00)","2019년 부평전력지사 362kV GIS 정밀점검","인천CC S/Y 인천복합#5,6G/T-#3S/T 7B00 GIS 정밀점검","2019-04-08 09:00","2019-04-10 18:00","2019-04-08 09:00","2019-04-10 18:00","연속",null,null,null,201902180111]
[49,"인천","직할","신부평S/S 서인천CC-신부평#2T/L CB (7271)","신부평S/S 7271CB 362kV GIS 정밀점검","신부평S/S 7271CB 362kV GIS 정밀점검","2019-04-08 08:00","2019-04-10 18:00","2019-04-08 08:00","2019-04-10 18:00","연속",null,null,null,201902200210]
[50,"인천","직할","서인천CC-신부평#2T/L-#2 M.Tr 1차 CB (7200)","신부평S/S 7200CB 362kV GIS 정밀점검","신부평S/S 7200CB 362kV GIS 정밀점검","2019-04-04 08:00","2019-04-06 18:00","2019-04-04 08:00","2019-04-06 18:00","연속",null,null,null,201902200209]
[51,"인천","인천","신경서S/S 신경서서인천CCT/L-TIE CB (7400)","신경서S/S 7400 GIS 조작시험","신경서S/S 7400 GIS 조작시험","2019-04-03 13:00","2019-04-03 18:00","2019-04-03 13:00","2019-04-03 18:00","당일",null,null,null,201902070255]
[52,"인천","인천","신경서인천CC#1 T/L-#2 M.Tr 1차 CB (7200)","신경서S/S 7200 GIS 조작시험","신경서S/S 7200 GIS 조작시험","2019-04-03 09:00","2019-04-03 13:00","2019-04-03 09:00","2019-04-03 13:00","당일",null,null,null,201902070241]
[53,"인천","인천","신경서S/S 신경서서인천CCT/L CB (7472)","신경서S/S 7472 GIS 조작시험","신경서S/S 7472 GIS 조작시험","2019-04-02 13:00","2019-04-02 18:00","2019-04-02 13:00","2019-04-02 18:00","당일",null,null,null,201902070256]
[54,"인천","인천","신경서S/S 서인천인천CC#2T/L CB (7372)","신경서S/S 7372 GIS 조작시험","신경서S/S 7372 GIS 조작시험","2019-04-02 09:00","2019-04-02 13:00","2019-04-02 09:00","2019-04-02 13:00","당일",null,null,null,201902070254]
[55,"인천","인천","신경서S/S 신경서인천CC#1T/L CB (7271)","신경서S/S 7271 GIS 조작시험","신경서S/S 7271 GIS 조작시험","2019-04-01 13:00","2019-04-01 18:00","2019-04-01 13:00","2019-04-01 18:00","당일",null,null,null,201902070239]
[56,"인천","인천","신가좌가정#1 T/L","345kV신가좌-가정#1T/L 정밀점검","345kV신가좌-가정#1T/L 정밀점검","2019-04-01 09:00","2019-04-04 18:00","2019-04-01 09:00","2019-04-04 18:00","연속",null,null,null,201902150152]
[57,"인천","인천","신경서S/S 신경서신인천CCT/L CB (7171)","신경서S/S 7171 GIS 조작시험","신경서S/S 7171 GIS 조작시험","2019-04-01 09:00","2019-04-01 13:00","2019-04-01 09:00","2019-04-01 13:00","당일",null,null,null,201902070227]
[58,"인천","인천","인천CC S/Y 인천복합 #5,6G/T CB (7B71)","2019년 부평전력지사 362kV GIS 정밀점검","인천CC S/Y 인천복합 #5,6G/T 7B71 GIS 정밀점검","2019-04-01 09:00","2019-04-03 18:00","2019-04-01 09:00","2019-04-03 18:00","연속",null,null,null,201902180110]
[59,"인천","직할","서인천CC-신부평#1T/L-#1 M.Tr 1차 CB (7100)","신부평S/S 7100CB 누기보수","신부평S/S 7100CB 누기보수","2019-04-01 09:00","2019-04-02 18:00","2019-04-01 09:00","2019-04-02 18:00","연속",null,null,null,201902180242]
[60,"인천","시흥","신시흥영흥TP#2 T/L","신시흥-영흥#2T/L 정밀점검","신시흥-영흥#2T/L 정밀점검","2019-04-01 08:00","2019-04-05 18:00","2019-04-01 08:00","2019-04-05 18:00","연속",null,null,null,201902150087]
[61,"인천","시흥","신시흥영흥TP#4 T/L","신시흥-영흥#4T/L 정밀점검","신시흥-영흥#4T/L 정밀점검","2019-04-01 08:00","2019-04-05 18:00","2019-04-29 08:00","2019-05-03 18:00","연속",null,null,null,201902150088]
[62,"인천","직할","신부평S/S 345kV #4Sh.R CB (7479)","신부평S/S 7479CB 362kV GIS 정밀점검","신부평S/S 7479CB 362kV GIS 정밀점검(#4Sh.R)","2019-04-01 08:00","2019-04-03 18:00","취소","취소","연속",null,null,null,201902200208]
[63,"경기북부","고양","신덕은동두천CC#1 T/L","서울문산고속도로 지장이설공사 관련 휴전","345kV 신덕은동두천CC#1 T/L No.157-158 안전조치 휴전 (이설구간 154kV 월롱-금촌#2T/L 지장이설개소 4회선구간)","2019-04-27 09:00","2019-05-19 18:00","2019-04-27 09:00","2019-05-19 18:00","연속",null,null,null,201902180109]
[64,"경기북부","고양","신파주S/S #1SVC Tr CB","신파주S/S 345kV SVC용 주변압기 보통점검 - 총액공사","변전총액공사 - 345kV SVC용 주변압기 보통점검 - SVC 부속설비 보통점검 - 23kV #7 FC용 차단기 초기점검 - #7 FC 벨런싱 작업","2019-04-01 10:00","2019-04-04 18:00","취소","취소","연속",null,null,null,201902070168]
[65,"경기북부","고양","신김포신파주#2 T/L","신파주S/S CLR 이음발생 점검 공사","신파주S/S 신김포신파주#2T/L CLR 이음발생 점검","2019-04-22 13:00","2019-04-22 18:00","2019-04-22 13:00","2019-04-22 18:00","당일",null,null,null,201902260325]
[66,"경기북부","고양","신김포신파주#1 T/L","신파주S/S CLR 이음발생 점검 공사","신파주S/S 신김포신파주#1T/L CLR 이음발생 점검","2019-04-22 09:00","2019-04-22 12:00","2019-04-22 09:00","2019-04-22 12:00","당일",null,null,null,201902260324]
[67,"경기북부","구리","동서울미금#1 T/L","미금S/S 345kV #73BAY B/F반 교체공사","미금S/S 345kV #73BAY B/F반 교체","2019-04-22 09:00","2019-04-26 18:00","취소","취소","연속",null,null,null,201812170074]
[68,"경기북부","구리","미금성동#2 T/L","구리전력 19년도 장기사용 성능저하 자기애자 교체공사","구리전력 19년도 장기사용 성능저하 자기애자 교체공사","2019-04-01 09:00","2019-04-01 18:00","2019-04-01 09:00","2019-04-01 18:00","당일",null,null,null,201902140070]
[69,"경기북부","구리","미금S/S #2 M.Tr A","미금S/S 345kV #73BAY B/F반 교체공사","미금S/S 345kV #73BAY B/F반 교체","2019-04-22 09:00","2019-04-26 18:00","2019-04-22 09:00","2019-04-26 18:00","연속",null,null,null,201812170075]
[70,"경기북부","구리","신가평신의정부#1 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 신의정부-내촌#1T/L 정밀점검 상단병가선로","2019-04-11 08:00","2019-04-16 18:00","2019-04-11 08:00","2019-04-16 18:00","연속",null,null,null,201902130633]
[71,"경기북부","구리","신가평S/S 345kV #2 BUS","345kV GIS 정밀점검 공사(19년 계약분)","345kV GIS 정밀점검 공사(19년 계약분) - 신가평S/S 7372 GIS 정밀점검 중 7352DS 정밀","2019-04-08 09:00","2019-04-09 18:00","취소","취소","연속",null,null,null,201902080285]
[72,"경기북부","구리","신가평포천LNGCC#1 T/L","345kV 신가평-포천LNGCC#1T/L 송전선로 정밀점검","- 신가평S/S ~ 포천LNGCC 철탑 177기 송전선로 정밀점검","2019-04-08 08:30","2019-04-23 18:00","2019-04-08 08:30","2019-04-23 18:00","연속",null,null,null,201901140096]
[73,"경기북부","구리","신가평S/S 345kV #2 BUS","345kV GIS 정밀점검 공사(19년 계약분)","345kV GIS 정밀점검 공사(19년 계약분) - 신가평S/S 7472 GIS 정밀점검 중 7452DS 정밀","2019-04-24 09:00","2019-04-25 18:00","2019-04-24 09:00","2019-04-25 18:00","연속",null,null,null,201902080287]
[74,"경기북부","구리","신가평포천LNGCC#2 T/L","345kV 신가평-포천LNGCC#2T/L 송전선로 정밀점검","- 신가평S/S ~ 포천LNGCC 철탑 177기 송전선로 정밀점검","2019-04-24 08:30","2019-05-10 18:00","2019-04-24 08:30","2019-05-10 18:00","연속",null,null,null,201901140097]
[75,"경기북부","구리","신가평신의정부#2 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 신의정부-내촌#2T/L 정밀점검 상단병가선로","2019-04-01 08:00","2019-04-04 18:00","2019-04-01 08:00","2019-04-04 18:00","연속",null,null,null,201902130629]
[76,"경기북부","구리","신포천동두천CC#1 T/L","345kV GIS 정밀점검 공사(19년 계약분)","345kV GIS 정밀점검 공사(19년 계약분) - 신포천S/S 7571, 7500 GIS 정밀점검","2019-04-15 09:00","2019-04-18 18:00","2019-04-15 09:00","2019-04-18 18:00","연속",null,null,null,201902080292]
[77,"경기북부","구리","신포천S/S #1 M.Tr A","신포천S/S 345kV #1M.Tr WTI 불량보수","신포천S/S 345kV #1M.Tr WTI 불량보수 - A상 불량 WTI 교체","2019-04-30 09:00","2019-04-30 18:00","2019-04-30 09:00","2019-04-30 18:00","당일",null,null,null,201902180176]
[78,"경기북부","구리","신포천동두천CC#2 T/L","345kV GIS 정밀점검 공사(19년 계약분)","345kV GIS 정밀점검 공사(19년 계약분) - 신포천S/S 7671, 7600 GIS 정밀점검","2019-04-22 09:00","2019-04-26 18:00","2019-04-22 09:00","2019-04-26 18:00","연속",null,null,null,201902080301]
[79,"경기북부","직할","동두천CC #2S/T 1차 GIS CB (7472)","동두천CC 유압펌프 누유보수","7472CB A상 릴리프벨브 누유보수","2019-04-24 09:00","2019-04-24 14:00","2019-04-24 09:00","2019-04-24 14:00","당일",null,null,null,201902140197]
[80,"경기북부","직할","동두천CC #1TIE-#1G/T 1차 CB (7100)","동두천CC 유압펌프 누유보수","7100CB A상 릴리프벨브 누유보수","2019-04-23 09:00","2019-04-23 14:00","2019-04-23 09:00","2019-04-23 14:00","당일",null,null,null,201902140195]
[81,"경기북부","직할","동두천CC #1S/T 1차 GIS CB (7372)","동두천CC 유압펌프 누유보수","7372CB C상 배관 누유보수","2019-04-23 14:00","2019-04-23 18:00","2019-04-23 14:00","2019-04-23 18:00","당일",null,null,null,201902140196]
[82,"경기북부","직할","신의정부양주#2 T/L","345kV신의정부양주#2T/L OPGW 증설공사","가공지선(AWS 120SQ)를 OPGW 120SQ로 교체","2019-04-22 09:00","2019-05-05 18:00","2019-04-22 09:00","2019-05-05 18:00","연속",null,null,null,201902110078]
[83,"경기북부","직할","양주S/S #1 M.Tr A","양주S/S 옥외철구 GIS화 전력구공사","양주S/S #1 M.Tr A 인출측 전력구공사","2019-04-27 09:00","2019-04-29 18:00","2019-04-27 09:00","2019-04-29 18:00","연속",null,null,null,201901110019]
[84,"경기북부","직할","양주S/S #2 M.Tr A","양주S/S 345kV M.Tr 3차측 SIS화 공사","- #2Main, #2Sh.R-1~2, #2STr, #2PT 총 5CCT 및 큐비클 설치","2019-04-04 09:00","2019-04-13 18:00","2019-04-04 09:00","2019-04-13 18:00","연속",null,null,null,201902180024]
[85,"경기북부","직할","양주S/S #3 M.Tr A","양주S/S 옥외철구 GIS화 전력구공사","양주S/S #3 M.Tr A 인출측 전력구공사","2019-04-01 09:00","2019-04-03 18:00","2019-04-01 09:00","2019-04-03 18:00","연속",null,null,null,201901110014]
[86,"경기북부","직할","양주S/S #4 M.Tr A","양주S/S 345kV M.Tr 3차측 SIS화 공사","-#4Main, #4Sh.R, #4PT 총 3CCT 및 큐비클 설치","2019-04-14 09:00","2019-04-23 18:00","2019-04-14 09:00","2019-04-23 18:00","연속",null,null,null,201902180026]
[87,"경기북부","직할","양주S/S #2 M.Tr A","양주S/S 옥외철구 GIS화 전력구공사","양주S/S #2 M.Tr A 인출측 전력구공사","2019-04-24 09:00","2019-04-26 18:00","2019-04-24 09:00","2019-04-26 18:00","연속",null,null,null,201901110018]
[88,"경기북부","직할","양주S/S #4 M.Tr A","양주S/S 옥외철구 GIS화 전력구공사","양주S/S #4 M.Tr A 인출측 전력구공사","2019-04-30 09:00","2019-05-02 18:00","2019-04-30 09:00","2019-05-02 18:00","연속",null,null,null,201901110020]
[89,"경기북부","직할","신의정부미금#1 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33,No.34~38","2019-04-02 09:00","2019-04-08 18:00","2019-04-02 09:00","2019-04-08 18:00","연속"]
[90,"경기북부","구리","동서울미금#1 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33,No.34~38 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2019-04-06 09:00","2019-04-08 18:00","취소","취소","매일"]
[91,"경기북부","구리","동서울미금#2 T/L","345kV 신의정부-미금T/L 전선접속개소 전선교체공사","345kV 신의정부-미금#1,2T/L 전력선 교체: No.1.2~4,No.29~33,No.34~38 (상단 345kV 신의정부-미금#1,2T/L 작업 안전을 위한 병행하단 휴전)","2019-04-06 09:00","2019-04-08 18:00","취소","취소","매일"]
[92,"경기북부","직할","양주S/S 345kV #4 Sh.R CB","양주변전소 옥외철구 GIS화 공사","가공지선 철거","2019-04-03 09:00","2019-04-03 18:00","2019-04-03 09:00","2019-04-03 18:00","당일"]
[93,"경기","군포","서서울#2S/S 345kV 서서울2-신성남#2T/L CB (7B71)","서서울#2S/S 345kV 7B71 GIS 하자점검","서서울#2S/S 345kV 7B71 GIS 하자점검","2019-04-11 09:00","2019-04-13 18:00","취소","취소","당일"]
[94,"경기","군포","서서울2S/S 345kV #71 BUS GIS","서서울2S/S 362kV GIS DS 제작사 하자보수(#71BUS)","서서울2S/S 362kV GIS DS 제작사 하자보수(#71BUS) - 7A51, 7B51 DS","2019-04-08 09:00","2019-04-13 18:00","2019-04-08 09:00","2019-04-13 18:00","연속"]
[95,"경기","군포","서서울#2S/S 345kV 서서울2-신성남#1T/L CB (7A71)","서서울#2S/S 345kV 7A71 GIS 하자점검","서서울#2S/S 345kV 7A71 GIS 하자점검","2019-04-08 09:00","2019-04-10 18:00","취소","취소","당일"]
[96,"경기","군포","서서울S/S #4 M.Tr","'19년 군포P/O 변전정비회사 총액공사","- 345kV 7872,7800 GIS 보통점검, 154kV 6444 GIS 초기점검","2019-04-29 09:30","2019-04-29 18:00","2019-04-29 09:30","2019-04-29 18:00","당일"]
[97,"경기","군포","서서울S/S #3 M.Tr","154kV 남군포S/S 건설사업","o서서울S/S~남군포S/S간 신설 변전설비 무부하 가압 - 서서울~남군포#1.2T/L","2019-04-23 09:00","2019-04-26 18:00","취소","취소","연속"]
[98,"경기","군포","신안산S/S 345kV #70 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","○ 362kV 40kA 8CB 철거, 63kA 11CB 설치 - PT반 제어케이블 이설 휴전","2019-04-27 09:00","2019-04-28 18:00","2019-04-25 09:00","2019-04-26 18:00","연속"]
[99,"경기","군포","화성신안산 T/L","345kV 신안산S/S 용량부족 GIS 대체공사","○ 362kV 40kA 8CB 철거, 63kA 11CB 설치 - 70Bay #75BUS측 무부하가압","2019-04-25 18:00","2019-04-26 18:00","2019-04-23 09:00","2019-04-26 18:00","연속"]
[100,"경기","군포","신안산S/S 345kV #75 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","○ 362kV 40kA 8CB 철거, 63kA 11CB 설치 - 70Bay GIS ~ #75BUS 모선 Docking","2019-04-20 09:00","2019-04-26 18:00","2019-04-18 09:00","2019-04-24 18:00","연속"]
[101,"경기","군포","화성신안산 T/L","345kV 신안산S/S 용량부족 GIS 대체공사","○ 362kV 40kA 8CB 철거, 63kA 11CB 설치 - 70Bay GIS #70BUS측 무부하가압","2019-04-18 18:00","2019-04-19 18:00","2019-04-16 09:00","2019-04-17 18:00","연속"]
[102,"경기","군포","신안산S/S 345kV #70 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","○ 362kV 40kA 8CB 철거, 63kA 11CB 설치 - 70Bay GIS ~ #70BUS 모선 Docking","2019-04-13 09:00","2019-04-19 18:00","2019-04-11 09:00","2019-04-17 18:00","연속"]
[103,"경기","군포","신안산S/S #4 M.Tr A","2019년 군포 154kV GIS정밀점검 공사 (대상 2차 GIS)","2019년 군포 154kV GIS정밀점검 공사 - #4M.Tr 2차 GIS 정밀점검","2019-04-10 09:00","2019-04-12 20:00","2019-04-10 09:00","2019-04-12 20:00","연속"]
[104,"경기","군포","화성신안산 T/L","345kV 신안산S/S 용량부족 GIS 대체공사","○ 362kV 40kA 8CB 철거, 63kA 11CB 설치 - 송전선로 인출변경 및 사용전검사, 실부하가압","2019-04-30 09:00","2019-05-12 18:00","2019-04-30 09:00","2019-05-15 18:00","연속"]
[105,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 #61BUS 무부하가압용 주변압기","2019-04-20 16:00","2019-04-21 16:00","취소","취소","연속"]
[106,"경기","동부","곤지암동서울#2 T/L","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS 무부하가압용 수전선로 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2019-04-13 18:00","2019-04-14 18:00","2019-04-13 18:00","2019-04-14 18:00","연속"]
[107,"경기","동부","곤지암S/S 345kV #2 BUS","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #2BUS측 설치 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2019-04-08 09:30","2019-04-14 18:00","2019-04-08 09:30","2019-04-14 18:00","연속"]
[108,"경기","동부","곤지암동서울#2 T/L","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS 무부하가압용 수전선로 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2019-04-06 18:00","2019-04-07 18:00","2019-04-06 18:00","2019-04-07 18:00","연속"]
[109,"경기","동부","곤지암S/S 345kV #1 BUS","곤지암S/S 362kV GIS 설치공사","곤지암S/S 362kV GIS 설치공사 관련 #1BUS측 설치 - 362kV GIS(63kA, 6300A) 2CB 설치(76Bay)","2019-04-01 09:30","2019-04-07 18:00","2019-04-01 09:30","2019-04-07 18:00","연속"]
[110,"경기","성남","서안성신진천#2 T/L","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ71Bay 용량대체 ㅇ 기타 부대공사 x 1식 ㅇ 무부하 및 실부하 가압","2019-04-01 09:00","2019-05-22 09:00","취소","취소","연속"]
[111,"경기","성남","서안성S/S #2 M.Tr A","19년 345kV GIS 정밀점검 공사","- 서안성S/S #1M.Tr 정밀점검 - 2차 GIS 정밀점검 - #2S.Tr 보통","2019-04-15 09:00","2019-04-26 18:00","2019-04-15 09:00","2019-04-26 18:00","연속"]
[112,"경기","성남","신안성서안성#1 T/L","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ무부하 가압(7151DS 전단까지)","2019-04-27 09:00","2019-04-28 09:00","취소","취소","연속"]
[113,"경기","성남","서안성S/S #1 M.Tr A","19년 345kV GIS 정밀점검 공사","- 서안성S/S #1M.Tr 정밀점검 - #1S.Tr 보통","2019-04-01 09:00","2019-04-12 18:00","2019-04-01 09:00","2019-04-12 18:00","연속"]
[114,"경기","성남","서안성S/S 345kV #1 BUS","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ71Bay GIS(7171, 7500) 용량대체 ㅇ 기타 부대공사 x 1식","2019-04-01 09:00","2019-04-28 09:00","취소","취소","연속"]
[115,"경기","성남","서안성S/S #3 M.Tr A","19년 345kV GIS 정밀점검 공사","- 서안성S/S #3M.Tr 정밀점검 - 2차 GIS 정밀점검","2019-04-29 09:00","2019-05-10 18:00","2019-04-29 09:00","2019-05-10 18:00","연속"]
[116,"경기","성남","서안성S/S #1 M.Tr A","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ 71Bay 용량대체 ㅇ 기타 부대공사 x 1식","2019-04-28 09:00","2019-05-22 09:00","취소","취소","연속"]
[117,"경기","성남","서안성S/S 345kV #2 BUS","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ71Bay GIS(7172) 용량대체 ㅇ 기타 부대공사 x 1식","2019-04-28 09:00","2019-05-20 09:00","취소","취소","연속"]
[118,"경기","성남","신성남S/S #3 M.Tr A","19년 성남전력지사 변전협력총액공사","3M.Tr 2차 GIS(초기) -7300,7372 조작 -부싱절연유채유","2019-04-23 09:00","2019-04-23 18:00","2019-04-23 09:00","2019-04-23 18:00","당일"]
[119,"경기","성남","신성남S/S #5 M.Tr A","19년 성남전력지사 변전협력총액공사","- #5M.Tr 2차 GIS 보통점검 - 7600,7672 조작시험, 3차 CB 조작시험 - 부싱절연유채유 - 1차 LA 초기","2019-04-25 09:00","2019-04-25 18:00","2019-04-25 09:00","2019-04-25 18:00","당일"]
[120,"경기","성남","신수원S/S 345kV #1 BUS","신수원S/S 345kV 용량부족 GIS 대체공사","- 345kV GIS(40kA, 4000A) × 14CB 철거 - 345kV GIS(63kA, 6300A) × 14CB 신설","2019-04-01 08:00","2019-04-04 18:00","2019-04-01 08:00","2019-04-04 18:00","연속"]
[121,"경기","성남","신수원S/S #3 M.Tr A","신수원S/S 345kV 용량부족 GIS 대체공사","- 345kV GIS(40kA, 4000A) × 14CB 철거 - 345kV GIS(63kA, 6300A) × 14CB 신설","2019-04-01 08:00","2019-04-30 18:00","2019-04-27 08:00","2019-06-23 18:00","연속"]
[122,"경기","성남","신수원S/S 345kV #2 BUS","신수원S/S 345kV 용량부족 GIS 대체공사","- 345kV GIS(40kA, 4000A) × 14CB 철거 - 345kV GIS(63kA, 6300A) × 14CB 신설","2019-04-05 08:00","2019-04-08 18:00","취소","취소","연속"]
[123,"경기","성남","신수원S/S 345kV #1 BUS","신수원S/S 345kV 용량부족 GIS 대체공사","- 345kV GIS(40kA, 4000A) × 14CB 철거 - 345kV GIS(63kA, 6300A) × 14CB 신설","2019-04-27 08:00","2019-04-28 18:00","2019-04-25 08:00","2019-04-26 18:00","연속"]
[124,"경기","성남","신수원S/S 345kV #2 BUS","신수원S/S 345kV 용량부족 GIS 대체공사","- 345kV GIS(40kA, 4000A) × 14CB 철거 - 345kV GIS(63kA, 6300A) × 14CB 신설","2019-04-29 08:00","2019-04-30 18:00","2019-04-27 08:00","2019-04-30 18:00","연속"]
[125,"경기","성남","신안성S/S 신안성-신성남#1T/L-TIE CB (7500)","19년 345kV GIS 정밀점검","신안성S/S 신안성-신성남#1T/L TIE GIS 7500 정밀점검","2019-04-15 09:00","2019-04-21 18:00","2019-04-15 09:00","2019-04-21 18:00","연속"]
[126,"경기","성남","신안성S/S #2 M.Tr 2차 CB (7571)","19년 345kV GIS 정밀점검","신안성S/S #2M.Tr 2차 정밀점검","2019-04-08 09:00","2019-04-14 18:00","2019-04-08 09:00","2019-04-14 18:00","연속"]
[127,"경기","성남","신안성S/S 신안성-신성남#2T/L-TIE CB (7600)","19년 345kV GIS 정밀점검","신안성S/S 신안성-신성남#2T/L TIE GIS 7600 정밀점검","2019-04-29 09:00","2019-05-05 18:00","2019-04-29 09:00","2019-05-05 18:00","연속"]
[128,"경기","성남","신안성S/S 신안성-신성남#1T/L CB (7572)","19년 345kV GIS 정밀점검","신안성S/S 신안성-신성남#1T/L GIS 7572 정밀점검","2019-04-22 09:00","2019-04-28 18:00","2019-04-22 09:00","2019-04-28 18:00","연속"]
[129,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울#2T/L EBA 자기애관 교체공사","탄벌지구 No.67CH 자기애관 교체(3상)","2019-04-02 08:00","2019-04-04 18:00","2019-04-02 08:00","2019-04-04 18:00","연속"]
[130,"경기","성남","신용인S/S 신용인-삼성T/L GIS","19년 성남전력지사 변전협력총액공사","- 7671,7600 하자점검 - LA 대체, CVT 보통점검","2019-04-15 09:00","2019-04-15 18:00","2019-04-15 09:00","2019-04-15 18:00","당일"]
[131,"경기","성남","신용인S/S 345kV #2 BUS","신용인S/S #4M.Tr 증설공사 무부하가압 및 사용전검사","345/154kV M.Tr x 3대 설치 362kV GIS x 2CB 설치 170kV GIS x 4CCT 설치 기타 부대작업 x 1식","2019-04-30 14:00","2019-04-30 18:00","2019-04-30 14:00","2019-04-30 18:00","연속"]
[132,"경기","성남","신용인동서울#1 T/L","신용인S/S #4M.Tr 증설공사 무부하가압 및 사용전검사","345/154kV M.Tr x 3대 설치 362kV GIS x 2CB 설치 170kV GIS x 4CCT 설치 기타 부대작업 x 1식","2019-04-30 14:00","2019-05-03 18:00","2019-04-30 14:00","2019-05-03 18:00","연속"]
[133,"경기","성남","신용인S/S 345kV #1 BUS","신용인S/S #4M.Tr 증설공사 무부하가압 및 사용전검사","345/154kV M.Tr x 3대 설치 362kV GIS x 2CB 설치 170kV GIS x 4CCT 설치 기타 부대작업 x 1식","2019-04-30 18:00","2019-05-03 18:00","2019-04-30 18:00","2019-05-03 18:00","연속"]
[134,"경기","직할","화성S/S 345kV #70 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ #70-71 SEC GIS 교체관련 #70BUS측 모선연결","2019-04-12 09:00","2019-04-22 18:00","취소","취소","연속"]
[135,"경기","직할","화성S/S 345kV #2LCR 75BUS GIS CB (7577)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ #1CLR 이설설치관련 안전이격거리 확보","2019-04-11 09:00","2019-04-11 18:00","2019-04-29 09:00","2019-04-30 18:00","당일"]
[136,"경기","직할","화성S/S 345kV #71 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ #1CLR 전력케이블 내압시험","2019-04-23 09:00","2019-04-24 18:00","취소","취소","연속"]
[137,"경기","직할","화성S/S 345kV #71 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ #1CLR , GIS 및 70-71GIS 최초가압","2019-04-28 10:00","2019-04-29 10:00","취소","취소","연속"]
[138,"경기","직할","화성신안산 T/L","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ #1CLR, GIS 및 #70-71 SEC GIS 최초가압","2019-04-28 10:00","2019-04-29 10:00","취소","취소","연속"]
[139,"경기","직할","화성S/S 345kV #70 BUS","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ #1CLR, GIS 및 70-71 SEC GIS 최초가압","2019-04-28 10:00","2019-04-29 10:00","취소","취소","연속"]
[140,"경기","직할","아산화성#2 T/L","345kV 신평택-화성T/L 건설관련 안전이격 확보공사","아산화성 No.128 인클로징공사 (19m → 25m)","2019-04-02 07:00","2019-04-07 18:00","2019-04-02 07:00","2019-04-07 18:00","연속"]
[141,"경기","직할","화성S/S #2 CLR 76BUS GIS CB (7577)","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ #1CLR 이설설치관련 안전이격거리 확보","2019-04-11 09:00","2019-04-11 18:00","2019-04-29 09:00","2019-04-30 18:00","당일"]
[142,"경기","직할","화성서서울#1 T/L","화성S/S 용량부족 차단기대체 및 SW증설 공사","○ 40/50kA GIS → 63kA GIS 용량대체(26CB) ○ #70-71 SEC GIS 교체관련 70BUS측 모선무부하 가압","2019-04-21 11:00","2019-04-22 11:00","취소","취소","연속"]
[143,"충북","직할","신제천동해#2 T/L","345kV 신제천S/S TCSC 설치공사","TCSC 592.3MVar × 2조 보호배전반 설치 × 1식 - 신제천, 동해S/S 신제천동해#1,2T/L 송전선로보호반 대체 - 신제천S/S 신제천동해#1,2T/L GIB용 보호반 설치","2019-04-22 09:00","2019-04-26 18:00","2019-05-06 09:00","2019-05-10 18:00","연속",null,null,null,201902110213]
[144,"충북","직할","신제천동해#1 T/L","345kV 신제천S/S TCSC 설치공사","TCSC 592.3MVar × 2조 보호배전반 설치 × 1식 - 신제천, 동해S/S 신제천동해#1,2T/L 송전선로보호반 대체 - 신제천S/S 신제천동해#1,2T/L GIB용 보호반 설치","2019-04-15 09:00","2019-04-19 18:00","2019-04-29 09:00","2019-05-03 18:00","연속",null,null,null,201902110224]
[145,"충북","직할","신제천S/S 345kV #1 BUS","신제천S/S 345kV #1BUS부 DS 제작사(LS) 하자대체","- 345kV 수평 EDS 제작사 하자대체 - 대상 : 73351,7451,7651,7751,7951,7A51","2019-04-01 09:00","2019-04-13 18:00","2019-04-01 09:00","2019-04-13 18:00","연속",null,null,null,201902130368]
[146,"충북","직할","곤지암신충주#1 T/L","345kV 신충주S/S #4M.Tr 증설공사","345kV 76BAY 증설분 #1 BUS측~#4M.Tr 무부하가압선로","2019-04-09 15:00","2019-04-10 15:00","2019-04-09 15:00","2019-04-10 15:00","연속",null,null,null,201901100118]
[147,"충북","직할","신충주S/S 345kV #1 BUS","345kV 신충주S/S #4M.Tr 증설공사","345kV 76 BAY #1 모선 GIB 연결, 무부하(4 M.Tr 포함)","2019-04-04 09:00","2019-04-10 15:00","2019-04-04 09:00","2019-04-10 15:00","연속",null,null,null,201902120507]
[148,"충북","직할","신충주S/S 345kV #2 BUS","345kV 신충주S/S #4M.Tr 증설공사","345kV 76 BAY #2 모선 GIB 연결, 무부하(4 M.Tr 포함)","2019-04-10 15:00","2019-04-17 15:00","2019-04-10 15:00","2019-04-17 15:00","연속",null,null,null,201902120508]
[149,"충북","직할","신충주S/S #3 M.Tr A","345kV 신충주S/S #4M.Tr 증설공사","345kV 76BAY 증설분 #2 BUS측~#4M.Tr 무부하가압선로(선로단독운전시 #2BUS측 #3 M.Tr 도 휴전수반)","2019-04-16 15:00","2019-04-17 15:00","취소","취소","연속",null,null,null,201902120514]
[150,"충북","직할","곤지암신충주#1 T/L","345kV 신충주S/S #4M.Tr 증설공사","345kV 76BAY 증설분 #2 BUS측~#4M.Tr 무부하가압선로","2019-04-16 15:00","2019-04-17 15:00","2019-04-16 15:00","2019-04-17 15:00","연속",null,null,null,201902120513]
[151,"충북","청주","신옥천세종#1 T/L","345kV 신옥천-세종T/L 초기점검","345kV 신옥천-세종T/L #1 No.49~79호 345kV 세종-청원T/L #2 No.1~30호 (병가) 지지물 30기 및 전력선 ST/AW 410X2B 12.398km 초기점검","2019-04-22 07:00","2019-04-30 18:00","2019-04-22 07:00","2019-04-30 18:00","매일",null,null,null,201902120511]
[152,"충북","청주","신옥천신남원#1 T/L","2018-2019년 송전정비 협력회사 총액공사(청주전력)","345kV 신옥천-신남원#1T/L - 전력선 교체 : No.226.1 ~ 227(내장~내장, 1구간) - 가공지선 교체 : No.220 ~ 223 - 표시구 설치 : No.219 ~ 220, No.221 ~ 222, No.246 ~ 247","2019-04-19 07:30","2019-04-21 19:00","2019-04-19 07:30","2019-04-21 19:00","연속",null,null,null,201902120176]
[153,"충북","청주","신옥천신계룡 T/L","18~19년 청주전력 변전협력회사 총액공사","신옥천S/S 345kV 신옥천신계룡T/L 7772, 7700 GIS 초기점검","2019-04-04 09:30","2019-04-05 18:00","2019-04-04 09:30","2019-04-05 18:00","연속",null,null,null,201902120397]
[154,"충북","청주","신옥천신남원#2 T/L","2018-2019년 송전정비 협력회사 총액공사(청주전력)","345kV 신옥천-신남원 #2 T/L - 전력선 교체 : No.226.1 ~ 227(내장~내장.1구간) - 표시구 설치 : No.219 ~ 220, No.221 ~ 222, No.246 ~ 247","2019-04-22 07:30","2019-04-23 19:00","2019-04-22 07:30","2019-04-23 19:00","연속",null,null,null,201902120177]
[155,"충북","청주","청원S/S #1 M.Tr A","18~19년 청주전력 변전협력회사 총액공사","청원S/S 345kV #1M.Tr 1차 GIS 초기점검 및 M.Tr 3차측 지지애자 교체","2019-04-01 09:30","2019-04-02 18:00","2019-04-01 09:30","2019-04-02 18:00","연속",null,null,null,201902120381]
[156,"충북","청주","청원S/S TIE-#3 M.Tr 1차 GIS","18~19년 청주전력 변전협력회사 총액공사","청원S/S 345kV TIE-#3M.Tr 1차 GIS A상 CB Airing Valve 누기보수","2019-04-03 09:30","2019-04-03 18:00","2019-04-03 09:30","2019-04-03 18:00","당일",null,null,null,201902120391]
[157,"충북","청주","세종청원#2 T/L","345kV 세종-청원T/L 초기점검","345kV 세종-청원T/L #2 No.1~30호 345kV 신옥천-세종T/L #1 No.49~79호(병가) 지지물 30기 및 전력선 ST/AW 410X2B 12.398km 초기점검","2019-04-22 07:00","2019-04-30 18:00","2019-04-22 07:00","2019-04-30 18:00","매일",null,null,null,201902120548]
[158,"충북","충주","신진천S/S #2 M.Tr A","18-19년 충주전력지사 변전정비 총액공사","신진천S/S 345kV #2M.Tr 보호 PNL 대체","2019-04-15 09:00","2019-04-18 18:00","2019-04-15 09:00","2019-04-18 18:00","연속",null,null,null,201902110702]
[159,"대전충남","대전","신계룡S/S #1 M.Tr A","신계룡S/S 345kV #1M.Tr 보호반 교체 및 병행작업","신계룡S/S 345kV #1M.Tr 보호반 교체 및 병행작업","2019-04-08 09:00","2019-04-12 18:00","2019-04-08 09:00","2019-04-12 18:00","연속",null,null,null,201902120255]
[160,"대전충남","서산","당진T/P #1TIE Tr 2차 CB (7271)","19년도 서산P/O 735/345 GIS 점검공사","345kV GIS 정밀점검","2019-04-15 09:00","2019-04-19 18:00","2019-04-29 09:00","2019-05-03 18:00","연속",null,null,null,201902120095]
[161,"대전충남","서산","북당진S/S GSEPS #2호기 -TIE CB (7500)","19년도 변전정비회사 총액공사","345kV GIS 보통점검","2019-04-02 09:00","2019-04-02 18:00","2019-04-02 09:00","2019-04-02 18:00","당일",null,null,null,201902120083]
[162,"대전충남","서산","북당진S/S 개폐소-북당진T/L CB (7171)","19년도 변전정비회사 총액공사","345kV GIS 보통점검","2019-04-03 09:00","2019-04-03 18:00","2019-04-03 09:00","2019-04-03 18:00","당일",null,null,null,201902120086]
[163,"대전충남","서산","북당진S/S 개폐소#1-현대제철T/L TIE CB (7100)","19년도 변전정비회사 총액공사","345kV GIS 보통점검","2019-04-04 09:00","2019-04-04 18:00","2019-04-04 09:00","2019-04-04 18:00","당일",null,null,null,201902120089]
[164,"대전충남","서산","북당진S/S 북당진-현대제철T/L CB (7172)","19년도 변전정비회사 총액공사","345kV GIS 보통점검","2019-04-05 09:00","2019-04-05 18:00","2019-04-05 09:00","2019-04-05 18:00","당일",null,null,null,201902120092]
[165,"대전충남","서산","북당진S/S GSEPS #2호기 CB (7572)","19년도 변전정비회사 총액공사","345kV GIS 보통점검","2019-04-01 09:00","2019-04-01 18:00","2019-04-01 09:00","2019-04-01 18:00","당일",null,null,null,201902120081]
[166,"대전충남","서산","신서산S/S #3 Sh.R-신서산태안TP#2T/L CB (7500)","19년도 서산P/O 735/345 GIS 점검공사","345kV GIS 정밀점검","2019-04-22 09:00","2019-04-26 18:00","2019-04-22 09:00","2019-04-26 18:00","연속",null,null,null,201902120099]
[167,"대전충남","서산","신서산신당진#2 T/L","345kV 신서산-신당진T/L 피뢰기 설치공사","345kV 신서산-신당진T/L 피뢰기 설치공사 No.1~42","2019-04-08 07:30","2019-04-17 18:00","2019-04-08 07:30","2019-04-17 18:00","매일",null,null,null,201902130591]
[168,"대전충남","서산","태안T/P 70-71-0 SEC CB (70-71-0)","19년도 변전정비회사 총액공사","345kV GIS 보통점검","2019-04-29 09:00","2019-04-29 18:00","2019-04-29 09:00","2019-04-29 18:00","당일",null,null,null,201902120113]
[169,"대전충남","서산","태안T/P 75-76-0 SEC CB (75-76-0)","19년도 변전정비회사 총액공사","345kV GIS 초기점검","2019-04-30 09:00","2019-04-30 18:00","2019-04-30 09:00","2019-04-30 18:00","당일",null,null,null,201902120117]
[170,"대전충남","서산","태안T/P #2 M.Tr CB","최초가압(태안화력S/Y #2M.Tr 증설공사)","345kV M.Tr * 1Bank 설치 345kV GIS * 1CB 설치 154kV GIS * 1CCT 설치 기타부대작업 * 1식","2019-04-29 10:00","2019-04-30 18:00","취소","취소","연속",null,null,null,201901300032]
[171,"대전충남","서산","태안T/P 345kV #72 BUS","최초가압(태안화력S/Y #2M.Tr 증설공사)","345kV M.Tr * 1Bank 설치 345kV GIS * 1CB 설치 154kV GIS * 1CCT 설치 기타부대작업 * 1식","2019-04-29 10:00","2019-04-30 18:00","2019-04-29 10:00","2019-04-30 18:00","연속",null,null,null,201902130156]
[172,"대전충남","서산","태안T/P 7호기 1차 CB (7772)","345kV 태안화력S/Y #2M.Tr 증설공사","1. #77BAY B/F반 대체(2CB용 →3CB용) 2. 기타부대작업","2019-04-06 09:00","2019-04-17 18:00","2019-04-06 09:00","2019-04-17 18:00","연속",null,null,null,201901300028]
[173,"대전충남","서산","신서산태안화력#1 T/L","345kV 신서산-태안화력#1T/L 정밀점검","345kV 신서산-태안화력#1T/L 정밀점검 - No.0-1-136(137기)","2019-04-18 07:00","2019-04-30 18:00","2019-04-18 07:00","2019-04-30 18:00","연속",null,null,null,201902110300]
[174,"대전충남","서산","태안T/P 4호기 1차 CB(7472) (7472)","19년도 변전정비회사 총액공사","345kV GIS 보통점검","2019-04-17 09:00","2019-04-17 18:00","2019-04-17 09:00","2019-04-17 18:00","당일",null,null,null,201902120170]
[175,"대전충남","서산","태안T/P TIE - 4호기 1차 CB(7400) (7400)","19년도 변전정비회사 총액공사","345kV GIS 보통점검","2019-04-18 09:00","2019-04-18 18:00","2019-04-18 09:00","2019-04-18 18:00","당일",null,null,null,201902120171]
[176,"대전충남","서산","태안T/P TIE-1호기 1차CB(신) (7100)","19년도 변전정비회사 총액공사","345kV GIS 보통점검","2019-04-19 09:00","2019-04-19 18:00","2019-04-19 09:00","2019-04-19 18:00","당일",null,null,null,201902120173]
[177,"대전충남","아산","청양신온양#1 T/L","[송전]345kV 청양-신온양T/L 120호 안전이격확보공사","- 기설 120호 철거/신설 1기 - 가철탑 철거/신설 1기 - 기타 부대공사","2019-04-08 08:00","2019-04-12 18:00","2019-04-08 08:00","2019-04-12 18:00","연속",null,null,null,201902120286]
[178,"대전충남","아산","청양신온양#2 T/L","[송전]345kV 청양-신온양T/L 120호 안전이격확보공사","- 기설 120호 철거/신설 1기 - 가철탑 철거/신설 1기 - 기타 부대공사","2019-04-01 08:00","2019-04-05 18:00","2019-04-01 08:00","2019-04-05 18:00","연속",null,null,null,201902120285]
[179,"대전충남","아산","신탕정S/S #3 M.Tr A","신탕정S/S 345kV #3M.Tr 보통점검 등","1. 345KV #3M.Tr 보통점검 2. 1차 7371 GIS(초기점검) 3. 2차 6344 GIS(보통점검)","2019-04-02 09:00","2019-04-03 18:00","2019-04-02 09:00","2019-04-03 18:00","연속",null,null,null,201812240091]
[180,"대전충남","아산","아산S/S #1 M.Tr A","아산S/S 345kV #1M.Tr 보통점검 등","○아산S/S 345kV #1M.Tr 보통점검 등","2019-04-04 09:00","2019-04-05 18:00","2019-04-04 09:00","2019-04-05 18:00","연속",null,null,null,201902150223]
[181,"대전충남","아산","신서산아산#2 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-04-18 07:00","2019-04-27 18:00","취소","취소","연속",null,null,null,201902130254]
[182,"대전충남","아산","신서산아산#1 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-04-08 07:00","2019-04-17 18:00","취소","취소","연속",null,null,null,201902130250]
[183,"대전충남","청양","보령C/C #1 M.Tr 1차 CB (7172)","보령C/C 362kV GIS 보통점검(7172)","보령C/C 362kV GIS 보통점검(7172)","2019-04-11 09:00","2019-04-11 18:00","2019-04-11 09:00","2019-04-11 18:00","당일",null,null,null,201902110175]
[184,"대전충남","청양","보령C/C #4 M.Tr 1차 CB (7472)","보령C/C 362kV GIS 보통점검(7472)","보령C/C 362kV GIS 보통점검","2019-04-09 09:00","2019-04-09 18:00","2019-04-09 09:00","2019-04-09 18:00","당일",null,null,null,201902120110]
[185,"대전충남","청양","보령C/C 보령연락#1T/L-#1 M.Tr 1차 CB (7100)","보령C/C 362kV GIS 보통점검(7100)","보령C/C 362kV GIS 보통점검(7100)","2019-04-10 09:00","2019-04-10 18:00","2019-04-10 09:00","2019-04-10 18:00","당일",null,null,null,201902110178]
[186,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-04-03 09:00","2019-04-03 18:00","2019-04-03 09:00","2019-04-03 18:00","당일",null,null,null,201902080047]
[187,"대전충남","청양","아산보령화력#2 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-04-04 09:00","2019-04-04 18:00","2019-04-04 09:00","2019-04-04 18:00","당일",null,null,null,201902080051]
[188,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-04-13 09:00","2019-04-13 18:00","2019-04-13 09:00","2019-04-13 18:00","당일",null,null,null,201902080046]
[189,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-04-15 09:00","2019-04-15 18:00","2019-04-15 09:00","2019-04-15 18:00","당일",null,null,null,201902080048]
[190,"대전충남","청양","아산보령화력#2 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-04-30 09:00","2019-04-30 18:00","2019-04-30 09:00","2019-04-30 18:00","당일",null,null,null,201902080054]
[191,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-04-02 09:00","2019-04-02 18:00","2019-04-02 09:00","2019-04-02 18:00","당일",null,null,null,201902080040]
[192,"대전충남","청양","청양보령화력#1 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-04-01 09:00","2019-05-17 18:00","2019-04-01 09:00","2019-05-17 18:00","연속",null,null,null,201902080027]
[193,"대전충남","청양","보령T/P #6 M.Tr 1차 CB (7671)","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-04-01 09:00","2019-05-17 18:00","2019-04-01 09:00","2019-05-17 18:00","연속",null,null,null,201902120140]
[194,"대전충남","청양","아산보령화력#2 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-04-12 09:00","2019-04-12 18:00","2019-04-12 09:00","2019-04-12 18:00","당일",null,null,null,201902080053]
[195,"대전충남","청양","신옥천청양 T/L","[송전]345kV 신옥천-청양T/L 지장철탑이설공사[요청자직접시행]","ㅇ 요청자(성인산업) 직접시행 지장이설공사 ㅇ 철탑 : 3기 철거(No.145,146,147), 4기 설치(No.145,146,146-1,147) ㅇ 전력선 : ACSR480 x 4B x 2C (선로길이 : 1.802km x 2C) ㅇ 가철탑 2기 설치철거 외 기타 부대공사 시행","2019-04-06 07:00","2019-04-13 18:00","취소","취소","연속",null,null,null,201902130308]
[196,"대전충남","청양","신계룡청양 T/L","[송전]345kV 신옥천-청양T/L 지장철탑이설공사[요청자직접시행]","ㅇ 요청자(성인산업) 직접시행 지장이설공사 ㅇ 철탑 : 3기 철거(No.145,146,147), 4기 설치(No.145,146,146-1,147) ㅇ 전력선 : ACSR480 x 4B x 2C (선로길이 : 1.802km x 2C) ㅇ 가철탑 2기 설치철거 외 기타 부대공사 시행","2019-04-14 07:00","2019-04-18 18:00","취소","취소","연속",null,null,null,201902130304]
[197,"대전충남","청양","청양S/S #1 M.Tr A","2019년 청양S/S #1M.Tr 및 OLTC 정밀점검 공사","#1M.Tr 및 OLTC 정밀점검","2019-04-15 09:00","2019-05-03 18:00","2019-04-27 09:00","2019-05-10 18:00","연속",null,null,null,201902070017]
[198,"대전충남","청양","신계룡청양 T/L","[송전]345kV 신옥천-청양T/L 지장철탑이설공사[요청자직접시행]","ㅇ 요청자(성인산업) 직접시행 지장이설공사 ㅇ 철탑 : 3기 철거(No.145,146,147), 4기 설치(No.145,146,146-1,147) ㅇ 전력선 : ACSR480 x 4B x 2C (선로길이 : 1.802km x 2C) ㅇ 가철탑 2기 설치철거 외 기타 부대공사 시행","2019-04-01 07:00","2019-04-05 18:00","취소","취소","연속",null,null,null,201902130302]
[199,"전북","군산","군산새만금#1 T/L","YPP 송전선로 보호배전반 성능개선","YPP 송전선로 보호배전반 로직변경","2019-04-23 10:00","2019-04-23 18:00","2019-04-23 10:00","2019-04-23 18:00","당일",null,null,null,201901310030]
[200,"전북","군산","군산새만금#2 T/L","YPP 송전선로 보호배전반 성능개선","YPP 송전선로 보호배전반 로직변경","2019-04-24 10:00","2019-04-24 18:00","2019-04-24 10:00","2019-04-24 18:00","당일",null,null,null,201901310031]
[201,"전북","군산","새만금S/S #1Sh.R CB","관내주변압기 점검공사","1. 리액터 초기점검 2. 345kV GIS 초기점검","2019-04-17 09:30","2019-04-18 18:00","2019-04-17 09:30","2019-04-18 18:00","연속",null,null,null,201901180114]
[202,"전북","직할","신남원광양#1 T/L","345kV 신남원-광양T/L 안전이격 확보공사","가. 철탑철거 : 2기 [No.214(T-14), No.216(F-21)] 나. 철탑설치 : 2기 [No.214(C2-26), No.216(SF-36)] 다. 전력선 교체 : 1.790km [ACSR 480㎟ x 2B] , 12가닥 라. 가선로 구성 : 가철탑 1기 (No.216","2019-04-12 18:00","2019-04-19 18:00","2019-04-12 18:00","2019-04-19 18:00","연속",null,null,null,201810310061]
[203,"광주전남","강진","신강진S/S #3 M.Tr A","신강진S/S 345kV #3 M.Tr 부싱 절연열화 측정","- 신강진S/S 345kV #3 M.Tr 부싱 절연열화 측정","2019-04-29 09:00","2019-04-29 18:00","취소","취소","당일",null,null,null,201901080076]
[204,"광주전남","강진","신화순신강진#1 T/L","신강진S/S 345kV #1M.Tr 및 OLTC 정밀점검공사","345kV M.Tr 및 OLTC 정밀점검 : 3대(단상x1BANK) 기타 기계적보호장치 교체","2019-04-08 09:00","2019-04-19 18:00","취소","취소","연속",null,null,null,201902130192]
[205,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S 345kV #1M.Tr 및 OLTC 정밀점검공사","345kV M.Tr 및 OLTC 정밀점검 : 3대(단상x1BANK) 기타 기계적보호장치 교체","2019-04-08 09:00","2019-04-19 18:00","취소","취소","연속",null,null,null,201902130185]
[206,"광주전남","강진","신강진S/S #3 M.Tr A","신강진S/S 345kV #3 M.Tr 부싱 절연열화 측정","- 신강진S/S 345kV #3 M.Tr 부싱 절연열화 측정","2019-04-29 09:00","2019-04-29 18:00","취소","취소","당일",null,null,null,201901080076]
[207,"광주전남","광주","신남원-신광주#1T/L-#2 M.Tr 1차 CB(신) (7400)","19년 변전총액공사(7400 장미)","7400 CB 장기미동작 차단기 점검","2019-04-02 12:00","2019-04-02 15:00","2019-04-02 12:00","2019-04-02 15:00","당일",null,null,null,201902080391]
[208,"광주전남","광주","신광주S/S 한빛NP-신광주#2T/L CB(신) (7271)","19년 변전총액공사(7271 장미)","7271 CB 장기미동작 차단기 점검","2019-04-01 09:00","2019-04-01 11:00","2019-04-01 09:00","2019-04-01 11:00","당일",null,null,null,201902080379]
[209,"광주전남","광주","신광주S/S 한빛NP-신광주#2T/L-TIE CB(신) (7200)","19년 변전총액공사(7200 장미)","7200 CB 장기미동작 차단기 점검","2019-04-01 11:00","2019-04-01 13:00","2019-04-01 11:00","2019-04-01 13:00","당일",null,null,null,201902080380]
[210,"광주전남","광주","신광주S/S 신남원-신광주#2T/L CB(신) (7371)","19년 변전총액공사(7371 장미)","7371 CB 장기미동작 차단기 점검","2019-04-01 13:00","2019-04-01 15:00","2019-04-01 13:00","2019-04-01 15:00","당일",null,null,null,201902080382]
[211,"광주전남","광주","신광주S/S 신남원-신광주#2T/L-TIE CB(신) (7300)","19년 변전총액공사(7300 장미)","7300 CB 장기미동작 차단기 점검","2019-04-01 15:00","2019-04-01 17:00","2019-04-01 15:00","2019-04-01 17:00","당일",null,null,null,201902080386]
[212,"광주전남","광주","신광주S/S 신남원-신광주#1T/L CB(신) (7471)","19년 변전총액공사(7471 장미)","7471 CB 장기미동작 차단기 점검","2019-04-02 09:00","2019-04-02 12:00","2019-04-02 09:00","2019-04-02 12:00","당일",null,null,null,201902080390]
[213,"광주전남","광주","신광주S/S #2 M.Tr 1차 CB(신) (7472)","19년 변전총액공사(7472 장미)","7472 CB 장기미동작 차단기 점검","2019-04-02 15:00","2019-04-02 18:00","2019-04-02 15:00","2019-04-02 18:00","당일",null,null,null,201902080392]
[214,"광주전남","광주","신광주S/S 신광주-신화순#2T/L CB(신) (7571)","19년 변전총액공사(7571 장미)","7571 CB 장기미동작 차단기 점검","2019-04-03 09:00","2019-04-03 11:00","2019-04-03 09:00","2019-04-03 11:00","당일",null,null,null,201902080394]
[215,"광주전남","광주","신광주S/S 신광주-신화순#2T/L-TIE CB(신) (7500)","19년 변전총액공사(7500 장미)","7500 CB 장기미동작 차단기 점검","2019-04-03 11:00","2019-04-03 13:00","2019-04-03 11:00","2019-04-03 13:00","당일",null,null,null,201902080395]
[216,"광주전남","광주","신광주S/S TIE-#4 M.Tr 1차 CB (7800)","19년 변전총액공사(7800 장미)","7800 CB 장기미동작 차단기 점검","2019-04-03 13:00","2019-04-03 15:00","2019-04-03 13:00","2019-04-03 15:00","당일",null,null,null,201902080396]
[217,"광주전남","광주","신광주S/S #3 M.Tr 1차 CB(신) (7672(신))","19년 변전총액공사(7672 장미)","7672 CB 장기미동작 차단기 점검","2019-04-04 15:00","2019-04-04 18:00","2019-04-04 15:00","2019-04-04 18:00","당일",null,null,null,201902080400]
[218,"광주전남","광주","신광주-신화순#1T/L-#3 M.Tr 1차 CB(15년) (7600(신))","19년 변전총액공사(7600 장미)","7600 CB 장기미동작 차단기 점검","2019-04-04 12:00","2019-04-04 15:00","2019-04-04 12:00","2019-04-04 15:00","당일",null,null,null,201902080399]
[219,"광주전남","광주","신광주S/S 신광주-신화순#1T/L CB(15년) (7671(신))","19년 변전총액공사(7671 장미)","7671 CB 장기미동작 차단기 점검","2019-04-04 09:00","2019-04-04 12:00","2019-04-04 09:00","2019-04-04 12:00","당일",null,null,null,201902080398]
[220,"광주전남","광주","신광주S/S #4 M.Tr 1차 CB (7872)","19년 변전총액공사(7872 장미)","7872 CB 장기미동작 차단기 점검","2019-04-03 15:00","2019-04-03 17:00","2019-04-03 15:00","2019-04-03 17:00","당일",null,null,null,201902080397]
[221,"광주전남","광주","신화순S/S #2 M.Tr A","신화순S/S 345kV #2M.Tr 휴전 (변전협력회사공사)","신화순S/S 신광주-신화순#1T/L 1ST, 2ND PNL 교체,77BAY BF PNL 교체 신광주S/S 신광주-신화순#1T/L 1ST, 2ND PNL 교체,77BAY BF PNL 교체","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201901140086]
[222,"광주전남","광주","신화순S/S #2 M.Tr A","신화순S/S 345kV #2M.Tr 휴전 (변전협력회사공사)","신화순S/S 신광주-신화순#1T/L 1ST, 2ND PNL 교체,77BAY BF PNL 교체 신광주S/S 신광주-신화순#1T/L 1ST, 2ND PNL 교체,77BAY BF PNL 교체","2019-04-08 09:00","2019-04-08 18:00","취소","취소","당일",null,null,null,201901140086]
[223,"광주전남","목포","한빛2NP한빛3NP #4T/L","한빛연락#4T/L 보호PNL 성능개선","한빛연락#4T/L 보호PNL 성능개선","2019-04-02 09:00","2019-04-03 18:00","2019-04-02 09:00","2019-04-03 18:00","연속",null,null,null,201902220074]
[224,"광주전남","순천","광양S/S 345kV #71 BUS","광양 362kV GIS 용량대체 공사","362kV #71BUS GIS PT교체","2019-04-20 09:00","2019-04-21 18:00","2019-04-20 09:00","2019-04-21 18:00","당일",null,null,null,201901150102]
[225,"광주전남","순천","광양S/S 345kV #76 BUS","광양 362kV GIS 용량대체 공사","362kV #76BUS GIS PT교체","2019-04-27 09:00","2019-04-28 18:00","2019-04-27 09:00","2019-04-28 18:00","당일",null,null,null,201901150103]
[226,"광주전남","순천","광양S/S #3 M.Tr A","19년 순천전력지사 345kV 변압기 정밀점검 공사","광양S/S 345kV #3MTR 변압기 정밀점검","2019-04-01 09:00","2019-04-11 18:00","2019-04-01 09:00","2019-04-11 18:00","연속",null,null,null,201902120050]
[227,"광주전남","순천","광양여수TP T/L","19년 변전 정비회사 총액공사","* 광양S/S 7471GIS 초기, LA, CVT 하자점검 * 여수화력S/Y 7171GIS 보통, LA, CVT(A,C)보통, CVT B상 교체","2019-04-03 09:00","2019-04-04 18:00","2019-04-03 09:00","2019-04-04 18:00","연속",null,null,null,201902120073]
[228,"광주전남","순천","신남원광양#2 T/L","19년 변전 정비회사 총액공사","* 광양S/S 7171GIS 초기, LA, CVT(B)하자, CVT A상 교체","2019-04-12 09:00","2019-04-12 18:00","취소","취소","당일",null,null,null,201902120103]
[229,"광주전남","순천","여수T/P #3 Tie-Tr","19년 순천전력지사 345kV 변압기 정밀점검 공사","여수화력S/Y 345kV #3MTR 변압기 정밀점검","2019-04-22 09:00","2019-05-02 18:00","2019-04-24 09:00","2019-05-05 18:00","연속",null,null,null,201902120055]
[230,"광주전남","순천","광양율촌CC T/L","19년 변전 정비회사 총액공사","* 율촌CC 7171, 7100GIS 보통점검","2019-04-19 09:00","2019-04-19 18:00","2019-04-19 09:00","2019-04-19 18:00","당일",null,null,null,201902120120]
[231,"광주전남","광주","신광주신화순#2T/L","신화순S/S 신광주-신화순 #2T/L(변전협력회사공사)","신화순S/S 신광주-신화순 #2T/L 1ST, 2ND PNL 교체, 77BAY BF PNL 교체, 신과주S/S 1ST, 2ND PNL 교체","2019-04-18 09:00","2019-04-29 18:00","2019-04-18 09:00","2019-04-29 18:00","연속"]
[232,"광주전남","광주","신광주신화순#1T/L","신화순S/S 신광주-신화순 #2T/L(변전협력회사공사)","신화순S/S 신광주-신화순 #1T/L 1ST, 2ND PNL 교체, 77BAY BF PNL 교체, 신과주S/S 1ST, 2ND PNL 교체","2019-04-04 09:00","2019-04-15 18:00","2019-04-04 09:00","2019-04-15 18:00","연속"]
[233,"대구","경산","신경산S/S 345kV #2 BUS","신경산S/S 345kV #2BUS 휴전","○ 모선 인터록시험 ○ 무부하가압(4/13 18:00 시작) (인출~7400CB~#2BUS) ○ 실부하 위상측정","2019-04-13 09:00","2019-04-14 18:00","2019-04-13 09:00","2019-04-14 18:00","연속",null,null,null,201901070141]
[234,"대구","경산","신경산S/S #3 M.Tr A","신경산S/S 362kV 장기사용 GIS 대체공사","장기사용 362kV GIS 및 BUS 교체(7371, 7300, 7372, #1,2BUS)","2019-04-18 09:00","2019-06-18 18:00","2019-04-18 09:00","2019-06-18 18:00","연속",null,null,null,201902110669]
[235,"대구","경산","울주신경산#2 T/L","신경산S/S 362kV 장기사용 GIS 대체공사","장기사용 362kV GIS 및 BUS 교체(7371, 7300, 7372, #1,2BUS)","2019-04-18 09:00","2019-06-18 18:00","2019-04-18 09:00","2019-06-18 18:00","연속",null,null,null,201902110668]
[236,"대구","경산","신경산S/S 345kV #2 BUS","신경산S/S 362kV 장기사용 GIS 대체공사","장기사용 362kV GIS 및 BUS 교체(7371, 7300, 7372, #1,2BUS)","2019-04-18 09:00","2019-04-25 09:00","2019-04-18 09:00","2019-04-25 09:00","연속",null,null,null,201902110671]
[237,"대구","경산","신경산대구#2 T/L","신경산S/S 362kV 장기사용 GIS 대체공사","장기사용 362kV GIS 및 BUS 교체(7371, 7300, 7372, #1,2BUS)관련 #2BUS 무부하가압 선로","2019-04-24 18:00","2019-04-25 09:00","2019-04-24 18:00","2019-04-25 09:00","연속",null,null,null,201902110677]
[238,"대구","경산","신경산S/S 345kV #1 BUS","신경산S/S 362kV 장기사용 GIS 대체공사","장기사용 362kV GIS 및 BUS 교체(7371, 7300, 7372, #1,2BUS)","2019-04-25 09:00","2019-05-02 09:00","2019-04-25 09:00","2019-05-02 09:00","연속",null,null,null,201902110679]
[239,"대구","경산","신경산S/S 345kV #1 BUS","신경산S/S 345kV #1BUS 휴전","○ 모선 인터록시험 ○ 무부하가압(4/11 18:00 시작) (인출~7471CB~#1BUS) ○ 실부하 위상측정","2019-04-11 09:00","2019-04-13 09:00","2019-04-11 09:00","2019-04-13 09:00","연속",null,null,null,201901070138]
[240,"대구","달성","고령S/S 345kV #2 BUS","345kV 고령S/S #1M.Tr 증설공사","-345kV #2BUS GIS Docking","2019-04-13 09:00","2019-04-23 18:00","2019-04-13 09:00","2019-04-23 18:00","연속",null,null,null,201902210054]
[241,"대구","달성","고령S/S 345kV #1 BUS","345kV 고령S/S #1M.Tr 증설공사","-345kV #1BUS GIS Docking","2019-04-02 09:00","2019-04-12 18:00","2019-04-02 09:00","2019-04-12 18:00","연속",null,null,null,201902200095]
[242,"대구","달성","서대구고령#2 T/L","345kV 고령S/S #1M.Tr 증설공사","-345kV #1BUS PT 교체공사 안전이격 거리 확보 (BUS PT 교체 사유 : 철공진 해소 위함)","2019-04-05 09:00","2019-04-05 18:00","2019-04-05 09:00","2019-04-05 18:00","당일",null,null,null,201902200096]
[243,"대구","달성","서대구고령#2 T/L","345kV 고령S/S #1M.Tr 증설공사","-345kV #1BUS, #1M.Tr, 154kV #60BUS 무부하 가압용 선로","2019-04-11 09:00","2019-04-12 18:00","2019-04-11 09:00","2019-04-12 18:00","연속",null,null,null,201902200102]
[244,"대구","달성","고령S/S #3 M.Tr A","345kV 고령S/S #1M.Tr 증설공사","-345kV #2BUS PT 교체공사 안전이격 거리 확보 (BUS PT 교체 사유 : 철공진 해소 위함)","2019-04-16 09:00","2019-04-16 18:00","2019-04-16 09:00","2019-04-16 18:00","당일",null,null,null,201902200097]
[245,"대구","달성","서대구고령#2 T/L","345kV 고령S/S #1M.Tr 증설공사","-345kV #2BUS, #1M.Tr, 154kV #65BUS 무부하 가압용 선로","2019-04-22 09:00","2019-04-23 18:00","2019-04-22 09:00","2019-04-23 18:00","연속",null,null,null,201902200103]
[246,"대구","달성","북경남대구#1 T/L","피뢰기설치 안전확보","안전확보","2019-04-01 07:30","2019-04-01 18:00","2019-04-01 07:30","2019-04-01 18:00","당일",null,null,null,201902200141]
[247,"대구","칠곡","북대구S/S #2 M.Tr A","북대구S/S #2M.Tr 보통점검 및 병행작업","북대구S/S #2M.Tr 보통점검 및 병행작업","2019-04-03 09:30","2019-04-03 18:00","2019-04-03 09:30","2019-04-03 18:00","당일",null,null,null,201902070427]
[248,"대구","칠곡","북대구S/S #1 M.Tr A","북대구S/S #1M.Tr 보통점검 및 병행작업","북대구S/S #1M.Tr 보통점검 및 병행작업","2019-04-16 09:30","2019-04-16 18:00","2019-04-16 09:30","2019-04-16 18:00","당일",null,null,null,201902070440]
[249,"대구","칠곡","서대구S/S #2 M.Tr A","서대구S/S #2M.Tr 1,2차 CB 장기미동작점검","서대구S/S #2M.Tr 1,2차 CB 장기미동작점검","2019-04-17 09:30","2019-04-17 18:00","2019-04-17 09:30","2019-04-17 18:00","당일",null,null,null,201902070441]
[250,"대구","칠곡","북대구서대구#1 T/L","북대구,서대구S/S 북대구-서대구#1T/L 장기미동작점검","북대구,서대구S/S 북대구-서대구#1T/L 장기미동작점검","2019-04-30 09:30","2019-04-30 18:00","2019-04-30 09:30","2019-04-30 18:00","당일",null,null,null,201902070444]
[251,"대구","칠곡","서대구S/S #3 M.Tr A","서대구S/S #3M.Tr 1,2차 CB 장기미동작점검","서대구S/S #3M.Tr 1,2차 CB 장기미동작점검","2019-04-23 09:30","2019-04-23 18:00","2019-04-23 09:30","2019-04-23 18:00","당일",null,null,null,201902070442]
[252,"대구","칠곡","서대구S/S #1M.Tr A","서대구S/S #1M.Tr 부싱절연유 채유 및 병행작업","서대구S/S #1M.Tr 부싱절연유 채유 및 병행작업","2019-04-11 09:30","2019-04-11 18:00","2019-04-11 09:30","2019-04-11 18:00","당일",null,null,null,201902070437]
[253,"대구","칠곡","북대구서대구#2 T/L","북대구,서대구S/S 북대구-서대구#2T/L 장기미동작점검","북대구,서대구S/S 북대구-서대구#2T/L 장기미동작점검","2019-04-26 09:30","2019-04-26 18:00","2019-04-26 09:30","2019-04-26 18:00","당일",null,null,null,201902070443]
[254,"대구","포항","신영일안동CC T/L","2019년도 가공송전 순시점검 위탁공사","345kV 신영일-안동CC T/L No.186~256 송전선로 정밀점검","2019-04-15 08:00","2019-04-17 18:00","취소","취소","연속",null,null,null,201902080471]
[255,"대구","포항","신포항신영일 T/L","2019년도 가공송전 순시점검 위탁공사","345kV 신포항-신영일 T/L No.1~74 송전선로 정밀점검","2019-04-18 08:00","2019-04-19 18:00","2019-04-18 08:00","2019-04-19 18:00","연속",null,null,null,201902080465]
[256,"대구","포항","신포항청송PP T/L","2019년도 가공송전 순시점검 위탁공사","345kV 신포항-청송PP T/L No.77~220 송전선로 정밀점검","2019-04-22 08:00","2019-04-26 18:00","2019-04-22 08:00","2019-04-26 18:00","연속",null,null,null,201902080461]
[257,"대구","포항","신포항S/S #1 M.Tr A","포항전력지사 변전협력회사 총액공사","포항전력지사 변전협력회사 총액공사","2019-04-01 09:00","2019-04-02 18:00","2019-04-01 09:00","2019-04-02 18:00","연속",null,null,null,201902110530]
[258,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 안전이격확보공사","345kV 신포항-북대구T/L 안전이격확보공사(본선로 구성) - No.116,118 철탑교체, No.113~118 전선교체","2019-04-08 08:00","2019-04-15 18:00","2019-04-08 08:00","2019-04-15 18:00","연속",null,null,null,201902070071]
[259,"대구","포항","선산신포항 T/L","345kV 신포항-북대구T/L 안전이격확보공사","345kV 신포항-북대구T/L 안전이격확보공사(본선로 구성) - No.116,118 철탑교체, No.113~118 전선교체","2019-04-01 08:00","2019-04-07 18:00","2019-04-01 08:00","2019-04-07 18:00","연속",null,null,null,201902070069]
[260,"대구","포항","동울산월성NP#1 T/L","월성S/Y 7771, 7700 CB 보통점검","월성S/Y 7771, 7700 CB 보통점검","2019-04-29 09:00","2019-04-29 18:00","2019-04-29 09:00","2019-04-29 18:00","당일",null,null,null,201812130072]
[261,"대구","포항","월성2N/P #4 M.Tr 2차 CB (7772)","월성S/Y 7772 GIS 보통점검","월성S/Y 7772 GIS 보통점검","2019-04-30 09:00","2019-04-30 18:00","2019-04-30 09:00","2019-04-30 18:00","당일",null,null,null,201811140003]
[262,"경북","구미","선산S/S #2 M.Tr A","2019년도 구미전력지사 변전정비업체 총액공사","6244CB 초기점검 1,2차 부싱 절연유 채유 96P 수분방지 침투커버 설치","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902110759]
[263,"경북","구미","선산S/S #3 M.Tr A","2019년도 구미전력지사 변전정비업체 총액공사","6344CB 초기점검 1,2차 부싱 절연유 채유 96P 수분방지 침투커버 설치 3차LA 보통점검","2019-04-09 09:00","2019-04-09 18:00","2019-04-09 09:00","2019-04-09 18:00","당일",null,null,null,201902110760]
[264,"경북","구미","선산S/S #4 M.Tr A","2019년도 구미전력지사 변전정비업체 총액공사","6444CB 초기점검","2019-04-10 09:00","2019-04-10 18:00","2019-04-10 09:00","2019-04-10 18:00","당일",null,null,null,201902110761]
[265,"경북","구미","선산S/S #1 M.Tr A","2019년도 구미전력지사 변전정비업체 총액공사","M.Tr 하자점검 7072CB 하자점검 6144CB 초기점검 1,2,3차 LA 하자점검 2차 부싱 절연유 채유","2019-04-01 09:00","2019-04-03 18:00","2019-04-01 09:00","2019-04-03 18:00","당일",null,null,null,201902110565]
[266,"경북","영주","신영주예천PP#2 T/L","'19년 영주전력 가공송전위탁공사 송전선로 정밀점검","345kV 신영주-예천PP#2T/L 송전선로 정밀점검","2019-04-15 09:00","2019-04-18 18:00","2019-04-15 09:00","2019-04-18 18:00","연속",null,null,null,201902110237]
[267,"경북","영주","신영주예천PP#1 T/L","'18-19년 영주전력지사 가공송전협력회사 총액공사(피뢰기 설치공사)","345kV 신영주-예천PP#1T/L 피뢰기 설치공사","2019-04-08 08:00","2019-04-12 18:00","2019-04-08 08:00","2019-04-12 18:00","연속",null,null,null,201902110232]
[268,"경북","직할","안동복합S/S 신영일-안동CCT/L-TIE GIS","18~19년 경북직할 변전정비회사 총액공사","안동복합S/S 7300 GIS 개폐타임 측정","2019-04-18 11:00","2019-04-18 13:00","2019-04-18 11:00","2019-04-18 13:00","당일",null,null,null,201902190221]
[269,"경북","직할","안동복합S/S 신영주-안동CCT/L-TIE GIS","18~19년 경북직할 변전정비회사 총액공사","안동복합S/S 7200 GIS 개폐타임 측정","2019-04-18 14:00","2019-04-18 16:00","2019-04-18 14:00","2019-04-18 16:00","당일",null,null,null,201902080055]
[270,"경북","직할","안동CC #1 Tie-Tr","18~19년 경북직할 변전정비회사 총액공사","안동복합S/S #1M.Tr 초기점검 및 1차 2차 GIS 초기점검","2019-04-25 09:00","2019-04-26 18:00","2019-04-25 09:00","2019-04-26 18:00","매일",null,null,null,201902080121]
[271,"경북","직할","안동복합S/S Unit 1 Tr 1차 GIS","18~19년 경북직할 변전정비회사 총액공사","안동복합S/S Unit 1 Tr 1차(7372) GIS 개폐타임 측정","2019-04-18 09:00","2019-04-18 11:00","2019-04-18 09:00","2019-04-18 11:00","당일",null,null,null,201902080039]
[272,"부산울산","동부산","신양산S/S #4 M.Tr A","345kV 신양산S/S 현대화 공사","345kV 신양산S/S 현대화 공사 - 덕트 기초 터파기(안전이격)","2019-04-04 09:00","2019-04-05 18:00","2019-04-04 09:00","2019-04-05 18:00","연속",null,null,null,201901310230]
[273,"부산울산","동부산","신양산북부산#2 T/L","345kV 신양산-북부산 등 2개T/L 안전이격확보공사","1. 본선로 구성 2. 개요 : 철탑설치 : 42호(신설 4회선), 철탑철거 : 42호(기설), 전선교체 : 41-43호","2019-04-23 07:00","2019-04-27 18:00","2019-04-23 07:00","2019-04-27 18:00","연속",null,null,null,201902080226]
[274,"부산울산","동부산","신양산북부산#1 T/L","345kV 신양산-북부산 등 2개T/L 안전이격확보공사","1. 본선로 구성 2. 개요 : 철탑설치 : 42호(신설 4회선), 철탑철거 : 42호(기설), 전선교체 : 41-43호","2019-04-15 07:00","2019-04-22 18:00","2019-04-15 07:00","2019-04-22 18:00","연속",null,null,null,201902080229]
[275,"부산울산","동부산","신양산S/S 신양산-고리NP#1T/L CB (7671)","신양산S/S 362kV GIS 조작시험","신양산S/S 362kV 7671GIS 조작시험","2019-04-01 14:00","2019-04-01 17:00","2019-04-01 14:00","2019-04-01 17:00","당일",null,null,null,201902100009]
[276,"부산울산","동부산","신양산S/S #3 M.Tr 1차 CB (7572)","신양산S/S 362kV GIS 조작시험","신양산S/S 362kV 7572GIS 조작시험","2019-04-01 09:30","2019-04-01 14:00","2019-04-01 09:30","2019-04-01 14:00","당일",null,null,null,201902100008]
[277,"부산울산","동부산","신양산S/S #4 M.Tr 1차 CB (7672)","신양산S/S 362kV GIS 조작시험","신양산S/S 362kV 7672GIS 조작시험","2019-04-02 14:00","2019-04-02 17:00","2019-04-02 14:00","2019-04-02 17:00","당일",null,null,null,201902100011]
[278,"부산울산","동부산","신양산S/S 신양산#1T/L-#4 M.Tr 1차 CB (7600)","신양산S/S 362kV GIS 조작시험","신양산S/S 362kV 7600GIS 조작시험","2019-04-02 09:30","2019-04-02 14:00","2019-04-02 09:30","2019-04-02 14:00","당일",null,null,null,201902100010]
[279,"부산울산","동부산","신양산S/S #1 M.Tr A","345kV 신양산S/S 현대화 공사","345kV 신양산S/S 현대화 공사 - 덕트 기초 터파기(안전이격)","2019-04-09 09:00","2019-04-11 18:00","2019-04-09 09:00","2019-04-11 18:00","연속",null,null,null,201901310228]
[280,"부산울산","동부산","신양산북부산#2 T/L","345kV 신양산-북부산 등 2개T/L 안전이격확보공사","1. 가선로 구성 2. 개요 : 철탑설치 : 42호(신설 4회선), 철탑철거 : 42호(기설), 전선교체 : 41-43호","2019-04-10 07:00","2019-04-12 18:00","2019-04-10 07:00","2019-04-12 18:00","연속",null,null,null,201902080224]
[281,"부산울산","북부산","북부산신울산#2 T/L","19년 가공송전 순시점검 위탁공사","345kV 북부산-신울산#2T/L 정밀점검 시행(ST-49호, 50기)","2019-04-15 09:00","2019-04-19 18:00","취소","취소","매일",null,null,null,201902080022]
[282,"부산울산","북부산","북부산S/S #3 M.Tr A","북부산S/S 345kV #3M.Tr 정밀점검 공사","북부산S/S 345kV #3M.Tr 정밀점검 공사","2019-04-29 09:00","2019-05-15 18:00","2019-04-29 09:00","2019-05-15 18:00","연속",null,null,null,201902130272]
[283,"부산울산","북부산","북부산신울산#1 T/L","19년 가공송전 순시점검 위탁공사","345kV 북부산-신울산#1T/L 정밀점검 시행(ST-49호, 50기)","2019-04-08 09:00","2019-04-12 18:00","취소","취소","매일",null,null,null,201902080018]
[284,"부산울산","북부산","서부산북부산#3 T/L","2019년 북부산 변전협력회사 총액공사","북부산S/S 345kV 서부산-북부산#3T/L 챔버 가스누기 보수","2019-04-01 09:00","2019-04-05 18:00","2019-04-01 09:00","2019-04-05 18:00","연속",null,null,null,201902220041]
[285,"부산울산","울산","동울산S/S #1 M.Tr A","2018~19년 변전협력 총액공사","- M.Tr 보통점검 - 7100, 7172GIS 보통점검 - 6144GIS 보통점검","2019-04-10 09:00","2019-04-11 18:00","2019-04-10 09:00","2019-04-11 18:00","연속",null,null,null,201901310261]
[286,"부산울산","울산","동울산S/S #2 M.Tr A","2018~19년 변전협력 총액공사","- M.Tr 보통점검 - 7200, 7272GIS 보통점검 - 6244GIS 보통점검","2019-04-08 09:00","2019-04-09 18:00","2019-04-08 09:00","2019-04-09 18:00","연속",null,null,null,201901310260]
[287,"부산울산","울산","신온산S/S S-OIL#6T/L CB (7571)","2018~19년 변전협력회사 총액공사","- 75BAY B/F 보호반 성능개선","2019-04-01 15:00","2019-04-01 18:00","2019-04-01 15:00","2019-04-01 18:00","당일",null,null,null,201901310244]
[288,"부산울산","울산","신온산S/S S-OIL#6T/L-#3M.Tr 1차 TIE CB (7500)","2018~19년 변전협력회사 총액공사","- 75BAY B/F 보호반 성능개선","2019-04-01 12:00","2019-04-01 15:00","2019-04-01 12:00","2019-04-01 15:00","당일",null,null,null,201901310243]
[289,"부산울산","울산","신온산S/S #1 M.Tr A","2018~19년 변전협력 총액공사","- M.Tr 보통점검","2019-04-02 09:00","2019-04-03 18:00","2019-04-02 09:00","2019-04-03 18:00","연속",null,null,null,201901310268]
[290,"부산울산","울산","신온산S/S 345kV #1 BUS","2018~19년 변전협력회사 총액공사","- #1BUS 모선보호반 교체","2019-04-08 09:00","2019-04-11 18:00","2019-04-08 09:00","2019-04-11 18:00","연속",null,null,null,201901310256]
[291,"부산울산","울산","신온산울산TP T/L","2018~19년 변전협력 총액공사","- 74BAY B/F 보호반 대체","2019-04-22 09:00","2019-04-25 18:00","취소","취소","연속",null,null,null,201901310275]
[292,"부산울산","울산","신온산S/S 345kV #2 BUS","2018~19년 변전협력회사 총액공사","- #2BUS 모선보호반 교체","2019-04-15 09:00","2019-04-18 18:00","2019-04-15 09:00","2019-04-18 18:00","연속",null,null,null,201901310258]
[293,"부산울산","울산","신온산S/S #2 M.Tr A","2018~19년 변전협력 총액공사","- 74BAY B/F 보호반 대체","2019-04-22 09:00","2019-04-25 18:00","취소","취소","연속",null,null,null,201901310276]
[294,"부산울산","울산","신온산S/S #3 M.Tr 1차 CB (7572)","2018~19년 변전협력 총액공사","- 75BAY B/F 보호반 성능개선","2019-04-01 09:00","2019-04-01 12:00","2019-04-01 09:00","2019-04-01 12:00","당일",null,null,null,201901310242]
[295,"부산울산","울산","신울산고리NP#1 T/L","18-19년 동부산전력지사 송전정비 협력회사 총액공사","1. 만곡개소 정비 : 34호, 2. 노후 금구류 교체 : 15, 15-1, 16호, 3. 피뢰기 설치 : 5-1, 50호","2019-04-04 08:00","2019-04-05 18:00","2019-04-04 08:00","2019-04-05 18:00","연속",null,null,null,201901080165]
[296,"부산울산","울산","신울산S/S #3 M.Tr A","2018~19년 변전협력 총액공사","- M.Tr 보통점검 - 7571GIS 보통점검","2019-04-29 09:00","2019-04-30 18:00","2019-04-29 09:00","2019-04-30 18:00","연속",null,null,null,201901310283]
[297,"부산울산","울산","울주S/S #2 M.Tr 1차-TIE CB (7400)","2018~19년 변전협력 총액공사","- 7400GIS 하자점검","2019-04-25 09:00","2019-04-25 18:00","2019-04-25 09:00","2019-04-25 18:00","당일",null,null,null,201901310282]
[298,"부산울산","울산","울주S/S #2 M.Tr 1차 CB (7472)","2018~19년 변전협력 총액공사","- 7472GIS 하자점검","2019-04-24 09:00","2019-04-24 18:00","2019-04-24 09:00","2019-04-24 18:00","당일",null,null,null,201901310281]
[299,"부산울산","울산","울산C/C #1 M.Tr A","2018-19년 울산전력지사 변전협력회사 총액공사 ","울산C/C 345kV 74Bay B/F PNL 대체","2019-04-26 09:00","2019-04-30 18:00","2019-04-26 09:00","2019-04-30 18:00","연속"]
[300,"부산울산","울산","울산C/C 기력4호기 1차 CB","2018-19년 울산전력지사 변전협력회사 총액공사 ","울산C/C 345kV 74Bay B/F PNL 대체(7472)","2019-04-26 09:00","2019-04-30 18:00","2019-04-26 09:00","2019-04-30 18:00","연속"]
[301,"경남","직할","신김해S/S #1 M.Tr A","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) - 65-66B/S 철거(안전이격거리)","2019-04-06 08:00","2019-04-07 17:30","2019-04-06 08:00","2019-04-07 17:30","연속",null,null,null,201902190295]
[302,"경남","직할","신마산신김해#1 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","345kV 신김해-북부산#2T/L 정밀점검관련 안전거리확보, 345kV 신마산-신김해#1(22~27호) 병가","2019-04-01 09:00","2019-04-01 18:00","2019-04-01 09:00","2019-04-01 18:00","당일",null,null,null,201812280042]
[303,"경남","직할","신김해S/S #1 M.Tr A","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) - 65-66B/S 설치(안전이격거리)","2019-04-12 07:00","2019-04-14 17:30","2019-04-12 07:00","2019-04-14 17:30","연속",null,null,null,201902190297]
[304,"경남","직할","신김해S/S #2 M.Tr A","신김해S/S 345kV #2M.Tr 보통점검","신김해S/S 345kV #2M.Tr 보통점검 (병행)#2M.Tr 1차 CB, #74BAY TIE CB 보통점검, 1,2,3차 LA 보통점검, 3차 PT 보통점검","2019-04-23 09:30","2019-04-25 17:30","2019-04-23 09:30","2019-04-25 17:30","연속",null,null,null,201902080171]
[305,"경남","직할","창원삼천포TP#2 T/L","창원S/S 345kV 창원-삼천포T/P #2T/L CB 초기점검","창원S/S 345kV 창원-삼천포T/P #2T/L CB 초기점검, 72BAY TIE CB 초기점검","2019-04-08 09:30","2019-04-08 17:30","2019-04-08 09:30","2019-04-08 17:30","당일",null,null,null,201902080167]
[306,"경남","직할","창원삼천포TP#1 T/L","창원S/S 345kV 창원-삼천포T/P #1T/L CB 초기점검","창원S/S 345kV 창원-삼천포T/P #1T/L CB 초기점검, 73BAY TIE CB 초기점검","2019-04-09 09:30","2019-04-09 17:30","2019-04-09 09:30","2019-04-09 17:30","당일",null,null,null,201902080168]
[307,"경남","진주","의령하동화력#2 T/L","의령SS 의령하동화력#2 T/L CPD 대체","의령SS 의령하동화력#2 T/L CPD 대체 하동TP CPD 점검","2019-04-19 10:00","2019-04-21 18:00","2019-04-19 10:00","2019-04-21 18:00","연속",null,null,null,201901310288]
[308,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령#1T/L 송전선로 정밀점검","345kV 신남원-의령#1T/L 송전선로 정밀점검","2019-04-22 09:00","2019-04-26 18:00","2019-04-22 09:00","2019-04-26 18:00","매일",null,null,null,201901310086]
[309,"경남","진주","고령의령#2 T/L","345kV 고령의령#2 T/L PT 보통점검","345kV 고령의령#2 T/L PT 보통점검 7571CB 보통점검","2019-04-27 09:30","2019-04-27 18:00","2019-04-27 09:30","2019-04-27 18:00","당일",null,null,null,201902010155]
[310,"경남","진주","신남원의령#2 T/L","345kV 신남원-의령#2T/L 송전선로 정밀점검","345kV 신남원-의령#2T/L 송전선로 정밀점검","2019-04-29 09:00","2019-05-03 18:00","2019-04-29 09:00","2019-05-03 18:00","매일",null,null,null,201901310092]
[311,"경남","진주","하동T/P #8 M.Tr 1차 CB (7872)","하동T/P #8 M.Tr 1차 CB(7872) 조작시험","하동T/P #8 M.Tr 1차 CB(7872) 조작시험","2019-04-30 14:00","2019-04-30 18:00","2019-04-30 14:00","2019-04-30 18:00","당일",null,null,null,201901310192]
[312,"경남","진주","광양하동화력#1 T/L","345kV 광양-하동화력#1T/L 항공장애표시구 설치공사","345kV 광양-하동화력#1T/L 13~14, 16~17, 17~18, 18~19, 23~24호 구간 항공장애표시구 설치","2019-04-11 07:00","2019-04-13 18:00","2019-04-11 07:00","2019-04-13 18:00","매일",null,null,null,201902070042]
[313,"경남","진주","광양하동화력#2 T/L","345kV 광양-하동화력#2T/L 항공장애표시구 설치공사","345kV 광양-하동화력#2T/L 13~14, 16~17, 17~18, 18~19, 23~24호 구간 항공장애표시구 설치","2019-04-14 07:00","2019-04-15 18:00","2019-04-14 07:00","2019-04-15 18:00","매일",null,null,null,201902070044]
[314,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력#1T/L 항공장애표시구 설치공사","345kV 의령-하동화력#1T/L 2~3, 6~7, 7~8, 15~16, 19~20, 61~62호 구간 항공장애표시구 설치","2019-04-16 07:00","2019-04-18 18:00","2019-04-16 07:00","2019-04-18 18:00","매일",null,null,null,201902070047]
[315,"경남","진주","하동T/P TIE-#4 M.Tr 1차 CB (7400)","하동T/P TIE-#4 M.Tr 1차 CB(7400) 조작시험","하동T/P TIE-#4 M.Tr 1차 CB(7400) 조작시험","2019-04-16 10:00","2019-04-16 14:00","2019-04-16 10:00","2019-04-16 14:00","당일",null,null,null,201901310199]
[316,"경남","진주","하동T/P TIE-#8 M.Tr 1차 CB (7800)","하동T/P TIE-#8 M.Tr 1차 CB(7800) 조작시험","하동T/P TIE-#8 M.Tr 1차 CB(7800) 조작시험","2019-04-30 10:00","2019-04-30 14:00","2019-04-30 10:00","2019-04-30 14:00","당일",null,null,null,201901310191]
[317,"경남","진주","하동T/P #4 M.Tr 1차 CB (7472)","하동T/P #4 M.Tr 1차 CB(7472) 조작시험","하동T/P #4 M.Tr 1차 CB(7472) 조작시험","2019-04-16 14:00","2019-04-16 18:00","2019-04-16 14:00","2019-04-16 18:00","당일",null,null,null,201901310200]
[318,"경남","통영","(신)신고성S/S #3 M.Tr 1차-G5호기 1차 GIS","삼천포,신고성S/S 용량부족차단기 대체공사","#3M.Tr 1차 인출변경에 따른 보호배전반 준공시험","2019-04-27 09:00","2019-04-30 18:00","2019-04-27 09:00","2019-04-30 18:00","연속",null,null,null,201901300186]
[319,"경남","통영","(신)신고성S/S #3 M.Tr 1차 GIS","삼천포,신고성S/S 용량부족차단기 대체공사","#3M.Tr 1차 인출변경에 따른 보호배전반 준공시험","2019-04-27 09:00","2019-04-30 18:00","2019-04-27 09:00","2019-04-30 18:00","연속",null,null,null,201901300185]
[320,"경남","통영","(신)신고성S/S TIE#1T/L-고성하이#1T/L CB","삼천포,신고성S/S 용량부족차단기 대체공사","삼천포-고성하이화력#1T/L 인출 GIB 사용주파내전압시험","2019-04-12 09:00","2019-04-12 18:00","2019-04-12 09:00","2019-04-12 18:00","당일",null,null,null,201901300198]
[321,"경남","통영","(신)신고성S/S 고성하이화력#1T/L GIS","삼천포,신고성S/S 용량부족차단기 대체공사","삼천포-고성하이화력#1T/L 인출 GIB 사용주파내전압시험","2019-04-12 09:00","2019-04-12 18:00","2019-04-12 09:00","2019-04-12 18:00","당일",null,null,null,201901300199]
[322,"경남","통영","신고성S/S #3 M.Tr A","삼천포,신고성S/S 용량부족차단기 대체공사","#3M.Tr 1차 인출변경","2019-04-10 09:00","2019-04-30 18:00","2019-04-10 09:00","2019-04-30 18:00","연속",null,null,null,201901300181]
[323,"경남","직할","신김해창원#1 T/L","창원S/S 345kV 7172 CB 가스누기 외함 교체 시험가압","7172 CB 가스누기 외함 교체 후 시험가압선로","2019-04-11 17:30","2019-04-12 17:30","2019-04-11 17:30","2019-04-12 17:30","연속"]
[324,"경남","직할","창원S/S #1 M.Tr A","창원S/S 345kV #1M.Tr 초기점검","창원S/S 345kV #1M.Tr 초기점검 -병행 : 7172 CB 가스누기 외함 교체","2019-04-10 08:30","2019-04-13 17:30","2019-04-10 08:30","2019-04-13 17:30","연속"]
[325,"경남","직할","창원S/S 345kV #2 BUS","창원S/S 345kV 7172 CB 가스누기 외함 교체","7172 CB 가스누기 외함 교체 후 시험가압","2019-04-11 17:30","2019-04-12 17:30","2019-04-11 17:30","2019-04-12 17:30","연속"]
[326,"부산울산",null,"고리NP 1호기 주변압기 CB(7200,7272)","고리1호기 영구정지 O/H 휴전작업\n* 조작차단기 : CB 7200, 7272  ","K-1 주변압기/보조변압기 (A/B) 일반점검 및 갑종보호계전기 연동시험","2019-04-15 10:00","2019-04-24 17:00","2019-04-15 10:00","2019-04-24 17:00","연속"]
[327,"인천",null,"인천복합GT1,2호기 주변압기 CB(7500,7572)","간이정비공사","보호계전기 시험 및 정기검사","2019-04-01 09:00","2019-04-10 18:00","2019-04-01 09:00","2019-04-10 18:00","연속"]
[328,"인천",null,"인천복합ST1호기 주변압기 CB(7600,7672)","간이정비공사","보호계전기 시험 및 정기검사","2019-04-01 09:00","2019-04-10 18:00","2019-04-01 09:00","2019-04-10 18:00","연속"]
[329,"경북",null,"청송양수 2호기 주변압기 CB(7200,7272)","#2 B급 계획예방정비공사","#2 B급 계획예방정비공사","2019-04-16 09:00","2019-04-30 18:00","2019-04-16 09:00","2019-04-30 18:00","연속"]
[330,"대전충남",null,"청양보령화력#2 T/L","GIS 77Bay 보통점검 및 선로보호반 시험","GIS 77Bay 보통점검 및 선로보호반 시험","2019-04-22 09:00","2019-04-26 17:00","취소","취소","연속"]
[331,"경기","성남","신수원S/S #4 M.Tr","신수원S/S 345kV 용량부족 GIS 대체공사","- 345kV GIS(40kA, 4000A) × 14CB 철거 - 345kV GIS(63kA, 6300A) × 14CB 신설","2019-04-01 08:00","2019-04-24 18:00","2019-04-01 08:00","2019-04-24 18:00","연속"]
[332,"경기","성남","신수원삼성#2 T/L","신수원S/S 345kV 용량부족 GIS 대체공사","- 345kV GIS(40kA, 4000A) × 14CB 철거 - 345kV GIS(63kA, 6300A) × 14CB 신설","2019-04-27 08:00","2019-06-23 18:00","2019-04-27 08:00","2019-06-23 18:00","연속"]

{"sheet":"154송부","index":2,"n_rows":542,"n_cols":16,"rows_kept":542,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
["2019년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","방학S/S 154kV #1 BUS TIE GIS","19년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2019-04-02 10:00","2019-04-02 13:00","2019-04-02 10:00","2019-04-02 13:00","당일",null,null,null,201902120157]
[2,"서울","성동","방학S/S 도봉방학#2T/L GIS","19년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2019-04-03 13:00","2019-04-03 15:00","2019-04-03 13:00","2019-04-03 15:00","당일",null,null,null,201902120164]
[3,"서울","성동","방학S/S 도봉방학#1T/L GIS","19년 성동P/O 관내 170kV GIS 조작시험","170kV GIS 조작시험 (차단기 개폐타임 측정)","2019-04-03 10:00","2019-04-03 13:00","2019-04-03 10:00","2019-04-03 13:00","당일",null,null,null,201902120162,"O"]
[4,"서울","성동","구리신내#1 T/L","2019년 성동P/O 변전정비회사 총액공사","170kV GIS 보통점검 (신내S/S 구리신내#1T/L)","2019-04-05 09:30","2019-04-05 17:00","2019-04-05 09:30","2019-04-05 17:00","당일",null,null,null,201902120328]
[5,"서울","성동","창동돈암 T/L","2019년 성동P/O 변전정비회사 총액공사","170kV GIS 보통점검 (창동S/S 창동돈암T/L)","2019-04-01 09:30","2019-04-01 17:00","2019-04-01 09:30","2019-04-01 17:00","당일",null,null,null,201902120288]
[6,"서울","성동","방학창동#1 T/L","2019년 성동P/O 변전정비회사 총액공사","170kV GIS 보통점검 (창동S/S 방학창동#1T/L)","2019-04-02 09:30","2019-04-02 17:00","2019-04-02 09:30","2019-04-02 17:00","당일",null,null,null,201902120324,"O"]
[7,"서울","성동","방학창동#2 T/L","2019년 성동P/O 변전정비회사 총액공사","170kV GIS 보통점검 (창동S/S 방학창동#2T/L)","2019-04-03 09:30","2019-04-03 17:00","2019-04-03 09:30","2019-04-03 17:00","당일",null,null,null,201902120325]
[8,"서울","중부","동빙고반포#2 T/L","154kV 동빙고반포#2T/L OF케이블 절연유 채취","154kV 동빙고반포#2T/L OF케이블 절연유 채취","2019-04-03 09:30","2019-04-03 17:00","2019-04-03 09:30","2019-04-03 17:00","당일",null,null,null,201902140041]
[9,"서울","중부","수색상암#1 T/L","2019년 중부전력지사 변전협력회사 총액공사","ㅇ154kV 수색상암#1T/L GIS 보통점검","2019-04-25 09:00","2019-04-25 18:00","2019-04-25 09:00","2019-04-25 18:00","당일",null,null,null,201902130399]
[10,"서울","중부","수색상암#2 T/L","2019년 중부전력지사 변전협력회사 총액공사","ㅇ154kV 수색상암#2T/L GIS 보통점검","2019-04-26 09:00","2019-04-26 18:00","2019-04-26 09:00","2019-04-26 18:00","당일",null,null,null,201902130410]
[11,"서울","중부","중부용산#1 T/L","2019년 중부전력지사 변전협력회사 총액공사","ㅇ154kV 중부용산#1T/L GIS 보통점검","2019-04-11 09:00","2019-04-11 18:00","2019-04-11 09:00","2019-04-11 18:00","당일",null,null,null,201902130387]
[12,"서울","중부","중부용산#2 T/L","2019년 중부전력지사 변전협력회사 총액공사","ㅇ154kV 중부용산#2T/L GIS 보통점검","2019-04-12 09:00","2019-04-12 18:00","2019-04-12 09:00","2019-04-12 18:00","당일",null,null,null,201902130388]
[13,"서울","직할","서소문S/S 154kV #2 BUS","19년 직할 변전협력회사 총액공사","PT 하자점검","2019-04-29 14:00","2019-04-29 18:00","2019-04-29 14:00","2019-04-29 18:00","당일",null,null,null,201902140187]
[14,"서울","직할","서소문S/S 154kV #1 BUS","19년 직할 변전협력회사 총액공사","PT 하자점검","2019-04-29 09:00","2019-04-29 14:00","2019-04-29 09:00","2019-04-29 14:00","당일",null,null,null,201902140186]
[15,"서울","직할","운니원남#1 T/L","19년 직할 변전협력회사 총액공사","GIS 및 PT 보통점검","2019-04-18 09:00","2019-04-18 18:00","2019-04-18 09:00","2019-04-18 18:00","당일",null,null,null,201902140182]
[16,"서울","직할","옥인운니#2 T/L","19년 직할 변전협력회사 총액공사","GIS 및 PT 보통점검","2019-04-17 09:00","2019-04-17 18:00","2019-04-17 09:00","2019-04-17 18:00","당일",null,null,null,201902140180]
[17,"서울","직할","운니원남#2 T/L","19년 직할 변전협력회사 총액공사","GIS 및 PT 보통점검","2019-04-19 09:00","2019-04-19 18:00","2019-04-19 09:00","2019-04-19 18:00","당일",null,null,null,201902140183]
[18,"서울","직할","옥인운니#1 T/L","19년 직할 변전협력회사 총액공사","GIS 및 PT 보통점검","2019-04-16 09:00","2019-04-16 18:00","2019-04-16 09:00","2019-04-16 18:00","당일",null,null,null,201902140179]
[19,"남서울","동서울","가락수서#2 T/L","170kV GIS 정밀점검","가락S/S 170kV GIS 정밀점검 수서S/S 조작시험 및 전자변교체","2019-04-17 14:00","2019-04-19 18:00","2019-04-17 14:00","2019-04-19 18:00","연속",null,null,null,201902130418]
[20,"남서울","동서울","가락수서#1 T/L","170kV GIS 정밀점검","가락S/S 170kV GIS 정밀점검 수서S/S 조작시험 및 전자변교체","2019-04-15 09:00","2019-04-17 14:00","2019-04-15 09:00","2019-04-17 14:00","연속",null,null,null,201902130413,"O"]
[21,"남서울","동서울","동서울S/S 66-67-0 SEC CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-04-18 09:00","2019-04-18 18:00","취소","취소","당일",null,null,null,201902130465]
[22,"남서울","동서울","동서울S/S 154kV #1 BUS TIE CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-04-15 09:00","2019-04-15 14:00","취소","취소","당일",null,null,null,201902130434]
[23,"남서울","동서울","동서울서종#1 T/L","170kV GCB 보통점검","170kV GCB 보통점검","2019-04-08 10:00","2019-04-08 18:00","2019-04-08 10:00","2019-04-08 18:00","당일",null,null,null,201902130359,"O"]
[24,"남서울","동서울","동서울서종#2 T/L","170kV GCB 보통점검","170kV GCB 보통점검","2019-04-09 10:00","2019-04-09 18:00","2019-04-09 10:00","2019-04-09 18:00","당일",null,null,null,201902130360]
[25,"남서울","동서울","동서울S/S 61-62-0 SEC CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-04-17 14:00","2019-04-17 18:00","취소","취소","당일",null,null,null,201902130461]
[26,"남서울","동서울","동서울S/S 65-66-0 SEC CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-04-17 09:00","2019-04-17 14:00","취소","취소","당일",null,null,null,201902130458]
[27,"남서울","동서울","동서울S/S 60-61-0 SEC CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-04-16 14:00","2019-04-16 18:00","취소","취소","당일",null,null,null,201902130449]
[28,"남서울","동서울","동서울S/S 154kV #2 BUS TIE CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-04-16 09:00","2019-04-16 14:00","취소","취소","당일",null,null,null,201902130446]
[29,"남서울","동서울","산성수서#1 T/L","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-04-24 09:00","2019-04-24 14:00","취소","취소","당일",null,null,null,201902130380]
[30,"남서울","동서울","산성수서#2 T/L","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-04-24 14:00","2019-04-24 18:00","취소","취소","당일",null,null,null,201902130381]
[31,"남서울","동서울","동서울신장#1 T/L","신장S/S 170kV 장기사용 GIS 교체공사(#1BUS 무부하 가압용)","신장S/S 170kV 장기사용 GIS 교체공사(#1BUS 무부하 가압용)","2019-04-20 16:00","2019-04-20 18:00","취소","취소","당일",null,null,null,201902130638]
[32,"남서울","동서울","동서울신장#2 T/L","신장S/S 170kV 장기사용 GIS 교체공사","신장S/S 170kV 장기사용 GIS 교체공사","2019-04-01 09:00","2019-04-30 18:00","취소","취소","연속",null,null,null,201902130636]
[33,"남서울","동서울","동서울신장#1 T/L","신장S/S 170kV 장기사용 GIS 교체공사(#2BUS 무부하 가압용)","신장S/S 170kV 장기사용 GIS 교체공사(#2BUS 무부하 가압용)","2019-04-05 16:00","2019-04-05 18:00","취소","취소","당일",null,null,null,201902130637]
[34,"남서울","동서울","강동풍납#2 T/L","154kV 강동-풍납T/L 풍납S/S 인출구간 선종교체공사","OF케이블 XLPE케이블 선종교체","2019-04-22 09:00","2019-05-31 18:00","취소","취소","연속",null,null,null,201902080230]
[35,"남서울","영등포","광명구공#3 T/L","광명-구공#3T/L 보통점검 및 보호반교체","광명-구공#3T/L 보통점검 및 송전선로 보호반교체","2019-04-20 09:00","2019-04-21 18:00","2019-04-20 09:00","2019-04-21 18:00","연속",null,null,null,201902110322]
[36,"남서울","영등포","광명구공#1 T/L","구공S/S 154kV GIS 조작점검","광명-구공#1T/L GIS 점검","2019-04-06 09:00","2019-04-06 14:00","2019-04-06 09:00","2019-04-06 14:00","당일",null,null,null,201902110563]
[37,"남서울","영등포","광명구공#2 T/L","구공S/S 154kV GIS 조작점검","광명-구공#2T/L GIS 점검","2019-04-06 14:00","2019-04-06 18:00","2019-04-06 14:00","2019-04-06 18:00","당일",null,null,null,201902110578]
[38,"남서울","영등포","천왕구로#1 T/L","구로S/S 154kV GIS 조작시험","천왕-구로#1T/L GIS 조작시험","2019-04-05 09:00","2019-04-05 14:00","2019-04-05 09:00","2019-04-05 14:00","당일",null,null,null,201902110457]
[39,"남서울","영등포","천왕구로#2 T/L","구로S/S 154kV GIS 조작시험","천왕-구로#2T/L GIS 조작시험","2019-04-05 14:00","2019-04-05 18:00","2019-04-05 14:00","2019-04-05 18:00","당일",null,null,null,201902110458]
[40,"남서울","영등포","독산대방#1 T/L","독산S/S 154kV GIS 조작시험","독산-대방#1T/L GIS 조작시험","2019-04-07 09:00","2019-04-07 14:00","취소","취소","당일",null,null,null,201902110481]
[41,"남서울","영등포","독산대방#2 T/L","독산S/S 154kV GIS 조작시험","독산-대방#2T/L GIS 조작시험","2019-04-07 14:00","2019-04-07 18:00","취소","취소","당일",null,null,null,201902110483]
[42,"남서울","영등포","마곡S/S 154kV #1 BUS","154kV 마곡S/S #4M.Tr 증설공사","154kV M.Tr x 1 bank 170kV GIS x 1 cct 25.8kV SIS x 3 cct","2019-04-08 10:00","2019-04-10 10:00","2019-04-06 10:00","2019-04-07 10:00","연속",null,null,null,201902080311]
[43,"남서울","영등포","화곡마곡#2 T/L","154kV 마곡S/S #4M.Tr 증설공사","170kV GIS 1CCT 증설 - 무부하가압(24H)","2019-04-09 10:00","2019-04-10 10:00","2019-04-06 10:00","2019-04-07 10:00","연속",null,null,null,201902080312]
[44,"남서울","영등포","화곡마곡#2 T/L","154kV 마곡S/S #4M.Tr 증설공사","170kV GIS 1CCT 증설 - 무부하가압(24H)","2019-04-11 10:00","2019-04-12 10:00","2019-04-13 10:00","2019-04-14 10:00","연속",null,null,null,201902080316]
[45,"남서울","영등포","마곡S/S 154kV #2 BUS","154kV 마곡S/S #4M.Tr 증설공사","154kV M.Tr x 1 bank 170kV GIS x 1 cct 25.8kV SIS x 3 cct","2019-04-10 10:00","2019-04-12 10:00","2019-04-13 10:00","2019-04-14 10:00","연속",null,null,null,201902080315]
[46,"남서울","영등포","신광명시흥#2 T/L","신광명-시흥#2T/L LA 및 GIS 점검","시흥S/S 신광명-시흥#2T/L LA 점검 신광명S/S 신광명-시흥#2T/L 154kV GIS 초기점검","2019-04-14 09:00","2019-04-14 18:00","취소","취소","당일",null,null,null,201902110303]
[47,"남서울","영등포","신광명시흥#1 T/L","신광명-시흥#1T/L LA 및 GIS 점검","시흥S/S 154kV LA 점검 및 신광명S/S 154kV GIS 초기점검","2019-04-13 09:00","2019-04-13 18:00","취소","취소","당일",null,null,null,201902110296]
[48,"남서울","직할","대방신길#1 T/L","154kV 신길인출전력구 OF케이블 선종교체공사","154kV 신길인출전력구 내 154kV 대방-신길#1T/L 선종교체공사 교체선종 : OF 1200 -&gtXLPE 1200","2019-04-29 09:00","2019-06-21 18:00","2019-04-29 09:00","2019-06-21 18:00","연속",null,null,null,201902120179]
[49,"인천","시흥","신시흥남동#1T/L","신시흥,남동S/S 신시흥남동#1T/L GIS 보통점검","신시흥,남동S/S 신시흥남동#1T/L GIS 보통점검","2019-04-04 10:00","2019-04-04 18:00","2019-04-04 10:00","2019-04-04 18:00","당일"]
[50,"인천","시흥","신시흥남동#2T/L","신시흥,남동S/S 신시흥남동#2T/L GIS 보통점검","신시흥,남동S/S 신시흥남동#2T/L GIS 보통점검","2019-04-05 10:00","2019-04-05 18:00","2019-04-05 10:00","2019-04-05 18:00","당일"]
[51,"인천","인천","신경서경서#3T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압","신경서S/S 서인천CC신경서T/L 정밀점검 관련 무부하 가압(#65BUS 휴전 및 신경서경서#3T/L 이용) ","2019-04-06 15:00","2019-04-06 18:00","2019-04-06 15:00","2019-04-06 18:00","당일"]
[52,"인천","인천","신경서S/S 154kV #65 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압 ","신경서S/S 서인천CC신경서T/L 정밀점검 관련 무부하 가압(#65BUS 휴전 및 신경서경서#3T/L 이용) ","2019-04-06 15:00","2019-04-06 18:00","2019-04-06 15:00","2019-04-06 18:00","당일"]
[53,"인천","인천","신현포스코CC#1T/L","SVL 교체공사","구형 SVL을 신형 SVL로 교체(난연성 확보) ","2019-04-09 09:00","2019-04-12 18:00","2019-04-09 09:00","2019-04-12 18:00","연속"]
[54,"인천","인천","신경서S/S 154kV #61 BUS","9년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압 ","신경서S/S 신경서청라#1T/L GIS 정밀점검 관련 무부하가압 ","2019-04-10 15:00","2019-04-10 18:00","2019-04-10 15:00","2019-04-10 18:00","당일"]
[55,"인천","인천","신경서경서#1T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압 ","신경서S/S 신경서청라#1T/L GIS 정밀점검 관련 무부하가압","2019-04-10 15:00","2019-04-10 18:00","2019-04-10 15:00","2019-04-10 18:00","당일"]
[56,"인천","인천","신경서S/S 154kV #66 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압 ","신경서S/S 신경서청라#2T/L GIS 정밀점검 관련 무부하가압 ","2019-04-13 15:00","2019-04-13 18:00","2019-04-13 15:00","2019-04-13 18:00","당일"]
[57,"인천","인천","신경서경서#2T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압 ","신경서S/S 신경서청라#2T/L GIS 정밀점검 관련 무부하가압 ","2019-04-13 15:00","2019-04-13 18:00","2019-04-13 15:00","2019-04-13 18:00","당일"]
[58,"인천","직할","계양원창T/L","154kV 계양-원창T/L EBA PD 집합반 설치공사 ","루원C/H EBA PD 집합반 설치 ","2019-04-15 09:00","2019-04-16 18:00","2019-04-15 09:00","2019-04-16 18:00","연속"]
[59,"인천","인천","신현포스코CC#2T/L","SVL 교체공사","구형 SVL을 신형 SVL로 교체(난연성 확보) ","2019-04-16 09:00","2019-04-19 18:00","2019-04-16 09:00","2019-04-19 18:00","연속"]
[60,"인천","김포","경서북인천#1T/L"," 김포전력지사 154kV GIS 정밀점검공사","경서S/S 154kV 경서-북인천#1T/L GIS 정밀점검 ","2019-04-22 09:00","2019-04-24 14:00","2019-04-22 09:00","2019-04-24 14:00","연속"]
[61,"인천","시흥","도림S/S 154kV #2 BUS","154kV 도림분기 SW 증설사업 ","154kV GIS 2CCT 설치 가. 신시흥-도림#1T/L 나. 도림-오봉#1T/L ","2019-04-22 09:00","2019-04-28 18:00","2019-04-22 09:00","2019-04-28 18:00","연속"]
[62,"인천","김포","경서북인천#2T/L","김포전력지사 154kV GIS 정밀점검공사 ","경서S/S 154kV 경서-북인천#2T/L GIS 정밀점검 ","2019-04-24 09:00","2019-04-26 18:00","2019-04-24 09:00","2019-04-26 18:00","연속"]
[63,"인천","시흥","도림오봉T/L","154kV 도림분기 SW 증설사업 ","154kV GIS 2CCT 설치 가. 신시흥-도림#1T/L 나. 도림-오봉#1T/L ","2019-04-26 09:00","2019-04-28 18:00","2019-04-26 09:00","2019-04-28 18:00","연속"]
[64,"인천","시흥","도림S/S 154kV #1 BUS","154kV 도림분기 SW 증설사업 ","154kV GIS 2CCT 설치 가. 신시흥-도림#1T/L 나. 도림-오봉#1T/L ","2019-04-29 09:00","2019-05-05 18:00","2019-04-29 09:00","2019-05-05 18:00","연속"]
[65,"인천","직할","신부평S/S 154kV #66 BUS","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검(#66BUS)","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검(DS 점검 및 무부하가압용)","2019-04-30 14:00","2019-05-01 14:00","2019-04-30 14:00","2019-05-01 14:00","연속",null,null,null,201902180264]
[66,"인천","직할","신부평부흥#1 T/L","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검(#61BUS)","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검(DS 점검 및 무부하가압용)","2019-04-30 10:00","2019-04-30 14:00","2019-04-30 10:00","2019-04-30 14:00","당일",null,null,null,201902210056]
[67,"인천","인천","인천CC S/Y 154kV #1 BUS TIE GIS","인천화력S/Y 6100 GIS 조작시험","인천화력S/Y 6100 GIS 조작시험","2019-04-30 09:00","2019-04-30 18:00","2019-04-30 09:00","2019-04-30 18:00","당일",null,null,null,201902080207]
[68,"인천","직할","신부평S/S 154kV #61 BUS","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검(#61BUS)","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검(DS 점검 및 무부하가압용)","2019-04-29 14:00","2019-04-30 14:00","2019-04-29 14:00","2019-04-30 14:00","연속",null,null,null,201902180263]
[69,"인천","김포","계양김포#1 T/L","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사 - 사유 : 불로지구 공동주택 신축공사 지장 - 공사시행 : 대광에이엠씨(요청자). 끝.","2019-04-29 09:00","2019-05-17 18:00","취소","취소","연속",null,null,null,201902210078]
[70,"인천","인천","영종경서 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","영종S/S 영종경서T/L GIS 정밀점검","2019-04-29 09:00","2019-05-01 18:00","2019-04-29 09:00","2019-05-01 18:00","연속",null,null,null,201902180283]
[71,"인천","인천","인천CC북인천#1 T/L","인천화력S/Y 인천CC북인천#1T/L GIS 조작시험","-인천화력S/Y 인천CC북인천#1T/L GIS 조작시험 -북인천S/S 인천CC북인천#1T/L GIS 조작시험(병행)","2019-04-29 09:00","2019-04-29 18:00","2019-04-29 09:00","2019-04-29 18:00","당일",null,null,null,201902080206]
[72,"인천","시흥","북시화서시화#3 T/L","서시화,북시화S/S 북시화서시화#3T/L GIS 정밀점검","서시화,북시화S/S 북시화서시화#3T/L GIS 정밀점검","2019-04-29 08:30","2019-05-02 18:00","2019-04-29 08:30","2019-05-02 18:00","연속",null,null,null,201902140154]
[73,"인천","직할","신부평중동#1 T/L","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검","2019-04-29 08:00","2019-05-01 18:00","2019-04-29 08:00","2019-05-01 18:00","연속",null,null,null,201902180265]
[74,"인천","직할","부천S/S 154kV #1 BUS","부천S/S 부천원미#2T/L 170kV GIS 정밀점검(#1BUS)","부천S/S 부천원미#2T/L 170kV GIS 정밀점검(무부하 가압용)","2019-04-27 10:00","2019-04-27 16:00","2019-04-27 10:00","2019-04-27 16:00","당일",null,null,null,201902180254]
[75,"인천","직할","부천도당#2 T/L","부천S/S 부천원미#2T/L 170kV GIS 정밀점검","부천S/S 부천원미#2T/L 170kV GIS 정밀점검(무부하 가압용)","2019-04-27 10:00","2019-04-27 16:00","2019-04-27 10:00","2019-04-27 16:00","당일",null,null,null,201902210048]
[76,"인천","김포","김포S/S 154kV #2 BUS","154kV 계양-김포#2T/L 지장이설공사 준공시험","154kV 계양-김포#2T/L 지장이설공사 준공시험 - 상체크 등 시험. 끝.","2019-04-25 09:00","2019-04-25 18:00","2019-04-25 09:00","2019-04-25 18:00","당일",null,null,null,201902210076]
[77,"인천","직할","부천원미#2 T/L","부천S/S 부천원미#2T/L 170kV GIS 정밀점검","부천S/S 부천원미#2T/L 170kV GIS 정밀점검","2019-04-25 08:00","2019-04-27 18:00","2019-04-25 08:00","2019-04-27 18:00","연속",null,null,null,201902180252]
[78,"인천","직할","부천도당#1 T/L","부천S/S 부천원미#1T/L 170kV GIS 정밀점검","부천S/S 부천원미#1T/L 170kV GIS 정밀점검(무부하 가압용)","2019-04-24 10:00","2019-04-24 16:00","2019-04-20 10:00","2019-04-20 16:00","당일",null,null,null,201902210047]
[79,"인천","직할","부천S/S 154kV #1 BUS","부천S/S 부천원미#1T/L 170kV GIS 정밀점검(#1BUS)","부천S/S 부천원미#1T/L 170kV GIS 정밀점검(무부하 가압용)","2019-04-24 10:00","2019-04-24 16:00","2019-04-20 10:00","2019-04-20 16:00","당일",null,null,null,201902180256]
[80,"인천","인천","신현송현#2 T/L","신현S/S 신현송현#2T/L GIS 초기점검","신현S/S 신현송현#2T/L GIS 초기점검","2019-04-24 09:00","2019-04-24 18:00","2019-04-24 09:00","2019-04-24 18:00","당일",null,null,null,201902080205]
[81,"인천","인천","영종중산 T/L","영종S/S 영종중산T/L GIS 하자점검","-영종S/S 영종중산T/L GIS 하자점검 -중산S/S 영종중산T/L GIS 조작시험(병행)","2019-04-23 09:00","2019-04-23 18:00","2019-04-23 09:00","2019-04-23 18:00","당일",null,null,null,201902080203]
[82,"인천","시흥","동시화서시화 T/L","서시화S/S 154kV 동시화서시화 T/L GIS 정밀점검","서시화S/S 154kV 동시화서시화 T/L GIS 정밀점검","2019-04-22 08:30","2019-04-23 18:00","2019-04-22 08:30","2019-04-23 18:00","연속",null,null,null,201902140147]
[83,"인천","직할","부천원미#1 T/L","부천S/S 부천원미#1T/L 170kV GIS 정밀점검","부천S/S 부천원미#1T/L 170kV GIS 정밀점검","2019-04-22 08:00","2019-04-24 18:00","2019-04-22 08:00","2019-04-24 18:00","연속",null,null,null,201902180251]
[84,"인천","인천","신경서중산 T/L","신경서S/S 신경서중산T/L GIS 하자점검","-신경서S/S 신경서중산T/L GIS 하자점검 -중산S/S 신경서중산T/L GIS 조작시험(병행)","2019-04-19 09:00","2019-04-19 18:00","2019-04-19 09:00","2019-04-19 18:00","당일",null,null,null,201902080202]
[85,"인천","직할","부천원미#2 T/L","부천S/S DB하이텍T/L 170kV GIS 정밀점검","부천S/S DB하이텍T/L 170kV GIS 정밀점검 (#2BUS DS점검 및 무부하가압용 부천원미#2T/L 휴전)","2019-04-18 10:00","2019-04-18 16:00","2019-04-13 10:00","2019-04-13 16:00","당일",null,null,null,201902200205]
[86,"인천","직할","부천S/S 154kV #2 BUS","부천S/S DB하이텍T/L 170kV GIS 정밀점검(#2BUS)","부천S/S DB하이텍T/L 170kV GIS 정밀점검(DS점검 및 무부하 가압용 모선휴전)","2019-04-18 10:00","2019-04-19 10:00","2019-04-13 10:00","2019-04-14 10:00","연속",null,null,null,201902180248]
[87,"인천","인천","학익연수#1 T/L","학익S/S 학익연수#1T/L GIS 조작시험","학익S/S 학익연수#1T/L GIS 조작시험","2019-04-18 09:00","2019-04-18 18:00","2019-04-18 09:00","2019-04-18 18:00","당일",null,null,null,201902080201]
[88,"인천","직할","부천원미#1 T/L","부천S/S DB하이텍T/L 170kV GIS 정밀점검","부천S/S DB하이텍T/L 170kV GIS 정밀점검 (#1BUS DS점검 및 무부하가압용 부천원미#1T/L 휴전)","2019-04-17 10:00","2019-04-17 16:00","2019-04-06 10:00","2019-04-06 16:00","당일",null,null,null,201902200204]
[89,"인천","직할","부천S/S 154kV #1 BUS","부천S/S DB하이텍T/L 170kV GIS 정밀점검(#1BUS)","부천S/S DB하이텍T/L 170kV GIS 정밀점검(DS점검 및 무부하 가압용 모선휴전)","2019-04-17 10:00","2019-04-18 10:00","2019-04-06 10:00","2019-04-06 16:00","연속",null,null,null,201902180247]
[90,"인천","시흥","도림오봉 T/L","154kV 도림-오봉T/L EBA PD집합반 설치공사","154kV 도림-오봉T/L EBA PD집합반 설치공사","2019-04-17 09:00","2019-04-17 18:00","2019-04-17 09:00","2019-04-17 18:00","당일",null,null,null,201902120440]
[91,"인천","직할","계양북인천 T/L","154kV 계양-북인천T/L EBA PD 집합반 설치공사","루원C/H EBA PD 집합반 설치","2019-04-17 09:00","2019-04-18 18:00","2019-04-17 09:00","2019-04-18 18:00","연속",null,null,null,201902210046]
[92,"인천","시흥","신시흥오봉 T/L","154kV 신시흥-오봉T/L EBA PD집합반 설치공사","154kV 신시흥-오봉T/L EBA PD집합반 설치공사","2019-04-16 09:00","2019-04-16 18:00","2019-04-16 09:00","2019-04-16 18:00","당일",null,null,null,201902120438]
[93,"인천","인천","신현송현#1 T/L","신현S/S 신현송현#1T/L GIS 초기점검","신현S/S 신현송현#1T/L GIS 초기점검","2019-04-16 09:00","2019-04-16 18:00","2019-04-20 09:00","2019-04-20 18:00","당일",null,null,null,201902080194]
[94,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 - S/T GIS 인출 정비공사","2019-04-15 14:00","2019-04-18 14:00","2019-04-15 14:00","2019-04-18 14:00","연속",null,null,null,201902070311]
[95,"인천","시흥","신시흥북시화#1 T/L","신시흥#2S/S 신시흥북시화#1T/L 부싱 이격거리 확보 공사","신시흥#2S/S 신시흥북시화#1T/L 부싱 이격거리 확보 공사","2019-04-15 08:30","2019-04-17 18:00","2019-04-15 08:30","2019-04-17 18:00","연속",null,null,null,201902150041]
[96,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 - S/T GIS 인출 정비공사","2019-04-14 09:00","2019-04-15 14:00","2019-04-14 09:00","2019-04-15 14:00","연속",null,null,null,201902070310]
[97,"인천","직할","중동S/S S/T GIS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 -S/T GIS 인출 정비공사","2019-04-14 09:00","2019-04-23 18:00","2019-04-14 09:00","2019-04-23 18:00","연속",null,null,null,201902070309]
[98,"인천","인천","신가좌S/S 154kV #2 BUS TIE GIS","신가좌S/S 6200GIS 조작시험","신가좌S/S 6200GIS 조작시험","2019-04-12 13:00","2019-04-12 18:00","2019-04-12 13:00","2019-04-12 18:00","당일",null,null,null,201902080118]
[99,"인천","김포","신경서경서#3 T/L","경서S/S 154kV 신경서-경서#3T/L GIS 조작시험","경서S/S 154kV 신경서-경서#3T/L 677 GIS 조작시험","2019-04-12 10:00","2019-04-12 15:00","2019-04-12 10:00","2019-04-12 15:00","당일",null,null,null,201902140099]
[100,"인천","인천","신가좌S/S 61-62 SEC GIS","신가좌S/S 61-62GIS 조작시험","신가좌S/S 61-62GIS 조작시험","2019-04-12 09:00","2019-04-12 13:00","2019-04-12 09:00","2019-04-12 13:00","당일",null,null,null,201902080117]
[101,"인천","인천","신가좌S/S 154kV #1 BUS TIE GIS","신가좌S/S 6100GIS 조작시험","신가좌S/S 6100GIS 조작시험","2019-04-11 13:00","2019-04-11 18:00","2019-04-11 13:00","2019-04-11 18:00","당일",null,null,null,201902080115]
[102,"인천","김포","신경서경서#2 T/L","경서S/S 154kV 신경서-경서#2T/L GIS 조작시험","경서S/S 154kV 신경서-경서#2T/L 667 GIS 조작시험","2019-04-11 10:00","2019-04-11 15:00","2019-04-11 10:00","2019-04-11 15:00","당일",null,null,null,201902140098]
[103,"인천","인천","신가좌S/S 60-61 SEC GIS","신가좌S/S 60-61GIS 조작시험","신가좌S/S 60-61GIS 조작시험","2019-04-11 09:00","2019-04-11 13:00","2019-04-11 09:00","2019-04-11 13:00","당일",null,null,null,201902080113]
[104,"인천","시흥","신시흥북시화#1 T/L","신시흥#2S/S #67-68SEC GIS 대체공사[무부하용]","신시흥#2S/S #67-68SEC GIS 대체공사[무부하용]","2019-04-11 08:30","2019-04-12 08:30","취소","취소","연속",null,null,null,201902140121]
[105,"인천","김포","신경서경서#1 T/L","경서S/S 154kV 신경서-경서#1T/L GIS 조작시험","경서S/S 154kV 신경서-경서#1T/L 647 GIS 조작시험","2019-04-10 10:00","2019-04-10 15:00","2019-04-10 10:00","2019-04-10 15:00","당일",null,null,null,201902140097]
[106,"인천","김포","김포S/S 154kV #1 BUS","154kV 계양-김포#2T/L 지장이설공사 준공시험","154kV 계양-김포#2T/L 지장이설공사 준공시험 - 상체크 등 시험. 끝.","2019-04-10 09:00","2019-04-10 18:00","2019-04-10 09:00","2019-04-10 18:00","당일",null,null,null,201901150187]
[107,"인천","인천","신가좌S/S 154kV #3 BUS TIE GIS","신가좌S/S 6300GIS 조작시험","신가좌S/S 6300GIS 조작시험","2019-04-09 13:00","2019-04-09 18:00","2019-04-09 13:00","2019-04-09 18:00","당일",null,null,null,201902080112]
[108,"인천","김포","경서양촌#2 T/L","경서S/S 154kV 경서-양촌#2T/L GIS 조작시험","경서S/S 154kV 경서-양촌#2T/L 687 GIS 조작시험","2019-04-09 10:00","2019-04-09 15:00","2019-04-09 10:00","2019-04-09 15:00","당일",null,null,null,201902140096]
[109,"인천","인천","신가좌S/S 65-66 SEC GIS","신가좌S/S 65-66 GIS 조작시험","신가좌S/S 65-66 GIS 조작시험","2019-04-09 09:00","2019-04-09 13:00","2019-04-09 09:00","2019-04-09 13:00","당일",null,null,null,201902080111]
[110,"인천","김포","경서양촌#1 T/L","경서S/S 154kV 경서-양촌#1T/L GIS 하자점검","경서S/S 154kV 경서-양촌#1T/L 617 GIS 하자점검","2019-04-08 10:00","2019-04-08 18:00","2019-04-08 10:00","2019-04-08 18:00","당일",null,null,null,201902140095]
[111,"인천","김포","계양김포#2 T/L","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사 - 사유 : 불로지구 공동주택 신축공사 지장 - 공사시행 : 대광에이엠씨(요청자). 끝.","2019-04-08 09:00","2019-04-26 18:00","취소","취소","연속",null,null,null,201902210074]
[112,"인천","시흥","신시흥시화#2 T/L","신시흥#2S/S #67-68SEC GIS 대체공사[이격거리]","신시흥#2S/S #67-68SEC GIS 대체공사[이격거리]","2019-04-08 08:30","2019-04-09 18:00","취소","취소","연속",null,null,null,201902140119]
[113,"인천","시흥","신시흥북시화#1 T/L","신시흥#2S/S #67-68SEC GIS 대체공사[이격거리]","신시흥#2S/S #67-68SEC GIS 대체공사[이격거리]","2019-04-08 08:30","2019-04-09 18:00","취소","취소","연속",null,null,null,201902140118]
[114,"인천","직할","중동화곡#1 T/L","154kV중동화곡T/L 태풍취약철탑 보강공사","154kV중동화곡T/L 태풍취약철탑 보강공사","2019-04-07 11:00","2019-04-07 15:00","2019-04-07 11:00","2019-04-07 15:00","당일",null,null,null,201902150230]
[115,"인천","직할","중동화곡#2 T/L","154kV중동화곡T/L 태풍취약철탑 보강공사","154kV중동화곡T/L 태풍취약철탑 보강공사","2019-04-07 08:00","2019-04-07 11:00","2019-04-07 08:00","2019-04-07 11:00","당일",null,null,null,201902150231]
[116,"인천","직할","신부평고강#2 T/L","154kV신부평고강T/L 태풍취약철탑 보강공사","154kV신부평고강T/L 태풍취약철탑 보강공사","2019-04-06 13:00","2019-04-06 18:00","2019-04-06 13:00","2019-04-06 18:00","당일",null,null,null,201902150229]
[117,"인천","직할","신부평고강#1 T/L","154kV신부평고강T/L 태풍취약철탑 보강공사","154kV신부평고강T/L 태풍취약철탑 보강공사","2019-04-06 08:00","2019-04-06 13:00","2019-04-06 08:00","2019-04-06 13:00","당일",null,null,null,201902150228]
[118,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 - #2G/T GIS 인출 정비공사","2019-04-05 14:00","2019-04-08 14:00","2019-04-05 14:00","2019-04-08 14:00","연속",null,null,null,201902070308]
[119,"인천","인천","남인천S/S 154kV #1 BUS TIE GIS","남인천S/S 6100 GIS 보통점검","남인천S/S 6100 GIS 보통점검","2019-04-05 09:00","2019-04-05 18:00","2019-04-05 09:00","2019-04-05 18:00","당일",null,null,null,201902070257]
[120,"인천","인천","신가좌S/S 66-67 SEC GIS","신가좌S/S 66-67 GIS 조작시험","신가좌S/S 66-67 GIS 조작시험","2019-04-05 09:00","2019-04-05 18:00","2019-04-05 09:00","2019-04-05 18:00","당일",null,null,null,201902070271]
[121,"인천","시흥","신시흥시화#2 T/L","신시흥#2S/S #67-68SEC GIS 대체공사[무부하용]","신시흥#2S/S #67-68SEC GIS 대체공사[무부하용]","2019-04-05 08:30","2019-04-06 08:30","취소","취소","연속",null,null,null,201902140117]
[122,"인천","인천","신경서서인천CC T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","신경서S/S 서인천CC신경서T/L GIS 정밀점검","2019-04-04 09:00","2019-04-06 18:00","2019-04-04 09:00","2019-04-06 18:00","연속",null,null,null,201902180279]
[123,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 - #2G/T GIS 인출 정비공사","2019-04-04 09:00","2019-04-05 14:00","2019-04-04 09:00","2019-04-05 14:00","연속",null,null,null,201902070307]
[124,"인천","직할","중동S/S #2 G/T GIS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 - #2G/T GIS 인출 정비공사","2019-04-04 09:00","2019-04-13 18:00","2019-04-04 09:00","2019-04-13 18:00","연속",null,null,null,201902070306]
[125,"인천","시흥","신시흥시화#2 T/L","신시흥#2S/S #67-68SEC GIS 대체공사[이격거리]","신시흥#2S/S #67-68SEC GIS 대체공사[이격거리]","2019-04-01 08:30","2019-04-03 18:00","취소","취소","연속",null,null,null,201902140116]
[126,"인천","시흥","신시흥북시화#1 T/L","신시흥#2S/S #67-68SEC GIS 대체공사[이격거리]","신시흥#2S/S #67-68SEC GIS 대체공사[이격거리]","2019-04-01 08:30","2019-04-03 18:00","취소","취소","연속",null,null,null,201902140107]
[127,"인천","직할","신부평중동#1 T/L","중동S/S 170kV 인출GIS 정비공사[무부하가압용]","중동S/S 170kV 인출GIS 정비공사 - S/T GIS 인출 정비공사[무부하가압용]","2019-04-22 15:00","2019-04-23 15:00","2019-04-22 15:00","2019-04-23 15:00","연속","연속"]
[128,"인천","직할","신부평중동#2 T/L","중동S/S 170kV 인출GIS 정비공사[무부하가압용]","중동S/S 170kV 인출GIS 정비공사 - G/T#3 GIS 인출 정비공사[무부하가압용]","2019-04-02 15:00","2019-04-03 15:00","2019-04-02 15:00","2019-04-03 15:00","연속","연속"]
[129,"인천","직할","신부평중동#3 T/L","중동S/S 170kV 인출GIS 정비공사[무부하가압용]","중동S/S 170kV 인출GIS 정비공사 - G/T#2 GIS 인출 정비공사[무부하가압용]","2019-04-12 15:00","2019-04-13 15:00","2019-04-12 15:00","2019-04-13 15:00","연속","연속"]
[130,"인천","직할","신부평중동#1 T/L","중동S/S 170kV 인출GIS 정비공사[무부하가압용]","중동S/S 170kV 인출GIS 정비공사 - #5M.Tr GIS 인출 정비공사[무부하가압용]","2019-04-24 15:00","2019-04-25 15:00","2019-04-24 15:00","2019-04-25 15:00","연속","연속"]
[131,"경기북부","고양","양주고양#2 T/L","154kV 양주-고양#2T/L 지장송전선로 이설공사","서울문산고속도로 건설관련 지장철탑 이설 (154kV 양주-고양T/L 26호-28호)","2019-04-17 06:00","2019-04-21 18:00","2019-04-17 06:00","2019-04-21 18:00","연속",null,null,null,201902180107]
[132,"경기북부","고양","양주고양#1 T/L","154kV 양주-고양#1T/L 지장송전선로 이설공사","서울문산고속도로 건설관련 지장철탑 이설 (154kV 양주-고양T/L 26호-28호)","2019-04-22 06:00","2019-04-26 18:00","2019-04-22 06:00","2019-04-26 18:00","연속",null,null,null,201902180108,"O"]
[133,"경기북부","고양","백학남면#1 T/L","송전선로 항공장애표시구 설치공사","송전선로 항공장애표시구 설치공사 시행 - 345kV 신덕은-동두천CC 등 15개T/L 381개 - 하단 병가선로로 동시휴전","2019-04-01 08:00","2019-04-05 18:00","2019-04-01 08:00","2019-04-05 18:00","연속",null,null,null,201902150166]
[134,"경기북부","고양","백학남면#2 T/L","송전선로 항공장애표시구 설치공사","송전선로 항공장애표시구 설치공사 시행 - 345kV 신덕은-동두천CC 등 15개T/L 381개 - 하단 병가선로로 동시휴전","2019-04-08 08:00","2019-04-12 18:00","2019-04-08 08:00","2019-04-12 18:00","연속",null,null,null,201902150168]
[135,"경기북부","고양","양주불광#1 T/L","154kV 문산-월롱 등 11개T/L 피뢰기 설치공사","ㅇ 양주-불광 #1T/L No.1-5 피뢰기 설치","2019-04-24 07:00","2019-04-26 18:00","2019-04-24 07:00","2019-04-26 18:00","매일",null,null,null,201902130602]
[136,"경기북부","고양","월롱금촌#2 T/L","154kV 월롱-금촌#2T/L 지장송전선로 이설공사","서울문산고속도로 건설관련 지장철탑 이설 (154kV 월롱-금촌T/L 3-6호, 10-14호)","2019-04-27 06:00","2019-05-05 18:00","2019-04-27 06:00","2019-05-05 18:00","연속",null,null,null,201902180106]
[137,"경기북부","구리","구리신내#2 T/L","구리S/S 154kV 구리-신내 #2T/L GIS 보통점검공사","구리S/S 154kV 구리-신내 #2T/L GIS 보통점검공사","2019-04-15 09:00","2019-04-15 18:00","2019-04-15 09:00","2019-04-15 18:00","당일",null,null,null,201902150107]
[138,"경기북부","구리","내촌용정#2 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 내촌-용정#2T/L 정밀점검","2019-04-18 08:00","2019-04-22 18:00","2019-04-21 08:00","2019-04-25 18:00","연속",null,null,null,201902130635]
[139,"경기북부","구리","내촌용정#1 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 내촌-용정#1T/L 정밀점검","2019-04-08 08:00","2019-04-10 18:00","2019-04-08 08:00","2019-04-10 18:00","연속",null,null,null,201902130631]
[140,"경기북부","구리","덕소진건#1 T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업 154kV 덕소-진건#1T/L, 154kV 덕소-마석#1T/L 동시휴전작업으로 신설 덕소S/S 계통병입","2019-04-02 09:00","2019-05-09 18:00","2019-04-02 09:00","2019-05-09 18:00","연속",null,null,null,201901170028,"O"]
[141,"경기북부","구리","덕소마석#1 T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업 154kV 덕소-진건#1T/L, 154kV 덕소-마석#1T/L 동시휴전작업으로 신설 덕소S/S 계통병입","2019-04-02 09:00","2019-05-09 18:00","2019-04-02 09:00","2019-05-09 18:00","연속",null,null,null,201901170027,"O"]
[142,"경기북부","구리","마석청평HP#2 T/L","154kV 덕소마석T/L 등 2구간 OPGW 시설공사","1. OPGW 70/100SQ 24/48C SM 25.038km 시설 2. 광케이블(FOFC) 24/48C SM 1.018km 시설","2019-04-19 09:00","2019-04-19 18:00","2019-04-19 09:00","2019-04-19 18:00","연속",null,null,null,201902070214]
[143,"경기북부","구리","마석청평HP#1 T/L","154kV 덕소마석T/L 등 2구간 OPGW 시설공사","1. OPGW 70/100SQ 24/48C SM 25.038km 시설 2. 광케이블(FOFC) 24/48C SM 1.018km 시설","2019-04-20 09:00","2019-04-30 18:00","2019-04-20 09:00","2019-04-30 18:00","매일",null,null,null,201902070213,"O"]
[144,"경기북부","구리","미금구리#1 T/L","구리S/S 미금-구리 #1T/L GIS 보통점검공사","구리S/S 미금-구리 #1T/L GIS 보통점검공사","2019-04-03 09:00","2019-04-03 18:00","2019-04-03 09:00","2019-04-03 18:00","당일",null,null,null,201902200171]
[145,"경기북부","구리","미금광장 T/L","154kV 화양T/L 지장송전선로 이설공사","154kV 화양T/L No.18(구) 철탑 이설(1기철거, 1기 신설) 및 전선작업","2019-04-20 06:00","2019-04-21 18:00","2019-04-20 06:00","2019-04-21 18:00","연속",null,null,null,201812060043]
[146,"경기북부","구리","미금화양 T/L","154kV 화양T/L 지장송전선로 이설공사","154kV 화양T/L No.18(구) 철탑 이설(1기철거, 1기 신설) 및 전선작업","2019-04-20 06:00","2019-04-24 18:00","2019-04-20 06:00","2019-04-24 18:00","연속",null,null,null,201812060041]
[147,"경기북부","구리","미금광장 T/L","154kV 화양T/L 지장송전선로 이설공사","154kV 화양T/L No.18(구) 철탑 이설(1기철거, 1기 신설) 및 전선작업","2019-04-25 06:00","2019-04-27 18:00","2019-04-25 06:00","2019-04-27 18:00","연속",null,null,null,201812060042]
[148,"경기북부","구리","미금구리#2 T/L","154kV GIS 차단기 조작시험(18년도분)","154kV GIS 차단기 조작시험(18년도분)","2019-04-02 10:00","2019-04-02 18:00","2019-04-02 10:00","2019-04-02 18:00","당일",null,null,null,201902200165]
[149,"경기북부","구리","별내도봉 T/L","일진전기제 조립식 중간접속함(PMJ) 교체공사","별내-도봉T/L J/B#1~J/B#3 9상 교체 (R-Type → Flat-Type)","2019-04-15 08:00","2019-04-21 18:00","취소","취소","연속",null,null,null,201902070068,"O"]
[150,"경기북부","구리","신포천백학#1 T/L","송전선로 항공장애표시구 설치공사","송전선로 항공장애표시구 설치공사 시행 - 345kV 신덕은-동두천CC 등 15개T/L 381개","2019-04-08 08:00","2019-04-12 18:00","2019-04-08 08:00","2019-04-12 18:00","연속",null,null,null,201902150167]
[151,"경기북부","구리","신포천백학#2 T/L","송전선로 항공장애표시구 설치공사","송전선로 항공장애표시구 설치공사 시행 - 345kV 신덕은-동두천CC 등 15개T/L 381개","2019-04-01 08:00","2019-04-05 18:00","2019-04-01 08:00","2019-04-05 18:00","연속",null,null,null,201902150165]
[152,"경기북부","구리","문막용문 T/L","154kV 지제분기T/L 건설공사","○ 구간 : 기설 154kV 용문T/L No.80,81 ~ 지제S/S ○ 지지물 : 신설 철탑 2기(No.81, 2) ○ 전력선 : ACSR 410㎡ * 2B * 2C, 0.5km ○ 공정 1. 문막-지제#2T/L 80-81-ST 가선 2. 지제-용문#1T/L 2-1-ST 가선 3. 지제-용문#1T/L 용문SS~지제SS간 OPGW 교체","2019-04-08 07:00","2019-04-20 18:00","2019-04-08 07:00","2019-04-20 18:00","연속",null,null,null,201902180271]
[153,"경기북부","구리","운천철원#1 T/L","송전선로 항공장애표시구 설치공사","송전선로 항공장애표시구 설치공사 시행 - 345kV 신덕은-동두천CC 등 15개T/L 381개","2019-04-18 08:00","2019-04-24 18:00","2019-04-18 08:00","2019-04-24 18:00","연속",null,null,null,201902150171,"O"]
[154,"경기북부","구리","운천철원#2 T/L","송전선로 항공장애표시구 설치공사","송전선로 항공장애표시구 설치공사 시행 - 345kV 신덕은-동두천CC 등 15개T/L 381개","2019-04-08 08:00","2019-04-12 18:00","2019-04-08 08:00","2019-04-12 18:00","연속",null,null,null,201902150170]
[155,"경기북부","구리","진건별내#1 T/L","일진전기제 조립식 중간접속함(PMJ) 교체공사","진건-별내#1T/L J/B#6~J/B#8 9상 교체 (R-Type → Flat-Type)","2019-04-22 08:00","2019-04-28 18:00","2019-04-22 08:00","2019-04-28 18:00","연속",null,null,null,201902070073,"O"]
[156,"경기북부","구리","진건별내#2 T/L","일진전기제 조립식 중간접속함(PMJ) 교체공사","진건-별내#2T/L J/B#6~J/B#8 9상 교체 (R-Type → Flat-Type)","2019-04-29 08:00","2019-05-05 18:00","2019-04-29 08:00","2019-05-05 18:00","연속",null,null,null,201902070076]
[157,"경기북부","구리","별내진접 T/L","154kV GIS 정밀점검(18년 설계분)","154kV GIS 정밀점검 시험가압18년 설계분) - 6433정밀 후 별내진접, #2BUS, 6432 통해 시험가압","2019-04-01 17:30","2019-04-01 18:00","2019-04-01 17:30","2019-04-01 18:00","당일",null,null,null,201902180132]
[158,"경기북부","구리","도봉진접 T/L","154kV 도봉-진접T/L 피뢰기 설치공사","ㅇ 피뢰기 설치 - 도봉진접(별내도봉) No.10~22호 13기 - 도봉진접(진접분기) No.1~27호 27기","2019-04-22 07:00","2019-04-24 18:00","2019-04-06 07:00","2019-04-07 18:00","연속",null,null,null,201811150089]
[159,"경기북부","구리","진접S/S 154kV #2 BUS","154kV GIS 정밀점검(18년 설계분)","154kV GIS 정밀점검 시험가압18년 설계분) - 진접S/S #4M.Tr 1차 GIS 정밀 후 #2BUS, 6432 통해 시험가압","2019-04-01 17:30","2019-04-01 18:00","2019-04-01 17:30","2019-04-01 18:00","당일",null,null,null,201902180129]
[160,"경기북부","구리","덕소팔당HP청평HP T/L","청평H/P 154kV 덕소-팔당HP-청평HP T/L GCB 보통점검공사","청평H/P 154kV 덕소-팔당HP-청평HP T/L GCB 보통점검공사","2019-04-18 09:00","2019-04-18 18:00","2019-04-18 09:00","2019-04-18 18:00","당일",null,null,null,201902150110]
[161,"경기북부","구리","서홍천청평PP T/L","345kV 신가평-포천LNGCC#1T/L 송전선로 정밀점검","- 신가평S/S ~ 포천LNGCC 철탑 177기 송전선로 정밀점검 관련 병가선로(서홍천-청평PPT/L) 휴전","2019-04-08 08:30","2019-04-09 18:00","2019-04-08 08:30","2019-04-09 18:00","연속",null,null,null,201901140120]
[162,"경기북부","직할","녹양백석#1 T/L","'19년 변전정비회사 총액공사 (녹양S/S 녹양-백석 #1 T/L)","170kV GIS 보통점검","2019-04-02 09:00","2019-04-02 18:00","2019-04-02 09:00","2019-04-02 18:00","당일",null,null,null,201902150266]
[163,"경기북부","직할","녹양백석#2 T/L","'19년 변전정비회사 총액공사 (녹양S/S 녹양-백석 #2 T/L)","170kV GIS 보통점검","2019-04-03 09:00","2019-04-03 18:00","2019-04-03 09:00","2019-04-03 18:00","당일",null,null,null,201902150267]
[164,"경기북부","직할","신의정부내촌#2 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 신의정부-내촌#2T/L 정밀점검","2019-04-01 08:00","2019-04-08 18:00","2019-04-01 08:00","2019-04-08 12:00","연속",null,null,null,201902130628]
[165,"경기북부","직할","신의정부내촌#1 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 신의정부-내촌#1T/L 정밀점검","2019-04-11 08:00","2019-04-18 18:00","2019-04-11 08:00","2019-04-18 12:00","연속",null,null,null,201902130632]
[166,"경기북부","직할","신의정부송우#2 T/L","2018~2019년 경기북부직할 가공송전 정비회사 총액공사","154kV 신의정부-송우#2T/L 피뢰기 설치","2019-04-17 08:00","2019-04-18 13:00","2019-04-19 08:00","2019-04-20 13:00","연속",null,null,null,201902130634]
[167,"경기북부","직할","신의정부송우#1 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 신의정부-내촌#2T/L 정밀점검 하단병가선로","2019-04-05 08:00","2019-04-05 18:00","2019-04-05 08:00","2019-04-05 18:00","연속",null,null,null,201902130630]
[168,"경기북부","직할","양주은평#2 T/L","154kV 문산-월롱 등 11개T/L 피뢰기 설치공사","ㅇ 양주-은평 #2T/L No.1-5 피뢰기 설치","2019-04-24 07:00","2019-04-26 18:00","2019-04-27 07:00","2019-04-29 18:00","매일",null,null,null,201902130606]
[169,"경기북부","직할","양주쌍문#1 T/L","양주 S/S 옥외철구 GIS화 전력구공사","양주-쌍문#1T/L 인출측 전력구공사","2019-04-09 09:00","2019-04-11 18:00","2019-04-13 09:00","2019-04-14 18:00","연속",null,null,null,201902140063,"O"]
[170,"경기북부","직할","양주쌍문#2 T/L","양주 S/S 옥외철구 GIS화 전력구공사","양주-쌍문#2T/L 인출측 전력구공사","2019-04-06 09:00","2019-04-08 18:00","2019-04-06 09:00","2019-04-08 18:00","연속",null,null,null,201902140062]
[171,"경기북부","직할","양주S/S 154kV #61 BUS","양주변전소 옥외철구 GIS화 공사","가공지선 철거","2019-04-04 09:00","2019-04-04 18:00","2019-04-04 09:00","2019-04-04 18:00","당일"]
[172,"경기북부","직할","양주S/S 154kV #62 BUS","양주변전소 옥외철구 GIS화 공사","가공지선 철거","2019-04-05 09:00","2019-04-05 18:00","2019-04-05 09:00","2019-04-05 18:00","당일"]
[173,"경기","군포","신안산남안산#2 T/L","남안산S/S 신안산-남안산#2T/L GIS 보통점검","남안산 : 신안산-남안산#2T/L GIS 보통점검 신안산 : 신안산-남안산#2T/L GIS 조작시험","2019-04-16 09:00","2019-04-16 18:00","2019-04-16 09:00","2019-04-16 18:00","당일",null,null,null,201902110448]
[174,"경기","군포","신안산남안산#1 T/L","남안산S/S 신안산-남안산#1T/L GIS 보통점검","남안산 : 신안산-남안산#1T/L GIS 보통점검 신안산 : 신안산-남안산#1T/L GIS 조작시험","2019-04-26 09:00","2019-04-26 18:00","2019-04-26 09:00","2019-04-26 18:00","당일",null,null,null,201902110443]
[175,"경기","군포","서서울#2남수원 #1T/L","154kV 봉담분기T/L 건설공사","154kV 봉담분기T/L 건설공사 관련 안전이격 - 신설 No.1, 8 기초 가시설 철거 관련 안전이격 (기설 No.32, 38 건립선하 내 중장비 투입 작업)","2019-04-24 08:00","2019-04-25 18:00","2019-04-24 08:00","2019-04-25 18:00","연속",null,null,null,201902130332]
[176,"경기","군포","서서울#2남수원 #1T/L","154kV 봉담분기T/L 건설공사","154kV 봉담분기T/L 건설공사 관련 안전이격 - 신설 No.1, 8 상부재 조립 관련 안전이격 (기설 No.32, 38 근접 작업)","2019-04-29 08:00","2019-05-02 18:00","2019-04-29 08:00","2019-05-02 18:00","연속",null,null,null,201902130335]
[177,"경기","군포","서서울#2일동 #2T/L","서서울#2S/S 서서울2-일동#2T/L GIS 하자점검","서서울#2S/S 서서울2-일동#2T/L GIS 하자점검","2019-04-09 09:00","2019-04-09 18:00","2019-04-09 09:00","2019-04-09 18:00","당일",null,null,null,201902110123]
[178,"경기","군포","서서울#2일동 #1T/L","서서울#2S/S 서서울2-일동#1T/L GIS 하자점검","서서울#2S/S 서서울2-일동#1T/L GIS 하자점검","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902110122]
[179,"경기","군포","서안양S/S 서서울2-서안양T/L GIS","서안양S/S 서서울2-서안양T/L GIS 조작시험","서안양S/S 서서울2-서안양T/L GIS 조작시험 서서울2S/S 서서울2-서안양T/L GIS 하자점검","2019-04-25 09:00","2019-04-25 18:00","2019-04-25 09:00","2019-04-25 18:00","당일",null,null,null,201902110633]
[180,"경기","군포","서안양소래 T/L","서안양SS 서안양소래 T/L 보통점검","서안양SS 154kV 서안양소래 T/L 보통점검","2019-04-30 09:00","2019-04-30 18:00","2019-04-30 09:00","2019-04-30 18:00","당일",null,null,null,201902110652]
[181,"경기","군포","시화성곡 T/L","성곡S/S 시화-성곡T/L GIS 조작시험","성곡 : 조작시험, 시화 : 조작시험.","2019-04-23 09:00","2019-04-23 14:00","2019-04-24 09:00","2019-04-24 14:00","당일",null,null,null,201902110503]
[182,"경기","군포","시화동시화#2 T/L","2018년 군포전력 GIS 정밀점검공사_시화S/S 시화동시화#2","시화S/S 시화동시화#2TL GIS 정밀점검 - CB 정밀점검 및 전자변 교체","2019-04-06 08:00","2019-04-07 18:00","2019-04-06 08:00","2019-04-07 18:00","연속",null,null,null,201901230023]
[183,"경기","군포","조암S/S 조암-구문천#2T/L GIS","2019년 군포 154kV GIS정밀점검 공사","2019년 군포 154kV GIS정밀점검 공사 -조암구문천 #2 T/L GIS정밀점검","2019-04-29 08:00","2019-05-01 20:00","2019-04-29 08:00","2019-05-01 20:00","연속",null,null,null,201902120389]
[184,"경기","군포","조암S/S 조암-구문천#1T/L GIS","2019년 군포 154kV GIS정밀점검 공사","2019년 군포 154kV GIS정밀점검 공사 -#3M.Tr GIS 무부하가압용","2019-04-25 08:00","2019-04-27 20:00","2019-04-25 08:00","2019-04-27 20:00","연속",null,null,null,201902120560]
[185,"경기","동부","가남S/S 154kV 왕암-가남#2T/L GIS","19년 동부변전협력회사 총액공사","가남: 왕암-가남 #2T/L GIS(보통) ,43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-04-10 09:00","2019-04-10 18:00","2019-04-10 09:00","2019-04-10 18:00","당일",null,null,null,201902130244]
[186,"경기","동부","가남S/S 154kV 왕암-가남#1T/L GIS","19년 동부변전협력회사 총액공사","가남: 왕암-가남 #1T/L GIS(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-04-09 09:00","2019-04-09 18:00","2019-04-09 09:00","2019-04-09 18:00","당일",null,null,null,201902130169]
[187,"경기","동부","곤지암S/S 154kV #66 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설(3차작업) - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-04-22 08:30","2019-05-05 17:30","취소","취소","연속",null,null,null,201902130400]
[188,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-22 08:30","2019-04-24 17:30","취소","취소","연속",null,null,null,201902130401]
[189,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-17 08:30","2019-04-20 17:30","취소","취소","연속",null,null,null,201902130390]
[190,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-17 08:30","2019-04-20 17:30","취소","취소","연속",null,null,null,201902130395]
[191,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-14 08:30","2019-04-16 17:30","취소","취소","연속",null,null,null,201902130382]
[192,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-14 08:30","2019-04-16 17:30","취소","취소","연속",null,null,null,201902130384]
[193,"경기","동부","곤지암S/S 곤지암-이천#1T/L GIS","19년 동부변전협력회사 총액공사","곤지암-이천#1T/L 보호반대체(~3)","2019-04-01 09:00","2019-04-03 18:00","2019-04-01 09:00","2019-04-03 18:00","연속",null,null,null,201902130158]
[194,"경기","동부","곤지암S/S 154kV #66 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설(1차작업) - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-04-01 08:30","2019-04-07 17:30","취소","취소","연속",null,null,null,201902130348]
[195,"경기","동부","곤지암S/S 154kV #2 BUS TIE GIS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 6200 B/T 장기휴전 필요 - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-04-01 08:30","2019-04-18 17:30","취소","취소","연속",null,null,null,201902130362]
[196,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-01 08:30","2019-04-03 17:30","취소","취소","연속",null,null,null,201902130365]
[197,"경기","동부","곤지암S/S 154kV #1 Sh.C CB","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 Sh.C 장기휴전 - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-04-01 08:30","2019-04-18 17:30","취소","취소","연속",null,null,null,201902130363]
[198,"경기","동부","곤지암S/S 154kV #2 Sh.C CB","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 Sh.C 장기휴전 - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-04-01 08:30","2019-04-18 17:30","취소","취소","연속",null,null,null,201902130349]
[199,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-01 08:30","2019-04-03 17:30","취소","취소","연속",null,null,null,201902130352]
[200,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-이천T/L 피뢰기 설치공사","피뢰기설치","2019-04-30 09:00","2019-04-30 18:00","2019-04-30 09:00","2019-04-30 18:00","당일",null,null,null,201902110429]
[201,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-29 08:30","2019-05-01 17:30","취소","취소","연속",null,null,null,201902130543]
[202,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-29 08:30","2019-05-01 17:30","취소","취소","연속",null,null,null,201902130545]
[203,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-11 08:30","2019-04-13 17:30","취소","취소","연속",null,null,null,201902130378]
[204,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-11 08:30","2019-04-13 17:30","취소","취소","연속",null,null,null,201902130379]
[205,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-08 08:30","2019-04-10 17:30","취소","취소","연속",null,null,null,201902130375]
[206,"경기","동부","곤지암S/S 154kV #61 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설(2차작업) - 증설(4CCT): #4M.Tr Main, 6300 B/T, B/S, 62-67 PT - 이설(4CCT): #1Sh.C, #2Sh.C, 6200 B/T, 61-66 PT","2019-04-08 08:30","2019-04-21 17:30","취소","취소","연속",null,null,null,201902130370]
[207,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-08 08:30","2019-04-10 17:30","취소","취소","연속",null,null,null,201902130372]
[208,"경기","동부","곤지암S/S 곤지암-이천#2T/L GIS","19년 동부변전협력회사 총액공사","곤지암-이천#2T/L 보호반대체(~6)","2019-04-04 09:00","2019-04-06 18:00","2019-04-04 09:00","2019-04-06 18:00","연속",null,null,null,201902130159]
[209,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-04 08:30","2019-04-06 17:30","취소","취소","연속",null,null,null,201902130369]
[210,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-04 08:30","2019-04-07 17:30","취소","취소","연속",null,null,null,201902130366]
[211,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-22 08:30","2019-04-24 17:30","취소","취소","연속",null,null,null,201902130403]
[212,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-25 08:30","2019-04-28 17:30","취소","취소","연속",null,null,null,201902130412]
[213,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-04-25 08:30","2019-04-28 17:30","취소","취소","연속",null,null,null,201902130406]
[214,"경기","동부","성현산성#2 T/L","154kV 산성-성현 지중T/L 이설공사","○ 구 간 : 기설 154㎸ 산성-성현T/L #15 ~ #19 ○ 선종/회선길이 : 154㎸ XLPE 2,000㎟, 3회선-1.71㎞","2019-04-03 09:00","2019-04-17 18:00","2019-04-03 09:00","2019-04-17 18:00","연속",null,null,null,201902130240]
[215,"경기","동부","산성S/S 산성-수서#2T/L GIS","19년 동부변전협력회사 총액공사","산성: 산성-수서 #1,2T/L (개폐타임), Remote 회로분리 시행","2019-04-11 14:00","2019-04-11 18:00","2019-04-11 14:00","2019-04-11 18:00","당일",null,null,null,201902130246]
[216,"경기","동부","산성S/S 산성-수서#1T/L GIS","19년 동부변전협력회사 총액공사","산성: 산성-수서 #1,2T/L (개폐타임), Remote 회로분리 시행","2019-04-11 09:00","2019-04-11 14:00","2019-04-11 09:00","2019-04-11 14:00","당일",null,null,null,201902130245]
[217,"경기","동부","성현S/S 성현-산성 #1T/L GIS","19년 동부변전협력회사 총액공사","성현:산성-성현#1T/L GIS(보통), 43L/R 회로보완 확인 및 Remote 회로분리 시행 산성:산성-성현#1T/L (개폐타임), Remote 회로분리 시행 야탑:야탑-성현#1T/L GIS(보통) 43LR 회로보완확인","2019-04-19 09:00","2019-04-19 18:00","2019-04-19 09:00","2019-04-19 18:00","당일",null,null,null,201902130319]
[218,"경기","동부","성현S/S 154kV #1 BUS TIE GIS","19년 동부변전협력회사 총액공사","성현:6100 GIS(개폐타임),43L/R 회로보완 확인 및 Remote 회로분리 시행 야탑:야탑-성현#1T/L GIS(보통) 43LR 회로보완확인","2019-04-18 09:00","2019-04-18 18:00","2019-04-18 09:00","2019-04-18 18:00","당일",null,null,null,201902130320]
[219,"경기","동부","초월성현#1 T/L","154kV 곤지암-초월T/L 상간스페이서점검, 항공구설치","곤지암-초월T/L 상간스페이서점검 (4회선 구간 안전상조치), 항공구설치","2019-04-26 09:00","2019-04-26 18:00","2019-04-26 09:00","2019-04-26 18:00","당일",null,null,null,201902110419]
[220,"경기","성남","남사진위#2 T/L","ES 투입불량 확인","ES 투입불량 확인 및 불량 시 조치","2019-04-08 09:00","2019-04-11 18:00","2019-04-08 09:00","2019-04-11 18:00","연속",null,null,null,201902120455]
[221,"경기","성남","삼미동탄2열병합#2 T/L","19년 성남전력지사 변전협력총액공사","- GIS 하자점검","2019-04-05 09:00","2019-04-05 18:00","2019-04-03 10:00","2019-04-03 18:00","당일",null,null,null,201902120553]
[222,"경기","성남","삼미S/S 154kV삼미-동2열병합#1T/L(677)GIS","19년 성남전력지사 변전협력총액공사","GIS 하자점검","2019-04-04 09:00","2019-04-04 18:00","2019-04-02 10:00","2019-04-02 18:00","당일",null,null,null,201902120549]
[223,"경기","성남","삼미동탄2열병합#3 T/L","19년 성남전력지사 변전협력총액공사","삼미-동탄열병합#3T/L 하자점검","2019-04-02 09:00","2019-04-02 18:00","2019-04-04 10:00","2019-04-04 18:00","당일",null,null,null,201902120458]
[224,"경기","성남","서안성S/S 154kV #60BUS","19년 성남전력지사 170kV GIS 정밀점검","서안성 #1M.Tr 무부하 가압","2019-04-13 09:00","2019-04-13 18:00","2019-04-13 09:00","2019-04-13 18:00","당일",null,null,null,201902120022]
[225,"경기","성남","서안성S/S 154kV #66BUS","19년 성남전력지사 170kV GIS 정밀점검","서안성 #2M.Tr 2차 정밀점검 무부하","2019-04-27 09:00","2019-04-27 18:00","2019-04-27 09:00","2019-04-27 18:00","당일",null,null,null,201902120357]
[226,"경기","성남","신수원병점#2 T/L","자기애관 교체공사","작업대상 : 신수원-병점T/L 신수원C/H, 병점C/H EBA 12EA 작업내용 : 자기애관을 폴리머애관으로 교체","2019-04-01 09:00","2019-04-04 18:00","2019-04-01 09:00","2019-04-04 18:00","연속",null,null,null,201901220070]
[227,"경기","성남","신수원병점#1 T/L","자기애관 교체공사","작업대상 : 신수원-병점T/L 신수원C/H, 병점C/H EBA 12EA 작업내용 : 자기애관을 폴리머애관으로 교체","2019-04-01 09:00","2019-04-04 18:00","2019-04-01 09:00","2019-04-04 18:00","연속",null,null,null,201902110207]
[228,"경기","직할","남수원S/S 154kV #1 BUS","남수원S/S 154kV 장기사용 GIS 교체공사","남수원S/S 154kV 장기사용 GIS 교체공사(서서울2-남수원#2T/L,#1M.Tr)","2019-04-11 09:00","2019-04-12 18:00","2019-04-11 09:00","2019-04-12 18:00","연속",null,null,null,201901070299]
[229,"경기","직할","과천동안양#1 T/L","동안양S/S 옥내화부지확보 변전설비 이설공사","O. 과천-동안양#1,2T/L 의왕-동안양#1T/L 인출변경공사","2019-04-03 09:00","2019-04-16 18:00","2019-04-03 09:00","2019-04-16 18:00","연속",null,null,null,201902130547]
[230,"경기","직할","과천동안양#2 T/L","동안양S/S 옥내화부지확보 변전설비 이설공사","O. 과천-동안양#1,2T/L 의왕-동안양#1T/L 인출변경공사","2019-04-03 09:00","2019-04-11 18:00","2019-04-03 09:00","2019-04-11 18:00","연속",null,null,null,201902130548]
[231,"경기","직할","의왕동안양#1 T/L","동안양S/S 옥내화부지확보 변전설비 이설공사","O. 과천-동안양#1,2T/L 의왕-동안양#1T/L 인출변경공사","2019-04-03 09:00","2019-04-11 18:00","2019-04-03 09:00","2019-04-11 18:00","연속",null,null,null,201902130552]
[232,"경기","직할","남수원발안#1 T/L","발안S/S #5M.Tr 증설","1. 변압기 1Bank 설치 2. GIS 설치","2019-04-02 09:00","2019-04-24 17:00","2019-04-02 09:00","2019-04-23 17:00","연속",null,null,null,201902080056]
[233,"경기","직할","발안S/S 154kV #1 BUS","발안S/S #5M.Tr 증설","1. 변압기 1Bank 설치 2. GIS 설치","2019-04-02 09:00","2019-04-07 17:00","2019-04-02 09:00","2019-04-07 17:00","연속",null,null,null,201902080049]
[234,"경기","직할","발안구문천#1 T/L","발안S/S #5M.Tr 증설","1. 변압기 1Bank 설치 2. GIS 설치","2019-04-15 17:00","2019-04-16 17:00","2019-04-15 17:00","2019-04-16 17:00","연속",null,null,null,201902080058]
[235,"경기","직할","발안S/S 154kV #2 BUS","발안S/S #5M.Tr 증설","1. 변압기 1Bank 설치 2. GIS 설치","2019-04-08 09:00","2019-04-16 17:00","2019-04-08 09:00","2019-04-16 17:00","연속",null,null,null,201902080052]
[236,"경기","직할","발안구문천#1 T/L","발안S/S #5M.Tr 증설","1. 변압기 1Bank 설치 2. GIS 설치","2019-04-06 17:00","2019-04-07 17:00","2019-04-06 17:00","2019-04-07 17:00","연속",null,null,null,201902080057]
[237,"경기","직할","발안S/S 154kV #1 BUS","발안S/S #5M.Tr 증설","1. 변압기 1Bank 설치 2. GIS 설치","2019-04-17 09:00","2019-04-24 17:00","2019-04-17 09:00","2019-04-24 17:00","연속",null,null,null,201902080050]
[238,"경기","직할","서수원율전#2 T/L","154kV 서수원-율전#2T/L 일진제 PMJ 교체공사","일진제 PMJ 중간접속함 교체공사(하자)","2019-04-15 09:00","2019-04-21 18:00","2019-04-15 09:00","2019-04-21 18:00","연속",null,null,null,201901290218]
[239,"경기","직할","서수원율전#1 T/L","154kV 서수원-율전#1T/L 일진제 PMJ 교체공사","일진제 PMJ 중간접속함 교체공사(하자)","2019-04-08 09:00","2019-04-14 18:00","2019-04-08 09:00","2019-04-14 18:00","연속",null,null,null,201901290217]
[240,"경기","직할","의왕S/S 의왕-동안양#2T/L(657) GIS","의왕S/S 154kV 장기사용 GIS 대체공사","의왕S/S 의왕-동안양#2T/L(657), 군포전철#2T/L(647) GIS 대체","2019-04-12 09:00","2019-04-30 18:00","2019-04-12 09:00","2019-04-30 18:00","연속",null,null,null,201902130177]
[241,"경기","직할","의왕동안양#2 T/L","154kV 의왕S/S SW 증설공사(금정-전철 #1T/L)","ㅇ 의왕S/S SW증설설비 최초가압","2019-04-01 09:00","2019-04-02 18:00","2019-04-01 09:00","2019-04-02 18:00","연속",null,null,null,201902130321]
[242,"경기","직할","의왕S/S 율전-의왕#1T/L(687) GIS","의왕S/S 154kV 장기사용 GIS 대체공사","의왕S/S 의왕-동안양#2T/L(657), 군포전철#2T/L(647) GIS 대체관련 #1BUS 무부하가압용","2019-04-20 09:00","2019-04-21 09:00","2019-04-22 09:00","2019-04-23 09:00","연속",null,null,null,201902130186]
[243,"경기","직할","화성S/S 154kV #66 BUS","154kV 화성-발안T/L 일진제 PMJ 접속함(리콜분) 교체공사","화성-발안#2T/L J/B#1-4 접속함 교체 후 무부하가압","2019-04-06 16:00","2019-04-07 16:00","2019-04-06 16:00","2019-04-07 16:00","연속",null,null,null,201901020141]
[244,"경기","평택","고덕S/S 고덕-평택#1T/L CB","154kV 고덕-삼성전자T/L S.W 증설","154kV 고덕-삼성전자#3,4T/L 무부하 가압","2019-04-04 11:00","2019-04-05 11:00","2019-04-04 11:00","2019-04-05 11:00","연속",null,null,null,201901290197]
[245,"경기","평택","안성S/S 154kV #60 BUS","안성S/S 170kV GIS 용량대체공사","서안성-안성#1T/L GIS 철거 및 설치 6100B/T GIS 철거 및 설치 #2M.Tr GIS 철거 및 설치 - #60BUS 준공시험 - 무부하가압","2019-04-18 14:00","2019-04-19 18:00","2019-04-18 14:00","2019-04-19 18:00","연속",null,null,null,201901020041]
[246,"경기","평택","안성S/S 154kV #65 BUS","안성S/S 170kV GIS 용량대체공사","서안성-안성#2T/L GIS 철거 및 설치 #3M.Tr GIS 철거 및 설치 - #2BUS 철거 및 설치 - 준공시험","2019-04-30 18:00","2019-05-10 14:00","2019-04-30 18:00","2019-05-10 14:00","연속",null,null,null,201901150200]
[247,"경기","평택","서안성안성#2 T/L","안성S/S 170kV GIS 용량대체공사","서안성-안성#2T/L GIS 철거 및 설치 #3M.Tr GIS 철거 및 설치","2019-04-20 08:00","2019-05-11 18:00","2019-04-20 08:00","2019-05-11 18:00","연속",null,null,null,201901150196]
[248,"경기","평택","안성S/S 154kV #60 BUS","안성S/S 170kV GIS 용량대체공사","서안성-안성#1T/L GIS 철거 및 설치 6100B/T GIS 철거 및 설치 #2M.Tr GIS 철거 및 설치 - CB, #1BUS 철거 및 설치","2019-04-02 18:00","2019-04-09 18:00","2019-04-02 18:00","2019-04-09 18:00","연속",null,null,null,201901020039]
[249,"경기","평택","안성S/S 154kV #60 BUS","안성S/S 170kV GIS 용량대체공사","서안성-안성#2T/L GIS 철거 및 설치 #3M.Tr GIS 철거 및 설치 - CB, #1BUS 철거 및 설치","2019-04-23 18:00","2019-04-30 18:00","2019-04-23 18:00","2019-04-30 18:00","연속",null,null,null,201901150199]
[250,"경기","평택","안성S/S 154kV #65 BUS","안성S/S 170kV GIS 용량대체공사","서안성-안성#2T/L GIS 철거 및 설치 #3M.Tr GIS 철거 및 설치 - #2BUS 철거 및 설치","2019-04-20 08:00","2019-04-23 18:00","2019-04-20 08:00","2019-04-23 18:00","연속",null,null,null,201901150198]
[251,"경기","평택","안성S/S 154kV #65 BUS","안성S/S 170kV GIS 용량대체공사","서안성-안성#1T/L GIS 철거 및 설치 6100B/T GIS 철거 및 설치 #2M.Tr GIS 철거 및 설치 - #2BUS 철거 및 설치 - 준공시험","2019-04-09 18:00","2019-04-18 14:00","2019-04-09 18:00","2019-04-18 14:00","연속",null,null,null,201901020040]
[252,"경기","평택","고덕진위#1 T/L","154kV 고덕-진위T/L 30호 지장철탑 이설공사","남사나들목 개설 관련 30호 지장이설 2기 신설, 1기 철거","2019-04-30 09:00","2019-05-02 18:00","2019-04-30 09:00","2019-05-02 18:00","연속",null,null,null,201902120107]
[253,"경기","평택","고덕진위#2 T/L","154kV 고덕-진위T/L 30호 지장철탑 이설공사","남사나들목 개설 관련 30호 지장이설 2기 신설, 1기 철거","2019-04-27 09:00","2019-04-29 18:00","2019-04-27 09:00","2019-04-29 18:00","연속",null,null,null,201902120105]
[254,"경기","평택","청북평택#2 T/L","154kV 청북-평택#2T/L 보호반 대체","154kV 청북S/S 청북-평택#2T/L 보호반 대체 / 평택S/S 청북-평택#2T/L 보호반 대체 / 평택S/S GCB 보통점검 / 평택S/S PT, LA 보통점검","2019-04-13 10:00","2019-04-15 18:00","2019-04-13 10:00","2019-04-15 18:00","연속",null,null,null,201902130168]
[255,"경기","평택","청북평택#1 T/L","154kV 청북-평택#1T/L 보호반 대체","154kV 청북S/S 청북-평택#1T/L 보호반 대체 / 평택S/S 청북-평택#1T/L 보호반 대체","2019-04-06 10:00","2019-04-08 18:00","2019-04-06 10:00","2019-04-08 18:00","연속",null,null,null,201902130154]
[256,"경기","평택","평택추팔#2 T/L","154kV 평택추팔 34-38 안전이격확보공사","지지물 교체 3기, 임시선로 2기, 인클로징 1기","2019-04-19 08:00","2019-04-22 18:00","2019-04-19 08:00","2019-04-22 18:00","연속",null,null,null,201902070324]
[257,"경기","평택","평택추팔#1 T/L","154kV 평택추팔 34-38 안전이격확보공사","지지물 교체 3기, 임시선로 2기, 인클로징 1기","2019-04-23 08:00","2019-04-26 18:00","2019-04-23 08:00","2019-04-26 18:00","연속",null,null,null,201902070326]
[258,"경기","평택","포승S/S 포승-청북T/L GIS","포승S/S 포승-청북T/L GIS 조작시험","포승S/S 포승-청북T/L GIS 조작시험","2019-04-16 14:00","2019-04-16 18:00","2019-04-14 14:00","2019-04-14 18:00","당일",null,null,null,201902200107]
[259,"경기","평택","포승S/S 만호-포승T/L GIS","포승S/S 만호-포승T/L GIS 조작시험","포승S/S 만호-포승T/L GIS 조작시험","2019-04-16 10:00","2019-04-16 14:00","2019-04-14 10:00","2019-04-14 14:00","당일",null,null,null,201902200106]
[260,"강원","강릉","강릉횡계#2 T/L","2019년 변전협력회사 총액공사","154kV GIS 보통점검","2019-04-08 10:00","2019-04-08 18:00","2019-04-08 10:00","2019-04-08 18:00","당일",null,null,null,201902130501]
[261,"강원","동해","동해동영월 T/L","2018~2019년도 동해전력지사 송전정비 협력회사 총액공사","전선접속개소 전선교체공사 구간 : 154kV 영월화력T/L No.151~156","2019-04-26 08:00","2019-04-30 18:00","2019-04-26 08:00","2019-04-30 18:00","연속",null,null,null,201902110148]
[262,"강원","동해","동해정선 T/L","2018~2019년도 동해전력지사 송전정비 협력회사 총액공사","전선접속개소 전선교체공사 구간 : 154kV 영월화력T/L No.151~156, 1.785km","2019-04-22 08:00","2019-04-25 18:00","2019-04-22 08:00","2019-04-25 18:00","연속",null,null,null,201902110116]
[263,"강원","동해","삼척동해TP T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 삼척-동해TPT/L 정밀점검","2019-04-08 09:00","2019-04-12 18:00","2019-04-08 09:00","2019-04-12 18:00","매일",null,null,null,201902080510]
[264,"강원","동해","이원삼척 T/L","2019년 가송송전선로 순시점검 위탁공사","154kV 이원-삼척T/L 정밀점검 시행","2019-04-15 09:00","2019-04-19 18:00","2019-04-15 09:00","2019-04-19 18:00","연속",null,null,null,201902080496]
[265,"강원","동해","이원동해TP T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 이원동해TP T/L 정밀점검 시행","2019-04-01 09:00","2019-04-03 18:00","2019-04-01 09:00","2019-04-03 18:00","매일",null,null,null,201902080463]
[266,"강원","원주","홍천상남#1 T/L","2019년 원주전력지사 변전정비회사 총액공사","상남S/S 홍천-상남#1T/L 장기미동작 차단기 조작시험","2019-04-09 10:00","2019-04-09 14:00","2019-04-09 10:00","2019-04-09 14:00","당일",null,null,null,201902130408]
[267,"강원","직할","남춘천춘천 T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검","2019-04-22 09:00","2019-04-24 18:00","2019-04-22 09:00","2019-04-24 18:00","매일",null,null,null,201902080087]
[268,"강원","직할","서홍천춘천열병합 T/L","2018~2019년 강원직할 송전정비회사 총액공사","불량애자 교체 6기 17련","2019-04-24 07:00","2019-04-24 18:00","2019-04-25 07:00","2019-04-25 18:00","당일",null,null,null,201902080088]
[269,"강원","직할","서홍천청평PP T/L","2018~2019년 강원직할 송전정비회사 총액공사","불량애자 교체 5기 12련","2019-04-11 07:00","2019-04-11 18:00","2019-04-11 07:00","2019-04-11 18:00","당일",null,null,null,201902080089]
[270,"강원","직할","양구화천HP#2 T/L","2018~2019년 강원직할 송전정비회사 총액공사","상간스페이서 설치 18EA No.13~14 등 4경간","2019-04-10 07:00","2019-04-10 18:00","2019-04-10 07:00","2019-04-10 18:00","당일",null,null,null,201902080092]
[271,"강원","직할","양구화천HP#1 T/L","2018~2019년 강원직할 송전정비회사 총액공사","상간스페이서 설치 18EA No.13~14 등 4경간","2019-04-09 07:00","2019-04-09 18:00","2019-04-09 07:00","2019-04-09 18:00","당일",null,null,null,201902080091]
[272,"강원","직할","의암H/P 154kV BUS","2018년~2019년 강원지역본부 직할 변전정비 총액공사","의암H/P 154kV BUS PT 보통점검","2019-04-04 09:00","2019-04-04 18:00","2019-04-04 09:00","2019-04-04 18:00","당일",null,null,null,201902130195]
[273,"강원","직할","청평HP의암HP T/L","2018년~2019년 강원지역본부 직할 변전정비 총액공사","의암H/P 154kV 청평HP-의암HP T/L DS, LA 보통점검","2019-04-04 09:00","2019-04-04 18:00","2019-04-04 09:00","2019-04-04 18:00","당일",null,null,null,201902130194]
[274,"강원","직할","상남인제#1 T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검","2019-04-02 09:00","2019-04-10 18:00","2019-04-02 09:00","2019-04-12 18:00","매일",null,null,null,201902080084]
[275,"강원","직할","상남인제#2 T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검","2019-04-11 09:00","2019-04-19 18:00","2019-04-29 09:00","2019-05-10 18:00","매일",null,null,null,201902080085]
[276,"강원","직할","춘천소양강HP T/L","'19년 가공송전선로 순시점검 위탁공사","정밀점검","2019-04-16 09:00","2019-04-17 18:00","2019-04-16 09:00","2019-04-17 18:00","연속",null,null,null,201901160010]
[277,"강원","직할","춘천열병합S/Y #1BUS TIE CB","2018~2019년 강원지역본부 직할 변전정비 총액공사","○ 154kV #1BUS-TIE GIS 하자점검","2019-04-02 10:00","2019-04-02 14:00","2019-04-02 10:00","2019-04-02 14:00","당일",null,null,null,201902110072]
[278,"강원","직할","남춘천춘천열병합#1 T/L","2018~2019년 강원지역본부 직할 변전정비 총액공사","○ 154kV 춘천열병합S/Y 남춘천-춘천열병합#1T/L GIS 하자점검 ○ 남춘천-춘천열병합#1T/L LA 하자점검","2019-04-05 10:00","2019-04-05 18:00","2019-04-10 10:00","2019-04-10 18:00","당일",null,null,null,201902110085]
[279,"강원","직할","남춘천춘천열병합#2 T/L","2018~2019년 강원지역본부 직할 변전정비 총액공사","○ 남춘천-춘천열병합#2T/L GIS 하자점검 ○ 남춘천-춘천열병합#2T/L LA 하자점검","2019-04-08 10:00","2019-04-08 18:00","2019-04-15 10:00","2019-04-15 18:00","당일",null,null,null,201902110086]
[280,"강원","직할","춘천열병합S/Y Step-Up TR CB","2018~2019년 강원지역본부 직할 변전정비 총액공사","○ Step Up TR GIS 하자점검","2019-04-11 10:00","2019-04-11 18:00","2019-04-11 10:00","2019-04-11 18:00","당일",null,null,null,201902110146]
[281,"강원","직할","청평PP춘천열병합 T/L","2018~2019년 강원직할 송전정비회사 총액공사","불량애자 교체 9기 18련","2019-04-12 07:00","2019-04-13 18:00","2019-04-12 07:00","2019-04-13 18:00","연속",null,null,null,201902080090]
[282,"강원","직할","춘천열병합S/Y Station Aux TR CB","2018~2019년 강원지역본부 직할 변전정비 총액공사","○ 154kV 춘천열병합S/Y Station Aux TR GIS 하자점검","2019-04-03 10:00","2019-04-03 18:00","2019-04-03 10:00","2019-04-03 18:00","당일",null,null,null,201902110084]
[283,"강원","직할","철원화천#2 T/L","2019년 상반기 장기 미동작 차단기 조작시험","화천S/S 154kV 철원-화천 #2 T/L 차단기 조작시험","2019-04-10 14:00","2019-04-10 18:00","2019-04-15 14:00","2019-04-15 18:00","당일",null,null,null,201902070138]
[284,"강원","직할","화천화천HP#2 T/L","2018~2019년 강원지역본부 직할 변전정비 총액공사","○ 화천S/S 화천-화천HP #2T/L GIS 보통점검 및 피뢰기 A, B, C상 보통점검","2019-04-24 10:00","2019-04-24 18:00","2019-04-24 10:00","2019-04-24 18:00","당일",null,null,null,201902130357]
[285,"강원","직할","철원화천#1 T/L","2019년 상반기 장기 미동작 차단기 조작시험","화천S/S 154kV 철원-화천 #1 T/L 차단기 조작시험","2019-04-10 10:00","2019-04-10 14:00","2019-04-15 10:00","2019-04-15 14:00","당일",null,null,null,201902070136,"O"]
[286,"강원","태백","동영월영월CC T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 신제천-영월CC #2T/L 안전이격확보 No.1~2-1(신제천-영월No.76~78)","2019-04-18 09:00","2019-04-18 18:00","2019-04-18 09:00","2019-04-18 18:00","당일",null,null,null,201902120023]
[287,"강원","태백","정선영월CC T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 신제천-영월CC #1T/L 안전이격확보 No.1~2-1(신제천-영월No.76~78)","2019-04-11 09:00","2019-04-11 18:00","2019-04-11 09:00","2019-04-11 18:00","당일",null,null,null,201902120018]
[288,"강원","태백","영월CC S/Y 154kV #1 BUS TIE CB","18~19년 태백전력지사 변전전문회사 총액공사","영월CC 154kV #1 Bus Tie 보통점검","2019-04-01 09:00","2019-04-01 18:00","2019-04-01 09:00","2019-04-01 18:00","당일",null,null,null,201902190168]
[289,"강원","태백","태백삼척GP#1 T/L","19년 태백전력지사 170kV GIS 정밀점검","태백S/S 태백-삼척GP GIS 정밀점검","2019-04-15 10:00","2019-04-17 14:00","2019-04-15 10:00","2019-04-17 14:00","연속",null,null,null,201902120362]
[290,"강원","태백","도계태백 T/L","19년 태백전력지사 170kV GIS 정밀점검","태백S/S 도계-태백T/L GIS 정밀점검","2019-04-10 14:00","2019-04-12 18:00","2019-04-10 14:00","2019-04-12 18:00","연속",null,null,null,201902120382]
[291,"강원","태백","태백삼척GP#2 T/L","19년 태백전력지사 170kV GIS 정밀점검","태백S/S 태백-삼척GP GIS 정밀점검","2019-04-20 10:00","2019-04-27 18:00","2019-04-20 10:00","2019-04-27 18:00","연속",null,null,null,201902120374]
[292,"충북","직할","단양영월CC#2 T/L","154kV 단양-영월CCT/L 안전이격 확보공사","가. 공사구간 : 154kV 단양-영월CCT/L 13~16호, 52~55호 - 철탑교체 5기(14,15,52,53,54호), 전선교체 1.092km","2019-04-27 07:00","2019-05-25 18:00","취소","취소","연속",null,null,null,201902120502]
[293,"충북","직할","단양영월CC#1 T/L","154kV 단양-영월CCT/L 안전이격 확보공사","가. 공사구간 : 154kV 단양영월CCT/L 13~16호, 52~55호 - 철탑교체 5기(14,15,52,53,54호), 전선교체 1.092km","2019-04-22 07:00","2019-04-26 18:00","취소","취소","연속",null,null,null,201902120497]
[294,"충북","직할","신제천영월CC#1 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 신제천-영월CC #1T/L 정밀점검 (No.1~78)","2019-04-08 08:00","2019-04-16 18:00","2019-04-08 08:00","2019-04-16 18:00","매일",null,null,null,201902120011]
[295,"충북","직할","신제천영월CC#2 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 신제천-영월CC #2T/L 정밀점검 (No.1~78)","2019-04-17 08:00","2019-04-25 18:00","2019-04-17 08:00","2019-04-25 18:00","매일",null,null,null,201902120020]
[296,"충북","직할","제천영월#1 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 신제천-영월CC #2 T/L 정밀점검 안전이격확보 No.34(신제천-영월CC No.26)","2019-04-17 09:00","2019-04-17 18:00","2019-04-17 09:00","2019-04-17 18:00","당일",null,null,null,201902120014]
[297,"충북","직할","제천영월#2 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 신제천-영월CC #1 T/L 정밀점검 안전이격확보 No.34(신제천-영월CC No.26)","2019-04-10 09:00","2019-04-10 18:00","2019-04-10 09:00","2019-04-10 18:00","당일",null,null,null,201902120024]
[298,"충북","청주","청원죽림#1 T/L","154kV 청원-청주 등 8개 T/L 송전피뢰기 설치공사","154kV 청원-죽림 #1 T/L - 송전피뢰기 설치 : No.1~No.5","2019-04-06 07:00","2019-04-07 18:00","2019-04-06 07:00","2019-04-07 18:00","매일",null,null,null,201902120169]
[299,"충북","충주","진천만승#1 T/L","154kV 서운-만승 등 2개T/L 전력선교체공사","154kV 진천-만승#1T/L No.35~37 전력선교체(상하단 4선)","2019-04-24 08:00","2019-04-28 18:00","취소","취소","연속",null,null,null,201902130542,"O"]
[300,"충북","충주","서운만승 T/L","154kV 서운-만승 등 2개T/L 전력선교체공사","154kV 서운-만승T/L No.81~83 전력선교체(중하단4선)","2019-04-24 08:00","2019-04-28 18:00","취소","취소","연속",null,null,null,201902130541,"O"]
[301,"충북","충주","증평괴산 T/L","154kV 음성-증평 등 2개T/L 전력선 교체공사","○ 154kV 음성-증평T/L No.62~65 전전접속개소해소 전력선교체 ○ 대상개소 : 음성-증평측 하단 2선, 증평-괴산측 하단 2선","2019-04-17 08:00","2019-04-19 18:00","취소","취소","연속",null,null,null,201902130572]
[302,"충북","충주","음성증평 T/L","154kV 음성-증평 등 2개T/L 전력선 교체공사","○ 154kV 음성-증평T/L No.62~65 전전접속개소해소 전력선교체 ○ 대상개소 : 음성-증평측 하단 2선, 증평-괴산측 하단 2선","2019-04-14 08:00","2019-04-16 18:00","취소","취소","연속",null,null,null,201902130570]
[303,"충북","충주","충주S/S 충주-풍동T/L GIS","2019년 상반기 충주전력지사 170kV GIS 정밀점검","충주S/S 충주-풍동T/L GIS 정밀점검","2019-04-23 17:30","2019-04-25 18:00","취소","취소","연속",null,null,null,201902110168,"O"]
[304,"충북","충주","충주S/S 154kV #60-61 BUS SEC GIS","2019년 상반기 충주전력지사 170kV GIS 정밀점검","충주S/S #60-61 SEC GIS 정밀점검","2019-04-22 09:00","2019-04-23 18:00","취소","취소","연속",null,null,null,201902110180]
[305,"충북","충주","풍동음성#2 T/L","154kV 음성-증평 등 2개T/L 전력선 교체공사","○ 154kV 풍동-음성T/L No.21~22 전전접속개소해소 전력선교체 ○ 대상개소 : #2측 하단내측 전선 1가닥","2019-04-12 08:00","2019-04-13 18:00","취소","취소","연속",null,null,null,201902130579]
[306,"충북","직할","왕암가남#2T/L","왕암S/S 154kV SW 증설공사","증설 GIS 무부하 가압 전원 GIS 170kV 50kA 1250A x 1CCT 설치","2019-04-09 10:00","2019-04-10 10:00","2019-04-09 10:00","2019-04-10 10:00","연속"]
[307,"충북","직할","왕암가남#2T/L","왕암S/S 154kV SW 증설공사","154kV 봉양전철#2T/L 최초 가압(상업운전) GIS 170kV 50kA 1250A x 1CCT","2019-04-22 14:00","2019-04-22 18:00","취소","취소","당일"]
[308,"대전충남","세종","덕진송강#2 T/L","154kV 세종-송강, 덕진-대화연결 지중T/L 건설공사","○ 덕진-송강T/L 계통변경 ○ 세종-송강, 덕진-대화 연결T/L 신규 선로구성 - 케이블 포설 및 접속 - 기설 OF케이블 철거","2019-04-15 08:00","2019-04-26 18:00","취소","취소","연속",null,null,null,201902080150]
[309,"대전충남","세종","덕진송강#1 T/L","154kV 세종-송강, 덕진-대화연결 지중T/L 건설공사","○ 덕진-송강T/L 계통변경 ○ 세종-송강, 덕진-대화 연결T/L 신규 선로구성 - 케이블 포설 및 접속 - 기설 OF케이블 철거","2019-04-01 08:00","2019-04-12 18:00","취소","취소","연속",null,null,null,201902080148]
[310,"대전충남","세종","월산서세종 T/L","[송전]154kV 월산-서세종T/L 정밀점검","[송전] 43~57 월산-서세종T/L 정밀점검 시행","2019-04-09 08:00","2019-04-10 18:00","2019-04-09 08:00","2019-04-10 18:00","매일",null,null,null,201902110711]
[311,"대전충남","세종","천안전의#1 T/L","154kV천안-전의T/L지장송전선로 이설공사","철탑설치 : 3기(No.6,12,13) 철탑철거 : 3기(No.6,12,13)","2019-04-01 08:00","2019-04-03 18:00","취소","취소","연속",null,null,null,201902120040]
[312,"대전충남","세종","천안전의#2 T/L","154kV천안-전의T/L지장송전선로 이설공사","철탑설치 : 3기(No.6,12,13) 철탑철거 : 3기(No.6,12,13)","2019-04-04 08:00","2019-04-06 18:00","취소","취소","연속",null,null,null,201902120052]
[313,"대전충남","세종","천안전의#1 T/L","154kV천안-전의T/L지장송전선로 이설공사","철탑설치 : 3기(No.6,12,13) 철탑철거 : 3기(No.6,12,13)","2019-04-07 08:00","2019-04-10 18:00","취소","취소","연속",null,null,null,201902120045]
[314,"대전충남","세종","천안전의#2 T/L","154kV천안-전의T/L지장송전선로 이설공사","철탑설치 : 3기(No.6,12,13) 철탑철거 : 3기(No.6,12,13)","2019-04-11 08:00","2019-04-26 18:00","취소","취소","연속",null,null,null,201902120054]
[315,"대전충남","세종","천안전의#1 T/L","154kV천안-전의T/L지장송전선로 이설공사","철탑설치 : 3기(No.6,12,13) 철탑철거 : 3기(No.6,12,13)","2019-04-27 08:00","2019-04-30 18:00","취소","취소","연속",null,null,null,201902120049]
[316,"대전충남","세종","조치원월산 T/L","[송전]154kV 조치원-월산T/L 안전이격확보공사","[송전]154kV 조치원-월산T/L 안전이격확보공사 -철탑3기 교체 : 16,17,19 -철탑3기 보강 : 13,14,18","2019-04-02 07:00","2019-04-08 18:00","2019-03-29 07:00","2019-04-08 18:00","연속",null,null,null,201902190167]
[317,"대전충남","아산","장재불당#1 T/L","19년 154KV GIS 정밀점검 공사","1.장재-불당#1TL GIS 정밀점검 - 보조계전기 교체 - AIR RING 밸브교체, DS오링교체","2019-04-09 09:00","2019-04-12 18:00","2019-04-09 09:00","2019-04-12 18:00","연속",null,null,null,201901230039]
[318,"대전충남","아산","장재불당#2 T/L","19년 154KV GIS 정밀점검 공사","1.장재-불당#2TL GIS 정밀점검 - 보조계전기 교체 - AIR RING 밸브교체, DS오링교체","2019-04-16 09:00","2019-04-19 18:00","2019-04-16 09:00","2019-04-19 18:00","연속",null,null,null,201901230040]
[319,"대전충남","아산","신온양한샘#1 T/L","신온양S/S 154kV 신온양-한샘#1T/L GIS 하자점검","○신온양S/S 154kV 신온양-한샘#1T/L GIS 하자점검","2019-04-01 09:00","2019-04-01 18:00","2019-04-01 09:00","2019-04-01 18:00","당일",null,null,null,201902120096]
[320,"대전충남","아산","신온양한샘#2 T/L","신온양S/S 154kV 신온양-한샘#2T/L GIS 하자점검","○신온양S/S 154kV 신온양-한샘#2T/L GIS 하자점검","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902120097]
[321,"대전충남","아산","신온양석곡#1 T/L","석곡S/S 154kV 신온양-석곡#1T/L GIS 하자점검","○석곡S/S 154kV 신온양-석곡#1T/L GIS 하자점검","2019-04-22 09:00","2019-04-22 18:00","2019-04-22 09:00","2019-04-22 18:00","당일",null,null,null,201902120108]
[322,"대전충남","아산","신온양석곡#2 T/L","석곡S/S 154kV 신온양-석곡#2T/L GIS 하자점검","○석곡S/S 154kV 신온양-석곡#2T/L GIS 하자점검","2019-04-23 09:00","2019-04-23 18:00","2019-04-23 09:00","2019-04-23 18:00","당일",null,null,null,201902120109]
[323,"대전충남","아산","아산합덕#2 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-04-18 07:00","2019-04-27 18:00","취소","취소","연속",null,null,null,201902130256]
[324,"대전충남","아산","아산인주#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","154kV 아산-인주#2T/L 피뢰기설치 (11기, 33set)","2019-04-20 07:00","2019-04-21 18:00","2019-04-20 07:00","2019-04-21 18:00","매일",null,null,null,201902120296]
[325,"대전충남","아산","아산합덕#1 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-04-08 07:00","2019-04-17 18:00","취소","취소","연속",null,null,null,201902130252]
[326,"대전충남","아산","아산인주#1 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","154kV 아산-인주#1T/L 피뢰기설치 (35기, 105set)","2019-04-13 07:00","2019-04-14 18:00","2019-04-13 07:00","2019-04-14 18:00","매일",null,null,null,201902120291]
[327,"대전충남","아산","온양풍세#1 T/L","19년 아산관내 154kv GIS 정밀점검 공사","1. 차단기 637 정밀점검 2. 보조계전기 교체,AIR-RING 밸브 교체 3. 기타작업","2019-04-06 06:00","2019-04-07 18:00","2019-04-06 06:00","2019-04-07 18:00","연속",null,null,null,201901230042]
[328,"대전충남","아산","아산온양#1 T/L","[송전] 154kV 아산-온양 등 2개T/L 이도조정공사","ㅇ이도조정 - 154kV 아산-온양T/L No.55~56 (상단) - 154kV 온양-풍세T/L No.1~2 (하단)","2019-04-06 07:00","2019-04-06 18:00","2019-04-06 07:00","2019-04-06 18:00","당일",null,null,null,201902080180]
[329,"대전충남","아산","풍세장재#2 T/L","풍세S/S 154kV 풍세-장재#2T/L GIS 보통점검","○풍세S/S 154kV 풍세-장재#2T/L GIS 보통점검","2019-04-30 09:00","2019-04-30 18:00","2019-04-30 09:00","2019-04-30 18:00","당일",null,null,null,201902070301]
[330,"대전충남","아산","풍세장재#1 T/L","풍세S/S 154kV 풍세-장재#1T/L GIS 보통점검","○풍세S/S 154kV 풍세-장재#1T/L GIS 보통점검","2019-04-29 09:00","2019-04-29 18:00","2019-04-29 09:00","2019-04-29 18:00","당일",null,null,null,201902070300]
[331,"대전충남","청양","관창대천#1 T/L","154kV 관창-대천T/L 39호 철탑 철거","관창-대천T/L 39호 철탑철거","2019-04-14 08:00","2019-04-14 18:00","2019-04-14 08:00","2019-04-14 18:00","당일",null,null,null,201902210039]
[332,"대전충남","청양","관창대천#2 T/L","154kV 관창-대천T/L 39호 철탑 철거","관창-대천T/L 39호 철탑철거","2019-04-14 08:00","2019-04-14 18:00","2019-04-14 08:00","2019-04-14 18:00","당일",null,null,null,201902210040]
[333,"대전충남","청양","관창보령복합 T/L","전선부식진단","대상개소 : 1~8, 11~15호 전선부식진단","2019-04-22 07:00","2019-04-23 18:00","2019-04-22 07:00","2019-04-23 18:00","매일",null,null,null,201902080430]
[334,"대전충남","청양","관창보령화력 T/L","전선부식진단","대상개소 : 1~8, 11~15호 전선부식진단","2019-04-24 07:00","2019-04-25 18:00","2019-04-24 07:00","2019-04-25 18:00","매일",null,null,null,201902080432]
[335,"전북","군산","군공소룡#1 T/L","YPP 송전선로 보호배전반 성능개선","YPP 송전선로 보호배전반 로직 변경","2019-04-22 10:00","2019-04-22 15:00","2019-04-22 10:00","2019-04-22 15:00","당일",null,null,null,201901310009]
[336,"전북","군산","군공소룡#2 T/L","YPP 송전선로 보호배전반 성능개선","YPP 송전선로 보호배전반 로직 변경","2019-04-22 15:00","2019-04-22 18:00","2019-04-22 15:00","2019-04-22 18:00","당일",null,null,null,201901310011]
[337,"전북","군산","군산복합S/Y S/T T/L CB","군산P/O 차단기 점검공사","1. 6133 차단기 조작시험","2019-04-03 09:00","2019-04-03 18:00","2019-04-03 09:00","2019-04-03 18:00","당일",null,null,null,201902210069]
[338,"전북","군산","군공군산CC#1 T/L","군산P/O 154kV 차단기 조작시험","1. 군공-군산복합#1T/L 차단기 조작시험(군공, 군산복합)","2019-04-03 09:00","2019-04-03 13:00","2019-04-03 09:00","2019-04-03 13:00","당일",null,null,null,201902210070]
[339,"전북","군산","군공군산CC#2 T/L","군산P/O 154kV 차단기 조작시험","1. 군공-군산복합#2T/L 차단기 조작시험(군공, 군산복합)","2019-04-03 13:00","2019-04-03 18:00","2019-04-03 13:00","2019-04-03 18:00","당일",null,null,null,201902210071]
[340,"전북","군산","군산복합S/Y G/T #1T/L CB","군산P/O 154kV 차단기 조작시험","1. 6233 차단기 조작시험","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902210067]
[341,"전북","군산","군산복합S/Y G/T #2T/L CB","군산P/O 154kV 차단기 조작시험","1. 6333 차단기 조작시험","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902210068]
[342,"전북","군산","군산복합S/Y 154kV #1 BUS TIE CB","군산P/O 154kV 차단기 조작시험","1. 6100 차단기 조작시험","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902210065]
[343,"전북","군산","군산서군산#2 T/L","154㎸ 군산서군산T/L 안전이격거리확보공사","-철탑신설 : 2기(25, 26호) -철탑철거 : 2기(25, 26호)","2019-04-25 07:00","2019-04-27 18:00","취소","취소","당일",null,null,null,201902110065]
[344,"전북","군산","군산서군산#1 T/L","154㎸ 군산서군산T/L 안전이격거리확보공사","-철탑신설 : 2기(25, 26호) -철탑철거 : 2기(25, 26호)","2019-04-21 07:00","2019-04-22 18:00","2019-04-21 07:00","2019-04-22 18:00","당일",null,null,null,201902200064]
[345,"전북","군산","군산서군산#1 T/L","154㎸ 군산서군산T/L 안전이격거리확보공사","-철탑신설 : 2기(25, 26호) -철탑철거 : 2기(25, 26호)","2019-04-25 07:00","2019-04-27 18:00","취소","취소","당일",null,null,null,201902110064]
[346,"전북","군산","군산이리#2 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 이리 : 6A7 차단기 하자점검 2. 군산 : CVT보통점검 3. 군산 :657 차단기 조작시험","2019-04-09 09:30","2019-04-09 18:00","2019-04-09 09:30","2019-04-09 18:00","당일",null,null,null,201902110582]
[347,"전북","군산","군산이리#1 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 이리 : 697 차단기 하자점검 2. 군산 : CVT보통점검 3. 군산 :647 차단기 조작시험","2019-04-25 09:30","2019-04-25 18:00","2019-04-25 09:30","2019-04-25 18:00","당일",null,null,null,201902110577]
[348,"전북","군산","군산서군산#2 T/L","154㎸ 군산서군산T/L 안전이격거리확보공사","-철탑신설 : 2기(25, 26호) -철탑철거 : 2기(25, 26호)","2019-04-23 07:00","2019-04-24 18:00","2019-04-23 07:00","2019-04-24 18:00","당일",null,null,null,201902200065]
[349,"전북","군산","새만금군장#1 T/L","154kV 비응분기 지중T/L 건설공사","○ 구간 : 기설 새만금-군장 2∏ 분기 ~ 비응S/S ○ 선종/회선길이 : 154kV XLPE 1200㎟, 4회선-1km ○ 포설 및 접속 : 포설8구간, 중간접속8개소, 종단접속4개소","2019-04-08 10:00","2019-05-07 18:00","2019-04-08 10:00","2019-05-07 18:00","연속",null,null,null,201902210248]
[350,"전북","군산","동군산군산CC#1 T/L","군산P/O 차단기 점검공사","1. 동군산 : 697 하자점검 2. 군산복합 : 627 차단기 조작시험","2019-04-08 09:00","2019-04-08 13:00","2019-04-08 09:00","2019-04-08 13:00","당일",null,null,null,201902210004]
[351,"전북","군산","동군산군산CC#2 T/L","군산P/O 차단기 점검공사","1. 동군산 : 687 하자점검 2. 군산복합 : 617 차단기 조작시험","2019-04-08 13:00","2019-04-08 18:00","2019-04-08 13:00","2019-04-08 18:00","당일",null,null,null,201902210006]
[352,"전북","군산","이리백산#1 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 이리 : 657 차단기 하자점검","2019-04-12 09:30","2019-04-12 13:00","2019-04-12 09:30","2019-04-12 13:00","당일",null,null,null,201902120305]
[353,"전북","군산","이리백산#2 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 이리 : 667 차단기 하자점검","2019-04-12 13:00","2019-04-12 18:00","2019-04-12 13:00","2019-04-12 18:00","당일",null,null,null,201902120306]
[354,"전북","군산","이리전주#2 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 이리 : 647 차단기 하자점검","2019-04-10 13:00","2019-04-10 18:00","2019-04-10 13:00","2019-04-10 18:00","당일",null,null,null,201902120302]
[355,"전북","군산","이리전주#1 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 이리 : 637 차단기 하자점검","2019-04-10 09:30","2019-04-10 13:00","2019-04-10 09:30","2019-04-10 13:00","당일",null,null,null,201902120301]
[356,"전북","군산","영등팔봉#1 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 팔봉 - 657 차단기 하자점검 - LA 3대 초기점검 2. 영등 : 637 차단기 조작시험","2019-04-26 09:30","2019-04-26 18:00","2019-04-27 09:30","2019-04-27 18:00","당일",null,null,null,201902120308]
[357,"전북","군산","영등팔봉#2 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 팔봉 : 687 차단기 하자점검 2. 영등 : 647 차단기 조작시험","2019-04-16 09:00","2019-04-16 13:00","2019-04-20 09:00","2019-04-20 13:00","당일",null,null,null,201902120310]
[358,"전북","김제","담양김제 T/L","YPP 송전선로 보호배전반 성능개선","YPP 송전선로 보호배전반 로직변경","2019-04-24 10:00","2019-04-24 18:00","2019-04-24 10:00","2019-04-24 18:00","당일",null,null,null,201901310032]
[359,"전북","김제","신김제남전주#2 T/L","남전주S/S #4M.Tr 1차 GIS 교체공사","남전주S/S #4M.Tr 1차 GIS 교체공사","2019-04-08 09:00","2019-04-19 18:00","2019-04-08 09:00","2019-04-19 18:00","매일",null,null,null,201901180086]
[360,"전북","김제","정공S/S 154kV #1 BUS TIE GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2019-04-26 09:00","2019-04-26 18:00","2019-04-26 09:00","2019-04-26 18:00","당일",null,null,null,201902180228]
[361,"전북","김제","신김제정공#1 T/L","154kV 신김제-동전주#1T/L 피뢰기 설치공사 병가구간 휴전","154kV 신김제-동전주#1T/L 피뢰기 설치공사 병가구간 휴전","2019-04-20 07:00","2019-04-21 18:00","2019-04-20 07:00","2019-04-21 18:00","매일",null,null,null,201902110154]
[362,"전북","김제","정공칠보HP T/L","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2019-04-30 09:00","2019-04-30 18:00","2019-04-30 09:00","2019-04-30 18:00","당일",null,null,null,201902180233]
[363,"전북","김제","정공담양 T/L","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2019-04-29 09:00","2019-04-29 18:00","2019-04-29 09:00","2019-04-29 18:00","당일",null,null,null,201902180229]
[364,"전북","김제","정주고창#2 T/L","정주S/S 170kV GIS 설치공사","정주S/S 정주-고창#2T/L 차단기 이설 고창S/S 송전선로 보호배전반 교체","2019-04-18 09:00","2019-04-26 18:00","2019-04-18 09:00","2019-04-26 18:00","연속",null,null,null,201811150199]
[365,"전북","김제","정공정주#2 T/L","정주S/S 170kV GIS 설치공사","정주S/S 정공-정주#2T/L 차단기 이설 정공S/S 송전선로 보호배전반 교체","2019-04-10 09:00","2019-04-17 18:00","2019-04-10 09:00","2019-04-17 18:00","연속",null,null,null,201811150195]
[366,"전북","김제","정공정주#1 T/L","정주S/S 170kV GIS 설치공사","정주S/S 정공-정주#1T/L 차단기 이설 정공S/S 송전선로 보호배전반 교체","2019-04-03 09:00","2019-04-09 18:00","2019-04-03 09:00","2019-04-09 18:00","연속",null,null,null,201811150193]
[367,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주#2T/L 항공장애표시구 설치공사","○ 항공장애표시구 설치 - 작업구간 : No.1~83","2019-04-27 07:00","2019-04-27 18:00","2019-04-27 07:00","2019-04-27 18:00","매일",null,null,null,201902110150]
[368,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주#1T/L 피뢰기 설치공사","○ 피뢰기 설치(83기) - 작업구간 : No.1~83","2019-04-15 07:00","2019-04-26 18:00","2019-04-15 07:00","2019-04-26 18:00","매일",null,null,null,201902110144]
[369,"전북","직할","무주진안 T/L","[송전] 154kV 금산-무주T/L 애자련 보강공사","[송전] 154kV 금산-무주#1T/L 애자련 보강시 4회선구간 안전 확보 (금산-무주T/L No.61,66)","2019-04-22 08:00","2019-04-22 18:00","2019-04-22 08:00","2019-04-22 18:00","당일",null,null,null,201902120505]
[370,"전북","직할","무주용담수력 T/L","2019년 전북직할 170kV 차단기 정밀점검공사","- 차단기 정밀점검","2019-04-23 08:00","2019-04-25 18:00","취소","취소","연속",null,null,null,201902150120]
[371,"전북","직할","북전주봉동#1 T/L","2019년 전북직할 170kV 차단기 정밀점검공사","- 차단기 정밀점검","2019-04-29 07:00","2019-04-30 18:00","2019-04-29 07:00","2019-04-30 18:00","연속",null,null,null,201902150123]
[372,"전북","직할","북전주용담수력 T/L","154kV 동전주-북전주#2T/L 정밀점검","송전선로 정밀점검","2019-04-26 07:00","2019-04-27 18:00","2019-04-26 07:00","2019-04-27 18:00","매일",null,null,null,201901180057]
[373,"광주전남","강진","강진남창#1 T/L","2019년도 차단기 및 개폐장치 조작시험","-차단기 현장조작 및 원방조작 -계전기 Trip 시험 및 개폐타임 측정","2019-04-12 09:00","2019-04-12 18:00","2019-04-12 09:00","2019-04-12 18:00","당일",null,null,null,201902080409]
[374,"광주전남","강진","해남해남CS#2 T/L","해남S/S 154kV 해남-해남C/S#2T/L PT 보통점검","- 해남S/S 154kV 해남-해남C/S#2T/L PT 보통점검 - 해남S/S,해남C/S 154kV 해남-해남C/S#2T/L 조작시험","2019-04-02 09:00","2019-04-02 18:00","2019-04-02 09:00","2019-04-02 18:00","당일",null,null,null,201902110187]
[375,"광주전남","강진","해남해남CS#1 T/L","해남S/S 154kV 해남-해남C/S#1T/L PT 보통점검","- 해남S/S 154kV 해남-해남C/S#1T/L PT 보통점검 - 해남S/S,해남C/S 154kV 해남-해남C/S#1T/L 조작시험","2019-04-01 09:00","2019-04-01 18:00","2019-04-01 09:00","2019-04-01 18:00","당일",null,null,null,201902110183]
[376,"광주전남","강진","남창해남CS#1 T/L","2019년도 차단기 및 개폐장치 조작시험","-차단기 현장조작 및 원방조작 -계전기 Trip 시험 및 개폐타임 측정","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902080405]
[377,"광주전남","강진","남창해남CS#2 T/L","2019년도 차단기 및 개폐장치 조작시험","-차단기 현장조작 및 원방조작 -계전기 Trip 시험 및 개폐타임 측정","2019-04-09 09:00","2019-04-09 18:00","2019-04-09 09:00","2019-04-09 18:00","당일",null,null,null,201902080407]
[378,"광주전남","강진","화원진도#2 T/L","2019년도 차단기 및 개폐장치 조작시험","-차단기 현장조작 및 원방조작 -계전기 Trip 시험 및 개폐타임 측정","2019-04-15 09:00","2019-04-15 18:00","2019-04-15 09:00","2019-04-15 18:00","당일",null,null,null,201902080413]
[379,"광주전남","강진","화원진도#1 T/L","2019년도 차단기 및 개폐장치 조작시험","-차단기 현장조작 및 원방조작 -계전기 Trip 시험 및 개폐타임 측정","2019-04-16 09:00","2019-04-16 18:00","2019-04-16 09:00","2019-04-16 18:00","당일",null,null,null,201902080416]
[380,"광주전남","광주","계림S/S 154kV #60 BUS","19년 변전총액공사(#60BUS)","154kV PT 집합반 교체","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902080098]
[381,"광주전남","광주","계림S/S 154kV #61 BUS","19년 변전총액공사(#61BUS)","154kV PT 집합반 교체","2019-04-08 09:00","2019-04-08 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902080099]
[382,"광주전남","광주","계림S/S 154kV #65 BUS","19년 변전총액공사(#65BUS)","154kV PT 집합반 교체","2019-04-09 09:00","2019-04-09 18:00","2019-04-09 09:00","2019-04-09 18:00","당일",null,null,null,201902080100]
[383,"광주전남","광주","계림S/S 154kV #66 BUS","19년 변전총액공사(#66BUS)","154kV PT 집합반 교체","2019-04-09 09:00","2019-04-09 18:00","2019-04-09 09:00","2019-04-09 18:00","당일",null,null,null,201902080101]
[384,"광주전남","광주","신광주곡성#1 T/L","154kV 곡성E/C #4M.Tr 설치공사","154kV 곡성E/C #4M.Tr 설치에 따른 신광주곡성#1T/L로 #4M.Tr 초기 가압","2019-04-29 09:00","2019-04-30 09:00","2019-04-29 09:00","2019-04-30 09:00","연속",null,null,null,201902200004]
[385,"광주전남","광주","신광주계림#1 T/L","19년 광주변전총액공사","신광주S/S 신광주-계림#1T/L GIS 하자점검, CVT 하자점검 계림S/S 신광주-계림#1T/L GIS 장기미동작 차단기점검","2019-04-11 09:00","2019-04-11 18:00","2019-04-11 09:00","2019-04-11 18:00","당일",null,null,null,201902110745]
[386,"광주전남","광주","신광주장성#2 T/L","19년 광주변전총액공사","신광주-장성#2T/L GIS 하자점검, CVT 하자점검","2019-04-05 09:00","2019-04-05 18:00","2019-04-05 09:00","2019-04-05 18:00","당일",null,null,null,201902110743]
[387,"광주전남","광주","신광주장성#1 T/L","19년 광주변전총액공사","신광주-장성#1T/L GIS 하자점검, CVT 하자점검","2019-04-04 09:00","2019-04-04 18:00","2019-04-04 09:00","2019-04-04 18:00","당일",null,null,null,201902110742]
[388,"광주전남","광주","신광주곡성#2 T/L","19년 광주변전총액공사","신광주-곡성#2T/L GIS 하자점검, CVT 보통점검","2019-04-09 09:00","2019-04-09 18:00","2019-04-26 09:00","2019-04-26 18:00","당일",null,null,null,201902110741]
[389,"광주전남","광주","신광주계림#2 T/L","19년 광주변전총액공사","신광주S/S 신광주-계림#2T/L GIS 하자점검, CVT 보통점검, LA 대체","2019-04-12 09:00","2019-04-12 18:00","2019-04-10 09:00","2019-04-10 18:00","당일",null,null,null,201902110746]
[390,"광주전남","광주","신광주곡성#1 T/L","19년 광주변전총액공사","신광주-곡성#1T/L GIS 하자점검","2019-04-10 09:00","2019-04-10 18:00","2019-04-29 09:00","2019-04-29 18:00","당일",null,null,null,201902110740]
[391,"광주전남","목포","남악북항#2 T/L","송전정비 총액공사(상간스페이서 설치)","154kV 남악-북항T/L 갤러핑고장개소 상간스페이서 설치","2019-04-05 07:00","2019-04-16 18:00","2019-04-05 07:00","2019-04-16 18:00","매일",null,null,null,201902130593]
[392,"광주전남","목포","남악북항#1 T/L","송전정비 총액공사(상간스페이서 설치)","154kV 남악-북항T/L 갤러핑고장개소 상간스페이서 설치","2019-04-17 07:00","2019-04-28 18:00","2019-04-17 07:00","2019-04-28 18:00","매일",null,null,null,201902130601]
[393,"광주전남","순천","광양순천#2 T/L","19년 변전 정비회사 총액공사","* 광양S/S 광양-순천#2T/L LA초기, CB타임측정","2019-04-26 09:00","2019-04-26 18:00","2019-04-26 09:00","2019-04-26 18:00","당일",null,null,null,201902120118]
[394,"광주전남","순천","서순천주암HP T/L","19년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 서순천-주암HP T/L GIS 정밀점검","2019-04-04 09:00","2019-04-05 18:00","2019-04-04 09:00","2019-04-05 18:00","연속",null,null,null,201902070262]
[395,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌T/L 안전이격확보공사","공 사 개 요 가. 작업구간 : 154kV 순천-율촌T/L No.62~65호 나. 작업내용 ○ 154kV 순천-율촌T/L 철탑상향 : 1기 - 63호(17 → 30m) : 13m 상향 ※ 관형지지물 활용 선하지 내 철탑이설","2019-04-20 07:00","2019-04-21 18:00","2019-04-21 07:00","2019-04-23 18:00","연속",null,null,null,201902200088]
[396,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌T/L 안전이격확보공사","공 사 개 요 가. 작업구간 : 154kV 순천-율촌T/L No.62~65호 나. 작업내용 ○ 154kV 순천-율촌T/L 철탑상향 : 1기 - 63호(17 → 30m) : 13m 상향 ※ 관형지지물 활용 선하지 내 철탑이설","2019-04-20 07:00","2019-04-21 18:00","2019-04-21 07:00","2019-04-23 18:00","연속",null,null,null,201902200089]
[397,"광주전남","순천","순천승주#1 T/L","19년 변전 정비회사 총액공사","* 순천S/S 순천-승주#1T/L CB 타임측정 * 승주S/S 순천-승주#1T/L LA교체","2019-04-15 09:00","2019-04-15 18:00","2019-04-15 09:00","2019-04-15 18:00","당일",null,null,null,201902120102]
[398,"광주전남","순천","승주S/S 154kV #1 BUS","승주 #3M.Tr 증설 사업","승주 #3M.Tr 170kV GIS 설치 - #1BUS DS 설치","2019-04-02 09:00","2019-04-05 11:00","2019-04-02 09:00","2019-04-05 11:00","연속",null,null,null,201901150126]
[399,"광주전남","순천","승주S/S 154kV #2 BUS","승주 #3M.Tr 증설 사업","승주 #3M.Tr 170kV GIS 설치 - #2BUS DS 설치","2019-04-05 11:00","2019-04-09 18:00","2019-04-05 11:00","2019-04-09 18:00","연속",null,null,null,201901150127]
[400,"광주전남","순천","승주S/S 154kV #1 BUS","승주 #3M.Tr 증설 사업","승주 #3M.Tr 170kV GIS 설치 - #1BUS DS 설치","2019-04-02 09:00","2019-04-05 11:00","2019-04-02 09:00","2019-04-05 11:00","연속",null,null,null,201901150126]
[401,"광주전남","순천","승주S/S 154kV #2 BUS","승주 #3M.Tr 증설 사업","승주 #3M.Tr 170kV GIS 설치 - #2BUS DS 설치","2019-04-05 11:00","2019-04-09 18:00","2019-04-05 11:00","2019-04-09 18:00","연속",null,null,null,201901150127]
[402,"광주전남","순천","승주S/S 154kV #1 BUS","승주 #3M.Tr 증설 사업","승주 #3M.Tr 무부하 가압 - 화순승주#1T/L 및 #1BUS 통한 #3 무부하 가압","2019-04-29 14:00","2019-04-30 14:00","2019-04-29 14:00","2019-04-30 14:00","당일",null,null,null,201901150138]
[403,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 초기점검, 정밀점검","2019년 가공송전 순시점검 위탁공사 초기점검. 정밀점검 - No.22 ~ 24 (3기), No.37 ~ 승주S/T (60기)","2019-04-10 08:00","2019-04-13 18:00","2019-04-10 08:00","2019-04-13 18:00","매일",null,null,null,201902130389]
[404,"광주전남","순천","계림승주#2 T/L","19년 변전 정비회사 총액공사","* 승주S/S 계림-승주#2T/L LA교체","2019-04-11 09:00","2019-04-11 18:00","2019-04-11 09:00","2019-04-11 18:00","당일",null,null,null,201902120122]
[405,"광주전남","순천","여수TP화치#1 T/L","19년 순천전력지사 170kV GIS 정밀점검공사","여수화력S/Y 여수TP-화치#1 T/L GIS 정밀점검","2019-04-08 09:00","2019-04-09 18:00","취소","취소","연속",null,null,null,201902210083]
[406,"광주전남","순천","호남TP여수TP#1 T/L","‘18-19년도 순천전력지사 변전협력회사 총액공사","화남화력 CB타임측정, 여수화력 GIS 보통","2019-04-01 09:00","2019-04-01 18:00","2019-04-01 09:00","2019-04-01 18:00","당일",null,null,null,201901140168]
[407,"광주전남","순천","호남TP여수TP#2 T/L","‘18-19년도 순천전력지사 변전협력회사 총액공사","화남화력 CB타임측정, 여수화력 GIS 보통","2019-04-02 09:00","2019-04-02 18:00","2019-04-02 09:00","2019-04-02 18:00","당일",null,null,null,201901140170]
[408,"광주전남","순천","여수TP용성#2 T/L","19년 순천전력지사 170kV GIS 정밀점검공사","여수화력S/Y 여수TP-용성#2 T/L GIS 정밀점검","2019-04-11 09:00","2019-04-12 18:00","취소","취소","연속",null,null,null,201902070269]
[409,"광주전남","순천","여수TP화치#2 T/L","19년 순천전력지사 170kV GIS 정밀점검공사","여수화력S/Y 여수TP-화치#2 T/L GIS 정밀점검","2019-04-15 09:00","2019-04-16 18:00","취소","취소","연속",null,null,null,201902070268]
[410,"광주전남","순천","호남TP여수TP#2 T/L","‘18-19년도 순천전력지사 변전협력회사 총액공사","화남화력 CB타임측정, 여수화력 GIS 보통","2019-04-02 09:00","2019-04-02 18:00","취소","취소","당일",null,null,null,201901140170]
[411,"광주전남","순천","호남TP여수TP#1 T/L","‘18-19년도 순천전력지사 변전협력회사 총액공사","화남화력 CB타임측정, 여수화력 GIS 보통","2019-04-01 09:00","2019-04-01 18:00","취소","취소","당일",null,null,null,201901140168]
[412,"광주전남","순천","여천여수#1 T/L","19년 변전 정비회사 총액공사","* 여천S/S 여천-여수#1T/L GIS 보통 * 여수S/S 여천-여수#1T/L CB 타임측정","2019-04-16 09:00","2019-04-16 18:00","2019-04-16 09:00","2019-04-16 18:00","당일",null,null,null,201902120078]
[413,"광주전남","순천","율촌여수산단#1 T/L","19년 변전 정비회사 총액공사","* 율촌S/S 율촌-여수산단#1T/L GIS 보통점검 * 여수산단 율촌-여수산단#1T/L GIS 보통점검","2019-04-17 09:00","2019-04-17 18:00","2019-04-17 09:00","2019-04-17 18:00","당일",null,null,null,201902120106]
[414,"광주전남","순천","율촌여수산단#2 T/L","19년 변전 정비회사 총액공사","* 율촌S/S 율촌-여수산단#2T/L GIS 보통점검 * 여수산단 율촌-여수산단#2T/L GIS 보통점검","2019-04-18 09:00","2019-04-18 18:00","2019-04-18 09:00","2019-04-18 18:00","당일",null,null,null,201902120111]
[415,"광주전남","순천","율촌화치#1 T/L","19년 변전 정비회사 총액공사","* 율촌S/S 율촌-화치#1T/L CB타임측정 * 화치S/S 율촌-화치#1T/L GIS 보통점검","2019-04-23 09:00","2019-04-23 18:00","2019-04-23 09:00","2019-04-23 18:00","당일",null,null,null,201902120115]
[416,"광주전남","순천","율촌화치#2 T/L","19년 변전 정비회사 총액공사","* 율촌S/S 율촌-화치#2T/L CB타임측정 * 화치S/S 율촌-화치#2T/L GIS 보통점검","2019-04-24 09:00","2019-04-24 18:00","2019-04-24 09:00","2019-04-24 18:00","당일",null,null,null,201902120116]
[417,"광주전남","순천","율촌민자#1 T/L","154kV 율촌-민자#1T/L 정밀점검","2019년 가공송전 순시점검 위탁공사 정밀점검 - No.1 ~ 9 (9기)","2019-04-25 08:00","2019-04-25 18:00","2019-04-25 08:00","2019-04-25 18:00","당일",null,null,null,201902120518]
[418,"광주전남","순천","율촌민자#2 T/L","154kV 율촌-민자#2T/L 정밀점검","2019년 가공송전 순시점검 위탁공사 정밀점검 - No.1 ~ 9 (9기)","2019-04-29 08:00","2019-04-29 18:00","2019-04-29 08:00","2019-04-29 18:00","당일",null,null,null,201902120521]
[419,"광주전남","순천","여천호남TP#1 T/L","154kV 여천-호남T/P #1T/L 자기애관 교체공사","○ 154kV 여천-호남T/P #1T/L 자기애관을 폴리머애관으로 교체(3대)","2019-04-04 07:00","2019-04-05 18:00","2019-04-04 07:00","2019-04-05 18:00","연속",null,null,null,201901040088]
[420,"광주전남","직할","나주금천#2 T/L","154kV 금천S/S #3M.Tr 증설공사","○154kV #1BUS 무부하 시험가압용(24시간 이상) ----------------------- ○154/23kV M.Tr 1BANK 설치 ○170kV GIS 1CCT 설치 ○25.8kV SIS 4CCT 설치 ○ 기타 부대공사 1식","2019-04-25 14:00","2019-04-26 14:00","2019-04-25 14:00","2019-04-26 14:00","연속",null,null,null,201902080162]
[421,"광주전남","직할","나주금천#1 T/L","154kV 나주S/S 옥내화 인출지중화 공사","변전 : 보호반대체, 통신, 계통시험 송전 : 송전선로 가선 및 LA 설치, EBA 선로접속 통신 : OPGW 설치 및 시험","2019-04-12 06:00","2019-04-13 18:00","2019-04-12 06:00","2019-04-13 18:00","연속",null,null,null,201902210100]
[422,"광주전남","직할","신화순나주#2 T/L","154kV 나주S/S 옥내화 인출지중화 공사","안전이격","2019-04-27 06:00","2019-04-27 18:00","2019-04-27 06:00","2019-04-27 18:00","당일",null,null,null,201902210103]
[423,"광주전남","직할","나주엄다#2 T/L","154kV 나주S/S 옥내화 인출지중화 공사","변전 : 보호반대체, 통신, 계통시험 송전 : 송전선로 가선 및 LA 설치, EBA 선로접속","2019-04-26 06:00","2019-05-02 18:00","2019-04-26 06:00","2019-05-02 18:00","연속",null,null,null,201902210102]
[424,"광주전남","직할","나주금천#2 T/L","154kV 나주S/S 옥내화 인출지중화 공사","변전 : 보호반대체, 통신, 계통시험 송전 : 송전선로 가선 및 LA 설치, EBA 선로접속","2019-04-12 06:00","2019-04-19 18:00","2019-04-12 06:00","2019-04-19 18:00","연속",null,null,null,201902210101]
[425,"대구","경산","하양반야월#1 T/L","일진제 PMJ 중간접속함 교체공사","일진제 PMJ 중간접속함 교체공사","2019-04-22 09:00","2019-05-05 18:00","2019-04-22 09:00","2019-05-05 18:00","연속",null,null,null,201902140056]
[426,"대구","경산","청도밀양#2 T/L","가공송전선로 순시점검 위탁공사","154kV 청도-밀양#2T/L 정밀점검","2019-04-08 08:00","2019-04-10 18:00","2019-04-08 08:00","2019-04-10 18:00","연속",null,null,null,201902080077]
[427,"대구","경산","청도밀양#1 T/L","가공송전선로 순시점검 위탁공사","154kV 청도-밀양#1T/L 정밀점검","2019-04-03 08:00","2019-04-05 18:00","2019-04-02 08:00","2019-04-04 18:00","연속",null,null,null,201902080063]
[428,"대구","경산","대구청도#1 T/L","가공송전선로 순시점검 위탁공사","154kV 청도-밀양#2T/L 정밀점검 안전확보","2019-04-08 08:00","2019-04-10 18:00","2019-04-08 08:00","2019-04-10 18:00","매일",null,null,null,201902080078]
[429,"대구","경산","대구청도#2 T/L","가공송전선로 순시점검 위탁공사","154kV 청도-밀양#1T/L 정밀점검 안전확보","2019-04-03 08:00","2019-04-05 18:00","2019-04-02 08:00","2019-04-04 18:00","매일",null,null,null,201902080073]
[430,"대구","달성","다산강창#1 T/L","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사","2019-04-01 09:00","2019-04-02 18:00","2019-04-01 09:00","2019-04-02 18:00","연속",null,null,null,201902090048]
[431,"대구","달성","다산강창#2 T/L","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사","2019-04-03 09:00","2019-04-04 18:00","2019-04-03 09:00","2019-04-04 18:00","연속",null,null,null,201902090049]
[432,"대구","달성","고령다산#2 T/L","달성전력지사 변전총액공사","LA대체,CVT보통","2019-04-09 09:00","2019-04-09 18:00","2019-04-08 09:00","2019-04-08 18:00","당일",null,null,null,201902090071]
[433,"대구","달성","고령S/S 154kV #65 BUS","345kV 고령S/S #1M.Tr 증설공사","-154kV #65BUS 무부하 가압","2019-04-22 09:00","2019-04-23 18:00","2019-04-22 09:00","2019-04-23 18:00","연속",null,null,null,201902200105]
[434,"대구","달성","고령논공#1 T/L","달성전력지사 변전총액공사","CVT하자, LA초기","2019-04-08 09:00","2019-04-08 18:00","2019-04-07 09:00","2019-04-07 18:00","당일",null,null,null,201902090070]
[435,"대구","달성","대구봉덕#1 T/L","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사(TEST선로)","2019-04-13 13:00","2019-04-15 18:00","2019-04-12 13:00","2019-04-13 18:00","매일",null,null,null,201902090057]
[436,"대구","달성","대구청도#1 T/L","피뢰기설치","No.1-5","2019-04-01 07:30","2019-04-01 18:00","취소","취소","당일",null,null,null,201902200142]
[437,"대구","달성","내당두류#2 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사(보통점검)","2019-04-19 09:00","2019-04-19 18:00","취소","취소","당일",null,null,null,201902090097]
[438,"대구","달성","내당두류#1 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사(보통점검)","2019-04-18 09:00","2019-04-18 18:00","취소","취소","당일",null,null,null,201902090096]
[439,"대구","달성","상인봉덕#2 T/L","상인봉덕#2T/L 43PDA불량분 교체작업","상인봉덕#2T/L 43PDA불량분 교체작업","2019-04-15 09:00","2019-04-15 18:00","2019-04-15 09:00","2019-04-15 18:00","당일",null,null,null,201902190033]
[440,"대구","직할","범물남대구#1 T/L","남대구S/S 차단기 개폐타임 측정","남대구S/S 차단기 개폐타임 측정","2019-04-25 09:30","2019-04-25 13:00","취소","취소","당일",null,null,null,201902120208]
[441,"대구","직할","범물남대구#2 T/L","남대구S/S 차단기 개폐타임 측정","남대구S/S 차단기 개폐타임 측정","2019-04-25 13:00","2019-04-25 16:00","취소","취소","당일",null,null,null,201902120210]
[442,"대구","칠곡","남구미광평#1 T/L","(TEST 선로)광평S/S 154kV BUS-TIE GIS 정밀점검","(TEST 선로)광평S/S 154kV BUS-TIE GIS 정밀점검","2019-04-02 09:00","2019-04-03 18:00","2019-04-02 09:00","2019-04-03 18:00","매일",null,null,null,201902070366]
[443,"경북","구미","청리상주#1 T/L","2019년도 구미전력지사 변전정비업체 총액공사","YPP제 보호계전기 성능개선 LA 대체공사 GIS보통점검","2019-04-26 09:00","2019-04-26 14:00","2019-04-26 09:00","2019-04-26 14:00","당일",null,null,null,201902110763]
[444,"경북","구미","청리상주#2 T/L","2019년도 구미전력지사 변전정비업체 총액공사","YPP제 보호계전기 성능개선 LA 대체공사 GIS보통점검","2019-04-26 14:00","2019-04-26 18:00","2019-04-26 14:00","2019-04-26 18:00","당일",null,null,null,201902110764]
[445,"경북","구미","선산안계#1 T/L","154kV 해평분기 지중T/L 건설공사","O 구 간 : 154kV 해평E/C ~ 분기맨홀(선산-안계T/L 2파이 분기)&ltbr&gtO 선 종 : 154kV XLPE 2000㎟ 4회선- 0.1㎞","2019-04-10 09:00","2019-04-25 18:00","2019-04-10 09:00","2019-04-25 18:00","연속",null,null,null,201901170124]
[446,"경북","영주","영주(SA)봉화#1 T/L","'19년 영주전력 가공송전위탁공사 송전선로 정밀점검(영주-봉화)","154kV 영주봉화#1T/L No.1~81 송전선로 정밀점검","2019-04-29 09:00","2019-05-03 18:00","2019-04-29 09:00","2019-05-03 18:00","연속",null,null,null,201902110243]
[447,"경북","영주","점촌문경 T/L","154kV 점촌S/S #4M.Tr 증설공사 (안전이격거리 확보)","154kV 점촌S/S #4M.Tr 증설공사 - 6433GIS 증설관련 안전이격거리확보 (즉시가압조건)","2019-04-25 09:00","2019-04-27 18:00","2019-04-26 09:00","2019-04-27 18:00","매일",null,null,null,201902140125]
[448,"경북","직할","안동동안동#1 T/L","18~19년 경북직할 변전정비회사 총액공사","동안동S/S 611, 612, 617 Air 누기개소 점검 및 GIS 개폐타임 측정","2019-04-23 08:00","2019-04-23 18:00","2019-04-10 08:00","2019-04-10 18:00","당일",null,null,null,201902080036]
[449,"경북","직할","안동동안동#2 T/L","18~19년 경북직할 변전정비회사 총액공사","동안동S/S 656, 659-3ES Air 누기개소 점검 및 GIS 개폐타임 측정","2019-04-24 08:00","2019-04-24 18:00","2019-04-11 08:00","2019-04-11 18:00","당일",null,null,null,201902080037]
[450,"경북","직할","안동복합풍산#2 T/L","18~19년 경북직할 변전정비회사 총액공사","안동복합S/S 및 풍산S/S 풍산-안동CC#2T/L GIS 초기점검","2019-04-11 09:00","2019-04-12 18:00","취소","취소","매일",null,null,null,201902080116]
[451,"경북","직할","안동복합풍산#1 T/L","18~19년 경북직할 변전정비회사 총액공사","안동복합S/S 및 풍산S/S 풍산-안동CC#1T/L GIS 초기점검","2019-04-09 09:00","2019-04-10 18:00","취소","취소","매일",null,null,null,201902080114]
[452,"경북","직할","봉화울진 T/L","154kV 봉화-울진T/L 정밀점검","154kV 봉화-울진T/L 정밀점검(No.1~53)","2019-04-02 07:00","2019-04-06 18:00","2019-04-02 07:00","2019-04-06 18:00","연속",null,null,null,201902110636]
[453,"경북","직할","안동풍산 T/L","154kV 안동-풍산T/L 용량증대 전선교체공사","- 전체 지지물 : 설치 16기, 전력선 : HSTACIR/AW 240㎟*S*1C, 16.016km 1) 1차분 (11월19일~11월30일) : 완료 지지물 : 설치 3기, 전력선 : HSTACIR/AW 240㎟*S*1C, 5.312km 2) 2차분 (2019년 4월22일~5월10일) 지지물 : 설치 13기, 전력선 : HSTACIR/AW 240㎟*S*1C, 10.704km","2019-04-22 08:00","2019-05-10 18:00","2019-04-22 08:00","2019-05-10 18:00","연속",null,null,null,201902130393]
[454,"경북","직할","울진현종산풍력#1 T/L","154kV 울진-현종산풍력T/L 정밀점검","154kV 울진-현종산풍력T/L 정밀점검(No.54~117)","2019-04-22 07:00","2019-04-26 18:00","2019-04-22 07:00","2019-04-26 18:00","연속",null,null,null,201902110637]
[455,"경북","직할","현종산풍력평해#2 T/L","154kV 현종산풍력-평해#2T/L 정밀점검","154kV 현종산풍력-평해#2T/L 정밀점검(No.1~87)","2019-04-25 07:00","2019-05-03 18:00","2019-04-25 07:00","2019-05-03 18:00","연속",null,null,null,201902110640]
[456,"부산울산","동부산","구서노포#1 T/L","2019년 가공송전 순시점검 위탁공사(동부산)","154kV 구서-노포T/L 정밀점검 ㅇ구간 : 구서C/H ~ 노포S/S (18기)","2019-04-08 09:00","2019-04-09 18:00","2019-04-08 09:00","2019-04-09 18:00","매일",null,null,null,201902080352]
[457,"부산울산","동부산","노포정관#2 T/L","345kV 신양산-북부산 등 2개T/L 안전이격확보공사","1. 본선로 구성 2. 공사개요 : 철탑설치 : 10호, 철탑철거 : 9,10호, 전선교체 : 8-12호","2019-04-10 07:00","2019-04-27 18:00","2019-04-10 07:00","2019-04-27 18:00","연속",null,null,null,201902080221]
[458,"부산울산","동부산","노포정관#1 T/L","345kV 신양산-북부산 등 2개T/L 안전이격확보공사","1. 가선로 구성 2. 공사개요 : 철탑설치 : 10호, 철탑철거 : 9,10호, 전선교체 : 8-12호","2019-04-04 07:00","2019-04-07 18:00","2019-04-04 07:00","2019-04-07 18:00","연속",null,null,null,201902080217]
[459,"부산울산","동부산","구서노포#1 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 작업내용 : 154kV 노포-정관#2T/L 피뢰기 설치관련 안전이격확보","2019-04-19 08:00","2019-04-19 18:00","2019-04-19 08:00","2019-04-19 18:00","당일",null,null,null,201902080233]
[460,"부산울산","동부산","노포정관#1 T/L","345kV 신양산-북부산 등 2개T/L 안전이격확보공사","1. 본선로 구성 2. 공사개요 : 철탑설치 : 10호, 철탑철거 : 9,10호, 전선교체 : 8-12호","2019-04-29 07:00","2019-05-02 18:00","2019-04-29 07:00","2019-05-02 18:00","연속",null,null,null,201902080218]
[461,"부산울산","동부산","명례고리NP T/L","2019년 가공송전 순시점검 위탁공사(동부산)","장기사용 전선 건전성 점검 ㅇ구간 : 18호 ~ 고리NPS/S(5경간)","2019-04-16 09:00","2019-04-16 18:00","2019-04-16 09:00","2019-04-16 18:00","당일",null,null,null,201902080351]
[462,"부산울산","동부산","웅촌서창#1 T/L","18-19년 송전정비 협력회사 총액공사(동부산)","애자교체 ㅇ구간 : 21~23호","2019-04-11 08:00","2019-04-11 18:00","2019-04-11 08:00","2019-04-11 18:00","당일",null,null,null,201902080340]
[463,"부산울산","동부산","서창산막#1 T/L","서창S/S 170kV GIS 조작시험","서창S/S 170kV 667GIS 조작시험(서창-산막#1T/L)","2019-04-21 09:30","2019-04-21 14:00","2019-04-21 09:30","2019-04-21 14:00","당일",null,null,null,201902100007]
[464,"부산울산","동부산","서창산막#2 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 작업내용 : 154kV 노포-정관#2T/L 피뢰기 설치관련 안전이격확보(23호)","2019-04-20 08:00","2019-04-20 18:00","2019-04-20 08:00","2019-04-20 18:00","당일",null,null,null,201902080231]
[465,"부산울산","동부산","수영정보#1 T/L","수영S/S 170kV GIS 조작시험","1.수영S/S 170kV 637GIS 조작시험(수영-정보#1T/L) 2.[병행]정보S/S 627GIS 조작시험","2019-04-10 09:30","2019-04-10 14:00","취소","취소","당일",null,null,null,201902100006]
[466,"부산울산","동부산","수영정보#2 T/L","수영S/S 170kV GIS 하자점검","1.수영S/S 170kV 657GIS 하자점검(수영-정보#2T/L) 2.[병행]정보S/S 637GIS 하자점검","2019-04-12 09:30","2019-04-12 17:00","취소","취소","당일",null,null,null,201902100005]
[467,"부산울산","동부산","신양산S/S 154kV #60 BUS","345kV 신양산S/S 현대화 공사","345kV 신양산S/S 현대화 공사 - 덕트 기초 터파기(안전이격)","2019-04-09 09:00","2019-04-11 18:00","2019-04-09 09:00","2019-04-11 18:00","연속",null,null,null,201901310229]
[468,"부산울산","동부산","우동대연 T/L","우동S/S 170kV GIS 조작시험","우동S/S 170kV 627GIS 조작시험(우동-대연T/L)","2019-04-06 09:30","2019-04-06 14:00","2019-04-06 09:30","2019-04-06 14:00","당일",null,null,null,201902100003]
[469,"부산울산","동부산","정관고리NP T/L","2019년 가공송전 순시점검 위탁공사(동부산)","장기사용 전선 건전성 점검 ㅇ구간 : 18호 ~ 고리NPS/S(5경간)","2019-04-17 09:00","2019-04-17 18:00","2019-04-17 09:00","2019-04-17 18:00","당일",null,null,null,201902080349]
[470,"부산울산","북부산","김해S/S 154kV BUS TIE GIS CB","2018년 북부산 변전협력회사 총액공사","김해S/S 154kV Bus-Tie 하자점검","2019-04-16 10:00","2019-04-16 18:00","2019-04-16 10:00","2019-04-16 18:00","당일",null,null,null,201901310187]
[471,"부산울산","북부산","매리김해#1 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","- 피뢰기 설치공사 : 매리-김해#1T/L NO.1~50호 49기","2019-04-08 09:00","2019-04-12 18:00","2019-04-07 09:00","2019-04-11 18:00","연속",null,null,null,201902220039]
[472,"부산울산","북부산","호포매리#1 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","피뢰기 설치공사 관련 안전이격 - 피뢰기 설치공사 : 매리-김해#1T/L NO.1~50호 49기","2019-04-09 09:00","2019-04-09 18:00","2019-04-07 09:00","2019-04-07 18:00","당일",null,null,null,201902220037]
[473,"부산울산","북부산","매리김해#2 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","피뢰기 설치공사 관련 안전이격 - 피뢰기 설치공사 : 매리-김해#1T/L NO.1~50호 49기","2019-04-10 07:00","2019-04-12 18:00","2019-04-09 07:00","2019-04-11 18:00","연속",null,null,null,201902220038]
[474,"부산울산","북부산","양산물금 T/L","154㎸ 물금-삼랑진등 6개 T/L 자기애관 교체공사","자기애관 → 폴리머 애관 교체","2019-04-15 09:00","2019-04-18 12:00","2019-04-15 09:00","2019-04-18 12:00","연속",null,null,null,201902070368]
[475,"부산울산","북부산","삼계어방#2 T/L","154㎸ 물금-삼랑진등 6개 T/L 자기애관 교체공사","자기애관 → 폴리머 애관 교체","2019-04-27 09:00","2019-04-29 18:00","취소","취소","연속",null,null,null,201902070380]
[476,"부산울산","북부산","북부산양산 T/L","양산S/S 취약설비 현대화공사","북부산양산T/L (신)양산S/S 수용","2019-04-22 09:00","2019-05-03 18:00","취소","취소","연속",null,null,null,201902080081]
[477,"부산울산","북부산","양산산막#1 T/L","154kV 양산S/S 현대화 관련 전력케이블 인출정비공사","양산-산막#1T/L EBA 폴리머애관 설치시 안전이격","2019-04-19 09:00","2019-04-19 18:00","2019-04-19 09:00","2019-04-19 18:00","당일",null,null,null,201902190169]
[478,"부산울산","북부산","양산산막#1 T/L","양산S/S 취약설비 현대화공사","양산산막#1T/L (신)양산S/S 수용","2019-04-22 09:00","2019-05-03 18:00","취소","취소","연속",null,null,null,201902080083]
[479,"부산울산","서부산","서부산S/S 154kV #1 BUS TIE CB","서부산S/S #1BUSTIE GIS 보통점검","서부산S/S #1BUSTIE GIS 보통점검","2019-04-11 10:00","2019-04-11 18:00","2019-04-11 10:00","2019-04-11 18:00","당일",null,null,null,201902070117]
[480,"부산울산","서부산","서부산S/S 154kV #66 BUS","19년 서부산전력지사 GIS 정밀점검공사","서부산S/S #4S/T용 MTR GIS 정밀점검 - 정밀점검후 시험가압","2019-04-30 17:00","2019-04-30 18:00","2019-04-30 17:00","2019-04-30 18:00","당일",null,null,null,201902110201]
[481,"부산울산","울산","신온산온산#1 T/L","2018~19년 변전협력 총액공사","- 657GIS 보통점검(신온산) - 647GIS 차단기 동작시험(온산)","2019-04-04 09:00","2019-04-04 18:00","2019-04-04 09:00","2019-04-04 18:00","당일",null,null,null,201901310250]
[482,"부산울산","울산","신온산온산#2 T/L","2018~19년 변전협력 총액공사","- 617GIS 보통점검(신온산) - 657GIS 차단기 동작시험(온산)","2019-04-05 09:00","2019-04-05 18:00","2019-04-05 09:00","2019-04-05 18:00","당일",null,null,null,201901310251]
[483,"부산울산","울산","신울산영남TP#2 T/L","2019년 가공송전 순시점검 위탁공사","□ 공사내용 : 154kV 신울산-영남TP#2T/L 애자발취대상 제원확인 및 정밀점검 □ 공사기간 : 2019.04.22 ~ 2019.04.26","2019-04-22 09:00","2019-04-26 18:00","2019-04-22 09:00","2019-04-26 18:00","연속",null,null,null,201902070322]
[484,"부산울산","울산","신울산명례#1 T/L","2018~19년 변전협력 총액공사","- 6P7 GIS 보통점검","2019-04-01 09:00","2019-04-01 18:00","2019-04-01 09:00","2019-04-01 18:00","당일",null,null,null,201901310245]
[485,"부산울산","울산","신울산영남TP#1 T/L","2019년 가공송전 순시점검 위탁공사","□ 공사내용 : 154kV 신울산-영남TP#1T/L 애자발취대상 제원확인 및 정밀점검 □ 공사기간 : 2019.04.15 ~ 2019.04.19","2019-04-15 09:00","2019-04-19 18:00","2019-04-15 09:00","2019-04-19 18:00","연속",null,null,null,201902070318]
[486,"부산울산","울산","신울산울산#1 T/L","2019년 가공송전 순시점검 위탁공사","154kV 신울산-영남TP#1T/L 정밀점검 안전확보선로","2019-04-15 09:00","2019-04-15 18:00","2019-04-15 09:00","2019-04-15 18:00","당일",null,null,null,201902070327]
[487,"부산울산","울산","신울산울산#2 T/L","2019년 가공송전 순시점검 위탁공사","154kV 신울산-영남TP#2T/L 정밀점검 안전확보선로","2019-04-22 09:00","2019-04-22 18:00","2019-04-22 09:00","2019-04-22 18:00","당일",null,null,null,201902070325]
[488,"부산울산","울산","온산처용#1 T/L","2018~19년 변전협력 총액공사","- 687GIS 보통점검(처용) - 677GIS 보통점검(온산)","2019-04-26 09:00","2019-04-26 18:00","2019-04-25 09:00","2019-04-25 18:00","당일",null,null,null,201901310277]
[489,"부산울산","울산","용연울산TP#1 T/L","2019년 울산전력지사 170kV 장기사용GIS 대체공사","- 154kV 한국가스T/L #1DS 투입 후 시험가압(1H)","2019-04-12 16:00","2019-04-12 17:00","2019-04-13 16:00","2019-04-13 17:00","당일",null,null,null,201901310265]
[490,"부산울산","울산","용연울산TP#3 T/L","2019년 울산전력지사 170kV 장기사용GIS 대체공사","- 154kV 한국가스T/L #2BUS 시험가압선로(1H)","2019-04-03 18:00","2019-04-03 19:00","2019-04-03 18:00","2019-04-03 19:00","당일",null,null,null,201901310249]
[491,"부산울산","울산","용연울산TP#3 T/L","2019년 울산전력지사 170kV 장기사용GIS 대체공사","- 154kV 한국가스T/L 2BUS, 2DS, 상부모선, C/H 시험가압선로(24H)","2019-04-11 16:00","2019-04-12 16:00","2019-04-12 16:00","2019-04-13 16:00","연속",null,null,null,201901310263]
[492,"부산울산","울산","용연울산TP#1 T/L","2019년 울산전력지사 170kV 장기사용 GIS 대체공사","- 154KV 한국가스T/L #1BUS 시험가압선로(24H)","2019-04-06 18:00","2019-04-07 18:00","2019-04-06 18:00","2019-04-07 18:00","연속",null,null,null,201901310253]
[493,"부산울산","울산","울주외동#2 T/L","154㎸ 울주-외동T/L OPGW 이도조정 및 금구류 교체공사","154㎸ 울주-외동#2 등 2개T/L 송전선로 갤로핑 고장예방관련 OPGW 이도조정","2019-04-02 07:00","2019-04-04 18:00","2019-04-02 07:00","2019-04-04 18:00","연속",null,null,null,201902110218]
[494,"부산울산","울산","온산처용#2 T/L","2018~19년 변전협력 총액공사","- 657GIS 보통점검 - 피뢰기 교체","2019-04-19 09:00","2019-04-19 18:00","2019-04-19 09:00","2019-04-19 18:00","당일",null,null,null,201901310280]
[495,"부산울산","직할","부산영도#1 T/L","2019년 직할 변전협력회사 총액공사","- 부산S/S 부산-영도#1T/L GIS 보통점검 - 영도S/S 부산-영도#1T/L GIS 미동작점검","2019-04-12 10:00","2019-04-12 18:00","취소","취소","당일",null,null,null,201902080064]
[496,"부산울산","직할","부산수정#2 T/L","2019년 직할 변전협력회사 총액공사","- 부산S/S 부산-수정#2T/L GIS 보통점검 - 수정S/S 부산-수정#2T/L GIS 미동작점검","2019-04-11 10:00","2019-04-11 18:00","2019-04-11 10:00","2019-04-11 18:00","당일",null,null,null,201902010266]
[497,"부산울산","직할","부산영도#2 T/L","2019년 직할 변전협력회사 총액공사","- 부산S/S 부산-영도#2T/L GIS 보통점검 - 영도S/S 부산-영도#2T/L GIS 보통점검","2019-04-15 10:00","2019-04-15 18:00","취소","취소","당일",null,null,null,201902080066]
[498,"부산울산","직할","부산수정#1 T/L","2019년 직할 변전협력회사 총액공사","- 부산S/S 부산-수정#1T/L GIS 보통점검 - 수정S/S 부산-수정#1T/L GIS 미동작점검","2019-04-10 10:00","2019-04-10 18:00","2019-04-10 10:00","2019-04-10 18:00","당일",null,null,null,201902080251]
[499,"부산울산","직할","범일S/S 154kV #1 BUS TIE CB(6100)","2019년 직할 변전협력회사 총액공사","- B/P PNL 대체","2019-04-22 10:00","2019-04-25 18:00","2019-04-22 10:00","2019-04-25 18:00","연속"]
[500,"경남","직할","신김해삼정#2 T/L","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) :65-66B/S GIS 교체(철거 안전이격거리 확보)","2019-04-06 08:00","2019-04-07 17:30","2019-04-06 08:00","2019-04-07 17:30","연속",null,null,null,201901290014]
[501,"경남","직할","신김해S/S 154kV #65 BUS","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) - #65BUS 설치","2019-04-12 07:00","2019-04-14 17:30","2019-04-12 07:00","2019-04-14 17:30","연속",null,null,null,201902190284]
[502,"경남","직할","신김해지사#1 T/L","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) :65-66B/S GIS 교체(철거, 설치 안전이격거리 확보)","2019-04-06 08:00","2019-04-09 17:30","2019-04-06 08:00","2019-04-09 17:30","연속",null,null,null,201901290016]
[503,"경남","직할","신김해장유#1 T/L","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) - #66BUS 시험가압","2019-04-16 17:30","2019-04-17 09:30","2019-04-16 17:30","2019-04-17 09:30","연속",null,null,null,201902190306]
[504,"경남","직할","신김해S/S 154kV #65 BUS","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) :65-66B/S GIS 교체","2019-04-06 08:00","2019-04-07 17:30","2019-04-06 08:00","2019-04-07 17:30","연속",null,null,null,201901290012]
[505,"경남","직할","신김해장유#1 T/L","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) :65-66B/S GIS 교체(65-66-2DS 시험가압선로)","2019-04-18 15:30","2019-04-19 17:30","2019-04-18 15:30","2019-04-19 17:30","연속",null,null,null,201901290020]
[506,"경남","직할","신김해삼정#2 T/L","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) - 65-66B/S 설치(안전이격거리), #65BUS 시험가압","2019-04-12 07:00","2019-04-14 17:30","2019-04-12 07:00","2019-04-14 17:30","연속",null,null,null,201902190301]
[507,"경남","직할","신김해S/S 154kV #66 BUS","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) :65-66B/S GIS 교체","2019-04-06 08:00","2019-04-17 09:30","2019-04-06 08:00","2019-04-17 09:30","연속",null,null,null,201901290013]
[508,"경남","직할","신김해삼정#2 T/L","신김해S/S 170kV 장기사용GIS 대체공사(5차공정)","신김해S/S 170kV 장기사용GIS 대체공사(5차공정) :65-66B/S GIS 교체(65-66-1DS, CB 시험가압선로)","2019-04-17 17:30","2019-04-18 15:30","2019-04-17 17:30","2019-04-18 15:30","연속",null,null,null,201901290018]
[509,"경남","직할","신월삼정#1 T/L","2019년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검(안전거리확보)","2019-04-08 08:00","2019-04-08 18:00","2019-04-08 08:00","2019-04-08 18:00","당일",null,null,null,201902080060]
[510,"경남","직할","신월동읍#2 T/L","2019년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2019-04-15 08:00","2019-04-19 18:00","2019-04-15 08:00","2019-04-19 18:00","매일",null,null,null,201902080061]
[511,"경남","직할","신월동읍#1 T/L","2019년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2019-04-08 08:00","2019-04-12 18:00","2019-04-08 08:00","2019-04-12 18:00","매일",null,null,null,201902080059]
[512,"경남","직할","신월삼정#2 T/L","2019년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검(안전거리 확보)","2019-04-15 08:00","2019-04-15 18:00","2019-04-15 08:00","2019-04-15 18:00","당일",null,null,null,201902080062]
[513,"경남","직할","차룡창공#2 T/L","창공S/S 154kV 차룡-창공#2T/L CB 하자점검","창공S/S 154kV 차룡-창공#2T/L CB 하자점검","2019-04-04 09:30","2019-04-04 17:30","2019-04-04 09:30","2019-04-04 17:30","당일",null,null,null,201902080156]
[514,"경남","직할","차룡창공#1 T/L","창공S/S 154kV 차룡-창공#1T/L CB 하자점검","창공S/S 154kV 차룡-창공#1T/L CB 하자점검","2019-04-03 09:30","2019-04-03 17:30","2019-04-03 09:30","2019-04-03 17:30","당일",null,null,null,201902080154]
[515,"경남","진주","진주개양#1 T/L","진주개양#1 T/L 송전선로 보호반 대체","진주개양#1 T/L 송전선로 보호반 대체 진주 617 조작시험","2019-04-22 09:00","2019-04-24 18:00","2019-04-27 09:00","2019-04-28 18:00","연속",null,null,null,201901310271]
[516,"경남","진주","의령동진주#1 T/L","154kV 의령-함양T/L 송전용 피뢰기 설치 안전이격","154kV 의령-함양T/L 송전용 피뢰기 설치 안전이격","2019-04-07 07:30","2019-04-07 19:00","2019-04-07 07:30","2019-04-07 19:00","당일",null,null,null,201902070283]
[517,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주#2T/L 송전용 피뢰기 설치","154kV 의령-동진주#2T/L 송전용 피뢰기 설치(5기)","2019-04-06 07:30","2019-04-06 19:00","2019-04-06 07:30","2019-04-06 19:00","당일",null,null,null,201902070275]
[518,"경남","진주","의령산청 T/L","154kV 의령-동진주#2T/L 송전용 피뢰기 설치 안전이격","154kV 의령-동진주#2T/L 송전용 피뢰기 설치 안전이격","2019-04-06 07:30","2019-04-06 19:00","2019-04-06 07:30","2019-04-06 19:00","당일",null,null,null,201902070277]
[519,"경남","진주","의령함양 T/L","154kV 의령-함양T/L 송전용 피뢰기 설치(5기)","154kV 의령-함양T/L 송전용 피뢰기 설치(5기)","2019-04-07 07:30","2019-04-07 19:00","2019-04-07 07:30","2019-04-07 19:00","당일",null,null,null,201902070280]
[520,"경남","진주","하동하동화력#1 T/L","154kV 하동-하동화력#1T/L 송전선로 정밀점검","154kV 하동-하동화력#1T/L 송전선로 정밀점검","2019-04-08 09:00","2019-04-11 18:00","2019-04-08 09:00","2019-04-11 18:00","매일",null,null,null,201902050001]
[521,"경남","진주","하동하동화력#2 T/L","154kV 하동-하동화력#2T/L 송전선로 정밀점검","154kV 하동-하동화력#2T/L 송전선로 정밀점검","2019-04-15 09:00","2019-04-17 18:00","2019-04-15 09:00","2019-04-17 18:00","매일",null,null,null,201902050002]
[522,"경남","진주","광양하동#1 T/L","154kV 광양-하동#1T/L 송전용 피뢰기 설치(20기)","154kV 광양-하동#1T/L 송전용 피뢰기 설치(20기)","2019-04-13 07:30","2019-04-14 19:00","2019-04-13 07:30","2019-04-14 19:00","매일",null,null,null,201902070293]
[523,"경남","진주","광양하동#2 T/L","154kV 광양-하동#1T/L 송전용 피뢰기 설치 안전이격","154kV 광양-하동#1T/L 송전용 피뢰기 설치 안전이격","2019-04-13 07:30","2019-04-14 19:00","2019-04-13 07:30","2019-04-14 19:00","매일",null,null,null,201902070294]
[524,"경남","진주","합천수력#2 T/L","154kV 거창-합천#1T/L 송전용 피뢰기 설치 안전이격","154kV 거창-합천#1T/L 송전용 피뢰기 설치 안전이격","2019-04-08 07:30","2019-04-08 19:00","2019-04-08 07:30","2019-04-08 19:00","당일",null,null,null,201902070292]
[525,"경남","통영","삼천포S/S 신고성-삼천포#1T/L GIS","삼천포S/S 신고성-삼천포#1T/L GIS 보통점검","삼천포S/S 신고성-삼천포#1T/L GIS 보통점검","2019-04-16 09:30","2019-04-16 18:00","2019-04-16 09:30","2019-04-16 18:00","당일",null,null,null,201902090043]
[526,"경남","통영","신고성삼천포#2 T/L","154kV 신고성-삼천포#2T/L 피뢰기 설치공사","154kV 신고성-삼천포#2T/L 1~5호 피뢰기 설치공사","2019-04-15 07:00","2019-04-15 18:00","2019-04-15 07:00","2019-04-15 18:00","당일",null,null,null,201902080086]
[527,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 피뢰기 설치공사","154kV 신고성-거제#2T/L 피뢰기 설치공사","2019-04-13 07:00","2019-04-14 18:00","2019-04-13 07:00","2019-04-14 18:00","매일",null,null,null,201902080106]
[528,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 피뢰기 설치공사","154kV 신고성-거제#2T/L 피뢰기 설치공사","2019-04-20 07:00","2019-04-21 18:00","2019-04-20 07:00","2019-04-21 18:00","매일",null,null,null,201902080107]
[529,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 피뢰기 설치공사","154kV 신고성-거제#2T/L 피뢰기 설치공사","2019-04-27 07:00","2019-04-28 18:00","2019-04-27 07:00","2019-04-28 18:00","매일",null,null,null,201902080108]
[530,"경남","통영","신고성S/S 154kV #61 BUS","삼천포,신고성S/S 용량부족차단기대체공사","#3M.Tr 가압시 위상체크","2019-04-30 16:00","2019-04-30 18:00","2019-04-30 16:00","2019-04-30 18:00","당일",null,null,null,201901300182]
[531,"경남","통영","통영거제#1 T/L","154kV 신고성-거제#2T/L 피뢰기 설치공사 안전확보차","154kV 신고성-거제#2T/L 피뢰기 설치공사 안전확보차","2019-04-28 07:00","2019-04-28 18:00","2019-04-28 07:00","2019-04-28 18:00","당일",null,null,null,201902080182]
[532,"경남","함안","가야사봉#1 T/L","154kV 가야-사봉#1T/L 피뢰기 설치작업","154kV 가야-사봉#1T/L 30~43호 피뢰기 설치작업","2019-04-02 07:00","2019-04-02 18:00","2019-04-02 07:00","2019-04-02 18:00","당일",null,null,null,201902080419]
[533,"경남","함안","진영한림정#2 T/L","154kV 진영-한림정T/L 4호 지장송전선로 이설공사","1. 사업구간 : 3~5호 (0.62km) 2. 사업위치 : 경남 김해시 진영읍 설창리 산1-4번지 일원 3. 송전선로 : 154kV 410㎟ Ｘ S, 2회선, 전선교체 1.24C-km 4. 지 지 물 : 1기 교체(사각철탑 C2-30m ⇒ 관형주 SPC2-36m)","2019-04-13 08:00","2019-04-14 18:00","2019-04-13 08:00","2019-04-14 18:00","연속",null,null,null,201902070296]
[534,"경남","함안","신김해진영#2 T/L","진영S/S 신김해-진영#2T/L GIS 보통점검","진영S/S 신김해-진영#2T/L GIS 보통점검","2019-04-24 09:30","2019-04-24 17:30","2019-04-24 09:30","2019-04-24 17:30","당일",null,null,null,201901300005]
[535,"경남","함안","진영한림정#1 T/L","154kV 진영-한림정T/L 4호 지장송전선로 이설공사","1. 사업구간 : 3~5호 (0.62km) 2. 사업위치 : 경남 김해시 진영읍 설창리 산1-4번지 일원 3. 송전선로 : 154kV 410㎟ Ｘ S, 2회선, 전선교체 1.24C-km 4. 지 지 물 : 1기 교체(사각철탑 C2-30m ⇒ 관형주 SPC2-36m)","2019-04-06 08:00","2019-04-07 18:00","2019-04-06 08:00","2019-04-07 18:00","연속",null,null,null,201902070295]
[536,"경남","함안","신마산칠서#2 T/L","154kV 신마산-칠서T/L 접속개소 전선교체공사","5~6호, 18~27호 전력선 교체","2019-04-01 07:00","2019-04-07 18:00","2019-04-11 07:00","2019-04-17 18:00","연속",null,null,null,201902070028]
[537,"경남","함안","신마산칠서#1 T/L","154kV 신마산-칠서T/L 접속개소 전선교체공사","5~6호, 18~27호 전력선 교체","2019-04-08 07:00","2019-04-14 18:00","2019-04-18 07:00","2019-04-24 18:00","연속",null,null,null,201902070032]
[538,"대구","달성","창녕구지#2 T/L","154kV 구지-서구지SW 증설공사","154kV 구지-서구지SW 증설공사 관련 안전확보","2019-04-01 09:00","2019-04-14 18:00","2019-04-01 09:00","2019-04-14 18:00","연속"]