{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["종합","765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":13,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"종합","index":0,"n_rows":37,"n_cols":33,"rows_kept":37,"cut":false,"hidden":true,"merged":[[0,0,0,15],[7,14,7,15],[7,1,7,2],[8,1,8,2],[7,9,7,13],[7,3,7,6],[8,3,8,6],[14,14,14,15],[10,1,10,2],[11,1,11,2],[14,9,14,13],[9,1,9,2],[14,2,14,6],[11,3,11,6],[10,3,10,6],[9,3,9,6]]}
[{"$f":"\"'19년 \"&R15&\"월 휴전심의 결과\"","v":"'19년 5월 휴전심의 결과"}]
[]
[]
[]
[]
[]
["◎ 전체 심의결과"]
["전   압","신 청",null,"채 택",null,null,null,"일정\n조정","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)"]
["765kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B9-I9","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J9,L9,N9)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O9/B9)","v":{"$error":"#REF!"}}]
["345kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B10-I10","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J10,L10,N10)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O10/B10)","v":{"$error":"#REF!"}}]
["154kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B11-I11","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J11,L11,N11)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O11/B11)","v":{"$error":"#REF!"}}]
["계",{"$f":"SUM(B9:B11)","v":{"$error":"#REF!"}},null,{"$f":"SUM(D9:D11)","v":{"$error":"#REF!"}},null,null,null,{"$f":"SUM(H9:H11)","v":{"$error":"#REF!"}},{"$f":"SUM(J12,L12,N12)","v":{"$error":"#REF!"}},{"$f":"SUM(J9:J11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(L9:L11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(N9:N11)","v":{"$error":"#REF!"}},{"$f":"SUM(O9:O11)","v":{"$error":"#REF!"}},{"$f":"(O12/B12)","v":{"$error":"#REF!"}}]
[]
["◎ 본부별 심의결과",{"$nulls":16},"월"]
["사업소","신 청","(765/345/154)",{"$nulls":4},"채 택","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)",null,null,5]
["서   울",{"$f":"SUM(C16:G16)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},{"$f":"B16-I16","v":{"$error":"#REF!"}},{"$f":"SUM(J16,L16,N16)","v":{"$error":"#REF!"}},{"$f":"SUM(S16:U16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W16:Y16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA16:AC16)","v":{"$error":"#REF!"}},{"$f":"SUM(AE16:AG16)","v":{"$error":"#REF!"}},{"$f":"(O16/B16)","v":{"$error":"#REF!"}},null,"서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}}]
["남서울",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$f":"SUM(J17,L17,N17)","v":{"$error":"#REF!"}},{"$f":"SUM(S17:U17)","v":{"$error":"#REF!"}},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"남서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}}]
["인   천",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"인천",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}}]
["경기북부",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기북부",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}}]
["경   기",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}}]
["강   원",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"강원",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}}]
["충   북",{"$f":"SUM(C22:G22)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"충북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}}]
["대전충남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"대전충남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}}]
["전   북",{"$f":"SUM(C24:G24)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"전북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}}]
["광주전남",{"$f":"SUM(C25:G25)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"광주전남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}}]
["대구",{"$f":"SUM(C26:G26)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},{"$f":"B26-I26","v":{"$error":"#REF!"}},{"$f":"SUM(J26,L26,N26)","v":{"$error":"#REF!"}},{"$f":"SUM(S26:U26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W26:Y26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA26:AC26)","v":{"$error":"#REF!"}},{"$f":"SUM(AE26:AG26)","v":{"$error":"#REF!"}},{"$f":"(O26/B26)","v":{"$error":"#REF!"}},null,"대구",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}}]
["경북",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}}]
["부산울산",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"부산울산",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}}]
["경   남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$f":"SUM(W29:Y29)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA29:AC29)","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},null,"경남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}}]
["제   주",{"$f":"SUM(C30:G30)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$f":"(O30/B30)","v":{"$error":"#REF!"}},null,"제주",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}}]
[]
[" 붙임 :  1. 집중심의내역 1부"]
[" 붙임 :  전압별 검토서 1부. 끝."]
[]
[null,{"$f":"SUM(B16:B30)","v":{"$error":"#REF!"}},{"$f":"SUM(C16:C30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(E16:E30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(G16:G30)","v":{"$error":"#REF!"}},{"$f":"SUM(H16:H30)","v":{"$error":"#REF!"}},{"$f":"SUM(I16:I30)","v":{"$error":"#REF!"}},{"$f":"SUM(J16:J30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(L16:L30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(N16:N30)","v":{"$error":"#REF!"}},{"$f":"SUM(O16:O30)","v":{"$error":"#REF!"}}]
[{"$f":"COUNTIF(B36:N36,\"NO\")","v":0},{"$f":"IF(B35=B12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(C35=B9,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(E35=B10,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(G35=B11,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(H35=D12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(I35=I12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(J35=J12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(L35=L12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(N35=N12,\"\",\"NO\")","v":{"$error":"#REF!"}}]
[{"$f":"IF(A36>=1,\"틀린곳\",\"\")","v":""},{"$f":"IF(B36=\"NO\",\"총계\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C36=\"NO\",\"765\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(D36=\"NO\",\"총계\",\"\")","v":""},{"$f":"IF(E36=\"NO\",\"345\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(G36=\"NO\",\"154\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(H36=\"NO\",\"채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(I36=\"NO\",\"불채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(J36=\"NO\",\"병행\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(L36=\"NO\",\"취소\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(N36=\"NO\",\"연기\",\"\")","v":{"$error":"#REF!"}}]

{"sheet":"765송부","index":1,"n_rows":8,"n_cols":16,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 5월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"대전충남","서산","신서산신안성#2 T/L","765kV 신중부분기T/L 건설공사","○ 구간 : 765kV 신서산-신안성T/L 2∏분기 ○ 전력선 : ACSR(C) 480(6B)×2C ○ 선로길이 : 4.594km","2019-05-01 06:00","2019-05-15 18:00","2019-05-01 06:00","2019-05-15 18:00","연속",null,null,null,201807110007]
[2,"대전충남","서산","신서산신안성#1 T/L","765kV 신중부분기T/L 건설공사","○ 구간 : 765kV 신서산-신안성T/L 2∏분기 ○ 전력선 : ACSR(C) 480(6B)×2C ○ 선로길이 : 4.594km","2019-05-16 06:00","2019-05-30 18:00","2019-05-16 06:00","2019-05-30 18:00","연속",null,null,null,201807110008]
[3,"부산울산",null,"신고리4호기 주변압기CB(8300,8372)","신고리4호기 부하탈락시험(50%)\n* 조작차단기 : 8300, 8372","○ 주발전기 50% 운전중 SWYD PCB 개방","2019-05-22 05:00","2019-05-22 15:00","2019-05-22 05:00","2019-05-22 15:00","연속"]
[4,"부산울산",null,"신고리4호기 주변압기CB(8300,8372)","신고리4호기 부하탈락시험(80%)\n* 조작차단기 : 8300, 8372","○ 주발전기 80% 운전중 SWYD PCB 개방","2019-05-31 12:00","2019-05-31 22:00","2019-05-31 12:00","2019-05-31 22:00","연속"]

{"sheet":"345송부","index":2,"n_rows":323,"n_cols":16,"rows_kept":323,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,14,3,14],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 5월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S 345kV 양주-중부#1T/L TIE GIS","19년 중부전력지사 변전협력회사 총액공사","ㅇ345kV 7100 BUS TIE GIS 보통점검","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-09 18:00","당일"]
[2,"남서울","강남","신성남신양재#1 T/L","345kV 신성남-신양재#1,2T/L BPT 보수공사","1. OF케이블 경보회로 점검에 따른 부적합 개소 적출 2. 부적합 개소에 대한 설비 보수 시행","2019-05-13 09:00","2019-05-14 18:00","2019-05-13 09:00","2019-05-14 18:00","연속"]
[3,"남서울","강남","신성남신양재 #2 T/L","345kV 신성남-신양재#1,2T/L BPT 보수공사","1. OF케이블 경보회로 점검에 따른 부적합 개소 적출 2. 부적합 개소에 대한 설비 보수 시행","2019-05-15 09:00","2019-05-16 18:00","2019-05-15 09:00","2019-05-16 18:00","연속"]
[4,"남서울","동서울","동서울미금#2 T/L","345kV 동서울-미금#1,2T/L 자기애관 교체공사","대상설비 : 345kV 동서울-미금#1,2T/L No.18C/H 6상 공사내용 : 자기애관 교체 (폴리머애관)","2019-05-11 09:00","2019-05-14 18:00","2019-05-11 09:00","2019-05-14 18:00","연속"]
[5,"남서울","동서울","동서울미금#1 T/L","345kV 동서울-미금#1,2T/L 자기애관 교체공사","대상설비 : 345kV 동서울-미금#1,2T/L No.18C/H 6상 공사내용 : 자기애관 교체 (폴리머애관)","2019-05-04 09:00","2019-05-07 18:00","2019-05-04 09:00","2019-05-07 18:00","연속"]
[6,"남서울","동서울","동서울미금#1 T/L","동서울S/S 345kV #2 Sh.R 증설사업","- 345kV Sh.R(200 Mvar) x 1대 설치","2019-05-02 09:00","2019-05-03 18:00","취소","취소","연속"]
[7,"남서울","영등포","신광명S/S 345kV #72 BAY TIE CB A (7200A)","신광명S/S #7200 GIS 조작시험","CB 동작시간 측정 SF6 가스 수분측정 CT 절연열화 측정","2019-05-02 10:00","2019-05-02 14:00","취소","취소","당일"]
[8,"남서울","영등포","신광명S/S 345kV #76 BAY TIE GIS","신광명S/S #7600 GIS 조작시험","CB 동작시간 측정 SF6 가스 수분측정 CT 절연열화 측정","2019-05-01 14:00","2019-05-01 18:00","취소","취소","당일"]
[9,"남서울","영등포","신광명S/S 345kV #75 BAY TIE GIS","신광명S/S #7500 GIS 조작시험","CB 동작시간 측정 SF6 가스 수분측정 CT 절연열화 측정","2019-05-01 10:00","2019-05-01 14:00","취소","취소","당일"]
[10,"남서울","영등포","신광명S/S #3 M.Tr","#3M.Tr 1,2차 점검","7271조작시험 6344 초기점검","2019-05-10 09:00","2019-05-10 18:00","취소","취소","당일"]
[11,"남서울","영등포","신광명S/S #2 M.Tr","#2M.Tr 1,2차 점검","7571조작시험 6244 초기점검","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-10 18:00","당일"]
[12,"남서울","영등포","신광명S/S #1 M.Tr","#1M.Tr 1,2,3차 점검","7471 조작시험 6144, 4189 초기점검","2019-05-08 09:00","2019-05-08 18:00","취소","취소","당일"]
[13,"남서울","영등포","신광명S/S 345kV #74 BAY TIE CB A (7400A)","신광명S/S #7400 GIS 조작시험","CB 동작시간 측정 SF6 가스 수분측정 CT 절연열화 측정","2019-05-02 14:00","2019-05-02 18:00","취소","취소","당일"]
[14,"남서울","직할","영등포S/S 345kV 신광명-영등포#1T/L CB A (7171/A)","영등포S/S 345kV 신광명-영등포#1T/L(7171)CB 정밀점검공사","영등포S/S 345kV 신광명-영등포#1T/L(7171)CB 정밀점검공사","2019-05-27 09:00","2019-05-30 18:00","2019-05-27 09:00","2019-05-30 18:00","연속"]
[15,"남서울","직할","신광명영등포#2 T/L","영등포S/S 신광명-영등포#2T/L 보호배전반 교체공사","영등포S/S 신광명-영등포#2T/L 보호배전반 교체공사","2019-05-04 09:00","2019-05-06 18:00","취소","취소","연속"]
[16,"남서울","직할","영등포S/S 345kV #2 M.Tr 1차 CB A (7272/A)","영등포S/S 345kV 7272 GIS 정밀점검공사","영등포S/S 345kV 7272 GIS 정밀점검공사","2019-05-07 09:00","2019-05-10 18:00","2019-05-07 09:00","2019-05-10 18:00","연속"]
[17,"남서울","직할","영등포S/S #3 M.Tr","영등포S/S 345kV 7300,7372 GIS 정밀점검 공사","영등포S/S 345kV 7300, 7372 및 연관 DS GIS 정밀점검 공사","2019-05-13 09:00","2019-05-24 18:00","2019-05-13 09:00","2019-05-24 18:00","연속"]
[18,"남서울","동서울","동서울S/S 345kV #75 BUS","동서울S/S 345kV #2Sh.R 증설사업","- 345kV Sh.R * 1대 설치 - 345kV GIS CB *2대 설치","2019-05-02 09:00","2019-05-03 18:00","취소","취소","연속"]
[19,"남서울","동서울","동서울S/S 345kV #1Sh.R 1차-TIE CB A","동서울S/S 345kV #2Sh.R 증설사업","- 345kV Sh.R * 1대 설치 - 345kV GIS CB *2대 설치","2019-05-09 10:00","2019-05-10 16:00","2019-05-09 10:00","2019-05-10 16:00","연속"]
[20,"남서울","동서울","동서울S/S #2Sh.R 1차 CB","동서울S/S 345kV #2Sh.R 증설사업","- 345kV Sh.R * 1대 설치 - 345kV GIS CB *2대 설치","2019-05-09 10:00","2019-05-10 16:00","2019-05-09 10:00","2019-05-10 16:00","연속"]
[21,"남서울","동서울","동서울S/S 345kV #1Sh.R 1차 CB A","동서울S/S 345kV #2Sh.R 증설사업","- 345kV Sh.R * 1대 설치 - 345kV GIS CB *2대 설치","2019-05-09 10:00","2019-05-10 16:00","2019-05-09 10:00","2019-05-10 16:00","연속"]
[22,"남서울","동서울","동서울S/S 345kV #1Sh.R 선로측 CB A","동서울S/S 345kV #2Sh.R 증설사업","- 345kV Sh.R * 1대 설치 - 345kV GIS CB *2대 설치","2019-05-09 10:00","2019-05-10 16:00","2019-05-09 10:00","2019-05-10 16:00","연속"]
[23,"인천","시흥","서서울#2신시흥#1 T/L","신시흥-영흥#4T/L 정밀점검 ","신시흥-영흥#4T/L 정밀점검","2019-05-03 08:00","2019-05-03 11:00","2019-05-03 08:00","2019-05-03 11:00"]
[24,"인천","시흥","화성신시흥 T/L","신시흥-영흥#4T/L 정밀점검 ","신시흥-영흥#4T/L 정밀점검","2019-05-03 11:00","2019-05-03 14:00","2019-05-03 11:00","2019-05-03 14:00"]
[25,"인천","인천","신경서S/S 345kV 신경서-포스코SY#1T/L CB (7371)","신경서S/S 7371GIS 보통점검","신경서S/S 7371GIS 보통점검","2019-05-02 09:00","2019-05-02 18:00","2019-05-02 09:00","2019-05-02 18:00","당일"]
[26,"인천","인천","신경서S/S 345kV 신경서포스코SY#1-신경서 CB(7300)","신경서S/S 7300GIS 보통점검","신경서S/S 7300GIS 보통점검","2019-05-03 09:00","2019-05-03 18:00","2019-05-03 09:00","2019-05-03 18:00","당일"]
[27,"인천","시흥","영흥T/P 345kV #2T.Tr 1차 CB A (7372)","영흥T/P CB(7372) 구조개선","영흥T/P 345kV #2T.Tr 1차 CB (7372)","2019-05-04 09:00","2019-05-10 18:00","2019-05-04 09:00","2019-05-10 18:00","연속"]
[28,"인천","인천","신경서S/S #3 M.Tr 1차 CB (7572)","2019년 부평전력지사 362kV GIS 정밀점검","신경서S/S #3 M.Tr 1차 GIS 정밀점검","2019-05-06 09:00","2019-05-08 18:00","2019-05-06 09:00","2019-05-08 18:00","연속"]
[29,"인천","인천","서인천C/C 345kV #3 Sh.R","서인천C/C 7B79GIS 하자점검","서인천C/C 7B79GIS 하자점검","2019-05-07 09:00","2019-05-07 18:00","2019-05-07 09:00","2019-05-07 18:00","당일"]
[30,"인천","인천","신경서S/S 345kV #1 Sh.R","신경서S/S #1Sh.R 하자점검","신경서S/S #1Sh.R 하자점검 신경서S/S 7179GIS 조작시험","2019-05-08 09:00","2019-05-09 18:00","2019-05-08 09:00","2019-05-09 18:00","연속"]
[31,"인천","인천","신가좌S/S 345kV 신가좌-가정#1T/L CB (7271)","신가좌S/S 7271GIS 조작시험","신가좌S/S 7271GIS 조작시험","2019-05-09 09:00","2019-05-09 13:00","2019-05-09 09:00","2019-05-09 13:00","당일"]
[32,"인천","인천","신경서S/S 345kV 신경서-포스코S/Y#2T/L CB (7571_A)","신경서S/S 7571GIS 보통점검","신경서S/S 7571GIS 보통점검","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-09 18:00","당일"]
[33,"인천","인천","신가좌S/S 345kV 신가좌-신시흥#2T/L CB (7471)","신가좌S/S 7471GIS 조작시험","신가좌S/S 7471GIS 조작시험","2019-05-09 13:00","2019-05-09 18:00","2019-05-09 13:00","2019-05-09 18:00","당일"]
[34,"인천","인천","신가좌S/S 345kV 신가좌가정#1-신가좌신시 CB(7200)","신가좌S/S 7200GIS 조작시험","신가좌S/S 7200GIS 조작시험","2019-05-10 09:00","2019-05-10 13:00","2019-05-10 09:00","2019-05-10 13:00","당일"]
[35,"인천","김포","신김포S/S 345kV #4 SH.R","신김포S/S 345kV #4Sh.R 보통점검","신김포S/S 345kV #4Sh.R 보통점검","2019-05-10 10:00","2019-05-10 18:00","2019-05-10 10:00","2019-05-10 18:00","당일"]
[36,"인천","인천","신가좌S/S 345kV 신가좌신시흥#2T/L-#3 M.Tr CB (7400)","신가좌S/S 7400GIS 조작시험","신가좌S/S 7400GIS 조작시험","2019-05-10 13:00","2019-05-10 18:00","2019-05-10 13:00","2019-05-10 18:00","당일"]
[37,"인천","시흥","영흥T/P 345kV #1T.Tr 1차-#2T.Tr 1차 CB (7300)","영흥T/P 7300 CB : 7372CB 구조개선 무부가 가압용","영흥T/P 7300CB : 345kV #2T.Tr 1차 CB (7372) 무부하 가압용","2019-05-10 17:00","2019-05-10 18:00","2019-05-10 17:00","2019-05-10 18:00","연속"]
[38,"인천","시흥","신시흥영흥TP#2 T/L","345kV 신시흥-영흥 #2T/L 정밀점검","345kV 신시흥-영흥 #2T/L 정밀점검 -#2(상),4(하)T/L 동시휴전","2019-05-13 08:00","2019-05-15 18:00","취소","취소","연속"]
[39,"인천","시흥","신시흥영흥TP#4 T/L","345kV 신시흥-영흥 #4T/L 정밀점검","345kV 신시흥-영흥 #4T/L 정밀점검 -#2(상),4(하)T/L 동시휴전","2019-05-13 08:00","2019-05-15 18:00","취소","취소","연속"]
[40,"인천","인천","서인천C/C 345kV #1 Sh.R","서인천C/C 7379GIS 하자점검","서인천C/C 7379GIS 하자점검","2019-05-13 09:00","2019-05-13 18:00","2019-05-13 09:00","2019-05-13 18:00","당일"]
[41,"인천","인천","신가좌S/S 345kV 신가좌-신시흥#1T/L CB (7272)","신가좌S/S 7272GIS 조작시험","신가좌S/S 7272GIS 조작시험","2019-05-13 09:00","2019-05-13 13:00","2019-05-13 09:00","2019-05-13 13:00","당일"]
[42,"인천","직할","서인천CC-신부평#1T/L-#1 M.Tr 1차 CB (7100)","신부평S/S 7100CB 누기보수","신부평S/S 7100CB 누기보수","2019-05-13 09:00","2019-05-14 18:00","2019-05-13 09:00","2019-05-14 18:00","연속"]
[43,"인천","인천","신가좌S/S 345kV #2 M.TR 1차 CB A (7372_A)","신가좌S/S 7372GIS 조작시험","신가좌S/S 7372GIS 조작시험","2019-05-13 13:00","2019-05-13 18:00","2019-05-13 13:00","2019-05-13 18:00","당일"]
[44,"인천","인천","신가좌S/S 345kV #2 M.TR 1차 TIE CB A (7300_A)","신가좌S/S 7300GIS 보통점검","신가좌S/S 7300GIS 보통점검","2019-05-14 09:00","2019-05-14 18:00","2019-05-14 09:00","2019-05-14 18:00","당일"]
[45,"인천","직할","신부평S/S 345kV #4Sh.R CB (7479)","신부평S/S 7479CB 362kV GIS 정밀점검","신부평S/S 7479CB 362kV GIS 정밀점검(#4Sh.R)","2019-05-15 08:00","2019-05-17 18:00","취소","취소","연속"]
[46,"인천","인천","신가좌S/S 345kV #3 M.TR 1차 CB A (7472_A)","신가좌S/S 7472GIS 보통점검","신가좌S/S 7472GIS 보통점검","2019-05-15 09:00","2019-05-15 18:00","2019-05-15 09:00","2019-05-15 18:00","당일"]
[47,"인천","인천","신인천C/C 345kV 4MT101 CB A (7772_A)","신인천C/C 7772GIS 조작시험","신인천C/C 7772GIS 조작시험","2019-05-16 09:00","2019-05-16 13:00","2019-05-16 09:00","2019-05-16 13:00","당일"]
[48,"인천","인천","신인천C/C 345kV #70-#71 SEC CB (70-71-0_)","신인천C/C 70-71-0 GIS 조작시험","신인천C/C 70-71-0 GIS 조작시험","2019-05-16 13:00","2019-05-16 18:00","2019-05-16 13:00","2019-05-16 18:00","당일"]
[49,"인천","인천","신인천C/C 345kV #76-#77 SEC CB (76-77-0_)","신인천C/C 76-77-0 GIS 하자점검","신인천C/C 76-77-0 GIS 하자점검","2019-05-17 09:00","2019-05-17 18:00","2019-05-17 09:00","2019-05-17 18:00","당일"]
[50,"인천","인천","서인천C/C 345kV #2 Sh.R","서인천복합S/Y #2Sh.R 대체공사","서인천복합S/Y #2Sh.R 대체공사 - 기존 #2Sh.R 철거 - 신규 #2Sh.R 설치 및 GIB 개조","2019-05-20 09:00","2019-06-07 18:00","2019-05-20 09:00","2019-06-07 18:00","연속"]
[51,"인천","인천","인천CC S/Y 345kV 인천복합 #3,4 G/T CB A (7571_A)","인천CC S/Y 7571 GIS 조작시험","인천CC S/Y 7571 GIS 조작시험","2019-05-20 09:00","2019-05-20 13:00","2019-05-20 09:00","2019-05-20 13:00","당일"]
[52,"인천","직할","서인천CC-신부평#2T/L-#2 M.Tr 1차 CB (7200)","신부평S/S 7200CB 362kV GIS 정밀점검","신부평S/S 7200CB 362kV GIS 정밀점검","2019-05-20 09:00","2019-05-22 18:00","2019-05-20 09:00","2019-05-22 18:00","연속"]
[53,"인천","시흥","신시흥#2S/S 345kV 신시흥-영흥TP#1T/L-#6 CB(7100)","신시흥#1S/S 345kV 신시흥영흥TP#1T/L-#6M.Tr 동작점검","신시흥#1S/S 345kV 신시흥영흥TP#1T/L-#6M.Tr[7100] 동작점검","2019-05-20 10:00","2019-05-20 14:00","2019-05-20 10:00","2019-05-20 14:00","당일"]
[54,"인천","인천","인천CC S/Y 345kV 인천복합 #2 S/T CB A (7671_A)","인천CC S/Y 7671 GIS 조작시험","인천CC S/Y 7671 GIS 조작시험","2019-05-20 13:00","2019-05-20 18:00","2019-05-20 13:00","2019-05-20 18:00","당일"]
[55,"인천","시흥","신시흥#2S/S 345kV 화성-신시흥T/L TIE CB (7400)","신시흥#1S/S 345kV 화성-신시흥T/L TIE CB 동작점검","신시흥#1S/S 345kV 화성-신시흥T/L TIE CB [7400] 동작점검","2019-05-20 14:00","2019-05-20 18:00","2019-05-20 14:00","2019-05-20 18:00","당일"]
[56,"인천","인천","인천CC S/Y 345kV 인천CC#3,4G/T-인천CC#1T/L CB(7500)","인천CC S/Y 7500GIS 조작시험","인천CC S/Y 7500GIS 조작시험","2019-05-21 09:00","2019-05-21 13:00","2019-05-21 09:00","2019-05-21 13:00","당일"]
[57,"인천","시흥","신시흥#2S/S 345kV 서서울2-신시흥#1T/L CB(7500)","신시흥#1S/S 345kV 서서울2-신시흥T/L TIE CB 동작점검","신시흥#1S/S 345kV 서서울2-신시흥T/L TIE CB [7500] 동작점검","2019-05-21 10:00","2019-05-21 14:00","2019-05-21 10:00","2019-05-21 14:00","당일"]
[58,"인천","인천","인천CC S/Y 345kV 인천복합#2S/T-인천복합 CB(7600)","인천CC S/Y 7600GIS 조작시험","인천CC S/Y 7600GIS 조작시험","2019-05-21 13:00","2019-05-21 18:00","2019-05-21 13:00","2019-05-21 18:00","당일"]
[59,"인천","시흥","신시흥#2S/S 345kV 서서울2-신시흥#1T/L CB (7571)","신시흥#1S/S 345kV 서서울2-신시흥T/L CB 동작점검","신시흥#1S/S 345kV 서서울2-신시흥T/L CB [7571] 동작점검","2019-05-21 14:00","2019-05-21 18:00","2019-05-21 14:00","2019-05-21 18:00","당일"]
[60,"인천","시흥","신시흥#2S/S #5 M.Tr","신시흥#2S/S #4 BUS TIE GIS 정밀점검(무부하가압)","신시흥#2S/S #4 BUS TIE GIS 정밀점검(무부하가압)","2019-05-22 09:00","2019-05-22 18:00","2019-05-22 09:00","2019-05-22 18:00","당일"]
[61,"인천","인천","인천CC S/Y 345kV 인천복합 #1,2 G/T CB(7572)","인천CC S/Y 7572GIS 조작시험","인천CC S/Y 7572GIS 조작시험","2019-05-22 09:00","2019-05-22 13:00","2019-05-22 09:00","2019-05-22 13:00","당일"]
[62,"인천","인천","인천CC S/Y 345kV 인천복합 #1 S/T CB(7672)","인천CC S/Y 7672GIS 조작시험","인천CC S/Y 7672GIS 조작시험","2019-05-22 13:00","2019-05-22 18:00","2019-05-22 13:00","2019-05-22 18:00","당일"]
[63,"인천","직할","신부평S/S 서인천CC-신부평#2T/L CB (7271)","신부평S/S 7271CB 362kV GIS 정밀점검","신부평S/S 7271CB 362kV GIS 정밀점검","2019-05-23 08:00","2019-05-25 18:00","2019-05-23 08:00","2019-05-25 18:00","연속"]
[64,"인천","인천","신가좌S/S #4 M.Tr A","신가좌S/S #4M.Tr 휴전","신가좌S/S #4M.Tr 누유보수 신가좌S/S #4-1Sh.R 초기점검","2019-05-23 09:00","2019-05-24 18:00","2019-05-23 09:00","2019-05-24 18:00","연속"]
[65,"인천","인천","인천CC S/Y 345kV 신경서-인천CC#1T/L CB(7271)","인천CC S/Y 7271GIS 하자점검","인천CC S/Y 7271GIS 하자점검","2019-05-23 09:00","2019-05-23 18:00","2019-05-23 09:00","2019-05-23 18:00","당일"]
[66,"인천","시흥","영흥#2T/P 345kV 영흥TP연락#1T/L CB (7671)","영흥#2TP 345kV 영흥TP연락#1T/L CB 동작점검","영흥#2TP 345kV 영흥TP연락#1T/L CB [7671] 동작점검","2019-05-23 10:00","2019-05-23 14:00","2019-05-23 10:00","2019-05-23 14:00","당일"]
[67,"인천","시흥","영흥#2T/P 345kV 영흥TP연락#1T/L-#5G/T CB(7600)","영흥#2T/P 345kV 영흥TP연락#1T/L-#5G/T TIE 동작점검","영흥#2T/P 345kV 영흥TP연락#1T/L-#5G/T TIE [7600]동작점검","2019-05-23 14:00","2019-05-23 18:00","2019-05-23 14:00","2019-05-23 18:00","당일"]
[68,"인천","인천","인천CC S/Y 345kV 신경서인천CC#1T/L TIE CB(7200)","인천CC S/Y 7200GIS 하자점검","인천CC S/Y 7200GIS 하자점검","2019-05-24 09:00","2019-05-24 18:00","2019-05-24 09:00","2019-05-24 18:00","당일"]
[69,"인천","시흥","영흥#2T/P 345kV #5G/T 1차 CB (7672)","영흥#2T/P 345kV #5G/T 1차 CB A 동작점검","영흥#2T/P 345kV #5G/T 1차 CB A [7672] 동작점검","2019-05-24 10:00","2019-05-24 14:00","2019-05-24 10:00","2019-05-24 14:00","당일"]
[70,"인천","시흥","영흥#2T/P 신시흥-영흥TP#3T/L CB (7771)","영흥#2T/P 신시흥-영흥TP#3T/L CB A 동작점검","영흥#2T/P 신시흥-영흥TP#3T/L CB A [7771] 동작점검","2019-05-24 14:00","2019-05-24 18:00","2019-05-24 14:00","2019-05-24 18:00","당일"]
[71,"인천","시흥","신시흥#2S/S #5 M.Tr A","신시흥#2S/S #65 Sh.C GIS 정밀점검(무부하가압)","신시흥#2S/S #65 Sh.C GIS 정밀점검(무부하가압)","2019-05-25 09:00","2019-05-25 18:00","2019-05-25 09:00","2019-05-25 18:00","당일"]
[72,"인천","인천","인천CC S/Y 345kV 포스코S/Y-인천CC#1T/L CB (7A71)","인천CC S/Y 7A71GIS 보통점검","인천CC S/Y 7A71GIS 보통점검","2019-05-27 09:00","2019-05-27 18:00","2019-05-27 09:00","2019-05-27 18:00","당일"]
[73,"인천","시흥","영흥#2T/P 345kV 신시흥-영흥TP#3T/L-#6G/T  CB(7700)","영흥#2T/P 345kV 신시흥-영흥TP#3T/L-#6G/T 동작점검","영흥#2T/P 345kV 신시흥-영흥TP#3T/L-#6G/T TIE [7700]동작점검","2019-05-27 10:00","2019-05-27 18:00","2019-05-27 10:00","2019-05-27 18:00","당일"]
[74,"인천","인천","인천CC S/Y 345kV 포스코S/Y인천CC#1-#2T/L CB (7A00)","인천CC S/Y 7A00GIS 보통점검","인천CC S/Y 7A00GIS 보통점검","2019-05-28 09:00","2019-05-28 18:00","2019-05-28 09:00","2019-05-28 18:00","당일"]
[75,"인천","시흥","신시흥#2S/S 345kV 신시흥-영흥TP#1T/L CB (7171)","신시흥#1S/S 345kV 신시흥-영흥TP#1T/L CB 동작점검","신시흥#1S/S 345kV 신시흥-영흥TP#1T/L CB [7171] 동작점검","2019-05-28 10:00","2019-05-28 14:00","2019-05-28 10:00","2019-05-28 14:00","당일"]
[76,"인천","시흥","신시흥#2S/S 345kV 신시흥-신안산T/L CB (7371)","신시흥#1S/S 345kV 신시흥-신안산T/L CB 동작점검","신시흥#1S/S 345kV 신시흥-신안산T/L CB [7371] 동작점검","2019-05-28 14:00","2019-05-28 18:00","2019-05-28 14:00","2019-05-28 18:00","당일"]
[77,"인천","인천","인천CC S/Y 345kV 포스코S/Y-인천CC#2T/L CB (7A72)","인천CC S/Y 7A72GIS 보통점검","인천CC S/Y 7A72GIS 보통점검","2019-05-29 09:00","2019-05-29 18:00","2019-05-29 09:00","2019-05-29 18:00","당일"]
[78,"경기북부","고양","신덕은S/S 신덕은-LG디스플레이T/L TIE CB (7000)","345kV 신덕은E/C LG 디스플이 T/L 사용전검사(실부하시험)","345kV LG 디스플이 T/L 사용전검사(실부하시험)","2019-05-09 14:00","2019-05-09 16:00","2019-05-09 14:00","2019-05-09 16:00","당일"]
[79,"경기북부","고양","신덕은동두천CC#2 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사 - 345kV 신덕은-동두천CC#2T/L 15경간 항공구 설치 - 154kV 백학-남면#1T/L 병가선로 43RC Off","2019-05-20 08:00","2019-05-24 18:00","2019-05-20 08:00","2019-05-24 18:00","연속"]
[80,"경기북부","고양","신파주S/S #1 M.Tr A","19년도 고양전력지사 변전협력회사 총액공사(M.Tr 보통점검)","#1M.Tr 및 부속설비(GIS, LA등)보통점검","2019-05-13 10:00","2019-05-14 18:00","2019-05-13 10:00","2019-05-14 18:00","연속"]
[81,"경기북부","고양","신파주S/S #2 M.Tr","19년도 고양전력지사 변전협력회사 총액공사(M.Tr 보통점검)","#2M.Tr 및 부속설비(GIS, LA등)보통점검","2019-05-16 10:00","2019-05-17 18:00","2019-05-16 10:00","2019-05-17 18:00","연속"]
[82,"경기북부","고양","신파주S/S #3 M.Tr","19년도 고양전력지사 변전협력회사 총액공사(M.Tr 보통점검)","#3M.Tr 및 부속설비(GIS, LA등)보통점검","2019-05-20 10:00","2019-05-21 18:00","2019-05-20 10:00","2019-05-21 18:00","연속"]
[83,"경기북부","구리","미금S/S 345kV 동서울-미금 #2T/L-TIE GIS","19년 구리전력 345kV GIS 보통점검(단독차단기 휴전)","19년 구리전력 345kV GIS 보통점검(단독차단기 휴전) - 미금S/S 7400GIS 보통점검","2019-05-27 09:00","2019-05-27 18:00","2019-05-27 09:00","2019-05-27 18:00","당일"]
[84,"경기북부","구리","미금S/S #1 M.Tr","미금 자기애자 교체공사","미금 자기애자 교체공사","2019-05-07 09:00","2019-05-08 18:00","2019-05-07 09:00","2019-05-08 18:00","매일"]
[85,"경기북부","구리","미금S/S 345kV #75 BUS","19년 구리전력지사 345kV GIS정밀점검","19년 구리전력지사 345kV GIS정밀점검 - #2BUS 휴전, 7552DS 정밀","2019-05-05 09:00","2019-05-06 18:00","취소","취소","연속"]
[86,"경기북부","구리","미금성동#2 T/L","345kV 미금S/S 감시제어설비 교체공사","- 노후 축모반 교체(기존 아날로그 시스템 → SA혼용시스템) - 제어케이블 포설, 결선","2019-05-07 09:00","2019-05-13 18:00","취소","취소","연속"]
[87,"경기북부","구리","미금성동#3 T/L","345kV 미금S/S 감시제어설비 교체공사","- 노후 축모반 교체(기존 아날로그 시스템 → SA혼용시스템) - 제어케이블 포설, 결선","2019-05-21 09:00","2019-05-27 18:00","2019-05-21 09:00","2019-05-27 18:00","연속"]
[88,"경기북부","구리","미금성동#4 T/L","345kV 미금S/S 감시제어설비 교체공사","- 노후 축모반 교체(기존 아날로그 시스템 → SA혼용시스템) - 제어케이블 포설, 결선","2019-05-28 09:00","2019-06-03 18:00","2019-05-28 09:00","2019-06-03 18:00","연속"]
[89,"경기북부","구리","미금S/S 345kV #6 Sh.R","19년 구리전력지사 345kV GIS정밀점검","19년 구리전력지사 345kV GIS정밀점검 - 7679GIS 정밀점검","2019-05-20 09:00","2019-05-23 18:00","취소","취소","연속"]
[90,"경기북부","구리","동서울미금#1 T/L","애자교체 공사","애자교체 공사","2019-05-12 07:00","2019-05-12 12:00","2019-05-12 07:00","2019-05-12 12:00","당일"]
[91,"경기북부","구리","동서울미금#2 T/L","애자교체 공사","애자교체 공사","2019-05-12 12:00","2019-05-12 18:00","2019-05-12 12:00","2019-05-12 18:00","당일"]
[92,"경기북부","구리","미금S/S #3 M.Tr A","미금 #3M.Tr 3차측 절연보강","미금 #3M.Tr 3차측 절연보강","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-09 18:00","당일"]
[93,"경기북부","구리","미금성동#1 T/L","345kV 미금S/S 감시제어설비 교체공사","- 노후 축모반 교체(기존 아날로그 시스템 → SA혼용시스템) - 제어케이블 포설, 결선","2019-05-14 09:00","2019-05-20 18:00","2019-05-14 09:00","2019-05-20 18:00","연속"]
[94,"경기북부","구리","신가평S/S 345kV #3 Sh.R","19년 구리전력 345kV GIS 보통점검","19년 구리전력 345kV GIS 보통점검 - 신가평S/S 7479GIS 보통점검","2019-05-28 09:00","2019-05-28 18:00","2019-05-28 09:00","2019-05-28 18:00","당일"]
[95,"경기북부","구리","신가평S/S 345kV #4 Sh.R","19년 구리전력 345kV GIS 보통점검","19년 구리전력 345kV GIS 보통점검 - 신가평S/S 7679GIS 보통점검","2019-05-29 09:00","2019-05-29 18:00","2019-05-29 09:00","2019-05-29 18:00","당일"]
[96,"경기북부","구리","신포천S/S #4 M.Tr A","345kV GIS 정밀점검 공사(19년 계약분)","345kV GIS 정밀점검 공사(19년 계약분) - 신포천S/S 7671, 7600 GIS 정밀점검 중 7602DS 정밀","2019-05-02 09:00","2019-05-03 18:00","2019-05-02 09:00","2019-05-03 18:00","연속"]
[97,"경기북부","직할","신의정부S/S 345kV 예비 M.Tr CB","18-19 변전협력 총액공사","신의정부S/S 예비M.Tr 부싱 절연유 채유","2019-05-02 10:00","2019-05-02 18:00","취소","취소","당일"]
[98,"경기북부","직할","신의정부S/S #3 M.Tr","18-19 변전협력 총액공사","신의정부S/S #3M.Tr 부싱 절연유 채유","2019-05-02 10:00","2019-05-03 13:00","2019-05-02 10:00","2019-05-03 13:00","연속"]
[99,"경기북부","직할","신의정부양주#2 T/L","345kV신의정부양주#2T/L OPGW 증설공사","가공지선(AWS 120SQ)를 OPGW 120SQ로 교체","2019-05-27 08:00","2019-06-09 18:00","2019-05-27 08:00","2019-06-09 18:00","연속"]
[100,"경기북부","직할","양주S/S #3 M.Tr A","양주S/S 옥외철구 GIS화 전력구공사","양주S/S #3 M.Tr A 인출측 전력구공사","2019-05-03 09:00","2019-05-05 18:00","취소","취소","연속"]
[101,"경기북부","직할","양주S/S #1 M.Tr A","양주S/S 옥외철구 GIS화 전력구공사","양주S/S #1 M.Tr A 인출측 전력구공사","2019-05-09 09:00","2019-05-11 18:00","취소","취소","연속"]
[102,"경기북부","직할","양주S/S #2 M.Tr A","양주S/S 옥외철구 GIS화 전력구공사","양주S/S #2 M.Tr A 인출측 전력구공사","2019-05-06 09:00","2019-05-08 18:00","취소","취소","연속"]
[103,"경기북부","직할","양주S/S #4 M.Tr A","양주S/S 옥외철구 GIS화 전력구공사","양주S/S #4 M.Tr A 인출측 전력구공사","2019-05-12 09:00","2019-05-14 18:00","취소","취소","연속"]
[104,"경기북부","직할","양주S/S 345kV #4 Sh.R 1차 GIS","'19년 변전협력회사 총액공사","개폐타임측정","2019-05-02 14:00","2019-05-02 18:00","2019-05-02 14:00","2019-05-02 18:00","당일"]
[105,"경기","군포","서서울2S/S 345kV 서서울2-신시흥#1T/L GIS","서서울#2S/S 7D72 GIS 하자점검","서서울#2S/S 7D72 GIS 하자점검","2019-05-13 09:00","2019-05-13 14:00","2019-05-13 09:00","2019-05-13 14:00","당일"]
[106,"경기","군포","서서울2S/S 345kV 서서울2-신시흥#2T/L GIS","서서울#2S/S 7C72 GIS 하자점검","서서울#2S/S 7C72 GIS 하자점검","2019-05-13 14:00","2019-05-13 18:00","2019-05-13 14:00","2019-05-13 18:00","당일"]
[107,"경기","군포","서서울2S/S 345kV 서서울2화성#1-TIE GIS","서서울#2S/S 7C00 GIS 하자점검","서서울#2S/S 7C00 GIS 하자점검","2019-05-14 09:00","2019-05-14 14:00","2019-05-14 09:00","2019-05-14 14:00","당일"]
[108,"경기","군포","서서울2S/S 345kV 서서울2화성#2-TIE GIS","서서울#2S/S 7D00 GIS 하자점검","서서울#2S/S 7D00 GIS 하자점검","2019-05-14 14:00","2019-05-14 18:00","2019-05-14 14:00","2019-05-14 18:00","당일"]
[109,"경기","군포","서서울2S/S 345kV 서서울2-화성#1T/L GIS","서서울#2S/S 7C71 GIS 하자점검","서서울#2S/S 7C71 GIS 하자점검","2019-05-15 09:00","2019-05-15 14:00","2019-05-15 09:00","2019-05-15 14:00","당일"]
[110,"경기","군포","서서울2S/S 345kV 서서울2-화성#2T/L GIS","서서울#2S/S 7D71 GIS 하자점검","서서울#2S/S 7D71 GIS 하자점검","2019-05-15 14:00","2019-05-15 18:00","2019-05-15 14:00","2019-05-15 18:00","당일"]
[111,"경기","군포","화성서서울 #2 T/L","345kV 신안산분기T/L OPGW 시설공사","공사장소 : 화성S/S-No.2~No.56~신안산S/S 시설내역: OPGW 120㎟ 24C SM 17.566km, 48C SM 4.113㎞ 시설","2019-05-08 00:07","2019-05-09 18:00","2019-05-08 00:07","2019-05-09 18:00","연속"]
[112,"경기","군포","서서울신광명#1 T/L","19년 군포 변전정비회사 총액공사","서서울신광명1TL 7571 GIS 보통점검 및 LA, CVT 보통점검","2019-05-16 10:00","2019-05-16 18:00","2019-05-16 10:00","2019-05-16 18:00","당일"]
[113,"경기","군포","서서울S/S #3 M.Tr","154kV 남군포S/S 건설사업","o서서울S/S~남군포S/S간 신설 변전설비 무부하 가압 - 서서울~남군포#1.2T/L","2019-05-09 09:00","2019-05-10 18:00","2019-05-09 09:00","2019-05-10 18:00","연속"]
[114,"경기","군포","서서울S/S #3 M.Tr","'19년 군포P/O 변전정비회사 총액공사","345kV 7672,7600 GIS 보통점검, 154kV 6344 GIS 초기점검, 1,2차 LA, 3차 GPT 보통점검","2019-05-14 10:00","2019-05-15 18:00","2019-05-14 10:00","2019-05-15 18:00","당일"]
[115,"경기","군포","서서울신광명#2 T/L","19년 군포 변전정비회사 총액공사","서서울신광명2TL 7671 GIS 보통점검 및 LA, CVT 보통점검","2019-05-17 10:00","2019-05-17 18:00","2019-05-17 10:00","2019-05-17 18:00","당일"]
[116,"경기","군포","신안산S/S 345kV #75 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","- 70BAY GIS 무부하가압 및 Angle 측정, 실부하가압","2019-05-09 14:00","2019-05-10 14:00","2019-05-16 14:00","2019-05-16 16:00","연속"]
[117,"경기","군포","신안산S/S 345kV #70 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","- 70BAY GIS 무부하가압 및 Angle 측정, 실부하가압","2019-05-10 14:00","2019-05-10 16:00","2019-05-16 16:00","2019-05-17 16:00","당일"]
[118,"경기","군포","신안산S/S 345kV #70 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","- 70BAY GIS 무부하가압 및 Angle 측정, 실부하가압","2019-05-09 09:00","2019-05-09 14:00","2019-05-16 09:00","2019-05-16 14:00","당일"]
[119,"경기","군포","신안산S/S #1 M.Tr","345kV 신안산S/S 용량부족 GIS 대체공사","- 345kV 70Bay 용량대체","2019-05-16 09:00","2019-07-31 18:00","2019-05-16 09:00","2019-07-31 18:00","연속"]
[120,"경기","동부","곤지암S/S 345kV 곤지암-동서울#2T/L CB(7471)","19년 동부변전협력회사 총액공사","곤지암:7471.7400 GIS (개폐타임)","2019-05-29 09:00","2019-05-29 14:00","2019-05-29 09:00","2019-05-29 14:00","당일"]
[121,"경기","동부","곤지암S/S 345kV 곤지암-동서울#2T/L TIE CB (7400)","19년 동부변전협력회사 총액공사","곤지암:7471.7400 GIS (개폐타임)","2019-05-29 14:00","2019-05-29 18:00","2019-05-29 14:00","2019-05-29 18:00","당일"]
[122,"경기","동부","곤지암S/S 345kV #3 M.Tr 1차 CB A (7572-A)","19년 동부변전협력회사 총액공사","곤지암:7572,7500 GIS (개폐타임)","2019-05-30 09:00","2019-05-30 14:00","2019-05-30 09:00","2019-05-30 14:00","당일"]
[123,"경기","동부","곤지암S/S 345kV #3 M.Tr 1차-TIE CB A (7500-A)","19년 동부변전협력회사 총액공사","곤지암:7572,7500 GIS (개폐타임)","2019-05-30 14:00","2019-05-30 18:00","2019-05-30 14:00","2019-05-30 18:00","당일"]
[124,"경기","동부","곤지암S/S 345kV 곤지암-신충주#2T/L CB A (7171-A)","19년 동부변전협력회사 총액공사","곤지암: 7171,7372 GIS (개폐타임)","2019-05-31 09:00","2019-05-31 14:00","2019-05-31 09:00","2019-05-31 14:00","당일"]
[125,"경기","동부","곤지암S/S 345kV #2 M.Tr 1차 CB A (7372-A)","19년 동부변전협력회사 총액공사","곤지암: 7171,7372 GIS (개폐타임)","2019-05-31 14:00","2019-05-31 18:00","2019-05-31 14:00","2019-05-31 18:00","당일"]
[126,"경기","동부","곤지암동서울#1 T/L","345kV 곤지암-동서울#1T/L 송전선로 정밀점검","345kV 곤지암-동서울#1T/L 송전선로 정밀점검 1~41호","2019-05-20 09:00","2019-05-22 18:00","2019-05-20 09:00","2019-05-22 18:00","연속"]
[127,"경기","동부","곤지암동서울#2 T/L","345kV 곤지암-동서울#2T/L 송전선로 정밀점검","345kV 곤지암-동서울#2T/L 송전선로 정밀점검 1~41호","2019-05-23 09:00","2019-05-25 18:00","2019-05-23 09:00","2019-05-25 18:00","연속"]
[128,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 #66BUS 무부하가압용 주변압기","2019-05-04 16:00","2019-05-05 16:00","2019-05-04 16:00","2019-05-05 16:00","연속"]
[129,"경기","동부","곤지암S/S 345kV #1 M.Tr 1차 CB(7172)","19년 동부변전협력회사 총액공사","곤지암:7172.7100 GIS (개폐타임)","2019-05-24 09:00","2019-05-24 14:00","2019-05-24 09:00","2019-05-24 14:00","당일"]
[130,"경기","동부","곤지암S/S 345kV 곤지암-신충주#2T/L-#1 M.Tr CB(7100)","19년 동부변전협력회사 총액공사","곤지암:7172.7100 GIS (개폐타임)","2019-05-24 14:00","2019-05-24 18:00","2019-05-24 14:00","2019-05-24 18:00","당일"]
[131,"경기","동부","곤지암S/S 345kV 곤지암-신충주#1T/L CB (7271)","19년 동부변전협력회사 총액공사","곤지암:7271.7200 GIS (개폐타임)","2019-05-27 09:00","2019-05-27 14:00","2019-05-27 09:00","2019-05-27 14:00","당일"]
[132,"경기","동부","곤지암S/S 345kV 곤지암-신충주#1T/L-TIE CB (7200)","19년 동부변전협력회사 총액공사","곤지암:7271.7200 GIS (개폐타임)","2019-05-27 14:00","2019-05-27 18:00","2019-05-27 14:00","2019-05-27 18:00","당일"]
[133,"경기","동부","곤지암S/S 345kV 곤지암-동서울#1T/L CB (7371)","19년 동부변전협력회사 총액공사","곤지암:7371.7300 GIS (개폐타임)","2019-05-28 09:00","2019-05-28 14:00","2019-05-28 09:00","2019-05-28 14:00","당일"]
[134,"경기","동부","곤지암S/S 345kV 곤지암-동서울#1T/L-#2 M.Tr CB(7300)","19년 동부변전협력회사 총액공사","곤지암:7371.7300 GIS (개폐타임)","2019-05-28 14:00","2019-05-28 18:00","2019-05-28 14:00","2019-05-28 18:00","당일"]
[135,"경기","성남","서안성S/S #1 M.Tr","서안성S/S #1M.Tr 2차 GIS 정밀점검","서안성S/S #1M.Tr 2차 GIS 정밀점검","2019-05-13 09:00","2019-05-15 15:00","2019-05-13 09:00","2019-05-15 15:00","당일"]
[136,"경기","성남","서안성S/S #2 M.Tr","서안성S/S #2M.Tr 2차 GIS 정밀점검","서안성S/S #2M.Tr 2차 GIS 정밀점검","2019-05-15 15:00","2019-05-17 18:00","2019-05-15 15:00","2019-05-17 18:00","당일"]
[137,"경기","성남","신성남동서울#1 T/L","7471,7400 GIS 조작시험","7471,7400 GIS 조작시험","2019-05-17 09:00","2019-05-17 18:00","2019-05-17 09:00","2019-05-17 18:00","당일"]
[138,"경기","성남","신성남S/S #2 M.Tr","19년 성남전력지사 변전협력총액공사","-7200,7272 조작 -부싱절연유채유 -#1S.Tr 보통, 4289-1,2 조작 -누유보수","2019-05-02 09:00","2019-05-03 18:00","2019-05-02 09:00","2019-05-03 18:00","연속"]
[139,"경기","성남","신성남S/S 345kV #70-#71 SEC GIS","신성남S/S 70-71 조작시험","신성남S/S 70-71 조작시험","2019-05-14 09:00","2019-05-14 14:00","2019-05-14 09:00","2019-05-14 14:00","당일"]
[140,"경기","성남","신성남S/S #4 M.Tr","7500,7572,6444 GIS조작시험","7500,7572,6444 GIS조작시험","2019-05-13 09:00","2019-05-13 18:00","2019-05-13 09:00","2019-05-13 18:00","당일"]
[141,"경기","성남","신성남S/S 345kV 신안성-신성남#1T/L CB (7671)","7671 조작시험","7671 조작시험","2019-05-20 09:00","2019-05-20 18:00","2019-05-20 09:00","2019-05-20 18:00","당일"]
[142,"경기","성남","신성남S/S 345kV #75-#76 SEC GIS","GIS 조작시험","신성남S/S 75-76조작시험","2019-05-14 14:00","2019-05-14 18:00","2019-05-14 14:00","2019-05-14 18:00","당일"]
[143,"경기","성남","345kV 신안성-서안성#1T/L GIS","19년 성남전력지사 변전협력총액공사","- 7C00,7C72 보통 - 가보제 345T/L 로직개선(계통)","2019-05-18 09:00","2019-05-18 18:00","2019-05-18 09:00","2019-05-18 18:00","연속"]
[144,"경기","성남","345kV 신안성-서안성#2T/L GIS","19년 성남전력지사 변전협력총액공사","7B72,7B00 보통점검","2019-05-11 09:00","2019-05-11 18:00","2019-05-11 09:00","2019-05-11 18:00","연속"]
[145,"경기","성남","345kV 신안성-신성남#2T/L CB (7672)","19년 성남전력지사 345kV GIS 정밀점검","345kV GIS 정밀점검","2019-05-07 09:00","2019-05-11 18:00","2019-05-07 09:00","2019-05-11 18:00","연속"]
[146,"경기","성남","신안성S/S 345kV #5 Sh.R 1차 GIS","19년 성남전력지사 345kV GIS 정밀점검","#5Sh.R GIS 정밀점검","2019-05-20 09:00","2019-05-24 18:00","2019-05-20 09:00","2019-05-24 18:00","연속"]
[147,"경기","성남","#5Sh.R 1차-신안성신용인#1T/L TIE CB (7700)","19년 성남전력지사 345kV GIS 정밀점검","#5Sh.R-신안성신용인#1T/L GIS 정밀점검","2019-05-27 09:00","2019-05-31 18:00","2019-05-27 09:00","2019-05-31 18:00","연속"]
[148,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울#2T/L EBA 자기애관 교체공사","- 345kV 신용인-동서울#2T/L No.67CH 애관교체 3상 - 시공사 : 일진전기(주)","2019-05-13 08:00","2019-05-15 18:00","2019-05-13 08:00","2019-05-15 18:00","연속"]
[149,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울#1T/L EBA 자기애관 교체공사","- 345kV 신용인-동서울#1T/L No.67CH 애관교체 3상 - 시공사 : 일진전기(주)","2019-05-09 08:00","2019-05-11 18:00","2019-05-09 08:00","2019-05-11 18:00","연속"]
[150,"경기","성남","신용인S/S #2 M.Tr","19년 성남전력지사 170KV GIS 정밀점검공사","#2M.Tr 2차 GIS 정밀점검공사","2019-05-20 09:00","2019-05-22 18:00","2019-05-20 09:00","2019-05-22 18:00","연속"]
[151,"경기","성남","신용인S/S 신용인-신수원T/L GIS","19년 성남전력지사 변전협력총액공사","- 7771,7770 하자점검 -LA,CVT 하자점검","2019-05-16 09:00","2019-05-16 18:00","2019-05-16 09:00","2019-05-16 18:00","연속"]
[152,"경기","직할","화성서서울#1 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 345kV 화성S/S GIS 용량대체 및 SW증설공사 O. 70-71SEC GIS 대체관련 #70BUS측 모선무부하 가압","2019-05-11 09:00","2019-05-12 18:00","2019-05-11 09:00","2019-05-12 18:00","연속"]
[153,"경기","직할","화성평택T/P#2 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 345kV 화성S/S GIS 용량대체 및 SW증설공사 O. 인출변경용 GIB 기초설치관련 안전이격거리 확보","2019-05-20 09:00","2019-05-25 18:00","2019-05-20 09:00","2019-05-25 18:00","연속"]
[154,"경기","직할","화성신안산 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 345kV 화성S/S GIS 용량대체 및 SW증설공사 O. 인출변경용 GIB 기초설치관련 안전이격거리 확보","2019-05-13 09:00","2019-05-18 18:00","2019-05-13 09:00","2019-05-18 18:00","연속"]
[155,"경기","직할","화성신시흥 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 345kV 화성S/S GIS 용량대체 및 SW증설공사 O. 인출변경용 GIB 기초설치관련 안전이격거리 확보","2019-05-07 09:00","2019-05-12 18:00","2019-05-07 09:00","2019-05-12 18:00","연속"]
[156,"경기","직할","화성S/S 345kV #70 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 345kV 화성S/S GIS 용량대체 및 SW증설공사 O. #70-71 SEC GIS대체관련 70BUS측 모선연결","2019-05-02 09:00","2019-05-12 18:00","2019-05-02 09:00","2019-05-12 18:00","연속"]
[157,"경기","직할","화성S/S 345kV #70 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 345kV 화성S/S GIS 용량대체 및 SW증설공사 O. #1CLR_GIS 및 70-71GIS 최초가압","2019-05-29 09:00","2019-05-30 18:00","2019-05-29 09:00","2019-05-30 18:00","연속"]
[158,"경기","직할","화성신안산 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 345kV 화성S/S GIS 용량대체 및 SW증설공사 O. #1CLR_GIS 및 70-71 SEC GIS 최초가압","2019-05-29 09:00","2019-05-30 18:00","2019-05-29 09:00","2019-05-30 18:00","연속"]
[159,"경기","직할","화성평택T/P#1 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 345kV 화성S/S GIS 용량대체 및 SW증설공사 O. 인출변경용 GIB 기초설치관련 안전이격거리 확보","2019-05-27 09:00","2019-06-01 18:00","2019-05-27 09:00","2019-06-01 18:00","연속"]
[160,"경기","직할","화성S/S 345kV #71 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 345kV 화성S/S GIS 용량대체 및 SW증설공사 O. #1CLR_GIS 및 70-71 SEC GIS 최초가압","2019-05-29 09:00","2019-05-30 18:00","2019-05-29 09:00","2019-05-30 18:00","당일"]
[161,"경기","직할","화성S/S 345kV #71 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 345kV 화성S/S GIS 용량대체 및 SW증설공사 O. #1CLR 전력케이블 내압시험","2019-05-27 09:00","2019-05-28 18:00","2019-05-27 09:00","2019-05-28 18:00","당일"]
[162,"강원","강릉","신양양S/S #1 M.Tr","변압기 보통점검 OLTC 정밀점검","변압기 보통점검 OLTC 정밀점검","2019-05-21 10:00","2019-05-23 18:00","2019-05-21 10:00","2019-05-23 18:00","연속"]
[163,"강원","강릉","신양양S/S 345kV #3 M.Tr 1차 TIE CB (7400)","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험","2019-05-20 14:00","2019-05-20 18:00","2019-05-20 14:00","2019-05-20 18:00","당일"]
[164,"강원","강릉","신양양S/S 345kV #3 M.Tr 1차 CB (7472)","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험","2019-05-20 10:00","2019-05-20 14:00","2019-05-20 10:00","2019-05-20 14:00","당일"]
[165,"강원","강릉","신양양S/S #2 M.Tr","변압기 보통점검 OLTC 정밀점검","변압기 보통점검 OLTC 정밀점검","2019-05-27 10:00","2019-05-29 18:00","2019-05-27 10:00","2019-05-29 18:00","연속"]
[166,"강원","동해","삼척GP한울NP1#2 T/L","2019년도 가공송전선로 순시점검 위탁공사","정밀점검 : 58기","2019-05-27 09:00","2019-05-30 18:00","2019-05-27 09:00","2019-05-30 18:00","매일"]
[167,"강원","동해","삼척GP한울NP1#1 T/L","2019년도 가공송전선로 순시점검 위탁공사","정밀점검 : 58기","2019-05-20 09:00","2019-05-23 18:00","2019-05-20 09:00","2019-05-23 18:00","매일"]
[168,"강원","태백","신태백S/S 345kV #3 Sh.R 1차 #1-2 CB(7571)","18~19년 태백전력지사 변전전문회사 총액공사","신태백S/S 345kV 7571CB 보통점검","2019-05-07 09:00","2019-05-07 18:00","2019-05-07 09:00","2019-05-07 18:00","당일"]
[169,"강원","태백","신태백S/S 765kV #4 M.Tr 2차 CB(7771)","18~19년 태백전력지사 변전전문회사 총액공사","신태백S/S 345kV 7771CB 보통점검","2019-05-10 09:00","2019-05-10 18:00","2019-05-10 09:00","2019-05-10 18:00","당일"]
[170,"강원","태백","신태백S/S 345kV #3 Sh.R 1차 #1-1 CB(7579)","18~19년 태백전력지사 변전전문회사 총액공사","신태백S/S 345kV 7579CB 보통점검","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-09 18:00","당일"]
[171,"강원","태백","신태백S/S 345kV #3Sh.R 1차-한울NP2#1T/L CB(7500)","18~19년 태백전력지사 변전전문회사 총액공사","신태백S/S 345kV 7500CB 보통점검","2019-05-08 09:00","2019-05-08 18:00","2019-05-08 09:00","2019-05-08 18:00","당일"]
[172,"강원","태백","신태백S/S 345kV #77 BAY T/L-#4 M.Tr 2차 CB(7700)","18~19년 태백전력지사 변전전문회사 총액공사","신태백S/S 345kV 7700CB 보통점검","2019-05-13 09:00","2019-05-13 18:00","2019-05-13 09:00","2019-05-13 18:00","당일"]
[173,"충북","직할","신진천S/S #1 M.Tr","신진천S/S 345kV #1M.Tr 1차 GIS 초기점검","신진천S/S 345kV #1M.Tr 1차 GIS 초기점검","2019-05-13 10:00","2019-05-14 18:00","2019-05-13 10:00","2019-05-14 18:00","연속"]
[174,"충북","직할","신제천동해#2 T/L","345kV 신제천S/S TCSC 설치공사","TCSC 592.3MVar × 2조 보호배전반 설치 × 1식 - 신제천, 동해S/S 신제천동해#1,2T/L 송전선로보호반 대체 - 신제천S/S 신제천동해#1,2T/L GIB용 보호반 설치","2019-05-06 09:00","2019-05-10 18:00","2019-05-06 09:00","2019-05-10 18:00","연속"]
[175,"충북","청주","신옥천세종#2 T/L","345kV 신옥천-세종#2T/L 초기점검","345kV 신옥천-세종T/L #2 No.49~79호 345kV 세종-청원T/L #1 No.1~30호 (병가) 지지물 30기 및 전력선 ST/AW 410X2B 12.398km 초기점검","2019-05-27 09:00","2019-05-31 18:00","2019-05-27 09:00","2019-05-31 18:00","매일"]
[176,"충북","청주","세종청원#1 T/L","345kV 세종-청원#1T/L 초기점검","345kV 신옥천-세종T/L #2 No.49~79호 345kV 세종-청원T/L #1 No.1~30호 (병가) 지지물 30기 및 전력선 ST/AW 410X2B 12.398km 초기점검","2019-05-27 09:00","2019-05-31 18:00","2019-05-27 09:00","2019-05-31 18:00","매일"]
[177,"충북","청주","신중부청원#2 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","345kV 신중부-청원#2T/L - 애자련보강 : No.19","2019-05-15 09:00","2019-05-15 18:00","2019-05-15 09:00","2019-05-15 18:00","당일"]
[178,"충북","청주","신중부청원#1 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","345kV 신중부-청원#1T/L 불량애자교체 : No.72~74, 37 애자련 보강 : No.19","2019-05-13 09:00","2019-05-14 18:00","2019-05-13 09:00","2019-05-14 18:00","매일"]
[179,"충북","충주","신제천S/S #3 M.Tr","신제천 #3M.Tr 기계적보호장치 교체","기계적보호장치 교체 및 시험","2019-05-08 09:00","2019-05-10 18:00","2019-05-08 09:00","2019-05-10 18:00","연속"]
[180,"충북","충주","신충주S/S STATCOM M.Tr 1차 - TIE GIS","직할 소방설비정밀점검 용역","신충주S/S STATCOM 제어동 소방설비정밀점검","2019-05-03 09:00","2019-05-03 18:00","2019-05-03 09:00","2019-05-03 18:00","당일"]
[181,"충북","충주","신충주S/S STATCOM M.Tr 1차 GIS","직할 소방설비정밀점검 용역","신충주S/S STATCOM 제어동 소방설비정밀점검","2019-05-03 09:00","2019-05-03 18:00","2019-05-03 09:00","2019-05-03 18:00","당일"]
[182,"충북","충주","신충주S/S #2 M.Tr","#2M.Tr C상 변압기 정밀점검","- 신충주S/S #2M.Tr C상 가스이상(요주의Ⅱ)에 따른 변압기 정밀점검","2019-05-20 09:00","2019-05-24 18:00","2019-05-27 09:00","2019-05-31 18:00","연속"]
[183,"충북","충주","신충주S/S #3 M.Tr","#3M.Tr 냉각팬 제작사(효성) 하자대체","- 신충주S/S #3M.Tr 냉각팬 절연불량 신품교체(12대. 철거 및 설치)","2019-05-14 09:00","2019-05-16 18:00","2019-05-14 09:00","2019-05-16 18:00","연속"]
[184,"충북","청주","신옥천세종#1 T/L","345kV 신옥천-세종#2T/L 초기점검","345kV 신옥천-세종T/L #2 No.49~79호 345kV 세종-청원T/L #1 No.1~30호 (병가) 지지물 30기 및 전력선 ST/AW 410X2B 12.398km 초기점검","2019-05-20 09:00","2019-05-24 18:00","2019-05-20 09:00","2019-05-24 18:00","매일"]
[185,"충북","청주","세종청원#2 T/L","345kV 세종-청원#1T/L 초기점검","345kV 신옥천-세종T/L #2 No.49~79호 345kV 세종-청원T/L #1 No.1~30호 (병가) 지지물 30기 및 전력선 ST/AW 410X2B 12.398km 초기점검","2019-05-20 09:00","2019-05-24 18:00","2019-05-20 09:00","2019-05-24 18:00","매일"]
[186,"대전충남","대전","신계룡S/S 345kV #70 BUS","신계룡S/S 345kV #1BUS측 DS(7651) 보통점검 및 병행작업","신계룡S/S 345kV #1BUS측 DS(7651) 보통점검 및 병행작업","2019-05-19 09:00","2019-05-20 18:00","2019-05-19 09:00","2019-05-20 18:00","연속"]
[187,"대전충남","대전","신계룡S/S 345kV #75 BUS","신계룡S/S 345kV #2BUS측 DS(7652) 보통점검 및 병행작업","신계룡S/S 345kV #2BUS측 DS(7652) 보통점검 및 병행작업","2019-05-15 09:00","2019-05-16 18:00","2019-05-15 09:00","2019-05-16 18:00","연속"]
[188,"대전충남","대전","신계룡S/S #3 M.Tr","신계룡S/S 345kV #3M.Tr 정밀점검 및 병행작업","신계룡S/S 345kV #3M.Tr 정밀점검 및 병행작업","2019-05-13 09:00","2019-05-20 18:00","2019-05-13 09:00","2019-05-20 18:00","연속"]
[189,"대전충남","서산","신당진신당진개폐소#1 T/L","송전선로 보호배전반 업그레이드 작업","- 345kV 신당진-연락#1T/L 보호배전반 업그레이드 작업","2019-05-13 09:00","2019-05-13 18:00","취소","취소","당일"]
[190,"대전충남","서산","신당진신당진개폐소#2 T/L","송전선로 보호배전반 업그레이드 작업","- 345kV 신당진-연락#2T/L 보호배전반 업그레이드 작업","2019-05-14 09:00","2019-05-14 18:00","취소","취소","당일"]
[191,"대전충남","서산","신서산S/S 345kV #4 Sh.R CB (7771)","19년도 서산P/O 변전정비회사 총액공사","- 345kV GIS 보통점검","2019-05-03 09:00","2019-05-03 18:00","2019-05-03 09:00","2019-05-03 18:00","당일"]
[192,"대전충남","서산","#5 Sh.R 1차 CB A (7971A)","19년도 서산P/O 변전정비회사 총액공사","- 345kV GIS 보통점검","2019-05-24 09:00","2019-05-24 18:00","2019-05-24 09:00","2019-05-24 18:00","당일"]
[193,"대전충남","서산","태안T/P 345kV 8호기 1차 CB A (7872A)","19년도 서산P/O 765/345kV GIS 점검공사","- 345kV GIS 정밀점검","2019-05-20 09:00","2019-05-24 18:00","2019-05-20 09:00","2019-05-24 18:00","연속"]
[194,"대전충남","서산","태안T/P 345kV #1M.Tr-8호기 1차 CB A (7800A)","19년도 서산P/O 765/345kV GIS 점검공사","- 345kV GIS 정밀점검","2019-05-13 09:00","2019-05-17 18:00","2019-05-13 09:00","2019-05-17 18:00","연속"]
[195,"대전충남","서산","태안T/P 345kV #1M.Tr 1차 CB A (7871A)","19년도 서산P/O 765/345kV GIS 점검공사","- 345kV GIS 정밀점검","2019-05-06 09:00","2019-05-10 18:00","2019-05-06 09:00","2019-05-10 18:00","연속"]
[196,"대전충남","서산","태안T/P 345kV #75-76 SEC CB A (75-76-0A)","19년도 서산P/O 변전정비회사 총액공사","- 345kV GIS 보통점검","2019-05-02 09:00","2019-05-02 18:00","2019-05-02 09:00","2019-05-02 18:00","당일"]
[197,"대전충남","서산","태안T/P 345kV 7호기 1차-TIE CB A (7700A)","19년도 서산P/O 765/345kV GIS 점검공사","- 345kV GIS 정밀점검","2019-05-27 09:00","2019-05-31 18:00","2019-05-27 09:00","2019-05-31 18:00","연속"]
[198,"대전충남","서산","태안T/P 345kV #70-#71 SEC CB A (70-71-0A)","19년도 서산P/O 변전정비회사 총액공사","- 345kV GIS 보통점검","2019-05-01 09:00","2019-05-01 18:00","2019-05-01 09:00","2019-05-01 18:00","당일"]
[199,"대전충남","아산","청양신온양#1 T/L","[송전]345kV 청양-신온양T/L 120호 안전이격확보공사","345kV 청양-신온양T/L 120호 안전이격확보공사","2019-05-13 07:00","2019-05-17 18:00","취소","취소","연속"]
[200,"대전충남","아산","청양신온양#2 T/L","[송전]345kV 청양-신온양T/L 120호 안전이격확보공사","345kV 청양-신온양T/L 120호 안전이격확보공사","2019-05-20 07:00","2019-05-24 18:00","취소","취소","연속"]
[201,"대전충남","아산","아산보령화력#1 T/L","[송전]항공장애표시구 설치공사","항공장애표시구 설치 : No.143-144, 147-148, 154-155 간","2019-05-08 07:30","2019-05-08 18:00","2019-05-08 07:30","2019-05-08 18:00","당일"]
[202,"대전충남","청양","보령C/C 보령연락#2T/L-#2 M.Tr 1차 CB (7200)","보령C/C 345kV 차단기 부동작예방조작시험","보령C/C 345kV 차단기 부동작예방조작시험(7200)","2019-05-07 09:00","2019-05-07 14:00","2019-05-07 09:00","2019-05-07 14:00","당일"]
[203,"대전충남","청양","보령C/C 보령연락#1T/L CB (7171)","보령C/C 345kV 차단기 부동작예방조작시험","보령C/C 345kV 차단기 부동작예방조작시험(7171)","2019-05-07 14:00","2019-05-07 18:00","2019-05-07 14:00","2019-05-07 18:00","당일"]
[204,"대전충남","청양","보령C/C #3 M.Tr 1차 CB (7372)","보령C/C 345kV 차단기 부동작예방조작시험","보령C/C 345kV 차단기 부동작예방조작시험(7372)","2019-05-08 09:00","2019-05-08 14:00","2019-05-08 09:00","2019-05-08 14:00","당일"]
[205,"대전충남","청양","보령C/C #2 M.Tr 1차 CB (7272)","보령C/C 345kV 차단기 부동작예방조작시험","보령C/C 345kV 차단기 부동작예방조작시험(7272)","2019-05-08 14:00","2019-05-08 18:00","2019-05-08 14:00","2019-05-08 18:00","당일"]
[206,"대전충남","청양","보령C/C 청양보령복합T/L CB (7371)","보령C/C 345kV 차단기 부동작예방조작시험","보령C/C 345kV 차단기 부동작예방조작시험(7371)","2019-05-09 09:00","2019-05-09 14:00","2019-05-09 09:00","2019-05-09 14:00","당일"]
[207,"대전충남","청양","보령C/C #3 M.Tr 1차-청양보령#2T/L CB (7300)","보령C/C 345kV 차단기 부동작예방조작시험","보령C/C 345kV 차단기 부동작예방조작시험(7300)","2019-05-09 14:00","2019-05-09 18:00","2019-05-09 14:00","2019-05-09 18:00","당일"]
[208,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-05-14 09:00","2019-05-14 14:00","2019-05-14 09:00","2019-05-14 14:00","당일"]
[209,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-05-14 14:00","2019-05-17 18:00","2019-05-14 14:00","2019-05-17 18:00","연속"]
[210,"대전충남","청양","아산보령화력#2 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 7671 GIS 교체 ○ 보령화력 345kV 7600 GIS 교체 ○ 보령화력 345kV 7672 GIS 교체","2019-05-09 07:30","2019-05-10 18:00","2019-05-09 07:30","2019-05-10 18:00","연속"]
[211,"대전충남","청양","보령T/P 345kV #71 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 71BUS 교체","2019-05-20 09:00","2019-06-13 18:00","2019-05-20 09:00","2019-06-13 18:00","연속"]
[212,"대전충남","청양","청양S/S #2 M.Tr","청양S/S #2M.Tr 보통점검 공사","#2M.Tr 보통점검 및 1차 GIS(7772,7700) 보통점검 공사","2019-05-13 09:00","2019-05-14 18:00","2019-05-13 09:00","2019-05-14 18:00","연속"]
[213,"대전충남","청양","청양S/S 345kV #75 BUS","청양S/S 345kV PT 집합반 설치","청양S/S 345kV PT 집합반 설치","2019-05-16 09:00","2019-05-16 18:00","2019-05-16 09:00","2019-05-16 18:00","당일"]
[214,"대전충남","청양","청양S/S 345kV #70 BUS","청양S/S 345kV PT 집합반 설치","청양S/S 345kV PT 집합반 설치","2019-05-15 09:00","2019-05-15 18:00","2019-05-15 09:00","2019-05-15 18:00","당일"]
[215,"전북","김제","신김제S/S #4 M.Tr","YPP 345kV 변압기 보호배전반 성능개선(신김제 4M.Tr)","YPP 345kV 변압기 보호배전반 로직 수정 및 정정 변경","2019-05-13 10:00","2019-05-13 18:00","2019-05-13 10:00","2019-05-13 18:00","당일"]
[216,"전북","직할","신남원S/S 신남원-광양#2 - TIE GIS(7600)","신남원S/S 345kV 차단기 점검공사(7600)","신남원S/S 신남원-광양#2 - TIE GIS 보통점검","2019-05-20 10:00","2019-05-20 18:00","2019-05-20 10:00","2019-05-20 18:00","당일"]
[217,"전북","직할","신옥천신남원#2-신남원한빛NP#2 T/L GIS(7100)","신남원S/S 345kV 차단기 점검공사(7100)","신옥천신남원#2-신남원한빛NP#2 T/L GIS 조작시험","2019-05-24 12:00","2019-05-24 15:00","2019-05-24 12:00","2019-05-24 15:00","당일"]
[218,"전북","직할","신남원S/S 신옥천-신남원#2 T/L GIS(7171)","신남원S/S 345kV 차단기 점검공사(7171)","신남원S/S 신옥천-신남원#2 T/L GIS 조작시험","2019-05-24 09:00","2019-05-24 12:00","2019-05-24 09:00","2019-05-24 12:00","당일"]
[219,"전북","직할","신남원S/S 신옥천-신남원#1 T/L GIS(7271)","신남원S/S 345kV 차단기 점검공사(7271)","신옥천-신남원#1 T/L GIS 조작시험","2019-05-23 15:00","2019-05-23 18:00","2019-05-23 15:00","2019-05-23 18:00","당일"]
[220,"전북","직할","신남원S/S 신남원-한빛NP#1 T/L GIS(7272)","신남원S/S 345kV 차단기 점검공사(7272)","신남원-한빛#1TL GIS 보통점검","2019-05-23 12:00","2019-05-23 15:00","2019-05-23 12:00","2019-05-23 15:00","당일"]
[221,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주T/L 항공구 설치공사","항공구장애표시구 설치 : No.21~112","2019-05-20 07:00","2019-05-22 18:00","2019-05-20 07:00","2019-05-22 18:00","매일"]
[222,"전북","직할","신남원S/S 신남원-의 령#1 - TIE GIS(7300)","신남원S/S 345kV 차단기 점검공사(7300)","신남원S/S 신남원-의령#1 - TIE GIS 보통점검","2019-05-22 14:00","2019-05-22 18:00","2019-05-22 14:00","2019-05-22 18:00","당일"]
[223,"전북","직할","신남원S/S 신남원-의 령#1 T/L GIS(7371)","신남원S/S 345kV 차단기 점검공사(7371)","신남원S/S 신남원-의령#1T/L GIS 조작시험","2019-05-22 10:00","2019-05-22 14:00","2019-05-22 10:00","2019-05-22 14:00","당일"]
[224,"전북","직할","신남원S/S 신남원-의 령#2 - TIE GIS(7400)","신남원S/S 345kV 차단기 점검공사(7400)","신남원S/S 신남원-의령#2 - TIE GIS 보통점검","2019-05-21 14:00","2019-05-21 18:00","2019-05-21 14:00","2019-05-21 18:00","당일"]
[225,"전북","직할","신남원S/S 신남원-한빛NP#2 T/L GIS(7172)","신남원S/S 345kV 차단기 점검공사(7172)","신남원S/S 신남원-한빛NP#2 T/L GIS 조작시험","2019-05-24 15:00","2019-05-24 18:00","2019-05-24 15:00","2019-05-24 18:00","당일"]
[226,"전북","직할","신남원S/S 신남원-의 령#2 T/L GIS(7471)","신남원S/S 345kV 차단기 점검공사(7471)","신남원S/S 신남원-의령#2 T/L GIS 보통점검","2019-05-21 10:00","2019-05-21 14:00","2019-05-21 10:00","2019-05-21 14:00","당일"]
[227,"전북","직할","신남원S/S 신옥천신남원#1-신남원한빛NP#1 T/L GIS(7200)","신남원S/S 345kV 차단기 점검공사(7200)","신옥천신남원#1-신남원한빛NP#1 T/L GIS 보통점검","2019-05-23 09:00","2019-05-23 12:00","2019-05-23 09:00","2019-05-23 12:00","당일"]
[228,"전북","군산","군산S/S #1 M.Tr","군산P/O 154kV GIS 정밀점검공사 (변압기)","군산S/S #1M.Tr 2차 GIS 정밀점검공사","2019-05-15 09:00","2019-05-16 18:00","2019-05-15 09:00","2019-05-16 18:00","연속"]
[229,"전북","군산","군산S/S #2 M.Tr","군산P/O 154kV GIS 정밀점검공사 (변압기)","군산S/S #2M.Tr 2차 GIS 정밀점검공사","2019-05-20 09:00","2019-05-21 18:00","2019-05-20 09:00","2019-05-21 18:00","연속"]
[230,"전북","군산","군산새만금#1 T/L","YPP 송전선로 보호배전반 성능개선","YPP 송전선로 보호배전반 로직변경","2019-05-20 10:00","2019-05-20 18:00","2019-05-20 10:00","2019-05-20 18:00","당일"]
[231,"전북","군산","군산새만금#2 T/L","YPP 송전선로 보호배전반 성능개선","YPP 송전선로 보호배전반 로직변경","2019-05-21 10:00","2019-05-21 18:00","2019-05-21 10:00","2019-05-21 18:00","당일"]
[232,"광주전남","강진","신강진S/S 345kV #1 BUS GIS","신강진S/S 345kV 취약설비 GIS화 공사","- 345kV 옥외철구 -> GIS화","2019-05-01 09:00","2019-05-08 18:00","2019-05-01 09:00","2019-05-08 18:00","연속"]
[233,"광주전남","강진","신강진S/S 345kV #2 BUS GIS","신강진S/S 345kV 취약설비 GIS화 공사","- 345kV 옥외철구 -> GIS화","2019-05-19 09:00","2019-05-26 18:00","2019-05-19 09:00","2019-05-26 18:00","연속"]
[234,"광주전남","광주","신광주S/S #4 M.Tr","새롬제 345kV #4M.Tr 보호반 성능개선","345kV #4M.Tr 보호반 변압기 3차측 지락보호요소 정정변경 및 주변압기 96P,96D 오동작 방지 관련 회로개선","2019-05-14 09:00","2019-05-16 18:00","2019-05-14 09:00","2019-05-16 18:00","연속"]
[235,"광주전남","광주","신화순S/S 345kV #3 M.Tr 1차 CB A (7572)","19년 광주변전총액공사(7572CB 보통점검)","345kV 7572CB 보통점검","2019-05-08 09:00","2019-05-08 18:00","2019-05-08 09:00","2019-05-08 18:00","당일"]
[236,"광주전남","광주","신화순S/S 345kV #3 M.Tr 1차 TIE CB A (7500)","19년 광주변전총액공사(7500CB 보통점검)","345kV 7500CB 보통점검","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-09 18:00","당일"]
[237,"대구","경산","신경산대구#2 T/L","신경산S/S 362kV 장기사용 GIS 대체공사","장기사용 362kV GIS 및 BUS 교체(7371, 7300, 7372, #1,2BUS)관련 #1BUS 무부하가압 선로","2019-05-01 18:00","2019-05-02 09:00","2019-05-04 18:00","2019-05-05 09:00","연속"]
[238,"대구","달성","고령S/S #1 Sh.R","345kV 고령S/S #1Sh.R 설치공사","- 345kV 친환경 GIB 설치 - 기타부대공사","2019-05-27 09:00","2019-05-31 18:00","2019-05-27 09:00","2019-05-31 18:00","연속"]
[239,"대구","달성","북경남고령#2 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사(보통점검)","2019-05-16 09:00","2019-05-16 18:00","2019-05-16 09:00","2019-05-16 18:00","당일"]
[240,"대구","달성","서대구고령#2 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사(보통점검)","2019-05-14 09:00","2019-05-14 18:00","2019-05-14 09:00","2019-05-14 18:00","연속"]
[241,"대구","달성","대구S/S 345kV #1 Sh.R","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사","2019-05-07 09:00","2019-05-10 18:00","2019-05-13 09:00","2019-05-16 18:00","연속"]
[242,"대구","달성","대구S/S 345kV #2 Sh.R","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사","2019-05-13 09:00","2019-05-16 18:00","2019-05-20 09:00","2019-05-23 18:00","연속"]
[243,"대구","칠곡","북대구S/S 345kV 북대구-선산T/L-TIE CB A (7200)","북대구S/S TIE 북대구-선산 7200GIS 보통점검","북대구S/S TIE 북대구-선산 7200GIS 보통점검","2019-05-09 09:30","2019-05-09 18:00","취소","취소","당일"]
[244,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S #4M.Tr 휴전작업","서대구S/S #4M.Tr 휴전작업","2019-05-02 09:30","2019-05-02 18:00","2019-05-02 09:30","2019-05-02 18:00","당일"]
[245,"대구","칠곡","서대구S/S 북경남-서대구#1T/L CB A (7471)","서대구S/S 북경남-서대구#1T/L 7471 GCB 장기미동작점검","서대구S/S 북경남-서대구#1T/L 7471 GCB 장기미동작점검","2019-05-07 09:30","2019-05-07 15:00","취소","취소","당일"]
[246,"대구","포항","신영일S/S 345kV 신영일-안동CC T/L TIE CB (7600-A)","신영일S/S 345kV 신영일-안동CC TIE 7600 CB 조작시험","신영일S/S 345kV 신영일-안동CC TIE 7600 CB 조작시험","2019-05-15 14:00","2019-05-15 18:00","2019-05-15 14:00","2019-05-15 18:00","당일"]
[247,"대구","포항","신영일S/S 345kV 신영일-안동CC T/L CB A (7671-A)","신영일S/S 345kV 신영일-안동CC T/L 7671 CB 조작시험","신영일S/S 345kV 신영일-안동CC T/L CB 조작시험","2019-05-15 09:00","2019-05-15 14:00","2019-05-15 09:00","2019-05-15 14:00","당일"]
[248,"대구","포항","신포항S/S #3 M.Tr A","신포항S/S #3 M.Tr C상 누유개소 보수작업","신포항S/S #3 M.Tr C상 누유개소 보수작업","2019-05-29 09:30","2019-05-31 18:00","2019-05-29 09:30","2019-05-31 18:00","연속"]
[249,"대구","포항","신포항신월성NP#1 T/L","신포항신월성NP#1 T/L GIS, CB보통점검","신포항신월성NP#1 T/L GIS, CB보통점검","2019-05-27 09:30","2019-05-28 18:00","2019-05-27 09:30","2019-05-28 18:00","연속"]
[250,"대구","포항","신포항신월성NP#2 T/L","신포항신월성NP#2 T/L GIS, CB보통점검","신포항신월성NP#2 T/L GIS, CB보통점검","2019-05-22 09:30","2019-05-23 18:00","2019-05-22 09:30","2019-05-23 18:00","연속"]
[251,"대구","포항","월성연락#2 T/L","월성S/Y 4호기 OH관련 78BAY 점검","월성S/Y 4호기 OH관련 78BAY 점검","2019-05-20 09:30","2019-05-21 18:00","취소","취소","연속"]
[252,"대구","포항","월성2N/P 345kV #4 SS TR 1차 CB A (7872-A)","월성S/Y 4호기 OH관련 78BAY 점검","월성S/Y 4호기 OH관련 78BAY 점검","2019-05-20 09:30","2019-05-21 18:00","2019-05-20 09:30","2019-05-21 18:00","연속"]
[253,"경북","구미","서대구선산#2 T/L","2019년도 구미전력지사 변전정비업체 총액공사","- GIS보통점검 - PT보통점검","2019-05-27 09:00","2019-05-28 18:00","2019-05-27 09:00","2019-05-28 18:00","연속"]
[254,"경북","영주","신제천신영주#1 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","신제천-신영주 #1T/L 송전선로 보호반 교체","2019-05-27 09:00","2019-05-31 18:00","2019-05-27 09:00","2019-05-31 18:00","연속"]
[255,"경북","영주","신영주한울NP2#2 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #2T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #2T/L GIB용 보호반 설치","2019-05-20 10:00","2019-05-24 14:00","취소","취소","연속"]
[256,"경북","영주","신영주한울NP2#1 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #1T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #1T/L GIB용 보호반 설치","2019-05-13 10:00","2019-05-17 14:00","취소","취소","연속"]
[257,"경북","직할","신영주안동CC T/L","18~19년 경북직할 변전정비회사 총액공사","안동복합S/S 신영주-안동CC 송전선로 보호반 대체공사","2019-05-20 09:00","2019-05-24 18:00","2019-05-20 09:00","2019-05-24 18:00","연속"]
[258,"부산울산","동부산","고리N/P S/Y 345kV #71-#72 SEC CB (71-72-0)","고리NP S/Y 362kV GIS 보통점검","고리NP S/Y 362kV GIS 보통점검(72-72-0)","2019-05-20 09:30","2019-05-21 14:00","2019-05-20 09:30","2019-05-21 14:00","연속"]
[259,"부산울산","동부산","고리N/P S/Y 345kV #76-#77 SEC CB (76-77-0)","고리NP S/Y 362kV GIS 보통점검","고리NP S/Y 362kV GIS 보통점검(76-77-0)","2019-05-21 14:00","2019-05-22 18:00","2019-05-21 14:00","2019-05-22 18:00","연속"]
[260,"부산울산","동부산","신양산S/S #4 M.Tr","신양산E/C #4M.Tr 인출측 CVT 대체","1.신양산E/C #4M.Tr 인출측 CVT 대체 2. 7672GIS 조작시험 3.447-1,2,3VCB 보통점검 4. #4-1Sh.R 보통점검","2019-05-02 09:30","2019-05-03 18:00","2019-05-02 09:30","2019-05-03 18:00","연속"]
[261,"부산울산","동부산","신양산S/S #2 M.Tr","신양산E/C 345kV M.Tr 부싱절연유 채유","1.신양산E/C 345kV M.Tr 부싱절연유 채유(#2M.Tr) 2.신양산E/C 7372GIS 조작시험","2019-05-13 09:30","2019-05-13 14:00","2019-05-09 09:30","2019-05-09 14:00","당일"]
[262,"부산울산","동부산","신양산고리NP#2 T/L","신양산E/C 신양산-고리#2T/L 인출측 CVT 대체","1.신양산E/C 신양산-고리#2T/L 인출측 CVT 대체 2. 신양산E/C 1차측 LA 대체 3. 신양산E/C 7571,7500GIS 조작시험","2019-05-07 09:30","2019-05-08 18:00","취소","취소","연속"]
[263,"부산울산","북부산","북부산신울산#2 T/L","19년 가공송전 순시점검 위탁공사","345kV 북부산-신울산#2T/L 정밀점검 시행(ST-49호, 50기)","2019-05-20 09:00","2019-05-24 18:00","2019-05-20 09:00","2019-05-24 18:00","매일"]
[264,"부산울산","북부산","북부산신울산#1 T/L","19년 가공송전 순시점검 위탁공사","345kV 북부산-신울산#1T/L 정밀점검 시행(ST-49호, 50기)","2019-05-13 09:00","2019-05-17 18:00","2019-05-13 09:00","2019-05-17 18:00","매일"]
[265,"부산울산","북부산","북부산신온산 T/L","2019년 북부산 변전협력회사 총액공사","북부산S/S 345kV 북부산-신온산T/L 보호반 대체","2019-05-26 09:00","2019-05-31 18:00","2019-05-26 09:00","2019-05-31 18:00","연속"]
[266,"부산울산","서부산","서부산S/S #2 M.Tr","서부산E/C 345kV #2M.Tr 수냉각 관련 PNL 교체","서부산E/C 345kV #2M.Tr 수냉각 관련 PNL 교체","2019-05-13 10:00","2019-05-21 18:00","2019-05-13 10:00","2019-05-21 18:00","연속"]
[267,"부산울산","서부산","서부산S/S #1 M.Tr","서부산E/C 345kV #1M.Tr 수냉각 관련 PNL 교체","서부산E/C 345kV #1M.Tr 수냉각 관련 PNL 교체","2019-05-01 10:00","2019-05-09 18:00","2019-05-02 10:00","2019-05-10 18:00","연속"]
[268,"부산울산","서부산","서부산S/S #3 M.Tr","서부산E/C 345kV #3M.Tr 수냉각 관련 PNL 교체","서부산E/C 345kV #3M.Tr 수냉각 관련 PNL 교체","2019-05-27 10:00","2019-06-04 18:00","2019-05-27 10:00","2019-06-04 18:00","연속"]
[269,"부산울산","울산","동울산S/S #3M.Tr 1차 CB (7472)","18~19년 변전협력 총액공사","- 7472GIS 보통점검","2019-05-20 09:00","2019-05-20 18:00","2019-05-20 09:00","2019-05-20 18:00","당일"]
[270,"부산울산","울산","동울산S/S 동울산-월성NP#1T/L CB (7171)","18~19년 변전협력 총액공사","- 7171GIS 보통점검","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-09 18:00","당일"]
[271,"부산울산","울산","동울산S/S TIE-#3M.Tr 1차 CB (7400)","18~19년 변전협력 총액공사","- 7400GIS 보통점검","2019-05-17 09:00","2019-05-17 18:00","2019-05-17 09:00","2019-05-17 18:00","당일"]
[272,"부산울산","울산","신온산S/S 신울산-신온산#2T/L 1차 CB (7171)","18~19년 변전협력 총액공사","- 7171GIS 보통점검","2019-05-07 09:00","2019-05-07 18:00","취소","취소","당일"]
[273,"부산울산","울산","신온산S/S S-OIL#5T/L CB (7172)","18~19년 변전협력 총액공사","- 7172GIS 하자점검","2019-05-14 09:00","2019-05-14 18:00","2019-05-14 09:00","2019-05-14 18:00","당일"]
[274,"부산울산","울산","신온산S/S 신울산#2T/L-S-OIL#5T/L TIE CB (7100)","18~19년 변전협력 총액공사","- 7100GIS 보통점검","2019-05-13 09:00","2019-05-13 18:00","2019-05-13 09:00","2019-05-13 18:00","당일"]
[275,"부산울산","울산","신울산S/S #4 M.Tr 1차 TIE CB (7600)","18~19년 변전협력 총액공사","- 7600GIS 보통점검","2019-05-14 09:00","2019-05-14 18:00","2019-05-14 09:00","2019-05-14 18:00","당일"]
[276,"부산울산","울산","신울산S/S #1M.Tr 1차 CB (7172)","18~19년 변전협력 총액공사","- 7172GIS 보통점검","2019-05-10 09:00","2019-05-10 18:00","2019-05-10 09:00","2019-05-10 18:00","당일"]
[277,"부산울산","울산","신울산S/S #4 M.Tr 1차 CB (7672)","18~19년 변전협력 총액공사","- 7672GIS 보통점검","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-09 18:00","당일"]
[278,"부산울산","울산","신울산S/S 70-71 SEC CB (70-71-0)","18~19년 변전협력 총액공사","- 345kV #70-71B/S 보통점검","2019-05-17 09:00","2019-05-17 18:00","2019-05-17 09:00","2019-05-17 18:00","당일"]
[279,"부산울산","울산","신울산S/S 75-76 SEC CB (75-76-0)","18~19년 변전협력 총액공사","- 345kV #75-76B/S 보통점검","2019-05-20 09:00","2019-05-20 18:00","2019-05-20 09:00","2019-05-20 18:00","당일"]
[280,"부산울산","울산","울산C/C #3,4 G/T 1차 CB (7772)","18~19년 변전협력 총액공사","- 7772GIS 보통점검","2019-05-31 09:00","2019-05-31 18:00","2019-05-31 09:00","2019-05-31 18:00","당일"]
[281,"부산울산","울산","울산C/C #2,3 S/T-#3,4 G/T CB (7700)","18~19년 변전협력 총액공사","- 7700GIS 보통점검","2019-05-30 09:00","2019-05-30 18:00","2019-05-30 09:00","2019-05-30 18:00","당일"]
[282,"부산울산","울산","울산C/C 기력4호기 1차 CB (7472)","18~19년 변전협력 총액공사","- 7472GIS 보통점검","2019-05-23 09:00","2019-05-23 18:00","2019-05-23 09:00","2019-05-23 18:00","당일"]
[283,"부산울산","울산","울산C/C #1M.Tr 1차-기력4호기 1차 CB (7400)","18~19년 변전협력 총액공사","- 7400GIS 보통점검","2019-05-22 09:00","2019-05-22 18:00","2019-05-22 09:00","2019-05-22 18:00","당일"]
[284,"부산울산","울산","울산C/C #1M.Tr 1차 CB (7471)","18~19년 변전협력 총액공사","- 7471GIS 보통점검","2019-05-21 09:00","2019-05-21 18:00","2019-05-21 09:00","2019-05-21 18:00","당일"]
[285,"부산울산","울산","울산C/C 북부산-울산TPT/L CB (7571)","18~19년 변전협력 총액공사","- 7571GIS 보통점검","2019-05-24 09:00","2019-05-24 18:00","2019-05-24 09:00","2019-05-24 18:00","당일"]
[286,"부산울산","울산","울산C/C 기력5호기 1차 CB (7572)","18~19년 변전협력 총액공사","- 7572GIS 보통점검","2019-05-28 09:00","2019-05-28 18:00","2019-05-28 09:00","2019-05-28 18:00","당일"]
[287,"부산울산","울산","울산C/C 북부산T/L-기력5호기 1차 CB (7500)","18~19년 변전협력 총액공사","- 7500GIS 보통점검","2019-05-27 09:00","2019-05-27 18:00","2019-05-27 09:00","2019-05-27 18:00","당일"]
[288,"부산울산","울산","신온산울산TP T/L","154kV 온산-처용#2T/L 송전선로용 피뢰기 설치공사","- 154kV 온산-처용#2T/L 작업관련 4회선 병가구간 안전이격거리 확보 (구간 : No.1~9)","2019-05-01 08:00","2019-05-01 18:00","2019-05-11 08:00","2019-05-11 18:00","당일"]
[289,"부산울산","울산","울산C/C #5,6 G/T 1차 CB (7872)","18~19년 변전협력 총액공사","- 7872GIS 보통점검","2019-05-07 09:00","2019-05-07 18:00","2019-05-07 09:00","2019-05-07 18:00","당일"]
[290,"부산울산","울산","울산C/C #2,3 S/T CB (7771)","18~19년 변전협력 총액공사","- 7771GIS 보통점검","2019-05-29 09:00","2019-05-29 18:00","2019-05-29 09:00","2019-05-29 18:00","당일"]
[291,"부산울산","울산","울주월성NP#1 T/L","18~19년 변전협력 총액공사","- 7971GIS 보통점검 - 7900 차단기 동작시험 - CVT, LA대체","2019-05-16 09:00","2019-05-16 18:00","2019-05-16 09:00","2019-05-16 18:00","당일"]
[292,"경남","직할","신김해S/S #5 M.Tr","신김해S/S 345kV #5M.Tr 보통점검","신김해S/S 345kV #5M.Tr 보통점검 (병행)신김해S/S 345kV #5M.Tr 1, 2차 CB 보통점검, 2차 LA 보통점검","2019-05-20 09:30","2019-05-22 17:30","2019-05-20 09:30","2019-05-22 17:30","연속"]
[293,"경남","직할","창원S/S #3 M.Tr","창원S/S 345kV #3M.Tr 초기점검","창원S/S 345kV #3M.Tr 초기점검 (병행)창원S/S 345kV #3M.Tr 1, 2차 CB 초기점검","2019-05-13 09:30","2019-05-15 17:30","2019-05-13 09:30","2019-05-15 17:30","연속"]
[294,"경남","진주","의령산청양수#2 T/L","345kV 의령-산청양수T/L 항공장애표시구 설치공사(가공지선)","ㅇ345kV 의령-산청양수T/L 항공장애표시구 설치 (총 33경간, 138개 설치 - 가공지선) - 작업구간 : 2~3, 6~7, 10~11, 12~13, 20~21, 24~25, 26~27, 29~30, 41~42, 44~45, 48~49, 51~52, 56~57, 59~60, 62~63, 64~65, 65~66, 66~67, 67~68, 6","2019-05-25 07:00","2019-06-08 18:00","취소","취소","매일"]
[295,"경남","진주","의령산청양수#1 T/L","345kV 의령-산청양수T/L 항공장애표시구 설치공사(OPGW)","ㅇ345kV 의령-산청양수T/L 항공장애표시구 설치 (총 33경간, 133개 설치 - OPGW) - 작업구간 : 2~3, 6~7, 10~11, 12~13, 20~21, 24~25, 26~27, 29~30, 41~42, 44~45, 48~49, 51~52, 56~57, 59~60, 62~63, 64~65, 65~66, 66~67, 67~68, 6","2019-05-25 07:00","2019-06-08 18:00","2019-05-25 07:00","2019-05-31 18:00","매일"]
[296,"경남","진주","하동T/P 345kV #7 M.Tr 1차 TIE CB(7700)","하동T/P TIE-#7 M.Tr 1차 CB(7700) 조작시험","하동T/P TIE-#7 M.Tr 1차 CB(7700) 조작시험","2019-05-24 10:00","2019-05-24 14:00","2019-05-24 10:00","2019-05-24 14:00","당일"]
[297,"경남","진주","하동T/P 345kV #75-#76 SEC CB (75-76-0)","하동T/P 345kV BUS-SEC B/F PNL 대체공사","하동T/P 345kV B/S(#70-#71,#75-#76) B/F PNL 대체공사","2019-05-06 09:00","2019-05-11 18:00","2019-05-07 09:00","2019-05-11 18:00","연속"]
[298,"경남","진주","하동T/P 345kV #70-#71 SEC CB(70-71-0)","하동T/P 345kV BUS-SEC B/F PNL 대체공사","하동T/P 345kV B/S(#70-#71,#75-#76) B/F PNL 대체공사","2019-05-06 09:00","2019-05-11 18:00","2019-05-07 09:00","2019-05-11 18:00","연속"]
[299,"경남","진주","하동T/P 345kV 의령-하동TP#2T/L-#5 M.Tr CB(7500)","하동T/P 의령-하동TP#2T/L-#5M.Tr CB(7500) 조작시험","하동T/P 의령-하동TP#2T/L-#5M.Tr CB(7500) 조작시험","2019-05-02 10:00","2019-05-02 14:00","2019-05-02 10:00","2019-05-02 14:00","당일"]
[300,"경남","진주","하동T/P 345kV #5 M.Tr 1차 CB(7572)","하동T/P #5M.Tr 1차 CB(7572) 조작시험","하동T/P #5M.Tr 1차 CB(7572) 조작시험","2019-05-02 14:00","2019-05-02 17:00","2019-05-02 14:00","2019-05-02 17:00","당일"]
[301,"경남","진주","하동T/P 345kV #7 M.Tr 1차 CB(7772)","하동T/P #7 M.Tr 1차 CB(7772) 조작시험","하동T/P #7 M.Tr 1차 CB(7772) 조작시험","2019-05-24 14:00","2019-05-24 17:00","2019-05-24 14:00","2019-05-24 17:00","당일"]
[302,"경남","통영","신고성삼천포화력#2 T/L","삼천포,신고성S/S 용량부족차단기 대체공사","신고성S/S 345kV M.Tr 신GIS로 이설에 따른 신고성-삼천포화력간 송전선로 정지","2019-05-10 10:00","2019-05-10 18:00","2019-05-10 10:00","2019-05-10 18:00","당일"]
[303,"경남","통영","신고성삼천포화력#1 T/L","삼천포,신고성S/S 용량부족차단기 대체공사","신고성S/S 345kV M.Tr 신GIS로 이설에 따른 신고성-삼천포화력간 송전선로 정지","2019-05-10 10:00","2019-05-10 18:00","2019-05-10 10:00","2019-05-10 18:00","당일"]
[304,"경남","통영","신고성S/S #4 M.Tr","삼천포,신고성S/S 용량부족차단기 대체공사","#4M.Tr 1차 인출변경","2019-05-10 09:00","2019-05-31 18:00","2019-05-10 09:00","2019-05-31 18:00","연속"]
[305,"경남","함안","신마산S/S #5 M.Tr","345kV 신마산 용량부족 차단기 대체공사 피뢰기 보강작업","345kV 신마산 용량부족 차단기 대체공사 관련 주변압기 1차측 피뢰기 보강","2019-05-15 09:00","2019-05-16 18:00","2019-05-15 09:00","2019-05-16 18:00","연속"]
[306,"경남","함안","신마산S/S #2 M.Tr","345kV 신마산 용량부족 차단기 대체공사 피뢰기 보강작업","345kV 신마산 용량부족 차단기 대체공사 관련 주변압기 1차측 피뢰기 보강","2019-05-07 09:00","2019-05-08 18:00","2019-05-07 09:00","2019-05-08 18:00","연속"]
[307,"경남","함안","신마산S/S #3 M.Tr","345kV 신마산 용량부족 차단기 대체공사 피뢰기 보강작업","345kV 신마산 용량부족 차단기 대체공사 관련 주변압기 1차측 피뢰기 보강","2019-05-09 09:00","2019-05-10 18:00","2019-05-09 09:00","2019-05-10 18:00","연속"]
[308,"경남","함안","신마산S/S #4 M.Tr","345kV 신마산 용량부족 차단기 대체공사 피뢰기 보강작업","345kV 신마산 용량부족 차단기 대체공사 관련 주변압기 1차측 피뢰기 보강","2019-05-13 09:00","2019-05-14 18:00","2019-05-13 09:00","2019-05-14 18:00","연속"]
[309,"경남","함안","의령신마산#1 T/L","345kV 의령-신마산T/L 정밀점검","1~115호 정밀점검","2019-05-20 09:00","2019-05-24 18:00","2019-05-20 09:00","2019-05-24 18:00","매일"]
[310,"경남","함안","의령신마산#2 T/L","345kV 의령-신마산T/L 정밀점검","1~115호 정밀점검","2019-05-27 09:00","2019-05-31 18:00","2019-05-27 09:00","2019-05-31 18:00","매일"]
[311,"경남","함안","신마산S/S #1 M.Tr","345kV 신마산 용량부족 차단기 대체공사 피뢰기 보강작업","345kV 신마산 용량부족 차단기 대체공사 관련 주변압기 1차측 피뢰기 보강","2019-05-02 09:00","2019-05-03 18:00","2019-05-02 09:00","2019-05-03 18:00","연속"]
[312,"경북",null,"신한울한울#1T/L","보호계전기 교체","선로보호반 보호계전기 CPU 모듈교체 및 시험","2019-05-13 09:00","2019-05-15 12:00","2019-05-13 09:00","2019-05-15 12:00","연속"]
[313,"경북",null,"신한울한울#2T/L","보호계전기 교체","선로보호반 보호계전기 CPU 모듈교체 및 시험","2019-05-15 12:00","2019-05-17 18:00","2019-05-15 12:00","2019-05-17 18:00","연속"]
[314,"경북",null,"예천양수#1,2호기 주변압기 CB(7100,7172,7200,7271)","자체기동발전기 예비시험","자체기동발전기 예비시험","2019-05-08 14:00","2019-05-08 17:00","2019-05-08 14:00","2019-05-08 17:00","연속"]
[315,"경북",null,"예천양수#1호기 주변압기 CB(7100,7172)","전기설비 정기검사","전기설비 정기검사","2019-05-15 08:00","2019-05-17 18:00","2019-05-15 08:00","2019-05-17 18:00","연속"]
[316,"경북",null,"예천양수#1,2호기 주변압기 CB(7100,7172,7200,7271)","자체기동발전기 예비시험","자체기동발전기 예비시험","2019-05-21 14:00","2019-05-21 17:00","2019-05-21 14:00","2019-05-21 17:00","연속"]
[317,"경북",null,"예천양수#2호기 주변압기 CB(7200,7271)","전기설비 정기검사","전기설비 정기검사","2019-05-22 08:00","2019-05-24 18:00","2019-05-22 08:00","2019-05-24 18:00","연속"]
[318,"경북",null,"예천양수#1,2호기 주변압기 CB(7100,7172,7200,7271)","자체기동발전기 본시험","자체기동발전기 본시험","2019-05-30 15:00","2019-05-30 17:00","2019-05-30 15:00","2019-05-30 17:00","연속"]
[319,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 무부하가압","2019-05-25 16:00","2019-05-26 16:00","2019-05-25 16:00","2019-05-26 16:00","연속"]

{"sheet":"154송부","index":3,"n_rows":518,"n_cols":16,"rows_kept":518,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 5월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","상계노원열병합 T/L","2019년 성동P/O 변전정비회사 총액공사","154kV GIS 초기점검","2019-05-08 09:30","2019-05-08 18:00","취소","취소","당일"]
[2,"서울","성동","양주쌍문#2 T/L","2019년 성동P/O 변전정비회사 총액공사","154kV GIS 보통점검","2019-05-03 10:00","2019-05-03 18:00","2019-05-03 10:00","2019-05-03 18:00","당일"]
[3,"서울","성동","화양성수 T/L","2019년 성동P/O 170kV GIS 정밀점검공사","2019년 성동P/O 170kV GIS 정밀점검공사 - 4개 S/S : T/L(10), M.Tr(5), TIE(2)","2019-05-14 09:00","2019-05-15 18:00","취소","취소","연속"]
[4,"서울","성동","미금화양 T/L","2019년 성동P/O 170kV GIS 정밀점검공사","2019년 성동P/O 170kV GIS 정밀점검공사 - 4개 S/S : T/L(10), M.Tr(5), TIE(2)","2019-05-16 09:00","2019-05-17 18:00","취소","취소","연속"]
[5,"서울","중부","동빙고S/S 154kV #60 BUS","2019년 중부P/O 170 GIS 정밀점검공사","2019년 중부P/O 170 GIS 정밀점검공사","2019-05-16 17:00","2019-05-16 18:00","2019-05-16 17:00","2019-05-16 18:00","당일"]
[6,"서울","중부","용산동빙고 T/L","2019년 중부P/O 170kV 정밀점검공사","1. 공사명 : 2019년 중부P/O 170kV 정밀점검공사","2019-05-13 10:00","2019-05-15 10:00","2019-05-13 10:00","2019-05-15 10:00","연속"]
[7,"서울","중부","동빙고반포#1 T/L","2019년 중부P/O 170kV 정밀점검공사","1. 공사명 : 2019년 중부P/O 170kV 정밀점검공사","2019-05-28 17:00","2019-05-28 18:00","2019-05-28 17:00","2019-05-28 18:00","당일"]
[8,"서울","중부","동빙고S/S 154kV #60-65 BUS TIE GIS","2019년 중부P/O 170kV 정밀점검공사","1. 공사명 : 2019년 중부P/O 170kV 정밀점검공사","2019-05-27 10:00","2019-05-28 18:00","2019-05-27 10:00","2019-05-28 18:00","연속"]
[9,"서울","중부","동빙고S/S 154kV #60 BUS","2019년 중부P/O 170 GIS 정밀점검공사","2019년 중부P/O 170 GIS 정밀점검공사","2019-05-28 17:00","2019-05-28 18:00","2019-05-28 17:00","2019-05-28 18:00","당일"]
[10,"서울","중부","순화동빙고 T/L","2019년 중부P/O 170kV 정밀점검공사","1. 공사명 : 2019년 중부P/O 170kV 정밀점검공사","2019-05-15 10:00","2019-05-16 18:00","2019-05-15 10:00","2019-05-16 18:00","연속"]
[11,"서울","중부","동빙고S/S 154kV #65 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-05-15 09:00","2019-05-15 10:00","2019-05-15 09:00","2019-05-15 10:00","당일"]
[12,"서울","중부","수색상암#1 T/L","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색상암#1T/L #1, 2DS 및 Line DS 보통점검","2019-05-04 10:00","2019-05-04 18:00","2019-05-04 10:00","2019-05-04 18:00","당일"]
[13,"서울","중부","수색S/S 154kV #65 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색상암#1T/L #1, 2DS 및 Line DS 보통점검","2019-05-04 14:00","2019-05-04 18:00","2019-05-04 14:00","2019-05-04 18:00","당일"]
[14,"서울","중부","원흥수색#2 T/L","19년 중부전력지사 변전협력회사 총액공사","ㅇ수색S/S 154kV 원흥수색#2T/L GIS 차단기 동작시험","2019-05-29 09:00","2019-05-29 12:00","2019-05-29 09:00","2019-05-29 12:00","연속"]
[15,"서울","중부","수색S/S 154kV #60 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV #2M.Tr 1차 #1, 2DS보통점검","2019-05-18 10:00","2019-05-18 14:00","2019-05-18 10:00","2019-05-18 14:00","당일"]
[16,"서울","중부","수색S/S 154kV #65 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV BUSTIE #1, 2DS 보통점검","2019-05-25 14:00","2019-05-25 18:00","2019-05-25 14:00","2019-05-25 18:00","당일"]
[17,"서울","중부","수색상암#2 T/L","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색상암#2T/L #1, 2DS 및 Line DS 보통점검","2019-05-11 10:00","2019-05-11 18:00","2019-05-11 10:00","2019-05-11 18:00","당일"]
[18,"서울","중부","수색S/S 154kV #65 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV #2M.Tr #1, 2DS 보통점검","2019-05-18 14:00","2019-05-18 18:00","2019-05-18 14:00","2019-05-18 18:00","당일"]
[19,"서울","중부","수색S/S 154kV #60 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색상암#1T/L #1, 2DS 및 Line DS 보통점검","2019-05-04 10:00","2019-05-04 14:00","2019-05-04 10:00","2019-05-04 14:00","당일"]
[20,"서울","중부","수색S/S 154kV #60 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색상암#2T/L #1, 2DS 및 Line DS 보통점검","2019-05-11 10:00","2019-05-11 14:00","2019-05-11 10:00","2019-05-11 14:00","당일"]
[21,"서울","중부","수색S/S 154kV #65 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색상암#2T/L #1, 2DS 및 Line DS 보통점검","2019-05-11 14:00","2019-05-11 18:00","2019-05-11 14:00","2019-05-11 18:00","당일"]
[22,"서울","중부","수색S/S 154kV #60 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV BUSTIE #1, 2DS보통점검","2019-05-25 10:00","2019-05-25 14:00","2019-05-25 10:00","2019-05-25 14:00","당일"]
[23,"서울","중부","수색S/S 154kV #60-#65 BUS TIE CB","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV BUS TIE #1, 2DS","2019-05-25 10:00","2019-05-25 18:00","2019-05-25 10:00","2019-05-25 18:00","당일"]
[24,"서울","중부","은평S/S 154kV 양주-은평#2T/L GIS","19년 중부전력지사 변전협력회사 총액공사","ㅇ은평S/S 154kV 양주은평#1T/L GIS 차단기 동작시험","2019-05-23 12:00","2019-05-23 15:00","2019-05-23 12:00","2019-05-23 15:00","당일"]
[25,"서울","중부","은평S/S 154kV 양주-은평#1T/L GIS","19년 중부전력지사 변전협력회사 총액공사","ㅇ은평S/S 154kV 양주은평#1T/L GIS 차단기 동작시험","2019-05-23 09:00","2019-05-23 12:00","2019-05-23 09:00","2019-05-23 12:00","당일"]
[26,"서울","중부","수색은평#1 T/L","154kV 원흥-수색T/L 지중화 정비공사","수색S/S ~ No.9 전력선 선종교체 - ACSR240, 330 → HSTACIR, ACMR 330 - 하단작업 대비 상단선로 휴전","2019-05-13 07:00","2019-05-15 18:00","2019-05-27 06:00","2019-05-31 18:00","연속"]
[27,"서울","중부","수색은평#2 T/L","154kV 원흥-수색T/L 지중화 정비공사","수색S/S ~ No.9 전력선 선종교체 - ACSR240, 330 → HSTACIR, ACMR 330 - 하단작업 대비 상단선로 휴전","2019-05-16 07:00","2019-05-18 18:00","2019-05-27 06:00","2019-05-31 18:00","연속"]
[28,"서울","중부","중부S/S 154kV #60-#61 SEC GIS","19년 중부전력지사 변전협력회사 총액공사","ㅇ154kV #60-#61 SEC GIS 보통점검","2019-05-07 09:00","2019-05-07 18:00","2019-05-07 09:00","2019-05-07 18:00","당일"]
[29,"서울","중부","중부S/S 154kV 중부-아현T/L GIS","19년 중부전력지사 변전협력회사 총액공사","ㅇ중부S/S 154kV 중부아현T/L GIS 차단기 동작시험","2019-05-20 09:00","2019-05-20 12:00","2019-05-20 09:00","2019-05-20 12:00","당일"]
[30,"서울","중부","중부S/S 154kV #61-#66 BUS TIE GIS","19년 중부전력지사 변전협력회사 총액공사","ㅇ154kV #61-#66 BUSTIE GIS 보통점검","2019-05-02 09:00","2019-05-02 18:00","2019-05-02 09:00","2019-05-02 18:00","당일"]
[31,"서울","중부","중부S/S 154kV #65-#66 SEC GIS","19년 중부전력지사 변전협력회사 총액공사","ㅇ154kV #65-#66 SEC GIS 보통점검","2019-05-08 09:00","2019-05-08 18:00","2019-05-08 09:00","2019-05-08 18:00","당일"]
[32,"서울","직할","중앙서소문 T/L","19년 직할 변전협력회사 총액공사","GIS 하자점검","2019-05-20 09:00","2019-05-20 18:00","2019-05-20 09:00","2019-05-20 18:00","당일"]
[33,"서울","직할","종로서소문 T/L","19년 직할 변전협력회사 총액공사","송전선로보호반 대체, GIS 하자점검","2019-05-15 09:00","2019-05-22 18:00","2019-05-15 09:00","2019-05-22 18:00","연속"]
[34,"서울","직할","서대문세종로 T/L","19년 직할 GIS 조작시험","GIS 조작시험","2019-05-02 09:00","2019-05-02 18:00","2019-05-02 09:00","2019-05-02 18:00","당일"]
[35,"남서울","강남","대치논현#2 T/L","변전설비 점검","변전설비 점검","2019-05-03 09:00","2019-05-03 18:00","2019-05-03 09:00","2019-05-03 18:00","당일"]
[36,"남서울","강남","대치논현#1 T/L","변전설비 점검","변전설비 점검","2019-05-02 09:00","2019-05-02 18:00","2019-05-02 09:00","2019-05-02 18:00","당일"]
[37,"남서울","동서울","가락S/S 154kV #1 BUS TIE CB","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-05-07 09:00","2019-05-09 18:00","2019-05-07 09:00","2019-05-09 18:00","연속"]
[38,"남서울","동서울","강동풍납#2 T/L","154kV 강동-풍납T/L 풍납S/S 인출구간 선종교체공사","선종교체 (OF케이블을 XLPE케이블로 교체)","2019-05-01 09:00","2019-06-15 18:00","2019-05-01 09:00","2019-06-15 18:00","연속"]
[39,"남서울","동서울","강동상일#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2019-05-10 09:00","2019-05-10 14:00","2019-05-10 09:00","2019-05-10 14:00","당일"]
[40,"남서울","동서울","강동상일#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2019-05-10 14:00","2019-05-10 18:00","2019-05-10 14:00","2019-05-10 18:00","당일"]
[41,"남서울","동서울","동서울신장#1 T/L","신장S/S 170kV 장기사용 GIS 교체공사","신장S/S 170kV 장기사용 GIS 교체공사","2019-05-01 09:00","2019-05-31 18:00","2019-05-01 09:00","2019-05-31 18:00","연속"]
[42,"남서울","동서울","동서울신장#2 T/L","신장S/S 170kV 장기사용 GIS 교체공사(#1BUS 무부하 가압용)","신장S/S 170kV 장기사용 GIS 교체공사(#1BUS 무부하 가압용)","2019-05-20 16:00","2019-05-20 18:00","2019-05-20 16:00","2019-05-20 18:00","당일"]
[43,"남서울","동서울","동서울신장#2 T/L","신장S/S 170kV 장기사용 GIS 교체공사(#2BUS 무부하 가압용)","신장S/S 170kV 장기사용 GIS 교체공사(#2BUS 무부하 가압용)","2019-05-06 16:00","2019-05-06 18:00","2019-05-06 16:00","2019-05-06 18:00","당일"]
[44,"남서울","영등포","신광명소래 T/L","154kV 신광명-소래T/L 피뢰기설치공사, 철탑정밀점검","- 154kV 신광명-소래T/L 5기(No.2,4,7,14,19) 피뢰기설치공사 - 철탑정밀점검","2019-05-06 07:00","2019-05-08 18:00","2019-05-25 07:00","2019-05-26 18:00","연속"]
[45,"남서울","영등포","화곡마곡#1 T/L","화곡-마곡#1T/L GIS 점검","마곡(하자점검) 화곡(보통점검)","2019-05-18 10:00","2019-05-18 18:00","2019-05-18 10:00","2019-05-18 18:00","당일"]
[46,"남서울","영등포","중동화곡#1 T/L","화곡S/S 154kV GIS 보통점검","CB 동작시간 측정 SF6가스 수분측정 CT 절연저항 측정","2019-05-11 10:00","2019-05-11 18:00","2019-05-11 10:00","2019-05-11 18:00","당일"]
[47,"남서울","영등포","화곡마곡#2 T/L","화곡-마곡#2T/L GIS 점검","마곡(하자점검) 화곡(보통점검)","2019-05-19 10:00","2019-05-19 18:00","2019-05-19 10:00","2019-05-19 18:00","당일"]
[48,"남서울","영등포","중동화곡#2 T/L","화곡S/S 154kV GIS 보통점검","CB 동작시간 측정 SF6가스 수분측정 CT 절연저항 측정","2019-05-12 10:00","2019-05-12 18:00","2019-05-12 10:00","2019-05-12 18:00","당일"]
[49,"남서울","직할","대림S/S 154kV #60 BUS","154kV 대림E/C GIS 설치공사","ㅇ 154kV GIS x 4CCT 설치 ㅇ 기타부대설비 1식 설치","2019-05-21 09:00","2019-05-31 18:00","2019-05-21 09:00","2019-05-31 18:00","연속"]
[50,"인천","인천","신경서서인천CC T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","신경서S/S 서인천CC신경서T/L GIS 정밀점검","2019-05-23 09:00","2019-05-25 18:00","2019-05-23 09:00","2019-05-25 18:00","연속"]
[51,"인천","인천","신경서경서#3T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압","신경서S/S 서인천CC신경서T/L 정밀점검 관련 무부하 가압(#65BUS 휴전 및 신경서경서#3T/L 이용) ","2019-05-25 12:00","2019-05-25 18:00","2019-05-25 12:00","2019-05-25 18:00","연속"]
[52,"인천","인천","신경서S/S 154kV #65 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압 ","신경서S/S 서인천CC신경서T/L 정밀점검 관련 무부하 가압(#65BUS 휴전 및 신경서경서#3T/L 이용) ","2019-05-25 12:00","2019-05-25 18:00","2019-05-25 12:00","2019-05-25 18:00","연속"]
[53,"인천","인천","신경서S/S 154kV #61 BUS","9년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압 ","신경서S/S 신경서청라#1T/L GIS 정밀점검 관련 무부하가압 ","2019-05-29 12:00","2019-05-29 18:00","2019-05-29 12:00","2019-05-29 18:00","연속"]
[54,"인천","인천","신경서경서#1T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압 ","신경서S/S 신경서청라#1T/L GIS 정밀점검 관련 무부하가압","2019-05-29 12:00","2019-05-29 18:00","2019-05-29 12:00","2019-05-29 18:00","연속"]
[55,"인천","인천","신가좌부개#2 T/L","신가좌부개#2T/L GIS 조작시험","신가좌S/S 신가좌부개#2T/L GIS 조작시험","2019-05-31 09:00","2019-05-31 18:00","2019-05-31 09:00","2019-05-31 18:00","당일"]
[56,"인천","인천","신가좌부개#1 T/L","신가좌부개#1T/L GIS 조작시험","신가좌S/S 신가좌부개#1T/L GIS 조작시험","2019-05-31 09:00","2019-05-31 18:00","2019-05-31 09:00","2019-05-31 18:00","당일"]
[57,"인천","시흥","도림오봉 T/L","154kV 도림분기(증) 지중T/L 건설공사","O 선종/회선길이 : XLPE 2500, 2회선*2.41km","2019-05-30 09:00","2019-06-10 18:00","2019-05-30 09:00","2019-06-10 18:00","연속"]
[58,"인천","김포","계양김포#1 T/L","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사 - 사유 : 불로지구 공동주택 신축공사 지장 - 공사시행 : 대광에이엠씨(요청자). 끝.","2019-05-27 09:00","2019-06-14 18:00","2019-05-27 09:00","2019-06-14 18:00","연속"]
[59,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사(화곡2,#1M.Tr,중동#2)","중동화곡#2t/L,#1M.Tr,신부평중동#2T/L 철거 및 상부BUS 설치","2019-05-26 14:00","2019-05-28 18:00","2019-05-26 14:00","2019-05-28 18:00","당일"]
[60,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사(화곡2,#1M.Tr,중동#2)","중동화곡#2t/L,#1M.Tr,신부평중동#2T/L 철거 및 상부BUS 설치","2019-05-24 09:00","2019-05-26 14:00","2019-05-24 09:00","2019-05-26 14:00","연속"]
[61,"인천","직할","중동화곡#2 T/L","중동S/S 170kV 인출GIS 정비공사(중동화곡#2T/L)","중동화곡#2t/L 철거 및 상부BUS 설치","2019-05-24 09:00","2019-06-05 18:00","2019-05-24 09:00","2019-06-05 18:00","연속"]
[62,"인천","직할","신부평중동#2 T/L","중동S/S 170kV 인출GIS 정비공사(신부평중동#2T/L)","신부평중동#2t/L 철거 및 상부BUS 설치","2019-05-24 09:00","2019-06-05 18:00","2019-05-24 09:00","2019-06-05 18:00","연속"]
[63,"인천","김포","김포S/S 154kV #2 BUS","154kV 계양-김포#2T/L 지장이설공사 준공시험","154kV 계양-김포#2T/L 지장이설공사 준공시험 - 상체크 등 시험. 끝.","2019-05-23 09:00","2019-05-23 18:00","2019-05-23 09:00","2019-05-23 18:00","당일"]
[64,"인천","시흥","서안양소래 T/L","154kV 서서울소래T/L OPGW 항공장애표시구 시설공사","154kV 서서울소래T/L(OPGW) 항공장애표시구 설치공사 - 설치구간 OPGW 1조 이므로 양회선 동시휴전 필요 - 서서울2소래(좌)-서서울2서안양(우), 서서울2소래(좌)-서안양소래(우)","2019-05-22 16:00","2019-05-22 18:00","2019-05-22 16:00","2019-05-22 18:00","당일"]
[65,"인천","직할","중동S/S 154kV #66 BUS","중동S/S 170kV 인출GIS 정비공사(6100,신부평중동#1T/L)","신부평중동#1T/L,6100BUS TIE 상체크 및 무부하가압","2019-05-22 11:00","2019-05-23 15:00","2019-05-22 11:00","2019-05-23 15:00","연속"]
[66,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사(6100,신부평중동#1T/L)","신부평중동#1T/L,6100BUS TIE 상체크 및 무부하가압","2019-05-22 11:00","2019-05-23 15:00","2019-05-22 11:00","2019-05-23 15:00","연속"]
[67,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사(6100,신부평중동#1T/L)","신부평중동#1T/L,6100BUS TIE 상체크 및 무부하가압","2019-05-22 09:00","2019-05-22 11:00","2019-05-22 09:00","2019-05-22 11:00","당일"]
[68,"인천","직할","중동S/S 154kV #61 BUS","중동S/S 170kV 인출GIS 정비공사(6100,신부평중동#1T/L)","신부평중동#1T/L,6100BUS TIE 상체크 및 무부하가압","2019-05-22 09:00","2019-05-22 11:00","2019-05-22 09:00","2019-05-22 11:00","당일"]
[69,"인천","김포","양곡S/S 154kV #65 BUS","김포전력지사 154kV GIS 정밀점검공사","양곡S/S 154kV 양촌-양곡#2T/L 642DS 내부점검","2019-05-21 14:00","2019-05-22 18:00","2019-05-21 14:00","2019-05-22 18:00","연속"]
[70,"인천","시흥","서서울#2소래 T/L","154kV 서서울2-소래T/L 일진제 R-type PMJ교체공사","154kV 서서울2-소래T/L 일진제 R-type PMJ교체공사","2019-05-21 09:00","2019-05-27 18:00","2019-05-21 09:00","2019-05-27 18:00","연속"]
[71,"인천","김포","양곡S/S 154kV #60 BUS","김포전력지사 154kV GIS 정밀점검공사","양곡S/S 154kV 양촌-양곡#2T/L 641DS 내부점검","2019-05-20 09:00","2019-05-21 14:00","2019-05-20 09:00","2019-05-21 14:00","연속"]
[72,"인천","직할","신부평고강#2 T/L","154kV 신부평-고강#2T/L EBA 자기애관 교체공사","EBA 애관 교체 (자기애관 → 폴리머애관)","2019-05-19 09:00","2019-05-19 18:00","2019-05-19 09:00","2019-05-19 18:00","당일"]
[73,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강#1T/L EBA PD진단용 집합반 설치공사","철탑(강관주)형 EBA PD진단용 집합반 설치","2019-05-18 09:00","2019-05-18 18:00","2019-05-18 09:00","2019-05-18 18:00","당일"]
[74,"인천","시흥","신시흥#1S/S 154kV #60-#65 BUS TIE GIS","신시흥#1S/S 170kV #60-#65 BUS TIE GIS 동작점검","신시흥#1S/S 170kV #60-#65 BUS TIE GIS 동작점검","2019-05-17 14:00","2019-05-17 18:00","2019-05-17 14:00","2019-05-17 18:00","당일"]
[75,"인천","인천","인천CC북인천#1 T/L","인천복합S/Y 154㎸ GIS 미사용 접속설비 철거공사","6133, 6333 GIS 철거 관련 61BUS 모선 시험가압","2019-05-16 18:00","2019-05-17 18:00","2019-05-16 18:00","2019-05-17 18:00","연속"]
[76,"인천","인천","인천CC S/Y 154kV #61-#66 BUS TIE GIS","인천복합S/Y 154㎸ GIS 미사용 접속설비 철거공사","6133, 6333 GIS 철거 관련 61BUS 모선 시험가압","2019-05-16 18:00","2019-05-17 18:00","2019-05-16 18:00","2019-05-17 18:00","연속"]
[77,"인천","김포","양곡S/S 154kV #65 BUS","김포전력지사 154kV GIS 정밀점검공사","양곡S/S 154kV #4M.Tr 6432DS 내부점검","2019-05-16 16:00","2019-05-17 18:00","2019-05-16 16:00","2019-05-17 18:00","연속"]
[78,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사(6100,신부평중동#1T/L)","신부평중동#1T/L,6100BUS TIE 철거 및 상부BUS설치","2019-05-16 14:00","2019-05-18 18:00","2019-05-16 14:00","2019-05-18 18:00","당일"]
[79,"인천","김포","김포S/S 154kV #1 BUS","154kV 계양-김포#2T/L 지장이설공사 준공시험","154kV 계양-김포#2T/L 지장이설공사 준공시험 - 상체크 등 시험. 끝.","2019-05-16 09:00","2019-05-16 18:00","2019-05-16 09:00","2019-05-16 18:00","당일"]
[80,"인천","김포","양곡S/S 154kV #60 BUS","김포전력지사 154kV GIS 정밀점검공사","양곡S/S 154kV #4M.Tr 6431DS 내부점검","2019-05-15 14:00","2019-05-16 16:00","2019-05-15 18:00","2019-05-16 16:00","연속"]
[81,"인천","김포","양곡S/S 154kV #65 BUS","김포전력지사 154kV GIS 정밀점검공사","양곡S/S 154kV #3M.Tr 6332DS 내부점검","2019-05-14 14:00","2019-05-15 18:00","2019-05-14 14:00","2019-05-15 18:00","연속"]
[82,"인천","인천","신가좌인천#2 T/L","신가좌인천#2T/L 휴전","신가좌S/S 신가좌인천#2T/L GIS 조작시험 인천S/S 신가좌인천#2T/L GIS 조작시험","2019-05-14 09:00","2019-05-14 18:00","2019-05-13 09:00","2019-05-13 18:00","당일"]
[83,"인천","인천","신현포스코CC#2 T/L","SVL 교체공사","구형 SVL을 신형SVL로 교체(난연성 확보)","2019-05-14 09:00","2019-05-17 18:00","2019-05-14 09:00","2019-05-17 18:00","연속"]
[84,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사(6100,신부평중동#1T/L)","신부평중동#1T/L,6100BUS TIE 철거 및 상부BUS설치","2019-05-14 09:00","2019-05-16 14:00","2019-05-14 09:00","2019-05-16 14:00","연속"]
[85,"인천","직할","신부평중동#1 T/L","중동S/S 170kV 인출GIS 정비공사(신부평중동#1T/L)","신부평중동#1T/L 철거 및 상부BUS설치","2019-05-14 09:00","2019-05-23 18:00","2019-05-14 09:00","2019-05-23 18:00","연속"]
[86,"인천","직할","중동S/S 154kV #1 BUS TIE CB","중동S/S 170kV 인출GIS 정비공사(6100BUSTIE)","6100BUS TIE 철거 및 신설 BUS TIE 제어,감시케이블 결선, 보호케이블 포설 및 결선 작업","2019-05-14 09:00","2019-05-23 18:00","2019-05-14 09:00","2019-05-23 18:00","연속"]
[87,"인천","김포","양곡S/S 154kV #60 BUS","김포전력지사 154kV GIS 정밀점검공사","양곡S/S 154kV #3M.Tr 6331DS 내부점검","2019-05-13 09:00","2019-05-14 14:00","2019-05-13 09:00","2019-05-14 14:00","연속"]
[88,"인천","인천","인천T/P 154kV #61 BUS","인천복합S/Y 154㎸ GIS 미사용 접속설비 철거공사","6133, 6333 GIS #1DS 철거 관련 모선 휴전","2019-05-13 09:00","2019-05-17 18:00","2019-05-13 09:00","2019-05-17 18:00","연속"]
[89,"인천","인천","인천CC북인천#1 T/L","인천복합S/Y 154㎸ GIS 미사용 접속설비 철거공사","6133, 6333 GIS 철거 관련 66BUS 모선 시험가압","2019-05-11 18:00","2019-05-12 18:00","2019-05-11 18:00","2019-05-12 18:00","연속"]
[90,"인천","인천","인천CC S/Y 154kV #61-#66 BUS TIE GIS","인천복합S/Y 154㎸ GIS 미사용 접속설비 철거공사","6133, 6333 GIS 철거 관련 66BUS 모선 시험가압","2019-05-11 18:00","2019-05-12 18:00","2019-05-11 18:00","2019-05-12 18:00","연속"]
[91,"인천","시흥","학익연수#2 T/L","연수S/S 170kV 학익연수#2T/L GIS 하자점검","연수S/S 170kV 학익연수#2T/L GIS 하자점검","2019-05-10 14:00","2019-05-10 18:00","2019-05-10 14:00","2019-05-10 18:00","당일"]
[92,"인천","직할","중동S/S 154kV #66 BUS","중동S/S 170kV 인출GIS 정비공사(#1G/T)","#1G/T GIS 상체크 시험 및 무부하조작","2019-05-10 11:00","2019-05-11 15:00","2019-05-10 11:00","2019-05-11 15:00","연속"]
[93,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사(#1G/T)","#1G/T GIS 상체크 시험 및 무부하조작","2019-05-10 11:00","2019-05-11 15:00","2019-05-10 11:00","2019-05-11 15:00","연속"]
[94,"인천","시흥","학익연수#1 T/L","연수S/S 170kV 학익연수#1T/L GIS 하자점검","연수S/S 170kV 학익연수#1T/L GIS 하자점검","2019-05-10 10:00","2019-05-10 14:00","2019-05-10 10:00","2019-05-10 14:00","당일"]
[95,"인천","시흥","신시흥도림 T/L","154kV 도림분기(증) 지중T/L 건설공사","O 선종/회선길이 : XLPE 2500, 2회선*2.41km","2019-05-10 09:00","2019-05-17 18:00","2019-05-10 09:00","2019-05-17 18:00","연속"]
[96,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사(#1G/T GIS)","#1G/T GIS 상체크 시험 및 무부하조작","2019-05-10 09:00","2019-05-10 11:00","2019-05-10 09:00","2019-05-10 11:00","당일"]
[97,"인천","직할","중동S/S 154kV #61 BUS","중동S/S 170kV 인출GIS 정비공사(#1G/T)","#1G/T GIS 상체크 시험 및 무부하조작","2019-05-10 09:00","2019-05-10 11:00","2019-05-10 09:00","2019-05-10 11:00","당일"]
[98,"인천","직할","신부평중동#3 T/L","중동S/S 170kV 인출GIS 정비공사(#1G/T)","#1G/T GIS 상체크 시험 및 무부하조작","2019-05-10 09:00","2019-05-11 15:00","2019-05-10 09:00","2019-05-11 15:00","연속"]
[99,"인천","김포","양곡S/S 154kV #65 BUS","김포전력지사 154kV GIS 정밀점검공사","양곡S/S 154kV #2M.Tr 6232DS 내부점검","2019-05-08 14:00","2019-05-09 18:00","2019-05-08 14:00","2019-05-09 18:00","연속"]
[100,"인천","인천","인천T/P 154kV #66 BUS","인천복합S/Y 154㎸ GIS 미사용 접속설비 철거공사","6133, 6333 GIS #2DS 철거 관련 모선 휴전","2019-05-08 09:00","2019-05-12 18:00","2019-05-08 09:00","2019-05-12 18:00","연속"]
[101,"인천","직할","부개원미#2 T/L","부개S/S 부개-원미#2T/L GIS 보통점검","부개S/S 부개-원미#2T/L GIS 보통점검 원미S/S 부개-원미#2T/L GIS 보통점검(병행)","2019-05-08 09:00","2019-05-08 18:00","2019-05-08 09:00","2019-05-08 18:00","연속"]
[102,"인천","시흥","신시흥북시화#2 T/L","신시흥#1S/S 신시흥북시화#2T/L 초기점검","신시흥#1S/S 신시흥북시화#2T/L 초기점검","2019-05-07 14:00","2019-05-07 18:00","2019-05-07 14:00","2019-05-07 18:00","당일"]
[103,"인천","시흥","신시흥북시화#1 T/L","신시흥#1S/S 신시흥북시화#1T/L 초기점검","신시흥#1S/S 신시흥북시화#1T/L 초기점검","2019-05-07 10:00","2019-05-07 14:00","2019-05-07 10:00","2019-05-07 14:00","당일"]
[104,"인천","김포","계양김포#2 T/L","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사","154kV 계양-김포T/L M/H#3~김포C/H 지장이설공사 - 사유 : 불로지구 공동주택 신축공사 지장 - 공사시행 : 대광에이엠씨(요청자). 끝.","2019-05-07 09:00","2019-05-24 18:00","2019-05-07 09:00","2019-05-24 18:00","연속"]
[105,"인천","김포","양곡S/S 154kV #60 BUS","김포전력지사 154kV GIS 정밀점검공사","양곡S/S 154kV #2M.Tr 6231DS 내부점검","2019-05-07 09:00","2019-05-08 14:00","2019-05-07 09:00","2019-05-08 14:00","연속"]
[106,"인천","인천","신경서영종 T/L","신경서,영종S/S 신경서영종T/L 보호반 대체공사","신경서S/S 신경서영종T/L 보호반 대체 영종S/S 신경서영종T/L 보호반 대체 신경서S/S 신경서영종T/L 보통점검 및 보조계전기 교체공사 영종S/S 신경서영종T/L 보통점검","2019-05-07 09:00","2019-05-11 18:00","2019-05-07 09:00","2019-05-11 18:00","연속"]
[107,"인천","인천","신현포스코CC#1 T/L","SVL 교체공사","구형 SVL을 신형 SVL로 교체(난연성 확보)","2019-05-07 09:00","2019-05-10 18:00","2019-05-07 09:00","2019-05-10 18:00","연속"]
[108,"인천","인천","인천CC S/Y 345kV #1,2 SU Tr 1차 GIS","인천복합S/Y 154㎸ GIS 미사용 접속설비 철거공사","6133, 6333 GIS 철거","2019-05-07 09:00","2019-05-17 18:00","2019-05-07 09:00","2019-05-17 18:00","연속"]
[109,"인천","인천","인천CC S/Y 345kV #1 M.Tr 1차 GIS","인천복합S/Y 154㎸ GIS 미사용 접속설비 철거공사","6133, 6333 GIS 철거","2019-05-07 09:00","2019-05-17 18:00","2019-05-07 09:00","2019-05-17 18:00","연속"]
[110,"인천","직할","부개원미#1 T/L","부개S/S 부개-원미#1T/L GIS 보통점검","부개S/S 부개-원미#1T/L GIS 보통점검 원미S/S 부개-원미#1T/L GIS 보통점검(병행)","2019-05-07 09:00","2019-05-07 18:00","2019-05-07 09:00","2019-05-07 18:00","연속"]
[111,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 - #1G/T GIS 인출 정비공사","2019-05-05 14:00","2019-05-08 18:00","2019-05-05 14:00","2019-05-08 18:00","당일"]
[112,"인천","직할","신부평S/S 154kV #61 BUS","신부평S/S 신부평청천#1T/L 170kV GIS 정밀점검(#61BUS)","신부평S/S 신부평청천#1T/L 170kV GIS 정밀점검(무부하가압용)","2019-05-04 10:00","2019-05-04 16:00","2019-05-04 10:00","2019-05-04 16:00","당일"]
[113,"인천","직할","중동S/S #1 G/T GIS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 - #1G/T GIS 인출 정비공사","2019-05-04 09:00","2019-05-13 18:00","2019-05-04 09:00","2019-05-13 18:00","연속"]
[114,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 - #1G/T GIS 인출 정비공사","2019-05-04 09:00","2019-05-05 14:00","2019-05-04 09:00","2019-05-05 14:00","연속"]
[115,"인천","시흥","도림오봉 T/L","154kV 도림분기 SW 증설공사","- 154kV GIS 2CCT 설치 - 송전선로 보호반 4면(도림2, 신시흥1, 오봉1) - 기타 부대작업 1식. 끝.","2019-05-03 09:00","2019-05-05 18:00","2019-05-03 09:00","2019-05-05 18:00","연속"]
[116,"인천","김포","양곡S/S 154kV #65 BUS","김포전력지사 154kV GIS 정밀점검공사","양곡S/S 154kV #1M.Tr 6132DS 내부점검","2019-05-02 16:00","2019-05-03 18:00","2019-05-02 16:00","2019-05-03 18:00","연속"]
[117,"인천","인천","신가좌인천#3 T/L","신가좌인천#3 T/L GIS 압력게이지 보수","신가좌인천#3 T/L GIS 압력게이지 보수","2019-05-02 09:00","2019-05-02 18:00","2019-05-02 09:00","2019-05-02 18:00","당일"]
[118,"인천","김포","양곡S/S 154kV #60 BUS","김포전력지사 154kV GIS 정밀점검공사","양곡S/S 154kV #1M.Tr 6131DS 내부점검","2019-05-01 14:00","2019-05-02 16:00","2019-05-01 14:00","2019-05-02 16:00","연속"]
[119,"인천","직할","신부평부흥#2 T/L","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검(#66BUS)","신부평S/S 신부평중동#1T/L 170kV GIS 정밀점검(DS 점검 및 무부하가압용)","2019-05-01 10:00","2019-05-01 14:00","2019-05-01 10:00","2019-05-01 14:00","당일"]
[120,"경기북부","고양","양주고양#1 T/L","서울문산고속도로 지장철탑이설 관련 OPGW이설공사 안전조치","공사대상 : 154kV 신덕은-원흥#1,2T/L No.13-16 4회선구간 안전조치 필요 안전조치 구간 : 154kV 양주-고양T/L No.29(154kV 신덕은-원흥T/L No.16)","2019-05-25 07:00","2019-05-26 18:00","2019-05-25 07:00","2019-05-26 18:00","연속"]
[121,"경기북부","고양","양주불광#2 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 양주-불광#2T/L No.1-15 정밀점검 시행","2019-05-02 07:00","2019-05-03 18:00","2019-05-04 07:00","2019-05-05 18:00","연속"]
[122,"경기북부","고양","신덕은원흥#1 T/L","154kV 신덕은-원흥T/L 송전용량증대 전력선교체공사","ㅇ 전선교체 : 12.03km - No.10~13, 17~30, 39~60) - 교체전선 : ACSR 330/240㎟ ⇒ ASCC 430㎟","2019-05-20 07:00","2019-06-09 18:00","2019-05-20 07:00","2019-06-09 18:00","연속"]
[123,"경기북부","고양","신덕은원흥#2 T/L","154kV 신덕은-원흥T/L 송전용량증대 전력선교체공사","ㅇ 전선교체 : 12.03km - No.10~13, 17~30, 39~60) - 교체전선 : ACSR 330/240㎟ ⇒ ASCC 430㎟","2019-05-20 07:00","2019-06-09 18:00","2019-05-20 07:00","2019-06-09 18:00","연속"]
[124,"경기북부","고양","신파주문발#1 T/L","파주운정3지구 지장송전선로 지중화공사","- 공사구간 : 154kV 신파주-문발#1,2T/L J/B#1∼#6 2.012km - 선종 및 선로길이 : XLPE 2500㎟×2C 0.801km / XLPE 2000㎟(D)×2C 1.211km","2019-05-20 08:00","2019-06-30 18:00","2019-05-20 08:00","2019-06-30 18:00","연속"]
[125,"경기북부","고양","원흥수색#2 T/L","154kV 원흥-수색T/L 지중화 정비공사","수색S/S ~ No.9 전력선 선종교체 - ACSR240, 330 → HSTACIR, ACMR 330","2019-05-13 06:00","2019-05-17 18:00","2019-05-13 06:00","2019-05-17 18:00","연속"]
[126,"경기북부","고양","원흥수색#1 T/L","154kV 원흥-수색T/L 지중화 정비공사","수색S/S ~ No.9 전력선 선종교체 - ACSR240, 330 → HSTACIR, ACMR 330","2019-05-13 06:00","2019-05-17 18:00","2019-05-13 06:00","2019-05-17 18:00","연속"]
[127,"경기북부","고양","월롱금촌#1 T/L","154kV 월롱-금촌#1T/L 지장송전선로 이설공사","154kV 월롱-금촌#1T/L No.3-6,10-14 지장이설공사","2019-05-06 06:00","2019-05-14 18:00","2019-05-12 06:00","2019-05-20 18:00","연속"]
[128,"경기북부","고양","월롱금촌#2 T/L","154kV 월롱-금촌#2T/L 지장송전선로 이설공사","154kV 월롱-금촌#2T/L No.3-6,10-14 지장이설공사","2019-05-15 06:00","2019-05-19 18:00","2019-05-21 06:00","2019-05-25 18:00","연속"]
[129,"경기북부","구리","덕소진건#2 T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업 154kV 덕소-진건#2T/L, 154kV 덕소-마석#2T/L 동시휴전작업으로 신설 덕소S/S 계통병입 및 부하절체","2019-05-20 09:00","2019-06-22 18:00","2019-05-30 09:00","2019-06-29 18:00","연속"]
[130,"경기북부","구리","덕소마석#2 T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업 154kV 덕소-진건#2T/L, 154kV 덕소-마석#2T/L 동시휴전작업으로 신설 덕소S/S 계통병입 및 부하절체","2019-05-20 09:00","2019-06-22 18:00","2019-05-30 09:00","2019-06-29 18:00","연속"]
[131,"경기북부","구리","미금광장 T/L","154kV 화양T/L 지장송전선로 이설공사","154kV 화양T/L No.18(구) 철탑 이설(1기철거, 1기 신설) 및 전선작업","2019-05-11 06:00","2019-05-12 18:00","2019-05-11 06:00","2019-05-12 18:00","연속"]
[132,"경기북부","구리","미금광장 T/L","154kV 화양T/L 지장송전선로 이설공사","154kV 화양T/L No.18(구) 철탑 이설(1기철거, 1기 신설) 및 전선작업","2019-05-16 06:00","2019-05-18 18:00","2019-05-16 06:00","2019-05-18 18:00","연속"]
[133,"경기북부","구리","미금화양 T/L","154kV 화양T/L 지장송전선로 이설공사","154kV 화양T/L No.18(구) 철탑 이설(1기철거, 1기 신설) 및 전선작업","2019-05-11 06:00","2019-05-15 18:00","2019-05-11 06:00","2019-05-15 18:00","연속"]
[134,"경기북부","구리","별내도봉 T/L","154kV 별내-도봉T/L 송전선로 정밀점검","- No.1(C/H) ~ 도봉S/S 철탑 22기 송전선로 정밀점검","2019-05-16 08:30","2019-05-17 18:00","2019-05-16 08:30","2019-05-17 18:00","연속"]
[135,"경기북부","구리","신의정부송우#1 T/L","154kV 신의정부-송우T/L No.48 안전이격거리확보공사","지지물 1기 설치/ 1기 철거, 전력선 2C-km, 0.658km 교체","2019-05-11 09:00","2019-05-14 18:00","2019-05-11 09:00","2019-05-14 18:00","연속"]
[136,"경기북부","구리","옥정송우#1 T/L","154kV 신의정부-송우T/L No.48 안전이격거리확보공사","지지물 1기 설치/ 1기 철거, 전력선 2C-km, 0.658km 교체 (하단 병가선로 휴전필요)","2019-05-12 09:00","2019-05-12 18:00","2019-05-12 09:00","2019-05-12 18:00","연속"]
[137,"경기북부","구리","옥정송우#2 T/L","154kV 신의정부-송우T/L No.48 안전이격거리확보공사","지지물 1기 설치/ 1기 철거, 전력선 2C-km, 0.658km 교체 (하단 병가선로 휴전필요)","2019-05-12 09:00","2019-05-17 18:00","2019-05-12 09:00","2019-05-17 18:00","연속"]
[138,"경기북부","구리","신의정부송우#2 T/L","154kV 신의정부-송우T/L No.48 안전이격거리확보공사","지지물 1기 설치/ 1기 철거, 전력선 2C-km, 0.658km 교체","2019-05-15 09:00","2019-05-17 18:00","2019-05-15 09:00","2019-05-17 18:00","연속"]
[139,"경기북부","구리","신의정부송우#2 T/L","154kV 신의정부-송우T/L No.48 안전이격거리확보공사","지지물 1기 설치/ 1기 철거, 전력선 2C-km, 0.658km 교체","2019-05-11 09:00","2019-05-11 18:00","2019-05-11 09:00","2019-05-11 18:00","연속"]
[140,"경기북부","구리","신포천포천#1 T/L","'18~'19년 경기북부직할 가공송전 정비회사 총액공사","○ 압축인류클램프 교체(No.1,11,14) ○ SB 댐퍼 철거(신포천S/S)","2019-05-07 08:00","2019-05-07 18:00","2019-05-07 08:00","2019-05-07 18:00","당일"]
[141,"경기북부","구리","신포천전곡#1 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사 - 154kV 신포천-전곡#1T/L 2경간 항공구 설치","2019-05-22 08:00","2019-05-23 18:00","2019-05-22 08:00","2019-05-23 18:00","연속"]
[142,"경기북부","구리","신포천덕계#2 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사 - 154kV 신포천-덕계#2T/L 2경간 항공구 설치","2019-05-22 08:00","2019-05-23 18:00","2019-05-22 08:00","2019-05-23 18:00","연속"]
[143,"경기북부","구리","신포천덕계#1 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사 - 154kV 신포천-덕계#1T/L 2경간 항공구 설치","2019-05-20 08:00","2019-05-21 18:00","2019-05-20 08:00","2019-05-21 18:00","연속"]
[144,"경기북부","구리","신포천전곡#2 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사 - 154kV 신포천-전곡#2T/L 2경간 항공구 설치","2019-05-20 08:00","2019-05-21 18:00","2019-05-20 08:00","2019-05-21 18:00","연속"]
[145,"경기북부","구리","신포천동두천#1 T/L","'18~'19년 경기북부직할 가공송전 정비회사 총액공사","○ 피뢰기 설치(No.1-5) ○ 압축인류클램프 교체(No.1,11,14) ○ SB 댐퍼 철거(신포천S/S)","2019-05-02 08:00","2019-05-03 18:00","2019-05-02 08:00","2019-05-03 18:00","연속"]
[146,"경기북부","구리","신포천포천#2 T/L","'18~'19년 경기북부직할 가공송전 정비회사 총액공사","○ 피뢰기 설치(No.1-5) ○ 압축인류클램프 교체(No.1,11,14) ○ SB 댐퍼 철거(신포천S/S)","2019-05-02 08:00","2019-05-03 18:00","2019-05-02 08:00","2019-05-03 18:00","연속"]
[147,"경기북부","구리","신포천동두천#2 T/L","'18~'19년 경기북부직할 가공송전 정비회사 총액공사","○ 피뢰기 설치(No.44-56) 압축인류클램프 교체(No.1,11,14)","2019-05-07 08:00","2019-05-09 18:00","2019-05-07 08:00","2019-05-09 18:00","연속"]
[148,"경기북부","구리","진건별내#1 T/L","154kV 덕소S/S 옥내화 사업 최초가압","덕소S/S 옥내화 최초가압 선로 휴전신청","2019-05-09 09:00","2019-05-10 18:00","2019-05-09 09:00","2019-05-10 18:00","연속"]
[149,"경기북부","구리","진접S/S 154kV #60-#65 BUS TIE CB","진접S/S 154kV #1 BUS TIE GIS 보통점검공사","진접S/S 154kV #1 BUS TIE GIS 보통점검공사","2019-05-07 09:00","2019-05-07 18:00","2019-05-07 09:00","2019-05-07 18:00","당일"]
[150,"경기북부","구리","청평H/P 154kV #3 M.Tr 2차 CB","19년도 구리전력지사 GIS/GCB 정밀점검공사","19년도 구리전력지사 GIS/GCB 정밀점검공사","2019-05-01 09:00","2019-05-02 18:00","2019-05-01 09:00","2019-05-02 18:00","연속"]
[151,"경기북부","구리","청평P/P 154KV #2 M.Tr 2차 CB","청평P/P 154kV #2M.Tr 2차 GCB 보통점검공사","청평P/P 154kV #2M.Tr 2차 GCB 보통점검공사","2019-05-07 09:00","2019-05-07 18:00","2019-05-07 09:00","2019-05-07 18:00","당일"]
[152,"경기북부","구리","팔당H/P 154kV #2 M.Tr 1차 CB","팔당H/P 154kV #2M.Tr 1차 GIS 보통점검공사","팔당H/P 154kV #2M.Tr 1차 GIS 보통점검공사","2019-05-14 09:00","2019-05-14 18:00","취소","취소","당일"]
[153,"경기북부","구리","팔당H/P 154kV #1 M.Tr 1차 CB","팔당H/P 154kV #1M.Tr 1차 GIS 보통점검공사","팔당H/P 154kV #1M.Tr 1차 GIS 보통점검공사","2019-05-13 09:00","2019-05-13 18:00","취소","취소","당일"]
[154,"경기북부","직할","금오상계#1 T/L","2019년 가공송전선로 순시점검 위탁공사","○ 정밀점검 (No.1-30)","2019-05-27 08:00","2019-05-31 18:00","취소","취소","연속"]
[155,"경기북부","직할","금오상계#1 T/L","2019년 가공송전선로 순시점검 위탁공사","○ 정밀점검 (No.1-30)","2019-05-20 08:00","2019-05-24 18:00","취소","취소","연속"]
[156,"경기북부","직할","도봉방학#2 T/L","'19년도 직할 변전정비회사 총액공사","도봉S/S 154kV 도봉-방학 #2 T/L GCB 개폐타임 측정","2019-05-13 14:00","2019-05-13 18:00","2019-05-13 14:00","2019-05-13 18:00","당일"]
[157,"경기북부","직할","도봉방학#1 T/L","'19년도 직할 변전정비회사 총액공사","도봉S/S 154kV 도봉-방학 #1 T/L GCB 개폐타임 측정","2019-05-13 09:00","2019-05-13 14:00","2019-05-13 09:00","2019-05-13 14:00","당일"]
[158,"경기북부","직할","백석덕계#1 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사 - 154kV 백석-덕계#1T/L 1경간 항공구 설치","2019-05-02 08:00","2019-05-02 18:00","2019-05-02 08:00","2019-05-02 18:00","당일"]
[159,"경기북부","직할","백석덕계#2 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사 - 154kV 백석-덕계#2T/L 1경간 항공구 설치","2019-05-03 08:00","2019-05-03 18:00","2019-05-03 08:00","2019-05-03 18:00","당일"]
[160,"경기북부","직할","녹양백석#1 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사 - 154kV 백석-덕계#2T/L 1경간 항공구 설치 - 154kV 하단병가선로 녹양-백석#1T/L 43RC Off","2019-05-03 08:00","2019-05-03 18:00","2019-05-03 08:00","2019-05-03 18:00","당일"]
[161,"경기북부","직할","녹양백석#2 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사 - 154kV 백석-덕계#1T/L 1경간 항공구 설치 - 154kV 하단병가선로 녹양-백석#2T/L 43RC Off","2019-05-02 08:00","2019-05-02 18:00","2019-05-02 08:00","2019-05-02 18:00","당일"]
[162,"경기북부","직할","양주은평#1 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 양주-불광#2T/L No.1-15 정밀점검 시행 (병가선로 휴전 : 양주-은평#1T/L No.2-12)","2019-05-02 07:00","2019-05-03 18:00","2019-05-04 07:00","2019-05-05 18:00","연속"]
[163,"경기북부","직할","양주S/S 154kV #60-#65 BUS TIE GIS","'19년도 직할 변전정비회사 총액공사","양주S/S 154kV #1 BUS-TIE GIS 개폐타임 측정","2019-05-01 09:00","2019-05-01 14:00","2019-05-01 09:00","2019-05-01 14:00","당일"]
[164,"경기북부","직할","양주금촌#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주-금촌#1T/L 인출측 전력구공사","2019-05-08 09:00","2019-05-09 18:00","2019-05-08 09:00","2019-05-09 18:00","연속"]
[165,"경기북부","직할","양주금촌#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주-금촌#2T/L 인출측 전력구공사","2019-05-06 09:00","2019-05-07 18:00","2019-05-06 09:00","2019-05-07 18:00","연속"]
[166,"경기북부","직할","양주S/S 154kV #66-#67 SEC GIS","'19년도 직할 변전정비회사 총액공사","양주S/S 154kV #66-67 GIS 개폐타임 측정","2019-05-10 16:00","2019-05-10 18:00","2019-05-02 15:00","2019-05-02 18:00","당일"]
[167,"경기북부","직할","양주S/S 154kV #62-#67 BUS TIE GIS","'19년도 직할 변전정비회사 총액공사","양주S/S 154kV #3 BUS-TIE GIS 개폐타임 측정","2019-05-10 09:00","2019-05-10 14:00","2019-05-10 09:00","2019-05-10 14:00","당일"]
[168,"경기북부","직할","양주S/S 154kV #60 BUS","18~19 직할 변전정비회사 총액공사","#60 BUS CVT, LA 보통점검","2019-05-07 09:30","2019-05-07 18:00","2019-05-07 09:30","2019-05-07 18:00","당일"]
[169,"경기북부","직할","양주S/S SVC M.Tr 1차 GIS","'19년 변전협력회사 총액공사","개폐타임측정","2019-05-02 09:00","2019-05-02 14:00","2019-05-02 09:00","2019-05-02 14:00","당일"]
[170,"경기북부","직할","양주S/S 154kV #61-#66 BUS TIE GIS","'19년도 직할 변전정비회사 총액공사","양주S/S 154kV #2 BUS-TIE GIS 개폐타임 측정","2019-05-01 14:00","2019-05-01 18:00","2019-05-02 09:00","2019-05-02 12:00","당일"]
[171,"경기북부","직할","용현도봉#1 T/L","2019년 가공송전선로 순시점검 위탁공사","○ 정밀점검 (No.1-36)","2019-05-27 08:00","2019-05-31 18:00","취소","취소","연속"]
[172,"경기북부","직할","용현도봉#2 T/L","2019년 가공송전선로 순시점검 위탁공사","○ 정밀점검 (No.1-36)","2019-05-20 08:00","2019-05-24 18:00","취소","취소","연속"]
[173,"경기북부","직할","양주S/S 154kV #65 BUS","18~19년도 직할 변전정비회사 총액공사","154kV #65 BUS CVT, LA 보통점검","2019-05-01 09:00","2019-05-01 14:00","2019-05-03 09:00","2019-05-03 18:00","연속"]
[174,"경기북부","직할","양주S/S 154kV #66 BUS","18~19년도 직할 변전정비회사 총액공사","154kV #66 BUS CVT, LA 보통점검","2019-05-01 14:00","2019-05-01 18:00","2019-05-02 09:00","2019-05-02 18:00","연속"]
[175,"경기북부","구리","미금덕소#1 T/L","장기사용 자기애자 교체공사(안전이격확보)","장기사용 자기애자 교체공사(안전이격확보)","2019-05-07 07:00","2019-05-07 18:00","2019-05-07 07:00","2019-05-07 18:00","연속"]
[176,"경기북부","구리","마석청평HP#1 T/L","154kV 덕소S/S 옥내화 사업 최초가압","덕소S/S 옥내화 최초가압 선로 휴전신청","2019-05-09 09:00","2019-05-10 18:00","2019-05-09 09:00","2019-05-10 18:00","연속"]
[177,"경기","군포","화성남양#2 T/L","345kV 신안산분기T/L OPGW시설공사","공사장소 : 화성S/S-No.2~No.56~신안산S/S 시설내역: OPGW 120㎟ 24C SM 17.566km, 48C SM 4.113㎞ 시설","2019-05-04 09:00","2019-05-05 18:00","2019-05-04 09:00","2019-05-05 18:00","연속"]
[178,"경기","군포","사강S/S 154kV 남양-사강#1T/L GIS","사강S/S 154kV #1 Sh.C 대체공사(무부하 가압용)","사강S/S 154kV #1 Sh.C 대체공사(무부하 가압용)","2019-05-16 09:00","2019-05-17 18:00","2019-05-16 09:00","2019-05-17 18:00","연속"]
[179,"경기","군포","서서울#2남수원 #1T/L","154kV 봉담E/C 건설공사","- 남수원-봉담T/L 가선작업 및 보호배전반 대체","2019-05-28 09:00","2019-06-17 18:00","2019-05-28 09:00","2019-06-17 18:00","연속"]
[180,"경기","군포","서서울#2소래 T/L","154kV 신광명-소래T/L 피뢰기설치공사,철탑정밀점검(병가선로 휴전)","154kV 신광명-소래T/L 5기(No.2,4,7,14,19) 피뢰기설치공사(병가선로 휴전) -철탑정밀점검","2019-05-06 07:00","2019-05-08 18:00","취소","취소","연속"]
[181,"경기","군포","서서울#2남수원 #1T/L","154kV 서서울2-남수원T/L 40,42호 안전이격확보공사","철탑교체(인클로징공법) : 2기, 철거 :1기, 전선교체 : 1.039km","2019-05-14 07:30","2019-05-16 18:00","2019-05-14 07:30","2019-05-16 18:00","연속"]
[182,"경기","군포","서서울#2남수원 #2T/L","154kV 서서울2-남수원T/L 40,42호 안전이격확보공사","철탑교체(인클로징공법) : 2기, 철거 :1기, 전선교체 : 1.039km","2019-05-17 07:30","2019-05-27 18:00","2019-05-17 07:30","2019-05-27 18:00","연속"]
[183,"경기","군포","서서울#2일동 #2T/L","2018-19년 송전정비회사 총액공사","154kV 일동-원곡#1T/L 휴전작업 관련 안전이격거리 확보","2019-05-16 08:00","2019-05-17 18:00","2019-05-16 08:00","2019-05-17 18:00","매일"]
[184,"경기","군포","서서울#2일동 #1T/L","2018-19년 송전정비회사 총액공사","154kV 일동-원곡#1T/L 휴전작업 관련 안전이격거리 확보","2019-05-18 08:00","2019-05-18 18:00","2019-05-18 08:00","2019-05-18 18:00","당일"]
[185,"경기","군포","서서울#2서안양 T/L","154kV 서서울2-서안양T/L 일진제 R-type PMJ교체공사","154kV 서서울2-서안양T/L 일진제 R-type PMJ교체공사","2019-05-28 09:00","2019-06-03 18:00","2019-05-28 09:00","2019-06-03 18:00","연속"]
[186,"경기","군포","서서울#2서안양 T/L","154kV 서서울소래T/L OPGW 항공장애표시구 시설공사","154kV 서서울소래T/L(OPGW) 항공장애표시구 설치공사 - 설치구간 OPGW 1조 이므로 양회선 동시휴전 필요 - 서서울2소래(좌)-서서울2서안양(우), 서서울2소래(좌)-서안양소래(우)","2019-05-22 08:00","2019-05-22 16:00","2019-05-22 08:00","2019-05-22 16:00","연속"]
[187,"경기","군포","신안산성포#2 T/L","'19년 군포P/O 변전정비회사 총액공사","신안산측 보통점검, 성포측 조작시험","2019-05-03 09:00","2019-05-03 18:00","2019-05-03 09:00","2019-05-03 18:00","당일"]
[188,"경기","군포","신안산성포#1 T/L","'19년 군포P/O 변전정비회사 총액공사","신안산측 보통점검, 성포측 조작시험","2019-05-02 10:00","2019-05-02 18:00","2019-05-02 10:00","2019-05-02 18:00","당일"]
[189,"경기","군포","신안산성포#3 T/L","'19년 군포P/O 변전정비회사 총액공사","신안산측 조작시험, 성포측 보통점검","2019-05-09 10:00","2019-05-09 18:00","2019-05-09 10:00","2019-05-09 18:00","당일"]
[190,"경기","군포","조암S/S 조암-구문천#1T/L GIS","2019년 군포 154kV GIS정밀점검 공사","2019년 군포 154kV GIS정밀점검 공사 -조암구문천 #1 T/L GIS정밀점검","2019-05-07 08:00","2019-05-09 20:00","2019-05-07 08:00","2019-05-09 20:00","연속"]
[191,"경기","군포","성곡중시화 T/L","2019년 군포 154kV GIS정밀점검 공사 - 중시화 6100","2019년 군포 154kV GIS정밀점검 공사 - 6100 GIS 무부하가압용","2019-05-14 18:00","2019-05-15 18:00","2019-05-14 18:00","2019-05-15 18:00","연속"]
[192,"경기","동부","가남S/S 154kV 이천-가남#2T/L GIS","19년 동부변전협력회사 총액공사","가남: 이천-가남 #2T/L (보통) -43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-05-03 09:00","2019-05-03 18:00","2019-05-01 09:00","2019-05-01 18:00","당일"]
[193,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-02 08:30","2019-05-04 17:30","2019-05-02 08:30","2019-05-04 17:30","연속"]
[194,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-02 08:30","2019-05-04 17:30","2019-05-02 08:30","2019-05-04 17:30","연속"]
[195,"경기","동부","성현산성#1 T/L","154kV 산성-성현 지중T/L 지장 이설공사","○ 구 간 : 기설 154㎸ 산성-성현T/L #15 ~ #19 ○ 선종/회선길이 : 154㎸ XLPE 2,000㎟, 3회선-1.71㎞","2019-05-20 09:00","2019-06-20 18:00","2019-05-20 09:00","2019-06-20 18:00","연속"]
[196,"경기","동부","성현산성#3 T/L","154kV 산성-성현 지중T/L 지장 이설공사","○ 구 간 : 기설 154㎸ 산성-성현T/L #15 ~ #19 ○ 선종/회선길이 : 154㎸ XLPE 2,000㎟, 3회선-1.71㎞","2019-05-02 09:00","2019-05-16 18:00","2019-05-02 09:00","2019-05-16 18:00","연속"]
[197,"경기","동부","오포S/S 154kV 오포-모현#2T/L GIS","19년 동부변전협력회사 총액공사","오포: 오포-모현#2T/L GIS(보통),43L/R 회로보완 확인","2019-05-22 09:00","2019-05-22 18:00","2019-05-22 09:00","2019-05-22 18:00","당일"]
[198,"경기","동부","율현S/S 154kV 곤지암-율현#2T/L GIS","19년 동부변전협력회사 총액공사","율현: 곤지암-율현#2T/L GIS(보통)43L/R 회로보완 확인 및 Remote 회로분리 시행, 보호반대체","2019-05-08 09:00","2019-05-10 18:00","2019-05-08 09:00","2019-05-10 18:00","연속"]
[199,"경기","성남","서안성S/S 154kV #60 BUS","성남전력 GIS 정밀점검공사","성남전력 #1M.Tr 2차 GIS 정밀점검공사","2019-05-15 09:00","2019-05-15 15:00","2019-05-15 09:00","2019-05-15 15:00","당일"]
[200,"경기","성남","서안성S/S 154kV #66 BUS","성남전력 GIS 정밀점검공사","성남전력 #2M.Tr 2차 GIS 정밀점검공사","2019-05-17 09:00","2019-05-17 18:00","2019-05-17 09:00","2019-05-17 18:00","당일"]
[201,"경기","성남","신성남S/S 154kV 신성남-정자#1T/L GIS","19년 성남전력지사 변전협력총액공사","GIS 조작시험","2019-05-09 10:00","2019-05-09 18:00","2019-05-09 10:00","2019-05-09 18:00","당일"]
[202,"경기","성남","신성남S/S 154kV 신성남-서판교#1T/L GIS","19년 성남전력지사 변전협력총액공사","GIS 조작시험","2019-05-10 10:00","2019-05-10 18:00","2019-05-10 10:00","2019-05-10 18:00","당일"]
[203,"경기","성남","신성남정자#2 T/L","19년 성남전력지사 변전협력총액공사","GIS 조작","2019-05-29 14:00","2019-05-29 18:00","2019-05-29 14:00","2019-05-29 18:00","당일"]
[204,"경기","성남","신성남서판교#2 T/L","170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2019-05-29 09:00","2019-05-31 18:00","2019-05-29 09:00","2019-05-31 18:00","당일"]
[205,"경기","성남","신용인S/S 154kV #67 BUS","19년 성남전력지사 170KV GIS 정밀점검공사","신용인 #6Sh.C GIS 정밀점검","2019-05-18 09:00","2019-05-18 18:00","2019-05-18 09:00","2019-05-18 18:00","당일"]
[206,"경기","성남","신용인S/S 154kV #66 BUS","19년 성남전력지사 170KV GIS 정밀점검공사","#2M.Tr 2차 GIS 정밀점검공사","2019-05-22 09:00","2019-05-22 18:00","2019-05-22 09:00","2019-05-22 18:00","당일"]
[207,"경기","성남","신용인S/S 154kV #61 BUS","19년 성남전력지사 170KV GIS 정밀점검공사","60-61SEC GIS 정밀점검공사","2019-05-25 09:00","2019-05-25 18:00","2019-05-25 09:00","2019-05-25 18:00","당일"]
[208,"경기","성남","신용인S/S 154kV #62 BUS","19년 성남전력지사 170KV GIS 정밀점검공사","신용인 #5Sh.C GIS 정밀점검","2019-05-15 09:00","2019-05-15 18:00","2019-05-15 09:00","2019-05-15 18:00","당일"]
[209,"경기","성남","신용인S/S 154kV #61 BUS","19년 성남전력지사 170KV GIS 정밀점검공사","신용인 #3Sh.C GIS 정밀점검","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-09 18:00","당일"]
[210,"경기","성남","신용인용인#2 T/L","154kV 신용인-용인#2T/L 정밀점검","154kV 신용인-용인#2T/L(No.1-27) 송전선로 정밀점검","2019-05-22 08:00","2019-05-23 18:00","2019-05-22 08:00","2019-05-23 18:00","매일"]
[211,"경기","성남","신용인S/S 154kV #60-#61 SEC GIS","19년 성남전력지사 170KV GIS 정밀점검공사","60-61SEC GIS 정밀점검공사","2019-05-23 09:00","2019-05-25 18:00","2019-05-23 09:00","2019-05-25 18:00","연속"]
[212,"경기","성남","신용인S/S 154kV #65-#66 SEC GIS","19년 성남전력지사 170KV GIS 정밀점검공사","65-66SEC GIS 정밀점검공사","2019-05-27 09:00","2019-05-29 18:00","2019-05-27 09:00","2019-05-29 18:00","연속"]
[213,"경기","성남","신용인용인#1 T/L","154kV 신용인-용인#1T/L 정밀점검","154kV 신용인-용인#1T/L(No.1-27) 송전선로 정밀점검","2019-05-20 08:00","2019-05-21 18:00","2019-05-20 08:00","2019-05-21 18:00","매일"]
[214,"경기","성남","신용인S/S 154kV #62 BUS","19년 성남전력지사 170KV GIS 정밀점검공사","신용인 #7Sh.C GIS 정밀점검","2019-05-31 09:00","2019-05-31 18:00","2019-05-31 09:00","2019-05-31 18:00","당일"]
[215,"경기","성남","신용인S/S 154kV #66 BUS","19년 성남전력지사 170KV GIS 정밀점검공사","65-66SEC GIS 정밀점검공사","2019-05-29 09:00","2019-05-29 18:00","2019-05-29 09:00","2019-05-29 18:00","당일"]
[216,"경기","직할","남수원발안#1 T/L","2018-2019년 송전정비회사 총액공사","154kV 서서울2-남수원#2T/L 피뢰기 설치 관련 안전이격거리확보(50~70호)","2019-05-23 07:30","2019-05-27 18:00","2019-05-23 07:30","2019-05-27 18:00","매일"]
[217,"경기","직할","남수원발안#2 T/L","154kV 봉담분기T/L OPGW 시설공사","공사장소 : 서서울-봉담-남수원S/S OPGW 100SQ 48C 6km, 24C 12C 12km 비금속광케이블 2.7km 시설","2019-05-30 07:00","2019-06-03 18:00","2019-05-30 07:00","2019-06-03 18:00","매일"]
[218,"경기","직할","신수원동수원#2 T/L","154kV 동수원변전소 현대화공사","(주)대진전력,(합)부광전업사","2019-05-13 09:00","2019-06-13 18:00","2019-05-13 09:00","2019-06-13 18:00","연속"]
[219,"경기","직할","관양동안양#1 T/L","19년 직할 변전협력회사 총액공사","동안양S/S 관양-동안양#1T/L GIS 조작시험","2019-05-27 10:00","2019-05-27 18:00","2019-05-27 10:00","2019-05-27 18:00","당일"]
[220,"경기","직할","의왕동안양#1 T/L","154kV 동안양S/S 인출T/L 정비공사","154kV 동안양S/S 옥내화 사업 관련 인출 T/L 정비공사 - 공사규모 : ACSR 410B×4C×0.05km, 보강 1기(No.1) - 공사내용 : 동안양S/S 구내 S/T 이설 및 인출 철탑 보강","2019-05-24 08:00","2019-05-31 18:00","2019-05-24 08:00","2019-05-31 18:00","연속"]
[221,"경기","직할","발안S/S 154kV #65 BUS","발안S/S #5M.TR 무부하가압","M.Tr * 1Bank 설치","2019-05-28 15:00","2019-05-29 15:00","2019-05-28 15:00","2019-05-29 15:00","연속"]
[222,"경기","직할","발안구문천#1 T/L","발안S/S #5M.TR 무부하가압","M.Tr * 1Bank 설치","2019-05-28 14:00","2019-05-29 15:00","2019-05-28 14:00","2019-05-29 15:00","연속"]
[223,"경기","직할","발안S/S 154kV #60 BUS","발안S/S #5M.TR 무부하가압","M.Tr * 1Bank 설치","2019-05-28 14:00","2019-05-28 15:00","2019-05-28 14:00","2019-05-28 15:00","당일"]
[224,"경기","직할","서서울서수원#1 T/L","서서울서수원#1T/L 170kV GIS 정밀점검 공사","서서울서수원#1T/L 170kV GIS 정밀점검","2019-05-30 09:00","2019-06-01 18:00","2019-05-30 09:00","2019-06-01 18:00","연속"]
[225,"경기","직할","율전의왕#1 T/L","의왕S/S 154kV 장기사용 GIS 대체공사","의왕S/S 율전-의왕#1T/L GIS 대체공사","2019-05-07 09:00","2019-05-24 18:00","2019-05-07 09:00","2019-05-24 18:00","연속"]
[226,"경기","평택","고덕송탄#1 T/L","송탄S/S 154kV 고덕송탄#1 T/L GIS 보통점검","송탄S/S 154kV 고덕송탄#1 T/L GIS 보통점검 / LA 대체공사","2019-05-02 10:00","2019-05-02 18:00","2019-05-02 10:00","2019-05-02 18:00","당일"]
[227,"경기","평택","고덕송탄#2 T/L","송탄S/S 154kV 고덕송탄#2 T/L GIS 보통점검","송탄S/S 154kV 고덕송탄#2 T/L GIS 보통점검","2019-05-03 10:00","2019-05-03 18:00","2019-05-03 10:00","2019-05-03 18:00","당일"]
[228,"경기","평택","안성S/S 154kV #65 BUS","안성S/S 170kV GIS 용량대체공사","소사벌-안성T/L GIS 철거 및 설치 #1M.Tr GIS 철거 및 설치 #60/65 PT 철거 및 설치공사","2019-05-28 18:00","2019-06-06 14:00","2019-05-28 18:00","2019-06-06 14:00","연속"]
[229,"경기","평택","안성S/S 154kV #60 BUS","안성S/S 170kV GIS 용량대체공사","소사벌-안성T/L GIS 철거 및 설치 #1M.Tr GIS 철거 및 설치 #60/65 PT 철거 및 설치공사","2019-05-21 18:00","2019-05-28 18:00","2019-05-21 18:00","2019-05-28 18:00","연속"]
[230,"경기","평택","안성S/S 154kV #65 BUS","안성S/S 170kV GIS 용량대체공사","소사벌-안성T/L GIS 철거 및 설치 #1M.Tr GIS 철거 및 설치 #60/65 PT 철거 및 설치공사","2019-05-18 08:00","2019-05-21 18:00","2019-05-18 08:00","2019-05-21 18:00","연속"]
[231,"경기","평택","소사벌안성 T/L","안성S/S 170kV GIS 용량대체공사","소사벌-안성T/L GIS 철거 및 설치 #1M.Tr GIS 철거 및 설치 #60/65 PT 철거 및 설치공사","2019-05-18 08:00","2019-06-07 18:00","2019-05-18 08:00","2019-06-07 18:00","연속"]
[232,"경기","평택","안성S/S 154kV #60 BUS","안성S/S 170kV GIS 용량대체공사","서안성-안성#2T/L GIS 철거 및 설치 #3M.Tr GIS 철거 및 설치 -#60BUS 준공시험 - 무부하가압","2019-05-10 14:00","2019-05-11 18:00","2019-05-10 14:00","2019-05-11 18:00","연속"]
[233,"경기","평택","오산향남#1 T/L","154kV 오산-향남T/L 전선접속개소 교체공사","- 154kV 오산-향남T/L No.5-9 및 No.18-19 전선접속개소 교체공사","2019-05-01 07:00","2019-05-06 18:00","2019-05-01 07:00","2019-05-06 18:00","연속"]
[234,"경기","평택","오산평택#1 T/L","(안전이격휴전)154kV 오산-향남T/L 전선접속개소 교체공사","- 154kV 오산-향남T/L No.5-9 및 No.18-19 전선접속개소 교체공사를 위한 안전이격휴전","2019-05-01 07:00","2019-05-06 18:00","2019-05-01 07:00","2019-05-06 18:00","매일"]
[235,"경기","평택","오산평택#2 T/L","(안전이격휴전)154kV 오산-향남T/L 전선접속개소 교체공사","- 154kV 오산-향남T/L No.5-9 및 No.18-19 전선접속개소 교체공사를 위한 안전이격휴전","2019-05-07 07:00","2019-05-13 18:00","2019-05-07 07:00","2019-05-13 18:00","매일"]
[236,"경기","평택","오산향남#2 T/L","154kV 오산-향남T/L 전선접속개소 교체공사","- 154kV 오산-향남T/L No.5-9 및 No.18-19 전선접속개소 교체공사","2019-05-07 07:00","2019-05-13 18:00","2019-05-07 07:00","2019-05-13 18:00","연속"]
[237,"경기","평택","송탄오성CC #1T/L","154kV 송탄-오성CC#1T/L 가선로 구성","고덕산단진입도로 개설관련 지장이설 가선로구성 공사시행","2019-05-20 07:00","2019-05-23 18:00","2019-05-20 07:00","2019-05-23 18:00","연속"]
[238,"경기","평택","청북평택#2 T/L","154kV 청북S/S #5M.Tr 증설용 GIS 설치공사","ㅇ #5M.TR증설설비 무부하 가압 - 170kV GIS, #5M.Tr, 25.8kV GIS, 전력케이블","2019-05-14 10:30","2019-05-15 18:00","2019-05-14 10:30","2019-05-15 18:00","연속"]
[239,"경기","평택","고덕평택#2 T/L","평택S/S 고덕-평택#2 T/L GIS 초기점검","평택S/S 고덕-평택#2 T/L GIS 초기점검","2019-05-31 10:00","2019-05-31 18:00","2019-05-31 10:00","2019-05-31 18:00","당일"]
[240,"경기","평택","고덕평택#1 T/L","평택S/S 고덕-평택#1 T/L GIS 초기점검","평택S/S 고덕-평택#1 T/L GIS 초기점검","2019-05-30 10:00","2019-05-30 18:00","2019-05-30 10:00","2019-05-30 18:00","당일"]
[241,"경기","평택","평택오성CC#1 T/L","평택S/S 평택오성CC#1 T/L GCB 조작시험","평택S/S 평택오성CC#1 T/L GCB 조작시험","2019-05-10 10:00","2019-05-10 18:00","2019-05-10 10:00","2019-05-10 18:00","당일"]
[242,"경기","평택","평택오성CC#2 T/L","평택S/S 평택오성CC#2 T/L GCB 보통점검","평택S/S 평택오성CC#2 T/L GCB 보통점검 / PT,LA 보통점검","2019-05-03 10:00","2019-05-03 18:00","2019-05-03 10:00","2019-05-03 18:00","당일"]
[243,"경기","평택","평택TP평택CC#2 T/L","평택C/C 평택복합#2 T/L GIS 전자변교체","평택C/C 평택복합#2 T/L GIS 전자변교체 및 조작시험","2019-05-07 10:00","2019-05-07 18:00","2019-05-07 10:00","2019-05-07 18:00","당일"]
[244,"경기","평택","평택TP평택CC#1 T/L","평택C/C 평택복합#1 T/L GIS 전자변교체","평택C/C 평택복합#1 T/L GIS 전자변교체 및 조작시험","2019-05-02 10:00","2019-05-02 18:00","2019-05-02 10:00","2019-05-02 18:00","당일"]
[245,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-06 08:30","2019-05-08 17:30","2019-05-06 08:30","2019-05-08 17:30","연속"]
[246,"경기","동부","곤지암S/S 154kV #2 BUS TIE GIS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설","2019-05-06 08:30","2019-05-23 17:30","2019-05-06 08:30","2019-05-23 17:30","연속"]
[247,"경기","동부","곤지암S/S 154kV #2 Sh.C","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설","2019-05-06 08:30","2019-05-23 17:30","2019-05-06 08:30","2019-05-23 17:30","연속"]
[248,"경기","동부","곤지암S/S 154kV #1 Sh.C","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설","2019-05-06 08:30","2019-05-23 17:30","2019-05-06 08:30","2019-05-23 17:30","연속"]
[249,"경기","동부","곤지암S/S 154kV #66 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설","2019-05-06 08:30","2019-05-12 17:30","2019-05-06 08:30","2019-05-12 17:30","연속"]
[250,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-06 08:30","2019-05-08 17:30","2019-05-06 08:30","2019-05-08 17:30","연속"]
[251,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-09 08:30","2019-05-12 17:30","2019-05-09 08:30","2019-05-12 17:30","연속"]
[252,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-09 08:30","2019-05-11 17:30","2019-05-09 08:30","2019-05-11 17:30","연속"]
[253,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-13 08:30","2019-05-15 17:30","2019-05-13 08:30","2019-05-15 17:30","연속"]
[254,"경기","동부","곤지암S/S 154kV #61 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설","2019-05-13 08:30","2019-05-26 17:30","2019-05-13 08:30","2019-05-26 17:30","연속"]
[255,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-13 08:30","2019-05-15 17:30","2019-05-13 08:30","2019-05-15 17:30","연속"]
[256,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-16 08:30","2019-05-18 17:30","2019-05-16 08:30","2019-05-18 17:30","연속"]
[257,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-16 08:30","2019-05-18 17:30","2019-05-16 08:30","2019-05-18 17:30","연속"]
[258,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-19 08:30","2019-05-21 17:30","2019-05-19 08:30","2019-05-21 17:30","연속"]
[259,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-19 08:30","2019-05-21 17:30","2019-05-19 08:30","2019-05-21 17:30","연속"]
[260,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-22 08:30","2019-05-25 17:30","2019-05-22 08:30","2019-05-25 17:30","연속"]
[261,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-22 08:30","2019-05-25 17:30","2019-05-22 08:30","2019-05-25 17:30","연속"]
[262,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 무부하가압","2019-05-25 16:00","2019-05-26 16:00","345kV로 이동","345kV로 이동","연속"]
[263,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-27 08:30","2019-05-29 17:30","2019-05-27 08:30","2019-05-29 17:30","연속"]
[264,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-27 08:30","2019-05-29 17:30","2019-05-27 08:30","2019-05-29 17:30","연속"]
[265,"경기","동부","곤지암S/S 154kV #66 BUS","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설","2019-05-27 08:30","2019-06-09 17:30","2019-05-27 08:30","2019-06-09 17:30","연속"]
[266,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-30 08:30","2019-06-02 17:30","2019-05-30 08:30","2019-06-02 17:30","연속"]
[267,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-05-30 08:30","2019-06-02 17:30","2019-05-30 08:30","2019-06-02 17:30","연속"]
[268,"강원","동해","동해이원#1 T/L","2019년 동해전력지사 170kV GIS 정밀점검","1. 이원S/S 동해-이원#1T/L GIS 정밀점검","2019-05-27 09:30","2019-05-29 18:00","2019-05-27 09:30","2019-05-29 18:00","연속"]
[269,"강원","동해","동해이원#2 T/L","2019년 동해전력지사 170kV GIS 정밀점검","1. 이원S/S 동해-이원#2T/L GIS 정밀점검","2019-05-23 09:30","2019-05-25 18:00","2019-05-23 09:30","2019-05-25 18:00","연속"]
[270,"강원","동해","이원도계 T/L","2019년 동해전력지사 170kV GIS 정밀점검","1. 이원S/S 이원-도계T/L GIS 정밀점검","2019-05-20 09:30","2019-05-22 18:00","2019-05-20 09:30","2019-05-22 18:00","연속"]
[271,"강원","원주","횡성홍천#1 T/L","154kV 홍천T/L 안전이격 확보공사","○ 철탑교체 : No.65,66,68 ○ 전력선 교체 : No.64~69","2019-05-20 08:00","2019-05-28 18:00","2019-05-20 08:00","2019-05-28 18:00","연속"]
[272,"강원","원주","횡성홍천#2 T/L","154kV 홍천T/L 안전이격 확보공사","○ 철탑교체 : No.65,66,68 ○ 전력선 교체 : No.64~69","2019-05-20 08:00","2019-05-28 18:00","2019-05-20 08:00","2019-05-28 18:00","연속"]
[273,"강원","직할","북춘천화천HP T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검 24기","2019-05-29 09:00","2019-05-30 18:00","2019-05-29 09:00","2019-05-30 18:00","연속"]
[274,"강원","직할","북춘천춘천HP T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검 24기","2019-05-13 09:00","2019-05-14 18:00","2019-05-13 09:00","2019-05-14 18:00","연속"]
[275,"강원","직할","인제양구#2 T/L","2018~2019년 강원지역본부 직할 변전정비 총액공사","○ 인제S/S 인제-양구 #2T/L GIS 및 피뢰기 A, B, C상 보통점검 ○ 양구S/S 인제-양구 #2T/L GIS 보통점검","2019-05-14 10:00","2019-05-14 18:00","2019-05-14 10:00","2019-05-14 18:00","당일"]
[276,"강원","직할","철원화천#2 T/L","철원S/S 154kV 비즌비츠로T/L용 GIS설치공사","154kV GIS 50KA 1250A 2CCT 설치관련 BUS 건전성확인(#66BUS)","2019-05-23 14:00","2019-05-24 14:00","2019-05-23 14:00","2019-05-24 14:00","연속"]
[277,"강원","직할","철원화천#2 T/L","철원S/S 154kV 비즌비츠로T/L용 GIS설치공사","154kV GIS 50KA 1250A 2CCT 설치관련 BUS 건전성확인(#61BUS)","2019-05-16 14:00","2019-05-17 14:00","2019-05-16 14:00","2019-05-17 14:00","연속"]
[278,"강원","직할","춘천북춘천#2 T/L","2018년~2019년 강원지역본부 직할 변전정비 총액공사","춘천S/S 154kV 춘천-북춘천 #2 T/L GIS 보통점검","2019-05-09 10:00","2019-05-09 14:00","2019-05-09 10:00","2019-05-09 14:00","당일"]
[279,"강원","직할","춘천북춘천#1 T/L","2018~2019년 강원직할 송전정비회사 총액공사","PD집합반 설치 및 불량애자 교체","2019-05-15 09:00","2019-05-15 18:00","2019-05-15 09:00","2019-05-15 18:00","당일"]
[280,"강원","직할","춘천북춘천#2 T/L","2018~2019년 강원직할 송전정비회사 총액공사","PD집합반 설치","2019-05-16 09:00","2019-05-16 18:00","취소","취소","당일"]
[281,"강원","직할","화천화천HP#1 T/L","2018~2019년 강원지역본부 직할 변전정비 총액공사","○ 화천S/S 화천-화천HP #1T/L GIS 보통점검 및 피뢰기 A, B, C상 보통점검","2019-05-02 10:00","2019-05-02 18:00","2019-05-02 10:00","2019-05-02 18:00","당일"]
[282,"강원","태백","고한영월 T/L","19년 태백전력지사 가공송전선로 위탁공사","154kV 고한-영월T/L 가공송전선로 정밀점검","2019-05-23 09:00","2019-05-30 18:00","2019-05-23 09:00","2019-05-30 18:00","연속"]
[283,"강원","태백","이원태백 T/L","19년 태백전력지사 170kV GIS 정밀점검","태백S/S 이원-태백T/L GIS 정밀점검","2019-05-06 09:00","2019-05-08 14:00","2019-05-06 09:00","2019-05-08 14:00","연속"]
[284,"강원","태백","태백고한 T/L","19년 태백전력지사 가공송전선로 위탁공사","154kV 태백-고한T/L 가공송전선로 정밀점검","2019-05-07 09:00","2019-05-10 18:00","2019-05-09 09:00","2019-05-12 18:00","연속"]
[285,"강원","태백","태백영월 T/L","19년 태백전력지사 가공송전선로 위탁공사","154kV 태백-영월T/L 가공송전선로 정밀점검","2019-05-13 09:00","2019-05-22 18:00","2019-05-13 09:00","2019-05-22 18:00","연속"]
[286,"강원","직할","철원화천#1 T/L","2018~19년 강원직할 송전정비회사 총액공사","송전선로용 피뢰기 설치 5기, 15세트","2019-05-20 09:00","2019-05-20 18:00","2019-05-27 09:00","2019-05-27 18:00","연속"]
[287,"강원","직할","철원화천#2 T/L","2018~19년 강원직할 송전정비회사 총액공사","송전선로용 피뢰기 설치 54기, 162세트","2019-05-21 08:00","2019-05-24 18:00","2019-05-28 08:00","2019-05-31 18:00","연속"]
[288,"충북","직할","삼죽만승 T/L","만승S/S 154kV 삼죽만승T/L CVT 초기점검","만승S/S 154kV 삼죽만승T/L CVT 초기점검","2019-05-15 10:00","2019-05-15 18:00","취소","취소","당일"]
[289,"충북","청주","상주보은 T/L","154kV 청원-청주 등 8개 T/L 송전피뢰기 설치공사","154kV 상주-보은T/L 피뢰기 설치 No.60~110","2019-05-13 08:00","2019-05-16 18:00","취소","취소","매일"]
[290,"충북","청주","오송북청주#2 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","154kV 오송-북청주#2T/L SB댐퍼 취부 : No.39*6개 불량애자 교체 : No.5, 21, 35","2019-05-04 08:00","2019-05-04 18:00","2019-05-04 08:00","2019-05-04 18:00","당일"]
[291,"충북","청주","서청주사직#2 T/L","18~19년 청주전력 변전협력회사 총액공사","사직S/S, 서청주S/S 154kV 서청주사직#2T/L 송전선로보호반 대체","2019-05-11 09:30","2019-05-12 18:00","2019-05-12 09:30","2019-05-12 18:00","연속"]
[292,"충북","청주","사직북청주#1 T/L","18~19년 청주전력 변전협력회사 총액공사","사직S/S, 북청주S/S 154kV 사직북청주#1T/L 송전선로보호반 대체","2019-05-13 09:30","2019-05-15 18:00","취소","취소","연속"]
[293,"충북","청주","청원오송#1 T/L","18-19년 송전정비 협력회사 총액공사(청주 전력)","154kV 청원-오송#1T/L - 가공지선교체 : No.4~5 - 항공구설치 : No.4~5","2019-05-05 08:00","2019-05-05 18:00","취소","취소","당일"]
[294,"충북","청주","초정청주#1 T/L","청주S/S 154kV GIS화 공사","옥외철구 GIS화 공사","2019-05-10 08:00","2019-05-18 18:00","2019-05-13 08:00","2019-05-20 18:00","연속"]
[295,"충북","청주","청원청주#2 T/L","청주S/S 154kV GIS화 공사","옥외철구 GIS화 공사","2019-05-10 08:00","2019-05-18 18:00","2019-05-13 08:00","2019-05-20 18:00","연속"]
[296,"충북","충주","단양영월CC#2 T/L","154kV 단양-영월CCT/L 안전이격 확보공사","○ 공사구간 : 154kV 단양-영월CCT/L No.13~16, 51~55 ○ 철탑교체 : 154kV 2회선용 사각철탑 5기(No.14,15,52,53,54)","2019-05-18 07:00","2019-05-24 18:00","2019-05-25 07:00","2019-05-27 18:00","연속"]
[297,"충북","충주","단양영월CC#1 T/L","154kV 단양-영월CCT/L 안전이격 확보공사","가. 공사구간 : 154kV 단양-영월CCT/L 13~16호, 52~55호 - 철탑교체 5기(14,15,52,53,54호), 전선교체 1.092km","2019-05-26 07:00","2019-05-31 18:00","취소","취소","연속"]
[298,"충북","충주","단양영월CC#1 T/L","154kV 단양-영월CCT/L 안전이격 확보공사","○ 공사구간 : 154kV 단양-영월CCT/L No.13~16, 51~55 ○ 철탑교체 : 154kV 2회선용 사각철탑 5기(No.14,15,52,53,54)","2019-05-13 07:00","2019-05-17 18:00","2019-05-20 07:00","2019-05-24 18:00","연속"]
[299,"충북","충주","왕암충주 T/L","18-19년 충주전력지사 변전정비 총액공사","충주S/S 왕암-충주T/L GIS 보통점검","2019-05-14 09:00","2019-05-14 18:00","2019-05-14 09:00","2019-05-14 18:00","당일"]
[300,"충북","충주","충주충주HP#2 T/L","18-19년 충주전력지사 변전정비 총액공사","충주S/S 충주-충주HP#2T/L GIS 보통점검","2019-05-21 09:00","2019-05-21 18:00","취소","취소","당일"]
[301,"충북","충주","충주충주HP#1 T/L","18-19년 충주전력지사 변전정비 총액공사","충주S/S 충주-충주HP#1T/L GIS 보통점검","2019-05-22 09:00","2019-05-22 18:00","취소","취소","당일"]
[302,"충북","충주","북충주충주 T/L","18-19년 충주전력지사 변전정비 총액공사","충주S/S 북충주-충주T/L GIS 보통점검","2019-05-28 09:00","2019-05-28 18:00","2019-05-28 09:00","2019-05-28 18:00","당일"]
[303,"충북","충주","충주S/S 154kV #61-#66 BUS TIE GIS","18-19년 충주전력지사 변전정비 총액공사","충주S/S 6200 BUSTIE GIS 보통점검","2019-05-29 09:00","2019-05-29 18:00","2019-05-29 09:00","2019-05-29 18:00","당일"]
[304,"충북","충주","충주S/S 154kV #65-#66 BUS SEC GIS","18-19년 충주전력지사 변전정비 총액공사","충주S/S #65-66SEC GIS 보통점검","2019-05-07 09:00","2019-05-07 18:00","2019-05-07 09:00","2019-05-07 18:00","당일"]
[305,"대전충남","대전","신옥천추부#2 T/L","[송전] 154kV 신옥천-추부T/L 피뢰기 설치공사","[송전] 154kV 신옥천-추부#2T/L 피뢰기 설치","2019-05-10 08:00","2019-05-10 18:00","2019-05-10 08:00","2019-05-10 18:00","당일"]
[306,"대전충남","서산","신당진당진#2 T/L","당진S/S 154kV 취약설비 GIS화 공사","154kV GCB 철거 X 11대(DS, LA 등 관련기기) 154kV GIS 설치 X 15대 옥외철구 개선 - #1~#4M.Tr, #1SH.C 옥외 철구구간 철거 - 철구 상부모선 및 인하선 교체(HDCC -> 전력선) 기타부대작업","2019-05-31 09:00","2019-06-04 18:00","취소","취소","연속"]
[307,"대전충남","세종","천안전의#1 T/L","154kV천안-전의T/L지장송전선로 이설공사","철탑설치 : 3기(No.6,12,13) 철탑철거 : 3기(No.6,12,13)","2019-05-09 08:00","2019-05-12 18:00","2019-05-09 08:00","2019-05-12 18:00","연속"]
[308,"대전충남","아산","불당서천안#1 T/L","19년 154kV GIS 정밀점검 공사","○불당S/S 154kV 불당-서천안#1T/L GIS 정밀점검공사","2019-05-31 09:00","2019-06-01 18:00","2019-05-30 09:00","2019-05-30 18:00","연속"]
[309,"대전충남","아산","불당서천안#2 T/L","19년 154kV GIS 정밀점검 공사","○불당S/S 154kV 불당-서천안#2T/L GIS 정밀점검공사","2019-05-29 09:00","2019-05-30 18:00","2019-05-31 09:00","2019-05-31 18:00","연속"]
[310,"대전충남","아산","아산S/S 154kV #60 BUS","아산S/S 154kV #3Sh.C 1DS(#60BUS)측 가스누기 보수","○아산S/S 154kV #3Sh.C 1DS(#60BUS)측 가스누기 보수","2019-05-15 09:00","2019-05-16 18:00","2019-05-15 09:00","2019-05-16 18:00","연속"]
[311,"대전충남","아산","아산인주#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","154kV 아산-인주#2T/L 피뢰기 설치공사(4회선 병가구간) [안전이격거리 확보] 154kV 아산-합덕#2T/L","2019-05-05 07:00","2019-05-05 18:00","취소","취소","당일"]
[312,"대전충남","아산","아산인주#1 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","154kV 아산-인주#1T/L 피뢰기 설치공사(4회선 병가구간) [안전이격거리 확보] 154kV 아산-합덕#1T/L","2019-05-04 07:00","2019-05-04 18:00","취소","취소","당일"]
[313,"대전충남","아산","아산합덕#1 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","154kV 아산-인주 #1T/L 피뢰기 설치공사(4회선 병가구간) [안전이격거리 확보]154kV 아산-합덕#1T/L","2019-05-04 07:00","2019-05-04 18:00","취소","취소","당일"]
[314,"대전충남","아산","아산합덕#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","154kV 아산-인주 #2T/L 피뢰기 설치공사(4회선 병가구간) [안전이격거리 확보]154kV 아산-합덕#12/L","2019-05-05 07:00","2019-05-05 18:00","취소","취소","당일"]
[315,"대전충남","청양","신풍공주#2 T/L","154kV 신풍E/C #3M.Tr증설공사","O 154kV GIS(170kV 50kA 1250A) 설치 * 1CCT O 기타 부대공사 * 1식","2019-05-18 18:00","2019-05-19 18:00","2019-05-18 18:00","2019-05-19 18:00","연속"]
[316,"대전충남","청양","신풍공주#1 T/L","154kV 신풍E/C #3M.Tr증설공사","O 154kV GIS(170kV 50kA 1250A) 설치 * 1CCT O 기타 부대공사 * 1식","2019-05-13 18:00","2019-05-14 18:00","2019-05-13 18:00","2019-05-14 18:00","연속"]
[317,"대전충남","청양","동군산장항#1 T/L","장항S/S 170kV GIS 보통점검","장항S/S 170kV GIS 보통점검 C 대 상 : 154kv동군산-장항#1T/L C 내 용 : 170kV GIS, LA 및 CVT 보통점검","2019-05-10 09:00","2019-05-10 18:00","2019-05-10 09:00","2019-05-10 18:00","당일"]
[318,"전북","군산","군산서군산#1 T/L","154㎸ 군산서군산T/L 안전이격거리확보공사","-철탑신설 : 2기(25, 26호) -철탑철거 : 2기(25, 26호)","2019-05-23 07:00","2019-05-26 18:00","2019-05-23 07:00","2019-05-26 18:00","연속"]
[319,"전북","군산","군산서군산#2 T/L","154㎸ 군산서군산T/L 안전이격거리확보공사","-철탑신설 : 2기(25, 26호) -철탑철거 : 2기(25, 26호)","2019-05-27 07:00","2019-06-01 18:00","2019-05-27 07:00","2019-06-01 18:00","연속"]
[320,"전북","군산","새만금군장#2 T/L","154kV 비응분기 지중T/L 건설공사","○ 구간 : 기설 새만금-군장 2∏ 분기 ~ 비응S/S ○ 선종/회선길이 : 154kV XLPE 1200㎟, 4회선-1km ○ 포설 및 접속 : 포설8구간, 중간접속8개소, 종단접속4개소","2019-05-24 09:00","2019-06-23 18:00","2019-05-24 09:00","2019-06-23 18:00","연속"]
[321,"전북","군산","군공내초#1 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 내초S/S 617 초기점검 2. 군공S/S 697 조작시험","2019-05-20 09:30","2019-05-20 18:00","2019-05-20 09:30","2019-05-20 18:00","당일"]
[322,"전북","군산","군공내초#2 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 내초S/S 627 초기점검 2. 군공S/S 6A7 조작시험","2019-05-21 09:30","2019-05-21 18:00","2019-05-21 09:30","2019-05-21 18:00","당일"]
[323,"전북","군산","군산서군산#2 T/L","서군산S/S 현대화관련 부지확보공사","서군산S/S #2BUS CVT 이설, #1 BUS-TIE 이설, #1M.Tr 차단기 설치","2019-05-27 07:00","2019-06-01 18:00","2019-05-27 07:00","2019-06-01 18:00","연속"]
[324,"전북","군산","팔봉두마#2 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 617 차단기 하자점검 2. LA 초기점검","2019-05-27 09:30","2019-05-27 18:00","2019-05-27 09:30","2019-05-27 18:00","당일"]
[325,"전북","군산","팔봉두마#1 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 637 차단기 하자점검 2. LA 초기점검","2019-05-24 09:30","2019-05-24 18:00","2019-05-24 09:30","2019-05-24 18:00","당일"]
[326,"전북","김제","김제부안#2 T/L","김제 및 부안S/S 154kV GIS 보통점검","김제 및 부안S/S 154kV GIS 보통점검","2019-05-30 10:00","2019-05-31 18:00","2019-05-30 10:00","2019-05-31 18:00","매일"]
[327,"전북","김제","김제부안#1 T/L","김제 및 부안S/S 154kV GIS 보통점검","김제 및 부안S/S 154kV GIS 보통점검","2019-05-28 10:00","2019-05-29 18:00","2019-05-28 10:00","2019-05-29 18:00","매일"]
[328,"전북","김제","신김제전주#1 T/L","김제P/O 장기사용 기타설비 교체공사","신김제S/S 신김제-전주#1T/L LA(A,B,C) 교체","2019-05-02 09:00","2019-05-02 18:00","2019-05-02 09:00","2019-05-02 18:00","당일"]
[329,"전북","김제","신김제전주#2 T/L","김제P/O 장기사용 기타설비 교체공사","신김제S/S 신김제-전주#2T/L LA(A,B,C) 교체","2019-05-03 09:00","2019-05-03 18:00","2019-05-03 09:00","2019-05-03 18:00","당일"]
[330,"전북","김제","신김제정공#2 T/L","154kV 신김제-정공#2T/L 항공구 설치공사","154kV 신김제-정공#2T/L No.73~74호 항공구 설치","2019-05-13 09:00","2019-05-13 18:00","2019-05-13 09:00","2019-05-13 18:00","당일"]
[331,"전북","직할","무주진안 T/L","154kV 무주-진안T/L 정밀점검","154kV 북전주-진안T/L(무주-진안) No.105-175호","2019-05-12 08:30","2019-05-22 17:00","2019-05-13 08:30","2019-05-23 17:00","매일"]
[332,"전북","직할","무주용담수력 T/L","2019년 전북직할 170kV 차단기 정밀점검공사","차단기 정밀점검 (평일 : 매일작업, 주말 : 연속작업)","2019-05-08 08:00","2019-05-11 18:00","2019-05-09 08:00","2019-05-12 18:00","연속"]
[333,"전북","군산","군산영등#1 T/L","차단기 GIS 정밀점검","차단기 GIS 정밀점검","2019-05-08 09:00","2019-05-09 18:00","2019-05-08 09:00","2019-05-09 18:00","연속"]
[334,"전북","군산","군산영등#2 T/L","차단기 GIS 정밀점검","차단기 GIS 정밀점검","2019-05-13 09:00","2019-05-14 18:00","2019-05-13 09:00","2019-05-14 18:00","연속"]
[335,"전북","김제","김제칠보HP T/L","유압경보 관련 점검","유압경보 관련 점검","2019-05-02 09:00","2019-05-03 18:00","2019-05-13 09:00","2019-05-17 18:00","연속"]
[336,"전북","군산","군공소룡#1 T/L","송전선로 보호배전반 성능개선","송전선로 보호배전반 성능개선","2019-05-23 10:00","2019-05-23 18:00","2019-05-23 10:00","2019-05-23 18:00","연속"]
[337,"전북","군산","군공소룡#2 T/L","송전선로 보호배전반 성능개선","송전선로 보호배전반 성능개선","2019-05-24 10:00","2019-05-24 18:00","2019-05-24 10:00","2019-05-24 18:00","연속"]
[338,"광주전남","강진","신강진강진#2 T/L","154kV 인출선로 모선 재배열공사","가. 공사장소 : 신강진S/S 154kV 인출선로 나. 휴전선로 : 154kV 신강진-강진#2T/L 다. 작업내용 - 인출선로 모선 재배열을 위한 선로 재배열공사 - 선종/길이 : 신강진-대불#1T/L(XLPE 2000SQ X 1C(D) X 0.12km) 신강진-강진#2T/L(XLPE 2000SQ X 1C(D) X 0.12km) - 접속 : EB-G 4개소, EB-A 4개소","2019-05-27 09:00","2019-07-06 18:00","취소","취소","연속"]
[339,"광주전남","광주","계림충장#2 T/L","19년 광주 변전 총액공사 (계림-충장2T/L)","계림-충장#2T/L 양단 보호반 교체, 계림S/S GIS 보통점검, 충장S/S 장기미동작CB점검","2019-05-20 09:00","2019-05-22 18:00","2019-05-20 09:00","2019-05-22 18:00","연속"]
[340,"광주전남","광주","계림충장#3 T/L","19년 광주 변전 총액공사 (계림-충장3T/L)","계림-충장#3T/L 양단 보호반 교체, 계림S/S GIS 보통점검, 충장S/S 장기미동작CB점검","2019-05-27 09:00","2019-05-29 18:00","2019-05-27 09:00","2019-05-29 18:00","연속"]
[341,"광주전남","광주","담양일곡#2 T/L","19년 광주변전총액공사(담양일곡#2T/L)","담양S/S 담양-일곡#2T/L CVT대체, GIS 보통점검 일곡S/S 담양-일곡#2T/L GIS 보통점검","2019-05-16 09:00","2019-05-17 18:00","2019-05-16 09:00","2019-05-17 18:00","연속"]
[342,"광주전남","광주","담양김제 T/L","19년 광주변전총액공사(담양김제T/L)","담양S/S 담양-김제T/L CVT대체, GIS 장기미동작차단기 점검, T/L PNL 와이피피제 보호계전기 성능개선","2019-05-22 09:00","2019-05-23 18:00","2019-05-22 09:00","2019-05-23 18:00","연속"]
[343,"광주전남","광주","정공담양 T/L","19년 광주변전총액공사(담양정공T/L)","담양S/S 담양-정공T/L CVT대체, GIS 장기미동작차단기 점검","2019-05-27 09:00","2019-05-28 18:00","2019-05-27 09:00","2019-05-28 18:00","연속"]
[344,"광주전남","광주","담양일곡#1 T/L","19년 광주변전총액공사(담양일곡#1T/L)","담양S/S 담양-일곡#1T/L CVT대체, GIS 장기미동작차단기 점검 일곡S/S 담양-일곡#1T/L GIS 보통점검","2019-05-08 09:00","2019-05-09 18:00","2019-05-08 09:00","2019-05-09 18:00","연속"]
[345,"광주전남","목포","안좌S/S 154KV 신안그린T/L GIS","`19년 목포변전 총액공사(신안그린T/L GIS 하자점검)","`19년 목포변전 총액공사(신안그린T/L GIS 하자점검)","2019-05-08 09:00","2019-05-08 18:00","2019-05-08 09:00","2019-05-08 18:00","당일"]
[346,"광주전남","목포","장성영광#1 T/L","2019년 목포전력지사 170kV GIS 정밀점검공사","○ 영광S/S 장성-영광#1T/L GIS 정밀점검","2019-05-27 09:00","2019-05-30 18:00","2019-05-27 09:00","2019-05-30 18:00","연속"]
[347,"광주전남","순천","광양순천#1 T/L","154kV 광양-순천#1 T/L 송전협력 불량애자교체","18~19년도 순천전력 협력회사 총액공사 - 광양-순천#1 T/L 불량애자교체 : No.0.01호(1기)","2019-05-15 08:00","2019-05-15 18:00","2019-05-15 08:00","2019-05-15 18:00","당일"]
[348,"광주전남","순천","광양하동#2 T/L","154kV 광양하동#2T/L 정밀점검","19년 가공송전 순시점검 위탁공사 No.38~광양ST 정밀점검","2019-05-14 08:00","2019-05-16 18:00","2019-05-14 08:00","2019-05-16 18:00","매일"]
[349,"광주전남","순천","광양하동#1 T/L","154kV 광양하동#1T/L 정밀점검","19년 가공송전 순시점검 위탁공사 No.38~광양ST 정밀점검","2019-05-09 08:00","2019-05-13 18:00","2019-05-09 08:00","2019-05-13 18:00","매일"]
[350,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌T/L 안전이격확보공사","공 사 개 요 가. 작업구간 : 154kV 순천-율촌T/L No.62~65호 나. 작업내용 ○ 154kV 순천-율촌T/L 철탑상향 : 1기 - 63호(17 → 30m) : 13m 상향 ※ 관형지지물 활용 선하지 내 철탑이설","2019-05-04 07:00","2019-05-05 18:00","2019-05-04 07:00","2019-05-05 18:00","연속"]
[351,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌T/L 안전이격확보공사","공 사 개 요 가. 작업구간 : 154kV 순천-율촌T/L No.62~65호 나. 작업내용 ○ 154kV 순천-율촌T/L 철탑상향 : 1기 - 63호(17 → 30m) : 13m 상향 ※ 관형지지물 활용 선하지 내 철탑이설","2019-05-04 07:00","2019-05-05 18:00","2019-05-04 07:00","2019-05-05 18:00","연속"]
[352,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주#2 T/L 송전협력 불량애자교체","18~19년도 순천전력 협력회사 총액공사 - 순천-승주#2 T/L 불량애자교체 : No.2호(1기)","2019-05-16 08:00","2019-05-16 18:00","2019-05-16 08:00","2019-05-16 18:00","당일"]
[353,"광주전남","순천","여수소라#1 T/L","154kV 여수소라#1T/L 정밀점검","19년 가공송전 순시점검 위탁공사 여수ST~소라ST 정밀점검","2019-05-27 08:00","2019-05-28 18:00","2019-05-27 08:00","2019-05-28 18:00","매일"]
[354,"광주전남","순천","여수소라#2 T/L","154kV 여수소라#2T/L 정밀점검","19년 가공송전 순시점검 위탁공사 여수ST~소라ST 정밀점검","2019-05-07 08:00","2019-05-08 18:00","2019-05-07 08:00","2019-05-08 18:00","매일"]
[355,"광주전남","순천","여수TP용성#2 T/L","19년 순천전력지사 170kV GIS 정밀점검","여수화력 : 여수T/P-용성#2T/L GIS 정밀점검","2019-05-07 09:00","2019-05-08 18:00","취소","취소","연속"]
[356,"광주전남","순천","여수TP여천#1 T/L","18~19년 변전 정비회사 총액공사","여천S/S : 여수T/P-여천#1T/L GIS, LA 보통 여수화력 : 여수T/P-여천#1T/L GIS 보통, CT단자대 교체","2019-05-10 09:00","2019-05-10 18:00","2019-05-10 09:00","2019-05-10 18:00","당일"]
[357,"광주전남","순천","여수TP여천#2 T/L","18~19년 변전 정비회사 총액공사","여천S/S : 여수T/P-여천#2T/L GIS, LA 보통 여수화력 : 여수T/P-여천#2T/L GIS 보통, CT단자대 교체","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-09 18:00","당일"]
[358,"광주전남","순천","여천호남TP#2 T/L","18~19년 변전 정비회사 총액공사","여천S/S : 여천-호남T/P#2T/L GIS 보통 호남화력 : 여천-호남T/P#2T/L GIS CB Time측정","2019-05-17 09:00","2019-05-17 18:00","2019-05-17 09:00","2019-05-17 18:00","당일"]
[359,"광주전남","순천","여천S/S 154kV LG화학여수T/L GIS","19년 순천전력지사 170kV GIS 정밀점검","여천 : LG화학-여수T/L(운휴) GIS 정밀점검","2019-05-21 09:00","2019-05-23 18:00","2019-05-21 09:00","2019-05-23 18:00","연속"]
[360,"광주전남","순천","여수산단S/S YNCC#1T/L CB","154kV YNCC#1T/L 취약지지물 교체공사","18~19년 송전정비 협력회사 총액공사 154kV YNCC#1T/L 취약지지물 교체공사","2019-05-30 08:00","2019-06-03 18:00","2019-05-30 08:00","2019-06-03 18:00","연속"]
[361,"광주전남","순천","여천여수산단#1 T/L","19년 순천전력지사 170kV GIS 정밀점검","여천 : 여천-여수산단#1T/L GIS 정밀점검","2019-05-30 09:00","2019-05-31 18:00","2019-05-30 09:00","2019-05-31 18:00","연속"]
[362,"광주전남","순천","여천S/S 154kV YNCC#1T/L GIS","19년 순천전력지사 170kV GIS 정밀점검","여천 : YNCC#1T/L(운휴) GIS 정밀점검","2019-05-27 09:00","2019-05-28 18:00","2019-05-27 09:00","2019-05-28 18:00","연속"]
[363,"광주전남","순천","율촌화치#1 T/L","19년 변전 정비회사 총액공사","* 율촌S/S 율촌-화치#1T/L CB타임측정 * 화치S/S 율촌-화치#1T/L GIS 보통점검","2019-05-13 09:00","2019-05-13 18:00","2019-05-13 09:00","2019-05-13 18:00","당일"]
[364,"광주전남","순천","율촌화치#2 T/L","19년 변전 정비회사 총액공사","* 율촌S/S 율촌-화치#2T/L CB타임측정 * 화치S/S 율촌-화치#2T/L GIS 보통점검","2019-05-14 09:00","2019-05-14 18:00","2019-05-14 09:00","2019-05-14 18:00","당일"]
[365,"광주전남","직할","남광주금천#1 T/L","154kV 금천S/S #3M.Tr 증설공사","○154kV #2BUS 무부하 시험가압용(24시간 이상) ----------------------- ○154/23kV M.Tr 1BANK 설치 ○170kV GIS 1CCT 설치 ○25.8kV SIS 4CCT 설치 ○ 기타 부대공사 1식","2019-05-16 14:00","2019-05-17 14:00","2019-05-16 14:00","2019-05-17 14:00","연속"]
[366,"광주전남","직할","남광주금천#1 T/L","154kV 금천S/S #3M.Tr 증설공사","○154kV #1BUS 무부하 시험가압용(24시간 이상) ----------------------- ○154/23kV M.Tr 1BANK 설치 ○170kV GIS 1CCT 설치 ○25.8kV SIS 4CCT 설치 ○ 기타 부대공사 1식","2019-05-09 14:00","2019-05-10 14:00","2019-05-09 14:00","2019-05-10 14:00","연속"]
[367,"광주전남","직할","나주금천#2 T/L","154kV 금천S/S #3M.Tr 증설공사","○154kV #2BUS 무부하 시험가압용(24시간 이상) ----------------------- ○154/23kV M.Tr 1BANK 설치 ○170kV GIS 1CCT 설치 ○25.8kV SIS 4CCT 설치 ○ 기타 부대공사 1식","2019-05-02 14:00","2019-05-03 14:00","2019-05-02 14:00","2019-05-03 14:00","연속"]
[368,"광주전남","직할","나주금천#1 T/L","154kV 나주S/S 옥내화 인출정비공사","□ 변전(7) : 보호반대체(3), 통신(2), 계통시험(2) □ 송전(5/29~6/1): C/H설치 가선 및 LA설치(2), EBA 선로접속(2) □ 통신 : OPGW 설치 및 시험(2) [나주-금천#1T/L]","2019-05-29 07:00","2019-06-04 18:00","2019-05-29 07:00","2019-06-04 18:00","연속"]
[369,"광주전남","직할","신화순나주#2 T/L","154kV 나주S/S 옥내화 인출정비공사","□ 변전(7) : 보호반대체(3), 통신(2), 계통시험(2) □ 송전(5/29~6/2): C/H설치 가선 및 LA설치(2), EBA 선로접속(2)","2019-05-29 07:00","2019-06-04 18:00","2019-05-29 07:00","2019-06-04 18:00","연속"]
[370,"광주전남","직할","남광주금천#2 T/L","남광주S/S 154kV 남광주-금천 #2T/L (GIS 정밀점검)","2019년 직할 170kV GIS 정밀점검공사 - 내용 : CB, 상부 BUS, C/H 내부 정밀점검","2019-05-20 09:00","2019-05-21 18:00","2019-05-20 09:00","2019-05-21 18:00","연속"]
[371,"광주전남","직할","농성화정#2 T/L","[변전] 18-19년 직할협력회사 총액공사","○ 장기미동작차단기 점검","2019-05-08 13:00","2019-05-08 18:00","2019-05-08 13:00","2019-05-08 18:00","당일"]
[372,"광주전남","직할","농성화정#1 T/L","[변전] 18-19년 직할협력회사 총액공사","○ 장기미동작차단기 점검","2019-05-08 09:00","2019-05-08 12:00","2019-05-08 09:00","2019-05-08 12:00","당일"]
[373,"광주전남","직할","신화순매월#2 T/L","154kV 효천1 신화순-매월 T/L 송전선로 이설공사","광주효천 1지구 택지지구내 154kV 신화순-매월 T/L No.69~70호의 일부 구간 지중화를 위하여 임시선로를 구성하고 C/H철탑 2기를 건설 후 본 선로에 연결하기 위함","2019-05-01 07:00","2019-05-05 18:00","2019-05-01 07:00","2019-05-05 18:00","연속"]
[374,"광주전남","직할","신화순매월#1 T/L","154kV 효천1 신화순-매월 T/L 송전선로 이설공사","광주효천 1지구 택지지구내 154kV 신화순-매월 T/L No.69~70호의 일부 구간 지중화를 위하여 임시선로를 구성하고 C/H철탑 2기를 건설 후 본 선로에 연결하기 위함","2019-05-01 07:00","2019-05-05 18:00","2019-05-06 07:00","2019-05-10 18:00","연속"]
[375,"광주전남","직할","매월화정#2 T/L","매월S/S 154kV 매월-화정 #2T/L (GIS 정밀점검)","2019년 직할 170kV GIS 정밀점검공사 - 내용 : CB, 상부BUS, C/H 내부 정밀점검","2019-05-16 09:00","2019-05-18 18:00","2019-05-16 09:00","2019-05-18 18:00","연속"]
[376,"광주전남","직할","매월화정#1 T/L","매월S/S 154kV 매월-화정 #1T/L (GIS 정밀점검)","2019년 직할 170kV GIS 정밀점검공사 - 내용 : CB, 상부BUS, C/H 내부 정밀점검","2019-05-13 09:00","2019-05-15 18:00","취소","취소","연속"]
[377,"광주전남","광주","신광주곡성#2 T/L","19년 광주변전총액공사","신광주-곡성#2T/L GIS 하자점검, CVT 보통점검","2019-05-24 09:00","2019-05-24 18:00","2019-05-24 09:00","2019-05-24 18:00","당일"]
[378,"광주전남","광주","신광주곡성#1 T/L","19년 광주변전총액공사","신광주-곡성#1T/L GIS 하자점검","2019-05-27 09:00","2019-05-27 18:00","2019-05-27 09:00","2019-05-27 18:00","연속"]
[379,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성 #1T/L(자기애관 교체공사)","154kV 여수TP-용성 #1T/L 자기애관을 폴리머애관으로 교체(6대)","2019-05-18 09:00","2019-05-19 18:00","취소","취소","연속"]
[380,"대구","경산","진량노변 T/L","노변S/S 진량노변 T/L 조작시험","장기미동작 차단기 조작시험","2019-05-12 09:00","2019-05-12 14:00","2019-05-12 09:00","2019-05-12 14:00","당일"]
[381,"대구","경산","하양반야월#2 T/L","일진제 PMJ 중간접속함 교체공사","일진제 PMJ 중간접속함 교체공사","2019-05-06 09:00","2019-05-19 18:00","2019-05-06 09:00","2019-05-19 18:00","연속"]
[382,"대구","경산","신경산진량 T/L","EBA절연유 채유","EBA절연유 채유","2019-05-31 09:00","2019-05-31 18:00","취소","취소","당일"]
[383,"대구","경산","안심대구그린파워#1 T/L","안심S/S 안심-신서열병합#1T/L EBG 해체점검","안심S/S 안심-신서열병합 EBG 해체점검","2019-05-07 09:00","2019-05-11 18:00","취소","취소","연속"]
[384,"대구","달성","대구범물#1 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사(TL보호반 대체)","2019-05-07 09:00","2019-05-08 18:00","2019-05-16 09:00","2019-05-17 18:00","연속"]
[385,"대구","달성","대구범물#2 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사(TL보호반 대체)","2019-05-09 09:00","2019-05-10 18:00","2019-05-20 09:00","2019-05-21 18:00","연속"]
[386,"대구","달성","상인봉덕#1 T/L","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사(TEST선로)","2019-05-28 13:00","2019-05-28 18:00","2019-05-28 13:00","2019-05-28 18:00","매일"]
[387,"대구","달성","상인봉덕#1 T/L","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사(TEST선로)","2019-05-30 13:00","2019-05-30 18:00","2019-05-30 13:00","2019-05-30 18:00","매일"]
[388,"대구","직할","동인공평#2 T/L","공평S/S 170kV GIS 정밀점검(TEST선로)","공평S/S 170kV GIS 정밀점검(TEST선로)","2019-05-24 13:00","2019-05-25 18:00","2019-05-24 13:00","2019-05-25 18:00","매일"]
[389,"대구","직할","동인공평#2 T/L","공평S/S 동인-공평#2T/L GIS 정밀점검","공평S/S 동인-공평#2T/L GIS 정밀점검","2019-05-20 09:00","2019-05-22 18:00","2019-05-20 09:00","2019-05-22 18:00","연속"]
[390,"대구","직할","범물남대구#1 T/L","EBA 절연유 채유","EBA 절연유 채유","2019-05-02 09:00","2019-05-02 18:00","2019-05-02 09:00","2019-05-02 18:00","당일"]
[391,"대구","직할","범물남대구#2 T/L","EBA 절연유 채유","EBA 절연유 채유","2019-05-03 09:00","2019-05-03 18:00","2019-05-03 09:00","2019-05-03 18:00","당일"]
[392,"대구","직할","동인내당#1 T/L","OF케이블 절연유 채유","OF케이블 절연유 채유","2019-05-27 09:00","2019-05-27 18:00","2019-05-27 09:00","2019-05-27 18:00","당일"]
[393,"대구","직할","동인내당#2 T/L","OF케이블 절연유 채유","OF케이블 절연유 채유","2019-05-28 09:00","2019-05-28 18:00","2019-05-28 09:00","2019-05-28 18:00","당일"]
[394,"대구","직할","노변효목#1 T/L","EBA절연유 채유","EBA절연유 채유","2019-05-10 09:00","2019-05-10 18:00","2019-05-10 09:00","2019-05-10 18:00","당일"]
[395,"대구","칠곡","북대구관음#2 T/L","관음S/S 북대구-관음#1,2T/L LA 교체","관음S/S 북대구-관음#1,2T/L LA 교체","2019-05-30 09:30","2019-05-30 18:00","2019-05-30 09:30","2019-05-30 18:00","당일"]
[396,"대구","칠곡","북대구관음#1 T/L","관음S/S 북대구-관음#1,2T/L LA 교체","관음S/S 북대구-관음#1,2T/L LA 교체","2019-05-30 09:30","2019-05-30 18:00","2019-05-30 09:30","2019-05-30 18:00","당일"]
[397,"대구","칠곡","구미광평#2 T/L","광평S/S 구미-광평#2T/L GIS 보통점검","광평S/S 구미-광평#2T/L GIS 보통점검","2019-05-10 09:30","2019-05-10 15:00","2019-05-10 09:30","2019-05-10 15:00","당일"]
[398,"대구","포항","건천천북#1 T/L","포항 가공송전 154kV 건천-천북#1T/L SB댐퍼 설치","154kV 건천-천북/L No. 21~96(25기)","2019-05-20 08:00","2019-05-21 18:00","2019-05-20 08:00","2019-05-21 18:00","연속"]
[399,"대구","포항","건천천북#2 T/L","포항 가공송전 154kV 건천-천북#2T/L SB댐퍼 설치","154kV 건천-천북/L No. 21~96(25기)","2019-05-14 08:00","2019-05-15 18:00","2019-05-14 08:00","2019-05-15 18:00","연속"]
[400,"경북","구미","청리상주#1 T/L","2019년도 구미전력지사 변전정비업체 총액공사","- 와이피피제 보호계전기 성능개선 - LA대체공사 - GIS보통점검","2019-05-21 07:00","2019-05-21 14:00","2019-05-21 07:00","2019-05-21 14:00","당일"]
[401,"경북","구미","상주S/S 154kV #60-#65 BUS TIE GIS","2019년도 구미전력지사 변전정비업체 총액공사","- GIS보통점검","2019-05-09 09:00","2019-05-09 18:00","2019-05-09 09:00","2019-05-09 18:00","당일"]
[402,"경북","구미","청리상주#2 T/L","2019년도 구미전력지사 변전정비업체 총액공사","- 와이피피제 보호계전기 성능개선 - LA대체공사 - GIS보통점검","2019-05-21 14:00","2019-05-21 18:00","2019-05-21 14:00","2019-05-21 18:00","당일"]
[403,"경북","영주","점촌문경 T/L","154kV 점촌S/S #4M.Tr 증설공사 (안전이격거리 확보)","154kV 점촌S/S #4M.Tr 증설공사 - 6433GIS 증설관련 안전이격거리확보 (즉시가압조건)","2019-05-03 09:00","2019-05-04 18:00","2019-05-03 09:00","2019-05-04 18:00","매일"]
[404,"경북","직할","신영주안동#1 T/L","154kV 신영주-안동T/L 정밀점검","154kV 신영주-안동#1T/L 정밀점검 (No.57~97/41기)","2019-05-27 08:00","2019-05-29 18:00","2019-05-27 08:00","2019-05-29 18:00","연속"]
[405,"경북","직할","신영주안동#2 T/L","154kV 신영주-안동T/L 정밀점검","154kV 신영주-안동#2T/L 정밀점검 (No.57~97/41기)","2019-05-30 08:00","2019-06-03 18:00","2019-05-30 08:00","2019-06-03 18:00","연속"]
[406,"경북","직할","울진현종산풍력 T/L","154kV 울진-현종산풍력#1T/L 정밀점검","154kV 울진-현종산풍력#1T/L 정밀점검 No.53~104","2019-05-14 09:00","2019-05-17 18:00","2019-05-14 09:00","2019-05-17 18:00","연속"]
[407,"경북","직할","현종산풍력평해#2 T/L","154kV 현종산풍력-평해#2T/L 정밀점검","154kV 현종산풍력-평해#2T/L 정밀점검(No.14~87)","2019-05-07 07:00","2019-05-13 18:00","취소","취소","연속"]
[408,"경북","청리","선산청리#2T/L","345kV 선산분기 등 12개T/L 송전선로용 피뢰기 설치공사 ","154kV 선산-청리T/L 송전선로용 피뢰기 설치공사 ","2019-05-20 07:00","2019-05-20 18:00","2019-05-20 07:00","2019-05-20 18:00","연속"]
[409,"부산울산","동부산","구서노포#2 T/L","구서E/C 170kV GIS 보통점검","1.구서E/C 170kV 617GIS 보통점검 2. 노포E/C 617GIS 조작시험","2019-05-09 09:30","2019-05-09 17:00","2019-05-09 09:30","2019-05-09 17:00","당일"]
[410,"부산울산","동부산","신울산명례#2 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 대상선로/작업내용 : 154kV 신울산-명례#2T/L/송전선로용 피뢰기 설치(No.1 ~43, 43기)","2019-05-13 08:00","2019-05-17 18:00","2019-05-13 08:00","2019-05-17 18:00","연속"]
[411,"부산울산","동부산","명례정관 T/L","2019년 가공송전 순시점검 위탁공사-동부산","송전선로 정밀점검 구간 : 명례C/H ~ 4호(4기)","2019-05-03 09:00","2019-05-03 18:00","2019-05-03 09:00","2019-05-03 18:00","당일"]
[412,"부산울산","동부산","웅촌서창#2 T/L","2018-2019년 동부산전력지사 송전정비 협력회사 총액공사","애자교체 구간 : 21~23호(3기)","2019-05-13 09:00","2019-05-13 18:00","2019-05-13 09:00","2019-05-13 18:00","당일"]
[413,"부산울산","동부산","웅촌서창#2 T/L","2018-2019년 동부산전력지사 송전정비 협력회사 총액공사","애자교체 구간 : 21~23호(3기)","2019-05-13 09:00","2019-05-13 18:00","취소","취소","당일"]
[414,"부산울산","북부산","매리김해#2 T/L","2018년 북부산 변전협력회사 총액공사","김해S/S 154kV 매리-김해#2T/L 미동작점검","2019-05-09 10:00","2019-05-09 18:00","2019-05-09 10:00","2019-05-09 18:00","당일"]
[415,"부산울산","북부산","김해어방#2 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","154kV 김해-어방#2T/L 피뢰기 설치공사(1, 2호)","2019-05-08 07:00","2019-05-08 12:00","2019-05-08 07:00","2019-05-08 12:00","당일"]
[416,"부산울산","북부산","김해어방#1 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","154kV 김해-어방#2T/L 피뢰기 설치공사(1, 2호) - 154kV 김해-어방#1T/L(안전이격 휴전)","2019-05-08 07:00","2019-05-08 12:00","2019-05-08 07:00","2019-05-08 12:00","당일"]
[417,"부산울산","북부산","북부산S/S 154kV #60-#65 BUS TIE CB","2019년 북부산 변전협력회사 총액공사","북부산S/S 154kV 6100 Bus-Tie 미동작점검","2019-05-28 14:00","2019-05-28 18:00","2019-05-28 14:00","2019-05-28 18:00","당일"]
[418,"부산울산","북부산","북부산S/S 154kV #60-#61 SEC CB","2019년 북부산 변전협력회사 총액공사","북부산S/S 154kV 60-61-0 Bus-section 미동작점검","2019-05-10 14:00","2019-05-10 18:00","2019-05-10 14:00","2019-05-10 18:00","당일"]
[419,"부산울산","북부산","북부산S/S 154kV #62-#67 BUS TIE CB","2019년 북부산 변전협력회사 총액공사","북부산S/S 154kV 6300 Bus-Tie 미동작점검","2019-05-10 10:00","2019-05-10 14:00","2019-05-10 10:00","2019-05-10 14:00","당일"]
[420,"부산울산","북부산","북부산S/S 154kV #61-#66 BUS TIE CB","2019년 북부산 변전협력회사 총액공사","북부산S/S 154kV 6200 Bus-Tie 미동작점검","2019-05-28 10:00","2019-05-28 14:00","2019-05-28 10:00","2019-05-28 14:00","당일"]
[421,"부산울산","북부산","북부산구포#1 T/L","2019년 북부산 변전협력회사 총액공사","북부산S/S 154kV 북부산-구포#1T/L 미동작점검","2019-05-21 10:00","2019-05-21 14:00","2019-05-21 10:00","2019-05-21 14:00","당일"]
[422,"부산울산","북부산","삼계어방#2 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","154kV 삼계-어방#1T/L 피뢰기 설치공사(1~46호) - 154kV 삼계-어방#2T/L(안전이격 휴전)","2019-05-04 07:00","2019-05-05 18:00","2019-05-04 07:00","2019-05-05 18:00","매일"]
[423,"부산울산","북부산","한림정삼계#2 T/L","154kV 매리-김해 등 9개T/L 피뢰기 설치공사","154kV 삼계-어방#1T/L 피뢰기 설치공사(1~46호) - 154kV 한림정-삼계#2T/L(안전이격 휴전)","2019-05-06 07:00","2019-05-06 18:00","2019-05-06 07:00","2019-05-06 18:00","연속"]
[424,"부산울산","북부산","김해어방#1 T/L","154㎸ 물금-삼랑진등 6개 T/L 자기애관 교체공사","자기애관 → 폴리머 애관 교체","2019-05-01 09:00","2019-05-03 18:00","2019-05-01 09:00","2019-05-03 18:00","연속"]
[425,"부산울산","북부산","김해어방#2 T/L","154㎸ 물금-삼랑진등 6개 T/L 자기애관 교체공사","154㎸ 김해-어방 #1 T/L 자기애관 교체 관련 안전이격 확보","2019-05-01 09:00","2019-05-01 18:00","2019-05-01 09:00","2019-05-01 18:00","당일"]
[426,"부산울산","북부산","삼계어방#1 T/L","154㎸ 물금-삼랑진등 6개 T/L 자기애관 교체공사","자기애관 → 폴리머 애관 교체","2019-05-04 09:00","2019-05-07 09:00","2019-05-04 09:00","2019-05-07 09:00","연속"]
[427,"부산울산","북부산","서부산엄궁#1 T/L","2019년 북부산 변전협력회사 총액공사","엄궁S/S 154kV 서부산-엄궁#1T/L 미동작점검","2019-05-23 10:00","2019-05-23 14:00","2019-05-23 10:00","2019-05-23 14:00","당일"]
[428,"부산울산","북부산","모라엄궁#2 T/L","2019년 북부산 변전협력회사 총액공사","엄궁S/S 154kV 모라-엄궁#2T/L 미동작점검","2019-05-16 10:00","2019-05-16 14:00","2019-05-16 10:00","2019-05-16 14:00","당일"]
[429,"부산울산","북부산","호포매리#1 T/L","2019년 북부산 변전협력회사 총액공사","호포S/S 154kV 호포-매리1T/L 미동작 점검","2019-05-11 10:00","2019-05-11 18:00","2019-05-11 10:00","2019-05-11 18:00","당일"]
[430,"부산울산","북부산","호포매리#2 T/L","2019년 북부산 변전협력회사 총액공사","호포S/S 154kV 호포-매리2T/L 미동작 점검","2019-05-12 10:00","2019-05-12 18:00","2019-05-12 10:00","2019-05-12 18:00","당일"]
[431,"부산울산","서부산","신김해지사#2 T/L","19년 서부산전력지사 GIS 정밀점검공사","지사S/S 신김해-지사#2T/L(6C7)GIS 정밀점검 - 차단기, 상부BUS, 인출DS 정밀점검","2019-05-23 08:00","2019-05-24 18:00","2019-05-23 08:00","2019-05-24 18:00","연속"]
[432,"부산울산","서부산","신김해지사#1 T/L","19년 서부산전력지사 GIS 정밀점검공사","지사S/S 신김해-지사#1T/L(687)GIS 정밀점검 - 차단기, 상부BUS, 인출DS 정밀점검","2019-05-27 08:00","2019-05-28 18:00","2019-05-27 08:00","2019-05-28 18:00","연속"]
[433,"부산울산","울산","신울산영남TP#1 T/L","154kV 두왕E/C 건설사업","-신울산-영남T/P #1T/L 보호반 대체작업 -파이분기 긴선작업 -무부하가압(5.31~6.1), 사용전검사(6.3~5), 실부하가압(6.5)","2019-05-27 08:30","2019-06-07 18:00","2019-05-27 08:30","2019-06-07 18:00","연속"]
[434,"부산울산","울산","신울산웅촌#2 T/L","18~19년 변전협력 총액공사","- 667차단기 동작시험(신울산S/S) - 627차단기 동작시험(웅촌S/S)","2019-05-02 13:00","2019-05-02 18:00","2019-05-02 13:00","2019-05-02 18:00","당일"]
[435,"부산울산","울산","신울산웅촌#1 T/L","18~19년 변전협력 총액공사","- 657차단기 동작시험(신울산S/S) - 647차단기 동작시험(웅촌S/S)","2019-05-02 09:00","2019-05-02 12:00","2019-05-02 09:00","2019-05-02 12:00","당일"]
[436,"부산울산","울산","신울산명례#1 T/L","2019년 가공송전 순시점검 위탁공사-동부산","송전선로 정밀점검 구간 : 신울산E/C ~ 명례C/H(43기)","2019-05-07 09:00","2019-05-10 18:00","2019-05-07 09:00","2019-05-10 18:00","연속"]
[437,"부산울산","울산","신울산옥동#1 T/L","'19년도 장기사용 170kV GIS 대체공사","'19년도 장기사용 170kV GIS 대체공사 - 옥동E/C측 GIS 대체대상설비","2019-05-07 08:00","2019-05-31 18:00","2019-05-07 08:00","2019-05-31 18:00","연속"]
[438,"부산울산","울산","신온산온산#2 T/L","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","- 154kV #3M.Tr 1차 시험가압선로 1H","2019-05-10 17:00","2019-05-10 18:00","2019-05-24 17:00","2019-05-24 18:00","당일"]
[439,"부산울산","울산","신온산온산#1 T/L","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","- 154kV #1M.Tr 1차 시험가압선로 1H","2019-05-08 17:00","2019-05-08 18:00","2019-05-17 17:00","2019-05-17 18:00","당일"]
[440,"부산울산","울산","온산처용#2 T/L","154kV 온산-처용#2T/L 송전선로용 피뢰기 설치공사","- 송전선로용 피뢰기 설치공사 : 1~20호(19기)","2019-05-01 08:00","2019-05-02 18:00","2019-05-01 08:00","2019-05-02 18:00","연속"]
[441,"부산울산","울산","용연울산TP#1 T/L","154kV 용연-울산TP #1T/L 불량금구류 교체공사","ㅁ 작업내용 : 불량금구류 교체 ㅁ 선로명 : 154kV 용연-울산TP #1T/L ㅁ 작업개소 : No.4,5,7,9(4기)","2019-05-20 08:00","2019-05-21 14:00","2019-05-20 08:00","2019-05-21 14:00","연속"]
[442,"부산울산","울산","용연울산TP#2 T/L","154kV 용연-울산TP #2T/L 불량금구류 교체공사","ㅁ 작업내용 : 불량금구류 교체 ㅁ 선로명 : 154kV 용연-울산TP #2T/L ㅁ 작업개소 : No.1(1기)","2019-05-21 14:00","2019-05-21 18:00","2019-05-21 14:00","2019-05-21 18:00","당일"]
[443,"부산울산","울산","울산울산TP#1 T/L","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 154kV SK케미칼T/L GIS 케이블헤드 단말처리 관련 안전이격","2019-05-07 09:00","2019-05-07 18:00","2019-05-07 09:00","2019-05-07 18:00","당일"]
[444,"부산울산","울산","울산울산TP#1 T/L","울산화력S/Y 154kV SK케미칼T/L 지중케이블 접속작업","울산화력S/Y 154kV SK케미칼T/L 지중케이블 접속작업 - 지중케이블 내압시험후 GIS 내부도체연결작업(크레인 사용 안전이격","2019-05-02 09:00","2019-05-03 18:00","2019-05-02 09:00","2019-05-03 18:00","연속"]
[445,"부산울산","울산","신울산울산#1 T/L","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","- 154kV #1Sh.C Main GIS 정밀점검 시험가압선로 1H","2019-05-25 17:00","2019-05-25 18:00","2019-05-25 17:00","2019-05-25 18:00","당일"]
[446,"부산울산","울산","신울산웅촌#1 T/L","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","- 154kV #1M.Tr 1차 시험가압선로 1H","2019-05-16 17:00","2019-05-16 18:00","2019-05-08 17:00","2019-05-08 18:00","당일"]
[447,"부산울산","울산","신울산웅촌#2 T/L","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","- 154kV #2M.Tr 1차 시험가압선로 1H","2019-05-21 17:00","2019-05-21 18:00","2019-05-10 17:00","2019-05-10 18:00","당일"]
[448,"부산울산","울산","신울산웅촌#1 T/L","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","- 154kV #1BUS TIE 정밀점검 시험가압선로 1H","2019-05-23 17:00","2019-05-23 18:00","2019-05-23 17:00","2019-05-23 18:00","당일"]
[449,"부산울산","울산","용연처용#2 T/L","18~19년 변전협력 총액공사","- GIS 초기점검","2019-05-22 09:00","2019-05-22 18:00","2019-05-22 09:00","2019-05-22 18:00","당일"]
[450,"부산울산","울산","용연처용#1 T/L","18~19년 변전협력 총액공사","- GIS 초기점검","2019-05-24 09:00","2019-05-24 18:00","2019-05-24 09:00","2019-05-24 18:00","당일"]
[451,"부산울산","직할","범일서면#2 T/L","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 범일-서면#2T/L(627) GIS 정밀점검 -차단부 및 상부BUS, Cable Head부 정밀점검 -모선DS부 점검","2019-05-21 10:00","2019-05-23 20:00","2019-05-21 10:00","2019-05-23 20:00","연속"]
[452,"부산울산","직할","서면S/S 154kV #60 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 범일-서면#1T/L(617)GIS #1DS부 정밀점검","2019-05-15 10:00","2019-05-16 20:00","2019-05-15 10:00","2019-05-16 20:00","연속"]
[453,"부산울산","직할","서면S/S 154kV #60 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 미남-서면#1T/L(637)GIS #1DS부 정밀점검","2019-05-29 10:00","2019-05-30 20:00","2019-05-29 10:00","2019-05-30 20:00","연속"]
[454,"부산울산","직할","서면S/S 154kV #65 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 범일-서면#1T/L(617)GIS #2DS부 정밀점검","2019-05-14 10:00","2019-05-14 20:00","2019-05-14 10:00","2019-05-14 20:00","당일"]
[455,"부산울산","직할","범일서면#1 T/L","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 범일-서면#1T/L(617) GIS 정밀점검 -차단부 및 상부BUS, Cable Head부 정밀점검 -모선DS부 점검","2019-05-14 10:00","2019-05-16 20:00","2019-05-14 10:00","2019-05-16 20:00","연속"]
[456,"부산울산","직할","서면S/S 154kV #60 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 범일-서면#2T/L(627)GIS #1DS부 정밀점검","2019-05-22 10:00","2019-05-23 20:00","2019-05-22 10:00","2019-05-23 20:00","연속"]
[457,"부산울산","직할","서면S/S 154kV #65 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 범일-서면#2T/L(627)GIS #2DS부 정밀점검","2019-05-21 10:00","2019-05-21 20:00","2019-05-21 10:00","2019-05-21 20:00","당일"]
[458,"부산울산","직할","서면S/S 154kV #65 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 미남-서면#1T/L(637)GIS #2DS부 정밀점검","2019-05-28 10:00","2019-05-28 20:00","2019-05-28 10:00","2019-05-28 20:00","당일"]
[459,"부산울산","직할","양정범천 T/L","2019년 직할 변전협력회사 총액공사","- 양정S/S 양정-범천T/L GIS 미동작점검 - 범천S/S 양정-범천T/L GIS 미동작점검","2019-05-08 10:00","2019-05-08 18:00","2019-05-08 10:00","2019-05-08 18:00","당일"]
[460,"부산울산","직할","수정범일#2 T/L","2019년 상반기 직할 170kV GIS 정밀점검공사","수정S/S 170kV 6333 GIS 시험가압선로 -CB부 및 상부모선 시험가압(2시간)","2019-05-10 18:00","2019-05-10 20:00","2019-05-10 18:00","2019-05-10 20:00","연속"]
[461,"부산울산","직할","수정범일#1 T/L","2019년 상반기 직할 170kV GIS 정밀점검공사","수정S/S 170kV 6133 GIS 시험가압선로 -CB부 및 상부모선 시험가압(2시간)","2019-05-03 18:00","2019-05-03 20:00","2019-05-03 18:00","2019-05-03 20:00","연속"]
[462,"부산울산","직할","수정범일#2 T/L","2019년 상반기 직할 170kV GIS 정밀점검공사","수정S/S 170kV 6233 GIS 시험가압선로 -CB부 및 상부모선 시험가압(2시간)","2019-05-08 18:00","2019-05-08 20:00","2019-05-08 18:00","2019-05-08 20:00","연속"]
[463,"경남","직할","창원완암#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-05-22 07:00","2019-05-24 18:00","2019-05-22 07:00","2019-05-24 18:00","연속"]
[464,"경남","직할","창원완암#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-05-22 07:00","2019-05-27 18:00","2019-05-22 07:00","2019-05-24 18:00","연속"]
[465,"경남","직할","완암안민#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-05-25 07:00","2019-05-29 18:00","2019-05-25 07:00","2019-05-29 18:00","연속"]
[466,"경남","직할","완암안민#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-05-25 07:00","2019-05-27 18:00","2019-05-25 07:00","2019-05-27 18:00","연속"]
[467,"경남","직할","창원완암#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-05-28 07:00","2019-05-29 18:00","2019-05-28 07:00","2019-05-29 18:00","연속"]
[468,"경남","직할","수출월림#2 T/L","월림S/S 154kV 수출-월림#2T/L CB 보통점검","월림S/S 154kV 수출-월림#2T/L CB 보통점검","2019-05-27 09:30","2019-05-27 17:30","2019-05-27 09:30","2019-05-27 17:30","당일"]
[469,"경남","진주","사천개양#2 T/L","개양S/S 사천-개양#2T/L(657) 조작시험","개양S/S 사천-개양#2T/L(657) 조작시험","2019-05-09 10:00","2019-05-09 14:00","2019-05-09 10:00","2019-05-09 14:00","당일"]
[470,"경남","진주","동진주진주#2 T/L","동진주S/S 동진주-진주#2T/L(647) 조작시험","동진주S/S 동진주-진주#2T/L(647) 조작시험 [병행] 진주S/S 동진주-진주#2T/L(637) 조작시험","2019-05-25 13:00","2019-05-25 15:00","2019-05-25 09:00","2019-05-25 14:00","당일"]
[471,"경남","진주","동진주진주#1 T/L","동진주S/S 동진주-진주#1T/L(637) 조작시험","동진주S/S 동진주-진주#1T/L(637) 조작시험","2019-05-25 09:30","2019-05-25 12:00","2019-05-25 14:00","2019-05-25 18:00","당일"]
[472,"경남","진주","사봉개양#1 T/L","154kV 사봉-개양#1T/L 송전선로 초기점검","154kV 사봉-개양#1T/L 송전선로 초기점검","2019-05-11 09:00","2019-05-11 12:00","2019-05-07 09:00","2019-05-07 12:00","당일"]
[473,"경남","진주","사봉개양#2 T/L","154kV 사봉-개양#2T/L 송전선로 초기점검","154kV 사봉-개양#2T/L 송전선로 초기점검","2019-05-11 13:00","2019-05-11 17:00","2019-05-07 13:00","2019-05-07 17:00","당일"]
[474,"경남","진주","산청함양 T/L","산청S/S #2M.Tr 용량변경공사","#2M.Tr 시험가압 (24시간)","2019-05-28 13:00","2019-05-29 13:00","2019-05-28 13:00","2019-05-29 13:00","연속"]
[475,"경남","진주","의령S/S 154kV #60-#65 BUS TIE CB","의령S/S 154kV #60-#65 BUSTIE CB(6100) 조작시험","의령S/S 154kV #60-#65 BUSTIE CB(6100) 조작시험","2019-05-16 10:00","2019-05-16 12:00","2019-05-16 10:00","2019-05-16 12:00","당일"]
[476,"경남","진주","함양거창#1 T/L","함양S/S 함양-거창#1T/L(687) 조작시험","함양S/S 함양-거창#1T/L(687) 조작시험","2019-05-21 10:00","2019-05-21 14:00","2019-05-21 10:00","2019-05-21 14:00","당일"]
[477,"경남","진주","산청함양 T/L","154kV 산청-함양T/L 애자련보강공사","154kV 산청-함양T/L 애자련보강공사","2019-05-08 07:30","2019-05-09 18:00","2019-05-08 07:30","2019-05-09 18:00","연속"]
[478,"경남","진주","함양거창#2 T/L","함양S/S 함양-거창#2T/L(677) 조작시험","함양S/S 함양-거창#2T/L(677) 조작시험","2019-05-21 14:00","2019-05-21 17:00","2019-05-21 14:00","2019-05-21 17:00","당일"]
[479,"경남","진주","쌍림합천#1 T/L","합천S/S 쌍림-합천#1T/L CB(657) 조작시험","합천S/S 쌍림-합천#1T/L CB(657) 조작시험","2019-05-20 10:00","2019-05-20 14:00","2019-05-20 10:00","2019-05-20 14:00","당일"]
[480,"경남","진주","쌍림합천#2 T/L","합천S/S 쌍림-합천#2T/L CB(667) 조작시험","합천S/S 쌍림-합천#2T/L CB(667) 조작시험","2019-05-20 14:00","2019-05-20 17:00","2019-05-20 14:00","2019-05-20 17:00","당일"]
[481,"경남","통영","통영거제#1 T/L","154kV 통영-거제#1T/L 정밀점검","154kV 통영-거제#1T/L 정밀점검","2019-05-25 09:00","2019-05-26 18:00","2019-05-25 09:00","2019-05-26 18:00","매일"]
[482,"경남","통영","신고성S/S 154kV #65 BUS","삼천포,신고성S/S 용량부족차단기 대체공사","#4M.Tr 1차 인출변경 관련 위상체크","2019-05-31 14:00","2019-05-31 18:00","2019-05-31 14:00","2019-05-31 18:00","당일"]
[483,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 피뢰기 설치공사","154kV 신고성-거제#2T/L 피뢰기 설치공사","2019-05-04 07:00","2019-05-05 18:00","2019-05-04 07:00","2019-05-05 18:00","매일"]
[484,"경남","통영","신고성고성 T/L","154kV 신고성-거제#2T/L 피뢰기 설치 안전확보차","154kV 신고성-거제#2T/L 피뢰기 설치 안전확보차(2~3호)","2019-05-05 07:00","2019-05-05 18:00","2019-05-05 07:00","2019-05-05 18:00","당일"]
[485,"경남","통영","신고성통영 T/L","154kV 신고성-통영T/L 피뢰기 설치","154kV 신고성-통영T/L 피뢰기 설치","2019-05-11 07:00","2019-05-11 18:00","2019-05-11 07:00","2019-05-11 18:00","당일"]
[486,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제#1T/L 191호 지지애자 보강","154kV 신고성-거제#1T/L 191호 지지애자 보강","2019-05-11 08:00","2019-05-12 18:00","2019-05-11 08:00","2019-05-12 18:00","매일"]
[487,"경남","통영","신고성S/S 154kV #61 BUS","신고성S/S 154kV 신규수용공사","- 신고성-삼천포신재생T/L 증설 - 무부하가압(5.20~21)","2019-05-16 08:30","2019-05-21 18:00","2019-05-16 08:30","2019-05-21 18:00","연속"]
[488,"경남","통영","신고성삼천포#2 T/L","신고성S/S 154kV 신규수용공사","- 신고성-삼천포신재생T/L 증설 - 무부하가압(5.20~21)","2019-05-20 15:00","2019-05-21 15:00","2019-05-20 15:00","2019-05-21 15:00","연속"]
[489,"경남","통영","신고성S/S 154kV #66 BUS","신고성S/S 154kV 신규수용공사","- 신고성-삼천포신재생T/L 증설 - 무부하가압(5.27~28)","2019-05-22 08:30","2019-05-28 18:00","2019-05-22 08:30","2019-05-28 18:00","연속"]
[490,"경남","통영","신고성삼천포#2 T/L","신고성S/S 154kV 신규수용공사","- 신고성-삼천포신재생T/L 증설 - 무부하가압(5.27~28)","2019-05-27 15:00","2019-05-28 15:00","2019-05-27 15:00","2019-05-28 15:00","연속"]
[491,"경남","함안","가야사봉#2 T/L","가야S/S 가야-사봉#2T/L GIS 조작시험","가야S/S 가야-사봉#2T/L GIS 조작시험","2019-05-22 09:30","2019-05-22 17:30","2019-05-22 09:30","2019-05-22 17:30","당일"]
[492,"경남","함안","마산수출#2 T/L","마산S/S 마산-수출#2T/L GCB 조작시험","마산S/S 마산-수출#2T/L GCB 조작시험","2019-05-16 13:30","2019-05-16 17:30","2019-05-16 13:30","2019-05-16 17:30","당일"]
[493,"경남","함안","마산수출#1 T/L","마산S/S 마산-수출#1T/L GCB 조작시험","마산S/S 마산-수출#1T/L GCB 조작시험","2019-05-16 09:30","2019-05-16 13:30","2019-05-16 09:30","2019-05-16 13:30","당일"]
[494,"경남","함안","신마산차룡#2 T/L","신마산S/S 신마산-차룡#2T/L GCB 조작시험","신마산S/S 신마산-차룡#2T/L GCB 조작시험","2019-05-15 13:30","2019-05-15 17:30","2019-05-15 13:30","2019-05-15 17:30","당일"]
[495,"경남","함안","신마산차룡#1 T/L","신마산S/S 신마산-차룡#1T/L GCB 조작시험","신마산S/S 신마산-차룡#1T/L GCB 조작시험","2019-05-15 09:30","2019-05-15 13:30","2019-05-15 09:30","2019-05-15 13:30","당일"]
[496,"경남","함안","중리가야#2 T/L","2018~2019년 함안전력지사 송전정비 협력회사 총액공사","○ 154kV 중리-가야#1,2T/L SB댐퍼 설치공사 - 5/12(일) : #1T/L 10기(41,42,45,47~52호,가야S/T) - 5/12(일) : #2T/L 7기(41,42,47~50호,가야S/T)","2019-05-12 08:00","2019-05-12 18:00","2019-05-12 08:00","2019-05-12 18:00","당일"]
[497,"경남","함안","중리가야#1 T/L","2018~2019년 함안전력지사 송전정비 협력회사 총액공사","○ 154kV 중리-가야#1T/L SB댐퍼 설치공사 1. 5/12(일) : #1T/L 10기(41,42,45,47~52호,가야S/T) 2. 5/13(월) : #1T/L 14기(중리S/T 1~4,6~14호) 3. 5/14(화) : #1T/L 8기(16~18,28~31,36호)","2019-05-12 08:00","2019-05-14 18:00","2019-05-12 08:00","2019-05-14 18:00","매일"]
[498,"경남","함안","신마산중리#2 T/L","2018~2019년 함안전력지사 송전정비 협력회사 총액공사","○ 154kV 신마산-중리#1,2T/L SB댐퍼 설치공사 1. 5/18(토) : 154kV 신마산-중리 #1T/L 3기(신마산S/T,14, 15호) 2. 5/18(토) : 154kV 신마산-중리#2T/L 11기(신마산S/T,1~8,14,15호) 3. 5/18(토) : 154kV 신마산-진동T/L 안전이격 확보휴전","2019-05-18 08:00","2019-05-18 18:00","2019-05-18 08:00","2019-05-18 18:00","당일"]
[499,"경남","함안","중리가야#2 T/L","2018~2019년 함안전력지사 송전정비 협력회사 총액공사","○ 154kV 중리-가야#2T/L SB댐퍼 설치공사 1. 5/15(수) : #2T/L 8기(16~18,28~31,36호) 2. 5/16(목) : #2T/L 14기(중리S/T,1~4,6~14호)","2019-05-15 08:00","2019-05-16 18:00","2019-05-15 08:00","2019-05-16 18:00","당일"]
[500,"경남","함안","신마산중리#1 T/L","2018~2019년 함안전력지사 송전정비 협력회사 총액공사","○ 154kV 신마산-중리#1T/L SB댐퍼 설치공사 1. 5/16(목) : 신마산-중리#1T/L 8기(16~19, 22~25호) 2. 5/17(금) : 신마산-중리#1T/L 7기(26,28~32호, 중리S/T) 3. 5/18(토) : 신마산-중리 #1T/L 3기(신마산S/T,14, 15호)","2019-05-16 08:00","2019-05-18 18:00","2019-05-16 08:00","2019-05-18 18:00","매일"]
[501,"경남","함안","신마산중리#2 T/L","2018~2019년 함안전력지사 송전정비 협력회사 총액공사","○ 154kV 신마산-중리#2T/L SB댐퍼 설치공사 1. 5/14(화) : #2T/L 8기(25,26,28~32호,중리S/T)","2019-05-14 08:00","2019-05-14 18:00","2019-05-14 08:00","2019-05-14 18:00","당일"]
[502,"강원","강릉","동해강릉 T/L","2019년 가공송전선로 순시점검 위탁공사","○ 정밀점검 - 154kV 강릉T/L No.8-1~67호","2019-05-21 07:00","2019-05-24 18:00","2019-05-21 07:00","2019-05-24 18:00","매일"]
[503,"강원","강릉","신양양양양#1 T/L","2018~19년 송전정비 협력회사 총액공사(4회선구간병행휴전)","○ 점퍼선교체 - 154kV 주문진양양#2T/L No.60호 등 17개소(4회선구간병행휴전)","2019-05-15 07:00","2019-05-15 18:00","2019-05-15 07:00","2019-05-15 18:00","당일"]
[504,"강원","강릉","신양양양양#2 T/L","2018~19년 송전정비 협력회사 총액공사","○ 전선교체공사 및 4회선구간병행휴전 - 5/24 : 154kV 주문진양양#1T/L 점퍼선교체작업(4회선구간병행휴전) - 5/27~28 : 154kV 신양양-양양#2T/L No.49~52호 전선교체공사","2019-05-24 07:00","2019-05-28 18:00","2019-05-24 07:00","2019-05-28 18:00","매일"]
[505,"강원","강릉","북평영동TP#2 T/L","2018~19년 송전정비 협력회사 총액공사","○ 국산애자교체 - 154kV 북평-영동TP #1T/L No.55 등 5개소","2019-05-09 07:00","2019-05-10 18:00","2019-05-09 07:00","2019-05-10 18:00","당일"]
[506,"강원","강릉","북평영동TP#1 T/L","2018~19년 송전정비 협력회사 총액공사","○ 국산애자교체 - 154kV 북평-영동TP #1T/L No.55 등 6개소","2019-05-07 07:00","2019-05-08 18:00","2019-05-07 07:00","2019-05-08 18:00","당일"]
[507,"강원","강릉","북평영동TP#1 T/L","2019년 가공송전선로 순시점검 위탁공사(4회선구간병행휴전)","○ 정밀점검 - 154kV 강릉T/L No.1~67호 4회선구간병행휴전","2019-05-13 07:00","2019-05-13 18:00","2019-05-13 07:00","2019-05-13 18:00","당일"]
[508,"강원","강릉","동해영동TP T/L","2019년 가공송전선로 순시점검 위탁공사","○ 정밀점검 - 154kV 강릉T/L No.1~8호","2019-05-20 07:00","2019-05-20 18:00","2019-05-20 07:00","2019-05-20 18:00","당일"]
[509,"강원","강릉","북평영동TP#2 T/L","2019년 가공송전선로 순시점검 위탁공사(4회선구간병행휴전)","○ 정밀점검 - 154kV 강릉T/L No.1~8호(4회선구간병행휴전)","2019-05-20 07:00","2019-05-20 18:00","2019-05-20 07:00","2019-05-20 18:00","당일"]
[510,"강원","강릉","강릉영동TP T/L","2019년 가공송전선로 순시점검 위탁공사","○ 정밀점검 - 154kV 강릉T/L No.1~67호","2019-05-13 07:00","2019-05-17 18:00","2019-05-13 07:00","2019-05-17 18:00","매일"]
[511,"강원","강릉","횡계평창 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-05-27 10:00","2019-05-29 18:00","2019-05-29 10:00","2019-05-31 18:00","연속"]
[512,"강원","강릉","강릉횡계#1 T/L","2018~19년 송전정비 협력회사 총액공사","○ 국산애자교체 - 154kV 강릉수력T/L No.10, 33호","2019-05-21 07:00","2019-05-21 18:00","2019-05-21 07:00","2019-05-21 18:00","매일"]
[513,"강원","강릉","강릉횡계#2 T/L","2019년 가공송전선로 순시점검 위탁공사(4회선구간병행휴전)","○ 정밀점검 - 154kV 강릉T/L No.1~67호(4회선구간병행휴전)","2019-05-14 07:00","2019-05-14 18:00","2019-05-14 07:00","2019-05-14 18:00","당일"]
[514,"강원","동해","이원동해TP T/L","2019년 동해전력지사 170kV GIS 정밀점검","1. 이원S/S 이원-동해TPT/L GIS 정밀점검","2019-05-16 09:30","2019-05-18 18:00","2019-05-16 09:30","2019-05-18 18:00","연속"]