{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["종합","765송부","345송부","154송부","시송전설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":14,"comments":2,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"종합","index":0,"n_rows":37,"n_cols":33,"rows_kept":37,"cut":false,"hidden":true,"merged":[[14,14,14,15],[10,1,10,2],[11,1,11,2],[14,9,14,13],[9,1,9,2],[14,2,14,6],[11,3,11,6],[10,3,10,6],[9,3,9,6],[0,0,0,15],[7,14,7,15],[7,1,7,2],[8,1,8,2],[7,9,7,13],[7,3,7,6],[8,3,8,6]]}
[{"$f":"\"'19년 \"&R15&\"월 휴전심의 결과\"","v":"'19년 6월 휴전심의 결과"}]
[]
[]
[]
[]
[]
["◎ 전체 심의결과"]
["전   압","신 청",null,"채 택",null,null,null,"일정\n조정","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)"]
["765kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B9-I9","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J9,L9,N9)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O9/B9)","v":{"$error":"#REF!"}}]
["345kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B10-I10","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J10,L10,N10)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O10/B10)","v":{"$error":"#REF!"}}]
["154kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B11-I11","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J11,L11,N11)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O11/B11)","v":{"$error":"#REF!"}}]
["계",{"$f":"SUM(B9:B11)","v":{"$error":"#REF!"}},null,{"$f":"SUM(D9:D11)","v":{"$error":"#REF!"}},null,null,null,{"$f":"SUM(H9:H11)","v":{"$error":"#REF!"}},{"$f":"SUM(J12,L12,N12)","v":{"$error":"#REF!"}},{"$f":"SUM(J9:J11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(L9:L11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(N9:N11)","v":{"$error":"#REF!"}},{"$f":"SUM(O9:O11)","v":{"$error":"#REF!"}},{"$f":"(O12/B12)","v":{"$error":"#REF!"}}]
[]
["◎ 본부별 심의결과",{"$nulls":16},"월"]
["사업소","신 청","(765/345/154)",{"$nulls":4},"채 택","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)",null,null,6]
["서   울",{"$f":"SUM(C16:G16)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},{"$f":"B16-I16","v":{"$error":"#REF!"}},{"$f":"SUM(J16,L16,N16)","v":{"$error":"#REF!"}},{"$f":"SUM(S16:U16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W16:Y16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA16:AC16)","v":{"$error":"#REF!"}},{"$f":"SUM(AE16:AG16)","v":{"$error":"#REF!"}},{"$f":"(O16/B16)","v":{"$error":"#REF!"}},null,"서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}}]
["남서울",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$f":"SUM(J17,L17,N17)","v":{"$error":"#REF!"}},{"$f":"SUM(S17:U17)","v":{"$error":"#REF!"}},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"남서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}}]
["인   천",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"인천",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}}]
["경기북부",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기북부",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}}]
["경   기",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}}]
["강   원",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"강원",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}}]
["충   북",{"$f":"SUM(C22:G22)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"충북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}}]
["대전충남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"대전충남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}}]
["전   북",{"$f":"SUM(C24:G24)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"전북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}}]
["광주전남",{"$f":"SUM(C25:G25)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"광주전남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}}]
["대구",{"$f":"SUM(C26:G26)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},{"$f":"B26-I26","v":{"$error":"#REF!"}},{"$f":"SUM(J26,L26,N26)","v":{"$error":"#REF!"}},{"$f":"SUM(S26:U26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W26:Y26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA26:AC26)","v":{"$error":"#REF!"}},{"$f":"SUM(AE26:AG26)","v":{"$error":"#REF!"}},{"$f":"(O26/B26)","v":{"$error":"#REF!"}},null,"대구",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}}]
["경북",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}}]
["부산울산",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"부산울산",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}}]
["경   남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$f":"SUM(W29:Y29)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA29:AC29)","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},null,"경남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}}]
["제   주",{"$f":"SUM(C30:G30)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$f":"(O30/B30)","v":{"$error":"#REF!"}},null,"제주",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}}]
[]
[" 붙임 :  1. 집중심의내역 1부"]
[" 붙임 :  전압별 검토서 1부. 끝."]
[]
[null,{"$f":"SUM(B16:B30)","v":{"$error":"#REF!"}},{"$f":"SUM(C16:C30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(E16:E30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(G16:G30)","v":{"$error":"#REF!"}},{"$f":"SUM(H16:H30)","v":{"$error":"#REF!"}},{"$f":"SUM(I16:I30)","v":{"$error":"#REF!"}},{"$f":"SUM(J16:J30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(L16:L30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(N16:N30)","v":{"$error":"#REF!"}},{"$f":"SUM(O16:O30)","v":{"$error":"#REF!"}}]
[{"$f":"COUNTIF(B36:N36,\"NO\")","v":0},{"$f":"IF(B35=B12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(C35=B9,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(E35=B10,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(G35=B11,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(H35=D12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(I35=I12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(J35=J12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(L35=L12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(N35=N12,\"\",\"NO\")","v":{"$error":"#REF!"}}]
[{"$f":"IF(A36>=1,\"틀린곳\",\"\")","v":""},{"$f":"IF(B36=\"NO\",\"총계\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C36=\"NO\",\"765\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(D36=\"NO\",\"총계\",\"\")","v":""},{"$f":"IF(E36=\"NO\",\"345\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(G36=\"NO\",\"154\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(H36=\"NO\",\"채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(I36=\"NO\",\"불채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(J36=\"NO\",\"병행\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(L36=\"NO\",\"취소\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(N36=\"NO\",\"연기\",\"\")","v":{"$error":"#REF!"}}]

{"sheet":"765송부","index":1,"n_rows":20,"n_cols":16,"rows_kept":20,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 6월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S 765kV #2 BUS","765kV #85BUS 보호반 교체공사","765kV #85BUS 보호반 교체","2019-06-17 08:00","2019-06-28 18:00","2019-06-17 08:00","2019-06-28 18:00","연속",null,null,null,201902280289]
[2,"경기북부","구리","신가평S/S #1 M.Tr A-1","19년도 신가평변전소 765kV GIS 점검공사","82Bay(8200CB,8272CB) GIS 하자점검/#1MTr 하자점검(모장순)","2019-06-17 09:00","2019-06-19 18:00","2019-06-10 09:00","2019-06-12 18:00","연속",null,null,null,201901150058]
[3,"경기북부","구리","신태백신가평#1 T/L","19년도 신가평변전소 765kV GIS 점검공사","#2BUS 시험가압선로","2019-06-28 09:00","2019-06-28 18:00","취소","취소","당일",null,null,null,201903060500]
[4,"경기북부","구리","신태백신가평#1 T/L","19년도 신가평변전소 765kV GIS 점검공사","Trench제 부싱단자교체(유사고장), #3M.Tr 시험가압선로","2019-06-13 09:00","2019-06-14 18:00","취소","취소","연속",null,null,null,201903060494]
[5,"경기","성남","신안성신가평 T/L","2018-2019년 성남전력지사 송전정비회사 총액공사","- 765kV 신안성-신가평T/L 항공장애표시도장(10기)","2019-06-01 07:00","2019-06-20 18:00","취소","취소","연속",null,null,null,201904050367]
[6,"강원","태백","신태백신가평#2 T/L","345kV 신영주, 신제천 TCSC 설치사업","신영주, 신제천S/S TCSC 설치공사 - TCSC 제어용 신호 구성을 위한 SPS 설치(신태백, 신제천, 신영주S/S) - 접점 및 보호계전기 동작 관련 연동시험","2019-06-14 09:00","2019-06-14 18:00","취소","취소","당일",null,null,null,201904150171]
[7,"강원","태백","신태백신가평#1 T/L","345kV 신영주, 신제천TCSC 설치사업","신영주, 신제천S/S TCSC 설치공사 - TCSC 제어용 신호 구성을 위한 SPS 설치(신태백, 신제천, 신영주S/S) - 접점 및 보호계전기 동작 관련 연동시험","2019-06-13 09:00","2019-06-13 18:00","취소","취소","당일",null,null,null,201904150168]
[8,"대전충남","서산","당진화력S/Y 765KV 8호기 1차 CB B","19년 서산PO 765/345kV GIS 점검공사","당진화력 765KV 765KV 8호기 1차 CB (8771) 보통점검","2019-06-17 09:00","2019-06-21 18:00","2019-06-17 09:00","2019-06-21 18:00","연속",null,null,null,201904120063]
[9,"대전충남","서산","765KV 7호기 1차-8호기 1차 CB B","19년 서산PO 765/345kV GIS 점검공사","당진화력 765KV 7호기 1차-8호기 1차 CB(8700) 보통점검","2019-06-10 09:00","2019-06-14 18:00","2019-06-10 09:00","2019-06-14 18:00","연속",null,null,null,201904120061]
[10,"부산울산","동부산","신고리S/S 765kV 신고리G5T/L CB(8572)","2019년 신고리E/C 765kV GIS 보통점검","신고리E/C 8500 GIS 보통점검 안전확보","2019-06-12 09:30","2019-06-14 18:00","2019-06-12 09:30","2019-06-14 18:00","연속",null,null,null,201904030183]
[11,"부산울산","동부산","신고리S/S 765kV #3 M.Tr 1차-신고리G5T/L CB(8500)","2019년 신고리E/C 765kV GIS 보통점검","신고리E/C 8500 GIS 보통점검","2019-06-12 09:30","2019-06-14 18:00","2019-06-12 09:30","2019-06-14 18:00","연속",null,null,null,201904030182]
[12,"부산울산","동부산","신고리S/S #2 M.Tr A-1","2019년 신고리E/C 765kV GIS 보통점검","신고리E/C 8671,8600 GIS 보통점검","2019-06-17 09:30","2019-06-20 18:00","2019-06-17 09:30","2019-06-20 18:00","연속",null,null,null,201904030194]
[13,"부산울산",null,"신고리NP4호기 주변압기 CB(8300,8372)","주발전기 100% 운전중 SWYD PCB 개방 후 주변압기 점검","주발전기 100% 운전중 SWYD PCB 개방 후 주변압기 점검","2019-06-24 16:00","2019-07-15 09:00","2019-06-24 16:00","2019-07-15 09:00","연속"]
[14,"부산울산","새울본부","신고리#4 주변압기 CB(8300,8372)","신고리4호기 부하탈락시험(100%)\n* 조작차단기 : 8300, 8372","○ 주발전기 100% 운전중 SWYD PCB 개방\n  후 주변압기 점검","2019-06-07 14:00","2019-06-07 23:00","2019-06-07 14:00","2019-06-07 23:00","연속"]
[15,"부산울산","새울본부","신고리#4 주변압기 CB(8300,8372)","신고리4호기 간이정비\n* 조작차단기 : 8300, 8372","○ 주변압기 점검","2019-06-11 11:00","2019-06-26 16:00","2019-06-11 11:00","2019-06-26 16:00","연속"]
[16,"부산울산","새울본부","신고리#4 주변압기 CB(8300,8372)","신고리4호기 소내전원절체 시험\n* 조작차단기 : 8300, 8372","○ 고압차단기반 소내전원 절체 시험","2019-06-30 11:00","2019-06-30 15:00","2019-06-30 11:00","2019-06-30 15:00","연속"]

{"sheet":"345송부","index":2,"n_rows":230,"n_cols":16,"rows_kept":230,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,14,3,14],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 6월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S 345kV 양주-중부#2T/L GIS","19년 중부전력지사 변전협력회사 총액공사","ㅇ345kV 양주중부#2T/L GIS 차단기 동작시험","2019-06-04 14:00","2019-06-04 18:00","2019-06-04 14:00","2019-06-04 18:00","당일"]
[2,"서울","중부","양주중부#1 T/L","19년 중부전력지사 변전협력회사 총액공사","ㅇ345kV 7100 BUS TIE GIS 보통점검 ㅇ345kV 양주중부#1T/L GIS 차단기 동작시험","2019-06-05 09:00","2019-06-05 18:00","2019-06-05 09:00","2019-06-05 18:00","당일"]
[3,"남서울","강남","신양재S/S 345kV #75 PT GIS","신양재S/S 345kV #2BUS PT GIS 보통점검","신양재S/S 345kV #2BUS PT GIS 보통점검","2019-06-12 14:00","2019-06-12 18:00","2019-06-12 14:00","2019-06-12 18:00","당일"]
[4,"남서울","강남","신양재S/S 345kV #2 Sh.R","신양재S/S 345kV #2Sh.R GIS 개폐타임측정","신양재S/S 345kV #2Sh.R GIS 개폐타임측정","2019-06-10 14:00","2019-06-10 18:00","2019-06-10 14:00","2019-06-10 18:00","당일"]
[5,"남서울","강남","신양재S/S 345kV #1 Sh.R","신양재S/S 345kV #1Sh.R GIS 개폐타임측정","신양재S/S 345kV #1Sh.R GIS 개폐타임측정","2019-06-10 10:00","2019-06-10 14:00","취소","취소","당일"]
[6,"남서울","강남","신양재S/S 345kV #3 Sh.R","신양재S/S #3Sh.R GIS 개폐타임측정","신양재S/S #3Sh.R GIS 개폐타임측정","2019-06-11 10:00","2019-06-11 14:00","2019-06-11 10:00","2019-06-11 14:00","당일"]
[7,"남서울","강남","신양재S/S 345kV #70 PT GIS","신양재S/S 345kV #1BUS PT GIS 보통점검","신양재S/S 345kV #1BUS PT GIS 보통점검","2019-06-12 10:00","2019-06-12 14:00","2019-06-12 10:00","2019-06-12 14:00","당일"]
[8,"남서울","강남","신양재S/S 345kV #4 Sh.R","신양재S/S #4Sh.R GIS 개폐타임측정","신양재S/S #4Sh.R GIS 개폐타임측정","2019-06-11 14:00","2019-06-11 18:00","2019-06-11 14:00","2019-06-11 18:00","당일"]
[9,"남서울","직할","영등포S/S 345kV #3 Sh.R ","영등포S/S 345kV #3Sh.R GIS 다빈도 개폐장치 정밀점검공사","영등포S/S 345kV #3Sh.R GIS 다빈도 개폐장치 정밀점검공사","2019-06-10 09:00","2019-06-14 18:00","2019-06-10 09:00","2019-06-14 18:00","연속"]
[10,"인천","시흥","신시흥#1S/S 345kV 신시흥-영흥TP#3T/L CB (7771)","신시흥#1S/S 345kV 7771 정밀점검 및 7761DS 누기보수","신시흥#1S/S 345kV 7771 정밀점검 및 7761DS C상 누기보수","2019-06-24 09:00","2019-06-27 18:00","2019-06-24 09:00","2019-06-27 18:00","연속"]
[11,"인천","시흥","신시흥영흥TP#3 T/L","신시흥#1S/S 345kV 7771 정밀점검 및 7761DS 누기보수","신시흥#1S/S 345kV 7771CB 정밀점검 및 7761DS C상 누기보수","2019-06-10 08:00","2019-06-14 18:00","2019-06-10 08:00","2019-06-14 18:00","연속"]
[12,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥#1S/S 345kV #2M.Tr 피뢰기 대체","신시흥#1S/S 345kV #2M.Tr 피뢰기 대체 및 2차 GIS 동작, #2S.Tr 보통점검 및 #2S.Tr CB 동작점검","2019-06-06 09:00","2019-06-07 18:00","2019-06-06 09:00","2019-06-07 18:00","연속"]
[13,"인천","시흥","영흥T/P 345kV 영흥TP연락#2T/L-#2G.Tr 1차 CB(7200)","영흥T/P 345kV 7200 CB 동작점검","영흥T/P 345kV 7200 CB 동작점검","2019-06-03 09:00","2019-06-03 14:00","2019-06-03 09:00","2019-06-03 14:00","당일"]
[14,"인천","시흥","영흥T/P 345kV #1T.Tr 1차-#2T.Tr 1차 CB A (7300)","영흥T/P 345kV 7300CB 동작점검","영흥T/P 345kV 7300CB 동작점검","2019-06-03 14:00","2019-06-03 18:00","2019-06-03 14:00","2019-06-03 18:00","당일"]
[15,"인천","시흥","영흥T/P 345kV #2G.Tr 1차 CB(7272)","영흥T/P 345kV #2G.Tr 1차 CB (7272) 동작점검","영흥T/P 345kV #2G.Tr 1차 CB (7272) 동작점검","2019-06-24 14:00","2019-06-24 18:00","2019-06-24 14:00","2019-06-24 18:00","당일"]
[16,"인천","시흥","영흥T/P 345kV 신시흥-영흥TP#2T/L-#3G.Tr CB(7400)","영흥T/P 345kV 7400 CB 동작점검","영흥T/P 345kV 신시흥-영흥TP#2T/L-#3G.Tr (7400) 동작점검","2019-06-24 09:00","2019-06-24 14:00","2019-06-24 09:00","2019-06-24 14:00","당일"]
[17,"인천","인천","서인천C/C 345kV #4 Sh.R","서인천복합S/Y #4Sh.R 보통점검 및 7A79 GIS 하자점검","서인천복합S/Y #4Sh.R 보통점검 서인천복합S/Y 7A79 GIS 하자점검","2019-06-10 09:00","2019-06-11 18:00","2019-06-24 09:00","2019-06-25 18:00","연속"]
[18,"인천","인천","서인천CC신부평#3 T/L","서인천복합S/Y #2Sh.R 대체공사","서인천복합S/Y #2Sh.R 대체공사 - 기존 #2Sh.R 철거 - 신규 #2Sh.R 설치 및 GIB 개조","2019-06-05 09:00","2019-06-07 18:00","2019-06-19 09:00","2019-06-21 18:00","연속"]
[19,"인천","인천","서인천C/C 345kV #75-77 CLR #7777 CB A (7777_A)","서인천C/C 7777 GIS 초기점검","서인천C/C 7777 GIS 초기점검","2019-06-17 09:00","2019-06-17 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[20,"인천","인천","서인천C/C 345kV #75-77 CLR #7577 CB A (7577_A)","서인천C/C 7577 GIS 초기점검","서인천C/C 7577 GIS 초기점검","2019-06-14 09:00","2019-06-14 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[21,"인천","인천","서인천C/C 345kV #70-72 CLR #7277 CB A (7277_A)","서인천C/C 7277 GIS 초기점검","서인천C/C 7277 GIS 초기점검","2019-06-13 09:00","2019-06-13 18:00","2019-06-12 09:00","2019-06-12 18:00","당일"]
[22,"인천","인천","서인천C/C 345kV #70-72 CLR #7077 CB A (7077_A)","서인천C/C 7077 GIS 초기점검","서인천C/C 7077 GIS 초기점검","2019-06-12 09:00","2019-06-12 18:00","2019-06-12 09:00","2019-06-12 18:00","당일"]
[23,"인천","인천","신가좌S/S 345kV 신가좌-가정#1T/L CB(7271)","신가좌S/S 7271GIS 조작시험","신가좌S/S 7271GIS 조작시험","2019-06-18 09:00","2019-06-18 13:00","2019-06-18 09:00","2019-06-18 13:00","당일"]
[24,"인천","인천","신가좌S/S 345kV 신가좌가정#1-신가좌신시흥 CB(7200)","신가좌S/S 7200GIS 조작시험","신가좌S/S 7200GIS 조작시험","2019-06-18 13:00","2019-06-18 18:00","2019-06-18 13:00","2019-06-18 18:00","당일"]
[25,"인천","인천","신가좌신시흥#2 T/L","345kV신가좌신시흥#2T/L 애자련보강","345kV신가좌신시흥#2T/L 가공송전선로 애자련보강","2019-06-28 08:00","2019-06-28 18:00","2019-06-28 08:00","2019-06-28 18:00","연속"]
[26,"인천","인천","신가좌신시흥#1 T/L","345kV신가좌신시흥#1T/L 애자련보강","345kV신가좌신시흥#1T/L 가공송전선로 애자련보강","2019-06-29 08:00","2019-06-29 18:00","2019-06-29 08:00","2019-06-29 18:00","연속"]
[27,"인천","인천","신가좌S/S 345kV #1 M.Tr 1차 CB(7172)","신가좌S/S 7172GIS 초기점검","신가좌S/S 7172GIS 초기점검","2019-06-07 09:00","2019-06-07 18:00","2019-06-07 09:00","2019-06-07 18:00","당일"]
[28,"인천","인천","신가좌S/S 345kV 신가좌가정#2T/L-#1 M.Tr CB(7100)","신가좌S/S 7100GIS 초기점검","신가좌S/S 7100GIS 초기점검","2019-06-05 09:00","2019-06-05 18:00","2019-06-05 09:00","2019-06-05 18:00","당일"]
[29,"인천","인천","신가좌S/S 345kV 신가좌-가정#2T/L CB(7171)","신가좌S/S 7171GIS 초기점검","신가좌S/S 7171GIS 초기점검","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[30,"인천","인천","인천CC S/Y #2 Tie-Tr","인천복합S/Y #2Tie-Tr 휴전작업","- #2Tie-Tr 보통점검 -6244, 4289 GIS 조작시험 - 부싱절연유 채유","2019-06-03 09:00","2019-06-04 18:00","2019-06-03 09:00","2019-06-04 18:00","연속"]
[31,"인천","인천","인천CC S/Y 345kV 신경서인천CC#2-가정인천 CB(7400)","인천CC S/Y 7400 GIS 조작시험","인천CC S/Y 7400 GIS 조작시험","2019-06-07 09:00","2019-06-07 18:00","2019-06-07 09:00","2019-06-07 18:00","당일"]
[32,"인천","인천","인천CC S/Y 345kV #1Sh.R 1차 CB (7202_A)","인천CC 345kV Sh.R 증설공사(7272CB)","- 72BAY 불량 B/F PNL 대체 - 345kV #1Sh.R 가압 및 사용전검사(7272CB)","2019-06-18 10:00","2019-06-26 17:00","2019-06-18 10:00","2019-06-26 17:00","연속"]
[33,"인천","인천","인천CC S/Y 345kV #1 Sh.R CB","인천CC 345kV Sh.R 증설공사","- 345kV #1 Sh.R 시험가압 및 사용전검사","2019-06-24 12:00","2019-06-25 12:00","2019-06-24 12:00","2019-06-25 12:00","연속"]
[34,"인천","인천","인천CC S/Y 345kV #2 Sh.R CB","인천CC 345kV Sh.R 증설공사","- 345kV #2 Sh.R 시험가압 및 사용전검사","2019-06-25 12:00","2019-06-26 17:00","2019-06-25 12:00","2019-06-26 17:00","연속"]
[35,"인천","인천","신경서인천CC#1 T/L","인천CC 345kV Sh.R 증설공사","- 72BAY 불량 B/F PNL 대체","2019-06-18 10:00","2019-06-21 17:00","2019-06-18 10:00","2019-06-21 17:00","연속"]
[36,"인천","인천","포스코S/Y 345kV #4 STEP-UP-TR T/L CB A (7472)","포스코S/Y 7472GIS 조작시험","포스코S/Y 7472GIS 조작시험","2019-06-19 13:00","2019-06-19 18:00","2019-06-19 13:00","2019-06-19 18:00","당일"]
[37,"경기북부","고양","신덕은S/S 신덕은-LG디스플레이 #1T/L GIS","345kV 신덕은-LG 디스플레이#1T/L GIS 초기점검(총액공사)","345kV 신덕은-LG 디스플레이#1T/L GIS 초기점검(7071,7000)","2019-06-10 09:00","2019-06-12 18:00","2019-06-10 09:00","2019-06-12 18:00","연속"]
[38,"경기북부","고양","신덕은파주문산CC#1 T/L","345kV 신덕은-파주문산CC#1T/L GIS 하자점검(총액공사)","345kV 신덕은-파주문산#1T/L GIS 하자점검 (신덕은 7572, 파주문산CC 7471,7400)","2019-06-10 09:00","2019-06-12 18:00","2019-06-10 09:00","2019-06-12 18:00","연속"]
[39,"경기북부","구리","미금S/S #3 M.Tr A","미금S/S 감시제어설비 교체공사","미금S/S 노후 모자익반 교체","2019-06-10 09:00","2019-06-14 18:00","2019-06-10 09:00","2019-06-14 18:00","연속"]
[40,"경기북부","구리","신의정부미금#1 T/L","미금S/S 감시제어설비 교체공사","미금S/S 노후 모자익반 교체","2019-06-10 09:00","2019-06-14 18:00","2019-06-10 09:00","2019-06-14 18:00","연속"]
[41,"경기북부","직할","신의정부S/S #1 M.Tr","'18-19년 변전협력회사 총액공사(차단기 개폐타임)","개폐타임측정(7200,7272)","2019-06-11 09:00","2019-06-11 18:00","2019-06-11 09:00","2019-06-11 18:00","당일"]
[42,"경기북부","구리","신가평S/S 345kV 신가평-미금#1T/L GIS","19년 구리전력 345kV GIS 보통점검","19년 구리전력 345kV GIS 보통점검(7772) - 신가평S/S 7772GIS 보통점검","2019-06-12 09:00","2019-06-12 18:00","2019-06-07 09:00","2019-06-07 18:00","당일"]
[43,"경기북부","직할","신의정부S/S #2 M.Tr","'18-19년 변전협력회사 총액공사(차단기 개폐타임)","개폐타임측정(7300,7372)","2019-06-12 09:00","2019-06-12 18:00","2019-06-12 09:00","2019-06-12 18:00","당일"]
[44,"경기북부","고양","신덕은S/S 신덕은-LG디스플레이#2T/L GIS","345kV 신덕은-LG 디스플레이#2T/L GIS 초기점검(총액공사)","345kV 신덕은-LG 디스플레이#1T/L GIS 초기점검(7071,7000)","2019-06-13 09:00","2019-06-14 18:00","2019-06-13 09:00","2019-06-14 18:00","연속"]
[45,"경기북부","고양","신덕은파주문산CC#2 T/L","345kV 신덕은-파주문산CC#2T/L GIS 하자점검(총액공사)","345kV 신덕은-파주문산#2T/L GIS 하자점검 (신덕은 7372, 파주문산CC 7371,7300)","2019-06-13 09:00","2019-06-14 18:00","2019-06-13 09:00","2019-06-14 18:00","연속"]
[46,"경기북부","구리","신가평S/S 345kV 신가평-신의정부#1T/L GIS","19년 구리전력 345kV GIS 보통점검","19년 구리전력 345kV GIS 보통점검(7672) - 신가평S/S 7672GIS 보통점검","2019-06-13 09:00","2019-06-13 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[47,"경기북부","직할","신의정부S/S #4 M.Tr A","'18-19년 변전협력회사 총액공사(차단기 개폐타임)","개폐타임측정(7872)","2019-06-13 09:00","2019-06-13 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[48,"경기북부","구리","신가평S/S 345kV #4Sh.R 1차-신가평신의정부 CB(7600)","19년 구리전력 345kV GIS 보통점검","19년 구리전력 345kV GIS 보통점검(7600) - 신가평S/S 7600GIS 보통점검","2019-06-14 09:00","2019-06-14 18:00","2019-06-14 09:00","2019-06-14 18:00","당일"]
[49,"경기북부","직할","신파주양주#1 T/L","'18-19년 변전협력회사 총액공사(차단기 개폐타임)","개폐타임측정(7300,7371)","2019-06-19 09:00","2019-06-19 18:00","2019-06-19 09:00","2019-06-19 18:00","당일"]
[50,"경기북부","직할","양주S/S #2 M.Tr","154kV 지축E/C 옥내화 사업","154kV 지축E/C 건설-무부하가압","2019-06-17 09:00","2019-06-18 18:00","2019-06-17 09:00","2019-06-18 18:00","연속"]
[51,"경기북부","고양","신파주신덕은#2 T/L","2019년 가공송전 순시점검 위탁공사","ㅇ 345kV 신파주-신덕은#2T/L No.61-66 정밀점검","2019-06-19 07:00","2019-06-21 18:00","2019-06-19 07:00","2019-06-21 18:00","연속"]
[52,"경기","동부","곤지암S/S #3 M.Tr A","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 #66BUS 무부하가압용 주변압기","2019-06-08 16:00","2019-06-09 16:00","2019-06-15 16:00","2019-06-16 16:00","연속"]
[53,"경기","동부","곤지암신충주#1 T/L","345kV 곤지암-신충주T/L 접속개소 전선교체공사","345kV 곤지암-신충주T/L 접속개소 전선교체공사","2019-06-21 07:30","2019-06-28 18:00","취소","취소","연속"]
[54,"경기","동부","곤지암신충주#2 T/L","345kV 곤지암-신충주T/L 접속개소 전선교체공사","345kV 곤지암-신충주T/L 접속개소 전선교체공사","2019-06-29 07:30","2019-07-06 18:00","취소","취소","연속"]
[55,"경기","성남","서안성S/S #1 M.Tr A","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ 71Bay 용량대체 ㅇ 기타 부대공사 x 1식","2019-06-11 09:00","2019-08-13 09:00","2019-06-01 09:00","2019-07-10 09:00","연속"]
[56,"경기","성남","서안성S/S 345kV #1 BUS","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ71Bay GIS(7171, 7100) 용량대체 ㅇ 기타 부대공사 x 1식","2019-06-11 09:00","2019-07-05 09:00","2019-06-01 09:00","2019-06-04 18:00","연속"]
[57,"경기","성남","서안성신진천#2 T/L","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ71Bay 용량대체 ㅇ 기타 부대공사 x 1식 ㅇ 무부하 및 실부하 가압","2019-06-11 09:00","2019-08-13 09:00","2019-06-01 09:00","2019-07-10 09:00","연속"]
[58,"경기","성남","신성남S/S 345kV 서서울2-신성남#2T/L GIS","7171 조작시험","7171 조작시험","2019-06-25 09:00","2019-06-25 18:00","2019-06-25 09:00","2019-06-25 18:00","당일"]
[59,"경기","성남","신성남S/S #6 M.Tr","7872, 2차 조작,3차보통","7872, 2차 조작,3차보통 #6-1,2Sh.R CB 보통","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[60,"경기","성남","신성남S/S 345kV 신안성-신성남#2T/L GIS","7571 조작시험","7571 조작시험","2019-06-14 09:00","2019-06-14 18:00","2019-06-14 09:00","2019-06-14 18:00","당일"]
[61,"경기","성남","신성남S/S 345kV 서서울2-신성남#1T/L CB A (7271)","7271 조작시험","7271 조작시험","2019-06-14 09:00","2019-06-14 18:00","2019-06-14 09:00","2019-06-14 18:00","당일"]
[62,"경기","성남","신성남S/S 345kV 345KV STATCOM TIE GIS","7000 조작시험","7000 조작시험","2019-06-21 09:00","2019-06-21 14:00","2019-06-21 09:00","2019-06-21 14:00","당일"]
[63,"경기","성남","신성남S/S 345kV 신성남-동서울#1T/L GIS","7371 조작시험","7371 조작시험","2019-06-21 14:00","2019-06-21 18:00","2019-06-21 14:00","2019-06-21 18:00","당일"]
[64,"경기","성남","신성남S/S 345kV #STATCOM M.Tr 1차 GIS","7072 조작시험","7072 조작시험","2019-06-25 09:00","2019-06-25 18:00","2019-06-25 09:00","2019-06-25 18:00","당일"]
[65,"경기","성남","신성남S/S 345kV 신안성-신성남#1T/L GIS","7671조작,LA초기,CVT 보통","-7671조작,LA초기,CVT 보통 -가보제 345T/L 로직개선(계통)","2019-06-26 09:00","2019-06-26 18:00","2019-06-26 09:00","2019-06-26 18:00","당일"]
[66,"경기","성남","신수원S/S #4 M.Tr","신수원S/S 345kV 용량부족 GIS 대체공사","- 345kV GIS(40kA, 4000A) × 14CB 철거 - 345kV GIS(63kA, 6300A) × 14CB 신설","2019-06-24 09:00","2019-07-04 18:00","2019-06-24 09:00","2019-07-04 18:00","연속"]
[67,"경기","성남","신안성S/S 345kV #5 Sh.R","345kV GIS 정밀점검-#5Sh.R FEEDER 7779","345kV GIS 정밀점검-#5Sh.R FEEDER 7779","2019-06-17 09:00","2019-06-21 18:00","2019-06-17 09:00","2019-06-21 18:00","연속"]
[68,"경기","성남","신안성S/S 345kV #7 Sh.R 1차 GIS","7B71 보통","7B71 보통","2019-06-05 09:00","2019-06-05 18:00","2019-06-05 09:00","2019-06-05 18:00","당일"]
[69,"경기","성남","신안성S/S 345kV #6 Sh.R","345kV GIS 정밀점검-#6Sh.R FEEDER 7979","345kV GIS 정밀점검-#7Sh.R FEEDER 7979 7971,7900 GIS 보통점검","2019-06-24 09:00","2019-06-28 18:00","2019-06-24 09:00","2019-06-28 18:00","연속"]
[70,"경기","성남","신안성S/S 345kV 신안성-신용인#1T/L GIS","345kV GIS 정밀점검-7772","345kV GIS 정밀점검-7772","2019-06-10 09:00","2019-06-14 18:00","2019-06-10 09:00","2019-06-14 18:00","연속"]
[71,"경기","성남","신안성S/S 345kV 신안성-신용인#2T/L GIS","345kV GIS 정밀점검-7872","345kV GIS 정밀점검-7872","2019-06-24 09:00","2019-06-28 18:00","2019-06-24 09:00","2019-06-28 18:00","연속"]
[72,"경기","성남","신안성S/S 765kV #5 M.Tr 2차 GIS","#5M.Tr 2차 7C71 보통","- #5M.Tr 2차 7C71 보통 -DS 보조계전기교체","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[73,"경기","직할","화성평택T/P#1 T/L","화성S/S 362kV GIS 용량대체공사","O. 7B BAY 모선자재 반입을 위한 안전이격거리 확보","2019-06-13 09:00","2019-06-13 14:00","2019-06-13 09:00","2019-06-13 14:00","당일"]
[74,"경기","직할","화성평택T/P#2 T/L","화성S/S 362kV GIS 용량대체공사","O. 7B BAY 모선자재 반입을 위한 안전이격거리 확보","2019-06-13 14:00","2019-06-13 18:00","2019-06-13 14:00","2019-06-13 18:00","당일"]
[75,"경기","직할","화성신시흥 T/L","화성S/S 362kV GIS 용량대체공사","O. 7B BAY 모선자재 반입을 위한 안전이격거리 확보","2019-06-14 14:00","2019-06-14 18:00","2019-06-14 14:00","2019-06-14 18:00","당일"]
[76,"경기","직할","화성신안산 T/L","화성S/S 362kV GIS 용량대체공사","O. 7B BAY 모선자재 반입을 위한 안전이격거리 확보","2019-06-14 09:00","2019-06-14 14:00","2019-06-14 09:00","2019-06-14 14:00","당일"]
[77,"경기","직할","화성S/S 345kV #76 BUS","345kV 화성S/S 362kV GIS 용량대체 및 SW 증설공사","O. 345kV 화성-신평택CC #1,2T/L 증설관련 무부하 가압","2019-06-18 10:00","2019-06-19 18:00","2019-06-18 10:00","2019-06-19 18:00","연속"]
[78,"경기","직할","화성S/S 345kV #70 BUS","345kV 화성-신평택CCT/L 건설공사 #1, #2T/L 무부하가압","345kV 화성-신평택CCT/L 건설공사 #1, #2T/L 무부하가압","2019-06-25 14:00","2019-06-27 14:00","취소","취소","연속"]
[79,"경기","직할","화성S/S #4 M.Tr","19년 직할 변전협력회사 총액공사","화성S/S #4M.Tr 1차 조작, 2차 보통, 1,2차 LA 보통, 3차 PT 보통점검","2019-06-25 09:00","2019-06-25 18:00","2019-06-25 09:00","2019-06-25 18:00","당일"]
[80,"경기","직할","화성S/S 345kV #75 BUS","345kV 화성S/S 362kV GIS 용량대체 및 SW 증설공사","O. 345kV 화성-신평택CC #1,2T/L 증설관련 무부하 가압","2019-06-18 10:00","2019-06-19 18:00","취소","취소","연속"]
[81,"경기","직할","서서울#2화성#1 T/L CB","345kV 화성-신평택CCT/L 건설공사 #1, #2T/L 무부하가압","345kV 화성-신평택CCT/L 건설공사 #1, #2T/L 무부하가압","2019-06-25 14:00","2019-06-27 14:00","2019-06-25 14:00","2019-06-27 14:00","연속"]
[82,"경기","직할","화성S/S 345kV #2 CLR 75BUS GIS","345kV 화성S/S 362kV GIS 용량대체 및 SW 증설공사","O. 345kV 화성-신평택CC #1,2T/L 증설관련 무부하 가압","2019-06-18 10:00","2019-06-19 18:00","2019-06-18 10:00","2019-06-19 18:00","연속"]
[83,"경기","직할","화성평택T/P#1 T/L","345kV 화성S/S 362kV GIS 용량대체 및 SW 증설공사","O. 345kV 화성-신평택CC #1,2T/L 증설관련 무부하 가압","2019-06-18 10:00","2019-06-19 18:00","2019-06-18 10:00","2019-06-19 18:00","연속"]
[84,"경기","직할","화성S/S 345kV #2 CLR 76BUS GIS","345kV 화성S/S 362kV GIS 용량대체 및 SW 증설공사","O. 345kV 화성-신평택CC #1,2T/L 증설관련 무부하 가압","2019-06-18 10:00","2019-06-19 18:00","2019-06-18 10:00","2019-06-19 18:00","연속"]
[85,"강원","강릉","동해신양양 T/L","2018~19년 송전정비 협력회사 총액공사","○ 345kV 동해-신양양T/L No.80~81 등 19개소 스페이서댐퍼 교체작업","2019-06-10 07:00","2019-06-17 18:00","2019-06-10 07:00","2019-06-17 18:00","매일"]
[86,"강원","강릉","동해양양PP T/L","2018~19년 송전정비 협력회사 총액공사","○ 345kV 동해-양양PP T/L No.144~145 등 15개소 스페이서댐퍼 교체작업","2019-06-18 07:00","2019-06-20 18:00","2019-06-18 07:00","2019-06-20 18:00","매일"]
[87,"강원","강릉","양양P/P 345kV 신양양-양양P/PT/L-#1 M.Tr CB(7100)","장기 미동작 차단기 조작시험","장기 미동작 차단기 조작시험","2019-06-14 10:00","2019-06-14 14:00","2019-06-14 10:00","2019-06-14 14:00","당일"]
[88,"강원","강릉","양양P/P 345kV 동해-양양P/PT/L-#4 M.Tr 1 CB(7300)","장기 미동작 차단기 조작시험","장기 미동작 차단기 조작시험","2019-06-14 14:00","2019-06-14 18:00","2019-06-14 14:00","2019-06-14 18:00","당일"]
[89,"강원","동해","동해삼척GP#2 T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검 : 85기","2019-06-06 09:00","2019-06-09 18:00","2019-06-06 09:00","2019-06-09 18:00","매일"]
[90,"강원","동해","동해삼척GP#1 T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검 : 85기","2019-06-02 09:00","2019-06-05 18:00","2019-06-02 09:00","2019-06-05 18:00","매일"]
[91,"강원","동해","신제천동해#1 T/L","2018~2019년 송전정비회사 총액공사(전선접속개소 해소)","○ 작업내용 : 전선 접속개소 해소 ○ 공사구간 : No.293~297(2c-1.507km)","2019-06-24 07:00","2019-06-28 18:00","2019-06-24 07:00","2019-06-28 18:00","연속"]
[92,"강원","동해","삼척G/PS/S 삼척G/P한울N/P1#2T/L-#2M.Tr CB(7400)","삼척GP 345kV GIS 누유개소 보수공사","1. 누유개소 보수공사 2. [병행] 장기미동작 차단기 조작시험","2019-06-19 09:30","2019-06-19 13:30","2019-06-19 09:30","2019-06-19 13:30","당일"]
[93,"강원","동해","삼척G/PS/S 동해삼척G/P#1T/L-#3M.Tr CB(7600)","삼척GP 345kV GIS 누유개소 보수공사","1. 누유개소 보수공사 2. [병행] 장기미동작 차단기 조작시험","2019-06-21 09:30","2019-06-21 15:00","2019-06-21 09:30","2019-06-21 15:00","당일"]
[94,"강원","동해","삼척G/PS/S 345kV #3M.Tr 1차 CB(7672)","삼척GP 345kV GIS 누유개소 보수공사","1. 누유개소 보수공사 2. [병행] 장기미동작 차단기 조작시험","2019-06-19 14:00","2019-06-19 18:00","2019-06-19 14:00","2019-06-19 18:00","당일"]
[95,"강원","동해","삼척G/PS/S 345kV #2STEP UP CB(7572)","삼척GP #2StepUp Tr 측 LCP PNL 보수 공사","1. LCP PNL 보수공사 2. [병행] 장기미동작 차단기 조작시험","2019-06-18 09:30","2019-06-18 18:00","2019-06-18 09:30","2019-06-18 18:00","당일"]
[96,"강원","동해","삼척G/P #1 Tie-Tr CB","삼척GP 345kV #1M.Tr 누유개소 보수공사","1. 누유개소 보수공사 2. [병행] 장기미동작 차단기 조작시험","2019-06-24 09:30","2019-06-25 18:00","2019-06-24 09:30","2019-06-25 18:00","연속"]
[97,"강원","태백","신태백S/S #74BAYT/L CB(7472)","18~19년 변전전문회사 총액공사","신태백변전소 7472CB 조작시험","2019-06-19 10:00","2019-06-19 18:00","2019-06-17 10:00","2019-06-17 14:00","당일"]
[98,"강원","태백","신태백S/S #2Sh.R 1차-#74BAYT/L TIE CB(7400)","18~19년 변전전문회사 총액공사","신태백변전소 7400CB 조작시험","2019-06-18 10:00","2019-06-18 18:00","취소","취소","당일"]
[99,"강원","태백","신태백S/S #2 Sh.R 1차 #1-1 CB(7479)","18~19년 변전전문회사 총액공사","신태백변전소 7479CB 조작시험","2019-06-17 10:00","2019-06-17 18:00","취소","취소","당일"]
[100,"강원","태백","신태백S/S #2 Sh.R 1차 #1-2 CB(7471)","18~19년 변전전문회사 총액공사","신태백변전소 7471CB 조작시험","2019-06-14 10:00","2019-06-14 18:00","취소","취소","당일"]
[101,"강원","태백","신태백S/S #73 BAY T/L CB(7372)","18~19년 변전전문회사 총액공사","신태백변전소 7372CB 조작시험","2019-06-13 10:00","2019-06-13 18:00","2019-06-19 14:00","2019-06-19 18:00","당일"]
[102,"강원","태백","신태백S/S #2 M.Tr 2차 TIE CB(7300)","18~19년 변전전문회사 총액공사","신태백변전소 7300CB 조작시험","2019-06-12 10:00","2019-06-12 18:00","2019-06-19 10:00","2019-06-19 14:00","당일"]
[103,"강원","태백","신태백S/S 신태백-한울N/P2#2T/L CB (7672)","18~19년 변전전문회사 총액공사","신태백변전소 7672CB 조작시험","2019-06-24 10:00","2019-06-24 18:00","2019-06-20 10:00","2019-06-20 14:00","당일"]
[104,"강원","태백","신태백S/S 한울N/P2#2T/L-#3 M.Tr CB(7600)","18~19년 변전전문회사 총액공사","신태백변전소 7600CB 조작시험","2019-06-25 10:00","2019-06-25 18:00","2019-06-18 14:00","2019-06-18 18:00","당일"]
[105,"강원","태백","신태백S/S #2 M.Tr 2차 CB(7371)","18~19년 변전전문회사 총액공사","신태백변전소 7371CB 조작시험","2019-06-26 10:00","2019-06-26 18:00","2019-06-18 10:00","2019-06-18 14:00","당일"]
[106,"강원","태백","신태백S/S 신태백-한울N/P2#1T/L CB(7572)","18~19년 변전전문회사 총액공사","신태백변전소 7572CB 조작시험","2019-06-20 10:00","2019-06-20 18:00","2019-06-17 14:00","2019-06-17 18:00","당일"]
[107,"강원","태백","신태백S/S #3 M.Tr 2차 CB(7671)","18~19년 변전전문회사 총액공사","신태백변전소 7671CB 조작시험","2019-06-21 10:00","2019-06-21 18:00","2019-06-20 14:00","2019-06-20 18:00","당일"]
[108,"충북","직할","신진천S/S #4 M.Tr","2019년 직할 변전정비회사 총액공사(조작시험)","#4M.Tr 2차 차단기 조작시험(개폐타임 측정)","2019-06-05 15:00","2019-06-05 16:30","2019-06-05 15:00","2019-06-05 16:30","당일"]
[109,"충북","직할","서안성신진천#2 T/L","345kV 신진천S/S 용량부족 GIS 대체공사","신진천S/S 345kV 73BAY 차단기 용량변경 2CB-양 모선 제외","2019-06-11 08:00","2019-09-11 18:00","취소","취소","연속"]
[110,"충북","청주","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L 안전이격거리 확보공사","철탑설치 2기, 철탑철거 3기(가철탑 2기 설치), 전선가선(1,211km)","2019-06-26 08:00","2019-06-28 19:00","2019-06-26 08:00","2019-06-28 19:00","연속"]
[111,"충북","청주","신옥천신남원#2 T/L","345kV 신옥천-신남원T/L 안전이격거리 확보공사","철탑설치 2기, 철탑철거 3기(가철탑 2기 설치), 전선가선(1,211km)","2019-06-06 08:00","2019-06-25 19:00","2019-06-06 08:00","2019-06-25 19:00","연속"]
[112,"충북","청주","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L 안전이격거리 확보공사","철탑설치 2기, 철탑철거 3기(가철탑 2기 설치), 전선가선(1,211km)","2019-06-03 08:00","2019-06-05 19:00","2019-06-03 08:00","2019-06-05 19:00","연속"]
[113,"충북","청주","신옥천S/S #3 M.Tr","18~19년 청주전력 변전협력회사 총액공사","신옥천S/S #3Sh.R 보호반 대체","2019-06-17 09:00","2019-06-17 18:00","2019-06-17 09:00","2019-06-17 18:00","당일"]
[114,"충북","청주","신옥천S/S #2 M.Tr","18~19년 청주전력 변전협력회사 총액공사","신옥천S/S #2Sh.R 보호반 대체","2019-06-13 09:00","2019-06-13 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[115,"충북","청주","신옥천S/S #1 M.Tr","18~19년 청주전력 변전협력회사 총액공사","신옥천S/S #1Sh.R 보호반 대체","2019-06-10 09:00","2019-06-10 18:00","2019-06-10 09:00","2019-06-10 18:00","당일"]
[116,"충북","청주","청원S/S #3 M.Tr","18~19년 청주전력 변전협력회사 총액공사","청원S/S #3M.Tr 2차 154kV GIS 보통점검","2019-06-07 09:00","2019-06-07 18:00","2019-06-07 09:00","2019-06-07 18:00","당일"]
[117,"대전충남","대전","신계룡청양 T/L","154kV 신계룡-청양T/L 전력선 교체공사","전력선 교체 (No.77~79 등 6구간)","2019-06-03 07:00","2019-06-15 18:00","2019-06-03 07:00","2019-06-15 18:00","연속"]
[118,"대전충남","서산","신당진신당진개폐소#1 T/L","송전선로 보호배전반 업그레이드 작업","345kV 신당진-연락#1T/L 보호배전반 업그레이드 작업","2019-06-17 09:00","2019-06-17 18:00","2019-06-17 09:00","2019-06-17 18:00","당일"]
[119,"대전충남","서산","신당진신당진개폐소#2 T/L","송전선로 보호배전반 업그레이드 작업","345kV 신당진-연락#2T/L 보호배전반 업그레이드 작업","2019-06-18 09:00","2019-06-18 18:00","2019-06-18 09:00","2019-06-18 18:00","당일"]
[120,"대전충남","서산","신서산신당진#2 T/L","345kV 신서산-신당진#2T/L 피뢰기 설치공사","345kV 신서산-신당진#2T/L 피뢰기 설치공사 No.1~42(전원측 설치)","2019-06-04 07:30","2019-06-11 18:00","2019-06-04 07:30","2019-06-11 18:00","매일"]
[121,"대전충남","서산","태안T/P 7호기 1차 CB A (7772A)","'19년 서산전력지사 765/345kV GIS 점검공사","354kV 태안T/P 7호기 1차 CB(7772) 정밀점검","2019-06-03 09:00","2019-06-07 18:00","2019-06-03 09:00","2019-06-07 18:00","연속"]
[122,"대전충남","아산","청양신온양#2 T/L","[송전]345kV 청양-신온양T/L 120호 안전이격확보공사","345kV 청양-신온양T/L 120호 안전이격확보공사","2019-06-10 07:00","2019-06-14 18:00","취소","취소","연속"]
[123,"대전충남","아산","청양신온양#1 T/L","[송전]345kV 청양-신온양T/L 120호 안전이격확보공사","345kV 청양-신온양T/L 120호 안전이격확보공사","2019-06-03 07:00","2019-06-07 18:00","취소","취소","연속"]
[124,"대전충남","아산","신서산아산#2 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-06-15 07:00","2019-06-25 18:00","취소","취소","연속"]
[125,"대전충남","아산","신서산아산#1 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-06-04 07:00","2019-06-14 18:00","취소","취소","연속"]
[126,"대전충남","아산","아산S/S #3 M.Tr","아산S/S 345kV #3M.Tr 하자점검 등","○아산S/S 345kV #3M.Tr 하자점검 등","2019-06-25 09:00","2019-06-26 18:00","2019-06-25 09:00","2019-06-26 18:00","연속"]
[127,"대전충남","아산","아산S/S #4 M.Tr","아산S/S 345kV #4M.Tr 1차 LA 교체 및 개폐타임 측정","○아산S/S 345kV #4M.Tr 1차 LA 교체 및 개폐타임 측정","2019-06-27 09:00","2019-06-27 18:00","2019-06-27 09:00","2019-06-27 18:00","당일"]
[128,"대전충남","청양","청양보령화력#1 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","보령화력 제2발전소 접속설비(362kV GIS) 교체공사(4차) - 76BUS 교체","2019-06-23 09:00","2019-06-24 18:00","2019-06-23 09:00","2019-06-24 18:00","연속"]
[129,"대전충남","청양","청양보령화력#1 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","보령화력 제2발전소 접속설비(362kV GIS) 교체공사(4차) - 76BUS 교체","2019-06-19 09:00","2019-06-20 18:00","2019-06-19 09:00","2019-06-20 18:00","연속"]
[130,"대전충남","청양","보령T/P 345kV #76 BUS","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","○ 보령화력 345kV 76BUS 교체","2019-06-17 09:00","2019-07-11 18:00","2019-06-17 09:00","2019-07-11 18:00","연속"]
[131,"대전충남","청양","보령T/P 345kV #2 M.Tr 1차 CB A (7272(A))","보령T/P 362kV 차단기 보통점검","보령T/P 362kV 차단기 보통점검(7272)","2019-06-12 09:00","2019-06-12 18:00","2019-06-12 09:00","2019-06-12 18:00","당일"]
[132,"대전충남","청양","아산보령화력#2 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사","보령화력 제2발전소 접속설비(362kV GIS) 교체공사(4차) - 71BUS 교체","2019-06-10 09:00","2019-06-13 18:00","2019-06-10 09:00","2019-06-13 18:00","연속"]
[133,"대전충남","청양","보령T/P 보령연락#1T/L-#2 M.Tr 1차 CB A (7200(A))","보령T/P 362kV 차단기 보통점검","보령T/P 362kV 차단기 보통점검(7200)","2019-06-11 09:00","2019-06-11 18:00","2019-06-11 09:00","2019-06-11 18:00","당일"]
[134,"대전충남","청양","신옥천청양 T/L","[송전]345kV 신옥천-청양T/L 지장철탑이설공사[요청자직접시행]","ㅇ 요청자(성인산업) 직접시행 지장이설공사 ㅇ 철탑 : 3기 철거(No.145,146,147), 4기 설치(No.145,146,146-1,147) ㅇ 전력선 : ACSR480 x 4B x 2C (선로길이 : 1.802km x 2C) ㅇ 가철탑 2기 설치철거 외 기타 부대공사 시행","2019-06-16 07:00","2019-06-24 18:00","2019-06-16 07:00","2019-06-24 18:00","연속"]
[135,"대전충남","청양","신계룡청양 T/L","[송전]345kV 신옥천-청양T/L 지장철탑이설공사[요청자직접시행]","ㅇ 요청자(성인산업) 직접시행 지장이설공사 ㅇ 철탑 : 3기 철거(No.145,146,147), 4기 설치(No.145,146,146-1,147) ㅇ 전력선 : ACSR480 x 4B x 2C (선로길이 : 1.802km x 2C) ㅇ 가철탑 2기 설치철거 외 기타 부대공사 시행","2019-06-27 07:00","2019-07-01 18:00","2019-06-27 07:00","2019-07-01 18:00","연속"]
[136,"전북","김제","신김제S/S #3 M.Tr","345kV 변압기 3차측 누유개소 보수","#3M.Tr 3차측 누유보수","2019-06-04 09:30","2019-06-04 18:00","2019-06-04 09:30","2019-06-04 18:00","당일"]
[137,"전북","김제","신김제한빛NP#2 T/L","345kV 신김제-한빛#2T/L 전선접속개소 해소공사","공사개요 ○ 전력선 교체 : 1.862C-km (No.117〜122호) ○ 연가해소 : 2기 (No.49,200호) ○ 점퍼선 교체 : 1기 (No.207호) ○ 애자련 보강 : 2기 (No.43,44호)","2019-06-12 08:00","2019-06-21 18:00","2019-06-12 08:00","2019-06-21 18:00","연속"]
[138,"전북","직할","신남원한빛NP#2 T/L","345kV 신남원-한빛#2T/L 전선 교체공사","No.121~124, 158~159, 167~171호 전력선 교체 No.27,124호 연가해소, No.24호 등 7기 점퍼선 교체 등 ","2019-06-24 07:00","2019-07-05 18:00","2019-06-24 07:00","2019-07-05 18:00","연속"]
[139,"광주전남","광주","신남원신광주#1 T/L","345kV 신남원-신광주 접속개소해소공사","No.137~140,153~155,156호","2019-06-17 08:00","2019-06-21 18:00","2019-06-17 08:00","2019-06-21 18:00","연속"]
[140,"광주전남","광주","신남원신광주#2 T/L","345kV 신남원-신광주 접속개소해소공사","No.137~140,153~155,156호","2019-06-24 08:00","2019-06-28 18:00","2019-06-24 08:00","2019-06-28 18:00","연속"]
[141,"광주전남","광주","신광주S/S #1 M.Tr 1차 CB(7172)","19년 광주변전총액(345kV 7172 장기미동작차단기점검)","신광주S/S 345kV 7172 장기미동작차단기점검","2019-06-03 15:00","2019-06-03 17:00","2019-06-03 15:00","2019-06-03 17:00","당일"]
[142,"광주전남","광주","신광주S/S 신광주-한빛NP #1T/L CB(7171)","19년 광주변전총액(345kV 7171 장기미동작차단기점검)","신광주S/S 345kV 7171 장기미동작차단기점검","2019-06-03 11:00","2019-06-03 13:00","2019-06-03 11:00","2019-06-03 13:00","당일"]
[143,"광주전남","광주","신광주S/S #2 M.Tr 1차 CB(7472)","19년 광주변전총액(345kV 7472 장기미동작차단기점검)","신광주S/S 345kV 7472 장기미동작차단기점검","2019-06-03 09:00","2019-06-03 11:00","2019-06-03 09:00","2019-06-03 11:00","당일"]
[144,"광주전남","광주","신광주S/S 신광주-한빛NP #1T/L TIE CB(7100)","19년 광주변전총액(345kV 7100 장기미동작차단기점검)","신광주S/S 345kV 7100 장기미동작차단기점검","2019-06-03 13:00","2019-06-03 15:00","2019-06-03 13:00","2019-06-03 15:00","당일"]
[145,"광주전남","광주","신화순S/S 신광주-신화순#2T/L CB(7871)","19년 광주변전총액(345kV 7871 장기미동작차단기점검)","신화순S/S 345kV 7871 장기미동작차단기점검","2019-06-05 11:00","2019-06-05 13:00","2019-06-05 11:00","2019-06-05 13:00","당일"]
[146,"광주전남","광주","신화순S/S #2 M.TR 1차 CB(7772)","19년 광주변전총액(345kV 7772 장기미동작차단기점검)","신화순S/S 345kV 7772 장기미동작차단기점검","2019-06-05 09:00","2019-06-05 11:00","2019-06-05 09:00","2019-06-05 11:00","당일"]
[147,"광주전남","광주","신화순S/S 신광주신화순#1T/L-#2M.TR CB(7700)","19년 광주변전총액(345kV 7700 장기미동작차단기점검)","신화순S/S 345kV 7700 장기미동작차단기점검","2019-06-04 15:00","2019-06-04 17:00","2019-06-04 15:00","2019-06-04 17:00","당일"]
[148,"광주전남","광주","신화순S/S 신광주-신화순#1T/L CB(7771)","19년 광주변전총액(345kV 7771 장기미동작차단기점검)","신화순S/S 345kV 7771 장기미동작차단기점검","2019-06-04 13:00","2019-06-04 15:00","2019-06-04 13:00","2019-06-04 15:00","당일"]
[149,"광주전남","광주","신화순S/S 신광주-신화순#2T/L TIE CB(7800)","19년 광주변전총액(345kV 7800 장기미동작차단기점검)","신화순S/S 345kV 7800 장기미동작차단기점검","2019-06-05 13:00","2019-06-05 15:00","2019-06-05 13:00","2019-06-05 15:00","당일"]
[150,"광주전남","광주","신화순S/S 신화순-신강진#2T/L CB(7971)","19년 광주변전총액(345kV 7971 장기미동작차단기점검)","신화순S/S 345kV 7971 장기미동작차단기점검","2019-06-05 15:00","2019-06-05 17:00","2019-06-05 15:00","2019-06-05 17:00","당일"]
[151,"광주전남","광주","신화순S/S 신화순신강진#2TL-#1M.TR CB(7900)","19년 광주변전총액(345kV 7900 장기미동작차단기점검)","신화순S/S 345kV 7900 장기미동작차단기점검","2019-06-20 09:00","2019-06-20 11:00","2019-06-20 09:00","2019-06-20 11:00","당일"]
[152,"광주전남","광주","신화순S/S #1 M.TR 1차 CB(7972)","19년 광주변전총액(345kV 7972 장기미동작차단기점검)","신화순S/S 345kV 7972 장기미동작차단기점검","2019-06-20 11:00","2019-06-20 13:00","2019-06-20 11:00","2019-06-20 13:00","당일"]
[153,"광주전남","광주","신화순S/S 신화순-신강진#1T/L CB(7A71)","19년 광주변전총액(345kV 7A71 장기미동작차단기점검)","신화순S/S 345kV 7A71 장기미동작차단기점검","2019-06-20 13:00","2019-06-20 15:00","2019-06-20 13:00","2019-06-20 15:00","당일"]
[154,"광주전남","광주","신화순S/S 신화순-신강진#1T/L TIE CB (7A00)","19년 광주변전총액(345kV 7A00 장기미동작차단기점검)","신화순S/S 345kV 7A00 장기미동작차단기점검","2019-06-20 15:00","2019-06-20 17:00","2019-06-20 15:00","2019-06-20 17:00","당일"]
[155,"광주전남","광주","신화순S/S #1 M.Tr","신화순S/S 345kV #1M.Tr 휴전 (변전협력회사공사)","신화순변전소 79BAY B/F 교체","2019-06-10 09:00","2019-06-13 18:00","2019-06-10 09:00","2019-06-13 18:00","연속"]
[156,"광주전남","광주","신화순S/S 345KV #3 M.TR 1차 CB C (7572-C)","19년 광주변전총액(345kV 7572 장기미동작차단기점검)","신화순S/S 345kV 7572 장기미동작차단기점검","2019-06-04 11:00","2019-06-04 13:00","2019-06-04 11:00","2019-06-04 13:00","당일"]
[157,"광주전남","광주","신화순S/S 345KV #3 M.TR 1차 TIE CB B (7500-B)","19년 광주변전총액(345kV 7500 장기미동작차단기점검)","신화순S/S 345kV 7500 장기미동작차단기점검","2019-06-04 09:00","2019-06-04 11:00","2019-06-04 09:00","2019-06-04 11:00","당일"]
[158,"광주전남","광주","신화순S/S #2 M.Tr A","신화순S/S 345kV #2M.Tr 휴전 (변전협력회사공사)","1.신화순S/S 345kV #2M.Tr 2차 접지불량 조작함수리 2.신화순S/S 345kV #2M.Tr B상 상부 누유개소 해소작업","2019-06-17 09:00","2019-06-18 18:00","2019-06-17 09:00","2019-06-18 18:00","연속"]
[159,"광주전남","목포","한빛3N/P 345kV 한빛연락#3T/L GIS","한빛N/P #3S/Y GIS 보통점검(7C Bay)","`18~19년 변전협력 총액공사 한빛N/P #3S/Y GIS 보통점검(7C Bay)","2019-06-25 09:00","2019-06-27 18:00","2019-06-25 09:00","2019-06-27 18:00","연속"]
[160,"광주전남","순천","여수T/P #1 Tie-Tr","여수화력S/Y #1M.Tr 2차 전력케이블 EBA 교체공사","#1M.Tr 2차 전력케이블 EBA 교체(자기애관-&gt폴리머)","2019-06-18 09:00","2019-06-20 18:00","2019-06-18 09:00","2019-06-20 18:00","연속"]
[161,"대구","경산","신경산S/S 345kV #75 BUS","신경산S/S 362kV GIS 대체공사(73BAY)","○ 7352DS 관련 준공시험 ○ 신설GIS 무부하 가압(인출~7300CB~7372CB~#2BUS)","2019-06-03 09:00","2019-06-04 18:00","2019-06-03 09:00","2019-06-04 18:00","연속"]
[162,"대구","경산","신경산대구#2 T/L","2019년 가공송전 순시점검 위탁공사 정밀점검","345kV 신경산-대구#2T/L 정밀점검 시행(No.1-107)","2019-06-10 08:00","2019-06-18 18:00","2019-06-10 08:00","2019-06-11 18:00","연속"]
[163,"대구","경산","신경산S/S 345kV #70 BUS","신경산S/S 362kV GIS 대체공사(73BAY)","○ 7351DS 관련 준공시험 ○ 신설GIS 무부하 가압(인출~7371CB~#1BUS)","2019-06-01 09:00","2019-06-03 09:00","2019-06-01 09:00","2019-06-03 09:00","연속"]
[164,"대구","경산","울주신경산#1 T/L","신경산S/S 362kV GIS 대체공사(72BAY)","○ #1BUS 접속 건전성 확보관련 무부하 가압","2019-06-27 18:00","2019-06-28 09:00","2019-06-27 18:00","2019-06-28 09:00","연속"]
[165,"대구","경산","울주신경산#1 T/L","신경산S/S 362kV GIS 대체공사(72BAY)","○ #2BUS 접속 건전성 확인 무부하 가압","2019-06-18 18:00","2019-06-19 09:00","2019-06-19 18:00","2019-06-20 09:00","연속"]
[166,"대구","경산","신경산대구#1 T/L","신경산S/S 362kV GIS 대체공사(72BAY)","○ #1BUS 철거 및 설치 안전이격 확보","2019-06-21 09:00","2019-06-21 18:00","2019-06-22 09:00","2019-06-22 18:00","당일"]
[167,"대구","경산","신경산S/S 345kV #70 BUS","신경산S/S 362kV GIS 대체공사(72BAY)","○ BUS 및 7251DS, 7271CB 철거 및 설치 ○ 모선PT 및 ES 철거 및 설치 ○ 모선PT 및 ES 준공시험, 무부하 가압","2019-06-19 09:00","2019-06-28 09:00","2019-06-20 09:00","2019-06-28 09:00","연속"]
[168,"대구","경산","신경산대구#1 T/L","2019년 가공송전 순시점검 위탁공사 정밀점검","345kV 신경산-대구#1T/L 정밀점검 시행(No.1-107)","2019-06-19 08:00","2019-06-27 18:00","2019-06-19 08:00","2019-06-27 18:00","연속"]
[169,"대구","경산","신경산S/S #2 M.Tr","신경산S/S 362kV GIS 대체공사(72BAY)","○ #2BUS 철거 및 설치 안전이격 확보","2019-06-12 09:00","2019-06-12 18:00","2019-06-14 09:00","2019-06-14 18:00","당일"]
[170,"대구","경산","신경산대구#2 T/L","신경산S/S 362kV GIS 대체공사(72BAY)","○ 신경산-대구#2T/L GIS 철거 및 설치 ○ 준공시험 및 무부하 가압","2019-06-10 09:00","2019-07-18 18:00","2019-06-12 09:00","2019-07-16 18:00","연속"]
[171,"대구","경산","신경산S/S 345kV #75 BUS","신경산S/S 362kV GIS 대체공사(72BAY)","○ BUS 및 7202(7252)DS, 7200CB 철거 및 설치 ○ 모선PT 및 ES 철거 및 설치 ○ 모선PT 및 ES 준공시험, 무부하 가압","2019-06-10 09:00","2019-06-19 09:00","2019-06-12 09:00","2019-06-20 09:00","연속"]
[172,"대구","달성","서대구고령#2 T/L","고령S/S 362kV GIS CT 교체공사(무부하 가압용)","고령S/S 362kV GIS CT 교체공사(무부하 가압_24시간) - 71BAY 무부하 가압","2019-06-04 09:00","2019-06-05 18:00","2019-06-08 09:00","2019-06-09 18:00","연속"]
[173,"대구","달성","고령S/S 345kV #70 BUS","고령S/S 362kV GIS CT 교체공사(무부하 가압용)","고령S/S 362kV GIS CT 교체공사(무부하 가압_24시간) - 71BAY 무부하 가압","2019-06-04 09:00","2019-06-05 18:00","2019-06-08 09:00","2019-06-09 18:00","연속"]
[174,"대구","달성","서대구고령#1 T/L","2019년 달성전력지사 가공송전 순시점검 위탁공사","초기점검(구간 : 16,18호)","2019-06-05 09:00","2019-06-05 18:00","2019-06-12 08:30","2019-06-12 18:00","당일"]
[175,"대구","칠곡","북대구S/S 345kV 북대구-선산T/L-TIE CB A (7200)","북대구S/S TIE 북대구-선산 7200GIS 보통점검","북대구S/S TIE 북대구-선산 7200GIS 보통점검","2019-06-11 09:30","2019-06-11 18:00","취소","취소","당일"]
[176,"대구","칠곡","서대구S/S 북경남-서대구#1T/L CB A (7471)","서대구S/S 북경남-서대구#1T/L 7471 GCB 장기미동작점검","서대구S/S 북경남-서대구#1T/L 7471 GCB 장기미동작점검","2019-06-07 09:30","2019-06-07 12:00","취소","취소","당일"]
[177,"대구","칠곡","서대구S/S 345kV 서대구-고령#1T/L CB A (7172)","서대구S/S 서대구-고령#1T/L 7172 GCB 장기미동작점검","서대구S/S 서대구-고령#1T/L 7172 GCB 장기미동작점검","2019-06-03 09:30","2019-06-03 12:00","취소","취소","당일"]
[178,"대구","포항","신포항신영일 T/L","신포항-신영일T/L 송전선로 보호반 교체공사","신포항-신영일T/L 송전선로 보호반 교체공사","2019-06-03 09:00","2019-06-07 18:00","2019-06-17 09:00","2019-06-21 18:00","연속"]
[179,"경북","구미","서대구선산#1 T/L","19년 구미전력지사 변전정비업체 총액공사","- GIS 조작시험","2019-06-14 09:00","2019-06-14 18:00","2019-06-14 09:00","2019-06-14 18:00","당일"]
[180,"경북","영주","신영주한울NP2#1 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #1T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #1T/L GIB용 보호반 설치","2019-06-10 10:00","2019-06-14 14:00","취소","취소","연속"]
[181,"경북","영주","신제천신영주#2 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","신제천-신영주#2T/L 송전선로 보호반 대체공사 7B71 7B00 GIS 하자점검 YPP 성능개선 시행","2019-06-17 09:00","2019-06-21 18:00","2019-06-17 09:00","2019-06-21 18:00","연속"]
[182,"경북","영주","신영주한울NP2#2 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #1T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #1T/L GIB용 보호반 설치","2019-06-17 10:00","2019-06-21 14:00","취소","취소","연속"]
[183,"경북","영주","신영주S/S #1 M.Tr","2018-19년도 영주전력지사 변전협력업체 총액공사","신영주S/S 345kV #1M.Tr 보통점검","2019-06-24 09:00","2019-06-28 18:00","2019-06-24 09:00","2019-06-28 18:00","연속"]
[184,"경북","직할","신영주청송PP T/L","18~19년 경북직할 변전정비회사 총액공사","청송양수S/Y 신영주-청송PP 송전선로 보호반 대체공사","2019-06-10 09:00","2019-06-14 18:00","2019-06-10 09:00","2019-06-14 18:00","연속"]
[185,"부산울산","동부산","신양산신대연#1 T/L","신양산E/C 362kV GIS 보통점검","신양산E/C 362kV 7271,7200GIS 보통점검(신양산-신대연#1T/L)","2019-06-19 09:30","2019-06-20 18:00","2019-06-19 09:30","2019-06-20 18:00","연속"]
[186,"부산울산","동부산","신양산신대연#2 T/L","154kV 시랑분기T/L 건설공사","154kV 시랑분기T/L 계통연결 작업을 위한 안전거리확보 (상단 : 345kV 신양산-신대연T/L, 하단 : 154kV 신양산-좌동T/L) - 전력선 긴선 및 가공지선설치 : 기설 신양산-좌동#1T/L 16호 - 신설 1호, 기설 17호 - 신설 1호","2019-06-26 00:08","2019-06-29 18:00","2019-06-26 00:08","2019-06-29 18:00","연속"]
[187,"부산울산","동부산","신양산신대연#1 T/L","154kV 시랑분기T/L 건설공사","154kV 시랑분기T/L 계통연결 작업을 위한 안전거리확보 (상단 : 345kV 신양산-신대연T/L, 하단 : 154kV 신양산-좌동T/L) - 전력선 긴선 및 가공지선설치 : 기설 신양산-좌동#2T/L 16호 - 신설 1호, 기설 17호 - 신설 1호","2019-06-10 08:00","2019-06-15 18:00","2019-06-10 08:00","2019-06-15 18:00","연속"]
[188,"부산울산","울산","동울산신울산#2 T/L","OPGW 중요선로 점검결과 불량사항 정비공사","345㎸ 동울산-신울산#2T/L 불량 OPGW 금구류 교체(No.40호 등 철탑 10기)","2019-06-19 08:00","2019-06-21 18:00","2019-06-19 08:00","2019-06-21 18:00","연속"]
[189,"부산울산","울산","동울산신울산#1 T/L","OPGW 중요선로 점검결과 불량사항 정비공사","345㎸ 동울산-신울산#1T/L 불량 OPGW 금구류 교체(No.125호)","2019-06-18 08:00","2019-06-18 18:00","2019-06-18 08:00","2019-06-18 18:00","당일"]
[190,"부산울산","울산","동울산월성NP#2 T/L","OPGW 중요선로 점검결과 불량사항 정비공사","345㎸ 동울산-월성NP#2T/L 불량 OPGW 금구류 교체(No.3호 등 철탑 11기)","2019-06-24 08:00","2019-06-27 18:00","2019-06-24 08:00","2019-06-27 18:00","연속"]
[191,"부산울산","울산","신온산S/S #1 M.Tr","2018~19년 변전협력 총액공사","- 1,2차 피뢰기 A,B,C상 교체","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[192,"부산울산","울산","신온산S/S #3 M.Tr","2018~19년 변전협력 총액공사","- 1,2차 피뢰기 A,B,C상 교체","2019-06-05 09:00","2019-06-05 18:00","2019-06-05 09:00","2019-06-05 18:00","당일"]
[193,"부산울산","울산","신울산S/S #2 M.Tr 1차 CB(7371)","2018~19년 변전협력 총액공사","- 7371 차단기 동작시험","2019-06-07 09:00","2019-06-07 18:00","2019-06-14 09:00","2019-06-14 18:00","당일"]
[194,"부산울산","울산","신울산S/S 고리NP#1T/L-#3 M.Tr 1차 CB(7500)","18~19년 변전협력 총액공사","- 7500GIS 보통점검","2019-06-03 09:00","2019-06-03 18:00","2019-06-03 09:00","2019-06-03 18:00","당일"]
[195,"부산울산","울산","신온산신울산#1 T/L","울산전력지사 관내 OPGW 항공장애표시구 설치공사","345㎸ 신울산-신온산#1T/L No.21호~No.22호 구간 항공장애표시구 설치","2019-06-13 08:00","2019-06-13 18:00","2019-06-13 08:00","2019-06-13 18:00","당일"]
[196,"부산울산","울산","신온산신울산#2 T/L","울산전력지사 관내 OPGW 항공장애표시구 설치공사","345㎸ 신울산-신온산#2T/L No.21호~No.22호 구간 항공장애표시구 설치","2019-06-14 08:00","2019-06-14 18:00","2019-06-14 08:00","2019-06-14 18:00","당일"]
[197,"부산울산","울산","울주월성NP#2 T/L","2018~19년 변전협력 총액공사","- 7A71, 7A00GIS 차단기 동작시험 - CVT교체작업","2019-06-06 09:00","2019-06-06 18:00","2019-06-06 09:00","2019-06-06 18:00","당일"]
[198,"부산울산","울산","울주고리NP#2 T/L","2018~19년 변전협력 총액공사","- 7571GIS 차단기 동작시험 - CVT교체작업","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[199,"부산울산","울산","울주S/S #4 M.Tr 1차 CB(7872)","2018~19년 변전협력 총액공사","- 7872GIS 차단기 동작시험","2019-06-05 12:00","2019-06-05 15:00","2019-06-05 12:00","2019-06-05 15:00","당일"]
[200,"부산울산","울산","울주S/S 울주-월성NP#1T/L TIE CB(7900)","2018~19년 변전협력 총액공사","- 7900GIS 차단기 동작시험","2019-06-05 15:00","2019-06-05 18:00","2019-06-05 15:00","2019-06-05 18:00","당일"]
[201,"부산울산","울산","울주S/S 345kV #3 M.Tr 1차 CB A (7672-A)","2018~19년 변전협력 총액공사","- 7672GIS 차단기 동작시험","2019-06-05 09:00","2019-06-05 12:00","2019-06-05 09:00","2019-06-05 12:00","당일"]
[202,"부산울산","직할","신대연S/S 345kV #2 Sh.R 1차 GIS","2019년 직할 변전협력회사 총액공사","- 신대연S/S #2Sh.R,7579 GIS 미동작점검","2019-06-14 10:00","2019-06-14 18:00","2019-06-14 10:00","2019-06-14 18:00","당일"]
[203,"부산울산","직할","신대연S/S 345kV #2 Sh.R CB","2019년 직할 변전협력회사 총액공사","- 신대연S/S #2Sh.R,7579 GIS 미동작점검","2019-06-14 10:00","2019-06-14 18:00","2019-06-14 10:00","2019-06-14 18:00","당일"]
[204,"경남","직할","신김해신녹산#1 T/L","2018~19년도 경남본부 직할 송전협력회사 총액공사","345kV 신김해-신녹산#1T/L 불량애자(폴리머) 교체","2019-06-03 07:00","2019-06-04 18:00","2019-06-03 07:00","2019-06-04 18:00","매일"]
[205,"경남","직할","신김해신녹산#2 T/L","2018~19년도 경남본부 직할 송전협력회사 총액공사","345kV 신김해-신녹산#2T/L 불량애자(폴리머) 교체","2019-06-05 07:00","2019-06-05 12:00","2019-06-05 07:00","2019-06-05 12:00","당일"]
[206,"경남","직할","창원삼천포TP#1 T/L","345 창원-삼천포화력T/L 102-105호 등 5개구간 전력선 교체공사","전선접속개소 전력선 교체 및 노후 스페이셔 댐퍼 교체","2019-06-01 07:00","2019-06-20 18:00","2019-06-01 07:00","2019-06-20 18:00","연속"]
[207,"경남","진주","산청P/P 의령-산청PP#1T/L-#2 M.Tr CB(7271)","산청P/P 의령-산청PP#1T/L-#2M.Tr 1차(7271) 정밀점검","산청P/P 의령-산청PP#1T/L-#2M.Tr 1차 CB(7271) 정밀점검","2019-06-24 09:00","2019-06-30 18:00","2019-06-24 09:00","2019-06-30 18:00","연속"]
[208,"경남","진주","산청P/P 의령-산청PP#1T/L-#1 M.Tr CB(7100)","산청P/P 의령-산청PP#1T/L-#1M.Tr 1차(7100) 정밀점검","산청P/P 의령-산청PP#1T/L-#1M.Tr 1차 CB(7100) 정밀점검","2019-06-17 09:00","2019-06-23 18:00","2019-06-17 09:00","2019-06-23 18:00","연속"]
[209,"경남","진주","의령산청양수#2 T/L","345kV 의령-산청양수#2T/L 항공장애표시구 설치공사(가공지선)","ㅇ345kV 의령-산청양수T/L 항공장애표시구 설치 (총 33경간, 138개 설치 - 가공지선) - 작업구간 : 2~3, 6~7, 10~11, 12~13, 20~21, 24~25, 26~27, 29~30, 41~42, 44~45, 48~49, 51~52, 56~57, 59~60, 62~63, 64~65, 65~66, 66~67, 67~68, 6","2019-06-01 07:00","2019-06-07 18:00","2019-06-03 07:00","2019-06-11 18:00","매일"]
[210,"경남","진주","산청P/P 의령-산청PP#2T/L-#2 M.Tr CB(7200)","산청P/P 의령-산청PP#2T/L-#2M.Tr 1차(7200) 조작시험","산청P/P 의령-산청PP#2T/L-#2M.Tr 1차 CB(7200) 조작시험","2019-06-05 10:00","2019-06-05 18:00","2019-06-05 10:00","2019-06-05 18:00","당일"]
[211,"경남","진주","의령S/S 345kV #70 BUS","의령S/S 345kV #70BUS 모선보호반 대체공사","의령S/S 345kV #70BUS 모선보호반 대체공사","2019-06-15 09:00","2019-06-17 18:00","2019-06-15 09:00","2019-06-17 18:00","연속"]
[212,"경남","진주","의령S/S 345kV #75 BUS","의령S/S 345kV #75BUS 모선보호반 대체공사","의령S/S 345kV #75BUS 모선보호반 대체공사","2019-06-22 09:00","2019-06-24 18:00","2019-06-22 09:00","2019-06-24 18:00","연속"]
[213,"경남","진주","고령의령#1 T/L","의령S/S 345kV 고령-의령#1T/L 및 76B/F 보호반 대체공사","의령S/S 345kV 고령-의령#1T/L 및 76B/F 보호반 대체공사 [병행] 7671 CB 조작시험, PT하자점검","2019-06-25 09:00","2019-07-04 18:00","2019-06-25 09:00","2019-07-04 18:00","연속"]
[214,"경남","통영","신마산삼천포화력#2 T/L","삼천포,신고성S/S 용량부족차단기 대체공사","신마산-삼천포화력#2T/L 인출 점프선 횡진방지 장치 설치","2019-06-22 09:00","2019-06-22 18:00","2019-06-22 09:00","2019-06-22 18:00","당일"]
[215,"경남","통영","삼천포T/P TIE#1T/L-#2 G.Tr TIE CB(7200)","삼천포,신고성S/S 용량부족차단기 대체공사","신마산-삼천포화력#2T/L 점프선 횡진방지 장치 설치를 위한 안전거리 이격 확복(7200)","2019-06-22 09:00","2019-06-22 18:00","2019-06-22 09:00","2019-06-22 18:00","당일"]
[216,"경남","통영","삼천포T/P 345kV 삼천포-TIE#1T/L CB (7272)","삼천포,신고성S/S 용량부족차단기 대체공사","신마산-삼천포화력#2T/L 점프선 횡진방지 장치 설치를 위한 안전거리 이격 확복(7272)","2019-06-22 09:00","2019-06-22 18:00","2019-06-22 09:00","2019-06-22 18:00","당일"]
[217,"경남","통영","(신)신고성S/S 345kV 삼천포#1T/L-고성하이 CB(7A00)","삼천포,신고성S/S 용량부족차단기 대체공사","신마산-삼천포화력#2T/L 점프선 횡진방지 장치 설치를 위한 안전거리 이격 확보(7A00)","2019-06-22 09:00","2019-06-22 18:00","2019-06-22 09:00","2019-06-22 18:00","당일"]
[218,"경남","통영","(신)신고성S/S 345kV 삼천포-TIE#1T/L CB (7A72)","삼천포,신고성S/S 용량부족차단기 대체공사","신마산-삼천포화력#2T/L 점프선 횡진방지 장치 설치를 위한 안전거리 이격 확보(7A72)","2019-06-22 09:00","2019-06-22 18:00","2019-06-22 09:00","2019-06-22 18:00","당일"]
[219,"경남","통영","(신)신고성S/S 345kV G6호기 1차 CB(7671)","삼천포,신고성S/S 용량부족차단기 대체공사","6호기 인출측 시험 가압","2019-06-29 09:00","2019-06-30 09:00","2019-06-29 09:00","2019-06-30 09:00","연속"]
[220,"경남","통영","(신)신고성S/S 345kV #71 BUS CB","삼천포,신고성S/S 용량부족차단기 대체공사","6호기 인출측 시험 가압","2019-06-29 09:00","2019-06-30 09:00","2019-06-29 09:00","2019-06-30 09:00","연속"]
[221,"대구",null,"월성NP4호기 주변압기 CB(7700,7772)","소내전원 절체시험","소내전원 절체시험","2019-06-01 09:00","2019-06-02 22:00","2019-06-01 09:00","2019-06-02 22:00","연속"]
[222,"대구",null,"월성NP4호기 기동변압기 CB(7800,7872)","소내전원 절체시험","소내전원 절체시험","2019-06-01 09:00","2019-06-02 22:00","2019-06-01 09:00","2019-06-02 22:00","연속"]
[223,"대구",null,"월성NP4호기 주변압기 CB(7700,7772)","계통연결전 발전기 링크조립 및 대기","계통연결전 발전기 링크조립 및 대기","2019-06-02 22:00","2019-06-09 08:00","2019-06-02 22:00","2019-06-09 08:00","연속"]
[224,"대구",null,"월성NP2호기 주변압기 CB(7300,7372)","- 주변압기/소내용변압기 일반점검\n- 주/소내용변압기 보호계전기 \n   정기시험(차단기 연동시험 포함)","- 주변압기/소내용변압기 일반점검\n- 주/소내용변압기 보호계전기 \n   정기시험(차단기 연동시험 포함)","2019-06-12 09:00","2019-06-28 18:00","2019-06-12 09:00","2019-06-28 18:00","연속"]
[225,"광주전남",null,"한빛NP 6호기 주변압기 CB(7E00,7E71)","○ 주변압기 일반점검\n○ 소내보조변압기 일반점검\n○ 갑종보호계전기 삼중화 개선 및 준공시험","○ 주변압기 일반점검\n○ 소내보조변압기 일반점검\n○ 갑종보호계전기 삼중화 개선 및 준공시험","2019-06-01 09:00","2019-06-22 17:00","2019-06-01 09:00","2019-06-22 17:00","연속"]
[226,"광주전남",null,"한빛NP 6호기 대기보조변압기 CB(7C00,7C71)","○ 대기보조변압기 일반점검\n○ 갑종보호계전기 삼중화 개선 및 준공시험","○ 대기보조변압기 일반점검\n○ 갑종보호계전기 삼중화 개선 및 준공시험","2019-06-24 09:00","2019-07-08 17:00","2019-06-24 09:00","2019-07-08 17:00","연속"]

{"sheet":"154송부","index":3,"n_rows":450,"n_cols":16,"rows_kept":450,"cut":false,"hidden":false,"merged":[[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 6월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","천호구의#2 T/L","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-06-10 09:00","2019-06-11 17:30","2019-06-10 09:00","2019-06-11 17:30","연속"]
[2,"서울","성동","상계S/S 154kV 금오-상계#2T/L GIS","19년 성동P/O 관내 154kV 차단기 조작시험","154kV GIS 조작시험 (차단기 개폐타임 측정)","2019-06-14 10:00","2019-06-14 13:00","2019-06-14 10:00","2019-06-14 13:00","당일"]
[3,"서울","성동","성동S/S 154kV #65 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-06-19 15:30","2019-06-19 17:30","2019-06-19 15:30","2019-06-19 17:30","연속"]
[4,"서울","성동","성동휘경#2 T/L","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-06-24 09:00","2019-06-25 17:30","2019-06-24 09:00","2019-06-25 17:30","연속"]
[5,"서울","성동","성동S/S 154kV #61 BUS","154kV 성동-왕십리E/C SW 증설공사","O 170kV GIS 50kA 2000A x 2CCT(성동 및 왕십리 각 1CCT) O 송전선로 보호배전반 각 1면(단거리보호방식, 재폐로 미적용) O 기타 부대설비","2019-06-17 09:00","2019-06-21 18:00","2019-06-17 09:00","2019-06-21 18:00","연속"]
[6,"서울","성동","성동S/S 154kV #66 BUS","154kV 성동-왕십리E/C SW 증설공사","O 170kV GIS 50kA 2000A x 2CCT(성동 및 왕십리 각 1CCT) O 송전선로 보호배전반(단거리송전방식, 재폐로 제외) O 기타 부대설비","2019-06-22 09:00","2019-06-26 18:00","2019-06-22 09:00","2019-06-26 18:00","연속"]
[7,"서울","성동","성동S/S 154kV #61 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-06-28 15:30","2019-06-28 17:30","2019-06-28 15:30","2019-06-28 17:30","연속"]
[8,"서울","성동","성동S/S 154kV #65 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-06-21 15:30","2019-06-21 17:30","2019-06-21 15:30","2019-06-21 17:30","연속"]
[9,"서울","성동","성동왕십리 T/L","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-06-18 09:00","2019-06-19 17:30","2019-06-18 09:00","2019-06-19 17:30","연속"]
[10,"서울","성동","성동S/S 154kV #60 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-06-25 15:30","2019-06-25 17:30","2019-06-25 15:30","2019-06-25 17:30","연속"]
[11,"서울","성동","왕십리용두 T/L","154kV 성동-왕십리E/C SW 증설공사","O 170kV GIS 50kA 2000A 2CCT O 송전선로 보호배전반 2면 O 기타 부대설비","2019-06-30 09:00","2019-07-01 18:00","2019-06-30 09:00","2019-07-01 18:00","연속"]
[12,"서울","성동","창동S/S 154kV #60-#65 BUS TIE GIS","19년 성동P/O 관내 154kV 차단기 조작시험","154kV GIS 조작시험 (차단기 개폐타임 측정)","2019-06-14 13:30","2019-06-14 16:00","2019-06-14 13:30","2019-06-14 16:00","당일"]
[13,"서울","성동","휘경S/S 154kV 휘경-종암#1T/L GIS","19년 성동P/O 장기사용 노후배전반 교체공사","휘경종암#1T/L 보호반 노후대체","2019-06-10 10:00","2019-06-13 17:00","2019-06-10 10:00","2019-06-13 17:00","연속"]
[14,"서울","성동","휘경S/S 154kV 휘경-종암#2T/L GIS","19년 성동P/O 장기사용 노후배전반 교체공사","휘경종암#2T/L 보호반 노후대체","2019-06-03 10:00","2019-06-07 17:00","2019-06-03 10:00","2019-06-07 17:00","연속"]
[15,"서울","중부","당인리목동#2 T/L","19년 중부전력지사 변전협력회사 총액공사","ㅇ당인리S/S 154kV 당인리목동#2T/L GIS 보통점검","2019-06-14 10:00","2019-06-14 18:00","2019-06-14 10:00","2019-06-14 18:00","당일"]
[16,"서울","중부","동빙고반포#2 T/L","2019년 중부P/O 170kV 정밀점검공사","ㅇ 154kV 동빙고반포#2T/L GIS 정밀점검","2019-06-03 09:00","2019-06-04 18:00","2019-06-03 09:00","2019-06-04 18:00","당일"]
[17,"서울","중부","중부용산#1 T/L","2019년 중부P/O 170kV GIS 정밀점검공사","2019년 중부P/O 170kV GIS 정밀점검공사","2019-06-11 17:00","2019-06-11 18:00","2019-06-11 17:00","2019-06-11 18:00","당일"]
[18,"서울","중부","중부당인리#2 T/L","19년 중부P/O 변전협력회사 총액공사","ㅇ 154kV 중부당인리#2T/L GIS 차단기 동작시험","2019-06-07 14:00","2019-06-07 18:00","2019-06-07 14:00","2019-06-07 18:00","당일"]
[19,"서울","중부","중부S/S 154kV #60-#65 BUS TIE GIS","19년 중부P/O 변전협력회사 총액공사","ㅇ 154kV #1BUSTIE GIS 차단기 동작시험","2019-06-04 10:00","2019-06-04 14:00","2019-06-04 10:00","2019-06-04 14:00","당일"]
[20,"서울","중부","중부당인리#1 T/L","19년 중부P/O 변전협력회사 총액공사","ㅇ 154kV 중부당인리#1T/L GIS 차단기 동작시험","2019-06-07 10:00","2019-06-07 14:00","2019-06-07 10:00","2019-06-07 14:00","당일"]
[21,"남서울","강남","논일역삼#1 T/L","논일-역삼#1T/L GIS 점검","역삼S/S 논일-역삼#1T/L GIS 개폐타임측정 논일S/S 논일-역삼#1T/L GIS 하자점검","2019-06-03 09:00","2019-06-03 18:00","2019-06-03 09:00","2019-06-03 18:00","당일"]
[22,"남서울","강남","논일역삼#2 T/L","논일-역삼#2T/L GIS 점검","역삼S/S 논일-역삼#2T/L GIS 개폐타임측정 논일S/S 논일-역삼#2T/L GIS 하자점검","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[23,"남서울","동서울","동서울S/S 154kV #65-#66 SEC CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-06-10 09:00","2019-06-10 18:00","2019-06-10 09:00","2019-06-10 18:00","당일"]
[24,"남서울","동서울","동서울S/S 154kV #2 T BUS TIE CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-06-03 09:00","2019-06-03 18:00","2019-06-03 09:00","2019-06-03 18:00","당일"]
[25,"남서울","동서울","동서울S/S 154kV #60-#65 BUS TIE CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-06-03 09:00","2019-06-03 18:00","2019-06-03 09:00","2019-06-03 18:00","당일"]
[26,"남서울","동서울","동서울가락#1 T/L","차단기 조작시험","동서울S/S 170kV GCB 초기점검 가락S/S 170kV GIS 보통점검","2019-06-12 09:00","2019-06-12 18:00","2019-06-12 09:00","2019-06-12 18:00","당일"]
[27,"남서울","동서울","동서울S/S 154kV #66-#67 SEC CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-06-11 09:00","2019-06-11 18:00","2019-06-11 09:00","2019-06-11 18:00","당일"]
[28,"남서울","동서울","동서울S/S 154kV #60-#61 SEC CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-06-07 09:00","2019-06-07 18:00","2019-06-07 09:00","2019-06-07 18:00","당일"]
[29,"남서울","동서울","동서울S/S 154kV #62-#67 BUS TIE CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-06-05 09:00","2019-06-05 18:00","2019-06-05 09:00","2019-06-05 18:00","당일"]
[30,"남서울","동서울","동서울S/S 154kV #61-#62 SEC CB","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[31,"남서울","동서울","수서S/S 154kV #1 BUS TIE CB","차단기 조작시험 및 전자변교체","수서S/S GIS 조작시험 및 전자변교체","2019-06-13 09:00","2019-06-13 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[32,"남서울","동서울","산성수서#2 T/L","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-06-28 14:00","2019-06-28 18:00","2019-06-28 14:00","2019-06-28 18:00","당일"]
[33,"남서울","동서울","산성수서#1 T/L","차단기 조작시험 및 전자변교체","차단기 조작시험 및 전자변교체","2019-06-28 09:00","2019-06-28 14:00","2019-06-28 09:00","2019-06-28 14:00","당일"]
[34,"남서울","동서울","신장덕소#2 T/L","신장S/S 170kV 장기사용 GIS 교체공사","신장S/S 170kV 장기사용 GIS 교체공사","2019-06-04 09:00","2019-06-30 18:00","2019-06-04 09:00","2019-06-30 18:00","연속"]
[35,"남서울","동서울","신장덕소#1 T/L","신장S/S 170kV 장기사용 GIS 교체공사(#2BUS 무부하가압)","신장S/S 170kV 장기사용 GIS 교체공사 - #2BUS 무부하가압 및 모선절체","2019-06-06 16:00","2019-06-07 09:00","2019-06-06 16:00","2019-06-07 09:00","연속"]
[36,"남서울","동서울","신장덕소#1 T/L","신장S/S 170kV 장기사용 GIS 교체공사(#1BUS 무부하가압)","신장S/S 170kV 장기사용 GIS 교체공사 - #1BUS 무부하가압 및 모선절체","2019-06-20 16:00","2019-06-21 09:00","2019-06-20 16:00","2019-06-21 09:00","연속"]
[37,"남서울","영등포","독산대방#2 T/L","독산-대방#2T/L GIS 조작시험(양단)","CB 동작시간측정","2019-06-24 13:00","2019-06-24 15:00","2019-06-24 13:00","2019-06-24 15:00","당일"]
[38,"남서울","영등포","독산대방#1 T/L","독산-대방#1T/L GIS 조작시험(양단)","CB 동작시간측정","2019-06-24 10:00","2019-06-24 12:00","2019-06-24 10:00","2019-06-24 12:00","당일"]
[39,"남서울","영등포","신정목동#1 T/L","목동S/S, 신정S/S 154kV GIS 정밀점검공사","-CB 동작시간 측정 -주회로 접촉저항 측정 -주회로, 보조회로, 제어회로 절연저항 측정 -SF6가스 수분 및 SO2 측정 -CT 포화시험 -경보시험 및 조작시험","2019-06-10 09:00","2019-06-13 18:00","2019-06-10 09:00","2019-06-13 18:00","연속"]
[40,"남서울","영등포","신정목동#2 T/L","목동S/S 154kV GIS 정밀점검공사","-CB 동작시간 측정 -주회로 접촉저항 측정 -주회로, 보조회로, 제어회로 절연저항 측정 -SF6가스 수분 및 SO2 측정 -CT 포화시험 -경보시험 및 조작시험","2019-06-27 09:00","2019-06-28 18:00","2019-06-27 09:00","2019-06-28 18:00","연속"]
[41,"남서울","영등포","신광명시흥#2 T/L","신광명-시흥#2T/L 154kV GIS 점검","신광명(초기점검) 시흥(조작시험)","2019-06-08 09:00","2019-06-08 18:00","2019-06-08 09:00","2019-06-08 18:00","당일"]
[42,"남서울","영등포","신광명광명#1 T/L","신광명-광명#1T/L 154kV GIS 초기점검","CB동작시간측정 SF6 수분 및 SO2측정 CT, 주회로 절연저항 측정 경보 및 조작시험","2019-06-15 09:00","2019-06-15 18:00","2019-06-15 09:00","2019-06-15 18:00","당일"]
[43,"남서울","영등포","신광명광명#2 T/L","2019-2020년 영등포전력지사 지중송전설비 위탁정비공사","PD 진단용 집합반 설치작업","2019-06-22 09:00","2019-06-22 18:00","2019-06-22 09:00","2019-06-22 18:00","당일"]
[44,"남서울","영등포","신광명시흥#1 T/L","신광명-시흥#1T/L 154kV GIS 점검","신광명(초기점검) 시흥(조작시험)","2019-06-01 09:00","2019-06-01 18:00","2019-06-01 09:00","2019-06-01 18:00","당일"]
[45,"남서울","영등포","온수소래 T/L","2019-2020년 영등포전력지사 지중송전설비 위탁정비공사","PD 진단용 집합반 설치작업","2019-06-11 09:00","2019-06-12 18:00","2019-06-11 09:00","2019-06-12 18:00","당일"]
[46,"남서울","영등포","중동화곡#2 T/L","154kV 중동화곡#1,2T/L EBA 자기애관교체공사","종단접속함(EBA) 절연파괴시 자기애관 폭발, 비산에 의한 2차 피해를 예방하고 선제적 노후 설비 보강을 통해 안정적 설비운영을 기하기 위함","2019-06-14 18:00","2019-06-17 09:00","2019-06-06 18:00","2019-06-09 09:00","연속"]
[47,"남서울","영등포","중동화곡#1 T/L","154kV 중동화곡#1,2T/L EBA 자기애관교체공사","종단접속함(EBA) 절연파괴시 자기애관 폭발, 비산에 의한 2차 피해를 예방하고 선제적 노후 설비 보강을 통해 안정적 설비운영을 기하기 위함","2019-06-21 18:00","2019-06-24 09:00","2019-06-23 18:00","2019-06-26 09:00","연속"]
[48,"남서울","직할","대림S/S 154kV #65 BUS","154kV 대림E/C GIS 설치공사","ㅇ 154kV GIS x 4CCT 설치 ㅇ 기타부대설비 1식 설치","2019-06-03 09:00","2019-06-14 18:00","2019-06-03 09:00","2019-06-14 18:00","연속"]
[49,"남서울","직할","양평양천#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험 차단기 전자변교체","2019-06-26 09:00","2019-06-26 18:00","2019-06-26 09:00","2019-06-26 18:00","당일"]
[50,"남서울","직할","양평양천#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험 차단기 전자변교체","2019-06-27 09:00","2019-06-27 18:00","2019-06-27 09:00","2019-06-27 18:00","당일"]
[51,"남서울","직할","영등포양평#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험 차단기 전자변교체","2019-06-28 09:00","2019-06-28 14:00","2019-06-28 09:00","2019-06-28 14:00","당일"]
[52,"남서울","직할","영등포양평#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험 차단기 전자변교체","2019-06-28 14:00","2019-06-28 18:00","2019-06-28 14:00","2019-06-28 18:00","당일"]
[53,"남서울","영등포","고강화곡#2 T/L","고강화곡#2 T/L 87 계전기 교체","고강화곡#2 T/L 87 계전기 교체","2019-06-02 09:00","2019-06-02 18:00","2019-06-02 09:00","2019-06-02 18:00","당일"]
[54,"인천","김포","경서양촌#1 T/L","154kV 경서-양촌 #1T/L 가공지선 교체공사","154kV 경서-양촌 #1T/L No.10~11 가공지선 교체공사","2019-06-23 08:00","2019-06-23 18:00","2019-06-23 08:00","2019-06-23 18:00","당일"]
[55,"인천","김포","김포S/S 154kV #1 BUS","154kV 계양-김포#1T/L 지장이설공사 준공시험","154kV 계양-김포#1T/L 지장이설공사 준공시험 - 상체크 등 시험. 끝.","2019-06-13 09:00","2019-06-13 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[56,"인천","김포","계양김포#2 T/L","검단신도시 송전선로 지중화공사-철탑 가이설","기설선로 No. 9~13호 가선작업, 연선, 긴선","2019-06-17 07:00","2019-06-22 18:00","2019-06-17 07:00","2019-06-22 18:00","연속"]
[57,"인천","김포","신김포양곡#1 T/L","양곡S/S 154kV 신김포-양곡#1 T/L GIS 조작시험","양곡S/S 154kV 신김포-양곡#1 T/L GIS 조작시험","2019-06-28 10:00","2019-06-28 18:00","2019-06-28 10:00","2019-06-28 18:00","당일"]
[58,"인천","김포","신김포양곡#2 T/L","양곡S/S 154kV 신김포-양곡#2 T/L GIS 조작시험","양곡S/S 154kV 신김포-양곡#2 T/L GIS 조작시험","2019-06-29 10:00","2019-06-29 18:00","2019-06-29 10:00","2019-06-29 18:00","당일"]
[59,"인천","김포","양촌양곡#1 T/L","154kV양촌양곡#1T/L 애자련보강","154kV양촌양곡#1T/L 가공송전선로 애자련보강","2019-06-24 08:00","2019-06-25 18:00","2019-06-24 08:00","2019-06-25 18:00","연속"]
[60,"인천","김포","양촌양곡#2 T/L","154kV양촌양곡#2T/L 애자련보강","154kV양촌양곡#2T/L 가공송전선로 애자련보강","2019-06-26 08:00","2019-06-27 18:00","2019-06-26 08:00","2019-06-27 18:00","연속"]
[61,"인천","김포","신경서왕길#2 T/L","154kV신경서왕길#2T/L 가공송전선로 정밀점검","154kV신경서왕길#2T/L 가공송전선로 정밀점검","2019-06-13 09:00","2019-06-14 18:00","2019-06-13 09:00","2019-06-14 18:00","연속"]
[62,"인천","시흥","신시흥남동#2 T/L","154kV 도림분기T/L C/H 가선공사","도림분기C/H 전력선 연결공사 - 구간 신시흥-오봉 No.26~27","2019-06-26 08:00","2019-06-27 18:00","2019-06-26 08:00","2019-06-27 18:00","연속"]
[63,"인천","시흥","신시흥남동#1 T/L","154kV 도림분기T/L C/H 가선공사","도림분기C/H 전력선 연결공사 - 구간 신시흥-오봉 No.26~27","2019-06-24 08:00","2019-06-25 18:00","2019-06-24 08:00","2019-06-25 18:00","연속"]
[64,"인천","시흥","도림S/S 154kV #65 BUS","154kV 도림분기 T/L 증설사업 초기가압","가. 상확인(신시흥-도림, 도림-오봉#1T/L) 나. 무부하가압 다. 원상복구조작","2019-06-28 14:00","2019-06-29 18:00","2019-06-28 14:00","2019-06-29 18:00","연속"]
[65,"인천","시흥","도림S/S 154kV #60 BUS","154kV 도림분기 SW 증설공사 인터록 시험 시행","가. 해당설비 : 신시흥도림#1, 도림오봉#1T/L 나. 시험내역 : 모선ES, 차단기간 인터록 확인 등 다. 기타사항 : 신부평-청천 초기가압 일정 중복에 따른 예비휴전으로 일정 변동 소지 발생있음. 끝.","2019-06-11 09:00","2019-06-11 14:00","2019-06-11 09:00","2019-06-11 14:00","당일"]
[66,"인천","시흥","도림S/S 154kV #65 BUS","154kV 도림분기 SW 증설공사 인터록 시험 시행","가. 해당설비 : 신시흥도림#1, 도림오봉#1T/L 나. 시험내역 : 모선ES, 차단기간 인터록 확인 등 다. 기타사항 : 신부평-청천 초기가압 일정 중복에 따른 예비휴전으로 일정 변동 소지 발생있음. 끝.","2019-06-11 14:00","2019-06-11 18:00","2019-06-11 14:00","2019-06-11 18:00","당일"]
[67,"인천","시흥","도림S/S 154kV #60 BUS","154kV 도림분기 T/L 증설사업 초기가압","가. 상확인(신시흥-도림, 도림-오봉#1T/L) 나. 무부하가압 다. 원상복구조작","2019-06-28 09:00","2019-06-28 14:00","2019-06-28 09:00","2019-06-28 14:00","연속"]
[68,"인천","시흥","북시화서시화#3 T/L","북시화S/S #5M.Tr 1차 GIS 정밀점검(무부하용)","북시화S/S #5M.Tr 1차 GIS 정밀점검(무부하용)","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[69,"인천","시흥","북시화S/S 154kV #60 BUS","북시화S/S #5M.Tr 1차 GIS 정밀점검(무부하용)","북시화S/S #5M.Tr 1차 GIS 정밀점검(무부하용)","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[70,"인천","시흥","신시흥#1S/S 154kV #60 BUS","154kV 도림분기 T/L 증설사업 초기가압","가. 상확인(신시흥-도림#1T/L) 나. 무부하가압(24시간) 다. 원상복구조작","2019-06-28 09:00","2019-06-29 18:00","2019-06-28 09:00","2019-06-29 18:00","연속"]
[71,"인천","시흥","신시흥시화#2 T/L","신시흥S/S 신시흥시화#2T/L 동작점검","신시흥S/S 신시흥시화#2T/L 동작점검","2019-06-14 14:00","2019-06-14 18:00","2019-06-14 14:00","2019-06-14 18:00","당일"]
[72,"인천","시흥","신시흥시화#1 T/L","신시흥S/S 신시흥시화#1T/L 동작점검","신시흥S/S 신시흥시화#1T/L 동작점검","2019-06-14 09:00","2019-06-14 14:00","2019-06-14 09:00","2019-06-14 14:00","당일"]
[73,"인천","시흥","신시흥#2S/S 154kV #63 BUS","신시흥#2S/S 170kV #65 Sh.C GIS 정밀점검(무부하용)","신시흥#2S/S 170kV #65 Sh.C GIS 정밀점검(무부하용)","2019-06-18 09:00","2019-06-18 18:00","2019-06-18 09:00","2019-06-18 18:00","당일"]
[74,"인천","시흥","신시흥#2S/S 154kV #63 BUS","신시흥#2S/S 170kV #63-#68 BUSTIE 정밀점검(무부하)","신시흥#2S/S 170kV #63-#68 BUSTIE 정밀점검(무부하)","2019-06-13 09:00","2019-06-13 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[75,"인천","시흥","신시흥북시화#1 T/L","신시흥#2S/S 170kV #63-#68 BUSTIE 정밀점검(무부하)","신시흥#2S/S 170kV #63-#68 BUSTIE 정밀점검(무부하)","2019-06-13 09:00","2019-06-13 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[76,"인천","시흥","신시흥#2S/S 154kV #63-#68 BUS TIE GIS","신시흥#2S/S 170kV #63-#68 BUSTIE GIS 정밀점검","신시흥#2S/S 170kV #63-#68 BUSTIE GIS 정밀점검","2019-06-12 09:00","2019-06-13 18:00","2019-06-12 09:00","2019-06-13 18:00","연속"]
[77,"인천","시흥","신시흥북시화#1 T/L","신시흥#2S/S 170kV #65 Sh.C GIS 정밀점검(무부하용)","신시흥#2S/S 170kV #65 Sh.C GIS 정밀점검(무부하용)","2019-06-18 09:00","2019-06-18 18:00","2019-06-18 09:00","2019-06-18 18:00","당일"]
[78,"인천","시흥","오봉S/S 154kV #60 BUS","154kV 도림분기 T/L 증설사업 최초가압","T/L 상확인용 모선 교번 휴전 시행 - 신시흥도림#1T/L, 도림오봉#1T/L","2019-06-28 09:00","2019-06-29 18:00","2019-06-28 09:00","2019-06-29 18:00","연속"]
[79,"인천","시흥","신시흥오봉 T/L","154kV 도림S/S 가공분기 및 보호반 대체공사","가. 신시흥 오봉 송전선로 보호반 대체작업(6/19 ~ 6/27) 나. 신시흥-도림, 도림-오봉 가공분기 작업(6/24 ~ 6/27) 다. 최초가압(신시흥-도림, 도림-오봉#1T/L)","2019-06-19 09:00","2019-06-29 18:00","2019-06-19 09:00","2019-06-29 18:00","연속"]
[80,"인천","시흥","오봉남동#2 T/L","154kV 도림분기 T/L 증설 초기가압","가. 신시흥도림, 도림오봉#1T/L 상확인 시험 나. 신시흥도림, 도림오봉#1T/L 무부하 가압 다. 원상복구 조작","2019-06-28 09:00","2019-06-29 18:00","2019-06-28 09:00","2019-06-29 18:00","연속"]
[81,"인천","인천","관교만수 T/L","154kV 만수S/S S.W 증설공사","- 154kV GIS(5CCT) 설치","2019-06-22 09:00","2019-06-22 10:00","2019-06-22 09:00","2019-06-22 10:00","당일"]
[82,"인천","인천","신가좌주안#1 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","신가좌S/S 신가좌주안#1T/L GIS 정밀점검 - 170㎸ GIS 정밀점검 × 1Bay - 기타작업 × 1식","2019-06-17 09:00","2019-06-19 18:00","2019-06-17 09:00","2019-06-19 18:00","연속"]
[83,"인천","인천","신가좌주안#2 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","신가좌S/S 신가좌주안#2T/L GIS 정밀점검 - 170㎸ GIS 정밀점검 × 1Bay - 기타작업 × 1식","2019-06-20 09:00","2019-06-22 18:00","취소","취소","연속"]
[84,"인천","인천","신경서S/S 154kV #66 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압","신경서S/S 신경서청라#2T/L GIS 정밀점검 관련 무부하가압","2019-06-01 12:00","2019-06-01 18:00","2019-06-01 12:00","2019-06-01 18:00","당일"]
[85,"인천","인천","신경서경서#2 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 관련 무부하가압","신경서S/S 신경서청라#2T/L GIS 정밀점검 관련 무부하가압","2019-06-01 12:00","2019-06-01 18:00","2019-06-01 12:00","2019-06-01 18:00","당일"]
[86,"인천","인천","영종경서 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","영종S/S 영종경서 T/L GIS 정밀점검 - 170㎸ GIS 정밀점검 × 1Bay - 기타작업 × 1식","2019-06-03 09:00","2019-06-05 18:00","2019-06-03 09:00","2019-06-05 18:00","연속"]
[87,"인천","인천","영종S/S 154kV #65 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","영종S/S #2M.Tr 1차 GIS 정밀점검 관련 무부하가압용","2019-06-12 13:00","2019-06-12 18:00","2019-06-12 13:00","2019-06-12 18:00","당일"]
[88,"인천","인천","영종경서 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","영종S/S 154kV BUS TIE GIS 정밀점검 관련 무부하가압용","2019-06-14 13:00","2019-06-14 18:00","2019-06-14 13:00","2019-06-14 18:00","당일"]
[89,"인천","인천","영종S/S 154kV #65 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","영종S/S 154kV BUS TIE GIS 정밀점검 관련 무부하가압용","2019-06-14 13:00","2019-06-14 18:00","2019-06-14 13:00","2019-06-14 18:00","당일"]
[90,"인천","인천","영종경서 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","영종S/S #2M.Tr 1차 GIS 정밀점검 관련 무부하가압용","2019-06-12 13:00","2019-06-12 18:00","2019-06-12 13:00","2019-06-12 18:00","당일"]
[91,"인천","인천","영종경서 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","영종S/S #1M.Tr 1차 GIS 정밀점검 관련 무부하가압용","2019-06-08 13:00","2019-06-08 18:00","2019-06-08 13:00","2019-06-08 18:00","당일"]
[92,"인천","인천","영종S/S 154kV #60 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","영종S/S #1M.Tr 1차 GIS 정밀점검 관련 무부하가압용","2019-06-08 13:00","2019-06-08 18:00","2019-06-08 13:00","2019-06-08 18:00","당일"]
[93,"인천","인천","북인천원창 T/L","154kV 북인천-원창T/L 조립식접속함 교체공사","일진전기 R-Type 조립식접속함(PMJ) 교체","2019-06-04 09:00","2019-06-10 18:00","2019-06-04 09:00","2019-06-10 18:00","연속"]
[94,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사(화곡2,#1M.Tr,중동#2)","중동화곡#2t/L,#1M.Tr,신부평중동#2T/L 상체크 및 무부하가압","2019-06-04 11:00","2019-06-05 15:00","2019-06-04 11:00","2019-06-05 15:00","당일"]
[95,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사(화곡1,2M.Tr,부천하수2)","중동S/S 170kV 인출GIS 정비공사(화곡#1,#2M.Tr,부천하수#2)","2019-06-10 09:00","2019-06-12 14:00","2019-06-10 09:00","2019-06-12 14:00","연속"]
[96,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사(중동#3,부천하수#1)","중동S/S 170kV 인출GIS 정비공사(중동#3,부천하수#1)","2019-06-25 14:00","2019-06-27 18:00","2019-06-25 14:00","2019-06-27 18:00","연속"]
[97,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사(화곡2,#1M.Tr,중동#2)","중동화곡#2t/L,#1M.Tr,신부평중동#2T/L 상체크 및 무부하가압","2019-06-04 09:00","2019-06-04 11:00","2019-06-04 09:00","2019-06-04 11:00","당일"]
[98,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사(중동#3,부천하수#1)","중동S/S 170kV 인출GIS 정비공사(중동#3,부천하수#1)","2019-06-24 09:00","2019-06-25 14:00","2019-06-24 09:00","2019-06-25 14:00","연속"]
[99,"인천","직할","중동S/S 154kV 신부평-중동#3T/L GIS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 - 신부평-중동#3T/L","2019-06-24 09:00","2019-07-03 18:00","2019-06-24 09:00","2019-07-03 18:00","연속"]
[100,"인천","직할","중동S/S 154kV #66 BUS","중동S/S 170kV 인출GIS 정비공사(화곡1,2M.Tr,부천하수2)","화곡#1,#2M.Tr,부천하수#2 GIS 상체크 시험 및 무부하조작","2019-06-21 11:00","2019-06-22 15:00","2019-06-21 11:00","2019-06-22 15:00","연속"]
[101,"인천","직할","중동S/S 154kV #65 BUS","중동S/S 170kV 인출GIS 정비공사(화곡1,2M.Tr,부천하수2)","화곡#1,#2M.Tr,부천하수#2 GIS 상체크 시험 및 무부하조작","2019-06-21 11:00","2019-06-22 15:00","2019-06-21 11:00","2019-06-22 15:00","연속"]
[102,"인천","직할","중동S/S 154kV #61 BUS","중동S/S 170kV 인출GIS 정비공사(화곡1,2M.Tr,부천하수2)","화곡#1,#2M.Tr,부천하수#2 GIS 상체크 시험 및 무부하조작","2019-06-21 09:00","2019-06-21 11:00","2019-06-21 09:00","2019-06-21 11:00","연속"]
[103,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사(화곡1,2M.Tr,부천하수2)","화곡#1,#2M.Tr,부천하수#2 GIS 상체크 시험 및 무부하조작","2019-06-21 09:00","2019-06-21 11:00","2019-06-21 09:00","2019-06-21 11:00","연속"]
[104,"인천","직할","중동S/S 154kV #60 BUS","중동S/S 170kV 인출GIS 정비공사(화곡1,2M.Tr,부천하수2)","중동S/S 170kV 인출GIS 정비공사(화곡#1,#2M.Tr,부천하수#2)","2019-06-12 14:00","2019-06-14 18:00","2019-06-12 14:00","2019-06-14 18:00","연속"]
[105,"인천","직할","중동S/S 154kV 중동-화곡#1T/L GIS","중동S/S 170kV 인출GIS 정비공사","중동S/S 170kV 인출GIS 정비공사 - 중동-화곡#1T/L GIS","2019-06-10 09:00","2019-06-22 18:00","2019-06-10 09:00","2019-06-22 18:00","연속"]
[106,"경기북부","고양","양주불광#1 T/L","154kV 지축E/C 옥내화 사업","154kV 지축E/C 건설 및 불광S/S 철거","2019-06-03 09:00","2019-06-18 18:00","2019-06-03 09:00","2019-06-18 18:00","연속"]
[107,"경기북부","고양","불광서대문#2 T/L","154kV 지축E/C 옥내화 사업","154kV 지축E/C 옥내화 및 불광S/S 철거","2019-06-03 09:00","2019-06-18 18:00","2019-06-03 09:00","2019-06-18 18:00","연속"]
[108,"경기북부","고양","신파주S/S 154kV #61-#66 BUS TIE GIS","2019년 고양P/O 변전정비회사 총액공사(신파주S/S #6200BT)","신파주S/S #6200BT GIS 보통점검","2019-06-07 09:30","2019-06-07 18:00","2019-06-07 09:30","2019-06-07 18:00","당일"]
[109,"경기북부","고양","신파주S/S 154kV #65-#66 SEC GIS","2019년 고양P/O 변전정비회사 총액공사(신파주S/S #65-#66)","신파주S/S #65-#66SEC GIS 보통점검","2019-06-04 09:30","2019-06-04 18:00","2019-06-04 09:30","2019-06-04 18:00","당일"]
[110,"경기북부","고양","신파주S/S 154kV #60-#65 BUS TIE GIS","2019년 고양P/O 변전정비회사 총액공사(신파주S/S #6100BT)","신파주S/S #6100BT GIS 보통점검","2019-06-05 09:30","2019-06-05 18:00","2019-06-05 09:30","2019-06-05 18:00","당일"]
[111,"경기북부","고양","신파주S/S 154kV #60-#61 SEC GIS","2019년 고양P/O 변전정비회사 총액공사(신파주S/S #60-#61)","신파주S/S #60-#61SEC GIS 보통점검","2019-06-03 09:30","2019-06-03 18:00","2019-06-03 09:30","2019-06-03 18:00","당일"]
[112,"경기북부","고양","신덕은원흥#2 T/L","154kV 신덕은-원흥#2T/L No.14 지장철탑 이설공사","서울문산고속도로 건설공사 관련 지장철탑 이설공사 ㅇ 작업구간 : 154kV 신덕은-원흥#2T/L No.13~15 ㅇ 철탑교체 : 154kV 신덕은-원흥#2T/L No.14","2019-06-01 06:00","2019-06-04 18:00","2019-06-01 06:00","2019-06-04 18:00","연속"]
[113,"경기북부","고양","신덕은원흥#1 T/L","154kV 신덕은-원흥#1T/L No.14 지장철탑 이설공사","서울문산고속도로 건설공사 관련 지장철탑 이설공사 ㅇ 작업구간 : 154kV 신덕은-원흥#1T/L No.13~15 ㅇ 철탑교체 : 154kV 신덕은-원흥#1T/L No.14","2019-06-01 06:00","2019-06-04 18:00","2019-06-01 06:00","2019-06-04 18:00","연속"]
[114,"경기북부","구리","덕소마석#2 T/L","154kV 덕소-마석#2T/L 노후취약금구 교체공사","ㅇ 노후취약금구 교체 - 대상 : No.22호 상,중,하단","2019-06-05 07:00","2019-06-05 18:00","2019-06-05 07:00","2019-06-05 18:00","당일"]
[115,"경기북부","구리","마석청평HP#2 T/L","154kV 덕소S/S 옥내화 사업 최초가압","덕소S/S 옥내화 최초가압 선로 휴전신청","2019-06-26 09:00","2019-06-27 18:00","2019-06-26 09:00","2019-06-27 18:00","연속"]
[116,"경기북부","구리","미금덕소#2 T/L","154kV 미금-덕소#2T/L 송전선로 정밀점검","- 미금S/S ~ 덕소S/S 철탑 15기 송전선로 정밀점검","2019-06-04 08:30","2019-06-04 18:00","2019-06-04 08:30","2019-06-04 18:00","당일"]
[117,"경기북부","구리","미금덕소#1 T/L","154kV 미금-덕소#2T/L 송전선로 정밀점검","- 미금S/S ~ 덕소S/S 철탑 15기 송전선로 정밀점검","2019-06-03 08:30","2019-06-03 18:00","2019-06-03 08:30","2019-06-03 18:00","당일"]
[118,"경기북부","구리","별내진접 T/L","154kV 별내-진접T/L 불량애자교체공사","ㅇ 불량애자교체 - 대상 : No.21호 상단전원","2019-06-03 07:00","2019-06-03 12:00","2019-06-03 07:00","2019-06-03 12:00","당일"]
[119,"경기북부","구리","신포천포천#2 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 포천-운천#2T/L 정밀점검 상단병가선로","2019-06-12 08:00","2019-06-12 18:00","2019-06-12 08:00","2019-06-12 18:00","연속"]
[120,"경기북부","구리","신포천포천#1 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 포천-운천#1T/L 정밀점검 상단병가선로","2019-06-04 08:00","2019-06-04 18:00","2019-06-04 08:00","2019-06-04 18:00","연속"]
[121,"경기북부","구리","운천전곡#2 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 포천-운천#1T/L 정밀점검 하단병가선로","2019-06-11 08:00","2019-06-11 18:00","2019-06-11 08:00","2019-06-11 18:00","당일"]
[122,"경기북부","구리","운천전곡#1 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 포천-운천#2T/L 정밀점검 하단병가선로","2019-06-18 08:00","2019-06-18 18:00","2019-06-18 08:00","2019-06-18 18:00","당일"]
[123,"경기북부","구리","진건별내#2 T/L","154kV 덕소S/S 옥내화 사업 최초가압","덕소S/S 옥내화 최초가압 선로 휴전신청","2019-06-26 09:00","2019-06-27 18:00","2019-06-26 09:00","2019-06-27 18:00","연속"]
[124,"경기북부","구리","서홍천청평PP T/L","청평P/P 서홍천-청평P/P 과열개소 보수","청평P/P 서홍천-청평P/P 과열개소 (인출부싱단자) 보수","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[125,"경기북부","구리","팔당H/P 154kV #1 M.Tr 1차 CB","팔당H/P 154kV #1M.Tr 1차 GIS 보통점검공사","팔당H/P 154kV #1M.Tr 1차 GIS 보통점검공사","2019-06-17 09:20","2019-06-17 18:00","2019-06-17 09:20","2019-06-17 18:00","당일"]
[126,"경기북부","구리","포천운천#2 T/L","2019년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2019-06-12 08:00","2019-06-18 18:00","2019-06-12 08:00","2019-06-18 18:00","연속"]
[127,"경기북부","구리","포천운천#1 T/L","2019년 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2019-06-04 08:00","2019-06-11 18:00","2019-06-04 08:00","2019-06-11 18:00","연속"]
[128,"경기북부","직할","양주은평#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주은평#2 T/L 인출선 전력구공사","2019-06-21 09:00","2019-06-21 18:00","2019-06-21 09:00","2019-06-21 18:00","연속"]
[129,"경기북부","직할","양주고양#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주고양#1T/L 인출선 전력구공사","2019-06-10 09:00","2019-06-11 18:00","2019-06-10 09:00","2019-06-11 18:00","연속"]
[130,"경기북부","직할","양주고양#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주고양#2T/L 인출선 전력구공사","2019-06-07 09:00","2019-06-08 18:00","2019-06-07 09:00","2019-06-08 18:00","연속"]
[131,"경기북부","직할","양주은평#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주은평#1T/L 인출선 전력구공사","2019-06-20 09:00","2019-06-20 18:00","2019-06-20 09:00","2019-06-20 18:00","연속"]
[132,"경기북부","직할","양주금촌#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주금촌#2T/L 인출선 관련 전력구공사","2019-06-03 09:00","2019-06-04 18:00","2019-06-03 09:00","2019-06-04 18:00","연속"]
[133,"경기북부","직할","양주금촌#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주금촌#1T/L 인출선 전력구공사","2019-06-05 09:00","2019-06-06 18:00","2019-06-05 09:00","2019-06-06 18:00","연속"]
[134,"경기북부","직할","양주녹양#1 T/L","18~19 직할 변전정비회사 총액공사","양주-녹양 #1 T/L CVT, LA 점검","2019-06-05 09:00","2019-06-05 18:00","2019-06-09 09:00","2019-06-09 18:00","당일"]
[135,"경기북부","직할","양주불광#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주불광#2 T/L 인출선 전력구공사","2019-06-19 09:00","2019-06-19 18:00","2019-06-19 09:00","2019-06-19 18:00","연속"]
[136,"경기북부","호수","호수S/S 154kV 일산-호수#1T/L GIS","2019년 고양P/O 변전정비회사 총액공사(일산-호수#1T/L)","154kV 일산-호수#1T/L GIS 보통점검","2019-06-17 10:00","2019-06-17 18:00","2019-06-17 10:00","2019-06-17 18:00","당일"]
[137,"경기북부","호수","호수S/S 154kV 일산-호수#2T/L GIS","2019년 고양P/O 변전정비회사 총액공사(일산-호수#2T/L)","154kV 일산-호수#2T/L GIS 보통점검","2019-06-18 10:00","2019-06-18 18:00","2019-06-18 10:00","2019-06-18 18:00","당일"]
[138,"경기북부","직할","양주S/S 154kV #66 BUS","154kV 지축E/C 옥내화 사업","154kV 지축E/C 건설-무부하 가압","2019-06-17 09:00","2019-06-18 18:00","2019-06-17 09:00","2019-06-18 18:00","연속"]
[139,"경기","군포","관양평촌#2 T/L","'19년 군포P/O 변전정비회사 총액공사","관양S/S 관양-평촌#2T/L CB 보통점검 평촌S/S 관양-평촌#2T/L CB 조작시험","2019-06-27 14:00","2019-06-27 18:00","2019-06-27 14:00","2019-06-27 18:00","당일"]
[140,"경기","군포","관양평촌#1 T/L","'19년 군포P/O 변전정비회사 총액공사","관양S/S 관양-평촌#1T/L GIS 보통점검 평촌S/S 관양-평촌#1T/L GIS 조작시험","2019-06-27 09:00","2019-06-27 14:00","2019-06-27 09:00","2019-06-27 14:00","당일"]
[141,"경기","군포","마도사강#2 T/L","사강S/S 마도-사강#2T/L GIS 조작시험","사강S/S 마도-사강#2T/L GIS 조작시험 마도S/S 마도-사강#2T/L GIS 조작시험","2019-06-25 09:00","2019-06-25 18:00","2019-06-25 09:00","2019-06-25 18:00","당일"]
[142,"경기","군포","사강남양#1 T/L","사강S/S 사강-남양#1T/L GIS 조작시험","사강S/S 사강-남양#1T/L GIS 조작시험","2019-06-26 09:00","2019-06-26 14:00","2019-06-26 09:00","2019-06-26 14:00","당일"]
[143,"경기","군포","사강남양#2 T/L","사강S/S 사강-남양#2T/L GIS 조작시험","사강S/S 사강-남양#2T/L GIS 조작시험","2019-06-26 14:00","2019-06-26 18:00","2019-06-26 14:00","2019-06-26 18:00","당일"]
[144,"경기","군포","서서울#2남수원 #2T/L","154kV 서서울2-남수원T/L 40,42호 안전이격확보공사","-철탑신설 2기, 철거 1기, 전선교체 : 1.039km(6가닥), 피뢰기 설치 : 1~70호","2019-06-05 07:00","2019-06-14 18:00","2019-06-05 07:00","2019-06-14 18:00","연속"]
[145,"경기","군포","서서울#2남수원 #1T/L","154kV 봉담E/C 건설공사","- 남수원-봉담T/L 가선작업 및 보호배전반 대체","2019-06-17 09:00","2019-07-03 18:00","취소","취소","연속"]
[146,"경기","군포","서서울#2남수원 #1T/L","154kV 서서울2-남수원T/L 40,42호 안전이격확보공사","-철탑신설 2기, 철거 1기, 전선교체 : 1.039km(6가닥)","2019-06-03 07:00","2019-06-04 18:00","2019-06-03 07:00","2019-06-04 18:00","연속"]
[147,"경기","군포","서서울#2남수원 #1T/L","154kV 서서울2-남수원T/L 40,42호 안전이격확보공사","-철탑신설 2기, 철거 1기, 전선교체 : 1.039km(6가닥)","2019-06-15 07:00","2019-06-21 18:00","2019-06-15 07:00","2019-06-21 18:00","연속"]
[148,"경기","군포","서서울율전#2 T/L","율전분기T/L 비규격EBA(종단접속함) 자기애관 교체공사","154kV 서서울-율전#2T/L 율전#1C/H 자기애관 교체작업","2019-06-17 09:00","2019-06-21 18:00","2019-06-17 09:00","2019-06-21 18:00","연속"]
[149,"경기","군포","서서울율전#1 T/L","율전분기T/L 비규격EBA(종단접속함) 자기애관 교체공사","154kV 서서울-율전#1T/L 율전#1C/H 자기애관 교체작업","2019-06-10 09:00","2019-06-14 18:00","2019-06-10 09:00","2019-06-14 18:00","연속"]
[150,"경기","군포","서서울산본#2 T/L","'19년 군포P/O 변전정비회사 총액공사","- 서서울변전소 657 GIS 초기점검, LA,PT 보통 및 산본변전소 667 GIS 조작시험","2019-06-28 14:00","2019-06-28 18:00","2019-06-28 14:00","2019-06-28 18:00","당일"]
[151,"경기","군포","서안양S/S 154kV 삼천리#2T/L GIS","2019년 군포 154kV GIS정밀점검 공사 - 삼천리#2TL","2019년 군포 154kV GIS정밀점검 공사 - 삼천리 #2T/L GIS 정밀점검","2019-06-06 08:00","2019-06-09 20:00","2019-06-06 08:00","2019-06-09 20:00","연속"]
[152,"경기","군포","서안양S/S 154kV 삼천리#1T/L GIS","2019년 군포 154kV GIS정밀점검 공사 - 삼천리#1TL","2019년 군포 154kV GIS정밀점검 공사 - 삼천리 #1T/L GIS 정밀점검","2019-06-03 08:00","2019-06-05 20:00","2019-06-03 08:00","2019-06-05 20:00","연속"]
[153,"경기","군포","안양S/S 154kV 안양-평촌#2T/L GIS","안양S/S 안양-평촌#2T/L GIS 하자점검","안양 : 하자점검 평촌 : 조작시험","2019-06-28 09:00","2019-06-28 14:00","2019-06-28 09:00","2019-06-28 14:00","당일"]
[154,"경기","군포","서서울#2일동 #1T/L","2018-19년도 송전정비회사 총액공사","- 11호 154kV 일동-원곡#1T/L 애자장치 교체 관련 안전이격거리확보","2019-06-24 07:00","2019-06-24 18:00","2019-06-24 07:00","2019-06-24 18:00","당일"]
[155,"경기","군포","서서울#2일동 #2T/L","2018-19년도 송전정비회사 총액공사","- 1~11호간 154kV 일동-원곡#1T/L 피뢰기 설치 관련 안전이격거리확보","2019-06-21 07:00","2019-06-22 18:00","2019-06-21 07:00","2019-06-22 18:00","당일"]
[156,"경기","군포","성곡중시화 T/L","2019년 군포 154kV GIS정밀점검 공사 - 중시화 6100","2019년 군포 154kV GIS정밀점검 공사 - 6100 GIS 무부하가압용","2019-06-17 08:00","2019-06-19 20:00","2019-06-17 08:00","2019-06-19 20:00","연속"]
[157,"경기","군포","평촌S/S 154kV 안양-평촌#1T/L GIS","2019년 군포 154kV GIS정밀점검 공사 - 안양-평촌1TL","2019년 군포 154kV GIS정밀점검 공사 - 안양S/S 안양-평촌 #1T/L GIS 정밀점검 - 평촌S/S 안양-평촌 #1T/L GIS 하자점검","2019-06-24 08:00","2019-06-26 20:00","2019-06-24 08:00","2019-06-26 20:00","매일"]
[158,"경기","동부","곤지암이천#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-06-03 08:30","2019-06-05 17:30","2019-06-03 08:30","2019-06-05 17:30","연속"]
[159,"경기","동부","곤지암율현#2 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-06-03 08:30","2019-06-05 17:30","2019-06-03 08:30","2019-06-05 17:30","연속"]
[160,"경기","동부","곤지암이천#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-06-06 08:30","2019-06-08 17:30","2019-06-06 08:30","2019-06-08 17:30","연속"]
[161,"경기","동부","곤지암S/S 154kV 곤지암-초월#1T/L GIS","19년 동부변전협력회사 총액공사","초월:곤지암-초월#1T/L GIS(보통) 43L/R 회로보완 확인 및 Remote 회로분리 시행, 보호반대체(~12)","2019-06-10 09:00","2019-06-12 18:00","2019-06-24 09:00","2019-06-26 18:00","연속"]
[162,"경기","동부","곤지암율현#1 T/L","345kV 곤지암S/S #4M.Tr 증설공사","곤지암S/S 170kV GIS 증설 및 이설관련 크레인 안전거리 이격","2019-06-06 08:30","2019-06-08 17:30","2019-06-06 08:30","2019-06-08 17:30","연속"]
[163,"경기","동부","곤지암S/S 154kV 곤지암-초월#2T/L GIS","19년 동부변전협력회사 총액공사","초월:곤지암-초월#2T/L GIS(개폐타임) 43L/R 회로보완 확인 및 Remote 회로분리 시행, 보호반대체(~15)","2019-06-13 09:00","2019-06-15 18:00","2019-06-27 09:00","2019-06-29 18:00","연속"]
[164,"경기","동부","분당S/S 154kV 성현-분당#1T/L GIS","19년 동부변전협력회사 총액공사","성현:성현-분당#1T/L 43L/R 회로보완 확인 및 Remote 회로분리 시행, 보호반대체(~22)","2019-06-19 09:00","2019-06-21 18:00","2019-06-19 09:00","2019-06-21 18:00","연속"]
[165,"경기","동부","분당S/S 154kV 분당-오포#1T/L GIS","19년 동부변전협력회사 총액공사","분당: 분당-오포#1T/L LA 대체","2019-06-17 09:00","2019-06-17 18:00","2019-06-17 09:00","2019-06-17 18:00","당일"]
[166,"경기","동부","분당S/S 154kV 분당-오포#2T/L GIS","19년 동부변전협력회사 총액공사","분당: 분당-오포#2T/L LA 대체","2019-06-18 09:00","2019-06-18 18:00","2019-06-18 09:00","2019-06-18 18:00","당일"]
[167,"경기","동부","분당S/S 154kV 성현-분당#2T/L GIS","19년 동부변전협력회사 총액공사","성현:성현-분당#2T/L 2DS 에어누기보수 43L/R 회로보완 확인 및 Remote 회로분리 시행, 보호반 대체 (~26)","2019-06-24 09:00","2019-06-26 18:00","2019-06-24 09:00","2019-06-26 18:00","연속"]
[168,"경기","동부","성현S/S 154kV #60-#65 BUS TIE GIS","19년 동부변전협력회사 총액공사","성현:6100 GIS(개폐타임),43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-06-05 09:00","2019-06-05 18:00","2019-06-05 09:00","2019-06-05 18:00","당일"]
[169,"경기","동부","이천가남#1 T/L","154kV 이천-가남#1T/L C/H 및 LA점검","지중송전설비 C/H및 LA점검","2019-06-17 09:00","2019-06-17 18:00","2019-06-22 09:00","2019-06-22 18:00","당일"]
[170,"경기","동부","이천가남#2 T/L","154kV 이천-가남#2T/L C/H 및 LA점검","지중송전설비 C/H및 LA점검","2019-06-18 09:00","2019-06-18 18:00","2019-06-23 09:00","2019-06-23 18:00","당일"]
[171,"경기","성남","154kV 삼미-동탄2열병합#1T/L GIS","차단기 카운터 불량 조치","차단기 카운터 불량 조치","2019-06-10 14:00","2019-06-10 18:00","2019-06-10 14:00","2019-06-10 18:00","당일"]
[172,"경기","성남","모현S/S 154kV 오포-모현#2T/L GIS","DC 접지해소","DC 접지해소","2019-06-27 14:00","2019-06-27 18:00","2019-06-27 14:00","2019-06-27 18:00","당일"]
[173,"경기","성남","모현S/S 154kV 오포-모현#1T/L GIS","DC 접지해소","DC 접지해소","2019-06-27 09:00","2019-06-27 14:00","2019-06-27 09:00","2019-06-27 14:00","당일"]
[174,"경기","성남","서안성S/S 154kV #61-#66 BUS TIE GIS","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-06-10 09:00","2019-06-12 18:00","2019-06-10 09:00","2019-06-12 18:00","연속"]
[175,"경기","성남","서안성S/S 154kV #61 BUS","170kV GIS 정밀점검 무부하","170kV GIS 정밀점검 무부하","2019-06-26 09:00","2019-06-26 18:00","2019-06-26 09:00","2019-06-26 18:00","당일"]
[176,"경기","성남","서안성S/S 154kV #60-#61 SEC GIS","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-06-24 09:00","2019-06-26 18:00","2019-06-24 09:00","2019-06-26 18:00","연속"]
[177,"경기","성남","서안성S/S 154kV 서안성-남사#2T/L GIS","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-06-19 14:00","2019-06-22 18:00","2019-06-19 14:00","2019-06-22 18:00","연속"]
[178,"경기","성남","서안성S/S 154kV #65 BUS","170kV GIS 정밀점검 무부하","170kV GIS 정밀점검 무부하","2019-06-28 09:00","2019-06-29 18:00","2019-06-28 09:00","2019-06-29 18:00","당일"]
[179,"경기","성남","서안성S/S 154kV #66 BUS","170kV GIS 정밀점검 무부하","170kV GIS 정밀점검 무부하","2019-06-28 09:00","2019-06-29 18:00","2019-06-28 09:00","2019-06-29 18:00","당일"]
[180,"경기","성남","서안성S/S 154kV #65-#66 SEC GIS","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-06-27 14:00","2019-06-29 18:00","2019-06-27 14:00","2019-06-29 18:00","연속"]
[181,"경기","성남","서안성S/S 154kV #60 BUS","170kV GIS 정밀점검 무부하","170kV GIS 정밀점검 무부하","2019-06-26 09:00","2019-06-26 18:00","2019-06-26 09:00","2019-06-26 18:00","당일"]
[182,"경기","성남","서안성S/S 154kV #65 BUS","170kV GIS 정밀점검 무부하","170kV GIS 정밀점검 무부하","2019-06-21 09:00","2019-06-22 18:00","2019-06-21 09:00","2019-06-22 18:00","당일"]
[183,"경기","성남","서안성S/S 154kV #60 BUS","170kV GIS 정밀점검 무부하","170kV GIS 정밀점검 무부하","2019-06-19 09:00","2019-06-19 18:00","2019-06-19 09:00","2019-06-19 18:00","당일"]
[184,"경기","성남","서안성S/S 154kV 서안성-남사#1T/L GIS","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-06-17 09:00","2019-06-19 18:00","2019-06-17 09:00","2019-06-19 18:00","연속"]
[185,"경기","성남","서안성S/S 154kV 서안성-남사#2T/L GIS","170kV GIS 정밀점검 무부하","170kV GIS 정밀점검 무부하","2019-06-14 09:00","2019-06-15 18:00","2019-06-14 09:00","2019-06-15 18:00","당일"]
[186,"경기","성남","서안성S/S 154kV #60-#65 BUS TIE GIS","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-06-12 14:00","2019-06-15 18:00","2019-06-12 14:00","2019-06-15 18:00","연속"]
[187,"경기","성남","서안성S/S 154kV 서안성-안성#2T/L GIS","170kV GIS 정밀점검 무부하","170kV GIS 정밀점검 무부하","2019-06-12 09:00","2019-06-12 18:00","2019-06-12 09:00","2019-06-12 18:00","당일"]
[188,"경기","성남","신갈수원열병합#1T/L","신갈S/S GIS 대체공사","신갈S/S GIS 대체공사","2019-06-03 09:00","2019-07-19 18:00","2019-06-03 09:00","2019-07-19 18:00","연속"]
[189,"경기","성남","신갈S/S 154kV #65 BUS","신갈S/S GIS 대체공사","신갈S/S GIS 대체공사","2019-06-11 09:00","2019-06-21 18:00","2019-06-11 09:00","2019-06-21 18:00","연속"]
[190,"경기","성남","신수원S/S 154kV #66-#67 SEC GIS","조작시험","조작시험","2019-06-27 09:00","2019-06-27 18:00","2019-06-27 09:00","2019-06-27 18:00","당일"]
[191,"경기","성남","신수원S/S 154kV 신수원-북동탄#2T/L GIS","신수원-북동탄#2T/L 조작시험","신수원-북동탄#2T/L 조작시험","2019-06-19 09:00","2019-06-19 18:00","2019-06-19 09:00","2019-06-19 18:00","당일"]
[192,"경기","성남","신수원S/S 154kV #65-#66 SEC GIS","조작시험","조작시험","2019-06-21 09:00","2019-06-21 14:00","2019-06-21 09:00","2019-06-21 14:00","당일"]
[193,"경기","성남","신수원S/S 154kV #61-#62 SEC GIS","조작시험","조작시험","2019-06-21 14:00","2019-06-21 18:00","2019-06-21 14:00","2019-06-21 18:00","당일"]
[194,"경기","성남","신수원S/S 154kV #61-#66 BUS-TIE GIS","조작시험","조작시험","2019-06-21 14:00","2019-06-21 18:00","2019-06-21 14:00","2019-06-21 18:00","당일"]
[195,"경기","성남","신용인용인#1 T/L","154kV 신용인-용인#1T/L 정밀점검","154kV 신용인-용인#1T/L(No.1-27) 송전선로 정밀점검","2019-06-03 08:00","2019-06-04 18:00","2019-06-03 08:00","2019-06-04 18:00","매일"]
[196,"경기","성남","신용인용인#2 T/L","154kV 신용인-용인#2T/L 정밀점검","154kV 신용인-용인#2T/L(No.1-27) 송전선로 정밀점검","2019-06-05 08:00","2019-06-07 18:00","2019-06-05 08:00","2019-06-07 18:00","매일"]
[197,"경기","성남","신용인S/S 154kV #61-#66 BUS TIE GIS","조작시험","조작시험","2019-06-12 14:00","2019-06-12 18:00","2019-06-12 14:00","2019-06-12 18:00","당일"]
[198,"경기","성남","신용인S/S 154kV #60-#65 BUS TIE GIS","조작시험","조작시험","2019-06-12 09:00","2019-06-12 14:00","2019-06-12 09:00","2019-06-12 14:00","당일"]
[199,"경기","직할","남수원발안#1 T/L","2018-19년도 송전정비회사 총액공사","-50~70호간 서서울2-남수원#2T/L 피뢰기 설치 관련 안전이격거리확보","2019-06-12 07:00","2019-06-14 18:00","2019-06-12 07:00","2019-06-14 18:00","당일"]
[200,"경기","직할","신수원동수원#1 T/L","154kV 동수원변전소 현대화공사","ㅇ154kV 신수원-동수원#1T/L 인출변경,전력케이블 교체, 보호배전반 교체","2019-06-14 09:00","2019-07-12 18:00","2019-06-14 09:00","2019-07-12 18:00","연속"]
[201,"경기","직할","의왕동안양#2 T/L","154kV 동안양S/S 인출T/L 정비공사","154kV 동안양S/S 옥내화 사업 관련 인출 T/L 정비공사 - 공사규모 : ACSR 410B×4C×0.05km, 보강 1기(No.1) - 공사내용 : 동안양S/S 구내 S/T 이설 및 인출 철탑 보강","2019-06-07 08:00","2019-06-14 18:00","2019-06-07 08:00","2019-06-14 18:00","연속"]
[202,"경기","직할","의왕동안양#2 T/L","154kV 동안양S/S 옥내화 부지확보 변전설비 이설공사","O. #60BUS 모선철거관련 안전이격거리 확보","2019-06-18 09:00","2019-06-21 18:00","2019-06-18 09:00","2019-06-21 18:00","연속"]
[203,"경기","직할","서서울서수원#2 T/L","서서울서수원#2T/L 170kV GIS 정밀점검 공사","서서울서수원#2T/L 170kV GIS 정밀점검","2019-06-03 09:00","2019-06-05 18:00","2019-06-03 09:00","2019-06-05 18:00","연속"]
[204,"경기","직할","율전의왕#2 T/L","의왕S/S 154kV 장기사용 GIS 교체공사","군포전철#2T/L GIS(647) 교체공사 (#1BUS 무부하 가압용)","2019-06-11 09:00","2019-06-12 09:00","2019-06-04 09:00","2019-06-05 09:00","연속"]
[205,"경기","직할","군포전철#2/L CB","의왕S/S 154kV 장기사용 GIS 교체공사","군포전철#2T/L GIS(647) 교체공사","2019-06-04 09:00","2019-07-05 18:00","2019-06-04 09:00","2019-07-05 18:00","연속"]
[206,"경기","직할","화성S/S 154kV #61-#66 BUS TIE GIS","19년 직할 변전협력회사 총액공사","화성S/S 154kV 6200 BUS TIE GIS 조작시험","2019-06-18 14:00","2019-06-18 18:00","2019-06-18 14:00","2019-06-18 18:00","당일"]
[207,"경기","직할","화성S/S 154kV #65-#66 SEC GIS","19년 직할 변전협력회사 총액공사","화성S/S 154kV 65-66 BUS SEC GIS 조작시험","2019-06-19 14:00","2019-06-19 18:00","2019-06-19 14:00","2019-06-19 18:00","당일"]
[208,"경기","직할","화성S/S 154kV #60-#61 SEC GIS","19년 직할 변전협력회사 총액공사","화성S/S 154kV 60-61 BUS SEC GIS 조작시험","2019-06-19 10:00","2019-06-19 14:00","2019-06-19 10:00","2019-06-19 14:00","당일"]
[209,"경기","직할","화성S/S 154kV #60-#65 BUS TIE GIS","19년 직할 변전협력회사 총액공사","화성S/S 154kV 6100 BUS TIE GIS 조작시험","2019-06-18 10:00","2019-06-18 14:00","2019-06-18 10:00","2019-06-18 14:00","당일"]
[210,"경기","평택","서운삼죽 T/L","2019년 가공송전선로 순시점검 위탁공사(충북 직할)","No.29~92 정밀점검","2019-06-03 09:00","2019-06-07 18:00","2019-06-03 09:00","2019-06-07 18:00","매일"]
[211,"경기","평택","안성S/S 154kV #65 BUS","안성S/S 170kV GIS 용량대체공사","송탄-안성T/L GIS 철거 및 설치","2019-06-18 16:00","2019-06-27 16:00","2019-06-18 16:00","2019-06-27 16:00","연속"]
[212,"경기","평택","안성S/S 154kV #60 BUS","안성S/S 170kV GIS 용량대체공사","송탄-안성T/L GIS 철거 및 설치","2019-06-11 16:00","2019-06-18 16:00","2019-06-11 16:00","2019-06-18 16:00","연속"]
[213,"경기","평택","송탄안성 T/L","안성S/S 170kV GIS 용량대체공사","송탄-안성T/L GIS 철거 및 설치","2019-06-10 08:00","2019-06-28 18:00","2019-06-10 08:00","2019-06-28 18:00","연속"]
[214,"경기","평택","안성S/S 154kV #65 BUS","안성S/S 170kV GIS 용량대체공사","송탄-안성T/L GIS 철거 및 설치","2019-06-10 08:00","2019-06-11 16:00","2019-06-10 08:00","2019-06-11 16:00","연속"]
[215,"경기","평택","안성S/S 154kV #60 BUS","안성S/S 170kV GIS 용량대체공사","소사벌-안성T/L GIS 철거 및 설치 #1M.Tr GIS 철거 및 설치 #60/65 PT 철거 및 설치공사","2019-06-06 14:00","2019-06-07 14:00","2019-06-06 14:00","2019-06-07 14:00","연속"]
[216,"경기","평택","안성S/S 154kV #60 BUS","안성S/S 170kV GIS 용량대체공사","송탄-안성T/L GIS 철거 및 설치","2019-06-27 16:00","2019-06-28 16:00","2019-06-27 16:00","2019-06-28 16:00","연속"]
[217,"경기","평택","오산향남#1 T/L","154kV 오산-향남T/L 전선접속개소 교체공사","- 154kV 오산-향남T/L No.5-9 및 No.18-19 전선접속개소 교체공사","2019-06-07 07:00","2019-06-11 18:00","2019-06-07 07:00","2019-06-11 18:00","연속"]
[218,"경기","평택","오산향남#2 T/L","154kV 오산-향남T/L 전선접속개소 교체공사","- 154kV 오산-향남T/L No.5-9 및 No.18-19 전선접속개소 교체공사","2019-06-12 07:00","2019-06-16 18:00","2019-06-12 07:00","2019-06-16 18:00","연속"]
[219,"경기","평택","원정평택T/P#2 T/L","원정S/S 154kV 원정-평택T/P#2 T/L GIS 조작시험","원정S/S 154kV 원정-평택T/P#2 T/L GIS 조작시험","2019-06-07 14:00","2019-06-07 18:00","2019-06-07 14:00","2019-06-07 18:00","당일"]
[220,"경기","평택","원정평택T/P#1 T/L","원정S/S 154kV 원정-평택T/P#1 T/L GIS 조작시험","원정S/S 154kV 원정-평택T/P#1 T/L GIS 조작시험","2019-06-07 10:00","2019-06-07 14:00","2019-06-07 10:00","2019-06-07 14:00","당일"]
[221,"경기","평택","청북평택#2 T/L","154kV 청북S/S #5M.Tr 증설용 GIS 설치공사","ㅇ #5M.TR증설설비 무부하 가압 - 170kV GIS, #5M.Tr, 25.8kV GIS, 전력케이블","2019-06-03 10:30","2019-06-04 18:00","2019-06-03 10:30","2019-06-04 18:00","연속"]
[222,"경기","평택","둔포추팔#1 T/L","추팔S/S 154kV 둔포-추팔#1 T/L GIS 보통점검","추팔S/S 154kV 둔포-추팔#1 T/L GIS 보통점검 / LA 보통점검","2019-06-13 10:00","2019-06-13 18:00","2019-06-13 10:00","2019-06-13 18:00","당일"]
[223,"경기","평택","둔포추팔#2 T/L","추팔S/S 154kV 둔포-추팔#2 T/L GIS 보통점검","추팔S/S 154kV 둔포-추팔#2 T/L GIS 보통점검 / LA 보통점검","2019-06-14 10:00","2019-06-14 18:00","2019-06-14 10:00","2019-06-14 18:00","당일"]
[224,"경기","평택","오산평택#2 T/L","154kV 오산평택T/L 고덕지구 임시이설공사(구간 60~71호)","평택고덕지구 조성관련 지장선로 임시이설공사 154kV 오산평택T/L 고덕지구 지장선로 임시이설(구간 60~71호)","2019-06-12 08:00","2019-06-16 18:00","2019-06-12 08:00","2019-06-16 18:00","연속"]
[225,"경기","평택","오산평택#2 T/L","154kV 오산평택T/L 임시이설공사 안전작업거리확보(60~71호)","고덕지구조성 지장선로 임시이설공사 4회선 안전작업거리 확보 154kV 오산평택T/L 고덕지구 지장선로 임시이설(구간 60~71호)","2019-06-05 08:00","2019-06-06 18:00","2019-06-05 08:00","2019-06-06 18:00","연속"]
[226,"경기","평택","오산평택#1 T/L","154kV 오산평택T/L 고덕지구 임시이설공사(구간 60~71호)","평택고덕지구 조성관련 지장선로 임시이설공사 154kV 오산평택T/L 고덕지구 지장선로 임시이설(구간 60~71호)","2019-06-05 08:00","2019-06-11 18:00","2019-06-05 08:00","2019-06-11 18:00","연속"]
[227,"경기","평택","오산평택#1 T/L","154kV 오산평택T/L 임시이설공사 안전작업거리확보(60~71호)","고덕지구조성 지장선로 임시이설공사 4회선 안전작업거리 확보 154kV 오산평택T/L 고덕지구 지장선로 임시이설(구간 60~71호)","2019-06-01 08:00","2019-06-02 18:00","2019-06-01 08:00","2019-06-02 18:00","연속"]
[228,"경기","평택","오산평택#2 T/L","154kV 오산평택T/L 고덕지구 임시이설공사(구간 60~71호)","평택고덕지구 조성관련 지장선로 임시이설공사 154kV 오산평택T/L 고덕지구 지장선로 임시이설(구간 60~71호)","2019-06-01 08:00","2019-06-04 18:00","2019-06-01 08:00","2019-06-04 18:00","연속"]
[229,"경기","평택","포승평택TP#2 T/L","포승S/S 154kV 포승-평택T/P#2T/L GIS 조작시험","포승S/S 154kV 포승-평택T/P#2T/L GIS 조작시험","2019-06-27 10:00","2019-06-27 18:00","2019-06-27 10:00","2019-06-27 18:00","당일"]
[230,"경기","직할","서서울#2남수원 #1T/L","154kV 봉담E/C 건설공사","- 남수원-봉담T/L 가선작업 및 보호배전반 대체","2019-06-17 09:00","2019-07-03 18:00","취소","취소","연속"]
[231,"경기","평택","고덕진위#2 T/L","고덕S/S 154kV SW신규수용공사","ㅇ 154kV #2BUS측 무부하 가압 - 고덕-프랙스에어#1,2T/L","2019-06-17 09:00","2019-06-18 18:00","2019-06-17 09:00","2019-06-18 18:00","연속"]
[232,"경기","평택","고덕진위#2 T/L","고덕S/S 154kV SW신규수용공사","ㅇ 154kV #2BUS측 무부하 가압 - 고덕-프랙스에어#1,2T/L","2019-06-25 09:00","2019-06-26 18:00","2019-06-25 09:00","2019-06-26 18:00","연속"]
[233,"강원","강릉","신제천주진#1 T/L","2019년 송전 정비회사 총액공사(송전선로용 피뢰기 설치)","송전전로용 피뢰기 5기 설치 (No.1~No.5)","2019-06-10 08:00","2019-06-11 18:00","2019-06-10 08:00","2019-06-11 18:00","매일"]
[234,"강원","동해","동해영동TP T/L","2018~2019년 동해전력지사 송전정비 협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-06-27 08:00","2019-06-28 18:00","취소","취소","연속"]
[235,"강원","동해","동해강릉 T/L","2018~2019년 동해전력지사 송전정비 협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-06-24 08:00","2019-06-26 18:00","취소","취소","연속"]
[236,"강원","동해","북평영동TP#1 T/L","2018~2019년 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-06-27 08:00","2019-06-28 18:00","취소","취소","연속"]
[237,"강원","동해","북평영동TP#1 T/L","2018~2019년 동해전력지사 송전정비 협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-06-24 08:00","2019-06-26 18:00","취소","취소","연속"]
[238,"강원","동해","북평영동TP#2 T/L","2018~2019년 동해전력지사 송전정비 협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-06-27 08:00","2019-06-28 18:00","취소","취소","연속"]
[239,"강원","동해","이원삼척 T/L","2019년 동해전력지사 170kV GIS 정밀점검","1. GIS 정밀점검 2. [병행]송전선로 보호배전반 교체공사","2019-06-10 09:30","2019-06-15 18:00","2019-06-10 09:30","2019-06-15 18:00","연속"]
[240,"강원","동해","이원태백 T/L","2019년 동해전력지사 170kV GIS 정밀점검","1. GIS 정밀점검","2019-06-03 09:30","2019-06-05 18:00","2019-06-05T09:00:00","2019-06-07T18:00:00","연속"]
[241,"강원","원주","신제천남원주#1 T/L","2019년 원주전력지사 변전정비회사 총액공사","남원주S/S 154kV 신제천-남원주#1T/L GIS 보통점검","2019-06-04 10:00","2019-06-04 18:00","2019-06-05 10:00","2019-06-05 18:00","당일"]
[242,"강원","직할","철원화천#2 T/L","철원S/S 154kV 비즌비츠로T/L용 GIS 설치공사","170kV 1250A 2CCT 설치 및 시험가압","2019-06-10 09:00","2019-06-11 18:00","2019-06-10 09:00","2019-06-11 18:00","연속"]
[243,"강원","직할","운천철원#2 T/L","2019년 상반기 장기 미동작 차단기 조작시험","철원S/S 154kV 운천-철원 #2 T/L 차단기 조작시험","2019-06-14 14:00","2019-06-14 18:00","2019-06-14 14:00","2019-06-14 18:00","당일"]
[244,"강원","직할","운천철원#1 T/L","2019년 상반기 장기 미동작 차단기 조작시험","철원S/S 154kV 운천-철원 #1 T/L 차단기 조작시험","2019-06-14 10:00","2019-06-14 14:00","2019-06-14 10:00","2019-06-14 14:00","당일"]
[245,"강원","직할","가평춘천HP T/L","154kV 화천T/L No.65~69 안전이격확보공사","No.65~69 철탑교체(5기), 전력선 2.132km 교체","2019-06-21 07:00","2019-06-30 18:00","취소","취소","매일"]
[246,"강원","직할","화천화천HP#2 T/L","2018~2019년 강원직할 송전정비회사 총액공사(애자교체)","섬락애자 교체(20장)","2019-06-05 07:00","2019-06-05 18:00","2019-06-05 07:00","2019-06-05 18:00","당일"]
[247,"강원","직할","가평화천HP T/L","154kV 화천T/L No.65~69 안전이격확보공사","No.65~69 철탑교체(5기), 전력선 2.132km 교체","2019-06-11 07:00","2019-06-20 18:00","취소","취소","연속"]
[248,"강원","태백","신제천영월CC#2 T/L","19년 태백전력지사 170kV GIS 정밀점검","영월CC 신제천영월CC#2T/L GIS 정밀점검","2019-06-19 10:00","2019-06-20 18:00","취소","취소","연속"]
[249,"강원","태백","신제천영월CC#1 T/L","19년 태백전력지사 170kV GIS 정밀점검","영월CC 신제천영월CC#1T/L GIS 정밀점검","2019-06-17 10:00","2019-06-18 18:00","취소","취소","연속"]
[250,"강원","태백","제천영월#1 T/L","18~19년 변전전문회사 총액공사","영월변전소 제천영월#1T/L GIS 조작시험","2019-06-03 10:00","2019-06-03 18:00","2019-06-13T10:00:00","2019-06-13T18:00:00","당일"]
[251,"강원","태백","도계태백 T/L","19년 태백전력지사 170kV GIS 정밀점검 공사","태백변전소 도계태백T/L GIS 정밀점검","2019-06-10 09:00","2019-06-11 18:00","2019-06-13T09:00:00","2019-06-15T18:00:00","연속"]
[252,"강원","태백","태백삼척GP#2 T/L","2018~2019년 동해전력지사 송전정비 협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-06-09 10:00","2019-06-16 18:00","2019-06-16T10:00:00","2019-06-23T18:00:00","연속"]
[253,"충북","직할","남음성덕산#2 T/L","덕산S/S 154kV 남음성-덕산#2T/L GIS 보통점검","덕산S/S 154kV 남음성-덕산#2T/L GIS 보통점검","2019-06-04 10:00","2019-06-04 18:00","2019-06-04 10:00","2019-06-04 18:00","당일"]
[254,"충북","직할","진천덕산#1 T/L","덕산S/S 154kV 진천-덕산#1T/L GIS 보통점검","덕산S/S 154kV 진천-덕산#1T/L GIS 보통점검","2019-06-05 10:00","2019-06-05 18:00","2019-06-05 10:00","2019-06-05 18:00","당일"]
[255,"충북","직할","진천덕산#2 T/L","덕산S/S 154kV 진천-덕산#2T/L GIS 보통점검","덕산S/S 154kV 진천-덕산#2T/L GIS 보통점검","2019-06-07 10:00","2019-06-07 18:00","2019-06-07 10:00","2019-06-07 18:00","당일"]
[256,"충북","직할","남음성덕산#1 T/L","덕산S/S 154kV 남음성-덕상#1T/L GIS 보통점검","덕산S/S 154kV 남음성-덕상#1T/L GIS 보통점검","2019-06-03 10:00","2019-06-03 18:00","2019-06-03 10:00","2019-06-03 18:00","당일"]
[257,"충북","직할","서운만승 T/L","154kV 서운-만승 등 2개T/L 전력선 교체공사","No.81~83 전력선 교체","2019-06-10 07:00","2019-06-14 18:00","2019-06-15 07:00","2019-06-16 18:00","연속"]
[258,"충북","직할","진천만승#2 T/L","2019년 가공송전선로 순시점검 위탁공사","No.1~50 정밀점검","2019-06-03 08:00","2019-06-07 18:00","2019-06-03 08:00","2019-06-07 18:00","연속"]
[259,"충북","직할","진천만승#1 T/L","154kV 서운-만승 등 2개T/L 전력선 교체공사","No.35~37 전력선교체","2019-06-10 07:00","2019-06-14 18:00","2019-06-15 07:00","2019-06-16 18:00","연속"]
[260,"충북","청주","상주보은 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-06-20 07:00","2019-06-22 18:00","취소","취소","연속"]
[261,"충북","청주","상주보은 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-06-01 07:00","2019-06-02 18:00","취소","취소","연속"]
[262,"충북","청주","사직북청주#2 T/L","18~19년 청주전력 변전협력회사 총액공사","사직S/S 사직-북청주#2T/L 154kV GIS 보통점검","2019-06-09 09:00","2019-06-09 18:00","2019-06-23 09:00","2019-06-23 18:00","당일"]
[263,"충북","청주","상주영동 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-06-03 07:00","2019-06-04 18:00","취소","취소","연속"]
[264,"충북","청주","상주영동 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-06-17 07:00","2019-06-19 18:00","취소","취소","연속"]
[265,"충북","청주","신진천오창#1 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","154kV 신진천-오창#1T/L 항공표시구, 불량애자 교체 항공표시구 교체 : No.14~15, No.46~47 불량애자 교체 : No.17","2019-06-08 12:00","2019-06-09 18:00","2019-06-08 12:00","2019-06-09 18:00","연속"]
[266,"충북","청주","신진천오창#2 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","154kV 신진천-오창#2T/L 항공표시구 교체 항공표시구 교체 : No.14~15, No.46~47","2019-06-08 07:00","2019-06-08 12:00","2019-06-08 07:00","2019-06-08 12:00","연속"]
[267,"충북","청주","청원죽림#2 T/L","154kV 청원-죽림T/L 정밀점검","154kV 청원-죽림T/L No.1~22 정밀점검","2019-06-15 09:00","2019-06-16 18:00","2019-06-15 09:00","2019-06-16 18:00","매일"]
[268,"충북","청주","청원죽림#1 T/L","154kV 청원-죽림T/L 정밀점검","154kV 청원-죽림T/L No.1~22 정밀점검","2019-06-01 09:00","2019-06-02 18:00","2019-06-01 09:00","2019-06-02 18:00","매일"]
[269,"충북","청주","청원오송#1 T/L","18~19년 청주전력 변전협력회사 총액공사","청원S/S 청원-오송#1T/L 154kV GIS 보통점검","2019-06-16 09:00","2019-06-16 18:00","2019-06-22 09:00","2019-06-22 18:00","당일"]
[270,"충북","충주","단양영월CC#2 T/L","154kV 단양-영월CCT/L 안전이격 확보공사","○ 공사구간 : 154kV 단양-영월CCT/L No.13~16, 51~55 ○ 철탑교체 : 154kV 2회선용 사각철탑 5기(No.14,15,52,53,54)","2019-06-17 07:00","2019-06-23 18:00","2019-06-17 07:00","2019-06-23 18:00","연속"]
[271,"충북","충주","단양영월CC#1 T/L","154kV 단양-영월CCT/L 안전이격 확보공사","○ 공사구간 : 154kV 단양-영월CCT/L No.13~16, 51~55 ○ 철탑교체 : 154kV 2회선용 사각철탑 5기(No.14,15,52,53,54)","2019-06-24 07:00","2019-06-28 18:00","2019-06-24 07:00","2019-06-28 18:00","연속"]
[272,"충북","충주","신제천제천#1 T/L","2018-2019년 송전정비회사 총액공사","피뢰기 설치 (No.1-5)","2019-06-03 08:00","2019-06-04 18:00","2019-06-03 08:00","2019-06-03 18:00","매일"]
[273,"충북","충주","신제천왕암#1 T/L","2018-2019년 송전정비회사 총액공사","피뢰기 설치 (No.1-5)","2019-06-03 08:00","2019-06-04 18:00","2019-06-27 08:00","2019-06-28 18:00","매일"]
[274,"충북","충주","신제천왕암#2 T/L","왕암S/S 건물 누수에 따른 안전점검 등","왕암S/S 건물 누수에 따른 안전점검을 위한 인접 전력설비 휴전","2019-06-12 10:00","2019-06-12 18:00","2019-06-12 10:00","2019-06-12 18:00","당일"]
[275,"충북","충주","왕암가남#2 T/L","왕암S/S 154kV SW 증설공사","GIS[170kV 50kA 1250A ] x 2CCT 설치 보호배전반 ㅌ2면 설치 기타 부대공사","2019-06-11 10:00","2019-06-11 18:00","2019-06-11 10:00","2019-06-11 18:00","당일"]
[276,"대전충남","서산","신당진당진#1 T/L","당진S/S 154kV 전력케이블 포설공사","#1SH.C용 전력케이블 관로포설 - 관로 터파기 및 파형관 포설 기타부대작업 ※ 휴전사유 : 관로 터파기시 상부 충전부 근접","2019-06-03 09:00","2019-06-03 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[277,"대전충남","서산","당진송악#2 T/L","154kV 해미-홍성 등 11개 T/L 피뢰기 설치공사","154kV 당진-송악#2T/L 피뢰기 설치공사 공사대상 : No.1~40호","2019-06-12 07:30","2019-06-15 18:00","2019-06-12 07:30","2019-06-15 18:00","매일"]
[278,"대전충남","서산","당진S/S 154kV #1 SC","당진S/S 154kV 전력케이블 포설공사","#1SH.C용 전력케이블 관로포설 - 전력케이블 포설 및 접속 기타부대작업","2019-06-04 09:00","2019-10-31 18:00","2019-06-04 09:00","2019-10-31 18:00","연속"]
[279,"대전충남","서산","신당진당진#2 T/L","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험","2019-06-27 10:00","2019-06-27 18:00","2019-06-27 10:00","2019-06-27 18:00","당일"]
[280,"대전충남","서산","서산태안 T/L","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험","2019-06-26 10:00","2019-06-26 18:00","2019-06-26 10:00","2019-06-26 18:00","당일"]
[281,"대전충남","서산","신당진S/S 154kV #61-#66 BUS TIE CB","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험","2019-06-12 10:00","2019-06-12 18:00","2019-06-12 10:00","2019-06-12 18:00","당일"]
[282,"대전충남","서산","신당진S/S 154kV #60-#65 BUS TIE CB","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험","2019-06-13 09:00","2019-06-13 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[283,"대전충남","서산","신당진S/S 154kV #60-#61 SEC CB","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험","2019-06-05 09:00","2019-06-05 18:00","취소","취소","당일"]
[284,"대전충남","서산","신당진S/S 154kV #65-#66 SEC CB","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험","2019-06-10 09:00","2019-06-10 18:00","취소","취소","당일"]
[285,"대전충남","서산","합덕송악#2 T/L","154kV 합덕-송악#2T/L 설비 보강공사","154kV 합덕-송악#2T/L 설비 보강공사 No.1 이중접속크램프 설치","2019-06-02 08:00","2019-06-03 18:00","2019-06-02 08:00","2019-06-03 18:00","매일"]
[286,"대전충남","서산","합덕송악#1 T/L","154kV 해미-홍성 등 11개 T/L 피뢰기 설치공사","154kV 당진-송악#2T/L 피뢰기 설치공사 병가구간 안전이격 확보","2019-06-12 07:30","2019-06-15 18:00","2019-06-12 07:30","2019-06-15 18:00","매일"]
[287,"대전충남","세종","덕진송강#1 T/L","154kV 세종-송강, 덕진-대화 연결 지중T/L 건설공사","1. 설치 가. 세종-송강 : 신설C/H~M/H#4 나. 덕진-대화 : 덕진E/C~신설C/H 2. 철거 : 덕진-송강T/L(덕진E/C~M/H#4)","2019-06-03 08:00","2019-06-15 17:00","취소","취소","연속"]
[288,"대전충남","세종","덕진송강#2 T/L","154kV 세종-송강, 덕진-대화 연결 지중T/L 건설공사","1. 설치 가. 세종-송강 : 신설C/H~M/H#4 나. 덕진-대화 : 덕진E/C~신설C/H 2. 철거 : 덕진-송강T/L(덕진E/C~M/H#4)","2019-06-17 08:00","2019-06-29 17:00","취소","취소","연속"]
[289,"대전충남","세종","부강월산#2 T/L","[변전] 170kV 장기미동작 차단기 조작시험","○170kV 장기미동작 차단기 조작시험 ○메커니즘 점검 및 전자변 교체","2019-06-11 09:30","2019-06-11 18:00","2019-06-11 09:30","2019-06-11 18:00","당일"]
[290,"대전충남","세종","부강월산#1 T/L","[변전] 170kV 장기미동작 차단기 조작시험","○170kV 장기미동작 차단기 조작시험 ○메커니즘 점검 및 전자변 교체","2019-06-10 09:30","2019-06-10 18:00","2019-06-10 09:30","2019-06-10 18:00","당일"]
[291,"대전충남","세종","조치원전의#2 T/L","[변전] 170kV 장기미동작 차단기 조작시험","○170kV 장기미동작 차단기 조작시험","2019-06-04 13:00","2019-06-04 18:00","2019-06-04 13:00","2019-06-04 18:00","당일"]
[292,"대전충남","세종","조치원전의#1 T/L","[변전] 170kV 장기미동작 차단기 조작시험","○170kV 장기미동작 차단기 조작시험","2019-06-04 09:30","2019-06-04 13:00","2019-06-04 09:30","2019-06-04 13:00","당일"]
[293,"대전충남","아산","서천안탕정#1 T/L","154kV 장재-천안 등 4개T/L 일진제 PMJ 교체공사","일진제 R-type 조립식접속함(PMJ) 교체","2019-06-25 08:00","2019-07-01 18:00","취소","취소","연속"]
[294,"대전충남","아산","아산합덕#1 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-06-04 07:00","2019-06-14 18:00","취소","취소","연속"]
[295,"대전충남","아산","아산합덕#2 T/L","[송전]345kV 신서산-아산 등 2개T/L 지장송전선로 이설공사","가. 철탑 설치 및 철거 : 2기 [No.83(B4-28 → Bb4-36), No.84(F4-29 → F4-39)] 나. 전력선교체 - ACSR 480㎟ x 4B x 2C × 1.778km [No.82~83 1선 교체, No.83~88 24선 교체] - ACSR 410㎟ x 2B x 2C × 1.778km [No.83~88 24선 교체]","2019-06-15 07:00","2019-06-25 18:00","취소","취소","연속"]
[296,"대전충남","아산","아산인주#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","154kV 아산-인주 #2T/L 피뢰기 설치 9기분","2019-06-15 07:00","2019-06-16 18:00","2019-06-15 07:00","2019-06-16 18:00","매일"]
[297,"대전충남","아산","아산인주#1 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기설치공사","154kV 아산-인주#1T/L 피뢰기 설치 10기분","2019-06-08 07:00","2019-06-09 18:00","2019-06-08 07:00","2019-06-09 18:00","매일"]
[298,"대전충남","아산","온양풍세#2 T/L","온양S/S 154kV 온양-풍세#2T/L GIS 정밀점검","○온양S/S 154kV 온양-풍세#2T/L GIS 정밀점검","2019-06-22 09:00","2019-06-23 18:00","2019-06-08 09:00","2019-06-09 18:00","연속"]
[299,"대전충남","아산","풍세장재#2 T/L","154kV 장재-천안 등 4개T/L 일진제 PMJ 교체공사","일진제 R-type 조립식접속함(PMJ) 교체","2019-06-18 08:00","2019-06-24 18:00","취소","취소","연속"]
[300,"대전충남","아산","풍세장재#1 T/L","154kV 장재-천안 등 4개T/L 일진제 PMJ 교체공사","일진제 R-type 조립식접속함(PMJ) 교체","2019-06-11 08:00","2019-06-17 18:00","취소","취소","연속"]
[301,"대전충남","아산","장재천안#2 T/L","[송전] 154kV 장재-천안T/L 전력선 점검","ㅇNo.7~8 간 전력선 점검 및 보수","2019-06-18 08:00","2019-06-18 18:00","2019-06-18 08:00","2019-06-18 18:00","당일"]
[302,"대전충남","청양","신풍공주#1 T/L","154kV 신풍E/C #3M.Tr증설공사","O 154kV GIS(170kV 50kA 1250A) 설치 * 1CCT O 기타 부대공사 * 1식","2019-06-25 10:00","2019-06-27 18:00","2019-06-25 10:00","2019-06-27 18:00","연속"]
[303,"대전충남","청양","청양신풍#1 T/L","청양S/S 154kV 차단기 부동작예방 조작시험","청양S/S 154kV 차단기 부동작예방 조작시험 - 대상 : 154kV 청양-신풍#1T/L","2019-06-03 09:00","2019-06-03 14:00","2019-06-03 09:00","2019-06-03 14:00","당일"]
[304,"대전충남","청양","청양신풍#2 T/L","청양S/S 154kV 차단기 부동작예방 조작시험","청양S/S 154kV 차단기 부동작예방 조작시험 - 대상 : 154kV 청양-신풍#2T/L","2019-06-03 14:00","2019-06-03 18:00","2019-06-03 14:00","2019-06-03 18:00","당일"]
[305,"대전충남","서산","서산태안화력 T/L","154kV 서산-태안화력T/L 항공장애표시구 정비","154kV서산-태안화력T/L 항공장애표시구 정비 - No.38-39 (2개 정비)","2019-06-01 09:00","2019-06-01 18:00","2019-06-01 09:00","2019-06-01 18:00","당일"]
[306,"전북","군산","군산S/S 154kV #62-#67 BUS TIE CB","군산P/O 154kV 이상 차단기 조작시험(6200)","6200 개폐타임측정","2019-06-20 10:30","2019-06-20 12:00","2019-06-20 10:30","2019-06-20 12:00","당일"]
[307,"전북","군산","군산S/S 154kV #60-#65 BUS TIE CB","군산P/O 154kV 이상 차단기 조작시험(6100)","6100개폐타임측정","2019-06-20 09:00","2019-06-20 10:30","2019-06-20 09:00","2019-06-20 10:30","당일"]
[308,"전북","군산","군산서군산#2 T/L","154kV 군산-서군산 등 2개T/L 비표준자기애관 교체공사","비표준 자기애관 교체공사","2019-06-30 09:00","2019-07-10 18:00","2019-06-30 09:00","2019-07-10 18:00","연속"]
[309,"전북","군산","군산서군산#1 T/L","154kV 군산-서군산 등 2개T/L 비표준자기애관 교체공사","비표준 자기애관 교체공사","2019-06-20 09:00","2019-06-29 18:00","2019-06-20 09:00","2019-06-29 18:00","연속"]
[310,"전북","군산","군산서군산#2 T/L","군산서군산T/L 안전이격거리확보공사","-철탑신설 2기(25,26)","2019-06-17 07:00","2019-06-19 18:00","2019-06-17 07:00","2019-06-19 18:00","연속"]
[311,"전북","군산","동군산장항#2 T/L","군산P/O 차단기 점검공사(154, 345kV)","1. 647 차단기 하자점검","2019-06-05 09:30","2019-06-05 13:00","2019-06-05 09:30","2019-06-05 13:00","당일"]
[312,"전북","군산","군산서군산#2 T/L","서군산S/S 현대화관련 부지확보공사","서군산S/S 현대화관련 부지확보공사","2019-06-11 09:00","2019-06-15 18:00","2019-06-11 09:00","2019-06-15 18:00","당일"]
[313,"전북","군산","영등팔봉#1 T/L","154kV 군산-서군산 등 2개T/L 비표준자기애관 교체공사","비표준자기애관 교체공사","2019-06-20 09:00","2019-06-29 18:00","2019-06-20 09:00","2019-06-29 18:00","연속"]
[314,"전북","군산","영등팔봉#2 T/L","154kV 군산-서군산 등 2개T/L 비표준자기애관 교체공사","비표준자기애관 교체공사","2019-06-30 09:00","2019-07-10 18:00","2019-06-30 09:00","2019-07-10 18:00","연속"]
[315,"전북","군산","이리백산#1 T/L","이리백산T/L 항공장애표시구설치공사","항공구설치 : 36~37, 43~45","2019-06-04 07:00","2019-06-05 18:00","2019-06-04 07:00","2019-06-05 18:00","당일"]
[316,"전북","군산","이리백산#2 T/L","이리백산T/L 항공장애표시구설치공사","항공구설치 : 36~37, 43~45","2019-06-07 07:00","2019-06-07 18:00","2019-06-07 07:00","2019-06-07 18:00","당일"]
[317,"전북","김제","백산김제#2 T/L","이리백산T/L 항공장애표시구설치공사","항공구설치 안전이격거리확보","2019-06-04 07:00","2019-06-05 18:00","2019-06-04 07:00","2019-06-05 18:00","연속"]
[318,"전북","김제","백산김제#1 T/L","이리백산T/L 항공장애표시구설치공사","항공구설치 : 36~37, 43~45","2019-06-07 07:00","2019-06-07 18:00","2019-06-07 07:00","2019-06-07 18:00","당일"]
[319,"전북","김제","신김제정공#2 T/L","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2019-06-04 10:00","2019-06-04 18:00","2019-06-04 10:00","2019-06-04 18:00","당일"]
[320,"전북","김제","신김제남전주#2 T/L","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2019-06-14 10:00","2019-06-14 18:00","2019-06-14 10:00","2019-06-14 18:00","당일"]
[321,"전북","김제","신김제남전주#1 T/L","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2019-06-13 10:00","2019-06-13 18:00","2019-06-13 10:00","2019-06-13 18:00","당일"]
[322,"전북","김제","신김제정공#1 T/L","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2019-06-03 10:00","2019-06-03 18:00","2019-06-03 10:00","2019-06-03 18:00","당일"]
[323,"전북","직할","팔봉봉동#1 T/L","관내SS 154kV 이상 차단기 점검공사","봉동SS 팔봉-봉동#1TL 차단기 조작시험","2019-06-03 09:30","2019-06-03 14:00","2019-06-01 09:30","2019-06-01 14:00","당일"]
[324,"전북","직할","팔봉봉동#2 T/L","관내SS 154kV 이상 차단기 점검공사","봉동SS 팔봉-봉동#2TL 차단기 조작시험","2019-06-03 14:00","2019-06-03 18:00","2019-06-01 14:00","2019-06-01 18:00","당일"]
[325,"전북","직할","이리전주#1 T/L","관내SS 154kV 이상 차단기 점검공사","전주SS 이리-전주#1TL 차단기 조작시험","2019-06-11 09:00","2019-06-11 14:00","2019-06-11 09:00","2019-06-11 14:00","당일"]
[326,"전북","직할","이리전주#2 T/L","관내SS 154kV 이상 차단기 점검공사","전주SS 이리-전주#2TL 차단기 조작시험","2019-06-11 14:00","2019-06-11 18:00","2019-06-11 14:00","2019-06-11 18:00","당일"]
[327,"전북","직할","북전주봉동#1 T/L","154kV 북전주-봉동T/L 피뢰기 설치공사","154kV 북전주-봉동T/L 피뢰기 설치공사 No.1~9 (4기)","2019-06-04 07:30","2019-06-04 18:00","2019-06-04 07:30","2019-06-04 18:00","당일"]
[328,"전북","직할","북전주봉동#2 T/L","관내SS 154kV 이상 차단기 점검공사","봉동SS 북전주-봉동#2TL 차단기 조작시험 북전주SS 북전주-봉동#2TL 차단기 조작시험","2019-06-05 09:30","2019-06-05 18:00","2019-06-05 09:30","2019-06-05 18:00","당일"]
[329,"전북","김제","정공칠보HP T/L","154kV GIS 정밀점검","가스누기 보수","2019-06-24 09:00","2019-06-26 18:00","2019-06-24 09:00","2019-06-26 18:00","연속"]
[330,"광주전남","강진","강진남창#1 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,남창S/S 보호배전반 대체, 시험, LA, CVT 이설 송전선로 철거 및 가선, 선로접속, 모선POST 철거 OPGW 설치 및 시험","2019-06-25 09:00","2019-07-06 18:00","취소","취소","연속"]
[331,"광주전남","강진","강진남창#2 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,신강진,남창S/S 보호배전반 대체, 시험 강진-남창#2T/L, 신강진-강진#2T/L 직결","2019-06-17 09:00","2019-06-24 18:00","취소","취소","연속"]
[332,"광주전남","강진","신강진강진#2 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,신강진,남창S/S 보호배전반 대체, 시험 강진-남창#2T/L, 신강진-강진#2T/L 직결","2019-06-17 09:00","2019-06-24 18:00","취소","취소","연속"]
[333,"광주전남","강진","신강진강진#2 T/L","154kV 인출선로 모선 재배열공사","가. 공사장소 : 신강진S/S 154kV 인출선로 나. 휴전선로 : 154kV 신강진-강진#2T/L 다. 작업내용 - 인출선로 모선 재배열을 위한 선로 재배열공사 - 선종/길이 : 신강진-대불#1T/L(XLPE 2000SQ X 1C(D) X 0.12km) 신강진-강진#2T/L(XLPE 2000SQ X 1C(D) X 0.12km) - 접속 : EB-G 4개소, EB-A 4개소","2019-06-15 09:00","2019-07-25 18:00","2019-06-15 09:00","2019-07-25 18:00","연속"]
[334,"광주전남","광주","계림S/S 154kV #61 BUS","19년 변전총액공사(#61BUS)","154kV PT 집합반 교체","2019-06-19 09:00","2019-06-19 18:00","2019-06-19 09:00","2019-06-19 18:00","당일"]
[335,"광주전남","광주","계림S/S 154kV #65 BUS","19년 변전총액공사(#65BUS)","154kV PT 집합반 교체","2019-06-18 09:00","2019-06-18 18:00","2019-06-18 09:00","2019-06-18 18:00","당일"]
[336,"광주전남","광주","계림S/S 154kV #66 BUS","19년 변전총액공사(#66BUS)","154kV PT 집합반 교체","2019-06-18 09:00","2019-06-18 18:00","2019-06-18 09:00","2019-06-18 18:00","당일"]
[337,"광주전남","광주","계림S/S 154kV #60 BUS","19년 변전총액공사(#60BUS)","154kV PT 집합반 교체","2019-06-17 09:00","2019-06-17 18:00","2019-06-17 09:00","2019-06-17 18:00","당일"]
[338,"광주전남","광주","계림S/S 154kV #61 BUS","19년 변전총액공사(#61BUS)","154kV PT 집합반 교체","2019-06-17 09:00","2019-06-17 18:00","2019-06-17 09:00","2019-06-17 18:00","당일"]
[339,"광주전남","광주","계림S/S 154kV #60 BUS","19년 변전총액공사(#60BUS)","154kV PT 집합반 교체","2019-06-19 09:00","2019-06-19 18:00","2019-06-19 09:00","2019-06-19 18:00","당일"]
[340,"광주전남","광주","신광주계림#2 T/L","19년 광주전력지사 170kV GIS 정밀점검공사","계림S/S 신광주-계림#2T/L GIS 정밀점검","2019-06-03 09:00","2019-06-05 18:00","2019-06-03 09:00","2019-06-05 18:00","연속"]
[341,"광주전남","광주","북광주계림#2 T/L","19년 광주변전총액공사","북광주-계림#2T/L GIS 보통점검","2019-06-11 09:00","2019-06-11 18:00","2019-06-11 09:00","2019-06-11 18:00","당일"]
[342,"광주전남","광주","계림충장#1 T/L","19년 광주변전총액공사","계림-충장#1T/L GIS 보통점검","2019-06-12 09:00","2019-06-12 18:00","2019-06-12 09:00","2019-06-12 18:00","당일"]
[343,"광주전남","광주","북광주계림#1 T/L","19년 광주변전총액공사","북광주-계림#1T/L GIS 보통점검","2019-06-10 09:00","2019-06-10 18:00","2019-06-10 09:00","2019-06-10 18:00","당일"]
[344,"광주전남","광주","신화순평동 T/L","154kV 나주S/S 옥내화 건설공사","154kV 나주옥내화 건설관련 송전선로 이설 신화순-평동T/L -> 직결해제(신화순-나주#1T/L, 나주-평동#1T/L)","2019-06-07 09:00","2019-06-14 18:00","2019-06-07 09:00","2019-06-14 18:00","연속"]
[345,"광주전남","광주","장성영광#2 T/L","19년 광주전력지사 170kV GIS 정밀점검공사","장성S/S 장성-영광#2T/L GIS 정밀점검","2019-06-10 09:00","2019-06-12 18:00","2019-06-10 09:00","2019-06-12 18:00","연속"]
[346,"광주전남","광주","충장농성#1 T/L","19년 광주변전총액공사","충장-농성#1T/L 장기미동작 차단기 점검","2019-06-13 09:00","2019-06-13 14:00","2019-06-13 09:00","2019-06-13 14:00","당일"]
[347,"광주전남","광주","충장농성#2 T/L","19년 광주변전총액공사","충장-농성#2T/L 장기미동작 차단기 점검","2019-06-13 14:00","2019-06-13 18:00","2019-06-13 14:00","2019-06-13 18:00","당일"]
[348,"광주전남","순천","서순천주암HP T/L","19년 순천전력지사 GIS 정밀점검공사","서순천S/S 서순천-주암HP T/L GIS 정밀점검","2019-06-27 09:00","2019-06-28 18:00","2019-06-27 09:00","2019-06-28 18:00","연속"]
[349,"광주전남","순천","승주서순천 T/L","19년 순천전력지사 GIS 정밀점검공사","서순천S/S 승주-서순천T/L GIS 정밀점검","2019-06-24 09:00","2019-06-25 18:00","2019-06-24 09:00","2019-06-25 18:00","연속"]
[350,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주#1 T/L 갤러핑우려개소 상간스페이서 설치","18~19년도 순천전력 협력회사 총액공사 - 순천-승주#1 T/L 갤러핑 우려개소 상간스페이서설치 - No.109~110호(3set)","2019-06-19 08:00","2019-06-19 18:00","2019-06-19 08:00","2019-06-19 18:00","당일"]
[351,"광주전남","순천","승주주암HP T/L","154kV 승주-주암HP T/L 피뢰기 설치","18~19년도 순천전력 협력회사 총액공사 - 승주-주암HP T/L 피뢰기 설치 - No.26호(3SET)","2019-06-20 08:30","2019-06-20 13:00","2019-06-20 08:30","2019-06-20 13:00","당일"]
[352,"광주전남","순천","여수소라#1 T/L","19년 변전정비회사 총액공사","여수S/S 여수-소라#1T/L GIS 보조계전기 교체","2019-06-26 10:00","2019-06-26 18:00","2019-06-26 10:00","2019-06-26 18:00","당일"]
[353,"광주전남","순천","여수T/P 154kV #66 BUS","여수화력S/Y 154kV GS칼텍스#1T/L 선로 무부하가압","여수화력S/Y 154kV GS칼텍스#1T/L EBA 철거공사","2019-06-03 17:00","2019-06-04 17:00","취소","취소","연속"]
[354,"광주전남","순천","여수TP화치#1 T/L","여수화력S/Y 154kV GS칼텍스#1T/L 선로 무부하가압","여수화력S/Y 154kV GS칼텍스#1T/L EBA 철거공사","2019-06-03 17:00","2019-06-04 17:00","취소","취소","연속"]
[355,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성 #1T/L(자기애관 교체공사)","○ 154kV 여수TP-용성 #1T/L 자기애관을 폴리머애관으로 교체(6대)","2019-06-08 07:00","2019-06-09 18:00","취소","취소","연속"]
[356,"광주전남","순천","호남TP여수TP#1 T/L","여수화력S/Y 154kV GS칼텍스#1T/L 선로 무부하가압","여수화력S/Y 154kV GS칼텍스#1T/L EBA 철거공사","2019-06-03 17:00","2019-06-04 17:00","취소","취소","연속"]
[357,"광주전남","순천","여천여수산단#2 T/L","19년 순천전력지사 GIS 정밀점검공사","여천S/S 여천-여수산단#2T/L GIS 정밀점검","2019-06-03 09:00","2019-06-04 18:00","2019-06-03 09:00","2019-06-04 18:00","연속"]
[358,"광주전남","순천","여천S/S 154kV #60 BUS","한화에너지 LOOP 운전 관련(여천계-용성계)","한화에너지 LOOP 운전 관련(여천계-용성계)","2019-06-11 13:00","2019-06-11 14:00","2019-06-11 13:00","2019-06-11 14:00","당일"]
[359,"광주전남","순천","여천여수산단#1 T/L","한화에너지 LOOP 운전 관련(여천계-용성계)","한화에너지 LOOP 운전 관련(여천계-용성계)","2019-06-11 13:00","2019-06-11 14:00","2019-06-11 13:00","2019-06-11 14:00","당일"]
[360,"광주전남","순천","여천S/S 154kV #61-#66 BUS TIE GIS","여천S/S 154kV 절환모선 설치공사","여천S/S 6400(#2T-BUS TIE) 모선보호반 Feeder 증설","2019-06-17 09:00","2019-06-17 18:00","2019-06-17 09:00","2019-06-17 18:00","당일"]
[361,"광주전남","순천","여천S/S 154kV #60-#61 SEC GIS","여천S/S 154kV 절환모선 설치공사","여천S/S 6400(#2T-BUS TIE) 모선보호반 Feeder 증설","2019-06-17 09:00","2019-06-17 18:00","2019-06-17 09:00","2019-06-17 18:00","당일"]
[362,"광주전남","순천","여천S/S 154kV #65-#66 SEC GIS","여천S/S 154kV 절환모선 설치공사","여천S/S 6400(#2T-BUS TIE) 모선보호반 Feeder 증설","2019-06-17 09:00","2019-06-17 18:00","2019-06-17 09:00","2019-06-17 18:00","당일"]
[363,"광주전남","순천","여천여수산단#2 T/L","한화에너지 LOOP 운전 관련(여천계-용성계)","한화에너지 LOOP 운전 관련(여천계-용성계)","2019-06-11 13:00","2019-06-11 14:00","2019-06-11 13:00","2019-06-11 14:00","당일"]
[364,"광주전남","직할","나주엄다#2 T/L","154kV 나주옥내화 건설공사","송전선로 이설 신화순-평동T/L 안전이격거리 확보를 위한 병행휴전","2019-06-08 09:00","2019-06-08 18:00","2019-06-08 09:00","2019-06-08 18:00","당일"]
[365,"광주전남","직할","일곡비아#2 T/L","[자동화] CID 업그레이드","○ CID 업그레이드","2019-06-07 13:00","2019-06-07 18:00","2019-06-05 13:00","2019-06-05 18:00","당일"]
[366,"광주전남","직할","일곡비아#1 T/L","[자동화] CID 업그레이드","○ CID 업그레이드","2019-06-07 09:00","2019-06-07 13:00","2019-06-05 09:00","2019-06-05 13:00","당일"]
[367,"광주전남","광주","신광주일곡#1T/L","154kV 신광주-일곡#1T/L  정밀점검","2019년 가공송전 순시점검 위탁공사\n신광주ST-일곡ST No.1~21 정밀점검","2019-06-15 09:00","2019-06-16 18:00","2019-06-15 09:00","2019-06-16 18:00","매일"]
[368,"광주전남","광주","신광주일곡#2T/L","154kV 신광주-일곡#1T/L  정밀점검","2019년 가공송전 순시점검 위탁공사\n신광주ST-일곡ST No.1~21 정밀점검","2019-06-22 09:00","2019-06-23 18:00","2019-06-22 09:00","2019-06-23 18:00","매일"]
[369,"광주전남","직할","매월화정#2T/L","매월S/S 154kV 매월-화정 #2T/L (GIS 정밀점검)","2019년 직할 170kV GIS 정밀점검공사 - 내용 : CB, 상부BUS, C/H 내부 정밀점검","2019-06-28 09:00","2019-06-29 18:00","2019-06-28 09:00","2019-06-29 18:00","연속"]
[370,"광주전남","직할","남광주금천#1T/L","154kV 금천S/S #3M.Tr 증설공사"," ○최종 무부하 가압 - 154kV #3M.Tr, 170kV GIS, 25.8kV SIS","2019-06-18 10:00","2019-06-19 14:00","2019-06-18 10:00","2019-06-19 10:00","연속"]
[371,"광주전남","직할","나주엄다#2T/L","154kV 나주옥내화 건설공사","송전선로 이설 신화순-나주#1T/L 안전이격거리 확보를 위한 병행휴전","2019-06-01 09:00","2019-06-01 12:00","2019-06-01 09:00","2019-06-01 12:00","당일"]
[372,"광주전남","광주","일곡비아#1T/L","154kV 신광주-일곡#1T/L  정밀점검","2019년 가공송전 순시점검 위탁공사\n신광주ST-일곡ST No.1~21 정밀점검 안전이격","2019-06-15 09:00","2019-06-15 18:00","2019-06-15 09:00","2019-06-15 18:00","당일"]
[373,"광주전남","광주","일곡비아#2T/L","154kV 신광주-일곡#1T/L  정밀점검","2019년 가공송전 순시점검 위탁공사\n신광주ST-일곡ST No.1~21 정밀점검 안전이격","2019-06-22 09:00","2019-06-22 18:00","2019-06-22 09:00","2019-06-22 18:00","당일"]
[374,"대구","경산","신경산노변 T/L","신경산S/S 신경산-노변T/L","GIS 하자점검","2019-06-11 14:00","2019-06-11 18:00","2019-06-11 14:00","2019-06-11 18:00","당일"]
[375,"대구","경산","신경산진량 T/L","신경산S/S 신경산-진량T/L","GIS 하자점검","2019-06-11 09:00","2019-06-11 14:00","2019-06-11 09:00","2019-06-11 14:00","당일"]
[376,"대구","달성","다산강창#2 T/L","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사","2019-06-12 09:00","2019-06-13 18:00","2019-06-12 09:00","2019-06-13 18:00","연속"]
[377,"대구","달성","다산강창#1 T/L","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사","2019-06-10 09:00","2019-06-11 18:00","2019-06-10 09:00","2019-06-11 18:00","연속"]
[378,"대구","달성","내당두류#2 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사(보통점검)","2019-06-20 09:00","2019-06-20 18:00","2019-06-20 09:00","2019-06-20 18:00","당일"]
[379,"대구","달성","내당두류#1 T/L","달성전력지사 변전총액공사","달성전력지사 변전총액공사(보통점검)","2019-06-19 09:00","2019-06-19 18:00","2019-06-19 09:00","2019-06-19 18:00","당일"]
[380,"대구","달성","상인봉덕#1 T/L","달성전력지사 정밀점검공사","달성전력지사 정밀점검공사(TEST선로)","2019-06-04 13:00","2019-06-04 18:00","2019-06-04 13:00","2019-06-04 18:00","당일"]
[381,"대구","포항","울주외동#1 T/L","외동S/S 울주-외동#1T/L GIS 보통점검","외동S/S 울주-외동#1T/L GIS 보통점검","2019-06-24 09:00","2019-06-24 18:00","2019-06-24 09:00","2019-06-24 18:00","당일"]
[382,"대구","포항","울주외동#2 T/L","외동S/S 울주-외동#2T/L GIS 보통점검","외동S/S 울주-외동#2T/L GIS 보통점검","2019-06-25 09:00","2019-06-25 18:00","2019-06-25 09:00","2019-06-25 18:00","당일"]
[383,"경북","영주","점촌문경 T/L","'19년 영주전력 가공송전위탁공사 송전선로 정밀점검(문경분기,점촌문경))","154kV 문경분기T/L No.1~30 송전선로 정밀점검","2019-06-07 09:00","2019-06-08 18:00","2019-05-31 09:00","2019-06-01 18:00","연속"]
[384,"경북","영주","문경단양 T/L","'19년 영주전력 가공송전위탁공사 송전선로 정밀점검(문경분기,문경단양)","154kV 문경분기T/L No.1~30 송전선로 정밀점검","2019-06-14 09:00","2019-06-15 18:00","2019-06-07 09:00","2019-06-08 18:00","연속"]
[385,"경북","직할","안동S/S 154kV #2 M.Tr CB","18~19년 경북직할 변전정비회사 총액공사","안동S/S #2M.Tr 1차, 2차GIS 조작시험","2019-06-24 09:00","2019-06-24 13:00","취소","취소","당일"]
[386,"경북","직할","안동S/S 154kV #3 M.Tr CB","18~19년 경북직할 변전정비회사 총액공사","안동S/S #3M.Tr 1차, 2차GIS 조작시험","2019-06-24 14:00","2019-06-24 18:00","취소","취소","당일"]
[387,"경북","직할","안동S/S 154kV #1 M.Tr CB","18~19년 경북직할 변전정비회사 총액공사","안동S/S #1M.Tr 보통점검 및 1차,2차 GIS 조작시험","2019-06-27 09:00","2019-06-28 18:00","취소","취소","당일"]
[388,"경북","직할","영덕진보#1 T/L","18~19년 경북직할 변전정비회사 총액공사","영덕S/S 영덕-진보#1T/L CVT초기점검, GIS조작시험 진보S/S GIS 조작시험","2019-06-18 09:00","2019-06-18 18:00","2019-06-18 09:00","2019-06-18 18:00","당일"]
[389,"경북","직할","영덕진보#2 T/L","18~19년 경북직할 변전정비회사 총액공사","영덕S/S 영덕-진보#2T/L CVT초기점검, GIS조작시험 진보S/S GIS 조작시험","2019-06-19 09:00","2019-06-19 18:00","2019-06-19 09:00","2019-06-19 18:00","당일"]
[390,"경북","직할","울진삼척GP#2 T/L","18~19년 경북직할 변전정비회사 총액공사","울진S/S 울진-삼척GP#2T/L CVT 보통점검 및 GIS 조작시험","2019-06-21 13:00","2019-06-21 18:00","2019-06-21 13:00","2019-06-21 18:00","당일"]
[391,"경북","직할","울진삼척GP#1 T/L","18~19년 경북직할 변전정비회사 총액공사","울진S/S 울진-삼척GP#1T/L CVT 보통점검 및 GIS 조작시험","2019-06-21 09:00","2019-06-21 13:00","2019-06-21 09:00","2019-06-21 13:00","당일"]
[392,"경북","직할","영덕평해#1 T/L","154kV 평해S/S 옥외철구설비 현대화 공사","170kV GIS 상용주파 내전압 시험","2019-06-11 09:00","2019-06-11 18:00","2019-06-11 09:00","2019-06-11 18:00","당일"]
[393,"경북","직할","영덕평해#2 T/L","154kV 평해S/S 옥외철구설비 현대화 공사","170kV GIS 상용주파 내전압 시험","2019-06-11 09:00","2019-06-11 18:00","2019-06-11 09:00","2019-06-11 18:00","당일"]
[394,"경북","직할","봉화현종산풍력 T/L","154kV 봉화-현종산풍력T/L 정밀점검","154kV 봉화-현종산풍력T/L No.54~104 정밀점검","2019-06-24 08:00","2019-06-26 18:00","2019-06-24 08:00","2019-06-26 18:00","연속"]
[395,"부산울산","동부산","구서노포#2 T/L","2019년 가공송전 순시점검 위탁공사(동부산)","154kV 구서-노포T/L 정밀점검 ㅇ구간 : 구서C/H ~ 노포S/S (18기)","2019-06-03 09:00","2019-06-04 18:00","2019-06-03 09:00","2019-06-04 18:00","연속"]
[396,"부산울산","동부산","신양산S/S 154kV #67 BUS","154kV 시랑E/C 건설공사","시랑변전소 계통병입 및 무부하가압 전 선로 상체크(신양산-시랑#2T/L)","2019-06-17 09:00","2019-06-17 10:00","2019-06-17 09:00","2019-06-17 10:00","연속"]
[397,"부산울산","동부산","신양산좌동#2 T/L","154kV 시랑E/C 건설공사","시랑변전소 계통병입 및 시험가압 - 상대단변전소(신양산, 좌동) 보호배전반 대체 및 최초가압","2019-06-10 08:00","2019-06-20 18:00","2019-06-10 08:00","2019-06-20 18:00","연속"]
[398,"부산울산","동부산","신양산S/S 154kV #60 BUS","345kV 신양산S/S 현대화 공사","345kV 신양산S/S 현대화 공사 - 덕트 기초 되메우기(안전이격)","2019-06-04 09:00","2019-06-04 18:00","2019-06-04 09:00","2019-06-04 18:00","당일"]
[399,"부산울산","북부산","구포모라#1 T/L","2019년 북부산 154kV GIS 정밀점검 공사","구포E/C 154kV 구포-모라#1T/L GIS 정밀점검","2019-06-10 09:00","2019-06-12 18:00","2019-06-10 09:00","2019-06-13 18:00","연속"]
[400,"부산울산","북부산","북부산호포 T/L","2019년 북부산 변전협력회사 총액공사","북부산E/C 154kV 북부산-호포T/L 미동작점검","2019-06-13 10:00","2019-06-13 18:00","2019-06-13 10:00","2019-06-13 18:00","당일"]
[401,"부산울산","북부산","모라엄궁#1 T/L","2019년 북부산 변전협력회사 총액공사","엄궁E/C 154kV 모라-엄궁#1T/L GIS 하자점검","2019-06-21 10:00","2019-06-21 18:00","2019-06-21 10:00","2019-06-21 18:00","당일"]
[402,"부산울산","북부산","엄궁학장#2 T/L","2019년 북부산 변전협력회사 총액공사","학장E/C 154kV 엄궁-학장#2T/L GIS 하자점검","2019-06-20 10:00","2019-06-20 18:00","2019-06-20 10:00","2019-06-20 18:00","당일"]
[403,"부산울산","북부산","엄궁학장#1 T/L","2019년 북부산 변전협력회사 총액공사","학장E/C 154kV 엄궁-학장#1T/L GIS 하자점검","2019-06-18 10:00","2019-06-18 18:00","2019-06-18 10:00","2019-06-18 18:00","당일"]
[404,"부산울산","서부산","녹공마천#2 T/L","녹공S/S 녹공-마천#2T/L GIS 개폐타임 측정","녹공S/S 녹공-마천#2T/L GIS 개폐타임 측정","2019-06-05 10:00","2019-06-05 18:00","2019-06-05 10:00","2019-06-05 18:00","당일"]
[405,"부산울산","서부산","서부산신평#2 T/L","154kV 서부산-신평, YK T/L 지중화사업(19.10)","○ 지중 : 서부산-신평#1T/L 지중화관련 지중케이블 포설 및 접속 ○ 송전공사 : 서부산-신평#1T/L 가공연결작업","2019-06-15 10:00","2019-06-27 11:00","2019-06-15 10:00","2019-06-27 11:00","연속"]
[406,"부산울산","서부산","서부산신평#2 T/L","154kV 서부산-신평T/L 계통정비공사","(#1 T/L 휴전 작업중) - 서부산-신평T/L 3호 철탑보강, 암 설치 - 서부산C/H ~ 3호 #1 T/L 가선작업 ※ 안전이격조건 [#2 T/L 비상 시 투입가능]","2019-06-07 07:00","2019-06-12 18:00","2019-06-07 07:00","2019-06-12 18:00","연속"]
[407,"부산울산","서부산","서부산신평#1 T/L","154kV 서부산-신평T/L 계통정비공사","(#2 T/L 휴전 작업 중) - 서부산-신평T/L 3호 철탑보강, 암 설치 - 서부산C/H ~ 3호 #2T/L 가선작업 ※ 안전이격조건 [#1 T/L 비상 시 투입가능]","2019-06-15 07:00","2019-06-17 18:00","2019-06-15 07:00","2019-06-17 18:00","연속"]
[408,"부산울산","서부산","서부산신평#1 T/L","154kV 서부산-신평, YK T/L 지중화사업(19.10)","○ 지중 : 서부산-신평#1T/L 지중화관련 지중케이블 포설 및 접속 ○ 송전공사 : 서부산-신평#1T/L 가공연결작업","2019-06-01 10:00","2019-06-14 18:00","2019-06-01 10:00","2019-06-14 18:00","연속"]
[409,"부산울산","서부산","서부산S/S 154kV #66 BUS","154kV 서부산-신평, YK T/L 지중화사업(19.10)","서부산-신평#2T/L 지중T/L 시험가압용","2019-06-26 10:00","2019-06-27 11:00","2019-06-26 10:00","2019-06-27 11:00","연속"]
[410,"부산울산","서부산","서부산S/S 154kV #61 BUS","154kV 서부산-신평, YK T/L 지중화사업(19.10)","서부산-신평#1T/L 지중T/L 시험가압용","2019-06-13 10:00","2019-06-14 11:00","2019-06-13 10:00","2019-06-14 11:00","연속"]
[411,"부산울산","울산","신울산영남TP#2 T/L","154kV 두왕E/C 건설사업","-신울산-영남T/P #2T/L 보호반 대체작업 -파이분기 긴선작업 -사용전검사(6.12~13), 실부하가압(6.12)","2019-06-07 08:30","2019-06-13 18:00","2019-06-07 08:30","2019-06-13 18:00","연속"]
[412,"부산울산","울산","신울산두왕#1 T/L CB","154kV 두왕분기T/L 건설공사","- 신울산-영남T/P #2T/L 분기작업을 위한 안전이격거리확보 - 비상시 작업자 철수 후 즉시가압가능","2019-06-07 08:00","2019-06-07 18:00","2019-06-07 08:00","2019-06-07 18:00","당일"]
[413,"부산울산","울산","신울산언양#1 T/L","154kV 신울산-언양#1T/L 장기사용애자 발췌공사","ㅁ 작업내용 : 장기사용애자 발췌 ㅁ 선로명 : 154kV 신울산-언양#1T/L ㅁ 대상철탑 : No.7, 9, 13, 14(4기)","2019-06-24 08:00","2019-06-25 18:00","2019-06-24 08:00","2019-06-25 18:00","연속"]
[414,"부산울산","울산","두왕영남TP#1 T/L CB","154kV 두왕분기T/L 건설공사","- 신울산-영남T/P #2T/L 분기작업을 위한 안전이격거리확보 - 비상시 작업자 철수 후 즉시가압가능","2019-06-07 08:00","2019-06-07 18:00","2019-06-07 08:00","2019-06-07 18:00","당일"]
[415,"부산울산","울산","신울산옥동#2 T/L","2019년 울산전력지사 170kV 장기사용GIS 대체공사","- 장기사용GIS 대체설비대상","2019-06-03 09:00","2019-06-21 18:00","2019-06-03 09:00","2019-06-21 18:00","연속"]
[416,"부산울산","울산","울산울산TP#1 T/L","울산-영남t/p 전력구공사","울산-영남t/p 전력구공사의 관로작업시 이격안전거리 확보용","2019-06-03 08:00","2019-06-17 18:00","2019-06-03 08:00","2019-06-17 18:00","매일"]
[417,"부산울산","울산","울산울산TP#2 T/L","울산-영남t/p 전력구공사","울산-영남t/p 전력구공사의 관로작업시 이격안전거리 확보용","2019-06-18 08:00","2019-06-30 18:00","2019-06-18 08:00","2019-06-30 18:00","매일"]
[418,"부산울산","울산","울주외동#1 T/L","154kV 울주-외동#1T/L 항공장애표시구 설치공사","ㅁ 작업내용 : 항공장애표시구 설치 ㅁ 선로명 : 154kV 울주-외동#1T/L ㅁ 작업구간 : No.2~3","2019-06-03 08:00","2019-06-03 18:00","2019-06-03 08:00","2019-06-03 18:00","당일"]
[419,"부산울산","울산","울주입실#1 T/L","154kV 울주-외동#1T/L 항공장애표시구 설치공사(안전확보)","ㅁ 작업내용 : 항공장애표시구 설치 ㅁ 작업선로명 : 154kV 울주-외동#1T/L ㅁ 안전확보 선로명 : 154kV 울주-입실#1T/L ㅁ 작업구간 : No.2~3","2019-06-03 08:00","2019-06-03 18:00","2019-06-03 08:00","2019-06-03 18:00","당일"]
[420,"부산울산","직할","수정범일#2 T/L","2019년 직할 변전협력회사 총액공사","- 범일S/S 수정-범일 #2T/L GIS 보통 점검 - 수정S/S 수정-범일 #2T/L GIS 미동작점검","2019-06-18 10:00","2019-06-18 18:00","2019-06-24 10:00","2019-06-24 18:00","당일"]
[421,"부산울산","직할","수정범일#1 T/L","2019년 직할 변전협력회사 총액공사","- 범일S/S 수정-범일 #1T/L GIS 보통 점검 - 수정S/S 수정-범일 #1T/L GIS 미동작점검","2019-06-17 10:00","2019-06-17 18:00","2019-06-21 10:00","2019-06-21 18:00","당일"]
[422,"부산울산","직할","서면S/S 154kV #65 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV BUS-TIE(6100)GIS #2DS부 정밀점검","2019-06-11 10:00","2019-06-11 20:00","2019-06-11 10:00","2019-06-11 20:00","당일"]
[423,"부산울산","직할","서면S/S 154kV #60 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV BUS-TIE(6100)GIS #1DS부 정밀점검","2019-06-12 10:00","2019-06-13 20:00","2019-06-12 10:00","2019-06-13 20:00","연속"]
[424,"부산울산","직할","서면S/S 154kV #60 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 미남-서면#2T/L(647)GIS #1DS부 정밀점검","2019-06-04 10:00","2019-06-05 20:00","2019-06-04 10:00","2019-06-05 20:00","연속"]
[425,"부산울산","직할","서면S/S 154kV #60 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 범지T/L(677)GIS #1DS부 정밀점검","2019-06-23 12:30","2019-06-23 13:30","2019-06-23 12:30","2019-06-23 13:30","당일"]
[426,"부산울산","직할","서면S/S 154kV #65 BUS","2019년 상반기 직할 170kV GIS 정밀점검공사","서면S/S 170kV 미남-서면#2T/L(647)GIS #2DS부 정밀점검","2019-06-03 10:00","2019-06-03 20:00","2019-06-03 10:00","2019-06-03 20:00","당일"]
[427,"부산울산","동부산","신울산명례#1 T/L","2019년 가공송전 순시점검 위탁공사-동부산","송전선로 정밀점검 구간 : 신울산E/C ~ 명례C/H(43기)","2019-06-17 09:00","2019-06-20 18:00","2019-06-17 09:00","2019-06-20 18:00","연속"]
[428,"부산울산","동부산","신울산명례#2 T/L","154kV 노포-정관 등 10개T/L 송전용 피뢰기 설치공사","1. 대상선로/작업내용 : 154kV 신울산-명례#2T/L/송전선로용 피뢰기 설치(No.1 ~43, 43기)","2019-06-10 08:00","2019-06-14 18:00","2019-06-10 08:00","2019-06-14 18:00","연속"]
[429,"경남","직할","신김해주촌#1 T/L","2018~19년도 경남본부 직할 송전협력회사 총액공사","345kV 신김해-신녹산#1T/L 불량애자(폴리머) 교체 안전거리 확보휴전","2019-06-03 07:00","2019-06-03 18:00","2019-06-03 07:00","2019-06-03 18:00","당일"]
[430,"경남","직할","신김해주촌#2 T/L","주촌, 신김해S/S 154kV 신김해-주촌#2T/L CB 장기미동작 점검","주촌, 신김해S/S 154kV 신김해-주촌#2T/L CB 장기미동작 점검","2019-06-13 09:00","2019-06-13 18:00","2019-06-13 09:00","2019-06-13 18:00","당일"]
[431,"경남","직할","주촌삼계#1 T/L","주촌S/S 154kV 주촌-삼계#1T/L CB 장기미동작 점검","주촌S/S 154kV 주촌-삼계#1T/L CB 장기미동작 점검","2019-06-25 09:00","2019-06-25 18:00","2019-06-25 09:00","2019-06-25 18:00","당일"]
[432,"경남","직할","주촌삼계#2 T/L","주촌S/S 154kV 주촌-삼계#2T/L CB 장기미동작 점검","주촌S/S 154kV 주촌-삼계#2T/L CB 장기미동작 점검","2019-06-26 09:00","2019-06-26 18:00","2019-06-26 09:00","2019-06-26 18:00","당일"]
[433,"경남","진주","하동개양#1 T/L","개양S/S 하동-개양#1T/L CB(637) 정밀점검","개양S/S 하동-개양#1T/L CB(637) 정밀점검","2019-06-06 09:00","2019-06-09 18:00","취소","취소","연속"]
[434,"경남","진주","하동개양#2 T/L","개양S/S 하동-개양#2T/L CB(627) 조작시험","개양S/S 하동-개양#2T/L CB(627) 조작시험","2019-06-01 09:30","2019-06-01 14:00","2019-06-01 09:30","2019-06-01 14:00","당일"]
[435,"경남","진주","진주개양#2 T/L","개양S/S 진주-개양#2T/L(617)조작시험","개양S/S 진주-개양#2T/L(617)조작시험 [병행] 진주S/S 진주-개양#2T/L(627)조작시험","2019-06-03 10:00","2019-06-03 17:00","2019-06-03 10:00","2019-06-03 17:00","당일"]
[436,"경남","진주","사천개양#1 T/L","개양S/S 하동-개양#1T/L CB(637) 정밀점검","개양S/S 하동-개양#1T/L CB(637) 정밀점검 후 시험가압","2019-06-09 15:00","2019-06-09 18:00","취소","취소","연속"]
[437,"경남","진주","사천개양#1 T/L","개양S/S 사천-개양#1T/L CB(667) 정밀점검","개양S/S 사천-개양#1T/L CB(667) 정밀점검 사천S/S 사천-개양#1T/L CB(657) 정밀점검","2019-06-10 09:00","2019-06-14 18:00","취소","취소","연속"]
[438,"경남","진주","진주개양#1 T/L","개양S/S 사천-개양#1T/L CB(667) 정밀점검","개양S/S 사천-개양#1T/L CB(667) 정밀점검 후 시험가압","2019-06-12 15:00","2019-06-12 18:00","취소","취소","연속"]
[439,"경남","진주","가야사봉#1 T/L","사봉S/S 가야-사봉#1T/L CB(617) 정밀점검","사봉S/S 가야-사봉#1T/L CB(617) 정밀점검","2019-06-20 09:00","2019-06-21 18:00","2019-06-12 09:00","2019-06-13 18:00","연속"]
[440,"경남","진주","사봉개양#1 T/L","사봉S/S 가야-사봉#1T/L CB(617) 정밀점검","사봉S/S 가야-사봉#1T/L CB(617) 정밀점검 후 시험가압","2019-06-21 15:00","2019-06-21 18:00","2019-06-13 15:00","2019-06-13 18:00","연속"]
[441,"경남","진주","사천개양#2 T/L","사천S/S 사천-개양#2T/L CB(687) 정밀점검","사천S/S 사천-개양#2T/L CB(687) 정밀점검","2019-06-17 09:00","2019-06-18 18:00","2019-06-10 09:00","2019-06-11 18:00","연속"]
[442,"경남","진주","삼천포사천#2 T/L","사천S/S 사천-개양#2T/L CB(687) 정밀점검","사천S/S 사천-개양#2T/L CB(687) 정밀점검 후 시험가압","2019-06-18 15:00","2019-06-18 18:00","2019-06-11 15:00","2019-06-11 18:00","당일"]
[443,"경남","진주","삼천포사천#1 T/L","사천S/S 사천-개양#1T/L CB(657) 정밀점검","사천S/S 사천-개양#1T/L CB(657) 정밀점검 정밀점검 후 시험가압","2019-06-14 15:00","2019-06-14 18:00","취소","취소","연속"]
[444,"경남","함안","신마산차룡#2 T/L","154kV 신마산-차룡T/L 정밀점검","1~47호 정밀점검","2019-06-19 09:00","2019-06-21 18:00","취소","취소","매일"]
[445,"경남","함안","신마산차룡#1 T/L","154kV 신마산-차룡T/L 정밀점검","1~47호 정밀점검","2019-06-12 09:00","2019-06-14 18:00","취소","취소","매일"]
[446,"부산울산",null,"신고리NP4호기 대기보조변압기 CB(6500,6572)","주변압기 휴전 중 대기보조변압기 휴전 후 발전소 건전성 확인","주변압기 휴전 중 대기보조변압기 휴전 후 발전소 건전성 확인","2019-06-24 16:00","2019-06-24 18:00","2019-06-24 16:00","2019-06-24 18:00","당일"]

{"sheet":"시송전설비","index":4,"n_rows":1,"n_cols":17,"rows_kept":1,"cut":false,"hidden":true,"merged":[[0,16,0,21]]}
["1차\n사업소","2차\n사업소","설비명",{"$nulls":8},"연간\n반영","비고","Key-point","시송전설비 여부","찾는함수","=IF(ISERROR(VLOOKUP(D5,시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D5,시송전설비!$C$2:$O$130,13,0))"]