{"text_format":"2","workbook":"xlsx","n_sheets":5,"sheets":["종합","765송부","345송부","154송부","시송전설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":14,"comments":2,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"종합","index":0,"n_rows":37,"n_cols":33,"rows_kept":37,"cut":false,"hidden":true,"merged":[[0,0,0,15],[7,14,7,15],[7,1,7,2],[8,1,8,2],[7,9,7,13],[7,3,7,6],[8,3,8,6],[14,14,14,15],[10,1,10,2],[11,1,11,2],[14,9,14,13],[9,1,9,2],[14,2,14,6],[11,3,11,6],[10,3,10,6],[9,3,9,6]]}
[{"$f":"\"'19년 \"&R15&\"월 휴전심의 결과\"","v":"'19년 7월 휴전심의 결과"}]
[]
[]
[]
[]
[]
["◎ 전체 심의결과"]
["전   압","신 청",null,"채 택",null,null,null,"일정\n조정","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)"]
["765kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B9-I9","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J9,L9,N9)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O9/B9)","v":{"$error":"#REF!"}}]
["345kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B10-I10","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J10,L10,N10)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O10/B10)","v":{"$error":"#REF!"}}]
["154kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B11-I11","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J11,L11,N11)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O11/B11)","v":{"$error":"#REF!"}}]
["계",{"$f":"SUM(B9:B11)","v":{"$error":"#REF!"}},null,{"$f":"SUM(D9:D11)","v":{"$error":"#REF!"}},null,null,null,{"$f":"SUM(H9:H11)","v":{"$error":"#REF!"}},{"$f":"SUM(J12,L12,N12)","v":{"$error":"#REF!"}},{"$f":"SUM(J9:J11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(L9:L11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(N9:N11)","v":{"$error":"#REF!"}},{"$f":"SUM(O9:O11)","v":{"$error":"#REF!"}},{"$f":"(O12/B12)","v":{"$error":"#REF!"}}]
[]
["◎ 본부별 심의결과",{"$nulls":16},"월"]
["사업소","신 청","(765/345/154)",{"$nulls":4},"채 택","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)",null,null,7]
["서   울",{"$f":"SUM(C16:G16)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},{"$f":"B16-I16","v":{"$error":"#REF!"}},{"$f":"SUM(J16,L16,N16)","v":{"$error":"#REF!"}},{"$f":"SUM(S16:U16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W16:Y16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA16:AC16)","v":{"$error":"#REF!"}},{"$f":"SUM(AE16:AG16)","v":{"$error":"#REF!"}},{"$f":"(O16/B16)","v":{"$error":"#REF!"}},null,"서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}}]
["남서울",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$f":"SUM(J17,L17,N17)","v":{"$error":"#REF!"}},{"$f":"SUM(S17:U17)","v":{"$error":"#REF!"}},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"남서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}}]
["인   천",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"인천",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}}]
["경기북부",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기북부",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}}]
["경   기",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}}]
["강   원",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"강원",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}}]
["충   북",{"$f":"SUM(C22:G22)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"충북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}}]
["대전충남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"대전충남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}}]
["전   북",{"$f":"SUM(C24:G24)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"전북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}}]
["광주전남",{"$f":"SUM(C25:G25)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"광주전남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}}]
["대구",{"$f":"SUM(C26:G26)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},{"$f":"B26-I26","v":{"$error":"#REF!"}},{"$f":"SUM(J26,L26,N26)","v":{"$error":"#REF!"}},{"$f":"SUM(S26:U26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W26:Y26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA26:AC26)","v":{"$error":"#REF!"}},{"$f":"SUM(AE26:AG26)","v":{"$error":"#REF!"}},{"$f":"(O26/B26)","v":{"$error":"#REF!"}},null,"대구",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}}]
["경북",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}}]
["부산울산",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"부산울산",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}}]
["경   남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$f":"SUM(W29:Y29)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA29:AC29)","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},null,"경남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}}]
["제   주",{"$f":"SUM(C30:G30)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$f":"(O30/B30)","v":{"$error":"#REF!"}},null,"제주",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}}]
[]
[" 붙임 :  1. 집중심의내역 1부"]
[" 붙임 :  전압별 검토서 1부. 끝."]
[]
[null,{"$f":"SUM(B16:B30)","v":{"$error":"#REF!"}},{"$f":"SUM(C16:C30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(E16:E30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(G16:G30)","v":{"$error":"#REF!"}},{"$f":"SUM(H16:H30)","v":{"$error":"#REF!"}},{"$f":"SUM(I16:I30)","v":{"$error":"#REF!"}},{"$f":"SUM(J16:J30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(L16:L30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(N16:N30)","v":{"$error":"#REF!"}},{"$f":"SUM(O16:O30)","v":{"$error":"#REF!"}}]
[{"$f":"COUNTIF(B36:N36,\"NO\")","v":0},{"$f":"IF(B35=B12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(C35=B9,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(E35=B10,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(G35=B11,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(H35=D12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(I35=I12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(J35=J12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(L35=L12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(N35=N12,\"\",\"NO\")","v":{"$error":"#REF!"}}]
[{"$f":"IF(A36>=1,\"틀린곳\",\"\")","v":""},{"$f":"IF(B36=\"NO\",\"총계\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C36=\"NO\",\"765\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(D36=\"NO\",\"총계\",\"\")","v":""},{"$f":"IF(E36=\"NO\",\"345\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(G36=\"NO\",\"154\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(H36=\"NO\",\"채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(I36=\"NO\",\"불채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(J36=\"NO\",\"병행\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(L36=\"NO\",\"취소\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(N36=\"NO\",\"연기\",\"\")","v":{"$error":"#REF!"}}]

{"sheet":"765송부","index":1,"n_rows":12,"n_cols":17,"rows_kept":12,"cut":false,"hidden":false,"merged":[[2,16,3,16],[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 7월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부","계통안정 사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백신가평#2 T/L","18~19년 변전전문회사 총액공사","신태백S/S 8671, 8600CB 조작시험","2019-07-04 10:00","2019-07-04 18:00","취소","취소","당일"]
[2,"강원","태백","신태백신가평#1 T/L","18~19년 변전전문회사 총액공사","신태백S/S 8571, 8500CB 조작시험","2019-07-03 10:00","2019-07-03 18:00","취소","취소","당일"]
[3,"강원","태백","신태백신한울#1 T/L","18~19년 변전전문회사 총액공사","신태백S/S 8471, 8400CB 조작시험","2019-07-02 10:00","2019-07-02 18:00","취소","취소","당일"]
[4,"강원","태백","신태백신한울#2 T/L","18~19년 변전전문회사 총액공사","신태백S/S 8371, 8300CB 조작시험","2019-07-01 10:00","2019-07-01 18:00","취소","취소","당일"]
[5,"강원","태백","신태백신가평#2 T/L","345kV 신영주, 신제천 TCSC 설치사업","345kV 신영주, 신제천 TCSC 설치공사\n- TCSC 제어용 신호 구성을 위한 SPS 설치(신태백,신제천,신영주S/S)\n- 접점 및 보호계전기 동작 관련 연동시험","2019-07-16 09:00","2019-07-16 18:00","취소","취소","당일"]
[6,"강원","태백","신태백신가평#1 T/L","345kV 신영주, 신제천 TCSC 설치사업","345kV 신영주, 신제천 TCSC 설치공사\n- TCSC 제어용 신호 구성을 위한 SPS 설치(신태백,신제천,신영주S/S)\n- 접점 및 보호계전기 동작 관련 연동시험","2019-07-15 09:00","2019-07-15 18:00","취소","취소","당일"]
[7,"부산울산","동부산","신고리S/S #1 M.Tr A-1","2019년 신고리E/C 765kV GIS 보통점검 공사","신고리E/C 8471,8400,8472 GIS 보통점검","2019-07-08 09:30","2019-07-12 18:00","2019-07-08 09:30","2019-07-12 18:00","연속"]
[8,"부산울산","동부산","북경남신고리NP#2 T/L","2019년 신고리E/C 765kV GIS 보통점검 공사","신고리E/C 8371 GIS 보통점검","2019-07-01 09:30","2019-07-03 18:00","2019-07-02 09:30","2019-07-04 18:00","연속"]

{"sheet":"345송부","index":2,"n_rows":99,"n_cols":17,"rows_kept":99,"cut":false,"hidden":false,"merged":[[2,16,3,16],[2,15,3,15],[2,14,3,14],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 7월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부","계통안정 사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","동서울","동서울S/S SVC M.Tr CB(7771,7700)","SVC 정기점검","SVC 정기점검","2019-07-08 09:00","2019-07-09 18:00","2019-07-04 09:00","2019-07-05 18:00","연속"]
[2,"남서울","동서울","동서울S/S #2 M.Tr A","#2M.Tr 3차측 접속부 과열개소 보수 및 1,2차 GIS 점검","345kV #2M.Tr 3차측 접속부 과열개소 보수 1차 GIS 보통점검, 2차 GCB 하자점검 등","2019-07-03 09:00","2019-07-04 18:00","2019-07-03 09:00","2019-07-04 18:00","연속"]
[3,"남서울","동서울","동서울S/S #1 M.Tr A","#1M.Tr 3차측 접속부 과열개소 보수 및 1,2차 GIS 점검","345kV #1M.Tr 3차측 접속부 과열개소 보수 1차 GIS 조작시험 및 보통점검, 2차 GCB 초기점검 등","2019-07-01 09:00","2019-07-02 18:00","2019-07-01 09:00","2019-07-02 18:00","연속"]
[4,"남서울","직할","영등포S/S 345kV #2 Sh.R","362kV GIS 보통점검","362kV GIS 보통점검","2019-07-01 10:00","2019-07-01 18:00","2019-07-02 10:00","2019-07-02 18:00","당일"]
[5,"남서울","직할","영등포S/S 345kV #1 Sh.R","362kV GIS 보통점검","362kV GIS 보통점검","2019-07-01 10:00","2019-07-01 18:00","2019-07-01 10:00","2019-07-01 18:00","당일"]
[6,"인천","인천","서인천C/C 345kV #1 Sh.R","서인천C/C 7379GIS 하자점검","서인천C/C 7379GIS 하자점검","2019-07-02 09:00","2019-07-02 18:00","2019-07-02 09:00","2019-07-02 18:00","당일"]
[7,"인천","인천","신인천C/C 345kV #76-#77 SEC CB (76-77-0_)","신인천C/C 76-77-0 GIS 하자점검","신인천C/C 76-77-0 GIS 하자점검","2019-07-05 09:00","2019-07-05 18:00","2019-07-05 09:00","2019-07-05 18:00","당일"]
[8,"인천","인천","신인천C/C 345kV 4MT101 CB A (7772_A)","신인천C/C 7772GIS 조작시험","신인천C/C 7772GIS 조작시험","2019-07-03 09:00","2019-07-03 13:00","2019-07-03 09:00","2019-07-03 13:00","당일"]
[9,"인천","인천","신인천C/C 345kV #70-#71 SEC CB (70-71-0_)","신인천C/C 70-71-0 GIS 조작시험","신인천C/C 70-71-0 GIS 조작시험","2019-07-04 13:00","2019-07-04 18:00","2019-07-04 13:00","2019-07-04 18:00","당일"]
[10,"경기북부","고양","신파주S/S SVC M.Tr CB(7771,7700)","345kV 신파주S/S SVC 냉각설비 보통점검 - 변전총액공사","-SVC 냉각설비 보통점검 - 20kV 차단기 초기점검 - FC7 밸런싱 작업 시행","2019-07-01 10:00","2019-07-04 18:00","2019-07-01 10:00","2019-07-04 18:00","연속"]
[11,"경기북부","구리","미금S/S 345kV #6 Sh.R","19년 구리전력지사 345kV GIS정밀점검","19년 구리전력지사 345kV GIS정밀점검 - 7679GIS 정밀점검","2019-07-01 09:00","2019-07-05 18:00","2019-07-01 09:00","2019-07-05 18:00","연속"]
[12,"경기북부","구리","신포천S/S #3 M.TR A","신포천S/S 345kV #3M.Tr B상 WTI 교체","신포천S/S 345kV #3M.Tr B상 WTI 교체","2019-07-09 09:00","2019-07-09 18:00","2019-07-09 09:00","2019-07-09 18:00","당일"]
[13,"경기북부","구리","신포천S/S #1 M.TR A","신포천S/S 345kV #1M.Tr A상 WTI 교체","신포천S/S 345kV #1M.Tr A상 WTI 교체","2019-07-08 09:00","2019-07-08 18:00","2019-07-08 09:00","2019-07-08 18:00","당일"]
[14,"경기북부","직할","양주S/S #3 M.Tr A","양주변전소 옥외철구 GIS화 공사","가공지선 설치","2019-07-04 09:00","2019-07-04 18:00","2019-07-04 09:00","2019-07-04 18:00","당일"]
[15,"경기북부","직할","양주S/S 345kV #6 Sh.R","양주변전소 옥외철구 GIS화 공사","가공지선 설치","2019-07-04 09:00","2019-07-04 18:00","2019-07-04 09:00","2019-07-04 18:00","당일"]
[16,"경기북부","직할","양주S/S #4 M.Tr A","양주S/S 옥외철구 GIS화 전력구공사","양주S/S 345kV #4 M.Tr A 인출측 전력구공사","2019-07-08 09:00","2019-07-10 18:00","2019-07-08 09:00","2019-07-10 18:00","연속"]
[17,"경기북부","직할","양주S/S #2 M.Tr A","양주변전소 옥외철구 GIS화 공사","가공지선 설치","2019-07-05 09:00","2019-07-05 18:00","2019-07-05 09:00","2019-07-05 18:00","당일"]
[18,"경기북부","구리","미금S/S STATCOM M.Tr CB(7972,7900)","미금S/S 감시제어설비 교체공사","미금S/S 노후 모자익반 교체","2019-07-08 09:00","2019-07-12 18:00","2019-07-08 09:00","2019-07-12 18:00","연속"]
[19,"경기북부","구리","미금S/S 345kV #4 Sh.R","미금S/S 감시제어설비 교체공사","미금S/S 노후 모자익반 교체","2019-07-15 09:00","2019-07-19 18:00","2019-07-15 09:00","2019-07-19 18:00","연속"]
[20,"경기","성남","서안성S/S 345kV #1 BUS","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ71Bay #1BUS 연결 ㅇ 기타 부대공사 x 1식","2019-07-02 09:00","2019-07-05 09:00","2019-07-05 09:00","2019-07-08 09:00","연속"]
[21,"경기","성남","서안성S/S 345kV #1 BUS","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ무부하 가압관련 BUS 휴전","2019-07-08 09:00","2019-07-09 09:00","2019-07-08 09:00","2019-07-09 09:00","연속"]
[22,"경기","성남","신안성서안성#1 T/L","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ71Bay 무부하 가압용 선로","2019-07-08 09:00","2019-07-09 09:00","2019-07-08 09:00","2019-07-09 09:00","연속"]
[23,"경기","성남","서안성S/S 345kV #2 BUS","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ71Bay #2BUS 연결 및 무부하 가압 ㅇ 기타 부대공사 x 1식","2019-07-05 09:00","2019-07-08 09:00","2019-07-02 09:00","2019-07-05 09:00","연속"]
[24,"경기","성남","신성남S/S #1 M.Tr A","1차,2차 GIS 조작시험","1차 7100,7172 2차 6144 조작시험","2019-07-01 09:00","2019-07-01 18:00","2019-07-01 09:00","2019-07-01 18:00","당일"]
[25,"경기","성남","신안성S/S 345kV 신안성-신용인#2T/L GIS","362kV GIS 정밀점검공사","362kV GIS 정밀점검공사","2019-07-08 09:00","2019-07-11 18:00","2019-07-08 09:00","2019-07-11 18:00","당일"]
[26,"경기","성남","신용인S/S 신용인-삼성T/L GIS","7671 GIS 하자점검","7671 GIS 하자점검","2019-07-12 14:00","2019-07-12 18:00","2019-07-12 14:00","2019-07-12 18:00","당일"]
[27,"경기","성남","신용인S/S #3 M.Tr A","누유 하자보수","- #3M.Tr 1차,3차LA 대체 - 누유 하자보수 - 2차 GIS 보통","2019-07-05 09:00","2019-07-05 18:00","2019-07-05 09:00","2019-07-05 18:00","당일"]
[28,"경기","성남","신용인S/S 345kV 신용인삼성T/L-TIE GIS","7600 GIS 하자점검","7600 GIS 하자점검","2019-07-12 09:00","2019-07-12 14:00","2019-07-12 09:00","2019-07-12 14:00","당일"]
[29,"경기","직할","화성평택T/P#1 T/L","화성S/S 362kV GIS 용량대체공사","O. 362kV (63kA,6300A) x 30대 교체 O. 화성-평택TP #1T/L 77BAY -> 7BBay 이설","2019-07-08 09:00","2019-08-09 18:00","취소","취소","연속"]
[30,"경기","직할","화성신안산 T/L","화성S/S 362kV GIS 용량대체공사","O. 362kV (63kA,6300A) x 30대 교체공사 O. 화성-신안산T/L 이용 7B BAY #71BUS 무부하 가압","2019-07-04 11:00","2019-07-05 11:00","취소","취소","연속"]
[31,"경기","직할","화성S/S 345kV #71 BUS","345kV 화성S/S GIS 용량대체 및 SW 증설공사","O. 362kV GIS(63kA,6000A) x 30대 설치 O. 인출변경용 7B 임시BAY #71BUS측 연결","2019-07-01 10:00","2019-07-05 18:00","취소","취소","연속"]
[32,"경기","직할","화성S/S 345kV #2 CLR 75BUS GIS(7577)","345kV 화성S/S GIS 용량대체 및 SW 증설공사","O. 362kV GIS(63kA,6000A) x 30대 설치 O. #2CLR B상 기둥 재설치","2019-07-01 09:00","2019-07-31 18:00","취소","취소","연속"]
[33,"경기","직할","화성S/S 345kV #2 CLR 76BUS GIS","345kV 화성S/S GIS 용량대체 및 SW 증설공사","O. 362kV GIS(63kA,6000A) x 30대 설치 O. #2CLR B상 기둥 재설치","2019-07-01 09:00","2019-07-31 18:00","취소","취소","연속"]
[34,"경기","군포","서서울#2신시흥#1T/L","서서울2S/S 362kV GIS DS 부분방전 발생 관련 GIS 내부점검","서서울2S/S 362kV GIS DS 부분방전 발생 관련 GIS 내부점검 - 7D02 DS","2019-07-01 09:00","2019-07-03 18:00","2019-07-01 09:00","2019-07-03 18:00","연속"]
[35,"강원","강릉","신양양S/S #3 M.Tr A","YPP제 보호계전기 성능개선","1. #3M.Tr 보호배전반 성능개선","2019-07-09 10:30","2019-07-09 18:00","2019-07-09 10:30","2019-07-09 18:00","당일"]
[36,"강원","동해","동해S/S #2 M.Tr A","2019년 동해P/O 변전협력회사 총액공사","1. LA 보통점검 2. PT 보통점검 3. 장기미동작차단기 조작시험 4. 과열개소 보수","2019-07-02 09:30","2019-07-04 18:00","2019-07-02 09:30","2019-07-04 18:00","매일"]
[37,"강원","동해","삼척G/P #3 Tie-Tr","YPP제 보호계전기 성능개선","1. #3M.Tr 보호배전반 성능개선","2019-07-11 10:00","2019-07-11 18:00","2019-07-11 10:00","2019-07-11 18:00","당일"]
[38,"강원","동해","삼척G/P #2 Tie-Tr","YPP제 보호계전기 성능개선","1. #2M.Tr 보호배전반 성능개선","2019-07-10 10:30","2019-07-10 18:00","2019-07-10 10:30","2019-07-10 18:00","당일"]
[39,"충북","충주","신제천동해#2 T/L","345kV 신제천S/S TCSC 설치공사","345kV 신제천S/S TCSC 설치공사 - TCSC 설비연결 및 제작사(ABB) 부하시험","2019-07-08 09:00","2019-07-12 18:00","취소","취소","연속"]
[40,"충북","충주","신제천동해#1 T/L","345kV 신제천S/S TCSC 설치공사","345kV 신제천S/S TCSC 설치공사 - TCSC 설비연결 및 제작사(ABB) 부하시험","2019-07-01 09:00","2019-07-05 18:00","취소","취소","연속"]
[41,"충북","충주","신제천S/S #3 M.Tr A","18-19년 직할 변전정비 총액공사","#3M.Tr 기계적보호장치(96D) 교체 및 시험. 1.2차 GIS 보통점검. #12Sh.R 초기점검. 3차 VCB 초기점검.","2019-07-01 09:00","2019-07-03 18:00","2019-07-01 09:00","2019-07-03 18:00","연속"]
[42,"대전충남","아산","신온양S/S 345kV 신온양-서서울#2T/L CB A (7771)","신온양S/S 345kV 신온양-서서울#2T/L 7771 GIS 보통점검","○신온양S/S 345kV 신온양-서서울#2T/L 7771 GIS 보통점검","2019-07-04 09:00","2019-07-04 18:00","2019-07-04 09:00","2019-07-04 18:00","당일"]
[43,"대전충남","아산","신온양S/S CB (7800)","신온양S/S 345kV 7800 TIE GIS 보통점검","○신온양S/S 345kV 7800 TIE GIS 보통점검","2019-07-03 09:00","2019-07-03 18:00","2019-07-03 09:00","2019-07-03 18:00","당일"]
[44,"대전충남","아산","신온양S/S 345kV 신온양-서서울#1T/L CB A (7871)","신온양S/S 345kV 신온양-서서울#1T/L 7871 GIS 보통점검","○신온양S/S 345kV 신온양-서서울#1T/L 7871 GIS 보통점검","2019-07-05 09:00","2019-07-05 18:00","2019-07-05 09:00","2019-07-05 18:00","당일"]
[45,"대전충남","아산","신서산아산#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","154kV 합덕-송악T/L 피뢰기 설치공사(26기분) [안전이격거리]345k 신서산-아산T/L 휴전","2019-07-06 07:00","2019-07-07 18:00","취소","취소","매일"]
[46,"대전충남","청양","청양보령화력#1 T/L","보령화력 제2발전소 접속설비(362kV GIS) 교체공사(4차)","보령화력 제2발전소 접속설비(362kV GIS) 교체공사(4차) - 71,76BUS 교체","2019-07-08 09:00","2019-07-11 18:00","취소","취소","연속"]
[47,"전북","김제","신김제S/S #1 M.Tr A","관내S/S 154, 345kV GIS 조작시험","관내S/S 154, 345kV GIS 조작시험","2019-07-05 10:00","2019-07-05 18:00","2019-07-05 10:00","2019-07-05 18:00","당일"]
[48,"전북","김제","신김제S/S #2 M.Tr A","관내S/S 154, 345kV GIS 조작시험","관내S/S 154, 345kV GIS 조작시험","2019-07-11 10:00","2019-07-11 18:00","2019-07-11 10:00","2019-07-11 18:00","당일"]
[49,"전북","김제","신김제S/S 신김제한빛NP#1T/L CB(7371,7300)","관내S/S 345kV 신김제-한빛#1T/L GIS 조작시험 (7371,7300 CB 각각 진행)","관내S/S 345kV 신김제-한빛#1T/L GIS 조작시험 (7371,7300 CB 각각 진행)","2019-07-08 10:00","2019-07-08 18:00","2019-07-08 10:00","2019-07-08 18:00","당일"]
[50,"전북","군산","군산S/S #1 M.Tr ","유호전기(제) 345kV 변압기 보호배전반 성능개선","본사 성능개선 지시관련 인출 DS 접점관련 회로 보완","2019-07-03 10:00","2019-07-03 18:00","2019-07-03 10:00","2019-07-03 18:00","당일"]
[51,"전북","군산","군산S/S #3 M.Tr ","유호전기(제) 345kV 변압기 보호배전반 성능개선","본사 성능개선 지시관련 인출 DS 접점관련 회로 보완","2019-07-04 10:00","2019-07-04 18:00","2019-07-04 10:00","2019-07-04 18:00","당일"]
[52,"전북","군산","새만금S/S #2 M.Tr ","유호전기(제) 345kV 변압기 보호배전반 성능개선","본사 성능개선 지시관련 인출 DS 접점관련 회로 보완","2019-07-09 10:00","2019-07-09 18:00","2019-07-09 10:00","2019-07-09 18:00","당일"]
[53,"전북","군산","새만금S/S #3 M.Tr ","유호전기(제) 345kV 변압기 보호배전반 성능개선","본사 성능개선 지시관련 인출 DS 접점관련 회로 보완","2019-07-11 10:00","2019-07-11 18:00","2019-07-11 10:00","2019-07-11 18:00","당일"]
[54,"전북","직할","신옥천무주양수 T/L","ABB(제) 345kV 송전선로 보호배전반 성능개선","재폐로 관련 보호협조 시간 개선","2019-07-12 10:30","2019-07-12 18:00","2019-07-12 10:30","2019-07-12 18:00","당일"]
[55,"광주전남","강진","신강진S/S #1 M.Tr A","신강진S/S 345kV #1M.Tr 및 OLTC 정밀점검공사","345kV M.Tr 및 OLTC 정밀점검 : 3대(단상x1BANK) 누유보수 및 기타 부속품 교체 : 1식","2019-07-01 09:00","2019-07-12 18:00","2019-07-01 09:00","2019-07-12 18:00","연속"]
[56,"대구","경산","신경산S/S 345kV #75 BUS","신경산S/S 362kV GIS 대체공사(72BAY)","○ 모선인터록시험 ○ 무부하가압(7/13 18:00 예정) ○ 실부하 위상측정","2019-07-13 09:00","2019-07-15 09:00","2019-07-19 09:00","2019-07-20 18:00","연속"]
[57,"대구","경산","신경산S/S 345kV #70 BUS","신경산S/S 362kV GIS 대체공사(72BAY)","○ 모선 인터록시험 ○ 무부하가압(7/11 18:00 예정) ○ 실부하 위상측정","2019-07-11 09:00","2019-07-13 09:00","2019-07-17 09:00","2019-07-19 09:00","연속"]
[58,"대구","달성","대구S/S #1 M.Tr A","M.Tr 보통점검 및 GIS 보통점검","M.Tr 보통점검 및 GIS 보통점검","2019-07-08 09:00","2019-07-08 18:00","취소","취소","당일"]
[59,"대구","포항","신월성N/P 345kV #2 SA.TR 1차 CB A (7272-A)","신월성 7272 GIS 보통점검","신월성 7272 GIS 보통점검","2019-07-31 09:00","2019-07-31 18:00","취소","취소","당일"]
[60,"대구","포항","신포항신월성NP#4 T/L","345kV 신포항-신월성 등 2개 T/L 스페이서 댐퍼 교체 공사","스페이서 댐퍼 교체 no.4~30","2019-07-15 09:00","2019-07-19 18:00","2019-07-15 09:00","2019-07-19 18:00","연속"]
[61,"대구","포항","신월성N/P 345kV #2 M.Tr 1차 CB A (7172-A)","신월성 7172 GIS 보통점검","신월성 7172 GIS 보통점검","2019-07-17 09:00","2019-07-17 18:00","2019-07-17 09:00","2019-07-17 18:00","당일"]
[62,"대구","포항","월성연락#2 T/L","월성-연락#2T/L 휴전","신월성 7200,7271 GIS 보통점검 월성 7871 조작시험 LCR, DS 보통점검","2019-07-29 09:00","2019-07-30 18:00","취소","취소","연속"]
[63,"대구","포항","신포항북대구 T/L","신포항 72BF반 교체작업","신포항 72BF반 교체작업","2019-07-15 09:00","2019-07-19 18:00","취소","취소","연속"]
[64,"대구","포항","월성2N/P 345kV F1-#2 SS TR 1차 TIE CB A (7400-A)","월성S/Y 7400 GIS 보통점검","월성S/Y 7400 GIS 보통점검","2019-07-04 09:00","2019-07-04 18:00","2019-07-02 09:00","2019-07-02 18:00","당일"]
[65,"대구","포항","울주월성NP#2 T/L","345kV 신포항-신월성 등 2개 T/L 스페이서 댐퍼 교체 공사","스페이서 댐퍼 교체 no.4~30","2019-07-15 08:00","2019-07-19 18:00","2019-07-15 08:00","2019-07-19 18:00","연속"]
[66,"대구","포항","월성2N/P 345kV #2 SS TR 1차 CB A (7472-A)","월성S/Y 7472 GIS 보통점검","월성S/Y 7472 GIS 보통점검","2019-07-04 09:00","2019-07-04 18:00","2019-07-03 09:00","2019-07-03 18:00","당일"]
[67,"경북","영주","신영주S/S #3 M.Tr A","2018-19년도 영주전력지사 변전협력업체 총액공사","신영주S/S #3M.Tr 2차 CB 조작시험","2019-07-01 09:00","2019-07-01 18:00","2019-07-01 09:00","2019-07-01 18:00","당일"]
[68,"경북","영주","신영주S/S #2 M.Tr A","2018-19년도 영주전력지사 변전협력업체 총액공사","신영주S/S #2M.Tr 2차 CB 조작시험","2019-07-02 09:00","2019-07-02 18:00","2019-07-02 09:00","2019-07-02 18:00","당일"]
[69,"경북","영주","신영주한울NP2#1 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #1T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #1T/L GIB용 보호반 설치","2019-07-15 10:00","2019-07-19 14:00","취소","취소","연속"]
[70,"경북","영주","신영주한울NP2#2 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #2T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #2T/L GIB용 보호반 설치","2019-07-22 10:00","2019-07-26 14:00","취소","취소","연속"]
[71,"부산울산","동부산","신양산S/S #1 M.Tr","신양산E/C 362kV GIS 공기압력계 교체","신양산E/C 362kV GIS 공기압력계 교체(#1M.Tr)","2019-07-03 09:30","2019-07-03 17:00","2019-07-03 09:30","2019-07-03 17:00","당일"]
[72,"부산울산","울산","동울산월성NP#1 T/L","YPP제 345kV 송전선로 보호반 성능개선작업","- YPP제 345kV Line DS FAIL 성능개선","2019-07-02 09:00","2019-07-02 18:00","2019-07-06 09:00","2019-07-06 18:00","당일"]
[73,"부산울산","울산","울주고리NP#1 T/L","고리NP S/Y 362kV GIS 가스블럭 교체","고리NP S/Y 362kV GIS 가스블럭 교체(울주-고리#1T/L)","2019-07-03 09:30","2019-07-03 18:00","2019-07-05 09:00","2019-07-05 14:00","당일"]
[74,"부산울산","울산","울주고리NP#2 T/L","고리NP S/Y 362kV GIS 가스블럭 교체","고리NP S/Y 362kV GIS 가스블럭 교체(울주-고리#2T/L","2019-07-04 09:30","2019-07-04 18:00","2019-07-05 14:00","2019-07-05 18:00","당일"]
[75,"경남","진주","산청P/P 345kV 의령-산청PP#1T/L-#2 M.Tr 1 (7271)","산청P/P 의령-산청PP#1T/L-#2M.Tr 1차(7271) 정밀점검","산청P/P 의령-산청PP#1T/L-#2M.Tr 1차 CB(7271) 정밀점검","2019-07-01 09:00","2019-07-04 18:00","2019-07-01 09:00","2019-07-04 18:00","연속"]
[76,"경남","진주","의령S/S #1 M.Tr A","의령S/S #1M.Tr 2차 CB(6133) 정밀점검","의령S/S #1M.Tr 2차 CB(6133) 정밀점검","2019-07-05 09:00","2019-07-06 18:00","2019-07-04 09:00","2019-07-06 18:00","연속"]
[77,"경남","통영","창원삼천포TP#2 T/L","삼천포,신고성S/S 용량부족차단기 대체공사","345kV 창원-삼천포화력#2T/L 인출변경(구GIS-&gt신GIS)","2019-07-01 09:00","2019-07-12 18:00","2019-07-01 09:00","2019-07-12 18:00","연속"]
[78,"경남","통영","삼천포T/P 345kV 삼천포-TIE#2T/L CB A (75571_A)","삼천포,신고성S/S 용량부족차단기 대체공사","창원-삼천포화력#2T/L 인출철구 설치를 위한 안전이격거리 확보(7571)","2019-07-06 09:00","2019-07-06 18:00","2019-07-06 09:00","2019-07-06 18:00","당일"]
[79,"경남","통영","삼천포T/P CB (75000_A)","삼천포,신고성S/S 용량부족차단기 대체공사","창원-삼천포화력#2T/L 인출철구 설치를 위한 안전이격거리 확보 (7500)","2019-07-06 09:00","2019-07-06 18:00","2019-07-06 09:00","2019-07-06 18:00","당일"]
[80,"경남","통영","(신)신고성S/S 345kV TIE#2T/L-G4호기 CB (7400_A)","삼천포,신고성S/S 용량부족차단기 대체공사","창원-삼천포화력#2T/L 인출철구 설치를 위한 안전이격거리 확보(7400)","2019-07-06 09:00","2019-07-06 18:00","2019-07-06 09:00","2019-07-06 18:00","당일"]
[81,"경남","통영","(신)신고성S/S 345kV 삼천포-TIE#2T/L CB (7472_B)","삼천포,신고성S/S 용량부족차단기 대체공사","창원-삼천포화력#2T/L 인출철구 설치를 위한 안전이격거리 확보 (7472)","2019-07-06 09:00","2019-07-06 18:00","2019-07-06 09:00","2019-07-06 18:00","당일"]
[82,"경남","함안","북경남S/S #5 Sh.R","북경남S/S #5Sh.R 보통점검 및 GIS 보통점검","북경남S/S #5Sh.R 보통점검 및 GIS(7779,7771,7700) 보통점검","2019-07-01 09:30","2019-07-02 17:30","2019-07-01 09:30","2019-07-02 17:30","연속"]
[83,"경남","함안","북경남S/S 북경남-고령#2T/L CB (7772)","북경남S/S 345kV 북경남-고령#2T/L GIS 7772 보통점검","북경남S/S 345kV 북경남-고령#2T/L GIS 7772 보통점검","2019-07-03 09:30","2019-07-03 17:30","2019-07-03 09:30","2019-07-03 17:30","당일"]
[84,"경남","함안","북경남S/S 북경남-대구#2T/L CB (7572)","북경남 345kV 북경남-대구#2T/L GIS 7572 보통점검","북경남S/S 345kV 북경남-대구#2T/L GIS 7572 보통점검","2019-07-09 09:30","2019-07-09 17:30","2019-07-09 09:30","2019-07-09 17:30","당일"]
[85,"경남","함안","북경남S/S #70 BUS-대구#2T/L TIE CB (7500)","북경남 345kV 북경남-대구#2T/L GIS 7500 보통점검","북경남S/S 345kV 북경남-대구#2T/L GIS 7500 보통점검","2019-07-08 09:30","2019-07-08 17:30","2019-07-08 09:30","2019-07-08 17:30","당일"]
[86,"경남","함안","북경남S/S 북경남-서대구#2T/L CB (7972)","북경남S/S 345kV 북경남-서대구#2T/L GIS 7972 보통점검","북경남S/S 345kV 북경남-서대구#2T/L GIS 7972 보통점검","2019-07-04 09:30","2019-07-04 17:30","2019-07-04 09:30","2019-07-04 17:30","당일"]
[87,"경남","함안","북경남S/S 북경남-대구#1T/L CB (7672)","북경남 345kV 북경남-대구#1T/L GIS 7672 보통점검","북경남S/S 345kV 북경남-대구#1T/L GIS 7672 보통점검","2019-07-11 09:30","2019-07-11 17:30","2019-07-11 09:30","2019-07-11 17:30","당일"]
[88,"경남","함안","북경남S/S #70 BUS-대구 #1T/L TIE CB (7600)","북경남 345kV 북경남-대구#1T/L GIS 7600 보통점검","북경남S/S 345kV 북경남-대구#1T/L GIS 7600 보통점검","2019-07-10 09:30","2019-07-10 17:30","2019-07-10 09:30","2019-07-10 17:30","당일"]
[89,"광주전남",null,"한빛6호기 주변압기 CB(7E00,7E71)","한빛6호기 12차 O/H 중 주변압기\n점검\n* 조작차단기 : CB 7E00, 7E71","○ 소내자동전원절체 시험 수행\n○ SAT 실부하 위상각 측정\n○ 갑종보호계전기 삼중화 개선 및 준공시험","2019-07-09 10:00","2019-07-09 17:00","2019-07-09 10:00","2019-07-09 17:00","연속"]
[90,"대구",null,"월성2호기 기동변압기 CB(7400,7472)","월성 2호기  제18차 계획예방정비관련 주변압기/소내용변압기 점검\n* 조작차단기 : CB7400,CB7472","- 기동용변압기 일반점검\n- 기동용변압기 보호계전기 정기시험\n   (차단기 연동시험 포함)","2019-07-01 09:00","2019-07-05 18:00","2019-07-01 09:00","2019-07-05 18:00","연속"]
[91,"대구",null,"월성2호기 주변압기 CB(7300,7372)","월성 2호기  제18차 계획예방정비관련 주변압기 CT라인점검 및 모선 보호계전기 삼중화 \n* 조작차단기 : CB7300,CB7372","- 주변압기 CT라인 점검\n- BUA 모선보호 보호계전기 삼중화","2019-07-11 09:00","2019-07-12 18:00","2019-07-11 09:00","2019-07-12 18:00","연속"]
[92,"대구",null,"월성2호기 기동변압기 CB(7400,7472)","월성 2호기  제18차 계획예방정비관련 주변압기/소내용변압기 점검\n* 조작차단기 : CB7400,CB7472","- SST->UST 소내전원절체시험","2019-07-12 18:00","2019-07-14 18:00","2019-07-12 18:00","2019-07-14 18:00","연속"]
[93,"대구",null,"월성2호기 주변압기 CB(7300,7372)","월성 2호기  제18차 계획예방정비관련 주변압기/소내용변압기 점검\n* 조작차단기 : CB7300,CB7372","- UST->SST 소내전원절체시험","2019-07-12 18:00","2019-07-14 18:00","2019-07-12 18:00","2019-07-14 18:00","연속"]
[94,"대구",null,"월성2호기 주변압기 CB(7300,7372)","월성 2호기 제16차 계획예방정비관련 소내전원절체시험\n*조작차단기 :                CB7300, CB7372","- 계통병입전 IPB링크 조립 및 계통병입 대기\n- 발전기 성능시험","2019-07-14 18:00","2019-07-19 18:00","2019-07-14 18:00","2019-07-19 18:00","연속"]
[95,"대구",null,"신월성2호기 주변압기 CB(7100,7172)","신월성2호기 3차 계획예방정비\n#2 MTR/UAT/EXTR 점검\n* 조작차단기 : CB 7100, 7172","○ MTR/UAT/EXTR 일반점검 등","2019-07-14 09:00","2019-08-05 18:00","2019-07-14 09:00","2019-08-05 18:00","연속"]

{"sheet":"154송부","index":3,"n_rows":136,"n_cols":17,"rows_kept":136,"cut":false,"hidden":false,"merged":[[95,16,98,16],[2,16,3,16],[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 7월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부","계통안정 사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S 154kV #60 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-07-11 15:30","2019-07-11 17:30","취소","취소","당일"]
[2,"서울","성동","성동S/S 154kV #60-#61 SEC GIS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-07-10 09:00","2019-07-11 17:30","취소","취소","연속"]
[3,"서울","성동","성동S/S 154kV #66 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-07-09 15:30","2019-07-09 17:30","취소","취소","당일"]
[4,"서울","성동","성동S/S 154kV #60 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-07-05 15:30","2019-07-05 17:30","2019-07-05 15:30","2019-07-05 17:30","당일"]
[5,"서울","성동","성동S/S 154kV #60-#65 BUS TIE GIS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-07-04 09:00","2019-07-05 17:30","2019-07-04 08:00","2019-07-05 17:30","연속"]
[6,"서울","성동","성동S/S 154kV #66 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-07-03 15:30","2019-07-03 17:30","2019-07-03 15:30","2019-07-03 17:30","당일"]
[7,"서울","성동","성동S/S 154kV #66 BUS","154kV 성동-왕십리E/C SW 증설공사","O 170kV GIS 50kA 2000A x 2CCT O 송전선로보호배전반(단거리) x 2면 O 기타부대설비공사 1식","2019-07-15 14:00","2019-07-16 14:00","2019-07-13 14:00","2019-07-14 14:00","연속"]
[8,"서울","성동","성동S/S 154kV #61 BUS","154kV 성동-왕십리E/C SW 증설공사","O 170kV GIS 50kA 2000A x 2CCT O 송전선로보호배전반(단거리) x 2면 O 기타부대설비공사 1식","2019-07-15 09:00","2019-07-15 14:00","2019-07-13 09:00","2019-07-13 14:00","연속"]
[9,"서울","성동","성동S/S 154kV #61-#66 BUS TIE GIS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-07-08 09:00","2019-07-09 17:30","취소","취소","연속"]
[10,"서울","성동","왕십리용두 T/L","154kV 성동-왕십리","O 170kV GIS 50kA 2000A 2CCT O 송전선로 보호배전반 2면 O 기타 부대설비","2019-07-05 09:00","2019-07-06 18:00","2019-07-05 09:00","2019-07-06 18:00","연속"]
[11,"서울","성동","왕십리용두 T/L","154kV 성동-왕십리E/C SW 증설공사","O 170kV GIS 50kA 2000A x 2CCT O 송전선로보호배전반(단거리) x 2면 O 기타부대설비공사 1식","2019-07-15 09:00","2019-07-16 14:00","취소","취소","연속"]
[12,"남서울","동서울","신장덕소#2 T/L","신장S/S 170kV 장기사용 GIS 교체공사","신장S/S 170kV 장기사용 GIS 교체공사 - #2BUS 무부하가압","2019-07-05 16:00","2019-07-06 09:00","2019-07-05 16:00","2019-07-06 09:00","연속"]
[13,"남서울","동서울","신장덕소#1 T/L","신장S/S 170kV 장기사용 GIS 교체공사","신장S/S 170kV 장기사용 GIS 교체공사","2019-07-03 09:00","2019-07-30 18:00","2019-07-03 09:00","2019-07-30 18:00","연속"]
[14,"남서울","동서울","신장덕소#2 T/L","신장S/S 170kV 장기사용 GIS 교체공사","신장S/S 170kV 장기사용 GIS 교체공사 - #1BUS 무부하가압","2019-07-18 16:00","2019-07-19 09:00","2019-07-18 16:00","2019-07-19 09:00","연속"]
[15,"남서울","영등포","마곡가양#1 T/L","154kV 마곡-가양#1T/L 접속함 과열개소 보수공사","154kV 마곡-가양#1T/L M/H#4 C상 접속함 과열개소 보수","2019-07-06 09:00","2019-07-06 18:00","2019-07-06 09:00","2019-07-06 18:00","당일"]
[16,"남서울","영등포","부천신정#1 T/L","신정S/S 154kV GIS 정밀점검공사","주회로 접촉저항 측정 보조회로, 제어회로 절연저항 측정 가스회수 및 차단기 내부점검 가스주입 및 경보시험 CT포화시험 차단기 조작시험","2019-07-01 09:00","2019-07-02 18:00","2019-07-01 09:00","2019-07-02 18:00","연속"]
[17,"남서울","영등포","부천신정#2 T/L","신정S/S 154kV GIS 정밀점검공사","주회로 접촉저항 측정 보조회로, 제어회로 절연저항 측정 가스회수 및 차단기 내부점검 가스주입 및 경보시험 CT포화시험 차단기 조작시험","2019-07-04 09:00","2019-07-05 18:00","2019-07-04 09:00","2019-07-05 18:00","연속"]
[18,"인천","시흥","북시화서시화#3 T/L","서시화S/S 북시화서시화#3T/L 정밀점검","서시화S/S 북시화서시화#3T/L 정밀점검","2019-07-01 08:30","2019-07-05 18:00","2019-07-01 08:30","2019-07-05 18:00","연속"]
[19,"인천","인천","계양북인천 T/L","북인천S/S 계양북인천T/L GIS 조작시험","북인천S/S 계양북인천T/L GIS 조작시험","2019-07-01 09:00","2019-07-01 18:00","2019-07-01 09:00","2019-07-01 18:00","당일"]
[20,"경기북부","고양","신파주문발#1 T/L","파주운정3지구 지장송전선로 지중화공사","- 공사구간 : 154kV 신파주-문발#1,2T/L J/B#1∼#6 2.012km - 선종 및 선로길이 : XLPE 2500㎟×2C 0.801km / XLPE 2000㎟(D)×2C 1.211km","2019-07-15 08:00","2019-08-29 18:00","2019-07-15 08:00","2019-08-29 18:00","연속"]
[21,"경기북부","구리","신장덕소#2 T/L","덕소E/C 옥내화공사","덕소E/C 옥내화공사 신장-덕소T/L 가압","2019-07-30 09:00","2019-07-31 18:00","2019-07-30 09:00","2019-07-31 18:00","연속"]
[22,"경기북부","구리","신장덕소#1 T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업 154kV 신장-덕소#1T/L 휴전작업으로 신설 덕소S/S 계통병입 및 부하절체","2019-07-03 09:00","2019-08-01 18:00","2019-07-03 09:00","2019-08-01 18:00","연속"]
[23,"경기북부","직할","남면백석#2 T/L","18-19년도 직할 변전정비회사 총액공사","백석s/s 154kV 백석-남면 #2 T/L 1차 GIS 개폐타임 측정","2019-07-01 09:00","2019-07-01 18:00","2019-07-01 09:00","2019-07-01 18:00","당일"]
[24,"경기북부","직할","양주금촌#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주금촌#2 T/L 인출선 측 전력구공사","2019-07-01 09:00","2019-07-02 18:00","2019-07-01 09:00","2019-07-02 18:00","연속"]
[25,"경기북부","직할","양주S/S 154kV #62 BUS","양주변전소 옥외철구 GIS화 공사","가공지선 설치","2019-07-04 09:00","2019-07-04 18:00","2019-07-04 09:00","2019-07-04 18:00","당일"]
[26,"경기북부","직할","양주고양#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주고양#2 T/L 인출측 전력구공사","2019-07-05 09:00","2019-07-06 18:00","2019-07-05 09:00","2019-07-06 18:00","연속"]
[27,"경기북부","직할","양주금촌#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주금촌#1 T/L 인출측 전력구공사","2019-07-03 09:00","2019-07-04 18:00","2019-07-03 09:00","2019-07-04 18:00","연속"]
[28,"경기북부","직할","용현도봉#2 T/L","18-19년도 직할 변전정비회사 총액공사","용현S/S 154kV 용현-도봉 #2 T/L 1차 GIS 개폐타임 측정","2019-07-03 09:00","2019-07-03 18:00","2019-07-03 09:00","2019-07-03 18:00","당일"]
[29,"경기북부","직할","용현도봉#1 T/L","18-19년도 직할 변전정비회사 총액공사","용현S/S 154kV 용현-도봉 #1 T/L 1차 GIS 개폐타임 측정","2019-07-02 09:00","2019-07-02 18:00","2019-07-02 09:00","2019-07-02 18:00","당일"]
[30,"경기","군포","관양동안양#2 T/L","'19년 군포P/O 변전정비회사 총액공사","관양S/S 관양-동안양#2T/L GIS 보통점검","2019-07-08 14:00","2019-07-08 18:00","2019-07-08 14:00","2019-07-08 18:00","당일"]
[31,"경기","군포","관양동안양#1 T/L","'19년 군포P/O 변전정비회사 총액공사","관양S/S 관양-동안양#1T/L GIS 보통점검","2019-07-08 09:00","2019-07-08 14:00","2019-07-08 09:00","2019-07-08 14:00","당일"]
[32,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-율현T/L 불량애자교체 및 안전이격휴전","7/9 - 불량애자교체 7/10 - 안전이격 휴전 (작업없음)","2019-07-09 08:00","2019-07-10 18:00","취소","취소","매일"]
[33,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-이천T/L 피뢰기 설치공사","7/9 - 안전이격 휴전 (작업없음) 7/10 - 피뢰기 설치 : 곤지암-이천, 곤지암-율현T/L 1~5호 (4회선 구간)","2019-07-09 08:00","2019-07-10 18:00","취소","취소","매일"]
[34,"경기","동부","곤지암율현#1 T/L","154kV 곤지암-율현T/L 불량애자교체","불량애자교체","2019-07-08 08:00","2019-07-08 18:00","취소","취소","당일"]
[35,"경기","동부","초월성현#2 T/L","154kV 초월-성현T/L 불량애자교체","불량애자교체","2019-07-01 08:00","2019-07-02 18:00","2019-07-01 08:00","2019-07-02 18:00","매일"]
[36,"경기","동부","곤지암초월#2 T/L","154kV 초월-성현T/L 불량애자교체","안전이격 휴전 (초월성현T/L 4회선 구간)","2019-07-02 08:00","2019-07-02 18:00","2019-07-02 08:00","2019-07-02 18:00","당일"]
[37,"경기","동부","초월성현#1 T/L","154kV 초월-성현T/L 불량애자교체","불량애자교체","2019-07-03 08:00","2019-07-05 18:00","2019-07-03 08:00","2019-07-05 18:00","매일"]
[38,"경기","동부","곤지암초월#1 T/L","154kV 곤지암-초월T/L 상간스페이서점검","상간스페이서 점검","2019-07-03 08:00","2019-07-03 18:00","2019-07-03 08:00","2019-07-03 18:00","당일"]
[39,"경기","성남","남사S/S 154kV 용인-남사#2T/L GIS","GIS 보통점검","GIS 보통점검","2019-07-04 09:00","2019-07-04 18:00","2019-07-04 09:00","2019-07-04 18:00","연속"]
[40,"경기","성남","남사S/S 154kV 용인-남사#1T/L GIS","GIS 보통점검","GIS 보통점검","2019-07-01 09:00","2019-07-01 18:00","2019-07-01 09:00","2019-07-01 18:00","연속"]
[41,"경기","성남","서안성S/S 154kV #66 BUS","154kV GIS 정밀점검공사 무부하","154kV GIS 정밀점검공사 무부하","2019-07-10 09:00","2019-07-10 18:00","취소","취소","당일"]
[42,"경기","성남","서안성S/S 154kV #61-#66 BUS TIE GIS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2019-07-15 14:00","2019-07-17 18:00","취소","취소","연속"]
[43,"경기","성남","서안성S/S 154kV #65-#66 SEC GIS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2019-07-11 14:00","2019-07-13 18:00","취소","취소","연속"]
[44,"경기","성남","서안성S/S 154kV #60-#61 SEC GIS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2019-07-01 09:00","2019-07-03 18:00","취소","취소","연속"]
[45,"경기","성남","서안성S/S 154kV 서안성-안성#2T/L GIS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2019-07-08 14:00","2019-07-10 18:00","2019-07-13 09:00","2019-07-14 18:00","연속"]
[46,"경기","성남","서안성S/S 154kV #65 BUS","154kV GIS 정밀점검공사 무부하","154kV GIS 정밀점검공사 무부하","2019-07-13 09:00","2019-07-13 18:00","취소","취소","연속"]
[47,"경기","성남","서안성S/S 154kV #61 BUS","154kV GIS 정밀점검공사 무부하","154kV GIS 정밀점검공사 무부하","2019-07-06 09:00","2019-07-06 18:00","취소","취소","연속"]
[48,"경기","성남","서안성S/S 154kV 서안성-안성#1T/L GIS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2019-07-04 09:00","2019-07-06 18:00","2019-07-06 09:00","2019-07-07 18:00","연속"]
[49,"경기","성남","서안성S/S 154kV #60 BUS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2019-07-03 09:00","2019-07-03 18:00","취소","취소","당일"]
[50,"경기","성남","신용인S/S 154kV #65-#66 SEC GIS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2019-07-10 14:00","2019-07-13 18:00","취소","취소","연속"]
[51,"경기","성남","신용인S/S 154kV #60 BUS","154kV GIS 정밀점검공사 무부하","154kV GIS 정밀점검공사 무부하","2019-07-10 09:00","2019-07-10 18:00","취소","취소","당일"]
[52,"경기","성남","신용인S/S 154kV #60-#61 SEC GIS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2019-07-08 09:00","2019-07-10 18:00","취소","취소","연속"]
[53,"경기","성남","신용인용인#2 T/L","154kV 신용인-용인#2T/L 송전선로 정밀점검","154kV 신용인-용인#2T/L(No.1~27) 송전선로 정밀점검","2019-07-08 09:00","2019-07-09 18:00","취소","취소","당일"]
[54,"경기","성남","신용인용인#1 T/L","154kV 신용인-용인#1T/L 송전선로 정밀점검","154kV 신용인-용인#1T/L(No.1~27) 송전선로 정밀점검","2019-07-02 09:00","2019-07-03 18:00","취소","취소","당일"]
[55,"경기","성남","신용인S/S 154kV #65 BUS","154kV GIS 정밀점검공사 무부하","154kV GIS 정밀점검공사 무부하","2019-07-13 09:00","2019-07-13 18:00","취소","취소","당일"]
[56,"경기","직할","서서울#2남수원 #2T/L","154kV 봉담E/C 건설공사","- 서서울#2-봉담-남수원#2T/L 전선 가선 - 서서울#2, 남수원#2T/L측 보호배전반 대체","2019-07-04 09:00","2019-07-19 18:00","2019-07-03 09:00","2019-07-18 18:00","연속"]
[57,"경기","직할","남수원발안#2 T/L","2018-2019년 송전정비회사 총액공사","154kV 서서울2-남수원#2T/L 50호 송전용 피뢰기 설치(1기) 관련 안전이격거리확보","2019-07-04 09:00","2019-07-04 12:00","2019-07-04 09:00","2019-07-04 12:00","당일"]
[58,"경기","직할","율전의왕#2 T/L","율전분기T/L 비규격EBA(종단접속함) 자기애관 교체공사","154kV 율전-의왕#2T/L 율전#1C/H 자기애관 교체작업","2019-07-01 09:00","2019-07-05 18:00","2019-07-01 09:00","2019-07-05 18:00","당일"]
[59,"경기","평택","고덕진위#2 T/L","고덕E/C 154kV SW 신규수용공사","ㅇ 무부하 가압 - 고덕-프렉스에어#1,2 T/L","2019-07-11 09:00","2019-07-12 18:00","2019-07-11 09:00","2019-07-12 18:00","연속"]
[60,"경기","평택","고덕진위#2 T/L","154kV 고덕-진위T/L 30호 지장철탑 이설공사","남사나들목 개설 관련 30호 지장이설 2기 신설, 1기 철거","2019-07-16 09:00","2019-07-19 18:00","취소","취소","연속"]
[61,"경기","평택","고덕진위#1 T/L","154kV 고덕-진위T/L 30호 지장철탑 이설공사","남사나들목 개설 관련 30호 지장이설 2기 신설, 1기 철거","2019-07-20 09:00","2019-07-23 18:00","취소","취소","연속"]
[62,"경기","평택","포승평택TP#1 T/L","154kV 포승-평택T/P #1T/L 보호반 대체 공사","평택T/P 154kV 포승-평택T/P #1T/L 보호반 대체 공사 / 포승S/S 154kV 포승-평택T/P #1T/L 보호반 대체 공사, GIS 조작시험","2019-07-01 10:00","2019-07-03 18:00","2019-07-01 10:00","2019-07-03 18:00","연속"]
[63,"강원","강릉","강릉횡계#2 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","강릉횡계#2T/L EBA PD진단센서 및 집합반 설치공사","2019-07-02 09:00","2019-07-02 18:00","2019-07-02 09:00","2019-07-02 18:00","당일"]
[64,"강원","강릉","강릉횡계#1 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","강릉횡계#1T/L EBA PD진단센서 및 집합반 설치공사","2019-07-01 09:00","2019-07-01 18:00","2019-07-01 09:00","2019-07-01 18:00","당일"]
[65,"강원","원주","홍천상남#2 T/L","2018~2019년 송전정비 협력회사 총액공사(항공표지구설치)","○ 항공표지구 설치 : 154kV 상남T/L No. 64등 10개소","2019-07-01 08:00","2019-07-03 18:00","2019-07-01 08:00","2019-07-03 18:00","매일"]
[66,"강원","원주","홍천상남#1 T/L","2018~2019년 송전정비 협력회사 총액공사(항공표지구설치)","○ 항공표지구 설치 : 154kV 상남T/L No. 64등 10개소","2019-07-04 08:00","2019-07-06 18:00","2019-07-04 08:00","2019-07-06 18:00","매일"]
[67,"강원","태백","신제천영월CC#2 T/L","19년 태백전력지사 170kV GIS 정밀점검 공사","신제천-영월CC #2T/L GIS 정밀점검","2019-07-03 10:00","2019-07-04 18:00","취소","취소","연속"]
[68,"강원","태백","신제천영월CC#1 T/L","19년 태백전력지사 170kV GIS 정밀점검 공사","신제천-영월CC #1T/L GIS 정밀점검","2019-07-01 10:00","2019-07-02 18:00","취소","취소","연속"]
[69,"충북","직할","만승S/S 154kV #60-#65 BUS TIE GIS","만승S/S 154kV #60-#65 BUS TIE GIS 보통점검","만승S/S 154kV #60-#65 BUS TIE GIS 보통점검","2019-07-05 10:00","2019-07-05 18:00","2019-07-05 10:00","2019-07-05 18:00","당일"]
[70,"충북","청주","옥천보은 T/L","18~19년 청주전력 변전협력회사 총액공사","보은S/S 옥천보은T/L 154kV GIS 하자점검","2019-07-04 09:00","2019-07-04 12:00","2019-07-04 09:00","2019-07-04 12:00","당일"]
[71,"충북","청주","오송북청주#1 T/L","18~19년 청주전력 변전협력회사 총액공사","북청주S/S 오송북청주#1T/L 154kkV GIS 보통점검 오송S/S 오송북청주#1T/L 154kkV GIS 보통점검","2019-07-06 09:30","2019-07-06 18:00","취소","취소","당일"]
[72,"충북","청주","서청주사직#1 T/L","18~19년 청주전력 변전협력회사 총액공사","사직S/S 서청주사직#1T/L 154kV GIS 보통점검 서청주S/S 서청주사직#1T/L 154kV GIS 보통점검","2019-07-07 09:30","2019-07-07 18:00","취소","취소","당일"]
[73,"충북","충주","금왕S/S 154kV #60-#65 BUS TIE GIS","직할변전협력회사 총액공사","154kV GIS 보통점검. 상시여자계전기 교체.","2019-07-05 10:00","2019-07-05 18:00","2019-07-05 10:00","2019-07-05 18:00","당일"]
[74,"대전충남","대전","남대전신흥#3 T/L","신흥,남대전S/S 154kV 남대전-신흥#3T/L 보호배전반 성능개선","신흥,남대전S/S 154kV 남대전-신흥#3T/L 보호배전반 성능개선","2019-07-01 09:00","2019-07-01 18:00","2019-07-01 09:00","2019-07-01 18:00","당일"]
[75,"대전충남","서산","합덕송악#2 T/L","[송전]154kV 신온양-석곡 등 10개T/L 피뢰기 설치공사","154kV 합덕-송악T/L 피뢰기 설치(26기분)","2019-07-06 07:00","2019-07-07 18:00","취소","취소","매일"]
[76,"대전충남","아산","서천안탕정#2 T/L","154kV 장재-천안 등 4개T/L 일진제 PMJ 교체공사","일진제 R-type 조립식접속함(PMJ) 교체","2019-07-01 08:00","2019-07-07 18:00","취소","취소","연속"]
[77,"대전충남","아산","신온양석곡#2 T/L","신온양S/S 154kV 신온양-석곡#2T/L GIS 보통점검 등","○신온양S/S 154kV 신온양-석곡#2T/L GIS 보통점검 및 하이드로오일 고압호스 교체","2019-07-02 09:00","2019-07-02 18:00","2019-07-02 09:00","2019-07-02 18:00","당일"]
[78,"대전충남","아산","신온양석곡#2 T/L","신온양S/S 154kV 신온양-석곡#2T/L GIS 보통점검 등","○신온양S/S 154kV 신온양-석곡#2T/L GIS 보통점검 및 하이드로오일 고압호스 교체","2019-07-02 09:00","2019-07-02 18:00","취소","취소","당일"]
[79,"대전충남","아산","아산온양#1 T/L","[송전]154kV 아산-온양#1T/L 불량애자교체공사","[송전]154kV 아산-온양#1T/L 불량애자교체공사","2019-07-06 07:00","2019-07-06 14:00","2019-07-06 07:00","2019-07-06 14:00","당일"]
[80,"대전충남","아산","한샘둔포#1 T/L","[송전]154kV 한샘-둔포 #1T/L 불량애자교체공사","154kV 한샘-둔포 #1T/L No.9호 불량애자교체공사(중단 1련 내장애자)","2019-07-05 08:00","2019-07-05 18:00","2019-07-05 08:00","2019-07-05 18:00","당일"]
[81,"대전충남","청양","옥산서천화력#1 T/L","154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사","[송전] 154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사 ○ 지지물 2기 설치/1기 철거(기설No.5) ○ 전력선 신설(0.552km)","2019-07-30 07:00","2019-08-17 18:00","2019-07-30 07:00","2019-08-17 18:00","연속"]
[82,"대전충남","청양","대천서천화력#1 T/L","154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사","[송전] 154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사 ○ 지지물 2기 설치/1기 철거(기설No.5) ○ 전력선 신설(0.552km)","2019-07-30 07:00","2019-08-17 18:00","2019-07-30 07:00","2019-08-17 18:00","연속"]
[83,"대전충남","아산","아산온양#2 T/L","[송전]154kV 아산-온양T/L 불량애자교체공사","[송전]154kV 아산-온양T/L 불량애자교체공사","2019-07-06 14:00","2019-07-06 18:00","2019-07-06 14:00","2019-07-06 18:00","당일"]
[84,"전북","군산","군산서군산#2 T/L","154kV 군산-서군산 등 2개T/L 비표준자기애관 교체공사","비표준 자기애관 교체공사","2019-07-11 09:00","2019-07-20 18:00","2019-07-11 09:00","2019-07-20 18:00","연속"]
[85,"전북","군산","군산서군산#1 T/L","154kV 군산-서군산 등 2개T/L 비표준자기애관 교체공사","비표준 자기애관 교체공사","2019-07-21 09:00","2019-07-30 18:00","2019-07-21 09:00","2019-07-30 18:00","연속"]
[86,"전북","김제","신김제S/S 154kV 신김제-동전주#1T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2019-07-04 10:00","2019-07-04 13:00","2019-07-06 10:00","2019-07-06 13:00","당일"]
[87,"전북","김제","신김제S/S 154kV 신김제-동전주#2T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2019-07-04 13:00","2019-07-04 16:00","2019-07-06 13:00","2019-07-06 16:00","당일"]
[88,"광주전남","강진","신강진강진#1 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","신강진보호배전반 대체, 시험","2019-07-21 09:00","2019-08-01 18:00","취소","취소","연속"]
[89,"광주전남","강진","영암강진#2 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","영암, 강진S/S 보호반 대체, 시험 송전선로 분기모선 철거, 임시선로 가선 OPGW설치 및 시험","2019-07-01 09:00","2019-07-06 18:00","2019-07-01 09:00","2019-07-06 18:00","연속"]
[90,"광주전남","강진","영암강진#1 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","영암, 강진 보호반 대체, 시험 송전선로 철거 및 임시선로 가선","2019-07-07 09:00","2019-07-12 18:00","2019-07-07 09:00","2019-07-12 18:00","연속"]
[91,"광주전남","강진","강진장흥#1 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","장흥, 강진 보호반대체, 시험, CVT이설 지중케이블 EBA 및 EBG 접속 OPGW 설치 및 시험","2019-07-13 09:00","2019-07-20 18:00","2019-07-13 09:00","2019-07-20 18:00","연속"]
[92,"광주전남","강진","강진장흥#2 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","장흥, 강진 보호반대체, 시험, CVT이설 지중케이블 EBA 및 EBG 접속 OPGW 설치 및 시험","2019-07-21 09:00","2019-07-28 18:00","취소","취소","연속"]
[93,"광주전남","강진","강진남창#2 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,신강진,남창S/S 보호배전반 대체, 시험 강진-남창#2T/L, 신강진-강진#2T/L 직결","2019-07-01 09:00","2019-07-08 18:00","취소","취소","연속"]
[94,"광주전남","강진","신강진강진#2 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,신강진,남창S/S 보호배전반 대체, 시험 강진-남창#2T/L, 신강진-강진#2T/L 직결","2019-07-01 09:00","2019-07-08 18:00","취소","취소","연속"]
[95,"광주전남","강진","강진남창#1 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,남창S/S 보호배전반 대체, 시험, LA, CVT 이설 송전선로 철거 및 가선, 선로접속, 모선POST 철거 OPGW 설치 및 시험","2019-07-09 09:00","2019-07-20 18:00","취소","취소","연속"]
[96,"광주전남","순천","여천여수#2 T/L","여천S/S 154kV 절환모선 설치공사","여수산단측 절환모선 무부하 가압","2019-07-02 11:00","2019-07-03 11:00","2019-07-02 11:00","2019-07-03 11:00","연속"]
[97,"광주전남","순천","여천여수#1 T/L","여천S/S 154kV 절환모선 설치공사","여천측 절환모선 무부하 가압","2019-07-01 11:00","2019-07-02 11:00","2019-07-01 11:00","2019-07-02 11:00","연속"]
[98,"광주전남","직할","매월화정#1 T/L","매월S/S 154kV 매월-화정 #1T/L (GIS 정밀점검)","2019년 직할 170kV GIS 정밀점검공사 - 내용 : CB, 상부BUS, C/H 내부 정밀점검","2019-07-01 09:00","2019-07-02 18:00","2019-07-01 09:00","2019-07-02 18:00","연속"]
[99,"광주전남","순천","여수TP여천#2 T/L","여천S/S 154kV 절환모선 설치공사","여수산단측 절환모선 무부하 가압","2019-07-02 11:00","2019-07-03 11:00","2019-07-02 11:00","2019-07-03 11:00","연속"]
[100,"광주전남","순천","여천호남TP#1 T/L","여천S/S 154kV 절환모선 설치공사","여천측 절환모선 무부하 가압","2019-07-01 11:00","2019-07-02 11:00","2019-07-01 11:00","2019-07-02 11:00","연속"]
[101,"대구","달성","논공달성#2 T/L","논공달성#2T/L 차단기동작특성시험","논공달성#2T/L 차단기동작특성시험","2019-07-10 09:00","2019-07-10 18:00","2019-07-01 09:00","2019-07-01 18:00","당일"]
[102,"대구","달성","성서달성#1 T/L","성서달성#1,2T/L 차단기동작특성시험","성서달성#1,2T/L 차단기동작특성시험","2019-07-11 09:00","2019-07-11 13:00","취소","취소","당일"]
[103,"대구","달성","성서달성#2 T/L","성서달성#1,2T/L 차단기동작특성시험","성서달성#1,2T/L 차단기동작특성시험","2019-07-11 13:00","2019-07-11 18:00","취소","취소","당일"]
[104,"대구","달성","달성상인#1 T/L","달성상인#1,2T/L 차단기동작특성시험","달성상인#1,2T/L 차단기동작특성시험","2019-07-12 09:00","2019-07-12 13:00","2019-07-11 09:00","2019-07-11 18:00","당일"]
[105,"대구","달성","달성상인#2 T/L","달성상인#1,2T/L 차단기동작특성시험","달성상인#1,2T/L 차단기동작특성시험","2019-07-12 13:00","2019-07-12 18:00","2019-07-12 09:00","2019-07-12 18:00","당일"]
[106,"대구","달성","두류봉덕#2 T/L","두류봉덕#1,2T/L 차단기동작특성시험","두류봉덕#1,2T/L 차단기동작특성시험","2019-07-08 13:00","2019-07-08 18:00","취소","취소","당일"]
[107,"대구","달성","두류봉덕#1 T/L","두류봉덕#1,2T/L 차단기동작특성시험","두류봉덕#1,2T/L 차단기동작특성시험","2019-07-08 09:00","2019-07-08 13:00","취소","취소","당일"]
[108,"대구","달성","상인봉덕#1 T/L","상인봉덕#1T/L 보호PNL 대체작업","상인봉덕#1T/L 보호PNL 대체작업","2019-07-04 09:00","2019-07-05 18:00","2019-07-04 09:00","2019-07-05 18:00","연속"]
[109,"대구","직할","노변효목#2 T/L","일진제 PMJ 중간접속함 교체공사","일진제 PMJ 중간접속함 교체공사","2019-07-15 09:00","2019-07-21 18:00","취소","취소","연속"]
[110,"대구","직할","노변효목#1 T/L","일진제 PMJ 중간접속함 교체공사","일진제 PMJ 중간접속함 교체공사","2019-07-08 09:00","2019-07-14 18:00","취소","취소","연속"]
[111,"부산울산","동부산","구서명장#2 T/L","2018-2019 동부산전력지사 송전정비 협력회사 총액공사","불량 금구류 교체 ㅇ작업내용 : 4호 1개소 불량 압축인류크램프 교체","2019-07-01 08:00","2019-07-02 18:00","2019-07-01 08:00","2019-07-02 18:00","연속"]
[112,"부산울산","북부산","김해어방#2 T/L","2019년 북부산 변전협력회사 총액공사","김해E/C 154kV 김해-어방2T/L GIS 초기 점검","2019-07-04 10:00","2019-07-04 18:00","2019-07-04 10:00","2019-07-04 18:00","당일"]
[113,"부산울산","울산","신울산S/S 154kV #61-#66 BUS TIE CB","18~19년 변전협력 총액공사","- 신울산S/S 154kV #61-#66 BUS TIE 차단기 동작시험","2019-07-02 13:00","2019-07-02 18:00","2019-07-02 13:00","2019-07-02 18:00","당일"]
[114,"부산울산","울산","신울산S/S 154kV #63-#68 BUS TIE CB","18~19년 변전협력 총액공사","- 신울산S/S 154kV #63-#68 BUS TIE 차단기 동작시험","2019-07-04 09:00","2019-07-04 13:00","2019-07-04 09:00","2019-07-04 13:00","당일"]
[115,"부산울산","울산","신울산S/S 154kV #60-#65 BUS TIE CB","18~19년 변전협력 총액공사","- 신울산S/S 154kV #60-#65 BUS TIE 차단기 동작시험","2019-07-02 09:00","2019-07-02 13:00","2019-07-02 09:00","2019-07-02 13:00","당일"]
[116,"부산울산","울산","신울산S/S 154kV #65-#66 SEC CB","18~19년 변전협력 총액공사","- 신울산S/S 154kV #65-#66 BUS SEC차단기 동작시험","2019-07-01 13:00","2019-07-01 18:00","2019-07-01 13:00","2019-07-01 18:00","당일"]
[117,"부산울산","울산","신울산S/S 154kV #60-#61 SEC CB","18~19년 변전협력 총액공사","- 신울산S/S 154kV #60-61BUS SEC 차단기 동작시험","2019-07-01 09:00","2019-07-01 13:00","2019-07-01 09:00","2019-07-01 13:00","당일"]
[118,"부산울산","울산","영남T/P 154kV #60-#65 BUS TIE CB","18~19년 변전협력 총액공사","- 영남T/P 154kV #60-#65 BUS TIE GIS 보통점검","2019-07-08 09:00","2019-07-08 18:00","취소","취소","당일"]
[119,"부산울산","울산","용연울산TP#3 T/L","18~19년 변전협력 총액공사","- (용연, 울산TP)154kV 용연-울산TP#3 T/L 양단 차단기 동작시험","2019-07-04 09:00","2019-07-04 13:00","2019-07-04 09:00","2019-07-04 13:00","당일"]
[120,"부산울산","울산","울산T/P 154kV #60-#65 BUS TIE CB","18~19년 변전협력 총액공사","- 울산T/P 154kV #60-#65 BUS TIE 차단기 동작시험","2019-07-05 09:00","2019-07-05 18:00","2019-07-05 09:00","2019-07-05 18:00","당일"]
[121,"부산울산","울산","울산T/P 154kV #61-#66 BUS TIE CB","18~19년 변전협력 총액공사","울산T/P 154kV #6200BUS TIE GIS 차단기 동작시험","2019-07-01 09:00","2019-07-01 13:00","2019-07-01 09:00","2019-07-01 13:00","당일"]
[122,"부산울산","울산","울산울산TP#1 T/L","18~19년 변전협력 총액공사","- 울산화력 154kV 울산-울산TP#1 T/L 617GIS 보통점검","2019-07-09 09:00","2019-07-09 18:00","2019-07-09 09:00","2019-07-09 18:00","당일"]
[123,"부산울산","울산","울산T/P 154kV #65-#66 SEC CB","18~19년 변전협력 총액공사","울산T/P 154kV #65-66BUS SEC GIS 보통점검","2019-07-10 09:00","2019-07-10 18:00","2019-07-10 09:00","2019-07-10 18:00","당일"]
[124,"부산울산","울산","울산울산TP#2 T/L","18~19년 변전협력 총액공사","- 울산화력 154kV 울산-울산TP#2 T/L 627GIS 보통점검","2019-07-10 09:00","2019-07-10 18:00","2019-07-10 09:00","2019-07-10 18:00","당일"]
[125,"부산울산","울산","울산T/P 154kV #60-#61 SEC CB","18~19년 변전협력 총액공사","- 울산T/P 154kV #60-#61 BUS SEC GIS 보통점검","2019-07-12 09:00","2019-07-12 18:00","2019-07-03 09:00","2019-07-03 18:00","당일"]
[126,"부산울산","울산","신울산웅촌#1 T/L","2019년 울산전력지사 170kV 개폐장치 정밀점검공사","- 154kV #1BUS TIE 정밀점검 시험가압선로 1H","2019-05-23 17:00","2019-05-23 18:00","취소","취소","당일"]
[127,"경남","진주","의령동진주#1 T/L","의령S/S #1M.Tr 2차 CB(6133) 정밀점검","의령S/S #1M.Tr 2차 CB(6133) 정밀점검 후 시험가압","2019-07-06 15:00","2019-07-06 18:00","2019-07-06 15:00","2019-07-06 18:00","당일"]
[128,"경남","통영","신고성S/S 154kV #61-#66 BUS TIE GIS","신고성S/S 154kV 6200B/T 조작시험","신고성S/S 154kV 6200B/T 조작시험","2019-07-02 14:00","2019-07-02 18:00","2019-07-02 14:00","2019-07-02 18:00","당일"]
[129,"경남","통영","신고성S/S 154kV #65 BUS","삼천포,신고성S/S 용량부족차단기 대체공사","#4M.Tr 1차 인출변경 관련 위상체크","2019-07-10 14:00","2019-07-10 18:00","2019-07-10 14:00","2019-07-10 18:00","당일"]
[130,"경남","통영","신고성S/S 154kV #60-#65 BUS TIE GIS","신고성S/S 154kV 6100B/T 조작시험","신고성S/S 154kV 6100B/T 조작시험","2019-07-02 09:30","2019-07-02 14:00","2019-07-02 09:30","2019-07-02 14:00","당일"]
[131,"경남","함안","신마산차룡#1 T/L","신마산S/S 신마산-차룡#1T/L GCB 조작시험","신마산S/S 신마산-차룡#1T/L GCB 조작시험","2019-07-05 09:30","2019-07-05 13:30","2019-07-05 09:30","2019-07-05 13:30","당일"]
[132,"경남","함안","신마산차룡#2 T/L","신마산S/S 신마산-차룡#2T/L GCB 조작시험","신마산S/S 신마산-차룡#2T/L GCB 조작시험","2019-07-05 13:30","2019-07-05 17:30","2019-07-05 13:30","2019-07-05 17:30","당일"]

{"sheet":"시송전설비","index":4,"n_rows":1,"n_cols":17,"rows_kept":1,"cut":false,"hidden":true,"merged":[[0,16,0,21]]}
["1차\n사업소","2차\n사업소","설비명",{"$nulls":8},"연간\n반영","비고","Key-point","시송전설비 여부","찾는함수","=IF(ISERROR(VLOOKUP(D5,시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D5,시송전설비!$C$2:$O$130,13,0))"]