{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765송부","index":0,"n_rows":20,"n_cols":17,"rows_kept":20,"cut":false,"hidden":false,"merged":[[2,16,3,16],[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n 여부","계통안정 사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #4 M.Tr A-1","신가평S/S #78Bay B/F 보호반 교체공사","신가평S/S #78Bay B/F 보호반 교체공사","2019-09-30 09:00","2019-10-04 18:00","취소","취소","연속"]
[2,"경기북부","구리","신안성신가평 T/L","765kV 신안성-신가평T/L 항공장애표지구 교체공사","ㅇ 항공장애표지구 교체 - 구간 : No.135~137","2019-09-20 07:00","2019-09-20 18:00","취소","취소","당일"]
[3,"경기북부","구리","신가평S/S 765kV #80 BUS","신가평S/S #80BUS 보호반 교체공사","신가평S/S #80BUS 보호반 교체공사","2019-09-16 09:00","2019-09-27 18:00","2019-09-16 09:00","2019-09-25 18:00","연속"]
[4,"경기","성남","신안성S/S 765kV #85 BUS","BUS PRO반 대체","BUS PRO반 대체","2019-09-30 09:00","2019-10-05 18:00","취소","취소","연속"]
[5,"경기","성남","신안성S/S 765kV #80 BUS","BUS PRO반 대체","- BUS PRO반 대체 - 800kV GIS 정밀점검공사","2019-09-16 09:00","2019-09-27 18:00","취소","취소","연속"]
[6,"강원","태백","신태백신가평#1 T/L","신태백T/L 민원 관련 항공장애표시구 교체","765kV 신태백-신가평#1T/L 항공장애표시구 교체","2019-09-25 10:00","2019-09-29 18:00","2019-09-26 10:00","2019-09-30 18:00","연속"]
[7,"강원","태백","신태백S/S #2 M.Tr A-1","19년 신태백변전소 주변압기 계전기 성능개선","신태백변전소 #2M.Tr 계전기 성능개선","2019-09-02 10:00","2019-09-02 18:00","2019-09-02 10:00","2019-09-02 18:00","당일"]
[8,"강원","태백","신태백S/S #3 M.Tr A-1","19년 신태백변전소 주변압기 계전기 성능개선","신태백변전소 #3M.Tr 계전기 성능개선","2019-09-03 10:00","2019-09-03 18:00","2019-09-03 10:00","2019-09-03 18:00","당일"]
[9,"강원","태백","신태백S/S #4 M.Tr A-1","19년 태백전력지사 765kV 주변압기 정밀점검 공사","신태백변전소 #4M.Tr 정밀점검 공사 / [병행] 9/23(월) 8500CB조작시험 / [병행] 9/23(월) 7771CB 보통점검","2019-09-18 10:00","2019-12-31 18:00","취소","취소","연속"]
[10,"강원","태백","신태백신가평#1 T/L","345kV 신영주, 신제천TCSC 설치사업","신영주, 신제천S/S TCSC 설치공사 - TCSC 제어용 신호 구성을 위한 SPS 설치(신태백, 신제천, 신영주S/S) - 접점 및 보호계전기 동작 관련 연동시험","2019-09-23 09:00","2019-09-23 18:00","취소","취소","당일"]
[11,"강원","태백","신태백신가평#2 T/L","345kV 신영주, 신제천TCSC 설치사업","신영주, 신제천S/S TCSC 설치공사 - TCSC 제어용 신호 구성을 위한 SPS 설치(신태백, 신제천, 신영주S/S) - 접점 및 보호계전기 동작 관련 연동시험","2019-09-24 09:00","2019-09-24 18:00","2019-10-01 09:00","2019-10-02 18:00","연속"]
[12,"경북","영주","신한울S/S #1 M.Tr A-1","신한울S/S 벨로우즈 교체 공사","- 신한울S/S 벨로우즈 교체 공사","2019-09-23 09:00","2019-09-27 18:00","취소","취소","연속"]
[13,"부산울산","동부산","신고리S/S #3 Tie-Tr A-1","YPP제 보호배전반 성능개선","보호배전반 인출 DS 상태 감시회로 개선","2019-09-27 09:30","2019-09-27 18:00","2019-09-27 09:30","2019-09-27 18:00","당일"]
[14,"부산울산","동부산","신고리S/S #3 Tie-Tr A-1","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 362kV 7672,7600GIS 구조개선관련 시험가압(#3M.Tr)","2019-09-06 18:00","2019-09-07 18:00","2019-09-06 18:00","2019-09-07 18:00","연속"]
[15,"부산울산","동부산","신고리S/S #2 Tie-Tr A-1","2019년 신고리E/C 765kV GIS 보통점검 공사","8671, 8600 GIS 보통점검","2019-09-23 09:30","2019-09-26 18:00","2019-09-23 09:30","2019-09-26 18:00","연속"]
[16,"경남","함안","북경남S/S #4 M.Tr A-1","북경남S/S #4M.Tr 1차측 Spacer 교체공사","북경남S/S #4M.Tr 1차측 Spacer 73EA 교체공사 시행","2019-09-17 10:00","2019-11-19 10:00","2019-09-17 10:00","2019-11-19 10:00","연속"]

{"sheet":"345송부","index":1,"n_rows":239,"n_cols":17,"rows_kept":239,"cut":false,"hidden":false,"merged":[[2,16,3,16],[2,15,3,15],[2,14,3,14],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부","계통안정 사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S 345kV #1 M.Tr 1차 GIS","19년 중부전력지사 변전협력회사 총액공사","ㅇ345kV #1M.Tr 1차 GIS 차단기 동작시험","2019-09-20 10:00","2019-09-20 13:00","2019-09-02 10:00","2019-09-02 13:00","당일"]
[2,"남서울","강남","신양재S/S 345kV #1 Sh.R 1차 GIS","신양재S/S 345kV 7171 GIS ES 보수","신양재S/S 345kV 7171 GIS ES 보수","2019-09-19 09:00","2019-09-19 18:00","2019-09-17 09:00","2019-09-17 18:00","당일"]
[3,"남서울","강남","신성남신양재 #2 T/L","신양재S/S #2Sh.R용 345kV GIS 대체 작업(무부하가압 시험)","신양재S/S #2Sh.R용 345kV GIS 대체 작업(무부하가압 시험)","2019-09-18 09:00","2019-09-27 18:00","2019-09-18 09:00","2019-09-27 18:00","연속"]
[4,"남서울","강남","신양재S/S 345kV #2 Sh.R","신양재S/S #2Sh.R용 345kV GIS 대체 작업","신양재S/S #2Sh.R용 345kV GIS 대체 작업","2019-09-18 09:00","2019-09-27 18:00","2019-09-18 09:00","2019-09-27 18:00","연속"]
[5,"남서울","동서울","신용인동서울#2 T/L","2019년도 동서울P/O 가공송전 순시점검 위탁공사","#2T/L 정밀점검(No.82~동서울S/T) / 한전KPS 작업","2019-09-27 08:00","2019-09-28 18:00","2019-09-27 08:00","2019-09-28 18:00","연속"]
[6,"남서울","동서울","신용인동서울#1 T/L","2019년도 동서울P/O 가공송전 순시점검 위탁공사","#1T/L 정밀점검(No.82~동서울S/T) / 한전KPS 작업","2019-09-25 08:00","2019-09-26 18:00","2019-09-25 08:00","2019-09-26 18:00","연속"]
[7,"남서울","영등포","신시흥신광명#1 T/L","345kV 신시흥-신광명#1T/L 압축인류클램프 점검","345kV 신시흥-신광명#1T/L 압축인류클램프 점검","2019-09-06 09:00","2019-09-06 18:00","취소","취소","당일"]
[8,"인천","김포","신김포S/S 345kV #1 Sh.R","YPP제 345kV T60(87) 계전기 성능개선","오동작 방지 관련 DSP모듈 교체","2019-09-19 10:00","2019-09-19 18:00","2019-09-19 10:00","2019-09-19 18:00","당일"]
[9,"인천","김포","신김포S/S 345kV #2 Sh.R","YPP제 345kV T60(87) 계전기 성능개선","오동작 방지 관련 DSP모듈 교체","2019-09-20 09:00","2019-09-20 18:00","2019-09-20 09:00","2019-09-20 18:00","당일"]
[10,"인천","김포","가정개폐소 345kV 신가좌-가정#2T/L TIE CB A (7300A)","(가정 7300CB 휴전)신부평#2S/S 362kV GIS 설치공사","가정개폐소 7372 CB 설치 가정개폐소 7272 LINE PT 설치 가정개폐소 7472 LINE PT 설치 기타부대작업","2019-09-23 09:00","2019-10-14 18:00","2019-09-23 09:00","2019-10-14 18:00","연속"]
[11,"인천","김포","가정개폐소 345kV #75 BUS","신부평#2S/S 362kV GIS 설치공사","가정개폐소 7372 CB 설치 7272, 7472 LINE PT 설치 기타부대작업","2019-09-23 09:00","2019-09-27 18:00","2019-09-23 09:00","2019-09-27 18:00","연속"]
[12,"인천","김포","신김포서인천CC T/L","YPP제 345kV 송전선로 보호배전반 성능개선","○ 보호계전기 내부 로직개선 및 펌웨어 업그레이드 ○ 인출DS 감시접점 Keep Ry 회로변경","2019-09-23 09:00","2019-09-23 18:00","2019-09-23 09:00","2019-09-23 18:00","당일"]
[13,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S #1M.Tr 휴전작업","- 7172 GIS 초기점검 - 6144 GIS 조작시험 - #1-2 Sh.R 보통점검 - 4179, 4179-1,2 VCB 조작시험 - 4179-3, 4189 VCB 보통점검","2019-09-23 09:00","2019-09-24 18:00","2019-09-23 09:00","2019-09-24 18:00","연속"]
[14,"인천","시흥","영흥1TP영흥2TP #1T/L","영흥S/Y 영흥TP연락#1T/L(7171) GIS 정밀점검","영흥S/Y 영흥TP연락#1T/L(7171) GIS 정밀점검","2019-09-23 09:00","2019-09-26 18:00","2019-09-23 09:00","2019-09-26 18:00","연속"]
[15,"인천","김포","신김포S/S 345kV #1 Sh.R","신김포S/S 345kV #1Sh.R 소음측정","신김포S/S 345kV #1Sh.R 소음측정 - 소음 민원 발생에 따른 휴전 시 소음측정","2019-09-24 03:00","2019-09-24 05:00","2019-09-24 03:00","2019-09-24 05:00","당일"]
[16,"인천","김포","신김포S/S #2 M.Tr","신김포S/S 345kV #2M.Tr 소음측정","신김포S/S 345kV #2M.Tr 소음측정 - 소음 민원 발생에 따른 휴전 시 소음측정","2019-09-24 03:00","2019-09-24 05:00","2019-09-24 03:00","2019-09-24 05:00","당일"]
[17,"인천","김포","신김포S/S #1 M.Tr","신김포S/S 345kV #1M.Tr 소음측정","신김포S/S 345kV #1M.Tr 소음측정 - 소음 민원 발생에 따른 휴전 시 소음측정","2019-09-24 03:00","2019-09-24 05:00","2019-09-24 03:00","2019-09-24 05:00","당일"]
[18,"인천","김포","신김포S/S 345kV #2 Sh.R","신김포S/S 345kV #2Sh.R 소음측정","신김포S/S 345kV #2Sh.R 소음측정 - 소음 민원 발생에 따른 휴전 시 소음측정","2019-09-24 03:00","2019-09-24 05:00","2019-09-24 03:00","2019-09-24 05:00","당일"]
[19,"인천","부평","포스코CC인천TP#2T/L","345kV 포스코SY-인천CC #2T/L DTS 복구공사","345kV 포스코SY-인천CC #2T/L DTS 복구공사","2019-09-24 09:00","2019-09-25 18:00","2019-09-24 09:00","2019-09-25 18:00","연속"]
[20,"인천","부평","신가좌신시흥#2 T/L","YPP제 345kV 송전선로 보호배전반 성능개선","○ 보호계전기 내부 로직개선 및 펌웨어 업그레이드 ○ 인출DS 감시접점 Keep Ry 회로변경","2019-09-25 09:00","2019-09-25 18:00","2019-09-25 09:00","2019-09-25 18:00","당일"]
[21,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S #3M.Tr 휴전작업","- 6344 GIS 조작시험","2019-09-25 09:00","2019-09-25 18:00","2019-09-25 09:00","2019-09-25 18:00","당일"]
[22,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S #2M.Tr 휴전작업","- 6244 GIS 조작시험 - #2-3 Sh.R 초기점검 - 4279, 4289, 4279-1,2,3 VCB 조작시험","2019-09-26 09:00","2019-09-27 18:00","2019-09-26 09:00","2019-09-27 18:00","연속"]
[23,"인천","부평","서인천C/C 345kV #2 Sh.R","서인천C/C 7479GIS 하자점검","서인천C/C 7479GIS 하자점검","2019-09-30 09:00","2019-09-30 18:00","2019-09-30 09:00","2019-09-30 18:00","당일"]
[24,"인천","시흥","영흥1TP영흥2TP #2T/L","영흥S/Y 영흥TP연락#2T/L(7271) GIS 정밀점검","영흥S/Y 영흥TP연락#2T/L(7271) GIS 정밀점검","2019-09-30 09:00","2019-10-04 18:00","2019-09-30 09:00","2019-10-04 18:00","연속"]
[25,"경기북부","고양","신덕은동두천CC#2 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","송전선로 항공장애표시구 설치 - 345kV 신덕은-동두천CCT/L (ACSR 29경간)","2019-09-23 08:00","2019-09-27 18:00","취소","취소","연속"]
[26,"경기북부","고양","신파주양주#1 T/L","고양전력지사 OPGW 항공장애표시구 정비공사","345kV 신파주-양주 등 8개T/L OPGW 항공장애표시구 정비공사","2019-09-26 09:00","2019-09-30 18:00","2019-09-26 09:00","2019-09-30 18:00","연속"]
[27,"경기북부","고양","신파주양주#2 T/L","345kV 신파주-양주T/L No.12 안전이격거리 확보공사","○ 구 간 : 345kV 신파주-양주T/L No.10~13 ○ 철 탑 : 1기 신설, 1기 철거","2019-09-28 06:00","2019-10-02 18:00","2019-09-28 06:00","2019-10-02 18:00","연속"]
[28,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치(안전이격확보) - 기타 부대공사","2019-09-16 08:00","2019-09-27 18:00","2019-09-16 08:00","2019-09-27 18:00","매일"]
[29,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 170kV 장기사용GIS 교체공사(6차분)","- 170kV GIS 철거, 설치(안전이격확보) - 기타 부대공사","2019-09-30 10:00","2019-10-18 18:00","2019-09-30 10:00","2019-10-18 18:00","매일"]
[30,"경기북부","구리","동서울미금#2 T/L","미금S/S 동서울미금#2T/L CVT B상 누유여부 점검","미금S/S 동서울미금#2T/L CVT B상 누유여부 점검","2019-09-24 09:00","2019-09-24 18:00","2019-09-24 09:00","2019-09-24 18:00","당일"]
[31,"경기북부","구리","동서울미금#1 T/L","미금S/S 동서울미금#1T/L CVT B상 유면계점검","미금S/S 동서울미금#1T/L CVT B상 유면계점검","2019-09-23 09:00","2019-09-23 18:00","2019-09-23 09:00","2019-09-23 18:00","당일"]
[32,"경기북부","구리","신가평미금#2 T/L","미금S/S 345kV #78BAY B/F반 교체공사","미금S/S 345kV #78BAY B/F반 교체","2019-09-30 09:00","2019-10-04 18:00","취소","취소","연속"]
[33,"경기북부","구리","신가평S/S 345kV #3 Sh.R","신가평S/S 345kV #3 Sh.R 내부점검","절연유 가스분석 이상에 따른 내부점검","2019-09-16 09:00","2019-09-20 18:00","2019-09-16 09:00","2019-09-20 18:00","연속"]
[34,"경기북부","구리","신포천S/S 345kV #70 BUS","신포천S/S 345kV #1BUS 가스누기보수공사","신포천S/S 345kV #1BUS 가스누기보수공사 - #1BUS 휴전(연속) - 신포천포천LNGC/C #1,2T/L (매일)","2019-09-30 09:00","2019-10-09 18:00","2019-09-30 09:00","2019-10-09 18:00","연속"]
[35,"경기북부","직할","신의정부S/S 345kV #2 Sh.R","'19년 변전협력회사 총액공사(신의정부S/S #2Sh.R 보호반 교체)","신의정부S/S #2Sh.R 보호반 교체","2019-09-23 09:00","2019-09-25 18:00","양주4Sh.R과 중복","양주4Sh.R과 중복","연속"]
[36,"경기북부","직할","신의정부S/S #4 M.Tr","345kV M.Tr 본체 및 OLTC 정밀점검","#4M.Tr A,B,C상 본체 및 OLTC 정밀점검","2019-09-23 09:00","2019-10-04 18:00","2019-09-23 09:00","2019-10-04 18:00","연속"]
[37,"경기북부","직할","신의정부S/S 345kV #3 Sh.R","'19년 변전협력회사 총액공사(신의정부S/S #3Sh.R 보호반 교체)","신의정부S/S #3Sh.R 보호반 교체","2019-09-30 09:00","2019-10-02 18:00","양주4Sh.R과 중복","양주4Sh.R과 중복","연속"]
[38,"경기북부","직할","양주S/S 345kV #4 Sh.R","양주변전소 옥외철구 GIS화 공사","가공지선 설치","2019-09-22 09:00","2019-10-04 18:00","2019-09-22 09:00","2019-10-04 18:00","매일"]
[39,"경기북부","직할","양주S/S #3 M.Tr","양주변전소 옥외철구 GIS화 공사","가공지선 설치","2019-09-22 09:00","2019-09-25 18:00","2019-09-22 09:00","2019-09-25 18:00","매일"]
[40,"경기북부","직할","양주S/S #2 M.Tr","154kV 지축E/C 옥내화 사업","154kV 지축E/C 옥내화 사업 - 이설선로 무부하가압","2019-09-26 09:00","2019-09-27 18:00","2019-09-26 09:00","2019-09-27 18:00","연속"]
[41,"경기북부","직할","양주S/S #1 M.Tr","345kV M.Tr 본체 정밀점검 및 부싱대체 공사","#1M.Tr C상 1차 및 2차 부싱 대체","2019-09-16 09:00","2019-09-20 18:00","2019-09-16 09:00","2019-09-20 18:00","연속"]
[42,"경기북부","직할","양주S/S #2 M.Tr","양주변전소 옥외철구 GIS화 공사","가공지선 설치","2019-09-29 09:00","2019-10-04 18:00","2019-09-29 09:00","2019-10-04 18:00","매일"]
[43,"경기","군포","신안산S/S #1 M.Tr","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #71BAY(#1M.Tr) 용량대체 - 345kV 40kA 2CB 철거, 345kV 63kA 3CB 설치","2019-09-02 09:00","2019-10-31 18:00","2019-09-02 09:00","2019-10-31 18:00","연속"]
[44,"경기","동부","곤지암신충주#1 T/L","345kV 곤지암-신충주T/L 접속개소 전선교체공사","345kV 곤지암-신충주T/L 접속개소 전선교체공사","2019-09-21 07:30","2019-09-26 18:00","취소","취소","연속"]
[45,"경기","동부","곤지암신충주#2 T/L","345kV 곤지암-신충주T/L 접속개소 전선교체공사","345kV 곤지암-신충주T/L 접속개소 전선교체공사","2019-09-27 07:30","2019-10-02 18:00","취소","취소","연속"]
[46,"경기","성남","서안성신진천#1 T/L","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ74Bay 용량대체공사관련 무부하 가압","2019-09-30 09:00","2019-10-01 09:00","2019-09-30 09:00","2019-10-01 09:00","연속"]
[47,"경기","성남","서안성S/S 345kV #1 BUS","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ74Bay GIS 용량대체 ㅇ 기타 부대공사 x 1식","2019-09-02 09:00","2019-10-01 09:00","2019-09-02 09:00","2019-10-01 09:00","연속"]
[48,"경기","성남","신안성서안성#2 T/L","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ74Bay 용량대체 ㅇ기타 부대공사 x 1식","2019-09-02 09:00","2019-10-18 09:00","2019-09-02 09:00","2019-10-18 09:00","연속"]
[49,"경기","성남","서안성S/S #3 M.Tr","345kV 서안성S/S GIS 용량대체공사[변전전문]","ㅇ 74Bay 용량대체 ㅇ 기타 부대공사 x 1식","2019-09-02 09:00","2019-10-18 09:00","2019-09-02 09:00","2019-10-18 09:00","연속"]
[50,"경기","성남","신성남동서울#2 T/L","345kV 신성남-동서울#2T/L 애자련 교체공사","- 345kV 신성남-동서울#2T/L 2기 애자련 교체","2019-09-18 08:00","2019-09-19 18:00","2019-09-18 08:00","2019-09-19 18:00","연속"]
[51,"경기","성남","신성남동서울#1 T/L","345kV 신성남-동서울#1T/L 애자련 교체공사","- 345kV 신성남-동서울#1T/L 3기 애자련 교체","2019-09-16 08:00","2019-09-17 18:00","2019-09-16 08:00","2019-09-17 18:00","연속"]
[52,"경기","성남","서서울#2신성남#1T/L","345kV 서서울2-신성남T/L 안전이격 확보공사","345kV 서서울2-신성남T/L No.26 철탑교체(1기 신설, 1기철거) - 공사구간 : No.24~No.27","2019-09-21 07:00","2019-09-25 18:00","취소","취소","연속"]
[53,"경기","성남","신성남S/S 345kV STATCOM CB","인터록 회로보완","- 인터록 회로보완 - 소내전원 Control UV Trip 회로보완","2019-09-25 09:00","2019-09-25 18:00","2019-09-25 09:00","2019-09-25 18:00","당일"]
[54,"경기","성남","서서울#2신성남#2T/L","345kV 서서울2-신성남T/L 안전이격 확보공사","345kV 서서울2-신성남T/L No.26 철탑교체(1기 신설, 1기철거) - 공사구간 : No.24~No.27","2019-09-26 07:00","2019-09-30 18:00","취소","취소","연속"]
[55,"경기","성남","신성남S/S #4 M.Tr","옥외분전반 대체","옥외분전반 대체","2019-09-26 09:00","2019-09-26 18:00","2019-09-26 09:00","2019-09-26 18:00","당일"]
[56,"경기","성남","신성남S/S 345kV 신성남-동서울#2T/L GIS","차단기 조작시험 (단독차단기 휴전)","차단기 조작시험","2019-09-17 09:00","2019-09-17 18:00","2019-09-17 09:00","2019-09-17 18:00","당일"]
[57,"경기","성남","신안성신수원#1 T/L","154kV 신용인-용인T/L OPGW 증설공사","용인S/S~신용인S/S간 OPGW(24C→48C) 8.814km 교체","2019-09-18 07:00","2019-09-22 18:00","취소","취소","연속"]
[58,"경기","성남","신수원S/S 345kV #70 BUS","PT PNL 대체","PT PNL 대체","2019-09-22 09:00","2019-09-22 18:00","2019-09-22 09:00","2019-09-22 18:00","당일"]
[59,"경기","성남","신수원S/S 345kV #75 BUS","PT PNL 대체","PT PNL 대체","2019-09-21 14:00","2019-09-21 18:00","2019-09-21 14:00","2019-09-21 18:00","당일"]
[60,"경기","성남","신수원S/S 345kV #70 BUS","PT PNL 대체","PT PNL 대체","2019-09-21 09:00","2019-09-21 14:00","2019-09-21 09:00","2019-09-21 14:00","당일"]
[61,"경기","성남","신용인S/S #3 M.Tr","누유보수","2차 GIS 보통점검 누유보수 (서원) 1,3차 LA 대체","2019-09-27 09:00","2019-09-27 18:00","2019-09-27 09:00","2019-09-27 18:00","당일"]
[62,"경기","성남","신용인S/S #1 M.Tr","신용인S/S #1M.Tr 2차 GIS 보통점검","- #1M.Tr 2차 GIS 보통점검 - 1차 LA 대체, N상 LA 보통 - 부싱절연유 채유","2019-09-30 09:00","2019-09-30 18:00","2019-09-30 09:00","2019-09-30 18:00","당일"]
[63,"경기","직할","화성S/S #3 M.Tr","19년 직할 변전협력회사 총액공사","화성S/S #2M.Tr 1차(7200,7272) GIS 조작, 2차(6244) GIS 조작, 2차 LA 하자, 1차(B), 2차(A,B,C) 부싱절연유 채유, 3차 절연화 시공","2019-09-25 09:00","2019-09-25 18:00","2019-09-25 09:00","2019-09-25 18:00","당일"]
[64,"경기","직할","화성S/S #1 M.Tr","19년 직할 변전협력회사 총액공사","화성S/S #1M.Tr 1차(7100,7172) GIS 조작, 2차(6144) GIS 조작, 2차 LA 하자, 1차(A,B), 2차(A,B,C) 부싱절연유 채유, 3차 절연화 시공, #1-1,1-2 Sh.R 하자점검","2019-09-26 09:00","2019-09-26 18:00","2019-09-26 09:00","2019-09-26 18:00","당일"]
[65,"경기","직할","화성S/S #2 M.Tr","19년 직할 변전협력회사 총액공사","화성S/S #2M.Tr 1차(7200,7272) GIS 조작, 2차(6244) GIS 조작, 2차 LA 하자, 1차(B), 2차(A,B,C) 부싱절연유 채유, 3차 절연화시공","2019-09-30 09:00","2019-09-30 18:00","2019-09-30 09:00","2019-09-30 18:00","당일"]
[66,"경기","직할","화성S/S 345kV #71 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV GIS(40/50kA)-&gt60kA 교체(26CB) O. 7B(임시) BAY #71BUS 연결","2019-09-02 10:00","2019-09-06 18:00","2019-09-02 10:00","2019-09-06 18:00","연속"]
[67,"경기","직할","화성신안산 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV GIS(40/50kA)-&gt60kA 교체(26CB) O. 7B(임시) BAY #71BUS 연결_화성-신안산#1T/L 이용 무부하가압","2019-09-05 17:00","2019-09-06 17:00","2019-09-05 17:00","2019-09-06 17:00","연속"]
[68,"경기","직할","화성평택T/P#1 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV GIS(40/50kA)-&gt60kA 교체(26CB) O. 화성SS 362kV 화성-평택TP#1T/L GIS 교체공사","2019-09-09 17:00","2019-10-16 17:00","2019-09-09 17:00","2019-10-16 17:00","연속"]
[69,"강원","강릉","신양양S/S #1 M.Tr","2019 변전협력회사 총액공사","신양양 362kV #1M.Tr 1차 GIS 보통점검 신양양 154kV #1M.Tr 2차 GIS 보통점검","2019-09-30 10:00","2019-10-01 18:00","2019-09-30 10:00","2019-10-01 18:00","매일"]
[70,"강원","강릉","신양양S/S #3 M.Tr","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험 신양양 #3M.Tr 1,2,3차 CB, #3M.Tr 1차-TIE CB","2019-09-02 10:00","2019-09-02 18:00","2019-09-02 10:00","2019-09-02 18:00","연속"]
[71,"강원","동해","동해북평TP#3 T/L","2019년 동해전력지사 장기미동작차단기 조작시험","1.장기미동작차단기 조작시험","2019-09-20 10:00","2019-09-20 18:00","2019-09-20 10:00","2019-09-20 18:00","당일"]
[72,"강원","동해","동해북평TP#2 T/L","2019년 동해전력지사 장기미동작차단기 조작시험","1.장기미동작차단기 조작시험","2019-09-19 10:00","2019-09-19 18:00","2019-09-19 10:00","2019-09-19 18:00","당일"]
[73,"강원","동해","동해북평TP#1 T/L","2019년 동해전력지사 장기미동작차단기 조작시험","1.장기미동작차단기 조작시험","2019-09-18 10:00","2019-09-18 18:00","2019-09-18 10:00","2019-09-18 18:00","당일"]
[74,"강원","동해","동해삼척GP#1 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","○ 전력선 접속개소 해소 : No.5 ∼ 6 등 8개소 15.448C-km ○ 가공지선 접속개소 해소 : No.12 ∼ 17 등 3개소 5.944C-km","2019-09-23 08:00","2019-10-06 18:00","취소","취소","연속"]
[75,"강원","동해","동해신양양 T/L","동해-신양양T/L 송전선로보호반 대체공사","1. 송전선로보호반 대체","2019-09-23 09:30","2019-09-27 18:00","취소","취소","연속"]
[76,"강원","동해","신제천동해#2 T/L","345kV 동해T/L 전선 접속개소 해소공사","○ 공사구간 : 345kV 동해#1,2T/L No.293~297","2019-09-05 07:00","2019-09-07 18:00","취소","취소","연속"]
[77,"강원","동해","신제천동해#1 T/L","345kV 동해T/L 전선 접속개소 해소공사","○ 공사구간 : 345kV 동해#1,2T/L No.293~297","2019-09-02 07:00","2019-09-04 18:00","취소","취소","연속"]
[78,"강원","태백","신태백S/S 345kV #3Sh.R 1차-한울N/P2#1T/L TIE CB A (7500_A)","19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7579CB 보통점검에 의한 휴전","2019-09-20 10:00","2019-09-20 18:00","취소","취소","당일"]
[79,"강원","태백","신태백S/S 345kV #3 Sh.R","19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7579CB 보통점검","2019-09-20 10:00","2019-09-20 18:00","취소","취소","당일"]
[80,"강원","태백","신태백S/S 345kV #3 Sh.R 1차 #1-2 CB A (7571_A)","19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7579CB 보통점검에 의한 휴전","2019-09-20 10:00","2019-09-20 18:00","취소","취소","당일"]
[81,"강원","태백","신태백S/S 345kV #2Sh.R 1차-#74BAYT/L TIE CB A (7400_A)","19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7400CB 조작시험","2019-09-16 10:00","2019-09-17 18:00","취소","취소","연속"]
[82,"강원","태백","신태백S/S 345kV #2 Sh.R","19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7479CB 조작시험","2019-09-16 10:00","2019-09-17 18:00","취소","취소","연속"]
[83,"강원","태백","신태백S/S 345kV #2 Sh.R 1차 #1-2 CB A (7471_A)","19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7471CB 조작시험","2019-09-16 10:00","2019-09-17 18:00","취소","취소","연속"]
[84,"충북","직할","서안성신진천#1 T/L","2018~19년 충주전력지사 송전정비회사 총액공사","피뢰기 설치(1~35), 스페이서교체(18~19,20~30),조류퇴치장치설치(2~16,27~30,32~35)","2019-09-23 07:00","2019-09-28 18:00","2019-09-23 07:00","2019-09-28 18:00","매일"]
[85,"충북","청주","세종남청주#1 T/L","345kV 신옥천-남청주구간 OPGW 시설공사","345kV 신옥천-남청주구간 가공지선 철거 및 OPGW 34km 시설","2019-09-12 09:00","2019-09-17 18:00","2019-09-12 09:00","2019-09-17 18:00","연속"]
[86,"충북","청주","남청주S/S #1 M.Tr","18-19년 청주전력 변전협력회사 총액공사","남청주S/S 345kV #1M.Tr 권선온도계 교체","2019-09-10 09:30","2019-09-10 18:00","2019-09-10 09:30","2019-09-10 18:00","당일"]
[87,"충북","청주","신옥천세종#1 T/L","345kV 신옥천-남청주구간 OPGW 시설공사","345kV 신옥천-남청주구간 가공지선 철거 및 OPGW 34km 시설","2019-09-01 09:00","2019-09-13 18:00","2019-09-01 09:00","2019-09-13 18:00","연속"]
[88,"충북","청주","신옥천S/S #3 M.Tr","신옥천S/S 154kV GIS화 공사","154kV GIS 26CCT 설치","2019-09-24 09:00","2019-10-02 18:00","2019-09-24 09:00","2019-10-02 18:00","연속"]
[89,"충북","충주","신제천동해#2 T/L","345kV 신제천S/S TCSC 설치공사","345kV 신제천S/S TCSC 설치공사 - TCSC 설비연결 및 제작사(ABB) 부하시험","2019-09-16 09:00","2019-09-20 18:00","2019-09-16 09:00","2019-09-20 18:00","연속"]
[90,"충북","충주","신제천S/S 345KV #70 BUS","신제천S/S 345kV #1BUS부 DS 제작사(LS) 하자대체","- 345kV 수평 EDS 조작불량 관련 제작사(LS) 하자대체 - 대상 : 73351,7451,7651,7751,7951,7A51","2019-09-23 09:00","2019-10-04 18:00","2019-09-23 09:00","2019-10-04 18:00","연속"]
[91,"충북","충주","신제천동해#1 T/L","345kV 신제천S/S TCSC 설치공사","345kV 신제천S/S TCSC 설치공사 - TCSC 설비연결 및 제작사(ABB) 부하시험","2019-09-02 09:00","2019-09-06 18:00","2019-09-02 09:00","2019-09-06 18:00","연속"]
[92,"대전충남","서산","당진화력S/Y 345kV #1 TIE Tr 2차 CB A (7271A)","19년도 서산P/O 765/345kV GIS 점검공사","- 당진화력S/S 345kV #1TIE-Tr GIS(7271) 정밀점검","2019-09-30 09:00","2019-10-04 18:00","2019-09-30 09:00","2019-10-04 18:00","연속"]
[93,"대전충남","서산","345kV #1 TIE Tr-2호기 1차 CB A (7200A)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 - 당진T/P TIE Tr 1차-2호기 1차 (7200)CB","2019-09-25 14:00","2019-09-25 18:00","2019-09-25 14:00","2019-09-25 18:00","당일"]
[94,"대전충남","서산","345kV #71 TIE Tr-1호기 1차 CB A (7100A)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 - 당진T/P #1 M.Tr 1차-1호기 1차 (7100)CB","2019-09-25 10:00","2019-09-25 14:00","2019-09-25 10:00","2019-09-25 14:00","당일"]
[95,"대전충남","서산","북당진S/S 345kV #70 BUS","345kV 북당진E/C #1M.Tr용 362kV GIS 설치공사","362kV GIS 3CB 설치","2019-09-30 09:00","2019-10-09 18:00","2019-09-30 09:00","2019-10-09 18:00","연속"]
[96,"대전충남","서산","신당진연락#2T/L-#3 M.TR 1차 TIE CB B (7800B)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 - 신당진S/S #3M.Tr - TIE (7800)CB","2019-09-26 14:00","2019-09-26 18:00","2019-09-26 14:00","2019-09-26 18:00","당일"]
[97,"대전충남","서산","신당진연락#1T/L-#2 M.TR 1차 TIE CB B (7600B)","19년도 차단기 부동작 예방시험","차단기 부동작 예방시험 - 신당진S/S #2M.Tr - TIE (7600)CB","2019-09-26 10:00","2019-09-26 14:00","2019-09-26 10:00","2019-09-26 14:00","당일"]
[98,"대전충남","서산","신당진S/S 345kV 신당진연락#1T/L CB A (7471A)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 -신당진S/S 345kV 신당진연락#1T/L (7471)CB","2019-09-24 10:00","2019-09-24 14:00","2019-09-24 10:00","2019-09-24 14:00","당일"]
[99,"대전충남","서산","신서산태안화력#2 T/L","19년도 노후배전반 교체공사","- 신서산S/S 345kV 75BAY B/F 보호반 대체공사 - 75BAY : #3Sh.R, 신서산-태안화력#2T/L","2019-09-23 09:00","2019-10-04 18:00","2019-09-28 07:00","2019-10-04 18:00","연속"]
[100,"대전충남","서산","신서산S/S 345kV #5 Sh.R","19년도 서산P/O 변전정비회사 총액공사","- 신서산S/S 345kV #5Sh.R 및 #5Sh.R GIS(7979) 보통점검","2019-09-18 09:00","2019-09-20 18:00","2019-09-18 09:00","2019-09-20 18:00","연속"]
[101,"대전충남","서산","신서산S/S #5 Sh.R 7979CB","19년도 서산P/O 변전정비회사 총액공사","- 신서산S/S 345kV #5Sh.R 및 #5Sh.R GIS(7979) 보통점검","2019-09-18 09:00","2019-09-20 18:00","2019-09-18 09:00","2019-09-20 18:00","연속"]
[102,"대전충남","서산","신서산S/S #3 Sh.R CB","19년도 노후배전반 교체공사","- 신서산S/S 345kV 75BAY B/F 보호반 대체공사 - 75BAY : #3Sh.R, 신서산-태안화력#2T/L","2019-09-23 09:00","2019-10-04 18:00","2019-09-23 09:00","2019-10-04 18:00","연속"]
[103,"대전충남","서산","태안T/P 345kV #72 BUS","19년도 서산P/O 765/345kV GIS 점검공사","- 태안화력 345kV 7871CB 절연롯드 교체작업 후 무부하가압 - 362kV 현대제 유사고장 관련","2019-09-27 09:00","2019-09-27 18:00","2019-09-27 09:00","2019-09-27 18:00","당일"]
[104,"대전충남","서산","태안T/P #1 M.Tr A","19년도 서산P/O 변전정비회사 총액공사","- 태안화력 345kV #1M.Tr 보통점검 - 태안화력 #1M.Tr 1차 GIS(7871) 정밀점검 및 절연롯드 교체작업","2019-09-23 09:00","2019-09-27 18:00","2019-09-26 09:00","2019-09-27 18:00","연속"]
[105,"대전충남","세종","세종S/S #2 M.Tr","세종S/S #2M.Tr 감시 카메라 교체작업","#2M.Tr 상부 감시 폐쇄회로 카메라 고장으로 인한 휴전 후 교체작업","2019-09-24 09:00","2019-09-24 18:00","2019-09-24 09:00","2019-09-24 18:00","당일"]
[106,"대전충남","아산","신온양S/S 345kV 신온양-신탕정#1T/L TIE CB A (7900)","신온양S/S 345kV 7900 GIS 보통점검","신온양S/S 345kV 7900 GIS 보통점검","2019-09-27 09:00","2019-09-27 18:00","2019-09-27 09:00","2019-09-27 18:00","당일"]
[107,"대전충남","아산","청양신온양#2 T/L","[송전]345kV청양-신온양#2T/L 정밀점검","345kV청양-신온양#2T/L No.89~150호 정밀점검","2019-09-28 08:00","2019-10-01 18:00","2019-09-28 09:00","2019-09-29 18:00","매일"]
[108,"대전충남","아산","신탕정S/S #2 M.TR","신탕정S/S 345kV #2M.Tr실 상부 배기팬 보수","신탕정S/S 345kV #2M.Tr실 상부 배기팬 보수","2019-09-25 09:00","2019-09-25 18:00","취소","취소","당일"]
[109,"대전충남","청양","청양보령화력#2T/L","345kV 청양-보령#2T/L 정밀점검 공사","1~86호 정밀점검","2019-09-23 09:00","2019-09-30 18:00","취소","취소","매일"]
[110,"대전충남","서산","신서산아산#1 T/L","345kV 신서산-신당진#2T/L 피뢰기 설치공사 ","신서산-신당진T/L 피뢰기 설치공사 (4회선 병가구간 안전이격 휴전) ","2019-09-21 07:30","2019-09-22 18:00","2019-09-21 07:30","2019-09-22 18:00","매일"]
[111,"대전충남","서산","신서산신당진#2 T/L","345kV 신서산-신당진#2T/L 피뢰기 설치공사 ","신서산-신당진T/L 피뢰기 설치공사 No.7~32 (4회선구간) ","2019-09-21 07:30","2019-09-22 18:00","2019-09-21 07:30","2019-09-22 18:00","매일"]
[112,"전북","직할","북경남무주양수 T/L","345kV 북경남2분기T/L 항공장애표시구 설치공사","1.항공장애표시구 설치(No.14~15, 89~90) ※관련 근거 : 공항시설법 기준 2.절연저항 측정 및 불량애자 교체 ※관련 근거 : 가공송전운영업무 기준","2019-09-16 08:30","2019-09-18 18:00","2019-09-16 08:30","2019-09-18 18:00","연속"]
[113,"전북","직할","북경남무주양수 T/L","345kV 북경남2분기 항공장애구 설치공사","졀연저항 측정 및 항공장애표시구 설치","2019-09-16 08:30","2019-09-18 18:00","취소","취소","연속"]
[114,"전북","직할","신옥천신남원#2 T/L","345kV 신옥천-신남원T/L 안전이격거리 확보공사","- 철탑교체 : 2기(No.66, 67) - 임시선로 구성(가철탑 1기) 및 기타 부대공사","2019-09-18 07:00","2019-09-23 18:00","2019-09-18 07:00","2019-09-23 18:00","연속"]
[115,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L 안전이격거리 확보공사","- 철탑교체 : 2기(No.66, 67) - 임시선로 구성(가철탑 1기) 및 기타 부대공사","2019-09-16 07:00","2019-09-17 18:00","2019-09-16 07:00","2019-09-17 18:00","연속"]
[116,"전북","직할","신남원의령#1 T/L","345kV 신남원-의령T/L 항공구 설치공사","항공구 설치 - No.138~139 등 4경간","2019-09-30 07:00","2019-10-01 18:00","2019-09-30 07:00","2019-10-01 18:00","매일"]
[117,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L 안전이격거리 확보공사","- 철탑교체 : 2기(No.66, 67) - 임시선로 구성(가철탑 1기) 및 기타 부대공사","2019-09-24 07:00","2019-09-29 18:00","2019-09-24 07:00","2019-09-29 18:00","연속"]
[118,"광주전남","강진","신강진광양#2 T/L","신강진S/S 345kV 취약설비 GIS화","345kV 옥외 철구 -> 345kV GIS 화 (75BAY)","2019-09-02 09:00","2019-11-22 18:00","2019-09-02 09:00","2019-11-22 18:00","연속"]
[119,"광주전남","강진","신강진S/S #3 M.Tr","신강진S/S 345kV 취약설비 GIS화","345kV 옥외 철구 -> 345kV GIS 화 (75BAY)","2019-09-02 09:00","2019-11-22 18:00","2019-09-02 09:00","2019-11-22 18:00","연속"]
[120,"광주전남","강진","신강진S/S 345KV #1 BUS CB(철구)","신강진S/S 345kV 취약설비 GIS화","345kV 옥외 철구 -> 345kV GIS 화 (75BAY)","2019-09-02 09:00","2019-11-22 18:00","2019-09-02 09:00","2019-11-22 18:00","연속"]
[121,"광주전남","강진","신강진S/S 345kV #2 BUS CB(철구)","신강진S/S 345kV 취약설비 GIS화","345kV 옥외 철구 -> 345kV GIS 화 (75BAY)","2019-09-02 09:00","2019-11-22 18:00","2019-09-02 09:00","2019-11-22 18:00","연속"]
[122,"광주전남","광주","신광주S/S #2 M.Tr","신광주S/S 345kV #2 M.Tr 휴전작업(19년 광주변전총액공사)","신광주 #2M.Tr 1차 LA 대체, 2차 LA 대체, 3차 LA 보통점검 신광주 #2M.Tr 1차 CVT 보통점검, 3차 CVT 보통점검 신광주 #2M.Tr 2차 GIS 하자점검 신광주 #2M.Tr 3차 VCB(4284) 보통점검 신광주 #2M.Tr 3차 VCB(4279-1,2) 장기미동작 차단기점검 신광주 #2M.Tr 3차 DS(4286, 4275-1,2) 보통점검","2019-09-25 10:00","2019-09-27 18:00","2019-09-25 10:00","2019-09-27 18:00","연속"]
[123,"광주전남","광주","신광주S/S #1 M.Tr","19년 광주변전총액(LA,GIS,VCB,DS 점검)","1. 345kV #1M.Tr 1차 LA 초기점검 2. 154kV #1M.Tr 2차 GIS 하자점검(박진아) 3. VCB 점검 : 4184(보통), 4179-1,2(장기미동작점검) 4. 단로기 보통점검 : 4186,4185,4175-1,4175-2 5. 분로리액터 하자점검 : #1-2Sh.R","2019-09-23 09:00","2019-09-24 18:00","2019-09-23 09:00","2019-09-24 18:00","연속"]
[124,"광주전남","광주","신광주신화순#1 T/L","신화순S/S 신광주-신화순#1T/L (변전협력회사공사)","신화순S/S 신광주-신화순#1T/L 1ST, 2ND PNL 교체,77BAY BF PNL 교체 신광주S/S 신광주-신화순#1T/L 1ST, 2ND PNL 교체","2019-09-30 09:00","2019-10-16 18:00","2019-09-30 09:00","2019-10-16 18:00","연속"]
[125,"광주전남","광주","신화순S/S #2 M.Tr","신화순S/S 345kV #2M.Tr 휴전 (변전협력회사공사)","신화순S/S 신광주-신화순#1T/L 1ST, 2ND PNL 교체,77BAY BF PNL 교체 신광주S/S 신광주-신화순#1T/L 1ST, 2ND PNL 교체,77BAY BF PNL 교체","2019-09-30 09:00","2019-10-16 18:00","2019-09-30 09:00","2019-10-16 18:00","연속"]
[126,"광주전남","순천","광양S/S #3 M.Tr","18-19년도 변전정비회사 총액공사(기계적보호장치 회로변경)","기계적보호장치 경보운전 관련 회로보완","2019-09-25 10:00","2019-09-25 18:00","2019-09-25 10:00","2019-09-25 18:00","당일"]
[127,"광주전남","순천","광양S/S #2 M.Tr","18-19년도 변전정비회사 총액공사(기계적보호장치 회로변경)","기계적보호장치 경보운전 관련 회로보완","2019-09-24 10:00","2019-09-24 18:00","2019-09-24 10:00","2019-09-24 18:00","당일"]
[128,"광주전남","순천","광양S/S #1 M.Tr","18-19년도 변전정비회사 총액공사(기계적보호장치 회로변경)","기계적보호장치 경보운전 관련 회로보완","2019-09-23 10:00","2019-09-23 18:00","2019-09-23 10:00","2019-09-23 18:00","당일"]
[129,"광주전남","순천","여수T/P #3 Tie-Tr","18-19년도 변전정비회사 총액공사(기계적보호장치 회로변경)","기계적보호장치 경보운전 관련 회로보완","2019-09-27 10:00","2019-09-27 18:00","2019-09-27 10:00","2019-09-27 18:00","당일"]
[130,"광주전남","순천","여수T/P #2 Tie-Tr","18-19년도 변전정비회사 총액공사(기계적보호장치 회로변경)","기계적보호장치 경보운전 관련 회로보완","2019-09-26 10:00","2019-09-26 18:00","2019-09-26 10:00","2019-09-26 18:00","당일"]
[131,"대구","경산","신경산S/S #1 M.Tr","신경산S/S 345kV #1M.Tr 휴전","#1M.Tr 보호반 대체","2019-09-02 09:00","2019-09-06 18:00","2019-09-02 09:00","2019-09-06 18:00","연속"]
[132,"대구","경산","신경산S/S 345kV #70 BUS","신경산S/S 362kV GIS 대체공사","71BAY 7171CB, 7151, 7161DS 철거 및 설치","2019-09-25 09:00","2019-10-03 09:00","2019-09-25 09:00","2019-10-03 09:00","연속"]
[133,"대구","경산","신경산S/S 345kV #75 BUS","신경산S/S 362kV GIS 대체공사","71BAY측 7172CB, 7152DS, 7162DS 철거 및 설치","2019-09-17 09:00","2019-09-25 09:00","2019-09-17 09:00","2019-09-25 09:00","연속"]
[134,"대구","경산","신경산대구#1 T/L","신경산S/S 362kV GIS 대체공사","71BAY GIS 대체","2019-09-17 09:00","2019-11-05 18:00","2019-09-17 09:00","2019-11-05 18:00","연속"]
[135,"대구","경산","신경산S/S #2 M.Tr","신경산S/S 362kV GIS 대체공사","71BAY GIS 대체","2019-09-17 09:00","2019-11-05 18:00","2019-09-17 09:00","2019-11-05 18:00","연속"]
[136,"대구","경산","신경산대구#2 T/L","회전형 스페이서 설치공사 안전확보","154kV 경산-자인#1T/L 회전형 스페이서 설치공사 안전확보용 -No.56~57, 67~68, 74~75","2019-09-06 08:00","2019-09-06 18:00","2019-09-06 08:00","2019-09-06 18:00","당일"]
[137,"대구","경산","신경산대구#2 T/L","신경산S/S 362kV GIS 대체공사","#2BUS 접속 건전성확인 무부하 가압용 선로","2019-09-24 18:00","2019-09-25 09:00","2019-09-24 18:00","2019-09-25 09:00","연속"]
[138,"대구","달성","고령S/S #4 M.Tr","고령S/S 78B/F PNL 대체작업","고령S/S 78B/F PNL 대체작업","2019-09-17 09:00","2019-09-25 18:00","취소 ","취소","연속"]
[139,"대구","달성","고령S/S #3 M.Tr","고령S/S 76B/F PNL 대체작업","고령S/S 76B/F PNL 대체작업","2019-09-02 09:00","2019-09-10 18:00","취소 ","취소","연속"]
[140,"대구","달성","북경남고령#1 T/L","고령S/S 78B/F PNL 대체작업","고령S/S 78B/F PNL 대체작업","2019-09-17 09:00","2019-09-25 18:00","취소 ","취소","연속"]
[141,"대구","달성","북경남고령#2 T/L","345kV 북경남1분기T/L 항공장애표시구 설치공사","1.항공장애표시구 설치(No.20~24, 26~30) ※관련 근거 : 공항시설법 기준","2019-09-26 08:30","2019-09-28 18:00","취소 ","취소","연속"]
[142,"대구","달성","서대구고령#1 T/L","고령S/S 76B/F PNL 대체작업","고령S/S 76B/F PNL 대체작업","2019-09-02 09:00","2019-09-10 18:00","취소 ","취소","연속"]
[143,"대구","달성","북경남대구#2 T/L","345kV 북경남1분기T/L 항공장애표시구 설치공사","1.항공장애표시구 설치(No.20~24, 26~30) ※관련근거 : 공항시설법 기준","2019-09-26 08:30","2019-09-28 18:00","취소 ","취소","연속"]
[144,"대구","달성","북경남대구#1 T/L","345kV 북경남1분기T/L 항공장애표시구 설치공사","1.항공장애표시구 설치(No.20~24, 26~30) ※관련근거 : 공항시설법 기준","2019-09-18 08:30","2019-09-20 18:00","취소 ","취소","연속"]
[145,"대구","칠곡","북대구S/S 345kV 북대구-서대구#2T/L CB A (7371)","북대구S/S 북대구-서대구#2T/L CB 장기미동작점검","북대구S/S 북대구-서대구#2T/L CB 장기미동작점검","2019-09-19 09:30","2019-09-19 12:00","2019-09-19 09:30","2019-09-19 12:00","당일"]
[146,"대구","칠곡","북대구S/S 345kV 서대구#2T/L-#1 M.Tr 1차 TIE CB A (7300)","북대구S/S 북대구-서대구#2T/L TIE CB 장기미동작점검","북대구S/S 북대구-서대구#2T/L TIE CB 장기미동작점검","2019-09-19 13:00","2019-09-19 15:00","2019-09-19 13:00","2019-09-19 15:00","당일"]
[147,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S #2M.Tr 2차 6242DS PD발생 조치","북대구S/S #2M.Tr 2차 6242DS PD발생 조치","2019-09-25 09:30","2019-09-26 18:00","2019-09-25 09:30","2019-09-26 18:00","연속"]
[148,"대구","칠곡","북경남서대구#1 T/L","345kV 북경남2분기T/L 항공장애표시구 설치공사","1.항공장애표시구 설치(No.14~15, 89~90)] ※관련 근거 : 공항시설법 기준 2.절연저항 측정 및 불량애자 교체 ※관련 근거 : 가공송전운영업무 기준","2019-09-16 08:30","2019-09-18 18:00","취소 ","취소","연속"]
[149,"대구","칠곡","북경남서대구#2 T/L","345kV 북경남2분기T/L 항공장애표시구 설치공사","1.항공장애표시구 설치(No.14~15, 89~90) ※관련 근거 : 공항시설법 기준 2.절연저항 측정 및 불량애자 교체 ※관련 근거 : 가공송전운영업무 기준","2019-09-19 08:30","2019-09-20 18:00","취소 ","취소","연속"]
[150,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S #3M.Tr 1,2차 CB 점검","서대구S/S #3M.Tr 1,2차 CB 점검","2019-09-27 09:30","2019-09-27 18:00","2019-09-27 09:30","2019-09-27 18:00","당일"]
[151,"대구","칠곡","서대구고령#2 T/L","서대구S/S 서대구-고령#2T/L CVT 이음발생관련 점검","서대구S/S 서대구-고령#2T/L CVT 이음발생관련 점검","2019-09-17 09:30","2019-09-17 18:00","취소 ","취소","당일"]
[152,"대구","포항","신포항신월성NP#2 T/L","항공장애 주간표지 및 항공장애등 정비공사","항공장애표시구 설치 No.3-4 등 4개소","2019-09-03 08:00","2019-09-03 18:00","2019-09-03 08:00","2019-09-03 18:00","당일"]
[153,"대구","포항","신포항신월성NP#1 T/L","항공장애 주간표지 및 항공장애등 정비공사","항공장애표시구 설치 No.3-4 등 4개소","2019-09-02 08:00","2019-09-02 18:00","2019-09-02 08:00","2019-09-02 18:00","당일"]
[154,"대구","포항","신포항신영일 T/L","신포항-신영일T/L 보호반 대체작업","신포항-신영일T/L 보호반 대체작업","2019-09-23 09:00","2019-09-27 18:00","취소 ","취소","연속"]
[155,"대구","포항","신포항S/S #3 M.Tr","신포항 #3M.Tr 누유개소 보수","신포항 #3M.Tr 누유개소 보수 및 절연유 PCB정화작업","2019-09-30 09:00","2019-10-03 18:00","2019-09-30 09:00","2019-10-03 18:00","연속"]
[156,"대구","포항","신포항신월성NP#3 T/L","345kV 신포항-신월성NP#3,4 등2개T/L 스페이서 댐퍼 교체공사","No.4~30 호 스페이서 댐퍼 교체","2019-09-23 08:00","2019-09-27 18:00","2019-09-23 08:00","2019-09-27 18:00","연속"]
[157,"대구","포항","울주월성NP#1 T/L","345kV 신포항-신월성NP#3,4 등2개T/L 스페이서 댐퍼 교체공사","No.4~30 호 스페이서 댐퍼 교체","2019-09-23 08:00","2019-09-27 18:00","2019-09-23 08:00","2019-09-27 18:00","연속"]
[158,"경북","구미","북대구선산 T/L","2019년 가공송전 순시점검 위탁공사","345kV 서대구-선산#1,2T/L 북대구-선산 및 선산-신포항T/L - 현수애자 절연성능진단 시행결과 현수애자 불량의심개소 발견 - 휴전 후 절연저항 측정 후 애자 교체작업 시행 - 345kV 서대구-선산#1T/L : 10장, 서대구-선산#2T/L : 10장 - 345kV 북대구-선산T/L : 2장, 선산-신포항T/L : 1장","2019-09-04 09:00","2019-09-04 18:00","2019-09-04 09:00","2019-09-04 18:00","당일"]
[159,"경북","구미","서대구선산#2 T/L","2019년 가공송전 순시점검 위탁공사","345kV 서대구-선산#1,2T/L 북대구-선산 및 선산-신포항T/L - 현수애자 절연성능진단 시행결과 현수애자 불량의심개소 발견 - 휴전 후 절연저항 측정 후 애자 교체작업 시행 - 345kV 서대구-선산#1T/L : 10장, 서대구-선산#2T/L : 10장 - 345kV 북대구-선산T/L : 2장, 선산-신포항T/L : 1장","2019-09-05 09:00","2019-09-09 18:00","2019-09-05 09:00","2019-09-09 18:00","매일"]
[160,"경북","구미","선산신포항 T/L","2019년 가공송전 순시점검 위탁공사","345kV 서대구-선산#1,2T/L 북대구-선산 및 선산-신포항T/L - 현수애자 절연성능진단 시행결과 현수애자 불량의심개소 발견 - 휴전 후 절연저항 측정 후 애자 교체작업 시행 - 345kV 서대구-선산#1T/L : 10장, 서대구-선산#2T/L : 10장 - 345kV 북대구-선산T/L : 2장, 선산-신포항T/L : 1장","2019-09-09 09:00","2019-09-09 18:00","2019-09-09 09:00","2019-09-09 18:00","당일"]
[161,"경북","구미","서대구선산#1 T/L","2019년 가공송전 순시점검 위탁공사","345kV 서대구-선산#1,2T/L 북대구-선산 및 선산-신포항T/L - 현수애자 절연성능진단 시행결과 현수애자 불량의심개소 발견 - 휴전 후 절연저항 측정 후 애자 교체작업 시행 - 345kV 서대구-선산#1T/L : 10장, 서대구-선산#2T/L : 10장 - 345kV 북대구-선산T/L : 2장, 선산-신포항T/L : 1장","2019-09-02 09:00","2019-09-04 18:00","2019-09-02 09:00","2019-09-04 18:00","매일"]
[162,"경북","영주","신영주한울NP2#1 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #1T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #1T/L GIB용 보호반 설치","2019-09-02 10:00","2019-09-06 15:00","2019-09-02 10:00","2019-09-06 15:00","연속"]
[163,"경북","영주","신영주한울NP2#2 T/L","345kV 신영주S/S TCSC 설치공사","- TCSC 555.28MVar × 2조 설치 - 신영주S/S 신영주-한울NP2 #2T/L 송전선로보호반 개조 × 1식 - 신영주S/S 신영주-한울NP2 #2T/L GIB용 보호반 설치","2019-09-16 10:00","2019-09-20 15:00","2019-09-16 10:00","2019-09-20 15:00","연속"]
[164,"경북","직할","안동C/C 신영주-안동CC T/L GIS(7271)","18~19년 경북본부 직할 변전정비회사 총액공사","안동복합S/S 7271GIS 조작시험","2019-09-05 13:00","2019-09-05 15:00","2019-09-05 13:00","2019-09-05 15:00","당일"]
[165,"경북","직할","안동CC #1 Tie-Tr","18~19년 경북본부 직할 변전정비회사 총액공사","안동복합S/S #1M.Tr 1차,2차 GIS 조작시험 및 #1M.Tr 초기점검","2019-09-09 09:00","2019-09-10 16:00","2019-09-09 09:00","2019-09-10 16:00","매일"]
[166,"경북","직할","안동C/C 신영일-안동CC T/L GIS(7371)","18~19년 경북본부 직할 변전정비회사 총액공사","안동복합S/S 7371GIS 조작시험","2019-09-05 10:00","2019-09-05 12:00","2019-09-05 10:00","2019-09-05 12:00","당일"]
[167,"경북","직할","안동C/C 345kV #2M.Tr 1차 GIS(7272)","18~19년 경북본부 직할 변전정비회사 총액공사","안동복합S/S 7272GIS 조작시험","2019-09-05 15:00","2019-09-05 17:00","2019-09-05 15:00","2019-09-05 17:00","당일"]
[168,"경북","직할","청송P/P 신포항-청송PP T/L-#2M.Tr 2차 TIE GIS(7200)","18~19년 경북본부 직할 변전정비회사 총액공사","청송양수S/Y 7200GIS 조작시험","2019-09-03 13:00","2019-09-03 15:00","2019-09-16 13:00","2019-09-16 15:00","당일"]
[169,"경북","직할","청송P/P 청송P/P 신포항-청송PP T/L GIS(7271)","18~19년 경북본부 직할 변전정비회사 총액공사","청송양수S/Y 7271GIS 조작시험","2019-09-03 10:00","2019-09-03 12:00","2019-09-16 10:00","2019-09-16 12:00","당일"]
[170,"경북","직할","청송P/P #2 M.Tr 2차 GIS(7272)","18~19년 경북본부 직할 변전정비회사 총액공사","청송양수S/Y 7272GIS 조작시험","2019-09-03 15:00","2019-09-03 17:00","2019-09-16 15:00","2019-09-16 17:00","당일"]
[171,"경북","직할","청송P/P 신영주-청송PP T/L GIS(7171)","18~19년 경북본부 직할 변전정비회사 총액공사","청송양수S/Y 7171GIS 조작시험","2019-09-02 10:00","2019-09-02 12:00","2019-09-04 10:00","2019-09-04 12:00","당일"]
[172,"경북","직할","청송P/P 신영주-청송PP T/L-#1M.Tr 2차 TIE GIS(7100)","18~19년 경북본부 직할 변전정비회사 총액공사","청송양수S/Y 7100GIS 조작시험","2019-09-02 13:00","2019-09-02 15:00","2019-09-04 13:00","2019-09-04 15:00","당일"]
[173,"부산울산","동부산","고리2N/P 345kV #76 BUS","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 362kV 7672,7600GIS 구조개선관련 시험가압(#76BUS)","2019-09-06 18:00","2019-09-07 18:00","2019-09-06 18:00","2019-09-07 18:00","연속"]
[174,"부산울산","동부산","신양산신대연#1 T/L","154kV 시랑분기T/L 건설공사","154kV 시랑분기T/L 계통연결 작업을 위한 안전거리확보 (상단 : 345kV 신양산-신대연T/L, 하단 : 154kV 신양산-좌동T/L) - 전력선 긴선 및 가공지선설치 : 기설 신양산-좌동#2T/L 16호 - 신설 1호, 기설 17호 - 신설 1호","2019-09-16 08:00","2019-09-21 18:00","2019-09-16 08:00","2019-09-21 18:00","연속"]
[175,"부산울산","동부산","신양산S/S #3 M.TR","신양산E/C 345kV M.Tr 보호PNL 대체","신양산E/C 345kV M.Tr 보호PNL 대체(#3M.Tr)","2019-09-23 09:30","2019-09-27 18:00","2019-09-23 09:30","2019-09-27 18:00","연속"]
[176,"부산울산","동부산","신양산신대연#2 T/L","154kV 시랑분기T/L 건설공사","154kV 시랑분기T/L 계통연결 작업을 위한 안전거리확보 (상단 : 345kV 신양산-신대연T/L, 하단 : 154kV 신양산-좌동T/L) - 전력선 긴선 및 가공지선설치 : 기설 신양산-좌동#1T/L 16호 - 신설 1호, 기설 17호 - 신설 1호","2019-09-28 08:00","2019-10-01 18:00","2019-09-28 08:00","2019-10-01 18:00","연속"]
[177,"부산울산","북부산","북부산S/S 345kV 신양산-북부산#1T/L CB ((신)7172)","2019년 북부산 변전협력회사 총액공사","북부산E/C 345kV 신양산-북부산#1T/L 7172 GIS 초기점검","2019-09-27 09:00","2019-09-27 18:00","2019-09-27 09:00","2019-09-27 18:00","당일"]
[178,"부산울산","북부산","북부산S/S #1 M.Tr","2019년 북부산 변전협력회사 총액공사","북부산E/C 345kV #1M.Tr 1,2차 GIS 초기점검","2019-09-24 09:00","2019-09-24 18:00","2019-09-24 09:00","2019-09-24 18:00","당일"]
[179,"부산울산","울산","동울산신울산#2 T/L","울산전력지사 관내 OPGW 항공장애표시구 설치공사","345㎸ 동울산-신울산#2T/L No.104호~No.105호 구간 항공장애표시구 설치","2019-09-25 08:00","2019-09-26 18:00","2019-09-25 08:00","2019-09-26 18:00","연속"]
[180,"부산울산","울산","동울산신울산#1 T/L","345kV 동울산-신울산#1T/L 항공장애표시구 설치공사","ㅇ 항공장애표시구 설치 : No.78~81, 97~98, 104~105 [감사원 설비관리 실태점검 감사 지적사항 조치]","2019-09-23 08:00","2019-09-24 18:00","2019-09-23 08:00","2019-09-24 18:00","매일"]
[181,"부산울산","울산","신온산S/S 345kV 신온산T/L-TIE CB(7300)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 신온산S/S 345kV 신온산T/L-TIE 7300CB 휴전 - 7309-6ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-23 15:00","2019-09-23 17:00","2019-09-23 15:00","2019-09-23 17:00","당일"]
[182,"부산울산","울산","신온산S/S 345kV 북부산-신온산T/L CB(7371)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 신온산S/S 345kV 북부산-신온산T/L 7371CB 휴전 - 7309-1ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-23 11:00","2019-09-23 13:00","2019-09-23 11:00","2019-09-23 13:00","당일"]
[183,"부산울산","울산","신온산S/S 345kV 신울산-신온산#1T/L CB(7271)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","신온산S/S 345kV 신울산-신온산#1T/L 7271CB 휴전 - 7209-1ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-23 09:00","2019-09-23 11:00","2019-09-23 09:00","2019-09-23 11:00","당일"]
[184,"부산울산","울산","신온산S/S 345kV #1 M.Tr 1차 CB(7272)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 신온산S/S 345kV #1 M.Tr 1차 7272CB 휴전 - 7209-6ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-23 13:00","2019-09-23 15:00","2019-09-23 13:00","2019-09-23 15:00","당일"]
[185,"부산울산","울산","신온산S/S 345kV 신온산-울산TPT/L CB(7471)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 신온산S/S 345kV 신온산-울산TPT/L 7471CB 휴전 - 7409-1ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-24 09:00","2019-09-24 11:00","2019-09-24 09:00","2019-09-24 11:00","당일"]
[186,"부산울산","울산","신온산S/S 345kV #2 M.Tr 1차 CB(7472)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 신온산S/S 345kV #2 M.Tr 1차 7472CB 휴전 - 7409-6ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-24 11:00","2019-09-24 13:00","2019-09-24 11:00","2019-09-24 13:00","당일"]
[187,"부산울산","울산","신온산S/S 345kV #3 M.Tr 1차 CB(7572)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 신온산S/S 345kV #3 M.Tr 1차 7572CB 휴전 - 7509-6ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-24 13:00","2019-09-24 15:00","2019-09-24 13:00","2019-09-24 15:00","당일"]
[188,"부산울산","울산","신울산S/S #2 M.Tr","18~19년 변전협력 총액공사","- 신울산S/S 345kV #2M.Tr 2차 6264GCB 차단기 동작시험","2019-09-27 09:00","2019-09-27 18:00","2019-09-27 09:00","2019-09-27 18:00","당일"]
[189,"부산울산","울산","울산C/C 345kV 북부산T/L-기력5호기 1차 TIE CB(7500)","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산복합S/Y 7500GIS 보통점검","2019-09-24 09:00","2019-09-24 18:00","2019-09-24 09:00","2019-09-24 18:00","당일"]
[190,"부산울산","울산","북부산울산TP T/L","송전선로 항공장애 표시등 및 주간표지 설치공사","항공도장 : 7~8호(2기)","2019-09-30 09:00","2019-10-02 18:00","2019-09-30 09:00","2019-10-02 18:00","연속"]
[191,"부산울산","울산","울주S/S #4 M.Tr","18~19년 변전협력 총액공사","- 울주S/S 345kV #4M.Tr 보호반 교체작업","2019-09-23 09:00","2019-09-27 18:00","취소","취소","연속"]
[192,"부산울산","울산","울주월성NP#1 T/L","YPP제 345kV 송전선로 보호반 성능개선작업","- 울주S/S 7971, 7900GIS 보통점검 - CVT, LA교체 - PITR 정기점검(병행)","2019-09-30 09:00","2019-10-02 18:00","취소","취소","연속"]
[193,"부산울산","울산","울주S/S 345kV 울주-월성NP#2T/L CB(7A71)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 울주S/S 345kV 울주-월성NP#2T/L 7A71CB휴전 - 7A09-1ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-26 13:00","2019-09-26 15:00","2019-09-26 13:00","2019-09-26 15:00","당일"]
[194,"부산울산","울산","울주S/S 345kV #4 M.Tr 1차 CB(7872)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 울주S/S 345kV #4 M.Tr 1차 7872CB휴전 - 7809-6ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-26 11:00","2019-09-26 13:00","2019-09-26 11:00","2019-09-26 13:00","당일"]
[195,"부산울산","울산","울주S/S 345kV 울주-고리NP#2T/L TIE CB(7500)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 울주S/S 345kV 울주-고리NP#2T/L TIE 7500CB 휴전 - 7509-6ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-30 13:30","2019-09-30 15:00","2019-09-30 13:30","2019-09-30 15:00","당일"]
[196,"부산울산","울산","울주S/S 345kV 울주-고리NP#2T/L CB(7571)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 울주S/S 345kV 울주-고리NP#2T/L 7571CB휴전 - 7509-1ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-30 12:00","2019-09-30 13:30","2019-09-30 12:00","2019-09-30 13:30","당일"]
[197,"부산울산","울산","울주고리NP#2 T/L","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 362kV 7C72,7C00GIS 구조개선관련 시험가압(울주-고리#2T/L)","2019-09-27 18:00","2019-09-28 18:00","2019-09-27 18:00","2019-09-28 18:00","연속"]
[198,"부산울산","울산","울주S/S 345kV #3 M.Tr 1차 CB(7672)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 울주S/S 345kV #3 M.Tr 1차 7672CB - 7609-6ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-27 13:30","2019-09-27 15:00","2019-09-27 13:30","2019-09-27 15:00","당일"]
[199,"부산울산","울산","울주S/S 345kV 울주-고리NP#1T/L CB(7671)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 울주S/S 345kV 울주-고리NP#1T/L C7671CB 휴전 - 7609-1ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-27 12:00","2019-09-27 13:30","2019-09-27 12:00","2019-09-27 13:30","당일"]
[200,"부산울산","울산","울주S/S 345kV 울주-월성NP#2T/L TIE CB(7A00)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 울주S/S 345kV 울주-월성NP#2T/L TIE 7A00CB 휴전 - 7A09-6ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-26 15:00","2019-09-26 17:00","2019-09-26 15:00","2019-09-26 17:00","당일"]
[201,"부산울산","울산","울주S/S 345kV 울주-신경산#1T/L CB(7871)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 울주S/S 345kV 울주-신경산#1T/L 7871CB 휴전 - 7809-1ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-26 09:00","2019-09-26 11:00","2019-09-26 09:00","2019-09-26 11:00","당일"]
[202,"부산울산","울산","울주S/S 345kV 울주-신경산#2T/L TIE CB(7700)","울주S/S 345kV #75BUS 고장발생관련 재발방지대책","- 울주S/S 345kV 울주-신경산#2T/L TIE 7700CB - 7709-6ES 조작함 내 구속핀 걸림량 개선품 교체","2019-09-27 15:00","2019-09-27 16:30","2019-09-27 15:00","2019-09-27 16:30","당일"]
[203,"경남","직할","신마산신김해#1 T/L","2018-2019 경남 직할 송전협력회사 총액공사","345kV 신마산-신김해#1,2T/L 12-15호 중단 전력선 교체(직선 슬리브 제거)","2019-09-16 07:00","2019-09-18 18:00","2019-09-16 07:00","2019-09-18 18:00","연속"]
[204,"경남","직할","신마산신김해#2 T/L","2018-2019 경남 직할 송전협력회사 총액공사","345kV 신마산-신김해#1,2T/L 12-15호 중단 전력선 교체(직선 슬리브 제거)","2019-09-19 07:00","2019-09-21 18:00","2019-09-19 07:00","2019-09-21 18:00","연속"]
[205,"경남","직할","신김해S/S #3 M.Tr","19년도 직할 170kV GIS 정밀점검","신김해S/S #1-2 Sh.C GCB 정밀점검 시험가압선로 : #3M.Tr , #62BUS","2019-09-27 16:30","2019-09-27 18:00","2019-09-27 16:30","2019-09-27 18:00","당일"]
[206,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산T/L 78호 지장송전선로 이설공사","345kV 신김해-북부산T/L 77~81호 간 지장이설공사[본탑 1기, 계탑 1기]","2019-09-23 07:00","2019-10-04 18:00","2019-09-23 07:00","2019-10-04 18:00","연속"]
[207,"경남","직할","창원삼천포TP#1 T/L","345kV 창원-삼천포화력T/L 102-105호 등 5개구간 전력선 교체","전선접속개소(직선슬리브 제거) 전력선 교체 및 노후금구류(스페이서댐퍼)교체","2019-09-23 07:00","2019-10-12 18:00","2019-09-23 07:00","2019-10-12 18:00","연속"]
[208,"경남","진주","의령산청양수#1 T/L","345kV 의령-산청양수#1T/L 21~22호 항공장애표시구 정비","○ 345kV 의령-산청양수#1T/L 21~22호 구간 항공장애표시구 정비 - 정비물량 : 항공장애표시구 2개 정비(소음방지 충진제 시공)","2019-09-17 07:00","2019-09-17 12:00","2019-09-17 07:00","2019-09-17 12:00","당일"]
[209,"경남","진주","의령S/S #3 M.Tr","의령S/S #3M.Tr 하자점검","의령S/S #3M.Tr 하자점검 의령S/S #3M.Tr 1, 2차 CB(7872, 6344) 하자점검","2019-09-09 09:00","2019-09-10 18:00","2019-09-09 09:00","2019-09-10 18:00","연속"]
[210,"경남","진주","의령하동화력#2 T/L","의령S/S 의령-하동화력#2T/L CPD 대체작업","의령S/S 의령-하동화력#2T/L CPD 대체작업","2019-09-26 09:00","2019-09-28 18:00","2019-09-26 09:00","2019-09-28 18:00","연속"]
[211,"경남","진주","의령산청양수#2 T/L","의령S/S 345kV 73 Bay B/F PNL 대체공사","의령S/S 345kV 73 Bay B/F PNL 대체공사","2019-09-17 13:00","2019-09-20 18:00","2019-09-17 13:00","2019-09-20 18:00","연속"]
[212,"경남","진주","의령S/S #1 M.Tr","의령S/S 345kV 73 Bay B/F PNL 대체공사","의령S/S 345kV 73 Bay B/F PNL 대체공사","2019-09-17 13:00","2019-09-20 18:00","2019-09-17 13:00","2019-09-20 18:00","연속"]
[213,"경남","진주","의령하동화력#1 T/L","하동T/P 의령-하동TP#1T/L LA 보통점검","하동T/P 의령-하동TP#1T/L LA 보통점검 의령S/S 의령-하동TP#1T/L LA, PT보통점검","2019-09-29 09:00","2019-09-30 18:00","2019-09-29 09:00","2019-09-30 18:00","연속"]
[214,"경남","진주","하동T/P 345kV #7 M.Tr 1차 CB(7772)","하동T/P #7 M.Tr 1차 CB(7772) 조작시험","하동T/P #7 M.Tr 1차 CB(7772) 조작시험","2019-09-18 14:00","2019-09-18 17:00","2019-09-18 14:00","2019-09-18 17:00","당일"]
[215,"경남","진주","하동T/P 345kV #7 M.Tr 1차 TIE CB(7700)","하동T/P TIE-#7 M.Tr 1차 CB(7700) 조작시험","하동T/P TIE-#7 M.Tr 1차 CB(7700) 조작시험","2019-09-18 10:00","2019-09-18 14:00","2019-09-18 10:00","2019-09-18 14:00","당일"]
[216,"경남","통영","삼천포T/P 345kV #2 G.Tr 1차 CB A (7271)","(신)신고성S/S #2GEN 2차 GIS(7271) 조작시험","(신)신고성S/S #2GEN 2차 GIS(7271) 조작시험","2019-09-20 09:30","2019-09-20 11:30","2019-09-20 09:30","2019-09-20 11:30","당일"]
[217,"경남","통영","삼천포T/P 345kV #3 G.Tr 1차 CB(7371)","삼천포T/P #3GEN GIS(7371) 조작시험","삼천포T/P #3GEN GIS(7371) 조작시험","2019-09-17 09:30","2019-09-17 12:00","2019-09-17 09:30","2019-09-17 12:00","당일"]
[218,"경남","통영","삼천포T/P 345kV 신마산-삼천포화력#2T/L CB(7272)","(신)신고성S/S 신마산-삼천포화력#2T/L GIS(7272) 조작시험","(신)신고성S/S 신마산-삼천포화력#2T/L GIS(7272) 조작시험","2019-09-20 15:00","2019-09-20 18:00","2019-09-20 15:00","2019-09-20 18:00","당일"]
[219,"경남","통영","삼천포T/P 345kV 신마산#2T/L-#2 G.Tr TIE CB(7200)","(신)신고성S/S 신마산#2-#2GEN 2차 GIS(7200) 조작시험","(신)신고성S/S 신마산#2-#2GEN 2차 GIS(7200) 조작시험","2019-09-20 13:00","2019-09-20 15:00","2019-09-20 13:00","2019-09-20 15:00","당일"]
[220,"경남","통영","신마산삼천포화력#1 T/L","345kV 신마산-삼천포화력T/L 정밀점검","1~177호 정밀점검","2019-09-02 08:30","2019-09-10 18:00","2019-09-02 08:30","2019-09-10 18:00","매일"]
[221,"경남","통영","삼천포T/P 345kV #1 G.Tr 1차 CB(7171)","(신)신고성S/S #1GEN GIS(7171) 조작시험","(신)신고성S/S #1GEN GIS(7171) 조작시험","2019-09-19 09:30","2019-09-19 11:30","2019-09-19 09:30","2019-09-19 11:30","당일"]
[222,"경남","통영","삼천포T/P 345kV 창원-삼천포화력#1T/L CB(7572)","삼천포T/P 창원-삼천포화력#T/L GIS(7572) 조작시험","삼천포T/P 창원-삼천포화력#T/L GIS(7572) 조작시험","2019-09-18 15:00","2019-09-18 18:00","2019-09-18 15:00","2019-09-18 18:00","당일"]
[223,"경남","통영","삼천포T/P 345kV 창원#1T/L-TIE#2T/L TIE CB(7500)","삼천포T/P 창원#1-TIE#2T/L GIS(7500) 조작시험","삼천포T/P 창원#1-TIE#2T/L GIS(7500) 조작시험","2019-09-18 13:00","2019-09-18 15:00","2019-09-18 13:00","2019-09-18 15:00","당일"]
[224,"경남","통영","삼천포T/P 345kV 삼천포-TIE#2T/L CB(7571)","삼천포T/P 삼천포-TIE#2T/L GIS(7571) 조작시험","삼천포T/P 삼천포-TIE#2T/L GIS(7571) 조작시험","2019-09-18 09:30","2019-09-18 11:30","2019-09-18 09:30","2019-09-18 11:30","당일"]
[225,"경남","통영","삼천포T/P 345kV 신마산#1T/L-#3 G.Tr 1차 TIE CB(7300)","삼천포T/P #3GEN GIS(7300) 조작시험","삼천포T/P #3GEN GIS(7300) 조작시험","2019-09-17 13:00","2019-09-17 16:00","2019-09-17 13:00","2019-09-17 16:00","당일"]
[226,"경남","통영","(신)삼천포T/P 345kV #1 M.Tr 1차-#1 G.Tr 1차 TIE GIS(7100)","(신)신고성S/S #1M.Tr-#1GEN GIS(7100) 조작시험","(신)신고성S/S #1M.Tr-#1GEN GIS(7100) 조작시험","2019-09-19 13:00","2019-09-19 15:00","2019-09-19 13:00","2019-09-19 15:00","당일"]
[227,"경남","통영","(신)삼천포T/P #1 M.Tr 1차 GIS(7172)","(신)신고성S/S #1M.Tr 1차 GIS(7172) 조작시험","(신)신고성S/S #1M.Tr 1차 GIS(7172) 조작시험","2019-09-19 15:00","2019-09-19 18:00","2019-09-19 15:00","2019-09-19 18:00","당일"]
[228,"경북","한울본부","한울5호기 주변압기 CB(7D00,7D72)","5호기 11차 계획예방정비\n* 조작차단기 : CB 7D00, 7D72","○ 주/소내보조/여자변압기 일반점검 \n○ 소내전원 절체(UAT→SAT)시험","2019-09-26 10:00","2019-11-04 10:00","2019-09-26 10:00","2019-11-04 10:00","연속"]
[229,"경북","한울본부","한울3호기 주변압기 CB(7900,7972)","3호기 15차 계획예방정비 \n* 조작차단기 : CB 7900, 7972","○ 주변압기,소내보조변압기 일반점검","2019-09-04 10:00","2019-10-04 14:00","2019-09-04 10:00","2019-10-04 14:00","연속"]
[230,"부산울산","고리본부","고리4호기\n기동변압기#1 CB(7C00,7C72)","공사명 : 기동변압기#1 휴전\n조작차단기 : 7C00, 7C72","○ 기동변압기 교체공사","2019-09-11 08:00","2019-10-21 23:00","2019-09-11 08:00","2019-10-21 23:00","연속"]
[231,"부산울산","고리본부","고리3호기\n주변압기 CB(7900,7972)","공사명 : 고리3호기 제25차 계획예방정비\n조작차단기 : 7900, 7972","○ 고리3호기 제25차 계획예방정비","2019-09-06 08:00","2020-01-12 23:00","2019-09-06 08:00","2020-01-12 23:00","연속"]
[232,"부산울산","고리본부","고리3호기\n기동변압기#1 CB(7500,7572)","공사명 : 기동변압기#1 휴전\n조작차단기 : 7500, 7572","○ 기동변압기 교체공사","2019-09-16 08:00","2019-09-20 23:00","2019-09-16 08:00","2019-09-20 23:00","연속"]
[233,"부산울산","고리본부","고리3호기\n기동변압기#2 CB(7D00,7D72)","공사명 : 기동변압기#2 휴전\n조작차단기 : 7D00, 7D72","○ 기동변압기 교체공사","2019-09-23 08:00","2019-11-07 23:00","2019-09-23 08:00","2019-11-07 23:00","연속"]
[234,"경북","직할","청송P/P #1M.Tr 2차 GIS(7172)","18~19년 경북본부 직할 변전정비회사 총액공사","청송양수S/Y 7172GIS 조작시험","2019-09-02 15:00","2019-09-02 17:00","2019-09-04 15:00","2019-09-04 17:00","당일"]
[235,"대전충남","아산","청양신온양#2 T/L","[송전]345kV청양-신온양#2T/L 정밀점검","345kV청양-신온양#2T/L No.89~150호 정밀점검","2019-09-21 08:00","2019-09-22 18:00","2019-09-21 08:00","2019-09-22 18:00","매일"]

{"sheet":"154송부","index":2,"n_rows":420,"n_cols":17,"rows_kept":420,"cut":false,"hidden":false,"merged":[[2,16,3,16],[2,15,3,15],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,14,3,14],[2,12,3,12],[2,13,3,13],[2,2,3,2],[2,11,3,11]]}
[]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)","처리사유","Key-point","시송전설비\n여부","계통안정 사유"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","광장S/S 154kV 화양-광장T/L GIS","19년 성동P/O 장기사용 노후배전반 교체공사","광장, 화양S/S 화양광장T/L 보호반 노후대체","2019-09-23 10:00","2019-09-26 17:00","2019-09-23 10:00","2019-09-26 17:00","당일"]
[2,"서울","성동","구의S/S 154kV 천호-구의#2T/L GIS","19년 성동P/O 장기사용 노후배전반 교체공사","구의S/S 천호구의#2T/L 보호배전반 노후대체","2019-09-30 10:00","2019-10-02 17:00","2019-09-30 10:00","2019-10-02 17:00","연속"]
[3,"서울","성동","성동S/S 154kV #61-#66 BUS TIE GIS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-09-24 08:00","2019-09-25 17:30","2019-09-24 08:00","2019-09-25 17:30","연속"]
[4,"서울","성동","성동S/S 154kV #66 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-09-25 15:30","2019-09-25 17:30","2019-09-25 15:30","2019-09-25 17:30","당일"]
[5,"서울","성동","성동S/S 154kV #60-#61 SEC GIS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-09-26 08:00","2019-09-27 17:30","2019-09-26 08:00","2019-09-27 17:30","연속"]
[6,"서울","성동","성동S/S 154kV #60 BUS","2019년 성동P/O 154kV GIS 정밀점검공사","2019년 성동P/O 154kV GIS 정밀점검공사 - 3개 S/S : T/L(9), M.Tr(3), BUS TIE_SEC(4)","2019-09-27 15:30","2019-09-27 17:30","2019-09-27 15:30","2019-09-27 17:30","당일"]
[7,"서울","성동","화양S/S 154kV 화양-성수T/L GIS","19년 성동P/O 관내 154kV 차단기 조작시험","154kV GIS 조작시험 (차단기 개폐타임 측정)","2019-09-11 10:00","2019-09-11 14:00","2019-09-11 10:00","2019-09-11 14:00","당일"]
[8,"서울","중부","동빙고S/S 154kV #60 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-09-24 17:00","2019-09-24 18:00","2019-09-24 17:00","2019-09-24 18:00","당일"]
[9,"서울","중부","동빙고반포#1 T/L","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-09-23 09:00","2019-09-24 18:00","2019-09-23 09:00","2019-09-24 18:00","연속"]
[10,"서울","중부","수색상암#1 T/L","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-09-06 17:00","2019-09-06 18:00","취소","취소","당일"]
[11,"서울","중부","상암S/S 154kV #60 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-09-06 17:00","2019-09-06 18:00","2019-09-06 17:00","2019-09-06 18:00","당일"]
[12,"서울","중부","용산S/S 154kV #65 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-09-27 17:00","2019-09-27 18:00","2019-09-27 17:00","2019-09-27 18:00","당일"]
[13,"서울","중부","중부용산#2 T/L","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-09-27 17:00","2019-09-27 18:00","2019-09-29 09:00","2019-09-29 10:00","당일"]
[14,"서울","중부","은평세종로 T/L","은평S/S 170kV GIS 대체공사(1차분)","은평S/S 170kV GIS 대체공사(1차분) - 은평녹번T/L, 은평세종로T/L GIS","2019-09-30 09:00","2019-10-23 10:00","2019-09-30 09:00","2019-10-23 10:00","연속"]
[15,"서울","중부","은평녹번 T/L","은평S/S 170kV GIS 대체공사(1차분)","은평S/S 170kV GIS 대체공사(1차분) - 은평녹번T/L, 은평세종로T/L GIS","2019-09-30 09:00","2019-10-23 10:00","2019-09-30 09:00","2019-10-23 10:00","연속"]
[16,"서울","중부","중부S/S 154kV #66 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-09-20 17:00","2019-09-20 18:00","2019-09-22 17:00","2019-09-22 18:00","당일"]
[17,"남서울","강남","논현S/S 154kV #65 BUS","논현S/S 논현-선릉#2T/L DS 조작기 보수 관련 시험가압","논현S/S 논현-선릉#2T/L DS 조작기 보수 관련 시험가압","2019-09-18 09:00","2019-09-19 18:00","2019-09-18 09:00","2019-09-19 18:00","연속"]
[18,"남서울","동서울","가락수서#1 T/L","170kV GIS 조작시험","수서S/S 조작시험","2019-09-06 09:30","2019-09-06 14:00","2019-09-06 09:30","2019-09-06 14:00","당일"]
[19,"남서울","동서울","가락수서#2 T/L","170kV GIS 조작시험","수서S/S 조작시험","2019-09-06 14:00","2019-09-06 18:00","2019-09-06 14:00","2019-09-06 18:00","당일"]
[20,"남서울","동서울","잠실강남#1 T/L","차단기 보통점검 및 하자점검","잠실 : 보통점검 강남 : 하자점검","2019-09-16 10:00","2019-09-16 18:00","2019-09-16 10:00","2019-09-16 18:00","당일"]
[21,"남서울","동서울","잠실강남#2 T/L","차단기 보통점검 및 하자점검","잠실 : 보통점검 강남 : 하자점검","2019-09-17 10:00","2019-09-17 18:00","2019-09-17 10:00","2019-09-17 18:00","당일"]
[22,"남서울","동서울","강남선릉#1 T/L","차단기 하자점검 및 조작시험","강남 : 차단기 하자점검 선릉 : 차단기 조작시험","2019-09-19 10:00","2019-09-19 18:00","2019-09-19 10:00","2019-09-19 18:00","당일"]
[23,"남서울","동서울","강남선릉#2 T/L","차단기 하자점검 및 조작시험","강남 : 차단기 하자점검 선릉 : 차단기 조작시험","2019-09-20 10:00","2019-09-20 18:00","2019-09-20 10:00","2019-09-20 18:00","당일"]
[24,"남서울","동서울","동서울가락#2 T/L","170kV GCB 조작시험 및 GIS 보통점검","가락 : 170kV GIS 보통점검","2019-09-05 09:00","2019-09-05 18:00","2019-09-05 09:00","2019-09-05 18:00","당일"]
[25,"남서울","동서울","동서울신장#1 T/L","154kV동서울-신장T/L 이도조정","○대상 : No.8~9 ○내용 : 이도조정","2019-09-23 08:00","2019-09-23 18:00","2019-09-21 08:00","2019-09-21 18:00","당일"]
[26,"남서울","동서울","동서울신장#2 T/L","154kV동서울-신장T/L 이도조정","○대상 : No.8~9 ○내용 : 이도조정","2019-09-24 08:00","2019-09-24 18:00","2019-09-22 08:00","2019-09-22 18:00","당일"]
[27,"남서울","동서울","동서울서종#1 T/L","애자련 보강공사 시행","○대상 : 154kV동서울-서종T/L No.72,73 ○내용 : 현수애자(1련→2련) 보강공사시행","2019-09-25 08:00","2019-09-25 15:00","2019-09-25 08:00","2019-09-25 15:00","당일"]
[28,"남서울","동서울","동서울서종#2 T/L","애자련 보강공사 시행","○대상 : 154kV동서울-서종T/L No.72,73 ○내용 : 현수애자(1련→2련) 보강공사시행","2019-09-25 15:00","2019-09-26 18:00","2019-09-25 15:00","2019-09-26 18:00","연속"]
[29,"남서울","동서울","동서울송파#2 T/L","170kV GCB 하자점검 및 GIS 조작시험","동서울 : 170kV GCB 하자점검 송파 : 170kV GIS 조작시험","2019-09-04 09:00","2019-09-04 18:00","2019-09-04 09:00","2019-09-04 18:00","당일"]
[30,"남서울","동서울","동서울송파#1 T/L","170kV GCB 하자점검 및 GIS 조작시험","동서울 : 170kV GCB 하자점검 송파 : 170kV GIS 조작시험","2019-09-03 09:00","2019-09-03 18:00","2019-09-03 09:00","2019-09-03 18:00","당일"]
[31,"남서울","동서울","강동풍납#1 T/L","154kV 강동-풍납T/L 풍납S/S 인출구간 선종교체공사","선종교체 (OF케이블을 XLPE케이블로 교체)","2019-09-23 09:00","2019-11-07 11:00","2019-09-23 09:00","2019-11-07 11:00","연속"]
[32,"남서울","영등포","광명구공#1 T/L","154kV 광명S/S 인출전력구 OF케이블 선종 교체공사","- 154kV 광명-구공#1, 2T/L 광명SS-JB1 1구간 케이블 212m 교체 등 - 154kV 신광명-광명#1, 2T/L 광명SS-JB8 1구간 케이블 330m 교체 등","2019-09-30 09:00","2019-10-24 18:00","취소","취소","연속"]
[33,"남서울","영등포","당인리목동#2 T/L","154kV당인리-목동T/L 선종교체공사","○ 위 치 : 서울시 강서구 목동 목동S/S, 목동C/H ○ 구 간 : 목동S/S ∼ 목동C/H ○ 케이블 철거 : 154㎸ OF 2000㎟ × 1회선, 3.7㎞ ○ 선종 및 길이 : 154㎸ XLPE 2000㎟ × 1회선, 3.7㎞ ○ 케이블 포설 : 6구간 ○ 케이블 접속 : 보통접속 1개소, 절연접속 4개소 종단접속 2개소","2019-09-18 09:00","2019-12-27 18:00","2019-09-18 09:00","2019-12-27 18:00","연속"]
[34,"남서울","영등포","신광명광명#2 T/L","선도전기 송전선로 보호반 성능개선","87,21Ry 펌웨어 업데이트","2019-09-24 14:00","2019-09-24 17:00","취소","취소","당일"]
[35,"남서울","영등포","신광명광명#1 T/L","신광명S/S 170kV GIS 초기점검","CB동작시간 측정 수분 및 SF6 가스 농도 측정 접촉저항 및 절연저항 측정 경보시험 및 조작시험","2019-09-27 10:00","2019-09-27 18:00","취소","취소","당일"]
[36,"남서울","영등포","부천신정#2 T/L","부천신정#1T/L GIS 정밀점검공사","CB 동작시간측정 절연저항측정 접촉저항측정 수분 및 SF6가스 측정 CT포화시험","2019-09-25 14:00","2019-09-27 18:00","2019-09-25 14:00","2019-09-27 18:00","연속"]
[37,"남서울","영등포","부천신정#1 T/L","부천신정#1T/L GIS 정밀점검공사","CB 동작시간측정 절연저항측정 접촉저항측정 수분 및 SF6가스 측정 CT포화시험","2019-09-23 09:00","2019-09-25 14:00","2019-09-23 09:00","2019-09-25 14:00","연속"]
[38,"남서울","영등포","중동화곡#2 T/L","화곡S/S 중동-화곡#2T/L 보호반 대체","화곡S/S 중동-화곡#2T/L 보호반 대체","2019-09-30 09:00","2019-10-02 18:00","2019-09-25 09:00","2019-09-27 18:00","연속"]
[39,"남서울","직할","봉천신길#1 T/L","154kV 신길인출전력구 OF케이블 선종교체공사","154kV 신길인출전력구 내 154kV 봉천-신길#1T/L 선종교체공사 교체선종 : OF 1200 -&gtXLPE 1200","2019-09-02 09:00","2019-11-06 18:00","2019-09-02 09:00","2019-11-06 18:00","연속"]
[40,"남서울","직할","영등포목동#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-09-23 09:00","2019-09-25 14:00","2019-09-23 09:00","2019-09-25 14:00","연속"]
[41,"남서울","직할","영등포목동#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-09-25 14:00","2019-09-27 18:00","2019-09-25 14:00","2019-09-27 18:00","연속"]
[42,"남서울","영등포","신정S/S 154kV #65 BUS","신정S/S 부천-신정#2T/L GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 SF6 가스 수분 및 농도 측정 CT 포화시험 경보시험 및 조작시험","2019-09-27 14:00","2019-09-27 18:00","2019-09-27 14:00","2019-09-27 18:00","당일"]
[43,"남서울","영등포","신정S/S 154kV #60 BUS","신정S/S 부천-신정#1T/L GIS 정밀점검공사","CB 동작시간 측정 절연저항, 접촉저항 측정 SF6 가스 수분 및 농도 측정 CT 포화시험 경보시험 및 조작시험","2019-09-25 09:00","2019-09-25 14:00","2019-09-25 09:00","2019-09-25 14:00","당일"]
[44,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-오봉T/L 부재보강공사","154kV 신시흥-오봉T/L No.27 부재보강공사","2019-09-21 08:00","2019-09-21 18:00","2019-09-21 08:00","2019-09-21 18:00","당일"]
[45,"인천","부평","신가좌주안#1 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","신가좌S/S 신가좌-주안 #1T/L GIS(647) 정밀점검 1) 170㎸ GIS 정밀점검 × 1식 2) 기타 부대작업 × 1식","2019-09-21 09:00","2019-09-22 18:00","2019-09-21 09:00","2019-09-22 18:00","연속"]
[46,"인천","시흥","도림오봉#2 T/L","154kV 신시흥-오봉T/L 부재보강공사","154kV 신시흥-오봉T/L No.27 부재보강공사","2019-09-22 08:00","2019-09-22 18:00","2019-09-22 08:00","2019-09-22 18:00","당일"]
[47,"인천","직할","임학계양#2 T/L","154kV계양-북인천T/L 피뢰기 설치공사(병가선로)","154kV계양-북인천T/L 피뢰기 설치공사 관련 병가선로 휴전","2019-09-23 08:00","2019-09-25 18:00","2019-09-23 08:00","2019-09-25 18:00","연속"]
[48,"인천","직할","계양북인천 T/L","154kV계양-북인천T/L 피뢰기 설치공사","154kV계양-북인천T/L 피뢰기 설치공사","2019-09-23 08:00","2019-09-25 18:00","2019-09-23 08:00","2019-09-25 18:00","연속"]
[49,"인천","김포","영종경서 T/L","경서S/S 154kV 영종경서T/L 보호반 대체공사","경서S/S 154kV 영종경서T/L 보호반 대체공사","2019-09-23 09:00","2019-09-27 18:00","2019-09-23 09:00","2019-09-27 18:00","연속"]
[50,"인천","김포","신경서경서#2 T/L","지중송전선로 병행지선 설치관련 보호계전기 재정정","○ 154kV 신경서-경서T/L 병행지선 설치 관련 보호계전기 재정정","2019-09-23 09:00","2019-09-23 18:00","2019-09-23 09:00","2019-09-23 18:00","당일"]
[51,"인천","김포","왕길양촌#1 T/L","지중송전선로 병행지선 설치관련 보호계전기 재정정","○ 154kV 왕길-양촌T/L 병행지선 설치 관련 보호계전기 재정정","2019-09-23 09:00","2019-09-23 18:00","2019-09-23 09:00","2019-09-23 18:00","당일"]
[52,"인천","부평","신가좌인천#3 T/L","154kV 신가좌-인천 #3T/L 자켓 점검 및 보수","자켓 점검 및 보수","2019-09-23 09:00","2019-09-24 18:00","2019-09-23 09:00","2019-09-24 18:00","연속"]
[53,"인천","시흥","동시화서시화 T/L","서시화S/S 170kV 동시화서시화T/L 정밀점검","서시화S/S 170kV 동시화서시화T/L 정밀점검","2019-09-23 09:00","2019-09-24 18:00","2019-09-23 09:00","2019-09-24 18:00","연속"]
[54,"인천","직할","신부평부흥#1 T/L","부흥,신부평S/S 신부평-부흥#1T/L 조작시험","부흥S/S 신부평-부흥#1T/L 조작시험 신부평S/S 신부평-부흥#1T/L 조작시험(병행)","2019-09-23 09:30","2019-09-23 18:00","2019-09-23 09:30","2019-09-23 18:00","연속"]
[55,"인천","시흥","북시화서시화#1 T/L","154kV 북시화서시화#1T/L 선로정수 측정","154kV 북시화서시화#1T/L 병행지선 설치관련 선로정수 측정","2019-09-23 10:00","2019-09-23 13:00","2019-09-23 10:00","2019-09-23 13:00","당일"]
[56,"인천","시흥","서안양소래 T/L","소래S/S 170kV 서안양소래T/L 조작시험","소래S/S 170kV 서안양소래T/L 조작시험","2019-09-23 10:00","2019-09-23 18:00","2019-09-23 10:00","2019-09-23 18:00","당일"]
[57,"인천","시흥","북시화서시화#2 T/L","154kV 북시화서시화#2T/L 선로정수 측정","154kV 북시화서시화#2T/L 병행지선 설치관련 선로정수 측정","2019-09-23 13:00","2019-09-23 16:00","2019-09-23 13:00","2019-09-23 16:00","당일"]
[58,"인천","김포","왕길양촌#2 T/L","지중송전선로 병행지선 설치관련 보호계전기 재정정","○ 154kV 왕길-양촌T/L 병행지선 설치 관련 보호계전기 재정정","2019-09-24 09:00","2019-09-24 18:00","2019-09-24 09:00","2019-09-24 18:00","당일"]
[59,"인천","부평","학익연수#1 T/L","154kV 학익-연수#1T/L 선로정수 측정 및 보호계전기 정정값 반영","지중송전선로 병행지선 설치보강 후 선로정수 변동분 반영으로 계전기 오동작 방지[계통운영부 계통시험파트에서 반영 시행]","2019-09-24 09:00","2019-09-24 13:00","2019-09-24 09:00","2019-09-24 13:00","당일"]
[60,"인천","직할","신부평부흥#2 T/L","부흥,신부평S/S 신부평-부흥#2T/L 조작시험","부흥S/S 신부평-부흥#2T/L 조작시험 신부평S/S 신부평-부흥#2T/L 조작시험(병행)","2019-09-24 09:30","2019-09-24 18:00","2019-09-24 09:30","2019-09-24 18:00","연속"]
[61,"인천","시흥","신시흥#1S/S 154kV #65-#66 SEC GIS","신시흥#1S/S #65-#66 SEC GIS 조작시험","신시흥#1S/S #65-#66 SEC GIS 조작시험","2019-09-24 10:00","2019-09-24 14:00","2019-09-24 10:00","2019-09-24 14:00","당일"]
[62,"인천","부평","학익연수#2 T/L","154kV 학익-연수#2T/L 선로정수 측정 및 보호계전기 정정값 반영","지중송전선로 병행지선 설치보강 후 선로정수 변동분 반영으로 계전기 오동작 방지[계통운영부 계통시험파트에서 반영 시행]","2019-09-24 13:30","2019-09-24 18:00","2019-09-24 13:30","2019-09-24 18:00","당일"]
[63,"인천","시흥","신시흥#1S/S 154kV #66-#67 SEC GIS","신시흥#1S/S #66-#67 SEC GIS 조작시험","신시흥#1S/S #66-#67 SEC GIS 조작시험","2019-09-24 14:00","2019-09-24 18:00","2019-09-24 14:00","2019-09-24 18:00","당일"]
[64,"인천","직할","신부평중동#1 T/L","154kV 신부평-중동#1T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-중동#1T/L 병행지선 설치공사 - 설치개소 : J/B#9~#11 (전력구 : 0.7km)","2019-09-25 09:00","2019-09-25 12:00","2019-09-25 09:00","2019-09-25 12:00","당일"]
[65,"인천","시흥","신시흥#1S/S 154kV #60-#61 SEC GIS","신시흥#1S/S #60-#61 SEC GIS 조작시험","신시흥#1S/S #60-#61 SEC GIS 조작시험","2019-09-25 10:00","2019-09-25 14:00","2019-09-25 10:00","2019-09-25 14:00","당일"]
[66,"인천","직할","신부평중동#2 T/L","154kV 신부평-중동#2T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-중동#2T/L 병행지선 설치공사 - 설치개소 : J/B#9~#11 (전력구 : 0.7km)","2019-09-25 13:00","2019-09-25 18:00","2019-09-25 13:00","2019-09-25 18:00","당일"]
[67,"인천","시흥","신시흥#1S/S 154kV #61-#62 SEC GIS","신시흥#1S/S #61-#62 SEC GIS 조작시험","신시흥#1S/S #61-#62 SEC GIS 조작시험","2019-09-25 14:00","2019-09-25 18:00","2019-09-25 14:00","2019-09-25 18:00","당일"]
[68,"인천","직할","계양원창 T/L","154kV임학-계양#1T/L 피뢰기 설치공사(병가선로)","154kV임학-계양#1T/L 피뢰기 설치공사 관련 병가선로 휴전","2019-09-26 08:00","2019-09-28 18:00","2019-09-26 08:00","2019-09-28 18:00","연속"]
[69,"인천","직할","임학계양#1 T/L","154kV임학-계양#1T/L 피뢰기 설치공사","154kV임학-계양#1T/L 피뢰기 설치공사","2019-09-26 08:00","2019-09-28 18:00","2019-09-26 08:00","2019-09-28 18:00","연속"]
[70,"인천","부평","인천남인천#1 T/L","인천,남인천S/S 인천남인천#1T/L 조작시험","-인천S/S 인천남인천#1T/L 조작시험 -남인천S/S 인천남인천#1T/L 조작시험","2019-09-26 09:00","2019-09-26 18:00","2019-09-26 09:00","2019-09-26 18:00","당일"]
[71,"인천","직할","신부평중동#3 T/L","154kV 신부평-중동#3T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-중동#3T/L 병행지선 설치공사 - 설치개소 : J/B#9~#11 (전력구 : 0.7km)","2019-09-26 09:00","2019-09-26 12:00","2019-09-26 09:00","2019-09-26 12:00","당일"]
[72,"인천","직할","신부평고강#1 T/L","고강,신부평S/S 신부평-고강#1T/L 조작시험","고강S/S 신부평-고강#1T/L 조작시험 신부평S/S 신부평-고강#1T/L 조작시험(병행)","2019-09-26 09:30","2019-09-26 18:00","2019-09-28 09:30","2019-09-28 18:00","연속"]
[73,"인천","부평","신가좌인천#2 T/L","신가좌,인천S/S 신가좌인천#2 T/L 조작시험","-신가좌S/S 신가좌인천#2 T/L 조작시험 -인천S/S 신가좌인천#2 T/L 조작시험","2019-09-27 09:00","2019-09-27 18:00","2019-09-27 09:00","2019-09-27 18:00","당일"]
[74,"인천","시흥","북시화서시화#3 T/L","북시화S/S #5M.Tr GIS 정밀점검(무부하용 T/L)","북시화S/S #5M.Tr GIS 정밀점검(무부하용 북시화서시화#3 T/L)","2019-09-27 09:00","2019-09-27 18:00","2019-09-27 09:00","2019-09-27 18:00","당일"]
[75,"인천","직할","신부평고강#2 T/L","고강,신부평S/S 신부평-고강#2T/L 조작시험","고강S/S 신부평-고강#2T/L 조작시험 신부평S/S 신부평-고강#2T/L 조작시험(병행)","2019-09-27 09:30","2019-09-27 18:00","2019-09-29 09:30","2019-09-29 18:00","연속"]
[76,"인천","부평","신가좌주안#2 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","신가좌S/S 신가좌-주안 #2T/L GIS(617) 정밀점검 1) 170㎸ GIS 정밀점검 × 1식 2) 기타 부대작업 × 1식","2019-09-28 09:00","2019-09-29 18:00","2019-09-28 09:00","2019-09-29 18:00","연속"]
[77,"인천","부평","신가좌신현#1 T/L","신현S/S 신가좌신현#1T/L GIS 조작시험","신현S/S 신가좌신현#1T/L GIS 조작시험","2019-09-30 09:00","2019-09-30 13:00","2019-09-30 09:00","2019-09-30 13:00","당일"]
[78,"인천","직할","계양김포#1 T/L","계양S/S 계양김포#1T/L 170kV GIS 조작시험","계양S/S 계양김포#1T/L 170kV GIS 조작시험","2019-09-30 09:30","2019-09-30 14:00","2019-09-30 09:30","2019-09-30 14:00","연속"]
[79,"인천","부평","신가좌신현#2 T/L","신현S/S 신가좌신현#2T/L GIS 조작시험","신현S/S 신가좌신현#2T/L GIS 조작시험","2019-09-30 13:00","2019-09-30 18:00","2019-09-30 13:00","2019-09-30 18:00","당일"]
[80,"인천","직할","계양김포#2 T/L","계양S/S 계양김포#2T/L 170kV GIS 조작시험","계양S/S 계양김포#2T/L 170kV GIS 조작시험","2019-09-30 14:00","2019-09-30 18:00","2019-09-30 14:00","2019-09-30 18:00","연속"]
[81,"경기북부","고양","양주금촌#2 T/L","고양전력지사 OPGW 항공장애표시구 정비공사","345kV 신파주-양주 등 8개T/L OPGW 항공장애표시구 정비공사","2019-09-22 09:00","2019-09-25 18:00","2019-09-22 09:00","2019-09-25 18:00","연속"]
[82,"경기북부","고양","백학남면#1 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","송전선로 항공장애표시구 설치 - 345kV 신덕은-동두천CCT/L (ACSR 29경간) - 하단병가선로 안전이격 확보로 동시휴전","2019-09-23 08:00","2019-09-24 18:00","2019-09-23 08:00","2019-09-24 18:00","연속"]
[83,"경기북부","고양","양주불광#2 T/L","154kV 지축E/C 옥내화 사업","154kV 지축E/C 옥내화 사업 - 이설선로 무부하가압","2019-09-16 09:00","2019-09-27 18:00","2019-09-16 09:00","2019-09-27 18:00","연속"]
[84,"경기북부","고양","불광서대문#1 T/L","154kV 지축E/C 옥내화 사업","154kV 지축E/C 옥내화 사업 - 이설선로 무부하가압","2019-09-16 09:00","2019-09-27 18:00","2019-09-16 09:00","2019-09-27 18:00","연속"]
[85,"경기북부","고양","신덕은S/S 154kV #60-#65 BUS TIE CB","2019년 고양P/O 변전정비회사 총액공사","신덕은S/S 154kV #60-#65 BUS PRO PNL 교체공사","2019-09-23 09:00","2019-09-27 18:00","2019-09-23 09:00","2019-09-27 18:00","연속"]
[86,"경기북부","고양","신덕은원흥#1 T/L","154kV 신덕은-원흥T/L 송전용량증대 전력선교체공사","ㅇ 전력선교체 : 12.03km - 구간 : No.10~13, No.17~30, No.39~46, NO.48~60 ㅇ 계탑 및 애자련변경 - No.10(계탑), No.11(애자련변경)","2019-09-30 07:00","2019-10-19 18:00","2019-09-30 07:00","2019-10-19 18:00","연속"]
[87,"경기북부","구리","가평청평HP#1 T/L","19년 구리전력 CVT 보통점검","19년 구리전력 CVT 보통점검","2019-09-23 09:00","2019-09-23 14:00","취소","취소","당일"]
[88,"경기북부","구리","가평화천HP T/L","154kV 화천T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - No.133~134","2019-09-30 07:00","2019-09-30 18:00","취소","취소","연속"]
[89,"경기북부","구리","가평청평HP#2 T/L","154kV 화천T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - No.133~134","2019-09-30 07:00","2019-09-30 18:00","취소","취소","연속"]
[90,"경기북부","구리","가평춘천HP T/L","19년 구리전력 CVT 보통점검","19년 구리전력 CVT 보통점검","2019-09-23 14:00","2019-09-23 18:00","취소","취소","당일"]
[91,"경기북부","구리","덕소S/S 154KV 신장-덕소#1T/L CB","154kV 덕소E/C 최초가압","신장-덕소#2T/L 최초가압","2019-09-04 09:00","2019-09-05 18:00","2019-09-04 09:00","2019-09-05 18:00","연속"]
[92,"경기북부","구리","덕소팔당HP청평HP T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업 154kV 덕소-팔당-청평T/L 휴전작업으로 신설 덕소S/S 계통병입 및 부하절체","2019-09-17 09:00","2019-10-11 18:00","취소","취소","연속"]
[93,"경기북부","구리","미금덕소#2 T/L","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치(시험가압) - 기타 부대공사","2019-09-20 18:00","2019-09-21 08:00","2019-09-20 18:00","2019-09-21 08:00","연속"]
[94,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-09-17 08:00","2019-09-21 08:00","2019-09-17 08:00","2019-09-21 08:00","연속"]
[95,"경기북부","구리","미금덕소#2 T/L","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치(시험가압) - 기타 부대공사","2019-09-16 18:00","2019-09-17 08:00","2019-09-16 18:00","2019-09-17 08:00","연속"]
[96,"경기북부","구리","미금덕소#2 T/L","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치(안전이격확보) - 기타 부대공사","2019-09-16 08:00","2019-09-27 18:00","취소","취소","매일"]
[97,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-09-16 08:00","2019-09-17 08:00","2019-09-16 08:00","2019-09-17 08:00","연속"]
[98,"경기북부","구리","미금덕소#1 T/L","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치(안전이격확보) - 기타 부대공사","2019-09-16 08:00","2019-09-27 18:00","취소","취소","매일"]
[99,"경기북부","구리","미금S/S 154kV #60-#65 BUS TIE GIS","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-09-16 08:00","2019-09-28 18:00","2019-09-16 08:00","2019-09-28 18:00","연속"]
[100,"경기북부","구리","미금덕소#1 T/L","미금S/S 170kV 장기사용GIS 교체공사(6차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-09-30 08:00","2019-10-19 18:00","2019-09-30 08:00","2019-10-19 18:00","연속"]
[101,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용GIS 교체공사(6차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-09-30 08:00","2019-10-01 08:00","2019-09-30 08:00","2019-10-01 08:00","연속"]
[102,"경기북부","구리","미금구리#2 T/L","미금S/S 170kV 장기사용GIS 교체공사(6차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-09-30 08:00","2019-10-19 18:00","2019-09-30 08:00","2019-10-19 18:00","연속"]
[103,"경기북부","구리","미금S/S 154kV #60 BUS","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-09-28 10:00","2019-09-28 15:00","2019-09-28 10:00","2019-09-28 15:00","연속"]
[104,"경기북부","구리","미금덕소#2 T/L","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치(시험가압) - 기타 부대공사","2019-09-27 18:00","2019-09-28 16:00","2019-09-27 18:00","2019-09-28 16:00","연속"]
[105,"경기북부","구리","미금S/S 154kV #65 BUS","미금S/S 170kV 장기사용GIS 교체공사(5차분)","- 170kV GIS 철거, 설치 - 기타 부대공사","2019-09-21 08:00","2019-09-28 16:00","2019-09-21 08:00","2019-09-28 16:00","연속"]
[106,"경기북부","구리","별내도봉 T/L","154kV 별내-도봉T/L PMJ 교체공사","○ 대상 : J/B#1~#3 구간 3개소 9상 ○ 내용 : 일진제 조립식 중간접속함 형태 변경(R→Flat Type)","2019-09-30 09:00","2019-10-06 18:00","취소","취소","연속"]
[107,"경기북부","구리","별내진접 T/L","154kV 별내-진접T/L 불량애자교체공사","ㅇ 불량애자교체 - 대상 : No.21호 상단전원","2019-09-17 07:00","2019-09-17 12:00","2019-09-17 07:00","2019-09-17 12:00","당일"]
[108,"경기북부","구리","서종청평PP#2 T/L","154kV 서종-청평PPT/L 초기점검","154kV 서종-청평PP#2T/L No.65(C/H) 초기점검","2019-09-30 13:00","2019-09-30 18:00","2019-09-30 13:00","2019-09-30 18:00","당일"]
[109,"경기북부","구리","서종청평PP#1 T/L","154kV 서종-청평PPT/L 초기점검","154kV 서종-청평PP#1T/L No.65(C/H) 초기점검","2019-09-30 08:00","2019-09-30 13:00","2019-09-30 08:00","2019-09-30 13:00","당일"]
[110,"경기북부","구리","신포천백학#1 T/L","345kV 신덕은-동두천CC 등 15개T/L 항공구 설치공사","송전선로 항공장애표시구 설치 - 345kV 신덕은-동두천CCT/L (ACSR 29경간) - 하단병가선로 안전이격 확보로 동시휴전","2019-09-25 08:00","2019-09-27 18:00","2019-09-25 08:00","2019-09-27 18:00","연속"]
[111,"경기북부","구리","신포천백학#2 T/L","직할 관내 OPGW 항공장애표시구 설치 공사","직할 관내 OPGW 항공장애표시구 설치 공사 - 신포천백학#2T/L 항공장애표시구 17개 설치","2019-09-23 06:00","2019-09-24 18:00","2019-09-23 06:00","2019-09-24 18:00","연속"]
[112,"경기북부","구리","문막지제#1 T/L","154kV 문막-지제T/L 항공장애시설물 정비공사","ㅇ 항공장애표시구 설치 - No.4~5호 등 21경간","2019-09-23 07:00","2019-09-27 18:00","2019-09-23 07:00","2019-09-27 18:00","연속"]
[113,"경기북부","구리","도봉진접 T/L","154kV 도봉-진접T/L 피뢰기 설치공사","ㅇ 피뢰기 설치 - 도봉진접(별내도봉) No.10~22호 13기 - 도봉진접(진접분기) No.1~27호 27기","2019-09-18 07:00","2019-09-20 18:00","2019-09-21 07:00","2019-09-22 18:00","매일"]
[114,"경기북부","구리","청평HP의암HP T/L","2018~19년도 구리전력지사 가공송전정비 협력회사 총액공사","ㅇ 애자련보강공사 - 대상 : No.37,38","2019-09-17 11:00","2019-09-17 18:00","2019-09-17 11:00","2019-09-17 18:00","당일"]
[115,"경기북부","직할","양주S/S 154kV #66 BUS","154kV 지축E/C 옥내화 사업","154kV 지축E/C 옥내화 사업 - 이설선로 무부하가압","2019-09-26 09:00","2019-09-27 18:00","2019-09-26 09:00","2019-09-27 18:00","연속"]
[116,"경기북부","직할","양주고양#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주고양#1 T/L 인출측 전력구공사","2019-09-19 09:00","2019-09-20 18:00","2019-09-19 09:00","2019-09-20 18:00","연속"]
[117,"경기북부","직할","양주고양#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주고양#2 T/L 인출측 전력구공사","2019-09-17 09:00","2019-09-18 18:00","2019-09-17 09:00","2019-09-18 18:00","연속"]
[118,"경기","군포","화성남양#2 T/L","154kV화성-남양#2T/L 정밀점검(19년 가공송전 위탁공사)","154kV화성-남양#2T/L 1호~26호 정밀점검","2019-09-28 09:00","2019-09-29 18:00","2019-09-28 09:00","2019-09-29 18:00","당일"]
[119,"경기","군포","화성남양#1 T/L","154kV화성-남양#1T/L 정밀점검(19년 가공송전 위탁공사)","154kV화성-남양#1T/L 1호~26호 정밀점검","2019-09-21 09:00","2019-09-22 18:00","2019-09-21 09:00","2019-09-22 18:00","당일"]
[120,"경기","군포","서서울율전#2 T/L","154kV서서울-율전#2T/L 초기점검(19년 가공송전 위탁공사)","154kV서서울-율전#2T/L 6호~15호 초기점검","2019-09-18 09:00","2019-09-19 18:00","2019-09-18 09:00","2019-09-19 18:00","당일"]
[121,"경기","군포","신시흥시화#1 T/L","2019년 군포P/O 변전정비회사 총액공사","시화S/S 154kV 시화-신시흥#1T/L GIS 초기점검, LA 하자점검","2019-09-30 09:00","2019-09-30 14:00","2019-09-30 09:00","2019-09-30 14:00","당일"]
[122,"경기","군포","신시흥시화#2 T/L","2019년 군포P/O 변전정비회사 총액공사","시화S/S 154kV 시화-신시흥#2T/L GIS 초기점검","2019-09-30 14:00","2019-09-30 18:00","2019-09-30 14:00","2019-09-30 18:00","당일"]
[123,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-율현T/L 송전선로 정밀점검","송전선로 정밀점검","2019-09-23 09:00","2019-09-26 18:00","취소","취소","연속"]
[124,"경기","동부","곤지암율현#1 T/L","154kV 곤지암-율현T/L 송전선로 정밀점검","송전선로 정밀점검","2019-09-30 09:00","2019-10-02 18:00","취소","취소","연속"]
[125,"경기","동부","곤지암율현#1 T/L","154kV 곤지암-율현T/L 송전선로 정밀점검","송전선로 정밀점검","2019-09-27 09:00","2019-09-27 18:00","취소","취소","당일"]
[126,"경기","동부","곤지암초월#1 T/L","154kV 곤지암-초월#1T/L PMJ 접속함 교체공사","유사고장예방 접속함교체(리콜대상 공사) - 대상선로 : 곤지암-초월#1T/L 중간접속함 6EA","2019-09-30 08:00","2019-10-13 18:00","2019-09-30 08:00","2019-10-13 18:00","연속"]
[127,"경기","동부","곤지암이천#1 T/L","154kV 곤지암-율현 #1T/L 정밀점검","안전이격 휴전(곤지암-율현T/L 4회선 구간)","2019-09-30 08:00","2019-09-30 18:00","취소","취소","당일"]
[128,"경기","동부","곤지암이천#1 T/L","154kV 곤지암-율현 #1T/L 정밀점검","안전이격 휴전(곤지암-율현T/L 4회선 구간)","2019-09-27 08:00","2019-09-27 18:00","취소","취소","당일"]
[129,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-율현 #2T/L 정밀점검","안전이격 휴전(곤지암-율현T/L 4회선 구간)","2019-09-25 08:00","2019-09-26 18:00","취소","취소","매일"]
[130,"경기","동부","오포S/S 154kV 오포-모현#1T/L GIS","19년 동부변전협력회사 총액공사","오포: 오포-모현#1T/L GIS(보통),43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-09-26 09:30","2019-09-26 18:00","2019-09-26 09:30","2019-09-26 18:00","당일"]
[131,"경기","성남","진위동탄#1 T/L","GIS 초기점검","GIS 초기점검","2019-09-18 09:00","2019-09-18 14:00","2019-09-18 09:00","2019-09-18 14:00","당일"]
[132,"경기","성남","남사동탄#1 T/L","GIS 초기점검","- GIS 초기점검","2019-09-16 09:00","2019-09-16 14:00","2019-09-16 09:00","2019-09-16 14:00","당일"]
[133,"경기","성남","진위동탄#2 T/L","GIS 초기점검","GIS 초기점검","2019-09-18 14:00","2019-09-18 18:00","2019-09-18 14:00","2019-09-18 18:00","당일"]
[134,"경기","성남","남사동탄#2 T/L","GIS 초기점검","- GIS 초기점검","2019-09-16 14:00","2019-09-16 18:00","2019-09-16 14:00","2019-09-16 18:00","당일"]
[135,"경기","성남","서안성안성#1 T/L","상부부스 가스누기 조치","상부부스 가스누기 조치","2019-09-30 09:00","2019-10-01 18:00","2019-09-30 09:00","2019-10-01 18:00","당일"]
[136,"경기","성남","신성남서판교 #3 T/L","DS 접점불량조치(제작사 하자)","DS 접점불량조치(제작사 하자)","2019-09-26 09:00","2019-09-26 18:00","2019-09-26 09:00","2019-09-26 18:00","당일"]
[137,"경기","성남","신수원S/S 154kV #61-#66 BUS-TIE GIS","GIS 조작시험","GIS 조작시험","2019-09-27 14:00","2019-09-27 18:00","2019-09-27 14:00","2019-09-27 18:00","당일"]
[138,"경기","성남","신수원S/S 154kV #66-#67 SEC GIS","GIS 조작시험","GIS 조작시험","2019-09-26 14:00","2019-09-26 18:00","2019-09-26 14:00","2019-09-26 18:00","당일"]
[139,"경기","성남","신수원S/S 154kV #65-#66 SEC GIS","GIS 조작시험","GIS 조작시험","2019-09-26 09:00","2019-09-26 14:00","2019-09-26 09:00","2019-09-26 14:00","당일"]
[140,"경기","성남","신수원북동탄#1 T/L","GIS 조작시험","GIS 조작시험","2019-09-28 14:00","2019-09-28 18:00","2019-09-28 14:00","2019-09-28 18:00","당일"]
[141,"경기","성남","신수원S/S 154kV #61-#62 SEC GIS","GIS 조작시험","GIS 조작시험","2019-09-27 09:00","2019-09-27 14:00","2019-09-27 09:00","2019-09-27 14:00","당일"]
[142,"경기","성남","신용인S/S 154kV #66 BUS","65-66SEC GIS 정밀점검 무부하","65-66SEC GIS 정밀점검 무부하","2019-09-28 09:00","2019-09-28 18:00","2019-09-28 09:00","2019-09-28 18:00","당일"]
[143,"경기","성남","신용인S/S 154kV #65-#66 SEC GIS","GIS 정밀점검","GIS 정밀점검","2019-09-27 09:00","2019-09-28 18:00","2019-09-27 09:00","2019-09-28 18:00","연속"]
[144,"경기","성남","신용인S/S 154kV #61 BUS","60-61SEC GIS 정밀점검 무부하","60-61SEC GIS 정밀점검 무부하","2019-09-26 09:00","2019-09-26 18:00","2019-09-26 09:00","2019-09-26 18:00","당일"]
[145,"경기","성남","신용인S/S 154kV #60-#61 SEC GIS","GIS 정밀점검","GIS 정밀점검","2019-09-25 09:00","2019-09-26 18:00","2019-09-25 09:00","2019-09-26 18:00","연속"]
[146,"경기","성남","신용인용인#1 T/L","154kV 신용인-용인T/L OPGW 증설공사","용인S/S~신용인S/S간 OPGW(24C→48C) 8.814km 교체","2019-09-16 07:00","2019-09-24 18:00","2019-09-16 07:00","2019-09-24 18:00","연속"]
[147,"경기","성남","오천용인#1 T/L","기 154kV 율현-용인T/L No.30 항공장애표시구 및 표시등 설치","기 154kV 율현-용인T/L No.30 항공장애표시구 및 표시등 설치(요청자 시행)","2019-09-24 08:00","2019-09-24 18:00","2019-09-06 08:00","2019-09-06 18:00","당일"]
[148,"경기","성남","오천용인#2 T/L","기 154kV 율현-용인T/L No.30 항공장애표시구 및 표시등 설치","기 154kV 율현-용인T/L No.30 항공장애표시구 및 표시등 설치(요청자 시행)","2019-09-24 08:00","2019-09-24 18:00","2019-09-06 08:00","2019-09-06 18:00","당일"]
[149,"경기","성남","용인남사#1 T/L","154kV 신용인-용인T/L OPGW 증설공사","용인S/S~신용인S/S간 OPGW(24C→48C) 8.814km 교체","2019-09-23 07:00","2019-09-24 18:00","2019-09-11 07:00","2019-09-12 18:00","연속"]
[150,"경기","직할","남수원발안#1 T/L","발안S/S #5M.Tr 증설","1. 변압기 1Bank 설치 2. GIS 설치","2019-09-24 09:00","2019-10-18 17:00","2019-09-24 09:00","2019-10-18 17:00","연속"]
[151,"경기","직할","남수원발안#1 T/L","154kV 발안-향남T/L OPGW 증설공사","발안S/S~향남S/S간 OPGW 6.288km 증설(24C→48C)","2019-09-08 00:07","2019-09-08 18:00","2019-09-08 00:07","2019-09-08 18:00","연속"]
[152,"경기","직할","남수원발안#2 T/L","154kV 발안-향남T/L OPGW 증설공사","발안S/S~향남S/S간 OPGW 6.288km 증설(24C→48C)","2019-09-02 00:07","2019-09-07 18:00","2019-09-02 00:07","2019-09-07 18:00","연속"]
[153,"경기","직할","발안향남#2 T/L","154kV 발안-향남T/L OPGW 증설공사","발안S/S~향남S/S간 OPGW 6.288km 증설(24C→48C)","2019-09-02 00:07","2019-09-08 18:00","2019-09-02 00:07","2019-09-08 18:00","연속"]
[154,"경기","직할","화성발안#1 T/L","19년 직할 변전협력회사 총액공사","화성-발안#1T/L 보호반 대체공사(화성, 발안)","2019-09-09 09:00","2019-09-11 18:00","2019-09-09 09:00","2019-09-11 18:00","연속"]
[155,"경기","직할","발안S/S 154kV #2 BUS","발안S/S #5M.Tr 증설","1. 변압기 1Bank 설치 2. GIS 설치","2019-09-30 09:00","2019-10-08 17:00","2019-09-30 09:00","2019-10-08 17:00","연속"]
[156,"경기","직할","발안구문천#1 T/L","발안S/S #5M.Tr 증설","1. 변압기 1Bank 설치 2. GIS 설치","2019-09-28 17:00","2019-09-29 17:00","2019-09-28 17:00","2019-09-29 17:00","연속"]
[157,"경기","직할","발안S/S 154kV #1 BUS","발안S/S #5M.Tr 증설","1. 변압기 1Bank 설치 2. GIS 설치","2019-09-24 09:00","2019-09-29 17:00","2019-09-24 09:00","2019-09-29 17:00","연속"]
[158,"경기","직할","서수원율전#1 T/L","154kV 서수원율전 #1TL 피뢰기 설치공사(No.1,17호)","154kV 서수원율전 #1TL 피뢰기 설치공사(No.1,17호)","2019-09-20 08:00","2019-09-20 18:00","2019-09-01 14:00","2019-09-01 18:00","당일"]
[159,"경기","직할","서서울서수원#1 T/L","2019년 직할 154kV GIS 정밀점검공사","서수원S/S 15kV #3M.Tr 1차 GIS 정밀점검공사(무부하가압용)","2019-09-03 14:00","2019-09-04 18:00","2019-09-03 14:00","2019-09-04 18:00","연속"]
[160,"경기","직할","서서울서수원#2 T/L","2019년 직할 154kV GIS 정밀점검공사","서수원S/S 15kV #4M.Tr 1차 GIS 정밀점검공사(무부하가압용)","2019-09-06 14:00","2019-09-07 18:00","2019-09-06 14:00","2019-09-07 18:00","연속"]
[161,"경기","직할","서서울서수원#1 T/L","2019년 직할 154kV GIS 정밀점검공사","서수원S/S 154kV 서서울서수원#1 T/L GIS 정밀점검공사","2019-09-09 09:00","2019-09-11 18:00","2019-09-09 09:00","2019-09-11 18:00","연속"]
[162,"경기","직할","서서울율전#1 T/L","154kV 율전분기T/L 중간접속함 해체점검공사","율전전력구내 J/B#1,2,3(9상) 해체점검","2019-09-30 09:00","2019-10-04 18:00","2019-09-30 09:00","2019-10-04 18:00","연속"]
[163,"경기","직할","율전의왕#1 T/L","154kV 율전분기T/L 중간접속함 해체점검공사","율전전력구내 J/B#1,2,3(9상) 해체점검","2019-09-23 09:00","2019-09-27 18:00","2019-09-23 09:00","2019-09-27 18:00","연속"]
[164,"경기","직할","의왕동안양#1 T/L","의왕S/S 154kV 장기사용 GIS 대체공사","의왕S/S 군포전철#2T/L(647) GIS 대체(무부하가압용)","2019-09-29 10:00","2019-10-01 10:00","2019-09-29 10:00","2019-10-01 10:00","연속"]
[165,"경기","직할","화성장덕 T/L","(안전이격)154kV 화성발안 #2TL 피뢰기 설치공사(No2-4)","(안전이격)154kV 화성발안 #2TL 피뢰기 설치공사(No2-4)","2019-09-01 07:00","2019-09-01 14:00","2019-09-01 07:00","2019-09-01 14:00","당일"]
[166,"경기","직할","화성수촌#2 T/L","(안전이격)154kV 화성발안 #2TL 피뢰기 설치공사(No2-4)","(안전이격)154kV 화성발안 #2TL 피뢰기 설치공사(No2-4)","2019-09-01 07:00","2019-09-01 14:00","2019-09-01 07:00","2019-09-01 14:00","당일"]
[167,"경기","직할","화성발안#2 T/L","154kV 화성발안 #2TL 피뢰기 설치공사(No2-4)","154kV 화성발안 #2TL 피뢰기 설치공사(No2-4)","2019-09-01 07:00","2019-09-01 14:00","2019-09-01 07:00","2019-09-01 14:00","당일"]
[168,"경기","평택","고덕송탄#1 T/L","고덕,송탄S/S 고덕-송탄#1T/L 보호반 개선공사","고덕,송탄S/S 고덕-송탄#1T/L 보호반 개선공사","2019-09-29 09:00","2019-09-29 13:00","2019-09-29 09:00","2019-09-29 13:00","당일"]
[169,"경기","평택","고덕진위#2 T/L","고덕S/S 154kV SW 증설공사 (고덕-동평택#1,2T/L)","ㅇ 고덕S/S 154kV SW #65BUS측 기기설치 - 고덕-동평택#1,2 T/L ㅇ 154kV #65BUS측 무부하 가압","2019-09-19 18:00","2019-09-20 18:00","2019-09-19 18:00","2019-09-20 18:00","연속"]
[170,"경기","평택","고덕진위#2 T/L","고덕S/S 154kV SW 증설공사 (고덕-동평택#1,2T/L)","ㅇ 고덕S/S 154kV SW #60BUS측 기기설치 - 고덕-동평택#1,2 T/L ㅇ 154kV #60BUS측 무부하 가압","2019-09-26 18:00","2019-09-27 18:00","2019-09-26 18:00","2019-09-27 18:00","연속"]
[171,"경기","평택","고덕평택#1 T/L","고덕,평택S/S 고덕-평택#1T/L 보호반 개선공사","고덕,평택S/S 고덕-평택#1T/L 보호반 개선공사","2019-09-28 09:00","2019-09-28 13:00","2019-09-28 09:00","2019-09-28 13:00","당일"]
[172,"경기","평택","고덕송탄#2 T/L","고덕,송탄S/S 고덕-송탄#2T/L 보호반 개선공사","고덕,송탄S/S 고덕-송탄#2T/L 보호반 개선공사","2019-09-29 13:00","2019-09-29 17:00","2019-09-29 13:00","2019-09-29 17:00","당일"]
[173,"경기","평택","고덕평택#2 T/L","고덕,평택S/S 고덕-평택#2T/L 보호반 개선공사","고덕,평택S/S 고덕-평택#2T/L 보호반 개선공사","2019-09-28 13:00","2019-09-28 17:00","2019-09-28 13:00","2019-09-28 17:00","당일"]
[174,"경기","평택","포승만호 T/L","154kV 포승-만호T/L PD집합반 설치공사","154kV 포승-만호T/L PD집합반 설치공사 - 만호C/H PD 센서 설치","2019-09-26 13:00","2019-09-26 17:00","2019-09-26 13:00","2019-09-26 17:00","당일"]
[175,"경기","평택","만호청북#1 T/L","154kV 만호-청북T/L PD집합반 설치공사","154kV 만호-청북T/L PD집합반 설치공사 - 만호C/H, 청북C/H PD 센서 설치","2019-09-26 09:00","2019-09-26 13:00","2019-09-26 09:00","2019-09-26 13:00","당일"]
[176,"경기","평택","포승만호 T/L","(안전이격) 154kV 포승-평택TP #2 피뢰기 설치공사","(안전이격) 154kV 포승-평택TP #2 피뢰기 설치공사(No.32~39)","2019-09-19 09:00","2019-09-19 18:00","2019-09-19 09:00","2019-09-19 18:00","당일"]
[177,"경기","평택","만호청북#1 T/L","(안전이격) 154kV 포승-평택TP #2 피뢰기 설치공사","(안전이격) 154kV 포승-평택TP #2 피뢰기 설치공사(No.24~31)","2019-09-18 09:00","2019-09-18 18:00","2019-09-18 09:00","2019-09-18 18:00","당일"]
[178,"경기","평택","서운삼죽 T/L","2019년 가공송전선로 순시점검 위탁공사(충북 직할)","정밀점검(No.73~92)","2019-09-28 08:00","2019-09-29 18:00","2019-09-28 08:00","2019-09-29 18:00","매일"]
[179,"경기","평택","송탄소사벌 T/L","154kV 송탄-소사벌T/L PD집합반 설치공사","154kV 송탄-소사벌T/L PD집합반 설치공사 - 소사벌C/H PD 센서 설치","2019-09-27 13:00","2019-09-27 17:00","2019-09-27 09:00","2019-09-27 19:00","당일"]
[180,"경기","평택","평택오성CC#2 T/L","오성C/C 154kV GIS 평택-오성C/C#2T/L 가스누기 보수공사","오성C/C 154kV GIS 평택-오성C/C#2T/L 상부BUS 가스누기 보수공사","2019-09-24 10:00","2019-09-25 18:00","2019-09-24 10:00","2019-09-25 18:00","연속"]
[181,"경기","평택","원정평택T/P#1 T/L","154kV 원정-평택TP #1T/L PD집합반 설치공사","154kV 원정-평택TP#1T/L PD집합반 설치공사 - 원정#2C/H PD 센서 설치","2019-09-25 10:00","2019-09-25 13:00","2019-09-25 10:00","2019-09-25 13:00","당일"]
[182,"경기","평택","원정만호#2 T/L","원정S/S 154kV 원정-만호#2 T/L GIS 조작시험","원정S/S 154kV 원정-만호#2 T/L GIS 조작시험","2019-09-30 10:00","2019-09-30 18:00","2019-09-30 10:00","2019-09-30 18:00","당일"]
[183,"경기","평택","원정평택T/P#2 T/L","154kV 원정-평택TP #2T/L PD집합반 설치공사","154kV 원정-평택TP#2T/L PD집합반 설치공사 - 원정#2C/H PD 센서 설치","2019-09-25 13:00","2019-09-25 20:00","2019-09-25 13:00","2019-09-25 20:00","당일"]
[184,"경기","평택","고덕진위#1 T/L","154kV 고덕-진위T/L 30호 지장철탑 이설공사","남사나들목 개설 관련 30호 지장이설 2기 신설, 1기 철거","2019-09-02 07:00","2019-09-05 18:00","2019-09-02 07:00","2019-09-05 18:00","연속"]
[185,"경기","평택","고덕진위#2 T/L","154kV 고덕-진위T/L 30호 지장철탑 이설공사","남사나들목 개설 관련 30호 지장이설 2기 신설, 1기 철거","2019-09-06 07:00","2019-09-09 18:00","2019-09-06 07:00","2019-09-09 18:00","연속"]
[186,"경기","평택","포승청북 T/L","154kV 포승-청북T/L PD집합반 설치공사","154kV 포승-청북T/L PD집합반 설치공사 - 청북C/H PD 센서 설치","2019-09-27 10:00","2019-09-27 13:00","취소","취소","당일"]
[187,"경기","평택","포승평택TP#2 T/L","154kV 포승-평택TP #2 피뢰기 설치공사","154kV 포승-평택TP #2 피뢰기 설치공사","2019-09-17 09:00","2019-09-24 18:00","2019-09-17 09:00","2019-09-24 18:00","연속"]
[188,"경기","평택","포승평택TP#1 T/L","154kV 포승-평택TP #1 SB 댐퍼 정비","154kV 포승-평택TP #1 SB 댐퍼 정비","2019-09-16 13:00","2019-09-16 18:00","2019-09-16 13:00","2019-09-16 18:00","당일"]
[189,"경기","성남","신용인용인#2 T/L","154kV 신용인-용인#2T?L 송전선로 정밀점검","154kV 신용인-용인#2T?L 송전선로 정밀점검","2019-09-09 09:00","2019-09-10 18:00","2019-09-09 09:00","2019-09-10 18:00","연속"]
[190,"강원","강릉","간성S/S 154kV #1 Sh.C CB","간성S/S #4M.Tr 증설공사","GIS[170kV 50kA1250A] x 1CCT 설치 GIB 대체에 따른 설비 안전 확보[DS 가동자까지 전압인가]","2019-09-17 09:00","2019-09-27 18:00","2019-09-17 09:00","2019-09-27 18:00","연속"]
[191,"강원","강릉","강릉북강릉#2 T/L","154kV 강릉-북강릉-주문진-양양간 OPGW교체공사","- OPGW 13.022km 교체 - 항공장애표시구 26개 철거 - 항공장애표시구 40개 시설","2019-09-19 08:00","2019-10-01 18:00","2019-09-19 08:00","2019-10-01 18:00","연속"]
[192,"강원","강릉","동해강릉 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","동해강릉T/L EBA PD진단센서 및 집합반 설치공사","2019-09-02 08:00","2019-09-02 18:00","2019-09-02 08:00","2019-09-02 18:00","당일"]
[193,"강원","강릉","강릉횡계#1 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","강릉횡계#1T/L EBA PD진단센서 및 집합반 설치공사","2019-09-02 08:00","2019-09-02 18:00","2019-09-02 08:00","2019-09-02 18:00","당일"]
[194,"강원","강릉","강릉횡계#2 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","강릉횡계#2T/L EBA PD진단센서 및 집합반 설치공사","2019-09-03 08:00","2019-09-03 18:00","2019-09-03 08:00","2019-09-03 18:00","당일"]
[195,"강원","강릉","강릉영동TP T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","강릉영동TP T/L EBA PD진단센서 및 집합반 설치공사","2019-09-03 08:00","2019-09-03 18:00","2019-09-03 08:00","2019-09-03 18:00","당일"]
[196,"강원","강릉","속초간성#1 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","속초간성#1T/L EBA PD진단센서 및 집합반 설치공사","2019-09-04 08:00","2019-09-04 12:30","2019-09-04 08:00","2019-09-04 12:30","당일"]
[197,"강원","강릉","속초간성#2 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","속초간성#2T/L EBA PD진단센서 및 집합반 설치공사","2019-09-04 12:30","2019-09-04 18:00","2019-09-04 12:30","2019-09-04 18:00","당일"]
[198,"강원","강릉","횡계평창 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2019-09-30 10:00","2019-10-03 18:00","2019-09-30 10:00","2019-10-03 18:00","연속"]
[199,"강원","동해","동해영동TP T/L","2018~2019년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-09-20 08:00","2019-09-22 18:00","2019-09-20 08:00","2019-09-22 18:00","연속"]
[200,"강원","동해","동해강릉 T/L","2018~2019년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-09-16 08:00","2019-09-18 18:00","2019-09-16 08:00","2019-09-18 18:00","연속"]
[201,"강원","동해","북평영동TP#1 T/L","2018~2019년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-09-20 08:00","2019-09-22 18:00","2019-09-20 08:00","2019-09-22 18:00","연속"]
[202,"강원","동해","북평영동TP#2 T/L","2018~2019년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-09-20 08:00","2019-09-22 18:00","2019-09-20 08:00","2019-09-22 18:00","연속"]
[203,"강원","동해","북평영동TP#1 T/L","2018~2019년도 동해전력지사 송전정비협력회사 총액공사","154kV 동해분기T/L 인출정비공사 철탑 4기 철거, 2기 신설","2019-09-16 08:00","2019-09-18 18:00","2019-09-16 08:00","2019-09-18 18:00","연속"]
[204,"강원","원주","남원주원주#1 T/L","18-19년 원주전력지사 변전정비회사 총액공사","남원주-원주#1T/L 6896 ES 에어 누기 조치","2019-09-02 10:00","2019-09-02 18:00","2019-09-02 10:00","2019-09-02 18:00","당일"]
[205,"강원","직할","남춘천춘천열병합#1 T/L","2019년 가공송전선로 순시점검 위탁공사","초기점검 및 절연저항측정","2019-09-17 07:30","2019-09-20 18:00","2019-09-03 07:00","2019-09-03 18:00","매일"]
[206,"강원","직할","남춘천춘천열병합#2 T/L","2019년 가공송전선로 순시점검 위탁공사","초기점검 및 절연저항측정","2019-09-23 07:30","2019-09-26 18:00","2019-09-04 07:00","2019-09-04 18:00","매일"]
[207,"강원","직할","서홍천청평PP T/L","345kV 신가평-포천LNGCC T/L 항공장애시설물 정비공사 병가선로","ㅇ 항공장애표시구 설치 - No.37~41호 경간","2019-09-23 07:00","2019-09-24 18:00","취소","취소","연속"]
[208,"강원","직할","상남인제#1 T/L","2018년~2019년 강원지역본부 직할 변전정비 총액공사","154kV 효성제 GIS 비상트립장치 케이블 교체","2019-09-20 15:00","2019-09-20 17:00","2019-09-20 15:00","2019-09-20 17:00","당일"]
[209,"강원","직할","춘천북춘천#2 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","춘천북춘천#2T/L EBA PD진단센서 및 집합반 설치공사","2019-09-26 08:00","2019-09-26 18:00","취소","취소","당일"]
[210,"강원","직할","춘천북춘천#1 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","춘천북춘천#1T/L EBA PD진단센서 및 집합반 설치공사","2019-09-25 08:00","2019-09-25 18:00","취소","취소","당일"]
[211,"강원","직할","남춘천춘천 T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","남춘천춘천T/L EBA PD진단센서 및 집합반 설치공사","2019-09-25 08:00","2019-09-25 18:00","취소","취소","당일"]
[212,"강원","직할","춘천소양강HP T/L","154kV 인제-양구 등 12개T/L PD집합반 설치공사","춘천소양강HP T/L EBA PD진단센서 및 집합반 설치공사","2019-09-26 08:00","2019-09-26 18:00","취소","취소","당일"]
[213,"강원","직할","가평춘천HP T/L","154kV 화천T/L No.65~69 안전이격확보공사","No.65~69 철탑교체(5기), 전력선 2.132km 교체","2019-09-23 09:00","2019-10-06 18:00","2019-09-23 09:00","2019-10-06 18:00","연속"]
[214,"강원","직할","서홍천춘천열병합 T/L","2019년 가공송전선로 순시점검 위탁공사","초기점검 및 절연저항측정","2019-09-23 07:30","2019-09-25 18:00","취소","취소","매일"]
[215,"강원","직할","청평PP춘천열병합 T/L","2019년 가공송전선로 순시점검 위탁공사","초기점검 및 절연저항측정","2019-09-17 07:30","2019-09-19 18:00","취소","취소","연속"]
[216,"강원","직할","철원화천#2 T/L","2018년~2019년 강원지역본부 직할 변전정비 총액공사","154kV 효성제 GIS 비상트립장치 케이블 교체","2019-09-27 14:00","2019-09-27 18:00","2019-09-19 10:00","2019-09-19 14:00","당일"]
[217,"강원","직할","철원화천#1 T/L","2019년 상반기 장기 미동작 차단기 조작시험","차단기 조작시험","2019-09-27 10:00","2019-09-27 14:00","2019-09-19 14:00","2019-09-19 18:00","당일"]
[218,"강원","직할","가평화천HP T/L","154kV 화천T/L No.65~69 안전이격확보공사","No.65~69 철탑교체(5기), 전력선 2.132km 교체","2019-09-23 09:00","2019-10-06 18:00","2019-09-23 09:00","2019-10-06 18:00","연속"]
[219,"강원","태백","동해동영월 T/L","‘18∼19년 태백전력지사 송전정비 협력회사 총액공사","154kV 영월화력T/L 전력선 교체공사","2019-09-25 08:00","2019-10-04 18:00","2019-09-25 08:00","2019-10-04 18:00","연속"]
[220,"강원","태백","신제천영월CC#2 T/L","19년 태백전력지사 154kV GIS 정밀점검 공사","영월개폐소 신제천-영월CC #2/L GIS 정밀점검","2019-09-25 10:00","2019-09-26 18:00","2019-09-25 10:00","2019-09-26 18:00","연속"]
[221,"강원","태백","영월C/C 154kV 영월G/T#3T/L CB","2019년 영월발전본부 발전설비 계획예방정비 공사","영월발전본부 GT#3 점검 / [병행] 9/4(수) 영월CC GT#3 GIS 보통점검","2019-09-02 10:00","2019-09-18 15:00","2019-09-02 10:00","2019-09-18 15:00","연속"]
[222,"강원","태백","영월C/C 154kV 영월S/T#1T/L CB","2019년 영월발전본부 발전설비 계획예방정비 공사","영월발전본부 ST#1 점검 / [병행] 9/5(목) 영월CC ST #1 GIS 보통점검","2019-09-02 10:00","2019-10-25 15:00","2019-09-02 10:00","2019-10-25 15:00","연속"]
[223,"강원","태백","신제천영월CC#1 T/L","19년 태백전력지사 154kV GIS 정밀점검 공사","영월개폐소 신제천-영월CC #1T/L GIS 정밀점검","2019-09-23 10:00","2019-09-24 18:00","2019-09-23 10:00","2019-09-24 18:00","연속"]
[224,"강원","태백","정선영월CC T/L","‘18∼19년 태백전력지사 송전정비 협력회사 총액공사","154kV 영월화력T/L 전력선 교체공사","2019-09-16 08:00","2019-09-24 18:00","2019-09-16 08:00","2019-09-24 18:00","연속"]
[225,"강원","태백","영월C/C 154kV 영월G/T#2T/L CB","2019년 영월발전본부 발전설비 계획예방정비 공사","영월발전본부 GT#2 점검 / [병행] 9/6(금) 영월CC GT#2 GIS 보통점검","2019-09-02 10:00","2019-10-25 15:00","2019-09-02 10:00","2019-10-25 15:00","연속"]
[226,"강원","태백","영월S/S 154kV 영월G/T#1T/L CB","2019년 영월발전본부 발전설비 계획예방정비 공사","영월발전본부 GT#1 점검 / [병행] 9/18(수) 영월SS GT #1 GIS 보통점검","2019-09-18 10:00","2019-10-25 10:00","2019-09-18 10:00","2019-10-25 10:00","연속"]
[227,"강원","태백","이원태백 T/L","19년 태백전력지사 154kV GIS 정밀점검 공사","태백변전소 이원태백T/L GIS 정밀점검","2019-09-05 09:00","2019-09-07 18:00","2019-09-05 09:00","2019-09-07 18:00","연속"]
[228,"강원","태백","태백삼척GP#1 T/L","19년 태백전력지사 154kV GIS 정밀점검 공사","태백변전소 태백-삼척GP #1T/L GIS 정밀점검","2019-09-02 09:00","2019-09-04 18:00","2019-09-02 09:00","2019-09-04 18:00","연속"]
[229,"충북","직할","광혜원S/S 154kV #60-#65 BUS TIE GIS","광혜원S/S 154kV #60-65BUSTIE GIS 보통점검","광혜원S/S 154kV #60-65BUSTIE GIS 보통점검","2019-09-16 10:00","2019-09-16 18:00","2019-09-16 10:00","2019-09-16 18:00","당일"]
[230,"충북","직할","진천광혜원#2 T/L","2019년 가공송전선로 순시점검 위탁공사(충북 직할)","정밀점검(No.27~46)","2019-09-28 08:00","2019-09-29 18:00","2019-09-28 08:00","2019-09-29 18:00","매일"]
[231,"충북","직할","진천광혜원#1 T/L","2018~19년 충주전력지사 송전정비회사 총액공사","압축인류클램프 교체(만승S/S), 아킹혼 교체(11,37,49)","2019-09-21 07:00","2019-09-22 18:00","2019-09-21 07:00","2019-09-22 18:00","매일"]
[232,"충북","직할","서운광혜원 T/L","2019년 가공송전선로 순시점검 위탁공사(충북 직할)","정밀점검(No.29~56)","2019-09-18 08:00","2019-09-22 18:00","2019-09-18 08:00","2019-09-22 18:00","매일"]
[233,"충북","청주","남청주오송#1 T/L","345kV 신옥천-남청주구간 OPGW 시설공사","345kV 신옥천-남청주구간 가공지선 철거 및 OPGW 34km 시설","2019-09-15 09:00","2019-09-15 18:00","2019-09-15 09:00","2019-09-15 18:00","연속"]
[234,"충북","청주","남청주죽림#1 T/L","18-19년 청주전력 변전협력회사 총액공사","남청주,죽림S/S 154kV 남청주죽림#1T/L 보통점검 죽림S/S 154kV 남청주죽림#1T/L 피뢰기 대체","2019-09-21 10:00","2019-09-22 18:00","2019-09-21 10:00","2019-09-22 18:00","연속"]
[235,"충북","청주","부강신탄진 T/L","청주전력지사 송전정비 협력회사 총액공사","No.13, 17, 18, 19 (9개소) 불량 압축인류크램프 및 잠바소켓 교체작업","2019-09-23 08:00","2019-09-26 18:00","2019-09-23 08:00","2019-09-26 18:00","매일"]
[236,"충북","청주","부강월산#1 T/L","청주전력지사 송전정비 협력회사 총액공사","No.2,3,6,8,10,12,13 (9개소) 불량 압축인류크램프 및 잠바소켓 교체작업","2019-09-18 08:00","2019-09-20 18:00","2019-09-18 08:00","2019-09-20 18:00","매일"]
[237,"충북","청주","부강대청HP T/L","청주전력지사 송전정비 협력회사 총액공사","No.2,3,6,8,10,12,13 (9개소) 불량 압축인류크램프 및 잠바소켓 교체작업","2019-09-18 08:00","2019-09-20 18:00","2019-09-18 08:00","2019-09-20 18:00","연속"]
[238,"충북","청주","서청주사직#2 T/L","18-19년 청주전력 변전협력회사 총액공사","서청주S/S 154kV 서청주사직#2T/L 보호반 대체 사직S/S 154kV 서청주사직#2T/L 보호반 대체","2019-09-28 10:00","2019-09-29 18:00","2019-09-28 10:00","2019-09-29 18:00","연속"]
[239,"충북","청주","신옥천추부#2 T/L","신옥천S/S 154kV GIS화 공사","154kV GIS 26CCT 설치(옥외철구→GIS 부하절체)","2019-09-27 09:00","2019-10-02 18:00","2019-09-28 09:00","2019-10-03 18:00","연속"]
[240,"충북","청주","신옥천남대전#1 T/L","신옥천S/S 154kV GIS화 공사","154kV GIS 26CCT 설치(옥외철구→GIS 부하절체)","2019-09-27 09:00","2019-10-02 18:00","2019-09-27 09:00","2019-10-02 18:00","연속"]
[241,"충북","충주","단양영월CC#2 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 단양영월CC#2 T/L 정밀점검(No.1~1.4)","2019-09-17 08:00","2019-09-17 18:00","2019-09-17 08:00","2019-09-17 18:00","당일"]
[242,"충북","충주","단양영월CC#1 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 단양영월CC#1 T/L 정밀점검(No.1~1.4)","2019-09-16 08:00","2019-09-16 18:00","2019-09-16 08:00","2019-09-16 18:00","당일"]
[243,"충북","충주","신제천주진#2 T/L","18-19년 충북직할 변전정비 총액공사","154kV GIS 보통점검.","2019-09-17 09:00","2019-09-17 18:00","2019-09-17 09:00","2019-09-17 18:00","당일"]
[244,"충북","충주","신제천왕암#2 T/L","왕암E/C 건물 누수 관련 원인 파악을 위한 인근 송전선로 안전이격 휴전","왕암E/C 건물 누수 관련 원인 파악을 위한 인근 송전선로 안전이격 휴전","2019-09-03 10:00","2019-09-03 18:00","2019-09-03 10:00","2019-09-03 18:00","당일"]
[245,"충북","충주","제천영월#1 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 단양영월CC#1 T/L 정밀점검 안전이격확보(No.1~1.4)","2019-09-16 08:00","2019-09-16 18:00","2019-09-16 08:00","2019-09-16 18:00","당일"]
[246,"충북","충주","제천영월#2 T/L","2019년 가공송전선로 순시점검 위탁공사(정밀점검)","154kV 단양영월CC#2 T/L 정밀점검 안전이격확보(No.1~1.4)","2019-09-17 08:00","2019-09-17 18:00","2019-09-17 08:00","2019-09-17 18:00","당일"]
[247,"충북","충주","신제천제천#1 T/L","154kV 신제천-제천T/L 노후 피뢰기 교체공사","ㅇ 154kV 신제천-제천#1 T/L 피뢰기 교체공사 - 대상 : #1T/L 자기제 피뢰기 3기 - 내용 : 자기제 → 폴리머 피뢰기 교체공사","2019-09-26 09:00","2019-09-26 18:00","2019-09-26 09:00","2019-09-26 18:00","당일"]
[248,"충북","충주","신제천제천#2 T/L","154kV 신제천-제천T/L 노후 피뢰기 교체공사","ㅇ 154kV 신제천-제천#2T/L 피뢰기 교체공사 - 대상 : #2T/L 자기제 피뢰기 3기 - 내용 : 자기제 → 폴리머 피뢰기 교체공사","2019-09-27 09:00","2019-09-27 18:00","2019-09-27 09:00","2019-09-27 18:00","당일"]
[249,"대전충남","대전","남대전신흥#3 T/L","남대전S/S 154kV 남대전-신흥#3T/L 보호반 성능개선 및 병행작업","남대전S/S 154kV 남대전-신흥#3T/L 보호반 성능개선 및 병행작업","2019-09-20 09:00","2019-09-20 18:00","2019-09-20 09:00","2019-09-20 18:00","당일"]
[250,"대전충남","대전","팔봉두마#1 T/L","OPGW 항공장애표시구 교체공사","154kV 신계룡-은진#2T/L OPGW 불량 항공장애표시구 교체 (No.24~25, 2개)","2019-09-25 09:00","2019-09-25 18:00","2019-09-25 09:00","2019-09-25 18:00","당일"]
[251,"대전충남","서산","당진S/S 154kV #1 SC","당진S/S 154kV측 취약설비 GIS화 공사","#1SH.C용 전력케이블 활용 신설 및 기설 모선 연결 - 기설 GCB와 Sh.C 간 결선분리 - 기설 GCB와 EBA 간 연결 - 기타부대작업","2019-09-09 09:00","2019-10-31 18:00","2019-09-09 09:00","2019-10-31 18:00","연속"]
[252,"대전충남","서산","신당진당진#2 T/L","당진S/S 154kV측 취약설비 GIS화 공사","154kV 옥외철구형 설비 GIS화 - 옥외설비 철거(GCB, DS, GIDS, LA, CVT 등) - 옥외철구 전력선 교체(CU-&gtAL) 디지털 혼용운영시스템 이설 신설GIS 무부하 가압(24H)","2019-09-20 08:00","2019-09-25 18:00","2019-09-20 08:00","2019-09-25 18:00","연속"]
[253,"대전충남","서산","당진송악#1 T/L","당진S/S 154kV측 취약설비 GIS화 공사","154kV 옥외철구형 설비 GIS화 - 옥외설비 철거(GCB, DS, GIDS, LA, CVT 등) - 옥외철구 전력선 교체(CU-&gtAL) 디지털 혼용운영시스템 이설","2019-09-20 09:00","2019-09-25 18:00","2019-09-20 09:00","2019-09-25 18:00","연속"]
[254,"대전충남","서산","당진화력S/Y 154kV #1 BUS TIE CB","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 - 당진T/P 154kV #1 BUS TIE (6100)CB","2019-09-23 10:00","2019-09-23 14:00","2019-09-23 10:00","2019-09-23 14:00","당일"]
[255,"대전충남","서산","서산태안화력 T/L","154kV 서산-태안화력T/L 항공장애표시구 철거","154kV 서산-태안화력T/L No.38~39","2019-09-22 09:00","2019-09-22 18:00","2019-09-28 09:00","2019-09-28 18:00","당일"]
[256,"대전충남","서산","신당진S/S 154kV #60 BUS","19년도 서산P/O 154kV GIS 정밀점검공사","- 신당진S/S 154kV 신당진-당진#2T/L #1DS 정밀점검","2019-09-21 09:00","2019-09-21 18:00","2019-09-21 09:00","2019-09-21 18:00","당일"]
[257,"대전충남","서산","신당진S/S 154kV #65 BUS","19년도 서산P/O 154kV GIS 정밀점검공사","- 신당진S/S 154kV 신당진-당진#2T/L #2DS 정밀점검","2019-09-22 09:00","2019-09-22 18:00","2019-09-22 09:00","2019-09-22 18:00","당일"]
[258,"대전충남","세종","신풍공주#2 T/L","2019년 세종P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검 11BAY - 공주S/S 154kV #1Sh.C GIS 등 5BAY - 덕진S/S 대덕-덕진#1T/L GIS 등 6BAY","2019-09-26 09:00","2019-09-27 18:00","2019-09-26 09:00","2019-09-27 18:00","연속"]
[259,"대전충남","세종","신풍공주#1 T/L","2019년 세종P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검 11BAY - 공주S/S 154kV #1Sh.C GIS 등 5BAY - 덕진S/S 대덕-덕진#1T/L GIS 등 6BAY","2019-09-24 09:00","2019-09-25 18:00","2019-09-24 09:00","2019-09-25 18:00","연속"]
[260,"대전충남","세종","덕진송강#1 T/L","154kV 세종-송강, 덕진-대화 연결 지중T/L 건설공사","1. 설치 가. 세종-송강 : 신설C/H~M/H#4 나. 덕진-대화 : 덕진E/C~신설C/H 2. 철거 : 덕진-송강T/L(덕진E/C~M/H#4)","2019-09-23 09:30","2019-10-08 17:00","2019-09-23 09:30","2019-10-08 17:00","연속"]
[261,"대전충남","세종","서세종S/S 154kV #60-#65 BUS TIE GIS","154kV 모선보호반 계전기 성능개선(YPP)","모선보호반 계전기 성능개선 및 GIS 연동시험 병행","2019-09-25 09:00","2019-09-25 18:00","2019-09-25 09:00","2019-09-25 18:00","당일"]
[262,"대전충남","세종","부강월산#2 T/L","154kV 부강-월산T/L 불량애자교체공사","[송전] 부강-월산#2T/L 불량애자교체 6기 - No.11 20 22 31 36 39","2019-09-16 07:00","2019-09-17 18:00","2019-09-16 07:00","2019-09-17 18:00","매일"]
[263,"대전충남","아산","인주탕정#1 T/L","인주,탕정S/S 인주-탕정#1T/L GIS 보통점검 및 전자변 교체","인주,탕정S/S 인주-탕정#1T/L GIS 보통점검 및 전자변 교체","2019-09-28 09:00","2019-09-28 18:00","2019-09-28 09:00","2019-09-28 18:00","당일"]
[264,"대전충남","청양","관창보령화력 T/L","[송전] 154kV 보관T/L 전력선 부식상태 진단","○ 철탑구간 : No.1~8 , 11~15 ○ 품셈실사 3회 병행시행 예정","2019-09-23 09:00","2019-09-25 18:00","2019-09-23 09:00","2019-09-25 18:00","매일"]
[265,"대전충남","청양","보령TP보령CC T/L","보령T/P 154kV보령복합T/L 차단기 전자변 교체","보령T/P 154kV보령복합T/L 차단기 전자변 교체 - 메커니즘 점검 - 차단기 부동작 예방 조작시험","2019-09-26 09:00","2019-09-26 18:00","2019-09-26 09:00","2019-09-26 18:00","당일"]
[266,"대전충남","청양","보령T/P 154kV #60-#65 BUS TIE CB","보령T/P Bus-Tie(6100) 전자변 교체 및 메커니즘 점검","보령T/P Bus-Tie(6100) 전자변 교체 및 메커니즘 점검 - 메커니즘 점검 - 차단기 부동작 예방 조작시험","2019-09-30 09:00","2019-09-30 18:00","2019-09-30 09:00","2019-09-30 18:00","당일"]
[267,"전북","군산","군산S/S 154kV #66 BUS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #61M.Tr 1차 GIS 정밀점검공사 (군산-동군산#1T/L 활용 무부하 가압)","2019-09-03 15:00","2019-09-03 17:00","2019-09-03 15:00","2019-09-03 17:00","연속"]
[268,"전북","군산","군산S/S 154kV 군산-영등#2T/L GIS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV 군산-영등#2T/L GIS 정밀점검공사","2019-09-09 09:00","2019-09-10 18:00","2019-09-09 09:00","2019-09-10 18:00","연속"]
[269,"전북","군산","군산S/S 154kV 군산-영등#1T/L GIS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV 군산-영등#1T/L GIS 정밀점검공사","2019-09-04 09:00","2019-09-05 18:00","2019-09-04 09:00","2019-09-05 18:00","연속"]
[270,"전북","군산","군산S/S 154kV 군산-동군산#1T/L GIS","군산P/O 170kV GIS 정밀점검공사","군산S/S 170kV #61M.Tr 1차 GIS 정밀점검공사 (군산-동군산#1T/L 활용 무부하 가압)","2019-09-03 15:00","2019-09-03 17:00","2019-09-03 15:00","2019-09-03 17:00","연속"]
[271,"전북","군산","내초S/S 154kV #60 BUS","내초S/S #3M.Tr 1차 GIS 부분방전 해소공사","1. 내초S/S #3M.Tr 1차 GIS 부분방전 해소","2019-09-26 09:00","2019-09-27 18:00","2019-09-26 09:00","2019-09-27 18:00","연속"]
[272,"전북","군산","군공내초#2 T/L","군산P/O 154kV 차단기 점검공사","1.군공-내초#2T/L 차단기 하자점검","2019-09-10 09:30","2019-09-10 18:00","2019-09-10 09:30","2019-09-10 18:00","당일"]
[273,"전북","군산","내초군장#1 T/L","내초S/S #3M.Tr 1차 GIS 부분방전 해소공사","1. 내초S/S #3M.Tr 1차 GIS 부분방전 해소","2019-09-26 09:00","2019-09-27 18:00","2019-09-26 09:00","2019-09-27 18:00","연속"]
[274,"전북","군산","군공내초#1 T/L","군산P/O 154kV 차단기 점검공사","1.군공-내초#1T/L 차단기 하자점검","2019-09-09 09:30","2019-09-09 18:00","2019-09-09 09:30","2019-09-09 18:00","당일"]
[275,"전북","군산","서군산S/S 154kV #60-#65 BUS TIE CB","서군산S/S 현대화관련 부지확보공사","서군산S/S 현대화관련 부지확보공사","2019-09-02 09:00","2019-09-07 18:00","2019-09-02 09:00","2019-09-07 18:00","연속"]
[276,"전북","군산","서군산S/S 154kV #60 BUS","서군산S/S 현대화관련 부지확보공사","서군산S/S 현대화관련 부지확보공사","2019-09-02 09:00","2019-09-07 18:00","2019-09-02 09:00","2019-09-07 18:00","연속"]
[277,"전북","군산","서군산소룡#1 T/L","서군산S/S 현대화관련 부지확보공사","서군산S/S 현대화관련 부지확보공사","2019-09-02 09:00","2019-09-07 18:00","2019-09-02 09:00","2019-09-07 18:00","연속"]
[278,"전북","군산","익산전철#2 T/L CB","군산P/O 154kV 차단기 점검공사","1. 익산전철#2T/L 차단기 하자점검","2019-09-06 09:30","2019-09-06 18:00","취소","취소","당일"]
[279,"전북","군산","이리백산#2 T/L","이리백산T/L 항공장애표시구설치공사","항공장애구 설치 - 36~36,38~39, 39~40","2019-09-26 08:00","2019-09-27 18:00","2019-09-26 08:00","2019-09-27 18:00","매일"]
[280,"전북","군산","익산전철#1 T/L CB","군산P/O 154kV 차단기 점검공사","1. 익산전철#1T/L 차단기 하자점검","2019-09-05 09:30","2019-09-05 18:00","취소","취소","당일"]
[281,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2019-09-30 08:00","2019-09-30 18:00","2019-09-30 08:00","2019-09-30 18:00","당일"]
[282,"전북","김제","백산김제#1 T/L","이리백산T/L 항공장애표시구설치공사","항공장애구 설치 - 36~36,38~39, 39~40","2019-09-26 08:00","2019-09-27 18:00","2019-09-26 08:00","2019-09-27 18:00","매일"]
[283,"전북","김제","신김제동전주#2 T/L","154kV 신김제-정공T/L 정밀점검","No.1~11호 4회선 구간 안전거리 확보.","2019-09-30 08:00","2019-10-01 17:00","2019-09-28 08:00","2019-09-29 17:00","매일"]
[284,"전북","김제","신김제동전주#2 T/L","154kV 신김제-정공T/L 정밀점검","No.1~11호 4회선 구간 안전거리 확보.","2019-09-16 08:00","2019-09-17 17:00","2019-09-21 08:00","2019-09-22 17:00","매일"]
[285,"전북","김제","정공S/S 154kV #60 BUS","154kV 정공E/C #5M.Tr 및 KCFT T/L 증설 공사","- 154kV M.Tr(15/20MVA *3대) * 1BANK 설치 - 170kV GIS(1250A) * 2CCT 설치 - 22.9kV GIS(2000A, 600A) * 4CCT 설치","2019-09-23 08:00","2019-10-01 18:00","2019-09-23 08:00","2019-10-01 18:00","연속"]
[286,"전북","김제","신김제정공#1 T/L","154kV 정공E/C #5M.Tr 및 KCFT T/L 증설 공사","- 154kV M.Tr(15/20MVA *3대) * 1BANK 설치 - 170kV GIS(1250A) * 2CCT 설치 - 22.9kV GIS(2000A, 600A) * 4CCT 설치","2019-09-23 08:00","2019-10-07 18:00","2019-09-23 08:00","2019-10-07 18:00","연속"]
[287,"전북","김제","정공S/S 154kV #60-#65 BUS TIE CB","154kV 정공E/C #5M.Tr 및 KCFT T/L 증설 공사","- 154kV M.Tr(15/20MVA *3대) * 1BANK 설치 - 170kV GIS(1250A) * 2CCT 설치 - 22.9kV GIS(2000A, 600A) * 4CCT 설치","2019-09-23 08:00","2019-10-07 18:00","2019-09-23 08:00","2019-10-07 18:00","연속"]
[288,"전북","김제","신김제정공#2 T/L","154kV 신김제-정공T/L 정밀점검","No.1~88호 정밀점검","2019-09-16 08:00","2019-09-20 18:00","2019-09-16 08:00","2019-09-20 18:00","연속"]
[289,"전북","직할","무주용담수력 T/L","관내S/S 노후배전반 대체공사","1. 154kV 무주-용담수력T/L 보호배전반 대체","2019-09-16 10:00","2019-09-27 18:00","2019-09-16 10:00","2019-09-27 18:00","연속"]
[290,"광주전남","강진","강진S/S 154kV 신강진-강진#2T/L CB","강진S/S 154kV이하 취약설비 GIS화 사업","강진,신강진,남창S/S 보호배전반 대체, 시험 강진-남창#2T/L, 신강진-강진#2T/L 직결","2019-09-16 09:00","2019-10-31 18:00","2019-09-16 09:00","2019-10-31 18:00","연속"]
[291,"광주전남","강진","강진S/S 154kV 강진-남창#2T/L CB","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,신강진,남창S/S 보호배전반 대체, 시험 강진-남창#2T/L, 신강진-강진#2T/L 직결","2019-09-16 09:00","2019-10-31 18:00","2019-09-16 09:00","2019-10-31 18:00","연속"]
[292,"광주전남","강진","강진남창#1 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,남창S/S 보호배전반 대체, 시험, LA, CVT 이설 송전선로 철거 및 가선, 선로접속, 모선POST 철거 OPGW 설치 및 시험","2019-09-24 09:00","2019-10-05 18:00","2019-09-24 09:00","2019-10-05 18:00","연속"]
[293,"광주전남","강진","남창S/S 154kV 강진-남창#2T/L CB A","강진S/S 154kV 이하 취약설비 GIS화 사업","강진,신강진,남창S/S 보호배전반 대체, 시험 강진-남창#2T/L, 신강진-강진#2T/L 직결","2019-09-16 09:00","2019-09-23 18:00","취소","취소","연속"]
[294,"광주전남","강진","해남C/S 154kV #2 C.Tr 1차 GIS","#1HVDC 노후변환섧비 교체사업","역송, CLD, 임시모선모드, Schim Control 현장부하시험","2019-09-23 09:00","2019-11-16 18:00","2019-09-23 09:00","2019-11-16 18:00","연속"]
[295,"광주전남","강진","해남C/S 154kV #1 DTF GIS","#1HVDC 노후변환섧비 교체사업","역송, CLD, 임시모선모드, Schim Control 현장부하시험","2019-09-23 09:00","2019-11-16 18:00","2019-09-23 09:00","2019-11-16 18:00","연속"]
[296,"광주전남","강진","해남C/S 154kV #1 Sh.C GIS","#1HVDC 노후변환섧비 교체사업","역송, CLD, 임시모선모드, Schim Control 현장부하시험","2019-09-23 09:00","2019-11-16 18:00","2019-09-23 09:00","2019-11-16 18:00","연속"]
[297,"광주전남","강진","해남C/S 154kV #1 HPF GIS","#1HVDC 노후변환섧비 교체사업","역송, CLD, 임시모선모드, Schim Control 현장부하시험","2019-09-23 09:00","2019-11-16 18:00","2019-09-23 09:00","2019-11-16 18:00","연속"]
[298,"광주전남","강진","해남C/S 154kV #1 C.Tr 1차 GIS","#1HVDC 노후변환섧비 교체사업","역송, CLD, 임시모선모드, Schim Control 현장부하시험","2019-09-23 09:00","2019-11-16 18:00","2019-09-23 09:00","2019-11-16 18:00","연속"]
[299,"광주전남","강진","해남C/S 154kV #2 Sh.C GIS","#1HVDC 노후변환섧비 교체사업","역송, CLD, 임시모선모드, Schim Control 현장부하시험","2019-09-23 09:00","2019-11-16 18:00","2019-09-23 09:00","2019-11-16 18:00","연속"]
[300,"광주전남","강진","해남C/S 154kV #2 HPF GIS","#1HVDC 노후변환섧비 교체사업","역송, CLD, 임시모선모드, Schim Control 현장부하시험","2019-09-23 09:00","2019-11-16 18:00","2019-09-23 09:00","2019-11-16 18:00","연속"]
[301,"광주전남","강진","해남C/S 154kV #2 DTF GIS","#1HVDC 노후변환섧비 교체사업","역송, CLD, 임시모선모드, Schim Control 현장부하시험","2019-09-23 09:00","2019-11-16 18:00","2019-09-23 09:00","2019-11-16 18:00","연속"]
[302,"광주전남","광주","계림충장#3 T/L","19년 광주 변전 총액공사 (계림-충장3T/L)","계림-충장#3T/L 양단 보호반 교체, 계림S/S GIS 보통점검, 충장S/S 장기미동작CB점검","2019-09-23 09:00","2019-09-25 18:00","2019-09-23 09:00","2019-09-25 18:00","연속"]
[303,"광주전남","광주","계림충장#2 T/L","19년 광주 변전 총액공사 (계림-충장2T/L)","계림-충장#2T/L 양단 보호반 교체, 계림S/S GIS 보통점검, 충장S/S 장기미동작CB점검","2019-09-04 09:00","2019-09-06 18:00","2019-09-04 09:00","2019-09-06 18:00","연속"]
[304,"광주전남","광주","신광주장성#2 T/L","154kV 인출선로 모선 재배열공사","가. 공사장소 : 신광주S/S 154kV 인출선로 나. 휴전선로 : 154kV 신광주-곡성#1T/L 다. 작업내용 - 인출선로 모선 재배열을 위한 선로 재배열공사 - 선종/길이 : 신광주-곡성#1T/L(XLPE 2000SQ X 1C(D) X 0.07km) 신광주-장성#2T/L(XLPE 2000SQ X 1C(D","2019-09-30 09:00","2019-09-30 18:00","2019-09-30 09:00","2019-09-30 18:00","연속"]
[305,"광주전남","광주","신광주곡성#1 T/L","154kV 인출선로 모선 재배열공사","가. 공사장소 : 신광주S/S 154kV 인출선로 나. 휴전선로 : 154kV 신광주-곡성#1T/L 다. 작업내용 - 인출선로 모선 재배열을 위한 선로 재배열공사 - 선종/길이 : 신광주-곡성#1T/L(XLPE 2000SQ X 1C(D) X 0.07km) 신광주-장성#2T/L(XLPE 2000SQ X 1C(D) X 0.07km)","2019-09-17 09:00","2019-10-25 18:00","2019-09-17 09:00","2019-10-25 18:00","연속"]
[306,"광주전남","광주","하남장성#2 T/L","19년 광주변전총액(장기미동작차단기 점검)","장성S/S 하남-장성#2T/L 장기미동작차단기 점검","2019-09-11 14:00","2019-09-11 18:00","2019-09-11 14:00","2019-09-11 18:00","당일"]
[307,"광주전남","광주","하남장성#1 T/L","19년 광주변전총액(장기미동작차단기 점검)","장성S/S 하남-장성#1T/L 장기미동작차단기 점검","2019-09-11 09:00","2019-09-11 14:00","2019-09-11 09:00","2019-09-11 14:00","당일"]
[308,"광주전남","목포","장성영광#1 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.117~125호","2019-09-19 07:00","2019-09-22 18:00","2019-09-19 07:00","2019-09-22 18:00","연속"]
[309,"광주전남","목포","영광홍농 T/L","영광-홍농T/L No.21-28호 OPGW 교체공사","영광-홍농 No21~28호(장성-영광T/L No.139-146호) 서비스 지장구간 OPGW 교체공사","2019-09-19 07:00","2019-09-22 18:00","2019-09-19 07:00","2019-09-22 18:00","연속"]
[310,"광주전남","목포","장성영광#2 T/L","154kV장성-영광T/L전선접속개소전선교체공사","0 전선 및 금구류 교체 : No.117~125호","2019-09-23 07:00","2019-09-26 18:00","2019-09-23 07:00","2019-09-26 18:00","연속"]
[311,"광주전남","순천","순천율촌#2 T/L","154kV 순천-율촌T/L 케이블헤드(EB-A) 진단센서 설치공사","- UWB 센서 설치 : 3상 - 동축케이블 포설(EB-A ~ C/H기초) - PD집합반 설치","2019-09-26 14:00","2019-09-26 18:00","2019-09-26 14:00","2019-09-26 18:00","당일"]
[312,"광주전남","순천","순천율촌#1 T/L","154kV 순천-율촌T/L 케이블헤드(EB-A) 진단센서 설치공사","- UWB 센서 설치 : 3상 - 동축케이블 포설(EB-A ~ C/H기초) - PD집합반 설치","2019-09-26 09:00","2019-09-26 14:00","2019-09-26 09:00","2019-09-26 14:00","당일"]
[313,"광주전남","순천","여수TP화치#1 T/L","19년 순천 변전협력회사 총액공사","[여수화력] #1, 2DS 댐퍼 및 CT 단자대교체 [화치] GIS 보조계전기 교체","2019-09-23 10:00","2019-09-23 18:00","2019-09-23 10:00","2019-09-23 18:00","당일"]
[314,"광주전남","순천","여수T/P 154kV #60-#61 SEC GIS","19년 순천 변전협력회사 총액공사","[여수화력] 60-65BUS SEC GIS #2DS 댐퍼교체","2019-09-24 10:00","2019-09-24 18:00","2019-09-24 10:00","2019-09-24 18:00","당일"]
[315,"광주전남","순천","여천S/S 154kV 여수TP-여천#1T/L GIS","한화석유T/L 운휴설비 지중케이블 철거 공사","여천S/S 한화석유T/L C/H 막음처리 관련 안전 이격거리 확보","2019-09-30 09:00","2019-10-01 18:00","2019-09-30 09:00","2019-10-01 18:00","연속"]
[316,"대구","경산","노변효목#1 T/L","일진제 PMJ교체공사","일진제 R-Type PMJ 교체","2019-09-16 09:00","2019-09-21 18:00","2019-09-16 09:00","2019-09-21 18:00","연속"]
[317,"대구","경산","노변효목#2 T/L","일진제 PMJ교체공사","일진제 R-Type PMJ 교체","2019-09-23 09:00","2019-09-28 18:00","2019-09-23 09:00","2019-09-28 18:00","연속"]
[318,"대구","달성","대구범물#1 T/L","2018~19년도 대구지역본부 직할 가공송전 정비회사 총액공사","154kV 대구-범물#1T/L 회전형 스페이서 설치공사 -No.19~20, 21~22, 38~39","2019-09-09 08:00","2019-09-09 18:00","2019-09-09 08:00","2019-09-09 18:00","당일"]
[319,"대구","달성","대구봉덕#2 T/L","대구,봉덕S/S 대구-봉덕#2T/L 보호반대체작업","대구,봉덕S/S 대구-봉덕#2T/L 보호반대체작업","2019-09-02 09:00","2019-09-03 18:00","2019-09-18 09:00","2019-09-19 18:00","연속"]
[320,"대구","달성","내당두류#2 T/L","두류S/S 모선보호반 대체작업(TEST)","두류S/S 모선보호반 대체작업(TEST)","2019-09-27 15:30","2019-09-27 16:00","2019-09-27 15:30","2019-09-27 16:00","당일"]
[321,"대구","달성","두류봉덕#2 T/L","두류S/S 모선보호반 대체작업(TEST)","두류S/S 모선보호반 대체작업(TEST)","2019-09-27 16:30","2019-09-27 17:00","2019-09-27 16:30","2019-09-27 17:00","당일"]
[322,"대구","달성","두류봉덕#1 T/L","두류S/S 모선보호반 대체작업(TEST)","두류S/S 모선보호반 대체작업(TEST)","2019-09-27 16:00","2019-09-27 16:30","2019-09-27 16:00","2019-09-27 16:30","당일"]
[323,"대구","달성","내당두류#1 T/L","두류S/S 모선보호반 대체작업(TEST)","두류S/S 모선보호반 대체작업(TEST)","2019-09-27 14:30","2019-09-27 15:00","2019-09-27 14:30","2019-09-27 15:00","당일"]
[324,"대구","칠곡","구미광평#2 T/L","광평S/S 구미-광평#2T/L GIS 장기미동작점검","광평S/S 구미-광평#2T/L GIS 장기미동작점검","2019-09-20 14:00","2019-09-20 18:00","취소","취소","당일"]
[325,"대구","칠곡","남구미광평#1 T/L","2018~19년 송전정비회사 총액공사","154kV남구미-광평T/L 15호 철거","2019-09-02 08:00","2019-09-04 18:00","2019-09-02 08:00","2019-09-04 18:00","연속"]
[326,"대구","칠곡","남구미광평#2 T/L","2018~19년 송전정비회사 총액공사","(안전확보)154kV남구미-광평T/L 15호 철거","2019-09-02 08:00","2019-09-04 18:00","2019-09-02 08:00","2019-09-04 18:00","연속"]
[327,"대구","포항","울주입실#2 T/L","2019년도 가공송전 순시점검 위탁공사","154kV영일-입실 T/L 송전선로 정밀점검 안전확보차","2019-09-30 08:00","2019-10-01 18:00","2019-09-30 08:00","2019-10-01 18:00","연속"]
[328,"대구","포항","울주입실#1 T/L","2019년도 가공송전 순시점검 위탁공사","345kV울주-월성NP#1 T/L 송전선로 정밀점검 안전확보차","2019-09-24 08:00","2019-09-25 18:00","2019-09-24 08:00","2019-09-25 18:00","연속"]
[329,"경북","구미","선산S/S 154kV 선산-청리#2T/L GIS","19년 구미전력지사 변전정비업체 총액공사","- GIS 조작시험","2019-09-27 15:00","2019-09-27 18:00","취소","취소","당일"]
[330,"경북","구미","선산S/S 154kV 선산-청리#1T/L GIS","19년 구미전력지사 변전정비업체 총액공사","- GIS 조작시험 - LA 대체공사","2019-09-27 09:00","2019-09-27 15:00","취소","취소","당일"]
[331,"경북","구미","선산S/S 154kV #5 Sh.C","선산S/S 노후배전반 대체공사","선산S/S 노후배전반 대체공사","2019-09-16 08:30","2015-09-18 17:00","취소","취소","연속"]
[332,"경북","구미","선산S/S 154kV #3 Sh.C","선산S/S 노후배전반 대체공사","선산S/S 노후배전반 대체공사","2019-09-05 08:30","2015-09-08 17:00","취소","취소","연속"]
[333,"경북","구미","선산S/S 154kV #4 Sh.C","선산S/S 노후배전반 대체공사","선산S/S 노후배전반 대체공사 (SH.C 고장으로 운휴중)","2019-09-21 08:30","2015-09-30 17:00","취소","취소","연속"]
[334,"경북","구미","선산S/S 154kV #2 Sh.C","선산S/S 노후배전반 대체공사","선산S/S 노후배전반 대체공사","2019-09-05 08:30","2015-09-08 17:00","취소","취소","연속"]
[335,"경북","구미","선산S/S 154kV #1 Sh.C","선산S/S 노후배전반 대체공사","선산S/S 노후배전반 대체공사(설비고장으로 운휴중)","2019-09-21 08:30","2015-09-30 17:00","취소","취소","연속"]
[336,"경북","구미","선산S/S 154kV #6 Sh.C","선산S/S 노후배전반 대체공사","선산S/S 노후배전반 대체공사","2019-09-16 08:30","2015-09-18 17:00","취소","취소","연속"]
[337,"경북","영주","점촌단양 T/L","2018-19년도 영주전력지사 변전협력업체 총액공사","점촌S/S 점촌-단양T/L 피뢰기 교체","2019-09-28 09:00","2019-09-28 18:00","2019-09-28 09:00","2019-09-28 18:00","당일"]
[338,"경북","직할","안동복합S/S 154kV #60-#65 BUS TIE GIS","18~19년 경북본부 직할 변전정비회사 총액공사","안동복합S/S 6100GIS 조작시험","2019-09-10 16:00","2019-09-10 18:00","2019-09-10 16:00","2019-09-10 18:00","당일"]
[339,"경북","직할","풍산안동CC#2 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","안동복합S/S, 풍산S/S GIS 조작시험","2019-09-06 14:00","2019-09-06 18:00","2019-09-06 14:00","2019-09-06 18:00","당일"]
[340,"경북","직할","풍산안동CC#1 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","안동복합S/S, 풍산S/S GIS 조작시험","2019-09-06 09:00","2019-09-06 13:00","2019-09-06 09:00","2019-09-06 13:00","당일"]
[341,"경북","직할","현종산풍력평해#2 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","평해S/S 현종산풍력-평해#2T/L GCB, 6233 조작시험","2019-09-30 10:00","2019-09-30 14:00","2019-09-30 10:00","2019-09-30 14:00","당일"]
[342,"경북","직할","현종산풍력평해#1 T/L","'19년 경북직할 가공송전선로 위탁공사","154kV 현종산풍력-평해#1T/L No.14~87 정밀점검","2019-09-23 08:00","2019-09-27 18:00","2019-09-23 08:00","2019-09-27 18:00","연속"]
[343,"부산울산","동부산","구서명장#2 T/L","18-19 동부산전력지사 송전정비 협력회사 총액공사","불량압축인류크램프 정비","2019-09-30 08:00","2019-10-01 18:00","2019-09-30 08:00","2019-10-01 18:00","연속"]
[344,"부산울산","동부산","수영정보#1 T/L","수영E/C 170kV GIS 차단기 동작시험","1.수영E/C 170kV 637GIS 차단기 동작시험(수영-정보#1T/L) 2.정보E/C 170kV 627GIS 차단기 동작시험","2019-09-26 09:30","2019-09-26 14:00","2019-09-26 09:30","2019-09-26 14:00","당일"]
[345,"부산울산","동부산","수영정보#2 T/L","수영E/C 170kV 657GIS 하자점검","1.수영E/C 170kV 657GIS 하자점검(수영-정보#2T/L) 2.정보E/C 170kV 637GIS 하자점검","2019-09-25 09:30","2019-09-25 17:00","2019-09-25 09:30","2019-09-25 17:00","당일"]
[346,"부산울산","동부산","신양산좌동#2 T/L","154kV 시랑S/S 건설공사","154kV 시랑S/S 계통병입 및 최초가압","2019-09-16 10:00","2019-09-26 18:00","2019-09-16 10:00","2019-09-26 18:00","연속"]
[347,"부산울산","북부산","한림정삼계#1 T/L","2019년 북부산전력지사 가공순시점검 위탁공사","154kV 삼계-어방#2T/L 송전선로 정밀점검(1~51호) 작업자 안전이격거리확보","2019-09-29 09:00","2019-09-29 17:00","2019-09-29 09:00","2019-09-29 17:00","당일"]
[348,"부산울산","북부산","삼계어방#1 T/L","2019년 북부산전력지사 가공순시점검 위탁공사","154kV 삼계-어방#2T/L 송전선로 정밀점검(1~51호) 작업자 안전이격거리확보","2019-09-28 09:00","2019-09-28 18:00","취소","취소","당일"]
[349,"부산울산","북부산","삼계어방#1 T/L","2019년 북부산 154kV GIS 정밀점검 공사","삼계E/C 154kV 삼계-어방#1T/L GIS 정밀점검","2019-09-21 09:00","2019-09-22 18:00","2019-09-21 09:00","2019-09-22 18:00","연속"]
[350,"부산울산","북부산","삼계S/S 154kV #60 BUS","2019년 북부산 154kV GIS 정밀점검 공사","삼계E/C 154kV 삼계-어방#1T/L GIS 정밀점검(시험가압 1H)","2019-09-22 17:00","2019-09-22 18:00","2019-09-22 17:00","2019-09-22 18:00","당일"]
[351,"부산울산","북부산","삼계어방#2 T/L","2019년 북부산 154kV GIS 정밀점검 공사","삼계E/C 154kV 삼계-어방#2T/L GIS 정밀점검","2019-09-28 09:00","2019-09-29 18:00","2019-09-28 09:00","2019-09-29 18:00","연속"]
[352,"부산울산","북부산","삼계S/S 154kV #60 BUS","2019년 북부산 154kV GIS 정밀점검 공사","삼계E/C 154kV 삼계-어방#2T/L GIS 정밀점검(시험가압 1H)","2019-09-29 17:00","2019-09-29 18:00","2019-09-29 17:00","2019-09-29 18:00","당일"]
[353,"부산울산","북부산","한림정삼계#2 T/L","2019년 북부산전력지사 가공순시점검 위탁공사","154kV 삼계-어방#1T/L 송전선로 정밀점검(1~51호) 작업자 안전이격거리확보","2019-09-21 09:00","2019-09-21 18:00","2019-09-21 09:00","2019-09-21 18:00","당일"]
[354,"부산울산","북부산","삼계어방#2 T/L","2019년 북부산전력지사 가공순시점검 위탁공사","154kV 삼계-어방#1T/L 송전선로 정밀점검(1~51호) 작업자 안전이격거리확보","2019-09-22 09:00","2019-09-22 17:00","취소","취소","당일"]
[355,"부산울산","북부산","양산물금 T/L","154kV 양산S/S 취약설비 현대화공사","○ 양산-물금T/L 앙산 SA 변전소 수용 ○ 양산-물금T/L 가공송전 인입선 설치 ○ 양산-물금T/L 사용전 검사","2019-09-14 10:00","2019-09-20 18:00","2019-09-14 10:00","2019-09-20 18:00","연속"]
[356,"부산울산","북부산","양산산막#2 T/L","154kV 양산S/S 취약설비 현대화공사","○ 양산-산막#2T/L 앙산 SA 변전소 수용(시험가압 24H) ○ 양산-산막#2T/L 지중케이블 접속작업 ○ 양산-산막#2T/L 사용전 검사","2019-09-14 10:00","2019-10-08 18:00","2019-09-14 10:00","2019-10-08 18:00","연속"]
[357,"부산울산","서부산","서부산엄궁#1 T/L","서부산E/C 서부산-엄궁T/L 개폐타임 측정","서부산E/C 서부산-엄궁T/L 개폐타임 측정","2019-09-23 10:00","2019-09-23 18:00","2019-09-23 10:00","2019-09-23 18:00","당일"]
[358,"부산울산","울산","방어진영남TP#1 T/L","송전선로 항공장애 표시등 및 주간표지 설치공사","항공도장 : 9~15호(6기)","2019-09-23 09:00","2019-09-27 18:00","2019-09-23 09:00","2019-09-27 18:00","연속"]
[359,"부산울산","울산","방어진영남TP#2 T/L","송전선로 항공장애 표시등 및 주간표지 설치공사","항공도장 : 9~15호(6기)","2019-09-28 09:00","2019-10-02 18:00","2019-09-28 09:00","2019-10-02 18:00","연속"]
[360,"부산울산","울산","신울산명례#2 T/L","18~19년 변전협력 총액공사","- 신울산S/S 154kV 신울산-명례#2T/L 6Q7 GIS보통점검","2019-09-26 09:00","2019-09-26 18:00","2019-09-26 09:00","2019-09-26 18:00","당일"]
[361,"부산울산","울산","신울산S/S 154kV #68 BUS","18~19년 변전협력 총액공사","- 신울산S/S 154kV 6302DS 조작함 교체 및 DS링크축 조정 - 신울산S/S 154kV 6300GCB 차단기 동작시험","2019-09-25 09:00","2019-09-25 18:00","2019-09-25 09:00","2019-09-25 18:00","당일"]
[362,"부산울산","울산","신울산두왕#1 T/L","18~19년 변전협력 총액공사","- 154kV 신울산-두왕#1T/L 6K1 #1DS 단로기 조작박스 교체","2019-09-24 09:00","2019-09-24 18:00","2019-09-24 09:00","2019-09-24 18:00","당일"]
[363,"부산울산","울산","신울산S/S 154kV #62 BUS","18~19년 변전협력 총액공사","- 154kV 신울산-두왕#1T/L 6K1 #1DS 단로기 조작박스 교체","2019-09-24 09:00","2019-09-24 18:00","2019-09-24 09:00","2019-09-24 18:00","당일"]
[364,"부산울산","울산","신울산S/S 154kV #63-#68 BUS TIE CB","18~19년 변전협력 총액공사","- 신울산S/S 154kV 6302DS 조작함 교체 및 DS링크축 조정 - 신울산S/S 154kV 6300GCB 차단기 동작시험","2019-09-25 09:00","2019-09-25 18:00","2019-09-25 09:00","2019-09-25 18:00","당일"]
[365,"부산울산","울산","신울산언양#2 T/L","154kV 신울산-언양#2T/L 장기사용애자 시료발취","ㅇ 장기사용애자 시료발취 : No.1, 2","2019-09-30 08:00","2019-09-30 18:00","2019-09-30 08:00","2019-09-30 18:00","당일"]
[366,"부산울산","울산","옥동외동#1 T/L","154kV 외동-옥동#1T/L 취약철탑 암교체 및 항공장애표시구 설치","ㅁ 취약철탑 암교체 : No.3, 10, 16(3기) ㅁ 송전선로용 피뢰기 설치 : No.8~10(3기) ㅁ 항공장애표시구 설치 : No.12~13 [감사원 설비관리 실태점검 감사 지적사항 조치]","2019-09-27 08:00","2019-09-29 18:00","2019-09-27 08:00","2019-09-29 18:00","매일"]
[367,"부산울산","울산","옥동외동#2 T/L","154kV 외동-옥동#2T/L 취약철탑 암교체 및 항공장애표시구 설치","ㅁ 취약철탑 암교체 : No.3, 10, 16(3기) ㅁ 송전선로용 피뢰기 설치 : No.8~10(3기) ㅁ 항공장애표시구 설치 : No.11~12 [감사원 설비관리 실태점검 감사 지적사항 조치]","2019-09-27 08:00","2019-09-29 18:00","2019-09-27 08:00","2019-09-29 18:00","매일"]
[368,"부산울산","울산","온산처용#1 T/L","18~19년 변전협력 총액공사","- 온산S/S 154kV 온산-처용#1T/L 677GIS 보통점검 - 처용S/S 154kV 온산-처용#1T/L 687GIS 보통점검","2019-09-30 09:00","2019-09-30 18:00","2019-09-30 09:00","2019-09-30 18:00","당일"]
[369,"부산울산","울산","용연처용#1 T/L","154kV 용연-처용#1T/L 항공장애표시구 설치공사","ㅇ 항공장애표시구 설치 : No.12~16, 18~19 [감사원 설비관리 실태점검 감사 지적사항 조치]","2019-09-25 08:00","2019-09-26 18:00","2019-09-25 08:00","2019-09-26 18:00","매일"]
[370,"부산울산","울산","용연울산TP#1 T/L","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산화력S/Y 154kV #1/2GT 6533GIS 대체관련 #1BUS 시험가압선로 24H","2019-09-18 18:00","2019-09-19 18:00","2019-09-18 18:00","2019-09-19 18:00","연속"]
[371,"부산울산","울산","용연울산TP#1 T/L","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산T/P 154kV #1,2 G/T GIS(6533) 대체설비 철거 후 #2BUS 시험가압 선로(1H)","2019-09-09 17:00","2019-09-09 18:00","2019-09-09 17:00","2019-09-09 18:00","당일"]
[372,"부산울산","울산","울산T/P 154kV #66 BUS","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산T/P 154kV #1,2 G/T GIS(6533) 대체설비 상부모선, #2DS철거","2019-09-09 09:00","2019-09-09 18:00","2019-09-09 09:00","2019-09-09 18:00","당일"]
[373,"부산울산","울산","울산T/P 154kV #1,2 G/T CB","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산T/P 154kV #1,2 G/T GIS(6533) 대체설비","2019-09-09 09:00","2019-09-24 18:00","2019-09-09 09:00","2019-09-24 18:00","연속"]
[374,"부산울산","울산","울산T/P 154kV #65 BUS","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산T/P 154kV S/T #1GEN용 GIS(6433) 대체설비 상부모선, #2DS철거","2019-09-25 09:00","2019-09-26 18:00","2019-09-25 09:00","2019-09-26 18:00","연속"]
[375,"부산울산","울산","울산T/P 154kV S/T CB","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산T/P 154kV S/T #1GEN용 GIS(6433) 대체설비","2019-09-25 09:00","2019-10-12 18:00","2019-09-25 09:00","2019-10-12 18:00","연속"]
[376,"부산울산","울산","울산T/P 154kV #61 BUS","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산T/P 154kV #1,2 G/T GIS(6533) 대체설비 #BUS철거 및 #1DS, CB설치","2019-09-16 09:00","2019-09-19 18:00","2019-09-16 09:00","2019-09-19 18:00","연속"]
[377,"부산울산","울산","용연울산TP#1 T/L","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산화력 154KV #1/2GT용 6533GIS 신규#2BUS, CB, 상부모선 시험가압선로 24H","2019-09-23 17:00","2019-09-24 18:00","2019-09-23 17:00","2019-09-24 18:00","연속"]
[378,"부산울산","울산","울산T/P 154kV #61 BUS","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산화력 154KV #1/2GT용 6533GIS 신규#1DS 투입 후 시험가압1H","2019-09-24 17:00","2019-09-24 18:00","2019-09-24 17:00","2019-09-24 18:00","당일"]
[379,"부산울산","울산","울산울산TP#1 T/L","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산화력 154KV #1/2GT용 6533GIS 신규#2BUS 시험가압선로1H","2019-09-26 17:00","2019-09-26 18:00","2019-09-26 17:00","2019-09-26 18:00","당일"]
[380,"부산울산","울산","울산T/P 154kV #60 BUS","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산T/P 154kV #1,2 G/T GIS(6533) 대체설비 #1DS, CB철거 및 설치","2019-09-30 08:00","2019-10-04 18:00","2019-09-30 08:00","2019-10-04 18:00","연속"]
[381,"부산울산","울산","용연울산TP#1 T/L","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산T/P 154kV #1,2 G/T GIS(6533) 대체설비 #1BUS 시험가압선로 1H","2019-09-11 17:00","2019-09-11 18:00","2019-09-11 17:00","2019-09-11 18:00","당일"]
[382,"부산울산","울산","울산T/P 154kV #61 BUS","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산T/P 154kV #1,2 G/T GIS(6533) 대체설비 #1DS, CB철거","2019-09-10 09:00","2019-09-11 18:00","2019-09-10 09:00","2019-09-11 18:00","연속"]
[383,"부산울산","울산","울산T/P 154kV #66 BUS","19년 울산전력지사 170kV 장기사용GIS 대체공사","- 울산화력 154KV #1/2GT용 6533GIS #2BUS철거 및 신규#2BUS, CB, 상부모선 설치","2019-09-20 09:00","2019-09-24 18:00","2019-09-20 09:00","2019-09-24 18:00","연속"]
[384,"부산울산","울산","효문방어진 T/L","18~19년 변전협력 총액공사","- 효문S/S 154kV 효문-방어진T/L 617GIS 차단기 동작시험","2019-09-21 09:00","2019-09-21 18:00","2019-09-21 09:00","2019-09-21 18:00","당일"]
[385,"부산울산","직할","개금범천#2 T/L","2019년 직할 변전협력회사 총액공사","- 개금E/C 개금-범천 #2T/L GIS 차단기 동작시험 - 범천E/C 개금-범천 #2T/L GIS 차단기 동작시험","2019-09-24 14:00","2019-09-24 18:00","2019-09-24 14:00","2019-09-24 18:00","당일"]
[386,"부산울산","직할","개금범천#1 T/L","2019년 직할 변전협력회사 총액공사","- 개금E/C 개금-범천 #1T/L GIS 차단기 동작시험 - 범천E/C 개금-범천 #1T/L GIS 차단기 동작시험","2019-09-24 10:00","2019-09-24 14:00","2019-09-24 10:00","2019-09-24 14:00","당일"]
[387,"부산울산","직할","범일S/S 154kV #1 BUS TIE CB","2019년 직할 변전협력회사 총액공사","- B/P PNL 대체","2019-09-02 10:00","2019-09-05 18:00","2019-09-02 10:00","2019-09-05 18:00","연속"]
[388,"부산울산","직할","양정범천 T/L","2019년 직할 변전협력회사 총액공사","- 범천S/S 양정-범천T/L GIS 차단기 동작시험","2019-09-26 10:00","2019-09-26 14:00","2019-09-26 10:00","2019-09-26 14:00","당일"]
[389,"경남","직할","신김해삼정#2 T/L","2018-2019 경남 직할 송전협력회사 총액공사","154kV 신김해-삼정#2T/L 항공장애표시구 설치(9-10,10-11호 가공지선 구간)","2019-09-25 07:00","2019-09-25 12:00","2019-09-25 07:00","2019-09-25 12:00","당일"]
[390,"경남","직할","신김해삼정#1 T/L","2018-2019 경남 직할 송전협력회사 총액공사","154kV 신김해-삼정#1T/L 항공장애표시구 설치(9-10,10-11호 OPGW 구간)","2019-09-25 12:00","2019-09-25 18:00","2019-09-25 12:00","2019-09-25 18:00","당일"]
[391,"경남","직할","신김해장유#2 T/L","신김해S/S 신김해-장유 #2T/L CB, LA 보통점검","신김해S/S 신김해-장유 #2T/L CB,LA 보통점검 병행: 장유S/S 신김해-장유 #2T/L CB 조작시험 점검","2019-09-24 09:30","2019-09-24 18:00","2019-09-24 09:30","2019-09-24 18:00","당일"]
[392,"경남","직할","신김해진영#1 T/L","송전선로 OPGW 항공장애표시구 설치공사","154KV 신김해-진영#1T/L 29-31호 9개 설치","2019-09-07 09:00","2019-09-07 18:00","2019-09-07 09:00","2019-09-07 18:00","당일"]
[393,"경남","직할","신김해장유#1 T/L","신김해S/S 신김해-장유 #1T/L CB, LA 보통점검","신김해S/S 신김해-장유 #1T/L CB,LA 보통점검 병행: 장유S/S 신김해-장유 #1T/L CB 조작시험 점검","2019-09-23 08:00","2019-09-23 17:30","2019-09-23 08:00","2019-09-23 17:30","당일"]
[394,"경남","직할","신김해주촌#1 T/L","2018-2019 경남 직할 송전협력회사 총액공사","154kV 신김해-주촌#1T/L 항공장애표시구 설치(22-23,30-31호 가공지선 구간)","2019-09-24 07:00","2019-09-24 15:00","2019-09-24 07:00","2019-09-24 15:00","당일"]
[395,"경남","직할","완암안민#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-09-14 07:00","2019-09-16 18:00","2019-09-28 07:00","2019-09-30 18:00","연속"]
[396,"경남","직할","창원완암#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-09-17 07:00","2019-09-18 18:00","취소","취소","연속"]
[397,"경남","직할","완암안민#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-09-14 07:00","2019-09-18 18:00","2019-09-28 07:00","2019-09-30 18:00","연속"]
[398,"경남","직할","창원완암#2 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-09-11 07:00","2019-09-13 18:00","2019-09-12 07:00","2019-09-14 18:00","연속"]
[399,"경남","직할","창원완암#1 T/L","154kV 창원, 월림인출변경T/L 건설공사","345kV 창원S/S 건설관련 계통 정비","2019-09-11 07:00","2019-09-16 18:00","2019-09-12 07:00","2019-09-14 18:00","연속"]
[400,"경남","직할","수출월림#1 T/L","19년도 직할 170kV GIS 정밀점검","월림S/S 수출-월림#1T/L CB 정밀점검 시험가압선로: 수출-월림#1T/L","2019-09-23 08:00","2019-09-24 18:00","2019-09-23 08:00","2019-09-24 18:00","연속"]
[401,"경남","진주","개양S/S 154kV #65 BUS","개양S/S 154kV 하동-개양#1T/L CB(637) 정밀점검 시험가압","개양S/S 154kV 하동-개양#1T/L CB(637) 정밀점검 시험가압","2019-09-22 17:00","2019-09-22 17:30","2019-09-22 17:00","2019-09-22 17:30","당일"]
[402,"경남","진주","하동개양#1 T/L","개양S/S 154kV 하동-개양#1T/L CB(637) 정밀점검","개양S/S 154kV 하동-개양#1T/L CB(637) 정밀점검","2019-09-21 09:00","2019-09-22 18:00","2019-09-21 09:00","2019-09-22 18:00","연속"]
[403,"경남","진주","사천개양#1 T/L","개양S/S 154kV BUS-TIE CB(6100) 정밀점검 후 시험가압","개양S/S 154kV BUS-TIE CB(6100) 정밀점검 후 시험가압","2019-09-19 17:00","2019-09-19 17:30","2019-09-24 17:00","2019-09-24 17:30","당일"]
[404,"경남","진주","사천개양#2 T/L","개양S/S 154kV 하동-개양#1T/L CB(637) 정밀점검 시험가압","개양S/S 154kV 하동-개양#1T/L CB(637) 정밀점검 시험가압","2019-09-22 17:00","2019-09-22 17:30","2019-09-22 17:00","2019-09-22 17:30","당일"]
[405,"경남","진주","개양S/S 154kV #60-#65 BUS TIE CB","개양S/S 154kV BUS-TIE CB(6100) 정밀점검","개양S/S 154kV BUS-TIE CB(6100) 정밀점검","2019-09-18 09:00","2019-09-19 18:00","2019-09-23 09:00","2019-09-24 18:00","연속"]
[406,"경남","진주","개양S/S 154kV #60 BUS","개양S/S 154kV BUS-TIE CB(6100) 정밀점검 후 시험가압","개양S/S 154kV BUS-TIE CB(6100) 정밀점검 후 시험가압","2019-09-19 17:00","2019-09-19 17:30","2019-09-24 17:00","2019-09-24 17:30","당일"]
[407,"경남","진주","삼천포사천#1 T/L","사천S/S 154kV 사천-개양#1T/L CB(657) 정밀점검 시험가압","사천S/S 154kV 사천-개양#1T/L CB(657) 정밀점검 시험가압","2019-09-27 17:00","2019-09-27 17:30","2019-09-27 17:00","2019-09-27 17:30","당일"]
[408,"경남","진주","사천개양#1 T/L","사천S/S 154kV 사천-개양#1T/L CB(657) 정밀점검","사천S/S 154kV 사천-개양#1T/L CB(657) 정밀점검","2019-09-26 09:00","2019-09-27 18:00","2019-09-26 09:00","2019-09-27 18:00","연속"]
[409,"경남","진주","의령함양 T/L","154kV 의령-함양T/L 애자련보강공사","154kV 의령-함양T/L 애자련보강, 이도조정, 전선교체","2019-09-28 07:30","2019-09-29 18:00","2019-09-28 07:30","2019-09-29 18:00","연속"]
[410,"경남","진주","하동S/S 154kV #60-#65 BUS TIE CB","하동S/S 154kV #1BUS-TIE CB(6100) 조작시험","하동S/S 154kV #1BUS-TIE CB(6100) 조작시험","2019-09-20 14:00","2019-09-20 17:00","2019-09-20 14:00","2019-09-20 17:00","당일"]
[411,"경남","진주","합천S/S 154kV #60-#65 BUS TIE CB","합천S/S 154kV #1 BUS-TIE CB(6100) 조작시험","합천S/S 154kV #1 BUS-TIE CB(6100) 조작시험","2019-09-30 10:00","2019-09-30 12:00","2019-09-30 10:00","2019-09-30 12:00","당일"]
[412,"경남","통영","신고성거제#1 T/L","154kV 신고성-거제#1T/L 송전선로 보호 PNL 대체공사","거제S/S,신고성S/S측 신고성-거제#1T/L PNL 대체공사","2019-09-21 09:30","2019-09-22 18:00","2019-09-21 09:30","2019-09-22 18:00","연속"]
[413,"경남","통영","신고성거제#2 T/L","154kV 신고성-거제#2T/L 정밀점검","154kV 신고성-거제#2T/L 정밀점검","2019-09-28 09:00","2019-09-29 18:00","2019-09-28 09:00","2019-09-29 18:00","매일"]
[414,"경남","통영","진동S/S 154kV #60 BUS","진동S/S 170kV 모선보강공사","170kV GIS 4CCT 증설공사 - 170kV B/T GIS 1CCT - 170kV B/S GIS 2CCT - 170kV PT&ES GIS 1CCT","2019-09-30 09:00","2019-10-10 09:00","2019-09-30 09:00","2019-10-10 09:00","연속"]
[415,"경남","함안","창녕초동#2 T/L","154kV 창녕-초동#2 T/L 49호 과열개소 정비","154kV 창녕-초동#2 T/L 49호 하단선 부하측 과열개소 정비","2019-09-20 08:30","2019-09-20 18:00","2019-09-20 08:30","2019-09-20 18:00","당일"]
[416,"경남","함안","신마산칠서#1 T/L","154kV 칠서분기T/L OPGW 증설공사","칠서S/S ICT실~칠서분기T/L 34호간 OPGW 5.321Km 증설","2019-09-30 09:00","2019-10-06 18:00","취소","취소","연속"]