{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["종합","765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":13,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"종합","index":0,"n_rows":37,"n_cols":33,"rows_kept":37,"cut":false,"hidden":true,"merged":[[0,0,0,15],[7,14,7,15],[7,1,7,2],[8,1,8,2],[7,9,7,13],[7,3,7,6],[8,3,8,6],[14,14,14,15],[10,1,10,2],[11,1,11,2],[14,9,14,13],[9,1,9,2],[14,2,14,6],[11,3,11,6],[10,3,10,6],[9,3,9,6]]}
[{"$f":"\"'19년 \"&R15&\"월 휴전심의 결과\"","v":"'19년 11월 휴전심의 결과"}]
[]
[]
[]
[]
[]
["◎ 전체 심의결과"]
["전   압","신 청",null,"채 택",null,null,null,"일정\n조정","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)"]
["765kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B9-I9","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J9,L9,N9)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O9/B9)","v":{"$error":"#REF!"}}]
["345kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B10-I10","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J10,L10,N10)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O10/B10)","v":{"$error":"#REF!"}}]
["154kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B11-I11","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J11,L11,N11)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O11/B11)","v":{"$error":"#REF!"}}]
["계",{"$f":"SUM(B9:B11)","v":{"$error":"#REF!"}},null,{"$f":"SUM(D9:D11)","v":{"$error":"#REF!"}},null,null,null,{"$f":"SUM(H9:H11)","v":{"$error":"#REF!"}},{"$f":"SUM(J12,L12,N12)","v":{"$error":"#REF!"}},{"$f":"SUM(J9:J11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(L9:L11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(N9:N11)","v":{"$error":"#REF!"}},{"$f":"SUM(O9:O11)","v":{"$error":"#REF!"}},{"$f":"(O12/B12)","v":{"$error":"#REF!"}}]
[]
["◎ 본부별 심의결과",{"$nulls":16},"월"]
["사업소","신 청","(765/345/154)",{"$nulls":4},"채 택","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)",null,null,11]
["서   울",{"$f":"SUM(C16:G16)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},{"$f":"B16-I16","v":{"$error":"#REF!"}},{"$f":"SUM(J16,L16,N16)","v":{"$error":"#REF!"}},{"$f":"SUM(S16:U16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W16:Y16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA16:AC16)","v":{"$error":"#REF!"}},{"$f":"SUM(AE16:AG16)","v":{"$error":"#REF!"}},{"$f":"(O16/B16)","v":{"$error":"#REF!"}},null,"서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}}]
["남서울",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$f":"SUM(J17,L17,N17)","v":{"$error":"#REF!"}},{"$f":"SUM(S17:U17)","v":{"$error":"#REF!"}},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"남서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}}]
["인   천",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"인천",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}}]
["경기북부",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기북부",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}}]
["경   기",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}}]
["강   원",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"강원",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}}]
["충   북",{"$f":"SUM(C22:G22)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"충북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}}]
["대전충남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"대전충남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}}]
["전   북",{"$f":"SUM(C24:G24)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"전북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}}]
["광주전남",{"$f":"SUM(C25:G25)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"광주전남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}}]
["대구",{"$f":"SUM(C26:G26)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},{"$f":"B26-I26","v":{"$error":"#REF!"}},{"$f":"SUM(J26,L26,N26)","v":{"$error":"#REF!"}},{"$f":"SUM(S26:U26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W26:Y26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA26:AC26)","v":{"$error":"#REF!"}},{"$f":"SUM(AE26:AG26)","v":{"$error":"#REF!"}},{"$f":"(O26/B26)","v":{"$error":"#REF!"}},null,"대구",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}}]
["경북",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}}]
["부산울산",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"부산울산",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}}]
["경   남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$f":"SUM(W29:Y29)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA29:AC29)","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},null,"경남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}}]
["제   주",{"$f":"SUM(C30:G30)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$f":"(O30/B30)","v":{"$error":"#REF!"}},null,"제주",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}}]
[]
[" 붙임 :  1. 집중심의내역 1부"]
[" 붙임 :  전압별 검토서 1부. 끝."]
[]
[null,{"$f":"SUM(B16:B30)","v":{"$error":"#REF!"}},{"$f":"SUM(C16:C30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(E16:E30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(G16:G30)","v":{"$error":"#REF!"}},{"$f":"SUM(H16:H30)","v":{"$error":"#REF!"}},{"$f":"SUM(I16:I30)","v":{"$error":"#REF!"}},{"$f":"SUM(J16:J30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(L16:L30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(N16:N30)","v":{"$error":"#REF!"}},{"$f":"SUM(O16:O30)","v":{"$error":"#REF!"}}]
[{"$f":"COUNTIF(B36:N36,\"NO\")","v":0},{"$f":"IF(B35=B12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(C35=B9,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(E35=B10,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(G35=B11,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(H35=D12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(I35=I12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(J35=J12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(L35=L12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(N35=N12,\"\",\"NO\")","v":{"$error":"#REF!"}}]
[{"$f":"IF(A36>=1,\"틀린곳\",\"\")","v":""},{"$f":"IF(B36=\"NO\",\"총계\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C36=\"NO\",\"765\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(D36=\"NO\",\"총계\",\"\")","v":""},{"$f":"IF(E36=\"NO\",\"345\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(G36=\"NO\",\"154\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(H36=\"NO\",\"채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(I36=\"NO\",\"불채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(J36=\"NO\",\"병행\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(L36=\"NO\",\"취소\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(N36=\"NO\",\"연기\",\"\")","v":{"$error":"#REF!"}}]

{"sheet":"765송부","index":1,"n_rows":14,"n_cols":13,"rows_kept":14,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 11월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #4 M.Tr","신가평S/S #78BAY B/F반 교체공사","신가평S/S #78BAYB/F반 교체 : 신가평4MTr-신가평미금2","2019-11-08 09:00","2019-11-13 18:00","2019-11-08 09:00","2019-11-13 18:00","연속"]
[2,"경기북부","구리","신가평S/S #1 M.Tr","신가평S/S #1M.Tr 철공진해소 공사","신가평S/S #1M.Tr 철공진해소 공사","2019-11-15 09:00","2019-11-27 18:00","2019-11-15 09:00","2019-11-27 18:00","연속"]
[3,"경기","성남","신안성S/S 765kV #80 BUS","765kV GIS 정밀점검","765kV GIS 정밀점검","2019-11-25 09:00","2019-12-06 18:00","취소","취소","연속"]
[4,"강원","태백","신태백신한울#2 T/L","18-19년 태백전력지사 변전전문회사 총액공사","신태백변전소 765kV 신태백-신한울 #2T/L 8371CB 조작시험, 부싱 육안점검","2019-11-04 10:00","2019-11-04 18:00","2019-11-04 10:00","2019-11-04 18:00","당일"]
[5,"강원","태백","신태백신가평#2 T/L","18~19년 태백전력지사 변전정비회사 총액공사","800kV GIS 8671, 8600CB 조작시험","2019-11-06 10:00","2019-11-06 18:00","2019-11-06 10:00","2019-11-06 18:00","당일"]
[6,"강원","태백","신태백신한울#1 T/L","18-19년 태백전력지사 변전전문회사 총액공사","신태백변전소 765kV 신태백-신한울 #1T/L 8471CB 조작시험, 부싱 육안점검","2019-11-05 10:00","2019-11-05 18:00","2019-11-05 10:00","2019-11-05 18:00","당일"]
[7,"대전충남","서산","신서산신중부#2 T/L","보호반 성능개선","보호반 성능개선","2019-11-30 09:00","2019-11-30 18:00","2019-11-30 09:00","2019-11-30 18:00","당일"]
[8,"대전충남","서산","신서산S/S #3 M.Tr","19년도 서산P/O 노후배전반 교체공사","- 신서산S/S 345kV 76BAY BF반 대체공사 - 신서산S/S 735kV #3M.Tr 3차측 PT대체공사","2019-11-25 09:00","2019-11-29 18:00","취소","취소","연속"]
[9,"부산울산","동부산","신고리N/P #3 Tie-Tr","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 362kV 7500,7572GIS 구조개선관련 시험가압(#3M.Tr)","2019-11-29 18:00","2019-11-30 18:00","2019-11-29 18:00","2019-11-30 18:00","연속"]
[10,"부산울산","동부산","북경남신고리NP#1 T/L","2019년 신고리E/C 765kV GIS 보통점검 공사","8271 GIS 보통점검","2019-11-11 09:30","2019-11-15 18:00","2019-11-11 09:30","2019-11-15 18:00","연속"]

{"sheet":"345송부","index":2,"n_rows":312,"n_cols":13,"rows_kept":312,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 11월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #3 M.Tr A","19년 성동P/O 관내 154kV 차단기 조작시험","154kV GIS 조작시험 (#3M.Tr 2차 차단기 개폐타임 측정)","2019-11-15 10:00","2019-11-15 14:00","2019-11-15 10:00","2019-11-15 14:00","당일"]
[2,"서울","중부","중부서울CC#2 T/L","19년 중부전력지사 변전협력회사 총액공사","ㅇ345kV 서울CC#2 T/L 초기점검","2019-11-20 09:00","2019-11-20 18:00","2019-11-20 09:00","2019-11-20 18:00","당일"]
[3,"서울","중부","중부S/S #2 M.Tr A","19년 중부전력지사 변전협력회사 총액공사","ㅇ345kV #2M.Tr 1, 2차 GIS 보통점검","2019-11-14 10:00","2019-11-15 18:00","2019-11-14 10:00","2019-11-15 18:00","연속"]
[4,"서울","중부","중부S/S 345kV #75 BUS","2019년 중부S/S 345kV GIS 정밀점검공사","7452DS, 7409-8ES 정밀점검","2019-11-07 10:00","2019-11-08 18:00","2019-11-07 10:00","2019-11-08 18:00","연속"]
[5,"서울","중부","중부S/S 345kV #70 BUS","2019년 중부S/S 345kV GIS 정밀점검공사","7451DS, 7409-1ES 정밀점검","2019-11-11 10:00","2019-11-12 18:00","2019-11-11 10:00","2019-11-12 18:00","연속"]
[6,"서울","중부","중부서울CC#1 T/L","19년 중부전력지사 변전협력회사 총액공사","ㅇ345kV 서울CC#1 T/L 초기점검","2019-11-18 09:00","2019-11-19 18:00","2019-11-18 09:00","2019-11-19 18:00","연속"]
[7,"남서울","강남","신양재S/S #3 M.Tr 1차 CB (7300)","ES 보수작업","ES 보수작업(7300 CB 휴전, 7309-1 ES 보수)","2019-11-13 09:00","2019-11-13 14:00","취소","취소","당일"]
[8,"남서울","강남","신양재S/S #3 M.Tr 1차 CB (7300)","ES 보수작업","ES 보수작업(7372 CB 휴전, 7309-8 ES 보수)","2019-11-13 14:00","2019-11-13 18:00","취소","취소","당일"]
[9,"남서울","강남","신양재S/S #2 M.Tr 1차 CB (7272)","ES 보수작업","ES 보수작업 (7272 CB 휴전, 7209-8 ES 보수)","2019-11-12 09:00","2019-11-12 18:00","취소","취소","당일"]
[10,"남서울","강남","신양재S/S #1 M.Tr 1차 CB (7172)","ES 보수작업","ES 보수작업(7172 CB 휴전, 7109-8 ES 보수)","2019-11-11 14:00","2019-11-11 18:00","취소","취소","당일"]
[11,"남서울","강남","신양재S/S 신성남-신양재#1T/L CB (7171)","ES 보수작업","ES 보수작업(7171 CB 휴전, 7109-1 ES 보수)","2019-11-11 09:00","2019-11-11 14:00","취소","취소","당일"]
[12,"남서울","동서울","동서울S/S #4 M.Tr","동서울S/S 154kV 현대화 공사","○ 전력구 흙막이 작업(H-Beam Filing)","2019-11-05 08:30","2019-11-05 17:00","2019-11-04 08:30","2019-11-04 17:00","당일"]
[13,"남서울","동서울","동서울S/S 345kV #1 Sh.R","345kV GIS 보통점검","345kV GIS 보통점검","2019-11-07 09:30","2019-11-07 18:00","2019-11-07 09:30","2019-11-07 18:00","당일"]
[14,"남서울","동서울","동서울S/S #3 M.Tr","동서울S/S 154kV 현대화 공사","○ 전력구 흙막이 작업(H-Beam Filing)","2019-11-12 08:30","2019-11-12 17:00","2019-11-12 08:30","2019-11-12 17:00","당일"]
[15,"남서울","동서울","동서울S/S #2 M.Tr","동서울S/S 154kV 현대화 공사","○ T-BUS DS철거 및 인출Lead 직결","2019-11-18 08:30","2019-11-19 17:00","2019-11-18 08:30","2019-11-19 17:00","연속"]
[16,"남서울","동서울","동서울S/S #1 M.Tr","동서울S/S 154kV 현대화 공사","○ T-BUS DS철거 및 인출Lead 직결","2019-11-20 08:30","2019-11-21 17:00","2019-11-20 08:30","2019-11-21 17:00","연속"]
[17,"남서울","동서울","동서울S/S #70-#71 SEC CB","345kV GIS 보통점검","345kV GIS 보통점검","2019-11-04 09:00","2019-11-04 14:00","취소","취소","당일"]
[18,"남서울","동서울","동서울S/S #75-#76 SEC CB","345kV GIS 보통점검","345kV GIS 보통점검","2019-11-04 14:00","2019-11-04 18:00","취소","취소","당일"]
[19,"남서울","영등포","신광명S/S 345kV #75 BUS","신광명S/S 345kV CVT 보통점검","- CVT 보통점검","2019-11-06 13:00","2019-11-06 15:00","취소","취소","당일"]
[20,"남서울","영등포","신광명S/S 345kV #70 BUS","신광명S/S 345kV CVT 보통점검","- CVT 보통점검","2019-11-06 10:00","2019-11-06 12:00","취소","취소","당일"]
[21,"인천","부평","서인천C/C #2 Tie-Tr","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 6100 BUS TIE GIS 정밀점검 관련 무부하가압용","2019-11-09 13:00","2019-11-09 18:00","2019-11-09 13:00","2019-11-09 18:00","당일"]
[22,"인천","부평","서인천C/C #4 Tie-Tr","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 6200 BUS TIE GIS 정밀점검 관련 무부하가압용","2019-11-13 13:00","2019-11-13 18:00","2019-11-13 13:00","2019-11-13 18:00","당일"]
[23,"인천","시흥","신가좌신시흥#1 T/L","'18~19년 가공송전 정비회사 총액공사","345kV 신가좌-신시흥T/L No.68~70(345kV 신시흥-신광명T/L No.45~47) 항공장애표시 도장공사(4회선 병가구간)","2019-11-16 08:00","2019-11-16 13:00","2019-11-16 08:00","2019-11-16 13:00","당일"]
[24,"인천","시흥","신시흥신광명#1 T/L","'18~19년 가공송전 정비회사 총액공사","345kV 신가좌-신시흥T/L No.68~70(345kV 신시흥-신광명T/L No.45~47) 항공장애표시 도장공사(4회선 병가구간)","2019-11-16 08:00","2019-11-16 13:00","2019-11-16 08:00","2019-11-16 13:00","당일"]
[25,"인천","시흥","신가좌신시흥#2 T/L","'18~19년 가공송전 정비회사 총액공사","345kV 신가좌-신시흥T/L No.68~70(345kV 신시흥-신광명T/L No.45~47) 항공장애표시 도장공사(4회선 병가구간)","2019-11-16 13:00","2019-11-16 18:00","2019-11-16 13:00","2019-11-16 18:00","당일"]
[26,"인천","시흥","신시흥신광명#2 T/L","'18~19년 가공송전 정비회사 총액공사","345kV 신가좌-신시흥T/L No.68~70(345kV 신시흥-신광명T/L No.45~47) 항공장애표시 도장공사(4회선 병가구간)","2019-11-16 13:00","2019-11-16 18:00","2019-11-16 13:00","2019-11-16 18:00","당일"]
[27,"인천","시흥","신가좌신시흥#1 T/L","'18~19년 가공송전 정비회사 총액공사","345kV 신가좌-신시흥T/L No.68~70(345kV 신시흥-신광명T/L No.45~47) 항공장애표시 도장공사(4회선 병가구간)","2019-11-17 08:00","2019-11-17 13:00","2019-11-17 08:00","2019-11-17 13:00","당일"]
[28,"인천","시흥","신시흥신광명#1 T/L","'18~19년 가공송전 정비회사 총액공사","345kV 신가좌-신시흥T/L No.68~70(345kV 신시흥-신광명T/L No.45~47) 항공장애표시 도장공사(4회선 병가구간)","2019-11-17 08:00","2019-11-17 13:00","2019-11-17 08:00","2019-11-17 13:00","당일"]
[29,"인천","시흥","신가좌신시흥#2 T/L","'18~19년 가공송전 정비회사 총액공사","345kV 신가좌-신시흥T/L No.68~70(345kV 신시흥-신광명T/L No.45~47) 항공장애표시 도장공사(4회선 병가구간)","2019-11-17 13:00","2019-11-17 18:00","2019-11-17 13:00","2019-11-17 18:00","당일"]
[30,"인천","시흥","신시흥신광명#2 T/L","'18~19년 가공송전 정비회사 총액공사","345kV 신가좌-신시흥T/L No.68~70(345kV 신시흥-신광명T/L No.45~47) 항공장애표시 도장공사(4회선 병가구간)","2019-11-17 13:00","2019-11-17 18:00","2019-11-17 13:00","2019-11-17 18:00","당일"]
[31,"인천","시흥","영흥T/P 영흥TP연락#2T/L-#2G.Tr 1차 TIE CB(7200)","영흥T/P 영흥TP연락#2T/L-#2G.Tr1차TIE CB(7200)조작","영흥T/P 영흥TP연락#2T/L-#2G.Tr1차TIE CB(7200)조작","2019-11-27 10:00","2019-11-27 18:00","2019-11-27 10:00","2019-11-27 18:00","당일"]
[32,"인천","시흥","신시흥#2S/S 345kV 신시흥-신안산T/L-#5 M.Tr 1차 TIE CB(7300)","신시흥#2S/S 신시흥신안산T/L-#5M.Tr1차TIECB(7300)조작","신시흥#2S/S 신시흥신안산T/L-#5M.Tr1차TIECB(7300)조작","2019-11-26 14:00","2019-11-26 18:00","2019-11-26 14:00","2019-11-26 18:00","당일"]
[33,"인천","시흥","신시흥#2S/S 화성-신시흥T/L CB(7471)","신시흥#2S/S 화성-신시흥T/L CB(7471) 조작","신시흥#2S/S 화성-신시흥T/L CB(7471) 조작","2019-11-26 10:00","2019-11-26 14:00","2019-11-26 10:00","2019-11-26 14:00","당일"]
[34,"인천","시흥","신시흥#2S/S 신시흥-영흥TP#2T/L CB(7271)","신시흥#2S/S 신시흥-영흥TP#2T/L CB(7271) 조작","신시흥#2S/S 신시흥-영흥TP#2T/L CB(7271) 조작","2019-11-25 14:00","2019-11-25 18:00","2019-11-25 14:00","2019-11-25 18:00","당일"]
[35,"인천","시흥","신시흥#2S/S 신시흥-영흥TP#1T/L CB(7171)","신시흥#2S/S 신시흥-영흥TP#1T/L CB(7171) 조작","신시흥#2S/S 신시흥-영흥TP#1T/L CB(7171) 조작","2019-11-25 10:00","2019-11-25 14:00","2019-11-25 10:00","2019-11-25 14:00","당일"]
[36,"인천","시흥","신시흥#2S/S 서서울2-신시흥#2T/L CB(7671)","신시흥#2S/S 서서울2-신시흥#2T/L CB(7671) 조작","신시흥#2S/S 서서울2-신시흥#2T/L CB(7671) 조작","2019-11-22 14:00","2019-11-22 18:00","2019-11-22 14:00","2019-11-22 18:00","당일"]
[37,"인천","시흥","신시흥#2S/S 서서울2-신시흥#1T/L CB(7571)","신시흥#2S/S 서서울2-신시흥#1T/L CB(7571) 조작","신시흥#2S/S 서서울2-신시흥#1T/L CB(7571) 조작","2019-11-22 10:00","2019-11-22 14:00","2019-11-22 10:00","2019-11-22 14:00","당일"]
[38,"인천","시흥","신시흥#2S/S 신시흥-신안산T/L CB(7371)","신시흥#2S/S 345kV 신시흥-신안산T/L CB(7371) 조작","신시흥#2S/S 345kV 신시흥-신안산T/L CB(7371) 조작","2019-11-21 14:00","2019-11-21 18:00","2019-11-21 14:00","2019-11-21 18:00","당일"]
[39,"인천","시흥","신시흥#2S/S 서서울2-신시흥#2T/L-#4 M.Tr 1차 TIE CB(7600)","신시흥#2S/S 서서울2신시흥#2T/L-#4 M.Tr 1차(7600)조작","신시흥#2S/S 서서울2신시흥#2T/L-#4 M.Tr 1차(7600)조작","2019-11-21 10:00","2019-11-21 14:00","2019-11-21 10:00","2019-11-21 14:00","당일"]
[40,"인천","김포","신김포서인천CC T/L","345kV 신김포-서인천CCT/L 자기애관 교체공사","○ 대상설비 : 345kV 아라뱃길C/H EBA 6상 ○ 공사내용 : 자기애관 대체 폴리머애관 교체공사","2019-11-18 09:00","2019-11-29 18:00","2019-11-18 09:00","2019-11-29 18:00","연속"]
[41,"인천","시흥","신시흥#2S/S 서서울2-신시흥#1T/L TIE CB(7500)","신시흥#2S/S 서서울2-신시흥#1T/L TIE CB(7500) 조작","신시흥#2S/S 서서울2-신시흥#1T/L TIE CB(7500) 조작","2019-11-15 14:00","2019-11-15 18:00","2019-11-15 14:00","2019-11-15 18:00","당일"]
[42,"인천","시흥","신시흥#2S/S 신시흥-영흥TP#2T/L TIE CB(7200)","신시흥#2S/S 신시흥-영흥TP#2T/L TIE CB(7200) 조작","신시흥#2S/S 신시흥-영흥TP#2T/L TIE CB(7200) 조작","2019-11-15 10:00","2019-11-15 14:00","2019-11-15 10:00","2019-11-15 14:00","당일"]
[43,"인천","시흥","신시흥#1S/S 신가좌-신시흥#2T/L CB(7C71)","신시흥#1S/S 신가좌-신시흥#2T/L CB(7C71) 조작","신시흥#1S/S 신가좌-신시흥#2T/L CB(7C71) 조작","2019-11-14 14:00","2019-11-14 18:00","2019-11-14 14:00","2019-11-14 18:00","당일"]
[44,"인천","시흥","신시흥#1S/S 신가좌-신시흥#1T/L CB(7B71)","신시흥#1S/S 신가좌-신시흥#1T/L CB(7B71) 조작","신시흥#1S/S 신가좌-신시흥#1T/L CB(7B71) 조작","2019-11-14 10:00","2019-11-14 14:00","2019-11-14 10:00","2019-11-14 14:00","당일"]
[45,"인천","시흥","신시흥#1S/S 신시흥-영흥TP#4T/L CB(7871)","신시흥#1S/S 신시흥-영흥TP#4T/L CB(7871) 조작","신시흥#1S/S 신시흥-영흥TP#4T/L CB(7871) 조작","2019-11-13 14:00","2019-11-13 18:00","2019-11-13 14:00","2019-11-13 18:00","당일"]
[46,"인천","시흥","신시흥#1S/S 신가좌-신시흥#1T/L-1M.Tr 1차 TIE CB(7B00)","신시흥#1S/S 신가좌-신시흥#1T/L-1M.Tr 1차(7B00) 조작","신시흥#1S/S 신가좌-신시흥#1T/L-1M.Tr 1차(7B00) 조작","2019-11-13 10:00","2019-11-13 14:00","2019-11-13 10:00","2019-11-13 14:00","당일"]
[47,"인천","시흥","신시흥#1S/S 신시흥-신광명#2T/L-2M.Tr 1차 TIE CB(7A00)","신시흥#1S/S 신시흥-신광명#2T/L-2M.Tr 1차(7A00) 조작","신시흥#1S/S 신시흥-신광명#2T/L-2M.Tr 1차(7A00) 조작","2019-11-12 14:00","2019-11-12 18:00","2019-11-12 14:00","2019-11-12 18:00","당일"]
[48,"인천","부평","신경서인천CC#1 T/L","신경서S/S 7291ES 전자변 교체공사","- 신경서S/S 7291ES 전자변(A,B,C상) 교체 - 현장,원방 조작시험","2019-11-12 10:00","2019-11-12 18:00","2019-11-12 10:00","2019-11-12 18:00","당일"]
[49,"인천","시흥","신시흥#1S/S 신시흥-신광명#1T/L CB(7971)","신시흥#1S/S 신시흥-신광명#1T/L CB(7971) 조작시험","신시흥#1S/S 신시흥-신광명#1T/L CB(7971) 조작시험","2019-11-12 10:00","2019-11-12 14:00","2019-11-12 10:00","2019-11-12 14:00","당일"]
[50,"인천","직할","서인천CC신부평#3 T/L","유호제 345kV 송전선로 보호배전반 성능개선","○ 인출DS 감시접점 Keep Ry 회로변경","2019-11-12 10:00","2019-11-12 18:00","2019-11-12 10:00","2019-11-12 18:00","당일"]
[51,"인천","시흥","신시흥#1S/S 신시흥-신광명#1T/L TIE CB(7900)","신시흥#1S/S 신시흥-신광명#1T/L TIE CB(7900) 조작","신시흥#1S/S 신시흥-신광명#1T/L TIE CB(7900) 조작","2019-11-11 14:00","2019-11-11 18:00","2019-11-11 14:00","2019-11-11 18:00","당일"]
[52,"인천","직할","신부평S/S 서인천CC-신부평#2T/L CB(7271)","신부평S/S 362kV 서인천신부평#1T/L 7271 GIS 조작시험","신부평S/S 362kV 서인천신부평#1T/L 7271 GIS 조작시험","2019-11-11 14:00","2019-11-11 18:00","2019-11-11 14:00","2019-11-11 18:00","당일"]
[53,"인천","부평","신가좌가정#2 T/L","YPP제 345kV 송전선로 보호배전반 성능개선","○ 보호계전기 내부 로직개선 및 펌웨어 업그레이드 ○ 인출DS 감시접점 Keep Ry 회로변경","2019-11-11 10:00","2019-11-11 18:00","2019-11-11 10:00","2019-11-11 18:00","당일"]
[54,"인천","시흥","신시흥#1S/S 신시흥-영흥TP#3T/L TIE CB(7700)","신시흥#1S/S 신시흥-영흥TP#3T/L TIE CB(7700) 조작","신시흥#1S/S 신시흥-영흥TP#3T/L TIE CB(7700) 조작","2019-11-11 10:00","2019-11-11 14:00","2019-11-11 10:00","2019-11-11 14:00","당일"]
[55,"인천","직할","신부평S/S 서인천CC-신부평#1T/L CB(7171)","신부평S/S 362kV 서인천신부평#1T/L 7171 GIS 조작시험","신부평S/S 362kV 서인천신부평#1T/L 7171 GIS 조작시험","2019-11-11 09:30","2019-11-11 14:00","2019-11-11 09:30","2019-11-11 14:00","당일"]
[56,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥#2S/S 345kV #6M.Tr 부싱유 채유 및 2차 조작","신시흥#2S/S 345kV #6M.Tr 부싱유 채유 및 2차 조작 및 #4S.Tr 보통점검","2019-11-08 10:00","2019-11-08 18:00","2019-11-08 10:00","2019-11-08 18:00","당일"]
[57,"인천","시흥","신시흥#2S/S #5 M.Tr","신시흥#2S/S 345kV #5M.Tr 부싱유 채유 및 2차 조작","신시흥#2S/S 345kV #5M.Tr 부싱유 채유 및 2차 조작","2019-11-07 10:00","2019-11-07 18:00","2019-11-07 10:00","2019-11-07 18:00","당일"]
[58,"인천","시흥","신시흥#2S/S #4 M.Tr","신시흥#2S/S 345kV #4M.Tr 부싱유 채유 및 1차 보통","신시흥#2S/S 345kV #4M.Tr 부싱유 채유 및 1차 보통","2019-11-06 10:00","2019-11-06 18:00","2019-11-06 10:00","2019-11-06 18:00","당일"]
[59,"인천","시흥","영흥1TP영흥2TP#2 T/L","YPP제 345kV 송전선로 보호배전반 성능개선","○ 보호계전기 내부 로직개선 및 펌웨어 업그레이드 ○ 인출DS 감시접점 Keep Ry 회로변경","2019-11-05 10:00","2019-11-05 18:00","2019-11-05 10:00","2019-11-05 18:00","당일"]
[60,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥#1S/S 345kV #3M.Tr PL-LA3 분전함대체","신시흥#1S/S 345kV #3M.Tr PL-LA3 분전함대체 및 #2S.Tr CB 조작","2019-11-05 09:00","2019-11-05 18:00","2019-11-05 09:00","2019-11-05 18:00","당일"]
[61,"인천","시흥","영흥1TP영흥2TP#1 T/L","YPP제 345kV 송전선로 보호배전반 성능개선","○ 보호계전기 내부 로직개선 및 펌웨어 업그레이드 ○ 인출DS 감시접점 Keep Ry 회로변경","2019-11-04 10:00","2019-11-04 18:00","2019-11-04 10:00","2019-11-04 18:00","당일"]
[62,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥#1S/S 345kV #1M.Tr 부싱유채유","신시흥#1S/S 345kV #1M.Tr 부싱유채유 및 3차 MAIN CB, #1S.Tr CB, #1-1,1-2 Sh.R CB 조작시험 및 PL-LA1 분전함 대체","2019-11-04 09:00","2019-11-04 18:00","2019-11-04 09:00","2019-11-04 18:00","당일"]
[63,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥#1S/S 345kV #2M.Tr 부싱유채유 및 2차 GIS 조작","신시흥#1S/S 345kV #2M.Tr 부싱유채유 및 2차 GIS 조작시험","2019-11-01 10:00","2019-11-01 18:00","2019-11-01 10:00","2019-11-01 18:00","당일"]
[64,"경기북부","고양","신파주S/S 신파주-양주#1T/L CB(7371)","변전총액공사-345kV GIS 보통점검","신파주-양주#1T/L 7371 CB 보통점검","2019-11-06 09:00","2019-11-06 18:00","2019-11-06 09:00","2019-11-06 18:00","당일"]
[65,"경기북부","고양","신파주S/S 신파주-신덕은#2-신김포#2 CB(7500)","변전총액공사-345kV GIS 보통점검","신파주S/S 7500 CB 보통점검","2019-11-07 09:00","2019-11-07 18:00","2019-11-07 09:00","2019-11-07 18:00","당일"]
[66,"경기북부","고양","신파주S/S 신김포-신파주#2T/L CB(7572)","변전총액공사-345kV GIS 보통점검","신파주S/S 7572 CB 보통점검","2019-11-08 09:00","2019-11-08 18:00","2019-11-08 09:00","2019-11-08 18:00","당일"]
[67,"경기북부","고양","신파주신덕은#1 T/L","2019년 가공송전선로 순시점검 위탁공사","345kV 신파주-신덕은#1,2T/L 정밀점검","2019-11-04 09:00","2019-11-08 18:00","취소","취소","연속"]
[68,"경기북부","고양","신파주신덕은#2 T/L","2019년 가공송전선로 순시점검 위탁공사","345kV 신파주-신덕은#1,2T/L 정밀점검","2019-11-11 09:00","2019-11-15 18:00","취소","취소","연속"]
[69,"경기북부","구리","미금성동#2 T/L","345kV T/L보호반(유호) 성능개선","345kV T/L보호반(유호) 성능개선","2019-11-13 09:00","2019-11-13 18:00","2019-11-13 09:00","2019-11-13 18:00","당일"]
[70,"경기북부","구리","미금성동#1 T/L","345kV T/L보호반(유호) 성능개선","345kV T/L보호반(유호) 성능개선","2019-11-12 09:00","2019-11-12 18:00","2019-11-12 09:00","2019-11-12 18:00","당일"]
[71,"경기북부","구리","동서울미금#2 T/L","345kV T/L보호반(가보) 성능개선","345kV T/L보호반(가보) 성능개선","2019-11-24 09:00","2019-11-24 18:00","2019-11-24 09:00","2019-11-24 18:00","당일"]
[72,"경기북부","구리","미금S/S 345kV #4 Sh.R","Sh.R 초기점검","Sh.R 초기점검","2019-11-07 09:00","2019-11-07 18:00","2019-11-07 09:00","2019-11-07 18:00","당일"]
[73,"경기북부","구리","신가평미금#2 T/L","미금S/S #78BAY B/F반 교체공사","신가평, 미금S/S #78BAY B/F반 교체(신가평4MTr-신가평미금2)","2019-11-08 09:00","2019-11-13 18:00","2019-11-08 09:00","2019-11-13 18:00","연속"]
[74,"경기북부","구리","미금S/S 345kV #1 Sh.R","Sh.R 보통점검","Sh.R 보통점검","2019-11-06 09:00","2019-11-06 18:00","2019-11-06 09:00","2019-11-06 18:00","당일"]
[75,"경기북부","구리","신가평S/S 345kV #4 Sh.R","신가평S/S #76Bay B/F 보호반 교체공사","신가평S/S #76Bay B/F 보호반 교체공사 : 신가평신의정부1-#4Sh.R","2019-11-18 09:00","2019-11-22 18:00","2019-11-18 09:00","2019-11-22 18:00","연속"]
[76,"경기북부","구리","신가평신의정부#1 T/L","신가평S/S #76Bay B/F 보호반 교체공사","신가평S/S #76Bay B/F 보호반 교체공사 : 신가평신의정부1-#4Sh.R","2019-11-18 09:00","2019-11-22 18:00","2019-11-18 09:00","2019-11-22 18:00","연속"]
[77,"경기북부","직할","신의정부S/S 345kV #3 Sh.R","'19년 직할 총액공사(#3Sh.R 보호배전반 대체공사)","'19년 직할 총액공사(#3Sh.R 보호배전반 대체공사)","2019-11-13 07:00","2019-11-15 18:00","2019-11-13 07:00","2019-11-15 18:00","연속"]
[78,"경기북부","직할","신의정부S/S 345kV #2 Sh.R","'19년 직할 총액공사(#2Sh.R 보호배전반 대체공사)","'19년 직할 총액공사(#2Sh.R 보호배전반 대체공사)","2019-11-11 07:00","2019-11-12 18:00","2019-11-11 07:00","2019-11-12 18:00","연속"]
[79,"경기북부","직할","신의정부미금#1 T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검(No.56~69)","2019-11-06 08:00","2019-11-07 18:00","2019-11-06 08:00","2019-11-07 18:00","연속"]
[80,"경기북부","직할","신가평신의정부#1 T/L","과열개소 보수점검(신가평-신의정부#1T/L)","지지볼트 과열에 의한 보수","2019-11-15 09:00","2019-11-15 18:00","2019-11-15 09:00","2019-11-15 18:00","연속"]
[81,"경기북부","직할","신의정부미금#2 T/L","2018~2019년 경기북부직할 가공송전 정비회사 총액공사","불량애자교체(No.53,59)","2019-11-04 08:00","2019-11-05 18:00","2019-11-04 08:00","2019-11-05 18:00","연속"]
[82,"경기북부","직할","양주S/S #1 M.Tr","양주S/S 345kV #1M.Tr 방열기 하자보수","양주S/S 345kV #1M.Tr 방열기 설치","2019-11-04 09:00","2019-11-08 18:00","2019-11-04 09:00","2019-11-08 18:00","연속"]
[83,"경기북부","구리","미금S/S #2 M.Tr"," 미금S/S #73BAY B/F보호반 교체공사"," 미금S/S #73BAY B/F보호반 교체공사","2019-11-04 09:00","2019-11-08 18:00","취소","취소","연속"]
[84,"경기북부","구리","동서울미금#1 T/L"," 미금S/S #73BAY B/F보호반 교체공사"," 미금S/S #73BAY B/F보호반 교체공사","2019-11-04 09:00","2019-11-08 18:00","취소","취소","연속"]
[85,"경기","군포","서서울#2신시흥#2 T/L","군포전력 송전정비회사 총액공사","345kV 서서울2신시흥T/L 활선애자청소(4기)","2019-11-01 08:00","2019-11-01 18:00","취소","취소","매일"]
[86,"경기","군포","서서울#2신시흥#1 T/L","군포전력 송전정비회사 총액공사","345kV 서서울2신시흥T/L 활선애자청소(4기)","2019-11-01 08:00","2019-11-01 18:00","취소","취소","매일"]
[87,"경기","군포","서서울#2신시흥#2 T/L","345kV서서울2-신시흥TL정밀점검(가공송전위탁공사)","345kV서서울2-신시흥#2TL No.54~98 가공송전선로 정밀점검","2019-11-07 09:00","2019-11-12 18:00","취소","취소","매일"]
[88,"경기","군포","서서울#2신시흥#1 T/L","345kV서서울2-신시흥TL정밀점검(가공송전위탁공사)","345kV서서울2-신시흥#1TL No.54~98 가공송전선로 정밀점검","2019-11-01 09:00","2019-11-06 18:00","취소","취소","매일"]
[89,"경기","군포","신온양서서울#2 T/L","345kV 신온양서서울외 2개T/L 지장철탑이설공사(임시선로구성)","임시선로 구성 No.61, 61-1, 61-2, 62 임시선로 구성","2019-11-17 08:00","2019-11-21 18:00","취소","취소","연속"]
[90,"경기","군포","신온양서서울#1 T/L","345kV 신온양서서울외 2개T/L 지장철탑이설공사(임시선로구성)","임시선로 구성 No.61, 61-1, 61-2, 62 임시선로 구성","2019-11-22 08:00","2019-11-28 18:00","취소","취소","연속"]
[91,"경기","군포","신온양서서울#2 T/L","345kV 신온양서서울외 2개T/L 지장철탑이설공사(임시선로구성)","임시선로 구성 No.61, 61-1, 61-2, 62 임시선로 구성","2019-11-29 08:00","2019-12-03 18:00","취소","취소","연속"]
[92,"경기","군포","신안산S/S 345kV #2 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #72BAY(#3M.Tr) 용량대체 - 345kV #2BUS측 DS(7252) 링크 분리 및 고정 안전작업 확보","2019-11-04 14:00","2019-11-04 18:00","2019-11-04 14:00","2019-11-04 18:00","연속"]
[93,"경기","군포","신안산S/S 345kV #1 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #72BAY(#3M.Tr) 용량대체 - 345kV #1BUS측 DS(7251) 링크 분리 및 고정 안전작업 확보","2019-11-04 09:00","2019-11-04 14:00","2019-11-04 09:00","2019-11-04 14:00","연속"]
[94,"경기","군포","신안산S/S #3 M.Tr","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #72BAY(#3M.Tr) 용량대체 - 345kV 40kA 2CB 철거, 345kV 63kA 3CB 설치","2019-11-04 09:00","2019-12-31 18:00","취소","취소","연속"]
[95,"경기","군포","신시흥신안산 T/L","군포전력 송전정비회사 총액공사","345kV 신시흥신안산T/L 활선애자청소(4기)","2019-11-01 08:00","2019-11-05 18:00","취소","취소","매일"]
[96,"경기","성남","신안성서안성#1 T/L","345kV 서안성S/S GIS 용량대체공사","ㅇ72Bay #1BUS 무부하가압","2019-11-16 09:00","2019-11-18 09:00","취소","취소","연속"]
[97,"경기","성남","서안성S/S 345kV #70 BUS","345kV 서안성S/S GIS 용량대체공사","ㅇ 72Bay GIS 철거 및 설치(2CB) ㅇ 기타 부대공사","2019-11-01 09:00","2019-11-18 09:00","취소","취소","연속"]
[98,"경기","성남","서안성S/S 345kV #75 BUS","345kV 서안성S/S GIS 용량대체공사","ㅇ 72Bay GIS 철거 및 설치(2CB) ㅇ 기타 부대공사","2019-11-18 09:00","2019-12-06 09:00","취소","취소","연속"]
[99,"경기","성남","서안성신진천#2 T/L","송전정비회사 총액공사(전력선교체)","ㅇ#2T/L 84-86 하단 2가닥 전력선 교체","2019-11-25 08:00","2019-11-26 18:00","취소","취소","연속"]
[100,"경기","성남","서안성신진천#1 T/L","345kV 서안성-신진천#1T/L 정밀점검","345kV 서안성-신진천#1T/L 정밀점검 - 구간 : No.36~서안성S/S : 철탑 63기, 22.050km","2019-11-27 09:00","2019-11-30 18:00","취소","취소","연속"]
[101,"경기","성남","서안성신진천#1 T/L","345kV 서안성S/S GIS 용량대체공사","ㅇ 72Bay GIS 철거 및 설치(2CB) ㅇ 기타 부대공사","2019-11-01 09:00","2019-12-06 09:00","취소","취소","연속"]
[102,"경기","성남","신안성신성남#2 T/L","345kV 신용인-동서울#1T/L 애자련 교체공사","- 345kV 신용인-동서울#1T/L 2기 애자련 교체 관련 안전이격거리 확보차","2019-11-15 08:00","2019-11-16 18:00","취소","취소","연속"]
[103,"경기","성남","신안성신성남#1 T/L","345kV 신성남-동서울#1T/L 애자련 교체공사","- 345kV 신성남-동서울#1T/L 3기 애자련 교체 관련 안전이격거리 확보차","2019-11-18 08:00","2019-11-19 18:00","취소","취소","연속"]
[104,"경기","성남","신성남동서울#1 T/L","345kV 신성남-동서울#1T/L 애자련 교체공사","- 345kV 신성남-동서울#1T/L 3기 애자련 교체","2019-11-18 08:00","2019-11-19 18:00","취소","취소","연속"]
[105,"경기","성남","신안성신성남#1 T/L","345kV 신용인-동서울#1T/L 애자련 교체공사","- 345kV 신용인-동서울#1T/L 3기 애자련 교체 관련 안전이격거리 확보차","2019-11-13 08:00","2019-11-14 18:00","취소","취소","연속"]
[106,"경기","성남","신성남S/S #6 M.Tr","EOCR 보조Ry 교체","EOCR 보조Ry 교체","2019-11-12 09:00","2019-11-12 18:00","2019-11-12 09:00","2019-11-12 18:00","당일"]
[107,"경기","성남","신성남동서울#2 T/L","신성남-동서울TL OPGW시설공사(대장지구)","신성남동서울T/L 불곡산C/H~동서울 구간 OPGW 증설","2019-11-20 07:00","2019-12-09 18:00","취소","취소","연속"]
[108,"경기","성남","신안성신성남#2 T/L","345kV 신성남-동서울#2T/L 애자련 교체공사","345kV 신성남-동서울#2T/L 2기 애자련 교체 관련 안전이격거리 확보차","2019-11-20 08:00","2019-11-21 18:00","취소","취소","연속"]
[109,"경기","성남","신안성신수원#1 T/L","154kV 신용인-용인T/L OPGW 증설공사","용인S/S~신용인S/S간 OPGW(24C→48C) 8.814km 교체","2019-11-29 07:00","2019-11-01 18:00","2019-11-30 07:00","2019-12-01 18:00","연속"]
[110,"경기","성남","신안성신용인#1 T/L","LA 하자점검","LA 하자점검","2019-11-12 09:00","2019-11-12 18:00","취소","취소","당일"]
[111,"경기","성남","신안성신수원#1 T/L","7972 GIS 보통점검","7972 GIS 보통점검","2019-11-10 09:00","2019-11-10 18:00","2019-11-10 09:00","2019-11-10 18:00","당일"]
[112,"경기","성남","신안성신수원#2 T/L","GIS 보통점검","신안성:7A72,7A00 보통 신수원:LA 대체","2019-11-09 09:00","2019-11-09 18:00","2019-11-09 09:00","2019-11-09 18:00","당일"]
[113,"경기","성남","신안성S/S 765kV #3 M.Tr 2차 GIS","DS 보조Ry 교체 (7871CB 단독휴전)","7851,7861DS 보조Ry 교체","2019-11-06 09:00","2019-11-06 18:00","2019-11-06 09:00","2019-11-06 18:00","당일"]
[114,"경기","성남","신안성신용인#2 T/L","LA하자, CVT 대체 , 보조Ry 교체","신용인:LA 하자, CVT 대체 신안성:7822EDS,7801,7802DS보조Ry교체","2019-11-11 09:00","2019-11-11 18:00","취소","취소","당일"]
[115,"경기","성남","신용인동서울#1 T/L","신성남-동서울TL OPGW시설공사(대장지구)","신성남동서울T/L 불곡산C/H~동서울 구간 OPGW 증설","2019-11-23 07:00","2019-11-23 18:00","2019-11-23 07:00","2019-11-23 18:00","연속"]
[116,"경기","성남","신용인S/S #2 M.Tr","3차 절연보강","3차 절연보강","2019-11-08 09:00","2019-11-08 18:00","2019-11-08 09:00","2019-11-08 18:00","당일"]
[117,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울#1T/L 애자련 교체공사","- 345kV 신용인-동서울#1T/L 3기 애자련 교체","2019-11-13 08:00","2019-11-14 18:00","2019-11-13 08:00","2019-11-14 18:00","연속"]
[118,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울#2T/L 애자련 교체공사","- 345kV 신용인-동서울#2T/L 2기 애자련 교체","2019-11-15 08:00","2019-11-16 18:00","2019-11-15 08:00","2019-11-16 18:00","연속"]
[119,"경기","직할","화성신시흥 T/L","군포전력 송전정비회사 총액공사","345kV 화성신시흥T/L 활선애자청소(13기)","2019-11-01 08:00","2019-11-05 18:00","취소","취소","매일"]
[120,"경기","직할","화성신안산 T/L","군포전력 송전정비회사 총액공사","345kV 화성신안산T/L 활선애자청소(9기)","2019-11-04 08:00","2019-11-05 18:00","취소","취소","매일"]
[121,"경기","직할","화성서서울#1 T/L","군포전력 송전정비회사 총액공사","345kV 화성서서울T/L 활선애자청소(19기)","2019-11-06 08:00","2019-11-08 18:00","취소","취소","매일"]
[122,"경기","직할","화성서서울#2 T/L","군포전력 송전정비회사 총액공사","345kV 화성서서울T/L 활선애자청소(19기)","2019-11-06 08:00","2019-11-08 18:00","취소","취소","매일"]
[123,"경기","직할","화성평택T/P#2 T/L","군포전력 송전정비회사 총액공사","345kV 화성평택TPT/L 활선애자청소(21기)","2019-11-11 08:00","2019-11-14 18:00","취소","취소","매일"]
[124,"경기","직할","화성평택T/P#1 T/L","군포전력 송전정비회사 총액공사","345kV 화성평택TPT/L 활선애자청소(21기)","2019-11-11 08:00","2019-11-14 18:00","취소","취소","매일"]
[125,"경기","직할","화성S/S 345kV #2 CLR 76BUS GIS","19년 직할 변전협력회사 총액공사","화성S/S #2CLR 75,76BUS GIS 초기점검","2019-11-05 14:00","2019-11-05 18:00","2019-11-05 14:00","2019-11-05 18:00","당일"]
[126,"경기","직할","화성S/S 345kV #75-#76 SEC GIS","19년 직할 변전협력회사 총액공사","화성S/S 75-76 SEC GIS 초기점검","2019-11-06 09:00","2019-11-06 18:00","2019-11-06 09:00","2019-11-06 18:00","당일"]
[127,"경기","직할","화성서서울#1 T/L","345kV 신안산분기T/L OPGW 시설공사","가. 공사장소 : 화성S/S~신안산S/S 나. 시설내역 - OPGW 120㎟ 24C 17.566㎞ 시설 - OPGW 120㎟ 48C 4.113㎞ 시설 - 비금속광케이블(FOFC) 24C 0.465㎞ 시설 - 비금속광케이블(FOFC) 48C 0.332㎞ 시설","2019-11-07 07:00","2019-11-07 18:00","2019-11-07 07:00","2019-11-07 18:00","연속"]
[128,"경기","직할","서서울#2화성 #2 T/L","19년 직할 변전협력회사 총액공사","화성S/S 화성-서서울#2T/L GIS 조작, PT하자, LA 하자점검","2019-11-01 09:00","2019-11-01 18:00","2019-11-01 09:00","2019-11-01 18:00","당일"]
[129,"경기","직할","아산화성#1 T/L","345kV 신온양서서울외 2개T/L 지장철탑이설공사(임시선로구성)","임시선로 구성 No.85 임시선로 구성","2019-11-08 08:00","2019-11-12 18:00","취소","취소","연속"]
[130,"경기","직할","아산화성#2 T/L","345kV 신온양서서울외 2개T/L 지장철탑이설공사(임시선로구성)","임시선로 구성 No.85 임시선로 구성","2019-11-13 08:00","2019-11-16 18:00","취소","취소","연속"]
[131,"경기","직할","화성신안산 T/L","19년 직할 변전협력회사 총액공사","화성S/S 화성-신안산T/L 1차 GIS 조작, PT,LA 하자점검","2019-11-15 09:00","2019-11-15 18:00","취소","취소","당일"]
[132,"경기","직할","화성신안산 T/L","봉담-송산 고속도로 지장철탑 이설공사","봉담-송산 고속도로 지장철탑 이설공사(345kV 화성-신안산T/L No.16~20)","2019-11-21 07:00","2019-11-30 18:00","2019-11-21 07:00","2019-11-30 18:00","연속"]
[133,"경기","직할","화성S/S #2 CLR 75BUS GIS(7577)","19년 직할 변전협력회사 총액공사","화성S/S #2CLR 75,76BUS GIS 초기점검","2019-11-05 09:00","2019-11-05 14:00","2019-11-05 09:00","2019-11-05 14:00","당일"]
[134,"강원","동해","동해신양양 T/L","2019년 동해전력지사 변전협력회사 총액공사","1. 송전선로 보호반 대체","2019-11-11 09:30","2019-11-15 18:00","2019-11-11 09:30","2019-11-15 18:00","당일"]
[135,"강원","동해","삼척GP한울NP #1 T/L","2019년 동해전력지사 가공송전선로순시점검 위탁공사","정밀점검","2019-11-18 09:00","2019-11-22 18:00","2019-11-18 09:00","2019-11-22 18:00","매일"]
[136,"강원","동해","삼척GP한울NP #2 T/L","2019년 동해전력지사 가공송전선로순시점검 위탁공사","정밀점검","2019-11-25 09:00","2019-11-29 18:00","2019-11-25 09:00","2019-11-29 18:00","매일"]
[137,"강원","동해","동해삼척GP#2 T/L","345kV 동해-삼척GPT/L 전선접속개소 전선교체공사","공사개요 ○ 전력선 접속개소 해소 : No.5 ∼ 6 등 8개소 15.448C-km ○ 가공지선 접속개소 해소 : No.12 ∼ 17 등 3개소 5.944C-km","2019-11-05 08:00","2019-11-19 18:00","2019-11-05 08:00","2019-11-19 18:00","연속"]
[138,"강원","태백","신태백S/S #2 Sh.R 1차 #1-2 CB(7471)","18-19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7471CB 조작시험","2019-11-07 10:00","2019-11-08 18:00","2019-11-07 10:00","2019-11-08 18:00","연속"]
[139,"강원","태백","신태백S/S 345kV #2 Sh.R","18-19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7479, 7471, 7400CB 조작시험","2019-11-07 10:00","2019-11-08 18:00","2019-11-07 10:00","2019-11-08 18:00","연속"]
[140,"강원","태백","신태백S/S 345kV #3 Sh.R","18-19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7479CB 보통점검","2019-11-11 10:00","2019-11-11 18:00","2019-11-11 10:00","2019-11-11 18:00","당일"]
[141,"강원","태백","신태백S/S #3Sh.R 1차-한울N/P2#1T/L TIE CB(7500)","18-19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7579CB 보통점검에 따른 필요 휴전","2019-11-11 10:00","2019-11-11 18:00","2019-11-11 10:00","2019-11-11 18:00","당일"]
[142,"강원","태백","신태백S/S #3 Sh.R 1차 #1-2 CB(7571)","18-19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7579CB 보통점검에 따른 필요 휴전","2019-11-11 10:00","2019-11-11 18:00","2019-11-11 10:00","2019-11-11 18:00","당일"]
[143,"강원","태백","신태백S/S #2Sh.R 1차-#74BAYT/L TIE CB(7400)","18-19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7400CB 조작시험","2019-11-07 10:00","2019-11-08 18:00","2019-11-07 10:00","2019-11-08 18:00","연속"]
[144,"충북","직할","신중부신진천#2 T/L","345kV 신중부-신진천T/L 안전이격거리 확보공사","철탑도장 1기","2019-11-28 07:30","2019-11-29 19:00","2019-11-21 07:30","2019-11-22 19:00","당일"]
[145,"충북","직할","신중부신진천#1 T/L","345kV 신중부-신진천T/L 안전이격거리 확보공사","철탑설치 5기, 철탑철거 5기(가철탑 4기 설치), 전선가선(6.6km)","2019-11-19 07:30","2019-11-27 19:00","2019-11-15 07:30","2019-11-20 19:00","연속"]
[146,"충북","청주","신옥천신남원#1 T/L","345kV 신옥천-신남원 T/L 스페이서 간격조정공사","345kV 신옥천-신남원 #1 T/L - No. 179~184 등 56경간 스페이서 설치간격 조정","2019-11-18 08:00","2019-11-24 18:00","2019-11-18 08:00","2019-11-24 18:00","매일"]
[147,"충북","청주","신옥천신남원#2 T/L","345kV 신옥천-신남원 T/L 스페이서 간격조정공사","345kV 신옥천-신남원 #2 T/L - No. 179~184 등 56경간 스페이서 설치간격 조정","2019-11-25 08:00","2019-12-01 18:00","2019-11-25 08:00","2019-12-01 18:00","매일"]
[148,"충북","청주","신옥천S/S #1 M.Tr","신옥천S/S 154kV GIS화 공사","154kV GIS 26CCT 설치 옥외철구→GIS 부하절체","2019-11-04 09:00","2019-11-07 18:00","2019-11-04 09:00","2019-11-07 18:00","연속"]
[149,"충북","충주","신제천신충주#1 T/L","2018-2019년 송전정비회사 총액공사","항공장애표시구 설치 (No.23~185)","2019-11-04 08:00","2019-11-07 18:00","2019-11-04 08:00","2019-11-07 18:00","매일"]
[150,"충북","충주","신제천신영주#1 T/L","2018-2019년 송전정비회사 총액공사","항공장애표시구 설치 (No.49~119)","2019-11-08 08:00","2019-11-08 18:00","2019-11-08 08:00","2019-11-08 18:00","당일"]
[151,"충북","충주","신충주S/S #2 M.Tr","신충주S/S #2M.Tr C상 변압기 및 OLTC정밀점검","#2M.Tr 정밀점검 *1상 #2M.Tr OLTC 정밀점검*1상","2019-11-11 09:00","2019-11-15 18:00","2019-11-11 09:00","2019-11-15 18:00","연속"]
[152,"충북","충주","신충주S/S STATCOM CB","신충주S/S STATCOM 제어동 소방설비 점검 등","1. STATCOM 제어동 소방설비 점검 2. #1 Cooling System 3번 방열팬 누수보수 3. Yard 내 수목 제초 4. 18-19년도 직할 변전정비 총액공사 (STATCOM Tr - TIE, Tr 1차 GIS 및 변압기 초기점검)","2019-11-04 09:30","2019-11-06 18:00","2019-11-04 09:30","2019-11-06 18:00","당일"]
[153,"대전충남","대전","신계룡S/S #1 M.Tr","신계룡S/S 345kV 72BAY B/F PNL 교체","신계룡S/S 345kV 72BAY B/F PNL 교체","2019-11-25 09:00","2019-11-29 18:00","2019-11-25 09:00","2019-11-29 18:00","연속"]
[154,"대전충남","대전","신옥천신계룡 T/L","[송전] 345kV 신옥천-신계룡T/L 전선접속개소 전력선 교체공사","[송전] 345kV 신옥천-신계룡T/L 전선접속개소 전력선 교체 (No.1~4,6~8)","2019-11-25 07:00","2019-11-29 18:00","취소","취소","연속"]
[155,"대전충남","서산","당진T/P #72 TIE TR 1차-TIE CB(7300)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 -당진T/P #2M.Tr 1차 - TIE 7300CB 부동작 예방시험","2019-11-20 10:00","2019-11-20 14:00","2019-11-20 10:00","2019-11-20 14:00","당일"]
[156,"대전충남","서산","당진T/P #72 Tie-Tr","보호반 성능개선","보호반 성능개선","2019-11-18 09:00","2019-11-18 18:00","2019-11-18 09:00","2019-11-18 18:00","당일"]
[157,"대전충남","서산","신당진S/S #3 M.Tr 1차 CB(7872)","19년도 차단기 부동작 예방시험","19년도 차단기 부동작 예방시험 -신당진S/S 345kV #3M.tr 1차 7872CB 부동작 예방시험","2019-11-14 10:00","2019-11-14 14:00","2019-11-14 10:00","2019-11-14 14:00","당일"]
[158,"대전충남","서산","신서산태안TP#1 T/L","19년도 서산P/O 노후배전반 교체공사","- 신서산S/S 345kV 76BAY BF반 대체공사 - 신서산S/S 735kV #3M.Tr 3차측 PT대체공사","2019-11-25 09:00","2019-11-29 18:00","취소","취소","연속"]
[159,"대전충남","서산","태안T/P #1 M.Tr","19년도 서산P/O 변전정비회사 총액공사","- 태안화력 345kV #1M.Tr 임시점검 - 태안화력 345kV 7871 GIS 무부하가압(11.8)","2019-11-04 09:00","2019-11-08 18:00","취소","취소","연속"]
[160,"대전충남","서산","신당진개폐소태안TP#1 T/L","154kV 태안화력 T/L 피뢰기 설치공사","154kV 태안-태안화력 T/L 피뢰기 설치공사 No.1~51 (안전이격)","2019-11-09 07:30","2019-11-10 18:00","취소","취소","매일"]
[161,"대전충남","서산","태안T/P #1 M.Tr 1차 CB(7871)","19년도 서산P/O 765/345kV GIS 점검공사","- 태안화력 345kV 7871 GIS 정밀점검 - 태안화력 345kV 7871 GIS 절연롯드 교체작업","2019-11-04 09:00","2019-11-08 18:00","2019-11-04 09:00","2019-11-08 18:00","연속"]
[162,"대전충남","서산","태안T/P 345kV #72 BUS","19년도 서산P/O 765/345kV GIS 점검공사","- 태안화력 345kV 7871 GIS 무부하가압(11.7-8)","2019-11-07 14:00","2019-11-08 18:00","2019-11-07 14:00","2019-11-08 18:00","연속"]
[163,"대전충남","세종","세종S/S #3 M.Tr","세종변전소 #3 M.Tr 카메라 보수","세종변전소 345 #3 M.Tr 설비 감시용 카메라 장애 관련 오토리프트 설치 및 카메라 장애 보수","2019-11-04 09:00","2019-11-04 18:00","2019-11-04 09:00","2019-11-04 18:00","당일"]
[164,"대전충남","아산","신온양신탕정#2 T/L","345kV 북당진-신탕정T/L 건설공사(2공구)","345kV 북당진-신탕정T/L 건설공사(2공구) - 청양-신탕정 임시선로 구성 관련 점퍼선 취부","2019-11-04 07:00","2019-11-07 18:00","2019-11-04 07:00","2019-11-07 18:00","연속"]
[165,"대전충남","아산","신온양신탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사(2공구)","345kV 북당진-신탕정T/L 건설공사(2공구) - 345kV 신온양-신탕정T/L 미시공개소(점퍼선 및 이도조정세트)","2019-11-10 07:00","2019-11-12 18:00","2019-11-10 07:00","2019-11-12 18:00","연속"]
[166,"대전충남","아산","청양신온양#2 T/L","345kV북당진-신탕정T/L 건설공사(2공구)","345kV 북당진-신탕정T/L 건설공사(2공구) - 84호 점퍼선취부, 84호~85호 가공지선 긴선, 항공장애표시구 및 부속품 취부 등","2019-11-08 07:00","2019-11-09 18:00","2019-11-08 07:00","2019-11-09 18:00","연속"]
[167,"대전충남","아산","아산S/S #1 M.Tr","아산S/S 345kV #1M.Tr 부싱절연유 채유","아산S/S 345kV #1M.Tr 부싱절연유 채유","2019-11-04 09:00","2019-11-04 18:00","2019-11-04 09:00","2019-11-04 18:00","당일"]
[168,"대전충남","아산","아산S/S #2 M.Tr","아산S/S 345kV #2M.Tr 부싱절연유 채유","아산S/S 345kV #2M.Tr 부싱절연유 채유","2019-11-05 09:00","2019-11-05 18:00","2019-11-05 09:00","2019-11-05 18:00","당일"]
[169,"대전충남","아산","아산화성#2 T/L","345kV 북당진-신탕정T/L OPGW 시설공사","북당진-신탕정T/L 신설관련 OPGW 교체작업","2019-11-28 09:00","2019-11-29 18:00","취소","취소","연속"]
[170,"대전충남","아산","아산화성#1 T/L","345kV 북당진-신탕정T/L 건설공사(2공구)","345kV 북당진-신탕정T/L 건설공사(2공구) - 78호~79호 가공지선 긴선 및 항공장애표시구 취부","2019-11-13 07:00","2019-11-13 18:00","취소","취소","당일"]
[171,"대전충남","청양","보령TP보령CC#2 T/L","송전선로 보호반 성능개선","송전선로 보호반 성능개선(양단) - YPP제 DS Fail 관련 성능개선","2019-11-10 09:00","2019-11-10 18:00","2019-11-10 09:00","2019-11-10 18:00","당일"]
[172,"대전충남","청양","아산보령TP#2 T/L","송전선로 보호반 성능개선","송전선로 보호반 성능개선(양단) - YPP제 DS Fail 관련 성능개선","2019-11-09 09:00","2019-11-09 18:00","2019-11-09 09:00","2019-11-09 18:00","당일"]
[173,"대전충남","청양","보령T/P #4 M.Tr 1차 CB(7472)","보령T/P 362kV GIS 초기점검","보령T/P 362kV GIS 초기점검 - 대상 : 7472","2019-11-07 09:00","2019-11-07 18:00","2019-11-07 09:00","2019-11-07 18:00","당일"]
[174,"대전충남","청양","보령T/P #75-#76 SEC CB","보령T/P 362kV GIS 하자점검","보령T/P 362kV GIS 하자점검 - 대상 : 75-76","2019-11-22 09:00","2019-11-22 18:00","2019-11-29 09:00","2019-11-29 18:00","당일"]
[175,"대전충남","청양","보령T/P #3,4 SU TR 1차 CB(7372)","보령T/P 362kV GIS(7372) 초기점검","보령T/P 362kV GIS 하자점검 - 대상 : 7372","2019-11-27 09:00","2019-11-27 18:00","2019-11-27 09:00","2019-11-27 18:00","당일"]
[176,"대전충남","청양","보령T/P #70-#71 SEC CB","보령T/P 362kV GIS 초기점검","보령T/P 362kV GIS 초기점검 - 대상 : 70-71","2019-11-15 09:00","2019-11-15 18:00","2019-11-15 09:00","2019-11-15 18:00","당일"]
[177,"대전충남","청양","보령T/P #5 M.Tr 1차 CB(7572)","보령T/P 362kV GIS(7572) 초기점검","보령T/P 362kV GIS 하자점검 - 대상 : 7572","2019-11-28 09:00","2019-11-28 18:00","2019-11-28 09:00","2019-11-28 18:00","당일"]
[178,"대전충남","청양","청양보령TP#2 T/L","송전선로 보호반 성능개선","송전선로 보호반 성능개선(양단) - 유호제 DS Fail 관련 성능개선","2019-11-17 09:00","2019-11-17 18:00","2019-11-17 09:00","2019-11-17 18:00","당일"]
[179,"대전충남","청양","신옥천청양 T/L","[송전] 345kV 신옥천-청양T/L 정밀점검","[송전] 345kV 신옥천-청양T/L 정밀점검 (No.84-1~92,106~119)","2019-11-18 08:00","2019-11-21 18:00","취소","취소","매일"]
[180,"대전충남","청양","청양S/S #2 M.Tr TIE CB(7700)","청양S/S 362kV 차단기 전자변 교체","청양S/S 362kV 차단기 전자변 교체 및 메커니즘 점검 - 대상 : 7700","2019-11-20 09:00","2019-11-21 18:00","2019-11-20 09:00","2019-11-21 18:00","연속"]
[181,"대전충남","청양","청양S/S #2 M.Tr 1차 CB(7772)","청양S/S 362kV 차단기 전자변 교체","청양S/S 362kV 차단기 전자변 교체 및 메커니즘 점검 - 대상 : 7772","2019-11-25 09:00","2019-11-26 18:00","2019-11-25 09:00","2019-11-26 18:00","연속"]
[182,"대전충남","청양","청양보령TP#1 T/L","송전선로 보호반 성능개선","송전선로 보호반 성능개선(양단) - 유호제 DS Fail 관련 성능개선","2019-11-16 09:00","2019-11-16 18:00","2019-11-16 09:00","2019-11-16 18:00","당일"]
[183,"대전충남","서산","신서산신당진#1 T/L","민원구간 서산P/O OPGW 항공장애표시구 시설공사","OPGW 항공장애표시구 26개 설치","2019-11-02 09:00","2019-11-03 18:00","2019-11-02 09:00","2019-11-03 18:00","매일"]
[184,"전북","김제","신김제S/S #3 M.Tr","신김제S/S AC,DC 옥외분전반 교체공사","신김제S/S AC,DC 옥외분전반 교체공사 안전이격거리 확보","2019-11-18 09:00","2019-11-19 18:00","2019-11-18 09:00","2019-11-19 18:00","연속"]
[185,"전북","직할","신남원의령#2 T/L","항공장애표시구 시설공사","신남원-의령#2T/L 항공장애표시구 26개 시설","2019-11-05 09:00","2019-11-05 18:00","취소","취소","당일"]
[186,"전북","직할","신남원S/S 345kV #70 BUS","신남원S/S 345kV GIS CB/DS GAS 누기 보수공사","- 345kV GIS CB/DS SF6 GAS 누기에 따른 보수공사 - 345kV #70BUS GAS 감압","2019-11-11 09:30","2019-11-29 17:00","2019-11-11 09:30","2019-11-29 17:00","연속"]
[187,"전북","직할","신남원신광주#1 T/L","신남원S/S 345kV GIS CB/DS GAS 누기 보수공사","- 345kV GIS CB/DS SF6 GAS 누기에 따른 보수공사","2019-11-11 09:30","2019-11-29 17:00","2019-11-11 09:30","2019-11-29 17:00","연속"]
[188,"광주전남","강진","신강진S/S 345kV #70 BUS (GIS)","신강진S/S 345kV 이하 취약설비 GIS화 사업","옥외철구 -> GIS화 75BAY 가압 조작","2019-11-27 14:00","2019-11-28 14:00","2019-11-27 14:00","2019-11-28 14:00","연속"]
[189,"광주전남","강진","신강진S/S 345kV #75 BUS (GIS)","신강진S/S 345kV 이하 취약설비 GIS화 사업","옥외철구 -> GIS화 75BAY 가압 조작","2019-11-28 14:00","2019-11-29 14:00","2019-11-28 14:00","2019-11-29 14:00","연속"]
[190,"광주전남","강진","신강진S/S 345kV #1 BUS (GIS)","신강진S/S 345kV 취약설비 GIS화","345kV 옥외 철구 -> 345kV GIS 화 (75BAY)","2019-11-02 09:00","2019-11-06 18:00","2019-11-09 09:00","2019-11-13 18:00","연속"]
[191,"광주전남","강진","신강진S/S #1 M.Tr","2018∼'19년도 강진전력지사 변전정비회사 총액공사","- #1M.Tr A,B,C상 1,2차 부싱 절연유 채유(추적분석)","2019-11-26 09:00","2019-11-26 18:00","2019-11-26 09:00","2019-11-26 18:00","당일"]
[192,"광주전남","광주","신광주S/S #3 M.Tr","19년 광주변전총액(LA,CVT,GIS,VCB,DS,S.Tr 점검)","1. 345kV #3M.Tr 1차,2차,3차 LA 보통점검, 3차 CVT 보통 2. 154kV #3M.Tr 2차 GIS 하자점검 3. VCB 점검 : 4384, 4389(보통), 4379-1,2(장기미동작점검) 4. 단로기 보통점검 : 4386,4385,4375-1,4375-2 5. 분로리액터 하자점검 : #3-1,2Sh.R 6. 소내변압기 보통점검 : #2S.Tr A,B,C상 7. AC/DC 옥외분전반 교체","2019-11-04 09:00","2019-11-06 18:00","2019-11-04 09:00","2019-11-06 18:00","연속"]
[193,"광주전남","순천","광양율촌CC T/L","345V 광양-율촌CCT/L 항공장애표시구 설치공사","18~19년도 순천전력 협력회사 총액공사 - 광양-율촌CCT/L 항공장애표시구 설치 : No.101~102호","2019-11-13 07:00","2019-11-13 13:00","2019-11-13 07:00","2019-11-13 13:00","당일"]
[194,"광주전남","순천","신남원광양#2 T/L","신남원-광양 OPGW용 항공구 설치","신남원-광양T/L No.138~208구간 7개경간 항공구 42조 시설","2019-11-07 08:00","2019-11-08 18:00","2019-11-07 08:00","2019-11-08 18:00","연속"]
[195,"광주전남","순천","광양여수TP T/L","345V 신남원-광양#1T/L 불량애자교체공사(안전거리확보)","18~19년도 순천전력 협력회사 총액공사 - 신남원-광양#1 T/L 불량애자교체 : No.14호(1기) - 병가선로 안전거리확보","2019-11-18 07:00","2019-11-18 18:00","2019-11-18 07:00","2019-11-18 18:00","당일"]
[196,"광주전남","순천","신남원광양#1 T/L","19년 순천 변전협력회사 총액공사","[광양] 신남원-광양#1T/L CVT(A,B상) 교체","2019-11-18 10:00","2019-11-19 18:00","2019-11-18 10:00","2019-11-19 18:00","연속"]
[197,"광주전남","순천","여수T/P #2 Tie-Tr","19년 순천변전협력회사총액공사(72BAY B/F반 대체)","여수화력S/Y 345kV 72BAY B/F반 대체","2019-11-01 10:00","2019-11-06 18:00","2019-11-01 10:00","2019-11-06 18:00","연속"]
[198,"광주전남","순천","율촌CC여수TP T/L","19년 순천변전협력회사총액공사(72BAY B/F반 대체)","여수화력S/Y 345kV 72BAY B/F반 대체","2019-11-01 10:00","2019-11-06 18:00","2019-11-01 10:00","2019-11-06 18:00","연속"]
[199,"대구","경산","울주신경산#1 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 울주-신경산 No.118~120 - No.119 가철탑 활용 임시선로 구성","2019-11-17 09:00","2019-11-20 18:00","취소","취소","연속"]
[200,"대구","경산","울주신경산#2 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 울주-신경산 No.118~120 - No.119 가철탑 활용 임시선로 구성","2019-11-13 09:00","2019-11-16 18:00","취소","취소","연속"]
[201,"대구","경산","신경산S/S #4 M.Tr","2018~19년 경산변전협력 총액공사","-GIS점검 및 계전기성개선","2019-11-12 09:00","2019-11-12 18:00","2019-11-12 09:00","2019-11-12 18:00","당일"]
[202,"대구","경산","신경산S/S #3 M.Tr","2018~19년 경산변전협력 총액공사","-GIS점검 및 계전기성개선","2019-11-11 09:00","2019-11-11 18:00","2019-11-11 09:00","2019-11-11 18:00","당일"]
[203,"대구","경산","신경산S/S 345kV #75 BUS","신경산S/S 362kV GIS 대체공사","모선ES~DS간 인터록 시험 모선DS 조작시험, 자체인터록 시험 무부하 가압(송전선로~7100CB~7172CB~#1BUS~#2M.Tr)","2019-11-01 09:00","2019-11-02 09:00","2019-11-01 09:00","2019-11-02 09:00","연속"]
[204,"대구","경산","신경산대구#2 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 신경산-대구 No.3~6 - No.5 가철탑 활용 임시선로 구성","2019-11-27 09:00","2019-11-30 18:00","2019-11-23 09:00","2019-11-28 18:00","연속"]
[205,"대구","경산","신경산대구#1 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 신경산-대구 No.3~6 - No.5 가철탑 활용 임시선로 구성","2019-11-23 09:00","2019-11-26 18:00","2019-11-19 09:00","2019-11-22 18:00","연속"]
[206,"대구","달성","북경남고령#2 T/L","고령S/S 북경남고령2/L 계전기 성능개선(시험팀 요청휴전)","고령S/S 북경남고령2/L 계전기 성능개선(시험팀 요청휴전)","2019-11-25 09:00","2019-11-25 18:00","2019-11-25 09:00","2019-11-25 18:00","당일"]
[207,"대구","달성","고령의령#2 T/L","고령S/S 고령의령2T/L 계전기 성능개선(시험팀 요청휴전)","고령S/S 고령의령2T/L 계전기 성능개선(시험팀 요청휴전)","2019-11-26 14:00","2019-11-26 18:00","2019-11-26 14:00","2019-11-26 18:00","당일"]
[208,"대구","달성","고령의령#1 T/L","고령S/S 고령의령1T/L 계전기 성능개선(시험팀 요청휴전)","고령S/S 고령의령1T/L 계전기 성능개선(시험팀 요청휴전)","2019-11-26 09:00","2019-11-26 14:00","2019-11-26 09:00","2019-11-26 14:00","당일"]
[209,"대구","달성","북경남고령#1 T/L","고령S/S 78B/F 교체작업","78B/F 대체, 차단기동작특성시험,보통점검, 지지애자 교체작업","2019-11-11 09:00","2019-11-19 18:00","2019-11-11 09:00","2019-11-19 18:00","연속"]
[210,"대구","달성","고령S/S #4 M.Tr","고령S/S 78B/F 교체작업","78B/F 대체, 차단기동작특성시험,보통점검, 지지애자 교체작업","2019-11-11 09:00","2019-11-19 18:00","2019-11-11 09:00","2019-11-19 18:00","연속"]
[211,"대구","달성","북경남대구#2 T/L","대구S/S 북경남대구2T/L 계전기 성능개선(시험팀 요청휴전)","대구S/S 북경남대구2T/L 계전기 성능개선(시험팀 요청휴전)","2019-11-27 14:00","2019-11-27 18:00","2019-11-27 14:00","2019-11-27 18:00","당일"]
[212,"대구","달성","북경남대구#2 T/L","'18-'19년 달성 송전정비 협력회사 총액공사","항공구 설치 No.62-63 안전확보","2019-11-04 12:00","2019-11-04 18:00","2019-11-04 12:00","2019-11-04 18:00","당일"]
[213,"대구","달성","북경남대구#1 T/L","대구S/S 북경남대구1/L 계전기 성능개선(시험팀 요청휴전)","대구S/S 북경남대구1/L 계전기 성능개선(시험팀 요청휴전)","2019-11-27 09:00","2019-11-27 14:00","2019-11-27 09:00","2019-11-27 14:00","당일"]
[214,"대구","칠곡","서대구S/S 북경남-서대구#1T/L CB(7471)","서대구S/S 북경남-서대구#1T/L 7471 CB 장기미동작점검","서대구S/S 북경남-서대구#1T/L 7471 CB 장기미동작점검","2019-11-05 13:00","2019-11-05 15:00","2019-11-29 13:00","2019-11-29 15:00","당일"]
[215,"대구","칠곡","서대구S/S 서대구-선산#2T/L CB(7872)","서대구S/S 서대구-선산#2T/L 7872 CB 장기미동작점검","서대구S/S 서대구-선산#2T/L 7872 CB 장기미동작점검","2019-11-07 09:30","2019-11-07 12:00","2019-11-15 09:30","2019-11-15 12:00","당일"]
[216,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2019-11-28 08:00","2019-11-28 18:00","2019-11-28 08:00","2019-11-28 18:00","당일"]
[217,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2019-11-29 08:00","2019-11-29 18:00","2019-11-29 08:00","2019-11-29 18:00","당일"]
[218,"대구","칠곡","서대구S/S 서대구-고령#1T/L CB(7172)","서대구S/S 서대구-고령#1T/L 7172CB 장기미동작점검","서대구S/S 서대구-고령#1T/L 7172CB 장기미동작점검","2019-11-05 09:30","2019-11-05 12:00","2019-11-29 09:30","2019-11-29 12:00","당일"]
[219,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2019-11-18 08:00","2019-11-19 18:00","2019-11-18 08:00","2019-11-19 18:00","연속"]
[220,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2019-11-25 08:00","2019-11-27 18:00","2019-11-25 08:00","2019-11-27 18:00","연속"]
[221,"대구","칠곡","서대구S/S 북대구-서대구#2T/L CB(7772)","서대구S/S 북대구서대구#2T/L 7772 CB 장기미동작점검","서대구S/S 북대구서대구#2T/L 7772 CB 장기미동작점검","2019-11-07 13:00","2019-11-07 15:00","2019-11-15 13:00","2019-11-15 15:00","당일"]
[222,"대구","포항","신영일S/S #3 M.Tr 1차 TIE CB(7500)","신영일S/S 7500 GIS 조작시험","신영일S/S 7500 GIS 조작시험","2019-11-01 14:00","2019-11-01 18:00","2019-11-01 14:00","2019-11-01 18:00","당일"]
[223,"대구","포항","신영일안동CC T/L","345kv 신영일-안동CCT/L 계전기 성능개선","345kv 신영일-안동CCT/L 계전기 성능개선","2019-11-08 09:30","2019-11-08 18:00","취소","취소","당일"]
[224,"대구","포항","신포항신영일 T/L","신포항-신영일T/L 보호반 대체","신포항-신영일T/L 보호반 대체","2019-11-11 09:00","2019-11-15 18:00","취소","취소","연속"]
[225,"대구","포항","신영일S/S #3 M.Tr","신영일S/S 154kV 62-67 모선보호반 대체(TEST)","신영일S/S 154kV 62-67 모선보호반 대체(TEST)","2019-11-21 15:00","2019-11-21 15:30","2019-11-21 15:00","2019-11-21 15:30","당일"]
[226,"대구","포항","신영일S/S #4 M.Tr","신영일S/S 154kV 63-68 모선보호반 대체(TEST)","신영일S/S 154kV 63-68 모선보호반 대체(TEST)","2019-11-28 16:30","2019-11-28 17:00","2019-11-28 16:30","2019-11-28 17:00","당일"]
[227,"대구","포항","신영일S/S #3 M.Tr 1차 CB(7572)","신영일S/S 7572 GIS 조작시험","신영일S/S 7572 GIS 조작시험","2019-11-01 09:30","2019-11-01 14:00","2019-11-01 09:30","2019-11-01 14:00","당일"]
[228,"대구","포항","신월성N/P 신포항-신월성NP#3-#1M.Tr 2차 TIE CB(7400)","신월성 7400,7472 GIS 보통점검","신월성 7400,7472 GIS 보통점검","2019-11-25 09:30","2019-11-25 18:00","2019-11-25 09:30","2019-11-25 18:00","당일"]
[229,"대구","포항","신월성N/P #1M.Tr 1차 CB(7472)","신월성 7400,7472 GIS 보통점검","신월성 7400,7472 GIS 보통점검","2019-11-25 09:30","2019-11-25 18:00","2019-11-25 09:30","2019-11-25 18:00","당일"]
[230,"대구","포항","월성NP신월성NP#1T/L","월성연락#1T/L GIS 보통점검","신월성 7371 보통점검, 월성 7471 GIS 조작시험","2019-11-14 09:30","2019-11-14 18:00","2019-11-14 09:30","2019-11-14 18:00","당일"]
[231,"대구","포항","신월성N/P 신포항-신월성NP#3T/L CB(7471)","신월성 7471 GIS 보통점검","신월성 7471 GIS 보통점검","2019-11-07 09:30","2019-11-07 18:00","2019-11-07 09:30","2019-11-07 18:00","당일"]
[232,"대구","포항","신월성N/P #1SA.TR 1차 CB(7372)","신월성 7300,7372 GIS 보통점검","신월성 7300,7372 GIS 보통점검","2019-11-05 09:30","2019-11-05 18:00","2019-11-05 09:30","2019-11-05 18:00","당일"]
[233,"대구","포항","신월성N/P 월성연락#1T/L-#1SA.TR 1차 TIE CB(7300)","신월성 7300,7372 GIS 보통점검","신월성 7300,7372 GIS 보통점검","2019-11-05 09:30","2019-11-05 18:00","2019-11-05 09:30","2019-11-05 18:00","당일"]
[234,"대구","포항","신포항신월성NP#1 T/L","345kV 신포항-신월성#1TL 보호반 성능개선","345kV 신포항-신월성#1TL 보호반 성능개선","2019-11-19 09:00","2019-11-19 18:00","2019-11-19 09:00","2019-11-19 18:00","당일"]
[235,"대구","포항","신포항신월성NP#2 T/L","345kV 신포항-신월성#2TL 보호반 성능개선","345kV 신포항-신월성#2TL 보호반 성능개선","2019-11-20 09:00","2019-11-20 18:00","2019-11-20 09:00","2019-11-20 18:00","당일"]
[236,"대구","포항","신포항신월성NP#3 T/L","신포항S/S 신포항-신월성 #3T/L 계전기 성능개선","신포항S/S 신포항-신월성 #3T/L 계전기 성능개선","2019-11-27 09:00","2019-11-27 18:00","2019-11-27 09:00","2019-11-27 18:00","당일"]
[237,"대구","포항","월성2N/P #1 M.Tr 2차 CB(7272)","월성 7272 GIS 조작시험","월성 7272 GIS 보통점검","2019-11-18 14:00","2019-11-18 18:00","2019-11-18 14:00","2019-11-18 18:00","당일"]
[238,"대구","포항","월성2N/P 울주-월성#2T/L-#1 M.Tr 2차 CB(7200)","월성 7200 GIS 조작시험","월성 7200GIS 조작시험","2019-11-18 09:30","2019-11-18 14:00","2019-11-18 09:30","2019-11-18 14:00","당일"]
[239,"대구","포항","월성2N/P 울주-월성N/P #1T/L CB(7571)","월성 7571 GIS 조작시험","월성 7571 GIS 조작시험","2019-11-15 14:00","2019-11-15 18:00","2019-11-15 14:00","2019-11-15 18:00","당일"]
[240,"대구","포항","월성2N/P #1 SS TR 1차 CB(7671)","월성 7671 GIS 조작시험","월성 7671 GIS 조작시험","2019-11-15 09:30","2019-11-15 14:00","2019-11-15 09:30","2019-11-15 14:00","당일"]
[241,"대구","포항","동울산월성NP#1 T/L","월성 동울산-월성#1T/L 계전기 성능개선","월성 동울산-월성#1T/L 계전기 성능개선","2019-11-06 09:30","2019-11-06 18:00","2019-11-06 09:30","2019-11-06 18:00","당일"]
[242,"대구","포항","월성2N/P 동울산-월성NP#1T/L CB(7771)","월성 7771 GIS 조작시험","월성 7771 GIS 조작시험","2019-11-08 09:30","2019-11-08 14:00","2019-11-08 09:30","2019-11-08 14:00","당일"]
[243,"대구","포항","월성2N/P 울주-월성N/P #2T/L CB(7271)","월성 7271 GIS 조작시험","월성 7271 GIS 조작시험","2019-11-08 14:00","2019-11-08 18:00","2019-11-08 14:00","2019-11-08 18:00","당일"]
[244,"경북","구미","선산S/S 345kV #75 BUS","345kV 현대제 GIS 접지개폐기 개선작업","- 345kV 현대제 GIS 접지개폐기 구속핀 걸림량 부족 방지를 위한 개선작업","2019-11-07 14:00","2019-11-07 18:00","2019-11-07 14:00","2019-11-07 18:00","당일"]
[245,"경북","구미","선산S/S 345kV #70 BUS","345kV 현대제 GIS 접지개폐기 개선작업","- 345kV 현대제 GIS 접지개폐기 구속핀 걸림량 부족 방지를 위한 개선작업","2019-11-07 09:00","2019-11-07 14:00","2019-11-07 09:00","2019-11-07 14:00","당일"]
[246,"경북","영주","삼척GP한울NP #2 T/L","YPP 계전기 성능개선","YPP 계전기 성능개선","2019-11-07 13:00","2019-11-07 18:00","취소","취소","당일"]
[247,"경북","영주","삼척GP한울NP #1 T/L","YPP 계전기 성능개선","YPP 계전기 성능개선","2019-11-07 09:00","2019-11-07 13:00","2019-11-07 09:00","2019-11-07 13:00","당일"]
[248,"경북","영주","한울1NP한울2NP#2 T/L","YPP 계전기 성능개선","YPP 계전기 성능개선","2019-11-12 13:00","2019-11-12 18:00","취소","취소","당일"]
[249,"경북","영주","한울1NP한울2NP#1 T/L","YPP 계전기 성능개선","YPP 계전기 성능개선","2019-11-12 09:00","2019-11-12 13:00","2019-11-12 09:00","2019-11-12 13:00","당일"]
[250,"경북","영주","한울2NP한울3NP#3 T/L","YPP 계전기 성능개선","YPP 계전기 성능개선","2019-11-08 09:00","2019-11-08 13:00","2019-11-08 09:00","2019-11-08 13:00","당일"]
[251,"경북","영주","신태백한울NP#1 T/L","YPP 계전기 성능개선","YPP 계전기 성능개선","2019-11-11 09:00","2019-11-11 13:00","취소","취소","당일"]
[252,"경북","영주","신태백한울NP#2 T/L","YPP 계전기 성능개선","YPP 계전기 성능개선","2019-11-11 13:00","2019-11-11 18:00","취소","취소","당일"]
[253,"경북","영주","한울2NP한울3NP#4 T/L","YPP 계전기 성능개선","YPP 계전기 성능개선","2019-11-08 13:00","2019-11-08 18:00","취소","취소","당일"]
[254,"경북","직할","신영일안동CC T/L","'19년 경북직할 가공송전선로 위탁공사 정밀점검","345kV 신영일-안동CC T/L 정밀점검 및 항공장애표시구 설치공사","2019-11-18 08:00","2019-11-22 18:00","취소","취소","연속"]
[255,"경북","직할","안동C/C #1 M.Tr 1차 GIS(7171)","18~19년 경북본부 직할 변전정비회사 총액공사","1차 GIS 조작시험","2019-11-06 12:00","2019-11-06 16:00","2019-11-06 12:00","2019-11-06 16:00","당일"]
[256,"경북","직할","안동C/C #1 M.Tr TIE GIS(7100)","18~19년 경북본부 직할 변전정비회사 총액공사","1차 GIS 조작시험","2019-11-06 09:00","2019-11-06 12:00","2019-11-06 09:00","2019-11-06 12:00","당일"]
[257,"경북","직할","안동C/C #1 Tie-Tr","18~19년 경북본부 직할 변전정비회사 총액공사","#1M.Tr 초기점검, 2차 GIS 조작시험, 시험팀 성능개선작업","2019-11-05 09:00","2019-11-05 18:00","2019-11-05 09:00","2019-11-05 18:00","당일"]
[258,"부산울산","동부산","고리2N/P 345kV #76 BUS","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 362kV 7500,7572GIS 구조개선관련 시험가압(#76BUS)","2019-11-29 18:00","2019-11-30 18:00","2019-11-29 18:00","2019-11-30 18:00","연속"]
[259,"부산울산","동부산","신양산S/S #2 M.Tr","신양산E/C 170kV GCB 차단기 동작시험","신양산E/C 170kV GCB 차단기 동작시험(#2M.Tr)","2019-11-01 09:30","2019-11-01 14:00","2019-11-13 09:30","2019-11-13 14:00","당일"]
[260,"부산울산","동부산","신양산신대연#1 T/L","신양산E/C 345kV 송전선로보호반 성능개선","신양산E/C 345kV 송전선로보호반 성능개선(신양산-신대연#1T/L)","2019-11-12 09:30","2019-11-12 18:00","2019-11-12 09:30","2019-11-12 18:00","당일"]
[261,"부산울산","동부산","신양산고리NP#1 T/L","345㎸ 신양산-고리NP T/L OPGW 증설공사","345㎸ 신양산-고리NP#1T/L OPGW 23.05㎞(120SQ/48C) 증설, S/T↔ICT실간 비금속광케이블 0.305㎞ 등 부대설비 1식","2019-11-04 07:00","2019-11-10 18:00","2019-11-04 07:00","2019-11-17 18:00","연속"]
[262,"부산울산","북부산","북부산S/S #4 M.Tr","2019년 북부산 변전협력회사 총액공사","북부산E/C 345kV #4M.Tr 2차측 GIS 차단기 조작시험","2019-11-20 14:00","2019-11-20 18:00","2019-11-20 14:00","2019-11-20 18:00","당일"]
[263,"부산울산","북부산","북부산S/S 신김해-북부산#2T/L CB((신)7471)","2019년 북부산 변전협력회사 총액공사","북부산E/C 345kV 신김해-북부산#2T/L 7471GIS 초기점검","2019-11-12 09:00","2019-11-12 18:00","2019-11-12 09:00","2019-11-12 18:00","당일"]
[264,"부산울산","북부산","북부산S/S #3 M.Tr","2019년 북부산 변전협력회사 총액공사","북부산E/C 345kV #3M.Tr 2차측 GIS 차단기 조작시험","2019-11-20 10:00","2019-11-20 14:00","2019-11-20 10:00","2019-11-20 14:00","당일"]
[265,"부산울산","서부산","서부산S/S 345kV #1 Sh.R","서부산E/C 345kV #1Sh.R 수냉각PNL 교체","서부산E/C 345kV #1Sh.R 수냉각PNL 교체","2019-11-04 10:00","2019-11-10 18:00","2019-11-04 10:00","2019-11-10 18:00","연속"]
[266,"부산울산","서부산","서부산S/S 345kV #2 Sh.R","서부산E/C 345kV #2Sh.R 수냉각PNL 교체","서부산E/C 345kV #2Sh.R 수냉각PNL 교체","2019-11-11 10:00","2019-11-17 18:00","2019-11-11 10:00","2019-11-17 18:00","연속"]
[267,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산E/C 345kV #3M.Tr 보호PNL 성능개선(유호)","신녹산E/C 345kV #3M.Tr 보호PNL 성능개선(유호)","2019-11-15 10:00","2019-11-15 18:00","2019-11-13 10:00","2019-11-13 18:00","당일"]
[268,"부산울산","울산","동울산월성NP#1 T/L","YPP제 345kV 송전선로 보호반 성능개선작업","동울산E/C 345kV 동울산-월성NP#1 T/L YPP제 송전선로 보호반 성능개선","2019-11-12 09:00","2019-11-13 18:00","2019-11-12 09:00","2019-11-13 18:00","연속"]
[269,"부산울산","울산","신온산S/S #2 M.Tr","18~19년 변전협력 총액공사","- 신온산E/C 345kV #74BAY B/F PNL 교체작업","2019-11-25 09:00","2019-11-29 18:00","취소","취소","연속"]
[270,"부산울산","울산","신온산울산TP T/L","18~19년 변전협력 총액공사","- 울산복합S/Y 345kV 76Bay B/F PNL 교체작업 - 신온산S/S 345kV 74BAY B/F PNL 교체작업 - 울산복합측 7671GIS 보통점검","2019-11-25 09:00","2019-11-29 18:00","취소","취소","연속"]
[271,"부산울산","울산","북부산울산TP T/L","18~19년 변전협력 총액공사","- 울산복합S/Y 345kV 75Bay B/F PNL 교체작업","2019-11-04 09:00","2019-11-08 18:00","취소","취소","연속"]
[272,"부산울산","울산","울산C/C #3 Tie-Tr","18~19년 변전협력 총액공사","- 울산복합 345kV #3M.Tr A상 1,2차 부싱 절연유 채유","2019-10-22 09:00","2019-10-22 18:00","취소","취소","당일"]
[273,"부산울산","울산","울산C/C #2 Tie-Tr","18~19년 변전협력 총액공사","- 울산복합 345kV #2M.Tr A상 1,2차 부싱 절연유 채유","2019-10-21 09:00","2019-10-21 18:00","취소","취소","당일"]
[274,"부산울산","울산","울산C/C #1 Tie-Tr","18~19년 변전협력 총액공사","- 울산복합 345kV #1M.Tr A상 1,2차 부싱 절연유 채유","2019-10-19 09:00","2019-10-19 18:00","취소","취소","당일"]
[275,"부산울산","울산","울주고리NP#1 T/L","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 362kV 7B00,7B72GIS 구조개선관련 시험가압(울주-고리#1T/L)","2019-11-01 18:00","2019-11-02 18:00","2019-11-15 18:00","2019-11-16 18:00","연속"]
[276,"부산울산","울산","울주고리NP#2 T/L","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 362kV 7C72,7C00 GIS 구조개선관련 시험가압(울주-고리#2T/L)","2019-11-15 18:00","2019-11-16 18:00","2019-11-01 18:00","2019-11-02 18:00","연속"]
[277,"부산울산","직할","신대연S/S 345kV #2 Sh.R","2019년 직할 변전협력회사 총액공사","- 신대연E/C #2Sh.R 초기점검","2019-11-05 10:00","2019-11-05 18:00","2019-11-05 10:00","2019-11-05 18:00","당일"]
[278,"경남","직할","신김해S/S #3 M.Tr","신김해S/S 345kV #3M.Tr 1차 CB 조작시험","신김해S/S 345kV #3M.Tr 1차 CB 조작시험","2019-11-01 09:30","2019-11-01 17:30","2019-11-01 09:30","2019-11-01 17:30","당일"]
[279,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산T/L 78호 지장송전선로 이설공사","345kV 신김해-북부산T/L 77~81호 간 지장이설공사[본탑 1기, 계탑 1기]","2019-11-22 07:00","2019-12-02 18:00","취소","취소","연속"]
[280,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산T/L 78호 지장송전선로 이설공사","345kV 신김해-북부산T/L 77~81호 간 지장이설공사[본탑 1기, 계탑 1기]","2019-11-11 07:00","2019-11-21 18:00","취소","취소","연속"]
[281,"경남","직할","신김해S/S #1 M.Tr","신김해S/S 345kV #73BAY B/F PNL 대체공사","신김해S/S 345kV #73BAY B/F PNL 대체공사","2019-11-25 09:30","2019-11-29 17:30","2019-11-25 09:30","2019-11-29 17:30","연속"]
[282,"경남","직할","신김해창원#2 T/L","창원S/S 345kV 신김해-창원#2T/L CB 조작시험","창원S/S 345kV 신김해-창원#2T/L, #74BAY TIE CB 조작시험 (병행)신김해S/S 345kV 신김해-창원#2T/L, #72BAY TIE CB 조작시험","2019-11-08 09:30","2019-11-08 17:30","2019-11-08 09:30","2019-11-08 17:30","연속"]
[283,"경남","직할","창원S/S #3 M.Tr","창원S/S 154kV #3Sh.C CB 정밀점검","창원S/S 154kV #3Sh.C CB 정밀점검 시험가압선로 : #3M.Tr, #66BUS","2019-11-12 16:00","2019-11-13 18:00","2019-11-12 16:00","2019-11-13 18:00","연속"]
[284,"경남","직할","창원S/S #3 M.Tr","창원S/S 154kV #4Sh.C CB 정밀점검","창원S/S 154kV #4Sh.C CB 정밀점검 시험가압선로 : #3M.Tr, #66BUS","2019-11-26 16:00","2019-11-27 18:00","2019-11-26 16:00","2019-11-27 18:00","연속"]
[285,"경남","진주","의령신마산#1 T/L","의령S/S 의령-신마산#1T/L-TIE 79Bay B/F PNL 대체","의령S/S 의령-신마산#1T/L-TIE 79Bay B/F PNL 대체","2019-11-04 09:00","2019-11-08 18:00","2019-11-04 09:00","2019-11-08 18:00","연속"]
[286,"경남","진주","의령S/S #75-#76 SEC CB","의령S/S 345kV B/S(#70-71,#75-76)B/F PNL 대체","의령S/S 345kV B/S(#70-71,#75-76)B/F PNL 대체","2019-11-25 09:00","2019-11-29 18:00","취소","취소","연속"]
[287,"경남","진주","의령S/S #70-#71 SEC CB","의령S/S 345kV B/S(#70-71,#75-76)B/F PNL 대체","의령S/S 345kV B/S(#70-71,#75-76)B/F PNL 대체","2019-11-25 09:00","2019-11-29 18:00","취소","취소","연속"]
[288,"경남","진주","신남원의령#2 T/L","의령S/S 신남원-의령#2T/L-TIE 77 Bay B/F PNL 대체","의령S/S 신남원-의령#2T/L-TIE 77 Bay B/F PNL 대체","2019-11-11 09:00","2019-11-15 18:00","2019-11-11 09:00","2019-11-15 18:00","연속"]
[289,"경남","통영","삼천포T/P 창원-삼천포화력#1T/L CB(7572)","구)삼천포T/P 창원-삼천포화력#T/L GIS(7572) 조작시험","구)삼천포T/P 창원-삼천포화력#T/L GIS(7572) 조작시험","2019-11-05 09:30","2019-11-05 18:00","2019-11-05 09:30","2019-11-05 18:00","당일"]
[290,"경남","통영","(신)신고성S/S 삼천포-TIE#2T/L CB(7472)","(신)신고성S/S 345kV CB(7472) GIS 초기점검","(신)신고성S/S 345kV CB(7472) GIS 초기점검","2019-11-04 09:30","2019-11-04 18:00","2019-11-04 09:30","2019-11-04 18:00","당일"]
[291,"경남","통영","신고성S/S #2 M.Tr","신고성S/S 345kV #2M.Tr OLTC 상부카바 보수","신고성S/S 345kV #2M.Tr OLTC 상부카바 보수","2019-11-20 09:30","2019-11-20 18:00","2019-11-20 09:30","2019-11-20 18:00","당일"]
[292,"경남","통영","(신)삼천포T/P #75-#76 SEC CB","(신)신고성S/S 345kV CB(75-76) 조작시험","(신)신고성S/S 345kV CB(75-76) 조작시험","2019-11-05 09:30","2019-11-05 18:00","2019-11-05 09:30","2019-11-05 18:00","당일"]
[293,"경남","함안","신마산삼천포화력#2 T/L","345kV 신마산-삼천포화력 #2 T/L 정밀점검","1~177호 정밀점검","2019-11-04 08:30","2019-11-12 18:00","2019-11-04 08:30","2019-11-12 18:00","매일"]
[294,"경남","함안","신마산삼천포화력#1 T/L","345kV 신마산-삼천포화력 #1 T/L 정밀점검","1~177호 정밀점검","2019-11-20 08:30","2019-11-29 18:00","2019-11-20 08:30","2019-11-29 18:00","매일"]
[295,"경남","함안","신마산S/S #5 M.Tr 1차 GIS(7572)","신마산S/S 345kV #5M.Tr 1차 GIS 7572 초기점검","신마산S/S 345kV #5M.Tr 1차 GIS 7572 초기점검","2019-11-01 09:30","2019-11-01 17:30","2019-11-01 09:30","2019-11-01 17:30","당일"]
[296,"대구",null,"신월성1호기 대기보조변압기 CB(7300,7372)","신월성1호기 5차 계획예방정비\n#1 대기보조변압기(SAT) 점검\n* 조작차단기 : CB 7300, 7372","○ SAT 일반점검 등","2019-11-01 09:00","2019-11-16 18:00","2019-11-01 09:00","2019-11-16 18:00","연속"]
[297,"대구",null,"신월성1호기 주변압기 CB(7400,7472)","신월성1호기 5차 계획예방정비\n#1 MTR/UAT/EXTR 점검\n* 조작차단기 : CB 7400, 7472","○ MTR/UAT/EXTR 일반점검 등","2019-11-18 09:00","2019-12-10 18:00","2019-11-18 09:00","2019-12-10 18:00","연속"]
[298,"경북",null,"한울3호기 주변압기 CB(7900,7972)","3호기 15차 계획예방정비 소내전원 절체시험\n* 조작차단기 : CB 7900, 7972","○ 소내전원 절체시험\n- 절체시험 후 개방차단기 재투입","2019-11-04 10:00","2019-11-04 18:00","2019-11-04 10:00","2019-11-04 18:00","연속"]
[299,"경북",null,"한울5호기 대기보조변압기 CB(7E00,7E72)","5호기 11차 계획예방정비\n* 조작차단기 : CB 7E00, 7E72","대기보조변압기 일반점검 ","2019-11-05 10:00","2019-11-22 15:00","2019-11-05 10:00","2019-11-22 15:00","연속"]
[300,"경북",null,"한울5호기 주변압기 CB(7D00,7D72)","5호기 11차 계획예방정비\n* 조작차단기 : CB 7D00, 7D72","소내전원 절체(UAT→SAT)시험","2019-11-30 10:00","2019-11-30 16:00","2019-11-30 10:00","2019-11-30 16:00","연속"]
[301,"부산울산",null,"고리3호기\n기동변압기#1 CB(7500,7572)","공사명 : 기동변압기#1 휴전\n조작차단기 : 7500, 7572","○ 기동변압기 교체공사","2019-11-14 08:00","2020-01-03 23:00","2019-11-14 08:00","2020-01-03 23:00","연속"]
[302,"전북",null,"신김제S/S 7171 CB","차단기 정밀점검 공사","차단기 정밀점검 공사","2019-11-04 08:00","2019-11-11 08:00","2019-11-04 08:00","2019-11-11 08:00","연속"]
[303,"전북",null,"신김제S/S 7271 CB","차단기 정밀점검 공사","차단기 정밀점검 공사","2019-11-11 08:00","2019-11-17 18:00","2019-11-11 08:00","2019-11-17 18:00","연속"]
[304,"전북",null,"신김제S/S 345kV #1 BUS","차단기 정밀점검 공사 시험가압","차단기 정밀점검 공사 시험가압","2019-11-09 18:00","2019-11-11 08:00","2019-11-09 18:00","2019-11-11 08:00","연속"]
[305,"전북",null,"신김제S/S 345kV #1 BUS","차단기 정밀점검 공사 시험가압","차단기 정밀점검 공사 시험가압","2019-11-16 09:00","2019-11-17 18:00","2019-11-16 09:00","2019-11-17 18:00","연속"]
[306,"강원",null,"양양양수1호기 주변압기 CB(7100,7172)","계획예방정비","계획예방정비","2019-11-04 09:00","2019-11-24 24:00","2019-11-04 09:00","2019-11-24 24:00","연속"]
[307,"경북",null,"예천양수2호기 주변압기 CB(7271,7200)","배수작업","배수작업","2019-11-02 08:00","2019-11-13 24:00","2019-11-02 08:00","2019-11-13 24:00","연속"]
[308,"경북",null,"예천양수1호기 주변압기 CB(7100,7172)","계획예방정비","계획예방정비","2019-11-04 09:00","2020-02-09 24:00","2019-11-04 09:00","2020-02-09 24:00","연속"]

{"sheet":"154송부","index":3,"n_rows":618,"n_cols":13,"rows_kept":618,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 11월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","금오상계#1 T/L","2019년도 가공송전 순시점검 위탁공사(서울본부)","송전선로 정밀점검 : No.36∼54(14기)","2019-11-04 09:00","2019-11-05 18:00","2019-11-04 09:00","2019-11-05 18:00","연속"]
[2,"서울","성동","금오상계#2 T/L","2019년도 가공송전 순시점검 위탁공사(서울본부)","송전선로 정밀점검 : No.36∼54(14기)","2019-11-06 09:00","2019-11-07 18:00","2019-11-06 09:00","2019-11-07 18:00","연속"]
[3,"서울","성동","양주쌍문#2 T/L","19년 성동P/O 관내 154kV 차단기 조작시험","154kV GIS 조작시험 (차단기 개폐타임 측정)","2019-11-07 10:00","2019-11-07 16:00","2019-11-09 10:00","2019-11-09 16:00","당일"]
[4,"서울","성동","화양성수 T/L","19년 성동P/O 관내 154kV 차단기 조작시험","154kV GIS 조작시험 (차단기 개폐타임 측정)","2019-11-06 10:00","2019-11-06 16:00","2019-11-11 10:00","2019-11-11 16:00","당일"]
[5,"서울","성동","미금화양 T/L","19년 성동P/O 관내 154kV 차단기 조작시험","154kV GIS 조작시험 (차단기 개폐타임 측정)","2019-11-05 10:00","2019-11-05 16:00","2019-11-05 10:00","2019-11-05 16:00","당일"]
[6,"서울","중부","동빙고S/S 154kV #65 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 154kV #2BUS PT 보통점검","2019-11-08 14:00","2019-11-08 18:00","2019-11-08 14:00","2019-11-08 18:00","당일"]
[7,"서울","중부","동빙고S/S 154kV #60 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 154kV #1BUS PT 보통점검","2019-11-08 10:00","2019-11-08 14:00","2019-11-08 10:00","2019-11-08 14:00","당일"]
[8,"서울","중부","상암S/S 154kV #60 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사(#3M.Tr 1차 시험가압용)","2019-11-27 17:00","2019-11-27 18:00","2019-11-27 17:00","2019-11-27 18:00","당일"]
[9,"서울","중부","수색상암#1 T/L","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사(#3M.Tr 1차 시험가압용)","2019-11-27 17:00","2019-11-27 18:00","2019-11-27 17:00","2019-11-27 18:00","당일"]
[10,"서울","중부","수색상암#2 T/L","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-11-28 09:00","2019-11-30 18:00","2019-11-28 09:00","2019-11-30 18:00","연속"]
[11,"서울","중부","수색S/S 154kV #65 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색중부#1T/L #1, 2DS 및 Line DS 보통점검","2019-11-24 14:00","2019-11-24 18:00","2019-11-24 14:00","2019-11-24 18:00","당일"]
[12,"서울","중부","수색S/S 154kV #60 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 중부수색#1T/L #1, 2DS 및 Line DS 보통점검","2019-11-24 10:00","2019-11-24 14:00","2019-11-24 10:00","2019-11-24 14:00","당일"]
[13,"서울","중부","수색S/S 154kV #60-#65 BUS TIE CB","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사","2019-11-21 09:00","2019-11-23 18:00","2019-11-21 09:00","2019-11-23 18:00","연속"]
[14,"서울","중부","수색S/S 154kV #65 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사(수색은평#2T/L 시험가압용)","2019-11-16 17:00","2019-11-16 18:00","취소","취소","연속"]
[15,"서울","중부","수색S/S 154kV #65 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색중부#2T/L #1, 2DS 및 Line DS 보통점검","2019-11-16 14:00","2019-11-16 18:00","2019-11-16 14:00","2019-11-16 18:00","당일"]
[16,"서울","중부","수색S/S 154kV #60 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 수색중부#2T/L #1, 2DS 및 Line DS 보통점검","2019-11-16 10:00","2019-11-16 14:00","2019-11-16 10:00","2019-11-16 14:00","당일"]
[17,"서울","중부","수색S/S 154kV #60 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 원흥수색#1T/L #1, 2DS 및 Line DS 보통점검","2019-11-09 10:00","2019-11-09 14:00","2019-11-09 10:00","2019-11-09 14:00","당일"]
[18,"서울","중부","수색S/S 154kV #65 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ 수색S/S 154kV 원흥수색#1T/L #1, 2DS 및 Line DS 보통점검","2019-11-09 14:00","2019-11-09 18:00","2019-11-09 14:00","2019-11-09 18:00","당일"]
[19,"서울","중부","수색S/S 154kV #65 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사(수색상암#2T/L 시험가압용)","2019-11-30 17:00","2019-11-30 18:00","2019-11-30 17:00","2019-11-30 18:00","연속"]
[20,"서울","중부","수색S/S 154kV #65 BUS","2019년 중부P/O 170kV 정밀점검공사","ㅇ 2019년 중부P/O 170kV 정밀점검공사(BUS TIE CB 시험가압용)","2019-11-23 17:00","2019-11-23 18:00","2019-11-23 17:00","2019-11-23 18:00","연속"]
[21,"서울","중부","용산S/S 154kV #65 BUS","마포,용산E/C 154kV SW 증설공사","- 용산E/C 170kV GIS 1CCT 증설 - 마포E/C 170kV GIS 1CCT 증설","2019-11-11 08:00","2019-11-14 16:00","2019-11-11 08:00","2019-11-14 16:00","연속"]
[22,"서울","중부","용산S/S 154kV #60 BUS","마포,용산E/C 154kV SW 증설공사","- 용산E/C 170kV GIS 1CCT 증설 - 마포E/C 170kV GIS 1CCT 증설","2019-11-15 14:00","2019-11-15 16:00","2019-11-15 14:00","2019-11-15 16:00","당일"]
[23,"서울","중부","중부용산#1 T/L","마포,용산E/C 154kV SW 증설공사","- 용산E/C 170kV GIS 1CCT 증설 - 마포E/C 170kV GIS 1CCT 증설","2019-11-13 16:00","2019-11-14 16:00","2019-11-13 16:00","2019-11-14 16:00","연속"]
[24,"서울","중부","용산S/S 154kV #60 BUS","마포,용산E/C 154kV SW 증설공사","- 용산E/C 170kV GIS 1CCT 증설 - 마포E/C 170kV GIS 1CCT 증설","2019-11-04 08:00","2019-11-08 16:00","2019-11-04 08:00","2019-11-08 16:00","연속"]
[25,"서울","중부","중부용산#1 T/L","마포,용산E/C 154kV SW 증설공사","- 용산E/C 170kV GIS 1CCT 증설 - 마포E/C 170kV GIS 1CCT 증설","2019-11-07 16:00","2019-11-08 16:00","2019-11-07 16:00","2019-11-08 16:00","연속"]
[26,"서울","중부","은평S/S 154kV #65 BUS","은평S/S 170kV GIS 대체공사(2차분)","은평S/S 170kV GIS 대체공사(2차분) - 수색은평#2T/L, #4M.Tr 1차 GIS","2019-11-06 13:00","2019-11-18 10:00","2019-11-04 09:00","2019-11-18 10:00","연속"]
[27,"서울","중부","중부S/S 154kV #61 BUS","2019년 중부P/O 170kV 정밀점검공사","2019년 중부P/O 170kV 정밀점검공사(#3M.Tr 2차 시험가압용)","2019-11-08 17:00","2019-11-08 18:00","2019-11-08 17:00","2019-11-08 18:00","연속"]
[28,"서울","중부","중부S/S 154kV #61-#66 BUS TIE GIS","19년 중부전력지사 변전협력회사 총액공사","ㅇ154kV #61-#66 BUSTIE GIS 내부점검","2019-11-04 10:00","2019-11-05 18:00","2019-11-04 10:00","2019-11-05 18:00","연속"]
[29,"서울","중부","중부S/S 154kV #66 BUS","19년 중부전력지사 변전협력회사 총액공사","ㅇ154kV #61-#66 BUSTIE GIS 내부점검(시험가압)","2019-11-05 17:00","2019-11-05 18:00","2019-11-05 17:00","2019-11-05 18:00","당일"]
[30,"남서울","강남","역삼S/S 154kV #60-#65 BUS TIE CB","170kV GIS 개폐타임측정","170kV GIS 개폐타임측정","2019-11-01 09:00","2019-11-01 18:00","2019-11-01 09:00","2019-11-01 18:00","당일"]
[31,"남서울","동서울","강동풍납#2 T/L","송전선로 보호반 교체공사","송전선로 보호반 교체공사","2019-11-01 09:00","2019-11-04 18:00","2019-11-01 09:00","2019-11-04 18:00","연속"]
[32,"남서울","동서울","동서울가락#2 T/L","동서울S/S 154kV 현대화 공사","○ 전력구 흙막이 작업(H-Beam Filing)","2019-11-06 08:30","2019-11-06 17:00","2019-11-06 08:30","2019-11-06 17:00","당일"]
[33,"남서울","동서울","동서울가락#1 T/L","동서울S/S 154kV 현대화 공사","○ 전력구 흙막이 작업(H-Beam Filing)","2019-11-07 08:30","2019-11-07 17:00","2019-11-07 08:30","2019-11-07 17:00","당일"]
[34,"남서울","동서울","동서울송파#2 T/L","동서울S/S 154kV 현대화 공사","○ 전력구 흙막이 작업(H-Beam Filing)","2019-11-08 18:30","2019-11-08 17:00","2019-11-08 18:30","2019-11-08 17:00","당일"]
[35,"남서울","동서울","동서울서종#2 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-11-15 08:30","2019-11-16 17:00","2019-11-15 08:30","2019-11-16 17:00","연속"]
[36,"남서울","동서울","동서울신장#1 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-11-15 08:30","2019-11-16 17:00","2019-11-15 08:30","2019-11-16 17:00","연속"]
[37,"남서울","동서울","동서울서종#1 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-11-18 08:30","2019-11-19 17:00","2019-11-18 08:30","2019-11-19 17:00","연속"]
[38,"남서울","동서울","동서울신장#2 T/L","동서울S/S 154kV 현대화 공사","○ T-BUS DS철거 및 인출Lead 직결 ○ LA 및 CVT 이설","2019-11-01 08:30","2019-11-02 17:00","2019-11-01 08:30","2019-11-02 17:00","연속"]
[39,"남서울","동서울","동서울송파#1 T/L","동서울S/S 154kV 현대화 공사","○ 전력구 흙막이 작업(H-Beam Filing)","2019-11-11 08:30","2019-11-11 17:00","2019-11-11 08:30","2019-11-11 17:00","당일"]
[40,"남서울","영등포","가양S/S 154kV #60 BUS","가양S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-08 10:00","2019-11-08 11:00","취소","취소","당일"]
[41,"남서울","영등포","가양S/S 154kV #65 BUS","가양S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-08 11:00","2019-11-08 12:00","취소","취소","당일"]
[42,"남서울","영등포","구공S/S 154kV #65 BUS","구공S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-12 10:00","2019-11-12 11:00","2019-11-12 10:00","2019-11-12 11:00","당일"]
[43,"남서울","영등포","구공S/S 154kV #60 BUS","구공S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-12 09:00","2019-11-12 10:00","2019-11-12 09:00","2019-11-12 10:00","당일"]
[44,"남서울","영등포","천왕구로#2 T/L","전철T/L GIS 무부하가압용","정밀점검 무부하가압용","2019-11-19 16:00","2019-11-19 17:00","2019-11-19 16:00","2019-11-19 17:00","당일"]
[45,"남서울","영등포","구로S/S 154kV #65 BUS","구로S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-04 10:00","2019-11-04 11:00","2019-11-04 10:00","2019-11-04 11:00","당일"]
[46,"남서울","영등포","구로S/S 154kV #65 BUS","전철T/L GIS 무부하가압용","정밀점검 무부하가압용","2019-11-19 16:00","2019-11-19 17:00","2019-11-19 16:00","2019-11-19 17:00","당일"]
[47,"남서울","영등포","구로S/S 154kV #60 BUS","구로S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-04 09:00","2019-11-04 10:00","2019-11-04 09:00","2019-11-04 10:00","당일"]
[48,"남서울","영등포","대방S/S 154kV #60 BUS","대방S/S 170kV GIS 정밀점검공사","#1M.Tr 무부하가압용","2019-11-12 16:00","2019-11-12 17:00","2019-11-12 16:00","2019-11-12 17:00","당일"]
[49,"남서울","영등포","독산대방#1 T/L","대방S/S 170kV GIS 정밀점검공사","#1M.Tr 무부하가압용","2019-11-12 16:00","2019-11-12 17:00","2019-11-12 16:00","2019-11-12 17:00","당일"]
[50,"남서울","영등포","대방S/S 154kV #65 BUS","대방S/S 170kV GIS 정밀점검공사","#2M.Tr 무부하가압용","2019-11-16 16:00","2019-11-16 17:00","2019-11-16 16:00","2019-11-16 17:00","당일"]
[51,"남서울","영등포","독산대방#2 T/L","대방S/S 170kV GIS 정밀점검공사","#2M.Tr 무부하가압용","2019-11-16 16:00","2019-11-16 17:00","2019-11-16 16:00","2019-11-16 17:00","당일"]
[52,"남서울","영등포","독산대방#1 T/L","대방S/S 170kV GIS 정밀점검공사","#3M.Tr 무부하가압용","2019-11-23 16:00","2019-11-23 17:00","2019-11-23 16:00","2019-11-23 17:00","당일"]
[53,"남서울","영등포","대방S/S 154kV #60 BUS","대방S/S 170kV GIS 정밀점검공사","#3M.Tr 무부하가압용","2019-11-23 16:00","2019-11-23 17:00","2019-11-23 16:00","2019-11-23 17:00","당일"]
[54,"남서울","영등포","독산대방#1 T/L","대방S/S 170kV GIS 정밀점검공사","#6100 BUSTIE 무부하가압용","2019-11-29 16:00","2019-11-29 17:00","2019-11-29 16:00","2019-11-29 17:00","당일"]
[55,"남서울","영등포","대방S/S 154kV #60 BUS","대방S/S 170kV GIS 정밀점검공사","#6100 BUSTIE 무부하가압용","2019-11-29 16:00","2019-11-29 17:00","2019-11-29 16:00","2019-11-29 17:00","당일"]
[56,"남서울","영등포","시흥독산#2 T/L","독산S/S 170kV GIS 에어드레인밸브 점검","170kV GIS 에어드레인밸브 점검","2019-11-01 09:00","2019-11-01 18:00","2019-11-04 09:00","2019-11-04 18:00","당일"]
[57,"남서울","영등포","등촌S/S 154kV #65 BUS","등촌S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-15 10:00","2019-11-15 11:00","취소","취소","당일"]
[58,"남서울","영등포","등촌S/S 154kV #60 BUS","등촌S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-15 09:00","2019-11-15 10:00","취소","취소","당일"]
[59,"남서울","영등포","당인리목동#1 T/L","목동S/S 170kV GIS 조작시험","- 차단기 개폐타임 측정","2019-11-20 10:00","2019-11-20 12:00","2019-11-20 10:00","2019-11-20 12:00","당일"]
[60,"남서울","영등포","신정목동#1 T/L","신정S/S 170kV GIS 정밀점검공사","-#1M.Tr 무부하 가압용","2019-11-01 16:00","2019-11-01 17:00","2019-11-01 16:00","2019-11-01 17:00","당일"]
[61,"남서울","영등포","신정S/S 154kV #60 BUS","신정S/S 170kV GIS 정밀점검공사","-#1M.Tr 무부하 가압용","2019-11-01 16:00","2019-11-01 17:00","2019-11-01 16:00","2019-11-01 17:00","당일"]
[62,"남서울","영등포","신정S/S 154kV #65 BUS","신정S/S #2M.Tr 1차 170kV GIS 정밀점검공사","#2M.Tr 1차 무부하가압용","2019-11-05 16:00","2019-11-05 17:00","2019-11-05 16:00","2019-11-05 17:00","당일"]
[63,"남서울","영등포","신정목동#2 T/L","신정S/S #2M.Tr 1차 170kV GIS 정밀점검공사","#2M.Tr 1차 무부하가압용","2019-11-05 16:00","2019-11-05 17:00","2019-11-05 16:00","2019-11-05 17:00","당일"]
[64,"남서울","영등포","천왕S/S 154kV #60 BUS","천왕S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-05 10:00","2019-11-05 11:00","2019-11-05 10:00","2019-11-05 11:00","당일"]
[65,"남서울","영등포","천왕S/S 154kV #65 BUS","천왕S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-05 11:00","2019-11-05 12:00","2019-11-05 11:00","2019-11-05 12:00","당일"]
[66,"남서울","영등포","화곡S/S 154kV #65 BUS","화곡S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-08 14:00","2019-11-08 15:00","취소","취소","당일"]
[67,"남서울","영등포","화곡S/S 154kV #60 BUS","화곡S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-08 13:00","2019-11-08 14:00","취소","취소","당일"]
[68,"남서울","직할","사당봉천#1 T/L","OF케이블 절연유 채유작업(사당-봉천#1T/L))","절연열화 확인을 위한 절연유 채유 급유구간 및 채유장소 - 사당 EBG ~ M/H#8 : 사당EBG, M/H#8 - M/H#8 ~ M/H#15-1 : M/H#8, M/H#15-1(봉천전력구 말단)","2019-11-25 10:00","2019-11-26 10:00","취소","취소","연속"]
[69,"남서울","직할","사당봉천#2 T/L","장기사용 보호배전반 교체공사","장기사용 송전선로 보호배전반 교체공사","2019-11-25 09:00","2019-11-27 18:00","취소","취소","연속"]
[70,"남서울","직할","사당봉천#1 T/L","OF케이블 절연유 채유작업(사당-봉천#1T/L))","절연열화 확인을 위한 절연유 채유 급유구간 및 채유장소 - 사당 EBG ~ M/H#8 : 사당EBG, M/H#8 - M/H#8 ~ M/H#15-1 : M/H#8, M/H#15-1(봉천전력구 말단)","2019-11-11 10:00","2019-11-12 10:00","2019-11-11 10:00","2019-11-12 10:00","연속"]
[71,"남서울","직할","대방신길#2 T/L","장기사용 보호배전반 교체공사","장기사용 송전선로 보호배전반 교체공사","2019-11-20 09:00","2019-11-22 18:00","취소","취소","연속"]
[72,"남서울","직할","대방신길#1 T/L","장기사용 보호배전반 교체공사","장기사용 송전선로 보호배전반 교체공사","2019-11-18 09:00","2019-11-20 18:00","취소","취소","연속"]
[73,"남서울","직할","봉천신길#2 T/L","직할 170kV GIS 정밀점검","봉천-신길#2T/L (무부하) 봉천변전소","2019-11-06 18:00","2019-11-09 18:00","2019-11-06 18:00","2019-11-09 18:00","연속"]
[74,"남서울","직할","사당신림 T/L","OF케이블 절연유 보충(사당-신림T/L)","동계시 유압 하한치 근접으로 급유보충 구간 : M/H #8~M/H #4","2019-11-28 10:00","2019-11-29 18:00","취소","취소","연속"]
[75,"남서울","직할","영등포구로#1 T/L","직할 170kV GIS 정밀점검","직할 170kV GIS 정밀점검 (무부하) 상대단 변전소","2019-11-11 09:00","2019-11-13 14:00","2019-11-11 09:00","2019-11-13 14:00","연속"]
[76,"남서울","직할","영등포구로#2 T/L","직할 170kV GIS 정밀점검","직할 170kV GIS 정밀점검 (무부하) 상대단 변전소","2019-11-13 14:00","2019-11-16 18:00","2019-11-13 14:00","2019-11-16 18:00","연속"]
[77,"남서울","영등포","신광명광명#1 T/L","2019-2020년 영등포전력지사 지중송전설비 위탁정비공사","EBA PD진단용 집합반 설치","2019-11-02 09:00","2019-11-02 18:00","2019-11-02 09:00","2019-11-02 18:00","당일"]
[78,"남서울","영등포","중동화곡#2 T/L","화곡S/S 154kV 송전선로 보호반 교체(중동-화곡#2T/L)","- 154kV 송전선로 보호반 교체 - 제어케이블 결선 및 CT, PT 케이블 결선","2019-11-04 09:00","2019-11-08 18:00","취소","취소","연속"]
[79,"남서울","영등포","신광명S/S 154kV #60 BUS","신광명S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-07 10:00","2019-11-07 11:00","2019-11-07 10:00","2019-11-07 11:00","당일"]
[80,"남서울","영등포","신광명S/S 154kV #65 BUS","신광명S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-07 11:00","2019-11-07 12:00","2019-11-07 11:00","2019-11-07 12:00","당일"]
[81,"남서울","영등포","신광명S/S 154kV #61 BUS","신광명S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-07 13:00","2019-11-07 14:00","2019-11-07 13:00","2019-11-07 14:00","당일"]
[82,"남서울","영등포","신광명S/S 154kV #66 BUS","신광명S/S 170kV PT GIS 보통점검","- PT GIS 보통점검","2019-11-07 14:00","2019-11-07 15:00","2019-11-07 14:00","2019-11-07 15:00","당일"]
[83,"남서울","영등포","신광명광명#2 T/L","2019-2020년 영등포전력지사 지중송전설비 위탁정비공사","EBA PD진단용 집합반 설치","2019-11-09 09:00","2019-11-09 18:00","취소","취소","당일"]
[84,"남서울","영등포","신광명시흥#2 T/L","154kV 신광명-시흥#2T/L 피뢰기 설치공사","공사대상 : 신광명-시흥#2T/L No.20","2019-11-10 07:00","2019-11-10 18:00","취소","취소","당일"]
[85,"남서울","영등포","신광명시흥#1 T/L","신광명S/S 170kV GIS 하자보수 및 보통점검","- 170kV GIS 크랙 하자보수 - 154kV 1차 피뢰기 보통점검","2019-11-11 09:00","2019-11-11 14:00","취소","취소","당일"]
[86,"남서울","영등포","신광명시흥#2 T/L","신광명S/S 170kV GIS 하자보수 및 보통점검","- 170kV GIS 접합부 크랙 하자보수 - 154kV 1차 피뢰기 보통점검","2019-11-11 14:00","2019-11-11 18:00","취소","취소","당일"]
[87,"인천","부평","서인천C/C 154kV #65BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 ","서인천복합S/Y 6100 BUS TIE GIS 정밀점검 관련 무부하가압용 ","2019-11-09 09:00","2019-11-09 18:00","2019-11-09 09:00","2019-11-09 18:00","당일"]
[88,"인천","부평","서인천C/C 154kV #66BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사 ","서인천복합S/Y 6200 BUS TIE GIS 정밀점검 관련 무부하가압용 ","2019-11-13 09:00","2019-11-13 18:00","2019-11-13 09:00","2019-11-13 18:00","당일"]
[89,"인천","부평","송현포스코CC#2 T/L","154kV 송현-포스코CC #2T/L 크로스본딩 결선공사 ","1크로스본딩 구간 결선공사","2019-11-01 09:00","2019-11-01 18:00","2019-11-01 09:00","2019-11-01 18:00","당일"]
[90,"인천","김포","영종경서 T/L","154kV 영종-경서/L 선로정수 측정","병행지선 설치선로 보호계전기 정정자료(선로정수) 취득","2019-11-27 09:00","2019-11-27 13:00","2019-11-27 09:00","2019-11-27 13:00","당일"]
[91,"인천","김포","경서북인천#2 T/L","154kV 경서-북인천#2T/L 선로정수 측정","병행지선 설치선로 보호계전기 정정자료(선로정수) 취득","2019-11-26 13:00","2019-11-26 18:00","2019-11-26 13:00","2019-11-26 18:00","당일"]
[92,"인천","김포","경서북인천#1 T/L","154kV 경서-북인천#1T/L 선로정수 측정","병행지선 설치선로 보호계전기 정정자료(선로정수) 취득","2019-11-26 09:00","2019-11-26 13:00","2019-11-26 09:00","2019-11-26 13:00","당일"]
[93,"인천","김포","신경서경서#2 T/L","154kV 신경서-경서#2T/L 선로정수 측정","병행지선 설치선로 보호계전기 정정자료(선로정수) 취득","2019-11-25 13:00","2019-11-25 18:00","2019-11-25 13:00","2019-11-25 18:00","당일"]
[94,"인천","김포","신경서경서#1 T/L","154kV 신경서-경서#1T/L 선로정수 측정","병행지선 설치선로 보호계전기 정정자료(선로정수) 취득","2019-11-25 09:00","2019-11-25 13:00","2019-11-25 09:00","2019-11-25 13:00","당일"]
[95,"인천","김포","경서S/S 154kV #60 BUS","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사(계통시험) - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타 부대공사 1식","2019-11-24 08:00","2019-11-24 18:00","2019-11-24 08:00","2019-11-24 18:00","연속"]
[96,"인천","김포","경서양촌#1 T/L","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사(최종 무부하 시행) - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타 부대공사 1식","2019-11-22 18:00","2019-11-23 18:00","2019-11-22 18:00","2019-11-23 18:00","연속"]
[97,"인천","직할","신부평S/S 154kV #61-#66 BUS TIE CB","신부평S/S 170kV 6200 BUS TIE GIS 조작시험","신부평S/S 170kV 6200 BUS TIE GIS 조작시험","2019-11-15 09:30","2019-11-15 14:00","2019-11-15 09:30","2019-11-15 14:00","당일"]
[98,"인천","직할","부천원미#2 T/L","154kV 부천-원미#2T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 부천-원미#2T/L 병행지선 설치공사 - 설치개소 : J/B#12~부천EBG (전력구 : 0.4km)","2019-11-14 14:00","2019-11-14 18:00","2019-11-14 14:00","2019-11-14 18:00","당일"]
[99,"인천","부평","신경서서인천CC T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 서인천CC-신경서T/L GIS(617) 정밀점검 1) 170㎸ GIS 정밀점검 × 1식 2) 기타 부대작업 × 1식","2019-11-14 09:00","2019-11-16 18:00","2019-11-14 09:00","2019-11-16 18:00","연속"]
[100,"인천","직할","부천원미#1 T/L","154kV 부천-원미#1T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 부천-원미#1T/L 병행지선 설치공사 - 설치개소 : J/B#12~부천EBG (전력구 : 0.4km)","2019-11-14 09:00","2019-11-14 14:00","2019-11-14 09:00","2019-11-14 14:00","당일"]
[101,"인천","김포","경서S/S 154kV #65 BUS","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사 - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타 부대공사 1식","2019-11-13 15:00","2019-11-23 18:00","2019-11-13 15:00","2019-11-23 18:00","연속"]
[102,"인천","김포","경서양촌#1 T/L","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사(무부하 시행) - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타 부대공사 1식","2019-11-12 15:00","2019-11-13 15:00","2019-11-12 15:00","2019-11-13 15:00","연속"]
[103,"인천","직할","신부평임학#2 T/L","154kV 신부평-임학#2T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-임학#2T/L 병행지선 설치공사 - 설치개소 : J/B#18~임학EBG (전력구 : 0.8km)","2019-11-12 14:00","2019-11-12 18:00","2019-11-12 14:00","2019-11-12 18:00","당일"]
[104,"인천","직할","신부평임학#1 T/L","154kV 신부평-임학#1T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-임학#1T/L 병행지선 설치공사 - 설치개소 : J/B#18~임학EBG (전력구 : 0.8km)","2019-11-12 09:00","2019-11-12 14:00","2019-11-12 09:00","2019-11-12 14:00","당일"]
[105,"인천","직할","부흥부개#2 T/L","154kV 부흥-부개#2T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 부흥-부개#2T/L 병행지선 설치공사 - 설치개소 : J/B#6~부흥EBG (전력구,관로 : 0.4km)","2019-11-11 14:00","2019-11-11 18:00","2019-11-11 14:00","2019-11-11 18:00","당일"]
[106,"인천","부평","서인천C/C 154kV #61-#66 BUS TIE GIS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 6200 BUS TIE GIS 정밀점검 1) 170㎸ GIS 정밀점검 × 1식 2) 기타 부대작업 × 1식","2019-11-11 09:00","2019-11-13 18:00","2019-11-11 09:00","2019-11-13 18:00","연속"]
[107,"인천","직할","부흥부개#1 T/L","154kV 부흥-부개#1T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 부흥-부개#1T/L 병행지선 설치공사 - 설치개소 : J/B#6~부흥EBG (전력구,관로 : 0.4km)","2019-11-11 09:00","2019-11-11 14:00","2019-11-11 09:00","2019-11-11 14:00","당일"]
[108,"인천","직할","고강화곡#2 T/L","고강S/S 고강화곡#2T/L 170kV GIS 조작시험","고강S/S 고강화곡#2T/L 170kV GIS 조작시험","2019-11-09 14:00","2019-11-09 18:00","2019-11-09 14:00","2019-11-09 18:00","연속"]
[109,"인천","직할","고강화곡#1 T/L","고강S/S 고강화곡#1T/L 170kV GIS 조작시험","고강S/S 고강화곡#1T/L 170kV GIS 조작시험","2019-11-09 09:30","2019-11-09 14:00","2019-11-09 09:30","2019-11-09 14:00","연속"]
[110,"인천","직할","신부평부흥#2 T/L","154kV 신부평-부흥#2T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-부흥#2T/L 병행지선 설치공사 - 설치개소 : J/B#9~부흥EBG (전력구,관로 : 0.9km)","2019-11-08 14:00","2019-11-08 18:00","2019-11-08 14:00","2019-11-08 18:00","당일"]
[111,"인천","직할","신부평부흥#1 T/L","154kV 신부평-부흥#1T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-부흥#1T/L 병행지선 설치공사 - 설치개소 : J/B#9~부흥EBG (전력구,관로 : 0.9km)","2019-11-08 09:00","2019-11-08 14:00","2019-11-08 09:00","2019-11-08 14:00","당일"]
[112,"인천","직할","계양원창 T/L","154kV 계양-원창T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 계양-원창T/L 병행지선 설치공사 - 설치개소 : J/B#3~#4 (전력구 : 0.4km)","2019-11-07 10:00","2019-11-07 18:00","2019-11-07 10:00","2019-11-07 18:00","당일"]
[113,"인천","부평","서인천C/C 154kV #60-#65 BUS TIE GIS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 6100 BUS TIE GIS 정밀점검 1) 170㎸ GIS 정밀점검 × 1식 2) 기타 부대작업 × 1식","2019-11-07 09:00","2019-11-09 18:00","2019-11-07 09:00","2019-11-09 18:00","연속"]
[114,"인천","직할","신부평고강#2 T/L","154kV 신부평-고강#2T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-고강#2T/L 병행지선 설치공사 - 설치개소 : J/B#3~#5, J/B#10~고강EBG (전력구 : 1.3km)","2019-11-06 14:00","2019-11-06 18:00","취소","취소","당일"]
[115,"인천","부평","서인천C/C 154kV #66 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 65-66 BUS SEC GIS 정밀점검 관련 무부하가압용","2019-11-06 13:00","2019-11-06 18:00","2019-11-06 13:00","2019-11-06 18:00","당일"]
[116,"인천","부평","서인천C/C 154kV #61-#66 BUS TIE GIS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 65-66 BUS SEC GIS 정밀점검 관련 무부하가압용","2019-11-06 13:00","2019-11-06 18:00","2019-11-06 13:00","2019-11-06 18:00","당일"]
[117,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강#1T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-고강#1T/L 병행지선 설치공사 - 설치개소 : J/B#3~#5, J/B#10~고강EBG (전력구 : 1.3km)","2019-11-06 09:00","2019-11-06 14:00","취소","취소","당일"]
[118,"인천","김포","경서S/S 154kV #60 BUS","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사 - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타 부대공사 1식","2019-11-06 08:00","2019-11-13 15:00","2019-11-06 08:00","2019-11-13 15:00","연속"]
[119,"인천","직할","신부평중동#3 T/L","154kV 신부평-중동#3T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-중동#3T/L 병행지선 설치공사 - 설치개소 : J/B#9~#11 (전력구 : 0.7km)","2019-11-05 10:00","2019-11-05 18:00","2019-11-05 10:00","2019-11-05 18:00","당일"]
[120,"인천","직할","부천도당#2 T/L","부천S/S 도당부천#2T/L 170kV GIS 조작시험","부천S/S 도당부천#2T/L 170kV GIS 조작시험","2019-11-04 14:00","2019-11-04 18:00","2019-11-04 14:00","2019-11-04 18:00","연속"]
[121,"인천","직할","신부평중동#2 T/L","154kV 신부평-중동#2T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-중동#2T/L 병행지선 설치공사 - 설치개소 : J/B#9~#11 (전력구 : 0.7km)","2019-11-04 14:00","2019-11-04 18:00","2019-11-04 14:00","2019-11-04 18:00","당일"]
[122,"인천","직할","부천도당#1 T/L","부천S/S 도당부천#1T/L 170kV GIS 조작시험","부천S/S 도당부천#1T/L 170kV GIS 조작시험","2019-11-04 09:30","2019-11-04 14:00","2019-11-04 09:30","2019-11-04 14:00","연속"]
[123,"인천","김포","신김포장기#2 T/L","신김포S/S 154kV 신김포-장기#2T/L 보호반 대체","신김포S/S 154kV 신김포-장기#2T/L 보호반 대체","2019-11-04 09:00","2019-11-08 18:00","2019-11-04 09:00","2019-11-08 18:00","연속"]
[124,"인천","부평","서인천C/C 154kV #65-#66 SEC GIS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 65-66 BUS SEC GIS 정밀점검 1) 170㎸ GIS 정밀점검 × 1식 2) 기타 부대작업 × 1식","2019-11-04 09:00","2019-11-06 18:00","2019-11-04 09:00","2019-11-06 18:00","연속"]
[125,"인천","직할","신부평중동#1 T/L","154kV 신부평-중동#1T/L 병행지선 설치 및 보호계전기 정정·시험","154kV 신부평-중동#1T/L 병행지선 설치공사 - 설치개소 : J/B#9~#11 (전력구 : 0.7km)","2019-11-04 09:00","2019-11-04 14:00","2019-11-04 09:00","2019-11-04 14:00","당일"]
[126,"인천","김포","경서S/S 154kV #65 BUS","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사 - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타부대공사 1식","2019-11-04 08:00","2019-11-05 18:00","2019-11-04 08:00","2019-11-05 18:00","연속"]
[127,"인천","김포","경서S/S 154kV #60 BUS","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사(계통시험) - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타부대공사 1식","2019-11-03 08:00","2019-11-03 18:00","2019-11-03 08:00","2019-11-03 18:00","당일"]
[128,"인천","직할","임학계양#2 T/L","임학,계양S/S 임학계양#2T/L 170kV GIS 조작시험","임학,계양S/S 임학계양#2T/L 170kV GIS 조작시험","2019-11-02 14:00","2019-11-02 18:00","2019-11-02 14:00","2019-11-02 18:00","연속"]
[129,"인천","직할","임학계양#1 T/L","임학,계양S/S 임학계양#1T/L 170kV GIS 조작시험","임학,계양S/S 임학계양#1T/L 170kV GIS 조작시험","2019-11-02 09:30","2019-11-02 14:00","2019-11-02 09:30","2019-11-02 14:00","연속"]
[130,"인천","김포","경서양촌#1 T/L","경서S/S 170kV GIS 개조공사","○ 경서S/S 170kV GIS 개조공사(최종 무부하 시행) - #3M.Tr, #4M.Tr 1차 GIS 철거 - #3M.Tr, #4M.Tr 1차 GIS 개조 및 설치 - 기타부대공사 1식","2019-11-01 18:00","2019-11-02 18:00","2019-10-30 18:00","2019-11-01 18:00","연속"]
[131,"인천","부평","서인천C/C 154kV #61-#66 BUS TIE GIS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 60-61 BUS SEC GIS 정밀점검 관련 무부하가압용","2019-11-01 13:00","2019-11-01 18:00","2019-11-01 13:00","2019-11-01 18:00","당일"]
[132,"인천","부평","서인천C/C 154kV #61 BUS","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","서인천복합S/Y 60-61 BUS SEC GIS 정밀점검 관련 무부하가압용","2019-11-01 13:00","2019-11-01 18:00","2019-11-01 13:00","2019-11-01 18:00","당일"]
[133,"경기북부","고양","신파주금촌#2 T/L","154kV 신덕은-원흥/신파주-금촌T/L 계통변경공사","ㅇ 전선교체 : 신덕은-원흥T/L No.46-48 ㅇ 계탑 : No.9 ㅇ 철탑 및 암보강 : No.10 ㅇ 계통변경 : 신덕은-원흥/신파주-금촌 ⇒ 신파주-원흥/신덕은-금촌","2019-11-21 18:00","2019-12-01 18:00","2019-11-21 18:00","2019-12-01 18:00","연속"]
[134,"경기북부","고양","신파주금촌#1 T/L","154kV 신덕은-원흥/신파주-금촌T/L 계통변경공사","ㅇ 전선교체 : 신덕은-원흥T/L No.46-48 ㅇ 계탑 : No.9 ㅇ 철탑 및 암보강 : No.10 ㅇ 계통변경 : 신덕은-원흥/신파주-금촌 ⇒ 신파주-원흥/신덕은-금촌","2019-11-21 18:00","2019-12-01 18:00","2019-11-21 18:00","2019-12-01 18:00","연속"]
[135,"경기북부","고양","남면S/S 154kV 남면-백석#2T/L GIS","2019 고양P/O 변전정비회사 총액공사(남면-백석#2T/L GIS)","남면S/S 남면-백석#2 T/L GIS 하자점검","2019-11-04 09:00","2019-11-04 18:00","2019-11-04 09:00","2019-11-04 18:00","당일"]
[136,"경기북부","고양","남면S/S 154kV 남면-백석#1T/L GIS","2019 고양P/O 변전정비회사 총액공사(남면-백석#1T/L GIS)","남면S/S 남면-백석#1 T/L GIS 하자점검","2019-11-05 09:00","2019-11-05 18:00","2019-11-05 09:00","2019-11-05 18:00","당일"]
[137,"경기북부","고양","문발덕이#1 T/L","변전총액공사-170kV GIS 조작시험","덕이S/S 문발-덕이#1T/L 차단기 조작시험","2019-11-12 10:00","2019-11-12 13:00","2019-11-12 10:00","2019-11-12 13:00","당일"]
[138,"경기북부","고양","신파주문발#1 T/L","변전총액공사-170kV GIS 조작시험","신파주S/S 신파주-문발#1T/L 차단기 조작시험","2019-11-12 14:00","2019-11-12 17:00","2019-11-12 14:00","2019-11-12 17:00","당일"]
[139,"경기북부","고양","신덕은원흥#2 T/L","154kV 신덕은-원흥T/L 송전용량증대 전력선교체공사","전력선교체 ㅇ No.10-13, 17-30, 39-60, 12.03km ㅇ 계탑 : No.10 ㅇ 애자장치변경 : No.11","2019-11-01 18:00","2019-11-21 18:00","2019-11-01 18:00","2019-11-21 18:00","연속"]
[140,"경기북부","고양","신덕은원흥#1 T/L","154kV 신덕은-원흥T/L 송전용량증대 전력선교체공사","전력선교체 ㅇ No.10-13, 17-30, 39-60, 12.03km ㅇ 계탑 : No.10 ㅇ 애자장치변경 : No.11","2019-11-01 18:00","2019-11-21 18:00","2019-11-01 18:00","2019-11-21 18:00","연속"]
[141,"경기북부","고양","원흥수색#1 T/L","19-20년 지중송전설비 위탁정비공사","케이블헤드 및 피뢰기 점검 - 16호 C/H","2019-11-08 09:00","2019-11-08 18:00","2019-11-08 09:00","2019-11-08 18:00","당일"]
[142,"경기북부","고양","원흥수색#2 T/L","19-20년 지중송전설비 위탁정비공사","케이블헤드 및 피뢰기 점검 - 16호 C/H","2019-11-11 09:00","2019-11-11 18:00","2019-11-11 09:00","2019-11-11 18:00","당일"]
[143,"경기북부","고양","신덕은원흥#1 T/L","154kV 신덕은-원흥/신파주-금촌T/L 계통변경공사","ㅇ 전선교체 : 신덕은-원흥T/L No.46-48 ㅇ 계탑 : No.9 ㅇ 철탑 및 암보강 : No.10 ㅇ 계통변경 : 신덕은-원흥/신파주-금촌 ⇒ 신파주-원흥/신덕은-금촌","2019-11-25 07:00","2019-12-01 18:00","2019-11-25 07:00","2019-12-01 18:00","연속"]
[144,"경기북부","고양","신덕은원흥#2 T/L","154kV 신덕은-원흥/신파주-금촌T/L 계통변경공사","ㅇ 전선교체 : 신덕은-원흥T/L No.46-48 ㅇ 계탑 : No.9 ㅇ 철탑 및 암보강 : No.10 ㅇ 계통변경 : 신덕은-원흥/신파주-금촌 ⇒ 신파주-원흥/신덕은-금촌","2019-11-25 07:00","2019-12-01 18:00","2019-11-25 07:00","2019-12-01 18:00","연속"]
[145,"경기북부","고양","일산호수#1 T/L","변전총액공사 - 170kV GIS 차단기 조작시험","일산S/S 일산-호수#1,2T/L 차단기 조작시험","2019-11-11 09:00","2019-11-11 12:00","2019-11-11 09:00","2019-11-11 12:00","당일"]
[146,"경기북부","고양","일산호수#2 T/L","변전총액공사 - 170kV GIS 차단기 조작시험","일산S/S 일산-호수#1,2T/L 차단기 조작시험","2019-11-11 13:00","2019-11-11 15:00","2019-11-11 13:00","2019-11-11 15:00","당일"]
[147,"경기북부","고양","일산지도#2 T/L","기중종단접속함(EB-A) 자기애관 교체공사","기설 자기애관 → 폴리머애관 교체","2019-11-25 09:00","2019-11-28 18:00","2019-11-25 09:00","2019-11-28 18:00","연속"]
[148,"경기북부","고양","일산지도#1 T/L","기중종단접속함(EB-A) 자기애관 교체공사","기설 자기애관 → 폴리머애관 교체","2019-11-18 09:00","2019-11-22 18:00","2019-11-18 09:00","2019-11-22 18:00","연속"]
[149,"경기북부","고양","덕이호수#2 T/L","변전총액공사-170kV GIS 조작시험","호수S/S 덕이-호수#2T/L 차단기 조작시험","2019-11-01 14:00","2019-11-01 17:00","2019-11-01 14:00","2019-11-01 17:00","당일"]
[150,"경기북부","고양","덕이호수#1 T/L","변전총액공사-170kV GIS 조작시험","호수S/S 덕이-호수#1T/L 차단기 조작시험","2019-11-01 10:00","2019-11-01 13:00","2019-11-01 10:00","2019-11-01 13:00","당일"]
[151,"경기북부","구리","가평청평HP#1 T/L","154kV 가평-청평#1 CVT 점검","154kV 가평-청평#1 CVT 점검","2019-11-14 09:00","2019-11-14 18:00","2019-11-14 09:00","2019-11-14 18:00","당일"]
[152,"경기북부","구리","미금덕소#1 T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업 154kV 덕소-팔당T/L, 154kV 미금-덕소#1T/L, 154kV 미금-덕소#2T/L 동시휴전작업으로 기설변전소 정지 및 신설 덕소S/S 계통병입","2019-11-04 09:00","2019-12-05 18:00","2019-11-04 09:00","2019-12-05 18:00","연속"]
[153,"경기북부","구리","미금덕소#2 T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업 154kV 덕소-팔당T/L, 154kV 미금-덕소#1T/L, 154kV 미금-덕소#2T/L 동시휴전작업으로 기설변전소 정지 및 신설 덕소S/S 계통병입","2019-11-04 09:00","2019-12-05 18:00","2019-11-04 09:00","2019-12-05 18:00","연속"]
[154,"경기북부","구리","덕소팔당HP T/L","154㎸ 덕소S/S 옥내화관련 지중T/L 건설공사","154kV 덕소S/S 옥내화공사 시행에 따른 관련 지중T/L 정비사업 154kV 덕소-팔당T/L, 154kV 미금-덕소#1T/L, 154kV 미금-덕소#2T/L 동시휴전작업으로 기설변전소 정지 및 신설 덕소S/S 계통병입","2019-11-04 09:00","2019-11-28 18:00","2019-11-04 09:00","2019-11-28 18:00","연속"]
[155,"경기북부","구리","미금S/S 154kV #60-#65 BUS TIE CB","'18~19년 구리전력지사 변전협력 총액공사","2019년도 장기무동작 차단기 조작시험","2019-11-18 09:00","2019-11-18 14:00","2019-11-18 09:00","2019-11-18 14:00","당일"]
[156,"경기북부","구리","미금S/S 154kV #62-#67 BUS TIE CB","'18~19년 구리전력지사 변전협력 총액공사","2019년도 장기무동작 차단기 조작시험","2019-11-19 09:00","2019-11-19 18:00","2019-11-19 09:00","2019-11-19 18:00","당일"]
[157,"경기북부","구리","미금S/S 154kV #61-#66 BUS TIE CB","'18~19년 구리전력지사 변전협력 총액공사","2019년도 장기무동작 차단기 조작시험","2019-11-18 14:00","2019-11-18 18:00","2019-11-18 14:00","2019-11-18 18:00","당일"]
[158,"경기북부","구리","별내도봉 T/L","154kV 별내-도봉T/L 송전선로 정밀점검","154kV 별내-도봉T/L 철탑 22기 송전선로 정밀점검","2019-11-12 09:00","2019-11-13 18:00","2019-11-12 09:00","2019-11-13 18:00","매일"]
[159,"경기북부","구리","신포천포천#1 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 포천-운천#1T/L 정밀점검 상단병가선로","2019-11-11 08:00","2019-11-11 18:00","2019-11-11 08:00","2019-11-11 18:00","당일"]
[160,"경기북부","구리","신포천포천#2 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 포천-운천#2T/L 정밀점검 상단병가선로","2019-11-18 08:00","2019-11-18 18:00","2019-11-18 08:00","2019-11-18 18:00","당일"]
[161,"경기북부","구리","운천전곡#1 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 포천-운천#2T/L 정밀점검 하단병가선로","2019-11-21 08:00","2019-11-21 18:00","2019-11-21 08:00","2019-11-21 18:00","당일"]
[162,"경기북부","구리","운천전곡#2 T/L","2019년 가공송전선로 순시점검 위탁공사","154kV 포천-운천#1T/L 정밀점검 하단병가선로","2019-11-15 08:00","2019-11-15 18:00","2019-11-15 08:00","2019-11-15 18:00","당일"]
[163,"경기북부","구리","청평H/P 154kV #60 BUS","청평수력 변전설비 점검","청평수력 변전설비 합동점검(한전, 한수원, 제작사)","2019-11-05 09:00","2019-11-05 13:00","2019-11-05 09:00","2019-11-05 13:00","당일"]
[164,"경기북부","구리","포천운천#1 T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검(No.1~65)","2019-11-11 08:00","2019-11-15 18:00","2019-11-11 08:00","2019-11-15 18:00","연속"]
[165,"경기북부","구리","신포천포천#1 T/L","'18~19년 구리전력지사 변전협력 총액공사","2019년도 장기무동작 차단기 조작시험","2019-11-12 14:00","2019-11-12 18:00","2019-11-12 14:00","2019-11-12 18:00","당일"]
[166,"경기북부","구리","포천운천#2 T/L","2019년 가공송전선로 순시점검 위탁공사","정밀점검(No.1~65)","2019-11-18 08:00","2019-11-22 18:00","2019-11-18 08:00","2019-11-22 18:00","연속"]
[167,"경기북부","직할","신포천덕계#2 T/L","18~19 직할 변전정비회사 총액공사","□ 신포천-덕계 #2 T/L LA 대체","2019-11-29 09:00","2019-11-29 18:00","2019-11-29 09:00","2019-11-29 18:00","당일"]
[168,"경기북부","직할","도봉방학#1 T/L","18~19 직할 변전정비회사 총액공사","□ 도봉-방학 #1 T/L CVT 초기점검","2019-11-07 14:00","2019-11-07 18:00","2019-11-07 14:00","2019-11-07 18:00","당일"]
[169,"경기북부","직할","동두천S/S 154kV 신포천-동두천#2T/L GIS","19년 직할 변전정비회사 총액공사","동두천S/S 신포천-동두천 #2 T/L A상 피뢰기 과열 대체","2019-11-01 09:00","2019-11-01 18:00","2019-11-01 09:00","2019-11-01 18:00","당일"]
[170,"경기북부","직할","신의정부송우#2 T/L","2018~2019년 경기북부직할 가공송전 정비회사 총액공사","345kV 신의정부-미금#2T/L 불량애자교체 하단병가선로(안전이격거리 확보용)","2019-11-04 08:00","2019-11-05 18:00","2019-11-04 08:00","2019-11-05 18:00","연속"]
[171,"경기북부","직할","신의정부송우#2 T/L","신의정부S/S 하자보수(DS조작로드 교체공사)","DS부 조작로드 발청에 의한 교체공사","2019-11-21 09:00","2019-11-21 18:00","2019-11-21 09:00","2019-11-21 18:00","연속"]
[172,"경기북부","직할","신의정부송우#1 T/L","2019년 가공송전선로 순시점검 위탁공사","345kV 신의정부-미금#1T/L 정밀점검 하단병가선로(안전이격거리 확보용)","2019-11-06 08:00","2019-11-07 18:00","2019-11-06 08:00","2019-11-07 18:00","연속"]
[173,"경기북부","직할","신의정부송우#1 T/L","신의정부S/S 하자보수(DS조작로드 교체공사)","DS부 조작로드 발청에 의한 교체공사","2019-11-18 09:00","2019-11-18 18:00","2019-11-18 09:00","2019-11-18 18:00","연속"]
[174,"경기북부","직할","신의정부내촌#2 T/L","신의정부S/S 하자보수(DS조작로드 교체공사)","DS부 조작로드 발청에 의한 교체공사","2019-11-19 09:00","2019-11-19 18:00","2019-11-19 09:00","2019-11-19 18:00","연속"]
[175,"경기북부","직할","신의정부내촌#1 T/L","신의정부S/S 하자보수(DS조작로드 교체공사)","DS부 조작로드 발청에 의한 교체공사","2019-11-20 09:00","2019-11-20 18:00","2019-11-20 09:00","2019-11-20 18:00","연속"]
[176,"경기북부","직할","양주금촌#1 T/L","양주S/S옥외철구 GIS화 전력구공사","양주금촌#1T/L 인출측 전력구공사","2019-11-06 09:00","2019-11-07 18:00","취소","취소","연속"]
[177,"경기북부","직할","양주은평#1 T/L","양주S/S옥외철구 GIS화 전력구공사","양주은평#1T/L 인출측 전력구공사","2019-11-18 09:00","2019-11-19 18:00","2019-11-18 09:00","2019-11-19 18:00","연속"]
[178,"경기북부","직할","양주금촌#2 T/L","양주S/S옥외철구 GIS화 전력구공사","양주금촌#2T/L 인출측 전력구공사","2019-11-04 09:00","2019-11-05 18:00","취소","취소","연속"]
[179,"경기북부","직할","양주녹양#2 T/L","양주S/S옥외철구 GIS화 전력구공사","양주녹양#2 T/L 인출측 전력구공사","2019-11-27 09:00","2019-11-28 18:00","2019-11-27 09:00","2019-11-28 18:00","연속"]
[180,"경기북부","직할","양주녹양#1 T/L","양주S/S옥외철구 GIS화 전력구공사","양주녹양#1T/L 인출측 전력구공사","2019-11-25 09:00","2019-11-26 18:00","2019-11-25 09:00","2019-11-26 18:00","연속"]
[181,"경기북부","직할","양주S/S 154kV #60-#61 SEC CB","19년 직할 변전정비회사 총액공사","양주S/S 154kV #60-#61 CB 개폐타임 측정","2019-11-08 09:00","2019-11-08 14:00","2019-11-08 09:00","2019-11-08 14:00","당일"]
[182,"경기북부","직할","양주지축#2 T/L","양주S/S옥외철구 GIS화 전력구공사","양주지축#2T/L 인출측 전력구공사","2019-11-11 09:00","2019-11-12 18:00","2019-11-11 09:00","2019-11-12 18:00","연속"]
[183,"경기북부","직할","양주쌍문#1 T/L","양주S/S옥외철구 GIS화 전력구공사","양주쌍문#1T/L 인출측 전력구공사","2019-11-23 09:00","2019-11-24 18:00","2019-11-23 09:00","2019-11-24 18:00","연속"]
[184,"경기북부","직할","양주지축#1 T/L","양주S/S옥외철구 GIS화 전력구공사","양주지축#1T/L 인출측 전력구공사","2019-11-13 09:00","2019-11-14 18:00","2019-11-13 09:00","2019-11-14 18:00","연속"]
[185,"경기북부","직할","양주쌍문#2 T/L","양주S/S옥외철구 GIS화 전력구공사","양주쌍문#2T/L 인출측 전력구공사","2019-11-16 09:00","2019-11-17 18:00","2019-11-16 09:00","2019-11-17 18:00","연속"]
[186,"경기북부","직할","양주은평#2 T/L","양주S/S옥외철구 GIS화 전력구공사","양주은평#2T/L 인출측 전력구공사","2019-11-20 09:00","2019-11-21 18:00","2019-11-20 09:00","2019-11-21 18:00","연속"]
[187,"경기북부","직할","양주녹양#1 T/L","고양전력지사 OPGW 항공장애표시구 정비공사","345kV 신파주-양주 등 8개T/L OPGW 항공장애표시구 정비공사","2019-11-21 07:00","2019-11-22 18:00","2019-11-21 07:00","2019-11-22 18:00","연속"]
[188,"경기북부","직할","용현S/S 154kV 신의정부-용현#1T/L GIS","19년 직할 변전정비회사 총액공사","용현S/S 신의정부-용현 #1 T/L 개폐타임 측정","2019-11-25 09:00","2019-11-25 14:00","취소","취소","당일"]
[189,"경기북부","직할","용현S/S 154kV 신의정부-용현#2T/L GIS","19년 직할 변전정비회사 총액공사","용현S/S 신의정부-용현 #2 T/L 개폐타임 측정","2019-11-25 14:00","2019-11-25 18:00","취소","취소","당일"]
[190,"경기북부","구리","덕소진건#1 T/L","154kV 덕소E/C 옥내화 건설공사","154kV 덕소-팔당T/L 최초가압","2019-11-27 09:00","2019-11-28 18:00","2019-11-27 09:00","2019-11-28 18:00","연속"]
[191,"경기북부","구리","미금광장 T/L","154kV 화양T/L 항공장애시설물 정비공사","항공장애표시구 설치 - NO.25~26,28~30","2019-11-08 07:00","2019-11-08 18:00","2019-11-08 07:00","2019-11-08 18:00","당일"]
[192,"경기북부","직할","신의정부S/S 154kV #62BUS","신의정부S/S 하자보수(DS조작로드 교체공사)","DS부 조작로드 발청에 의한 교체공사","2019-11-18 09:00","2019-11-21 18:00","2019-11-18 09:00","2019-11-21 18:00","연속"]
[193,"경기북부","고양","신덕은문산#1 T/L","154kV 신덕은-원흥T/L 송전용량증대 전력선교체공사","휴전용 임시 SPS 사전조치용","2019-11-01 15:00","2019-11-01 16:00","2019-11-01 15:00","2019-11-01 16:00","당일"]
[194,"경기북부","고양","신덕은문산#2 T/L","154kV 신덕은-원흥T/L 송전용량증대 전력선교체공사","휴전용 임시 SPS 사전조치용","2019-11-01 16:00","2019-11-01 17:00","2019-11-01 16:00","2019-11-01 17:00","당일"]
[195,"경기","군포","서서울#2소래 T/L","154kV서서울2-소래TL초기점검(가공송전위탁공사)","154kV서서울2-소래TL No.36~38 초기점검","2019-11-25 09:00","2019-11-25 18:00","취소","취소","당일"]
[196,"경기","군포","서서울#2서안양 T/L","154kV서서울2-서안양TL초기점검(가공송전위탁공사)","154kV서서울2-서안양TL No.36~38 초기점검","2019-11-26 09:00","2019-11-26 18:00","취소","취소","당일"]
[197,"경기","군포","서서울율전#2 T/L","154kV서서울-율전TL 현수애자절연성능진단(가공송전위탁공사)","154kV서서울-율전#2TL No.1~24 현수애자절연성능진단","2019-11-27 09:00","2019-11-29 18:00","취소","취소","매일"]
[198,"경기","군포","서서울율전#1 T/L","154kV서서울-율전TL 현수애자절연성능진단(가공송전위탁공사)","154kV서서울-율전#1TL No.1~24 현수애자절연성능진단","2019-11-27 09:00","2019-11-29 18:00","취소","취소","매일"]
[199,"경기","군포","수촌조암#1 T/L","군포전력 송전정비회사 총액공사","조암-수촌T/L 31~32호 항공장애표시구 설치 공사","2019-11-26 09:00","2019-11-26 18:00","2019-11-26 09:00","2019-11-26 18:00","당일"]
[200,"경기","군포","일동원곡#1 T/L","군포전력 송전정비회사 총액공사","서서울-일동T/L 19~20호 항공장애표시구 설치 공사(4회선 상단구간)","2019-11-27 09:00","2019-11-27 18:00","2019-11-27 09:00","2019-11-27 18:00","당일"]
[201,"경기","군포","서서울#2일동 #2T/L","군포전력 송전정비회사 총액공사","서서울2-일동T/L 19~20호 항공장애표시구 설치 공사(4회선 하단구간)","2019-11-27 09:00","2019-11-27 18:00","2019-11-27 09:00","2019-11-27 18:00","당일"]
[202,"경기","군포","장덕마도 T/L","군포전력 송전정비회사 총액공사","장덕-마도T/L 51~52호 항공장애표시구 설치 공사","2019-11-25 09:00","2019-11-25 18:00","2019-11-25 09:00","2019-11-25 18:00","당일"]
[203,"경기","군포","조암구문천#2 T/L","조암-구문천#2T/L 선도제 보호계전기 성능개선공사","조암-구문천#2T/L 선도제 보호계전기 성능개선공사","2019-11-05 09:00","2019-11-05 18:00","2019-11-05 09:00","2019-11-05 18:00","당일"]
[204,"경기","동부","왕암가남#1 T/L","154kV 왕암-가남T/L 활선애자청소","154kV 왕암-가남#1T/L 206,207,208,209,210,219호 활선애자청소","2019-11-12 08:00","2019-11-12 18:00","취소","취소","당일"]
[205,"경기","동부","왕암가남#2 T/L","154kV 왕암-가남T/L 활선애자청소","154kV 왕암-가남#2T/L 206,207,208,209,210,219호 활선애자청소","2019-11-12 08:00","2019-11-12 18:00","취소","취소","당일"]
[206,"경기","동부","이천가남#2 T/L","154kV 이천-가남T/L 활선애자청소","154kV 이천-가남#2T/L 29,30,31,32,33,42호 활선애자청소","2019-11-12 08:00","2019-11-12 18:00","취소","취소","당일"]
[207,"경기","동부","이천가남#1 T/L","154kV 이천-가남T/L 활선애자청소","154kV 이천-가남#1T/L 29,30,31,32,33,42호 활선애자청소","2019-11-12 08:00","2019-11-12 18:00","취소","취소","당일"]
[208,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-이천#2T/L 송전선로용 피뢰기 설치공사","곤지암-이천#2T/L 1~5호 송전선로용 피뢰기 설치","2019-11-11 08:00","2019-11-11 18:00","취소","취소","당일"]
[209,"경기","동부","곤지암이천#1 T/L","154kV 곤지암-율현#1 T/L 불량애자교체","안전이격 휴전 (곤지암-율현T/L 4회선 구간)","2019-11-07 09:00","2019-11-07 18:00","취소","취소","당일"]
[210,"경기","동부","곤지암S/S 154kV 곤지암-율현#2T/L GIS","19년 동부변전협력회사 총액공사","곤지암 : 곤지암-율현#2T/L 보호반대체(~6) 곤지암: 곤지암-율현#2T/L 메카니즘 유면창 누유보수 율현 : 곤지암-율현#2T/L 보호반대체(~6) 율현: 곤지암-율현#2T/L GIS(보통),43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-11-04 09:30","2019-11-06 18:00","취소","취소","연속"]
[211,"경기","동부","곤지암S/S 154kV 곤지암-율현#1T/L GIS","19년 동부변전협력회사 총액공사","곤지암 : 곤지암-율현#1T/L 보호반대체(~9) 율현 : 곤지암-율현#1T/L 보호반대체(~9)","2019-11-07 09:30","2019-11-09 18:00","취소","취소","연속"]
[212,"경기","동부","곤지암이천#2 T/L","154kV 곤지암-율현#2 T/L 피뢰기설치 및 불량애자교체","안전이격 휴전 (곤지암-율현T/L 4회선 구간)","2019-11-06 09:00","2019-11-06 18:00","취소","취소","당일"]
[213,"경기","동부","곤지암율현#2 T/L","154kV 곤지암-이천#2T/L 송전선로용 피뢰기 설치공사","안전이격 휴전(곤지암-이천T/L 4회선 구간)","2019-11-11 08:00","2019-11-11 18:00","취소","취소","당일"]
[214,"경기","동부","성현분당#1 T/L","154kV 성현-분당T/L 현수애자절연성능진단","현수애자 절연성능진단","2019-11-26 09:00","2019-11-26 18:00","취소","취소","당일"]
[215,"경기","동부","성현분당#2 T/L","154kV 성현-분당T/L 현수애자절연성능진단","현수애자 절연성능진단","2019-11-26 09:00","2019-11-26 18:00","취소","취소","당일"]
[216,"경기","동부","야탑S/S 154kV 야탑-성현#2T/L GIS","19년 동부변전협력회사 총액공사","야탑:야탑-성현#2T/L (정밀-&gt보통) 43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-11-08 09:30","2019-11-08 18:00","취소","취소","당일"]
[217,"경기","동부","야탑S/S 154kV #60-#65 BUS TIE GIS","19년 동부변전협력회사 총액공사","야탑:6100 GIS(정밀-&gt보통) 43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-11-13 09:30","2019-11-13 18:00","취소","취소","당일"]
[218,"경기","동부","야탑S/S 154kV 동판교-야탑T/L GIS","19년 동부변전협력회사 총액공사","야탑:동판교-야탑T/L (정밀-&gt보통) 43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-11-05 09:30","2019-11-05 18:00","취소","취소","연속"]
[219,"경기","동부","여주문막#1 T/L","154kV 여주-문막#1T/L 불량애자교체","불량애자교체","2019-11-07 09:00","2019-11-07 18:00","취소","취소","당일"]
[220,"경기","동부","오천S/S 154kV #65-#66 SEC GIS","19년 동부변전협력회사 총액공사","오천: 65-66 SEC GIS(초기)","2019-11-19 09:30","2019-11-19 18:00","취소","취소","당일"]
[221,"경기","동부","오천S/S 154kV 오천-율현#1T/L GIS","19년 동부변전협력회사 총액공사","오천: 오천-율현#1T/L GIS(초기)","2019-11-14 09:30","2019-11-14 18:00","2019-11-14 09:30","2019-11-14 18:00","당일"]
[222,"경기","동부","오천S/S 154kV 용인-오천#2T/L GIS","19년 동부변전협력회사 총액공사","오천: 용인-오천#2T/L GIS(초기)","2019-11-13 09:30","2019-11-13 18:00","2019-11-13 09:30","2019-11-13 18:00","당일"]
[223,"경기","동부","오천S/S 154kV #60-#61 SEC GIS","19년 동부변전협력회사 총액공사","오천: 60-61 SEC GIS(초기)","2019-11-26 09:30","2019-11-26 18:00","취소","취소","당일"]
[224,"경기","동부","오천S/S 154kV #61-#66 BUS TIE GIS","19년 동부변전협력회사 총액공사","오천: 6200 GIS(초기)","2019-11-25 09:30","2019-11-25 18:00","취소","취소","당일"]
[225,"경기","동부","오천S/S 154kV 오천-율현#2T/L GIS","19년 동부변전협력회사 총액공사","오천: 오천-율현#2T/L GIS(초기)","2019-11-15 09:30","2019-11-15 18:00","2019-11-15 09:30","2019-11-15 18:00","당일"]
[226,"경기","동부","오천S/S 154kV 용인-오천#1T/L GIS","19년 동부변전협력회사 총액공사","오천: 용인-오천#1T/L GIS(초기)","2019-11-18 09:30","2019-11-18 18:00","2019-11-18 09:30","2019-11-18 18:00","당일"]
[227,"경기","동부","오천S/S 154kV #60-#65 BUS TIE GIS","19년 동부변전협력회사 총액공사","오천: 6100 GIS(초기)","2019-11-08 09:30","2019-11-08 18:00","취소","취소","당일"]
[228,"경기","동부","중원S/S 154kV 중원-야탑T/L GIS","19년 동부변전협력회사 총액공사","중원 : 중원-야탑T/L 보호반대체(~13) 중원:중원-야탑T/L (보통) 43L/R 회로보완 확인 및 Remote 회로분리 시행,메카니즘 오일 누유 보수 야탑 : 중원-야탑T/L 보호반대체(~13) 야탑:중원-야탑T/L (정밀-&gt보통) 43L/R 회로보완 확인 및 Remote 회로분리 시행","2019-11-11 09:30","2019-11-13 18:00","2019-11-11 09:30","2019-11-13 18:00","연속"]
[229,"경기","성남","농서삼성#2T/L CB","하이드로겐 오일 누유보수","하이드로겐 오일 누유보수","2019-11-08 09:00","2019-11-08 18:00","취소","취소","당일"]
[230,"경기","성남","남사동탄#1 T/L","154kV 동탄S/S #1M.Tr 증설공사","170kV #60BUS 무부하 가압","2019-11-20 09:00","2019-11-21 18:00","2019-11-20 09:00","2019-11-21 18:00","연속"]
[231,"경기","성남","남사동탄#1 T/L","154kV 동탄S/S #1M.Tr 증설공사","170kV #65BUS 무부하 가압","2019-11-22 09:00","2019-11-23 18:00","2019-11-22 09:00","2019-11-23 18:00","연속"]
[232,"경기","성남","남사동탄#1 T/L","154kV 동탄S/S #1M.Tr 증설공사","23kV #40,45BUS 무부하 가압","2019-11-29 09:00","2019-11-30 18:00","2019-11-29 09:00","2019-11-30 18:00","연속"]
[233,"경기","성남","남사동탄#1 T/L","154kV 동탄S/S #1M.Tr 증설공사","최초가압","2019-11-30 09:00","2019-12-01 18:00","2019-11-30 09:00","2019-12-01 18:00","연속"]
[234,"경기","성남","모현S/S 154kV #60 BUS","154kV 모현E/C #3M.Tr 증설공사","ㅇ154kV M.Tr 신설 x 1Bank ㅇ154kV GIS x 4CCT(1M, 2BS, 1BT) ㅇ22.9kV E-GIS x 4CCT(1M, 2BS, 1BT)","2019-11-04 09:00","2019-11-06 14:00","취소","취소","연속"]
[235,"경기","성남","모현S/S 154kV #60 BUS","154kV 모현E/C #3M.Tr 증설공사","ㅇ154kV M.Tr 신설 x 1Bank ㅇ154kV GIS x 4CCT(1M, 2BS, 1BT) ㅇ22.9kV E-GIS x 4CCT(1M, 2BS, 1BT)","2019-11-11 09:00","2019-11-20 18:00","2019-11-11 09:00","2019-11-20 18:00","연속"]
[236,"경기","성남","오포모현#2 T/L","154kV 오포-모현#2T/L OPGW 항공장애표시구 설치공사","항공장애표시구 설치 : 14~16호","2019-11-11 07:00","2019-11-11 18:00","2019-11-11 07:00","2019-11-11 18:00","당일"]
[237,"경기","성남","오포모현#1 T/L","154kV 오포-모현#1T/L 항공장애표시구 설치공사","0 항공장애표시구 설치 : 5-6호 등 3개소","2019-11-08 12:00","2019-11-09 18:00","2019-11-08 12:00","2019-11-09 18:00","연속"]
[238,"경기","성남","모현용인#1 T/L","154kV 모현E/C #3M.Tr 증설공사","ㅇ154kV M.Tr 신설 x 1Bank ㅇ154kV GIS x 4CCT(1M, 2BS, 1BT) ㅇ22.9kV E-GIS x 4CCT(1M, 2BS, 1BT)","2019-11-25 09:00","2019-11-26 18:00","2019-11-25 09:00","2019-11-26 18:00","연속"]
[239,"경기","성남","모현용인#1 T/L","154kV 모현E/C #3M.Tr 증설공사","ㅇ154kV M.Tr 신설 x 1Bank ㅇ154kV GIS x 4CCT(1M, 2BS, 1BT) ㅇ22.9kV E-GIS x 4CCT(1M, 2BS, 1BT)","2019-11-15 09:00","2019-11-16 18:00","2019-11-15 09:00","2019-11-16 18:00","연속"]
[240,"경기","성남","모현S/S 154kV #65 BUS","154kV 모현E/C #3M.Tr 증설공사","ㅇ154kV M.Tr 신설 x 1Bank ㅇ154kV GIS x 4CCT(1M, 2BS, 1BT) ㅇ22.9kV E-GIS x 4CCT(1M, 2BS, 1BT)","2019-11-21 09:00","2019-11-30 18:00","2019-11-21 09:00","2019-11-30 18:00","연속"]
[241,"경기","성남","모현용인#1 T/L","154kV 모현-용인#1T/L 항공장애표시구 설치공사","0 항공장애표시구 설치 : 3-4호 등 14개소 39개","2019-11-04 07:00","2019-11-08 12:00","2019-11-04 07:00","2019-11-08 12:00","연속"]
[242,"경기","성남","모현S/S 154kV #65 BUS","154kV 모현E/C #3M.Tr 증설공사","ㅇ154kV M.Tr 신설 x 1Bank ㅇ154kV GIS x 4CCT(1M, 2BS, 1BT) ㅇ22.9kV E-GIS x 4CCT(1M, 2BS, 1BT)","2019-11-06 14:00","2019-11-08 18:00","취소","취소","연속"]
[243,"경기","성남","병점S/S 154kV 병점-에어T/L GIS","GIS 보통점검","GIS 보통점검","2019-11-08 09:00","2019-11-08 18:00","취소","취소","당일"]
[244,"경기","성남","서판교S/S 154kV #60 BUS","154kV 서판교S/S SW 신규수용공사 최초가압","○ 서판교S/S 증설설비 최초가압","2019-11-11 09:00","2019-11-11 14:00","취소","취소","당일"]
[245,"경기","성남","서판교S/S 154kV #65 BUS","154kV 서판교S/S SW 신규수용공사 최초가압","○ 서판교S/S 증설설비 최초가압","2019-11-11 14:00","2019-11-12 18:00","취소","취소","연속"]
[246,"경기","성남","서판교중원#2 T/L","154kV 서판교S/S SW 신규수용공사(서판교-수자원T/L)","○ 154kV 서판교S/S SW 증설(서판교-수자원T/L) - 154kV GIS(2000A, 50kA) 1CCT","2019-11-11 09:00","2019-11-12 18:00","취소","취소","연속"]
[247,"경기","성남","서판교S/S 154kV #65 BUS","서판교S/S 170kV GIS 설치공사","○ 서판교-수자원T/L용 GIS 준공시험(#65BUS)","2019-11-05 09:00","2019-11-05 18:00","취소","취소","당일"]
[248,"경기","성남","서판교S/S 154kV #60 BUS","서판교S/S 170kV GIS 설치공사","○ 서판교-수자원T/L용 GIS 준공시험(#60BUS)","2019-11-04 09:00","2019-11-04 18:00","취소","취소","당일"]
[249,"경기","성남","기흥신갈#2 T/L","신갈 154kV GIS 대체","신갈 GIS 대체","2019-11-04 09:00","2019-11-22 18:00","2019-11-04 09:00","2019-11-22 18:00","연속"]
[250,"경기","성남","기흥신갈#1 T/L","신갈 154kV GIS 대체 안전이격","신갈 154kV GIS 대체 안전이격","2019-11-04 09:00","2019-11-05 18:00","2019-11-04 09:00","2019-11-05 18:00","연속"]
[251,"경기","성남","기흥신갈#2 T/L","신갈 154kV GIS 대체 안전이격","신갈 154kV GIS 대체 안전이격","2019-11-25 09:00","2019-11-26 18:00","취소","취소","연속"]
[252,"경기","성남","신갈S/S 154kV #60 BUS","신갈 154kV GIS 대체","신갈 GIS 대체","2019-11-25 09:00","2019-12-01 18:00","취소","취소","연속"]
[253,"경기","성남","신갈S/S 154kV #65 BUS","신갈 154kV GIS 대체","신갈 GIS 대체","2019-11-18 09:00","2019-11-22 18:00","취소","취소","연속"]
[254,"경기","성남","농서신갈#1 T/L","신갈 154kV GIS 대체 안전이격","신갈 154kV GIS 대체 안전이격","2019-11-15 09:00","2019-11-16 18:00","취소","취소","연속"]
[255,"경기","성남","신갈S/S 154kV #60 BUS","신갈 154kV GIS 대체","신갈 GIS 대체","2019-11-11 09:00","2019-11-17 18:00","취소","취소","연속"]
[256,"경기","성남","신갈S/S 154kV #65 BUS","신갈 154kV GIS 대체","신갈 GIS 대체","2019-11-04 09:00","2019-11-10 18:00","취소","취소","연속"]
[257,"경기","성남","농서신갈#1 T/L","신갈 154kV GIS 대체 안전이격","신갈 154kV GIS 대체 안전이격","2019-11-04 09:00","2019-11-05 18:00","취소","취소","연속"]
[258,"경기","성남","기흥신갈#1 T/L","신갈 154kV GIS 대체 안전이격","신갈 154kV GIS 대체 안전이격","2019-11-15 09:00","2019-11-16 18:00","2019-11-15 09:00","2019-11-16 18:00","연속"]
[259,"경기","성남","농서신갈#1 T/L","신갈 154kV GIS 대체","신갈 GIS 대체","2019-11-25 09:00","2019-12-20 18:00","2019-11-25 09:00","2019-12-20 18:00","연속"]
[260,"경기","성남","신갈S/S 154kV #60-#65 BUS TIE GIS","신갈 154kV GIS 대체","신갈 GIS 대체","2019-11-25 09:00","2019-12-20 18:00","2019-11-25 09:00","2019-12-20 18:00","연속"]
[261,"경기","성남","신성남정자#1 T/L","유압UNIT 점검 (제작사)","유압UNIT 점검 (제작사)","2019-11-04 09:00","2019-11-04 18:00","2019-11-04 09:00","2019-11-04 18:00","당일"]
[262,"경기","성남","신수원S/S 154kV 비오씨T/L GIS","GIS 보통점검","GIS 보통점검","2019-10-02 09:00","2019-10-02 18:00","취소","취소","당일"]
[263,"경기","성남","신수원S/S 154kV 삼반#1T/L GIS","GIS 보통점검","GIS 보통점검","2019-11-04 09:00","2019-11-04 18:00","취소","취소","당일"]
[264,"경기","성남","신수원S/S 154kV 삼반#2T/L GIS","GIS 보통점검","GIS 보통점검","2019-11-05 09:00","2019-11-05 18:00","취소","취소","당일"]
[265,"경기","성남","동반#1T/L CB","GIS 보통점검","GIS 보통점검 LA 하자점검","2019-11-06 09:00","2019-11-06 18:00","취소","취소","당일"]
[266,"경기","성남","동반#2T/L CB","GIS 보통점검","GIS 보통점검 LA 보통점검","2019-11-07 09:00","2019-11-07 18:00","취소","취소","당일"]
[267,"경기","성남","신수원S/S 154kV 신수원-프렉스#2T/L GIS","GIS 보통점검","GIS 보통점검","2019-11-11 09:00","2019-11-11 18:00","취소","취소","당일"]
[268,"경기","성남","신용인동백#2 T/L","154kV 신용인-용인T/L OPGW 증설공사","용인S/S~신용인S/S간 OPGW(24C→48C) 8.814km 교체","2019-11-11 07:00","2019-11-12 18:00","취소","취소","연속"]
[269,"경기","성남","신용인기흥#2 T/L","154kV 신용인-용인T/L OPGW 증설공사","용인S/S~신용인S/S간 OPGW(24C→48C) 8.814km 교체","2019-11-11 07:00","2019-11-12 18:00","취소","취소","연속"]
[270,"경기","성남","신용인용인#1 T/L","154kV 신용인-용인T/L OPGW 증설공사","용인S/S~신용인S/S간 OPGW(24C→48C) 8.814km 교체","2019-11-27 07:00","2019-12-03 18:00","취소","취소","연속"]
[271,"경기","성남","용인남사#1 T/L","154kV 신용인-용인T/L OPGW 증설공사","용인S/S~신용인S/S간 OPGW(24C→48C) 8.814km 교체","2019-11-27 07:00","2019-11-28 18:00","취소","취소","연속"]
[272,"경기","직할","남수원S/S 154kV #1 BUS","남수원S/S 154kV 장기사용 GIS 교체공사","서서울2남수원#2T/L 및 #1M.Tr 1차 GIS 교체","2019-11-12 09:00","2019-11-12 18:00","취소","취소","연속"]
[273,"경기","직할","봉담남수원#1T/L","남수원S/S 154kV 장기사용 GIS 교체공사","서서울2남수원#2T/L 및 #1M.Tr 1차 GIS 교체","2019-11-11 09:00","2019-11-12 09:00","2019-11-11 09:00","2019-11-12 09:00","연속"]
[274,"경기","직할","동수원S/S 154kV #2 BUS TIE GIS","19년 직할 변전협력회사 총액공사","동수원S/S 6100,6200GIS 초기점검","2019-11-12 14:00","2019-11-12 18:00","취소","취소","당일"]
[275,"경기","직할","동수원S/S 154kV #60-61 SEC GIS","19년 직할 변전협력회사 총액공사","동수원S/S 60-61,65-66 GIS 초기점검","2019-11-13 09:00","2019-11-13 14:00","취소","취소","당일"]
[276,"경기","직할","동수원S/S 154kV #1 BUS TIE GIS","19년 직할 변전협력회사 총액공사","동수원S/S 6100,6200GIS 초기점검","2019-11-12 09:00","2019-11-12 14:00","취소","취소","당일"]
[277,"경기","직할","동수원S/S 154kV #65-66 SEC GIS","19년 직할 변전협력회사 총액공사","동수원S/S 60-61,65-66 GIS 초기점검","2019-11-13 14:00","2019-11-13 18:00","취소","취소","당일"]
[278,"경기","직할","동수원우만#1 T/L","19-20년 지중송전 위탁정비공사","OF 케이블 절연유 채취밸브 설치 및 절연유 채유","2019-11-18 09:00","2019-11-19 18:00","취소","취소","당일"]
[279,"경기","직할","동수원우만#2 T/L","19-20년 지중송전 위탁정비공사","OF 케이블 절연유 채취밸브 설치 및 절연유 채유","2019-11-25 09:00","2019-11-26 18:00","취소","취소","당일"]
[280,"경기","직할","발안S/S 154kV #65 BUS","발안S/S #5M.Tr 증설","GIS * 1CCT 설치","2019-11-11 09:00","2019-11-20 17:00","취소","취소","연속"]
[281,"경기","직할","발안구문천#1 T/L","발안S/S #5M.Tr 증설","GIS * 1CCT 설치","2019-11-09 17:00","2019-11-10 17:00","취소","취소","연속"]
[282,"경기","직할","발안S/S 154kV #60 BUS","발안S/S #5M.Tr 증설","GIS * 1CCT 설치","2019-11-05 09:00","2019-11-10 17:00","취소","취소","연속"]
[283,"경기","직할","남수원발안#1 T/L","발안S/S #5M.Tr 증설","GIS * 1CCT 설치","2019-11-05 09:00","2019-11-29 18:00","취소","취소","당일"]
[284,"경기","직할","발안S/S 154kV #60 BUS","발안S/S #5M.Tr 증설","GIS * 1CCT 설치","2019-11-21 09:00","2019-11-29 17:00","취소","취소","연속"]
[285,"경기","직할","발안구문천#1 T/L","발안S/S #5M.Tr 증설","GIS * 1CCT 설치","2019-11-19 17:00","2019-11-20 17:00","취소","취소","연속"]
[286,"경기","직할","남수원발안#1 T/L","2019년 직할 154kV GIS 정밀점검공사","발안S/S 남수원-발안#1T/L GIS 정밀점검공사","2019-11-28 09:00","2019-11-30 18:00","취소","취소","연속"]
[287,"경기","직할","발안향남#1 T/L","2019년 직할 154kV GIS 정밀점검공사","발안S/S 발안-향남#1T/L GIS 정밀점검공사","2019-11-22 09:00","2019-11-24 18:00","취소","취소","연속"]
[288,"경기","직할","발안S/S 154kV #65 BUS","2019년 직할 154kV GIS 정밀점검공사","발안S/S 남수원-발안#1T/L GIS 정밀점검공사(무부하가압)","2019-11-29 14:00","2019-11-30 18:00","취소","취소","연속"]
[289,"경기","직할","발안향남#1 T/L","2019년 직할 154kV GIS 정밀점검공사","발안S/S 남수원-발안#1T/L GIS 정밀점검공사(무부하가압)","2019-11-29 14:00","2019-11-30 18:00","취소","취소","연속"]
[290,"경기","직할","발안S/S 154kV #65 BUS","2019년 직할 154kV GIS 정밀점검공사","발안S/S 발안-향남#2T/L GIS 정밀점검공사(DS점검)","2019-11-26 14:00","2019-11-27 18:00","취소","취소","연속"]
[291,"경기","직할","남수원발안#2 T/L","2019년 직할 154kV GIS 정밀점검공사","발안S/S 발안-향남#2T/L GIS 정밀점검공사(DS점검)","2019-11-26 14:00","2019-11-27 18:00","취소","취소","연속"]
[292,"경기","직할","발안S/S 154kV #60 BUS","2019년 직할 154kV GIS 정밀점검공사","발안S/S 발안-향남#2T/L GIS 정밀점검공사(DS점검)","2019-11-25 09:00","2019-11-26 14:00","취소","취소","연속"]
[293,"경기","직할","남수원발안#1 T/L","2019년 직할 154kV GIS 정밀점검공사","발안S/S 발안-향남#1T/L GIS 정밀점검공사(무부하가압)","2019-11-23 14:00","2019-11-24 18:00","취소","취소","연속"]
[294,"경기","직할","발안S/S 154kV #65 BUS","2019년 직할 154kV GIS 정밀점검공사","발안S/S 발안-향남#1T/L GIS 정밀점검공사(DS점검)","2019-11-23 14:00","2019-11-24 18:00","취소","취소","연속"]
[295,"경기","직할","발안S/S 154kV #60 BUS","2019년 직할 154kV GIS 정밀점검공사","발안S/S 발안-향남#1T/L GIS 정밀점검공사(DS점검)","2019-11-22 09:00","2019-11-23 14:00","취소","취소","연속"]
[296,"경기","직할","발안향남#2 T/L","2019년 직할 154kV GIS 정밀점검공사","발안S/S 발안-향남#2T/L GIS 정밀점검공사","2019-11-25 09:00","2019-11-27 18:00","취소","취소","연속"]
[297,"경기","직할","서수원S/S 154kV #65 GIS BUS","2019년 직할 154kV GIS 정밀점검공사","서수원S/S #4M.Tr 1차 GIS 정밀점검공사(DS점검)","2019-11-05 14:00","2019-11-06 18:00","취소","취소","연속"]
[298,"경기","직할","서수원S/S 154kV #60 GIS BUS","2019년 직할 154kV GIS 정밀점검공사","서수원S/S #4M.Tr 1차 GIS 정밀점검공사(DS점검)","2019-11-04 09:00","2019-11-05 14:00","취소","취소","연속"]
[299,"경기","직할","서수원율전#1 T/L","2019년 직할 154kV GIS 정밀점검공사","서수원S/S #4M.Tr 1차 GIS 정밀점검공사(무부하가압)","2019-11-05 14:00","2019-11-06 18:00","2019-11-13 14:00","2019-11-14 18:00","연속"]
[300,"경기","직할","세교S/S 154kV #61-#66 BUS TIE GIS","19년 직할 변전협력회사 총액공사","세교S/S 6200,4200 GIS 초기점검","2019-11-07 09:00","2019-11-07 14:00","취소","취소","당일"]
[301,"경기","직할","세교S/S 154kV #65-#66 SEC GIS","19년 직할 변전협력회사 총액공사","세교S/S 60-61,65-66 GIS 초기점검","2019-11-08 14:00","2019-11-08 18:00","취소","취소","당일"]
[302,"경기","직할","세교S/S 154kV #60-#61 SEC GIS","19년 직할 변전협력회사 총액공사","세교S/S 60-61,65-66 GIS 초기점검","2019-11-08 09:00","2019-11-08 14:00","취소","취소","당일"]
[303,"경기","직할","의왕S/S 154kV #60-65 BUS TIE GIS","19년 직할 변전협력회사 총액공사","의왕S/S 6100 BUS TIE 초기점검","2019-11-19 09:00","2019-11-19 18:00","취소","취소","당일"]
[304,"경기","직할","호매실S/S 154kV #60-#61 SEC GIS","19년 직할 변전협력회사 총액공사","호매실S/S 60-61,65-66 GIS 초기점검","2019-11-08 09:00","2019-11-08 14:00","취소","취소","당일"]
[305,"경기","직할","호매실S/S 154kV #65-#66 SEC GIS","19년 직할 변전협력회사 총액공사","호매실S/S 60-61,65-66 GIS 초기점검","2019-11-08 14:00","2019-11-08 18:00","취소","취소","당일"]
[306,"경기","직할","호매실S/S 154kV #61-#66 BUS TIE GIS","19년 직할 변전협력회사 총액공사","호매실S/S 6200, 4200 초기점검","2019-11-06 09:00","2019-11-06 14:00","취소","취소","당일"]
[307,"경기","직할","화성발안#1 T/L","2019년 직할 154kV GIS 정밀점검공사","화성S/S 화성-장덕T/L GIS 정밀점검공사(무부하가압)","2019-11-19 14:00","2019-11-20 18:00","2019-11-19 14:00","2019-11-20 18:00","연속"]
[308,"경기","직할","화성S/S 154kV #65 BUS","2019년 직할 154kV GIS 정밀점검공사","화성S/S 화성-장덕T/L GIS 정밀점검공사(DS점검)","2019-11-19 14:00","2019-11-20 18:00","2019-11-19 14:00","2019-11-20 18:00","연속"]
[309,"경기","직할","화성S/S 154kV #60 BUS","2019년 직할 154kV GIS 정밀점검공사","화성S/S 화성-장덕T/L GIS 정밀점검공사(DS점검)","2019-11-18 10:00","2019-11-19 14:00","2019-11-18 10:00","2019-11-19 14:00","연속"]
[310,"경기","직할","화성장덕 T/L","2019년 직할 154kV GIS 정밀점검공사","화성S/S 화성-장덕T/L GIS 정밀점검공사","2019-11-18 10:00","2019-11-20 18:00","취소","취소","연속"]
[311,"경기","직할","화성수촌#1 T/L","2019년 직할 154kV GIS 정밀점검공사","화성S/S #62Sh.C GIS 정밀점검공사(무부하가압)","2019-11-15 14:00","2019-11-16 18:00","2019-11-15 14:00","2019-11-16 18:00","연속"]
[312,"경기","직할","화성남양#2 T/L","19년 직할 변전협력회사 총액공사","화성S/S 화성-남양#2T/L GIS 조작시험","2019-11-02 09:00","2019-11-02 18:00","2019-11-02 09:00","2019-11-02 18:00","당일"]
[313,"경기","직할","화성S/S 154kV #66-#67 SEC GIS","19년 직할 변전협력회사 총액공사","화성S/S 6300,61-62,66-67 GIS 조작시험","2019-11-26 15:00","2019-11-26 18:00","2019-11-26 15:00","2019-11-26 18:00","당일"]
[314,"경기","직할","화성S/S 154kV #61-#62 SEC GIS","19년 직할 변전협력회사 총액공사","화성S/S 6300,61-62,66-67 GIS 조작시험","2019-11-26 12:00","2019-11-26 15:00","2019-11-26 12:00","2019-11-26 15:00","당일"]
[315,"경기","직할","화성S/S 154kV #62-#67 BUS TIE GIS","19년 직할 변전협력회사 총액공사","화성S/S 6300,61-62,66-67 GIS 조작시험","2019-11-26 09:00","2019-11-26 12:00","2019-11-26 09:00","2019-11-26 12:00","당일"]
[316,"경기","직할","화성수촌#1 T/L","19년 직할 변전협력회사 총액공사","화성S/S 화성-수촌#1,2T/L LA 하자점검","2019-11-21 09:00","2019-11-21 14:00","2019-11-21 09:00","2019-11-21 14:00","당일"]
[317,"경기","직할","화성수촌#2 T/L","19년 직할 변전협력회사 총액공사","화성S/S 화성-수촌#1,2T/L LA 하자점검","2019-11-21 14:00","2019-11-21 18:00","2019-11-21 14:00","2019-11-21 18:00","당일"]
[318,"경기","직할","화성발안#2 T/L","19년 직할 변전협력회사 총액공사","화성S/S 화성-발안#2T/L 보호반대체, LA보통점검 발안S/S 화성-발안#2T/L 보호반대체","2019-11-27 09:00","2019-11-29 18:00","2019-11-13 09:00","2019-11-15 18:00","당일"]
[319,"경기","직할","화성남양#1 T/L","345kV 신안산분기T/L OPGW시설공사","공사장소 : 화성S/S-No.2~No.56~신안산S/S 시설내역: OPGW 120㎟ 24C SM 17.566km, 48C SM 4.113㎞ 시설","2019-11-16 07:00","2019-11-16 18:00","2019-11-16 07:00","2019-11-16 18:00","연속"]
[320,"경기","직할","화성마도 T/L","군포전력 송전정비회사 총액공사","345kV 화성평택TPT/L 활선애자청소(21기) 관련 4회선 병가구간","2019-11-14 08:00","2019-11-14 18:00","취소","취소","매일"]
[321,"경기","직할","화성장덕 T/L","군포전력 송전정비회사 총액공사","345kV 화성평택TPT/L 활선애자청소(21기) 관련 4회선 병가구간","2019-11-14 08:00","2019-11-14 18:00","취소","취소","매일"]
[322,"경기","직할","화성S/S 154kV #67 Sh.C","19년 직할 변전협력회사 총액공사","화성S/S #67,68Sh.C GIS 조작시험","2019-11-12 09:00","2019-11-12 14:00","취소","취소","당일"]
[323,"경기","직할","화성S/S 154kV #68 Sh.C","19년 직할 변전협력회사 총액공사","화성S/S #67,68Sh.C GIS 조작시험","2019-11-12 14:00","2019-11-12 18:00","취소","취소","당일"]
[324,"경기","직할","화성S/S 154kV #62 Sh.C","2019년 직할 154kV GIS 정밀점검공사","화성S/S #62Sh.C GIS 정밀점검공사","2019-11-11 09:00","2019-11-13 18:00","취소","취소","연속"]
[325,"경기","직할","화성S/S 154kV #60 BUS","2019년 직할 154kV GIS 정밀점검공사","화성S/S #62Sh.C GIS 정밀점검공사(DS점검)","2019-11-14 09:00","2019-11-15 14:00","2019-11-14 09:00","2019-11-15 14:00","연속"]
[326,"경기","직할","화성S/S 154kV #65 BUS","2019년 직할 154kV GIS 정밀점검공사","화성S/S #62Sh.C GIS 정밀점검공사(DS점검)","2019-11-15 14:00","2019-11-16 18:00","2019-11-15 14:00","2019-11-16 18:00","연속"]
[327,"경기","평택","고덕S/S 154kV #61 BUS","154kV 송탄, 진위#1,2T/L DS 조작기 개선","154kV 송탄,진위#1,2T/L DS 조작기 개선 - DS 조작메카니즘 부품 교체","2019-11-19 09:00","2019-11-19 18:00","취소","취소","당일"]
[328,"경기","평택","고덕S/S 154kV #65 BUS","154kV 평택#1,2T/L 및 #1,2 M.Tr DS 조작기 개선","154kV 평택#1,2T/L 및 #1,2 M.Tr DS 조작기 개선 - DS 조작메카니즘 부품 교체","2019-11-26 09:00","2019-11-26 18:00","취소","취소","당일"]
[329,"경기","평택","고덕S/S 154kV #66 BUS","154kV 송탄, 진위#1,2T/L DS 조작기 개선","154kV 진위#1,2T/L DS 조작기 개선 - DS 조작메카니즘 부품 교체","2019-11-20 09:00","2019-11-20 18:00","취소","취소","당일"]
[330,"경기","평택","고덕평택#2 T/L","고덕S/S 154kV SW 증설공사 (고덕-동평택#1,2T/L)","ㅇ 고덕S/S 154kV SW #65BUS측 기기설치 - 고덕-동평택#1,2 T/L ㅇ 154kV #65BUS측 무부하 가압","2019-11-28 18:00","2019-11-29 18:00","취소","취소","연속"]
[331,"경기","평택","고덕S/S 154kV 고덕-진위#2T/L CB","154kV 진위#1,2T/L DS 조작기 개선","154kV 진위#2T/L DS 조작기 개선 - 진위#2T/L DS 6C1 부품교체","2019-11-19 09:00","2019-11-19 10:30","2019-11-19 09:00","2019-11-19 10:30","당일"]
[332,"경기","평택","고덕S/S 154kV 고덕-진위#1T/L CB","154kV 진위#1,2T/L DS 조작기 개선","154kV 진위#1T/L DS 조작기 개선 - 진위#1T/L DS 6B1 부품교체","2019-11-19 10:30","2019-11-19 12:00","2019-11-19 10:30","2019-11-19 12:00","당일"]
[333,"경기","평택","고덕S/S 154kV 고덕-송탄#1T/L CB","154kV 송탄#1,2T/L DS 조작기 개선","154kV 송탄#1T/L DS 조작기 개선 - 송탄#1T/L DS 6D1 부품교체","2019-11-19 13:00","2019-11-19 14:30","2019-11-19 13:00","2019-11-19 14:30","당일"]
[334,"경기","평택","고덕S/S 154kV 고덕-송탄#2T/L CB","154kV 송탄#1,2T/L DS 조작기 개선","154kV 송탄#2T/L DS 조작기 개선 - 송탄#2T/L DS 6F1 부품교체","2019-11-19 14:30","2019-11-19 16:00","2019-11-19 14:30","2019-11-19 16:00","당일"]
[335,"경기","평택","고덕S/S 345KV #2 M.TR 2차 CB","345kV #2 M.Tr 2차 및 60-61-01 DS 조작기 개선","345kV #2 M.Tr 2차 DS 6241 및 60-61-1 조작기 개선 - 345kV #2 M.Tr 2차 DS 6241, 60-61-1, 6101 부품교체","2019-11-06 14:30","2019-11-06 18:00","취소","취소","당일"]
[336,"경기","평택","고덕S/S 345KV #1 M.TR 2차 CB","345kV #1 M.Tr 2차 DS 6141 조작기 개선","345kV #1 M.Tr 2차 DS 6141 조작기 개선 - 345kV #1 M.Tr 2차 DS 6141 부품교체","2019-11-06 13:00","2019-11-06 14:30","취소","취소","당일"]
[337,"경기","평택","고덕S/S 154kV 고덕-평택#2T/L CB","154kV 평택#1,2T/L DS 조작기 개선","154kV 평택#2T/L DS 조작기 개선 - 평택#2T/L DS 6A1 부품교체","2019-11-26 10:30","2019-11-26 12:00","취소","취소","당일"]
[338,"경기","평택","고덕S/S 154kV 고덕-평택#1T/L CB","154kV 평택#1,2T/L DS 조작기 개선","154kV 평택#1T/L DS 조작기 개선 - 평택#1T/L DS 691 부품교체","2019-11-26 09:00","2019-11-26 10:30","취소","취소","당일"]
[339,"경기","평택","고덕S/S 154kV #65 BUS","고덕S/S 154kV SW 증설공사 (고덕-동평택#1,2T/L)","ㅇ 고덕S/S 154kV SW #65BUS측 기기설치 - 고덕-동평택#1,2 T/L ㅇ 154kV #65BUS측 무부하 가압","2019-11-25 09:00","2019-11-29 18:00","취소","취소","연속"]
[340,"경기","평택","고덕S/S 154kV 고덕-송탄#2T/L CB","154kV 송탄#1,2T/L DS 조작기 개선","154kV 송탄#2T/L DS 조작기 개선 - 송탄#2T/L DS 6F2 부품교체","2019-11-20 14:30","2019-11-20 16:00","2019-11-20 14:30","2019-11-20 16:00","당일"]
[341,"경기","평택","고덕S/S 154kV 고덕-송탄#1T/L CB","154kV 송탄#1,2T/L DS 조작기 개선","154kV 송탄#1T/L DS 조작기 개선 - 송탄#1T/L DS 6D2 부품교체","2019-11-20 13:00","2019-11-20 14:30","2019-11-20 13:00","2019-11-20 14:30","당일"]
[342,"경기","평택","고덕S/S 154kV 고덕-진위#1T/L CB","154kV 진위#1,2T/L DS 조작기 개선","154kV 진위#2T/L DS 조작기 개선 - 진위#2T/L DS 6B2 부품교체","2019-11-20 10:30","2019-11-20 12:00","2019-11-20 10:30","2019-11-20 12:00","당일"]
[343,"경기","평택","고덕S/S 154kV 고덕-진위#2T/L CB","154kV 진위#1,2T/L DS 조작기 개선","154kV 진위#2T/L DS 조작기 개선 - 진위#2T/L DS 6C2 부품교체","2019-11-20 09:00","2019-11-20 10:30","2019-11-20 09:00","2019-11-20 10:30","당일"]
[344,"경기","평택","서운안성#2 T/L","154kV 서운안성T/L 송전선로 정밀점검","1. 작업내용 : 송전선로 정밀점검 2. 작업구간 - #1T/L : 안성S/S~28호 - #2T/L : 안성S/S~42호","2019-11-27 09:00","2019-11-29 18:00","취소","취소","연속"]
[345,"경기","평택","서운안성#1 T/L","154kV 서운안성T/L 송전선로 정밀점검","1. 작업내용 : 송전선로 정밀점검 2. 작업구간 - #1T/L : 안성S/S~28호 - #2T/L : 안성S/S~42호","2019-11-25 09:00","2019-11-26 18:00","취소","취소","연속"]
[346,"경기","평택","평택전철#2T/L CB","송탄S/S 154kV 평택전철#2T/L GIS 보통점검","송탄S/S 154kV 평택전철#2T/L GIS 보통점검","2019-11-21 10:00","2019-11-21 18:00","취소","취소","당일"]
[347,"경기","평택","평택전철#1T/L CB","송탄S/S 154kV 평택전철#1T/L GIS 보통점검","송탄S/S 154kV 평택전철#1T/L GIS 보통점검","2019-11-20 10:00","2019-11-20 18:00","취소","취소","당일"]
[348,"경기","평택","포승청북 T/L","154kV 포승-청북T/L PD집합반 설치공사","154kV 포승-청북T/L PD집합반 설치공사 - 청북C/H PD 센서 설치","2019-11-01 09:00","2019-11-01 17:00","취소","취소","당일"]
[349,"경기","평택","포승평택TP#1 T/L","군포전력 송전정비회사 총액공사","345kV 화성평택TPT/L 활선애자청소(21기) 관련 4회선 병가 하단구간","2019-11-11 08:00","2019-11-11 18:00","취소","취소","매일"]
[350,"경기","평택","포승평택TP#2 T/L","군포전력 송전정비회사 총액공사","345kV 화성평택TPT/L 활선애자청소(21기) 관련 4회선 병가 하단구간","2019-11-11 08:00","2019-11-11 18:00","취소","취소","매일"]
[351,"경기","평택","포승S/S 154kV #60 BUS","포승S/S #2M.Tr 1차 GIS 정밀점검공사 관련 무부하가압","포승S/S #2M.Tr 1차 GIS 정밀점검공사 관련 무부하가압","2019-11-06 09:00","2019-11-07 18:00","취소","취소","연속"]
[352,"강원","강릉","속초간성#2 T/L","2019 변전협력회사 총액공사","170kV GIS 보통점검, LA 대체","2019-11-07 10:00","2019-11-07 18:00","2019-11-07 10:00","2019-11-07 18:00","당일"]
[353,"강원","강릉","속초간성#1 T/L","2019 변전협력회사 총액공사","170kV GIS 보통점검, LA 대체","2019-11-05 10:00","2019-11-05 18:00","2019-11-05 10:00","2019-11-05 18:00","당일"]
[354,"강원","강릉","신양양양양#2 T/L","154kV 강릉-북강릉-주문진-양양간 OPGW교체공사","- OPGW 3.592km 교체 - 항공장애표시구 64개 철거 - 항공장애표시구 86개 설치","2019-11-08 08:00","2019-11-11 18:00","2019-11-08 08:00","2019-11-11 18:00","연속"]
[355,"강원","강릉","신양양양양#1 T/L","154kV 강릉-북강릉-주문진-양양간 OPGW교체공사","- OPGW 26.364km 교체 - 항공장애표시구 55개 철거 - 항공장애표시구 55개 설치","2019-11-02 08:00","2019-11-04 18:00","2019-11-02 08:00","2019-11-04 18:00","연속"]
[356,"강원","강릉","주진평창#1 T/L","154kV 주진평창T/L 안전이격확보공사","○ 철탑4기 설치 및 철거 - 대상 : 154kV 주진평창T/L No.26~29","2019-11-11 07:00","2019-11-17 18:00","2019-11-11 07:00","2019-11-17 18:00","연속"]
[357,"강원","강릉","주진평창#2 T/L","154kV 주진평창T/L 안전이격확보공사","○ 철탑4기 설치 및 철거 - 대상 : 154kV 주진평창T/L No.26~29","2019-11-18 07:00","2019-11-24 18:00","2019-11-18 07:00","2019-11-24 18:00","연속"]
[358,"강원","강릉","주진평창#1 T/L","154kV 주진평창T/L 안전이격확보공사","○ 철탑4기 설치 및 철거 - 대상 : 154kV 주진평창T/L No.26~29","2019-11-11 07:00","2019-11-19 18:00","취소","취소","연속"]
[359,"강원","강릉","주진평창#2 T/L","154kV 주진평창T/L 안전이격확보공사","○ 철탑4기 설치 및 철거 - 대상 : 154kV 주진평창T/L No.26~29","2019-11-11 07:00","2019-11-19 18:00","취소","취소","연속"]
[360,"강원","동해","동해동영월 T/L","2018~2019년 동해전력지사 송전정비협력회사 총액공사","스페이서 설치","2019-11-25 09:00","2019-11-27 18:00","2019-11-25 09:00","2019-11-27 18:00","연속"]
[361,"강원","동해","동해정선 T/L","2018~2019년 동해전력지사 송전정비협력회사 총액공사","스페이서 설치","2019-11-18 09:00","2019-11-20 18:00","2019-11-18 09:00","2019-11-20 18:00","연속"]
[362,"강원","동해","울진삼척GP#2 T/L","18-19태백전력지사 송전정비회사 총액공사","154kV 울진-삼척GP #2T/L No.2 ~ No.3간 전선 교체작업","2019-11-19 09:00","2019-11-21 18:00","2019-11-19 09:00","2019-11-21 18:00","연속"]
[363,"강원","원주","남원주원주#2 T/L","2019년 하반기 장기미동작 차단기 동작시험","2019년 하반기 장기미동작 차단기 동작시험","2019-11-04 10:00","2019-11-04 18:00","2019-11-04 10:00","2019-11-04 18:00","당일"]
[364,"강원","원주","홍천남춘천 T/L","2019년 하반기 장기미동작 차단기 동작시험","2019년 하반기 장기미동작 차단기 동작시험","2019-11-05 10:00","2019-11-05 14:00","2019-11-08 10:00","2019-11-08 14:00","당일"]
[365,"강원","원주","홍천S/S 154kV #60-#65 BUS TIE CB","2019년 하반기 장기미동작 차단기 동작시험","2019년 하반기 장기미동작 차단기 동작시험","2019-11-05 14:00","2019-11-05 18:00","2019-11-08 14:00","2019-11-08 18:00","당일"]
[366,"강원","직할","서홍천청평PP T/L","2019년 하반기 장기 미동작 차단기 동작시험","서홍천S/S 154kV 서홍천-청평PP T/L 차단기 동작시험","2019-11-04 10:00","2019-11-04 18:00","2019-11-04 10:00","2019-11-04 18:00","당일"]
[367,"강원","직할","서홍천청평PP T/L","345kV 신가평-포천LNGCC#1T/L 항공장애표시구 설치 병가선로","ㅇ 항공장애표시구 설치 - 작업구간 : 345kV 신가평포천LNGCC#1T/L No.37~41호간 - 병가구간 : 154kV 서홍천청평PP T/L No.19~23호간","2019-11-25 07:00","2019-11-26 18:00","2019-11-25 07:00","2019-11-26 18:00","연속"]
[368,"강원","직할","화천H/P 154kV #60 BUS","2018-2019 강원본부 직할 변전정비 총액공사","○ 장기사용 기타설비 노후대체 - 화천H/P #1 BUS 및 #2 BUS PT A, B, C 교체","2019-11-06 09:00","2019-11-06 18:00","2019-11-06 09:00","2019-11-06 18:00","당일"]
[369,"충북","직할","진천광혜원#1 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","보호배전반 이설(계전기실 → 감시실)","2019-11-28 09:00","2019-11-30 18:00","2019-11-28 09:00","2019-11-30 18:00","연속"]
[370,"충북","직할","서운광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","보호배전반 이설(계전기실 → 감시실)","2019-11-21 09:00","2019-11-23 18:00","2019-11-21 09:00","2019-11-23 18:00","연속"]
[371,"충북","직할","진천광혜원#2 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","보호배전반 이설(계전기실 → 감시실)","2019-11-25 09:00","2019-11-27 18:00","2019-11-25 09:00","2019-11-27 18:00","연속"]
[372,"충북","직할","신진천진천#2 T/L","154kV 신진천-오창T/L 정밀점검(병가안전휴전)","154kV 신진천-오창T/L No.1~2구간 병가안전휴전 (154kV 신진천-진천T/L No.30~31구간 병가)","2019-11-09 09:00","2019-11-09 18:00","취소","취소","당일"]
[373,"충북","직할","신진천S/S 154kV #65 BUS","신진천S/S 154kV #65BUS PT 철공진 방지장치 개선","신진천S/S 154kV #65BUS PT 철공진 방지장치 개선 - Relay PT 결선을 Meter PT로 변경","2019-11-01 10:00","2019-11-01 18:00","2019-11-01 10:00","2019-11-01 18:00","당일"]
[374,"충북","직할","신진천S/S 154kV #62-#67 BUS TIE GIS","'19년 직할 154kV GIS 정밀점검 공사","신진천S/S 154kV #2BUSTIE 보통점검+조작부 정밀점검, GIS 발청보수작업","2019-11-18 10:00","2019-11-19 18:00","2019-11-18 10:00","2019-11-19 18:00","연속"]
[375,"충북","직할","신진천S/S 154kV #65-#66 SEC GIS","'19년 직할 154kV GIS 정밀점검 공사","신진천S/S 154kV #65-#66 SEC GIS 보통점검+조작부 정밀점검, 발청보수","2019-11-21 10:00","2019-11-22 18:00","2019-11-21 10:00","2019-11-22 18:00","연속"]
[376,"충북","청주","남청주청주#2 T/L","154kV 청원-청주T/L 계통정비공사","17호 철탑 교체(1기), 18호 철탑 철거(2기), 전력선교체(4.104C-km)","2019-11-06 08:00","2019-11-08 18:00","2019-11-05 08:00","2019-11-07 18:00","연속"]
[377,"충북","청주","상주보은 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-11-01 07:00","2019-11-02 19:00","2019-11-01 07:00","2019-11-02 19:00","연속"]
[378,"충북","청주","상주보은 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-11-03 07:00","2019-11-04 19:00","2019-11-03 07:00","2019-11-04 19:00","연속"]
[379,"충북","청주","서청주사직#1 T/L","18-19년 청주전력 변전협력회사 총액공사","사직S/S 서청주사직#1T/L 154kV GIS 보통점검 서청주S/S 서청주사직#1T/L 154kV GIS 보통점검","2019-11-17 09:30","2019-11-17 18:00","취소","취소","당일"]
[380,"충북","청주","상주영동 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-11-03 07:00","2019-11-04 19:00","2019-11-03 07:00","2019-11-04 19:00","연속"]
[381,"충북","청주","상주영동 T/L","154kV 상주T/L 안전이격거리 확보공사","154kV 상주T/L 안전이격 확보공사 - 철탑 1기 교체 - 전선교체 : No.86 ~ 88","2019-11-01 07:00","2019-11-02 19:00","2019-11-01 07:00","2019-11-02 19:00","연속"]
[382,"충북","청주","오송북청주#1 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","불량애자 교체 및 아킹혼 철거 - 불량애자 교체 : No. 9. 38 - 아킹혼 철거 : No.20~28, 31 154kV 국사-봉명#1T/L - 전력선 교체 : No.8 ~ 11 - 아킹혼 철거 : No.2, 8 - 불량애자 교체 : No.2, 5, 8","2019-11-30 07:00","2019-12-01 19:00","2019-11-30 07:00","2019-12-01 19:00","연속"]
[383,"충북","청주","오송북청주#1 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","불량애자 교체 및 아킹혼 철거 - 불량애자 교체 : No. 9. 38 - 아킹혼 철거 : No.20~28, 31 154kV 국사-봉명#1T/L - 전력선 교체 : No.5 ~ 8 하단 외측, No.8~11 - 불량애자 교체 : No.8 하단 전원 내측 8번 불량애자 교체 - 아킹혼 철거 : No.1","2019-11-23 07:00","2019-11-24 19:00","2019-11-23 07:00","2019-11-24 19:00","연속"]
[384,"충북","청주","신진천오창#1 T/L","154kV 신진천-오창T/L 정밀점검(한전KPS)","154kV 신진천-오창T/L No.1~48 정밀점검","2019-11-09 08:00","2019-11-10 18:00","취소","취소","매일"]
[385,"충북","청주","신진천오창#2 T/L","154kV 신진천-오창T/L 정밀점검(한전KPS)","154kV 신진천-오창T/L No.1~48 정밀점검","2019-11-02 08:00","2019-11-03 18:00","2019-11-02 08:00","2019-11-03 18:00","매일"]
[386,"충북","청주","신진천오창#1 T/L","154kV 신진천-오창T/L 정밀점검(한전KPS)","154kV 신진천-오창T/L No.1~48 정밀점검","2019-11-16 08:00","2019-11-16 18:00","2019-11-16 08:00","2019-11-16 18:00","당일"]
[387,"충북","충주","신제천영월CC#1 T/L","2018-2019년 송전정비회사 총액공사","애자련 보강 (No.31,51,55,65)","2019-11-18 08:00","2019-11-19 18:00","2019-11-18 08:00","2019-11-19 18:00","매일"]
[388,"충북","충주","신제천영월CC#2 T/L","2018-2019년 송전정비회사 총액공사","애자련 보강 (No.31,51,55,65)","2019-11-20 08:00","2019-11-21 18:00","2019-11-20 08:00","2019-11-21 18:00","매일"]
[389,"충북","충주","왕암가남#1 T/L","154kV 왕암-북충주 등 2개T/L 지장철탑이설공사","제천제3산업단지 조성에 지장이 되는 철탑이설 - 철탑이설 : 6기(4회선 4기, 2회선 2기) - 철탑철거 : 13기(4회선 4기, 2회선 5기, CP주 4기) - 전선교체 : 3.818C-km(240), 3.786C-km(410)","2019-11-23 08:00","2019-11-26 18:00","2019-11-23 08:00","2019-11-26 18:00","연속"]
[390,"충북","충주","왕암충주 T/L","154kV 왕암-북충주 등 2개T/L 지장철탑이설공사","제천제3산업단지 조성에 지장이 되는 철탑이설 - 철탑이설 : 6기(4회선 4기, 2회선 2기) - 철탑철거 : 13기(4회선 4기, 2회선 5기, CP주 4기) - 전선교체 : 3.818C-km(240), 3.786C-km(410)","2019-11-23 08:00","2019-11-26 18:00","2019-11-23 08:00","2019-11-26 18:00","연속"]
[391,"충북","충주","왕암가남#1 T/L","154kV 왕암-북충주 등 2개T/L 지장철탑이설공사","제천제3산업단지 조성에 지장이 되는 철탑이설 - 철탑이설 : 6기(4회선 4기, 2회선 2기) - 철탑철거 : 13기(4회선 4기, 2회선 5기, CP주 4기) - 전선교체 : 3.818C-km(240), 3.786C-km(410)","2019-11-11 08:00","2019-11-16 18:00","2019-11-11 08:00","2019-11-16 18:00","연속"]
[392,"충북","충주","왕암북충주 T/L","154kV 왕암-북충주 등 2개T/L 지장철탑이설공사","제천제3산업단지 조성에 지장이 되는 철탑이설 - 철탑이설 : 6기(4회선 4기, 2회선 2기) - 철탑철거 : 13기(4회선 4기, 2회선 5기, CP주 4기) - 전선교체 : 3.818C-km(240), 3.786C-km(410)","2019-11-11 08:00","2019-11-16 18:00","2019-11-11 08:00","2019-11-16 18:00","연속"]
[393,"충북","충주","왕암가남#2 T/L","왕암S/S 154kV GIS(봉양전철) 설치공사","봉양전철#1TL 건설분 무부하 시험가압","2019-11-29 18:00","2019-11-30 12:00","2019-11-29 18:00","2019-11-30 12:00","연속"]
[394,"충북","충주","왕암가남#2 T/L","154kV 왕암-북충주 등 2개T/L 지장철탑이설공사","제천제3산업단지 조성에 지장이 되는 철탑이설 - 철탑이설 : 6기(4회선 4기, 2회선 2기) - 철탑철거 : 13기(4회선 4기, 2회선 5기, CP주 4기) - 전선교체 : 3.818C-km(240), 3.786C-km(410)","2019-11-17 08:00","2019-11-22 18:00","2019-11-17 08:00","2019-11-22 18:00","연속"]
[395,"충북","충주","왕암충주 T/L","154kV 왕암-북충주 등 2개T/L 지장철탑이설공사","제천제3산업단지 조성에 지장이 되는 철탑이설 - 철탑이설 : 6기(4회선 4기, 2회선 2기) - 철탑철거 : 13기(4회선 4기, 2회선 5기, CP주 4기) - 전선교체 : 3.818C-km(240), 3.786C-km(410)","2019-11-17 08:00","2019-11-22 18:00","2019-11-17 08:00","2019-11-22 18:00","연속"]
[396,"충북","충주","풍동음성#2 T/L","154kV 풍동-음성 등 2개T/L 전선접속개소 전선교체공사","No.21~22 전력선교체","2019-11-14 08:00","2019-11-15 18:00","2019-11-14 08:00","2019-11-15 18:00","연속"]
[397,"충북","충주","충주S/S 154kV #60-#61 BUS SEC GIS","19년 충주전력지사 170kV GIS 정밀점검","GIS 정밀점검(CB)","2019-11-13 09:00","2019-11-14 18:00","2019-11-13 09:00","2019-11-14 18:00","연속"]
[398,"충북","충주","충주풍동 T/L","19년 충주전력지사 170kV GIS 정밀점검","GIS 정밀점검(CB,상부DS)","2019-11-04 09:00","2019-11-05 18:00","2019-11-04 09:00","2019-11-05 18:00","연속"]
[399,"대전충남","대전","신옥천남대전#2 T/L","154kV 신옥천-남대전 등 3개T/L 자기애관 교체공사","154kV 신옥천-남대전#2T/L 자기애관 3상 → 폴리머애관 교체","2019-11-11 09:00","2019-11-14 18:00","2019-11-11 09:00","2019-11-14 18:00","연속"]
[400,"대전충남","대전","신옥천남대전#1 T/L","154kV 신옥천-남대전 등 3개T/L 자기애관 교체공사","154kV 신옥천-남대전#1T/L 자기애관 3상 → 폴리머애관 교체","2019-11-04 09:00","2019-11-07 18:00","2019-11-04 09:00","2019-11-07 18:00","연속"]
[401,"대전충남","대전","신옥천남대전#3 T/L","154kV 신옥천-남대전 등 3개T/L 자기애관 교체공사","154kV 신옥천-남대전#3T/L 자기애관 3상 → 폴리머애관 교체","2019-11-18 09:00","2019-11-21 18:00","2019-11-18 09:00","2019-11-21 18:00","연속"]
[402,"대전충남","대전","신옥천남대전#4 T/L","154kV 신옥천-남대전 등 3개T/L 자기애관 교체공사","154kV 신옥천-남대전#4T/L 자기애관 3상 → 폴리머애관 교체","2019-11-25 09:00","2019-11-28 18:00","2019-11-25 09:00","2019-11-28 18:00","연속"]
[403,"대전충남","서산","신당진당진#1 T/L","당진S/S 154kV측 취약설비 GIS화","154kV 옥외철구형 설비 GIS화 - 옥외설비 철거(GCB, DS, GIDS, LA, CVT 등) - 옥외철구 전력선 교체(CU-&gtAL) 디지털 혼용운영시스템 이설","2019-11-25 08:00","2019-11-29 18:00","취소","취소","연속"]
[404,"대전충남","서산","당진송악#2 T/L","당진S/S 154kV측 취약설비 GIS화","154kV 옥외철구형 설비 GIS화 - 옥외설비 철거(GCB, DS, GIDS, LA, CVT 등) - 옥외철구 전력선 교체(CU-&gtAL) 디지털 혼용운영시스템 이설","2019-11-25 08:00","2019-11-29 18:00","취소","취소","연속"]
[405,"대전충남","서산","서산홍성 T/L","서산P/O OPGW 항공장애표시구 시설공사","OPGW 항공장애표시구 18개 설치","2019-11-09 09:00","2019-11-10 18:00","2019-11-09 09:00","2019-11-10 18:00","매일"]
[406,"대전충남","서산","석문당진화력#2 T/L","19년도 서산P/O 154kV GIS 정밀점검공사","- 석문S/S 154kV 석문-당진화력#2T/L GIS(687) 정밀점검","2019-11-04 09:00","2019-11-06 18:00","2019-11-04 09:00","2019-11-06 18:00","연속"]
[407,"대전충남","서산","당진송악#1 T/L","서산P/O OPGW 항공장애표시구 시설공사","OPGW 항공장애표시구 26개 설치","2019-11-16 09:00","2019-11-17 18:00","2019-11-16 09:00","2019-11-17 18:00","매일"]
[408,"대전충남","서산","합덕송악#2 T/L","서산P/O OPGW 항공장애표시구 시설공사","OPGW 항공장애표시구 26개 설치","2019-11-16 09:00","2019-11-17 18:00","2019-11-16 09:00","2019-11-17 18:00","매일"]
[409,"대전충남","서산","태안태안화력 T/L","태안S/S ~ 태안화력 OPGW 증설공사","장소 : 154kV 서산-태안T/L 태안S/S S/T ∼ No.58(분기) 내역 : 항공장애표시구 47개 시설","2019-11-09 07:30","2019-11-11 18:00","취소","취소","매일"]
[410,"대전충남","서산","서산태안 T/L","태안S/S ~ 태안화력 OPGW 증설공사","장소 : 154kV 서산-태안T/L 태안S/S S/T ∼ No.58(분기) 내역 : OPGW 100SQ/48C 7.202km 증설","2019-11-12 07:00","2019-11-16 18:00","취소","취소","연속"]
[411,"대전충남","서산","해미홍성 T/L","서산P/O OPGW 항공장애표시구 시설공사","OPGW 항공장애표시구 13개 설치","2019-11-23 09:00","2019-11-24 18:00","2019-11-23 09:00","2019-11-24 18:00","매일"]
[412,"대전충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 정밀점검","154kV 조치원-전의T/L 55기 정밀점검 시행","2019-11-04 07:00","2019-11-13 18:00","2019-11-04 07:00","2019-11-13 18:00","매일"]
[413,"대전충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의T/L 정밀점검","154kV 조치원-전의T/L 55기 정밀점검 시행","2019-11-04 07:00","2019-11-13 18:00","2019-11-04 07:00","2019-11-13 18:00","매일"]
[414,"대전충남","아산","장재불당#1 T/L","불당S/S 154kV 장재-불당#1T/L GIS 전자변 교체","불당S/S 154kV 장재-불당#1T/L GIS 전자변 교체","2019-11-13 09:00","2019-11-13 18:00","취소","취소","당일"]
[415,"대전충남","아산","신온양석곡#2 T/L","신온양S/S 신온양-석곡#2T/L GIS 유압 고압호스 교체","신온양S/S 154kV 신온양-석곡#2T/L GIS Hydraulic oil 고압호스 교체","2019-11-04 09:00","2019-11-04 18:00","2019-11-04 09:00","2019-11-04 18:00","당일"]
[416,"대전충남","아산","온양풍세#2 T/L","온양S/S 154kV 온양-풍세#2T/L GIS 전자변 교체","온양S/S 154kV 온양-풍세#2T/L GIS 전자변 교체","2019-11-11 09:00","2019-11-11 18:00","취소","취소","당일"]
[417,"대전충남","아산","인주탕정#1 T/L","154kV 인주-불당 송전선로 C/H 건설공사","154kV 인주-불당 송전선로 C/H 건설공사 - 본선로 작업을 위한 임시선로 구성(가철탑2) 및 가선","2019-11-21 07:00","2019-11-27 18:00","취소","취소","연속"]
[418,"대전충남","아산","서천안탕정#2 T/L","154kV 인주-불당 송전선로 C/H 건설공사","154kV 인주-불당 송전선로 C/H 건설공사 - 본선로 작업을 위한 임시선로 구성(가철탑2) 및 가선","2019-11-21 07:00","2019-11-27 18:00","취소","취소","연속"]
[419,"대전충남","아산","서천안탕정#1 T/L","154kV 인주-불당 송전선로 C/H 건설공사","154kV 인주-불당 송전선로 C/H 건설공사 - 본선로 작업을 위한 임시선로 구성(가철탑2) 및 가선","2019-11-14 07:00","2019-11-20 18:00","취소","취소","연속"]
[420,"대전충남","아산","인주탕정#2 T/L","154kV 인주-불당 송전선로 C/H 건설공사","154kV 인주-불당 송전선로 C/H 건설공사 - 본선로 작업을 위한 임시선로 구성(가철탑2) 및 가선","2019-11-14 07:00","2019-11-20 18:00","2019-11-14 07:00","2019-11-15 18:00","연속"]
[421,"대전충남","아산","신온양한샘#2 T/L","한샘S/S 신온양-한샘#1,2T/L GIS 유압 고압호스 교체","한샘S/S 신온양-한샘#1,2T/L GIS Hydraulic oil 고압호스 교체","2019-11-05 09:00","2019-11-05 18:00","2019-11-05 09:00","2019-11-05 18:00","당일"]
[422,"대전충남","아산","신온양한샘#1 T/L","한샘S/S 154kV #2BUS측 누기개소 보수","○한샘S/S 154kV #2BUS측 누기개소 보수 ○병행) 신온양S/S GIS 유압 고압호스 교체","2019-11-18 09:00","2019-11-20 18:00","2019-11-18 09:00","2019-11-20 18:00","연속"]
[423,"대전충남","청양","보령TP보령CC T/L","현수 불량애자 교체공사","S/T, 1, 37, 38 불량애자 교체","2019-11-21 08:00","2019-11-22 18:00","2019-11-14 07:00","2019-11-14 18:00","매일"]
[424,"대전충남","청양","관창보령CC T/L","현수 불량애자 교체공사","No.8,37,38,1,S/T 불량애자 교체","2019-11-18 08:00","2019-11-20 18:00","2019-11-12 08:00","2019-11-13 18:00","매일"]
[425,"대전충남","청양","관창보령TP T/L","현수 불량애자 교체공사","2, 37, 38 불량애자 교체","2019-11-23 08:00","2019-11-25 18:00","2019-11-15 07:00","2019-11-15 18:00","매일"]
[426,"대전충남","청양","서천대천#1 T/L","154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사","[송전] 154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사 ○ 지지물 1기 설치(신설No.5) ○ 전력선 신설(0.261km), 공중이동(0.233km) ※ 본선로 구성 서천E/C 전력공급","2019-11-15 07:00","2019-11-24 18:00","2019-11-30 07:00","2019-12-09 18:00","연속"]
[427,"대전충남","청양","서천옥산#1 T/L","154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사","[송전] 154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사 ○ 지지물 1기 설치(신설No.5) ○ 전력선 신설(0.261km), 공중이동(0.233km) ※ 본선로 구성 서천E/C 전력공급","2019-11-15 07:00","2019-11-24 18:00","2019-11-30 07:00","2019-12-09 18:00","연속"]
[428,"대전충남","청양","서천대천#2 T/L","154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사","[송전] 154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사 ○ 지지물 1기 설치(신설No.5) ○ 전력선 신설(0.261km), 공중이동(0.233km) ※ 본선로 구성 서천E/C 전력공급","2019-11-05 07:00","2019-11-14 18:00","2019-11-20 07:00","2019-11-29 18:00","연속"]
[429,"대전충남","청양","서천옥산#2 T/L","154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사","[송전] 154kV 옥산-서천 등 2개T/L 지장송전선로 이설공사 ○ 지지물 1기 설치(신설No.5) ○ 전력선 신설(0.261km), 공중이동(0.233km) ※ 본선로 구성 서천E/C 전력공급","2019-11-05 07:00","2019-11-14 18:00","2019-11-20 07:00","2019-11-29 18:00","연속"]
[430,"전북","군산","군공S/S 154kV #60-#65 BUS TIE GIS","군산P/O 154kV 이상 차단기 조작시험","군공S/S 6100CB 차단기 조작시험","2019-11-07 09:00","2019-11-07 10:00","2019-11-07 09:00","2019-11-07 10:00","당일"]
[431,"전북","군산","동군산장항#1 T/L","154kV 동군산-장항T/L 용량증대 전선교체공사","154kV 동군산-장항#1T/L 전선교체(ACSR240,330㎟ → ASCC 310㎟) 철도횡단구간 전선교체 시행 : No.18~22","2019-11-26 07:00","2019-11-26 18:00","2019-11-26 07:00","2019-11-26 18:00","당일"]
[432,"전북","군산","동군산장항#1 T/L","154kV 동군산-장항T/L 용량증대 전선교체공사","154kV 동군산-장항#1T/L 전선교체(ACSR240,330㎟ → ASCC 310㎟)","2019-11-04 07:00","2019-11-13 18:00","2019-11-04 07:00","2019-11-13 18:00","연속"]
[433,"전북","군산","동군산장항#2 T/L","154kV 동군산-장항T/L 용량증대 전선교체공사","154kV 동군산-장항#2T/L 전선교체(ACSR240,330㎟ → ASCC 310㎟)","2019-11-15 07:00","2019-11-25 18:00","2019-11-15 07:00","2019-11-25 18:00","연속"]
[434,"전북","군산","군산서군산#1 T/L","서군산S/S 현대화관련 부지확보공사","서군산S/S 현대화관련 부지확보공사","2019-11-22 09:00","2019-11-23 18:00","2019-11-22 09:00","2019-11-23 18:00","연속"]
[435,"전북","군산","군산서군산#1 T/L","서군산S/S 현대화관련 부지확보공사","서군산S/S 현대화관련 부지확보공사(POST보강, 무부하가압)","2019-11-11 09:00","2019-11-13 18:00","2019-11-11 09:00","2019-11-13 18:00","연속"]
[436,"전북","군산","군산영등#1 T/L","영등S/S 154kV 군산-영등#1T/L GIS 누유개소 해소공사","영등S/S 154kV 군산-영등#1T/L GIS 누유개소 해소공사","2019-11-25 09:00","2019-12-06 18:00","취소","취소","연속"]
[437,"전북","군산","이리전주#1 T/L","154kV 이리-전주T/L 일부지중화관련 철탑교체공사","- 철탑교체 4기 : 49, 50, 51, 52호 - 전선교체 : 47~50, 51~53호 - 가선로 구성 및 기타 부대공사","2019-11-17 09:00","2019-11-19 18:00","2019-11-17 09:00","2019-11-19 18:00","연속"]
[438,"전북","군산","이리전주#2 T/L","154kV 이리-전주T/L 일부지중화관련 철탑교체공사","- 철탑교체 4기 : 49, 50, 51, 52호 - 전선교체 : 47~50, 51~53호 - 가선로 구성 및 기타 부대공사","2019-11-07 09:00","2019-11-16 18:00","2019-11-07 09:00","2019-11-16 18:00","연속"]
[439,"전북","군산","팔봉S/S 154kV 팔봉-봉동#2T/L GIS","군산P/O 154kV 차단기 조작시험","팔봉S/S 팔봉-봉동#2T/L CB 조작시험","2019-11-12 15:00","2019-11-12 16:00","취소","취소","당일"]
[440,"전북","군산","팔봉두마#1 T/L","군산P/O 장기사용 기타설비 대체공사","팔봉-두마 #1 T/L CVT 교체 시행","2019-11-18 09:00","2019-11-18 18:00","2019-11-18 09:00","2019-11-18 18:00","당일"]
[441,"전북","군산","팔봉두마#2 T/L","군산P/O 장기사용 기타설비 대체공사","팔봉-두마 #2 T/L CVT 교체 시행","2019-11-19 09:00","2019-11-19 18:00","2019-11-19 09:00","2019-11-19 18:00","당일"]
[442,"전북","군산","영등팔봉#1 T/L","군산P/O 장기사용 기타설비 대체공사","영등-팔봉 #1 T/L CVT 교체 시행","2019-11-20 09:00","2019-11-20 18:00","취소","취소","당일"]
[443,"전북","군산","영등팔봉#2 T/L","군산P/O 장기사용 기타설비 대체공사","- 영등-팔봉 #2 T/L CVT 교체 시행 - 영등-팔봉 #2 T/L LA 교체시행(A, B, C상)","2019-11-21 09:00","2019-11-21 18:00","취소","취소","당일"]
[444,"전북","군산","팔봉S/S 팔봉-봉동#1T/L GIS","군산P/O 154kV 차단기 조작시험","팔봉S/S 팔봉-봉동#1T/L CB 조작시험","2019-11-12 14:00","2019-11-12 15:00","취소","취소","당일"]
[445,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2019-11-01 09:00","2019-11-01 18:00","2019-11-01 09:00","2019-11-01 18:00","당일"]
[446,"전북","김제","정주고창#2 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2019-11-02 08:00","2019-11-07 18:00","2019-11-02 08:00","2019-11-07 18:00","연속"]
[447,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2019-11-08 08:00","2019-11-13 18:00","2019-11-08 08:00","2019-11-13 18:00","연속"]
[448,"전북","김제","고창S/S 154kV 고창-영광#1T/L GIS","관내S/S 154kV GIS 조작시험","관내S/S 154kV GIS 조작시험","2019-11-28 15:00","2019-11-28 17:00","2019-11-28 15:00","2019-11-28 17:00","당일"]
[449,"전북","김제","백산김제#2 T/L","백산-김제#2T/L 항공장애표시구 시설공사","ㅇ 항공장애표시구 19개 시설","2019-11-08 07:00","2019-11-08 18:00","취소","취소","당일"]
[450,"전북","김제","담양김제 T/L","백산-김제#2T/L 항공장애표시구 시설공사","ㅇ 항공장애표시구 19개 시설","2019-11-08 07:00","2019-11-08 18:00","취소","취소","당일"]
[451,"전북","김제","신김제남전주#1 T/L","154kV 남전주-임실T/L OPGW 증설공사","OPGW 교체관련 병가철탑 안전확보","2019-11-05 09:00","2019-11-08 18:00","취소","취소","연속"]
[452,"전북","김제","칠보H/P 154kV #60 BUS","칠보S/Y 김제-칠보T/L 가스누기 보수공사","칠보S/Y 김제-칠보T/L 가스누기 보수공사","2019-11-18 09:00","2019-11-22 18:00","2019-11-04 09:00","2019-11-06 18:00","연속"]
[453,"전북","김제","칠보H/P 154kV #1 M.Tr 1차 GIS","칠보S/Y 김제-칠보T/L 가스누기 보수공사","칠보S/Y 김제-칠보T/L 가스누기 보수공사","2019-11-18 09:00","2019-11-22 18:00","2019-11-04 09:00","2019-11-06 18:00","연속"]
[454,"전북","김제","김제칠보HP T/L","칠보S/Y 김제-칠보T/L 가스누기 보수공사","칠보S/Y 김제-칠보T/L 가스누기 보수공사","2019-11-18 09:00","2019-11-22 18:00","2019-11-04 09:00","2019-11-06 18:00","연속"]
[455,"전북","김제","신김제남전주#1 T/L","신김제-남전주#1T/L 항공장애표시구 시설공사","ㅇ 항공장애표시구 적색 39개 철거, 86개 시설","2019-11-11 07:00","2019-11-14 18:00","취소","취소","매일"]
[456,"전북","김제","신김제전주#2 T/L","신김제-전주#2T/L 항공장애표시구 시설공사","ㅇ 항공장애표시구 백색 9개 시설","2019-11-11 07:00","2019-11-14 18:00","2019-11-11 07:00","2019-11-14 18:00","매일"]
[457,"전북","김제","신김제전주#1 T/L","신김제-남전주#2T/L 항공장애표시구 시설공사","ㅇ 항공장애표시구 백색 24개 철거, 59개 시설","2019-11-18 07:00","2019-11-20 18:00","2019-11-18 07:00","2019-11-20 18:00","매일"]
[458,"전북","김제","신김제정공#2 T/L","신김제-정공#2T/L 항공장애표시구 시설공사","ㅇ 항공장애표시구 백색 42개 철거, 147개 시설","2019-11-21 07:00","2019-11-29 18:00","취소","취소","매일"]
[459,"전북","김제","신김제남전주#2 T/L","신김제-남전주#2T/L 항공장애표시구 시설공사","ㅇ 항공장애표시구 백색 24개 철거, 59개 시설","2019-11-18 07:00","2019-11-20 18:00","취소","취소","매일"]
[460,"전북","김제","정공담양 T/L","154kV 담양-김제T/L No.101,102호 초기점검","154kV 담양-김제T/L No.101, 102호 초기점검","2019-11-18 08:00","2019-11-18 18:00","2019-11-19 08:00","2019-11-19 18:00","당일"]
[461,"전북","직할","무주용담수력 T/L","154kV 무주-용담수력T/L 보호배전반 대체공사","1. 무주, 용담수력측 송전선로 보호배전반 대체","2019-11-04 09:00","2019-11-15 18:00","취소","취소","연속"]
[462,"전북","직할","북전주용담수력 T/L","154kV 북전주-용담수력T/L 수용가측 보호배전반 점검공사","1. 한국수자원공사 용담지사 보호배전반 점검","2019-11-04 09:00","2019-11-04 18:00","취소","취소","당일"]
[463,"광주전남","강진","영암강진#1 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","송전선로 철거 및 가선, 선로접속, 모선POST 철거 OPGW 설치 및 시험","2019-11-20 09:00","2019-11-26 18:00","2019-11-20 09:00","2019-11-26 18:00","연속"]
[464,"광주전남","강진","신강진강진#1 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","신강진보호배전반 대체, 시험, LA, CVT 이설 송전선로 철거 및 가선, 선로접속, 모선철구 철거","2019-11-02 09:00","2019-11-13 18:00","2019-11-02 09:00","2019-11-13 18:00","연속"]
[465,"광주전남","강진","영암강진#2 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","영암S/S 보호배전반 대체, 시험, LA, CVT 이설 송전선로 철거 및 가선, 선로접속, 모선POST 철거 OPGW 설치 및 시험","2019-11-20 09:00","2019-11-26 18:00","2019-11-20 09:00","2019-11-26 18:00","연속"]
[466,"광주전남","강진","강진장흥#2 T/L","강진S/S 154kV 이하 취약설비 GIS화 사업","장흥S/S 보호반대체, CVT이설, OPGW 설치 및 시험","2019-11-27 09:00","2019-12-04 18:00","2019-11-27 09:00","2019-12-04 18:00","연속"]
[467,"광주전남","강진","남창S/S 154kV 강진-남창#2T/L CB A","강진S/S 154kV 이하 취약설비 GIS화 사업","송전선로 가선, 선로접속, LA, CVT이설 강진-남창#2T/L, 신강진-강진#2T/L 직결해제","2019-11-14 09:00","2019-11-19 18:00","2019-11-14 09:00","2019-11-19 18:00","연속"]
[468,"광주전남","강진","남창해남CS#2 T/L","남창-해남C/S T/L OPGW 교체공사","남창-해남C/S 구간 OPGW 코어 불량지점 교체","2019-11-12 08:00","2019-11-13 18:00","취소","취소","연속"]
[469,"광주전남","강진","남창해남CS#1 T/L","19년 변전설비 개폐장치 및 차단기 조작시험","현장조작→원방조작→계전기연동시험→개폐타임측정","2019-11-13 09:00","2019-11-13 18:00","취소","취소","당일"]
[470,"광주전남","강진","신강진대불#1 T/L","2019년 가공송전 순시점검 위탁공사","국산애자 특별진단 - 애자 절연 저항 측정 신강진-대불 65호","2019-11-05 09:00","2019-11-05 14:00","2019-11-05 09:00","2019-11-05 14:00","당일"]
[471,"광주전남","강진","신강진S/S 154kV 신강진-강진#2T/L CB","강진S/S 154kV이하 취약설비 GIS화 사업","송전선로 가선, 선로접속, LA,CVT 이설 강진-남창#2T/L, 신강진-강진#2T/L 직결해제","2019-11-14 09:00","2019-11-19 18:00","2019-11-14 09:00","2019-11-19 18:00","연속"]
[472,"광주전남","강진","진도C/S P2+FF1 GIS","관내S/S 170kV GIS 정밀점검 공사","ㅇ GIS 정밀점검","2019-11-07 09:00","2019-11-09 18:00","취소","취소","연속"]
[473,"광주전남","강진","해남해남CS#2 T/L","남창-해남C/S T/L OPGW 교체공사","남창-해남C/S OPGW 코어 불량개소 교체","2019-11-12 08:00","2019-11-13 18:00","취소","취소","연속"]
[474,"광주전남","광주","계림충장#3 T/L","19년 광주 변전 총액공사 (계림-충장3T/L)","계림-충장#3T/L 양단 보호반 교체, 계림S/S GIS 보통점검, 충장S/S 장기미동작CB점검","2019-11-06 09:00","2019-11-08 18:00","2019-11-06 09:00","2019-11-08 18:00","연속"]
[475,"광주전남","광주","신광주계림#2 T/L","계림S/S 154kV 신광주-계림#2T/L 휴전","계림S/S 154kV 신광주-계림#2T/L 정밀점검공사 미비사항 조치","2019-11-01 09:00","2019-11-01 18:00","2019-11-01 09:00","2019-11-01 18:00","당일"]
[476,"광주전남","광주","신광주일곡#2 T/L","신광주,일곡S/S 신광주-일곡#2T/L 송전선로 보호반 교체","신광주,일곡S/S 신광주-일곡#2T/L 송전선로 보호반 교체 신광주S/S 신광주-일곡#2T/L GIS 하자점검","2019-11-15 09:00","2019-11-18 18:00","취소","취소","연속"]
[477,"광주전남","광주","신광주일곡#1 T/L","신광주,일곡S/S 신광주-일곡#1T/L 송전선로 보호반 교체","신광주,일곡S/S 신광주-일곡#1T/L 송전선로 보호반 교체 신광주S/S 신광주-일곡#1T/L GIS 하자점검 신광주S/S 신광주-일곡#1T/L LA C상 절연 볼트 불량 관련 점검","2019-11-11 09:00","2019-11-13 18:00","취소","취소","연속"]
[478,"광주전남","광주","신광주일곡#2 T/L","신광주S/S 신광주-일곡#2T/L 송전선로 보호반 이동","신광주,일곡S/S 신광주-일곡#2T/L 송전선로 보호반 교체 전 사전 작업(신광주 측 보호반 이동)","2019-11-01 09:00","2019-11-01 18:00","취소","취소","당일"]
[479,"광주전남","광주","담양일곡#2 T/L","154kV 담양-일곡T/L 190-192호 지장송전선로 지중화 공사","가. 공 사 명 : 담양첨단문화복합단지 지장송전선로 지중화 공사 나. 공사시행 : 요청자 직접시행(담양대숲마루 주식회사) 다. 대상설비 : 154kV 담양-일곡 #1,2T/L 189 ∼ 192호 라. 공사내용 ○ 가공분야 : C/H 철탑2기 신설(188∼193호간 임시선로 구성) ○ 지중분야 : 관로 785m(XLPE 1,200㎟*S*2C)","2019-11-20 08:00","2019-11-22 18:00","취소","취소","연속"]
[480,"광주전남","광주","담양일곡#1 T/L","154kV 담양-일곡T/L 190-192호 지장송전선로 지중화 공사","가. 공 사 명 : 담양첨단문화복합단지 지장송전선로 지중화 공사 나. 공사시행 : 요청자 직접시행(담양대숲마루 주식회사) 다. 대상설비 : 154kV 담양-일곡 #1,2T/L 189 ∼ 192호 라. 공사내용 ○ 가공분야 : C/H 철탑2기 신설(188∼193호간 임시선로 구성) ○ 지중분야 : 관로 785m(XLPE 1,200㎟*S*2C)","2019-11-23 08:00","2019-11-25 18:00","취소","취소","연속"]
[481,"광주전남","목포","나주엄다#1 T/L","154kV 나주-엄다T/L 26호 안전이격확보공사","154kV 나주-엄다T/L 26호 안전이격확보공사 -#1T/L 암 공중이동 및 철탑조립","2019-11-13 08:00","2019-11-13 18:00","2019-11-13 08:00","2019-11-13 18:00","당일"]
[482,"광주전남","목포","나주엄다#1 T/L","154kV 나주-엄다T/L 26호 안전이격확보공사","154kV 나주-엄다T/L 26호 안전이격확보공사 -#1T/L 보조암설치","2019-11-11 08:00","2019-11-11 13:00","2019-11-11 08:00","2019-11-11 13:00","당일"]
[483,"광주전남","목포","나주엄다#2 T/L","154kV 나주-엄다T/L 26호 안전이격확보공사","154kV 나주-엄다T/L 26호 안전이격확보공사 -#2T/L 암조립 및 철탑조립","2019-11-11 13:00","2019-11-12 18:00","2019-11-11 13:00","2019-11-12 18:00","연속"]
[484,"광주전남","순천","승주S/S 154kV #60-#65 BUS TIE GIS","19년 순천변전협력회사총액공사(모선보호반 교체)","승주S/S 154kV 모선보호반 교체","2019-11-18 09:00","2019-11-21 18:00","2019-11-19 09:00","2019-11-22 18:00","연속"]
[485,"광주전남","순천","여수TP여천#2 T/L","19년 순천 변전협력회사 총액공사(현수애자절연진단 및 교체)","여천 여수TP-여천#2T/L 현수애자 절연성능 진단 및 교체","2019-11-08 10:00","2019-11-08 18:00","2019-11-08 10:00","2019-11-08 18:00","당일"]
[486,"광주전남","직할","나주금천#1 T/L","2019년도 직할 가공송전선로 순시점검 위탁공사","○ 154kV 신화순-나주#1T/L 정밀점검 4회선 병가구간 안전이격거리 확보 - 40~63호, 24기","2019-11-07 13:00","2019-11-11 13:00","2019-11-07 13:00","2019-11-11 13:00","연속"]
[487,"광주전남","직할","남광주금천#1 T/L","2019년도 직할 가공송전선로 순시점검 위탁공사","○ 154kV 신화순-나주#1T/L 정밀점검 4회선 병가구간 안전이격거리 확보 - 38~39호, 2기","2019-11-07 08:00","2019-11-07 13:00","2019-11-07 08:00","2019-11-07 13:00","당일"]
[488,"광주전남","직할","남광주금천#2 T/L","2019년도 직할 가공송전선로 순시점검 위탁공사","○ 154kV 신화순-나주#2T/L 정밀점검 4회선 병가구간 안전이격거리 확보 - 38~39호, 2기","2019-11-18 13:00","2019-11-18 18:00","2019-11-18 13:00","2019-11-18 18:00","당일"]
[489,"광주전남","직할","나주금천#2 T/L","2019년도 직할 가공송전선로 순시점검 위탁공사","○ 154kV 신화순-나주#2T/L 정밀점검 4회선 병가구간 안전이격거리 확보 - 40~63호, 24기","2019-11-13 13:00","2019-11-18 13:00","2019-11-13 13:00","2019-11-18 13:00","연속"]
[490,"광주전남","직할","신화순나주#2 T/L","2019년도 직할 가공송전선로 순시점검 위탁공사","○ 154kV 신화순-나주#2T/L 정밀점검 - 신화순S/S ~ 나주S/S, 72기","2019-11-13 08:00","2019-11-21 18:00","2019-11-13 08:00","2019-11-21 18:00","연속"]
[491,"광주전남","직할","신화순나주#1 T/L","2019년도 직할 가공송전선로 순시점검 위탁공사","○ 154kV 신화순-나주#1T/L 정밀점검 - 신화순S/S ~ 나주S/S, 72기","2019-11-04 08:00","2019-11-12 18:00","2019-11-04 08:00","2019-11-12 18:00","연속"]
[492,"광주전남","강진","진도C/S P1+FF1 GIS","관내S/S 170kV GIS 정밀점검 공사","ㅇ GIS 정밀점검","2019-11-04 09:00","2019-11-06 18:00","취소","취소","연속"]
[493,"대구","경산","청도밀양#2 T/L","송전정비 협력회사 총액공사","항공장애구 설치 안전확보","2019-11-15 08:00","2019-11-15 18:00","취소","취소","당일"]
[494,"대구","경산","청도밀양#1 T/L","송전정비 협력회사 총액공사","항공장애구 설치 안전확보","2019-11-18 08:00","2019-11-18 18:00","취소","취소","당일"]
[495,"대구","달성","고령S/S 154kV #61 BUS","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-27 18:00","2019-11-28 18:00","취소","취소","연속"]
[496,"대구","달성","고령S/S 154kV #60 BUS","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-27 18:00","2019-11-28 18:00","취소","취소","연속"]
[497,"대구","달성","고령쌍림#1 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-24 08:00","2019-11-28 18:00","취소","취소","연속"]
[498,"대구","달성","고령다산#1 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-24 08:00","2019-11-28 18:00","취소","취소","연속"]
[499,"대구","달성","고령S/S 154kV #65 BUS","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-22 18:00","2019-11-23 18:00","취소","취소","연속"]
[500,"대구","달성","고령S/S 154kV #66 BUS","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-22 18:00","2019-11-23 18:00","취소","취소","연속"]
[501,"대구","달성","고령쌍림#2 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-19 08:00","2019-11-24 18:00","취소","취소","연속"]
[502,"대구","달성","고령다산#2 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-19 08:00","2019-11-23 18:00","취소","취소","연속"]
[503,"대구","달성","고령다산#1 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-18 14:00","2019-11-18 16:00","취소","취소","당일"]
[504,"대구","달성","고령쌍림#2 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-18 11:00","2019-11-18 14:00","취소","취소","당일"]
[505,"대구","달성","고령쌍림#1 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-11-18 09:00","2019-11-18 11:00","취소","취소","당일"]
[506,"대구","달성","고령다산#1 T/L","18-19년 달성전력 송전정비 협력회사 총액공사","철탑 애자 오손시스템 설치공사","2019-11-01 07:00","2019-11-01 18:00","2019-11-01 07:00","2019-11-01 18:00","당일"]
[507,"대구","달성","논공S/S 154kV #1 EM.Tr CB","2019년 2차 변전소 종합예방진단시스템 설치작업","변압기 부싱 진단장치 설치 등","2019-11-18 09:00","2019-11-21 18:00","2019-11-18 09:00","2019-11-21 18:00","연속"]
[508,"대구","달성","논공S/S 154kV #1 EM.Tr CB","논공S/S #2,3M.Tr 부싱절연유 채유작업","논공S/S #2,3M.Tr 부싱절연유 채유작업(#2,3 M.Tr과 LOOP 시행)","2019-11-11 09:00","2019-11-11 18:00","2019-11-11 09:00","2019-11-11 18:00","당일"]
[509,"대구","달성","다산강창#1 T/L","2019년 가공송전 순시점검 위탁공사","정밀점검(No.1~55)","2019-11-01 12:00","2019-11-07 18:00","2019-11-01 12:00","2019-11-07 18:00","연속"]
[510,"대구","달성","대구청도#1 T/L","대구-청도T/L 장기사용 지지물 교체공사","철탑 설치 및 보강 : 17~20호 설치, 22호 보강 철탑철거:17~21호 전선교체:15~22호","2019-11-18 08:00","2019-11-27 18:00","취소","취소","연속"]
[511,"대구","달성","대구청도#2 T/L","대구-청도T/L 장기사용 지지물 교체공사","철탑 설치 및 보강 : 17~20호 설치, 22호 보강 철탑철거:17~21호 전선교체:15~22호","2019-11-11 08:00","2019-11-16 18:00","취소","취소","연속"]
[512,"대구","달성","대구청도#2 T/L","대구-청도T/L 장기사용 지지물 교체공사","철탑 설치 및 보강 : 17~20호 설치, 22호 보강 철탑철거:17~21호 전선교체:15~22호","2019-11-28 08:00","2019-12-06 18:00","취소","취소","연속"]
[513,"대구","달성","대구봉덕#2 T/L","'18-'19년 달성 송전정비 협력회사 총액공사","항공구 설치 안전확보 No.6-7,7-8,13-14,19-20,20-21","2019-11-06 07:30","2019-11-07 18:00","2019-11-06 07:30","2019-11-07 18:00","연속"]
[514,"대구","직할","동인공평#2 T/L","공평S/S 모선보호반 교체 시험","공평S/S 모선보호반 교체 시험","2019-11-07 10:30","2019-11-07 11:00","2019-11-07 10:30","2019-11-07 11:00","당일"]
[515,"대구","직할","동인공평#1 T/L","공평S/S 모선보호반 교체 시험","공평S/S 모선보호반 교체 시험","2019-11-07 10:00","2019-11-07 10:30","2019-11-07 10:00","2019-11-07 10:30","당일"]
[516,"대구","직할","노변효목#1 T/L","지중송전 EBA절연유 채유 및 접지선 교체공사","○ 지중송전 규격미달 접지선 교체공사 ○ EBA 열화진단용 절연유 채유","2019-11-07 10:00","2019-11-07 18:00","2019-11-07 10:00","2019-11-07 18:00","당일"]
[517,"대구","포항","울주외동#2 T/L","외동S/S 울주외동#2 T/L 공기조작부 정밀점검","외동S/S 울주외동#2 T/L 공기조작부 정밀점검","2019-11-07 09:00","2019-11-07 18:00","2019-11-07 09:00","2019-11-07 18:00","당일"]
[518,"대구","포항","울주외동#1 T/L","외동S/S 울주외동#1 T/L 공기조작부 정밀점검","외동S/S 울주외동#1 T/L 공기조작부 정밀점검","2019-11-06 09:00","2019-11-06 18:00","2019-11-06 09:00","2019-11-06 18:00","당일"]
[519,"경북","구미","점촌동상주개폐소#2 T/L","문경 모전지구 지중화 사업","-154kV 동상주-점촌#2T/L No.8~12 지중화 - C/H위치 : No.8, 12호","2019-11-25 08:00","2019-12-01 18:00","취소","취소","연속"]
[520,"경북","구미","점촌동상주개폐소#1 T/L","문경 모전지구 지중화 사업","-154kV 동상주-점촌#1T/L No.8~12 지중화 - C/H위치 : No.8, 12호","2019-11-18 08:00","2019-11-24 18:00","취소","취소","연속"]
[521,"경북","구미","청리상주#1 T/L","345kV 선산분기 등 12개T/L 송전선로용 피뢰기 설치공사","154kV 상주-보은T/L 송전선로용 피뢰기 설치공사 안전확보를 위한 휴전","2019-11-01 07:00","2019-11-01 18:00","2019-11-01 07:00","2019-11-01 18:00","당일"]
[522,"경북","구미","선산청리#1 T/L","19년 구미전력지사 변전정비업체 총액공사","- LA 보통점검 - GIS 조작시험","2019-11-05 09:00","2019-11-05 15:00","2019-11-05 09:00","2019-11-05 15:00","당일"]
[523,"경북","구미","선산청리#2 T/L","19년 구미전력지사 변전정비업체 총액공사","- GIS 조작시험","2019-11-05 15:00","2019-11-05 18:00","2019-11-05 15:00","2019-11-05 18:00","당일"]
[524,"경북","구미","청리상주#1 T/L","154kV 청리-상주T/L 안전이격확보공사(No.50~59)","공사개요 : 1937년 설치된 노후철탑을 교체하여 전력공급에 만전을 기하고자함 o 구간 : 154kV 청리-상주T/L No.50 ~ 59 o 선종 : ACSR 330 * 2C *. 2.9km o 철탑기수 : 10기철거, 9기 설치","2019-11-18 09:00","2019-12-10 18:00","2019-11-18 09:00","2019-12-10 18:00","연속"]
[525,"경북","구미","청리상주#1 T/L","154kV 청리-상주T/L 안전이격확보공사(No.50~59)","공사개요 : 1937년 설치된 노후철탑을 교체하여 전력공급에 만전을 기하고자함 o 구간 : 154kV 청리-상주T/L No.50 ~ 59 o 선종 : ACSR 330 * 2C *. 2.9km o 철탑기수 : 10기철거, 9기 설치","2019-11-06 09:00","2019-11-06 18:00","2019-11-06 09:00","2019-11-06 18:00","당일"]
[526,"경북","구미","청리상주#2 T/L","154kV 청리-상주T/L 안전이격확보공사(No.50~59)","공사개요 : 1937년 설치된 노후철탑을 교체하여 전력공급에 만전을 기하고자함 o 구간 : 154kV 청리-상주T/L No.50 ~ 59 o 선종 : ACSR 330 * 2C *. 2.9km o 철탑기수 : 10기철거, 9기 설치","2019-11-07 09:00","2019-12-10 18:00","2019-11-07 09:00","2019-12-10 18:00","연속"]
[527,"경북","직할","풍산안동CC#2 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","초기점검","2019-11-14 09:00","2019-11-15 18:00","2019-11-14 09:00","2019-11-15 18:00","당일"]
[528,"경북","직할","풍산안동CC#1 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","초기점검","2019-11-07 09:00","2019-11-08 18:00","2019-11-07 09:00","2019-11-08 18:00","매일"]
[529,"경북","직할","신영주안동#2 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","조작시험","2019-11-13 14:00","2019-11-13 18:00","2019-11-13 14:00","2019-11-13 18:00","당일"]
[530,"경북","직할","신영주안동#1 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","조작시험","2019-11-13 09:00","2019-11-13 14:00","2019-11-13 09:00","2019-11-13 14:00","당일"]
[531,"경북","직할","안동동안동#1 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","LA A,B,C상 교체","2019-11-12 09:00","2019-11-12 18:00","2019-11-12 09:00","2019-11-12 18:00","당일"]
[532,"경북","직할","현종산풍력평해#1 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","초기점검","2019-11-26 09:00","2019-11-26 18:00","취소","취소","당일"]
[533,"부산울산","동부산","구서명장#2 T/L","18-19년 동부산전력지사 송전정비 협력회사 총액공사","154kV 신양산-구서#2T/L 작업 안전이격확보","2019-11-28 08:00","2019-11-29 18:00","2019-11-28 08:00","2019-11-29 18:00","연속"]
[534,"부산울산","동부산","구서명장#1 T/L","18-19년 동부산전력지사 송전정비 협력회사 총액공사","154kV 신양산-구서#1T/L 작업 안전이격확보","2019-11-21 08:00","2019-11-22 18:00","2019-11-21 08:00","2019-11-22 18:00","연속"]
[535,"부산울산","동부산","정관고리NP T/L","정관E/C 170kV GIS 차단기 동작시험","정관E/C 170kV GIS 차단기 동작시험(정관-고리T/L)","2019-11-04 09:30","2019-11-04 14:00","2019-11-04 09:30","2019-11-04 14:00","당일"]
[536,"부산울산","동부산","시랑좌동#2 T/L","좌동E/C 154kV 시랑-좌동#1T/L 피뢰기 교체관련 안전이격","좌동E/C 154kV 시랑-좌동#1T/L 피뢰기 교체관련 안전이격","2019-11-06 09:30","2019-11-06 18:00","2019-11-06 09:30","2019-11-06 18:00","당일"]
[537,"부산울산","동부산","시랑좌동#1 T/L","좌동E/C 154kV 시랑-좌동#1T/L 피뢰기 교체","좌동E/C 154kV 시랑-좌동#1T/L 피뢰기 교체","2019-11-06 09:30","2019-11-06 18:00","2019-11-06 09:30","2019-11-06 18:00","당일"]
[538,"부산울산","북부산","양산물금 T/L","물금E/C 154kV 모선분리공사","물금E/C 154kV 모선분리공사","2019-11-12 09:00","2019-11-12 14:00","2019-11-12 09:00","2019-11-12 14:00","당일"]
[539,"부산울산","북부산","북부산물금 T/L","물금E/C 154kV 모선분리공사","물금E/C 154kV 모선분리공사","2019-11-12 14:00","2019-11-12 18:00","2019-11-12 14:00","2019-11-12 18:00","당일"]
[540,"부산울산","북부산","북부산물금 T/L","물금E/C 154kV GIS 모선분리공사","물금E/C 154kV GIS 모선분리공사(시험가압)","2019-11-09 15:00","2019-11-10 17:00","2019-11-09 15:00","2019-11-10 17:00","연속"]
[541,"부산울산","북부산","북부산물금 T/L","154kV 북부산E/C 구내 인출Bay 변경 전력구공사","전력구공사 - 154kV 북부산-물금T/L 안전이격휴전","2019-11-29 07:00","2019-11-30 18:00","2019-11-29 07:00","2019-11-30 18:00","연속"]
[542,"부산울산","북부산","양산산막#2 T/L","18-19년 동부산전력지사 송전정비 협력회사 총액공사","154kV 반천-언양#1T/L 작업 안전이격확보","2019-11-04 08:00","2019-11-04 18:00","2019-11-04 08:00","2019-11-04 18:00","당일"]
[543,"부산울산","북부산","양산산막#1 T/L","2019년 북부산 변전협력회사 총액공사","산막E/C 154kV 양산-산막#1T/L GIS 조작시험","2019-11-08 10:00","2019-11-08 18:00","2019-11-08 10:00","2019-11-08 18:00","당일"]
[544,"부산울산","북부산","양산산막#1 T/L","18-19년 동부산전력지사 송전정비 협력회사 총액공사","154kV 반천-언양#2T/L 작업 안전이격확보","2019-11-06 08:00","2019-11-06 18:00","2019-11-06 08:00","2019-11-06 18:00","당일"]
[545,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막T/L 안전이격확보공사","-154kV 서창-산막T/L No. 17∼21 안전이격확보공사 1. 구 간 : 154㎸ 서창-산막T/L 17∼21 안전이격확보공사 2. 지 지 물 : 철탑 3기(No. 18, 19, 20) 교체 ○ 공법 : Helper Tower[No. 18] / Enclosing[No. 19, 20] 3. 전 력 선 : ACSR 330㎟ × S ×","2019-11-23 07:00","2019-11-24 18:00","2019-11-23 07:00","2019-11-24 18:00","연속"]
[546,"부산울산","북부산","언양산막#2 T/L","2019년 북부산 변전협력회사 총액공사","산막E/C 154언양-산막#2T/L GIS 차단기 조작시험","2019-11-07 10:00","2019-11-07 18:00","취소","취소","당일"]
[547,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막T/L 안전이격확보공사","-154kV 서창-산막T/L No. 17∼21 안전이격확보공사 1. 구 간 : 154㎸ 서창-산막T/L 17∼21 안전이격확보공사 2. 지 지 물 : 철탑 3기(No. 18, 19, 20) 교체 ○ 공법 : Helper Tower[No. 18] / Enclosing[No. 19, 20] 3. 전 력 선 : ACSR 330㎟ × S ×","2019-11-09 07:00","2019-11-10 18:00","2019-11-09 07:00","2019-11-10 18:00","연속"]
[548,"부산울산","북부산","서창산막#2 T/L","154kV 서창-산막T/L 안전이격확보공사","-154kV 서창-산막T/L No. 17∼21 안전이격확보공사 1. 구 간 : 154㎸ 서창-산막T/L 17∼21 안전이격확보공사 2. 지 지 물 : 철탑 3기(No. 18, 19, 20) 교체 ○ 공법 : Helper Tower[No. 18] / Enclosing[No. 19, 20] 3. 전 력 선 : ACSR 330㎟ × S ×","2019-11-30 07:00","2019-12-01 18:00","2019-11-30 07:00","2019-12-01 18:00","연속"]
[549,"부산울산","북부산","서창산막#2 T/L","154kV 서창-산막T/L 안전이격확보공사","-154kV 서창-산막T/L No. 17∼21 안전이격확보공사 1. 구 간 : 154㎸ 서창-산막T/L 17∼21 안전이격확보공사 2. 지 지 물 : 철탑 3기(No. 18, 19, 20) 교체 ○ 공법 : Helper Tower[No. 18] / Enclosing[No. 19, 20] 3. 전 력 선 : ACSR 330㎟ × S ×","2019-11-16 07:00","2019-11-17 18:00","2019-11-16 07:00","2019-11-17 18:00","연속"]
[550,"부산울산","북부산","양산물금 T/L","154kV 삼랑진양수 스위치야드 현대화 사업","○ 양산-물금T/L 점퍼선 분리 작업 및 포우스트 인출송전선로 연결 ○ 삼랑진양수 현대화공사 관련 GIS 설비 앵글측정 및 시험가압 ○ 스위치야드 GIS 설비 계통병입 (본가압)","2019-11-18 09:00","2019-11-28 18:00","2019-11-18 09:00","2019-11-28 18:00","연속"]
[551,"부산울산","서부산","서부산다대#2 T/L","154kV 서부산-다대T/L 지장이설 및 선종교체공사","선로명 : 154kV 서부산-다대T/L 구 간 : J/B#2 ~ J/B#5 (1.09km) 작업내용 : 을숙도대교-장림고개간 지하차도건설공사에 따른 지장이설 및 케이블 선종교체","2019-11-04 09:00","2020-01-17 18:00","2019-11-04 09:00","2020-01-17 18:00","연속"]
[552,"부산울산","울산","두왕영남TP#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-11-20 07:00","2019-11-21 18:00","2019-11-20 07:00","2019-11-21 18:00","연속"]
[553,"부산울산","울산","두왕영남TP#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-11-07 07:00","2019-11-08 18:00","2019-11-07 07:00","2019-11-08 18:00","연속"]
[554,"부산울산","울산","두왕영남TP#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-11-11 07:00","2019-11-15 18:00","2019-11-11 07:00","2019-11-15 18:00","연속"]
[555,"부산울산","울산","두왕영남TP#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-11-18 07:00","2019-11-19 18:00","2019-11-18 07:00","2019-11-19 18:00","연속"]
[556,"부산울산","울산","방어진영남TP#2 T/L","울산전력지사 관내 OPGW 항공장애표시구 설치공사","No.3호~No.4호 구간 항공장애표시구 12개 설치","2019-11-03 09:00","2019-11-03 18:00","2019-11-03 09:00","2019-11-03 18:00","당일"]
[557,"부산울산","울산","방어진영남TP#1 T/L","울산전력지사 관내 OPGW 항공장애표시구 설치공사","No.3호~No.4호 구간 항공장애표시구 13개 설치","2019-11-02 09:00","2019-11-02 18:00","2019-11-02 09:00","2019-11-02 18:00","당일"]
[558,"부산울산","울산","신울산두왕#2 T/L","2019년도 가공송전 순시점검 위탁공사","1) 정밀점검 ○ 154kV 신울산-두왕#2T/L No.2~6(5기) ○ 병가선로 휴전 - 공사명 : 154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사 - 휴전설비 : 154kV 신울산-울산#2T/L (11/16~18)","2019-11-16 08:00","2019-11-16 18:00","2019-11-16 08:00","2019-11-16 18:00","당일"]
[559,"부산울산","울산","신울산울산#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-11-09 07:00","2019-11-09 18:00","취소","취소","당일"]
[560,"부산울산","울산","신울산울산#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-11-16 07:00","2019-11-16 18:00","취소","취소","당일"]
[561,"부산울산","울산","신울산울산#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-11-10 07:00","2019-11-10 18:00","취소","취소","당일"]
[562,"부산울산","울산","신울산울산#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-11-17 07:00","2019-11-17 18:00","취소","취소","당일"]
[563,"부산울산","울산","옥동외동#2 T/L","154kV 외동-옥동#2T/L 취약철탑 Arm교체공사","ㅁ 외동-옥동T/L 취약철탑 Arm 교체 : No.10, 22 ㅁ 송전선로용 피뢰기 설치 : No.8~10(3기)","2019-11-10 08:00","2019-11-10 18:00","2019-11-10 08:00","2019-11-10 18:00","당일"]
[564,"부산울산","울산","옥동외동#1 T/L","154kV 외동-옥동#1T/L 취약철탑 Arm교체공사","ㅁ 외동-옥동T/L 취약철탑 Arm 교체 : No.10, 22 ㅁ 송전선로용 피뢰기 설치 : No.8~10(3기) ㅁ 항공장애표시구 설치 : No.11~12 [감사원 설비관리 실태점검 감사 지적사항 조치] ㅁ 동시휴전(거래소승인)","2019-11-09 08:00","2019-11-09 18:00","2019-11-09 08:00","2019-11-09 18:00","당일"]
[565,"부산울산","울산","옥동외동#1 T/L","154kV 외동-옥동#2T/L 취약철탑 Arm 교체공사(안전확보)","ㅁ 외동-옥동#2T/L 취약철탑 Arm 교체(편심발생) : No.10, 22 ㅁ 안전확보","2019-11-10 08:00","2019-11-10 18:00","2019-11-10 08:00","2019-11-10 18:00","당일"]
[566,"부산울산","울산","옥동외동#2 T/L","154kV 외동-옥동#1T/L 취약철탑 Arm 교체공사(안전확보)","ㅁ 외동-옥동#1T/L 취약철탑 Arm 교체(편심발생) : No.10, 22 ㅁ 항공장애표시구 설치: No.11~12 ,가공지선 1조 철탑 ㅁ 안전확보","2019-11-09 08:00","2019-11-09 18:00","2019-11-09 08:00","2019-11-09 18:00","당일"]
[567,"부산울산","울산","용연처용#2 T/L","울산전력지사 관내 OPGW 항공장애표시구 설치공사","154㎸ 용연-처용#2T/L No.12호~No.16호, No.18호~No.19호 구간 항공장애표시구 설치","2019-11-11 08:00","2019-11-12 18:00","2019-11-11 08:00","2019-11-12 18:00","연속"]
[568,"부산울산","울산","용연울산TP#3 T/L","2019년 울산화력 170kV 장기사용GIS 대체공사","- 용연E/C 154kV 롯데케미칼T/L #2BUS, #2DS, CB, 상부모선 시험가압선로 24H 및 #1DS 투입후 시험가압 1H 선로","2019-11-06 17:00","2019-11-07 18:00","2019-11-06 17:00","2019-11-07 18:00","연속"]
[569,"부산울산","울산","울산울산TP#1 T/L","2019년 울산화력 170kV 장기사용GIS 대체공사","- 울산화력S/Y 154KV SK에너지No2FCC#1T/L #1BUS 시험가압 24H","2019-11-20 18:00","2019-11-21 18:00","2019-11-20 18:00","2019-11-21 18:00","연속"]
[570,"부산울산","울산","용연울산TP#2 T/L","345kV 신울산복합-북부산T/L 건설사업","○ 공사목적 : 345kV 신울산복합-북부산T/L 울산화력ST~No.12 가선공사 - 용연-울산TP T/L 및 SK에너지 선로 횡단구간 발받침철탑 철거 및 보호망 설치 철거","2019-11-26 07:00","2019-11-26 18:00","2019-11-26 07:00","2019-11-26 18:00","당일"]
[571,"부산울산","울산","울산T/P 154kV #65 BUS","2019년 울산화력 170kV 장기사용GIS 대체공사","- 울산화력S/Y SK에너지No2FCC#1T/L 상부모선, 부싱, #2DS 철거 및 신규GIB 설치(내용년수 경과 및 인출점 변경)","2019-11-11 09:00","2019-11-15 18:00","2019-11-11 09:00","2019-11-15 18:00","연속"]
[572,"부산울산","울산","울산T/P 154kV #65-#66 SEC CB","2019년 울산화력 170kV 장기사용GIS 대체공사","- 울산화력S/Y 154kV SK에너지No2FCC#1T/L #2BUS 철거 설치 관련 SEC GIS조정(공간확보)","2019-11-11 09:00","2019-11-15 18:00","2019-11-11 09:00","2019-11-15 18:00","연속"]
[573,"부산울산","울산","울산울산TP#1 T/L","2019년 울산화력 170kV 장기사용GIS 대체공사","- 울산화력S/Y 154KV SK에너지No2FCC#1T/L #2BUS 시험가압 24H","2019-11-14 17:00","2019-11-15 17:00","2019-11-14 17:00","2019-11-15 17:00","연속"]
[574,"부산울산","울산","울산T/P 154kV #60 BUS","2019년 울산화력 170kV 장기사용GIS 대체공사","- 울산화력S/Y 154kV SK에너지NO2FCC#1T/L #1DS, CB철거 및 신규GIB설치","2019-11-18 09:00","2019-11-21 18:00","2019-11-18 09:00","2019-11-21 18:00","연속"]
[575,"부산울산","울산","용연울산TP#3 T/L","345kV 신울산복합-북부산T/L 건설공사","○ 공사목적 : 345kV 신울산복합-북부산T/L 울산화력ST~No.12 가선공사 - 본선로 ST~No.12호 연선 및 No.3,4,5 긴선 작업","2019-11-08 07:00","2019-11-13 18:00","2019-11-08 07:00","2019-11-13 18:00","연속"]
[576,"부산울산","울산","용연울산TP#3 T/L","345kV 신울산복합-북부산T/L 건설공사","○ 공사목적 : 345kV 신울산복합-북부산T/L 울산화력ST~No.12 가선공사 - 본선로 ST~No.12호 연선 및 No.3,4,5 긴선 작업","2019-11-16 07:00","2019-11-19 18:00","2019-11-16 07:00","2019-11-19 18:00","연속"]
[577,"부산울산","울산","용연울산TP#3 T/L","345kV 신울산복합-북부산T/L 건설공사","○ 공사목적 : 345kV 신울산복합-북부산T/L 울산화력ST~No.12 가선공사 - 본선로 ST~No.12호 연선 및 No.3,4,5 긴선 작업","2019-11-22 07:00","2019-11-25 18:00","2019-11-22 07:00","2019-11-25 18:00","연속"]
[578,"부산울산","울산","용연울산TP#3 T/L","345kV 신울산복합-북부산T/L 건설공사","○ 공사목적 : 345kV 신울산복합-북부산T/L 울산화력ST~No.12 가선공사 - 본선로 ST~No.12호 연선 및 No.3,4,5 긴선 작업","2019-11-02 07:00","2019-11-05 18:00","2019-11-02 07:00","2019-11-05 18:00","연속"]
[579,"부산울산","울산","용연울산TP#1 T/L","345kV 신울산복합-북부산T/L 건설사업","○ 공사목적 : 345kV 신울산복합-북부산T/L 울산화력ST~No.12 가선공사 - 용연-울산TP T/L 및 SK에너지 선로 횡단구간 발받침철탑 철거 및 보호망 설치 철거","2019-11-26 07:00","2019-11-26 18:00","2019-11-26 07:00","2019-11-26 18:00","당일"]
[580,"부산울산","울산","울주외동#2 T/L","154kV 외동-옥동#1T/L 회전스페이서 설치공사(안전확보)","ㅁ외동-옥동#1(울주-외동#2)T/L 병가개소 안전확보 : No.46~47(27~28), 57~58(38~39)","2019-11-08 08:00","2019-11-08 18:00","2019-11-08 08:00","2019-11-08 18:00","당일"]
[581,"부산울산","울산","울주외동#1 T/L","154kV 외동-옥동#2T/L 회전스페이서 설치공사(안전확보)","ㅁ외동-옥동#2(울주-외동#1)T/L 병가개소 안전확보 : No.46~47(27~28), 57~58(38~39)","2019-11-13 08:00","2019-11-13 18:00","2019-11-13 08:00","2019-11-13 18:00","당일"]
[582,"부산울산","울산","신울산웅촌#2 T/L","18~19년 변전협력 총액공사","- 웅촌E/C 154kV #2Sh.C MAIN GIS 정밀점검 시험가압선로 1H","2019-11-07 17:00","2019-11-07 18:00","2019-11-07 17:00","2019-11-07 18:00","당일"]
[583,"부산울산","울산","신울산웅촌#1 T/L","18~19년 변전협력 총액공사","- 웅촌E/C 154kV #1Sh.C MAIN GIS 정밀점검 시험가압선로 1H","2019-11-05 17:00","2019-11-05 18:00","2019-11-05 17:00","2019-11-05 18:00","당일"]
[584,"부산울산","직할","범일서면#1 T/L","범일,서면S/S 범일-서면#1T/L 보호배전반 성능개선(제작사 가보)","- 범일,서면E/C 범일-서면#1,2T/L 보호배전반 성능개선(제작사 가보)","2019-11-04 10:00","2019-11-04 14:00","2019-11-04 10:00","2019-11-04 14:00","당일"]
[585,"부산울산","직할","범일서면#2 T/L","범일,서면S/S 범일-서면#1T/L 보호배전반 성능개선(제작사 가보)","- 범일,서면E/C 범일-서면#1,2T/L 보호배전반 성능개선(제작사 가보)","2019-11-04 14:00","2019-11-04 18:00","2019-11-04 14:00","2019-11-04 18:00","당일"]
[586,"부산울산","북부산","양산산막#1 T/L","양산S/S 현대화공사","154kV #1Sh.C 시험가압 선로","2019-11-28 18:00","2019-11-29 18:00","2019-11-28 18:00","2019-11-29 18:00","연속"]
[587,"경남","직할","녹공마천#2 T/L","마천S/S 154kV 녹공-마천#2T/L 보호PNL 대체","마천S/S 154kV 녹공-마천#2T/L 보호PNL 대체 및 CB 조작시험","2019-11-11 09:30","2019-11-13 17:30","취소","취소","연속"]
[588,"경남","직할","녹공마천#1 T/L","마천S/S 154kV 녹공-마천#1T/L 보호PNL 대체","마천S/S 154kV 녹공-마천#1T/L 보호PNL 대체 및 CB 조작시험","2019-11-04 09:30","2019-11-06 17:30","2019-11-25 10:00","2019-11-27 18:00","연속"]
[589,"경남","직할","신김해지사#2 T/L","신김해S/S 신김해-지사 #2T/L CB 조작시험 점검","신김해S/S 신김해-지사 #2T/L CB 조작시험 점검","2019-11-07 09:30","2019-11-07 17:30","2019-11-07 09:30","2019-11-07 17:30","당일"]
[590,"경남","직할","주촌삼계#2 T/L","154kV 주촌E/C #4M.Tr 증설공사","주촌E/C #4M.Tr 증설관련 무부하시험가압 선로","2019-11-20 14:00","2019-11-21 15:00","2019-11-20 14:00","2019-11-21 15:00","연속"]
[591,"경남","직할","창원S/S 154kV #66 BUS","창원S/S 154kV #3Sh.C CB 정밀점검","창원S/S 154kV #3Sh.C CB 정밀점검 시험가압선로 : #61-66 BUS-TIE, #66BUS","2019-11-12 16:00","2019-11-13 18:00","2019-11-12 16:00","2019-11-13 18:00","당일"]
[592,"경남","직할","창원S/S 154kV #3 Sh.C CB","창원S/S 154kV #3Sh.C CB 정밀점검","창원S/S 154kV #3Sh.C CB 정밀점검","2019-11-04 08:00","2019-11-13 18:00","2019-11-04 08:00","2019-11-13 18:00","연속"]
[593,"경남","진주","의령산청 T/L","의령S/S 154kV 의령-산청T/L LA 대체작업","의령S/S 154kV 의령-산청T/L LA 대체작업","2019-11-16 10:00","2019-11-16 17:00","2019-11-16 10:00","2019-11-16 17:00","당일"]
[594,"경남","진주","의령S/S 154kV #1 EM.Tr CB","의령S/S 154kV #1EM.Tr 1차 CB(E6133) 조작시험","의령S/S 154kV #1EM.Tr 1차 CB(E6133) 조작시험","2019-11-21 10:00","2019-11-21 14:00","2019-11-21 10:00","2019-11-21 14:00","당일"]
[595,"경남","진주","광양하동#2 T/L","하동E/C 154kV #2M.Tr 용량변경공사","무부하시험가압을 위한 시험가압선로","2019-11-21 15:00","2019-11-22 15:00","2019-11-23 15:00","2019-11-24 15:00","연속"]
[596,"경남","진주","의령함양 T/L","함양S/S 의령-함양T/L(667) CB 조작시험","함양S/S 의령-함양T/L(667) CB 조작시험","2019-11-30 10:00","2019-11-30 14:00","2019-11-30 10:00","2019-11-30 14:00","당일"]
[597,"경남","진주","합천S/S 154kV #60-#65 BUS TIE CB","합천S/S 154kV BUS PRO 보호반 대체","합천S/S 154kV BUS PRO 보호반 대체","2019-11-18 09:00","2019-11-20 18:00","2019-11-18 09:00","2019-11-20 18:00","연속"]
[598,"경남","통영","고성통영 T/L","154kV 고성-통영T/L 정밀점검","154kV 고성-통영T/L 정밀점검(96~147호)","2019-11-02 09:00","2019-11-03 18:00","2019-11-02 12:00","2019-11-03 18:00","매일"]
[599,"경남","함안","동읍S/S 154kV 신월-동읍#2T/L GIS","동읍S/S 154kV 신월-동읍#2T/L GIS 조작시험","동읍S/S 154kV 신월-동읍#2T/L GIS 조작시험","2019-11-26 13:30","2019-11-26 17:30","2019-11-26 13:30","2019-11-26 17:30","당일"]
[600,"경남","함안","동읍S/S 154kV 신월-동읍#1T/L GIS","동읍S/S 154kV 신월-동읍#1T/L GIS 조작시험","동읍S/S 154kV 신월-동읍#1T/L GIS 조작시험","2019-11-26 09:30","2019-11-26 13:30","2019-11-26 09:30","2019-11-26 13:30","당일"]
[601,"경남","함안","신마산S/S 154kV 신마산-마산#2T/L CB","신마산S/S 154kV 신마산-마산#2T/L CB 조작시험","신마산S/S 154kV 신마산-마산#2T/L CB 조작시험 (병행 : 마산S/S 154kV 신마산-마산#2T/L CB 조작시험)","2019-11-04 09:30","2019-11-04 13:30","2019-11-04 09:30","2019-11-04 13:30","당일"]
[602,"경남","함안","신마산S/S 154kV #60-#65 BUS TIE CB","신마산S/S 154kV #60-#65 BUS TIE CB 조작시험","신마산S/S 154kV #60-#65 BUS TIE CB 조작시험","2019-11-04 13:30","2019-11-04 15:30","2019-11-04 13:30","2019-11-04 15:30","당일"]
[603,"경남","함안","신마산S/S 154kV #61-#66 BUS TIE CB","신마산S/S 154kV #61-#66 BUS TIE CB 조작시험","신마산S/S 154kV #61-#66 BUS TIE CB 조작시험","2019-11-04 15:30","2019-11-04 17:30","2019-11-04 15:30","2019-11-04 17:30","당일"]
[604,"경남","함안","신마산S/S 154kV #60-#61 SEC CB","신마산S/S 154kV #60-#61 SEC CB 조작시험","신마산S/S 154kV #60-#61 SEC CB 조작시험","2019-11-11 09:30","2019-11-11 13:30","2019-11-11 09:30","2019-11-11 13:30","당일"]
[605,"경남","함안","신마산S/S 154kV #65-#66 SEC CB","신마산S/S 154kV #65-#66 SEC CB 조작시험","신마산S/S 154kV #65-#66 SEC CB 조작시험","2019-11-11 13:30","2019-11-11 15:30","2019-11-11 13:30","2019-11-11 15:30","당일"]
[606,"경남","함안","신마산S/S 154kV #60 BUS","신마산S/S 154kV #60 BUS PT,LA 보통점검","신마산S/S 154kV #60 BUS PT,LA 보통점검","2019-11-12 09:30","2019-11-12 13:30","2019-11-12 09:30","2019-11-12 13:30","당일"]
[607,"경남","함안","신마산S/S 154kV #65 BUS","신마산S/S 154kV #65 BUS PT,LA 보통점검","신마산S/S 154kV #65 BUS PT,LA 보통점검","2019-11-12 13:30","2019-11-12 17:30","2019-11-12 13:30","2019-11-12 17:30","당일"]
[608,"경남","함안","신마산S/S 154kV #61 BUS","신마산S/S 154kV #61 BUS PT,LA 보통점검","신마산S/S 154kV #61 BUS PT,LA 보통점검","2019-11-13 09:30","2019-11-13 13:30","2019-11-13 09:30","2019-11-13 13:30","당일"]
[609,"경남","함안","신마산S/S 154kV #66 BUS","신마산S/S 154kV #66 BUS PT,LA 보통점검","신마산S/S 154kV #66 BUS PT,LA 보통점검","2019-11-13 13:30","2019-11-13 17:30","2019-11-13 13:30","2019-11-13 17:30","당일"]
[610,"경남","함안","칠서S/S 154kV #60 BUS","칠서S/S 154kV #60 BUS 모선구분차단기 설치","칠서S/S 154kV #60 BUS 모선구분차단기 설치","2019-11-06 09:00","2019-11-15 18:30","2019-11-06 09:00","2019-11-15 18:30","연속"]
[611,"경남","함안","칠서S/S 154kV 신마산-칠서#1T/L GIS","칠서S/S 154kV #60 BUS 모선구분차단기 설치 안전이격거리 확보","칠서S/S 154kV #60 BUS 모선구분차단기 설치 안전이격거리 확보 OPGW 증설 병행","2019-11-09 09:00","2019-11-11 18:30","2019-11-09 09:00","2019-11-11 18:30","연속"]
[612,"경남","함안","칠서S/S 154kV #65 BUS","칠서S/S 154kV #65 BUS 모선구분차단기 설치","칠서S/S 154kV #65 BUS 모선구분차단기 설치","2019-11-19 09:00","2019-11-29 18:30","2019-11-19 09:00","2019-11-29 18:30","연속"]
[613,"경남","함안","칠서S/S 154kV 신마산-칠서#1T/L GIS","칠서S/S 154kV #65 BUS 모선구분차단기 설치 안전이격거리 확보","칠서S/S 154kV #65 BUS 모선구분차단기 설치 안전이격거리 확보 OPGW 증설 병행","2019-11-23 09:00","2019-11-25 18:30","2019-11-23 09:00","2019-11-25 18:30","연속"]
[614,"경남","함안","칠서S/S 154kV 신마산-칠서#2T/L GIS","칠서S/S 154kV 신마산-칠서#2T/L GIS 조작시험","칠서S/S 154kV 신마산-칠서#2T/L GIS 조작시험","2019-11-02 09:30","2019-11-02 13:30","2019-11-02 09:30","2019-11-02 13:30","당일"]