{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["종합","765송부","345송부","154송부"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":13,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"종합","index":0,"n_rows":37,"n_cols":33,"rows_kept":37,"cut":false,"hidden":true,"merged":[[0,0,0,15],[7,14,7,15],[7,1,7,2],[8,1,8,2],[7,9,7,13],[7,3,7,6],[8,3,8,6],[14,14,14,15],[10,1,10,2],[11,1,11,2],[14,9,14,13],[9,1,9,2],[14,2,14,6],[11,3,11,6],[10,3,10,6],[9,3,9,6]]}
[{"$f":"\"'19년 \"&R15&\"월 휴전심의 결과\"","v":"'19년 12월 휴전심의 결과"}]
[]
[]
[]
[]
[]
["◎ 전체 심의결과"]
["전   압","신 청",null,"채 택",null,null,null,"일정\n조정","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)"]
["765kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B9-I9","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J9,L9,N9)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O9/B9)","v":{"$error":"#REF!"}}]
["345kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B10-I10","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J10,L10,N10)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O10/B10)","v":{"$error":"#REF!"}}]
["154kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B11-I11","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J11,L11,N11)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O11/B11)","v":{"$error":"#REF!"}}]
["계",{"$f":"SUM(B9:B11)","v":{"$error":"#REF!"}},null,{"$f":"SUM(D9:D11)","v":{"$error":"#REF!"}},null,null,null,{"$f":"SUM(H9:H11)","v":{"$error":"#REF!"}},{"$f":"SUM(J12,L12,N12)","v":{"$error":"#REF!"}},{"$f":"SUM(J9:J11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(L9:L11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(N9:N11)","v":{"$error":"#REF!"}},{"$f":"SUM(O9:O11)","v":{"$error":"#REF!"}},{"$f":"(O12/B12)","v":{"$error":"#REF!"}}]
[]
["◎ 본부별 심의결과",{"$nulls":16},"월"]
["사업소","신 청","(765/345/154)",{"$nulls":4},"채 택","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)",null,null,12]
["서   울",{"$f":"SUM(C16:G16)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},{"$f":"B16-I16","v":{"$error":"#REF!"}},{"$f":"SUM(J16,L16,N16)","v":{"$error":"#REF!"}},{"$f":"SUM(S16:U16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W16:Y16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA16:AC16)","v":{"$error":"#REF!"}},{"$f":"SUM(AE16:AG16)","v":{"$error":"#REF!"}},{"$f":"(O16/B16)","v":{"$error":"#REF!"}},null,"서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}}]
["남서울",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$f":"SUM(J17,L17,N17)","v":{"$error":"#REF!"}},{"$f":"SUM(S17:U17)","v":{"$error":"#REF!"}},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"남서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}}]
["인   천",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"인천",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}}]
["경기북부",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기북부",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}}]
["경   기",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}}]
["강   원",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"강원",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}}]
["충   북",{"$f":"SUM(C22:G22)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"충북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}}]
["대전충남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"대전충남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}}]
["전   북",{"$f":"SUM(C24:G24)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"전북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}}]
["광주전남",{"$f":"SUM(C25:G25)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"광주전남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}}]
["대구",{"$f":"SUM(C26:G26)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},{"$f":"B26-I26","v":{"$error":"#REF!"}},{"$f":"SUM(J26,L26,N26)","v":{"$error":"#REF!"}},{"$f":"SUM(S26:U26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W26:Y26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA26:AC26)","v":{"$error":"#REF!"}},{"$f":"SUM(AE26:AG26)","v":{"$error":"#REF!"}},{"$f":"(O26/B26)","v":{"$error":"#REF!"}},null,"대구",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}}]
["경북",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}}]
["부산울산",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"부산울산",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}}]
["경   남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$f":"SUM(W29:Y29)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA29:AC29)","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},null,"경남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}}]
["제   주",{"$f":"SUM(C30:G30)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$f":"(O30/B30)","v":{"$error":"#REF!"}},null,"제주",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}}]
[]
[" 붙임 :  1. 집중심의내역 1부"]
[" 붙임 :  전압별 검토서 1부. 끝."]
[]
[null,{"$f":"SUM(B16:B30)","v":{"$error":"#REF!"}},{"$f":"SUM(C16:C30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(E16:E30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(G16:G30)","v":{"$error":"#REF!"}},{"$f":"SUM(H16:H30)","v":{"$error":"#REF!"}},{"$f":"SUM(I16:I30)","v":{"$error":"#REF!"}},{"$f":"SUM(J16:J30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(L16:L30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(N16:N30)","v":{"$error":"#REF!"}},{"$f":"SUM(O16:O30)","v":{"$error":"#REF!"}}]
[{"$f":"COUNTIF(B36:N36,\"NO\")","v":0},{"$f":"IF(B35=B12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(C35=B9,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(E35=B10,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(G35=B11,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(H35=D12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(I35=I12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(J35=J12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(L35=L12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(N35=N12,\"\",\"NO\")","v":{"$error":"#REF!"}}]
[{"$f":"IF(A36>=1,\"틀린곳\",\"\")","v":""},{"$f":"IF(B36=\"NO\",\"총계\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C36=\"NO\",\"765\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(D36=\"NO\",\"총계\",\"\")","v":""},{"$f":"IF(E36=\"NO\",\"345\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(G36=\"NO\",\"154\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(H36=\"NO\",\"채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(I36=\"NO\",\"불채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(J36=\"NO\",\"병행\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(L36=\"NO\",\"취소\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(N36=\"NO\",\"연기\",\"\")","v":{"$error":"#REF!"}}]

{"sheet":"765송부","index":1,"n_rows":8,"n_cols":13,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 12월 휴전계획서"}]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성S/S 765kV #85 BUS","모선보호반 대체","모선보호반 대체","2019-12-16 09:00","2019-12-29 18:00","취소","취소","연속"]
[2,"경기","성남","신안성S/S 765kV #80 BUS","모선보호반 대체 및 GIS 정밀점검공사","- 모선보호반 대체 - 765kV GIS 정밀점검공사","2019-12-02 09:00","2019-12-13 18:00","2019-12-02 09:00","2019-12-13 18:00","연속"]
[3,"경남","함안","북경남S/S #3 M.Tr A-1","북경남S/S #3M.Tr 보호반 성능개선","북경남S/S #3M.Tr 보호반 성능개선(YPP제 보호반 성능개선, DS접점 직결)","2019-12-06 09:00","2019-12-06 18:00","2019-12-10 09:00","2019-12-10 18:00","연속"]
[4,"경남","함안","북경남신고리NP#1 T/L","765kV 북경남-신고리NP #1 T/L 착설방지링 설치","765kV 북경남-신고리NP #1 T/L 착설방지링 설치","2019-12-02 08:30","2019-12-05 18:00","취소","취소","매일"]

{"sheet":"345송부","index":2,"n_rows":123,"n_cols":13,"rows_kept":123,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 12월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","부평","서인천C/C #3 Tie-Tr","서인천C/C #3M.Tr 1차 부싱절연유 채유","서인천C/C #3M.Tr 1차 부싱절연유 채유","2019-12-02 09:00","2019-12-02 18:00","2019-12-02 09:00","2019-12-02 18:00","연속"]
[2,"인천","부평","서인천C/C #4 Tie-Tr","서인천CC #4M.Tr 1차 부싱절연유 채유","서인천CC #4M.Tr 1차 부싱절연유 채유","2019-12-04 09:00","2019-12-04 18:00","2019-12-04 09:00","2019-12-04 18:00","연속"]
[3,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S #4M.Tr 1,2차 부싱절연유 채유","신가좌S/S #4M.Tr 1,2차 부싱절연유 채유","2019-12-18 09:00","2019-12-18 18:00","2019-12-18 09:00","2019-12-18 18:00","연속"]
[4,"인천","부평","신경서S/S #2 M.Tr","신경서S/S #2M.Tr 휴전작업","신경서S/S #2M.Tr 휴전작업 - #2M.Tr 1차측 옥외분전반 대체 - 3차측 LA 대체","2019-12-02 09:00","2019-12-03 18:00","2019-12-02 09:00","2019-12-03 18:00","연속"]
[5,"인천","부평","신경서S/S #3 M.Tr","신경서S/S #3M.Tr 1,2차 부싱절연유 채유","신경서S/S #3M.Tr 1,2차 부싱절연유 채유","2019-12-16 09:00","2019-12-16 18:00","2019-12-16 09:00","2019-12-16 18:00","연속"]
[6,"인천","부평","인천C/C #1 Tie-Tr","인천C/C #1Tie-Tr 1,2차부싱절연유 채유","인천CC #1Tie-Tr 1,2차 부싱절연유 채유","2019-12-09 09:00","2019-12-09 18:00","2019-12-09 09:00","2019-12-09 18:00","연속"]
[7,"인천","시흥","신시흥신광명#1 T/L","신시흥S/S 신시흥신광명#1T/L 피뢰기대체","신시흥S/S 신시흥신광명#1T/L 피뢰기대체","2019-12-02 09:00","2019-12-03 18:00","취소","취소","연속"]
[8,"경기북부","고양","신덕은S/S #2 M.Tr","2019년 고양P/O 변전정비회사 총액공사","신덕은S/S #2M.Tr 3차 피뢰기(21kV) 교체공사","2019-12-07 09:00","2019-12-07 13:00","2019-12-07 09:00","2019-12-07 13:00","연속"]
[9,"경기북부","고양","신덕은S/S #1 M.Tr","디지털압력감시장치 시범적용차","신덕은S/S #1M.Tr 디지털압력감시장치 시범적용차","2019-12-07 13:00","2019-12-08 18:00","2019-12-07 13:00","2019-12-08 18:00","연속"]
[10,"경기북부","구리","미금성동#1 T/L","미금S/S 감시제어설비 교체공사","장기노후 모자익반 교체","2019-12-02 09:00","2019-12-06 18:00","취소","취소","연속"]
[11,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 감시제어설비 교체공사","장기노후 모자익반 교체","2019-12-02 09:00","2019-12-06 18:00","취소","취소","연속"]
[12,"경기북부","구리","신가평S/S 345kV #75 BUS","19년 구리전력지사 345kV GIS 정밀점검공사","신가평S/S 7372 GIS 정밀점검(7352DS 정밀점검)","2019-12-02 09:00","2019-12-03 18:00","취소","취소","연속"]
[13,"경기북부","구리","신가평포천LNGCC#2 T/L","19년 구리전력지사 345kV GIS 정밀점검공사","신가평S/S 7372 GIS 정밀점검","2019-12-02 09:00","2019-12-11 18:00","취소","취소","연속"]
[14,"경기북부","직할","양주S/S #3 M.Tr","양주S/S 345kV #3M.Tr 하자점검 및 부싱 절연유 채유","양주S/S 345kV #3M.Tr C상 하자점검 양주S/S 345kV #3M.Tr A, B상 부싱절연유 채유 및 절연열화 측정","2019-12-09 09:00","2019-12-10 18:00","2019-12-09 09:00","2019-12-10 18:00","연속"]
[15,"경기북부","직할","양주S/S #2 M.Tr","양주S/S 345kV M.Tr 부싱 대체 및 정밀점검 공사","#2M.Tr B 정밀점검 및 1차, 2차 부싱 대체","2019-12-02 09:00","2019-12-06 18:00","2019-12-02 09:00","2019-12-06 18:00","연속"]
[16,"경기","군포","신안산S/S 345kV #2 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #72BAY(#3M.Tr) 용량대체 - 345kV #2BUS측 무부하가압용","2019-12-11 09:00","2019-12-11 14:00","2019-12-11 09:00","2019-12-11 14:00","연속"]
[17,"경기","군포","신안산S/S 345kV #1 BUS","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #72BAY(#3M.Tr) 용량대체 - 345kV #1BUS측 무부하가압용","2019-12-11 14:00","2019-12-12 14:00","2019-12-11 14:00","2019-12-12 14:00","연속"]
[18,"경기","군포","신시흥신안산#2 T/L","345kV 신안산S/S 용량부족 GIS 대체공사","345kV 신안산S/S 용량부족 GIS 대체공사 - #72BAY(#3M.Tr) 용량대체 - 345kV #1BUS측 무부하가압용 선로","2019-12-11 14:00","2019-12-12 14:00","2019-12-11 14:00","2019-12-12 14:00","연속"]
[19,"경기","성남","서안성신진천#2 T/L","송전정비회사 총액공사(전력선교체)","ㅇ#2T/L 84-86 하단 2가닥 전력선 교체","2019-12-07 08:00","2019-12-08 18:00","2019-12-13 08:00","2019-12-13 18:00","연속"]
[20,"경기","성남","신안성신성남#1 T/L","345kV 신용인-동서울#1T/L 애자련 교체공사","- 345kV 신용인-동서울#1T/L 3기 애자련 교체 관련 안전이격거리 확보차","2019-12-02 08:00","2019-12-03 18:00","취소","취소","연속"]
[21,"경기","성남","신성남S/S STATCOM CB","STATCOM 냉각설비 점검","STATCOM 냉각설비 점검","2019-12-02 09:00","2019-12-04 18:00","취소","취소","연속"]
[22,"경기","성남","신안성신성남#2 T/L","345kV 신성남-동서울#2T/L 애자련 교체공사","345kV 신성남-동서울#2T/L 2기 애자련 교체 관련 안전이격거리 확보차","2019-12-08 08:00","2019-12-09 18:00","취소","취소","연속"]
[23,"경기","성남","신안성신성남#2 T/L","345kV 신용인-동서울#2T/L 애자련 교체공사","- 345kV 신용인-동서울#2T/L 2기 애자련 교체 관련 안전이격거리 확보차","2019-12-04 08:00","2019-12-05 18:00","취소","취소","연속"]
[24,"경기","성남","신안성신성남#1 T/L","345kV 신성남-동서울#1T/L 애자련 교체공사","- 345kV 신성남-동서울#1T/L 3기 애자련 교체 관련 안전이격거리 확보차","2019-12-06 08:00","2019-12-07 18:00","취소","취소","연속"]
[25,"경기","성남","신성남동서울#1 T/L","345kV 신성남-동서울#1T/L 애자련 교체공사","- 345kV 신성남-동서울#1T/L 3기 애자련 교체","2019-12-06 08:00","2019-12-07 18:00","취소","취소","연속"]
[26,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울#1T/L 애자련 교체공사","- 345kV 신용인-동서울#1T/L 3기 애자련 교체","2019-12-02 08:00","2019-12-03 18:00","취소","취소","연속"]
[27,"경기","성남","신안성신용인#2 T/L","LA 하자점검","LA 하자점검","2019-12-06 14:00","2019-12-06 18:00","2019-12-06 14:00","2019-12-06 18:00","연속"]
[28,"경기","성남","신안성신용인#1 T/L","LA 하자점검","LA 하자점검","2019-12-06 09:00","2019-12-06 14:00","2019-12-06 09:00","2019-12-06 14:00","연속"]
[29,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울#2T/L 애자련 교체공사","- 345kV 신용인-동서울#2T/L 3기 애자련 교체","2019-12-04 08:00","2019-12-05 18:00","취소","취소","연속"]
[30,"경기","직할","화성신안산 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-신안산#1T/L 이용 77BAY #76BUS 무부하 가압","2019-12-24 16:00","2019-12-26 10:00","취소","취소","연속"]
[31,"경기","직할","화성S/S 345kV #76 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-신안산#1T/L 이용 77BAY #76BUS 무부하 가압","2019-12-24 16:00","2019-12-26 10:00","취소","취소","연속"]
[32,"경기","직할","화성신안산 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-신안산#1T/L 이용 77BAY #71BUS 무부하 가압","2019-12-23 16:00","2019-12-24 16:00","취소","취소","연속"]
[33,"경기","직할","화성S/S 345kV #71 BUS","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-신안산#1T/L 이용 77BAY #71BUS 무부하 가압","2019-12-23 16:00","2019-12-24 16:00","취소","취소","연속"]
[34,"경기","직할","화성S/S #4 M.Tr","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. #3M.Tr측 POST 및 BEAM 보강 안전이격거리 확보","2019-12-09 09:00","2019-12-12 17:00","취소","취소","연속"]
[35,"경기","직할","화성S/S #3 M.Tr","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. #3M.Tr측 POST 및 BEAM 보강 안전이격거리 확보","2019-12-02 09:00","2019-12-05 17:00","취소","취소","연속"]
[36,"경기","직할","화성평택T/P#1 T/L","345kV 화성S/S GIS 용량대체 및 SW증설공사","O. 362kV (40/50kA -> 63kA) GIS 30대 교체 O. 화성-평택T/P #1T/L 7BBAY -> 77BAY 이설","2019-12-09 09:00","2019-12-27 18:00","취소","취소","연속"]
[37,"경기","성남","서안성S/S #4M.Tr","서안성S/S #4M.Tr 제작사 하자처리","서안성S/S #4M.Tr 제작사 하자처리","2019-12-02 09:00","2019-12-02 18:00","취소","취소","연속"]
[38,"경기","성남","신용인동서울#1T/L","345kV 신성남-동서울T/L OPGW 시설공사(대장지구)","345kV 신성남-동서울T/L OPGW 시설공사(대장지구)(안전이격)","2019-12-10 07:00","2019-12-10 18:00","취소","취소","연속"]
[39,"경기","성남","신성남동서울#2T/L","345kV 신성남-동서울T/L OPGW 시설공사(대장지구)","345kV 신성남-동서울T/L OPGW 시설공사(대장지구)","2019-12-08 07:00","2019-12-10 18:00","취소","취소","연속"]
[40,"강원","강릉","신양양S/S #1 M.Tr","신양양S/S 345kV #1 M.Tr A 과열개소 보수","신양양S/S 345kV #1 M.Tr A 과열개소 보수","2019-12-02 10:00","2019-12-02 18:00","2019-12-02 10:00","2019-12-02 18:00","연속"]
[41,"강원","동해","삼척G/P 345kV #1STEP UP GIS(7772)","삼척GP 345kV GIS 누유개소 보수","1. 누유개소 보수","2019-12-03 10:00","2019-12-03 18:00","2019-12-03 10:00","2019-12-03 18:00","연속"]
[42,"강원","태백","신태백S/S #73 BAY T/L CB(7372)","'19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7372CB 러버히터설치","2019-12-04 10:00","2019-12-04 14:00","2019-12-04 10:00","2019-12-04 14:00","연속"]
[43,"강원","태백","신태백S/S #2 M.Tr 2차 TIE CB(7300)","'19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7300CB 러버히터설치","2019-12-03 14:00","2019-12-03 18:00","2019-12-03 14:00","2019-12-03 18:00","연속"]
[44,"강원","태백","신태백S/S #2 M.Tr 2차 CB(7371)","'19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7371CB 러버히터설치 및 전자변상태 점검","2019-12-03 10:00","2019-12-03 14:00","2019-12-03 10:00","2019-12-03 14:00","연속"]
[45,"강원","태백","신태백S/S 신태백-한울N/P2#1T/L CB(7572)","'19년 태백전력지사 변전전문회사 총액공사","신태백변전소 7572CB 러버히터설치","2019-12-04 14:00","2019-12-04 18:00","2019-12-04 14:00","2019-12-04 18:00","연속"]
[46,"충북","직할","서안성신진천#2 T/L","2018~19년 충주전력지사 송전정비회사 총액공사","스페이서교체(17~19)","2019-12-03 07:00","2019-12-03 18:00","취소","취소","연속"]
[47,"충북","청주","세종남청주#1 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","154kV 남청주-오송#1T/L 가공지선 교체 : No.4~5","2019-12-08 07:00","2019-12-08 18:00","2019-12-08 07:00","2019-12-08 18:00","연속"]
[48,"충북","청주","신옥천S/S #3 M.Tr","신옥천S/S 154kV GIS화 공사","옥외철구 POST, BEAM 철거 관련 안전이격 확보","2019-12-04 09:00","2019-12-04 18:00","2019-12-04 09:00","2019-12-04 18:00","연속"]
[49,"충북","청주","신옥천S/S #1 M.Tr","신옥천S/S 154kV GIS화 공사","옥외철구 POST, BEAM 철거 관련 안전이격 확보","2019-12-02 09:00","2019-12-02 18:00","취소","취소","연속"]
[50,"충북","청주","신옥천신남원#2 T/L","345kV 신옥천-신남원 T/L 스페이서 설치간격 조정공사","345kV 신옥천-신남원 T/L 55경간 스페이서 설치간격 조정공사","2019-12-09 09:00","2019-12-15 18:00","2019-12-04 09:00","2019-12-10 18:00","매일"]
[51,"충북","청주","신옥천신남원#1 T/L","345kV 신옥천-신남원 T/L 스페이서 설치간격 조정공사","345kV 신옥천-신남원 T/L 55경간 스페이서 설치간격 조정공사","2019-12-02 09:00","2019-12-08 18:00","2019-11-27 08:00","2019-12-03 18:00","매일"]
[52,"충북","청주","신옥천S/S #2 M.Tr","신옥천S/S 154kV GIS화 공사","옥외철구 POST, BEAM 철거 관련 안전이격 확보","2019-12-03 09:00","2019-12-03 18:00","2019-12-03 09:00","2019-12-03 18:00","연속"]
[53,"충북","충주","신제천S/S #3 M.Tr","'18-19년 변전정비회사 총액공사","신제천S/S #3M.Tr 23kV 3차측 AL 모선조정","2019-12-06 09:00","2019-12-06 18:00","2019-12-06 09:00","2019-12-06 18:00","연속"]
[54,"대전충남","대전","신계룡S/S #2 M.Tr","신계룡S/S 345kV #2M.Tr 1차 차단기 동작시험 및 병행작업","신계룡S/S 345kV #2M.Tr 1차 차단기 동작시험 및 병행작업","2019-12-04 09:00","2019-12-04 18:00","2019-12-04 09:00","2019-12-04 18:00","연속"]
[55,"대전충남","대전","신옥천신계룡 T/L","[송전] 345kV 신옥천-신계룡T/L 전선접속개소 전력선 교체공사","[송전] 345kV 신옥천-신계룡T/L 전선접속개소 전력선 교체 (No.1~4,6~8)","2019-12-02 07:00","2019-12-06 18:00","취소","취소","연속"]
[56,"대전충남","서산","북당진S/S #4-1 M.Tr TIE CB(7700)","345kV 북당진E/C #1M.Tr용 362kV GIS 설치공사","#70BUS 인터록 시험및 무부하 가압(7651DS, 7671CB, 7661DS)","2019-12-07 10:00","2019-12-08 14:00","2019-12-07 10:00","2019-12-08 14:00","연속"]
[57,"대전충남","서산","북당진S/S 345kV #75 BUS","345kV 북당진E/C #1M.Tr용 362kV GIS 설치공사","#70BUS 인터록 시험및 무부하 가압(7651DS, 7671CB, 7661DS)","2019-12-07 10:00","2019-12-08 14:00","2019-12-07 10:00","2019-12-08 14:00","연속"]
[58,"대전충남","서산","북당진S/S #4-1 M.Tr CB(7772)","345kV 북당진E/C #1M.Tr용 362kV GIS 설치공사","#70BUS 인터록 시험및 무부하 가압(7651DS, 7671CB, 7661DS)","2019-12-07 10:00","2019-12-08 14:00","2019-12-07 10:00","2019-12-08 14:00","연속"]
[59,"대전충남","서산","신당진개폐소 345kV 신당진개폐소-태안TP#2T/L GIS(7C71)","19년 서산P/O 변전협력 총액공사","신당진S/S 345kV 개폐소-태안화력#2T/L GIS(7C71) 하자점검","2019-12-06 09:00","2019-12-06 18:00","2019-12-06 09:00","2019-12-06 18:00","연속"]
[60,"대전충남","서산","신당진개폐소태안TP#1 T/L","19년 서산P/O 변전협력 총액공사","보호반 성능개선","2019-12-02 09:00","2019-12-02 18:00","취소","취소","연속"]
[61,"대전충남","서산","신당진S/S #1 M.Tr","19년 서산P/O 변전협력 총액공사","345kV #1M.Tr 2차 (6144)GIS 전자변교체 및 1차 LA 하자점검","2019-12-02 09:00","2019-12-02 18:00","2019-12-02 09:00","2019-12-02 18:00","연속"]
[62,"대전충남","서산","신당진S/S 신서산-신당진#2T/L CB(7772)","'19년 차단기 부동작 시험","신당진S/S 신서산-신당진#2T/L (7772) CB 부동작 예방시험","2019-12-03 10:00","2019-12-03 14:00","2019-12-03 10:00","2019-12-03 14:00","연속"]
[63,"대전충남","서산","신당진S/S #2 M.Tr","19년 서산P/O 변전협력 총액공사","신당진S/S 345kV #2 M.Tr 2차 6244 GIS 전자변교체 및 1차 LA 하자점검","2019-12-05 09:00","2019-12-05 18:00","2019-12-05 09:00","2019-12-05 18:00","연속"]
[64,"대전충남","청양","청양S/S #75-#76 SEC CB","청양S/S 345kV 차단기 부동작 예방 조작시험","청양S/S 345kV 차단기 부동작 예방 조작시험 - 대상 : 75-76","2019-12-03 13:00","2019-12-03 18:00","2019-12-03 13:00","2019-12-03 18:00","연속"]
[65,"대전충남","청양","신옥천청양 T/L","[송전] 345kV 신옥천-청양T/L 정밀점검","[송전] 345kV 신옥천-청양T/L 정밀점검 (No.84-1~92,106~119)","2019-12-09 08:00","2019-12-12 18:00","취소","취소","매일"]
[66,"대전충남","청양","청양S/S #70-#71 SEC CB","청양S/S 345kV 차단기 부동작 예방 조작시험","청양S/S 345kV 차단기 부동작 예방 조작시험 - 대상 : 70-71","2019-12-03 09:00","2019-12-03 13:00","2019-12-03 09:00","2019-12-03 13:00","연속"]
[67,"전북","군산","청양군산#1 T/L","청양군산1TL 압력계 교체","7371CB Air 압력계 교체","2019-12-02 09:00","2019-12-02 18:00","취소","취소","연속"]
[68,"전북","김제","군산신김제#2 T/L","2019년 345kV GIS 정밀점검공사","- 차단기 내부 분해점검 - 기타부태공사 1식","2019-12-01 09:00","2019-12-12 18:00","취소","취소","연속"]
[69,"전북","김제","신김제S/S 군산-신김제#1T/L TIE CB (7200)","관내S/S 345kV GIS 보통점검","관내S/S 154kV GIS 보통점검, T/L 미휴전","2019-12-13 10:00","2019-12-13 18:00","2019-12-13 10:00","2019-12-13 18:00","연속"]
[70,"전북","김제","군산신김제#1 T/L","2019년 345kV GIS 정밀점검공사","- 차단기 내부 분해점검 - 기타부태공사 1식","2019-12-13 09:00","2019-12-24 18:00","취소","취소","연속"]
[71,"전북","직할","북경남무주양수 T/L","345kV 신옥천-북경남T/L 전력선 교체공사","345kV 신옥천-북경남T/L 전력선 교체공사 구 간 : 신옥천-북경남 No.253~255 등 5경간(4.5km) 작업내용 : 전선접속개소 전력선 교체공사","2019-12-01 08:00","2019-12-10 18:00","취소","취소","연속"]
[72,"전북","직할","신남원한빛NP#2 T/L","신남원SS 345kV 신남원-한빛#2T/L LA점검공사","신남원SS 345kV 신남원-한빛#2T/L LA점검공사","2019-12-17 10:00","2019-12-17 18:00","2019-12-17 10:00","2019-12-17 18:00","연속"]
[73,"전북","직할","신남원신광주#2 T/L","장기 사용 송전선로 보호배전반 대체공사","신남원-신광주 #2 T/L 보호배전반 대체","2019-12-16 09:00","2019-12-24 18:00","2019-12-16 09:00","2019-12-24 18:00","연속"]
[74,"광주전남","강진","신화순신강진#1 T/L","신강진S/S 345kV 취약설비 GIS화","- 옥외철구 -> GIS화","2019-12-04 07:00","2019-12-31 18:00","2019-11-30 08:00","2019-12-27 18:00","연속"]
[75,"광주전남","광주","신강진광양#1 T/L"," '18~19년 송전정비협력회사 총액공사","345kV 신강진-광양#1T/L 불량애자교체 - No.152 ~ 273호, 총 8기","2019-12-09 07:00","2019-12-11 18:00","2019-12-09 07:00","2019-12-11 18:00","매일"]
[76,"광주전남","강진","신강진S/S #2M.Tr","신강진S/S 345kV 취약설비 GIS화","- 옥외철구 -> GIS화 - 이격거리 확보","2019-12-04 07:00","2019-12-06 18:00","2019-12-02 08:00","2019-12-04 18:00","연속"]
[77,"광주전남","강진","신강진S/S #2M.Tr","신강진S/S 345kV 취약설비 GIS화","- 옥외철구 -> GIS화 - 이격거리 확보","2019-12-24 07:00","2019-12-26 18:00","2019-12-24 07:00","2019-12-26 18:00","연속"]
[78,"광주전남","광주","신광주S/S #4 M.Tr","19년 광주 변전총액공사(#4M.Tr B/F 판넬대체)","신광주S/S 345kV #4M.Tr B/F 판넬대체","2019-12-09 09:00","2019-12-13 18:00","취소","취소","연속"]
[79,"대구","경산","울주신경산#1 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 울주-신경산 No.118~120 - 본 선로 구성","2019-12-20 09:00","2019-12-26 18:00","취소","취소","연속"]
[80,"대구","경산","울주신경산#1 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 울주-신경산 No.118~120 - No.119 가철탑 활용 임시선로 구성","2019-12-05 09:00","2019-12-10 18:00","2019-12-19 09:00","2019-12-24 18:00","연속"]
[81,"대구","경산","울주신경산#2 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 울주-신경산 No.118~120 - 본 선로 구성","2019-12-27 09:00","2020-01-04 18:00","취소","취소","연속"]
[82,"대구","경산","울주신경산#2 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 울주-신경산 No.118~120 - No.119 가철탑 활용 임시선로 구성","2019-12-01 09:00","2019-12-04 18:00","2019-12-15 09:00","2019-12-18 18:00","연속"]
[83,"대구","서대구","북경남서대구#1 T/L","2019년 가공송전 순시점검 위탁공사","절연저항 측정 및 불량애자 교체 ","2019-12-02 08:30","2019-12-04 18:00","2019-12-02 08:30","2019-12-04 18:00","연속"]
[84,"대구","서대구","북경남서대구#2 T/L","2019년 가공송전 순시점검 위탁공사","절연저항 측정 및 불량애자 교체 ","2019-12-05 08:30","2019-12-06 18:00","2019-12-05 08:30","2019-12-06 18:00","연속"]
[85,"경북","영주","삼척GP한울NP#2 T/L","YPP계전기 성능개선","YPP계전기 성능개선","2019-12-09 09:00","2019-12-09 18:00","취소","취소","연속"]
[86,"경북","영주","한울1NP한울2NP#2 T/L","YPP계전기 성능개선","YPP계전기 성능개선","2019-12-10 09:00","2019-12-10 18:00","취소","취소","연속"]
[87,"경북","영주","한울2NP한울3NP#4 T/L","YPP계전기 성능개선","YPP계전기 성능개선","2019-12-17 09:00","2019-12-17 18:00","2019-12-17 09:00","2019-12-17 18:00","연속"]
[88,"경북","영주","신태백한울NP#2 T/L","YPP계전기 성능개선","YPP계전기 성능개선","2019-12-19 09:00","2019-12-19 18:00","2019-12-19 09:00","2019-12-19 18:00","연속"]
[89,"경북","영주","신태백한울NP#1 T/L","YPP계전기 성능개선","YPP계전기 성능개선","2019-12-18 09:00","2019-12-18 18:00","2019-12-18 09:00","2019-12-18 18:00","연속"]
[90,"경북","직할","신영일안동CC T/L","'18-19년 경북직할 가공송전 정비회사","345kV 신영일-안동복합CCT/L 항공장애표시구 설치","2019-12-02 07:00","2019-12-02 18:00","2019-12-02 07:00","2019-12-02 18:00","연속"]
[91,"부산울산","동부산","고리N/P S/Y 345kV #1 CLR CB","고리NP S/Y 362kV GIS 차단기 동작시험","고리NP S/Y 362kV 7077GIS 차단기 동작시험(#1CLR)","2019-12-03 09:30","2019-12-03 14:00","2019-12-09 09:30","2019-12-09 14:00","연속"]
[92,"부산울산","동부산","고리N/P S/Y 345kV #2 CLR CB","고리NP S/Y 362kV GIS 가스블럭교체","1.고리NP S/Y 362kV GIS 가스블럭교체(#2CLR) 2.고리NP S/Y 7577GIS 차단기 동작시험","2019-12-02 09:30","2019-12-02 18:00","2019-12-10 09:30","2019-12-10 18:00","연속"]
[93,"부산울산","동부산","신양산북부산#2 T/L","345kV 신양산-북부산 등 2개T/L 안전이격 확보공사","피뢰기 설치 : 42호(1기, 3set)","2019-12-06 09:00","2019-12-06 18:00","취소","취소","연속"]
[94,"부산울산","동부산","신양산북부산#1 T/L","345kV 신양산-북부산 등 2개T/L 안전이격 확보공사","피뢰기 설치 : 42호(1기, 3set)","2019-12-05 09:00","2019-12-05 18:00","취소","취소","연속"]
[95,"부산울산","동부산","신양산고리NP#1 T/L","고리NP S/Y 362kV GIS 구조개선관련 시험가압","고리NP S/Y 362kV 7972,7900GIS 구조개선관련 시험가압(신양산-고리#1T/L)","2019-12-13 14:00","2019-12-14 14:00","2019-12-13 14:00","2019-12-14 14:00","연속"]
[96,"부산울산","북부산","북부산S/S 신양산-북부산#2T/L CB(7771)","2019년 북부산 변전협력회사 총액공사","북부산E/C 345kV 신양산-북부산#2T/L 7771단독차단기GIS 보통점검","2019-12-03 09:00","2019-12-03 18:00","2019-12-03 09:00","2019-12-03 18:00","연속"]
[97,"부산울산","울산","신울산S/S 신울산-고리NP#1T/L CB(7572)","18~19년 변전협력 총액공사","- 신울산E/C 345kV 신울산-고리NP#1T/L 차단기 보통점검","2019-12-04 09:00","2019-12-04 18:00","2019-12-04 09:00","2019-12-04 18:00","연속"]
[98,"부산울산","울산","신울산S/S #2 M.Tr","18~19년 변전협력 총액공사","- 신울산E/C 345kV #2M.Tr 누유보수 및 6264 차단기 동작시험","2019-12-03 09:00","2019-12-04 18:00","2019-12-03 09:00","2019-12-04 18:00","연속"]
[99,"부산울산","울산","울산C/C #1 Tie-Tr","18~19년 변전협력 총액공사","- 울산복합 345kV #1M.Tr A상 1,2차 부싱 절연유 채유","2019-12-01 09:00","2019-12-01 18:00","2019-12-01 09:00","2019-12-01 18:00","연속"]
[100,"부산울산","울산","울산C/C #3 Tie-Tr","18~19년 변전협력 총액공사","- 울산복합 345kV #3M.Tr A상 1,2차 부싱 절연유 채유","2019-12-08 09:00","2019-12-08 18:00","2019-12-08 09:00","2019-12-08 18:00","연속"]
[101,"부산울산","울산","울산C/C 신온산-울산TPT/L CB(7671)","18~19년 변전협력 총액공사","- 울산복합 345kV 신온산-울산TPT/L 7671차단기 보통점검","2019-12-05 09:00","2019-12-05 18:00","2019-12-05 09:00","2019-12-05 18:00","연속"]
[102,"부산울산","울산","울산C/C #2 Tie-Tr","18~19년 변전협력 총액공사","- 울산복합 345kV #2M.Tr A상 1,2차 부싱 절연유 채유","2019-12-07 09:00","2019-12-07 18:00","2019-12-07 09:00","2019-12-07 18:00","연속"]
[103,"부산울산","울산","울주S/S #4 M.Tr","18~19년 변전협력 총액공사","- 울주E/C 345kV #4M.Tr 보호배전반 교체 - 3차PT 보통점검","2019-12-02 09:00","2019-12-06 18:00","2019-12-02 09:00","2019-12-06 18:00","연속"]
[104,"경남","직할","신마산신김해#2 T/L","송전선로 OPGW 항공장애표시구 설치 공사","154KV 신마산-신김해#2T/L 3-4, 28-29호 항공장애표시구 설치","2019-12-06 13:00","2019-12-06 18:00","2019-12-06 13:00","2019-12-06 18:00","연속"]
[105,"경남","직할","신김해S/S #2 M.Tr","신김해S/S #2M.Tr 3차 PT 보통점검, 3차 CB 조작시험","신김해S/S #2M.Tr 3차 PT 보통점검, 3차 CB 조작시험","2019-12-04 09:30","2019-12-04 17:30","2019-12-04 09:30","2019-12-04 17:30","연속"]
[106,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산T/L 78호 지장송전선로 이설공사","345kV 신김해-북부산T/L 77~81호 간 지장이설공사[본탑 1기, 계탑 1기]","2019-12-06 07:00","2019-12-16 18:00","2019-12-06 07:00","2019-12-16 18:00","연속"]
[107,"경남","직할","신마산신김해#1 T/L","송전선로 OPGW 항공장애표시구 설치 공사","154KV 신마산-신김해#1T/L 3-4, 28-29호 항공장애표시구 설치","2019-12-06 07:00","2019-12-06 12:00","2019-12-06 07:00","2019-12-06 12:00","연속"]
[108,"경남","직할","신김해S/S #4 M.Tr","신김해S/S #4M.Tr 3차 PT 보통점검","신김해S/S #4M.Tr 3차 PT 보통점검","2019-12-05 09:30","2019-12-05 17:30","2019-12-05 09:30","2019-12-05 17:30","연속"]
[109,"경남","진주","의령산청양수#1 T/L","의령S/S 74Bay B/F PNL 대체 공사","의령S/S 74Bay B/F PNL 대체 공사","2019-12-09 09:00","2019-12-13 18:00","2019-12-09 09:00","2019-12-13 18:00","연속"]
[110,"경남","함안","신마산S/S #1 M.Tr","신마산S/S 345kV #1 M.Tr 방호벽 사다리 철거 관련 안전이격","신마산S/S 345kV #1 M.Tr 방호벽 사다리 철거 관련 안전이격","2019-12-02 09:00","2019-12-02 13:30","2019-12-02 09:00","2019-12-02 13:30","연속"]
[111,"경남","함안","신마산S/S #2 M.Tr","신마산S/S 345kV #2 M.Tr 방호벽 사다리 철거 관련 안전이격","신마산S/S 345kV #2 M.Tr 방호벽 사다리 철거 관련 안전이격","2019-12-02 13:30","2019-12-02 18:00","2019-12-02 13:30","2019-12-02 18:00","연속"]
[112,"경남","함안","신마산S/S #5 M.Tr","신마산S/S 345kV #5 M.Tr 방호벽 사다리 철거 관련 안전이격","신마산S/S 345kV #5 M.Tr 방호벽 사다리 철거 관련 안전이격","2019-12-03 09:30","2019-12-03 13:30","2019-12-03 09:30","2019-12-03 13:30","연속"]
[113,"남서울","동서울","동서울S/S #3 M.Tr","서울동남권지역 전기공급시설 전력구 공사, 동서울-강남5차","○ 전력구 흙막이 작업(H-Beam Filing)","2019-12-04 08:30","2019-12-04 17:30","2019-12-08 08:30","2019-12-08 17:30","연속"]
[114,"경북",null,"한울4호기 대기보조변압기1 CB(7700,7772)","4호기 14차 계획예방정비 \n* 조작차단기 : CB 7700, 7772","○ 대기보조변압기 02M 일반점검","2019-12-10 14:00","2019-12-30 14:00","2019-12-10 14:00","2019-12-30 14:00","연속"]
[115,"경북",null,"한울4호기 대기보조변압기2 CB(7800,7872)","4호기 14차 계획예방정비 \n* 조작차단기 : CB 7800, 7872","○ 대기보조변압기 02N 일반점검","2019-12-10 14:00","2019-12-30 14:00","2019-12-10 14:00","2019-12-30 14:00","연속"]
[116,"경북",null,"한울4호기 주변압기 CB(7A00,7A72)","4호기 14차 계획예방정비 \n* 조작차단기 : CB 7A00, 7A72","○ 주변압기,소내보조변압기 일반점검","2019-12-31 14:00","2020-01-31 14:00","2019-12-31 14:00","2020-01-31 14:00","연속"]
[117,"대구",null,"신월성1호기 주변압기 CB(7400,7472)","신월성 1호기 5차 계획예방정비\n#1 소내전원절체시험 \n* 조작차단기 : CB 7400, 7472","○ 소내전원절체시험시 주변압기 \n   모의 보호신호에 의한 PCB개방","2019-12-11 09:00","2019-12-12 18:00","2019-12-11 09:00","2019-12-12 18:00","연속"]
[118,"경북",null,"한울2호기 주변압기CB(7200,7272)","2호기 22차 계획예방정비\n* 조작차단기 : CB 7200, 7272","○ 비상보조변압기 일반점검","2019-12-03 13:00","2019-12-12 14:00","2019-12-03 13:00","2019-12-12 14:00","연속"]
[119,"경북",null,"예천양수2호기 주변압기 CB(7200)","SFC 차단기 설치","SFC 차단기 설치","2019-12-02 08:00","2019-12-13 20:00","2019-12-02 08:00","2019-12-13 20:00","연속"]

{"sheet":"154송부","index":3,"n_rows":217,"n_cols":13,"rows_kept":217,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2019년도 \"&종합!R15&\"월 휴전계획서\"","v":"2019년도 12월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","마장용두 T/L","마장 변전소 디지털화 공사","마장 변전소 노후 23kV GIS 교체 공사 대비 SA혼용운영시스템 설치 및 제어케이블 이설 공사","2019-12-02 09:00","2019-12-02 18:00","2019-12-02 09:00","2019-12-02 18:00","연속"]
[2,"남서울","강남","신양재신사#3 T/L","신양재S/S 신양재-신사#3T/L GIS 전자변 교체","신양재S/S 신양재-신사#3T/L GIS 전자변 교체","2019-12-10 09:00","2019-12-10 18:00","2019-12-10 09:00","2019-12-10 18:00","연속"]
[3,"남서울","강남","신양재사당#1 T/L","154kV 신양재-사당T/L 자기애관 교체공사","자기애과 교체 × 6상","2019-12-02 09:00","2019-12-06 18:00","2019-12-02 09:00","2019-12-06 18:00","연속"]
[4,"남서울","강남","신양재사당#2 T/L","154kV 신양재-사당T/L 자기애관 교체공사","자기애과 교체 × 6상","2019-12-09 09:00","2019-12-13 18:00","2019-12-09 09:00","2019-12-13 18:00","연속"]
[5,"남서울","영등포","목동S/S 154kV #65 BUS","154kV당인리-목동T/L 선종교체공사","0 휴전내용 : 154kV당인리-목동#2T/L 무부하 가압 관련으로 상시험차.","2019-12-26 10:00","2019-12-26 11:00","2019-12-26 10:00","2019-12-26 11:00","연속"]
[6,"남서울","동서울","동서울송파#2 T/L","서울동남권지역 전기공급시설 전력구 공사, 동서울-강남5차","○ 전력구 흙막이 작업(H-Beam Filing)","2019-12-02 08:30","2019-12-02 17:30","2019-12-02 08:30","2019-12-02 17:30","연속"]
[7,"남서울","동서울","동서울송파#1 T/L","서울동남권지역 전기공급시설 전력구 공사, 동서울-강남5차","○ 전력구 흙막이 작업(H-Beam Filing)","2019-12-03 08:30","2019-12-03 17:30","2019-12-03 08:30","2019-12-03 17:30","연속"]
[8,"남서울","동서울","동서울S/S 345kV #3 M.Tr CB","서울동남권지역 전기공급시설 전력구 공사, 동서울-강남5차","○ 전력구 흙막이 작업(H-Beam Filing)","2019-12-04 08:30","2019-12-04 17:30","취소","취소","연속"]
[9,"남서울","동서울","동서울강동#2 T/L","서울동남권지역 전기공급시설 전력구 공사, 동서울-강남5차","○ 전력구 흙막이 작업(H-Beam Filing)","2019-12-05 08:30","2019-12-05 17:30","2019-12-05 08:30","2019-12-05 17:30","연속"]
[10,"인천","김포","신김포장기#1 T/L","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사(무부하가압) - 170kV GIS 4CCT","2019-12-12 09:00","2019-12-13 18:00","취소","취소","연속"]
[11,"인천","김포","신김포장기#1 T/L","신김포S/S #63D.Tr 증설공사","- #63D.Tr 최초 무부하가압용","2019-12-16 09:00","2019-12-17 18:00","취소","취소","연속"]
[12,"인천","김포","신김포S/S 154kV #65 BUS","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사 - 170kV GIS 4CCT","2019-12-09 09:00","2019-12-13 18:00","취소","취소","연속"]
[13,"인천","김포","신김포S/S 154kV #60 BUS","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사 - 170kV GIS 4CCT","2019-12-02 09:00","2019-12-06 18:00","취소","취소","연속"]
[14,"인천","김포","신김포장기#1 T/L","345kV 신김포S/S #63D.Tr 증설공사","345kV 신김포S/S #63D.Tr 증설공사(무부하가압) - 170kV GIS 4CCT","2019-12-05 09:00","2019-12-06 18:00","취소","취소","연속"]
[15,"인천","김포","양촌양곡#2 T/L","154kV 양촌-양곡#2T/L 피뢰기 열화진단","○ 피뢰기 열화진단 - 내 용 : 도블테스트, 절연저항, 누설전류, 금구류 오결합 여부","2019-12-05 09:00","2019-12-06 18:00","취소","취소","연속"]
[16,"인천","김포","양촌양곡#1 T/L","154kV 양촌-양곡#1T/L 피뢰기 열화진단","○ 피뢰기 열화진단 - 내 용 : 도블테스트, 절연저항, 누설전류, 금구류 오결합 여부","2019-12-03 09:00","2019-12-04 18:00","취소","취소","연속"]
[17,"인천","부평","관교만수 T/L","154kV 관교-만수T/L 선로정수 측정","지중송전선로 병행지선 설치보강(18년 旣완료) 후 선로정수 변동분 반영으로 계전기 오동작 방지(계통시험파트 측정시행)","2019-12-02 09:00","2019-12-02 13:00","2019-12-02 09:00","2019-12-02 13:00","연속"]
[18,"인천","부평","신현포스코CC#2 T/L","신현S/S 신현포스코CC#2T/L GIS 초기점검","신현S/S 신현포스코CC#2T/L GIS 초기점검","2019-12-04 09:00","2019-12-04 18:00","2019-12-04 09:00","2019-12-04 18:00","연속"]
[19,"인천","부평","원창포스코CC#2 T/L","원창S/S 원창포스코CC#2T/L GIS 보통점검 및 보조계전기 교체공사","원창S/S 원창포스코CC#2T/L GIS 보통점검 및 보조계전기 교체","2019-12-03 09:00","2019-12-03 18:00","2019-12-03 09:00","2019-12-03 18:00","연속"]
[20,"인천","부평","원창포스코CC#1 T/L","원창S/S 원창포스코CC#1T/L GIS 보통점검 및 보조계전기 교체공사","원창S/S 원창포스코CC#1T/L GIS 보통점검 및 보조계전기 교체","2019-12-02 09:00","2019-12-02 18:00","2019-12-02 09:00","2019-12-02 18:00","연속"]
[21,"인천","부평","인천CC포스코CC#1 T/L","인천화력S/Y 인천CC포스코CC#1T/L GIS 조작시험","인천화력S/Y 인천CC포스코CC#1T/L GIS 조작시험","2019-12-05 09:00","2019-12-05 13:00","2019-12-05 09:00","2019-12-05 13:00","연속"]
[22,"인천","부평","인천CC포스코CC#2 T/L","인천화력S/Y 인천CC포스코CC#2T/L GIS 조작시험","인천화력S/Y 인천CC포스코CC#2T/L GIS 조작시험","2019-12-05 13:00","2019-12-05 18:00","2019-12-05 13:00","2019-12-05 18:00","연속"]
[23,"인천","직할","임학계양#1 T/L","임학계양#1T/L 광케이블 시설공사","임학-계양S/S 광케이블 시설(OPGW 7,097km, OFC 1.764km)","2019-12-09 09:00","2019-12-13 18:00","2019-12-09 09:00","2019-12-13 18:00","연속"]
[24,"인천","직할","계양원창 T/L","임학계양#1T/L 광케이블 시설공사","임학-계양S/S 광케이블 시설(OPGW 7,097km, OFC 1.764km)","2019-12-09 09:00","2019-12-13 18:00","2019-12-09 09:00","2019-12-13 18:00","연속"]
[25,"인천","직할","경서북인천#1 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","북인천S/S #1M.Tr 1차 GIS 정밀점검 관련 무부하가압용","2019-12-11 13:00","2019-12-11 18:00","2019-12-11 13:00","2019-12-11 18:00","연속"]
[26,"인천","직할","경서북인천#1 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","북인천S/S 6100 BUS TIE GIS 정밀점검 관련 무부하가압용","2019-12-04 13:00","2019-12-04 18:00","2019-12-04 13:00","2019-12-04 18:00","연속"]
[27,"인천","직할","경서북인천#2 T/L","2019년 부평전력지사 170㎸ GIS 정밀점검 공사","북인천S/S #2M.Tr 1차 GIS 정밀점검 관련 무부하가압용","2019-12-18 13:00","2019-12-18 18:00","2019-12-18 13:00","2019-12-18 18:00","연속"]
[28,"경기북부","고양","신덕은S/S 154kV #60-#65 BUS TIE CB","2019년 고양P/O 변전정비회사 총액공사","신덕은S/S 154kV #60-#65 BUS PRO PNL 교체공사","2019-12-03 09:00","2019-12-05 18:00","2019-12-03 09:00","2019-12-05 18:00","연속"]
[29,"경기북부","고양","월롱S/S 154kV 문산-월롱#2T/L GIS","2019 고양P/O 변전정비회사 총액공사(문산-월롱#2T/L GIS)","월롱S/S 문산-월롱#2 T/L GIS 보통점검","2019-12-04 10:00","2019-12-04 18:00","2019-12-04 10:00","2019-12-04 18:00","연속"]
[30,"경기북부","고양","월롱S/S 154kV 문산-월롱#1T/L GIS","2019 고양P/O 변전정비회사 총액공사(문산-월롱#1T/L GIS)","월롱S/S 문산-월롱#1 T/L GIS 보통점검","2019-12-03 10:00","2019-12-03 18:00","2019-12-03 10:00","2019-12-03 18:00","연속"]
[31,"경기북부","구리","팔당H/P 154kV #1 M.Tr 1차 CB","'18~19년도 구리전력 변전협력 총액공사","팔당H/P 154kV #1M.Tr 1차 GIS 보통점검공사","2019-12-05 09:00","2019-12-05 18:00","2019-12-05 09:00","2019-12-05 18:00","연속"]
[32,"경기북부","직할","신의정부S/S 154kV #67 BUS","신의정부S/S 하자보수(DS조작로드 교체공사)","DS부 조작로드 발청에 의한 교체공사","2019-12-02 09:00","2019-12-05 18:00","2019-12-02 09:00","2019-12-05 18:00","연속"]
[33,"경기북부","직할","신의정부S/S 154kV #67 BUS","신의정부S/S 하자보수(DS조작로드 교체공사)","DS부 조작로드 발청에 의한 교체공사","2019-12-09 09:00","2019-12-13 18:00","2019-12-09 09:00","2019-12-13 18:00","연속"]
[34,"경기북부","직할","양주녹양#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주녹양#2 T/L 인출측 전력구공사","2019-12-18 09:00","2019-12-19 18:00","2019-12-18 09:00","2019-12-19 18:00","연속"]
[35,"경기북부","직할","양주녹양#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주녹양#1 T/L 인출측 전력구공사","2019-12-16 09:00","2019-12-17 18:00","2019-12-16 09:00","2019-12-17 18:00","연속"]
[36,"경기북부","직할","양주쌍문#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주쌍문#1T/L 인출측 전력구공사","2019-12-08 09:00","2019-12-08 18:00","2019-12-08 09:00","2019-12-08 18:00","연속"]
[37,"경기북부","직할","양주쌍문#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주쌍문#2T/L 인출측 전력구공사","2019-12-07 09:00","2019-12-07 18:00","2019-12-07 09:00","2019-12-07 18:00","연속"]
[38,"경기북부","직할","양주지축#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주지축#1T/L 인출측 전력구공사","2019-12-04 09:00","2019-12-05 18:00","2019-12-04 09:00","2019-12-05 18:00","연속"]
[39,"경기북부","직할","양주지축#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주지축#2 T/L인출측 전력구공사","2019-12-02 09:00","2019-12-03 18:00","2019-12-02 09:00","2019-12-03 18:00","연속"]
[40,"경기북부","직할","양주금촌#2 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주금촌#2 T/L 인출측 전력구공사","2019-12-02 09:00","2019-12-02 18:00","2019-12-02 09:00","2019-12-02 18:00","연속"]
[41,"경기북부","직할","양주금촌#1 T/L","양주S/S 옥외철구 GIS화 전력구공사","양주금촌#1 T/L 인출측 전력구공사","2019-12-03 09:00","2019-12-03 18:00","2019-12-03 09:00","2019-12-03 18:00","연속"]
[42,"경기","동부","이천S/S 154kV 이천-율현#2T/L GIS","19년 동부변전협력회사 총액공사","이천:이천-율현#2 LA대체","2019-12-06 09:30","2019-12-06 18:00","2019-12-06 09:30","2019-12-06 18:00","연속"]
[43,"경기","동부","이천S/S 154kV 이천-율현#1T/L GIS","19년 동부변전협력회사 총액공사","이천:이천-율현#1 LA대체","2019-12-05 09:30","2019-12-05 18:00","2019-12-05 09:30","2019-12-05 18:00","연속"]
[44,"경기","성남","모현용인#1 T/L","154kV 모현-용인#1T/L 항공장애표시구 설치공사","0 항공장애표시구 설치 : 3-4호 등 14개소 39개","2019-12-02 07:00","2019-12-06 12:00","2019-12-02 07:00","2019-12-06 12:00","연속"]
[45,"경기","성남","오포모현#1 T/L","154kV 오포-모현#1T/L 항공장애표시구 설치공사","0 항공장애표시구 설치 : 5-6호 등 3개소","2019-12-06 12:00","2019-12-07 18:00","2019-12-06 12:00","2019-12-07 18:00","연속"]
[46,"경기","성남","서안성남사#1 T/L","154kV 서안성-남사T/L 피뢰기 설치 및 전선접속개소 교체공사","- 154kV 서안성-남사T/L 피뢰기 설치 및 전선교체공사 (No.1-20, 60 SET 및 No.10-11 전선교체공사)","2019-12-01 07:00","2019-12-02 18:00","2019-12-01 07:00","2019-12-02 18:00","연속"]
[47,"경기","성남","서안성남사#2 T/L","154kV 서안성-남사T/L 전선접속개소 교체공사","- 154kV 서안성-남사T/L 전선교체공사 (No.10-11 전선교체공사)","2019-12-03 07:00","2019-12-03 18:00","2019-12-03 07:00","2019-12-03 18:00","연속"]
[48,"경기","성남","서안성안성#2 T/L","(안전이격휴전) 154kV 서안성-남사T/L 피뢰기 설치공사","- (안전이격휴전) 154kV 서안성-남사T/L 피뢰기 설치 시 154kV 서안성-남사 No.1 병가","2019-12-01 07:00","2019-12-01 09:00","2019-12-01 07:00","2019-12-01 09:00","연속"]
[49,"경기","성남","신갈S/S 154kV #60-#65 BUS TIE GIS","170kV GIS 대체","170kV GIS 대체","2019-12-02 09:00","2019-12-18 18:00","2019-12-02 09:00","2019-12-18 18:00","연속"]
[50,"경기","성남","신갈수원열병합T/L","GIS 조작시험","GIS 조작시험","2019-12-05 09:00","2019-12-05 18:00","2019-12-05 09:00","2019-12-05 18:00","연속"]
[51,"경기","성남","신용인S/S 154kV #61-#62 SEC GIS","GIS 조작시험","GIS 조작시험","2019-12-03 09:00","2019-12-03 18:00","2019-12-03 09:00","2019-12-03 18:00","연속"]
[52,"경기","직할","봉담남수원#1 T/L","19년 직할 변전협력회사 총액공사","남수원S/S 6100,봉담-남수원#1T/L GIS 초기점검","2019-12-04 14:00","2019-12-04 18:00","취소","취소","연속"]
[53,"경기","직할","남수원발안#1 T/L","19년 직할 GIS 정밀점검공사","발안S/S 남수원-발안#1T/L GIS 정밀점검공사","2019-12-02 09:00","2019-12-04 18:00","취소","취소","연속"]
[54,"경기","직할","남수원발안#2 T/L","19년 직할 GIS 정밀점검공사","발안S/S 남수원-발안#2T/L GIS 정밀점검공사","2019-12-05 09:00","2019-12-07 18:00","취소","취소","연속"]
[55,"경기","직할","율전의왕#1 T/L","19년 직할 변전협력회사 총액공사","율전S/S 율전-의왕#1T/L GIS 조작시험","2019-12-05 09:00","2019-12-05 18:00","2019-12-05 09:00","2019-12-05 18:00","연속"]
[56,"경기","평택","고덕진위#2 T/L","고덕S/S 154kV SW 증설공사 (고덕-동평택#1,2T/L)","ㅇ 고덕S/S 154kV SW #60BUS측 기기설치 - 고덕-동평택#1,2 T/L ㅇ 154kV #60BUS측 무부하 가압","2019-12-05 18:00","2019-12-06 18:00","2019-12-05 18:00","2019-12-06 18:00","연속"]
[57,"경기","평택","포승청북 T/L","345kV 신온양서서울외 2개T/L 지장철탑이설공사(임시선로구성)","임시선로 구성 No.43 임시선로 구성","2019-12-09 08:00","2019-12-11 18:00","취소","취소","연속"]
[58,"경기","평택","만호청북#1 T/L","345kV 신온양서서울외 2개T/L 지장철탑이설공사(임시선로구성)","임시선로 구성 No.43 임시선로 구성","2019-12-05 08:00","2019-12-08 18:00","취소","취소","연속"]
[59,"경기","직할","발안구문천#2T/L","19년 직할 변전협력회사 총액공사","발안S/S 발안-구문천#2T/L 43LR 경보수용","2019-12-02 10:00","2019-12-02 18:00","취소","취소","연속"]
[60,"경기","직할","관양동안양#2T/L","19년 직할 변전협력회사 총액공사","GIS 조작시험","2019-12-06 09:00","2019-12-06 14:00","2019-12-06 09:00","2019-12-06 14:00","연속"]
[61,"경기","성남","서안성S/S #61-62 SEC CB","GIS 제작사 하자처리","GIS 제작사 하자처리","2019-12-03 09:00","2019-12-03 18:00","2019-12-03 09:00","2019-12-03 18:00","연속"]
[62,"경기","동부","곤지암이천#1T/L","154kV 곤지암-율현#1T/L 불량애자 교체","154kV 곤지암-율현#1T/L 불량애자 교체(안전이격)","2019-12-08 08:00","2019-12-08 18:00","취소","취소","연속"]
[63,"경기","동부","곤지암이천#2T/L","154kV 곤지암-율현#2T/L 불량애자 교체","154kV 곤지암-율현#2T/L 불량애자 교체(안전이격)","2019-12-07 08:00","2019-12-07 18:00","취소","취소","연속"]
[64,"경기","동부","곤지암율현#1T/L","154kV 곤지암-율현#1T/L 불량애자 교체","154kV 곤지암-율현#1T/L 불량애자 교체","2019-12-08 08:00","2019-12-08 18:00","취소","취소","연속"]
[65,"경기","동부","곤지암율현#2T/L","154kV 곤지암-율현#2T/L 불량애자 교체","154kV 곤지암-율현#2T/L 불량애자 교체","2019-12-07 08:00","2019-12-07 18:00","취소","취소","연속"]
[66,"강원","동해","삼척동해TP T/L","154kV 동해화력T/L 자기애관 교체공사","기중종단접속(EBA) 자기애관을 폴리머애관으로 교체(6기)","2019-12-09 09:00","2019-12-10 18:00","2019-12-03 09:00","2019-12-04 18:00","연속"]
[67,"강원","동해","이원동해TP T/L","154kV 동해화력T/L 자기애관 교체공사","기중종단접속(EBA) 자기애관을 폴리머애관으로 교체(6기)","2019-12-16 09:00","2019-12-17 18:00","2019-12-05 09:00","2019-12-06 18:00","연속"]
[68,"강원","직할","양구화천HP#1 T/L","2018-2019 강원본부 직할 변전정비 총액공사 기기점검","154kV 양구-화천H/P T/L 피뢰기 보통점검 - 양구S/S 및 화천H/P 양단 작업","2019-12-03 09:00","2019-12-03 18:00","2019-12-03 09:00","2019-12-03 18:00","연속"]
[69,"강원","직할","양구화천HP#2 T/L","2018-2019 강원본부 직할 변전정비 총액공사 기기점검","154kV 양구-화천H/P #1, #2 T/L 피뢰기 보통점검 - 양구S/S 및 화천H/P 양단 작업","2019-12-04 09:00","2019-12-04 18:00","2019-12-04 09:00","2019-12-04 18:00","연속"]
[70,"강원","직할","춘천H/P 154kV #2 M.Tr 2차 CB","2018-2019 변전정비 총액공사 기기점검","#1M.Tr 및 #2M.Tr DS 보통점검 (모선휴전 동반 필요)","2019-12-10 10:00","2019-12-10 12:00","2019-12-10 10:00","2019-12-10 12:00","연속"]
[71,"강원","직할","가평춘천HP T/L","2018-2019 변전정비 총액공사 기기점검","#1M.Tr 및 #2M.Tr DS 보통점검 (모선휴전 동반 필요)","2019-12-10 10:00","2019-12-10 12:00","2019-12-10 10:00","2019-12-10 12:00","연속"]
[72,"강원","직할","북춘천춘천HP T/L","2018-2019 변전정비 총액공사 기기점검","#1M.Tr 및 #2M.Tr DS 보통점검 (모선휴전 동반 필요)","2019-12-10 10:00","2019-12-10 12:00","2019-12-10 10:00","2019-12-10 12:00","연속"]
[73,"강원","직할","춘천H/P 154kV #1 M.Tr 2차 CB","2018-2019 변전정비 총액공사 기기점검","#1M.Tr 및 #2M.Tr DS 보통점검 (모선휴전 동반 필요)","2019-12-10 10:00","2019-12-10 12:00","2019-12-10 10:00","2019-12-10 12:00","연속"]
[74,"강원","직할","춘천H/P 154kV #60 BUS","2018-2019 변전정비 총액공사 기기점검","#1M.Tr 및 #2M.Tr DS 보통점검 (모선휴전 동반 필요)","2019-12-10 10:00","2019-12-10 12:00","2019-12-10 10:00","2019-12-10 12:00","연속"]
[75,"강원","직할","화천화천HP#2 T/L","18~19 강원본부 직할 변전정비 총액공사","○ 154kV 화천-화천H/P #2T/L A,B,C LA, PT 보통점검","2019-12-05 14:00","2019-12-05 18:00","2019-12-05 14:00","2019-12-05 18:00","연속"]
[76,"강원","직할","화천화천HP#1 T/L","18~19 강원본부 직할 변전정비 총액공사","○ 154kV 화천-화천H/P T/L A,B,C LA, PT 보통점검","2019-12-05 10:00","2019-12-05 14:00","2019-12-05 10:00","2019-12-05 14:00","연속"]
[77,"강원","직할","화천H/P 154kV #60 BUS","2018-2019 강원본부 직할 변전정비 총액공사 기기점검","&lt노후 기타설비 대체공사> 화천H/P 154kV #1 및 #2BUS PT A, B, C","2019-12-17 09:00","2019-12-17 18:00","2019-12-17 09:00","2019-12-17 18:00","연속"]
[78,"강원","직할","북춘천화천HP T/L","2018-2019 강원본부 직할 변전정비 총액공사 기기점검","154kV 보통점검 - GCB 초기점검, DS L, LA A, B, C, PT C 보통점검","2019-12-16 09:00","2019-12-18 18:00","2019-12-16 09:00","2019-12-18 18:00","연속"]
[79,"강원","직할","화천H/P 154kV #65 BUS","2018-2019 강원본부 직할 변전정비 총액공사 기기점검","ㅇ노후 기타설비 대체공사 화천H/P 154kV #1 및 #2BUS PT A, B, C","2019-12-18 09:00","2019-12-18 18:00","2019-12-18 09:00","2019-12-18 18:00","연속"]
[80,"강원","태백","제천영월#2 T/L","'19년 태백전력지사 변전전문회사 총액공사","영월변전소 제천-영월#2T/L GIS 러버히터 설치 공사","2019-12-02 10:00","2019-12-02 14:00","2019-12-02 10:00","2019-12-02 14:00","연속"]
[81,"강원","태백","영월_영월CC T/L","'19년 태백전력지사 변전전문회사 총액공사","영월변전소 영월-영월CC T/L GIS 러버히터 설치 공사","2019-12-02 14:00","2019-12-02 18:00","2019-12-02 14:00","2019-12-02 18:00","연속"]
[82,"충북","직할","신진천오창#2 T/L","154kV 신진천-진천T/L OPGW 증설공사","154kV 신진천-진천T/L 가공지선 철거 및 OPGW 10km 시설","2019-12-07 09:00","2019-12-08 18:00","취소","취소","매일"]
[83,"충북","직할","신진천진천#1 T/L","154kV 신진천-진천T/L OPGW 증설공사","154kV 신진천-진천T/L 가공지선 철거 및 OPGW 10km 시설","2019-12-08 09:00","2019-12-08 18:00","취소","취소","연속"]
[84,"충북","직할","신진천진천#2 T/L","154kV 신진천-진천T/L OPGW 증설공사","154kV 신진천-진천T/L 가공지선 철거 및 OPGW 10km 시설","2019-12-07 09:00","2019-12-07 18:00","취소","취소","연속"]
[85,"충북","직할","신진천S/S 154kV #62 BUS","신진천S/S 154kV #8Sh.C GIS 정밀점검 무부하가압","신진천S/S 154kV #8Sh.C GIS 정밀점검 무부하가압","2019-12-04 10:00","2019-12-04 12:00","2019-12-07 10:00","2019-12-07 12:00","연속"]
[86,"충북","직할","신진천S/S 154kV #66-#67 SEC GIS","신진천S/S 154kV #66-67 SEC GIS 보통점검","신진천S/S 154kV #66-67 SEC GIS 보통점검","2019-12-03 10:00","2019-12-03 18:00","2019-12-01 13:00","2019-12-01 18:00","연속"]
[87,"충북","직할","신진천S/S 154kV #61-#62 SEC GIS","신진천S/S 154kV #61-62 SEC GIS 보통점검","신진천S/S 154kV #61-62 SEC GIS 보통점검","2019-12-02 10:00","2019-12-02 18:00","2019-12-01 08:00","2019-12-01 13:00","연속"]
[88,"충북","직할","진천덕산#1 T/L","2018~19년 직할 송전정비회사 총액공사","No.26 불량애자교체","2019-12-03 13:00","2019-12-03 18:00","2019-12-03 13:00","2019-12-03 18:00","연속"]
[89,"충북","청주","남청주오송#1 T/L","18-19년 송전정비 협력회사 총액공사(청주전력)","154kV 남청주-오송#1T/L 가공지선 교체 : No.4~5","2019-12-08 07:00","2019-12-08 18:00","2019-12-08 07:00","2019-12-08 18:00","연속"]
[90,"충북","청주","부강월산#1 T/L","18-19년 청주전력지사 변전협력회사 총액공사","GIS LCP내 k102Ry 불량 교체","2019-12-02 10:00","2019-12-02 14:00","2019-12-02 10:00","2019-12-02 14:00","연속"]
[91,"충북","청주","오송북청주#2 T/L","154kV 오송-북청주T/L 정밀점검","154kV 오송-북청주T/L No.20~47 정밀점검(32~46 병가)","2019-12-07 09:00","2019-12-07 18:00","2019-12-07 09:00","2019-12-07 18:00","연속"]
[92,"충북","청주","신옥천추부#1 T/L","신옥천S/S 154kV GIS화 공사","옥외철구 BEAM 보강 관련 안전이격 확보(GIS측 작업없음)","2019-12-05 09:00","2019-12-05 14:00","2019-12-05 09:00","2019-12-05 14:00","연속"]
[93,"충북","청주","신옥천추부#2 T/L","신옥천S/S 154kV GIS화 공사","옥외철구 BEAM 보강 관련 안전이격 확보(GIS측 작업없음)","2019-12-05 14:00","2019-12-06 17:00","2019-12-05 14:00","2019-12-06 17:00","연속"]
[94,"충북","청주","옥천영동 T/L","18-19년 청주전력 변전협력회사 총액공사","영동S/S 옥천영동T/L 154kV GIS 조작시험","2019-12-02 10:00","2019-12-02 14:00","2019-12-02 10:00","2019-12-02 14:00","연속"]
[95,"충북","충주","음성금왕#1 T/L","2018~19년 충주전력지사 송전정비회사 총액공사","불량애자교체(No.2,50 )","2019-12-04 08:00","2019-12-05 18:00","취소","취소","매일"]
[96,"충북","충주","금왕남음성#2 T/L","2018~19년 충주전력지사 송전정비회사 총액공사","154kV 음성-금왕#1T/L 안전이격확보","2019-12-05 08:00","2019-12-05 18:00","취소","취소","매일"]
[97,"충북","충주","금왕남음성#1 T/L","2018~19년 충주전력지사 송전정비회사 총액공사","154kV 음성-금왕#2T/L 안전이격확보","2019-12-07 08:00","2019-12-07 18:00","취소","취소","매일"]
[98,"충북","충주","신제천S/S 154KV #60-#65 BUS TIE GIS","'18-19년 직할 변전정비 총액공사","154kV GIS 보통점검","2019-12-03 09:00","2019-12-03 14:00","2019-12-03 09:00","2019-12-03 14:00","연속"]
[99,"충북","충주","신제천S/S 154KV #60-#61 SEC GIS","'18-19년 직할 변전정비 총액공사","154kV GIS 보통점검","2019-12-03 14:00","2019-12-03 18:00","2019-12-03 14:00","2019-12-03 18:00","연속"]
[100,"충북","충주","신제천S/S 154KV #61-#62 SEC GIS","'18-19년 직할 변전정비 총액공사","154kV GIS 보통점검","2019-12-04 09:00","2019-12-04 14:00","2019-12-04 09:00","2019-12-04 14:00","연속"]
[101,"충북","충주","신제천S/S 154KV #66-#67 SEC GIS","'18-19년 직할 변전정비 총액공사","154kV GIS 보통점검","2019-12-04 14:00","2019-12-04 18:00","2019-12-04 14:00","2019-12-04 18:00","연속"]
[102,"충북","충주","신제천S/S 154KV #66 BUS","신제천 #3Sh.C GIS 차단부대체 무부하가압","신제천 154kV #3Sh.C GIS 제작사(LS) 차단부 하자대체 건전성확인을 위한 무부하가압.","2019-12-09 10:00","2019-12-09 17:00","2019-12-09 10:00","2019-12-09 17:00","연속"]
[103,"충북","충주","왕암충주 T/L","154kV 왕암-북충주 등 2개T/L 지장철탑이설공사","제천제3산업단지 조성에 지장이 되는 철탑이설 - 철탑이설 : 6기(4회선 4기, 2회선 2기) - 철탑철거 : 13기(4회선 4기, 2회선 5기, CP주 4기) - 전선교체 : 3.818C-km(240), 3.786C-km(410)","2019-12-02 08:00","2019-12-02 18:00","2019-12-09 08:00","2019-12-09 18:00","연속"]
[104,"충북","충주","음성금왕#2 T/L","2018~19년 충주전력지사 송전정비회사 총액공사","불량애자교체(45,50호)","2019-12-06 08:00","2019-12-07 18:00","취소","취소","연속"]
[105,"충북","충주","풍동음성#1 T/L","18-19년 직할 변전정비 총액공사","음성S/S 풍동음성#1T/L GIS 보통점검. 공기조작부 정밀점검.","2019-12-02 09:00","2019-12-02 18:00","2019-12-02 09:00","2019-12-02 18:00","연속"]
[106,"대전충남","대전","팔봉두마#2 T/L","두마S/S 154kV 팔봉두마#2T/L 전자변 교체","두마S/S 154kV 팔봉두마#2T/L 전자변 교체","2019-12-03 09:00","2019-12-03 18:00","2019-12-03 09:00","2019-12-03 18:00","연속"]
[107,"대전충남","대전","팔봉두마#1 T/L","두마S/S 154kV 팔봉두마#1T/L 전자변 교체","두마S/S 154kV 팔봉두마#1T/L 전자변 교체","2019-12-02 09:00","2019-12-02 18:00","2019-12-02 09:00","2019-12-02 18:00","연속"]
[108,"대전충남","대전","신계룡S/S 154kV #1 EM.Tr CB","신계룡S/S 154kV #1EM.Tr 1차 차단기 동작시험 및 병행작업","신계룡S/S 154kV #1EM.Tr 1차 차단기 동작시험 및 병행작업","2019-12-05 09:00","2019-12-05 18:00","2019-12-05 09:00","2019-12-05 18:00","연속"]
[109,"대전충남","서산","신당진당진#1 T/L","당진S/S 154kV측 취약설비 GIS화","154kV 옥외철구형 설비 GIS화 - 옥외설비 철거(GCB, DS, GIDS, LA, CVT 등) - 옥외철구 전력선 교체(CU-&gtAL) 디지털 혼용운영시스템 이설","2019-12-02 08:00","2019-12-06 18:00","2019-12-02 08:00","2019-12-06 18:00","연속"]
[110,"대전충남","서산","당진송악#2 T/L","당진S/S 154kV측 취약설비 GIS화","154kV 옥외철구형 설비 GIS화 - 옥외설비 철거(GCB, DS, GIDS, LA, CVT 등) - 옥외철구 전력선 교체(CU-&gtAL) 디지털 혼용운영시스템 이설","2019-12-02 08:00","2019-12-06 18:00","2019-12-02 08:00","2019-12-06 18:00","연속"]
[111,"대전충남","아산","한샘둔포#1 T/L","둔포S/S 154kV 한샘-둔포#1T/L GIS 전자변 교체","둔포S/S 154kV 한샘-둔포#1T/L GIS 전자변 교체","2019-12-04 09:00","2019-12-04 18:00","2019-12-04 09:00","2019-12-04 18:00","연속"]
[112,"대전충남","아산","신탕정탕정#2 T/L","신탕정,탕정S/S 154kV 신탕정-탕정#2T/L GIS 보통점검","신탕정,탕정S/S 154kV 신탕정-탕정#2T/L GIS 보통점검, 탕정S/S GIS 전자변 교체","2019-12-03 09:00","2019-12-03 18:00","취소","취소","연속"]
[113,"대전충남","아산","신탕정탕정#1 T/L","신탕정,탕정S/S 154kV 신탕정-탕정#1T/L GIS 보통점검","신탕정,탕정S/S 154kV 신탕정-탕정#1T/L GIS 보통점검, 탕정S/S GIS 전자변 교체","2019-12-02 09:00","2019-12-02 18:00","취소","취소","연속"]
[114,"대전충남","직할","세종송강#2 T/L","[송전]국제과학비즈니스벨트 지장송전선로 이설 및 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.82~83 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2019-12-14 07:00","2019-12-19 18:00","취소","취소","연속"]
[115,"대전충남","직할","세종송강#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 이설 및 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.82~83 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2019-12-20 07:00","2019-12-21 18:00","취소","취소","연속"]
[116,"대전충남","직할","세종송강#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 이설 및 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.82~83 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2019-12-12 07:00","2019-12-13 18:00","취소","취소","연속"]
[117,"대전충남","직할","신탄진대청HP T/L","170kV GIS 전자변 교체","전자변 교체","2019-12-04 09:00","2019-12-04 18:00","취소","취소","연속"]
[118,"전북","군산","이리전주#2 T/L","154kV 이리-전주T/L 일부지중화관련 철탑교체공사","- 철탑교체 4기 : 49, 50, 51, 52호 - 전선교체 : 47~50, 51~53호 - 가선로 구성 및 기타 부대공사","2019-12-26 09:00","2019-12-31 18:00","2019-12-26 09:00","2019-12-31 18:00","연속"]
[119,"전북","군산","이리전주#1 T/L","154kV 이리-전주T/L 일부지중화관련 철탑교체공사","- 철탑교체 4기 : 49, 50, 51, 52호 - 전선교체 : 47~50, 51~53호 - 가선로 구성 및 기타 부대공사","2019-12-10 09:00","2019-12-24 18:00","2019-12-10 09:00","2019-12-24 18:00","연속"]
[120,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2019-12-09 08:00","2019-12-14 18:00","2019-12-09 08:00","2019-12-14 18:00","연속"]
[121,"전북","김제","정주고창#2 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2019-12-03 08:00","2019-12-08 18:00","2019-12-03 08:00","2019-12-08 18:00","연속"]
[122,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2019-12-02 08:00","2019-12-02 18:00","2019-12-02 08:00","2019-12-02 18:00","연속"]
[123,"전북","김제","정공S/S 154kV #60-#65 BUS TIE CB","154kV 정공E/C #5M.Tr 설치공사","- #5M.Tr 무부하가압 관련 휴전","2019-12-04 09:30","2019-12-05 18:00","2019-12-04 09:30","2019-12-05 18:00","연속"]
[124,"전북","김제","정공S/S 154kV #60 BUS","154kV 정공E/C #5M.Tr 설치공사","- #5M.Tr 무부하 가압 관련 휴전","2019-12-04 09:30","2019-12-05 18:00","2019-12-04 09:30","2019-12-05 18:00","연속"]
[125,"전북","김제","신김제정공#1 T/L","154kV 정공E/C #5M.Tr 설치공사","- M.Tr 상부모선 설치 관련 휴전 및","2019-12-02 09:30","2019-12-05 18:00","2019-12-02 09:30","2019-12-05 18:00","연속"]
[126,"전북","직할","신김제동전주#2 T/L","동전주SS 신김제-동전주#2T/L 차단기점검","동전주SS 신김제-동전주#2T/L 장기미동작 차단기 점검","2019-12-17 10:00","2019-12-17 18:00","취소","취소","연속"]
[127,"전북","김제","김제칠보HP T/L","칠보S/Y  가스누기 보수공사","칠보S/Y  가스누기 보수공사","2019-12-09 09:00","2019-12-11 18:00","2019-12-09 09:00","2019-12-11 18:00","연속"]
[128,"전북","김제","칠보H/P 154kV #1 M.Tr 1차 GIS","칠보S/Y  가스누기 보수공사","칠보S/Y  가스누기 보수공사","2019-12-09 09:00","2019-12-11 18:00","2019-12-09 09:00","2019-12-11 18:00","연속"]
[129,"전북","김제","칠보H/P 154kV #60 BUS","칠보S/Y  가스누기 보수공사","칠보S/Y  가스누기 보수공사","2019-12-09 09:00","2019-12-11 18:00","2019-12-09 09:00","2019-12-11 18:00","연속"]
[130,"전북","김제","정공칠보HP T/L","칠보S/Y  가스누기 보수공사","칠보S/Y  가스누기 보수공사","2019-12-12 09:00","2019-12-12 18:00","2019-12-12 09:00","2019-12-12 18:00","연속"]
[131,"전북","김제","칠보H/P 154kV #2 M.Tr 1차 GIS","칠보S/Y  가스누기 보수공사","칠보S/Y  가스누기 보수공사","2019-12-06 09:00","2019-12-06 18:00","2019-12-06 09:00","2019-12-06 18:00","연속"]
[132,"광주전남","강진","신강진대불#1 T/L","국산애자 특별진단(신강진-대불#1)","2019년도 가공송전 순시점검 위탁공사 신강진-대불#1T/L 국산애자 특별진단차","2019-12-09 09:00","2019-12-10 18:00","2019-12-09 09:00","2019-12-10 18:00","매일"]
[133,"광주전남","강진","신강진대불#2 T/L","국산애자 특별진단(신강진-대불#2)","2019년도 가공송전 순시점검 위탁공사 신강진-대불#2T/L 국산애자 특별진단차","2019-12-11 09:00","2019-12-12 18:00","2019-12-11 09:00","2019-12-12 18:00","매일"]
[134,"광주전남","강진","남창해남CS#2 T/L"," 남창-해남C/S T/L OPGW 교체공사","남창-해남C/S 구간 OPGW 코어 불량지점 교체","2019-12-05 08:00","2019-12-06 18:00","2019-12-05 08:00","2019-12-06 18:00","연속"]
[135,"광주전남","강진","해남해남CS#2 T/L"," 남창-해남C/S T/L OPGW 교체공사","남창-해남C/S 구간 OPGW 코어 불량지점 교체","2019-12-05 08:00","2019-12-06 18:00","2019-12-05 08:00","2019-12-06 18:00","연속"]
[136,"광주전남","광주","신화순S/S #1EM.Tr CB","19년 광주변전총액(4385-1,2DS 점검)","신화순S/S #3M.Tr 3차 DS점검(4385-1,2) 관련 4384 CB 휴전 → ESS 소내전원 확보용 : #1ES.Tr 가압 용도","2019-12-02 09:00","2019-12-02 18:00","2019-12-02 09:00","2019-12-02 18:00","연속"]
[137,"광주전남","목포","나주엄다#1 T/L","154kV 나주-엄다T/L 26호 안전이격확보공사","-#1T/L 암 공중이동 및 철탑조립","2019-12-19 08:00","2019-12-19 18:00","2019-12-19 08:00","2019-12-19 18:00","연속"]
[138,"광주전남","목포","나주엄다#1 T/L","154kV 나주-엄다T/L 26호 안전이격확보공사","-#1T/L 보조암설치","2019-12-16 08:00","2019-12-16 13:00","2019-12-16 08:00","2019-12-16 13:00","연속"]
[139,"광주전남","목포","나주엄다#2 T/L","154kV 나주-엄다T/L 26호 안전이격확보공사","-#2T/L 암조립 및 철탑조립","2019-12-16 13:00","2019-12-18 18:00","2019-12-16 13:00","2019-12-18 18:00","연속"]
[140,"광주전남","목포","영광S/S 154kV 재원태양광T/L GIS","`19년 목포전력지사 변전협력총액공사(GIS 점검)","GIS 점검","2019-12-03 09:00","2019-12-03 18:00","2019-12-03 09:00","2019-12-03 18:00","연속"]
[141,"광주전남","직할","나주평동#2 T/L","154kV 왕곡E/C 건설사업","(지중, 가공)154kV 나주-평동T/L No.19 - 20호간 선하지 C/H 2기 신설 - C/H(관형지지물) 2기 신설(No.19-1, 19-2) - 전력선 연,긴선 250m - C/H 인하선 연결 (변전)154kV 왕곡E/C 건설공사 - 나주-평동#2T/L 송전선로보호반 이설 및 설치 - 나주-왕곡#2T/L, 왕곡-평동#2T/L 무부하가","2019-12-16 09:00","2019-12-20 18:00","2019-12-16 09:00","2019-12-20 18:00","연속"]
[142,"광주전남","직할","나주평동#2 T/L","154kV 왕곡E/C 건설사업","(지중, 가공)154kV 나주-평동T/L No.19 - 20호간 선하지 C/H 2기 신설 - C/H(관형지지물) 2기 신설(No.19-1, 19-2) - 전력선 연,긴선 250m - C/H 인하선 연결","2019-12-08 09:00","2019-12-08 18:00","2019-12-08 09:00","2019-12-08 18:00","연속"]
[143,"광주전남","직할","나주평동#1 T/L","154kV 왕곡E/C 건설사업","(지중, 가공)154kV 나주-평동T/L No.19 - 20호간 선하지 C/H 2기 신설 - C/H(관형지지물) 2기 신설(No.19-1, 19-2) - 전력선 연,긴선 250m - C/H 인하선 연결 (변전)154kV 왕곡E/C 건설공사 - 나주-평동#1T/L 송전선로보호반 이설 및 설치 - 나주-왕곡#1T/L, 왕곡-평동#1T/L 무부하가","2019-12-08 09:00","2019-12-13 18:00","2019-12-08 09:00","2019-12-13 18:00","연속"]
[144,"광주전남","직할","농성S/S 154kV 농성-화정#1T/L GIS","18-19년 직할 변전정비회사 총액공사","- 송전선로 보호반 대체","2019-12-09 09:00","2019-12-11 12:00","2019-12-09 09:00","2019-12-11 12:00","연속"]
[145,"광주전남","직할","농성S/S 154kV 농성-화정#2T/L GIS","18-19년 직할 변전정비회사 총액공사","- 송전선로 보호반 대체","2019-12-11 13:00","2019-12-13 18:00","2019-12-11 13:00","2019-12-13 18:00","연속"]
[146,"광주전남","직할","매월S/S 154kV 매월-화정#1T/L GIS","18-19년 직할 변전정비회사 총액공사","- 송전선로 보호반 대체","2019-12-02 09:00","2019-12-04 18:00","2019-12-02 09:00","2019-12-04 18:00","연속"]
[147,"대구","달성","고령S/S 154kV #61 BUS","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-18 18:00","2019-12-19 18:00","취소","취소","연속"]
[148,"대구","달성","고령쌍림#2 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-09 11:00","2019-12-09 14:00","취소","취소","연속"]
[149,"대구","달성","고령다산#1 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-09 14:00","2019-12-09 16:00","취소","취소","연속"]
[150,"대구","달성","고령다산#2 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-10 08:00","2019-12-14 18:00","취소","취소","연속"]
[151,"대구","달성","고령쌍림#2 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-10 08:00","2019-12-15 18:00","취소","취소","연속"]
[152,"대구","달성","고령S/S 154kV #66 BUS","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-13 18:00","2019-12-14 18:00","취소","취소","연속"]
[153,"대구","달성","고령S/S 154kV #60 BUS","고령S/S 154kV 고령-서구지T/L S/W 증설공사","고령S/S 154kV 고령-서구지T/L S/W 증설공사","2019-12-01 18:00","2019-12-02 18:00","2019-12-01 18:00","2019-12-02 18:00","연속"]
[154,"대구","달성","고령S/S 154kV #61 BUS","고령S/S 154kV 고령-서구지T/L S/W 증설공사","고령S/S 154kV 고령-서구지T/L S/W 증설공사","2019-12-01 18:00","2019-12-02 18:00","2019-12-01 18:00","2019-12-02 18:00","연속"]
[155,"대구","달성","고령쌍림#2 T/L","고령S/S 154kV 인출변경공사","고령S/S 154kV 인출변경공사","2019-12-01 18:00","2019-12-02 18:00","2019-12-01 18:00","2019-12-02 18:00","연속"]
[156,"대구","달성","고령쌍림#1 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-09 09:00","2019-12-09 11:00","취소","취소","연속"]
[157,"대구","달성","고령S/S 154kV #60 BUS","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-18 18:00","2019-12-19 18:00","취소","취소","연속"]
[158,"대구","달성","고령쌍림#1 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-15 08:00","2019-12-19 18:00","취소","취소","연속"]
[159,"대구","달성","고령다산#1 T/L","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-15 08:00","2019-12-19 18:00","취소","취소","연속"]
[160,"대구","달성","고령S/S 154kV #65 BUS","154kV 고령-구지T/L 건설공사","154kV 고령-구지T/L 건설관련 송전선로 인출변경 및 PNL 이설공사","2019-12-13 18:00","2019-12-14 18:00","취소","취소","연속"]
[161,"대구","칠곡","구미광평#2 T/L","광평S/S 구미-광평#2T/L GIS 보통점검","광평S/S 구미-광평#2T/L GIS 보통점검","2019-12-03 09:30","2019-12-03 15:00","2019-12-08 13:00","2019-12-08 18:00","연속"]
[162,"대구","포항","건천천북#1 T/L","천북S/S 건천-천북#1TL 공기조작부 정밀점검","천북S/S 건천-천북#1TL 공기조작부 정밀점검","2019-12-17 09:00","2019-12-17 14:00","2019-12-17 09:00","2019-12-17 14:00","연속"]
[163,"대구","포항","건천천북#2 T/L","천북S/S 건천-천북#2TL 공기조작부 정밀점검","천북S/S 건천-천북#2TL 공기조작부 정밀점검","2019-12-17 14:00","2019-12-17 18:00","2019-12-17 14:00","2019-12-17 18:00","연속"]
[164,"대구","포항","청하영덕#1 T/L","청하-영덕#1,2TL 휴전( 청하변전소 외벽 보수작업)","청하-영덕#1,2TL 휴전( 청하변전소 외벽 보수작업)","2019-12-02 07:00","2019-12-06 18:00","2019-12-02 07:00","2019-12-06 18:00","매일"]
[165,"대구","포항","청하영덕#2 T/L","청하-영덕#1,2TL 휴전( 청하변전소 외벽 보수작업)","청하-영덕#1,2TL 휴전( 청하변전소 외벽 보수작업)","2019-12-02 07:00","2019-12-06 18:00","2019-12-02 07:00","2019-12-06 18:00","매일"]
[166,"경북","구미","남인동인동#1 T/L","2018-19년도 구미전력지사 가공송전협력회사 총액공사","ㅇ 선산-금전T/L S/T, 3호 애자교체 144개 ㅇ 선산-산동T/L 1,2,3,4호 애자교체 750개 ㅇ 서대구-남인동T/L 57,68호 애자교체 210개 ㅇ 남인동-인동T/L 165개","2019-12-05 07:00","2019-12-05 18:00","2019-12-05 07:00","2019-12-05 18:00","연속"]
[167,"경북","구미","남인동인동#2 T/L","2018-19년도 구미전력지사 가공송전협력회사 총액공사","ㅇ 선산-금전T/L S/T, 3호 애자교체 144개 ㅇ 선산-산동T/L 1,2,3,4호 애자교체 750개 ㅇ 서대구-남인동T/L 57,68호 애자교체 210개 ㅇ 남인동-인동T/L 165개","2019-12-04 07:00","2019-12-04 18:00","2019-12-04 07:00","2019-12-04 18:00","연속"]
[168,"경북","직할","안동풍산 T/L","154kV 안동-풍산T/L 공사현장 고도제한장치 설치","154kV 안동-풍산T/L 공사현장 고도제한장치 설치","2019-12-03 08:00","2019-12-05 18:00","2019-12-07 08:00","2019-12-08 18:00","연속"]
[169,"경북","직할","봉화현종산풍력 T/L","18~19년 경북본부 직할 변전정비회사 총액공사","DAIS 초기점검","2019-12-10 09:00","2019-12-10 18:00","2019-12-10 09:00","2019-12-10 18:00","연속"]
[170,"부산울산","동부산","구서노포#2 T/L","케이블 헤드 및 피뢰기 점검","케이블 헤드 및 피뢰기 점검","2019-12-03 14:00","2019-12-03 18:00","2019-12-03 14:00","2019-12-03 18:00","연속"]
[171,"부산울산","동부산","구서노포#1 T/L","케이블 헤드 및 피뢰기 점검","케이블 헤드 및 피뢰기 점검","2019-12-03 09:00","2019-12-03 14:00","2019-12-03 09:00","2019-12-03 14:00","연속"]
[172,"부산울산","동부산","신양산S/S 154kV #61-#62 SEC CB","신양산E/C 170kV GCB 차단기 동작시험","신양산E/C 170kV GCB 차단기 동작시험(61-62-0)","2019-12-06 14:00","2019-12-06 18:00","2019-12-06 14:00","2019-12-06 18:00","연속"]
[173,"부산울산","동부산","신양산S/S 154kV #60-#61 SEC CB","신양산E/C 170kV GCB 차단기 동작시험","신양산E/C 170kV GCB 차단기 동작시험(60-61-0)","2019-12-04 14:00","2019-12-04 18:00","2019-12-04 14:00","2019-12-04 18:00","연속"]
[174,"부산울산","동부산","신양산S/S 154kV #60-#65 BUS TIE CB","신양산E/C 170kV GCB 차단기 동작시험","신양산E/C 170kV GCB 차단기 동작시험(6100)","2019-12-04 09:30","2019-12-04 14:00","2019-12-04 09:30","2019-12-04 14:00","연속"]
[175,"부산울산","동부산","신양산S/S 154kV #65-#66 SEC CB","신양산E/C 170kV GCB 차단기 동작시험","신양산E/C 170kV GCB 차단기 동작시험(65-66-0)","2019-12-06 09:30","2019-12-06 14:00","2019-12-06 09:30","2019-12-06 14:00","연속"]
[176,"부산울산","동부산","신양산S/S 154kV #66-#67 SEC CB","신양산E/C 170kV GCB 차단기 동작시험","신양산E/C 170kV GCB 차단기 동작시험(66-67-0)","2019-12-05 14:00","2019-12-05 18:00","2019-12-05 14:00","2019-12-05 18:00","연속"]
[177,"부산울산","동부산","신양산S/S 154kV #62-#67 BUS TIE CB","신양산E/C 170kV GCB 차단기 동작시험","신양산E/C 170kV GCB 차단기 동작시험(6200)","2019-12-05 09:30","2019-12-05 14:00","2019-12-05 09:30","2019-12-05 14:00","연속"]
[178,"부산울산","북부산","호포물금 T/L","2019년 북부산 변전협력회사 총액공사","호포,물금E/C 154kV 호포-물금T/L GIS 차단기 동작시험","2019-12-04 09:00","2019-12-04 18:00","2019-12-04 09:00","2019-12-04 18:00","연속"]
[179,"부산울산","북부산","북부산물금 T/L","2019년 북부산 변전협력회사 총액공사","북부산,물금E/C 154kV 북부산-물금T/L GIS 차단기 동작시험","2019-12-05 09:00","2019-12-05 18:00","2019-12-05 09:00","2019-12-05 18:00","연속"]
[180,"부산울산","북부산","북부산물금 T/L","154kV 북부산E/C 구내 인출Bay 변경 전력구공사","전력구공사 - 154kV 북부산-물금 T/L 안전이격휴전","2019-12-09 08:00","2019-12-10 18:00","2019-12-09 08:00","2019-12-10 18:00","연속"]
[181,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-양산T/L 피뢰기 설치, 금구류 및 전선교체공사","154kV 북부산-양산T/L 피뢰기 설치, 금구류 및 전선교체공사 안전이격확보 1. 피뢰기 설치 : No. 49-63(15기) 2. 금구류 교체 : No. 2, 3, 37-39, 49-63(19기) 3. 전력선 교체 : No. 2-3, 37-39(3구간) 4. 아킹혼 설치 : No. 2, 3, 37-39, 양수#1C/H(6기). 끝.","2019-12-02 07:00","2019-12-13 18:00","2019-12-02 07:00","2019-12-13 18:00","매일"]
[182,"부산울산","북부산","북부산양산 T/L","154kV 북부산-양산T/L 피뢰기 설치, 금구류 및 전선교체공사","154kV 북부산-양산T/L 피뢰기 설치, 금구류 및 전선교체공사 1. 피뢰기 설치 : No. 49-63(15기) 2. 금구류 교체 : No. 2, 3, 37-39, 49-63(19기) 3. 전력선 교체 : No. 2-3, 37-39(3구간) 4. 아킹혼 설치 : No. 2, 3, 37-39, 양수#1C/H(6기). 끝.","2019-12-02 07:00","2019-12-13 18:00","2019-12-02 07:00","2019-12-13 18:00","연속"]
[183,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막T/L 안전이격확보공사","-154kV 서창-산막T/L No. 17∼21 안전이격확보공사 1. 구 간 : 154㎸ 서창-산막T/L 17∼21 안전이격확보공사 2. 지 지 물 : 철탑 3기(No. 18, 19, 20) 교체 ○ 공법 : Helper Tower[No. 18] / Enclosing[No. 19, 20] 3. 전 력 선 : ACSR 330㎟ × S ×","2019-12-07 07:00","2019-12-08 18:00","2019-12-07 07:00","2019-12-08 18:00","연속"]
[184,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막#1,2T/L 56~62호 지장철탑 이설공사","154kV 서창-산막#1,2T/L 56~62호 1.571km 이설","2019-12-14 08:00","2019-12-15 18:00","2019-12-14 08:00","2019-12-15 18:00","연속"]
[185,"부산울산","북부산","서창산막#2 T/L","154kV 서창-산막#1,2T/L 56~62호 지장철탑 이설공사","154kV 서창-산막#1,2T/L 56~62호 1.571km 이설","2019-12-21 08:00","2019-12-22 18:00","2019-12-21 08:00","2019-12-22 18:00","연속"]
[186,"부산울산","북부산","양산산막#1 T/L","양산S/S 현대화공사","154kV #1Sh.C 시험가압 선로","2019-12-16 10:00","2019-12-17 10:00","2019-12-16 10:00","2019-12-17 10:00","연속"]
[187,"부산울산","북부산","북부산호포 T/L","2019년 북부산 변전협력회사 총액공사","북부산,호포E/C 154kV 북부산-호포T/L LA 보통점검","2019-12-06 09:00","2019-12-06 18:00","2019-12-06 09:00","2019-12-06 18:00","연속"]
[188,"부산울산","울산","두왕영남TP#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-12-04 07:00","2019-12-04 18:00","2019-12-04 07:00","2019-12-04 18:00","연속"]
[189,"부산울산","울산","두왕영남TP#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-12-02 07:00","2019-12-03 18:00","2019-12-02 07:00","2019-12-03 18:00","연속"]
[190,"부산울산","울산","신울산S/S 154kV #63-#68 BUS TIE CB","18~19년 변전협력 총액공사","- 신울산E/C154kV #63-#68 BUS TIE 6302DS 과열조치 및 6300차단기 동작시험","2019-12-04 09:00","2019-12-04 18:00","2019-12-04 09:00","2019-12-04 18:00","연속"]
[191,"부산울산","울산","신울산S/S 154kV #68 BUS","18~19년 변전협력 총액공사","- 신울산E/C154kV #63-#68 BUS TIE 6302DS 과열조치","2019-12-04 09:00","2019-12-04 18:00","2019-12-04 09:00","2019-12-04 18:00","연속"]
[192,"부산울산","울산","신울산울산#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2019-12-01 07:00","2019-12-01 18:00","2019-12-01 07:00","2019-12-01 18:00","연속"]
[193,"부산울산","울산","언양산막#1 T/L","18-19년 동부산전력지사 송전정비 협력회사 총액공사","154kV 반천-언양#2T/L 휴전관련 안전이격","2019-12-11 08:00","2019-12-11 18:00","취소","취소","연속"]
[194,"부산울산","울산","용연처용#2 T/L","345kV 신울산복합-북부산T/L 건설공사","○ 154kV 용연-처용T/L 임시선로 구성 - 구간 : No.5~8호","2019-12-08 07:00","2019-12-11 18:00","2019-12-08 07:00","2019-12-11 18:00","연속"]
[195,"부산울산","울산","용연처용#2 T/L","345kV 신울산복합-북부산T/L 건설공사","345kV 신울산복합-북부산T/L 횡단선로 보호망 설치 - 구간 : 154kV 용연-처용T/L No.11~12호 사이","2019-12-23 07:00","2019-12-23 18:00","2019-12-23 07:00","2019-12-23 18:00","연속"]
[196,"부산울산","울산","용연처용#1 T/L","345kV 신울산복합-북부산T/L 건설공사","○ 154kV 용연-처용T/L 임시선로 구성 - 구간 : No.5~8호","2019-12-04 07:00","2019-12-07 18:00","2019-12-04 07:00","2019-12-07 18:00","연속"]
[197,"부산울산","울산","용연처용#1 T/L","345kV 신울산복합-북부산T/L 건설공사","345kV 신울산복합-북부산T/L 횡단선로 보호망 설치 - 구간 : 154kV 용연-처용T/L No.11~12호 사이","2019-12-23 07:00","2019-12-23 18:00","2019-12-23 07:00","2019-12-23 18:00","연속"]
[198,"부산울산","울산","울산울산TP#1 T/L","345kV 신울산복합-북부산T/L 건설공사","154kV 울산-울산TP 임시선로를 본선로(345kV 신울산복합-북부산T/L과 병가)구성 작업시행","2019-12-24 07:00","2020-01-04 18:00","2019-12-24 07:00","2020-01-04 18:00","연속"]
[199,"경남","직할","녹공마천#2 T/L","마천S/S 154kV 녹공-마천#2T/L 보호PNL 대체","마천S/S 154kV 녹공-마천#2T/L 보호PNL 대체 및 CB 조작시험","2019-12-02 09:30","2019-12-04 17:30","2019-12-02 09:30","2019-12-04 17:30","연속"]
[200,"경남","직할","신김해진영#1 T/L","송전선로 OPGW 항공장애표시구 설치 공사","154KV 신김해-진영#1T/L 29-31호 항공장애표시구 설치","2019-12-01 07:00","2019-12-01 18:00","2019-12-01 07:00","2019-12-01 18:00","연속"]
[201,"경남","직할","신김해삼정#1 T/L","송전선로 OPGW 항공장애표시구 설치 공사","154KV 신김해-삼정#1T/L 9-11호 항공장애표시구 설치","2019-12-05 07:00","2019-12-05 12:00","2019-12-05 07:00","2019-12-05 12:00","연속"]
[202,"경남","직할","신김해장유#1 T/L","송전선로 OPGW 항공장애표시구 설치 공사","154KV 신김해-장유#1T/L 12-13호 항공장애표시구 설치","2019-12-06 07:00","2019-12-06 12:00","2019-12-06 07:00","2019-12-06 12:00","연속"]
[203,"경남","직할","신월동읍#2 T/L","154kV 신월-동읍#2T/L 노후금구류 교체공사","#2T/L 2~28호, 31호 노후 금구류 교체","2019-12-06 07:00","2019-12-15 18:00","2019-12-06 07:00","2019-12-15 18:00","매일"]
[204,"경남","진주","사천개양#2 T/L","154kV 사천-개양T/L No.8 안전이격확보 공사","○ 154kV 사천-개양T/L No.8 신설철탑조립(인클로징) 및 No.7~10 구간 전력선 교체(0.849 C-km)","2019-12-08 07:00","2019-12-09 18:00","2019-12-08 07:00","2019-12-09 18:00","연속"]
[205,"경남","진주","사천개양#1 T/L","154kV 사천-개양T/L No.8 안전이격확보공사","○ 154kV 사천-개양T/L No.8 신설철탑조립(인클로징) 및 No.7~10 구간 전력선 교체(0.849 C-km)","2019-12-06 07:00","2019-12-07 18:00","2019-12-06 07:00","2019-12-07 18:00","연속"]
[206,"경남","통영","통영거제#2 T/L","2019년 170kV GIS 정밀점검 공사 시험가압","2019년 170kV GIS 정밀점검 공사 시험가압","2019-12-07 07:30","2019-12-07 09:30","취소","취소","연속"]
[207,"경남","통영","통영거제#2 T/L","OPGW 항공장애표시구 미설치 구간 설치 공사","154KV 통영-거제#2T/L 16-17호 항공장애표시구 설치","2019-12-14 07:00","2019-12-14 18:00","2019-12-07 07:00","2019-12-07 18:00","연속"]
[208,"경남","통영","통영거제#2 T/L","2019년 170kV GIS 정밀점검 공사 시험가압","2019년 170kV GIS 정밀점검 공사 시험가압","2019-12-01 07:30","2019-12-01 09:30","취소","취소","연속"]
[209,"경남","통영","아주S/S 대우조선 T/L CB","아주S/S 154kV 대우조선T/L 피뢰기 대체공사","아주S/S 154kV 대우조선T/L 피뢰기 대체공사","2019-08-11 09:00","2019-08-11 18:00","취소","취소","연속"]
[210,"경남","함안","창녕초동#2 T/L","OPGW 항공장애표시구 미설치 구간 설치 공사","154KV 창녕-초동#2T/L 50-51, 53-54호 항공장애표시구 설치","2019-12-04 13:00","2019-12-04 18:00","2019-12-04 13:00","2019-12-04 18:00","연속"]
[211,"경남","함안","창녕초동#1 T/L","OPGW 항공장애표시구 미설치 구간 설치 공사","154KV 창녕-초동#1T/L 50-51, 53-54호 항공장애표시구 설치","2019-12-04 07:00","2019-12-04 12:00","2019-12-04 07:00","2019-12-04 12:00","연속"]
[212,"경남","함안","한림정삼계#1 T/L","154kV 한림정-삼계 #1T/L 10호 초기점검","154kV 한림정-삼계 T/L 10호 초기점검","2019-12-14 08:30","2019-12-14 13:00","2019-12-14 08:30","2019-12-14 13:00","연속"]
[213,"경남","함안","한림정삼계#2 T/L","154kV 한림정-삼계 #2T/L 10호 초기점검","154kV 한림정-삼계 T/L 10호 초기점검","2019-12-14 13:00","2019-12-14 18:00","2019-12-14 13:00","2019-12-14 18:00","연속"]