{"text_format":"2","workbook":"xlsx","n_sheets":4,"sheets":["종합","345송부","154송부","시송전설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":12,"comments":2,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"종합","index":0,"n_rows":37,"n_cols":33,"rows_kept":37,"cut":false,"hidden":true,"merged":[[0,0,0,15],[7,14,7,15],[7,1,7,2],[8,1,8,2],[7,9,7,13],[7,3,7,6],[8,3,8,6],[14,14,14,15],[10,1,10,2],[11,1,11,2],[14,9,14,13],[9,1,9,2],[14,2,14,6],[11,3,11,6],[10,3,10,6],[9,3,9,6]]}
[{"$f":"\"'20년 \"&R15&\"월 휴전심의 결과\"","v":"'20년 2월 휴전심의 결과"}]
[]
[]
[]
[]
[]
["◎ 전체 심의결과"]
["전   압","신 청",null,"채 택",null,null,null,"일정\n조정","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)"]
["765kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B9-I9","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J9,L9,N9)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O9/B9)","v":{"$error":"#REF!"}}]
["345kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B10-I10","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J10,L10,N10)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O10/B10)","v":{"$error":"#REF!"}}]
["154kV",{"$f":"MAX(#REF!)","v":{"$error":"#REF!"}},null,{"$f":"B11-I11","v":{"$error":"#REF!"}},null,null,null,{"$f":"COUNTIF(#REF!,\"일정조정\")","v":{"$error":"#REF!"}},{"$f":"SUM(J11,L11,N11)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"병행\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"취소\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"연기\")","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"Y\")","v":{"$error":"#REF!"}},{"$f":"(O11/B11)","v":{"$error":"#REF!"}}]
["계",{"$f":"SUM(B9:B11)","v":{"$error":"#REF!"}},null,{"$f":"SUM(D9:D11)","v":{"$error":"#REF!"}},null,null,null,{"$f":"SUM(H9:H11)","v":{"$error":"#REF!"}},{"$f":"SUM(J12,L12,N12)","v":{"$error":"#REF!"}},{"$f":"SUM(J9:J11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(L9:L11)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(N9:N11)","v":{"$error":"#REF!"}},{"$f":"SUM(O9:O11)","v":{"$error":"#REF!"}},{"$f":"(O12/B12)","v":{"$error":"#REF!"}}]
[]
["◎ 본부별 심의결과",{"$nulls":16},"월"]
["사업소","신 청","(765/345/154)",{"$nulls":4},"채 택","불채택","(병행/취소/연기)",{"$nulls":4},"연간계획반영(%)",null,null,2]
["서   울",{"$f":"SUM(C16:G16)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"서울\")","v":{"$error":"#REF!"}},{"$f":"B16-I16","v":{"$error":"#REF!"}},{"$f":"SUM(J16,L16,N16)","v":{"$error":"#REF!"}},{"$f":"SUM(S16:U16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W16:Y16)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA16:AC16)","v":{"$error":"#REF!"}},{"$f":"SUM(AE16:AG16)","v":{"$error":"#REF!"}},{"$f":"(O16/B16)","v":{"$error":"#REF!"}},null,"서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R16)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R16)","v":{"$error":"#REF!"}}]
["남서울",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"남서울\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$f":"SUM(J17,L17,N17)","v":{"$error":"#REF!"}},{"$f":"SUM(S17:U17)","v":{"$error":"#REF!"}},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"남서울",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R17)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R17)","v":{"$error":"#REF!"}}]
["인   천",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"인천\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"인천",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R18)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R18)","v":{"$error":"#REF!"}}]
["경기북부",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기북부\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기북부",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R19)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R19)","v":{"$error":"#REF!"}}]
["경   기",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경기\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경기",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R20)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R20)","v":{"$error":"#REF!"}}]
["강   원",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"강원\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"강원",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R21)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R21)","v":{"$error":"#REF!"}}]
["충   북",{"$f":"SUM(C22:G22)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"충북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"충북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R22)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R22)","v":{"$error":"#REF!"}}]
["대전충남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대전충남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"대전충남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R23)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R23)","v":{"$error":"#REF!"}}]
["전   북",{"$f":"SUM(C24:G24)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"전북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"전북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R24)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R24)","v":{"$error":"#REF!"}}]
["광주전남",{"$f":"SUM(C25:G25)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"광주전남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"광주전남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R25)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R25)","v":{"$error":"#REF!"}}]
["대구",{"$f":"SUM(C26:G26)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"대구\")","v":{"$error":"#REF!"}},{"$f":"B26-I26","v":{"$error":"#REF!"}},{"$f":"SUM(J26,L26,N26)","v":{"$error":"#REF!"}},{"$f":"SUM(S26:U26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(W26:Y26)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA26:AC26)","v":{"$error":"#REF!"}},{"$f":"SUM(AE26:AG26)","v":{"$error":"#REF!"}},{"$f":"(O26/B26)","v":{"$error":"#REF!"}},null,"대구",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R26)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R26)","v":{"$error":"#REF!"}}]
["경북",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경북\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"경북",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R27)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R27)","v":{"$error":"#REF!"}}]
["부산울산",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"부산울산\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},null,"부산울산",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R28)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R28)","v":{"$error":"#REF!"}}]
["경   남",{"$error":"#REF!"},{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"경남\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$f":"SUM(W29:Y29)","v":{"$error":"#REF!"}},"/",{"$f":"SUM(AA29:AC29)","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},null,"경남",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R29)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R29)","v":{"$error":"#REF!"}}]
["제   주",{"$f":"SUM(C30:G30)","v":{"$error":"#REF!"}},{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},"/",{"$f":"COUNTIF(#REF!,\"제주\")","v":{"$error":"#REF!"}},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},"/",{"$error":"#REF!"},"/",{"$error":"#REF!"},{"$error":"#REF!"},{"$f":"(O30/B30)","v":{"$error":"#REF!"}},null,"제주",{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"병행\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"취소\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"연기\",#REF!,R30)","v":{"$error":"#REF!"}},null,{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}},{"$f":"COUNTIFS(#REF!,\"y\",#REF!,R30)","v":{"$error":"#REF!"}}]
[]
[" 붙임 :  1. 집중심의내역 1부"]
[" 붙임 :  전압별 검토서 1부. 끝."]
[]
[null,{"$f":"SUM(B16:B30)","v":{"$error":"#REF!"}},{"$f":"SUM(C16:C30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(E16:E30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(G16:G30)","v":{"$error":"#REF!"}},{"$f":"SUM(H16:H30)","v":{"$error":"#REF!"}},{"$f":"SUM(I16:I30)","v":{"$error":"#REF!"}},{"$f":"SUM(J16:J30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(L16:L30)","v":{"$error":"#REF!"}},null,{"$f":"SUM(N16:N30)","v":{"$error":"#REF!"}},{"$f":"SUM(O16:O30)","v":{"$error":"#REF!"}}]
[{"$f":"COUNTIF(B36:N36,\"NO\")","v":0},{"$f":"IF(B35=B12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(C35=B9,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(E35=B10,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(G35=B11,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(H35=D12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(I35=I12,\"\",\"NO\")","v":{"$error":"#REF!"}},{"$f":"IF(J35=J12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(L35=L12,\"\",\"NO\")","v":{"$error":"#REF!"}},null,{"$f":"IF(N35=N12,\"\",\"NO\")","v":{"$error":"#REF!"}}]
[{"$f":"IF(A36>=1,\"틀린곳\",\"\")","v":""},{"$f":"IF(B36=\"NO\",\"총계\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(C36=\"NO\",\"765\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(D36=\"NO\",\"총계\",\"\")","v":""},{"$f":"IF(E36=\"NO\",\"345\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(G36=\"NO\",\"154\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(H36=\"NO\",\"채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(I36=\"NO\",\"불채택\",\"\")","v":{"$error":"#REF!"}},{"$f":"IF(J36=\"NO\",\"병행\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(L36=\"NO\",\"취소\",\"\")","v":{"$error":"#REF!"}},"",{"$f":"IF(N36=\"NO\",\"연기\",\"\")","v":{"$error":"#REF!"}}]

{"sheet":"345송부","index":1,"n_rows":35,"n_cols":13,"rows_kept":35,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2020년도 \"&종합!R15&\"월 휴전계획서\"","v":"2020년도 2월 휴전계획서"}]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","직할","양주S/S 345kV 신파주-양주#2T/L CB(7471)","19년 미동작 차단기 조작시험","조작시험","2020-02-03 14:00","2020-02-03 18:00","2020-02-03 14:00","2020-02-03 18:00","연속"]
[2,"경기북부","직할","양주S/S 345kV 신파주-양주#2T/L-#2 M.Tr 1차 TIE CB(7400)","19년 미동작 차단기 조작시험","조작시험","2020-02-03 09:00","2020-02-03 14:00","2020-02-03 09:00","2020-02-03 14:00","연속"]
[3,"충북","청주","신옥천청양 T/L","20-21년 청주전력 변전협력회사 총액공사","신옥천청양T/L C상 CVT 전압 계측값 불량 관련 설비 점검","2020-02-26 10:00","2020-02-26 18:00","2020-02-22 10:00","2020-02-22 18:00","연속"]
[4,"충북","청주","신옥천S/S #2 M.Tr","20-21년 청주전력 변전협력회사 총액공사","신옥천S/S #2M.Tr 2차측 N상 접속 불량 조치","2020-02-27 09:30","2020-02-27 18:00","2020-02-27 09:30","2020-02-27 18:00","연속"]
[5,"대전충남","서산","북당진S/S 345kV #2 Tie.Tr CB(7572)","345kV 북당진E/C #1M.Tr 증설공사","#1M.Tr 무부하 가압","2020-02-25 13:00","2020-02-26 13:00","2020-02-15 09:00","2020-02-16 18:00","연속"]
[6,"대전충남","서산",null,"345kV 신송산분기T/L 건설공사","- 해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-02-19 07:00","2020-02-23 18:00","취소","취소","연속"]
[7,"대전충남","서산","북당진S/S 345kV #70 BUS","345kV 북당진E/C #1M.Tr 증설공사","#1M.Tr 무부하 가압","2020-02-25 13:00","2020-02-26 13:00","2020-02-15 09:00","2020-02-16 18:00","연속"]
[8,"대전충남","서산","북당진S/S 345kV #2 Tie.Tr CB(7572)","345kV 북당진E/C #1M.Tr 증설공사","#1M.Tr 무부하 가압","2020-02-25 13:00","2020-02-26 13:00","취소","취소","연속"]
[9,"대전충남","서산","신당진개폐소현대제철 T/L","345kV 신송산분기T/L 건설공사","- 해당구간 : No.71 ~ No.69 구간내 No.70 선로 - 공사내용 : No.70 선로 가철탑 이설 전력선 공중이동 ACSR/AW 480SQ x 4B x 2C (0.793km)","2020-02-24 07:00","2020-02-28 18:00","취소","취소","연속"]
[10,"전북","군산","청양군산#2 T/L","345kV 청양-군산T/L 정밀점검 공사","345kV 청양-군산#2T/L 정밀점검 공사 : 군산S/S ~ No.61","2020-02-24 08:00","2020-02-28 17:00","2020-02-24 08:00","2020-02-28 17:00","매일"]
[11,"전북","군산","청양군산#1 T/L","345kV 청양-군산T/L 정밀점검 공사","345kV 청양-군산#1T/L 정밀점검 공사 : 군산S/S ~ No.61","2020-02-17 08:00","2020-02-21 17:00","2020-02-17 08:00","2020-02-21 17:00","매일"]
[12,"광주전남","강진","신강진S/S 7300 TIE CB(7300)","신강진S/S 345kV 취약설비 GIS화 공사","-7300 CB 실린더 교체","2020-02-12 09:00","2020-02-12 18:00","2020-02-12 09:00","2020-02-12 18:00","연속"]
[13,"광주전남","강진","신강진S/S 7400 TIE CB(7400)","신강진S/S 345kV 취약설비 GIS화","- 7400 유압시스템 점검","2020-02-11 09:00","2020-02-11 18:00","2020-02-11 09:00","2020-02-11 18:00","연속"]
[14,"광주전남","광주","신광주신화순#2 T/L","20년 광주변전총액(신광주-신화순#2T/L PNL 교체)","1. 신광주, 신화순S/S 신광주-신화순#2T/L 1ST, 2ND PNL 교체 2. 신광주S/S 신광주-신화순#2T/L CVT 단자반 교체","2020-02-17 09:00","2020-02-28 18:00","2020-02-17 09:00","2020-02-28 18:00","연속"]
[15,"광주전남","광주","신광주신화순#1 T/L","20년 광주변전총액(신광주-신화순#1T/L PNL 교체)","1. 신광주, 신화순S/S 신광주-신화순#1T/L 1ST, 2ND PNL 교체 2. 신광주S/S 신광주-신화순#1T/L CVT 단자반 교체","2020-02-03 09:00","2020-02-14 18:00","2020-02-03 09:00","2020-02-14 18:00","연속"]
[16,"대구","경산","신경산대구#2 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 신경산-대구 No.3~6 - No.5 본선로 구성","2020-02-07 08:00","2020-02-16 18:00","2020-02-07 08:00","2020-02-16 18:00","연속"]
[17,"대구","경산","신경산대구#1 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 신경산-대구 No.3~6 - No.5 본선로 구성","2020-02-17 08:00","2020-02-26 18:00","2020-02-17 08:00","2020-02-26 18:00","연속"]
[18,"대구","칠곡","북대구S/S 345kV TIE-북대구-선산T/L CB(7200)","북대구S/S TIE 북대구-선산T/L 7200 GIS 컨트롤블럭교체","북대구S/S TIE 북대구-선산T/L 7200 GIS 컨트롤블럭교체","2020-02-26 09:30","2020-02-26 18:00","취소","취소","연속"]
[19,"대구","칠곡","북대구S/S 345kV TIE-신포항-북대구T/L CB(7100)","북대구S/S TIE 신포항-북대구T/L 7100 GIS 컨트롤블럭교체","북대구S/S TIE 신포항-북대구T/L 7100 GIS 컨트롤블럭교체","2020-02-19 09:30","2020-02-19 18:00","취소","취소","연속"]
[20,"대구","칠곡","북대구S/S 345kV 신포항-북대구T/L CB(7172)","북대구S/S 신포항-북대구T/L 7172 GIS 컨트롤블럭교체","북대구S/S 신포항-북대구T/L 7172 GIS 컨트롤블럭교체","2020-02-24 09:30","2020-02-24 18:00","취소","취소","연속"]
[21,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2020-02-17 08:00","2020-02-17 18:00","취소","취소","연속"]
[22,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2020-02-19 08:00","2020-02-19 18:00","취소","취소","연속"]
[23,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2020-02-18 08:00","2020-02-18 18:00","취소","취소","연속"]
[24,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","T-BUS 및 8DS 철거","2020-02-20 08:00","2020-02-20 18:00","취소","취소","연속"]
[25,"부산울산","동부산","신양산북부산#2 T/L","[1차] 345kV 신양산S/S 현대화공사","1. 내용 - 신양산-북부산#2T/L 제어케이블 이설 - 345kV #2M.Tr 및 1,2,3차 제어케이블 이설 - 345kV #2M.Tr 2차 인출변경 - 154kV 신양산-수영#2T/L 인출변경 2. 선로 이설 후 - 신규 GIS 시험가압(24H)","2020-02-24 09:00","2020-03-10 18:00","2020-02-24 09:00","2020-03-10 18:00","연속"]
[26,"부산울산","동부산","신양산S/S #2 M.Tr","[1차] 345kV 신양산S/S 현대화공사","1. 내용 - 신양산-북부산#2T/L 제어케이블 이설 - 345kV #2M.Tr 및 1,2,3차 제어케이블 이설 - 345kV #2M.Tr 2차 인출변경 - 154kV 신양산-수영#2T/L 인출변경 2. 선로 이설 후 - 신규 GIS 시험가압(24H)","2020-02-24 09:00","2020-03-10 18:00","2020-02-24 09:00","2020-03-10 18:00","연속"]
[27,"대구",null,"월성 1호기 기동용변압기 CB(7671, 7600)","제2차 안전유지설비점검 관련 전원절체시험","- SST->UST 소내전원절체시험","2020-02-03 09:00","2020-02-05 18:00","2020-02-03 09:00","2020-02-05 18:00","연속"]
[28,"대구",null,"월성 1호기 주변압기 CB(7272, 7200)","제2차 안전유지설비점검 관련 전원절체시험","- UST->SST 소내전원절체시험","2020-02-03 09:00","2020-02-05 18:00","2020-02-03 09:00","2020-02-05 18:00","연속"]
[29,"광주전남",null,"한빛 3호기 주변압기 CB(7700, 7771)","한빛3호기 17차 O/H 공사","○ 3호기 OH 완료에 따른 계통연결(시험/최종)\n○ 정비내용\n   - 주변압기 교체공사, 보조변압기 일반점검\n   - 보호계전기 정정, 개체시험 및 연동시험 등","2020-02-25 18:00","2020-02-25 23:59","2020-02-25 18:00","2020-02-25 23:59","연속"]
[30,"광주전남",null,"한빛 4호기 주변압기 CB(7A00, 7A71)","한빛4호기 16차 O/H 공사","○ 4호기 OH 완료에 따른 계통연결(시험/최종)\n○ 정비내용\n   - GIB/GIS 교체공사, 주/보조변압기 일반점검\n   - 보호계전기 정정, 개체시험 및 연동시험 등","2020-02-29 17:00","2020-02-29 23:00","2020-02-29 17:00","2020-02-29 23:00","연속"]
[31,"경북",null,"한울 4호기 주변압기 CB(7A00, 7A72)","4호기 14차 계획예방정비 소내전원 절체시험","○ 소내전원 절체시험\n- 절체시험 후 개방차단기 재투입","2020-02-06 16:00","2020-02-06 22:00","2020-02-06 16:00","2020-02-06 22:00","연속"]

{"sheet":"154송부","index":2,"n_rows":54,"n_cols":13,"rows_kept":54,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,12,3,12],[2,2,3,2],[2,11,3,11]]}
[{"$f":"\"2020년도 \"&종합!R15&\"월 휴전계획서\"","v":"2020년도 2월 휴전계획서"}]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)","처리결과\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","동서울","동서울강동#2 T/L","서울 동남권지역 전기공급시설 전력구공사(동서울#2-강남 5차)","전력구 흙막이 작업(H-Pile 천공 및 근입)","2020-02-18 14:00","2020-02-18 18:00","2020-02-18 14:00","2020-02-18 18:00","연속"]
[2,"남서울","동서울","동서울강동#1 T/L","서울 동남권지역 전기공급시설 전력구공사(동서울#2-강남5차)","전력구 흙막이 작업(H-Pile 천공 및 근입)","2020-02-18 09:00","2020-02-18 14:00","2020-02-18 09:00","2020-02-18 14:00","연속"]
[3,"경기북부","고양","신파주송포#2 T/L","154kV 신파주-송포#1,2T/L 하자보수공사","- 대상 : 154kV 신파주-송포#1,2T/L 맨홀#17~#18 관로 약 410m 구간 (규격 : XLPE 2000㎟, LS / 준공년월 : 2010.02) - 내용 : 154kV 신파주-송포#1,2T/L 일부구간 선로교체 및 선형 개량 - 사유 : 경과지 일부 사유지 침범관련 하자보수공사 시행","2020-02-24 09:00","2020-03-09 18:00","취소","취소","연속"]
[4,"경기북부","고양","신파주송포#1 T/L","154kV 신파주-송포#1,2T/L 하자보수공사","- 대상 : 154kV 신파주-송포#1,2T/L 맨홀#17~#18 관로 약 410m 구간 (규격 : XLPE 2000㎟, LS / 준공년월 : 2010.02) - 내용 : 154kV 신파주-송포#1,2T/L 일부구간 선로교체 및 선형 개량 - 사유 : 경과지 일부 사유지 침범관련 하자보수 시행","2020-02-10 09:00","2020-02-24 18:00","취소","취소","연속"]
[5,"경기북부","구리","구리신내#2 T/L","20~21 구리전력 변전정비 총액공사","구리S/S 154kV 구리-신내#2T/L GIS 조작시험","2020-02-26 09:00","2020-02-26 18:00","취소","취소","연속"]
[6,"경기북부","직할","진접S/S 154kV #60-#65 BUS TIE GIS","20~21 구리전력 변전정비 총액공사","진접S/S 154kV #1 BUS-TIE GIS 조작시험","2020-02-27 09:00","2020-02-27 18:00","2020-02-27 09:00","2020-02-27 18:00","연속"]
[7,"강원","원주","신제천남원주#2 T/L","신제천-남원주 #2 T/L 과열개소 정비","신제천-남원주 #2 T/L 과열개소 정비","2020-02-10 10:00","2020-02-10 18:00","2020-02-10 10:00","2020-02-10 18:00","연속"]
[8,"대전충남","직할","세종송강#2 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.82~83 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2020-02-19 07:00","2020-02-24 18:00","취소","취소","연속"]
[9,"대전충남","직할","세종송강#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.82~83 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2020-02-25 07:00","2020-02-26 18:00","취소","취소","연속"]
[10,"대전충남","직할","세종송강#1 T/L","[송전]국제과학비즈니스벨트 지장송전선로 지중화공사(요청자시행)","ㅇ 요청자(한국토지주택공사) 직접시행 지장이설 및 지중화공사 ㅇ 공사구간 : 154kV 세종-송강T/L No.82~83 ㅇ 철탑 : C/H 1기 설치, 가철탑 1기 ㅇ 전력선 : HSTACIR/AW 330 x S x 2C (1.041km) ㅇ CH 1기 설치, 가철탑 1기 설치철거 외 기타 부대공사 시행","2020-02-17 07:00","2020-02-18 18:00","취소","취소","연속"]
[11,"전북","군산","군공소룡#1 T/L","군산P/O 차단기 점검공사","군공-소룡#1T/L 차단기 보통점검","2020-02-04 09:00","2020-02-04 15:00","취소","취소","연속"]
[12,"전북","군산","군공소룡#2 T/L","군산P/O 차단기 조작시험","군공-소룡#2T/L 차단기 조작시험","2020-02-04 15:00","2020-02-04 17:00","취소","취소","연속"]
[13,"전북","군산","군공S/S 154kV #60-#65 BUS TIE CB","군산P/O 차단기 점검공사(154kV)","1. 6100 차단기 보통점검","2020-02-10 09:30","2020-02-10 18:00","2020-02-10 09:30","2020-02-10 18:00","연속"]
[14,"전북","군산","내초군장#1 T/L","군산P/O 차단기 조작시험","1. 군장 627 차단기 조작시험 2. 내초 665 차단기 조작시험","2020-02-11 09:30","2020-02-11 13:00","취소","취소","연속"]
[15,"전북","군산","내초군장#2 T/L","군산P/O 차단기 조작시험","1. 군장 637 차단기 조작시험 2. 내초 667 차단기 조작시험","2020-02-11 13:00","2020-02-11 18:00","취소","취소","연속"]
[16,"전북","군산","군공내초#1 T/L","군산P/O 차단기 조작시험","군공-내초#1T/L 차단기 조작시험","2020-02-03 09:00","2020-02-03 12:00","취소","취소","연속"]
[17,"전북","군산","군공내초#2 T/L","군산P/O 차단기 조작시험","군공-내초#2T/L 차단기 조작시험","2020-02-03 13:00","2020-02-03 16:00","취소","취소","연속"]
[18,"전북","군산","비응S/S 154KV #65-#66 SEC CB","군산P/O 차단기 점검공사(154kV)","1. 65-66-0 차단기 보통점검","2020-02-18 09:30","2020-02-18 11:30","취소","취소","연속"]
[19,"전북","군산","비응S/S 154KV #60-#61 SEC CB","군산P/O 차단기 점검공사(154kV)","1. 60-61-0 차단기 보통점검","2020-02-18 13:00","2020-02-18 18:00","취소","취소","연속"]
[20,"전북","군산","비응S/S 154KV #60-#65 BUS TIE CB","군산P/O 차단기 점검공사(154kV)","1. 6100 차단기 보통점검","2020-02-13 09:30","2020-02-13 13:00","취소","취소","연속"]
[21,"전북","군산","비응S/S 154KV #61-#66 BUS TIE CB","군산P/O 차단기 점검공사(154kV)","1. 6200 차단기 보통점검","2020-02-13 13:00","2020-02-13 18:00","취소","취소","연속"]
[22,"전북","군산","소룡S/S 154kV #60-#65 BUS TIE CB","군산P/O 차단기 점검공사(154kV)","1. 6100 차단기 보통점검","2020-02-12 09:30","2020-02-12 18:00","취소","취소","연속"]
[23,"전북","군산","영등팔봉#1 T/L","군산P/O 차단기 조작시험","영등-팔봉#1T/L 차단기 조작시험","2020-02-05 09:00","2020-02-05 12:00","취소","취소","연속"]
[24,"전북","군산","팔봉S/S 154kV #60-#65 BUS TIE CB","군산P/O 차단기 조작시험","1. 팔봉 6100 차단기 조작시험","2020-02-19 09:30","2020-02-19 13:00","취소","취소","연속"]
[25,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2020-02-24 08:00","2020-02-29 18:00","2020-02-24 08:00","2020-02-29 18:00","연속"]
[26,"전북","김제","정주고창#2 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2020-02-18 08:00","2020-02-23 18:00","2020-02-18 08:00","2020-02-23 18:00","연속"]
[27,"전북","김제","정주고창#1 T/L","154kV 정주-고창 안전이격거리 확보공사","철탑 교체 : No.39, 40 전력선 교체 : No.37~41","2020-02-17 08:00","2020-02-17 18:00","2020-02-17 08:00","2020-02-17 18:00","연속"]
[28,"전북","김제","신김제정공#1 T/L","KCFT #1 GIS 시험가압","정밀점검 및 KCFT 선로점검후 시험가압","2020-02-21 09:00","2020-02-21 18:00","2020-02-21 09:00","2020-02-21 18:00","연속"]
[29,"전북","김제","정공S/S 154kV #60 BUS","KCFT #1 GIS 시험가압","정밀점검 및 KCFT 선로점검후 시험가압","2020-02-21 09:00","2020-02-21 18:00","2020-02-21 09:00","2020-02-21 18:00","연속"]
[30,"광주전남","광주","신광주일곡#2 T/L","신광주S/S 신광주-일곡#2T/L 송전선로 보호반 이동","신광주,일곡S/S 신광주-일곡#2T/L 송전선로 보호반 교체 전 사전 작업(신광주 측 보호반 이동)","2020-02-03 09:00","2020-02-03 18:00","취소","취소","연속"]
[31,"광주전남","광주","신광주일곡#1 T/L","신광주,일곡S/S 신광주-일곡#1T/L 송전선로 보호반 교체","신광주,일곡S/S 신광주-일곡#1T/L 송전선로 보호반 교체 신광주S/S 신광주-일곡#1T/L GIS 하자점검 신광주S/S 신광주-일곡#1T/L LA C상 절연 볼트 불량 관련 점검","2020-02-04 09:00","2020-02-06 18:00","취소","취소","연속"]
[32,"광주전남","광주","신광주일곡#2 T/L","신광주,일곡S/S 신광주-일곡#2T/L 송전선로 보호반 교체","신광주,일곡S/S 신광주-일곡#2T/L 송전선로 보호반 교체 신광주S/S 신광주-일곡#2T/L GIS 하자점검","2020-02-10 09:00","2020-02-12 18:00","취소","취소","연속"]
[33,"대구","경산","경산자인#1 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 신경산-대구 No.3~6 - No.5 본선로 구성","2020-02-07 08:00","2020-02-16 18:00","2020-02-07 08:00","2020-02-16 18:00","연속"]
[34,"대구","경산","경산자인#2 T/L","345kV 울주-신경산 등 5개T/L 지장송전선로 이설공사","○ 345kV 신경산-대구 No.3~6 - No.5 본선로 구성","2020-02-17 08:00","2020-02-26 18:00","2020-02-17 08:00","2020-02-26 18:00","연속"]
[35,"대구","경산","노변효목#1 T/L","154kV 시지분기 지중T/L 건설공사","노변효목T/L M/H#3,4 ~ 시지E/C구간 2파이 분기,XLPE2,000 *4C*0.24km","2020-02-17 09:00","2020-04-10 18:00","취소","취소","연속"]
[36,"대구","달성","현풍유가#1 T/L","유가S/S 현풍유가#1T/L 유압펌프 교체작업","유가S/S 현풍유가#1T/L 유압펌프 교체작업","2020-02-19 09:00","2020-02-19 18:00","2020-02-19 09:00","2020-02-19 18:00","연속"]
[37,"대구","직할","노변효목#2 T/L","효목S/S 노변-효목#2 전자변 교체 등","효목S/S 노변-효목#2 전자변 교체, 차단기 동작시험","2020-02-13 09:30","2020-02-13 18:00","2020-02-27 09:30","2020-02-27 18:00","연속"]
[38,"부산울산","동부산","신양산수영#2 T/L","[1차] 345kV 신양산S/S 현대화공사","1. 내용 - 신양산-북부산#2T/L 제어케이블 이설 - 345kV #2M.Tr 및 1,2,3차 제어케이블 이설 - 345kV #2M.Tr 2차 인출변경 - 154kV 신양산-수영#2T/L 인출변경 2. 선로 이설 후 - 신규 GIS 시험가압(24H)","2020-02-24 09:00","2020-03-10 18:00","2020-02-24 09:00","2020-03-10 18:00","연속"]
[39,"부산울산","서부산","서부산다대#1 T/L","154kV 서부산-다대T/L 지장이설 및 선종교체공사","선로명 : 154kV 서부산-다대#1T/L 구 간 : J/B#2 ~ J/B#5 (1.01km) 작업내용 : 을숙도대교-장림고개간 지하차도건설공사에 따른 지장이설 및 케이블 선종교체","2020-02-03 09:00","2020-04-03 18:00","2020-02-03 09:00","2020-04-03 18:00","연속"]
[40,"부산울산","울산","두왕영남TP#2 T/L","154kV 울산분기T/L 건설공사","○ 구간 : 154kV 두왕-영남TP T/L No.20∼No.21(CH), No.26(CH)∼No.28 ○ 지지물 : C/H 철탑 2기 ○ 전력선 : HSTACIR/AW 410㎟×S×2C - 0.432km ○ 현 휴전작업 공사개요 : 기설 두왕-영남TP T/L No.21, No.26 철거 후 C/H 신설을 위한 가선로 구성","2020-02-28 07:00","2020-03-01 18:00","2020-02-28 07:00","2020-03-01 18:00","연속"]
[41,"부산울산","울산","신울산울산#2 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-02-26 07:00","2020-02-27 18:00","취소","취소","연속"]
[42,"부산울산","울산","신울산울산#1 T/L","154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사","1) 154㎸ 신울산-울산T/L ○ 철탑교체 : 2기(No.12, 13) ○ 전선 교체 : 11∼14호[0.945C-km, HSTACIR/AW 330㎟] 2) 154㎸ 두왕-영남TPT/L ○ 철탑교체 : 2기( No.29, 30) ○ 전선 교체 : 28∼31호[0.585C-km, HSTACIR/AW 410㎟]","2020-02-24 07:00","2020-02-25 18:00","취소","취소","연속"]
[43,"부산울산","울산","신울산두왕#2 T/L","2019년도 가공송전 순시점검 위탁공사","1) 정밀점검 ○ 154kV 신울산-두왕#2T/L No.2~6(5기) ○ 병가선로 휴전 - 공사명 : 154㎸ 신울산-울산 등 2개T/L 지장송전선로 이설공사 - 휴전설비 : 154kV 신울산-울산#2T/L (2/26~27)","2020-02-26 07:00","2020-02-26 18:00","2020-02-26 07:00","2020-02-26 18:00","연속"]
[44,"부산울산","울산","신울산웅촌#2 T/L","2020년 울산전력지사 170kV 개폐장치 정밀점검공사","- 154kV #2Sh.C MAIN GIS 정밀점검 후 시험가압선로 1H","2020-02-06 17:00","2020-02-06 18:00","2020-02-06 17:00","2020-02-06 18:00","연속"]
[45,"부산울산","울산","신울산웅촌#1 T/L","2020년 울산전력지사 170kV 개폐장치 정밀점검공사","- 154kV #1Sh.C MAIN GIS 정밀점검 후 시험가압선로 1H","2020-02-04 17:00","2020-02-04 18:00","2020-02-04 17:00","2020-02-04 18:00","연속"]
[46,"경남","직할","천선S/S 154kV #65-#66 SEC CB","천선S/S 65-66 BUS-SEC CB 조작시험 점검","천선S/S 65-66 BUS-SEC CB 조작시험 점검","2020-02-25 13:30","2020-02-25 17:30","2020-02-25 13:30","2020-02-25 17:30","연속"]
[47,"경남","직할","천선S/S 154kV #61-#66 BUS TIE CB","천선S/S #1,2 BUS-TIE CB 조작시험 점검","천선S/S #1,2 BUS-TIE CB 조작시험 점검","2020-02-24 13:30","2020-02-24 17:30","2020-02-24 13:30","2020-02-24 17:30","연속"]
[48,"경남","직할","천선S/S 154kV #60-#61 SEC CB","천선S/S #60-61,#65-66 BUS-TIE CB 조작시험 점검","천선S/S #60-61,#65-66 BUS-TIE CB 조작시험 점검","2020-02-25 09:30","2020-02-25 13:30","2020-02-25 09:30","2020-02-25 13:30","연속"]
[49,"경남","직할","천선S/S 154kV #61-#66 BUS TIE CB","천선S/S #60-61,#65-66 BUS-TIE CB 조작시험 점검","천선S/S #60-61,#65-66 BUS-TIE CB 조작시험 점검","2020-02-25 13:30","2020-02-25 17:30","취소","취소","연속"]
[50,"경남","직할","천선S/S 154kV #60-#65 BUS TIE CB","천선S/S #1,2 BUS-TIE CB 조작시험 점검","천선S/S #1,2 BUS-TIE CB 조작시험 점검","2020-02-24 09:30","2020-02-24 13:30","2020-02-24 09:30","2020-02-24 13:30","연속"]

{"sheet":"시송전설비","index":3,"n_rows":1,"n_cols":17,"rows_kept":1,"cut":false,"hidden":true,"merged":[[0,16,0,21]]}
["1차\n사업소","2차\n사업소","설비명",{"$nulls":8},"연간\n반영","비고","Key-point","시송전설비 여부","찾는함수","=IF(ISERROR(VLOOKUP(D5,시송전설비!$C$2:$O$130,13,0)),\"-\",VLOOKUP(D5,시송전설비!$C$2:$O$130,13,0))"]