{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":9,"n_cols":11,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 3월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신태백신가평#1 T/L","22~23년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 신가평S/S 765kV #84BAY B/F보호반 교체","2022-03-18 09:00","2022-03-28 18:00","2022-03-18 09:00","2022-03-28 18:00","연속"]
[2,"경기북부","구리","신가평S/S #3 M.Tr","22~23년 구리전력지사 변전정비회사 총액공사","장기사용 배전반 교체공사 - 신가평S/S 765kV #84BAY B/F보호반 교체","2022-03-18 09:00","2022-03-28 18:00","2022-03-18 09:00","2022-03-28 18:00","연속"]
[3,"강원","태백","신태백S/S #4 M.Tr","22-23년 태백전력지사 변전정비회사 총액공사","신태백S/S 765kV 85Bay B/F PNL 교체 [병행] 신태백S/S #4M.Tr 보통점검(3/18~4/1)","2022-03-18 09:00","2022-04-01 18:00","2022-03-18 09:00","2022-04-01 18:00","연속"]
[4,"충북","직할","신중부신안성#1 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","항공장애표시구 교체 (3경간)","2022-03-19 07:30","2022-03-20 18:00","취소","취소","매일"]
[5,"충북","직할","신중부S/S CB 8571","신중부변전소 765kV GIS 하자보수 공사","현대제 765kV GIS 지락고장 방지를 위한 내부부품 교체","2022-03-28 09:00","2022-04-01 18:00","2022-03-28 09:00","2022-04-01 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":299,"n_cols":11,"rows_kept":299,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 3월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S #3 M.Tr","'22-23 중부P/O 변전협력회사 총액공사","1차 GIS 보통점검","2022-03-25 09:00","2022-03-25 18:00","2022-03-25 09:00","2022-03-25 18:00","연속"]
[2,"서울","중부","중부S/S #1 M.Tr","'22-23 중부P/O 변전협력회사 총액공사","주변압기 보통점검(A, C상) 주변압기 하자점검(B상)","2022-03-15 09:00","2022-03-16 18:00","2022-03-15 09:00","2022-03-16 18:00","연속"]
[3,"서울","중부","중부S/S #4 M.Tr","'22-23 중부P/O 변전협력회사 총액공사","주변압기 초기점검 3차 PT, LA 초기점검 1차 GIS 및 PT 초기점검 2차 GIS 초기점검","2022-03-17 09:00","2022-03-18 18:00","2022-03-17 09:00","2022-03-18 18:00","연속"]
[4,"서울","중부","중부S/S #2 M.Tr","'22-23 중부P/O 변전협력회사 총액공사","1차 GIS 보통점검","2022-03-24 09:00","2022-03-24 18:00","2022-03-24 09:00","2022-03-24 18:00","연속"]
[5,"남서울","동서울","동서울S/S #4 M.Tr","동서울S/S 노후 주변압기 교체 및 이설공사","○ 345kV 주변압기 11대 교체 및 이설","2022-03-02 09:00","2022-04-08 18:00","2022-03-02 09:00","2022-04-08 18:00","연속"]
[6,"남서울","영등포","신광명신문래#2 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2022-03-24 10:00","2022-06-28 18:00","2022-03-24 10:00","2022-06-28 18:00","연속"]
[7,"남서울","영등포","신광명S/S #75 BUS","345kV 신광명S/S GIS 용량대체공사","- 345kV 63kA GIS 24CB 설치","2022-03-19 09:00","2022-03-21 14:00","2022-03-19 09:00","2022-03-21 14:00","연속"]
[8,"남서울","영등포","신광명S/S #3 M.Tr","345kV 신광명S/S 노후 변압기 교체공사(소내이설)","#2S.TR 전원부 전력케이블 포설 소내이설(#4M.Tr -> #3M.Tr)","2022-03-31 09:00","2022-04-01 18:00","2022-03-31 09:00","2022-04-01 18:00","연속"]
[9,"남서울","영등포","신광명S/S #70 BUS","345kV 신광명S/S GIS 용량대체공사","- 345kV 63kA GIS 24CB 설치","2022-03-21 14:00","2022-03-23 18:00","2022-03-21 14:00","2022-03-23 18:00","연속"]
[10,"인천","부평","서인천C/C #2 Sh.R (CB 7479)","서인천C/C 345kV #2 Sh.R 하자점검","서인천C/C 345kV #2 Sh.R 하자점검","2022-03-03 09:00","2022-03-03 18:00","2022-03-03 09:00","2022-03-03 18:00","연속"]
[11,"인천","부평","서인천C/C CB 7100","서인천S/Y 7100GIS 조작시험","서인천S/Y 7100GIS 조작시험","2022-03-07 09:00","2022-03-07 12:00","취소","취소","연속"]
[12,"인천","부평","서인천C/C CB 7171","서인천S/Y 7171GIS 조작시험","서인천S/Y 7171GIS 조작시험","2022-03-07 12:00","2022-03-07 15:00","취소","취소","연속"]
[13,"인천","부평","서인천C/C CB 7172","서인천S/Y 7172GIS 조작시험","서인천S/Y 7172GIS 조작시험","2022-03-07 15:00","2022-03-07 18:00","취소","취소","연속"]
[14,"인천","부평","서인천C/C #2 Sh.R (CB 7479)","서인천C/C 345kV #2 Sh.R 제작사 하자보수(절연유 여과)","초기운전 절연유 분석 가스요주의 3회 판명에 의한 제작사 하자보수","2022-03-21 09:00","2022-03-23 18:00","2022-03-21 09:00","2022-03-23 18:00","연속"]
[15,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S #3M.Tr 휴전작업","부싱절연유채유, 7472GIS 보통점검, 7400GIS 조작시험, 6344GIS 조작시험","2022-03-11 09:00","2022-03-11 18:00","2022-03-11 09:00","2022-03-11 18:00","연속"]
[16,"인천","부평","신가좌S/S CB 7471","신가좌S/S 7471GIS 조작시험","신가좌S/S 7471GIS 조작시험","2022-03-03 09:00","2022-03-03 18:00","2022-03-03 09:00","2022-03-03 18:00","연속"]
[17,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S #4M.Tr 휴전작업","부싱절연유채유, 7600, 7672GIS 보통점검, CVT 초기점검","2022-03-14 09:00","2022-03-14 18:00","2022-03-14 09:00","2022-03-14 18:00","연속"]
[18,"인천","부평","인천C/C CB 7500","인천복합S/Y 7500GIS 조작시험","인천복합S/Y 7500GIS 조작시험","2022-03-22 13:00","2022-03-22 18:00","2022-03-22 13:00","2022-03-22 18:00","연속"]
[19,"인천","부평","인천C/C CB 7100","인천복합S/Y 7100GIS 보통점검 및 전자변교체","인천복합S/Y 7100GIS 보통점검 및 전자변교체","2022-03-23 09:00","2022-03-23 18:00","2022-03-23 09:00","2022-03-23 18:00","연속"]
[20,"인천","부평","인천C/C CB 7371","인천복합S/Y 7371GIS 하자점검","인천복합S/Y 7371GIS 하자점검","2022-03-25 09:00","2022-03-25 13:00","2022-03-25 09:00","2022-03-25 13:00","연속"]
[21,"인천","부평","인천C/C CB 7571","인천복합S/Y 7571GIS 조작시험","인천복합S/Y 7571GIS 조작시험","2022-03-25 13:00","2022-03-25 18:00","2022-03-25 13:00","2022-03-25 18:00","연속"]
[22,"인천","부평","인천C/C CB 7171","인천복합S/Y 7171GIS 보통점검 및 전자변교체","인천복합S/Y 7171GIS 보통점검 및 전자변교체","2022-03-31 09:00","2022-03-31 18:00","2022-03-31 09:00","2022-03-31 18:00","연속"]
[23,"인천","부평","인천C/C #2 Sh.R (CB 7379)","인천C/C 345kV #2 Sh.R 하자점검","인천C/C 345kV #2 Sh.R 하자점검 -7379GIS 하자점검","2022-03-07 09:00","2022-03-07 18:00","2022-03-07 09:00","2022-03-07 18:00","연속"]
[24,"인천","부평","인천C/C CB 7272","인천복합S/Y 7272GIS 하자점검","인천복합S/Y 7272GIS 하자점검","2022-03-22 09:00","2022-03-22 13:00","2022-03-22 09:00","2022-03-22 13:00","연속"]
[25,"인천","부평","인천C/C CB 7400","인천복합S/Y 7400GIS 조작시험","인천복합S/Y 7400GIS 조작시험","2022-03-21 13:00","2022-03-21 18:00","2022-03-21 13:00","2022-03-21 18:00","연속"]
[26,"인천","부평","인천C/C CB 7200","인천복합S/Y 7200GIS 보통점검","인천복합S/Y 7200GIS 보통점검","2022-03-21 09:00","2022-03-21 13:00","2022-03-21 09:00","2022-03-21 13:00","연속"]
[27,"인천","부평","인천C/C #76 BUS","인천복합S/Y 345kV 76BUS 모선보호반 교체","인천복합S/Y 345kV 76BUS 모선보호반 교체","2022-03-14 09:00","2022-03-18 18:00","2022-03-14 09:00","2022-03-18 18:00","연속"]
[28,"인천","부평","신경서인천CC#1 T/L","신경서인천CC #1T/L 7221(인출DS) 가스누기 보수","신경서인천CC #1T/L 7221(인출DS) 가스누기 보수","2022-03-10 09:00","2022-03-11 18:00","2022-03-10 09:00","2022-03-11 18:00","연속"]
[29,"인천","부평","인천C/C #1 Sh.R (CB 7279)","인천C/C 345kV #1 Sh.R 하자점검","인천C/C 345kV #1 Sh.R 하자점검 -7279GIS 하자점검","2022-03-02 09:00","2022-03-02 18:00","2022-03-02 09:00","2022-03-02 18:00","연속"]
[30,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥#1S/S 345kV #3 M.Tr 보통점검","신시흥#1S/S 345kV #3 M.Tr 보통점검","2022-03-21 09:00","2022-03-24 18:00","2022-03-21 09:00","2022-03-24 18:00","연속"]
[31,"인천","시흥","신시흥#1S/S CB 7771","신시흥#1S/S 345kV 7771 GIS 보통점검","신시흥#1S/S 345kV 7771 GIS 보통점검","2022-03-07 09:00","2022-03-07 18:00","2022-03-07 09:00","2022-03-07 18:00","연속"]
[32,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥#1S/S 345kV #1 M.Tr 보통점검","신시흥#1S/S 345kV #1 M.Tr 보통점검","2022-03-28 09:00","2022-03-31 18:00","2022-03-28 09:00","2022-03-31 18:00","연속"]
[33,"인천","시흥","영흥T/P CB 7571","영흥T/P 345kV 7571 GIS 보통점검","영흥T/P 345kV 7571 GIS 보통점검","2022-03-08 09:00","2022-03-08 18:00","2022-03-08 09:00","2022-03-08 18:00","연속"]
[34,"인천","시흥","영흥T/P CB 7472","영흥T/P 345kV 7472 GIS 보통점검","영흥T/P 345kV 7472 GIS 보통점검","2022-03-17 09:00","2022-03-17 18:00","2022-03-17 09:00","2022-03-17 18:00","연속"]
[35,"인천","시흥","영흥T/P CB 7471","영흥T/P 345kV 7471 GIS 보통점검","영흥T/P 345kV 7471 GIS 보통점검","2022-03-16 09:00","2022-03-16 18:00","2022-03-16 09:00","2022-03-16 18:00","연속"]
[36,"인천","시흥","영흥T/P CB 7572","영흥T/P 345kV 7572 GIS 보통점검","영흥T/P 345kV 7572 GIS 보통점검","2022-03-18 09:00","2022-03-18 18:00","2022-03-18 09:00","2022-03-18 18:00","연속"]
[37,"인천","직할","갈산S/S CB 7571","갈산S/S 갈산신광명#3TL 7571 GIS하자점검","갈산S/S 갈산신광명#3TL 7571 GIS하자점검","2022-03-15 09:30","2022-03-15 18:00","2022-03-15 09:30","2022-03-15 18:00","연속"]
[38,"인천","직할","갈산S/S #2 M.Tr","갈산S/S #2M.Tr 변압기, 1,2차 GIS하자점검","갈산S/S #2M.Tr 변압기, 1,2차 GIS하자점검","2022-03-16 09:30","2022-03-18 18:00","2022-03-16 09:30","2022-03-18 18:00","연속"]
[39,"인천","직할","갈산S/S #3 M.Tr","갈산S/S #3M.Tr 변압기, 1,2차 GIS하자점검","갈산S/S #3M.Tr 변압기, 1,2차 GIS하자점검","2022-03-28 09:30","2022-03-30 18:00","2022-03-28 09:30","2022-03-30 18:00","연속"]
[40,"인천","직할","갈산S/S CB 7471","갈산S/S 가정갈산#3TL 7471 GIS하자점검","갈산S/S 가정갈산#3TL 7471 GIS하자점검","2022-03-14 09:30","2022-03-14 18:00","2022-03-14 09:30","2022-03-14 18:00","연속"]
[41,"인천","직할","갈산S/S CB 7171","갈산S/S 가정갈산#1TL 7171 GIS하자점검","갈산S/S 가정갈산#1TL 7171 GIS하자점검","2022-03-10 09:30","2022-03-10 18:00","2022-03-10 09:30","2022-03-10 18:00","연속"]
[42,"인천","직할","갈산S/S CB 7172","갈산S/S 갈산신광명#1TL 7172 GIS하자점검","갈산S/S 갈산신광명#1TL 7172 GIS하자점검","2022-03-07 09:30","2022-03-07 18:00","2022-03-07 09:30","2022-03-07 18:00","연속"]
[43,"인천","직할","갈산S/S CB 7371","갈산S/S 갈산신광명#2TL 7371 GIS하자점검","갈산S/S 갈산신광명#2TL 7371 GIS하자점검","2022-03-08 09:30","2022-03-08 18:00","2022-03-08 09:30","2022-03-08 18:00","연속"]
[44,"인천","직할","갈산S/S CB 7271","갈산S/S 가정갈산#2TL 7271 GIS하자점검","갈산S/S 가정갈산#2TL 7271 GIS하자점검","2022-03-11 09:30","2022-03-11 18:00","2022-03-11 09:30","2022-03-11 18:00","연속"]
[45,"경기북부","고양","신파주신덕은#1 T/L","362kV GIS 보통점검 및 유사고장 방지 - 총액","신파주S/S 7171 GIS 보통점검 신덕은S/S 신파주-신덕은#1T/L 재폐로 결상 회로 개선","2022-03-14 09:00","2022-03-15 18:00","2022-03-14 09:00","2022-03-15 18:00","연속"]
[46,"경기북부","구리","미금S/S #1 Sh.R (CB 7179)","구리전력지사 345kV GIS 점검","구리전력지사 345kV GIS 점검","2022-03-14 09:00","2022-03-14 18:00","2022-03-14 09:00","2022-03-14 18:00","연속"]
[47,"경기북부","구리","미금S/S #3 Sh.R (CB 7379)","구리전력지사 345kV GIS 점검","구리전력지사 345kV GIS 점검","2022-03-15 09:00","2022-03-15 18:00","2022-03-15 09:00","2022-03-15 18:00","연속"]
[48,"경기북부","구리","미금S/S CB 7172","미금SS 7172CB C상 Trip라인 회로점검","미금SS 7172CB C상 Trip라인 회로점검","2022-03-03 09:00","2022-03-03 18:00","2022-03-03 09:00","2022-03-03 18:00","연속"]
[49,"경기북부","구리","미금S/S #6 Sh.R (CB 7679)","구리전력지사 345kV GIS 점검","구리전력지사 345kV GIS 점검","2022-03-22 09:00","2022-03-22 18:00","2022-03-22 09:00","2022-03-22 18:00","연속"]
[50,"경기북부","구리","미금S/S #4 Sh.R (CB 7479)","구리전력지사 345kV GIS 점검","구리전력지사 345kV GIS 점검","2022-03-21 09:00","2022-03-21 18:00","2022-03-21 09:00","2022-03-21 18:00","연속"]
[51,"경기북부","구리","미금S/S #5 Sh.R (CB 7579)","구리전력지사 345kV GIS 점검","구리전력지사 345kV GIS 점검","2022-03-17 09:00","2022-03-17 18:00","2022-03-17 09:00","2022-03-17 18:00","연속"]
[52,"경기북부","구리","미금성동#1 T/L","345kV 미금S/S 용량부족 차단기 대체공사","71BAY GIS 용량대체(50kA→63kA)","2022-03-28 09:00","2022-06-14 18:00","2022-03-28 09:00","2022-06-14 18:00","연속"]
[53,"경기북부","구리","미금S/S #1 M.Tr","345kV 미금S/S 용량부족 차단기 대체공사","71BAY GIS 용량대체(50kA→63kA)","2022-03-28 09:00","2022-06-14 18:00","2022-03-28 09:00","2022-06-14 18:00","연속"]
[54,"경기북부","구리","신가평미금#1 T/L","345kV 신가평-미금T/L EB-A 자기애관 교체공사","○ EB-A 애관 교체 (자기제 → 폴리머제) ○ 신미#1C/T 6상 및 신미#2C/T 6상","2022-03-14 08:00","2022-03-25 18:00","2022-03-14 08:00","2022-03-25 18:00","연속"]
[55,"경기북부","구리","포천C/C CB 7171","포천CC 차단기 조작로드 교체공사","포천CC 차단기 조작로드 교체공사","2022-03-14 09:00","2022-03-18 18:00","2022-03-14 09:00","2022-03-18 18:00","연속"]
[56,"경기북부","구리","포천C/C CB 7271","포천CC 차단기 조작로드 교체공사","포천CC 차단기 조작로드 교체공사","2022-03-21 09:00","2022-03-25 18:00","2022-03-21 09:00","2022-03-25 18:00","연속"]
[57,"경기북부","직할","신의정부S/S #1 M.Tr","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7200, 7272 보통점검","2022-03-23 09:00","2022-03-24 18:00","2022-03-23 09:00","2022-03-24 18:00","연속"]
[58,"경기북부","직할","신의정부S/S CB 7472","22-23년 직할 변전정비회사 총액공사","신의정부S/S 345kV #1Sh.R 보통점검","2022-03-17 09:00","2022-03-18 18:00","2022-03-17 09:00","2022-03-18 18:00","연속"]
[59,"경기북부","직할","신의정부S/S #4 M.Tr","22-23년 직할 변전정비회사 총액공사","신의정부S/S 345kV #4M.Tr A,B상 보통점검","2022-03-14 09:00","2022-03-16 18:00","2022-03-14 09:00","2022-03-16 18:00","연속"]
[60,"경기북부","직할","신의정부S/S #1 Sh.R (CB 7479)","22-23년 직할 변전정비회사 총액공사","신의정부S/S 345kV #1Sh.R 보통점검","2022-03-17 09:00","2022-03-18 18:00","2022-03-17 09:00","2022-03-18 18:00","연속"]
[61,"경기북부","직할","신의정부S/S #3 M.Tr","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7500, 7572 CB 보통점검","2022-03-21 09:00","2022-03-22 18:00","2022-03-21 09:00","2022-03-22 18:00","연속"]
[62,"경기북부","직할","신의정부S/S CB 7400","22-23년 직할 변전정비회사 총액공사","신의정부S/S 345kV #1Sh.R 보통점검","2022-03-17 09:00","2022-03-18 18:00","2022-03-17 09:00","2022-03-18 18:00","연속"]
[63,"경기북부","직할","신파주양주#1 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","양주S/S 362kV GIS 7300, 7371 CB 조작시험 및 7301 DS 결상 점검","2022-03-25 09:00","2022-03-25 18:00","2022-03-25 09:00","2022-03-25 18:00","연속"]
[64,"경기북부","직할","신파주양주#2 T/L","양주S/S 362kV GIS PT 노후 대체공사 시행","- 362kV GIS #1BUS PT 노후 대체 시 안전 이격거리 확보","2022-03-14 09:00","2022-03-17 18:00","2022-03-14 09:00","2022-03-17 18:00","매일"]
[65,"경기북부","직할","양주S/S #1 BUS","양주S/S 362kV GIS PT 노후 대체공사","- 내용년수 초과 #1BUS GIS PT 대체","2022-03-14 08:00","2022-03-18 18:00","2022-03-14 08:00","2022-03-18 18:00","연속"]
[66,"경기북부","직할","양주중부#1 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","양주S/S 362kV GIS 7571, 7500 CB 보통점검","2022-03-28 09:00","2022-03-29 18:00","2022-03-28 09:00","2022-03-29 18:00","연속"]
[67,"경기북부","직할","양주중부#2 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","양주S/S 362kV GIS 7671, 7600 CB 보통점검","2022-03-30 09:00","2022-03-31 18:00","2022-03-30 09:00","2022-03-31 18:00","연속"]
[68,"경기북부","구리","미금S/S #2 M.Tr"," 2022~23 구리전력 변전협력 총액공사"," 미금S/S 345kV #2M.Tr 보통점검, H0부싱 교체","2022-03-14 09:00","2022-03-18 18:00","2022-03-14 09:00","2022-03-18 18:00","연속"]
[69,"경기","군포","서서울#2S/S CB 7C00","서서울2S/S 서서울2-화성#1T/L(7C00) GIS 보통점검","서서울2S/S 서서울2-화성#1T/L(7C00) GIS 보통점검","2022-03-21 09:00","2022-03-21 18:00","2022-03-21 09:00","2022-03-21 18:00","연속"]
[70,"경기","군포","서서울#2S/S CB 7D72","서서울2S/S 서서울2-신시흥#1T/L GIS 보통점검","서서울2S/S 서서울2-신시흥#1T/L GIS(7D72) 보통점검","2022-03-31 09:00","2022-03-31 18:00","2022-03-31 09:00","2022-03-31 18:00","연속"]
[71,"경기","군포","서서울#2S/S CB 7D71","서서울2S/S 서서울2-화성#2T/L(7D71) GIS 보통점검","서서울2S/S 서서울2-화성#2T/L(7D71) GIS 보통점검","2022-03-22 09:00","2022-03-22 18:00","2022-03-22 09:00","2022-03-22 18:00","연속"]
[72,"경기","군포","서서울#2신성남#1 T/L","서서울2S/S 서서울2-신성남#1T/L GIS 보통점검","서서울2-신성남#1T/L GIS (7A71,7A00) 보통점검","2022-03-17 09:00","2022-03-17 18:00","취소","취소","연속"]
[73,"경기","군포","서서울#2신성남#2 T/L","서서울2S/S 서서울2-신성남#2T/L GIS 보통점검","서서울2-신성남#2T/L GIS (7B71,7B00) 보통점검","2022-03-18 09:00","2022-03-18 18:00","취소","취소","연속"]
[74,"경기","군포","서서울#2S/S CB 7C72","서서울2S/S 서서울2-신시흥#2T/L GIS 보통점검","서서울2S/S 서서울2-신시흥#2T/L GIS(7C72) 보통점검","2022-03-23 09:00","2022-03-23 18:00","2022-03-23 09:00","2022-03-23 18:00","연속"]
[75,"경기","군포","서서울#2S/S CB 7C71","서서울2S/S 서서울2-화성#1T/L(7C71) GIS 보통점검","서서울2S/S 서서울2-화성#1T/L(7C71) GIS 보통점검","2022-03-21 09:00","2022-03-21 18:00","2022-03-21 09:00","2022-03-21 18:00","연속"]
[76,"경기","군포","서서울#2S/S CB 7D00","서서울2S/S 서서울2-화성#2T/L(7D00) GIS 보통점검","서서울2S/S 서서울2-화성#2T/L(7D00) GIS 보통점검","2022-03-22 09:00","2022-03-22 18:00","2022-03-22 09:00","2022-03-22 18:00","연속"]
[77,"경기","군포","신온양서서울#2 T/L","서서울S/S 서서울-신온양#2T/L(7772,7700) GIS 보통 등","서서울S/S 서서울-신온양#2T/L(7772,7700) GIS 보통,PT보통, 결상회로개선","2022-03-25 09:00","2022-03-25 18:00","취소","취소","연속"]
[78,"경기","군포","신온양서서울#1 T/L","서서울S/S 서서울-신온양#1T/L(7472,7400) GIS 보통 등","서서울S/S 서서울-신온양#1T/L(7472,7400) GIS 보통,PT보통, 결상회로개선","2022-03-24 09:00","2022-03-24 18:00","취소","취소","연속"]
[79,"경기","군포","서서울S/S #4 M.Tr","서서울SS #4M.Tr 누유 점검, 1차 GIS 보통(7800,7872)","서서울SS #4M.Tr 누유 점검,1차 GIS 보통(7800,7872)","2022-03-03 09:00","2022-03-03 18:00","2022-03-03 09:00","2022-03-03 18:00","연속"]
[80,"경기","동부","곤지암S/S CB 7600","곤지암S/S 345kV 차단기 설치공사","7671GIS 인출 GIB 설치","2022-03-02 09:00","2022-03-11 10:00","2022-03-02 09:00","2022-03-11 10:00","연속"]
[81,"경기","동부","곤지암S/S CB 7671","곤지암S/S 345kV 차단기 설치공사","7671GIS 인출 GIB 설치","2022-03-02 09:00","2022-03-11 10:00","2022-03-02 09:00","2022-03-11 10:00","연속"]
[82,"경기","동부","곤지암동서울#2 T/L","곤지암S/S 345kV 차단기 설치공사","무부하 가압 선로","2022-03-10 10:00","2022-03-11 10:00","2022-03-10 10:00","2022-03-11 10:00","연속"]
[83,"경기","동부","곤지암S/S #1 BUS","곤지암S/S 345kV 차단기 설치공사","무부하 가압","2022-03-10 10:00","2022-03-11 10:00","2022-03-10 10:00","2022-03-11 10:00","연속"]
[84,"경기","동부","곤지암신충주#2 T/L","22년 동부 변전정비 총액공사","곤지암:7171(조작),7100(조작)(동시) [성능개선:결상회로개선]","2022-03-14 09:30","2022-03-14 18:00","취소","취소","연속"]
[85,"경기","동부","곤지암신충주#2 T/L","22년 동부 변전정비 총액공사","곤지암:7171(조작),7100(조작)(동시) [성능개선:결상회로개선]","2022-03-14 09:30","2022-03-14 18:00","취소","취소","연속"]
[86,"경기","동부","곤지암신충주#1 T/L","22년 동부 변전정비 총액공사","곤지암:7271(조작),7200(조작)(동시) [성능개선:결상회로개선]","2022-03-15 09:30","2022-03-15 18:00","취소","취소","연속"]
[87,"경기","동부","곤지암신충주#1 T/L","22년 동부 변전정비 총액공사","곤지암:7271(조작),7200(조작)(동시) [성능개선:결상회로개선]","2022-03-15 09:30","2022-03-15 18:00","취소","취소","연속"]
[88,"경기","동부","곤지암동서울#1 T/L","22년 동부 변전정비 총액공사","곤지암:7371(조작,전자변교체(I)) 7300(조작)(동시) [성능개선:결상회로개선]","2022-03-16 09:30","2022-03-16 18:00","2022-03-16 09:30","2022-03-16 18:00","연속"]
[89,"경기","동부","곤지암동서울#1 T/L","22년 동부 변전정비 총액공사","곤지암:7371(조작,전자변교체(I)) 7300(조작)(동시) [성능개선:결상회로개선]","2022-03-16 09:30","2022-03-16 18:00","취소","취소","연속"]
[90,"경기","동부","곤지암동서울#2 T/L","22년 동부 변전정비 총액공사","곤지암:7400(조작),7471(조작)(동시) [성능개선:결상회로개선]","2022-03-17 09:30","2022-03-17 18:00","2022-03-17 09:30","2022-03-17 18:00","연속"]
[91,"경기","동부","곤지암동서울#2 T/L","22년 동부 변전정비 총액공사","곤지암:7400(조작),7471(조작)(동시) [성능개선:결상회로개선]","2022-03-17 09:30","2022-03-17 18:00","취소","취소","연속"]
[92,"경기","성남","신성남S/S #3 M.Tr","22년 성남전력지사 변전정비회사 총액공사","- M.Tr,NGR 보통점검 - 7372 조작시험 - 1,2,3차 LA 보통점검 - 3차 모선 보통점검 - 3차 PT 보통점검 - C상 H1 부싱 교체, 모선환원","2022-03-14 09:00","2022-03-18 18:00","2022-03-14 09:00","2022-03-18 18:00","연속"]
[93,"경기","성남","신수원S/S #1 M.Tr","22년 성남전력지사 변전정비회사 총액공사","- M.Tr,NGR 보통점검 - 7172 하자점검 - CVT 초기점검 - 2차 GIS 조작시험 - 3차 GIS 보통점검 - 3차 모선 보통점검 - 2차 LA 보통점검","2022-03-16 09:00","2022-03-17 18:00","2022-03-16 09:00","2022-03-17 18:00","연속"]
[94,"경기","성남","신수원S/S #2 M.Tr","22년 성남전력지사 변전정비회사 총액공사","- M.Tr,NGR 보통점검 - 7272 하자점검 - 2차 GIS 조작시험 - 3차 GIS 보통점검 - CVT 초기점검 - 3차 모선 보통점검 - 2차 LA 보통점검","2022-03-23 09:00","2022-03-24 18:00","2022-03-23 09:00","2022-03-24 18:00","연속"]
[95,"경기","성남","신안성신수원#1 T/L","22년 성남전력지사 변전정비회사 총액공사","-7900,7971 보통점검 - LA 보통점검","2022-03-22 09:00","2022-03-22 18:00","2022-03-22 09:00","2022-03-22 18:00","연속"]
[96,"경기","성남","신안성S/S #5 Sh.R (CB 7779)","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검(7771,7779) - #1 Group 불량 FAN 철거","2022-03-08 09:00","2022-03-08 18:00","2022-03-08 09:00","2022-03-08 18:00","연속"]
[97,"경기","성남","신용인신수원 T/L","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검(7771,7700)","2022-03-15 09:00","2022-03-15 18:00","2022-03-15 09:00","2022-03-15 18:00","연속"]
[98,"경기","직할","화성서서울#2 T/L","345kV 화성S/S GIS 용량대체공사","화성서서울#2TL 72-&gt75Bay 환원","2022-03-10 08:00","2022-03-29 18:00","2022-03-10 08:00","2022-03-29 18:00","연속"]
[99,"경기","직할","화성신안산#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","화성S/S 화성-신안산T/L GIS 초기점검","2022-03-10 10:00","2022-03-10 18:00","2022-03-10 10:00","2022-03-10 18:00","연속"]
[100,"경기","직할","화성S/S #70 BUS","345kV 화성S/S GIS 용량대체공사","- 화성서서울#2TL 75 Bay 무부하가압(7571 CB)","2022-03-26 11:00","2022-03-27 11:00","2022-03-26 06:00","2022-03-27 06:00","연속"]
[101,"경기","직할","화성S/S #75 BUS","345kV 화성S/S GIS 용량대체공사","- 화성서서울#2TL 75 Bay 무부하가압(7500CB)","2022-03-27 11:00","2022-03-28 11:00","2022-03-27 06:00","2022-03-28 06:00","연속"]
[102,"경기","직할","아산화성#2 T/L","345kV 화성S/S GIS 용량대체공사","아산화성#2TL 74-&gt72Bay 임시이설","2022-03-29 08:00","2022-04-18 18:00","2022-03-29 08:00","2022-04-18 18:00","연속"]
[103,"경기","직할","화성S/S #2 M.Tr","345kV 화성S/S GIS 용량대체공사","- #3M.TR 1차측 GIS 용량대체(7471 CB)","2022-03-29 09:00","2022-06-28 18:00","2022-03-29 09:00","2022-06-28 18:00","연속"]
[104,"경기","직할","화성S/S #1 M.Tr","345kV 화성S/S GIS 용량대체공사","73,74Bay GIS 용량대체 중 예비M.Tr 모선철거 - 철거중 안전이격거리 확보","2022-03-20 09:00","2022-03-20 18:00","2022-03-20 09:00","2022-03-20 18:00","연속"]
[105,"경기","평택","고덕S/S #4 M.Tr","고덕S/S 345kV #4M.Tr 누유보수","고덕S/S 345kV #4M.Tr C상 상부 누유보수","2022-03-14 10:00","2022-03-14 18:00","2022-03-14 10:00","2022-03-14 18:00","연속"]
[106,"경기","평택","고덕S/S #1 BUS","고덕변전소 2단계 HVDC용 362kV GIS 설치공사","고덕변전소 2단계 HVDC용 362kV GIS 설치공사","2022-03-14 09:00","2022-03-19 18:00","2022-03-14 09:00","2022-03-19 18:00","연속"]
[107,"경기","평택","고덕S/S #2 BUS","고덕변전소 2단계 HVDC용 362kV GIS 설치공사","고덕변전소 2단계 HVDC용 362kV GIS 설치공사","2022-03-21 09:00","2022-03-26 18:00","2022-03-21 09:00","2022-03-26 18:00","연속"]
[108,"강원","강릉","신양양양양PP T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 병가구간 휴전 : 154kV 신양양-인제 #1T/L No.3~6 피뢰기 설치","2022-03-07 07:00","2022-03-07 18:00","취소","취소","연속"]
[109,"강원","강릉","안인개폐소신양양 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 병가구간 휴전 : 154kV 신양양-인제 #2T/L No.3~6 피뢰기 설치","2022-03-06 07:00","2022-03-06 18:00","2022-03-06 07:00","2022-03-06 18:00","연속"]
[110,"강원","동해","신제천동해#1 T/L","2022년 동해전력지사 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2022-03-10 08:00","2022-03-18 18:00","취소","취소","매일"]
[111,"강원","동해","동해S/S #2 BUS","동해S/S 345kV PT 대체공사","1. #2BUS 모선 PT 대체","2022-03-28 09:00","2022-04-01 18:00","2022-03-28 09:00","2022-04-01 18:00","연속"]
[112,"강원","동해","동해안인개폐소#1 T/L","동해S/S 345kV 모선 PT 대체 관련 인근 Bay 휴전","동해S/S 345kV 모선 PT 대체 안전이격 관련 인근 Bay 휴전","2022-03-21 09:00","2022-03-25 18:00","2022-03-21 09:00","2022-03-25 18:00","매일"]
[113,"강원","동해","동해S/S #1 BUS","동해S/S 345kV PT 대체공사","1. 동해S/S 모선 PT 대체","2022-03-21 09:00","2022-03-25 18:00","2022-03-21 09:00","2022-03-25 18:00","연속"]
[114,"강원","동해","신제천동해#2 T/L","2022년 동해전력지사 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2022-03-21 08:00","2022-03-29 18:00","취소","취소","매일"]
[115,"강원","동해","동해북평TP#1 T/L","동해S/S 과부하 방지 회로 구성","1. 동해S/S 과부하 방지 회로 구성","2022-03-17 09:00","2022-03-17 18:00","2022-03-17 09:00","2022-03-17 18:00","연속"]
[116,"강원","동해","동해북평TP#2 T/L","동해S/S 과부하 방지 회로 구성","1. 동해S/S 과부하 방지 회로 구성","2022-03-16 09:00","2022-03-16 18:00","2022-03-16 09:00","2022-03-16 18:00","연속"]
[117,"강원","동해","동해북평TP#3 T/L","동해S/S 과부하 방지 회로 구성","1. 동해S/S 과부하 방지 회로 구성","2022-03-15 09:00","2022-03-15 18:00","2022-03-15 09:00","2022-03-15 18:00","연속"]
[118,"강원","동해","동해S/S #3 M.Tr","동해S/S #3M.Tr 과부하 방지 회로 구성","1. 동해S/S #3M.Tr 과부하 방지 회로 구성","2022-03-14 09:00","2022-03-14 18:00","2022-03-14 09:00","2022-03-14 18:00","연속"]
[119,"강원","태백","신태백S/S #2 Sh.R (CB 7479)","2022년 신태백S/S 345kV #2Sh.R GIS 정밀점검공사","2022년 신태백S/S 345kV #2Sh.R GIS 정밀점검","2022-03-21 10:00","2022-04-01 18:00","2022-03-21 10:00","2022-04-01 18:00","연속"]
[120,"강원","태백","신태백S/S CB 7372","22-23년 태백전력지사 변전정비회사 총액공사","신태백S/S 345kV 신태백-삼척BP#1T/L 보호반 교체공사 [병행] 345kV 7372CB 초기점검(03/15)","2022-03-14 10:00","2022-04-01 18:00","2022-03-14 10:00","2022-04-01 18:00","연속"]
[121,"강원","태백","신태백S/S CB 7471","2022년 신태백S/S 345kV #2Sh.R GIS 정밀점검공사","2022년 신태백S/S 345kV #2Sh.R GIS 정밀점검 [병행] 신태백S/S 345kV 7471CB 초기점검(3/28)","2022-03-21 10:00","2022-04-01 18:00","2022-03-21 10:00","2022-04-01 18:00","연속"]
[122,"강원","태백","신태백S/S CB 7472","22-23년 태백전력지사 변전정비회사 총액공사","신태백S/S 345kV 신태백-삼척BP#2T/L 보호반 교체공사 [병행] 345kV 7472CB 초기점검(03/17)","2022-03-14 10:00","2022-04-01 18:00","2022-03-14 10:00","2022-04-01 18:00","연속"]
[123,"강원","태백","신태백S/S CB 7400","22-23년 태백전력지사 변전정비회사 총액공사","신태백S/S 345kV 신태백-삼척BP#2T/L 보호반 교체공사 [병행] 345kV 7400CB 초기점검(03/16)","2022-03-14 10:00","2022-04-01 18:00","2022-03-14 10:00","2022-04-01 18:00","연속"]
[124,"강원","태백","신태백S/S CB 7300","22-23년 태백전력지사 변전정비회사 총액공사","신태백S/S 345kV 신태백-삼척BP#1T/L 보호반 교체공사 [병행] 345kV 7300CB 초기점검(03/14)","2022-03-14 10:00","2022-04-01 18:00","2022-03-14 10:00","2022-04-01 18:00","연속"]
[125,"충북","청주","남청주S/S #1 BUS","345kV PT/CT집합반 노후교체","[22-23 청주전력 변전정비 총액공사] 345kV PT집합반 및 CT집합반 노후교체","2022-03-16 10:00","2022-03-16 16:00","취소","취소","연속"]
[126,"충북","청주","남청주S/S #2 BUS","345kV PT/CT집합반 노후교체","[22-23 청주전력 변전정비 총액공사] 345kV PT집합반 및 CT집합반 노후교체","2022-03-17 10:00","2022-03-17 16:00","취소","취소","연속"]
[127,"충북","청주","남청주S/S #1 BUS","345kV PT/CT집합반 노후교체","[22-23 청주전력 변전정비 총액공사] 345kV PT집합반 및 CT집합반 노후교체","2022-03-18 10:00","2022-03-18 16:00","취소","취소","연속"]
[128,"충북","청주","남청주S/S #4 M.Tr","변압기보호반 및 B/F반 노후교체","[22-23 청주전력 변전정비 총액공사] 345kV #4M.Tr 보호반 & 78BAY B/F반 노후교체","2022-03-21 10:00","2022-03-25 18:00","취소","취소","연속"]
[129,"충북","청주","세종남청주#2 T/L","추락방지시설 설치공사","1. 공 사 명 : 2022-2023년 청주전력지사 송전협력회사 총액공사 2. 공사장소 : 345kV 세종-남청주T/L No.21, 22 3. 공사내역 : 수평 추락방지시설 설치","2022-03-22 07:00","2022-03-23 18:00","2022-03-22 07:00","2022-03-23 18:00","매일"]
[130,"충북","청주","신옥천S/S #2 M.Tr","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검 및 3차측 모선보강","2022-03-17 10:00","2022-03-18 18:00","2022-03-17 10:00","2022-03-18 18:00","연속"]
[131,"충북","청주","신옥천S/S #1 M.Tr","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검","2022-03-02 10:00","2022-03-02 18:00","2022-03-02 10:00","2022-03-02 18:00","연속"]
[132,"충북","청주","신옥천S/S #3 M.Tr","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검 및 3차측 모선보강","2022-03-07 10:00","2022-03-08 18:00","2022-03-07 10:00","2022-03-08 18:00","연속"]
[133,"충북","청주","신옥천세종#1 T/L","추락방지시설 설치공사","1. 공 사 명 : 2022-2023년 청주전력지사 송전협력회사 총액공사 2. 공사장소 : 345kV 신옥천-세종T/L No.57, 58 3. 공사내역 : 수평 추락방지시설 설치","2022-03-22 07:00","2022-03-23 18:00","2022-03-22 07:00","2022-03-23 18:00","매일"]
[134,"충북","충주","신제천신충주#2 T/L","345kV 신제천-신충주 등 4개 T/L 추락방지시설 설치공사","345kV 신제천-신충주#2 T/L 추락방지시설 설치공사","2022-02-22 07:00","2022-03-17 18:00","2022-02-22 07:00","2022-03-17 18:00","매일"]
[135,"충북","충주","곤지암신충주#1 T/L","345kV 신제천-신충주 등 4개 T/L 추락방지시설 설치공사","345kV 곤지암-신충주#1T/L 추락방지시설 설치공사","2022-03-01 07:00","2022-03-17 18:00","2022-03-01 07:00","2022-03-17 18:00","매일"]
[136,"대전세종충남","대전","신계룡청양 T/L","[송전] 345kV 신옥천-청양 등 2개T/L 추락방지시설 설치공사","[송전] 345kV 신계룡-청양T/L 추락방지시설 설치공사","2022-03-30 08:00","2022-03-30 18:00","2022-03-30 08:00","2022-03-30 18:00","매일"]
[137,"대전세종충남","대전","신옥천신계룡 T/L","[송전] 345kV 신옥천-청양 등 2개T/L 추락방지시설 설치공사","[송전] 345kV 신옥천-신계룡T/L 추락방지시설 설치공사","2022-03-21 08:00","2022-03-29 18:00","2022-03-21 08:00","2022-03-29 18:00","매일"]
[138,"대전세종충남","서산","당진T/P #71 Tie-Tr","당진화력S/S 345kV #71TIE-Tr 1차 LA, CVT 대체","당진화력S/S 345kV #71TIE-Tr 1차 LA, CVT 대체","2022-03-14 10:00","2022-03-18 18:00","취소","취소","연속"]
[139,"대전세종충남","서산","북당진S/S #1 BUS","북당진변전소 2단계 HVDC용 362kV GIS 설치공사","- 북당진S/S 345kV 79, 7A Bay 5CB 증설","2022-03-01 09:00","2022-03-07 18:00","2022-03-01 09:00","2022-03-07 18:00","연속"]
[140,"대전세종충남","서산","북당진S/S #2 BUS","북당진변전소 2단계 HVDC용 362kV GIS 설치공사","- 북당진S/S 345kV 79, 7A Bay 5CB 증설","2022-03-21 09:00","2022-03-27 18:00","2022-03-21 09:00","2022-03-27 18:00","연속"]
[141,"대전세종충남","서산","북당진현대제철 T/L","345kV 신송산분기T/L 건설공사","345kV 현대제철T/L 본선로 구성","2022-03-23 09:00","2022-04-01 18:00","2022-03-23 09:00","2022-04-01 18:00","연속"]
[142,"대전세종충남","서산","신당진개폐소현대제철 T/L","345kV 신송산분기T/L 건설공사","345kV 현대제철T/L 본선로 구성","2022-03-13 09:00","2022-03-22 18:00","2022-03-13 09:00","2022-03-22 18:00","연속"]
[143,"대전세종충남","서산","신당진S/S #1 M.Tr","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -#1M.Tr 2차 교체","2022-03-21 08:00","2022-04-08 18:00","2022-03-21 08:00","2022-04-08 18:00","연속"]
[144,"대전세종충남","서산","신당진S/S #3 M.Tr","22년 서산P/O 170kV GIS 정밀점검","신당진S/S 345kV #3M.Tr 2차 GIS(6344) 정밀점검 (병행) #3M.Tr 1차 GIS 7800, 7872 CB 보통점검","2022-03-14 10:00","2022-03-16 18:00","2022-03-14 10:00","2022-03-16 18:00","연속"]
[145,"대전세종충남","서산","신당진S/S SEC CB 70710","22년도 장기 미동작 차단기 조작시험","신당진S/S 345kV #70-#71 SEC 70-71-0CB 조작시험","2022-03-23 10:00","2022-03-23 14:00","2022-03-23 10:00","2022-03-23 14:00","연속"]
[146,"대전세종충남","서산","신당진S/S CB 7771","22년도 장기 미동작 차단기 조작시험","신당진S/S 345kV 신당진연락#2T/L 7771CB 조작시험","2022-03-23 14:00","2022-03-23 18:00","2022-03-23 14:00","2022-03-23 18:00","연속"]
[147,"대전세종충남","서산","신당진S/S CB 7700","22년도 장기 미동작 차단기 조작시험","신당진S/S 345kV 신당진연락#2-신서산#2T/L TIE 7700CB 조작시험","2022-03-24 10:00","2022-03-24 14:00","2022-03-24 10:00","2022-03-24 14:00","연속"]
[148,"대전세종충남","서산","신당진S/S CB 7772","22년도 장기 미동작 차단기 조작시험","신당진S/S 345kV 신서산-신당진#2T/L 7772CB 조작시험","2022-03-24 14:00","2022-03-24 18:00","2022-03-24 14:00","2022-03-24 18:00","연속"]
[149,"대전세종충남","서산","신서산태안TP#1 T/L","신서산S/S 345kV 신서산-태안화력#1T/L 7662DS 가스누기보수","신서산S/S 345kV 신서산-태안화력#1T/L 7662DS 가스누기 보수공사 - DS부 가스 회수 후 O-ring 교체","2022-03-28 09:00","2022-03-30 18:00","2022-03-28 09:00","2022-03-30 18:00","연속"]
[150,"대전세종충남","서산","태안T/P #1 Tie-Tr","태안T/P 345kV #1M.Tr 1차 PT측 스페이서 교체","태안T/P 345kV #1M.Tr 1차 PT측 스페이서 교체","2022-03-21 10:00","2022-03-25 18:00","2022-03-21 10:00","2022-03-25 18:00","연속"]
[151,"대전세종충남","서산","태안T/P #71 BUS","태안T/P 345kV 71-72-0 SEC CB 조작로드 교체공사","태안T/P 345kV 71-72-0 SEC CB 조작로드 교체공사","2022-03-28 10:00","2022-04-08 18:00","2022-03-28 10:00","2022-04-08 18:00","연속"]
[152,"대전세종충남","서산","태안T/P #76 BUS","태안T/P 345kV #76BUS 보호반 대체","태안T/P 345kV #76BUS 보호반 대체","2022-03-21 10:00","2022-03-25 18:00","2022-03-21 10:00","2022-03-25 18:00","연속"]
[153,"대전세종충남","천안","신온양S/S #1 BUS","신온양S/S 345kV #1BUS(#70) 모선보호반 대체","신온양S/S 345kV #1BUS(#70) 모선보호반 대체","2022-03-29 09:00","2022-04-01 18:00","2022-03-29 09:00","2022-04-01 18:00","연속"]
[154,"대전세종충남","천안","신온양S/S #3 M.Tr","신온양S/S 신온양-한샘#2TL GIS 누기보수","신온양S/S 신온양-한샘#2TL GIS 누기보수","2022-03-21 09:00","2022-03-25 18:00","2022-03-21 09:00","2022-03-25 18:00","연속"]
[155,"대전세종충남","천안","신온양S/S 예비 M.Tr","신온양S/S 345kV 예비변압기 1차 부싱 복구작업","신온양S/S 345kV 예비변압기 1차 부싱 복구작업","2022-03-15 09:00","2022-03-18 18:00","취소","취소","연속"]
[156,"대전세종충남","천안","신온양S/S CB 7700","신온양S/S 345kV 7700CB 개폐타임 측정","신온양S/S 345kV 7700CB 개폐타임 측정","2022-03-02 09:00","2022-03-02 18:00","2022-03-02 09:00","2022-03-02 18:00","연속"]
[157,"대전세종충남","천안","아산S/S #2 M.Tr","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-03-14 09:00","2022-03-17 18:00","2022-03-14 09:00","2022-03-17 18:00","연속"]
[158,"대전세종충남","천안","아산S/S #2 M.Tr","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-03-28 09:00","2022-03-30 18:00","2022-03-28 09:00","2022-03-30 18:00","연속"]
[159,"대전세종충남","천안","아산화성#1 T/L","345kV 아산S/S 취약설비 보강 및 배전반 정비공사","  - (2월취소 재신청) 345kV 집중제어감시반+디지탈축소형모자익 설치 * 1식","2022-03-10 09:00","2022-03-18 18:00","취소","취소","연속"]
[160,"대전세종충남","청양","보령T/P SEC CB 70710","보령T/P 345kV BUS-SEC(70-71-0) GIS 보통점검","보령T/P 345kV BUS-SEC(70-71-0) GIS 보통점검","2022-03-14 09:00","2022-03-14 18:00","2022-03-14 09:00","2022-03-14 18:00","연속"]
[161,"대전세종충남","청양","보령T/P CB 7271","보령T/P 345kV 보령연락T/L(7271) GIS 보통점검","보령T/P 345kV 보령연락T/L(7271) GIS 보통점검","2022-03-28 09:00","2022-03-28 18:00","2022-03-28 09:00","2022-03-28 18:00","연속"]
[162,"대전세종충남","청양","보령T/P SEC CB 75760","보령T/P 345kV BUS-SEC(75-76-0) GIS 보통점검","보령T/P 345kV BUS-SEC(75-76-0) GIS 보통점검","2022-03-15 09:00","2022-03-15 18:00","2022-03-15 09:00","2022-03-15 18:00","연속"]
[163,"대전세종충남","청양","신옥천청양 T/L","[송전] 345kV 신옥천-청양 등 2개T/L 추락방지시설 설치공사","[송전] 345kV 신옥천-청양T/L 추락방지시설 설치공사","2022-03-31 08:00","2022-04-07 18:00","2022-03-31 08:00","2022-04-07 18:00","매일"]
[164,"대전세종충남","청양","청양신탕정#1 T/L","청양S/S 73BAY B/F PNL 및 송전선로 보호반 대체","청양S/S 73BAY B/F PNL 및 송전선로 보호반 대체","2022-03-07 09:00","2022-03-18 18:00","취소","취소","연속"]
[165,"대전세종충남","청양","청양군산#2 T/L","청양S/S 73BAY B/F PNL 대체","청양S/S 73BAY B/F PNL 대체","2022-03-07 09:00","2022-03-18 18:00","취소","취소","연속"]
[166,"대전세종충남","청양","청양군산#1 T/L","[송전] 345kV 청양-군산#1T/L 피뢰기 설치공사","공사내용 : 345kV 청양-군산#1T/L 송전선로용 피뢰기 설치공사 공사구간 : No.62 ~ 178 (117기)","2022-03-21 07:00","2022-03-25 18:00","2022-03-21 07:00","2022-03-25 18:00","매일"]
[167,"전북","군산","군산S/S #2 M.Tr","군산S/S 장기사용 170kV GIS 대체공사2 (시험가압)","- 장기사용 GIS 대체","2022-03-16 18:00","2022-03-17 18:00","취소","취소","연속"]
[168,"전북","군산","군산S/S #1 M.Tr","군산S/S 장기사용 170kV GIS 대체공사2 (시험가압)","- 장기사용 GIS 대체","2022-03-24 18:00","2022-03-25 18:00","취소","취소","연속"]
[169,"전북","군산","군산S/S #1 M.Tr","군산S/S 장기사용 170kV GIS 대체공사1 (시험가압)","- 장기사용 GIS 대체 시험가압 선로","2022-03-16 18:00","2022-03-17 18:00","취소","취소","연속"]
[170,"전북","군산","군산S/S #2 M.Tr","군산S/S 장기사용 170kV GIS 대체공사2 (시험가압)","- 장기사용 GIS 대체","2022-03-24 18:00","2022-03-25 18:00","취소","취소","연속"]
[171,"전북","군산","군산S/S #3 M.Tr","군산S/S #3M.Tr 누유개소 보수공사","군산S/S #3M.Tr 누유개소 보수공사","2022-03-07 09:00","2022-03-08 18:00","2022-03-07 09:00","2022-03-08 18:00","연속"]
[172,"광주전남","광주","신광주S/S #4 M.Tr","22년 광주전력 변전정비회사 총액공사","- 154kV GIS(6444) 보통점검 - 362kV ES 누기 조치 - 362kV GIS 조작시험","2022-03-07 09:00","2022-03-07 18:00","2022-03-10 09:00","2022-03-10 18:00","연속"]
[173,"광주전남","광주","신광주S/S CB 7172","22~23년 광주전력지사 변전협력회사 총액공사(신광주#1M.Tr 1차)","차단기 조작시험 단상 재폐로 회로 보완 및 시험","2022-03-14 09:00","2022-03-14 14:00","2022-03-14 09:00","2022-03-14 14:00","연속"]
[174,"광주전남","광주","신광주S/S CB 7171","22~23년 광주전력지사 변전협력회사 총액공사(신광주-한빛#1T/L)","차단기 조작시험 단상 재폐로 회로 보완 및 시험","2022-03-08 14:00","2022-03-08 18:00","2022-03-15 14:00","2022-03-15 18:00","연속"]
[175,"광주전남","광주","신광주S/S CB 7572","22년 광주전력지사 변전협력회사 총액공사(7572CB 하자점검)","#1Sh.R 1차 (7572CB) 하자점검 - 즉시가압 불가","2022-03-10 09:00","2022-03-10 18:00","2022-03-10 09:00","2022-03-10 18:00","연속"]
[176,"광주전남","광주","신광주S/S #1 Sh.R (CB 7579)","22년 광주전력지사 변전협력회사 총액공사(#1Sh.R 초기점검)","#1Sh.R 초기점검 - 즉시가압 불가","2022-03-10 09:00","2022-03-11 18:00","2022-03-10 09:00","2022-03-11 18:00","연속"]
[177,"광주전남","광주","신광주S/S CB 7500","22년 광주전력지사 변전협력회사 총액공사(7579CB 하자점검)","#1Sh.R 1차 (7579CB) 하자점검 - 즉시가압불가","2022-03-11 09:00","2022-03-11 18:00","2022-03-11 09:00","2022-03-11 18:00","연속"]
[178,"광주전남","광주","신광주한빛NP#2 T/L","22~23년 광주 변전협력회사 총액공사","345kV 신광주S/S 신광주-한빛#2T/L PT, LA 보통점검","2022-03-02 09:00","2022-03-02 18:00","2022-03-03 09:00","2022-03-03 18:00","연속"]
[179,"광주전남","광주","신남원신광주#1 T/L","345kV 신남원-신광주T/L 피뢰기 및 추락방지장치 설치공사","345kV 신남원-신광주T/L 피뢰기 및 추락방지장치 설치공사 - 피뢰기 설치공사","2022-03-02 07:00","2022-03-08 18:00","2022-03-02 07:00","2022-03-08 18:00","매일"]
[180,"광주전남","광주","신광주S/S #2 BUS","22년 광주변전총액(2BUS 모선보호반 교체)","345kV #2BUS PRO 보호반 교체(즉시가압 불가능)","2022-03-28 09:00","2022-04-01 18:00","취소","취소","연속"]
[181,"광주전남","광주","신광주신화순#2 T/L","21년 철탑 추락방지장치 설치공사","345kv 신광주-신화순 T/L 수평 추락방지장치 설치","2022-03-21 07:00","2022-03-25 18:00","2022-03-21 07:00","2022-03-25 18:00","매일"]
[182,"광주전남","광주","신광주S/S #1 BUS","22년 광주변전총액(1BUS 모선보호반 교체)","345kV #1BUS PRO 보호반 교체(즉시가압 불가능)","2022-03-21 09:00","2022-03-25 18:00","취소","취소","연속"]
[183,"광주전남","광주","신광주신화순#1 T/L","21년 철탑 추락방지장치 설치공사","345kV 신광주-신화순T/L 수평 추락방지장치 설치","2022-03-28 07:00","2022-04-01 18:00","2022-03-28 07:00","2022-04-01 18:00","매일"]
[184,"광주전남","광주","신광주S/S CB 7872","22~23년 광주전력지사 변전협력회사 총액공사(7872CB)","22~23년 광주전력지사 변전협력회사 총액공사(7872CB) - CB조작시험","2022-03-16 13:00","2022-03-16 18:00","2022-03-16 13:00","2022-03-16 18:00","연속"]
[185,"광주전남","광주","신광주S/S CB 7800","22~23년 광주전력지사 변전협력회사 총액공사(7800CB)","22~23년 광주전력지사 변전협력회사 총액공사(7800CB) - CB조작시험","2022-03-16 09:00","2022-03-16 13:00","2022-03-16 09:00","2022-03-16 13:00","연속"]
[186,"광주전남","광주","신광주S/S CB 7500","22~23년 광주전력지사 변전협력회사 총액공사(7500CB)","22~23년 광주전력지사 변전협력회사 총액공사(7500CB) - CB 조작시험","2022-03-15 13:00","2022-03-15 18:00","2022-03-15 13:00","2022-03-15 18:00","연속"]
[187,"광주전남","광주","신광주S/S CB 7571","22~23년 광주전력지사 변전협력회사 총액공사(7571CB)","22~23년 광주전력지사 변전협력회사 총액공사(7571CB) - CB 조작시험","2022-03-15 09:00","2022-03-15 13:00","2022-03-15 09:00","2022-03-15 13:00","연속"]
[188,"광주전남","광주","신광주S/S CB 7271","22~23년 광주전력지사 변전협력회사 총액공사(신광주-한빛#2T/L)","차단기 조작시험 단상 재폐로 회로 보완 및 시험","2022-03-14 14:00","2022-03-14 18:00","2022-03-14 14:00","2022-03-14 18:00","연속"]
[189,"광주전남","광주","신광주S/S CB 7100","22~23년 광주전력지사 변전협력회사 총액공사(신광주#1M.Tr TIE)","차단기 조작시험 단상 재폐로 회로 보완 및 시험","2022-03-08 09:00","2022-03-08 14:00","2022-03-15 09:00","2022-03-15 14:00","연속"]
[190,"광주전남","광주","신화순S/S CB 7700","22~23년 광주전력지사 변전협력회사 총액공사(7700CB)","22~23년 광주전력지사 변전협력회사 총액공사(7700CB) -CB 조작시험","2022-03-17 13:00","2022-03-17 18:00","2022-03-07 13:00","2022-03-07 18:00","연속"]
[191,"광주전남","광주","신화순S/S CB 7771","22~23년 광주전력지사 변전협력회사 총액공사(7771CB)","22~23년 광주전력지사 변전협력회사 총액공사(7771CB) - CB조작시험","2022-03-17 09:00","2022-03-17 13:00","2022-03-07 09:00","2022-03-07 13:00","연속"]
[192,"광주전남","광주","신화순S/S CB 7800","22~23년 광주전력지사 변전협력회사 총액공사(신화순SS 7800CB)","22~23년 광주전력지사 변전협력회사 총액공사(신화순SS 7800CB) - 조작시험","2022-03-24 09:00","2022-03-24 13:00","2022-03-08 09:00","2022-03-08 13:00","연속"]
[193,"광주전남","광주","신화순S/S CB 7971","22~23년 광주전력지사 변전협력회사 총액공사(신화순SS 7971CB)","22~23년 광주전력지사 변전협력회사 총액공사(신화순SS 7971CB) - 조작시험","2022-03-24 13:00","2022-03-24 18:00","2022-03-08 13:00","2022-03-08 18:00","연속"]
[194,"광주전남","광주","신화순S/S CB 7900","22~23년 광주전력지사 변전협력회사 총액공사(신화순 7900CB)","22~23년 광주전력지사 변전협력회사 총액공사(신화순 7900CB) - 조작시험","2022-03-31 09:00","2022-03-31 13:00","2022-03-31 09:00","2022-03-31 13:00","연속"]
[195,"광주전남","광주","신화순S/S CB 7972","22~23년 광주전력지사 변전협력회사 총액공사(신화순 7972CB)","22~23년 광주전력지사 변전협력회사 총액공사(신화순 7972CB) - 조작시험","2022-03-31 13:00","2022-03-31 18:00","2022-03-31 13:00","2022-03-31 18:00","연속"]
[196,"광주전남","목포","한빛1NP한빛2NP#2 T/L","2022-23년도 목포전력지사 변전협력회사 총액공사","GIS, 피뢰기 보통점검 및 보호반 성능개선 등","2022-03-16 09:00","2022-03-18 18:00","2022-03-10 09:00","2022-03-12 18:00","연속"]
[197,"광주전남","목포","한빛1NP한빛2NP#1 T/L","2022-23년도 목포전력지사 변전협력회사 총액공사","GIS, 피뢰기 보통점검 및 보호반 성능개선 등","2022-03-02 09:00","2022-03-04 18:00","2022-03-02 09:00","2022-03-04 18:00","연속"]
[198,"광주전남","목포","한빛#1N/P CB 7372","2022-23년도 목포전력지사 변전협력회사 총액공사","2022-23년도 목포전력지사 변전협력회사 총액공사","2022-03-07 09:00","2022-03-11 18:00","취소","취소","연속"]
[199,"광주전남","목포","한빛#1N/P CB 7472","2022-23년도 목포전력지사 변전협력회사 총액공사","2022-23년도 목포전력지사 변전협력회사 총액공사","2022-03-07 09:00","2022-03-11 18:00","취소","취소","연속"]
[200,"광주전남","목포","한빛1NP한빛2NP#1 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A CB 9대) × 1식 철거 - 362kV GIS(63kA 6300A CB 9대) × 1식 설치 - 362kV GIS(40kA 4000A #1BUS) × 1식 철거 - 362kV GIS(63kA 6300A #1BUS) × 1식 설치 - 기기기초 보강 및 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2022-03-28 09:00","2022-05-25 18:00","2022-03-22 09:00","2022-05-21 18:00","연속"]
[201,"광주전남","목포","신남원한빛NP#1 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A CB 9대) × 1식 철거 - 362kV GIS(63kA 6300A CB 9대) × 1식 설치 - 362kV GIS(40kA 4000A #1BUS) × 1식 철거 - 362kV GIS(63kA 6300A #1BUS) × 1식 설치 - 기기기초 보강 및 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2022-03-28 09:00","2022-05-27 18:00","2022-03-22 09:00","2022-05-21 18:00","연속"]
[202,"대구","달성","북경남대구#1 T/L","345kV 북경남-대구T/L 안전이격거리 확보공사","345kV 북경남-대구T/L 안전이격거리 확보공사 본선로 구성","2022-03-18 07:00","2022-03-31 18:00","2022-03-18 07:00","2022-03-31 18:00","연속"]
[203,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","345kV #4M.Tr 보호반 개조 (154kV 1.5CB 차단방식 적용)","2022-03-16 09:00","2022-03-17 18:00","취소","취소","연속"]
[204,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","345kV #3M.Tr 보호반 개조 (154kV 1.5CB 차단방식 적용)","2022-03-14 09:00","2022-03-15 18:00","취소","취소","연속"]
[205,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","345kV #2M.Tr 보호반 개조 (154kV 1.5CB 차단방식 적용)","2022-03-10 09:00","2022-03-11 18:00","취소","취소","연속"]
[206,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","345kV #1M.Tr 보호반 개조 (154kV 1.5CB 차단방식 적용)","2022-03-07 09:00","2022-03-08 18:00","취소","취소","연속"]
[207,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 선하지 마을진입교량 개체공사 안전확보","345kV 신포항-북대구T/L 선하지 마을진입교량 개체공사 안전확보","2022-03-25 10:00","2022-03-25 15:00","2022-03-25 10:00","2022-03-25 15:00","연속"]
[208,"대구","포항","선산신포항 T/L","345kV 신포항-북대구T/L 선하지 마을진입교량 개체공사 안전확보","345kV 신포항-북대구T/L 선하지 마을진입교량 개체공사 안전확보","2022-03-25 10:00","2022-03-25 15:00","2022-03-25 10:00","2022-03-25 15:00","연속"]
[209,"대구","포항","신포항S/S #3 M.Tr","신포항S/S #3M.Tr 누유개소 조치","신포항S/S #3M.Tr 누유개소 조치","2022-03-11 09:00","2022-03-11 18:00","2022-03-14 09:00","2022-03-15 18:00","연속"]
[210,"대구","포항","신포항신영일 T/L","신포항S/S 신포항-신영일 PT,LA보통점검","신포항S/S 신포항-신영일 PT,LA보통점검","2022-03-02 09:00","2022-03-02 18:00","2022-03-02 09:00","2022-03-02 18:00","연속"]
[211,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 선하지 마을진입교량 개체공사 안전확보","345kV 신포항-북대구T/L 선하지 마을진입교량 개체공사 안전확보","2022-03-04 07:00","2022-03-04 13:00","2022-03-03 07:00","2022-03-03 13:00","연속"]
[212,"대구","포항","선산신포항 T/L","345kV 신포항-북대구T/L 선하지 마을진입교량 개체공사 안전확보","345kV 신포항-북대구T/L 선하지 마을진입교량 개체공사 안전확보","2022-03-04 13:00","2022-03-04 19:00","2022-03-03 13:00","2022-03-03 19:00","연속"]
[213,"대구","포항","선산신포항 T/L","신포항S/S 선산-신포항T/L 결상회로보완 및 조작시험","신포항S/S 선산-신포항T/L 결상회로보완 및 조작시험","2022-03-07 09:00","2022-03-07 18:00","2022-03-11 09:00","2022-03-11 18:00","연속"]
[214,"대구","포항","신포항신월성NP#4 T/L","신포항S/S 가공지선측 과열개소 관련 안전확보 휴전","신포항S/S 가공지선측 과열개소 관련 안전확보 휴전","2022-03-10 09:00","2022-03-10 14:00","2022-03-10 09:00","2022-03-10 18:00","연속"]
[215,"경북","영주","신영주안동CC T/L","345kV 영포 등 2개T/L 추락방지시설 설치공사","345kV 신영주-안동CCT/L 추락방지시설 설치공사 (No.1 ~ No.49)","2022-03-14 09:00","2022-03-18 18:00","2022-03-14 09:00","2022-03-18 18:00","매일"]
[216,"경북","영주","신영주S/S #1 M.Tr","신영주S/S 154kV GIS 하자보수","3P DS 롱런 관련 조치 등 제작사 하자보수","2022-03-16 09:00","2022-03-16 12:00","2022-03-16 09:00","2022-03-16 12:00","연속"]
[217,"경북","영주","신영주S/S #2 M.Tr","신영주S/S 154kV GIS 하자보수","3P DS 롱런 관련 조치 등 제작사 하자보수","2022-03-21 15:00","2022-03-21 17:00","2022-03-21 15:00","2022-03-21 17:00","연속"]
[218,"경북","영주","신영주S/S #3 M.Tr","신영주S/S 154kV GIS 하자보수","3P DS 롱런 관련 조치 등 제작사 하자보수","2022-03-22 09:00","2022-03-22 12:00","2022-03-22 09:00","2022-03-22 12:00","연속"]
[219,"경북","영주","신영주한울NP#1 T/L","22-23년 영주전력지사 변전정비회사 총액공사","차단기 보통점검","2022-03-15 09:00","2022-03-15 18:00","2022-03-15 09:00","2022-03-15 18:00","연속"]
[220,"경북","영주","신영주S/S STATCOM (CB 7971, 7900)","신영주S/S 345kV STATCOM 휴전 작업","- 냉각실 냉각펌프 1EA 교체 - Valve Room 내 열화상카메라 설치","2022-03-21 09:00","2022-03-25 18:00","2022-03-21 09:00","2022-03-25 18:00","연속"]
[221,"경북","영주","신영주한울NP#2 T/L","22-23년 영주전력지사 변전정비회사 총액공사","차단기 보통점검 3/20(월) / 한울2발 79BAY 이음조치 3/22(화) ~ 3/24(목)","2022-03-21 09:00","2022-03-24 18:00","2022-03-07 09:00","2022-03-12 18:00","연속"]
[222,"경북","영주","신한울한울#2 T/L","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","2022-03-26 14:00","2022-03-26 18:00","2022-03-26 14:00","2022-03-26 18:00","연속"]
[223,"경북","영주","신한울한울#1 T/L","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","2022-03-26 09:00","2022-03-26 14:00","2022-03-26 09:00","2022-03-26 14:00","연속"]
[224,"경북","영주","한울1NP한울2NP#2 T/L","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","2022-03-27 14:00","2022-03-27 18:00","2022-03-27 14:00","2022-03-27 18:00","연속"]
[225,"경북","영주","한울2NP한울3NP#3 T/L","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","2022-03-28 09:00","2022-03-28 14:00","2022-03-28 09:00","2022-03-28 14:00","연속"]
[226,"경북","영주","한울1NP한울2NP#1 T/L","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","2022-03-27 09:00","2022-03-27 14:00","2022-03-27 09:00","2022-03-27 14:00","연속"]
[227,"경북","영주","한울2NP한울3NP#4 T/L","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","345kV신영주-한울NP2 등 5개 T/L 추락방지시설 설치공사","2022-03-28 14:00","2022-03-28 18:00","2022-03-28 14:00","2022-03-28 18:00","연속"]
[228,"부산울산","동부산","고리N/P #75 BUS","신고리 5,6호기 접속설비공사","345kV 50kA 4,000A GIS * 2CB(7400, 7472) 증설","2022-03-10 09:00","2022-03-24 18:00","2022-03-17 09:00","2022-03-31 18:00","연속"]
[229,"부산울산","동부산","신양산S/S #1 M.Tr","신양산S/S 주변압기 3차측 현대화 공사","신양산S/S 주변압기 3차측 현대화 공사","2022-03-21 09:00","2022-04-01 18:00","취소","취소","연속"]
[230,"부산울산","북부산","북부산S/S #1 M.Tr","북부산S/S 345kV M.Tr 3차측 현대화공사","북부산S/S 345kV M.Tr 3차측 현대화공사(1BANK)","2022-03-02 09:00","2022-04-15 18:00","2022-03-02 09:00","2022-04-15 18:00","연속"]
[231,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산T/L 81~84호간 지장철탑 이설공사","가선로 구성작업 연긴선 (#2TL)","2022-03-10 08:00","2022-03-18 18:00","2022-03-10 08:00","2022-03-17 18:00","연속"]
[232,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산-신울산T/L 81~84호간 지장철탑 이설공사","본선로 구성작업 연긴선(#1TL)및 철탑 조립 81-1호 82호","2022-03-21 08:00","2022-04-04 18:00","2022-03-21 08:00","2022-04-04 18:00","연속"]
[233,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","73BAY #2BUS 대체 및 7371,7300 대체","2022-03-02 09:00","2022-03-25 15:00","2022-03-02 09:00","2022-03-25 15:00","연속"]
[234,"부산울산","울산","신온산남울산#2 T/L","345kV 신온산S/S 용량부족 차단기 대체공사","73BAY GIS(7371,7300) 대체","2022-03-02 09:00","2022-04-27 15:00","2022-03-02 09:00","2022-04-27 15:00","연속"]
[235,"부산울산","울산","신온산S/S #2 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","73BAY GIS(7371,7300) 대체관련 안전이격거리 확보","2022-03-02 09:00","2022-03-25 15:00","2022-03-02 09:00","2022-03-25 15:00","연속"]
[236,"부산울산","울산","신온산S/S #1 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","73BAY #1BUS 대체","2022-03-28 09:00","2022-04-13 15:00","2022-03-28 09:00","2022-04-13 15:00","연속"]
[237,"부산울산","울산","신온산남울산#1 T/L","345kV 신온산S/S 용량부족 차단기 대체공사","73BAY~74BAY 전단 #1BUS 철거 및 설치 관련 안전이격 확보","2022-03-29 09:00","2022-04-01 17:00","2022-03-29 09:00","2022-04-01 17:00","연속"]
[238,"부산울산","울산","신울산고리NP#1 T/L","2022년 고리NP S/Y 345kV GIS 정밀점검 공사 관련 시험가압","7300,7372 GIS 정밀점검 후 시험가압","2022-03-20 15:00","2022-03-20 17:00","2022-03-30 15:00","2022-03-30 17:00","연속"]
[239,"부산울산","울산","신울산고리NP#1 T/L","신고리 5,6호기 접속설비공사 관련 고리N/P SW 증설","345kV GIS * 2CB 증설(7400,7472)","2022-03-23 09:00","2022-03-30 18:00","2022-03-02 09:00","2022-03-16 18:00","연속"]
[240,"부산울산","울산","울산C/C CB 7171","22~23년 변전협력회사 총액공사","- GIS(7171) 하자점검","2022-03-17 09:00","2022-03-17 18:00","2022-03-17 09:00","2022-03-17 18:00","연속"]
[241,"부산울산","울산","울산C/C CB 7400","22~23년 변전협력회사 총액공사","- GIS(7400) 차단기 동작시험","2022-03-21 14:00","2022-03-21 18:00","2022-03-21 14:00","2022-03-21 18:00","연속"]
[242,"부산울산","울산","울산C/C CB 7871","22~23년 변전협력회사 총액공사","- GIS(7871) 차단기 동작시험","2022-03-23 09:00","2022-03-23 12:00","2022-03-23 09:00","2022-03-23 12:00","연속"]
[243,"부산울산","울산","울산C/C CB 7800","22~23년 변전협력회사 총액공사","- GIS(7800) 차단기 동작시험","2022-03-23 12:00","2022-03-23 15:00","취소","취소","연속"]
[244,"부산울산","울산","울산C/C CB 7872","22~23년 변전협력회사 총액공사","- GIS(7872) 차단기 동작시험","2022-03-23 15:00","2022-03-23 18:00","취소","취소","연속"]
[245,"부산울산","울산","울산C/C CB 7100","22~23년 변전협력회사 총액공사","- GIS(7100) 차단기 동작시험","2022-03-18 09:00","2022-03-18 14:00","2022-03-18 09:00","2022-03-18 14:00","연속"]
[246,"부산울산","울산","울산C/C CB 7172","22~23년 변전협력회사 총액공사","- GIS(7172) 차단기 동작시험","2022-03-18 14:00","2022-03-18 18:00","2022-03-18 14:00","2022-03-18 18:00","연속"]
[247,"부산울산","울산","울산C/C CB 7471","22~23년 변전협력회사 총액공사","- GIS(7471) 차단기 동작시험","2022-03-21 09:00","2022-03-21 14:00","취소","취소","연속"]
[248,"부산울산","울산","울산C/C CB 7771","22~23년 변전협력회사 총액공사","- GIS(7771) 차단기 동작시험","2022-03-22 09:00","2022-03-22 12:00","2022-03-22 09:00","2022-03-22 12:00","연속"]
[249,"부산울산","울산","울산C/C CB 7A72","22~23년 변전협력회사 총액공사","- GIS(7A72) 차단기 동작시험","2022-03-25 14:00","2022-03-25 18:00","2022-03-25 14:00","2022-03-25 18:00","연속"]
[250,"부산울산","울산","울산C/C CB 7A00","22~23년 변전협력회사 총액공사","- GIS(7A00) 차단기 동작시험","2022-03-25 09:00","2022-03-25 14:00","2022-03-25 09:00","2022-03-25 14:00","연속"]
[251,"부산울산","울산","울산C/C CB 7A71","22~23년 변전협력회사 총액공사","- GIS(7A71) 하자점검","2022-03-24 09:00","2022-03-24 18:00","2022-03-24 09:00","2022-03-24 18:00","연속"]
[252,"부산울산","울산","울산C/C CB 7700","22~23년 변전협력회사 총액공사","- GIS(7700) 차단기 동작시험","2022-03-22 12:00","2022-03-22 15:00","2022-03-22 12:00","2022-03-22 15:00","연속"]
[253,"부산울산","울산","울산C/C CB 7772","22~23년 변전협력회사 총액공사","- GIS(7772) 차단기 동작시험","2022-03-22 15:00","2022-03-22 18:00","2022-03-22 15:00","2022-03-22 18:00","연속"]
[254,"부산울산","울산","울주고리NP#2 T/L","345kV 울주-고리NP 등 3개T/L 추락방지시설 설치공사","내용: 추락방지 수평와이어 설치 구간: 345kV 울주-고리NPT/L 1~92호","2022-03-01 07:00","2022-03-08 18:00","2022-03-01 07:00","2022-03-06 18:00","연속"]
[255,"부산울산","울산","울주고리NP#1 T/L","345kV 울주-고리NP 등 3개T/L 추락방지시설 설치공사","내용: 추락방지 수평와이어 설치 구간: 345kV 울주-고리NPT/L 1~92호","2022-03-10 07:00","2022-03-18 18:00","2022-03-07 07:00","2022-03-16 18:00","연속"]
[256,"부산울산","울산","울주S/S #4 M.Tr","22~23년 변전협력회사 총액공사","- M.Tr 보통점검 - 7872 차단기 동작시험","2022-03-14 09:00","2022-03-15 18:00","2022-03-14 09:00","2022-03-15 18:00","연속"]
[257,"부산울산","울산","울주S/S CB 7500","22~23년 변전협력회사 총액공사","- GIS(7500) 차단기 동작시험","2022-03-22 09:00","2022-03-22 12:00","2022-03-22 09:00","2022-03-22 12:00","연속"]
[258,"부산울산","울산","울주S/S CB 7671","22~23년 변전협력회사 총액공사","- GIS(7671) 차단기 동작시험","2022-03-22 12:00","2022-03-22 15:00","2022-03-22 12:00","2022-03-22 15:00","연속"]
[259,"부산울산","울산","울주S/S CB 7600","22~23년 변전협력회사 총액공사","- GIS(7600) 차단기 동작시험","2022-03-22 15:00","2022-03-22 18:00","2022-03-22 15:00","2022-03-22 18:00","연속"]
[260,"부산울산","울산","울주S/S CB 7871","22~23년 변전협력회사 총액공사","- GIS(7871) 차단기 동작시험","2022-03-23 14:00","2022-03-23 18:00","2022-03-23 14:00","2022-03-23 18:00","연속"]
[261,"부산울산","울산","울주S/S CB 7771","22~23년 변전협력회사 총액공사","- GIS(7771) 차단기 동작시험","2022-03-23 09:00","2022-03-23 14:00","2022-03-23 09:00","2022-03-23 14:00","연속"]
[262,"부산울산","울산","울주S/S CB 7A00","22~23년 변전협력회사 총액공사","- GIS(7A00) 차단기 동작시험","2022-03-25 14:00","2022-03-25 18:00","2022-03-25 14:00","2022-03-25 18:00","연속"]
[263,"부산울산","울산","울주S/S CB 7A71","22~23년 변전협력회사 총액공사","- GIS(7A71) 차단기 동작시험","2022-03-25 09:00","2022-03-25 14:00","2022-03-25 09:00","2022-03-25 14:00","연속"]
[264,"부산울산","울산","울주S/S CB 7971","22~23년 변전협력회사 총액공사","- GIS(7971) 차단기 동작시험","2022-03-24 09:00","2022-03-24 14:00","2022-03-24 09:00","2022-03-24 14:00","연속"]
[265,"부산울산","울산","울주S/S CB 7900","22~23년 변전협력회사 총액공사","- GIS(7900) 차단기 동작시험","2022-03-24 14:00","2022-03-24 18:00","2022-03-24 14:00","2022-03-24 18:00","연속"]
[266,"부산울산","직할","신대연S/S #1 Sh.R (CB 7079)","22년 상반기 직할 주변압기 정밀점검 공사","신대연S/S 345kV #1 Sh.R 정밀점검","2022-03-01 09:00","2022-03-06 18:00","취소","취소","연속"]
[267,"부산울산","직할","신대연S/S #2 M.Tr","22년 상반기 직할 주변압기 정밀점검 공사","신대연S/S 345kV #2 M.Tr 정밀점검, #2S.Tr 보통점검, 4289 GIS 보통점검","2022-03-28 09:00","2022-03-30 18:00","취소","취소","연속"]
[268,"부산울산","직할","신대연S/S #1 M.Tr","22년 상반기 직할 주변압기 정밀점검 공사","신대연S/S 345kV #1 M.Tr 정밀점검, #1S.Tr 보통점검, 4189 GIS 보통점검","2022-03-14 09:00","2022-03-25 18:00","취소","취소","연속"]
[269,"경남","직할","신김해북부산#1 T/L","신김해S/S 신김해-북부산#1T/L GIS 보통점검","신김해S/S 신김해-북부산#1T/L GIS 보통점검 (병행)PT 초기점검","2022-03-18 09:30","2022-03-18 17:30","2022-03-18 09:30","2022-03-18 17:30","연속"]
[270,"경남","직할","신김해S/S #3 M.Tr","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-03-28 08:00","2022-04-01 17:30","2022-03-28 08:00","2022-04-01 17:30","연속"]
[271,"경남","직할","신김해S/S #4 M.Tr","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-03-21 08:00","2022-03-25 17:30","2022-03-21 08:00","2022-03-25 17:30","연속"]
[272,"경남","직할","신김해창원#1 T/L","창원S/S 신김해-창원#1T/L GIS 보통점검","창원S/S 신김해-창원#1T/L GIS 보통점검","2022-03-17 09:30","2022-03-17 17:30","2022-03-17 09:30","2022-03-17 17:30","연속"]
[273,"경남","진주","하동T/P CB 7200","하동T/P 7200, 7272 GIS 조작시험","하동T/P 7200, 7272 GIS 조작시험","2022-03-22 09:00","2022-03-22 13:00","2022-03-22 09:00","2022-03-22 13:00","연속"]
[274,"경남","진주","하동T/P CB 7272","하동T/P 7200, 7272 GIS 조작시험","하동T/P 7200, 7272 GIS 조작시험","2022-03-22 13:00","2022-03-22 16:00","2022-03-22 13:00","2022-03-22 16:00","연속"]
[275,"경남","진주","하동T/P CB 7400","하동T/P 7400, 7472 GIS 조작시험","하동T/P 7400, 7472 GIS 조작시험","2022-03-30 09:00","2022-03-30 13:00","2022-03-30 09:00","2022-03-30 13:00","연속"]
[276,"경남","진주","하동T/P CB 7472","하동T/P 7400, 7472 GIS 조작시험","하동T/P 7400, 7472 GIS 조작시험","2022-03-30 13:00","2022-03-30 16:00","2022-03-30 13:00","2022-03-30 16:00","연속"]
[277,"경남","통영","창원삼천포TP#1 T/L","SPS 차단조건 추가 공사","1. 창원-삼천포화력#1/TL 차단기 접점 제공 2. 창원-삼천포화력#1/TL Ry 동작신호 제공","2022-03-28 10:00","2022-04-01 18:00","2022-03-28 10:00","2022-04-01 18:00","연속"]
[278,"경남","통영","신고성S/S #2 M.Tr","신고성S/S 345kV #2 M.Tr 누유개소 보수","1. 신고성S/S 345kV #2 M.Tr 누유개소 보수 2. 신고성S/S 345kV #2 M.Tr 2차 GIS 조작싷ㅁ 3. 신고성S/S 345kV #2 M.Tr 3차 VCB, S.Tr 보통점검 4. 신고성S/S 345kV #2 M.Tr 옥외모선 점검","2022-03-14 10:00","2022-03-16 18:00","2022-03-14 10:00","2022-03-16 18:00","연속"]
[279,"경남","함안","북경남대구#1 T/L","북경남S/S 북경남대구#1 T/L GIS 보통점검 외","북경남S/S 북경남-대구#1T/L GIS 보통점검(7600,7671), 단산재폐로관련 회로개선(본사지시)","2022-03-14 09:30","2022-03-15 18:00","취소","취소","연속"]
[280,"경남","함안","북경남대구#2 T/L","북경남S/S 북경남대구#2 T/L GIS 보통점검 외","북경남S/S 북경남-대구#2T/L GIS 보통점검(7500,7571), 단상재폐로관련 회로개선(본사지시)","2022-03-17 09:30","2022-03-18 18:00","취소","취소","연속"]
[281,"경남","함안","신마산S/S #3 M.Tr","신마산S/S 345kV M.Tr EBA 자기애관 교체공사","자기애관 -> 폴리머애관 교체","2022-03-21 08:00","2022-03-25 18:00","2022-03-21 08:00","2022-03-28 08:00","연속"]
[282,"경남","함안","신마산S/S #4 M.Tr","신마산S/S 345kV M.Tr EBA 자기애관 교체공사","자기애관 -> 폴리머애관 교체","2022-03-28 08:00","2022-04-01 18:00","2022-03-28 08:00","2022-04-04 08:00","연속"]
[283,"경남","함안","신마산S/S #2 M.Tr","신마산S/S 345kV M.Tr EBA 자기애관 교체공사","자기애관 -> 폴리머애관 교체","2022-03-14 08:00","2022-03-18 18:00","2022-03-14 08:00","2022-03-21 08:00","연속"]
[284,"경남","함안","신마산S/S #1 M.Tr","신마산S/S 345kV M.Tr EBA 자기애관 교체공사","자기애관 -> 폴리머애관 교체","2022-03-07 08:00","2022-03-12 18:00","2022-03-07 08:00","2022-03-14 08:00","연속"]
[285,"광주전남",null,"한빛N/P #3호기 주변압기 (CB 7700, 7771)","한빛3호기 18차 계획예방정비 * 조작차단기 : CB 7700, 7771, 7772","○ 한빛3호기 주변압기 가스절연모선 교체 ○ 스위치야드 GIS 77 Bay 교체 ○ 한빛 SPS 모드변경(1-0-2) #5,6 中 1대 차단","2022-03-22 10:00","2022-05-30 23:59","2022-03-22 09:00","2022-05-30 23:59","연속"]
[286,"광주전남",null,"한빛N/P #3-1S/U Tr (CB 7600, 7671)","한빛3호기 18차 계획예방정비 * 조작차단기 : CB 7600, 7671, 7672","○ 한빛3호기 기동변압기 가스절연모선 교체 ○ 한빛3호기 CV Cable 설비개선 ○ 스위치야드 GIS 76 Bay 교체","2022-03-22 10:00","2022-05-30 23:59","2022-03-22 09:00","2022-05-30 23:59","연속"]
[287,"경북",null,"한울N/P #1호기 주변압기 (CB 7100, 7172)","1호기 24차 계획예방정비 * 조작차단기 : CB 7100, 7172","○ 주/소내보조/여자변압기 일반점검","2022-03-19 16:00","2022-04-20 15:00","2022-03-19 16:00","2022-04-20 15:00","연속"]
[288,"경북",null,"한울N/P #6호기 주변압기 (CB 7C00, 7C72)","6호기 12차 계획예방정비 * 조작차단기 : CB 7C00, 7C72","○ 소내전원 절체(UAT→SAT)시험","2022-03-28 13:00","2022-03-28 18:00","2022-03-28 13:00","2022-03-28 18:00","연속"]
[289,"경북",null,"한울N/P #6호기 대기보조변압기 (CB 7B00, 7B72)","6호기 12차 계획예방정비 * 조작차단기 : CB 7B00, 7B72","○ 대기보조변압기 일반점검","2022-03-17 17:00","2022-03-27 10:00","2022-03-17 17:00","2022-03-27 10:00","연속"]
[290,"부산울산",null,"고리N/P #2호기 주변압기 (CB 7300, 7372)","2호기 31차 계획예방정비","○ GIB 개선작업 ○ 주/보조 변압기 일반점검","2022-02-28 00:01","2022-03-30 23:59","2022-02-26 13:00","2022-04-12 09:00","연속"]
[291,"대전세종충남",null,"신보령T/P #2호기 주변압기 (CB 7200, 7272)","2호기 계획예방정비공사","2호기 주변압기 점검","2022-03-10 09:00","2022-05-22 18:00","2022-03-10 09:00","2022-05-22 18:00","연속"]
[292,"강원",null,"양양P/P #3호기 주변압기(7200,7272)","갑종보호계전기 시험","갑종보호계전기 시험","2022-03-02 09:00","2022-03-03 18:00","2022-03-02 09:00","2022-03-03 18:00","연속"]
[293,"강원",null,"양양P/P #2호기 주변압기(7200,7271)","정기검사 수검","정기검사 수검","2022-03-14 09:00","2022-03-15 13:00","2022-03-14 09:00","2022-03-15 13:00","연속"]
[294,"강원",null,"양양P/P #3호기 주변압기(7200,7272)","정기검사 수검","정기검사 수검","2022-03-16 09:00","2022-03-17 13:00","2022-03-16 09:00","2022-03-17 13:00","연속"]
[295,"전북",null,"무주P/P #1호기 주변압기","B급 계획예방정비","B급 계획예방정비","2022-03-14 00:01","2022-06-11 23:59","2022-03-14 00:01","2022-06-11 23:59","연속"]

{"sheet":"154설비","index":2,"n_rows":519,"n_cols":11,"rows_kept":519,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 3월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","도봉방학#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-03-14 10:00","2022-03-14 17:00","2022-03-14 10:00","2022-03-14 17:00","연속"]
[2,"서울","성동","도봉방학#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-03-15 10:00","2022-03-15 17:00","2022-03-15 10:00","2022-03-15 17:00","연속"]
[3,"서울","성동","방학창동#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검(양단)","2022-03-16 10:00","2022-03-16 17:00","취소","취소","연속"]
[4,"서울","성동","방학창동#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검(양단)","2022-03-17 10:00","2022-03-17 17:00","취소","취소","연속"]
[5,"서울","성동","방학S/S CB 6100","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-03-18 10:00","2022-03-18 17:00","2022-03-18 10:00","2022-03-18 17:00","연속"]
[6,"서울","성동","금오상계#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 금오-상계T/L No.37~54(13기) 추락방지시설 설치공사","2022-03-18 08:00","2022-03-21 18:00","취소","취소","매일"]
[7,"서울","성동","금오상계#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 금오-상계T/L No.37~54(13기) 추락방지시설 설치공사","2022-03-22 08:00","2022-03-22 18:00","취소","취소","연속"]
[8,"서울","성동","양주쌍문#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 양주-쌍문T/L No.28~38(9기) 추락방지시설 설치공사","2022-03-03 08:00","2022-03-03 18:00","취소","취소","연속"]
[9,"서울","성동","양주쌍문#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 양주-쌍문T/L No.28~38(9기) 추락방지시설 설치공사","2022-03-02 08:00","2022-03-02 18:00","취소","취소","연속"]
[10,"서울","중부","순화동빙고 T/L","'22-23 중부P/O 변전협력회사 총액공사","170kV GIS 보통점검 인출 PT 보통점검","2022-03-30 09:00","2022-03-30 18:00","2022-03-30 09:00","2022-03-30 18:00","연속"]
[11,"서울","중부","상암등촌#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 상암-등촌T/L No.3, No.7 추락방지시설 설치공사","2022-03-16 08:00","2022-03-16 13:00","취소","취소","연속"]
[12,"서울","중부","상암등촌#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 상암-등촌T/L No.3, No.7 추락방지시설 설치공사","2022-03-16 13:00","2022-03-16 18:00","취소","취소","연속"]
[13,"서울","중부","원흥상암 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 원흥-수색T/L No.1~2(4기) 추락방지시설 설치공사","2022-03-31 08:00","2022-03-31 18:00","취소","취소","연속"]
[14,"서울","중부","원흥수색#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 원흥-수색T/L No.1~2(4기) 추락방지시설 설치공사","2022-03-29 08:00","2022-03-30 18:00","취소","취소","연속"]
[15,"서울","중부","양주은평#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 양주-은평T/L No.31~33(3기) 추락방지시설 설치공사","2022-03-17 13:00","2022-03-17 18:00","취소","취소","연속"]
[16,"서울","중부","양주은평#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 양주-은평T/L No.31~33(3기) 추락방지시설 설치공사","2022-03-17 08:00","2022-03-17 13:00","취소","취소","연속"]
[17,"서울","중부","은평녹번#2 T/L","'22-23 중부P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-03-25 09:00","2022-03-25 18:00","2022-03-25 09:00","2022-03-25 18:00","연속"]
[18,"서울","중부","현저서대문#1 T/L","'22-23 중부P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-03-28 09:00","2022-03-28 18:00","2022-03-28 09:00","2022-03-28 18:00","연속"]
[19,"서울","중부","지축현저#1 T/L","'22-23 중부P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-03-30 09:00","2022-03-30 18:00","2022-03-30 09:00","2022-03-30 18:00","연속"]
[20,"서울","중부","지축현저#2 T/L","'22-23 중부P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-03-31 09:00","2022-03-31 18:00","2022-03-31 09:00","2022-03-31 18:00","연속"]
[21,"서울","중부","현저서대문#2 T/L","'22-23 중부P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-03-29 09:00","2022-03-29 18:00","2022-03-29 09:00","2022-03-29 18:00","연속"]
[22,"남서울","강남","동빙고반포#2 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","- 동빙고-반포#1,2T/L GIS 보통점검","2022-03-11 09:00","2022-03-11 18:00","2022-03-11 09:00","2022-03-11 18:00","연속"]
[23,"남서울","강남","신사반포#1 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","- 신사반포#1,2T/L GIS 조작시험","2022-03-14 09:00","2022-03-14 14:00","2022-03-14 09:00","2022-03-14 14:00","연속"]
[24,"남서울","강남","신사반포#2 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","- 신사반포#1,2T/L GIS 조작시험","2022-03-14 14:00","2022-03-14 18:00","2022-03-14 14:00","2022-03-14 18:00","연속"]
[25,"남서울","강남","동빙고반포#1 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","- 동빙고-반포#1,2T/L GIS 보통점검","2022-03-11 09:00","2022-03-11 18:00","2022-03-11 09:00","2022-03-11 18:00","연속"]
[26,"남서울","동서울","가락S/S CB 6100","가락SS 6100BT GIS 보통점검","가락SS 6100BT GIS 보통점검","2022-03-15 09:00","2022-03-15 18:00","2022-03-15 09:00","2022-03-15 18:00","연속"]
[27,"남서울","동서울","동서울신장#2 T/L","세종-포천 고속도로 건설 지장송전선로 지중화(이설)공사","S/T~No.1 하단 전력구 건설공사","2022-03-02 07:00","2022-03-02 18:00","2022-03-02 07:00","2022-03-02 18:00","연속"]
[28,"남서울","동서울","송파잠실#2 T/L","송파,잠실SS 송파-잠실2TL GIS 정기점검","송파,잠실SS 송파-잠실2TL GIS 정기점검","2022-03-31 09:00","2022-03-31 14:00","2022-03-31 09:00","2022-03-31 14:00","연속"]
[29,"남서울","동서울","송파잠실#3 T/L","송파,잠실SS 송파-잠실3TL GIS 정기점검","송파,잠실SS 송파-잠실3TL GIS 정기점검","2022-03-31 14:00","2022-03-31 18:00","2022-03-31 14:00","2022-03-31 18:00","연속"]
[30,"남서울","동서울","송파잠실#4 T/L","송파,잠실SS 송파-잠실4TL GIS 정기점검","송파,잠실SS 송파-잠실4TL GIS 정기점검","2022-03-30 09:00","2022-03-30 18:00","2022-03-30 09:00","2022-03-30 18:00","연속"]
[31,"남서울","동서울","산성수서#2 T/L","수서SS 산성-수서2TL GIS 조작시험","수서SS 산성-수서2TL GIS 조작시험","2022-03-07 14:00","2022-03-07 18:00","2022-03-07 14:00","2022-03-07 18:00","연속"]
[32,"남서울","동서울","산성수서#1 T/L","수서SS 산성-수서1TL GIS 조작시험","수서SS 산성-수서1TL GIS 조작시험","2022-03-07 09:00","2022-03-07 14:00","2022-03-07 09:00","2022-03-07 14:00","연속"]
[33,"남서울","동서울","가락수서#2 T/L","가락-수서2T/L GIS 정기점검","가락-수서2TL 가락SS 보통, 수서SS 조작시험","2022-03-03 09:00","2022-03-03 18:00","2022-03-03 09:00","2022-03-03 18:00","연속"]
[34,"남서울","동서울","가락수서#1 T/L","수서SS 가락-수서1T/L GIS 누기보수,보통점검","수서SS 가락-수서1T/L GIS 누기보수,보통점검","2022-03-12 09:00","2022-03-13 18:00","2022-03-12 09:00","2022-03-13 18:00","연속"]
[35,"남서울","동서울","신장S/S CB 6100","신장SS 6100BT GIS 하자점검","신장SS 6100BT GIS 하자점검","2022-03-08 09:00","2022-03-08 18:00","2022-03-08 09:00","2022-03-08 18:00","연속"]
[36,"남서울","동서울","신장덕소#2 T/L","신장SS 신장-덕소2TL GIS 하자점검","신장SS 신장-덕소2TL GIS 하자점검","2022-03-07 14:00","2022-03-07 18:00","2022-03-07 14:00","2022-03-07 18:00","연속"]
[37,"남서울","동서울","신장덕소#1 T/L","신장SS 신장-덕소1TL GIS 하자점검","신장SS 신장-덕소1TL GIS 하자점검","2022-03-07 09:00","2022-03-07 14:00","2022-03-07 09:00","2022-03-07 14:00","연속"]
[38,"남서울","동서울","탄천대치#1 T/L","대치-탄천1TL GIS 정기점검","대치-탄천1TL GIS 정기점검 탄천:보통","2022-03-22 09:00","2022-03-22 14:00","2022-03-22 09:00","2022-03-22 14:00","연속"]
[39,"남서울","동서울","탄천선릉#2 T/L","탄천-선릉2TL GIS 정기점검","탄천-선릉2TL GIS 정기점검 탄천:보통,선릉:조작","2022-03-21 14:00","2022-03-21 18:00","2022-03-21 14:00","2022-03-21 18:00","연속"]
[40,"남서울","동서울","탄천선릉#1 T/L","탄천-선릉1TL GIS 정기점검","탄천-선릉1TL GIS 정기점검 탄천:보통,선릉:조작","2022-03-21 09:00","2022-03-21 14:00","2022-03-21 09:00","2022-03-21 14:00","연속"]
[41,"남서울","동서울","탄천대치#2 T/L","대치-탄천2TL GIS 정기점검","대치-탄천2TL GIS 정기점검 탄천:보통","2022-03-22 14:00","2022-03-22 18:00","2022-03-22 14:00","2022-03-22 18:00","연속"]
[42,"남서울","동서울","탄천S/S CB 6100","탄천SS 6100BT GIS 정기점검","탄천SS 6100BT GIS 정기점검","2022-03-23 09:00","2022-03-23 14:00","2022-03-23 09:00","2022-03-23 14:00","연속"]
[43,"남서울","동서울","탄천S/S CB 6200","탄천SS 6200BT GIS 정기점검","탄천SS 6200BT GIS 정기점검","2022-03-23 14:00","2022-03-23 18:00","2022-03-23 14:00","2022-03-23 18:00","연속"]
[44,"남서울","동서울","탄천S/S SEC CB 60610","탄천SS 60-61 SEC GIS 정기점검","탄천SS 60-61 SEC GIS 정기점검","2022-03-24 09:00","2022-03-24 14:00","2022-03-24 09:00","2022-03-24 14:00","연속"]
[45,"남서울","동서울","탄천S/S SEC CB 65660","탄천SS 65-66 SEC GIS 정기점검","탄천SS 65-66 SEC GIS 정기점검","2022-03-24 14:00","2022-03-24 18:00","2022-03-24 14:00","2022-03-24 18:00","연속"]
[46,"남서울","영등포","광명구공#3 T/L","광명S/S 장기사용 154kV GIS 교체공사","154kV GIS 12대 교체 등 657교체, 61-66BUS PT 설치, 4/5-6 무부하 가압","2022-03-28 09:00","2022-04-13 18:00","취소","취소","연속"]
[47,"남서울","영등포","신광명광명#1 T/L","광명S/S 장기사용 154kV GIS 교체공사","154kV GIS 12대 교체 등 #2BUS 무부하가압 선로","2022-03-29 18:00","2022-03-30 18:00","취소","취소","연속"]
[48,"남서울","영등포","신문래구로#2 T/L","154kV 구로인출전력구 OF케이블 선종교체공사","○ 공사구간 : 구로S/S ∼ M/H#25(3구간) ○ 대상선로 : 154kV 신문래-구로#1,2T/L ○ 선종 및 길이 : 154kV OF 1,200㎟ → XLPE 1,200㎟ 1.1km × 2C ○ 케이블포설 및 접속개소 : 6구간(2회선×3구간), 8개소(2회선 : 중간 6, 종단 2)","2022-03-24 09:00","2022-06-13 18:00","2022-03-24 09:00","2022-06-13 18:00","연속"]
[49,"남서울","영등포","신문래목동#1 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 공압식 차단기 보통점검(신문래-목동#1)","2022-03-24 09:00","2022-03-24 18:00","2022-03-24 09:00","2022-03-24 18:00","연속"]
[50,"남서울","영등포","신정목동#1 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 공압식 차단기 보통점검(신정-목동#1)","2022-03-15 09:00","2022-03-15 18:00","2022-03-15 09:00","2022-03-15 18:00","연속"]
[51,"남서울","영등포","오류목동 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 공압식 차단기 보통점검(오류-목동)","2022-03-25 09:00","2022-03-25 18:00","2022-03-25 09:00","2022-03-25 18:00","연속"]
[52,"남서울","영등포","목동S/S CB 6100","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 공압식 차단기 보통점검(6100)","2022-03-14 09:00","2022-03-14 18:00","2022-03-14 09:00","2022-03-14 18:00","연속"]
[53,"남서울","영등포","신광명소래 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","*- 154kV 신광명-소래T/L 보호반 교체공사 (인천본부 병행)","2022-03-21 09:00","2022-03-25 18:00","2022-03-21 09:00","2022-03-25 18:00","연속"]
[54,"남서울","영등포","천왕오류#2 T/L","2021-2022년 영등포전력지사 지중송전설비 위탁정비공사","OF케이블 절연유 채유","2022-03-10 08:00","2022-03-10 18:00","2022-03-10 08:00","2022-03-10 18:00","연속"]
[55,"남서울","영등포","화곡마곡#2 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 보통점검(마곡S/S 화곡-마곡#1,2T/L) - 전자변 교체","2022-03-27 09:00","2022-03-27 18:00","취소","취소","연속"]
[56,"남서울","영등포","화곡마곡#1 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 보통점검(마곡S/S 화곡-마곡#1,2T/L)","2022-03-26 09:00","2022-03-26 18:00","취소","취소","연속"]
[57,"남서울","직할","봉천신길#2 T/L","154kV GIS 정밀점검공사_봉천-신길#2T/L","154kV GIS 정밀점검공사_봉천-신길#2T/L","2022-03-16 14:00","2022-03-18 18:00","2022-03-16 14:00","2022-03-18 18:00","연속"]
[58,"남서울","직할","봉천신길#1 T/L","154kV GIS 정밀점검공사_봉천-신길#1T/L","154kV GIS 정밀점검공사_봉천-신길#1T/L","2022-03-14 09:00","2022-03-16 14:00","2022-03-14 09:00","2022-03-16 14:00","연속"]
[59,"남서울","직할","사당봉천#2 T/L","154kV GIS 정밀점검공사_사당-봉천#2T/L","154kV GIS 정밀점검공사_사당-봉천#2T/L","2022-03-10 14:00","2022-03-12 18:00","2022-03-10 14:00","2022-03-12 18:00","연속"]
[60,"남서울","직할","사당봉천#1 T/L","154kV GIS 정밀점검공사_사당-봉천#1T/L","154kV GIS 정밀점검공사_사당-봉천#1T/L","2022-03-07 09:00","2022-03-10 14:00","2022-03-07 09:00","2022-03-10 14:00","연속"]
[61,"인천","김포","경서양촌#2 T/L","경서S/S 154kV 경서-양촌#2T/L GIS 조작점검","경서S/S 154kV 경서-양촌#2T/L GIS 조작점검","2022-03-24 14:00","2022-03-24 18:00","2022-03-17 14:00","2022-03-17 18:00","연속"]
[62,"인천","김포","경서양촌#1 T/L","경서S/S 154kV 경서-양촌#1T/L GIS 보통점검","경서S/S 154kV 경서-양촌#1T/L GIS 보통점검","2022-03-24 10:00","2022-03-24 14:00","2022-03-17 10:00","2022-03-17 14:00","연속"]
[63,"인천","김포","경서북인천#2 T/L","경서S/S 154kV 경서-북인천#2T/L GIS 보통점검","경서S/S 154kV 경서-북인천#2T/L GIS 보통점검 (병행) PITR 인터록 케이블포설 및 결선작업","2022-03-03 10:00","2022-03-03 18:00","2022-03-02 10:00","2022-03-03 18:00","연속"]
[64,"인천","김포","양촌양곡#1 T/L","양곡S/S 154kV 양촌-양곡#1T/L GIS 조작시험","*양곡S/S 154kV 양촌-양곡#1T/L GIS 조작시험 (병행) 전자변 러버히터 설치작업","2020-03-07 10:00","2020-03-07 18:00","2022-03-07 10:00","2022-03-07 18:00","연속"]
[65,"인천","김포","신김포양곡#1 T/L","양곡S/S 154kV 신김포-양곡#1T/L GIS 조작시험","양곡S/S 154kV 신김포-양곡#1T/L GIS 조작시험","2022-03-11 10:00","2022-03-11 18:00","2022-03-11 10:00","2022-03-11 18:00","연속"]
[66,"인천","김포","왕길양촌#2 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #2BUS 측 설치(1차 김포열병합1,2T/L, PT) - 인근BAY 휴전","2022-03-23 14:00","2022-03-24 14:00","2022-03-23 14:00","2022-03-24 14:00","연속"]
[67,"인천","김포","왕길양촌#2 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #1BUS 측 설치(1차 김포열병합1,2T/L, PT) - 무부하 가압","2022-03-10 14:00","2022-03-11 14:00","2022-03-10 14:00","2022-03-11 14:00","연속"]
[68,"인천","김포","왕길양촌#2 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #2BUS 측 설치(1차 김포열병합1,2T/L, PT) - 인근BAY 휴전","2022-03-28 09:00","2022-03-31 18:00","2022-03-28 09:00","2022-03-31 18:00","연속"]
[69,"인천","김포","양촌양곡#2 T/L","154kV 양촌S/S S.W 신규수용공사","*154kV 양촌S/S S.W 신규수용공사 - #1BUS 측 설치 (2차 B/T,B/S 설치) - 인근BAY휴전","2022-03-14 09:00","2022-03-16 18:00","2022-03-14 09:00","2022-03-16 18:00","연속"]
[70,"인천","부평","주안만수#2 T/L","만수S/S 주안만수#2 T/L GIS 조작시험","만수S/S 주안만수#2 T/L GIS 조작시험","2022-03-29 09:00","2022-03-29 18:00","2022-03-29 09:00","2022-03-29 18:00","연속"]
[71,"인천","부평","관교만수#2 T/L","만수S/S 관교만수#2T/L GIS 조작시험","만수S/S 관교만수#2T/L GIS 조작시험","2022-03-28 09:00","2022-03-28 18:00","2022-03-28 09:00","2022-03-28 18:00","연속"]
[72,"인천","부평","서인천C/C SEC CB 60610","서인천C/C 60-61SEC GIS 보통점검","서인천C/C 60-61SEC GIS 보통점검","2022-03-24 09:00","2022-03-24 13:00","2022-03-24 09:00","2022-03-24 13:00","연속"]
[73,"인천","부평","서인천C/C SEC CB 65660","서인천C/C 65-66SEC GIS 보통점검","서인천C/C 65-66SEC GIS 보통점검","2022-03-24 13:00","2022-03-24 18:00","2022-03-24 13:00","2022-03-24 18:00","연속"]
[74,"인천","부평","신가좌신현#2 T/L","신가좌S/S 신가좌신현#2T/L GIS 조작시험","신가좌S/S 신가좌신현#2T/L GIS 조작시험","2022-03-17 13:00","2022-03-17 18:00","2022-03-25 09:00","2022-03-25 18:00","연속"]
[75,"인천","부평","신가좌부개#1 T/L","신가좌S/S 신가좌부개#1 T/L GIS 조작시험","신가좌S/S 신가좌부개#1 T/L GIS 조작시험","2022-03-18 09:00","2022-03-18 13:00","2022-03-08 09:00","2022-03-08 13:00","연속"]
[76,"인천","부평","신가좌부개#2 T/L","신가좌S/S 신가좌부개#2 T/L GIS 조작시험","신가좌S/S 신가좌부개#2 T/L GIS 조작시험","2022-03-18 13:00","2022-03-18 18:00","취소","취소","연속"]
[77,"인천","부평","신가좌신현#1 T/L","신가좌S/S 신가좌신현#1T/L GIS 조작시험","신가좌S/S 신가좌신현#1T/L GIS 조작시험","2022-03-17 09:00","2022-03-17 13:00","2022-03-17 09:00","2022-03-17 18:00","연속"]
[78,"인천","부평","학익연수#1 T/L","학익S/S 학익연수#1 T/L GIS 조작시험","학익S/S 학익연수#1 T/L GIS 조작시험","2022-03-11 09:00","2022-03-11 14:00","2022-03-11 09:00","2022-03-11 14:00","연속"]
[79,"인천","부평","학익연수#2 T/L","학익S/S 학익연수#2 T/L GIS 조작시험","학익S/S 학익연수#2 T/L GIS 조작시험","2022-03-11 14:00","2022-03-11 18:00","2022-03-11 14:00","2022-03-11 18:00","연속"]
[80,"인천","부평","남인천학익#2 T/L","학익S/S 남인천학익#2T/L GIS 조작시험","학익S/S 남인천학익#2T/L GIS 조작시험","2022-03-07 09:00","2022-03-07 13:00","2022-03-07 09:00","2022-03-07 13:00","연속"]
[81,"인천","시흥","남동연수#2 T/L","154kV 남동-연수 #2 T/L OF케이블 선종교체공사","154kV 남동S/S ∼ 연수S/S [OF 2,000㎟ → XLPE 2,000㎟ 1C, 2.8km]","2022-03-14 09:00","2022-05-19 18:00","2022-03-14 09:00","2022-05-19 18:00","연속"]
[82,"인천","시흥","북시화서시화#1 T/L","북시화S/S 154kV GIS 교체공사","○ 북시화S/S 154kV GIS 교체공사(SA혼용) - 154kV 북시화서시화#1T/L GIS 교체(IED) - 기타부대공사 1식","2022-03-11 07:30","2022-03-27 18:00","2022-03-11 07:30","2022-03-27 18:00","연속"]
[83,"인천","시흥","신시흥북시화#1 T/L","북시화S/S 154kV GIS 교체공사(무부하가압)","○ 북시화S/S 154kV GIS 교체공사(SA혼용) - 154kV 북시화서시화#1T/L GIS 교체(IED) - 기타부대공사 1식","2022-03-26 10:00","2022-03-27 18:00","2022-03-26 10:00","2022-03-27 18:00","연속"]
[84,"인천","시흥","신시흥북시화#1 T/L","북시화S/S 154kV GIS 교체공사(무부하가압)","○ 북시화S/S 154kV GIS 교체공사(SA혼용) - 154kV 북시화서시화#1T/L GIS 교체(IED) - 기타부대공사 1식","2022-03-17 13:00","2022-03-18 13:00","2022-03-17 13:00","2022-03-18 13:00","연속"]
[85,"인천","시흥","신시흥북시화#1 T/L","북시화S/S 154kV GIS 교체공사(무부하가압)","○ 북시화S/S 154kV GIS 교체공사(SA혼용) - 154kV 북시화서시화#1T/L GIS 교체(IED) - 기타부대공사 1식","2022-03-13 14:00","2022-03-13 15:00","2022-03-13 14:00","2022-03-13 15:00","연속"]
[86,"인천","시흥","서안양소래 T/L","소래S/S 154kV 서안양소래 T/L GIS 조작시험","소래S/S 154kV 서안양소래 T/L GIS 조작시험","2022-03-15 09:00","2022-03-15 18:00","2022-03-15 09:00","2022-03-15 18:00","연속"]
[87,"인천","시흥","신시흥남동#2 T/L","신시흥S/S 154kV 신시흥남동#2 T/L GIS 초기점검","신시흥S/S 154kV 신시흥남동#2 T/L GIS 초기점검","2022-03-12 09:00","2022-03-12 18:00","2022-03-12 09:00","2022-03-12 18:00","연속"]
[88,"인천","시흥","남동연수#1 T/L","연수S/S 154kV 남동연수#1 T/L GIS 보통점검","연수S/S 154kV 남동연수#1 T/L GIS 보통점검","2022-03-08 09:00","2022-03-08 18:00","2022-03-08 09:00","2022-03-08 18:00","연속"]
[89,"인천","직할","갈산S/S SEC CB 65660","갈산S/S 65-66SEC GIS하자점검","갈산S/S 65-66SEC GIS하자점검","2022-03-25 09:30","2022-03-25 18:00","2022-03-25 09:30","2022-03-25 18:00","연속"]
[90,"인천","직할","갈산S/S CB 6100","갈산S/S 6100TIE GIS하자점검","갈산S/S 6100TIE GIS하자점검","2022-03-31 09:30","2022-03-31 18:00","2022-03-31 09:30","2022-03-31 18:00","연속"]
[91,"인천","직할","갈산S/S SEC CB 60610","갈산S/S 60-61SEC GIS하자점검","갈산S/S 60-61SEC GIS하자점검","2022-03-24 09:30","2022-03-24 18:00","2022-03-24 09:30","2022-03-24 18:00","연속"]
[92,"인천","직할","계양김포#1 T/L","검단신도시 지중화공사","*검단신도시 택지개발 관련 가공송전선로 지중화","2022-03-17 09:00","2022-05-07 18:00","2022-03-17 09:00","2022-05-07 18:00","연속"]
[93,"인천","직할","임학계양#1 T/L","345kV 서인천-신부평 등 11개T/L 구형 SVL교체공사","구형 SVL 교체를 통한 난연성 확보 및 파급고장 예방","2022-03-07 09:00","2022-03-08 18:00","2022-03-07 09:00","2022-03-08 18:00","연속"]
[94,"인천","직할","고강화곡#3 T/L","고강S/S 고강화곡#3T/L GIS 하자점검","고강S/S 고강화곡#3T/L GIS 하자점검","2022-03-21 09:30","2022-03-21 18:00","2022-03-21 09:30","2022-03-21 18:00","연속"]
[95,"인천","직할","고강화곡#2 T/L","고강S/S 고강화곡#2T/L GIS 보통점검","고강S/S 고강화곡#2T/L GIS 보통점검","2022-03-22 09:30","2022-03-22 18:00","2022-03-22 09:30","2022-03-22 18:00","연속"]
[96,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강#1T/L EBA 비표준형 자기애관 교체공사","종단접속함(EBA) 고장시 자기애관 비산에 따른 2차 인명·설비피해 방지","2022-03-12 09:00","2022-03-13 18:00","취소","취소","연속"]
[97,"인천","직할","신부평도당#2 T/L","345kV 서인천-신부평 등 11개T/L 구형 SVL교체공사","구형 SVL 교체를 통한 난연성 확보 및 파급고장 예방","2022-03-02 09:00","2022-03-03 18:00","2022-03-02 09:00","2022-03-03 18:00","연속"]
[98,"인천","직할","부천원미#1 T/L","345kV 서인천-신부평 등 11개T/L 구형 SVL교체공사","구형 SVL 교체를 통한 난연성 확보 및 파급고장 예방","2022-03-14 09:00","2022-03-16 18:00","2022-03-14 09:00","2022-03-16 18:00","연속"]
[99,"인천","직할","부천원미#2 T/L","345kV 서인천-신부평 등 11개T/L 구형 SVL교체공사","구형 SVL 교체를 통한 난연성 확보 및 파급고장 예방","2022-03-17 09:00","2022-03-18 18:00","2022-03-17 09:00","2022-03-18 18:00","연속"]
[100,"인천","직할","부개원미#2 T/L","345kV 서인천-신부평 등 11개T/L 구형 SVL교체공사","구형 SVL 교체를 통한 난연성 확보 및 파급고장 예방","2022-03-28 09:00","2022-03-31 18:00","취소","취소","연속"]
[101,"경기북부","고양","양주금촌#1 T/L","2022 고양P/O 변전정비회사 총액공사","170KV GIS 초기점검","2022-03-23 10:00","2022-03-23 18:00","2022-03-23 10:00","2022-03-23 18:00","연속"]
[102,"경기북부","고양","양주금촌#2 T/L","2022 고양P/O 변전정비회사 총액공사","170KV GIS 초기점검","2022-03-24 10:00","2022-03-24 18:00","2022-03-24 10:00","2022-03-24 18:00","연속"]
[103,"경기북부","고양","능곡상암#1 T/L","2022 고양P/O 변전정비회사 총액공사","170KV GIS 보통점검","2022-03-17 10:00","2022-03-17 18:00","2022-03-03 10:00","2022-03-03 10:00","연속"]
[104,"경기북부","고양","능곡상암#2 T/L","2022 고양P/O 변전정비회사 총액공사","170KV GIS 보통점검","2022-03-18 10:00","2022-03-18 18:00","2022-03-04 10:00","2022-03-04 10:00","연속"]
[105,"경기북부","고양","신파주송포#2 T/L","154kV 신파주-송포#2T/L 고정형 절연유 채취밸브 설치공사","활선OF 케이블용 고정형 절연유 채취밸브","2022-03-28 09:00","2022-04-01 18:00","2022-03-17 09:00","2022-03-23 18:00","연속"]
[106,"경기북부","고양","신파주송포#1 T/L","154kV 신파주-송포#1T/L 고정형 절연유 채취밸브 설치공사","활선OF 케이블용 고정형 절연유 채취밸브","2022-03-21 09:00","2022-03-25 18:00","2022-03-10 09:00","2022-03-16 18:00","연속"]
[107,"경기북부","고양","신파주원흥#2 T/L","2022 고양P/O 변전정비회사 총액공사","170KV GIS 보통점검","2022-03-11 10:00","2022-03-11 18:00","2022-03-11 10:00","2022-03-11 18:00","연속"]
[108,"경기북부","고양","신파주원흥#1 T/L","2022 고양P/O 변전정비회사 총액공사","170KV GIS 보통점검","2022-03-10 10:00","2022-03-10 18:00","2022-03-10 10:00","2022-03-10 18:00","연속"]
[109,"경기북부","고양","고양일산#2 T/L","고양전력지사 추락방지시설 설치공사","ㅇ 추락방지시설(와이어, 수직,수평) 설치","2022-03-21 07:00","2022-03-21 18:00","2022-03-28 07:00","2022-03-28 18:00","연속"]
[110,"경기북부","고양","일산송포#2 T/L","154kV 일산-송포#2T/L 고정형 절연유 채취밸브 설치공사","활선OF 케이블용 고정형 절연유 채취밸브","2022-03-14 09:00","2022-03-18 18:00","취소","취소","연속"]
[111,"경기북부","고양","일산지도#2 T/L","고양전력지사 추락방지시설 설치공사","ㅇ 추락방지시설(와이어, 수직,수평) 설치","2022-03-21 07:00","2022-03-22 18:00","2022-03-28 07:00","2022-03-29 18:00","연속"]
[112,"경기북부","고양","일산송포#1 T/L","154kV 일산-송포#1T/L 고정형 절연유 채취밸브 설치공사","활선OF 케이블용 고정형 절연유 채취밸브","2022-03-02 09:00","2022-03-08 18:00","2022-02-28 09:00","2022-03-05 18:00","연속"]
[113,"경기북부","고양","지도능곡#1 T/L","154kV 지도-능곡#1T/L 선종교체공사","○ 지도S/S ~ #1S/J, #16S/J ~ 능곡S/S 구간 OF 케이블 → XLPE 케이블 선종교체공사","2022-03-28 09:00","2022-05-13 18:00","2022-03-30 09:00","2022-05-15 18:00","연속"]
[114,"경기북부","고양","일산호수#2 T/L","대한전선제 열경화공법 EBG 보강공사","154kV 일산-호수#2T/L 일산, 호수EBG 점검","2022-03-29 09:00","2022-03-31 18:00","취소","취소","연속"]
[115,"경기북부","고양","일산호수#1 T/L","대한전선제 열경화공법 EBG 보강공사","154kV 일산-호수#1T/L 일산, 호수EBG 점검","2022-03-24 09:00","2022-03-28 18:00","2022-02-28 09:00","2022-03-03 18:00","연속"]
[116,"경기북부","구리","가평화천HP T/L","송전선로 추락방지시설 설치공사","154kV 화천T/L 추락방지시설설치(No.70~135)","2022-03-21 08:00","2022-03-25 18:00","취소","취소","연속"]
[117,"경기북부","구리","내촌용정#2 T/L","154kV 신의정부-내촌 등 3개T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : No.2~5","2022-03-28 07:00","2022-03-29 18:00","2022-03-28 07:00","2022-03-29 18:00","연속"]
[118,"경기북부","구리","덕소S/S SEC CB 65660","22~23년 구리전력 변전협력 총액공사","덕소S/S 154kV #65-66 SEC GIS 하자점검","2022-03-16 14:00","2022-03-16 18:00","2022-03-16 14:00","2022-03-16 18:00","연속"]
[119,"경기북부","구리","덕소S/S SEC CB 60610","22~23년 구리전력 변전협력 총액공사","덕소S/S 154kV #60-61 SEC GIS 하자점검","2022-03-16 09:00","2022-03-16 14:00","2022-03-16 09:00","2022-03-16 14:00","연속"]
[120,"경기북부","구리","덕소S/S CB 6200","22~23년 구리전력 변전협력 총액공사","덕소S/S 154kV #61-66 BUSTIE GIS 하자점검","2022-03-15 14:00","2022-03-15 18:00","2022-03-15 14:00","2022-03-15 18:00","연속"]
[121,"경기북부","구리","덕소S/S CB 6100","22~23년 구리전력 변전협력 총액공사","덕소S/S 154kV #60-65 BUSTIE GIS 하자점검","2022-03-15 09:00","2022-03-15 14:00","2022-03-15 09:00","2022-03-15 14:00","연속"]
[122,"경기북부","구리","마석S/S CB 6100","22~23년 구리전력 변전협력 총액공사","마석S/S 154kV #60-65 BUSTIE GIS 보통점검","2022-03-17 09:00","2022-03-17 18:00","2022-03-17 09:00","2022-03-17 18:00","연속"]
[123,"경기북부","구리","미금S/S SEC CB 65660","22~23년 구리전력 변전협력 총액공사","미금S/S 154kV #65-66 SEC GIS 조작시험","2022-03-22 14:00","2022-03-22 18:00","2022-03-22 14:00","2022-03-22 18:00","연속"]
[124,"경기북부","구리","미금S/S SEC CB 60610","22~23년 구리전력 변전협력 총액공사","미금S/S 154kV #60-61 SEC GIS 조작시험","2022-03-22 09:00","2022-03-22 14:00","2022-03-22 09:00","2022-03-22 14:00","연속"]
[125,"경기북부","구리","별내S/S CB 6100","22~23년 구리전력 변전협력 총액공사","별내S/S 154kV #60-65 BUSTIE GIS 보통점검","2022-03-23 09:00","2022-03-23 18:00","2022-03-23 09:00","2022-03-23 18:00","연속"]
[126,"경기북부","구리","서종청평PP#2 T/L","'21-22년 지중송전설비 위탁정비공사","154kV 서종-청평PP#2T/L 서종C/T 피뢰기 점검 및 애관청소, PD집합반 설치","2022-03-30 09:00","2022-03-30 18:00","2022-03-30 09:00","2022-03-30 18:00","연속"]
[127,"경기북부","구리","동서울서종#1 T/L","154kV 동서울-서종T/L 지장송전선로 이설공사","ㅇ 철탑 1기 설치, 2기보강, 2기 철거 ㅇ 전선교체 0.652km","2022-03-28 07:00","2022-04-01 18:00","2022-03-27 07:00","2022-04-01 18:00","연속"]
[128,"경기북부","구리","동서울서종#2 T/L","154kV 동서울-서종T/L 지장송전선로 이설공사","ㅇ 철탑 1기 설치, 2기보강, 2기 철거 ㅇ 전선교체 0.652km","2022-03-19 07:00","2022-03-27 18:00","2022-03-19 07:00","2022-03-26 18:00","연속"]
[129,"경기북부","구리","동서울서종#1 T/L","154kV 동서울-서종T/L 지장송전선로 이설공사","ㅇ 철탑 1기 설치, 2기보강, 2기 철거 ㅇ 전선교체 0.652km","2022-03-19 07:00","2022-03-20 18:00","2022-03-19 07:00","2022-03-20 18:00","연속"]
[130,"경기북부","구리","신포천S/S CB 6100","22~23년 구리전력 변전협력 총액공사","신포천S/S 154kV #60-65 BUSTIE GIS 보통점검","2022-03-25 09:00","2022-03-25 14:00","2022-03-25 09:00","2022-03-25 14:00","연속"]
[131,"경기북부","구리","신포천S/S CB 6200","22~23년 구리전력 변전협력 총액공사","신포천S/S 154kV #61-66 BUSTIE GIS 보통점검","2022-03-25 14:00","2022-03-25 18:00","2022-03-25 14:00","2022-03-25 18:00","연속"]
[132,"경기북부","구리","신포천S/S SEC CB 65660","22~23년 구리전력 변전협력 총액공사","신포천S/S 154kV #65-66 SEC GIS 보통점검","2022-03-24 14:00","2022-03-24 18:00","2022-03-24 14:00","2022-03-24 18:00","연속"]
[133,"경기북부","구리","신포천S/S SEC CB 60610","22~23년 구리전력 변전협력 총액공사","신포천S/S 154kV #60-61 SEC GIS 보통점검","2022-03-24 09:00","2022-03-24 14:00","2022-03-24 09:00","2022-03-24 14:00","연속"]
[134,"경기북부","구리","서홍천청평PP T/L","청평양수 스위치야드 노후 154kV GIS 대체공사(전문)","o 154kV GIS x 5CCT 설치 o 기타 부대공사 1식","2022-03-02 08:00","2022-03-02 18:00","2022-03-18 08:00","2022-03-18 18:00","연속"]
[135,"경기북부","구리","포천운천#2 T/L","포천변전소 옥내화 공사","송전전력구 H-Pile 시공시 안전이격 확보","2022-03-14 10:00","2022-03-16 17:00","2022-03-14 10:00","2022-03-16 17:00","연속"]
[136,"경기북부","구리","포천운천#1 T/L","포천변전소 옥내화 공사","송전전력구 H-Pile 시공시 안전이격 확보","2022-03-17 10:00","2022-03-21 10:00","2022-03-17 10:00","2022-03-21 10:00","연속"]
[137,"경기북부","구리","신포천포천#1 T/L","포천변전소 옥내화 공사","송전전력구 H-Pile 시공시 안전이격 확보","2022-03-21 10:00","2022-03-23 17:00","2022-03-21 10:00","2022-03-23 17:00","연속"]
[138,"경기북부","구리","용정포천#1 T/L","포천변전소 옥내화 공사","송전전력구 H-Pile 시공시 안전이격 확보","2022-03-21 10:00","2022-03-23 17:00","2022-03-21 10:00","2022-03-23 17:00","연속"]
[139,"경기북부","구리","용정포천#2 T/L","154kV 포천S/S 옥내화 건설공사","○ 옥외철구 적외선 센서 설치 ○ 옥외철구 안전망 설치","2022-03-10 10:00","2022-03-16 17:00","2022-03-10 10:00","2022-03-16 17:00","연속"]
[140,"경기북부","구리","신포천포천#2 T/L","포천변전소 옥내화 공사","송전전력구 H-Pile 시공시 안전이격 확보","2022-03-10 10:00","2022-03-14 10:00","2022-03-10 10:00","2022-03-14 10:00","연속"]
[141,"경기북부","직할","남면백석#1 T/L","'21-22년 지중송전설비 위탁정비공사","154kV 남면-백석#1T/L 남백C/T 피뢰기 점검 및 애관 청소","2022-03-23 09:00","2022-03-23 18:00","2022-03-23 09:00","2022-03-23 18:00","연속"]
[142,"경기북부","직할","남면백석#2 T/L","'21-22년 지중송전설비 위탁정비공사","154kV 남면-백석#2T/L 남백C/T 피뢰기 점검 및 애관 청소","2022-03-24 09:00","2022-03-24 18:00","2022-03-24 09:00","2022-03-24 18:00","연속"]
[143,"경기북부","직할","신의정부내촌#1 T/L","154kV 신의정부-내촌 등 3개T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : No.46~64","2022-03-28 07:00","2022-04-01 18:00","2022-03-28 07:00","2022-04-01 18:00","연속"]
[144,"경기북부","직할","양주지축#1 T/L","고양전력지사 추락방지시설 설치공사","ㅇ 추락방지시설(와이어, 수직,수평) 설치","2022-03-17 07:00","2022-03-18 18:00","2022-03-24 07:00","2022-03-25 18:00","연속"]
[145,"경기북부","직할","양주은평#1 T/L","고양전력지사 추락방지시설 설치공사","ㅇ 추락방지시설(와이어, 수직,수평) 설치","2022-03-14 07:00","2022-03-16 18:00","2022-03-21 07:00","2022-03-23 18:00","연속"]
[146,"경기북부","직할","양주지축#2 T/L","고양전력지사 추락방지시설 설치공사","ㅇ 추락방지시설(와이어, 수직,수평) 설치","2022-03-14 07:00","2022-03-16 18:00","2022-03-21 07:00","2022-03-23 18:00","연속"]
[147,"경기북부","직할","양주은평#2 T/L","고양전력지사 추락방지시설 설치공사","ㅇ 추락방지시설(와이어, 수직,수평) 설치","2022-03-17 07:00","2022-03-18 18:00","2022-03-24 07:00","2022-03-25 18:00","연속"]
[148,"경기","군포","시화중시화 T/L","시화SS 시화-성곡TL GIS 조작시험","시화SS 시화-성곡TL GIS 조작시험","2022-03-28 14:00","2022-03-28 18:00","2022-03-28 14:00","2022-03-28 18:00","연속"]
[149,"경기","군포","시화성곡 T/L","시화SS 시화-성곡TL GIS 조작시험","시화SS 시화-성곡TL GIS 조작시험","2022-03-28 09:00","2022-03-28 14:00","2022-03-28 09:00","2022-03-28 14:00","연속"]
[150,"경기","군포","시화중시화 T/L","154kV 중시화S/S SW 증설공사","154kV GIS 2CCT 증설(637,6B7) 무부하가압을 위한 휴전","2022-03-25 10:00","2022-03-26 10:00","2022-03-25 10:00","2022-03-26 10:00","연속"]
[151,"경기","군포","시화중시화 T/L","154kV 중시화S/S SW 증설공사","154kV GIS 2CCT 증설(637,6B7) 무부하가압을 위한 휴전","2022-03-19 10:00","2022-03-20 10:00","2022-03-19 10:00","2022-03-20 10:00","연속"]
[152,"경기","동부","감곡가남#1 T/L","22년 동부 변전정비 총액공사","가남:감곡-가남#1T/L(보통)","2022-03-12 09:30","2022-03-12 14:00","2022-03-12 09:30","2022-03-12 14:00","연속"]
[153,"경기","동부","이천가남#2 T/L","22년 동부 변전정비 총액공사","가남:이천-가남#2T/L(보통)","2022-03-13 09:30","2022-03-13 18:00","2022-03-13 09:30","2022-03-13 18:00","연속"]
[154,"경기","동부","감곡가남#2 T/L","22년 동부 변전정비 총액공사","가남:감곡-가남#2T/L(보통)","2022-03-12 14:00","2022-03-12 18:00","2022-03-12 14:00","2022-03-12 18:00","연속"]
[155,"경기","동부","곤지암초월#1 T/L","154kV 곤지암-초월 불량애자교체","154kV 곤지암-초월 불량애자교체(총 15기)","2022-03-14 08:00","2022-03-17 18:00","2022-03-14 08:00","2022-03-17 18:00","연속"]
[156,"경기","동부","곤지암초월#2 T/L","154kV 곤지암-초월 불량애자교체","154kV 곤지암-초월 불량애자교체(총 15기)","2022-03-21 08:00","2022-03-24 18:00","2022-03-21 08:00","2022-03-24 18:00","연속"]
[157,"경기","동부","산성수서#1 T/L","22년 동부 변전정비 총액공사","산성:산성-수서#1T/L(조작) 산성-수서#2T/L(조작)","2022-03-07 09:30","2022-03-07 14:00","2022-03-07 09:30","2022-03-07 14:00","연속"]
[158,"경기","동부","성현산성#2 T/L","22년 동부 변전정비 총액공사","산성:산성-성현#2T/L(조작) 산성-성현#3T/L(조작) 성현:산성-성현#2T/L(조작) 산성-성현#3T/L(보통)","2022-03-11 09:30","2022-03-11 14:00","2022-03-11 09:30","2022-03-11 14:00","연속"]
[159,"경기","동부","성현산성#3 T/L","22년 동부 변전정비 총액공사","산성:산성-성현#2T/L(조작) 산성-성현#3T/L(조작) 성현:산성-성현#2T/L(조작) 산성-성현#3T/L(보통)","2022-03-11 14:00","2022-03-11 18:00","2022-03-11 14:00","2022-03-11 18:00","연속"]
[160,"경기","동부","성현산성#1 T/L","22년 동부 변전정비 총액공사","산성:산성-성현#1T/L(조작) 성현:산성-성현#1T/L (보통,전자변교체(H))","2022-03-10 09:30","2022-03-10 18:00","2022-03-10 09:30","2022-03-10 18:00","연속"]
[161,"경기","동부","산성수서#2 T/L","22년 동부 변전정비 총액공사","산성:산성-수서#1T/L(조작) 산성-수서#2T/L(조작)","2022-03-07 14:00","2022-03-07 18:00","2022-03-07 14:00","2022-03-07 18:00","연속"]
[162,"경기","동부","초월성현#2 T/L","22년 동부 변전정비 총액공사","성현:초월-성현#2T/L(조작) 초월:초월-성현#2T/L (보통,전자변교체(H))","2022-03-08 09:30","2022-03-08 18:00","2022-03-08 09:30","2022-03-08 18:00","연속"]
[163,"경기","동부","초월성현#1 T/L","22년 동부 변전정비 총액공사","성현:초월-성현#1T/L(조작) 초월:초월-성현#1T/L (보통,전자변교체(H))","2022-03-07 09:30","2022-03-07 18:00","2022-03-07 09:30","2022-03-07 18:00","연속"]
[164,"경기","동부","성현분당#1 T/L","154kV 성현-분당T/L 수평추락방지장치설치","154kV 성현-분당등 2개T/L 수평추락방지장치설치(57기)","2022-03-28 08:00","2022-03-31 18:00","2022-03-28 08:00","2022-03-31 18:00","연속"]
[165,"경기","동부","동판교야탑 T/L","22년 동부 변전정비 총액공사","야탑:동판교-야탑T/L(보통)","2022-03-04 09:30","2022-03-04 18:00","2022-03-04 09:30","2022-03-04 18:00","연속"]
[166,"경기","성남","기흥신갈#2 T/L","22년 성남전력지사 변전정비회사 총액공사","- GIS 하자점검","2022-03-21 09:00","2022-03-21 14:00","2022-03-21 09:00","2022-03-21 14:00","연속"]
[167,"경기","성남","신봉이의#2 T/L","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검","2022-03-17 14:00","2022-03-17 18:00","2022-03-17 14:00","2022-03-17 18:00","연속"]
[168,"경기","성남","신봉이의#1 T/L","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검","2022-03-17 09:00","2022-03-17 14:00","2022-03-17 09:00","2022-03-17 14:00","연속"]
[169,"경기","성남","신성남서판교 #3 T/L","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검","2022-03-11 09:00","2022-03-11 18:00","2022-03-11 09:00","2022-03-11 18:00","연속"]
[170,"경기","성남","신수원S/S #60 BUS","신수원S/S 154kV 신규수용공사(린데코리아)","170kV GIS 1CCT 설치","2022-03-28 08:00","2022-04-06 18:00","2022-03-28 08:00","2022-04-06 18:00","연속"]
[171,"경기","성남","신용인S/S SEC CB 65660","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검","2022-03-07 14:00","2022-03-07 18:00","2022-03-07 14:00","2022-03-07 18:00","연속"]
[172,"경기","성남","신용인S/S SEC CB 60610","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검","2022-03-07 09:00","2022-03-07 14:00","2022-03-07 09:00","2022-03-07 14:00","연속"]
[173,"경기","직할","과천동안양#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","동안양S/S 과천-동안양#2T/L VCB 보통점검, 피뢰기 대체","2022-03-22 10:00","2022-03-22 18:00","2022-03-22 10:00","2022-03-22 18:00","연속"]
[174,"경기","직할","의왕동안양#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","동안양S/S 의왕-동안양#2T/L VCB 공압부 내부점검, 피뢰기 대체","2022-03-21 10:00","2022-03-21 18:00","2022-03-21 10:00","2022-03-21 18:00","연속"]
[175,"경기","직할","서서울서수원#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","서수원S/S 서서울-서수원#1T/L GIS 보통점검, LA,CVT 보통점검","2022-03-28 10:00","2022-03-28 18:00","2022-03-28 10:00","2022-03-28 18:00","연속"]
[176,"경기","직할","서서울서수원#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","서수원S/S 서서울-서수원#2T/L GIS 보통점검, LA,CVT 보통점검","2022-03-29 10:00","2022-03-29 18:00","2022-03-29 10:00","2022-03-29 18:00","연속"]
[177,"경기","직할","서서울율전#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","율전S/S 서서울-율전#1,2T/L GIS 조작시험","2022-03-04 10:00","2022-03-04 14:00","2022-03-04 10:00","2022-03-04 14:00","연속"]
[178,"경기","직할","율전의왕#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","율전S/S 율전-의왕#1,2T/L GIS 조작시험","2022-03-08 14:00","2022-03-08 18:00","2022-03-08 14:00","2022-03-08 18:00","연속"]
[179,"경기","직할","서서울율전#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","율전S/S 서서울-율전#1,2T/L GIS 조작시험","2022-03-04 14:00","2022-03-04 18:00","2022-03-04 14:00","2022-03-04 18:00","연속"]
[180,"경기","직할","율전의왕#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","율전S/S 율전-의왕#1,2T/L GIS 조작시험","2022-03-08 10:00","2022-03-08 14:00","2022-03-08 10:00","2022-03-08 14:00","연속"]
[181,"경기","직할","화성남양#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","화성S/S 화성-남양#1,2T/L GIS 조작시험","2022-03-05 14:00","2022-03-05 18:00","2022-03-05 14:00","2022-03-05 18:00","연속"]
[182,"경기","직할","화성남양#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","화성S/S 화성-남양#1,2T/L GIS 조작시험","2022-03-05 10:00","2022-03-05 14:00","2022-03-05 10:00","2022-03-05 14:00","연속"]
[183,"경기","평택","고덕S/S #60 BUS","고덕S/S 154kV 고덕-평택#1T/L DS 조작기 개선","고덕S/S 154kV 고덕-평택#1T/L DS 리바운딩현상 관련 조작기 개선","2022-03-21 09:00","2022-03-21 13:00","2022-03-21 09:00","2022-03-21 13:00","연속"]
[184,"경기","평택","고덕평택#1 T/L","고덕S/S 154kV 고덕-평택#1T/L DS 조작기 개선","*고덕S/S 154kV 고덕-평택#1T/L DS 리바운딩 현상관련 조작기 개선","2022-03-21 09:00","2022-03-21 18:00","2022-03-21 09:00","2022-03-21 18:00","연속"]
[185,"경기","평택","고덕진위#2 T/L","22년 평택전력지사 변전협력회사 총액공사","*고덕S/S 154kV 고덕-진위#2T/L GIS 보통점검","2022-03-18 10:00","2022-03-18 18:00","2022-03-18 10:00","2022-03-18 18:00","연속"]
[186,"경기","평택","고덕진위#1 T/L","22년 평택전력지사 변전협력회사 총액공사","*고덕S/S 고덕-진위#1T/L GIS 보통점검","2022-03-17 10:00","2022-03-17 18:00","2022-03-17 10:00","2022-03-17 18:00","연속"]
[187,"경기","평택","고덕평택#2 T/L","154kV 고덕#2-평택,동평택 지중T/L 인출정비공사","1. 공사목적 : 345kV 고덕2S/S 건설에 따른 계통 보강 2. 공사구간 : 345kV 고덕2S/S ～ 154kV 고덕-평택, 동평택T/L J/B#1 3. 선종 및 회선길이 - 고덕2-평택 : 154kV XLPE 1200㎟ 2회선(D)-0.0435㎞ - 고덕2-동평택 : 154kV XLPE 1200㎟ 2회선-0.438㎞","2022-03-09 09:00","2022-03-31 18:00","취소","취소","연속"]
[188,"경기","평택","고덕S/S #65 BUS","고덕S/S 154kV 고덕-평택#2T/L DS 조작기 개선","고덕S/S 154kV 고덕-평택#2T/L DS 리바운딩현상 관련 조작기 개선","2022-03-22 13:00","2022-03-22 17:00","2022-03-22 13:00","2022-03-22 17:00","연속"]
[189,"경기","평택","고덕평택#2 T/L","고덕S/S 154kV 고덕-평택#2T/L DS 조작기 개선","*고덕S/S 154kV 고덕-평택#2T/L DS 리바운딩현상 관련 조작기 개선","2022-03-22 09:00","2022-03-22 18:00","2022-03-22 09:00","2022-03-22 18:00","연속"]
[190,"경기","평택","고덕S/S #60 BUS","고덕S/S 154kV 고덕-평택#2T/L DS 조작기 개선","고덕S/S 154kV 고덕-평택#2T/L DS 리바운딩현상 관련 조작기 개선","2022-03-22 09:00","2022-03-22 13:00","2022-03-22 09:00","2022-03-22 13:00","연속"]
[191,"경기","평택","고덕S/S #65 BUS","고덕S/S 154kV 고덕-평택#1T/L DS 조작기 개선","고덕S/S 154kV 고덕-평택#1T/L DS 리바운딩현상 관련 조작기 개선","2022-03-21 13:00","2022-03-21 17:00","2022-03-21 13:00","2022-03-21 17:00","연속"]
[192,"경기","평택","오산향남#2 T/L","22년 평택전력지사 변전협력회사 총액공사","오산S/S 154kV 오산-향남#2T/L GIS 보통점검","2022-03-08 10:00","2022-03-08 18:00","2022-03-08 10:00","2022-03-08 18:00","연속"]
[193,"경기","평택","오산향남#1 T/L","22년 평택전력지사 변전협력회사 총액공사","오산S/S 154kV 오산-향남#1T/L GIS 보통점검","2022-03-07 10:00","2022-03-07 18:00","2022-03-07 10:00","2022-03-07 18:00","연속"]
[194,"경기","평택","둔포추팔#2 T/L","22년 평택전력지사 변전협력회사 총액공사","추팔S/S 154kV 둔포-추팔#2T/L GIS 보통점검 및 LA 보통점검","2022-03-29 10:00","2022-03-29 18:00","2022-03-29 10:00","2022-03-29 18:00","연속"]
[195,"경기","평택","둔포추팔#1 T/L","22년 평택전력지사 변전협력회사 총액공사","추팔S/S 154kV 둔포-추팔#1T/L GIS 보통점검 및 LA 보통점검","2022-03-28 10:00","2022-03-28 18:00","2022-03-28 10:00","2022-03-28 18:00","연속"]
[196,"경기","평택","오산평택#1 T/L","22년 평택전력지사 변전협력회사 총액공사","*평택S/S 오산-평택#1T/L GCB 보통점검 및 PT,LA 보통점검","2022-03-11 10:00","2022-03-11 18:00","2022-03-11 10:00","2022-03-11 18:00","연속"]
[197,"경기","평택","청북평택#1 T/L","22년 평택전력지사 변전협력회사 총액공사","*평택S/S 154kV 청북-평택#1T/L GCB 보통점검 및 PT,LA 보통점검","2022-03-24 10:00","2022-03-24 18:00","2022-03-24 10:00","2022-03-24 18:00","연속"]
[198,"경기","평택","평택추팔#1 T/L","22년 평택전력지사 변전협력회사 총액공사","평택S/S 154kV 평택-추팔#1T/L GCB 보통점검","2022-03-25 10:00","2022-03-25 18:00","2022-03-25 10:00","2022-03-25 18:00","연속"]
[199,"경기","평택","오산평택#2 T/L","22년 평택전력지사 변전협력회사 총액공사","*평택S/S 154kV 오산-평택#2T/L GCB 보통점검 및 PT,LA 보통점검","2022-03-18 10:00","2022-03-18 18:00","2022-03-18 10:00","2022-03-18 18:00","연속"]
[200,"경기","평택","포승청북 T/L","22년 평택전력지사 변전협력회사 총액공사","포승S/S 154kV 포승-청북T/L 보호반 대체","2022-03-14 10:00","2022-03-16 18:00","2022-03-14 10:00","2022-03-16 18:00","연속"]
[201,"강원","강릉","속초간성#1 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 병가구간 휴전 : 154kV 간성-인제 #2T/L No.142~144","2022-03-31 07:00","2022-03-31 18:00","2022-03-31 07:00","2022-03-31 18:00","연속"]
[202,"강원","강릉","간성인제#2 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 간성-인제 #2T/L No.142~144","2022-03-31 07:00","2022-03-31 18:00","2022-03-31 07:00","2022-03-31 18:00","연속"]
[203,"강원","강릉","강릉영동TP T/L","154kV 강릉T/L No.28-32 안전이격거리 확보공사","○ 철탑 신설 3기, 철거 3기, 전력선교체 No.28-32, OPGW교체 No.28-32, 애자금구류 교체 및 피뢰기 설치 No.29,30,31","2022-03-14 08:00","2022-03-22 18:00","취소","취소","연속"]
[204,"강원","강릉","동해강릉 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 동해-강릉T/L No.55~67","2022-03-10 07:00","2022-03-11 18:00","취소","취소","매일"]
[205,"강원","강릉","동해강릉 T/L","154kV 강릉T/L No.28-32 안전이격거리 확보공사","○ 철탑 신설 3기, 철거 3기, 전력선교체 No.28-32, OPGW교체 No.28-32, 애자금구류 교체 및 피뢰기 설치 No.29,30,31","2022-03-14 08:00","2022-03-22 18:00","취소","취소","연속"]
[206,"강원","강릉","북강릉주문진#2 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 북강릉주문진 #2T/L No.1~55","2022-03-12 07:00","2022-03-16 18:00","2022-03-12 07:00","2022-03-16 18:00","매일"]
[207,"강원","강릉","신양양인제#2 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 신양양-인제 #2T/L No.3~6","2022-03-06 07:00","2022-03-06 18:00","취소","취소","연속"]
[208,"강원","강릉","신양양속초#1 T/L","2022~2023년 가공송전협력회사 총액공사","○ 항공장애표시구 설치 - 154kV 신양양속초T/L No.30~31(적4, 백3)","2022-03-22 08:00","2022-03-22 12:00","취소","취소","연속"]
[209,"강원","강릉","신양양양양#2 T/L","2022~2023년 가공송전협력회사 총액공사","○ 항공장애표시구 설치(작업자 안전을 위한 4회선구간 휴전) - 154kV 신양양속초T/L No.30~31(적4, 백3)","2022-03-22 08:00","2022-03-22 12:00","취소","취소","연속"]
[210,"강원","강릉","신양양속초#2 T/L","2022~2023년 가공송전협력회사 총액공사","○ 항공장애표시구 설치 - 154kV 신양양속초T/L No.30~31(적4, 백3)","2022-03-22 12:00","2022-03-22 18:00","취소","취소","연속"]
[211,"강원","강릉","신양양양양#1 T/L","2022~2023년 가공송전협력회사 총액공사","○ 항공장애표시구 설치(작업자 안전을 위한 4회선구간 휴전) - 154kV 신양양속초T/L No.30~31(적4, 백3)","2022-03-22 12:00","2022-03-22 18:00","취소","취소","연속"]
[212,"강원","강릉","신양양인제#1 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 신양양인제 #1T/L No.3~6","2022-03-07 07:00","2022-03-07 18:00","취소","취소","연속"]
[213,"강원","강릉","강릉영동TP T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 병가구간 작업을 위한 휴전 : 154kV 강릉횡계#2 T/L No. 11~36","2022-03-07 07:00","2022-03-08 18:00","취소","취소","매일"]
[214,"강원","강릉","주문진양양#1 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 병가구간 휴전 : 154kV 북강릉-주문진 #2T/L No.1~55 피뢰기 설치","2022-03-12 07:00","2022-03-13 18:00","2022-03-12 07:00","2022-03-13 18:00","매일"]
[215,"강원","강릉","주진평창#1 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 주진평창 #1T/L No.1~57","2022-03-25 07:00","2022-03-30 18:00","2022-03-25 07:00","2022-03-30 18:00","매일"]
[216,"강원","강릉","평창올림픽 T/L","2022 변전협력회사 총액공사","평창S/S 170kV GIS, LA, PT 보통점검","2022-03-23 10:00","2022-03-23 18:00","2022-03-23 10:00","2022-03-23 18:00","연속"]
[217,"강원","강릉","횡계올림픽 T/L","2022 변전협력회사 총액공사","170kV GIS 보통점검","2022-03-21 10:00","2022-03-21 18:00","2022-03-21 10:00","2022-03-21 18:00","연속"]
[218,"강원","강릉","강릉횡계#2 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 강릉횡계 #2T/L No.11~36","2022-03-07 07:00","2022-03-11 18:00","2022-03-07 07:00","2022-03-11 18:00","매일"]
[219,"강원","강릉","강릉횡계#1 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 병가구간 작업을 위한 휴전 : 154kV 동해-강릉T/L No.64~66-2","2022-03-11 07:00","2022-03-11 18:00","2022-03-11 07:00","2022-03-11 18:00","연속"]
[220,"강원","강릉","횡계평창 T/L","2022 변전협력회사 총액공사","횡계S/S 170kV GIS 보통점검 - 병행 : 평창S/S 170kV GIS, LA, PT 보통점검","2022-03-22 10:00","2022-03-22 18:00","2022-03-22 10:00","2022-03-22 18:00","연속"]
[221,"강원","원주","신제천남원주#1 T/L","154kV 신제천-남원주T/L No.42~46 안전이격 확보공사","- 철탑 교체 4기(42,43,45,46호) [인클로징] - 전력선 교체 6경간(40~46호) 2C-1.924km - 가공지선 신설(42~43호,45~46호) 1C-0.399km","2022-03-19 08:00","2022-03-28 18:00","2022-03-19 08:00","2022-03-28 18:00","연속"]
[222,"강원","원주","신제천남원주#2 T/L","154kV 신제천-남원주T/L No.42~46 안전이격 확보공사","- 철탑 교체 4기(42,43,45,46호) [인클로징] - 전력선 교체 6경간(40~46호) 2C-1.924km - 가공지선 신설(42~43호,45~46호) 1C-0.399km","2022-03-19 08:00","2022-03-28 18:00","2022-03-19 08:00","2022-03-28 18:00","연속"]
[223,"강원","원주","신제천남원주#1 T/L","154kV 신제천-남원주T/L No.42~46 안전이격 확보공사","- 철탑 교체 4기(42,43,45,46호) [인클로징] - 전력선 교체 6경간(40~46호) 2C-1.924km - 가공지선 신설(42~43호,45~46호) 1C-0.399km","2022-03-29 08:00","2022-04-03 18:00","2022-03-29 08:00","2022-04-03 18:00","연속"]
[224,"강원","직할","남춘천춘천열병합#2 T/L","피뢰기 및 추락방지장치 설치공사","154kV 남춘천-춘천열병합#2T/L 피뢰기, 추락방지장치 설치 154kv 서홍천-춘천열병합 병행작업 안전확보","2022-03-02 00:08","2022-03-06 18:00","2022-03-03 00:08","2022-03-08 18:00","매일"]
[225,"강원","직할","남춘천춘천열병합#1 T/L","피뢰기 및 추락방지장치 설치공사","154kV 청평PP-춘천열병합 병행작업 안전확보","2022-03-07 08:00","2022-03-18 18:00","2022-03-10 08:00","2022-03-16 18:00","매일"]
[226,"강원","직할","남춘천춘천 T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","154kV 남춘천-춘천T/L 전선교체 45C-km 154kV 남춘천-춘천T/L 추락방지장치 설치","2022-03-14 09:00","2022-08-03 18:00","취소","취소","연속"]
[227,"강원","직할","서홍천춘천열병합 T/L","2022년 가공송전선로 순시점검 위탁공사 정밀점검","154kV 서홍천-춘천열병합T/L 정밀점검 154kV 청평양수, 남춘천-춘천열병합 피뢰기 및 추락방지장치 설치","2022-03-02 08:00","2022-03-06 18:00","2022-03-03 00:08","2022-03-08 18:00","매일"]
[228,"강원","직할","청평PP춘천열병합 T/L","2022년 가공송전선로 순시점검 위탁공사 정밀점검","154kV 청평PP-춘천열병합T/L 정밀점검 시행 피뢰기 및 수직수평추락방지장치 설치","2022-03-07 08:00","2022-03-13 18:00","2022-03-10 08:00","2022-03-16 18:00","매일"]
[229,"강원","직할","철원화천#2 T/L","피뢰기 및 추락방지장치 설치공사_직할","철원-화천#1,2T/L No.1~13,41~49,77~103 (동시휴전) 피뢰기 설치 156set, 추락방지장치 51기, 아킹혼철거 156set","2022-03-16 08:00","2022-03-29 18:00","2022-03-16 08:00","2022-03-29 18:00","매일"]
[230,"강원","직할","철원화천#1 T/L","피뢰기 및 추락방지장치 설치공사_직할","철원-화천#1,2T/L No.1~13,41~49,77~103 (동시휴전) 피뢰기 설치 156set, 추락방지장치 51기, 아킹혼철거 156set","2022-03-30 08:00","2022-04-05 18:00","2022-03-30 08:00","2022-04-05 18:00","매일"]
[231,"강원","태백","동해동영월 T/L","2021년 가공송전 순시점검 위탁공사","154kV 동해-동영월T/L 정밀점검","2022-03-14 08:00","2022-03-15 18:00","2022-03-14 08:00","2022-03-15 18:00","연속"]
[232,"강원","태백","동영월영월CC T/L","22-23년 태백전력지사 변전정비회사 총액공사","동영월S/S 154kV 동영월-영월CCT/L 보호반 교체공사 [병행,송전] 154kV 동영월-영월CCT/L 정밀점검(03/16~03/17)","2022-03-16 10:00","2022-03-25 18:00","2022-03-16 10:00","2022-03-25 18:00","연속"]
[233,"강원","태백","신제천영월CC#2 T/L","22-23년 태백전력지사 변전정비회사 총액공사","영월CC 154kV 신제천-영월CC#2T/L GIS 보통점검","2022-03-11 10:00","2022-03-11 18:00","2022-03-11 10:00","2022-03-11 18:00","연속"]
[234,"강원","태백","신제천영월CC#1 T/L","22-23년 태백전력지사 변전정비회사 총액공사","영월CC 154kV 신제천-영월CC#1T/L GIS 보통점검","2022-03-04 10:00","2022-03-04 18:00","2022-03-04 10:00","2022-03-04 18:00","연속"]
[235,"충북","직할","서운광혜원 T/L","22년도 충북직할 변전협력회사 총액공사","서운-광혜원T/L GIS 보통점검","2022-03-14 09:00","2022-03-14 18:00","2022-03-14 09:00","2022-03-14 18:00","연속"]
[236,"충북","직할","광혜원S/S CB 6200","22년도 충북직할 변전협력회사 총액공사","#61-#66 BUS TIE GIS 보통점검","2022-03-16 09:00","2022-03-16 18:00","취소","취소","연속"]
[237,"충북","직할","신진천오창#2 T/L","추락방지시설 설치공사","신진천오창#2T/L 추락방지시설 설치공사","2022-03-12 07:30","2022-03-12 18:00","2022-03-12 07:30","2022-03-12 18:00","연속"]
[238,"충북","직할","신진천진천#1 T/L","추락방지시설 설치공사","신진천진천#1T/L 추락방지시설 설치공사","2022-03-12 07:30","2022-03-12 18:00","취소","취소","연속"]
[239,"충북","직할","신진천오창#1 T/L","추락방지시설 설치공사","추락방지시설 설치공사","2022-03-13 07:30","2022-03-13 18:00","2022-03-13 07:30","2022-03-13 18:00","연속"]
[240,"충북","직할","신진천진천#2 T/L","추락방지시설 설치공사","추락방지시설 설치공사","2022-03-13 07:30","2022-03-13 18:00","취소","취소","연속"]
[241,"충북","직할","신진천S/S SEC CB 60610","22년도 충북직할 변전협력회사 총액공사","#60-#61 SEC GIS 보통점검","2022-03-24 09:00","2022-03-24 18:00","2022-03-24 09:00","2022-03-24 18:00","연속"]
[242,"충북","청주","남청주오송#1 T/L","송전선로 보호반 노후교체","[22-23 청주전력 변전정비 총액공사] 154kV 남청주-오송#1T/L 송전선로 보호반 노후교체","2022-03-14 09:00","2022-03-17 18:00","취소","취소","연속"]
[243,"충북","청주","서청주사직#2 T/L","송전선로 보호반 노후교체 및 GIS 보통점검","[22-23 청주전력 변전정비 총액공사] 154kV 서청주-사직#2T/L 송전선로 보호반 노후교체 사직측 170kV GIS 보통점검","2022-03-28 09:00","2022-03-31 18:00","2022-03-28 09:00","2022-03-31 18:00","연속"]
[244,"충북","청주","사직북청주#2 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 보통점검","2022-03-25 10:00","2022-03-25 18:00","2022-03-25 10:00","2022-03-25 18:00","연속"]
[245,"충북","청주","신옥천남대전#2 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검","2022-03-11 10:00","2022-03-11 18:00","취소","취소","연속"]
[246,"충북","청주","신옥천남대전#1 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검","2022-03-10 10:00","2022-03-10 18:00","취소","취소","연속"]
[247,"충북","청주","신옥천남대전#3 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검","2022-03-14 10:00","2022-03-14 18:00","취소","취소","연속"]
[248,"충북","청주","신옥천남대전#4 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검","2022-03-15 10:00","2022-03-15 18:00","취소","취소","연속"]
[249,"충북","충주","감곡가남#1 T/L","추락방지시설 설치공사","감곡가남#1T/L 추락방지지설 설치공사","2022-03-26 07:30","2022-03-26 18:00","취소","취소","연속"]
[250,"충북","충주","감곡가남#2 T/L","추락방지시설 설치공사","감곡가남#2T/L 추락방지시설 설치공사","2022-03-20 07:30","2022-03-20 18:00","취소","취소","연속"]
[251,"충북","충주","금왕남음성#2 T/L","22-23년 충주전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2022-03-16 14:00","2022-03-16 18:00","취소","취소","연속"]
[252,"충북","충주","남음성덕산#1 T/L","22-23년 충주전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2022-03-17 10:00","2022-03-17 14:00","취소","취소","연속"]
[253,"충북","충주","남음성덕산#2 T/L","22-23년 충주전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2022-03-17 14:00","2022-03-17 18:00","취소","취소","연속"]
[254,"충북","충주","금왕남음성#1 T/L","22-23년 충주전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2022-03-16 10:00","2022-03-16 14:00","취소","취소","연속"]
[255,"충북","충주","신충주북충주#2 T/L","22-23년 충주전력지사 변전협력회사 총액공사","170kV GIS 보통점검(양단)","2022-03-07 09:30","2022-03-07 18:00","2022-03-07 09:30","2022-03-07 18:00","연속"]
[256,"충북","충주","신충주감곡#1 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주감곡#1T/L 정밀점검","2022-03-14 07:30","2022-03-25 18:00","취소","취소","매일"]
[257,"충북","충주","신충주음성#2 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주음성#2T/L 정밀점검","2022-03-14 07:30","2022-03-18 18:00","취소","취소","매일"]
[258,"충북","충주","신충주음성#2 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주음성#2T/L 정밀점검","2022-03-28 09:00","2022-04-01 18:00","취소","취소","매일"]
[259,"충북","충주","신충주감곡#2 T/L","추락방지시설 설치공사","신충주감곡#2T/L 추락방지시설 설치공사","2022-03-26 07:30","2022-03-26 18:00","취소","취소","연속"]
[260,"충북","충주","왕암여주#1 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주감곡#1T/L 정밀점검 (병가선로)","2022-03-21 09:00","2022-03-22 18:00","취소","취소","매일"]
[261,"충북","충주","음성금왕#2 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","정밀점검","2022-03-28 09:00","2022-03-29 18:00","취소","취소","매일"]
[262,"충북","충주","북충주충주 T/L","22-23년 충주전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2022-03-03 09:30","2022-03-03 16:00","2022-03-03 09:30","2022-03-03 16:00","연속"]
[263,"대전세종충남","대전","신옥천남대전#4 T/L","[송전] 154kV 신옥천-남대전삼사T/L 정밀점검","[송전] 154kV 신옥천-남대전삼사#4T/L 정밀점검","2022-03-31 08:00","2022-04-04 18:00","취소","취소","매일"]
[264,"대전세종충남","대전","신옥천남대전#3 T/L","[송전] 154kV 신옥천-남대전삼사T/L 정밀점검","[송전] 154kV 신옥천-남대전삼사#3T/L 정밀점검","2022-03-28 08:00","2022-03-30 18:00","취소","취소","매일"]
[265,"대전세종충남","대전","신계룡두마#1 T/L","[송전] 345kV 신옥천-청양T/L 등 17개T/L 추락방지장치 설치","[송전] 345kV 신계룡-두마T/L 추락방지장치 설치공사","2022-03-30 08:00","2022-03-30 18:00","2022-03-30 08:00","2022-03-30 18:00","연속"]
[266,"대전세종충남","대전","신계룡두마#2 T/L","[송전] 154kV 가수원-서대전 등 6개T/L 피뢰기 설치공사","[송전] 154kV 신계룡-두마#2T/L 피뢰기 설치","2022-03-31 08:00","2022-03-31 12:00","2022-03-31 08:00","2022-03-31 12:00","연속"]
[267,"대전세종충남","서산","대산석문#1 T/L","154kV 대산-석문 T/L 안전이격확보공사","154kV 대산-석문 T/L 안전이격확보공사 -No.12~18","2022-03-15 08:00","2022-03-18 18:00","2022-03-16 08:00","2022-03-23 18:00","연속"]
[268,"대전세종충남","서산","대산석문#2 T/L","154kV 대산-석문 T/L 안전이격확보공사","154kV 대산-석문 T/L 안전이격확보공사 -No.12~18","2022-03-02 08:00","2022-03-14 18:00","2022-03-03 08:00","2022-03-15 18:00","연속"]
[269,"대전세종충남","서산","대산석문#1 T/L","154kV 대산-석문 T/L 안전이격확보공사","154kV 대산-석문 T/L 안전이격확보공사 -No.12~18","2022-03-02 08:00","2022-03-04 18:00","2022-03-02 08:00","2022-03-02 18:00","연속"]
[270,"대전세종충남","서산","당진송악#1 T/L","22년 서산P/O 변전협력회사 총액공사","송악S/S 154kV 당진-송악#1T/L GIS 보통점검, LA 대체","2022-03-02 10:00","2022-03-02 18:00","2022-03-02 10:00","2022-03-02 18:00","연속"]
[271,"대전세종충남","서산","당진송악#2 T/L","22년 서산P/O 변전협력회사 총액공사","송악S/S 154kV 당진-송악#2T/L GIS 보통점검, LA 대체","2022-03-03 10:00","2022-03-03 18:00","2022-03-03 10:00","2022-03-03 18:00","연속"]
[272,"대전세종충남","서산","신당진S/S CB 6100","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -BUS-TIE 교체","2022-03-21 08:00","2022-04-08 18:00","취소","취소","연속"]
[273,"대전세종충남","서산","신당진당진#1 T/L","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -신당진-당진#1T/L 교체","2022-03-21 08:00","2022-04-08 18:00","취소","취소","연속"]
[274,"대전세종충남","서산","신당진서산#1 T/L","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -65BUS 무부하가압(종카바)","2022-03-22 12:00","2022-03-22 13:00","취소","취소","연속"]
[275,"대전세종충남","서산","신당진서산#1 T/L","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 - #60BUS 무부하가압","2022-03-29 13:00","2022-03-30 13:00","취소","취소","연속"]
[276,"대전세종충남","서산","신당진S/S #65 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 - DS 6102, 642 철거,설치","2022-03-30 13:00","2022-04-08 18:00","취소","취소","연속"]
[277,"대전세종충남","서산","신당진S/S #65 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","신당진-당진#1T/L, #60-65BUS-TIE, #1M.Tr 2차 GIS 교체","2022-03-21 08:00","2022-03-22 13:00","취소","취소","연속"]
[278,"대전세종충남","서산","신당진S/S #60 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -DS 6101, 641 철거,설치 -CB 6100, 647 설치","2022-03-22 13:00","2022-03-30 13:00","취소","취소","연속"]
[279,"대전세종충남","서산","신당진S/S #61 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 - #60BUS 무부하가압","2022-03-29 13:00","2022-03-30 13:00","취소","취소","연속"]
[280,"대전세종충남","서산","신당진S/S #66 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -65BUS 무부하가압","2022-03-22 12:00","2022-03-22 13:00","취소","취소","연속"]
[281,"대전세종충남","서산","태안안면#2 T/L","22년 서산P/O 변전협력회사 총액공사","태안S/S 154kV 태안-안면#2T/L GIS 보통점검","2022-03-21 10:00","2022-03-21 18:00","취소","취소","연속"]
[282,"대전세종충남","서산","서산태안 T/L","22년 서산P/O 170kV GIS 정밀점검","서산S/S 154kV 서산-태안T/L GIS(637) 정밀점검","2022-03-21 10:00","2022-03-23 18:00","2022-03-12 09:00","2022-03-13 18:00","연속"]
[283,"대전세종충남","서산","서산태안화력 T/L","22년 서산P/O 변전협력회사 총액공사","태안T/P 154kV 서산-태안화력T/L GIS (617) 보통점검 및 LA 대체","2022-03-31 10:00","2022-03-31 18:00","2022-03-31 10:00","2022-03-31 18:00","연속"]
[284,"대전세종충남","서산","해미홍성 T/L","22년 서산P/O 170kV GIS 정밀점검","해미S/S 154kV 해미-홍성T/L GIS(637) 정밀점검","2022-03-30 14:00","2022-04-01 18:00","2022-03-19 09:00","2022-03-20 18:00","연속"]
[285,"대전세종충남","서산","서산해미 T/L","22년 서산P/O 170kV GIS 정밀점검","해미S/S 154kV 서산-해미T/L GIS(617) 정밀점검","2022-03-28 10:00","2022-03-30 14:00","2022-03-26 09:00","2022-03-27 18:00","연속"]
[286,"대전세종충남","세종","덕진공주#1 T/L","[변전]2022년 세종PO 변전협력회사 총액공사","공주S/S 덕진-공주#1T/L GIS 보통점검 덕진S/S 덕진-공주#1T/L GIS 조작시험","2022-03-02 09:00","2022-03-02 18:00","취소","취소","연속"]
[287,"대전세종충남","세종","신풍공주#2 T/L","[변전]2022년 세종PO 변전협력회사 총액공사","공주S/S 신풍-공주#2T/L GIS 보통점검","2022-03-04 14:00","2022-03-04 18:00","2022-03-04 14:00","2022-03-04 18:00","연속"]
[288,"대전세종충남","세종","신풍공주#1 T/L","[변전]2022년 세종PO 변전협력회사 총액공사","공주S/S 신풍-공주#1T/L GIS 보통점검","2022-03-04 09:00","2022-03-04 14:00","2022-03-04 09:00","2022-03-04 14:00","연속"]
[289,"대전세종충남","세종","덕진공주#2 T/L","[변전]2022년 세종PO 변전협력회사 총액공사","공주S/S 덕진-공주#2T/L GIS 보통점검 덕진S/S 덕진-공주#2T/L GIS 조작시험","2022-03-03 09:00","2022-03-03 18:00","취소","취소","연속"]
[290,"대전세종충남","세종","덕진대화#1 T/L","154kV 덕진-대화T/L 철탑 추락방지시설 설치공사","[송전] 154kV 덕진-대화#1T/L 철탑 추락방지시설 설치 - No.2~21호(20기)","2022-03-14 07:00","2022-03-17 18:00","2022-03-14 07:00","2022-03-17 18:00","매일"]
[291,"대전세종충남","세종","덕진대화#2 T/L","154kV 덕진-대화T/L 철탑 추락방지시설 설치공사","[송전] 154kV 덕진-대화#2T/L 철탑 추락방지시설 설치 - No.2~21호(20기)","2022-03-18 07:00","2022-03-21 18:00","2022-03-18 07:00","2022-03-21 18:00","매일"]
[292,"대전세종충남","세종","덕진유성#2 T/L","[변전]2022년 세종PO 변전협력회사 총액공사","덕진S/S 덕진-유성#2T/L GIS 보통점검","2022-03-11 14:00","2022-03-11 18:00","취소","취소","연속"]
[293,"대전세종충남","세종","대덕덕진#1 T/L","[변전]2022년 세종PO 변전협력회사 총액공사","덕진S/S 대덕-덕진#1T/L GIS 보통점검","2022-03-11 09:00","2022-03-11 14:00","취소","취소","연속"]
[294,"대전세종충남","세종","세종둔곡#1 T/L","[변전]2022년 세종PO 변전협력회사 총액공사","*둔곡S/S 154kV 세종-둔곡#1T/L GIS 하자점검","2022-03-14 09:00","2022-03-14 14:00","2022-03-14 09:00","2022-03-14 14:00","연속"]
[295,"대전세종충남","세종","둔곡송강#1 T/L","[변전]2022년 세종PO 변전협력회사 총액공사","*둔곡S/S 154kV 둔곡-송강#1T/L GIS 하자점검","2022-03-16 09:00","2022-03-16 14:00","2022-03-16 09:00","2022-03-16 14:00","연속"]
[296,"대전세종충남","세종","둔곡송강#2 T/L","[변전]2022년 세종PO 변전협력회사 총액공사","*둔곡S/S 154kV 둔곡-송강#2T/L GIS 하자점검","2022-03-17 09:00","2022-03-17 14:00","2022-03-17 09:00","2022-03-17 14:00","연속"]
[297,"대전세종충남","세종","세종둔곡#2 T/L","[변전]2022년 세종PO 변전협력회사 총액공사","*둔곡S/S 154kV 세종-둔곡#2T/L GIS 하자점검","2022-03-18 09:00","2022-03-18 14:00","2022-03-18 09:00","2022-03-18 14:00","연속"]
[298,"대전세종충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의T/L 지장송전선로 이설공사","*○ 공사구간 : 154kV 조치원-전의T/L No.20~24 ○ 지지물 : 신설 3기 설치, 임시 3기 설치/철거, 기설 3기 철거 ○ 전력선 : ASCC/TW 430 x S x 2C, 1.388km(전선교체)","2022-03-28 07:00","2022-04-01 18:00","2022-03-28 07:00","2022-04-01 18:00","연속"]
[299,"대전세종충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의#1T/L 안전이격확보공사","*154kV 조치원-전의#1T/L 가선로 본탑 이설 No.6~10","2022-03-16 08:00","2022-03-18 18:00","2022-03-16 08:00","2022-03-18 18:00","연속"]
[300,"대전세종충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 지장송전선로 이설공사","*○ 공사구간 : 154kV 조치원-전의T/L No.20~24 ○ 지지물 : 신설 3기 설치, 임시 3기 설치/철거, 기설 3기 철거 ○ 전력선 : ASCC/TW 430 x S x 2C, 1.388km(전선교체)","2022-03-21 07:00","2022-03-25 18:00","2022-03-21 07:00","2022-03-25 18:00","연속"]
[301,"대전세종충남","세종","세종S/S #60 BUS","세종S/S 154kV 네이버#1,2T/L GIS 증설","154kV 네이버#1T/L GIS 설치","2022-03-21 09:00","2022-03-23 14:00","취소","취소","연속"]
[302,"대전세종충남","세종","세종서세종#1 T/L","세종S/S 154kV 네이버#1,2T/L GIS 증설","세종S/S 154kV 네이버#1T/L GIS 설치(#60BUS 무부하가압)","2022-03-22 14:00","2022-03-23 14:00","취소","취소","연속"]
[303,"대전세종충남","세종","세종S/S #61 BUS","세종S/S 154kV 네이버#1,2T/L GIS 증설","154kV 네이버#2T/L GIS 설치","2022-03-23 14:00","2022-03-26 14:00","취소","취소","연속"]
[304,"대전세종충남","세종","세종둔곡#1 T/L","세종S/S 154kV 네이버#1,2T/L GIS 증설","세종S/S 154kV 네이버#2T/L GIS 증설(#61BUS 무부하가압)","2022-03-25 14:00","2022-03-26 14:00","취소","취소","연속"]
[305,"대전세종충남","세종","세종S/S #65 BUS","세종S/S 154kV 네이버#1,2T/L GIS 증설","154kV 네이버#1T/L GIS 설치","2022-03-28 09:00","2022-04-01 14:00","취소","취소","연속"]
[306,"대전세종충남","세종","세종서세종#1 T/L","세종S/S 154kV 네이버#1,2T/L GIS 증설","세종S/S 154kV 네이버#1T/L GIS 설치(#65BUS 무부하가압)","2022-03-31 14:00","2022-04-01 14:00","취소","취소","연속"]
[307,"대전세종충남","천안","둔포석곡#1 T/L","둔포S/S 154kV 둔포-석곡#1TL GIS 보통점검","둔포S/S 154kV 둔포-석곡#1TL GIS 보통점검","2022-03-10 09:00","2022-03-10 18:00","2022-03-10 09:00","2022-03-10 18:00","연속"]
[308,"대전세종충남","천안","둔포석곡#2 T/L","둔포S/S 154kV 둔포-석곡#2TL GIS 보통점검","둔포S/S 154kV 둔포-석곡#2TL GIS 보통점검","2022-03-11 09:00","2022-03-11 18:00","2022-03-11 09:00","2022-03-11 18:00","연속"]
[309,"대전세종충남","천안","신온양한샘#1 T/L","345kV 아산-화성 등 13개T/L 성능저하 점퍼지지애자 교체공사","154kV 신온양-한샘T/L No. 40, 43 성능저하 점퍼지지애자 교체","2022-03-03 09:00","2022-03-03 14:00","2022-03-03 09:00","2022-03-03 14:00","연속"]
[310,"대전세종충남","천안","신온양한샘#2 T/L","신온양S/S 신온양-한샘#2TL GIS 누기보수","신온양S/S 신온양-한샘#2TL GIS 누기보수","2022-03-21 09:00","2022-03-25 18:00","2022-03-21 09:00","2022-03-25 18:00","연속"]
[311,"대전세종충남","천안","아산S/S #65 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-03-10 09:00","2022-03-23 14:00","2022-03-10 09:00","2022-03-23 14:00","연속"]
[312,"대전세종충남","천안","아산합덕#1 T/L","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-03-10 09:00","2022-04-06 16:00","2022-03-10 09:00","2022-04-06 16:00","연속"]
[313,"대전세종충남","천안","아산예산#1 T/L","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-03-10 09:00","2022-03-14 18:00","2022-03-10 09:00","2022-03-14 18:00","연속"]
[314,"대전세종충남","천안","아산S/S #66 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-03-10 09:00","2022-03-23 14:00","2022-03-10 09:00","2022-03-23 14:00","연속"]
[315,"대전세종충남","천안","아산S/S #60 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-03-23 14:00","2022-04-05 14:00","2022-03-23 14:00","2022-04-05 14:00","연속"]
[316,"대전세종충남","천안","아산S/S #61 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-03-23 09:00","2022-04-05 14:00","2022-03-23 09:00","2022-04-05 14:00","연속"]
[317,"대전세종충남","천안","아산예산#1 T/L","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-03-22 14:00","2022-03-23 14:00","2022-03-22 14:00","2022-03-23 14:00","연속"]
[318,"대전세종충남","천안","아산예산#2 T/L","154kV 예산S/S GIS 설치공사(전문)","154kV 예산S/S GIS 설치공사(전문) - GIS 부속자재 설치(LINE PT 등)","2022-03-11 09:00","2022-03-11 18:00","2022-03-11 09:00","2022-03-11 18:00","연속"]
[319,"대전세종충남","천안","아산예산#1 T/L","154kV 예산S/S GIS 설치공사(전문)","154kV 예산S/S GIS 설치공사(전문) - GIS 부속자재 설치(LINE PT 등)","2022-03-10 09:00","2022-03-10 18:00","2022-03-10 09:00","2022-03-10 18:00","연속"]
[320,"대전세종충남","천안","장재불당#1 T/L","장재S/S 154kV 장재-불당#1TL GIS 보통점검","*장재S/S 154kV 장재-불당#1TL GIS 보통점검","2022-03-30 09:00","2022-03-30 18:00","2022-03-30 09:00","2022-03-30 18:00","연속"]
[321,"대전세종충남","천안","장재불당#2 T/L","장재S/S 154kV 장재-불당#2TL GIS 보통점검","*장재S/S 154kV 장재-불당#2TL GIS 보통점검","2022-03-31 09:00","2022-03-31 18:00","2022-03-31 09:00","2022-03-31 18:00","연속"]
[322,"대전세종충남","천안","풍세장재#2 T/L","345kV 아산-화성 등 13개T/L 성능저하 점퍼지지애자 교체공사","154kV 풍세-장재T/L, 154kV 장재-천안T/L 병가구간 성능저하 점퍼지지애자 교체 - 154kV 풍세-장재T/L No. 18","2022-03-03 14:00","2022-03-03 18:00","2022-03-03 14:00","2022-03-03 18:00","연속"]
[323,"대전세종충남","천안","장재천안#1 T/L","345kV 아산-화성 등 13개T/L 성능저하 점퍼지지애자 교체공사","*154kV 풍세-장재T/L, 154kV 장재-천안T/L 병가구간 성능저하 점퍼지지애자 교체 - 154kV 풍세-장재T/L No. 18","2022-03-03 14:00","2022-03-03 18:00","2022-03-03 14:00","2022-03-03 18:00","연속"]
[324,"대전세종충남","천안","둔포직산#2 T/L","직산S/S 154kV 직산-둔포#2TL GIS 하자점검","직산S/S 154kV 직산-둔포#2TL GIS 하자점검","2022-03-04 09:00","2022-03-04 18:00","2022-03-04 09:00","2022-03-04 18:00","연속"]
[325,"대전세종충남","천안","둔포직산#1 T/L","직산S/S 154kV 직산-둔포#1TL GIS 하자점검","직산S/S 154kV 직산-둔포#1TL GIS 하자점검","2022-03-03 09:00","2022-03-03 18:00","2022-03-03 09:00","2022-03-03 18:00","연속"]
[326,"대전세종충남","천안","서천안탕정#2 T/L","탕정S/S 154kV 서천안-탕정#2TL GIS 보통점검","탕정S/S 154kV 서천안-탕정#2TL GIS 보통점검","2022-03-18 09:00","2022-03-18 18:00","2022-03-18 09:00","2022-03-18 18:00","연속"]
[327,"대전세종충남","천안","서천안탕정#1 T/L","탕정S/S 154kV 서천안-탕정#1TL GIS 보통점검","탕정S/S 154kV 서천안-탕정#1TL GIS 보통점검","2022-03-17 09:00","2022-03-17 18:00","2022-03-17 09:00","2022-03-17 18:00","연속"]
[328,"전북","김제","정주고창#1 T/L","보호계전기 성능개선","보호계전기 성능개선","2022-03-15 09:30","2022-03-15 18:00","2022-03-15 09:30","2022-03-15 18:00","연속"]
[329,"전북","김제","정주고창#2 T/L","보호계전기 성능개선","보호계전기 성능개선","2022-03-16 09:30","2022-03-16 18:00","2022-03-16 09:30","2022-03-16 18:00","연속"]
[330,"전북","김제","정공정주#2 T/L","보호계전기 성능개선","보호계전기 성능개선","2022-03-17 09:30","2022-03-17 18:00","2022-03-17 09:30","2022-03-17 18:00","연속"]
[331,"전북","김제","김제부안#1 T/L","보호계전기 성능개선","보호계전기 성능개선","2022-03-18 09:30","2022-03-18 18:00","2022-03-18 09:30","2022-03-18 18:00","연속"]
[332,"전북","군산","팔봉봉동#1 T/L","왕궁변전소 건설공사","왕궁변전소 건설공사","2022-03-14 09:00","2022-03-23 18:00","취소","취소","연속"]
[333,"전북","군산","팔봉봉동#2 T/L","왕궁변전소 건설공사","왕궁변전소 건설공사","2022-03-24 09:00","2022-04-01 18:00","취소","취소","연속"]
[334,"전북","직할","동전주북전주#2 T/L","장기사용 GIS 교체공사(MAIN 교체)","장기사용 GIS 교체공사(MAIN 교체)","2022-03-14 09:00","2022-04-17 18:00","취소","취소","연속"]
[335,"전북","직할","동전주태평#2 T/L","장기사용 GIS 교체공사 (시험가압)","장기사용 GIS 교체공사 (시험가압)","2022-03-17 09:00","2022-03-18 09:00","취소","취소","연속"]
[336,"전북","군산","군산서군산#2 T/L","취약지지물 교체공사","취약지지물 교체공사","2022-03-14 07:00","2022-03-16 18:00","취소","취소","연속"]
[337,"전북","군산","군산서군산#1 T/L","취약지지물 교체공사","취약지지물 교체공사","2022-03-17 07:00","2022-03-21 18:00","취소","취소","연속"]
[338,"전북","군산","군산S/S CB 6100","장기사용 GIS 교체공사(MAIN 교체)","장기사용 GIS 교체공사(MAIN 교체)","2022-03-15 09:00","2022-04-06 18:00","취소","취소","연속"]
[339,"전북","군산","군산이리#1 T/L","장기사용 GIS 교체공사(MAIN 교체)","장기사용 GIS 교체공사(MAIN 교체)","2022-03-15 09:00","2022-04-06 18:00","취소","취소","연속"]
[340,"전북","군산","군산S/S 65 BUS","장기사용 GIS 교체공사","장기사용 GIS 교체공사","2022-03-15 09:00","2022-03-17 18:00","취소","취소","연속"]
[341,"전북","군산","군산S/S 60 BUS","장기사용 GIS 교체공사","장기사용 GIS 교체공사","2022-03-17 18:00","2022-03-25 18:00","취소","취소","연속"]
[342,"전북","군산","군산S/S 65 BUS","장기사용 GIS 교체공사","장기사용 GIS 교체공사","2022-03-25 18:00","2022-04-06 16:00","취소","취소","연속"]
[343,"전북","군산","군산영등#2 T/L","장기사용 GIS 교체공사(시험가압)","장기사용 GIS 교체공사(시험가압)","2022-03-15 09:00","2022-04-06 18:00","취소","취소","연속"]
[344,"전북","군산","군산S/S 66 BUS","장기사용 GIS 교체공사(시험가압)","장기사용 GIS 교체공사(시험가압)","2022-03-15 09:00","2022-03-17 18:00","취소","취소","연속"]
[345,"전북","군산","군산S/S 61 BUS","군산S/S 23kV SIS PD 합동진단","군산S/S 23kV SIS PD 합동진단","2022-03-17 18:00","2022-03-25 18:00","취소","취소","연속"]
[346,"전북","군산","군산S/S 66 BUS","군산S/S 23kV SIS PD 합동진단","군산S/S 23kV SIS PD 합동진단","2022-03-25 18:00","2022-04-06 16:00","취소","취소","연속"]
[347,"전북","군산","군산S/S CB 6100"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-03 09:00","2022-03-03 18:00","2022-03-03 09:00","2022-03-03 18:00","연속"]
[348,"전북","군산","군산S/S CB 6300"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-03 09:00","2022-03-03 18:00","2022-03-03 09:00","2022-03-03 18:00","연속"]
[349,"전북","군산","내초군장#1 T/L"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-17 09:00","2022-03-17 18:00","2022-03-17 09:00","2022-03-17 18:00","연속"]
[350,"전북","군산","내초군장#2 T/L"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-24 09:00","2022-03-24 18:00","2022-03-24 09:00","2022-03-24 18:00","연속"]
[351,"전북","군산","군산동군산#1 T/L"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-02 09:00","2022-03-02 18:00","2022-03-02 09:00","2022-03-02 18:00","연속"]
[352,"전북","군산","군산동군산#2 T/L"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-03 09:00","2022-03-03 18:00","2022-03-03 09:00","2022-03-03 18:00","연속"]
[353,"전북","군산","이리백산#1 T/L"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-29 09:00","2022-03-29 18:00","2022-03-29 09:00","2022-03-29 18:00","연속"]
[354,"전북","군산","이리백산#2 T/L"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-30 09:00","2022-03-30 18:00","2022-03-30 09:00","2022-03-30 18:00","연속"]
[355,"전북","군산","팔봉두마#2 T/L"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-08 09:00","2022-03-08 18:00","2022-03-28 09:00","2022-03-28 18:00","연속"]
[356,"전북","군산","팔봉두마#1 T/L"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-10 09:00","2022-03-10 18:00","2022-03-29 09:00","2022-03-29 18:00","연속"]
[357,"전북","군산","영등팔봉#1 T/L"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-15 09:00","2022-03-15 18:00","취소","취소","연속"]
[358,"전북","군산","영등팔봉#2 T/L"," 군산P/O 154kV 이상 차단기 보통점검"," 군산P/O 154kV 이상 차단기 보통점검","2022-03-16 09:00","2022-03-16 18:00","취소","취소","연속"]
[359,"전북","군산","군산이리#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","154kV 군산-이리 등 4개T/L OPGW 증설공사","2022-03-19 07:00","2022-03-26 18:00","취소","취소","연속"]
[360,"전북","군산","군산영등#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","154kV 군산-이리 등 4개T/L OPGW 증설공사","2022-03-19 07:00","2022-03-26 18:00","취소","취소","연속"]
[361,"전북","김제","신김제전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","2022-03-21 08:00","2022-03-22 18:00","취소","취소","연속"]
[362,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","2022-03-21 08:00","2022-03-22 18:00","취소","취소","연속"]
[363,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","2022-03-23 08:00","2022-03-28 18:00","취소","취소","연속"]
[364,"전북","김제","신김제전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","2022-03-23 08:00","2022-03-28 18:00","취소","취소","연속"]
[365,"전북","김제","신김제전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","2022-03-30 08:00","2022-04-06 18:00","취소","취소","연속"]
[366,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","2022-03-30 08:00","2022-04-06 18:00","취소","취소","연속"]
[367,"전북","군산","신김제전주#2 T/L","154kV 신김제-전주T/L OPGW 교체공사","154kV 신김제-전주T/L OPGW 교체공사","2022-03-29 07:00","2022-03-29 18:00","취소","취소","연속"]
[368,"전북","군산","신김제남전주#2 T/L","154kV 신김제-전주T/L OPGW 교체공사","154kV 신김제-전주T/L OPGW 교체공사","2022-03-29 07:00","2022-03-29 18:00","취소","취소","연속"]
[369,"광주전남","강진","영암금정#1 T/L","154kV 영암-금정T/L 안전이격거리 확보","광주-강진간 고속도로 공사 관련 안전이격거리 확보","2022-03-21 08:00","2022-03-25 18:00","2022-03-21 08:00","2022-03-25 18:00","매일"]
[370,"광주전남","강진","영암금정#2 T/L","154kV 영암-금정T/L 안전이격거리 확보","광주-강진간 고속도로 공사 관련 안전이격거리 확보","2022-03-21 08:00","2022-03-25 18:00","2022-03-21 08:00","2022-03-25 18:00","매일"]
[371,"광주전남","강진","대불S/S #3 Sh.C (CB 6379)","대불S/S 154kV 이하 GIS 교체(SA화)공사(3차)","대불S/S 154kV 이하 GIS 교체(SA화)공사(3차) - 대불-남악#1T/L, #1,#3Sh.C GIS 교체","2022-03-02 10:00","2022-04-06 16:00","2022-03-02 10:00","2022-04-06 16:00","연속"]
[372,"광주전남","강진","대불남악#1 T/L","대불S/S 154kV 이하 GIS 교체(SA화)공사(3차)","대불S/S 154kV 이하 GIS 교체(SA화)공사(3차) - 대불-남악#1T/L, #1,#3Sh.C GIS 교체","2022-03-02 10:00","2022-04-06 16:00","2022-03-02 10:00","2022-04-06 16:00","연속"]
[373,"광주전남","강진","대불S/S #2 Sh.C (CB 6279)","대불S/S 154kV 이하 GIS 교체(SA화)공사(3차) 안전이격확보","대불S/S 154kV 이하 GIS 교체(SA화)공사(3차) - 대불-남악#1T/L, #1,#3Sh.C GIS 교체 안전이격 확보","2022-03-02 10:00","2022-04-06 16:00","2022-03-02 10:00","2022-04-06 16:00","연속"]
[374,"광주전남","강진","대불S/S #1 Sh.C (CB 6179)","대불S/S 154kV 이하 GIS 교체(SA화)공사(3차)","대불S/S 154kV 이하 GIS 교체(SA화)공사(3차) - 대불-남악#1T/L, #1,#3Sh.C GIS 교체","2022-03-02 10:00","2022-04-06 16:00","2022-03-02 10:00","2022-04-06 16:00","연속"]
[375,"광주전남","강진","진도서제주#2 T/L (제2연계선 #2Pole) CB","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) #Bipole(#1, 2 Pole) 연차점검","2022-03-28 09:00","2022-04-11 18:00","2022-03-28 09:00","2022-04-11 18:00","연속"]
[376,"광주전남","강진","진도C/S #2 BUS","진도C/S 170kV GIS 증설공사(전문)","170kV GIS 50kA * 1CCT 증설","2022-03-12 09:00","2022-03-16 18:00","2022-04-06 09:00","2022-04-11 18:00","연속"]
[377,"광주전남","강진","진도C/S #1 BUS","진도C/S 170kV GIS 증설공사(전문)","170kV GIS 50kA * 1CCT 증설","2022-03-07 09:00","2022-03-11 18:00","2022-04-02 09:00","2022-04-05 18:00","연속"]
[378,"광주전남","강진","진도진도CS#1 T/L","진도C/S 170kV GIS 증설공사(전문)","170kV GIS 50kA * 1CCT 증설 #1BUS 무부하가압","2022-03-10 09:00","2022-03-11 18:00","2022-04-02 09:00","2022-04-04 18:00","연속"]
[379,"광주전남","강진","진도진도CS#1 T/L","진도C/S 170kV GIS 증설공사(전문)","170kV GIS 50kA * 1CCT 증설 #2BUS 무부하가압","2022-03-15 09:00","2022-03-16 18:00","2022-04-10 09:00","2022-04-11 18:00","연속"]
[380,"광주전남","강진","진도진도CS#2 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","진도S/S, 진도C/S 진도-진도C/S #2T/L GIS 보통점검(비상시 20분이내 가압 가능)","2022-03-08 10:00","2022-03-08 18:00","2022-04-06 10:00","2022-04-06 18:00","연속"]
[381,"광주전남","광주","계림충장#3 T/L","22년 광주전력 변전협력회사 총액공사 (보통점검)","- 보통점검 - 즉시가압 불가","2022-03-23 09:00","2022-03-23 18:00","취소","취소","연속"]
[382,"광주전남","광주","북광주계림#2 T/L","22년 광주전력 변전협력회사 총액공사 (보통점검)","- 보통점검 - 즉시가압 불가","2022-03-03 09:00","2022-03-03 18:00","취소","취소","연속"]
[383,"광주전남","광주","계림충장#1 T/L","22년 광주전력 변전협력회사 총액공사 (보통점검)","- 보통점검 - 즉시가압 불가","2022-03-21 09:00","2022-03-21 18:00","취소","취소","연속"]
[384,"광주전남","광주","계림소태 T/L","22년 광주전력 변전협력회사 총액공사 (보통점검)","- 보통점검 - 즉시가압 불가","2022-03-16 09:00","2022-03-16 18:00","취소","취소","연속"]
[385,"광주전남","광주","계림충장#2 T/L","22년 광주전력 변전협력회사 총액공사 (보통점검)","- 보통점검 - 즉시가압 불가","2022-03-22 09:00","2022-03-22 18:00","취소","취소","연속"]
[386,"광주전남","광주","북광주계림#1 T/L","22년 광주전력 변전협력회사 총액공사 (에어누기, 보통점검)","- 에어누기 조치 (오링 교체) - 보통점검 -즉시가압 불가","2022-03-02 09:00","2022-03-02 18:00","취소","취소","연속"]
[387,"광주전남","광주","계림승주#1 T/L","154kV 계림-승주T/L 안전이격확보공사","154kV 계림-승주T/L 안전이격확보공사","2022-03-28 07:00","2022-03-31 18:00","취소","취소","연속"]
[388,"광주전남","광주","계림승주#2 T/L","154kV 계림-승주T/L 안전이격확보공사","154kV 계림-승주T/L 안전이격확보공사","2022-03-22 07:00","2022-03-27 18:00","취소","취소","연속"]
[389,"광주전남","광주","계림승주#1 T/L","154kV 계림-승주T/L 안전이격확보공사","154kV 계림-승주T/L 안전이격확보공사","2022-03-21 07:00","2022-03-21 18:00","2022-03-21 07:00","2022-03-21 18:00","연속"]
[390,"광주전남","광주","남광주금천#1 T/L","22년 광주전력 변전협력회사 총액공사 (보통점검)","- 보통점검 - 즉시가압 불가","2022-03-31 09:00","2022-03-31 18:00","2022-03-31 09:00","2022-03-31 18:00","연속"]
[391,"광주전남","광주","담양김제 T/L","21년 철탑 추락방지장치 설치공사","154kV 담양-일곡T/L 4회선 철탑 추락방지장치 설치","2022-03-10 07:00","2022-03-16 18:00","취소","취소","매일"]
[392,"광주전남","광주","정공담양 T/L","21년 철탑추락방지장치 설치공사","154kV 담양-일곡T/L 4회선 철탑 수평추락방지장치 설치","2022-03-02 07:00","2022-03-08 18:00","2022-03-02 07:00","2022-03-08 18:00","매일"]
[393,"광주전남","광주","담양일곡#1 T/L","21년 철탑 추락방지장치 설치공사","154kV 담양-일곡T/L 수평 추락방지장치 설치(14기)","2022-03-02 07:00","2022-03-08 18:00","취소","취소","매일"]
[394,"광주전남","광주","담양일곡#2 T/L","21년 철탑추락방지장치 설치공사","154kV 담양-일곡T/L 수평 추락방지장치 설치","2022-03-10 07:00","2022-03-16 18:00","2022-03-02 07:00","2022-03-08 18:00","매일"]
[395,"광주전남","광주","북광주일곡#1 T/L","22년 광주전력 변전총액 (154kV 북광주 모선보호반 교체)","154kV 북광주 모선보호반 교체","2022-03-14 11:00","2022-03-14 12:00","2022-03-14 11:00","2022-03-14 12:00","연속"]
[396,"광주전남","광주","북광주계림#2 T/L","22년 광주전력 변전총액 (154kV 북광주 모선보호반 교체)","154kV 북광주 모선보호반 교체","2022-03-14 10:00","2022-03-14 11:00","2022-03-14 10:00","2022-03-14 11:00","연속"]
[397,"광주전남","광주","북광주계림#1 T/L","22년 광주전력 변전총액 (154kV 북광주 모선보호반 교체)","154kV 북광주 모선보호반 교체","2022-03-14 09:00","2022-03-14 10:00","2022-03-14 09:00","2022-03-14 10:00","연속"]
[398,"광주전남","광주","북광주계림#2 T/L","22년 광주전력 변전총액 (154kV 북광주 모선보호반 교체)","154kV 북광주 모선보호반 교체","2022-03-17 10:00","2022-03-17 11:00","2022-03-17 10:00","2022-03-17 11:00","연속"]
[399,"광주전남","광주","북광주일곡#1 T/L","22년 광주전력 변전총액 (154kV 북광주 모선보호반 교체)","154kV 북광주 모선보호반 교체","2022-03-17 11:00","2022-03-17 12:00","2022-03-17 11:00","2022-03-17 12:00","연속"]
[400,"광주전남","광주","북광주계림#1 T/L","22년 광주전력 변전총액 (154kV 북광주 모선보호반 교체)","154kV 북광주 모선보호반 교체","2022-03-17 09:00","2022-03-17 10:00","2022-03-17 09:00","2022-03-17 10:00","연속"]
[401,"광주전남","광주","북광주일곡#2 T/L","22년 광주전력 변전총액 (154kV 북광주 모선보호반 교체)","154kV 북광주 모선보호반 교체","2022-03-17 13:00","2022-03-17 14:00","2022-03-17 13:00","2022-03-17 14:00","연속"]
[402,"광주전남","광주","북광주일곡#2 T/L","22년 광주전력 변전총액 (154kV 북광주 모선보호반 교체)","154kV 북광주 모선보호반 교체","2022-03-14 13:00","2022-03-14 14:00","2022-03-14 13:00","2022-03-14 14:00","연속"]
[403,"광주전남","광주","신화순화순#1 T/L","21년 철탑 추락방지장치 설치공사","345kV 신광주-신화순T/L 4회선 철탑 추락방지장치 설치","2022-03-28 07:00","2022-04-01 18:00","2022-03-28 07:00","2022-04-01 18:00","매일"]
[404,"광주전남","광주","신화순화순#2 T/L","21년 철탑 추락방지장치 설치공사","345kV 신광주-신화순T/L 4회선 철탑 추락방지장치 설치","2022-03-21 07:00","2022-03-25 18:00","2022-03-21 07:00","2022-03-25 18:00","매일"]
[405,"광주전남","광주","신화순S/S CB 6100","22년 광주전력 변전협력회사 총액공사 (신화순 6100)","#1BUS-TIE 유압시스템 교체","2022-03-28 09:00","2022-03-29 18:00","2022-03-28 09:00","2022-03-29 18:00","매일"]
[406,"광주전남","광주","신광주장성#2 T/L","22년 광주전력 변전협력회사 총액공사 (보통점검)","- 보통점검 - 즉시가압 불가","2022-03-29 09:00","2022-03-29 18:00","취소","취소","연속"]
[407,"광주전남","광주","장성영광#1 T/L","21~22년 지중송전 위탁정비공사","○ 장성-영광 #1 T/L 장성S/S 내 C/T 철탑 피뢰기 절연성능 점검(도블측정)","2022-03-31 09:00","2022-03-31 18:00","2022-03-31 09:00","2022-03-31 18:00","연속"]
[408,"광주전남","광주","장성영광#2 T/L","22년 광주전력 변전협력회사 총액공사 (보통점검)","- 보통점검 - 즉시가압 불가","2022-03-30 09:00","2022-03-30 18:00","2022-03-30 09:00","2022-03-30 18:00","연속"]
[409,"광주전남","목포","엄다무안햇빛#1 T/L","154kV 엄다-운남T/L 용량증대 전선교체공사","ㅇ 목적 : 신안지역 신재생발전 계통 연계를 위하여 송전선로 설비보강 시행 ㅇ 공사개요 - ACSR/AW 330㎟에서 ASCC/TW 430㎟로 용량증대 전선교체 - 엄다S/S 구내 C/T철탑 개조","2022-03-02 09:00","2022-03-31 18:00","취소","취소","연속"]
[410,"광주전남","순천","광양S/S CB 6200","영인제 모선보호반 성능개선","영인제 모선보호반 성능개선","2022-03-08 10:00","2022-03-08 18:00","2022-03-08 10:00","2022-03-08 18:00","연속"]
[411,"광주전남","순천","광양S/S CB 6100","영인제 모선보호반 성능개선","영인제 모선보호반 성능개선","2022-03-08 10:00","2022-03-08 18:00","2022-03-08 10:00","2022-03-08 18:00","연속"]
[412,"광주전남","순천","광양순천#1 T/L","세니온제 154송전선로보호IED 성능개선","세니온제 154송전선로보호IED 성능개선","2022-03-03 10:00","2022-03-03 18:00","취소","취소","연속"]
[413,"광주전남","순천","여수TP용성#1 T/L","대한제 열경화공법 EBG 보강공사","여수TP-용성#1 T/L EBG 해체점검(6상)","2022-03-22 09:00","2022-03-30 18:00","취소","취소","연속"]
[414,"광주전남","순천","여수TP여천#1 T/L","여천S/S #1M.Tr 교체공사 관련 안전 이격거리","○ 154kV M.Tr(154/23kV, 15/20MVA × 3대) 현장 개조 및 설치 × 1Bank ○ 154kV M.Tr(154/23kV, 45/60MVA) 철거 × 1Bank ○ 기타 부대설비 × 1식","2022-03-02 09:00","2022-03-02 18:00","취소","취소","연속"]
[415,"광주전남","직할","하남장성#1 T/L","하남-장성T/L OPGW 취약개소 정비공사","하남-장성 #1T/L No.19,20호간 OPGW 항공구 2개 교체 댐퍼 시설 1개소(No.23), 아머로드 교체 3개소(No.1,29,34) OPGW 슬립 조치 2개소(No.32,34호) 비아-하남 #2T/L No.55,56호간 OPGW 항공구 3개 교체","2022-03-15 09:00","2022-03-16 17:00","취소","취소","연속"]
[416,"광주전남","직할","비아하남#1 T/L","하남-장성T/L OPGW 취약개소 정비공사","하남-장성 #1T/L No.19,20호간 OPGW 항공구 2개 교체(비아하남 병가) 댐퍼 시설 1개소(No.23), 아머로드 교체 3개소(No.1,29,34) OPGW 슬립 조치 2개소(No.32,34호) 비아-하남 #2T/L No.55,56호간 OPGW 항공구 3개 교체","2022-03-15 09:00","2022-03-16 17:00","취소","취소","연속"]
[417,"광주전남","직할","비아하남#2 T/L","하남-장성T/L OPGW 취약개소 정비공사","하남-장성 #1T/L No.19,20호간 OPGW 항공구 2개 교체(비아-하남 병가) 댐퍼 시설 1개소(No.23), 아머로드 교체 3개소(No.1,29,34) OPGW 슬립 조치 2개소(No.32,34호) 비아-하남 #2T/L No.55,56호간 OPGW 항공구 3개 교체","2022-03-17 09:00","2022-03-17 17:00","취소","취소","연속"]
[418,"광주전남","직할","하남장성#2 T/L","하남-장성T/L OPGW 취약개소 정비공사","하남-장성 #1T/L No.19,20호간 OPGW 항공구 2개 교체 댐퍼 시설 1개소(No.23), 아머로드 교체 3개소(No.1,29,34) OPGW 슬립 조치 2개소(No.32,34호) 비아-하남 #2T/L No.55,56호간 OPGW 항공구 3개 교체","2022-03-17 09:00","2022-03-17 17:00","취소","취소","연속"]
[419,"대구","경산","대구청도#1 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-03-18 18:00","2022-03-19 09:30","2022-03-18 18:00","2022-03-19 09:30","연속"]
[420,"대구","경산","청도밀양#1 T/L","청도S/S 154kV GIS 교체공사","154kV GIS 교체","2022-03-10 09:30","2022-04-01 18:00","2022-03-10 09:30","2022-04-01 18:00","연속"]
[421,"대구","경산","대구청도#2 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-03-24 18:00","2022-03-25 09:30","2022-03-24 18:00","2022-03-25 09:30","연속"]
[422,"대구","칠곡","김천금릉#1 T/L","금릉S/S 154kV LA 보통점검","금릉S/S 154kV LA 보통점검","2022-03-30 09:30","2022-03-30 18:00","2022-03-30 09:30","2022-03-30 18:00","연속"]
[423,"대구","칠곡","어모김천#1 T/L","154kV 김천S/S 현대화 공사","154kV 김천S/S 현대화 공사","2022-03-07 15:00","2022-03-07 18:00","취소","취소","연속"]
[424,"대구","칠곡","농소김천#1 T/L","154kV 김천S/S 현대화공사","154kV 김천S/S 현대화공사","2022-03-07 09:00","2022-03-07 15:00","취소","취소","연속"]
[425,"대구","칠곡","남구미농소#2 T/L","남구미,농소S/S 154kV GIS 보통점검","남구미,농소S/S 154kV GIS 보통점검","2022-03-25 09:30","2022-03-25 18:00","2022-03-25 09:30","2022-03-25 18:00","연속"]
[426,"대구","칠곡","남구미농소#1 T/L","남구미,농소S/S 154kV GIS 보통점검","남구미,농소S/S 154kV GIS 보통점검","2022-03-24 09:30","2022-03-24 18:00","2022-03-21 09:30","2022-03-21 18:00","연속"]
[427,"대구","칠곡","서대구남구미#1 T/L","남구미S/S 154kV GIS 보통점검","남구미S/S 154kV GIS 보통점검","2022-03-10 09:30","2022-03-10 14:00","2022-03-10 09:30","2022-03-10 14:00","연속"]
[428,"대구","칠곡","서대구남구미#2 T/L","남구미S/S 154kV GIS 보통점검","남구미S/S 154kV GIS 보통점검","2022-03-10 14:00","2022-03-10 18:00","2022-03-10 14:00","2022-03-10 18:00","연속"]
[429,"대구","칠곡","고아어모#2 T/L","어모S/S 154kV LA 보통점검","어모S/S 154kV LA 보통점검","2022-03-28 14:00","2022-03-28 18:00","2022-03-28 14:00","2022-03-28 18:00","연속"]
[430,"대구","칠곡","고아어모#1 T/L","어모S/S 154kV LA 보통점검","어모S/S 154kV LA 보통점검","2022-03-28 09:30","2022-03-28 14:00","2022-03-28 09:30","2022-03-28 14:00","연속"]
[431,"대구","포항","건천천북#1 T/L","154㎸건천-천북T/L 지중화 공사","피뢰기점검","2022-03-02 09:00","2022-03-02 18:00","2022-03-07 09:00","2022-03-07 18:00","연속"]
[432,"대구","포항","건천천북#2 T/L","154㎸건천-천북T/L 지중화 공사","피뢰기점검","2022-03-03 09:00","2022-03-03 18:00","2022-03-08 09:00","2022-03-08 18:00","연속"]
[433,"대구","포항","옥동외동#1 T/L","외동S/S 외동-옥동#1T/L GIS, LA보통점검","외동S/S 외동-옥동#1T/L GIS, LA보통점검","2022-03-24 09:00","2022-03-24 18:00","2022-03-24 09:00","2022-03-24 18:00","연속"]
[434,"대구","포항","울주외동#1 T/L","울주-외동#1T/L GIS 보통점검","울주-외동#1T/L GIS 보통점검","2022-03-15 09:00","2022-03-15 18:00","2022-03-15 09:00","2022-03-15 18:00","연속"]
[435,"대구","포항","울주외동#2 T/L","울주-외동#2T/L GIS,LA 보통점검","울주-외동#2T/L GIS,LA 보통점검","2022-03-16 09:00","2022-03-16 18:00","2022-03-16 09:00","2022-03-16 18:00","연속"]
[436,"대구","포항","옥동외동#2 T/L","외동S/S 외동-옥동#2T/L GIS, LA보통점검","외동S/S 외동-옥동#2T/L GIS, LA보통점검","2022-03-23 09:00","2022-03-23 18:00","2022-03-17 09:00","2022-03-17 18:00","연속"]
[437,"경북","구미","선산청리#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- LA 교체[선산S/S] - GIS 보통점검[청리S/S]","2022-03-22 09:00","2022-03-22 18:00","2022-03-22 09:00","2022-03-22 18:00","연속"]
[438,"경북","구미","선산청리#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- LA 교체[선산S/S] - GIS 보통점검, LA 보통점검[청리S/S]","2022-03-21 09:00","2022-03-21 18:00","2022-03-21 09:00","2022-03-21 18:00","연속"]
[439,"경북","구미","청리상주#1 T/L","154kV 청리-상주T/L 안전이격거리 확보공사(No.60~62)","공사개요 : 1937년 설치된 노후철탑을 교체하여 전력공급에 만전을 기하고자함 o 구간 : 154kV 청리-상주T/L No.60~62 o 선종 : ACSR 330 * 2C *. 1.530km o 철탑기수 : 3기 설치, 3기 철거","2022-02-25 07:00","2022-03-08 18:00","2022-02-25 07:00","2022-03-08 18:00","연속"]
[440,"경북","구미","청리상주#2 T/L","154kV 청리-상주T/L 안전이격거리 확보공사(No.60~62)","공사개요 : 1937년 설치된 노후철탑을 교체하여 전력공급에 만전을 기하고자함 o 구간 : 154kV 청리-상주T/L No.60~62 o 선종 : ACSR 330 * 2C *. 1.530km o 철탑기수 : 3기 설치, 3기 철거","2022-02-25 07:00","2022-03-08 18:00","2022-02-25 07:00","2022-03-08 18:00","연속"]
[441,"경북","영주","신영주안동#2 T/L","신영주S/S 154kV GIS 하자보수","3P DS 롱런 관련 조치 등 제작사 하자보수","2022-03-15 15:00","2022-03-15 17:00","2022-03-15 15:00","2022-03-15 17:00","연속"]
[442,"경북","영주","신영주안동#1 T/L","신영주S/S 154kV GIS 하자보수","3P DS 롱런 관련 조치 등 제작사 하자보수","2022-03-15 13:00","2022-03-15 15:00","2022-03-15 13:00","2022-03-15 15:00","연속"]
[443,"경북","영주","신영주영주#2 T/L","신영주S/S 154kV GIS 하자보수","3P DS 롱런 관련 조치 등 제작사 하자보수","2022-03-18 13:00","2022-03-18 15:00","2022-03-18 13:00","2022-03-18 15:00","연속"]
[444,"경북","영주","신영주영주#1 T/L","신영주S/S 154kV GIS 하자보수","3P DS 롱런 관련 조치 등 제작사 하자보수","2022-03-16 15:00","2022-03-16 17:00","2022-03-16 15:00","2022-03-16 17:00","연속"]
[445,"부산울산","동부산","구서노포#2 T/L","154kV 언양-산막 등 2개 T/L 자기애관 교체공사","비표준형 자기애관 교체 자기애관을 폴리머 애관으로 교체 및 직선슬리브 작업","2022-03-28 09:00","2022-04-08 18:00","취소","취소","연속"]
[446,"부산울산","동부산","구서노포#1 T/L","154kV 언양-산막 등 2개 T/L 자기애관 교체공사","비표준형 자기애관 교체 자기애관을 폴리머 애관으로 교체 및 직선슬리브 작업","2022-03-21 09:00","2022-03-26 18:00","취소","취소","연속"]
[447,"부산울산","동부산","신울산명례#1 T/L","명례S/S 617CB 가스누기 보수 조치","명례S/S 617CB 가스누기 보수(신울산-명례#1T/L)","2022-03-02 09:00","2022-03-03 18:00","2022-03-02 09:00","2022-03-03 18:00","연속"]
[448,"부산울산","동부산","수영정보#2 T/L","수영S/S 657GIS 보통점검","수영S/S 657GIS 보통점검 병행)정보S/S 637GIS 보통점검","2022-03-05 09:30","2022-03-05 17:00","취소","취소","연속"]
[449,"부산울산","동부산","신양산S/S #65 BUS","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","2022-03-14 09:00","2022-03-18 18:00","2022-03-14 09:00","2022-03-18 18:00","연속"]
[450,"부산울산","동부산","신양산구서#1 T/L","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","2022-03-14 09:00","2022-03-14 18:00","2022-03-14 09:00","2022-03-14 18:00","연속"]
[451,"부산울산","동부산","수영우동 T/L","우동S/S 617GIS 차단기 동작시험","우동S/S 617GIS 차단기 동작시험","2022-03-04 09:30","2022-03-04 14:00","취소","취소","연속"]
[452,"부산울산","북부산","물금삼랑진PP#2 T/L","물금S/S 154kV 양산열병합 신규수용공사","170kV GIS 50kA 1,250A 2CCT 증설 - 67BAY #2DS부 시험가압","2022-03-04 15:00","2022-03-05 18:00","2022-03-02 15:00","2022-03-03 18:00","연속"]
[453,"부산울산","북부산","물금삼랑진PP#2 T/L","물금S/S 154kV 양산열병합 신규수용공사","170kV GIS 50kA 1,250A 2CCT 증설 - 67BAY 케이블 접속 후 무부하가압","2022-03-24 15:00","2022-03-25 15:00","2022-03-24 15:00","2022-03-25 15:00","연속"]
[454,"부산울산","북부산","물금삼랑진PP#1 T/L","물금S/S 154kV 양산열병합 신규수용공사","170kV GIS 50kA 1,250A 2CCT 증설 - 63BAY 케이블 접속 후 무부하가압","2022-03-23 15:00","2022-03-24 15:00","2022-03-23 15:00","2022-03-24 15:00","연속"]
[455,"부산울산","북부산","물금삼랑진PP#1 T/L","22-23년 북부산전력지사 변전 총액공사","삼랑진S/Y 154KV 물금-삼랑진PP #1T/L GIS 하자점검","2022-03-28 10:00","2022-03-28 18:00","2022-03-28 10:00","2022-03-28 18:00","연속"]
[456,"부산울산","북부산","북부산삼랑진PP T/L","22-23년 북부산전력지사 변전 총액공사","삼랑진S/Y 154KV 북부산-삼랑진PP T/L GIS 하자점검","2022-03-30 10:00","2022-03-30 18:00","취소","취소","연속"]
[457,"부산울산","북부산","물금삼랑진PP#2 T/L","22-23년 북부산전력지사 변전 총액공사","삼랑진S/Y 154KV 물금-삼랑진PP #2T/L GIS 하자점검","2022-03-29 10:00","2022-03-29 18:00","2022-03-29 10:00","2022-03-29 18:00","연속"]
[458,"부산울산","북부산","양산산막#1 T/L","22-23년 북부산전력지사 변전 총액공사","양산S/S 154KV 양산-산막#1T/L GIS 하자점검","2022-03-22 09:00","2022-03-22 18:00","2022-03-22 09:00","2022-03-22 18:00","연속"]
[459,"부산울산","북부산","양산산막#2 T/L","22-23년 북부산전력지사 변전 총액공사","양산S/S 154KV 양산-산막#2T/L GIS 하자점검","2022-03-23 09:00","2022-03-23 18:00","2022-03-23 09:00","2022-03-23 18:00","연속"]
[460,"부산울산","북부산","엄궁학장#2 T/L","사상-하단간 도시철도공사 관련 관로 및 맨홀 매달기 사전작업","M/H#7, 8, 9 접속함 진동방지 및 활락방지 작업","2022-03-14 09:00","2022-03-18 18:00","취소","취소","연속"]
[461,"부산울산","북부산","엄궁학장#1 T/L","사상-하단간 도시철도공사 관련 관로 및 맨홀 매달기 사전작업","M/H#7, 8, 9 접속함 진동방지 및 활락방지 작업","2022-03-07 09:00","2022-03-11 18:00","취소","취소","연속"]
[462,"부산울산","북부산","호포물금 T/L","22-23년 북부산전력지사 변전 총액공사","호포S/S 154kV 호포-물금T/L GIS 차단기 조작시험","2022-03-21 09:00","2022-03-21 18:00","2022-03-16 10:00","2022-03-16 18:00","연속"]
[463,"부산울산","서부산","녹공마천#2 T/L","녹공S/S 녹공-마천#2T/L 송전선로 보호 IED 성능개선","녹공S/S 녹공-마천#2T/L 송전선로 보호 IED 성능개선 병행작업 : 마천S/S 녹공-마천#2T/L 송전선로 보호 IED 성능개선","2022-03-08 09:00","2022-03-08 18:00","2022-03-08 09:00","2022-03-08 18:00","연속"]
[464,"부산울산","서부산","녹공마천#1 T/L","녹공S/S 녹공-마천#1T/L 송전선로 보호 IED 성능개선","녹공S/S 녹공-마천#1T/L 송전선로 보호 IED 성능개선 병행작업 : 마천S/S 녹공-마천#1T/L 송전선로 보호 IED 성능개선","2022-03-07 09:00","2022-03-07 18:00","2022-03-07 09:00","2022-03-07 18:00","연속"]
[465,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진-영남TP T/L 접속설비보강공사","2T/L : 전선교체 5가닥교체공사(5가닥, 2.114C-KM) , 피뢰기갭혼교체작업","2022-03-22 07:00","2022-04-01 18:00","취소","취소","연속"]
[466,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진-영남TP T/L 접속설비보강공사","1T/L : 폴리머지지애자 설치 4기","2022-03-21 07:00","2022-03-21 18:00","취소","취소","연속"]
[467,"부산울산","울산","신울산S/S #62 BUS","신울산S/S 154kV 현대화공사","두왕#1 T/L 모선측 DS 철거","2022-03-11 08:00","2022-03-12 18:00","취소","취소","연속"]
[468,"부산울산","울산","신울산웅촌#1 T/L","2021~2022년 북부산전력지사 지중송전 위탁정비공사","EBA 절연유 채취 및 절연유 보충작업","2022-03-02 09:00","2022-03-03 18:00","2022-03-02 09:00","2022-03-03 18:00","연속"]
[469,"부산울산","울산","신울산울산#2 T/L","신울산S/S 154kV 현대화공사","현대화 GIS 내전압 시험관련 절연이격거리 확보","2022-03-14 08:30","2022-03-15 17:00","취소","취소","연속"]
[470,"부산울산","울산","신울산명례#2 T/L","신울산S/S 154kV 현대화공사","현대화 GIS 내전압 시험관련 절연이격거리 확보","2022-03-18 08:30","2022-03-19 17:00","취소","취소","연속"]
[471,"부산울산","울산","신울산S/S #67 BUS","신울산S/S 154kV 현대화공사","두왕#1 T/L 모선측 DS 철거","2022-03-10 08:00","2022-03-10 18:00","취소","취소","연속"]
[472,"부산울산","울산","신울산두왕#1 T/L","신울산S/S 154kV 현대화공사","기설 GCB, 모선DS 철거 및 M.Tr 2차 지중관로 공사 복귀 시 현대화(GIS) 설비로 복귀","2022-03-10 08:00","2022-07-15 18:00","취소","취소","연속"]
[473,"부산울산","울산","신울산S/S #61 BUS","신울산S/S 154kV 현대화공사","기설 6271 DS 철거관련 휴전 - 154kV 현대화 관련 BUS DUCT 구성 - 154kV 6279, 6276, 6271, 6276 철거","2022-03-03 08:00","2022-03-04 17:00","취소","취소","연속"]
[474,"부산울산","울산","신울산S/S #66 BUS","신울산S/S 154kV 현대화공사","기설 6272 DS 철거관련 휴전 - 154kV 현대화 관련 BUS DUCT 구성 - 154kV 6279, 6276, 6271, 6276 철거","2022-03-02 08:00","2022-03-02 17:00","취소","취소","연속"]
[475,"부산울산","울산","신온산온산#3 T/L","22~23년 변전협력회사 총액공사","- GIS 보통점검","2022-03-28 09:00","2022-03-28 18:00","2022-03-28 09:00","2022-03-28 18:00","연속"]
[476,"부산울산","울산","신온산온산#1 T/L","22~23년 변전협력회사 총액공사","- 차단기 동작시험","2022-03-15 09:00","2022-03-15 18:00","2022-03-15 09:00","2022-03-15 18:00","연속"]
[477,"부산울산","울산","용연울산TP#1 T/L","22~23년 변전협력회사 총액공사","- GIS 보통점검 - 전자변 교체","2022-03-14 09:00","2022-03-14 18:00","2022-03-14 09:00","2022-03-14 18:00","연속"]
[478,"부산울산","울산","용연울산TP#3 T/L","22~23년 변전협력회사 총액공사","양단 차단기 동작시험 피뢰기 보통점검","2022-03-10 09:00","2022-03-10 18:00","2022-03-10 09:00","2022-03-10 18:00","연속"]
[479,"부산울산","울산","용연울산TP#2 T/L","22~23년 변전협력회사 총액공사","- GIS 보통점검 - 전자변 교체","2022-03-16 09:00","2022-03-16 18:00","2022-03-16 09:00","2022-03-16 18:00","연속"]
[480,"부산울산","울산","두왕울산#2 T/L","22년 상반기 154kV GIS 정밀점검공사","- 태광#2T/L 시험가압 선로","2022-03-15 17:00","2022-03-15 18:00","2022-03-15 17:00","2022-03-15 18:00","연속"]
[481,"부산울산","울산","울주외동#1 T/L","22~23년 변전협력회사 총액공사","피뢰기 보통점검","2022-03-10 09:00","2022-03-10 18:00","취소","취소","연속"]
[482,"부산울산","울산","울주외동#2 T/L","22~23년 변전협력회사 총액공사","피뢰기 보통점검","2022-03-11 09:00","2022-03-11 18:00","취소","취소","연속"]
[483,"부산울산","울산","웅촌서창#1 T/L","22~23년 변전협력회사 총액공사","차단기 동작시험","2022-03-30 09:00","2022-03-30 18:00","2022-03-27 09:00","2022-03-27 18:00","연속"]
[484,"부산울산","울산","웅촌서창#2 T/L","22~23년 변전협력회사 총액공사","- GIS 보통점검","2022-03-29 09:00","2022-03-29 18:00","2022-03-26 09:00","2022-03-26 18:00","연속"]
[485,"부산울산","직할","범일서면#2 T/L","22-23년 직할 변전협력회사 총액공사","서면S/S 154kV 범일-서면#1,2T/L GIS 보통점검, 에어링 밸브 교체 범일S/S 154kV 범일-서면#1,2T/L GIS 보통점검","2022-03-12 09:00","2022-03-12 18:00","취소","취소","연속"]
[486,"부산울산","직할","범일서면#1 T/L","22-23년 직할 변전협력회사 총액공사","서면S/S 154kV 범일-서면#1,2T/L GIS 보통점검, 에어링 밸브 교체 범일S/S 154kV 범일-서면#1,2T/L GIS 보통점검","2022-03-12 09:00","2022-03-12 18:00","취소","취소","연속"]
[487,"경남","직할","신김해삼정#1 T/L","신김해S/S 154kV (구)#62M.Tr 1차 GIS 철거공사","신김해S/S 154kV (구)#62M.Tr 1차 GIS 철거공사 안전이격휴전","2022-03-21 09:00","2022-03-27 18:00","2022-03-21 09:00","2022-03-27 18:00","매일"]
[488,"경남","직할","신김해진례#1 T/L","진례S/S 신김해-진례#1T/L GIS 초기점검","진례S/S 신김해-진례#1T/L GIS 초기점검 (병행)신김해S/S 신김해-진례#1T/L 보통점검, LA,PT 보통점검","2022-03-13 09:30","2022-03-13 17:30","2022-03-13 09:30","2022-03-13 17:30","연속"]
[489,"경남","진주","하동개양#2 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-07 13:00","2022-03-07 18:00","2022-03-11 13:00","2022-03-11 18:00","연속"]
[490,"경남","진주","사천개양#1 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-08 09:00","2022-03-08 13:00","2022-03-08 09:00","2022-03-08 13:00","연속"]
[491,"경남","진주","사천개양#2 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-08 13:00","2022-03-08 18:00","2022-03-08 13:00","2022-03-08 18:00","연속"]
[492,"경남","진주","하동개양#1 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-07 09:00","2022-03-07 13:00","2022-03-11 09:00","2022-03-11 13:00","연속"]
[493,"경남","진주","함양거창#1 T/L","거창S/S 함양-거창#1,2T/L GIS 조작시험","거창S/S 함양-거창#1,2T/L GIS 조작시험","2022-03-15 09:00","2022-03-15 13:00","2022-03-15 09:00","2022-03-15 13:00","연속"]
[494,"경남","진주","함양거창#2 T/L","거창S/S 함양-거창#1,2T/L GIS 조작시험","거창S/S 함양-거창#1,2T/L GIS 조작시험","2022-03-15 13:00","2022-03-15 16:00","2022-03-15 13:00","2022-03-15 16:00","연속"]
[495,"경남","진주","의령동진주#2 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-10 13:00","2022-03-10 18:00","취소","취소","연속"]
[496,"경남","진주","의령동진주#1 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-10 09:00","2022-03-10 13:00","취소","취소","연속"]
[497,"경남","진주","동진주진주#2 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-10 13:00","2022-03-10 18:00","취소","취소","연속"]
[498,"경남","진주","진주개양#1 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-19 09:00","2022-03-19 13:00","취소","취소","연속"]
[499,"경남","진주","동진주진주#1 T/L","진주S/S #1M.Tr 3차 부싱 교체","진주S/S #1M.Tr 3차 부싱 교체","2022-03-23 09:00","2022-03-25 18:00","2022-03-23 09:00","2022-03-25 18:00","연속"]
[500,"경남","진주","진주개양#2 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-19 13:00","2022-03-19 18:00","취소","취소","연속"]
[501,"경남","진주","하동하동화력 T/L","하동S/S 태금-하동T/L, 하동-하동화력T/L GIS 조작시험","하동S/S 태금-하동T/L, 하동-하동화력T/L GIS 조작시험","2022-03-10 13:00","2022-03-10 16:00","2022-03-10 13:00","2022-03-10 16:00","연속"]
[502,"경남","진주","태금하동#1 T/L","하동S/S 태금-하동T/L, 하동-하동화력T/L GIS 조작시험","하동S/S 태금-하동T/L, 하동-하동화력T/L GIS 조작시험","2022-03-10 09:00","2022-03-10 13:00","2022-03-10 09:00","2022-03-10 13:00","연속"]
[503,"경남","진주","쌍림합천#1 T/L","합천S/S 쌍림-합천#1,2T/L GIS 조작시험","합천S/S 쌍림-합천#1,2T/L GIS 조작시험","2022-03-11 09:00","2022-03-11 13:00","취소","취소","연속"]
[504,"경남","진주","쌍림합천#2 T/L","합천S/S 쌍림-합천#1,2T/L GIS 조작시험","합천S/S 쌍림-합천#1,2T/L GIS 조작시험","2022-03-11 13:00","2022-03-11 16:00","취소","취소","연속"]
[505,"경남","통영","신고성통영 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-06 13:00","2022-03-06 18:00","2022-03-06 13:00","2022-03-06 18:00","연속"]
[506,"경남","통영","신고성고성 T/L","2021-2022년 경남본부 지중송전 정비전문공사","PD집합반 설치","2022-03-06 09:00","2022-03-06 13:00","2022-03-06 09:00","2022-03-06 13:00","연속"]
[507,"경남","함안","김해S/S CB 6100","김해S/S 154kV #1-#2 BUS TIE GIS 보통점검","김해S/S 154kV #1-#2 BUS TIE GIS 보통점검","2022-03-31 09:30","2022-03-31 18:00","2022-03-31 09:30","2022-03-31 18:00","연속"]
[508,"경남","함안","매리김해#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","154kV 호포-매리T/L 24호 본철탑 조립시 안전이격 확보","2022-03-26 07:00","2022-03-29 18:00","취소","취소","매일"]
[509,"경남","함안","호포매리#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","154kV 호포-매리T/L 24호 본철탑 조립시 안전이격 확보","2022-03-26 07:00","2022-03-29 18:00","취소","취소","매일"]
[510,"경남","함안","진영수산#2 T/L","2021-2022년 경남본부 지중송전 정비전문공사","피뢰기 열화진단","2022-03-16 13:00","2022-03-16 18:00","2022-03-16 13:00","2022-03-16 18:00","연속"]
[511,"경남","함안","진영수산#1 T/L","2021-2022년 경남본부 지중송전 정비전문공사","피뢰기 열화진단","2022-03-16 09:00","2022-03-16 13:00","2022-03-16 09:00","2022-03-16 13:00","연속"]
[512,"경남","함안","신마산칠서#2 T/L","신마산S/S 154kV 신마산-칠서#2T/L CB 보통점검 외","신마산S/S 154kV 신마산-칠서#2T/L CB 보통점검 칠서S/S 154kV 신마산-칠서#2T/L GIS 조작시험","2022-03-15 09:30","2022-03-15 18:00","2022-03-15 09:30","2022-03-15 18:00","연속"]
[513,"경남","함안","신마산칠서#1 T/L","신마산S/S 154kV 신마산-칠서#1T/L CB 보통점검 외","신마산S/S 154kV 신마산-칠서#1T/L CB 보통점검 칠서S/S 154kV 신마산-칠서#1T/L GIS 조작시험","2022-03-14 09:30","2022-03-14 18:00","2022-03-14 09:30","2022-03-14 18:00","연속"]
[514,"경남","함안","창녕초동#1 T/L","초동S/S 154kV 창녕-초동#1T/L GIS 보통점검","초동S/S 154kV 창녕-초동#1T/L GIS 보통점검","2022-03-17 09:30","2022-03-17 18:00","2022-03-17 09:30","2022-03-17 18:00","연속"]
[515,"경남","함안","창녕초동#2 T/L","초동S/S 154kV 창녕-초동#2T/L GIS 보통점검","초동S/S 154kV 창녕-초동#2T/L GIS 보통점검","2022-03-18 09:30","2022-03-18 18:00","2022-03-18 09:30","2022-03-18 18:00","연속"]