{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":18,"n_cols":11,"rows_kept":18,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 4월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S CB 8471","신가평변전소 765kV GIS 점검공사","8471CB 보통점검공사","2022-04-26 09:00","2022-04-28 18:00","2022-04-26 09:00","2022-04-28 18:00","연속"]
[2,"경기북부","구리","신가평S/S #2 M.Tr","765kV GIS 정밀점검공사, #2M.Tr 온도센서 교체","765kV GIS 정밀점검공사, #2M.Tr 온도센서 교체","2022-04-04 09:00","2022-04-05 18:00","2022-04-04 09:00","2022-04-05 18:00","연속"]
[3,"강원","태백","신태백S/S #2 M.Tr","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 765kV 83Bay B/F PNL 교체 [병행] 신태백S/S 345kV 7371CB 초기점검(04/04)","2022-04-04 09:00","2022-04-15 18:00","2022-04-04 09:00","2022-04-15 18:00","연속"]
[4,"강원","태백","신태백신한울NP#2 T/L","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 765kV 83Bay B/F PNL 교체","2022-04-04 09:00","2022-04-15 18:00","2022-04-04 09:00","2022-04-15 18:00","연속"]
[5,"강원","태백","신태백S/S #3 M.Tr","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 765kV 84Bay B/F PNL 교체 [병행] 신태백S/S 345kV 7671CB 초기점검 (04/18) [병행] 신태백S/S 345kV 7600CB 초기점검 (04/19)","2022-04-18 09:00","2022-04-29 18:00","2022-04-18 09:00","2022-04-29 18:00","연속"]
[6,"강원","태백","신태백신한울NP#1 T/L","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 765kV 84Bay B/F PNL 교체","2022-04-18 09:00","2022-04-29 18:00","2022-04-18 09:00","2022-04-29 18:00","연속"]
[7,"충북","직할","신중부S/S CB 8500","신중부S/S 765kV GIS 하자보수","신중부S/S 765kV GIS 유사고장 방지를 위한 제작사 하자보수 - GIS 정밀점검 및 부품교체","2022-04-18 09:00","2022-04-21 23:50","취소","취소","연속"]
[8,"충북","직할","신중부S/S #3 M.Tr","신중부S/S 765kV #3M.Tr 초기점검공사","신중부S/S 765kV #3M.Tr 초기점검공사 - 주기도래 기기점검 시행 신중부S/S 765kV GIS 유사고장 방지를 위한 제작사 하자보수 - GIS 정밀점검 및 부품교체","2022-04-25 09:00","2022-05-01 18:00","2022-04-25 09:00","2022-05-01 18:00","연속"]
[9,"충북","직할","신서산신중부#2 T/L","신중부S/S 765kV GIS 하자보수","신중부S/S 765kV GIS 유사고장 방지를 위한 제작사 하자보수 - GIS 정밀점검 및 부품교체","2022-04-01 09:00","2022-04-03 18:00","취소","취소","연속"]
[10,"대전세종충남","서산","신서산S/S #3 M.Tr","765kV 신서산-당진화력#2T/L 송전선로 및 차단실패보호반 대체공사","765kV 신서산-당진화력#2T/L 송전선로 및 차단실패보호반 대체공사 및 변압기 정밀점검","2022-04-11 09:00","2022-05-24 18:00","2022-04-11 09:00","2022-05-24 18:00","연속"]
[11,"대전세종충남","서산","신서산당진TP#2 T/L","765kV 신서산-당진화력#2T/L 송전선로 및 차단실패보호반 대체공사","765kV 신서산-당진화력#2T/L 송전선로 및 차단실패보호반 대체공사","2022-04-11 09:00","2022-04-20 18:00","2022-04-11 09:00","2022-04-20 18:00","연속"]
[12,"대전세종충남","서산","신서산신중부#1 T/L","[송전] 765kV 신서산-신중부T/L 항공구 교체공사","ㅇ765kV 신서산-신중부T/L No.12-13호 등 21개 경간 항공구 교체 시행 - 볼트탈락 및 항공구 탈락개소, 민원개소 등 전개소 정비시행","2022-04-04 07:00","2022-04-10 18:00","취소","취소","연속"]
[13,"대전세종충남","서산","신서산신중부#2 T/L","[송전] 22년 가공송전 순시점검 위탁공사 정밀점검","765kV 신서산-신중부#2T/L 정밀점검 - No.1~169(169기)","2022-04-21 08:00","2022-05-01 18:00","2022-04-21 08:00","2022-05-01 18:00","연속"]
[14,"대전세종충남",null,"당진T/P CB 8171","GIS 정밀점검","GIS 정밀점검","2022-04-25 10:00","2022-04-29 18:00","2022-04-25 10:00","2022-04-29 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":238,"n_cols":11,"rows_kept":238,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 4월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","동서울","동서울S/S #3 M.Tr","동서울S/S 노후 주변압기 교체 및 이설공사","○ 345kV 주변압기 교체 및 이설 * 11대 ○ 기타 부대작업 * 1식","2022-04-18 09:00","2022-05-10 18:00","2022-04-18 09:00","2022-05-10 18:00","연속"]
[2,"남서울","동서울","신용인동서울#2 T/L","동서울S/S 노후 주변압기 교체 및 이설공사","○ 345kV 주변압기 교체 및 이설 * 11대 ○ 기타 부대작업 * 1식","2022-04-05 15:00","2022-04-06 15:00","2022-04-12 14:00","2022-04-13 14:00","연속"]
[3,"남서울","영등포","신광명S/S CB 7171","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GCB 조작시험","2022-04-13 09:00","2022-04-13 14:00","취소","취소","연속"]
[4,"남서울","영등포","신광명S/S CB 7272","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GCB 조작시험","2022-04-18 09:00","2022-04-18 18:00","취소","취소","연속"]
[5,"남서울","영등포","신광명S/S CB 7500","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GIS 조작시험","2022-04-11 14:00","2022-04-11 18:00","취소","취소","연속"]
[6,"남서울","영등포","신광명S/S CB 7572","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GIS 조작시험","2022-04-11 09:00","2022-04-11 14:00","취소","취소","연속"]
[7,"남서울","영등포","신광명S/S CB 7472","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GCB 보통점검","2022-04-26 14:00","2022-04-26 18:00","취소","취소","연속"]
[8,"남서울","영등포","신광명S/S CB 7471","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GCB 보통점검","2022-04-26 09:00","2022-04-26 14:00","취소","취소","연속"]
[9,"남서울","영등포","신광명S/S CB 7672","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GIS 조작시험","2022-04-12 09:00","2022-04-12 14:00","취소","취소","연속"]
[10,"남서울","영등포","신광명S/S CB 7600","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GIS 조작시험","2022-04-12 14:00","2022-04-12 18:00","취소","취소","연속"]
[11,"남서울","영등포","신광명S/S #4 M.Tr","345kV 신광명S/S 노후 주변압기 교체공사(#4M.TR)","노후 주변압기 교체 * 2대 접지 및 기타 부대작업 *1식 병행작업 : #4M.Tr 1차측 EBA 설치","2022-04-04 09:00","2022-05-20 18:00","2022-04-06 09:00","2022-05-20 18:00","연속"]
[12,"남서울","영등포","신광명S/S CB 7100","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GCB 조작시험","2022-04-13 14:00","2022-04-13 18:00","취소","취소","연속"]
[13,"남서울","영등포","신광명S/S CB 7172","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GCB 보통점검","2022-04-14 09:00","2022-04-14 18:00","취소","취소","연속"]
[14,"남서울","영등포","신광명S/S CB 7271","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GCB 조작시험","2022-04-15 09:00","2022-04-15 14:00","취소","취소","연속"]
[15,"남서울","영등포","신광명S/S CB 7200","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GCB 조작시험","2022-04-15 14:00","2022-04-15 18:00","취소","취소","연속"]
[16,"남서울","영등포","신광명S/S CB 7400","'22~23년 영등포P/O 변전협력회사 총액공사","- 345kV GCB 보통점검","2022-04-25 09:00","2022-04-25 18:00","취소","취소","연속"]
[17,"남서울","직할","신문래S/S #1 M.Tr","362kV GIS 보통점검 공사","362kV GIS 보통점검 공사 - 1,2차 GIS 보통점검 시행","2022-04-05 09:00","2022-04-05 18:00","2022-04-05 09:00","2022-04-05 18:00","연속"]
[18,"남서울","직할","신문래S/S CB 7100","362kV GIS 보통점검 공사","362kV GIS 보통점검 공사","2022-04-06 09:00","2022-04-06 18:00","2022-04-06 09:00","2022-04-06 18:00","연속"]
[19,"남서울","직할","신문래S/S #3 M.Tr","362kV GIS 보통점검 공사","362kV GIS 보통점검 공사 - 1,2차 GIS 보통점검 시행","2022-04-14 09:00","2022-04-14 18:00","2022-04-14 09:00","2022-04-14 18:00","연속"]
[20,"남서울","직할","신문래S/S CB 7300","362kV GIS 보통점검 공사","362kV GIS 보통점검 공사","2022-04-13 09:00","2022-04-13 18:00","2022-04-13 09:00","2022-04-13 18:00","연속"]
[21,"남서울","직할","신문래S/S CB 7200","362kV GIS 보통점검 공사","362kV GIS 보통점검 공사","2022-04-12 09:00","2022-04-12 18:00","2022-04-12 09:00","2022-04-12 18:00","연속"]
[22,"남서울","직할","신문래S/S #2 M.Tr","362kV GIS 보통점검 공사","362kV GIS 보통점검 공사 - 1,2차 GIS 보통점검 시행","2022-04-11 09:00","2022-04-11 18:00","2022-04-11 09:00","2022-04-11 18:00","연속"]
[23,"인천","부평","신김포서인천CC T/L","신김포서인천CC T/L 결상회로 보완, 7100, 7171GiS 조작시험","신김포서인천CC T/L 결상회로 보완, 7100, 7171GiS 조작시험","2022-04-04 09:00","2022-04-04 18:00","취소","취소","연속"]
[24,"인천","직할","갈산S/S #1 M.Tr","갈산S/S #1M.Tr 변압기, 1,2차 GIS하자점검","갈산S/S #1M.Tr 변압기, 1,2차 GIS하자점검","2022-04-04 09:30","2022-04-06 18:00","취소","취소","연속"]
[25,"인천","부평","신김포신인천CC T/L","신김포신인천CC T/L 결상회로 보완, 7700, 7771GiS 조작시험","신김포신인천CC T/L 결상회로 보완, 7700, 7771GiS 조작시험","2022-04-05 09:00","2022-04-05 18:00","취소","취소","연속"]
[26,"인천","부평","신경서서인천CC T/L","서인천S/Y 신경서서인천CC T/L 보호반 교체","서인천S/Y, 신경서S/S 신경서서인천CC T/L 보호반 교체 - 7200, 7271GIS 보통점검(서인천) - 7400, 7472GIS 보통점검(신경서)","2022-04-11 09:00","2022-04-15 18:00","2022-04-11 09:00","2022-04-15 18:00","연속"]
[27,"인천","시흥","신시흥#2S/S #4 M.Tr","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사(이격거리 확보)","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사(이격거리 확보)","2022-04-11 09:00","2022-04-27 18:00","취소","취소","연속"]
[28,"인천","시흥","신시흥영흥TP#3 T/L","영흥#2S/Y 신시흥영흥TP#3 T/L 보호반 성능개선 및 결상회로보완","영흥#2S/Y 신시흥영흥TP#3 T/L 보호반 성능개선 및 결상회로보완","2022-04-11 09:00","2022-04-12 14:00","2022-04-11 09:00","2022-04-12 14:00","연속"]
[29,"인천","부평","서인천C/C #1 Sh.R (CB 7379)","서인천C/C #1 Sh.R 보호반 성능개선 및 7379GIS 보통점검","서인천C/C 345kV #1 Sh.R 보호반 성능개선 및 7379GIS 보통점검","2022-04-12 09:00","2022-04-12 18:00","2022-04-12 09:00","2022-04-12 18:00","연속"]
[30,"인천","시흥","신시흥신광명#1 T/L","신시흥S/S 신시흥신광명#1 T/L 결상회로보완","신시흥S/S 신시흥신광명#1 T/L 결상회로보완","2022-04-12 14:00","2022-04-12 18:00","취소","취소","연속"]
[31,"인천","시흥","신시흥영흥TP#4 T/L","신시흥S/S 신시흥영흥TP#4 T/L 보호반 성능개선 및 결상회로보완","신시흥S/S 신시흥영흥TP#4 T/L 보호반 성능개선 및 결상회로보완","2022-04-13 09:00","2022-04-14 18:00","2022-04-13 09:00","2022-04-14 18:00","연속"]
[32,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S #1M.Tr 휴전작업","3차측 VCB교체, #1S.Tr 보통점검, 부싱절연유 채유, 6144GIS 조작시험, CVT초기점검","2022-04-18 09:00","2022-04-22 18:00","2022-04-18 09:00","2022-04-22 18:00","연속"]
[33,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥#2S/Y 영흥TP연락#1 T/L 보호반 성능개선 및 결상회로보완","영흥#2S/Y 영흥TP연락#1 T/L 보호반 성능개선 및 결상회로보완","2022-04-18 09:00","2022-04-19 18:00","2022-04-18 09:00","2022-04-19 18:00","연속"]
[34,"인천","부평","서인천C/C #4 Sh.R (7A79)","서인천C/C #4 Sh.R 휴전작업","서인천C/C 345kV #4 Sh.R 보통점검 및 7A79GIS 보통점검","2022-04-19 09:00","2022-04-19 18:00","2022-04-19 09:00","2022-04-19 18:00","연속"]
[35,"인천","부평","서인천C/C #1 CLR (CB 7077, 7277)","서인천C/C 345kV #70-72 CLR 휴전","서인천C/C 345kV #70-72 CLR #077, 7277GIS 조작시험","2022-04-20 09:00","2022-04-20 13:00","2022-04-20 09:00","2022-04-20 13:00","연속"]
[36,"인천","시흥","영흥1TP영흥2TP#2 T/L","영흥#2S/Y 영흥TP연락#2 T/L 보호반 성능개선 및 결상회로보완","영흥#2S/Y 영흥TP연락#2 T/L 보호반 성능개선 및 결상회로보완","2022-04-20 09:00","2022-04-21 18:00","2022-04-20 09:00","2022-04-21 18:00","연속"]
[37,"인천","부평","서인천C/C #2 CLR (CB 7577, 7777)","서인천C/C 345kV #75-77 CLR 휴전","서인천C/C 345kV #75-77 CLR #7577, 7777GIS 조작시험","2022-04-20 13:00","2022-04-20 18:00","2022-04-20 13:00","2022-04-20 18:00","연속"]
[38,"인천","부평","서인천C/C #2 CLR (CB 7577, 7777)","서인천C/C 345kV #75-77 CLR 휴전","서인천C/C 345kV #75-77 CLR #7577, 7777GIS 조작시험","2022-04-20 13:00","2022-04-20 18:00","취소","취소","연속"]
[39,"인천","부평","신경서S/S CB 7300","신경서S/S 7300GIS 보통점검 및 전자변 교체","신경서S/S 7300GIS 보통점검 및 전자변 교체","2022-04-25 09:00","2022-04-25 18:00","2022-04-25 09:00","2022-04-25 18:00","연속"]
[40,"인천","부평","신경서S/S CB 7272","신경서S/S 7272GIS 보통점검 및 전자변교체","신경서S/S 7272GIS 보통점검 및 전자변교체","2022-04-26 09:00","2022-04-26 18:00","2022-04-26 09:00","2022-04-26 18:00","연속"]
[41,"인천","부평","신경서S/S CB 7371","신경서S/S 7371GIS 보통점검 및 전자변 교체","신경서S/S 7371GIS 보통점검 및 전자변 교체","2022-04-27 09:00","2022-04-27 18:00","2022-04-27 09:00","2022-04-27 18:00","연속"]
[42,"인천","부평","신경서S/S CB 7172","신경서S/S 7172GIS 조작시험 및 전자변교체","신경서S/S 7172GIS 조작시험 및 전자변교체","2022-04-28 09:00","2022-04-28 13:00","2022-04-28 09:00","2022-04-28 13:00","연속"]
[43,"인천","시흥","서서울#2신시흥#1 T/L","신시흥S/S 서서울2신시흥#1 T/L 결상회로보완","신시흥S/S 서서울2신시흥#1 T/L 결상회로보완","2022-04-28 09:00","2022-04-28 14:00","2022-04-28 09:00","2022-04-28 14:00","연속"]
[44,"인천","부평","신경서S/S CB 7200","신경서S/S 7200GIS 조작시험","신경서S/S 7200GIS 조작시험","2022-04-28 13:00","2022-04-28 18:00","2022-04-28 13:00","2022-04-28 18:00","연속"]
[45,"인천","시흥","서서울#2신시흥#2 T/L","신시흥S/S 서서울2신시흥#2 T/L 보호반 성능개선 및 결상회로보완","신시흥S/S 서서울2신시흥#2 T/L 보호반 성능개선 및 결상회로보완","2022-04-28 14:00","2022-04-28 18:00","취소","취소","연속"]
[46,"인천","부평","신경서S/S CB 7171","신경서S/S 7171GIS 조작시험","신경서S/S 7171GIS 조작시험","2022-04-29 09:00","2022-04-29 13:00","2022-04-29 09:00","2022-04-29 13:00","연속"]
[47,"인천","시흥","신시흥신안산#2 T/L","신시흥S/S 신시흥신안산#2T/L 결상회로보완","신시흥S/S 신시흥신안산#2T/L 결상회로보완","2022-04-29 09:00","2022-04-29 18:00","2022-04-29 09:00","2022-04-29 18:00","연속"]
[48,"인천","부평","신경서S/S CB 7100","신경서S/S 7100GIS 조작시험","신경서S/S 7100GIS 조작시험","2022-04-29 13:00","2022-04-29 18:00","2022-04-29 13:00","2022-04-29 18:00","연속"]
[49,"경기북부","고양","신파주S/S #76 BUS","345kV 신파주S/S #4M.Tr용 362kV GIS 증설공사(전문)","○ 362kV GIS(4000A, 50A) x 1CB 설치 ○ 기타 부대공사 x 1식","2022-04-04 09:00","2022-04-21 18:00","2022-04-04 09:00","2022-04-21 18:00","연속"]
[50,"경기북부","고양","신파주S/S CB 7771","345kV 신파주S/S #4M.Tr용 362kV GIS 증설공사(전문)","○ 362kV GIS(4000A, 50A) x 1CB 설치 ○ 기타 부대공사 x 1식","2022-04-04 09:00","2022-04-22 15:00","2022-04-04 09:00","2022-04-22 15:00","연속"]
[51,"경기북부","고양","신파주S/S CB 7500","362kV GIS 보통점검 - 변전총액공사","신파주S/S 345kV 7500GIS 보통점검","2022-04-27 09:30","2022-04-27 18:00","2022-04-27 09:30","2022-04-27 18:00","연속"]
[52,"경기북부","고양","신파주S/S CB 7572","362kV GIS 보통점검 - 변전총액공사","신파주S/S 345kV 7572GIS 보통점검","2022-04-26 09:30","2022-04-26 18:00","2022-04-26 09:30","2022-04-26 18:00","연속"]
[53,"경기북부","고양","신파주S/S CB 7300","362kV GIS 보통점검 - 변전총액공사","신파주S/S 345kV 7300GIS 보통점검","2022-04-20 09:30","2022-04-20 18:00","2022-04-20 09:30","2022-04-20 18:00","연속"]
[54,"경기북부","고양","신파주S/S CB 7371","362kV GIS 보통점검 - 변전총액공사","신파주S/S 345kV 7371GIS 보통점검","2022-04-19 09:30","2022-04-19 18:00","2022-04-19 09:30","2022-04-19 18:00","연속"]
[55,"경기북부","구리","신의정부미금#2 T/L","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","- 미금S/S 345kV 신의정부-미금#2T/L LA A, B, C 보통점검 - 미금S/S 345kV 신의정부-미금#2T/L PT A, B, C 초기점검","2022-04-06 09:00","2022-04-06 18:00","취소","취소","연속"]
[56,"경기북부","구리","신의정부미금#1 T/L","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","- 미금S/S 345kV 신의정부-미금#1T/L LA A, B, C 보통점검 - 미금S/S 345kV 신의정부-미금#1T/L PT A, B, C 초기점검","2022-04-05 09:00","2022-04-05 18:00","취소","취소","연속"]
[57,"경기북부","구리","신가평미금#2 T/L","2022~23 구리전력 변전협력 총액공사","미금S/S 신가평-미금#2T/L GIS (7871, 7800 CB) 보통점검공사","2022-04-21 09:00","2022-04-22 18:00","2022-04-21 09:00","2022-04-22 18:00","연속"]
[58,"경기북부","구리","미금S/S CB 7271","2022~23 구리전력 변전협력 총액공사","미금S/S 미금-성동#2T/L 7271 CB 보통점검","2022-04-07 09:00","2022-04-07 18:00","취소","취소","연속"]
[59,"경기북부","구리","미금S/S #1 Sh.R (CB 7179)","미금S/S #1Sh.R 고장복구공사","미금S/S #1Sh.R 대체 * 1식","2022-04-25 09:00","2022-06-30 18:00","2022-04-25 09:00","2022-06-30 18:00","연속"]
[60,"경기북부","구리","신가평S/S #3 Sh.R (CB 7479)","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","장기사용 배전반 교체공사 -신가평S/S #74Bay B/F보호반 교체","2022-04-11 09:00","2022-04-15 18:00","취소","취소","연속"]
[61,"경기북부","구리","신가평포천LNGCC#1 T/L","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","장기사용 배전반 교체공사 -신가평S/S #74Bay B/F보호반 교체","2022-04-11 09:00","2022-04-15 18:00","2022-04-11 09:00","2022-04-15 18:00","연속"]
[62,"경기북부","구리","신가평S/S CB 7471","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","장기사용 배전반 교체공사 -신가평S/S #74Bay B/F보호반 교체","2022-04-11 09:00","2022-04-15 18:00","취소","취소","연속"]
[63,"경기북부","구리","신포천S/S CB 7271","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-포천LNGCC #2T/L GIS (7271 CB) 보통점검","2022-04-28 14:00","2022-04-28 18:00","2022-04-28 14:00","2022-04-28 18:00","연속"]
[64,"경기북부","구리","신포천S/S CB 7200","2022~23 구리전력 변전정비 총액공사","신포천S/S 345kV 포천LNG#2-#2M.Tr TIE 7200 차단기 보통점검","2022-04-28 09:00","2022-04-28 14:00","2022-04-28 09:00","2022-04-28 14:00","연속"]
[65,"경기북부","구리","신포천S/S #4 M.Tr","22~23년 구리전력 변전협력 총액공사","신포천S/S 345kV #4M.Tr 보통점검","2022-04-18 09:00","2022-04-19 18:00","2022-04-18 09:00","2022-04-19 18:00","연속"]
[66,"경기북부","구리","신포천S/S #3 M.Tr","22~23년 구리전력 변전협력 총액공사","신포천S/S 345kV #3M.Tr 보통점검","2022-04-14 09:00","2022-04-15 18:00","2022-04-14 09:00","2022-04-15 18:00","연속"]
[67,"경기북부","구리","신포천S/S #1 M.Tr","22~23년 구리전력 변전협력 총액공사","신포천S/S 345kV #1M.Tr 보통점검","2022-04-12 09:00","2022-04-13 18:00","2022-04-12 09:00","2022-04-13 18:00","연속"]
[68,"경기북부","직할","신의정부양주#1 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7371 보통점검","2022-04-11 09:00","2022-04-12 18:00","2022-04-11 09:00","2022-04-12 18:00","연속"]
[69,"경기북부","직할","신의정부양주#2 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7471 보통점검","2022-04-13 09:00","2022-04-14 18:00","2022-04-13 09:00","2022-04-14 18:00","연속"]
[70,"경기북부","직할","신가평신의정부#1 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7800, 7871 조작시험","2022-04-20 09:00","2022-04-20 18:00","2022-04-20 09:00","2022-04-20 18:00","연속"]
[71,"경기북부","직할","신가평신의정부#2 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7700 초기점검, 7771 보통점검","2022-04-18 09:00","2022-04-19 18:00","2022-04-18 09:00","2022-04-19 18:00","연속"]
[72,"경기북부","직할","양주S/S #1 M.Tr","양주S/S 종합예방진단시스템 시스템 조정","○ OLTC TPI 세팅값 조정","2022-04-26 10:00","2022-04-26 14:00","2022-04-05 09:00","2022-04-05 18:00","연속"]
[73,"경기북부","직할","양주S/S #3 M.Tr","345kV 양주S/S STATCOM 건설사업","#6S.Tr 증설 및 시험(STATCOM #2S.Tr)","2022-04-18 09:00","2022-04-22 18:00","2022-04-25 09:00","2022-04-29 18:00","연속"]
[74,"경기북부","직할","양주S/S #3 M.Tr","345kV 양주S/S STATCOM 건설사업","#6S.Tr 증설 및 시험(STATCOM #2S.Tr)","2022-04-11 09:00","2022-04-15 18:00","2022-04-18 09:00","2022-04-22 18:00","연속"]
[75,"경기북부","직할","양주S/S SVC M.Tr (CB 7771, 7700)","345kV 양주S/S STATCOM 건설사업","STATCOM 실부하 가압(4/11~15) 및 시운전","2022-04-25 09:00","2022-05-31 18:00","취소","취소","연속"]
[76,"경기","군포","신온양서서울#2 T/L","서서울SS 신온양-서서울#2TL(7772,7700) GIS보통 등","신온양-서서울#2T/L GIS 보통 및 결상회로 개선, PT보통","2022-04-19 09:00","2022-04-19 18:00","취소","취소","연속"]
[77,"경기","군포","신온양서서울#1 T/L","서서울SS 신온양-서서울#1TL(7472,7400) GIS보통 등","신온양-서서울#1T/L GIS 보통 및 결상회로 개선, PT보통","2022-04-18 09:00","2022-04-18 18:00","취소","취소","연속"]
[78,"경기","군포","서서울S/S #1 M.Tr","서서울S/S 345kV #1M.Tr 보호반 대체","#1M.Tr 보호반 대체, 96P,D커버설치, 1차 GIS, 3차 VCB조작, PT 보통점검","2022-04-04 09:00","2022-04-08 18:00","2022-04-04 09:00","2022-04-08 18:00","연속"]
[79,"경기","동부","곤지암S/S #1 Sh.R (CB 7179)","22년 동부 변전정비 총액공사","곤지암:7179(보통)","2022-04-13 09:30","2022-04-13 18:00","2022-04-13 09:30","2022-04-13 18:00","연속"]
[80,"경기","동부","곤지암동서울#1 T/L","22년 동부 변전정비 총액공사","곤지암:#73Bay B/F 보호반대체(~15)","2022-04-25 09:30","2022-04-29 18:00","2022-04-25 09:30","2022-04-29 18:00","연속"]
[81,"경기","동부","곤지암S/S #2 M.Tr","22년 동부 변전정비 총액공사","곤지암:#2M.Tr 보호반대체(~15)","2022-04-25 09:30","2022-04-29 18:00","2022-04-25 09:30","2022-04-29 18:00","연속"]
[82,"경기","성남","신수원S/S #3 M.Tr","22년 성남전력지사 변전정비회사 총액공사","- C상 하자점검 - 2차 GIS 조작시험 - CVT 초기점검 - 1,2차 LA 대체","2022-04-28 09:00","2022-04-28 18:00","2022-04-28 09:00","2022-04-28 18:00","연속"]
[83,"경기","성남","신성남S/S CB 7500","22년 성남전력지사 변전정비회사 총액공사","7502DS 가스 누기보수(7500CB 휴전)","2022-04-08 09:00","2022-04-08 18:00","2022-04-08 09:00","2022-04-08 18:00","연속"]
[84,"경기","성남","신안성신용인#2 T/L","345kV 신안성-신용인T/L OPGW 증설공사","345kV 신안성-신용인T/L OPGW 증설공사","2022-04-11 07:00","2022-05-10 18:00","취소","취소","연속"]
[85,"경기","성남","신안성신성남#2 T/L","345kV 신안성-신용인T/L OPGW 증설공사","345kV 신안성-신용인T/L OPGW 증설공사","2022-04-11 07:00","2022-05-08 18:00","취소","취소","연속"]
[86,"경기","직할","화성S/S CB 7772","345kV 화성S/S GIS 용량대체공사","77Bay 7772CB 철거 및 B/F반 교체","2022-04-19 08:00","2022-05-10 18:00","2022-04-19 08:00","2022-05-10 18:00","연속"]
[87,"경기","직할","화성평택TP#1 T/L","345kV 화성S/S GIS 용량대체공사","화성평택TP#1TL 77Bay 7772CB 철거(B/F반 교체)","2022-04-19 08:00","2022-05-10 18:00","2022-04-19 08:00","2022-05-10 18:00","연속"]
[88,"경기","평택","서안성신진천#1 T/L","세종-포천간 도로개설 관련 지장이설 철탑부재 측정","54호 1기 승탑 및 부재측정","2022-04-20 07:00","2022-04-20 18:00","2022-04-20 07:00","2022-04-20 18:00","연속"]
[89,"경기","평택","서안성S/S #4 M.Tr","22년 평택전력지사 변전협력회사 총액공사","서안성S/S #4M.Tr 보통점검, 부싱 절연유 채유 및 1,2차 GIS 보통점검","2022-04-05 10:00","2022-04-06 18:00","2022-04-05 10:00","2022-04-06 18:00","연속"]
[90,"경기","평택","서안성S/S #2 BUS","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사 - 345kV 고덕#2-서안성 #1,2T/L용 GIS 증설공사","2022-04-11 09:00","2022-04-22 18:00","2022-04-11 09:00","2022-04-22 18:00","연속"]
[91,"경기","평택","서안성S/S #1 BUS","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사 - 345kV 고덕#2-서안성 #1,2T/L용 GIS 증설공사","2022-04-25 09:00","2022-05-13 18:00","2022-04-25 09:00","2022-05-13 18:00","연속"]
[92,"경기","평택","서안성S/S #2 M.Tr","서안성S/S #2M.Tr 인출 7322DS 가스누기 보수","서안성S/S #2M.Tr 인출 7322DS 가스누기 보수","2022-04-04 10:00","2022-04-04 18:00","2022-04-04 10:00","2022-04-04 18:00","연속"]
[93,"강원","강릉","안인개폐소강릉TP#2 T/L","2022-23 변전협력회사 총액공사","362kV GIS 초기점검","2022-04-26 10:00","2022-04-27 18:00","2022-04-26 10:00","2022-04-27 18:00","매일"]
[94,"강원","강릉","안인개폐소강릉TP#1 T/L","2022-23 변전협력회사 총액공사","362kV GIS 초기점검","2022-04-19 10:00","2022-04-20 18:00","2022-04-19 10:00","2022-04-20 18:00","매일"]
[95,"강원","강릉","안인개폐소양양PP T/L","2022-23 변전협력회사 총액공사","362kV GIS 초기점검","2022-04-13 10:00","2022-04-13 18:00","2022-04-13 10:00","2022-04-13 18:00","연속"]
[96,"강원","강릉","안인개폐소신양양 T/L","2022-23 변전협력회사 총액공사","362kV GIS 초기점검","2022-04-14 10:00","2022-04-14 18:00","2022-04-14 10:00","2022-04-14 18:00","연속"]
[97,"강원","동해","동해안인개폐소#1 T/L","22~23년 동해전력지사 변전정비 총액공사","1.SPS 설치 2. CVT 대체 3. LA 대체 4. 차단기 조작시험 [7471,7400]","2022-04-04 09:00","2022-04-06 14:00","2022-04-04 09:00","2022-04-06 14:00","연속"]
[98,"강원","동해","신제천동해#2 T/L","22~23년 동해전력지사 변전정비 총액공사","1.CVT 대체 2. LA 대체 3. 차단기 조작시험[7271,7200]","2022-04-21 09:00","2022-04-22 18:00","2022-04-21 09:00","2022-04-22 18:00","연속"]
[99,"강원","동해","신제천동해#1 T/L","22~23년 동해전력지사 변전정비 총액공사","1.CVT 대체 2. LA 대체 3. 차단기 조작시험[7171,7100]","2022-04-19 09:00","2022-04-20 18:00","2022-04-19 09:00","2022-04-20 18:00","연속"]
[100,"강원","동해","동해안인개폐소#2 T/L","22~23년 동해전력지사 변전정비 총액공사","1.SPS 설치 2. CVT 대체 3. LA 대체 4. 차단기 조작시험 [7371.7300]","2022-04-06 14:00","2022-04-08 18:00","2022-04-06 14:00","2022-04-08 18:00","연속"]
[101,"강원","동해","삼척GP한울NP#1 T/L","2022-23년 동해전력지사 송전협력회사 총액공사","점퍼지지애자 설치","2022-04-11 08:00","2022-04-14 18:00","2022-04-11 08:00","2022-04-14 18:00","연속"]
[102,"강원","동해","삼척GP한울NP#2 T/L","2022-23년 동해전력지사 송전협력회사 총액공사","점퍼지지애자 설치","2022-04-15 08:00","2022-04-19 18:00","2022-04-15 08:00","2022-04-19 18:00","연속"]
[103,"강원","태백","신태백S/S #3 Sh.R (CB 7579)","2022년 765kV 신태백S/S 345kV #3Sh.R GIS 정밀점검","2022년 765kV 신태백S/S 345kV #3Sh.R GIS 정밀점검","2022-04-04 09:00","2022-04-15 18:00","2022-04-04 09:00","2022-04-15 18:00","연속"]
[104,"강원","태백","신태백S/S CB 7500","2022년 765kV 신태백S/S 345kV #3Sh.R GIS 정밀점검","2022년 765kV 신태백S/S 345kV #3Sh.R GIS 정밀점검","2022-04-04 09:00","2022-04-15 18:00","2022-04-04 09:00","2022-04-15 18:00","연속"]
[105,"강원","태백","신태백S/S CB 7571","2022년 765kV 신태백S/S 345kV #3Sh.R GIS 정밀점검","2022년 765kV 신태백S/S 345kV #3Sh.R GIS 정밀점검","2022-04-04 09:00","2022-04-15 18:00","2022-04-04 09:00","2022-04-15 18:00","연속"]
[106,"충북","직할","신진천S/S #2 M.Tr","`22-23년 충북직할 변전협력회사 총액공사","신진천S/S 345kV #2M.Tr 3차측 지지애자 교체","2022-04-25 10:00","2022-04-26 18:00","2022-04-25 10:00","2022-04-26 18:00","연속"]
[107,"충북","직할","신진천S/S #1 M.Tr","`22-23년 충북직할 변전협력회사 총액공사","신진천S/S 345kV #1M.Tr 3차측 지지애자 교체","2022-04-18 10:00","2022-04-19 18:00","2022-04-18 10:00","2022-04-19 18:00","연속"]
[108,"충북","직할","신중부신진천#1 T/L","'22-23년 충북 직할 변전협력회사 총액공사","신중부-신진천#1T/L CVT 대체","2022-04-06 10:00","2022-04-07 18:00","2022-04-06 10:00","2022-04-07 18:00","연속"]
[109,"충북","직할","신중부신진천#2 T/L","'22-23년 충북 직할 변전협력회사 총액공사","신중부-신진천#2T/L CVT, LA 대체","2022-04-04 10:00","2022-04-05 18:00","2022-04-04 10:00","2022-04-05 18:00","연속"]
[110,"충북","직할","서안성신진천#1 T/L","NO.3,4 안전이격확보공사","345kV 서안성-신진천#1T/L 항공도장 및 환경친화도장 시행","2022-04-14 08:00","2022-04-15 18:00","취소","취소","매일"]
[111,"충북","직할","서안성신진천#2 T/L","NO.3,4 안전이격확보공사","345kV 서안성-신진천#2T/L 항공도장 및 환경친화도장 시행","2022-04-12 08:00","2022-04-13 18:00","취소","취소","매일"]
[112,"충북","직할","신진천S/S #5 M.Tr","신진천S/S 종합예방진단시스템 구축","신제천S/S 종합예방진단시스템 구축공사 -부싱 시험탭 분리 및 규격 실측 -OLTC센서 설치가능여부 확인 및 센서부 실측","2022-04-28 10:00","2022-04-28 14:00","2022-04-28 10:00","2022-04-28 14:00","연속"]
[113,"충북","직할","신진천S/S #3 M.Tr","신진천S/S 종합예방진단시스템 구축","신제천S/S 종합예방진단시스템 구축공사 -부싱 시험탭 분리 및 규격 실측 -OLTC센서 설치가능여부 확인 및 센서부 실측","2022-04-27 10:00","2022-04-27 14:00","2022-04-27 10:00","2022-04-27 14:00","연속"]
[114,"충북","직할","신진천S/S #4 M.Tr","신진천S/S 종합예방진단시스템 구축","신제천S/S 종합예방진단시스템 구축공사 -부싱 시험탭 분리 및 규격 실측 -OLTC센서 설치가능여부 확인 및 센서부 실측","2022-04-27 14:00","2022-04-27 18:00","2022-04-27 14:00","2022-04-27 18:00","연속"]
[115,"충북","청주","남청주S/S #2 M.Tr","345kV 변압기 보통점검","[22-23 청주전력 변전정비 총액공사] 345kV #2M.Tr 보통점검","2022-04-04 10:00","2022-04-05 18:00","2022-04-04 10:00","2022-04-05 18:00","연속"]
[116,"충북","충주","신제천S/S SVC (CB 7271, 7200)","신제천S/S SVC 변압기 방열기 접합부 누유조치","신제천S/S SVC 변압기 방열기 접합부 누유조치","2022-04-18 09:00","2022-04-20 18:00","2022-04-18 09:00","2022-04-20 18:00","연속"]
[117,"충북","충주","신제천S/S #2 M.Tr","2022년 충주전력지사 345kV 주변압기 및 OLTC 정밀점검 공사","#2M.Tr 정밀점검","2022-04-18 09:00","2022-04-29 18:00","2022-04-18 09:00","2022-04-29 18:00","연속"]
[118,"충북","충주","신충주S/S STATCOM (CB 7071, 7000)","충주전력지사 변전소 소방시설 점검용역","신충주S/S STATCOM 제어동 소방설비 작동점검","2022-04-07 09:30","2022-04-07 18:00","2022-04-07 09:30","2022-04-07 18:00","연속"]
[119,"대전세종충남","대전","신계룡S/S #2 M.Tr","신계룡S/S #2M.Tr 보통점검 및 병행작업","신계룡S/S #2M.Tr 보통점검 및 병행작업","2022-04-18 09:00","2022-04-20 18:00","2022-04-18 09:00","2022-04-20 18:00","연속"]
[120,"대전세종충남","대전","신계룡S/S #1 M.Tr","신계룡S/S #1M.Tr 보통점검 및 병행작업","신계룡S/S #1M.Tr 보통점검 및 병행작업","2022-04-11 09:00","2022-04-13 18:00","2022-04-11 09:00","2022-04-13 18:00","연속"]
[121,"대전세종충남","대전","신계룡S/S #3 M.Tr","신계룡S/S #3M.Tr 보통점검 및 병행작업","신계룡S/S #3M.Tr 보통점검 및 병행작업","2022-04-25 09:00","2022-04-28 18:00","취소","취소","연속"]
[122,"대전세종충남","서산","당진T/P #71 Tie-Tr","당진화력S/S 345kV #71TIE-Tr 1차 LA, CVT 대체","당진화력S/S 345kV #71TIE-Tr 1차 LA, CVT 대체","2022-04-11 10:00","2022-04-15 18:00","취소","취소","연속"]
[123,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","신당진개폐소 345kV 개폐소-태안화력#2T/L 가스누기 보수공사","신당진개폐소 345kV 개폐소-태안화력#2T/L 가스누기 보수공사 - (병행) LA 보통점검, CVT 하자점검","2022-04-11 09:00","2022-04-15 18:00","2022-04-25 09:00","2022-04-29 18:00","연속"]
[124,"대전세종충남","서산","신당진S/S SEC CB 75760","22년도 장기 미동작 차단기 조작시험","신당진S/S 345kV #75-#76 SEC 75-76-0 CB 조작시험","2022-04-13 10:00","2022-04-13 14:00","2022-04-13 10:00","2022-04-13 14:00","연속"]
[125,"대전세종충남","서산","신당진S/S CB 7471","22년도 장기 미동작 차단기 조작시험","신당진S/S 345kV 신당진연락#1T/L 7471CB 조작시험","2022-04-13 14:00","2022-04-13 18:00","취소","취소","연속"]
[126,"대전세종충남","서산","신당진S/S #1 M.Tr","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -#1M.Tr 2차 교체","2022-04-11 08:00","2022-04-29 18:00","2022-04-11 08:00","2022-04-29 18:00","연속"]
[127,"대전세종충남","서산","신서산태안TP#2 T/L","345kV 신서산-태안화력#2T/L 송전선로보호반 대체공사","345kV 신서산-태안화력#2T/L 송전선로보호반 대체공사","2022-04-04 09:00","2022-04-08 18:00","2022-04-04 09:00","2022-04-08 18:00","연속"]
[128,"대전세종충남","서산","태안T/P #1 Tie-Tr","태안T/P 345kV #1M.Tr 1차 PT측 스페이서 교체","태안T/P 345kV #1M.Tr 1차 PT측 스페이서 교체","2022-04-18 10:00","2022-04-22 18:00","2022-04-18 10:00","2022-04-22 18:00","연속"]
[129,"대전세종충남","천안","신온양S/S CB 7900","신온양S/S 345kV 7800, 7900GIS 보통점검","신온양S/S 345kV 7800, 7900GIS 보통점검","2022-04-25 14:00","2022-04-25 18:00","취소","취소","연속"]
[130,"대전세종충남","천안","신온양S/S #3 M.Tr","신온양S/S #3M.Tr 보통점검 및 예비상 1차부싱 복구작업","신온양S/S #3M.Tr 보통점검 및 예비상 1차부싱 복구작업","2022-04-04 09:00","2022-04-08 18:00","2022-04-04 09:00","2022-04-08 18:00","연속"]
[131,"대전세종충남","천안","신온양S/S 예비 M.Tr CB","신온양S/S #3M.Tr 보통점검 및 예비상 1차부싱 복구작업","신온양S/S #3M.Tr 보통점검 및 예비상 1차부싱 복구작업","2022-04-04 09:00","2022-04-08 18:00","취소","취소","연속"]
[132,"대전세종충남","천안","신온양S/S CB 7800","신온양S/S 345kV 7800, 7900GIS 보통점검","신온양S/S 345kV 7800, 7900GIS 보통점검","2022-04-25 09:00","2022-04-25 14:00","취소","취소","연속"]
[133,"대전세종충남","천안","신온양S/S #2BUS","신온양S/S 345kV #2BUS 모선보호반 대체","신온양S/S 345kV #2BUS 모선보호반 대체","2022-04-12 09:00","2022-04-15 18:00","2022-04-12 09:00","2022-04-15 18:00","연속"]
[134,"대전세종충남","천안","신탕정S/S #4 M.Tr","신탕정S/S 345kV #4M.Tr 하자관련 보수작업","신탕정S/S 345kV #4M.Tr 하자관련 보수작업","2022-04-18 09:00","2022-04-22 18:00","2022-04-18 09:00","2022-04-22 18:00","연속"]
[135,"대전세종충남","천안","아산보령TP#1 T/L","345kV 아산S/S 취약설비 보강 및 배전반 정비공사","- 모자익배전반 철거 * 1식 - 집중감시제어반+디지탈축소형모자익배전반 설치 *1식","2022-04-01 09:00","2022-04-18 18:00","2022-04-01 09:00","2022-04-18 18:00","연속"]
[136,"대전세종충남","천안","아산S/S #1 M.Tr","아산S/S 345kV #1 M.Tr 보통점검 및 부싱절연유 채유","아산S/S 345kV #1 M.Tr 보통점검 및 부싱절연유 채유","2022-04-11 09:00","2022-04-12 18:00","2022-04-11 09:00","2022-04-12 18:00","연속"]
[137,"대전세종충남","청양","청양군산#2 T/L","청양S/S 73BAY B/F PNL 대체","청양S/S 73BAY B/F PNL 대체","2022-04-25 09:00","2022-05-06 18:00","취소","취소","연속"]
[138,"대전세종충남","청양","청양신보령TP T/L","청양S/S 345kV #72BayB/F PNL 교체공사","청양S/S 345kV #72BayB/F PNL 교체공사","2022-04-18 09:00","2022-04-22 18:00","취소","취소","연속"]
[139,"대전세종충남","청양","청양보령CC T/L","청양S/S 345kV #72BayB/F PNL 교체공사","청양S/S 345kV #72BayB/F PNL 교체공사","2022-04-18 09:00","2022-04-22 18:00","취소","취소","연속"]
[140,"대전세종충남","청양","청양신탕정#1 T/L","청양S/S 73BAY B/F PNL 및 청양-신탕정#1T/L 보호반 대체","청양S/S 73BAY B/F PNL 및 청양-신탕정#1T/L 보호반 대체","2022-04-25 09:00","2022-05-06 18:00","취소","취소","연속"]
[141,"전북","군산","군산S/S #2 M.Tr","군산S/S 장기사용 170kV GIS 대체공사2 (시험가압)","- 장기사용 GIS 대체","2022-04-20 18:00","2022-04-22 18:00","취소","취소","연속"]
[142,"전북","군산","군산S/S #1 M.Tr","군산S/S 장기사용 170kV GIS 대체공사1 (시험가압)","- 장기사용 GIS 대체 시험가압 선로","2022-04-20 18:00","2022-04-22 18:00","취소","취소","연속"]
[143,"전북","김제","신김제S/S CB 7872","김제PO 154kV이상 차단기 조작시험","차단기 개폐시험","2022-04-29 10:00","2022-04-29 18:00","취소","취소","연속"]
[144,"전북","김제","신김제S/S CB 7800","김제PO 154kV이상 차단기 조작시험","차단기 개폐시험","2022-04-29 10:00","2022-04-29 18:00","취소","취소","연속"]
[145,"전북","김제","신김제S/S CB 7600","김제PO 154kV이상 차단기 조작시험","차단기 개폐시험","2022-04-28 10:00","2022-04-28 18:00","취소","취소","연속"]
[146,"전북","김제","신김제S/S CB 7672","김제PO 154kV이상 차단기 조작시험","차단기 개폐시험","2022-04-28 10:00","2022-04-28 18:00","취소","취소","연속"]
[147,"전북","직할","신옥천신남원#2 T/L","345kV 신옥천-신남원T/L 노후취약 지지물 교체공사","□ 공사내용 ○ 철탑교체 : No.152 (Ba-32m → Bas-42m, 인클로징 공법) ○ 전 력 선 : HSTACIR/AW 410㎟ x 2B x 2C [No.151∼153, 1.021C-㎞] ○ 가공지선 : AWS 100㎟ x S x 1C [No.151∼153, 1.021㎞] ○ 애자련 교체 및 기타 부대설비 공사","2022-04-30 09:00","2022-05-08 18:00","취소","취소","연속"]
[148,"전북","직할","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L 노후취약 지지물 교체공사","□ 공사내용 ○ 철탑교체 : No.152 (Ba-32m → Bas-42m, 인클로징 공법) ○ 전 력 선 : HSTACIR/AW 410㎟ x 2B x 2C [No.151∼153, 1.021C-㎞] ○ 가공지선 : AWS 100㎟ x S x 1C [No.151∼153, 1.021㎞] ○ 애자련 교체 및 기타 부대설비 공사","2022-04-22 09:00","2022-04-29 18:00","취소","취소","연속"]
[149,"광주전남","광주","신화순S/S #1 Sh.R CB","22~23년 광주전력지사 변전협력회사 총액공사","22~23년 광주전력지사 변전협력회사 총액공사 - #1Sh.R 초기점검 - 7679, 7600, 7672 초기점검","2022-04-05 09:00","2022-04-07 18:00","취소","취소","연속"]
[150,"광주전남","광주","신화순S/S CB 7600","22~23년 광주전력지사 변전협력회사 총액공사","22~23년 광주전력지사 변전협력회사 총액공사 - #1Sh.R 초기점검 - 7679, 7600, 7672 초기점검","2022-04-05 09:00","2022-04-07 18:00","2022-04-05 09:00","2022-04-07 18:00","연속"]
[151,"광주전남","광주","신화순S/S #1 Sh.R (CB 7679)","22~23년 광주전력지사 변전협력회사 총액공사","22~23년 광주전력지사 변전협력회사 총액공사 - #1Sh.R 초기점검 - 7679, 7600, 7672 초기점검","2022-04-05 09:00","2022-04-07 18:00","2022-04-05 09:00","2022-04-07 18:00","연속"]
[152,"광주전남","광주","신화순S/S CB 7672","22~23년 광주전력지사 변전협력회사 총액공사","22~23년 광주전력지사 변전협력회사 총액공사 - #1Sh.R 초기점검 - 7679, 7600, 7672 초기점검","2022-04-05 09:00","2022-04-07 18:00","2022-04-05 09:00","2022-04-07 18:00","연속"]
[153,"광주전남","광주","신화순S/S CB 7800","22~23년 광주전력지사 변전협력회사 총액공사(신화순SS 7800CB)","22~23년 광주전력지사 변전협력회사 총액공사(신화순SS 7800CB) - 조작시험","2022-04-08 09:00","2022-04-08 13:00","2022-04-08 09:00","2022-04-08 13:00","연속"]
[154,"광주전남","광주","신화순S/S CB 7971","22~23년 광주전력지사 변전협력회사 총액공사(신화순SS 7971CB)","22~23년 광주전력지사 변전협력회사 총액공사(신화순SS 7971CB) - 조작시험","2022-04-08 13:00","2022-04-08 18:00","2022-04-08 13:00","2022-04-08 18:00","연속"]
[155,"광주전남","광주","신화순S/S CB 7500","신화순S/S 345kV GIS 정밀점검","-7500 CB GIS 정밀점검 (즉시가압 불가)","2022-04-11 09:00","2022-04-14 18:00","취소","취소","연속"]
[156,"광주전남","광주","신화순S/S #3 M.Tr","신화순S/S 345kV GIS 정밀점검","-7500, 7572 CB GIS 정밀점검 (즉시가압 불가/ 주말에는 가압가능)","2022-04-11 09:00","2022-04-21 18:00","2022-04-11 09:00","2022-04-21 18:00","연속"]
[157,"광주전남","광주","신광주S/S CB 7100","22~23년 광주전력지사 변전협력회사 총액공사(신광주#1M.Tr TIE)","차단기 조작시험 단상 재폐로 회로 보완 및 시험","2022-04-15 09:00","2022-04-15 14:00","2022-04-15 09:00","2022-04-15 14:00","연속"]
[158,"광주전남","광주","신광주S/S CB 7171","22~23년 광주전력지사 변전협력회사 총액공사(신광주-한빛#1T/L)","차단기 조작시험 단상 재폐로 회로 보완 및 시험","2022-04-15 14:00","2022-04-15 18:00","2022-04-15 14:00","2022-04-15 18:00","연속"]
[159,"광주전남","광주","신광주신화순#1 T/L","21년 철탑 추락방지장치 설치공사","345kV 신광주-신화순T/L 수평 추락방지장치 설치","2022-04-18 07:00","2022-04-22 18:00","취소","취소","매일"]
[160,"광주전남","광주","신화순신강진#1 T/L","22~23년 광주 변전협력회사 총액공사","362kV GIS 차단기 조작시험 및 전자변교체(7A00, 7A71) -비상시 즉시가압 불가-","2022-04-18 09:00","2022-04-18 18:00","2022-04-18 09:00","2022-04-18 18:00","연속"]
[161,"광주전남","광주","신화순S/S CB 7572","신화순S/S 345kV GIS 정밀점검","-7572 CB GIS 정밀점검 (즉시가압 불가)","2022-04-18 09:00","2022-04-21 18:00","취소","취소","연속"]
[162,"광주전남","광주","신남원신광주#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","신광주S/S 362kV GIS 차단기 조작시험 및 전자변교체(7300, 7371) -비상시 즉시가압 불가-","2022-04-19 09:00","2022-04-19 18:00","2022-04-19 09:00","2022-04-19 18:00","연속"]
[163,"광주전남","광주","신광주S/S #70 BUS","22년 광주변전총액(1BUS 모선보호반 교체)","345kV #1BUS PRO 보호반 교체(즉시가압 불가능)","2022-04-21 09:00","2022-04-25 18:00","취소","취소","연속"]
[164,"광주전남","광주","신광주신화순#2 T/L","21년 철탑 추락방지장치 설치공사","345kV 신광주-신화순T/L 수평 추락방지장치 설치","2022-04-25 07:00","2022-04-29 18:00","취소","취소","매일"]
[165,"광주전남","광주","신화순신강진#2 T/L","신화순S/S 345kV GIS 정밀점검","-7971 CB GIS 정밀점검 (즉시가압 불가)","2022-04-25 09:00","2022-04-27 18:00","2022-04-25 09:00","2022-04-27 18:00","연속"]
[166,"광주전남","순천","여수T/P CB 7300","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y #3M.Tr, 2차 GIS 보통점검 및 1차 CB 타임측정 여수화력S/Y 7300 CB 타임측정","2022-04-25 09:00","2022-04-26 18:00","취소","취소","연속"]
[167,"광주전남","순천","여수T/P CB 7372","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y #3M.Tr, 2차 GIS 보통점검 및 1차 CB 타임측정 여수화력S/Y 7300 CB 타임측정","2022-04-25 09:00","2022-04-26 18:00","취소","취소","연속"]
[168,"광주전남","광주","신광주S/S #75 BUS","22년 광주변전총액(2BUS 모선보호반 교체)","345kV #2BUS PRO 보호반 교체(즉시가압 불가능)","2022-04-28 09:00","2022-05-01 18:00","취소","취소","연속"]
[169,"광주전남","광주","신광주신화순#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","신광주S/S 362kV 차단기 조작시험 및 전자변교체(7871) -비상시 즉시가압 불가-","2022-04-28 09:00","2022-04-29 18:00","취소","취소","연속"]
[170,"대구","달성","고령S/S #1 M.Tr","#1M.Tr Bay 하자점검","#1M.Tr Bay 하자점검","2022-04-25 09:00","2022-04-28 18:00","2022-04-25 09:00","2022-04-28 18:00","연속"]
[171,"대구","달성","대구S/S #3 M.Tr","대구S/S #3M.Tr 누유개소 보수","대구S/S #3M.Tr 누유개소 보수","2022-04-19 09:00","2022-04-19 18:00","2022-04-19 09:00","2022-04-19 18:00","연속"]
[172,"대구","달성","북경남대구#2 T/L","345kV 북경남-대구T/L 안전이격거리 확보공사","345kV 북경남-대구T/L 안전이격거리 확보공사 본선로 구성","2022-04-01 07:00","2022-04-14 18:00","2022-03-28 07:00","2022-04-06 18:00","연속"]
[173,"대구","칠곡","북대구선산 T/L","북대구S/S 북대구-선산T/L 7200, 7272 GIS 보통점검","북대구S/S 북대구-선산T/L 7200, 7272 GIS 보통점검","2022-04-15 09:30","2022-04-15 18:00","2022-04-15 09:30","2022-04-15 18:00","연속"]
[174,"대구","칠곡","신포항북대구 T/L","북대구S/S 신포항-북대구T/L 7171, 7100 GIS 보통점검","북대구S/S 신포항-북대구T/L 7171, 7100 GIS 보통점검","2022-04-18 09:30","2022-04-18 18:00","2022-04-18 09:30","2022-04-18 18:00","연속"]
[175,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S #2M.Tr 보통점검","북대구S/S #2M.Tr 보통점검","2022-04-22 09:30","2022-04-22 18:00","2022-04-22 09:30","2022-04-22 18:00","연속"]
[176,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S #3M.Tr 1,2차 LA 보통점검","서대구S/S #3M.Tr 1,2차 LA 보통점검","2022-04-26 09:30","2022-04-26 18:00","2022-04-26 09:30","2022-04-26 18:00","연속"]
[177,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S #1M.Tr 1차 PT 보통점검, GCB 장기미동작점검","서대구S/S #1M.Tr 1차 PT 보통점검, GCB 장기미동작점검","2022-04-27 09:30","2022-04-27 18:00","2022-04-27 09:30","2022-04-27 18:00","연속"]
[178,"대구","포항","신포항청송PP T/L","신포항S/S 신포항-청송TL LA,PT 보통점검","신포항S/S 신포항-청송TL LA,PT 보통점검","2022-04-26 09:00","2022-04-26 18:00","취소","취소","연속"]
[179,"대구","포항","신포항S/S #1 M.Tr","신포항SS #1M.Tr 보통점검,1차LA,PT,2차LA 보통점검","신포항SS #1M.Tr 보통점검,1차LA,PT,2차LA 보통점검","2022-04-19 09:00","2022-04-20 18:00","2022-04-19 09:00","2022-04-20 18:00","연속"]
[180,"경북","구미","선산S/S #70 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","77bay 교체(모선)","2022-04-26 09:00","2022-05-03 18:00","2022-04-26 09:00","2022-05-03 18:00","연속"]
[181,"경북","직할","신영주안동CC T/L","22~23년 경북본부 직할 변전정비회사 총액공사","7200, 7271 GIS 보통점검","2022-04-26 09:00","2022-04-26 18:00","취소","취소","연속"]
[182,"경북","직할","신영일안동CC T/L","22~23년 경북본부 직할 변전정비회사 총액공사","7300, 7371 GIS 보통점검","2022-04-25 09:00","2022-04-25 18:00","2022-04-25 09:00","2022-04-25 18:00","연속"]
[183,"경북","직할","신포항청송PP T/L","22~23년 경북본부 직할 변전정비회사 총액공사","7200 7271 GIS 보통점검, 7291, 7221 보조계전기 교체","2022-04-27 09:00","2022-04-29 18:00","2022-04-27 09:00","2022-04-29 18:00","매일"]
[184,"부산울산","동부산","고리1NP고리2NP #1T/L","고리NP S/Y 7077CB 정밀점검 및 시험가압","고리NP S/Y 7077CB 정밀점검 및 시험가압","2022-04-04 09:00","2022-04-11 18:00","2022-04-04 09:00","2022-04-15 18:00","연속"]
[185,"부산울산","동부산","고리1NP고리2NP #2T/L","고리NP S/Y 7577CB 정밀점검 및 시험가압","고리NP S/Y 7577CB 정밀점검 및 시험가압","2022-04-12 09:00","2022-04-19 18:00","2022-04-18 09:00","2022-04-29 18:00","연속"]
[186,"부산울산","동부산","신양산신대연#1 T/L","345kV 신양산-신대연 등 7개T/L 자기애관 교체공사","345kV 신고리-고리NP 자기애관 교체공사 자기애관2,500㎟을 폴리머애관 2,500㎟으로 변경","2022-04-18 08:00","2022-04-29 18:00","2022-04-18 08:00","2022-04-29 18:00","연속"]
[187,"부산울산","동부산","신양산북부산#2 T/L","신양산S/S 345kV 용량부족 차단기 교체공사","신양산 345kV 용량부족 차단기 교체공사 1차 - 73BAY GIS 교체(7371,7300,7372)","2022-04-25 09:00","2022-06-24 18:00","2022-04-25 09:00","2022-06-24 18:00","연속"]
[188,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S 345kV 용량부족 차단기 교체공사","신양산 345kV 용량부족 차단기 교체공사 1차 - 73BAY GIS 교체(7371,7300,7372)","2022-04-25 09:00","2022-06-24 18:00","2022-04-25 09:00","2022-06-24 18:00","연속"]
[189,"부산울산","동부산","신양산S/S #3 M.Tr","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드, 유압누유 발청조치","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드, 유압누유 발청조치","2022-04-11 09:00","2022-04-11 18:00","2022-04-11 09:00","2022-04-14 18:00","연속"]
[190,"부산울산","동부산","신양산S/S #1 M.Tr","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드, 유압누유 발청조치","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드, 유압누유 발청조치","2022-04-04 09:00","2022-04-04 14:00","2022-04-04 09:00","2022-04-04 14:00","연속"]
[191,"부산울산","동부산","신양산북부산#1 T/L","신양산S/S 자동재투입용 7400,7471 GIS 결상회로 보완","신양산S/S 자동재투입용 7400,7471 GIS 결상회로 보완","2022-04-05 09:30","2022-04-05 17:00","취소","취소","연속"]
[192,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산T/L 81~84호간 지장철탑 이설공사","본선로 구성작업 연긴선 (#2TL)","2022-04-05 08:00","2022-04-15 18:00","2022-04-05 08:00","2022-04-15 18:00","연속"]
[193,"부산울산","북부산","신김해북부산#2 T/L","북부산S/S 345kV M.Tr 3차측 현대화공사","북부산S/S 345kV M.Tr 3차측 현대화공사 #1Bank 시험가압선로(24H)","2022-04-28 18:00","2022-04-29 18:00","취소","취소","연속"]
[194,"부산울산","서부산","신김해신녹산#1 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 : 23~52호(22기)","2022-04-26 07:00","2022-05-02 18:00","2022-04-26 07:00","2022-05-02 18:00","연속"]
[195,"부산울산","서부산","신녹산S/S #2 M.Tr","신녹산S/S #2M.Tr 누유조치작업","신녹산S/S #2M.Tr 누유조치작업","2022-04-06 09:00","2022-04-07 18:00","2022-04-06 09:00","2022-04-07 18:00","연속"]
[196,"부산울산","서부산","신녹산S/S CB 7271","신녹산S/S 345kV 신김해-신녹산#1T/L CB Air 누기보수작업","신녹산S/S 345kV 신김해-신녹산#1T/L 7271 CB Air 누기보수작업","2022-04-01 09:00","2022-04-01 18:00","취소","취소","연속"]
[197,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","74BAY #2BUS 교체 및 7471, 7400, 7472 GIS 교체","2022-04-28 09:00","2022-06-03 15:00","취소","취소","연속"]
[198,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","#2BUS 시험가압 - 상체크 및 사용전검사","2022-04-26 09:30","2022-04-26 15:00","취소","취소","연속"]
[199,"부산울산","울산","신온산S/S #1 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","#1BUS 시험가압 - 상체크","2022-04-26 09:00","2022-04-26 09:30","취소","취소","연속"]
[200,"부산울산","울산","신온산남울산#1 T/L","345kV 신온산S/S 용량부족 차단기 대체공사","74BAY 7471, 7400, 7472 GIS 교체","2022-04-28 09:00","2022-07-15 15:00","취소","취소","연속"]
[201,"부산울산","울산","신온산S/S #3 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","74BAY 7471, 7400, 7472 GIS 교체 관련 안전이격거리 확보","2022-04-28 09:00","2022-06-03 15:00","취소","취소","연속"]
[202,"부산울산","울산","신온산S/S #2 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","74BAY 7471, 7400, 7472 GIS 교체","2022-04-28 09:00","2022-07-15 15:00","취소","취소","연속"]
[203,"부산울산","울산","신온산신울산#1 T/L","345kV 신온산S/S 용량부족 차단기 대체공사","#1BUS 시험가압","2022-04-12 15:00","2022-04-13 15:00","2022-04-28 15:00","2022-04-29 15:00","연속"]
[204,"부산울산","울산","신울산S/S #2 M.Tr","신울산S/S 345kV 차단기 용량대체공사","○ 345kV GIS 대체 관련 변압기 접속지점 변경(구 73BAY → 신 73BAY) ○ 345kV GIS 대체 관련 보호배전반 이설 및 연동시험","2022-04-11 09:00","2022-06-17 18:00","2022-04-11 09:00","2022-06-17 18:00","연속"]
[205,"경남","직할","신김해S/S #3 M.Tr","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-04-11 08:00","2022-04-15 17:30","2022-04-11 08:00","2022-04-15 19:00","연속"]
[206,"경남","직할","신김해S/S #2 M.Tr","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-04-04 08:00","2022-04-08 17:30","2022-04-04 08:00","2022-04-08 17:30","연속"]
[207,"경남","직할","신김해신녹산#1 T/L","2022년 경남 직할 345kV GIS 정밀점검 공사","2022년 경남 직할 345kV GIS 정밀점검 공사 신김해-신녹산#1T/L GIS(7771)","2022-04-25 08:00","2022-04-29 18:00","취소","취소","연속"]
[208,"경남","직할","신김해S/S #5 M.Tr","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-04-18 08:00","2022-04-22 17:30","2022-04-18 08:00","2022-04-22 17:30","연속"]
[209,"경남","진주","의령S/S #2 M.Tr","의령S/S #2M.Tr 보통점검","의령S/S #2M.Tr 보통점검 [병행]#2M.Tr 변전부속설비 점검(3차 PT, 1,3차 LA) [병행]2차 LA 대체 및 2,3차 CB 조작시험(6244,4279,427-1,2,4284)","2022-04-27 09:00","2022-04-28 18:00","2022-04-27 09:00","2022-04-28 18:00","연속"]
[210,"경남","진주","하동T/P SEC CB 70710","하동T/P 70-71-0, 75-76-0 GIS 조작시험","하동T/P 70-71-0, 75-76-0 GIS 조작시험","2022-04-06 09:00","2022-04-06 13:00","2022-04-06 09:00","2022-04-06 13:00","연속"]
[211,"경남","진주","하동T/P SEC CB 75760","하동T/P 70-71-0, 75-76-0 GIS 조작시험","하동T/P 70-71-0, 75-76-0 GIS 조작시험","2022-04-06 13:00","2022-04-06 16:00","2022-04-06 13:00","2022-04-06 16:00","연속"]
[212,"경남","진주","하동T/P CB 7700","하동T/P #77BAY 7700, 7772 GIS 조작시험","하동T/P #77BAY TIE(7700), M.Tr(7772) GIS 조작시험","2022-04-12 09:00","2022-04-12 13:00","취소","취소","연속"]
[213,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 철탑 추락방지시설 설치공사","○ 345kV 의령-하동화력#1T/L 철탑 추락방지시설 설치공사 - 수직 추락방지시설 설치 : No.2~134호 - 수평 추락방지시설 설치 : No.2~91호 (#1T/L 측)","2022-04-14 07:00","2022-04-25 18:00","2022-04-14 07:00","2022-04-25 18:00","연속"]
[214,"경남","진주","하동T/P CB 7872","하동T/P #78BAY 7800, 7872 GIS 조작시험","하동T/P #78BAY TIE(7800), M.Tr(7872) GIS 조작시험","2022-04-19 13:00","2022-04-19 16:00","2022-04-19 13:00","2022-04-19 16:00","연속"]
[215,"경남","진주","하동T/P CB 7772","하동T/P #77BAY 7700, 7772 GIS 조작시험","하동T/P #77BAY TIE(7700), M.Tr(7772) GIS 조작시험","2022-04-12 13:00","2022-04-12 16:00","취소","취소","연속"]
[216,"경남","진주","광양하동TP#1 T/L","하동T/P #73BAY 7371, 7300 GIS 조작시험","하동T/P #73BAY 7371, 7300 GIS 조작시험 [병행] 광양-하동TP #1T/L LA(ABC) 초기점검","2022-04-13 09:00","2022-04-13 17:00","2022-04-13 09:00","2022-04-13 17:00","연속"]
[217,"경남","진주","하동T/P CB 7800","하동T/P #78BAY 7800, 7872 GIS 조작시험","하동T/P #78BAY TIE(7800), M.Tr(7872) GIS 조작시험","2022-04-19 09:00","2022-04-19 13:00","2022-04-19 09:00","2022-04-19 13:00","연속"]
[218,"경남","통영","창원삼천포TP#2 T/L","SPS 차단조건 추가 공사","1. 창원-삼천포화력#2/TL 차단기 접점 제공 2. 창원-삼천포화력#2/TL Ry 동작신호 제공","2022-04-04 10:00","2022-04-08 18:00","2022-03-30 09:30","2022-03-31 18:00","연속"]
[219,"경남","통영","삼천포T/P #5호기 주변압기 (CB 7500, 7571)","신고성S/S 345kV #G5호기 CVT 보통점검","신고성S/S 345kV #G5호기 CVT 보통점검","2022-04-11 10:00","2022-04-11 18:00","2022-04-11 10:00","2022-04-11 18:00","연속"]
[220,"경남","통영","삼천포T/P #4호기 주변압기 (CB 7400, 7471)","신고성S/S 345kV #G4호기 CVT 보통점검","신고성S/S 345kV #G4호기 CVT 보통점검","2022-04-11 10:00","2022-04-11 18:00","2022-03-28 10:00","2022-03-28 18:00","연속"]
[221,"경남","통영","삼천포T/P #5호기 주변압기 (CB 7500, 7571)","신고성S/S 345kV #G5호기 CVT 보통점검","신고성S/S 345kV #G5호기 CVT 보통점검","2022-04-11 10:00","2022-04-11 18:00","취소","취소","연속"]
[222,"경남","통영","삼천포T/P #4호기 주변압기 (CB 7400, 7471)","신고성S/S 345kV #G4호기 CVT 보통점검","신고성S/S 345kV #G4호기 CVT 보통점검","2022-04-11 10:00","2022-04-11 18:00","취소","취소","연속"]
[223,"경남","함안","북경남S/S #6 Sh.R (CB 7979)","북경남S/S 345kV #6 Sh.R 7979 GIS 정밀점검","북경남S/S 345kV #6 Sh.R 7979 GIS 정밀점검","2022-04-11 09:00","2022-04-15 18:00","2022-04-11 09:00","2022-04-15 18:00","연속"]
[224,"경남","함안","북경남S/S #7 Sh.R (CB 7879)","북경남S/S 345kV #7 Sh.R 7879 GIS 정밀점검","북경남S/S 345kV #7 Sh.R 7879 GIS 정밀점검","2022-04-18 09:30","2022-04-22 18:00","2022-04-18 09:30","2022-04-22 18:00","연속"]
[225,"경남","함안","북경남고령#2 T/L","북경남S/S 345KV 북경남고령#2 T/L 보통점검","북경남S/S 345KV 북경남고령#2 T/L 보통점검(TIE,선로), 결상방지관련 회로 개선","2022-04-27 09:30","2022-04-28 17:30","2022-04-27 09:30","2022-04-28 17:30","연속"]
[226,"경남","함안","북경남서대구#2 T/L","북경남S/S 345KV 북경남서대구#2 T/L보통점검","북경남S/S 345KV 북경남서대구#2 T/L보통점검, 결상방지관련 회로 개선","2022-04-26 09:30","2022-04-26 17:30","2022-04-26 09:30","2022-04-26 17:30","연속"]
[227,"경남","함안","신마산S/S #5 M.Tr","신마산S/S 345kV M.Tr EBA 자기애관 교체공사","자기애관 -> 폴리머애관 교체","2022-04-04 08:00","2022-04-11 08:00","2022-04-04 08:00","2022-04-11 08:00","연속"]
[228,"대전세종충남",null,"청양신보령TP T/L","신보령T/P #72Bay GIS 정밀점검","신보령T/P #72Bay GIS 정밀점검","2022-04-04 09:00","2022-04-11 08:00","2022-04-04 09:00","2022-04-11 08:00","연속"]
[229,"경북",null,"한울1N/P #1호기 비상보조변압기 (CB 7300, 7372)","1호기 24차 계획예방정비 * 조작차단기 : CB 7300, 7372","○ 비상보조변압기 일반점검","2022-04-21 15:00","2022-04-28 15:00","2022-04-21 15:00","2022-04-28 15:00","연속"]
[230,"전북","김제","신김제S/S #4 M.Tr","김제PO 154kV이상 차단기 조작시험","차단기 개폐시험","2022-04-29 10:00","2022-04-29 18:00","2022-04-29 10:00","2022-04-29 18:00","연속"]
[231,"전북","김제","신김제S/S #3 M.Tr","김제PO 154kV이상 차단기 조작시험","차단기 개폐시험","2022-04-28 10:00","2022-04-28 18:00","2022-04-28 10:00","2022-04-28 18:00","연속"]
[232,"대전세종충남",null,"태안T/P #7호기 주변압기 (CB 7700, 7772)","전력용 변압기 정밀 절연진단","전력용 변압기 정밀 절연진단","2022-04-04 10:00","2022-06-13 10:00","2022-04-04 10:00","2022-06-13 10:00","연속"]
[233,"경남",null,"하동T/P #7호기 주변압기(7700,7772)","계획예방정비","계획예방정비","2022-04-06 14:00","2022-05-23 13:00","2022-04-06 14:00","2022-05-23 13:00","연속"]
[234,"강원",null,"양양P/P #3호기 주변압기(7200,7272)","계획중간정비","계획중간정비","2022-04-23 09:00","2022-04-23 18:00","2022-04-23 09:00","2022-04-23 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":628,"n_cols":11,"rows_kept":628,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","도봉방학#2 T/L","154㎸ 도봉(장암)S/S 옥내화 관련 지중T/L 건설공사","○도봉-방학#1,2T/L 철거(2C*0.63km) 신설(2C*0.57km)","2022-04-25 09:00","2022-06-15 18:00","2022-04-25 09:00","2022-06-15 18:00","연속"]
[2,"서울","성동","금오상계#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-04-07 14:00","2022-04-07 18:00","2022-04-07 14:00","2022-04-07 18:00","연속"]
[3,"서울","성동","금오상계#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-04-07 10:00","2022-04-07 14:00","2022-04-07 10:00","2022-04-07 14:00","연속"]
[4,"서울","성동","상봉휘경#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-04-06 09:30","2022-04-06 18:00","2022-04-06 09:30","2022-04-06 18:00","연속"]
[5,"서울","성동","상봉휘경#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-04-07 09:30","2022-04-07 18:00","2022-04-07 09:30","2022-04-07 18:00","연속"]
[6,"서울","성동","방학창동#1 T/L","2022년 성동P/O 154kV GIS 정밀점검공사","창동S/S 방학창동#1T/L GIS 정밀점검 공사","2022-04-27 09:30","2022-04-28 18:00","2022-04-27 09:30","2022-04-28 18:00","연속"]
[7,"서울","성동","창동돈암 T/L","2022년 성동P/O 154kV GIS 정밀점검공사","창동S/S 창동돈암T/L GIS 정밀점검 공사","2022-04-25 09:30","2022-04-26 18:00","2022-04-25 09:30","2022-04-26 18:00","연속"]
[8,"서울","성동","군자화양#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-04-18 13:00","2022-04-18 15:00","2022-04-18 13:00","2022-04-18 15:00","연속"]
[9,"서울","성동","화양성수 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-04-19 13:00","2022-04-19 15:00","2022-04-21 13:00","2022-04-21 15:00","연속"]
[10,"서울","성동","화양광장 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-04-20 09:30","2022-04-20 13:00","2022-04-20 09:30","2022-04-20 13:00","연속"]
[11,"서울","성동","미금화양 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-04-19 09:30","2022-04-19 13:00","2022-04-21 09:30","2022-04-21 13:00","연속"]
[12,"서울","성동","군자화양#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-04-18 09:30","2022-04-18 13:00","2022-04-18 09:30","2022-04-18 13:00","연속"]
[13,"서울","성동","휘경종암#2 T/L","안암 및 휘경변전소 인출 OF케이블 선종교체공사","1. 공사명 : 안암 및 휘경변전소 인출 OF케이블 선종교체공사 2. 대상선로 : 휘경종암#1, 2T/L 3. 공사내용 : 변전소내 화재확산 방지 OF→XLPE 선종교체 4. 공사구간 : 종단접속함(EBG)~첫번째 접속함 구간","2022-04-04 09:00","2022-05-12 18:00","2022-04-04 09:00","2022-05-12 18:00","연속"]
[14,"서울","직할","종로서소문 T/L","22년 직할 변전협력 총액공사","GIS 보통점검","2022-04-12 10:00","2022-04-12 18:00","2022-04-12 10:00","2022-04-12 18:00","연속"]
[15,"서울","직할","서소문S/S CB 6100","22년 직할 변전협력 총액공사","서소문S/S 모선보호반 대체공사","2022-04-26 10:00","2022-04-29 18:00","2022-04-26 10:00","2022-04-29 18:00","연속"]
[16,"서울","직할","중앙서소문 T/L","22년 직할 변전협력 총액공사","GIS 보통점검 -중앙S/S 중앙서소문T/L 조작시험(병행)","2022-04-13 10:00","2022-04-13 18:00","2022-04-13 10:00","2022-04-13 18:00","연속"]
[17,"남서울","강남","과천동안양#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 과천-동안양#1","2022-04-14 08:00","2022-04-15 18:00","2022-04-14 08:00","2022-04-15 18:00","연속"]
[18,"남서울","강남","과천동안양#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 과천-동안양#2","2022-04-18 08:00","2022-04-19 18:00","2022-04-18 08:00","2022-04-19 18:00","연속"]
[19,"남서울","강남","신양재과천#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : #3M.TR 1차 - 무부하 : 신양재-과천1, 60BUS","2022-04-01 16:00","2022-04-01 18:00","2022-04-01 16:00","2022-04-01 18:00","연속"]
[20,"남서울","강남","신양재과천#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 6100 BUS TIE - 무부하 : 신양재-과천2, 65BUS","2022-04-05 12:00","2022-04-05 14:00","2022-04-05 12:00","2022-04-05 14:00","연속"]
[21,"남서울","강남","신양재과천#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-과천1","2022-04-05 14:00","2022-04-06 18:00","2022-04-05 14:00","2022-04-06 18:00","연속"]
[22,"남서울","강남","신양재과천#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-과천2","2022-04-07 08:00","2022-04-08 18:00","2022-04-07 08:00","2022-04-08 18:00","연속"]
[23,"남서울","강남","논현논일#1 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 조작시험","2022-04-01 09:00","2022-04-01 14:00","2022-04-30 09:00","2022-04-30 14:00","연속"]
[24,"남서울","강남","논현논일#2 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 조작시험","2022-04-01 14:00","2022-04-01 18:00","2022-04-30 14:00","2022-04-30 18:00","연속"]
[25,"남서울","강남","논현S/S #1 BUS","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : #3M.TR 1차 - 무부하 : 논현-선릉1, 60BUS","2022-04-27 16:00","2022-04-27 18:00","취소","취소","연속"]
[26,"남서울","강남","논현선릉#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 논현-선릉#2","2022-04-25 08:00","2022-04-26 14:00","2022-04-25 08:00","2022-04-26 14:00","연속"]
[27,"남서울","강남","논현선릉#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : #3M.TR 1차 - 무부하 : 논현-선릉1, 60BUS","2022-04-27 16:00","2022-04-27 18:00","2022-04-27 16:00","2022-04-27 18:00","연속"]
[28,"남서울","강남","논현선릉#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 6100BUS TIE - 무부하 : 논현-선릉2, 65BUS","2022-04-29 16:00","2022-04-29 18:00","2022-04-29 16:00","2022-04-29 18:00","연속"]
[29,"남서울","강남","논현S/S #2 BUS","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 6100BUS TIE - 무부하 : 논현-선릉2, 65BUS","2022-04-29 16:00","2022-04-29 18:00","취소","취소","연속"]
[30,"남서울","강남","대치논현#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 논현-대치#2","2022-04-21 08:00","2022-04-22 18:00","2022-04-21 08:00","2022-04-22 18:00","연속"]
[31,"남서울","강남","신양재신사#3 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","-GIS 조작시험","2022-04-07 09:00","2022-04-07 14:00","2022-04-07 09:00","2022-04-07 14:00","연속"]
[32,"남서울","동서울","동서울가락#2 T/L","154kV 동서울-송파,가락T/L 지중화공사","○ 공사명 : 154kV 동서울-송파,가락T/L 지중화공사 ○ 공사기간 : 2020.10.19 ~ 2021.06.21 ○ 목적 : 하남감일지구 조성에 따른 가공송전선로 지중화 시행 ○ 주요공종 : 케이블포설 : 28구간, 케이블접속 : 32개소","2022-04-04 09:00","2022-05-10 18:00","취소","취소","연속"]
[33,"남서울","동서울","동서울S/S #67 BUS","동서울S/S 노후 주변압기 교체 및 이설공사","○ 345kV 주변압기 교체 및 이설 * 11대 ○ 기타 부대작업 * 1식","2022-04-05 15:00","2022-04-05 17:00","2022-04-05 15:00","2022-04-05 17:00","연속"]
[34,"남서울","동서울","동서울서종#2 T/L","154kV 동서울-서종T/L 철탑추락방지시설 설치공사","154kV 동서울-서종T/L 철탑추락방지시설 설치공사","2022-04-25 07:00","2022-05-01 17:00","취소","취소","연속"]
[35,"남서울","동서울","동서울서종#1 T/L","154kV 동서울-서종T/L 철탑추락방지시설 설치공사","154kV 동서울-서종T/L 철탑추락방지시설 설치공사","2022-04-18 07:00","2022-04-24 17:00","취소","취소","연속"]
[36,"남서울","동서울","가락수서#2 T/L","154kV 수서S/S 노후 23kV GIS 교체공사","154kV GIS 감시,제어 포인트 이설(RTU-&gt현장정보처리반)","2022-04-13 14:00","2022-04-14 18:00","2022-04-13 14:00","2022-04-14 18:00","연속"]
[37,"남서울","동서울","수서S/S #2 BUS","154kV 수서S/S 노후 23kV GIS 교체공사","154kV GIS 감시,제어 포인트 이설(RTU-&gt현장정보처리반)","2022-04-04 09:00","2022-04-04 18:00","취소","취소","연속"]
[38,"남서울","동서울","수서S/S #1 BUS","154kV 수서S/S 노후 23kV GIS 교체공사","154kV GIS 감시,제어 포인트 이설(RTU-&gt현장정보처리반)","2022-04-01 09:00","2022-04-01 18:00","취소","취소","연속"]
[39,"남서울","동서울","가락수서#1 T/L","154kV 수서S/S 노후 23kV GIS 교체공사","154kV GIS 감시,제어 포인트 이설(RTU-&gt현장정보처리반)","2022-04-04 09:00","2022-04-05 18:00","2022-04-04 09:00","2022-04-05 18:00","연속"]
[40,"남서울","동서울","수서S/S CB 6100","154kV 수서S/S 노후 23kV GIS 교체공사","154kV GIS 감시,제어 포인트 이설(RTU-&gt현장정보처리반)","2022-04-05 09:00","2022-04-06 18:00","2022-04-05 09:00","2022-04-06 18:00","연속"]
[41,"남서울","동서울","산성수서#1 T/L","154kV 수서S/S 노후 23kV GIS 교체공사","154kV GIS 감시,제어 포인트 이설(RTU-&gt현장정보처리반)","2022-04-06 09:00","2022-04-07 18:00","2022-04-06 09:00","2022-04-07 18:00","연속"]
[42,"남서울","동서울","산성수서#2 T/L","154kV 수서S/S 노후 23kV GIS 교체공사","154kV GIS 감시,제어 포인트 이설(RTU-&gt현장정보처리반)","2022-04-11 09:00","2022-04-12 18:00","2022-04-11 09:00","2022-04-12 18:00","연속"]
[43,"남서울","동서울","잠실S/S CB 6100","잠실SS 6100 BUSTIE GIS 정밀점검","170kV GIS 정밀점검공사","2022-04-18 09:00","2022-04-20 14:00","취소","취소","연속"]
[44,"남서울","동서울","잠실수서#1 T/L","잠실SS 잠실-수서1TL 정밀점검(수서SS : 조작시험)","170kV GIS 정밀점검공사","2022-04-07 09:00","2022-04-09 14:00","2022-04-07 09:00","2022-04-09 18:00","연속"]
[45,"남서울","동서울","잠실수서#2 T/L","잠실SS 잠실-수서2TL 정밀점검(수서SS : 조작시험)","170kV GIS 정밀점검공사","2022-04-11 09:00","2022-04-13 14:00","2022-04-11 09:00","2022-04-13 14:00","연속"]
[46,"남서울","동서울","송파잠실#1 T/L","잠실SS 송파-잠실1TL 정밀점검(송파SS : 조작시험)","170kV GIS 정밀점검공사","2022-04-15 18:00","2022-04-17 18:00","2022-04-15 18:00","2022-04-17 18:00","연속"]
[47,"남서울","동서울","잠실S/S #2 BUS","잠실SS 6133 170kV GIS 정밀점검 무부하가압(65BUS)","170kV GIS 정밀점검공사 무부하가압(65BUS)","2022-04-29 09:00","2022-04-29 14:00","취소","취소","연속"]
[48,"남서울","동서울","잠실수서#1 T/L","잠실SS 6100BT 정밀점검 무부하가압","170kV GIS 정밀점검공사 무부하가압","2022-04-20 09:00","2022-04-20 14:00","2022-04-20 09:00","2022-04-20 14:00","연속"]
[49,"남서울","동서울","잠실S/S #1 BUS","잠실SS 6233 170kV GIS 정밀점검 무부하가압(60BUS)","170kV GIS 정밀점검공사 무부하가압(60BUS)","2022-04-27 09:00","2022-04-27 14:00","취소","취소","연속"]
[50,"남서울","동서울","잠실S/S #1 BUS","잠실SS 6100 BUSTIE GIS 정밀점검 무부하가압(60BUS)","170kV GIS 정밀점검공사 무부하가압(60BUS)","2022-04-20 09:00","2022-04-20 14:00","취소","취소","연속"]
[51,"남서울","동서울","잠실수서#1 T/L","잠실SS 6133 170kV GIS 정밀점검 무부하가압(잠실수서1TL)","6133 170kV GIS 정밀점검공사 무부하가압(잠실수서1TL)","2022-04-29 09:00","2022-04-29 14:00","2022-04-29 09:00","2022-04-29 14:00","연속"]
[52,"남서울","동서울","잠실수서#2 T/L","잠실SS #2M.Tr 1차(6233)GIS 정밀점검 무부하가압","170kV GIS 정밀점검공사 무부하가압","2022-04-27 09:00","2022-04-27 14:00","2022-04-27 09:00","2022-04-27 14:00","연속"]
[53,"남서울","동서울","잠실수서#2 T/L","잠실SS #4M.Tr 1차(6433)GIS 정밀점검 무부하가압","170kV GIS 정밀점검공사 무부하가압","2022-04-22 09:00","2022-04-22 14:00","2022-04-22 09:00","2022-04-22 14:00","연속"]
[54,"남서울","동서울","잠실S/S #1 BUS","잠실SS 6433 170kV GIS 정밀점검 무부하가압(60BUS)","170kV GIS 정밀점검공사 무부하가압(60BUS)","2022-04-22 09:00","2022-04-22 14:00","취소","취소","연속"]
[55,"남서울","동서울","천호구의#1 T/L","154kV 천호S/S #4M.Tr 증설공사","가스변압기 1BANK 설치","2022-04-13 10:00","2022-04-14 10:00","2022-04-23 10:00","2022-04-24 10:00","연속"]
[56,"남서울","동서울","천호S/S #1 BUS","154kV 천호S/S #4M.Tr 증설공사","가스변압기 1BANK 설치","2022-04-13 10:00","2022-04-13 14:00","취소","취소","연속"]
[57,"남서울","동서울","천호S/S #2 BUS","154kV 천호S/S #4M.Tr 증설공사","가스변압기 1BANK 설치","2022-04-13 14:00","2022-04-14 10:00","취소","취소","연속"]
[58,"남서울","동서울","잠실탄천#2 T/L","잠실SS 잠실-탄천2TL 정밀점검(탄천SS : 보통점검)","170kV GIS 정밀점검공사","2022-04-04 14:00","2022-04-06 18:00","취소","취소","연속"]
[59,"남서울","동서울","잠실탄천#1 T/L","잠실SS 잠실-탄천1TL 정밀점검(탄천SS : 보통점검)","170kV GIS 정밀점검공사","2022-04-02 09:00","2022-04-04 14:00","취소","취소","연속"]
[60,"남서울","영등포","마곡가양#1 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 조작시험","2022-04-16 09:00","2022-04-16 18:00","2022-04-16 09:00","2022-04-16 18:00","연속"]
[61,"남서울","영등포","마곡가양#2 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 조작시험","2022-04-17 09:00","2022-04-17 18:00","2022-04-17 09:00","2022-04-17 18:00","연속"]
[62,"남서울","영등포","신광명광명#1 T/L","154kV 광명S/S 인출전력구 OF케이블 선종교체공사","선공교체 : OF/XLPE 2,000SQ 0.349km교체(D) 이종 및 종단접속 : 12상 및 기타 부대공사","2022-04-01 08:00","2022-05-31 18:00","2022-04-01 08:00","2022-05-31 18:00","연속"]
[63,"남서울","영등포","시흥독산#1 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 공압식차단기 조작시험","2022-04-06 09:00","2022-04-06 18:00","2022-04-06 09:00","2022-04-06 18:00","연속"]
[64,"남서울","영등포","시흥독산#2 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 공압식차단기 조작시험","2022-04-07 09:00","2022-04-07 18:00","2022-04-07 09:00","2022-04-07 18:00","연속"]
[65,"남서울","영등포","신광명시흥#2 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 공압식차단기 조작시험","2022-04-20 09:00","2022-04-20 18:00","2022-04-20 09:00","2022-04-20 18:00","연속"]
[66,"남서울","영등포","시흥S/S CB 6100","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 조작시험","2022-04-08 09:00","2022-04-08 18:00","2022-04-08 09:00","2022-04-08 18:00","연속"]
[67,"남서울","영등포","시흥S/S CB 6100","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 공압식차단기 조작시험","2022-04-27 09:00","2022-04-27 18:00","취소","취소","연속"]
[68,"남서울","영등포","신광명시흥#1 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 공압식차단기 조작시험","2022-04-19 09:00","2022-04-19 18:00","2022-04-19 09:00","2022-04-19 18:00","연속"]
[69,"남서울","영등포","온수S/S CB 6100","'22~23년 영등포P/O 변전협력회사 총액공사","- 170kV GIS 공압식차단기 조작시험","2022-04-28 09:00","2022-04-28 18:00","2022-04-28 09:00","2022-04-28 18:00","연속"]
[70,"남서울","직할","봉천신길#2 T/L","154kV GIS 정밀점검공사_봉천-신길#2T/L","154kV GIS 정밀점검공사_봉천-신길#2T/L","2022-04-06 14:00","2022-04-08 18:00","2022-04-06 14:00","2022-04-08 18:00","연속"]
[71,"남서울","직할","봉천신길#1 T/L","154kV GIS 정밀점검공사_봉천-신길#1T/L","154kV GIS 정밀점검공사_봉천-신길#1T/L","2022-04-04 09:00","2022-04-06 14:00","2022-04-04 09:00","2022-04-06 14:00","연속"]
[72,"남서울","직할","대방신길#1 T/L","170kV GIS 무부하가압 및 정밀점검 공사(신길 대방-신길#1)","170kV GIS 무부하가압 및 정밀점검 공사(신길 대방-신길#1)","2022-04-27 11:00","2022-04-29 18:00","2022-04-27 11:00","2022-04-29 18:00","연속"]
[73,"남서울","직할","신길S/S CB 6100","170kV GIS 정밀점검공사(신길 6100)","170kV GIS 정밀점검공사(신길 6100)","2022-04-25 09:00","2022-04-27 14:00","2022-04-25 09:00","2022-04-27 14:00","연속"]
[74,"남서울","직할","신길S/S #1 BUS","170kV GIS 정밀점검 무부하 가압용(#1BUS)","170kV GIS 정밀점검 무부하 가압용(#1BUS)","2022-04-27 11:00","2022-04-27 14:00","2022-04-27 11:00","2022-04-27 14:00","연속"]
[75,"남서울","직할","신문래구로#1 T/L","170kV GIS 보통점검 공사","170kV GIS 보통점검 공사","2022-04-18 09:00","2022-04-18 18:00","2022-04-18 09:00","2022-04-18 18:00","연속"]
[76,"남서울","직할","신문래목동#2 T/L","170kV GIS 보통점검 공사","170kV GIS 보통점검 공사","2022-04-20 09:00","2022-04-20 18:00","2022-04-20 09:00","2022-04-20 18:00","연속"]
[77,"인천","부평","신가좌주안#1 T/L","신가좌주안#1 T/L GIS 보통점검 및 보조계전기 교체","신가좌주안#1 T/L GIS 보통점검 및 보조계전기 교체 -주안S/S 신가좌주안#1 T/L GIS 보통점점검 병행","2022-04-01 09:00","2022-04-01 18:00","2022-04-01 09:00","2022-04-01 18:00","연속"]
[78,"인천","직할","갈산S/S CB 6200","갈산S/S 6200TIE GIS하자점검","갈산S/S 6200TIE GIS하자점검","2022-04-11 09:30","2022-04-11 18:00","2022-04-11 09:30","2022-04-11 18:00","연속"]
[79,"인천","부평","신가좌주안#2 T/L","신가좌주안#2 T/L GIS 보통점검 및 보조계전기 교체","신가좌주안#2 T/L GIS 보통점검 및 보조계전기 교체 - 주안S/S 신가좌주안#2 T/L GIS 보통점검 및 보조계전기 교체 병행","2022-04-02 09:00","2022-04-02 18:00","2022-04-02 09:00","2022-04-02 18:00","연속"]
[80,"인천","부평","서인천C/C CB 6100","서인천S/Y 60-65BUS 모선보호반 교체공사","서인천S/Y 60-65BUS 모선보호반 교체공사 -6100GIS 보통점검","2022-04-04 09:00","2022-04-08 18:00","2022-04-04 09:00","2022-04-08 18:00","연속"]
[81,"인천","시흥","도림오봉#1 T/L","도림SS 154kV 도림오봉#1T/L GIS 하자점검","도림SS 154kV 도림오봉#1T/L GIS 하자점검","2022-04-04 09:00","2022-04-04 14:00","2022-04-04 09:00","2022-04-04 14:00","연속"]
[82,"인천","직할","경서북인천#1 T/L","북인천S/S 경서북인천#1T/L GIS 정밀점검","북인천S/S 경서북인천#1T/L GIS 정밀점검","2022-04-04 09:30","2022-04-06 18:00","2022-04-04 09:30","2022-04-06 18:00","연속"]
[83,"인천","김포","왕길양촌#2 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #1BUS 측 설치(1차 김포열병합1,2T/L, PT) - 무부하 가압","2022-04-04 14:00","2022-04-05 14:00","2022-04-04 14:00","2022-04-05 14:00","연속"]
[84,"인천","시흥","도림오봉#2 T/L","도림SS 154kV 도림오봉#2 T/L GIS 조작시험","도림SS 154kV 도림오봉#2 T/L GIS 조작시험","2022-04-04 14:00","2022-04-04 18:00","2022-04-04 14:00","2022-04-04 18:00","연속"]
[85,"인천","시흥","신시흥시화#1 T/L","신시흥S/S 154kV 신시흥시화#1 T/L GIS 초기점검","신시흥S/S 154kV 신시흥시화#1 T/L GIS 초기점검","2022-04-05 09:00","2022-04-05 18:00","취소","취소","연속"]
[86,"인천","직할","신부평중동#1 T/L","345kV 서인천-신부평 등 11개T/L 구형 SVL교체공사","구형 SVL 교체를 통한 난연성 확보 및 파급고장 예방","2022-04-05 09:00","2022-04-08 18:00","2022-04-05 09:00","2022-04-08 18:00","연속"]
[87,"인천","김포","왕길양촌#2 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #2BUS 측 설치(1차 김포열병합1,2T/L, PT) - 인근BAY 휴전","2022-04-06 09:00","2022-04-08 18:00","2022-04-06 09:00","2022-04-08 18:00","연속"]
[88,"인천","시흥","신시흥도림#1 T/L","도림S/S 170kV 신시흥도림#1T/L GIS 하자점검","도림S/S 신시흥도림#1 T/L GIS 하자점검 신시흥S/S 신시흥도림#1 T/L GIS 조작시험","2022-04-06 09:00","2022-04-06 18:00","2022-04-06 09:00","2022-04-06 18:00","연속"]
[89,"인천","시흥","오봉고잔#1 T/L","오봉S/S 154kV 오봉고잔#1T/L GIS 조작시험","오봉S/S 154kV 오봉고잔#1T/L GIS 조작시험","2022-04-07 09:00","2022-04-07 14:00","2022-04-07 09:00","2022-04-07 14:00","연속"]
[90,"인천","직할","갈산도당#2 T/L","갈산S/S 갈산도당#2T/L GIS 하자점검","갈산S/S 갈산도당#2T/L GIS 하자점검","2022-04-07 09:30","2022-04-07 18:00","2022-04-07 09:30","2022-04-07 18:00","연속"]
[91,"인천","직할","경서북인천#2 T/L","북인천S/S 경서북인천#2T/L GIS 정밀점검","북인천S/S 경서북인천#2T/L GIS 정밀점검","2022-04-07 09:30","2022-04-09 18:00","2022-04-07 09:30","2022-04-09 18:00","연속"]
[92,"인천","시흥","오봉고잔#2 T/L","오봉S/S 154kV 오봉고잔#2T/L GIS 조작시험","오봉S/S 154kV 오봉고잔#2T/L GIS 조작시험","2022-04-07 14:00","2022-04-07 18:00","2022-04-07 14:00","2022-04-07 18:00","연속"]
[93,"인천","시흥","신시흥도림#2 T/L","도림S/S 154kV 신시흥도림#2T/L GIS 조작시험","도림S/S 154kV 신시흥도림#2T/L GIS 조작시험 신시흥S/S 154kV 신시흥도림#2T/L GIS 조작시험","2022-04-08 09:00","2022-04-08 18:00","2022-04-08 09:00","2022-04-08 18:00","연속"]
[94,"인천","직할","갈산도당#1 T/L","갈산S/S 갈산도당#1T/L GIS 하자점검","갈산S/S 갈산도당#1T/L GIS 하자점검","2022-04-08 09:30","2022-04-08 18:00","2022-04-09 09:30","2022-04-09 18:00","연속"]
[95,"인천","시흥","신시흥#1S/S #66 BUS","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사","2022-04-11 09:00","2022-04-12 16:00","2022-04-11 09:00","2022-04-12 16:00","연속"]
[96,"인천","시흥","신시흥남동#1 T/L","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사","2022-04-11 09:00","2022-04-27 18:00","2022-04-11 09:00","2022-04-27 18:00","연속"]
[97,"인천","직할","신부평중동#2 T/L","345kV 서인천-신부평 등 11개T/L 구형 SVL교체공사","구형 SVL 교체를 통한 난연성 확보 및 파급고장 예방","2022-04-12 09:00","2022-04-15 18:00","2022-04-12 09:00","2022-04-15 18:00","연속"]
[98,"인천","시흥","신시흥#1S/S CB 6200","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사(시험가압)","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사(시험가압)","2022-04-12 15:00","2022-04-12 16:00","2022-04-12 15:00","2022-04-12 16:00","연속"]
[99,"인천","시흥","신시흥#1S/S #61 BUS","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사","2022-04-12 16:00","2022-04-18 15:00","2022-04-12 16:00","2022-04-18 15:00","연속"]
[100,"인천","직할","임학계양#1 T/L","임학S/S #3M.Tr 1차 GIS 정밀점검(무부하가압용)","임학S/S #3M.Tr 1차 GIS 정밀점검(무부하가압용)","2022-04-13 09:30","2022-04-13 18:00","2022-04-13 09:30","2022-04-13 18:00","연속"]
[101,"인천","김포","왕길양촌#2 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #2BUS 측 설치(1차 김포열병합1,2T/L, PT) - 무부하 가압","2022-04-13 14:00","2022-04-14 14:00","2022-04-13 14:00","2022-04-14 14:00","연속"]
[102,"인천","김포","왕길양촌#1 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #1BUS 모선보호반 보호회로 이설","2022-04-15 09:00","2022-04-15 11:00","2022-04-15 09:00","2022-04-15 13:00","연속"]
[103,"인천","시흥","서서울#2소래 T/L","소래S/S 154kV 서서울2소래 T/L GIS 조작시험","소래S/S 154kV 서서울2소래 T/L GIS 조작시험","2022-04-15 09:00","2022-04-15 18:00","2022-04-16 09:00","2022-04-16 18:00","연속"]
[104,"인천","김포","왕길양촌#1 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #2BUS 모선보호반 보호회로 이설","2022-04-15 11:00","2022-04-15 13:00","취소","취소","연속"]
[105,"인천","김포","왕길양촌#2 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #1BUS 모선보호반 보호회로 이설","2022-04-15 13:00","2022-04-15 15:00","2022-04-15 13:00","2022-04-15 17:00","연속"]
[106,"인천","김포","왕길양촌#2 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #2BUS 모선보호반 보호회로 이설","2022-04-15 15:00","2022-04-15 17:00","취소","취소","연속"]
[107,"인천","직할","임학계양#1 T/L","임학S/S 공항철도계양#1T/L GIS 정밀점검(무부하가압용)","임학S/S 공항철도계양#1T/L GIS 정밀점검(무부하가압용)","2022-04-16 09:30","2022-04-16 18:00","2022-04-16 09:30","2022-04-16 18:00","연속"]
[108,"인천","시흥","신시흥#1S/S CB 6200","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사(무부하가압)","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사(무부하가압)","2022-04-17 15:00","2022-04-18 15:00","2022-04-17 15:00","2022-04-18 15:00","연속"]
[109,"인천","시흥","신시흥#1S/S #66 BUS","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사","2022-04-18 15:00","2022-04-27 12:00","2022-04-18 15:00","2022-04-27 12:00","연속"]
[110,"인천","직할","신부평중동#3 T/L","345kV 서인천-신부평 등 11개T/L 구형 SVL교체공사","구형 SVL 교체를 통한 난연성 확보 및 파급고장 예방","2022-04-19 09:00","2022-04-22 18:00","2022-04-19 09:00","2022-04-22 18:00","연속"]
[111,"인천","직할","부천원미#1 T/L","원미S/S #1M.Tr 1차 GIS 정밀점검(무부하가압용)","원미S/S #1M.Tr 1차 GIS 정밀점검(무부하가압용)","2022-04-20 09:30","2022-04-20 18:00","2022-04-20 09:30","2022-04-20 18:00","연속"]
[112,"인천","부평","서인천C/C #66 BUS","서인천C/C 154kV #66 BUS 가스누기 관련 보수","서인천C/C 154kV #66 BUS 가스누기 관련 보수","2022-04-21 09:00","2022-04-23 18:00","2022-04-21 09:00","2022-04-23 18:00","연속"]
[113,"인천","직할","부천원미#1 T/L","원미S/S #2M.Tr 1차 GIS 정밀점검(무부하가압용)","원미S/S #2M.Tr 1차 GIS 정밀점검(무부하가압용)","2022-04-23 09:30","2022-04-23 18:00","2022-04-22 09:30","2022-04-22 18:00","연속"]
[114,"인천","김포","신경서왕길#1 T/L","왕길S/S 170kV 신경서-왕길#1T/L GIS 정밀점검","왕길S/S 170kV 신경서-왕길#1T/L GIS 정밀점검","2022-04-25 09:00","2022-04-27 14:00","2022-04-25 09:00","2022-04-27 14:00","연속"]
[115,"인천","직할","부개원미#1 T/L","원미S/S 부개원미#1T/L GIS 정밀점검","원미S/S 부개원미#1T/L GIS 정밀점검","2022-04-25 09:30","2022-04-27 18:00","2022-04-23 09:30","2022-04-24 18:00","연속"]
[116,"인천","시흥","신시흥#1S/S #61 BUS","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사(실부하가압)","신시흥S/S 154kV 신시흥남동#1T/L GIS대체공사(실부하가압)","2022-04-27 12:00","2022-04-27 18:00","2022-04-27 12:00","2022-04-27 18:00","연속"]
[117,"인천","김포","신경서왕길#2 T/L","왕길S/S 170kV 신경서-왕길#2T/L GIS 정밀점검","왕길S/S 170kV 신경서-왕길#2T/L GIS 정밀점검","2022-04-27 14:00","2022-04-29 18:00","2022-04-27 14:00","2022-04-29 18:00","연속"]
[118,"인천","부평","신가좌S/S SEC CB 60610","신가좌S/S #60-#61 SEC GIS 조작시험 및 보조계전기 교체","신가좌S/S 154kV #60-#61 SEC GIS 조작시험 및 보조계전기 교체","2022-04-28 09:00","2022-04-28 18:00","2022-04-28 09:00","2022-04-28 18:00","연속"]
[119,"인천","시흥","오봉남동#1 T/L","오봉S/S 154kV 오봉남동#1 T/L GIS 조작시험","오봉S/S 154kV 오봉남동#1 T/L GIS 조작시험","2022-04-28 09:00","2022-04-28 14:00","2022-04-28 09:00","2022-04-28 14:00","연속"]
[120,"인천","직할","부개원미#2 T/L","원미S/S 부개원미#2T/L GIS 정밀점검","원미S/S 부개원미#2T/L GIS 정밀점검","2022-04-28 09:30","2022-04-30 18:00","2022-04-30 09:30","2022-05-01 18:00","연속"]
[121,"인천","시흥","오봉남동#2 T/L","오봉S/S 154kV 오봉남동#2 T/L GIS 조작시험","오봉S/S 154kV 오봉남동#2 T/L GIS 조작시험","2022-04-28 14:00","2022-04-28 18:00","2022-04-28 14:00","2022-04-28 18:00","연속"]
[122,"인천","부평","신가좌S/S SEC CB 65660","신가좌S/S #65-#66 SEC GIS 조작시험 및 보조계전기 교체","신가좌S/S 154kV #65-#66 SEC GIS 조작시험 및 보조계전기 교체","2022-04-29 09:00","2022-04-29 18:00","2022-04-29 09:00","2022-04-29 18:00","연속"]
[123,"인천","김포","왕길양촌#2 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - #1,2BUS 가압","2022-04-30 14:00","2022-05-01 16:00","2022-04-30 14:00","2022-05-01 16:00","연속"]
[124,"경기북부","고양","신덕은금촌#1 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2022-04-13 09:00","2022-04-13 18:00","2022-04-13 09:00","2022-04-13 18:00","연속"]
[125,"경기북부","고양","신덕은금촌#2 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2022-04-14 09:00","2022-04-14 18:00","2022-04-14 09:00","2022-04-14 18:00","연속"]
[126,"경기북부","고양","월롱금촌#2 T/L","170kV GIS 차단기 조작시험 - 변전총액공사","금촌S/S 154kV 월롱-금촌#2T/L GIS 차단기 조작시험","2022-04-06 10:00","2022-04-06 14:00","2022-04-06 10:00","2022-04-06 14:00","연속"]
[127,"경기북부","고양","월롱금촌#1 T/L","170kV GIS 차단기 조작시험 - 변전총액공사","금촌S/S 154kV 월롱-금촌#1T/L GIS 차단기 조작시험","2022-04-05 10:00","2022-04-05 14:00","2022-04-05 10:00","2022-04-05 14:00","연속"]
[128,"경기북부","고양","신덕은금촌#2 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2022-04-15 09:00","2022-04-15 18:00","2022-04-15 09:00","2022-04-15 18:00","연속"]
[129,"경기북부","고양","일산송포#1 T/L","154kV 일산-송포#1T/L 고정형 절연유 채취밸브 설치공사","활선OF 케이블용 고정형 절연유 채취밸브 설치","2022-04-04 09:00","2022-04-08 18:00","2022-04-04 09:00","2022-04-08 18:00","연속"]
[130,"경기북부","고양","일산송포#2 T/L","154kV 일산-송포#2T/L 고정형 절연유 채취밸브 설치공사","활선OF 케이블용 고정형 절연유 채취밸브 설치","2022-04-11 09:00","2022-04-15 18:00","2022-04-11 09:00","2022-04-15 18:00","연속"]
[131,"경기북부","고양","일산S/S SEC CB 60610","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2022-04-28 09:00","2022-04-28 18:00","2022-04-28 09:00","2022-04-28 18:00","연속"]
[132,"경기북부","고양","일산S/S SEC CB 65660","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2022-04-29 09:00","2022-04-29 18:00","2022-04-29 09:00","2022-04-29 18:00","연속"]
[133,"경기북부","고양","지도능곡#1 T/L","154kV 지도-능곡#1T/L 선종교체공사","○ 지도S/S ~ #1S/J, #16S/J ~ 능곡S/S 구간 OF 케이블 → XLPE 케이블 선종교체공사","2022-04-04 09:00","2022-05-20 18:00","2022-04-04 09:00","2022-05-20 18:00","연속"]
[134,"경기북부","구리","가평청평HP#1 T/L","2022년도 가공송전선로 순시점검 위탁공사","154kV 가평-춘천HP T/L 정밀점검 실시(No.129~135 병가구간 휴전)","2022-04-29 09:00","2022-04-29 18:00","2022-04-29 09:00","2022-04-29 18:00","연속"]
[135,"경기북부","구리","가평청평HP#2 T/L","송전선로 추락방지시설 설치공사","154kV 화천T/L 추락방지시설설치(No.129~135 병가구간)","2022-04-13 07:00","2022-04-14 18:00","2022-04-13 07:00","2022-04-14 18:00","연속"]
[136,"경기북부","구리","가평춘천HP T/L","2022년도 가공송전선로 순시점검 위탁공사","154kV 가평-춘천HP T/L 정밀점검 실시(No.70~135)","2022-04-25 09:00","2022-04-29 18:00","2022-04-25 09:00","2022-04-29 18:00","연속"]
[137,"경기북부","구리","구리S/S #1 BUS","구리S/S 170kV 장기사용 GIS 교체공사","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 구리-신내#2T/L GIS ○ #2M.Tr 1차 GIS ○ 6100BUSTIE GIS","2022-04-08 02:00","2022-04-21 02:00","2022-04-08 02:00","2022-04-21 02:00","연속"]
[138,"경기북부","구리","구리S/S #2 BUS","구리S/S 170kV 장기사용 GIS 교체공사","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 구리-신내#2T/L GIS ○ #2M.Tr 1차 GIS ○ 6100BUSTIE GIS","2022-04-04 09:00","2022-04-08 02:00","2022-04-04 09:00","2022-04-08 02:00","연속"]
[139,"경기북부","구리","구리S/S CB 6100","구리S/S 170kV 장기사용 GIS 교체공사","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 구리-신내#2T/L GIS ○ #2M.Tr 1차 GIS ○ 6100BUSTIE GIS","2022-04-04 09:00","2022-05-02 18:00","2022-04-04 09:00","2022-05-02 18:00","연속"]
[140,"경기북부","구리","구리신내#2 T/L","구리S/S 170kV 장기사용 GIS 교체공사","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 구리-신내#2T/L GIS ○ #2M.Tr 1차 GIS ○ 6100BUSTIE GIS","2022-04-04 09:00","2022-05-02 18:00","2022-04-04 09:00","2022-05-02 18:00","연속"]
[141,"경기북부","구리","미금구리#1 T/L","구리S/S 170kV 장기사용 GIS 교체공사(시험가압)","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 65BUS 시험가압","2022-04-07 15:00","2022-04-08 04:00","2022-04-07 15:00","2022-04-08 04:00","연속"]
[142,"경기북부","구리","미금구리#1 T/L","구리S/S 170kV 장기사용 GIS 교체공사(시험가압)","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 4.30(토) 17:00 ~ 5.2(월) 02:00 - 구리신내#2T/L, #2M.Tr 1차, BUSTIE GIS 시험가압(2DS측) ○ 5.2(월) 02:00 ~ 18:00 - 1DS측 건전성 확인 시험가압 및 최종 환원","2022-04-30 17:00","2022-05-02 18:00","2022-04-30 17:00","2022-05-02 18:00","연속"]
[143,"경기북부","구리","구리S/S #2 BUS","구리S/S 170kV 장기사용 GIS 교체공사","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 구리-신내#2T/L GIS ○ #2M.Tr 1차 GIS ○ 6100BUSTIE GIS","2022-04-21 02:00","2022-05-02 02:00","2022-04-21 02:00","2022-05-02 02:00","연속"]
[144,"경기북부","구리","미금구리#1 T/L","구리S/S 170kV 장기사용 GIS 교체공사(시험가압)","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 60BUS 시험가압","2022-04-19 17:00","2022-04-21 04:00","2022-04-19 17:00","2022-04-21 04:00","연속"]
[145,"경기북부","구리","미금구리#2 T/L","구리S/S 170kV 장기사용 GIS 교체공사(모선절체)","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 1BUS → 2BUS 절체","2022-04-08 02:00","2022-04-08 04:00","2022-04-08 02:00","2022-04-08 04:00","연속"]
[146,"경기북부","구리","구리신내#1 T/L","구리S/S 170kV 장기사용 GIS 교체공사(모선절체)","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 1BUS → 2BUS 절체","2022-04-08 02:00","2022-04-08 04:00","2022-04-08 02:00","2022-04-08 04:00","연속"]
[147,"경기북부","구리","미금구리#2 T/L","구리S/S 170kV 장기사용 GIS 교체공사(모선절체)","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 2BUS → 1BUS 절체","2022-04-21 02:00","2022-04-21 04:00","2022-04-21 02:00","2022-04-21 04:00","연속"]
[148,"경기북부","구리","구리신내#1 T/L","구리S/S 170kV 장기사용 GIS 교체공사(모선절체)","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 2BUS → 1BUS 절체","2022-04-21 02:00","2022-04-21 04:00","2022-04-21 02:00","2022-04-21 04:00","연속"]
[149,"경기북부","구리","내촌용정#1 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치 (수직+수평1회선)","2022-04-04 07:30","2022-04-04 18:00","2022-04-04 07:30","2022-04-04 18:00","연속"]
[150,"경기북부","구리","덕소진건#1 T/L","'22-23 구리전력 변전협력회사 총액공사","덕소S/S 154kV 덕소-진건#1T/L GIS 하자점검","2022-04-06 09:00","2022-04-06 14:00","2022-04-06 09:00","2022-04-06 14:00","연속"]
[151,"경기북부","구리","덕소진건#2 T/L","'22-23 구리전력 변전협력회사 총액공사","덕소S/S 154kV 덕소-진건#2T/L GIS 하자점검","2022-04-06 14:00","2022-04-06 18:00","2022-04-06 14:00","2022-04-06 18:00","연속"]
[152,"경기북부","구리","신장덕소#1 T/L","'22-23 구리전력 변전협력회사 총액공사","덕소S/S 154kV 신장-덕소#1T/L GIS 하자점검","2022-04-11 09:00","2022-04-11 14:00","2022-04-11 09:00","2022-04-11 14:00","연속"]
[153,"경기북부","구리","신장덕소#2 T/L","'22-23 구리전력 변전협력회사 총액공사","덕소S/S 154kV 신장-덕소#2T/L GIS 하자점검","2022-04-11 14:00","2022-04-11 18:00","2022-04-11 14:00","2022-04-11 18:00","연속"]
[154,"경기북부","구리","덕소마석#1 T/L","'22-23 구리전력 변전협력회사 총액공사","덕소S/S 154kV 덕소-마석#1T/L GIS 하자점검","2022-04-12 09:00","2022-04-12 14:00","2022-04-12 09:00","2022-04-12 14:00","연속"]
[155,"경기북부","구리","덕소마석#2 T/L","'22-23 구리전력 변전협력회사 총액공사","덕소S/S 154kV 덕소-마석#2T/L GIS 하자점검","2022-04-12 14:00","2022-04-12 18:00","2022-04-12 14:00","2022-04-12 18:00","연속"]
[156,"경기북부","구리","미금덕소#1 T/L","'22-23 구리전력 변전협력회사 총액공사","덕소S/S 154kV 미금-덕소#1T/L GIS 하자점검","2022-04-07 09:00","2022-04-07 14:00","2022-04-07 09:00","2022-04-07 14:00","연속"]
[157,"경기북부","구리","미금덕소#2 T/L","'22-23 구리전력 변전협력회사 총액공사","덕소S/S 154kV 미금-덕소#2T/L GIS 하자점검","2022-04-07 14:00","2022-04-07 18:00","2022-04-07 14:00","2022-04-07 18:00","연속"]
[158,"경기북부","구리","덕소팔당HP청평HP T/L","22-23 구리전력 변전협력회사 총액공사","덕소S/S 154kV 덕소-팔당-청평HPT/L GIS 하자점검","2022-04-13 14:00","2022-04-13 18:00","2022-04-13 14:00","2022-04-13 18:00","연속"]
[159,"경기북부","구리","덕소팔당HP T/L","'22-23 구리전력 변전협력회사 총액공사","덕소S/S 154kV 덕소-팔당T/L GIS 하자점검","2022-04-13 09:00","2022-04-13 14:00","2022-04-13 09:00","2022-04-13 14:00","연속"]
[160,"경기북부","구리","진건별내#2 T/L","구리전력 154kV GIS 보통점검","구리전력 154kV GIS 보통점검","2022-04-05 14:00","2022-04-05 18:00","2022-04-05 14:00","2022-04-05 18:00","연속"]
[161,"경기북부","구리","진건별내#1 T/L","구리전력 154kV GIS 보통점검","구리전력 154kV GIS 보통점검","2022-04-05 09:00","2022-04-05 14:00","2022-04-05 09:00","2022-04-05 14:00","연속"]
[162,"경기북부","구리","신포천동두천#1 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치 (수평1회선)","2022-04-25 07:30","2022-04-27 18:00","2022-04-25 07:30","2022-04-27 18:00","연속"]
[163,"경기북부","구리","신포천포천#1 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치 (수직+수평1회선)","2022-04-07 07:30","2022-04-15 18:00","2022-04-07 07:30","2022-04-15 18:00","연속"]
[164,"경기북부","구리","신포천동두천#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치 (수직+수평1회선)","2022-04-13 07:30","2022-04-19 18:00","2022-04-13 07:30","2022-04-17 18:00","연속"]
[165,"경기북부","구리","신포천전곡#1 T/L","구리전력 154kV GIS 보통점검","구리전력 154kV GIS 보통점검","2022-04-18 09:00","2022-04-18 14:00","2022-04-01 09:00","2022-04-01 14:00","연속"]
[166,"경기북부","구리","신포천포천#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치 (수평1회선)","2022-04-20 07:30","2022-04-25 18:00","2022-04-27 07:30","2022-05-02 18:00","연속"]
[167,"경기북부","구리","신포천전곡#2 T/L","구리전력 154kV GIS 보통점검","구리전력 154kV GIS 보통점검","2022-04-18 14:00","2022-04-18 18:00","2022-04-01 14:00","2022-04-01 18:00","연속"]
[168,"경기북부","구리","운천철원#2 T/L","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","운천S/S 154kV 운천-철원#2T/L GIS 조작시험","2022-04-19 14:00","2022-04-19 18:00","2022-04-19 14:00","2022-04-19 18:00","연속"]
[169,"경기북부","구리","운천S/S CB 6100","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","운천S/S 154kV #1-#2 BUS TIE GIS 조작시험","2022-04-20 09:00","2022-04-20 14:00","2022-04-20 09:00","2022-04-20 14:00","연속"]
[170,"경기북부","구리","운천철원#1 T/L","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","운천S/S 154kV 운천-철원#1T/L GIS 조작시험","2022-04-19 09:00","2022-04-19 14:00","2022-04-19 09:00","2022-04-19 14:00","연속"]
[171,"경기북부","구리","청평H/P #1호기 주변압기 (CB 6133)","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","청평H/P 154kV #1M.Tr 2차 GCB 조작시험","2022-04-12 09:00","2022-04-12 14:00","2022-04-12 09:00","2022-04-12 14:00","연속"]
[172,"경기북부","구리","청평H/P #2호기 주변압기 (CB 6233)","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","청평H/P 154kV #2M.Tr 2차 GCB 조작시험","2022-04-12 14:00","2022-04-12 18:00","2022-04-12 14:00","2022-04-12 18:00","연속"]
[173,"경기북부","구리","청평H/P #3호기 주변압기 (CB 6333)","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","청평H/P 154kV #3M.Tr 2차 GCB 조작시험","2022-04-13 09:00","2022-04-13 14:00","2022-04-13 09:00","2022-04-13 14:00","연속"]
[174,"경기북부","구리","서종청평PP#2 T/L","청평양수 스위치야드 노후 154kV GIS 대체공사","○ 154kV GIS 철거 및 설치 ○ 기타부대공사 1식","2022-04-14 09:00","2022-04-15 18:00","2022-04-14 09:00","2022-04-15 18:00","연속"]
[175,"경기북부","구리","서종청평PP#2 T/L","청평양수 스위치야드 노후 154kV GIS 대체공사","○ 154kV GIS 철거 및 설치 ○ 기타부대공사 1식","2022-04-07 09:00","2022-04-08 18:00","2022-04-07 09:00","2022-04-08 18:00","연속"]
[176,"경기북부","구리","청평P/P #2 BUS","청평양수 스위치야드 노후 154kV GIS 대체공사","○ 154kV GIS 철거 및 설치 ○ 기타부대공사 1식","2022-04-11 09:00","2022-04-15 18:00","2022-04-11 09:00","2022-04-15 18:00","연속"]
[177,"경기북부","구리","청평P/P #1 BUS","청평양수 스위치야드 노후 154kV GIS 대체공사","○ 154kV GIS 철거 및 설치 ○ 기타부대공사 1식","2022-04-04 09:00","2022-04-08 18:00","2022-04-04 09:00","2022-04-08 18:00","연속"]
[178,"경기북부","구리","용정포천#2 T/L","154kV 포천S/S 옥내화 토건공사","- 건축물 기초 콘크리트 타설 - 철골설치","2022-04-28 09:00","2022-05-13 18:00","2022-04-28 09:00","2022-05-13 18:00","연속"]
[179,"경기북부","직할","신의정부금오#1 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-04-07 14:00","2022-04-07 18:00","2022-04-07 14:00","2022-04-07 18:00","연속"]
[180,"경기북부","직할","양주녹양#1 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-04-14 14:00","2022-04-14 18:00","2022-04-14 14:00","2022-04-14 18:00","연속"]
[181,"경기북부","직할","양주녹양#2 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-04-14 09:00","2022-04-14 14:00","2022-04-14 09:00","2022-04-14 14:00","연속"]
[182,"경기북부","직할","백석덕계#1 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-04-26 09:00","2022-04-26 18:00","2022-04-26 09:00","2022-04-26 18:00","연속"]
[183,"경기북부","직할","신포천덕계#2 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-04-21 09:00","2022-04-21 14:00","2022-04-04 09:00","2022-04-04 14:00","연속"]
[184,"경기북부","직할","신포천덕계#1 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-04-21 14:00","2022-04-21 18:00","2022-04-04 14:00","2022-04-04 18:00","연속"]
[185,"경기북부","직할","별내도봉 T/L","154kV 장암S/S 옥내화관련 인출선로 정비공사","케이블타워 2기 설치, 산형강철탑 1기 보강 등","2022-04-08 09:00","2022-04-17 18:00","취소","취소","연속"]
[186,"경기북부","직할","도봉진접 T/L","154kV 장암S/S 옥내화관련 인출선로 정비공사","케이블타워 2기 설치, 산형강철탑 1기 보강 등","2022-04-08 09:00","2022-04-17 18:00","취소","취소","연속"]
[187,"경기북부","직할","신의정부금오#2 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-04-07 09:00","2022-04-07 14:00","2022-04-07 09:00","2022-04-07 14:00","연속"]
[188,"경기북부","직할","신의정부내촌#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치 (수직+수평1회선)","2022-04-04 07:30","2022-04-06 18:00","2022-04-04 07:30","2022-04-06 18:00","연속"]
[189,"경기북부","직할","양주지축#1 T/L","고양전력지사 추락방지시설 설치공사","ㅇ 추락방지시설(와이어 수직,수평) 설치","2022-04-06 07:00","2022-04-07 18:00","취소","취소","연속"]
[190,"경기북부","직할","양주은평#2 T/L","고양전력지사 추락방지시설 설치공사","ㅇ 추락방지시설(와이어 수직,수평) 설치","2022-04-06 07:00","2022-04-07 18:00","취소","취소","연속"]
[191,"경기북부","직할","양주지축#2 T/L","고양전력지사 추락방지시설 설치공사","ㅇ 추락방지시설(와이어 수직,수평) 설치","2022-04-04 07:00","2022-04-05 18:00","취소","취소","연속"]
[192,"경기북부","직할","양주은평#1 T/L","고양전력지사 추락방지시설 설치공사","ㅇ 추락방지시설(와이어 수직,수평) 설치","2022-04-04 07:00","2022-04-05 18:00","취소","취소","연속"]
[193,"경기북부","직할","옥정송우#2 T/L","154kV 옥정-송우T/L No.14 안전이격거리 확보공사","철탑신설 : 2기 / 철거 2기(가철탑 1기 설치철거 포함) 전력선 : 재사용(No.13~No.15)","2022-04-18 08:00","2022-04-19 18:00","2022-04-25 08:00","2022-04-26 18:00","연속"]
[194,"경기북부","직할","옥정송우#1 T/L","154kV 옥정-송우T/L No.14 안전이격거리 확보공사","철탑신설 : 2기 / 철거 2기(가철탑 1기 설치철거 포함) 전력선 : 재사용(No.13~No.15)","2022-04-20 08:00","2022-04-22 18:00","2022-04-27 08:00","2022-04-29 18:00","연속"]
[195,"경기북부","직할","옥정송우#2 T/L","154kV 옥정-송우T/L No.14 안전이격거리 확보공사","철탑신설 : 2기 / 철거 2기(가철탑 1기 설치철거 포함) 전력선 : 재사용(No.13~No.15)","2022-04-23 08:00","2022-04-24 18:00","2022-04-30 08:00","2022-05-01 18:00","연속"]
[196,"경기","동부","분당S/S SEC CB 65660","22년 동부 변전정비 총액공사","분당:60-61(조작),65-66(조작)","2022-04-15 14:00","2022-04-15 18:00","2022-04-15 14:00","2022-04-15 18:00","연속"]
[197,"경기","동부","분당S/S SEC CB 60610","22년 동부 변전정비 총액공사","분당:60-61(조작),65-66(조작)","2022-04-15 09:30","2022-04-15 14:00","2022-04-15 09:30","2022-04-15 14:00","연속"]
[198,"경기","동부","오포모현#1 T/L","22년 동부 변전정비 총액공사","오포:오포-모현#1T/L(보통)","2022-04-04 09:30","2022-04-04 18:00","2022-04-04 09:30","2022-04-04 18:00","연속"]
[199,"경기","동부","오포모현#2 T/L","22년 동부 변전정비 총액공사","오포:오포-모현#2T/L(보통)","2022-04-05 09:30","2022-04-05 18:00","2022-04-05 09:30","2022-04-05 18:00","연속"]
[200,"경기","동부","분당오포#1 T/L","22년 동부 변전정비 총액공사","오포:분당-오포#1T/L(보통)","2022-04-19 09:30","2022-04-19 18:00","2022-04-19 09:30","2022-04-19 18:00","연속"]
[201,"경기","동부","분당오포#2 T/L","22년 동부 변전정비 총액공사","오포:분당-오포#2T/L(보통)","2022-04-20 09:30","2022-04-20 18:00","2022-04-20 09:30","2022-04-20 18:00","연속"]
[202,"경기","동부","곤지암초월#1 T/L","22년 동부 변전정비 총액공사","초월:곤지암-초월#1T/L(보통)","2022-04-01 09:30","2022-04-01 18:00","2022-04-01 09:30","2022-04-01 18:00","연속"]
[203,"경기","성남","북동탄동탄2열병합#1 T/L","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검(양단)","2022-04-13 09:00","2022-04-13 14:00","2022-04-13 09:00","2022-04-13 14:00","연속"]
[204,"경기","성남","북동탄동탄2열병합#2 T/L","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검(양단)","2022-04-13 14:00","2022-04-13 18:00","2022-04-13 14:00","2022-04-13 18:00","연속"]
[205,"경기","성남","삼미동탄2열병합#3 T/L","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검(양단)","2022-04-22 09:00","2022-04-22 18:00","2022-04-22 09:00","2022-04-22 18:00","연속"]
[206,"경기","성남","삼미동탄2열병합#2 T/L","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검(양단)","2022-04-21 14:00","2022-04-21 18:00","2022-04-21 14:00","2022-04-21 18:00","연속"]
[207,"경기","성남","삼미동탄2열병합#1 T/L","22년 성남전력지사 변전정비회사 총액공사","- GIS 보통점검(양단)","2022-04-21 09:00","2022-04-21 14:00","2022-04-21 09:00","2022-04-21 14:00","연속"]
[208,"경기","성남","신성남#2S/S SEC CB 66670","22년 성남전력 170kV GIS 정밀/보통점검공사","- GIS 정밀점검","2022-04-27 14:00","2022-04-29 18:00","2022-04-27 14:00","2022-04-29 18:00","연속"]
[209,"경기","성남","신성남#2S/S SEC CB 61620","22년 성남전력 170kV GIS 정밀/보통점검공사","- GIS 정밀점검","2022-04-25 09:00","2022-04-27 14:00","2022-04-25 09:00","2022-04-27 14:00","연속"]
[210,"경기","성남","신수원S/S #60 BUS","신수원S/S 154kV 신규수용공사(린데코리아)","154kV 신수원-린데코리아 T/L 무부하가압 및 앵글측정","2022-04-26 10:00","2022-04-27 18:00","2022-04-26 10:00","2022-04-27 18:00","연속"]
[211,"경기","성남","신수원S/S #65 BUS","신수원S/S 154kV 신규수용공사(린데코리아)","154kV 신수원-린데코리아 T/L 무부하가압 및 앵글측정","2022-04-26 09:00","2022-04-26 10:00","2022-04-26 09:00","2022-04-26 10:00","연속"]
[212,"경기","성남","신수원S/S #65 BUS","신수원S/S 154kV 신규수용공사(린데코리아)","170kV GIS 1CCT 설치","2022-04-07 08:00","2022-04-19 18:00","2022-04-07 08:00","2022-04-19 18:00","연속"]
[213,"경기","직할","관양동안양#2 T/L","2022년 경기본부 직할 154kV GIS 정밀점검공사","2022년 경기본부 직할 154kV GIS 정밀점검공사","2022-04-27 09:00","2022-04-28 18:00","취소","취소","연속"]
[214,"경기","직할","관양평촌#1 T/L","22년 경기본부 직할 154kV GIS 정밀점검공사","22년 경기본부 직할 154kV GIS 정밀점검공사","2022-04-18 09:00","2022-04-19 18:00","2022-04-18 09:00","2022-04-19 18:00","연속"]
[215,"경기","직할","관양동안양#1 T/L","2022년 경기본부 직할 154kV GIS 정밀점검공사","2022년 경기본부 직할 154kV GIS 정밀점검공사","2022-04-25 09:00","2022-04-26 18:00","2022-04-25 09:00","2022-04-26 18:00","연속"]
[216,"경기","직할","동안양안양CC#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","동안양S/S 안열 #1T/L GIS 보통점검 안양복합S/Y 안열#1T/L 인출 상호인터록 및 사활경보 회로구성","2022-04-11 09:00","2022-04-11 18:00","2022-04-11 09:00","2022-04-11 18:00","연속"]
[217,"경기","직할","동안양안양CC#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","동안양S/S 안열 #2T/L GIS 보통점검 안양복합S/Y 안열#2T/L 인출 상호인터록 및 사활경보 회로구성","2022-04-12 09:00","2022-04-12 18:00","2022-04-12 09:00","2022-04-12 18:00","연속"]
[218,"경기","직할","발안구문천#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","발안-구문천#2T/L GIS 보통점검","2022-04-01 09:00","2022-04-01 18:00","2022-04-01 09:00","2022-04-01 18:00","연속"]
[219,"경기","직할","동수원우만#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","동수원-우만 #1, 2T/L GIS 조작시험","2022-04-01 09:00","2022-04-01 14:00","2022-04-01 09:00","2022-04-01 14:00","연속"]
[220,"경기","직할","동수원우만#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","동수원-우만 #1, 2T/L GIS 조작시험","2022-04-01 14:00","2022-04-01 18:00","2022-04-01 14:00","2022-04-01 18:00","연속"]
[221,"경기","직할","평촌안양2CC#3 T/L","2022-23 경기본부 직할변전협력회사 총액공사","평촌S/S 평촌-안양복합#3T/L 상호 인터록, 사활경보 회로구성 안양복합S/Y 평촌-안양복합#3T/L 상호 인터록, 사활경보 회로구성","2022-04-14 09:00","2022-04-14 18:00","2022-04-14 09:00","2022-04-14 18:00","연속"]
[222,"경기","직할","평촌안양2CC#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","평촌S/S 평촌-안양복합#1,2T/L 상호 인터록, 사활경보 회로구성 안양복합S/Y 평촌-안양복합#1,2T/L 상호 인터록, 사활경보 회로구성","2022-04-20 09:00","2022-04-20 14:00","2022-04-20 09:00","2022-04-20 14:00","연속"]
[223,"경기","직할","평촌안양2CC#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","평촌S/S 평촌-안양복합#1,2T/L 상호 인터록, 사활경보 회로구성 안양복합S/Y 평촌-안양복합#1,2T/L 상호 인터록, 사활경보 회로구성","2022-04-20 14:00","2022-04-20 18:00","2022-04-20 14:00","2022-04-20 18:00","연속"]
[224,"경기","직할","화성S/S #66 BUS","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 2차측, 화성-수촌#2T/L GIS #2DS 설치","2022-04-25 09:00","2022-05-10 18:00","2022-04-25 09:00","2022-05-10 18:00","연속"]
[225,"경기","직할","화성발안#2 T/L","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 2차측, 화성-수촌#2T/L GIS #1DS 및 CB 설치 후 무부하가압","2022-04-23 09:00","2022-04-24 18:00","취소","취소","연속"]
[226,"경기","직할","화성발안#2 T/L","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 2차측, 화성-수촌#2T/L GIS 대체 관련 안전이격거리 확보","2022-04-16 09:00","2022-04-17 18:00","취소","취소","연속"]
[227,"경기","직할","화성S/S #61 BUS","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 2차측, 화성-수촌#2T/L GIS #1DS 및 CB 철거 후 설치","2022-04-11 09:00","2022-04-24 18:00","2022-04-11 09:00","2022-04-24 18:00","연속"]
[228,"경기","직할","화성발안#2 T/L","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 2차측, 화성-수촌#2T/L GIS #2DS 분리 후 무부하가압","2022-04-09 09:00","2022-04-09 18:00","취소","취소","연속"]
[229,"경기","직할","화성S/S #66 BUS","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 2차측, 화성-수촌#2T/L GIS #2DS 분리","2022-04-07 09:00","2022-04-09 18:00","2022-04-07 09:00","2022-04-09 18:00","연속"]
[230,"경기","직할","화성수촌#2 T/L","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 2차측, 화성-수촌#2T/L GIS 교체","2022-04-07 09:00","2022-05-13 18:00","2022-04-07 09:00","2022-05-13 18:00","연속"]
[231,"경기","직할","화성발안#2 T/L","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 2차측, 화성-수촌#2T/L GIS 대체 관련 안전이격거리 확보","2022-04-30 09:00","2022-05-01 18:00","취소","취소","연속"]
[232,"경기","평택","고덕#2고덕 T/L","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사 - 170kV GIS 회로수정","2022-04-07 10:00","2022-04-07 12:00","2022-04-07 10:00","2022-04-07 12:00","연속"]
[233,"경기","평택","고덕#2S/S #2M.Tr 2차 CB 6700, 6772","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사 - 170kV GIS 회로수정","2022-04-07 10:00","2022-04-07 12:00","취소","취소","연속"]
[234,"경기","평택","고덕#2S/S #3M.Tr 2차 CB 6871, 6800","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사 - 170kV GIS 회로수정","2022-04-07 13:00","2022-04-07 15:00","취소","취소","연속"]
[235,"경기","평택","고덕#2동평택#2 T/L","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사 - 170kV GIS 회로수정","2022-04-07 13:00","2022-04-07 15:00","2022-04-07 13:00","2022-04-07 15:00","연속"]
[236,"경기","평택","서안성안성#1 T/L","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 서안성-안성#1T/L GIS 보통점검","2022-04-18 10:00","2022-04-18 18:00","2022-04-18 10:00","2022-04-18 18:00","연속"]
[237,"경기","평택","서안성S/S SEC CB 65660","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 154kV 65-66 SEC GIS 보통점검","2022-04-14 10:00","2022-04-14 18:00","2022-04-14 10:00","2022-04-14 18:00","연속"]
[238,"경기","평택","서안성S/S SEC CB 60610","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 154kV 60-61 SEC GIS 보통점검","2022-04-13 10:00","2022-04-13 18:00","2022-04-13 10:00","2022-04-13 18:00","연속"]
[239,"경기","평택","서안성남사#2 T/L","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 서안성-남사#2T/L GIS 보통점검","2022-04-12 10:00","2022-04-12 18:00","2022-04-12 10:00","2022-04-12 18:00","연속"]
[240,"경기","평택","서안성남사#1 T/L","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 서안성-남사#1T/L GIS 보통점검","2022-04-11 10:00","2022-04-11 18:00","2022-04-11 10:00","2022-04-11 18:00","연속"]
[241,"경기","평택","서안성안성#2 T/L","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 서안성-안성#2T/L GIS 보통점검","2022-04-19 10:00","2022-04-19 18:00","2022-04-19 10:00","2022-04-19 18:00","연속"]
[242,"경기","평택","서안성S/S CB 6300","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 154kV 6300 BUS TIE GIS 보통점검","2022-04-22 10:00","2022-04-22 18:00","2022-04-22 10:00","2022-04-22 18:00","연속"]
[243,"경기","평택","서안성S/S SEC CB 61620","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 154kV 61-62 SEC GIS 보통점검","2022-04-27 10:00","2022-04-27 18:00","2022-04-27 10:00","2022-04-27 18:00","연속"]
[244,"경기","평택","서안성S/S SEC CB 66670","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 154kV 66-67 SEC GIS 보통점검","2022-04-28 10:00","2022-04-28 18:00","2022-04-28 10:00","2022-04-28 18:00","연속"]
[245,"경기","평택","서안성S/S CB 6200","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 154kV 6200 BUS TIE GIS 보통점검","2022-04-08 10:00","2022-04-08 18:00","2022-04-08 10:00","2022-04-08 18:00","연속"]
[246,"경기","평택","서안성S/S CB 6100","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 154kV 6100 BUS TIE GIS 보통점검","2022-04-07 10:00","2022-04-07 18:00","2022-04-07 10:00","2022-04-07 18:00","연속"]
[247,"경기","평택","서운안성#2 T/L","세종-포천간 2공구 도로개설 관련 지장이설 휴전작업","임기 1기, 신설 1기","2022-04-20 07:00","2022-04-29 18:00","2022-04-20 07:00","2022-04-29 18:00","연속"]
[248,"경기","평택","서운안성#2 T/L","세종-포천간 2공구 도로개설 관련 지장이설 휴전작업","임기 1기, 신설 1기","2022-04-04 07:00","2022-04-09 18:00","2022-04-04 07:00","2022-04-09 18:00","연속"]
[249,"경기","평택","서운안성#1 T/L","세종-포천간 2공구 도로개설 관련 지장이설 휴전작업","임기 1기, 신설 1기","2022-04-11 07:00","2022-04-19 18:00","2022-04-11 07:00","2022-04-19 18:00","연속"]
[250,"경기","평택","원정만호#1 T/L","22년 평택전력지사 변전협력회사 총액공사","원정S/S 원정-만호#1T/L GIS 조작시험 및 에어링밸브 누기 보수","2022-04-04 10:00","2022-04-04 18:00","2022-04-04 10:00","2022-04-04 18:00","연속"]
[251,"경기","평택","원정만호#2 T/L","22년 평택전력지사 변전협력회사 총액공사","원정S/S 원정-만호#2T/L GIS 조작시험 및 만호S/S GIS 디지털유압력계 교체","2022-04-26 10:00","2022-04-27 18:00","2022-04-26 10:00","2022-04-27 18:00","연속"]
[252,"경기","평택","원정평택TP#1 T/L","22년 평택전력지사 변전협력회사 총액공사","원정S/S 원정-평택T/P#1T/L GIS 조작시험","2022-04-28 10:00","2022-04-28 18:00","2022-04-28 10:00","2022-04-28 18:00","연속"]
[253,"경기","평택","원정평택TP#2 T/L","22년 평택전력지사 변전협력회사 총액공사","원정S/S 원정-평택T/P#2T/L GIS 조작시험","2022-04-29 10:00","2022-04-29 18:00","2022-04-29 10:00","2022-04-29 18:00","연속"]
[254,"경기","평택","포승평택TP#1 T/L","22년 평택전력지사 변전협력회사 총액공사","포승S/S 포승-평택T/P#1T/L GIS 조작시험","2022-04-20 10:00","2022-04-20 18:00","2022-04-20 10:00","2022-04-20 18:00","연속"]
[255,"경기","평택","포승평택TP#2 T/L","22년 평택전력지사 변전협력회사 총액공사","포승S/S 포승-평택T/P#2T/L GIS 조작시험","2022-04-21 10:00","2022-04-21 18:00","2022-04-21 10:00","2022-04-21 18:00","연속"]
[256,"강원","강릉","강릉횡계#2 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 154kV 강릉횡계#2 No.11~36 피뢰기 설치공사","2022-04-04 08:00","2022-04-06 18:00","2022-04-04 08:00","2022-04-06 18:00","매일"]
[257,"강원","강릉","강릉횡계#1 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 동해-강릉T/L No.55~67 안전을 위한 병가구간 휴전","2022-04-07 08:00","2022-04-08 18:00","2022-04-07 08:00","2022-04-08 18:00","매일"]
[258,"강원","강릉","동해강릉 T/L","154kV 강릉T/L No.28-32 안전이격거리 확보공사","○ 철탑 신설 3기, 철거 3기, 전력선교체 No.28-32, OPGW교체 No.28-32, 애자금구류 교체 및 피뢰기 설치 No.29,30,31","2022-04-01 07:00","2022-04-11 18:00","2022-04-01 07:00","2022-04-11 18:00","연속"]
[259,"강원","강릉","강릉영동TP T/L","154kV 강릉T/L No.28-32 안전이격거리 확보공사","○ 철탑 신설 3기, 철거 3기, 전력선교체 No.28-32, OPGW교체 No.28-32, 애자금구류 교체 및 피뢰기 설치 No.29,30,31","2022-04-01 07:00","2022-04-13 18:00","2022-04-01 07:00","2022-04-13 18:00","연속"]
[260,"강원","동해","동해영동TP T/L","22~23년 동해전력지사 변전정비 총액공사","1. 차단부 점검 및 교체","2022-04-25 09:00","2022-04-29 18:00","2022-04-25 09:00","2022-04-29 18:00","연속"]
[261,"강원","동해","이원도계 T/L","22~23년 동해전력지사 변전정비 총액공사","1. GIS 보통점검 2. LA 보통점검","2022-04-12 09:00","2022-04-12 18:00","2022-04-12 09:00","2022-04-12 18:00","연속"]
[262,"강원","동해","동해이원#2 T/L","22~23년 동해전력지사 변전정비 총액공사","1. GIS 보통점검 2. LA 보통점검[이원S/S] 3. LA 보통점검[동해S/S]","2022-04-14 09:00","2022-04-14 18:00","2022-04-14 09:00","2022-04-14 18:00","연속"]
[263,"강원","동해","이원삼척 T/L","22~23년 동해전력지사 변전정비 총액공사","1. GIS 보통점검 2. LA 보통점검 [이원S/S] 3. LA 보통점검 [삼척S/S]","2022-04-11 09:00","2022-04-11 18:00","2022-04-11 09:00","2022-04-11 18:00","연속"]
[264,"강원","동해","동해이원#1 T/L","22~23년 동해전력지사 변전정비 총액공사","1. GIS 보통점검 2. LA 보통점검","2022-04-15 09:00","2022-04-15 18:00","2022-04-15 09:00","2022-04-15 18:00","연속"]
[265,"강원","원주","상남인제#1 T/L","2022년 원주전력지사 변전협력회사 총액공사","장기미동작 차단기 시험","2022-04-26 10:00","2022-04-26 18:00","2022-04-26 10:00","2022-04-26 18:00","연속"]
[266,"강원","원주","홍천상남#1 T/L","2022년 원주전력지사 변전협력회사 총액공사","장기미동작 차단기 시험","2022-04-29 10:00","2022-04-29 18:00","2022-04-29 10:00","2022-04-29 18:00","연속"]
[267,"강원","원주","홍천상남#2 T/L","2022년 원주전력지사 변전협력회사 총액공사","장기미동작 차단기 시험 피뢰기 보통점검","2022-04-28 10:00","2022-04-28 18:00","2022-04-28 10:00","2022-04-28 18:00","연속"]
[268,"강원","원주","상남인제#2 T/L","2022년 원주전력지사 변전협력회사 총액공사","장기미동작 차단기 시험 피뢰기 교체","2022-04-27 10:00","2022-04-27 18:00","2022-04-27 10:00","2022-04-27 18:00","연속"]
[269,"강원","원주","북원주횡성#1 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 보통점검, 월붓싱 커버설치","2022-04-11 10:00","2022-04-11 18:00","2022-04-11 10:00","2022-04-11 18:00","연속"]
[270,"강원","직할","남춘천춘천열병합#1 T/L","154kV 남춘천S/S 외장재 교체공사","드라이비트 철거 후 메탈판넬 및 AL시트 설치","2022-04-18 08:00","2022-04-26 18:00","2022-04-18 08:00","2022-04-26 18:00","연속"]
[271,"강원","직할","신양양인제#2 T/L","피뢰기 및 추락방지장치 설치공사_직할","신양양-인제#1,2 T/L No.30~131 (동시휴전) 피뢰기 설치 306set, 추락방지장치 설치 102기, 아킹혼철거 802set","2022-04-06 08:00","2022-04-25 18:00","2022-04-06 08:00","2022-04-25 18:00","매일"]
[272,"강원","직할","신양양인제#1 T/L","피뢰기 및 추락방지장치 설치공사_직할","신양양-인제#1,2 T/L No.30~131 (동시휴전) 피뢰기 설치 306set, 추락방지장치 설치 102기, 아킹혼철거 802set","2022-04-06 08:00","2022-04-25 18:00","2022-04-06 08:00","2022-04-25 18:00","매일"]
[273,"강원","직할","남춘천춘천 T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","154kV 남춘천-춘천T/L 용량증대 전선교체 : 45C-km","2022-04-18 08:00","2022-07-29 18:00","2022-04-18 08:00","2022-07-29 18:00","연속"]
[274,"강원","직할","북춘천화천HP T/L","화천HP 154kV 가평-화천HP T/L GCB 대체공사","- 화천HP 154kV 가평-화천HP T/L GCB 대체공사(인근선로 휴전)","2022-04-11 10:00","2022-04-12 18:00","취소","취소","연속"]
[275,"강원","직할","화천H/P #2 BUS","화천HP 154kV 가평-화천HP T/L GCB 대체공사","- 화천HP 154kV 가평-화천HP T/L GCB 대체공사","2022-04-11 10:00","2022-04-12 18:00","취소","취소","연속"]
[276,"강원","직할","북춘천화천HP T/L","화천HP 154kV 가평-화천HP T/L GCB 대체공사","- 화천HP 154kV 가평-화천HP T/L GCB 대체공사(인근선로 휴전)","2022-04-04 10:00","2022-04-07 18:00","취소","취소","연속"]
[277,"강원","직할","화천H/P #2 BUS","화천HP 154kV 가평-화천HP T/L GCB 대체공사","- 화천HP 154kV 가평-화천HP T/L GCB 대체공사","2022-04-04 10:00","2022-04-07 18:00","취소","취소","연속"]
[278,"강원","직할","가평화천HP T/L","화천HP 154kV 가평-화천HP T/L GCB 대체공사","- 화천HP 154kV 가평-화천HP T/L GCB 대체공사","2022-04-04 10:00","2022-04-15 18:00","취소","취소","연속"]
[279,"강원","직할","화천화천HP#1 T/L","피뢰기 및 추락방지장치 설치공사","수평추락방지장치 설치 5(기)","2022-04-08 08:00","2022-04-08 18:00","취소","취소","연속"]
[280,"강원","직할","화천화천HP#2 T/L","피뢰기 및 추락방지장치 설치공사","수평추락방지장치 설치 5(기)","2022-04-01 08:00","2022-04-01 18:00","취소","취소","연속"]
[281,"강원","직할","철원화천#1 T/L","피뢰기 및 추락방지장치 설치공사","수평추락방지장치 51(기)","2022-04-02 08:00","2022-04-08 18:00","취소","취소","매일"]
[282,"강원","태백","도계태백 T/L","22-23년 태백전력지사 변전협력회사 총액공사","태백S/S 154kV 도계-태백T/L GIS 보통점검 [병행]태백S/S 154kV 도계-태백T/L LA교체(04/28 ~ 04/29)","2022-04-28 10:00","2022-04-29 18:00","2022-04-28 10:00","2022-04-28 10:00","연속"]
[283,"강원","태백","이원태백 T/L","22-23년 태백전력지사 변전협력회사 총액공사","태백S/S 154kV 이원-태백T/L GIS 보통점검 [병행]태백S/S 154kV 이원-태백T/L LA교체(04/26 ~ 04/27)","2022-04-26 10:00","2022-04-27 18:00","2022-04-28 10:00","2022-04-28 10:00","연속"]
[284,"충북","직할","신진천오창#1 T/L","154㎸ 신충주-음성 등 3개 T/L 추락방지시설 설치공사","추락방지시설 설치 (총 146기)","2022-04-20 07:30","2022-04-21 18:00","2022-04-20 07:30","2022-04-21 18:00","매일"]
[285,"충북","직할","신진천진천#2 T/L","154㎸ 신충주-음성 등 3개 T/L 추락방지시설 설치공사","추락방지시설 설치 (총 146기)","2022-04-20 07:30","2022-04-21 18:00","2022-04-20 07:30","2022-04-21 18:00","매일"]
[286,"충북","직할","신진천오창#2 T/L","154㎸ 신충주-음성 등 3개 T/L 추락방지시설 설치공사","추락방지시설 설치 (총 146기)","2022-04-18 07:30","2022-04-19 18:00","2022-04-18 07:30","2022-04-19 18:00","매일"]
[287,"충북","직할","신진천진천#1 T/L","154㎸ 신충주-음성 등 3개 T/L 추락방지시설 설치공사","추락방지시설 설치 (총 146기)","2022-04-18 07:30","2022-04-19 18:00","2022-04-18 07:30","2022-04-19 18:00","매일"]
[288,"충북","청주","남청주청주#3 T/L","154kV 남청주-청주T/L 정밀점검","2022년 가공송전 순시점검 위탁공사 154kV 남청주-청주T/L No.1~88 정밀점검","2022-04-18 09:00","2022-04-26 18:00","2022-04-18 09:00","2022-04-26 18:00","매일"]
[289,"충북","청주","남청주청주#2 T/L","154kV 남청주-청주T/L 정밀점검","2022년 가공송전 순시점검 위탁공사 154kV 남청주-청주T/L No.1~88 정밀점검","2022-04-27 09:00","2022-05-06 18:00","2022-04-27 09:00","2022-05-06 18:00","매일"]
[290,"충북","청주","남청주청주#4 T/L","154kV 남청주-청주T/L 정밀점검","2022년 가공송전 순시점검 위탁공사 154kV 남청주-청주T/L No.1~88 정밀점검","2022-04-27 09:00","2022-05-06 18:00","2022-04-27 09:00","2022-05-06 18:00","매일"]
[291,"충북","청주","남청주청주#1 T/L","154kV 남청주-청주T/L 정밀점검","2022년 가공송전 순시점검 위탁공사 154kV 남청주-청주T/L No.1~88 정밀점검","2022-04-18 09:00","2022-04-26 18:00","2022-04-18 09:00","2022-04-26 18:00","매일"]
[292,"충북","청주","옥천보은 T/L","송전 추락방지시설 설치공사","1. 공 사 명 : 154kV 남청주-청주 등 4개T/L 추락방지시설 설치공사 2. 공사장소 : 154kV 신옥천-옥천T/L No.24~36(13기) [병가선로 154kV 상주-보은T/L No.1~13] 3. 공사내역 : 수평 추락방지시설 설치","2022-04-19 08:00","2022-04-20 18:00","2022-04-19 08:00","2022-04-20 18:00","매일"]
[293,"충북","청주","신옥천S/S SEC CB 65660","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-12 10:00","2022-04-12 18:00","2022-04-12 10:00","2022-04-12 18:00","연속"]
[294,"충북","청주","신옥천S/S SEC CB 61620","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-13 10:00","2022-04-13 18:00","2022-04-13 10:00","2022-04-13 18:00","연속"]
[295,"충북","청주","신옥천S/S SEC CB 66670","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-14 10:00","2022-04-14 18:00","2022-04-14 10:00","2022-04-14 18:00","연속"]
[296,"충북","청주","신옥천S/S SEC CB 60610","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-11 10:00","2022-04-11 18:00","2022-04-11 10:00","2022-04-11 18:00","연속"]
[297,"충북","청주","신옥천용운#2 T/L","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-08 10:00","2022-04-08 18:00","2022-04-08 10:00","2022-04-08 18:00","연속"]
[298,"충북","청주","신옥천용운#1 T/L","170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-07 10:00","2022-04-07 18:00","2022-04-07 10:00","2022-04-07 18:00","연속"]
[299,"충북","청주","신옥천옥천#2 T/L","송전 추락방지시설 설치공사","1. 공 사 명 : 154kV 남청주-청주 등 4개T/L 추락방지시설 설치공사 2. 공사장소 : 154kV 신옥천-옥천T/L No.24~36(13기) 3. 공사내역 : 수평 추락방지시설 설치","2022-04-19 08:00","2022-04-20 18:00","2022-04-19 08:00","2022-04-20 18:00","매일"]
[300,"충북","청주","신옥천S/S CB 6300","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-27 10:00","2022-04-27 18:00","2022-04-27 10:00","2022-04-27 18:00","연속"]
[301,"충북","청주","신옥천S/S CB 6200","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-26 10:00","2022-04-26 18:00","2022-04-26 10:00","2022-04-26 18:00","연속"]
[302,"충북","청주","신옥천유천 T/L","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-21 10:00","2022-04-21 18:00","2022-04-21 10:00","2022-04-21 18:00","연속"]
[303,"충북","청주","신옥천옥천#1 T/L","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-18 10:00","2022-04-18 18:00","2022-04-18 10:00","2022-04-18 18:00","연속"]
[304,"충북","청주","신옥천서대전 T/L","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-20 10:00","2022-04-20 18:00","2022-04-20 10:00","2022-04-20 18:00","연속"]
[305,"충북","청주","신옥천S/S CB 6100","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-04-25 10:00","2022-04-25 18:00","2022-04-25 10:00","2022-04-25 18:00","연속"]
[306,"충북","청주","남청주오송#2 T/L","송전 추락방지시설 설치공사","1. 공 사 명 : 154kV 남청주-청주 등 4개T/L 추락방지시설 설치공사 2. 공사장소 : 154kV 남청주-오송T/L No.1~56 3. 공사내역 : 수평 추락방지시설 설치","2022-04-04 07:00","2022-04-08 18:00","2022-04-04 07:00","2022-04-08 18:00","매일"]
[307,"충북","청주","남청주오송#1 T/L","송전 추락방지시설 설치공사","1. 공 사 명 : 154kV 남청주-청주 등 4개T/L 추락방지시설 설치공사 2. 공사장소 : 154kV 남청주-오송T/L No.1~56 3. 공사내역 : 수평 추락방지시설 설치","2022-04-11 07:00","2022-04-15 18:00","2022-04-11 07:00","2022-04-15 18:00","매일"]
[308,"충북","충주","감곡가남#1 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","감곡-가남#1,2T/L 정밀점검","2022-04-25 07:30","2022-04-26 18:00","취소","취소","매일"]
[309,"충북","충주","감곡가남#2 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","감곡-가남#1,2T/L 정밀점검","2022-04-04 07:30","2022-04-05 18:00","취소","취소","매일"]
[310,"충북","충주","신제천제천#2 T/L","22-23년 충주전력지사 변전협력회사 총액공사","신제천-제천#2T/L LA 대체","2022-04-04 09:00","2022-04-04 18:00","2022-04-04 09:00","2022-04-04 18:00","연속"]
[311,"충북","신충주","신충주음성#2 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주음성#2T/L 정밀점검, 주말제외 ","2022-04-06 07:30","2022-04-15 18:00","2022-04-06 07:30","2022-04-15 18:00","매일"]
[312,"충북","신충주","신충주음성#1 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주음성#1T/L 정밀점검, 주말제외 ","2022-04-27 07:30","2022-05-05 18:00","2022-04-27 07:30","2022-05-05 18:00","매일"]
[313,"충북","신충주","신충주감곡#2 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주감곡#2T/L 정밀점검, 주말제외","2022-04-25 07:30","2022-05-05 18:00","2022-04-25 07:30","2022-05-05 18:00","매일"]
[314,"충북","신충주","신충주감곡#1 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주감곡#1T/L 정밀점검, 주말제외","2022-04-04 07:30","2022-04-15 18:00","2022-04-04 07:30","2022-04-15 18:00","매일"]
[315,"대전세종충남","대전","금산무주#2 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 추부-금산#2T/L 추락방지시설 설치공사 안전거리 확보차","2022-04-19 08:00","2022-04-20 18:00","취소","취소","매일"]
[316,"대전세종충남","대전","신계룡두마#2 T/L","[송전]345kV 신옥천-청양 등 2개T/L 추락방지시설 설치공사","[송전] 345kV 신계룡-청양T/L 안전거리확보차","2022-04-20 08:00","2022-04-20 18:00","2022-04-20 08:00","2022-04-20 18:00","연속"]
[317,"대전세종충남","대전","신계룡두마#1 T/L","[송전]345kV 신옥천-청양 등 2개T/L 추락방지시설 설치공사","[송전] 345kV 신옥천-청양T/L 안전거리확보차","2022-04-21 08:00","2022-04-21 18:00","2022-04-21 08:00","2022-04-21 18:00","연속"]
[318,"대전세종충남","대전","추부금산#2 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 추부-금산#2T/L 추락방지시설 설치공사","2022-04-06 08:00","2022-04-20 18:00","취소","취소","매일"]
[319,"대전세종충남","대전","추부금산#1 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 추부-금산#1T/L 추락방지시설 설치공사","2022-04-25 08:00","2022-05-11 18:00","취소","취소","매일"]
[320,"대전세종충남","서산","당진S/S SEC CB 60610","22년 서산P/O 변전협력회사 총액공사","당진S/S 154kV #60-#61 SEC CB 하자점검","2022-04-15 09:00","2022-04-15 18:00","취소","취소","연속"]
[321,"대전세종충남","서산","당진S/S CB 6100","22년 서산P/O 변전협력회사 총액공사","당진S/S 154kV #6100 BUS TIE CB 하자점검","2022-04-12 09:00","2022-04-12 18:00","취소","취소","연속"]
[322,"대전세종충남","서산","당진S/S CB 6300","22년 서산P/O 변전협력회사 총액공사","당진S/S 154kV 6300 T-BUS TIE CB 하자점검","2022-04-07 09:00","2022-04-07 18:00","취소","취소","연속"]
[323,"대전세종충남","서산","당진S/S CB 6200","22년 서산P/O 변전협력회사 총액공사","당진S/S 154kV 6200 TIE CB 하자점검","2022-04-06 09:00","2022-04-06 18:00","취소","취소","연속"]
[324,"대전세종충남","서산","당진S/S SEC CB 65660","22년 서산P/O 변전협력회사 총액공사","당진S/S 154kV #65-#66 SEC CB 하자점검","2022-04-11 09:00","2022-04-11 18:00","취소","취소","연속"]
[325,"대전세종충남","서산","대산S/S SEC CB 60610","22년 서산P/O 변전협력회사 총액공사","대산S/S 154kV #60-#61 SEC CB 보통점검","2022-04-18 09:00","2022-04-18 18:00","취소","취소","연속"]
[326,"대전세종충남","서산","서산S/S #61 BUS","22년 서산P/O 154kV GIS 정밀점검공사","서산S/S 서산-성연T/L GIS (697) 정밀점검","2022-04-18 09:00","2022-04-19 18:00","2022-04-18 09:00","2022-04-19 18:00","연속"]
[327,"대전세종충남","서산","서산성연 T/L","22년 서산P/O 154kV GIS 정밀점검공사","서산S/S 서산-성연T/L GIS (697) 정밀점검","2022-04-18 09:00","2022-04-21 18:00","2022-04-16 09:00","2022-04-17 18:00","연속"]
[328,"대전세종충남","서산","서산S/S #66 BUS","22년 서산P/O 154kV GIS 정밀점검공사","서산S/S 서산-성연T/L GIS (697) 정밀점검","2022-04-20 09:00","2022-04-21 18:00","2022-04-20 09:00","2022-04-21 18:00","연속"]
[329,"대전세종충남","서산","서산S/S #60 BUS","22년 서산P/O 154kV GIS 정밀점검공사","서산S/S 서산-대산#4T/L GIS (657) 정밀점검","2022-04-25 09:00","2022-04-26 18:00","2022-04-25 09:00","2022-04-26 18:00","연속"]
[330,"대전세종충남","서산","서산대산#4 T/L","22년 서산P/O 154kV GIS 정밀점검공사","서산S/S 서산-대산#4T/L GIS (657) 정밀점검","2022-04-25 09:00","2022-04-28 18:00","2022-04-25 09:00","2022-04-28 18:00","연속"]
[331,"대전세종충남","서산","서산S/S #65 BUS","22년 서산P/O 154kV GIS 정밀점검공사","서산S/S 서산-대산#4T/L GIS (657) 정밀점검","2022-04-27 09:00","2022-04-28 18:00","2022-04-27 09:00","2022-04-28 18:00","연속"]
[332,"대전세종충남","서산","서산S/S CB 6100","22년 서산P/O 변전협력회사 총액공사","서산S/S 154kV 6100 BUS TIE CB 보통점검","2022-04-26 09:00","2022-04-26 18:00","2022-04-26 09:00","2022-04-26 18:00","연속"]
[333,"대전세종충남","서산","서산S/S #61 BUS","22년 서산P/O 154kV GIS 정밀점검공사","서산S/S 서산-대산T/L GIS (6A7) 정밀점검","2022-04-11 09:00","2022-04-12 18:00","2022-04-11 09:00","2022-04-12 18:00","연속"]
[334,"대전세종충남","서산","서산대산 T/L","22년 서산P/O 154kV GIS 정밀점검공사","서산S/S 서산-대산T/L GIS (6A7) 정밀점검","2022-04-11 09:00","2022-04-14 18:00","2022-04-11 09:00","2022-04-14 18:00","연속"]
[335,"대전세종충남","서산","서산S/S #66 BUS","22년 서산P/O 154kV GIS 정밀점검공사","서산S/S 서산-대산T/L GIS (6A7) 정밀점검","2022-04-13 09:00","2022-04-14 18:00","2022-04-13 09:00","2022-04-14 18:00","연속"]
[336,"대전세종충남","서산","석문당진화력#1 T/L","22년 서산P/O 변전협력회사 총액공사","석문S/S 154kV 석문-당진화력#1TL 617 CB 보통점검","2022-04-29 09:00","2022-04-29 18:00","2022-04-29 09:00","2022-04-29 18:00","연속"]
[337,"대전세종충남","서산","서산성연 T/L","22년 서산P/O 154kV GIS 정밀점검공사","성연S/S 서산-성연T/L GIS (627) 정밀점검","2022-04-04 09:00","2022-04-06 18:00","2022-04-02 09:00","2022-04-03 18:00","연속"]
[338,"대전세종충남","서산","합덕송악#2 T/L","22년 서산P/O 변전협력회사 총액공사","송악S/S 154kV 합덕-송악#2T/L 6B7 CB, LA 보통점검","2022-04-15 09:00","2022-04-15 18:00","2022-04-15 09:00","2022-04-15 18:00","연속"]
[339,"대전세종충남","서산","신당진S/S #65 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","신당진-당진#1T/L, #60-65BUS-TIE, #1M.Tr 2차 GIS 교체","2022-04-11 08:00","2022-04-12 13:00","2022-04-11 08:00","2022-04-12 13:00","연속"]
[340,"대전세종충남","서산","신당진서산#1 T/L","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -65BUS 무부하가압(종카바)","2022-04-12 12:00","2022-04-12 13:00","2022-04-12 12:00","2022-04-12 13:00","연속"]
[341,"대전세종충남","서산","신당진S/S CB 6100","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -BUS-TIE 교체","2022-04-11 08:00","2022-04-29 18:00","2022-04-11 08:00","2022-04-29 18:00","연속"]
[342,"대전세종충남","서산","신당진S/S #60 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -DS 6101, 641 철거,설치 -CB 6100, 647 설치","2022-04-12 13:00","2022-04-20 13:00","2022-04-12 13:00","2022-04-20 13:00","연속"]
[343,"대전세종충남","서산","신당진S/S #66 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -65BUS 무부하가압","2022-04-12 12:00","2022-04-12 13:00","2022-04-12 12:00","2022-04-12 13:00","연속"]
[344,"대전세종충남","서산","신당진서산#1 T/L","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 - #60BUS 무부하가압","2022-04-19 13:00","2022-04-20 13:00","2022-04-19 13:00","2022-04-20 13:00","연속"]
[345,"대전세종충남","서산","신당진S/S #61 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 - #60BUS 무부하가압","2022-04-19 13:00","2022-04-20 13:00","2022-04-19 13:00","2022-04-20 13:00","연속"]
[346,"대전세종충남","서산","신당진S/S #65 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 - DS 6102, 642 철거,설치","2022-04-20 13:00","2022-04-29 18:00","2022-04-20 13:00","2022-04-29 18:00","연속"]
[347,"대전세종충남","서산","신당진당진#1 T/L","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","#60-65BUS TIE, 신당진-당진#1T/L, #1M.Tr 2차 GIS 교체 -신당진-당진#1T/L 교체","2022-04-11 08:00","2022-04-29 18:00","2022-04-11 08:00","2022-04-29 18:00","연속"]
[348,"대전세종충남","서산","태안태안화력 T/L","22년 서산P/O 변전협력회사 총액공사","태안S/S 154kV 태안-태안화력T/L 637 CB 보통점검 및 LA 대체 태안T/P 154kV 태안-태안화력T/L 627 CB, LA, CVT 보통점검","2022-04-01 09:00","2022-04-01 18:00","2022-04-01 09:00","2022-04-01 18:00","연속"]
[349,"대전세종충남","세종","덕진S/S CB 6200","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-04-12 14:00","2022-04-12 18:00","취소","취소","연속"]
[350,"대전세종충남","세종","덕진S/S CB 6100","[변전]2022년 세종PO 변전협력회사 총액공사","170kV GIS 보통점검","2022-04-12 09:30","2022-04-12 14:00","취소","취소","연속"]
[351,"대전세종충남","세종","덕진S/S SEC CB 60610","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-04-14 09:30","2022-04-14 14:00","취소","취소","연속"]
[352,"대전세종충남","세종","덕진S/S SEC CB 65660","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-04-14 14:00","2022-04-14 18:00","취소","취소","연속"]
[353,"대전세종충남","세종","둔곡S/S SEC CB 60610","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-04-05 09:30","2022-04-05 14:00","취소","취소","연속"]
[354,"대전세종충남","세종","둔곡S/S SEC CB 65660","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-04-05 14:00","2022-04-05 18:00","취소","취소","연속"]
[355,"대전세종충남","세종","둔곡S/S CB 6100","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-04-11 09:30","2022-04-11 14:00","취소","취소","연속"]
[356,"대전세종충남","세종","둔곡S/S CB 6200","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-04-11 14:00","2022-04-11 18:00","취소","취소","연속"]
[357,"대전세종충남","세종","세종부강#1 T/L","154kV 세종분기T/L 건설공사","1. 구간 : (기설)154㎸ 부강-월산T/L No.17-19 ~ (신설)154㎸ 세종분기 T/L No.3(CH) 2. 선로길이 : 1.197㎞ (4C-0.507㎞, 2C-0.690㎞) 3. 지 지 물 : 4기(154kV용 4각철탑 2기, 154kV용 관형지지물 1기, 임시 철탑 1기)","2022-04-24 07:00","2022-04-28 18:00","취소","취소","매일"]
[358,"대전세종충남","세종","부강월산#1 T/L","154kV 세종분기T/L 건설공사","1. 구간 : (기설)154㎸ 부강-월산T/L No.17-19 ~ (신설)154㎸ 세종분기 T/L No.3(CH) 2. 선로길이 : 1.197㎞ (4C-0.507㎞, 2C-0.690㎞) 3. 지 지 물 : 4기(154kV용 4각철탑 2기, 154kV용 관형지지물 1기, 임시 철탑 1기)","2022-04-18 07:00","2022-04-23 18:00","2022-04-18 07:00","2022-04-23 18:00","연속"]
[359,"대전세종충남","세종","부강월산#2 T/L","154kV 세종분기T/L 건설공사","1. 구간 : (기설)154㎸ 부강-월산T/L No.17-19 ~ (신설)154㎸ 세종분기 T/L No.3(CH) 2. 선로길이 : 1.197㎞ (4C-0.507㎞, 2C-0.690㎞) 3. 지 지 물 : 4기(154kV용 4각철탑 2기, 154kV용 관형지지물 1기, 임시 철탑 1기)","2022-04-18 07:00","2022-04-22 18:00","취소","취소","매일"]
[360,"대전세종충남","세종","부강월산#2 T/L","154kV 세종분기T/L 건설공사","1. 구간 : (기설)154㎸ 부강-월산T/L No.17-19 ~ (신설)154㎸ 세종분기 T/L No.3(CH) 2. 선로길이 : 1.197㎞ (4C-0.507㎞, 2C-0.690㎞) 3. 지 지 물 : 4기(154kV용 4각철탑 2기, 154kV용 관형지지물 1기, 임시 철탑 1기)","2022-04-24 07:00","2022-04-29 18:00","2022-04-24 07:00","2022-04-29 18:00","연속"]
[361,"대전세종충남","세종","세종S/S #66 BUS","세종S/S 154kV 네이버#1,2T/L GIS 증설","154kV 네이버#2T/L GIS 설치","2022-04-13 14:00","2022-04-15 18:00","2022-04-13 14:00","2022-04-15 18:00","연속"]
[362,"대전세종충남","세종","세종둔곡#1 T/L","세종S/S 154kV 네이버#1,2T/L GIS 증설","세종S/S 154kV 네이버#2T/L GIS 증설(#61BUS 무부하가압)","2022-04-12 14:00","2022-04-13 14:00","2022-04-12 14:00","2022-04-13 14:00","연속"]
[363,"대전세종충남","세종","세종S/S #61 BUS","세종S/S 154kV 네이버#1,2T/L GIS 증설","154kV 네이버#2T/L GIS 설치","2022-04-11 09:00","2022-04-13 14:00","2022-04-11 09:00","2022-04-13 14:00","연속"]
[364,"대전세종충남","세종","세종서세종#1 T/L","세종S/S 154kV 네이버#1,2T/L GIS 증설","세종S/S 154kV 네이버#1T/L GIS 설치(#65BUS 무부하가압)","2022-04-07 18:00","2022-04-08 18:00","2022-04-07 18:00","2022-04-08 18:00","연속"]
[365,"대전세종충남","세종","세종S/S #65 BUS","세종S/S 154kV 네이버#1,2T/L GIS 증설","154kV 네이버#1T/L GIS 설치","2022-04-06 14:00","2022-04-08 18:00","2022-04-06 14:00","2022-04-08 18:00","연속"]
[366,"대전세종충남","세종","세종서세종#1 T/L","세종S/S 154kV 네이버#1,2T/L GIS 증설","세종S/S 154kV 네이버#1T/L GIS 설치(#60BUS 무부하가압)","2022-04-05 14:00","2022-04-06 14:00","2022-04-05 14:00","2022-04-06 14:00","연속"]
[367,"대전세종충남","세종","세종S/S #60 BUS","세종S/S 154kV 네이버#1,2T/L GIS 증설","154kV 네이버#1T/L GIS 설치","2022-04-04 09:00","2022-04-06 14:00","2022-04-04 09:00","2022-04-06 14:00","연속"]
[368,"대전세종충남","세종","세종월산#1 T/L","154kV 세종분기T/L 건설공사","1. 구간 : (기설)154㎸ 부강-월산T/L No.17-19 ~ (신설)154㎸ 세종분기 T/L No.3(CH) 2. 선로길이 : 1.197㎞ (4C-0.507㎞, 2C-0.690㎞) 3. 지 지 물 : 4기(154kV용 4각철탑 2기, 154kV용 관형지지물 1기, 임시 철탑 1기)","2022-04-24 07:00","2022-04-28 18:00","2022-04-24 07:00","2022-04-28 18:00","매일"]
[369,"대전세종충남","세종","세종둔곡#1 T/L","세종S/S 154kV 네이버#1,2T/L GIS 증설","세종S/S 154kV 네이버#2T/L GIS 증설(#66BUS 무부하가압)","2022-04-14 18:00","2022-04-15 18:00","2022-04-14 18:00","2022-04-15 18:00","연속"]
[370,"대전세종충남","세종","천안전의#2 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 보통점검","2022-04-15 09:30","2022-04-15 18:00","2022-04-15 09:30","2022-04-15 18:00","연속"]
[371,"대전세종충남","직할","대덕덕진#2 T/L","[송전] 철탑 추락방지장치 설치공사","○ 설치대상 : 154kV 대덕-덕진T/L No.1~14 (14기)","2022-04-18 08:00","2022-04-22 18:00","2022-04-18 08:00","2022-04-22 18:00","연속"]
[372,"대전세종충남","직할","대덕덕진#1 T/L","[송전] 철탑 추락방지장치 설치공사","○ 설치대상 : 154kV 대덕-덕진T/L No.1~14 (14기)","2022-04-18 08:00","2022-04-22 18:00","2022-04-18 08:00","2022-04-22 18:00","연속"]
[373,"대전세종충남","천안","둔포추팔#1 T/L","둔포SS 154kV 둔포-추팔#1,2T/L CB 개폐타임 측정","둔포SS 154kV 둔포-추팔#1,2T/L CB 개폐타임 측정","2022-04-01 09:00","2022-04-01 14:00","2022-04-06 09:00","2022-04-06 18:00","연속"]
[374,"대전세종충남","천안","둔포추팔#2 T/L","둔포SS 154kV 둔포-추팔#1,2T/L CB 개폐타임 측정","둔포SS 154kV 둔포-추팔#1,2T/L CB 개폐타임 측정","2022-04-01 14:00","2022-04-01 18:00","2022-04-07 09:00","2022-04-07 18:00","연속"]
[375,"대전세종충남","천안","서천안S/S #66 BUS","서천안S/S 154kV 65-66-2DS 가스누기 보수작업","서천안S/S 154kV 65-66-2DS 가스누기 보수작업","2022-04-19 09:00","2022-04-22 18:00","2022-04-12 09:00","2022-04-15 18:00","연속"]
[376,"대전세종충남","천안","서천안S/S SEC CB 65660","서천안S/S 154kV 65-66-2DS 가스누기 보수작업","서천안S/S 154kV 65-66-2DS 가스누기 보수작업","2022-04-19 09:00","2022-04-22 18:00","2022-04-12 09:00","2022-04-15 18:00","연속"]
[377,"대전세종충남","천안","신온양한샘#2 T/L","신온양S/S 154kV 신온양-한샘#2T/L 가스누기 보수작업","신온양S/S 154kV 신온양-한샘#2T/L 가스누기 보수작업","2022-04-04 09:00","2022-04-08 18:00","2022-04-04 09:00","2022-04-08 18:00","연속"]
[378,"대전세종충남","천안","신온양S/S #62 BUS","신온양S/S 154kV 신온양-한샘#2T/L 가스누기 보수작업","신온양S/S 154kV 신온양-한샘#2T/L 가스누기 보수작업","2022-04-04 09:00","2022-04-08 18:00","2022-04-04 09:00","2022-04-08 18:00","연속"]
[379,"대전세종충남","천안","아산예산#1 T/L","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-04-04 14:00","2022-04-05 14:00","취소","취소","연속"]
[380,"대전세종충남","천안","아산S/S #65 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-04-06 14:00","2022-04-06 15:00","취소","취소","연속"]
[381,"대전세종충남","천안","아산S/S #60 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-04-06 15:00","2022-04-06 16:00","취소","취소","연속"]
[382,"대전세종충남","천안","아산S/S #60 BUS","아산S/S 154kV 장기사용GIS 교체공사(5차분)","- 154kV GIS 2CCT, BUS PT 2조 철거 - 154kV GIS 1CCT, BUS PT 2조 설치","2022-04-07 09:00","2022-04-09 14:00","2022-04-04 09:00","2022-04-09 14:00","연속"]
[383,"대전세종충남","천안","아산인주#2 T/L","아산S/S 154kV 장기사용GIS 교체공사(5차분)","- 154kV GIS 2CCT, BUS PT 2조 철거 - 154kV GIS 1CCT, BUS PT 2조 설치","2022-04-07 09:00","2022-04-22 16:00","2022-04-04 09:00","2022-04-22 16:00","연속"]
[384,"대전세종충남","천안","아산S/S #3 Sh.C (CB 6379)","아산S/S 154kV 장기사용GIS 교체공사(5차분)","- 154kV GIS 2CCT, BUS PT 2조 철거 - 154kV GIS 1CCT, BUS PT 2조 설치","2022-04-07 09:00","2022-04-22 16:00","취소","취소","연속"]
[385,"대전세종충남","천안","아산S/S SEC CB 60610","아산S/S 154kV 장기사용GIS 교체공사(5차분)","- 154kV GIS 2CCT, BUS PT 2조 철거 - 154kV GIS 1CCT, BUS PT 2조 설치","2022-04-08 14:00","2022-04-09 14:00","2022-04-06 14:00","2022-04-07 14:00","연속"]
[386,"대전세종충남","천안","아산S/S #65 BUS","아산S/S 154kV 장기사용GIS 교체공사(5차분)","- 154kV GIS 2CCT, BUS PT 2조 철거 - 154kV GIS 1CCT, BUS PT 2조 설치","2022-04-09 14:00","2022-04-19 14:00","2022-04-07 14:00","2022-04-19 14:00","연속"]
[387,"대전세종충남","천안","아산S/S SEC CB 65660","아산S/S 154kV 장기사용GIS 교체공사(5차분)","- 154kV GIS 2CCT, BUS PT 2조 철거 - 154kV GIS 1CCT, BUS PT 2조 설치","2022-04-18 14:00","2022-04-19 14:00","2022-04-18 14:00","2022-04-19 14:00","연속"]
[388,"대전세종충남","천안","아산S/S #60 BUS","아산S/S 154kV 장기사용GIS 교체공사(5차분)","- 154kV GIS 2CCT, BUS PT 2조 철거 - 154kV GIS 1CCT, BUS PT 2조 설치","2022-04-19 14:00","2022-04-21 14:00","2022-04-19 14:00","2022-04-21 14:00","연속"]
[389,"대전세종충남","천안","아산S/S SEC CB 60610","아산S/S 154kV 장기사용GIS 교체공사(5차분)","- 154kV GIS 2CCT, BUS PT 2조 철거 - 154kV GIS 1CCT, BUS PT 2조 설치","2022-04-20 14:00","2022-04-21 14:00","2022-04-20 14:00","2022-04-21 14:00","연속"]
[390,"대전세종충남","천안","아산S/S #60 BUS","아산S/S 154kV 장기사용GIS 교체공사(5차분)","- 154kV GIS 2CCT, BUS PT 2조 철거 - 154kV GIS 1CCT, BUS PT 2조 설치","2022-04-22 14:00","2022-04-22 15:00","2022-04-22 14:00","2022-04-22 15:00","연속"]
[391,"대전세종충남","천안","아산S/S #65 BUS","아산S/S 154kV 장기사용GIS 교체공사(5차분)","- 154kV GIS 2CCT, BUS PT 2조 철거 - 154kV GIS 1CCT, BUS PT 2조 설치","2022-04-22 15:00","2022-04-22 16:00","2022-04-22 15:00","2022-04-22 16:00","연속"]
[392,"대전세종충남","천안","아산예산#1 T/L","154kV 예산S/S 미래화공사","예산S/S #3M.Tr 개조공사 관련(T/L 이설 및 GIS 무부하가압)","2022-04-25 09:00","2022-04-26 13:00","2022-04-25 09:00","2022-04-26 13:00","연속"]
[393,"대전세종충남","천안","인주불당#1 T/L","관내s/s 154kV 공압식 차단기 공기조작부점검및 보통점검","- 차단기 보통점검 - 공기조작부 메카니즘 점검 - 차단기 개폐타임측정및 기타작업","2022-04-19 09:00","2022-04-20 18:00","2022-04-26 09:00","2022-04-27 18:00","연속"]
[394,"대전세종충남","천안","인주불당#2 T/L","관내s/s 154kV 공압식 차단기 공기조작부점검및 보통점검","- 차단기 보통점검 - 공기조작부 메카니즘 점검 - 차단기 개폐타임측정및 기타작업","2022-04-21 09:00","2022-04-22 18:00","2022-04-28 09:00","2022-04-29 18:00","연속"]
[395,"대전세종충남","천안","한샘직산#2 T/L","[송전]154kV 한샘-둔포T/L 안전이격 확보공사","가. 철탑계탑 : 1기 [20호 : A2-15 -&gtA2-22] 나. 전력선 : 재사용 다. 가수전 : 가철주[B1-24] 1기(전선이동 포함) 라. 송전선로용 피뢰기 설치/철거 : 1기(20호) 마 OPGW 100mm2 x 1조 (전자제어파트 시행) 바. 기타 부대공사. 끝.","2022-04-13 07:00","2022-04-13 18:00","2022-04-13 07:00","2022-04-13 18:00","연속"]
[396,"대전세종충남","천안","한샘직산#2 T/L","[송전]154kV 한샘-둔포T/L 안전이격 확보공사","가. 철탑계탑 : 1기 [20호 : A2-15 -&gtA2-22] 나. 전력선 : 재사용 다. 가수전 : 가철주[B1-24] 1기(전선이동 포함) 라. 송전선로용 피뢰기 설치/철거 : 1기(20호) 마 OPGW 100mm2 x 1조 (전자제어파트 시행) 바. 기타 부대공사. 끝.","2022-04-16 07:00","2022-04-16 18:00","2022-04-16 07:00","2022-04-16 18:00","연속"]
[397,"대전세종충남","천안","한샘직산#1 T/L","[송전]154kV 한샘-둔포T/L 안전이격 확보공사","가. 철탑계탑 : 1기 [20호 : A2-15 -&gtA2-22] 나. 전력선 : 재사용 다. 가수전 : 가철주[B1-24] 1기(전선이동 포함) 라. 송전선로용 피뢰기 설치/철거 : 1기(20호) 마 OPGW 100mm2 x 1조 (전자제어파트 시행) 바. 기타 부대공사. 끝.","2022-04-14 07:00","2022-04-15 18:00","2022-04-14 07:00","2022-04-15 18:00","연속"]
[398,"대전세종충남","청양","관창대천#2 T/L","[송전] 154kV 관창-대천#2T/L 피뢰기 설치공사","154kV 관창-대천#2T/L 피뢰기 설치공사","2022-04-20 07:00","2022-04-22 18:00","2022-04-20 07:00","2022-04-22 18:00","매일"]
[399,"대전세종충남","청양","관창대천#1 T/L","154kV 관창-대천#1T/L 관련기기 점검","154kV 관창-대천#1T/L 관련기기 점검","2022-04-25 09:00","2022-04-25 18:00","2022-04-25 09:00","2022-04-25 18:00","연속"]
[400,"대전세종충남","청양","부여S/S SEC CB 65660","부여S/S BUS-SEC(65-66) 170kV GIS 하자점검","부여S/S BUS-SEC(65-66) 170kV GIS 하자점검","2022-04-06 09:00","2022-04-06 18:00","취소","취소","연속"]
[401,"대전세종충남","청양","부여S/S SEC CB 60610","부여S/S BUS-SEC(60-61) 170kV GIS 하자점검","부여S/S BUS-SEC(60-61) 170kV GIS 하자점검","2022-04-05 09:00","2022-04-05 18:00","취소","취소","연속"]
[402,"대전세종충남","청양","부여S/S CB 6100","부여S/S BUS-TIE(6100) 170kV GIS 하자점검","부여S/S BUS-TIE(6100) 170kV GIS 하자점검","2022-04-04 09:00","2022-04-04 18:00","취소","취소","연속"]
[403,"대전세종충남","청양","신서천대천#2 T/L","154kV 대천-서천#2T/L GIS 하자점검","154kV 대천-서천#2T/L GIS 하자점검","2022-04-28 09:00","2022-04-28 18:00","2022-04-28 09:00","2022-04-28 18:00","연속"]
[404,"대전세종충남","청양","신서천대천#1 T/L","154kV 대천-서천#1T/L GIS 하자점검","154kV 대천-서천#1T/L GIS 하자점검","2022-04-27 09:00","2022-04-27 18:00","2022-04-27 09:00","2022-04-27 18:00","연속"]
[405,"대전세종충남","청양","동군산장항#2 T/L","154kV 동군산-장항#2T/L 관련기기 점검","154kV 동군산-장항#2T/L 관련기기 점검","2022-04-29 09:00","2022-04-29 18:00","2022-04-29 09:00","2022-04-29 18:00","연속"]
[406,"대전세종충남","청양","청양관창#1 T/L","2022년 청양P/O 170kV GIS 정밀점검","2022년 청양P/O 170kV GIS 정밀점검","2022-04-04 09:00","2022-04-06 14:00","2022-04-04 09:00","2022-04-06 14:00","연속"]
[407,"대전세종충남","청양","청양관창#2 T/L","2022년 청양P/O 170kV GIS 정밀점검","2022년 청양P/O 170kV GIS 정밀점검","2022-04-06 14:00","2022-04-08 18:00","2022-04-06 14:00","2022-04-08 18:00","연속"]
[408,"대전세종충남","청양","청양신풍#1 T/L","2022년 청양P/O 170kV GIS 정밀점검","2022년 청양P/O 170kV GIS 정밀점검","2022-04-11 09:00","2022-04-13 14:00","2022-04-11 09:00","2022-04-13 14:00","연속"]
[409,"대전세종충남","청양","청양신풍#2 T/L","2022년 청양P/O 170kV GIS 정밀점검","2022년 청양P/O 170kV GIS 정밀점검","2022-04-13 14:00","2022-04-15 18:00","2022-04-13 14:00","2022-04-15 18:00","연속"]
[410,"전북","군산","군산S/S #60 BUS","군산S/S 장기사용 170kV GIS 대체공사1 (교체)","- 장기사용 GIS 대체","2022-04-06 16:00","2022-04-06 18:00","취소","취소","연속"]
[411,"전북","군산","군산영등#2 T/L","군산S/S 장기사용 170kV GIS 대체공사2 (대체)","- 장기사용 GIS 대체","2022-04-04 09:00","2022-04-22 18:00","취소","취소","연속"]
[412,"전북","군산","군산이리#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2022-04-23 07:00","2022-04-25 18:00","취소","취소","연속"]
[413,"전북","군산","군산영등#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2022-04-18 07:00","2022-04-25 18:00","취소","취소","연속"]
[414,"전북","군산","군산이리#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2022-04-02 07:00","2022-04-09 18:00","취소","취소","연속"]
[415,"전북","군산","군산영등#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2022-04-02 07:00","2022-04-07 18:00","취소","취소","연속"]
[416,"전북","군산","군산S/S #60 BUS","군산S/S 장기사용 170kV GIS 대체공사1 (교체)","- 장기사용 GIS 대체","2022-04-13 18:00","2022-04-22 18:00","취소","취소","연속"]
[417,"전북","군산","군산S/S CB 6100","군산S/S 장기사용 170kV GIS 대체공사1 (교체)","- 장기사용 GIS 대체","2022-04-04 09:00","2022-04-22 18:00","취소","취소","연속"]
[418,"전북","군산","군산S/S #66 BUS","군산S/S 장기사용 170kV GIS 대체공사2 (대체)","- 장기사용 GIS 대체","2022-04-04 09:00","2022-04-06 18:00","취소","취소","연속"]
[419,"전북","군산","군산S/S #65 BUS","군산S/S 장기사용 170kV GIS 대체공사1 (교체)","- 장기사용 GIS 대체","2022-04-22 16:00","2022-04-22 18:00","취소","취소","연속"]
[420,"전북","군산","군산S/S #60 BUS","군산S/S 장기사용 170kV GIS 대체공사1 (교체)","- 장기사용 GIS 대체","2022-04-22 16:00","2022-04-22 18:00","취소","취소","연속"]
[421,"전북","군산","군산S/S #66 BUS","군산S/S 장기사용 170kV GIS 대체공사1 (교체)","- 장기사용 GIS 대체","2022-04-22 16:00","2022-04-22 18:00","취소","취소","연속"]
[422,"전북","군산","군산S/S #61 BUS","군산S/S 장기사용 170kV GIS 대체공사1 (교체)","- 장기사용 GIS 대체","2022-04-22 16:00","2022-04-22 18:00","취소","취소","연속"]
[423,"전북","군산","군산이리#1 T/L","군산S/S 장기사용 170kV GIS 대체공사1 (교체)","- 장기사용 GIS 대체","2022-04-04 09:00","2022-04-22 18:00","취소","취소","연속"]
[424,"전북","군산","군산S/S #61 BUS","군산S/S 장기사용 170kV GIS 대체공사1 (교체)","- 장기사용 GIS 대체","2022-04-06 16:00","2022-04-06 18:00","취소","취소","연속"]
[425,"전북","군산","군산서군산#2 T/L","154kV 군산-서군산T/L 취약지지물 교체공사","기설철탑 철거 1기 신설철탑 건설 1기","2022-04-25 07:00","2022-04-27 18:00","취소","취소","연속"]
[426,"전북","군산","군산서군산#1 T/L","154kV 군산-서군산T/L 취약지지물 교체공사","기설철탑 철거 1기 신설철탑 건설 1기","2022-04-28 07:00","2022-04-29 18:00","취소","취소","연속"]
[427,"전북","군산","군산S/S #1 Sh.C (CB 6179)","군산S/S 장기사용 170kV GIS 대체공사1 (모선절체)","- 장기사용 GIS 대체 관련 모선절체용","2022-04-04 09:00","2022-04-22 18:00","취소","취소","연속"]
[428,"전북","군산","군산S/S CB 6300","군산S/S 장기사용 170kV GIS 대체공사1 (모선절체)","- 장기사용 GIS 대체 관련 모선절체용","2022-04-04 09:00","2022-04-22 18:00","취소","취소","연속"]
[429,"전북","군산","군산S/S #65 BUS","군산S/S 장기사용 170kV GIS 대체공사1 (교체)","- 장기사용 GIS 대체","2022-04-04 09:00","2022-04-06 18:00","취소","취소","연속"]
[430,"전북","군산","군산S/S #61 BUS","군산S/S 장기사용 170kV GIS 대체공사2 (대체)","- 장기사용 GIS 대체","2022-04-06 18:00","2022-04-13 18:00","취소","취소","연속"]
[431,"전북","군산","내초S/S 내초열병합#1 T/L CB","군산P/O 154kV 이상 차단기 점검공사","내초S/S 647 CB 보통점검","2022-04-26 09:00","2022-04-26 18:00","2022-04-26 09:00","2022-04-26 18:00","연속"]
[432,"전북","군산","동군산군산CC#2 T/L","군산P/O 154kV 이상 차단기 점검공사","동군산S/S 687 CB 보통점검","2022-04-12 09:00","2022-04-12 18:00","2022-04-12 09:00","2022-04-12 18:00","연속"]
[433,"전북","군산","동군산장항#1 T/L","군산P/O 154kV 이상 차단기 점검공사","동군산S/S 647 CB 보통점검","2022-04-27 09:00","2022-04-27 18:00","취소","취소","연속"]
[434,"전북","군산","동군산군산CC#1 T/L","군산P/O 154kV 이상 차단기 점검공사","동군산S/S 697 CB 보통점검","2022-04-13 09:00","2022-04-13 18:00","2022-04-13 09:00","2022-04-13 18:00","연속"]
[435,"전북","군산","서군산소룡#1 T/L","군산P/O 154kV 이상 차단기 점검공사","서군산S/S 637 CB 보통점검, 636 DS 점검 등","2022-04-06 09:00","2022-04-07 18:00","2022-04-06 09:00","2022-04-07 18:00","연속"]
[436,"전북","군산","팔봉봉동#2 T/L","154kV 왕궁S/S 건설공사","- 송전선보호반 교체(팔봉, 봉동S/S) * 4면 - 대국시험, 계통연계시험, 선로정수 - 무부하시험 및 사용전검사","2022-04-14 09:00","2022-04-22 18:00","취소","취소","연속"]
[437,"전북","군산","팔봉봉동#1 T/L","154kV 왕궁S/S 건설공사","- 송전선보호반 교체(팔봉, 봉동S/S) * 4면 - 대국시험, 계통연계시험, 선로정수 - 무부하시험 및 사용전검사","2022-04-04 09:00","2022-04-13 18:00","취소","취소","연속"]
[438,"전북","김제","신김제전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2022-04-04 08:00","2022-04-12 18:00","취소","취소","연속"]
[439,"전북","김제","신김제S/S #4 M.Tr","김제PO 154kV이상 차단기 조작시험","차단기 개폐시험","2022-04-29 10:00","2022-04-29 18:00","취소","취소","연속"]
[440,"전북","김제","신김제S/S #3 M.Tr","김제PO 154kV이상 차단기 조작시험","차단기 개폐시험","2022-04-28 10:00","2022-04-28 18:00","취소","취소","연속"]
[441,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2022-04-04 08:00","2022-04-12 18:00","취소","취소","연속"]
[442,"전북","김제","신김제전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2022-04-04 08:00","2022-04-12 18:00","취소","취소","연속"]
[443,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2022-04-04 09:00","2022-04-12 18:00","취소","취소","연속"]
[444,"전북","직할","남원임실#1 T/L","154kV 곡성-남원 등 2개T/L 피뢰기 설치공사","154kV 곡성-남원 등 2개 #1T/L 피뢰기 설치공사 - 154kV 남원-임실#1T/L No.1 ~ 83(84기), 252set","2022-04-25 09:00","2022-05-03 18:00","취소","취소","연속"]
[445,"전북","직할","신김제동전주#2 T/L","관내S/S 170kV 이상 차단기 점검공사","신김제-동전주#2T/L GIS 초기점검","2022-04-26 09:00","2022-04-26 18:00","2022-04-26 09:00","2022-04-26 18:00","연속"]
[446,"전북","직할","신김제동전주#1 T/L","관내S/S 170kV 이상 차단기 점검공사","신김제-동전주#1T/L GIS 초기점검","2022-04-25 09:00","2022-04-25 18:00","2022-04-25 09:00","2022-04-25 18:00","연속"]
[447,"전북","직할","동전주북전주#2 T/L","동전주S/S 장기사용 170kV GIS 교체공사(3차)","○ 동전주-북전주#2T/L GIS 교체","2022-04-04 09:00","2022-05-08 18:00","취소","취소","연속"]
[448,"전북","직할","무주용담수력 T/L","관내S/S 170kV 이상 차단기 점검공사","무주S/S 무주-용담수력T/L 차단기 보통점검","2022-04-19 09:00","2022-04-22 18:00","2022-04-19 09:00","2022-04-22 18:00","연속"]
[449,"전북","직할","금산무주#2 T/L","관내S/S 170kV 차단기 점검공사","관내S/S 170kV 차단기 점검공사","2022-04-01 09:00","2022-04-01 18:00","2022-04-01 09:00","2022-04-01 18:00","연속"]
[450,"전북","직할","북전주봉동#1 T/L","관내S/S 170kV 이상 차단기 점검공사","북전주S/S 북전주-봉동#1T/L 차단기 점검 공사","2022-04-28 09:00","2022-04-28 18:00","취소","취소","연속"]
[451,"전북","직할","북전주봉동#2 T/L","관내S/S 170kV 이상 차단기 점검공사","북전주S/S 북전주-봉동#2T/L 차단기 점검공사","2022-04-29 09:00","2022-04-29 18:00","취소","취소","연속"]
[452,"광주전남","순천","여수TP용성#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#1, 2T/L LA(A, B, C) 하자점검 여수화력S/Y 여수TP-용성#2T/L GIS 보통점검","2022-04-01 09:00","2022-04-01 14:00","취소","취소","연속"]
[453,"광주전남","순천","여수TP용성#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#1, 2T/L LA(A, B, C) 하자점검 여수화력S/Y 여수TP-용성#2T/L GIS 보통점검","2022-04-01 14:00","2022-04-01 18:00","취소","취소","연속"]
[454,"광주전남","강진","진도서제주#1 T/L (제2연계선 #1Pole) CB","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) #1 MonoPole 연차점검","2022-04-02 09:00","2022-04-11 18:00","2022-03-23 09:00","2022-03-28 18:00","연속"]
[455,"광주전남","강진","진도C/S #1 BUS","진도C/S 170kV GIS 증설공사(전문)","170kV GIS 50kA * 1CCT 증설","2022-04-02 09:00","2022-04-05 18:00","2022-04-02 09:00","2022-04-05 18:00","연속"]
[456,"광주전남","강진","진도진도CS#1 T/L","진도C/S 170kV GIS 증설공사(전문)","170kV GIS 50kA * 1CCT 증설 #1BUS 무부하가압","2022-04-02 09:00","2022-04-04 18:00","2022-04-02 09:00","2022-04-04 18:00","연속"]
[457,"광주전남","광주","담양김제 T/L","21년 철탑 추락방지장치 설치공사","154kV 담양-일곡T/L 4회선 철탑 추락방지장치 설치","2022-04-04 07:00","2022-04-08 18:00","2022-04-04 07:00","2022-04-08 18:00","매일"]
[458,"광주전남","광주","담양일곡#1 T/L","21년 철탑 추락방지장치 설치공사","154kV 담양-일곡T/L 수평 추락방지장치 설치(14기)","2022-04-04 07:00","2022-04-08 18:00","2022-04-04 07:00","2022-04-08 18:00","매일"]
[459,"광주전남","순천","여수T/P SEC CB 60610","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-04-04 09:00","2022-04-07 18:00","취소","취소","연속"]
[460,"광주전남","순천","여수T/P CB 6100","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-04-04 09:00","2022-04-07 18:00","취소","취소","연속"]
[461,"광주전남","순천","여수T/P SEC CB 65660","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-04-04 09:00","2022-04-07 18:00","취소","취소","연속"]
[462,"광주전남","직할","충장농성#1 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","농성SA 충장농성#1,2T/L GIS 초기점검 (즉시가압 가능)","2022-04-04 09:00","2022-04-04 14:00","2022-04-04 09:00","2022-04-04 14:00","연속"]
[463,"광주전남","직할","충장농성#2 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","농성SA 충장농성#1,2T/L GIS 초기점검 (즉시가압 가능)","2022-04-04 14:00","2022-04-04 18:00","2022-04-04 14:00","2022-04-04 18:00","연속"]
[464,"광주전남","광주","계림충장#1 T/L","22년 광주전력 변전협력회사 총액공사 (보통점검)","- 보통점검 - 즉시가압 불가","2022-04-05 09:00","2022-04-05 18:00","2022-04-05 09:00","2022-04-05 18:00","연속"]
[465,"광주전남","직할","매월화정#1 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","매월S/S 매월화정#1,2T/L GIS 보통점검 (즉시가압 가능)","2022-04-05 09:00","2022-04-05 14:00","취소","취소","연속"]
[466,"광주전남","직할","매월화정#2 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","매월S/S 매월화정#1,2T/L GIS 보통점검 (즉시가압 가능)","2022-04-05 14:00","2022-04-05 18:00","취소","취소","연속"]
[467,"광주전남","강진","진도C/S #2 BUS","진도C/S 170kV GIS 증설공사(전문)","170kV GIS 50kA * 1CCT 증설","2022-04-06 09:00","2022-04-11 18:00","2022-04-06 09:00","2022-04-11 18:00","연속"]
[468,"광주전남","광주","계림충장#2 T/L","22년 광주전력 변전협력회사 총액공사 (보통점검)","- 보통점검 - 즉시가압 불가","2022-04-06 09:00","2022-04-06 18:00","2022-04-06 09:00","2022-04-06 18:00","연속"]
[469,"광주전남","직할","농성화정#1 T/L","2022~23년 광주전남본부 직할 변전협력회사 총액공사","화정-농성 #1,2T/L 장기미동작 차단기 점검","2022-04-06 09:00","2022-04-06 18:00","2022-04-06 09:00","2022-04-06 18:00","연속"]
[470,"광주전남","강진","진도진도CS#2 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","진도S/S, 진도C/S 진도-진도C/S #2T/L GIS 보통점검(비상시 20분이내 가압 가능)","2022-04-06 10:00","2022-04-06 18:00","2022-04-06 10:00","2022-04-06 18:00","연속"]
[471,"광주전남","직할","수완흑석#2 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","수완S/S 수완흑석#2T/L GIS 보통점검 (즉시가압 가능)","2022-04-07 09:00","2022-04-07 18:00","2022-04-07 09:00","2022-04-07 18:00","연속"]
[472,"광주전남","순천","여수TP화치#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 여수TP-화치#1, 2T/L GIS 보통점검 화치S/S 여수TP-화치#1, 2T/L GIS CB 타임측정","2022-04-08 09:00","2022-04-08 14:00","취소","취소","연속"]
[473,"광주전남","순천","여수TP화치#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 여수TP-화치#1, 2T/L GIS 보통점검 화치S/S 여수TP-화치#1, 2T/L GIS CB 타임측정","2022-04-08 14:00","2022-04-08 18:00","취소","취소","연속"]
[474,"광주전남","강진","진도진도CS#1 T/L","진도C/S 170kV GIS 증설공사(전문)","170kV GIS 50kA * 1CCT 증설 #2BUS 무부하가압","2022-04-10 09:00","2022-04-11 18:00","2022-04-10 09:00","2022-04-11 18:00","연속"]
[475,"광주전남","목포","엄다무안햇빛#1 T/L","154kV 엄다-운남T/L 용량증대 전선교체공사","ㅇ 목적 : 신안지역 신재생발전 계통 연계를 위하여 송전선로 설비보강 시행 ㅇ 공사개요 - ACSR/AW 330㎟에서 ASCC/TW 430㎟로 용량증대 전선교체 - 엄다S/S 구내 C/T철탑 개조","2022-04-15 09:00","2022-05-19 18:00","2022-04-15 09:00","2022-05-19 18:00","연속"]
[476,"광주전남","광주","정공담양 T/L","21년 철탑추락방지장치 설치공사","154kV 담양-일곡T/L 4회선 철탑 수평추락방지장치 설치","2022-04-11 07:00","2022-04-15 18:00","2022-04-11 07:00","2022-04-15 18:00","매일"]
[477,"광주전남","광주","담양일곡#2 T/L","21년 철탑 추락방지장치 설치공사","154kV 담양-일곡T/L 수평 추락방지장치 설치(14기)","2022-04-11 07:00","2022-04-15 18:00","2022-04-11 07:00","2022-04-15 18:00","매일"]
[478,"광주전남","순천","여수T/P SEC CB 65660","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #61-66 BUS-Pro 보호반 대체","2022-04-11 09:00","2022-04-14 18:00","취소","취소","연속"]
[479,"광주전남","순천","여수T/P CB 6200","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #61-66 BUS-Pro 보호반 대체","2022-04-11 09:00","2022-04-14 18:00","취소","취소","연속"]
[480,"광주전남","순천","여수T/P SEC CB 60610","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #61-66 BUS-Pro 보호반 대체","2022-04-11 09:00","2022-04-14 18:00","취소","취소","연속"]
[481,"광주전남","광주","계림승주#1 T/L","154kV 계림-승주T/L 안전이격확보공사","154kV 계림-승주T/L 안전이격확보공사","2022-04-14 07:00","2022-04-15 18:00","2022-04-14 07:00","2022-04-15 18:00","연속"]
[482,"광주전남","순천","여천여수#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여천-여수#1T/L GIS 보통점검 여천S/S 여천-여수#2T/L GIS CB 티임측정","2022-04-15 09:00","2022-04-15 14:00","2022-04-15 09:00","2022-04-15 14:00","연속"]
[483,"광주전남","순천","여천여수#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여천-여수#1T/L GIS 보통점검 여천S/S 여천-여수#2T/L GIS CB 티임측정","2022-04-15 14:00","2022-04-15 18:00","2022-04-15 14:00","2022-04-15 18:00","연속"]
[484,"광주전남","광주","계림승주#2 T/L","154kV 계림-승주T/L 안전이격확보공사","154kV 계림-승주T/L 안전이격확보공사","2022-04-16 07:00","2022-04-23 18:00","2022-04-16 07:00","2022-04-23 18:00","연속"]
[485,"광주전남","광주","신화순화순#1 T/L","21년 철탑 추락방지장치 설치공사","345kV 신광주-신화순T/L 4회선 철탑 추락방지장치 설치","2022-04-18 07:00","2022-04-22 18:00","취소","취소","매일"]
[486,"광주전남","순천","율촌여수산단#2 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","여수산단 율촌-여수산단 #2T/L #1DS 스페이서 부 가스누기 조치 율촌S/S 율촌-여수산단#2T/L GIS 보통점검","2022-04-18 09:00","2022-04-19 18:00","취소","취소","연속"]
[487,"광주전남","직할","농성화정#2 T/L","직할 170kV GIS 정밀점검공사","직할 170kV GIS 정밀점검공사","2022-04-18 09:00","2022-04-21 18:00","취소","취소","연속"]
[488,"광주전남","순천","율촌여수산단#1 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","여수산단 율촌-여수산단 #1T/L #1DS 스페이서 부 가스누기 조치 율촌S/S 율촌-여수산단#1T/L GIS 보통점검","2022-04-20 09:00","2022-04-21 18:00","취소","취소","연속"]
[489,"광주전남","순천","여수TP용성#1 T/L","대한제 열경화공법 EBG 보강공사","여수TP-용성#1 T/L EBG 해체점검(6상)","2022-04-21 09:00","2022-04-29 18:00","취소","취소","연속"]
[490,"광주전남","순천","승주서순천 T/L","22-23년 순천전력지사 변전협력회사 총액공사","서순천S/S 승주-서순천T/L GIS 보통점검 승주S/S 승주-서순천T/L LA(A, B, C) 하자점검","2022-04-22 09:00","2022-04-22 18:00","2022-04-22 09:00","2022-04-22 18:00","연속"]
[491,"광주전남","순천","여천여수산단#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여천-여수산단#1,2T/L GIS 보통점검","2022-04-22 09:00","2022-04-22 14:00","2022-04-22 09:00","2022-04-22 14:00","연속"]
[492,"광주전남","순천","여천여수산단#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여천-여수산단#1,2T/L GIS 보통점검","2022-04-22 14:00","2022-04-22 18:00","2022-04-22 14:00","2022-04-22 18:00","연속"]
[493,"광주전남","광주","계림승주#1 T/L","154kV 계림-승주T/L 안전이격확보공사","154kV 계림-승주T/L 안전이격확보공사","2022-04-24 07:00","2022-04-29 18:00","2022-04-24 07:00","2022-04-29 18:00","연속"]
[494,"광주전남","광주","신화순화순#2 T/L","21년 철탑 추락방지장치 설치공사","345kV 신광주-신화순T/L 4회선 철탑 추락방지장치 설치","2022-04-25 07:00","2022-04-29 18:00","취소","취소","매일"]
[495,"광주전남","광주","신광주일곡#2 T/L","154kV 신광주-일곡T/L 케이블타워 이설공사","ㅇ 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 ㅇ 전선교체 : ACSR 410㎟ X 2B(2회선), 0.360km - 임시선로 구성 : 임시철탑 1기, ACSR 410㎟ X 2B(2회선) 0.547km","2022-04-25 09:00","2022-04-27 18:00","취소","취소","연속"]
[496,"광주전남","순천","여천호남TP#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여천-호남TP#1, 2T/L GIS 보통점검","2022-04-27 09:00","2022-04-27 14:00","취소","취소","연속"]
[497,"광주전남","순천","여천호남TP#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여천-호남TP#1, 2T/L GIS 보통점검","2022-04-27 14:00","2022-04-27 18:00","취소","취소","연속"]
[498,"광주전남","광주","신광주일곡#1 T/L","154kV 신광주-일곡T/L 케이블타워 이설공사","ㅇ 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 ㅇ 전선교체 : ACSR 410㎟ X 2B(2회선), 0.360km - 임시선로 구성 : 임시철탑 1기, ACSR 410㎟ X 2B(2회선) 0.547km","2022-04-28 09:00","2022-04-29 18:00","취소","취소","연속"]
[499,"광주전남","순천","여수TP여천#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여수TP-여천#1, 2T/L GIS 보통점검","2022-04-28 09:00","2022-04-28 14:00","취소","취소","연속"]
[500,"광주전남","순천","여수TP여천#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여수TP-여천#1, 2T/L GIS 보통점검","2022-04-28 14:00","2022-04-28 18:00","취소","취소","연속"]
[501,"광주전남","순천","순천승주#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","승주S/S 순천-승주#1T/L LA(A, B, C) 보통점검","2022-04-29 09:00","2022-04-29 18:00","2022-04-29 09:00","2022-04-29 18:00","연속"]
[502,"대구","경산","경산S/S #1 EM.Tr CB","22~23년 경산PO 변전협력회사 총액공사","- M.Tr, 1,2차GIS, LA, NGR 보통점검","2022-04-06 09:30","2022-04-06 18:00","2022-04-06 09:30","2022-04-06 18:00","연속"]
[503,"대구","경산","대구범물#1 T/L","22~23년 경산PO 변전협력회사 총액공사","- GIS, LA 초기점검","2022-04-21 09:30","2022-04-21 14:00","2022-04-21 09:30","2022-04-21 14:00","연속"]
[504,"대구","경산","대구범물#2 T/L","22~23년 경산PO 변전협력회사 총액공사","- GIS, LA 초기점검","2022-04-21 14:00","2022-04-21 18:00","2022-04-21 14:00","2022-04-21 18:00","연속"]
[505,"대구","경산","청도밀양#2 T/L","청도S/S 154kV GIS 교체공사","154kV GIS 교체","2022-04-06 09:30","2022-04-29 18:00","2022-04-06 09:30","2022-04-29 18:00","연속"]
[506,"대구","달성","강창성서#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 다산-강창T/L 정밀점검 (강창-성서 병가선로)","2022-04-21 08:00","2022-04-21 17:00","2022-04-21 08:00","2022-04-21 17:00","연속"]
[507,"대구","달성","강창성서#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 다산-강창T/L 정밀점검 (강창-성서 병가선로)","2022-04-14 08:00","2022-04-14 17:00","2022-04-14 08:00","2022-04-14 17:00","연속"]
[508,"대구","달성","다산강창#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 다산-강창T/L 정밀점검","2022-04-11 08:00","2022-04-14 17:00","2022-04-11 08:00","2022-04-14 17:00","연속"]
[509,"대구","달성","다산강창#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 다산-강창T/L 정밀점검","2022-04-18 08:00","2022-04-21 17:00","2022-04-18 08:00","2022-04-21 17:00","연속"]
[510,"대구","달성","달성월배#2 T/L","GIS초기점검","GIS초기점검","2022-04-06 09:00","2022-04-06 18:00","2022-04-04 09:00","2022-04-04 18:00","연속"]
[511,"대구","달성","북대구팔달#1 T/L","팔달S/S 팔달-북대구#1T/L GIS보통점검","팔달S/S 팔달-북대구#1T/L GIS보통점검","2022-04-18 09:00","2022-04-18 18:00","2022-04-18 09:00","2022-04-18 18:00","연속"]
[512,"대구","달성","북대구팔달#2 T/L","팔달S/S 팔달-북대구#2T/L GIS보통점검","팔달S/S 팔달-북대구#2T/L GIS보통점검","2022-04-22 09:00","2022-04-22 18:00","2022-04-22 09:00","2022-04-22 18:00","연속"]
[513,"대구","직할","공평침산 T/L","공평S/S 170kV GIS 정밀점검","공평S/S 170kV GIS 정밀점검","2022-04-25 09:00","2022-04-27 18:00","2022-04-25 09:00","2022-04-27 18:00","연속"]
[514,"대구","직할","공평서침산 T/L","공평S/S 170kV GIS 정밀점검","공평S/S 170kV GIS 정밀점검","2022-04-18 09:00","2022-04-20 18:00","2022-04-18 09:00","2022-04-20 18:00","연속"]
[515,"대구","직할","남대구동인#1 T/L","남대구S/S 남대구-동인#1,2T/L 휴전관련 작업","남대구S/S 남대구-동인#1,2T/L 휴전관련 작업","2022-04-08 09:30","2022-04-08 14:00","2022-04-08 09:30","2022-04-08 14:00","연속"]
[516,"대구","직할","범물남대구#2 T/L","남대구S/S 범물-남대구#1,2T/L 휴전 관련 작업","남대구S/S 범물-남대구#1,2T/L 휴전 관련 작업","2022-04-07 14:00","2022-04-07 18:00","2022-04-07 14:00","2022-04-07 18:00","연속"]
[517,"대구","직할","범물남대구#1 T/L","남대구S/S 범물-남대구#1,2T/L 휴전 관련 작업","남대구S/S 범물-남대구#1,2T/L 휴전 관련 작업","2022-04-07 09:30","2022-04-07 14:00","2022-04-07 09:30","2022-04-07 14:00","연속"]
[518,"대구","직할","남대구동인#2 T/L","남대구S/S 남대구-동인#1,2T/L 휴전관련 작업","남대구S/S 남대구-동인#1,2T/L 휴전관련 작업","2022-04-08 14:00","2022-04-08 18:00","2022-04-08 14:00","2022-04-08 18:00","연속"]
[519,"대구","직할","효목안심#1 T/L","효목S/S 효목-안심#1,2T/L 휴전관련 작업","효목S/S 효목-안심#1,2T/L 휴전관련 작업","2022-04-14 09:30","2022-04-14 14:00","2022-04-14 09:30","2022-04-14 14:00","연속"]
[520,"대구","직할","시지효목#1 T/L","효목S/S 시지-효목#1,2T/L 휴전 관련 작업차","효목S/S 시지-효목#1,2T/L 휴전 관련 작업차","2022-04-15 09:30","2022-04-15 14:00","2022-04-15 09:30","2022-04-15 14:00","연속"]
[521,"대구","직할","시지효목#2 T/L","효목S/S 시지-효목#1,2T/L 휴전관련 작업차","효목S/S 시지-효목#1,2T/L 휴전관련 작업차","2022-04-15 14:00","2022-04-15 18:00","2022-04-15 14:00","2022-04-15 18:00","연속"]
[522,"대구","직할","효목안심#2 T/L","효목S/S 효목-안심#1,2T/L 휴전관련 작업","효목S/S 효목-안심#1,2T/L 휴전관련 작업","2022-04-14 14:00","2022-04-14 18:00","2022-04-14 14:00","2022-04-14 18:00","연속"]
[523,"대구","칠곡","남구미광평#2 T/L","광평S/S 남구미-광평 #2T/L GIS 정밀점검","광평S/S 남구미-광평 #2T/L GIS 정밀점검","2022-04-27 09:30","2022-04-28 18:00","2022-04-27 09:30","2022-04-28 18:00","연속"]
[524,"대구","칠곡","구미광평#1 T/L","광평S/S 구미-광평#1T/L GIS 보통점검","광평S/S 구미-광평#1T/L GIS 보통점검","2022-04-07 09:30","2022-04-07 14:00","2022-04-07 09:30","2022-04-07 14:00","연속"]
[525,"대구","칠곡","광평S/S CB 6100","광평S/S 154kV 6100 BUS-TIE GIS 보통점검","광평S/S 154kV 6100 BUS-TIE GIS 보통점검","2022-04-07 14:00","2022-04-07 18:00","2022-04-07 14:00","2022-04-07 18:00","연속"]
[526,"대구","칠곡","구미광평#2 T/L","광평S/S 남구미-광평 #2T/L GIS 정밀점검 무부하 가압","광평S/S 남구미-광평 #2T/L GIS 정밀점검 무부하 가압","2022-04-28 13:00","2022-04-28 18:00","2022-04-28 13:00","2022-04-28 18:00","연속"]
[527,"대구","칠곡","김천금릉#1 T/L","대한전선 열경화공법 EBG 보강공사","대한전선 열경화공법 EBG 가스채취밸브 설치공사(스프링유닛점검 포함) 154kV 김천-금릉T/L 김천S/S EBG 6상","2022-04-04 08:00","2022-04-06 18:00","취소","취소","연속"]
[528,"대구","칠곡","김천금릉#2 T/L","대한전선 열경화공법 EBG 보강공사","대한전선 열경화공법 EBG 가스채취밸브 설치공사(스프링유닛점검 포함) 154kV 김천-금릉T/L 김천S/S EBG 6상","2022-04-01 08:00","2022-04-03 18:00","취소","취소","연속"]
[529,"대구","칠곡","성주금릉#2 T/L","성주S/S 성주-금릉#2T/L CVT 초기점검, GIS 장기미동작점검","성주S/S 성주-금릉#2T/L CVT 초기점검, GIS 장기미동작점검","2022-04-28 09:30","2022-04-28 18:00","2022-04-28 09:30","2022-04-28 18:00","연속"]
[530,"대구","칠곡","어모S/S CB 6100","어모S/S 154kV 6100 BUS-TIE GIS 보통점검","어모S/S 154kV 6100 BUS-TIE GIS 보통점검","2022-04-29 14:00","2022-04-29 18:00","2022-04-29 14:00","2022-04-29 18:00","연속"]
[531,"대구","포항","입실양북 T/L","입실S/S 입실-양북T/L 677 GIS 보통점검","입실S/S 입실-양북T/L 677 GIS 보통점검","2022-04-12 09:00","2022-04-12 18:00","2022-04-12 09:00","2022-04-12 18:00","연속"]
[532,"대구","달성","달성월배#1 T/L","GIS초기점검","GIS초기점검","2022-04-05 09:00","2022-04-05 18:00","2022-04-05 09:00","2022-04-05 18:00","연속"]
[533,"경북","구미","남인동인동#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- LA 교체, PT 보통점검[남인동S/S] - GIS 조작시험[인동S/S]","2022-04-12 14:00","2022-04-12 18:00","2022-04-12 14:00","2022-04-12 14:00","연속"]
[534,"경북","구미","남인동인동#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- LA 교체, PT 보통점검[남인동S/S] - GIS 조작시험[인동S/S]","2022-04-12 09:00","2022-04-12 14:00","2022-04-12 14:00","2022-04-12 14:00","연속"]
[535,"경북","구미","동상주점촌#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- GIS 하자점검[동상주개폐소]","2022-04-20 09:00","2022-04-20 14:00","2022-04-20 09:00","2022-04-20 14:00","연속"]
[536,"경북","구미","동상주점촌#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- GIS 하자점검[동상주개폐소]","2022-04-20 14:00","2022-04-20 18:00","2022-04-20 14:00","2022-04-20 18:00","연속"]
[537,"경북","영주","점촌문경 T/L","22-23년 영주전력지사 변전협력회사 총액공사","점촌,문경S/S 점촌-문경T/L 보호반 대체 문경S/S 점촌-문경T/L LA 보통점검","2022-04-23 09:00","2022-04-24 18:00","2022-04-23 09:00","2022-04-24 18:00","연속"]
[538,"경북","영주","예천점촌#2 T/L","22-23년 영주전력지사 변전협력회사 총액공사","예천S/S 예천-점촌#2T/L 보통점검 계전기 성능개선","2022-04-08 09:00","2022-04-08 18:00","2022-04-08 09:00","2022-04-08 18:00","연속"]
[539,"경북","영주","예천점촌#1 T/L","22-23년 영주전력지사 변전협력회사 총액공사","예천S/S 예천-점촌#1T/L 보통점검 계전기 성능개선","2022-04-07 09:00","2022-04-07 18:00","2022-04-07 09:00","2022-04-07 18:00","연속"]
[540,"경북","직할","신영주안동#1 T/L","154kV 신영주-안동 등 4개 T/L 피뢰기 설치공사","154kV 신영주-안동 등 4개 T/L 피뢰기 설치공사","2022-04-08 09:00","2022-04-13 18:00","2022-04-04 09:00","2022-04-11 18:00","매일"]
[541,"경북","직할","영덕평해#2 T/L","154kV 신영주-안동 등 4개 T/L 피뢰기 설치공사","154kV 신영주-안동 등 4개 T/L 피뢰기 설치공사","2022-04-14 09:00","2022-04-25 18:00","2022-04-12 09:00","2022-04-25 18:00","매일"]
[542,"경북","직할","현종산풍력평해#2 T/L","154kV 신영주-안동 등 4개 T/L 피뢰기 설치공사","154kV 신영주-안동 등 4개 T/L 피뢰기 설치공사","2022-04-26 09:00","2022-04-29 18:00","2022-04-26 09:00","2022-04-29 18:00","매일"]
[543,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 647 GIS 정밀점검","서창S/S 647 GIS 정밀점검","2022-04-02 09:00","2022-04-03 18:00","2022-04-02 09:00","2022-04-03 18:00","연속"]
[544,"부산울산","동부산","서창산막#2 T/L","서창S/S 687GIS 정밀점검","서창S/S 687GIS 정밀점검","2022-04-16 09:00","2022-04-17 18:00","2022-04-16 09:00","2022-04-17 18:00","연속"]
[545,"부산울산","동부산","신양산S/S #60 BUS","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","2022-04-04 09:00","2022-04-06 18:00","2022-04-04 09:00","2022-04-06 18:00","연속"]
[546,"부산울산","동부산","신양산S/S #61 BUS","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","2022-04-07 09:00","2022-04-08 18:00","2022-04-07 09:00","2022-04-08 18:00","연속"]
[547,"부산울산","동부산","신양산S/S #66 BUS","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","2022-04-12 09:00","2022-04-14 18:00","2022-04-12 09:00","2022-04-14 18:00","연속"]
[548,"부산울산","동부산","신양산구서#2 T/L","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","신양산S/S 현대제 GIS 동부쉬 교체 및 조작로드 유압누유 발청조치","2022-04-06 09:00","2022-04-06 18:00","2022-04-06 09:00","2022-04-06 18:00","연속"]
[549,"부산울산","북부산","개금범천#2 T/L","22-23 북부산전력지사 변전 총액공사","개금S/S 154kV 개금-범천#2T/L 차단기 조작시험","2022-04-26 10:00","2022-04-26 18:00","2022-04-26 10:00","2022-04-26 18:00","연속"]
[550,"부산울산","북부산","개금범천#1 T/L","22-23 북부산전력지사 변전 총액공사","개금S/S 154kV 개금-범천#1T/L 차단기 조작시험","2022-04-25 10:00","2022-04-25 18:00","2022-04-25 10:00","2022-04-25 18:00","연속"]
[551,"부산울산","북부산","서창산막#1 T/L","22-23 북부산전력지사 변전 총액공사","산막S/S 154kV 서창-산막#1T/L 보호반 대체","2022-04-23 09:00","2022-04-24 18:00","2022-04-23 09:00","2022-04-24 18:00","연속"]
[552,"부산울산","북부산","서창산막#1 T/L","345kV 북부산-신울산T/L 81~84호간 지장철탑 이설공사","345kV 북부산-신울산T/L 81~84호간 지장철탑 이설공사 관련 안적이격확보차 (81-1호~81-2호간 연긴선 작업시 안전이격확보)","2022-04-09 08:00","2022-04-10 18:00","2022-04-09 08:00","2022-04-10 18:00","매일"]
[553,"부산울산","북부산","서창산막#2 T/L","345kV 북부산-신울산T/L 81~84호간 지장철탑 이설공사","345kV 북부산-신울산T/L 81~84호간 지장철탑 이설공사 관련 안적이격확보차 (81-1호~81-2호간 연긴선 작업시 안전이격확보)","2022-04-09 08:00","2022-04-10 18:00","2022-04-09 08:00","2022-04-10 18:00","매일"]
[554,"부산울산","북부산","북부산삼랑진PP T/L","154kV물금-삼랑진 등 3개T/L 추락방지장치설치공사 등","철탑추락방지장치 설치","2022-04-01 08:00","2022-04-05 18:00","2022-04-01 08:00","2022-04-05 18:00","연속"]
[555,"부산울산","북부산","양산삼랑진PP T/L","154kV물금-삼랑진 등 3개T/L 추락방지장치설치공사 등","철탑추락방지장치 설치","2022-04-06 08:00","2022-04-08 18:00","2022-04-06 08:00","2022-04-08 18:00","연속"]
[556,"부산울산","북부산","북부산양산 T/L","154kV물금-삼랑진 등 3개T/L 추락방지장치설치공사 등","철탑추락방지장치 설치","2022-04-02 08:00","2022-04-03 18:00","2022-04-02 08:00","2022-04-03 18:00","연속"]
[557,"부산울산","서부산","용원녹공#2 T/L","녹공S/S 154kV 용원-녹공#2T/L GIS 동작시험","녹공S/S 154kV 용원-녹공#2T/L GIS 동작시험","2022-04-09 09:00","2022-04-09 18:00","2022-04-09 09:00","2022-04-09 18:00","연속"]
[558,"부산울산","서부산","서부산다대#1 T/L","다대S/S 154kV 서부산-다대#1T/L GIS 동작시험","병행 : 서부산S/S 154kV 서부산-다대#1T/L GIS 동작시험","2022-04-11 09:00","2022-04-11 18:00","2022-04-11 09:00","2022-04-11 18:00","연속"]
[559,"부산울산","서부산","서부산다대#2 T/L","다대S/S 154kV 서부산-다대#2T/L GIS 동작시험","병행 : 서부산S/S 154kV 서부산-다대#2T/L GIS 동작시험","2022-04-12 09:00","2022-04-12 18:00","2022-04-12 09:00","2022-04-12 18:00","연속"]
[560,"부산울산","서부산","서부산엄궁#1 T/L","서부산S/S 154kV 서부산-엄궁#1T/L GIS 동작시험","서부산S/S 154kV 서부산-엄궁#1T/L GIS 동작시험","2022-04-21 09:00","2022-04-21 18:00","2022-04-21 09:00","2022-04-21 18:00","연속"]
[561,"부산울산","서부산","서부산엄궁#2 T/L","서부산S/S 154kV 서부산-엄궁#2T/L GIS 동작시험","서부산S/S 154kV 서부산-엄궁#2T/L GIS 동작시험","2022-04-22 09:00","2022-04-22 18:00","2022-04-22 09:00","2022-04-22 18:00","연속"]
[562,"부산울산","서부산","신김해지사#1 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 : 30~40호(11기)","2022-04-12 07:00","2022-04-14 18:00","2022-04-12 07:00","2022-04-14 18:00","연속"]
[563,"부산울산","서부산","신김해지사#2 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 : 30~40호, 피뢰기설치 : 38호","2022-04-19 07:00","2022-04-21 18:00","2022-04-19 07:00","2022-04-21 18:00","연속"]
[564,"부산울산","울산","남울산S/S SEC CB 66670","22~23년 변전협력회사 총액공사","- GIS 하자점검","2022-04-22 09:00","2022-04-22 18:00","2022-04-22 09:00","2022-04-22 18:00","연속"]
[565,"부산울산","울산","남울산S/S SEC CB 61620","22~23년 변전협력회사 총액공사","- GIS 하자점검","2022-04-21 09:00","2022-04-21 18:00","2022-04-21 09:00","2022-04-21 18:00","연속"]
[566,"부산울산","울산","남울산처용#2 T/L","22~23년 변전협력회사 총액공사","- GIS(6971, 6900) 하자점검","2022-04-12 09:00","2022-04-12 18:00","2022-04-12 09:00","2022-04-12 18:00","연속"]
[567,"부산울산","울산","남울산처용#1 T/L","22~23년 변전협력회사 총액공사","- GIS(6772, 6700) 하자점검","2022-04-11 09:00","2022-04-11 18:00","2022-04-11 09:00","2022-04-11 18:00","연속"]
[568,"부산울산","울산","남울산성암#1 T/L","22~23년 변전협력회사 총액공사","- 남울산측 : GIS(6672) 하자점검 - 성암측 : GIS(637) 하자점검","2022-04-06 09:00","2022-04-06 18:00","2022-04-06 09:00","2022-04-06 18:00","연속"]
[569,"부산울산","울산","남울산용연#1 T/L","22~23년 변전협력회사 총액공사","- GIS(6671,6600) 하자점검","2022-04-05 09:00","2022-04-05 18:00","2022-04-14 09:00","2022-04-14 18:00","연속"]
[570,"부산울산","울산","남울산용연#2 T/L","22~23년 변전협력회사 총액공사","- GIS(6471, 6400) 하자점검","2022-04-01 09:00","2022-04-01 18:00","2022-04-13 09:00","2022-04-13 18:00","연속"]
[571,"부산울산","울산","남울산성암#2 T/L","22~23년 변전협력회사 총액공사","- 남울산측 : 6472 하자점검 - 성암측 : 6A7 하자점검","2022-04-04 09:00","2022-04-04 18:00","2022-04-04 09:00","2022-04-04 18:00","연속"]
[572,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진-영남TP T/L 접속설비보강공사","폴리머지지애자 설치 4기","2022-04-11 07:00","2022-04-11 18:00","2022-04-11 07:00","2022-04-11 18:00","연속"]
[573,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진-영남TP T/L 접속설비보강공사","#2T/L : No.1~No.5 전선교체 5가닥(2.114C-KM)","2022-04-12 07:00","2022-04-22 18:00","2022-04-12 07:00","2022-04-22 18:00","연속"]
[574,"부산울산","울산","산하방어진#1 T/L","22~23년 변전협력회사 총액공사","- 차단기 동작시험","2022-04-11 09:00","2022-04-11 18:00","2022-04-11 09:00","2022-04-11 18:00","연속"]
[575,"부산울산","울산","남울산신온산#1 T/L","22년 상반기 154kV GIS 정밀점검공사","- GIS 정밀점검 - 병행) 남울산측 GIS(6771) 하자점검","2022-04-25 09:00","2022-04-26 18:00","2022-04-25 09:00","2022-04-26 18:00","연속"]
[576,"부산울산","울산","신온산온산#2 T/L","22년 상반기 154kV GIS 정밀점검공사","- #60-65BUS-TIE GIS 정밀점검 관련 시험가압(1Hr)","2022-04-12 17:00","2022-04-12 18:00","2022-04-12 17:00","2022-04-12 18:00","연속"]
[577,"부산울산","울산","신울산S/S #62 BUS","신울산S/S 154kV 현대화공사","두왕#1 T/L 모선측 DS 철거","2022-04-19 08:00","2022-04-20 18:00","2022-04-19 08:00","2022-04-20 18:00","연속"]
[578,"부산울산","울산","신울산울산#1 T/L","신울산S/S 154kV 현대화공사","현대화 GIS 내전압 시험관련 절연이격거리 확보","2022-04-09 08:30","2022-04-09 17:00","취소","취소","연속"]
[579,"부산울산","울산","신울산S/S #67 BUS","신울산S/S 154kV 현대화공사","두왕#1 T/L 모선측 DS 철거","2022-04-18 08:30","2022-04-18 18:00","2022-04-18 08:30","2022-04-18 18:00","연속"]
[580,"부산울산","울산","신울산웅촌#1 T/L","154kV 신울산-웅촌#1 T/L EBA C상 해체접속","EBA C상 해체 및 접속","2022-04-18 09:00","2022-04-22 18:00","2022-04-18 09:00","2022-04-22 18:00","연속"]
[581,"부산울산","울산","신울산명례#1 T/L","신울산S/S 154kV 현대화공사","현대화 GIS 내전압 시험관련 절연이격거리 확보","2022-04-06 08:30","2022-04-06 17:00","취소","취소","연속"]
[582,"부산울산","울산","신울산명례#2 T/L","신울산S/S 154kV 현대화공사","현대화 GIS 내전압 시험관련 절연이격거리 확보","2022-04-07 08:30","2022-04-07 17:00","2022-04-07 08:30","2022-04-07 17:00","연속"]
[583,"부산울산","울산","신울산울산#2 T/L","신울산S/S 154kV 현대화공사","현대화 GIS 내전압 시험관련 절연이격거리 확보","2022-04-08 08:30","2022-04-08 17:00","취소","취소","연속"]
[584,"부산울산","울산","울산영남TP#2 T/L","22~23년 변전협력회사 총액공사","- GIS 보통점검","2022-04-26 09:00","2022-04-26 18:00","2022-04-26 09:00","2022-04-26 18:00","연속"]
[585,"부산울산","울산","울산영남TP#1 T/L","22~23년 변전협력회사 총액공사","- GIS 보통점검","2022-04-27 09:00","2022-04-27 18:00","2022-04-27 09:00","2022-04-27 18:00","연속"]
[586,"부산울산","울산","두왕울산#2 T/L","22년 상반기 154kV 개폐장치 정밀점검","22년 상반기 154kV 개폐장치 정밀점검 -울산s/s 태광#2t/l 시험가압 선로","2022-04-30 17:00","2022-04-30 18:00","2022-04-30 17:00","2022-04-30 18:00","연속"]
[587,"부산울산","직할","정보대연 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 : 1~13호","2022-04-05 07:00","2022-04-07 18:00","취소","취소","연속"]
[588,"부산울산","직할","우동대연 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 : 1~13호, 피뢰기 설치 : 1~13호","2022-04-08 07:00","2022-04-11 18:00","취소","취소","연속"]
[589,"부산울산","직할","범일서면#2 T/L","22-23년 직할 변전협력회사 총액공사","서면S/S 범일-서면#1,2T/L GIS 보통점검, 에어링밸브 교체 범일S/S 범일-서면#1,2T/L GIS 보통점검, #1 87 RY 교체(가보전기)","2022-04-18 09:00","2022-04-18 18:00","2022-04-18 09:00","2022-04-18 18:00","연속"]
[590,"부산울산","직할","범일서면#1 T/L","22-23년 직할 변전협력회사 총액공사","서면S/S 범일-서면#1,2T/L GIS 보통점검, 에어링밸브 교체 범일S/S 범일-서면#1,2T/L GIS 보통점검, #1 87 RY 교체(가보전기)","2022-04-18 09:00","2022-04-18 18:00","2022-04-18 09:00","2022-04-18 18:00","연속"]
[591,"부산울산","동부산","웅촌서창#1 T/L","서창S/S 6100 GIS 정밀점검 시험가압","서창S/S 6100 GIS 정밀점검 시험가압","2022-04-10 17:00","2022-04-10 18:00","2022-04-10 17:00","2022-04-10 18:00","연속"]
[592,"부산울산","동부산","웅촌서창#2 T/L","서창S/S #4M.Tr 1차 GIS 정밀점검 시험가압","서창S/S 6433 GIS 정밀점검 시험가압","2022-04-24 17:00","2022-04-24 18:00","2022-04-24 17:00","2022-04-24 18:00","연속"]
[593,"경남","직할","신김해삼정#2 T/L","가공송전 순시점검 위탁공사(정밀점검)","154kV 신김해-삼정#2T/L 정밀점검 1-42호(14-17 제외) 38기","2022-04-04 09:00","2022-04-08 18:00","2022-04-04 09:00","2022-04-08 18:00","매일"]
[594,"경남","직할","신월삼정#2 T/L","2022년 경남 직할 154kV GIS 정밀점검 공사","2022년 경남 직할 154kV GIS 정밀점검 공사 신월-삼정#2T/L(시험가압 선로)","2022-04-07 13:00","2022-04-07 18:00","2022-04-07 13:00","2022-04-07 18:00","연속"]
[595,"경남","직할","신월동읍#1 T/L","2022년 경남 직할 154kV GIS 정밀점검 공사","2022년 경남 직할 154kV GIS 정밀점검 공사 신월-동읍#1T/L","2022-04-04 08:00","2022-04-05 18:00","취소","취소","연속"]
[596,"경남","직할","안민천선#1 T/L","안민S/S 안민-천선#1T/L GIS 조작시험","안민S/S 안민-천선#1T/L GIS 조작시험","2022-04-28 09:30","2022-04-28 17:30","2022-04-28 09:30","2022-04-28 17:30","연속"]
[597,"경남","직할","안민천선#2 T/L","2022년 경남 직할 154kV GIS 정밀점검 공사","2022년 경남 직할 154kV GIS 정밀점검 공사 안민-천선#2T/L","2022-04-25 08:00","2022-04-26 18:00","2022-04-25 08:00","2022-04-26 18:00","연속"]
[598,"경남","직할","진례진영#1 T/L","진례S/S 진례-진영#1T/L GIS 초기점검","진례S/S 진례-진영#1T/L GIS 초기점검","2022-04-03 09:30","2022-04-03 17:30","2022-04-03 09:30","2022-04-03 17:30","연속"]
[599,"경남","직할","진례진영#2 T/L","진례S/S 진례-진영#2T/L GIS 초기점검","진례S/S 진례-진영#2T/L GIS 초기점검","2022-04-10 09:30","2022-04-10 17:30","2022-04-10 09:30","2022-04-10 17:30","연속"]
[600,"경남","진주","동진주진주#2 T/L","진주S/S #2M.Tr 보통점검 및 동진주-진주#2T/L LA대체","[병행]#2M.Tr 1,2차 LA, NGR 보통점검 [병행]진주S/S 진주-개양#2T/L LA대체, PT이설 및 초기점검","2022-04-04 09:00","2022-04-05 18:00","2022-04-04 09:00","2022-04-05 18:00","연속"]
[601,"경남","진주","광양하동#2 T/L","하동S/S 154kV 하동전철T/L 신규수용공사","- 170kV GIS X 2CCT 설치(지중) - 154kV 송전선로보호배전반 X 2면 설치 - 170kV GIS 기초공사 X 1식 - 기타부대공사 X 1식","2022-04-21 09:00","2022-04-21 18:00","2022-04-21 09:00","2022-04-21 18:00","연속"]
[602,"경남","진주","광양하동#2 T/L","하동S/S 154kV 하동전철T/L 신규수용공사","- 170kV GIS X 2CCT 설치(지중) - 154kV 송전선로보호배전반 X 2면 설치 - 170kV GIS 기초공사 X 1식 - 기타부대공사 X 1식","2022-04-11 09:00","2022-04-11 18:00","2022-04-11 09:00","2022-04-11 18:00","연속"]
[603,"경남","진주","광양하동#1 T/L","하동S/S 광양-하동#1,2T/L GIS 조작시험","하동S/S 광양-하동#1,2T/L GIS 조작시험","2022-04-08 10:00","2022-04-08 14:00","2022-04-08 10:00","2022-04-08 14:00","연속"]
[604,"경남","진주","쌍림합천#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 쌍림-합천#2 T/L(No.23~57) 정밀점검 시행","2022-04-13 09:00","2022-04-15 18:00","2022-04-13 09:00","2022-04-15 18:00","매일"]
[605,"경남","진주","쌍림합천#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 쌍림-합천#1T/L(No.23~57) 정밀점검 시행","2022-04-11 09:00","2022-04-12 18:00","2022-04-11 09:00","2022-04-12 18:00","매일"]
[606,"경남","통영","삼천포사천#1 T/L","154kV 신고성-삼천포#1T/L 피뢰기 설치공사","154kV 신고성-삼천포#1T/L 피뢰기 설치공사 (작업자 안전작업거리 확보휴전)","2022-04-27 09:00","2022-04-29 18:00","2022-04-27 09:00","2022-04-29 18:00","매일"]
[607,"경남","통영","신고성거제#2 T/L","2021-2022년 경남본부 지중송전 정비전문공사","지중송전선로용 피뢰기 점검","2022-04-10 13:00","2022-04-10 19:00","2022-04-10 13:00","2022-04-10 19:00","연속"]
[608,"경남","통영","신고성삼천포#1 T/L","154kV 신고성-삼천포#1T/L 피뢰기 설치공사","154kV 신고성-삼천포#1T/L 피뢰기 설치공사","2022-04-27 09:00","2022-04-29 18:00","2022-04-27 09:00","2022-04-29 18:00","매일"]
[609,"경남","통영","신고성거제#1 T/L","2021-2022년 경남본부 지중송전 정비전문공사","지중송전선로용 피뢰기점검","2022-04-10 07:00","2022-04-10 13:00","2022-04-10 07:00","2022-04-10 13:00","연속"]
[610,"경남","함안","호포매리#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","154kV 호포-매리T/L 24호 본철탑 조립시 안전이격 확보","2022-04-16 07:00","2022-04-19 18:00","2022-04-16 07:00","2022-04-19 18:00","매일"]
[611,"경남","함안","매리김해#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","154kV 호포-매리T/L 24호 본철탑 조립시 안전이격 확보","2022-04-16 07:00","2022-04-19 18:00","2022-04-16 07:00","2022-04-19 18:00","매일"]
[612,"경남","함안","청도밀양#1 T/L","154kV 청도-밀양#2T/L 추락방지장치 설치 관련 안전거리확보","154kV 청도-밀양#2T/L 추락방지장치 설치 관련 안전거리확보","2022-04-13 07:00","2022-04-15 18:00","2022-04-13 07:00","2022-04-22 18:00","매일"]
[613,"경남","함안","주촌삼계#2 T/L","삼계S/S 154kV 주촌-삼계#2T/L GIS 보통점검","삼계S/S 154kV 주촌-삼계#2T/L GIS 보통점검","2022-04-21 09:30","2022-04-21 17:30","2022-04-21 09:30","2022-04-21 17:30","연속"]
[614,"경남","함안","주촌삼계#1 T/L","삼계S/S 154kV 주촌-삼계#1T/L GIS 보통점검","삼계S/S 154kV 주촌-삼계#1T/L GIS 보통점검","2022-04-20 09:30","2022-04-20 17:30","2022-04-20 09:30","2022-04-20 17:30","연속"]
[615,"경남","함안","수산S/S CB 6200","수산S/S 154kV #61-#66 BUS TIE GIS 조작시험","수산S/S 154kV #61-#66 BUS TIE GIS 조작시험","2022-04-18 13:30","2022-04-18 18:30","2022-04-18 13:30","2022-04-18 18:30","연속"]
[616,"경남","함안","수산S/S CB 6100","수산S/S 154kV #60-#65 BUS TIE GIS 조작시험","수산S/S 154kV #60-#65 BUS TIE GIS 조작시험","2022-04-18 09:30","2022-04-18 13:30","2022-04-18 09:30","2022-04-18 13:30","연속"]
[617,"경남","함안","신마산중리#2 T/L","신마산S/S 154kV 신마산-중리#2T/L CB 보통점검","신마산S/S 154kV 신마산-중리#2T/L CB 보통점검","2022-04-16 09:00","2022-04-16 18:00","2022-04-16 09:00","2022-04-16 18:00","연속"]
[618,"경남","함안","신마산중리#1 T/L","신마산S/S 154kV 신마산-중리#1T/L CB 보통점검","신마산S/S 154kV 신마산-중리#1T/L CB 보통점검, LA, PT 보통점검","2022-04-09 09:00","2022-04-09 18:00","2022-04-09 09:00","2022-04-09 18:00","연속"]
[619,"경남","함안","중리가야#1 T/L","154kV 중리-가야T/L 20,21,38호 안전이격확보공사","철탑교체(3기) 및 전력선 교체(19~23, 37~39호간)","2022-04-05 07:00","2022-04-13 18:00","2022-04-05 07:00","2022-04-13 18:00","연속"]
[620,"경남","함안","중리가야#2 T/L","154kV 중리-가야T/L 20,21,38호 안전이격확보공사","철탑교체(3기) 및 전력선교체(19~23,37~39호간)","2022-04-14 07:00","2022-04-20 18:00","2022-04-14 07:00","2022-04-20 18:00","연속"]
[621,"경남","함안","창녕초동#2 T/L","154kV 창녕-초동#2T/L 추락방지장치 설치공사","154kV 창녕-초동#2T/L 추락방지장치 설치공사 (1~56호) 설치대상 : 56기(1~56호)","2022-04-18 07:00","2022-04-22 18:00","2022-04-18 07:00","2022-04-22 18:00","연속"]
[622,"경남","함안","한림정삼계#1 T/L","한림정S/S 154kV 한림정-삼계#1T/L GIS 보통점검","한림정S/S 154kV 한림정-삼계#1T/L GIS 보통점검, 삼계S/S 154kV 한림정-삼계#1T/L GIS 보통점검","2022-04-21 09:30","2022-04-21 17:30","2022-04-21 09:30","2022-04-21 17:30","연속"]
[623,"인천","직할","신부평고강#1 T/L","154kV 신부평-고강#1T/L EBA 비표준형 자기애관 교체공사","종단접속함(EBA) 고장시 자기애관 비산에 따른 2차 인명·설비피해 방지","2022-04-30 09:00","2022-05-01 18:00","2022-04-30 09:00","2022-05-01 18:00","연속"]
[624,"대전세종충남","서산","신당진S/S #60 BUS","신당진S/S 154kV 장기사용GIS 교체공사(3차분)","○ 신당진S/S GIS 교체 관련 (준공시험시 위상확인)","2022-04-29 18:00","2022 04-29 19:00","2022-04-29 18:00","2022 04-29 19:00","연속"]