{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":27,"n_cols":11,"rows_kept":27,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 5월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #2 M.Tr","신가평S/S 765kV GIS 보통점검공사","8300, 8372CB 보통점검 (5월 승인시 / 4월 휴전 취소)","2022-05-11 09:00","2022-05-13 18:00","2022-05-11 09:00","2022-05-13 18:00","연속"]
[2,"경기북부","구리","신가평S/S CB 8471","신가평변전소 765kV GIS 점검공사","765kV 8471 CB 보통점검공사 (통과시 4/26~28 신청분 취소)","2022-05-17 09:00","2022-05-19 18:00","2022-05-17 09:00","2022-05-19 18:00","연속"]
[3,"경기북부","구리","신가평S/S CB 8371","신가평S/S 765kV GIS 보통점검공사","8371, 83H1 CB 보통점검 (인출 미승인시 단독차단기 승인 요)","2022-05-09 09:00","2022-05-10 18:00","2022-05-09 09:00","2022-05-10 18:00","연속"]
[4,"경기","성남","신안성S/S #1 BUS","성남전력 GIS 가스누기보수 공사","- 8751 가스누기 보수공사","2022-05-16 09:00","2022-05-22 18:00","2022-05-16 09:00","2022-05-22 18:00","연속"]
[5,"경기","성남","신안성S/S #2 M.Tr","성남전력 GIS 가스누기보수 공사","- 가스누기 보수공사 무부하가압","2022-05-21 14:00","2022-05-22 14:00","2022-05-21 14:00","2022-05-22 14:00","연속"]
[6,"경기","성남","신안성S/S #2 BUS","성남전력 GIS 가스누기보수 공사","- 8652 가스누기 보수공사","2022-05-23 09:00","2022-05-29 18:00","2022-05-23 09:00","2022-05-29 18:00","연속"]
[7,"경기","성남","신안성S/S #2 M.Tr","성남전력 GIS 가스누기보수 공사","- 가스누기 보수공사 무부하가압","2022-05-28 14:00","2022-05-29 14:00","2022-05-28 14:00","2022-05-29 14:00","연속"]
[8,"경기","성남","신안성S/S #3 M.Tr","22년 성남전력지사 변전협력회사 총액공사","- OLTC MDU교체(A-1) - B/F 대체","2022-05-30 09:00","2022-06-13 18:00","2022-05-30 09:00","2022-06-13 18:00","연속"]
[9,"강원","태백","신태백S/S #2 BUS","22-23년 태백전력지사 변전정비회사 총액공사","신태백S/S 765kV #2BUS 보호반 대체","2022-05-23 10:00","2022-06-03 18:00","2022-05-16 10:00","2022-05-27 18:00","연속"]
[10,"강원","태백","신태백S/S #1 BUS","22-23년 태백전력지사 변전정비회사 총액공사","신태백S/S 765kV #1BUS 보호반 대체","2022-05-09 10:00","2022-05-20 18:00","2022-05-02 10:00","2022-05-13 18:00","연속"]
[11,"충북","직할","신서산신중부#1 T/L","신중부변전소 765kV GIS 제작사 하자보수","내부부품 교체 후 무부하가압을 위한 선로휴전","2022-05-07 10:00","2022-05-07 18:00","취소","취소","연속"]
[12,"충북","직할","신서산신중부#1 T/L","신중부변전소 765kV GIS 제작사 하자보수","내부부품 교체 후 무부하가압을 위한 선로휴전","2022-05-14 10:00","2022-05-14 18:00","취소","취소","연속"]
[13,"충북","직할","신중부S/S CB 8672","신중부변전소 765kV GIS 제작사 하자보수","현대제 765kV GIS 지락고장 방지를 위한 내부부품 교체","2022-05-09 10:00","2022-05-14 18:00","2022-05-12 10:00","2022-05-19 18:00","연속"]
[14,"충북","직할","신중부S/S CB 8600","신중부변전소 765kV GIS 제작사 하자보수","현대제 765kV GIS 지락고장 방지를 위한 내부부품 교체","2022-05-02 10:00","2022-05-07 18:00","2022-05-03 10:00","2022-05-10 18:00","연속"]
[15,"충북","직할","신중부S/S #4 M.Tr","신중부변전소 765kV GIS 제작사 하자보수","내부부품 교체 후 무부하가압을 위한 변압기휴전","2022-05-14 10:00","2022-05-14 18:00","2022-05-19 10:00","2022-05-19 18:00","연속"]
[16,"대전세종충남","서산","당진T/P CB 8100","서산P/O 765kV GIS 정밀점검공사","당진화력S/S 765kV #1TIE-Tr 1차 TIE GIS(8100) 정밀점검","2022-05-02 09:00","2022-05-06 18:00","2022-05-02 09:00","2022-05-06 18:00","연속"]
[17,"대전세종충남","서산","신서산S/S CB 8400","서산P/O 765kV GIS 정밀점검 공사","(T/L휴전 승인시 취소할 것) 신서산S/S 765kV TIE 8400 GIS 정밀점검 공사","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[18,"대전세종충남","서산","신서산S/S CB 8471","서산P/O 765kV GIS 정밀점검 공사","(T/L휴전 승인시 취소할 것) 신서산S/S 765kV 신서산-당진화력#1T/L 8471 GIS 정밀점검 공사","2022-05-09 09:00","2022-05-13 18:00","2022-05-09 09:00","2022-05-13 18:00","연속"]
[19,"대전세종충남","서산","신서산당진TP#1 T/L","서산P/O 노후 송전선로 및 차단실패 보호반 대체공사","서산P/O 노후 송전선로 및 차단실패 보호반 대체공사 - (병행) 765kV 8471, 8400 GIS 정밀점검 공사","2022-05-09 09:00","2022-05-20 18:00","2022-05-10 09:00","2022-05-20 18:00","연속"]
[20,"대전세종충남","서산","신서산신중부#1 T/L","[송전] 765kV 신서산-신중부T/L 항공구 교체공사","ㅇ765kV 신서산-신중부T/L No.12-13호 등 21개 경간 항공구 교체 시행 - 볼트탈락 및 항공구 탈락개소, 민원개소 등 전개소 정비시행","2022-05-02 07:00","2022-05-08 18:00","2022-05-03 07:00","2022-05-09 18:00","매일"]
[21,"부산울산","동부산","신고리N/P #1 Tie-Tr","신고리 5,6호기 접속설비공사","345kV 신고리-고리 #4T/L(가공) 신고리측 CH 철탑 전력선 인하 가선작업 안전이격거리(#1T/L) 확보","2022-05-02 09:00","2022-05-02 18:00","취소","취소","연속"]
[22,"부산울산","동부산","신고리N/P #2 Tie-Tr","신고리 5,6호기 접속설비공사","-신고리 #4M.Tr * 1BANK 증설 (#2M.Tr 8671CB, 8600CB 인출을 #2M.Tr에서 #4M.Tr로 변경) - 800kV 인출 GIB 설치 및 내전압시험 - 준공시험","2022-05-03 09:00","2022-07-30 18:00","취소","취소","연속"]
[23,"충북","직할","신중부S/S #4 M.Tr","신중부변전소 765kV GIS 제작사 하자보수","내부부품 교체 후 무부하가압을 위한 선로휴전","2022-05-10 10:00","2022-05-10 18:00","2022-05-10 10:00","2022-05-10 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":238,"n_cols":11,"rows_kept":238,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 5월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","양주중부#1 T/L","'22-'23중부P/O 변전협력회사 총액공사","362kV CB 조작시험","2022-05-12 10:00","2022-05-12 17:00","2022-05-12 10:00","2022-05-12 17:00","연속"]
[2,"서울","중부","양주중부#2 T/L","'22-'23중부P/O 변전협력회사 총액공사","362kV CB 조작시험","2022-05-13 10:00","2022-05-13 17:00","2022-05-13 10:00","2022-05-13 17:00","연속"]
[3,"남서울","강남","신양재S/S #3 M.Tr","2022년 강남전력지사 345kV M.Tr 정밀점검","2022년 강남전력지사 345kV M.Tr 정밀점검 - 점검대상 : #3M.TR A,B,C - 병행작업 1. #3M.Tr 2차 GIS 정밀점검 2. #3M.Tr 1차 GIS 조작시험","2022-05-10 09:00","2022-05-26 18:00","2022-05-10 09:00","2022-05-26 18:00","연속"]
[4,"남서울","동서울","신성남동서울#1 T/L","동서울S/S 노후 주변압기 교체 및 이설공사","○ 노후 주변압기 11대 교체 및 이설","2022-05-06 14:00","2022-05-07 14:00","2022-05-10 14:00","2022-05-11 14:00","연속"]
[5,"남서울","영등포","신시흥신광명#2 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","ㅇ 345kV 63kA GIS 24CB 설치 ㅇ 구내 인출변경 전력구 시공 관련 345kV LA 이설","2022-05-22 10:00","2022-05-31 18:00","취소","취소","연속"]
[6,"남서울","영등포","서서울신광명#1 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","ㅇ 345kV 63kA GIS 24CB 설치 ㅇ 구내 인출변경 전력구 시공 관련 345kV LA 이설","2022-05-02 10:00","2022-05-11 18:00","2022-05-02 10:00","2022-05-11 18:00","연속"]
[7,"남서울","영등포","신시흥신광명#1 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","ㅇ 345kV 63kA GIS 24CB 설치 ㅇ 구내 인출변경 전력구 시공 관련 345kV LA 이설","2022-05-12 10:00","2022-05-21 18:00","2022-05-12 10:00","2022-05-21 18:00","연속"]
[8,"남서울","영등포","신광명S/S #76 BUS","신광명 노후 주변압기 교체공사 (#4M.Tr 무부하 가압)","#4M.Tr 무부하 가압용 모선","2022-05-16 09:00","2022-05-17 18:00","2022-05-14 09:00","2022-05-15 18:00","연속"]
[9,"인천","김포","신김포신파주#2 T/L","345kV 신김포-신파주#2T/L 항공구 설치","항공장애표시구 설치 -신김포C/T~No.1(1경간)","2022-05-02 08:00","2022-05-02 13:00","2022-05-02 08:00","2022-05-02 13:00","연속"]
[10,"인천","직할","서인천CC신부평#1 T/L","345kV 서인천CC-신부평T/L 절연유 채취","345kV 서인천CC-신부평 등 2개T/L 절연유 채취","2022-05-02 09:00","2022-05-06 18:00","2022-05-02 09:00","2022-05-06 18:00","연속"]
[11,"인천","시흥","영흥T/P CB 7772","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV #6G.Tr 1차 GIS(7772) 정밀점검","2022-05-09 08:00","2022-05-11 18:00","취소","취소","연속"]
[12,"인천","부평","서인천C/C #1 M.Tr","서인천C/C 345kV #1 M.Tr 휴전작업","보통점검 및 부싱절연유 채유 77172GIS 조작시험, 6144GIS 보통점검","2022-05-09 09:00","2022-05-11 18:00","2022-05-09 09:00","2022-05-11 18:00","연속"]
[13,"인천","직할","갈산S/S #1 M.Tr","갈산S/S #1M.Tr 변압기, 1,2차 GIS하자점검","갈산S/S #1M.Tr 변압기, 1,2차 GIS하자점검","2022-05-09 09:30","2022-05-11 18:00","2022-05-09 09:30","2022-05-11 18:00","연속"]
[14,"인천","김포","가정개폐소 CB 7372","가정개폐소 345kV 가정-갈산#2T/L(7372) GIS 하자점검","가정개폐소 345kV 가정-갈산#2T/L(7372) GIS 하자점검","2022-05-09 10:00","2022-05-09 18:00","2022-05-09 10:00","2022-05-09 18:00","연속"]
[15,"인천","김포","가정개폐소 CB 7671","가정개폐소 345kV #1Sh.R 1차(7671) GIS 보통점검","가정개폐소 345kV #1Sh.R 1차(7671) GIS 보통점검","2022-05-10 10:00","2022-05-10 18:00","2022-05-10 10:00","2022-05-10 18:00","연속"]
[16,"인천","김포","가정개폐소 CB 7171","가정개폐소 345kV #2Sh.R 1차(7171) GIS 보통점검","가정개폐소 345kV #2Sh.R 1차(7171) GIS 보통점검","2022-05-11 10:00","2022-05-11 18:00","2022-05-11 10:00","2022-05-11 18:00","연속"]
[17,"인천","시흥","영흥T/P CB 7671","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV 영흥TP연락#1T/L GIS(7671) 정밀점검","2022-05-12 08:00","2022-05-14 18:00","취소","취소","연속"]
[18,"인천","김포","가정개폐소 CB 7172","가정개폐소 345kV #3Sh.R 1차(7172) GIS 보통점검","가정개폐소 345kV #3Sh.R 1차(7172) GIS 보통점검","2022-05-12 10:00","2022-05-12 18:00","2022-05-12 10:00","2022-05-12 18:00","연속"]
[19,"인천","김포","가정개폐소 CB 7100","가정개폐소 345kV 7100 TIE GIS 보통점검","가정개폐소 345kV #2Sh.R-#3Sh.R TIE(7100) GIS 보통점검","2022-05-13 10:00","2022-05-13 18:00","2022-05-13 10:00","2022-05-13 18:00","연속"]
[20,"인천","시흥","영흥T/P CB 7600","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV 영흥TP연락#1T/L-#5G.Tr 1차 TIE GIS(7600) 정밀점검","2022-05-16 08:00","2022-05-18 18:00","취소","취소","연속"]
[21,"인천","부평","신인천C/C CB 7872","신인천C/C 78Bay B/F 보호반 교체","신인천C/C 78Bay B/F 보호반 교체 -7800, 7871GIS 조작시험 -7872GIS 보통점검","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[22,"인천","부평","신경서신인천CC T/L","신인천C/C 78Bay B/F 보호반 교체","신인천C/C 78Bay B/F 보호반 교체 -7800, 7871GIS 조작시험 -7872GIS 보통점검","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[23,"인천","시흥","신시흥영흥TP#2 T/L","신시흥S/S 신시흥영흥TP#2 T/L 결상회로보완","신시흥S/S 신시흥영흥TP#2 T/L 결상회로보완","2022-05-16 09:00","2022-05-16 18:00","2022-05-16 09:00","2022-05-16 18:00","연속"]
[24,"인천","직할","신부평S/S #2 M.Tr","신부평S/S #2M.Tr 변압기 보통점검,7272,7200GIS 조작시험","신부평S/S #2M.Tr 변압기 보통점검,7272,7200GIS 조작시험","2022-05-16 09:00","2022-05-17 18:00","2022-05-16 09:00","2022-05-17 18:00","연속"]
[25,"인천","직할","서인천CC신부평#2 T/L","345kV 서인천CC-신부평T/L 절연유 채취 및 SVL교체공사","1. 345kV 서인천CC-신부평T/L 절연유 채취 2. 구형SVL 교체공사","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[26,"인천","직할","갈산S/S CB 7500","갈산S/S 362kV 7500TIE 하자점검관련 조치","갈산S/S 362kV 7500TIE 하자점검","2022-05-16 09:30","2022-05-16 14:00","2022-05-16 09:30","2022-05-16 14:00","연속"]
[27,"인천","김포","가정개폐소 SEC CB 70710","가정개폐소 345kV 70-71 SEC GIS 보통점검","가정개폐소 345kV 70-71 SEC GIS 보통점검","2022-05-16 10:00","2022-05-16 18:00","2022-05-16 10:00","2022-05-16 18:00","연속"]
[28,"인천","직할","갈산S/S CB 7371","갈산S/S 갈산신광명#2TL 7371 GIS하자점검관련 조치","갈산S/S 갈산신광명#2TL 7371 GIS하자점검","2022-05-16 14:00","2022-05-16 18:00","2022-05-16 14:00","2022-05-16 18:00","연속"]
[29,"인천","시흥","신시흥영흥TP#1 T/L","신시흥S/S 신시흥영흥TP#1 T/L 결상회로보완","신시흥S/S 신시흥영흥TP#1 T/L 결상회로보완","2022-05-17 09:00","2022-05-17 18:00","2022-05-17 09:00","2022-05-17 18:00","연속"]
[30,"인천","직할","갈산S/S CB 7300","갈산S/S 362kV 7300TIE 하자점검관련 조치","갈산S/S 362kV 7300TIE 하자점검","2022-05-17 09:30","2022-05-17 14:00","2022-05-17 09:30","2022-05-17 14:00","연속"]
[31,"인천","김포","가정개폐소 SEC CB 75760","가정개폐소 345kV 75-76 SEC GIS 보통점검","가정개폐소 345kV 75-76 SEC GIS 보통점검","2022-05-17 10:00","2022-05-17 18:00","2022-05-17 10:00","2022-05-17 18:00","연속"]
[32,"인천","직할","갈산S/S CB 7400","갈산S/S 362kV 7400TIE 하자관련 조치","갈산S/S 362kV 7400TIE 하자점검","2022-05-17 14:00","2022-05-17 18:00","2022-05-17 14:00","2022-05-17 18:00","연속"]
[33,"인천","시흥","신시흥신안산#1 T/L","신시흥S/S 신시흥신안산#1T/L 결상회로보완 및 LA대체","신시흥S/S 신시흥신안산#1T/L 결상회로보완 및 LA대체","2022-05-18 09:00","2022-05-19 18:00","2022-05-18 09:00","2022-05-19 18:00","연속"]
[34,"인천","직할","갈산S/S #2 M.Tr","갈산S/S #2M.Tr 변압기, 1,2차 GIS하자점검","갈산S/S #2M.Tr 변압기, 1,2차 GIS하자점검","2022-05-18 09:30","2022-05-20 18:00","2022-05-18 09:30","2022-05-20 18:00","연속"]
[35,"인천","시흥","영흥T/P CB 7672","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV #5G.Tr 1차 GIS(7672) 정밀점검","2022-05-19 08:00","2022-05-21 18:00","취소","취소","연속"]
[36,"인천","부평","신가좌신시흥#2 T/L","송전철탑 추락방지시설 설치","345kV 신가좌-신시흥#2T/L 송전철탑 추락방지시설 설치","2022-05-23 08:00","2022-05-27 18:00","2022-05-28 08:00","2022-05-29 18:00","연속"]
[37,"인천","시흥","영흥T/P CB 7871","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV 신시흥-영흥TP#1T/L GIS(7871) 정밀점검","2022-05-23 08:00","2022-05-25 18:00","취소","취소","연속"]
[38,"인천","직할","서인천CC신부평#3 T/L","345kV 서인천CC-신부평T/L 절연유 채취 및 SVL교체공사","1. 345kV 서인천CC-신부평T/L 절연유 채취 2. 구형SVL 교체공사","2022-05-23 09:00","2022-05-27 18:00","2022-05-23 09:00","2022-05-28 18:00","연속"]
[39,"인천","시흥","신시흥신광명#2 T/L","송전철탑 추락방지시설 설치","345kV 신시흥-신광명#2T/L 송전철탑 추락방지시설 설치","2022-05-26 08:00","2022-05-27 18:00","2022-05-28 08:00","2022-05-29 18:00","연속"]
[40,"인천","시흥","영흥T/P CB 7800","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV 신시흥-영흥TP#1T/L TIE GIS(7800) 정밀점검","2022-05-26 08:00","2022-05-28 18:00","취소","취소","연속"]
[41,"인천","직할","신부평S/S #3 M.Tr","신부평S/S #3M.Tr 변압기 보통점검,7372GIS 조작시험","신부평S/S 345kV #3M.Tr 변압기 보통점검,7372GIS 조작시험","2022-05-26 09:00","2022-05-27 18:00","2022-05-26 09:00","2022-05-27 18:00","연속"]
[42,"인천","부평","신가좌가정#1 T/L","송전철탑 추락방지시설 설치","345kV 신가좌-가정#1T/L 송전철탑 추락방지시설 설치","2022-05-30 08:00","2022-05-30 18:00","취소","취소","연속"]
[43,"인천","시흥","영흥T/P CB 7200","2022년 시흥전력지사 362kV 정밀점검공사","영흥T/P 345kV 영흥TP연락#2T/L-#2G.Tr 1차 TIE GIS(7200) 정밀점검","2022-05-30 08:00","2022-06-02 18:00","2022-05-30 08:00","2022-06-02 18:00","연속"]
[44,"인천","직할","서인천CC신부평#4 T/L","345kV 서인천CC-신부평T/L 절연유 채취","1. 345kV 서인천CC-신부평T/L 절연유 채취","2022-05-30 09:00","2022-06-03 18:00","2022-06-07 09:00","2022-06-09 18:00","연속"]
[45,"인천","직할","갈산S/S #1 Sh.R CB","갈산S/S #1Sh.R 초기점검, 7671,7600GIS 초기점검","갈산S/S #1Sh.R 초기점검, 7671,7600GIS 초기점검","2022-05-30 09:30","2022-05-31 18:00","2022-05-30 09:30","2022-05-31 18:00","매일"]
[46,"인천","부평","신가좌가정#2 T/L","송전철탑 추락방지시설 설치","345kV 신가좌-가정#2T/L 송전철탑 추락방지시설 설치","2022-05-31 08:00","2022-05-31 18:00","취소","취소","연속"]
[47,"경기북부","구리","미금성동#2 T/L","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 72Bay 차단기 1대 감시제어계측 포인트이관 (→SA) - 72Bay LCP 및 배전반 모자익반 제어케이블 철거 및 재결선","2022-05-09 09:00","2022-05-13 18:00","취소","취소","연속"]
[48,"경기북부","구리","동서울미금#2 T/L","2022~23 구리전력 변전협력 총액공사","미금S/S 동서울-미금#2T/L GIS 보통점검 - 7471, 7400 GIS 보통점검","2022-05-25 09:00","2022-05-26 18:00","2022-04-21 09:00","2022-04-22 18:00","연속"]
[49,"경기북부","구리","포천C/C CB 7271","포천CC 차단기 조작로드 교체공사","포천CC 차단기 조작로드 교체공사","2022-05-02 09:00","2022-05-06 18:00","2022-05-02 09:00","2022-05-06 18:00","연속"]
[50,"경기북부","직할","동두천C/C CB 7272","2022-2023년 경기북부 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7272 CB 보통점검","2022-05-03 09:00","2022-05-03 18:00","2022-05-03 09:00","2022-05-03 18:00","연속"]
[51,"경기북부","직할","동두천C/C CB 7300","2022-2023년 경기북부 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7300 CB 보통점검","2022-05-10 09:00","2022-05-10 18:00","2022-05-10 09:00","2022-05-10 18:00","연속"]
[52,"경기북부","직할","동두천C/C CB 7172","2022-2023년 경기북부 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7172 CB 보통점검","2022-05-02 09:00","2022-05-02 18:00","2022-05-02 09:00","2022-05-02 18:00","연속"]
[53,"경기북부","직할","동두천C/C CB 7372","2022-2023년 경기북부 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7372 CB 보통점검","2022-05-09 09:00","2022-05-09 18:00","2022-05-09 09:00","2022-05-09 18:00","연속"]
[54,"경기북부","직할","양주S/S STATCOM (CB 7771, 7700)","345kV 양주S/S STATCOM 건설사업","○ ±200MVar STATCOM 증설 ○ STATCOM 실부하시험 및 시운전","2022-05-02 09:00","2022-05-31 18:00","2022-05-02 09:00","2022-05-31 18:00","연속"]
[55,"경기","군포","서서울S/S #3 M.Tr","7600,7672 GIS 보통, #3Sh.R VCB 보통","7600,7672 GIS 보통, #3Sh.R VCB 보통, 3차 GPT 대체(자재확인), 96P 96D 커버설치,전자변대체,결상회로개선","2022-05-17 09:00","2022-05-20 18:00","2022-05-17 09:00","2022-05-18 18:00","연속"]
[56,"경기","군포","서서울S/S #2 M.Tr","7500,7572 GIS 보통, #2Sh.R VCB 보통","7500,7572 GIS 보통 및 전자변교체 #2Sh.R VCB 보통, 3차 GPT 대체(자재확인), 96D 커버 설치 등","2022-05-09 09:00","2022-05-13 18:00","2022-05-09 09:00","2022-05-10 18:00","연속"]
[57,"경기","동부","곤지암S/S #1 M.Tr","22년 동부 변전정비 총액공사","곤지암:#1M.Tr 보호반대체(~8)","2022-05-02 09:30","2022-05-06 18:00","2022-05-10 09:30","2022-05-13 18:00","연속"]
[58,"경기","동부","곤지암신충주#2 T/L","22년 동부 변전정비 총액공사","곤지암:#71Bay B/F 보호반대체(~8)","2022-05-02 09:30","2022-05-06 18:00","2022-05-10 09:30","2022-05-13 18:00","연속"]
[59,"경기","성남","신성남신양재#2 T/L","22년 성남전력지사 변전협력회사 총액공사","- 7771,7700 조작시험 - 러버히터 재설치 - 에어링 밸브 점검","2022-05-26 09:00","2022-05-26 18:00","2022-05-27 09:00","2022-05-27 18:00","연속"]
[60,"경기","성남","신수원S/S #4 M.Tr","22년 성남전력지사 변전협력회사 총액공사","- 2차 GIS 조작시험 - 1차 LA 대체 - 부싱절연유 채유","2022-05-30 09:00","2022-05-30 18:00","2022-05-30 09:00","2022-05-30 18:00","연속"]
[61,"경기","성남","신안성신용인#1 T/L","22년 성남전력지사 변전협력회사 총액공사","- 7700,7772 보통점검","2022-05-17 09:00","2022-05-17 18:00","2022-05-17 09:00","2022-05-17 18:00","연속"]
[62,"경기","성남","신안성신성남#1 T/L","22년 성남전력지사 변전협력회사 총액공사","- 7572,7500 보통점검 - 7500유압스위치교체(B상)","2022-05-12 09:00","2022-05-12 18:00","2022-05-12 09:00","2022-05-12 18:00","연속"]
[63,"경기","성남","신용인S/S #3 M.Tr","22년 성남전력 170kV GIS 정밀점검공사","- #3M.Tr 2차 GIS 정밀점검","2022-05-23 09:00","2022-05-25 14:00","2022-05-23 09:00","2022-05-25 14:00","연속"]
[64,"경기","성남","신용인S/S #4 M.Tr","22년 성남전력지사 변전협력회사 총액공사","- 3차 LA(B,C) 불량점검 - CVT 초기점검 - 부싱절연유 채유","2022-05-31 09:00","2022-05-31 18:00","2022-05-31 09:00","2022-05-31 18:00","연속"]
[65,"경기","성남","신용인동서울#1 T/L","고산1지구 345kV 신용인-동서울T/L 지중화공사","[가공송전] : 케이블헤드 설치 1기, 철탑 철거 2기(ACSR 480㎟ × 2B) [지중송전] : 476m 포설 접속, 고장점검출장치, 전력구 부대설비(XLPE 2,500㎟ × 2C)","2022-05-11 09:00","2022-05-31 18:00","2022-05-14 09:00","2022-05-31 18:00","연속"]
[66,"경기","직할","화성S/S #76 BUS","345kV 화성S/S GIS 용량대체공사","- 77 Bay 7700CB 무부하가압(7772 CB 철거)","2022-05-09 11:00","2022-05-10 11:00","2022-05-09 11:00","2022-05-10 11:00","연속"]
[67,"경기","평택","고덕S/S #2 BUS","고덕S/S 2단계 HVDC 연계용GIS 설치공사","모선보호반 86T Lock-Out Ry 추가설치","2022-05-26 09:00","2022-05-27 18:00","2022-05-26 09:00","2022-05-27 18:00","연속"]
[68,"경기","평택","고덕S/S #4 M.Tr","고덕S/S 345kV #4M.Tr 누유보수","고덕S/S 345kV #4M.Tr C상 상부 누유 제작사 보수","2022-05-11 10:00","2022-05-11 18:00","2022-05-11 10:00","2022-05-11 18:00","연속"]
[69,"경기","평택","고덕S/S #1 BUS","고덕S/S 2단계 HVDC 연계용GIS 설치공사","모선보호반 86T Lock-Out Ry 추가설치","2022-05-24 09:00","2022-05-25 18:00","2022-05-24 09:00","2022-05-25 18:00","연속"]
[70,"경기","평택","서안성신진천#1 T/L","345kV 고덕#2S/S 건설공사","- 서안성S/S 345kV GIS 3CB 증설 무부하가압용","2022-05-12 09:00","2022-05-13 04:00","2022-05-12 09:00","2022-05-13 04:00","연속"]
[71,"경기","평택","서안성신진천#1 T/L","세종-포천간 도로개설 관련 지장이설 임시이설(1-2공구)","임시1기, 보강 2기","2022-05-14 07:00","2022-05-29 18:00","2022-05-14 07:00","2022-05-29 18:00","연속"]
[72,"경기","평택","서안성S/S #1 M.Tr","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 345kV #1M.Tr 부싱절연유 채유 및 2차 GIS 보통점검","2022-05-23 10:00","2022-05-23 18:00","2022-05-23 10:00","2022-05-23 18:00","연속"]
[73,"경기","평택","서안성신진천#2 T/L","세종-포천간 도로개설 관련 지장이설 임시이설(1-2공구)","임시1기, 보강 2기","2022-05-30 07:00","2022-06-08 18:00","2022-05-30 07:00","2022-06-08 18:00","연속"]
[74,"경기","평택","서안성S/S #3 M.Tr","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 345kV #3M.Tr 부싱절연유 채유 및 2차 GIS 보통점검","2022-05-25 10:00","2022-05-25 18:00","2022-05-25 10:00","2022-05-25 18:00","연속"]
[75,"강원","강릉","신양양S/S CB 7172","2022년 362kV GIS 정밀점검","362kV GIS 정밀점검(7172)","2022-05-09 09:00","2022-05-13 18:00","취소","취소","연속"]
[76,"강원","강릉","신양양S/S #1 M.Tr","2022년 362kV GIS 정밀점검","362kV GIS 정밀점검(7172) &lt병행> - 신양양S/S #1M.Tr 3차 PT, LA, CB, #1S.Tr 보통점검 - 신양양S/S #1M.Tr 2차 GIS 정밀점검","2022-05-09 09:00","2022-05-13 18:00","2022-05-10 09:00","2022-05-12 18:00","연속"]
[77,"강원","강릉","신양양S/S #2 BUS","2022년 362kV GIS 정밀점검 무부하가압","362kV GIS 정밀점검(7172) 무부하가압","2022-05-13 16:00","2022-05-13 18:00","취소","취소","연속"]
[78,"강원","강릉","신양양S/S #2 M.Tr","2022년 362kV GIS 정밀점검","362kV GIS 정밀점검(7372) &lt병행> - 신양양S/S #2M.Tr 3차 PT, LA 보통점검 - 신양양S/S #2M.Tr 2차 GIS 정밀점검","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[79,"강원","강릉","신양양S/S #2 BUS","2022년 362kV GIS 정밀점검 무부하가압","362kV GIS 정밀점검(7372) 무부하가압","2022-05-20 16:00","2022-05-20 18:00","2022-05-20 16:00","2022-05-20 18:00","연속"]
[80,"강원","강릉","신양양S/S #2 M.Tr","2022년 362kV GIS 정밀점검","362kV GIS 정밀점검(7300)","2022-05-23 09:00","2022-05-27 18:00","2022-05-23 09:00","2022-05-27 18:00","연속"]
[81,"강원","강릉","신양양양양PP T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 신양양인제#1T/L No.3-6(작업자 안전확보를 위한 동일 편측 회선 휴전)","2022-05-30 07:00","2022-05-30 18:00","2022-05-30 07:00","2022-05-30 18:00","연속"]
[82,"강원","강릉","신양양S/S #1 BUS","2022년 362kV GIS 정밀점검 무부하가압","362kV GIS 정밀점검(7300) 무부하가압","2022-05-27 16:00","2022-05-27 18:00","2022-05-27 16:00","2022-05-27 18:00","연속"]
[83,"강원","강릉","안인개폐소신양양 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 신양양인제#2T/L No.3-6 (작업자 안전확보를 위한 동일 편측 회선 휴전)","2022-05-24 07:00","2022-05-24 18:00","2022-05-23 07:00","2022-05-23 18:00","연속"]
[84,"강원","동해","동해삼척GP#1 T/L","22~23 동해전력지사 변전정비 총액공사","1, CVT 초기점검 2. 차단기 조작시험[7571,7500]","2022-05-11 09:00","2022-05-11 18:00","2022-05-11 09:00","2022-05-11 18:00","연속"]
[85,"강원","동해","동해S/S #1 M.Tr","22~23 동해전력지사 변전정비 총액공사","1. 4719 3차측 VCB 대체 2. M.Tr 2차측 LA 초기점검 3. 차단기 조작시험 7172 4. 부싱 절연유 채유","2022-05-23 09:00","2022-05-27 18:00","2022-05-23 09:00","2022-05-27 18:00","연속"]
[86,"강원","동해","동해삼척GP#2 T/L","22~23 동해전력지사 변전정비 총액공사","1. CVT 초기점검 2. 차단기 조작시험[7671,7600]","2022-05-12 09:00","2022-05-12 18:00","2022-05-12 09:00","2022-05-12 18:00","연속"]
[87,"강원","동해","북평T/P CB 7272","동해전력지사 22년 362kV GIS 정밀점검 공사","1. GIS 정밀점검","2022-05-23 09:00","2022-05-27 18:00","2022-05-23 09:00","2022-05-27 18:00","연속"]
[88,"강원","동해","북평T/P CB 7172","동해전력지사 22년 362kV GIS 정밀점검 공사","1. GIS 정밀점검","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[89,"충북","청주","남청주S/S #4 M.Tr","변압기보호반 및 B/F반 노후교체","[22-23 청주전력 변전정비 총액공사] 345kV #4M.Tr 보호반 & 78BAY B/F반 노후교체","2022-05-16 10:00","2022-05-20 18:00","취소","취소","연속"]
[90,"충북","충주","신제천S/S #2 TCSC CB","2022년 신제천S/S 345kV TCSC 하자점검공사","2022년 신제천S/S 345kV TCSC 하자점검공사","2022-05-30 09:00","2022-06-03 18:00","취소","취소","연속"]
[91,"충북","충주","신제천S/S #4 M.Tr","22년 충주전력지사 345kV 변압기 및 OLTC 정밀점검 공사","#4M.Tr 정밀점검","2022-05-09 09:00","2022-05-20 18:00","취소","취소","연속"]
[92,"충북","충주","신제천신충주#1 T/L","345kV 신제천-신충주 등 4개 T/L 추락방지시설 설치공사","345kV 신제천-신충주#1 T/L 추락방지시설 설치공사","2022-05-02 07:00","2022-05-13 18:00","2022-05-02 07:00","2022-05-13 18:00","매일"]
[93,"충북","충주","신제천S/S #1 TCSC CB","2022년 신제천S/S 345kV TCSC 하자점검공사","2022년 신제천S/S 345kV TCSC 하자점검공사","2022-05-23 09:00","2022-05-27 18:00","취소","취소","연속"]
[94,"충북","충주","신충주S/S #4 M.Tr","신충주S/S 154kV GIS 설치공사","#62-63, #67-68 SEC 및 63-68 TIE GIS 설치 관련 안전이격 확보","2022-05-16 09:00","2022-05-18 18:00","2022-05-16 09:00","2022-05-18 18:00","연속"]
[95,"충북","충주","신충주S/S #4 M.Tr","신충주S/S 154kV GIS 설치공사","#62-63, #67-68 SEC 및 63-68 TIE GIS 설치 관련 안전이격 확보","2022-05-09 09:00","2022-05-11 18:00","2022-05-09 09:00","2022-05-11 18:00","연속"]
[96,"대전세종충남","대전","신계룡S/S #1 BUS","신계룡S/S 345kV 모선보호반 교체공사","신계룡S/S 345kV 모선보호반 교체공사","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[97,"대전세종충남","대전","신계룡S/S #2 BUS","신계룡S/S 345kV 모선보호반 교체공사","신계룡S/S 345kV 모선보호반 교체공사","2022-05-23 09:00","2022-05-27 18:00","2022-05-23 09:00","2022-05-27 18:00","연속"]
[98,"대전세종충남","대전","신계룡S/S #3 M.Tr","신계룡S/S #3M.Tr 보통점검 및 병행작업","주작업 : 신계룡S/S #3M.Tr 보통점검 병행작업 - #3M.Tr 1차, #3M.Tr 1차 TIE, 2차 GIS 보통점검 - 1차 GIDS 보통점검 - 피뢰기 보통점검 - 3차 계기용변성기 보통점검","2022-05-02 09:00","2022-05-04 18:00","2022-05-02 09:00","2022-05-04 18:00","연속"]
[99,"대전세종충남","서산","당진T/P #71 Tie-Tr","당진화력S/S 345kV #71TIE-Tr 1차 LA, CVT 대체","당진화력S/S 345kV #71TIE-Tr 1차 LA, CVT 대체 - (병행) 당진화력S/S 345kV #71TIE-Tr 및 2차 LA 보통점검, 부싱절연유 채유","2022-05-23 10:00","2022-05-27 18:00","2022-05-23 10:00","2022-05-27 18:00","연속"]
[100,"대전세종충남","서산","북당진S/S #1 M.Tr","22년 서산P/O 변전협력회사 총액공사","(바이오매스 휴전 병행) 북당진S/S #1M.Tr 부싱절연유 채유","2022-05-30 10:00","2022-05-30 14:00","2022-05-30 10:00","2022-05-30 14:00","연속"]
[101,"대전세종충남","서산","신당진개폐소태안TP#2 T/L"," 신당진개폐소 345kV 개폐소-태안화력#2T/L 가스누기 보수공사","신당진개폐소 345kV 개폐소-태안화력#2T/L 가스누기 보수공사 - (병행) 신당진개폐소 측 LA 보통점검, CVT 하자점검","2022-05-23 09:00","2022-05-27 18:00","2022-05-23 09:00","2022-05-27 18:00","연속"]
[102,"대전세종충남","서산","신당진개폐소 SEC CB 7A7B0","22년 서산P/O 변전협력회사 총액공사","신당진S/S 345kV 7A-7B-0 SEC GIS 보통점검","2022-05-23 09:00","2022-05-23 18:00","2022-05-23 09:00","2022-05-23 18:00","연속"]
[103,"대전세종충남","서산","신당진개폐소 SEC CB 7C7D0","22년 서산P/O 변전협력회사 총액공사","신당진S/S 345kV 7C-7D-0 SEC GIS 보통점검","2022-05-24 09:00","2022-05-24 18:00","2022-05-24 09:00","2022-05-24 18:00","연속"]
[104,"대전세종충남","서산","신당진S/S CB 7100","22년도 장기 미동작 차단기 조작시험","신당진S/S 345kV 신서산-신당진#1T/L TIE 7100 CB 조작시험","2022-05-11 10:00","2022-05-11 14:00","2022-05-11 10:00","2022-05-11 14:00","연속"]
[105,"대전세종충남","서산","신당진S/S CB 7400","22년도 장기 미동작 차단기 조작시험","신당진S/S 345kV 신당진연락#1T/L-#1 M.Tr 1차 TIE 7400CB 조작시험","2022-05-11 14:00","2022-05-11 18:00","2022-05-11 14:00","2022-05-11 18:00","연속"]
[106,"대전세종충남","서산","신서산S/S #3 Sh.R (CB 7579)","22년 서산P/O 변전협력회사 총액공사","신서산S/S 345kV #3Sh.R 7579 GIS 보통점검","2022-05-04 09:00","2022-05-04 18:00","2022-05-04 09:00","2022-05-04 18:00","연속"]
[107,"대전세종충남","서산","신서산S/S CB 7872","22년 서산P/O 변전협력회사 총액공사","신서산S/S 345kV 7872 GIS 보통점검","2022-05-03 09:00","2022-05-03 18:00","2022-05-03 09:00","2022-05-03 18:00","연속"]
[108,"대전세종충남","서산","신서산S/S CB 7500","22년 서산P/O 변전협력회사 총액공사","신서산S/S 345kV 7500 GIS 보통점검","2022-05-30 09:00","2022-05-30 18:00","2022-05-30 09:00","2022-05-30 18:00","연속"]
[109,"대전세종충남","천안","신온양서서울#1 T/L","신온양S/S 345kV 신온양서서울#1 T/L 결상관련 회로개선","신온양S/S 345kV 신온양서서울#1 T/L 결상관련 회로개선","2022-05-03 09:00","2022-05-03 18:00","취소","취소","연속"]
[110,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S 345kV 신온양서서울#2 T/L 결상관련 회로개선","신온양S/S 345kV 신온양서서울#2 T/L 결상관련 회로개선","2022-05-04 09:00","2022-05-04 18:00","취소","취소","연속"]
[111,"대전세종충남","천안","신온양신탕정#2 T/L","신온양S/S 345kV 신온양신탕정#2T/L 결상관련 회로개선","신온양S/S 345kV 신온양신탕정#2T/L 결상관련 회로개선","2022-05-02 09:00","2022-05-02 18:00","2022-05-02 09:00","2022-05-02 18:00","연속"]
[112,"대전세종충남","천안","신탕정S/S #4 M.Tr","(4월신청취소시)신탕정SS #4 M.Tr 하자보수 및 부분방전보수","(4월신청취소시)신탕정 345kV #4 M.Tr 하자보수 및 부분방전보수","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[113,"대전세종충남","천안","아산S/S #2 M.Tr","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-05-18 09:00","2022-05-23 18:00","2022-05-18 09:00","2022-05-23 18:00","연속"]
[114,"대전세종충남","천안","신서산아산#1 T/L","345kV 아산S/S 취약설비 보강 및 배전반 정비공사","- 모자익배전반 철거 * 1식 - 집중감시제어반+디지탈축소형모자익배전반 설치 *1식","2022-05-16 09:00","2022-06-08 18:00","2022-05-16 09:00","2022-06-08 18:00","연속"]
[115,"대전세종충남","천안","아산보령TP#2 T/L","345kV 아산S/S 취약설비 보강 및 배전반 정비공사","- 모자익배전반 철거 * 1식 - 집중감시제어반+디지탈축소형모자익배전반 설치 *1식","2022-05-16 09:00","2022-06-08 18:00","2022-05-16 09:00","2022-06-08 18:00","연속"]
[116,"대전세종충남","청양","보령C/C SEC CB 70710","345kV 차단기 부동작 예방 조작시험(70-71)","345kV 차단기 부동작 예방 조작시험(70-71)","2022-05-10 09:00","2022-05-10 14:00","2022-05-10 09:00","2022-05-10 14:00","연속"]
[117,"대전세종충남","청양","보령C/C SEC CB 75760","345kV 차단기 부동작 예방 조작시험(75-76)","345kV 차단기 부동작 예방 조작시험(75-76)","2022-05-10 14:00","2022-05-10 18:00","2022-05-10 14:00","2022-05-10 18:00","연속"]
[118,"대전세종충남","청양","보령C/C CB 7271","345kV 차단기 부동작 예방 조작시험(7271)","345kV 차단기 부동작 예방 조작시험(7271)","2022-05-13 14:00","2022-05-13 18:00","2022-05-13 14:00","2022-05-13 18:00","연속"]
[119,"대전세종충남","청양","보령C/C CB 7471","362kV GIS 보통점검","362kV GIS 보통점검","2022-05-11 09:00","2022-05-11 18:00","2022-05-11 09:00","2022-05-11 18:00","연속"]
[120,"대전세종충남","청양","보령C/C CB 7171","345kV 차단기 부동작 예방 조작시험(7171)","345kV 차단기 부동작 예방 조작시험(7171)","2022-05-13 09:00","2022-05-13 14:00","2022-05-13 09:00","2022-05-13 14:00","연속"]
[121,"대전세종충남","청양","신옥천청양 T/L","(4월 취소시)[송전]345kV 신옥천-청양T/L 추락방지장치 설치","(4월 취소시) [송전] 345kV 신옥천-청양T/L 철탑 추락방지장치 설치공사","2022-05-09 08:00","2022-05-13 18:00","취소","취소","매일"]
[122,"대전세종충남","청양","청양신탕정#1 T/L","청양S/S 73BAY B/F PNL 및 청양-신탕정#1T/L 보호반 대체","청양S/S 73BAY B/F PNL 및 청양-신탕정#1T/L 보호반 대체","2022-05-09 09:00","2022-05-18 18:00","취소","취소","연속"]
[123,"대전세종충남","청양","청양군산#2 T/L","청양S/S 73BAY B/F PNL 대체","청양S/S 73BAY B/F PNL 대체","2022-05-09 09:00","2022-05-18 18:00","취소","취소","연속"]
[124,"전북","직할","신남원한빛NP#1 T/L","345kV 신남원-한빛#1T/L 전선접속개소 전력선 교체공사","□ 시공구간 : 345kV 신남원-한빛#1T/L No.179~180, 183~184 구간 □ 시공내용 ○ 전력선, 가공지선 교체(0.603km) : ACSR 480㎟(전력선), ACSR 120㎟(가공지선) ○ 추락방지시설 설치 : 4기[수직,수평(#1T/L)]","2022-05-24 08:00","2022-06-02 17:00","2022-05-23 08:00","2022-05-31 18:00","연속"]
[125,"광주전남","광주","신광주S/S #3 M.Tr","22~23년 광주전력지사 변전협력회사 총액공사","신광주S/S #3M.Tr 1차 7672CB 전자변교체 및 2차 GIS 보통점검 (즉시가압 불가)","2022-05-12 09:00","2022-05-13 18:00","2022-05-12 09:00","2022-05-13 18:00","연속"]
[126,"광주전남","광주","신남원신광주#1 T/L","22년 광주전력 변전협력회사 총액공사 (PNL교체)","- 74 BAY B/F PNL 보호반 교체 (즉시가압 불가)","2022-05-23 09:00","2022-06-03 18:00","2022-05-23 09:00","2022-06-03 18:00","연속"]
[127,"광주전남","광주","신광주S/S #2 M.Tr","22년 광주전력 변전협력회사 총액공사 (PNL교체)","- #2M.Tr 보호반 교체 (즉시가압 불가)","2022-05-14 09:00","2022-05-31 18:00","2022-05-16 09:00","2022-06-03 18:00","연속"]
[128,"광주전남","목포","한빛2N/P #1 BUS","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A CB 9대) × 1식 철거 - 362kV GIS(63kA 6300A CB 9대) × 1식 설치 - 362kV GIS(40kA 4000A #1BUS) × 1식 철거 - 362kV GIS(63kA 6300A #1BUS) × 1식 설치 - 기기기초 보강, 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2022-05-25 09:00","2022-07-03 18:00","2022-05-25 09:00","2022-07-03 18:00","연속"]
[129,"광주전남","목포","한빛1NP한빛2NP#2 T/L","한빛N/P #2S/Y 362kV 장기사용 GIS 대체공사","- 362kV GIS(40kA 4000A CB 9대) × 1식 철거 - 362kV GIS(63kA 6300A CB 9대) × 1식 설치 - 362kV GIS(40kA 4000A #1BUS) × 1식 철거 - 362kV GIS(63kA 6300A #1BUS) × 1식 설치 - 기기기초 보강, 제어케이블 분리 및 결선 × 1식 - 기타 부대공사","2022-05-25 09:00","2022-07-21 18:00","2022-05-25 09:00","2022-07-21 18:00","연속"]
[130,"광주전남","순천","신강진광양#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345Kv 신강진-광양#1T/L GIS(7871) 및 CVT(A, B, C) 하자점검 광양S/S 신강진-광양#1T/L - TIE GIS(7800) 하자점검","2022-05-30 10:00","2022-05-31 18:00","2022-05-09 10:00","2022-05-10 18:00","연속"]
[131,"광주전남","순천","광양S/S #3 M.Tr","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345Kv #3M.Tr 보통점검 광양S/S #3M.Tr 1차 GIS(7772) 하자점검","2022-05-18 10:00","2022-05-20 18:00","2022-05-18 10:00","2022-05-20 18:00","연속"]
[132,"광주전남","순천","광양광양CC#2 T/L","광양S/S 362kV GIS 용량변경 교체공사","광양S/S 362kV GIS 용량변경 교체공사","2022-05-02 10:00","2022-07-29 16:00","취소","취소","연속"]
[133,"광주전남","순천","신강진광양#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345Kv 신강진-광양#2T/L GIS(7771) 광양S/S 신강진-광양21T/L - TIE GIS(7700) 하자점검","2022-05-23 10:00","2022-05-24 18:00","2022-05-23 10:00","2022-05-24 18:00","연속"]
[134,"광주전남","순천","광양광양제철#2 T/L","광양S/S 362kV GIS 용량변경 교체공사","광양S/S 362kV GIS 용량변경 교체공사","2022-05-02 10:00","2022-07-29 16:00","취소","취소","연속"]
[135,"광주전남","순천","광양광양제철#1 T/L","광양S/S 362kV GIS 용량변경 교체공사","광양S/S 362kV GIS 용량변경 교체공사","2022-05-02 10:00","2022-07-29 16:00","취소","취소","연속"]
[136,"광주전남","순천","광양광양CC#1 T/L","광양S/S 362kV GIS 용량변경 교체공사","광양S/S 362kV GIS 용량변경 교체공사","2022-05-02 10:00","2022-07-29 16:00","취소","취소","연속"]
[137,"광주전남","순천","여수T/P #3 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 여수화력S/Y #3M.Tr, 2차 GIS 보통점검 및 1차 CB 타임측정, 7300 CB 타임측정","2022-05-11 10:00","2022-05-12 18:00","취소","취소","연속"]
[138,"광주전남","순천","여수T/P #1 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 345Kv #1M.Tr 보통점검(OFU), 3차 GPT 하자점검","2022-05-02 10:00","2022-05-04 18:00","취소","취소","연속"]
[139,"대구","경산","신경산S/S #4 M.Tr","22~23년 경산PO 변전협력회사 총액공사","- 부싱절연유 채유, 3차 LA, PT 보통점검","2022-05-10 09:30","2022-05-10 18:00","2022-05-10 09:30","2022-05-10 18:00","연속"]
[140,"대구","경산","신경산S/S #3 M.Tr","22~23년 경산PO 변전협력회사 총액공사","- 부싱절연유 채유, 3차 PT 보통점검 - 신경산S/S 345kV #3M.Tr 1차 GIS 누수관련 보수작업","2022-05-11 09:30","2022-05-11 18:00","2022-05-11 09:30","2022-05-11 18:00","연속"]
[141,"대구","달성","신경산대구#1 T/L","#1M.Tr 1차 GIS 정밀점검 무부하가압[TEST 선로]","#1M.Tr 1차 GIS 정밀점검 무부하가압[TEST 선로]","2022-05-20 13:00","2022-05-20 18:00","2022-05-20 13:00","2022-05-20 18:00","연속"]
[142,"대구","달성","대구S/S #1 M.Tr","#1M.Tr OLTC 및 1·2차GIS 정밀점검","#1M.Tr OLTC 및 1·2차GIS 정밀점검","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[143,"대구","칠곡","북대구S/S #1 M.Tr","북대구S/S #1M.Tr 초기점검 / 1,2차 GIS 보통점검","북대구S/S #1M.Tr 초기점검 / 1,2차 GIS 보통점검","2022-05-06 09:30","2022-05-06 18:00","2022-05-06 09:30","2022-05-06 18:00","연속"]
[144,"대구","칠곡","서대구선산#1 T/L","서대구S/S 서대구-선산#1T/L GCB 결상회로보완","서대구S/S 서대구-선산#1T/L GCB 결상회로보완","2022-05-23 09:30","2022-05-23 18:00","2022-05-23 09:30","2022-05-23 18:00","연속"]
[145,"대구","칠곡","서대구선산#2 T/L","서대구S/S 서대구-선산#2T/L GCB 결상회로보완","서대구S/S 서대구-선산#2T/L GCB 결상회로보완","2022-05-24 09:30","2022-05-24 18:00","2022-05-24 09:30","2022-05-24 18:00","연속"]
[146,"대구","칠곡","북경남서대구#2 T/L","서대구S/S 북경남-서대구#2T/L GCB 결상회로보완","서대구S/S 북경남-서대구#2T/L GCB 결상회로보완","2022-05-03 09:30","2022-05-03 18:00","2022-05-03 09:30","2022-05-03 18:00","연속"]
[147,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 사전대비 옥외철구 계탑작업","2022-05-16 09:00","2022-05-18 18:00","2022-05-16 09:00","2022-05-18 18:00","연속"]
[148,"대구","칠곡","서대구고령#2 T/L","서대구S/S 서대구-고령#2T/L GCB 결상회로보완","서대구S/S 서대구-고령#2T/L GCB 결상회로보완","2022-05-04 09:30","2022-05-04 18:00","2022-05-04 09:30","2022-05-04 18:00","연속"]
[149,"대구","칠곡","서대구고령#1 T/L","서대구S/S 서대구-고령#1T/L GCB 결상회로보완","서대구S/S 서대구-고령#1T/L GCB 결상회로보완","2022-05-09 09:30","2022-05-09 18:00","2022-05-09 09:30","2022-05-09 18:00","연속"]
[150,"대구","칠곡","서대구S/S #2 M.Tr","345kV서대구S/S 154kV측 인출T/L 지중화공사","345kV서대구S/S 154kV측 인출T/L 지중화공사(안전확보)","2022-05-02 09:00","2022-05-02 18:00","2022-05-02 09:00","2022-05-02 18:00","연속"]
[151,"대구","칠곡","북경남서대구#1 T/L","서대구S/S 북경남-서대구#1T/L GCB 결상회로보완","서대구S/S 북경남-서대구#1T/L GCB 결상회로보완","2022-05-25 09:30","2022-05-25 18:00","2022-05-25 09:30","2022-05-25 18:00","연속"]
[152,"대구","포항","신포항신월성NP#1 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-05-30 09:00","2022-05-30 18:00","2022-05-18 09:00","2022-05-18 18:00","연속"]
[153,"대구","포항","신포항신월성NP#2 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-05-02 09:00","2022-05-02 18:00","2022-05-02 09:00","2022-05-02 18:00","연속"]
[154,"대구","포항","신포항S/S #2 M.Tr","신포항S/S #2M.Tr 1,2,3차 차단기 점검 및 조작시험","신포항S/S #2M.Tr 1,2,3차 차단기 점검 및 조작시험","2022-05-19 09:00","2022-05-20 18:00","2022-05-19 09:00","2022-05-20 18:00","연속"]
[155,"대구","포항","신포항S/S #4 M.Tr","신포항S/S #4M.Tr 1,2,3차 차단기 점검 및 조작시험","신포항S/S #4M.Tr 1,2,3차 차단기 점검 및 조작시험","2022-05-26 09:00","2022-05-26 18:00","2022-05-26 09:00","2022-05-26 18:00","연속"]
[156,"대구","포항","신울산월성NP#1 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-05-26 09:00","2022-05-26 18:00","2022-05-17 09:00","2022-05-17 18:00","연속"]
[157,"대구","포항","월성NP신월성NP#1 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-05-09 09:00","2022-05-10 18:00","2022-05-09 09:00","2022-05-10 18:00","연속"]
[158,"대구","포항","월성NP신월성NP#2 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-05-23 09:00","2022-05-24 18:00","2022-05-16 09:00","2022-05-16 18:00","연속"]
[159,"대구","포항","울주월성NP#1 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-05-11 09:00","2022-05-11 18:00","2022-05-11 09:00","2022-05-11 18:00","연속"]
[160,"대구","포항","월성N/P CB 7272","월성S/Y 7200, 7272 GIS 정밀점검","월성S/Y 7200, 7272 GIS 정밀점검","2022-05-16 09:00","2022-05-21 18:00","취소","취소","연속"]
[161,"대구","포항","월성N/P CB 7200","월성S/Y 7200, 7272 GIS 정밀점검","월성S/Y 7200, 7272 GIS 정밀점검","2022-05-16 09:00","2022-05-21 18:00","취소","취소","연속"]
[162,"대구","포항","울주월성NP#2 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사 및 무부하가압선로","2022-05-19 09:00","2022-05-21 18:00","취소","취소","연속"]
[163,"대구","포항","월성N/P CB 7671","월성S/Y 7671,7600 GIS 정밀점검","월성S/Y 7671,7600 GIS 정밀점검","2022-05-03 09:00","2022-05-08 18:00","2022-05-23 09:00","2022-05-28 18:00","연속"]
[164,"대구","포항","월성N/P CB 7600","월성S/Y 7671,7600 GIS 정밀점검","월성S/Y 7671,7600 GIS 정밀점검","2022-05-03 09:00","2022-05-08 18:00","2022-05-23 09:00","2022-05-28 18:00","연속"]
[165,"대구","포항","동울산월성NP T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-05-25 09:00","2022-05-25 18:00","2022-05-25 09:00","2022-05-25 18:00","연속"]
[166,"경북","구미","선산S/S #3 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치(콘크리트 타설) 관련 안전이격 확보","2022-05-28 09:00","2022-05-28 18:00","2022-05-28 09:00","2022-05-28 18:00","연속"]
[167,"경북","구미","선산S/S #2 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치(콘크리트 타설) 관련 안전이격 확보","2022-05-27 09:00","2022-05-27 18:00","2022-05-27 09:00","2022-05-27 18:00","연속"]
[168,"경북","구미","선산S/S #1 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치(콘크리트 타설) 관련 안전이격 확보","2022-05-26 09:00","2022-05-26 18:00","2022-05-26 09:00","2022-05-26 18:00","연속"]
[169,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","77bay 교체(모선) / 무부하가압 시험선로","2022-05-31 09:00","2022-05-31 18:00","2022-05-31 09:00","2022-05-31 18:00","연속"]
[170,"경북","구미","서대구선산#1 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치(콘크리트 타설) 관련 안전이격 확보","2022-05-24 09:00","2022-05-24 18:00","취소","취소","연속"]
[171,"경북","구미","서대구선산#2 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치(콘크리트 타설) 관련 안전이격 확보","2022-05-25 09:00","2022-05-25 18:00","취소","취소","연속"]
[172,"경북","구미","선산신포항 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","77bay 교체(모선) / 안전이격확보","2022-05-30 09:00","2022-05-30 18:00","2022-05-30 09:00","2022-05-30 18:00","연속"]
[173,"경북","영주","신제천신영주#2 T/L","2022년도 가공송전순시점검 위탁공사","345kV 신제천-신영주#2T/L 정밀점검","2022-05-23 07:30","2022-05-25 18:00","취소","취소","매일"]
[174,"경북","영주","신영주안동CC T/L","22-23년 영주전력지사 변전협력회사 총액공사","- B/F PNL 대체공사","2022-05-10 09:00","2022-05-13 18:00","2022-05-02 09:00","2022-05-04 18:00","연속"]
[175,"경북","영주","신영주청송PP T/L","2022-23년도 영주전력지사 송전정비회사 총액공사","고정형 폴리머 지지애자 설치공사","2022-05-17 09:00","2022-05-20 18:00","취소","취소","매일"]
[176,"경북","영주","신제천신영주#1 T/L","2022년도 가공송전순시점검 위탁공사","345kV 신제천-신영주#1T/L 정밀점검","2022-05-02 07:30","2022-05-04 18:00","2022-05-02 07:30","2022-05-04 18:00","매일"]
[177,"경북","영주","신영주S/S #3 M.Tr","22-23년 영주전력지사 변전협력회사 총액공사","6871 CB 초기점검 7772 CB 보통점검 부싱절연유 채유 누유조치 인재개발원 현장교육 시행(25~27일)","2022-05-24 09:00","2022-05-27 18:00","2022-05-24 09:00","2022-05-27 18:00","연속"]
[178,"경북","영주","신영주S/S #2 M.Tr","22-23년 영주전력지사 변전협력회사 총액공사","345kV #2M.Tr - 7472 CB보통점검 - 6771 CB 초기점검 - 누유 조치 - B/F PNL 대체공사","2022-05-10 09:00","2022-05-13 18:00","2022-05-10 09:00","2022-05-13 18:00","연속"]
[179,"경북","직할","안동C/C #2 Tie-Tr","22~23년 경북본부 직할 변전정비회사 총액공사","GIS보통점검,SIS 보통점검","2022-05-17 09:00","2022-05-17 18:00","2022-05-17 09:00","2022-05-17 18:00","연속"]
[180,"경북","직할","안동C/C #1 Tie-Tr","22~23년 경북본부 직할 변전정비회사 총액공사","GIS보통점검,SIS 보통점검","2022-05-16 09:00","2022-05-16 18:00","2022-05-16 09:00","2022-05-16 18:00","연속"]
[181,"부산울산","동부산","신양산S/S #4 M.Tr","신양산S/S 345kV M.Tr 3차측 현대화 공사","345kV #4M.Tr 3차측 현대화공사","2022-05-23 09:30","2022-06-24 18:00","취소","취소","연속"]
[182,"부산울산","동부산","신양산신대연#2 T/L","345kV 신양산-신대연 등 7개T/L 자기애관 교체공사","345kV 신양산-신대연T/L 자기애관 교체공사 자기애관2,500㎟을 폴리머애관 2,500㎟으로 변경","2022-05-02 08:00","2022-05-13 18:00","취소","취소","연속"]
[183,"부산울산","북부산","신김해북부산#2 T/L","북부산S/S 345kV 변압기 3차 현대화공사","북부산S/S 345kV #1M.Tr 3차 현대화 공사 시험가압(24h) ※시험가압선로 : 345kV 신김해-북부산#2T/L","2022-05-05 18:00","2022-05-06 18:00","2022-05-05 18:00","2022-05-06 18:00","연속"]
[184,"부산울산","북부산","북부산S/S #2 M.Tr","북부산S/S 345kV M.Tr 3차측 현대화공사","북부산S/S 345kV M.Tr 3차측 현대화공사(2BANK)","2022-05-09 09:00","2022-06-24 18:00","2022-05-09 09:00","2022-06-24 18:00","연속"]
[185,"부산울산","서부산","신김해신녹산#2 T/L","신김해신녹산#2 T/L 결상회로 성능개선 작업","신김해신녹산#2 T/L 결상회로 성능개선 작업 병행작업 : 7371, 7300 GIS 차단기 동작시험","2022-05-03 10:00","2022-05-03 18:00","취소","취소","연속"]
[186,"부산울산","서부산","신녹산S/S #2 M.Tr","2022년 상반기 서부산전력지사 관내 154kV GIS 정밀점검공사","2022년 상반기 서부산전력지사 관내 154kV GIS 정밀점검공사","2022-05-26 09:00","2022-05-27 18:00","2022-05-25 09:00","2022-05-26 18:00","연속"]
[187,"부산울산","울산","남울산S/S CB 7572","22~23년 변전협력회사 총액공사","GIS(7572) 하자점검","2022-05-18 09:00","2022-05-18 18:00","2022-05-18 09:00","2022-05-18 18:00","연속"]
[188,"부산울산","울산","남울산S/S CB 7372","22~23년 변전협력회사 총액공사","GIS(7372) 하자점검","2022-05-04 09:00","2022-05-04 18:00","2022-05-04 09:00","2022-05-04 18:00","연속"]
[189,"부산울산","울산","신온산S/S #2 M.Tr","신온산S/S 345kV #2M.Tr 3차 현대화 공사","M.Tr 3차 현대화공사","2022-05-19 09:00","2022-06-24 18:00","2022-05-19 09:00","2022-06-24 18:00","연속"]
[190,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","73BAY #2BUS(7352DS) 시험가압","2022-05-16 13:30","2022-05-16 17:00","2022-05-16 13:30","2022-05-16 17:00","연속"]
[191,"부산울산","울산","신온산S/S #1 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","73BAY #1BUS(7351DS) 시험가압","2022-05-16 13:00","2022-05-16 13:30","2022-05-16 13:00","2022-05-16 13:30","연속"]
[192,"부산울산","울산","신울산S/S #75 BUS","신울산S/S 345kV 차단기 용량대체공사","345kV #2M.Tr 1차측 인출 변경 관련 안전이격거리 확보","2022-05-19 09:00","2022-05-19 18:00","2022-05-12 09:00","2022-05-12 18:00","연속"]
[193,"부산울산","울산","신울산S/S #70 BUS","신울산S/S 345kV 차단기 용량대체공사","345kV #2M.Tr 1차측 인출 변경 관련 안전이격거리 확보","2022-05-18 09:00","2022-05-18 18:00","2022-05-11 09:00","2022-05-11 18:00","연속"]
[194,"부산울산","울산","신울산고리NP#2 T/L","신울산S/S 345kV 차단기 용량대체공사","345kV GIS 대체 관련 송전선로 접속지점 변경 시 안전이격거리 확보","2022-05-16 09:00","2022-05-17 18:00","2022-05-16 09:00","2022-05-17 18:00","연속"]
[195,"부산울산","울산","신울산S/S #4 M.Tr","신울산S/S 345kV 차단기 용량대체공사","345kV #3M.Tr 겐트리타워 설치 관련 안전이격거리 확보","2022-05-02 09:00","2022-05-04 18:00","취소","취소","연속"]
[196,"부산울산","울산","북부산신울산#1 T/L","신울산S/S 345kV 차단기 용량대체공사","345kV GIS 대체 관련 송전선로 접속지점 변경(구 74BAY → 신 75BAY) 345kV GIS 대체 관련 보호배전반 이설 및 연동시험","2022-05-02 09:00","2022-05-27 18:00","2022-05-09 09:00","2022-06-10 18:00","연속"]
[197,"부산울산","울산","울산C/C #1 BUS","울산복합S/Y 345kV 보호제어설비 전담운영공사","울산복합S/Y 345kV 보호제어설비 전담운영공사","2022-05-18 09:00","2022-05-23 18:00","2022-05-18 09:00","2022-05-23 18:00","연속"]
[198,"부산울산","울산","울산C/C CB 7500, 7572","울산복합S/Y 345kV 보호제어설비 전담운영공사","울산복합S/Y 345kV 보호제어설비 전담운영공사 병행) 남울산S/S 송전선로 보호반 대체","2022-05-30 09:00","2022-06-10 18:00","2022-05-30 09:00","2022-06-10 18:00","연속"]
[199,"부산울산","울산","남울산울산TP#1 T/L","울산복합S/Y 345kV 보호제어설비 전담운영공사","울산복합S/Y 345kV 보호제어설비 전담운영공사 병행1) 남울산S/S 송전선로 보호반 대체 병행2) 남울산S/S 7371, 7300 GIS 하자점검","2022-05-30 09:00","2022-06-10 18:00","2022-05-30 09:00","2022-06-10 18:00","연속"]
[200,"부산울산","울산","울산C/C #2 BUS","울산복합S/Y 345kV 보호제어설비 전담운영공사","울산복합S/Y 345kV 보호제어설비 전담운영공사","2022-05-24 09:00","2022-05-27 18:00","2022-05-24 09:00","2022-05-27 18:00","연속"]
[201,"경남","직할","신김해북부산#1 T/L","신김해S/S 신김해-북부산#1T/L GIS 보통점검","신김해S/S 신김해-북부산#1T/L GIS 보통점검 (병행)PT 초기점검","2022-05-31 09:30","2022-05-31 17:30","2022-05-31 09:30","2022-05-31 17:30","연속"]
[202,"경남","직할","창원S/S #1 M.Tr","창원S/S #1M.Tr 보통점검","창원S/S #1M.Tr 보통점검 (병행)7172, 6144 보통점검","2022-05-02 09:30","2022-05-03 18:00","2022-05-02 09:30","2022-05-03 18:00","연속"]
[203,"경남","직할","창원S/S #2 M.Tr","창원S/S #2M.Tr 보통점검","창원S/S #2M.Tr 보통점검 (병행)7272, 6244 보통점검","2022-05-16 09:30","2022-05-17 18:00","2022-05-16 09:30","2022-05-17 18:00","연속"]
[204,"경남","진주","의령신마산#2 T/L","의령S/S 7ABAY 신마산#2T/L LA(ABC) 교체","의령S/S 7ABAY 신마산#2T/L LA(ABC) 교체","2022-05-23 09:00","2022-05-23 18:00","2022-05-23 09:00","2022-05-23 18:00","연속"]
[205,"경남","진주","의령신마산#1 T/L","의령S/S 79BAY 신마산#1T/L LA(ABC) 대체","[병행] TIE(7900) GIS 누기조치","2022-05-12 09:00","2022-05-12 18:00","2022-05-12 09:00","2022-05-12 18:00","연속"]
[206,"경남","진주","하동T/P CB 7572","하동T/P 75BAY #5M.Tr(7572) GIS 조작시험","하동T/P 75BAY #5M.Tr(7572) GIS 조작시험","2022-05-16 09:00","2022-05-16 15:00","2022-05-16 09:00","2022-05-16 15:00","연속"]
[207,"경남","진주","하동T/P CB 7671","하동T/P 76BAY T/L(7671),TIE(7600) GIS 조작시험","하동T/P 76BAY 광양#2T/L(7671), TIE(7600) GIS 조작시험","2022-05-04 09:00","2022-05-04 14:00","2022-05-04 09:00","2022-05-04 14:00","연속"]
[208,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 철탑 추락방지시설 설치공사","○ 345kV 의령-하동화력#2T/L 철탑 추락방지시설 설치공사 - 수직 추락방지시설 설치 : No.2~134호 - 수평 추락방지시설 설치 : No.2~91호 (#2T/L 측)","2022-05-09 07:00","2022-05-17 18:00","2022-05-09 07:00","2022-05-17 18:00","연속"]
[209,"경남","진주","하동T/P CB 7600","하동T/P 76BAY T/L(7671),TIE(7600) GIS 조작시험","하동T/P 76BAY 광양#2T/L(7671), TIE(7600) GIS 조작시험","2022-05-04 14:00","2022-05-04 18:00","2022-05-04 14:00","2022-05-04 18:00","연속"]
[210,"경남","함안","북경남S/S #5 Sh.R (CB 7779)","북경남S/S 345kV #5Sh.R 1차 선로측 GIS 보통점검","북경남S/S 345kV #5Sh.R 1차 선로측 GIS 보통점검","2022-05-26 09:30","2022-05-26 17:30","취소","취소","연속"]
[211,"경남","함안","북경남서대구#1 T/L","북경남서대구#1 T/L 단상재폐로관련 회로개선","북경남서대구#1 T/L 단상재폐로관련 회로개선","2022-05-25 09:30","2022-05-25 17:30","2022-05-25 09:30","2022-05-25 17:30","연속"]
[212,"경남","함안","북경남고령#1 T/L","북경남고령#1 T/L 단상재폐로관련 회로개선","북경남고령#1 T/L 단상재폐로관련 회로개선","2022-05-24 09:30","2022-05-24 17:30","2022-05-24 09:30","2022-05-24 17:30","연속"]
[213,"경남","함안","북경남S/S CB 7771","북경남S/S 345kV #5Sh.R 1차 GIS 보통점검","북경남S/S 345kV #5Sh.R 1차 GIS 보통점검","2022-05-27 09:30","2022-05-27 17:30","취소","취소","연속"]
[214,"경남","함안","신마산S/S #4 M.Tr","신마산S/S 345kV #4 M.Tr 정밀점검","신마산S/S 345kV #4 M.Tr 정밀점검","2022-05-24 09:30","2022-05-27 17:30","2022-05-23 09:30","2022-05-26 17:30","연속"]
[215,"경남","함안","신마산신김해#2 T/L","345kV 신마산-신김해T/L 57~62호간 전선교체공사","57~62호간 전선교체","2022-05-28 07:00","2022-05-31 19:00","취소","취소","연속"]
[216,"경남","함안","신마산신김해#1 T/L","345kV 신마산-신김해T/L 57~62호간 전선교체공사","57~62호간 전선교체","2022-05-24 07:00","2022-05-27 19:00","취소","취소","연속"]
[217,"부산울산",null,"고리N/P #1호기 주변압기 (CB 7200, 7272)","고리1호기 제2차 영구정지 정기검사 * 조작차단기 : CB 7200, CB 7272 (DS 7222, DS 7201, DS 7202, DS 7262, DS 7252, ES 7292)","○ 고리1호기 주변압기 및 UAT 정밀점검","2022-05-30 09:00","2022-06-30 18:00","2022-05-30 09:00","2022-06-30 18:00","연속"]
[218,"대구",null,"월성N/P #1호기 주변압기 (CB 7671, 7600)","월성 1호기 안전유지설비점검 관련 MOT 휴전 *조작차단기 : CB7671,7600","○ MOT 정밀점검 ○ SWYD 7671, 7600 차단기 정밀점검 ○ MOT 전력량계 교체","2022-05-02 09:00","2022-05-11 18:00","2022-05-30 09:00","2022-09-01 18:00","연속"]
[219,"대구",null,"월성N/P #1 기동용 변압기 (CB 7200, 7272)","월성 1호기 안전유지설비점검 관련 SST 휴전 *조작차단기 : CB7272,7200","○ SST 정밀점검 ○ SWYD 7272, 7200 차단기 정밀점검 ○ SST 전력량계 교체","2022-05-12 09:00","2022-05-25 18:00","2022-05-23 09:00","2022-05-31 18:00","연속"]
[220,"대구",null,"월성N/P #1호기 주변압기 (CB 7671, 7600)","월성 1호기 안전유지설비점검 관련 전원절체시험 *조작차단기 : CB7671,7600","○ UST<->SST 소내전원절체시험","2022-05-26 09:00","2022-05-31 18:00","2022-05-23 09:00","2022-05-24 18:00","연속"]
[221,"광주전남",null,"한빛2NP #3호기 기동변압기 (CB 7571, 7500)","한빛3호기 18차 계획예방정비 * 조작차단기 : CB 7500, 7571","○ 한빛3호기 기동변압기 가스절연모선 교체 ○ 한빛3호기 CV Cable 설비개선 ○ 스위치야드 GIS 75 Bay 교체","2022-05-25 10:00","2022-07-24 23:59","2022-05-25 10:00","2022-07-24 23:59","연속"]
[222,"광주전남",null,"한빛2NP #1 BUS","한빛3호기 18차 계획예방정비 * 조작차단기 : CB 7A71, 7971, 7871, 7771, 7671, 7571","○ 한빛3호기 스위치야드 Main bus #1교체","2022-05-25 10:00","2022-06-29 23:59","취소","취소","연속"]
[223,"대전세종충남",null,"신보령T/P #1호기 주변압기 (CB 7100, 7172)","발전기 간이정비 및 주변압기 중성점 접속부 점검","발전기 간이정비 및 주변압기 중성점 접속부 점검","2022-05-30 09:00","2022-06-02 18:00","2022-05-30 09:00","2022-06-02 18:00","연속"]
[224,"인천","부평","신가좌신시흥#2 T/L","송전철탑 추락방지시설 설치","345kV 신가좌-신시흥#2T/L 송전철탑 추락방지시설 설치","2022-05-21 08:00","2022-05-22 18:00","2022-05-21 08:00","2022-05-22 18:00","연속"]
[225,"광주전남",null,"율촌C/C GT4호기 주변압기 (CB 7100,7172)","주변압기 점검","주변압기 점검","2022-05-19 09:00","2022-05-22 18:00","2022-05-19 09:00","2022-05-22 18:00","연속"]
[226,"광주전남",null,"율촌C/C ST2호기 주변압기 (CB 7200,7272)","주변압기 점검","주변압기 점검","2022-05-19 09:00","2022-05-22 18:00","2022-05-19 09:00","2022-05-22 18:00","연속"]
[227,"강원",null,"양양P/P #1,2,3,4호기 주변압기 (CB 7100,7172,7271,7200,7272,7300,7372)","자체기동 발전기 예비시험","자체기동 발전기 예비시험","2022-05-06 11:00","2022-05-06 13:00","2022-05-06 11:00","2022-05-06 13:00","연속"]
[228,"강원",null,"양양P/P #3호기 주변압기 (CB 7200,7272)","계획중간정비","계획중간정비","2022-05-07 09:00","2022-05-07 18:00","2022-05-07 09:00","2022-05-07 18:00","연속"]
[229,"강원",null,"양양P/P #2호기 주변압기 (CB 7271,7200)","계획중간정비","계획중간정비","2022-05-11 09:00","2022-05-11 18:00","2022-05-11 09:00","2022-05-11 18:00","연속"]
[230,"경북",null,"청송P/P #1,2호기 주변압기 (CB 7100,7172,7200,7272)","자체기동 발전기 예비시험","자체기동 발전기 예비시험","2022-05-11 10:00","2022-05-11 13:00","2022-05-11 10:00","2022-05-11 13:00","연속"]
[231,"강원",null,"양양P/P #1,2,3,4호기 주변압기 (CB 7100,7172,7271,7200,7272,7300,7372)","자체기동 발전기 정기시험","자체기동 발전기 정기시험","2022-05-13 11:00","2022-05-13 13:00","2022-05-13 11:00","2022-05-13 13:00","연속"]
[232,"강원",null,"양양P/P #4호기 주변압기 (CB 7300,7372)","계획중간정비","계획중간정비","2022-05-17 09:00","2022-05-17 18:00","2022-05-17 09:00","2022-05-17 18:00","연속"]
[233,"경북",null,"청송P/P #1,2호기 주변압기 (CB 7100,7172,7200,7272)","자체기동 발전기 정기시험","자체기동 발전기 정기시험","2022-05-20 10:00","2022-05-20 13:00","2022-05-20 10:00","2022-05-20 13:00","연속"]
[234,"경남",null,"산청P/P #1호기 주변압기 (CB 7100,7172)","전기설비 점검 및 하부댐 보수","전기설비 점검 및 하부댐 보수","2022-05-30 09:00","2022-06-16 23:59","2022-05-30 09:00","2022-06-16 23:59","연속"]

{"sheet":"154설비","index":2,"n_rows":530,"n_cols":11,"rows_kept":530,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 5월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","방학창동#2 T/L","2022년 성동P/O 154kV GIS 정밀점검공사","창동S/S 방학창동#2T/L GIS 정밀점검 공사","2022-05-02 09:30","2022-05-03 18:00","2022-05-02 09:30","2022-05-03 18:00","연속"]
[2,"서울","중부","옥인운니#2 T/L","OF케이블 절연유 채유","옥인운니#2T/L OF케이블 절연유분석 시료 채취","2022-05-03 09:30","2022-05-03 11:30","2022-05-03 09:30","2022-05-03 11:30","연속"]
[3,"서울","중부","지축현저#1 T/L","2022년 서울본부 가공송전 순시점검 위탁공사","지축-현저T/L No.4,4.1(2기) 철탑 정밀점검","2022-05-04 07:30","2022-05-04 13:00","2022-05-04 07:30","2022-05-04 13:00","연속"]
[4,"서울","성동","구리신내#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-05-04 10:00","2022-05-04 18:00","2022-05-04 10:00","2022-05-04 18:00","연속"]
[5,"서울","중부","지축현저#2 T/L","2022년 서울본부 가공송전 순시점검 위탁공사","지축-현저T/L No.4,4.1(2기) 철탑 정밀점검","2022-05-04 13:00","2022-05-04 18:00","2022-05-04 13:00","2022-05-04 18:00","연속"]
[6,"서울","성동","양주쌍문#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","1. 양주-쌍문T/L No.28~38(9기) 추락방지시설 설치공사 2. 양주-쌍문T/L No.28~38(11기) 송전피뢰기 설치공사","2022-05-09 07:30","2022-05-09 18:00","2022-06-13 07:30","2022-06-13 18:00","연속"]
[7,"서울","성동","양주쌍문#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","양주-쌍문T/L No.28~38(9기) 추락방지시설 설치공사","2022-05-10 07:30","2022-05-10 18:00","2022-06-14 07:30","2022-06-14 18:00","연속"]
[8,"서울","중부","중부당인리#1 T/L","'22-'23중부P/O 변전협력회사 총액공사","170kV CB 조작시험","2022-05-10 10:00","2022-05-10 17:00","2022-05-10 10:00","2022-05-10 17:00","연속"]
[9,"서울","직할","서소문S/S #1 BUS","22년 변전협력 총액","-PT 점검","2022-05-10 10:00","2022-05-10 15:00","2022-05-10 10:00","2022-05-10 15:00","연속"]
[10,"서울","직할","서소문S/S CB 6100","22년 변전협력 총액","GIS 보통점검","2022-05-10 10:00","2022-05-10 18:00","2022-05-10 10:00","2022-05-10 18:00","연속"]
[11,"서울","직할","서소문S/S #2 BUS","22년 변전협력 총액","-PT 점검","2022-05-10 15:00","2022-05-10 18:00","2022-05-10 15:00","2022-05-10 18:00","연속"]
[12,"서울","성동","금오상계#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","금오-상계T/L No.37~54(13기) 추락방지시설 설치공사","2022-05-11 07:30","2022-05-11 18:00","2022-06-16 07:30","2022-06-16 18:00","연속"]
[13,"서울","중부","중부당인리#2 T/L","'22-'23중부P/O 변전협력회사 총액공사","170kV CB 조작시험","2022-05-11 10:00","2022-05-11 17:00","2022-05-11 10:00","2022-05-11 17:00","연속"]
[14,"서울","직할","서소문S/S CB 6100","22년 변전협력 총액(모선보호반대체)","모선보호반 대체","2022-05-11 10:00","2022-05-13 18:00","2022-05-11 10:00","2022-05-13 18:00","연속"]
[15,"서울","성동","금오상계#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","금오-상계T/L No.37~54(13기) 추락방지시설 설치공사","2022-05-12 07:30","2022-05-12 18:00","2022-06-17 07:30","2022-06-17 18:00","연속"]
[16,"서울","직할","운니원남#1 T/L","22년 170kV GIS 정밀점검","-6100B/T 시험가압","2022-05-13 10:00","2022-05-13 18:00","취소","취소","연속"]
[17,"서울","성동","노원종암 T/L","2021~2022년 성동전력 지중송전 위탁정비공사","노원S/S 노원종암T/L EBG 가스채취밸브 설치공사","2022-05-16 09:00","2022-05-17 18:00","2022-05-16 09:00","2022-05-17 18:00","연속"]
[18,"서울","성동","구리신내#2 T/L","2022년 성동P/O 154kV GIS 정밀점검공사","신내S/S 구리신내#2T/L #1DS 링크 교체","2022-05-16 09:30","2022-05-17 18:00","2022-05-16 09:30","2022-05-17 18:00","연속"]
[19,"서울","성동","쌍문S/S #1 BUS","22년 성동 변전협력회사 총액공사","쌍문S/S 154kV PT 집합반 설치","2022-05-16 10:00","2022-05-16 18:00","2022-05-16 10:00","2022-05-16 18:00","연속"]
[20,"서울","성동","쌍문S/S CB 6100","22년 성동 변전협력회사 총액공사","쌍문S/S 154kV PT 집합반 설치","2022-05-16 10:00","2022-05-17 18:00","2022-05-16 10:00","2022-05-17 18:00","연속"]
[21,"서울","직할","원남미아#1 T/L","22년 170kV GIS 정밀점검","22년 170kV GIS 정밀점검","2022-05-16 10:00","2022-05-18 18:00","취소","취소","연속"]
[22,"서울","중부","상암등촌#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","1. 상암-등촌T/L No.3, No.7(2기) 추락방지시설 설치공사 2. 상암-등촌T/L No.2~6(5기) 송전피뢰기 설치공사","2022-05-17 07:30","2022-05-17 13:00","2022-06-15 07:30","2022-06-15 13:00","연속"]
[23,"서울","성동","쌍문S/S #2 BUS","22년 성동 변전협력회사 총액공사","쌍문S/S 154kV PT 집합반 설치","2022-05-17 10:00","2022-05-17 18:00","2022-05-17 10:00","2022-05-17 18:00","연속"]
[24,"서울","중부","상암등촌#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","상암-등촌T/L No.3, No.7 추락방지시설 설치공사","2022-05-17 13:00","2022-05-17 18:00","2022-06-15 13:00","2022-06-15 18:00","연속"]
[25,"서울","성동","쌍문수유 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-05-18 10:00","2022-05-18 18:00","2022-05-18 10:00","2022-05-18 18:00","연속"]
[26,"서울","직할","원남미아#2 T/L","22년 170kV GIS 정밀점검","22년 170kV GIS 정밀점검","2022-05-18 10:00","2022-05-20 18:00","취소","취소","연속"]
[27,"서울","중부","원흥수색#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","1. 원흥-수색T/L No.1~2(4기) 추락방지시설 설치공사 2. 원흥-수색T/L No.1~2(4기) 송전피뢰기 설치공사","2022-05-19 07:30","2022-05-20 18:00","2022-06-23 07:30","2022-06-24 18:00","연속"]
[28,"서울","성동","노원종암 T/L","2022년 성동P/O 154kV GIS 정밀점검공사(시험가압)","종암S/S #3M.Tr #1, 2DS 링크 교체 시험가압용","2022-05-19 13:00","2022-05-19 14:00","2022-05-19 13:00","2022-05-19 14:00","연속"]
[29,"서울","성동","성동휘경#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-05-20 10:00","2022-05-20 17:00","2022-05-20 10:00","2022-05-20 17:00","연속"]
[30,"서울","성동","노원종암 T/L","2022년 성동P/O 154kV GIS 정밀점검공사(시험가압)","종암S/S #3M.Tr #1, 2DS 링크 교체 시험가압용","2022-05-20 13:00","2022-05-20 14:00","2022-05-20 13:00","2022-05-20 14:00","연속"]
[31,"서울","성동","휘경종암#1 T/L","안암 및 휘경변전소 인출 OF케이블 선종교체공사","1. 공사명 : 안암 및 휘경변전소 인출 OF케이블 선종교체공사 2. 대상선로 : 휘경종암#1, 2T/L 3. 공사내용 : 변전소내 화재확산 방지 OF→XLPE 선종교체 4. 공사구간 : 종단접속함(EBG)~첫번째 접속함 구간","2022-05-23 09:00","2022-07-01 18:00","2022-05-23 09:00","2022-07-01 18:00","연속"]
[32,"서울","성동","창동쌍문#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검 (양단)","2022-05-23 10:00","2022-05-23 18:00","2022-05-23 10:00","2022-05-23 18:00","연속"]
[33,"서울","직할","운니원남#2 T/L","22년 170kV GIS 정밀점검","22년 170kV GIS 정밀점검","2022-05-23 10:00","2022-05-25 18:00","취소","취소","연속"]
[34,"서울","중부","양주은평#1 T/L","154kV 양주-은평T/L No.14 안전이격확보공사","1. 양주-은평T/L No.14 안전이격확보공사 2. 양주-은평T/L No.31~33(3기) 추락방지시설 설치공사","2022-05-24 07:30","2022-06-01 18:00","취소","취소","연속"]
[35,"서울","직할","운니원남#1 T/L","22년 170kV GIS 정밀점검","22년 170kV GIS 정밀점검","2022-05-25 09:00","2022-05-27 18:00","취소","취소","연속"]
[36,"서울","중부","수색S/S CB 6100","'22-'23중부P/O 변전협력회사 총액공사","170kV GCB 초기점검","2022-05-25 10:00","2022-05-25 17:00","2022-05-25 10:00","2022-05-25 17:00","연속"]
[37,"서울","중부","동빙고반포#1 T/L","'22-'23중부P/O 변전협력회사 총액공사","170kV GIS 보통점검","2022-05-26 10:00","2022-05-26 17:00","2022-05-26 10:00","2022-05-26 17:00","연속"]
[38,"서울","성동","신내상봉 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검 (양단)","2022-05-27 09:30","2022-05-27 18:00","2022-05-27 09:30","2022-05-27 18:00","연속"]
[39,"서울","중부","동빙고반포#2 T/L","'22-'23중부P/O 변전협력회사 총액공사","170kV GIS 보통점검","2022-05-27 10:00","2022-05-27 17:00","2022-05-27 10:00","2022-05-27 17:00","연속"]
[40,"서울","성동","쌍문미아 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-05-30 10:00","2022-05-30 18:00","2022-05-30 10:00","2022-05-30 18:00","연속"]
[41,"서울","중부","용산동빙고 T/L","'22년 중부P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검 병행(이주연)","2022-05-30 10:00","2022-05-31 17:00","2022-05-30 10:00","2022-05-31 17:00","연속"]
[42,"서울","성동","창동쌍문#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검 (양단)","2022-05-31 10:00","2022-05-31 18:00","2022-05-31 10:00","2022-05-31 18:00","연속"]
[43,"남서울","강남","신양재과천#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검","2022-05-19 08:00","2022-05-20 18:00","2022-05-19 08:00","2022-05-20 18:00","연속"]
[44,"남서울","강남","신양재신사#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검","2022-05-16 08:00","2022-05-18 18:00","2022-05-16 08:00","2022-05-18 18:00","연속"]
[45,"남서울","강남","신양재개포 T/L","154kV 신양재-개포T/L 신양재EBG 해체점검","지중송전 종단접속함(EBG) 고장관련 재발방지 대책으로 대한전선제 EBG 해체점검 및 부품교체(열경화공법을 다듬질공법으로 변경)","2022-05-16 09:00","2022-05-26 18:00","취소","취소","연속"]
[46,"남서울","동서울","가락동남 T/L","가락,동남S/S 가락-동남T/L 보호반대체공사","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-05-16 09:00","2022-05-19 18:00","2022-05-16 09:00","2022-05-19 18:00","연속"]
[47,"남서울","동서울","동남수서 T/L","동남,수서S/S 동남-수서T/L 보호반대체공사","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-05-23 09:00","2022-05-26 18:00","2022-05-23 09:00","2022-05-26 18:00","연속"]
[48,"남서울","동서울","동서울S/S #67 BUS","동서울S/S 노후 주변압기 교체 및 이설공사","○ 노후 주변압기 11대 교체 및 이설","2022-05-06 14:00","2022-05-06 16:00","2022-05-10 14:00","2022-05-10 16:00","연속"]
[49,"남서울","동서울","강동상일#1 T/L","상일SS 강동-상일1TL 정밀점검(강동SS : 조작시험)","170kV GIS 정밀점검공사","2022-05-04 09:00","2022-05-06 18:00","2022-05-04 09:00","2022-05-06 18:00","연속"]
[50,"남서울","동서울","상일S/S CB 6100","상일SS 6100 BUS TIE CB 정밀점검공사","170kV GIS 정밀점검공사","2022-05-11 09:00","2022-05-13 14:00","취소","취소","연속"]
[51,"남서울","동서울","상일S/S CB 6100","상일SS #1M.Tr 1차 GIS(6133) 정밀점검공사 무부하가압","170kV GIS 정밀점검공사 무부하가압","2022-05-18 14:00","2022-05-18 18:00","취소","취소","연속"]
[52,"남서울","동서울","상일S/S CB 6100","상일SS #2M.Tr 1차 GIS(6233) 정밀점검공사 무부하가압","170kV GIS 정밀점검공사 무부하가압","2022-05-21 14:00","2022-05-21 18:00","취소","취소","연속"]
[53,"남서울","동서울","강동상일#2 T/L","상일SS 강동-상일2TL 정밀점검(강동SS : 조작시험)","170kV GIS 정밀점검공사","2022-05-07 09:00","2022-05-09 18:00","2022-05-07 09:00","2022-05-09 18:00","연속"]
[54,"남서울","동서울","잠실수서#1 T/L","잠실SS 잠실-수서1TL 정밀점검 및 조작시험","170kV GIS 정밀점검공사","2022-05-30 09:00","2022-05-31 14:00","2022-05-30 09:00","2022-05-31 14:00","연속"]
[55,"남서울","동서울","잠실탄천#1 T/L","잠실SS 잠실-탄천1TL 정밀점검","170kV GIS 정밀점검공사","2022-05-23 09:00","2022-05-24 14:00","2022-05-23 09:00","2022-05-24 14:00","연속"]
[56,"남서울","동서울","잠실탄천#2 T/L","잠실SS 잠실-탄천2TL 정밀점검","170kV GIS 정밀점검공사","2022-05-25 09:00","2022-05-26 14:00","2022-05-25 09:00","2022-05-26 14:00","연속"]
[57,"남서울","영등포","마곡S/S CB 6100","'22~23년 영등포P/O 변전협력회사 총액공사","- 154kV GIS 보통점검(6100 B/T)","2022-05-17 09:00","2022-05-17 18:00","2022-05-17 09:00","2022-05-17 18:00","연속"]
[58,"남서울","영등포","마곡가양#2 T/L","`22~23년 영등포P/O 변전협력회사 총액공사","154kV 마곡-가양#2T/L 보통점검","2022-05-22 09:00","2022-05-22 18:00","2022-05-22 09:00","2022-05-22 18:00","연속"]
[59,"남서울","영등포","마곡가양#1 T/L","`22~23년 영등포P/O 변전협력회사 총액공사","154kV 마곡-가양#1T/L 보통점검","2022-05-21 09:00","2022-05-21 18:00","2022-05-21 09:00","2022-05-21 18:00","연속"]
[60,"남서울","영등포","신정목동#2 T/L","영등포전력지사 154kV GIS 정밀점검공사","- 154kV 신정-목동#2T/L GIS 정밀점검","2022-05-16 09:00","2022-05-18 18:00","2022-05-21 09:00","2022-05-22 18:00","연속"]
[61,"남서울","영등포","신문래목동#2 T/L","영등포전력지사 154kV GIS 정밀점검공사","- 154kV 신문래-목동#2T/L GIS 정밀점검","2022-05-19 09:00","2022-05-21 18:00","2022-05-18 09:00","2022-05-20 18:00","연속"]
[62,"남서울","영등포","고강화곡#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","- 화곡S/S 154kV 고강-화곡#1T/L GIS 정밀점검","2022-05-23 09:00","2022-05-25 18:00","2022-05-24 09:00","2022-05-26 18:00","연속"]
[63,"남서울","영등포","고강화곡#2 T/L","영등포전력지사 154kV GIS 정밀점검공사","- 화곡S/S 154kV 고강-화곡#2T/L GIS 정밀점검","2022-05-29 09:00","2022-05-31 18:00","2022-05-29 09:00","2022-05-31 18:00","연속"]
[64,"남서울","영등포","고강화곡#3 T/L","`22~23년 영등포P/O 변전협력회사 총액공사","154kV 고강-화곡#3T/L 조작시험","2022-05-13 09:00","2022-05-13 18:00","2022-05-13 09:00","2022-05-13 18:00","연속"]
[65,"남서울","직할","대방신길#2 T/L","170kV GIS 정밀점검공사(대방-신길#2T/L)","170kV GIS 정밀점검공사(대방-신길#2T/L)","2022-05-02 09:00","2022-05-03 18:00","2022-05-02 09:00","2022-05-03 18:00","연속"]
[66,"남서울","직할","신길S/S #1 BUS","170kV GIS 정밀점검 무부하가압(#1BUS)","170kV GIS 정밀점검 무부하가압(#1BUS)","2022-05-11 11:00","2022-05-11 14:00","2022-05-10 15:00","2022-05-10 18:00","연속"]
[67,"남서울","직할","봉천신길#1 T/L","170kV GIS 정밀점검공사(봉천-신길#1T/L)","170kV GIS 정밀점검공사(봉천-신길#1T/L)","2022-05-04 09:00","2022-05-06 18:00","2022-05-04 09:00","2022-05-06 18:00","연속"]
[68,"남서울","직할","대방신길#1 T/L","170kV GIS 정밀점검 무부하가압(#1BUS)","170kV GIS 정밀점검 무부하가압(#1BUS)","2022-05-13 15:00","2022-05-13 18:00","2022-05-12 15:00","2022-05-12 18:00","연속"]
[69,"남서울","직할","신길S/S #1 BUS","170kV GIS 정밀점검 무부하가압(#1BUS)","170kV GIS 정밀점검 무부하가압(#1BUS)","2022-05-13 15:00","2022-05-13 18:00","2022-05-12 15:00","2022-05-12 18:00","연속"]
[70,"남서울","직할","대방신길#1 T/L","170kV GIS 정밀점검 무부하가압(#1BUS)","170kV GIS 정밀점검 무부하가압(#1BUS)","2022-05-11 11:00","2022-05-11 14:00","2022-05-10 15:00","2022-05-10 18:00","연속"]
[71,"인천","부평","신경서경서#1 T/L","신경서경서#1 T/L GIS 보통점검","신경서경서#1 T/L GIS 보통점검 -경서S/S 신경서경서#1 T/L GIS 조작시험 병행","2022-05-02 09:00","2022-05-02 18:00","2022-05-02 09:00","2022-05-02 18:00","연속"]
[72,"인천","시흥","온수소래 T/L","소래S/S 154kV 온수소래 T/L 보호반 대체","소래S/S 154kV 온수소래 T/L 보호반 대체","2022-05-02 09:00","2022-05-06 18:00","2022-05-02 09:00","2022-05-06 18:00","연속"]
[73,"인천","직할","갈산부흥#1 T/L","갈산S/S 갈산부흥#1T/L GIS 하자점검(양단)","갈산S/S 갈산부흥#1T/L GIS 하자점검(양단)","2022-05-02 09:30","2022-05-02 18:00","2022-05-02 09:30","2022-05-02 18:00","연속"]
[74,"인천","부평","신경서경서#2 T/L","신경서경서#2 T/L GIS 보통점검","신경서경서#2 T/L GIS 보통점검 -경서S/S 신경서경서#2 T/L GIS 조작시험 병행","2022-05-03 09:00","2022-05-03 18:00","2022-05-03 09:00","2022-05-03 18:00","연속"]
[75,"인천","직할","갈산부흥#2 T/L","갈산S/S 갈산부흥#2T/L GIS 하자점검(양단)","갈산S/S 갈산부흥#2T/L GIS 하자점검(양단)","2022-05-03 09:30","2022-05-03 18:00","2022-05-03 09:30","2022-05-03 18:00","연속"]
[76,"인천","김포","신경서경서#3 T/L","경서S/S 154kV 신경서-경서#3T/L GIS 조작시험","경서S/S 154kV 신경서-경서#3T/L GIS 조작시험","2022-05-04 09:00","2022-05-04 18:00","2022-05-04 09:00","2022-05-04 18:00","연속"]
[77,"인천","김포","왕길양촌#1 T/L","왕길S/S 170kV 6100 TIE GIS 정밀점검용 무부하시험","왕길S/S 170kV 6100 TIE GIS 정밀점검용 무부하시험","2022-05-04 09:00","2022-05-04 18:00","2022-05-25 09:00","2022-05-25 18:00","연속"]
[78,"인천","직할","부천원미#1 T/L","원미S/S 6100 BUSTIE GIS 정밀점검(무부하가압용)","원미S/S 6100 BUSTIE GIS 정밀점검(무부하가압용)","2022-05-04 09:30","2022-05-04 18:00","2022-05-04 09:30","2022-05-04 18:00","연속"]
[79,"인천","직할","갈산부흥#3 T/L","갈산S/S 갈산부흥#3T/L GIS 하자점검","갈산S/S 갈산부흥#3T/L GIS 하자점검","2022-05-06 09:30","2022-05-06 18:00","2022-05-06 09:30","2022-05-06 18:00","연속"]
[80,"인천","직할","갈산도당#1 T/L","갈산S/S 갈산도당#1T/L GIS 하자점검","갈산S/S 갈산도당#1T/L GIS 하자점검","2022-05-07 09:30","2022-05-07 18:00","2022-05-07 09:30","2022-05-07 18:00","연속"]
[81,"인천","직할","경서북인천#1 T/L","북인천S/S 경서북인천#1T/L GIS 정밀점검","북인천S/S 경서북인천#1T/L GIS 정밀점검","2022-05-09 09:30","2022-05-11 14:00","2022-05-09 09:30","2022-05-11 14:00","연속"]
[82,"인천","직할","부천S/S CB 6100","부천S/S BUSTIE DS 링크 경보 회로개선","부천S/S BUSTIE DS 링크 경보 회로개선","2022-05-10 09:00","2022-05-10 18:00","2022-05-10 09:00","2022-05-10 18:00","연속"]
[83,"인천","김포","왕길양촌#1 T/L","왕길S/S 170kV #1M.Tr 1차 GIS 정밀점검용 무부하시험","왕길S/S 170kV #1M.Tr 1차 GIS 정밀점검용 무부하시험","2022-05-11 09:00","2022-05-11 18:00","2022-05-27 09:00","2022-05-27 18:00","연속"]
[84,"인천","직할","부천도당#1 T/L","부천S/S 도당부천#1T/L DS 링크 경보 회로 개선","부천S/S 도당부천#1T/L DS 링크 경보 회로 개선","2022-05-11 09:30","2022-05-11 18:00","2022-05-11 09:30","2022-05-11 18:00","연속"]
[85,"인천","직할","경서북인천#2 T/L","북인천S/S 경서북인천#2T/L GIS 정밀점검","북인천S/S 경서북인천#2T/L GIS 정밀점검","2022-05-11 14:00","2022-05-13 18:00","2022-05-11 14:00","2022-05-13 18:00","연속"]
[86,"인천","직할","부천도당#2 T/L","부천S/S 도당부천#2T/L DS 링크 경보 회로 개선","부천S/S 도당부천#2T/L DS 링크 경보 회로 개선","2022-05-12 09:30","2022-05-12 18:00","2022-05-12 09:30","2022-05-12 18:00","연속"]
[87,"인천","김포","왕길양촌#1 T/L","왕길S/S 170kV #2M.Tr 1차 GIS 정밀점검용 무부하시험","왕길S/S 170kV #2M.Tr 1차 GIS 정밀점검용 무부하시험","2022-05-13 09:00","2022-05-13 18:00","2022-05-31 09:00","2022-05-31 18:00","연속"]
[88,"인천","직할","부천원미#2 T/L","부천S/S 부천원미#2T/L DS 링크 경보 회로 개선","부천S/S 부천원미#2T/L DS 링크 경보 회로 개선","2022-05-16 09:30","2022-05-20 18:00","2022-05-16 09:30","2022-05-20 18:00","연속"]
[89,"인천","직할","부천신정#1 T/L","부천S/S 부천신정#1T/L DS 링크 경보 회로 개선","부천S/S 부천신정#1T/L DS 링크 경보 회로 개선","2022-05-14 09:30","2022-05-14 14:00","2022-05-14 09:30","2022-05-14 14:00","연속"]
[90,"인천","직할","부천신정#2 T/L","부천S/S 부천신정#2T/L DS 링크 경보 회로 개선","부천S/S 부천신정#2T/L DS 링크 경보 회로 개선","2022-05-14 14:00","2022-05-14 18:00","2022-05-14 14:00","2022-05-14 18:00","연속"]
[91,"인천","부평","관교만수#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단 전력구 #8, #12, 관교SJ,관교EB-G, 맨홀 #11","2022-05-19 09:00","2022-05-20 18:00","2022-05-19 09:00","2022-05-20 18:00","연속"]
[92,"인천","부평","신가좌인천#1 T/L","신가좌인천#1 T/L GIS 보통점검","신가좌인천#1 T/L GIS 보통점검 -신가좌S/S 신가좌인천#1 T/L GIS 조작시험 병행","2022-05-20 09:00","2022-05-20 18:00","2022-05-20 09:00","2022-05-20 18:00","연속"]
[93,"인천","김포","왕길양촌#2 T/L","154kV 왕길S/S #4M.Tr GIS 설치공사","- 154kV GIS × 4CCT 설치 - 기타부대공사 × 1식","2022-05-23 08:00","2022-05-26 11:00","2022-05-23 08:00","2022-05-26 11:00","연속"]
[94,"인천","부평","관교만수#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인 #1,#2,#6(2),#12, 관교SJ,관교EB-G","2022-05-23 09:00","2022-05-24 18:00","2022-05-23 09:00","2022-05-24 18:00","연속"]
[95,"인천","부평","서인천C/C CB 6200","서인천C/C 61,66BUS 모선보호반 교체","서인천C/C 61,66BUS 모선보호반 교체 -6200GIS 보통점검","2022-05-23 09:00","2022-05-27 18:00","2022-05-23 09:00","2022-05-27 18:00","연속"]
[96,"인천","직할","부천원미#1 T/L","부천S/S 부천원미#1T/L 보호반대체(양단)","부천S/S 부천원미#1T/L 보호반대체(양단)","2022-05-23 09:00","2022-05-27 18:00","2022-05-23 09:00","2022-05-27 18:00","연속"]
[97,"인천","부평","학익연수#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단 학익EB-G,학익SJ,연수EB-G, M/H#2,6,10","2022-05-24 09:00","2022-05-25 18:00","2022-05-24 09:00","2022-05-25 18:00","연속"]
[98,"인천","김포","경서양촌#1 T/L","양촌S/S 170kV #1M.Tr 1차 GIS 정밀점검용 무부하시험","양촌S/S 170kV #1M.Tr 1차 GIS 정밀점검용 무부하시험","2022-05-25 09:00","2022-05-25 18:00","취소","취소","연속"]
[99,"인천","부평","학익연수#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단 학익EB-G,학익SJ,연수EB-G, M/H#2,6,10","2022-05-26 09:00","2022-05-27 18:00","2022-05-26 09:00","2022-05-27 18:00","연속"]
[100,"인천","김포","경서양촌#1 T/L","양촌S/S 170kV #2M.Tr 1차 GIS 정밀점검용 무부하시험","양촌S/S 170kV #2M.Tr 1차 GIS 정밀점검용 무부하시험","2022-05-27 09:00","2022-05-27 18:00","취소","취소","연속"]
[101,"인천","김포","왕길양촌#1 T/L","154kV 왕길S/S #4M.Tr GIS 설치공사(무부하가압)","- 154kV GIS × 4CCT 설치 - 기타부대공사 × 1식","2022-05-27 18:00","2022-05-28 18:00","취소","취소","연속"]
[102,"인천","김포","왕길양촌#2 T/L","154kV 왕길S/S #4M.Tr GIS 설치공사","- 154kV GIS × 4CCT 설치 - 기타부대공사 × 1식","2022-05-30 08:00","2022-06-02 11:00","취소","취소","연속"]
[103,"인천","부평","신가좌부개#1 T/L","154kV 부개S/S 디지털변전소 혼용운영시스템 설치공사","154kV 부개S/S 디지털변전소 혼용운영시스템 설치공사","2022-05-30 09:00","2022-05-30 18:00","2022-05-30 09:00","2022-05-30 18:00","연속"]
[104,"인천","부평","신가좌인천#2 T/L","신가좌인천#2 T/L GIS 보통점검","신가좌인천#2 T/L GIS 보통점검 -신가좌S/S 신가좌인천#2 T/L GIS 조작시험 병행","2022-05-30 09:00","2022-05-30 18:00","2022-05-30 09:00","2022-05-30 18:00","연속"]
[105,"인천","부평","신가좌부개#2 T/L","신가좌S/S 신가좌부개#2 T/L GIS 조작시험 및 보조계전기 교체","신가좌S/S 신가좌부개#2 T/L GIS 조작시험 및 보조계전기 교체 - 부개S/S 신가좌S/S 신가좌부개#2 T/L GIS 조작시험 및 전자변 교체","2022-05-31 09:00","2022-05-31 18:00","2022-05-31 09:00","2022-05-31 18:00","연속"]
[106,"경기북부","고양","능곡S/S #2 BUS","22년 고양전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 시험가압","2022-05-19 09:00","2022-05-19 18:00","취소","취소","연속"]
[107,"경기북부","고양","능곡S/S #1 BUS","22년 고양전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 시험가압","2022-05-17 09:00","2022-05-17 18:00","취소","취소","연속"]
[108,"경기북부","고양","덕이S/S #2 BUS","덕이S/S 154kV #3M.Tr 공장입고수리 관련 무부하가압","덕이S/S 154kV #3M.Tr 제작사 공장입고수리 관련 무부하가압","2022-05-30 10:00","2022-05-31 10:00","2022-05-30 10:00","2022-05-31 10:00","연속"]
[109,"경기북부","고양","덕이호수#2 T/L","덕이S/S 154kV #3M.Tr 공장입고수리 관련 무부하가압","덕이S/S 154kV #3M.Tr 제작사 공장입고수리 관련 무부하가압","2022-05-30 10:00","2022-05-31 10:00","2022-05-30 10:00","2022-05-31 10:00","연속"]
[110,"경기북부","고양","신덕은문산#2 T/L","대한전선제 열경화공법 EBG 보강공사","문산EBG 스프링유니트 점검 및 가스새취밸브 설치","2022-05-24 09:00","2022-05-26 18:00","2022-05-24 09:00","2022-05-26 18:00","연속"]
[111,"경기북부","고양","신덕은문산#1 T/L","대한전선제 열경화공법 EBG 보강공사","문산EBG 스프링유니트 점검 및 가스새취밸브 설치","2022-05-19 09:00","2022-05-23 18:00","2022-05-19 09:00","2022-05-23 18:00","연속"]
[112,"경기북부","고양","문산월롱#1 T/L","대한전선제 열경화공법 EBG 보강공사","문산EBG 스프링유니트 점검 및 가스새취밸브 설치","2022-05-19 09:00","2022-05-23 18:00","2022-05-19 09:00","2022-05-23 18:00","연속"]
[113,"경기북부","고양","문산월롱#2 T/L","대한전선제 열경화공법 EBG 보강공사","문산EBG 스프링유니트 점검 및 가스새취밸브 설치","2022-05-24 09:00","2022-05-26 18:00","2022-05-24 09:00","2022-05-26 18:00","연속"]
[114,"경기북부","고양","신덕은S/S #66 BUS","22년 고양전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 시험가압","2022-05-10 09:00","2022-05-10 18:00","2022-05-10 09:00","2022-05-10 18:00","연속"]
[115,"경기북부","고양","신덕은금촌#2 T/L","154kV 신덕은-금촌#2T/L 노후 피뢰기 교체공사","노후 피뢰기 교체공사","2022-05-02 09:00","2022-05-03 18:00","2022-05-02 09:00","2022-05-03 18:00","연속"]
[116,"경기북부","고양","신덕은금촌#1 T/L","154kV 신덕은-금촌#1T/L 노후 피뢰기 교체공사","노후 피뢰기 교체공사","2022-05-04 09:00","2022-05-06 18:00","2022-05-04 09:00","2022-05-06 18:00","연속"]
[117,"경기북부","고양","신파주S/S CB 6100","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2022-05-17 09:00","2022-05-17 18:00","2022-05-17 09:00","2022-05-17 18:00","연속"]
[118,"경기북부","고양","신파주S/S SEC CB 60610","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2022-05-18 09:00","2022-05-18 18:00","2022-05-18 09:00","2022-05-18 18:00","연속"]
[119,"경기북부","고양","원흥S/S #2 BUS","22년 고양전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 시험가압","2022-05-24 09:00","2022-05-25 18:00","2022-05-24 09:00","2022-05-25 18:00","연속"]
[120,"경기북부","고양","원흥상암 T/L","22년 고양전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2022-05-23 09:00","2022-05-25 18:00","2022-05-23 09:00","2022-05-25 18:00","연속"]
[121,"경기북부","고양","월롱금촌#1 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 초기점검","2022-05-30 08:00","2022-05-30 17:00","2022-05-30 08:00","2022-05-30 17:00","연속"]
[122,"경기북부","고양","월롱금촌#2 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 초기점검","2022-05-31 08:00","2022-05-31 17:00","2022-05-31 08:00","2022-05-31 17:00","연속"]
[123,"경기북부","고양","일산S/S #60 BUS","22년 고양전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 시험가압","2022-05-04 09:00","2022-05-04 18:00","2022-05-04 09:00","2022-05-04 18:00","연속"]
[124,"경기북부","고양","고양일산#2 T/L","일산S/S 옥외PT 하우징 설치공사","옥외PT실 하우징 설치시 안전이격거리 확보를 위한 휴전","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[125,"경기북부","고양","일산지도#2 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검(병가선로)","2022-05-16 08:00","2022-05-17 17:00","2022-05-16 08:00","2022-05-17 17:00","연속"]
[126,"경기북부","구리","가평청평HP#2 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-05-23 14:00","2022-05-23 18:00","2022-05-23 14:00","2022-05-23 18:00","연속"]
[127,"경기북부","구리","가평화천HP T/L","송전선로 추락방지시설 설치공사","154kV 가평-화천T/L 수평추락방지시설설치(No.70~135)","2022-05-02 07:00","2022-05-11 18:00","2022-05-02 07:00","2022-05-11 18:00","연속"]
[128,"경기북부","구리","가평청평HP#2 T/L","송전선로 추락방지시설 설치공사","154kV 화천T/L 추락방지시설설치(No.129~135 병가구간)","2022-05-09 07:00","2022-05-10 18:00","2022-05-09 07:00","2022-05-10 18:00","연속"]
[129,"경기북부","구리","가평춘천HP T/L","2022년도 가공송전선로 순시점검 위탁공사","154kV 가평-춘천HP T/L 정밀점검 실시(No.70~135)","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[130,"경기북부","구리","가평청평HP#1 T/L","2022년도 가공송전선로 순시점검 위탁공사","154kV 가평-춘천HP T/L 정밀점검 실시(No.129~135 병가구간 휴전)","2022-05-20 09:00","2022-05-20 18:00","2022-05-20 09:00","2022-05-20 18:00","연속"]
[131,"경기북부","구리","구리S/S #1 BUS","구리S/S 170kV 장기사용 GIS 교체공사","구리S/S 170kV 장기사용 GIS 교체공사 - 2차분 ○ 구리-신내#2T/L GIS ○ #2M.Tr 1차 GIS ○ 6100BUSTIE GIS","2022-05-02 10:00","2022-05-02 18:00","2022-05-02 10:00","2022-05-02 18:00","연속"]
[132,"경기북부","구리","미금구리#2 T/L","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","미금-구리#2T/L GIS 조작시험","2022-05-25 14:00","2022-05-25 18:00","2022-05-25 14:00","2022-05-25 18:00","연속"]
[133,"경기북부","구리","미금구리#1 T/L","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","미금-구리#1T/L 조작시험","2022-05-25 09:00","2022-05-25 14:00","2022-05-25 09:00","2022-05-25 14:00","연속"]
[134,"경기북부","구리","내촌용정#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치","2022-05-02 07:30","2022-05-03 18:00","2022-05-06 07:30","2022-05-09 18:00","연속"]
[135,"경기북부","구리","내촌용정#1 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치","2022-05-09 07:30","2022-05-09 18:00","2022-05-23 07:30","2022-05-23 18:00","연속"]
[136,"경기북부","구리","덕소S/S SEC CB 65660","22-23 구리전력 변전협력 총액공사","154kV GIS 하자점검","2022-05-30 14:00","2022-05-30 18:00","2022-05-30 14:00","2022-05-30 18:00","연속"]
[137,"경기북부","구리","덕소S/S SEC CB 60610","22-23 구리전력 변전협력 총액공사","154kV GIS 하자점검","2022-05-30 09:00","2022-05-30 14:00","2022-05-30 09:00","2022-05-30 14:00","연속"]
[138,"경기북부","구리","덕소진건#2 T/L","21-22년 경기북부 직할 지중송전설비 위탁정비공사","덕진#3C/T 154kV 덕소-진건#2T/L EB-A 절연유 분석 (A,C상)","2022-05-18 09:00","2022-05-18 18:00","2022-05-18 09:00","2022-05-18 18:00","연속"]
[139,"경기북부","구리","덕소진건#1 T/L","21-22년 경기북부 직할 지중송전설비 위탁정비공사","덕진#3C/T 154kV 덕소-진건#1T/L EB-A 절연유 분석 (B상)","2022-05-17 09:00","2022-05-17 18:00","2022-05-17 09:00","2022-05-17 18:00","연속"]
[140,"경기북부","구리","마석청평HP#1 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-05-12 09:00","2022-05-12 14:00","2022-05-12 09:00","2022-05-12 14:00","연속"]
[141,"경기북부","구리","마석청평HP#2 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-05-12 14:00","2022-05-12 18:00","2022-05-12 14:00","2022-05-12 18:00","연속"]
[142,"경기북부","구리","미금S/S CB 6300","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-05-13 09:00","2022-05-13 18:00","2022-05-13 09:00","2022-05-13 18:00","연속"]
[143,"경기북부","구리","미금S/S CB 6200","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-05-11 09:00","2022-05-11 18:00","2022-05-11 09:00","2022-05-11 18:00","연속"]
[144,"경기북부","구리","별내별내열병합#2 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-05-31 09:00","2022-05-31 18:00","2022-05-31 09:00","2022-05-31 18:00","연속"]
[145,"경기북부","구리","별내별내열병합#1 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-05-26 09:00","2022-05-26 18:00","2022-05-26 09:00","2022-05-26 18:00","연속"]
[146,"경기북부","구리","신포천포천#1 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치","2022-05-17 07:30","2022-05-25 18:00","2022-05-24 07:30","2022-06-03 18:00","연속"]
[147,"경기북부","구리","신포천동두천#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치","2022-05-23 07:30","2022-05-30 18:00","2022-05-31 07:30","2022-06-08 18:00","연속"]
[148,"경기북부","구리","진접S/S CB 6100","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","154kV #1-#2 BUS TIE GIS 조작시험","2022-05-11 09:00","2022-05-11 18:00","2022-05-11 09:00","2022-05-11 18:00","연속"]
[149,"경기북부","구리","팔당H/P #2M.Tr 1차 CB","22-23 구리전력 변전협력 총액공사","154kV GIS 초기점검","2022-05-18 14:00","2022-05-18 18:00","2022-05-18 14:00","2022-05-18 18:00","연속"]
[150,"경기북부","구리","팔당H/P #1M.Tr 1차 CB","22-23 구리전력 변전협력 총액공사","154kV GIS 초기점검","2022-05-18 09:00","2022-05-18 14:00","2022-05-18 09:00","2022-05-18 14:00","연속"]
[151,"경기북부","구리","포천운천#1 T/L","154kV 포천S/S 옥내화 건설공사","POST 1기 철거 가공지선 이설","2022-05-10 09:00","2022-05-11 18:00","2022-05-10 09:00","2022-05-11 18:00","연속"]
[152,"경기북부","직할","별내도봉 T/L","154kV 장암S/S 옥내화관련 인출선로 정비공사","케이블타워 2기 설치, 산형강철탑 1기 보강 등","2022-05-14 09:00","2022-05-15 18:00","2022-05-14 09:00","2022-05-15 18:00","연속"]
[153,"경기북부","직할","도봉진접 T/L","154kV 장암S/S 옥내화관련 인출선로 정비공사","케이블타워 2기 설치, 산형강철탑 1기 보강 등","2022-05-13 09:00","2022-05-17 18:00","2022-05-13 09:00","2022-05-17 18:00","연속"]
[154,"경기북부","직할","별내도봉 T/L","154kV 장암S/S 옥내화관련 인출선로 정비공사","케이블타워 2기 설치, 산형강철탑 1기 보강 등","2022-05-18 09:00","2022-05-22 18:00","2022-05-18 09:00","2022-05-22 18:00","연속"]
[155,"경기북부","직할","신의정부내촌#1 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치","2022-05-02 07:30","2022-05-06 18:00","2022-05-03 07:30","2022-05-09 18:00","연속"]
[156,"경기북부","직할","신의정부내촌#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치","2022-05-09 07:30","2022-05-11 18:00","2022-05-23 07:30","2022-05-25 18:00","연속"]
[157,"경기북부","직할","옥정동두천#2 T/L","154kV 옥정S/S #3M.Tr 증설공사","154kV 옥정S/S #3M.Tr 170kV GIS 개폐장치 설치 - 170kV GIS #1, 2BUS측 조립시 인근Bay 가스 감압 - 무부하가압선로","2022-05-16 09:00","2022-05-20 20:00","2022-05-16 09:00","2022-05-20 20:00","연속"]
[158,"경기북부","직할","옥정동두천#1 T/L","21-22년 경기북부 직할 지중송전설비 위탁정비공사","옥정C/T 154kV 옥정-동두천#1T/L EB-A 절연유 분석 (A상)","2022-05-26 09:00","2022-05-26 18:00","2022-05-26 09:00","2022-05-26 18:00","연속"]
[159,"경기북부","직할","옥정S/S #1 BUS","154kV 옥정S/S #3M.Tr 증설공사","154kV 옥정S/S #3M.Tr 170kV GIS 개폐장치 설치 - 170kV GIS #1BUS측 조립 - 무부하 가압","2022-05-16 09:00","2022-05-20 20:00","2022-05-16 09:00","2022-05-20 20:00","연속"]
[160,"경기북부","직할","옥정동두천#2 T/L","154kV 옥정S/S #3M.Tr 증설공사","154kV 옥정S/S #3M.Tr 170kV GIS 개폐장치 설치 - 170kV GIS #1, 2BUS측 조립시 인근Bay 가스 감압 - 무부하가압선로","2022-05-10 09:00","2022-05-14 20:00","2022-05-10 09:00","2022-05-14 20:00","연속"]
[161,"경기북부","직할","옥정S/S #2 BUS","154kV 옥정S/S #3M.Tr 증설공사","154kV 옥정S/S #3M.Tr 170kV GIS 개폐장치 설치 - 170kV GIS #2BUS측 조립 - 무부하가압","2022-05-10 09:00","2022-05-14 20:00","2022-05-10 09:00","2022-05-14 20:00","연속"]
[162,"경기","군포","화성남양#1 T/L","남양SS 화성-남양#1TL GIS 보통점검","남양SS 화성-남양#1TL GIS 보통점검/ 화성측 병행","2022-05-23 09:00","2022-05-23 14:00","2022-05-23 09:00","2022-05-23 14:00","연속"]
[163,"경기","군포","화성남양#2 T/L","남양SS 화성-남양#2TL GIS 보통점검","남양SS 화성-남양#2TL GIS 보통점검/ 화성측 병행","2022-05-23 14:00","2022-05-23 18:00","2022-05-23 14:00","2022-05-23 18:00","연속"]
[164,"경기","군포","산본안양#1 T/L","안양S/S 산본-안양#1T/L GIS 보통점검","안양S/S 산본-안양#1T/L GIS 보통점검","2022-05-11 14:00","2022-05-11 18:00","2022-05-11 14:00","2022-05-11 18:00","연속"]
[165,"경기","군포","산본안양#2 T/L","산본S/S 산본-안양#2T/L 보통점검","산본S/S 산본-안양#2T/L 보통점검 및 안양S/S 산본-안양#2T/L 보통점검","2022-05-11 09:00","2022-05-11 14:00","2022-05-11 09:00","2022-05-11 14:00","연속"]
[166,"경기","군포","서서울율전#2 T/L","서서울-율전#2T/L LA 교체","서서울-율전#2T/L LA 교체","2022-05-13 09:00","2022-05-13 18:00","2022-05-13 09:00","2022-05-13 18:00","연속"]
[167,"경기","군포","서서울율전#1 T/L","서서울-율전#1T/L LA 교체","서서울-율전#1T/L LA 교체","2022-05-20 09:00","2022-05-20 18:00","2022-05-20 09:00","2022-05-20 18:00","연속"]
[168,"경기","군포","서서울산본#1 T/L","서서울S/S 서서울-산본#1T/L 보통점검","서서울S/S 서서울-산본#1T/L LA,CVT보통 및 산본S/S 서서울-산본#1T/L GIS 보통점검","2022-05-25 09:00","2022-05-25 18:00","2022-05-25 09:00","2022-05-25 18:00","연속"]
[169,"경기","군포","신안산남안산#1 T/L","남안산SS 신안산-남안산#1TL GIS 정밀점검","남안산SS 신안산-남안산#1TL GIS 정밀점검","2022-05-09 09:00","2022-05-11 18:00","2022-05-09 09:00","2022-05-11 18:00","연속"]
[170,"경기","군포","신안산남안산#2 T/L","남안산SS 신안산-남안산#2TL GIS 정밀점검","남안산SS 신안산-남안산#2TL GIS 정밀점검","2022-05-12 09:00","2022-05-12 18:00","2022-05-12 09:00","2022-05-12 18:00","연속"]
[171,"경기","군포","일동S/S #1 BUS","일동SS 일동고속철#1T/L 정밀점검 무부하 가압선로","일동SS 일동고속철#1T/L 정밀점검 무부하 가압선로","2022-05-25 16:00","2022-05-25 17:00","2022-05-25 16:00","2022-05-25 17:00","연속"]
[172,"경기","군포","일동S/S #1 BUS","일동SS 일동고속철#2T/L 정밀점검 무부하 가압선로","일동SS 일동고속철#2T/L 정밀점검 무부하 가압선로","2022-05-28 16:00","2022-05-28 17:00","2022-05-28 16:00","2022-05-28 17:00","연속"]
[173,"경기","동부","초월성현#1 T/L","초월S/S 154kV #5M.Tr 증설공사","#2BUS 무부하가압","2022-05-19 09:00","2022-05-20 18:00","2022-05-19 09:00","2022-05-20 18:00","연속"]
[174,"경기","동부","초월S/S CB 6100","22년 동부 변전정비협력공사","초월:6100(조작)","2022-05-02 09:30","2022-05-02 18:00","2022-05-02 09:30","2022-05-02 18:00","연속"]
[175,"경기","동부","초월성현#1 T/L","초월S/S 154kV #5M.Tr 증설공사","#1BUS 무부하가압","2022-05-26 09:00","2022-05-27 18:00","2022-05-26 09:00","2022-05-27 18:00","연속"]
[176,"경기","동부","오포모현#1 T/L","22년 동부 변전정비 총액공사","오포:오포-모현#1T/L(보통)","2022-05-09 09:30","2022-05-09 18:00","2022-05-09 09:30","2022-05-09 18:00","연속"]
[177,"경기","동부","오포모현#2 T/L","22년 동부 변전정비 총액공사","오포:오포-모현#2T/L(보통)","2022-05-10 09:30","2022-05-10 18:00","2022-05-10 09:30","2022-05-10 18:00","연속"]
[178,"경기","성남","용인덕성#1 T/L","22년 성남전력지사 변전협력회사 총액공사","- GIS 초기점검","2022-05-19 09:00","2022-05-19 14:00","2022-05-19 09:00","2022-05-19 14:00","연속"]
[179,"경기","성남","용인덕성#2 T/L","22년 성남전력지사 변전협력회사 총액공사","- GIS 초기점검","2022-05-19 14:00","2022-05-19 18:00","2022-05-19 14:00","2022-05-19 18:00","연속"]
[180,"경기","성남","신갈S/S 영통열병합T/L CB","22년 성남전력지사 변전협력회사 총액공사","- GIS 하자점검","2022-05-24 09:00","2022-05-24 18:00","2022-05-24 09:00","2022-05-24 18:00","연속"]
[181,"경기","성남","기흥신갈#1 T/L","22년 성남전력지사 변전협력회사 총액공사","- GIS 하자점검 - 보호반대체(양단)","2022-05-02 09:00","2022-05-04 18:00","2022-05-02 09:00","2022-05-04 18:00","연속"]
[182,"경기","성남","신성남정자 #3 T/L","22년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2022-05-31 09:00","2022-05-31 18:00","2022-05-31 09:00","2022-05-31 18:00","연속"]
[183,"경기","성남","신수원S/S CB 6200","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2022-05-16 09:00","2022-05-18 18:00","2022-05-16 09:00","2022-05-18 18:00","연속"]
[184,"경기","성남","신수원화성열병#2 T/L","22년 성남전력지사 변전협력회사 총액공사","- 화성열병합 O/H - GIS 조작시험","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[185,"경기","성남","신수원S/S #61 BUS","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검 무부하가압","2022-05-18 09:00","2022-05-18 18:00","2022-05-18 09:00","2022-05-18 18:00","연속"]
[186,"경기","성남","신수원S/S #60 BUS","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검 무부하가압","2022-05-13 09:00","2022-05-13 18:00","2022-05-13 09:00","2022-05-13 18:00","연속"]
[187,"경기","성남","신수원화성열병#1 T/L","22년 성남전력지사 변전협력회사 총액공사","- 화성열병합 O/H - GIS 조작시험","2022-05-09 09:00","2022-05-13 18:00","2022-05-09 09:00","2022-05-13 18:00","연속"]
[188,"경기","성남","신수원S/S SEC CB 65660","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2022-05-09 09:00","2022-05-11 14:00","2022-05-09 09:00","2022-05-11 14:00","연속"]
[189,"경기","성남","신수원S/S CB 6100","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2022-05-11 14:00","2022-05-13 18:00","2022-05-11 14:00","2022-05-13 18:00","연속"]
[190,"경기","성남","신수원S/S #65 BUS","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검 무부하가압","2022-05-11 09:00","2022-05-11 14:00","2022-05-11 09:00","2022-05-11 14:00","연속"]
[191,"경기","성남","신용인기흥#2 T/L","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검 무부하가압","2022-05-27 09:00","2022-05-27 18:00","2022-05-27 09:00","2022-05-27 18:00","연속"]
[192,"경기","성남","신용인S/S CB 6300","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2022-05-25 14:00","2022-05-27 18:00","2022-05-25 14:00","2022-05-27 18:00","연속"]
[193,"경기","성남","신용인S/S #67 BUS","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검 무부하가압","2022-05-27 09:00","2022-05-27 18:00","2022-05-27 09:00","2022-05-27 18:00","연속"]
[194,"경기","직할","관양평촌#1 T/L","22년 직할 154kV GIS 정밀점검공사","22년 직할 154kV GIS 정밀점검공사 무부하가압용","2022-05-12 09:00","2022-05-12 18:00","2022-05-12 09:00","2022-05-12 18:00","연속"]
[195,"경기","직할","관양동안양#2 T/L","22년 직할 154kV GIS 정밀점검공사","22년 직할 154kV GIS 정밀점검공사","2022-05-09 09:00","2022-05-10 18:00","2022-05-09 09:00","2022-05-10 18:00","연속"]
[196,"경기","직할","관양평촌#2 T/L","22년 직할 154kV GIS 정밀점검공사","22년 직할 154kV GIS 정밀점검공사","2022-05-03 09:00","2022-05-04 18:00","2022-05-03 09:00","2022-05-04 18:00","연속"]
[197,"경기","직할","동수원우만#2 T/L","'21-'22년 지중송전 위탁정비공사","OF 접속함 절연유 채유밸브 설치 및 채유(추적진단)","2022-05-03 09:00","2022-05-04 18:00","2022-05-03 09:00","2022-05-04 18:00","연속"]
[198,"경기","직할","서수원율전#1 T/L","22년 직할 154kV GIS 정밀점검공사","22년 직할 154kV GIS 정밀점검공사","2022-05-16 09:00","2022-05-17 18:00","2022-05-16 09:00","2022-05-17 18:00","연속"]
[199,"경기","직할","서수원율전#2 T/L","22년 직할 154kV GIS 정밀점검공사","22년 직할 154kV GIS 정밀점검공사","2022-05-18 09:00","2022-05-19 18:00","2022-05-18 09:00","2022-05-19 18:00","연속"]
[200,"경기","직할","화성S/S #61 BUS","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 2차측, 화성-수촌#2T/L GIS 준공시험","2022-05-11 09:00","2022-05-13 18:00","2022-05-11 09:00","2022-05-13 18:00","연속"]
[201,"경기","직할","화성S/S SEC CB 66670","2022-23 경기본부 직할변전협력회사 총액공사","61062, 66-67 SEC GIS 조작시험 - 43LR 경보수용, 변전기기 도장(범위 회의필요)","2022-05-27 14:00","2022-05-27 18:00","2022-05-27 14:00","2022-05-27 18:00","연속"]
[202,"경기","직할","화성S/S SEC CB 61620","2022-23 경기본부 직할변전협력회사 총액공사","61062, 66-67 SEC GIS 조작시험 - 43LR 경보수용, 변전기기 도장(범위 회의필요)","2022-05-27 09:00","2022-05-27 14:00","2022-05-27 09:00","2022-05-27 14:00","연속"]
[203,"경기","평택","고덕동평택#1 T/L","22년 평택전력지사 변전협력회사 총액공사","고덕S/S 고덕-동평택#2T/L GIS 하자점검","2022-05-30 10:00","2022-05-30 18:00","2022-05-30 10:00","2022-05-30 18:00","연속"]
[204,"경기","평택","고덕진위#2 T/L","22년 평택전력지사 변전협력회사 총액공사","고덕S/S 154kV 고덕-진위#2T/L GIS 보통점검","2022-05-13 10:00","2022-05-13 18:00","2022-05-13 10:00","2022-05-13 18:00","연속"]
[205,"경기","평택","고덕진위#1 T/L","22년 평택전력지사 변전협력회사 총액공사","고덕S/S 154kV 고덕-진위#1T/L GIS 보통점검","2022-05-12 10:00","2022-05-12 18:00","2022-05-12 10:00","2022-05-12 18:00","연속"]
[206,"경기","평택","서운안성#1 T/L","세종-포천간 도로개설 관련 지장이설 본이설(1-1공구)","본철탑 2기 설치","2022-05-09 07:00","2022-05-19 18:00","취소","취소","연속"]
[207,"경기","평택","서운광혜원 T/L","세종-포천간 도로개설 관련 지장이설 본이설(1-1공구)","본철탑 2기 설치","2022-05-09 07:00","2022-05-19 18:00","취소","취소","연속"]
[208,"경기","평택","서운안성#2 T/L","세종-포천간 도로개설 관련 지장이설 본이설(1-1공구)","본철탑 2기 설치","2022-05-20 07:00","2022-05-31 18:00","취소","취소","연속"]
[209,"경기"," 평택","서운삼죽 T/L","세종-포천간 도로개설 관련 지장이설 본이설(1-1공구)","본철탑 2기 설치","2022-05-20 07:00","2022-05-31 18:00","취소","취소","연속"]
[210,"경기","평택","고덕송탄#2 T/L","22년 평택전력지사 170kV GIS 정밀점검공사","송탄S/S 고덕-송탄#2T/L GIS 정밀점검","2022-05-18 09:00","2022-05-19 18:00","2022-05-18 09:00","2022-05-19 18:00","연속"]
[211,"경기","평택","고덕송탄#1 T/L","22년 평택전력지사 170kV GIS 정밀점검공사","송탄S/S 고덕-송탄#1T/L GIS 정밀점검","2022-05-16 09:00","2022-05-17 18:00","2022-05-16 09:00","2022-05-17 18:00","연속"]
[212,"경기","평택","평택추팔#2 T/L","22년 평택전력지사 170kV GIS 정밀점검공사","평택S/S 154kV 평택-추팔#2T/L GCB 공기조작부 정밀점검","2022-05-25 09:00","2022-05-26 18:00","2022-05-25 09:00","2022-05-26 18:00","연속"]
[213,"경기","평택","청북평택#2 T/L","22년 평택전력지사 170kV GIS 정밀점검공사","평택S/S 154kV 청북-평택#2T/L GCB 공기조작부 정밀점검","2022-05-30 09:00","2022-05-31 18:00","2022-05-30 09:00","2022-05-31 18:00","연속"]
[214,"경기","평택","평택오성CC#2 T/L","22년 평택전력지사 170kV GIS 정밀점검공사","평택S/S 154kV 평택-오성복합#2T/L GCB 공기조작부 정밀점검","2022-05-09 09:00","2022-05-10 18:00","취소","취소","연속"]
[215,"경기","평택","포승만호 T/L","22년 평택전력지사 변전협력회사 총액공사","포승S/S 포승-만호T/L GIS 조작시험","2022-05-02 10:00","2022-05-02 18:00","2022-05-02 10:00","2022-05-02 18:00","연속"]
[216,"강원","강릉","속초간성#1 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 간성인제#2T/L No.142-144 (작업자 안전확보를 위한 동일 편측 회선 휴전)","2022-05-23 07:00","2022-05-23 18:00","2022-05-23 07:00","2022-05-23 18:00","연속"]
[217,"강원","강릉","강릉영동TP T/L","154kV 강릉T/L No.28-32 안전이격거리 확보공사","○ 철탑 신설 3기, 철거 3기, 전력선교체 No.28-32, OPGW교체 No.28-32, 애자금구류 교체 및 피뢰기 설치 No.29,30,31","2022-05-02 07:00","2022-05-13 18:00","취소","취소","연속"]
[218,"강원","강릉","동해강릉 T/L","154kV 강릉T/L No.28-32 안전이격거리 확보공사","○ 철탑 신설 3기, 철거 3기, 전력선교체 No.28-32, OPGW교체 No.28-32, 애자금구류 교체 및 피뢰기 설치 No.29,30,31","2022-05-02 07:00","2022-05-13 18:00","취소","취소","연속"]
[219,"강원","강릉","강릉횡계#2 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○피뢰기 설치공사 : 154kV 강릉횡계#2T/L No.9, 10, 25~36","2022-05-02 07:00","2022-05-04 12:00","취소","취소","매일"]
[220,"강원","강릉","강릉횡계#1 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치공사 : 154kV 강릉횡계#1T/L No.9, 10","2022-05-04 12:00","2022-05-04 18:00","2022-05-04 12:00","2022-05-04 18:00","연속"]
[221,"강원","강릉","북강릉주문진#2 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치공사 : 154kV 북강릉주문진#2T/L No.1~55","2022-05-06 07:00","2022-05-12 18:00","2022-05-02 07:00","2022-05-10 18:00","매일"]
[222,"강원","강릉","강릉북강릉#1 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 북강릉주문진#2T/L No.2-10 (작업자 안전확보를 위한 동일 편측 회선 휴전)","2022-05-10 07:00","2022-05-11 18:00","2022-05-02 07:00","2022-05-03 18:00","매일"]
[223,"강원","강릉","신양양인제#2 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 신양양인제#2T/L No.3-6","2022-05-24 07:00","2022-05-24 18:00","2022-05-23 07:00","2022-05-25 14:30","연속"]
[224,"강원","강릉","북평영동TP#1 T/L","2022~2023년 강릉전력지사 가공송전협력회사 총액공사","○ 전선접속개소 해소 : 154kV 영동화력T/L No.46.1~47 등 4개소","2022-05-23 07:00","2022-05-28 18:00","2022-05-23 07:00","2022-05-28 18:00","연속"]
[225,"강원","강릉","주문진양양#1 T/L","154kV 속초간성 등 8개T/L 피뢰기 설치공사","○ 피뢰기 설치 : 154kV 북강릉주문진#2T/L No.50-55(작업자 안전확보를 위한 동일 편측 회선 휴전)","2022-05-06 07:00","2022-05-09 18:00","2022-05-04 07:00","2022-05-06 18:00","매일"]
[226,"강원","동해","동해T/P #2 M.Tr 2차 CB","22~23 동해전력지사 변전정비 총액공사","1. GIS 초기점검","2022-05-09 09:00","2022-05-09 18:00","취소","취소","연속"]
[227,"강원","동해","이원동해TP  T/L","22~23 동해전력지사 변전정비 총액공사","1.GIS 보통점검[이원] 2. LA 보통점검 3. GIS 보통점검 [동해TP] 4. 서포트 보강 [동해TP]","2022-05-16 09:00","2022-05-16 18:00","2022-05-16 09:00","2022-05-16 18:00","연속"]
[228,"강원","원주","신제천남원주#1 T/L","154kV 신제천-남원주T/L No.42~46 안전이격 확보공사","- 철탑 교체 4기(42,43,45,46호) [인클로징] - 전력선 교체 6경간(40~46호) 2C-1.924km - 가공지선 신설(42~43호,45~46호) 1C-0.399km","2022-05-07 08:00","2022-05-08 18:00","2022-05-07 08:00","2022-05-08 18:00","연속"]
[229,"강원","원주","신제천남원주#2 T/L","154kV 신제천-남원주T/L No.42~46 안전이격 확보공사","- 철탑 교체 4기(42,43,45,46호) [인클로징] - 전력선 교체 6경간(40~46호) 2C-1.924km - 가공지선 신설(42~43호,45~46호) 1C-0.399km","2022-05-07 08:00","2022-05-14 18:00","2022-05-07 08:00","2022-05-14 18:00","연속"]
[230,"강원","원주","신제천남원주#1 T/L","154kV 신제천-남원주T/L No.42~46 안전이격 확보공사","- 철탑 교체 4기(42,43,45,46호) [인클로징] - 전력선 교체 6경간(40~46호) 2C-1.924km - 가공지선 신설(42~43호,45~46호) 1C-0.399km","2022-05-15 08:00","2022-05-18 18:00","2022-05-15 08:00","2022-05-18 18:00","연속"]
[231,"강원","원주","북원주횡성#2 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 초기점검, CVT교체","2022-05-23 10:00","2022-05-23 18:00","2022-05-23 10:00","2022-05-23 18:00","연속"]
[232,"강원","직할","남춘천춘천열병합#1 T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","154kV 남춘천-춘천T/L 6회선 병가구간 작업을 위한 하단선로 휴전","2022-05-18 08:00","2022-06-07 18:00","2022-05-18 08:00","2022-06-07 18:00","연속"]
[233,"강원","직할","양구화천HP#1 T/L","피뢰기 및 추락방지장치 설치공사","- 수평 추락방지장치(와이어형) : 78(기) - 아킹혼철거 : 132(set)","2022-05-20 08:00","2022-05-29 18:00","2022-05-20 08:00","2022-05-29 18:00","연속"]
[234,"강원","직할","양구화천HP#2 T/L","피뢰기 및 추락방지장치 설치공사","- 피뢰기설치 : 80(기), 240(set) - 수직, 수평 추락방지장치(와이어형) : 78(기) - 아킹혼철거 : 504(set)","2022-05-02 08:00","2022-05-19 18:00","2022-05-02 08:00","2022-05-19 18:00","연속"]
[235,"강원","직할","간성인제#2 T/L","2022년 상반기 직할 170kV GIS 정밀점검","2022년 상반기 직할 170kV GIS 정밀점검 - 인제S/S 154kV 간성-인제 #2T/L GIS 정밀점검","2022-05-23 09:00","2022-05-25 14:30","2022-05-23 09:00","2022-05-25 14:30","연속"]
[236,"강원","직할","상남인제#2 T/L","2022년 상반기 직할 170kV GIS 정밀점검","2022년 상반기 직할 170kV GIS 정밀점검 - 인제S/S 154kV 상남-인제 #2T/L GIS 정밀점검","2022-05-18 14:30","2022-05-20 18:00","2022-05-18 14:30","2022-05-20 18:00","연속"]
[237,"강원","직할","신양양인제#1 T/L","2022년 상반기 직할 170kV GIS 정밀점검","2022년 상반기 직할 170kV GIS 정밀점검 - 인제S/S 154kV 신양양-인제 #1T/L GIS 정밀점검","2022-05-30 09:00","2022-06-02 18:00","2022-05-30 09:00","2022-06-02 18:00","연속"]
[238,"강원","직할","인제양구#2 T/L","2022년 상반기 직할 170kV GIS 정밀점검","2022년 상반기 직할 170kV GIS 정밀점검 - 인제S/S 154kV 인제-양구 #2T/L GIS 정밀점검","2022-05-25 14:30","2022-05-27 18:00","2022-05-25 14:30","2022-05-27 18:00","연속"]
[239,"강원","직할","간성인제#1 T/L","2022년 상반기 직할 170kV GIS 정밀점검","2022년 상반기 직할 170kV GIS 정밀점검 - 인제S/S 154kV 간성-인제 #1T/L GIS 정밀점검","2022-05-16 09:00","2022-05-18 14:30","2022-05-16 09:00","2022-05-18 14:30","연속"]
[240,"강원","태백","태백고한 T/L","22-23년 태백전력지사 변전정비회사 총액공사","태백S/S 154kV 태백-고한 T/L GIS 보통점검 [병행] 태백S/S 154kV 태백-고한 T/L LA교체","2022-05-02 10:00","2022-05-03 18:00","2022-05-02 10:00","2022-05-03 18:00","연속"]
[241,"강원","태백","태백삼척GP#1 T/L","22-23년 태백전력지사 변전정비회사 총액공사","태백S/S 154kV 태백-삼척GP #1T/L GIS 보통점검 [병행] 태백S/S 154kV 태백-삼척GP #1T/L LA교체","2022-05-09 10:00","2022-05-10 18:00","2022-05-09 10:00","2022-05-10 18:00","연속"]
[242,"강원","태백","태백영월 T/L","154kV 태백-영월T/L 피뢰기 설치공사","154kV 태백-영월T/L 피뢰기 설치공사","2022-05-09 09:00","2022-06-17 18:00","2022-05-09 09:00","2022-06-17 18:00","매일"]
[243,"충북","직할","서운광혜원 T/L","`22~23 충북직할 변전협력회사 총액공사","광혜원변전소 154kV GIS 보통점검","2022-05-16 10:00","2022-05-16 18:00","2022-05-16 10:00","2022-05-16 18:00","연속"]
[244,"충북","직할","신진천S/S CB 6100","22년도 장기미동작 차단기 점검","현장/원방조작 개폐타임측정 등","2022-05-11 10:00","2022-05-11 14:00","2022-05-11 10:00","2022-05-11 14:00","연속"]
[245,"충북","직할","신진천S/S CB 6300","22년도 장기미동작 차단기 점검","현장/원방조작 개폐타임측정 등","2022-05-11 14:00","2022-05-11 18:00","2022-05-11 14:00","2022-05-11 18:00","연속"]
[246,"충북","직할","신진천진천#1 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-05-22 10:00","2022-05-22 18:00","2022-05-22 10:00","2022-05-22 18:00","연속"]
[247,"충북","직할","진천덕산#2 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-05-26 10:00","2022-05-26 18:00","취소","취소","연속"]
[248,"충북","직할","진천광혜원#1 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-05-23 10:00","2022-05-23 18:00","2022-05-23 10:00","2022-05-23 18:00","연속"]
[249,"충북","직할","진천광혜원#2 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-05-24 10:00","2022-05-24 18:00","2022-05-24 10:00","2022-05-24 18:00","연속"]
[250,"충북","직할","진천덕산#1 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-05-25 10:00","2022-05-25 18:00","취소","취소","연속"]
[251,"충북","직할","신진천진천#2 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-05-29 10:00","2022-05-29 18:00","2022-05-29 10:00","2022-05-29 18:00","연속"]
[252,"충북","청주","서청주사직#2 T/L","22-23년 청주전력 변전정비회사 총액공사","서청주,사직S/S 154kV 서청주사직#2T/L 보호반 대체","2022-05-02 09:00","2022-05-04 18:00","취소","취소","연속"]
[253,"충북","청주","신옥천남대전#2 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검","2022-05-11 10:00","2022-05-11 18:00","2022-05-11 10:00","2022-05-11 18:00","연속"]
[254,"충북","청주","신옥천남대전#1 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검","2022-05-10 10:00","2022-05-10 18:00","2022-05-10 10:00","2022-05-10 18:00","연속"]
[255,"충북","청주","신옥천남대전#3 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검","2022-05-12 10:00","2022-05-12 18:00","2022-05-12 10:00","2022-05-12 18:00","연속"]
[256,"충북","청주","신옥천남대전#4 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검","2022-05-13 10:00","2022-05-13 18:00","2022-05-13 10:00","2022-05-13 18:00","연속"]
[257,"충북","충주","단양영월CC#1 T/L","154kV 제천-영월T/L 용량증대 전선교체공사","병가철탑 안전이격상 휴전","2022-05-10 08:00","2022-05-15 18:00","2022-05-10 08:00","2022-05-15 18:00","연속"]
[258,"충북","충주","신제천영월CC#1 T/L","154kV 제천-영월T/L 용량증대 전선교체공사","병가철탑 안전이격상 휴전","2022-05-30 08:00","2022-06-06 18:00","2022-05-30 08:00","2022-06-06 18:00","연속"]
[259,"충북","충주","신제천영월CC#2 T/L","154kV 제천-영월T/L 용량증대 전선교체공사","병가철탑 안전이격상 휴전","2022-05-20 08:00","2022-05-27 18:00","2022-05-20 08:00","2022-05-27 18:00","연속"]
[260,"충북","충주","신충주북충주#2 T/L","신충주S/S 154kV GIS 설치공사","#62-63, #67-68 SEC 및 63-68 TIE GIS 설치 후 무부하가압","2022-05-19 13:00","2022-05-20 13:00","2022-05-19 08:00","2022-05-21 18:00","연속"]
[261,"충북","충주","신충주북충주#2 T/L","신충주S/S 154kV GIS 설치공사","#62-63, #67-68 SEC 및 63-68 TIE GIS 설치 후 무부하가압","2022-05-12 13:00","2022-05-13 13:00","2022-05-13 13:00","2022-05-14 13:00","연속"]
[262,"충북","충주","신충주북충주#2 T/L","신충주S/S 154kV GIS 설치공사","#64 M.Tr 1차 + 재세능원#2 T/L + #7 Sh.C 용 GIS 설치 후 무부하가압","2022-05-26 13:00","2022-05-27 13:00","취소","취소","연속"]
[263,"충북","충주","왕암여주#1 T/L","345kV 신제천-신충주 등 4개 T/L 추락방지시설 설치공사","154kV 왕암-여주#1 T/L 추락방지시설 설치공사","2022-05-26 07:00","2022-05-26 18:00","2022-05-26 07:00","2022-05-26 18:00","연속"]
[264,"충북","충주","왕암여주#2 T/L","345kV 신제천-신충주 등 4개 T/L 추락방지시설 설치공사","154kV 왕암-여주#2 T/L 추락방지시설 설치공사","2022-05-25 07:00","2022-05-25 18:00","2022-05-25 07:00","2022-05-25 18:00","연속"]
[265,"충북","충주","제천영월#2 T/L","154kV 제천-영월T/L 용량증대 전선교체공사","3 ~ 39호 전선교체, 철탑교체 10기","2022-05-02 08:00","2022-05-06 18:00","2022-05-02 08:00","2022-05-06 18:00","연속"]
[266,"충북","충주","제천영월#1 T/L","154kV 제천-영월T/L 용량증대 전선교체공사","3 ~ 39호 전선교체, 철탑교체 10기","2022-05-09 08:00","2022-05-28 18:00","2022-05-09 08:00","2022-05-28 18:00","연속"]
[267,"충북","충주","제천영월#2 T/L","154kV 제천-영월T/L 용량증대 전선교체공사","3 ~ 39호 전선교체, 철탑교체 10기","2022-05-30 08:00","2022-06-18 18:00","2022-05-30 08:00","2022-06-18 18:00","연속"]
[268,"대전세종충남","대전","금산무주#2 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 추부-금산#2T/L 추락방지시설 설치공사 안전거리 확보차","2022-05-19 08:00","2022-05-20 18:00","취소","취소","매일"]
[269,"대전세종충남","대전","신계룡두마#1 T/L","두마S/S 154kV 신계룡-두마#1T/L GIS 보통점검 및 병행작업","두마S/S 154kV 신계룡-두마#1T/L GIS 보통점검 및 병행작업","2022-05-09 09:00","2022-05-09 18:00","취소","취소","연속"]
[270,"대전세종충남","대전","신계룡두마#2 T/L","두마S/S 154kV 신계룡-두마#2T/L GIS 보통점검 및 병행작업","두마S/S 154kV 신계룡-두마#2T/L GIS 보통점검 및 병행작업","2022-05-10 09:00","2022-05-10 18:00","취소","취소","연속"]
[271,"대전세종충남","대전","추부금산#1 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 추부-금산#1T/L 추락방지시설 설치공사","2022-05-25 08:00","2022-06-10 18:00","취소","취소","매일"]
[272,"대전세종충남","대전","추부금산#2 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 추부-금산#2T/L 추락방지시설 설치공사","2022-05-04 08:00","2022-05-20 18:00","취소","취소","매일"]
[273,"대전세종충남","서산","서산대산#3 T/L","22년 서산P/O 변전협력회사 총액공사","서산S/S 154kV 서산-대산#3T/L 667 GIS 및 LA 보통점검 - (병행) 대산S/S 154kV 서산-대산#3T/L 627 GIS 보통점검","2022-05-27 09:00","2022-05-27 18:00","2022-05-27 09:00","2022-05-27 18:00","연속"]
[274,"대전세종충남","서산","신당진S/S SEC CB 60610","신당진S/S 154kV 장기사용GIS 대체공사(4차)","#60BUS측 무부하가압","2022-05-07 14:00","2022-05-08 14:00","2022-05-07 14:00","2022-05-08 14:00","연속"]
[275,"대전세종충남","서산","신당진S/S SEC CB 65660","신당진S/S 154kV 장기사용GIS 대체공사(4차)","#65BUS 종카바 무부하가압","2022-05-02 18:00","2022-05-03 08:00","2022-05-02 18:00","2022-05-03 08:00","연속"]
[276,"대전세종충남","서산","신당진S/S SEC CB 65660","신당진S/S 154kV 장기사용GIS 대체공사(4차)","#65BUS측 GIS 무부하가압","2022-05-12 14:00","2022-05-13 14:00","2022-05-12 14:00","2022-05-13 14:00","연속"]
[277,"대전세종충남","서산","신당진S/S #65 BUS","신당진S/S 154kV 장기사용GIS 교체공사(4차분)","신당진-당진#2T/L, #60-65BUS PT GIS 교체 - #2BUS 종카바 설치","2022-05-02 08:00","2022-05-03 08:00","2022-05-02 08:00","2022-05-03 08:00","연속"]
[278,"대전세종충남","서산","신당진당진#2 T/L","신당진S/S 154kV 장기사용GIS 교체공사(4차분)","신당진-당진#2T/L, #60-65BUS PT GIS 교체","2022-05-02 08:00","2022-05-17 16:00","2022-05-02 08:00","2022-05-17 16:00","연속"]
[279,"대전세종충남","서산","신당진서산#1 T/L","신당진S/S 154kV 장기사용GIS 교체공사(4차분)","신당진-당진#2T/L, #60-65BUS PT GIS 교체 - #65BUS 무부하가압","2022-05-02 18:00","2022-05-03 08:00","2022-05-02 18:00","2022-05-03 08:00","연속"]
[280,"대전세종충남","서산","신당진S/S #60 BUS","신당진S/S 154kV 장기사용GIS 교체공사(4차분)","신당진-당진#2T/L, #60-65BUS PT GIS 교체 - DS 631, CB 637, #60 BUS PT&ES 철거,설치","2022-05-03 08:00","2022-05-08 14:00","2022-05-03 08:00","2022-05-08 14:00","연속"]
[281,"대전세종충남","서산","신당진서산#1 T/L","신당진S/S 154kV 장기사용GIS 교체공사(4차분)","신당진-당진#2T/L, #60-65BUS PT GIS 교체 - #60BUS 무부하가압","2022-05-07 14:00","2022-05-08 14:00","2022-05-07 14:00","2022-05-08 14:00","연속"]
[282,"대전세종충남","서산","신당진S/S #65 BUS","신당진S/S 154kV 장기사용GIS 교체공사(4차분)","신당진-당진#2T/L, #60-65BUS PT GIS 교체 - DS632 , CB637, #65BUS PT&ES 철거,설치","2022-05-08 14:00","2022-05-13 14:00","2022-05-08 14:00","2022-05-13 14:00","연속"]
[283,"대전세종충남","서산","신당진S/S #65 BUS","신당진S/S 154kV 장기사용GIS 교체공사(4차분)","신당진-당진#2T/L, #60-65BUS PT GIS 교체 - 준공시험 후 상체크(신당진-당진#2T/L 이용)","2022-05-17 15:00","2022-05-17 16:00","2022-05-17 15:00","2022-05-17 16:00","연속"]
[284,"대전세종충남","서산","신당진S/S #60 BUS","신당진S/S 154kV 장기사용GIS 교체공사(4차분)","신당진-당진#2T/L, #60-65BUS PT GIS 교체 - 준공시험 후 상체크(신당진-당진#2T/L 이용)","2022-05-17 14:00","2022-05-17 15:00","2022-05-17 14:00","2022-05-17 15:00","연속"]
[285,"대전세종충남","서산","신당진서산#1 T/L","신당진S/S 154kV 장기사용GIS 교체공사(4차분)","신당진-당진#2T/L, #60-65BUS PT GIS 교체 - #65BUS 무부하가압(2DS, CB, 6DS 투입)","2022-05-12 14:00","2022-05-13 14:00","2022-05-12 14:00","2022-05-13 14:00","연속"]
[286,"대전세종충남","서산","합덕송악#1 T/L","154kV 합덕S/S 당진전철#1,2T/L 및 #3M.Tr 증설공사","154kV 합덕S/S 당진전철#1,2T/L 및 #3M.Tr 증설공사 무부하가압","2022-05-13 14:00","2022-05-14 14:00","2022-05-13 14:00","2022-05-14 14:00","연속"]
[287,"대전세종충남","서산","합덕송악#1 T/L","154kV 합덕S/S 당진전철#1,2T/L 및 #3M.Tr 증설공사","154kV 합덕S/S 당진전철#1,2T/L 및 #3M.Tr 증설공사 무부하가압","2022-05-23 14:00","2022-05-24 14:00","2022-05-23 14:00","2022-05-24 14:00","연속"]
[288,"대전세종충남","세종","덕진대화#1 T/L","[송전]154kV 덕진-대화#1T/L 추락방지시설 설치공사","[송전] 154kV 덕진-대화#1T/L 철탑 추락방지시설 설치공사, 피뢰기설치 - 추락방지 설치 : No.3, 8~20 (14기) - 피뢰기 설치 : No.2~3, 8~21 (16기)","2022-05-25 07:00","2022-05-30 18:00","2022-05-25 07:00","2022-05-30 18:00","매일"]
[289,"대전세종충남","세종","덕진공주#2 T/L","[송전] 154kV 덕진-유성T/L 철탑 추락방지장치 설치공사","-철탑 수직, 수평 추락방지장치 설치공사 -동시휴전(4회선 선로) 154kV 덕진-유성#2T/L 5/2-12 154kV 덕진-공주#2T/L 5/6-12","2022-05-06 08:00","2022-05-12 18:00","2022-05-06 08:00","2022-05-12 18:00","연속"]
[290,"대전세종충남","세종","덕진유성#1 T/L","[송전] 154kV 덕진-유성T/L 철탑 추락방지장치 설치공사","-철탑 수직, 수평 추락방지장치 설치공사 -동시휴전(4회선 선로) 154kV 덕진-유성#1T/L 5/13-23 154kV 덕진-공주#1T/L 5/17-24","2022-05-13 08:00","2022-05-23 18:00","2022-05-13 08:00","2022-05-23 18:00","연속"]
[291,"대전세종충남","세종","덕진공주#1 T/L","[송전] 154kV 덕진-유성T/L 철탑 추락방지장치 설치공사","-철탑 수직, 수평 추락방지장치 설치공사 -동시휴전(4회선 선로) 154kV 덕진-유성#1T/L 5/13-23 154kV 덕진-공주#1T/L 5/17-24","2022-05-17 08:00","2022-05-24 18:00","2022-05-17 08:00","2022-05-24 18:00","연속"]
[292,"대전세종충남","세종","대덕덕진#2 T/L","[송전]154kV 덕진-대화#1T/L 추락방지시설 설치공사 병가선로","[송전] 154kV 덕진-대화#1T/L 철탑 추락방지시설 설치공사, 피뢰기설치 병가선로 - 추락방지 설치 : No.3, 8~20 (14기) - 피뢰기 설치 : No.2~3, 8~21 (16기)","2022-05-30 07:00","2022-05-30 18:00","2022-05-30 07:00","2022-05-30 18:00","매일"]
[293,"대전세종충남","세종","덕진대화#2 T/L","[송전]154kV 덕진-대화#2T/L 추락방지시설 설치공사","[송전] 154kV 덕진-대화#2T/L 철탑 추락방지시설 설치공사 - No.3, 8~11, 13, 15~20 (12기)","2022-05-31 07:00","2022-05-31 18:00","2022-05-31 07:00","2022-05-31 18:00","매일"]
[294,"대전세종충남","세종","덕진유성#2 T/L","[송전] 154kV 덕진-유성T/L 철탑 추락방지장치 설치공사","-철탑 수직, 수평 추락방지장치 설치공사 -동시휴전(4회선 선로) 154kV 덕진-유성#2T/L 5/2-12 154kV 덕진-공주#2T/L 5/6-12","2022-05-02 08:00","2022-05-12 18:00","2022-05-02 08:00","2022-05-12 18:00","연속"]
[295,"대전세종충남","세종","세종둔곡#2 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-05-25 09:30","2022-05-25 18:00","2022-05-25 09:30","2022-05-25 18:00","연속"]
[296,"대전세종충남","세종","세종둔곡#1 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-05-24 09:30","2022-05-24 18:00","2022-05-24 09:30","2022-05-24 18:00","연속"]
[297,"대전세종충남","세종","둔곡송강#2 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-05-12 09:30","2022-05-12 18:00","2022-05-12 09:30","2022-05-12 18:00","연속"]
[298,"대전세종충남","세종","둔곡송강#1 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 하자점검","2022-05-06 09:30","2022-05-06 18:00","2022-05-06 09:30","2022-05-06 18:00","연속"]
[299,"대전세종충남","세종","부강대청HP T/L","[송전]154kV 세종-부강#1T/L 추락방지시설 설치공사 병가선로","[송전] 154kV 세종-부강#1T/L 철탑 추락방지시설 설치, 불량애자교체, 피뢰기설치 병가선로 - 추락방지시설 설치 : No. 1~6 (6기) - 불량애자 교체공사 : No. 6 (1기) - 피뢰기 설치공사 : No.1~11 (11기)","2022-05-02 07:00","2022-05-04 18:00","2022-05-02 07:00","2022-05-04 18:00","매일"]
[300,"대전세종충남","세종","세종월산#1 T/L","[송전]154kV 세종-월산#1T/L 피뢰기설치","[송전] 154kV 세종-월산#1T/L 피뢰기설치 - No. 19~28, 35~43 (19기)","2022-05-09 07:00","2022-05-10 18:00","2022-05-09 07:00","2022-05-10 18:00","매일"]
[301,"대전세종충남","세종","세종부강#1 T/L","[송전]154kV 세종-부강#1T/L 추락방지시설 설치공사","[송전] 154kV 세종-부강#1T/L 철탑 추락방지시설 설치, 불량애자교체, 피뢰기설치 - 추락방지시설 설치 : No. 1~6 (6기) - 불량애자 교체공사 : No. 6 (1기) - 피뢰기 설치공사 : No.1~11 (11기)","2022-05-02 07:00","2022-05-06 18:00","2022-05-02 07:00","2022-05-05 18:00","매일"]
[302,"대전세종충남","세종","조치원월산 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2022-05-04 09:30","2022-05-04 14:00","2022-05-04 09:30","2022-05-04 14:00","연속"]
[303,"대전세종충남","세종","월산서세종 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2022-05-04 14:00","2022-05-04 18:00","2022-05-04 14:00","2022-05-04 18:00","연속"]
[304,"대전세종충남","세종","천안전의#1 T/L","[송전]154kV 천안-전의#1T/L 추락방지시설 설치공사","[송전] 154kV 천안-전의#1T/L 철탑 추락방지시설 설치공사 - No.0.1, 1~8, 10~32, 34~35, 37 (35기)","2022-05-30 07:00","2022-06-07 18:00","취소","취소","매일"]
[305,"대전세종충남","세종","조치원월산 T/L","[송전]154kV 조치원-전의T/L 지장송전선로 이설공사","○ 공사구간 : 154kV 조치원-전의T/L No.20~24 ○ 지지물 : 신설 3기 설치, 임시 3기 설치/철거, 기설 3기 철거 ○ 전력선 : ASCC/TW 430 x S x 2C, 1.388km(전선교체)","2022-05-16 07:00","2022-05-20 18:00","2022-05-16 07:00","2022-05-20 18:00","연속"]
[306,"대전세종충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 지장송전선로 이설공사","○ 공사구간 : 154kV 조치원-전의T/L No.20~24 ○ 지지물 : 신설 3기 설치, 임시 3기 설치/철거, 기설 3기 철거 ○ 전력선 : ASCC/TW 430 x S x 2C, 1.388km(전선교체)","2022-05-23 07:00","2022-05-27 18:00","2022-05-23 07:00","2022-05-27 18:00","연속"]
[307,"대전세종충남","직할","대화둔산#1 T/L","22년 직할 170kV GIS 정밀점검 공사","22년 직할 170kV GIS 정밀점검 공사","2022-05-02 09:00","2022-05-03 18:00","2022-05-02 09:00","2022-05-03 18:00","연속"]
[308,"대전세종충남","직할","신일S/S 대전열병합T/L CB","22년 직할 170kV GIS 정밀점검 공사","22년 직할 170kV GIS 정밀점검 공사","2022-05-17 09:00","2022-05-19 12:00","2022-05-17 09:00","2022-05-19 12:00","연속"]
[309,"대전세종충남","천안","신온양석곡#1 T/L","석곡S/S 신온양석곡#1 T/L GIS 보통점검","석곡S/S 신온양석곡#1 T/L GIS 보통점검","2022-05-03 09:00","2022-05-03 18:00","2022-05-03 09:00","2022-05-03 18:00","연속"]
[310,"대전세종충남","천안","신온양석곡#2 T/L","석곡S/S 신온양석곡#2 T/L GIS 보통점검","석곡S/S 신온양석곡#2 T/L GIS 보통점검","2022-05-04 09:00","2022-05-04 18:00","2022-05-04 09:00","2022-05-04 18:00","연속"]
[311,"대전세종충남","천안","신온양한샘#1 T/L","신온양S/S 154kV 신온양한샘#1 T/L GIS 보통점검","신온양S/S 154kV 신온양한샘#1 T/L GIS 보통점검","2022-05-09 09:00","2022-05-09 18:00","2022-05-09 09:00","2022-05-09 18:00","연속"]
[312,"대전세종충남","천안","아산예산#1 T/L","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-05-30 14:00","2022-05-31 14:00","2022-05-30 14:00","2022-05-31 14:00","연속"]
[313,"대전세종충남","천안","아산S/S #66 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-05-18 09:00","2022-05-31 14:00","2022-05-18 09:00","2022-05-31 14:00","연속"]
[314,"대전세종충남","천안","아산예산#1 T/L","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-05-18 09:00","2022-05-23 18:00","2022-05-18 09:00","2022-05-23 18:00","연속"]
[315,"대전세종충남","천안","아산S/S #65 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-05-18 09:00","2022-05-31 14:00","2022-05-18 09:00","2022-05-31 14:00","연속"]
[316,"대전세종충남","천안","아산합덕#1 T/L","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-05-18 09:00","2022-06-17 16:00","2022-05-18 09:00","2022-06-17 16:00","연속"]
[317,"대전세종충남","천안","아산예산#1 T/L","154kV 예산S/S 미래화공사","154kV 예산S/S 미래화공사 - T/L 인출변경 관련 휴전","2022-05-09 09:00","2022-05-10 13:00","취소","취소","연속"]
[318,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용 GIS 대체공사","154kV 아산-온양#1T/L GIS 교체(#65, 66BUS 무부하가압)","2022-05-19 10:00","2022-05-20 10:00","2022-05-19 10:00","2022-05-20 10:00","연속"]
[319,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용 GIS 대체공사","154kV 아산-온양#1T/L GIS 교체(#65, 66BUS 무부하가압)","2022-05-05 10:00","2022-05-06 10:00","2022-05-05 10:00","2022-05-06 10:00","연속"]
[320,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용 GIS 대체공사","154kV 아산-온양#1T/L GIS 교체(#60, 61BUS 무부하가압)","2022-05-12 10:00","2022-05-13 10:00","2022-05-12 10:00","2022-05-13 10:00","연속"]
[321,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용 GIS 대체공사","154kV 아산-온양#1T/L GIS 교체(#65, 66BUS 무부하가압)","2022-05-10 09:00","2022-05-10 10:00","2022-05-10 09:00","2022-05-10 10:00","연속"]
[322,"대전세종충남","천안","아산온양#2 T/L","온양S/S 154kV 장기사용 GIS 대체공사","154kV 아산-온양#2T/L GIS 교체","2022-05-09 10:00","2022-05-20 11:00","2022-05-09 10:00","2022-05-17 11:00","연속"]
[323,"대전세종충남","천안","장재천안#2 T/L","[송전]154kV 장재-천안T/L No.19~21 지장송전선로 지중화공사","154kV 장재-천안T/L No.19~21 지중화(요청자 직접시행) - XLPE 2,000㎟(D) × 2C, 1.202km","2022-05-30 08:00","2022-07-10 18:00","2022-05-31 14:00","2022-07-10 18:00","연속"]
[324,"대전세종충남","천안","장재천안#1 T/L","[송전]154kV 장재-천안T/L No.19~21 지장송전선로 지중화공사","154kV 장재-천안T/L No.19~21 지중화(요청자 직접시행) - XLPE 2,000㎟(D) × 2C, 1.202km","2022-05-30 08:00","2022-07-10 18:00","2022-05-31 14:00","2022-07-10 18:00","연속"]
[325,"대전세종충남","청양","청양신풍#1 T/L","2022년 청양P/O 170kV GIS 정밀점검","2022년 청양P/O 170kV GIS 정밀점검","2022-05-16 09:00","2022-05-18 14:00","2022-05-16 09:00","2022-05-18 14:00","연속"]
[326,"대전세종충남","청양","청양신풍#2 T/L","2022년 청양P/O 170kV GIS 정밀점검","2022년 청양P/O 170kV GIS 정밀점검","2022-05-18 14:00","2022-05-20 18:00","2022-05-18 14:00","2022-05-20 18:00","연속"]
[327,"대전세종충남","청양","청양관창#1 T/L","2022년 청양P/O 170kV GIS 정밀점검","2022년 청양P/O 170kV GIS 정밀점검","2022-05-09 09:00","2022-05-11 14:00","2022-05-09 09:00","2022-05-11 14:00","연속"]
[328,"대전세종충남","청양","청양관창#2 T/L"," 2022년 청양P/O 170kV GIS 정밀점검","2022년 청양P/O 170kV GIS 정밀점검","2022-05-11 14:00","2022-05-13 18:00","2022-05-11 14:00","2022-05-13 18:00","연속"]
[329,"대전세종충남","청양","청양S/S CB 6200","청양S/S 154kV BUS-TIE 관련 점검","청양S/S 154kV BUS-TIE 관련 점검(6200) - 차단기 부동작 예방 조작시험 - 영인제 모선보호반 성능개선","2022-05-11 14:00","2022-05-11 18:00","2022-05-11 14:00","2022-05-11 18:00","연속"]
[330,"대전세종충남","청양","청양S/S CB 6100","청양S/S 154kV BUS-TIE 관련 점검","청양S/S 154kV BUS-TIE 관련 점검(6100) - 차단기 부동작 예방 조작시험 - 영인제 모선보호반 성능개선","2022-05-11 09:00","2022-05-11 14:00","2022-05-11 09:00","2022-05-11 14:00","연속"]
[331,"대전세종충남","청양","홍성S/S #66 BUS","홍성 154kV 내포그린에너지 #1,2T/L GIS 증설","홍성 154kV 내포그린에너지 #1,2T/L GIS 증설","2022-05-30 09:00","2022-06-03 18:00","2022-05-09 09:00","2022-05-11 11:00","연속"]
[332,"대전세종충남","청양","홍성S/S #61 BUS","홍성 154kV 내포그린에너지 #1,2T/L GIS 증설","홍성 154kV 내포그린에너지 #1,2T/L GIS 증설","2022-05-23 09:00","2022-05-27 18:00","2022-05-11 11:00","2022-05-14 14:00","연속"]
[333,"대전세종충남","청양","홍성S/S #65 BUS","홍성 154kV 내포그린에너지 #1,2T/L GIS 증설","홍성 154kV 내포그린에너지 #1,2T/L GIS 증설","2022-05-16 09:00","2022-05-20 18:00","2022-05-02 09:00","2022-05-04 11:00","연속"]
[334,"대전세종충남","청양","홍성S/S #60 BUS","홍성 154kV 내포그린에너지 #1,2T/L GIS 증설","홍성 154kV 내포그린에너지 #1,2T/L GIS 증설","2022-05-09 09:00","2022-05-13 18:00","2022-05-04 11:00","2022-05-07 14:00","연속"]
[335,"전북","군산","탄소이리#2 T/L","군산P/O 154kV 이상 차단기 보통점검","이리S/S 647 CB 보통점검","2022-05-30 09:00","2022-05-30 18:00","2022-05-30 15:00","2022-05-30 20:00","연속"]
[336,"전북","군산","탄소이리#1 T/L","군산P/O 154kV 이상 차단기 보통점검","이리S/S 637 CB 보통점검","2022-05-31 09:00","2022-05-31 18:00","2022-05-31 15:00","2022-05-31 20:00","연속"]
[337,"전북","군산","팔봉봉동#2 T/L","154kV 왕궁S/S 건설사업","- 팔봉S/S 송전선보호반 대체 * 2면 - 봉동S/S 송전선보호반 대체 * 2면 - 대국시험, 계통연동시험, 선로정수","2022-05-09 15:00","2022-05-10 10:00","2022-05-09 15:00","2022-05-10 10:00","연속"]
[338,"전북","군산","팔봉봉동#1 T/L","154kV 왕궁S/S 건설사업","- 팔봉S/S 송전선보호반 대체 * 2면 - 봉동S/S 송전선보호반 대체 * 2면 - 대국시험, 계통연동시험, 선로정수","2022-05-02 15:00","2022-05-03 10:00","2022-05-02 15:00","2022-05-03 10:00","연속"]
[339,"전북","김제","정주고창#1 T/L","154kV 소성분기 송전선로 건설사업","154kV 소성분기 송전선로 건설사업 - 신설철탑 조립 및 #1T/L By-Pass 구성","2022-05-27 08:00","2022-05-31 18:00","취소","취소","연속"]
[340,"전북","김제","정주고창#2 T/L","154kV 소성분기 송전선로 건설사업","154kV 소성분기 송전선로 건설사업 - 가선로 구성","2022-05-23 08:00","2022-05-26 18:00","취소","취소","연속"]
[341,"전북","직할","남원임실#1 T/L","154kV 곡성-남원 등 2개T/L 피뢰기 설치공사","공사명 : 154kV 곡성-남원 등 2개T/L 피뢰기 설치공사 공사내용 : 154kV 남원-임실 #1T/L 피뢰기 설치공사 - 피뢰기 설치 : 84기","2022-05-23 09:00","2022-05-31 18:00","2022-05-23 09:00","2022-05-31 18:00","매일"]
[342,"광주전남","강진","대불삼호#2 T/L","대불S/S KC T/L 보호배전반 교체 공사","대불S/S KC T/L 보호배전반 교체 공사","2022-05-23 09:00","2022-05-23 18:00","취소","취소","연속"]
[343,"광주전남","강진","대불삼호#1 T/L","대불S/S KC T/L 보호배전반 교체 공사","대불S/S KC T/L 보호배전반 교체 공사","2022-05-23 09:00","2022-05-23 18:00","취소","취소","연속"]
[344,"광주전남","강진","신강진대불#1 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","대불S/S 신강진-대불#1,2T/L LA A,B,C 보통점검(비상시 20분이내 가압가능)","2022-05-26 10:00","2022-05-26 14:00","2022-05-26 10:00","2022-05-26 14:00","연속"]
[345,"광주전남","강진","신강진대불#2 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","대불S/S 신강진-대불#1,2T/L LA A,B,C 보통점검(비상시 20분이내 가압가능)","2022-05-26 14:00","2022-05-26 18:00","2022-05-26 14:00","2022-05-26 18:00","연속"]
[346,"광주전남","광주","신광주계림#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","신광주-계림#2T/L 보호반대체 (즉시가압 불가)","2022-05-23 09:00","2022-05-26 18:00","2022-05-23 09:00","2022-05-26 18:00","연속"]
[347,"광주전남","광주","신광주장성#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","신광주-장성#2T/L 170kV GIS 보통점검","2022-05-09 09:00","2022-05-09 18:00","2022-05-09 09:00","2022-05-09 18:00","연속"]
[348,"광주전남","광주","신광주계림#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","신광주-계림#1T/L 보호반대체 (즉시가압 불가)","2022-05-02 09:00","2022-05-04 18:00","2022-05-02 09:00","2022-05-04 18:00","연속"]
[349,"광주전남","광주","신화순화순#2 T/L","신화순S/S 154kV 금성산풍력T/L GIS 신규수용공사(#2BUS)","신화순S/S 154kV 금성산풍력T/L GIS 신규수용공사(#2BUS) - 2DS, 상부BUS, CHD, 라인PT 설치","2022-05-18 09:00","2022-05-19 18:00","2022-05-19 09:00","2022-05-20 18:00","연속"]
[350,"광주전남","광주","신화순화순#1 T/L","신화순S/S 154kV 금성산풍력T/L GIS 신규수용공사(#1BUS)","신화순S/S 154kV 금성산풍력T/L GIS 신규수용공사(#1BUS) - CB, #1DS 설치","2022-05-11 09:00","2022-05-12 18:00","2022-05-11 09:00","2022-05-12 18:00","연속"]
[351,"광주전남","광주","신화순화순#2 T/L","신화순S/S 154kV 금성산풍력T/L GIS 신규수용공사(무부하가압)","신화순S/S 154kV 금성산풍력T/L GIS 신규수용공사(무부하가압) - 고객측 CABLE 건전성 확인","2022-05-25 09:00","2022-05-26 18:00","2022-05-25 09:00","2022-05-26 18:00","연속"]
[352,"광주전남","광주","일곡비아#2 T/L","154kV 일곡-비아 지중화 토목공사","일곡S/S 구내 154kV 일곡-비아 #2T/L WALL BUSHING 근처 변전소 인입부 굴착 및 PASS맨홀 시공","2022-05-01 09:00","2022-05-31 18:00","2022-05-01 09:00","2022-05-31 18:00","연속"]
[353,"광주전남","목포","화원안좌#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 전선교체공사 1~22, 28~47호 - 추락방지시설 설치공사","2022-05-16 09:00","2022-06-13 18:00","취소","취소","연속"]
[354,"광주전남","목포","엄다무안햇빛#2 T/L","154kV 엄다-운남T/L 용량증대 전선교체공사","ㅇ 목적 : 신안지역 신재생발전 계통 연계를 위하여 송전선로 설비보강 시행 ㅇ 공사개요 - ACSR/AW 330㎟에서 ASCC/TW 430㎟로 용량증대 전선교체 - 엄다S/S 구내 C/T철탑 개조","2022-05-20 09:00","2022-06-18 18:00","2022-05-20 09:00","2022-06-18 18:00","연속"]
[355,"광주전남","목포","나주엄다#2 T/L","목포전력지사 개폐장치 보통점검 및 전자변 교체공사","엄다S/S 나주-엄다#2T/L GIS 보통점검 및 전자변 교체","2022-05-16 09:00","2022-05-17 18:00","2022-05-16 09:00","2022-05-17 18:00","연속"]
[356,"광주전남","순천","여수소라#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","소라S/S 여수-소라#1, 2T/L GIS CB 타임측정 여수S/S 여수-소라#1, 2T/L GIS CB 타임측정","2022-05-13 10:00","2022-05-13 14:00","2022-05-13 10:00","2022-05-13 14:00","연속"]
[357,"광주전남","순천","여수소라#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","소라S/S 여수-소라#1, 2T/L GIS CB 타임측정 여수S/S 여수-소라#1, 2T/L GIS CB 타임측정","2022-05-13 14:00","2022-05-13 18:00","2022-05-13 14:00","2022-05-13 18:00","연속"]
[358,"광주전남","순천","율촌여수산단#2 T/L","순천전력지사 170kV GIS 정밀점검","순천전력지사 170kV GIS 정밀점검","2022-05-25 09:00","2022-05-27 18:00","취소","취소","연속"]
[359,"광주전남","순천","율촌여수산단#1 T/L","순천전력지사 170kV GIS 정밀점검","순천전력지사 170kV GIS 정밀점검","2022-05-16 09:00","2022-05-18 18:00","취소","취소","연속"]
[360,"광주전남","순천","여수T/P CB 6100","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-05-04 09:00","2022-05-07 18:00","취소","취소","연속"]
[361,"광주전남","순천","여수T/P CB 6200","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #61-66 BUS-Pro 보호반 대체","2022-05-11 09:00","2022-05-14 18:00","취소","취소","연속"]
[362,"광주전남","순천","호남TP여수TP#2 T/L","순천전력지사 170kV GIS 정밀점검","순천전력지사 170kV GIS 정밀점검","2022-05-30 09:00","2022-05-31 18:00","취소","취소","연속"]
[363,"광주전남","순천","호남TP여수TP#1 T/L","순천전력지사 170kV GIS 정밀점검","순천전력지사 170kV GIS 정밀점검","2022-05-19 09:00","2022-05-20 18:00","취소","취소","연속"]
[364,"광주전남","순천","여수TP여천#2 T/L","순천전력지사 170kV GIS 정밀점검","순천전력지사 170kV GIS 정밀점검","2022-05-11 09:00","2022-05-12 18:00","취소","취소","연속"]
[365,"광주전남","순천","여수TP여천#1 T/L","순천전력지사 170kV GIS 정밀점검","순천전력지사 170kV GIS 정밀점검","2022-05-09 09:00","2022-05-10 18:00","취소","취소","연속"]
[366,"광주전남","순천","여수T/P #65 BUS","LG NCC 증설공사","#2DS 설치","2022-05-25 09:00","2022-05-27 18:00","취소","취소","연속"]
[367,"광주전남","순천","여수T/P SEC CB 65660","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-05-04 09:00","2022-05-07 18:00","취소","취소","연속"]
[368,"광주전남","순천","여수T/P SEC CB 60610","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-05-04 09:00","2022-05-07 18:00","취소","취소","연속"]
[369,"광주전남","순천","여수T/P SEC CB 65660","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #61-66 BUS-Pro 보호반 대체","2022-05-11 09:00","2022-05-14 18:00","취소","취소","연속"]
[370,"광주전남","순천","여수T/P SEC CB 60610","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #61-66 BUS-Pro 보호반 대체","2022-05-11 09:00","2022-05-14 18:00","취소","취소","연속"]
[371,"광주전남","순천","여천여수#2 T/L","여천S/S #2M.Tr 장기사용 교체 공사","#2M.Tr 1차 모선교체관련 안전이격확보 및 무부하가압","2022-05-24 10:00","2022-05-26 18:00","2022-05-24 10:00","2022-05-26 18:00","연속"]
[372,"광주전남","순천","여수TP용성#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#1T/L LA(A, B, C) 하자점검","2022-05-20 10:00","2022-05-20 14:00","취소","취소","연속"]
[373,"광주전남","순천","여수TP용성#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#2T/L LA(A, B, C) 하자점검 여수화력S/Y 여수TP-용성#2T/L GIS 보통점검","2022-05-19 10:00","2022-05-19 18:00","취소","취소","연속"]
[374,"광주전남","직할","비아하남#1 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","하남S/S 비아-하남#1T/L CVT 대체공사","2022-05-02 09:00","2022-05-02 18:00","2022-05-03 09:00","2022-05-03 18:00","연속"]
[375,"광주전남","직할","하남장성#1 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","하남S/S 하남-장성#1T/L GIS, CVT 보통점검, LA대체","2022-05-06 09:00","2022-05-06 18:00","2022-05-06 09:00","2022-05-06 18:00","연속"]
[376,"광주전남","직할","하남장성#2 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","하남S/S 하남-장성#2T/L GIS, LA 보통점검, CVT 대체","2022-05-04 09:00","2022-05-04 18:00","2022-05-04 09:00","2022-05-04 18:00","연속"]
[377,"광주전남","직할","농성화정#2 T/L","직할 170kV GIS 정밀점검공사","직할 170kV GIS 정밀점검공사","2022-05-09 09:00","2022-05-11 18:00","2022-05-16 09:00","2022-05-18 18:00","연속"]
[378,"대구","경산","신경산진량 T/L","22~23년 경산PO 변전협력회사 총액공사","- 신경산SS : GIS 보통점검 - 진량SS : 장기미동작 차단기 조작시험","2022-05-09 09:30","2022-05-09 18:00","2022-05-09 09:30","2022-05-09 18:00","연속"]
[379,"대구","경산","신경산노변 T/L","22~23년 경산PO 변전협력회사 총액공사","- 신경산SS : GIS 보통점검 - 노변SS : 장기미동작 차단기 조작시험","2022-05-02 09:30","2022-05-02 18:00","2022-05-02 09:30","2022-05-02 18:00","연속"]
[380,"대구","경산","진량노변 T/L","22~23년 경산PO 변전협력회사 총액공사","- 장기미동작 차단기 조작시험","2022-05-04 09:30","2022-05-04 18:00","2022-05-04 09:30","2022-05-04 18:00","연속"]
[381,"대구","경산","청도밀양#1 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-05-12 18:00","2022-05-13 09:30","2022-05-10 18:00","2022-05-11 09:30","연속"]
[382,"대구","경산","청도밀양#2 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-05-18 18:00","2022-05-19 09:30","2022-05-13 18:00","2022-05-14 09:30","연속"]
[383,"대구","경산","청도밀양#1 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-05-29 18:00","2022-05-30 09:30","2022-05-25 18:00","2022-05-26 09:30","연속"]
[384,"대구","달성","고령다산#2 T/L","고령S/S 고령-다산#2T/L GIS 하자점검","고령S/S 고령-다산#2T/L GIS 하자점검 다산S/S 차단기동작특성시험","2022-05-13 09:00","2022-05-13 18:00","2022-05-13 09:00","2022-05-13 18:00","연속"]
[385,"대구","달성","고령다산#1 T/L","고령S/S 고령-다산#1T/L GIS 하자점검","고령S/S 고령-다산#1T/L GIS 하자점검 다산S/S 차단기동작특성시험","2022-05-12 09:00","2022-05-12 18:00","2022-05-12 09:00","2022-05-12 18:00","연속"]
[386,"대구","달성","강창다사 T/L","다사S/S 강창-다사T/L GIS 보통점검","다사S/S 강창-다사T/L GIS 보통점검 강창S/S 차단기 동작특성시험","2022-05-24 09:00","2022-05-24 18:00","2022-05-24 09:00","2022-05-24 18:00","연속"]
[387,"대구","달성","달성상인#2 T/L","대한전선 열경화공법 EBG 보강공사","가스채취밸브 설치 : 상인S/S EBG 6상","2022-05-16 08:00","2022-05-18 18:00","취소","취소","연속"]
[388,"대구","달성","달성상인#1 T/L","대한전선 열경화공법 EBG 보강공사","가스채취밸브 설치 : 상인S/S EBG 6상","2022-05-09 08:00","2022-05-11 18:00","취소","취소","연속"]
[389,"대구","달성","대구봉덕#1 T/L","대구S/S 대구-청도#2T/L GIS 정밀점검 무부하가압[TEST 선로]","대구S/S 대구-청도#2T/L GIS 정밀점검 무부하가압[TEST 선로]","2022-05-24 13:00","2022-05-24 18:00","2022-05-24 13:00","2022-05-24 18:00","연속"]
[390,"대구","달성","대구청도#2 T/L","대구S/S 대구-청도#2 T/L GIS 정밀점검","대구S/S 대구-청도#2 T/L GIS 정밀점검","2022-05-23 09:00","2022-05-24 18:00","2022-05-23 09:00","2022-05-24 18:00","연속"]
[391,"대구","달성","두류봉덕#1 T/L","#60-#65 BUS TIE GIS 무부하가압[TEST 선로]","#60-#65 BUS TIE GIS 무부하가압[TEST 선로]","2022-05-26 13:00","2022-05-26 18:00","2022-05-26 13:00","2022-05-26 18:00","연속"]
[392,"대구","달성","내당두류#1 T/L","두류S/S 내당-두류#1 T/L GIS 정밀점검","두류S/S 내당-두류#1 T/L GIS 정밀점검","2022-05-30 09:00","2022-05-31 18:00","2022-05-30 09:00","2022-05-31 18:00","연속"]
[393,"대구","달성","두류봉덕#1 T/L","대한전선 열경화공법 EBG 보강공사","가스채취밸브 설치 : 두류S/S EBG 6상, 봉덕S/S EBG 6상","2022-05-10 08:00","2022-05-13 18:00","취소","취소","연속"]
[394,"대구","달성","두류봉덕#2 T/L","대한전선 열경화공법 EBG 보강공사","가스채취밸브 설치 : 두류S/S EBG 6상, 봉덕S/S EBG 6상","2022-05-17 08:00","2022-05-20 18:00","취소","취소","연속"]
[395,"대구","달성","월배와룡#2 T/L","월배S/S 월배-와룡#2 T/L GIS 정밀점검","월배S/S 월배-와룡#2 T/L GIS 정밀점검","2022-05-11 09:00","2022-05-12 18:00","2022-05-11 09:00","2022-05-12 18:00","연속"]
[396,"대구","달성","월배와룡#1 T/L","월배S/S 월배-와룡#1 T/L GIS 정밀점검","월배S/S 월배-와룡#1 T/L GIS 정밀점검","2022-05-09 09:00","2022-05-10 18:00","2022-05-09 09:00","2022-05-10 18:00","연속"]
[397,"대구","직할","동인내당#1 T/L","내당S/S 모선보호반 교체작업","내당S/S 모선보호반 교체작업(준공시험용)","2022-05-19 10:00","2022-05-19 10:30","2022-05-19 10:00","2022-05-19 10:30","연속"]
[398,"대구","직할","팔달내당#1 T/L","내당S/S 모선보호반 교체작업","내당S/S 모선보호반 교체작업(준공시험용)","2022-05-19 11:30","2022-05-19 12:00","2022-05-19 11:30","2022-05-19 12:00","연속"]
[399,"대구","직할","팔달내당#2 T/L","내당S/S 모선보호반 교체작업","내당S/S 모선보호반 교체작업(준공시험용)","2022-05-19 13:00","2022-05-19 13:30","2022-05-19 13:00","2022-05-19 13:30","연속"]
[400,"대구","직할","내당두류#1 T/L","내당S/S 모선보호반 교체작업","내당S/S 모선보호반 교체작업(준공시험용)","2022-05-19 13:30","2022-05-19 14:00","2022-05-19 13:30","2022-05-19 14:00","연속"]
[401,"대구","직할","내당두류#2 T/L","내당S/S 모선보호반 교체작업","내당S/S 모선보호반 교체작업(준공시험용)","2022-05-19 14:00","2022-05-19 14:30","2022-05-19 14:00","2022-05-19 14:30","연속"]
[402,"대구","직할","동인내당#2 T/L","내당S/S 모선보호반 교체작업","내당S/S 모선보호반 교체작업(준공시험용)","2022-05-19 10:30","2022-05-19 11:00","2022-05-19 10:30","2022-05-19 11:00","연속"]
[403,"대구","직할","동인내당#2 T/L","동인S/S 모선보호반 교체작업","동인S/S 모선보호반 교체작업(준공시험용)","2022-05-26 13:30","2022-05-26 14:00","2022-05-26 13:30","2022-05-26 14:00","연속"]
[404,"대구","직할","동인내당#1 T/L","동인S/S 모선보호반 교체작업","동인S/S 모선보호반 교체작업(준공시험용)","2022-05-26 11:30","2022-05-26 12:00","2022-05-26 11:30","2022-05-26 12:00","연속"]
[405,"대구","직할","남대구동인#2 T/L","동인S/S 모선보호반 교체작업","동인S/S 모선보호반 교체작업(준공시험용)","2022-05-26 11:00","2022-05-26 11:30","2022-05-26 11:00","2022-05-26 11:30","연속"]
[406,"대구","직할","남대구동인#1 T/L","동인S/S 모선보호반 교체작업","동인S/S 모선보호반 교체작업(준공시험용)","2022-05-26 10:00","2022-05-26 10:30","2022-05-26 10:00","2022-05-26 10:30","연속"]
[407,"대구","칠곡","구미광평#2 T/L","광평S/S 구미-광평 #2T/L GIS 정밀점검","광평S/S 구미-광평 #2T/L GIS 정밀점검","2022-05-02 09:30","2022-05-03 18:00","2022-05-02 09:30","2022-05-03 18:00","연속"]
[408,"대구","칠곡","김천금릉#1 T/L","금릉S/S 성주-금릉 #1T/L GIS 정밀점검 무부하 가압","금릉S/S 성주-금릉 #1T/L GIS 정밀점검 무부하 가압","2022-05-05 13:00","2022-05-05 18:00","2022-05-05 13:00","2022-05-05 18:00","연속"]
[409,"대구","칠곡","농소김천#1 T/L","154kV 김천S/S 현대화공사","154kV 농소-김천#1T/L #2BUS측 리드선 교체","2022-05-21 09:00","2022-05-21 15:00","2022-05-21 09:00","2022-05-21 15:00","연속"]
[410,"대구","칠곡","김천금릉#1 T/L","대한전선 열경화공법 EBG 보강공사","대한전선 열경화공법 EBG 가스채취밸브 설치공사(스프링유닛점검 포함) 154kV 김천-금릉T/L 김천S/S EBG 6상","2022-05-23 08:00","2022-05-24 18:00","2022-05-23 08:00","2022-05-23 18:00","연속"]
[411,"대구","칠곡","김천금릉#2 T/L","대한전선 열경화공법 EBG 보강공사","대한전선 열경화공법 EBG 가스채취밸브 설치공사(스프링유닛점검 포함) 154kV 김천-금릉T/L 김천S/S EBG 6상","2022-05-25 08:00","2022-05-26 18:00","2022-05-26 08:00","2022-05-26 18:00","연속"]
[412,"대구","칠곡","어모김천#1 T/L","154kV 김천S/S 현대화공사","154kV 어모-김천#1T/L #2BUS측 리드선 교체","2022-05-21 15:00","2022-05-21 18:00","2022-05-21 15:00","2022-05-21 18:00","연속"]
[413,"대구","칠곡","서대구칠곡#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 → GIS 부하전환 사전대비 옥외철구 계탑작업","2022-05-16 09:00","2022-05-18 18:00","2022-05-16 09:00","2022-05-18 18:00","연속"]
[414,"대구","포항","포항천북 T/L","건천-천북#1T/L A상 송전선로 불량개소 보수(안전이격)","건천-천북#1T/L A상 송전선로 불량개소 보수(안전이격)","2022-05-12 09:00","2022-05-12 18:00","2022-05-12 09:00","2022-05-12 18:00","연속"]
[415,"대구","포항","건천천북#1 T/L","건천-천북#1T/L A상 송전선로 불량개소 보수","건천-천북#1T/L A상 송전선로 불량개소 보수","2022-05-12 09:00","2022-05-12 18:00","2022-05-12 09:00","2022-05-12 18:00","연속"]
[416,"경북","구미","상주영동 T/L","154kV 화동분기T/L 건설공사","□ 목 적 : 신설 154kV 화동S/S 전력공급 □ 위 치 : 경북 상주시 화동면 이소리, 선교리 일원 □ 규 모 : 154kV ASCC 430㎟×S×4C×0.965㎞, 철탑 3기 □ 준공목표 : 2022년 9월","2022-05-17 07:00","2022-05-19 14:00","2022-05-17 07:00","2022-05-19 14:00","연속"]
[417,"경북","구미","상주보은 T/L","154kV 화동분기T/L 건설공사","□ 목 적 : 신설 154kV 화동S/S 전력공급 □ 위 치 : 경북 상주시 화동면 이소리, 선교리 일원 □ 규 모 : 154kV ASCC 430㎟×S×4C×0.965㎞, 철탑 3기 □ 준공목표 : 2022년 9월","2022-05-19 14:00","2022-05-20 18:00","2022-05-19 14:00","2022-05-20 18:00","연속"]
[418,"경북","영주","영주봉화#2 T/L","22-23년 영주전력지사 변전협력회사 총액공사","154kV 영주-봉화#2T/L - 봉화S/S CB 보통점검 - 영주SA LA 대체","2022-05-04 09:00","2022-05-04 18:00","취소","취소","연속"]
[419,"경북","영주","영주봉화#1 T/L","22-23년 영주전력지사 변전협력회사 총액공사","154kV 영주-봉화#1T/L - 봉화S/S CB 보통점검 - 영주SA LA 대체","2022-05-03 09:00","2022-05-03 18:00","취소","취소","연속"]
[420,"경북","직할","안동동안동#1 T/L","22~23년 경북본부 직할 변전정비회사 총액공사","안동-피뢰기 인하선 변경 동안동-GIS 조작시험","2022-05-19 09:00","2022-05-19 14:00","2022-05-19 09:00","2022-05-19 14:00","연속"]
[421,"경북","직할","안동안동HP T/L","22~23년 경북본부 직할 변전정비회사 총액공사","피뢰기 인하선 변경","2022-05-19 09:00","2022-05-19 18:00","2022-05-19 09:00","2022-05-19 18:00","연속"]
[422,"경북","직할","울진현종산풍력 T/L","154kV 울진-현종산풍력T/L 추락방지시설 설치공사","154kV 울진-현종산풍력T/L 추락방지시설 설치공사","2022-05-16 07:00","2022-05-26 18:00","2022-05-16 07:00","2022-05-26 18:00","매일"]
[423,"경북","직할","봉화울진 T/L","154kV 울진-현종산풍력T/L 추락방지시설 설치공사","154kV 봉화-울진T/L 추락방지시설 설치공사","2022-05-27 07:00","2022-06-09 18:00","2022-05-27 07:00","2022-06-09 18:00","매일"]
[424,"경북","직할","현종산풍력평해#2 T/L","154kV 신영주-안동 등 4개T/L 피뢰기 설치공사","154kV 현종산풍력-평해T/L No.1~87 피뢰기 설치","2022-05-25 07:00","2022-06-08 18:00","2022-05-25 07:00","2022-06-08 18:00","매일"]
[425,"경북","직할","현종산풍력평해#1 T/L","154kV 신영주-안동 등 4개T/L 피뢰기 설치공사","154kV 현종산-평해 T/L No.1~87 피뢰기 설치","2022-05-02 07:00","2022-05-03 18:00","2022-05-02 07:00","2022-05-03 18:00","매일"]
[426,"경북","직할","풍산안동CC#2 T/L","풍산S/S #3M.Tr 증설 및 모선보강공사","#3M.Tr 1차 6333 GIS #1 DS부 무부하가압","2022-05-18 09:00","2022-05-18 13:00","2022-05-18 09:00","2022-05-18 13:00","연속"]
[427,"경북","직할","풍산안동CC#2 T/L","풍산S/S #3M.Tr 증설 및 모선보강공사","#3M.Tr 1차 6333 GIS #2DS, CB 무부하가압","2022-05-20 11:00","2022-05-21 13:00","2022-05-20 11:00","2022-05-21 13:00","연속"]
[428,"경북","직할","풍산안동CC#1 T/L","풍산S/S #3M.Tr 증설 및 모선보강공사","(1) 05.22(일) 09:00~13:00 : #2BUS 무부하가압 (2) 05.22(일) 13:00~26(목) : #1BUS 교체 및 #61-#66 BUS SEC 설치 (3) 05.26(목)~27(금) : #61-#66 BUS SEC 무부하가압","2022-05-22 09:00","2022-05-27 18:00","2022-05-22 09:00","2022-05-27 18:00","연속"]
[429,"경북","직할","봉화현종산풍력 T/L","154kV 울진-현종산풍력T/L 추락방지시설 설치공사","154kV 봉화-현종산풍력T/L 추락방지시설 설치공사","2022-05-02 07:00","2022-05-13 18:00","2022-05-02 07:00","2022-05-13 18:00","매일"]
[430,"부산울산","동부산","구서노포#2 T/L","154kV 언양-산막 등 2개T/L 자기애관 교체공사(비표준)","154kV 구서-노포T/L 비표준 자기애관 교체공사 자기애관1,200㎟을 폴리머애관 1,200㎟으로 변경","2022-05-23 08:00","2022-05-27 18:00","2022-05-23 08:00","2022-05-27 18:00","연속"]
[431,"부산울산","동부산","구서노포#1 T/L","154kV 언양-산막 등 2개T/L 자기애관 교체공사(비표준)","154kV 구서-노포T/L 비표준 자기애관 교체공사 자기애관1,200㎟을 폴리머애관 1,200㎟으로 변경","2022-05-16 08:00","2022-05-20 18:00","2022-05-16 08:00","2022-05-20 18:00","연속"]
[432,"부산울산","동부산","명례고리NP T/L","명례S/S 154GIS 제어IED 펌웨어 업데이트","명례S/S 154GIS 제어IED 펌웨어 업데이트(명례-고리NP T/L)","2022-05-03 11:30","2022-05-03 14:00","취소","취소","연속"]
[433,"부산울산","동부산","신울산명례#2 T/L","명례S/S 154GIS 제어IED 펌웨어 업데이트","명례S/S 154GIS 제어IED 펌웨어 업데이트(신울산-명례#2T/L)","2022-05-02 14:00","2022-05-02 16:00","2022-05-02 14:00","2022-05-02 16:00","연속"]
[434,"부산울산","동부산","명례장안 T/L","명례S/S 154GIS 제어IED 펌웨어 업데이트","명례S/S 154GIS 제어IED 펌웨어 업데이트(명례-장안 T/L)","2022-05-03 14:00","2022-05-03 16:00","2022-05-03 14:00","2022-05-03 16:00","연속"]
[435,"부산울산","동부산","수영정보#2 T/L","수영S/S 657GIS 보통점검","수영S/S 657GIS 보통점검 병행)정보S/S 637GIS 보통점검","2022-05-07 09:30","2022-05-07 17:00","2022-05-07 09:30","2022-05-07 17:00","연속"]
[436,"부산울산","동부산","수영우동 T/L","우동S/S 617GIS 차단기 동작시험","우동S/S 617GIS 차단기 동작시험","2022-05-06 09:30","2022-05-06 14:00","2022-05-06 09:30","2022-05-06 14:00","연속"]
[437,"부산울산","북부산","북부산구포#2 T/L","영인제 송전선로 보호반 성능개선","구포S/S 154kV 북부산-구포#2T/L 보호반(영인제) 성능개선","2022-05-17 10:00","2022-05-17 18:00","2022-05-17 10:00","2022-05-17 18:00","연속"]
[438,"부산울산","북부산","북부산구포#1 T/L","영인제 송전선로 보호반 성능개선","구포S/S 154kV 북부산-구포#1T/L 보호반(영인제) 성능개선","2022-05-16 09:00","2022-05-16 18:00","2022-05-16 09:00","2022-05-16 18:00","연속"]
[439,"부산울산","북부산","북부산구포#3 T/L","22-23년 북부산전력지사 변전 총액공사","구포S/S 154kV 북부산-구포#3T/L GIS 조작시험","2022-05-26 10:00","2022-05-26 18:00","2022-05-26 10:00","2022-05-26 18:00","연속"]
[440,"부산울산","북부산","서창산막#2 T/L","154kV 서창-산막 등 3개T/L 지장철탑 이설공사","154kV 서창-산막#1,2T/L, 언양-산막#2T/L 본선로 이설(6회선 철탑구간) 작업내용 1) 154kV 서창-산막#1,2T/L 기설 80호~신설 82호 가선 2) 기설 및 신설구간 교차개소 해소 후 154kV 언양-산막#2T/L 기설 66호~서창-산막T/L 신설 83호까지 가선 3) 기설 84~85호 철거 및 신설 84-1~85호 가선","2022-05-07 07:30","2022-05-08 18:00","2022-05-07 07:30","2022-05-08 18:00","연속"]
[441,"부산울산","북부산","서창산막#2 T/L","22-23년 북부산전력지사 변전 총액공사","산막S/S 154kV 서창-산막#2T/L 송전선로 보호반 대체","2022-05-21 08:00","2022-05-22 18:00","2022-05-21 08:00","2022-05-22 18:00","연속"]
[442,"부산울산","북부산","양산산막#2 T/L","154kV 서창-산막 등 3개T/L 지장철탑 이설공사","154kV 양산-산막#1,2T/L, 언양-산막#1T/L 본선로 이설(6회선 철탑구간) 작업내용 1) 154kV 양산-산막#1,2T/L 기설 16호~신설 18호 가선 2) 가이설구간 철거 및 154kV 언양-산막#1T/L 기설 66호~양산-산막T/L 신설 19호까지 가선 3) 기설 양산-산막T/L 20~21호 철거 및 신설 20-1~21호 가선","2022-05-14 07:30","2022-05-15 18:00","2022-05-14 07:30","2022-05-15 18:00","연속"]
[443,"부산울산","북부산","언양산막#1 T/L","154kV 서창-산막 등 3개T/L 지장철탑 이설공사","154kV 양산-산막#1,2T/L, 언양-산막#1T/L 본선로 이설(6회선 철탑구간) 작업내용 1) 154kV 양산-산막#1,2T/L 기설 16호~신설 18호 가선 2) 가이설구간 철거 및 154kV 언양-산막#1T/L 기설 66호~양산-산막T/L 신설 19호까지 가선 3) 기설 양산-산막T/L 20~21호 철거 및 신설 20-1~21호 가선","2022-05-14 07:30","2022-05-15 18:00","2022-05-14 07:30","2022-05-15 18:00","연속"]
[444,"부산울산","북부산","양산산막#1 T/L","154kV 서창-산막 등 3개T/L 지장철탑 이설공사","154kV 양산-산막#1,2T/L, 언양-산막#1T/L 본선로 이설(6회선 철탑구간) 작업내용 1) 154kV 양산-산막#1,2T/L 기설 16호~신설 18호 가선 2) 가이설구간 철거 및 154kV 언양-산막#1T/L 기설 66호~양산-산막T/L 신설 19호까지 가선 3) 기설 양산-산막T/L 20~21호 철거 및 신설 20-1~21호 가선","2022-05-14 07:30","2022-05-15 18:00","2022-05-14 07:30","2022-05-15 18:00","연속"]
[445,"부산울산","북부산","언양산막#1 T/L","154kV 서창-산막 등 3개T/L 지장철탑 이설공사","154kV 서창-산막#1,2T/L, 언양-산막#2T/L 본선로 이설(6회선 철탑구간) 작업내용 1) 154kV 서창-산막#1,2T/L 기설 80호~신설 82호 가선 2) 기설 및 신설구간 교차개소 해소 후 154kV 언양-산막#2T/L 기설 66호~서창-산막T/L 신설 83호까지 가선 3) 기설 84~85호 철거 및 신설 84-1~85호 가선","2022-05-07 07:30","2022-05-08 18:00","2022-05-07 07:30","2022-05-08 18:00","연속"]
[446,"부산울산","북부산","언양산막#2 T/L","154kV 서창-산막 등 3개T/L 지장철탑 이설공사","154kV 서창-산막#1,2T/L, 언양-산막#2T/L 본선로 이설(6회선 철탑구간) 작업내용 1) 154kV 서창-산막#1,2T/L 기설 80호~신설 82호 가선 2) 기설 및 신설구간 교차개소 해소 후 154kV 언양-산막#2T/L 기설 66호~서창-산막T/L 신설 83호까지 가선 3) 기설 84~85호 철거 및 신설 84-1~85호 가선","2022-05-07 07:30","2022-05-08 18:00","2022-05-07 07:30","2022-05-08 18:00","연속"]
[447,"부산울산","북부산","서창산막#1 T/L","154kV 서창-산막 등 3개T/L 지장철탑 이설공사","154kV 서창-산막#1,2T/L, 언양-산막#2T/L 본선로 이설(6회선 철탑구간) 작업내용 1) 154kV 서창-산막#1,2T/L 기설 80호~신설 82호 가선 2) 기설 및 신설구간 교차개소 해소 후 154kV 언양-산막#2T/L 기설 66호~서창-산막T/L 신설 83호까지 가선 3) 기설 84~85호 철거 및 신설 84-1~85호 가선","2022-05-07 07:30","2022-05-08 18:00","2022-05-07 07:30","2022-05-08 18:00","연속"]
[448,"부산울산","북부산","언양산막#1 T/L","154kV 서창-산막 등 3개T/L 지장철탑 이설공사","154kV 언양-산막#1T/L 66~67호 구간 가선로 구성 작업내용 : 기설 언양산막 66호-신설 서창산막 82호-기설 언양산막 67호 가이설 선로 가선 (언양-산막T/L 67호의 모선로 : 서창-산막T/L 81호)","2022-05-01 07:30","2022-05-01 18:00","2022-05-01 07:30","2022-05-01 18:00","연속"]
[449,"부산울산","북부산","삼랑진P/P CB 6100","22-23년 북부산전력지사 변전 총액공사","삼랑진S/Y 154kV BUS TIE GIS 하자점검","2022-05-23 10:00","2022-05-23 18:00","2022-05-23 10:00","2022-05-23 18:00","연속"]
[450,"부산울산","북부산","양산산막#1 T/L","154kV 서창-산막 등 3개T/L 지장철탑 이설공사","154kV 양산-산막#1,2T/L 4회선 구간 가선로 구성 작업내용 : 가철탑 1기 조립 및 전력선, OPGW 가선로 구성 (모선로 : 서창-산막T/L 80~81호)","2022-05-01 07:30","2022-05-01 18:00","2022-05-01 07:30","2022-05-01 18:00","연속"]
[451,"부산울산","북부산","양산산막#2 T/L","154kV 서창-산막 등 3개T/L 지장철탑 이설공사","154kV 양산-산막#1,2T/L 4회선 구간 가선로 구성 작업내용 : 가철탑 1기 조립 및 전력선, OPGW 가선로 구성 (모선로 : 서창-산막T/L 80~81호)","2022-05-01 07:30","2022-05-01 18:00","2022-05-01 07:30","2022-05-01 18:00","연속"]
[452,"부산울산","북부산","엄궁학장#1 T/L","사상-하단간 도시철도공사 관련 관로 및 맨홀 매달기 사전작업","M/H#7, 8, 9 접속함 진동방지 및 활락방지 작업(부산교통공사)","2022-05-23 09:00","2022-05-28 18:00","2022-05-23 09:00","2022-05-28 18:00","연속"]
[453,"부산울산","북부산","엄궁학장#2 T/L","사상-하단간 도시철도공사 관련 관로 및 맨홀 매달기 사전작업","M/H#7, 8, 9 접속함 진동방지 및 활락방지 작업(부산교통공사)","2022-05-30 09:00","2022-06-04 18:00","2022-05-30 09:00","2022-06-04 18:00","연속"]
[454,"부산울산","북부산","호포물금 T/L","2022 북부산전력지사 154kV GIS 정밀점검","호포S/S 6333 GIS 정밀점검 - 시험가압 1h (시험가압선로 : 호포-물금#T/L)","2022-05-25 17:00","2022-05-25 18:00","2022-05-25 17:00","2022-05-25 18:00","연속"]
[455,"부산울산","서부산","서부산S/S CB 6100","서부산S/S 154kV #60-#65 BUS TIE GIS 동작시험","서부산S/S 154kV #60-#65 BUS TIE GIS 동작시험","2022-05-09 09:00","2022-05-09 18:00","2022-05-09 09:00","2022-05-09 18:00","연속"]
[456,"부산울산","서부산","서부산S/S CB 6200","서부산S/S 154kV #61-#66 BUS TIE GIS 동작시험","서부산S/S 154kV #61-#66 BUS TIE GIS 동작시험","2022-05-10 09:00","2022-05-10 18:00","2022-05-10 09:00","2022-05-10 18:00","연속"]
[457,"부산울산","울산","방어진영남TP#1 T/L","154kV 방어진-영남TP T/L 접속설비보강공사","폴리머지지애자 4기 설치","2022-05-09 07:00","2022-05-09 18:00","취소","취소","연속"]
[458,"부산울산","울산","방어진영남TP#2 T/L","154kV 방어진-영남TP T/L 접속설비보강공사","NO.1~5 : #2T/L 전선교체 5가닥","2022-05-10 07:00","2022-05-20 18:00","2022-05-18 07:00","2022-05-28 18:00","연속"]
[459,"부산울산","울산","성암울산TP#2 T/L","22~23년 변전협력회사 총액공사","GIS 하자점검","2022-05-04 09:00","2022-05-04 18:00","2022-05-04 09:00","2022-05-04 18:00","연속"]
[460,"부산울산","울산","성암울산TP#1 T/L","22~23년 변전협력회사 총액공사","GIS 하자점검","2022-05-09 09:00","2022-05-09 18:00","2022-05-09 09:00","2022-05-09 18:00","연속"]
[461,"부산울산","울산","남울산신온산#2 T/L","22년 상반기 154kV GIS 정밀점검 공사","1. GIS 정밀점검 2. 남울산S/S 6972 GIS 하자점검(병행)","2022-05-16 09:00","2022-05-17 18:00","2022-05-16 09:00","2022-05-17 18:00","연속"]
[462,"부산울산","울산","언양산막#1 T/L","154kV 언양-산막 등 2개T/L 자기애관 교체공사(비표준)","154kV 언양-산막T/L 비표준 자기애관 교체공사 자기애관2,000㎟을 폴리머애관 2,000㎟으로 변경","2022-05-30 09:00","2022-06-03 18:00","2022-05-30 09:00","2022-06-03 18:00","연속"]
[463,"부산울산","울산","울산T/P CB 6100","22년 상반기 154kV GIS 정밀점검 공사","GIS 정밀점검, 전자변 교체","2022-05-02 09:00","2022-05-03 18:00","2022-05-02 09:00","2022-05-03 18:00","연속"]
[464,"부산울산","울산","울산T/P #60 BUS","22년 상반기 154kV GIS 정밀점검 공사","GIS 정밀점검관련 사전 모선통합 및 시험가압(1Hr)","2022-05-02 09:00","2022-05-03 18:00","2022-05-02 09:00","2022-05-03 18:00","연속"]
[465,"부산울산","울산","성암울산TP#1 T/L","22년 상반기 154kV GIS 정밀점검 공사","#60-65BUS-TIE GIS 정밀점검 관련 시험가압(1Hr)","2022-05-03 17:00","2022-05-03 18:00","2022-05-03 17:00","2022-05-03 18:00","연속"]
[466,"부산울산","울산","울산T/P #66 BUS","22년 상반기 154kV GIS 정밀점검 공사","#61-66BUS-TIE GIS 정밀점검고나련 사전 모선절체 및 시험가압(1Hr)","2022-05-09 09:00","2022-05-10 18:00","2022-05-09 09:00","2022-05-10 18:00","연속"]
[467,"부산울산","울산","울산T/P CB 6200","22년 상반기 154kV GIS 정밀점검 공사","GIS 정밀점검, 전자변 교체","2022-05-09 09:00","2022-05-10 18:00","2022-05-09 09:00","2022-05-10 18:00","연속"]
[468,"부산울산","울산","용연울산TP#2 T/L","22년 상반기 154kV GIS 정밀점검 공사","#61-66BUS-TIE GIS 정밀점검 관련 시험가압(1Hr)","2022-05-10 17:00","2022-05-10 18:00","2022-05-10 17:00","2022-05-10 18:00","연속"]
[469,"부산울산","울산","직동반천#2 T/L","22~23년 동부산전력지사 가공송전협력회사 총액공사","-압축인류클램프 정비(직동S/S)","2022-05-03 13:00","2022-05-03 18:00","2022-05-03 13:00","2022-05-03 18:00","연속"]
[470,"부산울산","울산","울주직동#1 T/L","22~23년 변전협력회사 총액공사","- GIS 차단기 동작시험","2022-05-27 09:00","2022-05-27 18:00","2022-05-30 09:00","2022-05-30 14:00","연속"]
[471,"부산울산","울산","울주직동#2 T/L","22~23년 변전협력회사 총액공사","- GIS 차단기 동작시험","2022-05-30 09:00","2022-05-30 18:00","2022-05-30 14:00","2022-05-30 18:00","연속"]
[472,"부산울산","울산","직동반천#2 T/L","22~23년 변전협력회사 총액공사","- GIS 차단기 동작시험","2022-05-31 09:00","2022-05-31 18:00","취소","취소","연속"]
[473,"부산울산","울산","직동반천#1 T/L","22~23년 동부산전력지사 가공송전협력회사 총액공사","-압축인류클램프 정비(직동S/S)","2022-05-03 07:00","2022-05-03 13:00","2022-05-03 07:00","2022-05-03 13:00","연속"]
[474,"부산울산","울산","효문방어진 T/L","22~23년 변전협력회사 총액공사","- GIS 차단기 동작시험","2022-05-13 09:00","2022-05-13 18:00","2022-05-13 09:00","2022-05-13 18:00","연속"]
[475,"부산울산","직할","서면S/S CB 6100","22-23년 직할 변전협력회사 총액공사","서면S/S 154kV BUS-TIE GIS(6100) 보통점검","2022-05-13 09:00","2022-05-13 18:00","2022-05-13 09:00","2022-05-13 18:00","연속"]
[476,"부산울산","직할","수정범일#2 T/L","2022년 직할 170kV GIS 정밀점검","수정S/S 154kV BUS-TIE GIS(6100) 정밀점검, 무부하 시험가압","2022-05-24 14:00","2022-05-24 18:00","2022-05-24 14:00","2022-05-24 18:00","연속"]
[477,"부산울산","직할","수정S/S #2 BUS","2022년 직할 170kV GIS 정밀점검","수정S/S 154kV BUS-TIE GIS(6100) 정밀점검, 무부하 시험가압","2022-05-23 09:00","2022-05-24 18:00","2022-05-23 09:00","2022-05-24 18:00","연속"]
[478,"부산울산","직할","부산수정#2 T/L","2022년 직할 170kV GIS 정밀점검","수정S/S 부산-수정#2T/L GIS(667) 정밀점검 부산S/S 부산-수정#2T/L GIS(647) 보통점검","2022-05-18 09:00","2022-05-19 18:00","2022-05-18 09:00","2022-05-19 18:00","연속"]
[479,"부산울산","직할","부산수정#1 T/L","2022년 직할 170kV GIS 정밀점검","수정S/S 부산-수정#1T/L GIS(657) 정밀점검 부산S/S 부산-수정#1T/L GIS(637) 보통점검","2022-05-16 09:00","2022-05-17 18:00","2022-05-16 09:00","2022-05-17 18:00","연속"]
[480,"부산울산","직할","수정범일#2 T/L","2022년 직할 170kV GIS 정밀점검","수정S/S 수정-범일#2T/L GIS(627) 정밀점검, 보호반 IED 성능개선 범일S/S 수정-범일#2T/L GIS(627) 보통점검, 보호반 IED 성능개선","2022-05-11 09:00","2022-05-12 18:00","2022-05-11 09:00","2022-05-12 18:00","연속"]
[481,"부산울산","직할","수정범일#1 T/L","2022년 직할 170kV GIS 정밀점검","수정S/S 수정-범일#1T/L GIS(617) 정밀점검, 보호반 IED 성능개선 범일S/S 수정-범일#1T/L GIS(617) 보통점검, 보호반 IED 성능개선","2022-05-09 09:00","2022-05-10 18:00","2022-05-09 09:00","2022-05-10 18:00","연속"]
[482,"부산울산","직할","수정S/S CB 6100","2022년 직할 170kV GIS 정밀점검","수정S/S 154kV BUS-TIE GIS(6100) 정밀점검","2022-05-23 09:00","2022-05-24 18:00","2022-05-23 09:00","2022-05-24 18:00","연속"]
[483,"경남","직할","신김해지사#2 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-05-25 13:30","2022-05-27 18:00","2022-05-25 13:30","2022-05-27 18:00","연속"]
[484,"경남","직할","신김해주촌#1 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-05-09 08:00","2022-05-11 13:30","2022-05-09 08:00","2022-05-11 13:30","연속"]
[485,"경남","직할","신김해주촌#2 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-05-11 13:30","2022-05-13 18:00","2022-05-11 13:30","2022-05-13 18:00","연속"]
[486,"경남","직할","신김해지사#1 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-05-23 08:00","2022-05-25 13:30","2022-05-23 08:00","2022-05-25 13:30","연속"]
[487,"경남","직할","신월동읍#1 T/L","2022년 경남 직할 154kV GIS 정밀점검 공사","2022년 경남 직할 154kV GIS 정밀점검 공사 신월-동읍#1T/L","2022-05-03 08:00","2022-05-04 18:00","2022-05-03 08:00","2022-05-04 18:00","연속"]
[488,"경남","직할","신월동읍#2 T/L","신월S/S 신월-동읍#2T/L 조작시험","신월S/S 신월-동읍#2T/L 조작시험","2022-05-09 09:30","2022-05-09 18:00","2022-05-09 09:30","2022-05-09 18:00","연속"]
[489,"경남","직할","신월삼정#2 T/L","2022년 경남 직할 154kV GIS 정밀점검 공사","2022년 경남 직할 154kV GIS 정밀점검 공사 신월-삼정#2T/L(시험가압 선로)","2022-05-10 13:00","2022-05-10 18:00","2022-05-10 13:00","2022-05-10 18:00","연속"]
[490,"경남","진주","중리가야#1 T/L","가야S/S #3M.Tr 1차 GIS 정밀점검 시험가압선로","가야S/S #3M.Tr 1차 GIS 정밀점검 시험가압선로","2022-05-18 14:00","2022-05-18 18:00","2022-05-18 14:00","2022-05-18 18:00","연속"]
[491,"경남","진주","가야사봉#1 T/L","가야S/S 군북전철#1T/L 정밀점검 시험가압선로","가야S/S 군북전철#1T/L 정밀점검 시험가압선로","2022-05-31 14:00","2022-05-31 18:00","2022-05-31 14:00","2022-05-31 18:00","연속"]
[492,"경남","진주","사봉개양#2 T/L","추락방지시설 설치공사","□ 휴전설비 : 사봉-개양#2T/L, 진주-개양#1T/L, 가야-사봉#1T/L □ 설치대상 ○ 154kV 사봉-개양T/L No.1~56호 ☞ No.2~7 작업시 가야-사봉T/L 안전작업거리확보 휴전 필요 ☞ No52.~55 작업시 진주-개양T/L 안전작업거리확보 휴전 필요 ○ 154kV 진주-개양T/L No.1~15호 ☞ No.2~5 작업시 사봉-개양T/L 안전작업거리확보 휴전 필요","2022-05-19 07:30","2022-05-27 18:00","2022-05-19 07:30","2022-05-27 18:00","연속"]
[493,"경남","진주","사봉개양#1 T/L","추락방지시설 설치공사","□ 휴전설비 : 사봉-개양#1T/L, 진주-개양#2T/L, 가야-사봉#2T/L □ 설치대상 ○ 154kV 사봉-개양T/L No.1~56호 ☞ No.2~7 작업시 가야-사봉T/L 안전작업거리확보 휴전 필요 ☞ No52.~55 작업시 진주-개양T/L 안전작업거리확보 휴전 필요 ○ 154kV 진주-개양T/L No.1~15호 ☞ No.2~5 작업시 사봉-개양T/L 안전작업거리확보 휴전 필요","2022-05-10 07:30","2022-05-18 18:00","2022-05-10 07:30","2022-05-18 18:00","연속"]
[494,"경남","진주","가야사봉#1 T/L","[안전작업거리확보 휴전]추락방지시설 설치공사","□ 휴전설비 : 사봉-개양#2T/L, 진주-개양#1T/L, 가야-사봉#1T/L □ 설치대상 ○ 154kV 사봉-개양T/L No.1~56호 ☞ No.2~7 작업시 가야-사봉T/L 안전작업거리확보 휴전 필요 ☞ No52.~55 작업시 진주-개양T/L 안전작업거리확보 휴전 필요 ○ 154kV 진주-개양T/L No.1~15호 ☞ No.2~5 작업시 사봉-개양T/L 안전작업거리확보 휴전 필요","2022-05-19 07:30","2022-05-20 18:00","2022-05-19 07:30","2022-05-20 18:00","연속"]
[495,"경남","진주","가야사봉#2 T/L","[안전작업거리확보 휴전]추락방지시설 설치공사","□ 휴전설비 : 사봉-개양#1T/L, 진주-개양#2T/L, 가야-사봉#2T/L □ 설치대상 ○ 154kV 사봉-개양T/L No.1~56호 ☞ No.2~7 작업시 가야-사봉T/L 안전작업거리확보 휴전 필요 ☞ No52.~55 작업시 진주-개양T/L 안전작업거리확보 휴전 필요 ○ 154kV 진주-개양T/L No.1~15호 ☞ No.2~5 작업시 사봉-개양T/L 안전작업거리확보 휴전 필요","2022-05-10 07:30","2022-05-11 18:00","2022-05-10 07:30","2022-05-11 18:00","연속"]
[496,"경남","진주","의령동진주#2 T/L","의령S/S 의령-동진주#2T/L GIS 조작시험","[병행] LA 하자, PT 보통점검","2022-05-03 10:00","2022-05-03 18:00","2022-05-03 10:00","2022-05-03 18:00","연속"]
[497,"경남","진주","의령함양 T/L","의령S/S 의령-함양T/L GIS 조작시험","[병행] PT 보통점검, LA(ABC) 대체","2022-05-07 09:00","2022-05-07 18:00","2022-05-07 09:00","2022-05-07 18:00","연속"]
[498,"경남","진주","의령동진주#1 T/L","의령S/S 의령-동진주#1T/L GIS 조작시험","[병행] PT 보통점검, LA 하자점검","2022-05-02 10:00","2022-05-02 18:00","2022-05-02 10:00","2022-05-02 18:00","연속"]
[499,"경남","진주","진주개양#1 T/L","추락방지시설 설치공사","□ 휴전설비 : 사봉-개양#2T/L, 진주-개양#1T/L, 가야-사봉#1T/L □ 설치대상 ○ 154kV 사봉-개양T/L No.1~56호 ☞ No.2~7 작업시 가야-사봉T/L 안전작업거리확보 휴전 필요 ☞ No52.~55 작업시 진주-개양T/L 안전작업거리확보 휴전 필요 ○ 154kV 진주-개양T/L No.1~15호 ☞ No.2~5 작업시 사봉-개양T/L 안전작업거리확보 휴전 필요","2022-05-23 07:30","2022-05-27 18:00","2022-05-23 07:30","2022-05-27 18:00","연속"]
[500,"경남","진주","진주개양#2 T/L","추락방지시설 설치공사","□ 휴전설비 : 사봉-개양#1T/L, 진주-개양#2T/L, 가야-사봉#2T/L □ 설치대상 ○ 154kV 사봉-개양T/L No.1~56호 ☞ No.2~7 작업시 가야-사봉T/L 안전작업거리확보 휴전 필요 ☞ No52.~55 작업시 진주-개양T/L 안전작업거리확보 휴전 필요 ○ 154kV 진주-개양T/L No.1~15호 ☞ No.2~5 작업시 사봉-개양T/L 안전작업거리확보 휴전 필요","2022-05-16 07:30","2022-05-20 18:00","2022-05-16 07:30","2022-05-20 18:00","연속"]
[501,"경남","진주","광양하동#1 T/L","하동S/S 154kV 하동전철T/L 신규수용공사(안전이격거리 확보)","- 170kV GIS X 2CCT 설치(지중) - 154kV 송전선로보호배전반 X 2면 설치 - 기타부대공사 X 1식","2022-05-23 09:30","2022-05-23 17:30","취소","취소","연속"]
[502,"경남","진주","광양하동#2 T/L","하동S/S 154kV 하동전철T/L 신규수용공사(안전이격거리 확보)","- 170kV GIS X 2CCT 설치(지중) - 154kV 송전선로보호배전반 X 2면 설치 - 기타부대공사 X 1식","2022-05-16 09:30","2022-05-17 17:30","취소","취소","연속"]
[503,"경남","통영","고성통영 T/L","고성S/S 154kV 고성-통영T/L 보통점검 및 LA 보통점검","고성S/S 154kV 고성-통영T/L 보통점검 및 LA 보통점검","2022-05-07 09:30","2022-05-07 18:00","2022-05-07 09:30","2022-05-07 18:00","연속"]
[504,"경남","통영","신고성거제#1 T/L","154kV 진동-안정T/L 추락방지시설 설치공사","154kV 진동-안정T/L 추락방지시설 설치공사(병가구간)","2022-05-14 07:00","2022-05-15 18:00","2022-05-14 07:00","2022-05-15 18:00","매일"]
[505,"경남","통영","신고성거제#1 T/L","154kV 진동-안정T/L 추락방지시설 설치공사","154kV 진동-안정T/L 추락방지시설 설치공사(병가구간)","2022-05-07 07:00","2022-05-08 18:00","2022-05-07 07:00","2022-05-08 18:00","매일"]
[506,"경남","통영","신고성거제#2 T/L","154kV 진동-안정T/L 추락방지시설 설치공사","154kV 진동-안정T/L 추락방지시설 설치공사(병가구간)","2022-05-21 07:00","2022-05-22 18:00","2022-05-21 07:00","2022-05-22 18:00","매일"]
[507,"경남","통영","신고성거제#2 T/L","154kV 진동-안정T/L 추락방지시설 설치공사","154kV 진동-안정T/L 추락방지시설 설치공사(병가구간)","2022-05-28 07:00","2022-05-29 18:00","2022-05-28 07:00","2022-05-29 18:00","매일"]
[508,"경남","통영","진동안정#2 T/L","154kV 진동-안정T/L 추락방지시설 설치공사","154kV 진동-안정T/L 추락방지시설 설치공사","2022-05-21 07:00","2022-05-29 18:00","2022-05-21 07:00","2022-05-29 18:00","매일"]
[509,"경남","함안","김해어방#1 T/L","김해S/S 154kV 김해-어방#1T/L GIS 조작시험 외","김해S/S 154kV 김해-어방#1T/L GIS 조작시험 및 LA 보통, 어방S/S 154kV 김해-어방#1T/L GIS 조작시험","2022-05-19 09:30","2022-05-19 17:30","2022-05-19 09:30","2022-05-19 17:30","연속"]
[510,"경남","함안","김해어방#2 T/L","김해S/S 154kV 김해-어방#2T/L GIS 조작시험 외","김해S/S 154kV 김해-어방#2T/L GIS 조작시험 및 LA 보통, 어방S/S 154kV 김해-어방#2T/L GIS 조작시험 외","2022-05-30 09:30","2022-05-30 17:30","2022-05-23 09:30","2022-05-23 17:30","연속"]
[511,"경남","함안","매리김해#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","154kV 호포-매리T/L 24호 본철탑 조립시 안전이격 확보","2022-05-19 07:00","2022-05-22 18:00","2022-05-19 07:00","2022-05-22 18:00","매일"]
[512,"경남","함안","호포매리#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","154kV 호포-매리T/L 24호 본철탑 조립시 안전이격 확보","2022-05-19 07:00","2022-05-22 18:00","2022-05-19 07:00","2022-05-22 18:00","매일"]
[513,"경남","함안","매리김해#2 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 신설철탑 전력선 설치관련 안전이격","2022-05-28 07:00","2022-05-28 15:00","2022-05-29 07:00","2022-05-29 15:00","연속"]
[514,"경남","함안","호포매리#1 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : 전력선 및 가공지선 설치","2022-05-28 07:00","2022-05-31 18:00","2022-05-29 07:00","2022-06-02 18:00","연속"]
[515,"경남","함안","매리김해#1 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : 전력선 및 가공지선 설치","2022-05-28 07:00","2022-05-31 18:00","2022-05-29 07:00","2022-06-02 18:00","연속"]
[516,"경남","함안","초동밀양#1 T/L","초동-밀양#2T/L 피뢰기 및 추락방지장치 설치공사 관련 안전거리확보","154kV 초동-밀양#2T/L 피뢰기 및 추락방지장치 설치 관련 안전거리확보 (16~39호)","2022-05-11 08:00","2022-05-13 18:00","2022-05-11 08:00","2022-05-13 18:00","매일"]
[517,"경남","함안","초동밀양#2 T/L","154kV 초동-밀양#2T/L 피뢰기 및 추락방지장치 설치공사","154kV 초동-밀양#2T/L 추락방지장치 설치공사 설치대상 : 41기(1~39호)","2022-05-09 08:00","2022-05-13 18:00","2022-05-09 08:00","2022-05-13 18:00","연속"]
[518,"경남","함안","한림정삼계#2 T/L","삼계S/S 154kV 한림정-삼계#2T/L GIS 보통점검 외","삼계S/S 154kV 한림정-삼계#2T/L GIS 보통점검, LA 보통점검","2022-05-21 09:30","2022-05-21 17:30","2022-05-21 09:30","2022-05-21 17:30","연속"]
[519,"경남","함안","주촌삼계#1 T/L","삼계S/S 154kV 주촌-삼계#1T/L GIS(시험가압)","삼계S/S #1Sh.C 정밀점검 시험가압용","2022-05-03 17:00","2022-05-03 18:00","2022-05-03 17:00","2022-05-03 18:00","연속"]
[520,"경남","함안","삼계어방#1 T/L","삼계S/S 154kV 삼계-어방#1T/L GIS 보통점검 외","삼계S/S 154kV 삼계-어방#1T/L GIS 보통점검, 어방S/S 154kV 삼계-어방#1T/L GIS 조작시험","2022-05-07 09:30","2022-05-07 17:30","2022-05-07 09:30","2022-05-07 17:30","연속"]
[521,"경남","함안","주촌삼계#2 T/L","삼계S/S 154kV 주촌-삼계#2T/L GIS(시험가압)","삼계S/S #2Sh.C 정밀점검 시험가압용","2022-05-10 17:00","2022-05-10 18:00","2022-05-10 17:00","2022-05-10 18:00","연속"]
[522,"경남","함안","삼계어방#2 T/L","삼계S/S 154kV 삼계-어방#2T/L GIS 보통점검 외","삼계S/S 154kV 삼계-어방#2T/L GIS 보통점검, 어방S/S 154kV 삼계-어방#2T/L GIS 조작시험","2022-05-14 09:30","2022-05-14 17:30","2022-05-14 09:30","2022-05-14 17:30","연속"]
[523,"경남","함안","창녕초동#1 T/L","초동-밀양#2T/L 피뢰기 및 추락방지장치 설치공사 관련 안전거리확보","154kV 초동-밀양#2T/L 피뢰기 및 추락방지장치 설치 관련 안전거리확보 (49~56호)","2022-05-09 08:00","2022-05-09 18:00","2022-05-09 08:00","2022-05-09 18:00","연속"]
[524,"경기북부","구리","용정포천#2 T/L","154kV 포천S/S 옥내화 토건공사","154kV 포천S/S 옥내화 토건공사","2022-05-16 09:00","2022-05-20 18:00","2022-05-16 09:00","2022-05-20 18:00","연속"]
[525,"남서울","동서울","하남열병합#1T/L","송전선로 보통점검","고객선로 보통점검 시행","2022-05-09 09:00","2022-05-09 14:00","2022-05-09 09:00","2022-05-09 14:00","연속"]
[526,"남서울","동서울","하남열병합#2T/L","송전선로 보통점검","고객선로 보통점검 시행","2022-05-09 14:00","2022-05-09 18:00","2022-05-09 14:00","2022-05-09 18:00","연속"]