{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":9,"n_cols":11,"rows_kept":9,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 6월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"충북","직할","신중부신안성#1 T/L","신중부변전소 765kV GIS 제작사 하자보수","내부부품 교체 후 무부하가압을 위한 선로휴전","2022-06-25 10:00","2022-06-26 10:00","2022-06-25 10:00","2022-06-26 10:00","연속"]
[2,"충북","직할","신중부S/S CB 8671","신중부변전소 765kV GIS 제작사 하자보수","현대제 765kV GIS 지락고장 방지를 위한 내부부품 교체","2022-06-02 10:00","2022-06-12 10:00","2022-06-02 10:00","2022-06-12 10:00","연속"]
[3,"충북","직할","신서산신중부#1 T/L","차단기 조작시험","차단기 조작시험","2022-06-11 10:00","2022-06-12 10:00","2022-06-12 10:00","2022-06-12 12:00","연속"]
[4,"충북","직할","신중부S/S CB 8771","신중부변전소 765kV GIS 제작사 하자보수","현대제 765kV GIS 지락고장 방지를 위한 내부부품 교체","2022-06-15 10:00","2022-06-26 10:00","2022-06-15 10:00","2022-06-26 10:00","연속"]
[5,"경북",null,"신한울N/P #2호기 주변압기(8400,8472)","소내전원 절체시험 및 보호계전기 연동시험","소내전원 절체시험 및 보호계전기 연동시험","2022-06-08 14:00","2022-06-23 11:00","2022-06-08 14:00","2022-06-23 11:00","연속"]

{"sheet":"345설비","index":1,"n_rows":271,"n_cols":11,"rows_kept":271,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 6월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #1 Sh.R CB","22년 성동P/O 변전협력회사 총액공사","1차 GIS 보통점검","2022-06-27 10:00","2022-06-27 17:00","2022-06-27 10:00","2022-06-27 17:00","연속"]
[2,"서울","성동","성동S/S #2 Sh.R CB","22년 성동P/O 변전협력회사 총액공사","#2Sh.R 초기점검","2022-06-28 10:00","2022-06-28 17:00","2022-06-28 10:00","2022-06-28 17:00","연속"]
[3,"남서울","강남","신양재S/S #2 Sh.R CB","2022년 강남전력지사 345kV Sh.R 정밀점검","2022년 강남전력지사 345kV Sh.R 정밀점검 - 점검대상 : #2Sh.R - 병행작업 1. GIS 조작시험 2. Sh.R 보호반 대체","2022-06-20 09:00","2022-07-01 18:00","취소","취소","연속"]
[4,"남서울","강남","신양재S/S #2 M.Tr","22-23년도 강남전력지사 변전협력회사 총액공사","- M.TR 1,2차 GIS 조작시험 - S.TR 보통점검 - 3차측 VCB 초기점검 - 정기검사","2022-06-14 09:00","2022-06-15 18:00","2022-06-14 09:00","2022-06-15 18:00","연속"]
[5,"남서울","강남","신성남신양재 #1 T/L","21~22년 지중송전설비 위탁정비공사","345kV 신성남-신양재T/L 절연유 채유밸브 설치 및 절연유 채취","2022-06-07 09:00","2022-06-09 18:00","2022-06-13 09:00","2022-06-15 18:00","매일"]
[6,"남서울","강남","신성남신양재 #2 T/L","21~22년 지중송전설비 위탁정비공사","345kV 신성남-신양재T/L 절연유 채유밸브 설치 및 절연유 채취","2022-06-13 09:00","2022-06-15 18:00","2022-06-07 09:00","2022-06-09 18:00","매일"]
[7,"남서울","강남","신양재S/S #1 M.Tr","22-23년도 강남전력지사 변전협력회사 총액공사","- M.TR 1,2차 GIS 조작시험 - S.TR 보통점검 - 3차측 VCB 초기점검 - 정기검사","2022-06-07 09:00","2022-06-08 18:00","2022-06-07 09:00","2022-06-08 18:00","연속"]
[8,"남서울","강남","신양재S/S #1 Sh.R CB","2022년 강남전력지사 345kV Sh.R 정밀점검","2022년 강남전력지사 345kV Sh.R 정밀점검 - 점검대상 : #1Sh.R - 병행작업 1. GIS 조작시험 2. Sh.R 보호반 대체","2022-06-07 09:00","2022-06-17 18:00","취소","취소","연속"]
[9,"남서울","동서울","동서울S/S #1 M.Tr","동서울S/S 345kV #1,2M.Tr 2차 전력케이블 설치공사","○ 154kV XLPE 2,000㎟(D)×1C(#1M.Tr : 0.3km, #2M.Tr : 0.2km) ○ 케이블 포설 : 4구간 *3상 1구간 기준 ○ 케이블 접속 : 종단 8개소 *3상 1개소 기준 ○ 인하선 작업 : 모선 - EBA간 ○ 신설 전력케이블 및 170kV GIS 무부하 가압","2022-06-22 09:00","2022-06-29 18:00","2022-06-24 09:00","2022-07-01 18:00","연속"]
[10,"남서울","동서울","동서울S/S #2 M.Tr","동서울S/S 345kV #1,2M.Tr 2차 전력케이블 설치공사","○ 154kV XLPE 2,000㎟(D)×1C(#1M.Tr : 0.3km, #2M.Tr : 0.2km) ○ 케이블 포설 : 4구간 *3상 1구간 기준 ○ 케이블 접속 : 종단 8개소 *3상 1개소 기준 ○ 인하선 작업 : 모선 - EBA간 ○ 신설 전력케이블 및 170kV GIS 무부하 가압","2022-06-11 09:00","2022-06-12 18:00","취소","취소","연속"]
[11,"남서울","동서울","동서울S/S #2 M.Tr","동서울S/S 345kV #1,2M.Tr 2차 전력케이블 설치공사","○ 154kV XLPE 2,000㎟(D)×1C(#1M.Tr : 0.3km, #2M.Tr : 0.2km) ○ 케이블 포설 : 4구간 *3상 1구간 기준 ○ 케이블 접속 : 종단 8개소 *3상 1개소 기준 ○ 인하선 작업 : 모선 - EBA간 ○ 신설 전력케이블 및 170kV GIS 무부하 가압","2022-06-24 18:00","2022-07-01 18:00","2022-06-17 18:00","2022-06-19 18:00","연속"]
[12,"남서울","영등포","신광명S/S #70 BUS","345kV 신광명S/S GIS 용량대체","40kA GIS 철거, 63kA GIS 24CB 설치","2022-06-25 09:00","2022-06-25 14:00","2022-06-25 09:00","2022-06-25 14:00","연속"]
[13,"남서울","영등포","신시흥신광명#1 T/L","345kV 신광명S/S GIS 용량대체","40kA GIS 철거, 63kA GIS 24CB 설치","2022-06-25 14:00","2022-06-26 18:00","2022-06-25 14:00","2022-06-26 18:00","연속"]
[14,"남서울","영등포","신광명S/S #75 BUS","345kV 신광명S/S GIS 용량대체","40kA GIS 철거, 63kA GIS 24CB 설치","2022-06-25 14:00","2022-06-26 18:00","2022-06-25 14:00","2022-06-26 18:00","연속"]
[15,"남서울","영등포","서서울신광명#1 T/L","345kV 신광명S/S GIS 용량대체","40kA GIS 철거, 63kA GIS 24CB 설치","2022-06-25 09:00","2022-06-25 14:00","2022-06-25 09:00","2022-06-25 14:00","연속"]
[16,"남서울","영등포","신시흥신광명#2 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","ㅇ 345kV 63kA GIS 24CB 설치 ㅇ 구내 인출변경 전력구 시공 관련 345kV LA 이설","2022-06-02 10:00","2022-06-13 18:00","취소","취소","연속"]
[17,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥#1S/S 345kV #2M.Tr 2차 GIS 및 B/F 대체","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사 신시흥 7A BAY B/F 보호반 대체","2022-06-04 08:00","2022-06-22 18:00","2022-05-30 08:00","2022-06-17 18:00","연속"]
[18,"인천","직할","갈산S/S #2 Sh.R CB","갈산S/S #2Sh.R 초기점검, 7672GIS 초기점검","갈산S/S #2Sh.R 초기점검, 7672GIS 초기점검","2022-06-02 09:30","2022-06-03 18:00","2022-06-02 09:30","2022-06-03 18:00","연속"]
[19,"인천","시흥","영흥1TP영흥2TP#2 T/L","2022년 시흥전력지사 362kV 정밀점검공사","영흥T/P 345kV 영흥TP연락#2TL-#2G.Tr 1차 TIE GIS(7200) 정밀점검 관련 무부하가압용 휴전","2022-06-02 14:00","2022-06-02 15:00","2022-06-02 14:00","2022-06-02 15:00","연속"]
[20,"인천","부평","포스코CC인천TP#1 T/L","포스코인천CC #1T/L 보호반 성능개선(계통시험)","포스코인천CC #1T/L 보호반 성능개선(계통시험)","2022-06-03 09:00","2022-06-03 18:00","2022-06-02 08:00","2022-06-02 20:00","연속"]
[21,"인천","직할","신부평S/S #4 M.Tr","신부평S/S 345kV #4M.Tr 1차 7472,7400GIS 조작시험","신부평S/S 345kV #4M.Tr 1차 7472,7400GIS 조작시험 및 2차 6444GIS 보통점검","2022-06-03 09:30","2022-06-03 18:00","2022-06-03 09:30","2022-06-03 18:00","연속"]
[22,"인천","시흥","영흥T/P CB 7272","2022년 시흥전력지사 362kV 정밀점검공사","영흥T/P 345kV #2G.Tr 1차 GIS(7272) 정밀점검","2022-06-06 08:00","2022-06-09 18:00","2022-06-06 08:00","2022-06-09 18:00","연속"]
[23,"인천","부평","포스코CC인천TP#2 T/L","포스코인천CC #2T/L 보호반 성능개선(계통시험)","포스코인천CC #2T/L 보호반 성능개선(계통시험)","2022-06-07 09:00","2022-06-07 18:00","2022-06-03 08:00","2022-06-03 20:00","연속"]
[24,"인천","시흥","영흥1TP영흥2TP#2 T/L","2022년 시흥전력지사 362kV 정밀점검공사","영흥T/P 345kV #2G.Tr 1차 GIS(7272) 정밀점검 관련 무부하가압용 휴전","2022-06-09 14:00","2022-06-09 15:00","2022-06-09 14:00","2022-06-09 15:00","연속"]
[25,"인천","직할","신부평S/S CB 7271","신부평S/S 7172,7271 GIS조작시험","신부평S/S 7172,7271 GIS조작시험","2022-06-10 09:30","2022-06-10 14:00","2022-06-10 09:30","2022-06-10 14:00","연속"]
[26,"인천","직할","신부평S/S CB 7172","신부평S/S 7172,7271 GIS조작시험","신부평S/S 7172,7271 GIS조작시험","2022-06-10 14:00","2022-06-10 18:00","2022-06-10 14:00","2022-06-10 18:00","연속"]
[27,"인천","김포","신김포서인천CC T/L","345kV 신김포-서인천CC T/L 피뢰기 점검","345kV 신김포-서인천CC T/L 피뢰기 점검 - 대상 : 3상 피뢰기","2022-06-11 08:00","2022-06-11 18:00","2022-06-11 08:00","2022-06-11 18:00","연속"]
[28,"인천","시흥","영흥T/P CB 7772","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV #6G.Tr 1차 GIS(7772) 정밀점검","2022-06-13 08:00","2022-06-15 18:00","2022-06-13 08:00","2022-06-15 18:00","연속"]
[29,"인천","부평","서인천C/C CB 7472","서인천CC 7472GIS 보통점검 및 전자변 교체","서인천CC 7472GIS 보통점검 및 전자변 교체","2022-06-13 09:00","2022-06-13 18:00","2022-06-13 09:00","2022-06-13 18:00","연속"]
[30,"인천","직할","신부평S/S #3 Sh.R CB","신부평S/S 362kV 7379 GIS정밀점검공사","신부평S/S 362kV 7379 GIS정밀점검공사","2022-06-13 09:00","2022-06-15 18:00","2022-06-13 09:00","2022-06-15 18:00","연속"]
[31,"인천","부평","서인천C/C CB 7372","서인천CC 7372GIS 보통점검","서인천CC 7372GIS 보통점검","2022-06-14 09:00","2022-06-14 18:00","2022-06-14 09:00","2022-06-14 18:00","연속"]
[32,"인천","시흥","신시흥신광명#2 T/L","신시흥S/S 7A B/F 보호반 대체","신시흥S/S 7A B/F 보호반 대체","2022-06-06 09:00","2022-06-10 18:00","취소","취소","연속"]
[33,"인천","부평","서인천C/C CB 7400","서인천CC 7400GIS 보통점검","서인천CC 7400GIS 보통점검","2022-06-15 09:00","2022-06-15 18:00","2022-06-15 09:00","2022-06-15 18:00","연속"]
[34,"인천","시흥","영흥T/P CB 7671","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV 영흥TP연락#1T/L GIS(7671) 정밀점검","2022-06-16 08:00","2022-06-18 18:00","2022-06-16 08:00","2022-06-18 18:00","연속"]
[35,"인천","부평","서인천C/C CB 7471","서인천CC 7471GIS 보통점검","서인천CC 7471GIS 보통점검","2022-06-16 09:00","2022-06-16 18:00","2022-06-16 09:00","2022-06-16 18:00","연속"]
[36,"인천","직할","신부평S/S #1 Sh.R CB","신부평S/S #1Sh.R 보통점검, 7179GIS 조작시험","신부평S/S #1Sh.R 보통점검, 7179GIS 조작시험","2022-06-16 09:30","2022-06-17 18:00","2022-06-16 09:30","2022-06-17 18:00","연속"]
[37,"인천","부평","신가좌가정#1 T/L","송전철탑 추락방지시설 설치공사","345kV 신가좌-가정#1T/L 송전철탑 추락방지시설 설치공사","2022-06-18 08:00","2022-06-18 18:00","취소","취소","연속"]
[38,"인천","부평","신가좌가정#2 T/L","송전철탑 추락방지시설 설치공사","345kV 신가좌-가정#2T/L 송전철탑 추락방지시설 설치공사","2022-06-19 08:00","2022-06-19 18:00","취소","취소","연속"]
[39,"인천","시흥","영흥T/P CB 7600","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV 영흥TP연락#1T/L-#5G.Tr 1차 TIE GIS(7600) 정밀점검","2022-06-20 08:00","2022-06-22 18:00","2022-06-20 08:00","2022-06-22 18:00","연속"]
[40,"인천","시흥","신가좌신시흥#1 T/L","송전철탑 추락방지시설 설치공사","345kV 신가좌-신시흥#1T/L 송전철탑 추락방지시설 설치공사","2022-06-20 08:00","2022-06-22 18:00","2022-06-20 08:00","2022-06-22 18:00","연속"]
[41,"인천","직할","신부평S/S #2 Sh.R CB","신부평S/S 7279,7479GIS조작시험","신부평S/S 7279,7479GIS조작시험","2022-06-20 09:30","2022-06-20 14:00","2022-06-20 09:30","2022-06-20 14:00","연속"]
[42,"인천","직할","신부평S/S #4 Sh.R CB","신부평S/S 7279,7479GIS조작시험","신부평S/S 7279,7479GIS조작시험","2022-06-20 14:00","2022-06-20 18:00","2022-06-20 14:00","2022-06-20 18:00","연속"]
[43,"인천","시흥","영흥T/P CB 7672","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV #5G.Tr 1차 GIS(7672) 정밀점검","2022-06-23 08:00","2022-06-25 18:00","2022-06-23 08:00","2022-06-25 18:00","연속"]
[44,"인천","시흥","영흥T/P CB 7871","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV 신시흥-영흥TP#1T/L GIS(7871) 정밀점검","2022-06-27 08:00","2022-06-29 18:00","2022-06-27 08:00","2022-06-29 18:00","연속"]
[45,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥#1S/S 345kV #1 M.Tr 부싱 절연유 채유","신시흥#1S/S 345kV #1 M.Tr 부싱 절연유 채유","2022-06-27 09:00","2022-06-27 18:00","2022-06-27 09:00","2022-06-27 18:00","연속"]
[46,"인천","시흥","영흥T/P CB 7800","2022년 시흥전력지사 362kV 정밀점검공사","영흥#2T/P 345kV 신시흥-영흥TP#1T/L TIE GIS(7800) 정밀점검","2022-06-30 08:00","2022-07-02 18:00","2022-06-30 08:00","2022-07-02 18:00","연속"]
[47,"경기북부","구리","신가평포천LNGCC#2 T/L","송전선로 단상재폐로 결상회로 개선","송전선로 단상재폐로 결상회로 개선 신가평S/S 7300 GIS 보통점검공사","2022-06-03 09:00","2022-06-03 18:00","2022-06-03 09:00","2022-06-03 18:00","연속"]
[48,"경기북부","고양","신덕은파주문산CC#2 T/L","362kV GIS 및 CLR 보통점검, 유사고장방지 - 변전총액공사","1. 파주문산C/C 7372, 7371 GIS 보통점검 2. 신덕은S/S, 파주문산CC 신덕은-파주문산CC#2T/L 재폐로 결상회로 개선","2022-06-03 09:00","2022-06-08 18:00","2022-06-03 09:00","2022-06-08 18:00","연속"]
[49,"경기북부","직할","양주S/S #4 Sh.R CB","22-23년 경기북부 직할 변전협력회사 총액공사","#4Sh.R 냉각설비 세정","2022-06-08 12:00","2022-06-08 15:00","2022-06-15 12:00","2022-06-15 15:00","연속"]
[50,"경기북부","직할","양주S/S #6 Sh.R CB","22-23년 경기북부 직할 변전협력회사 총액공사","#6Sh.R 냉각설비 세정","2022-06-08 15:00","2022-06-08 18:00","2022-06-15 15:00","2022-06-15 18:00","연속"]
[51,"경기북부","고양","신덕은파주문산CC#1 T/L","362kV GIS 및 CLR 보통점검, 유사고장방지 - 변전총액공사","1. 파주문산C/C 7472, 7471 GIS 보통점검 2. 신덕은S/S, 파주문산CC 신덕은-파주문산CC#1T/L 재폐로 결상회로 개선","2022-06-09 09:00","2022-06-10 18:00","2022-06-09 09:00","2022-06-10 18:00","연속"]
[52,"경기북부","직할","양주중부#2 T/L","22~23년 고양전력 가공송전협력회사 총액공사","송전선로용 피뢰기 설치공사","2022-06-13 07:00","2022-06-17 18:00","2022-06-13 07:00","2022-06-17 18:00","연속"]
[53,"경기북부","구리","신가평S/S #3 Sh.R CB","'22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","장기사용 배전반 교체공사 -신가평S/S #74Bay B/F보호반 교체","2022-06-13 09:00","2022-06-17 18:00","2022-06-13 09:00","2022-06-17 18:00","연속"]
[54,"경기북부","구리","신가평포천LNGCC#1 T/L","'22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","장기사용 배전반 교체공사 - 신가평S/S #74Bay B/F보호반 교체","2022-06-13 09:00","2022-06-17 18:00","2022-06-13 09:00","2022-06-17 18:00","연속"]
[55,"경기북부","직할","신의정부S/S #2 M.Tr","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7300, 7372 CB 보통점검","2022-06-13 09:00","2022-06-14 18:00","2022-06-13 09:00","2022-06-14 18:00","연속"]
[56,"경기북부","구리","신가평S/S CB 7471","'22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","장기사용 배전반 교체공사 -신가평S/S #74Bay B/F보호반 교체","2022-06-13 09:00","2022-06-17 18:00","2022-06-13 09:00","2022-06-17 18:00","연속"]
[57,"경기북부","구리","신포천S/S CB 7671","22~23 구리전력 변전협력 총액공사","신포천S/S 신포천-동두천CC #2T/L 7671 차단기 조작시험","2022-06-14 09:00","2022-06-14 13:00","2022-06-14 09:00","2022-06-14 13:00","연속"]
[58,"경기북부","구리","신포천S/S CB 7471","22~23 구리전력 변전협력 총액공사","신포천S/S 신포천-포천CC #2T/L 7471 차단기 보통점검","2022-06-14 13:00","2022-06-14 18:00","2022-06-14 13:00","2022-06-14 18:00","연속"]
[59,"경기북부","직할","신의정부S/S #1 Sh.R","22-23년 경기북부 직할 변전협력회사 총액공사","#1Sh.R 냉각설비 세정","2022-06-14 14:00","2022-06-14 18:00","2022-06-14 14:00","2022-06-14 18:00","연속"]
[60,"경기북부","고양","신덕은S/S #2 M.Tr","22년 고양P/O 변전협력 총액공사","345kV M.Tr 상부 안전고리 설치관련 현장조사","2022-06-15 10:00","2022-06-15 14:00","취소","취소","연속"]
[61,"경기북부","고양","신덕은S/S #3 M.Tr","22년 고양P/O 변전협력 총액공사","345kV M.Tr 상부 안전고리 설치관련 현장조사","2022-06-15 14:00","2022-06-15 18:00","2022-06-15 10:00","2022-06-15 14:00","연속"]
[62,"경기북부","구리","미금S/S #2 M.Tr","미금S/S 종합예방진단시스템 설치","미금S/S 종합예방진단시스템 설치 관련 규격 실측 - OLTC 부분방전 센서 및 설치위치 간섭여부 확인 - 부싱진단장치 제작 관련 시험탭 규격 실측 - DGA 배관 설치 길이 산출","2022-06-16 09:00","2022-06-16 18:00","2022-06-16 09:00","2022-06-16 18:00","연속"]
[63,"경기북부","구리","미금S/S #3 M.Tr","미금S/S 종합예방진단시스템 설치","미금S/S 종합예방진단시스템 설치 관련 규격 실측 - OLTC 부분방전 센서 및 설치위치 간섭여부 확인 - 부싱진단장치 제작 관련 시험탭 규격 실측 - DGA 배관 설치 길이 산출","2022-06-17 09:00","2022-06-17 18:00","2022-06-17 09:00","2022-06-17 18:00","연속"]
[64,"경기북부","구리","미금S/S STATCOM CB","미금S/S STATCOM IGCT 교체공사","미금S/S STATCOM IGCT x 32EA 교체","2022-06-20 09:00","2022-06-24 18:00","2022-06-20 09:00","2022-06-24 18:00","연속"]
[65,"경기북부","고양","신덕은동두천CC#2 T/L","22~23년 고양전력지사 변전협력회사 총액공사","○ 신덕은S/S 345kV 74Bay B/F PNL 교체공사","2022-06-20 09:00","2022-06-24 18:00","2022-06-20 09:00","2022-06-24 18:00","연속"]
[66,"경기북부","고양","신덕은S/S #4 M.Tr","22~23년 고양전력지사 변전협력회사 총액공사","○ 신덕은S/S 345kV 74Bay B/F PNL 교체공사","2022-06-20 09:00","2022-06-24 18:00","2022-06-20 09:00","2022-06-24 18:00","연속"]
[67,"경기북부","구리","미금성동#2 T/L","미금S/S 감시제어설비 교체공사","장기사용 모자익반 교체 - 미금S/S 교체 72Bay 선로용 차단기 1대 감시제어 포인트이관 (→SA) - 72Bay LCP 및 배전반 모자익반 제어케이블 철거 및 신설분 결선","2022-06-20 09:00","2022-06-22 18:00","취소","취소","연속"]
[68,"경기북부","구리","신가평S/S #4 Sh.R CB","2022~23 구리전력 변전협력 총액공사","신가평S/S #4Sh.R 7671 GIS 보통점검 신가평S/S #4Sh.R 7679 GIS 조작시험","2022-06-21 09:00","2022-06-21 18:00","2022-06-21 09:00","2022-06-21 18:00","연속"]
[69,"경기북부","구리","신가평S/S CB 7671","2022~23 구리전력 변전협력 총액공사","신가평S/S #4Sh.R 7671 GIS 보통점검 신가평S/S #4Sh.R 7679 GIS 조작시험","2022-06-21 09:00","2022-06-21 18:00","2022-06-21 09:00","2022-06-21 18:00","연속"]
[70,"경기북부","구리","신가평S/S CB 7600","2022~23 구리전력 변전협력 총액공사","신가평S/S #4Sh.R 7671 GIS 보통점검 신가평S/S #4Sh.R 7679 GIS 조작시험","2022-06-21 09:00","2022-06-21 18:00","2022-06-21 09:00","2022-06-21 18:00","연속"]
[71,"경기북부","구리","신포천S/S #1 Sh.R CB","2022~23 구리전력 변전협력 총액공사","신포천S/S #1Sh.R 보통점검","2022-06-23 09:00","2022-06-24 18:00","2022-06-23 09:00","2022-06-24 18:00","연속"]
[72,"경기북부","구리","신포천S/S CB 7372","2022~23 구리전력 변전협력 총액공사","신포천S/S #1Sh.R 보통점검 신포천S/S 7372 GIS 보통점검","2022-06-23 09:00","2022-06-24 18:00","2022-06-23 09:00","2022-06-24 18:00","연속"]
[73,"경기북부","고양","신파주S/S #76 BUS","345kV 신파주S/S #4M.Tr 증설공사","가. 345kV 단상단권변압기(345/161/23kV 단상, 166.7MVA) x 3대 (현대) 나. 362kV GIS(4000A, 50kA, GIB 포함) x 1CB (현대) 다. 170kV GIS(2000A, 50kA, GIB 포함) x 1CCT (효성) 라. 보호배전반 x 1식 마. 기타 부대공사 x 1식","2022-06-23 09:00","2022-06-24 18:00","취소","취소","연속"]
[74,"경기북부","고양","신파주S/S SVC CB","345kV 신파주S/S #4M.Tr 증설공사","가. 345kV 단상단권변압기(345/161/23kV 단상, 166.7MVA) x 3대 (현대) 나. 362kV GIS(4000A, 50kA, GIB 포함) x 1CB (현대) 다. 170kV GIS(2000A, 50kA, GIB 포함) x 1CCT (효성) 라. 보호배전반 x 1식 마. 기타 부대공사 x 1식","2022-06-23 09:00","2022-06-24 18:00","취소","취소","연속"]
[75,"경기북부","구리","신포천S/S CB 7300","2022~23 구리전력 변전협력 총액공사","신포천S/S #1Sh.R 보통점검 신포천S/S 7300 GIS 보통점검","2022-06-23 09:00","2022-06-24 18:00","2022-06-23 09:00","2022-06-24 18:00","연속"]
[76,"경기북부","직할","양주중부#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","성능저하 지지애자 교체공사","2022-06-27 07:00","2022-06-30 18:00","2022-06-27 07:00","2022-06-30 18:00","연속"]
[77,"경기북부","고양","신덕은S/S #1 M.Tr","22년 상반기 고양전력 345kV 주변압기 및 OLTC 정밀점검공사","#1M.Tr A,B상 본체 및 OLTC 정밀점검공사","2022-06-27 09:00","2022-07-05 09:00","취소","취소","연속"]
[78,"경기북부","구리","신포천S/S CB 7500","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-동두천CC#1T/L TIE GIS (7500) 조작시험","2022-06-28 09:00","2022-06-28 14:00","2022-06-28 09:00","2022-06-28 14:00","연속"]
[79,"경기북부","구리","신포천S/S CB 7171","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-포천LNG#1T/L GIS 보통점검","2022-06-28 14:00","2022-06-28 18:00","2022-06-28 14:00","2022-06-28 18:00","연속"]
[80,"경기북부","직할","신의정부S/S #2 Sh.R CB","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7772 CB 조작시험, 7779 보통점검","2022-06-29 09:00","2022-06-30 14:00","취소","취소","연속"]
[81,"경기북부","직할","신의정부S/S CB 7772","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7772 CB 조작시험, 7779 보통점검","2022-06-29 09:00","2022-06-30 14:00","취소","취소","연속"]
[82,"경기북부","직할","신의정부S/S CB 7700","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7772 CB 조작시험, 7779 보통점검","2022-06-29 09:00","2022-06-30 14:00","취소","취소","연속"]
[83,"경기북부","구리","신포천포천LNGCC#2 T/L","송전선로 단상재폐로 결상회로 개선","신포천, 포천LNGC/C 송전선로 단상재폐로 결상회로 개선","2022-06-29 09:00","2022-06-29 18:00","2022-06-29 09:00","2022-06-29 18:00","연속"]
[84,"경기북부","구리","신포천S/S CB 7272","2022~23 구리전력 변전협력 총액공사","신포천S/S #2M.Tr 1차 7272 GIS 보통점검","2022-06-30 09:00","2022-06-30 14:00","2022-06-30 09:00","2022-06-30 14:00","연속"]
[85,"경기북부","구리","신포천S/S CB 7571","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-동두천CC #1T/L 7571 GIS 조작시험","2022-06-30 14:00","2022-06-30 18:00","2022-06-30 14:00","2022-06-30 18:00","연속"]
[86,"경기북부","직할","신의정부S/S CB 7872","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7872 CB 조작시험, 7879 보통점검","2022-06-30 14:00","2022-07-01 18:00","2022-06-30 14:00","2022-07-01 18:00","연속"]
[87,"경기북부","직할","신의정부S/S #3 Sh.R CB","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7872 CB 조작시험, 7879 보통점검","2022-06-30 14:00","2022-07-01 18:00","2022-06-30 14:00","2022-07-01 18:00","연속"]
[88,"경기북부","직할","신의정부S/S CB 7800","2022-2023년 경기북부 직할 변전협력회사 총액공사","신의정부S/S 362kV GIS 7872 CB 조작시험, 7879 보통점검","2022-06-30 14:00","2022-07-01 18:00","2022-06-30 14:00","2022-07-01 18:00","연속"]
[89,"경기","성남","신성남S/S #4 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr 보통점검 - 7572 보통점검 - 2차 GIS 조작시험 - 3차 모선 보통점검 - 부싱절연유 채유 - 순간압력센서 설치","2022-06-07 09:00","2022-06-08 18:00","2022-06-07 09:00","2022-06-08 18:00","연속"]
[90,"경기","성남","신성남S/S SEC CB 75760","22년 성남전력 GIS 보통점검 공사","- GIS 보통점검","2022-06-30 14:00","2022-06-30 18:00","2022-06-30 14:00","2022-06-30 18:00","연속"]
[91,"경기","성남","신성남S/S #5 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr 보통점검 - 부싱절연유 채유 - 순간압력센서 설치 - 2차 GIS 보통점검 - 3차 모선,DS 보통점검 - S.Tr 초기점검 - VCB 대체","2022-06-28 09:00","2022-06-29 18:00","2022-06-28 09:00","2022-06-29 18:00","연속"]
[92,"경기","성남","신성남S/S SEC CB 70710","22년 성남전력 GIS 보통점검 공사","- GIS 보통점검","2022-06-30 09:00","2022-06-30 14:00","2022-06-30 09:00","2022-06-30 14:00","연속"]
[93,"경기","성남","신성남S/S #2 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr 보통점검 - B상누유 누유보수 - 부싱절연유 채유 - 7272 보통점검 - 3차 모선 보통점검 - S.Tr 초기점검","2022-06-13 09:00","2022-06-17 18:00","2022-06-13 09:00","2022-06-17 18:00","연속"]
[94,"경기","성남","신성남S/S #1 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr,NGR 보통점검 - 7172 조작시험 - 2차 GIS 조작시험 - 순간압력센서 설치 - 부싱절연유 채유","2022-06-09 09:00","2022-06-10 18:00","2022-06-09 09:00","2022-06-10 18:00","연속"]
[95,"경기","성남","신성남S/S #3 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr 보통점검","2022-06-22 09:00","2022-06-23 18:00","2022-06-22 09:00","2022-06-23 18:00","연속"]
[96,"경기","성남","신수원S/S #1 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr,NGR 보통점검 - 7172 하자점검 - CVT 초기점검 - 1차 LA 대체 - 2차 GIS 조작시험 - 3차 GIS, 모선 보통점검 - 2차 LA 보통점검","2022-06-02 09:00","2022-06-03 18:00","2022-06-02 09:00","2022-06-03 18:00","연속"]
[97,"경기","성남","신수원S/S #2 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr 보통점검","2022-06-20 09:00","2022-06-21 18:00","2022-06-20 09:00","2022-06-21 18:00","연속"]
[98,"경기","성남","신용인동서울#2 T/L"," 고산1지구 345kV 신용인-동서울T/L 지중화공사"," 고산1지구 345kV 신용인-동서울T/L 지중화공사","2022-06-04 08:00","2022-06-23 18:00","2022-06-04 08:00","2022-06-23 18:00","연속"]
[99,"경기","성남","신안성신성남#2 T/L"," 345kV 신용인-동서울 등 2개T/L 지장철탑 이설공사"," 345kV 신용인-동서울 등 2개T/L 지장철탑 이설공사","2022-06-16 08:00","2022-06-23 18:00","2022-06-16 08:00","2022-06-23 18:00","연속"]
[100,"경기","성남","신용인동서울#1 T/L"," 345kV 신용인-동서울 등 2개T/L 지장철탑 이설공사"," 345kV 신용인-동서울 등 2개T/L 지장철탑 이설공사","2022-06-24 08:00","2022-07-01 18:00","2022-06-24 08:00","2022-07-01 18:00","연속"]
[101,"경기","성남","신안성신성남#1 T/L"," 345kV 신용인-동서울 등 2개T/L 지장철탑 이설공사"," 345kV 신용인-동서울 등 2개T/L 지장철탑 이설공사","2022-06-24 08:00","2022-07-01 18:00","2022-06-24 08:00","2022-07-01 18:00","연속"]
[102,"경기","성남","신안성신수원#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사 안전거리 확보(6회선 병가)","2022-06-14 08:00","2022-06-14 12:00","2022-06-14 08:00","2022-06-14 12:00","매일"]
[103,"경기","성남","신안성신수원#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사 안전거리 확보(6회선 병가)","2022-06-17 08:00","2022-06-17 12:00","2022-06-17 08:00","2022-06-17 12:00","매일"]
[104,"경기","성남","신안성S/S CB 7571","22년 성남전력지사 변전협력회사 총액공사","- 7571 보통점검","2022-06-23 09:00","2022-06-23 18:00","2022-06-23 09:00","2022-06-23 18:00","연속"]
[105,"경기","성남","신용인S/S CB 7772","22년 성남전력지사 변전협력회사 총액공사","- 7772 보통점검","2022-06-03 09:00","2022-06-03 18:00","2022-06-03 09:00","2022-06-03 18:00","연속"]
[106,"경기","성남","신용인S/S #2 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr 보통점검 - 부싱절연유 채유 - 2차 GIS 보통점검 - 3차 모선, DS 보통점검 - CVT 초기점검 - 3차 LA 하자점검 - S.Tr 대체","2022-06-30 09:00","2022-07-01 18:00","2022-06-30 09:00","2022-07-01 18:00","연속"]
[107,"경기","성남","신용인S/S #1 M.Tr","22년 성남전력 170kV GIS 정밀점검공사","- #1M.Tr 2차 GIS 정밀점검","2022-06-07 09:00","2022-06-09 18:00","2022-06-07 09:00","2022-06-09 18:00","연속"]
[108,"경기","직할","아산화성#2 T/L","345kV 화성S/S GIS 용량대체공사","아산화성#2TL 72-&gt74Bay 인출모선 환원","2022-06-07 08:00","2022-07-04 20:00","취소","취소","연속"]
[109,"경기","평택","고덕S/S #1 M.Tr","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사","2022-06-28 09:00","2022-07-01 18:00","2022-06-28 09:00","2022-07-01 18:00","연속"]
[110,"경기","평택","고덕고덕2#1 T/L CB","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사","2022-06-28 09:00","2022-07-01 18:00","2022-06-28 09:00","2022-07-01 18:00","연속"]
[111,"경기","평택","고덕S/S STATCOM CB","고덕S/S 345kV STATCOM 2/4분기 제작사 점검","시스템 운전상태 점검 등","2022-06-24 09:00","2022-06-26 18:00","2022-06-24 09:00","2022-06-26 18:00","연속"]
[112,"경기","평택","서안성S/S #4 M.Tr","345kV 서안성S/S GIS 증설공사","76Bay B/F 1CB 증설","2022-06-02 09:00","2022-06-03 18:00","2022-06-02 09:00","2022-06-03 18:00","연속"]
[113,"경기","평택","평택T/P #71 BUS"," 신평택C/C 345kV 7B51측 누기 보수"," 신평택C/C 345kV 7B51측 누기 보수","2022-06-02 09:00","2022-06-03 18:00","2022-06-02 09:00","2022-06-03 18:00","연속"]
[114,"경기","평택","평택T/P #2 TIE Tr","평택T/P 345kV #2TIE-Tr 권선온도계 교체","평택T/P 345kV #2TIE-Tr 불량 권선온도계 교체","2022-06-02 10:00","2022-06-02 18:00","2022-06-02 10:00","2022-06-02 18:00","연속"]
[115,"경기","평택","평택T/P CB 7771","22년 평택전력지사 변전협력회사 총액공사","평택T/P 362kV #1G/T 1차 7771 GIS 보통점검","2022-06-09 10:00","2022-06-09 18:00","2022-06-09 10:00","2022-06-09 18:00","연속"]
[116,"경기","평택","평택T/P CB 7700","22년 평택전력지사 변전협력회사 총액공사","평택T/P 362kV #1G/T 1차 TIE 7700 GIS 보통점검","2022-06-10 10:00","2022-06-10 18:00","2022-06-10 10:00","2022-06-10 18:00","연속"]
[117,"경기","평택","평택T/P CB 7871","22년 평택전력지사 변전협력회사 총액공사","평택T/P 362kV #2G/T 1차 7871 GIS 보통점검","2022-06-13 10:00","2022-06-13 18:00","2022-06-13 10:00","2022-06-13 18:00","연속"]
[118,"경기","평택","평택T/P CB 7800","22년 평택전력지사 변전협력회사 총액공사","평택T/P 362kV #2G/T 1차-#1S/T 1차 TIE 7800 GIS 보통점검","2022-06-14 10:00","2022-06-14 18:00","2022-06-14 10:00","2022-06-14 18:00","연속"]
[119,"경기","평택","화성신평택CC#1 T/L","22년 평택전력지사 변전협력회사 총액공사","평택T/P(신평택C/C) 화성-신평택C/C #1T/L GIS 보통점검 및 부싱,애자 코팅","2022-06-30 10:00","2022-06-30 18:00","2022-06-08 10:00","2022-06-08 18:00","연속"]
[120,"경기","평택","화성신평택CC#2 T/L","22년 평택전력지사 변전협력회사 총액공사","평택T/P(신평택C/C) 화성-신평택C/C #1T/L GIS 보통점검 및 부싱,애자 코팅","2022-06-29 10:00","2022-06-29 18:00","2022-06-07 10:00","2022-06-07 18:00","연속"]
[121,"경기","평택","평택T/P CB 7872","22년 평택전력지사 변전협력회사 총액공사","평택T/P 362kV #1S/T 1차 7872 GIS 보통점검","2022-06-15 10:00","2022-06-15 18:00","2022-06-15 10:00","2022-06-15 18:00","연속"]
[122,"강원","동해","동해안인개폐소#2 T/L","2022년 가공송전선로 순시점검 위탁공사","산불경과지역 정밀점검","2022-06-16 08:00","2022-06-20 18:00","2022-06-16 08:00","2022-06-20 18:00","매일"]
[123,"강원","동해","동해안인개폐소#1 T/L","2022년 가공송전선로 순시점검 위탁공사","산불경과지역 정밀점검","2022-06-13 08:00","2022-06-15 18:00","2022-06-13 08:00","2022-06-15 18:00","매일"]
[124,"강원","동해","동해S/S #2 M.Tr","22~23년 동해전력지사 변전정비 총액공사","1. 4729 3차측 MAIN VCB 대체 2. 2M.Tr 1차 CB 차단기 조작시험[7472]","2022-06-06 09:00","2022-06-10 18:00","2022-06-06 09:00","2022-06-10 18:00","연속"]
[125,"강원","동해","삼척G/P #3 Tie-Tr","22~23년 동해전력지사 변전정비 총액공사","1. 부싱절연유 채유","2022-06-14 14:00","2022-06-14 18:00","2022-06-14 14:00","2022-06-14 18:00","연속"]
[126,"강원","동해","삼척G/P #1 Tie-Tr","22~23년 동해전력지사 변전정비 총액공사","1. 부싱절연유 채유","2022-06-14 10:00","2022-06-14 14:00","2022-06-14 10:00","2022-06-14 14:00","연속"]
[127,"충북","직할","신진천S/S CB 7200","충북직할 변전협력회사 총액공사","345kV GIS 보통점검","2022-06-15 10:00","2022-06-15 18:00","2022-06-15 10:00","2022-06-15 18:00","연속"]
[128,"충북","직할","신진천S/S CB 7471","충북직할 변전협력회사 총액공사","345kV GIS 보통점검","2022-06-16 10:00","2022-06-16 18:00","2022-06-16 10:00","2022-06-16 18:00","연속"]
[129,"충북","직할","신중부신진천#1 T/L","22-23년 충북직할변전협력회사 총액공사","345kV CVT대체","2022-06-21 10:00","2022-06-23 18:00","취소","취소","연속"]
[130,"충북","청주","신옥천S/S #1 M.Tr","345kV M.Tr 보통점검","[22-23 청주전력 변전정비 총액공사] 신옥천S/S 345kV #1M.Tr 보통점검","2022-06-07 10:00","2022-06-09 18:00","2022-06-07 10:00","2022-06-09 18:00","연속"]
[131,"충북","충주","신충주S/S #1 M.Tr","22-23년 충주전력지사 변전협력회사 총액공사","신충주S/S #1M.Tr 1차,2차 GIS 보통점검","2022-06-13 09:00","2022-06-13 18:00","2022-06-13 09:00","2022-06-13 18:00","연속"]
[132,"충북","충주","신충주S/S #2 M.Tr","신충주S/S 154kV GIS 설치공사","재세능원#1T/L 설치 관련 안전이격 확보 (즉시가압 가능)","2022-06-18 09:00","2022-06-20 18:00","2022-06-18 09:00","2022-06-20 18:00","연속"]
[133,"충북","충주","신충주S/S #2 M.Tr","신충주S/S 154kV GIS 설치공사","재세능원#1T/L 설치 관련 안전이격 확보 (즉시가압 가능)","2022-06-25 09:00","2022-06-27 18:00","2022-06-25 09:00","2022-06-27 18:00","연속"]
[134,"대전세종충남","서산","당진T/P #72 Tie-Tr","22년 서산P/O 154kV GIS 정밀점검 공사","당진화력S/S 345kV #72TIE-Tr 2차 6B7 GIS 정밀점검 (병행1) 당진T/P 345kV #72 TIE-Tr 부싱절연유 채유 (병행2) 당진T/P 345kV #72 TIE-Tr 1차 7371, 7300 조작시험","2022-06-27 09:00","2022-06-29 18:00","2022-06-27 09:00","2022-06-29 18:00","연속"]
[135,"대전세종충남","서산","신당진개폐소북당진 T/L","22년 서산P/O 변전협력회사 총액공사","신당진S/S 345kV 개폐소-북당진T/L CB 결상회로 개선 (병행) 신당진S/S 345kV 개폐소-북당진T/L 7D71 GIS 보통점검","2022-06-20 09:00","2022-06-20 18:00","2022-06-20 09:00","2022-06-20 18:00","연속"]
[136,"대전세종충남","서산","북당진현대제철 T/L","345kV 북당진-현대제철 T/L 부싱 터미널 교체공사","345kV 북당진-현대제철 T/L 부싱 터미널 및 인하도선 교체(고객요청)","2022-06-07 09:00","2022-06-09 18:00","2022-06-07 09:00","2022-06-09 18:00","연속"]
[137,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","22년 서산P/O 변전협력회사 총액공사","신당진S/S 345kV 개폐소-태안화력#1T/L CB 결상회로 개선 (병행) 신당진S/S 345kV 개폐소-태안화력#1T/L 7A71 GIS, LA 및 CVT 보통점검","2022-06-17 09:00","2022-06-17 18:00","취소","취소","연속"]
[138,"대전세종충남","서산","신당진S/S CB 7471","22년도 장기 미동작 차단기 조작시험","신당진S/S 345kV 신당진-연락#1T/L 7471CB 조작시험","2022-06-22 10:00","2022-06-22 14:00","2022-06-22 10:00","2022-06-22 14:00","연속"]
[139,"대전세종충남","서산","태안T/P CB 7600","22년 서산P/O 변전협력회사 총액공사","태안화력S/S 345kV 신서산#1T/L-6호기 TIE 7600 CB 메커니즘 점검","2022-06-27 09:00","2022-06-27 18:00","2022-06-27 09:00","2022-06-27 18:00","연속"]
[140,"대전세종충남","서산","태안T/P CB 7671","22년 서산P/O 변전협력회사 총액공사","태안화력S/S 345kV 신서산-태안화력#1T/L 7671 GIS 보통점검","2022-06-24 09:00","2022-06-24 18:00","2022-06-24 09:00","2022-06-24 18:00","연속"]
[141,"대전세종충남","서산","태안T/P CB 7571","22년 서산P/O 변전협력회사 총액공사","태안화력S/S 345kV 개폐소-태안화력#1T/L 7571 GIS 보통점검","2022-06-29 09:00","2022-06-29 18:00","2022-06-29 09:00","2022-06-29 18:00","연속"]
[142,"대전세종충남","서산","태안T/P CB 7500","22년 서산P/O 변전협력회사 총액공사","태안화력S/S 345kV TIE 7500 CB 메커니즘 점검","2022-06-30 09:00","2022-06-30 18:00","2022-06-30 09:00","2022-06-30 18:00","연속"]
[143,"대전세종충남","서산","태안T/P CB 7672","22년 서산P/O 변전협력회사 총액공사","태안화력S/S 345kV 6호기 1차 7672 CB 메커니즘 점검","2022-06-28 09:00","2022-06-28 18:00","2022-06-28 09:00","2022-06-28 18:00","연속"]
[144,"대전세종충남","서산","태안T/P #1 Tie-Tr","태안T/P 345kV #1M.Tr 1차 PT측 스페이서 교체","태안T/P 345kV #1M.Tr 1차 PT측 스페이서 교체 (병행) 태안T/P 345kV #1M.Tr 1차 GIS 가스누기 보수공사","2022-06-07 09:00","2022-06-10 18:00","취소","취소","연속"]
[145,"대전세종충남","서산","태안T/P #2 Tie-Tr","22년 서산P/O 변전협력회사 총액공사","태안T/P 345kV #2M.Tr, 1(7771),2,3차 GIS, 1,2차 LA 보통점검","2022-06-13 09:00","2022-06-17 18:00","취소","취소","연속"]
[146,"대전세종충남","천안","신온양서서울#1 T/L","(5월취소시)신온양서서울1TL결상관련 회로개선","(5월취소시)신온양서서울1TL결상관련 회로개선","2022-06-28 09:00","2022-06-28 18:00","취소","취소","연속"]
[147,"대전세종충남","천안","신온양신탕정#2 T/L","(5월취소시)신온양신탕정2TL 결상관련 회로개선","(5월취소시)신온양신탕정2TL 결상관련 회로개선","2022-06-27 09:00","2022-06-27 18:00","2022-06-27 09:00","2022-06-27 18:00","연속"]
[148,"대전세종충남","천안","신온양신탕정#1 T/L","신온양S/S 345kV 79B/F 보호배전반 교체","신온양S/S 345kV 79B/F 보호배전반 교체","2022-06-21 09:00","2022-06-24 18:00","2022-06-21 09:00","2022-06-24 18:00","연속"]
[149,"대전세종충남","천안","신온양서서울#2 T/L","(5월취소시)신온양서서울2TL결상관련 회로개선","(5월취소시)신온양서서울2TL결상관련 회로개선","2022-06-29 09:00","2022-06-29 18:00","취소","취소","연속"]
[150,"대전세종충남","천안","아산S/S #2 M.Tr","아산S/S 345kV #2 M.Tr 정밀점검","아산S/S 345kV #2 M.Tr 정밀점검","2022-06-07 09:00","2022-06-10 18:00","2022-06-07 09:00","2022-06-10 18:00","연속"]
[151,"대전세종충남","천안","아산S/S CB 7371","아산S/S 345kV 7371GIS 보통점검, 7300CB 개폐타임 측정","아산S/S 345kV 7371GIS 보통점검, 7300CB 개폐타임 측정","2022-06-13 09:00","2022-06-13 14:00","2022-06-13 09:00","2022-06-13 14:00","연속"]
[152,"대전세종충남","천안","아산S/S CB 7300","아산S/S 345kV 7371GIS 보통점검, 7300CB 개폐타임 측정","아산S/S 345kV 7371GIS 보통점검, 7300CB 개폐타임 측정","2022-06-13 14:00","2022-06-13 18:00","2022-06-13 14:00","2022-06-13 18:00","연속"]
[153,"대전세종충남","청양","청양보령TP#1 T/L","345kV 청양-보령화력#1T/L 관련기기 점검","345kV 청양-보령화력#1T/L 관련기기 점검","2022-06-02 09:00","2022-06-03 18:00","취소","취소","연속"]
[154,"대전세종충남","청양","청양신탕정#1 T/L","(5월 취소시)청양S/S 73BAY B/F PNL 및 T/L 보호반 대체","(5월 취소시)청양S/S 73BAY B/F PNL 및 T/L 보호반 대체","2022-06-07 09:00","2022-06-18 18:00","취소","취소","연속"]
[155,"대전세종충남","청양","청양군산#2 T/L","(5월 취소시)청양S/S 73BAY B/F PNL 대체","(5월 취소시)청양S/S 73BAY B/F PNL 대체","2022-06-07 09:00","2022-06-18 18:00","취소","취소","연속"]
[156,"대전세종충남","청양","청양S/S #2 M.Tr","청양S/S 345kV #2M.Tr 정밀점검 공사","청양S/S 345kV #2M.Tr 정밀점검 공사","2022-06-06 09:00","2022-06-24 18:00","2022-06-06 09:00","2022-06-24 18:00","연속"]
[157,"대전세종충남","청양","신옥천청양 T/L","(5월 취소시)[송전] 345kV 신옥천-청양T/L 추락방지시설 설치공사","[송전] 345kV 신옥천-청양T/L 추락방지시설 설치공사","2022-06-20 08:00","2022-06-24 18:00","취소","취소","매일"]
[158,"전북","군산","군산S/S #1 M.Tr","군산P/O OLTC 정밀점검공사","군산S/S #1M.Tr A, B, C상 OLTC 점검","2022-06-13 09:00","2022-06-16 09:00","2022-06-13 09:00","2022-06-16 09:00","연속"]
[159,"전북","군산","군산S/S #4 M.Tr","군산P/O OLTC 정밀점검공사","군산S/S #4M.Tr A, B, C상 OLTC 점검","2022-06-16 09:00","2022-06-18 09:00","2022-06-16 09:00","2022-06-18 09:00","연속"]
[160,"전북","군산","군산새만금#1 T/L","군산P/O 154kV 이상 차단기 점검공사","- 군산 7771 CB 점검 - 새만금 7271 CB 점검","2022-06-27 09:00","2022-06-27 18:00","2022-06-27 09:00","2022-06-27 18:00","연속"]
[161,"전북","군산","군산새만금#2 T/L","군산P/O 154kV 이상 차단기 점검공사","- 군산 7871 CB 점검 - 새만금 7371 CB 점검","2022-06-29 09:00","2022-06-29 18:00","2022-06-29 09:00","2022-06-29 18:00","연속"]
[162,"전북","군산","군산S/S #3 M.Tr","군산S/S #3M.Tr 누유개소 보수공사","군산S/S #3M.Tr C상 누유개소 보수공사","2022-06-20 09:00","2022-06-20 18:00","2022-06-20 09:00","2022-06-20 18:00","연속"]
[163,"전북","군산","새만금S/S #3 M.Tr","군산P/O 154kV 이상 차단기 점검공사","- 새만금 7372 CB 점검 - 새만금 7300 CB 점검","2022-06-30 09:00","2022-06-30 18:00","2022-06-30 09:00","2022-06-30 18:00","연속"]
[164,"전북","군산","새만금S/S #2 M.Tr","군산P/O 154kV 이상 차단기 점검공사","- 새만금 7272 CB 점검 - 새만금 7200 CB 점검","2022-06-28 09:00","2022-06-28 18:00","2022-06-28 09:00","2022-06-28 18:00","연속"]
[165,"전북","김제","신김제S/S #1 M.Tr","신김제S/S 345kV 주변압기 보통점검","신김제S/S 345kV 주변압기 보통점검","2022-06-22 09:00","2022-06-25 18:00","2022-06-22 09:00","2022-06-25 18:00","연속"]
[166,"전북","직할","신남원S/S CB 7800","신남원S/S 장기사용 #78 Bay 차단실패보호반 대체공사","신남원S/S 장기사용 #78 Bay 차단실패보호반 대체공사 - 휴전선로 : 신남원-신광주#2T/L, 7800","2022-06-07 09:00","2022-06-10 18:00","2022-06-07 09:00","2022-06-10 18:00","연속"]
[167,"전북","김제","신김제S/S CB 7300"," 김제PO 154kV이상 차단기 조작시험"," 김제PO 154kV이상 차단기 조작시험","2022-06-17 09:30","2022-06-17 18:00","2022-06-17 09:30","2022-06-17 18:00","연속"]
[168,"광주전남","강진","신강진S/S #1 M.Tr","2022~23년도 강진전력지사 변전협력회사 총액공사","신강진S/S #1M.Tr 부싱 절연열화 진단","2022-06-09 10:00","2022-06-09 14:00","2022-06-09 10:00","2022-06-09 14:00","연속"]
[169,"광주전남","강진","신강진S/S #2 M.Tr","2022~23년도 강진전력지사 변전협력회사 총액공사","신강진S/S #2M.Tr 부싱 절연열화 진단","2022-06-09 14:00","2022-06-09 18:00","2022-06-09 14:00","2022-06-09 18:00","연속"]
[170,"광주전남","광주","신광주S/S CB 7171","22~23년 광주전력지사 변전협력회사 총액공사","362kV GIS 차단기 조작시험(7171CB)","2022-06-08 09:00","2022-06-08 14:00","2022-06-08 09:00","2022-06-08 14:00","연속"]
[171,"광주전남","광주","신광주S/S CB 7100","22~23년 광주전력지사 변전협력회사 총액공사","362kV GIS 차단기 조작시험(7100CB)","2022-06-08 14:00","2022-06-08 18:00","2022-06-08 14:00","2022-06-08 18:00","연속"]
[172,"광주전남","광주","신화순S/S #1 Sh.R CB","신화순S/S #1Sh.R 하자 조치","신화순S/S #1Sh.R 하자 조치","2022-06-06 09:00","2022-06-07 18:00","2022-06-06 09:00","2022-06-07 18:00","연속"]
[173,"광주전남","순천","광양C/C CB 7200","'22-23년 순천전력지사 변전협력회사 총액공사","광양CC 345kV 광양-광양CC #1T/L - #3M.Tr TIE CB 7200 CB 타임측정","2022-06-14 14:00","2022-06-14 18:00","2022-06-14 14:00","2022-06-14 18:00","연속"]
[174,"광주전남","순천","광양C/C CB 7100","'22-23년 순천전력지사 변전협력회사 총액공사","광양-광양CC#2T/L-#4M.Tr TIE 7100 CB","2022-06-13 14:00","2022-06-13 18:00","2022-06-13 14:00","2022-06-13 18:00","연속"]
[175,"광주전남","순천","광양C/C CB 7171","'22-23년 순천전력지사 변전협력회사 총액공사","광양CC 345kV 광양-광양CC #2T/L 7171CB","2022-06-13 10:00","2022-06-13 14:00","2022-06-13 10:00","2022-06-13 14:00","연속"]
[176,"광주전남","순천","광양C/C CB 7172","'22-23년 순천전력지사 변전협력회사 총액공사","광양CC 345kV #4M.Tr 1차 7172 CB타임측정","2022-06-15 10:00","2022-06-15 14:00","2022-06-15 10:00","2022-06-15 14:00","연속"]
[177,"광주전남","순천","광양C/C CB 7272","'22-23년 순천전력지사 변전협력회사 총액공사","광양CC 345kV #3M.Tr 1차 7272 CB타임측정","2022-06-15 14:00","2022-06-15 18:00","2022-06-15 14:00","2022-06-15 18:00","연속"]
[178,"광주전남","순천","광양C/C CB 7372","'22-23년 순천전력지사 변전협력회사 총액공사","광양CC 345kV #2M.Tr 1차 7372 CB타임측정","2022-06-16 10:00","2022-06-16 14:00","2022-06-16 10:00","2022-06-16 14:00","연속"]
[179,"광주전남","순천","광양C/C CB 7300","'22-23년 순천전력지사 변전협력회사 총액공사","광양CC 345kV #2M.Tr - #1M.Tr TIE 7300 CB 타임측정","2022-06-16 14:00","2022-06-16 18:00","2022-06-16 14:00","2022-06-16 18:00","연속"]
[180,"광주전남","순천","광양C/C CB 7371","'22-23년 순천전력지사 변전협력회사 총액공사","광양CC 345kV #1M.Tr 1차 7371 CB타임측정","2022-06-17 10:00","2022-06-17 14:00","2022-06-17 10:00","2022-06-17 14:00","연속"]
[181,"광주전남","순천","광양C/C CB 7271","'22-23년 순천전력지사 변전협력회사 총액공사","광양CC 345kV 광양-광양CC #1T/L 7271 CB 타임측정","2022-06-14 10:00","2022-06-14 14:00","2022-06-14 10:00","2022-06-14 14:00","연속"]
[182,"광주전남","순천","광양S/S CB 7600","'22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345kV 광양-하동TP#2T/L-TIE 7600 CB 타임측정","2022-06-02 14:00","2022-06-02 18:00","2022-06-02 14:00","2022-06-02 18:00","연속"]
[183,"광주전남","순천","광양S/S CB 7671","'22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345kV 광양-하동TP#2T/L 7671 CB 타임측정","2022-06-02 10:00","2022-06-02 14:00","2022-06-02 10:00","2022-06-02 14:00","연속"]
[184,"광주전남","순천","여수T/P #4 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 수치 측정","2022-06-28 10:00","2022-06-28 15:00","취소","취소","연속"]
[185,"광주전남","순천","여수T/P #3 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 여수화력S/Y #3M.Tr, 2차 GIS 보통점검 및 1차 CB 타임측정, 7300 CB 타임측정","2022-06-02 10:00","2022-06-03 18:00","취소","취소","연속"]
[186,"광주전남","순천","여수T/P #1 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 345Kv #1M.Tr 보통점검(OFU), 3차 GPT 하자점검","2022-06-07 10:00","2022-06-09 18:00","취소","취소","연속"]
[187,"광주전남","순천","여수T/P #2 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 수치 측정","2022-06-27 10:00","2022-06-27 15:00","취소","취소","연속"]
[188,"광주전남","순천","율촌C/C CB 7271","'22-23년 순천전력지사 변전협력회사 총액공사","율촌복합S/Y 345kV 율촌CC-여수TP T/L 7271 CB타임측정","2022-06-03 10:00","2022-06-03 14:00","2022-06-03 14:00","2022-06-03 18:00","연속"]
[189,"광주전남","순천","율촌C/C CB 7171","'22-23년 순천전력지사 변전협력회사 총액공사","율촌복합S/Y 345kV 광양-율촌CC T/L 7171CB 타임측정","2022-06-03 10:00","2022-06-03 14:00","2022-06-03 10:00","2022-06-03 14:00","연속"]
[190,"대구","경산","신경산S/S #1 M.Tr","22~23년 경산PO 변전협력회사 총액공사","- 6144장기미동작 차단기 조작시험 - LA 교체 - 부싱절연유 채유","2022-06-13 09:30","2022-06-13 18:00","2022-06-13 09:30","2022-06-13 18:00","연속"]
[191,"대구","경산","신경산S/S #2 M.Tr","22~23년 경산PO 변전협력회사 총액공사","부싱절연유 채유","2022-06-14 09:30","2022-06-14 18:00","2022-06-14 09:30","2022-06-14 18:00","연속"]
[192,"대구","달성","고령S/S #2 M.Tr","#2M.Tr 누유보수","#2M.Tr 누유보수(A상 샘플링밸브, B상 BCT단자)","2022-06-28 09:00","2022-06-28 18:00","2022-06-28 09:00","2022-06-28 18:00","연속"]
[193,"대구","달성","고령S/S #4 M.Tr","#4M.Tr OLTC 정밀점검","#4M.Tr OLTC 정밀점검","2022-06-07 09:00","2022-06-10 18:00","2022-06-07 09:00","2022-06-10 18:00","연속"]
[194,"대구","달성","북경남대구#1 T/L","대구S/S 7279GIS 정밀점검 무부하가압[TEST]","대구S/S 7279GIS 정밀점검 무부하가압[TEST]","2022-06-16 13:00","2022-06-16 18:00","2022-06-16 13:00","2022-06-16 18:00","연속"]
[195,"대구","달성","대구S/S #2 BUS","대구S/S 7279GIS 정밀점검 무부하가압","대구S/S 7279GIS 정밀점검 무부하가압","2022-06-16 13:00","2022-06-16 18:00","2022-06-16 13:00","2022-06-16 18:00","연속"]
[196,"대구","달성","대구S/S #1 BUS","대구S/S 7179GIS 정밀점검 무부하가압","대구S/S 7179GIS 정밀점검 무부하가압","2022-06-10 13:00","2022-06-10 18:00","2022-06-10 13:00","2022-06-10 18:00","연속"]
[197,"대구","달성","신경산대구#1 T/L","대구S/S 7179GIS 정밀점검 무부하가압[TEST]","대구S/S 7179GIS 정밀점검 무부하가압[TEST]","2022-06-10 13:00","2022-06-10 18:00","2022-06-10 13:00","2022-06-10 18:00","연속"]
[198,"대구","달성","대구S/S #1 Sh.R CB","대구S/S 7179GIS 정밀점검","대구S/S 7179GIS 정밀점검","2022-06-07 09:00","2022-06-10 18:00","2022-06-07 09:00","2022-06-10 18:00","연속"]
[199,"대구","달성","대구S/S #2 Sh.R CB","대구S/S 7279GIS 정밀점검","대구S/S 7279GIS 정밀점검","2022-06-13 09:00","2022-06-16 18:00","2022-06-13 09:00","2022-06-16 18:00","연속"]
[200,"대구","칠곡","북대구S/S #3 M.Tr","북대구S/S #3M.Tr 보통점검","북대구S/S #3M.Tr 보통점검","2022-06-02 09:30","2022-06-02 18:00","2022-06-02 09:30","2022-06-02 18:00","연속"]
[201,"대구","칠곡","서대구S/S CB 7772","서대구S/S 345kV 7772 GCB 장기미동작점검","서대구S/S 345kV 7772 GCB 장기미동작점검","2022-06-13 09:30","2022-06-13 14:00","2022-06-13 09:30","2022-06-13 14:00","연속"]
[202,"대구","칠곡","서대구S/S CB 7871","서대구S/S 345kV 7871 GCB 장기미동작점검","서대구S/S 345kV 7871 GCB 장기미동작점검","2022-06-13 14:00","2022-06-13 18:00","2022-06-13 14:00","2022-06-13 18:00","연속"]
[203,"대구","칠곡","서대구S/S CB 7771","서대구S/S 345kV 7771 GCB 장기미동작점검","서대구S/S 345kV 7771 GCB 장기미동작점검","2022-06-14 09:30","2022-06-14 14:00","2022-06-14 09:30","2022-06-14 14:00","연속"]
[204,"대구","칠곡","서대구S/S CB 7700","서대구S/S 345kV 7700 GCB 장기미동작점검","서대구S/S 345kV 7700 GCB 장기미동작점검","2022-06-14 14:00","2022-06-14 18:00","2022-06-14 14:00","2022-06-14 18:00","연속"]
[205,"대구","포항","신포항신월성NP#4 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-06-03 09:00","2022-06-03 18:00","취소","취소","연속"]
[206,"대구","포항","신포항신월성NP#3 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-06-02 09:00","2022-06-02 18:00","2022-06-02 09:00","2022-06-02 18:00","연속"]
[207,"대구","포항","월성N/P CB 7272","월성S/Y 7200, 7272 GIS 정밀점검","월성S/Y 7200, 7272 GIS 정밀점검","2022-06-07 09:00","2022-06-12 18:00","2022-06-07 09:00","2022-06-12 18:00","연속"]
[208,"대구","포항","울주월성NP#2 T/L","염해방지 애자코팅 공사","염해방지 애자코팅 공사","2022-06-10 09:00","2022-06-12 18:00","2022-06-10 09:00","2022-06-12 18:00","연속"]
[209,"대구","포항","월성N/P CB 7200","월성S/Y 7200, 7272 GIS 정밀점검","월성S/Y 7200, 7272 GIS 정밀점검","2022-06-07 09:00","2022-06-12 18:00","2022-06-07 09:00","2022-06-12 18:00","연속"]
[210,"대구","칠곡","북대구S/S #1 M.Tr","북대구S/S #1M.Tr 초기점검 / 1,2차 GIS 보통점검 ","북대구S/S #1M.Tr 초기점검 / 1,2차 GIS 보통점검 ","2022-06-03 09:30","2022-06-03 18:00","2022-06-03 09:30","2022-06-03 18:00","연속"]
[211,"부산울산","동부산","고리N/P CB 7271","고리N/P 7271CB 차단기 동작시험","고리N/P 7271CB 차단기 동작시험(신울산-고리#2T/L)","2022-06-15 09:30","2022-06-15 17:00","2022-06-30 09:30","2022-06-30 17:00","연속"]
[212,"부산울산","동부산","신양산북부산#2 T/L","신양산S/S 자동재투입용 7300,7371 GIS 결상회로 보완","신양산S/S 자동재투입용 7300,7371 GIS 결상회로 보완 병행)7300,7371 GIS 차단기 동작시험","2022-06-22 14:00","2022-06-22 18:00","취소","취소","연속"]
[213,"부산울산","동부산","신양산북부산#1 T/L","신양산S/S 자동재투입용 7400,7471 GIS 결상회로 보완","신양산S/S 자동재투입용 7400,7471 GIS 결상회로 보완(완료) 병행)7400,7471GIS 차단기 동작시험","2022-06-22 09:30","2022-06-22 14:00","취소","취소","연속"]
[214,"부산울산","동부산","신양산S/S #4 M.Tr","신양산S/S 345kV M.Tr 3차측 현대화 공사","345kV #4M.Tr 3차측 현대화공사","2022-06-07 09:30","2022-07-15 18:00","취소","취소","연속"]
[215,"부산울산","북부산","신김해북부산#1 T/L","22-23 북부산전력지사 변전 총액공사","북부산S/S 345kV 7371,7300, 7378 차단기 동작시험","2022-06-02 10:00","2022-06-02 18:00","2022-06-03 10:00","2022-06-03 18:00","연속"]
[216,"부산울산","북부산","신김해북부산#2 T/L","22-23 북부산전력지사 변전 총액공사","북부산S/S 345kV 7478 차단기 동작시험","2022-06-17 10:00","2022-06-17 14:00","2022-06-17 10:00","2022-06-17 14:00","연속"]
[217,"부산울산","북부산","북부산울산TP#1 T/L","북부산S/S 345kV 변압기 3차 현대화공사","북부산S/S 345kV #2M.Tr 3차 현대화 공사 시험가압(24h) ※시험가압선로 : 345kV 북부산-울산TP#1T/L","2022-06-23 18:00","2022-06-24 18:00","2022-06-30 18:00","2022-07-01 18:00","연속"]
[218,"부산울산","북부산","북부산S/S #4 M.Tr","22-23 북부산전력지사 변전협력회사 총액공사","#4M.Tr 1차측 CVT 설치","2022-06-27 09:00","2022-06-28 18:00","2022-06-27 09:00","2022-06-28 18:00","연속"]
[219,"부산울산","서부산","신김해신녹산#1 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 : 23~52호(22기)","2022-06-07 07:00","2022-06-12 18:00","2022-06-13 07:00","2022-06-13 18:00","연속"]
[220,"부산울산","서부산","신김해신녹산#2 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 : 23~52호(22기)","2022-06-14 07:00","2022-06-19 18:00","2022-06-14 07:00","2022-06-14 18:00","연속"]
[221,"부산울산","울산","동울산S/S #1 M.Tr","22~23년 변전협력회사 총액공사","- M.Tr 보통점검 - 1,2차 부싱절연유 채유 - 1차 GIS(7100,7172) 보통점검 - 1,2차 피뢰기 보통점검","2022-06-07 09:00","2022-06-08 18:00","2022-06-07 09:00","2022-06-08 18:00","연속"]
[222,"부산울산","울산","동울산S/S CB 7271","22~23년 변전협력회사 총액공사","- GIS(7271) 보통점검","2022-06-09 09:00","2022-06-09 18:00","2022-06-09 09:00","2022-06-09 18:00","연속"]
[223,"부산울산","울산","동울산S/S CB 7171","22~23년 변전협력회사 총액공사","- GIS(7171) 보통점검","2022-06-10 09:00","2022-06-10 18:00","2022-06-10 09:00","2022-06-10 18:00","연속"]
[224,"부산울산","울산","동울산S/S #2 M.Tr","22~23년 변전협력회사 총액공사","- 1차 GIS(7200, 7272) 보통점검 - 1,2차 피뢰기 보통점검","2022-06-13 09:00","2022-06-14 18:00","2022-06-13 09:00","2022-06-14 18:00","연속"]
[225,"부산울산","울산","동울산S/S #3 M.Tr","22~23년 변전협력회사 총액공사","- 1차 GIS(7472) 보통점검 - 1,2,3차 피뢰기 보통점검","2022-06-16 09:00","2022-06-16 18:00","2022-06-16 09:00","2022-06-16 18:00","연속"]
[226,"부산울산","울산","신온산신울산#2 T/L","345kV 신양산-신대연 등 7개T/L 자기애관 교체공사","345kV 신울산-신온산T/L 자기애관 교체공사 자기애관2,500㎟을 폴리머애관 2,500㎟으로 변경","2022-06-02 09:00","2022-06-17 18:00","2022-06-02 09:00","2022-06-17 18:00","연속"]
[227,"부산울산","울산","신울산S/S #75 BUS","신울산S/S 345kV 차단기 용량대체공사","345kV GIB - 옥외 모선 분리","2022-06-15 08:00","2022-06-15 18:00","2022-06-15 08:00","2022-06-15 18:00","연속"]
[228,"부산울산","울산","신울산S/S #1 M.Tr","신울산S/S 345kV 차단기 용량대체공사","○ 345kV GIS 대체 관련 #1M.Tr 접속지점 변경(구 71BAY → 신 76BAY) ○ 345kV GIS 대체 관련 보호배전반 이설 및 연동시험","2022-06-13 09:00","2022-07-22 18:00","2022-06-13 09:00","2022-07-22 18:00","연속"]
[229,"부산울산","울산","신울산S/S #76 BUS","신울산S/S 345kV 차단기 용량대체공사","345kV SEC 철거를 위한 도체 분리","2022-06-27 09:00","2022-06-30 18:00","2022-06-27 09:00","2022-06-30 18:00","연속"]
[230,"부산울산","울산","신울산S/S #71 BUS","신울산S/S 345kV 차단기 용량대체공사","345kV SEC 철거를 위한 도체 분리","2022-06-20 09:00","2022-06-23 18:00","2022-06-20 09:00","2022-06-23 18:00","연속"]
[231,"부산울산","울산","북부산신울산#2 T/L","신울산S/S 345kV 차단기 용량대체공사","○ 345kV GIS 대체 관련 송전선로 접속지점 변경(구 71BAY → 신 72BAY) ○ 345kV GIS 대체 관련 보호배전반 이설 및 연동시험","2022-06-13 09:00","2022-07-22 18:00","2022-06-13 09:00","2022-07-22 18:00","연속"]
[232,"부산울산","울산","신울산S/S #70 BUS","신울산S/S 345kV 차단기 용량대체공사","345kV GIB - 옥외 모선 분리","2022-06-14 08:00","2022-06-14 18:00","2022-06-14 08:00","2022-06-14 18:00","연속"]
[233,"부산울산","울산","남울산울산TP#2 T/L","울산복합S/Y 345kV 보호제어설비 전담운영공사","- 울산복합S/Y 345kV 보호제어설비 전담운영공사 - (병행) 남울산S/S 7471, 7400 GIS 하자점검 - (병행) 울산복합S/Y CVT 보통점검","2022-06-27 09:00","2022-07-15 18:00","2022-06-27 09:00","2022-07-15 18:00","연속"]
[234,"부산울산","울산","울산C/C #1 Tie-Tr","울산복합S/Y 345kV 보호제어설비 전담운영공사","- 울산복합S/Y 345kV 보호제어설비 전담운영공사 - (병행) 2차 GIS(6144) 차단기 동작시험","2022-06-13 09:00","2022-06-24 18:00","2022-06-13 09:00","2022-06-24 18:00","연속"]
[235,"부산울산","울산","울산C/C #2 Tie-Tr","22~23년 변전협력회사 총액공사","- 유사고장 방지관련 애자 절연코팅","2022-06-29 09:00","2022-07-01 18:00","2022-06-29 09:00","2022-07-01 18:00","연속"]
[236,"부산울산","울산","울산C/C CB 7672","울산복합S/Y 345kV 보호제어설비 전담운영공사","- 울산복합S/Y 345kV 보호제어설비 전담운영공사","2022-06-27 09:00","2022-07-15 18:00","2022-06-27 09:00","2022-07-15 18:00","연속"]
[237,"부산울산","울산","울산C/C #3 Tie-Tr","22년 상반기 154kV GIS 정밀점검 공사","- 2차 GIS 정밀점검 - (병행) M.Tr 보통점검","2022-06-02 09:00","2022-06-03 18:00","2022-06-06 09:00","2022-06-08 18:00","연속"]
[238,"부산울산","울산","울산C/C CB 7472","울산복합S/Y 345kV 보호제어설비 전담운영공사","- 울산복합S/Y 345kV 보호제어설비 전담운영공사","2022-06-13 09:00","2022-06-24 18:00","2022-06-13 09:00","2022-06-24 18:00","연속"]
[239,"부산울산","울산","울주S/S #3 M.Tr","22~23년 변전협력회사 총액공사","- 1차 피뢰기 대체","2022-06-08 09:00","2022-06-08 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[240,"부산울산","직할","신대연S/S #2 M.Tr","신대연S/S 종합예방진단시스템 설치공사","신대연S/S 종합예방진단시스템 설치공사 중 OLTC 상단 PD센서 설치를 위한 휴전 (단순 안전거리 이격 확보)","2022-06-03 09:00","2022-06-03 18:00","2022-06-03 09:00","2022-06-03 18:00","연속"]
[241,"부산울산","직할","신대연S/S #1 M.Tr","신대연S/S 종합예방진단시스템 설치공사","신대연S/S 종합예방진단시스템 설치공사 중 OLTC 상단 PD센서 설치를 위한 휴전 (단순 안전거리 이격 확보)","2022-06-02 09:00","2022-06-02 18:00","2022-06-02 09:00","2022-06-02 18:00","연속"]
[242,"경남","직할","신김해창원#1 T/L","신김해S/S 신김해-창원#1T/L 조작시험","7172(전자변교체),7100 조작시험 (병행)창원S/S 신김해-창원#1T/L 7171,7100 보통점검","2022-06-21 09:30","2022-06-21 17:30","2022-06-21 09:30","2022-06-21 17:30","연속"]
[243,"경남","진주","의령산청양수#2 T/L","산청P/P 의령-산청양수#2T/L(7200) GIS 정밀점검","[병행]산청P/P 7172GIS, PT(BC) 하자/보통점검, LA(ABC) 대체 [병행]의령S/S LA(ABC) 대체","2022-06-10 10:00","2022-06-17 18:00","2022-06-10 10:00","2022-06-17 18:00","연속"]
[244,"경남","진주","의령산청양수#1 T/L","산청P/P 의령-산청양수#1T/L(7100,7271) GIS 보통점검","[병행]산청P/P PT(ABC) 보통점검, LA(ABC) 대체 [병행]의령S/S PT(A) 초기점검, LA(ABC) 대체","2022-06-08 10:00","2022-06-09 18:00","2022-06-08 10:00","2022-06-09 18:00","연속"]
[245,"경남","진주","신남원의령#1 T/L","의령S/S #3M.Tr GIS 정밀점검(7872,6344) 시험가압선로","의령S/S #3M.Tr GIS 정밀점검(7872,6344) 시험가압선로","2022-06-05 10:00","2022-06-06 18:00","2022-06-05 10:00","2022-06-06 18:00","연속"]
[246,"경남","진주","의령S/S #3 M.Tr","의령S/S #3M.Tr 1차 GIS 정밀점검","[병행]의령S/S #3M.Tr 2차 GIS 정밀점검 [병행]의령S/S #3M.Tr 보통점검 등","2022-06-02 09:00","2022-06-06 18:00","2022-06-02 09:00","2022-06-06 18:00","연속"]
[247,"경남","통영","삼천포T/P #6호기 주변압기(CB 7600, 7671)","신고성S/S 345kV #G6호기 CVT 보통점검","신고성S/S 345kV #G6호기 CVT 보통점검","2022-06-02 10:00","2022-06-02 18:00","2022-06-09 10:00","2022-06-09 18:00","연속"]
[248,"경남","통영","삼천포T/P CB 7671","신고성S/S 345kV #G6호기 CVT 보통점검","신고성S/S 345kV #G6호기 CVT 보통점검","2022-06-02 10:00","2022-06-02 18:00","취소","취소","연속"]
[249,"경남","통영","신고성S/S #4 M.Tr","신고성S/S 345kV #4M.Tr 보통점검 등 6건","1. #4M.Tr 보통점검 2. 2차 GIS 조작시험 3. 3차 VCB 조작시험 4. 3차 PT 보통점검 5. 1,2,3차 LA 보통점검 6. 3차 DS 보통점검","2022-06-08 10:00","2022-06-09 18:00","2022-06-08 10:00","2022-06-09 18:00","연속"]
[250,"경남","통영","신고성S/S #1 M.Tr","신고성S/S #1M.Tr 2차 GIS 조작시험 등 4건","1. #1M.Tr 2차 GIS 조작시험 2. 3차 VCB 보통점검 3. #1-1Sh.R VCB 보통점검 4. #1-2Sh.R VCB 보통점검","2022-06-23 10:00","2022-06-24 18:00","2022-06-23 10:00","2022-06-24 18:00","연속"]
[251,"경남","통영","신고성S/S #3 M.Tr","신고성S/S #3M.Tr 2차 GIS 보통점검 및 전자변 교체 등 3건","1. #3M.Tr 2차 GIS 보통점검 및 전자변 교체 2. #3S.Tr C상 초기점검 3. #3S.Tr VCB 조작시험","2022-06-16 10:00","2022-06-16 18:00","2022-06-16 10:00","2022-06-16 18:00","연속"]
[252,"경남","함안","신옥천북경남 T/L","북경남S/S 345kV 신옥천-북경남T/L 단상재폐로 회로개선","북경남S/S 345kV 신옥천-북경남T/L 단상재폐로 회로개선","2022-06-08 09:00","2022-06-08 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[253,"경남","함안","북경남S/S #7 Sh.R CB","북경남S/S 345kV #7 Sh.R 7B79 GIS 정밀점검","북경남S/S 345kV #7 Sh.R 7B79 GIS 정밀점검","2022-06-20 09:00","2022-06-24 18:00","2022-06-20 09:00","2022-06-24 18:00","연속"]
[254,"경남","함안","북경남무주양수 T/L","북경남S/S 345kV 북경남-무주양수T/L 단상재폐로 회로개선","북경남S/S 345kV 북경남-무주양수T/L 단상재폐로 회로개선","2022-06-15 09:00","2022-06-15 18:00","2022-06-15 09:00","2022-06-15 18:00","연속"]
[255,"경남","함안","북경남S/S #6 Sh.R","북경남S/S 345kV #6 Sh.R 7979 GIS 정밀점검","북경남S/S 345kV #6 Sh.R 7979 GIS 정밀점검","2022-06-13 09:00","2022-06-17 18:00","2022-06-13 09:00","2022-06-17 18:00","연속"]
[256,"경남","함안","신마산신김해#1 T/L","345kV 신마산-신김해T/L 57~62호간 전선교체공사","57~62호간 전선교체","2022-06-02 07:00","2022-06-05 19:00","2022-06-02 07:00","2022-06-05 19:00","연속"]
[257,"경남","함안","신마산신김해#2 T/L","345kV 신마산-신김해T/L 57~62호간 전선교체공사","57~62호간 전선교체","2022-06-06 07:00","2022-06-09 19:00","2022-06-06 07:00","2022-06-09 19:00","연속"]
[258,"대구",null,"신월성N/P #2호기 주변압기 (CB 7100, 7172)","신월성 2호기 5차 계획예방정비, #2 MTR/UAT/EXTR 점검 * 조작차단기 : PCB 7100, 7172","○ MTR/UAT/EXTR 일반 점검 등","2022-06-22 09:00","2022-07-12 18:00","2022-06-22 09:00","2022-07-12 18:00","연속"]
[259,"경북",null,"신한울N/P #2호기 대기보조변압기(7200,7272)","보호계전기 연동시험","보호계전기 연동시험","2022-06-27 11:00","2022-07-01 11:00","2022-06-27 11:00","2022-07-01 11:00","연속"]
[260,"강원",null,"양양P/P #1호기 주변압기 (7100, 7172)","#1 UCB Operating Rod 측정","#1 UCB Operating Rod 측정","2022-06-14 09:00","2022-06-14 18:00","2022-06-14 09:00","2022-06-14 18:00","연속"]
[261,"강원",null,"양양P/P #4호기 주변압기 (7300, 7372)","#4 수차발전기 정기검사 수검","#4 수차발전기 정기검사 수검","2022-06-15 09:00","2022-06-16 13:00","2022-06-15 09:00","2022-06-16 13:00","연속"]
[262,"전북",null,"무주P/P #1,2호기 주변압기 (7100, 7200)","자체기동 발전기 예비시험","자체기동 발전기 예비시험","2022-06-15 13:00","2022-06-15 15:00","2022-06-15 13:00","2022-06-15 15:00","연속"]
[263,"전북",null,"무주P/P #1,2호기 주변압기 (7100, 7200)","자체기동 발전기 예비시험","자체기동 발전기 예비시험","2022-06-20 13:00","2022-06-21 15:00","2022-06-20 13:00","2022-06-21 15:00","연속"]
[264,"전북",null,"무주P/P #1,2 호기 주변압기 (7100, 7200)","자체기동 발전기 정기시험","자체기동 발전기 정기시험","2022-06-23 14:00","2022-06-23 16:00","2022-06-23 14:00","2022-06-23 16:00","연속"]
[265,"강원",null,"양양P/P #3호기 주변압기 (7200, 7272)","#3 여자기용 변압기 교체","#3 여자기용 변압기 교체","2022-06-27 09:00","2022-06-28 22:00","2022-06-27 09:00","2022-06-28 22:00","연속"]
[266,"강원",null,"양양P/P #2호기 주변압기 (7200, 7271)","#2 주변압기 점검","#2 주변압기 점검","2022-06-28 09:00","2022-06-30 22:00","2022-06-28 09:00","2022-06-30 22:00","연속"]
[267,"강원",null,"양양P/P #4호기 주변압기 (7300, 7372)","#4 여자기용 변압기 교체","#4 여자기용 변압기 교체","2022-06-29 09:00","2022-06-30 22:00","2022-06-29 09:00","2022-06-30 22:00","연속"]

{"sheet":"154설비","index":2,"n_rows":496,"n_cols":11,"rows_kept":496,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 6월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","군자성수 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-06-24 14:00","2022-06-24 18:00","2022-06-24 14:00","2022-06-24 18:00","연속"]
[2,"서울","성동","미아S/S CB 6100","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-06-08 10:00","2022-06-08 18:00","2022-06-08 10:00","2022-06-08 18:00","연속"]
[3,"서울","성동","수유미아 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-06-09 10:00","2022-06-09 18:00","2022-06-09 10:00","2022-06-09 18:00","연속"]
[4,"서울","성동","원남미아#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-06-21 10:00","2022-06-21 17:00","2022-06-21 10:00","2022-06-21 17:00","연속"]
[5,"서울","성동","방학S/S #1 BUS","154kV 장암S/S 옥내화 건설공사","장암S/S 옥내화 건설공사 최초가압 - 용현장암#1T/L, 장암방학#2T/L","2022-06-29 09:00","2022-06-30 18:00","2022-06-29 09:00","2022-06-30 18:00","연속"]
[6,"서울","성동","성동휘경#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-06-20 14:00","2022-06-20 18:00","2022-06-20 14:00","2022-06-20 18:00","연속"]
[7,"서울","성동","창동S/S CB 6100","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-06-09 09:30","2022-06-09 18:00","2022-06-09 09:30","2022-06-09 18:00","연속"]
[8,"서울","중부","녹번세종로 T/L","OF케이블 절연유 채유 및 보충","OF케이블 절연유 분석시료 채취 및 절연유 보충","2022-06-14 09:30","2022-06-14 16:00","2022-06-14 09:30","2022-06-14 16:00","연속"]
[9,"서울","중부","원흥상암 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","원흥-상암T/L No.1~2(4기) 추락방지시설 설치공사","2022-06-27 07:30","2022-06-27 18:00","2022-06-27 07:30","2022-06-27 18:00","연속"]
[10,"서울","중부","중부용산#1 T/L","22년 중부PO 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2022-06-06 10:00","2022-06-10 17:00","2022-06-07 10:00","2022-06-08 17:00","연속"]
[11,"서울","중부","중부용산#2 T/L","22년 중부PO 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2022-06-13 10:00","2022-06-17 17:00","2022-06-16 10:00","2022-06-17 17:00","연속"]
[12,"서울","직할","현저서대문#1 T/L","22년 직할 변전협력 총액공사","-170kV PT 점검","2022-06-22 09:00","2022-06-22 18:00","2022-06-22 09:00","2022-06-22 18:00","연속"]
[13,"서울","직할","운니원남#2 T/L","22년 170kV GIS 정밀점검","-170kV GIS 정밀점검","2022-06-09 10:00","2022-06-10 18:00","2022-06-09 10:00","2022-06-10 18:00","연속"]
[14,"서울","직할","운니S/S #1 BUS","22년 170kV GIS 정밀점검","-170kV GIS 정밀점검 시험가압용","2022-06-14 10:00","2022-06-14 18:00","2022-06-14 10:00","2022-06-14 18:00","연속"]
[15,"서울","직할","옥인운니#1 T/L","22년 170kV GIS 정밀점검 공사","-170kV GIS 정밀점검","2022-06-15 10:00","2022-06-16 18:00","2022-06-15 10:00","2022-06-16 18:00","연속"]
[16,"서울","직할","옥인운니#2 T/L","22년 170kV GIS 정밀점검 공사","-170kV GIS 정밀점검","2022-06-20 10:00","2022-06-21 18:00","2022-06-20 10:00","2022-06-21 18:00","연속"]
[17,"서울","직할","운니원남#1 T/L","22년 170kV GIS 정밀점검 공사","-170kV GIS 정밀점검","2022-06-22 10:00","2022-06-23 18:00","2022-06-22 10:00","2022-06-23 18:00","연속"]
[18,"서울","직할","옥인운니#1 T/L","22년 170kV GIS 정밀점검","-BUSTIE 시험가압용","2022-06-14 10:00","2022-06-14 18:00","2022-06-14 10:00","2022-06-14 18:00","연속"]
[19,"서울","직할","종로서소문 T/L","22년 변전협력회사 총액공사","-170kV PT 보통점검","2022-06-24 10:00","2022-06-24 18:00","2022-06-24 10:00","2022-06-24 18:00","연속"]
[20,"남서울","강남","신양재신사#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검","2022-06-02 08:00","2022-06-03 18:00","2022-06-02 08:00","2022-06-03 18:00","연속"]
[21,"남서울","강남","신양재역삼#3 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검","2022-06-07 08:00","2022-06-10 18:00","2022-06-07 08:00","2022-06-10 18:00","연속"]
[22,"남서울","강남","교대이수#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 2M.TR 1차, 교대-이수#2T/L GIS - 무부하 : 60BUS, 65BUS, 교대이수#1T/L","2022-06-29 10:00","2022-06-29 12:00","2022-06-29 10:00","2022-06-29 12:00","연속"]
[23,"남서울","강남","교대이수#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : #1MTR 1차, 교대-이수#1T/L GIS - 무부하 : 60BUS, 65BUS, 교대이수#2T/L","2022-06-24 16:00","2022-06-24 18:00","2022-06-24 16:00","2022-06-24 18:00","연속"]
[24,"남서울","강남","교대이수#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : #1MTR 1차, 교대-이수#1T/L GIS - 무부하 : 60BUS, 65BUS, 교대이수#2T/L","2022-06-22 10:00","2022-06-22 12:00","2022-06-22 10:00","2022-06-22 12:00","연속"]
[25,"남서울","동서울","동서울가락#1 T/L","가락S/S 동서울-가락#1T/L 170kV GIS 정밀점검","2022년 동서울전력지사 170kV GIS 정밀점검","2022-06-20 09:00","2022-06-21 18:00","2022-06-20 09:00","2022-06-21 18:00","연속"]
[26,"남서울","동서울","강동S/S #1 BUS","강동S/S #3M.Tr 1차 170kV GIS 정밀점검 무부하가압","2022년 동서울전력지사 170kV GIS 정밀점검","2022-06-24 14:00","2022-06-24 18:00","취소","취소","연속"]
[27,"남서울","동서울","강동천호#2 T/L","강동SS 강동-천호2TL GIS 전자변교체,조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-06-09 09:00","2022-06-09 18:00","취소","취소","연속"]
[28,"남서울","동서울","강동S/S #2 BUS","강동S/S #4M.Tr 1차 170kV GIS 정밀점검 무부하가압","2022년 동서울전력지사 170kV GIS 정밀점검","2022-06-28 14:00","2022-06-28 18:00","취소","취소","연속"]
[29,"남서울","동서울","강동천호#1 T/L","강동SS 강동-천호1TL GIS 전자변교체,조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-06-08 09:00","2022-06-08 18:00","취소","취소","연속"]
[30,"남서울","동서울","신양재개포 T/L","154kV 신양재,도곡-개포T/L 지장이설공사","양재대로 구조개선 사업(지하차도 건설)에 따른 전력설비 이설 □ 사업구간 : 154kV 신양재-개포T/L J/B#20 ~ M/H#19 □ 주요공정 - 케이블 철거 : XLPE 2,000㎟, 1C-0.32km(기설전력구+관로) - 케이블 설치 : XLPE 2,000㎟, 1C-0.35km(신설전력구+관로) - 케이블 접속 : 2개소","2022-06-07 09:00","2022-06-30 18:00","취소","취소","연속"]
[31,"남서울","동서울","동남위례#1 T/L","동남S/S 6100 BUS-TIE 170kV GIS 정밀점검 무부하가압","2022년 동서울전력지사 170kV GIS 정밀점검","2022-06-05 14:00","2022-06-05 18:00","취소","취소","연속"]
[32,"남서울","동서울","동남수서 T/L","동남SS 동남-수서TL 170kV GIS 정밀점검","2022년 동서울전력지사 170kV GIS 정밀점검공사","2022-06-02 09:00","2022-06-04 18:00","취소","취소","연속"]
[33,"남서울","동서울","동남S/S #2 BUS","동남S/S #2M.Tr 1차 170kV GIS 정밀점검 무부하가압","2022년 동서울전력지사 170kV GIS 정밀점검","2022-06-14 14:00","2022-06-14 18:00","2022-06-14 14:00","2022-06-14 18:00","연속"]
[34,"남서울","동서울","동남S/S CB 6100","동남S/S 6100 BUS-TIE 170kV GIS 정밀점검","2022년 동서울전력지사 170kV GIS 정밀점검","2022-06-04 09:00","2022-06-05 18:00","2022-06-07 09:00","2022-06-08 18:00","연속"]
[35,"남서울","동서울","동남S/S #1 BUS","동남S/S #1M.Tr 1차 170kV GIS 정밀점검 무부하가압","2022년 동서울전력지사 170kV GIS 정밀점검","2022-06-10 14:00","2022-06-10 18:00","2022-06-10 14:00","2022-06-10 18:00","연속"]
[36,"남서울","동서울","동남위례#2 T/L","동남S/S 동남-위례#2T/L GIS 정기점검(법정정기검사)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-06-08 09:00","2022-06-08 18:00","2022-06-03 09:00","2022-06-03 18:00","연속"]
[37,"남서울","동서울","동남S/S CB 6100","동남S/S #1M.Tr 1차 170kV GIS 정밀점검 무부하가압","2022년 동서울전력지사 170kV GIS 정밀점검","2022-06-10 14:00","2022-06-10 18:00","2022-06-10 14:00","2022-06-10 18:00","연속"]
[38,"남서울","동서울","동남S/S CB 6100","동남S/S #2M.Tr 1차 170kV GIS 정밀점검 무부하가압","2022년 동서울전력지사 170kV GIS 정밀점검","2022-06-14 14:00","2022-06-14 18:00","2022-06-14 14:00","2022-06-14 18:00","연속"]
[39,"남서울","동서울","가락동남 T/L","동남SS 가락-동남TL 170kV GIS 정밀점검","2022년 동서울전력지사 170kV GIS 정밀점검공사","2022-06-07 09:00","2022-06-08 18:00","취소","취소","연속"]
[40,"남서울","동서울","동남S/S #1 BUS","동남S/S 6100 BUS-TIE 170kV GIS 정밀점검 무부하가압","2022년 동서울전력지사 170kV GIS 정밀점검","2022-06-04 09:00","2022-06-05 18:00","2022-06-07 09:00","2022-06-08 18:00","연속"]
[41,"남서울","동서울","동남위례#1 T/L","동남S/S 동남-위례#1T/L GIS 정기점검(법정정기검사)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-06-07 09:00","2022-06-07 18:00","2022-06-02 09:00","2022-06-02 18:00","연속"]
[42,"남서울","동서울","동서울가락#2 T/L","동서울,가락S/S 동서울-가락#2T/L 보호반대체공사","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-06-13 09:00","2022-06-17 18:00","2022-06-13 09:00","2022-06-17 18:00","연속"]
[43,"남서울","동서울","동서울송파#2 T/L","방음벽 설치를 위한 송전선로 인근 크레인 사용(한국도로공사 시행)","방음벽 설치를 위한 송전선로 인근 크레인 사용(한국도로공사 시행) - 154kV 동서울-송파T/L No.8~9 전력선 하단","2022-06-11 09:00","2022-06-12 18:00","2022-06-11 09:00","2022-06-12 18:00","연속"]
[44,"남서울","동서울","동서울송파#1 T/L","방음벽 설치를 위한 송전선로 인근 크레인 사용(한국도로공사 시행)","방음벽 설치를 위한 송전선로 인근 크레인 사용(한국도로공사 시행) - 154kV 동서울-송파T/L No.8~9 전력선 하단","2022-06-11 09:00","2022-06-12 18:00","2022-06-11 09:00","2022-06-12 18:00","연속"]
[45,"남서울","동서울","동서울송파#1 T/L","방음벽 설치를 위한 송전선로 인근 크레인 사용(한국도로공사 시행)","방음벽 설치를 위한 송전선로 인근 크레인 사용(한국도로공사 시행) - 154kV 동서울-송파T/L No.8~9 전력선 하단","2022-06-18 09:00","2022-06-19 18:00","2022-06-18 09:00","2022-06-19 18:00","연속"]
[46,"남서울","동서울","동서울송파#2 T/L","방음벽 설치를 위한 송전선로 인근 크레인 사용(한국도로공사 시행)","방음벽 설치를 위한 송전선로 인근 크레인 사용(한국도로공사 시행) - 154kV 동서울-송파T/L No.8~9 전력선 하단","2022-06-18 09:00","2022-06-19 18:00","2022-06-18 09:00","2022-06-19 18:00","연속"]
[47,"남서울","동서울","신장S/S CB 6100","신장SS 6100BT 휴전(#1,3M.Tr 점검을 위한 모선통합)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-06-22 09:00","2022-06-23 18:00","2022-06-22 09:00","2022-06-23 18:00","연속"]
[48,"남서울","동서울","위례S/S #61 BUS","위례S/S 170kV GIS 증설공사","170kV GIS x 2CCT 설치","2022-06-13 09:00","2022-06-20 09:00","2022-06-13 09:00","2022-06-20 09:00","연속"]
[49,"남서울","동서울","위례S/S CB 6200","위례S/S 170kV GIS 증설공사","170kV GIS x 2CCT 설치","2022-06-17 17:00","2022-06-20 09:00","2022-06-17 17:00","2022-06-20 09:00","연속"]
[50,"남서울","동서울","위례S/S #66 BUS","위례S/S 170kV GIS 증설공사","170kV GIS x 2CCT 설치","2022-06-20 09:00","2022-06-24 18:00","2022-06-20 09:00","2022-06-24 18:00","연속"]
[51,"남서울","동서울","위례S/S CB 6200","위례S/S 170kV GIS 증설공사","170kV GIS x 2CCT 설치","2022-06-23 17:00","2022-06-24 18:00","2022-06-23 17:00","2022-06-24 18:00","연속"]
[52,"남서울","동서울","강동풍납#1 T/L","풍납SS 강동-풍납1TL GIS 보통점검(강동 : 조작)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-06-02 09:00","2022-06-02 18:00","2022-06-09 09:00","2022-06-09 18:00","연속"]
[53,"남서울","동서울","강동풍납#2 T/L","풍납SS 강동-풍납2TL GIS 보통점검(강동 : 조작)","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-06-03 09:00","2022-06-03 18:00","2022-06-10 09:00","2022-06-10 18:00","연속"]
[54,"남서울","영등포","신광명광명#2 T/L","154kV 광명S/S 인출전력구 OF케이블 선종교체공사","선종교체 : OF/XLPE 2,000SQ 0.349km 교체(D) 이종 및 종단접속 12상 및 기타 부대공사","2022-06-02 08:00","2022-07-31 18:00","취소","취소","연속"]
[55,"남서울","영등포","구로S/S #1 BUS","구로인출전력구 OF케이블 선종교체공사","○ 공사구간 : 구로S/S ∼ M/H#25(3구간) ○ 대상선로 : 154kV 신문래-구로#1,2T/L ○ 선종 및 길이 : 154kV OF 1,200㎟ → XLPE 1,200㎟ 1.1km × 2C ○ 케이블포설 및 접속개소 : 6구간(2회선×3구간), 8개소(2회선 : 중간 6, 종단 2)","2022-06-02 09:00","2022-06-02 18:00","2022-06-02 09:00","2022-06-02 18:00","연속"]
[56,"남서울","영등포","시흥독산#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(154kV BUS-TIE GIS)","2022-06-24 13:00","2022-06-24 16:00","2022-06-24 13:00","2022-06-24 16:00","연속"]
[57,"남서울","영등포","시흥독산#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#4M.Tr 1차 GIS)","2022-06-15 09:00","2022-06-15 12:00","2022-06-15 09:00","2022-06-15 12:00","연속"]
[58,"남서울","영등포","시흥독산#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#3M.Tr 1차 GIS)","2022-06-10 13:00","2022-06-10 16:00","2022-06-10 13:00","2022-06-10 16:00","연속"]
[59,"남서울","영등포","시흥독산#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#2M.Tr 1차 GIS)","2022-06-08 13:00","2022-06-08 16:00","2022-06-08 13:00","2022-06-08 16:00","연속"]
[60,"남서울","영등포","시흥독산#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#1M.Tr 1차 GIS)","2022-06-04 09:00","2022-06-04 12:00","2022-06-04 09:00","2022-06-04 12:00","연속"]
[61,"남서울","영등포","독산대방#2 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 독산-대방#2T/L GIS 정밀점검","2022-06-20 09:00","2022-06-22 14:00","2022-06-20 09:00","2022-06-22 14:00","연속"]
[62,"남서울","영등포","독산대방#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 독산-대방#1T/L GIS 정밀점검","2022-06-15 14:00","2022-06-17 18:00","2022-06-15 14:00","2022-06-17 18:00","연속"]
[63,"남서울","영등포","대림독산 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 대림-독산T/L GIS 정밀점검","2022-06-11 09:00","2022-06-12 18:00","2022-06-11 09:00","2022-06-12 18:00","연속"]
[64,"남서울","영등포","구공독산 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 구공-독산T/L GIS 정밀점검","2022-06-04 14:00","2022-06-06 18:00","2022-06-04 14:00","2022-06-06 18:00","연속"]
[65,"남서울","영등포","신광명S/S SEC CB 65660","'22~23년 영등포P/O 변전협력회사 총액공사","65-66SEC 보통점검","2022-06-21 09:00","2022-06-21 18:00","2022-06-21 09:00","2022-06-21 18:00","연속"]
[66,"남서울","영등포","신광명S/S SEC CB 60610","'22~23년 영등포P/O 변전협력회사 총액공사","60-61-SEC 보통점검","2022-06-20 09:00","2022-06-20 18:00","2022-06-20 09:00","2022-06-20 18:00","연속"]
[67,"남서울","영등포","부천신정#1 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","154kV 부천-신정#1T/L 보통점검","2022-06-02 09:00","2022-06-02 18:00","2022-06-02 09:00","2022-06-02 18:00","연속"]
[68,"남서울","영등포","부천신정#2 T/L","'22~23년 영등포P/O 변전협력회사 총액공사","154kV 부천-신정#2T/L 보통점검","2022-06-03 09:00","2022-06-03 18:00","2022-06-03 09:00","2022-06-03 18:00","연속"]
[69,"남서울","영등포","고강화곡#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#2M.Tr 1차 GIS)","2022-06-10 13:00","2022-06-10 16:00","2022-06-10 13:00","2022-06-10 16:00","연속"]
[70,"남서울","영등포","화곡S/S #60 BUS","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#2M.Tr 1차 GIS)","2022-06-10 13:00","2022-06-10 16:00","2022-06-10 13:00","2022-06-10 16:00","연속"]
[71,"남서울","영등포","고강화곡#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#1M.Tr 1차 GIS)","2022-06-08 13:00","2022-06-08 16:00","2022-06-08 13:00","2022-06-08 16:00","연속"]
[72,"남서울","영등포","화곡마곡#2 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 화곡-마곡#2T/L 정밀점검","2022-06-25 09:00","2022-06-26 18:00","2022-06-25 09:00","2022-06-26 18:00","연속"]
[73,"남서울","영등포","화곡S/S CB 6100","영등포전력지사 154kV GIS 정밀점검공사","154kV #1BUS-TIE 정밀점검","2022-06-02 09:00","2022-06-03 18:00","2022-06-02 09:00","2022-06-03 18:00","연속"]
[74,"남서울","영등포","화곡마곡#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 화곡-마곡#1T/L 정밀점검","2022-06-18 09:00","2022-06-19 18:00","2022-06-18 09:00","2022-06-19 18:00","연속"]
[75,"남서울","영등포","중동화곡#2 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 중동-화곡#2T/L 정밀점검","2022-06-11 09:00","2022-06-12 18:00","2022-06-11 09:00","2022-06-12 18:00","연속"]
[76,"남서울","영등포","중동화곡#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 중동-화곡#1T/L 정밀점검","2022-06-04 09:00","2022-06-05 18:00","2022-06-04 09:00","2022-06-05 18:00","연속"]
[77,"남서울","영등포","고강화곡#2 T/L","영등포전력지사 154kV GIS 정밀점검공사","- 화곡S/S 154kV 고강-화곡#2T/L GIS 정밀점검","2022-06-02 09:00","2022-06-04 18:00","2022-06-02 09:00","2022-06-04 18:00","연속"]
[78,"남서울","영등포","고강화곡#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#3M.Tr 1차 GIS)","2022-06-14 13:00","2022-06-14 16:00","2022-06-14 13:00","2022-06-14 16:00","연속"]
[79,"남서울","영등포","화곡S/S #60 BUS","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#3M.Tr 1차 GIS)","2022-06-14 13:00","2022-06-14 16:00","2022-06-14 13:00","2022-06-14 16:00","연속"]
[80,"남서울","영등포","화곡S/S #60 BUS","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#4M.Tr 1차 GIS)","2022-06-16 13:00","2022-06-16 16:00","2022-06-16 13:00","2022-06-16 16:00","연속"]
[81,"남서울","영등포","고강화곡#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#4M.Tr 1차 GIS)","2022-06-16 13:00","2022-06-16 16:00","2022-06-16 13:00","2022-06-16 16:00","연속"]
[82,"남서울","영등포","화곡S/S #60 BUS","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#1M.Tr 1차 GIS)","2022-06-08 13:00","2022-06-08 16:00","2022-06-08 13:00","2022-06-08 16:00","연속"]
[83,"남서울","직할","봉천신길#2 T/L","170kV GIS 보통점검공사","170kV GIS 보통점검공사","2022-06-07 09:00","2022-06-07 18:00","2022-06-07 09:00","2022-06-07 18:00","연속"]
[84,"남서울","직할","신림봉천 T/L","'21-'22년 지중송전 정비전문회사 총액공사","○ 작 업 명 : 절연유 채유 ○ 작업개소 : 신림EBG, SJ, M/H#15-1 ○ 작업내용 : 절연유 채유 및 열화분석","2022-06-27 09:00","2022-06-27 18:00","취소","취소","연속"]
[85,"남서울","직할","신문래양평#1 T/L","170kV GIS 정밀점검공사(신문래-양평#1T/L)","170kV GIS 정밀점검공사(신문래-양평#1T/L)","2022-06-20 09:00","2022-06-21 18:00","2022-06-20 09:00","2022-06-21 18:00","연속"]
[86,"남서울","직할","신문래양평#2 T/L","170kV GIS 정밀점검공사(신문래-양평#2T/L)","170kV GIS 정밀점검공사(신문래-양평#2T/L)","2022-06-22 09:00","2022-06-23 18:00","2022-06-22 09:00","2022-06-23 18:00","연속"]
[87,"인천","시흥","신시흥#1S/S #65 BUS","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","2022-06-04 09:00","2022-06-05 16:00","2022-06-04 09:00","2022-06-05 16:00","연속"]
[88,"인천","시흥","신시흥#1S/S CB 6100","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","시험가압","2022-06-05 15:00","2022-06-05 16:00","2022-06-05 15:00","2022-06-05 16:00","연속"]
[89,"인천","시흥","신시흥#1S/S #60 BUS","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","2022-06-05 16:00","2022-06-11 15:00","2022-06-05 16:00","2022-06-11 15:00","연속"]
[90,"인천","시흥","신시흥#1S/S CB 6100","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","60BUS 무부하가압","2022-06-10 15:00","2022-06-11 15:00","2022-06-10 15:00","2022-06-11 15:00","연속"]
[91,"인천","시흥","신시흥#1S/S #65 BUS","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","2022-06-11 15:00","2022-06-22 12:00","2022-06-11 15:00","2022-06-22 12:00","연속"]
[92,"인천","시흥","신시흥#1S/S #60 BUS","신시흥#1S/S 345kV #2M.Tr 2차 GIS대체공사","실부하가압","2022-06-22 12:00","2022-06-22 18:00","2022-06-22 12:00","2022-06-22 18:00","연속"]
[93,"인천","김포","경서양촌#1 T/L","154kV 경서-양촌#1T/L 경서C/T EBA 절연유 채유","154kV 경서-양촌#1T/L 경서C/T EBA 절연유 채유 - 공사대상 : EBA 6상","2022-06-26 09:00","2022-06-28 16:00","2022-06-26 09:00","2022-06-28 16:00","연속"]
[94,"인천","김포","경서양촌#2 T/L","154kV 경서-양촌#2T/L 경서C/T EBA 절연유 채유","154kV 경서-양촌#2T/L 경서C/T EBA 절연유 채유 - 공사대상 : EBA 6상","2022-06-28 13:00","2022-06-30 18:00","2022-06-28 13:00","2022-06-30 18:00","연속"]
[95,"인천","부평","신가좌S/S CB 6100","신가좌S/S 6100 BUS TIE GIS 조작시험 및 보조계전기 교체","신가좌S/S 6100 BUS TIE GIS 조작시험 및 보조계전기 교체","2022-06-02 09:00","2022-06-02 18:00","2022-06-02 09:00","2022-06-02 18:00","연속"]
[96,"인천","부평","신경서영종 T/L","신경서영종T/L 보호반 성능개선(계통시험)","신경서영종T/L 보호반 성능개선(계통시험)","2022-06-02 09:00","2022-06-02 18:00","2022-06-02 09:00","2022-06-02 18:00","연속"]
[97,"인천","부평","신가좌S/S CB 6200","신가좌S/S 6200 BUS TIE GIS 조작시험 및 보조계전기 교체","신가좌S/S 6200 BUS TIE GIS 조작시험 및 보조계전기 교체","2022-06-03 09:00","2022-06-03 18:00","2022-06-03 09:00","2022-06-03 18:00","연속"]
[98,"인천","부평","부흥부개#1 T/L","부흥부개#1 T/L 보호반 교체공사","부흥부개#1 T/L 보호반 교체공사 GIS 조작시험 및 전자변 교체","2022-06-04 09:00","2022-06-06 18:00","2022-06-04 09:00","2022-06-06 18:00","연속"]
[99,"인천","김포","왕길양촌#2 T/L","154kV 왕길S/S #4M.Tr GIS 설치공사","- 154kV GIS × 4CCT 설치 - 기타부대공사 × 1식","2022-06-07 08:00","2022-06-23 18:00","2022-06-07 08:00","2022-06-23 18:00","연속"]
[100,"인천","직할","갈산부흥#1 T/L","345kV 서인천-신부평 등 11개T/L 구형 SVL교체공사","구형 SVL 교체를 통한 난연성 확보 및 파급고장 예방","2022-06-07 09:00","2022-06-10 18:00","2022-06-07 09:00","2022-06-10 18:00","연속"]
[101,"인천","시흥","남동동춘 T/L","동춘S/S 154kV GIS 교체공사","○ 동춘S/S 154kV GIS 교체공사(6CCT 교체, 1CCT 철거) - 남동동춘T/L, #1,2,3M.Tr, BUS-TIE, PT&ES 교체 - 동춘#1T/L(운휴설비) 철거 - 기타부대공사 1식","2022-06-08 07:30","2022-07-05 18:00","2022-06-08 07:30","2022-07-05 18:00","연속"]
[102,"인천","부평","북인천원창 T/L","원창S/S 북인천원창T/L GIS 보통점검","원창S/S 북인천원창T/L GIS 보통점검","2022-06-08 09:00","2022-06-08 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[103,"인천","시흥","동춘S/S #1 BUS","동춘S/S 154kV GIS 교체공사","○ 동춘S/S 154kV GIS 교체공사(6CCT 교체, 1CCT 철거) - 남동동춘T/L, #1,2,3M.Tr, BUS-TIE, PT&ES 교체 - 동춘#1T/L(운휴설비) 철거 - 기타부대공사 1식","2022-06-11 15:00","2022-06-24 15:00","2022-06-11 15:00","2022-06-24 15:00","연속"]
[104,"인천","직할","고강화곡#1 T/L","고강S/S 고강화곡#1T/L GIS보통점검","고강S/S 고강화곡#1T/L GIS보통점검","2022-06-13 09:30","2022-06-13 18:00","2022-06-13 09:30","2022-06-13 18:00","연속"]
[105,"인천","김포","경서양촌#1 T/L","양촌S/S 170kV GIS 정밀점검 무부하 가압","양촌S/S 170kV #1M.Tr GIS 정밀점검 무부하 가압","2022-06-15 09:00","2022-06-15 18:00","2022-06-10 09:00","2022-06-10 18:00","연속"]
[106,"인천","김포","경서양촌#1 T/L","양촌S/S 170kV GIS 정밀점검 무부하 가압","양촌S/S 170kV #2M.Tr GIS 정밀점검 무부하 가압","2022-06-17 09:00","2022-06-17 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[107,"인천","부평","신가좌신현#1 T/L","신가좌, 신현S/S 신가좌신현#1T/L 보호반 교체공사","신가좌, 신현S/S 신가좌신현#1T/L 보호반 교체공사 신가좌측 GIS 조작시험, 전자변 및 보조계전기 교체","2022-06-20 09:00","2022-06-24 18:00","2022-06-20 09:00","2022-06-24 18:00","연속"]
[108,"인천","부평","신경서S/S CB 6200","신경서SS 6200GIS 보통점검","신경서SS 6200GIS 보통점검","2022-06-20 09:00","2022-06-20 18:00","2022-06-20 09:00","2022-06-20 18:00","연속"]
[109,"인천","부평","인천CC북인천#1 T/L","인천CC북인천#1T/L GIS 조작시험","인천CC북인천#1T/L GIS 조작시험","2022-06-21 09:00","2022-06-21 13:00","2022-06-21 09:00","2022-06-21 13:00","연속"]
[110,"인천","부평","인천CC북인천#2 T/L","인천CC북인천#2T/L GIS 조작시험","인천CC북인천#2T/L GIS 조작시험","2022-06-21 13:00","2022-06-21 18:00","2022-06-21 13:00","2022-06-21 18:00","연속"]
[111,"인천","부평","서인천CC신경서 T/L","서인천CC 서인천CC신경서 T/L GIS 보통점검","서인천CC 서인천CC신경서 T/L GIS 보통점검 -신경서측 GIS 보통 병행","2022-06-22 09:00","2022-06-22 18:00","2022-06-22 09:00","2022-06-22 18:00","연속"]
[112,"인천","김포","경서양촌#1 T/L","양촌S/S 170kV GIS 정밀점검 관련 무부하용","양촌S/S 170kV #3M.Tr 1차 GIS 정밀점검 무부하용","2022-06-22 16:00","2022-06-22 18:00","2022-06-03 09:00","2022-06-03 18:00","연속"]
[113,"인천","부평","신현송현#1 T/L","송현S/S 신현송현#1T/L GIS 보통점검","송현S/S 신현송현#1T/L GIS 보통점검","2022-06-23 09:00","2022-06-23 18:00","2022-06-25 09:00","2022-06-25 18:00","연속"]
[114,"인천","김포","경서양촌#1 T/L","양촌S/S 170kV GIS 정밀점검 관련 무부하용","양촌S/S 170kV 6100 TIE GIS 정밀점검 무부하용","2022-06-24 09:00","2022-06-24 18:00","2022-06-14 09:00","2022-06-14 18:00","연속"]
[115,"인천","시흥","동춘S/S #2 BUS","동춘S/S 154kV GIS 교체공사","○ 동춘S/S 154kV GIS 교체공사(6CCT 교체, 1CCT 철거) - 남동동춘T/L, #1,2,3M.Tr, BUS-TIE, PT&ES 교체 - 동춘#1T/L(운휴설비) 철거 - 기타부대공사 1식","2022-06-24 15:00","2022-07-04 18:00","2022-06-24 15:00","2022-07-04 18:00","연속"]
[116,"인천","김포","왕길양촌#1 T/L","154kV 왕길S/S #4M.Tr GIS 설치공사(무부하가압)","- 154kV GIS × 4CCT 설치 - 기타부대공사 × 1식","2022-06-24 18:00","2022-06-25 18:00","2022-06-24 18:00","2022-06-25 18:00","연속"]
[117,"인천","부평","신가좌신현#2 T/L","신가좌, 신현S/S 신가좌신현#2T/L 보호반 교체공사","신가좌, 신현S/S 신가좌신현#2T/L 보호반 교체공사 신가좌측 GIS 조작시험, 전자변 및 보조계전기 교체","2022-06-27 09:00","2022-07-01 18:00","2022-06-27 09:00","2022-07-01 18:00","연속"]
[118,"인천","김포","왕길양촌#2 T/L","154kV 양촌S/S S.W 신규수용공사","154kV 양촌S/S S.W 신규수용공사 - 김포열병합#1,2T/L 무부하가압","2022-06-30 10:00","2022-07-01 14:00","2022-06-30 10:00","2022-07-01 14:00","연속"]
[119,"경기북부","직할","신의정부용현#2 T/L","22-23 직할 변전협력 총액공사","170kV GIS 보통점검","2022-06-02 09:00","2022-06-02 18:00","2022-06-02 09:00","2022-06-02 18:00","연속"]
[120,"경기북부","구리","신포천S/S CB 6100","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-06-02 09:00","2022-06-02 14:00","2022-06-02 09:00","2022-06-02 14:00","연속"]
[121,"경기북부","고양","월롱금촌#1 T/L","대한전선제 열경화공법EBG 보강공사","금촌EBG 3상 스프링유니트 점검 및 채취밸브 설치","2022-06-02 09:00","2022-06-07 18:00","2022-06-02 09:00","2022-06-07 18:00","연속"]
[122,"경기북부","구리","신포천S/S CB 6200","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-06-02 14:00","2022-06-02 18:00","2022-06-02 14:00","2022-06-02 18:00","연속"]
[123,"경기북부","구리","미금S/S SEC CB 61620","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-06-03 09:00","2022-06-03 18:00","2022-06-03 09:00","2022-06-03 18:00","연속"]
[124,"경기북부","구리","진건S/S #61 BUS","진건S/S #4M.Tr 증설공사","진건S/S #4M.Tr용 개폐장치 증설 - 170kV GIS #1BUS측 조립 - 무부하 가압","2022-06-06 09:00","2022-06-08 18:00","2022-06-06 09:00","2022-06-08 18:00","연속"]
[125,"경기북부","직할","양주지축#2 T/L","고양전력지사 관내 송전철탑추락방지시설 설치공사","ㅇ 추락방지시설 설치","2022-06-07 07:00","2022-06-08 18:00","취소","취소","연속"]
[126,"경기북부","직할","양주은평#1 T/L","고양전력지사 관내 송전철탑추락방지시설 설치공사","ㅇ 추락방지시설 설치","2022-06-07 07:00","2022-06-08 18:00","취소","취소","연속"]
[127,"경기북부","고양","양주금촌#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","송전철탑 추락방지시설 설치(수평장치), 불량애자 교체","2022-06-07 07:00","2022-06-10 18:00","2022-06-07 07:00","2022-06-10 18:00","연속"]
[128,"경기북부","직할","신의정부용현#1 T/L","22-23 직할 변전협력 총액공사","170kV GIS 보통점검","2022-06-07 09:00","2022-06-07 18:00","2022-06-07 09:00","2022-06-07 18:00","연속"]
[129,"경기북부","고양","능곡상암#2 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2022-06-07 09:00","2022-06-07 18:00","2022-06-02 09:00","2022-06-02 18:00","연속"]
[130,"경기북부","구리","덕소진건#2 T/L","진건S/S #4M.Tr 증설공사","진건S/S #4M.Tr용 개폐장치 증설 - 시험가압선로(#61BUS)","2022-06-07 09:00","2022-06-08 18:00","2022-06-07 09:00","2022-06-08 18:00","연속"]
[131,"경기북부","구리","미금S/S SEC CB 66670","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-06-07 09:00","2022-06-07 18:00","2022-06-07 09:00","2022-06-07 18:00","연속"]
[132,"경기북부","고양","능곡상암#1 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2022-06-03 09:00","2022-06-03 18:00","2022-06-03 09:00","2022-06-03 18:00","연속"]
[133,"경기북부","직할","양주지축#1 T/L","고양전력지사 관내 송전철탑추락방지시설 설치공사","ㅇ 추락방지시설 설치","2022-06-09 07:00","2022-06-10 18:00","취소","취소","연속"]
[134,"경기북부","고양","일산지도#2 T/L","고양전력지사 관내 송전철탑추락방지시설 설치공사","ㅇ 추락방지시설 설치","2022-06-09 07:00","2022-06-10 18:00","취소","취소","연속"]
[135,"경기북부","고양","고양일산#2 T/L","고양전력지사 관내 송전철탑추락방지시설 설치공사","ㅇ 추락방지시설 설치","2022-06-09 07:00","2022-06-10 18:00","취소","취소","연속"]
[136,"경기북부","직할","양주은평#2 T/L","고양전력지사 관내 송전철탑추락방지시설 설치공사","ㅇ 추락방지시설 설치","2022-06-09 07:00","2022-06-10 18:00","취소","취소","연속"]
[137,"경기북부","구리","신포천포천#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치 (수평1회선)","2022-06-09 07:30","2022-06-14 18:00","2022-06-13 07:30","2022-06-16 18:00","연속"]
[138,"경기북부","직할","신의정부S/S SEC CB 61620","22-23 직할 변전협력 총액공사","170kV GIS 보통점검","2022-06-09 09:00","2022-06-09 18:00","2022-06-09 09:00","2022-06-09 18:00","연속"]
[139,"경기북부","구리","진건S/S #66 BUS","진건S/S #4M.Tr 증설공사","진건S/S #4M.Tr용 개폐장치 증설 - 170kV GIS #66BUS측 조립 - 무부하 가압","2022-06-09 09:00","2022-06-11 18:00","2022-06-09 09:00","2022-06-11 18:00","연속"]
[140,"경기북부","구리","덕소진건#2 T/L","진건S/S #4M.Tr 증설공사","진건S/S #4M.Tr용 개폐장치 증설 - 시험가압선로(#66BUS)","2022-06-10 09:00","2022-06-11 18:00","2022-06-10 09:00","2022-06-11 18:00","연속"]
[141,"경기북부","고양","신덕은문산#1 T/L","2022년 가공송전 순시점검 위탁공사","정밀점검","2022-06-13 08:00","2022-06-17 17:00","2022-06-13 08:00","2022-06-17 17:00","연속"]
[142,"경기북부","고양","문산월롱#1 T/L","2022년 가공송전 순시점검 위탁공사","휴작작업 병가선로","2022-06-13 08:00","2022-06-17 17:00","2022-06-13 08:00","2022-06-17 17:00","연속"]
[143,"경기북부","고양","일산호수#2 T/L","대한전선제 열경화공법EBG 보강공사","호수EBG 3상 스프링유니트 점검 및 채취밸브 설치","2022-06-13 09:00","2022-06-15 18:00","2022-06-13 09:00","2022-06-15 18:00","연속"]
[144,"경기북부","구리","지제S/S CB 6100","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-06-13 09:00","2022-06-13 18:00","2022-06-13 09:00","2022-06-13 18:00","연속"]
[145,"경기북부","구리","신포천동두천#1 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치 (수평1회선)","2022-06-14 07:30","2022-06-16 18:00","2022-06-16 07:30","2022-06-20 18:00","연속"]
[146,"경기북부","직할","신의정부S/S SEC CB 66670","22-23 직할 변전협력 총액공사","170kV GIS 보통점검","2022-06-14 09:00","2022-06-14 18:00","2022-06-14 09:00","2022-06-14 18:00","연속"]
[147,"경기북부","구리","운천전곡#1 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검, AIR 누기보수","2022-06-14 09:00","2022-06-14 18:00","2022-06-14 09:00","2022-06-14 18:00","연속"]
[148,"경기북부","구리","운천전곡#2 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검, AIR 누기보수","2022-06-15 09:00","2022-06-15 18:00","2022-06-15 09:00","2022-06-15 18:00","연속"]
[149,"경기북부","고양","일산지도#1 T/L","고양전력지사 관내T/L OPGW 항공장애표시구 설치공사 2차","154kV 일산-지도#1T/L 1경간 3개 항공구 설치","2022-06-17 07:00","2022-06-17 18:00","2022-06-17 07:00","2022-06-17 18:00","연속"]
[150,"경기북부","구리","청평H/P #4 M.Tr CB","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-06-17 09:00","2022-06-17 18:00","2022-06-17 09:00","2022-06-17 18:00","연속"]
[151,"경기북부","직할","옥정동두천#2 T/L","154kV 옥정S/S #3M.Tr 증설공사","- M.Tr, GIS, EGIS 시험가압선로","2022-06-17 09:00","2022-06-20 18:00","2022-06-17 09:00","2022-06-20 18:00","연속"]
[152,"경기북부","직할","옥정S/S #2 BUS","154kV 옥정S/S #3M.Tr 증설공사","154kV 옥정S/S #3M.Tr 증설공사 - 170kV GIS #2BUS측 준공시험 - M.Tr, GIS, EGIS 무부하가압","2022-06-17 09:00","2022-06-20 18:00","2022-06-17 09:00","2022-06-20 18:00","연속"]
[153,"경기북부","고양","문산월롱#2 T/L","2022년 가공송전 순시점검 위탁공사","휴작작업 병가선로","2022-06-20 08:00","2022-06-24 17:00","2022-06-20 08:00","2022-06-24 17:00","연속"]
[154,"경기북부","고양","신덕은문산#2 T/L","2022년 가공송전 순시점검 위탁공사","정밀점검","2022-06-20 08:00","2022-06-24 17:00","2022-06-20 08:00","2022-06-24 17:00","연속"]
[155,"경기북부","구리","용정포천#2 T/L","154kV 포천S/S 옥내화 토건공사","건축공사관련 철골설치","2022-06-20 09:00","2022-07-01 18:00","2022-06-21 09:00","2022-07-01 18:00","연속"]
[156,"경기북부","고양","덕이호수#2 T/L","덕이S/S 154kV #3M.Tr 공장입고수리 관련 무부하가압","덕이S/S 154kV #3M.Tr 제작사 공장입고수리 및 설치 후 무부하가압","2022-06-20 10:00","2022-06-21 10:00","2022-06-02 10:00","2022-06-03 10:00","연속"]
[157,"경기북부","고양","덕이S/S #2 BUS","덕이S/S 154kV #3M.Tr 공장입고수리 관련 무부하가압","덕이S/S 154kV #3M.Tr 제작사 공장입고수리 및 설치 후 무부하가압","2022-06-20 10:00","2022-06-21 10:00","2022-06-02 10:00","2022-06-03 10:00","연속"]
[158,"경기북부","직할","용현도봉#2 T/L","154kV 장암S/S 옥내화 건설공사","용현S/S 용현도봉#2T/L 송전선로 보호반 대체","2022-06-21 09:00","2022-06-29 09:00","취소","취소","연속"]
[159,"경기북부","고양","신파주S/S CB 6200","345kV 신파주S/S #4M.Tr 증설공사","가. 345kV 단상단권변압기(345/161/23kV 단상, 166.7MVA) x 3대 (현대) 나. 362kV GIS(4000A, 50kA, GIB 포함) x 1CB (현대) 다. 170kV GIS(2000A, 50kA, GIB 포함) x 1CCT (효성) 라. 보호배전반 x 1식 마. 기타 부대공사 x 1식","2022-06-23 09:00","2022-06-24 18:00","2022-06-23 09:00","2022-06-24 18:00","연속"]
[160,"경기북부","고양","신파주S/S #61 BUS","345kV 신파주S/S #4M.Tr 증설공사","가. 345kV 단상단권변압기(345/161/23kV 단상, 166.7MVA) x 3대 (현대) 나. 362kV GIS(4000A, 50kA, GIB 포함) x 1CB (현대) 다. 170kV GIS(2000A, 50kA, GIB 포함) x 1CCT (효성) 라. 보호배전반 x 1식 마. 기타 부대공사 x 1식","2022-06-23 09:00","2022-06-24 18:00","2022-06-23 09:00","2022-06-24 18:00","연속"]
[161,"경기북부","직할","별내도봉 T/L","154kV 장암S/S 옥내화관련 인출선로 정비공사","케이블타워 2기 설치, 산형강철탑 1기 보강 등","2022-06-25 09:00","2022-06-26 18:00","2022-06-25 09:00","2022-06-26 18:00","연속"]
[162,"경기북부","고양","월롱금촌#2 T/L","대한전선제 열경화공법EBG 보강공사","금촌EBG 3상 스프링유니트 점검 및 채취밸브 설치","2022-06-27 09:00","2022-06-29 18:00","2022-06-27 09:00","2022-06-29 18:00","연속"]
[163,"경기북부","직할","옥정동두천#2 T/L","154kV 옥정S/S #3M.Tr 증설공사","- M.Tr, GIS, EGIS 시험가압선로","2022-06-27 09:00","2022-06-28 18:00","2022-06-27 09:00","2022-06-28 18:00","연속"]
[164,"경기북부","직할","옥정S/S #1 BUS","154kV 옥정S/S #3M.Tr 증설공사","154kV 옥정S/S #3M.Tr 증설공사 - 170kV GIS #1BUS측 시험 - M.Tr, GIS, EGIS 무부하가압","2022-06-27 09:00","2022-06-28 18:00","2022-06-27 09:00","2022-06-28 18:00","연속"]
[165,"경기북부","직할","신의정부용현#2 T/L","154kV 장암S/S 옥내화 건설공사","장암S/S 옥내화 건설공사 최초가압 - 신의정부용현#2T/L 활용, 장암S/S 최초가압","2022-06-29 09:00","2022-06-30 18:00","취소","취소","연속"]
[166,"경기북부","직할","용현S/S #2 BUS","154kV 장암S/S 옥내화 건설공사","장암S/S 옥내화 건설공사 최초가압 - 용현장암#2T/L, 장암방학#2T/L","2022-06-29 09:00","2022-06-30 18:00","취소","취소","연속"]
[167,"경기북부","직할","용현도봉#2 T/L","154kV 장암S/S 옥내화 건설공사","장암S/S 옥내화 건설공사 최초가압 - 용현장암#2T/L, 장암방학#1T/L - 최초가압 후 전기안전공사 사용전검사 - 실부하가압","2022-06-29 09:00","2022-07-01 18:00","2022-06-29 09:00","2022-07-01 18:00","연속"]
[168,"경기북부","직할","도봉방학#1 T/L","154kV 장암S/S 옥내화 건설공사","장암S/S 옥내화 건설공사 최초가압 - 용현장암#2T/L, 장암방학#1T/L - 최초가압 후 전기안전공사 사용전검사 - 실부하가압","2022-06-29 09:00","2022-07-01 18:00","2022-06-29 09:00","2022-07-01 18:00","연속"]
[169,"경기북부","구리","진건S/S #66 BUS","진건S/S #4M.Tr 증설공사","진건S/S #4M.Tr 증설공사 - M.Tr, GIS, SIS 무부하가압","2022-06-30 09:00","2022-07-02 18:00","2022-06-30 09:00","2022-07-02 18:00","연속"]
[170,"경기","군포","서서울남군포#1 T/L","남군포S/S 154kV 신규수용공사(현대모비스)","남군포S/S 154kV GIS 증설공사","2022-06-22 14:00","2022-06-23 14:00","2022-06-22 14:00","2022-06-23 14:00","연속"]
[171,"경기","군포","서서울남군포#1 T/L","남군포S/S 154kV 신규수용공사(현대모비스)","남군포S/S 154kV GIS 증설공사","2022-06-15 14:00","2022-06-16 14:00","2022-06-15 14:00","2022-06-16 14:00","연속"]
[172,"경기","군포","서서울#2서안양 T/L","서안양SS 6100 170kV GIS 무부하가압용","서안양SS 6100 170kV GIS 무부하가압용","2022-06-28 18:00","2022-06-28 20:00","2022-06-28 18:00","2022-06-28 20:00","연속"]
[173,"경기","군포","신안산성포#2 T/L","성포SS 성포-안산2TL 170kV GIS 무부하가압용","성포SS 성포-안산2TL 170kV GIS 무부하가압용","2022-06-23 16:00","2022-06-23 18:00","2022-06-23 16:00","2022-06-23 18:00","연속"]
[174,"경기","군포","신안산성포#1 T/L","성포SS 성포-안산1TL 170kV GIS 무부하가압용","성포SS 성포-안산1TL 170kV GIS 무부하가압용","2022-06-21 16:00","2022-06-21 18:00","2022-06-21 16:00","2022-06-21 18:00","연속"]
[175,"경기","군포","신안산성포#2 T/L","성포SS 2M.Tr 170kV GIS 무부하가압용","성포SS 2M.Tr 170kV GIS 무부하가압용","2022-06-14 16:00","2022-06-14 18:00","2022-06-14 16:00","2022-06-14 18:00","연속"]
[176,"경기","군포","신안산성포#3 T/L","성포SS 신안산-성포3TL 170kV GIS 정밀점검공사","성포SS 신안산-성포3TL 170kV GIS 정밀점검공사","2022-06-15 09:00","2022-06-16 18:00","2022-06-15 09:00","2022-06-16 18:00","연속"]
[177,"경기","군포","성포안산#2 T/L","성포SS 성포-안산2TL 170kV GIS 정밀점검공사","성포SS 성포-안산2TL 170kV GIS 정밀점검공사","2022-06-22 09:00","2022-06-23 18:00","2022-06-22 09:00","2022-06-23 18:00","연속"]
[178,"경기","군포","성포안산#1 T/L","성포SS 성포-안산1TL 170kV GIS 정밀점검공사","성포SS 성포-안산1TL 170kV GIS 정밀점검공사","2022-06-20 09:00","2022-06-21 18:00","2022-06-20 09:00","2022-06-21 18:00","연속"]
[179,"경기","군포","성포안산#1 T/L","성포SS 신안산-성포3TL 170kV GIS 무부하가압용","성포SS 신안산-성포3TL 170kV GIS 무부하가압용","2022-06-16 16:00","2022-06-16 18:00","2022-06-16 16:00","2022-06-16 18:00","연속"]
[180,"경기","군포","신안산성포#1 T/L","성포SS 6100 170kV GIS 무부하가압용","성포SS 6100 170kV GIS 무부하가압용","2022-06-25 16:00","2022-06-25 18:00","2022-06-25 16:00","2022-06-25 18:00","연속"]
[181,"경기","군포","신안산성포#2 T/L","신안산SS 신안산-성포2TL 170kV GIS 정밀점검공사","신안산SS 신안산-성포2TL 170kV GIS 정밀점검공사","2022-06-09 09:00","2022-06-10 18:00","2022-06-09 09:00","2022-06-10 18:00","연속"]
[182,"경기","군포","신안산성포#1 T/L","신안산SS 신안산-성포1TL 170kV GIS 정밀점검공사","신안산SS 신안산-성포1TL 170kV GIS 정밀점검공사","2022-06-07 09:00","2022-06-08 18:00","2022-06-07 09:00","2022-06-08 18:00","연속"]
[183,"경기","군포","안양평촌#2 T/L","안양SS 안양-평촌2TL GIS 보통점검","안양SS 안양-평촌2TL GIS 보통점검","2022-06-17 14:00","2022-06-17 18:00","2022-06-17 14:00","2022-06-17 18:00","연속"]
[184,"경기","군포","안양평촌#1 T/L","안양SS 안양-평촌1TL GIS 보통점검","안양SS 안양-평촌1TL GIS 보통점검","2022-06-17 09:00","2022-06-17 14:00","2022-06-17 09:00","2022-06-17 14:00","연속"]
[185,"경기","군포","일동S/S #2 BUS","일동SS 일동고속철2TL GIS 무부하가압용","일동SS 일동고속철2TL GIS 무부하가압용","2022-06-04 16:00","2022-06-04 18:00","2022-06-04 16:00","2022-06-04 18:00","연속"]
[186,"경기","동부","성현S/S CB 6100","22년 동부 변전정비협력공사","성현:6100(조작),6179(조작)","2022-06-07 09:30","2022-06-07 14:00","2022-06-07 09:30","2022-06-07 14:00","연속"]
[187,"경기","동부","곤지암초월#1 T/L","22년 동부 변전정비협력공사","초월:곤지암-초월#1T/L(보통,LA보통) 곤지암:곤지암-초월#1 A,B,C 피뢰기 대체 [곤지암-용문#1T/L 안전이격 휴전]","2022-06-02 06:30","2022-06-02 18:00","2022-06-02 06:30","2022-06-02 18:00","연속"]
[188,"경기","동부","곤지암용문#1 T/L","22년 동부 변전정비협력공사","초월:곤지암-초월#1T/L(보통,LA보통) 곤지암:곤지암-초월#1 A,B,C 피뢰기 대체 [곤지암-용문#1T/L 안전이격 휴전]","2022-06-02 09:30","2022-06-02 18:00","2022-06-02 09:30","2022-06-02 18:00","연속"]
[189,"경기","동부","중원야탑 T/L","22년 동부 변전정비협력공사","22년 동부 변전정비협력공사","2022-06-03 09:30","2022-06-03 18:00","2022-06-03 09:30","2022-06-03 18:00","연속"]
[190,"경기","성남","진위동탄#2 T/L","동탄S/S #4M.Tr 증설공사","- #4M.Tr 1차 GIS 무부하가압","2022-06-23 16:00","2022-06-24 16:00","2022-06-23 16:00","2022-06-24 16:00","연속"]
[191,"경기","성남","진위동탄#1 T/L","동탄S/S #4M.Tr 증설공사","- #4M.Tr 1차 GIS 무부하가압","2022-06-30 16:00","2022-07-01 16:00","2022-06-30 16:00","2022-07-01 16:00","연속"]
[192,"경기","성남","덕성남사#2 T/L"," 22-23년 경기직할 가공송전 협력회사 총액공사","추락방지시설 설치","2022-06-07 08:00","2022-06-15 18:00","2022-06-07 08:00","2022-06-15 18:00","연속"]
[193,"경기","성남","서안성남사#1 T/L"," 22-23년 경기직할 가공송전 협력회사 총액공사","추락방지시설 설치","2022-06-10 08:00","2022-06-15 18:00","취소","취소","매일"]
[194,"경기","성남","덕성남사#1 T/L"," 22-23년 경기직할 가공송전 협력회사 총액공사","추락방지시설 설치","2022-06-16 08:00","2022-06-24 18:00","2022-06-16 08:00","2022-06-24 18:00","연속"]
[195,"경기","성남","서안성남사#2 T/L"," 22-23년 경기직할 가공송전 협력회사 총액공사","추락방지시설 설치","2022-06-16 08:00","2022-06-21 18:00","취소","취소","매일"]
[196,"경기","성남","신성남S/S SEC CB 62630","22년 성남전력 GIS 보통점검 공사","- GIS 보통점검","2022-06-16 09:00","2022-06-16 14:00","2022-06-16 09:00","2022-06-16 14:00","연속"]
[197,"경기","성남","신성남S/S SEC CB 67680","22년 성남전력 GIS 보통점검 공사","- GIS 보통점검","2022-06-16 14:00","2022-06-16 18:00","2022-06-16 14:00","2022-06-16 18:00","연속"]
[198,"경기","성남","신성남S/S CB 6400","22년 성남전력 GIS 보통점검 공사","- GIS 보통점검","2022-06-14 09:00","2022-06-14 18:00","2022-06-14 09:00","2022-06-14 18:00","연속"]
[199,"경기","성남","신용인기흥#2 T/L","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2022-06-15 14:00","2022-06-17 18:00","2022-06-15 14:00","2022-06-17 18:00","연속"]
[200,"경기","성남","신용인기흥#1 T/L","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2022-06-13 09:00","2022-06-15 14:00","2022-06-13 09:00","2022-06-15 14:00","연속"]
[201,"경기","성남","신용인동백#2 T/L","22년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험 - 까치집 제거","2022-06-02 14:00","2022-06-02 18:00","2022-06-02 14:00","2022-06-02 18:00","연속"]
[202,"경기","성남","신용인동백#1 T/L","22년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험 - 까치집 제거","2022-06-02 09:00","2022-06-02 14:00","2022-06-02 09:00","2022-06-02 14:00","연속"]
[203,"경기","성남","신용인S/S #67 BUS","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검 무부하가압","2022-06-24 09:00","2022-06-24 18:00","2022-06-24 09:00","2022-06-24 18:00","연속"]
[204,"경기","성남","신용인기흥#2 T/L","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검 무부하가압","2022-06-24 09:00","2022-06-24 18:00","2022-06-24 09:00","2022-06-24 18:00","연속"]
[205,"경기","성남","신용인S/S SEC CB 66670","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2022-06-22 14:00","2022-06-24 18:00","2022-06-22 14:00","2022-06-24 18:00","연속"]
[206,"경기","성남","신용인S/S #62 BUS","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검 무부하가압","2022-06-22 09:00","2022-06-22 14:00","2022-06-22 09:00","2022-06-22 14:00","연속"]
[207,"경기","성남","신용인기흥#2 T/L","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검 무부하가압","2022-06-22 09:00","2022-06-22 14:00","2022-06-22 09:00","2022-06-22 14:00","연속"]
[208,"경기","성남","신용인S/S SEC CB 61620","22년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2022-06-20 09:00","2022-06-22 14:00","2022-06-20 09:00","2022-06-22 14:00","연속"]
[209,"경기","성남","모현용인#2 T/L","154kV 모현-용인T/L 지장철탑 이설공사","154kV 모현-용인T/L 16~18호 철탑 교체(임시선로 구성) 공사시행 : 요청자 직접시행","2022-06-13 00:08","2022-06-20 18:00","2022-06-13 08:00","2022-06-20 18:00","연속"]
[210,"경기","성남","모현용인#1 T/L","154kV 모현-용인T/L 지장철탑 이설공사","154kV 모현-용인T/L 16~18호 철탑 교체(임시선로 구성) 공사시행 : 요청자 직접시행","2022-06-21 08:00","2022-06-28 18:00","2022-06-21 08:00","2022-06-28 18:00","연속"]
[211,"경기","성남","신용인용인#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사 안전거리 확보(4회선 병가)","2022-06-30 08:00","2022-06-30 18:00","2022-06-30 08:00","2022-06-30 18:00","매일"]
[212,"경기","직할","화성S/S #61 BUS","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 상확인","2022-06-26 09:00","2022-06-26 13:00","2022-06-26 09:00","2022-06-26 13:00","연속"]
[213,"경기","직할","화성S/S #66 BUS","화성S/S 154kV 장기사용 GIS 교체공사","#2M.Tr 상확인","2022-06-26 13:00","2022-06-26 18:00","2022-06-26 13:00","2022-06-26 18:00","연속"]
[214,"경기","평택","고덕#2고덕 T/L","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사","2022-06-13 09:00","2022-06-17 18:00","취소","취소","연속"]
[215,"경기","평택","고덕#2동평택#2 T/L"," 345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사","2022-06-20 09:00","2022-06-24 18:00","취소","취소","연속"]
[216,"경기","평택","고덕#2동평택#2 T/L"," 고덕#2S/S 154kV 신규수용공사(에어퍼스트)"," 고덕#2S/S 154kV 신규수용공사(에어퍼스트) 무부하가압","2022-06-28 10:00","2022-06-29 10:00","2022-06-28 10:00","2022-06-29 10:00","연속"]
[217,"경기","평택","고덕동평택#1 T/L"," 22년 평택전력지사 변전협력회사 총액공사","고덕S/S, 동평택S/S 170kV 고덕-동평택#1T/L GIS 하자점검","2022-06-29 10:00","2022-06-29 18:00","2022-06-29 10:00","2022-06-29 18:00","연속"]
[218,"경기","평택","서안성S/S SEC CB 60610","22년 평택전력지사 변전협력회사 총액공사","서안성S/S 170kV 60-61 SEC GIS 보통점검","2022-06-07 10:00","2022-06-07 18:00","2022-06-07 10:00","2022-06-07 18:00","연속"]
[219,"경기","평택","서안성안성#2 T/L"," 22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사 안전거리 확보(4회선 병가)","2022-06-15 15:00","2022-06-15 18:00","취소","취소","연속"]
[220,"경기","평택","서안성안성#1 T/L"," 22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사 안전거리 확보(4회선 병가)","2022-06-16 08:00","2022-06-16 11:00","취소","취소","연속"]
[221,"경기","평택","소사벌안성 T/L","22년 평택전력지사 170kV GIS 정밀점검공사","소사벌S/S 170kV 소사벌-안성T/L GIS 정밀점검","2022-06-07 09:00","2022-06-09 18:00","2022-06-04 09:00","2022-06-06 18:00","연속"]
[222,"경기","평택","청북평택#1 T/L","22년 평택전력지사 변전협력회사 총액공사","평택S/S 154kV 청북-평택#1T/L GCB 보통점검","2022-06-02 10:00","2022-06-02 18:00","2022-06-02 10:00","2022-06-02 18:00","연속"]
[223,"경기","평택","평택TP평택CC#1 T/L","22년 평택전력지사 변전협력회사 총액공사","평택C/C 170kV 평택복합#1T/L GIS 조작시험","2022-06-07 10:00","2022-06-07 18:00","취소","취소","연속"]
[224,"경기","평택","평택TP평택CC#2 T/L","22년 평택전력지사 변전협력회사 총액공사","평택C/C 170kV 평택복합#2T/L GIS 조작시험","2022-06-08 10:00","2022-06-08 18:00","취소","취소","연속"]
[225,"강원","강릉","신양양양양#1 T/L","2022년 170kV GIS 정밀점검","2022년 170kV GIS 정밀점검 - 병행 : 신양양S/S LA 보통점검, 양양S/S 차단기 조작시험","2022-06-16 09:00","2022-06-18 18:00","2022-06-16 09:00","2022-06-18 18:00","연속"]
[226,"강원","강릉","신양양인제#1 T/L","2022년 170kV GIS 정밀점검 무부하가압","2022년 170kV BUSTIE GIS 정밀점검 무부하가압 (매일휴전) -14일 13~14시 -15일 17~18시","2022-06-14 13:00","2022-06-15 18:00","2022-06-14 13:00","2022-06-15 18:00","매일"]
[227,"강원","강릉","신양양양양#2 T/L","2022년 170kV GIS 정밀점검","2022년 170kV GIS 정밀점검 - 병행 : 신양양S/S LA 보통점검, 양양S/S 차단기 조작시험","2022-06-20 09:00","2022-06-22 18:00","2022-06-20 09:00","2022-06-22 18:00","연속"]
[228,"강원","강릉","강릉영동TP T/L","영동화력S/Y 디지털화(SA) 공사","RTU 제어, 감시, 계측 케이블 LID반으로 이설","2022-06-27 09:00","2022-06-29 18:00","2022-06-27 09:00","2022-06-29 18:00","연속"]
[229,"강원","강릉","동해영동TP T/L","영동화력S/Y 디지털화(SA) 공사","RTU 제어, 감시, 계측 케이블 LID반으로 이설","2022-06-20 09:00","2022-06-22 18:00","2022-06-20 09:00","2022-06-22 18:00","연속"]
[230,"강원","강릉","평창올림픽 T/L","2022~2023년 강릉전력지사 가공송전협력회사 총액공사","○ BC링크 철거 - 154kV 올림픽분기T/L No.1 ~ 154kV 횡계-평창T/L No.7","2022-06-24 07:00","2022-06-24 18:00","2022-06-14 07:00","2022-06-14 18:00","연속"]
[231,"강원","강릉","횡계평창 T/L","2022~2023년 강릉전력지사 가공송전협력회사 총액공사","○ BC링크 철거 - 154kV 횡계-평창#1T/L No.6~7","2022-06-23 07:00","2022-06-23 18:00","2022-06-13 07:00","2022-06-13 18:00","연속"]
[232,"강원","동해","동해강릉 T/L","2022년 가공송전선로 순시점검 위탁공사","산불경과지역 정밀점검","2022-06-23 08:00","2022-06-24 18:00","2022-06-23 08:00","2022-06-24 18:00","매일"]
[233,"강원","동해","동해정선 T/L","2022-23년 동해전력지사 송전협력회사 총액공사","전선접속개소 전선교체","2022-06-13 08:00","2022-06-19 18:00","2022-06-13 08:00","2022-06-19 18:00","연속"]
[234,"강원","동해","동해동영월 T/L","2022-23년 동해전력지사 송전협력회사 총액공사","전선접속개소 전선교체","2022-06-07 08:00","2022-06-12 18:00","2022-06-07 08:00","2022-06-12 18:00","연속"]
[235,"강원","원주","남원주원주#2 T/L","2022~2023년 원주전력지사 가공송전협력회사 총액공사","○ 추락방지장치(수직, 수평) ○ 송전선로용 피뢰기 설치","2022-06-13 08:00","2022-06-17 17:00","취소","취소","매일"]
[236,"강원","원주","남원주원주#1 T/L","2022~2023년 원주전력지사 가공송전협력회사 총액공사","○ 추락방지장치(수직, 수평)","2022-06-07 08:00","2022-06-10 17:00","취소","취소","매일"]
[237,"강원","원주","홍천소양강HP T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","154kV 남춘천-춘천T/L 전선교체시 안전확보를 위한 인접선로 휴전 (전력선 연선 시 인접선로 근접 우려)","2022-06-30 08:00","2022-07-01 18:00","2022-06-30 08:00","2022-07-01 18:00","연속"]
[238,"강원","원주","횡성홍천#2 T/L","2022~2023년 원주전력지사 송전협력회사 총액공사","수직, 수평 추락방지장치 설치","2022-06-24 08:30","2022-06-28 18:00","2022-06-24 08:30","2022-06-28 18:00","매일"]
[239,"강원","원주","홍천소양강HP T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","154kV 남춘천-춘천T/L 전선교체시 안전확보를 위한 인접선로 휴전 (전력선 연선 시 인접선로 근접 우려)","2022-06-03 08:00","2022-06-05 18:00","취소","취소","연속"]
[240,"강원","직할","남춘천춘천열병합#2 T/L","피뢰기 및 추락방지장치 설치공사","154kV 남춘천-춘천열병합#2T/L 추락방지장치 설치","2022-06-23 09:00","2022-06-23 15:00","2022-06-23 09:00","2022-06-23 15:00","연속"]
[241,"강원","직할","인제양구#2 T/L","2022년 상반기 직할 170kV GIS 정밀점검","2022년 상반기 직할 170kV GIS 정밀점검 - 양구S/S 154kV 인제-양구 #2T/L GIS 정밀점검","2022-06-15 14:30","2022-06-17 18:00","2022-06-15 14:30","2022-06-17 18:00","연속"]
[242,"강원","직할","철원화천#2 T/L","피뢰기 및 추락방지장치 설치공사","피뢰기설치 156(set), 수직수평추락방지장치 설치 51(기),아킹혼철거 156(set)","2022-06-02 08:00","2022-06-13 19:00","2022-06-02 08:00","2022-06-13 19:00","매일"]
[243,"강원","직할","철원화천#1 T/L","피뢰기 및 추락방지장치 설치공사","수평추락방지장치 설치 51(기)","2022-06-14 08:00","2022-06-20 19:00","2022-06-14 08:00","2022-06-20 19:00","매일"]
[244,"강원","직할","춘천북춘천#1 T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","154kV 남춘천-춘천T/L 전선교체에 따른 4회선 병가구간 안전작업을 위한 하단선로 휴전","2022-06-08 08:00","2022-06-29 18:00","2022-06-08 08:00","2022-06-26 18:00","연속"]
[245,"강원","직할","춘천소양강HP T/L","154kV 남춘천-춘천 등 2개T/L 용량증대 전선교체공사","154kV 남춘천-춘천T/L 전선교체시 안전확보를 위한 인접선로 휴전 (전력선 연선 시 인접선로 근접 우려)","2022-06-20 08:00","2022-06-22 18:00","2022-06-27 08:00","2022-06-29 18:00","연속"]
[246,"강원","직할","북춘천화천HP T/L","2022~2023년 강원본부 직할 변전협력회사 총액공사","LA 보통점검, DS(A,B,L)보통점검, Line EDS 교체, PT 보통점검, #65BUS CVT 대체, 차단기 조작시험","2022-06-07 10:00","2022-06-09 18:00","2022-06-07 10:00","2022-06-09 18:00","연속"]
[247,"강원","직할","화천화천HP#2 T/L","피뢰기 및 추락방지장치 설치공사","수평추락방지장치 설치 5(기)","2022-06-13 08:00","2022-06-13 19:00","2022-06-13 08:00","2022-06-13 19:00","연속"]
[248,"강원","직할","화천화천HP#1 T/L","피뢰기 및 추락방지장치 설치공사","수평추락방지장치 설치 5(기)","2022-06-20 08:00","2022-06-20 19:00","2022-06-20 08:00","2022-06-20 19:00","연속"]
[249,"강원","직할","화천화천HP#1 T/L","2022년 상반기 직할 170kV GIS 정밀점검","2022년 상반기 직할 170kV GIS 정밀점검 - 화천S/S 154kV 화천-화천HP #1T/L GIS 정밀점검","2022-06-20 09:00","2022-06-22 14:30","2022-06-27 09:00","2022-06-29 18:00","연속"]
[250,"강원","직할","화천화천HP#2 T/L","2022년 상반기 직할 170kV GIS 정밀점검","2022년 상반기 직할 170kV GIS 정밀점검 - 화천S/S 154kV 화천-화천HP #2T/L GIS 정밀점검","2022-06-22 14:30","2022-06-24 18:00","2022-06-22 14:30","2022-06-24 18:00","연속"]
[251,"강원","태백","동영월영월CC T/L","2022년 태백전력지사 변전협력회사 총액공사","154kV 동영월-영월CCT/L 보호반 교체 (병행) 154kV 동영월-영월CCT/L 송전선로 정밀점검(6/20~6/24)","2022-06-20 10:00","2022-06-24 18:00","2022-06-20 10:00","2022-06-24 18:00","연속"]
[252,"강원","태백","제천영월#1 T/L","2022년 태백전력지사 변전협력회사 총액공사","영월S/S 154kV 제천-영월#1T/L GIS 조작시험","2022-06-24 10:00","2022-06-24 18:00","2022-06-24 10:00","2022-06-24 18:00","연속"]
[253,"강원","태백","제천영월#2 T/L","2022년 태백전력지사 변전협력회사 총액공사","영월S/S 154kV 제천-영월#2T/L GIS 조작시험","2022-06-27 10:00","2022-06-27 18:00","2022-06-27 10:00","2022-06-27 18:00","연속"]
[254,"강원","태백","영월영월CC T/L","2022년 태백전력지사 변전협력회사 총액공사","영월S/S 154kV 영월-영월CCT/L GIS 조작시험","2022-06-28 10:00","2022-06-28 18:00","2022-06-28 10:00","2022-06-28 18:00","연속"]
[255,"강원","태백","고한영월 T/L","2022~2023년 태백전력지사 가공송전 협력회사 총액공사","154kV 고한-영월T/L 추락방지장치 설치","2022-06-20 09:00","2022-07-01 18:00","2022-06-20 09:00","2022-07-01 18:00","매일"]
[256,"강원","태백","영월S/S CB 6100","2022년 태백전력지사 변전협력회사 총액공사","영월S/S 154kV #1BUS-TIE GIS 조작시험","2022-06-29 10:00","2022-06-29 18:00","2022-06-29 10:00","2022-06-29 18:00","연속"]
[257,"강원","태백","태백삼척GP#2 T/L","2022년 태백전력지사 변전협력회사 총액공사","태백S/S 154kV 태백-삼척GP#2T/L GIS 보통점검 (병행)태백S/S 154kV 태백-삼척GP#2T/L LA 교체(06/12)","2022-06-26 09:00","2022-06-29 18:00","2022-06-26 09:00","2022-06-29 18:00","연속"]
[258,"충북","직할","신진천S/S SEC CB 65660","충북직할 변전협력회사 총액공사","154kV GIS 보통점검","2022-06-22 10:00","2022-06-22 18:00","2022-06-22 10:00","2022-06-22 18:00","연속"]
[259,"충북","직할","신진천오창#2 T/L","충북직할 변전협력회사 총액공사","154kV GIS 보통점검","2022-06-05 10:00","2022-06-05 18:00","2022-06-05 10:00","2022-06-05 18:00","연속"]
[260,"충북","직할","진천덕산#1 T/L","22년 직할 송전정비 협력회사 총액감사","추락방지시설 설치 27기 (주말제외, 매일)","2022-06-07 08:00","2022-06-17 18:00","취소","취소","매일"]
[261,"충북","직할","진천덕산#2 T/L","22년 직할 송전정비 협력회사 총액공사","추락방지시설 설치 27기 (주말제외, 매일)","2022-06-20 08:00","2022-06-30 18:00","취소","취소","매일"]
[262,"충북","청주","남청주죽림#1 T/L","170 GIS 초기점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 초기점검, 보통점검","2022-06-13 10:00","2022-06-13 18:00","2022-06-13 10:00","2022-06-13 18:00","연속"]
[263,"충북","청주","남청주죽림#2 T/L","170 GIS 초기점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 초기점검, 보통점검","2022-06-14 10:00","2022-06-14 18:00","2022-06-14 10:00","2022-06-14 18:00","연속"]
[264,"충북","청주","북청주봉명#1 T/L","2022년 청주전력지사 170kV GIS 정밀점검공사","북청주S/S 154kV 북청주봉명#1T/L GIS 정밀점검공사","2022-06-02 09:00","2022-06-03 18:00","2022-06-02 09:00","2022-06-03 18:00","연속"]
[265,"충북","청주","북청주봉명#2 T/L","2022년 청주전력지사 170kV GIS 정밀점검공사","북청주S/S 154kV 북청주봉명#2T/L GIS 정밀점검공사","2022-06-07 09:00","2022-06-08 18:00","2022-06-07 09:00","2022-06-08 18:00","연속"]
[266,"충북","청주","서청주사직#2 T/L","22-23년 청주전력지사 변전정비회사 총액공사","서청주,사직S/S 154kV 서청주사직#2T/L 보호반 대체","2022-06-11 09:00","2022-06-12 18:00","2022-06-11 09:00","2022-06-12 18:00","연속"]
[267,"충북","청주","신옥천S/S SEC CB 61620","154kV 170 GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 하자점검","2022-06-10 10:00","2022-06-10 18:00","2022-06-10 10:00","2022-06-10 18:00","연속"]
[268,"충북","청주","청주율량#1 T/L","170 GIS 초기점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 초기점검","2022-06-02 10:00","2022-06-02 18:00","2022-06-02 10:00","2022-06-02 18:00","연속"]
[269,"충북","청주","청주율량#2 T/L","170 GIS 초기점검","[22-23 청주전력 변전정비 총액공사] 154kV 170GIS 초기점검","2022-06-03 10:00","2022-06-03 18:00","2022-06-03 10:00","2022-06-03 18:00","연속"]
[270,"충북","충주","단양영월CC#1 T/L","단양S/S 154kV 장기사용 GIS 대체공사","○ GIS(170kV 50kA) × 14CCT 철거, 2CCT 재사용 철거 ○ GIS(170kV 50kA) × 17CCT 설치, 3CCT 개조 및 설치 ○ SA 혼용운영시스템 설치 × 1식 ○ 기타 부대공사(GIS 기초 및 보호배전반 설치 등) × 1식","2022-06-06 08:00","2022-06-06 18:00","2022-06-06 08:00","2022-06-06 18:00","연속"]
[271,"충북","충주","단양영월CC#2 T/L","154kV 제천-영월T/L 용량증대 전선교체공사","병가철탑 안전이격상 휴전","2022-06-07 08:00","2022-06-11 18:00","2022-06-07 08:00","2022-06-11 18:00","연속"]
[272,"충북","충주","신제천제천#2 T/L","154kV 신제천-제천T/L 용량증대 전선교체공사","154kV 신제천-제천T/L 용량증대 전선교체공사 1. 전선교체 : 37경간 (345kV 신제천S/S ~ 154kV 제천S/S) 2. 추락방지장치 설치 : 수직 10기, 수평36기 설치","2022-06-23 09:00","2022-07-08 18:00","2022-06-23 09:00","2022-07-08 18:00","연속"]
[273,"충북","충주","신제천왕암#1 T/L","154kV 신제천-제천T/L 용량증대 전선교체공사","154kV 신제천-제천T/L 용량증대 전선교체공사 1. 전선교체 : 37경간 (345kV 신제천S/S ~ 154kV 제천S/S) 2. 추락방지장치 설치 : 수직 10기, 수평36기 설치","2022-06-07 09:00","2022-06-22 18:00","2022-06-07 09:00","2022-06-22 18:00","연속"]
[274,"충북","충주","신제천제천#1 T/L","154kV 신제천-제천T/L 용량증대 전선교체공사","154kV 신제천-제천T/L 용량증대 전선교체공사 1. 전선교체 : 37경간 (345kV 신제천S/S ~ 154kV 제천S/S) 2. 추락방지장치 설치 : 수직 10기, 수평36기 설치","2022-06-07 09:00","2022-06-22 18:00","2022-06-07 09:00","2022-06-22 18:00","연속"]
[275,"충북","충주","신제천왕암#2 T/L","154kV 신제천-제천T/L 용량증대 전선교체공사","154kV 신제천-제천T/L 용량증대 전선교체공사 1. 전선교체 : 37경간 (345kV 신제천S/S ~ 154kV 제천S/S) 2. 추락방지장치 설치 : 수직 10기, 수평36기 설치","2022-06-23 09:00","2022-07-08 18:00","2022-06-23 09:00","2022-07-08 18:00","연속"]
[276,"충북","충주","신충주S/S #67 BUS","신충주S/S 154kV GIS 설치공사","#64 M.Tr 1차 + 재세능원#2 T/L + #7 Sh.C 용 GIS 설치","2022-06-06 09:00","2022-06-15 18:00","2022-06-06 09:00","2022-06-15 18:00","연속"]
[277,"충북","충주","신충주북충주#2 T/L","신충주S/S 154kV GIS 설치공사","#64 M.Tr 1차 + 재세능원#2 T/L + #7 Sh.C 용 GIS 설치 후 무부하가압","2022-06-14 13:00","2022-06-15 13:00","2022-06-14 13:00","2022-06-15 13:00","연속"]
[278,"충북","충주","신충주북충주#2 T/L","신충주S/S 154kV GIS 설치공사","#64 M.Tr 1차 + 재세능원#2 T/L + #7 Sh.C 용 GIS 설치 후 무부하가압","2022-06-17 13:00","2022-06-18 13:00","2022-06-17 13:00","2022-06-18 13:00","연속"]
[279,"충북","충주","신충주음성#2 T/L","신충주S/S 154kV GIS 설치공사","재세능원#1 T/L GIS 설치 관련 스페이서 설치","2022-06-18 09:00","2022-06-19 14:00","2022-06-18 09:00","2022-06-19 14:00","연속"]
[280,"충북","충주","신충주음성#1 T/L","신충주S/S 154kV GIS 설치공사","재세능원#1 T/L GIS 설치 관련 안전이격 확보 및 무부하가압 (즉시가압 가능)","2022-06-26 14:00","2022-06-29 18:00","2022-06-26 14:00","2022-06-29 18:00","연속"]
[281,"충북","충주","신충주음성#2 T/L","신충주S/S 154kV GIS 설치공사","재세능원#1 T/L GIS 설치 관련 스페이서 설치","2022-06-25 09:00","2022-06-26 14:00","2022-06-25 09:00","2022-06-26 14:00","연속"]
[282,"충북","충주","신충주북충주#2 T/L","신충주S/S 154kV GIS 설치공사","#64 M.Tr 무부하가압","2022-06-23 13:00","2022-06-24 13:00","2022-06-23 13:00","2022-06-24 13:00","연속"]
[283,"충북","충주","신충주음성#1 T/L","신충주S/S 154kV GIS 설치공사","재세능원#1 T/L GIS 설치 관련 안전이격 확보 및 무부하가압 (즉시가압 가능)","2022-06-19 14:00","2022-06-22 18:00","2022-06-19 14:00","2022-06-22 18:00","연속"]
[284,"충북","충주","북충주충주 T/L","154kV 왕암-충주 등 2개T/L 압축인류클램프 정비공사","154kV 북충주-충주 TL 압축인류클램프 정비공사(주말작업없음)","2022-06-24 07:00","2022-06-29 18:00","2022-06-24 07:00","2022-06-29 18:00","매일"]
[285,"충북","충주","충주충주HP#2 T/L","154kV 왕암-충주 등 2개T/L 압축인류클램프 정비공사","154kV 충주-충주H/P#2TL 압축인류클램프 정비공사(주말작업없음)","2022-06-10 09:00","2022-06-16 18:00","2022-06-10 09:00","2022-06-16 18:00","매일"]
[286,"충북","충주","충주충주HP#1 T/L","154kV 왕암-충주 등 2개T/L 압축인류클램프 정비공사","154kV 충주-충주H/P#1TL 압축인류클램프 정비공사(주말작업없음)","2022-06-02 09:00","2022-06-09 18:00","2022-06-02 09:00","2022-06-09 18:00","매일"]
[287,"대전세종충남","대전","가수원대전서남부#1 T/L","가수원S/S 170kV LH열병합T/L GIS 보통점검","가수원S/S 170kV LH열병합T/L GIS 보통점검","2022-06-09 09:00","2022-06-09 18:00","2022-06-09 09:00","2022-06-09 18:00","연속"]
[288,"대전세종충남","대전","금산무주#1 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 금산-무주T/L 추락방지시설 설치공사","2022-06-30 08:00","2022-07-01 18:00","2022-06-30 08:00","2022-07-01 18:00","매일"]
[289,"대전세종충남","대전","팔봉두마#2 T/L","두마S/S 170kV 팔봉-두마#2T/L GIS 보통점검","두마S/S 170kV 팔봉-두마#2T/L GIS 보통점검","2022-06-08 09:00","2022-06-08 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[290,"대전세종충남","대전","팔봉두마#1 T/L","두마S/S 170kV 팔봉-두마#1T/L GIS 보통점검","두마S/S 170kV 팔봉-두마#1T/L GIS 보통점검","2022-06-07 09:00","2022-06-07 18:00","2022-06-07 09:00","2022-06-07 18:00","연속"]
[291,"대전세종충남","대전","신옥천서대전 T/L","[송전] 154kV 가수원-서대전 등 6개T/L 피뢰기 설치공사","[송전] 154kV 가수원-서대전T/L 피뢰기 설치공사 안전이격 확보","2022-06-07 08:00","2022-06-07 18:00","2022-06-07 08:00","2022-06-07 18:00","연속"]
[292,"대전세종충남","대전","은진함열#2 T/L","[송전] 154kV 가수원-서대전 등 6개T/L 피뢰기 설치공사","[송전] 154kV 은진-함열#2T/L 피뢰기 설치공사","2022-06-08 08:00","2022-06-13 18:00","2022-06-09 08:00","2022-06-13 18:00","매일"]
[293,"대전세종충남","대전","추부금산#1 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 추부-금산T/L 추락방지시설 설치공사","2022-06-16 08:00","2022-07-01 18:00","2022-06-16 08:00","2022-07-01 18:00","매일"]
[294,"대전세종충남","서산","서산성연 T/L","서산, 성연S/S 154kV 서산-성연T/L 보호반 대체","서산, 성연S/S 154kV 서산-성연T/L 보호반 대체 (병행) 서산S/S 154kV 서산-성연T/L 가스누기 보수공사","2022-06-25 09:00","2022-06-27 18:00","2022-06-04 09:00","2022-06-06 18:00","연속"]
[295,"대전세종충남","서산","합덕송악#1 T/L","22년 서산P/O 154kV GIS 정밀점검 공사","송악S/S 154kV 합덕-송악#1T/L 6F7 GIS 정밀점검","2022-06-20 09:00","2022-06-22 14:00","취소","취소","연속"]
[296,"대전세종충남","서산","합덕송악#2 T/L","22년 서산P/O 154kV GIS 정밀점검 공사","22년 서산P/O 154kV GIS 정밀점검 공사","2022-06-22 14:00","2022-06-24 18:00","취소","취소","연속"]
[297,"대전세종충남","서산","합덕송악#1 T/L","154kV 합덕S/S #3M.Tr 증설공사","154kV 합덕S/S #3M.Tr 증설공사 무부하가압","2022-06-29 10:00","2022-06-30 11:30","2022-06-29 10:00","2022-06-30 11:30","연속"]
[298,"대전세종충남","세종","천안전의#2 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","○154kV GIS 보통점검 -LA 보통점검 병행","2022-06-16 09:00","2022-06-16 18:00","2022-06-16 09:00","2022-06-16 18:00","연속"]
[299,"대전세종충남","세종","서세종조치원 T/L","[변전]2022년 세종P/O 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2022-06-13 09:30","2022-06-13 18:00","2022-06-13 09:30","2022-06-13 18:00","연속"]
[300,"대전세종충남","직할","대덕둔지 T/L","[변전]직할 변전협력회사 총액공사","대덕S/S 170kV GIS 보통점검","2022-06-08 09:00","2022-06-08 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[301,"대전세종충남","직할","대화둔산#2 T/L","22년 직할 170kV GIS 정밀점검 공사","22년 직할 170kV GIS 정밀점검 공사","2022-06-09 09:00","2022-06-10 18:00","2022-06-09 09:00","2022-06-10 18:00","연속"]
[302,"대전세종충남","직할","동대전신탄진#2 T/L","[송전] 154kV 동대전-신탄진T/L 철탑 추락방지장치 설치공사","-철탑 수직, 수평 추락방지장치 설치공사 : No.2 ~ 6, 9, 11, 18, 27~31 (수직13기, 수평13기) -동시휴전 진행","2022-06-21 08:00","2022-06-24 18:00","2022-06-21 08:00","2022-06-24 18:00","연속"]
[303,"대전세종충남","직할","동대전신탄진#1 T/L","[송전] 154kV 동대전-신탄진T/L 철탑 추락방지장치 설치공사","-철탑 수직, 수평 추락방지장치 설치공사 : No.2 ~ 6, 9, 11, 18, 27~31 (수직13기, 수평13기) -동시휴전 진행","2022-06-21 08:00","2022-06-24 18:00","2022-06-21 08:00","2022-06-24 18:00","연속"]
[304,"대전세종충남","직할","신탄진대청HP T/L","[송전] 154kV 동대전-신탄진T/L 철탑 추락방지장치 설치공사","-철탑 수직, 수평 추락방지장치 설치공사 : No.2 ~ 6, 9, 11, 18, 27~31 (수직13기, 수평13기) 좌상 : 동대전신탄진#1 , 우상 : 신탄진대청HP 좌중 : 동대전신탄진#2 , 우중 : 부강신탄진 -신탄진대청HP, 부강신탄진 동시휴전","2022-06-27 08:00","2022-06-28 18:00","2022-06-25 08:00","2022-06-26 18:00","연속"]
[305,"대전세종충남","직할","부강신탄진 T/L","[송전] 154kV 동대전-신탄진T/L 철탑 추락방지장치 설치공사","-철탑 수직, 수평 추락방지장치 설치공사 : No.2 ~ 6, 9, 11, 18, 27~31 (수직13기, 수평13기) 좌상 : 동대전신탄진#1 , 우상 : 신탄진대청HP 좌중 : 동대전신탄진#2 , 우중 : 부강신탄진 -신탄진대청HP, 부강신탄진 동시휴전","2022-06-27 08:00","2022-06-28 18:00","2022-06-25 08:00","2022-06-26 18:00","연속"]
[306,"대전세종충남","천안","서천안S/S SEC CB 65660","서천안SS 154kV B/S 65-66-2DS 누기보수작업","(5월취소시)서천안SS 154kV B/S 65-66-2DS 누기보수작업","2022-06-14 09:00","2022-06-17 18:00","2022-06-14 09:00","2022-06-17 18:00","연속"]
[307,"대전세종충남","천안","서천안S/S #66 BUS","서천안SS 154kV B/S 65-66-2DS 누기보수작업","(5월취소시)서천안SS 154kV B/S 65-66-2DS 누기보수작업","2022-06-14 09:00","2022-06-17 18:00","2022-06-14 09:00","2022-06-17 18:00","연속"]
[308,"대전세종충남","천안","아산S/S #60 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-06-07 09:00","2022-06-16 14:00","2022-06-07 09:00","2022-06-17 14:00","연속"]
[309,"대전세종충남","천안","아산S/S #61 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-06-07 09:00","2022-06-16 14:00","2022-06-07 09:00","2022-06-12 14:00","연속"]
[310,"대전세종충남","천안","아산S/S #65 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-06-17 14:00","2022-06-17 15:00","2022-06-17 14:00","2022-06-17 15:00","연속"]
[311,"대전세종충남","천안","아산S/S #60 BUS","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-06-17 15:00","2022-06-17 16:00","취소","취소","연속"]
[312,"대전세종충남","천안","아산합덕#2 T/L","아산S/S 154kV 장기사용GIS 교체공사","Line PT 회로보완(MCCB교체)","2022-06-21 09:00","2022-06-21 12:00","2022-06-21 09:00","2022-06-21 12:00","연속"]
[313,"대전세종충남","천안","아산인주#1 T/L","아산S/S 154kV 장기사용GIS 교체공사","Line PT 회로보완(MCCB교체)","2022-06-21 13:00","2022-06-21 18:00","2022-06-21 13:00","2022-06-21 18:00","연속"]
[314,"대전세종충남","천안","아산예산#1 T/L","아산S/S 154kV 장기사용GIS 교체공사(4차분)","- 154kV GIS 3CCT 철거 및 설치 - 657, 60-61-0, 65-66-0","2022-06-15 14:00","2022-06-16 14:00","2022-06-11 14:00","2022-06-12 14:00","연속"]
[315,"대전세종충남","천안","아산예산#2 T/L","154kV 예산S/S 미래화공사(일반)","154kV 예산S/S 미래화공사(일반) - 아산-예산#1T/L 인출변경(옥외철구 → 신설GIS)","2022-06-20 10:00","2022-07-01 17:00","취소","취소","연속"]
[316,"대전세종충남","천안","예산응봉#2 T/L","154kV 예산S/S 미래화공사(일반)","154kV 예산S/S 미래화공사(일반) - 예산-응봉#2T/L 인출변경(옥외철구 → 신설GIS)","2022-06-08 10:00","2022-07-01 17:00","취소","취소","연속"]
[317,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용 GIS 대체공사","154kV 아산-온양#1T/L GIS 교체(#65, 66BUS 무부하가압)","2022-06-12 10:00","2022-06-13 10:00","2022-06-12 10:00","2022-06-13 10:00","연속"]
[318,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용 GIS 대체공사","154kV 아산-온양#1T/L GIS 교체(#65, 66BUS 무부하가압)","2022-06-03 09:00","2022-06-03 10:00","2022-06-03 09:00","2022-06-03 10:00","연속"]
[319,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 154kV 장기사용 GIS 대체공사","154kV 아산-온양#1T/L GIS 교체(#60, 61BUS 무부하가압)","2022-06-05 10:00","2022-06-06 10:00","2022-06-05 10:00","2022-06-06 10:00","연속"]
[320,"대전세종충남","천안","서천안탕정#1 T/L","탕정SS 서천안탕정#1T/L GIS 제작자점검","탕정SS 서천안탕정#1T/L GIS 제작자점검","2022-06-08 09:00","2022-06-10 18:00","2022-06-08 09:00","2022-06-10 18:00","연속"]
[321,"대전세종충남","청양","신서천옥산#1 T/L","154kV 옥산-서천#1T/L 관련기기 점검","154kV 옥산-서천#1T/L 관련기기 점검","2022-06-08 09:00","2022-06-08 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[322,"대전세종충남","청양","신서천옥산#2 T/L","154kV 옥산-서천#2T/L 관련기기 점검","154kV 옥산-서천#2T/L 관련기기 점검","2022-06-09 09:00","2022-06-09 18:00","2022-06-09 09:00","2022-06-09 18:00","연속"]
[323,"대전세종충남","청양","동군산장항#2 T/L","154kV 동군산-장항#2T/L 관련기기 점검","154kV 동군산-장항#2T/L 관련기기 점검","2022-06-15 09:00","2022-06-15 18:00","취소","취소","연속"]
[324,"대전세종충남","청양","홍성S/S #61 BUS","홍성 154kV 내포그린에너지 #1,2T/L GIS 증설(더블챔버 조립)","- 내포그린에너지 #2T/L 무부하가압","2022-06-09 14:00","2022-06-10 14:00","2022-06-09 14:00","2022-06-10 14:00","연속"]
[325,"대전세종충남","청양","홍성S/S #65 BUS","홍성 154kV 내포그린에너지 #1,2T/L GIS 증설(더블챔버 조립)","- 내포그린에너지 #1T/L 무부하가압","2022-06-08 14:00","2022-06-09 14:00","2022-06-08 14:00","2022-06-09 14:00","연속"]
[326,"전북","군산","군산서군산#2 T/L","154kV 군산-서군산T/L 취약지지물 교체공사","기설철탑 철거 1기 신설철탑 건설 1기","2022-06-07 07:00","2022-06-09 18:00","2022-06-07 07:00","2022-06-09 18:00","연속"]
[327,"전북","군산","군산서군산#1 T/L","154kV 군산-서군산T/L 취약지지물 교체공사","기설철탑 철거 1기 신설철탑 건설 1기","2022-06-10 07:00","2022-06-11 18:00","2022-06-10 07:00","2022-06-11 18:00","연속"]
[328,"전북","김제","백산김제#2 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-06-21 15:00","2022-06-21 18:00","2022-06-21 15:00","2022-06-21 18:00","연속"]
[329,"전북","김제","백산김제#2 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-06-16 15:00","2022-06-16 18:00","2022-06-16 15:00","2022-06-16 18:00","연속"]
[330,"전북","김제","백산김제#1 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-06-14 15:00","2022-06-14 18:00","2022-06-14 15:00","2022-06-14 18:00","연속"]
[331,"전북","김제","백산김제#2 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-06-09 09:00","2022-06-10 18:00","2022-06-09 09:00","2022-06-10 18:00","연속"]
[332,"전북","김제","백산김제#1 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-06-07 09:00","2022-06-08 18:00","2022-06-07 09:00","2022-06-08 18:00","연속"]
[333,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2022-06-27 08:00","2022-06-28 18:00","취소","취소","연속"]
[334,"전북","김제","신김제전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2022-06-27 08:00","2022-06-28 18:00","취소","취소","연속"]
[335,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2022-06-29 08:00","2022-07-05 18:00","취소","취소","연속"]
[336,"전북","김제","신김제전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2022-06-29 08:00","2022-07-04 18:00","취소","취소","연속"]
[337,"전북","직할","전주서곡#2 T/L","2022년 전북직할 154kV 차단기 정밀점검","2022년 전북직할 154kV 차단기 정밀점검","2022-06-20 09:00","2022-06-24 18:00","취소","취소","연속"]
[338,"전북","직할","전주서곡#1 T/L","2022년 전북직할 154kV 차단기 정밀점검","2022년 전북직할 154kV 차단기 정밀점검","2022-06-13 09:00","2022-06-17 18:00","취소","취소","연속"]
[339,"전북","군산","팔봉봉동#2 T/L","154kV 왕궁S/S 건설사업","154kV 왕궁S/S 건설사업","2022-06-02 15:00","2022-06-03 11:00","2022-06-02 15:00","2022-06-03 11:00","연속"]
[340,"광주전남","광주","계림승주#2 T/L","154kV 계림-승주T/L 안전이격확보공사","철탑보조암 설치 41,47,48,49호","2022-06-01 07:00","2022-06-02 18:00","2022-06-02 07:00","2022-06-03 18:00","연속"]
[341,"광주전남","광주","정공담양 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 정공-담양T/L, #2M.Tr","2022-06-20 09:00","2022-07-30 18:00","취소","취소","연속"]
[342,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 정공-담양T/L, #2M.Tr","2022-06-20 09:00","2022-06-21 16:00","취소","취소","연속"]
[343,"광주전남","순천","여수TP여천#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2022-06-02 09:00","2022-06-03 18:00","취소","취소","연속"]
[344,"광주전남","광주","계림승주#1 T/L","154kV 계림-승주T/L 안전이격확보공사","- 41,47,48,49호 철탑조립 - 전력선 가선 40~50호","2022-06-03 07:00","2022-06-11 18:00","2022-06-04 07:00","2022-06-12 18:00","연속"]
[345,"광주전남","강진","진도진도CS#1 T/L","진도C/S 170kV GIS 증설공사(전문)","준공시험 완료 후 GIS 전체 무부하 가압","2022-06-06 09:00","2022-06-07 18:00","취소","취소","연속"]
[346,"광주전남","강진","진도C/S #2 BUS","진도C/S 170kV GIS 증설공사(전문)","준공시험 완료 후 GIS 전체 무부하 가압(#2DS)","2022-06-06 09:00","2022-06-06 12:00","취소","취소","연속"]
[347,"광주전남","강진","진도C/S #1 BUS","진도C/S 170kV GIS 증설공사(전문)","준공시험 완료 후 GIS 전체 무부하 가압(#1DS,CB,상부BUS)","2022-06-06 12:00","2022-06-07 12:00","취소","취소","연속"]
[348,"광주전남","광주","담양S/S #1 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 정공-담양T/L, #2M.Tr","2022-06-21 16:00","2022-06-25 18:00","취소","취소","연속"]
[349,"광주전남","광주","신광주장성#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","장성S/S 신광주-장성#1T/L 조작시험 (즉시가압 불가)","2022-06-10 09:00","2022-06-10 14:00","2022-06-10 09:00","2022-06-10 14:00","연속"]
[350,"광주전남","목포","장성영광#1 T/L","2022년도 목포전력지사 변전협력회사 총액공사","154kV GIS 보통점검(20분내 즉시가압 가능)","2022-06-07 09:00","2022-06-07 18:00","2022-06-07 09:00","2022-06-07 18:00","연속"]
[351,"광주전남","목포","장성영광#2 T/L","2022년도 목포전력지사 변전협력회사 총액공사","154kV GIS 보통점검(20분내 즉시가압 가능)","2022-06-07 09:00","2022-06-07 18:00","2022-06-23 09:00","2022-06-23 18:00","연속"]
[352,"광주전남","순천","여수TP여천#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2022-06-07 09:00","2022-06-08 18:00","취소","취소","연속"]
[353,"광주전남","강진","나주금천#1 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","나주S/A 나주-금천#1,2T/L GIS 하자점검","2022-06-07 10:00","2022-06-07 14:00","2022-06-07 10:00","2022-06-07 14:00","연속"]
[354,"광주전남","강진","나주금천#2 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","나주S/A 나주-금천#1,2T/L GIS 하자점검","2022-06-07 14:00","2022-06-07 18:00","2022-06-07 14:00","2022-06-07 18:00","연속"]
[355,"광주전남","광주","계림충장#3 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 계림-충장#3T/L 조작시험 (즉시가압 불가)","2022-06-08 09:00","2022-06-08 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[356,"광주전남","순천","호남TP여수TP#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2022-06-09 09:00","2022-06-10 18:00","취소","취소","연속"]
[357,"광주전남","광주","계림승주#2 T/L","154kV 계림-승주T/L 안전이격확보공사","전력선 가선 40~50호","2022-06-12 07:00","2022-06-17 18:00","2022-06-13 07:00","2022-06-18 18:00","연속"]
[358,"광주전남","순천","호남TP여수TP#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2022-06-13 09:00","2022-06-14 18:00","취소","취소","연속"]
[359,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) -#1B/T, #2B/T, 60-61B/S, 65-66B/S, 담양-일곡#2T/L","2022-06-25 09:00","2022-06-26 18:00","취소","취소","연속"]
[360,"광주전남","목포","화원안좌#2 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 전선교체공사 1~22, 28~47호 - 추락방지시설 설치공사","2022-06-14 09:00","2022-07-11 18:00","취소","취소","연속"]
[361,"광주전남","순천","율촌여수산단#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2022-06-15 09:00","2022-06-17 18:00","취소","취소","연속"]
[362,"광주전남","광주","담양일곡#2 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 정공-담양T/L, #2M.Tr - 담양-일곡#2T/L 이용 무부하가압 시행","2022-07-01 09:00","2022-07-02 12:00","취소","취소","연속"]
[363,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 정공-담양T/L, #2M.Tr","2022-06-27 09:00","2022-07-01 18:00","취소","취소","연속"]
[364,"광주전남","강진","강진남창#1 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","강진S/A 강진-남창#1T/L GIS 하자점검, 강진-남창#1T/L PT 보통점검, 강진-남창#1T/L LA A,B,C 보통점검","2022-06-17 10:00","2022-06-17 18:00","2022-06-17 10:00","2022-06-17 18:00","연속"]
[365,"광주전남","순천","율촌여수산단#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검","2022-06-20 09:00","2022-06-22 18:00","취소","취소","연속"]
[366,"광주전남","순천","여수TP화치#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 여수TP-화치#1T/L GIS 보통점검 및 상시여자 보조계전기 교체 화치S/S 여수TP-화치#1T/L GIS CB 타임측정","2022-06-20 09:00","2022-06-20 18:00","2022-06-20 09:00","2022-06-20 18:00","연속"]
[367,"광주전남","목포","고창영광 T/L","2022년도 목포전력지사 변전협력회사 총액공사","154kV GIS 보통점검(20분내 즉시가압 가능)","2022-06-21 09:00","2022-06-21 18:00","2022-06-21 09:00","2022-06-21 18:00","연속"]
[368,"광주전남","순천","여수TP화치#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 여수TP-화치#2T/L GIS 보통점검 및 상시여자 보조계전기 교체 화치S/S 여수TP-화치#2T/L GIS CB 타임측정","2022-06-21 09:00","2022-06-21 18:00","2022-06-21 09:00","2022-06-21 18:00","연속"]
[369,"광주전남","목포","안좌S/S 신안그린T/L CB","2022년 목포전력지사 정밀점검 및 GIS 개조공사","154kV 신안그린T/L GIS 정밀점검","2022-06-23 09:00","2022-06-24 18:00","2022-06-23 09:00","2022-06-24 18:00","연속"]
[370,"광주전남","광주","담양S/S #1 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 정공-담양T/L, #2M.Tr","2022-07-02 09:00","2022-07-02 18:00","취소","취소","연속"]
[371,"광주전남","순천","여수T/P #65 BUS","여수화력 LG화학 NCC 증설공사","170kV GIS 증설공사","2022-06-27 09:00","2022-06-28 18:00","취소","취소","연속"]
[372,"광주전남","순천","여천호남TP#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여천-호남TP#1T/L GIS 보통점검 및 상시여자 보조계전기 교체","2022-06-27 10:00","2022-06-27 18:00","2022-06-27 10:00","2022-06-27 18:00","연속"]
[373,"광주전남","순천","여천호남TP#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여천-호남TP#2T/L GIS 보통점검 및 상시여자 보조계전기 교체","2022-06-28 10:00","2022-06-28 18:00","2022-06-28 10:00","2022-06-28 18:00","연속"]
[374,"광주전남","광주","담양일곡#2 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) -#1B/T, #2B/T, 60-61B/S, 65-66B/S, 담양-일곡#2T/L","2022-07-02 16:00","2022-07-03 18:00","취소","취소","연속"]
[375,"광주전남","순천","여수TP용성#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#2T/L LA(A, B, C) 하자점검 여수화력S/Y 여수TP-용성#2T/L GIS 보통점검 및 상시여자 보조계전기 교체","2022-06-29 10:00","2022-06-29 18:00","취소","취소","연속"]
[376,"광주전남","순천","여수TP용성#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#1T/L LA(A, B, C) 하자점검","2022-06-30 10:00","2022-06-30 18:00","취소","취소","연속"]
[377,"대구","경산","노변시지#2 T/L","22~23년 경산PO 변전협력회사 총액공사","- 장기미동작 차단기 조작시험","2022-06-16 09:30","2022-06-16 18:00","취소","취소","연속"]
[378,"대구","경산","노변시지#1 T/L","22~23년 경산PO 변전협력회사 총액공사","- 장기미동작 차단기 조작시험","2022-06-15 09:30","2022-06-15 18:00","취소","취소","연속"]
[379,"대구","경산","대구청도#1 T/L","청도S/S 154kV GIS 교체공사","154kV GIS 교체","2022-06-02 09:30","2022-07-01 18:00","2022-06-02 09:30","2022-07-01 18:00","연속"]
[380,"대구","경산","청도밀양#2 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-06-16 18:00","2022-06-17 09:30","2022-06-16 18:00","2022-06-17 09:30","연속"]
[381,"대구","경산","청도밀양#1 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-06-09 18:00","2022-06-10 09:30","2022-06-09 18:00","2022-06-10 08:00","연속"]
[382,"대구","달성","고령쌍림#1 T/L","서구지S/S 건설공사","- 고령-서구지#1, 2 T/L 최초가압 TEST 선로","2022-06-22 10:00","2022-06-23 18:00","2022-06-22 10:00","2022-06-23 18:00","연속"]
[383,"대구","달성","논공S/S #1 EM.Tr CB","#E6133GIS 정밀점검","#E6133GIS 정밀점검","2022-06-09 09:00","2022-06-10 18:00","2022-06-09 09:00","2022-06-10 18:00","연속"]
[384,"대구","달성","논공현풍#2 T/L","논공S/S #E6133GIS 정밀점검 무부하가압[TEST]","논공S/S #E6133GIS 정밀점검 무부하가압[TEST]","2022-06-10 13:00","2022-06-10 18:00","2022-06-10 13:00","2022-06-10 18:00","연속"]
[385,"대구","달성","다사달서 T/L","다사S/S 다사-달서T/L GIS 정밀점검","다사S/S 다사-달서T/L GIS 정밀점검","2022-06-20 09:00","2022-06-21 18:00","2022-06-20 09:00","2022-06-21 18:00","연속"]
[386,"대구","달성","논공달성#2 T/L","달성S/S 논공-달성#2T/L GIS 차단기동작특성시험","달성S/S 논공-달성#2T/L GIS 차단기동작특성시험","2022-06-23 14:00","2022-06-23 18:00","2022-06-23 14:00","2022-06-23 18:00","연속"]
[387,"대구","달성","논공달성#1 T/L","달성S/S 논공-달성#1T/L GIS 차단기동작특성시험","달성S/S 논공-달성#1T/L GIS 차단기동작특성시험","2022-06-23 09:00","2022-06-23 14:00","2022-06-23 09:00","2022-06-23 14:00","연속"]
[388,"대구","달성","대구봉덕#1 T/L","대구S/S 697GIS 정밀점검 무부하가압 TEST","대구S/S 697GIS 정밀점검 무부하가압 TEST","2022-06-10 13:00","2022-06-10 18:00","2022-06-08 13:00","2022-06-08 18:00","연속"]
[389,"대구","달성","내당두류#2 T/L","내당-두류#2 T/L GIS 정밀점검","내당-두류#2 T/L GIS 정밀점검","2022-06-02 09:00","2022-06-03 18:00","2022-06-02 09:00","2022-06-03 18:00","연속"]
[390,"대구","달성","대구봉덕#1 T/L","봉덕S/S 대구-봉덕#1T/L GIS 차단기동작특성시험","봉덕S/S 대구-봉덕#1T/L GIS 차단기동작특성시험","2022-06-21 09:00","2022-06-21 14:00","2022-06-21 09:00","2022-06-21 14:00","연속"]
[391,"대구","달성","대구봉덕#2 T/L","봉덕S/S 대구-봉덕#2T/L GIS 차단기동작특성시험","봉덕S/S 대구-봉덕#2T/L GIS 차단기동작특성시험","2022-06-21 14:00","2022-06-21 18:00","2022-06-21 14:00","2022-06-21 18:00","연속"]
[392,"대구","달성","상인봉덕#2 T/L","상인변전소 디지털화 공사","상인변전소 디지털화 공사","2022-06-23 09:00","2022-06-24 18:00","2022-06-23 09:00","2022-06-24 18:00","연속"]
[393,"대구","달성","상인봉덕#1 T/L","상인변전소 디지털화 공사","상인변전소 디지털화 공사","2022-06-16 09:00","2022-06-17 18:00","2022-06-16 09:00","2022-06-17 18:00","연속"]
[394,"대구","직할","범물남대구#2 T/L","남대구S/S 범물-남대구#1,2,T/L 관련 휴전작업","남대구S/S 범물-남대구#1,2,T/L 관련 휴전작업","2022-06-07 14:00","2022-06-07 18:00","2022-06-07 14:00","2022-06-07 18:00","연속"]
[395,"대구","직할","남대구동인#2 T/L","남대구S/S 남대구-동인#1,2,T/L 관련 휴전작업","남대구S/S 남대구-동인#1,2,T/L 관련 휴전작업","2022-06-08 14:00","2022-06-08 18:00","2022-06-08 14:00","2022-06-08 18:00","연속"]
[396,"대구","직할","남대구동인#1 T/L","남대구S/S 남대구-동인#1,2,T/L 관련 휴전작업","남대구S/S 남대구-동인#1,2,T/L 관련 휴전작업","2022-06-08 09:30","2022-06-08 14:00","2022-06-08 09:30","2022-06-08 14:00","연속"]
[397,"대구","직할","범물남대구#1 T/L","남대구S/S 범물-남대구#1,2,T/L 관련 휴전작업","남대구S/S 범물-남대구#1,2,T/L 관련 휴전작업","2022-06-07 09:30","2022-06-07 14:00","2022-06-07 09:30","2022-06-07 14:00","연속"]
[398,"대구","직할","시지효목#2 T/L","효목S/S 시지-효목#1,2,T/L 관련 휴전작업","효목S/S 시지-효목#1,2,T/L 관련 휴전작업","2022-06-10 14:00","2022-06-10 18:00","2022-06-10 14:00","2022-06-10 18:00","연속"]
[399,"대구","직할","효목안심#1 T/L","효목S/S 효목-안심#1,2,T/L 관련 휴전작업","효목S/S 효목-안심#1,2,T/L 관련 휴전작업","2022-06-09 09:30","2022-06-09 14:00","2022-06-09 09:30","2022-06-09 14:00","연속"]
[400,"대구","직할","시지효목#1 T/L","효목S/S 시지-효목#1,2,T/L 관련 휴전작업","효목S/S 시지-효목#1,2,T/L 관련 휴전작업","2022-06-10 09:30","2022-06-10 14:00","2022-06-10 09:30","2022-06-10 14:00","연속"]
[401,"대구","직할","효목안심#2 T/L","효목S/S 효목-안심#1,2,T/L 관련 휴전작업","효목S/S 효목-안심#1,2,T/L 관련 휴전작업","2022-06-09 14:00","2022-06-09 18:00","2022-06-09 14:00","2022-06-09 18:00","연속"]
[402,"대구","칠곡","구미광평#1 T/L","광평S/S 구미-광평#1T/L GIS 보통점검","광평S/S 구미-광평#1T/L GIS 보통점검","2022-06-09 09:30","2022-06-09 14:00","2022-06-09 09:30","2022-06-09 14:00","연속"]
[403,"부산울산","동부산","웅촌서창#2 T/L","서창S/S 637GIS 차단기 동작시험","서창S/S 637GIS 차단기 동작시험","2022-06-30 09:30","2022-06-30 17:00","2022-06-30 09:30","2022-06-30 17:00","연속"]
[404,"부산울산","동부산","정관장안#2 T/L","장안S/S 667GIS 초기점검","장안S/S 667GIS 초기점검","2022-06-15 09:30","2022-06-15 17:00","2022-06-15 09:30","2022-06-15 17:00","연속"]
[405,"부산울산","동부산","정관장안#1 T/L","장안S/S 647GIS 초기점검","장안S/S 647GIS 초기점검","2022-06-14 09:30","2022-06-14 17:00","2022-06-14 09:30","2022-06-14 17:00","연속"]
[406,"부산울산","동부산","시랑좌동#1 T/L","154kV 시랑-좌동#1,2T/L 인출 옥외 피뢰기 접근금지 펜스시공","접근금지 펜스시공관련 안전이격 확보용 휴전","2022-06-08 09:00","2022-06-08 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[407,"부산울산","동부산","시랑좌동#2 T/L","154kV 시랑-좌동#1,2T/L 인출 옥외 피뢰기 접근금지 펜스시공","접근금지 펜스시공관련 안전이격 확보용 휴전","2022-06-08 09:00","2022-06-08 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[408,"부산울산","북부산","모라엄궁#1 T/L","22-23 북부산전력지사 변전 총액공사","엄궁S/S 154kV 모라-엄궁#1T/L 조작시험","2022-06-13 10:00","2022-06-13 18:00","2022-06-13 10:00","2022-06-13 18:00","연속"]
[409,"부산울산","북부산","모라엄궁#2 T/L","22-23 북부산전력지사 변전 총액공사","엄궁S/S 154kV 모라-엄궁#2T/L 조작시험","2022-06-14 10:00","2022-06-14 18:00","2022-06-14 10:00","2022-06-14 18:00","연속"]
[410,"부산울산","북부산","학장개금#1 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV 학장-개금#1T/L GIS 정밀점검","2022-06-27 09:00","2022-06-28 18:00","2022-06-27 09:00","2022-06-28 18:00","연속"]
[411,"부산울산","북부산","엄궁학장#1 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV 엄궁-학장#1T/L GIS 정밀점검","2022-06-21 09:00","2022-06-22 18:00","2022-06-21 09:00","2022-06-22 18:00","연속"]
[412,"부산울산","북부산","엄궁학장#2 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV 엄궁-학장#2T/L GIS 정밀점검","2022-06-23 09:00","2022-06-24 18:00","2022-06-23 09:00","2022-06-24 18:00","연속"]
[413,"부산울산","북부산","학장개금#2 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV 학장-개금#2T/L GIS 정밀점검","2022-06-29 09:00","2022-06-30 18:00","2022-06-29 09:00","2022-06-30 18:00","연속"]
[414,"부산울산","북부산","호포매리#1 T/L","22-23 북부산전력지사 변전 총액공사","호포S/S 154kV 호포-매리#1T/L GIS 차단기 조작시험","2022-06-09 10:00","2022-06-09 18:00","취소","취소","연속"]
[415,"부산울산","북부산","호포매리#2 T/L","22-23 북부산전력지사 변전 총액공사","호포S/S 154kV 호포-매리#2T/L GIS 차단기 조작시험","2022-06-10 10:00","2022-06-10 18:00","취소","취소","연속"]
[416,"부산울산","서부산","용원녹공#1 T/L","용원S/S 154kV 용원-녹공#1T/L 보호반대체","용원S/S 154kV 용원-녹공#1T/L 보호반대체 병행 : 녹공S/S 154kV 용원-녹공#1T/L 보호반대체","2022-06-21 09:00","2022-06-23 18:00","2022-06-18 09:00","2022-06-19 18:00","연속"]
[417,"부산울산","서부산","신김해지사#2 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","수평 추락방지장치 설치 : 30~37호(8기)","2022-06-22 07:00","2022-06-23 18:00","2022-06-22 07:00","2022-06-23 18:00","연속"]
[418,"부산울산","서부산","신김해지사#1 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","수평 추락방지장치 설치 : 30~37호(8기)","2022-06-20 07:00","2022-06-21 18:00","2022-06-20 07:00","2022-06-21 18:00","연속"]
[419,"부산울산","울산","두왕울산#2 T/L","세니온제 송전선로 보호반 성능개선","- 세니온제 송전선로 보호반 성능개선(계통시험파트)","2022-06-17 09:00","2022-06-17 18:00","2022-06-17 09:00","2022-06-17 18:00","연속"]
[420,"부산울산","울산","반천언양#1 T/L","세니온제 송전선로 보호반 성능개선","- 세니온제 송전선로 보호반 성능개선(계통시험파트)","2022-06-15 09:00","2022-06-15 18:00","2022-06-15 09:00","2022-06-15 18:00","연속"]
[421,"부산울산","울산","반천언양#2 T/L","세니온제 송전선로 보호반 성능개선","- 세니온제 송전선로 보호반 성능개선(계통시험파트)","2022-06-16 09:00","2022-06-16 18:00","2022-06-16 09:00","2022-06-16 18:00","연속"]
[422,"부산울산","울산","언양산막#2 T/L","154kV 언양-산막 등 2개T/L 자기애관 교체공사(비표준)","154kV 언양-산막T/L 비표준 자기애관 교체공사 자기애관을 폴리머애관으로 변경","2022-06-04 09:00","2022-06-08 18:00","취소","취소","연속"]
[423,"부산울산","울산","온산처용#2 T/L","22~23년 변전협력회사 총액공사","- GIS 차단기 동작시험 - 처용S/S 피뢰기 보통점검","2022-06-17 09:00","2022-06-17 18:00","2022-06-17 09:00","2022-06-17 18:00","연속"]
[424,"부산울산","울산","온산처용#1 T/L","22~23년 변전협력회사 총액공사","- 온산S/S GIS 보통점검, 전자변 교체","2022-06-20 09:00","2022-06-20 18:00","2022-06-20 09:00","2022-06-20 18:00","연속"]
[425,"부산울산","울산","울산T/P #60 BUS","울산화력S/Y 장기사용대체공사","#60-65 PT&ES 대체 #6100 BUS TIE CB 대체","2022-06-09 09:00","2022-06-17 18:00","2022-06-09 09:00","2022-06-17 18:00","연속"]
[426,"부산울산","울산","울산T/P CB 6100","울산화력S/Y 장기사용대체공사","#60-65BUS PT&ES 대체 #6100 BUS TIE CB 대체","2022-06-08 09:00","2022-06-28 18:00","2022-06-08 09:00","2022-06-28 18:00","연속"]
[427,"부산울산","울산","성암울산TP#2 T/L","울산화력S/Y 장기사용대체공사","#60-65 PT&ES 대체 #6100 BUS TIE CB 대체 #60BUS 시험가압","2022-06-16 18:00","2022-06-17 18:00","2022-06-16 18:00","2022-06-17 18:00","연속"]
[428,"부산울산","울산","울산T/P #65 BUS","울산화력S/Y 장기사용대체공사","#60-65 PT&ES 대체 #6100 BUS TIE CB 대체","2022-06-18 09:00","2022-06-28 18:00","2022-06-18 09:00","2022-06-28 18:00","연속"]
[429,"부산울산","울산","성암울산TP#2 T/L","울산화력S/Y 장기사용대체공사","#60-65 PT&ES 대체 #6100 BUS TIE CB 대체 #65BUS 시험가압","2022-06-27 18:00","2022-06-28 18:00","2022-06-27 18:00","2022-06-28 18:00","연속"]
[430,"부산울산","울산","울산T/P #60 BUS","울산화력S/Y 장기사용대체공사","#60-65 PT&ES 대체 #6100 BUS TIE CB 대체 #6100 BUS TIE #1DS 투입 시험가압","2022-06-28 17:00","2022-06-28 18:00","2022-06-28 17:00","2022-06-28 18:00","연속"]
[431,"부산울산","울산","울산T/P #65 BUS","울산화력S/Y 장기사용대체공사","#60-65BUS PT&ES 대체 #6100 BUS TIE CB 대체","2022-06-08 09:00","2022-06-08 18:00","2022-06-08 09:00","2022-06-08 18:00","연속"]
[432,"부산울산","울산","성암울산TP#2 T/L","울산화력S/Y 장기사용대체공사","#60-65BUS PT&ES 대체 #6100 BUS TIE CB 대체 #65BUS 시험가압","2022-06-08 17:00","2022-06-08 18:00","2022-06-08 17:00","2022-06-08 18:00","연속"]
[433,"부산울산","울산","울산영남TP#2 T/L","154kV 울산-영남TP T/L 16~19호간 지장철탑 이설공사","1. 사업목적 : 울산미포국가산업단지 부곡용연지구 조성에 지장이되는 송전선로 이설 2. 공사내용 - 철탑설치 5기(가철탑 2기), 철탑 철거 4기(가철탑 2기) - 전력선 및 금구류 교체 (0.801km) - 철탑 환경친화 도장","2022-06-27 07:00","2022-07-02 18:00","2022-06-27 07:00","2022-07-02 18:00","연속"]
[434,"부산울산","울산","울산영남TP#1 T/L","154kV 울산-영남TP T/L 16~19호간 지장철탑 이설공사","1. 사업목적 : 울산미포국가산업단지 부곡용연지구 조성에 지장이되는 송전선로 이설 2. 공사내용 - 철탑설치 5기(가철탑 2기), 철탑 철거 4기(가철탑 2기) - 전력선 및 금구류 교체 (0.801km) - 철탑 환경친화 도장","2022-06-20 07:00","2022-06-25 18:00","2022-06-20 07:00","2022-06-25 18:00","연속"]
[435,"부산울산","울산","울산영남TP#2 T/L","154kV 울산-영남TP T/L 16~19호간 지장철탑 이설공사","1. 사업목적 : 울산미포국가산업단지 부곡용연지구 조성에 지장이되는 송전선로 이설 2. 공사내용 - 철탑설치 5기(가철탑 2기), 철탑 철거 4기(가철탑 2기) - 전력선 및 금구류 교체 (0.801km) - 철탑 환경친화 도장","2022-06-06 07:00","2022-06-11 18:00","2022-06-06 07:00","2022-06-11 18:00","연속"]
[436,"부산울산","울산","신울산웅촌#2 T/L","22~23년 변전협력회사 총액공사","- GIS 차단기 동작시험 - 피뢰기 보통점검","2022-06-16 09:00","2022-06-16 18:00","2022-06-16 09:00","2022-06-16 18:00","연속"]
[437,"부산울산","직할","정보대연 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","수평용 추락방지장치 설치 : 1~13호","2022-06-27 07:00","2022-06-28 18:00","2022-06-27 07:00","2022-06-28 18:00","연속"]
[438,"부산울산","직할","우동대연 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","수평용 추락방지장치, 피뢰기 설치 : 1~13호","2022-06-29 07:00","2022-06-30 18:00","2022-06-29 07:00","2022-06-30 18:00","연속"]
[439,"부산울산","직할","범일S/S CB 6100","22-23년 직할 변전협력회사 총액공사","범일S/S 154kV BUS-TIE GIS (6100) 보통점검","2022-06-07 09:30","2022-06-07 18:00","2022-06-07 09:30","2022-06-07 18:00","연속"]
[440,"부산울산","직할","범천S/S CB 6100","22-23년 직할 변전협력회사 총액공사","범천S/S 154kV BUS-TIE GIS (6100) 하자점검","2022-06-10 09:30","2022-06-10 18:00","2022-06-10 09:30","2022-06-10 18:00","연속"]
[441,"부산울산","직할","양정범천 T/L","22-23년 직할 변전협력회사 총액공사","범천S/S 양정-범천T/L GIS 하자점검","2022-06-28 09:30","2022-06-28 18:00","2022-06-28 09:30","2022-06-28 18:00","연속"]
[442,"부산울산","직할","범일서면#1 T/L","22-23년 직할 변전협력회사 총액공사","서면S/S 범일-서면#1,2T/L GIS 보통점검, 에어링밸브 교체, 범일S/S 범일-서면#1,2T/L GIS 보통점검, #1T/L보호반 87 RY 교체 및 연동시험","2022-06-11 09:00","2022-06-11 18:00","2022-06-11 09:00","2022-06-11 18:00","연속"]
[443,"부산울산","직할","범일서면#2 T/L","22-23년 직할 변전협력회사 총액공사","서면S/S 범일-서면#1,2T/L GIS 보통점검, 에어링밸브 교체, 범일S/S 범일-서면#1,2T/L GIS 보통점검, #1T/L보호반 87 RY 교체 및 연동시험","2022-06-11 09:00","2022-06-11 18:00","2022-06-11 09:00","2022-06-11 18:00","연속"]
[444,"부산울산","직할","정보대연 T/L","22-23년 직할 변전협력회사 총액공사","대연S/S 정보-대연T/L GIS 조작시험, 우동-대연T/L GIS 조작시험","2022-06-15 09:30","2022-06-15 14:00","2022-06-15 09:30","2022-06-15 14:00","연속"]
[445,"부산울산","직할","우동대연 T/L","22-23년 직할 변전협력회사 총액공사","대연S/S 정보-대연T/L GIS 조작시험, 우동-대연T/L GIS 조작시험","2022-06-15 14:00","2022-06-15 18:00","2022-06-15 14:00","2022-06-15 18:00","연속"]
[446,"부산울산","직할","부산수정#1 T/L","2022년 직할 170kV GIS 정밀점검","수정S/S 부산-수정#1T/L GIS(657) 정밀점검 부산S/S 부산-수정#1T/L GIS(637) 보통점검","2022-06-07 09:00","2022-06-08 18:00","2022-06-07 09:00","2022-06-08 18:00","연속"]
[447,"부산울산","직할","부산수정#2 T/L","2022년 직할 170kV GIS 정밀점검","수정S/S 부산-수정#2T/L GIS(667) 정밀점검 부산S/S 부산-수정#2T/L GIS(647) 보통점검","2022-06-09 09:00","2022-06-10 18:00","2022-06-09 09:00","2022-06-10 18:00","연속"]
[448,"부산울산","직할","수정범일#1 T/L","2022년 직할 170kV GIS 정밀점검","수정S/S 수정-범일#1T/L GIS(627) 정밀점검, 보호반 IED 성능개선 범일S/S 수정-범일#1T/L GIS(617) 보통점검, 보호반 IED 성능개선","2022-06-13 09:00","2022-06-14 18:00","2022-06-13 09:00","2022-06-14 18:00","연속"]
[449,"부산울산","직할","수정범일#2 T/L","2022년 직할 170kV GIS 정밀점검","수정S/S 수정-범일#2T/L GIS(617) 정밀점검, 보호반 IED 성능개선 범일S/S 수정-범일#2T/L GIS(627) 보통점검, 보호반 IED 성능개선","2022-06-13 09:00","2022-06-16 18:00","2022-06-13 09:00","2022-06-16 18:00","연속"]
[450,"부산울산","직할","수정S/S #2 BUS","2022년 직할 170kV GIS 정밀점검","수정S/S 154kV BUS-TIE GIS (6100) 정밀점검, 무부하 시험가압","2022-06-20 09:00","2022-06-21 18:00","2022-06-20 09:00","2022-06-21 18:00","연속"]
[451,"부산울산","직할","수정S/S CB 6100","2022년 직할 170kV GIS 정밀점검","수정S/S 154kV BUS-TIE GIS (6100) 정밀점검","2022-06-20 09:00","2022-06-21 18:00","2022-06-20 09:00","2022-06-21 18:00","연속"]
[452,"부산울산","직할","수정범일#2 T/L","2022년 직할 170kV GIS 정밀점검","수정S/S 154kV BUS-TIE GIS (6100) 정밀점검, 무부하 시험가압","2022-06-21 16:00","2022-06-21 18:00","2022-06-21 16:00","2022-06-21 18:00","연속"]
[453,"경남","직할","신김해진례#1 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-06-25 08:00","2022-06-26 18:00","2022-06-25 08:00","2022-06-26 18:00","연속"]
[454,"경남","직할","신김해삼정#2 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-06-22 13:30","2022-06-24 18:00","2022-06-22 13:30","2022-06-24 18:00","연속"]
[455,"경남","직할","신김해삼정#1 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-06-20 08:00","2022-06-22 13:30","2022-06-20 08:00","2022-06-22 13:30","연속"]
[456,"경남","진주","사천개양#2 T/L","사천S/S 사천-개양#2T/L GIS 보통점검 및 LA 대체","사천S/S 사천-개양#2T/L GIS 보통점검 및 LA 대체","2022-06-05 10:00","2022-06-05 18:00","2022-06-05 10:00","2022-06-05 18:00","연속"]
[457,"경남","진주","사천개양#1 T/L","사천S/S 사천-개양#1T/L GIS 보통점검 및 LA 대체","사천S/S 사천-개양#1T/L GIS 보통점검 및 LA 대체","2022-06-04 10:00","2022-06-04 18:00","2022-06-04 10:00","2022-06-04 18:00","연속"]
[458,"경남","진주","산청함양 T/L","산청S/S 산청-함양T/L LA 대체","산청S/S 산청-함양T/L LA 대체","2022-06-30 10:00","2022-06-30 18:00","2022-06-30 10:00","2022-06-30 18:00","연속"]
[459,"경남","진주","의령산청 T/L","의령S/S 의령-산청T/L GIS 조작시험","[병행]LA 하자점검, PT 보통점검","2022-06-28 10:00","2022-06-28 18:00","2022-06-28 10:00","2022-06-28 18:00","연속"]
[460,"경남","진주","의령S/S #1 EM.Tr CB","의령S/S FR-ESS 정기점검","의령S/S FR-ESS 정기점검","2022-06-13 10:00","2022-06-17 18:00","2022-06-13 10:00","2022-06-17 18:00","연속"]
[461,"경남","진주","하동개양#1 T/L","추락방지시설 설치","□ 휴전설비 : 하동-개양, 하동-하동TP, 태금-하동, 하동-남해T/L □ 설치대상 ○ 154kV 하동-개양T/L No.1~108호(105기) ☞ 6회선 철탑(No.88) 설치시 하동-하동TP, 태금-하동, 하동-남해T/L 안전작업거리확보 휴전필요 ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 하동-개양#1,2T/L동시휴전 필요","2022-06-25 07:00","2022-06-26 18:00","취소","취소","연속"]
[462,"경남","진주","하동개양#1 T/L","추락방지시설 설치","□ 휴전설비 : 하동-개양, 하동-하동TP, 태금-하동, 하동-남해T/L □ 설치대상 ○ 154kV 하동-개양T/L No.1~108호(105기) ☞ 6회선 철탑(No.88) 설치시 하동-하동TP, 태금-하동, 하동-남해T/L 안전작업거리확보 휴전필요 ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 하동-개양#1,2T/L동시휴전 필요","2022-06-07 07:00","2022-06-19 18:00","취소","취소","연속"]
[463,"경남","진주","하동개양#2 T/L","추락방지시설 설치","□ 휴전설비 : 하동-개양, 하동-하동TP, 태금-하동, 하동-남해T/L □ 설치대상 ○ 154kV 하동-개양T/L No.1~108호(105기) ☞ 6회선 철탑(No.88) 설치시 하동-하동TP, 태금-하동, 하동-남해T/L 안전작업거리확보 휴전필요 ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 하동-개양#1,2T/L동시휴전 필요","2022-06-11 07:00","2022-06-12 18:00","취소","취소","연속"]
[464,"경남","진주","하동하동화력 T/L","추락방지시설 설치","□ 휴전설비 : 하동-개양, 하동-하동TP, 태금-하동, 하동-남해T/L □ 설치대상 ○ 154kV 하동-개양T/L No.1~108호(105기) ☞ 6회선 철탑(No.88) 설치시 하동-하동TP, 태금-하동, 하동-남해T/L 안전작업거리확보 휴전필요 ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 하동-개양#1,2T/L동시휴전 필요","2022-06-18 07:00","2022-06-18 18:00","2022-06-18 07:00","2022-06-18 18:00","연속"]
[465,"경남","진주","하동개양#2 T/L","추락방지시설 설치","□ 휴전설비 : 하동-개양, 하동-하동TP, 태금-하동, 하동-남해T/L □ 설치대상 ○ 154kV 하동-개양T/L No.1~108호(105기) ☞ 6회선 철탑(No.88) 설치시 하동-하동TP, 태금-하동, 하동-남해T/L 안전작업거리확보 휴전필요 ☞ 4회선 철탑(No.89~108) 설치시 안전작업거리확보를 위한 하동-개양#1,2T/L동시휴전 필요","2022-06-18 07:00","2022-06-30 18:00","취소","취소","연속"]
[466,"경남","진주","광양하동#1 T/L","하동S/S 154kV 하동전철T/L 신규수용공사(안전이격거리 확보)","- 170kV GIS X 2CCT 설치(지중) - 154kV 송전선로보호배전반 X 2면 설치 - 기타부대공사 X 1식","2022-06-13 09:30","2022-06-13 17:30","2022-06-13 09:30","2022-06-13 17:30","연속"]
[467,"경남","진주","광양하동#2 T/L","하동S/S 154kV 하동전철T/L 신규수용공사(안전이격거리 확보)","- 170kV GIS X 2CCT 설치(지중) - 154kV 송전선로보호배전반 X 2면 설치 - 기타부대공사 X 1식","2022-06-07 09:30","2022-06-08 17:30","2022-06-07 09:30","2022-06-08 17:30","연속"]
[468,"경남","통영","통영거제#1 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-06-04 07:00","2022-06-05 20:00","2022-06-04 07:00","2022-06-05 20:00","연속"]
[469,"경남","통영","통영거제#2 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-06-06 07:00","2022-06-06 18:00","2022-06-06 07:00","2022-06-06 18:00","연속"]
[470,"경남","통영","신고성거제#1 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-06-11 07:00","2022-06-12 18:00","2022-06-11 07:00","2022-06-12 18:00","연속"]
[471,"경남","통영","통영거제#1 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-06-12 19:00","2022-06-12 20:00","2022-06-12 19:00","2022-06-12 20:00","연속"]
[472,"경남","통영","신고성거제#2 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 (5회선, 임시철탑 5기 신설) - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-06-04 07:00","2022-06-06 18:00","2022-06-04 07:00","2022-06-06 18:00","연속"]
[473,"경남","통영","신고성삼천포#2 T/L","삼천포S/S 신고성-삼천포#2T/L GIS 보통점검 및 전자변교체","삼천포S/S 신고성-삼천포#2T/L GIS 보통점검 및 전자변교체","2022-06-11 10:00","2022-06-11 18:00","2022-06-11 10:00","2022-06-11 18:00","연속"]
[474,"경남","통영","삼천포사천#1 T/L","154kV 신고성-삼천포#1T/L 피뢰기 설치공사 안전작업거리 확보","154kV 신고성-삼천포#1T/L 피뢰기 설치공사 안전작업거리 확보","2022-06-05 07:00","2022-06-06 18:00","2022-06-05 07:00","2022-06-06 18:00","매일"]
[475,"경남","통영","신고성고성 T/L","154kV 신고성고성T/L 추락방지시설 설치공사","154kV 신고성고성T/L 추락방지시설 설치공사","2022-06-23 07:00","2022-06-26 18:00","2022-06-23 07:00","2022-06-26 18:00","매일"]
[476,"경남","통영","신고성삼천포#1 T/L","154kV 신고성-삼천포#1T/L 피뢰기 설치공사","154kV 신고성-삼천포#1T/L 피뢰기 설치공사","2022-06-05 07:00","2022-06-06 18:00","2022-06-05 07:00","2022-06-06 18:00","매일"]
[477,"경남","통영","통영거제#2 T/L","154kV 고성통영T/L 추락방지시설 설치공사 안전작업거리 확보","154kV 고성통영T/L 추락방지시설 설치공사 안전작업거리 확보","2022-06-18 07:00","2022-06-18 18:00","2022-06-18 07:00","2022-06-18 18:00","매일"]
[478,"경남","통영","고성통영 T/L","154kV 고성통영T/L 추락방지시설 설치공사","154kV 고성통영T/L 추락방지시설 설치공사","2022-06-18 07:00","2022-06-19 18:00","2022-06-18 07:00","2022-06-19 18:00","매일"]
[479,"경남","함안","매리김해#2 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : 전력선 및 가공지선 설치","2022-06-03 07:00","2022-06-06 18:00","취소","취소","연속"]
[480,"경남","함안","호포매리#2 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : 전력선 및 가공지선 설치","2022-06-03 07:00","2022-06-06 18:00","취소","취소","연속"]
[481,"경남","함안","청도밀양#1 T/L","154kV 청도-밀양#1T/L 피뢰기 및 추락방지장치 설치공사","154kV 청도-밀양#1T/L 피뢰기 및 추락방지장치 설치공사 48기(30~80호, 75~77호 제외)","2022-06-07 08:00","2022-06-11 18:00","2022-06-07 08:00","2022-06-09 18:00","연속"]
[482,"경남","함안","청도밀양#2 T/L","청도-밀양#1T/L 피뢰기 및 추락방지장치 설치공사 관련 안전거리확보","154kV 청도-밀양#1T/L 피뢰기 및 추락방지장치 설치공사 관련 안전거리확보(57~80호, 75~77호 제외)","2022-06-09 08:00","2022-06-11 18:00","2022-06-10 08:00","2022-06-11 18:00","연속"]
[483,"경남","함안","진영수산#1 T/L","154kV 진영-수산#1T/L 피뢰기 및 추락방지장치 설치공사","154kV 진영-수산#1T/L 피뢰기 및 추락방지장치 설치공사 32기(28~60호, 29호 제외)","2022-06-13 08:00","2022-06-17 18:00","2022-06-13 08:00","2022-06-17 18:00","연속"]
[484,"경남","함안","진영수산#2 T/L","154kV 진영-수산#2T/L 추락방지장치 설치공사","154kV 진영-수산#2T/L 추락방지장치 설치공사 32기(28~60호, 29호 제외)","2022-06-20 08:00","2022-06-22 18:00","2022-06-20 08:00","2022-06-22 18:00","연속"]
[485,"경기북부","구리","포천운천#2 T/L","철탑 추락방지시설 설치공사","철탑 추락방지시설 설치공사","2022-06-13 07:00","2022-06-13 18:00","2022-06-13 07:00","2022-06-13 18:00","연속"]
[486,"경기북부","직할","용현도봉#1 T/L","154kV 장암S/S 옥내화 건설공사","용현S/S 용현도봉#1T/L 송전선로 보호반 대체","2022-06-21 09:00","2022-06-29 09:00","2022-06-21 09:00","2022-06-29 09:00","연속"]
[487,"경기북부","직할","용현도봉#1 T/L","장암S/S 옥내화 건설공사","장암S/S 옥내화 건설공사 최초가압","2022-06-29 09:00","2022-07-01 09:00","2022-06-29 09:00","2022-07-01 09:00","연속"]
[488,"경기북부","직할","신의정부용현#1 T/L","장암S/S 옥내화 건설공사","장암S/S 옥내화 건설공사 최초가압","2022-06-29 09:00","2022-07-01 09:00","2022-06-29 09:00","2022-07-01 09:00","연속"]
[489,"경기북부","직할","용현S/S #1 BUS","154kV 장암S/S 옥내화 건설공사","장암S/S 옥내화 건설공사 최초가압 - 용현장암#2T/L, 장암방학#2T/L","2022-06-29 09:00","2022-06-30 18:00","2022-06-29 09:00","2022-06-30 18:00","연속"]
[490,"경기","평택","평택오성CC#2T/L","평택-오성복합#2T/L 정밀점검","평택-오성복합#2T/L 정밀점검","2022-06-11 09:00","2022-06-12 18:00","2022-06-11 09:00","2022-06-12 18:00","연속"]
[491,"경기","성남","용인덕성#2 T/L"," 22-23년 경기직할 가공송전 협력회사 총액공사","추락방지시설 설치","2022-06-24 08:00","2022-07-01 18:00","2022-06-24 08:00","2022-07-01 18:00","연속"]
[492,"경기","성남","신용인용인#2 T/L"," 22-23년 경기직할 가공송전 협력회사 총액공사","추락방지시설 설치","2022-06-24 08:00","2022-06-24 18:00","2022-06-24 08:00","2022-06-24 18:00","연속"]