{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":6,"n_cols":11,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 7월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"부산울산","동부산","신고리S/S #1 Tie-Tr","신고리 5,6호기 접속설비공사","345kV 신고리-고리 #4T/L CH 인하선 연결 (안전 이격거리 확보)","2022-07-26 09:00","2022-07-26 18:00","취소","취소","연속"]
[2,"부산울산","동부산","신고리S/S #2 Tie-Tr","신고리 5,6호기 접속설비공사","- 신고리 #4M.Tr 설치, #4M.Tr 2차측 GIB 설치, #4M.Tr 3차측 EGIS 설치 - #4M.Tr 1차측 GIB 설치, 내전압시험 - #4M.Tr 관련 설비 준공시험 - 기타 부태설비","2022-07-27 09:00","2022-10-31 18:00","취소","취소","연속"]

{"sheet":"345설비","index":1,"n_rows":72,"n_cols":11,"rows_kept":72,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 7월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","신양재S/S #1 Sh.R CB","2022년 강남전력지사 345kV Sh.R 정밀점검","2022년 강남전력지사 345kV Sh.R 정밀점검 - 점검대상 : #1Sh.R - 병행작업 1. GIS 조작시험 2. Sh.R 보호반 대체","2022-07-04 09:00","2022-07-15 18:00","2022-07-04 09:00","2022-07-15 18:00","연속"]
[2,"남서울","강남","신양재S/S #2 Sh.R CB","2022년 강남전력지사 345kV Sh.R 정밀점검","2022년 강남전력지사 345kV Sh.R 정밀점검 - 점검대상 : #2Sh.R - 병행작업 1. GIS 조작시험 2. Sh.R 보호반 대체","2022-07-18 09:00","2022-07-29 18:00","2022-07-18 09:00","2022-07-29 18:00","연속"]
[3,"남서울","동서울","동서울S/S #2 Sh.R CB","동서울SS #2Sh.R 보통, 7A72,7079 GIS 하자점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-07-18 09:00","2022-07-18 18:00","2022-07-18 09:00","2022-07-18 18:00","연속"]
[4,"남서울","동서울","동서울S/S #1 Sh.R CB","동서울SS 345kV #1Sh.R 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-07-04 09:00","2022-07-08 18:00","2022-07-04 09:00","2022-07-08 18:00","연속"]
[5,"남서울","동서울","동서울S/S #2 Sh.R CB","동서울SS #2Sh.R 보통, 7A72,7079 GIS 하자점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-07-11 09:00","2022-07-15 18:00","취소","취소","연속"]
[6,"인천","김포","신김포S/S #1 Sh.R CB","신김포S/S 362kV 7171 GIS 보통점검","신김포S/S 362kV 7171 GIS 보통점검","2022-07-06 10:00","2022-07-06 18:00","2022-07-06 10:00","2022-07-06 18:00","연속"]
[7,"경기북부","구리","미금S/S #1 Sh.R CB","미금S/S 345kV #1Sh.R 교체공사","345kV #1Sh.R 교체공사 시험가압","2022-07-27 09:00","2022-07-29 18:00","2022-07-27 09:00","2022-07-29 18:00","연속"]
[8,"경기북부","구리","미금S/S STATCOM CB","345kV 미금S/S 용량부족 차단기 대체공사","79Bay GIS 용량대체(50kA→63kA)","2022-07-04 09:00","2022-09-08 18:00","2022-07-04 09:00","2022-09-08 18:00","연속"]
[9,"경기","성남","신안성S/S CB 7B71","22년 성남전력지사 변전협력회사 총액공사","- B/F 대체 - Sh.R 보호반대체 - GIS 보통점검(7B71) - GIS 조작시험(7B79)","2022-07-04 09:00","2022-07-08 18:00","2022-07-04 09:00","2022-07-08 18:00","연속"]
[10,"경기","성남","신안성서안성#2 T/L","22년 성남전력지사 변전협력회사 총액공사","- B/F 대체 - GIS 보통점검(7B72,7B00)","2022-07-04 09:00","2022-07-08 18:00","2022-07-04 09:00","2022-07-08 18:00","연속"]
[11,"경기","성남","신안성S/S CB 7B72","22년 성남전력지사 변전협력회사 총액공사","- B/F 대체 - Sh.R 보호반대체 - GIS 보통점검(7B72) - GIS 조작시험(7B79)","2022-07-04 09:00","2022-07-08 18:00","2022-07-04 09:00","2022-07-08 18:00","연속"]
[12,"경기","직할","화성S/S #75 BUS","화성S/S 345kV GIS 용량대체","74Bay 75BUS 측 무부하시험","2022-07-03 09:00","2022-07-04 07:00","2022-07-03 09:00","2022-07-04 07:00","연속"]
[13,"경기","직할","화성S/S #70 BUS","화성S/S 345kV GIS 용량대체","74Bay 70BUS 측 무부하시험","2022-07-02 09:00","2022-07-03 09:00","2022-07-02 09:00","2022-07-03 09:00","연속"]
[14,"경기","평택","고덕S/S #4 M.Tr","고덕S/S 345kV #4M.Tr C상 상부 누유보수","고덕S/S 345kV #4M.Tr C상 상부 누유보수","2022-07-01 09:00","2022-07-01 18:00","2022-07-01 09:00","2022-07-01 18:00","연속"]
[15,"경기","평택","고덕S/S #2 M.Tr"," 345kV 고덕#2S/S 건설공사"," 345kV 고덕#2S/S 건설공사","2022-07-04 09:00","2022-07-07 18:00","2022-07-04 09:00","2022-07-07 18:00","연속"]
[16,"경기","평택","고덕S/S CB 7372","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사 - 고덕#2S/S 345kV측 및 고덕-고덕#2 #1, 2T/L 선로가압","2022-07-18 09:00","2022-07-18 10:00","2022-07-18 09:00","2022-07-18 10:00","연속"]
[17,"경기","평택","고덕S/S #1M.Tr","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 건설공사 - 고덕#2S/S 345kV측 및 고덕-고덕#2 #1, 2T/L 선로가압","2022-07-18 09:00","2022-07-18 10:00","2022-07-18 09:00","2022-07-18 10:00","연속"]
[18,"경기","평택","고덕고덕2#2 T/L"," 345kV 고덕#2S/S 건설공사"," 345kV 고덕#2S/S 건설공사","2022-07-04 09:00","2022-07-07 10:00","2022-07-04 09:00","2022-07-07 10:00","연속"]
[19,"경기","평택","평택T/P #1 TIE Tr","평택T/P 345kV #1Tie-Tr 부싱 압력센서 교체","평택T/P 345kV #1Tie-Tr 1차 부싱 질소 압력센서 교체","2022-07-01 10:00","2022-07-01 14:00","2022-07-01 10:00","2022-07-01 14:00","연속"]
[20,"경기","평택","평택T/P #3 TIE Tr","평택T/P 345kV #3Tie-Tr 2차 GIS 접지본드 과열보수","평택T/P 345k #3Tie-Tr 2차 GIS 접지본드 과열보수","2022-07-02 09:00","2022-07-02 18:00","2022-07-02 09:00","2022-07-02 18:00","연속"]
[21,"경기","평택","평택T/P #2 TIE Tr","평택T/P 345kV #2Tie-Tr 96P 충격압력계전기 교체","평택T/P 345kV #2Tie-Tr A상 96P 교체","2022-07-01 14:00","2022-07-01 18:00","2022-07-01 14:00","2022-07-01 18:00","연속"]
[22,"강원","강릉","안인개폐소신양양 T/L","2022~2023년 강릉전력지사 가공송전협력회사 총액공사","○ 추락방지시설 설치(수직 및 수평) - 345kV 양양양수T/L No.1~180","2022-07-04 08:00","2022-07-22 18:00","2022-07-04 08:00","2022-07-22 18:00","매일"]
[23,"강원","동해","삼척G/P CB 7500","22~23년 동해전력지사 변전정비 총액공사","1. 누유개소 보수","2022-07-01 09:00","2022-07-01 18:00","2022-07-01 09:00","2022-07-01 18:00","연속"]
[24,"대전세종충남","청양","보령C/C SEC CB 75760","345kV 차단기 부동작 예방 조작시험(75-76)","345kV 차단기 부동작 예방 조작시험(75-76)","2022-07-06 14:00","2022-07-06 18:00","2022-07-06 14:00","2022-07-06 18:00","연속"]
[25,"대전세종충남","청양","보령C/C SEC CB 70710","345kV 차단기 부동작 예방 조작시험(70-71)","345kV 차단기 부동작 예방 조작시험(70-71)","2022-07-06 09:00","2022-07-06 14:00","2022-07-06 09:00","2022-07-06 14:00","연속"]
[26,"대전세종충남","청양","청양S/S SEC CB 75760","345kV 차단기 부동작 예방 조작시험(75-76)","345kV 차단기 부동작 예방 조작시험(75-76)","2022-07-06 14:00","2022-07-06 18:00","2022-07-06 14:00","2022-07-06 18:00","연속"]
[27,"대전세종충남","청양","청양S/S SEC CB 70710","345kV 차단기 부동작 예방 조작시험(70-71)","345kV 차단기 부동작 예방 조작시험(70-71)","2022-07-06 09:00","2022-07-06 14:00","2022-07-06 09:00","2022-07-06 14:00","연속"]
[28,"광주전남","목포","신남원한빛NP#1 T/L","한빛N/P #2S/Y 362kV GIS 대체공사","#70BUS 무부하 및 실부하가압(6.30~7.2)","2022-07-01 09:00","2022-07-02 18:00","2022-07-01 09:00","2022-07-02 18:00","연속"]
[29,"광주전남","순천","광양율촌CC T/L","22년 가공송전 순시점검 위탁공사","345kV 신남원-광양 #1T/L 17호 과열개소 정비관련 4회선구간 안전이격거리 확보","2022-07-07 08:00","2022-07-07 18:00","취소","취소","연속"]
[30,"광주전남","순천","신남원광양#1 T/L","22년 가공송전 순시점검 위탁공사","345kV 신남원-광양 #1T/L 17호 과열개소 정비","2022-07-07 08:00","2022-07-07 18:00","취소","취소","연속"]
[31,"광주전남","순천","광양S/S #1 M.Tr","광양S/S #1M.Tr 1차 GIS 상부 가스 누기 제작사 합동점검","광양S/S #1M.Tr 1차 GIS 상부 가스 누기 조치","2022-07-06 10:00","2022-07-07 18:00","2022-07-06 10:00","2022-07-07 18:00","연속"]
[32,"광주전남","순천","광양여수TP T/L","22년 가공송전 순시점검 위탁공사","345kV 신남원-광양 #1T/L 3, 7, 106호 과열개소 정비관련 4회선구간 안전이격거리 확보","2022-07-05 08:00","2022-07-05 18:00","취소","취소","연속"]
[33,"광주전남","순천","신남원광양#2 T/L","22년 가공송전 순시점검 위탁공사","345kV 신남원-광양 #2T/L 3, 7, 106호 과열개소 정비","2022-07-05 08:00","2022-07-06 18:00","취소","취소","매일"]
[34,"광주전남","순천","광양S/S SEC CB 70710","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345Kv #70-71BUS SEC GIS 초기점검","2022-07-04 10:00","2022-07-04 18:00","취소","취소","연속"]
[35,"광주전남","순천","신강진광양#1 T/L","22년 가공송전 순시점검 위탁공사","345kV 광양-하동TP #2T/L 73호 과열개소 정비관련 4회선 구간 안전이격거리 확보","2022-07-04 08:00","2022-07-04 18:00","취소","취소","연속"]
[36,"광주전남","순천","광양하동TP#2 T/L","22년 가공송전 순시점검 위탁공사","345kV 광양-하동TP #2T/L 73호 과열개소 정비","2022-07-04 08:00","2022-07-04 18:00","취소","취소","연속"]
[37,"광주전남","순천","신남원광양#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345Kv 신남원-광양#1T/L CVT(A, B상) 하자점검 및 (C상) 대체","2022-07-01 10:00","2022-07-01 18:00","취소","취소","연속"]
[38,"광주전남","순천","여수T/P #70 BUS","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y #70BUS PT FUSE FAIL 관련 단자대 교체","2022-07-05 10:00","2022-07-05 18:00","취소","취소","연속"]
[39,"광주전남","순천","여수T/P #1 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 수치 측정","2022-07-13 10:00","2022-07-13 15:00","취소","취소","연속"]
[40,"광주전남","순천","여수T/P #3 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 수치 측정","2022-07-14 10:00","2022-07-14 15:00","취소","취소","연속"]
[41,"광주전남","순천","여수T/P #2 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 수치 측정","2022-07-18 10:00","2022-07-18 15:00","취소","취소","연속"]
[42,"광주전남","순천","여수T/P #4 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 수치 측정","2022-07-19 10:00","2022-07-19 15:00","취소","취소","연속"]
[43,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S #3M.Tr 2차 철구 → GIS 부하전환","2022-07-18 08:30","2022-07-20 18:00","취소","취소","연속"]
[44,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구-남인동#1T/L, #4M.Tr 부하전환(철구 → GIS)","2022-07-04 08:30","2022-07-07 18:00","취소","취소","연속"]
[45,"대구","포항","신포항신영일 T/L","신영일S/S 신포항-신영일TL PT,LA대체","신영일S/S 신포항-신영일TL PT,LA대체","2022-07-05 09:00","2022-07-06 18:00","2022-07-05 09:00","2022-07-06 18:00","연속"]
[46,"대구","포항","월성NP신월성NP#2 T/L","염해방지 애자코팅 공사","신월성S/Y 72Bay 무부하가압선로","2022-07-21 09:00","2022-07-22 18:00","2022-07-21 09:00","2022-07-22 18:00","연속"]
[47,"대구","포항","신월성N/P CB 7100","신월성S/Y 7100,7172 GIS 정밀점검","신월성S/Y 7100,7172 GIS 정밀점검","2022-07-03 09:00","2022-07-08 18:00","2022-07-03 09:00","2022-07-08 18:00","연속"]
[48,"대구","포항","신월성N/P CB 7272","신월성S/Y 7200,7272 GIS 정밀점검 및 가스누기보수","신월성S/Y 7200,7272 GIS 정밀점검 및 가스누기보수","2022-07-14 09:00","2022-07-22 18:00","2022-07-14 09:00","2022-07-22 18:00","연속"]
[49,"대구","포항","신포항신월성NP#4 T/L","염해방지 애자코팅 공사","신월성S/Y 71Bay 무부하가압선로","2022-07-07 09:00","2022-07-08 18:00","2022-07-07 09:00","2022-07-08 18:00","연속"]
[50,"대구","포항","신월성N/P CB 7172","신월성S/Y 7100,7172 GIS 정밀점검","신월성S/Y 7100,7172 GIS 정밀점검","2022-07-03 09:00","2022-07-08 18:00","2022-07-03 09:00","2022-07-08 18:00","연속"]
[51,"대구","포항","신월성N/P CB 7200","신월성S/Y 7200,7272 GIS 정밀점검 및 가스누기보수","신월성S/Y 7200,7272 GIS 정밀점검 및 가스누기보수","2022-07-14 09:00","2022-07-22 18:00","2022-07-14 09:00","2022-07-22 18:00","연속"]
[52,"대구","포항","월성N/P SEC CB 70710","월성S/Y 70-71 GIS 조작시험","월성S/Y 70-71 GIS 조작시험","2022-07-11 09:00","2022-07-11 14:00","2022-07-11 09:00","2022-07-11 14:00","연속"]
[53,"대구","포항","월성N/P SEC CB 75760","월성S/Y 75-76 GIS 조작시험","월성S/Y 75-76 GIS 조작시험","2022-07-11 14:00","2022-07-11 18:00","2022-07-11 14:00","2022-07-11 18:00","연속"]
[54,"부산울산","동부산","신양산S/S #4 M.Tr","안전이격확보(신양산S/S 345kV M.Tr 3차측 현대화 공사)","안전이격확보(345kV #4M.Tr 3차측 현대화공사)","2022-07-06 10:00","2022-07-06 18:00","2022-07-06 10:00","2022-07-06 18:00","연속"]
[55,"부산울산","동부산","신양산S/S #2 M.Tr","안전이격확보(신양산S/S 345kV M.Tr 3차측 현대화 공사)","안전이격확보(345kV #2M.Tr 3차측 현대화공사)","2022-07-07 10:00","2022-07-07 18:00","2022-07-07 10:00","2022-07-07 18:00","연속"]
[56,"부산울산","동부산","신양산S/S #1 M.Tr","안전이격확보(신양산S/S 345kV M.Tr 3차측 현대화 공사)","안전이격확보(345kV #1M.Tr 3차측 현대화공사)","2022-07-08 10:00","2022-07-08 18:00","2022-07-08 10:00","2022-07-08 18:00","연속"]
[57,"부산울산","서부산","서부산S/S 부산복합 #3,4 G/T 주변압기 (CB 7400, 7472)","서부산S/S 345kV #3,4 G/T GIS 동작시험","서부산S/S 345kV #3,4 G/T GIS 동작시험","2022-07-11 09:00","2022-07-11 18:00","2022-07-11 09:00","2022-07-11 18:00","연속"]
[58,"부산울산","서부산","서부산S/S CB 7300","서부산S/S 345kV 7300 TIE GIS 동작시험","서부산S/S 345kV 7300 TIE GIS 동작시험","2022-07-08 09:00","2022-07-08 18:00","취소","취소","연속"]
[59,"부산울산","서부산","서부산S/S #1 M.Tr","서부산S/S 345kV #1 M.Tr 1차 GIS 동작시험","서부산S/S 345kV #1 M.Tr 1차 GIS 동작시험","2022-07-06 09:00","2022-07-06 18:00","취소","취소","연속"]
[60,"부산울산","서부산","서부산S/S CB 7271","서부산S/S 345kV 서부산-북부산#2T/L GIS 동작시험","서부산S/S 345kV 서부산-북부산#2T/L GIS 동작시험","2022-07-05 09:00","2022-07-05 18:00","2022-07-05 09:00","2022-07-05 18:00","연속"]
[61,"부산울산","서부산","서부산S/S CB 7200","서부산S/S 북부산#2T/L-#1 M.Tr 1차 TIE GIS 동작시험","서부산S/S 북부산#2T/L-#1 M.Tr 1차 TIE GIS 동작시험","2022-07-04 09:00","2022-07-04 18:00","취소","취소","연속"]
[62,"부산울산","서부산","서부산S/S CB 7500","서부산S/S 345kV 7500 BUS-TIE GIS 동작시험","서부산S/S 345kV 7500 BUS-TIE GIS 동작시험","2022-07-12 09:00","2022-07-12 18:00","2022-07-12 09:00","2022-07-12 18:00","연속"]
[63,"부산울산","서부산","서부산S/S CB 7100","서부산S/S 345kV 7100 BUS-TIE GIS 초기점검","서부산S/S 345kV 7100 BUS-TIE GIS 초기점검","2022-07-13 09:00","2022-07-13 18:00","취소","취소","연속"]
[64,"부산울산","서부산","서부산S/S CB 7171","서부산S/S 345kV 서부산-북부산#1T/L GIS 초기점검","서부산S/S 345kV 서부산-북부산#1T/L GIS 초기점검","2022-07-14 09:00","2022-07-14 18:00","2022-07-14 09:00","2022-07-14 18:00","연속"]
[65,"부산울산","서부산","서부산S/S #2 M.Tr","서부산S/S 345kV #2 M.Tr 1차 GIS 초기점검","서부산S/S 345kV #2 M.Tr 1차 GIS 초기점검","2022-07-15 09:00","2022-07-15 18:00","취소","취소","연속"]
[66,"부산울산","울산","신울산S/S #75 BUS","신울산S/S 345kV 차단기 용량대체공사","345kV #1M.Tr 1차측 인출 변경 관련 안전이격거리 확보","2022-07-01 09:00","2022-07-01 18:00","2022-07-01 09:00","2022-07-01 18:00","연속"]
[67,"경남","진주","의령S/S #2 M.Tr","의령S/S #2M.Tr C상 H1부싱 절연열화 측정","의령S/S #2M.Tr C상 H1부싱 절연열화 측정","2022-07-05 09:00","2022-07-05 15:00","2022-07-05 09:00","2022-07-05 15:00","연속"]
[68,"대구",null,"신월성N/P #2 대기보조변압기 (CB 7200, 7272)","신월성 2호기 5차  계획예방정비, #2 대기보조변압기(SAT) 점검, *조작차단기 : PCB 7200, 7272","○ 대기보조변압기 일반점검 등","2022-07-08 09:00","2022-07-22 18:00","2022-07-08 09:00","2022-07-22 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":84,"n_cols":11,"rows_kept":84,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 7월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","직할","서소문S/S #2 BUS","22년 154kV GIS 정밀점검 공사","-#4M.Tr 1차 시험가압용","2022-07-05 10:00","2022-07-05 18:00","취소","취소","연속"]
[2,"남서울","강남","과천동안양#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 과천-동안양#2","2022-07-11 08:00","2022-07-13 18:00","2022-07-11 08:00","2022-07-13 18:00","연속"]
[3,"남서울","강남","신양재과천#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-과천2","2022-07-11 08:00","2022-07-13 18:00","2022-07-11 08:00","2022-07-13 18:00","연속"]
[4,"남서울","강남","신양재과천#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-과천1","2022-07-04 08:00","2022-07-06 18:00","2022-07-04 08:00","2022-07-06 18:00","연속"]
[5,"남서울","강남","과천동안양#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 과천-동안양#1","2022-07-04 08:00","2022-07-06 18:00","2022-07-04 08:00","2022-07-06 18:00","연속"]
[6,"남서울","강남","교대이수#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 2M.TR 1차, 교대-이수#2T/L GIS - 무부하 : 60BUS, 65BUS, 교대이수#1T/L","2022-07-01 16:00","2022-07-01 18:00","2022-07-01 16:00","2022-07-01 18:00","연속"]
[7,"남서울","동서울","위례S/S #66 BUS","154kV 동서울2-위례#2T/L 무부하가압","O 154kV 동서울2-위례#2T/L 무부하가압 O 인터록, 상 체크","2022-07-23 14:00","2022-07-24 14:00","2022-07-23 14:00","2022-07-24 14:00","연속"]
[8,"남서울","동서울","위례S/S CB 6100","154kV 동서울2-위례#1T/L SW 증설공사","○ 154kV 동서울2-위례#1T/L 무부하가압 ○ 인터록, 상 확인","2022-07-16 10:00","2022-07-17 14:00","2022-07-16 10:00","2022-07-17 14:00","연속"]
[9,"남서울","동서울","위례S/S #60 BUS","154kV 동서울2-위례#1T/L SW 증설공사","○ 154kV 동서울2-위례#1T/L 무부하가압 ○ 인터록, 상 확인","2022-07-16 14:00","2022-07-17 14:00","2022-07-16 14:00","2022-07-17 14:00","연속"]
[10,"남서울","동서울","위례S/S #65 BUS","154kV 동서울2-위례#1T/L SW 증설공사","○ 154kV 동서울2-위례#1T/L 무부하가압 ○ 인터록, 상 확인","2022-07-16 10:00","2022-07-16 14:00","2022-07-16 10:00","2022-07-16 14:00","연속"]
[11,"남서울","동서울","위례S/S CB 6200","154kV 동서울2-위례#2T/L 무부하 가압","O 154kV 동서울2-위례#2T/L 무부하가압 O 인터록, 상 확인","2022-07-23 10:00","2022-07-24 14:00","2022-07-23 10:00","2022-07-24 14:00","연속"]
[12,"남서울","동서울","위례S/S #61 BUS","154kV 동서울2-위례#2T/L 무부하 가압","O 154kV 동서울2-위례#2T/L 무부하가압 O 인터록, 상 확인","2022-07-23 10:00","2022-07-23 14:00","2022-07-23 10:00","2022-07-23 14:00","연속"]
[13,"남서울","직할","대방신길#1 T/L","'21-'22년 지중송전 정비전문회사 총액공사","○ 작 업 명 : 절연유 채유 ○ 작업개소 : J/B#23-2, #29, #38 ○ 작업내용 : 절연유 채유 및 열화분석","2022-07-02 09:00","2022-07-02 12:00","2022-07-02 09:00","2022-07-02 12:00","연속"]
[14,"인천","김포","신김포S/S SEC CB 65660","신김포S/S 170kV 65-66 SEC GIS 보통점검","신김포S/S 170kV 65-66 SEC GIS 보통점검","2022-07-04 10:00","2022-07-04 18:00","2022-07-04 10:00","2022-07-04 18:00","연속"]
[15,"인천","김포","신김포S/S SEC CB 60610","신김포S/S 170kV 60-61 SEC GIS 하자점검","신김포S/S 170kV 60-61 SEC GIS 하자점검","2022-07-01 10:00","2022-07-01 18:00","2022-07-01 10:00","2022-07-01 18:00","연속"]
[16,"인천","시흥","서시화S/S KGETS T/L (CB 657)","서시화S/S 154kV KG에너지T/L 보호반 대체","서시화S/S 154kV KG에너지T/L 보호반 대체","2022-07-30 08:00","2022-07-31 23:00","2022-07-30 08:00","2022-07-31 23:00","연속"]
[17,"경기북부","구리","덕소진건#2 T/L","진건S/S #4M.Tr 증설공사","진건S/S #4M.Tr 증설공사 - M.Tr, GIS, SIS 시험가압 선로","2022-07-01 09:00","2022-07-02 18:00","2022-07-01 09:00","2022-07-02 18:00","연속"]
[18,"경기","군포","서안양소래 T/L","서안양SS 170kV 서안양-소래TL GIS 정밀점검","서안양SS 170kV 서안양-소래TL GIS 정밀점검","2022-07-02 09:00","2022-07-03 18:00","2022-07-02 09:00","2022-07-03 18:00","연속"]
[19,"경기","성남","진위동탄#1 T/L","동탄S/S #4M.Tr 증설공사","- #4M.Tr 무부하가압","2022-07-14 14:00","2022-07-15 16:00","2022-07-14 14:00","2022-07-15 16:00","연속"]
[20,"경기","성남","진위동탄#1 T/L","동탄S/S #4M.Tr 증설공사","- #4M.Tr 1차 GIS 무부하가압","2022-07-08 16:00","2022-07-09 16:00","2022-07-08 16:00","2022-07-09 16:00","연속"]
[21,"경기","직할","봉담남수원#1 T/L","154kV 봉담S/S #1M.Tr 증설공사","봉담S/S #1M.Tr 증설공사(154kV GIS 1Bay 증설) - #60BUS 및 Main Bay 무부하가압","2022-07-16 09:00","2022-07-18 09:00","2022-07-16 09:00","2022-07-18 09:00","연속"]
[22,"경기","직할","봉담남수원#1 T/L","154kV 봉담S/S #1M.Tr 증설공사","봉담S/S #1M.Tr 증설공사(154kV GIS 1Bay 증설) - #65BUS 무부하가압","2022-07-09 09:00","2022-07-11 09:00","2022-07-09 09:00","2022-07-11 09:00","연속"]
[23,"경기","직할","고덕#2동평택#2 T/L"," 고덕2S/S 154kV 신규수용공사(에어퍼스트)"," 에어퍼스트T/L(6B Bay) GIS 증설","2022-07-07 10:00","2022-07-08 10:00","2022-07-07 10:00","2022-07-08 10:00","연속"]
[24,"경기","직할","고덕#2고덕 T/L"," 고덕2S/S 154kV 신규수용공사(에어퍼스트)"," 에어퍼스트T/L(64 Bay) GIS 증설","2022-07-19 10:00","2022-07-20 10:00","2022-07-19 10:00","2022-07-20 10:00","연속"]
[25,"경기","직할","고덕#2고덕 T/L"," 고덕2S/S 154kV 신규수용공사(에어퍼스트)"," 에어퍼스트T/L(64 Bay) GIS 증설","2022-07-28 10:00","2022-07-29 10:00","2022-07-28 10:00","2022-07-29 10:00","연속"]
[26,"강원","강릉","주진평창#1 T/L","2022~2023년 강릉전력지사 가공송전협력회사 총액공사","○ 압축인류클램프 부풀음개소 정비 - 154kV 주진-평창#1T/L 주진S/S 및 평창S/S 인출부분","2022-07-01 12:00","2022-07-01 18:00","2022-07-01 12:00","2022-07-01 18:00","연속"]
[27,"강원","강릉","주진평창#2 T/L","2022~2023년 강릉전력지사 가공송전협력회사 총액공사","○ 압축인류클램프 부풀음개소 정비 - 154kV 주진-평창#2T/L 주진S/S 인출부분","2022-07-01 08:00","2022-07-01 12:00","2022-07-01 08:00","2022-07-01 12:00","연속"]
[28,"충북","청주","신옥천추부#1 T/L","170kV GIS 하자점검","[22-23 청주전력 변전정비 총액공사] 170kV GIS 하자점검","2022-07-01 10:00","2022-07-01 18:00","2022-07-01 10:00","2022-07-01 18:00","연속"]
[29,"충북","충주","신충주감곡#2 T/L","신충주S/S 154kV GIS 설치공사","#1Sh.C GIS 설치 후 무부하가압 (즉시가압 가능)","2022-07-03 18:00","2022-07-04 18:00","2022-07-03 18:00","2022-07-04 18:00","연속"]
[30,"충북","충주","신충주감곡#2 T/L","신충주S/S 154kV GIS 설치공사","#1Sh.C GIS 설치 후 무부하가압 (즉시가압 가능)","2022-07-05 18:00","2022-07-06 18:00","2022-07-05 18:00","2022-07-06 18:00","연속"]
[31,"대전세종충남","서산","신당진서산#1 T/L","서산P/O 154kV GIS 정밀점검공사","서산S/S 154kV 신당진-서산#1T/L 647 GIS 정밀점검","2022-07-11 09:00","2022-07-14 18:00","2022-07-11 09:00","2022-07-14 18:00","연속"]
[32,"대전세종충남","천안","아산S/S CB 6100","아산S/S 154kV B/T 6100GIS 초기점검","아산S/S 154kV B/T 6100GIS 초기점검","2022-07-05 09:00","2022-07-05 18:00","2022-07-05 09:00","2022-07-05 18:00","연속"]
[33,"대전세종충남","천안","아산예산#1 T/L","154kV 예산S/S 미래화공사(일반)","154kV 예산S/S 미래화공사(일반) - 아산-예산#1T/L 인출변경(옥외철구 → 신설GIS)","2022-07-21 10:00","2022-07-25 17:00","2022-07-21 10:00","2022-07-25 17:00","연속"]
[34,"대전세종충남","천안","아산인주#1 T/L","인주S/S 154kV 아산-인주#1T/L 개폐타임 측정 및 CVT대체","인주S/S 154kV 아산-인주#1T/L 개폐타임 측정 및 CVT대체","2022-07-04 09:00","2022-07-04 18:00","취소","취소","연속"]
[35,"대전세종충남","천안","천안S/S CB 6100","[송전] 154kV 장재-천안T/L No.19~21 새텃말지구 지중화공사","154kV 장재-천안T/L No.19~21 새텃말지구 지중화공사(요청자 직접시행) - 선로정수 및 상확인시험","2022-07-16 09:00","2022-07-17 18:00","2022-07-16 09:00","2022-07-17 18:00","연속"]
[36,"대전세종충남","천안","천안S/S #1 BUS","[송전] 154kV 장재-천안T/L No.19~21 새텃말지구 지중화공사","154kV 장재-천안T/L No.19~21 새텃말지구 지중화공사(요청자 직접시행) - 무부하가압을 위한 #1→2BUS 절체","2022-07-16 09:00","2022-07-17 18:00","2022-07-16 09:00","2022-07-17 18:00","연속"]
[37,"대전세종충남","천안","서천안탕정#2 T/L","탕정·서천안S/S 서천안-탕정#1,2TL 고장파급시스템 설치","탕정·서천안S/S 서천안-탕정#1,2TL 고장파급시스템 설치","2022-07-06 14:00","2022-07-06 18:00","2022-07-06 14:00","2022-07-06 18:00","연속"]
[38,"대전세종충남","천안","서천안탕정#1 T/L","탕정·서천안S/S 서천안-탕정#1,2TL 고장파급시스템 설치","탕정·서천안S/S 서천안-탕정#1,2TL 고장파급시스템 설치","2022-07-06 09:00","2022-07-06 14:00","2022-07-06 09:00","2022-07-06 14:00","연속"]
[39,"대전세종충남","청양","동군산장항#1 T/L","154kV 동군산-장항#1T/L 관련기기 점검","- 차단기 부동작 예방 조작시험(647) - LA 및 CVT 대체","2022-07-01 09:00","2022-07-01 18:00","2022-07-01 09:00","2022-07-01 18:00","연속"]
[40,"전북","김제","정주고창#1 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-07-12 15:00","2022-07-12 18:00","2022-07-12 15:00","2022-07-12 18:00","연속"]
[41,"전북","김제","신김제남전주#2 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-07-09 15:00","2022-07-09 18:00","2022-07-09 15:00","2022-07-09 18:00","연속"]
[42,"전북","김제","신김제남전주#2 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검 시험가압선로","2022-07-06 15:00","2022-07-06 18:00","2022-07-06 15:00","2022-07-06 18:00","연속"]
[43,"광주전남","강진","남창S/S 모선연계T/L (CB 687G)","2022~23년 강진전력지사 변전협력회사 총액공사","남창S/S 모선연결T/L GIS 초기점검","2022-07-04 10:00","2022-07-04 14:00","취소","취소","연속"]
[44,"광주전남","광주","충장농성#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 계림-농성#2T/L 조작시험 (즉시가압 불가)","2022-07-01 14:00","2022-07-01 18:00","취소","취소","연속"]
[45,"광주전남","광주","충장농성#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 계림-농성#1T/L 조작시험 (즉시가압 불가)","2022-07-01 09:00","2022-07-01 14:00","취소","취소","연속"]
[46,"광주전남","직할","매월화정#1 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","매월S/S 매월화정#1,2T/L GIS 보통점검 (즉시가압 가능)","2022-07-05 09:00","2022-07-05 14:00","취소","취소","연속"]
[47,"광주전남","직할","매월화정#2 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","매월S/S 매월화정#1,2T/L GIS 보통점검 (즉시가압 가능)","2022-07-05 14:00","2022-07-05 18:00","취소","취소","연속"]
[48,"광주전남","직할","비아하남#2 T/L","2022∼23년 광주전남본부 직할 변전협력회사 총액공사","CVT 대체, LA 초기좀검, 장기미동작 차단기 점검, 공기배출밸브 구조개선","2022-07-15 09:00","2022-07-15 18:00","2022-07-15 09:00","2022-07-15 18:00","연속"]
[49,"대구","칠곡","서대구칠곡#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S 칠곡#1T/L 인출변경 관련 안전이격 확보","2022-07-21 08:30","2022-07-21 18:00","취소","취소","연속"]
[50,"대구","칠곡","북대구연락#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S 철구 및 GIS 간 임시모선연계","2022-07-14 08:30","2022-07-16 18:00","취소","취소","연속"]
[51,"대구","칠곡","북대구연락#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S 부하전환(철구 → GIS)","2022-07-14 08:30","2022-07-16 18:00","취소","취소","연속"]
[52,"대구","칠곡","서대구칠곡#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S 부하전환(철구 → GIS) 및 칠곡S/S 보호반 교체","2022-07-11 08:30","2022-07-13 18:00","취소","취소","연속"]
[53,"대구","칠곡","서대구남인동#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구-남인동#1T/L, #4M.Tr 부하전환(철구 → GIS)","2022-07-04 08:30","2022-07-07 18:00","취소","취소","연속"]
[54,"대구","칠곡","서대구남인동#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S 남인동#2T/L 철구 → GIS 부하전환","2022-07-18 08:30","2022-07-20 18:00","취소","취소","연속"]
[55,"대구","칠곡","서대구칠곡#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S 남인동#2T/L 철구 → GIS 부하전환","2022-07-21 08:30","2022-07-23 18:00","취소","취소","연속"]
[56,"경북","구미","선산구미#2T/L","154kV 선산-구미T/L 지장송전선로 임시이설 공사","1. 선 로 명 : 154kV 선산-구미T/L 2. 구 간 : 154kV 선산-구미T/L No.17-20 3. 공사수량 - 지지물 : 철거 2기(18-19), 설치 3기(18,18-1,19) - 전력선 : 철거 ACSR 410㎟ x 2B x 2C x 1km, ACSR 97㎟ x S x 1km 설치 ACSR 410㎟ x 2B","2022-06-28 09:00","2022-07-08 18:00","취소","취소","연속"]
[57,"경북","직할","풍산안동CC#2 T/L","풍산S/S #3M.Tr 증설 및 모선보강공사","○ 안동CC-풍산#2T/L 모선보호반 제어케이블 결선변경 ( #60-#65 모선보호반 → #61-#66모선보호반 )","2022-07-04 09:00","2022-07-05 18:00","2022-07-04 09:00","2022-07-05 18:00","연속"]
[58,"경북","직할","풍산안동CC#1 T/L","풍산S/S #3M.Tr 증설 및 모선보강공사","○ 안동CC-풍산#1T/L 모선보호반 제어케이블 결선변경 ( #60-#65 모선보호반 → #61-#66모선보호반 )","2022-07-06 09:00","2022-07-07 18:00","2022-07-06 09:00","2022-07-07 18:00","연속"]
[59,"경북","직할","풍산동상주개폐소 T/L","풍산S/S #3M.Tr 증설 및 모선보강공사","○ 동상주-풍산T/L 모선보호반 제어케이블 결선변경 ( #60-#65 모선보호반 → #61-#66모선보호반 )","2022-07-08 09:00","2022-07-11 18:00","2022-07-08 09:00","2022-07-11 18:00","연속"]
[60,"경북","직할","풍산안동CC#2 T/L","풍산S/S #3M.Tr 증설 및 모선보강공사","○ #3M.Tr 및 154, 23kV GIS 무부하가압","2022-07-21 09:00","2022-07-22 18:00","2022-07-21 09:00","2022-07-22 18:00","연속"]
[61,"부산울산","북부산","북부산미남#2 T/L","154kV 북부산-미남T/L OPGW 증설공사","북부산-미남간 OPGW 증설 : 6.2km","2022-07-04 08:00","2022-07-08 18:00","2022-07-18 08:00","2022-07-22 18:00","연속"]
[62,"부산울산","울산","신울산두왕#1 T/L","신울산S/S 154kV 현대화공사","기설 GCB, 모선DS 철거 및 M.Tr 2차 지중관로 공사 복귀 시 현대화(GIS) 설비로 복귀","2022-07-04 08:30","2022-11-09 18:00","2022-07-04 08:30","2022-11-09 18:00","연속"]
[63,"부산울산","울산","신울산S/S #62 BUS","신울산S/S 154kV 현대화공사","두왕#1 T/L 모선측 DS 철거","2022-07-05 08:00","2022-07-06 18:00","2022-07-05 08:00","2022-07-06 18:00","연속"]
[64,"부산울산","울산","신울산S/S #67 BUS","신울산S/S 154kV 현대화공사","두왕#1 T/L 모선측 DS 철거","2022-07-04 08:30","2022-07-04 18:00","2022-07-04 08:30","2022-07-04 18:00","연속"]
[65,"부산울산","울산","남울산처용#2 T/L","22~23년 변전협력회사 총액공사","- 처용S/S 시스템화","2022-07-04 09:00","2022-07-05 18:00","2022-07-04 09:00","2022-07-06 18:00","연속"]
[66,"부산울산","울산","남울산처용#1 T/L","22~23년 변전협력회사 총액공사","- 처용S/S 시스템화","2022-07-06 09:00","2022-07-07 18:00","2022-07-07 09:00","2022-07-09 18:00","연속"]
[67,"부산울산","직할","부산수정#1 T/L","21-22년 서부산전력지사 지중송전위탁 정비공사","OF케이블 절연유 시료채취 작업","2022-07-04 09:00","2022-07-06 18:00","2022-07-04 09:00","2022-07-06 18:00","연속"]
[68,"부산울산","직할","부산수정#2 T/L","21-22년 서부산전력지사 지중송전위탁 정비공사","OF케이블 절연유 시료채취 작업","2022-07-11 09:00","2022-07-13 18:00","2022-07-11 09:00","2022-07-13 18:00","연속"]
[69,"경남","직할","신김해진례#2 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-07-02 08:00","2022-07-03 18:00","2022-07-02 08:00","2022-07-03 18:00","연속"]
[70,"경남","직할","신월삼정#1 T/L","신월S/S 신월-삼정#1T/L 조작시험","신월S/S 신월-삼정#1T/L 조작시험","2022-07-01 09:30","2022-07-01 17:30","2022-07-01 09:30","2022-07-01 17:30","연속"]
[71,"경남","직할","신월삼정#2 T/L","신월S/S 신월-삼정#2T/L 조작시험","신월S/S 신월-삼정#2T/L 조작시험","2022-07-04 09:30","2022-07-04 17:30","2022-07-04 09:30","2022-07-04 17:30","연속"]
[72,"경남","진주","개양S/S CB 6100","개양S/S 154kV #1BUS-TIE(6100) GIS 조작시험","개양S/S 154kV #1BUS-TIE(6100) GIS 조작시험","2022-07-01 10:00","2022-07-01 18:00","2022-07-01 10:00","2022-07-01 18:00","연속"]
[73,"경남","진주","의령S/S CB 6100","의령S/S 154kV #1BUS-TIE(6100) GIS 조작시험","의령S/S 154kV #1BUS-TIE(6100) GIS 조작시험","2022-07-01 10:00","2022-07-01 18:00","2022-07-01 10:00","2022-07-01 18:00","연속"]
[74,"경남","진주","진주S/S CB 6100","진주S/S 154kV #1BUS-TIE(6100) GCB 조작시험","진주S/S 154kV #1BUS-TIE(6100) GCB 조작시험","2022-07-04 10:00","2022-07-04 18:00","2022-07-04 10:00","2022-07-04 18:00","연속"]
[75,"경남","진주","하동S/S CB 6100","하동S/S 154kV #1BUS-TIE(6100) GIS 조작시험","하동S/S 154kV #1BUS-TIE(6100) GIS 조작시험","2022-07-04 10:00","2022-07-04 18:00","2022-07-04 10:00","2022-07-04 18:00","연속"]
[76,"경남","함안","매리김해#2 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : 전력선 및 가공지선 설치","2022-07-09 07:00","2022-07-12 18:00","2022-07-16 07:00","2022-07-19 18:00","연속"]
[77,"경남","함안","호포매리#2 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : 전력선 및 가공지선 설치","2022-07-09 07:00","2022-07-12 18:00","2022-07-16 07:00","2022-07-19 18:00","연속"]
[78,"경남","함안","매리김해#1 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : 전력선 및 가공지선 설치","2022-07-02 07:00","2022-07-05 18:00","2022-07-09 07:00","2022-07-12 18:00","연속"]
[79,"경남","함안","호포매리#1 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : 전력선 및 가공지선 설치","2022-07-02 07:00","2022-07-05 18:00","2022-07-09 07:00","2022-07-12 18:00","연속"]
[80,"경남","함안","매리김해#2 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 신설철탑 전력선 설치관련 안전이격","2022-07-02 07:00","2022-07-02 15:00","2022-07-09 07:00","2022-07-09 15:00","연속"]