{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":13,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":13,"n_cols":11,"rows_kept":13,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 10월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"강원","태백","신태백S/S #4 M.Tr","22-23년 태백전력지사 변전협력회사 총액공사","345kV 77Bay B/F PNL 교체","2022-10-24 10:00","2022-10-27 18:00","2022-10-24 10:00","2022-10-27 18:00","연속"]
[2,"충북","직할","신중부S/S CB 8871","신중부S/S 765kV GIS 하자보수","현대제 GIS 내부정밀점검 및 부품교체","2022-10-13 09:00","2022-10-22 09:00","2022-10-11 09:00","2022-10-21 18:00","연속"]
[3,"충북","직할","신중부S/S CB 8700","신중부S/S 765kV GIS 하자보수","현대제 GIS 내부정밀점검 및 부품교체","2022-10-24 09:00","2022-10-29 09:00","2022-10-24 09:00","2022-11-01 18:00","연속"]
[4,"충북","직할","신중부신안성#1 T/L","765kV 신중부-신안성#1T/L 항공표시구 교체","765kV 신중부-신안성#1T/L 항공표시구 교체(28~30, 31~32호)","2022-10-29 09:00","2022-10-31 08:00","취소","취소","연속"]
[5,"충북","직할","신중부신안성#2 T/L","765kV 신중부-신안성T/L OPGW 항공장애표시구 교체공사","1. 공사구간 : #2T/L 28~30호, 31~32호(3경간) 2. 공사내용 ○ 승탑전 철탑 5기 및 선로 1,675m 드론 점검 ○ 풍소음 방지용 항공장애표시구 17개 교체","2022-10-22 09:00","2022-10-24 08:00","취소","취소","연속"]
[6,"대전세종충남","서산","신서산S/S #1 BUS","신서산S/S 765kV #80BUS 보호반 대체공사","신서산S/S 765kV #80BUS 보호반 대체공사","2022-10-17 09:00","2022-10-21 18:00","취소","취소","연속"]
[7,"부산울산","동부산","신고리N/P CB 8500","신고리S/S 765kV GIS 보통점검","신고리S/S 765kV GIS 보통점검(8500)","2022-10-24 09:00","2022-10-26 18:00","2022-10-24 09:00","2022-10-26 18:00","연속"]
[8,"경남","함안","북경남S/S #3 M.Tr","북경남S/S 765kV #3 M.Tr 8562DS 가스누기 불량조치","북경남S/S 765kV #3 M.Tr 8562DS 가스누기 불량조치","2022-10-17 09:30","2022-10-21 17:30","2022-10-17 09:30","2022-10-21 17:30","연속"]
[9,"충북","직할","신중부S/S #1 BUS","무부하 가압활용 (CB 8871 하자보수 후)","무부하 가압활용 (CB 8871 하자보수 후)","2022-10-21 09:00","2022-10-21 18:00","2022-10-21 09:00","2022-10-21 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":310,"n_cols":11,"rows_kept":310,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2022년도 10월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr","2022년 성동P/O 변전협력회사 총액공사","-154kV GIS 보통점검 -변압기실 FAN 교체","2022-10-19 09:00","2022-10-20 20:00","취소","취소","연속"]
[2,"서울","성동","성동S/S #1 M.Tr","2022년 성동P/O 변전협력회사 총액공사","-154kV GIS 보통점검 -변압기실 FAN 교체","2022-10-17 09:00","2022-10-18 20:00","취소","취소","연속"]
[3,"서울","중부","중부S/S #2 BUS","22-23년 중부P/O 총액공사","362kV PT 보통점검","2022-10-05 14:00","2022-10-05 17:00","2022-10-05 14:00","2022-10-05 17:00","연속"]
[4,"서울","중부","중부S/S #1 BUS","22-23년 중부P/O 총액공사","362kV PT 보통점검","2022-10-05 10:00","2022-10-05 14:00","2022-10-05 10:00","2022-10-05 14:00","연속"]
[5,"남서울","동서울","신성남동서울#1 T/L","동서울SS 345kV 신성남-동서울#1T/L GIS(7571)조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-10-01 09:00","2022-10-01 14:00","2022-10-01 09:00","2022-10-01 14:00","연속"]
[6,"남서울","동서울","동서울미금#2 T/L","'22~'23년 동서울전력지사 가공송전 협력회사 총액공사","점퍼지지애자 교체공사","2022-10-13 07:00","2022-10-13 13:00","2022-10-13 07:00","2022-10-13 13:00","연속"]
[7,"남서울","동서울","동서울미금#1 T/L","'22~'23년 동서울전력지사 가공송전 협력회사 총액공사","점퍼지지애자 교체공사","2022-10-06 07:00","2022-10-06 13:00","2022-10-06 07:00","2022-10-06 13:00","연속"]
[8,"남서울","동서울","동서울S/S #4 M.Tr","동서울S/S 154kV 옥외철구 GIS화 공사","○ 옥외철구-&gtGIS 운전전환 * 34CCT ○ 기타 부대작업 * 1식","2022-10-17 09:00","2022-11-03 18:00","2022-10-17 09:00","2022-11-03 18:00","연속"]
[9,"남서울","영등포","신시흥신광명#1 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","63kA GIS 24CB 설치","2022-10-15 09:00","2022-10-15 14:00","2022-10-15 09:00","2022-10-15 14:00","연속"]
[10,"남서울","영등포","신광명S/S #70 BUS","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","63kA GIS 24CB 설치","2022-10-15 14:00","2022-10-16 14:00","2022-10-15 14:00","2022-10-16 14:00","연속"]
[11,"남서울","영등포","서서울신광명#1 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","63kA GIS 24CB 설치","2022-10-15 14:00","2022-10-16 14:00","2022-10-15 14:00","2022-10-16 14:00","연속"]
[12,"남서울","영등포","신시흥신광명#2 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설)","345kV 신시흥-신광명#2T/L 철탑 암 추락방지시설 설치","2022-10-29 08:00","2022-10-30 18:00","2022-10-29 08:00","2022-10-30 18:00","연속"]
[13,"남서울","영등포","신광명S/S #75 BUS","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","63kA GIS 24CB 설치","2022-10-15 09:00","2022-10-15 14:00","2022-10-15 09:00","2022-10-15 14:00","연속"]
[14,"남서울","영등포","신광명S/S SEC CB 70710","2022~2023년 영등포P/O 변전협력회사 총액공사","345kV 70-71 GCB 보통점검","2022-10-31 09:00","2022-10-31 18:00","2022-10-31 09:00","2022-10-31 18:00","연속"]
[15,"남서울","영등포","신광명S/S CB 7300","2022~2023년 영등포P/O 변전협력회사 총액공사","345kV 7300 GCB 보통점검","2022-10-25 09:00","2022-10-25 18:00","취소","취소","연속"]
[16,"남서울","영등포","신광명S/S CB 7172","2022~2023년 영등포P/O 변전협력회사 총액공사","345kV 7172 GCB 보통점검","2022-10-24 09:00","2022-10-24 18:00","취소","취소","연속"]
[17,"남서울","영등포","신광명S/S #3 M.Tr","2022~2023년 영등포P/O 변전협력회사 총액공사","- 신광명S/S #3M.Tr 부싱 절연유 채유 - 362kV 7271,7200 GCB 조작시험","2022-10-19 09:00","2022-10-20 18:00","2022-10-19 09:00","2022-10-20 18:00","연속"]
[0,"남서울","영등포","서서울신광명#2 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","구내전력구 시공관련 지장 LA 이설","2022-10-19 10:00","2022-10-28 18:00","2022-10-19 10:00","2022-10-28 18:00","연속"]
[19,"남서울","영등포","신광명S/S #1 M.Tr","2022~2023년 영등포P/O 변전협력회사 총액공사","- 신광명S/S #1M.Tr 부싱 절연유 채유 - 362kV 7471, 7400 GIS 조작시험","2022-10-17 09:00","2022-10-18 18:00","2022-10-17 09:00","2022-10-18 18:00","연속"]
[20,"남서울","직할","신문래S/S #3 Sh.R (CB 7379)","362kV GIS 정밀점검공사(#3Sh.R)","362kV GIS 정밀점검공사(#3Sh.R)","2022-10-17 09:00","2022-10-21 18:00","취소","취소","연속"]
[21,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥#1S/S 345kV #1 M.Tr 부싱 절연유 채유","신시흥#1S/S 345kV #1 M.Tr 부싱 절연유 채유","2022-10-01 09:00","2022-10-01 14:00","2022-10-01 09:00","2022-10-01 14:00","연속"]
[22,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥#1S/S 345kV #2 M.Tr 부싱 절연유 채유","신시흥#1S/S 345kV #2 M.Tr 부싱 절연유 채유","2022-10-01 14:00","2022-10-01 18:00","2022-10-01 14:00","2022-10-01 18:00","연속"]
[23,"인천","시흥","신시흥S/S CB 7872","22년 시흥전력지사 362kV GIS 정밀점검 및 누기보수공사","7872 GIS 정밀점검","2022-10-04 09:00","2022-10-08 09:00","2022-10-04 09:00","2022-10-08 09:00","연속"]
[24,"인천","시흥","신시흥신안산#1 T/L","신시흥S/S 73 B/F 보호반 대체 및 #5M.Tr 보호반 대체","신시흥S/S 73 B/F 보호반 대체 및 #5M.Tr 보호반 대체","2022-10-04 09:00","2022-10-14 18:00","취소","취소","연속"]
[25,"인천","시흥","신시흥#2S/S #5 M.Tr","신시흥S/S 73 B/F 보호반 대체 및 #5M.Tr 보호반 대체","신시흥S/S 73 B/F 보호반 대체 및 #5M.Tr 보호반 대체","2022-10-04 09:00","2022-10-14 18:00","취소","취소","연속"]
[26,"인천","부평","신경서S/S #2 M.Tr","신경서S/S 4289VCB 교체관련 무부하 가압","신경서S/S 4289VCB 교체관련 무부하 가압","2022-10-06 09:00","2022-10-07 18:00","2022-10-06 09:00","2022-10-07 18:00","연속"]
[27,"인천","시흥","신시흥#1S/S #3 M.Tr","22년 시흥전력지사 362kV GIS 정밀점검 및 누기보수공사","7862DS 누기보수 관련 GIS 감압에 따른 휴전","2022-10-08 09:00","2022-10-10 18:00","2022-10-08 09:00","2022-10-10 18:00","연속"]
[28,"인천","시흥","신시흥S/S #76 BUS","22년 시흥전력지사 362kV GIS 정밀점검 및 누기보수공사","7862DS 누기보수 관련 GIS 감압에 따른 휴전","2022-10-08 09:00","2022-10-10 18:00","2022-10-08 09:00","2022-10-10 18:00","연속"]
[29,"인천","김포","신김포신파주#1 T/L","345kV 신김포-신파주#1T/L EBG 가스채취밸브 설치공사","신김포S/S, 신김포C/T EBG (1B,2B) B,C상 가스채취밸브 설치 및 스프링유닛 점검(8개소)","2022-10-11 08:00","2022-10-12 18:00","2022-10-11 08:00","2022-10-12 18:00","연속"]
[30,"인천","김포","신김포신파주#2 T/L","345kV 신김포-신파주#2T/L EBG 가스채취밸브 설치공사","신김포S/S, 신김포C/T EBG (1B,2B) B,C상 가스채취밸브 설치 및 스프링유닛 점검(7개소)","2022-10-13 08:00","2022-10-14 18:00","2022-10-13 08:00","2022-10-14 18:00","연속"]
[31,"인천","직할","신부평S/S #2 Sh.R (CB 7279)","신부평S/S #2Sh.R 조작시험","신부평S/S #2Sh.R 조작시험","2022-10-14 09:00","2022-10-14 14:00","2022-10-14 09:00","2022-10-14 14:00","연속"]
[32,"인천","직할","신부평S/S #4 Sh.R (CB 7479)","신부평S/S #4Sh.R 조작시험","신부평S/S #4Sh.R 조작시험","2022-10-14 14:00","2022-10-14 18:00","2022-10-14 14:00","2022-10-14 18:00","연속"]
[33,"인천","부평","서인천CC신부평#1 T/L","서인천S/Y 7ABAY B/F 보호반 교체","서인천S/Y 7ABAY B/F 보호반 교체","2022-10-17 09:00","2022-10-21 18:00","취소","취소","연속"]
[34,"인천","부평","서인천CC신부평#4 T/L","서인천S/Y 7ABAY B/F 보호반 교체","서인천S/Y 7ABAY B/F 보호반 교체","2022-10-17 09:00","2022-10-21 18:00","취소","취소","연속"]
[35,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥#2S/S 345kV #6 M.Tr 보호반 대체","신시흥#2S/S 345kV #6 M.Tr 보호반 대체","2022-10-17 09:00","2022-10-21 18:00","취소","취소","연속"]
[36,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥S/Y 345kV #70-#75 모선보호반 대체","영흥S/Y 345kV #70-#75 모선보호반 대체 관련 70BUS 휴전 (영흥화력 1,2호기 정지로 TIE GIS 개방중)","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[37,"인천","시흥","영흥1TP영흥2TP#2 T/L","영흥S/Y 345kV #70-#75 모선보호반 대체","영흥S/Y 345kV #70-#75 모선보호반 대체 관련 70BUS 휴전 (영흥화력 1,2호기 정지로 TIE GIS 개방중)","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[38,"인천","시흥","영흥T/P #70 BUS","영흥T/P 345kV 모선보호반 대체","영흥T/P 345kV 모선보호반 대체","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[39,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S #4M.Tr 3차측 VCB교체 관련 무부하가압","신가좌S/S #4M.Tr 3차측 VCB교체 관련 무부하가압","2022-10-20 09:00","2022-10-21 18:00","2022-10-20 09:00","2022-10-21 18:00","연속"]
[40,"인천","시흥","신시흥영흥TP#3 T/L","345kV 신시흥-영흥T/L 추락방지시설 설치공사","추락방지시설 설치(수직/수평) - 대상 : No.30~55(26기), #1,2,3,4T/L 공사 시행","2022-10-24 08:00","2022-10-29 18:00","2022-10-24 08:00","2022-10-29 18:00","연속"]
[41,"인천","부평","신인천C/C CB 7572","신인천S/Y 75BAY B/F 보호반 교체공사","신인천S/Y 75BAY B/F 보호반 교체공사","2022-10-24 09:00","2022-10-28 18:00","취소","취소","연속"]
[42,"인천","부평","신인천C/C #1,2GT 주변압기 (CB 7500, 7572)","신인천S/Y 75BAY B/F 보호반 교체공사","신인천S/Y 75BAY B/F 보호반 교체공사","2022-10-24 09:00","2022-10-28 18:00","2022-10-24 09:00","2022-10-28 18:00","연속"]
[43,"인천","시흥","신시흥#2S/S #4 M.Tr","신시흥#2S/S 345kV 76 B/F 보호반 대체","신시흥#2S/S 345kV 76 B/F 보호반 대체","2022-10-24 09:00","2022-10-28 18:00","취소","취소","연속"]
[44,"인천","시흥","서서울#2신시흥#2 T/L","신시흥#2S/S 345kV 76 B/F 보호반 대체","신시흥#2S/S 345kV 76 B/F 보호반 대체","2022-10-24 09:00","2022-10-28 18:00","취소","취소","연속"]
[45,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S #2M.Tr 3차측 VCB교체 관련 무부하가압","신가좌S/S #2M.Tr 3차측 VCB교체 관련 무부하가압","2022-10-27 09:00","2022-10-28 18:00","2022-10-27 09:00","2022-10-28 18:00","연속"]
[46,"인천","부평","신가좌신시흥#1 T/L","22~23년 가공송전 협력회사 총액공사","추락방지시설 설치공사","2022-10-31 08:00","2022-11-04 18:00","2022-10-31 08:00","2022-11-04 18:00","연속"]
[47,"인천","시흥","신시흥신광명#1 T/L","22~23년 가공송전 협력회사 총액공사","추락방지시설 설치공사","2022-10-31 08:00","2022-11-02 18:00","2022-10-31 08:00","2022-11-02 18:00","연속"]
[48,"인천","시흥","신시흥영흥TP#1 T/L","345kV 신시흥-영흥T/L 추락방지시설 설치공사","추락방지시설 설치(수직/수평) - 대상 : No.30~55(26기), #1,2,3,4T/L 공사 시행","2022-10-31 08:00","2022-11-05 18:00","취소","취소","매일"]
[49,"경기북부","고양","신덕은S/S #1 M.Tr","22년 고양전력지사 345kV 주변압기 및 OLTC 정밀점검공사","신덕은S/S #1M.Tr A,B상 본체 및 OLTC 정밀점검","2022-10-04 09:00","2022-10-14 18:00","2022-10-04 09:00","2022-10-14 18:00","연속"]
[50,"경기북부","고양","신파주S/S #2 M.Tr","22-23년 변전협력회사 총액공사","362kV GIS 보통점검(7372GIS)","2022-10-06 09:00","2022-10-06 18:00","2022-10-06 09:00","2022-10-06 18:00","연속"]
[51,"경기북부","고양","신파주S/S #3 M.Tr","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[52,"경기북부","고양","신파주양주#1 T/L","고양전력지사 관내T/L OPGW 항공장애표시구 설치공사 2차","345kV 신파주-양주#1T/L OPGW 6경간 24개 항공구 설치","2022-10-12 07:00","2022-10-14 18:00","취소","취소","연속"]
[53,"경기북부","고양","신파주양주#2 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","수평 와이어 추락방지시설 설치, 피뢰기 설치","2022-10-17 07:00","2022-10-28 18:00","취소","취소","연속"]
[54,"경기북부","고양","신김포신파주#2 T/L","고양전력지사 관내T/L OPGW 항공장애표시구 설치공사 2차","345kV 신김포-신파주#2T/L OPGW 1경간 3개 항공구 설치","2022-10-19 07:00","2022-10-20 12:00","취소","취소","연속"]
[55,"경기북부","고양","신파주S/S #1 M.Tr","22-23년 변전협력회사 총액공사","362kV GIS 보통점검(7272,7200GIS)","2022-10-04 09:00","2022-10-05 18:00","2022-10-04 09:00","2022-10-05 18:00","연속"]
[56,"경기북부","고양","신김포신파주#1 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","수평 와이어 추락방지시설 설치","2022-10-17 07:00","2022-10-18 18:00","취소","취소","연속"]
[57,"경기북부","구리","미금S/S CB 7672","2022~23 구리전력 변전협력 총액공사","미금S/S #3M.Tr 1차 7672 GIs 보통점검, 전자변교체","2022-10-27 09:00","2022-10-27 18:00","2022-10-27 09:00","2022-10-27 18:00","연속"]
[58,"경기북부","구리","미금S/S #1 BUS Sh.R (CB 7079, 7179)","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV #1,2,5 Sh.R Main 7079 GIS 보통점검 미금S/S 345kV #1Sh.R 7179 GIS 하자점검","2022-10-25 09:00","2022-10-25 18:00","2022-10-25 09:00","2022-10-25 18:00","연속"]
[59,"경기북부","구리","미금S/S #3 M.Tr","미금S/S 용량부족 차단기 대체공사(이격거리휴전)","345kV미금S/S 용량부족 차단기 대체공사 - 77Bay 기초보강작업 중 장비사용시 이격거리휴전","2022-10-01 09:00","2022-10-07 18:00","2022-10-01 09:00","2022-10-07 18:00","매일"]
[60,"경기북부","구리","신가평S/S CB 7271","2022~23 구리전력 변전협력 총액공사","신가평S/S #1M.Tr 2차 7271 GIS 보통점검","2022-10-04 09:00","2022-10-04 18:00","2022-10-04 09:00","2022-10-04 18:00","연속"]
[61,"경기북부","구리","신가평S/S CB 7200","2022~23 구리전력 변전협력 총액공사","신가평S/S #1M.Tr 2차 7200 GIS 보통점검","2022-10-06 09:00","2022-10-06 18:00","2022-10-06 09:00","2022-10-06 18:00","연속"]
[62,"경기북부","구리","신가평S/S CB 7871","2022~23 구리전력 변전협력 총액공사","신가평S/S #4M.Tr 2차 7871 GIS 보통점검공사","2022-10-12 09:00","2022-10-12 18:00","2022-10-12 09:00","2022-10-12 18:00","연속"]
[63,"경기북부","구리","신가평S/S CB 7771","2022~23 구리전력 변전협력 총액공사","신가평S/S #3M.Tr 2차 7771 GIS 보통점검","2022-10-13 09:00","2022-10-13 18:00","2022-10-13 09:00","2022-10-13 18:00","연속"]
[64,"경기북부","구리","신가평S/S CB 7772","2022~23 구리전력 변전협력 총액공사","신가평S/S 신가평-미금 #1T/L 7772 GIS 보통점검공사","2022-10-14 09:00","2022-10-14 18:00","2022-10-14 09:00","2022-10-14 18:00","연속"]
[65,"경기북부","구리","신가평S/S CB 7700","2022~23 구리전력 변전협력 총액공사","신가평S/S #3M.Tr 2차 - 신가평-미금#1T/L TIE 7700 GIS 보통점검","2022-10-18 09:00","2022-10-18 18:00","2022-10-18 09:00","2022-10-18 18:00","연속"]
[66,"경기북부","구리","신가평S/S CB 7571","2022~23 구리전력 변전협력 총액공사","신가평S/S #2M.Tr 2차 7571 GIS 보통점검","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[67,"경기북부","구리","신가평S/S CB 7472","2022~23 구리전력 변전협력 총액공사","신가평S/S 신가평-포천LNGCC#1T/L 7472 GIS 보통점검","2022-10-24 09:00","2022-10-24 18:00","2022-10-24 09:00","2022-10-24 18:00","연속"]
[68,"경기북부","구리","신포천S/S #1 M.Tr","22~23년 구리전력 변전협력 총액공사","신포천S/S 345kV #1M.Tr 주변압기 상부 안전대 걸이 설치 B상 접속개소 과열보수","2022-10-05 09:00","2022-10-05 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[69,"경기북부","구리","신포천S/S #3 M.Tr","22~23년 구리전력 변전협력 총액공사","신포천S/S 345kV #3M.Tr 주변압기 상부 안전대 걸이 설치 B상 접속개소 과열보수","2022-10-06 09:00","2022-10-06 18:00","2022-10-06 09:00","2022-10-06 18:00","연속"]
[70,"경기북부","구리","신포천S/S #4 M.Tr","22~23년 구리전력 변전협력 총액공사","신포천S/S 345kV #4M.Tr 주변압기 상부 안전대 걸이 설치","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[71,"경기북부","직할","신의정부양주#1 T/L","345kV 신의정부S/S CLR 설치공사(일반)","○ 마이크로파일 시공","2022-10-04 09:00","2022-10-05 18:00","2022-10-04 09:00","2022-10-05 18:00","연속"]
[72,"경기북부","직할","신의정부양주#2 T/L","345kV 신의정부S/S CLR 설치공사(일반)","○ 마이크로파일 시공","2022-10-06 09:00","2022-10-07 18:00","2022-10-06 09:00","2022-10-07 18:00","연속"]
[73,"경기북부","직할","양주S/S #1 M.Tr","2022-2023년 경기북부 직할 변전협력회사 총액공사","양주S/S 362kV GIS 7172 CB 조작시험","2022-10-04 09:00","2022-10-05 18:00","2022-10-04 09:00","2022-10-05 18:00","연속"]
[74,"경기북부","직할","양주S/S #3 M.Tr","22-23년 경기북부 직할 변전협력회사 총액공사","양주S/S #3MTR 보호반 대체, 정밀점검(본체:C상, OLTC:A,B,C상)","2022-10-11 09:00","2022-10-21 18:00","2022-10-11 09:00","2022-10-21 18:00","연속"]
[75,"경기북부","직할","양주중부#1 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 초기점검","2022-10-24 07:00","2022-10-24 17:00","2022-10-24 07:00","2022-10-24 17:00","연속"]
[76,"경기북부","직할","양주중부#2 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 초기점검","2022-10-25 07:00","2022-10-25 17:00","2022-10-25 07:00","2022-10-25 17:00","연속"]
[77,"경기북부","직할","양주S/S CB 7771","양주 STATCOM 건설사업","362kV GIS 플랫폼 설치","2022-10-31 09:00","2022-11-02 18:00","2022-10-31 09:00","2022-11-02 18:00","연속"]
[78,"경기","군포","서서울#2신시흥#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 17기","2022-10-19 07:00","2022-10-20 18:00","취소","취소","매일"]
[79,"경기","군포","서서울#2신시흥#1 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 17기","2022-10-17 07:00","2022-10-18 18:00","2022-10-17 07:00","2022-10-18 18:00","매일"]
[80,"경기","군포","신온양서서울#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 28기(총 73기)","2022-10-22 07:00","2022-10-23 18:00","취소","취소","매일"]
[81,"경기","군포","신온양서서울#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 28기(총 73기)","2022-10-15 07:00","2022-10-16 18:00","취소","취소","매일"]
[82,"경기","군포","서서울S/S CB 7600","서서울SS 7600 전자변교체","서서울SS 서서울-신광명#2T/L 7600전자변교체","2022-10-04 09:00","2022-10-07 18:00","2022-10-04 09:00","2022-10-07 18:00","연속"]
[83,"경기","군포","서서울S/S #1 M.Tr","서서울S/S #1 M.Tr CB 전자변 교체 및 96P,D 설치","서서울S/S #1 M.Tr CB(7300,7372) 전자변 교체 및 96P,D 설치 #1M.Tr 3차 GPT 대체","2022-10-24 09:00","2022-10-29 18:00","2022-10-24 09:00","2022-10-29 18:00","연속"]
[84,"경기","군포","서서울S/S #3 M.Tr","서서울S/S 3 M.Tr 1차 전자변 교체 및 3차 GPT 대체","서서울S/S 345kV #3 M.Tr(7672,7600) 3차 GPT 대체","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[85,"경기","군포","서서울S/S CB 7672","서서울S/S 345kV #3 M.Tr 1차 CB(7672) 전자변 교체","서서울S/S 345kV #3 M.Tr 1차 CB(7672) 전자변 교체","2022-10-17 09:00","2022-10-20 18:00","2022-10-17 09:00","2022-10-20 18:00","연속"]
[86,"경기","군포","서서울S/S #2 M.Tr","서서울S/S 2 M.Tr 1차 전자변 교체 및 3차 GPT 대체","서서울S/S 345kV #2 M.Tr(7572,7500)r 3차 GPT 대체","2022-10-14 09:00","2022-10-14 18:00","2022-10-14 09:00","2022-10-14 18:00","연속"]
[87,"경기","군포","서서울S/S CB 7572","서서울S/S 345kV #2 M.Tr 1차 CB(7572) 전자변 교체","서서울S/S 345kV #2 M.Tr 1차 CB(7572) 전자변 교체","2022-10-11 09:00","2022-10-14 18:00","2022-10-11 09:00","2022-10-14 18:00","연속"]
[88,"경기","군포","신온양서서울#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 17기(총 73기)","2022-10-29 07:00","2022-10-30 18:00","취소","취소","매일"]
[89,"경기","군포","서서울S/S #4 M.Tr","서서울S/S #4 M.Tr CB 전자변 교체 및 96P,D 설치","서서울S/S #4 M.Tr CB(7800,7872) 전자변 교체 및 96P 설치 #4M.Tr 3차 GPT 대체","2022-10-31 09:00","2022-11-05 18:00","2022-10-31 09:00","2022-11-05 18:00","연속"]
[90,"경기","동부","곤지암S/S CB 7500","345kV 곤지암S/S SK하이닉스 신규수용공사","75Bay B/F PNL 대체 7571GIS 전력케이블 접속","2022-10-17 09:00","2022-11-03 18:00","2022-10-17 09:00","2022-11-03 18:00","연속"]
[91,"경기","동부","곤지암S/S CB 7571","345kV 곤지암S/S SK하이닉스 신규수용공사","75Bay B/F PNL 대체 7571GIS 전력케이블 접속","2022-10-17 09:00","2022-11-03 15:00","2022-10-17 09:00","2022-11-03 15:00","연속"]
[92,"경기","동부","곤지암S/S #3 M.Tr","345kV 곤지암S/S SK하이닉스 신규수용공사","75Bay B/F PNL 대체","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[93,"경기","성남","신성남S/S SEC CB 75760","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2022-10-27 14:00","2022-10-27 18:00","2022-10-27 14:00","2022-10-27 18:00","연속"]
[94,"경기","성남","신성남S/S SEC CB 70710","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2022-10-27 09:00","2022-10-27 14:00","2022-10-27 09:00","2022-10-27 14:00","연속"]
[95,"경기","성남","신성남S/S STATCOM (CB 7000, 7072)","22년 성남전력지사 변전협력회사 총액공사","- 7000,7072 GIS 조작시험","2022-10-28 09:00","2022-10-28 18:00","2022-10-28 09:00","2022-10-28 18:00","연속"]
[96,"경기","성남","신수원S/S #2 M.Tr","신수원S/S 종합예방진단시스템 설치공사","신수원S/S 종합예방진단시스템 설치공사","2022-10-25 09:00","2022-10-25 18:00","2022-10-25 09:00","2022-10-25 18:00","연속"]
[97,"경기","성남","신수원S/S #4 M.Tr","신수원S/S 종합예방진단시스템 설치공사","신수원S/S 종합예방진단시스템 설치공사","2022-10-31 09:00","2022-10-31 18:00","2022-10-31 09:00","2022-10-31 18:00","연속"]
[98,"경기","성남","신수원S/S #3 M.Tr","신수원S/S 종합예방진단시스템 설치공사","신수원S/S 종합예방진단시스템 설치공사","2022-10-27 09:00","2022-10-27 18:00","2022-10-27 09:00","2022-10-27 18:00","연속"]
[99,"경기","성남","신수원S/S #1 M.Tr","신수원S/S 종합예방진단시스템 설치공사","신수원S/S 종합예방진단시스템 설치공사","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[100,"경기","성남","신안성신성남#1 T/L","345kV 신용인-동서울 등 2개T/L 지장철탑 이설공사","345kV 신용인-동서울T/L 14~16호 철탑 신설 (345kV 신안성-신성남T/L 70~73호 4회선 병가)","2022-10-02 08:00","2022-10-07 18:00","2022-10-02 08:00","2022-10-07 18:00","연속"]
[101,"경기","성남","신안성신성남#2 T/L","345kV 신용인-동서울 등 2개T/L 지장철탑 이설공사","345kV 신용인-동서울T/L 14~16호 철탑 신설 (345kV 신안성-신성남T/L 70~73호 4회선 병가)","2022-10-08 08:00","2022-10-14 18:00","2022-10-08 08:00","2022-10-14 18:00","연속"]
[102,"경기","성남","신안성S/S CB 7571","2022년 성남전력지사 변전협력회사 총액공사","- 7571 GIS 보통점검","2022-10-20 09:00","2022-10-20 14:00","2022-10-20 09:00","2022-10-20 14:00","연속"]
[103,"경기","성남","신안성S/S #5 Sh.R (CB 7779)","2022년 성남전력지사 변전협력회사 총액공사","- 7779 GIS 조작시험","2022-10-20 14:00","2022-10-20 18:00","2022-10-20 14:00","2022-10-20 18:00","연속"]
[104,"경기","성남","신용인S/S CB 7600","2022년 성남전력지사 변전협력회사 총액공사","- 7600 GIS 보통점검","2022-10-26 14:00","2022-10-26 18:00","2022-10-26 14:00","2022-10-26 18:00","연속"]
[105,"경기","성남","신용인S/S CB 7671","2022년 성남전력지사 변전협력회사 총액공사","- 7671 GIS 보통점검","2022-10-26 09:00","2022-10-26 14:00","2022-10-26 09:00","2022-10-26 14:00","연속"]
[106,"경기","성남","신용인S/S #2 M.Tr","22년 성남전력지사 M.Tr 보통점검 공사","- M.Tr 보통점검","2022-10-05 09:00","2022-10-06 18:00","2022-10-05 09:00","2022-10-06 18:00","연속"]
[107,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울T/L No.53 지장철탑 이설공사(서울세종)","서울세종 고속도로 개설관련 지장철탑 이설공사(요청자 부담 공사) - 임시선로 구성 후 본선로 구성 시행 - 1기 철거 1기 신설 - 시공업체 : 신우전설(주), 감리업체 : (주)동성기술감리단","2022-10-02 07:30","2022-10-07 18:00","2022-10-02 07:30","2022-10-07 18:00","연속"]
[108,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울T/L No.53 지장철탑 이설공사(서울세종)","서울세종 고속도로 개설관련 지장철탑 이설공사(요청자 부담 공사) - 임시선로 구성 후 본선로 구성 시행 - 1기 철거 1기 신설 - 시공업체 : 신우전설(주), 감리업체 : (주)동성기술감리단","2022-10-08 07:30","2022-10-14 18:00","2022-10-08 07:30","2022-10-14 18:00","연속"]
[109,"경기","직할","화성신평택CC#2 T/L","22-23년 군포전력 가공송전협력회사 총액공사","철탑추락방지장치 설치공사(42기)","2022-10-24 07:00","2022-10-28 18:00","2022-10-24 07:00","2022-10-28 18:00","연속"]
[110,"경기","직할","화성신평택CC#1 T/L","22-23년 군포전력 가공송전협력회사 총액공사","철탑추락방지장치 설치공사(42기)","2022-10-17 07:00","2022-10-21 18:00","2022-10-17 07:00","2022-10-21 18:00","연속"]
[111,"경기","직할","화성S/S #2 M.Tr","화성S/S 154kV 장기사용 GIS 교체공사(4차)","화성S/S 154kV 장기사용 GIS 교체공사(4차)","2022-10-31 09:00","2022-11-06 18:00","2022-10-31 09:00","2022-11-06 18:00","연속"]
[112,"경기","직할","아산화성#1 T/L","화성S/S 345kV 용량증대 GIS 교체공사","화성S/S 345kV 용량증대 GIS 교체공사","2022-10-07 09:00","2022-10-24 18:00","2022-10-18 09:00","2022-10-31 18:00","연속"]
[113,"경기","평택","고덕#2S/S #1 BUS","345kV 고덕#2S/S 건설공사","#3M.Tr 무부하가압","2022-10-17 09:00","2022-10-18 18:00","2022-10-17 09:00","2022-10-18 18:00","연속"]
[114,"경기","평택","고덕고덕2#2 T/L","345kV 고덕#2S/S 건설공사","#3M.Tr 무부하가압","2022-10-17 09:00","2022-10-18 18:00","2022-10-17 09:00","2022-10-18 18:00","연속"]
[115,"경기","평택","고덕#2S/S #2 M.Tr","345kV 고덕#2S/S 건설공사","#3M.Tr 무부하가압","2022-10-17 09:00","2022-10-18 18:00","2022-10-17 09:00","2022-10-18 18:00","연속"]
[116,"경기","평택","고덕S/S STATCOM (CB 7800, 7872)","고덕S/S 345kV STATCOM 점검공사","STATCOM 밸브, 제어기 및 관련 변전설비(M.Tr, GIS) 점검","2022-10-24 09:00","2022-11-11 18:00","2022-11-07 09:00","2022-11-25 18:00","연속"]
[117,"경기","평택","고덕S/S #3 M.Tr","22년 평택전력지사 변전협력회사 총액공사","고덕S/S #3M.Tr 3차 EGIS 하자점검","2022-10-05 10:00","2022-10-05 18:00","2022-10-05 10:00","2022-10-05 18:00","연속"]
[118,"경기","평택","서안성신진천#1 T/L","(2공구)세종-포천간 도로개설 관련 지장철탑 이설공사","2기 신설, 1기 임시","2022-10-25 07:00","2022-10-31 18:00","취소","취소","연속"]
[119,"경기","평택","서안성신진천#2 T/L","(2공구)세종-포천간 도로개설 관련 지장철탑 이설공사","2기 신설, 1기 임시","2022-10-20 07:00","2022-10-24 18:00","취소","취소","연속"]
[120,"경기","평택","서안성S/S #2 M.Tr","22년 평택전력지사 변전협력회사 총액공사","서안성S/S #2M.Tr 3차 GIS 보통점검 및 보호계전기 교체","2022-10-12 10:00","2022-10-12 18:00","2022-10-12 10:00","2022-10-12 18:00","연속"]
[121,"경기","평택","서안성S/S #1 M.Tr","22년 평택전력지사 변전협력회사 총액공사","서안성S/S #1M.Tr 3차 GIS 보통점검 및 보호계전기 교체","2022-10-11 10:00","2022-10-11 18:00","2022-10-11 10:00","2022-10-11 18:00","연속"]
[122,"경기","평택","신평택C/C CB 7A00","22년 평택전력지사 변전협력회사 총액공사","신평택C/C #2G/T 인출 PT MCCB 교체관련 7A00 GIS 휴전","2022-10-28 09:00","2022-10-28 18:00","2022-10-28 09:00","2022-10-28 18:00","연속"]
[123,"경기","평택","신평택C/C CB 7B72","22년 평택전력지사 변전협력회사 총액공사","신평택C/C #1S/T 1차 7B72 GIS 보통점검","2022-10-31 10:00","2022-10-31 18:00","2022-10-31 10:00","2022-10-31 18:00","연속"]
[124,"경기","평택","신평택C/C CB 7A72","22년 평택전력지사 변전협력회사 총액공사","신평택C/C #2G/T 1차 7A72 GIS 보통점검 및 #2G/T 인출 PT MCCB 교체","2022-10-28 09:00","2022-10-28 18:00","2022-10-28 09:00","2022-10-28 18:00","연속"]
[125,"경기","평택","신평택C/C CB 7972","22년 평택전력지사 변전협력회사 총액공사","신평택C/C #1G/T 1차 7972 GIS 보통점검","2022-10-27 10:00","2022-10-27 18:00","2022-10-27 10:00","2022-10-27 18:00","연속"]
[126,"경기","평택","평택T/P #2 CLR #7677 CB","22년 평택전력지사 변전협력회사 총액공사","신평택C/C 7677 GIS 보통점검 및 염해방지 코팅","2022-10-26 09:00","2022-10-26 18:00","취소","취소","연속"]
[127,"경기","평택","평택T/P #3 TIE Tr","평택T/P #3TIE-Tr B상 GIB 누기보수","평택T/P #3TIE-Tr B상 GIB 누기보수","2022-10-05 09:00","2022-10-07 18:00","2022-10-08 09:00","2022-10-10 18:00","연속"]
[128,"경기","평택","평택T/P #2 CLR #7577 CB","22년 평택전력지사 변전협력회사 총액공사","신평택C/C 7577 GIS 보통점검 및 염해방지 코팅","2022-10-26 09:00","2022-10-26 18:00","취소","취소","연속"]
[129,"경기","평택","평택T/P #1 CLR #7077 CB","22년 평택전력지사 변전협력회사 총액공사","신평택C/C 7077 GIS 보통점검 및 염해방지 코팅","2022-10-25 09:00","2022-10-25 18:00","취소","취소","연속"]
[130,"경기","평택","평택T/P #1 CLR #7177 CB","22년 평택전력지사 변전협력회사 총액공사","신평택C/C 7177 GIS 보통점검 및 염해방지 코팅","2022-10-25 09:00","2022-10-25 18:00","취소","취소","연속"]
[131,"강원","강릉","강릉T/P CB 7271","2022년 강릉전력지사 변전협력회사 총액공사","강릉TP 안인-강릉#2TL CB(7271) 초기점검","2022-10-13 10:00","2022-10-13 18:00","2022-10-13 10:00","2022-10-13 18:00","연속"]
[132,"강원","강릉","신양양S/S #3 M.Tr","2022년 345kV M.Tr 정밀점검","신양양S/S #3M.Tr OLTC 유면계 교체","2022-10-11 10:00","2022-10-14 18:00","2022-10-11 10:00","2022-10-14 18:00","연속"]
[133,"강원","강릉","안인개폐소S/S CB 7200","2022년 강릉전력지사 변전협력회사 총액공사","안인개폐소 안인신양양-동해안인#2 TIE CB(7200) 초기점검","2022-10-26 10:00","2022-10-26 18:00","2022-10-26 10:00","2022-10-26 18:00","연속"]
[134,"강원","강릉","안인개폐소S/S CB 7400","2022년 강릉전력지사 변전협력회사 총액공사","안인개폐소 안인-강릉#2TL TIE CB(7400) 초기점검","2022-10-11 10:00","2022-10-11 18:00","2022-10-11 10:00","2022-10-11 18:00","연속"]
[135,"강원","강릉","안인개폐소강릉TP#2 T/L","2022년 변전협력회사 총액공사","362kV GIs 초기점검 (안인개폐소 7400,7472 / 강릉화력 7271)","2022-10-11 10:00","2022-10-13 18:00","2022-10-04 10:00","2022-10-06 18:00","매일"]
[136,"강원","강릉","안인개폐소S/S CB 7472","2022년 강릉전력지사 변전협력회사 총액공사","안인개폐소 안인-강릉#2TL CB(7472) 초기점검","2022-10-12 10:00","2022-10-12 18:00","2022-10-12 10:00","2022-10-12 18:00","연속"]
[137,"강원","강릉","안인개폐소S/S CB 7100","2022년 강릉전력지사 변전협력회사 총액공사","안인개폐소 안인양양PP-동해안인 TIE CB(7100) 초기점검","2022-10-18 10:00","2022-10-18 18:00","2022-10-18 10:00","2022-10-18 18:00","연속"]
[138,"강원","강릉","안인개폐소S/S CB 7172","2022년 강릉전력지사 변전협력회사 총액공사","안인개폐소동해-안인#1TL TIE CB(7172) 초기점검","2022-10-20 10:00","2022-10-20 18:00","2022-10-20 10:00","2022-10-20 18:00","연속"]
[139,"강원","강릉","안인개폐소S/S CB 7272","2022년 강릉전력지사 변전협력회사 총액공사","안인개폐소동해-안인#2TL CB(7272) 초기점검","2022-10-25 10:00","2022-10-25 18:00","2022-10-25 10:00","2022-10-25 18:00","연속"]
[140,"강원","강릉","양양P/P CB 7371","2022년 강릉전력지사 변전협력회사 총액공사","양양양수S/Y 안인양양PPT/L CB(7371) 초기점검","2022-10-19 10:00","2022-10-19 18:00","2022-10-19 10:00","2022-10-19 18:00","연속"]
[141,"강원","강릉","안인개폐소양양PP T/L","2022년 변전협력회사 총액공사","양양양수 피뢰기 대체 안인개폐소 362kV GIS 초기점검 (7100) 양양양수 장기미동작 차단기 조작시험 (7371)","2022-10-18 10:00","2022-10-20 18:00","2022-10-18 10:00","2022-10-20 18:00","연속"]
[142,"강원","강릉","신양양양양PP T/L","2022년 변전협력회사 총액공사","양양양수 피뢰기, CVT 대체 양양PP(7171) 조작시험 신양양 362kV GIS(7171) LA 보통점검","2022-10-04 10:00","2022-10-06 18:00","취소","취소","연속"]
[143,"강원","동해","동해안인개폐소#1 T/L","345kV 동해-안인개폐소등 5개T/L 철탑추락방지장치 설치공사","철탑추락방지장치(수평) 설치(No.196~No.258) 64기","2022-10-17 08:00","2022-10-24 18:00","2022-10-17 08:00","2022-10-24 18:00","매일"]
[144,"강원","동해","동해안인개폐소#2 T/L","345kV 동해-안인개폐소등 5개T/L 철탑추락방지장치 설치공사","철탑추락방지장치(수평) 설치(No.196~No.258) 64기","2022-10-25 08:00","2022-11-01 18:00","2022-10-25 08:00","2022-11-01 18:00","매일"]
[145,"강원","태백","신태백S/S 가덕산풍력T/L (CB 7772)","22-23년 태백전력지사 변전협력회사 총액공사","345kV 77Bay B/F PNL 교체","2022-10-24 10:00","2022-10-27 18:00","2022-10-24 10:00","2022-10-27 18:00","연속"]
[146,"충북","직할","신진천S/S #2 M.Tr","345kV 신진천S/S 종합예방진단시스템 구축공사","○ 신진천S/S 종합예방진단시스템 구축 ○ 계획정비파트 병행작업 - #2M.Tr 주변압기 보통점검 - #2M.Tr 2차 GIS 보통점검 - #2M.Tr 1차 CVT 초기점검 - #2M.Tr 3차 PT 하자점검 - #2M.Tr 3차 LA 초기점검","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[147,"충북","직할","신진천S/S #3 M.Tr","345kV 신진천S/S 종합예방진단시스템 구축공사","○ 신진천S/S 종합예방진단시스템 구축 ○ 계획정비파트 병행작업 - #3M.Tr 1차 GIS 보통점검 - #3M.Tr 1차 TIE GIS 보통점검 - #3M.Tr 1,2,3차 LA 대체 - #3M.Tr 3차 PT 하자점검","2022-10-24 09:00","2022-10-28 18:00","2022-10-24 09:00","2022-10-28 18:00","연속"]
[148,"충북","직할","신진천S/S #5 M.Tr","345kV 신진천S/S 종합예방진단시스템 구축공사","○ 신진천S/S 종합예방진단시스템 구축 ○ 계획정비파트 병행작업 - #5M.Tr 주변압기 보통점검 - #5M.Tr 1차 GIS 보통점검 - #5M.Tr 2차 GIS 정밀점검 - #5M.Tr 1,2,3차 LA 초기점검 - #5M.Tr 1차 CVT 초기점검","2022-10-31 09:00","2022-11-04 18:00","2022-10-31 09:00","2022-11-04 18:00","연속"]
[149,"충북","직할","신진천S/S #4 M.Tr","345kV 신진천S/S 종합예방진단시스템 구축공사","○ 신진천S/S 종합예방진단시스템 구축 ○ 계획정비파트 병행작업 - #4M.Tr 1차 GIS 보통점검 - #4M.Tr 1차 CVT 초기점검 - #4M.Tr 3차 PT 초기점검 - #4M.Tr 3차 LA 초기점검","2022-10-11 09:00","2022-10-14 18:00","2022-10-11 09:00","2022-10-14 18:00","연속"]
[150,"충북","직할","신진천S/S #1 M.Tr","345kV 신진천S/S 종합예방진단시스템 구축공사","○ 신진천S/S 종합예방진단시스템 구축 ○ 계획정비파트 병행 작업 - #1M.Tr 2차 GIS 보통점검 - #1M.Tr 1차 CVT 초기점검 - #1M.Tr 3차 LA 초기점검","2022-10-04 09:00","2022-10-07 18:00","2022-10-04 09:00","2022-10-07 18:00","연속"]
[151,"충북","청주","신중부남청주#1 T/L","345kV 신청주분기T/L 건설공사","345kV 신청주분기T/L 임시선로 건설 1. 임시선로 구간 : (기설)345kV 신중부-남청주T/L No.37 ~ 가)No.38-1 ~ 가)No.40-1 ~ No.41 2. 선로길이 : 2C-1.21km 3. 지 지 물 : 2기(가철탑)","2022-10-12 07:00","2022-10-19 18:00","2022-10-12 07:00","2022-10-19 18:00","연속"]
[152,"충북","청주","신중부남청주#2 T/L","345kV 신청주분기T/L 건설공사","345kV 신청주분기T/L 임시선로 건설 1. 임시선로 구간 : (기설)345kV 신중부-남청주T/L No.37 ~ 가)No.38-1 ~ 가)No.40-1 ~ No.41 2. 선로길이 : 2C-1.21km 3. 지 지 물 : 2기(가철탑)","2022-10-04 07:00","2022-10-11 18:00","2022-10-04 07:00","2022-10-11 18:00","연속"]
[153,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사","#65-66 BUS SEC GIS 대체시 안전이격거리확보","2022-10-22 09:00","2022-10-22 14:00","취소","취소","연속"]
[154,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사","#60-61 BUS SEC GIS 대체시 안전이격거리확보","2022-10-29 09:00","2022-10-30 14:00","취소","취소","연속"]
[155,"충북","청주","세종남청주#1 T/L","남청주S/S 345kV 장기사용 GIS 교체공사","송전선로 인출 변경","2022-10-31 09:00","2022-11-04 18:00","2022-11-01 09:00","2022-11-05 18:00","연속"]
[156,"충북","청주","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L No.184~196 안전이격 확보공사","1. 구간 : 345kV 신옥천~신남원T/L No.184~196 2. 공사개요 - 지지물 4기교체(산형강 3기, 관형주1기) - 전선교체 : 3,166C-km(No.184~186, 190~196) - 전선이동(재사용) : 1,821C-km(No.186~190) - OPGW 교체 : 5.2km (No.184~196)","2022-10-18 08:00","2022-10-27 18:00","취소","취소","연속"]
[157,"충북","청주","신옥천신남원#2 T/L","345kV 신옥천-신남원T/L No.184~196 안전이격 확보공사","1. 구간 : 345kV 신옥천~신남원T/L No.184~196 2. 공사개요 - 지지물 4기교체(산형강 3기, 관형주1기) - 전선교체 : 3,166C-km(No.184~186, 190~196) - 전선이동(재사용) : 1,821C-km(No.186~190) - OPGW 교체 : 5.2km (No.184~196)","2022-10-08 09:00","2022-10-17 18:00","2022-10-08 09:00","2022-10-17 18:00","연속"]
[158,"충북","청주","신옥천신남원#1 T/L","345kV 신옥천-신남원T/L No.184~196 안전이격 확보공사","1. 구간 : 345kV 신옥천~신남원T/L No.184~196 2. 공사개요 - 지지물 4기교체(산형강 3기, 관형주1기) - 전선교체 : 3,166C-km(No.184~186, 190~196) - 전선이동(재사용) : 1,821C-km(No.186~190) - OPGW 교체 : 5.2km (No.184~196)","2022-10-01 08:00","2022-10-07 18:00","2022-10-01 08:00","2022-10-07 18:00","연속"]
[159,"충북","충주","신제천S/S SVC (CB 7271, 7200)","2022년 신제천S/S SVC 제어동 하반기 소방점검","2022년 신제천S/S SVC 제어동 하반기 소방점검","2022-10-13 09:00","2022-10-13 17:00","2022-10-13 09:00","2022-10-13 17:00","연속"]
[160,"충북","충주","신충주S/S STATCOM (7071, 7000)","2022년 신충주S/S STATCOM 제어동 하반기 소방점검","2022년 신충주S/S STATCOM 제어동 하반기 소방점검","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[161,"충북","충주","남청주S/S #1 M.Tr","남청주S/S 345kV 장기사용 GIS 교체공사","#65-66 BUS SEC GIS 대체시 안전이격거리확보","2022-10-15 09:00","2022-10-16 18:00","취소","취소","연속"]
[162,"충북","충주","남청주S/S CB 7600","남청주S/S 345kV 장기사용 GIS 교체공사","#65-66 BUS SEC GIS 대체시 안전이격거리확보","2022-10-20 09:00","2022-11-06 18:00","취소","취소","연속"]
[163,"충북","충주","남청주S/S #3 M.Tr","남청주S/S 345kV 장기사용 GIS 교체공사","76 BAY 2CB 철거 3CB 설치","2022-10-22 14:00","2022-10-23 18:00","취소","취소","연속"]
[164,"대전세종충남","대전","신계룡S/S #2 M.Tr","신계룡S/S #2M.Tr 정밀점검공사","신계룡S/S #2M.Tr 정밀점검공사","2022-10-17 09:00","2022-11-04 18:00","2022-10-17 09:00","2022-11-04 18:00","연속"]
[165,"대전세종충남","서산","당진T/P CB 7171","22년도 차단기 조작시험","22년도 차단기 조작시험","2022-10-24 13:00","2022-10-24 18:00","2022-10-24 13:00","2022-10-24 18:00","연속"]
[166,"대전세종충남","서산","당진T/P CB 7272","22년 서산P/O 변전협력회사 총액공사","당진화력S/S 345kV 7272 CB 전자변 교체","2022-10-05 09:00","2022-10-05 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[167,"대전세종충남","서산","당진T/P CB 7200","22년 서산P/O 변전협력회사 총액공사","당진화력S/S 345kV 7200 CB 전자변 교체","2022-10-04 09:00","2022-10-04 18:00","2022-10-04 09:00","2022-10-04 18:00","연속"]
[168,"대전세종충남","서산","북당진S/S CB 7572","22년 서산P/O 변전협력회사 총액공사","북당진S/S 345kV 7572 CB 보통점검","2022-10-05 09:00","2022-10-05 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[169,"대전세종충남","서산","태안T/P CB 7472","22년 서산P/O 변전협력회사 총액공사","(오버홀 병행) 태안화력S/Y 345kV 7472 CB 보통점검","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[170,"대전세종충남","서산","태안T/P CB 7400","22년 서산P/O 변전협력회사 총액공사","(오버홀 병행) 태안화력S/Y 345kV 7400 CB 보통점검","2022-10-19 09:00","2022-10-19 18:00","2022-10-19 09:00","2022-10-19 18:00","연속"]
[171,"대전세종충남","천안","신서산아산#2 T/L"," 345kV 아산S/S 취약설비 보강 및 배전반 정비공사","- 모자익배전반 철거 * 1식 - 집중감시제어반+디지탈축소형모자익배전반 설치 *1식 ","2022-10-17 09:00","2022-11-04 18:00","취소","취소","연속"]
[172,"대전세종충남","천안","아산S/S #1 M.Tr"," 345kV 아산S/S 취약설비 보강 및 배전반 정비공사","- 모자익배전반 철거 * 1식 - 집중감시제어반+디지탈축소형모자익배전반 설치 *1식 ","2022-10-17 09:00","2022-11-04 18:00","취소","취소","연속"]
[173,"대전세종충남","천안","신온양S/S CB 7571","22년 천안 관내 170kV GIS 정밀점검공사","- 신온양s/s 7571 차단기 보통점검","2022-10-28 09:00","2022-10-28 18:00","2022-10-28 09:00","2022-10-28 18:00","연속"]
[174,"대전세종충남","천안","신온양S/S #2 M.Tr","신온양S/S 345kV #2 M.Tr 1,2차 부싱절연유 채유","신온양S/S 345kV #2 M.Tr 1,2차 부싱절연유 채유","2022-10-06 09:00","2022-10-06 18:00","2022-10-06 09:00","2022-10-06 18:00","연속"]
[175,"대전세종충남","천안","신탕정S/S #1 M.Tr","신탕정S/S 345kV #1 M.Tr 배기팬 불량관련 보수작업","신탕정S/S 345kV #1 M.Tr 배기팬 불량관련 보수작업","2022-10-14 09:00","2022-10-14 18:00","2022-10-14 09:00","2022-10-14 18:00","연속"]
[176,"대전세종충남","천안","청양신탕정#2 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","345kV 청양-신온양T/L No.57~150 추락방지시설(수평) 설치","2022-10-10 08:00","2022-10-19 18:00","취소","취소","매일"]
[177,"대전세종충남","천안","신탕정S/S #4 M.Tr","신탕정S/S 345kV #4 M.Tr 하자 보수작업","신탕정S/S 345kV #4 M.Tr 하자 보수작업","2022-10-24 09:00","2022-10-28 18:00","취소","취소","연속"]
[178,"대전세종충남","천안","아산S/S CB 7872","아산S/S 345kV #4 M.Tr 7872, 7800CB 개폐타임 측정","아산S/S 345kV #4 M.Tr 7872, 7800CB 개폐타임 측정","2022-10-27 09:00","2022-10-27 14:00","2022-10-27 09:00","2022-10-27 14:00","연속"]
[179,"대전세종충남","천안","아산S/S CB 7800","아산S/S 345kV #4 M.Tr 7872, 7800CB 개폐타임 측정","아산S/S 345kV #4 M.Tr 7872, 7800CB 개폐타임 측정","2022-10-27 14:00","2022-10-27 18:00","2022-10-27 14:00","2022-10-27 18:00","연속"]
[180,"대전세종충남","천안","아산S/S #3 M.Tr","아산S/S 345kV #3 M.Tr 보통점검","아산S/S 345kV #3 M.Tr 보통점검","2022-10-31 09:00","2022-11-01 18:00","취소","취소","연속"]
[181,"대전세종충남","청양","보령T/P CB 7600","보령T/P 362kV GIS 보통점검","보령T/P 362kV GIS 보통점검","2022-10-06 09:00","2022-10-06 18:00","2022-10-06 09:00","2022-10-06 18:00","연속"]
[182,"대전세종충남","청양","보령T/P CB 7672","보령T/P 362kV GIS 보통점검","보령T/P 362kV GIS 보통점검","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[183,"대전세종충남","청양","청양보령TP#2 T/L","345kV 청양-보령화력#2T/L 관련기기 점검","345kV 청양-보령화력#2T/L 관련기기 점검 - 7672CB 조작시험 - CVT 대체","2022-10-12 09:00","2022-10-12 18:00","2022-10-12 09:00","2022-10-12 18:00","연속"]
[184,"대전세종충남","청양","청양신탕정#1 T/L","(9월 취소시)청양S/S 73Bay B/F 및 T/L PNL 교체공사","청양S/S 73Bay B/F PNL 및 송전선로 보호반 교체공사","2022-10-24 09:00","2022-11-04 18:00","취소","취소","연속"]
[185,"대전세종충남","청양","청양군산#2 T/L","(9월 취소시)청양S/S 73Bay B/F PNL 교체공사","청양S/S 73Bay B/F PNL 교체공사","2022-10-24 09:00","2022-11-04 18:00","취소","취소","연속"]
[186,"전북","김제","군산신김제#1 T/L","345kV 신김제-한빛T/L 추락방지시설 설치공사","○ 수직 및 수평#2T/L 추락방지시설 설치 : No.213~216(4기, 병가구간)","2022-10-17 07:30","2022-10-17 18:00","2022-10-17 07:30","2022-10-17 18:00","연속"]
[187,"전북","직할","신남원의령#1 T/L","신남원S/S 345kV #73Bay 차단실패보호반 대체공사","○ 휴전개소 : 7371, 7300 ○ 공 사 명 : 신남원S/S 345kV #73Bay 차단실패보호반 대체공사","2022-10-24 09:00","2022-10-28 18:00","2022-10-25 09:00","2022-10-29 18:00","연속"]
[188,"전북","직할","신남원의령#2 T/L","전북직할 신남원S/S 362kV GIS 정밀점검","전북직할 신남원S/S 362kV GIS 정밀점검 - 대상 : 7471 CB - 일정 : 10/31(월) 08:00 ~ 11/04 18:00 5일간","2022-10-31 08:00","2022-11-04 18:00","2022-10-31 08:00","2022-11-04 18:00","연속"]
[189,"광주전남","목포","한빛#3N/P CB 7B00","한빛#3S/Y 7B00 차단기 점검","한빛#3S/Y 7B00 차단기, 유압시스템 점검","2022-10-03 09:00","2022-10-03 18:00","2022-10-03 09:00","2022-10-03 18:00","연속"]
[190,"광주전남","광주","신광주한빛NP#2 T/L","2022년 광주전력 철탑추락방지장치 설치공사","345kV 신광주-한빛T/L 철탑추락방지장치 설치공사","2022-10-04 07:30","2022-10-20 18:00","2022-10-04 07:30","2022-10-20 18:00","연속"]
[191,"광주전남","순천","신강진광양#1 T/L","2022년 가공송전 순시점검 위탁공사","광양-하동TP #2T/L 73호 과열개소 정비 관련 4회선 구간 안전이격거리 확보","2022-10-04 09:00","2022-10-04 18:00","2022-10-04 09:00","2022-10-04 18:00","연속"]
[192,"광주전남","순천","광양하동TP#2 T/L","2022년 가공송전 순시점검 위탁공사","광양-하동TP #2T/L 73호 과열개소 정비","2022-10-04 09:00","2022-10-04 18:00","2022-10-04 09:00","2022-10-04 18:00","연속"]
[193,"광주전남","순천","여수T/P #1 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 345Kv #1M.Tr 보통점검(OFU), 3차 GPT 하자점검, 1, 2차 LA 대체 및 부싱절연유 채유","2022-10-04 09:00","2022-10-07 18:00","취소","취소","연속"]
[194,"광주전남","광주","신화순신강진#1 T/L","22년 광주전력 변전협력회사 총액공사","신화순-신강진#1T/L PNL 교체","2022-10-12 09:00","2022-10-21 18:00","2022-10-12 09:00","2022-10-21 18:00","연속"]
[195,"광주전남","순천","여수T/P #3 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 여수화력S/Y #3M.Tr, 2차 GIS 보통점검 및 1차 CB 타임측정, 7300 CB 타임측정","2022-10-12 09:00","2022-10-14 18:00","취소","취소","연속"]
[196,"광주전남","순천","여수T/P #4 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","#4M.Tr, 1차 GIS, 2차 GIS, 7400 GIS, 1차 LA, 2차 LA 7400 GIS CB 초기점검","2022-10-17 09:00","2022-10-20 18:00","2022-10-17 09:00","2022-10-20 18:00","연속"]
[197,"광주전남","순천","여수T/P CB 7100","362 GIS 정밀점검","GIS 정밀점검(CB)","2022-10-17 10:00","2022-10-19 14:00","취소","취소","연속"]
[198,"광주전남","순천","여수T/P CB 7172","362 GIS 정밀점검","GIS 정밀점검(CB)","2022-10-19 14:00","2022-10-21 18:00","2022-10-19 14:00","2022-10-21 18:00","연속"]
[199,"광주전남","순천","광양광양CC#1 T/L","345kV 광양-광양C/C T/L 불량애자 교체공사","41~광양CC(16기) 불량애자 교체 및 증결","2022-10-20 07:00","2022-10-28 18:00","2022-10-20 07:00","2022-10-28 18:00","연속"]
[200,"광주전남","광주","신광주한빛NP#1 T/L","2022년 광주전력 철탑추락방지장치 설치공사","345kV 신광주-한빛T/L 추락방지장치 설치공사","2022-10-21 07:30","2022-10-31 18:00","2022-10-21 07:30","2022-10-31 18:00","연속"]
[201,"광주전남","순천","광양C/C CB 7471","22-23년 순천전력지사 변전협력회사 총액공사","광양CC-여수TP #1T/L GIS 초기점검(7471)","2022-10-21 09:00","2022-10-21 18:00","2022-10-21 09:00","2022-10-21 18:00","연속"]
[202,"광주전남","광주","신화순S/S #1 M.Tr","22~23 광주전력 변전협력회사 총액공사","신화순S/S #1M.Tr 2차 GIS 유압유 교체 -비상시 즉시가압 불가-","2022-10-24 09:00","2022-10-24 18:00","2022-10-24 09:00","2022-10-24 18:00","연속"]
[203,"광주전남","목포","한빛2NP한빛3NP#3 T/L","2022년도 목포전력지사 변전협력회사 총액공사","초고압 애자절연 코팅제 시공,LA보통점검","2022-10-24 09:00","2022-10-28 18:00","2022-10-24 09:00","2022-10-28 18:00","연속"]
[204,"광주전남","순천","광양C/C CB 7472","22-23년 순천전력지사 변전협력회사 총액공사","광양CC-여수TP #2T/L GIS 초기점검(7472)","2022-10-24 09:00","2022-10-24 18:00","2022-10-24 09:00","2022-10-24 18:00","연속"]
[205,"광주전남","순천","광양C/C CB 7400","22-23년 순천전력지사 변전협력회사 총액공사","광양CC-여수TP #1T/L - 광양CC-여수TP #2T/L TIE GIS 초기점검(7400)","2022-10-25 09:00","2022-10-25 18:00","2022-10-25 09:00","2022-10-25 18:00","연속"]
[206,"광주전남","순천","여수T/P #2 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 수치 측정","2022-10-25 10:00","2022-10-25 15:00","2022-10-25 10:00","2022-10-25 15:00","연속"]
[207,"광주전남","강진","신화순신강진#2 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","신화순-신강진#2T/L 송전선로 보호반 대체 신화순-신강진#2T/L GIS 및 신화순-신강진#2T/L TIE GIS 하자","2022-10-26 09:00","2022-11-04 18:00","2022-10-26 09:00","2022-11-04 18:00","연속"]
[208,"광주전남","순천","여수T/P CB 7471","22-23년 순천전력지사 변전협력회사 총액공사","광양-여수TP T/L GIS 초기점검(7471)","2022-10-26 09:00","2022-10-26 18:00","2022-10-17 09:00","2022-10-20 18:00","연속"]
[209,"광주전남","순천","여수T/P CB 7371","22-23년 순천전력지사 변전협력회사 총액공사","율촌CC-여수TP T/L GIS 초기점검(7371)","2022-10-27 09:00","2022-10-27 18:00","2022-10-27 09:00","2022-10-27 18:00","연속"]
[210,"광주전남","순천","여수T/P SEC CB 70710","22-23년 순천전력지사 변전협력회사 총액공사","#70-71BUS SEC GIS 초기점검","2022-10-28 09:00","2022-10-28 18:00","2022-10-28 09:00","2022-10-28 18:00","연속"]
[211,"광주전남","순천","광양광양CC#2 T/L","345kV 광양-광양C/C T/L 불량애자 교체공사","41~광양CC(16기) 불량애자 교체 및 증결","2022-10-31 07:00","2022-11-08 18:00","2022-10-31 07:00","2022-11-08 18:00","연속"]
[212,"광주전남","순천","여수T/P SEC CB 75760","22-23년 순천전력지사 변전협력회사 총액공사","#75-76BUS SEC GIS 초기점검","2022-10-31 09:00","2022-10-31 18:00","2022-10-31 09:00","2022-10-31 18:00","연속"]
[213,"대구","경산","신경산S/S CB 7000","22~23년 경산PO 변전협력회사 총액공사","- 노후 보조계전기 교체","2022-10-04 09:30","2022-10-06 18:00","2022-10-04 09:30","2022-10-06 18:00","연속"]
[214,"대구","달성","고령의령#1 T/L","고령S/S 고령-의령#1T/L GIS, PT, LA 보통점검","고령S/S 고령-의령#1T/L GIS, PT, LA 보통점검","2022-10-19 09:00","2022-10-20 18:00","취소","취소","연속"]
[215,"대구","달성","서대구고령#1 T/L","345kV 서대구-고령T/L OPGW 광코어 용량 증설공사","서대구-고령T/L OPGW 광케이블 용량(24→48C) 증설 - 345kV 서대구-고령T/L 고령~서대구S/S(No.1~100) - 서대구-고령T/L 철탑 103기 금구류 교체 및 항공장애표시구 74대 교체 - 비금속광케이블 포설(서대구, 고령S/S) 및 성단 72코어, 랙 시설 등 부대공사","2022-10-19 09:00","2022-11-05 18:00","2022-10-19 09:00","2022-11-05 18:00","연속"]
[216,"대구","달성","고령의령#2 T/L","345kV 서대구-고령T/L OPGW 광코어 용량 증설공사","서대구-고령T/L 광케이블 OPGW 용량(24→48C) 증설 - 345kV 서대구-고령T/L 고령~서대구S/S(No.1~100) - 서대구-고령T/L 철탑 103기 금구류 교체 및 항공장애표시구 74대 교체 - 비금속광케이블 포설(서대구, 고령S/S) 및 성단 72코어, 랙 시설 등 부대공사 ※ 서대구-고령T/L No.1~5호 병가T/L로 고령-의령","2022-10-25 09:00","2022-10-26 18:00","2022-10-25 09:00","2022-10-26 18:00","연속"]
[217,"대구","달성","북경남고령#2 T/L","345kV 서대구-고령T/L OPGW 광코어 용량 증설공사","서대구-고령T/L 광케이블 OPGW 용량(24→48C) 증설 - 345kV 서대구-고령T/L 고령~서대구S/S(No.1~100) - 서대구-고령T/L 철탑 103기 금구류 교체 및 항공장애표시구 74대 교체 - 비금속광케이블 포설(서대구, 고령S/S) 및 성단 72코어, 랙 시설 등 부대공사 ※ OPGW 증설공사 시 구내 작업 안전확보(서대구-고령#","2022-10-25 09:00","2022-10-26 18:00","2022-10-25 09:00","2022-10-26 18:00","연속"]
[218,"대구","달성","북경남대구#2 T/L","345kV 북경남-대구T/L 안전이격거리 확보공사","345kV 북경남-대구T/L 안전이격거리 확보공사 전선교체","2022-10-05 07:00","2022-10-11 18:00","2022-10-05 07:00","2022-10-11 18:00","연속"]
[219,"대구","달성","대구S/S #3 M.Tr","#73B/F PNL 대체","#73B/F PNL 대체","2022-10-05 09:00","2022-10-11 18:00","2022-10-05 09:00","2022-10-11 18:00","연속"]
[220,"대구","달성","신경산대구#1 T/L","#71Bay B/F PNL 대체 및 결상회로 보완","#71Bay B/F PNL 대체 및 결상회로 보완","2022-10-13 09:00","2022-10-18 18:00","2022-10-13 09:00","2022-10-18 18:00","연속"]
[221,"대구","달성","대구S/S #1 M.Tr","#71Bay B/F PNL 대체 및 결상회로 보완","#71Bay B/F PNL 대체 및 결상회로 보완","2022-10-13 09:00","2022-10-18 18:00","2022-10-13 09:00","2022-10-18 18:00","연속"]
[222,"대구","달성","신경산대구#2 T/L","#72Bay B/F PNL 대체 및 결상회로 보완","#72Bay B/F PNL 대체 및 결상회로 보완","2022-10-31 09:00","2022-11-04 18:00","2022-10-31 09:00","2022-11-04 18:00","연속"]
[223,"대구","달성","대구S/S #2 M.Tr","#72Bay B/F PNL 대체 및 결상회로 보완","#72Bay B/F PNL 대체 및 결상회로 보완","2022-10-31 09:00","2022-11-04 18:00","2022-10-31 09:00","2022-11-04 18:00","연속"]
[224,"대구","칠곡","서대구S/S CB 7200","서대구S/S 345kV GCB 전자변 교체공사","서대구S/S 345kV GCB 전자변 교체공사","2022-10-12 14:00","2022-10-12 18:00","2022-10-12 14:00","2022-10-12 18:00","연속"]
[225,"대구","칠곡","서대구S/S CB 7872","서대구S/S 345kV GCB 전자변 교체공사","서대구S/S 345kV GCB 전자변 교체공사","2022-10-17 09:30","2022-10-17 18:00","2022-10-17 09:30","2022-10-17 18:00","연속"]
[226,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S #1M.Tr 2차, 성주#2T/L 부하전환(철구 → GIS)","2022-10-20 08:30","2022-10-25 18:00","2022-10-20 08:30","2022-10-25 18:00","연속"]
[227,"대구","칠곡","서대구S/S CB 7271","서대구S/S 345kV GCB 전자변 교체공사","서대구S/S 345kV GCB 전자변 교체공사","2022-10-12 09:30","2022-10-12 14:00","2022-10-12 09:30","2022-10-12 14:00","연속"]
[228,"대구","칠곡","서대구S/S CB 7472","서대구S/S 345kV GCB 전자변 교체공사","서대구S/S 345kV GCB 전자변 교체공사","2022-10-11 09:30","2022-10-11 14:00","2022-10-11 09:30","2022-10-11 14:00","연속"]
[229,"대구","칠곡","서대구S/S CB 7471","서대구S/S 345kV GCB 전자변 교체공사","서대구S/S 345kV GCB 전자변 교체공사","2022-10-06 09:30","2022-10-06 18:00","2022-10-06 09:30","2022-10-06 18:00","연속"]
[230,"대구","칠곡","서대구S/S CB 7400","서대구S/S 345kV GCB 전자변 교체공사","서대구S/S 345kV GCB 전자변 교체공사","2022-10-07 09:30","2022-10-07 18:00","2022-10-07 09:30","2022-10-07 18:00","연속"]
[231,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","345kV #2M.Tr 2차측 부하전환(철구 → GIS)","2022-10-11 08:30","2022-10-14 18:00","2022-10-11 08:30","2022-10-14 18:00","연속"]
[232,"대구","칠곡","서대구S/S CB 7800","서대구S/S 345kV GCB 전자변 교체공사","서대구S/S 345kV GCB 전자변 교체공사","2022-10-11 14:00","2022-10-11 18:00","2022-10-11 14:00","2022-10-11 18:00","연속"]
[233,"대구","포항","신영일S/S #4 M.Tr","신영일S/S #4M.Tr 1,2,3차 차단기점검 및 불량보수","신영일S/S #4M.Tr 1,2,3차 차단기점검 및 불량보수","2022-10-19 09:00","2022-10-20 18:00","2022-10-19 09:00","2022-10-20 18:00","연속"]
[234,"대구","포항","신영일S/S #3 M.Tr","신영일S/S #3M.Tr 1,2,3차 차단기점검 및 불량보수","신영일S/S #3M.Tr 1,2,3차 차단기점검 및 불량보수","2022-10-17 09:00","2022-10-18 18:00","2022-10-17 09:00","2022-10-18 18:00","연속"]
[235,"대구","포항","신포항신영일 T/L","신영일S/S 신포항-신영일T/L PT,LA 대체작업","신영일S/S 신포항-신영일T/L PT,LA 대체작업","2022-10-13 09:00","2022-10-14 18:00","2022-10-13 09:00","2022-10-14 18:00","연속"]
[236,"대구","포항","신영일안동CC T/L","신영일S/S 신영일-안동CC T/L PT,LA 대체작업","신영일S/S 신영일-안동CC T/L PT,LA 대체작업","2022-10-11 09:00","2022-10-12 18:00","취소","취소","연속"]
[237,"대구","포항","선산신포항 T/L","2022~23년도 대구직할 가공송전 협력회사 총액공사","345kV신포항-북대구T/L No.49~148 추락방지장치 설치","2022-10-06 07:30","2022-10-14 18:00","2022-10-06 07:30","2022-10-14 18:00","연속"]
[238,"대구","포항","월성N/P SEC CB 75760","월성S/Y 75-76 SEC GIS 조작시험","월성S/Y 75-76 SEC GIS 조작시험","2022-10-06 14:00","2022-10-06 18:00","2022-10-06 14:00","2022-10-06 18:00","연속"]
[239,"대구","포항","월성N/P SEC CB 70710","월성S/Y 70-71 SEC GIS 조작시험","월성S/Y 70-71 SEC GIS 조작시험","2022-10-06 09:00","2022-10-06 14:00","2022-10-06 09:00","2022-10-06 14:00","연속"]
[240,"경북","영주","신영주S/S #2 TCSC CB","신영주S/S 345kV TCSC 점검공사","- 신영주S/S 345kV #2TCSC 점검공사","2022-09-30 09:00","2022-10-02 18:00","2022-09-30 09:00","2022-10-02 18:00","연속"]
[241,"경북","영주","신영주S/S #3 M.Tr","22-23년 영주전력지사 변전협력회사 총액공사","- 부싱절연유 채유","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[242,"경북","구미","서대구선산#1 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-10-11 08:30","2022-10-12 18:00","2022-10-11 08:30","2022-10-12 18:00","연속"]
[243,"경북","구미","선산S/S #1 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-10-11 08:30","2022-10-12 18:00","2022-10-11 08:30","2022-10-12 18:00","연속"]
[244,"경북","영주","신영주S/S #1 M.Tr","22-23년 영주전력지사 변전협력회사 총액공사","- 1,2차 CB 보통/초기점검 - 주변압기 보통점검 - 3차 LA 대체 - 부싱절연유 채유","2022-10-12 09:00","2022-10-14 18:00","2022-10-12 09:00","2022-10-14 18:00","연속"]
[245,"경북","구미","선산S/S #3 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-10-13 08:30","2022-10-14 18:00","2022-10-13 08:30","2022-10-14 18:00","연속"]
[246,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-10-13 08:30","2022-10-14 18:00","2022-10-13 08:30","2022-10-14 18:00","연속"]
[247,"경북","영주","신영주S/S 예비 M.TR CB","22-23년 영주전력지사 변전협력회사 총액공사","- 부싱절연유 채유","2022-10-13 09:00","2022-10-13 18:00","취소","취소","연속"]
[248,"경북","구미","선산S/S #2 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-10-15 08:30","2022-10-16 18:00","2022-10-15 08:30","2022-10-16 18:00","연속"]
[249,"경북","구미","서대구선산#2 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초설치관련 안전이격 확보","2022-10-15 08:30","2022-10-16 18:00","2022-10-15 08:30","2022-10-16 18:00","연속"]
[250,"경북","직할","신포항청송PP T/L","22~23년 경북본부 직할 변전협력회사 총액공사","7271,7200 보통점검, CVT 교체","2022-10-17 09:00","2022-10-18 18:00","취소","취소","매일"]
[251,"경북","직할","신영주청송PP T/L","22~23년 경북본부 직할 변전협력회사 총액공사","7271,7200 보통점검, CVT 교체","2022-10-19 09:00","2022-10-19 18:00","취소","취소","매일"]
[252,"경북","영주","신영주S/S CB 7371","22-23년 영주전력지사 변전협력회사 총액공사","CB 보통점검","2022-10-21 09:00","2022-10-21 14:00","2022-10-21 09:00","2022-10-21 14:00","연속"]
[253,"경북","영주","신영주S/S CB 7300","22-23년 영주전력지사 변전협력회사 총액공사","CB 보통점검","2022-10-21 14:00","2022-10-21 18:00","2022-10-21 14:00","2022-10-21 18:00","연속"]
[254,"경북","구미","선산S/S #1 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #1BUS GIB 철거","2022-10-26 08:30","2022-10-31 18:00","2022-10-26 08:30","2022-10-31 18:00","연속"]
[255,"경북","구미","선산신포항 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #1BUS GIB 철거관련 안전거리 확보","2022-10-30 08:30","2022-10-30 18:00","2022-10-30 08:30","2022-10-30 18:00","연속"]
[256,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #1BUS GIB 철거관련 무부하가압 시험선로","2022-10-31 08:30","2022-10-31 18:00","2022-10-31 08:30","2022-10-31 18:00","연속"]
[257,"경북","구미","선산S/S #2 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #2BUS GIB 철거","2022-11-01 08:30","2022-11-06 18:00","2022-11-01 08:30","2022-11-06 18:00","연속"]
[258,"경북","구미","선산S/S #4 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","77bay #4M.Tr Bay GIS 교체","2022-11-01 08:30","2022-12-30 18:00","2022-11-01 08:30","2022-12-30 18:00","연속"]
[259,"경북","구미","선산S/S #3 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #2BUS GIB 철거관련 안전거리 확보","2022-11-05 08:30","2022-11-05 18:00","2022-11-05 08:30","2022-11-05 18:00","연속"]
[260,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #2BUS GIB 철거관련 무부하가압 시험선로","2022-11-06 08:30","2022-11-06 18:00","2022-11-06 08:30","2022-11-06 18:00","연속"]
[261,"경북","구미","선산S/S #1 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초공사(되메우기) 관련 안전거리 확보","2022-11-07 08:30","2022-11-07 18:00","2022-11-07 08:30","2022-11-07 18:00","연속"]
[262,"경북","구미","서대구선산#1 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초공사(되메우기) 관련 안전거리 확보","2022-11-07 08:30","2022-11-07 18:00","2022-11-07 08:30","2022-11-07 18:00","연속"]
[263,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S 345kV M.Tr 3차측 현대화 공사","345kV #2M.Tr 3차측 현대화공사","2022-10-04 09:00","2022-10-26 18:00","2022-10-11 09:00","2022-11-04 18:00","연속"]
[264,"부산울산","동부산","신양산북부산#2 T/L","'22년 동부산전력지사 가공송전 순시점검 위탁공사","-정밀점검","2022-10-10 09:00","2022-10-14 18:00","2022-10-31 09:00","2022-11-04 18:00","연속"]
[265,"부산울산","동부산","신양산S/S #1 M.Tr","신양산S/S 345kV M.Tr 3차측 현대화 공사","345kV #1M.Tr 3차측 현대화공사","2022-10-27 09:00","2022-11-16 18:00","2022-10-27 09:00","2022-11-16 18:00","연속"]
[266,"부산울산","동부산","신양산북부산#1 T/L","'22년 동부산전력지사 가공송전 순시점검 위탁공사","-정밀점검","2022-10-03 09:00","2022-10-07 18:00","2022-10-24 09:00","2022-10-28 18:00","연속"]
[267,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산S/S STATCOM 설치공사","- 345kV STATCOM 500mVar 1조 설치 - GIS(345kV 63kA) 2CB 설치 - 기타 부대작업 1식","2022-10-01 09:00","2022-10-02 18:00","2022-10-01 09:00","2022-10-02 18:00","연속"]
[268,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산S/S STATCOM 설치공사","- 345kV STATCOM 500mVar 1조 설치 - GIS(345kV 63kA) 2CB 설치 - 기타 부대작업 1식","2022-10-01 09:00","2022-10-02 18:00","2022-10-01 09:00","2022-10-02 18:00","연속"]
[269,"부산울산","북부산","신김해북부산#2 T/L","345kV 신김해-북부산#2T/L 송전선로 정밀점검","송전선로 정밀점검(1~57호) 철탑 추락방지장치 설치","2022-10-13 08:00","2022-10-21 18:00","2022-10-13 08:00","2022-10-21 18:00","연속"]
[270,"부산울산","서부산","서부산S/S CB 7571","서부산S/S 345kV #5,6 G/T 7571 GIS 동작시험","서부산S/S 345kV #5,6 G/T 7571 GIS 동작시험","2022-10-17 09:00","2022-10-17 18:00","2022-10-17 09:00","2022-10-17 18:00","연속"]
[271,"부산울산","서부산","서부산S/S CB 7500","서부산S/S 345kV 7500 BUS-TIE GIS 동작시험","서부산S/S 345kV 7500 BUS-TIE GIS 동작시험 [남부발전본부 7,8G/T O/H 시행기간]","2022-10-18 09:00","2022-10-18 14:00","2022-10-18 09:00","2022-10-18 14:00","연속"]
[272,"부산울산","서부산","서부산S/S CB 7471","서부산S/S 345kV #1,2 G/T 7471 GIS 동작시험","서부산S/S 345kV #1,2 G/T 7471 GIS 동작시험","2022-10-19 09:00","2022-10-19 18:00","2022-10-19 09:00","2022-10-19 18:00","연속"]
[273,"부산울산","서부산","서부산S/S CB 7400","서부산S/S 345kV 7400 BUS-TIE GIS 동작시험","서부산S/S 345kV 7400 BUS-TIE GIS 동작시험","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[274,"부산울산","서부산","서부산S/S CB 7472","서부산S/S 345kV #3,4 G/T 7472 GIS 동작시험","서부산S/S 345kV #3,4 G/T 7472 GIS 동작시험","2022-10-21 09:00","2022-10-21 18:00","2022-10-21 09:00","2022-10-21 18:00","연속"]
[275,"부산울산","서부산","서부산S/S #2 M.Tr","서부산S/S 345kV 차단기 용량부족 대체공사","○ 서부산S/S 집중감시제어반 구축 ○ 서부산S/S 71BAY SCADA 포인트 수용(모자익→ 집중감시제어반)","2022-10-24 09:00","2022-11-25 18:00","2022-10-24 09:00","2022-11-25 18:00","연속"]
[276,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","○ 서부산S/S 집중감시제어반 구축 ○ 서부산S/S 71BAY SCADA 포인트 수용(모자익→ 집중감시제어반)","2022-10-24 09:00","2022-11-25 18:00","2022-10-24 09:00","2022-11-25 18:00","연속"]
[277,"부산울산","서부산","서부산S/S CB 7572","서부산S/S 345kV #7,8 G/T 7572 GIS 동작시험","서부산S/S 345kV #7,8 G/T 7572 GIS 동작시험 [남부발전본부 7,8G/T O/H 시행기간]","2022-10-18 14:00","2022-10-18 18:00","2022-10-18 14:00","2022-10-18 18:00","연속"]
[278,"부산울산","서부산","신김해신녹산#1 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 : 23~52호(20기)","2022-10-16 07:00","2022-10-26 18:00","2022-10-16 07:00","2022-10-26 18:00","연속"]
[279,"부산울산","서부산","신김해신녹산#2 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 : 23~52호(20기)","2022-10-27 07:00","2022-10-29 18:00","2022-10-27 07:00","2022-10-29 18:00","연속"]
[280,"부산울산","울산","신온산S/S #1 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","74Bay 해당 #1BUS, 7472GIS 대체","2022-10-26 09:00","2022-11-08 18:00","2022-10-26 09:00","2022-11-08 18:00","연속"]
[281,"부산울산","울산","북부산울산TP#1 T/L","철탑 추락방지장치 설치","추락방지장치 설치 No. 1~32(32기)","2022-10-15 08:00","2022-10-23 18:00","2022-10-15 08:00","2022-10-23 18:00","연속"]
[282,"경남","직할","신김해북부산#1 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-10-10 08:00","2022-10-12 14:00","2022-10-10 08:00","2022-10-12 14:00","연속"]
[283,"경남","직할","신김해S/S #1 BUS","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-10-04 08:00","2022-10-05 17:30","2022-10-04 08:00","2022-10-05 17:30","연속"]
[284,"경남","직할","신김해S/S #2 BUS","345kV 신김해S/S 74BAY 용량부족 GIS 대체공사","345kV 신김해S/S 74BAY 용량부족 GIS 대체공사","2022-10-30 09:00","2022-11-10 18:00","2022-10-30 09:00","2022-11-10 18:00","연속"]
[285,"경남","직할","신김해북부산#2 T/L","신김해S/S 디지털축소형 모자익 대체공사","신김해S/S 디지털축소형 모자익 대체공사","2022-10-12 14:00","2022-10-14 18:00","취소","취소","연속"]
[286,"경남","직할","창원삼천포TP#2 T/L","345kV 창원-삼천포화력T/L 추락방지장치 설치공사","345kV 창원-삼천포화력#2T/L 수평 추락방지장치 설치","2022-10-24 09:00","2022-10-28 18:00","2022-10-24 09:00","2022-10-28 18:00","매일"]
[287,"경남","직할","창원삼천포TP#1 T/L","345kV 창원-삼천포화력T/L 추락방지장치 설치공사","345kV 창원-삼천포화력#1T/L 수평 추락방지장치 설치","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","매일"]
[288,"경남","진주","의령S/S #1 M.Tr","의령S/S #1M.Tr 보호배전반 교체","1. 2차 GIS(6144) 보통점검 2. 3차 VCB(4179)조작시험 및 #1,2DS 보통점검","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[289,"경남","진주","하동T/P CB 7372","하동T/P 7372, 7671 GIS 조작시험","하동T/P 7372, 7671 GIS 조작시험","2022-10-20 10:00","2022-10-20 14:00","2022-10-20 10:00","2022-10-20 14:00","연속"]
[290,"경남","진주","하동T/P CB 7671","하동T/P 7372, 7671 GIS 조작시험","하동T/P 7372, 7671 GIS 조작시험","2022-10-20 14:00","2022-10-20 17:00","2022-10-20 14:00","2022-10-20 17:00","연속"]
[291,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 수평 추락방지장치 설치공사","○ 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치(No.2~91) ○ 작업구간 : No.2~91","2022-10-22 07:00","2022-10-25 18:00","취소","취소","연속"]
[292,"경남","진주","하동T/P CB 7200","하동T/P 7200 GIS 조작시험","하동T/P 7200 GIS 조작시험","2022-10-14 10:00","2022-10-14 14:00","2022-10-14 10:00","2022-10-14 14:00","연속"]
[293,"경남","진주","하동T/P CB 7172","하동T/P 7100,7172 GIS 조작시험","하동T/P 7100,7172 GIS 조작시험","2022-10-07 14:00","2022-10-07 17:00","2022-10-07 14:00","2022-10-07 17:00","연속"]
[294,"경남","진주","하동T/P CB 7100","하동T/P 7100,7172 GIS 조작시험","하동T/P 7100,7172 GIS 조작시험","2022-10-07 10:00","2022-10-07 14:00","2022-10-07 10:00","2022-10-07 14:00","연속"]
[295,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 수평 추락방지장치 설치공사","○ 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치(No.2~91) ○ 작업구간 : No.2~91","2022-10-17 07:00","2022-10-21 18:00","취소","취소","연속"]
[296,"광주전남",null,"한빛#1N/P #1 기동변압기(X02) (CB 7F00, 7F72)","한빛1호기 26차 계획예방정비 * 조작차단기 : CB 7F00, 7F72","○ 한빛1호기 계획예방정비 수행 ○ GIB 개선 공사","2022-10-31 11:00","2022-12-08 14:00","2022-10-31 11:00","2022-12-08 14:00","연속"]
[297,"광주전남",null,"한빛#3N/P #6 대기보조변압기 (CB 7C00, 7C71)","한빛6호기 14차 O/H 중 대기보조변압기 점검 * 조작차단기: 7C00, 7C71 CB","○ 대기보조변압기 점검 ○ 갑종보호계전기 점검","2022-10-19 10:00","2022-11-01 14:00","2022-10-19 10:00","2022-11-01 14:00","연속"]
[298,"인천",null,"인천C/C #3,4GT 주변압기 (CB 7500, 7571)","보호계전기 시험 및 정기검사","보호계전기 시험 및 정기검사","2022-10-13 09:00","2022-10-20 18:00","2022-10-13 09:00","2022-10-20 18:00","연속"]
[299,"인천",null,"인천C/C #2ST 주변압기 (CB 7600, 7671)","보호계전기 시험 및 정기검사","보호계전기 시험 및 정기검사","2022-10-13 09:00","2022-10-20 18:00","2022-10-13 09:00","2022-10-20 18:00","연속"]
[300,"인천",null,"서인천C/C #75 BUS","모선보호반 교체","모선보호반 교체","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[301,"대전세종충남",null,"태안T/P #75 BUS","7152, 7452DS 가스누기 발생 개소 보수 공사","7152, 7452DS 가스누기 발생 개소 보수 공사","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[302,"강원",null,"양양P/P #4호기 주변압기 (CB 7300, 7372)","#4 계획중간정비\n(보조기기 절연저항 측정 등)","양양 P/P No.4 Main Tr 휴전","2022-10-06 09:00","2022-10-06 18:00","2022-10-06 09:00","2022-10-06 18:00","연속"]
[303,"경북",null,"청송P/P #1호기 주변압기 (CB 7100, 7172)","1호기 CT/PT 비오차 시험 및 주변압기 가스절연모선 점검","CB 7100, CB 7172","2022-10-12 09:00","2022-10-19 16:00","2022-10-12 09:00","2022-10-19 16:00","연속"]
[304,"경북",null,"청송P/P #2호기 주변압기 (CB 7200, 7272)","2호기 CT/PT 비오차 시험 및 주변압기 가스절연모선 점검","CB 7200, CB 7272","2022-10-19 16:00","2022-10-26 16:00","2022-10-19 16:00","2022-10-26 16:00","연속"]
[305,"전북",null,"무주P/P #1호기 주변압기 (CB 7100, 7172)","자체기동발전기 예비시험","자체기동발전기 신뢰성 확인","2022-10-27 14:00","2022-10-27 16:00","2022-10-27 14:00","2022-10-27 16:00","연속"]
[306,"전북",null,"무주P/P #2호기 주변압기 (CB 7200, 7272)","자체기동발전기 예비시험","자체기동발전기 신뢰성 확인","2022-10-27 14:00","2022-10-27 16:00","2022-10-27 14:00","2022-10-27 16:00","연속"]

{"sheet":"154설비","index":2,"n_rows":630,"n_cols":11,"rows_kept":630,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 10월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","쌍문미아 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-10-27 09:00","2022-10-27 18:00","2022-10-27 09:00","2022-10-27 18:00","연속"]
[2,"서울","성동","도봉방학#2 T/L","154kV 도봉(장암)S/S 옥내화 관련 지중T/L 건설공사","154kV 도봉-방학#2T/L 이설(도봉S/S ~ J/B#1 -> 장암S/S ~ J/B#1)","2022-10-04 09:00","2022-11-15 18:00","2022-10-04 09:00","2022-11-15 18:00","연속"]
[3,"서울","성동","성동휘경#1 T/L","'22년 성동P/O 노후 보호배전반 교체공사","성동, 휘경S/S 154kV 성동-휘경#1T/L 보호배전반 노후대체","2022-10-17 10:00","2022-10-20 18:00","2022-10-17 10:00","2022-10-20 18:00","연속"]
[4,"서울","성동","용두안암#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-10-14 09:30","2022-10-14 18:00","2022-10-14 09:30","2022-10-14 18:00","연속"]
[5,"서울","성동","용두안암#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-10-13 09:30","2022-10-13 18:00","2022-10-13 09:30","2022-10-13 18:00","연속"]
[6,"서울","성동","마장용두 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-10-12 09:30","2022-10-12 18:00","취소","취소","연속"]
[7,"서울","성동","왕십리용두 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-10-11 09:30","2022-10-11 18:00","취소","취소","연속"]
[8,"서울","성동","휘경종암#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-10-25 09:30","2022-10-25 18:00","취소","취소","연속"]
[9,"서울","성동","휘경종암#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-10-24 09:30","2022-10-24 18:00","취소","취소","연속"]
[10,"서울","중부","당인리S/S CB 6200","세니온제 IED 내부부품(콘덴서) 교체 성능개선 시행","성능개선 시행","2022-10-14 14:00","2022-10-14 18:00","2022-10-14 14:00","2022-10-14 18:00","연속"]
[11,"서울","중부","당인리S/S CB 6100","세니온제 IED 내부부품(콘덴서) 교체 성능개선 시행","성능개선 시행","2022-10-14 10:00","2022-10-14 14:00","2022-10-14 10:00","2022-10-14 14:00","연속"]
[12,"서울","중부","동빙고반포#1 T/L","22-23년 중부P/O 총액공사","170kV GIS 보통점검","2022-10-18 10:00","2022-10-18 17:00","2022-10-18 10:00","2022-10-18 17:00","연속"]
[13,"서울","중부","동빙고반포#2 T/L","22-23년 중부P/O 총액공사","170kV GIS 보통점검","2022-10-19 10:00","2022-10-19 17:00","2022-10-19 10:00","2022-10-19 17:00","연속"]
[14,"서울","중부","상암등촌#1 T/L","2022~2023년 가공송전협력회사 총액공사","추락방지장치 설치 : 2기, 피뢰기 설치 : 5기","2022-10-29 07:30","2022-10-29 13:00","2022-10-29 07:30","2022-10-29 13:00","연속"]
[15,"서울","중부","상암등촌#2 T/L","2022~2023년 가공송전협력회사 총액공사","추락방지장치 설치 : 2기, 위험표지구 보수 : 1경간, 번호찰 설치 : 3기","2022-10-29 13:00","2022-10-29 18:00","2022-10-29 13:00","2022-10-29 18:00","연속"]
[16,"서울","중부","수색상암 T/L","22-23년 중부P/O 총액공사","154kV LS 보통점검","2022-10-24 09:00","2022-10-24 18:00","2022-10-24 09:00","2022-10-24 18:00","연속"]
[17,"서울","중부","수색S/S #2 BUS","22-23년 중부P/O 총액공사","154kV LS 보통점검","2022-10-24 13:00","2022-10-24 18:00","2022-10-24 13:00","2022-10-24 18:00","연속"]
[18,"서울","중부","수색S/S #1 BUS","22-23년 중부P/O 총액공사","154kV LS 보통점검","2022-10-24 09:00","2022-10-24 13:00","2022-10-24 09:00","2022-10-24 13:00","연속"]
[19,"남서울","강남","동빙고반포#1 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설)","추락방지시설 설치","2022-10-11 08:00","2022-10-11 13:00","2022-10-11 08:00","2022-10-11 13:00","연속"]
[20,"남서울","강남","동빙고반포#2 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설)","추락방지시설 설치","2022-10-11 13:00","2022-10-11 18:00","2022-10-11 13:00","2022-10-11 18:00","연속"]
[21,"남서울","강남","신양재역삼#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-역삼#1T/L GIS","2022-10-01 08:00","2022-10-02 14:00","2022-10-01 08:00","2022-10-02 14:00","연속"]
[22,"남서울","강남","신양재역삼#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-역삼#2T/L GIS","2022-10-02 14:00","2022-10-03 18:00","2022-10-02 14:00","2022-10-03 18:00","연속"]
[23,"남서울","강남","논일역삼#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 논일-역삼#1T/L GIS","2022-10-04 08:00","2022-10-05 18:00","2022-10-04 08:00","2022-10-05 18:00","연속"]
[24,"남서울","강남","논일역삼#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 논일-역삼#2T/L GIS","2022-10-06 08:00","2022-10-07 18:00","2022-10-06 08:00","2022-10-07 18:00","연속"]
[25,"남서울","강남","신양재역삼#3 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-역삼#3T/L GIS","2022-10-08 08:00","2022-10-09 18:00","2022-10-08 08:00","2022-10-09 18:00","연속"]
[26,"남서울","강남","동빙고반포#1 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설)","추락방지시설 설치","2022-10-11 08:00","2022-10-11 13:00","취소","취소","연속"]
[27,"남서울","강남","동빙고반포#2 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설)","추락방지시설 설치","2022-10-11 13:00","2022-10-11 18:00","취소","취소","연속"]
[28,"남서울","강남","신양재역삼#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-역삼#1T/L GIS","2022-10-01 08:00","2022-10-02 14:00","취소","취소","연속"]
[29,"남서울","강남","신양재역삼#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-역삼#2T/L GIS","2022-10-02 14:00","2022-10-03 18:00","취소","취소","연속"]
[30,"남서울","강남","논일역삼#1 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 논일-역삼#1T/L GIS","2022-10-04 08:00","2022-10-05 18:00","취소","취소","연속"]
[31,"남서울","강남","논일역삼#2 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 논일-역삼#2T/L GIS","2022-10-06 08:00","2022-10-07 18:00","취소","취소","연속"]
[32,"남서울","강남","신양재역삼#3 T/L","2022년 강남전력지사 170kV GIS 정밀점검","2022년 강남전력지사 170kV GIS 정밀점검 - 점검대상 : 신양재-역삼#3T/L GIS","2022-10-08 08:00","2022-10-09 18:00","취소","취소","연속"]
[33,"남서울","동서울","가락S/S #2 BUS","동서울-가락#1T/L 무부하가압","동서울-가락#1T/L 무부하가압 선로","2022-10-19 09:50","2022-10-19 10:00","2022-10-19 09:50","2022-10-19 10:00","연속"]
[34,"남서울","동서울","강동천호#1 T/L","강동SS 강동-천호1TL GIS 전자변교체,조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-10-01 09:00","2022-10-01 14:00","2022-10-01 09:00","2022-10-01 14:00","연속"]
[35,"남서울","동서울","강동천호#2 T/L","강동SS 강동-천호2TL GIS 전자변교체,조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-10-01 14:00","2022-10-01 18:00","2022-10-01 14:00","2022-10-01 18:00","연속"]
[36,"남서울","동서울","동서울#2S/S #68 BUS","세종-포천 고속도로 건설 지장송전선로 지중화공사","한국도로공사 요청에 따른 154kV 팔수T/L 일부구간 지중화공사","2022-10-06 09:00","2022-10-07 18:00","2022-10-06 09:00","2022-10-07 18:00","연속"]
[37,"남서울","동서울","동서울#2S/S #68 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","- 지중화공사에 따른 선로가압전 무부하가압용 선로","2022-10-30 10:00","2022-10-31 18:00","2022-10-30 10:00","2022-10-31 18:00","연속"]
[38,"남서울","동서울","동서울#2S/S #68 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","- 지중화공사에 따른 선로가압전 무부하가압용 선로","2022-10-25 10:00","2022-10-26 18:00","취소","취소","연속"]
[39,"남서울","동서울","동서울#2S/S #68 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","지중화공사 관련 무무합 가압 BUS","2022-10-18 10:00","2022-10-20 10:00","2022-10-18 10:00","2022-10-20 10:00","연속"]
[40,"남서울","동서울","동서울#2S/S #68 BUS","세종-포천 고속도로 건설 지장송전선로 지중화공사","한국도로공사 요청에 따른 154kV 팔수T/L 일부구간 지중화공사","2022-10-11 09:00","2022-10-12 18:00","2022-10-11 09:00","2022-10-12 18:00","연속"]
[41,"남서울","동서울","동서울#2위례#1 T/L","세종-포천 고속도로 건설 지장송전선로 지중화공사","한국도로공사 요청에 따른 154kV 팔수T/L 일부구간 지중화 관련 무부하 가압 선로","2022-10-06 09:00","2022-10-07 18:00","2022-10-06 09:00","2022-10-07 18:00","연속"]
[42,"남서울","동서울","동서울#2위례#1 T/L","세종-포천 고속도로 건설 지장송전선로 지중화공사","한국도로공사 요청에 따른 154kV 동서울-신장T/L 일부구간 지중화공사 관련 무부하 가압 선로 휴전 요청","2022-10-11 09:00","2022-10-12 18:00","2022-10-11 09:00","2022-10-12 18:00","연속"]
[43,"남서울","동서울","동서울S/S #67 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","- 지중화공사에 따른 선로가압전 무부하가압용 선로","2022-10-30 10:00","2022-10-31 18:00","2022-10-30 10:00","2022-10-31 18:00","연속"]
[44,"남서울","동서울","동서울S/S #65 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","- 지중화공사에 따른 선로가압전 무부하가압용 선로","2022-10-30 10:00","2022-10-31 18:00","취소","취소","연속"]
[45,"남서울","동서울","동서울S/S #66 BUS(신)","세종-포천 고속도로 건설 지장송전선로 지중화공사","한국도로공사 요청에 따른 154kV 팔수T/L 일부구간 지중화공사","2022-10-06 09:00","2022-10-07 18:00","2022-10-06 09:00","2022-10-07 18:00","연속"]
[46,"남서울","동서울","동서울S/S #67 BUS(신)","세종-포천 고속도로 건설 지장송전선로 지중화공사","한국도로공사 요청에 따른 154kV 팔수T/L 일부구간 지중화공사","2022-10-06 09:00","2022-10-07 18:00","2022-10-06 09:00","2022-10-07 18:00","연속"]
[47,"남서울","동서울","동서울서종#2 T/L","세종-포천 고속도로 건설 지장송전선로 지중화공사","154kV 동서울-서종 및 팔수T/L 철탑 자재 운반을 위한 크레인 사용","2022-10-08 09:00","2022-10-09 18:00","2022-10-08 09:00","2022-10-09 18:00","연속"]
[48,"남서울","동서울","동서울신장#2 T/L","세종-포천 고속도로 건설 지장송전선로 지중화공사","한국도로공사 요청에 따른 154kV 동서울-신장T/L 일부구간 지중화","2022-10-06 09:00","2022-10-12 18:00","2022-10-06 09:00","2022-10-12 18:00","연속"]
[49,"남서울","동서울","동서울S/S #66 BUS(신)","세종-포천 고속도로 건설 지장송전선로 지중화공사","한국도로공사 요청에 따른 154kV 팔수T/L 일부구간 지중화공사","2022-10-11 09:00","2022-10-12 18:00","2022-10-11 09:00","2022-10-12 18:00","연속"]
[50,"남서울","동서울","동서울S/S #67 BUS(신)","세종-포천 고속도로 건설 지장송전선로 지중화공사","한국도로공사 요청에 따른 154kV 동서울-신장T/L 일부구간 지중화공사","2022-10-11 09:00","2022-10-12 18:00","2022-10-11 09:00","2022-10-12 18:00","연속"]
[51,"남서울","동서울","동서울S/S #66 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","- 지중화공사에 따른 선로가압전 무부하가압용 선로","2022-10-30 10:00","2022-10-31 18:00","2022-10-30 10:00","2022-10-31 18:00","연속"]
[52,"남서울","동서울","동서울송파#1 T/L","154kV 동서울-송파,가락T/L 지중화공사","LH 요청에 따른 154kV 동서울-송파,가락T/L 지중화공사","2022-10-26 09:00","2022-11-03 18:00","2022-10-26 09:00","2022-11-03 18:00","연속"]
[53,"남서울","동서울","동서울S/S #67 BUS","동서울S/S #62D.Tr 현장개조 및 설치공사","154kV M.Tr(45/60MVA) 현장개조 및 설치공사","2022-10-04 09:00","2022-10-21 18:00","2022-10-04 09:00","2022-10-21 18:00","연속"]
[54,"남서울","동서울","동서울가락#1 T/L","동서울-송파,가락T/L 지중화","동서울-송파,가락T/L 지중화","2022-10-04 09:00","2022-10-20 18:00","2022-10-04 09:00","2022-10-20 18:00","연속"]
[55,"남서울","동서울","동서울신장#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","세종-포천 고속도로 건설 지장송전선로 지중화(이설) 요청에 따른 송전선로 일부구간 지중화공사","2022-10-13 09:00","2022-10-20 18:00","2022-10-13 09:00","2022-10-20 18:00","연속"]
[56,"남서울","동서울","동서울S/S #65 BUS(신)","동서울S/S 154kV 옥외철구 GIS화 공사","○ 옥외철구-&gtGIS 운전전환 * 34CCT ○ 기타 부대작업 * 1식","2022-10-18 10:00","2022-10-20 10:00","2022-10-18 10:00","2022-10-20 10:00","연속"]
[57,"남서울","동서울","동서울S/S #66 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","지중화공사 관련 무무합 가압 BUS","2022-10-18 10:00","2022-10-20 10:00","2022-10-18 10:00","2022-10-20 10:00","연속"]
[58,"남서울","동서울","동서울S/S #67 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","지중화공사 관련 무무합 가압 BUS","2022-10-18 10:00","2022-10-20 10:00","2022-10-18 10:00","2022-10-20 10:00","연속"]
[59,"남서울","동서울","동서울S/S #60 BUS(신)","동서울S/S 154kV 옥외철구 GIS화 공사","○ 옥외철구-&gtGIS 운전전환 * 34CCT ○ 기타 부대작업 * 1식","2022-10-18 10:00","2022-10-20 10:00","2022-10-18 10:00","2022-10-20 10:00","연속"]
[60,"남서울","동서울","동서울서종#2 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","- 154kV 동서울-서종T/L 지중화공사에 따른 기설철탑과 CH 간 전력선 가선 - 선로가압전 무부하가압 등","2022-10-21 09:00","2022-10-26 18:00","2022-10-26 09:00","2022-10-31 18:00","연속"]
[61,"남서울","동서울","동서울S/S #67 BUS(신)","154kV 동서울-강동 등 3개T/L 지중화공사","- 지중화공사에 따른 선로가압전 무부하가압용 선로","2022-10-25 10:00","2022-10-26 18:00","취소","취소","연속"]
[62,"남서울","동서울","동서울S/S #66 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","- 지중화공사에 따른 선로가압전 무부하가압용 선로","2022-10-25 10:00","2022-10-26 18:00","취소","취소","연속"]
[63,"남서울","동서울","동서울서종#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","- 154kV 동서울-서종T/L 지중화공사에 따른 기설철탑과 CH 간 전력선 가선 - 선로가압전 무부하가압 등","2022-10-27 09:00","2022-10-31 18:00","취소","취소","연속"]
[64,"남서울","동서울","신장S/S #1 BUS","세종-포천 고속도로 건설 지장송전선로 지중화공사","한국도로공사 요청에 따른 154kV 동서울-신장T/L 일부구간 지중화공사","2022-10-11 09:50","2022-10-11 10:00","2022-10-11 09:50","2022-10-11 10:00","연속"]
[65,"남서울","동서울","신장덕소#2 T/L","'21~22년 동서울 지중송전 위탁공사","C/T 피뢰기 점검","2022-10-06 09:00","2022-10-06 18:00","2022-10-06 09:00","2022-10-06 18:00","연속"]
[66,"남서울","동서울","신장덕소#1 T/L","'21~22년 동서울 지중송전 위탁공사","C/T 피뢰기 점검","2022-10-05 09:00","2022-10-05 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[67,"남서울","동서울","신장S/S CB 6100","25.8kV 신규수용개폐장치 증설공사","신장S/S 25.8kV 신규수용개폐장치 증설공사(2Bay) 관련 154kV 모선통합","2022-10-31 09:00","2022-11-06 18:00","취소","취소","연속"]
[68,"남서울","동서울","신장S/S #1 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","지중화공사 관련 무무합 가압 BUS","2022-10-19 09:50","2022-10-19 10:00","2022-10-19 09:50","2022-10-19 10:00","연속"]
[69,"남서울","동서울","동서울#2위례#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","- 지중화공사에 따른 선로가압전 무부하가압용 선로","2022-10-30 09:00","2022-10-31 18:00","2022-10-30 09:00","2022-10-31 18:00","연속"]
[70,"남서울","동서울","동서울#2위례#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","- 지중화공사에 따른 선로가압전 무부하가압용 선로","2022-10-18 09:00","2022-10-20 18:00","2022-10-18 09:00","2022-10-20 18:00","연속"]
[71,"남서울","동서울","동서울#2위례#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","- 지중화공사에 따른 선로가압전 무부하가압용 선로","2022-10-25 09:00","2022-10-26 18:00","취소","취소","연속"]
[72,"남서울","영등포","가양S/S CB 6100","영등포전력지사 154kV GIS 정밀점검공사","154kV BUS TIE 정밀점검","2022-10-17 09:00","2022-10-18 18:00","2022-10-17 09:00","2022-10-18 18:00","연속"]
[73,"남서울","영등포","가양등촌#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#3M.Tr 1차 GIS)","2022-10-14 13:00","2022-10-14 18:00","2022-10-14 13:00","2022-10-14 18:00","연속"]
[74,"남서울","영등포","광명구공#1 T/L","154kV 광명S/S 가스변압기 교체공사(무부하가압)","무부하 가압","2022-10-25 14:00","2022-10-26 14:00","2022-10-25 14:00","2022-10-26 14:00","연속"]
[75,"남서울","영등포","광명구공#3 T/L","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#4M.Tr 1차 GIS)","2022-10-07 13:00","2022-10-07 18:00","2022-10-07 13:00","2022-10-07 18:00","연속"]
[76,"남서울","영등포","광명구공#3 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 광명-구공#3T/L GIS 정밀점검","2022-10-04 09:00","2022-10-05 18:00","2022-10-04 09:00","2022-10-05 18:00","연속"]
[77,"남서울","영등포","구공S/S #66 BUS","영등포전력지사 154kV GIS 정밀점검공사","무부하가압용(#4M.Tr 1차 GIS)","2022-10-07 13:00","2022-10-07 18:00","2022-10-07 13:00","2022-10-07 18:00","연속"]
[78,"남서울","영등포","상암등촌#1 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 상암-등촌#1T/L 정밀점검","2022-10-20 09:00","2022-10-21 18:00","2022-10-20 09:00","2022-10-21 18:00","연속"]
[79,"남서울","영등포","신광명천왕#3 T/L","154kV 신광명-천왕#3T/L 송전선로 보호반 대체공사","(신광명)154kV 신광명-천왕#3T/L 송전선로 보호반 대체공사 (천왕)154kV 신광명-천왕#3T/L 송전선로 보호반 대체공사","2022-10-12 09:00","2022-10-14 18:00","2022-10-12 09:00","2022-10-14 18:00","연속"]
[80,"남서울","영등포","신광명S/S #61 BUS","154kV 광명S/S 인출전력구 OF케이블 선종교체 상시험","광명S/S 인출전력구 선종교체 무부하 가압전 상시험","2022-10-31 10:00","2022-10-31 12:00","2022-10-31 10:00","2022-10-31 12:00","연속"]
[81,"남서울","영등포","신광명시흥#2 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설)","추락방지시설 설치","2022-10-24 08:00","2022-10-27 18:00","2022-10-24 08:00","2022-10-27 18:00","연속"]
[82,"남서울","영등포","신광명시흥#1 T/L","'22-'23년 가공송전 협력회사 총액공사(추락방지시설)","추락방지시설 설치","2022-10-17 08:00","2022-10-21 18:00","2022-10-17 08:00","2022-10-21 18:00","연속"]
[83,"남서울","영등포","신광명S/S #65 BUS","신광명 노후 주변압기 교체공사(#2M.Tr_무부하)","345kV M.Tr 교체 3대","2022-10-15 09:00","2022-10-15 18:00","2022-10-15 09:00","2022-10-15 18:00","연속"]
[84,"남서울","영등포","천왕오류#2 T/L","2021-2022년 영등포전력지사 지중송전설비 위탁정비공사","OF케이블 절연유 채유","2022-10-21 09:00","2022-10-21 18:00","2022-10-21 09:00","2022-10-21 18:00","연속"]
[85,"남서울","영등포","천왕구로#2 T/L","2021-2022년 영등포전력지사 지중송전설비 위탁정비공사","OF케이블 절연유 채유","2022-10-19 09:00","2022-10-20 18:00","2022-10-19 09:00","2022-10-20 18:00","연속"]
[86,"남서울","영등포","천왕구로#1 T/L","2021-2022년 영등포전력지사 지중송전설비 위탁정비공사","OF케이블 절연유 채유","2022-10-17 09:00","2022-10-18 18:00","2022-10-17 09:00","2022-10-18 18:00","연속"]
[87,"남서울","영등포","화곡마곡#2 T/L","영등포전력지사 154kV GIS 정밀점검공사","154kV 화곡-마곡#2T/L GIS 정밀점검","2022-10-09 09:00","2022-10-10 18:00","2022-10-09 09:00","2022-10-10 18:00","연속"]
[88,"남서울","직할","노들노량진 T/L","'21-'22년 남서울 직할 지중송전정비 전문회사 총액공사","○ 작 업 명 : 절연유 채유 및 접지선 교체 ○ 작업개소 : 노량진EBG, J/B#9-1, M/H#14 ○ 작업내용 : 절연유 채유 및 접지선 교체","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[89,"남서울","직할","봉천신길#1 T/L","봉천-신길#1T/L 보호배전반 대체공사","봉천-신길#1T/L 보호배전반 대체공사 - 봉천, 신길 양단 시행","2022-10-31 09:00","2022-11-04 18:00","2022-10-31 09:00","2022-11-04 18:00","연속"]
[90,"남서울","직할","사당신림 T/L","'21-'22년 남서울 직할 지중송전정비 전문회사 총액공사","○ 작 업 명 : 절연유 채유 및 접지선 교체 ○ 작업개소 : 사당, 신림EBG, SJ 및 M/H#2 등 4개 맨홀 ○ 작업내용 : 절연유 채유 비규격 접지선 교체","2022-10-25 09:00","2022-10-28 18:00","2022-10-25 09:00","2022-10-28 18:00","연속"]
[91,"남서울","직할","신문래구로#1 T/L","'21-'22년 남서울 직할 지중송전정비전문회사 총액공사","○ 작 업 명 : 절연유 채유 ○ 작업개소 : 신문래EBG, SJ, M/H#25 ○ 작업내용 : 절연유 채유 및 열화분석","2022-10-05 09:00","2022-10-05 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[92,"남서울","직할","신문래구로#2 T/L","'21-'22년 남서울 직할 지중송전정비 전문회사 총액공사","○ 작 업 명 : 절연유 채유 ○ 작업개소 : 신문래EBG, SJ, M/H#25 ○ 작업내용 : 절연유 채유 및 열화분석","2022-10-06 09:00","2022-10-06 18:00","2022-10-06 09:00","2022-10-06 18:00","연속"]
[93,"남서울","직할","신문래노량진 T/L","'21-'22년 남서울 직할 지중송전정비 전문회사 총액공사","○ 작 업 명 : 비규격 접지선 교체 ○ 작업개소 : M/H#1 등 16개 맨홀 ○ 작업내용 : 비규격 접지선 교체(150-&gt240SQ)","2022-10-11 09:00","2022-10-17 18:00","2022-10-11 09:00","2022-10-17 18:00","연속"]
[94,"남서울","직할","신문래여의 T/L","'21-'22년 남서울 직할 지중송전정비 전문회사 총액공사","○ 작 업 명 : 비규격 접지선 교체 ○ 작업개소 : M/H#1 등 13개 맨홀 및 J/B#15, #18 ○ 작업내용 : 절연유 채유 및 열화분석","2022-10-18 09:00","2022-10-24 18:00","2022-10-18 09:00","2022-10-24 18:00","연속"]
[95,"남서울","직할","신문래노들 T/L","'21-'22년 남서울 직할 지중송전정비 전문회사 총액공사","○ 작 업 명 : 절연유 채유 ○ 작업개소 : 신문래EBG, SJ, M/H#8 ○ 작업내용 : 절연유 채유 및 열화분석","2022-10-31 09:00","2022-10-31 18:00","2022-10-31 09:00","2022-10-31 18:00","연속"]
[96,"남서울","직할","신문래영오#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2022-10-05 09:00","2022-10-05 15:00","2022-10-05 09:00","2022-10-05 15:00","연속"]
[97,"남서울","직할","신문래영오#1 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2022-10-04 09:00","2022-10-04 15:00","2022-10-04 09:00","2022-10-04 15:00","연속"]
[98,"인천","김포","신경서경서#3 T/L","경서S/S 170kV 신경서-경서#3T/L GIS SA 혼용화공사","경서S/S 170kV 신경서-경서#3T/L GIS SA 혼용화공사","2022-10-19 09:00","2022-10-19 18:00","2022-10-19 09:00","2022-10-19 18:00","연속"]
[99,"인천","김포","신경서경서#1 T/L","경서S/S 170kV 신경서-경서#1T/L GIS SA 혼용화공사","경서S/S 170kV 신경서-경서#1T/L GIS SA 혼용화공사","2022-10-13 09:00","2022-10-13 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[100,"인천","김포","영종경서 T/L","경서S/S 170kV 영종-경서T/L GIS SA 혼용화공사","경서S/S 170kV 영종-경서T/L GIS SA 혼용화공사","2022-10-12 09:00","2022-10-12 18:00","2022-10-04 09:00","2022-10-04 18:00","연속"]
[101,"인천","김포","경서북인천#2 T/L","경서S/S 170kV 경서-북인천#2T/L GIS SA 혼용화공사","경서S/S 170kV 경서-북인천#2T/L GIS SA 혼용화공사","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[102,"인천","김포","경서양촌#1 T/L","검단3구역 도시개발사업 송전선로 지중화공사","○ 목적 : 검단3구역 도시개발관련 송전선로 지중화 ○ 공사구간 : 경서-양촌T/L No.15~19(약 1.4km) ○ 공사내용 : C/T 2기설치, 철탑 1기교체(인클로징), 임시철탑 5기 철거 ※ 요청자(검단3구역 도시개발조합) 시행","2022-10-18 08:00","2022-10-25 18:00","2022-10-18 08:00","2022-10-25 18:00","연속"]
[103,"인천","김포","경서양촌#2 T/L","검단3구역 도시개발사업 송전선로 지중화공사","○ 목적 : 검단3구역 도시개발관련 송전선로 지중화 ○ 공사구간 : 경서-양촌T/L No.15~19(약 1.4km) ○ 공사내용 : C/T 2기설치, 철탑 1기교체(인클로징), 임시철탑 5기 철거 ※ 요청자(검단3구역 도시개발조합) 시행","2022-10-18 08:00","2022-10-25 18:00","2022-10-18 08:00","2022-10-25 18:00","연속"]
[104,"인천","김포","경서북인천#1 T/L","경서S/S 170kV 경서-북인천#1T/L GIS SA 혼용화공사","경서S/S 170kV 경서-북인천#1T/L GIS SA 혼용화공사","2022-10-14 09:00","2022-10-14 18:00","2022-10-06 09:00","2022-10-06 18:00","연속"]
[105,"인천","김포","신경서경서#2 T/L","경서S/S 170kV 신경서-경서#2T/L GIS SA 혼용화공사","경서S/S 170kV 신경서-경서#2T/L GIS SA 혼용화공사","2022-10-18 09:00","2022-10-18 18:00","2022-10-18 09:00","2022-10-18 18:00","연속"]
[106,"인천","김포","신김포S/S CB 6200","신김포S/S 345kV #3M.Tr 증설공사(170kV GIS)","170kV GIS 무부하가압(61,66BUS)","2022-10-09 18:00","2022-10-10 18:00","2022-10-09 18:00","2022-10-10 18:00","연속"]
[107,"인천","김포","신김포S/S #61 BUS","신김포S/S 345kV #3M.Tr 증설공사(170kV GIS)","○ 170kV GIS x 1CCT 증설(#3M.Tr용)","2022-10-08 08:00","2022-10-10 18:00","2022-10-08 08:00","2022-10-10 18:00","연속"]
[108,"인천","김포","신김포S/S #66 BUS","신김포S/S 345kV #3M.Tr 증설공사(170kV GIS)","○ 170kV GIS x 1CCT 증설(#3M.Tr용)","2022-10-08 08:00","2022-10-10 18:00","2022-10-08 08:00","2022-10-10 18:00","연속"]
[109,"인천","김포","신김포S/S SEC CB 65660","신김포S/S 345kV #3M.Tr 증설공사(170kV GIS)","170kV GIS 무부하가압(61,66BUS)","2022-10-09 18:00","2022-10-10 18:00","2022-10-09 18:00","2022-10-10 18:00","연속"]
[110,"인천","김포","신김포양곡#1 T/L","양곡S/S 170kV 신김포-양곡#1T/L GIS 조작시험","양곡S/S 170kV 신김포-양곡#1T/L GIS 조작시험","2022-10-17 09:00","2022-10-17 14:00","2022-10-17 09:00","2022-10-17 14:00","연속"]
[111,"인천","김포","신김포양곡#2 T/L","양곡S/S 170kV 신김포-양곡#2T/L GIS 조작시험","양곡S/S 170kV 신김포-양곡#2T/L GIS 조작시험","2022-10-17 14:00","2022-10-17 18:00","2022-10-17 14:00","2022-10-17 18:00","연속"]
[112,"인천","김포","신경서왕길#2 T/L","154kV 신경서-왕길#2T/L EBA 절연유 채유","154kV 신경서-왕길#2T/L EBA 절연유 채유 - 공사대상 : #1C/T EBA(3상), #2C/T EBA(3상)","2022-10-31 14:00","2022-11-02 18:00","2022-10-31 14:00","2022-11-02 18:00","연속"]
[113,"인천","김포","신경서왕길#1 T/L","154kV 신경서-왕길#1T/L EBA 절연유 채유","154kV 신경서-왕길#1T/L EBA 절연유 채유 - 공사대상 : #1C/T EBA(3상), #2C/T EBA(3상)","2022-10-26 09:00","2022-10-28 13:00","2022-10-26 09:00","2022-10-28 13:00","연속"]
[114,"인천","김포","왕길양촌#1 T/L","154kV 왕길S/S #4M.Tr GIS 설치공사(무부하가압)","-154kV GIS × 4CCT 설치 -기타부대공사 × 1식 설치","2022-10-06 18:00","2022-10-07 18:00","2022-10-06 18:00","2022-10-07 18:00","연속"]
[115,"인천","부평","관교만수#1 T/L","관교S/S, 만수S/S 관교만수#1T/L 보호반교체","관교S/S, 만수S/S 관교만수#1T/L 보호반교체","2022-10-04 09:00","2022-10-07 18:00","취소","취소","연속"]
[116,"인천","부평","인천남인천#1 T/L","남인천S/S 인천남인천#1 T/L GIS 정밀점검","남인천S/S 인천남인천#1 T/L GIS 정밀점검","2022-10-31 09:00","2022-11-04 18:00","2022-10-31 09:00","2022-11-04 18:00","연속"]
[117,"인천","부평","부흥부개#2 T/L","부흥부개#2T/L 보호반 교체공사","- 부흥부개#2T/L 보호반교체 ※ 병행작업 : 부흥부개#2T/L SA혼용화 케이블이설","2022-10-01 09:00","2022-10-03 18:00","2022-10-01 09:00","2022-10-03 18:00","연속"]
[118,"인천","부평","송현포스코CC#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2022-10-13 09:00","2022-10-13 18:00","2022-10-13 09:00","2022-10-13 18:00","연속"]
[119,"인천","부평","송현포스코CC#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[120,"인천","부평","신경서영종 T/L","신경서SS 신경서영종T/L GIS 정밀점검","신경서SS 신경서영종T/L GIS 정밀점검","2022-10-17 09:00","2022-10-21 18:00","취소","취소","연속"]
[121,"인천","부평","북인천원창 T/L","원창S/S SK에너지T/L GIS 정밀점검 관련 무부하 가압 선로","SK에너지T/L(6A7) 정밀점검","2022-10-10 09:00","2022-10-10 18:00","2022-10-10 09:00","2022-10-10 18:00","연속"]
[122,"인천","부평","계양원창 T/L","원창S/S 계양원창T/L 보호반 교체공사","원창S/S 계양원창T/L 보호반 교체공사","2022-10-11 09:00","2022-10-14 18:00","2022-10-11 09:00","2022-10-14 18:00","연속"]
[123,"인천","부평","학익연수#2 T/L","학익SS #3M.Tr 1차 GIS 정밀점검","학익SS #3M.Tr 1차 GIS 정밀점검 관련 무부하가압 선로","2022-10-27 09:00","2022-10-27 18:00","취소","취소","연속"]
[124,"인천","부평","학익연수#2 T/L","학익SS #3M.Tr 1차 GIS 정밀점검","학익SS #3M.Tr 1차 GIS 정밀점검 관련 무부하가압 선로","2022-10-25 09:00","2022-10-25 18:00","2022-10-25 09:00","2022-10-27 18:00","연속"]
[125,"인천","시흥","시화동시화#1 T/L","동시화S/S 170kV 시화동시화#1T/L 보호반 대체","동시화S/S 170kV 시화동시화#1T/L 보호반 대체","2022-10-31 09:00","2022-11-04 18:00","2022-10-31 09:00","2022-11-04 18:00","연속"]
[126,"인천","시흥","신광명소래 T/L","154kV 서서울-소래T/L 추락방지시설 설치공사","ㅇ 추락방지시설 설치(수평) - No.45~92(설치대상 : 총 37기) - No.76부터 4회선 병가구간","2022-10-01 08:00","2022-10-03 18:00","2022-10-01 08:00","2022-10-03 18:00","매일"]
[127,"인천","시흥","신시흥남동#1 T/L","154kV 남동 등 2개T/L 추락방지시설 설치공사","#1T/L 추락방지시설 설치(수평) - 대상 : No.1~36 [No.1~32은 도림T/L 4회선 병가구간]","2022-10-21 08:00","2022-10-23 18:00","2022-10-21 08:00","2022-10-23 18:00","매일"]
[128,"인천","시흥","신시흥도림#1 T/L","154kV 남동 등 2개T/L 추락방지시설 설치공사","#1T/L 추락방지시설 설치(수평) - 대상 : No.1~36 [No.1~32은 도림T/L 4회선 병가구간]","2022-10-22 08:00","2022-10-23 18:00","2022-10-22 08:00","2022-10-23 18:00","매일"]
[129,"인천","시흥","신시흥남동#2 T/L","154kV 남동 등 2개T/L 추락방지시설 설치공사","#2T/L 추락방지시설 설치(수평) - 대상 : No.1~36 [No.1~32은 도림T/L 4회선 병가구간]","2022-10-28 08:00","2022-10-30 18:00","2022-10-28 08:00","2022-10-30 18:00","매일"]
[130,"인천","시흥","신시흥도림#2 T/L","154kV 남동 등 2개T/L 추락방지시설 설치공사","#2T/L 추락방지시설 설치(수평) - 대상 : No.1~36 [No.1~32은 도림T/L 4회선 병가구간]","2022-10-29 08:00","2022-10-30 18:00","2022-10-29 08:00","2022-10-30 18:00","매일"]
[131,"인천","직할","신부평고강#1 T/L","원종C/T EBA 비표준형 자기애관 교체공사","비표준형 자기애관 폴리머애관으로 교체","2022-10-29 09:00","2022-10-30 18:00","2022-10-29 09:00","2022-10-30 18:00","연속"]
[132,"인천","직할","임학계양#2 T/L","임학S/S 임학계양2T/L 초기점검","임학S/S 임학계양2T/L 초기점검","2022-10-13 09:00","2022-10-13 18:00","2022-10-13 09:00","2022-10-13 18:00","연속"]
[133,"인천","직할","임학계양#1 T/L","임학S/S 임학계양1T/L 보통점검","임학S/S 임학계양1T/L 보통점검","2022-10-12 09:00","2022-10-12 18:00","2022-10-12 09:00","2022-10-12 18:00","연속"]
[134,"인천","직할","신부평임학#1 T/L","임학S/S 신부평임학1T/L GIS 정밀점검","임학S/S 신부평임학1T/L GIS 정밀점검","2022-10-31 09:30","2022-11-02 18:00","2022-10-31 09:30","2022-11-02 18:00","연속"]
[135,"인천","김포","왕길양촌#1 T/L","왕길S/S #4M.Tr 증설 무부하가압용","왕길S/S #4M.Tr 증설 무부하가압용","2022-10-20 09:00","2022-10-21 10:00","2022-10-20 09:00","2022-10-21 10:00","연속"]
[136,"경기북부","고양","양주고양#1 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","수평 와이어 추락방지시설 설치, 지지애자 교체","2022-10-04 07:00","2022-10-07 18:00","2022-10-04 07:00","2022-10-07 18:00","연속"]
[137,"경기북부","고양","양주고양#2 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","수평 와이어 추락방지시설 설치","2022-10-11 07:00","2022-10-14 18:00","2022-10-11 07:00","2022-10-14 18:00","연속"]
[138,"경기북부","고양","고양일산#2 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","피뢰기 설치","2022-10-13 07:00","2022-10-13 18:00","2022-10-13 07:00","2022-10-13 18:00","연속"]
[139,"경기북부","고양","양주금촌#2 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","수평 와이어 추락방지시설 설치","2022-10-11 07:00","2022-10-14 18:00","2022-10-11 07:00","2022-10-14 18:00","연속"]
[140,"경기북부","고양","양주금촌#1 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","수평 와이어 추락방지시설 설치","2022-10-04 07:00","2022-10-07 18:00","2022-10-04 07:00","2022-10-07 18:00","연속"]
[141,"경기북부","고양","신파주S/S CB 6200","21-22년 변전협력회사 총액공사","170kV GIS 보통점검","2022-10-13 09:00","2022-10-13 18:00","2022-10-13 09:00","2022-10-13 18:00","연속"]
[142,"경기북부","고양","신파주S/S SEC CB 65660","21-22년 변전협력회사 총액공사","170kV GIS 보통점검","2022-10-14 09:00","2022-10-14 18:00","2022-10-14 09:00","2022-10-14 18:00","연속"]
[143,"경기북부","고양","신파주원흥#2 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","피뢰기 설치(병가선로)","2022-10-14 07:00","2022-10-14 18:00","2022-10-14 07:00","2022-10-14 18:00","연속"]
[144,"경기북부","고양","신파주원흥#2 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","지지애자 교체(병가선로)","2022-10-06 07:00","2022-10-06 18:00","2022-10-06 07:00","2022-10-06 18:00","연속"]
[145,"경기북부","고양","원흥S/S #2 BUS","154kV 원흥S/S #3M.Tr 증설공사","- 154/23kV M.Tr (상분리형, 60MVA) 설치 × 1Bank - 170kV GIS(50kA 1,250A, GIB 포함) 설치 × 1CCT - 25.8kV GIS(25kA 600A, GIB 포함) 설치 × 9CCT - 변압기 IED보호배전반 설치 × 1면 - 이더넷 스위치반 설치 × 1식 - 기타 부대공사 × 1식","2022-10-19 15:00","2022-10-21 20:00","2022-10-19 15:00","2022-10-21 20:00","연속"]
[146,"경기북부","고양","원흥상암 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 초기점검","2022-10-26 07:00","2022-10-26 17:00","2022-10-26 07:00","2022-10-26 17:00","연속"]
[147,"경기북부","고양","신파주원흥#2 T/L","154kV 원흥S/S #3M.Tr 증설공사","- 154/23kV M.Tr (상분리형, 60MVA) 설치 × 1Bank - 170kV GIS(50kA 1,250A, GIB 포함) 설치 × 1CCT - 25.8kV GIS(25kA 600A, GIB 포함) 설치 × 9CCT - 변압기 IED보호배전반 설치 × 1면 - 이더넷 스위치반 설치 × 1식 - 기타 부대공사 × 1식","2022-10-17 09:00","2022-10-21 20:00","2022-10-17 09:00","2022-10-21 20:00","연속"]
[148,"경기북부","고양","원흥S/S #1 BUS","154kV 원흥S/S #3M.Tr 증설공사","- 154/23kV M.Tr (상분리형, 60MVA) 설치 × 1Bank - 170kV GIS(50kA 1,250A, GIB 포함) 설치 × 1CCT - 25.8kV GIS(25kA 600A, GIB 포함) 설치 × 9CCT - 변압기 IED보호배전반 설치 × 1면 - 이더넷 스위치반 설치 × 1식 - 기타 부대공사 × 1식","2022-10-17 09:00","2022-10-19 15:00","2022-10-17 09:00","2022-10-19 15:00","연속"]
[149,"경기북부","고양","원흥수색#1 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 초기점검","2022-10-27 07:00","2022-10-28 17:00","2022-10-27 07:00","2022-10-28 17:00","연속"]
[150,"경기북부","고양","일산S/S CB 6100","22-23년 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2022-10-12 09:30","2022-10-12 12:00","2022-10-12 09:30","2022-10-12 12:00","연속"]
[151,"경기북부","고양","지도능곡#2 T/L","'21-'22년 지중송전설비 위탁정비공사","OF케이블 절연유 시료채취를 위한 휴전","2022-10-21 09:00","2022-10-21 18:00","2022-10-21 09:00","2022-10-21 18:00","연속"]
[152,"경기북부","고양","지도능곡#1 T/L","'21-'22년 지중송전설비 위탁정비공사","OF케이블 절연유 시료채취를 위한 휴전","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[153,"경기북부","고양","일산지도#1 T/L","고양전력지사 관내T/L OPGW 항공장애표시구 설치공사 2차","154kV 일산-지도#1T/L 1경간 3개 항공구 설치","2022-10-24 07:00","2022-10-24 18:00","2022-10-24 07:00","2022-10-24 18:00","연속"]
[154,"경기북부","고양","지축현저#2 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 초기점검","2022-10-18 07:00","2022-10-18 17:00","2022-10-18 07:00","2022-10-18 17:00","연속"]
[155,"경기북부","고양","지축현저#1 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 초기점검","2022-10-17 07:00","2022-10-17 17:00","2022-10-17 07:00","2022-10-17 17:00","연속"]
[156,"경기북부","구리","구리신내#1 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 초기점검","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[157,"경기북부","구리","신의정부내촌#2 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-10-19 14:00","2022-10-19 18:00","2022-10-19 14:00","2022-10-19 18:00","연속"]
[158,"경기북부","구리","신의정부내촌#1 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-10-19 09:00","2022-10-19 14:00","2022-10-19 09:00","2022-10-19 14:00","연속"]
[159,"경기북부","구리","내촌용정#2 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-10-20 14:00","2022-10-20 18:00","2022-10-20 14:00","2022-10-20 18:00","연속"]
[160,"경기북부","구리","내촌용정#1 T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-10-20 09:00","2022-10-20 14:00","2022-10-20 09:00","2022-10-20 14:00","연속"]
[161,"경기북부","구리","마석청평HP#2 T/L","'22~23년 구리전력지사 변전협력회사 총액공사","'22~23년 구리전력지사 변전협력회사 총액공사 - 154kV 마석-청평HP#2T/L 보호반 교체공사(마석, 청평수력 양단)","2022-10-24 09:00","2022-10-27 18:00","2022-10-24 09:00","2022-10-27 18:00","연속"]
[162,"경기북부","구리","마석청평HP#1 T/L","'22~23년 구리전력지사 변전협력회사 총액공사","'22~23년 구리전력지사 변전협력회사 총액공사 - 154kV 마석-청평HP#1T/L 보호반 교체공사(마석, 청평수력 양단)","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[163,"경기북부","구리","미금화양 T/L","미금S/S 154lV #64M.Tr 개폐장치 설치공사(전문)","○ 154kV GIS(Main) 설치 ⅹ 1CCT","2022-10-20 10:00","2022-10-21 18:00","2022-10-20 10:00","2022-10-21 18:00","연속"]
[164,"경기북부","구리","미금S/S #61 BUS","미금S/S 154lV #64M.Tr 개폐장치 설치공사(전문)","○ 154kV GIS(Main) 설치 ⅹ 1CCT","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[165,"경기북부","구리","미금S/S CB 6300","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-10-14 09:00","2022-10-14 18:00","2022-10-14 09:00","2022-10-14 18:00","연속"]
[166,"경기북부","구리","미금S/S #66 BUS","미금S/S 154lV #64M.Tr 개폐장치 설치공사(전문)","○ 154kV GIS(Main) 설치 ⅹ 1CCT","2022-10-24 09:00","2022-11-03 18:00","2022-10-24 09:00","2022-11-03 18:00","연속"]
[167,"경기북부","구리","미금S/S CB 6200","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-10-13 09:00","2022-10-13 18:00","2022-10-13 09:00","2022-10-13 18:00","연속"]
[168,"경기북부","구리","진건별내#2 T/L","22년도 구리전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2022-10-26 09:00","2022-10-27 18:00","2022-10-26 09:00","2022-10-27 18:00","연속"]
[169,"경기북부","구리","진건별내#1 T/L","22년도 구리전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2022-10-24 09:00","2022-10-25 18:00","2022-10-24 09:00","2022-10-25 18:00","연속"]
[170,"경기북부","구리","서종S/S #1 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 지중화공사 관련 무부하가압 선로","2022-10-30 09:50","2022-10-30 10:00","2022-10-30 09:50","2022-10-30 10:00","연속"]
[171,"경기북부","구리","서종S/S #2 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 지중화공사 관련 무부하가압 선로","2022-10-25 09:50","2022-10-25 10:00","2022-10-25 09:50","2022-10-25 10:00","연속"]
[172,"경기북부","구리","신포천동두천#1 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","추락방지시설 설치","2022-10-26 07:00","2022-10-27 18:00","2022-10-26 07:00","2022-10-27 18:00","연속"]
[173,"경기북부","구리","신포천전곡#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","추락방지시설 설치공사","2022-10-31 07:00","2022-11-04 18:00","2022-10-31 07:00","2022-11-04 18:00","연속"]
[174,"경기북부","구리","신포천덕계#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","추락방지시설 설치공사(병가선로 휴전)","2022-10-31 07:00","2022-10-31 18:00","2022-10-31 07:00","2022-10-31 18:00","연속"]
[175,"경기북부","구리","신포천백학#1 T/L","22년도 구리전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2022-10-17 09:00","2022-10-18 18:00","2022-10-17 09:00","2022-10-18 18:00","연속"]
[176,"경기북부","구리","신포천동두천#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","추락방지시설 설치","2022-10-04 07:00","2022-10-12 18:00","2022-10-05 07:00","2022-10-12 18:00","연속"]
[177,"경기북부","구리","청평PP춘천열병합 T/L","청평양수SY 노후 154kV GIS 노후 대체공사","○ 170kV GIS(50kA, 2000A) 철거 x 5CCT ○ 170kV GIS(50kA, 2000A) 설치 x 5CCT ○ 154kV 모선보호배전반 x 1Set ○ 154kV 옥외분전반 x 1면 ○ 제어케이블 포·결선 철거 및 설치 x 1식 ○ 기타 부대공사 x 1식","2022-10-10 09:00","2022-10-20 18:00","2022-10-10 09:00","2022-10-20 18:00","연속"]
[178,"경기북부","구리","서종청평PP#1 T/L","청평양수SY 노후 154kV GIS 노후 대체공사","○ 170kV GIS(50kA, 2000A) 철거 x 5CCT ○ 170kV GIS(50kA, 2000A) 설치 x 5CCT ○ 154kV 모선보호배전반 x 1Set ○ 154kV 옥외분전반 x 1면 ○ 제어케이블 포·결선 철거 및 설치 x 1식 ○ 기타 부대공사 x 1식","2022-10-10 09:00","2022-10-20 18:00","2022-10-10 09:00","2022-10-20 18:00","연속"]
[179,"경기북부","구리","청평P/P #1 M.Tr CB","청평양수 6136-1,2 DS 점검","6136-1,2 DS 점검","2022-10-05 09:00","2022-10-05 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[180,"경기북부","구리","청평P/P #1 BUS","청평양수SY 노후 154kV GIS 노후 대체공사","○ 170kV GIS(50kA, 2000A) 철거 x 5CCT ○ 170kV GIS(50kA, 2000A) 설치 x 5CCT ○ 154kV 모선보호배전반 x 1Set ○ 154kV 옥외분전반 x 1면 ○ 제어케이블 포·결선 철거 및 설치 x 1식 ○ 기타 부대공사 x 1식","2022-10-10 18:00","2022-10-12 18:00","2022-10-10 18:00","2022-10-12 18:00","연속"]
[181,"경기북부","구리","청평P/P #2 BUS","청평양수SY 노후 154kV GIS 노후 대체공사","○ 170kV GIS(50kA, 2000A) 철거 x 5CCT ○ 170kV GIS(50kA, 2000A) 설치 x 5CCT ○ 154kV 모선보호배전반 x 1Set ○ 154kV 옥외분전반 x 1면 ○ 제어케이블 포·결선 철거 및 설치 x 1식 ○ 기타 부대공사 x 1식","2022-10-13 18:00","2022-10-15 18:00","2022-10-13 18:00","2022-10-15 18:00","연속"]
[182,"경기북부","구리","청평P/P #2 BUS","청평양수SY 노후 154kV GIS 노후 대체공사","○ 170kV GIS(50kA, 2000A) 철거 x 5CCT ○ 170kV GIS(50kA, 2000A) 설치 x 5CCT ○ 154kV 모선보호배전반 x 1Set ○ 154kV 옥외분전반 x 1면 ○ 제어케이블 포·결선 철거 및 설치 x 1식 ○ 기타 부대공사 x 1식","2022-10-06 18:00","2022-10-07 18:00","2022-10-06 18:00","2022-10-07 18:00","연속"]
[183,"경기북부","구리","신포천포천#1 T/L","154kV 포천변전소 옥내화 토건공사","LA기초 설치 시 안전이격 확보","2022-10-01 09:00","2022-10-25 18:00","2022-10-01 09:00","2022-10-25 18:00","연속"]
[184,"경기북부","구리","포천운천#2 T/L","154kV 포천변전소 옥내화 토건공사","LA기초 설치 시 안전이격 확보","2022-10-01 09:00","2022-10-25 18:00","2022-10-01 09:00","2022-10-25 18:00","연속"]
[185,"경기북부","직할","녹양백석#2 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","154kV 녹양-백석#2T/L 송전선로 보호반 교체","2022-10-31 09:00","2022-11-03 18:00","2022-10-31 09:00","2022-11-03 18:00","연속"]
[186,"경기북부","직할","녹양백석#1 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","154kV 녹양-백석#1T/L 송전선로 보호반 교체","2022-10-24 09:00","2022-10-27 18:00","2022-10-24 09:00","2022-10-27 18:00","연속"]
[187,"경기북부","직할","신의정부S/S CB 6200","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-10-06 09:00","2022-10-06 18:00","2022-10-06 09:00","2022-10-06 18:00","연속"]
[188,"경기북부","직할","신의정부S/S CB 6100","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[189,"경기북부","직할","신의정부S/S CB 6300","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-10-05 09:00","2022-10-05 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[190,"경기북부","직할","신의정부송우#1 T/L","22-23 변전협력 총액공사","170kV GIS 보통점검","2022-10-13 09:00","2022-10-13 18:00","2022-10-13 09:00","2022-10-13 18:00","연속"]
[191,"경기북부","직할","양주지축#2 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 초기점검","2022-10-18 07:00","2022-10-18 17:00","2022-10-18 07:00","2022-10-18 17:00","연속"]
[192,"경기북부","직할","양주지축#1 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 초기점검","2022-10-17 07:00","2022-10-17 17:00","2022-10-17 07:00","2022-10-17 17:00","연속"]
[193,"경기북부","직할","옥정송우#2 T/L","철탑추락방지시설 설치공사","ㅇ 수평추락방지시설 설치 - 대상 : 154kV 옥정-송우T/L No.4호등 6개소","2022-10-28 07:00","2022-10-28 18:00","2022-10-28 07:00","2022-10-28 18:00","연속"]
[194,"경기북부","직할","옥정동두천#2 T/L","철탑추락방지시설 설치공사","ㅇ 수평추락방지시설 설치 - 대상 : 154kV 옥정-동두천T/L No.2호등 25개소","2022-10-31 07:00","2022-11-04 18:00","2022-10-31 07:00","2022-11-04 18:00","연속"]
[195,"경기북부","직할","옥정동두천#1 T/L","철탑추락방지시설 설치공사","ㅇ 수평추락방지시설 설치 - 대상 : 154kV 옥정-동두천T/L No.2호등 25개소","2022-10-24 07:00","2022-10-28 18:00","2022-10-24 07:00","2022-10-28 18:00","연속"]
[196,"경기","군포","서서울남군포#1 T/L","154kV 남군포S/S 신규수용공사(현대모비스)","154kV 현대모비스T/L GIS 설치","2022-10-25 14:00","2022-10-26 14:00","2022-10-25 14:00","2022-10-26 14:00","연속"]
[197,"경기","군포","서서울S/S #61 BUS","154kV 서서울-남군포#3T/L SW 증설공사","#61BUS 인터록시험","2022-10-19 09:00","2022-10-19 18:00","2022-10-19 09:00","2022-10-19 18:00","연속"]
[198,"경기","군포","서서울S/S #61 BUS","154kV 서서울-남군포#3T/L SW 증설공사","170kV GIS 1CCT 증설 #1DS, #61BUS 도킹","2022-10-04 09:00","2022-10-07 18:00","2022-10-04 09:00","2022-10-07 18:00","연속"]
[199,"경기","군포","서서울산본#1 T/L",null,"안전이격 및 무부하가압 선로","2022-10-04 09:00","2022-10-18 18:00","2022-10-04 09:00","2022-10-18 18:00","연속"]
[200,"경기","군포","서서울S/S #66 BUS","154kV 서서울-남군포#3T/L SW 증설공사","170kV GIS 1CCT 증설 #2DS, #66BUS 도킹","2022-10-11 09:00","2022-10-18 18:00","2022-10-11 09:00","2022-10-18 18:00","연속"]
[201,"경기","군포","성곡S/S CB 6100","성곡S/S #60-65 모선보호반 대체","성곡S/S #60-65 모선보호반 대체","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[202,"경기","군포","화성장덕 T/L","22-23 평택전력지사 협력회사 총액공사","철탑추락방지장치 설치","2022-10-04 09:00","2022-10-04 18:00","2022-10-04 09:00","2022-10-04 18:00","연속"]
[203,"경기","군포","수촌조암#2 T/L","조암S/S 수촌-조암#2TL GIS 보통점검","조암S/S 수촌-조암#2TL GIS 보통점검","2022-10-05 13:00","2022-10-05 18:00","2022-10-05 13:00","2022-10-05 18:00","연속"]
[204,"경기","군포","수촌조암#1 T/L","조암S/S 수촌-조암#1TL GIS 보통점검","조암S/S 수촌-조암#1TL GIS 보통점검","2022-10-05 09:00","2022-10-05 13:00","2022-10-05 09:00","2022-10-05 13:00","연속"]
[205,"경기","동부","분당S/S CB 6200","22년 동부전력 변전정비 총액공사","분당:6200(초기)","2022-10-19 09:30","2022-10-19 18:00","2022-10-19 09:30","2022-10-19 18:00","연속"]
[206,"경기","동부","산성수서#1 T/L","22년 동부전력 변전정비 총액공사","산성:산성-수서#1T/L CVT 사활불량","2022-10-21 09:30","2022-10-21 18:00","2022-10-21 09:30","2022-10-21 18:00","연속"]
[207,"경기","동부","분당오포#2 T/L","22년 동부전력 변전정비 총액공사","오포:분당-오포#2T/L(보통)","2022-10-07 09:30","2022-10-07 18:00","2022-10-07 09:30","2022-10-07 18:00","연속"]
[208,"경기","동부","분당오포#1 T/L","22년 동부전력 변전정비 총액공사","오포:분당-오포#1T/L(보통)","2022-10-06 09:30","2022-10-06 18:00","2022-10-06 09:30","2022-10-06 18:00","연속"]
[209,"경기","동부","성현분당#1 T/L","22년 동부전력 변전정비 총액공사","성현-분당#1T/L(보통)","2022-10-18 09:30","2022-10-18 14:00","2022-10-05 09:30","2022-10-05 14:00","연속"]
[210,"경기","성남","신봉이의#1 T/L","154kV 신성남-신봉 등 8개T/L 철탑 추락방지장치 설치공사","신성남-신봉, 신봉-이의, 화성-발안, 조암-구문천 수직/수평 추락방지장치 설치","2022-10-17 07:00","2022-10-18 18:00","2022-10-17 07:00","2022-10-18 18:00","연속"]
[211,"경기","성남","신성남신봉#1 T/L","154kV 신성남-신봉 등 8개T/L 철탑 추락방지장치 설치공사","신성남-신봉, 신봉-이의, 화성-발안, 조암-구문천 수직/수평 추락방지장치 설치 (휴일제외)","2022-10-04 07:00","2022-10-14 18:00","2022-10-04 07:00","2022-10-14 18:00","연속"]
[212,"경기","성남","신봉이의#2 T/L","154kV 신성남-신봉 등 8개T/L 철탑 추락방지장치 설치공사","신성남-신봉, 신봉-이의, 화성-발안, 조암-구문천 수직/수평 추락방지장치 설치","2022-10-13 07:00","2022-10-14 18:00","2022-10-13 07:00","2022-10-14 18:00","연속"]
[213,"경기","성남","신수원북동탄#1 T/L","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험 - 순간압력센서 설치","2022-10-07 09:00","2022-10-07 14:00","2022-10-07 09:00","2022-10-07 14:00","연속"]
[214,"경기","성남","신수원북동탄#2 T/L","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험 - 순간압력센서 설치","2022-10-07 14:00","2022-10-07 18:00","2022-10-07 14:00","2022-10-07 18:00","연속"]
[215,"경기","성남","신용인S/S CB 6100","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2022-10-18 09:00","2022-10-18 14:00","2022-10-18 09:00","2022-10-18 14:00","연속"]
[216,"경기","성남","신용인S/S CB 6200","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2022-10-18 14:00","2022-10-18 18:00","2022-10-18 14:00","2022-10-18 18:00","연속"]
[217,"경기","성남","모현용인#1 T/L","154kV 모현-용인T/L 지장철탑 이설공사","154kV 모현-용인T/L 16~18호 철탑 교체(본선로 구성) 공사시행 : 요청자 직접시행","2022-10-11 08:00","2022-10-20 18:00","2022-10-11 08:00","2022-10-20 18:00","연속"]
[218,"경기","성남","모현용인#2 T/L","154kV 모현-용인T/L 지장철탑 이설공사","154kV 모현-용인T/L 16~18호 철탑 교체(본선로 구성) 공사시행 : 요청자 직접시행","2022-10-21 08:00","2022-10-30 18:00","2022-10-21 08:00","2022-10-30 18:00","연속"]
[219,"경기","성남","신용인용인#1 T/L","170kV 효성제 GIS 스프링 조작기 교체공사","- 스프링 조작기 교체","2022-10-31 09:00","2022-10-31 18:00","2022-10-31 09:00","2022-10-31 18:00","연속"]
[220,"경기","성남","신용인용인#2 T/L","신용인용인T/L 등 철탑 추락방지장치 설치공사","신용인용인T/L 등 철탑 추락방지장치 설치공사","2022-10-06 09:00","2022-10-06 18:00","취소","취소","연속"]
[221,"경기","직할","조암구문천#2 T/L","22-23 평택전력지사 협력회사 총액공사","철탑추락방지장치 설치 아산화성 No.124 병가구간","2022-10-03 09:00","2022-10-04 18:00","2022-10-03 09:00","2022-10-04 18:00","연속"]
[222,"경기","직할","발안구문천#2 T/L","154kV 신성남-신봉 등 8개T/L 철탑 추락방지장치 설치공사","신성남-신봉, 신봉-이의, 화성-발안, 조암-구문천 수직/수평 추락방지장치 설치","2022-10-28 07:00","2022-10-28 18:00","2022-10-28 07:00","2022-10-28 18:00","연속"]
[223,"경기","직할","조암구문천#2 T/L","154kV 신성남-신봉 등 8개T/L 철탑 추락방지장치 설치공사","신성남-신봉, 신봉-이의, 화성-발안, 조암-구문천 수직/수평 추락방지장치 설치(휴일제외)","2022-10-28 07:00","2022-10-28 18:00","2022-10-28 07:00","2022-10-28 18:00","연속"]
[224,"경기","직할","발안구문천#1 T/L","154kV 신성남-신봉 등 8개T/L 철탑 추락방지장치 설치공사","신성남-신봉, 신봉-이의, 화성-발안, 조암-구문천 수직/수평 추락방지장치 설치","2022-10-27 07:00","2022-10-27 18:00","2022-10-27 07:00","2022-10-27 18:00","연속"]
[225,"경기","직할","조암구문천#1 T/L","154kV 신성남-신봉 등 8개T/L 철탑 추락방지장치 설치공사","신성남-신봉, 신봉-이의, 화성-발안, 조암-구문천 수직/수평 추락방지장치 설치(휴일제외)","2022-10-26 07:00","2022-10-27 18:00","2022-10-26 07:00","2022-10-27 18:00","연속"]
[226,"경기","직할","발안구문천#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","구문천, 발안S/S 발안-구문천#1T/L 보호반 대체","2022-10-12 09:00","2022-10-14 18:00","2022-10-12 09:00","2022-10-14 18:00","연속"]
[227,"경기","직할","서수원율전#2 T/L","21-22년 지중송전설비 위탁정비공사","피뢰기 및 C/T 점검","2022-10-17 13:00","2022-10-17 18:00","2022-10-17 13:00","2022-10-17 18:00","연속"]
[228,"경기","직할","서수원율전#1 T/L","21-22년 지중송전설비 위탁정비공사","피뢰기 및 C/T 점검","2022-10-17 09:00","2022-10-17 13:00","2022-10-17 09:00","2022-10-17 13:00","연속"]
[229,"경기","직할","서서울서수원#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 서서울-서수원T/L 철탑 정밀점검 19기(1호~19호)","2022-10-13 09:00","2022-10-14 18:00","2022-10-13 09:00","2022-10-14 18:00","매일"]
[230,"경기","직할","서서울서수원#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 서서울-서수원T/L 철탑 정밀점검 19기(1호~19호)","2022-10-11 09:00","2022-10-12 18:00","2022-10-11 09:00","2022-10-12 18:00","매일"]
[231,"경기","직할","화성마도 T/L","2022-23 경기본부 직할변전협력회사 총액공사","GIS 조작시험 및 LA 대체 등","2022-10-07 09:00","2022-10-07 14:00","2022-10-07 09:00","2022-10-07 14:00","연속"]
[232,"경기","직할","화성수촌#1 T/L","화성S/S 154kV 장기사용 GIS 교체공사","#60BUS 무부하가압","2022-10-01 09:00","2022-10-02 18:00","2022-10-01 09:00","2022-10-02 18:00","연속"]
[233,"경기","직할","화성장덕 T/L","2022-23 경기본부 직할변전협력회사 총액공사","GIS 조작시험 및 LA 대체 등","2022-10-07 14:00","2022-10-07 18:00","2022-10-07 14:00","2022-10-07 18:00","연속"]
[234,"경기","직할","화성S/S #65 BUS","화성S/S 154kV 장기사용 GIS 교체공사","#1M.Tr 2차, 화성-발안#1T/L, #60-#65BUS TIE GIS 2DS 설치","2022-10-15 09:00","2022-10-28 13:00","2022-10-15 09:00","2022-10-28 13:00","연속"]
[235,"경기","직할","화성S/S #60 BUS","화성S/S 154kV 장기사용 GIS 교체공사","화성S/S GIS 교체공사 준공시험 후 무부하가압","2022-10-28 13:00","2022-10-29 18:00","2022-10-28 13:00","2022-10-29 18:00","연속"]
[236,"경기","직할","화성S/S #66 BUS","화성S/S 154kV 장기사용 GIS 교체공사(4차)","화성S/S 154kV 장기사용 GIS 교체공사(4차)","2022-10-31 09:00","2022-11-02 18:00","2022-10-31 09:00","2022-11-02 18:00","연속"]
[237,"경기","직할","화성수촌#2 T/L","화성S/S 154kV 장기사용 GIS 교체공사(4차)","화성S/S 154kV 장기사용 GIS 교체공사(4차)","2022-10-31 09:00","2022-11-06 18:00","2022-10-31 09:00","2022-11-06 18:00","연속"]
[238,"경기","평택","만호청북#1 T/L","22-23 평택전력지사 가공송전 협력회사 총액공사","수평 철탑추락방지장치 설치(만호분기T/L) 성능저하 지지애자 설치(만호청북 No.18) 횡진방지 점퍼지지 설치(만호분기 No.12)","2022-10-07 09:00","2022-10-08 18:00","2022-10-07 09:00","2022-10-08 18:00","연속"]
[239,"경기","평택","소사벌안성 T/L","22년 평택전력지사 변전협력회사 총액공사","소사벌S/S 소사벌-안성T/L 보호반 대체","2022-10-05 09:00","2022-10-07 18:00","2022-10-05 09:00","2022-10-07 18:00","연속"]
[240,"경기","평택","송탄소사벌 T/L","22-23 평택전력지사 가공송전 협력회사 총액공사","1. 성능저하 지지애자 교체작업(추락방지시설 기설치개소) - 작업개소 송탄안성#1T/L No.4, 25 송탄소사벌(#2)T/L No.6,6.1,소사벌안성(#2)T/L No.54 2. 추락방지시설 설치(No.12,13)","2022-10-11 09:00","2022-10-12 18:00","2022-10-11 09:00","2022-10-12 18:00","연속"]
[241,"경기","평택","송탄안성 T/L","22-23 평택전력지사 가공송전 협력회사 총액공사","1. 성능저하 지지애자 교체작업(추락방지시설 기설치개소) - 작업개소 송탄안성#1T/L No.4, 25 송탄소사벌(#2)T/L No.6,6.1,소사벌안성(#2)T/L No.54 2. 추락방지시설 설치(No.12,13)","2022-10-14 09:00","2022-10-15 18:00","2022-10-14 09:00","2022-10-15 18:00","연속"]
[242,"경기","평택","평택오성CC#1 T/L","154kV 송탄오성(평택오성)T/L 항공도장 및 항공등 설치","요청자 시행 항공도장 및 항공등 설치 (안전이격확보)","2022-10-15 09:00","2022-10-17 18:00","2022-10-15 09:00","2022-10-17 18:00","연속"]
[243,"경기","평택","평택오성CC#2 T/L","154kV 평택-오성#2T/L OPGW 증설공사","차세대 광전송장치 도입에 따른 광코어 부족구간 용량 보강 (안전이격확보)","2022-10-18 09:00","2022-10-19 18:00","2022-10-18 09:00","2022-10-19 18:00","연속"]
[244,"경기","평택","송탄오성CC#1 T/L","154kV 평택-오성#2T/L OPGW 증설공사","차세대 광전송장치 도입에 따른 광코어 부족구간 용량 보강 (안전이격확보)","2022-10-18 09:00","2022-10-19 18:00","2022-10-18 09:00","2022-10-19 18:00","연속"]
[245,"경기","평택","송탄오성CC#2 T/L","154kV 송탄오성(평택오성)T/L 항공도장 및 항공등 설치","요청자 시행 항공도장 및 항공등 설치 (안전이격확보)","2022-10-15 09:00","2022-10-17 18:00","2022-10-15 09:00","2022-10-17 18:00","연속"]
[246,"경기","평택","원정평택TP#2 T/L","22년 평택전력지사 변전협력회사 총액공사","원정S/S 원정-평택T/P#2T/L GIS 조작시험","2022-10-14 10:00","2022-10-14 18:00","2022-10-14 10:00","2022-10-14 18:00","연속"]
[247,"경기","평택","원정평택TP#1 T/L","22년 평택전력지사 변전협력회사 총액공사","원정S/S 원정-평택T/P#1T/L GIS 조작시험","2022-10-24 10:00","2022-10-24 18:00","2022-10-24 10:00","2022-10-24 18:00","연속"]
[248,"경기","평택","청북평택#2 T/L","21-22년 지중송전 위탁정비공사(평택전력)","□ 피뢰기 열화진단 ○ 절연열화 측정 및 부싱청소","2022-10-10 14:00","2022-10-10 18:00","2022-10-10 14:00","2022-10-10 18:00","연속"]
[249,"경기","평택","청북평택#2 T/L","154kV 율북S/S 건설공사","154kV 율북S/S 무부하가압(무부하가압 선로)","2022-10-18 09:00","2022-10-19 18:00","2022-10-18 09:00","2022-10-19 18:00","연속"]
[250,"경기","평택","청북평택#1 T/L","21-22년 지중송전 위탁정비공사(평택전력)","□ 피뢰기 열화진단 ○ 절연열화 측정 및 부싱청소","2022-10-10 09:00","2022-10-10 14:00","2022-10-10 09:00","2022-10-10 14:00","연속"]
[251,"경기","평택","평택추팔#2 T/L","22-23 평택전력지사 가공송전 협력회사 총액공사","추락방지시설 설치(No.13)","2022-10-18 09:00","2022-10-18 18:00","2022-10-18 09:00","2022-10-18 18:00","연속"]
[252,"경기","평택","평택추팔#1 T/L","22-23 평택전력지사 가공송전 협력회사 총액공사","추락방지시설 설치(No.13)","2022-10-17 09:00","2022-10-17 18:00","2022-10-17 09:00","2022-10-17 18:00","연속"]
[253,"경기","평택","포승평택TP#2 T/L","22-23 평택전력지사 가공송전 협력회사 총액공사","수평 철탑추락방지장치 설치 포승청북 병가구간 및 2회선 구간 성능저하 지지애자 설치(No.32,39)","2022-10-07 09:00","2022-10-13 18:00","2022-10-07 09:00","2022-10-13 18:00","연속"]
[254,"경기","평택","포승평택TP#1 T/L","22-23 평택전력지사 가공송전 협력회사 총액공사","수평 철탑추락방지장치 설치 포승청북 병가구간 및 2회선 구간","2022-10-04 09:00","2022-10-06 18:00","취소","취소","연속"]
[255,"경기","평택","포승청북 T/L","22-23 평택전력지사 가공송전 협력회사 총액공사","수평 철탑추락방지장치 설치 포승청북T/L No.1,3~8, 10~16, 18","2022-10-04 09:00","2022-10-06 18:00","취소","취소","연속"]
[256,"경기","평택","포승만호 T/L","22-23 평택전력지사 가공송전 협력회사 총액공사","수평 철탑추락방지장치 설치 만호분기T/L No.10,11,12 포승만호T/L No.1,3~8 횡진방지 점퍼지지 설치 만호분기 No.11 포승만호 No.2(포승평택TP#2 No.39)","2022-10-11 09:00","2022-10-13 18:00","2022-10-11 09:00","2022-10-13 18:00","연속"]
[257,"강원","강릉","강릉횡계#1 T/L","`21~22년 강원본부 지중송전설비 위탁정비공사","작업내용 : 154kV 강릉C/H 피뢰기 점검 작업기간 - 강릉-횡계#1,동해-강릉T/L : `22.10.11 08:00 ~ 13:00 - 강릉-횡계#2,영동T/P-강릉T/L : `22.10.11 13:00 ~ 18:00","2022-10-11 08:00","2022-10-11 13:00","2022-10-11 08:00","2022-10-11 13:00","연속"]
[258,"강원","강릉","강릉횡계#2 T/L","`21~22년 강원본부 지중송전설비 위탁정비공사","작업내용 : 154kV 강릉C/H 피뢰기 점검 작업기간 - 강릉-횡계#1,동해-강릉T/L : `22.10.11 08:00 ~ 13:00 - 강릉-횡계#2,영동T/P-강릉T/L : `22.10.11 13:00 ~ 18:00","2022-10-04 13:00","2022-10-04 18:00","2022-10-04 08:00","2022-10-04 13:00","연속"]
[259,"강원","강릉","강릉영동TP T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV 탈황설비 GIS 대체, 170kV GIS 디지털변환, GIS 기초 보강(터파기, 거푸집 설치)","2022-10-04 08:00","2022-10-06 17:00","취소","취소","매일"]
[260,"강원","강릉","영동T/P #1 BUS","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV GIS 7CCT 대체, 170kV GIS 디지털변환, #1BUS 설치, 본체설치 (BUS TIE, BUS PT)","2022-10-19 08:00","2022-11-14 09:00","취소","취소","연속"]
[261,"강원","강릉","북평영동TP#2 T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV GIS 7CCT 대체, 170kV GIS 디지털변환, #1BUS 설치, 본체설치 (북평-영동TP #1,2T/L)","2022-10-31 08:00","2022-11-04 18:00","취소","취소","매일"]
[262,"강원","강릉","동해영동TP T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV 탈황설비 GIS 대체, 170kV GIS 디지털변환, GIS 기초 보강(터파기, 거푸집 설치)","2022-10-04 08:00","2022-10-07 18:00","취소","취소","매일"]
[263,"강원","강릉","북평영동TP#2 T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV GIS 7CCT 대체, 170kV GIS 디지털변환, #1BUS 설치, 본체설치 (BUS TIE, BUS PT)","2022-10-18 08:00","2022-10-21 18:00","취소","취소","매일"]
[264,"강원","강릉","주진평창#1 T/L","2022~2023년 강릉전력지사 가공송전협력회사 총액공사","○ 압축인류클램프 부풀음 개소 보수작업(주진S/S, 평창S/S)","2022-10-17 08:00","2022-10-17 18:00","2022-10-17 08:00","2022-10-17 18:00","연속"]
[265,"강원","동해","이원도계 T/L","154kV 도계변전소 외장재 교체 공사","산불 화재 확산 방지를 위한 노후 드라이비트 철거 및 메탈패널 교체","2022-10-31 10:00","2022-11-04 18:00","2022-10-31 10:00","2022-11-04 18:00","연속"]
[266,"강원","동해","동해T/P #1 M.Tr CB","22년 동해전력지사 변전정비팀 총액공사","1. GIS 초기점검","2022-10-04 09:00","2022-10-04 18:00","2022-10-04 09:00","2022-10-04 18:00","연속"]
[267,"강원","동해","삼척동해TP T/L","22년 동해전력지사 변전정비팀 총액공사","1. GIS PT 대체","2022-10-24 09:00","2022-10-27 18:00","2022-10-24 09:00","2022-10-27 18:00","연속"]
[268,"강원","동해","이원동해TP T/L","22년 동해전력지사 변전정비팀 총액공사","1. GIS PT 대체 2. GIS 보통점검(이원S/S, 동해TP) 3. LA 보통점검 4. 서포트 보강","2022-10-18 09:00","2022-10-21 18:00","2022-10-18 09:00","2022-10-21 18:00","연속"]
[269,"강원","동해","동해이원#1 T/L","2022년 동해전력지사 가공송전선로 순시점검 위탁공사","송전선로 정밀점검(No.1~28) 28기","2022-10-11 08:00","2022-10-14 18:00","2022-10-11 08:00","2022-10-14 18:00","매일"]
[270,"강원","동해","동해강릉 T/L","345kV 동해-안인개폐소등 5개T/L 철탑추락방지장치 설치공사","철탑추락방지장치(수평) 설치(No.54~No.94) 42기","2022-10-11 08:00","2022-10-15 18:00","2022-10-11 08:00","2022-10-15 18:00","매일"]
[271,"강원","동해","동해이원#2 T/L","2022년 동해전력지사 가공송전선로 순시점검 위탁공사","송전선로 정밀점검 및 피뢰기 촉 교체(No.1~28) 28기","2022-10-17 08:00","2022-10-21 18:00","2022-10-17 08:00","2022-10-21 18:00","매일"]
[272,"강원","동해","북평영동TP#2 T/L","345kV 동해-안인개폐소등 5개T/L 철탑추락방지장치 설치공사","철탑추락방지장치(수평) 설치(No.21~No.46-1) 24기","2022-10-07 08:00","2022-10-09 18:00","취소","취소","매일"]
[273,"강원","동해","북평영동TP#1 T/L","345kV 동해-안인개폐소등 5개T/L 철탑추락방지장치 설치공사","철탑추락방지장치(수평) 설치(No.21~No.46-1) 24기","2022-10-10 08:00","2022-10-12 18:00","취소","취소","매일"]
[274,"강원","동해","울진삼척GP#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 울진-삼척GP#1T/L 정밀점검","2022-10-04 09:00","2022-10-06 18:00","2022-10-04 09:00","2022-10-06 18:00","매일"]
[275,"강원","동해","울진삼척GP#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 울진-삼척GP#2T/L 정밀점검","2022-10-07 09:00","2022-10-12 18:00","2022-10-07 09:00","2022-10-12 18:00","매일"]
[276,"강원","원주","남원주원주#1 T/L","2022~2023년 송전협력회사 총액공사","추락방지장치 설치(전구간)","2022-10-04 08:00","2022-10-07 18:00","취소","취소","매일"]
[277,"강원","원주","신제천남원주#2 T/L","154kV 신제천-남원주T/L 불량애자 교체","성능저하 불량애자 교체 : 31기 257련","2022-10-24 08:00","2022-10-30 18:00","취소","취소","매일"]
[278,"강원","원주","신제천남원주#1 T/L","154kV 신제천-남원주T/L 불량애자 교체","성능저하 불량애자 교체 : 31기 257련","2022-10-17 08:00","2022-10-23 18:00","취소","취소","매일"]
[279,"강원","원주","남원주원주#2 T/L","2022~2023년 송전협력회사 총액공사","추락방지장치 설치(전구간)","2022-10-11 08:00","2022-10-14 18:00","취소","취소","매일"]
[280,"강원","원주","상남인제#2 T/L","'22년 상남S/S 모선구분차단기 설치공사","(안전이격 확보 휴전) 154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-10-17 09:00","2022-10-19 18:00","2022-10-17 09:00","2022-10-19 18:00","매일"]
[281,"강원","원주","홍천상남#1 T/L","'22년 상남S/S 모선구분차단기 설치공사","(안전이격 확보 휴전) 154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-10-05 09:00","2022-10-07 18:00","2022-10-05 09:00","2022-10-07 18:00","매일"]
[282,"강원","원주","상남S/S #2 BUS","'22년 상남S/S 모선구분차단기 설치공사","154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-10-04 09:00","2022-10-28 18:00","2022-10-04 09:00","2022-10-28 18:00","연속"]
[283,"강원","원주","홍천상남#1 T/L","'22년 상남S/S 모선구분차단기 설치공사","(무부하가압 휴전) 154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-10-27 09:00","2022-10-28 18:00","2022-10-27 09:00","2022-10-28 18:00","연속"]
[284,"강원","원주","홍천상남#2 T/L","'22년 상남S/S 모선구분차단기 설치공사","(안전이격 확보 휴전) 154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-10-11 09:00","2022-10-13 18:00","2022-10-11 09:00","2022-10-13 18:00","매일"]
[285,"강원","원주","상남인제#2 T/L","'22년 상남S/S 모선구분차단기 설치공사","(안전이격 확보 휴전) 154kV BUS TIE × 1CCT 154kV BUS SEC × 2CCT 154kV PT&ES × 1Bay 기타 부대공사 × 1식","2022-10-11 09:00","2022-10-13 18:00","2022-10-11 09:00","2022-10-13 18:00","매일"]
[286,"강원","원주","서원주문막#2 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 보통점검","2022-10-06 09:00","2022-10-06 18:00","취소","취소","연속"]
[287,"강원","원주","원주서원주#1 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 보통점검","2022-10-12 09:00","2022-10-12 18:00","취소","취소","연속"]
[288,"강원","원주","서원주문막#1 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 보통점검","2022-10-05 09:00","2022-10-05 18:00","취소","취소","연속"]
[289,"강원","원주","원주서원주#2 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 보통점검","2022-10-13 09:00","2022-10-13 18:00","취소","취소","연속"]
[290,"강원","원주","홍천남춘천 T/L","2022년 원주전력지사 변전협력회사 총액공사","피뢰기 교체","2022-10-31 09:00","2022-10-31 18:00","2022-10-17 09:00","2022-10-17 18:00","연속"]
[291,"강원","직할","양구화천HP#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 양구화천HP #1 T/L No. 70~80 초기점검","2022-10-03 08:00","2022-10-04 18:00","2022-10-03 08:00","2022-10-04 18:00","매일"]
[292,"강원","직할","청평HP의암HP T/L","22~23년 강원본부 직할 변전협력회사 총액공사","DS 보통점검","2022-10-11 09:00","2022-10-11 18:00","2022-10-11 09:00","2022-10-11 18:00","연속"]
[293,"강원","직할","의암H/P #1 M.Tr CB","22~23년 강원본부 직할 변전협력회사 총액공사","DS 보통점검","2022-10-11 09:00","2022-10-11 18:00","2022-10-11 09:00","2022-10-11 18:00","연속"]
[294,"강원","직할","간성인제#2 T/L","22~23년 강원직할 가공송전 협력회사 총액공사","154kV 간성-인제#2T/L 추락방지장치 설치, 압축인류크램프 정비","2022-10-24 07:00","2022-11-05 18:00","2022-10-24 07:00","2022-11-05 18:00","연속"]
[295,"강원","직할","춘천소양강HP T/L","22~23년 강원본부 직할 변전협력회사 총액공사","GIS 보통점검","2022-10-25 09:00","2022-10-25 18:00","2022-10-25 09:00","2022-10-25 18:00","연속"]
[296,"강원","직할","춘천북춘천#2 T/L","22~23년 강원본부 직할 변전협력회사 총액공사","GIS 보통점검","2022-10-05 09:00","2022-10-05 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[297,"강원","직할","춘천북춘천#1 T/L","22~23년 강원본부 직할 변전협력회사 총액공사","GIS 보통점검","2022-10-04 09:00","2022-10-04 18:00","취소","취소","연속"]
[298,"강원","직할","춘천S/S CB 6100","22~23년 강원본부 직할 변전협력회사 총액공사","GIS 보통점검","2022-10-26 10:00","2022-10-26 18:00","2022-10-26 10:00","2022-10-26 18:00","연속"]
[299,"강원","직할","서홍천춘천열병합 T/L","22~23년 강원본부 직할 변전협력회사 총액공사","GIS,PT 보통점검","2022-10-24 10:00","2022-10-24 18:00","2022-10-04 10:00","2022-10-04 18:00","연속"]
[300,"강원","직할","춘천열병합 CB 6100","22~23년 강원본부 직할 변전협력회사 총액공사","GIS 보통점검","2022-10-12 10:00","2022-10-12 18:00","2022-10-12 10:00","2022-10-12 18:00","연속"]
[301,"강원","직할","남춘천춘천열병합#2 T/L","22~23년 강원본부 직할 변전협력회사 총액공사","GIS,PT 보통점검","2022-10-13 10:00","2022-10-13 18:00","2022-10-13 10:00","2022-10-13 18:00","연속"]
[302,"강원","직할","북춘천화천HP T/L","22~23년 강원본부 직할 변전협력회사 총액공사","DS 보통점검","2022-10-15 10:00","2022-10-15 18:00","2022-10-15 10:00","2022-10-15 18:00","연속"]
[303,"강원","직할","화천H/P #1 M.Tr CB","22~23년 강원본부 직할 변전협력회사 총액공사","GCB,DS 보통점검","2022-10-18 10:00","2022-10-18 18:00","2022-10-18 10:00","2022-10-18 18:00","연속"]
[304,"강원","직할","가평화천HP T/L","22~23년 강원본부 직할 변전협력회사 총액공사","GCB 보통점검","2022-10-22 10:00","2022-10-22 18:00","2022-10-22 10:00","2022-10-22 18:00","연속"]
[305,"강원","태백","태백삼척GP#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 태백-삼척GP#2T/L 정밀점검","2022-10-23 09:00","2022-11-06 13:00","2022-10-23 09:00","2022-11-06 13:00","연속"]
[306,"강원","태백","태백영월 T/L","154kV 태백T/L 선종교체공사","전력선 교체 - 교체구간 : No.77~태백S/T, 12.472C-km(ACMR/TW 240SQ* S )","2022-10-06 09:00","2022-11-16 18:00","2022-10-06 09:00","2022-11-16 18:00","연속"]
[307,"강원","태백","태백삼척GP#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 태백-삼척GP#1T/L 정밀점검","2022-10-13 09:00","2022-10-21 18:00","2022-10-13 09:00","2022-10-21 18:00","매일"]
[308,"강원","태백","태백삼척GP#2 T/L","154kV 태초에너지 변전소 신설공사","154kV 태백-삼척GP#2T/L 임시선로 구성","2022-10-09 09:00","2022-10-09 13:00","2022-10-09 09:00","2022-10-09 13:00","연속"]
[309,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 삼죽-광혜원 T/L ↔ #1 Sh.C 간 인출변경 (공사기간 중 삼죽S/S 임시 전력공급용)","2022-10-09 09:00","2022-10-10 18:00","취소","취소","연속"]
[310,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","#66 BUS 무부하가압 (즉시가압 가능)","2022-10-15 09:00","2022-10-15 18:00","취소","취소","연속"]
[311,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","#61 BUS 무부하가압 (즉시가압 가능)","2022-10-18 09:00","2022-10-18 18:00","취소","취소","연속"]
[312,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 삼죽-광혜원 T/L ↔ #1 Sh.C 간 인출변경 원상복구, 154kV 장기사용 GIS 대체작업","2022-10-22 09:00","2022-10-23 18:00","취소","취소","연속"]
[313,"충북","직할","진천광혜원#1 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 장기사용 GIS 대체작업","2022-10-04 09:00","2022-10-08 18:00","취소","취소","연속"]
[314,"충북","직할","진천덕산#2 T/L","170kV LS제 GIS 가스주입구 개선공사","가스 오회수 방지를 위한 가스배관 개선","2022-10-01 10:00","2022-10-01 18:00","취소","취소","연속"]
[315,"충북","직할","진천덕산#1 T/L","2022년 가공 송전선로 추락방지장치 설치공사","진천-덕산#1T/L No.1~27 추락방지장치 설치 및 정밀점검 (주말 공휴일 제외)","2022-10-04 07:30","2022-10-14 18:00","2022-10-04 07:30","2022-10-14 18:00","매일"]
[316,"충북","직할","진천덕산#2 T/L","2022년 가공 송전선로 추락방지장치 설치공사","진천-덕산#2T/L No.1~27 추락방지장치 설치 및 정밀점검(주말 공휴일 제외)","2022-10-17 07:30","2022-10-21 18:00","2022-10-17 07:30","2022-10-21 18:00","매일"]
[317,"충북","청주","남청주죽림#1 T/L","22-23년 청주전력지사 변전정비회사 총액공사","남청주S/S 154kV 남청주-죽림#1T/L CLR,LA점검","2022-10-14 10:00","2022-10-14 16:00","2022-10-14 10:00","2022-10-14 16:00","연속"]
[318,"충북","청주","남청주S/S SEC CB 65660","남청주S/S 154kV 장기사용 GIS 대체공사","#65-66 BUS SEC GIS 대체","2022-10-15 09:00","2022-10-24 18:00","취소","취소","연속"]
[319,"충북","청주","오송북청주#2 T/L","345kV 신청주분기T/L 건설공사","345kV 신청주분기T/L 임시선로 가선작업 안전확보 1. 임시선로 구간 : (기설)345kV 신중부-남청주T/L No.37 ~ 가)No.38-1 ~ 가)No.40-1 ~ No.41 2. 선로길이 : 2C-1.21km 3. 지 지 물 : 2기(가철탑)","2022-10-04 07:00","2022-10-07 18:00","2022-10-04 07:00","2022-10-07 18:00","매일"]
[320,"충북","청주","오송북청주#1 T/L","345kV 신청주분기T/L 건설공사","345kV 신청주분기T/L 임시선로 가선작업 안전확보 1. 임시선로 구간 : (기설)345kV 신중부-남청주T/L No.37 ~ 가)No.38-1 ~ 가)No.40-1 ~ No.41 2. 선로길이 : 2C-1.21km 3. 지 지 물 : 2기(가철탑)","2022-10-06 09:00","2022-10-06 13:00","2022-10-06 09:00","2022-10-06 13:00","연속"]
[321,"충북","청주","북청주봉명#1 T/L","22-23년 청주전력지사 변전정비회사 총액공사","북청주,봉명S/S 154kV 북청주-봉명#1T/L 보호반 대체","2022-10-17 09:00","2022-10-18 18:00","2022-10-17 09:00","2022-10-18 18:00","연속"]
[322,"충북","청주","북청주봉명#2 T/L","22-23년 청주전력지사 변전정비회사 총액공사","북청주,봉명S/S 154kV 북청주-봉명#2T/L 보호반 대체","2022-10-19 09:00","2022-10-20 18:00","2022-10-19 09:00","2022-10-20 18:00","연속"]
[323,"충북","청주","사직북청주#2 T/L","22-23년 청주전력지사 변전정비회사 총액공사","사직S/S 154kV 사직-북청주#1T/L GIS 보통점검","2022-10-20 10:00","2022-10-20 18:00","2022-10-20 10:00","2022-10-20 18:00","연속"]
[324,"충북","청주","남청주오송#2 T/L","송전 추락방지시설 설치공사","1. 공 사 명 : 154kV 남청주-청주 등 4개T/L 추락방지시설 설치공사 2. 공사장소 : 154kV 남청주-오송T/L No.38~56 3. 공사내역 : 수평 추락방지시설 설치","2022-10-08 07:00","2022-10-09 18:00","2022-10-08 07:00","2022-10-09 18:00","매일"]
[325,"충북","청주","신진천오창#2 T/L","2022년 청주전력지사 170kV GIS 정밀점검공사","오창S/S 154kV 신진천오창#2T/L GIS 정밀점검","2022-10-01 09:00","2022-10-02 18:00","2022-10-01 09:00","2022-10-02 18:00","연속"]
[326,"충북","청주","신옥천옥천#1 T/L","옥천S/S 고속철도#1T/L 1DS부 교체작업","옥천S/S 고속철도#1T/L 1,2DS부 제작사 입회 교체작업 후 시험가압","2022-10-18 10:00","2022-10-19 12:00","2022-10-18 10:00","2022-10-19 12:00","매일"]
[327,"충북","청주","신옥천옥천#1 T/L","옥천S/S 고속철도#2T/L 1DS부 교체작업","옥천S/S 고속철도#2T/L 1DS부 제작사 입회 교체작업 후 시험가압","2022-10-21 10:00","2022-10-21 12:00","2022-10-21 10:00","2022-10-21 12:00","연속"]
[328,"충북","충주","감곡S/S CB 6100","22-23년 충주전력지사 변전정비총액공사","6100 BUS TIE GIS 보통점검","2022-10-04 14:00","2022-10-04 18:00","2022-10-15 10:00","2022-10-15 18:00","연속"]
[329,"충북","충주","감곡가남#2 T/L","2022년 가공 송전선로 추락방지장치 설치공사","감곡가남#2T/L No.1~3 추락방지장치 설치공사 및 No.1,2 정밀점검","2022-10-15 07:30","2022-10-16 18:00","2022-10-15 07:30","2022-10-15 18:00","매일"]
[330,"충북","충주","문경단양 T/L","단양S/S 154kV 장기사용 GIS 대체공사","○ 문경-단양 T/L 인출변경 (구 GIS → 신 GIS) ○ 문경-단양 T/L 감시·제어케이블 이설 (구 GIS → 신 GIS, 현장정보처리반 → SA현장정보처리반)","2022-10-09 08:00","2022-10-10 18:00","취소","취소","연속"]
[331,"충북","충주","점촌단양 T/L","단양S/S 154kV 장기사용 GIS 대체공사","○ 점촌-단양 T/L 인출변경 (구 GIS → 신 GIS) ○ 점촌-단양 T/L 감시·제어케이블 이설 (구 GIS → 신 GIS, 현장정보처리반 → SA현장정보처리반)","2022-10-02 08:00","2022-10-03 18:00","취소","취소","연속"]
[332,"충북","충주","북충주충주 T/L","154kV 왕암-충주 등 5개 T/L 불량 압축인류클램프 교체공사","불량 압축인류클램프 교체","2022-10-11 07:00","2022-10-13 18:00","2022-10-11 07:00","2022-10-13 18:00","매일"]
[333,"충북","충주","북충주S/S CB 6100","22-23년 충주전력지사 변전정비총액공사","6100 BUS TIE GIS 보통점검","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[334,"충북","충주","신충주북충주#1 T/L","2022년 충주전력지사 170kV GIS 정밀점검공사","신충주북충주#1 T/L GIS 정밀점검","2022-10-04 09:00","2022-10-05 18:00","2022-10-04 09:00","2022-10-05 18:00","연속"]
[335,"충북","충주","신제천왕암#1 T/L","154kV 신제천-제천T/L 용량증대 전선교체공사","1. 공사명 : 154kV 신제천-제천T/L 용량증대 전선교체공사 2. 공사구간 : 신제천S/S ~ 제천S/S 3. 전력선 교체 : 신제천S/S 내 인출 철구 ~ 제천S/S 인출철구(38경간)","2022-10-18 09:00","2022-10-28 18:00","2022-10-18 09:00","2022-10-28 18:00","연속"]
[336,"충북","충주","신제천S/S CB 6300","22-23년 충주전력지사 변전정비총액공사","6300 BUS TIE GIS 보통점검","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[337,"충북","충주","신제천S/S CB 6200","22-23년 충주전력지사 변전정비총액공사","6200 BUS TIE GIS 보통점검","2022-10-06 14:00","2022-10-06 18:00","2022-10-06 14:00","2022-10-06 18:00","연속"]
[338,"충북","충주","신제천S/S CB 6100","22-23년 충주전력지사 변전정비총액공사","6100 BUS TIE GIS 보통점검","2022-10-06 09:00","2022-10-06 14:00","2022-10-06 09:00","2022-10-06 14:00","연속"]
[339,"충북","충주","신제천영월CC#1 T/L","2022년 충주전력지사 170kV GIS 정밀점검공사","신제천영월CC#1 T/L GIS 정밀점검","2022-10-19 09:00","2022-10-20 18:00","취소","취소","연속"]
[340,"충북","충주","신충주북충주#2 T/L","154kV 왕암-충주 등 5개 T/L 불량 압축인류클램프 교체공사","불량 압축인류클램프 교체","2022-10-20 07:00","2022-10-21 18:00","2022-10-20 07:00","2022-10-21 18:00","매일"]
[341,"충북","충주","신충주감곡#1 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주감곡#1T/L 정밀점검, [10.8(토) ~ 10.10(월) 제외]","2022-10-06 07:30","2022-10-18 18:00","2022-10-06 07:30","2022-10-18 18:00","매일"]
[342,"충북","충주","신충주S/S CB 6100","22-23년 충주전력지사 변전정비총액공사","6100 BUS TIE GIS 보통점검","2022-10-17 09:00","2022-10-17 14:00","2022-10-17 09:00","2022-10-17 14:00","연속"]
[343,"충북","충주","신충주음성#2 T/L","2022년 직할 가공송전선로 순시점검 위탁공사","신충주음성#2T/L 정밀점검, 주말 및 공휴일 제외","2022-10-04 07:30","2022-10-12 18:00","2022-10-04 07:30","2022-10-12 18:00","매일"]
[344,"충북","충주","왕암여주#1 T/L","2022년 가공 송전선로 추락방지장치 설치공사","신충주감곡#1T/L 병가선로(신충주감곡 No.77~85)에 따른 휴전","2022-10-15 07:30","2022-10-16 18:00","2022-10-15 07:30","2022-10-16 18:00","매일"]
[345,"충북","충주","음성금왕#2 T/L","충북본부 직할 송전정비 협력회사 총액공사","추락방지지설 설치 31기","2022-10-24 07:30","2022-10-28 18:00","2022-10-24 07:30","2022-10-28 18:00","매일"]
[346,"충북","충주","제천영월#1 T/L","154kV 제천-영월T/L 용량증대 케이블 교체공사","154kV 제천-영월 #1T/L 지중케이블 철거, 포설, 접속","2022-10-25 09:00","2022-11-17 18:00","2022-10-25 09:00","2022-11-17 18:00","연속"]
[347,"충북","충주","신제천제천#1 T/L","154kV 신제천-제천T/L 용량증대 케이블 교체공사","154kV 신제천-제천 #1T/L 지중케이블 철거, 포설, 접속","2022-10-18 09:00","2022-11-10 18:00","2022-10-18 09:00","2022-11-10 18:00","연속"]
[348,"충북","충주","충주충주HP#1 T/L","154kV 왕암-충주등 5개T/L 불량압축인류클램프 교체공사","154kV 충주-충주HP T/L 불량 압축인류클램프 교체공사","2022-10-31 09:00","2022-11-04 18:00","2022-10-31 09:00","2022-11-04 18:00","연속"]
[349,"충북","충주","충주S/S CB 6200","22-23년 충주전력지사 변전정비총액공사","61-#66 BUS TIE GIS 보통점검","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[350,"충북","충주","충주S/S SEC CB 65660","22-23년 충주전력지사 변전정비총액공사","65-#66 BUS SEC GIS 보통점검","2022-10-19 09:00","2022-10-19 18:00","2022-10-19 09:00","2022-10-19 18:00","연속"]
[351,"충북","충주","신제천S/S CB 6200","22년 충주전력지사 170kV GIS정밀점검공사","#3Sh.C GIS 정밀점검 무부하가압","2022-10-30 09:00","2022-10-31 18:00","취소","취소","연속"]
[352,"충북","충주","신제천S/S #66 BUS","22년 충주전력지사 170kV GIS정밀점검공사","#3Sh.C GIS 정밀점검 무부하가압","2022-10-30 09:00","2022-10-31 18:00","취소","취소","연속"]
[353,"충북","충주","신제천S/S #67 BUS","22년 충주전력지사 170kV GIS정밀점검공사","#6Sh.C GIS 정밀점검 무부하가압","2022-10-28 09:00","2022-10-29 18:00","취소","취소","연속"]
[354,"충북","충주","신제천S/S CB 6300","22년 충주전력지사 170kV GIS정밀점검공사","#6Sh.C GIS 정밀점검 무부하가압","2022-10-28 09:00","2022-10-29 18:00","취소","취소","연속"]
[355,"대전세종충남","대전","금산무주#2 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 금산-무주T/L 추락방지시설 설치공사","2022-10-20 08:00","2022-11-11 18:00","취소","취소","매일"]
[356,"대전세종충남","대전","남대전신흥#1 T/L","남대전S/S 154kV 노후 GIS 대체공사","○ 170kV GIS 11CCT 교체 ○ 170kV GIS GIB 1식 교체 ○ 170kV GIS BUS PT 1조 교체","2022-10-13 14:00","2022-10-31 18:00","2022-10-13 14:00","2022-10-31 18:00","연속"]
[357,"대전세종충남","대전","신옥천남대전#4 T/L","남대전S/S 154kV 노후 GIS 대체공사","○ 170kV GIS 11CCT 교체 ○ 170kV GIS GIB 1식 교체 ○ 170kV GIS BUS PT 1조 교체","2022-10-13 14:00","2022-10-31 18:00","2022-10-13 14:00","2022-10-31 18:00","연속"]
[358,"대전세종충남","대전","신옥천남대전#1 T/L","남대전S/S 154kV 노후 GIS 대체공사","○ 170kV GIS 11CCT 교체 ○ 170kV GIS GIB 1식 교체 ○ 170kV GIS BUS PT 1조 교체","2022-10-04 07:00","2022-10-13 14:00","2022-10-04 07:00","2022-10-13 14:00","연속"]
[359,"대전세종충남","대전","논산은진#1 T/L","논산S/S 170kV 공압식 차단기 부동작 예방조작 시험","논산S/S 170kV 공압식 차단기 부동작 예방조작 시험","2022-10-05 09:00","2022-10-05 13:00","2022-10-05 09:00","2022-10-05 13:00","연속"]
[360,"대전세종충남","대전","부여논산#2 T/L","논산S/S 154kV 부여-논산#2T/L 피뢰기 교체 및 병행작업","논산S/S 154kV 부여-논산#2T/L 피뢰기 교체 및 병행작업","2022-10-13 09:00","2022-10-13 18:00","2022-10-13 09:00","2022-10-13 18:00","연속"]
[361,"대전세종충남","대전","부여논산#1 T/L","논산S/S 154kV 부여-논산#1T/L 피뢰기 교체 및 병행작업","논산S/S 154kV 부여-논산#1T/L 피뢰기 교체 및 병행작업","2022-10-12 09:00","2022-10-12 18:00","2022-10-12 09:00","2022-10-12 18:00","연속"]
[362,"대전세종충남","대전","논산은진#2 T/L","논산S/S 170kV 공압식 차단기 부동작 예방조작 시험","논산S/S 170kV 공압식 차단기 부동작 예방조작 시험","2022-10-05 14:00","2022-10-05 18:00","2022-10-05 14:00","2022-10-05 18:00","연속"]
[363,"대전세종충남","대전","신계룡두마#2 T/L","(9월 취소시) 345kV 신옥천-청양등17개T/L 추락방지장치 설치공사","[송전] 345kV 신옥천-신계룡T/L 추락방지장치 설치공사 안전거리 확보차","2022-10-21 08:00","2022-10-21 18:00","취소","취소","연속"]
[364,"대전세종충남","대전","신계룡두마#1 T/L","(9월 취소시) 345kV 신옥천-청양등17개T/L 추락방지장치 설치공사","[송전] 345kV 신옥천-신계룡T/L 추락방지장치 설치공사 안전거리 확보차","2022-10-13 08:00","2022-10-13 18:00","취소","취소","연속"]
[365,"대전세종충남","대전","추부금산#2 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 추부-금산T/L 추락방지시설 설치공사","2022-10-06 08:00","2022-10-21 18:00","취소","취소","매일"]
[366,"대전세종충남","대전","신옥천추부#1 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 신옥천-추부T/L 추락방지시설 설치공사","2022-10-04 08:00","2022-10-11 18:00","취소","취소","매일"]
[367,"대전세종충남","서산","합덕송악#2 T/L","서산P/O 154kV GIS 정밀점검공사","송악S/S 154kV 합덕-송악#2T/L GIS 6B7 정밀점검공사 - (병행) 154kV 합덕-송악#2T/L LA 보통점검","2022-10-12 09:00","2022-10-14 18:00","2022-10-12 09:00","2022-10-14 18:00","연속"]
[368,"대전세종충남","서산","신당진당진#1 T/L","154kV 합덕-송악T/L 송전선로용 피뢰기 설치공사","154kV 합덕-송악T/L 송전선로용 피뢰기 설치공사 안전이격","2022-10-21 08:00","2022-10-21 18:00","취소","취소","연속"]
[369,"대전세종충남","서산","태안안면#2 T/L","[송전]154kV 태안-안면T/L 전선교체공사","○ 공사구간 : 154kV 태안-안면T/L No.1~71(1공구 : No.1~33, 2공구 : No.33~71) ○ 전력선 : ACSR/AW 330㎟ × S × 2C -> ASCC/TW 430㎟ × S × 2C 21.778km(전선교체)","2022-10-31 07:00","2022-11-30 18:00","2022-10-31 07:00","2022-11-30 18:00","연속"]
[370,"대전세종충남","서산","서산태안 T/L","22년 서산P/O 변전협력회사 총액공사","태안S/S 154kV 서산-태안T/L CB 전자변 교체","2022-10-17 09:00","2022-10-17 18:00","2022-10-17 09:00","2022-10-17 18:00","연속"]
[371,"대전세종충남","서산","태안태안화력 T/L","22년 서산P/O 변전협력회사 총액공사","태안S/S 154kV 태안-태안화력T/L CB 전자변 교체","2022-10-04 09:00","2022-10-07 18:00","2022-10-04 09:00","2022-10-07 18:00","연속"]
[372,"대전세종충남","서산","서산태안화력 T/L","154kV 태안화력T/L 전선접속개소 전력선교체공사","154kV 서산-태안화력T/L No.2~6, 11~13 등 2개소 전력선교체","2022-10-11 08:00","2022-10-14 18:00","2022-10-11 08:00","2022-10-14 18:00","연속"]
[373,"대전세종충남","서산","합덕송악#1 T/L"," 서산P/O 154kV GIS 정밀점검공사","송악S/S 154kV 합덕-송악#1T/L GIS 6F7 정밀점검공사 - (병행) 154kV 합덕-송악#1T/L LA 보통점검 ","2022-10-05 09:00","2022-10-07 18:00","2022-10-05 09:00","2022-10-07 18:00","연속"]
[374,"대전세종충남","세종","덕진공주#2 T/L","[송전]154kV 덕진-공주#2T/L 추락방지시설 설치공사","[송전]154kV 덕진-공주#2T/L 추락방지시설 설치공사 - No. 1, 35~58, 60~61 (27기)","2022-10-05 07:00","2022-10-06 18:00","2022-10-05 07:00","2022-10-06 18:00","연속"]
[375,"대전세종충남","세종","덕진공주#1 T/L","[변전]2022년 세종P/O 154kV GIS 정밀점검공사","154kV GIS 정밀점검 시행(10BAY)","2022-10-13 09:00","2022-10-14 18:00","2022-10-13 09:00","2022-10-14 18:00","연속"]
[376,"대전세종충남","세종","덕진대화#2 T/L","[송전]154kV 덕진-대화#2T/L 추락방지시설 설치공사","[송전]154kV 덕진-대화#2T/L 추락방지시설 설치공사 - No. 3, 8~11, 13, 15~20 (12기)","2022-10-07 07:00","2022-10-07 18:00","2022-10-07 07:00","2022-10-07 18:00","연속"]
[377,"대전세종충남","세종","둔곡송강#1 T/L","[송전]154kV 둔곡-송강#1T/L 추락방지시설 설치공사","[송전]154kV 둔곡-송강#1T/L 추락방지시설 설치공사 - No. 2~14 (13기)","2022-10-27 07:00","2022-10-28 18:00","2022-10-27 07:00","2022-10-28 18:00","연속"]
[378,"대전세종충남","세종","둔곡송강#2 T/L","[송전]154kV 둔곡-송강#2T/L 추락방지시설 설치공사(수평)","[송전]154kV 둔곡-송강#2T/L 추락방지시설 설치공사(수평) - No. 2~14 (13기)","2022-10-31 07:00","2022-10-31 18:00","2022-10-31 07:00","2022-10-31 18:00","연속"]
[379,"대전세종충남","세종","세종둔곡#1 T/L","[송전]154kV 세종-둔곡#1T/L 추락방지시설 설치공사","[송전]154kV 세종-둔곡#1T/L 추락방지시설 설치공사 - No. 2~14 (13기)","2022-10-24 07:00","2022-10-25 18:00","2022-10-24 07:00","2022-10-25 18:00","연속"]
[380,"대전세종충남","세종","세종둔곡#2 T/L","[송전]154kV 세종-둔곡#2T/L 추락방지시설 설치공사(수평)","[송전]154kV 세종-둔곡#2T/L 추락방지시설 설치공사(수평) - No. 2~14 (13기)","2022-10-26 07:00","2022-10-26 18:00","2022-10-26 07:00","2022-10-26 18:00","연속"]
[381,"대전세종충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사 이격거리 확보","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 - 유사시 즉시가압가능","2022-10-11 07:00","2022-10-11 18:00","2022-10-11 07:00","2022-10-11 18:00","연속"]
[382,"대전세종충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 ○ 지지물 : 1기 교체(37호), 1기 인클로징(38호) ○ 전력선 교체 : ASCC 430 x S x 2C, 0.808km(36~39호) ○ 가공지선 설치 : ACSR 97 x S x 1C (37~39호)","2022-10-05 07:00","2022-10-06 18:00","2022-10-05 07:00","2022-10-06 18:00","연속"]
[383,"대전세종충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사 이격거리 확보","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 - 유사시 즉시 가압 가능","2022-10-05 07:00","2022-10-06 18:00","2022-10-05 07:00","2022-10-06 18:00","연속"]
[384,"대전세종충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 ○ 지지물 : 1기 교체(37호), 1기 인클로징(38호) ○ 전력선 교체 : ASCC 430 x S x 2C, 0.808km(36~39호) ○ 가공지선 설치 : ACSR 97 x S x 1C (37~39호)","2022-10-11 07:00","2022-10-11 18:00","2022-10-11 07:00","2022-10-11 18:00","연속"]
[385,"대전세종충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사 이격거리 확보","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 - 유사시 즉시가압가능","2022-10-07 07:00","2022-10-07 18:00","2022-10-07 07:00","2022-10-07 18:00","연속"]
[386,"대전세종충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 ○ 지지물 : 1기 교체(37호), 1기 인클로징(38호) ○ 전력선 교체 : ASCC 430 x S x 2C, 0.808km(36~39호) ○ 가공지선 설치 : ACSR 97 x S x 1C (37~39호)","2022-10-07 07:00","2022-10-07 18:00","2022-10-07 07:00","2022-10-07 18:00","연속"]
[387,"대전세종충남","직할","대덕둔지 T/L","22년 직할 관내 170kV GIS 정밀점검 공사","22년 직할 관내 170kV GIS 정밀점검 공사","2022-10-11 09:00","2022-10-12 18:00","2022-10-11 09:00","2022-10-12 18:00","연속"]
[388,"대전세종충남","직할","대화둔산#1 T/L","22년 직할 관내 170kV GIS 정밀점검 공사","대화변전소 22년 직할 관내 170kV GIS 정밀점검 공사","2022-10-03 09:00","2022-10-05 18:00","2022-10-03 09:00","2022-10-05 18:00","연속"]
[389,"대전세종충남","직할","송강신일#2 T/L","송강S/S 154kV GIS 주기도래 점검","□ 송강S/S 송강-신일#2T/L 보통점검","2022-10-05 09:00","2022-10-05 18:00","취소","취소","연속"]
[390,"대전세종충남","천안","신온양한샘#1 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","154kV 신온양-한샘#1T/L No.2~43 추락방지시설(수직,수평) 설치","2022-10-01 12:00","2022-10-01 18:00","취소","취소","연속"]
[391,"대전세종충남","천안","아산온양#1 T/L","아산S/S 154kV 아산온양#1T/L GIS 보통점검","아산S/S 154kV 아산온양#1T/L GIS 보통점검","2022-10-19 09:00","2022-10-19 18:00","2022-10-19 09:00","2022-10-19 18:00","연속"]
[392,"대전세종충남","천안","아산온양#2 T/L","아산S/S 아산-온양#2T/L GIS 보통점검","아산S/S 아산-온양#2T/L GIS 보통점검","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[393,"대전세종충남","천안","온양풍세#2 T/L","온양S/S 온양-풍세#2T/L GIS 보통점검","온양S/S 온양-풍세#2T/L GIS 보통점검","2022-10-18 09:00","2022-10-18 18:00","2022-10-18 09:00","2022-10-18 18:00","연속"]
[394,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 온양-풍세#1T/L GIS 보통점검","온양S/S 온양-풍세#1T/L GIS 보통점검","2022-10-17 09:00","2022-10-17 18:00","2022-10-17 09:00","2022-10-17 18:00","연속"]
[395,"대전세종충남","천안","아산인주#2 T/L","154kV 아산-인주#2T/L 송전선로 보호반 대체","154kV 아산-인주#2T/L 송전선로 보호반 대체","2022-10-11 09:00","2022-10-14 18:00","2022-10-11 09:00","2022-10-14 18:00","연속"]
[396,"대전세종충남","천안","아산인주#1 T/L","154kV 아산-인주#1T/L 송전선로 보호반 대체","154kV 아산-인주#1T/L 송전선로 보호반 대체","2022-10-04 09:00","2022-10-07 18:00","2022-10-04 09:00","2022-10-07 18:00","연속"]
[397,"대전세종충남","천안","장재천안#1 T/L","[송전]154kV 장재-천안T/L No.15~17 지장송전선로 지중화공사","154kV 장재-천안T/L No.15~17 지중화(요청자 직접시행) - XLPE 2,000㎟(D) × 2C, 0.361km","2022-10-17 07:00","2022-12-16 18:00","2022-10-17 07:00","2022-12-16 18:00","연속"]
[398,"대전세종충남","천안","장재천안#2 T/L","[송전]154kV 장재-천안T/L No.15~17 지장송전선로 지중화공사","154kV 장재-천안T/L No.15~17 지중화(요청자 직접시행) - XLPE 2,000㎟(D) × 2C, 0.361km","2022-10-17 07:00","2022-12-16 18:00","2022-10-17 07:00","2022-12-16 18:00","연속"]
[399,"대전세종충남","천안","천안전의#1 T/L","22년 170kV GIS 정밀점검 공사","- 154KV GIS 차단부 정밀점검 - 상부모선,쳄버 정밀점검 - 메카니즘 점검","2022-10-18 09:00","2022-10-20 18:00","2022-10-18 09:00","2022-10-20 18:00","연속"]
[400,"대전세종충남","천안","서천안탕정#2 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","[4회선 병가철탑 안전거리확보] 154kV 신온양-한샘#1T/L No.42 추락방지시설(수평) 설치","2022-10-01 12:00","2022-10-01 18:00","취소","취소","연속"]
[401,"대전세종충남","천안","서천안탕정#1 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","[4회선 병가철탑 안전거리확보] 154kV 신온양-한샘#1T/L No.42 추락방지시설(수평) 설치","2022-10-01 08:00","2022-10-01 12:00","취소","취소","연속"]
[402,"대전세종충남","천안","한샘직산#1 T/L","22년 170kV GIS 정밀점검 공사","- 154KV GIS 차단부 정밀점검 - 상부모선 정밀점검","2022-10-05 09:00","2022-10-07 18:00","2022-10-05 09:00","2022-10-07 18:00","연속"]
[403,"대전세종충남","천안","한샘직산#2 T/L","22년 170kV GIS 정밀점검 공사","- 154KV GIS 차단부 정밀점검 - 상부모선 정밀점검","2022-10-12 09:00","2022-10-14 18:00","2022-10-12 09:00","2022-10-14 18:00","연속"]
[404,"대전세종충남","청양","신서천대천#2 T/L","[지중] 154kV 대천S/S 인출T/L 지중화공사(1차)","○ 공 사 명 : 154kV 대천S/S 미래화사업 관련 인출T/L 지중화공사 ○ 공사대상 : 154kV 대천-서천 등 2개T/L ○ 선종 및 길이 : XLPE 2,500㎟ × 2C, 0.408km","2022-10-19 07:00","2022-11-04 18:00","2022-10-19 07:00","2022-11-04 18:00","연속"]
[405,"대전세종충남","청양","옥산부여#1 T/L","154KV 옥산부여T/L 노후금구류 교체공사","No.63~64호 노후금구류 및 전선교체","2022-10-26 09:00","2022-10-27 18:00","2022-10-26 09:00","2022-10-27 18:00","연속"]
[406,"대전세종충남","청양","청양관창#1 T/L","[송전] 154kV 청양-관창T/L 지장송전선로 이설공사","○ 공사구간 : 154kV 청양-관창T/L No.3~8 ○ 지지물 : 신설 1기 설치, 임시 2기 설치/철거, 기설 1기 철거 ○ 전력선 : ACSR 410 x 2B x 2C, 1.473km(전선교체)","2022-10-31 07:00","2022-11-04 18:00","2022-10-31 07:00","2022-11-04 18:00","연속"]
[407,"대전세종충남","청양","청양S/S CB 6100","청양S/S 154kV BUS-TIE 관련 점검","청양S/S 154kV BUS-TIE 관련 점검(6100) - 차단기 부동작 예방 조작시험 - 영인제 모선보호반 성능개선","2022-10-05 09:00","2022-10-05 14:00","2022-10-05 09:00","2022-10-05 14:00","연속"]
[408,"대전세종충남","청양","청양S/S CB 6200","청양S/S 154kV BUS-TIE 관련 점검","청양S/S 154kV BUS-TIE 관련 점검(6200) - 차단기 부동작 예방 조작시험 - 영인제 모선보호반 성능개선","2022-10-05 14:00","2022-10-05 18:00","2022-10-05 14:00","2022-10-05 18:00","연속"]
[409,"대전세종충남","청양","청양관창#2 T/L","[송전] 154kV 청양-관창T/L 지장송전선로 이설공사","○ 공사구간 : 154kV 청양-관창T/L No.3~8 ○ 지지물 : 신설 1기 설치, 임시 2기 설치/철거, 기설 1기 철거 ○ 전력선 : ACSR 410 x 2B x 2C, 1.473km(전선교체)","2022-10-24 07:00","2022-10-28 18:00","2022-10-24 07:00","2022-10-28 18:00","연속"]
[410,"전북","군산","내초SE열병합#1 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2022-10-24 09:00","2022-10-26 18:00","2022-10-24 09:00","2022-10-26 18:00","연속"]
[411,"전북","군산","내초SE열병합#2 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2022-10-31 09:00","2022-11-02 18:00","2022-10-31 09:00","2022-11-02 18:00","연속"]
[412,"전북","군산","탄소이리#2 T/L","154kV 이리-탄소T/L 송전선로 정밀점검","□ 작업내용 : 철탑,금구,애자,전선 등 이상여부점검","2022-10-11 09:00","2022-10-15 18:00","2022-10-11 09:00","2022-10-15 18:00","연속"]
[413,"전북","군산","탄소이리#1 T/L","154kV 이리-탄소T/L 송전선로 정밀점검","□ 작업내용 : 철탑,금구,애자,전선 등 이상여부점검","2022-10-04 09:00","2022-10-08 18:00","2022-10-04 09:00","2022-10-08 18:00","연속"]
[414,"전북","김제","정주부안#2 T/L","154kV 동부안분기T/L 건설공사","○ 위 치 : 154kV 정주-부안T/L No.58~60 ○ 규 모 : PIAC 410×S×2C×.0.55km, 철탑 4기(가철탑 포함) ○ 작업내용 : 임시선로 구성(No.58-가철탑-60) ○ 비상시 즉시가압여부 : 편측 가능(동시휴전 시)","2022-10-24 07:00","2022-10-29 18:00","2022-10-24 07:00","2022-10-29 18:00","연속"]
[415,"전북","김제","정주부안#1 T/L","154kV 동부안분기T/L 건설공사","○ 위 치 : 154kV 정주-부안T/L No.58~60 ○ 규 모 : PIAC 410×S×2C×.0.55km, 철탑 4기(가철탑 포함) ○ 작업내용 : 임시선로 구성(No.58-가철탑-60) ○ 비상시 즉시가압여부 : 편측 가능(동시휴전 시)","2022-10-24 07:00","2022-10-29 18:00","2022-10-24 07:00","2022-10-29 18:00","연속"]
[416,"전북","직할","동전주태평#2 T/L","동전주S/S 장기사용 170kV GIS 교체공사(3-4차, 시험가압)","○ 6233 GIS 교체 ○ 6200 B/T & 61, 66PT GIS 설치","2022-10-13 09:00","2022-10-14 18:00","2022-10-13 09:00","2022-10-14 18:00","연속"]
[417,"전북","직할","무주용담수력 T/L","[대세충] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[대세충 병가] 154kV 금산-무주T/L 추락방지시설 설치공사 안전거리 확보차","2022-10-31 08:00","2022-11-11 18:00","취소","취소","매일"]
[418,"전북","직할","북전주봉동#2 T/L","전북직할 154kV 차단기 정밀점검(무부하가압용)","전북직할 154kV 차단기 정밀점검(무부하가압용)","2022-10-12 15:00","2022-10-12 18:00","2022-10-12 15:00","2022-10-12 18:00","연속"]
[419,"전북","직할","북전주S/S #2 BUS","2022년 전북직할 154kV 차단기 점검공사 (무부하가압용)","차단기 정밀점검","2022-10-12 15:00","2022-10-12 18:00","2022-10-12 15:00","2022-10-12 18:00","연속"]
[420,"전북","직할","서곡태평#2 T/L","효성제 170kV GIS 조작기구부 교체공사","효성제 170kV GIS 조작기구부 교체공사","2022-10-21 09:00","2022-10-21 18:00","2022-10-21 09:00","2022-10-21 18:00","연속"]
[421,"전북","직할","서곡태평#1 T/L","효성제 170kV GIS 조작기구부 교체공사","효성제 170kV GIS 조작기구부 교체공사","2022-10-19 09:00","2022-10-19 18:00","2022-10-19 09:00","2022-10-19 18:00","연속"]
[422,"전북","직할","서곡태평#1 T/L","2022년 154kV 차단기 정밀점검공사(시험가압용도, 즉시가압 가능)","무부하가압 용도","2022-10-05 15:00","2022-10-05 18:00","2022-10-05 15:00","2022-10-05 18:00","연속"]
[423,"광주전남","강진","진도진도CS#1 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","진도S/S 진도-진도C/S #1,2T/L GIS 보통 진도C/S 진도-진도C/S #1,2T/L GIS 보통","2022-10-19 10:00","2022-10-19 14:00","2022-10-19 10:00","2022-10-19 14:00","연속"]
[424,"광주전남","강진","진도진도CS#2 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","진도S/S 진도-진도C/S #1,2T/L GIS 보통 진도C/S 진도-진도C/S #1,2T/L GIS 보통","2022-10-19 14:00","2022-10-19 18:00","2022-10-19 14:00","2022-10-19 18:00","연속"]
[425,"광주전남","목포","화원안좌#2 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 전선교체공사 1~47호(가공 : 송전운영부, 해저케이블 : 중부건설본부)","2022-10-02 07:00","2022-10-24 18:00","취소","취소","연속"]
[426,"광주전남","강진","해남진도#2 T/L","관내 OPGW 취약개소 및 광코어 접속불량개소 정비공사","해남-진도 #2T/L S.B댐퍼 11개소 정비","2022-10-03 07:00","2022-10-04 18:00","취소","취소","연속"]
[427,"광주전남","순천","여수T/P #60 BUS","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-10-04 09:00","2022-10-05 18:00","취소","취소","연속"]
[428,"광주전남","순천","여수TP화치#1 T/L","'22-23년 순천전력지사 변전정비 총액공사","154kV 송전선로 보호반 대체","2022-10-04 09:00","2022-10-06 18:00","취소","취소","연속"]
[429,"광주전남","강진","신강진대불#1 T/L","2022~23년 지중송전 위탁정비공사","○ 신강진S/S구내 신강진-대불(D)#1T/L 피뢰기 절연열화측정","2022-10-05 09:00","2022-10-05 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[430,"광주전남","순천","순천율촌#1 T/L","2022년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2022-10-05 09:00","2022-10-06 18:00","2022-10-05 09:00","2022-10-06 18:00","연속"]
[431,"광주전남","순천","여수T/P #65 BUS","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-10-06 09:00","2022-10-07 18:00","취소","취소","연속"]
[432,"광주전남","광주","신광주계림#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","계림S/S 신광주-계림#1T/L 조작시험","2022-10-07 09:00","2022-10-07 18:00","취소","취소","연속"]
[433,"광주전남","강진","완도강진 T/L","154kV 강진-남창T/L 용량증대 전선교체공사","ㅇ구간 - 154kV 강진-남창 #1T/L No.1~128 - 154kV 남창-완도 #2T/L No.1~48 ㅇ시공사 :삼부토건(주), 대동전기(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 520SQ로 전량교체) - 수직,수평와이어 설치","2022-10-10 07:30","2022-11-30 18:00","취소","취소","연속"]
[434,"광주전남","광주","일곡비아#2 T/L","154kV 일곡-비아 T/L 지중화공사","가. 설치분 1) 구 간 : 신설 맨홀#5 ∼ 일곡S/S 2) 선종/길이 : 154kV XLPE 2,000㎟ × 2C(D) × 0.374km 3) 케 이 블 : 포설 1구간, 접속 : 2개소 (PMIJ×1개소, 종단접속×1개소) 나. 철거분 1) 구 간 : 기설 맨홀#1 ∼ 일곡C/T 13호 2) 선종/길이 : 154kV XLPE 2,000㎟","2022-10-11 09:00","2022-11-01 18:00","취소","취소","연속"]
[435,"광주전남","순천","율촌화치#1 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-10-11 09:00","2022-10-12 18:00","2022-10-11 09:00","2022-10-12 18:00","연속"]
[436,"광주전남","목포","장성영광#1 T/L","2022년도 목포전력지사 변전협력회사 총액공사","2022년도 목포전력지사 변전협력회사 총액공사 20분내 가압 가능","2022-10-13 09:00","2022-10-13 13:00","2022-10-13 09:00","2022-10-13 13:00","연속"]
[437,"광주전남","순천","율촌화치#2 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-10-13 09:00","2022-10-14 18:00","2022-10-13 09:00","2022-10-14 18:00","연속"]
[438,"광주전남","목포","고창영광 T/L","2022년도 목포전력지사 변전협력회사 총액공사","2022년도 목포전력지사 변전협력회사 총액공사 20분내 가압 가능","2022-10-14 09:00","2022-10-14 18:00","2022-10-14 09:00","2022-10-14 18:00","연속"]
[439,"광주전남","강진","화원진도#2 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 4회선구간 작업자 안전이격확보 휴전(상시 가압조건 유지)","2022-10-15 07:00","2022-10-19 18:00","취소","취소","매일"]
[440,"광주전남","강진","화원진도#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- No.1, 2, 4회선구간 작업자 안전이격확보 휴전(상시 가압조건 유지)","2022-10-15 07:00","2022-10-16 18:00","취소","취소","매일"]
[441,"광주전남","강진","삼호화원#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- No. 4회선구간 안전이격화보 휴전(1 ~ 2호),","2022-10-15 07:00","2022-10-16 18:00","취소","취소","매일"]
[442,"광주전남","강진","진도C/S P2+FF1 CB","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) BiPole 연차점검","2022-10-15 09:00","2022-10-20 18:00","2022-10-15 09:00","2022-10-20 18:00","연속"]
[443,"광주전남","강진","진도C/S P1+FF1 CB","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) BiPole 연차점검","2022-10-15 09:00","2022-10-20 18:00","2022-10-15 09:00","2022-10-20 18:00","연속"]
[444,"광주전남","강진","진도C/S P1+FF2 CB","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) BiPole 연차점검","2022-10-15 09:00","2022-10-20 18:00","2022-10-15 09:00","2022-10-20 18:00","연속"]
[445,"광주전남","강진","진도C/S P2+FF2 CB","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) BiPole 연차점검","2022-10-15 09:00","2022-10-20 18:00","2022-10-15 09:00","2022-10-20 18:00","연속"]
[446,"광주전남","강진","서제주진도HVDC(2연계선) #1 Pole CB","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) BiPole 연차점검","2022-10-15 09:00","2022-10-20 18:00","2022-10-15 09:00","2022-10-20 18:00","연속"]
[447,"광주전남","강진","서제주진도HVDC(2연계선) #2 Pole CB","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) BiPole 연차점검","2022-10-15 09:00","2022-10-20 18:00","2022-10-15 09:00","2022-10-20 18:00","연속"]
[448,"광주전남","강진","진도진도CS#1 T/L","진도C/S 154kV Sh.R 설치공사","170kV GIS Sh.R Bay 전체 무부하가압","2022-10-17 09:00","2022-10-18 16:00","2022-10-17 09:00","2022-10-18 16:00","연속"]
[449,"광주전남","강진","진도C/S #1 BUS","진도C/S 154kV Sh.R 설치공사","170kV GIS Sh.R Bay 전체 무부하가압","2022-10-17 09:00","2022-10-18 16:00","2022-10-17 09:00","2022-10-18 16:00","연속"]
[450,"광주전남","순천","율촌여수산단#1 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-10-17 09:00","2022-10-19 18:00","취소","취소","연속"]
[451,"광주전남","강진","진도진도CS#1 T/L","진도C/S 154kV Sh.R 설치공사","154kV Sh.R 시험가압","2022-10-18 16:00","2022-10-18 18:00","2022-10-18 16:00","2022-10-18 18:00","연속"]
[452,"광주전남","강진","진도C/S #1 BUS","진도C/S 154kV Sh.R 설치공사","154kV Sh.R 시험가압","2022-10-18 16:00","2022-10-18 18:00","2022-10-18 16:00","2022-10-18 18:00","연속"]
[453,"광주전남","강진","삼호화원#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- No. 4회선구간 안전이격화보 휴전(0.1 ~ 1호),","2022-10-19 07:00","2022-10-19 18:00","취소","취소","연속"]
[454,"광주전남","광주","담양김제 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-10-19 08:00","2022-11-08 18:00","취소","취소","연속"]
[455,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-10-19 08:00","2022-10-21 15:00","취소","취소","연속"]
[456,"광주전남","광주","신광주계림#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","PT 보통점검(비상시 즉시가압 불가)","2022-10-19 09:00","2022-10-19 18:00","취소","취소","연속"]
[457,"광주전남","목포","무안햇빛개폐소S/S 무안솔라파크 T/L CB","2022년도 목포전력지사 변전협력회사 총액공사","2022년도 목포전력지사 변전협력회사 총액공사","2022-10-19 09:00","2022-10-19 18:00","2022-10-19 09:00","2022-10-19 18:00","연속"]
[458,"광주전남","순천","율촌여수산단#2 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-10-19 09:00","2022-10-21 18:00","취소","취소","연속"]
[459,"광주전남","강진","화원진도#1 T/L","154kV 화원-안좌T/L 용량증대 전선교체공사","- 4회선구간 작업자 안전이격확보 휴전(상시 가압조건 유지)","2022-10-20 07:00","2022-10-21 18:00","취소","취소","매일"]
[460,"광주전남","목포","무한햇빛개폐소S/S 무안햇빛발전소 T/L CB","2022년도 목포전력지사 변전협력회사 총액공사","2022년도 목포전력지사 변전협력회사 총액공사","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[461,"광주전남","순천","여수TP용성#1 T/L","대한제 열경화공법 EBG 보강공사","여수TP-용성#1 T/L EBG 해체점검(6상)","2022-10-20 09:00","2022-10-28 18:00","취소","취소","연속"]
[462,"광주전남","광주","담양S/S #1 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-10-21 15:00","2022-10-30 18:00","취소","취소","연속"]
[463,"광주전남","목포","영광홍농 T/L","2022년도 목포전력지사 변전협력회사 총액공사","2022년도 목포전력지사 변전협력회사 총액공사","2022-10-24 09:00","2022-10-24 18:00","2022-10-24 09:00","2022-10-24 18:00","연속"]
[464,"광주전남","순천","여수TP여천#1 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-10-24 09:00","2022-10-25 18:00","취소","취소","연속"]
[465,"광주전남","순천","호남TP여수TP#1 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-10-24 09:00","2022-10-25 18:00","취소","취소","연속"]
[466,"광주전남","광주","장성영광#2 T/L","22년 광주전력 변전협력회사 총액공사","장성-영광#2T/L GIS 보통점검","2022-10-25 09:00","2022-10-25 18:00","취소","취소","연속"]
[467,"광주전남","광주","충장농성#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 충장-농성#1T/L 조작시험","2022-10-25 09:00","2022-10-25 14:00","2022-10-25 09:00","2022-10-25 14:00","연속"]
[468,"광주전남","광주","충장농성#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 충장-농성#2T/L 조작시험","2022-10-25 14:00","2022-10-25 18:00","2022-10-25 14:00","2022-10-25 18:00","연속"]
[469,"광주전남","순천","호남TP여수TP#2 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-10-26 09:00","2022-10-27 18:00","취소","취소","연속"]
[470,"광주전남","순천","여수TP여천#2 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-10-26 09:00","2022-10-27 18:00","취소","취소","연속"]
[471,"광주전남","강진","나주금천#1 T/L","2022~23년 직할 가공송전 협력회사 총액공사","154kV 나주-금천T/L 추락방지시설 설치","2022-10-28 09:00","2022-10-28 18:00","2022-10-28 09:00","2022-10-28 18:00","매일"]
[472,"광주전남","순천","여수TP용성#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#1T/L LA(A, B, C) 하자점검","2022-10-28 09:00","2022-10-28 14:00","취소","취소","연속"]
[473,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-10-29 18:00","2022-10-30 18:00","취소","취소","연속"]
[474,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-10-31 08:00","2022-11-07 15:00","취소","취소","연속"]
[475,"광주전남","강진","나주금천#2 T/L","2022~23년 직할 가공송전 협력회사 총액공사","154kV 나주-금천T/L 추락방지시설 설치","2022-10-31 09:00","2022-10-31 18:00","2022-10-31 09:00","2022-10-31 18:00","매일"]
[476,"광주전남","순천","여수TP용성#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#2T/L LA(A, B, C) 하자점검 여수화력S/Y 여수TP-용성#2T/L GIS 보통점검 및 상시여자 보조계전기 교체","2022-10-31 10:00","2022-10-31 18:00","취소","취소","연속"]
[477,"대구","경산","청도밀양#1 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-10-26 18:00","2022-10-27 09:30","2022-10-26 18:00","2022-10-27 09:30","연속"]
[478,"대구","경산","대구청도#2 T/L","청도S/S 154kV GIS 교체공사","154kV GIS 교체","2022-10-17 09:30","2022-11-18 09:30","2022-10-17 09:30","2022-11-18 09:30","연속"]
[479,"대구","경산","대구청도#1 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-10-13 18:00","2022-10-14 09:30","2022-10-13 18:00","2022-10-14 09:30","연속"]
[480,"대구","달성","고령다산#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 고령-다산T/L 정밀점검","2022-10-17 08:00","2022-10-23 18:00","2022-10-17 08:00","2022-10-23 18:00","연속"]
[481,"대구","달성","고령쌍림#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 고령-다산T/L 정밀점검(154kV 고령-쌍림T/L 병가선로)","2022-10-17 08:00","2022-10-18 18:00","2022-10-17 08:00","2022-10-18 18:00","연속"]
[482,"대구","달성","고령쌍림#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 고령-다산T/L 정밀점검(154kV 고령-쌍림T/L 병가선로)","2022-10-24 08:00","2022-10-25 18:00","2022-10-24 08:00","2022-10-25 18:00","연속"]
[483,"대구","달성","고령다산#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 고령-다산T/L 정밀점검","2022-10-24 08:00","2022-10-28 18:00","2022-10-24 08:00","2022-10-28 18:00","연속"]
[484,"대구","달성","대구봉덕#2 T/L","2021~22년 달성전력지사 지중송전설비 위탁정비공사","154kV 대구-봉덕T/L 피뢰기 열화진단","2022-10-04 13:00","2022-10-04 17:00","2022-10-04 13:00","2022-10-04 17:00","연속"]
[485,"대구","달성","대구봉덕#1 T/L","2021~22년 달성전력지사 지중송전설비 위탁정비공사","154kV 대구-봉덕T/L 피뢰기 열화진단","2022-10-04 08:00","2022-10-04 12:00","2022-10-04 08:00","2022-10-04 12:00","연속"]
[486,"대구","달성","쌍림합천#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 쌍림-합천T/L 수평 추락방지장치 설치공사(154kV 고령-쌍림T/L 병가선로)","2022-10-13 08:00","2022-10-14 18:00","2022-10-13 08:00","2022-10-14 18:00","연속"]
[487,"대구","달성","쌍림합천#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 쌍림-합천T/L 수평 추락방지장치 설치공사(154kV 고령-쌍림T/L 병가선로)","2022-10-11 08:00","2022-10-12 18:00","2022-10-11 08:00","2022-10-12 18:00","연속"]
[488,"대구","달성","현풍유가#1 T/L","유가S/S 현풍-유가#1T/L LA 하자점검","유가S/S 현풍-유가#1T/L LA 하자점검","2022-10-28 09:00","2022-10-28 14:00","2022-10-28 09:00","2022-10-28 14:00","연속"]
[489,"대구","달성","현풍유가#2 T/L","유가S/S 현풍-유가#2T/L LA 하자점검","유가S/S 현풍-유가#2T/L LA 하자점검","2022-10-28 14:00","2022-10-28 18:00","2022-10-28 14:00","2022-10-28 18:00","연속"]
[490,"대구","칠곡","북대구구암#2 T/L","2022~23년도 대구직할 가공송전 협력회사 총액공사","북대구-구암T/L No.1~79 추락방지장치 설치","2022-10-25 07:30","2022-11-01 18:00","2022-10-25 07:30","2022-11-01 18:00","연속"]
[491,"대구","칠곡","북대구구암#1 T/L","2022~23년도 대구직할 가공송전 협력회사 총액공사","북대구-구암T/L No.1~79 추락방지장치 설치","2022-10-17 07:30","2022-10-26 18:00","2022-10-17 07:30","2022-10-26 18:00","연속"]
[492,"대구","칠곡","김천금릉#1 T/L","(안전확보) 154kV 성주-금릉#1T/L 정밀점검","(안전확보) 154kV 성주-금릉#1T/L 정밀점검 - 성주-금릉#1T/L No.101~102 (김천-금릉#1T/L No.36~37 병가)","2022-10-19 09:00","2022-10-19 18:00","2022-10-19 09:00","2022-10-19 18:00","연속"]
[493,"대구","칠곡","김천금릉#2 T/L","고정형 폴리머 점퍼지지애자 설치공사","김천-금릉#2T/L 고정형 폴리머 점퍼지지애자 설치공사 - No. 38","2022-10-27 09:00","2022-10-27 18:00","2022-10-27 09:00","2022-10-27 18:00","연속"]
[494,"대구","칠곡","남구미농소#2 T/L","고정형 폴리머 점퍼지지애자 설치공사","남구미-농소#2T/L 고정형 폴리머 점퍼지지애자 설치공사 - No.1, 3 (서대구-남구미#2T/L No.69 병가)","2022-10-05 09:00","2022-10-05 18:00","2022-10-05 09:00","2022-10-05 18:00","연속"]
[495,"대구","칠곡","북대구왜관#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","345kV #2M.Tr 2차측 부하전환(철구 → GIS) 안전이격 확보","2022-10-11 08:30","2022-10-14 18:00","2022-10-11 08:30","2022-10-14 18:00","연속"]
[496,"대구","칠곡","북대구왜관#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","345kV #2M.Tr 2차측 부하전환(철구 → GIS) 안전이격 확보","2022-10-11 08:30","2022-10-12 18:00","2022-10-11 08:30","2022-10-12 18:00","연속"]
[497,"대구","칠곡","북대구연락#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","345kV #2M.Tr 2차측 부하전환(철구 → GIS) 안전이격 확보","2022-10-11 08:30","2022-10-12 18:00","2022-10-11 08:30","2022-10-12 18:00","연속"]
[498,"대구","칠곡","서대구S/S #1 Sh.C CB","서대구S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 설비 부하전환 완료로 인한 장기 운휴","2022-10-20 08:30","2022-12-31 18:00","2022-10-20 08:30","2022-12-31 18:00","연속"]
[499,"대구","칠곡","서대구남인동#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S #1M.Tr 2차, 성주#2T/L 부하전환(철구 → GIS) 안전이격 확보","2022-10-20 08:30","2022-10-20 18:00","2022-10-20 08:30","2022-10-20 18:00","연속"]
[500,"대구","칠곡","서대구남구미#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구-남구미#2T/L 부하전환(철구 → GIS)","2022-10-03 08:30","2022-10-05 18:00","2022-10-03 08:30","2022-10-05 18:00","연속"]
[501,"대구","칠곡","서대구성주#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구-성주#1T/L 부하전환(철구 → GIS)","2022-10-06 08:30","2022-10-08 18:00","2022-10-06 08:30","2022-10-08 18:00","연속"]
[502,"대구","칠곡","서대구남구미#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S 154kV 서대구-남구미#1T/L 부하전환(철구 → GIS)","2022-10-17 08:30","2022-10-19 18:00","2022-10-17 08:30","2022-10-19 18:00","연속"]
[503,"대구","칠곡","서대구칠곡#1 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S #1M.Tr 2차, 성주#2T/L 부하전환(철구 → GIS) 안전이격 확보","2022-10-20 08:30","2022-10-21 18:00","2022-10-20 08:30","2022-10-21 18:00","연속"]
[504,"대구","칠곡","서대구남인동#1 T/L","고정형 폴리머 점퍼지지애자 설치공사","서대구-남인동#1T/L 고정형 폴리머 점퍼지지애자 설치공사 - No. 1, 2(칠곡-인동#2T/L No.8 병가), 25","2022-10-29 09:00","2022-10-29 18:00","2022-10-29 09:00","2022-10-29 18:00","연속"]
[505,"대구","칠곡","서대구칠곡#2 T/L","고정형 폴리머 점퍼지지애자 설치공사","서대구-칠곡#2T/L 고정형 폴리머 점퍼지지애자 설치공사 - No. 칠곡S/T, No.3(칠곡-인동#2 No.6 병가), 4(칠곡-인동#2 No.5 병가), 8","2022-10-28 09:00","2022-10-28 18:00","2022-10-28 09:00","2022-10-28 18:00","연속"]
[506,"대구","칠곡","서대구성주#1 T/L","(안전확보) 154kV 성주-금릉#1T/L 정밀점검","(안전확보) 154kV 성주-금릉#1T/L 정밀점검 - 성주-금릉#1T/L No.2 (서대구-성주#1T/L No.41 병가)","2022-10-11 09:00","2022-10-11 18:00","2022-10-11 09:00","2022-10-11 18:00","연속"]
[507,"대구","칠곡","서대구성주#2 T/L","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S #1M.Tr 2차, 성주#2T/L 부하전환(철구 → GIS)","2022-10-20 08:30","2022-10-25 18:00","2022-10-20 08:30","2022-10-25 18:00","연속"]
[508,"대구","칠곡","성주금릉#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 성주-금릉#2T/L 정밀점검 - No.1~102, S/T","2022-10-20 09:00","2022-10-28 18:00","2022-10-20 09:00","2022-10-28 18:00","연속"]
[509,"대구","칠곡","성주금릉#1 T/L","고정형 폴리머 점퍼지지애자 설치공사","성주-금릉#1T/L 고정형 폴리머 점퍼지지애자 설치공사 - No.84","2022-10-07 09:00","2022-10-07 18:00","2022-10-07 09:00","2022-10-07 18:00","연속"]
[510,"대구","칠곡","성주금릉#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 성주-금릉#1T/L 정밀점검 - No.1~102, S/T","2022-10-11 09:00","2022-10-19 18:00","2022-10-11 09:00","2022-10-19 18:00","연속"]
[511,"대구","칠곡","칠곡인동#2 T/L","고정형 폴리머 점퍼지지애자 설치공사","칠곡-인동#2T/L 고정형 폴리머 점퍼지지애자 설치공사 - No.8 (서대구-남인동#1 No.2 병가), 5(서대구-칠곡#2 No.4 병가), 6(서대구-칠곡#2 No.3 병가)","2022-10-28 09:00","2022-10-29 18:00","2022-10-28 09:00","2022-10-29 18:00","연속"]
[512,"대구","칠곡","칠곡인동#1 T/L","고정형 폴리머 점퍼지지애자 설치공사","칠곡-인동#1T/L 고정형 폴리머 점퍼지지애자 설치공사 - No.6(서대구-칠곡#1 No.3 병가), 7(서대구-칠곡#1 No.2 병가)","2022-10-21 09:00","2022-10-21 18:00","2022-10-21 09:00","2022-10-21 18:00","연속"]
[513,"대구","포항","상정영일 T/L","영일S/S 6333 GIS 교체공사","영일S/S 6333 GIS 교체공사 안전이격확보 및 테스트선로","2022-10-17 09:00","2022-10-28 18:00","2022-10-17 09:00","2022-10-28 18:00","연속"]
[514,"경북","구미","상주영동 T/L","154kV 화동S/S 건설공사(2차)","○ 화동S/S 보호반 이설(상주→화동) 및 시험 ○ 화동분기T/L OPGW 및 구내통신설비 설치 및 시험 ○ 화동S/S 무부하 가압, 사용전검사, 실부하 가압","2022-10-09 09:00","2022-10-14 18:00","2022-10-09 09:00","2022-10-14 18:00","연속"]
[515,"경북","영주","점촌문경 T/L","22-23년 영주전력지사 변전협력회사 총액공사","CB 조작시험","2022-10-18 10:00","2022-10-18 12:00","2022-10-23 09:00","2022-10-23 18:00","연속"]
[516,"경북","영주","예천점촌#2 T/L","22-23년 영주전력지사 변전협력회사 총액공사","LA 카운터 교체","2022-10-18 14:00","2022-10-18 18:00","2022-10-01 09:00","2022-10-01 18:00","연속"]
[517,"경북","직할","풍산안동CC#1 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","효성제 GIS 조작부 청소 및 그리스 재도포","2022-10-19 10:00","2022-10-19 14:00","2022-10-19 10:00","2022-10-19 14:00","연속"]
[518,"경북","직할","풍산안동CC#2 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","효성제 GIS 조작부 청소 및 그리스 재도포","2022-10-19 14:00","2022-10-19 18:00","2022-10-19 14:00","2022-10-19 18:00","연속"]
[519,"경북","구미","청리상주#1 T/L","154kV 청리S/S #4M.Tr 증설공사","- 154kV GIS 설치 관련 무부하가압","2022-10-20 09:00","2022-10-21 18:00","2022-10-20 09:00","2022-10-21 18:00","연속"]
[520,"경북","구미","청리상주#1 T/L","154kV 청리S/S #4M.Tr 증설공사","- 154kV GIS 설치 관련 무부하가압","2022-10-25 09:00","2022-10-26 18:00","2022-10-25 09:00","2022-10-26 18:00","연속"]
[521,"경북","직할","현종산풍력평해#1 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","효성제 GIS 조작부 청소 및 그리스 재도포","2022-10-25 10:00","2022-10-25 14:00","2022-10-25 10:00","2022-10-25 14:00","연속"]
[522,"경북","직할","현종산풍력평해#2 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","효성제 GIS 조작부 청소 및 그리스 재도포","2022-10-25 14:00","2022-10-25 18:00","2022-10-25 14:00","2022-10-25 18:00","연속"]
[523,"경북","직할","봉화현종산풍력 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","효성제 GIS 조작부 청소 및 그리스 재도포","2022-10-26 14:00","2022-10-26 18:00","2022-10-26 14:00","2022-10-26 18:00","연속"]
[524,"경북","직할","봉화현종산풍력 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","효성제 GIS 조작부 청소 및 그리스 재도포","2022-10-26 14:00","2022-10-26 18:00","2022-10-26 14:00","2022-10-26 18:00","연속"]
[525,"부산울산","동부산","신양산구서#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 설치","2022-10-06 08:00","2022-10-09 18:00","2022-10-06 08:00","2022-10-09 18:00","연속"]
[526,"부산울산","동부산","신양산구서#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 설치","2022-10-12 08:00","2022-10-16 18:00","2022-10-12 08:00","2022-10-16 18:00","연속"]
[527,"부산울산","동부산","노포정관#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 설치","2022-10-19 08:00","2022-10-21 18:00","2022-10-19 08:00","2022-10-21 18:00","연속"]
[528,"부산울산","동부산","노포정관#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 설치","2022-10-24 08:00","2022-10-26 18:00","2022-10-24 08:00","2022-10-26 18:00","연속"]
[529,"부산울산","동부산","구서노포#2 T/L","노포S/S 170GIS 정밀점검공사","노포S/S 6233GIS 정밀점검 시험가압","2022-10-28 17:00","2022-10-28 18:00","2022-10-28 17:00","2022-10-28 18:00","연속"]
[530,"부산울산","동부산","구서노포#1 T/L","노포S/S 170GIS 정밀점검공사","노포S/S 6133GIS 정밀점검 시험가압","2022-10-18 17:00","2022-10-18 18:00","2022-10-18 17:00","2022-10-18 18:00","연속"]
[531,"부산울산","동부산","웅촌서창#2 T/L","2021~2022년 직할 지중송전 위탁정비공사","EBA 절연유 채유","2022-10-20 09:00","2022-10-20 18:00","2022-10-20 09:00","2022-10-20 18:00","연속"]
[532,"부산울산","동부산","서창산막#1 T/L","2021~2022년 직할 지중송전 위탁정비공사","EBA 절연유 채유","2022-10-15 09:00","2022-10-15 18:00","2022-10-15 09:00","2022-10-15 18:00","연속"]
[533,"부산울산","동부산","웅촌서창#1 T/L","2021~2022년 직할 지중송전 위탁정비공사","EBA 절연유 채유","2022-10-21 09:00","2022-10-21 18:00","2022-10-21 09:00","2022-10-21 18:00","연속"]
[534,"부산울산","동부산","서창산막#2 T/L","2021~2022년 직할 지중송전 위탁정비공사","EBA 절연유 채유","2022-10-16 09:00","2022-10-16 18:00","2022-10-16 09:00","2022-10-16 18:00","연속"]
[535,"부산울산","동부산","신양산수영#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 설치","2022-10-03 08:00","2022-10-06 18:00","2022-10-03 08:00","2022-10-06 18:00","연속"]
[536,"부산울산","동부산","신양산수영#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 설치","2022-10-10 08:00","2022-10-16 18:00","2022-10-10 08:00","2022-10-16 18:00","연속"]
[537,"부산울산","북부산","호포물금 T/L","북부산-호포간 OPGW 증설공사","북부산-호포간 OPGW 증설 : 8.1km","2022-10-15 08:00","2022-10-15 18:00","2022-10-15 08:00","2022-10-15 18:00","연속"]
[538,"부산울산","북부산","북부산호포 T/L","북부산-호포간 OPGW 증설공사","북부산-호포간 OPGW 증설 : 8.1km","2022-10-14 08:00","2022-10-17 18:00","2022-10-14 08:00","2022-10-17 18:00","연속"]
[539,"부산울산","북부산","언양산막#2 T/L","154kV 언양-산막 등 2개 T/L 자기애관 교체공사","154kV 언양-산막T/L 비표준 자기애관 교체공사 자기애관2,000㎟을 폴리머애관 2,000㎟으로 변경","2022-10-24 09:00","2022-10-28 18:00","2022-10-24 09:00","2022-10-28 18:00","연속"]
[540,"부산울산","북부산","언양산막#1 T/L","154kV 언양-산막 등 2개 T/L 자기애관 교체공사","154kV 언양-산막T/L 비표준 자기애관 교체공사 자기애관2,000㎟을 폴리머애관 2,000㎟으로 변경","2022-10-17 09:00","2022-10-21 18:00","2022-10-17 09:00","2022-10-21 18:00","연속"]
[541,"부산울산","북부산","학장개금#2 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV 학장-개금#2T/L GIS 정밀점검","2022-10-04 08:00","2022-10-05 18:00","2022-10-06 08:00","2022-10-07 18:00","연속"]
[542,"부산울산","북부산","학장개금#2 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV 주례지하철T/L GIS 정밀점검 - 시험가압선로 : 학장-개금#2T/L , #2BUS","2022-10-09 17:00","2022-10-09 18:00","2022-10-09 17:00","2022-10-09 18:00","연속"]
[543,"부산울산","북부산","학장개금#1 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV #1M.Tr 1차 GIS 정밀점검 - 시험가압선로 : 학장-개금#1T/L , #1BUS","2022-10-12 17:00","2022-10-12 18:00","2022-10-12 17:00","2022-10-12 18:00","연속"]
[544,"부산울산","북부산","학장개금#1 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV BUS TIE GIS 정밀점검 - 시험가압선로 : 학장-개금#1T/L , #1BUS","2022-10-28 17:00","2022-10-28 18:00","2022-10-28 17:00","2022-10-28 18:00","연속"]
[545,"부산울산","북부산","학장개금#2 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV #4M.Tr 1차 GIS(6433) 정밀점검 - 시험가압선로 : 학장-개금#2T/L , #2BUS","2022-10-26 17:00","2022-10-26 18:00","2022-10-26 17:00","2022-10-26 18:00","연속"]
[546,"부산울산","북부산","학장개금#1 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV #3M.Tr 1차 GIS 정밀점검 - 시험가압선로 : 학장-개금#1T/L , #1BUS","2022-10-21 17:00","2022-10-21 18:00","2022-10-21 17:00","2022-10-21 18:00","연속"]
[547,"부산울산","북부산","학장개금#2 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV #2M.Tr 1차 GIS(6233) 정밀점검 - 시험가압선로 : 학장-개금#2T/L , #2BUS","2022-10-19 17:00","2022-10-19 18:00","2022-10-19 17:00","2022-10-19 18:00","연속"]
[548,"부산울산","북부산","엄궁학장#2 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV 엄궁-학장#2T/L GIS 정밀점검","2022-10-15 08:00","2022-10-16 18:00","2022-10-15 08:00","2022-10-16 18:00","연속"]
[549,"부산울산","서부산","서부산S/S #66 BUS","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검 -시험가압 관련 휴전","2022-10-28 14:00","2022-10-28 18:00","2022-10-28 14:00","2022-10-28 18:00","연속"]
[550,"부산울산","서부산","서부산S/S CB 6200","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검 -시험가압 관련 휴전","2022-10-28 14:00","2022-10-28 18:00","2022-10-28 14:00","2022-10-28 18:00","연속"]
[551,"부산울산","서부산","서부산신평#1 T/L","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검 - 시험가압선로","2022-10-28 14:00","2022-10-28 18:00","2022-10-28 14:00","2022-10-28 18:00","연속"]
[552,"부산울산","서부산","서부산S/S SEC CB 65660","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검","2022-10-27 09:00","2022-10-28 18:00","2022-10-27 09:00","2022-10-28 18:00","연속"]
[553,"부산울산","서부산","서부산S/S CB 6200","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검 -시험가압 관련 휴전","2022-10-25 14:00","2022-10-25 18:00","2022-10-25 14:00","2022-10-25 18:00","연속"]
[554,"부산울산","서부산","서부산S/S #61 BUS","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검 -시험가압 관련 휴전","2022-10-25 14:00","2022-10-25 18:00","2022-10-25 14:00","2022-10-25 18:00","연속"]
[555,"부산울산","서부산","서부산S/S SEC CB 60610","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검","2022-10-24 09:00","2022-10-25 18:00","2022-10-24 09:00","2022-10-25 18:00","연속"]
[556,"부산울산","서부산","서부산신평#1 T/L","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검 - 시험가압선로","2022-10-25 14:00","2022-10-25 18:00","2022-10-25 14:00","2022-10-25 18:00","연속"]
[557,"부산울산","서부산","신녹산용원#2 T/L","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검","2022-10-13 09:00","2022-10-14 18:00","2022-10-13 09:00","2022-10-14 18:00","연속"]
[558,"부산울산","서부산","신녹산용원#1 T/L","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검","2022-10-11 09:00","2022-10-12 18:00","2022-10-11 09:00","2022-10-12 18:00","연속"]
[559,"부산울산","서부산","신녹산녹산#2 T/L","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검","2022-10-06 09:00","2022-10-07 18:00","2022-10-06 09:00","2022-10-07 18:00","연속"]
[560,"부산울산","서부산","신녹산녹산#1 T/L","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검","2022-10-04 09:00","2022-10-05 18:00","2022-10-04 09:00","2022-10-05 18:00","연속"]
[561,"부산울산","서부산","신녹산S/S #1 Sh.C CB","신녹산S/S 154kV Sh.C GCB 설치공사","신녹산S/S 154kV Sh.C GCB 설치공사","2022-10-17 09:00","2022-12-16 18:00","2022-10-17 09:00","2022-12-16 18:00","연속"]
[562,"부산울산","울산","남울산신온산#2 T/L","154kV 추락방지장치 설치공사","ㅇ 수직수평 추락방지장치 설치(No.1~4)","2022-10-27 07:30","2022-10-27 18:00","2022-10-27 07:30","2022-10-27 18:00","연속"]
[563,"부산울산","울산","남울산신온산#1 T/L","154kV 추락방지장치 설치공사","ㅇ 수직수평 추락방지장치 설치(No.1~4)","2022-10-26 07:30","2022-10-26 18:00","2022-10-26 07:30","2022-10-26 18:00","연속"]
[564,"부산울산","울산","산하방어진#1 T/L","154kV 추락방지장치, 피뢰기 설치공사","ㅇ 효문-방어진(#산하-방어진) No.5~20 - 피뢰기, 추락방지장치 수직 수평 설치(16기)","2022-10-04 08:00","2022-10-07 18:00","2022-10-06 08:00","2022-10-14 18:00","연속"]
[565,"부산울산","울산","신울산언양#1 T/L","154kV 추락방지장치 설치공사","ㅇ 추락방지장치 설치 (No.1~63) - 수직+수평(15), 수평(37) 추락방지장치 설치","2022-10-19 08:00","2022-11-04 18:00","2022-10-19 08:00","2022-11-04 18:00","연속"]
[566,"부산울산","울산","신울산언양#2 T/L","2022~2023년 울산전력지사 가공송전협력회사 총액공사","□ 국산애자교체, 애자련보강 - 국산애자교체 : No.46(전원하단) - 애자련보강 : No.27,28,33","2022-10-03 08:00","2022-10-08 18:00","2022-10-03 08:00","2022-10-08 18:00","연속"]
[567,"부산울산","울산","신온산온산#3 T/L","22년 하반기 154kV 개폐장치 정밀점검공사","한국가스#1T/L GIS 정밀점검관련 시험가압(1Hr)","2022-10-23 17:00","2022-10-23 18:00","2022-10-23 17:00","2022-10-23 18:00","연속"]
[568,"부산울산","울산","두왕울산#2 T/L","154kV 울산-매암T/L SW증설공사","시험가압( #2DS, #6DS,CB 투입)","2022-10-28 14:00","2022-10-29 15:00","2022-10-28 14:00","2022-10-29 15:00","연속"]
[569,"부산울산","울산","울산S/S #1 BUS","154kV 울산-매암T/L SW증설공사","시험가압(1DS 투입)","2022-10-29 14:00","2022-10-29 15:00","2022-10-29 14:00","2022-10-29 15:00","연속"]
[570,"부산울산","울산","두왕울산#2 T/L","154kV 울산-매암T/L SW증설공사","가스감압","2022-10-24 09:00","2022-10-24 18:00","2022-10-24 09:00","2022-10-24 18:00","연속"]
[571,"부산울산","울산","울산S/S #2 BUS","154kV 울산-매암T/L SW증설공사","울산S/S 울산-매암T/L SW증설","2022-10-24 09:00","2022-10-29 14:00","2022-10-24 09:00","2022-10-29 14:00","연속"]
[572,"부산울산","울산","두왕울산#2 T/L","154kV 울산-매암T/L SW증설공사","가스 감압","2022-10-18 09:00","2022-10-18 18:00","2022-10-18 09:00","2022-10-18 18:00","연속"]
[573,"부산울산","울산","울산S/S #1 BUS","154kV 울산-매암T/L SW증설공사","울산S/S 울산-매암T/L SW증설","2022-10-18 09:00","2022-10-23 15:00","2022-10-18 09:00","2022-10-23 15:00","연속"]
[574,"부산울산","울산","두왕울산#2 T/L","154kV 울산-매암T/L SW증설공사","#1BUS 시험가압 (1DS 개방)","2022-10-22 15:00","2022-10-23 15:00","2022-10-22 15:00","2022-10-23 15:00","연속"]
[575,"부산울산","울산","온산처용#2 T/L","처용S/S 154kV 대한유화T/L GIS 대체공사","154kV GIS 50kA 2,000A 1CCT 대체","2022-10-03 17:00","2022-10-04 18:00","2022-10-03 17:00","2022-10-04 18:00","연속"]
[576,"부산울산","울산","온산처용#2 T/L","22년 하반기 154kV M.Tr 정밀점검공사","#4M.Tr 정밀점검관련 시험가압(1Hr)","2022-10-28 17:00","2022-10-28 18:00","2022-10-28 17:00","2022-10-28 18:00","연속"]
[577,"부산울산","울산","온산처용#2 T/L","22~23년 변전협력회사 총액공사","처용S/S SA시스템화","2022-10-24 09:00","2022-10-25 18:00","2022-10-24 09:00","2022-10-25 18:00","연속"]
[578,"부산울산","울산","온산처용#1 T/L","22~23년 변전협력회사 총액공사","처용S/S SA시스템화","2022-10-17 07:30","2022-10-18 18:00","2022-10-17 07:30","2022-10-18 18:00","연속"]
[579,"부산울산","울산","온산처용#2 T/L","22년 하반기 154kV 개폐장치 정밀점검공사","S-OIL #4T/L GIS 정밀점검관련 시험가압(1Hr)","2022-10-01 17:00","2022-10-01 18:00","2022-09-29 09:00","2022-09-29 10:00","연속"]
[580,"부산울산","직할","범일서면#2 T/L","22-23년 직할 변전협력회사 총액공사","서면S/S 범일-서면#2T/L GIS CB INDICATOR 불량 보수","2022-10-08 09:30","2022-10-08 18:00","2022-10-08 09:30","2022-10-08 18:00","연속"]
[581,"부산울산","직할","수정S/S #1 BUS","22-23년 직할 변전협력회사 총액공사","수정S/S 154kV PT집합반 대체","2022-10-13 09:30","2022-10-13 12:00","2022-10-13 09:30","2022-10-13 12:00","연속"]
[582,"부산울산","직할","수정S/S #2 BUS","22-23년 직할 변전협력회사 총액공사","수정S/S 154kV PT집합반 대체","2022-10-14 15:00","2022-10-14 18:00","2022-10-14 15:00","2022-10-14 18:00","연속"]
[583,"부산울산","직할","수정S/S #1 BUS","22-23년 직할 변전협력회사 총액공사","수정S/S 154kV PT집합반 대체","2022-10-14 10:00","2022-10-14 15:00","2022-10-14 10:00","2022-10-14 15:00","연속"]
[584,"부산울산","직할","수정S/S #2 BUS","22-23년 직할 변전협력회사 총액공사","수정S/S 154kV PT집합반 대체","2022-10-13 13:00","2022-10-13 18:00","2022-10-13 13:00","2022-10-13 18:00","연속"]
[585,"경남","직할","신김해삼정#2 T/L","22년 경남 직할 154kV 주변압기 및 OLTC 정밀점검 공사","22년 경남 직할 154kV 주변압기 및 OLTC 정밀점검 공사(시험가압)","2022-10-16 16:00","2022-10-16 18:00","2022-10-16 16:00","2022-10-16 18:00","연속"]
[586,"경남","직할","신월동읍#1 T/L","2022년도 지중송전 정비전문공사","154kV 신월-동읍#1T/L OF케이블 절연유 채유(분석)","2022-10-20 08:00","2022-10-20 10:00","2022-10-20 08:00","2022-10-20 10:00","연속"]
[587,"경남","직할","신월삼정#1 T/L","2022년도 지중송전 정비전문공사","154kV 신월-삼정#1T/L OF케이블 절연유 채유(분석)","2022-10-20 08:00","2022-10-20 10:00","2022-10-20 08:00","2022-10-20 10:00","연속"]
[588,"경남","직할","신월삼정#2 T/L","2022-2023년 경남본부 지중송전협력회사 총액공사","노후 피뢰기 교체","2022-10-20 10:00","2022-10-21 18:00","2022-10-20 10:00","2022-10-21 18:00","매일"]
[589,"경남","직할","신월동읍#2 T/L","2022년도 지중송전 정비전문공사","154kV 신월-동읍#2T/L OF케이블 절연유 채유(분석)","2022-10-20 10:00","2022-10-20 12:00","2022-10-20 10:00","2022-10-20 12:00","연속"]
[590,"경남","진주","개양S/S CB 6100","개양S/S 6100 GIS 보통점검","개양S/S 6100 GIS 보통점검","2022-10-28 10:00","2022-10-28 18:00","2022-10-28 10:00","2022-10-28 18:00","연속"]
[591,"경남","진주","의령동진주#2 T/L","2022년도 지중송전 정비전문공사","154kV 의령-동진주#2T/L PD(측정) 집합반 설치","2022-10-15 13:00","2022-10-15 17:00","2022-10-15 13:00","2022-10-15 17:00","연속"]
[592,"경남","진주","의령동진주#1 T/L","2022년도 지중송전 정비전문공사","154kV 의령-동진주#1T/L PD(측정)집합반 설치","2022-10-15 08:00","2022-10-15 12:00","2022-10-15 08:00","2022-10-15 12:00","연속"]
[593,"경남","진주","산청함양 T/L","154kV 산청S/S 외벽 리모델링공사","1. 공사목적 : 건물 노후화로 인한 외벽 누수 및 화재확산 위험에 따른 마감재 교체 시행 2. 공사개요 가. 기존 외벽 마감재 철거(전면교체) : 1,617 m2 나. 샌드위치패널(메탈패널) 설치 : 1,572 m2","2022-10-17 09:00","2022-10-22 18:00","2022-10-17 09:00","2022-10-22 18:00","연속"]
[594,"경남","진주","의령산청 T/L","154kV 산청S/S 외벽 리모델링공사","1. 공사목적 : 건물 노후화로 인한 외벽 누수 및 화재확산 위험에 따른 마감재 교체 시행 2. 공사개요 가. 기존 외벽 마감재 철거(전면교체) : 1,617 m2 나. 샌드위치패널(메탈패널) 설치 : 1,572 m2","2022-10-24 09:00","2022-10-29 18:00","2022-10-24 09:00","2022-10-29 18:00","연속"]
[595,"경남","진주","진주개양#2 T/L","154kV 진주-개양T/L 추락방지시설 설치공사","□ 휴전설비 : 진주-개양#1,2T/L 동시휴전 □ 설치대상 : 진주-개양#1,2T/L No.11~15","2022-10-09 07:00","2022-10-10 18:00","2022-10-09 07:00","2022-10-10 18:00","매일"]
[596,"경남","진주","동진주진주#1 T/L","154kV 동진주-진주T/L 추락방지장치 시설공사","□ 휴전설비 : 동진주진주#1,2T/L 동시휴전 □ 설치대상 : 동진주진주#1,2T/L No.1~4","2022-10-08 07:00","2022-10-08 18:00","2022-10-08 07:00","2022-10-08 18:00","연속"]
[597,"경남","진주","동진주진주#2 T/L","154kV 동진주-진주T/L 추락방지시설 설치공사","□ 휴전설비 : 동진주진주#1,2T/L 동시휴전 □ 설치대상 : 동진주진주#1,2T/L No.1~4","2022-10-08 07:00","2022-10-08 18:00","2022-10-08 07:00","2022-10-08 18:00","연속"]
[598,"경남","진주","진주개양#1 T/L","154kV 진주-개양T/L 추락방지장치 설치공사","□ 휴전설비 : 진주-개양#1,2T/L 동시휴전 □ 설치대상 : 진주-개양#1,2T/L No.11~15","2022-10-09 07:00","2022-10-10 18:00","2022-10-09 07:00","2022-10-10 18:00","매일"]
[599,"경남","통영","신고성고성 T/L","고성S/S 신고성-고성T/L GIS 보통점검 등 3건","1. 고성S/S 신고성-고성T/L GIS 보통점검 2. LA A,B,C 보통점검 3. 신고성S/S 신고성-고성T/L GIS 조작시험","2022-10-16 09:30","2022-10-16 18:00","2022-10-16 09:30","2022-10-16 18:00","연속"]
[600,"경남","통영","신고성거제#2 T/L","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","2022-10-29 07:00","2022-10-30 18:00","2022-10-29 07:00","2022-10-30 18:00","매일"]
[601,"경남","통영","신고성거제#2 T/L","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","2022-10-22 07:00","2022-10-23 18:00","2022-10-22 07:00","2022-10-23 18:00","매일"]
[602,"경남","통영","신고성거제#1 T/L","154kV 진동-안정#1T/L 추락방지장치 설치공사 안전작업거리 확보","154kV 진동-안정#1T/L 추락방지장치 설치공사 안전작업거리 확보","2022-10-08 07:00","2022-10-08 18:00","2022-10-08 07:00","2022-10-08 18:00","연속"]
[603,"경남","통영","신고성거제#1 T/L","154kV 진동-안정#1T/L 추락방지장치 설치공사 안전작업거리 확보","154kV 진동-안정#1T/L 추락방지장치 설치공사 안전작업거리 확보","2022-10-01 07:00","2022-10-03 18:00","2022-10-01 07:00","2022-10-03 18:00","매일"]
[604,"경남","통영","신고성통영 T/L","통영S/S 신고성-통영T/L GIS 정밀점검 등 2건","1. 통영S/S 신고성-통영T/L GIS 정밀점검 2. 신고성S/S 신고성-통영T/L GIS 조작시험","2022-10-09 09:30","2022-10-10 18:00","2022-10-09 09:30","2022-10-10 18:00","연속"]
[605,"경남","함안","매리김해#1 T/L","매리S/S 154kV #3M.TR GIS 정밀점검 1DS 시험가압용","매리S/S 154kV #3M.TR GIS 정밀점검 1DS 시험가압용(매리S/S 154kV 매리-김해#1T/L GIS)","2022-10-24 16:00","2022-10-24 17:00","2022-10-24 16:00","2022-10-24 17:00","연속"]
[606,"경남","함안","매리김해#1 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : #1T/L 전력선 및 가공지선 설치","2022-10-01 07:00","2022-10-04 18:00","2022-10-01 07:00","2022-10-04 18:00","연속"]
[607,"경남","함안","매리김해#2 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : #1T/L 전력선 및 가공지선 설치","2022-10-01 07:00","2022-10-01 15:00","2022-10-01 07:00","2022-10-01 15:00","연속"]
[608,"경남","함안","호포매리#1 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : #1T/L 전력선 및 가공지선 설치","2022-10-01 07:00","2022-10-04 18:00","2022-10-01 07:00","2022-10-04 18:00","연속"]
[609,"경남","함안","매리S/S CB 6100","매리S/S 154kV #1-#2 BUS TIE GIS 정밀점검","매리S/S 154kV #1-#2 BUS TIE GIS 정밀점검(단로기부 포함)","2022-10-05 09:30","2022-10-07 17:30","취소","취소","연속"]
[610,"경남","함안","매리김해#1 T/L","매리S/S 154kV #1-#2 BUS TIE GIS #1DS 시험가압","매리S/S 154kV #1-#2 BUS TIE GIS 정밀점검 #1DS부 시험가압(매리S/S 154kV 매리-김해#1T/L GIS)","2022-10-05 16:00","2022-10-05 17:00","취소","취소","연속"]
[611,"경남","함안","매리김해#2 T/L","매리S/S 154kV #1-#2 BUS TIE GIS #2DS 시험가압","매리S/S 154kV #1-#2 BUS TIE GIS 정밀점검 CB부, #2DS부 시험가압(매리S/S 154kV 매리-김해#2T/L GIS)","2022-10-07 16:00","2022-10-07 17:00","취소","취소","연속"]
[612,"경남","함안","매리김해#2 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : #2T/L 전력선 및 가공지선 설치","2022-10-08 07:00","2022-10-11 18:00","2022-10-08 07:00","2022-10-11 18:00","연속"]
[613,"경남","함안","매리김해#2 T/L","매리S/S 154kV #3M.TR GIS 정밀점검 2DS 시험가압용","매리S/S 154kV #3M.TR GIS 정밀점검 2DS 시험가압용(매리S/S 154kV 매리-김해#2T/L GIS)","2022-10-26 16:00","2022-10-26 17:00","2022-10-26 16:00","2022-10-26 17:00","연속"]
[614,"경남","함안","매리김해#2 T/L","매리S/S 154kV #2M.Tr GIS 정밀점검 2DS부 시험가압용","매리S/S 154kV #2M.Tr GIS 정밀점검 CB부, 2DS부 시험가압용(매리S/S 154kV 매리-김해#2T/L GIS)","2022-10-20 16:00","2022-10-20 17:00","2022-10-20 16:00","2022-10-20 17:00","연속"]
[615,"경남","함안","매리김해#1 T/L","매리S/S 154kV #2M.Tr GIS 정밀점검 1DS부 시험가압용","매리S/S 154kV #2M.Tr GIS 정밀점검 1DS부 시험가압용(매리S/S 154kV 매리-김해#1T/L GIS)","2022-10-18 16:00","2022-10-18 17:00","2022-10-18 16:00","2022-10-18 17:00","연속"]
[616,"경남","함안","매리김해#2 T/L","매리S/S 154kV #1M.TR 1차 GIS 정밀점검 #2DS 시험","매리S/S 154kV #1M.TR 1차 GIS 정밀점검 CB부,. #2DS부 시험가압용(매리S/S 154kV 매리-김해#2T/L GIS)","2022-10-14 16:00","2022-10-14 17:00","2022-10-14 16:00","2022-10-14 17:00","연속"]
[617,"경남","함안","매리김해#1 T/L","매리S/S 154kV #1M.TR 1차 GIS 정밀점검 #1DS 시험","매리S/S 154kV #1M.TR 1차 GIS 정밀점검 #1DS부 시험가압용(매리S/S 154kV 매리-김해#1T/L GIS)","2022-10-12 16:00","2022-10-12 17:00","2022-10-12 16:00","2022-10-12 17:00","연속"]
[618,"경남","함안","호포매리#2 T/L","154kV 호포-매리T/L 변위철탑 교체공사","154kV 호포-매리T/L 변위철탑 교체관련 전력선 설치 ㅇ 공사구간 : 154kV 호포-매리T/L 23호~매리S/S 0.503km ㅇ 작업내용 : #2T/L 전력선 및 가공지선 설치","2022-10-08 07:00","2022-10-11 18:00","2022-10-08 07:00","2022-10-11 18:00","연속"]
[619,"경남","함안","한림정삼계#1 T/L","삼계S/S 154kV 한림정-삼계#1T/L GIS 보통점검 외","삼계S/S 154kV 한림정-삼계#1T/L GIS 보통점검, 154kV LA ABC상 보통점검","2022-10-14 09:30","2022-10-14 17:30","2022-10-14 09:30","2022-10-14 17:30","연속"]
[620,"경남","함안","주촌삼계#2 T/L","삼계S/S 154kV #4M.TR GIS 정밀점검 시험가압용","삼계S/S 154kV #4M.TR GIS 정밀점검 시험가압용(삼계S/S 154kV 주촌-삼계#2T/L GIS)","2022-10-28 16:00","2022-10-28 17:00","2022-10-28 16:00","2022-10-28 17:00","연속"]
[621,"경남","함안","신마산S/S #61 BUS","신마산S/S 154kV #61 BUS 모선 PT,LA 보통점검","신마산S/S 154kV #61 BUS 모선 PT,LA 보통점검","2022-10-26 09:30","2022-10-26 13:30","2022-10-26 09:30","2022-10-26 13:30","연속"]
[622,"경남","함안","신마산S/S #65 BUS","신마산S/S 154kV #65 BUS 모선 PT,LA 보통점검","신마산S/S 154kV #65 BUS 모선 PT,LA 보통점검","2022-10-24 13:30","2022-10-24 17:30","2022-10-24 13:30","2022-10-24 17:30","연속"]
[623,"경남","함안","신마산S/S #60 BUS","신마산S/S 154kV #60 BUS 모선 PT,LA 보통점검","신마산S/S 154kV #60 BUS 모선 PT,LA 보통점검","2022-10-24 09:30","2022-10-24 13:30","2022-10-24 09:30","2022-10-24 13:30","연속"]
[624,"경남","함안","신마산S/S #66 BUS","신마산S/S 154kV #66 BUS 모선 PT,LA 보통점검","신마산S/S 154kV #66 BUS 모선 PT,LA 보통점검","2022-10-26 13:30","2022-10-26 17:30","2022-10-26 13:30","2022-10-26 17:30","연속"]
[625,"경남","함안","신마산칠서#2 T/L","칠서S/S 154kV 신마산-칠서#2T/L GIS 하자점검","칠서S/S 154kV 신마산-칠서#2T/L GIS 하자점검","2022-10-21 09:30","2022-10-21 17:30","2022-10-21 09:30","2022-10-21 17:30","연속"]
[626,"경남","함안","신마산칠서#1 T/L","칠서S/S 154kV 신마산-칠서#1T/L GIS 하자점검","칠서S/S 154kV 신마산-칠서#1T/L GIS 하자점검","2022-10-20 09:30","2022-10-20 17:30","2022-10-20 09:30","2022-10-20 17:30","연속"]