{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":17,"n_cols":11,"rows_kept":17,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 11월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성S/S #5 M.Tr","765kV M.Tr 보통점검 공사","- #5M.Tr 보통점검","2022-11-02 08:00","2022-11-16 18:00","2022-11-02 08:00","2022-11-16 18:00","연속"]
[2,"강원","태백","신태백S/S #3 M.Tr","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV 76Bay B/F PNL 교체","2022-11-14 10:00","2022-11-18 18:00","2022-11-14 10:00","2022-11-18 18:00","연속"]
[3,"충북","직할","신중부S/S CB 8800","신중부S/S 765kV GIS 하자보수","현대제 GIS 내부정밀점검 및 부품교체","2022-11-03 10:00","2022-11-11 18:00","2022-11-03 10:00","2022-11-11 18:00","연속"]
[4,"충북","직할","신중부S/S #5 M.Tr","신중부S/S 765kV GIS 하자보수","GIS 점검 후 무부하가압을 위한 변압기휴전","2022-11-11 10:00","2022-11-11 18:00","2022-11-11 10:00","2022-11-11 18:00","연속"]
[5,"충북","직할","신중부S/S CB 8872","신중부S/S 765kV GIS 하자보수","현대제 GIS 내부정밀점검 및 부품교체","2022-11-14 10:00","2022-11-22 18:00","2022-11-14 10:00","2022-11-22 18:00","연속"]
[6,"충북","직할","신중부S/S #5 M.Tr","신중부S/S 765kV GIS 하자보수","GIS 점검 후 무부하가압을 위한 변압기휴전","2022-11-22 10:00","2022-11-22 18:00","2022-11-22 10:00","2022-11-22 18:00","연속"]
[7,"충북","직할","신중부S/S #4 M.Tr","신중부변전소 345kV GIS DS Pin 교체공사","PD발생 개선을 위한 Pin 교체작업","2022-11-26 09:00","2022-11-27 18:00","2022-11-26 09:00","2022-11-27 18:00","연속"]
[8,"충북","직할","신중부S/S #2 BUS","신중부S/S 765kV GIS 하자보수","765kV GIS 점검 후 무부하가압을 위한 휴전","2022-11-01 09:00","2022-11-01 18:00","2022-11-02 09:00","2022-11-02 18:00","연속"]
[9,"부산울산","동부산","신고리N/P CB 8471","신고리S/S 765kV GIS 보통점검","신고리S/S 765kV GIS 보통점검(8471)","2022-11-01 09:00","2022-11-04 18:00","취소","취소","연속"]
[10,"부산울산","동부산","신고리N/P #3 Tie-Tr","신고리S/S 765kV GIS 정밀점검 관련 시험가압","신고리S/S 765kV GIS 정밀점검 관련 시험가압(8171,8100)","2022-11-19 09:00","2022-11-19 11:00","취소","취소","연속"]
[11,"부산울산","동부산","신고리N/P #1 BUS","신고리S/S 765kV GIS 정밀점검 관련 시험가압","신고리S/S 765kV GIS 정밀점검 관련 시험가압(8171,8100)","2022-11-19 09:00","2022-11-19 11:00","취소","취소","연속"]
[12,"부산울산","동부산","신고리N/P #3 Tie-Tr","신고리S/S #3M.Tr 3차측 전력케이블 교체","신고리S/S #3M.Tr 3차측 전력케이블 교체","2022-11-28 09:00","2022-12-09 18:00","취소","취소","연속"]
[13,"부산울산",null,"신고리N/P #2호기 주변압기 (CB 8100, 8171)","신고리2호기 7차 계획예방정비 *조작 차단기 : CB 8100, 8171","○ SWYD 8100, 8171 차단기 정밀점검 ○ 주변압기 점검","2022-11-04 09:00","2022-11-24 18:00","2022-11-04 09:00","2022-11-24 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":320,"n_cols":11,"rows_kept":320,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2022년도 11월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #3 M.Tr","성동S/S 345kV M.Tr 및 OLTC 정밀점검공사","#3M.Tr 정밀점검","2022-11-21 09:00","2022-12-02 18:00","2022-11-21 09:00","2022-12-02 18:00","연속"]
[2,"서울","성동","성동S/S #4 M.Tr","성동S/S #4M.Tr 러버백 교체","본체 컨서베이터 러버백 불량 교체","2022-11-14 09:00","2022-11-18 18:00","취소","취소","연속"]
[3,"남서울","강남","신양재S/S #1 Sh.R CB","신양재S/S 345kV #1Sh.R Ry PNL 회로개선","신양재S/S 345kV #1Sh.R Ry PNL 회로개선","2022-11-02 09:00","2022-11-02 14:00","2022-11-02 09:00","2022-11-02 14:00","연속"]
[4,"남서울","강남","신양재S/S #2 Sh.R CB","신양재S/S 345kV #2Sh.R Ry PNL 회로개선","신양재S/S 345kV #2Sh.R Ry PNL 회로개선","2022-11-02 14:00","2022-11-02 18:00","2022-11-02 14:00","2022-11-02 18:00","연속"]
[5,"남서울","동서울","동서울S/S #3 M.Tr","동서울S/S 154kV 옥외철구 GIS화 공사","동서울-서종#2, 팔수T/L EBG 접속 작업 활선 이격거리 확보","2022-11-04 09:00","2022-11-17 18:00","2022-11-04 09:00","2022-11-18 18:00","연속"]
[6,"남서울","영등포","신광명S/S CB 7100","2022~23년 영등포P/O 변전협력회사 총액공사","345kV 신시흥#1T/L-서서울#1T/L TIE GCB 조작시험","2022-11-07 09:00","2022-11-07 18:00","취소","취소","연속"]
[7,"남서울","영등포","신광명S/S CB 7472","2022~23년 영등포P/O 변전협력회사 총액공사","345kV 신시흥-신광명#2T/L GCB 보통점검","2022-11-04 09:00","2022-11-04 18:00","취소","취소","연속"]
[8,"남서울","영등포","신광명S/S CB 7272","2022~23년 영등포P/O 변전협력회사 총액공사","345kV 서서울-신광명#2T/L GCB 보통점검","2022-11-02 09:00","2022-11-02 18:00","취소","취소","연속"]
[9,"남서울","영등포","신광명S/S SEC CB 75760","2022~2023년 영등포P/O 변전협력회사 총액공사","345kV 75-76 GCB 보통점검","2022-11-01 09:00","2022-11-01 18:00","취소","취소","연속"]
[10,"남서울","영등포","신광명S/S CB 7372","2022~23년 영등포P/O 변전협력회사 총액공사","345kV #4M.Tr 1차 GCB 보통점검","2022-11-03 09:00","2022-11-03 18:00","취소","취소","연속"]
[11,"남서울","동서울","신성남동서울#2 T/L","동서울SS 345kV 신성남-동서울#2T/L GIS(7571) 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-11-11 09:00","2022-11-11 18:00","2022-11-11 09:00","2022-11-11 18:00","연속"]
[12,"인천","시흥","영흥1TP영흥2TP#2 T/L","345kV 신시흥-영흥T/L 정밀점검","정밀점검 - 대상 : No.1~8(8기), 영흥#1,3 및 연락#1,2T/L 공사 시행 - 영흥TP연락T/L 병가구간 작업","2022-11-01 08:00","2022-11-03 18:00","2022-11-01 08:00","2022-11-03 18:00","매일"]
[13,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S 345kV #2M.Tr 교체공사","-345kV M.Tr 철거 × 1Bank -345kV M.Tr 설치 × 1Bank -모선배선 철거 및 설치 × 1식 - 제어케이블 결선분리 및 결선 × 1식 - 접지장치 설치 × 1식","2022-11-01 09:00","2022-12-06 18:00","2022-11-01 09:00","2022-12-06 18:00","연속"]
[14,"인천","부평","신경서S/S #1 M.Tr","신경서S/S #1M.Tr 부싱절연유 채유 및 GIS 점검","신경서S/S #1M.Tr 부싱절연유 채유 및 GIS 점검(4189조작, 6144보통)","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","연속"]
[15,"인천","부평","인천C/C #1 Tie-Tr","인천C/C 6144GIS 보통점검 및 4189GIS 조작시험","인천C/C 6144GIS 보통점검 및 4189GIS 조작시험","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[16,"인천","부평","신인천C/C CB 7671","신인천S/Y 7672GIS 조작시험","신인천S/Y 7672GIS 조작시험","2022-11-04 09:00","2022-11-04 12:00","2022-11-04 09:00","2022-11-04 12:00","연속"]
[17,"인천","부평","인천C/C CB 7271","인천C/C 7271GIS 보통점검","인천C/C 7271GIS 보통점검","2022-11-04 09:00","2022-11-04 13:00","2022-11-04 09:00","2022-11-04 13:00","연속"]
[18,"인천","부평","신인천C/C SEC CB 70710","신인천S/Y 70-71 SEC GIS 보통점검","신인천S/Y 70-71 SEC GIS 보통점검","2022-11-04 12:00","2022-11-04 18:00","2022-11-04 12:00","2022-11-04 18:00","연속"]
[19,"인천","김포","신김포신인천CC T/L","345Kv 신김포-서인천CC 등 2개 T/L 추락방지시설 설치공사","추락방지시설 설치공사","2022-11-07 08:00","2022-11-11 18:00","2022-11-07 08:00","2022-11-11 18:00","연속"]
[20,"인천","부평","신인천C/C SEC CB 75760","신인천S/Y 75-76SEC GIS 보통점검 및 전자변 교체","신인천S/Y 75-76SEC GIS 보통점검 및 전자변 교체","2022-11-07 09:00","2022-11-07 18:00","2022-11-07 09:00","2022-11-07 18:00","연속"]
[21,"인천","부평","인천C/C CB 7C71","인천C/C 7C71GIS 보통점검","인천C/C 7C71GIS 보통점검","2022-11-07 09:00","2022-11-07 13:00","2022-11-07 09:00","2022-11-07 13:00","연속"]
[22,"인천","시흥","영흥T/P #75 BUS","영흥T/P 345kV 모선보호반 대체","영흥T/P 345kV 모선보호반 대체","2022-11-07 09:00","2022-11-11 18:00","2022-11-07 09:00","2022-11-11 18:00","연속"]
[23,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥#1S/S 345kV #3 M.Tr 보통점검","신시흥#1S/S 345kV #3 M.Tr 보통점검","2022-11-07 09:00","2022-11-11 18:00","2022-11-07 09:00","2022-11-11 18:00","연속"]
[24,"인천","부평","서인천C/C #4 M.Tr","서인천C/C 345kV #4 M.Tr 부싱절연유 채유 등","서인천C/C 345kV #4 M.Tr 부싱절연유 채유 6444GIS 조작, 7400GIS 보통, 7472GIS 보통 및 전자변교체 (발전소 협의 완료)","2022-11-08 09:00","2022-11-08 18:00","2022-11-08 09:00","2022-11-08 18:00","연속"]
[25,"인천","부평","인천C/C SEC CB 70710","인천C/C 70-71 SEC GIS 보통점검 및 전자변교체","인천C/C 70-71 SEC GIS 보통점검 및 전자변교체","2022-11-10 09:00","2022-11-10 18:00","2022-11-10 09:00","2022-11-10 18:00","연속"]
[26,"인천","부평","신인천C/C SEC CB 71720","신인천S/Y 71-72SEC GIS 보통점검","신인천S/Y 71-72SEC GIS 보통점검","2022-11-11 09:00","2022-11-11 13:00","2022-11-11 09:00","2022-11-11 13:00","연속"]
[27,"인천","부평","인천C/C SEC CB 75760","인천C/C 75-76 SEC GIS 보통점검 및 전자변교체","인천C/C 75-76 SEC GIS 보통점검 및 전자변교체","2022-11-11 09:00","2022-11-11 18:00","2022-11-11 09:00","2022-11-11 18:00","연속"]
[28,"인천","부평","신인천C/C SEC CB 76770","신인천S/Y 76-77SEC GIS 보통점검","신인천S/Y 76-77SEC GIS 보통점검","2022-11-11 13:00","2022-11-11 18:00","2022-11-11 13:00","2022-11-11 18:00","연속"]
[29,"인천","김포","신김포서인천CC T/L","345Kv 신김포-서인천CC 등 2개 T/L 추락방지시설 설치공사","추락방지시설 설치공사","2022-11-14 08:00","2022-11-18 18:00","2022-11-14 08:00","2022-11-18 18:00","연속"]
[30,"인천","시흥","신시흥영흥TP#1 T/L","345kV 신시흥-영흥T/L 정밀점검","정밀점검 - 대상 : No.1~8, 22~26(13기), #1,2,3,4T/L 공사 시행","2022-11-14 08:00","2022-11-23 18:00","2022-11-14 08:00","2022-11-23 18:00","매일"]
[31,"인천","부평","인천C/C CB 7B00","인천C/C 7B00GIS 보통점검 및 전자변교체","인천C/C 7B00GIS 보통점검 및 전자변교체","2022-11-14 09:00","2022-11-14 18:00","2022-11-14 09:00","2022-11-14 18:00","연속"]
[32,"인천","부평","인천C/C CB 7B71","인천C/C 7B71GIS 보통점검","인천C/C 7B71GIS 보통점검","2022-11-15 09:00","2022-11-15 18:00","2022-11-15 09:00","2022-11-15 18:00","연속"]
[33,"인천","부평","인천C/C CB 7B72","인천C/C 7B72GIS 보통점검","인천C/C 7B72GIS 보통점검","2022-11-16 09:00","2022-11-16 18:00","2022-11-16 09:00","2022-11-16 18:00","연속"]
[34,"인천","부평","신가좌신시흥#2 T/L","22~23년 가공송전 협력회사 총액공사","송전철탑 추락방지시설 설치공사(수평)","2022-11-21 08:00","2022-11-25 18:00","취소","취소","연속"]
[35,"인천","시흥","신시흥신광명#2 T/L","22~23년 가공송전 협력회사 총액공사","송전철탑 추락방지시설 설치공사(수평)","2022-11-21 08:00","2022-11-23 18:00","취소","취소","연속"]
[36,"인천","시흥","영흥1TP영흥2TP#1 T/L","345kV 신시흥-영흥T/L 정밀점검","정밀점검 - 대상 : No.1~8(8기), 영흥#1,3 및 연락#1,2T/L 공사 시행 - 영흥TP연락T/L 병가구간 작업","2022-11-21 08:00","2022-11-23 18:00","2022-11-21 08:00","2022-11-23 18:00","매일"]
[37,"인천","김포","신김포S/S CB 7100","신김포S/S 362kV 7100 개폐제어기 설치공사","신김포S/S 362kV 7100 개폐제어기 설치공사","2022-11-21 09:00","2022-11-26 18:00","2022-11-21 09:00","2022-11-26 18:00","연속"]
[38,"인천","김포","신김포S/S CB 7171","신김포S/S 362kV 7100 개폐제어기 설치공사 관련 휴전","신김포S/S 362kV 7100 개폐제어기 설치공사 관련 휴전","2022-11-21 09:00","2022-11-26 18:00","2022-11-21 09:00","2022-11-26 18:00","매일"]
[39,"인천","부평","인천C/C CB 7A72","인천복합S/Y 7A72GIS 보통점검 및 전자변 교체","인천복합S/Y 7A72GIS 보통점검 및 전자변 교체","2022-11-21 09:00","2022-11-21 18:00","2022-11-21 09:00","2022-11-21 18:00","연속"]
[40,"인천","부평","신경서S/S CB 7571","신경서S/S 7571GIS 보통점검 및 전자변 교체","신경서S/S 7571GIS 보통점검 및 전자변 교체","2022-11-22 09:00","2022-11-22 18:00","2022-11-22 09:00","2022-11-22 18:00","연속"]
[41,"인천","부평","인천C/C CB 7471","인천복합S/Y 7471GIS 보통점검 및 전자변 교체","인천복합S/Y 7471GIS 보통점검 및 전자변 교체","2022-11-23 09:00","2022-11-23 18:00","2022-11-23 09:00","2022-11-23 18:00","연속"]
[42,"인천","김포","신김포S/S CB 7272","신김포S/S 362kV 7200 개폐제어기 설치공사 관련 휴전","신김포S/S 362kV 7200 개폐제어기 설치공사 관련 휴전","2022-11-28 09:00","2022-12-03 18:00","2022-11-28 09:00","2022-12-03 18:00","매일"]
[43,"인천","김포","신김포S/S CB 7271","신김포S/S 362kV 7200 개폐제어기 설치공사 관련 휴전","신김포S/S 362kV 7200 개폐제어기 설치공사 관련 휴전","2022-11-28 09:00","2022-12-03 18:00","2022-11-28 09:00","2022-12-03 18:00","매일"]
[44,"인천","김포","신김포S/S CB 7200","신김포S/S 362kV 7200 개폐제어기 설치공사","신김포S/S 362kV 7200 개폐제어기 설치공사","2022-11-28 09:00","2022-12-03 18:00","2022-11-28 09:00","2022-12-03 18:00","연속"]
[45,"경기북부","고양","신파주신덕은#2 T/L","2022년도 고양전력지사 362kV GIS 정밀점검공사","7200 GIS 정밀점검","2022-11-01 09:00","2022-11-04 18:00","2022-11-14 09:00","2022-11-16 18:00","연속"]
[46,"경기북부","고양","신덕은S/S #3 M.Tr","22년 고양P/O 변전협력 총액공사","#3M.Tr 상부 안전 난간대 설치","2022-11-14 09:00","2022-11-14 18:00","2022-11-18 09:00","2022-11-18 18:00","연속"]
[47,"경기북부","고양","신덕은S/S #2 M.Tr","2022년도 고양전력지사 362kV GIS 정밀점검공사","7272 GIS 정밀점검","2022-11-07 09:00","2022-11-11 18:00","2022-11-07 09:00","2022-11-16 18:00","연속"]
[48,"경기북부","고양","신파주S/S #4 M.Tr","22년 고양P/O 변전협력 총액공사","#4M.Tr 상부 안전 난간대 설치","2022-11-18 09:00","2022-11-18 18:00","2022-11-18 09:00","2022-11-18 18:00","연속"]
[49,"경기북부","고양","신파주양주#2 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","추락방지시설,피뢰기 설치공사","2022-11-08 07:00","2022-11-16 18:00","2022-11-01 07:00","2022-11-09 18:00","연속"]
[50,"경기북부","고양","신파주양주#1 T/L","고양전력지사 관내T/L OPGW 항공장애표시구 설치공사 2차","345kV 신파주-양주#1T/L OPGW 6경간 24개 항공구 설치","2022-11-21 07:00","2022-11-23 18:00","2022-11-21 07:00","2022-11-23 18:00","연속"]
[51,"경기북부","구리","미금S/S #1 Sh.R CB","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV #1Sh.R 7179 GIS 보통점검","2022-11-08 09:00","2022-11-08 18:00","2022-11-08 09:00","2022-11-08 18:00","연속"]
[52,"경기북부","구리","미금/SS #6 Sh.R CB","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV #6Sh.R 7679 GIS 보통점검","2022-11-24 09:00","2022-11-24 18:00","2022-11-24 09:00","2022-11-24 18:00","연속"]
[53,"경기북부","구리","미금S/S CB 7572","2022~23 구리전력 변전협력 총액공사","미금S/S 미금-성동#3T/L GIS 보통점검공사 ( 7572 GIS )","2022-11-16 09:00","2022-11-16 18:00","2022-11-16 09:00","2022-11-16 18:00","연속"]
[54,"경기북부","구리","미금S/S CB 7671","2022~23 구리전력 변전협력 총액공사","미금S/S 신의정부-미금#1T/L 7671 GIS 보통점검","2022-11-28 09:00","2022-11-28 18:00","2022-11-28 09:00","2022-11-28 18:00","연속"]
[55,"경기북부","구리","미금S/S #4 Sh.R CB","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV #4Sh.R 7479 GIS 보통점검","2022-11-07 09:00","2022-11-07 18:00","2022-11-07 09:00","2022-11-07 18:00","연속"]
[56,"경기북부","구리","미금S/S #2 M.Tr","22~23년 구리전력 변전협력 총액공사","미금S/S 345kV #2M.Tr 보통점검, H0부싱 교체","2022-11-01 09:00","2022-11-08 18:00","2022-11-01 09:00","2022-11-08 18:00","연속"]
[57,"경기북부","구리","미금S/S STATCOM CB","미금S/S 345kV STATCOM 냉각설비 점검","미금S/S 345kV STATCOM 냉각설비 점검 및 회로보완","2022-11-07 09:00","2022-11-11 18:00","2022-11-07 09:00","2022-11-11 18:00","연속"]
[58,"경기북부","구리","신가평S/S CB 7600","2022~23 구리전력 변전협력 총액공사","신가평S/S #4Sh.R - 신의정부#1T/L TIE GIS (7600) 보통점검","2022-11-15 09:00","2022-11-15 18:00","2022-11-15 09:00","2022-11-15 18:00","연속"]
[59,"경기북부","구리","신가평S/S CB 7371","2022~23 구리전력 변전협력 총액공사","신가평S/S #2Sh.R 7371 GIS 보통점검, 7379 GIS 개폐타임 측정","2022-11-30 09:00","2022-11-30 18:00","2022-11-30 09:00","2022-11-30 18:00","연속"]
[60,"경기북부","구리","신가평S/S CB 7300","2022~23 구리전력 변전협력 총액공사","신가평S/S #2Sh.R 7371 GIS 보통점검, 7379 GIS 개폐타임 측정","2022-11-30 09:00","2022-11-30 18:00","2022-11-30 09:00","2022-11-30 18:00","연속"]
[61,"경기북부","구리","신가평S/S #2 Sh.R CB","2022~23 구리전력 변전협력 총액공사","신가평S/S #2Sh.R 7371 GIS 보통점검, 7379 GIS 개폐타임 측정","2022-11-30 09:00","2022-11-30 18:00","2022-11-30 09:00","2022-11-30 18:00","연속"]
[62,"경기북부","구리","신가평S/S CB 7672","2022~23 구리전력 변전협력 총액공사","신가평S/S 신가평-신의정부#1T/L GIS (7672) 보통점검","2022-11-14 09:00","2022-11-14 18:00","2022-11-14 09:00","2022-11-14 18:00","연속"]
[63,"경기북부","구리","신가평S/S CB 7572","2022~23 구리전력 변전협력 총액공사","신가평S/S 신가평-신의정부#2T/L GIS (7572) 보통점검","2022-11-21 09:00","2022-11-21 18:00","2022-11-21 09:00","2022-11-21 18:00","연속"]
[64,"경기북부","구리","신가평S/S CB 7372","2022~23 구리전력 변전협력 총액공사","신가평S/S 신가평-포천LNGCC#2T/L 73732 GIS 보통점검","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[65,"경기북부","구리","신포천포천CC#1 T/L","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-포천CC#1T/L 단상재폐로 결상회로 개선 7371 GIS 보통점검","2022-11-09 09:00","2022-11-09 18:00","취소","취소","연속"]
[66,"경기북부","구리","신포천포천CC#2 T/L","2022~23 구리전력 변전협력 총액공사","신포천S/S 신포천-포천CC#2T/L 단상재폐로 결상회로 개선","2022-11-10 09:00","2022-11-10 18:00","취소","취소","연속"]
[67,"경기북부","직할","신포천동두천CC#2 T/L","2022-2023년 경기북부 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7671 보통점검","2022-11-15 09:00","2022-11-15 18:00","2022-11-15 09:00","2022-11-15 18:00","연속"]
[68,"경기북부","직할","동두천C/C CB 7472","2022-2023년 경기북부 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7400, 7472 보통점검","2022-11-09 09:00","2022-11-10 18:00","2022-11-09 09:00","2022-11-10 18:00","연속"]
[69,"경기북부","직할","동두천C/C CB 7400","2022-2023년 경기북부 직할 변전협력회사 총액공사","동두천CC 362kV GIS 7400, 7472 보통점검","2022-11-09 09:00","2022-11-10 18:00","2022-11-09 09:00","2022-11-10 18:00","연속"]
[70,"경기북부","직할","신의정부S/S #4 M.Tr","22-23년 직할 변전 협력 총액 공사","#4M.Tr 보호반 보호계전기 CPU 모듈 교체","2022-11-03 10:00","2022-11-03 17:00","2022-11-30 10:00","2022-11-30 17:00","연속"]
[71,"경기북부","직할","양주S/S CB 7672","2022-2023년 경기북부 직할 변전협력회사 총액공사","양주S/S 362kV GIS 7672, 7479 CB 초기점검","2022-11-21 09:00","2022-11-23 18:00","2022-11-21 09:00","2022-11-23 18:00","연속"]
[72,"경기북부","직할","양주S/S #4 Sh.R CB","2022-2023년 경기북부 직할 변전협력회사 총액공사","양주S/S 362kV GIS 7672, 7479 CB 초기점검","2022-11-21 09:00","2022-11-23 18:00","2022-11-21 09:00","2022-11-23 18:00","연속"]
[73,"경기북부","직할","양주S/S CB 7600","2022-2023년 경기북부 직할 변전협력회사 총액공사","양주S/S 362kV GIS 7672, 7479 CB 초기점검","2022-11-21 09:00","2022-11-23 18:00","2022-11-21 09:00","2022-11-23 18:00","연속"]
[74,"경기북부","직할","양주S/S #4 M.Tr","22-23년 경기북부 직할 변전협력회사 총액공사","양주S/S 345kV #4M.Tr 정밀점검","2022-11-01 09:00","2022-11-07 18:00","취소","취소","연속"]
[75,"경기북부","직할","양주S/S #2 M.Tr","'22-23년 경기북부 직할 변전정비 총액공사","- 345kV #2M.Tr A상 2차 부싱 절연유 분석 이상에 따른 추적관리","2022-11-21 08:00","2022-11-22 18:00","2022-11-21 08:00","2022-11-22 18:00","연속"]
[76,"경기","군포","서서울S/S #1 M.Tr","서서울S/S 23kV Sh.C 철거공사","서서울S/S #1M.Tr 3차측 Main VCB 철거 서서울S/S #1M.Tr 3차 #1-1,2 Sh.R 대체","2022-11-09 09:00","2022-11-10 18:00","2022-11-17 09:00","2022-11-18 18:00","연속"]
[77,"경기","군포","서서울S/S #2 M.Tr","서서울S/S 23kV Sh.C 철거공사","서서울S/S #2M.Tr 3차측 Main VCB 철거","2022-11-07 09:00","2022-11-08 18:00","2022-11-16 09:00","2022-11-16 18:00","연속"]
[78,"경기","군포","서서울S/S #3 M.Tr","서서울S/S 23kV Sh.C 철거공사","서서울S/S #3M.Tr 3차측 Main VCB 철거 #3-1 Sh.R VCB 대체공사(병행)","2022-11-14 09:00","2022-11-15 18:00","2022-11-14 09:00","2022-11-15 18:00","연속"]
[79,"경기","군포","서서울신광명#2 T/L","서서울신광명#2 T/L 결상회로 개선, CVT 및 LA 보통점검","서서울신광명#2 T/L 결상회로 개선, CVT 및 LA 보통점검","2022-11-07 09:00","2022-11-07 18:00","취소","취소","연속"]
[80,"경기","군포","서서울S/S CB 7772","서서울S/S 345kV 신온양-서서울#2T/L CB(7772) 보통점검","서서울S/S 345kV 신온양-서서울#2T/L CB(7772) 보통점검","2022-11-18 10:00","2022-11-18 18:00","2022-11-18 10:00","2022-11-18 18:00","연속"]
[81,"경기","군포","서서울S/S CB 7472","서서울S/S 345kV 신온양-서서울#1T/L CB(7472) 보통점검","서서울S/S 345kV 신온양-서서울#1T/L CB(7472) 보통점검","2022-11-16 10:00","2022-11-16 18:00","2022-11-16 10:00","2022-11-16 18:00","연속"]
[82,"경기","군포","서서울#2신시흥#2 T/L","철탑 추락방지장치 설치공사","철탑 추락방지장치 설치공사","2022-11-15 07:00","2022-11-16 18:00","2022-11-14 07:00","2022-11-15 18:00","연속"]
[83,"경기","동부","곤지암S/S CB 7671","345kV 곤지암S/S SK하이닉스 신규수용공사","7671GIS 전력케이블 접속","2022-11-03 15:00","2022-11-14 18:00","2022-11-03 15:00","2022-11-14 18:00","연속"]
[84,"경기","동부","곤지암S/S CB 7600","345kV 곤지암S/S SK하이닉스 신규수용공사","7671GIS 전력케이블 접속","2022-11-03 15:00","2022-11-14 18:00","2022-11-03 15:00","2022-11-14 18:00","연속"]
[85,"경기","동부","곤지암신충주#2 T/L","여주복합발전소 연계선로 본선로 건설공사","4회선 2기 신설","2022-11-15 07:00","2022-11-28 18:00","2022-11-15 07:00","2022-11-28 18:00","연속"]
[86,"경기","동부","곤지암신충주#1 T/L","여주복합발전소 연계선로 본선로 건설공사","4회선 2기 신설","2022-11-01 07:00","2022-11-14 18:00","2022-11-01 07:00","2022-11-14 18:00","연속"]
[87,"경기","동부","곤지암S/S #1 M.Tr","22년 동부 변전정비 총액공사","곤지암:#1M.Tr 3차 A,B,C LA 대체 #1M.Tr 컨서베이터 배관 누유확인 (2일소요)(~23) [설비보강부 병행가능?]","2022-11-15 09:30","2022-11-15 18:00","2022-11-22 09:00","2022-11-23 18:00","연속"]
[88,"경기","동부","곤지암S/S #4 M.Tr","22년 동부 변전정비 총액공사","곤지암:#4M.Tr(하자),6444(하자) #4M.Tr2차LA(하자)? 곤지암:#4M.Tr(~22)(CVT 설치)","2022-11-10 09:30","2022-11-11 18:00","2022-11-10 09:30","2022-11-11 18:00","연속"]
[89,"경기","동부","곤지암S/S #2 M.Tr","22년 동부 변전정비 총액공사","곤지암:#2M.Tr 3차 A,B,C LA 대체 - B상 누설전류계 교체","2022-11-30 09:30","2022-11-30 18:00","2022-11-30 09:30","2022-11-30 18:00","연속"]
[90,"경기","동부","곤지암S/S #3 M.Tr","22년 동부 변전정비 총액공사","곤지암:#2M.Tr 3차 A,B,C LA 대체 - B상 누설전류계 교체","2022-11-02 09:30","2022-11-02 18:00","2022-11-02 09:30","2022-11-02 18:00","연속"]
[91,"경기","성남","신안성신성남#1 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치시설 설치공사","345V 신안성-신성남T/L No.63~93(신용인-동서울 병행 4회선구간) 총 21기 시행(기설치 및 지장이설 공사구간 제외)","2022-11-24 07:30","2022-12-02 18:00","2022-11-24 07:30","2022-12-02 18:00","연속"]
[92,"경기","성남","신안성신성남#2 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치시설 설치공사","345V 신안성-신성남T/L No.63~93(신용인-동서울 병행 4회선구간) 총 21기 시행(기설치 및 지장이설 공사구간 제외)","2022-11-18 07:30","2022-11-23 18:00","2022-11-18 07:30","2022-11-23 18:00","연속"]
[93,"경기","성남","신성남동서울#2 T/L","2022년 성남전력지사 변전협력회사 총액공사","- 7371,7300 조작시험 - CVT 대체(A,C상)","2022-11-10 09:00","2022-11-10 18:00","2022-11-10 09:00","2022-11-10 18:00","연속"]
[94,"경기","성남","신성남동서울#1 T/L","2022년 성남전력지사 변전협력회사 총액공사","- 7471,7400 조작시험 - CVT 대체(B,C상)","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[95,"경기","성남","신성남S/S CB 7272","2022년 성남전력지사 변전협력회사 총액공사","- 7272 조작시험","2022-11-04 09:00","2022-11-04 18:00","2022-11-04 09:00","2022-11-04 18:00","연속"]
[96,"경기","성남","신안성S/S CB 7971","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","연속"]
[97,"경기","성남","신안성신성남#1 T/L","2022-2023년 성남전력지사 가공송전 정비회사 총액공사","- 볼트리스형 스페이서댐퍼 교체 (6개 구간)","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","매일"]
[98,"경기","성남","신안성서안성#1 T/L","2022년 성남전력지사 변전협력회사 총액공사","- 7C B/F 대체","2022-11-08 09:00","2022-11-16 18:00","2022-11-08 09:00","2022-11-16 18:00","연속"]
[99,"경기","성남","신안성신용인#1 T/L","2022-2023년 성남전력지사 가공송전 정비회사 총액공사","- 볼트리스형 스페이서댐퍼 교체 (6개 구간)","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","매일"]
[100,"경기","성남","신안성S/S CB 7900","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-11-02 09:00","2022-11-02 18:00","2022-11-02 09:00","2022-11-02 18:00","연속"]
[101,"경기","성남","신안성S/S CB 7972","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[102,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울T/L No.53 지장철탑 이설공사(서울세종)","서울세종 고속도로 개설관련 지장철탑 이설공사(요청자 부담 공사) - 본선로 구성 시행(1기 철거 1기 신설) - 시공업체 : 신우전설(주), 감리업체 : (주)동성기술감리단","2022-11-24 07:30","2022-12-02 18:00","2022-11-24 07:30","2022-12-02 18:00","연속"]
[103,"경기","성남","신용인S/S #4 M.Tr","170kV 효성제 GIS 스프링 조작기 교체공사","- 스프링 조작기 교체","2022-11-10 09:00","2022-11-11 18:00","2022-11-10 09:00","2022-11-11 18:00","연속"]
[104,"경기","성남","신용인S/S #2 BUS","2022년 성남전력지사 변전협력회사 총액공사","- PT케이블 포설 및 결선","2022-11-09 14:00","2022-11-09 18:00","2022-11-09 14:00","2022-11-09 18:00","연속"]
[105,"경기","성남","신용인S/S #1 BUS","2022년 성남전력지사 변전협력회사 총액공사","- PT케이블 포설 및 결선","2022-11-09 09:00","2022-11-09 14:00","2022-11-09 09:00","2022-11-09 14:00","연속"]
[106,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울T/L No.53 지장철탑 이설공사(서울세종)","서울세종 고속도로 개설관련 지장철탑 이설공사(요청자 부담 공사) - 본선로 구성 시행(1기 철거 1기 신설) - 시공업체 : 신우전설(주), 감리업체 : (주)동성기술감리단","2022-11-14 07:30","2022-11-23 18:00","2022-11-14 07:30","2022-11-23 18:00","연속"]
[107,"경기","직할","화성서서울#1 T/L","345kV 화성S/S GIS 용량대체","76Bay UHF 센서 위치이동","2022-11-07 09:00","2022-11-10 18:00","2022-11-08 09:00","2022-11-11 18:00","연속"]
[108,"경기","직할","화성신평택CC#1 T/L","22-23년 군포전력 가공송전협력회사 총액공사","철탑추락방지장치 설치공사(42기) - 11/17(수능) 작업제외","2022-11-14 07:00","2022-11-18 18:00","2022-11-14 07:00","2022-11-18 18:00","연속"]
[109,"경기","직할","화성S/S #2 M.Tr","화성S/S 154kV 장기사용 GIS 교체공사(4차)","1DS, CB 등 GIS 대체 안전이격거리 확보","2022-11-21 09:00","2022-11-27 18:00","2022-11-21 09:00","2022-11-27 18:00","연속"]
[110,"경기","직할","화성S/S #2 M.Tr","화성S/S 154kV 장기사용 GIS 교체공사(4차)","#60-61BUS SEC 분리 안전이격거리","2022-11-12 09:00","2022-11-15 18:00","2022-11-12 09:00","2022-11-15 18:00","연속"]
[111,"경기","직할","화성S/S #71 BUS","345kV 화성S/S GIS 용량대체","7951 DS 가스누기 보수","2022-11-14 09:00","2022-11-18 18:00","2022-11-14 09:00","2022-11-18 18:00","연속"]
[112,"경기","직할","화성S/S #2 M.Tr","화성S/S 154kV 장기사용 GIS 교체공사(4차)","#65-66BUS SEC분리 안전이격거리","2022-11-01 09:00","2022-11-03 18:00","2022-11-01 09:00","2022-11-03 18:00","연속"]
[113,"경기","직할","화성신안산#1 T/L","2022-23 경기본부 직할변전협력회사 총액공사","GIS 하자점검 등","2022-11-02 09:00","2022-11-02 18:00","2022-11-02 09:00","2022-11-02 18:00","연속"]
[114,"경기","직할","화성신평택CC#2 T/L","22-23년 군포전력 가공송전협력회사 총액공사","철탑추락방지장치 설치공사(42기)","2022-11-21 07:00","2022-11-24 18:00","2022-11-21 07:00","2022-11-24 18:00","연속"]
[115,"경기","평택","고덕#2S/S #2 M.Tr","345kV 고덕#2S/S 건설공사","종합예방진단시스템 설치","2022-11-21 09:00","2022-11-25 18:00","2022-11-21 09:00","2022-11-25 18:00","연속"]
[116,"경기","평택","고덕#2S/S #1 M.Tr","345kV 고덕#2S/S 건설공사","종합예방진단시스템 설치","2022-11-14 09:00","2022-11-18 18:00","2022-11-14 09:00","2022-11-18 18:00","연속"]
[117,"경기","평택","고덕고덕2#2 T/L","345kV 고덕#2S/S 건설공사","#3M.Tr 무부하가압","2022-11-08 09:00","2022-11-09 18:00","2022-11-10 09:00","2022-11-11 18:00","연속"]
[118,"경기","평택","고덕#2S/S #1 BUS","345kV 고덕#2S/S 건설공사","#3M.Tr 무부하가압","2022-11-08 09:00","2022-11-09 18:00","2022-11-10 09:00","2022-11-11 18:00","연속"]
[119,"경기","평택","고덕S/S #2 M.Tr","일진제 170kV GIS 인출DS 인터록 개선","고덕S/S #2M.Tr 2차 GIS 인출 DS 인터록 개선","2022-11-10 14:00","2022-11-10 18:00","2022-11-10 14:00","2022-11-10 18:00","연속"]
[120,"경기","평택","고덕S/S STATCOM CB","고덕S/S 345kV STATCOM 점검공사","STATCOM 밸브, 제어기 및 관련 변전설비(M.Tr, GIS) 점검","2022-10-24 09:00","2022-11-11 18:00","2022-11-07 09:00","2022-11-25 18:00","연속"]
[121,"경기","평택","고덕S/S #1 M.Tr","일진제 170kV GIS 인출DS 인터록 개선","고덕S/S #1M.Tr 2차 GIS 인출DS 인터록 개선","2022-11-10 09:00","2022-11-10 14:00","2022-11-10 09:00","2022-11-10 14:00","연속"]
[122,"경기","평택","서안성신진천#1 T/L","(2공구)세종-포천간 도로개설 관련 지장철탑 이설공사","2기 신설, 1기 임시","2022-11-05 09:00","2022-11-10 18:00","2022-11-05 09:00","2022-11-10 18:00","연속"]
[123,"경기","평택","서안성신진천#2 T/L","(2공구)세종-포천간 도로개설 관련 지장철탑 이설공사","2기 신설, 1기 임시","2022-11-01 07:00","2022-11-04 18:00","2022-11-01 07:00","2022-11-04 18:00","연속"]
[124,"경기","평택","서안성신진천#2 T/L","(2공구)세종-포천간 도로개설 관련 지장철탑 이설공사","2기 신설, 1기 임시","2022-11-18 09:00","2022-11-24 18:00","2022-11-18 09:00","2022-11-24 18:00","연속"]
[125,"경기","평택","평택T/P #2 CLR #7677 CB","22년 평택전력지사 변전협력회사 총액공사","신평택C/C 7677 GIS 보통점검 및 염해방지 코팅","2022-11-15 09:00","2022-11-15 18:00","2022-11-15 09:00","2022-11-15 18:00","연속"]
[126,"경기","평택","평택T/P #2 CLR #7577 CB","22년 평택전력지사 변전협력회사 총액공사","신평택C/C 7577 GIS 보통점검 및 염해방지 코팅","2022-11-15 09:00","2022-11-15 18:00","2022-11-15 09:00","2022-11-15 18:00","연속"]
[127,"경기","평택","평택T/P #1 CLR #7077 CB","22년 평택전력지사 변전협력회사 총액공사","신평택C/C 7077 GIS 보통점검 및 염해방지 코팅","2022-11-14 09:00","2022-11-14 18:00","2022-11-14 09:00","2022-11-14 18:00","연속"]
[128,"경기","평택","평택T/P #1 CLR #7177 CB","22년 평택전력지사 변전협력회사 총액공사","신평택C/C 7177 GIS 보통점검 및 염해방지 코팅","2022-11-14 09:00","2022-11-14 18:00","2022-11-14 09:00","2022-11-14 18:00","연속"]
[129,"경기","평택","평택T/P SEC CB 70710","22년 평택전력지사 변전협력회사 총액공사","신평택C/C 362kV 70-71 SEC GIS 보통점검","2022-11-07 10:00","2022-11-07 18:00","2022-11-07 10:00","2022-11-07 18:00","연속"]
[130,"경기","평택","평택T/P SEC CB 75760","22년 평택전력지사 변전협력회사 총액공사","신평택C/C 362kV 75-76 SEC GIS 보통점검","2022-11-08 10:00","2022-11-08 18:00","2022-11-08 10:00","2022-11-08 18:00","연속"]
[131,"강원","동해","동해S/S CB 7672","22년 동해전력지사 변전정비팀 총액공사","장기미동작 차단기 조작시험","2022-11-08 14:00","2022-11-08 18:00","2022-11-08 14:00","2022-11-08 18:00","연속"]
[132,"강원","동해","동해S/S CB 7572","22년 동해전력지사 변전정비팀 총액공사","장기미동작 차단기 조작시험","2022-11-08 09:00","2022-11-08 14:00","2022-11-08 09:00","2022-11-08 14:00","연속"]
[133,"강원","동해","동해S/S CB 7372","22년 동해전력지사 변전정비팀 총액공사","장기미동작 차단기 조작시험","2022-11-07 14:00","2022-11-07 18:00","2022-11-07 14:00","2022-11-07 18:00","연속"]
[134,"강원","동해","동해S/S CB 7272","22년 동해전력지사 변전정비팀 총액공사","장기미동작 차단기 조작시험","2022-11-07 09:00","2022-11-07 14:00","2022-11-07 09:00","2022-11-07 14:00","연속"]
[135,"강원","동해","삼척GP한울NP #2 T/L","2022~23년 동해전력지사 가공송전 협력회사 총액공사","345kV 삼척GP-한울NP1#2T/L 산불경과지역 불량애자개소 절연저항 측정 및 교체","2022-11-10 07:00","2022-11-14 18:00","취소","취소","매일"]
[136,"강원","동해","삼척GP한울NP #1 T/L","2022~23년 동해전력지사 가공송전 협력회사 총액공사","345kV 삼척GP-한울NP1#1T/L 산불경과지역 불량애자개소 절연저항 측정 및 교체","2022-11-07 07:00","2022-11-09 18:00","취소","취소","매일"]
[137,"강원","태백","신태백S/S #1 BUS","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #1BUS B/P PNL 교체","2022-11-21 10:00","2022-11-25 18:00","2022-11-21 10:00","2022-11-25 18:00","연속"]
[138,"강원","태백","신태백S/S #2 BUS","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #2BUS B/P PNL 교체","2022-11-28 10:00","2022-12-02 18:00","2022-11-28 10:00","2022-12-02 18:00","연속"]
[139,"강원","태백","신태백한울NP #1 T/L","345kV 울태T/L 고정형 폴리머점퍼지지애자 설치공사","- 345kV 신태백-한울NP2T/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사 - 345kV 신태백-한울NP2#1T/L 정밀점검 - 신태백S/S 345kV 75Bay B/F PNL 교체 11/07 ~ 11/11(병행)","2022-11-07 09:00","2022-11-13 18:00","취소","취소","연속"]
[140,"강원","태백","신태백S/S #3 Sh.R CB","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV 75Bay B/F PNL 교체(11/7 ~ 11/11) 신태백S/S 345kV #3Sh.R 유중가스 발생원인 분석 및 점검공사(11/7 ~ 11/11)","2022-11-07 10:00","2022-11-11 18:00","2022-11-07 10:00","2022-11-11 18:00","연속"]
[141,"강원","태백","신태백한울NP #2 T/L","345kV 울태T/L 고정형 폴리머점퍼지지애자 설치공사","- 345kV 신태백-한울NP2T/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사 - 345kV 신태백-한울NP2#2T/L 정밀점검 - 신태백S/S 345kV 76Bay B/F PNL 교체 11/14 ~ 11/18 (병행)","2022-11-14 09:00","2022-11-20 18:00","취소","취소","연속"]
[142,"강원","태백","신태백S/S CB 7571","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV 75Bay B/F PNL 교체 (11/7 ~ 11/11) 신태백S/S 345kV #3Sh.R 유중가스 발생원인 분석 및 점검공사(11/7 ~ 11/11)","2022-11-07 10:00","2022-11-11 18:00","2022-11-07 10:00","2022-11-11 18:00","연속"]
[143,"충북","청주","남청주S/S #4 M.Tr","남청주S/S 345kV 장기사용 GIS 교체공사","78BAY 보호반 대체","2022-11-26 07:00","2022-11-27 18:00","취소","취소","연속"]
[144,"충북","청주","남청주S/S CB 7800","남청주S/S 345kV 장기사용 GIS 교체공사","7871 CB 설치","2022-11-21 09:00","2022-12-04 18:00","취소","취소","연속"]
[145,"충북","청주","세종남청주#1 T/L","남청주S/S 345kV 장기사용 GIS 교체공사","송전선로 인출 변경","2022-10-31 09:00","2022-11-04 18:00","취소","취소","연속"]
[146,"충북","청주","남청주S/S #3 M.Tr","남청주S/S 345kV 장기사용 GIS 교체공사","76 BAY 2CB 철거 3CB 설치","2022-11-05 09:00","2022-11-06 18:00","취소","취소","연속"]
[147,"충북","청주","신중부남청주#1 T/L","남청주S/S 345kV 장기사용 GIS 교체공사","송전선로 인출 변경","2022-11-21 09:00","2022-11-25 18:00","취소","취소","연속"]
[148,"충북","청주","세종남청주#2 T/L","남청주S/S 345kV 장기사용 GIS 교체공사","송전선로 인출 변경","2022-11-07 09:00","2022-11-11 18:00","취소","취소","연속"]
[149,"충북","청주","신중부남청주#2 T/L","남청주S/S 345kV 장기사용 GIS 교체공사","송전선로 인출 변경","2022-11-14 09:00","2022-11-18 18:00","취소","취소","연속"]
[150,"충북","청주","남청주S/S #3 M.Tr","남청주S/S 345kV 장기사용 GIS 교체공사","76 BAY 2CB 철거 3CB 설치","2022-11-19 09:00","2022-11-21 08:00","취소","취소","연속"]
[151,"충북","청주","세종남청주#1 T/L","남청주S/S 345kV 장기사용 GIS 교체공사","7672 무부하가압","2022-11-20 08:00","2022-11-21 08:00","취소","취소","연속"]
[152,"충북","청주","남청주S/S CB 7672","남청주S/S 345kV 장기사용 GIS 교체공사","76 BAY 2CB 철거 3CB 설치","2022-11-07 09:00","2022-11-21 08:00","취소","취소","연속"]
[153,"충북","청주","신옥천S/S #3 M.Tr","22~23년 청주전력지사 변전협력회사 총액공사","[22-23 청주전력 변전정비 총액공사] 신옥천S/S #2S.Tr 대체","2022-11-14 10:00","2022-11-16 18:00","2022-11-14 10:00","2022-11-16 18:00","연속"]
[154,"충북","청주","신옥천S/S #1 M.Tr","신옥천S/S #1M.Tr 2차측 GIS DS부 점검","신옥천S/S #1M.Tr DS부 상대표시창불량 점검","2022-11-22 10:00","2022-11-23 18:00","2022-11-22 10:00","2022-11-23 18:00","연속"]
[155,"충북","청주","신옥천S/S #2 M.Tr","345kV M.Tr 보통점검","[22-23 청주전력 변전정비 총액공사] 신옥천S/S 345kV #2M.Tr(예비) 보통점검, #1S.Tr 대체","2022-11-08 10:00","2022-11-10 18:00","2022-11-08 10:00","2022-11-10 18:00","연속"]
[156,"충북","청주","신옥천세종#1 T/L","22년 가공송전 순시점검 위탁공사","345kV 신옥천-세종#1 No.1.1 과열개소 계획정비","2022-11-14 09:00","2022-11-14 18:00","2022-11-14 09:00","2022-11-14 18:00","연속"]
[157,"충북","충주","신제천신영주#1 T/L","2022년 충주전력지사 가공송전 순시점검 위탁공사","345kV 신제천-신영주#1T/L No.1~80 정밀점검","2022-11-01 09:00","2022-11-09 18:00","취소","취소","매일"]
[158,"충북","충주","신제천신영주#2 T/L","2022년 충주전력지사 가공송전 순시점검 위탁공사","345kV 신제천-신영주#2T/L No.1~80 정밀점검","2022-11-10 09:00","2022-11-18 18:00","취소","취소","매일"]
[159,"충북","충주","신충주S/S #1 M.Tr","345kV 신충주S/S 종합예방진단시스템 구축공사","○ 신충주S/S 종합예방진단시스템 구축 - 부싱진단장비 설치, OLTC 진단장비 설치 등 ○ 정비파트 병행 작업 - #1M.Tr 보호반대체","2022-11-14 09:00","2022-11-16 18:00","취소","취소","연속"]
[160,"충북","충주","신충주S/S #3 M.Tr","345kV 신충주S/S 종합예방진단시스템 구축공사","○ 신충주S/S 종합예방진단시스템 구축 - 부싱진단장비 설치, OLTC 진단장비 설치 등 ○ 정비파트 병행 작업 - #3M.Tr 1,2차 부싱 절연유 채유","2022-11-21 09:00","2022-11-23 14:00","취소","취소","연속"]
[161,"충북","충주","신충주S/S #4 M.Tr","345kV 신충주S/S 종합예방진단시스템 구축공사","○ 신충주S/S 종합예방진단시스템 구축 - 부싱진단장비 설치, OLTC 진단장비 설치 등 ○ 정비파트 병행 작업 - #4M.Tr 1,2차 부싱 절연유 채유","2022-11-23 14:00","2022-11-25 18:00","취소","취소","연속"]
[162,"충북","충주","신충주S/S #2 M.Tr","345kV 신충주S/S 종합예방진단시스템 구축공사","○ 신충주S/S 종합예방진단시스템 구축 - 부싱진단장비 설치, OLTC 진단장비 설치 등 ○ 정비파트 병행 작업 - #2M.Tr 보호반대체","2022-11-09 09:00","2022-11-11 18:00","취소","취소","연속"]
[163,"충북","충주","신제천신충주#1 T/L","'22~'23년 충주전력지사 송전 협력회사 총액공사","동해안 발전제약완화 345kV 신충주 분기선로 변경 345kV 신충주분기T/L 124호 직결","2022-11-07 07:00","2022-11-14 18:00","2022-11-07 07:00","2022-11-14 18:00","연속"]
[164,"충북","직할","신중부S/S #5 Sh.R CB","신중부변전소 345kV GIS DS Pin 교체공사","PD발생 개선을 위한 Pin 교체작업","2022-11-23 09:00","2022-11-24 18:00","2022-11-23 09:00","2022-11-24 18:00","연속"]
[165,"충북","직할","신중부S/S CB 7A71","신중부변전소 345kV GIS DS Pin 교체공사","PD발생 개선을 위한 Pin 교체작업","2022-11-23 09:00","2022-11-24 18:00","2022-11-23 09:00","2022-11-24 18:00","연속"]
[166,"충북","직할","신중부S/S CB 7A00","신중부변전소 345kV GIS DS Pin 교체공사","PD발생 개선을 위한 Pin 교체작업","2022-11-23 09:00","2022-11-24 18:00","2022-11-23 09:00","2022-11-24 18:00","연속"]
[167,"충북","직할","신중부S/S #6 Sh.R CB","신중부변전소 345kV GIS DS Pin 교체공사","PD발생 개선을 위한 Pin 교체작업","2022-11-28 09:00","2022-11-29 18:00","2022-11-28 09:00","2022-11-29 18:00","연속"]
[168,"충북","직할","신중부S/S CB 7C71","신중부변전소 345kV GIS DS Pin 교체공사","PD발생 개선을 위한 Pin 교체작업","2022-11-28 09:00","2022-11-29 18:00","2022-11-28 09:00","2022-11-29 18:00","연속"]
[169,"충북","직할","신중부S/S CB 7C00","신중부변전소 345kV GIS DS Pin 교체공사","PD발생 개선을 위한 Pin 교체작업","2022-11-28 09:00","2022-11-29 18:00","2022-11-28 09:00","2022-11-29 18:00","연속"]
[170,"대전세종충남","서산","당진T/P CB 7172","22년 서산P/O 변전협력회사 총액공사","(오버홀병행) 당진화력S/S 345kV 7172CB 보통점검","2022-11-08 09:00","2022-11-08 18:00","2022-11-08 09:00","2022-11-08 18:00","연속"]
[171,"대전세종충남","서산","북당진고덕HVDC CB","북당진-고덕 2단계 HVDC 건설공사","1. 2단계 HVDC 건설공사 부하시험 선행작업 시행(필터 개체시험) 2. 북당진-고덕 HVDC 운영사업소 연차점검 3. 밸브GRP빔 리콜 교체 4. 1단계 불량사항 현장조치 등","2022-11-07 09:00","2022-12-16 18:00","2022-11-07 09:00","2022-12-16 18:00","연속"]
[172,"대전세종충남","서산","북당진현대제철 T/L","345kV 신송산분기T/L 건설공사","345kV 현대제철T/L 본선로 구성","2022-11-15 09:00","2022-11-21 18:00","2022-11-15 09:00","2022-11-21 18:00","연속"]
[173,"대전세종충남","서산","신당진개폐소북당진 T/L","345kV 신당진개폐소-북당진T/L 가공지선 설치 공사","345kV 신당진개폐소-북당진T/L 가공지선 설치 공사","2022-11-22 08:00","2022-11-22 18:00","2022-11-22 08:00","2022-11-22 18:00","연속"]
[174,"대전세종충남","서산","신당진개폐소현대제철 T/L","345kV 신송산분기T/L 건설공사","345kV 현대제철T/L 본선로 구성","2022-11-08 09:00","2022-11-14 18:00","2022-11-08 09:00","2022-11-14 18:00","연속"]
[175,"대전세종충남","서산","신당진S/S CB 7672","22년 서산P/O GIS 보통점검 공사","신당진S/S 345kV 7672CB 보통점검","2022-11-14 09:00","2022-11-14 18:00","2022-11-14 09:00","2022-11-14 18:00","연속"]
[176,"대전세종충남","서산","신당진S/S CB 7171","22년 서산P/O GIS 보통점검 공사","신당진S/S 345kV 7171CB 보통점검","2022-11-07 09:00","2022-11-07 18:00","2022-11-07 09:00","2022-11-07 18:00","연속"]
[177,"대전세종충남","서산","신당진S/S CB 7600","22년 서산P/O GIS 보통점검 공사","신당진S/S 345kV 7600CB 보통점검","2022-11-15 09:00","2022-11-15 18:00","2022-11-15 09:00","2022-11-15 18:00","연속"]
[178,"대전세종충남","서산","신서산신당진#2 T/L"," 345kV 신서산-신당진#2T/L 보호계전기 및 결상회로 개선"," 345kV 신서산-신당진#2T/L 보호계전기(양단) 및 결상회로(신서산) 개선","2022-11-07 09:00","2022-11-07 18:00","취소","취소","연속"]
[179,"대전세종충남","서산","신서산태안TP#2 T/L","345kV 신서산-태안화력T/L 항공장애표시구 교체 및 설치 공사","345kV 신서산-태안화력T/L 항공장애표시구 교체 및 설치 공사","2022-11-01 08:00","2022-11-03 18:00","취소","취소","매일"]
[180,"대전세종충남","서산","신서산아산#1 T/L","345신서산-아산 이도조정공사","345kV 신서산-아산#1T/L 이도조정공사(11.21) : No.48~50,69~70 154kV 합덕-송악 애자교체공사(4회선병가) (11.22~23) * 154kV 합덕-송악#1T/L 10월분 휴전 취소시","2022-11-28 08:00","2022-11-30 18:00","취소","취소","매일"]
[181,"대전세종충남","서산","신서산아산#2 T/L"," 345kV 아산S/S 취약설비 보강 및 배전반 정비공사","- 모자익배전반 철거 * 1식 - 집중감시제어반+디지탈축소형모자익배전반 설치 *1식 ","2022-11-07 09:00","2022-11-25 18:00","2022-11-01 09:00","2022-11-17 18:00","연속"]
[182,"대전세종충남","천안","아산S/S #1 M.Tr"," 345kV 아산S/S 취약설비 보강 및 배전반 정비공사","- 모자익배전반 철거 * 1식 - 집중감시제어반+디지탈축소형모자익배전반 설치 *1식 ","2022-11-07 09:00","2022-11-25 18:00","2022-11-01 09:00","2022-11-17 18:00","연속"]
[183,"대전세종충남","서산","신서산태안TP#1 T/L","345kV 신서산-태안화력T/L 항공장애표시구 교체공사","345kV 신서산-태안화력T/L 항공장애표시구 교체공사","2022-11-04 08:00","2022-11-05 18:00","취소","취소","매일"]
[184,"대전세종충남","세종","세종S/S #2 BUS","345kV 세종S/S #1M.Tr 증설공사","345kV M.Tr 1BANK 설치 362kV 1CB설치 170kV GIS 1CCT설치","2022-11-28 09:00","2022-12-03 18:00","2022-11-28 09:00","2022-12-03 18:00","연속"]
[185,"대전세종충남","세종","세종S/S CB 7200","345kV 세종S/S #1M.Tr 증설공사","345kV M.Tr 1BANK 설치 362kV 1CB설치 170kV GIS 1CCT설치","2022-11-28 09:00","2023-01-20 18:00","2022-11-28 09:00","2023-01-20 18:00","연속"]
[186,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S 345kV #4 M.Tr 1,2차 부싱절연유 채유","신온양S/S 345kV #4 M.Tr 1,2차 부싱절연유 채유","2022-11-07 09:00","2022-11-07 18:00","2022-11-07 09:00","2022-11-07 18:00","연속"]
[187,"대전세종충남","천안","신탕정S/S #4 M.Tr","신탕정S/S 345kV #4 M.Tr 하자보수","신탕정S/S 345kV #4 M.Tr 하자보수","2022-11-21 09:00","2022-11-25 18:00","2022-11-21 09:00","2022-11-25 18:00","연속"]
[188,"대전세종충남","천안","신탕정S/S #3 M.Tr","신탕정S/S 345kV #3 M.Tr 보통점검","신탕정S/S 345kV #3 M.Tr 보통점검","2022-11-09 09:00","2022-11-10 18:00","2022-11-09 09:00","2022-11-10 18:00","연속"]
[189,"대전세종충남","천안","아산S/S #3 M.Tr","아산S/S 345kV #3 M.Tr 보통점검","아산S/S 345kV #3 M.Tr 보통점검","2022-11-03 09:00","2022-11-04 18:00","2022-11-03 09:00","2022-11-04 18:00","연속"]
[190,"대전세종충남","청양","보령C/C CB 7372","345kV 차단기 부동작 예방 조작시험(7372)","345kV 차단기 부동작 예방 조작시험(7372)","2022-11-14 09:00","2022-11-14 14:00","2022-11-14 09:00","2022-11-14 14:00","연속"]
[191,"대전세종충남","청양","보령C/C CB 7400","345kV 차단기 부동작 예방 조작시험(7400)","345kV 차단기 부동작 예방 조작시험(7400)","2022-11-15 09:00","2022-11-15 14:00","2022-11-15 09:00","2022-11-15 14:00","연속"]
[192,"대전세종충남","청양","보령C/C CB 7471","345kV 차단기 부동작 예방 조작시험(7471)","345kV 차단기 부동작 예방 조작시험(7471)","2022-11-14 14:00","2022-11-14 18:00","2022-11-14 14:00","2022-11-14 18:00","연속"]
[193,"대전세종충남","청양","보령C/C CB 7472","345kV 차단기 부동작 예방 조작시험(7472)","345kV 차단기 부동작 예방 조작시험(7472)","2022-11-15 14:00","2022-11-15 18:00","2022-11-15 14:00","2022-11-15 18:00","연속"]
[194,"대전세종충남","청양","보령T/P CB 7171","345kV 차단기 부동작 예방 조작시험(7171)","345kV 차단기 부동작 예방 조작시험(7171)","2022-11-10 09:00","2022-11-10 11:00","2022-11-10 09:00","2022-11-10 11:00","연속"]
[195,"대전세종충남","청양","보령T/P CB 7272","345kV 차단기 부동작 예방 조작시험(7272)","345kV 차단기 부동작 예방 조작시험(7272)","2022-11-10 14:00","2022-11-10 18:00","2022-11-10 14:00","2022-11-10 18:00","연속"]
[196,"대전세종충남","청양","보령T/P CB 7200","345kV 차단기 부동작 예방 조작시험(7200)","345kV 차단기 부동작 예방 조작시험(7200)","2022-11-10 11:00","2022-11-10 14:00","2022-11-10 11:00","2022-11-10 14:00","연속"]
[197,"대전세종충남","청양","청양신탕정#1 T/L","(10월 취소시)청양S/S 73Bay B/F 및 T/L PNL 교체공사","청양S/S 73Bay B/F PNL 및 송전선로 보호반 교체공사","2022-11-14 09:00","2022-11-25 18:00","취소","취소","연속"]
[198,"대전세종충남","청양","청양군산#2 T/L","(10월 취소시)청양S/S 73Bay B/F PNL 교체공사","청양S/S 73Bay B/F PNL 교체공사","2022-11-14 09:00","2022-11-25 18:00","2022-11-14 09:00","2022-11-25 18:00","연속"]
[199,"대전세종충남","청양","청양보령TP#2 T/L","345kV 청양-보령화력#2T/L LA,CVT 대체 및 관련기기 점검","청양S/S LA, CVT(A,B) 대체 및 345kV 차단기 부동작 예방 조작시험(7672)","2022-11-08 09:00","2022-11-08 18:00","2022-11-08 09:00","2022-11-08 18:00","연속"]
[200,"전북","군산","군산새만금#2 T/L","육상태양광T/L 발전차단용 SPS설치공사","- 육상태양광T/L 발전차단용 SPS 설치 및 시험","2022-11-09 09:00","2022-11-10 18:00","2022-11-09 09:00","2022-11-10 18:00","연속"]
[201,"전북","군산","군산새만금#1 T/L","육상태양광T/L 발전차단용 SPS설치공사","- 육상태양광 발전차단용 SPS 설치","2022-11-07 09:00","2022-11-08 18:00","2022-11-07 09:00","2022-11-08 18:00","연속"]
[202,"전북","김제","신김제S/S #2 M.Tr","신김제S/S 345kV 주변압기 보통점검","신김제S/S 345kV 주변압기 보통점검","2022-11-07 09:00","2022-11-09 18:00","2022-11-13 09:00","2022-11-15 18:00","연속"]
[203,"전북","김제","신김제S/S #1 M.Tr","신김제S/S 345kV 주변압기 보통점검","신김제S/S 345kV 주변압기 보통점검","2022-11-01 09:00","2022-11-03 18:00","2022-11-01 09:00","2022-11-03 18:00","연속"]
[204,"전북","직할","신남원S/S CB 7200","22년도 전북직할 362kV GIS 단독차단기 정밀점검","22년도 전북직할 362kV GIS 단독차단기 정밀점검","2022-11-21 09:00","2022-11-25 18:00","2022-11-21 09:00","2022-11-25 18:00","연속"]
[205,"전북","직할","신남원S/S CB 7771","장기사용 #77Bay B/F반 대체공사","장기사용 #77Bay B/F반 대체공사","2022-11-28 09:00","2022-12-02 18:00","2022-11-28 09:00","2022-12-02 18:00","연속"]
[206,"전북","직할","신옥천신남원#1 T/L","22년도 전북직할 362kV GIS 단독차단기 정밀점검(시험가압)","22년도 전북직할 362kV GIS 단독차단기 정밀점검(시험가압)","2022-11-25 16:00","2022-11-25 18:00","2022-11-25 16:00","2022-11-25 18:00","연속"]
[207,"전북","직할","신남원S/S CB 7700","장기사용 #77Bay B/F반 대체공사","장기사용 #77Bay B/F반 대체공사","2022-11-28 09:00","2022-12-02 18:00","2022-11-28 09:00","2022-12-02 18:00","연속"]
[208,"전북","직할","신남원광양#2 T/L","345kV 신남원-의령 등 2개T/L 추락방지시설 설치공사","345kV 신남원-광양T/L No.209 ~ 242 - 수직, 수평 추락방지시설 설치 (34기)","2022-11-14 08:00","2022-11-18 17:00","2022-11-14 08:00","2022-11-18 17:00","매일"]
[209,"전북","직할","신남원광양#1 T/L","345kV 신남원-의령 등 2개T/L 추락방지시설 설치공사","345kV 신남원-광양T/L No.209 ~ 242 - 수직, 수평 추락방지시설 설치 (34기)","2022-11-07 08:00","2022-11-11 17:00","2022-11-07 08:00","2022-11-11 17:00","매일"]
[210,"전북","군산","군산S/S #2 M.Tr","군산P/O 부싱절연유 채유공사","부싱절연유 채유공사","2022-11-11 09:00","2022-11-11 18:00","2022-11-11 09:00","2022-11-11 18:00","연속"]
[211,"광주전남","강진","신강진S/S #4 M.Tr","2022~23년 강진전력지사 변전협력회사 총액공사","신강진S/S #4M.Tr 3차 LA, CB 보통, #4-1Sh.R 및 CB 보통, #4-2Sh.R 및 CB 보통, #4M.Tr 1,2차 GIS 하자","2022-11-16 10:00","2022-11-17 18:00","2022-11-07 10:00","2022-11-08 18:00","연속"]
[212,"광주전남","강진","신강진S/S #3 M.Tr","2022~23년 강진전력지사 변전협력회사 총액공사","신강진S/S #3M.Tr 하자, 3차 LA 하자, 1차 GIS 하자","2022-11-14 10:00","2022-11-15 18:00","2022-11-09 10:00","2022-11-10 18:00","연속"]
[213,"광주전남","강진","신강진광양#2 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","신강진S/S 신강진-광양#2T/L GIS 하자, 신강진-광양 7500GIS 하자","2022-11-21 10:00","2022-11-21 18:00","2022-11-21 10:00","2022-11-21 18:00","연속"]
[214,"광주전남","강진","신강진광양#1 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","신강진S/S 신강진-광양#1T/L GIS 하자, 신강진-광양 7400GIS 하자","2022-11-18 10:00","2022-11-18 18:00","2022-11-18 10:00","2022-11-18 18:00","연속"]
[215,"광주전남","강진","신강진S/S #1 M.Tr","2022~23년 강진전력지사 변전협력회사 총액공사","신강진S/S #1M.Tr 보통, 3차 CB 초기, #1-1Sh.R CB초기, #1-2Sh.R CB보통, #1S.Tr CB 보통","2022-11-07 10:00","2022-11-08 18:00","2022-11-16 10:00","2022-11-17 18:00","연속"]
[216,"광주전남","강진","신강진S/S #2 M.Tr","2022~23년 강진전력지사 변전협력회사 총액공사","신강진S/S #2M.Tr 3차 CB 보통, #2-1Sh.R 및 CB 보통, #2-2Sh.R 및 CB 보통, #2S.Tr 보통 및 CB 초기, #2M.Tr 1차 GIS 하자","2022-11-09 10:00","2022-11-10 18:00","2022-11-14 10:00","2022-11-15 18:00","연속"]
[217,"광주전남","광주","신광주S/S #2 M.Tr","22년 광주전력지사 변전협력회사 총액공사","신광주S/S #2M.Tr 3차측 Main 및 #2-1,2 Sh.R VCB 대체 (즉시가압 불가)","2022-11-25 09:00","2022-11-29 18:00","취소","취소","연속"]
[218,"광주전남","광주","신광주S/S #1 Sh.R CB","신광주S/S 345kV #1Sh.R (방음시설 설치)","345kV 신광주S/S 소음저감시설 설치 공사 - 345kV Sh.R 전면 방음시설 설치(인근마을 주민 소음민원 해소)","2022-11-28 09:00","2022-12-16 18:00","2022-11-28 09:00","2022-12-16 18:00","연속"]
[219,"광주전남","광주","신광주S/S #3 M.Tr","22년 광주전력지사 변전협력회사 총액공사","신광주S/S #3M.Tr 3차측 Main 및 #3-1,2 Sh.R, #2S.Tr VCB 대체 (즉시가압 불가)","2022-11-30 09:00","2022-12-05 18:00","취소","취소","연속"]
[220,"광주전남","광주","신광주S/S #1 M.Tr","22년 광주전력지사 변전협력회사 총액공사","3차 노후 차단기 교체 (3차 MAIN, S.TR, 1-1 SH.R, 1-2 SH.R)","2022-11-21 09:00","2022-11-24 18:00","2022-11-21 09:00","2022-11-24 18:00","연속"]
[221,"광주전남","광주","신광주S/S CB 7572","22년 광주변전 협력회사 총액공사(신광주 7572CB)","22년 광주변전 협력회사 총액공사 - 신광주 7572CB 하자점검","2022-11-08 09:00","2022-11-08 18:00","2022-11-08 09:00","2022-11-08 18:00","연속"]
[222,"광주전남","광주","신광주신화순#1 T/L","22-23 광주전력지사 송전정비회사 총액공사","345kV 신광주-신화순#1T/L 철탑추락방지장치 설치(수평)","2022-11-29 09:00","2022-12-08 18:00","취소","취소","매일"]
[223,"광주전남","광주","신광주S/S #1 BUS","22년 광주전력지사 변전협력회사 총액공사","모선보호반 교체 (즉시가압 불가)","2022-11-07 09:00","2022-11-11 18:00","2022-11-07 09:00","2022-11-11 18:00","연속"]
[224,"광주전남","광주","신광주S/S #2 BUS","22년 광주전력지사 변전협력회사 총액공사","모선보호반 교체 (즉시가압 불가)","2022-11-14 09:00","2022-11-18 18:00","2022-11-14 09:00","2022-11-18 18:00","연속"]
[225,"광주전남","목포","한빛#3N/P CB 7E00","한빛6호기 14차 계획예방정비 휴전","소내전원절체시험 주변압기→대기보조변압기 절체기능 확인","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[226,"광주전남","목포","한빛#3N/P CB 7E71","한빛6호기 14차 계획예방정비 휴전","소내전원절체시험 주변압기→대기보조변압기 절체기능 확인","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[227,"광주전남","순천","광양CC여수TP#1 T/L","345kV 광양CC-여수TP T/L 추락방지시설 설치공사","목적 : 승탑 작업자 추락방지를 위한 추락방지시설 설치 내용 : 수직, 수평 추락방지시설 설치","2022-11-21 08:00","2022-11-25 18:00","취소","취소","매일"]
[228,"광주전남","순천","광양CC여수TP#2 T/L","345kV 광양CC-여수TP T/L 추락방지시설 설치공사","목적 : 승탑 작업자 추락방지를 위한 추락방지시설 설치 내용 : 수직, 수평 추락방지시설 설치","2022-11-28 08:00","2022-11-30 18:00","취소","취소","매일"]
[229,"광주전남","순천","광양S/S SEC CB 70710","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 345kV #70-71 BUS SEC GIS 초기점검","2022-11-07 09:00","2022-11-07 18:00","취소","취소","연속"]
[230,"광주전남","순천","광양광양CC#1 T/L","광양S/S 362kV GIS 용량변경 교체공사","362kV GIS 79BAY 3CB 교체","2022-11-01 10:00","2023-01-31 17:00","취소","취소","연속"]
[231,"광주전남","순천","광양광양제철#1 T/L","광양S/S 362kV GIS 용량변경 교체공사","362kV GIS 79BAY 3CB 교체","2022-11-01 10:00","2023-01-31 17:00","취소","취소","연속"]
[232,"광주전남","순천","여수T/P CB 7272","'22-23년 순천전력지사 변전정비 총액공사","#2M.Tr 1차 7272 CB 타임측정","2022-11-01 10:00","2022-11-01 14:00","2022-11-01 10:00","2022-11-01 14:00","연속"]
[233,"광주전남","순천","여수T/P CB 7200","'22-23년 순천전력지사 변전정비 총액공사","#2M.Tr 1차 TIE 7200 CB 타임측정","2022-11-01 14:00","2022-11-01 18:00","2022-11-01 14:00","2022-11-01 18:00","연속"]
[234,"대구","달성","서대구고령#2 T/L","GIS, LA, PT 보통점검","7500, PT, LA 보통점검","2022-11-15 09:00","2022-11-16 18:00","2022-11-15 09:00","2022-11-16 18:00","연속"]
[235,"대구","달성","고령S/S #1 Sh.R (CB 7A79, 7A00, 7A72)","7ABay 및 Sh.R 하자점검","7ABay 및 Sh.R 하자점검","2022-11-08 09:00","2022-11-09 18:00","2022-11-08 09:00","2022-11-09 18:00","연속"]
[236,"대구","달성","고령S/S #3 M.Tr","#3M.Tr 휴전","-부싱절연유 채유 -S.Tr CB 대체 - 1차 차단기 동작특성시험","2022-11-21 09:00","2022-11-23 18:00","2022-11-21 09:00","2022-11-23 18:00","연속"]
[237,"대구","달성","고령의령#1 T/L","고령S/S 고령-의령#1T/L GIS, PT, LA 보통점검","고령S/S 고령-의령#1T/L GIS, PT, LA 보통점검","2022-11-10 09:00","2022-11-11 18:00","2022-11-10 09:00","2022-11-11 18:00","연속"]
[238,"대구","칠곡","북대구선산 T/L","B/F 보호반 설치공사","B/F 보호반 설치공사","2022-11-15 09:00","2022-11-22 18:00","2022-11-16 09:00","2022-11-22 18:00","연속"]
[239,"대구","칠곡","북경남서대구#2 T/L","북경남-서대구#2T/L 지지애자 교체공사","북경남-서대구#2T/L 지지애자 교체공사 - 서대구S/T","2022-11-21 12:00","2022-11-21 14:00","2022-11-21 12:00","2022-11-21 14:00","연속"]
[240,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","옥외철구 철거 관련 안전이격 확보","2022-11-07 08:30","2022-11-11 18:00","2022-11-07 08:30","2022-11-11 18:00","연속"]
[241,"대구","포항","신포항S/S #4 M.Tr","신포항S/S 345kV 주변압기 설치공사","신포항S/S 345kV M.Tr 대체","2022-11-21 08:00","2022-11-25 17:00","2022-11-21 08:00","2022-11-25 17:00","연속"]
[242,"대구","포항","신포항S/S #1 M.Tr","신포항S/S 345kV 주변압기 설치공사","신포항S/S 345kV M.Tr 대체","2022-11-01 08:00","2022-11-04 17:00","2022-11-01 08:00","2022-11-04 17:00","연속"]
[243,"대구","포항","신포항S/S #2 M.Tr","신포항S/S 345kV 주변압기 설치공사","신포항S/S 345kV M.Tr 대체","2022-11-07 08:00","2022-11-11 17:00","2022-11-07 08:00","2022-11-11 17:00","연속"]
[244,"대구","포항","선산신포항 T/L","2022년 칠곡전력 가공송전 순시점검 위탁공사","345kV 선산분기T/L 정밀점검","2022-11-07 09:00","2022-11-14 18:00","취소","취소","연속"]
[245,"대구","포항","신포항S/S #3 M.Tr","신포항S/S 345kV 주변압기 설치공사","신포항S/S 345kV M.Tr 대체","2022-11-14 08:00","2022-11-18 17:00","2022-11-14 08:00","2022-11-18 17:00","연속"]
[246,"대구","경산","신경산S/S #1 M.Tr","22~23년 경산PO 변전협력회사 총액공사 ","70Bay LCP 노후 보조계전기 교체","2022-11-07 09:30","2022-11-09 18:00","2022-11-07 09:30","2022-11-09 18:00","연속"]
[247,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #1BUS GIB 철거관련 무부하가압 시험선로","2022-10-31 08:30","2022-10-31 18:00","2022-10-31 08:30","2022-11-01 09:00","연속"]
[248,"경북","구미","서대구선산#1 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초공사(되메우기) 관련 안전거리 확보","2022-11-07 08:30","2022-11-07 18:00","2022-11-07 08:30","2022-11-07 18:00","연속"]
[249,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #1BUS GIB 철거관련 무부하가압 시험선로","2022-11-08 08:30","2022-11-08 18:00","2022-11-08 08:30","2022-11-08 18:00","연속"]
[250,"경북","구미","선산S/S #1 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초공사(되메우기) 관련 안전거리 확보","2022-10-31 08:30","2022-10-31 18:00","취소","취소","연속"]
[251,"경북","구미","서대구선산#1 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초공사(되메우기) 관련 안전거리 확보","2022-10-31 08:30","2022-10-31 18:00","취소","취소","연속"]
[252,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #2BUS GIB 철거관련 무부하가압 시험선로","2022-11-06 08:30","2022-11-06 18:00","2022-11-06 08:30","2022-11-06 18:00","연속"]
[253,"경북","구미","선산S/S #3 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","#75BUS 철거관련 안전거리 확보","2022-11-05 08:30","2022-11-05 18:00","2022-11-05 08:30","2022-11-05 18:00","연속"]
[254,"경북","구미","선산S/S #1 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초공사(되메우기) 관련 안전거리 확보","2022-11-07 08:30","2022-11-07 18:00","2022-11-07 08:30","2022-11-07 18:00","연속"]
[255,"경북","구미","선산S/S #3 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초공사(되메우기) 관련 안전거리 확보","2022-11-08 08:30","2022-11-08 18:00","2022-11-08 08:30","2022-11-08 18:00","연속"]
[256,"경북","구미","서대구선산#2 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","기초공사(되메우기) 관련 안전거리 확보","2022-11-09 08:30","2022-11-09 18:00","2022-11-09 08:30","2022-11-09 18:00","연속"]
[257,"경북","구미","선산S/S #2 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","기초공사(되메우기) 관련 안전거리 확보","2022-11-09 08:30","2022-11-09 18:00","2022-11-09 08:30","2022-11-09 18:00","연속"]
[258,"경북","구미","선산S/S #75 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #2BUS GIB 철거","2022-11-01 08:30","2022-11-06 18:00","2022-11-01 09:00","2022-11-06 18:00","연속"]
[259,"경북","구미","선산S/S #4 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","77bay #4M.Tr Bay GIS 교체","2022-11-01 08:30","2022-12-30 18:00","2022-11-01 09:00","2022-12-30 18:00","연속"]
[260,"경북","영주","신영주S/S #2 M.Tr","2022-23년 영주전력지사 변전협력회사 총액공사","부싱절연유 채유 2차 LA 대체","2022-11-21 10:00","2022-11-23 18:00","2022-11-21 10:00","2022-11-23 18:00","연속"]
[261,"경북","영주","신영주한울NP #2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","71BAY B/F 대체","2022-11-28 10:00","2022-11-30 18:00","취소","취소","연속"]
[262,"경북","영주","신영주예천PP#2 T/L","345kV신영주-한울NP2 등 5개TL 추락방지시설 설치공사","345kV신영주-한울NP2 등 5개TL 추락방지시설 설치 -345kV신영주-예천PPT/L 고정형 폴리머지지애자 설치","2022-11-16 08:00","2022-11-24 17:00","2022-11-16 08:00","2022-11-24 17:00","매일"]
[263,"경북","영주","신영주예천PP#1 T/L","345kV신영주-한울NP2 등 5개TL 추락방지시설 설치공사","345kV신영주-한울NP2 등 5개TL 추락방지시설 설치 -345kV신영주-예천PPT/L 고정형 폴리머지지애자 설치","2022-11-07 08:00","2022-11-15 17:00","2022-11-07 08:00","2022-11-15 17:00","매일"]
[264,"경북","영주","신영주S/S #1 M.Tr","2022-23년 영주전력지사 변전협력회사 총액공사","보호반 대체","2022-11-28 10:00","2022-11-30 18:00","2022-11-28 10:00","2022-11-30 18:00","연속"]
[265,"부산울산","동부산","고리N/P SEC CB 71720","고리NP S/Y 71-72-0 유압경보 관련 메커니즘 점검","고리NP S/Y 71-72-0 유압경보 관련 메커니즘 점검","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","연속"]
[266,"부산울산","동부산","신고리고리NP#1 T/L","345kV 신고리-고리NP#1,2T/L 자기애관교체공사","자기애관을 폴리머애관으로 교체","2022-11-16 09:00","2022-12-06 18:00","취소","취소","연속"]
[267,"부산울산","북부산","북부산울산TP#1 T/L","22년 북부산전력지사 345kV GIS 정밀점검","북부산S/S 345kV #2M.Tr 7572GIS 정밀점검 - 시험가압선로 : 북부산-울산TP#1 T/L","2022-11-26 17:00","2022-11-26 18:00","2022-11-26 17:00","2022-11-26 18:00","연속"]
[268,"부산울산","북부산","북부산울산TP#2 T/L","22-23 북부산전력지사 변전 총액공사","북부산S/S 345kV 북부산-울산TP#2T/L 차단기(7372) 조작시험","2022-11-18 09:00","2022-11-18 18:00","2022-11-18 09:00","2022-11-18 18:00","연속"]
[269,"부산울산","북부산","북부산S/S CB 7572","22년 북부산전력지사 345kV GIS 정밀점검","북부산S/S 345kV 7572GIS 정밀점검","2022-11-24 09:00","2022-11-26 18:00","2022-11-24 09:00","2022-11-26 18:00","연속"]
[270,"부산울산","북부산","북부산S/S CB 7772","22년 북부산전력지사 345kV GIS 정밀점검","북부산S/S 345kV 7772GIS 정밀점검","2022-11-10 09:00","2022-11-12 18:00","2022-11-10 09:00","2022-11-12 18:00","연속"]
[271,"부산울산","북부산","북부산S/S SEC CB 75760","22-23 북부산전력지사 변전 총액공사","북부산S/S 345kV 75-76 BUS SEC 차단기 조작시험","2022-11-14 14:00","2022-11-14 18:00","2022-11-14 14:00","2022-11-14 18:00","연속"]
[272,"부산울산","북부산","북부산S/S SEC CB 70710","22-23 북부산전력지사 변전 총액공사","북부산S/S 345kV 70-71 BUS SEC 차단기 조작시험","2022-11-14 09:00","2022-11-14 14:00","2022-11-14 09:00","2022-11-14 14:00","연속"]
[273,"부산울산","북부산","북부산S/S #3 M.Tr","22년 북부산전력지사 345kV GIS 정밀점검","북부산S/S 345kV #3M.Tr 7772GIS 정밀점검 - 시험가압선로","2022-11-12 17:00","2022-11-12 18:00","2022-11-12 17:00","2022-11-12 18:00","연속"]
[274,"부산울산","북부산","신양산북부산#2 T/L","22년 북부산전력지사 345kV GIS 정밀점검","북부산S/S 345kV #3M.Tr 7772GIS 정밀점검 - 시험가압선로 : 신양산-북부산#2 T/L","2022-11-12 17:00","2022-11-12 18:00","2022-11-12 17:00","2022-11-12 18:00","연속"]
[275,"부산울산","북부산","북부산S/S #2 M.Tr","22년 북부산전력지사 345kV GIS 정밀점검","북부산S/S 345kV #2M.Tr 7572GIS 정밀점검 - 시험가압선로","2022-11-26 17:00","2022-11-26 18:00","2022-11-26 17:00","2022-11-26 18:00","연속"]
[276,"부산울산","서부산","신김해신녹산#2 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 : 23~52호(20기)","2022-11-11 07:00","2022-11-20 18:00","2022-11-11 07:00","2022-11-20 18:00","연속"]
[277,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S 362kV GIS 정밀점검공사","신녹산S/S 362kV 7372 GIS 정밀점검 및 345kV #3M.Tr 보통점검","2022-11-21 09:00","2022-11-21 18:00","2022-11-21 09:00","2022-11-21 18:00","연속"]
[278,"부산울산","서부산","신김해신녹산#2 T/L","신녹산S/S 362kV GIS 정밀점검공사","신녹산S/S 362kV 7372 GIS 정밀점검 시험가압","2022-11-23 16:00","2022-11-23 18:00","2022-11-23 16:00","2022-11-23 18:00","연속"]
[279,"부산울산","울산","동울산신울산 T/L","철탑 추락방지장치 설치공사","전 구간 수직/수평 설치","2022-11-10 08:00","2022-11-20 18:00","2022-11-10 08:00","2022-11-20 18:00","연속"]
[280,"부산울산","울산","신온산S/S #4 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","75Bay GIS 대체공사 관련 안전이격거리 확보","2022-11-30 09:00","2022-12-14 18:00","2022-11-30 09:00","2022-12-14 18:00","매일"]
[281,"부산울산","울산","신온산S/S 신온산-SOIL#6 T/L (CB 7500, 7571)","345kV 신온산S/S 용량부족 차단기 대체공사","75Bay GIS 대체공사(7500, 7572)","2022-11-30 09:00","2023-01-12 18:00","2022-11-30 09:00","2023-01-12 18:00","연속"]
[282,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","74Bay GIS 대체 관련 #2BUS 시험가압","2022-11-28 12:00","2022-11-28 15:00","2022-11-28 12:00","2022-11-28 15:00","연속"]
[283,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","75Bay GIS 대체공사(7500, 7572)","2022-11-30 09:00","2022-12-13 18:00","2022-11-30 09:00","2022-12-13 18:00","연속"]
[284,"부산울산","울산","신온산S/S #4 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","74Bay GIS 대체 관련 #1BUS 시험가압","2022-11-07 09:00","2022-11-08 18:00","2022-11-07 09:00","2022-11-08 18:00","연속"]
[285,"부산울산","울산","신온산S/S #3 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","75Bay GIS 대체공사(7500, 7572)","2022-11-30 09:00","2023-01-12 18:00","2022-11-30 09:00","2023-01-12 18:00","연속"]
[286,"부산울산","울산","신온산S/S #1 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","74Bay GIS 대체 관련 #1BUS 시험가압","2022-11-28 09:00","2022-11-28 12:00","2022-11-28 09:00","2022-11-28 12:00","연속"]
[287,"부산울산","울산","신울산S/S #75 BUS","신울산S/S 345kV 용량대체공사","- #4M.Tr POST 철거 관련 모선 휴전","2022-11-14 09:00","2022-11-14 18:00","2022-11-14 09:00","2022-11-14 18:00","연속"]
[288,"부산울산","울산","신울산S/S #4 M.Tr","신울산S/S 345kV 용량대체공사","- #4M.Tr 보호반 및 76BAY B/F반 이설 - #4M.Tr 1차측 철구 철거 및 신규 설치","2022-11-14 09:00","2022-12-16 18:00","2022-11-14 09:00","2022-12-16 18:00","연속"]
[289,"부산울산","울산","울산C/C CB 7100","22년 울산복합S/Y 345kV GIS 보통점검공사","GIS(7100) 보통점검","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","연속"]
[290,"부산울산","울산","울산C/C CB 7172","22년 울산복합S/Y 345kV GIS 보통점검공사","GIS(7172) 보통점검","2022-11-02 09:00","2022-11-02 18:00","2022-11-02 09:00","2022-11-02 18:00","연속"]
[291,"부산울산","울산","울주고리NP#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","추락방지장치 및 피뢰기 설치(안전이격확보)","2022-11-16 07:00","2022-11-21 18:00","2022-11-16 07:00","2022-11-21 18:00","연속"]
[292,"부산울산","직할","신대연S/S #2 M.Tr","22-23년 직할 변전협력회사 총액공사","신대연S/S 345kV #2M.Tr, 7272GIS, #2S.Tr, 4189 GIS 보통점검","2022-11-28 09:30","2022-12-02 18:00","취소","취소","연속"]
[293,"부산울산","직할","신대연S/S #1 M.Tr","22-23년 직할 변전협력회사 총액공사","신대연S/S 345kV #1M.Tr 보통점검, 7172 GIS, #1S.Tr,4189 GIS 보통점검","2022-11-21 09:30","2022-11-25 18:00","2022-11-21 09:30","2022-11-25 18:00","연속"]
[294,"경남","직할","신김해S/S #5 M.Tr","신김해S/S #5M.Tr 본체 및 OLTC 정밀점검 공사","신김해S/S #5M.Tr 본체 및 OLTC 정밀점검 공사","2022-11-21 08:00","2022-12-09 18:00","2022-11-21 08:00","2022-12-09 18:00","연속"]
[295,"경남","직할","신마산신김해#1 T/L","345kV 신김해S/S 74BAY 용량부족 GIS 대체공사","345kV 신김해S/S 74BAY 용량부족 GIS 대체공사","2022-11-09 09:00","2022-11-10 18:00","2022-11-09 09:00","2022-11-10 18:00","연속"]
[296,"경남","직할","창원삼천포TP#1 T/L","345kV 창원-삼천포화력T/L 추락방지장치 설치공사","345kV 창원-삼천포화력T/L 103~183호(59기, 기설제외) 추락방지장치 설치","2022-11-14 08:00","2022-11-20 18:00","2022-11-14 08:00","2022-11-20 18:00","매일"]
[297,"경남","직할","창원삼천포TP#2 T/L","345kV 창원-삼천포화력T/L 추락방지장치 설치공사","345kV 창원-삼천포화력T/L 103~183호(59기, 기설제외) 추락방지장치 설치","2022-11-21 08:00","2022-11-27 18:00","2022-11-21 08:00","2022-11-27 18:00","매일"]
[298,"경남","진주","의령산청양수#2 T/L","산청P/P 의령-산청양수#2T/L LA교체","산청P/P 의령-산청양수#2T/L LA교체","2022-11-10 09:00","2022-11-10 18:00","2022-11-10 09:00","2022-11-10 18:00","연속"]
[299,"경남","진주","의령산청양수#1 T/L","산청P/P 의령-산청양수#1T/L LA교체","산청P/P 의령-산청양수#1T/L LA교체","2022-11-09 09:00","2022-11-09 18:00","2022-11-09 09:00","2022-11-09 18:00","연속"]
[300,"경남","진주","신남원의령#2 T/L","의령S/S 신남원-의령#2T/L PT초기점검","[병행]7721DS(C상) 구동모터 교체","2022-11-14 10:00","2022-11-14 18:00","2022-11-14 10:00","2022-11-14 18:00","연속"]
[301,"경남","진주","하동T/P SEC CB 75760","하동T/P 70-71-0, 75-76-0 GIS 조작시험","하동T/P 70-71-0, 75-76-0 GIS 조작시험","2022-11-01 14:00","2022-11-01 17:00","2022-11-01 14:00","2022-11-01 17:00","연속"]
[302,"경남","진주","광양하동TP#2 T/L","하동T/P 광양-하동화력#2T/L 변전설비 염해방지제 코팅","하동T/P 광양-하동화력#2T/L 변전설비 염해방지제 코팅","2022-11-02 10:00","2022-11-02 17:00","2022-11-02 10:00","2022-11-02 17:00","연속"]
[303,"경남","진주","하동T/P CB 7600","하동T/P 76BAY GIS(7600,7672) 조작시험","하동T/P 76BAY GIS(7600,7672) 조작시험","2022-11-07 10:00","2022-11-07 14:00","2022-11-07 10:00","2022-11-07 14:00","연속"]
[304,"경남","진주","하동T/P CB 7672","하동T/P 76BAY GIS(7600,7672) 조작시험","하동T/P 76BAY GIS(7600,7672) 조작시험","2022-11-07 14:00","2022-11-07 17:00","2022-11-07 14:00","2022-11-07 17:00","연속"]
[305,"경남","진주","하동T/P SEC CB 70710","하동T/P 70-71-0, 75-76-0 GIS 조작시험","하동T/P 70-71-0, 75-76-0 GIS 조작시험","2022-11-01 10:00","2022-11-01 14:00","2022-11-01 10:00","2022-11-01 14:00","연속"]
[306,"경남","통영","신고성S/S #4 M.Tr","신고성S/S #4M.Tr 보호반 대체","1. 신고성S/S #4M.Tr 보호반 대체","2022-11-14 09:00","2022-11-18 18:00","2022-11-14 09:00","2022-11-18 18:00","연속"]
[307,"경남","함안","북경남무주양수 T/L","고정형 폴리머 점퍼지지애자 설치공사","북경남-무주양수T/L 고정형 폴리머 점퍼지지애자 설치공사 - No.163","2022-11-21 09:00","2022-11-21 18:00","2022-11-21 09:00","2022-11-21 18:00","연속"]
[308,"경남","함안","신마산S/S #4 M.Tr","신마산S/S 345kV #4 M.Tr A 154kV LA ABC상 대체","신마산S/S 345kV #4 M.Tr A 154kV LA ABC상 대체","2022-11-16 09:30","2022-11-16 17:30","2022-11-16 09:30","2022-11-16 17:30","연속"]
[309,"경남","함안","신마산S/S #5 M.Tr","신마산S/S 345kV #5 M.Tr 보호반 대체","신마산S/S 345kV #5 M.Tr 보호반 대체, 154kV GCB 보통점검 및 전자변 교체(병행)","2022-11-28 09:30","2022-12-01 17:30","2022-11-28 09:30","2022-12-01 17:30","연속"]
[310,"경남","함안","신마산S/S #2 M.Tr","신마산S/S 345kV #2 M.Tr A 154kV LA ABC상 대체","신마산S/S 345kV #2 M.Tr A 154kV LA ABC상 대체","2022-11-15 09:30","2022-11-15 17:30","2022-11-15 09:30","2022-11-15 17:30","연속"]
[311,"대구",null,"신월성N/P #1호기 주변압기 (CB 7400, 7472)","신월성 1호기 7차 계획예방정비 #1 MTR/UAT/EXTR 점검 *조작차단기 : PCB 7400, 7472","○ MTR/UAT/EXTR 일반 점검 ○ EXTR 교체 등","2022-11-29 10:00","2022-12-17 16:00","2022-11-29 10:00","2022-12-17 16:00","연속"]
[312,"광주전남",null,"한빛N/P #6호기 주변압기 (CB 7C00, 7C71)","한빛6호기 14차 O/H 중 소내전원절체 시험 * 조작차단기: 7C00, 7C71 CB","○ 소내전원절체 시험","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[313,"경북",null,"한울N/P #5호기 주변압기 (CB 7D00, 7D72)","한울5호기 13차 계획예방정비 * 조작차단기: CB 7D00, 7D72","○ 주변압기 C상, 여자변압기 정밀점검 ○ 주/소내보조/여자변압기 일반점검 ","2022-11-02 17:00","2022-11-30 16:00","2022-11-02 17:00","2022-11-30 16:00","연속"]
[314,"전북","직할","신남원신광주#1 T/L","장기사용 #77Bay B/F반 대체공사","장기사용 #77Bay B/F반 대체공사","2022-11-28 09:00","2022-12-02 18:00","2022-11-28 09:00","2022-12-02 18:00","연속"]
[315,"전북","직할","신남원S/S #1 M.Tr","장기사용 #77Bay B/F반 대체공사","장기사용 #77Bay B/F반 대체공사","2022-11-28 09:00","2022-12-02 18:00","2022-11-28 09:00","2022-12-02 18:00","연속"]
[316,"부산울산","울산","울주고리NP#2 T/L","GIS 점검","GIS 점검","2022-11-28 09:00","2022-11-30 18:00","2022-11-28 09:00","2022-11-30 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":539,"n_cols":11,"rows_kept":539,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 11월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-11-10 10:00","2022-11-10 14:00","2022-11-10 10:00","2022-11-10 14:00","연속"]
[2,"서울","성동","구의광장#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-11-10 14:00","2022-11-10 18:00","2022-11-10 14:00","2022-11-10 18:00","연속"]
[3,"서울","성동","금오상계#1 T/L","2022년 가공송전 순시점검 위탁공사","불량애자검출 : 3기","2022-11-01 07:30","2022-11-01 18:00","2022-11-01 07:30","2022-11-01 18:00","연속"]
[4,"서울","성동","금오상계#2 T/L","2022년 가공송전 순시점검 위탁공사","불량애자검출 : 3기","2022-11-02 07:30","2022-11-02 18:00","2022-11-02 07:30","2022-11-02 18:00","연속"]
[5,"서울","성동","방학S/S CB 6100","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-11-07 10:00","2022-11-07 18:00","2022-11-07 10:00","2022-11-07 18:00","연속"]
[6,"서울","성동","방학창동#1 T/L","154kV 창동S/S 디지털화","154kV 창동S/S 디지털화 관련 ㅇ RTU - LID 제어케이블 이설 (170kV GIS, T/L 보호반 감시,제어,계측) ㅇ 현장 - SCADA 간 이설포인트 연동시험 등","2022-11-21 09:00","2022-11-22 18:00","2022-11-21 09:00","2022-11-22 18:00","연속"]
[7,"서울","성동","방학창동#2 T/L","154kV 창동S/S 디지털화","154kV 창동S/S 디지털화 관련 ㅇ RTU - LID 제어케이블 이설 (170kV GIS, T/L 보호반 감시,제어,계측) ㅇ 현장 - SCADA 간 이설포인트 연동시험 등","2022-11-23 09:00","2022-11-24 18:00","2022-11-23 09:00","2022-11-24 18:00","연속"]
[8,"서울","직할","신촌순화 T/L","154kV 신촌S/S 디지털화","154kV 신촌S/S 디지털화 관련 ㅇ 현장정보처리반 - SA LID반 제어케이블 이설 (GIS, T/L 보호반 감시,제어,계측) ㅇ 현장 - SCADA 간 이설포인트 연동시험 등","2022-11-21 09:00","2022-11-22 18:00","2022-11-21 09:00","2022-11-22 18:00","연속"]
[9,"서울","성동","쌍문S/S #1 BUS","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-11-04 10:00","2022-11-04 18:00","2022-11-04 10:00","2022-11-04 18:00","연속"]
[10,"서울","성동","쌍문S/S CB 6100","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-11-04 10:00","2022-11-04 18:00","2022-11-04 10:00","2022-11-04 18:00","연속"]
[11,"서울","중부","양주은평#1 T/L","154kV 양주-은평T/L No.14 안전이격확보공사","전선교체 및 긴선작업","2022-11-01 07:30","2022-11-09 18:00","2022-11-01 07:30","2022-11-09 18:00","연속"]
[12,"서울","직할","원남S/S CB 6100","22년 직할 변전협력 총액","-154kV GIS 보통점검","2022-11-18 10:00","2022-11-18 18:00","2022-11-18 10:00","2022-11-18 18:00","연속"]
[13,"서울","직할","원남미아#1 T/L","22년 직할 변전협력 총액","-#6100 휴전 관련 사전조작","2022-11-01 10:00","2022-11-01 18:00","2022-11-01 10:00","2022-11-01 18:00","연속"]
[14,"서울","직할","원남미아#2 T/L","22년 직할 변전협력 총액","-#6100 휴전 관련 사전조작","2022-11-01 10:00","2022-11-01 18:00","2022-11-01 10:00","2022-11-01 18:00","연속"]
[15,"서울","성동","창동돈암 T/L","154kV 창동S/S 디지털화","154kV 창동S/S 디지털화 관련 ㅇ RTU - LID 제어케이블 이설 (170kV GIS, T/L 보호반 감시,제어,계측) ㅇ 현장 - SCADA 간 이설포인트 연동시험 등","2022-11-28 09:00","2022-11-29 18:00","2022-11-28 09:00","2022-11-29 18:00","연속"]
[16,"서울","성동","창동쌍문#1 T/L","154kV 창동S/S 디지털화","154kV 창동S/S 디지털화 관련 ㅇ RTU - LID 제어케이블 이설 (T/L 보호반 감시,제어,계측) ㅇ 현장 - SCADA 간 이설포인트 연동시험 등","2022-11-16 09:00","2022-11-16 18:00","2022-11-16 09:00","2022-11-16 18:00","연속"]
[17,"서울","성동","창동쌍문#2 T/L","154kV 창동S/S 디지털화","154kV 창동S/S 디지털화 관련 ㅇ RTU - LID 제어케이블 이설 (T/L 보호반 감시,제어,계측) ㅇ 현장 - SCADA 간 이설포인트 연동시험 등","2022-11-18 09:00","2022-11-18 18:00","2022-11-18 09:00","2022-11-18 18:00","연속"]
[18,"남서울","강남","신양재신사#2 T/L","신사S/S 신양재-신사#2T/L GIS 조작시험","신사S/S 신양재-신사#2T/L GIS 조작시험","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","연속"]
[19,"남서울","강남","신양재신사#3 T/L","21~22년 지중송전설비 위탁정비공사","신양재-신사#3T/L 맨홀 내 접지선 보강","2022-11-07 09:00","2022-11-12 06:00","2022-11-07 09:00","2022-11-12 06:00","연속"]
[20,"남서울","동서울","강동S/S #1 BUS","154kV 강동S/S #1M.Tr 교체공사","#1M.Tr 교체공사 무부하 가압","2022-11-24 10:00","2022-11-25 10:00","취소","취소","연속"]
[21,"남서울","동서울","염곡개포#2 T/L","154kV 염곡-개포T/L 누유개소 정비공사","154kV 염곡-개포#2T/L 누유개소 정비","2022-11-14 09:00","2022-11-25 18:00","2022-11-14 09:00","2022-11-25 18:00","연속"]
[22,"남서울","동서울","동서울위례#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 일부구간 지중화공사 관련 무부하 선로","2022-11-22 10:00","2022-11-23 18:00","2022-11-22 10:00","2022-11-23 18:00","연속"]
[23,"남서울","동서울","동서울S/S #68G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 일부구간 지중화공사 관련 무부하 선로","2022-11-27 10:00","2022-11-28 18:00","2022-11-27 10:00","2022-11-28 18:00","연속"]
[24,"남서울","동서울","동서울S/S #68G BUS","154kV 동서울-송파,가락T/L 지중화","154kV 동서울-송파#1T/L 무부하가압","2022-11-02 10:00","2022-11-03 10:00","2022-11-02 10:00","2022-11-03 10:00","연속"]
[25,"남서울","동서울","동서울S/S #68G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동 등 3개T/L 지중화공사 관련 무부하선로","2022-11-22 10:00","2022-11-23 18:00","2022-11-22 10:00","2022-11-23 18:00","연속"]
[26,"남서울","동서울","동서울위례#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동 등 3개T/L 지중화공사 무부하선로","2022-11-27 10:00","2022-11-28 18:00","2022-11-27 10:00","2022-11-28 18:00","연속"]
[27,"남서울","동서울","동서울S/S #68G BUS","동서울S/S 154kV #62D.Tr 현장개조 및 설치공사","#62D.Tr 교체 완료에 따른 무부하 가압","2022-11-08 09:00","2022-11-09 18:00","2022-11-14 09:00","2022-11-15 18:00","연속"]
[28,"남서울","동서울","동서울위례#1 T/L","동서울S/S 154kV #62D.Tr 현장개조 및 설치공사","#62D.Tr 교체 완료에 따른 무부하 가압","2022-11-08 09:00","2022-11-09 18:00","2022-11-14 09:00","2022-11-15 18:00","연속"]
[29,"남서울","동서울","동서울S/S #65G BUS","154kV 동서울-송파,가락T/L 지중화","154kV 동서울-송파#1T/L 무부하가압","2022-11-02 10:00","2022-11-03 10:00","2022-11-02 10:00","2022-11-03 10:00","연속"]
[30,"남서울","동서울","동서울S/S #66G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동 등 3개T/L 지중화공사 관련 무부하선로","2022-11-22 10:00","2022-11-23 18:00","2022-11-22 10:00","2022-11-23 18:00","연속"]
[31,"남서울","동서울","동서울S/S #67G BUS","154kV 동서울-송파,가락T/L 지중화","154kV 동서울-송파#1T/L 무부하가압","2022-11-02 10:00","2022-11-03 10:00","2022-11-02 10:00","2022-11-03 10:00","연속"]
[32,"남서울","동서울","동서울서종#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 일부구간 지중화공사","2022-11-24 09:00","2022-11-28 18:00","2022-11-24 09:00","2022-11-28 18:00","연속"]
[33,"남서울","동서울","동서울S/S #67G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 일부구간 지중화공사 관련 무부하 선로","2022-11-22 10:00","2022-11-23 18:00","2022-11-22 10:00","2022-11-23 18:00","연속"]
[34,"남서울","동서울","동서울S/S #65G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 일부구간 지중화공사 관련 무부하 선로","2022-11-27 10:00","2022-11-28 10:00","2022-11-27 10:00","2022-11-28 10:00","연속"]
[35,"남서울","동서울","동서울S/S #66G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 일부구간 지중화공사 관련 무부하 선로","2022-11-27 10:00","2022-11-28 18:00","2022-11-27 10:00","2022-11-28 18:00","연속"]
[36,"남서울","동서울","동서울S/S #66G BUS","154kV 동서울-송파,가락T/L 지중화","154kV 동서울-송파#1T/L 무부하가압","2022-11-02 10:00","2022-11-03 10:00","2022-11-02 10:00","2022-11-03 10:00","연속"]
[37,"남서울","동서울","동서울S/S #67G BUS","동서울S/S 154kV #62D.Tr 현장개조 및 설치공사","#62D.Tr 교체 완료에 따른 무부하 가압","2022-11-08 09:00","2022-11-09 18:00","2022-11-14 09:00","2022-11-15 18:00","연속"]
[38,"남서울","동서울","동서울서종#2 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동 등 3개T/L 지중화공사","2022-11-18 09:00","2022-11-23 18:00","2022-11-18 09:00","2022-11-23 18:00","연속"]
[39,"남서울","동서울","동서울S/S #67G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동 등 3개T/L 지중화공사 관련 무부하선로","2022-11-27 10:00","2022-11-28 18:00","2022-11-27 10:00","2022-11-28 18:00","연속"]
[40,"남서울","동서울","신장S/S CB 6100","동서울전력 22년 신규수용개폐장치 증설공사","동서울전력 22년 신규수용개폐장치 증설공사_ 신장변전소 2Bay 증설","2022-11-21 09:00","2022-11-27 18:00","2022-11-21 09:00","2022-11-27 18:00","연속"]
[41,"남서울","영등포","광명구공#3 T/L","광명S/S 장기사용 154kV GIS 교체","-광명-구공#3T/L GIS 교체 -#61, 66BUS PT 설치 -기타작업 -무부하 가압 선로(11.20-11.21)","2022-11-01 09:00","2022-11-21 18:00","2022-11-01 09:00","2022-11-21 18:00","연속"]
[42,"남서울","영등포","신광명광명#1 T/L","광명S/S 장기사용 154kV GIS 교체","-광명-구공#2T/L GIS 교체 -BUS-TIE 6200 설치 -기타작업 -#2BUS 무부하 가압 선로","2022-11-27 16:00","2022-11-28 18:00","2022-11-27 16:00","2022-11-28 18:00","연속"]
[43,"남서울","영등포","신광명광명#1 T/L","광명S/S 장기사용 154kV GIS 교체","-광명-구공#3T/L GIS 교체(#1BUS 철거, 설치) -#61, 66BUS PT 설치 -기타작업 -#1BUS 무부하 가압 선로(신광명광명#1T/L)","2022-11-08 18:00","2022-11-09 18:00","2022-11-08 18:00","2022-11-09 18:00","연속"]
[44,"남서울","영등포","신광명광명#1 T/L","광명S/S 장기사용 154kV GIS 교체","-광명-구공#3T/L GIS 교체(#2BUS 철거) -#61, 66BUS PT 설치 -기타작업 -#2BUS 무부하 가압 선로(신광명광명#1T/L)","2022-11-02 18:00","2022-11-03 18:00","2022-11-02 18:00","2022-11-03 18:00","연속"]
[45,"남서울","영등포","신광명광명#1 T/L","22-23년 가공송전 협력회사 총액공사(추락방지시설)","추락방지시설 설치공사","2022-11-22 07:30","2022-11-22 18:00","2022-11-22 07:30","2022-11-22 18:00","연속"]
[46,"남서울","영등포","신광명천왕#1 T/L","2022~23년 영등포P/O 변전협력회사 총액공사","154kV GIS 조작시험(신광명-천왕#1,2T/L)","2022-11-18 09:00","2022-11-18 14:00","2022-11-18 09:00","2022-11-18 14:00","연속"]
[47,"남서울","영등포","신광명천왕#2 T/L","2022~23년 영등포P/O 변전협력회사 총액공사","154kV GIS 조작시험(신광명-천왕#1,2T/L)","2022-11-18 14:00","2022-11-18 18:00","2022-11-18 14:00","2022-11-18 18:00","연속"]
[48,"남서울","직할","봉천신길#2 T/L","봉천-신길#2T/L 보호배전반 대체공사","봉천-신길#2T/L 보호배전반 대체공사 - 봉천, 신길 양단 시행","2022-11-07 09:00","2022-11-11 18:00","2022-11-07 09:00","2022-11-11 18:00","연속"]
[49,"인천","부평","관교만수#1 T/L","관교S/S, 만수S/S 관교만수#1T/L 보호반교체","관교S/S, 만수S/S 관교만수#1T/L 보호반교체","2022-11-01 09:00","2022-11-04 18:00","2022-11-01 09:00","2022-11-04 18:00","연속"]
[50,"인천","부평","부개S/S CB 6100","부개S/S SA혼용화관련 케이블 이설공사","부개S/S SA혼용화관련 케이블 이설공사","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","연속"]
[51,"인천","직할","신부평중동#2 T/L","중동S/S 신부평-중동2TL ES PAD CRACK부 보수","중동S/S 신부평-중동2TL ES PAD CRACK부 보수","2022-11-01 09:00","2022-11-02 18:00","2022-11-01 09:00","2022-11-02 18:00","연속"]
[52,"인천","직할","신부평중동#3 T/L","중동S/S 신부평중동 2T/L 무부하 가압용","중동S/S 신부평중동 2T/L 무부하 가압용","2022-11-02 12:00","2022-11-02 18:00","2022-11-02 12:00","2022-11-02 18:00","연속"]
[53,"인천","직할","신부평임학#2 T/L","임학S/S 신부평임학#2T/L GIS 정밀점검","154kV 임학S/S 신부평임학#2T/L GIS 정밀점검","2022-11-03 09:30","2022-11-05 18:00","2022-11-03 09:30","2022-11-05 18:00","연속"]
[54,"인천","부평","인천C/C CB 6100","인천C/C 6100GIS 보통점검","인천C/C 6100GIS 보통점검","2022-11-04 09:00","2022-11-04 13:00","2022-11-04 09:00","2022-11-04 13:00","연속"]
[55,"인천","직할","신부평중동#1 T/L","중동S/S 6200B/T 무부하 가압용","중동S/S 6200B/T 무부하 가압용","2022-11-04 12:00","2022-11-04 18:00","2022-11-04 12:00","2022-11-04 18:00","연속"]
[56,"인천","부평","인천남인천#2 T/L","남인천S/S 인천남인천#2T/L GIS 보통점검","남인천S/S 인천남인천#2T/L GIS 보통점검 - 인천S/S측 GIS 조작시험 병행","2022-11-05 09:00","2022-11-05 18:00","2022-11-05 09:00","2022-11-05 18:00","연속"]
[57,"인천","부평","남인천학익#1 T/L","남인천SS 남인천학익#1T/L GIS 정밀점검","남인천SS 남인천학익#1T/L GIS 정밀점검","2022-11-07 09:00","2022-11-11 18:00","2022-11-07 09:00","2022-11-11 18:00","연속"]
[58,"인천","시흥","시화동시화#2 T/L","동시화S/S 154kV 시화동시화#2T/L 보호반 대체","동시화S/S 154kV 시화동시화#2T/L 보호반 대체","2022-11-07 09:00","2022-11-11 18:00","취소","취소","연속"]
[59,"인천","직할","갈산S/S CB 6200","갈산S/S 6200,61-66,60-65SEC 모선보호반 계전기교체","갈산S/S 6200,61-66,60-65SEC 모선보호반 계전기교체","2022-11-07 09:30","2022-11-07 18:00","2022-11-07 09:30","2022-11-07 18:00","연속"]
[60,"인천","직할","갈산S/S SEC CB 65660","갈산S/S 6200,61-66,60-65SEC 모선보호반 계전기교체","갈산S/S 6200,61-66,60-65SEC 모선보호반 계전기교체","2022-11-07 09:30","2022-11-07 18:00","2022-11-07 09:30","2022-11-07 18:00","연속"]
[61,"인천","직할","갈산S/S SEC CB 60610","갈산S/S 6200,61-66,60-65SEC 모선보호반 계전기교체","갈산S/S 6200,61-66,60-65SEC 모선보호반 계전기교체","2022-11-07 09:30","2022-11-07 18:00","2022-11-07 09:30","2022-11-07 18:00","연속"]
[62,"인천","부평","인천C/C SEC CB 60610","인천C/C 60-61 SEC GIS 보통점검","인천C/C 60-61 SEC GIS 보통점검","2022-11-07 13:00","2022-11-07 18:00","2022-11-07 13:00","2022-11-07 18:00","연속"]
[63,"인천","부평","인천C/C SEC CB 65660","인천C/C 65-66 SEC GIS 보통점검","인천C/C 65-66 SEC GIS 보통점검","2022-11-09 09:00","2022-11-09 18:00","2022-11-09 09:00","2022-11-09 18:00","연속"]
[64,"인천","부평","신가좌주안#1 T/L","신가좌S/S 신가좌주안#1T/L GIS 보통점검 및 보조계전기 교체","신가좌S/S 신가좌주안#1T/L GIS 보통점검 및 보조계전기 교체 - 주안S/S 신가좌주안#1T/LGIS 보통점검, 4144GIS 조작","2022-11-12 09:00","2022-11-12 18:00","2022-11-12 09:00","2022-11-12 18:00","연속"]
[65,"인천","시흥","북시화서시화#3 T/L","북시화S/S, 서시화S/S 154kV 북시화서시화#3 TL GIS 보통점검","북시화S/S, 서시화S/S 154kV 북시화서시화#3 TL GIS 보통점검","2022-11-12 09:00","2022-11-12 18:00","2022-11-12 09:00","2022-11-12 18:00","연속"]
[66,"인천","직할","신부평고강#1 T/L","원종C/T EBA 비표준형 자기애관 교체공사","비표준형 자기애관 폴리머애관으로 교체","2022-11-12 09:00","2022-11-15 18:00","취소","취소","연속"]
[67,"인천","부평","영종중산 T/L","영종SS 영종중산T/L GIS 정밀점검","영종SS 영종중산T/L GIS 정밀점검","2022-11-14 09:00","2022-11-16 18:00","2022-11-14 09:00","2022-11-16 18:00","연속"]
[68,"인천","직할","계양북인천 T/L","북인천S/S 계양북인천T/L GIS 조작시험","북인천S/S 계양북인천T/L GIS 조작시험","2022-11-14 09:00","2022-11-14 14:00","2022-11-14 09:00","2022-11-14 14:00","연속"]
[69,"인천","김포","양촌양곡#1 T/L","154kV 양곡S/S #5,6M.Tr 증설공사","양곡S/S #1M.Tr 이설관련 무부하가압용","2022-11-14 15:00","2022-11-15 15:00","2022-11-14 15:00","2022-11-15 15:00","연속"]
[70,"인천","김포","양촌양곡#1 T/L","154kV 양곡S/S #5,6M.Tr 증설공사","양곡S/S 옥외 인출철구 철거관련 안전이격거리 확보","2022-11-16 09:00","2022-11-16 18:00","2022-11-16 09:00","2022-11-16 18:00","연속"]
[71,"인천","시흥","동시화서시화 T/L","서시화S/S 154kV 동시화서시화T/L GIS 보통점검","서시화S/S 154kV 동시화서시화T/L GIS 보통점검 동시화S/S 154kV 동시화서시화T/L GIS 조작시험","2022-11-16 09:00","2022-11-16 18:00","2022-11-16 09:00","2022-11-16 18:00","연속"]
[72,"인천","부평","신가좌주안#2 T/L","신가좌S/S 신가좌주안#2T/L GIS 보통점검 및 보조계전기 교체","신가좌S/S 신가좌주안#2T/L GIS 보통점검 및 보조계전기 교체 - 주안S/S 신가좌주안#2T/LGIS 보통점검, 4244GIS 조작","2022-11-19 09:00","2022-11-19 18:00","2022-11-19 09:00","2022-11-19 18:00","연속"]
[73,"인천","부평","신경서영종 T/L","신경서SS 신경서영종T/L GIS 정밀점검","신경서SS 신경서영종T/L GIS 정밀점검","2022-11-21 09:00","2022-11-25 18:00","2022-11-21 09:00","2022-11-25 18:00","연속"]
[74,"인천","부평","신경서S/S #61 BUS","신경서SS 신경서영종T/L GIS 정밀점검","신경서SS 신경서영종T/L GIS 정밀점검 관련 모선휴전","2022-11-21 09:00","2022-11-22 13:00","2022-11-21 09:00","2022-11-22 13:00","연속"]
[75,"인천","부평","신경서S/S #66 BUS","신경서SS 신경서영종T/L GIS 정밀점검","신경서SS 신경서영종T/L GIS 정밀점검 관련 모선휴전","2022-11-22 13:00","2022-11-23 18:00","2022-11-22 13:00","2022-11-23 18:00","연속"]
[76,"인천","부평","원창포스코CC#2 T/L","154kV 원창S/S SW 증설공사","154kV 원창S/S SW 증설공사 - #2BUS 측 무부하가압","2022-11-22 13:00","2022-11-23 13:00","2022-11-22 13:00","2022-11-23 13:00","연속"]
[77,"인천","시흥","신시흥S/S CB 6300","154kV 신시흥#2S/S #62-#67 모선보호반 대체공사","신시흥#2S/S 154kV #62-#67 모선보호반 대체","2022-11-24 08:00","2022-11-30 18:00","2022-11-24 08:00","2022-11-30 18:00","연속"]
[78,"인천","시흥","신시흥S/S SEC CB 61620","154kV 신시흥#2S/S #62-#67 모선보호반 대체공사","신시흥#2S/S 154kV #62-#67 모선보호반 대체","2022-11-24 08:00","2022-11-30 18:00","2022-11-24 08:00","2022-11-30 18:00","연속"]
[79,"인천","시흥","신시흥S/S SEC CB 62630","154kV 신시흥#2S/S #62-#67 모선보호반 대체공사","신시흥#2S/S 154kV #62-#67 모선보호반 대체","2022-11-24 08:00","2022-11-30 18:00","2022-11-24 08:00","2022-11-30 18:00","연속"]
[80,"인천","시흥","신시흥S/S SEC CB 66670","154kV 신시흥#2S/S #62-#67 모선보호반 대체공사","신시흥#2S/S 154kV #62-#67 모선보호반 대체","2022-11-24 08:00","2022-11-30 18:00","2022-11-24 08:00","2022-11-30 18:00","연속"]
[81,"인천","시흥","신시흥S/S SEC CB 67680","154kV 신시흥#2S/S #62-#67 모선보호반 대체공사","신시흥#2S/S 154kV #62-#67 모선보호반 대체","2022-11-24 08:00","2022-11-30 18:00","2022-11-24 08:00","2022-11-30 18:00","연속"]
[82,"인천","김포","신김포S/S CB 6200","신김포S/S 170kV 6200 TIE GIS 보통점검","신김포S/S 170kV 6200 TIE GIS 보통점검","2022-11-28 09:00","2022-11-28 18:00","2022-11-24 09:00","2022-11-24 18:00","연속"]
[83,"인천","시흥","남동동춘 T/L","남동S/S 154kV 남동동춘 T/L GIS 조작시험","남동S/S 154kV 남동동춘 T/L GIS 조작시험","2022-11-28 09:00","2022-11-28 18:00","2022-11-28 09:00","2022-11-28 18:00","연속"]
[84,"경기북부","고양","신덕은금촌#1 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","피뢰기 설치공사","2022-11-01 07:00","2022-11-01 12:00","2022-11-01 07:00","2022-11-01 12:00","연속"]
[85,"경기북부","고양","지도능곡#2 T/L","하반기 고양전력 170kV GIS 정밀점검","170kV GIS 정밀점검 시험가압 선로(기간중 1시간)","2022-11-02 09:00","2022-11-03 18:00","2022-11-02 09:00","2022-11-03 18:00","연속"]
[86,"경기북부","고양","신덕은S/S #60 BUS","신덕은S/S 170kV GIS PD센서 불량교체","신덕은S/S 170kV GIS PD센서 불량교체 - #2M.TR 1DS부(2MTR, 60BUS 휴전)","2022-11-07 09:00","2022-11-10 18:00","2022-11-07 09:00","2022-11-10 18:00","연속"]
[87,"경기북부","고양","신덕은금촌#2 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검","2022-11-01 12:00","2022-11-04 18:00","2022-11-01 12:00","2022-11-04 18:00","연속"]
[88,"경기북부","고양","신파주원흥#1 T/L","2022년 가공송전 순시점검 위탁공사","송전설비 정밀점검","2022-11-15 07:00","2022-11-18 18:00","2022-11-15 07:00","2022-11-18 18:00","연속"]
[89,"경기북부","고양","원흥S/S #2 BUS","154kV 원흥S/S #3M.Tr 증설공사","- M.Tr, 170kV GIS, 25.8kV GIS 무부하 가압","2022-11-23 09:00","2022-11-24 18:00","2022-11-23 09:00","2022-11-24 18:00","연속"]
[90,"경기북부","고양","원흥S/S #1 BUS","154kV 원흥S/S #3M.Tr 증설공사","- M.Tr, 170kV GIS, 25.8kV GIS 무부하 가압","2022-11-21 09:00","2022-11-22 18:00","2022-11-21 09:00","2022-11-22 18:00","연속"]
[91,"경기북부","고양","신파주원흥#2 T/L","154kV 원흥S/S #3M.Tr 증설공사","- M.Tr, 170kV GIS, 25.8kV GIS 시험가압 선로","2022-11-21 09:00","2022-11-24 18:00","2022-11-21 09:00","2022-11-24 18:00","연속"]
[92,"경기북부","고양","신파주원흥#1 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","피뢰기 설치공사","2022-11-01 07:00","2022-11-01 12:00","2022-11-01 07:00","2022-11-01 12:00","연속"]
[93,"경기북부","고양","신파주원흥#2 T/L","22~23년 고양전력지사 가공송전협력회사 총액공사","피뢰기 설치공사","2022-11-01 12:00","2022-11-01 18:00","2022-11-01 12:00","2022-11-01 18:00","연속"]
[94,"경기북부","구리","덕소진건#2 T/L","21-22년 지중송전설비 위탁정비공사","C/T 피뢰기 교체","2022-11-03 14:00","2022-11-03 18:00","2022-11-03 14:00","2022-11-03 18:00","연속"]
[95,"경기북부","구리","신장덕소#2 T/L","21-22년 지중송전설비 위탁정비공사","C/T 피뢰기 교체","2022-11-02 14:00","2022-11-02 18:00","2022-11-02 14:00","2022-11-02 18:00","연속"]
[96,"경기북부","구리","신장덕소#1 T/L","21-22년 지중송전설비 위탁정비공사","C/T 피뢰기 교체","2022-11-02 09:00","2022-11-02 14:00","2022-11-02 09:00","2022-11-02 14:00","연속"]
[97,"경기북부","구리","덕소팔당HP T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-11-10 14:00","2022-11-10 18:00","2022-11-10 14:00","2022-11-10 18:00","연속"]
[98,"경기북부","구리","덕소진건#1 T/L","21-22년 지중송전설비 위탁정비공사","C/T 피뢰기 교체","2022-11-03 09:00","2022-11-03 14:00","2022-11-03 09:00","2022-11-03 14:00","연속"]
[99,"경기북부","구리","덕소팔당HP청평HP T/L","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-11-10 09:00","2022-11-10 14:00","2022-11-10 09:00","2022-11-10 14:00","연속"]
[100,"경기북부","구리","미금S/S SEC CB 61620","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-11-09 09:00","2022-11-09 18:00","2022-11-09 09:00","2022-11-09 18:00","연속"]
[101,"경기북부","구리","미금화양 T/L","345kV 미금S/S #64M.Tr 개폐장치 설치공사","○ 6433 GIS 무부하가압","2022-11-02 10:00","2022-11-03 18:00","2022-11-02 10:00","2022-11-03 18:00","연속"]
[102,"경기북부","구리","별내도봉 T/L","154kV 장암S/S 옥내화 건설공사","○ 별내S/S 별내장암T/L 보호반 대체","2022-11-05 09:00","2022-11-16 18:00","2022-11-05 09:00","2022-11-16 18:00","연속"]
[103,"경기북부","구리","서종S/S CB 6100","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-11-15 09:00","2022-11-15 18:00","2022-11-15 09:00","2022-11-15 18:00","연속"]
[104,"경기북부","구리","서종S/S #60 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 일부구간 지중화공사 관련 무부하 선로","2022-11-27 09:50","2022-11-27 10:00","2022-11-27 09:50","2022-11-27 10:00","연속"]
[105,"경기북부","구리","신포천동두천#1 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치(수평)","2022-11-18 07:00","2022-11-24 18:00","2022-11-18 07:00","2022-11-24 18:00","연속"]
[106,"경기북부","구리","신포천포천#1 T/L","2022년 직할 가공송전 순시점검 위탁공사","송전선로 정밀점검","2022-11-02 08:00","2022-11-02 18:00","2022-11-02 08:00","2022-11-02 18:00","연속"]
[107,"경기북부","구리","신포천동두천#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치(수평)","2022-11-03 07:00","2022-11-11 18:00","2022-11-03 07:00","2022-11-11 18:00","연속"]
[108,"경기북부","구리","용문S/S CB 6100","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-11-08 09:00","2022-11-08 18:00","취소","취소","연속"]
[109,"경기북부","구리","도봉진접 T/L","154kV 장암S/S 옥내화 건설공사","○ 진접S/S 장암진접T/L 보호반 대체","2022-11-18 09:00","2022-11-30 18:00","2022-11-18 09:00","2022-11-30 18:00","연속"]
[110,"경기북부","구리","청평H/P #4M.Tr CB","22-23 구리전력 변전협력 총액공사","154kV GIS 보통점검","2022-11-04 09:00","2022-11-04 18:00","취소","취소","연속"]
[111,"경기북부","구리","청평H/P CB 6100","22-23 구리전력 변전협력 총액공사","154kV GCB 보통점검","2022-11-16 09:00","2022-11-16 18:00","2022-11-16 09:00","2022-11-16 18:00","연속"]
[112,"경기북부","구리","청평H/P #2 M.Tr CB","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","청평수력 #2M.Tr 2차 GCB 조작시험","2022-11-29 09:00","2022-11-29 14:00","취소","취소","연속"]
[113,"경기북부","구리","청평H/P #1 M.Tr CB","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","청평수력 #1M.Tr 2차 GCB 조작시험","2022-11-30 09:00","2022-11-30 14:00","취소","취소","연속"]
[114,"경기북부","구리","청평H/P #3 M.Tr CB","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","청평수력 #3M.Tr 2차 GCB 조작시험","2022-11-29 14:00","2022-11-29 18:00","취소","취소","연속"]
[115,"경기북부","구리","청평HP의암HP T/L","22-23 구리전력 변전협력 총액공사","154kV GCB 보통점검","2022-11-17 09:00","2022-11-17 18:00","2022-11-17 09:00","2022-11-17 18:00","연속"]
[116,"경기북부","구리","청평P/P #1 M.Tr CB","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","청평양수 #1M.Tr 2차 GCB 조작시험","2022-11-16 14:00","2022-11-16 18:00","취소","취소","연속"]
[117,"경기북부","구리","청평P/P #2 M.Tr CB","22∼23년 경기북부본부 구리전력지사 변전협력회사 총액공사","청평양수 #2M.Tr 2차 GCB 조작시험","2022-11-16 09:00","2022-11-16 14:00","취소","취소","연속"]
[118,"경기북부","구리","팔당H/P CB 6100","22-23 구리전력 변전협력 총액공사","154kV GIS 초기점검","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[119,"경기북부","구리","신포천포천#2 T/L","154kV 포천변전소 옥내화 토건공사","LA기초 설치 시 안전이격 확보","2022-11-07 09:00","2022-12-02 18:00","2022-11-07 09:00","2022-12-02 18:00","연속"]
[120,"경기북부","구리","포천운천#2 T/L","154kV 신의정부-내촌 등 3개 T/L 철탑추락방지시설 설치공사","철탑추락방지시설 설치(수평)","2022-11-07 07:00","2022-11-08 18:00","2022-11-07 07:00","2022-11-08 18:00","연속"]
[121,"경기북부","구리","용정포천#1 T/L","154kV 포천변전소 옥내화 토건공사","LA기초 설치 시 안전이격 확보","2022-11-09 09:00","2022-12-02 18:00","2022-11-09 09:00","2022-12-02 18:00","연속"]
[122,"경기북부","구리","포천운천#1 T/L","2022년 직할 가공송전 순시점검 위탁공사","송전선로 정밀점검(154kV 신포천-포천#1 T/L 병가선로)","2022-11-02 08:00","2022-11-02 18:00","2022-11-02 08:00","2022-11-02 18:00","연속"]
[123,"경기북부","직할","양주녹양#2 T/L","녹양변전소 누수구간 보수공사","- 외벽 및 창호 코킹 보수 - 선홈통 보수","2022-11-05 09:00","2022-11-05 18:00","2022-11-05 09:00","2022-11-05 18:00","연속"]
[124,"경기북부","직할","녹양백석#1 T/L","녹양변전소 누수구간 보수공사","- 외벽 및 창호 코킹 보수 - 선홈통 보수","2022-11-05 09:00","2022-11-05 18:00","2022-11-05 09:00","2022-11-05 18:00","연속"]
[125,"경기북부","직할","양주녹양#2 T/L","22-23 변전협력 총액공사","170kV GIS 개폐타임 측정","2022-11-29 09:00","2022-11-29 18:00","2022-11-29 09:00","2022-11-29 18:00","연속"]
[126,"경기북부","직할","신의정부송우#1 T/L","신의정부S/S 154kV Sh.C 이설공사","신의정부S/S 154kV Sh.C용 GIS 설치 - 170kV GIS #67BUS 측 조립 - 무부하 시험가압","2022-11-28 08:00","2022-12-02 18:00","2022-11-28 08:00","2022-12-02 18:00","연속"]
[127,"경기북부","직할","신의정부S/S #62 BUS","신의정부S/S 154kV Sh.C 이설공사","신의정부S/S 154kV Sh.C용 GIS 설치 - 170kV GIS #62BUS 측 조립 - 무부하 시험가압","2022-11-28 08:00","2022-12-02 18:00","2022-11-28 08:00","2022-12-02 18:00","연속"]
[128,"경기북부","직할","옥정송우#2 T/L","2022년 직할 가공송전 순시점검 위탁공사","송전선로 정밀점검","2022-11-25 08:00","2022-11-25 18:00","2022-11-25 08:00","2022-11-25 18:00","연속"]
[129,"경기북부","직할","옥정동두천#1 T/L","2022년 직할 가공송전 순시점검 위탁공사","송전선로 정밀점검","2022-11-23 08:00","2022-11-25 18:00","2022-11-23 08:00","2022-11-25 18:00","연속"]
[130,"경기북부","직할","옥정송우#1 T/L","2022년 직할 가공송전 순시점검 위탁공사","송전선로 정밀점검","2022-11-15 08:00","2022-11-26 18:00","2022-11-15 08:00","2022-11-16 18:00","연속"]
[131,"경기북부","직할","옥정동두천#2 T/L","2022년 직할 가공송전 순시점검 위탁공사","송전선로 정밀점검","2022-11-11 08:00","2022-11-15 18:00","2022-11-11 08:00","2022-11-15 18:00","연속"]
[132,"경기북부","직할","옥정송우#1 T/L","철탑추락방지시설 설치공사","ㅇ 수평추락방지시설 설치 - 대상 : 154kV 옥정-송우T/L No.4호등 6개소","2022-11-01 07:00","2022-11-01 18:00","2022-11-01 07:00","2022-11-01 18:00","연속"]
[133,"경기북부","직할","용현도봉#2 T/L","154kV 장암S/S 옥내화 건설공사","○ 용현S/S 용현장암#2T/L 보호반 대체","2022-11-18 09:00","2022-11-30 18:00","2022-11-18 09:00","2022-11-30 18:00","연속"]
[134,"경기북부","직할","장암S/S #61 BUS","154kV 장암S/S 옥내화 건설공사","○ 장암방학#2T/L, 별내장암T/L 무부하가압","2022-11-14 10:00","2022-11-15 18:00","2022-11-14 10:00","2022-11-15 18:00","연속"]
[135,"경기북부","직할","장암진접#1 T/L","154kV 장암S/S 옥내화 건설공사","○ 장암진접T/L 무부하가압 ○ 장암진접T/L GIS 사용전검사","2022-11-28 10:00","2022-11-30 18:00","2022-11-28 10:00","2022-11-30 18:00","연속"]
[136,"경기북부","직할","장암S/S #61 BUS","154kV 장암S/S 옥내화 건설공사","○ 용현장암#2T/L, 장암진접T/L 무부하가압","2022-11-28 10:00","2022-11-29 18:00","2022-11-28 10:00","2022-11-29 18:00","연속"]
[137,"경기북부","직할","용현장암#2 T/L","154kV 장암S/S 옥내화 건설공사","○ 용현장암#2T/L 무부하가압 ○ 용현장암#2T/L GIS 사용전검사","2022-11-28 10:00","2022-11-30 18:00","2022-11-28 10:00","2022-11-30 18:00","연속"]
[138,"경기북부","직할","장암S/S #60 BUS","154kV 장암S/S 옥내화 건설공사","○ 용현장암#2T/L, 장암진접T/L 무부하가압","2022-11-28 10:00","2022-11-29 18:00","2022-11-28 10:00","2022-11-29 18:00","연속"]
[139,"경기북부","직할","장암방학#2 T/L","154kV 장암S/S 옥내화 건설공사","○ 장암방학#2T/L 무부하가압 ○ 장암방학#2T/L GIS 사용전검사","2022-11-14 10:00","2022-11-16 18:00","2022-11-14 10:00","2022-11-16 18:00","연속"]
[140,"경기북부","직할","별내장암#1 T/L","154kV 장암S/S 옥내화 건설공사","○ 별내장암T/L 무부하가압 ○ 별내장암T/L GIS 사용전검사","2022-11-14 10:00","2022-11-16 18:00","2022-11-14 10:00","2022-11-16 18:00","연속"]
[141,"경기북부","구리","서종S/S #65 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 일부구간 지중화공사 관련 무부하 선로","2022-11-22 09:50","2022-11-22 10:00","2022-11-22 09:50","2022-11-22 10:00","연속"]
[142,"경기","군포","남군포산본#1 T/L","남군포S/S 154kV SW증설공사","남군포S/S 154kV SW증설공사 무부하가압 -현대모비스T/LGIS 증설 -서서울-남군포#3T/L GIS 증설","2022-11-14 09:00","2022-11-15 18:00","2022-11-14 09:00","2022-11-15 18:00","연속"]
[143,"경기","군포","남군포산본#1 T/L","남군포S/S 154kV SW증설공사","남군포S/S 154kV SW증설공사 무부하가압 -현대모비스T/LGIS 증설 -서서울-남군포#3T/L GIS 증설","2022-11-07 09:00","2022-11-08 18:00","2022-11-07 09:00","2022-11-08 18:00","연속"]
[144,"경기","군포","남군포산본#2 T/L","남군포S/S 154kV SW증설공사","남군포S/S 154kV SW증설공사 무부하가압 -남군포-의왕#1,#2T/L GIS 증설","2022-11-24 09:00","2022-11-25 18:00","2022-11-24 09:00","2022-11-25 18:00","연속"]
[145,"경기","군포","사강남양#2 T/L","2022년 가공송전 순시점검 위탁공사","154kV 남양-사강T/L 초기점검","2022-11-28 09:00","2022-11-28 18:00","2022-11-28 09:00","2022-11-28 18:00","매일"]
[146,"경기","군포","사강남양#1 T/L","2022년 가공송전 순시점검 위탁공사","154kV 남양-사강T/L 초기점검","2022-11-29 09:00","2022-11-29 18:00","2022-11-29 09:00","2022-11-29 18:00","매일"]
[147,"경기","군포","마도사강#2 T/L","154kV 마도S/S #4M.Tr 증설공사","마도S/S #4M.Tr 증설공사(154kV GIS 증설) #2BUS 무부하가압","2022-11-15 09:00","2022-11-16 18:00","2022-11-15 09:00","2022-11-16 18:00","연속"]
[148,"경기","군포","마도사강#2 T/L","154kV 마도S/S #4M.Tr 증설공사","마도S/S #4M.Tr 증설공사 -#4M.Tr 무부하가압","2022-11-30 09:00","2022-12-01 18:00","2022-11-30 09:00","2022-12-01 18:00","연속"]
[149,"경기","군포","마도사강#2 T/L","154kV 마도S/S #4M.Tr 증설공사","마도S/S #4M.Tr 증설공사(154kV GIS 증설) #1BUS 무부하가압","2022-11-21 09:00","2022-11-22 18:00","2022-11-21 09:00","2022-11-22 18:00","연속"]
[150,"경기","군포","목내성곡#1 T/L","목내-성곡#1T/L 보호배전반 대체공사","목내-성곡#1T/L 보호배전반 대체공사","2022-11-14 09:00","2022-11-16 18:00","2022-11-21 09:00","2022-11-23 18:00","연속"]
[151,"경기","군포","서서울#2서안양 T/L","인정프린스아파트 지장송전선로 지중화공사","인클로징철탑 4기(No.4,5,7,8)","2022-11-07 08:00","2022-11-20 18:00","2022-11-07 08:00","2022-11-20 18:00","연속"]
[152,"경기","군포","서서울#2일동#1 T/L","서서울2-일동#1T/L 보호배전반 대체공사","서서울2-일동#1T/L 보호배전반 대체공사 서서울#2S/S 서서울2-일동#1T/L GIS 보통점검 송전 : LA 및 C/T 점검","2022-11-07 09:00","2022-11-09 18:00","2022-11-07 09:00","2022-11-09 18:00","연속"]
[153,"경기","군포","서서울#2소래 T/L","인정프린스아파트 지장송전선로 지중화공사","인클로징철탑 4기(No.4,5,7,8)","2022-11-21 08:00","2022-12-02 18:00","2022-11-21 08:00","2022-12-02 18:00","연속"]
[154,"경기","군포","서서울#2소래 T/L","인정프린스아파트 지장송전선로 지중화공사","인클로징철탑 4기(No.4,5,7,8)","2022-11-01 08:00","2022-11-06 18:00","2022-11-01 08:00","2022-11-06 18:00","연속"]
[155,"경기","군포","서서울S/S #66 BUS","154kV 서서울-남군포 #3T/L SW증설공사","154kV 서서울-남군포 #3T/L SW증설공사 -무부하가압","2022-11-09 13:00","2022-11-10 18:00","2022-11-09 13:00","2022-11-10 18:00","연속"]
[156,"경기","군포","서서울산본#1 T/L","154kV 서서울-남군포#3T/L SW증설공사","무부하가압선로","2022-11-09 09:00","2022-11-10 18:00","2022-11-09 09:00","2022-11-10 18:00","연속"]
[157,"경기","군포","장덕마도 T/L","현대자동차1TL 선종변경공사 무부하가압","현대자동차1TL 선종변경공사 무부하가압","2022-11-01 09:00","2022-11-02 09:00","2022-11-04 09:00","2022-11-05 18:00","연속"]
[158,"경기","군포","서서울S/S #61 BUS","154kV 서서울-남군포 #3T/L SW증설공사","154kV 서서울-남군포 #3T/L SW증설공사 -무부하가압","2022-11-09 09:00","2022-11-09 13:00","2022-11-09 09:00","2022-11-09 13:00","연속"]
[159,"경기","동부","성현S/S CB 6100","22년 동부 변전정비 총액공사","성현:6100(조작),6179(조작)","2022-11-18 09:30","2022-11-18 14:00","2022-11-18 09:30","2022-11-18 14:00","연속"]
[160,"경기","동부","초월성현#1 T/L","154kV 성현S/S 디지털화 공사","154kV 초월성현#1T/L 혼용시스템 이설","2022-11-07 09:00","2022-11-08 14:00","취소","취소","연속"]
[161,"경기","동부","초월성현#2 T/L","154kV 성현S/S 디지털화 공사","154kV 초월성현#2T/L 혼용시스템 이설","2022-11-08 14:00","2022-11-09 18:00","취소","취소","연속"]
[162,"경기","동부","성현분당#1 T/L","154kV 성현S/S 디지털화 공사","154kV 성현분당#1T/L 혼용시스템 이설","2022-11-03 09:00","2022-11-04 14:00","취소","취소","연속"]
[163,"경기","동부","성현분당#2 T/L","피뢰기, CVT 보통점검","피뢰기, CVT 보통점검","2022-11-04 14:00","2022-11-05 18:00","2022-11-04 09:30","2022-11-04 18:00","연속"]
[164,"경기","동부","왕암여주#1 T/L","22년 동부 변전정비 총액공사","여주:왕암-여주#1T/L(초기,LA보통)","2022-11-23 09:30","2022-11-23 18:00","2022-11-23 09:30","2022-11-23 18:00","연속"]
[165,"경기","동부","왕암여주#2 T/L","22년 동부 변전정비 총액공사","여주:왕암-여주#2T/L(초기,LA보통)","2022-11-24 09:30","2022-11-24 18:00","2022-11-24 09:30","2022-11-24 18:00","연속"]
[166,"경기","동부","초월성현#1 T/L","초월S/S 154kV #5M.Tr 증설공사","초월S/S 154kV #5M.Tr 증설 무부하가압선로","2022-11-28 09:30","2022-11-29 18:00","취소","취소","연속"]
[167,"경기","동부","분당S/S CB 6200","22년 동부 변전정비 총액공사","분당SS 6200 보통점검","2022-11-15 09:30","2022-11-15 18:00","2022-11-15 09:30","2022-11-15 18:00","연속"]
[168,"경기","성남","남사동탄#2 T/L","21-22년 지중송전 위탁정비공사(평택전력)","피뢰기 열화진단(절연열화 측정 및 부싱청소)","2022-11-09 09:00","2022-11-11 18:00","2022-11-02 09:00","2022-11-04 18:00","연속"]
[169,"경기","성남","신성남S/S CB 6200","2022년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험 - 순간압력센서 설치","2022-11-11 09:00","2022-11-11 18:00","2022-11-11 09:00","2022-11-11 18:00","연속"]
[170,"경기","성남","신용인S/S CB 6400","170kV 효성제 GIS 스프링 조작기 교체공사","- 스프링 조작기 교체","2022-11-18 09:00","2022-11-18 18:00","2022-11-18 09:00","2022-11-18 18:00","연속"]
[171,"경기","성남","신용인S/S SEC CB 62630","170kV 효성제 GIS 스프링 조작기 교체공사","- 스프링 조작기 교체","2022-11-23 09:00","2022-11-23 18:00","2022-11-23 09:00","2022-11-23 18:00","연속"]
[172,"경기","성남","신용인S/S SEC CB 67680","170kV 효성제 GIS 스프링 조작기 교체공사","- 스프링 조작기 교체","2022-11-22 09:00","2022-11-22 18:00","2022-11-22 09:00","2022-11-22 18:00","연속"]
[173,"경기","성남","오천용인#2 T/L","170kV 효성제 GIS 스프링 조작기 교체공사","- 스프링 조작기 교체","2022-11-30 09:00","2022-11-30 18:00","취소","취소","연속"]
[174,"경기","성남","오천용인#1 T/L","170kV 효성제 GIS 스프링 조작기 교체공사","- 스프링 조작기 교체","2022-11-29 09:00","2022-11-29 18:00","취소","취소","연속"]
[175,"경기","성남","신용인용인#2 T/L","170kV 효성제 GIS 스프링 조작기 교체공사","- 스프링 조작기 교체","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","연속"]
[176,"경기","성남","용인덕성#2 T/L","170kV 효성제 GIS 스프링 조작기 교체공사","- 스프링 조작기 교체","2022-11-04 09:00","2022-11-04 18:00","2022-11-04 09:00","2022-11-04 18:00","연속"]
[177,"경기","성남","용인덕성#1 T/L","170kV 효성제 GIS 스프링 조작기 교체공사","- 스프링 조작기 교체","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[178,"경기","성남","모현용인#1 T/L","154kV 모현-용인T/L 지장철탑 이설공사","154kV 모현-용인T/L 지장철탑 이설공사","2022-11-11 09:00","2022-11-20 18:00","2022-11-11 09:00","2022-11-20 18:00","연속"]
[179,"경기","성남","모현용인#2 T/L","154kV 모현-용인T/L 지장철탑 이설공사","154kV 모현-용인T/L 지장철탑 이설공사","2022-11-21 09:00","2022-11-30 18:00","2022-11-21 09:00","2022-11-30 18:00","연속"]
[180,"경기","직할","과천동안양#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 12기","2022-11-08 07:00","2022-11-08 18:00","2022-11-08 07:00","2022-11-08 18:00","매일"]
[181,"경기","직할","의왕동안양#1 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 40기","2022-11-08 07:00","2022-11-14 18:00","2022-11-01 07:00","2022-11-5 18:00","매일"]
[182,"경기","직할","의왕동안양#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 40기","2022-11-01 07:00","2022-11-07 18:00","2022-11-16 07:00","2022-11-21 18:00","매일"]
[183,"경기","직할","율전의왕#1 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 40기","2022-11-02 07:00","2022-11-03 18:00","2022-11-02 07:00","2022-11-03 18:00","매일"]
[184,"경기","직할","율전의왕#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 40기","2022-11-09 07:00","2022-11-10 18:00","2022-11-17 07:00","2022-11-18 18:00","매일"]
[185,"경기","직할","신봉이의#1 T/L","율전-동수원#2T/L EBA해체점검 공사 안전이격거리 확보","율전-동수원#2T/L B상 EBA해체점검 안전이격거리 확보","2022-11-09 09:00","2022-11-18 18:00","2022-11-09 09:00","2022-11-18 18:00","연속"]
[186,"경기","직할","화성S/S SEC CB 65660","화성S/S 154kV 장기사용 GIS 교체공사(4차)","GIS 대체","2022-11-01 09:00","2022-12-11 18:00","2022-11-01 09:00","2022-12-11 18:00","연속"]
[187,"경기","직할","화성S/S #66 BUS","화성S/S 154kV 장기사용 GIS 교체공사(4차)","#65-66BUS SEC분리","2022-11-01 09:00","2022-11-02 13:00","2022-11-01 09:00","2022-11-02 13:00","연속"]
[188,"경기","직할","화성S/S #65 BUS","화성S/S 154kV 장기사용 GIS 교체공사(4차)","#65-66BUS SEC 및 2DS 분리","2022-11-02 13:00","2022-11-11 18:00","2022-11-02 13:00","2022-11-11 18:00","연속"]
[189,"경기","직할","화성수촌#1 T/L","화성S/S 154kV 장기사용 GIS 교체공사(4차)","GIS 대체","2022-11-04 13:00","2022-12-08 18:00","2022-11-05 09:00","2022-12-08 18:00","연속"]
[190,"경기","직할","화성마도 T/L","화성S/S 154kV 장기사용 GIS 교체공사(4차)","#65-66BUS SEC 및 2DS 분리 후 무부하가압","2022-11-11 09:00","2022-11-11 18:00","2022-11-11 09:00","2022-11-11 18:00","연속"]
[191,"경기","직할","화성S/S #61 BUS","화성S/S 154kV 장기사용 GIS 교체공사(4차)","#60-61BUS SEC 분리","2022-11-11 18:00","2022-11-13 18:00","2022-11-11 18:00","2022-11-13 18:00","연속"]
[192,"경기","직할","화성수촌#2 T/L","화성S/S 154kV 장기사용 GIS 교체공사(4차)","#60-61BUS SEC 분리 안전이격거리 및 무부하가압","2022-11-12 09:00","2022-11-13 18:00","2022-11-12 09:00","2022-11-13 18:00","연속"]
[193,"경기","직할","화성S/S SEC CB 60610","화성S/S 154kV 장기사용 GIS 교체공사(4차)","GIS 대체","2022-11-12 09:00","2022-11-27 18:00","2022-11-12 09:00","2022-11-27 18:00","연속"]
[194,"경기","직할","화성S/S #60 BUS","화성S/S 154kV 장기사용 GIS 교체공사(4차)","1DS, CB 등 GIS 대체","2022-11-13 18:00","2022-11-24 18:00","2022-11-13 18:00","2022-11-24 18:00","연속"]
[195,"경기","직할","화성마도 T/L","화성S/S 154kV 장기사용 GIS 교체공사(4차)","1DS, CB 등 GIS 대체 후 무부하가압","2022-11-23 09:00","2022-11-24 18:00","2022-11-23 09:00","2022-11-24 18:00","연속"]
[196,"경기","직할","화성S/S #61 BUS","화성S/S 154kV 장기사용 GIS 교체공사(4차)","#60-61BUS SEC 도킹","2022-11-24 18:00","2022-11-27 18:00","2022-11-24 18:00","2022-11-27 18:00","연속"]
[197,"경기","직할","화성수촌#2 T/L","화성S/S 154kV 장기사용 GIS 교체공사(4차)","#60-61BUS SEC 도킹 안전이격거리 및 무부하가압","2022-11-26 09:00","2022-11-27 18:00","2022-11-26 09:00","2022-11-27 18:00","연속"]
[198,"경기","직할","화성S/S #65 BUS","화성S/S 154kV 장기사용 GIS 교체공사(4차)","2DS 설치 등 GIS 대체","2022-11-27 18:00","2022-12-06 18:00","2022-11-27 18:00","2022-12-06 18:00","연속"]
[199,"경기","직할","화성마도 T/L","2022-23 경기본부 직할변전협력회사 총액공사","GIS 조작시험 및 LA 대체 등","2022-11-09 09:00","2022-11-01 14:00","2022-11-09 09:00","2022-11-09 14:00","연속"]
[200,"경기","직할","화성장덕 T/L","2022-23 경기본부 직할변전협력회사 총액공사","GIS 조작시험 및 LA 대체 등","2022-11-09 14:00","2022-11-09 18:00","2022-11-09 14:00","2022-11-09 18:00","연속"]
[201,"경기","직할","봉담남수원#1 T/L","봉담S/S #1M.Tr 증설관련 앵글측정","봉담S/S #1M.Tr 증설관련 앵글측정","2022-11-04 09:00","2022-11-04 18:00","2022-11-04 16:00","2022-11-04 18:00","연속"]
[202,"경기","평택","고덕송탄#1 T/L","일진제 170kV GIS 인출DS 인터록 개선","고덕S/S 고덕-송탄#1T/L GIS 인출DS 인터록 개선","2022-11-01 10:00","2022-11-01 18:00","2022-11-01 10:00","2022-11-01 18:00","연속"]
[203,"경기","평택","서운삼죽 T/L","154kV 삼죽#5M.Tr 증설공사","154kV #2BUS측 무부하 가압","2022-11-25 18:00","2022-11-26 18:00","2022-11-25 18:00","2022-11-26 18:00","연속"]
[204,"강원","직할","남춘천춘천 T/L","2022~2023년 강원본부 직할 변전협력회사 총액공사","남춘천S/S SA혼용운영시스템 설치공사","2022-11-01 09:00","2022-11-03 18:00","2022-11-29 09:00","2022-11-30 18:00","연속"]
[205,"강원","동해","이원동해TP T/L","345kV 동해-안인개폐소 등 5개T/L 철탑추락방지장치 설치공사","154kV 동해화력T/L(이원동해TP T/L, 10기)철탑추락방지장치(수평) 설치","2022-11-02 07:00","2022-11-02 18:00","2022-11-02 07:00","2022-11-02 18:00","연속"]
[206,"강원","원주","상남S/S #61 BUS","상남S/S 모선구분차단기 설치공사","60-61 BUS SEC 및 PT집합반 설치 관련 시험","2022-11-02 09:00","2022-11-03 18:00","2022-11-02 09:00","2022-11-03 18:00","연속"]
[207,"강원","원주","상남S/S #1 BUS","상남S/S 모선구분차단기 설치공사","60-61 BUS SEC 및 PT집합반 설치 관련 시험","2022-11-02 09:00","2022-11-03 18:00","취소","취소","연속"]
[208,"강원","태백","영월S/S CB 6100","22-23년 태백전력지사 변전정비회사 총액공사","영월S/S 154kV B/P 보호반 대체","2022-11-02 09:00","2022-11-04 18:00","2022-11-01 09:00","2022-11-04 18:00","연속"]
[209,"강원","태백","영월S/S 영월G/T#1T/L CB","2022년 태백전력지사 154KV GIS 정밀점검공사","영월S/S 154kV 영월G/T #1T/L GIS 정밀점검","2022-11-02 09:00","2022-11-04 18:00","취소","취소","연속"]
[210,"강원","동해","이원삼척 T/L","345kV 동해-안인개폐소 등 5개T/L 철탑추락방지장치 설치공사","154kV 삼척분기T/L(이원-삼척T/L, 39기)철탑추락방지장치(수평) 설치","2022-11-03 07:00","2022-11-07 18:00","2022-11-03 07:00","2022-11-07 18:00","매일"]
[211,"강원","동해","동해정선 T/L","2022년 동해전력지사 가공송전 순시점검 위탁공사","154kV 동해-정선T/L No.249~250 경간 지장수목벌채","2022-11-04 07:00","2022-11-04 18:00","2022-11-04 07:00","2022-11-04 18:00","연속"]
[212,"강원","직할","서홍천춘천열병합 T/L","2022년 가공송전 순시점검 위탁공사","154kV 서홍천분기 병가구간 (No.8~23) 정밀점검","2022-11-07 09:00","2022-11-10 18:00","취소","취소","연속"]
[213,"강원","동해","도계태백 T/L","154kV 도계변전소 외장재 교체 공사","산불 화재 확산 방지를 위한 노후 드라이비트 철거 및 메탈패널 교체","2022-11-07 10:00","2022-11-11 18:00","2022-11-07 10:00","2022-11-11 18:00","연속"]
[214,"강원","동해","삼척동해TP T/L","345kV 동해-안인개폐소 등 5개T/L 철탑추락방지장치 설치공사","154kV 삼척분기, 동해화력T/L(삼척-동해TPT/L, 39+10기)철탑추락방지장치(수평) 설치","2022-11-08 07:00","2022-11-11 18:00","2022-11-08 07:00","2022-11-11 18:00","매일"]
[215,"강원","강릉","강릉영동TP T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV 탈황설비 GIS 대체, 170kV GIS 디지털변환, GIS 기초 보강(터파기, 거푸집 설치)","2022-11-08 08:00","2022-11-10 17:00","2022-11-08 08:00","2022-11-10 17:00","매일"]
[216,"강원","강릉","동해영동TP T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV 탈황설비 GIS 대체, 170kV GIS 디지털변환, GIS 기초 보강(터파기, 거푸집 설치)","2022-11-08 08:00","2022-11-10 18:00","2022-11-08 08:00","2022-11-10 18:00","매일"]
[217,"강원","원주","신제천남원주#1 T/L","2022년 원주전력지사 170kV GIS 정밀점검공사","GIS 정밀점검","2022-11-08 09:00","2022-11-10 18:00","취소","취소","연속"]
[218,"강원","강릉","북평영동TP#2 T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV GIS 7CCT 대체, 170kV GIS 디지털변환, #1BUS 시험가압 (BUS TIE, BUS PT, 북평-영동TP #1,2T/L)","2022-11-11 17:00","2022-11-12 17:00","2022-11-11 17:00","2022-11-12 17:00","연속"]
[219,"강원","동해","북평영동TP#1 T/L","345kV 동해안인개폐소 등 5개T/L 철탑추락방지장치 설치공사","154kV 북평영동TP#1 추락방지장치(수평분) 24기 설치","2022-11-13 08:00","2022-11-14 18:00","2022-11-13 08:00","2022-11-14 18:00","매일"]
[220,"강원","동해","동해강릉 T/L","345kV 동해안인개폐소 등 5개T/L 철탑추락방지장치 설치공사","154kV 동해강릉T/L 추락방지장치(수평분) 병가구간 6기 설치","2022-11-13 08:00","2022-11-13 18:00","2022-11-13 08:00","2022-11-13 18:00","연속"]
[221,"강원","직할","인제양구#1 T/L","154kV 상제 등 3개T/L 추락방지장치 설치공사","154kV 양구 T/L NO.1~66 호 추락방지장치 설치공사","2022-11-14 08:00","2022-11-25 18:00","2022-11-14 08:00","2022-11-25 18:00","연속"]
[222,"강원","직할","철원화천#2 T/L","22~23년 강원직할 가공송전 협력회사 총액공사","추락방지장치 설치공사","2022-11-14 08:00","2022-11-20 18:00","2022-11-14 08:00","2022-11-20 18:00","연속"]
[223,"강원","강릉","영동T/P #2 BUS","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV GIS 7CCT 대체, 170kV GIS 디지털변환, #2BUS 설치 (BUS TIE, BUS PT, 북평-영동TP #1,2T/L)","2022-11-14 09:00","2022-12-07 17:00","2022-11-14 09:00","2022-12-07 17:00","연속"]
[224,"강원","강릉","북평영동TP#2 T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV GIS 7CCT 대체, 170kV GIS 디지털변환, #2BUS 설치 (BUS TIE, BUS PT)","2022-11-14 09:00","2022-11-16 18:00","2022-11-14 09:00","2022-11-16 18:00","매일"]
[225,"강원","동해","동해영동TP T/L","345kV 동해안인개폐소 등 5개T/L 철탑추락방지장치 설치공사","154kV 동해영동TP 추락방지장치(수평분) 병가구간 6기 설치","2022-11-15 08:00","2022-11-15 18:00","2022-11-15 08:00","2022-11-15 18:00","연속"]
[226,"강원","직할","남춘천춘천열병합#2 T/L","2022~2023년 강원본부 직할 변전협력회사 총액공사","남춘천S/S SA혼용운영시스템 설치공사","2022-11-15 09:00","2022-11-16 18:00","취소","취소","연속"]
[227,"강원","강릉","주진평창#1 T/L","2022년 강원본부 주진S/S #3M.Tr 증설공사","주진S/S #3M.Tr 1차측 154kV GIS 증설(154kV #1, 2 BUS 측 GIS 설치)","2022-11-17 09:00","2022-11-29 18:00","2022-11-18 09:00","2022-12-01 18:00","연속"]
[228,"강원","강릉","주진S/S #2 BUS","2022년 강원본부 주진S/S #3M.Tr 증설공사","주진S/S #3M.Tr 1차측 154kV GIS 증설(154kV #2 BUS 측 GIS 설치)","2022-11-17 09:00","2022-11-22 18:00","2022-11-18 09:00","2022-11-23 18:00","연속"]
[229,"강원","강릉","주진둔내#1 T/L","2022년 강원본부 주진S/S #3M.Tr 증설공사","주진S/S #3M.Tr 1차측 154kV GIS 증설(154kV #1, 2 BUS 측 GIS 설치)","2022-11-17 09:00","2022-11-29 18:00","2022-11-18 09:00","2022-12-01 18:00","연속"]
[230,"강원","강릉","주진S/S CB 6100","2022년 강원본부 주진S/S #3M.Tr 증설공사","주진S/S #3M.Tr 1차측 154kV GIS 증설(154kV #2 BUS 측 GIS 설치)","2022-11-17 09:00","2022-11-22 18:00","2022-11-18 09:00","2022-11-23 18:00","연속"]
[231,"강원","직할","남춘천춘천열병합#1 T/L","2022~2023년 강원본부 직할 변전협력회사 총액공사","남춘천S/S SA혼용운영시스템 설치공사","2022-11-17 09:00","2022-11-18 18:00","취소","취소","연속"]
[232,"강원","태백","고한영월 T/L","154kV 영월-고한-태백간 OPGW 교체공사","- OPGW(OP-S-S48) 0.576km 교체 - OPGW(OP-S-L48) 0.79km 시설","2022-11-18 08:00","2022-11-20 18:00","2022-11-18 08:00","2022-11-22 18:00","연속"]
[233,"강원","강릉","북평영동TP#2 T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","170kV GIS 7CCT 대체, 170kV GIS 디지털변환, #2BUS 설치 (북평-영동TP #1,2T/L)","2022-11-21 08:00","2022-11-24 18:00","2022-11-21 08:00","2022-11-24 18:00","매일"]
[234,"강원","직할","철원화천#1 T/L","22~23년 강원직할 가공송전 협력회사 총액공사","추락방지장치 설치공사","2022-11-21 08:00","2022-11-25 18:00","2022-11-21 08:00","2022-11-25 18:00","연속"]
[235,"강원","강릉","신제천주진#2 T/L","2022년 강원본부 주진S/S #3M.Tr 증설공사","주진S/S #3M.Tr 1차측 154kV GIS 증설(154kV #2 BUS 무부하 가압선로)","2022-11-21 09:00","2022-11-22 18:00","2022-11-22 09:00","2022-11-23 18:00","연속"]
[236,"강원","직할","홍천남춘천 T/L","2022~23년 변전정비 총액공사","○ 남춘천S/S SA혼용운영시스템 설치공사 - 대상 : 154kV 홍천-남춘천 T/L","2022-11-21 09:00","2022-11-22 18:00","취소","취소","연속"]
[237,"강원","강릉","주진S/S CB 6100","2022년 강원본부 주진S/S #3M.Tr 증설공사","주진S/S #3M.Tr 1차측 154kV GIS 증설(154kV #1 BUS 측 GIS 설치)","2022-11-23 09:00","2022-11-29 18:00","2022-11-24 09:00","2022-12-01 18:00","연속"]
[238,"강원","강릉","주진S/S #1 BUS","2022년 강원본부 주진S/S #3M.Tr 증설공사","주진S/S #3M.Tr 1차측 154kV GIS 증설(154kV #1 BUS 측 GIS 설치)","2022-11-23 09:00","2022-11-29 18:00","2022-11-23 09:00","2022-11-29 18:00","연속"]
[239,"강원","직할","상남인제#1 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 양구 T/L No.1~9 병가구간 추락방지장치 설치","2022-11-24 08:00","2022-11-25 18:00","2022-11-24 08:00","2022-11-25 18:00","매일"]
[240,"강원","직할","북춘천화천HP T/L","22~23년 강원직할 가공송전 협력회사 총액공사","추락방지장치 설치공사","2022-11-26 08:00","2022-11-30 18:00","2022-11-26 08:00","2022-11-30 18:00","연속"]
[241,"강원","직할","인제양구#2 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 양구 T/L 추락방지장치 설치공사","2022-11-26 09:00","2022-12-03 18:00","2022-11-26 09:00","2022-12-03 18:00","연속"]
[242,"강원","태백","태백삼척GP#2 T/L","154kV 태백-삼척GP#2T/L 태초에너지 연계 공사","태백S/S, 삼척GP S/Y 154kV 태백-삼척GP#2 T/L PNL 교체, 태초에너지(주) 사용전 검사","2022-11-27 09:00","2022-11-27 13:00","2022-11-27 09:00","2022-11-27 13:00","연속"]
[243,"강원","강릉","신제천주진#2 T/L","2022년 강원본부 주진S/S #3M.Tr 증설공사","주진S/S #3M.Tr 1차측 154kV GIS 증설(154kV #1 BUS 무부하 가압 선로)","2022-11-28 09:00","2022-11-29 18:00","2022-11-30 09:00","2022-12-01 18:00","연속"]
[244,"충북","직할","신진천S/S #67 BUS","22년 직할 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압을 위한 휴전","2022-11-23 09:00","2022-11-23 18:00","취소","취소","연속"]
[245,"충북","직할","신진천S/S #67 BUS","22년 직할 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압을 위한 휴전","2022-11-16 09:00","2022-11-16 18:00","취소","취소","연속"]
[246,"충북","직할","신진천S/S #67 BUS","22년 직할 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압을 위한 휴전","2022-11-12 09:00","2022-11-12 18:00","2022-11-12 09:00","2022-11-12 18:00","연속"]
[247,"충북","직할","신진천S/S #67 BUS","22년 직할 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압을 위한 휴전","2022-11-09 09:00","2022-11-09 18:00","2022-11-09 09:00","2022-11-09 18:00","연속"]
[248,"충북","직할","신진천S/S #66 BUS","신진천변전소 #66BUS 가스누기개소 현장조치","신진천변전소 154kV GIS 배관 연결부 가스 누기개소 현장조치","2022-11-07 09:00","2022-11-08 18:00","취소","취소","연속"]
[249,"충북","직할","신진천진천#1 T/L","신진천변전소 #66BUS 가스누기개소 현장조치 (무부하가압)","신진천변전소 154kV GIS 배관 연결부 가스 누기개소 현장조치","2022-11-08 09:00","2022-11-08 18:00","취소","취소","연속"]
[250,"충북","직할","신진천S/S CB 6300","22년 직할 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압을 위한 휴전","2022-11-09 09:00","2022-11-09 18:00","2022-11-09 09:00","2022-11-09 18:00","연속"]
[251,"충북","직할","신진천S/S CB 6300","22년 직할 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압을 위한 휴전","2022-11-12 09:00","2022-11-12 18:00","2022-11-12 09:00","2022-11-12 18:00","연속"]
[252,"충북","직할","신진천S/S CB 6300","22년 직할 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압을 위한 휴전","2022-11-16 09:00","2022-11-16 18:00","2022-11-16 09:00","2022-11-16 18:00","연속"]
[253,"충북","직할","신진천S/S CB 6300","22년 직할 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압을 위한 휴전","2022-11-23 09:00","2022-11-23 18:00","2022-11-23 09:00","2022-11-23 18:00","연속"]
[254,"충북","직할","신진천S/S SEC CB 61620","'22년 직할 154kV GIS 정밀점검공사","GIS 조작부 정밀점검 및 전자변교체","2022-11-26 08:00","2022-11-26 18:00","취소","취소","연속"]
[255,"충북","직할","신진천S/S SEC CB 66670","'22년 직할 154kV GIS 정밀점검공사","GIS 조작부 정밀점검 및 전자변교체","2022-11-27 08:00","2022-11-27 18:00","취소","취소","연속"]
[256,"충북","직할","신진천S/S CB 6200","신진천변전소 #66BUS 가스누기개소 현장조치","신진천변전소 154kV GIS 배관 연결부 가스 누기개소 현장조치","2022-11-07 09:00","2022-11-08 18:00","2022-11-07 09:00","2022-11-08 18:00","연속"]
[257,"충북","직할","신진천진천#1 T/L","154kV 신진천-오창T/L OPGW 증설공사","신진천-진천#1T/L 29~30호 OPGW 교체 (신진천-오창#2T/L 병가구간)","2022-11-05 07:00","2022-11-05 18:00","취소","취소","연속"]
[258,"충북","직할","신진천진천#2 T/L","154kV 신진천-오창T/L OPGW 증설공사","신진천-오창#1T/L 2~30호 OPGW 증설 (신진천-진천#2T/L 병가구간)","2022-11-12 07:00","2022-11-12 18:00","취소","취소","연속"]
[259,"충북","청주","남청주오송#1 T/L","22-23년 청주전력 변전총액공사","- 154kV GIS 보통점검(전자변교체) - 남청주오송#1T/L 보호반 노후 교체","2022-11-05 09:00","2022-11-06 18:00","2022-11-05 09:00","2022-11-06 18:00","연속"]
[260,"충북","청주","국사봉명#1 T/L","2022~2023년도 청주전력지사 송전협력회사 총액공사","1. 공 사 명 : 2022~2023년도 청주전력지사 송전협력회사 총액공사 2. 공사장소 : 154kV 국사-봉명T/L No.11~26(14기) 3. 공사내역 : 추락방지시설 설치","2022-11-22 07:00","2022-11-23 18:00","2022-11-22 07:00","2022-11-23 18:00","매일"]
[261,"충북","청주","국사봉명#2 T/L","2022~2023년도 청주전력지사 송전협력회사 총액공사","1. 공 사 명 : 2022~2023년도 청주전력지사 송전협력회사 총액공사 2. 공사장소 : 154kV 국사-봉명T/L No.11~26(14기) 3. 공사내역 : 추락방지시설 설치","2022-11-24 07:00","2022-11-25 18:00","2022-11-24 07:00","2022-11-25 18:00","매일"]
[262,"충북","청주","신진천오창#1 T/L","154kV 문백-오창 송전선로 건설공사","구간 : (기설)154kV 신진천-오창T/L No.21-23 ∼ (신설)154kV 문백S/S S/T 전력선 및 선로길이 ○ ACSR 410㎟×2B×4C–0.046km ○ ACSR 410㎟×2B×2C–0.539km 지지물 ○ 설치 : 3기 [관형주 3기(신설C/H 2C, No.1 4C), 산형강 1기(가철탑 1C)] ○ 제각 : 1기 [산형강 1기","2022-11-08 09:00","2022-11-12 18:00","취소","취소","연속"]
[263,"충북","청주","신진천오창#2 T/L","154kV 문백-오창 송전선로 건설공사","구간 : (기설)154kV 신진천-오창T/L No.21-23 ∼ (신설)154kV 문백S/S S/T 전력선 및 선로길이 ○ ACSR 410㎟×2B×4C–0.046km ○ ACSR 410㎟×2B×2C–0.539km 지지물 ○ 설치 : 3기 [관형주 3기(신설C/H 2C, No.1 4C), 산형강 1기(가철탑 1C)] ○ 제각 : 1기 [산형강 1기]","2022-11-03 09:00","2022-11-07 18:00","취소","취소","연속"]
[264,"충북","청주","옥천보은 T/L","22~23년 송전협력회사 총액공사","고정형 폴리머 점퍼 지지애자 교체, 추락방지시설 설치","2022-11-15 08:00","2022-11-21 18:00","취소","취소","매일"]
[265,"충북","청주","신옥천옥천#2 T/L","22~23년 송전협력회사 총액공사","고정형 폴리머 점퍼 지지애자 교체, 추락방지시설 설치","2022-11-15 08:00","2022-11-18 18:00","2022-11-15 08:00","2022-11-18 18:00","매일"]
[266,"충북","청주","신옥천옥천#1 T/L","22~23년 송전협력회사 총액공사","고정형 폴리머 점퍼 지지애자 교체, 추락방지시설 설치","2022-11-07 08:00","2022-11-08 18:00","2022-11-07 08:00","2022-11-08 18:00","매일"]
[267,"충북","청주","옥천영동 T/L","22~23년 송전협력회사 총액공사","고정형 폴리머 점퍼 지지애자 교체, 추락방지시설 설치","2022-11-07 08:00","2022-11-11 18:00","취소","취소","매일"]
[268,"충북","충주","감곡S/S CB 6100","22년 충주전력지사 170kV GIS정밀점검공사","감곡S/S #3M.Tr 단로기 링크개선 #2BUS 무부하가압","2022-11-26 09:00","2022-11-26 18:00","취소","취소","연속"]
[269,"충북","충주","감곡S/S CB 6100","22년 충주전력지사 170KV GIS 정밀점검공사","감곡S/S #1M.Tr 1차GIS 정밀점검 무부하가압","2022-11-19 09:00","2022-11-19 18:00","취소","취소","연속"]
[270,"충북","충주","감곡S/S CB 6100","22년 충주전력지사 170KV GIS 정밀점검공사","감곡S/S #2M.Tr 1차GIS 정밀점검 부하가압","2022-11-22 09:00","2022-11-22 18:00","취소","취소","연속"]
[271,"충북","충주","감곡S/S CB 6100","22년 충주전력지사 170KV GIS 정밀점검공사","감곡S/S #3M.Tr 단로기 링크개선 #1BUS 무부하가압","2022-11-24 09:00","2022-11-24 18:00","취소","취소","연속"]
[272,"충북","충주","신충주감곡#2 T/L","22년 충주전력지사 170KV GIS 정밀점검공사","감곡S/S 신충주감곡#2T/L GIS 정밀점검","2022-11-21 09:00","2022-11-22 18:00","2022-11-21 09:00","2022-11-22 18:00","연속"]
[273,"충북","충주","문경단양 T/L","2022년 충주전력 가공송전선로 순시점검 위탁공사","154kV 단양T/L 지장수목벌채 시행","2022-11-28 08:00","2022-11-29 15:00","취소","취소","매일"]
[274,"충북","충주","신제천S/S SEC CB 61620","22-23년 충주전력지사 변전정비총액공사","61-62 BUS SEC GIS 보통점검","2022-11-11 09:00","2022-11-11 14:00","취소","취소","연속"]
[275,"충북","충주","신제천S/S SEC CB 66670","22-23년 충주전력지사 변전정비총액공사","66-67 BUS SEC GIS 보통점검","2022-11-11 14:00","2022-11-11 18:00","취소","취소","연속"]
[276,"충북","충주","신제천왕암#2 T/L","154kV 신제천-제천T/L 용량증대 전선교체공사","전력선 교체 : 38경간 추락방지 장치 : 수직 10기, 수평 36기 설치","2022-11-01 07:00","2022-11-03 18:00","2022-11-01 07:00","2022-11-03 18:00","연속"]
[277,"충북","충주","신제천주진#1 T/L","22-23년 충주전력지사 변전정비총액공사","LA 대체","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","연속"]
[278,"충북","충주","신제천S/S SEC CB 60610","22-23년 충주전력지사 변전정비총액공사","60-61 BUS SEC GIS 보통점검","2022-11-10 09:00","2022-11-10 14:00","취소","취소","연속"]
[279,"충북","충주","신제천S/S SEC CB 65660","22-23년 충주전력지사 변전정비총액공사","65-66 BUS SEC GIS 보통점검","2022-11-10 14:00","2022-11-10 18:00","2022-11-10 14:00","2022-11-10 18:00","연속"]
[280,"충북","충주","왕암여주#2 T/L","2022년 충주전력지사 가공송전 순시점검 위탁공사","154kV 왕암-여주#2T/L No.1~10 정밀점검","2022-11-14 09:00","2022-11-15 18:00","2022-11-14 09:00","2022-11-15 18:00","매일"]
[281,"충북","충주","왕암여주#1 T/L","2022년 충주전력지사 가공송전 순시점검 위탁공사","154kV 왕암-여주#1T/L No.1~10 정밀점검","2022-11-21 09:00","2022-11-22 18:00","2022-11-21 09:00","2022-11-22 18:00","매일"]
[282,"충북","충주","음성금왕#2 T/L","직할 가공송전 협력회사 총액공사 (추락방지시설 설치공정)","추락방지시설 설치 No. 7 ~ 40, 34기","2022-11-01 08:00","2022-11-08 18:00","취소","취소","매일"]
[283,"충북","충주","음성금왕#1 T/L","직할 가공송전 협력회사 총액공사 (추락방지시설 설치공정)","추락방지시설 설치 No. 7 ~ 40, 34기, 주말제외","2022-11-09 08:00","2022-11-22 18:00","취소","취소","매일"]
[284,"충북","충주","충주충주HP#2 T/L","154kV 왕암-충주 등 5개 T/L 불량 압축인류클램프 교체공사","154kV 충주-충주HP T/L 불량 압축인류클램프 교체공사","2022-11-21 07:00","2022-11-30 18:00","2022-11-21 08:00","2022-11-30 18:00","연속"]
[285,"충북","충주","충주충주HP#1 T/L","154kV 왕암-충주 등 5개 T/L 불량 압축인류클램프 교체공사","154kV 충주-충주HP T/L 불량 압축인류클램프 교체공사","2022-11-14 08:00","2022-11-18 18:00","2022-12-01 08:00","2022-12-07 18:00","연속"]
[286,"충북","청주","남청주청주#1 T/L","2022~2023년도 청주전력지사 송전협력회사 총액공사","1. 공 사 명 : 2022~2023년도 청주전력지사 송전협력회사 총액공사 2. 공사장소 : 154kV 남청주-청주T/L No.1~88(46기) 3. 공사내역 : 아킹혼설치","2022-11-28 07:00","2022-11-29 18:00","2022-11-28 07:00","2022-11-29 18:00","연속"]
[287,"충북","청주","남청주청주#3 T/L","2022~2023년도 청주전력지사 송전협력회사 총액공사","1. 공 사 명 : 2022~2023년도 청주전력지사 송전협력회사 총액공사 2. 공사장소 : 154kV 남청주-청주T/L No.1~88(46기) 3. 공사내역 : 아킹혼설치","2022-11-28 07:00","2022-11-29 18:00","2022-11-28 07:00","2022-11-29 18:00","연속"]
[288,"충북","직할","서운광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 삼죽-광혜원T/L ↔ 154kV 서운-광혜원T/L 간 임시회로 구성 (공사기간 중 삼죽S/S 임시 전력공급용)","2022-11-04 09:00","2022-11-20 18:00","취소","취소","연속"]
[289,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 삼죽-광혜원T/L ↔ 154kV 서운-광혜원T/L 간 임시회로 구성 원복 (공사기간 중 삼죽S/S 임시 전력공급용)","2022-11-20 09:00","2022-11-20 18:00","2022-11-20 09:00","2022-11-20 18:00","연속"]
[290,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 삼죽-광혜원T/L ↔ 154kV 서운-광혜원T/L 간 임시회로 구성 (공사기간 중 삼죽S/S 임시 전력공급용)","2022-11-05 09:00","2022-11-05 18:00","2022-11-05 09:00","2022-11-05 18:00","연속"]
[291,"충북","직할","진천광혜원#1 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 장기사용 GIS 대체작업","2022-11-21 09:00","2022-11-25 18:00","2022-11-21 09:00","2022-11-25 18:00","연속"]
[292,"대전세종충남","대전","금산무주#2 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 금산-무주T/L 철탑 추락방지시설 설치공사","2022-11-16 08:00","2022-11-24 18:00","2022-11-22 08:00","2022-11-30 18:00","매일"]
[293,"대전세종충남","대전","추부금산#2 T/L","[송전] 154kV 가수원-서대전 등 6개T/L 피뢰기 설치공사","[송전] 154kV 신옥천-추부T/L 피뢰기 설치공사 안전거리 확보차","2022-11-28 08:00","2022-11-28 11:00","취소","취소","연속"]
[294,"대전세종충남","대전","남대전신흥#2 T/L","남대전S/S 154kV 노후 GIS 교체공사(3차분)","667,6333 교체","2022-11-21 09:00","2022-12-23 18:00","2022-11-28 08:00","2022-12-16 18:00","연속"]
[295,"대전세종충남","대전","서대전유천#2 T/L","서대전S/S 154kV 장기사용 GIS 교체공사(2차분)","647,657,6333 교체","2022-11-06 09:00","2022-12-02 18:00","2022-11-06 09:00","2022-12-02 18:00","연속"]
[296,"대전세종충남","대전","신옥천서대전 T/L","서대전S/S 154kV 장기사용 GIS 교체공사(2차분)","647,657,6333 교체","2022-11-06 09:00","2022-12-02 18:00","2022-11-06 09:00","2022-12-02 18:00","연속"]
[297,"대전세종충남","대전","가수원서대전#2 T/L","서대전S/S 154kV 장기사용 GIS 교체공사(2차분)","647,657,6333 교체","2022-11-23 14:00","2022-11-24 14:00","2022-11-23 14:00","2022-11-24 14:00","연속"]
[298,"대전세종충남","대전","서대전S/S CB 6100","서대전S/S 154kV 장기사용 GIS 교체공사(2차분)","647,657,6333 교체","2022-11-23 14:00","2022-11-24 14:00","2022-11-23 14:00","2022-11-24 14:00","연속"]
[299,"대전세종충남","대전","논산은진#2 T/L","은진S/S 154kV 모선구분차단기 설치공사","#1BUS 무부하가압","2022-11-15 14:00","2022-11-16 14:00","2022-11-15 14:00","2022-11-16 14:00","연속"]
[300,"대전세종충남","대전","신옥천추부#2 T/L","[송전] 154kV 가수원-서대전 등 6개T/L 피뢰기 설치공사","[송전] 154kV 신옥천-추부T/L 피뢰기 설치공사","2022-11-25 08:00","2022-11-29 18:00","취소","취소","매일"]
[301,"대전세종충남","대전","추부금산#1 T/L","[송전] 154kV 가수원-서대전 등 6개T/L 피뢰기 설치공사","[송전] 154kV 신옥천-추부T/L 피뢰기 설치공사","2022-11-28 11:00","2022-12-07 18:00","취소","취소","매일"]
[302,"대전세종충남","대전","추부금산#2 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 추부-금산T/L 철탑 추락방지시설 설치공사","2022-11-03 08:00","2022-11-17 18:00","2022-11-09 08:00","2022-11-23 18:00","매일"]
[303,"대전세종충남","대전","신옥천추부#1 T/L","[송전] 345kV 신옥천-청양 등 17개T/L 추락방지시설 설치공사","[송전] 154kV 신옥천-추부T/L 철탑 추락방지시설 설치공사","2022-11-01 08:00","2022-11-07 18:00","2022-11-07 08:00","2022-11-11 18:00","매일"]
[304,"대전세종충남","서산","서산해미 T/L","154kV 신당진-서산 등 4개T/L 피뢰기설치공사","154kV 서산-해미T/L 피뢰기설치공사(No.65~138)","2022-11-07 08:00","2022-11-11 18:00","2022-11-21 08:00","2022-11-25 18:00","매일"]
[305,"대전세종충남","서산","서산홍성 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 신당진-서산#1T/L 피뢰기설치[No.2,3(154kV 서산-홍성T/L)]","2022-11-01 08:00","2022-11-01 18:00","취소","취소","연속"]
[306,"대전세종충남","서산","신당진서산#2 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 서산-해미T/L 피뢰기설치[No.136,137(154kV 신당진-서산#2T/L)]","2022-11-07 08:00","2022-11-07 18:00","취소","취소","연속"]
[307,"대전세종충남","서산","당진송악#2 T/L","상간스페이서설치공사","154kV 당진-송악 상간스페이서설치공사(11.24) : No.27~28 * 154kV 합덕-송악#1T/L 10월분 휴전 취소시 (4회선구간)","2022-11-29 08:00","2022-11-29 18:00","취소","취소","연속"]
[308,"대전세종충남","서산","당진송악#1 T/L","상간스페이서설치공사","154kV 당진-송악 상간스페이서설치공사(11.28) : No.27~28 * 154kV 합덕-송악#2T/L 10월분 휴전 취소시 (4회선구간)","2022-11-24 08:00","2022-11-24 18:00","취소","취소","연속"]
[309,"대전세종충남","서산","신당진서산#1 T/L","154kV 신당진-서산 등 4개T/L 피뢰기 설치공사","154kV 신당진-서산#1T/L 피뢰기설치(No.1~55)","2022-11-01 08:00","2022-11-04 18:00","취소","취소","매일"]
[310,"대전세종충남","서산","합덕송악#1 T/L","점퍼지지애자 교체공사 및 상간스페이서설치공사","154kV 합덕-송악 애자교체공사(11.22~23) : No.2,8,28,30,48 154kV 합덕-송악 상간스페이서설치공사(11.24) : No.85~86 * 154kV 합덕-송악#1T/L 10월분 휴전 취소시","2022-11-29 08:00","2022-12-01 18:00","취소","취소","매일"]
[311,"대전세종충남","서산","합덕송악#2 T/L","점퍼지지애자 교체공사 및 상간스페이서설치공사","154kV 합덕-송악 상간스페이서설치공사(11.28) : No.85~86 154kV 합덕-송악 애자교체공사(11.29~12.1) : No.5,15,35,37,41,44,49 * 154kV 합덕-송악#2T/L 10월분 휴전 취소시","2022-11-22 08:00","2022-11-24 18:00","취소","취소","매일"]
[312,"대전세종충남","서산","해미홍성 T/L","성능저하 점퍼지지애자 교체공사","154kV 해미-홍성T/L 점퍼지지애자 교체공사 - No.4, 9","2022-11-11 08:00","2022-11-11 18:00","취소","취소","연속"]
[313,"대전세종충남","세종","신풍공주#1 T/L","[송전]154kV 신풍-공주#1T/L 추락방지시설 설치공사","[송전]154kV 신풍-공주#1T/L 추락방지시설 설치공사 - No. 1, 1-1~1-14, 49~74 (41기)","2022-11-07 07:00","2022-11-30 18:00","2022-11-07 07:00","2022-11-30 18:00","매일"]
[314,"대전세종충남","세종","덕진공주#1 T/L","[변전]2022년 세종P/O 154kV GIS 정밀점검공사","154kV GIS 정밀점검 시행(10BAY)","2022-11-01 09:00","2022-11-03 18:00","2022-11-01 09:00","2022-11-03 18:00","연속"]
[315,"대전세종충남","세종","덕진대화#1 T/L","[송전] 154kV 덕진-대화T/L No.4~7 지장송전선로 지중화공사","154kV 덕진-대화T/L No.4~7 지장송전선로 지중화공사(요청자 직접시행) ○ 선로명 : 154kV 덕진-대화#1,2T/L ○ 선종 및 길이 : XLPE 1,200㎟ × 2C × S, 1.318km","2022-11-26 07:00","2022-11-30 18:00","2022-11-26 07:00","2022-11-30 18:00","연속"]
[316,"대전세종충남","세종","덕진대화#2 T/L","[송전] 154kV 덕진-대화T/L No.4~7 지장송전선로 지중화공사","154kV 덕진-대화T/L No.4~7 지장송전선로 지중화공사(요청자 직접시행) ○ 선로명 : 154kV 덕진-대화#1,2T/L ○ 선종 및 길이 : XLPE 1,200㎟ × 2C × S, 1.318km","2022-11-22 07:00","2022-11-25 18:00","2022-11-22 07:00","2022-11-25 18:00","연속"]
[317,"대전세종충남","세종","서세종조치원 T/L","[지중]22~23년 지중송전설비 위탁정비공사","○ 지중송전 EBA 절연유 채유 및 분석 의뢰(3상)","2022-11-30 09:00","2022-12-01 18:00","2022-11-30 09:00","2022-12-01 18:00","연속"]
[318,"대전세종충남","세종","세종서세종#2 T/L","[변전]'22년 세종P/O 변전협력회사 총액공사","-세종S/S 154kV 세종-서세종#2T/L PNL PDA 불량보수","2022-11-02 09:00","2022-11-02 18:00","2022-11-02 09:00","2022-11-02 18:00","연속"]
[319,"대전세종충남","세종","세종S/S #60 BUS","345kV 세종S/S #1M.Tr 2차 GIS 설치공사(전문)","345kV #1M.Tr 2차 GIS 1CCT 설치","2022-11-01 09:00","2022-11-04 14:00","2022-11-01 09:00","2022-11-04 14:00","연속"]
[320,"대전세종충남","세종","세종서세종#2 T/L","345kV 세종S/S #1M.Tr 2차 GIS 설치공사(전문)","345kV #1M.Tr 2차 GIS 1CCT 설치","2022-11-03 14:00","2022-11-04 14:00","2022-11-03 14:00","2022-11-04 14:00","연속"]
[321,"대전세종충남","세종","세종S/S #65 BUS","345kV 세종S/S #1M.Tr 2차 GIS 설치공사(전문)","345kV #1M.Tr 2차 GIS 1CCT 설치","2022-11-07 09:00","2022-11-10 14:00","2022-11-07 09:00","2022-11-10 14:00","연속"]
[322,"대전세종충남","세종","세종서세종#2 T/L","345kV 세종S/S #1M.Tr 2차 GIS 설치공사(전문)","345kV #1M.Tr 2차 GIS 1CCT 설치","2022-11-09 14:00","2022-11-10 14:00","2022-11-09 14:00","2022-11-10 14:00","연속"]
[323,"대전세종충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 - #2T/L No.36~39호 전력선 연,긴선 및 인수검사","2022-11-22 07:00","2022-11-29 18:00","2022-11-14 07:00","2022-11-23 18:00","연속"]
[324,"대전세종충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 - #2T/L 휴전작업에 따른 안전거리확보 * 유사시 #1T/L 긴급가압 가능","2022-11-07 07:00","2022-11-07 18:00","2022-10-31 07:00","2022-11-02 18:00","연속"]
[325,"대전세종충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 - 임시선로 구성(#2T/L) 기설 37호 - 가철탑 37호","2022-11-07 07:00","2022-11-07 18:00","2022-10-31 07:00","2022-11-02 18:00","연속"]
[326,"대전세종충남","세종","조치원전의#2 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 - #1T/L 휴전작업에 따른 안전거리확보 * 유사시 #2T/L 긴급가압 가능","2022-11-08 07:00","2022-11-21 18:00","2022-11-03 07:00","2022-11-11 18:00","연속"]
[327,"대전세종충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 - 37호 신설 철탑조립 - #1T/L No.36~39호 전력선 연,긴선 및 인수검사","2022-11-08 07:00","2022-11-21 18:00","2022-11-03 07:00","2022-11-11 18:00","연속"]
[328,"대전세종충남","세종","조치원전의#1 T/L","[송전]154kV 조치원-전의T/L 안전이격거리확보공사","○ 공사구간 : 154kV 조치원-전의T/L No.36~39 - #2T/L 휴전작업에 따른 안전거리확보 * 유사시 #1T/L 긴급가압 가능","2022-11-22 07:00","2022-11-29 18:00","2022-11-14 07:00","2022-11-23 18:00","연속"]
[329,"대전세종충남","직할","신흥동대전#1 T/L","170kV GIS 보통점검(동대전)","GIS 보통점검","2022-11-08 09:00","2022-11-08 18:00","2022-11-08 09:00","2022-11-08 18:00","연속"]
[330,"대전세종충남","직할","신흥동대전#3 T/L","170kV GIS 보통점검(동대전)","GIS 보통점검","2022-11-10 09:00","2022-11-10 18:00","2022-11-10 09:00","2022-11-10 18:00","연속"]
[331,"대전세종충남","직할","신흥동대전#2 T/L","170kV GIS 보통점검(동대전)","GIS 보통점검","2022-11-09 09:00","2022-11-09 18:00","2022-11-09 09:00","2022-11-09 18:00","연속"]
[332,"대전세종충남","직할","신탄진대청HP T/L","신탄진S/S 신탄진-대청HP T/L #1DS 조작함 교체","#1DS 조작함 교체","2022-11-01 09:00","2022-11-01 18:00","2022-11-01 09:00","2022-11-01 18:00","연속"]
[333,"대전세종충남","천안","신온양석곡#2 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","[4회선 병가철탑 안전거리확보] 154kV 신온양-한샘#2T/L No.2~7 추락방지시설(수평) 설치","2022-11-07 08:00","2022-11-07 18:00","2022-11-05 08:00","2022-11-05 18:00","연속"]
[334,"대전세종충남","천안","신온양석곡#1 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","[4회선 병가철탑 안전거리확보] 154kV 신온양-한샘#1T/L No.2~7 추락방지시설(수평) 설치","2022-11-01 08:00","2022-11-01 18:00","2022-11-01 08:00","2022-11-01 18:00","연속"]
[335,"대전세종충남","천안","신온양한샘#2 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","154kV 신온양-한샘#2T/L No.2~43 추락방지시설(수평) 설치","2022-11-07 08:00","2022-11-08 18:00","2022-11-05 08:00","2022-11-10 18:00","매일"]
[336,"대전세종충남","천안","신온양한샘#1 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","154kV 신온양-한샘#1T/L No.2~43 추락방지시설(수직,수평) 설치","2022-11-01 08:00","2022-11-04 18:00","2022-11-01 08:00","2022-11-04 18:00","매일"]
[337,"대전세종충남","천안","천안전의#2 T/L","케이블헤드 철탑 EBA 지상 PD진단시스템 구축","진단용 센서 설치(EBA 하부), 신호선 정리, 지상 집합반 설치 등","2022-11-02 09:00","2022-11-04 18:00","2022-11-02 09:00","2022-11-04 18:00","연속"]
[338,"대전세종충남","천안","서천안탕정#2 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","[4회선 병가철탑 안전거리확보] 154kV 신온양-한샘#1T/L No.42 추락방지시설(수평) 설치","2022-11-04 08:00","2022-11-04 18:00","취소","취소","연속"]
[339,"대전세종충남","천안","서천안탕정#1 T/L","345kV 아산-화성 등 15개 T/L 추락방지시설 설치공사","[4회선 병가철탑 안전거리확보] 154kV 신온양-한샘#2T/L No.42 추락방지시설(수평) 설치","2022-11-08 08:00","2022-11-08 18:00","취소","취소","연속"]
[340,"대전세종충남","천안","풍세장재#2 T/L","[송전] '22~'23년 천안전력지사 가공송전협력회사 총액공사","154kV 장재-천안 등 2개T/L 애자련 보강공사","2022-11-24 07:00","2022-11-26 18:00","2022-11-24 07:00","2022-11-26 18:00","매일"]
[341,"대전세종충남","천안","풍세장재#1 T/L","[송전] '22~'23년 천안전력지사 가공송전협력회사 총액공사","154kV 장재-천안 등 2개T/L 애자련 보강공사","2022-11-21 07:00","2022-11-23 18:00","2022-11-21 07:00","2022-11-23 18:00","매일"]
[342,"대전세종충남","청양","관창보령CC T/L","154kV 관창-보령복합T/L 관련기기 점검","관창S/S 154kV 차단기 부동작 예방 조작시험(677)","2022-11-09 14:00","2022-11-09 18:00","2022-11-09 14:00","2022-11-09 18:00","연속"]
[343,"대전세종충남","청양","관창보령CC T/L","154kV 관창-보령화력T/L 관련기기 점검","관창S/S, 보령T/P 154kV 차단기 부동작 예방 조작시험(667,627)","2022-11-09 09:00","2022-11-09 14:00","2022-11-09 09:00","2022-11-09 14:00","연속"]
[344,"대전세종충남","청양","관창대천#2 T/L","[지중] 154kV 대천S/S 인출T/L 지중화공사(2차)","○ 공 사 명 : 154kV 대천S/S 미래화사업 관련 인출T/L 지중화공사 ○ 공사대상 : 154kV 대천-서천 등 2개T/L ○ 선종 및 길이 : XLPE 2,500㎟ × 2C, 0.408km","2022-11-07 07:00","2022-11-23 18:00","2022-11-18 07:00","2022-11-26 18:00","연속"]
[345,"대전세종충남","청양","신서천대천#2 T/L","[지중] 154kV 대천S/S 인출T/L 지중화공사(2차가압)","154kV 대천S/S GIS화 관련 인출 송전선로 지중화공사 ○ 공사대상 : 154kV 대천-서천 등 2개T/L ○ 선종 및 길이 : XLPE 2,500㎟ × 2C, 0.408km","2022-11-22 07:00","2022-11-23 18:00","2022-11-25 07:00","2022-11-26 18:00","연속"]
[346,"대전세종충남","청양","보령TP보령CC T/L","154kV 보령복합T/L 관련기기 점검","보령T/P 154kV 차단기 부동작예방 조작시험(617) 및 LA, CVT 보통점검","2022-11-07 09:00","2022-11-07 18:00","2022-11-07 09:00","2022-11-07 18:00","연속"]
[347,"대전세종충남","청양","보령T/P CB 6100","154kV 차단기 부동작 예방 조작시험(6100)","154kV 차단기 부동작 예방 조작시험(6100)","2022-11-14 09:00","2022-11-18 18:00","2022-11-14 09:00","2022-11-18 18:00","연속"]
[348,"대전세종충남","청양","신서천T/P #66BUS","[지중] 154kV 대천S/S 인출T/L 지중화공사(1차가압)","154kV 대천S/S GIS화 관련 인출 송전선로 지중화공사 ○ 공사대상 : 154kV 대천-서천 등 2개T/L ○ 선종 및 길이 : XLPE 2,500㎟ × 2C, 0.408km","2022-11-03 07:00","2022-11-04 18:00","2022-11-03 07:00","2022-11-04 18:00","연속"]
[349,"대전세종충남","청양","신서천옥산#2 T/L","[지중] 154kV 대천S/S 인출T/L 지중화공사(1차가압)","154kV 대천S/S GIS화 관련 인출 송전선로 지중화공사 ○ 공사대상 : 154kV 대천-서천 등 2개T/L ○ 선종 및 길이 : XLPE 2,500㎟ × 2C, 0.408km","2022-11-03 07:00","2022-11-04 18:00","취소","취소","연속"]
[350,"대전세종충남","청양","신서천T/P #65 BUS","[지중] 154kV 대천S/S 인출T/L 지중화공사(1차가압)","154kV 대천S/S GIS화 관련 인출 송전선로 지중화공사 ○ 공사대상 : 154kV 대천-서천 등 2개T/L ○ 선종 및 길이 : XLPE 2,500㎟ × 2C, 0.408km","2022-11-03 07:00","2022-11-04 18:00","2022-11-03 07:00","2022-11-04 18:00","연속"]
[351,"대전세종충남","청양","옥산부여#1 T/L","케이블헤드 철탑 EBA 지상 PD진단시스템 구축","진단용 센서 설치(EBA 하부), 신호선 정리, 지상 집합반 설치 등","2022-11-07 09:00","2022-11-08 18:00","2022-11-07 09:00","2022-11-08 18:00","매일"]
[352,"대전세종충남","청양","옥산부여#2 T/L","케이블헤드 철탑 EBA 지상 PD진단시스템 구축","진단용 센서 설치(EBA 하부), 신호선 정리, 지상 집합반 설치 등","2022-11-09 09:00","2022-11-09 18:00","2022-11-09 09:00","2022-11-09 18:00","연속"]
[353,"대전세종충남","청양","은하홍성#2 T/L","[전자제어] 154kV 은하-홍성T/L OPGW 경로 이중화 안전이격확보","154kV 은하-홍성T/L OPGW 경로 이중화 공사","2022-11-07 08:00","2022-11-08 18:00","2022-11-07 08:00","2022-11-08 18:00","연속"]
[354,"대전세종충남","청양","은하홍성#1 T/L","[전자제어] 154kV 은하-홍성T/L OPGW 경로 이중화 공사","154kV 은하-홍성T/L OPGW 경로 이중화 공사","2022-11-01 08:00","2022-11-08 18:00","2022-11-01 08:00","2022-11-08 18:00","연속"]
[355,"대전세종충남","청양","청양은하#2 T/L","[전자제어] 154kV 은하-홍성T/L OPGW 경로 이중화 안전이격확보","154kV 은하-홍성T/L OPGW 경로 이중화 공사","2022-11-01 08:00","2022-11-06 18:00","2022-11-01 08:00","2022-11-06 18:00","연속"]
[356,"대전세종충남","청양","청양은하#2 T/L","(제어 취소시)[송전] 154kV 은하-홍성#1T/L 추락방지장치 설치","(제어 취소시)[송전] 154kV 은하-홍성#1T/L 철탑 추락방지장치 설치공사 안전이격확보","2022-11-07 08:00","2022-11-18 18:00","2022-11-07 08:00","2022-11-18 18:00","매일"]
[357,"대전세종충남","청양","은하홍성#1 T/L","(제어 취소시)[송전] 154kV 은하-홍성#1T/L 추락방지장치 설치","(제어 취소시)[송전] 154kV 은하-홍성#1T/L 철탑 추락방지장치 설치공사","2022-11-07 08:00","2022-11-18 18:00","2022-11-07 08:00","2022-11-18 18:00","매일"]
[358,"대전세종충남","청양","청양신풍#2 T/L","[송전]154kV 청양-신풍#2T/L 추락방지시설 설치공사","[송전]154kV 청양-신풍#2T/L 추락방지시설 설치공사 - No. 49~63 (15기)","2022-11-07 07:00","2022-11-16 18:00","2022-11-07 07:00","2022-11-16 18:00","매일"]
[359,"대전세종충남","청양","청양관창#2 T/L","[송전] 154kV 청양-관창T/L 지장송전선로 이설공사","○ 공사구간 : 154kV 청양-관창T/L No.3~8 ○ 지지물 : 신설 1기 설치, 임시 2기 설치/철거, 기설 1기 철거 ○ 전력선 : ACSR 410 x 2B x 2C, 1.473km(전선교체)","2022-11-14 07:00","2022-11-18 18:00","2022-11-18 07:00","2022-11-22 18:00","연속"]
[360,"대전세종충남","청양","청양관창#1 T/L","[송전] 154kV 청양-관창T/L 지장송전선로 이설공사","○ 공사구간 : 154kV 청양-관창T/L No.3~8 ○ 지지물 : 신설 1기 설치, 임시 2기 설치/철거, 기설 1기 철거 ○ 전력선 : ACSR 410 x 2B x 2C, 1.473km(전선교체)","2022-11-19 07:00","2022-11-23 18:00","2022-11-22 07:00","2022-11-26 18:00","연속"]
[361,"전북","군산","군산서군산#1 T/L","육상태양광T/L 발전차단용 SPS설치공사","- 육상태양광T/L 발전차단용 SPS 설치 및 시험","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[362,"전북","군산","군산S/S CB 6300","효성제 스프링타입 차단기 베어링 교체공사","효성제 스프링타입 차단기 베어링 교체공사","2022-11-07 09:00","2022-11-07 18:00","2022-11-07 09:00","2022-11-07 18:00","연속"]
[363,"전북","군산","군산서군산#2 T/L","육상태양광T/L 발전차단용 SPS설치공사","- 육상태양광T/L 발전차단용 SPS 설치 및 시험","2022-11-04 09:00","2022-11-04 18:00","2022-11-04 09:00","2022-11-04 18:00","연속"]
[364,"전북","군산","동군산군산CC#2 T/L","효성제 스프링타입 차단기 베어링 교체공사","효성제 스프링타입 차단기 베어링 교체공사","2022-11-20 09:00","2022-11-20 18:00","2022-11-20 09:00","2022-11-20 18:00","연속"]
[365,"전북","군산","동군산군산CC#1 T/L","효성제 스프링타입 차단기 베어링 교체공사","효성제 스프링타입 차단기 베어링 교체공사","2022-11-19 09:00","2022-11-19 18:00","2022-11-19 09:00","2022-11-19 18:00","연속"]
[366,"전북","군산","군산동군산#2 T/L","효성제 스프링타입 차단기 베어링 교체공사","효성제 스프링타입 차단기 베어링 교체공사","2022-11-27 09:00","2022-11-27 18:00","2022-11-27 09:00","2022-11-27 18:00","연속"]
[367,"전북","군산","군산동군산#1 T/L","효성제 스프링타입 차단기 베어링 교체공사","효성제 스프링타입 차단기 베어링 교체공사","2022-11-26 09:00","2022-11-26 18:00","2022-11-26 09:00","2022-11-26 18:00","연속"]
[368,"전북","군산","은진함열#2 T/L","효성제 스프링타입 차단기 베어링 교체공사","효성제 스프링타입 차단기 베어링 교체공사","2022-11-09 09:00","2022-11-09 18:00","2022-11-09 09:00","2022-11-09 18:00","연속"]
[369,"전북","군산","은진함열#1 T/L","효성제 스프링타입 차단기 베어링 교체공사","효성제 스프링타입 차단기 베어링 교체공사","2022-11-08 09:00","2022-11-08 18:00","2022-11-08 09:00","2022-11-08 18:00","연속"]
[370,"전북","김제","정주고창#1 T/L","154kV 소성분기T/L 건설공사","○ 위 치 : 154kV 정주-고창T/L No.28~29 ○ 작업내용 : #1T/L 공중이동, 긴선(By-pass 구성) 및 가철탑 철거","2022-11-28 08:00","2022-12-02 18:00","2022-12-05 08:00","2022-12-09 18:00","연속"]
[371,"전북","김제","정주고창#2 T/L","154kV 소성분기T/L 건설공사","○ 위 치 : 154kV 정주-고창T/L No.28~29 ○ 작업내용 : 본철탑(28-2호) 조립 및 #2T/L 공중이동(By-pass 구성)","2022-11-21 08:00","2022-11-24 18:00","2022-11-28 08:00","2022-12-02 18:00","연속"]
[372,"전북","김제","정주고창#1 T/L","154kV 소성분기T/L 건설공사","○ 위 치 : 154kV 정주-고창T/L No.28~29 ○ 작업내용 : 가철탑 조립 및 임시선로 구성","2022-11-14 08:00","2022-11-18 18:00","2022-11-21 08:00","2022-11-24 18:00","연속"]
[373,"전북","김제","이리백산#1 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-11-10 09:00","2022-11-11 18:00","2022-11-10 09:00","2022-11-11 18:00","연속"]
[374,"전북","김제","백산김제#1 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-11-01 09:00","2022-11-02 18:00","2022-11-01 09:00","2022-11-02 18:00","연속"]
[375,"전북","김제","이리백산#2 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-11-03 09:00","2022-11-04 18:00","2022-11-03 09:00","2022-11-04 18:00","연속"]
[376,"전북","김제","신김제남전주#2 T/L","345kV 신김제S/S #63D.Tr 증설공사(시험가압)","#63D.Tr 무부하가압 및 ANGLE 측정","2022-11-14 15:00","2022-11-15 11:00","2022-11-14 15:00","2022-11-15 11:00","연속"]
[377,"전북","직할","동전주북전주#2 T/L","동전주S/S 장기사용 170kV GIS 교체공사(4차)","○ 동전주-북전주#2T/L GIS 철거 및 설치","2022-11-01 09:00","2022-11-20 18:00","2022-11-01 09:00","2022-11-20 18:00","연속"]
[378,"전북","직할","무주진안 T/L","154kV 무주-진안 T/L 보호반 대체","154kV T/L 보호반 대체","2022-11-29 15:00","2022-11-30 10:00","2022-11-29 15:00","2022-11-30 10:00","연속"]
[379,"전북","직할","북전주S/S #2 BUS","북전주S/S 170kV GIS 대체공사","154kV #1Sh.C GIS 대체","2022-11-30 16:00","2022-12-08 18:00","2022-11-30 16:00","2022-12-08 18:00","연속"]
[380,"전북","직할","북전주S/S #1 BUS","북전주S/S 170kV GIS 대체공사","154kV #1Sh.C GIS 대체","2022-11-23 16:00","2022-11-30 16:00","2022-11-23 16:00","2022-11-30 16:00","연속"]
[381,"전북","직할","북전주S/S #2 BUS","북전주S/S 170kV GIS 대체공사","154kV #1Sh.C GIS 대체","2022-11-21 09:00","2022-11-23 16:00","2022-11-21 09:00","2022-11-23 16:00","연속"]
[382,"전북","직할","전주서곡#1 T/L","154kV 전주-서곡 #1T/L 보호반 대체","154kV T/L 보호반 대체","2022-11-21 09:00","2022-11-22 18:00","2022-11-21 09:00","2022-11-22 18:00","연속"]
[383,"전북","직할","전주서곡#2 T/L","154kV 전주-서곡 #2T/L 보호반 대체","154kV T/L 보호반 대체","2022-11-23 09:00","2022-11-24 18:00","2022-11-23 09:00","2022-11-24 18:00","연속"]
[384,"전북","군산","영등팔봉#1 T/L","군산P/O 154kV 이상 차단기 보통점검","영등-팔봉#1T/L 차단기 보통점검","2022-11-17 15:00","2022-11-17 20:00","2022-11-17 15:00","2022-11-17 20:00","연속"]
[385,"전북","군산","영등팔봉#2 T/L","군산P/O 154kV 이상 차단기 보통점검","영등-팔봉#2T/L 차단기 보통점검","2022-11-18 15:00","2022-11-18 20:00","2022-11-18 15:00","2022-11-18 20:00","연속"]
[386,"광주전남","강진","나주엄다#1 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","나주S/A 나주-엄다#1T/L GIS 하자","2022-11-11 10:00","2022-11-11 14:00","2022-11-11 10:00","2022-11-11 14:00","연속"]
[387,"광주전남","광주","신광주계림#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","계림S/S 신광주-계림#1T/L 조작시험","2022-11-15 09:00","2022-11-15 18:00","취소","취소","연속"]
[388,"광주전남","광주","담양S/S #1 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2022-11-25 15:00","2022-11-30 18:00","취소","취소","연속"]
[389,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2022-11-29 18:00","2022-11-30 18:00","취소","취소","연속"]
[390,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-11-20 15:00","2022-11-21 15:00","2022-11-23 16:00","2022-11-24 16:00","연속"]
[391,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-11-14 08:00","2022-11-21 15:00","2022-11-14 08:00","2022-11-24 16:00","연속"]
[392,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-11-12 18:00","2022-11-13 18:00","2022-11-12 16:00","2022-11-13 16:00","연속"]
[393,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-11-02 08:00","2022-11-04 15:00","2022-11-02 08:00","2022-11-04 16:00","연속"]
[394,"광주전남","광주","담양김제 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-11-02 08:00","2022-11-22 18:00","2022-11-02 08:00","2022-11-25 17:00","연속"]
[395,"광주전남","광주","담양S/S #1 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-11-04 15:00","2022-11-13 18:00","2022-11-05 08:00","2022-11-13 18:00","연속"]
[396,"광주전남","광주","담양일곡#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","담양S/S 담양-일곡#1T/L CVT 보통점검(비상시 즉시가압 불가) 일곡S/S 담양-일곡#1T/L 170kV GIS 보통점검","2022-11-10 09:00","2022-11-10 18:00","2022-11-10 09:00","2022-11-10 18:00","연속"]
[397,"광주전남","광주","담양일곡#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","담양S/S 담양-일곡#2T/L CVT 보통점검(비상시 즉시가압 불가)","2022-11-11 09:00","2022-11-11 18:00","2022-11-11 09:00","2022-11-11 18:00","연속"]
[398,"광주전남","광주","담양일곡#1 T/L","2022년 광주전력 철탑추락방지장치 설치공사","철탑추락방지장치 설치공사","2022-11-17 07:00","2022-11-26 18:00","2022-11-17 07:00","2022-11-26 18:00","매일"]
[399,"광주전남","광주","담양일곡#2 T/L","2022년 광주전력 철탑추락방지장치 설치공사","철탑추락방지장치 설치공사","2022-11-28 07:00","2022-12-04 18:00","2022-11-28 07:00","2022-12-04 18:00","매일"]
[400,"광주전남","광주","담양S/S #1 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-11-21 15:00","2022-11-22 15:00","2022-11-24 16:00","2022-11-25 16:00","연속"]
[401,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(1차) - 담양-김제T/L, #1M.Tr, #1B/T, #1PT","2022-11-21 15:00","2022-11-22 15:00","2022-11-24 17:00","2022-11-25 17:00","연속"]
[402,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2022-11-24 08:00","2022-11-25 15:00","취소","취소","연속"]
[403,"광주전남","광주","정공담양 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2022-11-24 08:00","2022-12-07 18:00","취소","취소","연속"]
[404,"광주전남","광주","신광주계림#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","PT 보통점검(비상시 즉시가압 불가)","2022-11-09 09:00","2022-11-09 18:00","취소","취소","연속"]
[405,"광주전남","광주","일곡S/S CB 6100","22년 광주전력지사 변전협력회사 총액공사","GIS 보통점검 (즉시가압 불가)","2022-11-07 09:00","2022-11-07 18:00","2022-11-07 09:00","2022-11-07 18:00","연속"]
[406,"광주전남","목포","안좌S/S 안좌스마트팜T/L CB","2022-23년도 목포전력지사 변전협력회사 총액공사","2022-23년도 목포전력지사 변전협력회사 총액공사","2022-11-02 09:00","2022-11-02 18:00","2022-11-02 09:00","2022-11-02 18:00","연속"]
[407,"광주전남","목포","나주엄다#1 T/L","2022-23년도 목포전력지사 변전협력회사 총액공사","2022-23년도 목포전력지사 변전협력회사 총액공사","2022-11-10 13:00","2022-11-10 18:00","2022-11-10 13:00","2022-11-10 18:00","연속"]
[408,"광주전남","목포","나주엄다#1 T/L","154kV 나주-엄다 등 2개T/L 추락방지장치 설치공사","154kV 나주-엄다T/L No.1 ~ 118호","2022-11-07 09:00","2022-11-23 18:00","2022-11-01 09:00","2022-11-19 18:00","매일"]
[409,"광주전남","목포","나주엄다#2 T/L","154kV 나주-엄다 등 2개T/L 추락방지장치 설치공사","154kV 나주-엄다T/L No.1 ~ 118호","2022-11-24 09:00","2022-11-30 18:00","2022-11-20 09:00","2022-11-30 18:00","매일"]
[410,"광주전남","순천","여수TP용성#1 T/L","대한제 열경화공법 EBG 보강공사","여수TP-용성#1 T/L EBG 해체점검(6상)","2022-11-02 09:00","2022-11-10 18:00","취소","취소","연속"]
[411,"광주전남","순천","여수TP용성#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#2T/L LA(A, B, C) 하자점검 여수화력S/Y 여수TP-용성#2T/L GIS 보통점검 및 상시여자 보조계전기 교체","2022-11-29 10:00","2022-11-29 18:00","취소","취소","연속"]
[412,"광주전남","순천","여천호남TP#2 T/L","대한제 열경화공법 EBG 보강공사","여천-호남#1 T/L EBG 해체점검(6상)","2022-11-16 09:00","2022-11-23 18:00","취소","취소","연속"]
[413,"광주전남","순천","여천호남TP#2 T/L","345kV 광양CC-여수TP T/L 추락방지시설 설치공사","목적 : 승탑 작업자 추락방지를 위한 추락방지시설 설치 내용 : 수직, 수평 추락방지시설 설치","2022-11-28 08:00","2022-11-28 18:00","취소","취소","연속"]
[414,"광주전남","순천","여천호남TP#1 T/L","345kV 광양CC-여수TP T/L 추락방지시설 설치공사","목적 : 승탑 작업자 추락방지를 위한 추락방지시설 설치 내용 : 수직, 수평 추락방지시설 설치","2022-11-22 08:00","2022-11-22 18:00","취소","취소","연속"]
[415,"광주전남","순천","여천호남TP#1 T/L","대한제 열경화공법 EBG 보강공사","여천-호남#1 T/L EBG 해체점검(6상)","2022-11-16 09:00","2022-11-23 18:00","취소","취소","연속"]
[416,"광주전남","순천","여수TP용성#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","용성S/S 여수TP-용성#1T/L LA(A, B, C) 하자점검","2022-11-28 10:00","2022-11-28 14:00","취소","취소","연속"]
[417,"광주전남","순천","순천율촌#1 T/L","2022년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2022-11-21 09:00","2022-11-22 18:00","2022-11-21 09:00","2022-11-22 18:00","연속"]
[418,"광주전남","순천","율촌여수산단#2 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-11-30 09:00","2022-12-01 18:00","취소","취소","연속"]
[419,"광주전남","순천","율촌여수산단#1 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-11-28 09:00","2022-11-29 18:00","취소","취소","연속"]
[420,"광주전남","순천","호남TP여수TP#2 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-11-17 09:00","2022-11-18 18:00","취소","취소","연속"]
[421,"광주전남","순천","여수TP여천#2 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-11-10 09:00","2022-11-11 18:00","취소","취소","연속"]
[422,"광주전남","순천","여수TP여천#1 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-11-08 09:00","2022-11-09 18:00","취소","취소","연속"]
[423,"광주전남","순천","호남TP여수TP#1 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-11-15 09:00","2022-11-16 18:00","취소","취소","연속"]
[424,"광주전남","순천","율촌S/S SEC CB 65660","'22-23년 순천전력지사 변전정비 총액공사","#65-66 BUS SEC GIS 초기점검","2022-11-03 10:00","2022-11-03 18:00","2022-11-03 10:00","2022-11-03 18:00","연속"]
[425,"광주전남","순천","율촌S/S SEC CB 60610","'22-23년 순천전력지사 변전정비 총액공사","#60-61 BUS SEC GIS 초기점검","2022-11-02 10:00","2022-11-02 18:00","2022-11-02 10:00","2022-11-02 18:00","연속"]
[426,"광주전남","순천","율촌S/S CB 6200","'22-23년 순천전력지사 변전정비 총액공사","6200 BUS TIE GIS 초기점검","2022-11-01 10:00","2022-11-01 18:00","2022-11-01 10:00","2022-11-01 18:00","연속"]
[427,"광주전남","직할","신화순매월#1 T/L","2022~23년 직할 가공송전 협력회사 총액공사","154kV 신화순-매월T/L 추락방지시설 설치","2022-11-17 09:00","2022-11-17 18:00","2022-11-17 09:00","2022-11-17 18:00","매일"]
[428,"광주전남","직할","신화순매월#2 T/L","2022~23년 직할 가공송전 협력회사 총액공사","154kV 신화순-매월T/L 추락방지시설 설치","2022-11-18 09:00","2022-11-18 18:00","2022-11-18 09:00","2022-11-18 18:00","매일"]
[429,"대구","경산","경산S/S #1 EM.Tr CB","경산FR-ESS #1E.MTR 휴전","경산FR-ESS 정기점검(#1~12)","2022-11-01 09:00","2022-11-11 18:00","2022-10-31 09:00","2022-11-11 18:00","연속"]
[430,"대구","경산","신경산노변 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","추락방지장치 설치, 국산애자교체, 피뢰기 설치 - 작업구간 : No.28","2022-11-12 07:30","2022-11-12 12:00","2022-11-12 07:30","2022-11-12 12:00","연속"]
[431,"대구","경산","진량노변 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","철탑추락방지장치 설치, 국산애자교체, 피뢰기 설치 - 작업구간 : No.28","2022-11-12 07:30","2022-11-12 18:00","2022-11-12 07:30","2022-11-12 18:00","연속"]
[432,"대구","경산","효목안심#1 T/L","'22년 경산P/O 154kV GIS 정밀점검 및 보통점검 공사","- GIS 정밀점검","2022-11-01 09:30","2022-11-02 18:00","2022-11-07 09:00","2022-11-08 18:00","연속"]
[433,"대구","경산","효목안심#2 T/L","'22년 경산P/O 154kV GIS 정밀점검 및 보통점검 공사","- GIS 정밀점검","2022-11-03 09:30","2022-11-04 18:00","2022-11-10 09:00","2022-11-11 18:00","연속"]
[434,"대구","경산","청도밀양#2 T/L","청도S/S 154kV GIS 교체공사","TEST선로","2022-11-02 18:00","2022-11-03 09:30","2022-11-02 18:00","2022-11-03 09:30","연속"]
[435,"대구","달성","강창성서#2 T/L","2021~22년 달성전력지사 지중송전설비 위탁정비공사","154kV 강창-성서T/L EBA 절연유 및 가스채취","2022-11-08 13:00","2022-11-08 17:00","2022-11-08 13:00","2022-11-08 17:00","연속"]
[436,"대구","달성","강창성서#1 T/L","2021~22년 달성전력지사 지중송전설비 위탁정비공사","154kV 강창-성서T/L EBA 절연유 및 가스채취","2022-11-08 08:00","2022-11-08 12:00","2022-11-08 08:00","2022-11-08 12:00","연속"]
[437,"대구","달성","논공달성#1 T/L","2021~22년 달성전력지사 지중송전설비 위탁정비공사","154kV 논공-달성T/L EBA 절연유 채취","2022-11-07 08:00","2022-11-07 12:00","2022-11-07 08:00","2022-11-07 12:00","연속"]
[438,"대구","달성","논공S/S #1 EM.Tr CB","논공S/S FR-ESS 정기점검","논공S/S FR-ESS 정기점검","2022-11-28 09:00","2022-12-02 18:00","2022-11-28 09:00","2022-12-02 18:00","연속"]
[439,"대구","달성","논공달성#2 T/L","2021~22년 달성전력지사 지중송전설비 위탁정비공사","154kV 논공-달성T/L EBA 절연유 채취","2022-11-07 13:00","2022-11-07 17:00","2022-11-07 13:00","2022-11-07 17:00","연속"]
[440,"대구","달성","두류봉덕#2 T/L","두류-봉덕#2T/L GIS차단기동작특성시험","두류-봉덕#2T/L GIS차단기동작특성시험","2022-11-06 14:00","2022-11-06 18:00","2022-11-06 14:00","2022-11-06 18:00","연속"]
[441,"대구","달성","두류봉덕#1 T/L","두류-봉덕#1T/L GIS차단기동작특성시험","두류-봉덕#1T/L GIS차단기동작특성시험","2022-11-06 09:00","2022-11-06 14:00","2022-11-06 09:00","2022-11-06 14:00","연속"]
[442,"대구","달성","상인봉덕#1 T/L","2021~22년 달성전력지사 지중송전설비 위탁정비공사","154kV 상인-봉덕T/L EBA 절연유 채취","2022-11-09 08:00","2022-11-09 12:00","2022-11-09 08:00","2022-11-09 12:00","연속"]
[443,"대구","달성","상인봉덕#2 T/L","2021~22년 달성전력지사 지중송전설비 위탁정비공사","154kV 상인-봉덕T/L EBA 절연유 채취","2022-11-09 13:00","2022-11-09 17:00","2022-11-09 13:00","2022-11-09 17:00","연속"]
[444,"대구","달성","성서달성#1 T/L","2021~22년 달성전력지사 지중송전설비 위탁정비공사","154kV 성서-달성T/L EBA 절연유 채취","2022-11-07 08:00","2022-11-07 12:00","2022-11-02 09:00","2022-11-02 18:00","연속"]
[445,"대구","달성","성서달성#2 T/L","2021~22년 달성전력지사 지중송전설비 위탁정비공사","154kV 성서-달성T/L EBA 절연유 채취","2022-11-07 13:00","2022-11-07 17:00","2022-11-07 09:00","2022-11-07 18:00","연속"]
[446,"대구","직할","동인내당#2 T/L","동인S/S 동인-내당#1T/L 보통점검","동인S/S 동인-내당#1T/L 보통점검","2022-11-04 09:30","2022-11-04 18:00","2022-11-05 14:00","2022-11-05 18:00","연속"]
[447,"대구","직할","동인내당#1 T/L","동인S/S 동인-내당#1T/L 보통점검","동인S/S 동인-내당#1T/L 보통점검","2022-11-03 09:30","2022-11-03 18:00","2022-11-05 09:00","2022-11-05 14:00","연속"]
[448,"대구","포항","신포항포항#1 T/L","154kV 신포항-포항T/L 지장선로 이설공사","○ 지지물 : 교체 2기(No.5,6) ○ 전력선 : 교체 No.5~6, 재사용 No.4~5,6~7","2022-11-30 08:00","2022-12-09 18:00","2022-11-30 08:00","2022-12-09 18:00","연속"]
[449,"대구","직할","팔달내당#1 T/L","평리6 재정비촉진구역 주택재개발정비사업 ","154kV 지장송전케이블 이설공사 ","2022-11-07 08:00","2022-11-26 18:00","2022-11-10 09:00","2022-12-17 18:00","연속"]
[450,"대구","직할","팔달내당#2 T/L","평리6 재정비촉진구역 주택재개발정비사업","154kV 지장송전케이블 이설공사 ","2022-11-27 09:00","2022-12-16 18:00","2022-11-10 09:00","2022-12-17 18:00","연속"]
[451,"경북","구미","선산청리#1 T/L","154kV 청리S/S #4M.Tr 증설공사","- #4M.Tr 설치 관련 무부하가압","2022-11-29 09:00","2022-11-30 18:00","2022-11-29 09:00","2022-11-30 18:00","연속"]
[452,"경북","영주","봉화S/S 춘양전철#2T/L CB","2022-23년 영주전력지사 변전협력회사 총액공사","보호반 대체","2022-11-14 10:00","2022-11-16 17:00","2022-11-14 10:00","2022-11-16 17:00","연속"]
[453,"경북","영주","신영주예천#1 T/L","신영주, 영주S/S 154kV 신규수용 SW 증설공사","○ 신영주S/S 154kV SK T/L 신규수용 공사 - #61BUS 무부하 가압 - 6951DS, 6971CB 무부하가압","2022-11-11 12:00","2022-11-12 12:00","2022-11-11 12:00","2022-11-12 12:00","연속"]
[454,"경북","영주","신영주예천#2 T/L","신영주, 영주S/S 154kV 신규수용 SW 증설공사","○ 신영주S/S 154kV SK T/L 신규수용 공사 - #66BUS 무부하가압 - 6971CB, 6972DS, 6900CB, 6901DS, 6902DS, 6921DS 무부하가압 - '대입수능'으로 22.11.16 환원 후 22.11.18 재휴전 시행","2022-11-15 09:00","2022-11-21 18:00","2022-11-15 09:00","2022-11-21 18:00","연속"]
[455,"경북","영주","신영주영주#1 T/L","신영주, 영주S/S 154kV 신규수용 SW 증설공사","154kV GIS 1CCT 증설","2022-11-22 09:00","2022-11-28 18:00","2022-11-22 09:00","2022-11-28 18:00","연속"]
[456,"경북","영주","예천점촌#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","CVT 대체 LA 카운터 교체","2022-11-18 09:00","2022-11-18 18:00","취소","취소","연속"]
[457,"경북","영주","동상주점촌#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","LA 카운터 교체","2022-11-08 10:00","2022-11-08 17:00","2022-11-08 10:00","2022-11-08 17:00","연속"]
[458,"경북","영주","예천점촌#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","CVT 대체","2022-11-24 10:00","2022-11-24 18:00","취소","취소","연속"]
[459,"경북","직할","풍산동상주개폐소 T/L","154kV 안동-풍산 등 2개T/L 지장송전선로 이설공사","[가 공] (1) 지지물 : 5기 설치 (C/H 1기, 임시철탑4기) 10기 철거 (No.59~64 6기, 임시철탑4기) 1기 보강 (No.58) (2) 전력선 : HSTACIR 240㎟×S, ACSR 410㎟×S×2C, 0.971km","2022-11-22 08:00","2022-12-11 18:00","2022-11-22 08:00","2022-12-11 18:00","연속"]
[460,"부산울산","동부산","수영정보#2 T/L","수영S/S 657GIS 보통점검","수영S/S 657GIS 보통점검 병행)정보S/S 637GIS 보통점검","2022-11-18 09:30","2022-11-18 17:00","2022-11-20 09:30","2022-11-20 17:00","연속"]
[461,"부산울산","동부산","정관장안#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","추락방지장치 및 피뢰기 설치","2022-11-07 07:00","2022-11-08 18:00","2022-11-07 07:00","2022-11-08 18:00","연속"]
[462,"부산울산","동부산","장안고리NP T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","추락방지장치 및 피뢰기 설치","2022-11-14 07:00","2022-11-14 18:00","2022-11-14 07:00","2022-11-14 18:00","연속"]
[463,"부산울산","동부산","정관장안#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","추락방지장치 및 피뢰기 설치, 금구류 교체","2022-11-09 09:00","2022-11-12 18:00","2022-11-09 09:00","2022-11-12 18:00","연속"]
[464,"부산울산","동부산","명례장안 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","추락방지장치 및 피뢰기 설치","2022-11-15 07:00","2022-11-15 18:00","2022-11-15 07:00","2022-11-15 18:00","연속"]
[465,"부산울산","북부산","구포S/S CB 6100","22-23년 북부산전력지사 변전총액공사","구포S/S 154kV 6100 BUS TIE CB 조작시험","2022-11-11 10:00","2022-11-11 18:00","2022-11-11 10:00","2022-11-11 18:00","연속"]
[466,"부산울산","북부산","북부산구포#2 T/L","22-23년 북부산전력지사 변전총액공사","구포S/S 154kV 북부산-구포#2T/L 차단기 조작시험","2022-11-15 09:00","2022-11-15 18:00","2022-11-15 09:00","2022-11-15 18:00","연속"]
[467,"부산울산","북부산","북부산구포#1 T/L","22-23년 북부산전력지사 변전총액공사","구포S/S 154kV 북부산-구포#1T/L 차단기 조작시험","2022-11-14 09:00","2022-11-14 18:00","2022-11-14 09:00","2022-11-14 18:00","연속"]
[468,"부산울산","북부산","북부산구포#3 T/L","22-23년 북부산전력지사 변전총액공사","구포S/S 154kV 북부산-구포#3T/L 차단기 조작시험","2022-11-18 09:00","2022-11-18 18:00","2022-11-18 09:00","2022-11-18 18:00","연속"]
[469,"부산울산","북부산","대저S/S CB 6100","22-23년 북부산전력지사 변전총액공사","대저S/S 154kV 6100 BUS TIE GIS 초기점검","2022-11-03 09:00","2022-11-03 14:00","2022-11-03 09:00","2022-11-03 14:00","연속"]
[470,"부산울산","북부산","대저S/S SEC CB 65660","22-23년 북부산전력지사 변전총액공사","대저S/S 154kV 65-66 BUS SEC GIS 초기점검","2022-11-04 14:00","2022-11-04 18:00","2022-11-04 14:00","2022-11-04 18:00","연속"]
[471,"부산울산","북부산","대저S/S SEC CB 60610","22-23년 북부산전력지사 변전총액공사","대저S/S 154kV 60-61 BUS SEC GIS 초기점검","2022-11-04 09:00","2022-11-04 14:00","2022-11-04 09:00","2022-11-04 14:00","연속"]
[472,"부산울산","북부산","구포대저#2 T/L","22-23 북부산전력지사 변전총액공사","대저S/S 154kV 구포-대저#2T/L GIS 초기점검","2022-11-08 09:00","2022-11-08 18:00","2022-11-08 09:00","2022-11-08 18:00","연속"]
[473,"부산울산","북부산","대저모라#1 T/L","22-23 북부산전력지사 변전총액공사","대저S/S 154kV 대저-모라#1T/L GIS 초기점검","2022-11-09 09:00","2022-11-09 18:00","2022-11-09 09:00","2022-11-09 18:00","연속"]
[474,"부산울산","북부산","구포대저#1 T/L","22-23년 북부산전력지사 변전총액공사","대저S/S 154kV 구포-대저#1T/L GIS 초기점검","2022-11-07 09:00","2022-11-07 18:00","2022-11-07 09:00","2022-11-07 18:00","연속"]
[475,"부산울산","북부산","대저S/S CB 6200","22-23년 북부산전력지사 변전총액공사","대저S/S 154kV 6200 BUS TIE GIS 초기점검","2022-11-03 14:00","2022-11-03 18:00","2022-11-03 14:00","2022-11-03 18:00","연속"]
[476,"부산울산","북부산","대저모라#2 T/L","22-23 북부산전력지사 변전총액공사","대저S/S 154kV 대저-모라#2T/L GIS 초기점검","2022-11-10 09:00","2022-11-10 18:00","2022-11-10 09:00","2022-11-10 18:00","연속"]
[477,"부산울산","북부산","모라S/S CB 6100","22-23년 북부산전력지사 변전총액공사","모라S/S 154kV 6100 BUS TIE 차단기 조작시험","2022-11-14 09:00","2022-11-14 18:00","2022-11-14 09:00","2022-11-14 18:00","연속"]
[478,"부산울산","북부산","미남S/S SEC CB 60610","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2022-11-08 13:00","2022-11-08 18:00","취소","취소","연속"]
[479,"부산울산","북부산","미남S/S #60 BUS","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2022-11-08 13:00","2022-11-08 18:00","취소","취소","연속"]
[480,"부산울산","북부산","미남S/S CB 6100","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2022-11-08 13:00","2022-11-08 18:00","취소","취소","연속"]
[481,"부산울산","북부산","미남S/S SEC CB 65660","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2022-11-08 13:00","2022-11-08 18:00","취소","취소","연속"]
[482,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(안전이격)","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(1~46호, 45기, 4회선 병가구간 포함)(안전이격)","2022-11-14 08:00","2022-11-19 18:00","2022-11-14 08:00","2022-11-19 18:00","연속"]
[483,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(1~46호, 45기, 4회선 병가구간 포함)","2022-11-14 08:00","2022-11-19 18:00","2022-11-14 08:00","2022-11-19 18:00","연속"]
[484,"부산울산","북부산","북부산양산 T/L","22-23 북부산전력지사 변전 총액공사","양산S/S 154kV 북부산-양산T/L GIS 하자점검","2022-11-09 09:00","2022-11-09 18:00","2022-11-09 09:00","2022-11-09 18:00","연속"]
[485,"부산울산","북부산","양산삼랑진PP T/L","22-23년 북부산전력지사 변전총액공사","양산S/S154kV 양산-삼랑진PPT/L LA하자점검","2022-11-08 09:00","2022-11-08 18:00","2022-11-08 09:00","2022-11-08 18:00","연속"]
[486,"부산울산","북부산","엄궁S/S CB 6100","22-23년 북부산전력지사 변전 총액공사","엄궁S/S 154kV 모선보호반 대체","2022-11-07 09:00","2022-11-11 18:00","2022-11-07 09:00","2022-11-11 18:00","연속"]
[487,"부산울산","북부산","학장개금#1 T/L","2022년 북부산전력지사 154kV GIS정밀점검","학장S/S 154kV 학장-개금#1T/L GIS 정밀점검","2022-11-01 08:00","2022-11-02 18:00","2022-11-01 08:00","2022-11-02 18:00","연속"]
[488,"부산울산","서부산","신녹산명지#2 T/L","154kV 명지-순아T/L SW 증설관련 전력케이블 이설공사","○ 신녹산-명지#2T/L 전력케이블 이설 × 1식","2022-11-01 09:00","2022-11-22 18:00","2022-11-01 09:00","2022-11-22 18:00","연속"]
[489,"부산울산","서부산","서부산S/S SEC CB 65660","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검","2022-11-02 09:00","2022-11-03 18:00","2022-11-02 09:00","2022-11-03 18:00","연속"]
[490,"부산울산","서부산","서부산S/S #61 BUS","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검 -시험가압 관련 휴전","2022-11-01 14:00","2022-11-01 18:00","2022-11-01 14:00","2022-11-01 18:00","연속"]
[491,"부산울산","서부산","서부산S/S #66 BUS","2022년도 하반기 서부산전력 GIS 정밀점검","2022년도 하반기 서부산전력 GIS 정밀점검 -시험가압 관련 휴전","2022-11-03 14:00","2022-11-03 18:00","2022-11-03 14:00","2022-11-03 18:00","연속"]
[492,"부산울산","울산","동울산산하#2 T/L","154kV. 추락방지장치 설치공사","동울산-산하 #2, 수직, 수평 추락방지장치 설치(9기)","2022-11-24 08:00","2022-11-30 18:00","2022-11-24 08:00","2022-11-30 18:00","연속"]
[493,"부산울산","울산","신울산매암#1 T/L","154kV 울산-매암T/L SW증설공사","울산-매암T/L 1H 시험가압 후 나머지 23H 6100이용하여 시험가압","2022-11-06 02:00","2022-11-06 03:00","2022-11-06 02:00","2022-11-06 03:00","연속"]
[494,"부산울산","울산","산하방어진#1 T/L","154kV 추락방지장치 설치공사(안전이격)","ㅇ 산하-방어진 추락방지장치 설치(안전이격) - 동울산-산하 #2 9호","2022-11-24 08:00","2022-11-24 18:00","2022-11-24 08:00","2022-11-24 18:00","연속"]
[495,"부산울산","울산","신울산S/S SEC CB 60610","22~23년 변전협력회사 총액공사","GIS 차단기 동작시험","2022-11-09 09:00","2022-11-09 14:00","2022-11-09 09:00","2022-11-09 14:00","연속"]
[496,"부산울산","울산","신울산S/S SEC CB 65660","22~23년 변전협력회사 총액공사","GIS 차단기 동작시험","2022-11-09 14:00","2022-11-09 18:00","2022-11-09 14:00","2022-11-09 18:00","연속"]
[497,"부산울산","울산","신울산울산#2 T/L","신울산S/S 154kV 현대화공사","신울산-울산#2T/L 인출변경[옥외철구(1CB)-&gtGIS(1.5CB)]","2022-11-18 08:30","2022-11-20 18:00","2022-11-18 08:30","2022-11-20 18:00","연속"]
[498,"부산울산","울산","신울산울산#1 T/L","신울산S/S 154kV 현대화공사","신울산-울산#1T/L 인출변경[옥외철구(1CB)-&gtGIS(1.5CB)]","2022-11-14 08:30","2022-11-16 18:00","2022-11-14 08:30","2022-11-16 18:00","연속"]
[499,"부산울산","울산","신울산명례#2 T/L","신울산S/S 154kV 현대화공사","신울산-명례#2T/L 인출변경[옥외철구(1CB)-&gtGIS(1.5CB)]","2022-11-28 08:30","2022-11-30 18:00","2022-11-28 08:30","2022-11-30 18:00","연속"]
[500,"부산울산","울산","신울산명례#1 T/L","신울산S/S 154kV 현대화공사","신울산-명례#1T/L 인출변경[옥외철구(1CB)-&gtGIS(1.5CB)]","2022-11-21 08:30","2022-11-23 18:00","2022-11-21 08:30","2022-11-23 18:00","연속"]
[501,"부산울산","울산","온산처용#1 T/L","22년 하반기 154kV 주변압기 정밀점검공사","온산 #3M.Tr 정밀점검관련 시험가압(1Hr)","2022-11-11 17:00","2022-11-11 18:00","2022-11-11 17:00","2022-11-11 18:00","연속"]
[502,"부산울산","울산","용연울산TP#3 T/L","철탑 추락방지장치 설치공사","남울산-울산TP 병가 구간(5, 6호간 설치)","2022-11-02 08:00","2022-11-02 18:00","2022-11-02 08:00","2022-11-02 18:00","연속"]
[503,"부산울산","울산","울주직동#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","추락방지장치 및 피뢰기 설치","2022-11-16 07:00","2022-11-18 18:00","2022-11-16 07:00","2022-11-18 18:00","연속"]
[504,"부산울산","울산","울주직동#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","추락방지장치 및 피뢰기 설치","2022-11-22 07:00","2022-11-22 18:00","2022-11-22 07:00","2022-11-22 18:00","연속"]
[505,"부산울산","울산","직동반천#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","추락방지장치 및 피뢰기 설치","2022-11-21 07:00","2022-11-22 18:00","2022-11-21 07:00","2022-11-22 18:00","연속"]
[506,"경남","직할","마천진해#2 T/L","154kV 마천-진해T/L 등 OPGW 증설 공사","1) OPGW 100㎟/48C → OPGW 100㎟/96C 교체 (5.671km) 2) ACSR 97㎟ → OPGW 100㎟/48C 교체 (6.169km) 3) 항공장애표시구 15개 교체 등","2022-11-14 07:00","2022-11-20 18:00","2022-11-19 07:00","2022-11-20 18:00","연속"]
[507,"경남","직할","마천진해#1 T/L","154kV 마천-진해T/L 등 OPGW 증설 공사","1) OPGW 100㎟/48C → OPGW 100㎟/96C 교체 (5.671km) 2) ACSR 97㎟ → OPGW 100㎟/48C 교체 (6.169km) 3) 항공장애표시구 15개 교체 등","2022-11-19 07:00","2022-11-23 18:00","2022-11-19 07:00","2022-11-23 18:00","연속"]
[508,"경남","진주","중리가야#2 T/L","가야S/S 중리-가야#2T/L GIS 정밀점검","가야S/S 중리-가야#2T/L GIS 정밀점검","2022-11-05 09:00","2022-11-06 18:00","2022-11-05 09:00","2022-11-06 18:00","연속"]
[509,"경남","진주","삼천포사천#1 T/L","154kV 효성제 스프링 GIS 메카니즘 교체(사천S/S 삼천포#1TL)","154kV 효성제 스프링 GIS 메카니즘 교체(사천S/S 삼천포#1TL)","2022-11-13 09:00","2022-11-13 18:00","2022-11-13 09:00","2022-11-13 18:00","연속"]
[510,"경남","진주","삼천포사천#2 T/L","154kV 효성제 스프링 GIS 메카니즘 교체(사천S/S 삼천포#2TL)","154kV 효성제 스프링 GIS 메카니즘 교체(사천S/S 삼천포#2TL)","2022-11-14 09:00","2022-11-14 18:00","2022-11-14 09:00","2022-11-14 18:00","연속"]
[511,"경남","진주","사천개양#1 T/L","사천S/S 사천-개양#1,2T/L LA교체","[참고] 11/19 : 작업, 11/20 : 안전이격확보","2022-11-19 10:00","2022-11-20 18:00","2022-11-19 10:00","2022-11-20 18:00","매일"]
[512,"경남","진주","사천개양#2 T/L","사천S/S 사천-개양#1,2T/L LA교체","[병행] 사천S/S 사천-개양#2T/L GIS 보통점검 [참고] 11/19 : 안전이격확보, 11/20 : 작업","2022-11-19 10:00","2022-11-20 18:00","2022-11-19 10:00","2022-11-20 18:00","매일"]
[513,"경남","통영","통영거제#1 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-11-26 07:00","2022-11-26 18:00","2022-11-26 07:00","2022-11-26 18:00","연속"]
[514,"경남","통영","신고성거제#2 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-11-06 07:00","2022-11-06 22:00","2022-11-06 07:00","2022-11-06 22:00","연속"]
[515,"경남","통영","통영거제#1 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-11-06 07:00","2022-11-06 22:00","2022-11-06 07:00","2022-11-06 22:00","연속"]
[516,"경남","통영","통영거제#1 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-11-12 07:00","2022-11-13 18:00","2022-11-12 07:00","2022-11-13 18:00","매일"]
[517,"경남","통영","신고성거제#1 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-11-19 07:00","2022-11-20 18:00","2022-11-19 07:00","2022-11-20 18:00","매일"]
[518,"경남","통영","통영거제#2 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-11-19 07:00","2022-11-20 18:00","2022-11-19 07:00","2022-11-20 18:00","매일"]
[519,"경남","통영","신고성거제#2 T/L","거제S/S 인출송전선로 지중이설공사 임시선로 구성","○ 임시선로 구성 - 통영-거제T/L 69호~거제S/S (0.8km, HSATCIR/AW330*S*2C) - 신고성-거제T/L 196호~거제S/S (0.8km, HSATCIR/AW410*S*2C) - 삼성조선T/L 3호~거제 (0.8km, HSATCIR/AW330*S*1C)","2022-11-12 07:00","2022-11-13 18:00","2022-11-12 07:00","2022-11-13 18:00","매일"]
[520,"경남","통영","신고성S/S 신고성-삼천포신재생T/L CB","신고성S/S 신재생T/L GIS 제작사 점검","1. 신고성S/S 신재생T/L GIS 제작사 점검","2022-11-03 09:00","2022-11-03 18:00","2022-11-03 09:00","2022-11-03 18:00","연속"]
[521,"경남","통영","신고성고성 T/L","154kV 신고성통영T/L 추락방지장치 설치 공사","154kV 신고성통영T/L 수평형 추락방지장치 설치 공사","2022-11-06 07:00","2022-11-06 18:00","2022-11-06 07:00","2022-11-06 18:00","연속"]
[522,"경남","통영","신고성통영 T/L","154kV 신고성통영T/L 추락방지장치 설치 공사","154kV 신고성통영T/L 수평형 추락방지장치 설치 공사","2022-11-05 07:00","2022-11-05 18:00","2022-11-05 07:00","2022-11-05 18:00","연속"]
[523,"경남","통영","고성통영 T/L","154kV 고성-통영T/L 항공장애표시구 교체 공사","154kV 고성-통영T/L 항공장애표시구 교체 공사","2022-11-27 09:00","2022-11-27 18:00","2022-11-27 09:00","2022-11-27 18:00","연속"]
[524,"경남","통영","통영거제#2 T/L","154kV 고성-통영T/L 항공장애표시구 교체 공사 안전작업거리 확보","154kV 고성-통영T/L 항공장애표시구 교체 공사 안전작업거리 확보","2022-11-27 09:00","2022-11-27 18:00","2022-11-27 09:00","2022-11-27 18:00","연속"]
[525,"경남","함안","김해어방#1 T/L","김해,어방S/S 154kV 김해-어방#1T/L 21계전기 로직 업데이트","김해,어방S/S 154kV 김해-어방#1T/L 21계전기 로직 업데이트","2022-11-24 10:00","2022-11-24 18:00","2022-11-24 10:00","2022-11-24 18:00","연속"]
[526,"경남","함안","매리김해#2 T/L","매리S/S 154kV 매리-김해#2T/L GIS 정밀점검","매리S/S 154kV 매리-김해#2T/L GIS 정밀점검","2022-11-21 09:30","2022-11-23 17:30","2022-11-21 09:30","2022-11-23 17:30","연속"]
[527,"경남","함안","매리김해#1 T/L","매리S/S 154kV 매리-김해#1T/L GIS 정밀점검","매리S/S 154kV 매리-김해#1T/L GIS 정밀점검","2022-11-14 09:30","2022-11-16 17:30","2022-11-14 09:30","2022-11-16 17:30","연속"]
[528,"경남","함안","초동밀양#1 T/L","22~23년도 함안전력지사 송전협력회사 총액공사","154kV 초동-밀양#1T/L 추락방지장치 설치공사 11.17(목) 수능으로 작업 미실시","2022-11-16 07:00","2022-11-16 18:00","2022-11-16 07:00","2022-11-16 18:00","매일"]
[529,"경남","함안","주촌삼계#1 T/L","삼계S/S 154kV 주촌-삼계#1T/L GIS 유압계통 점검","삼계S/S 154kV 주촌-삼계#1T/L GIS 유압계통 점검, 인근 옹벽 보수","2022-11-11 09:30","2022-11-11 17:30","2022-11-11 09:30","2022-11-11 17:30","연속"]
[530,"경남","함안","중리가야#1 T/L","중리S/S 154kV 중리-가야#1T/L GIS 정밀점검","중리S/S 154kV 중리-가야#1T/L GIS 정밀점검","2022-11-12 09:30","2022-11-13 17:30","2022-11-12 09:30","2022-11-13 17:30","연속"]
[531,"경남","함안","진영수산#1 T/L","22~23년도 함안전력지사 송전협력회사 총액공사","154kV 진영-수산#1T/L 추락방지장치 설치공사","2022-11-21 07:00","2022-11-24 18:00","2022-11-21 07:00","2022-11-24 18:00","매일"]
[532,"경남","함안","진례진영#1 T/L","진영S/S 154kV 진례-진영#1T/L GIS 정밀점검","진영S/S 154kV 진례-진영#1T/L GIS 정밀점검","2022-11-28 09:30","2022-11-30 17:30","2022-11-28 09:30","2022-11-30 17:30","연속"]
[533,"경남","함안","창녕초동#2 T/L","22~23년도 함안전력지사 송전협력회사 총액공사","154kV 창녕-초동#2T/L 추락방지장치 설치공사","2022-11-14 07:00","2022-11-15 18:00","2022-11-14 07:00","2022-11-15 18:00","연속"]
[534,"경남","함안","창녕초동#1 T/L","22~23년도 함안전력지사 송전협력회사 총액공사","154kV 창녕-초동#1T/L 추락방지장치 설치공사","2022-11-06 08:00","2022-11-12 18:00","2022-11-06 08:00","2022-11-12 18:00","연속"]
[535,"부산울산",null,"신고리N/P #2호기 대기보조변압기 (CB 6200, 6272)","신고리2호기 7차 계획예방정비 *조작 차단기 : CB 6200, 6272","○ SWYD 6200, 6272 차단기 일반점검 ○ 대기보조변압기 점검","2022-11-25 09:00","2022-12-07 18:00","2022-11-25 09:00","2022-12-07 18:00","연속"]