{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":10,"n_cols":11,"rows_kept":10,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 12월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #2 M.Tr","신가평S/S #2M.Tr 복구공사 (이설)","신가평S/S #2M.Tr 복구공사 (#4M.Tr C-R Tank 이설) 이설 분 설치 및 도체, GIB 조립 ※ 작업진행 상황에 따라 휴전기간 및 일정 변경될 수 있음","2022-12-19 09:00","2022-12-30 18:00","2022-12-31 09:00","2023-01-20 18:00","연속"]
[2,"경기북부","구리","신가평S/S #4 M.Tr","신가평S/S #2M.Tr 복구공사 (이설)","신가평S/S #2M.Tr 복구공사 (#4M.Tr C-R Tank 이설) - #4M.Tr C-R Tank 부속품/본체 철거 및 이동 ※ 작업진행 상황에 따라 휴전기간 및 일정 변경될 수 있음","2022-12-12 09:00","2022-12-16 18:00","2022-12-17 09:00","2022-12-20 18:00","연속"]
[3,"부산울산","동부산","신고리N/P #1 Tie-Tr","신고리 5,6호기 접속설비 공사","- 8471CB GROUP 감시, 경보 Interface PNL 수용 및 시험(제어케이블)","2022-12-14 09:00","2022-12-15 18:00","2022-12-14 09:00","2022-12-15 18:00","연속"]
[4,"부산울산","동부산","북경남신고리NP#1 T/L","신고리 5,6호기 접속설비공사","- 8271CB GROUP 감시, 경보 Interface PNL 수용 및 시험(제어케이블)","2022-12-12 09:00","2022-12-13 18:00","취소","취소","연속"]
[5,"부산울산",null,"신고리N/P #2호기 주변압기 (CB 8100, 8171)","신고리2호기 7차 계획예방정비 *조작 차단기 : CB 8100, 8171","○ 신고리2호기 소내전원절체 시험","2022-12-08 09:00","2022-12-08 18:00","2022-12-08 09:00","2022-12-08 18:00","연속"]
[6,"경북",null,"신한울N/P #2호기 주변압기 (CB 8400, 8472)","신한울2호기 주기시험 수행 *조작 차단기 : CB 8400, 8472","○ 신한울2호기 소내전원절체시험 및 보호계전기 연동시험 수행","2022-12-06 15:00","2022-12-12 18:00","2022-12-06 15:00","2022-12-12 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":146,"n_cols":11,"rows_kept":146,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2022년도 12월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S CB 7500","22년 성동P/O 변전협력회사 총액공사","미금성동#3T/L - #4M.Tr TIE GIS 보통점검","2022-12-05 09:00","2022-12-07 18:00","2022-12-05 09:00","2022-12-07 18:00","연속"]
[2,"서울","성동","성동S/S #1 M.Tr","2022년 성동P/O 변전협력회사 총액공사","-154kV GIS 보통점검 -변압기실 FAN 교체","2022-12-14 09:00","2022-12-15 20:00","2022-12-14 09:00","2022-12-15 20:00","연속"]
[3,"서울","성동","미금성동#3 T/L","22년 성동P/O 변전협력회사 총액공사","미금성동#3T/L 보통점검","2022-12-05 09:00","2022-12-05 18:00","2022-12-05 09:00","2022-12-05 18:00","연속"]
[4,"서울","성동","성동S/S #2 M.Tr","2022년 성동P/O 변전협력회사 총액공사","-154kV GIS 보통점검 -변압기실 FAN 교체","2022-12-12 09:00","2022-12-13 20:00","2022-12-12 09:00","2022-12-13 20:00","연속"]
[5,"서울","성동","성동S/S #4 M.Tr","성동S/S #4M.Tr 러버백 교체","본체 컨서베이터 러버백 불량 교체","2022-12-05 09:00","2022-12-09 18:00","2022-12-05 09:00","2022-12-09 18:00","연속"]
[6,"남서울","강남","신양재S/S #4 Sh.R CB","22-23년도 강남전력지사 변전협력회사 총액공사","-345kV #74BAY B/F PNL 대체 -345kV #3,4Sh.R PNL 대체","2022-12-12 09:00","2022-12-20 18:00","2022-12-12 09:00","2022-12-20 18:00","연속"]
[7,"남서울","강남","신양재S/S #3 Sh.R CB","22-23년도 강남전력지사 변전협력회사 총액공사","-345kV #74BAY B/F PNL 대체 -345kV #3,4Sh.R PNL 대체","2022-12-12 09:00","2022-12-20 18:00","2022-12-12 09:00","2022-12-20 18:00","연속"]
[8,"남서울","강남","신양재S/S CB 7271","22-23년도 강남전력지사 변전협력회사 총액공사","-7271 GIS 조작시험","2022-12-01 09:00","2022-12-01 18:00","2022-12-01 09:00","2022-12-01 18:00","연속"]
[9,"남서울","동서울","동서울S/S #2 M.Tr","동서울S/S 154kV 옥외철구 GIS화 공사","○ 옥외철구 -> GIS 운전전환 X 1식 ○ 기타 부대작업 X 1식","2022-12-19 09:00","2023-01-05 18:00","2022-12-19 09:00","2023-01-05 18:00","연속"]
[10,"남서울","영등포","신광명S/S #70 BUS","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2022-12-03 14:00","2022-12-04 14:00","2022-12-10 08:00","2022-12-10 14:00","연속"]
[11,"남서울","영등포","신광명S/S #75 BUS","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2022-12-03 09:00","2022-12-03 14:00","2022-12-10 14:00","2022-12-11 18:00","연속"]
[12,"남서울","직할","신문래S/S #3 Sh.R CB","362kV GIS 정밀점검공사","362kV GIS 정밀점검공사","2022-12-19 09:00","2022-12-23 18:00","2022-12-19 09:00","2022-12-23 18:00","연속"]
[13,"인천","김포","신김포S/S #3 Sh.R CB","신김포S/S 362kV 7600 개폐제어기 설치공사 관련 휴전","신김포S/S 362kV 7600 개폐제어기 설치공사 관련 휴전","2022-12-05 09:00","2022-12-10 18:00","2022-12-05 09:00","2022-12-10 18:00","매일"]
[14,"인천","김포","신김포S/S CB 7600","신김포S/S 362kV 7600 개폐제어기 설치공사","신김포S/S 362kV 7600 개폐제어기 설치공사","2022-12-05 09:00","2022-12-10 18:00","2022-12-05 09:00","2022-12-10 18:00","연속"]
[15,"인천","부평","신가좌신시흥#1 T/L","신가좌S/S 345kV #2M.Tr 교체공사(무부하가압)","-345kV M.Tr 철거 × 1Bank -345kV M.Tr 설치 × 1Bank -모선배선 철거 및 설치 × 1식 - 제어케이블 결선분리 및 결선 × 1식 - 접지장치 설치 × 1식","2022-12-03 13:00","2022-12-04 13:00","2022-12-03 13:00","2022-12-04 13:00","연속"]
[16,"인천","부평","인천C/C CB 7A00","인천복합S/Y 7A00GIS 보통점검 및 전자변 교체","인천복합S/Y 7A00GIS 보통점검 및 전자변 교체","2022-12-02 09:00","2022-12-02 18:00","2022-12-02 09:00","2022-12-02 18:00","연속"]
[17,"경기북부","직할","양주S/S CB 7700","양주 STATCOM 건설사업","- 인수점검 미비사항 조치 - 울타리 소동물 출입방지펜스 설치(7700CB)","2022-12-06 09:00","2022-12-07 18:00","2022-12-06 09:00","2022-12-07 18:00","연속"]
[18,"경기북부","직할","양주S/S STATCOM CB","양주 STATCOM 건설사업","- 인수점검 미비사항 조치 - 울타리 소동물 출입방지펜스 설치(7771CB)","2022-12-06 09:00","2022-12-07 18:00","2022-12-06 09:00","2022-12-07 18:00","연속"]
[19,"경기북부","구리","미금S/S CB 7500","2022~23 구리전력 변전정비 총액공사","미금S/S 신의정부-미금#2T/L TIE 7500 GIS 보통점검(7500CB)","2022-12-05 09:00","2022-12-05 18:00","2022-12-05 09:00","2022-12-05 18:00","연속"]
[20,"경기북부","구리","미금S/S CB 7600","2022~23 구리전력 변전정비 총액공사","미금S/S 신의정부-미금#1T/L TIE 7600 GIS 보통점검(7600CB)","2022-12-06 09:00","2022-12-06 18:00","취소","취소","연속"]
[21,"경기북부","구리","미금S/S #3 Sh.R CB","미금S/S 가변형 리액터(VSR) 설치공사","- 미금S/S #3Sh.R 철거 - 미금S/S VSR 설치","2022-12-01 09:00","2023-01-31 18:00","취소","취소","연속"]
[22,"경기북부","구리","미금S/S #2 M.Tr","미금S/S 종합예방진단시스템 설치","○ 미금S/S 종합예방진단시스템 설치 - OLTC 부분방전, 부싱진단장치, 유증가스분석장치 설치 - MLU PNL 설치 및 SUS 배관 연결, 케이블 결선 등","2022-12-01 09:00","2022-12-02 18:00","취소","취소","연속"]
[23,"경기북부","구리","미금S/S #3 M.Tr","미금S/S 종합예방진단시스템 설치","○ 미금S/S 종합예방진단시스템 설치 - OLTC 부분방전, 부싱진단장치, 유증가스분석장치 설치 - MLU PNL 설치 및 SUS 배관 연결, 케이블 결선 등","2022-12-07 09:00","2022-12-08 18:00","취소","취소","연속"]
[24,"경기북부","구리","미금S/S #1 M.Tr","미금S/S 종합예방진단시스템 설치","○ 미금S/S 종합예방진단시스템 설치 - OLTC 부분방전, 부싱진단장치, 유증가스분석장치 설치 - MLU PNL 설치 및 SUS 배관 연결, 케이블 결선 등","2022-12-05 09:00","2022-12-06 18:00","취소","취소","연속"]
[25,"경기북부","직할","양주S/S #1 M.Tr","#1M.Tr 3차 SIS실 구조개선","#1M.Tr 3차 SIS실 구조개선 - 단열재 시공 및 환기팬 교체 등","2022-12-08 09:00","2022-12-09 18:00","2022-12-08 09:00","2022-12-09 18:00","연속"]
[26,"경기","군포","신안산S/S #3 M.Tr","신안산SS 3M.Tr 보호반 개조공사","신안산SS 3M.Tr 보호반 개조공사","2022-12-01 09:00","2022-12-02 18:00","2022-12-01 09:00","2022-12-02 18:00","연속"]
[27,"경기","성남","신안성S/S CB 7A72","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-12-06 09:00","2022-12-06 18:00","취소","취소","연속"]
[28,"경기","성남","신안성S/S CB 7A00","2022년 성남전력 362/170kV GIS 보통점검 공사","- GIS 보통점검","2022-12-07 09:00","2022-12-07 18:00","취소","취소","연속"]
[29,"경기","직할","화성S/S #4 M.Tr","2022-23 경기본부 직할변전협력회사 총액공사","1차 LA 대체, 3차 VCB대체 및 부싱절연유 채유 등","2022-12-01 09:00","2022-12-02 18:00","2022-12-01 09:00","2022-12-02 18:00","연속"]
[30,"경기","직할","화성S/S #2 M.Tr","화성S/S 154kV 장기사용 GIS 교체공사(4차)","GIS대체(4차) 안전이격거리","2022-12-03 09:00","2022-12-04 18:00","2022-12-03 09:00","2022-12-04 18:00","연속"]
[31,"경기","직할","화성S/S #3 M.Tr","2022-23 경기본부 직할변전협력회사 총액공사","7672 GIS 초기점검 및 2차 LA 대체 등","2022-12-05 09:00","2022-12-05 18:00","취소","취소","연속"]
[32,"경기","직할","화성평택TP#2 T/L","2022-23 경기본부 직할변전협력회사 총액공사","LA, CVT 보통점검","2022-12-06 09:00","2022-12-06 18:00","취소","취소","연속"]
[33,"경기","직할","화성S/S #2 M.Tr","화성S/S 154kV 장기사용 GIS 교체공사(4차)","GIS대체(4차) 안전이격거리","2022-12-11 09:00","2022-12-11 18:00","2022-12-10 09:00","2022-12-11 18:00","연속"]
[34,"경기","평택","고덕#2S/S #2 M.Tr","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 변압기 종합예방진단장치 설치","2022-12-19 09:00","2022-12-21 18:00","2022-12-19 09:00","2022-12-21 18:00","연속"]
[35,"경기","평택","고덕#2S/S #1 M.Tr","345kV 고덕#2S/S 건설공사","345kV 고덕#2S/S 변압기 종합예방진단장치 설치","2022-12-14 09:00","2022-12-16 18:00","2022-12-14 09:00","2022-12-16 18:00","연속"]
[36,"경기","평택","고덕고덕2#1 T/L","북당진-고덕 2단계 HVDC 건설사업","고덕S/S 측 2단계 HVDC 연계용GIS(79, 7A) Bay 무부하가압 고덕C/S 2단계 필터 및 C.Tr용 전력케이블 무부하가압 고덕C/S 2단계 필터용GIS 무부하가압 고덕S/S #2BUS측 무부하가압","2022-12-01 09:00","2022-12-01 14:00","2022-12-01 09:00","2022-12-01 14:00","연속"]
[37,"경기","평택","고덕고덕2#2 T/L","북당진-고덕 2단계 HVDC 건설사업","고덕S/S 측 2단계 HVDC 연계용GIS(79, 7A) Bay 무부하가압 고덕C/S 2단계 필터 및 C.Tr용 전력케이블 무부하가압 고덕C/S 2단계 필터용GIS 무부하가압 고덕S/S #1BUS측 무부하가압","2022-12-01 14:00","2022-12-02 14:00","2022-12-01 14:00","2022-12-02 14:00","연속"]
[38,"경기","평택","고덕S/S #1 BUS","북당진-고덕 2단계 HVDC 건설사업","고덕S/S 측 2단계 HVDC 연계용GIS(79, 7A) Bay 무부하가압 고덕C/S 2단계 필터 및 C.Tr용 전력케이블 무부하가압 고덕C/S 2단계 필터용GIS 무부하가압 고덕S/S #1BUS측 무부하가압","2022-12-01 14:00","2022-12-02 14:00","2022-12-01 14:00","2022-12-02 14:00","연속"]
[39,"경기","평택","고덕S/S #2 BUS","북당진-고덕 2단계 HVDC 건설사업","고덕S/S 측 2단계 HVDC 연계용GIS(79, 7A) Bay 무부하가압 고덕C/S 2단계 필터 및 C.Tr용 전력케이블 무부하가압 고덕C/S 2단계 필터용GIS 무부하가압 고덕S/S #2BUS측 무부하가압","2022-12-01 09:00","2022-12-01 14:00","2022-12-01 09:00","2022-12-01 14:00","연속"]
[40,"경기","평택","화성평택TP#1 T/L","평택T/P 화성-평택T/P#1T/L 인출 DS 인디케이터 불량 보수","평택T/P 화성-평택T/P#1T/L 인출 7621 DS 인디케이터 축 불량 보수","2022-12-07 09:00","2022-12-07 18:00","취소","취소","연속"]
[41,"강원","강릉","강릉안인T/P CB 7271","2022년 강릉전력지사 변전협력회사 총액공사","강릉TP 안인-강릉#2TL CB(7271) 초기점검","2022-12-02 10:00","2022-12-02 18:00","취소","취소","연속"]
[42,"강원","강릉","신양양S/S CB 7171","2022년 강릉전력지사 변전협력회사 총액공사","신양양S/S 신양양-양양PP T/L CB(7171) 초기점검","2022-12-02 10:00","2022-12-02 18:00","2022-12-02 10:00","2022-12-02 18:00","연속"]
[43,"강원","강릉","안인개폐소 CB 7400","2022년 강릉전력지사 변전협력회사 총액공사","안인개폐소 안인-강릉#2TL CB(7400) 초기점검","2022-12-01 10:00","2022-12-01 14:00","취소","취소","연속"]
[44,"강원","강릉","안인개폐소 CB 7472","2022년 강릉전력지사 변전협력회사 총액공사","안인개폐소 안인-강릉#2TL CB(7472) 초기점검","2022-12-01 14:00","2022-12-01 18:00","취소","취소","연속"]
[45,"강원","동해","동해S/S STATCOM CB","동해전력지사 STATCOM 냉각설비 설비 개선","1. 냉각설비 설비개선 2. 냉각설비 점검","2022-12-05 09:00","2022-12-16 18:00","2022-12-05 09:00","2022-12-16 18:00","연속"]
[46,"충북","청주","남청주S/S #2 M.Tr","345kV M.Tr 보통점검","[22-23 청주전력 변전정비 총액공사] 남청주S/S 345kV #2M.Tr 보통점검","2022-12-03 10:00","2022-12-04 18:00","취소","취소","연속"]
[47,"대전세종충남","서산","당진T/P CB 7371","'22년도 차단기 조작시험","당진화력S/S #72 TIE-Tr 1차 CB (7371) CB 부동작 예방시험","2022-12-19 09:00","2022-12-19 14:00","2022-12-19 09:00","2022-12-19 14:00","연속"]
[48,"대전세종충남","서산","당진T/P CB 7300","'22년도 차단기 조작시험","당진화력S/S #72TIE-Tr 1차-TIE CB (7300) CB 부동작 예방시험","2022-12-19 14:00","2022-12-19 18:00","2022-12-19 14:00","2022-12-19 18:00","연속"]
[49,"대전세종충남","서산","당진T/P CB 7171","'22년도 차단기 조작시험","당진화력S/S #71 TIE-Tr 1차 CB (7171) CB 부동작 예방시험","2022-12-13 10:00","2022-12-13 18:00","2022-12-13 10:00","2022-12-13 18:00","연속"]
[50,"대전세종충남","서산","당진T/P #71 Tie-Tr","효성제 170kV GIS 베어링 발청관련 제작사 점검","당진화력S/S 345kV #71TIE-Tr 2차 6144 GIS 베어링 점검","2022-12-12 09:00","2022-12-12 18:00","2022-12-12 09:00","2022-12-12 18:00","연속"]
[51,"대전세종충남","서산","북당진S/S #2 BUS","북당진-고덕 2단계 HVDC 건설사업","북당진S/S 측 2단계 HVDC 연계용GIS(79, 7A) Bay 무부하가압 북당진C/S 2단계 필터 및 C.Tr용 전력케이블 무부하가압 북당진C/S 2단계 필터용GIS 무부하가압 북당진S/S #2BUS측 무부하가압","2022-12-01 17:00","2022-12-02 17:00","2022-12-01 17:00","2022-12-02 17:00","연속"]
[52,"대전세종충남","서산","북당진S/S #1 BUS","북당진-고덕 2단계 HVDC 건설사업","북당진S/S 측 2단계 HVDC 연계용GIS(79, 7A) Bay 무부하가압 북당진C/S 2단계 필터 및 C.Tr용 전력케이블 무부하가압 북당진C/S 2단계 필터용GIS 무부하가압 북당진S/S #1BUS측 무부하가압","2022-12-01 09:00","2022-12-01 17:00","2022-12-01 09:00","2022-12-01 17:00","연속"]
[53,"대전세종충남","서산","북당진현대제철 T/L","345kV 신송산분기T/L 건설공사","345kV 현대제철T/L 본선로 구성","2022-12-15 09:00","2022-12-21 18:00","취소","취소","연속"]
[54,"대전세종충남","서산","북당진S/S CB 7272","북당진S/S 345kV 7272CB 조작함 누유 보수","북당진S/S 345kV 7272CB 조작함 누유 보수","2022-12-08 09:00","2022-12-08 18:00","2022-12-08 09:00","2022-12-08 18:00","연속"]
[55,"대전세종충남","서산","북당진S/S CB 7200","북당진S/S 345kV 7200CB 조작함 누유 보수","북당진S/S 345kV 7200CB 조작함 누유 보수","2022-12-07 09:00","2022-12-07 18:00","2022-12-07 09:00","2022-12-07 18:00","연속"]
[56,"대전세종충남","서산","신당진개폐소현대제철 T/L","345kV 신송산분기T/L 건설공사","345kV 현대제철T/L 본선로 구성","2022-12-08 09:00","2022-12-14 18:00","취소","취소","연속"]
[57,"대전세종충남","서산","신당진S/S #3 M.Tr","신당진S/S 345kV #3M.Tr H0 부싱단자 과열보수","신당진S/S 345kV #3M.Tr H0 부싱단자 과열보수 (병행) 2차 GIS 베어링 발청관련 점검","2022-12-06 09:00","2022-12-06 18:00","취소","취소","연속"]
[58,"대전세종충남","천안","신온양서서울#2 T/L","345kV 신온양-서서울#2T/L CB 재폐로 회로개선","345kV 신온양-서서울#2T/L CB 재폐로 회로개선","2022-12-21 09:00","2022-12-21 18:00","취소","취소","연속"]
[59,"대전세종충남","천안","신온양서서울#1 T/L","345kV 신온양-서서울#1T/L CB 재폐로 회로개선","345kV 신온양-서서울#1T/L CB 재폐로 회로개선","2022-12-20 09:00","2022-12-20 18:00","취소","취소","연속"]
[60,"대전세종충남","천안","신온양S/S CB 7900","신온양S/S 7900, 7971GIS 보통점검","신온양S/S 7900, 7971GIS 보통점검","2022-12-09 14:00","2022-12-09 18:00","2022-12-09 14:00","2022-12-09 18:00","연속"]
[61,"대전세종충남","천안","신온양S/S CB 7971","신온양S/S 7900, 7971GIS 보통점검","신온양S/S 7900, 7971GIS 보통점검","2022-12-09 09:00","2022-12-09 14:00","2022-12-09 09:00","2022-12-09 14:00","연속"]
[62,"대전세종충남","천안","신온양서서울#1 T/L","(다른선로취소시)신온양S/S 345kV 78BAY B/F 교체","(다른선로취소시)신온양S/S 345kV 78BAY B/F 교체","2022-12-26 09:00","2022-12-30 18:00","취소","취소","연속"]
[63,"대전세종충남","천안","신온양신탕정#2 T/L","(다른선로취소시)신온양S/S 345kV 78BAY B/F 교체","(다른선로취소시)신온양S/S 345kV 78BAY B/F 교체","2022-12-26 09:00","2022-12-30 18:00","취소","취소","연속"]
[64,"대전세종충남","천안","신온양S/S #3 M.Tr","(다른선로취소시)신온양S/S 345kV 75BAY B/F 교체","(다른선로취소시)신온양S/S 345kV 75BAY B/F 교체","2022-12-19 09:00","2022-12-23 18:00","취소","취소","연속"]
[65,"대전세종충남","천안","신온양S/S CB 7571","(다른선로취소시)신온양S/S 345kV 75BAY B/F 교체","(다른선로취소시)신온양S/S 345kV 75BAY B/F 교체","2022-12-19 09:00","2022-12-23 18:00","취소","취소","연속"]
[66,"대전세종충남","천안","신온양서서울#2 T/L","(다른선로취소시)신온양S/S 345kV 77BAY B/F 교체","(다른선로취소시)신온양S/S 345kV 77BAY B/F 교체","2022-12-12 09:00","2022-12-16 18:00","취소","취소","연속"]
[67,"대전세종충남","천안","신온양S/S #4 M.Tr","(다른선로취소시)신온양S/S 345kV 77BAY B/F 교체","(다른선로취소시)신온양S/S 345kV 77BAY B/F 교체","2022-12-12 09:00","2022-12-16 18:00","취소","취소","연속"]
[68,"대전세종충남","천안","아산S/S CB 7172","아산S/S 345kV 7171, 7172, 7271CB 개폐타임 측정","아산S/S 345kV 7171, 7172, 7271CB 개폐타임 측정","2022-12-21 11:00","2022-12-21 15:00","취소","취소","연속"]
[69,"대전세종충남","천안","아산S/S CB 7271","아산S/S 345kV 7171, 7172, 7271CB 개폐타임 측정","아산S/S 345kV 7171, 7172, 7271CB 개폐타임 측정","2022-12-21 15:00","2022-12-21 18:00","취소","취소","연속"]
[70,"대전세종충남","천안","아산보령TP#1 T/L","23kV 1-2Sh.R 설치 이격거리 확보 휴전","23kV 1-2Sh.R 설치 이격거리 확보 휴전","2022-12-13 14:00","2022-12-16 18:00","취소","취소","매일"]
[71,"대전세종충남","천안","아산S/S #4 M.Tr","아산S/S 345kV #4 M.Tr 1,2차 부싱절연유 채유","아산S/S 345kV #4 M.Tr 1,2차 부싱절연유 채유","2022-12-15 09:00","2022-12-15 18:00","취소","취소","연속"]
[72,"대전세종충남","천안","아산S/S CB 7171","아산S/S 345kV 7171, 7172, 7271CB 개폐타임 측정","아산S/S 345kV 7171, 7172, 7271CB 개폐타임 측정","2022-12-21 09:00","2022-12-21 11:00","취소","취소","연속"]
[73,"대전세종충남","청양","보령C/C CB 7271","345kV 차단기 부동작 예방 조작시험(7271)","345kV 차단기 부동작 예방 조작시험(7271)","2022-12-01 13:00","2022-12-01 15:00","2022-12-01 13:00","2022-12-01 15:00","연속"]
[74,"대전세종충남","청양","보령C/C CB 7171","345kV 차단기 부동작 예방 조작시험(7171)","345kV 차단기 부동작 예방 조작시험(7171)","2022-12-01 10:00","2022-12-01 12:00","2022-12-01 10:00","2022-12-01 12:00","연속"]
[75,"대전세종충남","청양","청양S/S CB 7172","345kV 차단기 부동작 예방 조작시험(7172)","345kV 차단기 부동작 예방 조작시험(7172)","2022-12-05 10:00","2022-12-05 12:00","2022-12-05 10:00","2022-12-05 12:00","연속"]
[76,"대전세종충남","청양","청양S/S CB 7571","345kV 차단기 부동작 예방 조작시험(7571)","345kV 차단기 부동작 예방 조작시험(7571)","2022-12-05 13:00","2022-12-05 15:00","2022-12-05 13:00","2022-12-05 15:00","연속"]
[77,"대전세종충남","청양","청양S/S CB 7372","345kV 차단기 부동작 예방 조작시험(7372)","345kV 차단기 부동작 예방 조작시험(7372)","2022-12-06 15:00","2022-12-06 18:00","2022-12-06 15:00","2022-12-06 18:00","연속"]
[78,"대전세종충남","청양","청양S/S CB 7300","345kV 차단기 부동작 예방 조작시험(7300)","345kV 차단기 부동작 예방 조작시험(7300)","2022-12-06 13:00","2022-12-06 15:00","2022-12-06 13:00","2022-12-06 15:00","연속"]
[79,"대전세종충남","청양","청양S/S CB 7500","345kV 차단기 부동작 예방 조작시험(7500)","345kV 차단기 부동작 예방 조작시험(7500)","2022-12-05 15:00","2022-12-05 18:00","2022-12-05 15:00","2022-12-05 18:00","연속"]
[80,"대전세종충남","청양","청양S/S CB 7371","345kV 차단기 부동작 예방 조작시험(7371)","345kV 차단기 부동작 예방 조작시험(7371)","2022-12-06 10:00","2022-12-06 12:00","2022-12-06 10:00","2022-12-06 12:00","연속"]
[81,"전북","군산","군산새만금#1 T/L","군산변전소 345kV GIS 대체공사 (무부하가압)","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2022-12-30 18:00","2022-12-31 18:00","2022-12-30 18:00","2022-12-31 18:00","연속"]
[82,"전북","군산","군산S/S #75 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2022-12-20 09:00","2022-12-31 18:00","2022-12-20 09:00","2022-12-31 18:00","연속"]
[83,"전북","군산","군산S/S #70 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2022-12-01 09:00","2022-12-12 18:00","2022-12-01 09:00","2022-12-12 18:00","연속"]
[84,"전북","군산","군산새만금#1 T/L","군산변전소 345kV GIS 대체공사 (무부하가압)","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2022-12-11 18:00","2022-12-12 18:00","2022-12-11 18:00","2022-12-12 18:00","연속"]
[85,"전북","직할","신남원S/S CB 7272","전북직할 362kV 단독차단기 정밀점검(7272)","전북직할 362kV 단독차단기 정밀점검(7272)","2022-12-05 09:00","2022-12-09 18:00","2022-12-05 09:00","2022-12-09 18:00","연속"]
[86,"전북","직할","신남원신광주#2 T/L","전북직할 362kV 단독차단기 정밀점검(7272) 무부하가압","전북직할 362kV 단독차단기 정밀점검(7272) 무부하가압","2022-12-09 16:00","2022-12-09 18:00","2022-12-09 16:00","2022-12-09 18:00","연속"]
[87,"전북","직할","신남원S/S #2 BUS","전북직할 362kV 단독차단기 정밀점검(7272) 무부하가압","전북직할 362kV 단독차단기 정밀점검(7272) 무부하가압","2022-12-09 16:00","2022-12-09 18:00","2022-12-09 16:00","2022-12-09 18:00","연속"]
[88,"광주전남","순천","광양여수TP T/L","광양CC-여수TP T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직, 수평 추락방지장치 설치","2022-12-01 07:00","2022-12-01 12:00","취소","취소","연속"]
[89,"광주전남","순천","여수T/P #1 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 345Kv #1M.Tr 2차 LA 대체","2022-12-01 09:00","2022-12-02 18:00","2022-12-01 09:00","2022-12-02 18:00","연속"]
[90,"광주전남","순천","율촌CC여수TP T/L","광양CC-여수TP T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직, 수평 추락방지장치 설치","2022-12-02 07:00","2022-12-02 12:00","취소","취소","연속"]
[91,"광주전남","순천","여수T/P #3 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 설치 및 DGA 배관 설치","2022-12-03 09:00","2022-12-04 18:00","2022-12-03 09:00","2022-12-04 18:00","연속"]
[92,"광주전남","광주","신광주신화순#1 T/L","22~23년 광주전력지사 송전협력회사 총액공사","345kV 신광주-신화순#1T/L 수평추락방지장치 설치","2022-12-05 07:00","2022-12-10 18:00","취소","취소","매일"]
[93,"광주전남","순천","여수T/P #2 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 설치 및 DGA 배관 설치","2022-12-05 09:00","2022-12-06 18:00","취소","취소","연속"]
[94,"광주전남","광주","신화순S/S #3 M.Tr","22~23년 광주전력지사 변전협력회사 총액공사","#3M.Tr 3차측 절연보강","2022-12-07 09:00","2022-12-07 18:00","2022-12-07 09:00","2022-12-07 18:00","연속"]
[95,"광주전남","순천","여수T/P #4 Tie-Tr","종합예방진단시스템 5차분 설치공사","부싱 누설전류 센서 설치 및 DGA 배관 설치","2022-12-07 09:00","2022-12-08 18:00","취소","취소","연속"]
[96,"광주전남","광주","신광주신화순#2 T/L","22~23년 광주전력지사 송전협력 총액공사","345kV 신광주-신화순#2T/L 수평추락방지장치 설치공사","2022-12-12 07:00","2022-12-17 18:00","취소","취소","매일"]
[97,"광주전남","광주","신광주S/S CB 7500","22~23년 광주 변전협력회사 총액공사","- 신광주S/S 조상설비 제어 고장파급방지시스템 설치","2022-12-12 09:00","2022-12-14 18:00","2022-12-12 09:00","2022-12-14 18:00","연속"]
[98,"광주전남","광주","신광주S/S CB 7572","22~23년 광주 변전협력회사 총액공사","- 신광주S/S 조상설비 제어 고장파급방지시스템 설치","2022-12-12 09:00","2022-12-14 18:00","2022-12-12 09:00","2022-12-14 18:00","연속"]
[99,"광주전남","광주","신광주S/S #1 Sh.R CB","22~23년 광주 변전협력회사 총액공사","- 신광주S/S 조상설비 제어 고장파급방지장치 설치","2022-12-12 09:00","2022-12-14 18:00","2022-12-12 09:00","2022-12-14 18:00","연속"]
[100,"광주전남","순천","여수T/P CB 7300","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 율촌CC-여수TPT/L-#3M.Tr 1차 TIE GIS 7300 CB 보통점검","2022-12-15 09:00","2022-12-15 18:00","취소","취소","연속"]
[101,"광주전남","순천","여수T/P CB 7171","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 광양CC-여수TP #1T/L GIS 7271 CB 타임측정","2022-12-16 09:00","2022-12-16 14:00","2022-12-16 09:00","2022-12-16 14:00","연속"]
[102,"광주전남","순천","여수T/P CB 7271","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/Y 광양CC-여수TP #2T/L GIS 7271 CB 타임측정","2022-12-16 14:00","2022-12-16 18:00","2022-12-16 14:00","2022-12-16 18:00","연속"]
[103,"대구","경산","신경산S/S #2 M.Tr","22-23년 경산PO 변전협력회사 총액공사","- 부싱절연유 채유","2022-12-01 09:00","2022-12-01 14:00","2022-12-01 09:00","2022-12-01 14:00","연속"]
[104,"대구","칠곡","북대구S/S #1 M.Tr","북대구S/S #1M.Tr 보호반 43PDA 교체작업","북대구S/S #1M.Tr 보호반 43PDA 교체작업","2022-12-02 09:30","2022-12-02 18:00","2022-12-02 09:30","2022-12-02 18:00","연속"]
[105,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 154kV 옥외철구 설비 GIS화 공사","서대구S/S 옥외철구 설비 철거 관련 안전이격 확보","2022-12-05 08:30","2022-12-09 18:00","2022-12-19 08:30","2022-12-23 18:00","연속"]
[106,"대구","포항","신영일안동CC T/L","신영일S/S 신영일-안동CC T/L PT,LA 대체작업","신영일S/S 신영일-안동CC T/L PT,LA 대체작업","2022-12-21 09:00","2022-12-22 18:00","2022-12-06 09:00","2022-12-07 18:00","연속"]
[107,"대구","포항","신포항신월성NP#3 T/L","염해방지 애자코팅공사","염해방지 애자코팅공사","2022-12-05 09:00","2022-12-05 18:00","2022-12-05 09:00","2022-12-05 18:00","연속"]
[108,"대구","포항","신월성N/P CB 7472","신월성S/Y 7400,7472 GIS 보통점검","신월성S/Y 7400,7472 GIS 보통점검","2022-12-05 09:00","2022-12-05 18:00","2022-12-05 09:00","2022-12-05 18:00","연속"]
[109,"대구","포항","신월성N/P CB 7372","신월성S/Y 7300,7372 GIS 보통점검","신월성S/Y 7300,7372 GIS 보통점검","2022-12-20 09:00","2022-12-20 18:00","2022-12-20 09:00","2022-12-20 18:00","연속"]
[110,"대구","포항","신월성N/P CB 7300","신월성S/Y 7300,7372 GIS 보통점검","신월성S/Y 7300,7372 GIS 보통점검","2022-12-20 09:00","2022-12-20 18:00","2022-12-20 09:00","2022-12-20 18:00","연속"]
[111,"대구","포항","월성NP신월성NP#1 T/L","염해방지 애자코팅공사","염해방지 애자코팅공사","2022-12-20 09:00","2022-12-22 18:00","2022-12-20 09:00","2022-12-22 18:00","연속"]
[112,"대구","포항","신월성N/P CB 7400","신월성S/Y 7400,7472 GIS 보통점검","신월성S/Y 7400,7472 GIS 보통점검","2022-12-05 09:00","2022-12-05 18:00","2022-12-05 09:00","2022-12-05 18:00","연속"]
[113,"경북","구미","선산S/S #75 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #2BUS 설치","2022-12-12 09:30","2022-12-19 18:00","2022-12-12 09:30","2022-12-19 18:00","연속"]
[114,"경북","구미","선산S/S #3 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #2BUS 설치관련 안전거리 확보","2022-12-16 09:30","2022-12-16 18:00","2022-12-16 09:30","2022-12-16 18:00","연속"]
[115,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #2BUS 설치관련 무부하가압 시험선로","2022-12-17 09:00","2022-12-19 09:00","2022-12-17 09:00","2022-12-19 09:00","연속"]
[116,"경북","구미","선산신포항 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #2BUS 설치관련 안전거리 확보","2022-12-23 09:00","2022-12-23 18:00","2022-12-23 09:00","2022-12-23 18:00","연속"]
[117,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #1BUS 설치관련 무부하가압 시험선로","2022-12-24 09:00","2022-12-26 09:00","2022-12-24 09:00","2022-12-26 09:00","연속"]
[118,"경북","구미","선산S/S #70 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","345kV #1BUS 설치","2022-12-19 09:00","2022-12-26 09:00","2022-12-19 09:00","2022-12-26 09:00","연속"]
[119,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S 345kV 용량부족 차단기 교체공사 2차","신양산 345kV 용량부족 차단기 교체공사 2차 - 73BAY GIS 교체(7371,7300,7372)","2022-12-19 09:00","2023-03-18 18:00","취소","취소","연속"]
[120,"부산울산","동부산","신양산신대연#2 T/L","'22~'23년 동부산전력지가 가공송전 협력회사 총액공사","-345kV 신양산-신대연#2T/L 고장구간 이도조정","2022-12-19 07:00","2022-12-21 18:00","취소","취소","연속"]
[121,"부산울산","동부산","신양산북부산#2 T/L","신양산S/S 345kV 용량부족 차단기 교체공사 2차","신양산 345kV 용량부족 차단기 교체공사 2차 - 73BAY GIS 교체(7371,7300,7372)","2022-12-19 09:00","2023-03-18 18:00","취소","취소","연속"]
[122,"부산울산","동부산","신양산S/S #2 BUS","신양산S/S 345kV 용량부족 차단기 교체공사 1차","신양산 345kV 용량부족 차단기 교체공사 1차 - 72BAY GIS 시험가압용도","2022-12-05 09:00","2022-12-05 18:00","취소","취소","연속"]
[123,"부산울산","동부산","신양산S/S #1 BUS","신양산S/S 345kV 용량부족 차단기 교체공사 1차","신양산 345kV 용량부족 차단기 교체공사 1차 - 72BAY GIS 시험가압용도","2022-12-05 09:00","2022-12-05 18:00","취소","취소","연속"]
[124,"부산울산","북부산","북부산S/S #3 M.Tr","22-23년 북부산전력지사 변전총액공사","북부산S/S 345kV #3M.Tr 보통점검","2022-12-07 09:00","2022-12-08 18:00","2022-12-07 09:00","2022-12-08 18:00","연속"]
[125,"부산울산","서부산","서부산S/S #3,4GT CB","서부산S/S 345kV #3,4 G/T GIS 동작시험","서부산S/S 345kV #3,4 G/T GIS 동작시험","2022-12-06 09:00","2022-12-06 18:00","취소","취소","연속"]
[126,"부산울산","울산","신온산남울산#2 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2022-12-15 07:00","2023-01-03 18:00","취소","취소","연속"]
[127,"부산울산","울산","신온산S/S #1 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","74Bay GIS 대체 관련 #1BUS 시험가압","2022-12-13 09:00","2022-12-13 12:00","2022-12-13 09:00","2022-12-13 12:00","연속"]
[128,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","74Bay GIS 대체 관련 #2BUS 시험가압","2022-12-13 12:00","2022-12-13 15:00","2022-12-13 12:00","2022-12-13 15:00","연속"]
[129,"부산울산","울산","신온산S/S #4 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","75Bay GIS 대체공사 관련 안전이격거리 확보","2022-12-15 09:00","2023-01-04 18:00","2022-12-15 09:00","2023-01-04 18:00","연속"]
[130,"부산울산","울산","신온산S/S #2 BUS","345kV 신온산S/S 용량부족 차단기 대체공사","75Bay GIS 대체공사(7500, 7572)","2022-12-15 09:00","2023-01-03 18:00","2022-12-15 09:00","2023-01-03 18:00","연속"]
[131,"부산울산","울산","신온산S/S SOIL#6 T/L CB","345kV 신온산S/S 용량부족 차단기 대체공사","75Bay GIS 대체공사(7500, 7572)","2022-12-15 09:00","2023-02-07 18:00","2022-12-15 09:00","2023-02-07 18:00","연속"]
[132,"부산울산","울산","신온산S/S #3 M.Tr","345kV 신온산S/S 용량부족 차단기 대체공사","75Bay GIS 대체공사(7500, 7572)","2022-12-15 09:00","2023-02-07 18:00","2022-12-15 09:00","2023-02-07 18:00","연속"]
[133,"부산울산","울산","울주신경산#2 T/L","22년 하반기 345kV 개폐장치 정밀점검공사","GIS(7700) 정밀점검","2022-12-05 09:00","2022-12-07 18:00","2022-12-05 09:00","2022-12-07 18:00","연속"]
[134,"부산울산","울산","울주신경산#1 T/L","22년 하반기 345kV 개폐장치 정밀점검공사","GIS(7800) 정밀점검","2022-12-08 09:00","2022-12-10 18:00","2022-12-08 09:00","2022-12-10 18:00","연속"]
[135,"부산울산","울산","울주S/S CB 7672","22년 하반기 345kV 개폐장치 정밀점검공사","GIS(7672) 정밀점검","2022-12-12 09:00","2022-12-14 18:00","2022-12-12 09:00","2022-12-14 18:00","연속"]
[136,"부산울산","울산","울주S/S #3 M.Tr","22년 하반기 345kV 개폐장치 정밀점검공사","GIS(7672) 정밀점검관련 시험가압(1Hr)","2022-12-14 17:00","2022-12-14 18:00","2022-12-14 17:00","2022-12-14 18:00","연속"]
[137,"경남","함안","의령신마산#1 T/L","345kV 의령-신마산#1T/L 추락방지장치 설치공사","345kV 의령-신마산#1T/L 32, 106호 추락방지장치 설치공사(2기)[휴전작업]","2022-12-01 07:00","2022-12-01 18:00","2022-12-01 07:00","2022-12-01 18:00","연속"]
[138,"경남","함안","의령신마산#2 T/L","345kV 의령-신마산#2T/L 추락방지장치 설치공사","345kV 의령-신마산#2T/L 32, 106호 추락방지장치 설치공사(2기)[휴전작업]","2022-12-02 07:00","2022-12-02 13:00","2022-12-02 07:00","2022-12-02 13:00","연속"]
[139,"대구",null,"신월성N/P #1 대기보조변압기 (CB 7300, 7372)","신월성 1호기 7차  계획예방정비, #1 대기보조변압기(SAT) 점검 *조작차단기 : PCB 7300, 7372","○ 대기보조변압기 일반점검 등","2022-12-18 10:00","2023-01-01 16:00","2022-12-18 10:00","2023-01-01 16:00","연속"]
[140,"경북",null,"한울N/P #5 대기보조변압기 (CB 7E00, 7E72)","한울5호기 13차 계획예방정비 * 조작차단기: CB 7E00, 7E72","○ 대기보조변압기 일반점검 ○ 대기보조변압기 OLTC AVR 설계변경","2022-12-01 17:00","2022-12-13 16:00","2022-12-01 17:00","2022-12-13 16:00","연속"]
[141,"경북",null,"신한울N/P #2 대기보조변압기 (CB 7200, 7272)","신한울2호기 주기시험 수행 *조작 차단기 : CB 7200, 7272","○ 신한울2호기 보호계전기 연동시험 수행","2022-12-13 11:00","2022-12-16 15:00","2022-12-13 11:00","2022-12-16 15:00","연속"]
[142,"강원",null,"양양P/P #1 M.Tr (CB 7100, 7172)","주변압기 상부 누유점검 등","양양 P/P No.1 T/L 휴전","2022-12-07 09:00","2022-12-07 18:00","2022-12-07 09:00","2022-12-07 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":231,"n_cols":11,"rows_kept":231,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2022년도 12월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-12-08 14:00","2022-12-08 18:00","2022-12-08 14:00","2022-12-08 18:00","연속"]
[2,"서울","성동","구의광장#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2022-12-08 10:00","2022-12-08 14:00","2022-12-08 10:00","2022-12-08 14:00","연속"]
[3,"서울","성동","장암방학#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-12-02 10:00","2022-12-02 18:00","2022-12-02 10:00","2022-12-02 18:00","연속"]
[4,"서울","성동","양주쌍문#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 양주-쌍문T/L No.39(1기) 수평 추락방지시설 설치공사","2022-12-05 07:00","2022-12-05 13:00","취소","취소","연속"]
[5,"서울","성동","양주쌍문#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 양주-쌍문T/L No.39(1기) 수평 추락방지시설 설치공사","2022-12-05 13:00","2022-12-05 18:00","취소","취소","연속"]
[6,"서울","성동","왕십리용두 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-12-05 10:00","2022-12-05 17:00","2022-12-05 10:00","2022-12-05 17:00","연속"]
[7,"서울","성동","마장용두 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-12-06 10:00","2022-12-06 17:00","2022-12-06 10:00","2022-12-06 17:00","연속"]
[8,"서울","성동","휘경종암#2 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-12-02 10:00","2022-12-02 17:00","2022-12-02 10:00","2022-12-02 17:00","연속"]
[9,"서울","성동","휘경종암#1 T/L","2022년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2022-12-01 10:00","2022-12-01 17:00","2022-12-01 10:00","2022-12-01 17:00","연속"]
[10,"서울","중부","상암등촌#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 상암-등촌T/L No.1(1기) 수평 추락방지시설 설치공사","2022-12-07 13:00","2022-12-07 18:00","2022-12-03 13:00","2022-12-03 18:00","연속"]
[11,"서울","중부","상암등촌#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 상암-등촌T/L No.1(1기) 수평 추락방지시설 설치공사","2022-12-07 07:00","2022-12-07 13:00","2022-12-03 07:00","2022-12-03 13:00","연속"]
[12,"서울","중부","지축현저#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 지축-현저T/L No.4,4.1(2기) 수평 추락방지시설 설치공사","2022-12-08 13:00","2022-12-08 18:00","2022-12-08 13:00","2022-12-08 18:00","연속"]
[13,"서울","중부","지축현저#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 지축-현저T/L No.4,4.1(2기) 수평 추락방지시설 설치공사","2022-12-08 07:00","2022-12-08 13:00","2022-12-08 07:00","2022-12-08 13:00","연속"]
[14,"서울","성동","미금성동#3 T/L","22년 성동P/O 변전협력회사 총액공사","22년 성동P/O 변전협력회사 총액공사","2022-12-05 09:00","2022-12-05 18:00","취소","취소","연속"]
[15,"서울","성동","성동S/S #1 M.Tr","2022년 성동P/O 변전협력회사 총액공사","2022년 성동P/O 변전협력회사 총액공사","2022-12-14 09:00","2022-12-15 20:00","취소","취소","연속"]
[16,"서울","성동","성동S/S #2 M.Tr","2022년 성동P/O 변전협력회사 총액공사","2022년 성동P/O 변전협력회사 총액공사","2022-12-12 09:00","2022-12-13 20:00","취소","취소","연속"]
[17,"서울","성동","성동S/S #4 M.Tr","성동S/S #4M.Tr 러버백 교체","성동S/S #4M.Tr 러버백 교체","2022-12-05 09:00","2022-12-09 18:00","취소","취소","연속"]
[18,"서울","성동","성동S/S CB 7500","22년 성동P/O 변전협력회사 총액공사","22년 성동P/O 변전협력회사 총액공사","2022-12-05 09:00","2022-12-07 18:00","취소","취소","연속"]
[19,"남서울","동서울","강동S/S #1 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화공사 관련 무부하선로","2022-12-17 10:00","2022-12-17 10:10","2022-12-17 10:00","2022-12-17 10:10","연속"]
[20,"남서울","동서울","강동S/S CB 6100","154kV 강동S/S #1M.Tr 교체공사","154kV 강동S/S #1M.Tr 무부하가압","2022-12-11 10:00","2022-12-11 11:00","2022-12-11 10:00","2022-12-11 11:00","연속"]
[21,"남서울","동서울","강동S/S #2 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화공사 관련 무부하선로","2022-12-26 10:00","2022-12-26 10:10","2022-12-26 10:00","2022-12-26 10:10","연속"]
[22,"남서울","동서울","강동S/S #1 BUS","154kV 강동S/S #1M.Tr 교체공사","154kV 강동S/S #1M.Tr 무부하가압","2022-12-11 10:00","2022-12-11 11:00","2022-12-11 10:00","2022-12-11 11:00","연속"]
[23,"남서울","동서울","동서울S/S #68G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 지중화공사 관련 무부하가압 선로","2022-12-04 10:00","2022-12-05 18:00","취소","취소","연속"]
[24,"남서울","동서울","동서울위례#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 지중화공사 관련 무부하선로","2022-12-04 10:00","2022-12-05 18:00","취소","취소","연속"]
[25,"남서울","동서울","동서울서종#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 지중화공사 관련 휴전","2022-12-01 08:00","2022-12-05 18:00","2022-11-30 12:00","2022-12-05 18:00","연속"]
[26,"남서울","동서울","동서울S/S #65G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 지중화공사 관련 무부하가압 선로","2022-12-04 10:00","2022-12-05 18:00","2022-12-04 10:00","2022-12-05 18:00","연속"]
[27,"남서울","동서울","동서울S/S #67G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 지중화공사 관련 무부하가압 선로","2022-12-04 10:00","2022-12-05 18:00","취소","취소","연속"]
[28,"남서울","동서울","동서울강동#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화공사","2022-12-10 09:00","2022-12-18 18:00","2022-12-10 09:00","2022-12-18 18:00","연속"]
[29,"남서울","동서울","동서울S/S #65G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화공사 관련 무부하선로","2022-12-17 10:00","2022-12-18 10:00","2022-12-17 10:00","2022-12-18 10:00","연속"]
[30,"남서울","동서울","동서울S/S #67G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화공사 관련 무부하선로","2022-12-26 10:00","2022-12-27 10:00","2022-12-26 10:00","2022-12-27 10:00","연속"]
[31,"남서울","동서울","동서울S/S #66G BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 지중화공사 관련 무부하가압 선로","2022-12-04 10:00","2022-12-05 18:00","취소","취소","연속"]
[32,"남서울","동서울","잠실수서#2 T/L","수서SS 잠실-수서#2T/L LA 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2022-12-01 09:00","2022-12-01 18:00","2022-12-01 09:00","2022-12-01 18:00","연속"]
[33,"남서울","동서울","동서울위례#2 T/L","154kV 위례S/S #4M.Tr 증설공사","유입변압기 1BANK 설치","2022-12-13 10:00","2022-12-14 10:00","2022-12-13 10:00","2022-12-14 10:00","연속"]
[34,"남서울","동서울","위례S/S #61 BUS","154kV 위례S/S #4M.Tr 증설공사","유입변압기 1BANK 설치","2022-12-13 10:00","2022-12-13 16:00","2022-12-13 10:00","2022-12-13 16:00","연속"]
[35,"남서울","동서울","위례S/S #66 BUS","154kV 위례S/S #4M.Tr 증설공사","유입변압기 1BANK 설치","2022-12-13 16:00","2022-12-14 10:00","2022-12-13 16:00","2022-12-14 10:00","연속"]
[36,"남서울","영등포","신광명광명#1 T/L","광명S/S 장기사용 154kV GIS 교체","-광명-구공#2T/L GIS 교체 -BUS-TIE 6200 설치 -기타작업 -#1BUS 무부하 가압 선로","2022-12-07 18:00","2022-12-08 18:00","2022-12-07 18:00","2022-12-08 18:00","연속"]
[37,"남서울","강남","신양재신사#2 T/L","신사S/S 신양재-신사#2T/L GIS 조작시험","신사S/S 신양재-신사#2T/L GIS 조작시험 (동서울 현대화 관련 계통변경으로 평일작업 불가)","2022-12-10 09:00","2022-12-10 18:00","2022-12-10 09:00","2022-12-10 18:00","연속"]
[38,"인천","부평","원창포스코CC#2 T/L","154kV 원창S/S SW 증설공사","154kV 원창S/S SW 증설공사 - #1BUS 측 무부하가압","2022-12-01 10:00","2022-12-02 10:00","2022-12-01 10:00","2022-12-02 10:00","연속"]
[39,"인천","시흥","남동연수#2 T/L","남동S/S 170kV 남동연수#2 T/L GIS 메커니즘 점검","남동S/S 170kV 남동연수#2 T/L GIS 메커니즘 점검","2022-12-07 09:00","2022-12-07 18:00","2022-12-07 09:00","2022-12-07 18:00","연속"]
[40,"인천","시흥","남동연수#1 T/L","남동S/S 170kV 남동연수#1 T/L GIS 메커니즘 점검","남동S/S 170kV 남동연수#1 T/L GIS 메커니즘 점검","2022-12-06 09:00","2022-12-06 18:00","2022-12-06 09:00","2022-12-06 18:00","연속"]
[41,"경기북부","구리","미금화양 T/L","미금S/S 154kV #64M.Tr 증설공사","6433 GIS - #64M.Tr - 4444 EGIS 무부하가압","2022-12-06 12:00","2022-12-07 18:00","2022-12-10 12:00","2022-12-11 18:00","연속"]
[42,"경기북부","구리","미금S/S #61 BUS","미금S/S 154kV #64M.Tr 증설공사","인터록시험, #64M.Tr 최초가압","2022-12-05 09:00","2022-12-07 18:00","2022-12-10 09:00","2022-12-11 18:00","연속"]
[43,"경기북부","구리","미금S/S #66 BUS","미금S/S 154kV #64M.Tr 증설공사","인터록시험","2022-12-01 09:00","2022-12-02 18:00","2022-12-03 09:00","2022-12-04 18:00","연속"]
[44,"경기북부","구리","서종S/S #60 BUS","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-서종T/L 지중화공사 관련 상체크용 선로","2022-12-04 10:00","2022-12-04 10:10","2022-12-04 10:00","2022-12-04 10:10","연속"]
[45,"경기북부","직할","신포천덕계#2 T/L","22-23 변전협력 총액공사","신포천-덕계 #2T/L LA 보통점검","2022-12-05 14:00","2022-12-05 18:00","2022-12-05 14:00","2022-12-05 18:00","연속"]
[46,"경기북부","직할","신포천덕계#1 T/L","22-23 변전협력 총액공사","신포천-덕계 #1T/L LA 보통점검","2022-12-05 09:00","2022-12-05 14:00","2022-12-05 09:00","2022-12-05 14:00","연속"]
[47,"경기북부","직할","신의정부송우#1 T/L","신의정부S/S 154kV Sh.C 이설공사","신의정부S/S 154kV Sh.C용 GIS 설치 - 무부하 시험가압","2022-12-12 08:00","2022-12-14 18:00","2022-12-12 08:00","2022-12-14 18:00","연속"]
[48,"경기북부","직할","신의정부S/S #62 BUS","신의정부S/S 154kV Sh.C 이설공사","신의정부S/S 154kV Sh.C용 GIS 설치 - 무부하 시험가압","2022-12-12 08:00","2022-12-14 18:00","2022-12-12 08:00","2022-12-14 18:00","연속"]
[49,"경기북부","직할","신의정부S/S #67 BUS","신의정부S/S 154kV Sh.C 이설공사","신의정부S/S 154kV Sh.C용 GIS 설치 - 170kV GIS #67BUS 측 조립 - 무부하 시험가압","2022-12-05 08:00","2022-12-10 18:00","2022-12-05 08:00","2022-12-10 18:00","연속"]
[50,"경기","군포","남군포산본#2 T/L","남군포S/S 154kV SW증설공사","남군포S/S 154kV SW증설공사 무부하가압 -남군포-의왕#1,#2T/L GIS 증설","2022-12-05 09:00","2022-12-06 18:00","2022-12-05 09:00","2022-12-06 18:00","연속"]
[51,"경기","군포","남군포산본#1 T/L","남군포S/S 154kV SW 증설공사","현대모비스T/L 무부하가압","2022-12-13 10:00","2022-12-14 10:00","2022-12-13 10:00","2022-12-14 10:00","연속"]
[52,"경기","군포","마도사강#2 T/L","154kV 마도S/S #4M.Tr 증설공사","마도S/S #4M.Tr 증설공사-#4M.Tr 무부하가압","2022-12-19 09:00","2022-12-20 18:00","2022-12-19 09:00","2022-12-20 18:00","연속"]
[53,"경기","동부","오포모현#2 T/L","오포SS #4M.Tr 1차 GIS 증설","오포: #4M.Tr용 1차 GIS 증설 오포-모현#2T/L:11.25 - 11.26","2022-12-02 09:00","2022-12-03 18:00","2022-12-02 09:00","2022-12-03 18:00","연속"]
[54,"경기","동부","오포모현#2 T/L","오포: #4M.Tr용 1차 GIS 증설","오포: #4M.Tr용 1차 GIS 증설","2022-12-09 09:00","2022-12-10 18:00","2022-12-09 09:00","2022-12-10 18:00","연속"]
[55,"경기","동부","오포S/S #2 BUS","오포SS #4M.Tr 1차 GIS 증설","오포: #4M.Tr용 1차 GIS 증설 154kV #2BUS : 11.28 - 12.03","2022-12-05 09:00","2022-12-09 18:00","2022-12-05 09:00","2022-12-09 18:00","연속"]
[56,"경기","동부","초월성현#1 T/L","초월 154kV #5M.Tr 증설공사","#5M.Tr 무부하 가압용","2022-12-05 09:00","2022-12-06 18:00","2022-12-05 09:00","2022-12-06 18:00","연속"]
[57,"경기","직할","서수원율전#1 T/L","21-22년 지중송전설비 위탁정비공사","LA 및 C/T 점검","2022-12-01 09:00","2022-12-01 13:00","2022-12-01 09:00","2022-12-01 13:00","연속"]
[58,"경기","직할","서수원율전#2 T/L","21-22년 지중송전설비 위탁정비공사","LA 및 C/T 점검","2022-12-01 13:00","2022-12-01 18:00","2022-12-01 13:00","2022-12-01 18:00","연속"]
[59,"경기","직할","의왕동안양#2 T/L","서서울,의왕S/S 154kV SW 증설공사","남군포-의왕#1T/L GIS #2DS, 상부모선 설치 무부하가압","2022-12-22 18:00","2022-12-23 18:00","2022-12-22 18:00","2022-12-23 18:00","연속"]
[60,"경기","직할","의왕동안양#2 T/L","서서울,의왕S/S 154kV SW 증설공사","#2PT 이설 및 남군포-의왕#1T/L GIS #2BUS GIB 설치 무부하가압","2022-12-01 18:00","2022-12-02 18:00","2022-12-01 18:00","2022-12-02 18:00","연속"]
[61,"경기","직할","의왕동안양#2 T/L","서서울,의왕S/S 154kV SW 증설공사","1PT 이설 및 남군포-의왕#1T/L GIS #1DS, CB 설치 무부하가압","2022-12-14 13:00","2022-12-15 13:00","2022-12-14 13:00","2022-12-15 13:00","연속"]
[62,"경기","직할","화성수촌#2 T/L","화성S/S 154kV 장기사용 GIS 교체공사(4차)","GIS대체(4차) 안전이격","2022-12-03 09:00","2022-12-04 18:00","2022-12-03 09:00","2022-12-04 18:00","연속"]
[63,"경기","직할","화성S/S #60 BUS","화성S/S 154kV 장기사용 GIS 교체공사(4차)","대체GIS 무부하가압","2022-12-01 13:00","2022-12-10 18:00","2022-12-01 13:00","2022-12-10 18:00","연속"]
[64,"경기","직할","화성S/S #66 BUS","화성S/S 154kV 장기사용 GIS 교체공사(4차)","  #65-66BUS SEC 도킹","2022-12-11 09:00","2022-12-13 18:00","2022-12-11 09:00","2022-12-13 18:00","연속"]
[65,"경기","직할","화성수촌#2 T/L","화성S/S 154kV 장기사용 GIS 교체공사(4차)","GIS대체(4차) 안전이격거리","2022-12-11 09:00","2022-12-13 18:00","2022-12-11 09:00","2022-12-13 18:00","연속"]
[66,"경기","직할","화성S/S #65 BUS","화성S/S 154kV 장기사용 GIS 교체공사(4차)","#65-66BUS SECTION 위상측정","2022-12-13 12:00","2022-12-13 13:00","2022-12-13 12:00","2022-12-13 13:00","연속"]
[67,"경기","평택","서운안성#1 T/L","서운안성#1T/L 유압조작기 점검","서운안성#1T/L 유압조작기 점검","2022-12-01 09:00","2022-12-01 18:00","2022-12-01 09:00","2022-12-01 18:00","연속"]
[68,"경기","평택","서운삼죽 T/L","154kV 삼죽#5M.Tr 증설공사","154kV #1BUS측 무부하 가압","2022-12-01 18:00","2022-12-02 18:00","2022-12-01 10:00","2022-12-02 10:00","연속"]
[69,"경기","평택","서운삼죽 T/L","154kV 삼죽#5M.Tr 증설공사","154kV #5M.Tr 무부하 가압","2022-12-24 18:00","2022-12-25 18:00","2022-12-24 18:00","2022-12-25 18:00","연속"]
[70,"경기","평택","오산평택#2 T/L","평택고덕 지중화 임시이설공사","철탑 설치 1기(우선이설 63-1호) 철탑 철거 2기 (기설 62, 63호)","2022-12-21 08:00","2022-12-24 18:00","2022-12-21 08:00","2022-12-24 18:00","연속"]
[71,"경기","평택","오산평택#1 T/L","평택고덕 지중화 임시이설공사","철탑 설치 1기(우선이설 63-1호) 철탑 철거 2기 (기설 62, 63호)","2022-12-17 08:00","2022-12-20 18:00","2022-12-17 08:00","2022-12-20 18:00","연속"]
[72,"강원","강릉","북평영동TP#2 T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","#2Bus 시험가압,, 170kV GIS 7CCT 대체, 170kV GIS 디지털변환, #2BUS 설치 ((BUS TIE, BUS PT, 북평-영동TP #1,2T/L","2022-12-06 17:00","2022-12-06 19:00","2022-12-06 15:00","2022-12-06 17:00","연속"]
[73,"강원","강릉","북평영동TP#2 T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","북평-영동TP #2T/L GIS 이설에 따른 인출변경, 전력선 교체","2022-12-08 08:00","2022-12-08 17:00","2022-12-08 08:00","2022-12-08 17:00","연속"]
[74,"강원","강릉","북평영동TP#1 T/L","영동화력S/Y 170kV 장기사용 GIS대체공사","북평-영동TP #1T/L GIS 이설에 따른 인출변경, 전력선 교체","2022-12-09 08:00","2022-12-09 17:00","2022-12-09 08:00","2022-12-09 17:00","연속"]
[75,"강원","원주","남원주원주#1 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 장기미동작 차단기 동작시험","2022-12-12 09:00","2022-12-12 18:00","2022-12-12 09:00","2022-12-12 18:00","연속"]
[76,"강원","원주","남원주원주#2 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 장기미동작 차단기 동작시험","2022-12-13 09:00","2022-12-13 18:00","2022-12-13 09:00","2022-12-13 18:00","연속"]
[77,"강원","원주","원주서원주#2 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 보통점검","2022-12-02 09:00","2022-12-02 18:00","2022-12-02 09:00","2022-12-02 18:00","연속"]
[78,"강원","원주","원주서원주#1 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 보통점검","2022-12-01 09:00","2022-12-01 18:00","2022-12-01 09:00","2022-12-01 18:00","연속"]
[79,"강원","원주","북원주횡성#2 T/L","2022년 원주전력지사 변전협력회사 총액공사","GIS 보통점검","2022-12-05 09:00","2022-12-05 18:00","취소","취소","연속"]
[80,"강원","직할","상남인제#1 T/L","2022년 장기미동작 차단기 조작시험","인제S/S 154kV 상남-인제 #1T/L 차단기 조작시험","2022-12-01 10:00","2022-12-01 12:00","2022-12-01 10:00","2022-12-01 12:00","연속"]
[81,"강원","직할","북춘천춘천HP T/L","22~23년 강원직할 가공송전 협력회사 총액공사","추락방지장치 설치공사","2022-12-01 10:00","2022-12-05 18:00","2022-12-01 10:00","2022-12-05 18:00","연속"]
[82,"강원","직할","가평춘천HP T/L","2022년 장기미동작 차단기 조작시험","춘천HP 154kV 가평-춘천HP T/L 차단기 조작시험","2022-12-02 13:00","2022-12-02 15:00","2022-12-06 13:00","2022-12-06 15:00","연속"]
[83,"강원","직할","철원화천#1 T/L","2022년 장기미동작 차단기 조작시험","철원S/S 154kV 철원-화천#1T/L 차단기 조작시험","2022-12-05 09:00","2022-12-05 13:00","2022-12-05 09:00","2022-12-05 13:00","연속"]
[84,"강원","직할","철원화천#2 T/L","2022년 장기미동작 차단기 조작시험","철원S/S 154kV 철원-화천#2T/L 차단기 조작시험","2022-12-05 13:00","2022-12-05 18:00","2022-12-05 13:00","2022-12-05 18:00","연속"]
[85,"강원","직할","화천S/S CB 6100","2022~2023년 강원본부 직할 변전협력회사 총액공사","- 화천S/S 154kV 모선보호배전반 대체공사","2022-12-26 09:00","2022-12-30 18:00","2022-12-26 09:00","2022-12-30 18:00","연속"]
[86,"강원","태백","태백영월 T/L","154kV 영월에코윈드S/Y 건설공사","1. 154kV 태백-영월T/L 보호배전반 대체 및 대국시험 2. 영월에코윈드 송전선로 가선 작업 3. 154kV 영월에코윈드S/Y 최종가압","2022-12-15 09:00","2022-12-20 18:00","2022-12-15 09:00","2022-12-20 18:00","연속"]
[87,"강원","태백","고한영월 T/L","154kV 영월에코윈드S/Y 건설공사","1. 154kV 고한-영월T/L 보호배전반 대체 및 대국시험 2. 영월에코윈드 송전선로 가선 작업 3. 154kV 영월에코윈드S/Y 최초가압","2022-12-06 09:00","2022-12-13 18:00","2022-12-06 09:00","2022-12-13 18:00","연속"]
[88,"강원","태백","동해동영월 T/L","154kV 영월에코윈드S/Y 건설공사","압축인류클램프 동파로 인한 전력선 일부 교체","2022-12-01 09:00","2022-12-01 18:00","2022-12-01 09:00","2022-12-01 18:00","연속"]
[89,"강원","태백","동영월영월CC T/L","154kV 영월에코윈드S/Y 건설공사","압축인류클램프 동파로 인한 전력선 일부 교체","2022-12-02 09:00","2022-12-02 18:00","2022-12-02 09:00","2022-12-02 18:00","연속"]
[90,"강원","태백","철원S/S 비즌비츠로태양광#1T/L CB","22~23년 강원본부 직할 변전협력회사 총액공사","GIS 하자점검","2022-12-07 13:00","2022-12-07 20:00","2022-12-07 13:00","2022-12-07 20:00","연속"]
[91,"충북","청주","사직북청주#1 T/L","22-23년 청주전력 변전총액공사","154kV GIS 차단기 AUX 점검","2022-12-01 10:00","2022-12-01 18:00","2022-12-01 10:00","2022-12-01 18:00","연속"]
[92,"충북","청주","서청주사직#1 T/L","22-23년 청주전력 변전협력회사 총액공사","서청주S/S 154kV 서청주사직#1T/L 전자변 교체","2022-12-03 09:00","2022-12-03 18:00","2022-12-03 09:00","2022-12-03 18:00","연속"]
[93,"충북","충주","북충주충주 T/L","22~23년 충주전력지사 변전협력회사 총액공사","154kV GIS 보통점검","2022-12-01 09:00","2022-12-01 18:00","2022-12-01 09:00","2022-12-01 18:00","연속"]
[94,"충북","충주","충주충주HP#1 T/L","154kV 충주-충주HP T/L 인출변경공사","1. 공사개요 ○ 철탑 교체 1기 : 신설 설치(No.1) 및 기설 철거(No.1) ○ 전력선 교체 : 2경간(신설 G/T ~ 기설 No.2) - #1T/L 본 선로 구성(전력선 연선 및 긴선)","2022-12-01 07:00","2022-12-07 18:00","취소","취소","연속"]
[95,"대전세종충남","대전","금산무주#1 T/L","[송전] 154kV 가수원-서대전 등 6개T/L 피뢰기 설치공사","[송전] 154kV 금산-무주T/L 추락방지장치 설치공사 및 추부-금산T/L 피뢰기 설치공사 안전이격확보","2022-12-06 08:00","2022-12-12 18:00","2022-12-06 08:00","2022-12-12 18:00","매일"]
[96,"대전세종충남","대전","신옥천남대전#3 T/L","남대전S/S 154kV 노후 GIS 교체공사(3차분)","667,6333 교체시, 무부하 가압선로","2022-12-06 14:00","2022-12-07 14:00","2022-12-06 14:00","2022-12-07 14:00","연속"]
[97,"대전세종충남","대전","신옥천남대전#3 T/L","남대전S/S 154kV 노후 GIS 교체공사(3차분)","667,6333 교체시, 무부하 가압선로","2022-12-13 14:00","2022-12-14 14:00","2022-12-13 14:00","2022-12-14 14:00","연속"]
[98,"대전세종충남","대전","가수원서대전#2 T/L","서대전S/S 154kV 장기사용 GIS 교체공사(3차분)","687 교체","2022-12-07 09:00","2022-12-28 18:00","2022-12-07 09:00","2022-12-28 18:00","연속"]
[99,"대전세종충남","대전","논산은진#2 T/L","은진S/S 154kV 모선구분차단기 설치공사","#2BUS 무부하가압","2022-12-01 14:00","2022-12-02 14:00","2022-12-01 14:00","2022-12-02 14:00","연속"]
[100,"대전세종충남","서산","서산태안화력 T/L","효성제 170kV GIS 베어링 발청관련 제작사 점검","태안화력S/Y 154kV 617 GIS 베어링 점검","2022-12-16 09:00","2022-12-16 18:00","취소","취소","연속"]
[101,"대전세종충남","서산","태안태안화력 T/L","효성제 170kV GIS 베어링 발청관련 제작사 점검","태안화력S/Y 154kV 627 GIS 베어링 점검","2022-12-17 09:00","2022-12-17 18:00","취소","취소","연속"]
[102,"대전세종충남","세종","신풍공주#2 T/L","[송전]154kV 신풍-공주#2T/L 추락방지시설 설치공사","[송전]154kV 신풍-공주#2T/L 추락방지시설 설치공사 - No. 1, 1-1~1-14, 49~74 (41기)","2022-12-01 07:00","2022-12-13 18:00","2022-12-01 07:00","2022-12-13 18:00","매일"]
[103,"대전세종충남","천안","아산인주#2 T/L","154kV 아산인주#2 T/L 보호배전반 교체","154kV 아산인주#2 T/L 보호배전반 교체","2022-12-26 09:00","2022-12-30 18:00","취소","취소","연속"]
[104,"대전세종충남","천안","아산인주#1 T/L","154kV 아산인주#1 T/L 보호배전반 교체","154kV 아산인주#1 T/L 보호배전반 교체","2022-12-19 09:00","2022-12-23 18:00","취소","취소","연속"]
[105,"대전세종충남","천안","아산온양#1 T/L","아산S/S 154kV 아산-온양#1T/L GIS 보통점검","아산S/S 154kV 아산-온양#1T/L GIS 보통점검","2022-12-06 09:00","2022-12-06 18:00","취소","취소","연속"]
[106,"대전세종충남","천안","아산합덕#2 T/L","(11월취소시)아산S/S 아산합덕#2 T/L GIS 초기점검","(11월취소시)아산S/S 아산합덕#2 T/L GIS 초기점검","2022-12-09 09:00","2022-12-09 18:00","2022-12-09 09:00","2022-12-09 18:00","연속"]
[107,"대전세종충남","천안","아산온양#2 T/L","아산S/S 154kV 아산-온양#2T/L GIS 보통점검","아산S/S 154kV 아산-온양#2T/L GIS 보통점검","2022-12-07 09:00","2022-12-07 18:00","취소","취소","연속"]
[108,"대전세종충남","천안","온양풍세#2 T/L","온양S/S 154kV 온양-풍세#2T/L GIS 보통점검","온양S/S 154kV 온양-풍세#2T/L GIS 보통점검","2022-12-15 09:00","2022-12-15 18:00","2022-12-11 09:00","2022-12-11 18:00","연속"]
[109,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 154kV 온양-풍세#1T/L GIS 보통점검","온양S/S 154kV 온양-풍세#1T/L GIS 보통점검","2022-12-14 09:00","2022-12-14 18:00","2022-12-10 09:00","2022-12-10 18:00","연속"]
[110,"대전세종충남","천안","장재불당#2 T/L","154kV 장재불당#2 T/L 보호배전반 교체","154kV 장재불당#2 T/L 보호배전반 교체","2022-12-19 09:00","2022-12-23 18:00","취소","취소","연속"]
[111,"대전세종충남","천안","장재불당#1 T/L","154kV 장재불당#1 T/L 보호배전반 교체","154kV 장재불당#1 T/L 보호배전반 교체","2022-12-12 09:00","2022-12-16 18:00","취소","취소","연속"]
[112,"대전세종충남","천안","신탕정탕정#1 T/L","탕정S/S 신탕정탕정#1,2T/L CB 개폐타임 측정","탕정S/S 신탕정탕정#1,2T/L CB 개폐타임 측정","2022-12-02 09:00","2022-12-02 14:00","취소","취소","연속"]
[113,"대전세종충남","천안","서천안탕정#1 T/L","탕정S/S 서천안탕정#1,2T/L LA점검","탕정S/S 서천안탕정#1,2T/L LA점검","2022-12-08 09:00","2022-12-08 14:00","2022-12-08 09:00","2022-12-08 14:00","연속"]
[114,"대전세종충남","천안","서천안탕정#2 T/L","탕정S/S 서천안탕정#1,2T/L LA점검","탕정S/S 서천안탕정#1,2T/L LA점검","2022-12-08 14:00","2022-12-08 18:00","2022-12-08 14:00","2022-12-08 18:00","연속"]
[115,"대전세종충남","천안","신탕정탕정#2 T/L","탕정S/S 신탕정탕정#1,2T/L CB 개폐타임 측정","탕정S/S 신탕정탕정#1,2T/L CB 개폐타임 측정","2022-12-02 14:00","2022-12-02 18:00","취소","취소","연속"]
[116,"대전세종충남","청양","보령C/C #8 M.Tr 1차 CB","154kV 차단기 부동작 예방 조작시험(6333)","154kV 차단기 부동작 예방 조작시험(6333)","2022-12-02 15:00","2022-12-02 18:00","2022-12-02 15:00","2022-12-02 18:00","연속"]
[117,"대전세종충남","청양","보령C/C #7 M.Tr 1차 CB","154kV 차단기 부동작 예방 조작시험(6233)","154kV 차단기 부동작 예방 조작시험(6233)","2022-12-02 12:00","2022-12-02 15:00","2022-12-02 12:00","2022-12-02 15:00","연속"]
[118,"대전세종충남","청양","보령C/C #6 M.Tr 1차 CB","154kV 차단기 부동작 예방 조작시험(6133)","154kV 차단기 부동작 예방 조작시험(6133)","2022-12-02 10:00","2022-12-02 12:00","2022-12-02 10:00","2022-12-02 12:00","연속"]
[119,"대전세종충남","청양","청양신풍#1 T/L","[송전]154kV 청양-신풍#1T/L 추락방지시설 설치공사","[송전]154kV 청양-신풍#1T/L 추락방지시설 설치공사 - No. 49~63 (15기)","2022-12-01 07:00","2022-12-07 18:00","2022-12-01 07:00","2022-12-07 18:00","매일"]
[120,"전북","군산","군산이리#2 T/L","군산P/O 노후배전반 대체공사","군산P/O 노후배전반 대체공사","2022-12-13 09:00","2022-12-16 18:00","취소","취소","연속"]
[121,"전북","군산","군산영등#1 T/L","군산P/O 154kV이상 차단기 조작시험","군산S/S 667 차단기 개폐타임 측정","2022-12-19 09:00","2022-12-19 11:00","2022-12-19 09:00","2022-12-19 11:00","연속"]
[122,"전북","군산","군산영등#2 T/L","군산P/O 154kV 이상 차단기 조작시험","군산S/S 677 차단기 개폐타임 측정","2022-12-19 15:00","2022-12-19 18:00","2022-12-19 15:00","2022-12-19 18:00","연속"]
[123,"전북","김제","정주부안#1 T/L","154kV 동부안분기T/L 건설공사","○ 위 치 : 154kV 정주-부안T/L No.58~60 ○ 규 모 : PIAC 410×S×2C×.0.55km, 철탑 4기(가철탑 포함) ○ 작업내용 : 임시선로 구성(No.58-가철탑-60) ○ 비상시 즉시가압여부 : 편측 가능(동시휴전 시)","2022-12-05 07:00","2022-12-11 18:00","취소","취소","연속"]
[124,"전북","김제","정주부안#2 T/L","154kV 동부안분기T/L 건설공사","○ 위 치 : 154kV 정주-부안T/L No.58~60 ○ 규 모 : PIAC 410×S×2C×.0.55km, 철탑 4기(가철탑 포함) ○ 작업내용 : 임시선로 구성(No.58-가철탑-60) ○ 비상시 즉시가압여부 : 편측 가능(동시휴전 시)","2022-12-05 07:00","2022-12-11 18:00","취소","취소","연속"]
[125,"전북","김제","정주고창#1 T/L","154kV 소성분기T/L 건설공사","○ 위 치 : 154kV 정주-고창T/L No.28~29 ○ 작업내용 : #1T/L 공중이동, 긴선(By-pass 구성) 및 가철탑 철거","2022-12-05 08:00","2022-12-10 18:00","취소","취소","연속"]
[126,"전북","김제","김제S/S #1 EM.Tr CB","김제 FR-ESS 정기점검","김제 FR-ESS 정기점검(PCS 및 배터리 정기점검)","2022-12-12 10:00","2022-12-23 18:00","2022-12-12 10:00","2022-12-23 18:00","연속"]
[127,"전북","김제","백산김제#2 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-12-12 09:00","2022-12-13 18:00","2022-12-12 09:00","2022-12-13 18:00","연속"]
[128,"전북","김제","신김제전주#1 T/L","신김제S/S 154kV CVT 보통점검","154kV 신김제-전주#1T/L PT A상 보통점검","2022-12-27 09:00","2022-12-27 12:00","2022-12-27 09:00","2022-12-27 12:00","연속"]
[129,"전북","김제","신김제남전주#1 T/L","신김제S/S 170kV 차단기 보통점검 및 메커니즘 보수","신김제S/S 170kV 차단기 보통점검 및 메커니즘 보수","2022-12-29 10:00","2022-12-29 18:00","2022-12-29 10:00","2022-12-29 18:00","연속"]
[130,"전북","김제","신김제S/S #1 EM.Tr CB","신김제 FR-ESS 정밀점검","신김제 FR-ESS 정밀점검","2022-12-12 09:00","2022-12-16 18:00","2022-12-12 09:00","2022-12-16 18:00","연속"]
[131,"전북","김제","신김제전주#2 T/L","신김제S/S 170kV 차단기 및 CVT 보통점검","154kV 신김제-전주#2T/L 차단기 보통점검 및 PT A상 보통점검","2022-12-23 09:00","2022-12-23 18:00","2022-12-23 09:00","2022-12-23 18:00","연속"]
[132,"전북","김제","정공정주#1 T/L","정공S/S 154kV 정공-정주#1T/L CVT 교체","정공S/S 154kV 정공-정주#1T/L CVT 교체","2022-12-22 09:00","2022-12-22 18:00","2022-12-22 09:00","2022-12-22 18:00","연속"]
[133,"전북","김제","신김제정공#1 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-12-14 09:00","2022-12-16 18:00","취소","취소","연속"]
[134,"전북","김제","신김제정공#2 T/L","2022년 김제P/O 170kV GIS 정밀점검","2022년 김제P/O 170kV GIS 정밀점검","2022-12-19 09:00","2022-12-21 18:00","취소","취소","연속"]
[135,"전북","김제","정공칠보HP T/L","정공S/S 154kV 정공-칠보수력T/L CVT 교체","정공S/S 154kV 정공-칠보수력T/L CVT 교체","2022-12-28 09:00","2022-12-28 18:00","2022-12-28 09:00","2022-12-28 18:00","연속"]
[136,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","가. 철탑교체 : 설치 9기, 철거 9기, 가철탑 설치철거 6기 나. 전력선 교체 ○ 신김제-동전주T/L : 1.711C-km[ACSR 410㎟×2B] (33~39호) ○ 남전주-임실T/L : 1.235C-km[ACSR 410㎟×S] (23~28호) 다. 금구류 교체 및 기타 부대공사","2022-12-19 08:00","2022-12-25 17:00","취소","취소","연속"]
[137,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","가. 철탑교체 : 설치 9기, 철거 9기, 가철탑 설치·철거 6기 나. 전력선 교체 ○ 신김제-동전주T/L : 1.711C-km[ACSR 410㎟×2B] (33~39호) ○ 남전주-임실T/L : 1.235C-km[ACSR 410㎟×S] (23~28호) 다. 금구류 교체 및 기타 부대공사","2022-12-12 08:00","2022-12-18 17:00","취소","취소","연속"]
[138,"전북","직할","북전주진안 T/L","북전주S/S 북전주-진안T/L 효성제 메카니즘 점검 시행","북전주S/S 효성제 메카니즘 발청 교체","2022-12-15 15:00","2022-12-15 20:00","2022-12-15 15:00","2022-12-15 20:00","매일"]
[139,"전북","직할","북전주진안 T/L","진안, 북전주S/S 북전주-진안T/L 보통점검 시행(즉시가압가능)","진안, 북전주S/S 보통점검 시행","2022-12-14 15:00","2022-12-14 20:00","2022-12-14 15:00","2022-12-14 20:00","매일"]
[140,"전북","직할","무주진안 T/L","진안S/S 무주-진안T/L 보통점검(즉시가압 가능)","진안S/S 무주-진안T/L 보통점검(즉시가압 가능)","2022-12-13 15:00","2022-12-13 20:00","2022-12-13 15:00","2022-12-13 20:00","연속"]
[141,"광주전남","순천","여수TP화치#1 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직, 수평 추락방지장치 설치","2022-12-01 07:00","2022-12-01 12:00","취소","취소","연속"]
[142,"광주전남","순천","호남TP여수TP#2 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직, 수평 추락방지장치 설치","2022-12-01 07:00","2022-12-01 12:00","취소","취소","연속"]
[143,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2022-12-01 08:00","2022-12-06 15:00","취소","취소","연속"]
[144,"광주전남","광주","담양일곡#2 T/L","2022년 광주전력 철탑추락방지장치 설치공사","철탑추락방지장치 설치","2022-12-01 08:00","2022-12-06 18:00","2022-12-01 08:00","2022-12-06 18:00","매일"]
[145,"광주전남","목포","장성영광#1 T/L","2022년도 목포전력지사 변전협력회사 총액공사","2022년도 목포전력지사 변전협력회사 총액공사","2022-12-01 09:00","2022-12-01 13:00","2022-12-01 09:00","2022-12-01 13:00","연속"]
[146,"광주전남","직할","농성화정#2 T/L","2022~23년 직할 변전협력회사 총액공사","농성-화정#2T/L 170kV GIS 장기미동작 차단기 점검","2022-12-01 10:00","2022-12-01 12:00","2022-12-01 10:00","2022-12-01 12:00","연속"]
[147,"광주전남","목포","장성영광#2 T/L","2022년도 목포전력지사 변전협력회사 총액공사","2022년도 목포전력지사 변전협력회사 총액공사","2022-12-01 13:00","2022-12-01 18:00","2022-12-01 13:00","2022-12-01 18:00","연속"]
[148,"광주전남","순천","호남TP여수TP#1 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직, 수평 추락방지장치 설치","2022-12-02 07:00","2022-12-02 12:00","취소","취소","연속"]
[149,"광주전남","순천","여수TP화치#2 T/L","광양CC-여수TP T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직, 수평 추락방지장치 설치","2022-12-02 07:00","2022-12-02 12:00","취소","취소","연속"]
[150,"광주전남","목포","고창영광 T/L","2022년도 목포전력지사 변전협력회사 총액공사","2022년도 목포전력지사 변전협력회사 총액공사","2022-12-02 09:00","2022-12-02 18:00","2022-12-02 09:00","2022-12-02 18:00","연속"]
[151,"광주전남","광주","담양김제 T/L","2022년 광주전력 철탑추락방지장치 설치공사","담양-김제(정공-담양)T/L 철탑추락방지장치 설치","2022-12-07 07:00","2022-12-09 18:00","취소","취소","매일"]
[152,"광주전남","목포","운남S/S 신흥풍력T/L CB","2022년도 목포전력지사 변전협력회사 총액공사","2022년도 목포전력지사 변전협력회사 총액공사","2022-12-05 09:00","2022-12-05 18:00","2022-12-05 09:00","2022-12-05 18:00","연속"]
[153,"광주전남","순천","태금하동화력 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","태금S/S 태금-하동TP T/L GIS 초기점검","2022-12-05 10:00","2022-12-05 18:00","2022-12-05 10:00","2022-12-05 18:00","연속"]
[154,"광주전남","순천","율촌여수산단#2 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-12-08 09:00","2022-12-09 18:00","취소","취소","연속"]
[155,"광주전남","순천","율촌여수산단#1 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-12-12 09:00","2022-12-13 18:00","취소","취소","연속"]
[156,"광주전남","순천","호남TP여수TP#2 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-12-15 09:00","2022-12-16 18:00","취소","취소","연속"]
[157,"광주전남","순천","여수TP여천#2 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-12-19 09:00","2022-12-20 18:00","취소","취소","연속"]
[158,"광주전남","순천","여수TP여천#1 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-12-22 09:00","2022-12-23 18:00","취소","취소","연속"]
[159,"광주전남","순천","호남TP여수TP#1 T/L","'22년 순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검공사","2022-12-26 09:00","2022-12-27 18:00","취소","취소","연속"]
[160,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2022-12-05 15:00","2022-12-06 15:00","취소","취소","연속"]
[161,"광주전남","목포","영광홍농 T/L","2022년도 목포전력지사 변전협력회사 총액공사","2022년도 목포전력지사 변전협력회사 총액공사","2022-12-06 09:00","2022-12-06 18:00","2022-12-19 09:00","2022-12-19 18:00","연속"]
[162,"광주전남","광주","담양S/S #1 BUS","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2022-12-06 15:00","2022-12-07 15:00","취소","취소","연속"]
[163,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2022-12-06 18:00","2022-12-07 18:00","취소","취소","연속"]
[164,"광주전남","강진","대불삼호#2 T/L","대불변전소 KC T/L LINE PT 설치공사","대불변전소 KC T/L LINE PT 설치공사 관련 안전이격 확보","2022-12-07 09:00","2022-12-07 18:00","취소","취소","연속"]
[165,"광주전남","강진","대불삼호#1 T/L","대불변전소 KC T/L LINE PT 설치공사","대불변전소 KC T/L LINE PT 설치공사 관련 안전이격 확보","2022-12-07 09:00","2022-12-07 18:00","취소","취소","연속"]
[166,"광주전남","광주","정공담양 T/L","2022년 광주전력 철탑추락방지장치 설치공사","정공-담양TL 철탑추락방지장치 설치공사","2022-12-13 07:00","2022-12-15 18:00","2022-12-13 07:00","2022-12-15 18:00","매일"]
[167,"광주전남","순천","순천율촌#1 T/L","345kV 신강진-광양 등 29개T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직,수평 추락방지장치 설치","2022-12-09 07:00","2022-12-12 18:00","취소","취소","매일"]
[168,"광주전남","광주","신광주일곡#1 T/L","2022년 광주전력 철탑추락방지장치 설치공사","신광주-일곡T/L 추락방지장치 설치공사","2022-12-12 07:00","2022-12-13 18:00","취소","취소","매일"]
[169,"광주전남","순천","여수T/P SEC CB 60610","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-12-12 09:00","2022-12-16 18:00","취소","취소","연속"]
[170,"광주전남","순천","여수T/P SEC CB 65660","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-12-12 09:00","2022-12-16 18:00","취소","취소","연속"]
[171,"광주전남","순천","여수T/P CB 6100","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #60-65 BUS-Pro 보호반 대체","2022-12-12 09:00","2022-12-16 18:00","취소","취소","연속"]
[172,"광주전남","순천","순천율촌#2 T/L","345kV 신강진-광양 등 29개T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직,수평 추락방지장치 설치","2022-12-13 07:00","2022-12-13 18:00","취소","취소","연속"]
[173,"광주전남","순천","율촌여수산단#1 T/L","345kV 신강진-광양 등 29개T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직,수평 추락방지장치 설치","2022-12-14 07:00","2022-12-16 18:00","취소","취소","매일"]
[174,"광주전남","광주","신광주일곡#2 T/L","2022년 광주전력 철탑추락방지장치 설치공사","신광주-일곡T/L 철탑추락방지장치 설치공사","2022-12-14 09:00","2022-12-15 18:00","취소","취소","매일"]
[175,"광주전남","순천","율촌여수산단#2 T/L","345kV 신강진-광양 등 29개T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직,수평 추락방지장치 설치","2022-12-19 07:00","2022-12-20 18:00","취소","취소","매일"]
[176,"광주전남","순천","여수T/P CB 6200","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #61-66 BUS-Pro 보호반 대체","2022-12-19 09:00","2022-12-23 18:00","취소","취소","연속"]
[177,"광주전남","순천","여수T/P SEC CB 65660","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #61-66 BUS-Pro 보호반 대체","2022-12-19 09:00","2022-12-23 18:00","취소","취소","연속"]
[178,"광주전남","순천","여수T/P SEC CB 60610","'22-23년 순천전력지사 변전협력회사 총액공사","154kV #61-66 BUS-Pro 보호반 대체","2022-12-19 09:00","2022-12-23 18:00","취소","취소","연속"]
[179,"광주전남","순천","서순천주암HP T/L","345kV 신강진-광양 등 29개T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직,수평 추락방지장치 설치","2022-12-21 07:00","2022-12-21 18:00","취소","취소","연속"]
[180,"광주전남","순천","승주주암HP T/L","345kV 신강진-광양 등 29개T/L 추락방지시설 설치공사","목적 : 철탑 승탑자의 추락방지를 위한 추락방지 시설 설치 내용 : 수직,수평 추락방지장치 설치","2022-12-22 07:00","2022-12-22 18:00","취소","취소","연속"]
[181,"대구","경산","진량노변 T/L","'22년 경산P/O 154kV GIS 정밀점검 및 보통점검 공사","TEST 선로(주작업 : 진량S/S #1Sh.C 정밀점검)","2022-12-02 16:00","2022-12-02 18:00","2022-12-02 16:00","2022-12-02 18:00","연속"]
[182,"대구","직할","남대구동인#1 T/L","2021-22년 지중송전설비 위탁정비공사","남대구-동인#1T/L JB#2 A,B,C상 절연유 채유 -절연유 분석 결과에 따른 추적분석 필요","2022-12-06 09:00","2022-12-06 18:00","취소","취소","연속"]
[183,"대구","직할","범물남대구#1 T/L","2021-22년 지중송전설비 위탁정비공사","범물-남대구#1T/L EBA 절연유 채유(A상) -절연유 분석 결과에 따른 추적분석 필요","2022-12-07 09:00","2022-12-07 14:00","취소","취소","연속"]
[184,"경북","구미","해평S/S LGBCM#1T/L CB","2022년 해평S/S 154kV 개폐장치 신규수용 공사","- LG BCMT/L 증설관련 케이블 접속공사","2022-12-05 09:00","2022-12-09 18:00","취소","취소","연속"]
[185,"경북","영주","영주봉화#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","CB 조작시험 LA 대체","2022-12-01 09:00","2022-12-02 18:00","취소","취소","연속"]
[186,"경북","영주","봉화S/S 춘양전철#2T/L CB","2022-23년 영주전력지사 변전협력회사 총액공사","춘양전철#2T/L 보호반 대체","2022-12-05 09:00","2022-12-06 18:00","취소","취소","연속"]
[187,"경북","직할","안동풍산 T/L","154kV 안동-풍산 등 2개T/L 지장송전선로 이설공사","[가 공] (1) 지지물 : 5기 설치 (C/H 1기, 임시철탑4기) 10기 철거 (No.59~64 6기, 임시철탑4기) 1기 보강 (No.58) (2) 전력선 : HSTACIR 240㎟×S, ACSR 410㎟×S×2C, 0.971km","2022-12-19 08:00","2022-12-23 18:00","2022-12-19 08:00","2022-12-23 18:00","연속"]
[188,"부산울산","동부산","신양산구서#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","154kV 구서-명장#1T/L 휴전작업 관련 안전이격확보","2022-12-12 07:00","2022-12-13 18:00","2022-12-12 07:00","2022-12-13 18:00","연속"]
[189,"부산울산","동부산","신양산구서#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","154kV 구서-명장#2T/L 휴전작업 관련 안전이격확보","2022-12-14 07:00","2022-12-15 18:00","2022-12-14 07:00","2022-12-15 18:00","연속"]
[190,"부산울산","동부산","명례고리NP T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평추락방지장치, 피뢰기 설치","2022-12-01 07:00","2022-12-02 18:00","2022-12-01 07:00","2022-12-02 18:00","연속"]
[191,"부산울산","동부산","장안고리NP T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평추락방지장치, 피뢰기 설치","2022-12-06 07:00","2022-12-06 18:00","2022-12-06 07:00","2022-12-06 18:00","연속"]
[192,"부산울산","동부산","명례장안 T/L","신울산-명례-장안 OPGW 증설공사","신울산-명례-장안간 OPGW교체 : 19km","2022-12-03 09:00","2022-12-06 18:00","2022-12-05 07:00","2022-12-05 18:00","연속"]
[193,"부산울산","북부산","미남S/S CB 6100","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2022-12-19 13:00","2022-12-19 18:00","취소","취소","연속"]
[194,"부산울산","북부산","미남S/S SEC CB 60610","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2022-12-19 13:00","2022-12-19 18:00","취소","취소","연속"]
[195,"부산울산","북부산","미남S/S SEC CB 65660","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2022-12-19 13:00","2022-12-19 18:00","취소","취소","연속"]
[196,"부산울산","북부산","미남S/S #60 BUS","영인제 모선보호반 성능개선","미남S/S 154kV #60-65 모선보호반(영인제) 성능개선 (6100, 60-61, 65-66, 60BUS 휴전)","2022-12-19 13:00","2022-12-19 18:00","취소","취소","연속"]
[197,"부산울산","북부산","언양산막#1 T/L","22-23 북부산전력지사 변전 총액공사","산막S/S 154kV 언양-산막#1T/L 차단기 조작시험","2022-12-12 09:00","2022-12-12 18:00","2022-12-12 09:00","2022-12-12 18:00","연속"]
[198,"부산울산","북부산","양산산막#2 T/L","22-23 북부산전력지사 변전 총액공사","산막S/S 154kV 양산-산막#2T/L 차단기 조작시험","2022-12-01 09:00","2022-12-01 18:00","2022-12-01 09:00","2022-12-01 18:00","연속"]
[199,"부산울산","북부산","언양산막#2 T/L","22-23 북부산전력지사 변전 총액공사","산막S/S 154kV 언양-산막#2T/L 차단기 조작시험","2022-12-13 09:00","2022-12-13 18:00","2022-12-13 09:00","2022-12-13 18:00","연속"]
[200,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 양산분기T/L 수평 추락방지장치 설치(2~16호, 12기)","2022-12-14 09:00","2022-12-16 18:00","2022-12-14 09:00","2022-12-16 18:00","연속"]
[201,"부산울산","북부산","양산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 양산분기T/L 수평 추락방지장치 설치(2~16호, 12기)","2022-12-05 09:00","2022-12-08 18:00","2022-12-05 09:00","2022-12-08 18:00","연속"]
[202,"부산울산","울산","남울산신온산#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2022-12-15 07:00","2022-12-20 18:00","취소","취소","연속"]
[203,"부산울산","울산","두왕울산#1 T/L","2022년 울산전력지사 가공송전 순시점검 위탁공사","□ 154kV 두왕-울산#1T/L 가공송전 철탑 초기점검 -작업구간: 두왕S/S ~ No.2","2022-12-12 09:00","2022-12-14 18:00","2022-12-12 09:00","2022-12-14 18:00","연속"]
[204,"부산울산","울산","반천언양#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 설치","2022-12-07 07:00","2022-12-08 18:00","2022-12-07 07:00","2022-12-08 18:00","연속"]
[205,"부산울산","울산","반천언양#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","송전철탑 추락방지장치(수평) 설치","2022-12-09 07:00","2022-12-10 18:00","2022-12-09 07:00","2022-12-10 18:00","연속"]
[206,"부산울산","울산","산하방어진#1 T/L","154kV 추락방지장치 및 피뢰기 설치공사","ㅇ154kV효문-방어진(산하-방어진) 수직,수평 추락방지,피뢰기 설치 - 5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20[16기]","2022-12-12 08:00","2022-12-16 18:00","2022-12-12 08:00","2022-12-16 18:00","연속"]
[207,"부산울산","울산","성암울산TP#1 T/L","154kV 추락방지장치 설치공사","ㅇ 154kV 성암-울산TP #1 수직,수평 추락방지장치 설치 - 1 1.1 2 3 9 (5기)","2022-12-01 08:00","2022-12-02 18:00","2022-12-01 08:00","2022-12-02 18:00","연속"]
[208,"부산울산","울산","신울산언양#2 T/L","22~23년 변전협력회사 총액공사","GIS 차단기 동작시험","2022-12-08 09:00","2022-12-08 18:00","2022-12-08 09:00","2022-12-08 18:00","연속"]
[209,"부산울산","울산","신울산S/S CB 6100","22~23년 변전협력회사 총액공사","GIS 차단기 동작시험","2022-12-02 09:00","2022-12-02 14:00","2022-12-02 09:00","2022-12-02 14:00","연속"]
[210,"부산울산","울산","남울산용연#1 T/L","154kV 추락방지장치 설치공사","ㅇ154kV남울산-용연 #1 수직,수평 추락방지장치 설치 - 1, 2, 3[3기]","2022-12-05 08:00","2022-12-05 18:00","2022-12-05 08:00","2022-12-05 18:00","연속"]
[211,"부산울산","울산","두왕울산#2 T/L","154kV 울산-매암T/L SW증설공사","울산매암 SW증설관련 본선로 시험가압을 위한 울산측 시험가압 보조선로","2022-12-18 14:00","2022-12-19 14:00","2022-12-18 14:00","2022-12-19 14:00","연속"]
[212,"부산울산","울산","울산S/S #1 EM.Tr CB","22~23년 변전협력회사 총액공사","EM.Tr 보통점검","2022-12-12 09:00","2022-12-13 18:00","2022-12-12 09:00","2022-12-13 18:00","연속"]
[213,"부산울산","울산","온산처용#1 T/L","22년 하반기 154kV 개폐장치 정밀점검공사","대성산업가스T/L GIS 시험가압(1Hr)","2022-12-14 17:00","2022-12-14 18:00","2022-12-14 17:00","2022-12-14 18:00","연속"]
[214,"부산울산","울산","온산처용#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2022-12-21 07:00","2022-12-30 18:00","2022-12-21 07:00","2022-12-30 18:00","연속"]
[215,"부산울산","직할","정보대연 T/L","22-23년 직할 변전협력회사 총액공사","대연S/S 정보-대연T/L GIS 조작시험","2022-12-05 09:30","2022-12-05 18:00","2022-12-04 09:30","2022-12-04 18:00","연속"]
[216,"경남","직할","창공월림#1 T/L","154kV 창공-월림T/L 4-5호 인근 공사현장 안전확보","154kV 창공-월림T/L 4-5호 송전선로 직하 공장신축 공사현장 안전확보(민원)","2022-12-01 09:00","2022-12-31 18:00","2022-12-01 09:00","2022-12-31 18:00","연속"]
[217,"경남","직할","창공월림#2 T/L","154kV 창공-월림T/L 4-5호 인근 공사현장 안전확보","154kV 창공-월림T/L 4-5호 송전선로 직하 공장신축 공사현장 안전확보(민원)","2022-12-01 09:00","2022-12-31 18:00","2022-12-01 09:00","2022-12-31 18:00","연속"]
[218,"경남","통영","신마산진동 T/L","154kV 서마산분기(증)T/L 건설사업","154kV 서마산분기(증)T/L 건설사업","2022-12-13 09:00","2022-12-27 18:00","취소","취소","연속"]
[219,"경남","함안","신월동읍#1 T/L","154kV 신월-동읍#1T/L 추락방지장치 설치공사","154kV 신월-동읍#1T/L 34호 추락방지장치 설치공사[휴전작업]","2022-12-08 07:00","2022-12-08 16:00","2022-12-08 07:00","2022-12-08 16:00","연속"]
[220,"경남","함안","신월동읍#2 T/L","154kV 신월-동읍#2T/L 추락방지장치 설치공사","154kV 신월-동읍#2T/L 34호 추락방지장치 설치공사[휴전작업]","2022-12-08 16:00","2022-12-08 18:00","2022-12-08 16:00","2022-12-08 18:00","연속"]
[221,"경남","함안","서마산진동 T/L","154kV 서마산분기(증)T/L 건설사업","154kV 서마산분기(증)T/L 건설사업","2022-12-24 09:00","2022-12-31 18:00","취소","취소","연속"]
[222,"경남","함안","신마산서마산 T/L","154kV 서마산분기(증)T/L 건설사업","154kV 서마산분기(증)T/L 건설사업","2022-12-13 09:00","2022-12-31 18:00","취소","취소","연속"]
[223,"경남","함안","진영수산#2 T/L","154kV 진영-수산#2T/L 추락방지장치 설치공사","154kV 진영-수산#2T/L 추락방지장치 설치공사[휴전작업] - 대상 : 28, 30~60호(32기)","2022-12-05 07:00","2022-12-07 18:00","2022-12-05 07:00","2022-12-07 18:00","매일"]
[224,"경남","함안","진례진영#1 T/L","154kV 동읍-진영T/L 수직 추락방지장치 설치 관련 안전거리 확보","154kV 동읍-진영T/L 40호 수직(C각) 추락방지장치 설치 관련 안전거리확보[휴전작업] - 대상 : 154kV 진례-진영#1T/L 7호 - 로터리 암(C각)으로 휴전필요","2022-12-02 15:00","2022-12-02 18:00","2022-12-02 15:00","2022-12-02 18:00","연속"]
[225,"부산울산",null,"신고리N/P #65 BUS (CB 6172, 6272)","신고리1호기 7차 계획예방정비 *조작 차단기 : CB 6172, 6272","○ SWYD 6172, 6272 차단기 일반점검 ○ 154kV GIS #2BUS 방압변 교체","2022-12-12 09:00","2022-12-16 18:00","2022-12-12 09:00","2022-12-16 18:00","연속"]
[226,"남서울","동서울","동서울강동#1 T/L","154kV 동서울-강동 등 3개T/L 지중화공사","154kV 동서울-강동T/L 일부구간 지중화공사","2022-12-21 09:00","2022-12-27 18:00","2022-12-21 09:00","2022-12-27 18:00","연속"]
[227,"경기",null,"덕성남사#1 T/L","○ 인디케이터 기어 교체공사","○ 인디케이터 기어 교체공사","2022-12-02 09:00","2022-12-02 18:00","2022-12-02 09:00","2022-12-02 18:00","연속"]