{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":13,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":12,"n_cols":11,"rows_kept":12,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2023년도 4월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #2 M.Tr","신가평S/S 765kV M.Tr 이설공사","신가평S/S #2M.Tr 고장복구 - #4M.Tr B-R → #2M.Tr C-R 이설","2023-04-20 09:00","2023-05-03 18:00","2023-04-20 09:00","2023-05-03 18:00","연속"]
[2,"충북","직할","신서산신중부#2 T/L","신중부S/S 765kV GIS 유압매커니즘 부품교체","유압매커니즘 불량(압력0에서 유압 미상승) 해소를 위한 부품교체","2023-04-08 09:00","2023-04-09 18:00","취소","취소","연속"]
[3,"부산울산","동부산","신고리N/P #3 Tie-Tr","신고리 5,6호기 접속설비공사","- #3M.Tr 85BAY(8571,8500,8572) 설비진단처 준공시험 - 신고리 5호기(새울 3호기) 제어, 감시 인터페이스 판넬 연결, 시험","2023-04-17 09:00","2023-05-03 18:00","2023-04-21 09:00","2023-05-10 18:00","연속"]
[4,"경남","함안","북경남S/S CB 8700","북경남S/S 765kV GIS 보통점검공사 (8700)","북경남S/S 765kV GIS 보통점검공사 (8700)","2023-04-28 09:00","2023-04-29 18:00","2023-04-17 09:00","2023-04-18 18:00","연속"]
[5,"경남","함안","북경남S/S CB 8500","북경남S/S 765kV GIS 보통점검공사 (8500)","북경남S/S 765kV GIS 보통점검공사 (8500)","2023-04-24 09:00","2023-04-25 18:00","2023-04-19 09:00","2023-04-20 18:00","연속"]
[6,"경남","함안","북경남S/S CB 8571","북경남S/S 765kV GIS 보통점검공사 (8571)","북경남S/S 765kV GIS 보통점검공사 (8571)","2023-04-20 09:00","2023-04-21 18:00","2023-04-24 09:00","2023-04-25 18:00","연속"]
[7,"경남","함안","북경남S/S CB 8572","북경남S/S 765kV GIS 보통점검공사 (8572)","북경남S/S 765kV GIS 보통점검공사 (8572)","2023-04-26 09:00","2023-04-27 18:00","2023-04-26 09:00","2023-04-27 18:00","연속"]
[8,"부산울산",null,"새울N/P #1호기 주변압기 (CB 8200, 8272)","신고리3호기 4차 계획예방정비 *조작 차단기 : CB 8200, 8272","○ 주변압기 및 PCB 점검 후 주전력계통 재가압","2023-04-16 09:00","2023-06-12 18:00","2023-04-16 09:00","2023-06-12 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":257,"n_cols":11,"rows_kept":257,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2023년도 4월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","중부","중부S/S #4 M.Tr","23년 변전협력회사 총액공사","주변압기 보통점검","2023-04-12 10:00","2023-04-13 18:00","2023-04-12 10:00","2023-04-13 18:00","연속"]
[2,"서울","중부","양주중부#1 T/L","2023~2024년 중부전력지사 지중송전설비 위탁정비공사","지중송전선로 피뢰기점검","2023-04-19 09:00","2023-04-20 18:00","취소","취소","연속"]
[3,"남서울","강남","신양재S/S #2 M.Tr","2023년 강남전력지사 362kV GIS 정밀점검공사","- 대상설비 : 7200, 7272 GIS - 무부하가압 : 신성남-신양재#2T/L(병행휴전)","2023-04-10 09:00","2023-04-21 18:00","2023-04-10 09:00","2023-04-21 18:00","연속"]
[4,"남서울","강남","신양재S/S CB 7271","2023년 강남전력지사 362kV GIS 정밀점검공사","- 대상설비 : 7271 GIS - 무부하가압 : 신성남-신양재#2T/L(병행휴전)","2023-04-04 09:00","2023-04-07 18:00","2023-04-04 09:00","2023-04-07 18:00","연속"]
[5,"남서울","강남","신성남신양재#1 T/L","2023년 강남전력지사 362kV GIS 정밀점검공사","- 대상설비 : 7171 GIS - 무부하가압용 - (병행) 신성남S/S GIS 정밀점검","2023-04-28 14:00","2023-04-28 18:00","2023-04-24 09:00","2023-05-12 18:00","연속"]
[6,"남서울","강남","신양재S/S CB 7171","2023년 강남전력지사 362kV GIS 정밀점검공사","- 대상설비 : 7171 GIS","2023-04-24 09:00","2023-04-28 18:00","2023-04-24 09:00","2023-04-28 18:00","연속"]
[7,"남서울","동서울","신용인동서울#1 T/L","22~23년도 동서울전력지사 가공송전 협력회사 총액공사","추락방지시설 설치공사, 피뢰기 설치공사","2023-04-03 07:00","2023-04-07 17:00","2023-04-03 07:00","2023-04-07 17:00","연속"]
[8,"남서울","동서울","동서울S/S #3 M.Tr","동서울S/S 154kV 옥외철구 GIS화 공사","○ 청평양수SPS 회로변경(#2M.Tr->#3M.Tr) ○ 기타 부대작업 1식","2023-04-18 09:00","2023-04-21 18:00","2023-04-24 09:00","2023-04-28 18:00","연속"]
[9,"남서울","동서울","신용인동서울#2 T/L","22~23년도 동서울전력지사 가공송전 협력회사 총액공사","추락방지시설 설치공사","2023-04-10 07:00","2023-04-12 17:00","2023-04-10 07:00","2023-04-12 17:00","연속"]
[10,"남서울","동서울","곤지암동서울#1 T/L","22~23년도 동서울전력지사 가공송전 협력회사 총액공사","추락방지시설 설치공사","2023-04-27 07:00","2023-04-29 17:00","2023-04-27 07:00","2023-04-28 17:00","연속"]
[11,"남서울","동서울","곤지암동서울#2 T/L","22~23년도 동서울전력지사 가공송전 협력회사 총액공사","추락방지시설 설치공사","2023-04-23 07:00","2023-04-26 18:00","2023-04-24 07:00","2023-04-26 18:00","연속"]
[12,"남서울","동서울","신성남동서울#1 T/L","2023년 동서울전력지사 345kV GIS 정밀점검","2023년 동서울전력지사 345kV GIS 정밀점검(7500,7571)","2023-04-16 09:00","2023-04-21 18:00","2023-04-16 09:00","2023-04-21 18:00","연속"]
[13,"남서울","영등포","서서울신광명#1 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2023-04-29 09:00","2023-04-29 14:00","2023-04-29 09:00","2023-04-29 14:00","연속"]
[14,"남서울","영등포","신광명S/S #70 BUS","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2023-04-29 09:00","2023-04-29 14:00","2023-04-29 09:00","2023-04-29 14:00","연속"]
[15,"남서울","영등포","신시흥신광명#1 T/L","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2023-04-29 14:00","2023-04-30 18:00","2023-04-29 14:00","2023-04-30 18:00","연속"]
[16,"남서울","영등포","신광명S/S #75 BUS","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","345kV 63kA GIS 24CB 설치","2023-04-29 14:00","2023-04-30 18:00","2023-04-29 14:00","2023-04-30 18:00","연속"]
[17,"인천","김포","신김포S/S CB 7671","신김포S/S 345kV #3M.Tr 설치공사(전문)","362kV GIS x 1CB 증설(#3M.Tr 1차) 345kV #3M.Tr 변압기 무부하가압 계통시험팀 시험","2023-04-29 09:00","2023-04-29 18:00","취소","취소","연속"]
[18,"인천","김포","신김포S/S CB 7600","신김포S/S 345kV #3M.Tr 설치공사(전문)","362kV GIS x 1CB 증설(#3M.Tr 1차) 345kV #3M.Tr 변압기 무부하가압","2023-04-28 09:00","2023-04-29 18:00","취소","취소","연속"]
[19,"인천","김포","신김포S/S #76 BUS","신김포S/S 345kV #3M.Tr 설치공사(전문)","362kV GIS x 1CB 증설(#3M.Tr 1차) 345kV #3M.Tr 무부하가압","2023-04-28 09:00","2023-04-29 18:00","취소","취소","연속"]
[20,"인천","김포","신김포서인천CC T/L","345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사","추락방지시설 설치공사","2023-04-07 09:00","2023-04-08 18:00","2023-04-07 09:00","2023-04-08 18:00","연속"]
[21,"인천","김포","신김포신인천CC T/L","345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사","추락방지시설 설치공사","2023-04-14 09:00","2023-04-15 18:00","2023-04-14 09:00","2023-04-15 18:00","연속"]
[22,"인천","부평","서인천C/C CB 7A71","서인천C/C 345kV 서인천CC-신부평#1T/L GIS 보통점검","서인천C/C 345kV 7A71 GIS 보통점검","2023-04-17 09:00","2023-04-17 18:00","2023-04-17 09:00","2023-04-17 18:00","연속"]
[23,"인천","부평","서인천C/C CB 7A72","서인천C/C 345kV 서인천CC-신부평#4T/L GIS 보통점검","서인천S/Y 345kV 7A72GIS 보통점검","2023-04-10 09:00","2023-04-10 18:00","2023-04-10 09:00","2023-04-10 18:00","연속"]
[24,"인천","부평","신가좌신시흥#1 T/L","신가좌S/S #2M.Tr 교체공사","#2M.Tr A상 2차 부싱 교체","2023-04-27 09:00","2023-04-28 18:00","2023-04-27 09:00","2023-04-28 18:00","연속"]
[25,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S #2M.Tr 교체공사","#2M.Tr A상 2차 부싱 교체","2023-04-24 09:00","2023-04-28 18:00","2023-04-24 09:00","2023-04-28 18:00","연속"]
[26,"인천","부평","신가좌신시흥#1 T/L","가공송전 정비회사 총액공사","수평 추락방지시설 설치공사","2023-04-20 09:00","2023-04-23 18:00","취소","취소","연속"]
[27,"인천","부평","신경서S/S CB 7271","신경서S/S 345kV 신경서-인천CC#1T/L GIS 보통점검","신경서S/S 345kV 7271GIS 보통점검","2023-04-14 09:00","2023-04-14 18:00","2023-04-14 09:00","2023-04-14 18:00","연속"]
[28,"인천","부평","신경서S/S CB 7200","신경서S/S 345kV 신경서인천CC#1T/L-#2 M.Tr 보통점검","신경서S/S 345kV 7200 TIE GIS 보통점검","2023-04-12 09:00","2023-04-12 18:00","2023-04-12 09:00","2023-04-12 18:00","연속"]
[29,"인천","부평","신경서S/S CB 7100","345kV 신경서신인천CCT/L-#1 M.Tr TIE GIS 보통점검","신경서S/S 345kV 7100 TIE GIS 보통점검","2023-04-11 09:00","2023-04-11 18:00","2023-04-11 09:00","2023-04-11 18:00","연속"]
[30,"인천","부평","신경서S/S CB 7171","신경서S/S 345kV 신경서-신인천CCT/L GIS 가스누기 보수 공사","신경서S/S 345kV 7171GIS B상 가스누기 보수","2023-04-03 09:00","2023-04-05 18:00","2023-04-03 09:00","2023-04-05 18:00","연속"]
[31,"인천","부평","신인천C/C CB 7500","신인천C/C 345kV 3MT101 GIS 보통점검","신인천C/C 345kV 7500 GIS 보통점검","2023-04-19 09:00","2023-04-19 18:00","2023-04-19 09:00","2023-04-19 18:00","연속"]
[32,"인천","부평","신인천C/C CB 7871","신인천C/C 345kV 신경서-신인천C/C T/L GIS 보통점검","신인천C/C 345kV 7871GIS 보통점검","2023-04-20 09:00","2023-04-20 18:00","2023-04-20 09:00","2023-04-20 18:00","연속"]
[33,"인천","부평","신인천C/C CB 7800","신인천C/C 신경서신인천T/L-4MT201 TIE GIS 보통점검","신인천C/C 345kV 7800GIS 보통점검","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[34,"인천","부평","신인천C/C CB 7700","신인천C/C 신김포신인천T/L-4MT101 TIE GIS 보통점검","신인천C/C 345kV 7700GIS 보통점검","2023-04-25 09:00","2023-04-25 18:00","취소","취소","연속"]
[35,"인천","부평","신인천C/C CB 7771","신인천C/C 345kV 신김포-신인천C/C T/L GIS 보통점검","신인천C/C 345kV 7771GIS 보통점검","2023-04-26 09:00","2023-04-26 18:00","취소","취소","연속"]
[36,"인천","부평","신인천C/C CB 7871","신인천C/C 345kV 신경서-신인천C/C T/L GIS 보통점검","신인천C/C 345kV 7871GIS 보통점검","2023-04-27 09:00","2023-04-27 18:00","2023-04-27 09:00","2023-04-27 18:00","연속"]
[37,"인천","부평","신인천C/C CB 7572","신인천C/C 345kV 3MT101 GIS 보통점검","신인천C/C 345kV 7572GIS 보통점검","2023-04-28 09:00","2023-04-28 18:00","2023-04-28 09:00","2023-04-28 18:00","연속"]
[38,"인천","부평","인천C/C CB 7C00","인천CC 362kV TIE GIS(7C00) 보통점검","345kV 가정인천CC#2T/L-#2 TIE Tr 1차 TIE 7C00GIS 보통","2023-04-02 09:00","2023-04-02 18:00","취소","취소","연속"]
[39,"인천","부평","인천C/C #2 Tie-Tr","인천CC S/Y 345kV #2 TIE Tr 휴전작업","인천CC S/Y 345kV #2 TIE Tr 1차 7C72GIS 조작시험/2차 6244GIS 보통점검 및 3차측 4244GIS CT결선 변경작업","2023-04-01 09:00","2023-04-02 18:00","2023-04-01 09:00","2023-04-02 18:00","연속"]
[40,"인천","부평","포스코C/C CB 7272","포스코S/Y 345kV #2 STEP-UP-TR T/L GIS 보통점검","포스코S/Y 345kV 7272 보통점검","2023-04-25 09:00","2023-04-25 18:00","2023-04-25 09:00","2023-04-25 18:00","연속"]
[41,"인천","부평","포스코C/C CB 7372","포스코S/Y 345kV #3 STEP-UP-TR T/L GIS 보통점검","포스코S/Y 345kV 7372 보통점검","2023-04-26 09:00","2023-04-26 18:00","2023-04-26 09:00","2023-04-26 18:00","연속"]
[42,"인천","부평","포스코C/C CB 7472","포스코S/Y 345kV #4 STEP-UP-TR T/L GIS 보통점검","포스코S/Y 345kV 7472 보통점검","2023-04-27 09:00","2023-04-27 18:00","2023-04-27 09:00","2023-04-27 18:00","연속"]
[43,"인천","부평","포스코C/C CB 7172","포스코S/Y 345kV #1 STEP-UP-TR T/L GIS 보통점검","포스코S/Y 345kV 7172보통점검","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[44,"인천","시흥","신시흥신광명#1 T/L","가공송전 정비회사 총액공사","수평 추락방지시설 설치공사","2023-04-20 09:00","2023-04-23 18:00","취소","취소","연속"]
[45,"인천","시흥","신시흥영흥TP#4 T/L","345kV 영흥T/L 추락방지장치 설치공사","송전철탑 추락방지장치 설치 - 대상 : 4회선 구간 / No.22~26(5기),56~83(27기) 2회선 구간 / No.130~154","2023-04-15 07:00","2023-04-23 18:00","2023-04-15 07:00","2023-04-23 18:00","연속"]
[46,"인천","시흥","신시흥영흥TP#3 T/L","345kV 영흥T/L 추락방지장치 설치공사","송전철탑 추락방지장치 설치 - 대상 : 4회선 구간 / No.22~26(5기),56~83(27기)","2023-04-24 07:00","2023-04-30 18:00","2023-04-24 07:00","2023-04-30 18:00","연속"]
[47,"인천","시흥","서서울#2신시흥#1 T/L","신시흥S/S 345kV 서서울2신시흥#1 T/L GIS 보통점검","신시흥S/S 345kV 서서울2신시흥#1 T/L GIS 보통점검(7571) - LA 대체","2023-04-10 09:00","2023-04-10 18:00","2023-04-20 09:00","2023-04-20 18:00","연속"]
[48,"인천","시흥","신시흥영흥TP#1 T/L","345kV 영흥T/L 추락방지장치 설치공사","송전철탑 추락방지장치 설치 - 대상 : 4회선 구간 / No.22~26(5기),56~83(27기)","2023-04-24 07:00","2023-04-30 18:00","2023-04-24 07:00","2023-04-30 18:00","연속"]
[49,"인천","시흥","신시흥영흥TP#2 T/L","345kV 영흥T/L 추락방지장치 설치공사","송전철탑 추락방지장치 설치 - 대상 : 4회선 구간 / No.22~26(5기),56~83(27기) 2회선 구간 / No.130~154","2023-04-12 07:00","2023-04-20 18:00","2023-04-12 07:00","2023-04-20 18:00","연속"]
[50,"인천","시흥","신시흥#2S/S #5 M.Tr","신시흥S/S 345kV #5 M.Tr 보통점검","신시흥S/S 345kV #5 M.Tr 보통점검 - OLTC 보통점검 - 1,2,3차 LA 보통점검 - 1차 GIS 보통점검(7372, 7300), 2차 GIS 보통점검 - #5-1, 5-2 Sh.R VCB 초기점검 - 3차 PT 보통점검","2023-04-11 09:00","2023-04-14 18:00","2023-04-03 09:00","2023-04-14 18:00","연속"]
[51,"인천","시흥","신시흥S/S CB 7500","신시흥S/S 345kV 7500 GIS 보통점검","신시흥S/S 345kV 7500 GIS 보통점검","2023-04-03 09:00","2023-04-03 18:00","2023-04-19 09:00","2023-04-19 18:00","연속"]
[52,"인천","시흥","신시흥신안산#1 T/L","신시흥S/S 345kV 신시흥신안산#1T/L GIS 보통점검","신시흥S/S 345kV 신시흥신안산#1T/L GIS 보통점검(7371)","2023-04-04 09:00","2023-04-04 18:00","2023-04-03 09:00","2023-04-14 18:00","연속"]
[53,"인천","시흥","신시흥신안산#2 T/L","신시흥S/S 345kV 신시흥신안산#2T/L GIS 보통점검","신시흥S/S 345kV 신시흥신안산#2T/L GIS 보통점검(7471) - LA 대체","2023-04-05 09:00","2023-04-05 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[54,"인천","시흥","신시흥S/S CB 7400","신시흥S/S 345kV 7400 GIS 보통점검","신시흥S/S 345kV 7400 GIS 보통점검","2023-04-06 09:00","2023-04-06 18:00","2023-04-17 09:00","2023-04-17 18:00","연속"]
[55,"경기북부","고양","신파주신덕은#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","스페이서 교체","2023-04-14 07:00","2023-04-14 18:00","2023-04-14 07:00","2023-04-14 18:00","연속"]
[56,"경기북부","고양","신파주S/S #4 M.Tr","'22~23년 고양P/O 변전협력회사 총액공사","신파주S/S 345kV #4M.Tr 초기점검","2023-04-03 10:00","2023-04-04 18:00","2023-04-03 10:00","2023-04-04 18:00","연속"]
[57,"경기북부","고양","신파주S/S SEC CB 75760","22-23년 고양전력지사 변전협력회사 총액공사","신파주S/S 75-76 BUS-SEC GIS 보통점검","2023-04-07 09:30","2023-04-07 18:00","2023-04-07 09:30","2023-04-07 18:00","연속"]
[58,"경기북부","고양","신파주S/S SEC CB 70710","22-23년 고양전력지사 변전협력회사 총액공사","신파주S/S 70-71 BUS-SEC GIS 보통점검","2023-04-10 09:30","2023-04-10 18:00","2023-04-17 09:30","2023-04-17 18:00","연속"]
[59,"경기북부","구리","미금S/S CB 7900","2022~23 구리전력 변전협력 총액공사","미금SA 345KV STATCOM M.TR 1차 TIE 7900 GIS 보통점검","2023-04-27 09:00","2023-04-27 18:00","2023-04-27 09:00","2023-04-27 18:00","연속"]
[60,"경기북부","구리","미금S/S CB 7972","2022~23 구리전력 변전협력 총액공사","미금SA STATCOM M.TR 1차 7972 GIS 보통점검","2023-04-25 09:00","2023-04-25 18:00","2023-04-25 09:00","2023-04-25 18:00","연속"]
[61,"경기북부","구리","미금S/S CB 7771","2022~23 구리전력 변전협력 총액공사","미금SA 345KV 신가평-미금#1T/L 7771 GIS 보통점검","2023-04-18 09:00","2023-04-18 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[62,"경기북부","구리","미금S/S CB 7700","2022~23 구리전력 변전협력 총액공사","미금SA 345KV 신가평#1T/L-성동#4T/L TIE 7700 GIS 보통점검","2023-04-17 09:00","2023-04-17 18:00","2023-04-17 09:00","2023-04-17 18:00","연속"]
[63,"경기북부","구리","미금S/S CB 7772","2022~23 구리전력 변전협력 총액공사","미금SA 345KV 미금-성동#4T/L 7772 GIS 보통점검","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[64,"경기북부","구리","포천C/C CB 7300","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV 신포천포천CC#2T/L-#4S/UTR 1차 7300 GIS 조작시험","2023-04-20 15:00","2023-04-20 18:00","취소","취소","연속"]
[65,"경기북부","구리","포천C/C CB 7372","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV #4S/U TR 1차 7372 GIS 조작시험","2023-04-20 09:00","2023-04-20 12:00","취소","취소","연속"]
[66,"경기북부","구리","포천C/C CB 7271","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV #2S/U TR 1차 7271 GIS 조작시험","2023-04-13 09:00","2023-04-13 12:00","취소","취소","연속"]
[67,"경기북부","구리","포천C/C CB 7171","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV 신포천-포천CC #1T/L 7171 GIS 조작시험","2023-04-06 09:00","2023-04-06 12:00","취소","취소","연속"]
[68,"경기북부","구리","포천C/C CB 7100","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV 신포천포천CC#1T/L-#1S/U TR 1차 7100 GIS 조작시험","2023-04-06 12:00","2023-04-06 15:00","취소","취소","연속"]
[69,"경기북부","구리","포천C/C CB 7172","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV #1S/U TR 1차 7172 GIS 조작시험","2023-04-06 15:00","2023-04-06 18:00","취소","취소","연속"]
[70,"경기북부","구리","포천C/C CB 7371","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV 신포천-포천CC #2T/L 7371 GIS 조작시험","2023-04-20 12:00","2023-04-20 15:00","취소","취소","연속"]
[71,"경기북부","구리","포천C/C CB 7200","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV #2S/U TR-#3S/U TR TIE 7200 GIS 조작시험","2023-04-13 15:00","2023-04-13 18:00","취소","취소","연속"]
[72,"경기북부","구리","포천C/C CB 7272","2022~23 구리전력 변전협력 총액공사","포천C/C 345kV #3S/U TR 1차 7272 GIS 조작시험","2023-04-13 12:00","2023-04-13 15:00","취소","취소","연속"]
[73,"경기북부","구리","포천LNGC/C CB 7300","2022~23 구리전력 변전협력 총액공사","포천LNGC/C 신가평#2T/L-#1 S/T TR 2차 7300 GIS 보통점검","2023-04-10 09:00","2023-04-10 18:00","2023-04-21 09:00","2023-04-21 18:00","연속"]
[74,"경기북부","구리","포천LNGC/C CB 7171","2022~23 구리전력 변전협력 총액공사","포천LNGC/C 345kV 신포천-포천LNGC/C #1T/L 7171 GIS 보통점검","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[75,"경기북부","구리","포천LNGC/C CB 7100","2022~23 구리전력 변전협력 총액공사","포천LNGC/C 345kV 신포천#1T/L-#1 G/T TR 2차 7100 GIS 보통점검","2023-04-04 09:00","2023-04-04 18:00","2023-04-04 09:00","2023-04-04 18:00","연속"]
[76,"경기북부","구리","포천LNGC/C CB 7372","2022~23 구리전력 변전협력 총액공사","포천LNGC/C 345kV #1 S/T TR 2차 7372 GIS 보통점검","2023-04-11 09:00","2023-04-11 18:00","2023-04-26 09:00","2023-04-26 18:00","연속"]
[77,"경기북부","직할","신의정부S/S CB 7571","22-23년도 직할 변전협력회사 총액공사","신의정부SS 362kV GIS 7571 보통점검","2023-04-03 09:00","2023-04-04 18:00","2023-04-03 09:00","2023-04-04 18:00","연속"]
[78,"경기북부","직할","신의정부양주#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 345kV 신의정부-양주T/L No.1~80","2023-04-24 07:00","2023-05-04 18:00","2023-04-24 07:00","2023-05-04 18:00","연속"]
[79,"경기북부","직할","신의정부S/S #1 M.Tr","22-23년도 직할 변전협력회사 총액공사","신의정부SS 362kV GIS 7200, 7272 조작시험","2023-04-05 09:00","2023-04-06 18:00","2023-04-05 09:00","2023-04-06 18:00","연속"]
[80,"경기북부","직할","신의정부양주#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 345kV 신의정부-양주T/L No.1~97","2023-04-03 07:00","2023-04-14 18:00","2023-04-03 07:00","2023-04-14 18:00","연속"]
[81,"경기북부","직할","양주중부#2 T/L","22~23년 고양전력 가공송전협력회사 총액공사","지지애자 교체 및 피뢰기설치","2023-04-17 07:00","2023-04-21 18:00","취소","취소","연속"]
[82,"경기북부","직할","양주S/S CB 7472","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV GIS 7472 보통점검","2023-04-10 09:00","2023-04-12 18:00","2023-04-10 09:00","2023-04-12 18:00","연속"]
[83,"경기북부","직할","양주S/S #4 M.Tr","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV GIS 7700, 7772 보통점검","2023-04-17 09:00","2023-04-20 18:00","2023-04-17 09:00","2023-04-20 18:00","연속"]
[84,"경기","군포","서서울#2신시흥#1 T/L","2022-2023년 군포전력 가공송전협력회사 총액공사","345kV 서서울2-신시흥#1T/L 9호 애자교체","2023-04-03 07:00","2023-04-03 11:00","2023-04-03 07:00","2023-04-03 11:00","연속"]
[85,"경기","군포","신온양서서울#1 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-04-08 07:00","2023-04-09 18:00","취소","취소","연속"]
[86,"경기","군포","신온양서서울#1 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-04-15 07:00","2023-04-16 18:00","취소","취소","연속"]
[87,"경기","군포","신온양서서울#1 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-04-22 07:00","2023-04-23 18:00","취소","취소","연속"]
[88,"경기","군포","신온양서서울#1 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-04-01 07:00","2023-04-02 18:00","취소","취소","연속"]
[89,"경기","군포","신온양서서울#2 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-04-29 07:00","2023-04-30 18:00","취소","취소","연속"]
[90,"경기","동부","곤지암S/S #2 M.Tr","23년 동부 변전협력총액공사","곤지암:#2M.Tr(보통), 1.2차부싱절연유채유 7372,6244,4289(보통) #2S.Tr(보통) #2M.Tr 1차 LA(A,B,C)(보통) #2M.Tr 2차 LA(A,B,C)(대체) #2M.Tr 3차 LA(A,B,C)(대체)","2023-04-19 09:00","2023-04-20 18:00","2023-04-19 09:00","2023-04-20 18:00","연속"]
[91,"경기","동부","곤지암동서울#2 T/L","추락방지시설 설치공사","추락방지시설 설치","2023-04-28 07:00","2023-04-29 18:00","취소","취소","연속"]
[92,"경기","동부","곤지암S/S #1 M.Tr","23년 동부 변전협력총액공사","곤지암:#1M.Tr(보통), 1,2차 부싱절연유채유 7172,6144,4189(보통) #1S.Tr(보통) #1M.Tr 1차 LA(A,B,C)(보통) #1M.Tr 2차 LA(A,B,C)(대체) #1M.Tr 3차 LA(A,B,C)(대체)","2023-04-17 09:30","2023-04-18 18:00","2023-04-17 09:30","2023-04-18 18:00","연속"]
[93,"경기","동부","곤지암S/S #2 M.Tr","23년 동부 변전협력총액공사","곤지암:#2M.Tr(보통), 1,2차 부싱절연유채유 7172,6144,4189(보통) #1S.Tr(보통) #1M.Tr 1차 LA(A,B,C)(보통) #1M.Tr 2차 LA(A,B,C)(대체) #1M.Tr 3차 LA(A,B,C)(대체)","2023-04-19 09:30","2023-04-20 18:00","취소","취소","연속"]
[94,"경기","동부","곤지암동서울#1 T/L","추락방지시설 설치공사","추락방지시설 설치","2023-04-25 07:00","2023-04-27 18:00","취소","취소","연속"]
[95,"경기","동부","곤지암S/S #1 Sh.R (CB 7179)","23년 동부 변전협력총액공사","곤지암:#1Sh.R 7179(조작)","2023-04-24 09:30","2023-04-24 18:00","2023-03-21 09:30","2023-03-21 18:00","연속"]
[96,"경기","성남","신성남S/S #4 M.Tr","23년 성남전력 170, 362kV GIS 보통점검공사","- 7500, 7572 GIS 보통점검 - 2차 GIS 조작시험(대한중전기)","2023-04-27 09:00","2023-04-28 18:00","취소","취소","연속"]
[97,"경기","성남","신안성신수원#2 T/L","LS제 362kV GIS 설비개선공사","-(신수원) 제작사 EDS Unit 교체 -(신안성) 결상회로 개선[송운(변전)-10585]","2023-04-24 08:00","2023-04-26 18:00","2023-04-24 08:00","2023-04-26 18:00","연속"]
[98,"경기","성남","신수원S/S #4 M.Tr","23년 성남전력지사 변전협력회사 총액공사","-주변압기 보통점검 -1차 하우징 누유 점검 -예방진단시스템설치(예방정비팀) -1차 EDS Unit 교체(예방정비팀)","2023-04-19 09:00","2023-04-21 18:00","2023-04-19 09:00","2023-04-21 18:00","연속"]
[99,"경기","성남","신수원S/S #3 M.Tr","23년 성남전력지사 변전협력회사 총액공사","-주변압기 보통점검 -75Bay B/F 대체 -예방진단시스템설치(예방정비팀) -1차 EDS Unit 교체(예방정비팀)","2023-04-03 09:00","2023-04-12 18:00","2023-04-03 09:00","2023-04-12 18:00","연속"]
[100,"경기","성남","신용인S/S #3 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- 주변압기 보통점검 - 2차 GIS 조작시험 - 1, 3차 PT 보통점검 - 1, 2차 LA 보통점검","2023-04-17 09:00","2023-04-18 18:00","2023-04-17 09:00","2023-04-18 18:00","연속"]
[101,"경기","평택","고덕S/S #2 M.Tr","23년 평택전력지사 변전협력회사 총액공사","고덕S/S #2M.Tr 변압기 보통점검, 7472,7400GIS 보통점검, 6244GIS 보통점검 및 DC케이블 이설, 4289,4289-1,2SIS 보통점검, #2S.Tr 보통점검","2023-04-10 09:00","2023-04-11 18:00","2023-04-10 09:00","2023-04-11 18:00","연속"]
[102,"경기","평택","서안성S/S CB 7171","현대제 345kV GIS 유압조작시스템 구조개선 공사","7171GIS 유압조작시스템 구조개선","2023-04-11 09:00","2023-04-11 18:00","2023-04-27 09:00","2023-04-27 18:00","연속"]
[103,"경기","평택","서안성S/S #1 M.Tr","23년 평택전력지사 변전협력회사 총액공사 ","서안성S/S #1M.Tr 변압기 보통점검, 부싱절연유 채유","2023-04-12 09:00","2023-04-13 18:00","2023-04-03 09:00","2023-04-04 18:00","연속"]
[104,"경기","평택","서안성S/S CB 7471","현대제 345kV GIS 유압조작시스템 구조개선 공사","7471GIS 유압조작시스템 구조개선","2023-04-14 09:00","2023-04-14 18:00","2023-04-07 09:00","2023-04-07 18:00","연속"]
[105,"경기","평택","서안성S/S #2 M.Tr","23년 평택전력지사 변전협력회사 총액공사 ","서안성S/S #2M.Tr 변압기 보통점검, 부싱절연유 채유","2023-04-17 09:00","2023-04-18 18:00","2023-04-05 09:00","2023-04-06 18:00","연속"]
[106,"경기","평택","서안성S/S CB 7371","현대제 345kV GIS 유압조작시스템 구조개선 공사","7371GIS 유압조작시스템 구조개선","2023-04-19 09:00","2023-04-19 18:00","2023-04-19 09:00","2023-04-19 18:00","연속"]
[107,"경기","평택","서안성S/S CB 7400","현대제 345kV GIS 유압조작시스템 구조개선 공사","7400GIS 유압조작시스템 구조개선","2023-04-20 09:00","2023-04-20 18:00","2023-04-20 09:00","2023-04-20 18:00","연속"]
[108,"경기","평택","서안성S/S CB 7472","현대제 345kV GIS 유압조작시스템 구조개선 공사","7472GIS 유압조작시스템 구조개선","2023-04-21 09:00","2023-04-21 18:00","2023-04-21 09:00","2023-04-21 18:00","연속"]
[109,"경기","평택","서안성S/S CB 7271","현대제 345kV GIS 유압조작시스템 구조개선 공사","7271GIS 유압조작시스템 구조개선","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[110,"경기","평택","서안성S/S CB 7200","현대제 345kV GIS 유압조작시스템 구조개선 공사","7200GIS 유압조작시스템 구조개선","2023-04-25 09:00","2023-04-25 18:00","2023-04-25 09:00","2023-04-25 18:00","연속"]
[111,"경기","평택","서안성S/S CB 7672","현대제 345kV GIS 유압조작시스템 구조개선 공사","7672GIS 유압조작시스템 구조개선","2023-04-26 09:00","2023-04-26 18:00","2023-04-26 09:00","2023-04-26 18:00","연속"]
[112,"경기","평택","서안성S/S #4 M.Tr","345kV 고덕2-서안성T/L 건설공사","- 송전선로 ~ Gantry Tower 접속 - 송전선로 리드선 ~ GIS 부싱 접속","2023-04-03 09:00","2023-04-07 18:00","2023-04-10 09:00","2023-04-18 18:00","연속"]
[113,"경기","평택","서안성S/S CB 7671","345kV 고덕2-서안성T/L 건설공사","- 송전선로 ~ Gantry Tower 접속 - 송전선로 리드선 ~ GIS 부싱 접속","2023-04-03 09:00","2023-04-07 18:00","2023-04-10 09:00","2023-04-18 18:00","연속"]
[114,"강원","동해","동해S/S CB 7171","23년 동해S/S 362kV GIS 정밀점검","23년 동해S/S 362kV GIS 정밀점검","2023-04-27 09:00","2023-04-29 18:00","2023-04-27 09:00","2023-04-29 18:00","연속"]
[115,"강원","동해","동해S/S CB 7300","23년 동해S/S 362kV GIS 정밀점검","23년 동해S/S 362kV GIS 정밀점검","2023-04-24 09:00","2023-04-26 18:00","2023-04-24 09:00","2023-04-26 18:00","연속"]
[116,"강원","동해","동해S/S CB 7371","23년 동해S/S 362kV GIS 정밀점검","23년 동해S/S 362kV GIS 정밀점검","2023-04-20 09:00","2023-04-22 18:00","2023-04-20 09:00","2023-04-22 18:00","연속"]
[117,"강원","동해","동해S/S CB 7400","23년 동해S/S 362kV GIS 정밀점검","23년 동해S/S 362kV GIS 정밀점검","2023-04-17 09:00","2023-04-19 18:00","2023-04-17 09:00","2023-04-19 18:00","연속"]
[118,"강원","동해","동해S/S CB 7471","23년 동해S/S 362kV GIS 정밀점검","23년 동해S/S 362kV GIS 정밀점검","2023-04-13 09:00","2023-04-15 18:00","2023-04-13 09:00","2023-04-15 18:00","연속"]
[119,"강원","동해","동해S/S CB 7472","23년 동해S/S 362kV GIS 정밀점검","23년 동해S/S 362kV GIS 정밀점검","2023-04-10 09:00","2023-04-12 18:00","2023-04-10 09:00","2023-04-12 18:00","연속"]
[120,"강원","동해","동해S/S CB 7172","23년 동해S/S 362kV GIS 정밀점검","23년 동해S/S 362kV GIS 정밀점검","2023-04-04 09:00","2023-04-07 18:00","2023-04-04 09:00","2023-04-07 18:00","연속"]
[121,"강원","태백","신태백한울NP#2 T/L","345kV 울태T/L 고정형 폴리머점퍼지지애자 설치공사","- 345kV 신태백-한울NP2T/L 고정형 폴리머점퍼지지애자 및 수평추락방지장치 설치공사 - 345kV 신태백-한울NP2#2T/L 정밀점검(병행)","2023-04-03 09:00","2023-04-14 18:00","2023-04-03 09:00","2023-04-09 18:00","연속"]
[122,"충북","직할","신중부신진천#2 T/L","2022~2023년 청주전력지사 송전협력회사 총액공사(추락방지시설 설치)","345kV 신중부-신진천#2T/L 수평 추락방지시설 설치(No.8~27, 17기)","2023-04-19 07:00","2023-04-21 18:00","취소","취소","매일"]
[123,"충북","청주","남청주S/S #4 M.Tr","345kV 남청주S/S #5 M.Tr 증설공사","#5 M.Tr 무부하가압","2023-04-20 15:00","2023-04-21 15:00","2023-04-20 15:00","2023-04-21 15:00","연속"]
[124,"충북","청주","남청주S/S CB 7800","345kV 남청주S/S #5 M.Tr 증설공사","#5 M.Tr 1차 7871 CB 증설","2023-04-03 10:00","2023-04-21 18:00","2023-04-03 10:00","2023-04-21 18:00","연속"]
[125,"충북","청주","남청주S/S #4 M.Tr","345kV 남청주S/S #5 M.Tr 증설공사","#5 M.Tr 1차 7871 CB 증설 관련 78 BAY B/F반 대체 (2CB → 3CB)","2023-04-07 10:00","2023-04-10 18:00","2023-04-07 10:00","2023-04-10 18:00","연속"]
[126,"충북","충주","신제천신영주#1 T/L","2023년 충주전력 가공송전선로 순시점검 위탁공사","정밀점검","2023-04-03 07:00","2023-04-19 18:00","취소","취소","매일"]
[127,"충북","충주","신제천S/S SVC CB","2023년 신제천S/S 345kV SVC 보통점검","신제천S/S 345kV SVC 보통점검","2023-04-05 09:00","2023-04-18 18:00","취소","취소","연속"]
[128,"대전세종충남","서산","당진T/P CB 7272","23년 서산P/O 345kV GIS 보통점검공사","당진화력S/S 345kV 2호기 1차 CB 7272 보통점검 및 보조계전기 교체","2023-04-14 09:00","2023-04-14 18:00","2023-04-14 09:00","2023-04-14 18:00","연속"]
[129,"대전세종충남","서산","신당진개폐소 CB 7B00","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 현대제철T/L-TIE CB 7B00 보통점검","2023-04-25 09:00","2023-04-25 18:00","2023-04-25 09:00","2023-04-25 18:00","연속"]
[130,"대전세종충남","서산","신당진개폐소 CB 7B71","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 현대제철T/L CB 7B71 보통점검","2023-04-27 09:00","2023-04-27 18:00","2023-04-27 09:00","2023-04-27 18:00","연속"]
[131,"대전세종충남","서산","신당진개폐소 CB 7A72","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 연락#1T/L CB 7A72 보통점검","2023-04-20 09:00","2023-04-20 18:00","2023-04-20 09:00","2023-04-20 18:00","연속"]
[132,"대전세종충남","서산","신당진S/S #2 M.Tr","23년 서산P/O 345kV이하 M.Tr 보통점검공사","신당진S/S 345kV #2M.Tr 보통점검","2023-04-10 09:00","2023-04-12 18:00","2023-04-10 09:00","2023-04-12 18:00","연속"]
[133,"대전세종충남","서산","신당진S/S CB 7471","23년 서산P/O 345kV GIS 보통점검공사","신당진S/S 345kV 연락#1T/L CB 7471 보통점검","2023-04-18 09:00","2023-04-18 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[134,"대전세종충남","서산","신당진S/S #3 M.Tr","'23년 장기 미동작 차단기 조작시험","신당진S/S 345kV #3M.Tr 1, 2차 GIS(7872, 6344) 조작시험 (병행) #3M.Tr 1, 2, 3차 LA 보통점검","2023-04-18 09:00","2023-04-18 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[135,"대전세종충남","서산","신당진S/S #1 M.Tr","23년 서산P/O 345kV이하 M.Tr 보통점검공사","신당진S/S 345kV #1M.Tr 보통점검","2023-04-03 09:00","2023-04-05 18:00","2023-04-03 09:00","2023-04-05 18:00","연속"]
[136,"대전세종충남","서산","태안T/P #71 BUS","현대제 345kV 차단기 조작로드 교체공사","태안화력S/Y 345kV 71-72-0 SEC CB 조작로드 교체공사 (작업구간 겹침으로 BUS 휴전 필요)","2023-04-17 09:00","2023-04-28 18:00","2023-04-17 09:00","2023-04-28 18:00","연속"]
[137,"대전세종충남","서산","태안T/P CB 7872","23년 서산P/O 345kV GIS 보통점검공사","태안화력S/S 345kV #8 GEN 1차 CB 7872 보통점검 및 보조계전기 교체","2023-04-11 09:00","2023-04-13 18:00","2023-04-11 09:00","2023-04-13 18:00","연속"]
[138,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S 345kV 77Bay B/F보호반 교체","신온양S/S 345kV 77Bay B/F보호반 교체","2023-04-03 09:00","2023-04-07 18:00","취소","취소","연속"]
[139,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S 345kV 77Bay B/F보호반 교체","신온양S/S 345kV 77Bay B/F보호반 교체","2023-04-03 09:00","2023-04-07 18:00","2023-04-03 09:00","2023-04-07 18:00","연속"]
[140,"대전세종충남","천안","신온양신탕정#2 T/L","신온양S/S 345kV 78Bay B/F보호반 교체","신온양S/S 345kV 78Bay B/F보호반 교체","2023-04-17 09:00","2023-04-21 18:00","2023-04-17 09:00","2023-04-21 18:00","연속"]
[141,"대전세종충남","천안","신온양서서울#1 T/L","신온양S/S 345kV 78Bay B/F보호반 교체","신온양S/S 345kV 78Bay B/F보호반 교체","2023-04-17 09:00","2023-04-21 18:00","취소","취소","연속"]
[142,"대전세종충남","천안","신탕정S/S #4 M.Tr","(3월취소시)신탕정S/S 345kV #4M.Tr 하자보수","(3월취소시)신탕정S/S 345kV #4M.Tr 하자보수","2023-04-24 09:00","2023-04-28 18:00","2023-04-24 09:00","2023-04-28 18:00","연속"]
[143,"대전세종충남","천안","신온양신탕정#1 T/L","신탕정S/S 345kV 신온양-신탕정#1T/L GIS 보통점검","신탕정S/S 345kV 신온양-신탕정#1T/L GIS 보통점검","2023-04-26 09:00","2023-04-26 18:00","2023-04-26 09:00","2023-04-26 18:00","연속"]
[144,"대전세종충남","천안","아산S/S #2 M.Tr","아산S/S 345kV #2M.Tr 보통점검 및 부싱절연유 채유","아산S/S 345kV #2M.Tr 보통점검 및 부싱절연유 채유","2023-04-25 09:00","2023-04-25 18:00","2023-04-25 09:00","2023-04-25 18:00","연속"]
[145,"대전세종충남","천안","아산S/S CB 7300","아산S/S 345kV 7300 GIS 보통점검","아산S/S 345kV 7300 GIS 보통점검","2023-04-18 09:00","2023-04-18 14:00","2023-04-18 09:00","2023-04-18 14:00","연속"]
[146,"대전세종충남","천안","아산S/S CB 7800","아산S/S 345kV 7800, 7871 GIS 보통점검","아산S/S 345kV 7800, 7871 GIS 보통점검","2023-04-10 09:00","2023-04-10 14:00","2023-04-10 09:00","2023-04-10 14:00","연속"]
[147,"대전세종충남","천안","아산S/S CB 7872","아산S/S 345kV 7800, 7871 GIS 보통점검","아산S/S 345kV 7800, 7871 GIS 보통점검","2023-04-10 14:00","2023-04-10 18:00","2023-04-10 14:00","2023-04-10 18:00","연속"]
[148,"대전세종충남","천안","아산S/S CB 7500","아산S/S 345kV 7500, 7400 GIS 보통점검","아산S/S 345kV 7500, 7400 GIS 보통점검","2023-04-12 09:00","2023-04-12 14:00","2023-04-12 09:00","2023-04-12 14:00","연속"]
[149,"대전세종충남","천안","아산S/S CB 7400","아산S/S 345kV 7500, 7400 GIS 보통점검","아산S/S 345kV 7500, 7400 GIS 보통점검","2023-04-12 14:00","2023-04-12 18:00","2023-04-12 14:00","2023-04-12 18:00","연속"]
[150,"대전세종충남","천안","아산S/S CB 7272","아산S/S 345kV 7200, 7271 GIS 보통점검","아산S/S 345kV 7200, 7271 GIS 보통점검","2023-04-17 14:00","2023-04-17 18:00","2023-04-17 14:00","2023-04-17 18:00","연속"]
[151,"대전세종충남","천안","아산S/S CB 7200","아산S/S 345kV 7200, 7271 GIS 보통점검","아산S/S 345kV 7200, 7271 GIS 보통점검","2023-04-17 09:00","2023-04-17 14:00","2023-04-17 09:00","2023-04-17 14:00","연속"]
[152,"대전세종충남","천안","아산S/S CB 7172","아산S/S 345kV 7171, 7172 GIS 보통점검","아산S/S 345kV 7171, 7172 GIS 보통점검","2023-04-14 14:00","2023-04-14 18:00","2023-04-14 14:00","2023-04-14 18:00","연속"]
[153,"대전세종충남","천안","아산S/S CB 7171","아산S/S 345kV 7171, 7172 GIS 보통점검","아산S/S 345kV 7171, 7172 GIS 보통점검","2023-04-14 09:00","2023-04-14 14:00","2023-04-14 09:00","2023-04-14 14:00","연속"]
[154,"대전세종충남","청양","청양군산#1 T/L","[송전] 345kV 청양-군산T/L 가공지선 Arm 보강공사","345kV 청양-군산T/L No.94 가공지선 Arm 보강","2023-04-10 08:00","2023-04-14 18:00","취소","취소","매일"]
[155,"광주전남","강진","신강진S/S #2 M.Tr","22-23년 강진전력지사 변전전문회사 총액공사","- 신강진S/S 345kV 2M.Tr OLTC 절연유 보충 - 신강진S/S #2M.Tr 2차 LA A 보통점검 - 신강진S/S #2M.Tr 3차 BUS PT A,B,C 보통점검 - 신강진S/S #2S.Tr 하자 - 신강진S/S #2S.Tr CB 하자 및 DS 보통점검","2023-04-04 09:00","2023-04-04 18:00","2023-04-04 09:00","2023-04-04 18:00","연속"]
[156,"광주전남","광주","신광주S/S CB 7100","23년 광주전력지사 변전협력회사 총액공사(신광주 #1M.Tr)","- 362kV GIS(7100 CB) 보통점검 - #1M.Tr 3차측 차단기 교체(3차 Main, S.Tr)","2023-04-17 09:00","2023-04-19 18:00","2023-04-17 09:00","2023-04-19 18:00","연속"]
[157,"광주전남","광주","신광주S/S CB 7172","23년 광주전력지사 변전협력회사 총액공사","- 362kV GIS(7172) 조작시험 - #1M.Tr 3차 차단기 교체(3차 Main, S.Tr)","2023-04-17 09:00","2023-04-19 18:00","취소","취소","연속"]
[158,"광주전남","광주","신광주S/S CB 7600","23년 광주전력지사 변전협력회사 총액공사","- 345kV M.Tr 보통점검 - 362kV GIS 조작시험(7600,7672) - #3M.Tr 3차 차단기 교체(3차 Main, #1,2Sh.R, S.Tr) - 3차측 DS 점검","2023-04-24 09:00","2023-04-28 18:00","취소","취소","연속"]
[159,"광주전남","광주","신광주S/S #4 M.Tr","7872·7800 CB 조작시험, 현수애자 점검, 2차 LA 교체","7872·7800 CB 조작시험, 1·2차 현수애자 점검, 2차 LA 교체","2023-04-24 09:00","2023-04-25 18:00","취소","취소","연속"]
[160,"광주전남","광주","신광주S/S CB 7672","23년 광주전력지사 변전협력회사 총액공사","- 345kV M.Tr 보통점검 - 362kV GIS 조작시험(7600,7672) - #3M.Tr 3차 차단기 교체(3차 Main, #1,2Sh.R, S.Tr) - 3차측 DS 점검","2023-04-24 09:00","2023-04-28 18:00","취소","취소","연속"]
[161,"광주전남","광주","신남원신광주#1 T/L","7141,7400 CB 조작시험 / 현수애자 점검 / PD점검","- 7141,7400 CB 조작시험, 균압콘덴서 충전용량 측정 - 현수애자 점검 - PD 발생관련 점검","2023-04-11 09:00","2023-04-12 18:00","취소","취소","연속"]
[162,"광주전남","광주","신광주신화순#1 T/L","345kV 신광주-신화순T/L 추락방지시설설치공사","수평장치 설치 107기","2023-04-03 07:00","2023-04-10 18:00","취소","취소","연속"]
[163,"광주전남","광주","신광주신화순#2 T/L","345kV 신광주-신화순T/L 추락방지시설설치공사","수평장치 설치 107기","2023-04-11 07:00","2023-04-18 18:00","취소","취소","연속"]
[164,"광주전남","광주","신화순S/S #3 M.Tr","7572·7500 CB 조작시험, 2차 GIS 보통점검, 현수애자 점검","7572·7500 CB 조작시험, 2차 GIS 보통점검, 현수애자 점검","2023-04-26 09:30","2023-04-27 18:00","2023-04-26 09:30","2023-04-27 18:00","연속"]
[165,"광주전남","광주","신화순S/S #2 M.Tr","C상 누유개소 조치/7700,7772 조작시험/LA 초기점검","C상 누유개소 조치/7700,7772 조작시험/1,2,3차 LA 초기점검","2023-04-06 09:00","2023-04-07 18:00","2023-04-06 09:00","2023-04-07 18:00","연속"]
[166,"광주전남","순천","광양S/S #2 M.Tr","광양S/S 345kV 주변압기 철공진 방지 CVT 설치","광양S/S 345kV 주변압기 철공진 방지 CVT 설치","2023-04-26 08:00","2023-04-27 19:00","2023-04-26 08:00","2023-04-27 19:00","연속"]
[167,"광주전남","순천","광양S/S #1 M.Tr","광양S/S 345kV 주변압기 철공진 방지 CVT 설치","광양S/S 345kV 주변압기 철공진 방지 CVT 설치","2023-04-24 08:00","2023-04-25 19:00","2023-04-24 08:00","2023-04-25 19:00","연속"]
[168,"광주전남","순천","여수T/P CB 7371","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 율촌C/C-여수T/P #1T/L(7371) 하자점검","2023-04-17 09:00","2023-04-17 18:00","2023-04-17 09:00","2023-04-17 18:00","연속"]
[169,"광주전남","순천","여수T/P #2 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S #2M.Tr 보통점검 OFU 보통점검, 및 1차 GIS 보통점검, #2M.Tr 2차 LA 보통점검 #2M.Tr 3차 LA 하자점검 3차 GPT 보통점검,","2023-04-03 09:00","2023-04-07 18:00","취소","취소","연속"]
[170,"광주전남","순천","여수T/P #4 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S #4M.Tr 7400 GIS 하자점검 1차 GIS 하자점검(7472) 2차 GIS 하자점검(6444) 3차 GIS 하자점검 #4M.Tr LA 2차 하자점검 #4M.Tr LA 2차 M.Tr 상부 하자점검","2023-04-10 09:00","2023-04-14 18:00","취소","취소","연속"]
[171,"광주전남","순천","여수T/P CB 7300","차단기 균압콘덴서 제작사 합동 점검","균압콘덴서 점검","2023-04-13 09:00","2023-04-13 18:00","취소","취소","연속"]
[172,"대구","달성","북경남고령#1 T/L","2023년 가공송전 순시점검 위탁공사","345kV 북경남-대구#1T/L 정밀점검(345kV 북경남-고령#1T/L 병가) -4/8~4/9 주말간 환원","2023-04-10 08:00","2023-04-13 18:00","2023-04-10 08:00","2023-04-13 18:00","연속"]
[173,"대구","달성","북경남고령#2 T/L","2023년 가공송전 순시점검 위탁공사","345kV 북경남-대구#2T/L 정밀점검(345kV 북경남-고령#2T/L 병가) -4/22~4/23 주말간 환원","2023-04-17 08:00","2023-04-20 18:00","2023-04-17 08:00","2023-04-20 18:00","연속"]
[174,"대구","달성","북경남대구#2 T/L","2023년 가공송전 순시점검 위탁공사","345kV 북경남-대구#2T/L 정밀점검(345kV 북경남-고령#2T/L 병가) -4/22~4/23 주말간 환원","2023-04-17 08:00","2023-04-21 18:00","2023-04-17 08:00","2023-04-21 18:00","연속"]
[175,"대구","달성","북경남대구#1 T/L","2023년 가공송전 순시점검 위탁공사","345kV 북경남-대구#1T/L 정밀점검(345kV 북경남-고령#1T/L 병가) -4/8~4/9 주말간 환원","2023-04-10 08:00","2023-04-14 18:00","2023-04-10 08:00","2023-04-14 18:00","연속"]
[176,"대구","칠곡","서대구S/S CB 7771","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2023-04-10 09:30","2023-04-11 18:00","2023-04-10 09:30","2023-04-11 18:00","연속"]
[177,"대구","칠곡","북경남서대구#1 T/L","서대구S/S 북경남-서대구#1T/L LA, PT, GCB 점검","서대구S/S 북경남-서대구#1T/L LA, PT, GCB 점검","2023-04-25 09:30","2023-04-25 18:00","2023-04-25 09:30","2023-04-25 18:00","연속"]
[178,"대구","칠곡","서대구S/S CB 7700","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2023-04-12 09:30","2023-04-13 18:00","2023-04-12 09:30","2023-04-13 18:00","연속"]
[179,"대구","칠곡","서대구S/S CB 7772","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2023-04-17 09:30","2023-04-18 18:00","2023-04-17 09:30","2023-04-18 18:00","연속"]
[180,"대구","칠곡","서대구S/S CB 7871","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2023-04-19 09:30","2023-04-20 18:00","2023-04-19 09:30","2023-04-20 18:00","연속"]
[181,"대구","칠곡","서대구S/S CB 7372","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2023-04-24 09:30","2023-04-25 18:00","2023-04-24 09:30","2023-04-25 18:00","연속"]
[182,"대구","칠곡","서대구S/S CB 7300","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2023-04-03 09:30","2023-04-04 18:00","2023-04-03 09:30","2023-04-04 18:00","연속"]
[183,"대구","칠곡","서대구S/S CB 7571","서대구S/S 345kV GCB 공기조작부 정밀점검","서대구S/S 345kV GCB 공기조작부 정밀점검","2023-04-05 09:30","2023-04-06 18:00","2023-04-05 09:30","2023-04-06 18:00","연속"]
[184,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S GIS관련 광케이블 정비공사","○ 154kV 변전덕트 시설완공에 따른 구내 광케이블 정비 - 우회 가이설 광케이블 철거(6조, 2,640m) 및 본시설(4조, 1,900m) ○ 옥외철구 S/T POST 보강을 위한 광케이블 철거 및 재시설 - 서대구-칠곡T/L, 북대구-왜관, 관음T/L, 북대구-구암T/L","2023-04-26 09:00","2023-04-27 18:00","2023-04-26 09:00","2023-04-27 18:00","연속"]
[185,"대구","칠곡","북경남서대구#2 T/L","서대구S/S 북경남-서대구#2T/L LA 보통점검","서대구S/S 북경남-서대구#2T/L LA 보통점검","2023-04-24 09:30","2023-04-24 18:00","2023-04-24 09:30","2023-04-24 18:00","연속"]
[186,"대구","포항","신영일S/S #4 M.Tr","신영일S/S #4M.Tr 휴전작업","6446DS 구동불량 보수, GIS 조작시험, 1,2,3차 LA 초기점검","2023-04-24 09:00","2023-04-26 18:00","2023-04-24 09:00","2023-04-26 18:00","연속"]
[187,"대구","포항","신포항신월성NP#3 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","병가선로 안전확보","2023-04-03 07:00","2023-04-06 18:00","2023-04-03 07:00","2023-04-06 18:00","연속"]
[188,"대구","포항","신포항신월성NP#4 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","병가선로 안전확보","2023-04-13 07:00","2023-04-16 18:00","2023-04-13 07:00","2023-04-16 18:00","연속"]
[189,"대구","포항","선산신포항 T/L","신포항S/S 7100,7172 GCB 조작시험, LA,PT보통점검","신포항S/S 7100,7172 GCB 조작시험, LA,PT보통점검","2023-04-13 09:00","2023-04-13 18:00","취소","취소","연속"]
[190,"대구","포항","울주월성NP#1 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","정밀점검","2023-04-03 07:00","2023-04-12 18:00","2023-04-03 07:00","2023-04-12 18:00","연속"]
[191,"대구","포항","월성NP신월성NP#1 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","정밀점검","2023-04-05 07:00","2023-04-05 18:00","2023-04-05 07:00","2023-04-07 18:00","연속"]
[192,"대구","포항","월성N/P CB 7400","월성S/Y 7400,7472 GIS 조작시험","월성S/Y 7400,7472 GIS 조작시험","2023-04-05 09:00","2023-04-05 18:00","2023-04-05 09:00","2023-04-05 18:00","연속"]
[193,"대구","포항","월성N/P CB 7472","월성S/Y 7400,7472 GIS 조작시험","월성S/Y 7400,7472 GIS 조작시험","2023-04-05 09:00","2023-04-05 18:00","2023-04-05 09:00","2023-04-05 18:00","연속"]
[194,"대구","포항","울주월성NP#2 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","정밀점검","2023-04-13 07:00","2023-04-22 18:00","2023-04-13 07:00","2023-04-22 18:00","연속"]
[195,"경북","구미","선산S/S #75 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","준공시험관련 가압(상별 위상확인) 및 계통병입","2023-04-24 14:00","2023-04-25 18:00","2023-04-24 14:00","2023-04-25 18:00","연속"]
[196,"경북","구미","선산S/S #70 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","준공시험관련 가압(상별 위상확인)","2023-04-24 09:00","2023-04-24 14:00","2023-04-24 09:00","2023-04-24 14:00","연속"]
[197,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","준공시험관련 가압(상별 위상확인)","2023-04-24 09:00","2023-04-25 18:00","2023-04-24 09:00","2023-04-25 18:00","연속"]
[198,"경북","영주","삼척GP한울NP#2 T/L","2023년 한울1발S/Y 345kV GIS 정밀점검공사","2023년 한울1발S/Y 345kV GIS 정밀점검공사 - 7471 GIS","2023-04-05 09:00","2023-04-07 18:00","취소","취소","연속"]
[199,"경북","영주","한울1NP한울2NP#1 T/L","2023년 한울1발S/Y 345kV GIS 정밀점검공사","2023년 한울1발S/Y 345kV GIS 정밀점검공사 - 7271 GIS","2023-04-03 09:00","2023-04-05 18:00","취소","취소","연속"]
[200,"경북","영주","한울1NP한울2NP#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","초고압 애자 절연 코팅공사","2023-04-06 09:00","2023-04-07 09:00","2023-04-06 09:00","2023-04-07 09:00","연속"]
[201,"경북","영주","신한울한울#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","초고압 애자 절연 코팅공사","2023-04-11 09:00","2023-04-12 09:00","2023-04-11 09:00","2023-04-12 09:00","연속"]
[202,"경북","영주","신한울한울#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","초고압 애자 절연 코팅공사","2023-04-10 09:00","2023-04-11 09:00","2023-04-10 09:00","2023-04-11 09:00","연속"]
[203,"경북","직할","안동C/C #1 Tie-Tr","22~23년 경북본부 직할 변전협력회사 총액공사","M.Tr 보통점검","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[204,"경북","직할","안동C/C #2 Tie-Tr","22~23년 경북본부 직할 변전협력회사 총액공사","M.Tr 보통점검, 43PDA 교체","2023-04-04 09:00","2023-04-05 18:00","2023-04-04 09:00","2023-04-05 18:00","연속"]
[205,"경북","직할","신포항청송PP T/L","22~23년 경북본부 직할 변전협력회사 총액공사","CVT 교체","2023-04-10 09:00","2023-04-10 18:00","2023-04-10 09:00","2023-04-10 18:00","연속"]
[206,"부산울산","동부산","신양산신대연#2 T/L","345kV 신양산-신대연 등 7개T/L 자기애관교체공사","기설 자기애관을 폴리머애관으로 교체","2023-04-03 09:00","2023-04-18 18:00","2023-04-03 09:00","2023-04-18 18:00","연속"]
[207,"부산울산","북부산","서부산북부산#2 T/L","대한전선제 OF케이블 SJ접속함 채유 및 채유밸브 설치공사","1. 대 상 : 345kV 서부산-북부산T/L 2. 작업내용 : 접속함 절연유채유 및 채유밸브 설치 3. 업체명 : (주)공영전력","2023-04-28 09:00","2023-05-06 18:00","2023-04-28 09:00","2023-05-04 18:00","연속"]
[208,"부산울산","북부산","서부산북부산#1 T/L","대한전선제 OF케이블 SJ접속함 채유 및 채유밸브 설치공사","1. 대 상 : 345kV 서부산-북부산T/L 2. 작업내용 : 접속함 절연유채유 및 채유밸브 설치 3. 업체명 : (주)공영전력","2023-04-17 09:00","2023-04-25 18:00","2023-04-19 09:00","2023-04-25 18:00","연속"]
[209,"부산울산","북부산","신김해북부산#2 T/L","2022~23년 북부산전력지사가공송전 협력회사 총액공사","철탑도장 ○ 공사구간 : 345kV 신김해-북부산T/L No.26, No.27(좌측)","2023-04-26 07:00","2023-04-27 18:00","취소","취소","연속"]
[210,"부산울산","북부산","신양산북부산#2 T/L","북부산S/S STATCOM용 345kV GIS 설치공사","- STATCOM용 345kV GIS 2CB 설치 - 345kV 신양산북부산#2T/L 인출 GIS Bushing 이설","2023-04-04 09:00","2023-05-04 18:00","2023-04-04 09:00","2023-05-04 18:00","연속"]
[211,"부산울산","울산","남울산S/S CB 7400","345kV 남울산S/S 울산GPS 신규수용공사","362kV 63kA 6,300A GIS x 3CB 설치(7472,7200,7272)","2023-04-03 09:00","2023-05-12 18:00","2023-04-03 09:00","2023-05-12 18:00","연속"]
[212,"부산울산","울산","남울산울산TP#2 T/L","345kV 남울산S/S 울산GPS 신규수용공사","362kV 63kA 6,300A GIS x 3CB 설치(7472,7200,7272)","2023-04-03 09:00","2023-05-12 18:00","2023-04-03 09:00","2023-05-12 18:00","연속"]
[213,"부산울산","울산","남울산S/S #3 M.Tr","22~23년 변전협력회사 총액공사","- 부싱 종합예방진단시스템 동축 케이블 재설치(하자)","2023-04-13 09:00","2023-04-13 18:00","2023-04-13 09:00","2023-04-13 18:00","연속"]
[214,"부산울산","울산","남울산S/S #2 BUS","345kV 남울산S/S 울산GPS 신규수용공사","362kV 63kA 6,300A GIS x 3CB 설치(7472,7200,7272)","2023-04-03 09:00","2023-04-12 18:00","2023-04-03 09:00","2023-04-12 18:00","연속"]
[215,"부산울산","울산","남울산S/S #2 M.Tr","345kV 남울산S/S 울산GPS 신규수용공사","362kV 63kA 6,300A GIS x 3CB 설치(7472,7200,7272)","2023-04-03 09:00","2023-04-12 18:00","2023-04-03 09:00","2023-04-12 18:00","매일"]
[216,"부산울산","울산","동울산월성NP T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 및 폴리머점퍼지지애자 설치","2023-04-03 07:00","2023-04-18 18:00","취소","취소","연속"]
[217,"부산울산","울산","신온산S/S #4 M.Tr","신온산S/S 154kV APK T/L SW증설공사","170kV GIS(6G7 Bay) 1CCT증설 -CHAMBER 조립(전력케이블 접속잡업)","2023-04-10 09:00","2023-04-10 18:00","취소","취소","연속"]
[218,"부산울산","울산","신온산S/S CB 7271","22~23년 변전협력회사 총액공사","- GIS(7271) 하자점검","2023-04-06 09:00","2023-04-06 18:00","2023-04-06 09:00","2023-04-06 18:00","연속"]
[219,"부산울산","울산","신온산S/S CB 7272","22~23년 변전협력회사 총액공사","- GIS(7272) 하자점검","2023-04-05 09:00","2023-04-05 18:00","2023-04-05 09:00","2023-04-05 18:00","연속"]
[220,"부산울산","울산","신온산신울산#2 T/L","22~23년 변전협력회사 총액공사","- GIS(7171, 7100) 하자점검 - 피뢰기 보통점검","2023-04-13 09:00","2023-04-13 18:00","2023-04-13 09:00","2023-04-13 18:00","연속"]
[221,"부산울산","울산","신온산S/S CB 7200","22~23년 변전협력회사 총액공사","- GIS(7200) 하자점검","2023-04-04 09:00","2023-04-04 18:00","2023-04-04 09:00","2023-04-04 18:00","연속"]
[222,"부산울산","울산","신온산S/S #4 M.Tr","신온산S/S 154kV APK T/L SW증설공사","170kV GIS(6G7 Bay) 1CCT증설 -CHAMBER 개방(전력케이블 접속작업)","2023-04-03 08:00","2023-04-03 18:00","2023-04-17 08:00","2023-04-22 18:00","연속"]
[223,"부산울산","울산","신울산S/S 임시연락 T/L CB","신울산S/S 345kV 용량대체공사","- 연락T/L 철거","2023-04-17 09:00","2023-05-19 18:00","취소","취소","연속"]
[224,"부산울산","울산","신울산고리NP#1 T/L","신울산S/S 345kV 용량대체공사","- 345kV GIS 대체 관련 송전선로 접속지점 변경(구 75BAY → 신 74BAY) - 345kV GIS 대체 관련 보호배전반 이설 및 연동시험","2023-04-17 09:00","2023-05-19 18:00","취소","취소","연속"]
[225,"부산울산","울산","신울산S/S #5 M.Tr","신울산S/S 154kV 현대화공사","신울산S/S #5M.Tr 2차 관로 및 EBA 기초공사 2차 전력케이블 포접속 및 내전압 시험. 끝.","2023-04-17 09:00","2023-06-17 18:00","취소","취소","연속"]
[226,"부산울산","울산","울주S/S CB 7A00","22~23년 변전협력회사 총액공사","- GIS(7A00) 보통점검","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[227,"부산울산","울산","울주고리NP#1 T/L","22~23년 변전협력회사 총액공사","- GIS(7671) 보통점검 - CVT 보통점검","2023-04-05 09:00","2023-04-05 18:00","2023-04-05 09:00","2023-04-05 18:00","연속"]
[228,"경남","직할","창원S/S #1 M.Tr","창원S/S 345kV #1M.Tr 1,2,3차 CB 보통점검","창원S/S 345kV #1M.Tr 1,2,3차 CB 보통점검","2023-04-24 09:30","2023-04-25 18:00","2023-04-24 09:30","2023-04-25 18:00","연속"]
[229,"경남","직할","창원삼천포TP#2 T/L","345kV 창원-신고성T/L 추락방지장치 설치공사","345kV 창원-신고성T/L 추락방지장치 설치공사","2023-04-17 08:00","2023-04-23 18:00","2023-04-17 08:00","2023-04-23 18:00","매일"]
[230,"경남","직할","창원삼천포TP#1 T/L","345kV 창원-신고성T/L 추락방지장치 설치공사","345kV 창원-신고성T/L 추락방지장치 설치공사","2023-04-10 08:00","2023-04-16 18:00","2023-04-10 08:00","2023-04-16 18:00","매일"]
[231,"경남","직할","창원S/S #2 M.Tr","창원S/S 345kV #2M.Tr 1,2,3차 CB 보통점검","창원S/S 345kV #2M.Tr 1,2,3차 CB 보통점검","2023-04-26 09:30","2023-04-27 18:00","2023-04-26 09:30","2023-04-27 18:00","연속"]
[232,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력등 2개T/L 수평 추락방지장치 설치공사","○ 작업내용 - 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 - 345kV 의령-하동화력#1T/L측 가공지선 항공장애표시구 설치 ○ 작업구간 : - 추락방지장치 : No.1~152 - 항공장애표시구 : No.2,6.7,15,19,61","2023-04-12 07:00","2023-04-28 18:00","취소","취소","연속"]
[233,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력등 2개T/L 수평 추락방지장치 설치공사","○ 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 ○ 작업구간 : No.1~152","2023-04-29 07:00","2023-05-19 18:00","취소","취소","연속"]
[234,"경남","통영","삼천포T/P SEC CB 70710","신고성S/S 345kV SEC GIS 70-71-0 보통점검","신고성S/S 345kV SEC GIS (70-71-0) 보통점검","2023-04-28 09:00","2023-04-28 18:00","2023-04-28 09:00","2023-04-28 18:00","연속"]
[235,"경남","통영","삼천포T/P SEC CB 75760","신고성S/S 345kV SEC GIS 75-76-0 보통점검","신고성S/S 345kV SEC GIS (75-76-0) 보통점검","2023-04-27 09:00","2023-04-27 18:00","2023-04-27 09:00","2023-04-27 18:00","연속"]
[236,"경남","통영","삼천포T/P CB 7A71","신고성S/S 345kV 신고성-고성하이#1T/L GIS 7A71 보통점검","신고성S/S 345kV 신고성-고성하이#1T/L GIS(7A71) 보통점검","2023-04-26 09:00","2023-04-26 18:00","2023-04-26 09:00","2023-04-26 18:00","연속"]
[237,"경남","통영","삼천포T/P CB 7A00","신고성S/S 345kV TIE GIS (7A00) 보통점검","신고성S/S 345kV 신마산#1-고성하이#1 TIE GIS(7A00) 보통점검","2023-04-25 09:00","2023-04-25 18:00","2023-04-25 09:00","2023-04-25 18:00","연속"]
[238,"경남","통영","삼천포T/P CB 7A72","신고성S/S 345kV 신마산-신고성#1T/L GIS 7A72 보통점검","신고성S/S 345kV 신마산-신고성#1T/L GIS (7A72) 보통점검","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[239,"경남","통영","신고성S/S #1 M.Tr","신고성S/S #1M.Tr 보통점검","1. 신고성S/S #1M.Tr 보통점검 2. 신고성S/S #1M.Tr 1차 GIS 보통점검(7172, 7100) 3. 신고성S/S #1M.Tr 2차 GIS 보통점검 4 신고성S/S #1M.Tr 3차 VCB 조작시험 및 3차 PT, 모선 보통점검 5. 신고성S/S #1M.Tr 1,2,3차 LA 보통점검 6. 신고성S/S #1-1,2 Sh.R 보통점검 7. 신고성S/S #1S.Tr DS(M.Tr측/소내 TIE측) 보통점검","2023-04-17 09:00","2023-04-20 18:00","2023-04-17 09:00","2023-04-20 18:00","연속"]
[240,"경남","통영","삼천포T/P CB 7B71","신고성S/S 345kV 신고성-고성하이#2T/L GIS 7B71 보통점검","신고성S/S 345kV 신고성-고성하이#2T/L GIS(7B71) 보통점검","2023-04-14 09:00","2023-04-14 18:00","취소","취소","연속"]
[241,"경남","통영","삼천포T/P CB 7B00","신고성S/S 345kV TIE GIS(7B00) 보통점검","신고성S/S 345kV 창원#2T/L-고성하이#2T/L TIE(7B00) GIS 보통점검","2023-04-06 09:00","2023-04-06 18:00","2023-04-06 09:00","2023-04-06 18:00","연속"]
[242,"경남","통영","삼천포T/P CB 7471","신고성S/S 345kV #G4호기 1차 GIS(7471) 보통점검","신고성S/S 345kV #G4호기 1차 GIS(7471) 보통점검","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[243,"경남","함안","신마산S/S #2 M.Tr","신마산S/S 345kV #2 M.Tr 보통점검 외","신마산S/S 345kV #2 M.Tr 보통점검 외","2023-04-20 09:30","2023-04-21 17:30","2023-04-20 09:30","2023-04-21 17:30","연속"]
[244,"경남","함안","신마산S/S #3 M.Tr","신마산S/S 345kV #3 M.Tr 보통점검 외","신마산S/S 345kV #3 M.Tr 보통점검 외","2023-04-11 09:30","2023-04-12 17:30","2023-04-11 09:30","2023-04-12 17:30","연속"]
[245,"경북",null,"한울N/P #4호기 주변압기 (CB 7A00, 7A72)","한울4호기 제16차 계획예방정비 관련 소내전원 절체시험 * 조작차단기 : 7A00, 7A72","'한울4호기 제16차 계획예방정비 관련 소내전원 절체시험","2023-04-05 10:00","2023-04-05 18:00","2023-04-05 10:00","2023-04-05 18:00","연속"]
[246,"부산울산",null,"고리N/P #3호기 주변압기 (CB 7900, 7972)","고리 3호기 제 27차 계획예방정비 * 조작차단기: 7900, 7972","- 주/보조변압기 및 발전기 점검","2023-03-28 10:00","2023-06-02 17:00","2023-03-28 10:00","2023-06-02 17:00","연속"]
[247,"부산울산",null,"고리N/P #3호기 #1 기동변압기 (CB 7500, 7572)","고리 3호기 계획예방정비관련 기동변압기 #1 점검 * 조작차단기 : 7500, 7572","- 기동변압기 #1 점검 ","2023-04-18 10:00","2023-04-27 17:00","2023-04-18 10:00","2023-04-27 17:00","연속"]
[248,"대구",null,"월성N/P #2 기동용변압기 (CB 7400, 7472)","월성2호기 20차 O/H 중 기동용변압기 점검 및 소내모선 정전작업 * 조작차단기 : CB 7400, 7472","○ 기동용변압기 점검","2023-04-01 09:00","2023-04-09 18:00","2023-04-01 09:00","2023-04-09 18:00","연속"]
[249,"대구",null,"월성N/P #2호기 주변압기 (CB 7300, 7372)","월성2호기 20차 O/H 중 전원절체시험 * 조작차단기 : CB 7300,7372, 7400, 7472","○ 짝수모선휴전작업 ○ 소내전원절체시험 ○ 계통연결전 발전기 링크 조립 및 대기","2023-04-14 00:00","2023-04-22 23:59","2023-04-14 00:00","2023-04-22 23:59","연속"]
[250,"대구",null,"월성N/P #2 기동용변압기 (CB 7400, 7472)","월성2호기 20차 O/H 중 전원절체시험 * 조작차단기 : CB 7300,7372, 7400, 7472","○ 짝수모선휴전작업 ○ 소내전원절체시험","2023-04-14 00:00","2023-04-17 12:00","2023-04-14 00:00","2023-04-17 12:00","연속"]
[251,"경기",null,"신성남S/S #6 M.Tr","345kV GIS 정밀점검","345kV GIS 정밀점검","2023-04-25 09:00","2023-05-03 18:00","2023-04-25 09:00","2023-05-03 18:00","연속"]
[252,"대전세종충남",null,"북당진S/S GS당진복합 #6GT 주변압기 (CB 7800, 7872)","법정검사","법정검사","2023-04-05 09:30","2023-04-05 11:00","2023-04-05 09:30","2023-04-05 11:00","연속"]
[253,"대전세종충남",null,"북당진S/S GS당진복합 #7GT 주변압기 (CB 7700, 7772)","법정검사","법정검사","2023-04-05 13:00","2023-04-05 15:00","2023-04-05 13:00","2023-04-05 15:00","연속"]

{"sheet":"154설비","index":2,"n_rows":674,"n_cols":11,"rows_kept":674,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","광장S/S CB 6100","2023년 성동P/O 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-28 10:00","2023-04-28 18:00","2023-04-28 10:00","2023-04-28 18:00","연속"]
[2,"서울","성동","군자성수 T/L","2023년 성동P/O 변전정비회사 총액공사","군자S/S 154kV GIS 보통점검","2023-04-26 10:00","2023-04-26 17:00","2023-04-26 10:00","2023-04-26 17:00","연속"]
[3,"서울","성동","원남미아#2 T/L","2023년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2023-04-10 09:00","2023-04-12 18:00","2023-04-10 09:00","2023-04-12 18:00","연속"]
[4,"서울","성동","장암방학#2 T/L","2023년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2023-04-04 14:00","2023-04-04 17:00","2023-04-04 14:00","2023-04-04 17:00","연속"]
[5,"서울","성동","방학S/S CB 6100","2023년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2023-04-05 10:00","2023-04-06 17:00","2023-04-05 10:00","2023-04-06 17:00","연속"]
[6,"서울","성동","장암방학#1 T/L","2023년 성동P/O 변전협력회사 총액공사","154kV GIS 조작시험","2023-04-04 10:00","2023-04-04 14:00","2023-04-04 10:00","2023-04-04 14:00","연속"]
[7,"서울","성동","금오상계#1 T/L","2023년 성동P/O 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-20 10:00","2023-04-20 14:00","2023-04-20 10:00","2023-04-20 14:00","연속"]
[8,"서울","성동","금오상계#2 T/L","2023년 성동P/O 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-20 14:00","2023-04-20 18:00","2023-04-20 14:00","2023-04-20 18:00","연속"]
[9,"서울","성동","성동휘경#1 T/L","2023년 성동P/O 변전정비회사 총액공사","154kV GIS 보통점검","2023-04-21 10:00","2023-04-21 17:00","2023-04-21 10:00","2023-04-21 17:00","연속"]
[10,"서울","성동","쌍문수유 T/L","2023년 성동P/O 변전 협력회사 총액공사","154kV GIS 하자점검","2023-04-18 10:00","2023-04-18 17:00","2023-04-18 10:00","2023-04-18 17:00","연속"]
[11,"서울","성동","수유미아 T/L","2023년 성동P/O 변전 협력회사 총액공사","154kV GIS 하자점검","2023-04-19 10:00","2023-04-19 17:00","2023-04-19 10:00","2023-04-19 17:00","연속"]
[12,"서울","성동","신내상봉 T/L","2023~24년 성동전력지사 지중송전설비 위탁정비공사","신내상봉T/L EBG 가스채취밸브 설치공사","2023-04-10 09:00","2023-04-12 13:00","2023-04-10 09:00","2023-04-12 13:00","연속"]
[13,"서울","성동","양주쌍문#2 T/L","2023~24년 성동전력지사 지중송전설비 위탁정비공사","양주쌍문#2T/L EBG 가스채취밸브 설치공사","2023-04-05 13:00","2023-04-07 17:00","2023-04-05 13:00","2023-04-07 17:00","연속"]
[14,"서울","성동","양주쌍문#1 T/L","2023~24년 성동전력지사 지중송전설비 위탁정비공사","양주쌍문#1T/L EBG 가스채취밸브 설치공사","2023-04-03 09:00","2023-04-05 13:00","2023-04-03 09:00","2023-04-05 13:00","연속"]
[15,"서울","성동","용두안암#1 T/L","2023년 성동P/O 변전정비회사 총액공사","154kV GIS 조작시험","2023-04-13 10:00","2023-04-13 14:00","2023-04-13 10:00","2023-04-13 14:00","연속"]
[16,"서울","성동","용두안암#2 T/L","2023년 성동P/O 변전정비회사 총액공사","154kV GIS 조작시험","2023-04-13 14:00","2023-04-13 18:00","2023-04-13 14:00","2023-04-13 18:00","연속"]
[17,"서울","성동","방학창동#2 T/L","2023년 성동P/O 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-12 14:00","2023-04-12 18:00","2023-04-12 14:00","2023-04-12 18:00","연속"]
[18,"서울","성동","창동쌍문#1 T/L","2023년 성동P/O 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-11 10:00","2023-04-11 14:00","2023-04-11 10:00","2023-04-11 14:00","연속"]
[19,"서울","성동","창동쌍문#2 T/L","2023년 성동P/O 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-11 14:00","2023-04-11 18:00","2023-04-11 14:00","2023-04-11 18:00","연속"]
[20,"서울","성동","방학창동#1 T/L","2023년 성동P/O 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-12 10:00","2023-04-12 14:00","2023-04-12 10:00","2023-04-12 14:00","연속"]
[21,"서울","성동","창동돈암 T/L","2023년 성동P/O 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-18 10:00","2023-04-18 18:00","2023-04-18 10:00","2023-04-18 18:00","연속"]
[22,"서울","성동","화양광장 T/L","2023년 성동P/O 변전 협력회사 총액공사","154kV GIS 조작시험","2023-04-13 10:00","2023-04-13 17:00","2023-04-13 10:00","2023-04-13 17:00","연속"]
[23,"서울","성동","군자화양#2 T/L","2023년 성동P/O 변전 협력회사 총액공사","154kV GIS 보통점검","2023-04-11 10:00","2023-04-11 17:00","2023-04-11 10:00","2023-04-11 17:00","연속"]
[24,"서울","성동","화양상봉#2 T/L","2023년 성동P/O 변전 협력회사 총액공사","154kV GIS 조작시험","2023-04-12 14:00","2023-04-12 18:00","2023-04-12 14:00","2023-04-12 18:00","연속"]
[25,"서울","성동","군자화양#1 T/L","2023년 성동P/O 변전 협력회사 총액공사","154kV GIS 보통점검","2023-04-10 10:00","2023-04-10 17:00","2023-04-10 10:00","2023-04-10 17:00","연속"]
[26,"서울","중부","중부당인리#1 T/L","23년 GIS 정밀점검","GIS 정밀점검","2023-04-04 10:00","2023-04-05 18:00","2023-04-04 10:00","2023-04-05 18:00","연속"]
[27,"서울","중부","중부당인리#2 T/L","23년 GIS 정밀점검","GIS 정밀점검","2023-04-06 10:00","2023-04-07 18:00","2023-04-06 10:00","2023-04-07 18:00","연속"]
[28,"서울","중부","원흥상암 T/L","23년 GIS 정밀점검","GIS 정밀점검","2023-04-11 10:00","2023-04-12 18:00","2023-04-11 10:00","2023-04-12 18:00","연속"]
[29,"서울","중부","능곡상암#2 T/L","세니온제 154kV 송전선로보호반 성능개선","○ F/W 업데이트 및 연동시험","2023-04-05 14:00","2023-04-05 18:00","취소","취소","연속"]
[30,"서울","중부","능곡상암#1 T/L","세니온제 154kV 송전선로보호반 성능개선","○ F/W 업데이트 및 연동시험","2023-04-05 10:00","2023-04-05 14:00","취소","취소","연속"]
[31,"서울","중부","수색상암 T/L","23 중부P/O 총액공사","GCB 보통점검","2023-04-14 10:00","2023-04-14 18:00","2023-04-14 10:00","2023-04-14 18:00","연속"]
[32,"서울","중부","원흥수색#1 T/L","23 중부P/O 총액공사","LS ,PT,LA 보통점검","2023-04-27 10:00","2023-04-27 18:00","2023-04-27 10:00","2023-04-27 18:00","연속"]
[33,"서울","중부","수색S/S CB 6100","23 중부P/O 총액공사","차단기 조작시험","2023-04-27 10:00","2023-04-27 18:00","2023-04-27 10:00","2023-04-27 18:00","연속"]
[34,"서울","중부","수색S/S #2 BUS","23 중부P/O 총액공사","PT, 피뢰기 보통점검","2023-04-27 14:00","2023-04-27 18:00","2023-04-27 14:00","2023-04-27 18:00","연속"]
[35,"서울","중부","수색S/S #1 BUS","23 중부P/O 총액공사","PT, 피뢰기 보통점검","2023-04-27 10:00","2023-04-27 14:00","2023-04-27 10:00","2023-04-27 14:00","연속"]
[36,"서울","직할","서대문세종로 T/L","23년 서울본부 직할 170kV GIS 정밀점검공사","서대문S/S 170kV 서대문세종로T/L GIS 정밀점검공사","2023-04-24 09:00","2023-04-26 18:00","2023-04-24 09:00","2023-04-26 18:00","연속"]
[37,"서울","직할","순화동빙고 T/L","23년 직할 변전협력회사 총액공사","무부하 가압관련 안전이격휴전","2023-04-03 09:00","2023-04-06 18:00","2023-04-12 09:00","2023-04-19 18:00","연속"]
[38,"서울","직할","종로서소문 T/L","23년 직할 변전협력회사 총액공사","154kV GIS 보통점검","2023-04-12 09:00","2023-04-12 18:00","2023-04-12 09:00","2023-04-12 18:00","연속"]
[39,"서울","직할","중앙서소문 T/L","23년 직할 변전협력회사 총액공사","154kV GIS 보통점검","2023-04-11 09:00","2023-04-11 18:00","2023-04-11 09:00","2023-04-11 18:00","연속"]
[40,"남서울","강남","사당신림 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 : 사당-신림T/L GIS","2023-04-24 09:00","2023-04-25 18:00","2023-04-24 09:00","2023-04-25 18:00","연속"]
[41,"남서울","강남","사당봉천#2 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 : 사당-봉천#2T/L GIS(DS 포함) - 무부하가압 : 신양재-사당#1T/L","2023-04-26 09:00","2023-04-28 18:00","2023-04-26 09:00","2023-04-28 18:00","연속"]
[42,"남서울","강남","사당봉천#1 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 : 6100, 사당-봉천#1 GIS","2023-04-19 09:00","2023-04-21 18:00","2023-04-19 09:00","2023-04-21 18:00","연속"]
[43,"남서울","동서울","도곡개포 T/L","154kV 개포-신양재,도곡T/L 지장이설공사","양재대로 구조개선 사업(지하차도 건설)에 따른 전력설비 이설 □ 사업구간 : 154kV 도곡-개포T/L J/B#1 ~ M/H#2 □ 주요공정 - 케이블 철거 : XLPE 2,000㎟, 1C-0.32km(기설전력구+관로) - 케이블 설치 : XLPE 2,000㎟, 1C-0.35km(신설전력구+관로) - 케이블 접속 : 2개소","2023-04-10 07:00","2023-05-05 18:00","취소","취소","연속"]
[44,"남서울","동서울","동서울S/S SEC CB 63640G","동서울#2S/S 170kV 63-64 BUS GIS 초기점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-18 09:00","2023-04-18 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[45,"남서울","동서울","동서울S/S CB 6400G","동서울#2S/S 170kV 6400 BUS TIE GIS 초기점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-11 14:00","2023-04-11 18:00","2023-04-11 14:00","2023-04-11 18:00","연속"]
[46,"남서울","동서울","동서울S/S CB 6500G","동서울#2S/S 170kV 6500 BUS TIE GIS 하자점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-17 09:00","2023-04-17 14:00","2023-04-17 09:00","2023-04-17 14:00","연속"]
[47,"남서울","동서울","동서울S/S SEC CB 68690G","동서울#2S/S 170kV 68-69 BUS GIS 초기점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-18 09:00","2023-04-18 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[48,"남서울","동서울","동서울S/S CB 6300G","동서울S/S 170kV 6300 BUS TIE GIS 하자점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-11 09:00","2023-04-11 14:00","2023-04-11 09:00","2023-04-11 14:00","연속"]
[49,"남서울","동서울","동서울송파#1 T/L","동서울S/S 동서울-송파#1T/L 하자점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-03 07:00","2023-04-03 18:00","2023-04-03 07:00","2023-04-03 18:00","연속"]
[50,"남서울","동서울","동서울송파#2 T/L","동서울S/S 동서울-송파#2T/L 하자점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-04 07:00","2023-04-04 18:00","2023-04-04 07:00","2023-04-04 18:00","연속"]
[51,"남서울","동서울","동서울S/S SEC CB 62630G","동서울S/S 170kV 62-66 BUS GIS 하자점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-14 09:00","2023-04-14 14:00","2023-04-14 09:00","2023-04-14 14:00","연속"]
[52,"남서울","동서울","동서울S/S SEC CB 67680G","동서울S/S 170kV 67-68 BUS GIS 하자점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-14 14:00","2023-04-14 18:00","2023-04-14 14:00","2023-04-14 18:00","연속"]
[53,"남서울","동서울","논현선릉#2 T/L","선릉S/S 논현-선릉#2T/L 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-05 09:00","2023-04-05 18:00","취소","취소","연속"]
[54,"남서울","동서울","탄천선릉#2 T/L","선릉S/S 탄천-선릉#2T/L 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-04 09:00","2023-04-04 18:00","취소","취소","연속"]
[55,"남서울","동서울","탄천선릉#1 T/L","선릉S/S 탄천-선릉#1T/L 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-03 09:00","2023-04-03 18:00","취소","취소","연속"]
[56,"남서울","동서울","수서S/S #2 BUS","동서울전력지사 170kV GIS 정밀점검","#4M.Tr 1차 GIS 정밀점검","2023-04-06 09:00","2023-04-07 12:00","2023-04-06 09:00","2023-04-07 12:00","연속"]
[57,"남서울","동서울","수서S/S CB 6100","수서S/S 170kV GIS 정밀점검","동서울P/O 170kV GIS 정밀점검 - DS부 포함 점검","2023-04-06 09:00","2023-04-08 18:00","2023-04-06 09:00","2023-04-08 18:00","연속"]
[58,"남서울","동서울","수서S/S #2 BUS","수서S/S 170kV GIS 정밀점검","동서울P/O 170kV GIS 정밀점검 - DS부 포함 점검","2023-04-10 09:00","2023-04-12 12:00","2023-04-10 09:00","2023-04-12 12:00","연속"]
[59,"남서울","동서울","산성수서#1 T/L","동서울전력지사 170kV GIS 정밀점검","정밀점검대상 : 수서S/S #4M.Tr 1차 GIS - 무부하 가압용","2023-04-07 12:00","2023-04-07 14:00","2023-04-07 12:00","2023-04-07 14:00","연속"]
[60,"남서울","동서울","수서S/S #1 BUS","동서울전력지사 170kV GIS 정밀점검","#4M.Tr 1차 GIS 정밀점검 (1BUS측)","2023-04-07 14:00","2023-04-08 18:00","2023-04-07 14:00","2023-04-08 18:00","연속"]
[61,"남서울","동서울","산성수서#1 T/L","동서울전력지사 170kV GIS 정밀점검","정밀점검대상 : 수서S/S #4M.Tr 1차 GIS - 무부하 가압용","2023-04-08 12:00","2023-04-08 14:00","2023-04-08 12:00","2023-04-08 14:00","연속"]
[62,"남서울","동서울","수서S/S CB 6100","수서S/S 170kV GIS 정밀점검","동서울P/O 170kV GIS 정밀점검 - DS부 포함 점검","2023-04-10 09:00","2023-04-14 18:00","2023-04-10 09:00","2023-04-14 18:00","연속"]
[63,"남서울","동서울","수서S/S #1 BUS","수서S/S 170kV GIS 정밀점검","동서울P/O 170kV GIS 정밀점검 - DS부 포함 점검","2023-04-12 12:00","2023-04-14 18:00","2023-04-12 12:00","2023-04-14 18:00","연속"]
[64,"남서울","동서울","수서S/S CB 6100","수서S/S 170kV GIS 정밀점검","동서울P/O 170kV GIS 정밀점검 - DS부 포함 점검","2023-04-17 09:00","2023-04-21 18:00","2023-04-17 09:00","2023-04-21 18:00","연속"]
[65,"남서울","동서울","산성수서#2 T/L","수서S/S 170kV 산성-수서#2T/L GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 공사","2023-04-17 09:00","2023-04-21 18:00","2023-04-17 09:00","2023-04-21 18:00","연속"]
[66,"남서울","동서울","수서S/S #2 BUS","수서S/S 170kV GIS 정밀점검","동서울P/O 170kV GIS 정밀점검 - DS부 포함 점검","2023-04-17 09:00","2023-04-19 12:00","2023-04-17 09:00","2023-04-19 12:00","연속"]
[67,"남서울","동서울","산성수서#1 T/L","수서S/S 170kV 산성-수서#1T/L GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 공사","2023-04-10 09:00","2023-04-14 18:00","2023-04-10 09:00","2023-04-14 18:00","연속"]
[68,"남서울","동서울","가락수서#1 T/L","수서S/S 170kV 가락-수서#1T/L GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 공사","2023-04-24 09:00","2023-04-28 18:00","2023-04-24 09:00","2023-04-28 18:00","연속"]
[69,"남서울","동서울","수서S/S #1 BUS","수서S/S 170kV GIS 정밀점검","동서울P/O 170kV GIS 정밀점검 - DS부 포함 점검","2023-04-19 12:00","2023-04-21 18:00","2023-04-19 12:00","2023-04-21 18:00","연속"]
[70,"남서울","동서울","수서S/S #1 BUS","수서S/S 170kV GIS 정밀점검","동서울P/O 170kV GIS 정밀점검 - DS부 포함 점검","2023-04-26 12:00","2023-04-28 18:00","2023-04-26 12:00","2023-04-28 18:00","연속"]
[71,"남서울","동서울","수서S/S CB 6100","수서S/S 170kV GIS 정밀점검","동서울P/O 170kV GIS 정밀점검 - DS부 포함 점검","2023-04-24 09:00","2023-04-28 18:00","2023-04-24 09:00","2023-04-28 18:00","연속"]
[72,"남서울","동서울","수서S/S #2 BUS","수서S/S 170kV GIS 정밀점검","동서울P/O 170kV GIS 정밀점검 - DS부 포함 점검","2023-04-24 09:00","2023-04-26 12:00","2023-04-24 09:00","2023-04-26 12:00","연속"]
[73,"남서울","동서울","신장S/S #1 BUS","154kV 강일S/S 건설관련 GIS 설치공사","- 154kV GIS 2CCT 설치 - 기타 부대공사 1식","2023-04-24 09:00","2023-04-29 15:00","취소","취소","연속"]
[74,"남서울","동서울","동서울신장#1 T/L","154kV 동서울-신장 지중T/L 선종교체공사","(신설)XLPE 2500SQ 2C-0.3km (철거)XLPE 12000SQ 2C(D)-0.3km","2023-04-24 09:00","2023-05-23 18:00","취소","취소","연속"]
[75,"남서울","동서울","동서울신장#2 T/L","154kV 강일S/S 건설관련 GIS 설치공사","- 154kV GIS 2CCT 설치 - 기타 부대공사 1식","2023-04-28 09:00","2023-04-29 15:00","취소","취소","연속"]
[76,"남서울","동서울","송파잠실#1 T/L","잠실S/S 170kV 송파-잠실#1T/L 조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-21 09:00","2023-04-21 14:00","2023-04-21 09:00","2023-04-21 14:00","연속"]
[77,"남서울","동서울","잠실탄천#2 T/L","잠실S/S 170kV 잠실-탄천#2T/L 조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-20 14:00","2023-04-20 18:00","2023-04-20 14:00","2023-04-20 18:00","연속"]
[78,"남서울","동서울","잠실탄천#1 T/L","잠실S/S 170kV 잠실-탄천#1T/L 조작시험","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-04-20 09:00","2023-04-20 14:00","2023-04-20 09:00","2023-04-20 14:00","연속"]
[79,"남서울","동서울","송파잠실#4 T/L","잠실S/S 송파-잠실#4T/L 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 공사","2023-04-03 09:00","2023-04-05 18:00","2023-04-03 09:00","2023-04-05 18:00","연속"]
[80,"남서울","영등포","가양등촌#1 T/L","‘23∼’24년 영등포전력지사 지중송전 위탁전문회사 총액공사","○154kV 가양-등촌#1T/L OF케이블 절연유 채유","2023-04-17 09:00","2023-04-17 18:00","2023-04-17 09:00","2023-04-17 18:00","연속"]
[81,"남서울","영등포","가양등촌#2 T/L","‘23∼’24년 영등포전력지사 지중송전 위탁전문회사 총액공사","○154kV 가양-등촌#2T/L OF케이블 절연유 채유","2023-04-18 09:00","2023-04-18 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[82,"남서울","영등포","마곡가양#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-19 09:00","2023-04-19 14:00","취소","취소","연속"]
[83,"남서울","영등포","마곡가양#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-19 14:00","2023-04-19 18:00","취소","취소","연속"]
[84,"남서울","영등포","신광명광명#1 T/L","광명S/S 154kV 장기사용 GIS 교체공사","4차분(광-구#1T/L, #3M.Tr 1차, #1·2BUS SEC GIS) 철거 및 설치 - 인근설비 감압","2023-04-03 09:00","2023-04-06 18:00","2023-04-03 09:00","2023-04-06 18:00","연속"]
[85,"남서울","영등포","광명S/S #2 BUS","광명S/S 154kV 장기사용 GIS 교체공사","4차분(광-구#1T/L, #2M.Tr 1차, #1·2BUS SEC GIS) 철거 및 설치 - #2BUS 구형BUS 철거, 신형BUS 설치","2023-04-03 09:00","2023-04-12 18:00","2023-04-03 09:00","2023-04-12 18:00","연속"]
[86,"남서울","영등포","광명S/S #2 BUS","광명S/S 154kV 장기사용 GIS 교체공사","4차분(광-구#1T/L, #2M.Tr 1차, #1·2BUS SEC GIS) 철거 및 설치 - #2BUS DS 설치, 준공시험","2023-04-29 18:00","2023-05-19 18:00","2023-04-29 18:00","2023-05-19 18:00","연속"]
[87,"남서울","영등포","신광명광명#1 T/L","광명S/S 154kV 장기사용 GIS 교체공사","4차분(광-구#1T/L, #3M.Tr 1차, #1·2BUS SEC GIS) 철거 및 설치 - 인근설비 감압","2023-04-12 18:00","2023-04-17 18:00","2023-04-12 18:00","2023-04-17 18:00","연속"]
[88,"남서울","영등포","광명S/S #1 BUS","광명S/S 154kV 장기사용 GIS 교체공사","4차분(광-구#1T/L, #2M.Tr 1차, #1·2BUS SEC GIS) 철거 및 설치 - #1BUS 구형BUS 철거, 신형BUS, CB, 인출모선 설치","2023-04-12 18:00","2023-04-29 18:00","2023-04-12 18:00","2023-04-29 18:00","연속"]
[89,"남서울","영등포","구공독산 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검, 조작시험","2023-04-21 09:00","2023-04-21 18:00","2023-04-21 09:00","2023-04-21 18:00","연속"]
[90,"남서울","영등포","독산대방#1 T/L","대방-독산T/L 케이블 위치조정공사","대방-독산T/L 이설공사 중 토목(전력구)공사를 위한 케이블 위치변경(약 70m)","2023-04-10 09:00","2023-04-14 18:00","2023-04-10 09:00","2023-04-14 18:00","연속"]
[91,"남서울","영등포","독산대방#2 T/L","2023년 영등포전력지사 170kV GIS 정밀점검공사","-CB 동작시간 측정 -주회로 접촉저항 측정 -주회로, 보조회로, 제어회로 절연저항 측정 -SF6가스 수분 및 SO2 측정 -CT 포화시험 -경보시험 및 조작시험","2023-04-24 09:00","2023-04-25 18:00","2023-04-24 09:00","2023-04-25 18:00","연속"]
[92,"남서울","영등포","대림독산 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-18 09:00","2023-04-18 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[93,"남서울","영등포","신정목동#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-29 14:00","2023-04-29 18:00","2023-04-29 14:00","2023-04-29 18:00","연속"]
[94,"남서울","영등포","신정목동#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-29 09:00","2023-04-29 14:00","2023-04-29 09:00","2023-04-29 14:00","연속"]
[95,"남서울","영등포","시흥독산#1 T/L","2023년 영등포전력지사 170kV GIS 정밀점검공사","기아T/L 무부하가압용","2023-04-30 11:00","2023-04-30 13:30","2023-04-30 11:00","2023-04-30 13:30","연속"]
[96,"남서울","영등포","신광명시흥#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2023-04-07 09:00","2023-04-07 14:00","2023-04-07 09:00","2023-04-07 14:00","연속"]
[97,"남서울","영등포","신광명시흥#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2023-04-07 14:00","2023-04-07 18:00","2023-04-07 14:00","2023-04-07 18:00","연속"]
[98,"남서울","영등포","온수소래 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-06 09:00","2023-04-06 18:00","취소","취소","연속"]
[99,"남서울","영등포","신광명천왕#3 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2023-04-04 09:00","2023-04-04 18:00","2023-04-04 09:00","2023-04-04 18:00","연속"]
[100,"남서울","영등포","천왕S/S #1 BUS","2023년 영등포전력지사 170kV GIS 정밀점검공사","BUS-TIE 무부하가압용","2023-04-17 09:00","2023-04-18 18:00","2023-04-17 09:00","2023-04-18 18:00","연속"]
[101,"남서울","영등포","천왕오류#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2023-04-14 09:00","2023-04-14 18:00","2023-04-14 09:00","2023-04-14 18:00","연속"]
[102,"남서울","영등포","천왕오류#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2023-04-13 09:00","2023-04-13 18:00","2023-04-13 09:00","2023-04-13 18:00","연속"]
[103,"남서울","영등포","신광명천왕#2 T/L","2023년 영등포전력지사 170kV GIS 정밀점검공사","-CB 동작시간 측정 -주회로 접촉저항 측정 -주회로, 보조회로, 제어회로 절연저항 측정 -SF6가스 수분 및 SO2 측정 -CT 포화시험 -경보시험 및 조작시험","2023-04-12 09:00","2023-04-13 18:00","2023-04-12 09:00","2023-04-13 18:00","연속"]
[104,"남서울","영등포","천왕구로#2 T/L","‘23∼’24년 영등포전력지사 지중송전 위탁전문회사 총액공사","○154kV 천왕-구로#2T/L 절연유 채유밸브 설치 및 채유","2023-04-11 09:00","2023-04-12 18:00","2023-04-11 09:00","2023-04-12 18:00","연속"]
[105,"남서울","영등포","신광명천왕#1 T/L","2023년 영등포전력지사 170kV GIS 정밀점검공사","-CB 동작시간 측정 -주회로 접촉저항 측정 -주회로, 보조회로, 제어회로 절연저항 측정 -SF6가스 수분 및 SO2 측정 -CT 포화시험 -경보시험 및 조작시험","2023-04-10 09:00","2023-04-11 18:00","2023-04-10 09:00","2023-04-11 18:00","연속"]
[106,"남서울","영등포","천왕S/S #2 BUS","2023년 영등포전력지사 170kV GIS 정밀점검공사","#2M.Tr 무부하가압용","2023-04-06 15:00","2023-04-06 18:00","2023-04-06 15:00","2023-04-06 18:00","연속"]
[107,"남서울","영등포","천왕S/S #1 BUS","2023년 영등포전력지사 170kV GIS 정밀점검공사","#1M.Tr 무부하가압용","2023-04-04 15:00","2023-04-04 18:00","2023-04-04 15:00","2023-04-04 18:00","연속"]
[108,"남서울","영등포","화곡마곡#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-15 14:00","2023-04-15 18:00","2023-04-15 14:00","2023-04-15 18:00","연속"]
[109,"남서울","영등포","중동화곡#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-22 09:00","2023-04-22 14:00","2023-04-22 09:00","2023-04-22 14:00","연속"]
[110,"남서울","영등포","중동화곡#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-22 14:00","2023-04-22 18:00","취소","취소","연속"]
[111,"남서울","영등포","화곡마곡#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-04-15 09:00","2023-04-15 14:00","2023-04-15 09:00","2023-04-15 14:00","연속"]
[112,"남서울","직할","여의노량진 T/L","154kV 여의-노량진T/L J/B#3 접속함 리콜","154kV 여의-노량진T/L Triplex 접속 J/B#3 / 자발적 리콜(해체 후 재접속 : 대한전선)","2023-04-10 09:00","2023-04-17 18:00","2023-04-10 09:00","2023-04-17 18:00","연속"]
[113,"남서울","직할","봉천신길#1 T/L","OF케이블 절연유 채유밸브 설치","OF케이블 절연유 채유밸브 설치(SJ/B#17 등 3개소)","2023-04-06 09:00","2023-04-07 18:00","2023-04-06 09:00","2023-04-07 18:00","연속"]
[114,"남서울","직할","봉천신길#2 T/L","OF케이블 절연유 채유밸브 설치","OF케이블 절연유 채유밸브 설치(SJ/B#17 2개소)","2023-04-17 09:00","2023-04-18 18:00","2023-04-17 09:00","2023-04-18 18:00","연속"]
[115,"남서울","직할","신문래목동#1 T/L","170kV GIS 정밀점검 무부하가압(#65BUS)","170kV GIS 정밀점검 무부하가압(#65BUS) - 신문래S/S 154kV #62M.Tr 1차 GIS 정밀점검","2023-04-14 16:00","2023-04-14 18:00","2023-04-14 16:00","2023-04-14 18:00","연속"]
[116,"남서울","직할","신문래목동#1 T/L","170kV GIS 정밀점검 무부하가압(#65BUS)","170kV GIS 정밀점검 무부하가압(#65BUS) - 신문래S/S 154kV #61M.Tr 1차 GIS 정밀점검","2023-04-11 16:00","2023-04-11 18:00","2023-04-11 16:00","2023-04-11 18:00","연속"]
[117,"남서울","직할","신문래여의 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검 - 신문래S/S 154kV 신문래-여의T/L GIS","2023-04-06 09:00","2023-04-07 18:00","2023-04-06 09:00","2023-04-07 18:00","연속"]
[118,"남서울","직할","신문래노량진 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검 - 신문래S/S 154kV 신문래-노량진 T/L GIS","2023-04-03 09:00","2023-04-05 18:00","2023-04-03 09:00","2023-04-05 18:00","연속"]
[119,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검 무부하가압(#61BUS)","170kV GIS 정밀점검 무부하가압(#61BUS) - 신문래S/S 154kV #64M.Tr 1차 GIS 정밀점검","2023-04-20 16:00","2023-04-20 18:00","2023-04-20 16:00","2023-04-20 18:00","연속"]
[120,"남서울","직할","신문래양평#1 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검 - 신문래S/S 154kV 신문래-양평#1T/L GIS","2023-04-24 09:00","2023-04-25 18:00","2023-04-24 09:00","2023-04-25 18:00","연속"]
[121,"남서울","직할","신문래양평#2 T/L","170kV GIS 정밀점검","170kV GIS 정밀점검 - 신문래S/S 154kV 신문래-양평#2T/L GIS","2023-04-26 09:00","2023-04-27 18:00","2023-04-26 09:00","2023-04-27 18:00","연속"]
[122,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검 무부하가압(#61BUS)","170kV GIS 정밀점검 무부하가압(#61BUS) - 신문래S/S 154kV #63M.Tr 1차 GIS 정밀점검","2023-04-18 16:00","2023-04-18 18:00","2023-04-18 16:00","2023-04-18 18:00","연속"]
[123,"인천","김포","김포장기#1 T/L","154kV 김포-장기T/L(감정IC) 철거공사","ㅇ 공사구간 : M/H#4~#5 ㅇ 케이블 선종 및 회신 : XLPE 2,000㎟ x 2C(0.315km)","2023-05-07 08:00","2023-06-09 18:00","2023-05-07 08:00","2023-06-09 18:00","연속"]
[124,"인천","김포","김포장기#2 T/L","154kV 김포-장기T/L(감정IC) 철거공사","ㅇ 공사구간 : M/H#4~#5 ㅇ 케이블 선종 및 회신 : XLPE 2,000㎟ x 2C(0.315km)","2023-04-03 08:00","2023-05-06 18:00","2023-04-03 08:00","2023-05-06 18:00","연속"]
[125,"인천","김포","신김포S/S #61 BUS","신김포S/S 345kV #3M.Tr 설치공사(전문)","362kV GIS x 1CB 증설(#3M.Tr 1차) 345kV #3M.Tr 무부하가압 시험팀 시험","2023-04-29 14:00","2023-04-29 18:00","취소","취소","연속"]
[126,"인천","김포","신김포S/S CB 6200","신김포S/S 345kV #3M.Tr 설치공사(전문)","362kV GIS x 1CB 증설(#3M.Tr 1차) 345kV #3M.Tr 무부하가압 시험팀 시험","2023-04-28 09:00","2023-04-29 18:00","취소","취소","연속"]
[127,"인천","김포","신김포S/S #66 BUS","신김포S/S 345kV #3M.Tr 설치공사(전문)","362kV GIS x 1CB 증설(#3M.Tr 1차) 345kV #3M.Tr 무부하가압","2023-04-28 09:00","2023-04-29 14:00","취소","취소","연속"]
[128,"인천","부평","영종중산 T/L","154kV 을왕분기 지중T/L 건설공사","ㅇ 공사목적 : 신설 154kV 을왕S/S 전원공급 ㅇ 공사규모 : 154kV XLPE 2,000㎟, 2회선, 15km - 기설 154kV 영종-중산T/L π분기 * 휴전작업 완료후 복귀조작절차는 신설 을왕S/S 최초가압 관련내용에 따름","2023-04-26 09:00","2023-06-23 18:00","2023-04-19 09:00","2023-06-16 18:00","연속"]
[129,"인천","시흥","신시흥북시화#2 T/L","북시화S/S 신시흥북시화#2 T/L GIS 보통점검","북시화S/S 신시흥북시화#2 T/L GIS 보통점검 - LA, CVT 보통점검","2023-04-18 09:00","2023-04-18 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[130,"인천","시흥","북시화서시화#1 T/L","북시화S/S 북시화서시화#1 T/L GIS 초기점검","북시화S/S 북시화서시화#1 T/L GIS 초기점검","2023-04-03 09:00","2023-04-03 18:00","2023-04-17 14:00","2023-04-17 18:00","연속"]
[131,"인천","시흥","신시흥북시화#1 T/L","북시화S/S 신시흥북시화#1 T/L GIS 보통점검","북시화S/S 신시흥북시화#1 T/L GIS 보통점검 - LA, CVT 보통점검","2023-04-17 09:00","2023-04-17 18:00","2023-04-17 09:00","2023-04-17 14:00","연속"]
[132,"인천","시흥","서안양소래 T/L","가공송전 협력회사 총액공사(154kV 서소T/L 추락방지)","송전철탑 추락방지장치 설치 - 대상 : No.48~53(6기)","2023-04-07 07:00","2023-04-09 18:00","2023-04-07 07:00","2023-04-09 18:00","매일"]
[133,"인천","시흥","서서울#2소래 T/L","가공송전 협력회사 총액공사(154kV 서소T/L 추락방지)","송전철탑 추락방지장치 설치 - 대상 : No.48~53(6기)","2023-04-03 07:00","2023-04-06 18:00","2023-04-03 07:00","2023-04-06 18:00","매일"]
[134,"인천","시흥","온수소래 T/L","소래S/S 154kV 온수소래 T/L GIS 보통점검","소래S/S 154kV 온수소래 T/L GIS 보통점검","2023-04-20 09:00","2023-04-20 18:00","2023-04-21 09:00","2023-04-21 18:00","연속"]
[135,"인천","직할","부흥부개#2 T/L","부흥S/S 부흥부개#2T/L GIS 정밀점검","부흥S/S 부흥부개#2T/L GIS 정밀점검","2023-04-22 09:30","2023-04-23 18:00","2023-04-22 09:30","2023-04-23 18:00","연속"]
[136,"인천","직할","부흥부개#1 T/L","부흥S/S 부흥부개#1T/L GIS 정밀점검","부흥S/S 부흥부개#1T/L GIS 정밀점검","2023-04-15 09:30","2023-04-16 18:00","2023-04-15 09:30","2023-04-16 18:00","연속"]
[137,"인천","직할","갈산부흥#3 T/L","부흥S/S 6100 B/T GIS 정밀점검 무부하가압용","부흥S/S 6100 B/T GIS 정밀점검 무부하가압용","2023-04-14 14:00","2023-04-14 18:00","2023-04-14 14:00","2023-04-14 18:00","연속"]
[138,"인천","직할","갈산부흥#1 T/L","부흥S/S 갈산부흥#1T/L GIS 정밀점검","부흥S/S 갈산부흥#1T/L GIS 정밀점검","2023-04-05 09:30","2023-04-07 18:00","2023-04-05 09:30","2023-04-07 18:00","연속"]
[139,"인천","직할","갈산부흥#2 T/L","부흥S/S 갈산부흥#2T/L GIS 정밀점검","부흥S/S 갈산부흥#2T/L GIS 정밀점검","2023-04-08 09:30","2023-04-09 18:00","2023-04-08 09:30","2023-04-09 18:00","연속"]
[140,"인천","직할","중동S/S 부천복합 S/T CB 6413","중동s/s 170kV #S/T GIS 보통점검, ES PAD 보수","중동s/s 170kV #S/T GIS 보통점검, ES PAD CRACK부 보수","2023-04-10 09:30","2023-04-13 18:00","2023-04-10 09:30","2023-04-13 18:00","연속"]
[141,"인천","직할","중동S/S 부천복합 #1G/T CB 6113","중동s/s 170kV #1G/T GIS 보통점검","중동s/s 170kV #1G/T GIS 보통점검","2023-04-14 09:30","2023-04-14 18:00","2023-04-14 09:30","2023-04-14 18:00","연속"]
[142,"인천","직할","중동S/S 부천복합 #2G/T CB 6213","중동s/s 170kV #2G/T GIS 보통점검","중동s/s 170kV #2G/T GIS 보통점검","2023-04-10 09:30","2023-04-10 18:00","2023-04-10 09:30","2023-04-10 18:00","연속"]
[143,"인천","직할","중동화곡#2 T/L","중동s/s 중동화곡#2T/L GIS 보통점검","중동s/s 중동화곡#2T/L GIS 보통점검","2023-04-01 09:30","2023-04-01 18:00","2023-04-01 09:30","2023-04-01 18:00","연속"]
[144,"인천","김포","양촌S/S 김포열병합#1 T/L CB 677","양촌S/S 154kV 김포열병합#1T/L GIS 초기점검","양촌S/S 154kV 김포열병합#1T/L GIS 초기점검","2023-04-17 10:00","2023-04-17 18:00","2023-04-17 10:00","2023-04-17 18:00","연속"]
[145,"인천","김포","양촌S/S 김포열병합#2 T/L CB 697","양촌S/S 154kV 김포열병합#1T/L GIS 초기점검","양촌S/S 154kV 김포열병합#1T/L GIS 초기점검","2023-04-18 10:00","2023-04-18 18:00","2023-04-18 10:00","2023-04-18 18:00","연속"]
[146,"인천","김포","양촌양곡#1 T/L","양곡S/S #5, 6 M.Tr 증설공사 안전이격확보","양곡S/S #5, 6 M.Tr 증설공사 안전이격확보","2023-04-18 10:00","2023-04-18 18:00","2023-04-30 09:00","2023-04-30 18:00","연속"]
[147,"경기북부","고양","양주금촌#2 T/L","22~23년 고양전력 가공송전협력회사 총액공사","피뢰기설치 병가","2023-04-17 07:00","2023-04-17 18:00","2023-04-17 07:00","2023-04-17 18:00","연속"]
[148,"경기북부","고양","신덕은금촌#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","피뢰기 설치","2023-04-12 07:00","2023-04-12 18:00","2023-04-12 07:00","2023-04-12 18:00","연속"]
[149,"경기북부","고양","신덕은금촌#2 T/L","22~23년 고양전력 가공송전협력회사 총액공사","피뢰기 설치","2023-04-13 12:00","2023-04-14 18:00","2023-04-13 12:00","2023-04-14 18:00","연속"]
[150,"경기북부","고양","신덕은금촌#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2023-04-03 07:00","2023-04-03 18:00","2023-04-03 07:00","2023-04-03 18:00","연속"]
[151,"경기북부","고양","운정덕이#2 T/L","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-04-11 09:00","2023-04-11 18:00","2023-04-11 09:00","2023-04-11 18:00","연속"]
[152,"경기북부","고양","운정덕이#1 T/L","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-04-10 09:00","2023-04-10 18:00","2023-04-10 09:00","2023-04-10 18:00","연속"]
[153,"경기북부","고양","신덕은문산#2 T/L","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-04-20 09:00","2023-04-20 18:00","2023-04-20 09:00","2023-04-20 18:00","연속"]
[154,"경기북부","고양","신덕은문산#1 T/L","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-04-19 09:00","2023-04-19 18:00","2023-04-19 09:00","2023-04-19 18:00","연속"]
[155,"경기북부","고양","신파주송포#2 T/L","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-04-25 09:00","2023-04-25 18:00","2023-04-25 09:00","2023-04-25 18:00","연속"]
[156,"경기북부","고양","신파주송포#1 T/L","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[157,"경기북부","고양","신파주원흥#2 T/L","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-04-13 09:00","2023-04-13 18:00","2023-04-13 09:00","2023-04-13 18:00","연속"]
[158,"경기북부","고양","신파주문발#1 T/L","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-04-04 09:00","2023-04-04 18:00","2023-04-04 09:00","2023-04-04 18:00","연속"]
[159,"경기북부","고양","신파주원흥#1 T/L","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-04-12 09:00","2023-04-12 18:00","2023-04-12 09:00","2023-04-12 18:00","연속"]
[160,"경기북부","고양","일산S/S SEC CB 60610","22-23년 고양전력지사 변전협력회사 총액공사","일산S/S 60-61 BUS-SEC GIS 차단기 조작시험","2023-04-04 09:30","2023-04-04 12:00","2023-04-04 09:30","2023-04-04 12:00","연속"]
[161,"경기북부","고양","일산S/S SEC CB 65660","22-23년 고양전력지사 변전협력회사 총액공사","일산S/S 65-66 BUS-SEC GIS 차단기 조작시험","2023-04-04 13:00","2023-04-04 15:00","2023-04-04 13:00","2023-04-04 15:00","연속"]
[162,"경기북부","고양","일산송포#2 T/L","'23-'24년 지중송전설비 위탁정비공사","OF케이블 절연유 시료채취를 위한 휴전","2023-04-06 09:00","2023-04-06 18:00","2023-04-06 09:00","2023-04-06 18:00","연속"]
[163,"경기북부","고양","일산송포#1 T/L","'23-'24년 지중송전설비 위탁정비공사","OF케이블 절연유 시료채취를 위한 휴전","2023-04-05 09:00","2023-04-05 18:00","2023-04-05 09:00","2023-04-05 18:00","연속"]
[164,"경기북부","고양","양주지축#2 T/L","22~23년 고양전력 가공송전협력회사 총액공사","지지애자 교체, 추락방지장치 설치","2023-04-26 13:00","2023-04-28 18:00","2023-04-26 13:00","2023-04-28 18:00","연속"]
[165,"경기북부","고양","양주지축#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","지지애자 교체, 추락방지장치 설치","2023-04-24 07:00","2023-04-26 12:00","2023-04-24 07:00","2023-04-26 12:00","연속"]
[166,"경기북부","구리","신장덕소#2 T/L","구리전력 송전협력 총액공사_수평추락 설치","154kV 신장덕소#2T/L 수평 추락방지장치 설치 피뢰기설치공사 병행","2023-04-24 08:00","2023-04-27 18:00","2023-04-24 08:00","2023-04-27 18:00","연속"]
[167,"경기북부","구리","미금S/S CB 6300","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-04-25 14:00","2023-04-25 18:00","2023-04-25 14:00","2023-04-25 18:00","연속"]
[168,"경기북부","구리","미금덕소#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[169,"경기북부","구리","미금S/S CB 6100","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-04-19 09:00","2023-04-19 18:00","2023-04-19 09:00","2023-04-19 18:00","연속"]
[170,"경기북부","구리","미금화양 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-04-20 09:00","2023-04-20 18:00","2023-04-20 09:00","2023-04-20 18:00","연속"]
[171,"경기북부","구리","미금S/S CB 6200","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-04-25 09:00","2023-04-25 14:00","2023-04-25 09:00","2023-04-25 14:00","연속"]
[172,"경기북부","구리","미금S/S SEC CB 61620","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-04-27 09:00","2023-04-27 14:00","2023-04-27 09:00","2023-04-27 14:00","연속"]
[173,"경기북부","구리","미금S/S SEC CB 66670","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-04-27 14:00","2023-04-27 18:00","2023-04-27 14:00","2023-04-27 18:00","연속"]
[174,"경기북부","구리","신포천전곡#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","수평추락방지시설 설치(신포천-덕계#2 병가, 운천-전곡#2 병가)","2023-04-17 07:30","2023-04-18 18:00","2023-04-17 07:30","2023-04-18 18:00","연속"]
[175,"경기북부","구리","운천전곡#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-04-14 09:00","2023-04-14 18:00","2023-04-14 09:00","2023-04-14 18:00","연속"]
[176,"경기북부","구리","운천전곡#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","수평추락방지시설 설치(신포천-전곡#1 병가, 포천-운천#1병가)","2023-04-17 07:30","2023-04-26 18:00","2023-04-17 07:30","2023-04-26 18:00","연속"]
[177,"경기북부","구리","운천철원#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-04-06 14:00","2023-04-06 18:00","2023-04-06 14:00","2023-04-06 18:00","연속"]
[178,"경기북부","구리","운천철원#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-04-12 09:00","2023-04-12 18:00","2023-04-12 09:00","2023-04-12 18:00","연속"]
[179,"경기북부","구리","운천철원#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","수평추락방지시설 설치(철원-화천#1 병가)","2023-04-27 07:30","2023-04-28 18:00","2023-04-27 07:30","2023-04-28 18:00","연속"]
[180,"경기북부","구리","도봉진접 T/L","154kV 장암S/S 옥내화 건설공사","송전선로 보호반 대체","2023-04-22 09:00","2023-04-26 18:00","2023-04-29 09:00","2023-05-02 18:00","연속"]
[181,"경기북부","구리","청평P/P #1 BUS","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-04-17 18:00","2023-04-21 18:00","2023-04-14 09:00","2023-04-15 18:00","연속"]
[182,"경기북부","구리","청평P/P #2 BUS","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-04-26 18:00","2023-04-27 18:00","2023-04-27 09:00","2023-04-28 18:00","연속"]
[183,"경기북부","구리","청평P/P #1 BUS","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-04-24 18:00","2023-04-25 18:00","2023-04-21 08:00","2023-04-27 09:00","연속"]
[184,"경기북부","구리","청평PP춘천열병합 T/L","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-04-10 18:00","2023-04-21 18:00","2023-04-17 08:00","2023-04-28 18:00","연속"]
[185,"경기북부","구리","청평P/P #2 BUS","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-04-10 18:00","2023-04-14 18:00","2023-04-17 08:00","2023-04-21 08:00","연속"]
[186,"경기북부","구리","서종청평PP#1 T/L","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-04-10 18:00","2023-04-21 18:00","2023-04-17 08:00","2023-04-28 18:00","연속"]
[187,"경기북부","구리","청평P/P #2 BUS","청평양수 SY 노후 154kV GIS 대체공사","- 154kV GiS 5CCT 철거 및 설치 - 기타 부대공사 등","2023-04-06 18:00","2023-04-07 18:00","2023-04-12 08:00","2023-04-14 09:00","연속"]
[188,"경기북부","구리","포천운천#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","수평추락방지시설 설치(운천-전곡#2 병가)","2023-04-24 07:30","2023-04-26 18:00","2023-04-24 07:30","2023-04-26 18:00","연속"]
[189,"경기북부","구리","용정포천#1 T/L","154kV 포천변전소 옥내화 토건공사","송전전력구 H-PILE 인발을 위한 안전 확보","2023-04-14 09:00","2023-04-14 18:00","2023-04-14 09:00","2023-04-14 18:00","연속"]
[190,"경기북부","구리","신포천포천#2 T/L","154kV 포천변전소 옥내화 토건공사","송전전력구 H-PILE 인발을 위한 안전 확보","2023-04-14 09:00","2023-04-14 18:00","2023-04-14 09:00","2023-04-14 18:00","연속"]
[191,"경기북부","구리","포천운천#2 T/L","154kV 포천변전소 옥내화 토건공사","송전전력구 H-PILE 인발을 위한 안전 확보","2023-04-13 09:00","2023-04-13 18:00","2023-04-13 09:00","2023-04-13 18:00","연속"]
[192,"경기북부","구리","신포천포천#1 T/L","154kV 포천변전소 옥내화 토건공사","송전전력구 H-PILE 인발을 위한 안전 확보","2023-04-13 09:00","2023-04-13 18:00","2023-04-13 09:00","2023-04-13 18:00","연속"]
[193,"경기북부","직할","녹양백석#2 T/L","22-23년 직할 변전협력회사 총액공사","녹양백석#2T/L 170kV GIS 보통점검","2023-04-06 08:00","2023-04-06 18:00","2023-04-06 08:00","2023-04-06 18:00","연속"]
[194,"경기북부","직할","양주녹양#2 T/L","22-23년 직할 변전협력회사 총액공사","양주녹양#2T/L 170kV GIS 보통점검","2023-04-05 08:00","2023-04-05 18:00","2023-04-05 08:00","2023-04-05 18:00","연속"]
[195,"경기북부","직할","양주녹양#1 T/L","22-23년 직할 변전협력회사 총액공사","양주녹양#1T/L 170kV GIS 보통점검","2023-04-04 08:00","2023-04-04 18:00","2023-04-04 08:00","2023-04-04 18:00","연속"]
[196,"경기북부","직할","신의정부송우#2 T/L","22-23년 직할 변전협력회사 총액공사","신의정부송우#2 T/L 170kV GIS 보통점검","2023-04-12 08:00","2023-04-12 18:00","2023-04-12 08:00","2023-04-12 18:00","연속"]
[197,"경기북부","직할","양주은평#2 T/L","22~23년 고양전력 가공송전협력회사 총액공사","지지애자교체, 추락방지장치 설치","2023-04-24 07:00","2023-04-26 12:00","2023-04-24 07:00","2023-04-26 12:00","연속"]
[198,"경기북부","직할","양주은평#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2023-04-26 13:00","2023-04-28 18:00","2023-04-26 13:00","2023-04-28 18:00","연속"]
[199,"경기북부","직할","신의정부용현#2 T/L","22-23년 직할 변전협력회사 총액공사","신의정부용현#2 T/L 170kV GIS 보통점검","2023-04-19 08:00","2023-04-19 18:00","2023-04-19 08:00","2023-04-19 18:00","연속"]
[200,"경기북부","직할","용현도봉#2 T/L","154kV 장암S/S 옥내화 건설공사","송전선로 보호반 대체","2023-04-22 09:00","2023-04-28 18:00","2023-04-29 09:00","2023-05-04 18:00","연속"]
[201,"경기북부","직할","신의정부용현#1 T/L","22-23년 직할 변전협력회사 총액공사","신의정부용현#1 T/L 170kV GIS 보통점검","2023-04-18 08:00","2023-04-18 18:00","2023-04-18 08:00","2023-04-18 18:00","연속"]
[202,"경기북부","직할","장암S/S #66 BUS","154kV 장암S/S 옥내화 건설공사","용현도봉#2T/L → 용현장암#2T/L 이설 후 최초가압, 사용전검사","2023-04-26 09:00","2023-04-27 18:00","2023-05-03 09:00","2023-05-04 18:00","연속"]
[203,"경기북부","직할","용현장암#2 T/L","154kV 장암S/S 옥내화 건설공사","용현도봉#2T/L → 용현장암#2T/L 이설 후 최초가압, 사용전검사","2023-04-26 09:00","2023-04-28 18:00","2023-05-02 09:00","2023-05-04 18:00","연속"]
[204,"경기북부","직할","장암진접#1 T/L","154kV 장암S/S 옥내화 건설공사","도봉진접T/L → 장암진접T/L 이설 후 최초가압, 사용전검사","2023-04-24 13:00","2023-04-26 18:00","2023-04-30 09:00","2023-05-02 18:00","연속"]
[205,"경기북부","직할","장암S/S #65 BUS","154kV 장암S/S 옥내화 건설공사","도봉진접T/L → 장암진접T/L 이설 후 최초가압, 사용전검사","2023-04-24 09:00","2023-04-25 18:00","2023-04-30 09:00","2023-05-01 18:00","연속"]
[206,"경기","군포","남군포산본#2 T/L","남군포S/S 154kV SW증설공사","남군포-의왕 #1,2T/L 무부하가압 선로","2023-04-27 13:00","2023-04-28 16:00","2023-04-27 13:00","2023-04-28 16:00","연속"]
[207,"경기","군포","남군포산본#1 T/L","남군포S/S 154kV SW증설공사","서서울-남군포#3T/L 무부하가압 선로","2023-04-26 10:00","2023-04-27 13:00","2023-04-26 10:00","2023-04-27 13:00","연속"]
[208,"경기","군포","화성마도 T/L","마도S/S 화성-마도T/L GIS보통점검 및 세니온IED 성능개선","마도S/S 화성-마도T/L GIS보통점검 및 세니온IED 성능개선","2023-04-07 09:00","2023-04-07 18:00","2023-04-07 09:00","2023-04-07 18:00","연속"]
[209,"경기","군포","사강남양#2 T/L","사강,남양S/S 사강-남양#2T/L GIS 보통점검","사강,남양S/S 사강-남양#2T/L GIS 보통점검","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[210,"경기","군포","마도사강#1 T/L","사강S/S 마도-사강#1T/L GIS 조작시험, PT 보통점검","사강S/S 마도-사강#1T/L GIS 조작시험, PT 보통점검 / 마도S/S 마도-사강#1T/L GIS 보통점검 및 세니온 IED 성능개선","2023-04-19 09:00","2023-04-19 18:00","2023-04-19 09:00","2023-04-19 18:00","연속"]
[211,"경기","군포","사강남양#1 T/L","사강,남양S/S 사강-남양#1T/L GIS 보통점검","사강,남양S/S 사강-남양#1T/L GIS 보통점검","2023-04-17 09:00","2023-04-17 18:00","2023-04-17 09:00","2023-04-17 18:00","연속"]
[212,"경기","군포","서서울S/S #66 BUS","154kV 서서울-남군포#3T/L SW증설공사","서서울-남군포#3T/L 무부하가압(전압위상측정)","2023-04-26 12:00","2023-04-26 13:00","2023-04-26 12:00","2023-04-26 13:00","연속"]
[213,"경기","군포","서서울S/S #61 BUS","154kV 서서울-남군포#3T/L GIS 설치공사","#61BUS 인터록 및 조작시험","2023-04-03 09:00","2023-04-04 18:00","2023-04-03 09:00","2023-04-04 18:00","연속"]
[214,"경기","군포","서서울S/S #61 BUS","154kV 서서울-남군포#3T/L SW증설공사","서서울-남군포#3T/L 증설 무부하가압(전압위상 측정)","2023-04-26 10:00","2023-04-26 12:00","2023-04-26 10:00","2023-04-26 12:00","연속"]
[215,"경기","군포","서안양소래 T/L","서안양 154kV SW 증설공사(LG유플러스)","서안양-LG유플러스#1, 2T/L 무부하가압","2023-04-26 10:00","2023-04-27 10:00","2023-04-26 10:00","2023-04-27 10:00","연속"]
[216,"경기","군포","성곡S/S #2 BUS","성곡S/S 목내-성곡#2T/L GIS 정밀점검 무부하가압","성곡S/S 목내-성곡#2T/L GIS 정밀점검 무부하가압","2023-04-12 09:00","2023-04-12 18:00","2023-04-12 09:00","2023-04-12 18:00","연속"]
[217,"경기","군포","목내성곡#1 T/L","성곡S/S 목내-성곡#2T/L GIS 정밀점검 무부하가압","성곡S/S 목내-성곡#2T/L GIS 정밀점검 무부하가압","2023-04-12 09:00","2023-04-12 18:00","2023-04-12 09:00","2023-04-12 18:00","연속"]
[218,"경기","군포","목내성곡#2 T/L","성곡S/S 목내-성곡#2T/L GIS 정밀점검","성곡S/S 목내-성곡#2T/L GIS 정밀점검 / 목내S/S 목내-성곡#2T/L GIS 보통점검 및 보호반대체","2023-04-10 09:00","2023-04-12 18:00","2023-04-10 09:00","2023-04-12 18:00","연속"]
[219,"경기","군포","성곡S/S #2 BUS","성곡S/S 목내-성곡#1T/L GIS 정밀점검 무부하가압","성곡S/S 목내-성곡#1T/L GIS 정밀점검 무부하가압","2023-04-15 09:00","2023-04-15 18:00","2023-04-15 09:00","2023-04-15 18:00","연속"]
[220,"경기","군포","목내성곡#2 T/L","성곡S/S 목내-성곡#1T/L GIS 정밀점검 무부하가압","성곡S/S 목내-성곡#1T/L GIS 정밀점검 무부하가압","2023-04-15 09:00","2023-04-15 18:00","2023-04-15 09:00","2023-04-15 18:00","연속"]
[221,"경기","군포","목내성곡#1 T/L","성곡S/S 목내-성곡#1T/L GIS 정밀점검","성곡S/S 목내-성곡#1T/L GIS 정밀점검 / 목내S/S 목내-성곡#1T/L GIS 조작시험","2023-04-13 09:00","2023-04-15 18:00","2023-04-13 09:00","2023-04-15 18:00","연속"]
[222,"경기","군포","신안산남안산#2 T/L","신안산S/S 154kV 신안산-남안산#2T/L GIS 정밀점검","신안산S/S 154kV 신안산-남안산#2T/L GIS 정밀점검 / 남안산S/S 신안산-남안산#2T/L CT포화특성시험","2023-04-17 09:00","2023-04-19 18:00","2023-04-17 09:00","2023-04-19 18:00","연속"]
[223,"경기","군포","신안산남안산#1 T/L","신안산S/S 154kV 신안산-남안산#1T/L GIS 정밀점검","신안산S/S 154kV 신안산-남안산#1T/L GIS 정밀점검 / 남안산S/S 신안산-남안산#1T/L CT포화특성시험","2023-04-20 09:00","2023-04-21 18:00","2023-04-20 09:00","2023-04-21 18:00","연속"]
[224,"경기","군포","안산안산복합#2 T/L","안산C/C #1GT, 안산-안산복합#1,2,3TL GIS 보통점검","안산C/C #1GT, 안산-안산복합#1,2,3TL GIS 보통점검/ 안산S/S 안산-안산복합#1,2,3T/L GIS 보통점검","2023-04-29 13:00","2023-04-29 15:00","2023-04-29 13:00","2023-04-29 15:00","연속"]
[225,"경기","군포","목내안산복합#1 T/L","안산C/C #2GT, #1ST, 목내-안산복합#1,2TL GIS 보통점검","안산C/C #2GT, #1ST, 목내-안산복합#1,2TL GIS 보통점검/ 목내S/S 목내-안산복합#1,2T/L GIS 보통점검","2023-04-30 13:00","2023-04-30 15:00","2023-04-30 13:00","2023-04-30 15:00","연속"]
[226,"경기","군포","안산안산복합#3 T/L","안산C/C #1GT, 안산-안산복합#1,2,3TL GIS 보통점검","안산C/C #1GT, 안산-안산복합#1,2,3TL GIS 보통점검/ 안산S/S 안산-안산복합#1,2,3T/L GIS 보통점검","2023-04-29 15:00","2023-04-29 18:00","2023-04-29 15:00","2023-04-29 18:00","연속"]
[227,"경기","군포","목내안산복합#2 T/L","안산C/C #2GT, #1ST, 목내-안산복합#1,2TL GIS 보통점검","안산C/C #2GT, #1ST, 목내-안산복합#1,2TL GIS 보통점검/ 목내S/S 목내-안산복합#1,2T/L GIS 보통점검","2023-04-30 15:00","2023-04-30 18:00","2023-04-30 15:00","2023-04-30 18:00","연속"]
[228,"경기","군포","안산안산복합#1 T/L","안산C/C #1GT, 안산-안산복합#1,2,3TL GIS 보통점검","안산C/C #1GT, 안산-안산복합#1,2,3TL GIS 보통점검/ 안산S/S 안산-안산복합#1,2,3T/L GIS 보통점검","2023-04-29 11:00","2023-04-29 13:00","2023-04-29 11:00","2023-04-29 13:00","연속"]
[229,"경기","군포","서서울#2일동#2 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 24기","2023-04-03 07:00","2023-04-06 18:00","2023-04-03 07:00","2023-04-06 18:00","연속"]
[230,"경기","군포","서서울#2일동#1 T/L","철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 24기","2023-04-10 07:00","2023-04-12 18:00","2023-04-10 07:00","2023-04-12 18:00","연속"]
[231,"경기","군포","성곡중시화 T/L","중시화S/S #1,2M.Tr 1차 GIS 정밀점검 무부하선로","중시화S/S #1,2M.Tr 1차 GIS 정밀점검 무부하선로","2023-04-25 09:00","2023-04-28 18:00","2023-04-25 09:00","2023-04-28 18:00","연속"]
[232,"경기","동부","곤지암S/S CB 6200","23년 동부 변전협력총액공사","곤지암:61-66 모선보호반대체(~14) 6200(보통)","2023-04-10 09:30","2023-04-14 18:00","2023-04-10 09:30","2023-04-14 18:00","연속"]
[233,"경기","동부","곤지암S/S CB 6100","23년 동부 변전협력총액공사","곤지암:60-65 모선보호반대체(~7) 6100(보통)","2023-04-03 09:30","2023-04-07 18:00","2023-04-03 09:30","2023-04-06 18:00","연속"]
[234,"경기","동부","곤지암S/S SEC CB 60610","23년 동부 변전협력총액공사","곤지암:60-61(보통)","2023-04-07 09:30","2023-04-07 18:00","2023-04-07 09:30","2023-04-07 18:00","연속"]
[235,"경기","동부","곤지암S/S SEC CB 65660","23년 동부 변전협력총액공사","곤지암:65-66(보통)","2023-04-28 09:30","2023-04-28 18:00","2023-04-28 09:30","2023-04-28 18:00","연속"]
[236,"경기","동부","오포모현#1 T/L","추락방지시설 설치공사","추락방지시설 설치(4회선구간)","2023-04-16 07:00","2023-04-16 18:00","2023-04-16 07:00","2023-04-16 18:00","연속"]
[237,"경기","동부","오포모현#2 T/L","추락방지시설 설치공사","추락방지시설 설치(4회선구간)","2023-04-12 07:00","2023-04-14 18:00","2023-04-12 07:00","2023-04-14 18:00","연속"]
[238,"경기","동부","모현용인#1 T/L","추락방지시설 설치공사","추락방지시설 설치","2023-04-09 07:00","2023-04-13 18:00","2023-04-09 07:00","2023-04-13 18:00","연속"]
[239,"경기","동부","모현용인#2 T/L","추락방지시설 설치공사","추락방지시설 설치","2023-04-15 07:00","2023-04-16 18:00","2023-04-15 07:00","2023-04-16 18:00","연속"]
[240,"경기","동부","분당S/S SEC CB 65660","23년 동부 변전협력총액공사","분당:65-66(보통,전자변교체)","2023-04-26 09:30","2023-04-26 18:00","2023-04-26 09:30","2023-04-26 18:00","연속"]
[241,"경기","동부","분당오포#2 T/L","추락방지시설 설치공사","추락방지시설 설치","2023-04-30 07:00","2023-05-02 18:00","취소","취소","연속"]
[242,"경기","동부","분당S/S CB 6100","23년 동부 변전협력총액공사","분당:6100(보통,전자변교체)","2023-04-24 09:30","2023-04-24 18:00","2023-04-24 09:30","2023-04-24 18:00","연속"]
[243,"경기","동부","분당S/S SEC CB 60610","23년 동부 변전협력총액공사","분당:60-61(보통,전자변교체)","2023-04-25 09:30","2023-04-25 18:00","2023-04-25 09:30","2023-04-25 18:00","연속"]
[244,"경기","동부","산성수서#2 T/L","23년 동부 변전협력총액공사","산성:산성-수서#1T/L(조작) 산성-수서#2T/L(조작) 6100(조작)","2023-04-12 13:00","2023-04-12 15:30","2023-04-12 13:00","2023-04-12 15:30","연속"]
[245,"경기","동부","산성수서#1 T/L","23년 동부 변전협력총액공사","산성:산성-수서#1T/L(조작) 산성-수서#2T/L(조작) 6100(조작)","2023-04-12 09:30","2023-04-12 12:00","2023-04-12 09:30","2023-04-12 12:00","연속"]
[246,"경기","동부","야탑성현#1 T/L","성현S/S 장기사용 154kV GIS 교체공사","성현S/S 장기사용 154kV GIS 교체공사(1차) 산성-성현#3, 성현-분당#2, 야탑-성현#1T/L, #4M.Tr 1차 대체 60-61,65-66 B/S, 6200 B/T, 61-66 PT 설치","2023-04-24 09:00","2023-06-04 18:00","2023-04-24 09:00","2023-06-04 18:00","연속"]
[247,"경기","동부","성현산성#3 T/L","성현S/S 장기사용 154kV GIS 교체공사","성현S/S 장기사용 154kV GIS 교체공사(1차) 산성-성현#3, 성현-분당#2, 야탑-성현#1T/L, #4M.Tr 1차 대체 60-61,65-66 B/S, 6200 B/T, 61-66 PT 설치","2023-04-24 09:00","2023-06-04 18:00","2023-04-24 09:00","2023-06-04 18:00","연속"]
[248,"경기","동부","성현분당#2 T/L","성현S/S 장기사용 154kV GIS 교체공사","성현S/S 장기사용 154kV GIS 교체공사(1차) 산성-성현#3, 성현-분당#2, 야탑-성현#1T/L, #4M.Tr 1차 대체 60-61,65-66 B/S, 6200 B/T, 61-66 PT 설치","2023-04-24 09:00","2023-06-04 18:00","2023-04-24 09:00","2023-06-04 18:00","연속"]
[249,"경기","동부","성현분당#1 T/L","성현S/S SA화 공사","154kV 성현S/S SA화 공사 시행","2023-04-07 14:00","2023-04-08 18:00","2023-04-07 14:00","2023-04-08 18:00","연속"]
[250,"경기","동부","초월성현#2 T/L","성현S/S SA화 공사","154kV 성현S/S SA화 공사 시행","2023-04-06 09:00","2023-04-07 14:00","2023-04-06 09:00","2023-04-07 14:00","연속"]
[251,"경기","동부","초월성현#1 T/L","성현S/S SA화 공사","154kV 성현S/S SA화 공사 시행","2023-04-04 14:00","2023-04-05 18:00","2023-04-04 14:00","2023-04-05 18:00","연속"]
[252,"경기","동부","왕암여주#2 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치 및 성능저하 지지애자 교체공사, 158~203호","2023-04-05 07:30","2023-04-11 18:00","2023-04-05 07:30","2023-04-11 18:00","연속"]
[253,"경기","동부","초월성현#1 T/L","초월 #5M.Tr 증설공사","초월:곤지암-초월#1T/L(~23) #60BUS (#5M.Tr 증설공사)","2023-04-01 09:30","2023-04-02 18:00","2023-04-01 09:30","2023-04-02 18:00","연속"]
[254,"경기","성남","덕성남사#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사(휴전/4회선 병가 안전거리)","2023-04-11 08:00","2023-04-11 18:00","2023-04-11 08:00","2023-04-11 18:00","매일"]
[255,"경기","성남","서안성남사#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사(휴전)","2023-04-11 08:00","2023-04-11 18:00","2023-04-11 08:00","2023-04-11 18:00","매일"]
[256,"경기","성남","서안성남사#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사(휴전)","2023-04-12 08:00","2023-04-12 18:00","2023-04-12 08:00","2023-04-12 18:00","매일"]
[257,"경기","성남","덕성남사#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑 추락방지장치 설치공사(휴전/4회선 병가 안전거리)","2023-04-12 08:00","2023-04-12 18:00","2023-04-12 08:00","2023-04-12 18:00","매일"]
[258,"경기","성남","기흥신갈#2 T/L","효성제 GIS 부붐교체공사","- 스프링타입 조작기 부품교체(제작사)","2023-04-07 09:00","2023-04-07 18:00","2023-04-07 09:00","2023-04-07 18:00","연속"]
[259,"경기","성남","기흥신갈#1 T/L","효성제 GIS 부붐교체공사","- 스프링타입 조작기 부품교체(제작사)","2023-04-06 09:00","2023-04-06 18:00","2023-04-06 09:00","2023-04-06 18:00","연속"]
[260,"경기","성남","신봉이의#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","산형강 91기, 관형주 8기 수직/수평 추락방지장치 설치","2023-04-13 07:00","2023-04-14 18:00","2023-04-13 07:00","2023-04-14 18:00","연속"]
[261,"경기","성남","신봉이의#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","산형강 91기, 관형주 8기 수직/수평 추락방지장치 설치","2023-04-10 07:00","2023-04-12 18:00","2023-04-10 07:00","2023-04-12 18:00","연속"]
[262,"경기","성남","신성남S/S SEC CB 62630","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-04-05 09:00","2023-04-05 14:00","2023-04-05 09:00","2023-04-05 14:00","연속"]
[263,"경기","성남","신성남S/S SEC CB 67680","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-04-05 14:00","2023-04-05 18:00","2023-04-05 14:00","2023-04-05 18:00","연속"]
[264,"경기","성남","신성남사당#2 T/L","추락방지시설 설치공사","추락방지시설 설치(4회선 구간)","2023-04-22 07:00","2023-04-23 18:00","2023-04-22 07:00","2023-04-23 18:00","연속"]
[265,"경기","성남","신성남사당#1 T/L","추락방지시설 설치공사","추락방지시설 설치(4회선 구간)","2023-04-19 07:00","2023-04-21 18:00","2023-04-19 07:00","2023-04-21 18:00","연속"]
[266,"경기","성남","신성남과천#1 T/L","추락방지시설 설치공사","추락방지시설 설치","2023-04-19 07:00","2023-04-21 18:00","2023-04-19 07:00","2023-04-21 18:00","연속"]
[267,"경기","성남","신성남정자#1 T/L","23년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2023-04-24 09:00","2023-04-26 14:00","2023-04-24 09:00","2023-04-26 14:00","연속"]
[268,"경기","성남","신성남과천#2 T/L","추락방지시설 설치공사","추락방지시설 설치","2023-04-22 07:00","2023-04-23 18:00","2023-04-22 07:00","2023-04-23 18:00","연속"]
[269,"경기","성남","신성남정자#2 T/L","23년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2023-04-26 14:00","2023-04-28 18:00","2023-04-26 14:00","2023-04-28 18:00","연속"]
[270,"경기","직할","관양동안양#2 T/L","22-23 경기본부 직할 변전협력회사 총액공사","동안양S/S 관양-동안양#2T/L GIS 공압 메커니즘 점검","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[271,"경기","직할","평촌안양2CC#3 T/L","22-23 경기본부 직할 변전협력회사 총액공사","평촌S/S 평촌-안양2C/C#3T/L GIS 보통점검 안양2C/C 평촌-안양2C/C#3T/L GIS 보통점검","2023-04-11 09:00","2023-04-11 18:00","2023-04-11 09:00","2023-04-11 18:00","연속"]
[272,"경기","직할","평촌안양2CC#2 T/L","22-23 경기본부 직할 변전협력회사 총액공사","평촌S/S 평촌-안양2C/C#2T/L GIS 보통점검 안양2C/C 평촌-안양2C/C#2T/L GIS 보통점검","2023-04-10 09:00","2023-04-10 18:00","2023-04-10 09:00","2023-04-10 18:00","연속"]
[273,"경기","평택","고덕평택#2 T/L","345kV 고덕2S/S 건설사업","154kV 고덕-평택 #2T/L 인출변경","2023-04-17 09:00","2023-05-12 18:00","2023-04-21 09:00","2023-05-19 18:00","연속"]
[274,"경기","평택","고덕진위#2 T/L","345kV 고덕-서안성T/L 건설공사","(1) 선로길이 : 345kV ( 2회선 ) - 10.237km / 154kV ( 2회선 ) - 0.516 km (2) 지지물 ○ 345kV –154kV ( 4회선 ) : 설치 2기 ○ 345kV ( 2회선 ) : 설치 33기 ○ 154kV ( 1회선 ) : 설치 및 철거 1기 (가철탑) ○ 발받침 철탑 : 설치 및 철거 1기","2023-04-05 07:00","2023-04-08 18:00","2023-04-17 07:00","2023-04-20 18:00","연속"]
[275,"경기","평택","포승청북 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사)","케이블타워 및 피뢰기 점검","2023-04-11 10:00","2023-04-11 18:00","2023-04-11 10:00","2023-04-11 18:00","연속"]
[276,"경기","평택","서운안성#1 T/L","세종-포천간 도로개설 관련 지장이설공사","세종-포천간 도로개설 관련 지장이설공사","2023-04-01 09:00","2023-04-14 18:00","2023-04-01 09:00","2023-04-14 18:00","연속"]
[277,"경기","평택","서운안성#2 T/L","세종-포천간 도로개설 관련 지장이설공사","세종-포천간 도로개설 관련 지장이설공사","2023-04-15 09:00","2023-05-05 18:00","2023-04-15 09:00","2023-05-05 18:00","연속"]
[278,"강원","강릉","강릉횡계#1 T/L","23년도 가공송전선로 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 강릉-횡계#1T/L No.1~36","2023-04-24 08:00","2023-04-28 18:00","2023-04-24 08:00","2023-04-28 18:00","매일"]
[279,"강원","강릉","강릉횡계#2 T/L","23년도 가공송전선로 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 강릉-횡계#2T/L No.1~36","2023-04-17 08:00","2023-04-21 18:00","2023-04-17 08:00","2023-04-21 18:00","매일"]
[280,"강원","강릉","동해강릉 T/L","23년도 가공송전선로 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 강릉-횡계#1T/L 4회선 병가구간으로 작업자 안전을 위한 휴전 (No.64~67)","2023-04-28 08:00","2023-04-28 18:00","2023-04-28 08:00","2023-04-28 18:00","연속"]
[281,"강원","강릉","북강릉주문진#1 T/L","23년도 가공송전선로 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 강릉-북강릉#2T/L 4회선 병가구간으로 작업자 안전을 위한 휴전 (No.2~10)","2023-04-14 08:00","2023-04-14 18:00","2023-04-14 08:00","2023-04-14 18:00","연속"]
[282,"강원","강릉","강릉북강릉#2 T/L","23년도 가공송전선로 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 강릉-북강릉#2T/L No.1~45","2023-04-10 08:00","2023-04-14 18:00","2023-04-10 08:00","2023-04-14 18:00","매일"]
[283,"강원","강릉","북강릉주문진#2 T/L","23년도 가공송전선로 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 강릉-북강릉#1T/L 4회선 병가구간으로 작업자 안전을 위한 휴전 (No.2~10)","2023-04-07 08:00","2023-04-07 18:00","2023-04-07 08:00","2023-04-07 18:00","연속"]
[284,"강원","강릉","강릉북강릉#1 T/L","23년도 가공송전선로 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 강릉-북강릉#1T/L No.1~45","2023-04-03 08:00","2023-04-07 18:00","2023-04-03 08:00","2023-04-07 18:00","매일"]
[285,"강원","강릉","동해영동TP T/L","영동화력S/Y 170kV 장기사용 GIS 대체공사","- 영동TP 탈황설비용 154kV 6383 GIS 설치, 전력케이블 설치 안전이격 확보 - 발전소 병행휴전","2023-04-17 08:00","2023-05-12 18:00","2023-04-17 08:00","2023-05-12 18:00","매일"]
[286,"강원","강릉","영동T/P #2 BUS","영동화력S/Y 170kV 장기사용 GIS 대체공사","- 154kV 6383 GIS 가공부 Bushing 철거 - 4/18~19 #2Bus 시험가압","2023-04-17 08:00","2023-04-19 08:00","2023-04-17 08:00","2023-04-19 08:00","연속"]
[287,"강원","강릉","강릉영동TP T/L","영동화력S/Y 170kV 장기사용 GIS 대체공사","- 영동TP 탈황설비용 154kV 6383 GIS 설치, 전력케이블 설치 안전이격 확보 - 발전소 병행휴전","2023-04-17 08:00","2023-05-12 18:00","2023-04-17 08:00","2023-05-12 18:00","매일"]
[288,"강원","강릉","영동T/P #1 BUS","영동화력S/Y 170kV 장기사용 GIS 대체공사","- 154kV 6383 GIS GIB 철거, #1DS, 본체 GIS 설치 - 4/26~27 #1Bus 시험가압","2023-04-19 08:00","2023-04-27 08:00","2023-04-19 08:00","2023-04-27 08:00","연속"]
[289,"강원","강릉","영동T/P #2 BUS","영동화력S/Y 170kV 장기사용 GIS 대체공사","- 154kV 6383 GIS GIB 철거, #2DS, 상부BUS 설치 - #2Bus 시험가압","2023-04-27 08:00","2023-05-10 08:00","2023-04-27 08:00","2023-05-10 08:00","연속"]
[290,"강원","강릉","평창올림픽 T/L","2023 변전협력회사 총액공사","올림픽S/S 170kV GIS, LA 보통점검","2023-04-06 10:00","2023-04-06 18:00","2023-04-06 10:00","2023-04-06 18:00","연속"]
[291,"강원","강릉","횡계올림픽 T/L","2023 변전협력회사 총액공사","-170kV GIS 보통점검","2023-04-14 10:00","2023-04-14 18:00","2023-04-14 10:00","2023-04-14 18:00","연속"]
[292,"강원","강릉","주진평창#1 T/L","2023 변전협력회사 총액공사","평창S/S 주진평창#1T/L #1DS Aux.SW 교체","2023-04-11 10:00","2023-04-11 18:00","2023-04-11 10:00","2023-04-11 18:00","연속"]
[293,"강원","동해","동해T/P CB 6183","22~23 동해전력지사 변전정비 협력회사 공사","1. GIS 보통점검","2023-04-25 09:00","2023-04-25 13:00","2023-04-25 09:00","2023-04-25 13:00","연속"]
[294,"강원","동해","동해T/P CB 6283","22~23 동해전력지사 변전정비 협력회사 공사","1. GIS 보통점검","2023-04-25 13:00","2023-04-25 18:00","2023-04-25 13:00","2023-04-25 18:00","연속"]
[295,"강원","동해","삼척동해TP T/L","22~23 동해전력지사 변전정비 협력회사 공사","GIS 보통점검","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[296,"강원","동해","북평영동TP#1 T/L","`23~24년 강원본부 지중송전설비 위탁정비공사","작업내용 : 154kV 영동화력C/H 피뢰기 점검 작업기간 - 북평-영동T/P#1T/L : `23.04.27 08:00 ~ 13:00 - 북평-영동T/P#2T/L : `23.04.27 13:00 ~ 18:00","2023-04-27 08:00","2023-04-27 13:00","2023-04-27 08:00","2023-04-27 13:00","연속"]
[297,"강원","동해","북평영동TP#2 T/L","`23~24년 강원본부 지중송전설비 위탁정비공사","작업내용 : 154kV 영동화력C/H 피뢰기 점검 작업기간 - 북평-영동T/P#1T/L : `23.04.27 08:00 ~ 13:00 - 북평-영동T/P#2T/L : `23.04.27 13:00 ~ 18:00","2023-04-27 13:00","2023-04-27 18:00","2023-04-27 13:00","2023-04-27 18:00","연속"]
[298,"강원","동해","이원삼척 T/L","2022-23년 동해전력지사 가공송전협력회사 총액공사","No.7~9 항공장애표시구 교체","2023-04-10 08:00","2023-04-10 18:00","2023-04-10 08:00","2023-04-10 18:00","연속"]
[299,"강원","원주","남원주원주#2 T/L","2022~2023년 원주전력지사 가공송전 협력회사 총액공사","154kV 남원주-원주#2T/L 추락방지장치(수평) 설치 (31기)","2023-04-28 07:00","2023-05-01 18:00","2023-04-28 07:00","2023-05-01 18:00","매일"]
[300,"강원","원주","남원주원주#1 T/L","2022~2023년 원주전력지사 가공송전 협력회사 총액공사","154kV 남원주-원주#1T/L 추락방지장치(수평) 설치 (31기)","2023-04-24 07:00","2023-04-28 18:00","2023-04-24 07:00","2023-04-28 18:00","매일"]
[301,"강원","원주","서원주문막#2 T/L","구리전력 송전협력 총액공사_수평추락 설치","154kV 문막-지제#1T/L 수평 추락방지장치 설치, 문막지제#1 No.1~3호가 서원주문막 #2 No.48~50와 병가로 하단선로 휴전","2023-04-03 08:00","2023-04-03 18:00","2023-04-03 08:00","2023-04-03 18:00","연속"]
[302,"강원","원주","서원주문막#1 T/L","구리전력 송전협력 총액공사_수평추락 설치","154kV 문막-지제#2T/L 수평 추락방지장치 설치, 문막지제#2 No.1~3호가 서원주문막 #1 No.48~50와 병가로 하단선로 휴전","2023-04-12 08:00","2023-04-12 18:00","2023-04-12 08:00","2023-04-12 18:00","연속"]
[303,"강원","원주","홍천상남#2 T/L","2023년 원주전력지사 변전협력회사 총액공사","홍천 - GIS, LA, CVT 점검 상남 - GIS, CVT 점검","2023-04-13 10:00","2023-04-14 18:00","2023-04-13 10:00","2023-04-14 18:00","매일"]
[304,"강원","원주","홍천상남#1 T/L","2023년 원주전력지사 변전협력회사 총액공사","홍천 - GIS, LA, CVT 점검 상남 - GIS, CVT 점검, 피뢰기 교체","2023-04-10 10:00","2023-04-11 18:00","2023-04-10 10:00","2023-04-11 18:00","매일"]
[305,"강원","원주","북원주횡성#1 T/L","'22~23년 원주전력지사 송전협력회사 총액공사","○ 와이어형 추락방지장치 설치 ○ 고정형 폴리머애자 설치","2023-04-08 07:00","2023-04-09 18:00","2023-04-08 07:00","2023-04-09 18:00","매일"]
[306,"강원","원주","북원주횡성#2 T/L","'22~23년 원주전력지사 송전협력회사 총액공사","○ 와이어형 추락방지장치 설치 ○ 고정형 폴리머애자 설치","2023-04-15 07:00","2023-04-16 18:00","2023-04-15 07:00","2023-04-16 18:00","매일"]
[307,"강원","원주","둔내횡성#2 T/L","'22~23년 원주전력지사 송전협력회사 총액공사","○ 와이어형 추락방지장치 설치 - 추락방지장치 안전확보를 위한 휴전(6회선 병가구간)","2023-04-22 07:00","2023-04-22 18:00","2023-04-22 07:00","2023-04-22 18:00","연속"]
[308,"강원","원주","북원주횡성#1 T/L","'22~23년 원주전력지사 송전협력회사 총액공사","○ 와이어형 추락방지장치 설치 ○ 고정형 폴리머애자 설치","2023-04-22 07:00","2023-04-23 18:00","2023-04-22 07:00","2023-04-23 18:00","매일"]
[309,"강원","원주","횡성홍천#2 T/L","'22~23년 원주전력지사 송전협력회사 총액공사","○ 와이어형 추락방지장치 설치 ○ 피뢰기 설치","2023-04-22 07:00","2023-04-23 18:00","2023-04-22 07:00","2023-04-23 18:00","매일"]
[310,"강원","원주","북원주횡성#2 T/L","'22~23년 원주전력지사 송전협력회사 총액공사","○ 와이어형 추락방지장치 설치 ○ 고정형 폴리머애자 설치","2023-04-29 07:00","2023-04-30 18:00","2023-04-29 07:00","2023-04-30 18:00","매일"]
[311,"강원","원주","횡성홍천#1 T/L","'22~23년 원주전력지사 송전협력회사 총액공사","○ 와이어형 추락방지장치 설치 ○ 피뢰기 설치","2023-04-29 07:00","2023-04-30 18:00","2023-04-29 07:00","2023-04-30 18:00","매일"]
[312,"강원","원주","둔내횡성#1 T/L","'22~23년 원주전력지사 송전협력회사 총액공사","○ 와이어형 추락방지장치 설치 - 추락방지장치 안전확보를 위한 휴전(6회선 병가구간)","2023-04-29 07:00","2023-04-29 18:00","2023-04-29 07:00","2023-04-29 18:00","연속"]
[313,"강원","직할","남춘천춘천열병합#1 T/L","2022~23년 직할 변전정비 총액공사","- 남춘천S/S 154kV 남춘천-춘천열병합 #1T/L GIS 보통점검","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[314,"강원","직할","남춘천춘천열병합#2 T/L","2022~23년 직할 변전정비 총액공사","- 남춘천S/S 154kV 남춘천-춘천열병합 #2T/L GIS 보통점검","2023-04-04 09:00","2023-04-04 18:00","2023-04-04 09:00","2023-04-04 18:00","연속"]
[315,"강원","직할","인제양구#1 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 양구 T/L 철탑 추락방지장치 설치","2023-04-06 09:00","2023-04-20 18:00","2023-04-06 09:00","2023-04-20 18:00","매일"]
[316,"강원","직할","상남인제#1 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 상제 T/L 철탑 추락방지장치 설치","2023-04-06 08:00","2023-04-07 18:00","2023-04-06 08:00","2023-04-07 18:00","매일"]
[317,"강원","직할","철원화천#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","병가선로 휴전_운천-철원#1TL 수평추락방지시설 설치","2023-04-27 07:30","2023-04-28 18:00","2023-04-27 07:30","2023-04-28 18:00","연속"]
[318,"강원","직할","춘천북춘천#2 T/L","2023년 가공송전 순시점검 위탁공사","154kV 춘천분기 정밀점검","2023-04-24 09:00","2023-04-25 18:00","2023-04-24 09:00","2023-04-25 18:00","매일"]
[319,"강원","직할","춘천소양강HP T/L","2023년 가공송전 순시점검 위탁공사","154kV 춘천분기 정밀점검","2023-04-24 09:00","2023-04-27 18:00","2023-04-24 09:00","2023-04-27 18:00","매일"]
[320,"강원","직할","남춘천춘천 T/L","2023년 가공송전 순시점검 위탁공사","154kV 춘천분기 정밀점검","2023-04-18 09:00","2023-04-21 18:00","2023-04-18 09:00","2023-04-21 18:00","매일"]
[321,"강원","직할","춘천북춘천#1 T/L","2023년 가공송전 순시점검 위탁공사","154kV 춘천분기 정밀점검","2023-04-18 09:00","2023-04-19 18:00","2023-04-18 09:00","2023-04-19 18:00","매일"]
[322,"강원","직할","화천화천HP#1 T/L","2022~2023년 강원직할 가공송전협력회사 총액공사","압축인류크램프 보수","2023-04-04 08:00","2023-04-04 18:00","2023-04-04 08:00","2023-04-04 18:00","연속"]
[323,"강원","직할","화천화천HP#2 T/L","2022~2023년 강원본부 직할 변전협력회사 총액공사","- 화천, 화천HP 154kV 화천-화천HP#2T/L LA 초기점검","2023-04-24 10:00","2023-04-24 18:00","2023-04-24 10:00","2023-04-24 18:00","연속"]
[324,"강원","직할","철원화천#2 T/L","2022~2023년 강원본부 직할 변전협력회사 총액공사","- 철원, 화천S/S 154kV 철원-화천#2T/L LA(A,B,C) 교체","2023-04-25 10:00","2023-04-26 18:00","2023-04-25 10:00","2023-04-26 18:00","매일"]
[325,"강원","태백","영월S/S 영월G/T#1T/L CB","22-23년 태백전력지사 변전협력회사 총액공사","영월S/S 154kV 영월GT#1T/L 1차 GIS 조작시험","2023-04-25 09:00","2023-04-25 18:00","취소","취소","연속"]
[326,"강원","태백","영월영월CC T/L","22-23년 태백전력지사 변전협력회사 총액공사","영월S/S 154kV 영월-영월CC T/L GIS 조작시험","2023-04-26 09:00","2023-04-26 18:00","취소","취소","연속"]
[327,"강원","태백","영월S/S CB 6100","22-23년 태백전력지사 변전협력회사 총액공사","영월S/S 154kV BUS TIE GIS 보통점검","2023-04-25 09:00","2023-04-25 18:00","취소","취소","연속"]
[328,"강원","태백","이원태백 T/L","22~23년 태백전력지사 가공송전 협력회사 총액공사","송전용 피뢰기 설치","2023-04-03 08:00","2023-04-07 18:00","2023-04-03 08:00","2023-04-07 18:00","매일"]
[329,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 삼죽-광혜원T/L ↔ 154kV 서운-광혜원T/L 간 임시회로 구성","2023-04-19 10:00","2023-04-19 18:00","취소","취소","연속"]
[330,"충북","직할","서운광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","154kV 삼죽-광혜원T/L ↔ 154kV 서운-광혜원T/L 간 임시회로 구성","2023-04-17 10:00","2023-05-07 18:00","취소","취소","연속"]
[331,"충북","직할","진천광혜원#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","서운삼죽 병가선로 휴전 및 애자교체, 아킹혼 설지 No.38 전력선 애자교체, no. 45, 50 지지애자교체 (폴리머), No.38 아킹혼 설치","2023-04-11 07:30","2023-04-14 18:00","2023-04-11 07:30","2023-04-14 18:00","매일"]
[332,"충북","직할","신진천진천#1 T/L","154kV 신진천-오창T/L OPGW 증설공사","154kV 신진천-진천#1T/L 29~30호 OPGW 1드럼 시설","2023-04-24 07:00","2023-04-24 18:00","취소","취소","연속"]
[333,"충북","직할","신진천S/S SEC CB 61620","'23년 상반기 충북직할 154kV GIS 정밀점검공사","신진천변전소 154kV #61-62BUS SEC GIS 정밀점검","2023-04-10 09:00","2023-04-12 18:00","취소","취소","연속"]
[334,"충북","직할","신진천S/S SEC CB 66670","'23년 상반기 충북직할 154kV GIS 정밀점검공사","신진천변전소 154kV #66-67BUS SEC GIS 정밀점검","2023-04-16 09:00","2023-04-18 18:00","취소","취소","연속"]
[335,"충북","직할","신진천S/S SEC CB 60610","'23년 상반기 충북직할 154kV GIS 정밀점검공사(무부하가압)","신진천변전소 154kV #61M.Tr 1차 GIS 정밀점검 후 무부하 가압","2023-04-05 09:00","2023-04-05 18:00","2023-04-05 09:00","2023-04-05 18:00","연속"]
[336,"충북","직할","신진천진천#2 T/L","154kV신진천-오창T/L OPGW 증설공사","154kV신진천-오창#2T/L 2~3호 OPGW 1드럼 시설","2023-04-25 07:00","2023-04-25 18:00","취소","취소","연속"]
[337,"충북","직할","신진천S/S SEC CB 65660","'23년 상반기 충북직할 154kV GIS 정밀점검공사","신진천변전소 154kV #65-66BUS SEC GIS 정밀점검","2023-04-13 09:00","2023-04-15 18:00","취소","취소","연속"]
[338,"충북","직할","진천덕산#1 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","진천덕산#1 T/L 금구류 정비, 애자교체 등 No.10 금구류 정비, No.16 추락방지, No. 27 애자교체, No. 14 전력선 스풀라이스, 진천S/S 아킹혼 설치","2023-04-24 07:30","2023-04-26 18:00","2023-04-24 07:30","2023-04-26 18:00","매일"]
[339,"충북","직할","진천덕산#2 T/L","154kV 진천-덕산#2T/L 애자 절연저항 측정","154kV 진천-덕산#2T/L 애자 절연저항 측정 - No.1,2,5,8,9,15,27","2023-04-03 07:30","2023-04-04 18:00","2023-04-03 07:30","2023-04-04 18:00","매일"]
[340,"충북","청주","남청주오송#1 T/L","남청주S/S 장기사용 감시제어반 대체공사","감시/제어/경보 포인트 (구)모자익 → (신)집감반 이설 (즉시가압 가능)","2023-04-14 10:00","2023-04-14 18:00","2023-04-14 10:00","2023-04-14 18:00","연속"]
[341,"충북","청주","남청주죽림#2 T/L","남청주S/S 장기사용 감시제어반 대체공사","감시/제어/경보 포인트 (구)모자익 → (신)집감반 이설 (즉시가압 가능)","2023-04-11 10:00","2023-04-11 18:00","2023-04-11 10:00","2023-04-11 18:00","연속"]
[342,"충북","청주","남청주죽림#1 T/L","남청주S/S 장기사용 감시제어반 대체공사","감시/제어/경보 포인트 (구)모자익 → (신)집감반 이설 (즉시가압 가능)","2023-04-10 10:00","2023-04-10 18:00","2023-04-10 10:00","2023-04-10 18:00","연속"]
[343,"충북","청주","율량봉명#2 T/L","'22~23년 청주전력 변전협력회사 총액공사","170kV GIS 보통점검","2023-04-21 09:00","2023-04-21 18:00","2023-04-21 09:00","2023-04-21 18:00","연속"]
[344,"충북","청주","북청주봉명#1 T/L","'22~23년 청주전력 변전협력회사 총액공사","170kV GIS 보통점검","2023-04-20 09:00","2023-04-20 18:00","2023-04-20 09:00","2023-04-20 18:00","연속"]
[345,"충북","청주","서청주사직#1 T/L","23년 청주전력지사 170kV GIS 정밀점검","사직S/S 154kV 서청주-사직#1T/L GIS 정밀점검","2023-04-10 09:00","2023-04-11 18:00","취소","취소","연속"]
[346,"충북","청주","서청주사직#1 T/L","23년 청주전력지사 170kV GIS 정밀점검","서청주S/S 154kV 서청주-사직#1T/L 정밀점검","2023-04-12 09:00","2023-04-13 18:00","취소","취소","연속"]
[347,"충북","청주","신진천오창#1 T/L","154kV 문백-오창 송전선로 건설공사","신진천-오창T/L No.22호 인근 가선로 구성","2023-04-27 07:00","2023-04-29 18:00","2023-05-05 07:00","2023-05-07 18:00","연속"]
[348,"충북","청주","신진천오창#2 T/L","154kV 문백-오창 송전선로 건설공사","신진천-오창T/L No.22호 인근 가선로 구성","2023-04-24 07:00","2023-04-26 18:00","2023-04-29 07:00","2023-05-01 18:00","연속"]
[349,"충북","청주","청주율량#2 T/L","'22~23년 청주전력 변전협력회사 총액공사","170kV GIS 보통점검","2023-04-26 09:00","2023-04-26 18:00","2023-04-26 09:00","2023-04-26 18:00","연속"]
[350,"충북","충주","신충주감곡#2 T/L","154kV 신충주-감곡#2T/L 초기(정밀)점검","No.77~85(왕암여주#2 No.141~133 병가) 초기점검 및 86~88(감곡가남#1 No.1~3병가) 초기(정밀)점검","2023-04-05 07:30","2023-04-10 18:00","취소","취소","매일"]
[351,"충북","충주","감곡가남#1 T/L","154kV 감곡-가남#1T/L 초기(정밀)점검","154kV 감곡-가남#1T/L No.1,2 정밀점검 및 No.3,4 초기점검","2023-04-08 07:30","2023-04-09 18:00","취소","취소","매일"]
[352,"충북","충주","신제천왕암#2 T/L","22~23년 충주전력지사 변전협력회사 총액공사","신제천S/S 신제천왕암#T/L GIS 보통점검","2023-04-20 10:00","2023-04-20 18:00","2023-04-20 10:00","2023-04-20 18:00","연속"]
[353,"충북","충주","신제천왕암#1 T/L","345kV 신제천-신충주 등 6개 T/L 송전피뢰기 설치공사","154kV 신제천-왕암#1 T/L No.6~37 송전피뢰기 설치공사","2023-04-03 07:00","2023-04-06 18:00","2023-04-03 07:00","2023-04-06 18:00","매일"]
[354,"충북","충주","신제천제천#1 T/L","345kV 신제천-신충주 등 6개 T/L 송전피뢰기 설치공사","154kV 신제천-제천#1 T/L No.1~27 송전피뢰기 설치공사","2023-04-04 07:00","2023-04-07 18:00","2023-04-04 07:00","2023-04-07 18:00","매일"]
[355,"충북","충주","제천영월#1 T/L","22~23년 충주전력지사 변전협력회사 총액공사","제천S/S 제천영월#1T/L GIS 보통점검","2023-04-27 10:00","2023-04-27 18:00","2023-04-27 10:00","2023-04-27 18:00","연속"]
[356,"충북","충주","제천영월#2 T/L","22~23년 충주전력지사 변전협력회사 총액공사","제천S/S 제천영월#2T/L GIS 보통점검","2023-04-28 10:00","2023-04-28 18:00","2023-04-28 10:00","2023-04-28 18:00","연속"]
[357,"충북","충주","충주S/S CB 6100","22-23년 충주전력지사 변전정비 총액공사","충주S/S 154kV #60-#65 모선보호반 대체","2023-04-03 09:00","2023-04-07 18:00","2023-04-03 09:00","2023-04-07 18:00","연속"]
[358,"대전세종충남","대전","남대전신흥#2 T/L","남대전S/S 154kV GIS교체공사(6차분)","6100, 627, PT GIS 교체","2023-04-21 16:00","2023-04-24 09:00","2023-04-21 16:00","2023-04-24 09:00","연속"]
[359,"대전세종충남","대전","신옥천남대전#4 T/L","[송전] 345kV 신옥천-청양 등 7개T/L 추락방지장치 설치공사","[송전] 154kV 신옥천-남대전T/L 추락방지장치 설치공사","2023-04-21 08:00","2023-04-21 18:00","취소","취소","연속"]
[360,"대전세종충남","대전","남대전신흥#2 T/L","남대전S/S 154kV GIS교체공사(6차분)","6100, 627, PT GIS 교체","2023-04-13 16:00","2023-04-14 09:00","2023-04-13 16:00","2023-04-14 09:00","연속"]
[361,"대전세종충남","대전","남대전S/S CB 6100","남대전S/S 154kV GIS교체공사(6차분)","6100, 627, PT GIS 교체","2023-04-03 08:00","2023-04-26 18:00","2023-04-03 08:00","2023-04-26 18:00","연속"]
[362,"대전세종충남","대전","신옥천남대전#2 T/L","남대전S/S 154kV GIS교체공사(6차분)","6100, 627, PT GIS 교체","2023-04-03 08:00","2023-04-26 18:00","2023-04-03 08:00","2023-04-26 18:00","연속"]
[363,"대전세종충남","대전","남대전S/S CB 6100","남대전S/S 154kV GIS교체공사(6차분)","6100, 627, PT GIS 교체","2023-04-03 08:00","2023-04-26 18:00","취소","취소","연속"]
[364,"대전세종충남","대전","논산은진#2 T/L","논산S/S 170kV GIS 보통점검(논산-은진#2)","논산S/S 170kV GIS 보통점검(논산-은진#2)","2023-04-18 09:00","2023-04-18 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[365,"대전세종충남","대전","논산은진#1 T/L","논산S/S 170kV GIS 보통점검(논산-은진#1)","논산S/S 170kV GIS 보통점검(논산-은진#1)","2023-04-17 09:00","2023-04-17 18:00","2023-04-17 09:00","2023-04-17 18:00","연속"]
[366,"대전세종충남","대전","팔봉두마#1 T/L","[송전] 154kV 팔봉-두마T/L 정밀점검","[송전] 154kV 팔봉-두마T/L 정밀점검","2023-04-17 08:00","2023-04-21 18:00","취소","취소","매일"]
[367,"대전세종충남","대전","신흥동대전#2 T/L","신흥S/S 170kV GIS 보통점검(신흥-동대전#2)","신흥S/S 170kV GIS 보통점검(신흥-동대전#2)","2023-04-25 09:00","2023-04-25 18:00","2023-04-25 09:00","2023-04-25 18:00","연속"]
[368,"대전세종충남","대전","신흥동대전#1 T/L","신흥S/S 170kV GIS 보통점검(신흥-동대전#1)","신흥S/S 170kV GIS 보통점검(신흥-동대전#1)","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[369,"대전세종충남","대전","남대전신흥#3 T/L","신흥S/S 170kV GIS 보통점검(신흥-동대전#3)","신흥S/S 170kV GIS 보통점검(신흥-동대전#3)","2023-04-26 09:00","2023-04-26 18:00","취소","취소","연속"]
[370,"대전세종충남","대전","신옥천추부#2 T/L","[송전] 345kV 신옥천-청양 등 7개T/L 추락방지장치 설치공사","[송전] 154kV 신옥천-추부T/L 추락방지장치 설치공사","2023-04-03 08:00","2023-04-14 18:00","취소","취소","매일"]
[371,"대전세종충남","대전","추부금산#1 T/L","[송전] 345kV 신옥천-청양 등 7개T/L 추락방지장치 설치공사","[송전] 154kV 추부-금산T/L 추락방지장치 설치공사","2023-04-10 08:00","2023-05-09 18:00","취소","취소","매일"]
[372,"대전세종충남","대전","추부금산#1 T/L","추부S/S 170kV GIS 보통점검(추부-금산#1)","추부S/S 170kV GIS 보통점검(추부-금산#1)","2023-04-10 09:00","2023-04-10 18:00","취소","취소","연속"]
[373,"대전세종충남","대전","신옥천추부#1 T/L","추부S/S 170kV GIS 보통점검(신옥천-추부#1)","추부S/S 170kV GIS 보통점검(신옥천-추부#1)","2023-04-12 09:00","2023-04-12 18:00","2023-04-12 16:00","2023-04-12 20:00","연속"]
[374,"대전세종충남","대전","신옥천추부#2 T/L","추부S/S 170kV GIS 보통점검(신옥천-추부#1)","추부S/S 170kV GIS 보통점검(신옥천-추부#1)","2023-04-13 09:00","2023-04-13 18:00","취소","취소","연속"]
[375,"대전세종충남","대전","추부금산#2 T/L","추부S/S 170kV GIS 보통점검(추부-금산#2)","추부S/S 170kV GIS 보통점검(추부-금산#2)","2023-04-11 09:00","2023-04-11 18:00","2023-04-11 16:00","2023-04-11 20:00","연속"]
[376,"대전세종충남","서산","당진T/P CB 6100","23년 서산P/O 변전협력회사 총액공사","당진화력S/S 154kV 6100 CB 보통점검","2023-04-05 09:00","2023-04-05 18:00","2023-04-05 09:00","2023-04-05 18:00","연속"]
[377,"대전세종충남","서산","대산석문#1 T/L","154kV 석문S/S #3M.Tr 증설공사","154kV 석문S/S #3M.Tr 증설공사","2023-04-13 14:00","2023-04-14 14:00","취소","취소","연속"]
[378,"대전세종충남","서산","대산석문#1 T/L","154kV 석문S/S #3M.Tr 증설공사","154kV 석문S/S #3M.Tr 증설공사","2023-04-20 14:00","2023-04-21 14:00","취소","취소","연속"]
[379,"대전세종충남","서산","석문당진화력#2 T/L","23년 서산P/O 변전협력회사 총액공사","석문S/S 154kV 석문-당진화력#2T/L CB 보통점검","2023-04-07 09:00","2023-04-07 18:00","2023-04-07 09:00","2023-04-07 18:00","연속"]
[380,"대전세종충남","서산","신당진S/S SEC CB 60610","효성제 170kV GIS 베어링 교체공사","신당진S/S 154kV #60-#61 SEC CB 베어링 교체","2023-04-11 09:00","2023-04-11 18:00","2023-04-11 09:00","2023-04-11 18:00","연속"]
[381,"대전세종충남","서산","신당진S/S SEC CB 65660","효성제 170kV GIS 베어링 교체공사","신당진S/S 154kV #65-#66 SEC CB 베어링 교체","2023-04-12 09:00","2023-04-12 18:00","2023-04-12 09:00","2023-04-12 18:00","연속"]
[382,"대전세종충남","서산","신당진S/S CB 6100","효성제 170kV GIS 베어링 교체공사","신당진S/S 154kV #60-#65 BUS TIE CB 베어링 교체","2023-04-13 09:00","2023-04-13 18:00","2023-04-13 09:00","2023-04-13 18:00","연속"]
[383,"대전세종충남","서산","신당진S/S CB 6200","효성제 170kV GIS 베어링 교체공사","신당진S/S 154kV #60-#65 BUS TIE CB 베어링 교체 및 보통점검","2023-04-19 09:00","2023-04-20 18:00","2023-04-19 09:00","2023-04-20 18:00","매일"]
[384,"대전세종충남","서산","신당진당진#2 T/L","효성제 170kV GIS 베어링 교체공사","신당진S/S 154kV #60-#65 BUS TIE CB 베어링 교체 및 보통점검","2023-04-18 09:00","2023-04-19 18:00","2023-04-18 09:00","2023-04-19 18:00","매일"]
[385,"대전세종충남","서산","서산태안 T/L","154kV 태안분기T/L 건설공사","154kV 태안분기T/L 건설공사 휴전작업 개요(No.57~태안S/T) ○ No.59 ~ No.62 : 상단 가선로 공중이동 ○ No.64 ~ 태안S/T : 서산-태안T/L 하단 전력선 연,긴선 ○ No.79 ~ 태안S/T : 가공지전 연,긴선 ○ 서산-태안T/L 하단 (수평)추락방지장치 설치 및 이동통로용 안전발판(하단암) 설치. 끝.","2023-04-09 07:00","2023-05-06 18:00","2023-04-09 07:00","2023-05-06 18:00","연속"]
[386,"대전세종충남","세종","덕진공주#2 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험 -공주S/S LA 초기점검 병행 -덕진S/S CVT 초기점검 병행","2023-04-04 10:00","2023-04-04 18:00","2023-04-04 10:00","2023-04-04 18:00","연속"]
[387,"대전세종충남","세종","덕진공주#1 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험 -공주S/S LA 초기점검 병행 -덕진S/S CVT 초기점검 병행","2023-04-03 10:00","2023-04-03 18:00","2023-04-03 10:00","2023-04-03 18:00","연속"]
[388,"대전세종충남","세종","신풍공주#1 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험","2023-04-05 10:00","2023-04-05 14:00","2023-04-05 10:00","2023-04-05 14:00","연속"]
[389,"대전세종충남","세종","신풍공주#2 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험","2023-04-05 14:00","2023-04-05 18:00","2023-04-05 14:00","2023-04-05 18:00","연속"]
[390,"대전세종충남","세종","덕진대화#1 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험","2023-04-06 10:00","2023-04-06 14:00","2023-04-06 10:00","2023-04-06 14:00","연속"]
[391,"대전세종충남","세종","덕진대화#2 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험","2023-04-06 14:00","2023-04-06 18:00","2023-04-06 14:00","2023-04-06 18:00","연속"]
[392,"대전세종충남","세종","세종월산#1 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○세종S/S 154kV GIS 초기점검 ○월산S/S 154kV GIS 차단기 조작시험","2023-04-10 10:00","2023-04-10 18:00","2023-04-10 10:00","2023-04-10 18:00","연속"]
[393,"대전세종충남","세종","세종월산#2 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○세종S/S 154kV GIS 초기점검 ○월산S/S 154kV GIS 차단기 조작시험","2023-04-11 10:00","2023-04-11 18:00","2023-04-11 10:00","2023-04-11 18:00","연속"]
[394,"대전세종충남","세종","세종월산#1 T/L","월산S/S 154kV 남부열병합#1,2T/L 증설공사","154kV 남부열병합#1,2T/L 증설 - 상체크(세종월산#1T/L 활용 무부하 가압)","2023-04-25 08:00","2023-04-25 18:00","2023-04-25 08:00","2023-04-25 18:00","연속"]
[395,"대전세종충남","세종","월산S/S CB 6100","월산S/S 154kV 남부열병합#1,2T/L 증설공사","월산S/S 154kV 남부열병합#1,2T/L 증설 - 모선보호반 연동시험","2023-04-25 08:00","2023-04-26 18:00","2023-04-25 08:00","2023-04-26 18:00","연속"]
[396,"대전세종충남","세종","월산S/S #1 BUS","월산S/S 154kV 남부열병합#1,2T/L 증설공사","월산S/S 154kV 남부열병합#1,2T/L 증설 - 상체크(세종-월산#1T/L 무부하 가압 활용)","2023-04-25 08:00","2023-04-25 18:00","2023-04-25 08:00","2023-04-25 18:00","연속"]
[397,"대전세종충남","세종","천안전의#1 T/L","[송전]154kV 천안-전의#1T/L 추락방지시설 설치공사","[송전]154kV 천안-전의#1T/L 추락방지시설 설치공사 - No.0.1(C/H), 1~8, 10~34(33기)","2023-04-27 07:00","2023-05-12 18:00","2023-04-27 07:00","2023-05-12 18:00","매일"]
[398,"대전세종충남","세종","조치원월산 T/L","[송전]154kV 조치원-월산T/L 추락방지시설 설치공사","[송전]154kV 조치원-월산T/L 추락방지시설 설치공사 - No.1, 5~56 (53기)","2023-04-03 07:00","2023-04-26 18:00","취소","취소","매일"]
[399,"대전세종충남","직할","동대전신탄진#1 T/L","[송전]154kV 동대전-신탄진T/L No.19~21 안전이격공사","154kV 동대전-신탄진T/L No.19~21 안전이격공사(철탑3기 신설) #1,#2T/L 양회선 동시휴전 신청","2023-04-01 08:00","2023-04-28 18:00","2023-04-01 08:00","2023-04-28 18:00","연속"]
[400,"대전세종충남","직할","동대전신탄진#2 T/L","[송전]154kV 동대전-신탄진T/L No.19~21 안전이격공사","154kV 동대전-신탄진T/L No.19~21 안전이격공사(철탑3기신설) #1,#2T/L 양회선 동시휴전 신청","2023-04-01 08:00","2023-04-28 18:00","2023-04-01 08:00","2023-04-28 18:00","연속"]
[401,"대전세종충남","직할","둔곡송강#1 T/L","2023년 직할 170kV GIS 정밀점검 공사","2023년 직할 170kV GIS 정밀점검 공사","2023-04-29 09:00","2023-04-30 18:00","2023-04-29 09:00","2023-04-30 18:00","연속"]
[402,"대전세종충남","천안","둔포추팔#1 T/L","둔포S/S 154kV 둔포-추팔#1T/L 보호계전기 성능개선","둔포S/S 154kV 둔포-추팔#1T/L 보호계전기 성능개선","2023-04-05 09:00","2023-04-05 18:00","2023-04-05 09:00","2023-04-05 18:00","연속"]
[403,"대전세종충남","천안","장재불당#1 T/L","불당S/S 154kV 장재-불당#1T/L 노후 보호배전반 교체","불당S/S 154kV 장재-불당#1T/L 노후 보호배전반 교체","2023-04-10 09:00","2023-04-14 18:00","2023-04-10 09:00","2023-04-14 18:00","연속"]
[404,"대전세종충남","천안","불당서천안#1 T/L","(3월취소시)불당S/S 154kV 불당-서천안#1T/L 전자변교체","(3월취소시)불당S/S 154kV 불당-서천안#1T/L 전자변교체","2023-04-05 09:00","2023-04-05 18:00","취소","취소","연속"]
[405,"대전세종충남","천안","불당서천안#2 T/L","(3월취소시)불당S/S 154kV 불당-서천안#2T/L 전자변교체","(3월취소시)불당S/S 154kV 불당-서천안#2T/L 전자변교체","2023-04-06 09:00","2023-04-06 18:00","취소","취소","연속"]
[406,"대전세종충남","천안","장재불당#2 T/L","불당S/S 154kV 장재-불당#2T/L 노후 보호배전반 교체","불당S/S 154kV 장재-불당#2T/L 노후 보호배전반 교체","2023-04-24 09:00","2023-04-28 18:00","2023-04-24 09:00","2023-04-28 18:00","연속"]
[407,"대전세종충남","천안","서천안탕정#1 T/L","서천안S/S 154kV 서천안-탕정#1T/L GIS 보통점검","서천안S/S 154kV 서천안-탕정#1T/L GIS 보통점검","2023-04-12 09:00","2023-04-12 18:00","2023-04-12 09:00","2023-04-12 18:00","연속"]
[408,"대전세종충남","천안","서천안탕정#2 T/L","서천안S/S 154kV 서천안-탕정#2T/L GIS 보통점검","서천안S/S 154kV 서천안-탕정#2T/L GIS 보통점검","2023-04-13 09:00","2023-04-13 18:00","2023-04-13 09:00","2023-04-13 18:00","연속"]
[409,"대전세종충남","천안","둔포석곡#1 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사 등","○ 수직·수평 추락방지장치 설치공사 - 154kV 둔포-석곡T/L No. 2~10(9기) ※ 주말작업 없음.","2023-04-21 08:00","2023-04-21 18:00","2023-04-21 08:00","2023-04-21 18:00","연속"]
[410,"대전세종충남","천안","신온양석곡#2 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사 등","○ 수직·수평 추락방지장치 설치공사 - 154kV 신온양-석곡T/L No. 1~18(12기) - 154kV 신온양-한샘T/L No. 2~7(6기)","2023-04-27 08:00","2023-04-28 18:00","2023-04-27 08:00","2023-04-28 18:00","매일"]
[411,"대전세종충남","천안","신온양석곡#1 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사 등","○ 수직·수평 추락방지장치 설치공사 - 154kV 신온양-석곡T/L No. 1~18(12기) - 154kV 신온양-한샘T/L No. 2~7(6기)","2023-04-25 08:00","2023-04-26 18:00","2023-04-25 08:00","2023-04-26 18:00","매일"]
[412,"대전세종충남","천안","둔포석곡#2 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사 등","○ 수직·수평 추락방지장치 설치공사 - 154kV 둔포-석곡T/L No. 2~10(9기) ※ 주말작업 없음.","2023-04-24 08:00","2023-04-24 18:00","2023-04-24 08:00","2023-04-24 18:00","연속"]
[413,"대전세종충남","천안","신탕정탕정#2 T/L","신탕정,탕정SS 154kV 신탕정탕정#2TL GIS 보통점검","신탕정,탕정SS 154kV 신탕정탕정#2TL GIS 보통점검","2023-04-25 09:00","2023-04-25 18:00","2023-04-28 09:00","2023-04-28 18:00","연속"]
[414,"대전세종충남","천안","신탕정탕정#1 T/L","신탕정,탕정SS 154kV 신탕정탕정#1TL GIS 보통점검","신탕정,탕정SS 154kV 신탕정탕정#1TL GIS 보통점검","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[415,"대전세종충남","천안","아산인주#2 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 아산인주#1,#2T/L 횡단을 위한 보호망 설치(양회선 휴전) 및 와이어 포설 ※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-15 08:00","2023-04-15 12:00","2023-04-15 08:00","2023-04-15 12:00","연속"]
[416,"대전세종충남","천안","아산인주#1 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 아산인주#1,#2T/L 횡단을 위한 보호망 설치(양회선 휴전) 및 와이어 포설 ※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-15 08:00","2023-04-15 12:00","2023-04-15 08:00","2023-04-15 12:00","연속"]
[417,"대전세종충남","천안","아산인주#1 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 아산인주#1,#2T/L 횡단을 위한 보호망 철거(양회선 휴전)※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-30 08:00","2023-04-30 12:00","2023-04-30 08:00","2023-04-30 12:00","연속"]
[418,"대전세종충남","천안","인주불당#2 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 와이어 포설 및 연긴선 작업 ※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-15 13:00","2023-04-15 18:00","2023-04-15 13:00","2023-04-15 18:00","매일"]
[419,"대전세종충남","천안","아산인주#2 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 아산인주#1,#2T/L 횡단을 위한 보호망 철거(양회선 휴전)※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-30 08:00","2023-04-30 12:00","2023-04-30 08:00","2023-04-30 12:00","연속"]
[420,"대전세종충남","천안","인주불당#1 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 와이어 포설 및 연긴선 작업 ※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-15 13:00","2023-04-15 18:00","2023-04-15 13:00","2023-04-15 18:00","매일"]
[421,"대전세종충남","천안","인주불당#1 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 와이어 포설 및 연긴선 작업 ※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-29 08:00","2023-04-29 18:00","2023-04-29 08:00","2023-04-29 18:00","연속"]
[422,"대전세종충남","천안","인주불당#2 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 와이어 포설 및 연긴선 작업 ※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-29 08:00","2023-04-29 18:00","2023-04-29 08:00","2023-04-29 18:00","연속"]
[423,"대전세종충남","천안","인주불당#1 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 와이어 포설 및 연긴선 작업 ※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-22 08:00","2023-04-23 18:00","2023-04-22 08:00","2023-04-23 18:00","매일"]
[424,"대전세종충남","천안","인주불당#2 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 와이어 포설 및 연긴선 작업 ※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-16 08:00","2023-04-23 18:00","2023-04-16 08:00","2023-04-23 18:00","매일"]
[425,"대전세종충남","천안","인주불당#1 T/L","345kV북당진-신탕정T/L 건설공사","No.47 ~ 48 가선공사 - 와이어 포설 및 연긴선 작업 ※ 휴전선로에 승탑작업자 없음(거래소 긴급 가압 요청시 협조가능)","2023-04-16 08:00","2023-04-16 18:00","2023-04-16 08:00","2023-04-16 18:00","매일"]
[426,"대전세종충남","천안","풍세장재#2 T/L","풍세,장재S/S 154kV 풍세-장재#2T/L 보호계전기 성능개선","풍세,장재S/S 154kV 풍세-장재#2T/L 보호계전기 성능개선","2023-04-04 09:00","2023-04-04 18:00","2023-04-04 09:00","2023-04-04 18:00","연속"]
[427,"대전세종충남","천안","풍세장재#1 T/L","풍세,장재S/S 154kV 풍세-장재#1T/L 보호계전기 성능개선","풍세,장재S/S 154kV 풍세-장재#1T/L 보호계전기 성능개선","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[428,"대전세종충남","천안","신온양한샘#1 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사 등","○ 수직·수평 추락방지장치 설치공사 - 154kV 신온양-석곡T/L No. 2~7(6기) - 154kV 신온양-한샘T/L No. 2~7(6기)","2023-04-25 08:00","2023-04-26 18:00","2023-04-25 08:00","2023-04-26 18:00","매일"]
[429,"대전세종충남","천안","신온양한샘#1 T/L","한샘S/S 154kV 모선구분차단기 증설공사","한샘S/S 154kV 모선구분차단기 증설공사[안전이격]","2023-04-03 09:00","2023-04-05 18:00","2023-04-10 09:00","2023-04-12 18:00","연속"]
[430,"대전세종충남","천안","신온양한샘#2 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사 등","○ 수직·수평 추락방지장치 설치공사 - 154kV 신온양-석곡T/L No. 2~7(6기) - 154kV 신온양-한샘T/L No. 2~7(6기)","2023-04-27 08:00","2023-04-28 18:00","2023-04-27 08:00","2023-04-28 18:00","매일"]
[431,"대전세종충남","청양","청양관창#2 T/L","154kV GIS 차단기 부동작예방 조작시험","154kV GIS 차단기 부동작예방 조작시험","2023-04-13 09:00","2023-04-13 18:00","취소","취소","연속"]
[432,"대전세종충남","청양","청양관창#1 T/L","154kV GIS 차단기 부동작예방 조작시험","154kV GIS 차단기 부동작예방 조작시험","2023-04-12 09:00","2023-04-12 18:00","취소","취소","연속"]
[433,"대전세종충남","청양","신서천대천#1 T/L","[송전] 154kV 대천S/S 인출T/L 지중화공사","- 선종 및 길이 : XLPE 2,500㎟ × 4C, 0.136km - 휴전작업내용 : 가공-지중 연결 및 GIS 가압","2023-04-24 09:00","2023-04-28 18:00","취소","취소","연속"]
[434,"대전세종충남","청양","관창대천#1 T/L","[송전] 154kV 대천S/S 인출T/L 지중화공사","- 선종 및 길이 : XLPE 2,500㎟ × 4C, 0.136km - 휴전작업내용 : 가공-지중 연결 및 GIS 가압","2023-04-24 09:00","2023-04-28 18:00","취소","취소","연속"]
[435,"대전세종충남","청양","신서천옥산#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2023-04-25 09:00","2023-04-25 18:00","취소","취소","연속"]
[436,"대전세종충남","청양","동군산장항#2 T/L","[송전] 154kV 옥산-장항#1T/L 수평 추락방지장치 설치공사","345kV 청양-보령 등 11개T/L 철탑 추락방지장치 설치공사","2023-04-19 08:00","2023-04-21 18:00","취소","취소","매일"]
[437,"대전세종충남","청양","청양신풍#1 T/L","[송전] 154kV 청양-신풍#1T/L 수평 추락방지장치 설치공사","345kV 청양-보령 등 11개T/L 철탑 추락방지장치 설치공사","2023-04-24 08:00","2023-04-28 18:00","2023-04-24 08:00","2023-04-28 18:00","매일"]
[438,"전북","군산","군산영등#2 T/L","154kV 군산-이리T/L 정밀점검","가공송전선로 전선, 금구류, 철탑 등 정밀점검시행 ※ 154kV 군산-이리T/L 병가선로 휴전시행","2023-04-17 08:00","2023-04-20 17:00","2023-04-17 08:00","2023-04-19 17:00","매일"]
[439,"전북","군산","군산영등#1 T/L","154kV 군산-이리T/L 정밀점검","가공송전선로 전선, 금구류, 철탑 등 정밀점검시행 ※ 154kV 군산-이리T/L 병가선로 휴전시행","2023-04-10 08:00","2023-04-13 17:00","2023-04-10 08:00","2023-04-12 17:00","매일"]
[440,"전북","군산","군산이리#1 T/L","154kV 군산-이리T/L 정밀점검","가공송전선로 전선, 금구류, 철탑등 정밀점검 시행","2023-04-10 08:00","2023-04-13 18:00","취소","취소","매일"]
[441,"전북","군산","군산이리#2 T/L","154kV 군산-이리T/L 정밀점검","가공송전선로 전선, 금구류, 철탑등 정밀점검 시행","2023-04-17 08:00","2023-04-20 18:00","취소","취소","매일"]
[442,"전북","군산","왕궁봉동#2 T/L","군산P/O 154kV 차단기 보통점검","왕궁S/S 154kV 왕궁-봉동#2T/L 차단기 보통점검","2023-04-25 09:00","2023-04-25 18:00","취소","취소","연속"]
[443,"전북","군산","팔봉왕궁#1 T/L","군산P/O 154kV 차단기 보통점검","왕궁S/S 154kV 왕궁-팔봉#1T/L 차단기 보통점검","2023-04-27 09:00","2023-04-27 18:00","취소","취소","연속"]
[444,"전북","군산","팔봉왕궁#2 T/L","군산P/O 154kV 차단기 보통점검","왕궁S/S 154kV 왕궁-팔봉#2T/L 차단기 보통점검","2023-04-26 09:00","2023-04-26 18:00","취소","취소","연속"]
[445,"전북","군산","왕궁봉동#1 T/L","군산P/O 154kV 차단기 보통점검","왕궁S/S 154kV 왕궁-봉동#1T/L 차단기 보통점검","2023-04-24 09:00","2023-04-24 18:00","취소","취소","연속"]
[446,"전북","김제","정주고창#1 T/L","154kV 소성분기T/L 건설공사","- 작업내용 : #1T/L 가철탑 조립 및 가선로 구성 - 위 치 : 정읍시 소성면 등계리 5-3 일원 - 규 모 : P330㎟×S×4C(0.422km, 지지물 3기)","2023-04-03 07:00","2023-04-05 18:00","취소","취소","연속"]
[447,"전북","김제","정주고창#1 T/L","154kV 소성분기T/L 건설공사","- 작업내용 : #1T/L 본선로 구성 및 가철탑 철거 - 위 치 : 정읍시 소성면 등계리 5-3 일원 - 규 모 : P330㎟×S×4C(0.422km, 지지물 3기)","2023-04-10 07:00","2023-04-13 18:00","취소","취소","연속"]
[448,"전북","김제","정주고창#2 T/L","154kV 소성분기T/L 건설공사","- 작업내용 : 본철탑 조립 및 #2T/L 본선로 구성 - 위 치 : 정읍시 소성면 등계리 5-3 일원 - 규 모 : P330㎟×S×4C(0.422km, 지지물 3기)","2023-04-06 07:00","2023-04-08 18:00","취소","취소","연속"]
[449,"전북","김제","담양김제 T/L","김제S/S 170kV 차단기 보통점검","김제S/S 170kV 차단기 보통점검","2023-04-19 09:00","2023-04-19 18:00","2023-04-19 09:00","2023-04-19 18:00","연속"]
[450,"전북","김제","백산김제#2 T/L","김제S/S 170kV 차단기 보통점검","김제S/S 170kV 차단기 보통점검","2023-04-21 09:00","2023-04-21 18:00","2023-04-21 09:00","2023-04-21 18:00","연속"]
[451,"전북","김제","백산김제#1 T/L","김제S/S 170kV 차단기 보통점검","김제S/S 170kV 차단기 보통점검","2023-04-20 09:00","2023-04-20 18:00","2023-04-20 09:00","2023-04-20 18:00","연속"]
[452,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-04-26 08:00","2023-05-03 18:00","2023-04-26 08:00","2023-05-03 18:00","연속"]
[453,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-04-24 08:00","2023-04-25 18:00","2023-04-24 08:00","2023-04-25 18:00","연속"]
[454,"전북","김제","신김제전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-04-26 08:00","2023-05-02 18:00","2023-04-26 08:00","2023-05-02 18:00","연속"]
[455,"전북","김제","신김제전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-04-24 08:00","2023-04-25 18:00","2023-04-24 08:00","2023-04-25 18:00","연속"]
[456,"전북","김제","정공S/S SEC CB 60610","정공S/S 170kV GIS 차단기 보통점검","정공S/S 170kV GIS 차단기 보통점검","2023-04-26 09:00","2023-04-26 18:00","2023-04-26 09:00","2023-04-26 18:00","연속"]
[457,"전북","김제","정공S/S SEC CB 65660","정공S/S 170kV GIS 차단기 보통점검","정공S/S 170kV GIS 차단기 보통점검","2023-04-27 09:00","2023-04-27 18:00","2023-04-27 09:00","2023-04-27 18:00","연속"]
[458,"전북","김제","정공S/S CB 6200","정공S/S 170kV GIS 차단기 보통점검","정공S/S 170kV GIS 차단기 보통점검","2023-04-25 09:00","2023-04-25 18:00","2023-04-25 09:00","2023-04-25 18:00","연속"]
[459,"전북","김제","정공S/S CB 6100","정공S/S 170kV GIS 차단기 보통점검","정공S/S 170kV GIS 차단기 보통점검","2023-04-24 09:00","2023-04-24 18:00","2023-04-24 09:00","2023-04-24 18:00","연속"]
[460,"전북","김제","정공칠보HP T/L","154kV 정주-고창 등 4개T/L 추락방지시설 설치공사","154kV 정공분기T/L 수평추락방지장치 설치(14기)","2023-04-17 08:00","2023-04-19 18:00","취소","취소","연속"]
[461,"전북","김제","정공정주#1 T/L","154kV 정주-고창 등 4개T/L 추락방지시설 설치공사","154kV 정공분기T/L 수평추락방지장치 설치(14기)","2023-04-17 08:00","2023-04-19 18:00","취소","취소","연속"]
[462,"전북","김제","정공담양 T/L","정공S/S 170kV 차단기 보통점검","정공S/S 170kV 차단기 보통점검","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[463,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","No.36∼39 전력선 연긴선","2023-04-08 08:00","2023-04-12 17:00","2023-04-08 08:00","2023-04-12 17:00","연속"]
[464,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","No.36∼39 전력선 연긴선","2023-04-03 08:00","2023-04-07 17:00","2023-04-03 08:00","2023-04-07 17:00","연속"]
[465,"전북","직할","무주진안 T/L","'22년~'23년 가공송전 협력회사 총액공사","□ 작업대상 ○ 154kV 무주분기(무주-진안)T/L No.1~45 ○ 154kV 북전주-진안(무주-진안)T/L No.105~175 □ 작업내용 : 피뢰기 설치","2023-04-10 07:00","2023-04-21 18:00","2023-04-10 15:00","2023-04-21 18:00","매일"]
[466,"전북","직할","북전주봉동#1 T/L","'23년 전북직할 변전협력 총액공사","GIS 조작시험","2023-04-27 15:00","2023-04-27 18:00","취소","취소","연속"]
[467,"전북","직할","북전주봉동#2 T/L","'23년 전북직할 변전협력 총액공사","GIS 조작시험","2023-04-28 15:00","2023-04-28 18:00","취소","취소","연속"]
[468,"전북","직할","탄소전주#2 T/L","'23년 전북직할 변전협력 총액공사","GIS 보통점검","2023-04-04 15:00","2023-04-04 20:00","2023-04-04 15:00","2023-04-04 20:00","연속"]
[469,"전북","직할","전주서곡#1 T/L","전주,서곡S/S 전주-서곡#1T/L 보통점검","보통점검","2023-04-22 09:00","2023-04-22 18:00","취소","취소","연속"]
[470,"전북","직할","전주서곡#2 T/L","전주,서곡S/S 전주-서곡#2T/L 보통점검","보통점검","2023-04-23 09:00","2023-04-23 18:00","취소","취소","연속"]
[471,"전북","직할","신김제전주#2 T/L","'23년 전북직할 변전협력 총액공사","GIS 보통점검","2023-04-14 15:00","2023-04-14 20:00","2023-04-14 15:00","2023-04-14 20:00","연속"]
[472,"광주전남","강진","완도강진 T/L","154KV 남창-완도T/L 용량증대 전선교체공사","ㅇ구간 : 154kV 남창-완도 #2T/L No.1~48 ㅇ경간 : 16.9km 전선교체 ㅇ시공사 : 신한전력(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 520SQ로 전량교체)","2023-04-17 09:00","2023-05-27 18:00","2023-04-17 09:00","2023-05-27 18:00","연속"]
[473,"광주전남","강진","진도진도CS#2 T/L","진도-진도CS#2T/L 지멘스 87+21 계전기 교체(임시분→수리분)","진도-진도CS#2T/L 지멘스 87+21 계전기 교체(임시분→수리분) - 30분 내 즉시가압 가능","2023-04-20 10:00","2023-04-20 17:00","2023-04-20 10:00","2023-04-20 17:00","연속"]
[474,"광주전남","강진","해남제주HVDC#1 T/L (제1연계선)","23년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1Pole 변환설비 연차점검 -Thyristor Valve C.Tr, AC Filter, 공조설비, 냉각설비, 제어설비 등","2023-04-25 09:00","2023-05-09 18:00","2023-04-25 09:00","2023-05-09 18:00","연속"]
[475,"광주전남","강진","해남C/S #1 Sh.C CB","23년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2023-04-30 09:00","2023-05-09 18:00","2023-04-30 09:00","2023-05-09 18:00","연속"]
[476,"광주전남","강진","해남제주HVDC#2 T/L (제1연계선)","23년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #2Pole 변환설비 연차점검 -Thyristor Valve C.Tr, AC Filter, 공조설비, 냉각설비, 제어설비 등","2023-04-30 09:00","2023-05-14 18:00","2023-04-30 09:00","2023-05-14 18:00","연속"]
[477,"광주전남","강진","해남C/S #1 HPF CB","23년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2023-04-30 09:00","2023-05-09 18:00","2023-04-30 09:00","2023-05-09 18:00","연속"]
[478,"광주전남","강진","해남C/S #1 DTF CB","23년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2023-04-30 09:00","2023-05-09 18:00","2023-04-30 09:00","2023-05-09 18:00","연속"]
[479,"광주전남","강진","해남C/S #2 DTF CB","23년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2023-04-30 09:00","2023-05-09 18:00","2023-04-30 09:00","2023-05-09 18:00","연속"]
[480,"광주전남","강진","해남C/S #2 Sh.C CB","23년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2023-04-30 09:00","2023-05-09 18:00","2023-04-30 09:00","2023-05-09 18:00","연속"]
[481,"광주전남","강진","해남C/S #2 HPF CB","23년도 #1HVDC 변환설비 위탁정비공사 연차점검","#1HVDC(해남, 제주C/S) #1,2Pole 변환설비 연차점검 - 필터설비","2023-04-30 09:00","2023-05-09 18:00","2023-04-30 09:00","2023-05-09 18:00","연속"]
[482,"광주전남","광주","계림승주#1 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #1DS 무부하 가압","2023-04-07 15:00","2023-04-07 18:00","2023-04-07 15:00","2023-04-07 18:00","연속"]
[483,"광주전남","광주","계림S/S #60 BUS","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #1DS 무부하 가압","2023-04-07 15:00","2023-04-07 18:00","2023-04-07 15:00","2023-04-07 18:00","연속"]
[484,"광주전남","광주","계림S/S SEC CB 60610","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #1DS 무부하 가압","2023-04-07 15:00","2023-04-07 18:00","2023-04-07 15:00","2023-04-07 18:00","연속"]
[485,"광주전남","광주","계림승주#1 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) -BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #65BUS 및 Bay 신설분 무부하 가압","2023-04-06 15:00","2023-04-07 15:00","2023-04-06 15:00","2023-04-07 15:00","연속"]
[486,"광주전남","광주","남광주금천#1 T/L","세니온 보호계전기 일제 성능개선 시행(신화순)","세니온 보호계전기 일제 성능개선 시행 - 남광주S/S 남광주-금천#1,2T/L","2023-04-10 09:00","2023-04-10 14:00","2023-04-10 09:00","2023-04-10 14:00","연속"]
[487,"광주전남","광주","남광주금천#2 T/L","세니온 보호계전기 일제 성능개선 시행(신화순)","세니온 보호계전기 일제 성능개선 시행 - 남광주S/S 남광주-금천#1,2T/L","2023-04-10 14:00","2023-04-10 18:00","2023-04-10 14:00","2023-04-10 18:00","연속"]
[488,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2023-04-17 15:00","2023-04-18 15:00","2023-04-17 15:00","2023-04-18 15:00","연속"]
[489,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2023-04-18 17:00","2023-04-19 17:00","2023-04-18 17:00","2023-04-19 17:00","연속"]
[490,"광주전남","광주","담양일곡#1 T/L","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차)","담양S/S 154kV 이하 GIS 교체(SA화)공사(2차) - 정공-담양T/L, #2M.Tr","2023-04-09 15:00","2023-04-10 15:00","2023-04-09 15:00","2023-04-10 15:00","연속"]
[491,"광주전남","광주","신광주장성#1 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 신광주-장성#1T/L 1~74호 정밀점검","2023-04-17 07:00","2023-04-21 18:00","2023-04-17 07:00","2023-04-21 18:00","매일"]
[492,"광주전남","광주","신광주장성#2 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 신광주-장성#2T/L 1~74호 정밀점검","2023-04-24 07:00","2023-04-28 18:00","2023-04-24 07:00","2023-04-28 18:00","매일"]
[493,"광주전남","광주","신광주일곡#2 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 신광주-장성#2T/L 1~74호 정밀점검","2023-04-24 07:00","2023-04-24 18:00","2023-04-24 07:00","2023-04-24 18:00","연속"]
[494,"광주전남","광주","신광주일곡#1 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 신광주-장성#1T/L 1~74호 정밀점검","2023-04-17 07:00","2023-04-17 18:00","2023-04-17 07:00","2023-04-17 18:00","연속"]
[495,"광주전남","광주","신화순나주#1 T/L","세니온 보호계전기 일제 성능개선 시행(신화순)","세니온 보호계전기 일제 성능개선 시행 - 신화순S/S 신화순-나주#1,2T/L","2023-04-11 09:00","2023-04-11 14:00","2023-04-11 09:00","2023-04-11 14:00","연속"]
[496,"광주전남","광주","신화순나주#2 T/L","세니온 보호계전기 일제 성능개선 시행(신화순)","세니온 보호계전기 일제 성능개선 시행 - 신화순S/S 신화순-나주#1,2T/L","2023-04-11 14:00","2023-04-11 18:00","2023-04-11 14:00","2023-04-11 18:00","연속"]
[497,"광주전남","광주","장성영광#2 T/L","154kV 장성-영광T/L 안전이격확보공사","154kV 장성-영광T/L 안전이격확보공사","2023-04-02 07:00","2023-04-03 18:00","취소","취소","연속"]
[498,"광주전남","광주","계림충장#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 계림-충장#1T/L GIS 보통점검","2023-04-14 09:00","2023-04-14 18:00","2023-04-14 09:00","2023-04-14 18:00","연속"]
[499,"광주전남","광주","계림충장#3 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 계림-충장#3T/L GIS 보통점검","2023-04-21 09:00","2023-04-21 18:00","2023-04-21 09:00","2023-04-21 18:00","연속"]
[500,"광주전남","광주","계림충장#2 T/L","22~23년 광주전력지사 변전협력회사 총액공사","충장S/S 계림-충장#2T/L GIS 보통점검","2023-04-19 09:00","2023-04-19 18:00","2023-04-19 09:00","2023-04-19 18:00","연속"]
[501,"광주전남","목포","엄다무안햇빛#2 T/L","22-23년 목포전력지사 변전협력회사 총액공사","22-23년 목포전력지사 변전협력회사 총액공사 즉시 가압 가능","2023-04-04 09:00","2023-04-04 18:00","취소","취소","연속"]
[502,"광주전남","목포","엄다무안햇빛#1 T/L","22-23년 목포전력지사 변전협력회사 총액공사","22-23년 목포전력지사 변전협력회사 총액공사 즉시 가압 가능","2023-04-03 09:00","2023-04-03 18:00","취소","취소","연속"]
[503,"광주전남","목포","남악북항#1 T/L","22-23년 목포전력지사 변전협력회사 총액공사","22-23년 목포전력지사 변전협력회사 총액공사 즉시 가압 가능","2023-04-05 09:00","2023-04-05 18:00","취소","취소","연속"]
[504,"광주전남","목포","나주엄다#1 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 엄다-목포#2T/L 철탑 정밀점검","2023-04-03 09:00","2023-04-07 18:00","취소","취소","매일"]
[505,"광주전남","순천","보성벌교 T/L","154kV 벌교-고흥T/L 선종교체공사(1공구)","휴전목적 : 154kV 벌교-고흥T/L 4회선구간 선종교체작업 안전거리 확보 대상공사 - 구 간 : 154kV 벌교-고흥T/L 16.89km(벌교변전소 ∼ No.49) - 내 용 : 전력선 교체 ACSR/AW 410㎟ × S → ASCC/TW 520㎟ × S","2023-04-10 07:00","2023-04-13 18:00","2023-04-10 07:00","2023-04-13 18:00","매일"]
[506,"광주전남","순천","벌교고흥#1 T/L","154kV 벌교-고흥T/L 선종교체공사","154kV 벌교-고흥T/L No.1~고흥S/S (37.2km) ACSR/AW 410sq를 ASCC/TW 520sq로 교체","2023-04-10 07:00","2023-05-26 18:00","2023-04-10 07:00","2023-05-26 18:00","연속"]
[507,"광주전남","순천","벌교고흥#1 T/L","154kV 벌교-고흥T/L 선종교체공사","154kV 벌교-고흥T/L No.1~고흥S/S (37.2km) ACSR/AW 410sq를 ASCC/TW 520sq로 교체","2023-04-10 07:00","2023-05-26 18:00","취소","취소","연속"]
[508,"광주전남","순천","장흥벌교 T/L","154kV 벌교-고흥T/L 선종교체공사(1공구)","휴전목적 : 154kV 벌교-고흥T/L 4회선구간 선종교체작업 안전거리 확보 대상공사 - 구 간 : 154kV 벌교-고흥T/L 16.89km(벌교변전소 ∼ No.49) - 내 용 : 전력선 교체 ACSR/AW 410㎟ × S → ASCC/TW 520㎟ × S","2023-04-10 07:00","2023-04-15 18:00","2023-04-10 07:00","2023-04-15 18:00","연속"]
[509,"광주전남","순천","여수소라#1 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-04-10 09:00","2023-04-11 18:00","취소","취소","연속"]
[510,"광주전남","순천","여수소라#2 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-04-12 09:00","2023-04-13 18:00","취소","취소","연속"]
[511,"광주전남","순천","호남TP여수TP#2 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-04-05 09:00","2023-04-06 18:00","취소","취소","연속"]
[512,"광주전남","순천","호남TP여수TP#1 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-04-03 09:00","2023-04-04 18:00","취소","취소","연속"]
[513,"광주전남","순천","여수TP여천#1 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-04-17 09:00","2023-04-20 18:00","취소","취소","연속"]
[514,"광주전남","순천","율촌화치#2 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-04-10 09:00","2023-04-13 18:00","2023-04-10 09:00","2023-04-13 18:00","연속"]
[515,"광주전남","순천","율촌화치#1 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-04-03 09:00","2023-04-06 18:00","2023-04-03 09:00","2023-04-06 18:00","연속"]
[516,"광주전남","순천","순천율촌#1 T/L","율촌S/S 154kV #3M.Tr 증설공사[안전이격 확보]","율촌S/S 154kV #3M.Tr 증설공사 GIS 설치, M.Tr 모선배선 안전이격 확보 휴전 신청(매일 휴전 가능, 즉시 가압 가능)","2023-04-03 09:00","2023-04-07 18:00","2023-04-03 09:00","2023-04-07 18:00","매일"]
[517,"광주전남","순천","순천율촌#2 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-04-26 09:00","2023-04-27 18:00","2023-04-26 09:00","2023-04-27 18:00","연속"]
[518,"광주전남","순천","순천율촌#1 T/L","22년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-04-24 09:00","2023-04-25 18:00","2023-04-24 09:00","2023-04-25 18:00","연속"]
[519,"광주전남","직할","평동왕곡#1 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (평동-왕곡#1T/L 4호~94호)","2023-04-10 09:00","2023-04-25 18:00","2023-04-10 09:00","2023-04-25 18:00","매일"]
[520,"광주전남","직할","매월화정#1 T/L","2022~23년 직할 변전협력회사 총액공사","170kV GIS 보통점검","2023-04-17 14:00","2023-04-17 18:00","2023-04-17 14:00","2023-04-17 18:00","연속"]
[521,"광주전남","직할","농성화정#1 T/L","2022~23년 직할 변전협력회사 총액공사","170kV GIS 보통점검","2023-04-17 09:00","2023-04-17 14:00","2023-04-17 09:00","2023-04-17 14:00","연속"]
[522,"대구","경산","신경산노변 T/L","22~23년 경산PO 변전협력회사 총액공사","- GIS 보통점검","2023-04-04 09:30","2023-04-04 18:00","취소","취소","연속"]
[523,"대구","경산","안심대구그린파워#1 T/L","'23년 345, 154kV GIS 보통점검 및 154kV 정밀점검 공사","154kV GIS 정밀점검","2023-04-04 09:00","2023-04-05 18:00","2023-04-04 09:00","2023-04-05 18:00","연속"]
[524,"대구","경산","안심대구그린파워#2 T/L","'23년 345, 154kV GIS 보통점검 및 154kV 정밀점검 공사","154kV GIS 정밀점검","2023-04-06 09:00","2023-04-07 18:00","2023-04-06 09:00","2023-04-07 18:00","연속"]
[525,"대구","경산","안심대구그린파워#1 T/L","'23년 345, 154kV GIS 보통점검 및 154kV 정밀점검 공사","154kV GIS 정밀점검(6100CB 무부하가압용 선로)","2023-04-11 15:00","2023-04-11 18:00","2023-04-11 15:00","2023-04-11 18:00","연속"]
[526,"대구","경산","효목안심#2 T/L","22~23년 경산PO 변전협력회사 총액공사","- 차단기 조작시험","2023-04-11 14:00","2023-04-11 18:00","2023-04-11 14:00","2023-04-11 18:00","연속"]
[527,"대구","경산","효목안심#1 T/L","22~23년 경산PO 변전협력회사 총액공사","- 차단기 조작시험","2023-04-11 09:30","2023-04-11 14:00","2023-04-11 09:30","2023-04-11 14:00","연속"]
[528,"대구","경산","신경산진량 T/L","22~23년 경산PO 변전협력회사 총액공사","- 장기미동작 차단기 조작시험","2023-04-17 09:30","2023-04-17 18:00","취소","취소","연속"]
[529,"대구","경산","진량노변 T/L","22-23년 경산P/O 변전협력회사 총액공사","- 진량 : GIS 보통점검 - 노변 : 차단기 조작시험","2023-04-03 09:30","2023-04-03 18:00","2023-04-15 09:30","2023-04-15 18:00","연속"]
[530,"대구","달성","고령다산#2 T/L","고령-다산#2T/L OPGW 항공장애표시구 설치공사","OPGW 항공장애표시구 신규설치","2023-04-27 08:00","2023-04-28 18:00","2023-04-27 08:00","2023-04-28 18:00","연속"]
[531,"대구","달성","고령서구지#2 T/L","CVT, LA 보통점검","CVT, LA 보통점검","2023-04-18 09:00","2023-04-18 18:00","2023-04-18 09:00","2023-04-18 18:00","연속"]
[532,"대구","달성","고령다산#1 T/L","2022~23년 달성전력지사 가공송전 협력회사 총액공사","항공장애표시구 설치공사 및 폴리머 점퍼지지애자 교체공사","2023-04-25 07:00","2023-04-26 18:00","2023-04-25 07:00","2023-04-26 18:00","연속"]
[533,"대구","달성","논공달성#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 논공-달성T/L 수평 추락방지장치 설치공사","2023-04-24 07:00","2023-04-27 18:00","2023-04-24 07:00","2023-04-27 18:00","연속"]
[534,"대구","달성","논공달성#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 논공-달성T/L 수평 추락방지장치 설치공사","2023-04-11 07:00","2023-04-14 18:00","2023-04-11 07:00","2023-04-14 18:00","연속"]
[535,"대구","달성","다사S/S CB 6100","모선보호반 대체관련 휴전","모선보호반 대체관련 휴전","2023-04-11 09:00","2023-04-13 18:00","2023-04-11 09:00","2023-04-13 18:00","연속"]
[536,"대구","달성","다사달서 T/L","모선보호반 대체관련[TEST선로]","모선보호반 대체관련[TEST선로]","2023-04-13 14:30","2023-04-13 15:00","2023-04-13 14:30","2023-04-13 15:00","연속"]
[537,"대구","달성","다산강창#1 T/L","CB동작특성시험 및 LA카운터 교체","CB동작특성시험 및 LA카운터 교체","2023-04-05 09:00","2023-04-05 14:00","취소","취소","연속"]
[538,"대구","달성","다산강창#2 T/L","CB동작특성시험","CB동작특성시험","2023-04-05 14:00","2023-04-05 18:00","취소","취소","연속"]
[539,"대구","달성","대구봉덕#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-봉덕T/L 수평 추락방지장치 설치공사","2023-04-06 07:00","2023-04-07 18:00","2023-04-06 07:00","2023-04-07 18:00","연속"]
[540,"대구","달성","대구봉덕#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-봉덕T/L 수평 추락방지장치 설치공사","2023-04-03 07:00","2023-04-05 18:00","2023-04-03 07:00","2023-04-05 18:00","연속"]
[541,"대구","달성","대구범물#1 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","폴리머애자교체 및 No.41 수직 추락방지장치 설치","2023-04-10 07:30","2023-04-11 17:00","2023-04-10 07:30","2023-04-11 17:00","연속"]
[542,"대구","칠곡","북대구구암#2 T/L","154kV 북대구-구암T/L 지장송전선로 이설공사(지중화)","- 68~69호 , 71~72호 전력선 설치 - 임시 69~72호 전력선 철거","2023-04-21 07:30","2023-05-03 18:00","2023-04-21 07:30","2023-05-04 18:00","연속"]
[543,"대구","칠곡","북대구구암#1 T/L","154kV 북대구-구암T/L 지장송전선로 이설공사(지중화)","- 68~69호 , 71~72호 전력선 설치 - 임시 69~72호 전력선 철거","2023-04-21 07:30","2023-05-03 18:00","2023-04-21 07:30","2023-05-04 18:00","연속"]
[544,"대구","포항","왕신남포항 T/L","154kV 남포항분기T/L 건설사업","- 154kV 왕신-남포항T/L No.36 ~ 41(C/H) (전력선 신설 및 공중이동) - 154kV 왕신-남포항T/L ST ~ No.1(전력선 공중이동) - 154kV 왕신-남포항T/L No.37 철탑보강 - ACSR/AW 410㎟×2B×2C – 1.238km","2023-04-10 08:00","2023-05-02 18:00","2023-04-10 08:00","2023-05-02 18:00","연속"]
[545,"경북","구미","남인동S/S CB 6100","남인동S/S 154kV GIS 증설공사","- 154kV GIS(627) 증설","2023-04-06 09:00","2023-04-15 18:00","2023-04-06 09:00","2023-04-15 18:00","연속"]
[546,"경북","구미","남인동S/S #65 BUS","남인동S/S 154kV GIS 증설공사","- 154kV GIS(627) 증설","2023-04-10 09:00","2023-04-13 18:00","2023-04-09 12:00","2023-04-13 18:00","연속"]
[547,"경북","구미","남인동S/S #60 BUS","남인동S/S 154kV GIS 증설공사","- 154kV GIS(627) 증설","2023-04-14 09:00","2023-04-15 18:00","2023-04-14 09:00","2023-04-15 18:00","연속"]
[548,"경북","구미","남인동S/S #60 BUS","남인동S/S 154kV GIS 증설공사","- 154kV GIS(627) 증설","2023-04-06 09:00","2023-04-09 18:00","2023-04-06 09:00","2023-04-09 11:00","연속"]
[549,"경북","구미","서대구남인동#1 T/L","남인동S/S 154kV GIS 증설공사","- 154kV GIS(627) 증설","2023-04-08 09:00","2023-04-15 18:00","2023-04-08 09:00","2023-04-15 18:00","연속"]
[550,"경북","영주","동상주점촌#2 T/L","점촌S/S 154kV #1,2M.Tr 정밀점검공사","M.Tr 정밀점검 후 무부하가압","2023-04-24 09:00","2023-04-28 18:00","2023-04-24 09:00","2023-04-28 18:00","연속"]
[551,"경북","직할","안동동안동#2 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","GIS 조작시험","2023-04-12 14:00","2023-04-12 18:00","2023-04-12 14:00","2023-04-12 18:00","연속"]
[552,"경북","직할","안동동안동#1 T/L","22~23년 경북본부 직할 변전협력회사 총액공사","GIS 조작시험","2023-04-12 09:00","2023-04-12 14:00","2023-04-12 09:00","2023-04-12 14:00","연속"]
[553,"경북","직할","영덕진보#2 T/L","기설철탑 추락방지장치 설치공사","154kV 청하-영덕T/L 추락방지장치 설치 안전확보","2023-04-24 08:00","2023-04-24 18:00","2023-04-24 08:00","2023-04-24 18:00","연속"]
[554,"경북","직할","봉화울진 T/L","울진S/S 154kV 장기사용 GIS 교체공사","울진S/S 154kV 장기사용 GIS 교체공사(1차분) - #1BUS END COVER 처리 후 무부하 가압용","2023-04-05 09:00","2023-04-06 18:00","2023-04-04 09:00","2023-04-05 18:00","연속"]
[555,"경북","직할","봉화울진 T/L","울진S/S 154kV 장기사용 GIS 교체공사","울진S/S 154kV 장기사용 GIS 교체공사(1차분) - #2BUS END COVER 처리 후 무부하 가압용","2023-04-07 09:00","2023-04-08 18:00","2023-04-06 09:00","2023-04-07 18:00","연속"]
[556,"경북","직할","울진삼척GP#2 T/L","울진S/S 154kV 장기사용 GIS 교체공사","울진S/S 154kV 장기사용 GIS 교체공사(1차분) - 울진-삼척GP #2T/L 교체 및 BUS TIE 설치","2023-04-03 09:00","2023-04-26 18:00","2023-04-03 09:00","2023-04-21 18:00","연속"]
[557,"경북","직할","봉화울진 T/L","울진S/S 154kV 장기사용 GIS 교체공사","울진S/S 154kV 장기사용 GIS 교체공사(1차분) - #2BUS Adapter 설치 후 무부하 가압용","2023-04-26 09:00","2023-04-27 18:00","2023-04-20 09:00","2023-04-21 18:00","연속"]
[558,"경북","직할","울진삼척GP#1 T/L","울진S/S 154kV 장기사용 GIS 교체공사","울진S/S 154kV 장기사용 GIS 교체공사(2차분) - 울진-삼척GP #1T/L 철거 및 BUS SEC 설치","2023-04-27 09:00","2023-05-31 18:00","2023-04-24 09:00","2023-05-25 18:00","연속"]
[559,"경북","직할","봉화울진 T/L","울진S/S 154kV 장기사용 GIS 교체공사","울진S/S 154kV 장기사용 GIS 교체공사(1차분) - #1BUS Adapter 설치 후 무부하 가압용","2023-04-21 09:00","2023-04-22 18:00","2023-04-18 09:00","2023-04-19 18:00","연속"]
[560,"부산울산","동부산","구서노포#1 T/L","노포S/S 170GIS 정밀점검관련 시험가압","노포S/S 170GIS 정밀점검관련 시험가압(6100)","2023-04-04 17:00","2023-04-04 18:00","2023-04-04 17:00","2023-04-04 18:00","연속"]
[561,"부산울산","동부산","구서노포#2 T/L","노포S/S 170GIS 정밀점검관련 시험가압","노포S/S 170GIS 정밀점검관련 시험가압(6100)","2023-04-06 17:00","2023-04-06 18:00","2023-04-06 17:00","2023-04-06 18:00","연속"]
[562,"부산울산","동부산","정보대연 T/L","정보S/S 170GIS 정밀점검관련 시험가압","정보S/S 170GIS 정밀점검관련 시험가압(정보S/S #3M.Tr 1차 6333)","2023-04-27 13:00","2023-04-27 14:00","2023-04-27 13:00","2023-04-27 14:00","연속"]
[563,"부산울산","동부산","정보대연 T/L","정보S/S 170GIS 정밀점검관련 시험가압","정보S/S 170GIS 정밀점검관련 시험가압(정보S/S #3M.Tr 1차 6333)","2023-04-28 17:00","2023-04-28 18:00","2023-04-28 17:00","2023-04-28 18:00","연속"]
[564,"부산울산","북부산","개금범천#2 T/L","대한전선제 OF케이블 SJ접속함 채유","1. 대 상 : 154kV 개금-범천T/L SJ접속함 3개소 2. 업체명 : (주)공영전력","2023-04-20 09:00","2023-04-20 18:00","2023-04-20 09:00","2023-04-20 18:00","연속"]
[565,"부산울산","북부산","개금범천#1 T/L","대한전선제 OF케이블 SJ접속함 채유","1. 대 상 : 154kV 개금-범천T/L SJ접속함 3개소 2. 업체명 : (주)공영전력","2023-04-19 09:00","2023-04-19 18:00","2023-04-19 09:00","2023-04-19 18:00","연속"]
[566,"부산울산","북부산","구포S/S #2 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-04-20 09:00","2023-04-29 20:00","취소","취소","연속"]
[567,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사","2023-04-29 18:00","2023-04-29 20:00","취소","취소","연속"]
[568,"부산울산","북부산","구포대저#2 T/L","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사(2차분)","2023-04-18 18:00","2023-04-19 18:00","2023-04-18 18:00","2023-04-19 18:00","연속"]
[569,"부산울산","북부산","구포대저#2 T/L","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사(2차분)","2023-04-13 18:00","2023-04-13 20:00","2023-04-13 18:00","2023-04-13 20:00","연속"]
[570,"부산울산","북부산","북부산구포#2 T/L","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사(2차분)","2023-04-10 09:00","2023-04-29 20:00","2023-04-10 09:00","2023-04-29 20:00","연속"]
[571,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사(2차분)","2023-04-14 09:00","2023-04-19 18:00","2023-04-14 09:00","2023-04-19 18:00","연속"]
[572,"부산울산","북부산","구포S/S #2 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사(1차분)","2023-04-05 18:00","2023-04-06 18:00","2023-04-05 18:00","2023-04-06 18:00","연속"]
[573,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사(1차분)","2023-04-06 18:00","2023-04-06 20:00","2023-04-06 18:00","2023-04-06 20:00","연속"]
[574,"부산울산","북부산","구포S/S #2 BUS","구포S/S 154kV GIS 대체공사","구포S/S 154kV GIS 대체공사(2차분)","2023-04-10 09:00","2023-04-13 20:00","2023-04-10 09:00","2023-04-13 20:00","연속"]
[575,"부산울산","북부산","호포물금 T/L","세니온제 송전선로 보호반 성능 개선","물금S/S 154kV 호포-물금T/L 보호반 성능개선","2023-04-21 10:00","2023-04-21 18:00","2023-04-21 10:00","2023-04-21 18:00","연속"]
[576,"부산울산","북부산","북부산미남#2 T/L","2022~23년 북부산전력지사가공송전 협력회사 총액공사","철탑도장 ○ 공사구간 : 154kV 북부산-미남T/L No.21(좌측)","2023-04-19 07:00","2023-04-20 18:00","2023-04-19 07:00","2023-04-20 18:00","연속"]
[577,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 북부산-삼랑진T/L 1~46호 45기 수평 추락방지장치 설치(2회선 및 4회선 구간)","2023-04-20 08:30","2023-04-23 18:00","취소","취소","연속"]
[578,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 북부산-삼랑진T/L 1~46호 45기 수평 추락방지장치 설치 병가구간 안전확보","2023-04-22 08:30","2023-04-23 18:00","취소","취소","연속"]
[579,"부산울산","북부산","북부산물금 T/L","22-23년 북부산전력지사 변전총액공사","북부산S/S 154kV 북부산-물금T/L 보통점검","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[580,"부산울산","북부산","북부산호포 T/L","22-23년 북부산전력지사 변전총액공사","북부산S/S 154kV 북부산-호포T/L 보통점검","2023-04-04 09:00","2023-04-04 18:00","2023-04-04 09:00","2023-04-04 18:00","연속"]
[581,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 북부산-삼랑진T/L 1~46호 45기 수평 추락방지장치 설치(2회선 및 4회선 구간)","2023-04-15 08:30","2023-04-18 18:00","취소","취소","연속"]
[582,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 북부산-삼랑진T/L 1~46호 45기 수평 추락방지장치 설치 병가구간 안전확보","2023-04-15 08:30","2023-04-16 18:00","취소","취소","연속"]
[583,"부산울산","북부산","북부산미남#1 T/L","2022~23년 북부산전력지사가공송전 협력회사 총액공사","철탑도장 ○ 공사구간 : 154kV 북부산-미남T/L No.21(우측) SB댐퍼 교체 ○ 공사구간 : 154kV 북부산-미남T/L No.1","2023-04-17 07:00","2023-04-18 18:00","2023-04-17 07:00","2023-04-18 18:00","연속"]
[584,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 북부산-삼랑진T/L 1~46호 45기 수평 추락방지장치 설치 4회선 병가구간 안전확보","2023-04-29 08:30","2023-04-30 18:00","취소","취소","연속"]
[585,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 북부산-삼랑진T/L 1~46호 45기 수평 추락방지장치 설치(4회선 구간)","2023-04-29 08:30","2023-04-30 18:00","취소","취소","연속"]
[586,"부산울산","북부산","언양산막#1 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 언양-산막T/L 36~66호 30기 수평 추락방지장치 설치","2023-04-24 08:30","2023-04-28 18:00","취소","취소","연속"]
[587,"부산울산","북부산","서창산막#2 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 서창-산막T/L 25~69호 32기 수평 추락방지장치 설치 안전확보","2023-04-08 08:30","2023-04-09 18:00","취소","취소","연속"]
[588,"부산울산","북부산","서창산막#2 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 서창-산막T/L 25~69호 32기 수평 추락방지장치 설치 안전확보","2023-04-01 08:30","2023-04-02 18:00","취소","취소","연속"]
[589,"부산울산","북부산","서창산막#1 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 서창-산막T/L 25~69호 32기 수평 추락방지장치 설치","2023-04-08 08:30","2023-04-09 18:00","취소","취소","연속"]
[590,"부산울산","북부산","서창산막#1 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 서창-산막T/L 25~69호 32기 수평 추락방지장치 설치","2023-04-01 08:30","2023-04-02 18:00","취소","취소","연속"]
[591,"부산울산","북부산","양산삼랑진PP T/L","2022~23년 북부산전력지사가공송전 협력회사 총액공사","철탑도장 ○ 공사구간 : 154kV 양산분기T/L No.17, No.18(좌측)","2023-04-24 07:00","2023-04-25 18:00","2023-04-24 07:00","2023-04-25 18:00","연속"]
[592,"부산울산","북부산","엄궁S/S CB 6100","23년 북부산전력지사 154kV GIS 정밀점검 공사","엄궁S/S 154kV 6100 B/T GIS 정밀점검","2023-04-19 08:00","2023-04-20 18:00","2023-04-19 08:00","2023-04-20 18:00","연속"]
[593,"부산울산","북부산","모라엄궁#1 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","엄궁S/S 154kV 6133 GIS 정밀점검 시험가압선로 : 모라-엄궁#1T/L","2023-04-18 17:00","2023-04-18 18:00","2023-04-18 17:00","2023-04-18 18:00","연속"]
[594,"부산울산","북부산","모라엄궁#1 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","엄궁S/S 154kV 6100 B/T GIS 정밀점검 시험가압선로 : 모라-엄궁#1T/L","2023-04-20 17:00","2023-04-20 18:00","2023-04-20 17:00","2023-04-20 18:00","연속"]
[595,"부산울산","서부산","용원녹공#2 T/L","녹공S/S 용원녹공#2 T/L GIS 동작시험","녹공S/S 용원녹공#2 T/L GIS 동작시험","2023-04-06 09:00","2023-04-06 18:00","2023-04-06 09:00","2023-04-06 18:00","연속"]
[596,"부산울산","서부산","용원녹공#1 T/L","녹공S/S 용원녹공#1 T/L GIS 동작시험","녹공S/S 용원녹공#1 T/L GIS 동작시험","2023-04-05 09:00","2023-04-05 18:00","2023-04-05 09:00","2023-04-05 18:00","연속"]
[597,"부산울산","서부산","서부산부민#1 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","○ 서부산-부민#1T/L 집감반 POINT 수용","2023-04-03 09:00","2023-04-21 18:00","2023-04-03 09:00","2023-04-21 18:00","연속"]
[598,"부산울산","서부산","서부산S/S SEC CB 60610","서부산S/S 154kV #60-#61 SEC GIS 동작시험","서부산S/S 154kV #60-#61 SEC GIS 동작시험","2023-04-03 09:00","2023-04-03 18:00","2023-04-03 09:00","2023-04-03 18:00","연속"]
[599,"부산울산","서부산","서부산S/S SEC CB 65660","서부산S/S 154kV #65-#66 SEC GIS 동작시험","서부산S/S 154kV #65-#66 SEC GIS 동작시험","2023-04-04 09:00","2023-04-04 18:00","2023-04-04 09:00","2023-04-04 18:00","연속"]
[600,"부산울산","서부산","신김해지사#1 T/L","2023년 서부산전력지사 가공송전 순시점검 위탁공사","정밀점검 : 30~40호","2023-04-17 08:00","2023-04-17 18:00","2023-04-17 08:00","2023-04-17 18:00","연속"]
[601,"부산울산","서부산","신김해지사#2 T/L","2023년 서부산전력지사 가공송전 순시점검 위탁공사","정밀점검 : 30~40호","2023-04-19 08:00","2023-04-19 18:00","2023-04-19 08:00","2023-04-19 18:00","연속"]
[602,"부산울산","울산","두왕울산#1 T/L","154kV 추락방지장치 설치공사","ㅇ 수직, 수평 추락방지장치 설치 11기 (병가1기 포함)","2023-04-12 07:30","2023-04-14 18:00","2023-04-12 07:30","2023-04-14 18:00","연속"]
[603,"부산울산","울산","효문방어진 T/L","22~23년 변전협력회사 총액공사","- 피뢰기 보통점검","2023-04-11 09:00","2023-04-11 18:00","2023-04-11 09:00","2023-04-11 18:00","연속"]
[604,"부산울산","울산","산하방어진#1 T/L","22~23년 변전협력회사 총액공사","- 피뢰기 보통점검","2023-04-07 09:00","2023-04-07 18:00","2023-04-07 09:00","2023-04-07 18:00","연속"]
[605,"부산울산","울산","남울산성암#1 T/L","154kV SK멀티유틸리티#1,2T/L 신규수용공사","#1T/L 시험가압용 선로","2023-04-06 18:00","2023-04-07 18:00","2023-04-06 18:00","2023-04-07 18:00","연속"]
[606,"부산울산","울산","남울산성암#2 T/L","154kV SK멀티유틸리티#1,2T/L 신규수용공사","#2T/L 시험가압용 선로","2023-04-20 18:00","2023-04-21 18:00","2023-04-20 18:00","2023-04-21 18:00","연속"]
[607,"부산울산","울산","남울산성암#1 T/L","154kV SK멀티유틸리티#1,2T/L 신규수용공사","#1T/L 시험가압용 선로","2023-04-13 18:00","2023-04-14 19:00","2023-04-13 18:00","2023-04-14 19:00","연속"]
[608,"부산울산","울산","남울산성암#2 T/L","154kV SK멀티유틸리티#1,2T/L 신규수용공사","#2T/L 시험가압용 선로","2023-04-27 18:00","2023-04-28 19:00","2023-04-27 18:00","2023-04-28 19:00","연속"]
[609,"부산울산","울산","신울산울산#2 T/L","154kV 추락방지장치 설치공사","ㅇ 수직, 수평 추락방지장치 설치 17기","2023-04-04 07:30","2023-04-11 18:00","2023-04-04 07:30","2023-04-11 18:00","연속"]
[610,"부산울산","울산","신울산두왕#2 T/L","154kV 추락방지장치 설치공사","ㅇ 수직, 수평 추락방지장치 설치 7기 (병가5기 포함)","2023-04-10 07:30","2023-04-12 18:00","2023-04-10 07:30","2023-04-12 18:00","연속"]
[611,"부산울산","울산","신울산언양#1 T/L","2023년 가공송전 순시점검 위탁공사","-공사내용: 154kV 신울산-언양#1T/L 정밀점검 -작업구간: S/T~S/T(총 69기)","2023-04-24 09:00","2023-04-28 18:00","2023-04-24 09:00","2023-04-28 18:00","연속"]
[612,"부산울산","울산","신울산S/S #66 BUS","신울산S/S 154kV 현대화공사","신울산S/S #3M.Tr 2차 임시선로 구성관련 가공모선 설치","2023-04-01 08:30","2023-04-01 18:00","2023-04-01 08:30","2023-04-01 18:00","연속"]
[613,"부산울산","울산","울산영남TP#2 T/L","154kV 추락방지장치 설치공사","ㅇ 수평 추락방지장치 설치 20기","2023-04-17 07:30","2023-04-21 18:00","2023-04-17 07:30","2023-04-21 18:00","연속"]
[614,"부산울산","울산","옥동외동#2 T/L","154kV 외동-옥동 지장이설공사(LH측 요청자시행)","□ LH측 요청 휴전 시행(LH 직접시공) ㅇ #2 14호 인클로징,19호 상부재 보강 ㅇ 기설철탑 4기 철거, 가철탑 6기 신설","2023-04-17 07:00","2023-04-19 18:00","2023-04-17 07:00","2023-04-19 18:00","연속"]
[615,"부산울산","울산","옥동외동#1 T/L","154kV 외동-옥동 지장이설공사(LH측 요청자시행)","□ LH측 요청 휴전 시행(LH 직접시공) ㅇ #1 14호 인클로징,19호 상부재 보강 ㅇ 기설철탑 4기 철거, 가철탑 6기 신설","2023-04-20 07:00","2023-04-22 18:00","2023-04-20 07:00","2023-04-22 18:00","연속"]
[616,"부산울산","울산","신온산온산#2 T/L","22~23년 변전협력회사 총액공사","- 한국가스#1T/L GIS 정밀점검 관련 시험가압(1Hr)","2023-04-23 17:00","2023-04-23 18:00","2023-04-23 17:00","2023-04-23 18:00","연속"]
[617,"부산울산","울산","용연울산TP#3 T/L","22~23년 변전협력회사 총액공사","- 용연측 GIS 차단기 동작시험, 부싱 교체 - 울산TP측 GIS 차단기 동작시험","2023-04-12 09:00","2023-04-13 18:00","2023-04-12 09:00","2023-04-13 18:00","연속"]
[618,"부산울산","직할","우동대연 T/L","22~23년 서부산전력지사 가공송전 협력회사 총액공사","우동-대연T/L 피뢰기설치 : 1~13호","2023-04-10 09:00","2023-04-12 18:00","취소","취소","연속"]
[619,"부산울산","울산","신울산언양#1 T/L","2023년 가공송전 순시점검 위탁공사","-공사내용: 154kV 신울산-언양#1T/L 정밀점검 -작업구간: S/T~S/T(총 69기)","2023-04-24 09:00","2023-04-28 18:00","2023-04-24 09:00","2023-04-28 18:00","연속"]
[620,"경남","직할","녹공마천#2 T/L","마천S/S LID 이설 공사","마천S/S LID 이설 공사 대상설비 : 녹공-마천#2T/L(667) 병행 : 녹공-마천#2T/L 조작","2023-04-03 09:30","2023-04-04 18:00","2023-04-03 09:30","2023-04-04 18:00","연속"]
[621,"경남","직할","신김해삼정#1 T/L","삼정S/S 154kV GIS PD발생 조치작업","삼정S/S 154kV GIS PD발생 조치작업 대상설비 : 신김해-삼정#1T/L #1,2DS(641,2)","2023-04-19 09:30","2023-04-20 18:00","2023-04-19 09:30","2023-04-20 18:00","연속"]
[622,"경남","직할","신월동읍#2 T/L","2022-2023년 경남 직할 가공송전협력회사 총액공사","154kV 신월-동읍T/L 1~45호 구간 수평 추락방지장치 설치","2023-04-10 07:00","2023-04-17 18:00","2023-04-10 07:00","2023-04-17 18:00","매일"]
[623,"경남","직할","신월삼정#2 T/L","2022-2023년 경남 직할 가공송전협력회사 총액공사","154kV 신월-삼정T/L 1~2호 구간 수평 추락방지장치 설치","2023-04-15 07:00","2023-04-15 18:00","2023-04-15 07:00","2023-04-15 18:00","연속"]
[624,"경남","직할","신월삼정#1 T/L","2022-2023년 경남 직할 가공송전협력회사 총액공사","154kV 신월-삼정T/L 1~2호 구간 수평 추락방지장치 설치","2023-04-01 07:00","2023-04-01 18:00","2023-04-01 07:00","2023-04-01 18:00","연속"]
[625,"경남","진주","중리가야#1 T/L","가야S/S 중리-가야#1T/L GIS 보통점검","가야S/S 중리-가야#1T/L GIS 보통점검","2023-04-28 09:00","2023-04-28 18:00","2023-04-28 09:00","2023-04-28 18:00","연속"]
[626,"경남","진주","가야사봉#1 T/L","가야S/S 154kV #1Sh.C GIS(6179) 정밀점검(시험가압)","가야S/S 154kV #1Sh.C GIS(6179) 정밀점검(제작사) - #60BUS 및 가야-사봉#1T/L 휴전 시험가압용","2023-04-26 13:00","2023-04-26 15:00","2023-04-26 13:00","2023-04-26 15:00","연속"]
[627,"경남","진주","진주개양#1 T/L","22~23년 진주전력지사 송전협력회사 총액공사","154kV 사봉-개양T/L 피뢰기 설치, 수평가이드레일 설치 관련 진주-개양#1T/L 안전이격 확보 154kV 사봉-개양T/L 정밀점검(1~56호)(병행)","2023-04-15 13:00","2023-04-16 18:00","2023-04-15 13:00","2023-04-16 18:00","매일"]
[628,"경남","진주","진주개양#2 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검 안전거리확보","154kV 사봉-개양T/L 정밀점검(1~56호) - 2~5호 병가구간(진주-개양#2T/L) 휴전작업시 안전이격 확보","2023-04-08 09:00","2023-04-09 18:00","취소","취소","연속"]
[629,"경남","진주","진주개양#1 T/L","22~23년 진주전력지사 송전협력회사 총액공사","154kV 사봉-개양T/L 피뢰기 설치, 수평가이드레일 설치 관련 진주-개양#1T/L 안전이격 확보 154kV 사봉-개양T/L 정밀점검(1~56호)(병행)","2023-04-22 07:00","2023-04-22 18:00","2023-04-22 07:00","2023-04-22 18:00","매일"]
[630,"경남","진주","진주개양#2 T/L","22~23년 진주전력지사 송전협력회사 총액공사","154kV 사봉-개양#1T/L 피뢰기 설치, 수평가이드레일 설치 관련 진주-개양#2T/L 안전이격 확보 154kV 사봉-개양T/L 정밀점검(1~56호)(병행)","2023-04-15 07:00","2023-04-15 13:00","2023-04-15 07:00","2023-04-15 13:00","매일"]
[631,"경남","진주","의령동진주#2 T/L","동진주S/S 154kV #1M.Tr 1차 GIS 정밀점검(시험가압)","동진주S/S 154kV #1M.Tr 1차 GIS 6133 정밀점검(제작사) - #65BUS 및 의령-동진주2T/L 휴전 시험가압용","2023-04-21 13:00","2023-04-21 15:00","2023-04-21 13:00","2023-04-21 15:00","연속"]
[632,"경남","진주","의령동진주#2 T/L","동진주S/S 154kV 6100 B/T 정밀점검(시험가압)","동진주S/S 154kV 6100 B/T 정밀점검(제작사) - #65BUS 및 의령-동진주2T/L 휴전 시험가압용","2023-04-19 13:00","2023-04-19 15:00","2023-04-19 13:00","2023-04-19 15:00","연속"]
[633,"경남","진주","사봉개양#1 T/L","154kV 사봉-개양T/L 정밀점검(1~56호)","154kV 사봉-개양T/L 정밀점검(1~56호)","2023-04-08 09:00","2023-04-09 18:00","취소","취소","연속"]
[634,"경남","진주","사봉개양#2 T/L","22~23년 진주전력지사 송전협력회사 총액공사","154kV 사봉-개양T/L 피뢰기 설치, 수평가이드레일 설치","2023-04-22 07:00","2023-04-23 18:00","2023-04-22 07:00","2023-04-23 18:00","매일"]
[635,"경남","진주","사봉개양#1 T/L","154kV 사봉-개양T/L 정밀점검(1~56호)","154kV 사봉-개양T/L 정밀점검(1~56호)","2023-04-01 09:00","2023-04-02 18:00","취소","취소","연속"]
[636,"경남","진주","가야사봉#1 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검 안전거리확보","154kV 사봉-개양T/L 가공송전선로 정밀점검(병가선로) - 2~7호 병가구간(사봉-개양#1T/L) 휴전작업시 안전이격확보","2023-04-29 09:00","2023-04-30 18:00","2023-04-29 09:00","2023-04-30 18:00","매일"]
[637,"경남","진주","사봉개양#2 T/L","22~23년 진주전력지사 송전협력회사 총액공사","154kV 사봉-개양T/L 피뢰기 설치, 수평가이드레일 설치","2023-04-15 13:00","2023-04-16 18:00","2023-04-15 13:00","2023-04-16 18:00","매일"]
[638,"경남","진주","사봉개양#1 T/L","22~23년 진주전력지사 송전협력회사 총액공사","154kV 사봉-개양T/L 피뢰기 설치, 수평가이드레일 설치","2023-04-15 07:00","2023-04-15 13:00","2023-04-15 07:00","2023-04-15 13:00","매일"]
[639,"경남","진주","사봉개양#2 T/L","154kV 사봉-개양T/L 정밀점검(1~56호)","154kV 사봉-개양T/L 정밀점검(1~56호)","2023-04-29 09:00","2023-04-30 18:00","2023-04-29 09:00","2023-04-30 18:00","매일"]
[640,"경남","진주","가야사봉#2 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검 안전거리확보","154kV 사봉-개양T/L 가공송전선로 정밀점검(병가선로) - 2~7호 병가구간(사봉-개양#1T/L) 휴전작업시 안전이격확보","2023-04-01 09:00","2023-04-02 18:00","취소","취소","연속"]
[641,"경남","진주","의령동진주#1 T/L","154kV 거창-합천 등 14개 T/L 수평 추락방지시설 설치","○ 154kV 의령-동진주 #1 T/L 철탑 추락방지장치 설치공사 (연속) - 수평 추락방지장치 설치 : No.1~73(73기) - 평일작업","2023-04-02 07:00","2023-04-08 18:00","취소","취소","연속"]
[642,"경남","진주","의령동진주#2 T/L","154kV 거창-합천 등 14개 T/L 수평 추락방지시설 설치","○ 154kV 의령-동진주 #2 T/L 철탑 추락방지장치 설치공사 (연속) - 수평 추락방지장치 설치 : No.1~73(73기) - 평일작업","2023-04-09 07:00","2023-04-14 18:00","취소","취소","연속"]
[643,"경남","진주","하동하동화력 T/L","'23년 가공송전 순시점검 위탁공사","154kV 하동-남해T/L 1~113호(111기/22호(자선로), 95호 결번으로 제외) 정밀점검 - 2~21호 병가구간(하동-남해#1T/L) 휴전작업시 안전이격 확보","2023-04-14 09:00","2023-04-18 18:00","2023-04-14 09:00","2023-04-18 18:00","매일"]
[644,"경남","진주","광양하동#1 T/L","154kV 거창-합천 등 14개 T/L 수평 추락방지시설 설치","○ 154kV 광양-하동 #1 T/L 철탑 추락방지장치 설치공사 (연속) - 수평 추락방지장치 설치 : No.21~37(16기) - 평일작업","2023-04-10 07:00","2023-04-13 18:00","2023-04-10 07:00","2023-04-13 18:00","연속"]
[645,"경남","진주","광양하동#2 T/L","154kV 거창-합천 등 14개 T/L 수평 추락방지시설 설치","○ 154kV 광양-하동 #2 T/L 철탑 추락방지장치 설치공사 (연속) - 수평 추락방지장치 설치 : No.21~37(16기) - 평일작업","2023-04-12 07:00","2023-04-14 18:00","2023-04-12 07:00","2023-04-14 18:00","연속"]
[646,"경남","진주","함양거창#1 T/L","154kV 거창-합천 등 14개 T/L 수평 추락방지시설 설치","○ 154kV 함양-거창 #1 T/L 철탑 추락방지장치 설치공사 (연속) - 수평 추락방지장치 설치 : No.1~71(71기) - 평일작업","2023-04-13 07:00","2023-04-22 18:00","2023-04-13 07:00","2023-04-22 18:00","연속"]
[647,"경남","진주","쌍림합천#1 T/L","합천S/S 쌍림-합천#1T/L 보호반 대체","합천S/S 쌍림-합천#1T/L 보호반 대체","2023-04-03 09:00","2023-04-05 18:00","2023-04-03 09:00","2023-04-05 18:00","연속"]
[648,"경남","진주","쌍림합천#2 T/L","합천S/S 쌍림-합천#2T/L GIS 보통점검","합천S/S 쌍림-합천#2T/L GIS 보통점검","2023-04-20 09:00","2023-04-20 18:00","2023-04-20 09:00","2023-04-20 18:00","연속"]
[649,"경남","통영","신고성거제#2 T/L","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","2023-04-01 07:00","2023-04-02 18:00","2023-04-01 07:00","2023-04-02 18:00","매일"]
[650,"경남","통영","신고성삼천포#2 T/L","신고성S/S 신고성-삼천포#2T/L 보통점검 등 3건","1. 신고성S/S 신고성-삼천포#2T/L 보통점검 2. 신고성S/S 신고성-삼천포#2T/L LA 보통점검 3. 삼천포S/S 신고성-삼천포#2T/L 조작시험","2023-04-15 10:00","2023-04-15 18:00","2023-04-15 10:00","2023-04-15 18:00","연속"]
[651,"경남","통영","진동안정#1 T/L","154kV 진동-안정#1T/L 추락방지장치 설치공사","154kV 진동-안정#1T/L 추락방지장치 설치공사","2023-04-17 07:00","2023-04-28 18:00","2023-04-17 07:00","2023-04-28 18:00","매일"]
[652,"경남","통영","진동안정#2 T/L","154kV 진동-안정#2T/L 추락방지장치 설치공사","154kV 진동-안정#2T/L 추락방지장치 설치공사","2023-04-01 07:00","2023-04-14 18:00","2023-04-01 07:00","2023-04-14 18:00","매일"]
[653,"경남","함안","호포매리#1 T/L","매리S/S 호포매리#1 T/L GIS 정밀점검","매리S/S 호포매리#1 T/L GIS 정밀점검","2023-04-21 09:00","2023-04-23 18:00","2023-04-21 09:00","2023-04-23 18:00","연속"]
[654,"경남","함안","호포매리#2 T/L","매리S/S 호포매리#2 T/L GIS 정밀점검","매리S/S 호포매리#2 T/L GIS 정밀점검","2023-04-29 09:00","2023-05-01 18:00","2023-04-29 09:00","2023-05-01 18:00","연속"]
[655,"경남","함안","한림정삼계#2 T/L","삼계S/S 법면 제초작업 안전이격거리 확보","삼계S/S 법면 활선부 근접구간 제초작업","2023-04-02 13:00","2023-04-02 18:00","2023-04-02 13:00","2023-04-02 18:00","연속"]
[656,"경남","함안","삼계어방#2 T/L","154kV 삼계-어방T/L 9~14호 지장이설 공사","9~10호 전선공중이동, 13~14호 전선교체","2023-04-14 07:00","2023-04-16 18:00","2023-04-14 07:00","2023-04-16 18:00","연속"]
[657,"경남","함안","한림정삼계#1 T/L","154kV 삼계-어방T/L 9~14호 지장이설 공사","9~10호 전선공중이동, 13~14호 전선교체","2023-04-14 07:00","2023-04-16 18:00","2023-04-14 07:00","2023-04-16 18:00","연속"]
[658,"경남","함안","한림정삼계#1 T/L","삼계S/S 법면 제초작업 안전이격거리 확보","삼계S/S 법면 활선부 근접구간 제초작업","2023-04-02 13:00","2023-04-02 18:00","2023-04-02 13:00","2023-04-02 18:00","연속"]
[659,"경남","함안","한림정삼계#2 T/L","154kV 삼계-어방T/L 9~14호 지장이설 공사","9~10호 전선공중이동, 13~14호 전선교체","2023-04-07 07:00","2023-04-09 18:00","2023-04-07 07:00","2023-04-09 18:00","연속"]
[660,"경남","함안","주촌삼계#2 T/L","삼계S/S 법면 제초작업 안전이격거리 확보","삼계S/S 법면 활선부 근접구간 제초작업","2023-04-02 08:00","2023-04-02 13:00","2023-04-02 08:00","2023-04-02 13:00","연속"]
[661,"경남","함안","주촌삼계#1 T/L","삼계S/S 법면 제초작업 안전이격거리 확보","삼계S/S 법면 활선부 근접구간 제초작업","2023-04-02 08:00","2023-04-02 13:00","2023-04-02 08:00","2023-04-02 13:00","연속"]
[662,"경남","함안","삼계어방#1 T/L","154kV 삼계-어방T/L 9~14호 지장이설 공사","9~10호 전선공중이동, 13~14호 전선교체","2023-04-07 07:00","2023-04-09 18:00","2023-04-07 07:00","2023-04-09 18:00","연속"]
[663,"경남","함안","진영수산#1 T/L","2022~23년도 함안전력 송전정비회사 총액공사 피뢰기 설치","154kV 진영-수산#1T/L 피뢰기 설치(28~61호)","2023-04-03 07:00","2023-04-04 18:00","2023-04-03 07:00","2023-04-04 18:00","매일"]
[664,"경남","함안","진영한림정#1 T/L","한림정S/S 진영한림정#1 T/L GIS 보통점검","한림정S/S 진영한림정#1 T/L GIS 보통점검","2023-04-01 09:30","2023-04-01 17:30","2023-04-01 09:30","2023-04-01 17:30","연속"]
[665,"부산울산",null,"새울N/P #1 대기보조변압기 (CB 6271, 6200, 6471, 6400, 6472, 6571, 6671, 6771, 6572, 6672, 6772)","신고리3호기 4차 계획예방정비 *조작 차단기 : CB 6271, 6200, 6471, 6400, 6472, 6571, 6671, 6771, 6572, 6672, 6772","○ 신고리 154kV 수전선로 Tie Line 공급전원 변경 ○ 154kV SWYD 64 Bay 일반점검 ○ 대기보조변압기 일반점검 ○ 154kV BUS #1, 2 일반점검","2023-05-26 09:00","2023-06-06 18:00","2023-05-26 09:00","2023-06-06 18:00","연속"]
[666,"부산울산",null,"장안고리NP T/L","2호기 31차 계획예방정비 ○ 조작차단기\n  - 1호기 : CB 627, DS 626, DS 625, ES 103, CB 6283, DS 6285, ES 104\n  - 2호기 : CB 6383, DS 6385","○ 2호기 SAT 일반점검 ○ GCB 6383, DS 6385 점검 ○ SAT 보호계전기 개체/연동시험 ○ 변전소 설비측 한전 별도신청예정","2023-04-24 09:00","2023-05-03 18:00","2023-04-24 09:00","2023-05-03 18:00","연속"]
[667,"경기","동부","분당오포#1 T/L","추락방지시설 설치공사","추락방지시설 설치","2023-04-30 07:00","2023-05-02 18:00","2023-04-30 07:00","2023-05-02 18:00","연속"]
[668,"대전세종충남","청양","신서천대천#2 T/L","[송전] 154kV 대천S/S 인출T/L 지중화공사","- 선종 및 길이 : XLPE 2,500㎟ × 4C, 0.136km - 휴전작업내용 : 가공-지중 연결 및 GIS 가압","2023-04-22 06:00","2023-04-22 21:00","2023-04-22 06:00","2023-04-22 21:00","연속"]
[669,"대전세종충남","청양","관창대천#2 T/L","[송전] 154kV 대천S/S 인출T/L 지중화공사","- 선종 및 길이 : XLPE 2,500㎟ × 4C, 0.136km - 휴전작업내용 : 가공-지중 연결 및 GIS 가압","2023-04-23 06:00","2023-04-23 21:00","2023-04-23 06:00","2023-04-23 21:00","연속"]
[670,"대전세종충남","대전","신흥동대전#3 T/L","신흥S/S 170kV GIS 보통점검(신흥-동대전#3)","신흥S/S 170kV GIS 보통점검(신흥-동대전#3)","2023-04-26 09:00","2023-04-26 18:00","2023-04-26 09:00","2023-04-26 18:00","연속"]