{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":13,"n_cols":11,"rows_kept":13,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 6월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신태백신가평#2 T/L","송전선로 단상재폐로 결상회로 개선","송운(변전)-1085 (21.10.19) 「송전선로 단상 자동재투입용 GIS 결상회로 개선 시행 알림」 관련 유사고장 재발방지","2023-06-20 09:00","2023-06-20 18:00","2023-06-29 09:00","2023-06-29 18:00","연속"]
[2,"강원","태백","신태백S/S CB 8371","2023년 신태백S/S 800kV GIS 보통점검공사","765kV 신태백S/S 8371CB 보통점검","2023-06-14 14:00","2023-06-16 18:00","2023-06-14 14:00","2023-06-16 18:00","연속"]
[3,"강원","태백","신태백S/S CB 8600","2023년 신태백S/S 800kV GIS 보통점검공사","765kV 신태백S/S 8600CB 보통점검","2023-06-19 09:00","2023-06-21 18:00","2023-06-19 09:00","2023-06-21 18:00","연속"]
[4,"강원","태백","신태백S/S CB 8471","2023년 신태백S/S 800kV GIS 보통점검공사","765kV 신태백S/S 8471CB 보통점검","2023-06-12 09:00","2023-06-14 14:00","2023-06-12 09:00","2023-06-14 14:00","연속"]
[5,"강원","태백","신태백S/S #2 BUS","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 765kV #2BUS 보호반 교체","2023-06-09 09:00","2023-06-16 18:00","취소","취소","연속"]
[6,"강원","태백","신태백S/S #1 BUS","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 765kV #1BUS 보호반 교체","2023-06-01 09:00","2023-06-08 18:00","취소","취소","연속"]
[7,"충북","직할","신중부S/S CB 8571","신중부S/S 765kV GIS CB 유압시스템 교체공사","765kV 신서산-신중부#2T/L GIS(8571CB) 유압 메커니즘 부품 교체","2023-06-08 09:00","2023-06-09 18:00","2023-06-08 09:00","2023-06-09 18:00","연속"]
[8,"충북","직할","신중부신안성#2 T/L","765kV 신중부-신안성T/L OPGW 항공장애표시구 교체공사","○ 765kV 신중부-신안성#2T/L OPGW 항공장애표시구 교체공사 26개 - 풍소음 민원에 따른 교체 필요","2023-06-19 07:00","2023-06-23 18:00","2023-06-21 07:00","2023-06-25 18:00","연속"]
[9,"대전세종충남","서산","신서산신중부#2 T/L","23년 서산P/O 장기사용 노후 배전반 대체공사","신서산S/S 765kV 86 B/F 보호반 대체","2023-06-12 09:00","2023-06-16 18:00","취소","취소","연속"]

{"sheet":"345설비","index":1,"n_rows":340,"n_cols":11,"rows_kept":340,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2023년도 6월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #1 M.Tr","2023년 성동P/O 변전협력회사 총액공사","- M.Tr, 3차 LA, 3차 PT 보통점검 - 170kV GIS 조작시험 - 변압기실 공조 FAN 교체","2023-06-12 10:00","2023-06-14 18:00","2023-06-12 10:00","2023-06-14 18:00","연속"]
[2,"서울","성동","성동S/S #2 M.Tr","2023년 성동P/O 변전협력회사 총액공사","- 170kV GIS 조작시험 - 3차 PT 보통점검 - 변압기실 공조 FAN 교체","2023-06-07 10:00","2023-06-09 18:00","2023-06-07 10:00","2023-06-09 18:00","연속"]
[3,"서울","중부","중부S/S #1 Sh.R CB","23 중부P/O 총액공사","리액터 보통점검등","2023-06-26 10:00","2023-06-27 18:00","취소","취소","연속"]
[4,"서울","중부","중부S/S #2 Sh.R CB","23 중부P/O 총액공사","리액터 보통점검등","2023-06-28 10:00","2023-06-29 18:00","취소","취소","연속"]
[5,"남서울","강남","신양재S/S #2 Sh.R CB","2023년 강남전력지사 362kV GIS 정밀점검공사","- 대상설비 : 7279 GIS","2023-06-05 09:00","2023-06-09 18:00","취소","취소","연속"]
[6,"남서울","영등포","신시흥신광명#2 T/L","'22-'23년 가공송전 협력회사 총액공사","- 피뢰기 설치","2023-06-13 14:00","2023-06-23 18:00","2023-06-13 14:00","2023-06-23 18:00","연속"]
[7,"남서울","영등포","신시흥신광명#1 T/L","22-23년 영등포전력지사 가공송전 협력회사 총액공사","추락방지장치 설치공사","2023-06-08 07:00","2023-06-13 14:00","2023-06-07 07:00","2023-06-13 14:00","연속"]
[8,"남서울","강남","신양재S/S #2 M.Tr","2023년 강남전력지사 362kV GIS 정밀점검공사 ","  - 대상설비 : 7272 GIS\n- 무부하가압 : 신성남-신양재#2T/L(병행휴전) 이용 ","2023-06-03 09:00","2023-06-03 18:00","2023-06-03 09:00","2023-06-03 18:00","연속"]
[9,"인천","시흥","신시흥영흥TP#2 T/L"," 345kV 영흥T/L 부식금구류 교체"," 345kV 영흥T/L 부식금구류 교체","2023-06-01 07:00","2023-06-07 18:00","2023-06-01 07:00","2023-06-07 18:00","연속"]
[10,"인천","시흥","신시흥영흥TP#4 T/L"," 345kV 영흥T/L 부식금구류 교체"," 345kV 영흥T/L 부식금구류 교체","2023-06-01 07:00","2023-06-07 18:00","2023-06-01 07:00","2023-06-07 18:00","연속"]
[11,"인천","부평","포스코C/C CB 7472"," 포스코S/Y #4 STEP-UP-TR T/L 7472 GIS 보통점검"," 포스코S/Y #4 STEP-UP-TR T/L 7472 GIS 보통점검","2023-06-01 09:00","2023-06-01 18:00","2023-06-01 09:00","2023-06-01 18:00","연속"]
[12,"인천","시흥","신가좌신시흥#2 T/L"," 신시흥S/S 345kV 신가좌신시흥#2T/L GIS 보통점검"," 신시흥S/S 345kV 신가좌신시흥#2T/L GIS 보통점검","2023-06-02 09:00","2023-06-02 18:00","2023-06-02 09:00","2023-06-02 18:00","연속"]
[13,"인천","부평","서인천C/C CB 7A00"," 서인천CC 신부평#1-#4T/L TIE 7A00 GIS 보통점검"," 서인천CC 신부평#1-#4T/L TIE 7A00 GIS 보통점검","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[14,"인천","부평","신가좌S/S #1 BUS"," 신가좌S/S 345kV #70BUS 모선보호반 교체공사"," 신가좌S/S 345kV #70BUS 모선보호반 교체공사","2023-06-05 09:00","2023-06-09 18:00","취소","취소","연속"]
[15,"인천","부평","신인천C/C CB 7800"," 신인천S/Y 신경서신인천T/L-4MT201 TIE 7800 GIS보통점검"," 신인천S/Y 신경서신인천T/L-4MT201 TIE 7800 GIS보통점검","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[16,"인천","시흥","신시흥영흥TP#3 T/L"," 345kV 영흥T/L 부식금구류 교체"," 345kV 영흥T/L 부식금구류 교체","2023-06-08 07:00","2023-06-15 18:00","2023-06-08 07:00","2023-06-15 18:00","연속"]
[17,"인천","시흥","신시흥영흥TP#1 T/L"," 345kV 영흥T/L 부식금구류 교체"," 345kV 영흥T/L 부식금구류 교체","2023-06-08 07:00","2023-06-15 18:00","2023-06-08 07:00","2023-06-15 18:00","연속"]
[18,"인천","부평","인천C/C CB 7671"," 345kV 인천복합 #2 S/T 7671GIS 보통점검"," 345kV 인천복합 #2 S/T 7671GIS 보통점검","2023-06-09 09:00","2023-06-09 18:00","2023-06-09 09:00","2023-06-09 18:00","연속"]
[19,"인천","김포","신김포신인천CC T/L"," 345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사"," 345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사","2023-06-12 09:00","2023-06-14 18:00","2023-06-05 09:00","2023-06-07 18:00","연속"]
[20,"인천","부평","신가좌S/S #2 BUS"," 신가좌S/S 345kV #75모선보호반 교체공사"," 신가좌S/S 345kV #75모선보호반 교체공사","2023-06-12 09:00","2023-06-16 18:00","취소","취소","연속"]
[21,"인천","부평","인천C/C CB 7500"," 인천CC#3,4G/T-인천CC#1,2G/T TIE 7500GIS 보통점검"," 인천CC#3,4G/T-인천CC#1,2G/T TIE 7500GIS 보통점검","2023-06-13 09:00","2023-06-13 18:00","2023-06-13 09:00","2023-06-13 18:00","연속"]
[22,"인천","직할","신부평S/S #2 Sh.R CB"," 신부평S/S 345kV 7279 GIS 조작시험"," 신부평S/S 345kV 7279 GIS 조작시험","2023-06-13 09:30","2023-06-13 18:00","2023-06-13 09:30","2023-06-13 18:00","연속"]
[23,"인천","부평","인천C/C CB 7572"," 인천복합 #1,2 G/T 7572GIS 보통점검"," 인천복합 #1,2 G/T 7572GIS 보통점검","2023-06-14 09:00","2023-06-14 18:00","2023-06-14 09:00","2023-06-14 18:00","연속"]
[24,"인천","직할","신부평S/S CB 7271"," 신부평S/S 345kV 7271 GIS 조작시험"," 신부평S/S 345kV 7271 GIS 조작시험","2023-06-14 09:30","2023-06-14 18:00","2023-06-14 09:30","2023-06-14 18:00","연속"]
[25,"인천","김포","신김포서인천CC T/L"," 345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사"," 345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사","2023-06-15 09:00","2023-06-17 18:00","2023-06-08 09:00","2023-06-10 18:00","연속"]
[26,"인천","부평","인천C/C CB 7600"," 인천복합 #1,2 G/T 7600GIS 보통점검"," 인천복합 #1,2 G/T 7600GIS 보통점검","2023-06-15 09:00","2023-06-15 18:00","2023-06-15 09:00","2023-06-15 18:00","연속"]
[27,"인천","직할","신부평S/S CB 7371"," 신부평S/S 345kV 7371 GIS 조작시험"," 신부평S/S 345kV 7371 GIS 조작시험","2023-06-15 09:30","2023-06-15 18:00","2023-06-15 09:30","2023-06-15 18:00","연속"]
[28,"인천","부평","인천C/C CB 7672"," 인천복합 #1 S/T 7672GIS 보통점검"," 인천복합 #1 S/T 7672GIS 보통점검","2023-06-16 09:00","2023-06-16 18:00","2023-06-16 09:00","2023-06-16 18:00","연속"]
[29,"인천","직할","신부평S/S CB 7471"," 신부평S/S 345kV 7471 GIS 조작시험"," 신부평S/S 345kV 7471 GIS 조작시험","2023-06-16 09:30","2023-06-16 18:00","2023-06-16 09:30","2023-06-16 18:00","연속"]
[30,"인천","부평","신경서S/S #3 M.Tr"," 신경서S/S 345kV #3 M.Tr 휴전작업"," 신경서S/S 345kV #3 M.Tr 휴전작업","2023-06-19 09:00","2023-06-21 18:00","2023-06-19 09:00","2023-06-21 18:00","연속"]
[31,"인천","부평","신가좌신시흥#1 T/L"," 22~23년 가공송전 정비회사 총액공사"," 22~23년 가공송전 정비회사 총액공사","2023-06-19 09:00","2023-06-22 18:00","취소","취소","연속"]
[32,"인천","직할","신부평S/S #3 Sh.R CB"," 신부평S/S 345kV 7379 GIS 정밀점검"," 신부평S/S 345kV 7379 GIS 정밀점검","2023-06-19 09:30","2023-06-23 18:00","취소","취소","연속"]
[33,"인천","부평","신경서S/S #1 Sh.R CB"," 2023년 부평전력지사 362kV GIS 정밀점검"," 2023년 부평전력지사 362kV GIS 정밀점검","2023-06-20 09:00","2023-06-23 18:00","취소","취소","연속"]
[34,"인천","부평","서인천C/C CB 7172"," 서인천C/C 345kV #1 M.Tr 1차 7172GIS 보통점검"," 서인천C/C 345kV #1 M.Tr 1차 7172GIS 보통점검","2023-06-20 09:00","2023-06-20 18:00","2023-06-20 09:00","2023-06-20 18:00","연속"]
[35,"인천","부평","인천C/C CB 7571"," 인천CC 345kV 인천복합 #3,4 G/T 7571 GIS 보통점검"," 인천CC 345kV 인천복합 #3,4 G/T 7571 GIS 보통점검","2023-06-21 09:00","2023-06-21 18:00","2023-06-21 09:00","2023-06-21 18:00","연속"]
[36,"인천","직할","신부평S/S #1 Sh.R CB"," 신부평S/S 345kV 7179 GIS 정밀점검"," 신부평S/S 345kV 7179 GIS 정밀점검","2023-06-26 09:30","2023-06-30 18:00","취소","취소","연속"]
[37,"인천","부평","인천C/C CB 7271"," 인천CC 345kV 신경서-인천CC#1T/L 7271GIS 조작시험"," 인천CC 345kV 신경서-인천CC#1T/L 7271GIS 조작시험","2023-06-28 09:00","2023-06-28 12:00","2023-06-28 09:00","2023-06-28 12:00","연속"]
[38,"인천","부평","인천C/C CB 7200"," 인천CC 345kV 신경서-인천CC#1T/L 7200GIS 조작시험"," 인천CC 345kV 신경서-인천CC#1T/L 7200GIS 조작시험","2023-06-28 13:00","2023-06-28 18:00","2023-06-28 13:00","2023-06-28 18:00","연속"]
[39,"경기북부","고양","신덕은동두천CC#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","불량애자 교체","2023-06-09 12:00","2023-06-09 18:00","2023-06-09 12:00","2023-06-09 18:00","연속"]
[40,"경기북부","고양","신덕은S/S #4 M.Tr","2023년도 고양전력지사 362kV, 170kV GIS 보통점검공사","362kV GIS 보통점검 (7472 GIS)","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[41,"경기북부","고양","신파주신덕은#2 T/L","2023년도 고양전력지사 362kV, 170kV GIS 보통점검공사","362kV GIS 보통점검 (7571 GIS)","2023-06-12 09:00","2023-06-12 18:00","2023-06-12 09:00","2023-06-12 18:00","연속"]
[42,"경기북부","구리","미금S/S #1 Sh.R","2022~23 구리전력 변전협력회사 총액공사","미금S/S 345kV #1Sh.R 초기점검","2023-06-09 09:00","2023-06-09 18:00","2023-06-09 09:00","2023-06-09 18:00","연속"]
[43,"경기북부","구리","미금S/S #1 BUS Sh.R MAIN CB 7079","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV #1 BUS Sh.R MAIN GIS 조작시험 7079","2023-06-28 13:00","2023-06-28 15:30","2023-06-28 13:00","2023-06-28 15:30","연속"]
[44,"경기북부","구리","미금S/S #6 Sh.R CB","2022~23 구리전력 변전협력 총액공사","미금S/S 345kV #6 Sh.R GIS 조작시험 7679","2023-06-28 09:00","2023-06-28 12:30","2023-06-28 09:00","2023-06-28 12:30","연속"]
[45,"경기북부","구리","미금S/S CB 7771","2022~23 구리전력 변전협력 총액공사","미금SA 345KV 신가평-미금#1T/L 7771 GIS 보통점검","2023-06-29 09:00","2023-06-29 18:00","2023-06-29 09:00","2023-06-29 18:00","연속"]
[46,"경기북부","구리","미금S/S #3 VSR CB","#3VSR 설치공사관련 방음벽 재설치공사","#3VSR 설치공사관련 방음벽 재설치공사","2023-06-19 09:00","2023-06-23 18:00","취소","취소","연속"]
[47,"경기북부","구리","신가평S/S CB 7371","2022~23 구리전력 변전협력 총액공사","신가평S/S 345kV #2 Sh.R GIS 보통점검 7379","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[48,"경기북부","구리","신가평S/S #2 Sh.R CB","2022~23 구리전력 변전협력 총액공사","신가평S/S 345kV #2 Sh.R GIS 보통점검 7379 - Sh.R 개방용 7371 휴전","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[49,"경기북부","구리","신가평S/S CB 7372","2022~23 구리전력 변전협력 총액공사","신가평S/S 신가평-포천LNGCC#2T/L GIS 보통점검 7372","2023-06-02 09:00","2023-06-02 18:00","2023-06-02 09:00","2023-06-02 18:00","연속"]
[50,"경기북부","구리","신가평S/S CB 7771","2022~23 구리전력 변전협력 총액공사","신가평S/S #3 M.Tr 2차 GIS 보통점검 7771","2023-06-27 09:00","2023-06-27 18:00","2023-06-27 09:00","2023-06-27 18:00","연속"]
[51,"경기북부","구리","신가평S/S #4 Sh.R CB","2022~23 구리전력 변전협력 총액공사","신가평S/S 345kV #4 Sh.R GIS 보통점검 7679 - Sh.R 개방용 7471 휴전","2023-06-26 09:00","2023-06-26 18:00","2023-06-26 09:00","2023-06-26 18:00","연속"]
[52,"경기북부","구리","신가평S/S CB 7671","2022~23 구리전력 변전협력 총액공사","신가평S/S 345kV #4 Sh.R GIS 보통점검 7679","2023-06-26 09:00","2023-06-26 18:00","2023-06-26 09:00","2023-06-26 18:00","연속"]
[53,"경기북부","구리","신가평S/S CB 7600","2022~23 구리전력 변전협력 총액공사","345kV #4 Sh.R-신가평신의정부#1T/L GIS 보통점검 7600","2023-06-26 09:00","2023-06-26 18:00","2023-06-26 09:00","2023-06-26 18:00","연속"]
[54,"경기북부","구리","신가평S/S CB 7571","2022~23 구리전력 변전협력 총액공사","신가평S/S #2 M.Tr 2차 GIS 보통점검 7571","2023-06-21 09:00","2023-06-21 18:00","2023-06-21 09:00","2023-06-21 18:00","연속"]
[55,"경기북부","구리","신가평S/S #3 Sh.R CB","2022~23 구리전력 변전협력 총액공사","신가평S/S 345kV #3 Sh.R GIS 보통점검 7479 - Sh.R 개방용 7471 휴전","2023-06-08 09:00","2023-06-08 18:00","2023-06-08 09:00","2023-06-08 18:00","연속"]
[56,"경기북부","구리","신가평S/S CB 7400","2022~23 구리전력 변전협력 총액공사","신가평S/S 345kV #3 Sh.R GIS 보통점검 7479 - Sh.R 개방용 7400 휴전","2023-06-08 09:00","2023-06-08 18:00","2023-06-08 09:00","2023-06-08 18:00","연속"]
[57,"경기북부","구리","신가평S/S CB 7472","2022~23 구리전력 변전협력 총액공사","신가평S/S 신가평-포천LNGCC#1T/L GIS 보통점검 7472","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[58,"경기북부","구리","신가평S/S CB 7300","2022~23 구리전력 변전협력 총액공사","신가평S/S 345kV #2 Sh.R GIS 보통점검 7379 - Sh.R 개방용 7300 휴전","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[59,"경기북부","구리","신포천S/S #3 M.Tr","신포천S/S 종합예방진단시스템 설치","○ 신포천S/S 종합예방진단시스템 설치 관련 규격 실측 - OLTC 부분방전 센서 및 설치위치 간섭여부 확인 - 부싱진단장치 제작 관련 시험탭 규격 실측 - DGA 배관 설치 길이 산출","2023-06-28 09:00","2023-06-28 18:00","2023-06-28 09:00","2023-06-28 18:00","연속"]
[60,"경기북부","구리","신포천S/S #2 M.Tr","신포천S/S 종합예방진단시스템 설치","○ 신포천S/S 종합예방진단시스템 설치 관련 규격 실측 - OLTC 부분방전 센서 및 설치위치 간섭여부 확인 - 부싱진단장치 제작 관련 시험탭 규격 실측 - DGA 배관 설치 길이 산출","2023-06-27 09:00","2023-06-27 18:00","2023-06-27 09:00","2023-06-27 18:00","연속"]
[61,"경기북부","구리","신포천S/S #4 M.Tr","신포천S/S 종합예방진단시스템 설치","○ 신포천S/S 종합예방진단시스템 설치 관련 규격 실측 - OLTC 부분방전 센서 및 설치위치 간섭여부 확인 - 부싱진단장치 제작 관련 시험탭 규격 실측 - DGA 배관 설치 길이 산출","2023-06-29 09:00","2023-06-29 18:00","2023-06-29 09:00","2023-06-29 18:00","연속"]
[62,"경기북부","구리","신포천S/S #1 M.Tr","신포천S/S 종합예방진단시스템 설치","○ 신포천S/S 종합예방진단시스템 설치 관련 규격 실측 - OLTC 부분방전 센서 및 설치위치 간섭여부 확인 - 부싱진단장치 제작 관련 시험탭 규격 실측 - DGA 배관 설치 길이 산출","2023-06-26 09:00","2023-06-26 18:00","2023-06-26 09:00","2023-06-26 18:00","연속"]
[63,"경기북부","직할","신의정부S/S #3 Sh.R CB","22-23년 변전 협력 총액공사","Sh.R 물청소","2023-06-27 15:00","2023-06-27 17:00","2023-06-27 15:00","2023-06-27 17:00","연속"]
[64,"경기북부","직할","신의정부S/S #2 Sh.R CB","22-23년 변전 협력 총액공사","Sh.R 물청소","2023-06-27 13:00","2023-06-27 15:00","2023-06-27 13:00","2023-06-27 15:00","연속"]
[65,"경기북부","직할","신의정부S/S #1 Sh.R CB","22-23년 변전 협력 총액공사","Sh.R 물청소","2023-06-27 09:00","2023-06-27 12:00","2023-06-27 09:00","2023-06-27 12:00","연속"]
[66,"경기북부","직할","신의정부S/S CB 7300","22-23년도 직할 변전협력회사 총액공사","신의정부SS 362kV GIS 7300 조작시험","2023-06-08 13:00","2023-06-08 18:00","2023-06-08 13:00","2023-06-08 18:00","연속"]
[67,"경기북부","직할","신의정부S/S CB 7371","22-23년도 직할 변전협력회사 총액공사","신의정부SS 362kV GIS 7371 조작시험","2023-06-08 09:00","2023-06-08 13:00","2023-06-08 09:00","2023-06-08 13:00","연속"]
[68,"경기북부","직할","신가평신의정부#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 345kV 신가평-신의정부T/L No.102~134,136,138","2023-06-12 07:00","2023-06-20 18:00","2023-06-12 07:00","2023-06-20 18:00","연속"]
[69,"경기북부","직할","양주S/S CB 7171","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV GIS 7171 보통점검, 전자변교체","2023-06-20 09:00","2023-06-20 18:00","2023-06-20 09:00","2023-06-20 18:00","연속"]
[70,"경기북부","직할","양주S/S CB 7100","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV GIS 7100 보통점검, 전자변교체","2023-06-21 09:00","2023-06-21 18:00","2023-06-21 09:00","2023-06-21 18:00","연속"]
[71,"경기북부","직할","양주S/S #2 M.Tr","양주S/S 23kV SIS PT 구조개선 공사 및 M.Tr 보통점검","양주S/S 23kV SIS PT 구조개선 공사 M.Tr 보통점검 및 OLTC(B상) 정밀점검","2023-06-26 09:00","2023-06-30 18:00","2023-06-26 09:00","2023-06-30 18:00","연속"]
[72,"경기북부","직할","양주S/S #4 Sh.R CB","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV GIS 7672 전자변교체, #4Sh.R GIS 하자보수","2023-06-29 09:00","2023-06-29 18:00","2023-06-29 09:00","2023-06-29 18:00","연속"]
[73,"경기북부","직할","양주S/S CB 7600","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV GIS 7672 전자변교체, #4Sh.R GIS 하자보수","2023-06-29 09:00","2023-06-29 18:00","2023-06-29 09:00","2023-06-29 18:00","연속"]
[74,"경기북부","직할","양주S/S #4 M.Tr","양주S/S 23kV SIS PT 구조개선 공사","양주S/S 23kV SIS PT 구조개선 공사","2023-06-12 09:00","2023-06-14 18:00","2023-06-12 09:00","2023-06-14 18:00","연속"]
[75,"경기북부","직할","양주S/S CB 7672","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV GIS 7672 CB 전자변교체","2023-06-29 09:00","2023-06-29 18:00","2023-06-29 09:00","2023-06-29 18:00","연속"]
[76,"경기북부","직할","양주S/S #3 M.Tr","양주S/S 23kV SIS PT 구조개선 공사","양주S/S 23kV SIS PT 구조개선 공사","2023-06-20 09:00","2023-06-22 18:00","2023-06-20 09:00","2023-06-22 18:00","연속"]
[77,"경기북부","직할","양주S/S #1 M.Tr","양주S/S 23kV SIS PT 구조개선 공사","양주S/S 23kV SIS PT 구조개선 공사","2023-06-15 09:00","2023-06-19 18:00","2023-06-15 09:00","2023-06-19 18:00","연속"]
[78,"경기북부","직할","양주S/S CB 7771","22-23년도 직할 변전협력회사 총액공사","양주SS 362kV GIS 7771 보통점검, 전자변교체","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[79,"경기북부","직할","양주중부#2 T/L","22~23년 고양전력 가공송전협력회사 총액공사","성능저하 지지애자 교체, 피뢰기 교체","2023-06-12 07:00","2023-06-14 18:00","2023-06-12 07:00","2023-06-14 18:00","매일"]
[80,"경기북부","직할","양주S/S STATCOM CB","22-23년도 직할 변전협력회사 총액공사","양주S/S 345kV STATCOM 냉각설비 세정","2023-06-01 13:00","2023-06-01 18:00","2023-06-01 13:00","2023-06-01 18:00","연속"]
[81,"경기북부","직할","양주S/S CB 7771","22-23년도 직할 변전협력회사 총액공사","양주S/S 345kV STATCOM 냉각설비 세정","2023-06-01 13:00","2023-06-01 18:00","2023-06-01 13:00","2023-06-01 18:00","연속"]
[82,"경기북부","직할","양주S/S #6 Sh.R CB","22-23년도 직할 변전협력회사 총액공사","양주SS 345kV #6Sh.R 보통점검","2023-06-12 09:00","2023-06-13 18:00","2023-06-12 09:00","2023-06-13 18:00","매일"]
[83,"경기북부","직할","양주중부#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","성능저하 지지애자 교체","2023-06-15 07:00","2023-06-16 18:00","2023-06-15 07:00","2023-06-16 18:00","매일"]
[84,"경기북부","직할","양주S/S #5 Sh.R CB","22-23년도 직할 변전협력회사 총액공사","양주SS 345kV #5Sh.R 보통점검","2023-06-15 09:00","2023-06-16 18:00","2023-06-15 09:00","2023-06-16 18:00","매일"]
[85,"경기","군포","신안산S/S CB 7371","신안산S/S 7371 GIS 하자점검","신안산S/S 7371 GIS 하자점검","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[86,"경기","성남","신성남S/S #1 M.Tr","23년 성남전력 170, 362kV GIS 보통점검공사","- 7100, 7172 GIS 보통점검","2023-06-13 09:00","2023-06-14 18:00","2023-06-13 09:00","2023-06-14 18:00","연속"]
[87,"경기","성남","신성남S/S CB 7171","23년 성남전력 170, 362kV GIS 보통점검공사","- 7171GIS 보통점검","2023-06-23 09:00","2023-06-23 18:00","2023-06-23 09:00","2023-06-23 18:00","연속"]
[88,"경기","성남","신성남S/S CB 7271","23년 성남전력 170, 362kV GIS 보통점검공사","- 7271GIS 보통점검","2023-06-27 09:00","2023-06-27 18:00","2023-06-27 09:00","2023-06-27 18:00","연속"]
[89,"경기","성남","곤지암동서울#1 T/L","추락방지장치(수평) 설치공사","추락방지장치(수평) 설치공사","2023-06-07 07:00","2023-06-12 18:00","2023-06-07 07:00","2023-06-12 18:00","연속"]
[90,"경기","성남","곤지암동서울#2 T/L","추락방지장치(수평) 설치공사","추락방지장치(수평) 설치공사","2023-06-13 07:00","2023-06-15 18:00","2023-06-13 07:00","2023-06-15 18:00","연속"]
[91,"경기","성남","신성남동서울#1 T/L","추락방지장치(수평) 설치공사","41기","2023-06-17 07:00","2023-06-20 18:00","2023-06-17 07:00","2023-06-20 18:00","연속"]
[92,"경기","성남","신성남S/S #3 M.Tr","23년 성남전력 170, 362kV GIS 보통점검공사","- 7300, 7372 GIS 보통점검","2023-06-15 09:00","2023-06-16 18:00","2023-06-15 09:00","2023-06-16 18:00","연속"]
[93,"경기","성남","신성남동서울#2 T/L","추락방지장치(수평) 설치공사","41기","2023-06-21 07:00","2023-06-22 18:00","2023-06-21 07:00","2023-06-22 18:00","연속"]
[94,"경기","성남","신수원삼성#2 T/L","LS제 362kV GIS 설비개선공사","- 제작사 EDS Unit 교체","2023-06-14 09:00","2023-06-16 18:00","2023-06-14 09:00","2023-06-16 18:00","연속"]
[95,"경기","성남","신수원삼성#1 T/L","LS제 362kV GIS 설비개선공사","- 제작사 EDS Unit 교체","2023-06-07 09:00","2023-06-09 18:00","2023-06-07 09:00","2023-06-09 18:00","연속"]
[96,"경기","성남","신용인삼성 T/L","23년 성남전력 170, 362kV GIS 보통점검공사","- 7671, 7600 GIS 보통점검","2023-06-28 09:00","2023-06-30 18:00","2023-06-28 09:00","2023-06-30 18:00","연속"]
[97,"경기","성남","신안성신용인#2 T/L","23년 성남전력지사 변전협력회사 총액공사","- CVT 초기점검","2023-06-09 09:00","2023-06-09 18:00","2023-06-09 09:00","2023-06-09 18:00","연속"]
[98,"경기","성남","신용인S/S #4 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- 1차 CVT 하자점검","2023-06-20 09:00","2023-06-20 18:00","2023-06-20 09:00","2023-06-20 18:00","연속"]
[99,"경기","직할","화성S/S #70 BUS","화성S/S 345kV GIS 용량대체공사","73Bay 무부하가압(7371 CB)","2023-06-17 07:00","2023-06-18 07:00","2023-06-17 07:00","2023-06-18 07:00","연속"]
[100,"경기","직할","화성S/S #75 BUS","화성S/S 345kV GIS 용량대체공사","73Bay 무부하가압(7300, 7372 CB)","2023-06-18 07:00","2023-06-19 07:00","2023-06-18 07:00","2023-06-19 07:00","연속"]
[101,"경기","직할","화성평택TP#2 T/L","154kV 화성-장덕T/L OPGW 증설공사","154kV 화성-장덕T/L OPGW 증설공사","2023-06-21 09:00","2023-06-23 18:00","2023-06-21 09:00","2023-06-23 18:00","연속"]
[102,"경기","직할","아산화성#1 T/L","154kV 화성-장덕T/L OPGW 증설공사","154kV 화성-장덕T/L OPGW 증설공사","2023-06-24 09:00","2023-06-26 13:00","취소","취소","연속"]
[103,"경기","직할","아산화성#2 T/L","154kV 화성-장덕T/L OPGW 증설공사","154kV 화성-장덕T/L OPGW 증설공사","2023-06-27 09:00","2023-06-28 18:00","취소","취소","연속"]
[104,"경기","직할","화성평택TP#1 T/L","154kV 화성-장덕T/L OPGW 증설공사","154kV 화성-장덕T/L OPGW 증설공사","2023-06-27 09:00","2023-06-28 18:00","2023-06-27 09:00","2023-06-28 18:00","연속"]
[105,"경기","평택","고덕#2S/S #2 M.Tr","345kV 고덕#2S/S 건설공사","154kV 고덕2-평택 #1T/L 무부하가압","2023-06-20 09:00","2023-06-21 18:00","2023-06-20 09:00","2023-06-21 18:00","연속"]
[106,"경기","평택","서안성S/S #3 M.Tr","23년 평택전력지사 변전협력회사 총액공사","서안성S/S #3M.Tr 변압기 보통점검, 부싱절연유 채유, 등받이울 설치","2023-06-08 09:00","2023-06-09 18:00","2023-06-08 09:00","2023-06-09 18:00","연속"]
[107,"경기","평택","서안성S/S CB 7471","현대제 345kV GIS 유압조작기 개선공사(7471)","서안성S/S 345kV 7471GIS 유압조작기 개선","2023-06-15 14:00","2023-06-15 18:00","2023-06-15 14:00","2023-06-15 18:00","연속"]
[108,"경기","평택","서안성S/S CB 7371","현대제 345kV GIS 유압조작기 개선공사(7371)","서안성S/S 345kV 7371GIS 유압조작기 개선","2023-06-01 09:00","2023-06-01 14:00","2023-06-01 09:00","2023-06-01 14:00","연속"]
[109,"경기","평택","서안성S/S CB 7372","현대제 345kV GIS 유압조작기 개선공사(7372)","서안성S/S 345kV 7372GIS 유압조작기 개선","2023-06-15 09:00","2023-06-15 14:00","2023-06-15 09:00","2023-06-15 14:00","연속"]
[110,"경기","평택","서안성S/S CB 7472","현대제 345kV GIS 유압조작기 개선공사(7472)","서안성S/S 345kV 7472GIS 유압조작기 개선","2023-06-02 14:00","2023-06-02 18:00","2023-06-02 14:00","2023-06-02 18:00","연속"]
[111,"경기","평택","서안성S/S CB 7300","현대제 345kV GIS 유압조작기 개선공사(7300)","서안성S/S 345kV 7300GIS 유압조작기 개선","2023-06-01 14:00","2023-06-01 18:00","2023-06-01 14:00","2023-06-01 18:00","연속"]
[112,"경기","평택","서안성S/S CB 7400","현대제 345kV GIS 유압조작기 개선공사(7400)","서안성S/S 345kV 7400GIS 유압조작기 개선","2023-06-02 09:00","2023-06-02 14:00","2023-06-02 09:00","2023-06-02 14:00","연속"]
[113,"경기","평택","평택T/P #2 CLR CB","23년 평택전력지사 변전협력회사 총액공사","평택T/P #2CLR 한류리액터 울타리 보수, 애자코팅","2023-06-21 09:00","2023-06-25 18:00","2023-06-21 09:00","2023-06-25 18:00","연속"]
[114,"경기","평택","평택T/P CB 7677","23년 평택전력지사 변전협력회사 총액공사","평택T/P #2CLR 한류리액터 울타리 보수, 애자코팅","2023-06-21 09:00","2023-06-25 18:00","2023-06-21 09:00","2023-06-25 18:00","연속"]
[115,"강원","강릉","신양양S/S #1 M.Tr","신양양S/S 종합예방진단시스템 설치 공사","#1M.Tr 부싱 누설전류 진단센서 설치관련 부싱 시험탭 수치 확인","2023-06-12 09:00","2023-06-12 18:00","2023-06-28 09:00","2023-06-28 18:00","연속"]
[116,"강원","강릉","신양양S/S CB 7300","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험 (7300)","2023-06-09 14:00","2023-06-09 18:00","2023-06-09 14:00","2023-06-09 18:00","연속"]
[117,"강원","강릉","신양양S/S CB 7372","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험 (7372)","2023-06-09 10:00","2023-06-09 14:00","2023-06-09 10:00","2023-06-09 14:00","연속"]
[118,"강원","강릉","신양양S/S CB 7100","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험 (7100)","2023-06-08 14:00","2023-06-08 18:00","2023-06-08 14:00","2023-06-08 18:00","연속"]
[119,"강원","강릉","신양양S/S CB 7172","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험 (7172)","2023-06-08 10:00","2023-06-08 14:00","2023-06-08 10:00","2023-06-08 14:00","연속"]
[120,"강원","강릉","신양양S/S #3 M.Tr","신양양S/S 종합예방진단시스템 설치 공사","#3M.Tr 부싱 누설전류 진단센서 설치관련 부싱 시험탭 수치 확인","2023-06-14 09:00","2023-06-14 18:00","2023-06-26 09:00","2023-06-26 18:00","연속"]
[121,"강원","강릉","신양양S/S #2 M.Tr","신양양S/S 종합예방진단시스템 설치 공사","#2M.Tr 부싱 누설전류 진단센서 설치관련 부싱 시험탭 수치 확인","2023-06-13 09:00","2023-06-13 18:00","2023-06-27 09:00","2023-06-27 18:00","연속"]
[122,"강원","강릉","양양P/P CB 7200","2023년 362kV GIS 정밀점검","362kV GIS 정밀점검 -(6/12~6/16) 7200GIS 정밀점검 -(6/19~6/23) 7272GIS 정밀점검 시 유도전압 관계로 동시휴전","2023-06-19 09:00","2023-06-30 18:00","2023-06-19 09:00","2023-06-30 18:00","연속"]
[123,"강원","강릉","신양양양양PP T/L","2022-23 변전협력회사 총액공사","신양양S/S 보호배전반 회로보완, LA점검 양양PP PT,LA보통점검, 7171장기미동작 차단기 동작시험","2023-06-20 10:00","2023-06-21 18:00","취소","취소","매일"]
[124,"강원","강릉","양양P/P CB 7272","2023년 362kV GIS 정밀점검","362kV GIS 정밀점검 (6/12~6/16) 7200GIS 정밀점검 시 유도전압 관계로 동시휴전 (6/19~6/23) 7272GIS 정밀점검","2023-06-19 09:00","2023-06-30 18:00","2023-06-19 09:00","2023-06-30 18:00","연속"]
[125,"강원","강릉","양양P/P CB 7271","2023년 362kV GIS 정밀점검","362kV GIS 정밀점검 - #2M.Tr 1차 GIS (7271)","2023-06-12 09:00","2023-06-16 18:00","2023-06-12 09:00","2023-06-16 18:00","연속"]
[126,"강원","강릉","양양P/P CB 7171","장기미동작 차단기 조작시험","장기미동작 차단기 조작시험 (7171)","2023-06-02 10:00","2023-06-02 18:00","2023-06-02 10:00","2023-06-02 18:00","연속"]
[127,"강원","동해","동해삼척GP#2 T/L","동해S/S 345kV 용량부족차단기 대체공사","동해S/S 345kV 76Bay 용량부족차단기 3CB 대체","2023-06-12 09:00","2023-08-12 18:00","취소","취소","연속"]
[128,"강원","동해","동해안인개폐소#2 T/L","2023년 동해전력지사 가공송전선로 순시점검 위탁공사","○345kV 동해-안인개폐소 #2 No.46~64 정밀점검","2023-06-12 09:00","2023-06-12 18:00","2023-06-12 09:00","2023-06-12 18:00","연속"]
[129,"강원","동해","동해S/S #3 M.Tr","동해S/S 345kV 용량부족차단기 대체공사","동해S/S 345kV 76Bay 용량부족차단기 3CB 대체","2023-06-12 09:00","2023-08-12 18:00","취소","취소","연속"]
[130,"강원","동해","동해북평TP#1 T/L","22~23 동해전력지사 변전정비 협력회사 공사","임시 SPS 설치관련 휴전","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[131,"강원","태백","신태백S/S CB 7400","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #2Sh.R GIS 조작시험","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[132,"강원","태백","신태백S/S CB 7471","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #2Sh.R GIS 조작시험","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[133,"강원","태백","신태백S/S #2 Sh.R CB","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #2Sh.R GIS 조작시험","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[134,"강원","태백","신태백S/S CB 7500","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #3Sh.R GIS 조작시험 345kV #3Sh.R 콘서베이터 절연유 보충(병행)","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[135,"강원","태백","신태백S/S #3 Sh.R CB","22-23년 태백전력지사 변전협력회사 총액공사","신태백변전소 345kV #3Sh.R GIS 조작시험신 345kV #3Sh.R 콘서베이터 절연유 보충(병행)","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[136,"강원","태백","신태백S/S CB 7571","22-23년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV #3h.R GIS 조작시험 345kV #3Sh.R 콘서베이터 절연유 보충(병행)","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[137,"충북","직할","신중부S/S #6 Sh.R CB","'22-23년 충북직할 변전협력회사 총액공사","신중부S/S 345kV #6 Sh.R 개폐용 GIS(7C79) 보통점검","2023-06-08 10:00","2023-06-08 18:00","2023-06-08 10:00","2023-06-08 18:00","연속"]
[138,"충북","직할","신중부S/S CB 7C71","'22-23년 충북직할 변전협력회사 총액공사","신중부S/S 345kV #6 Sh.R 1차 GIS(7C71) 보통점검","2023-06-09 10:00","2023-06-09 18:00","2023-06-09 10:00","2023-06-09 18:00","연속"]
[139,"충북","직할","신중부S/S CB 7A71","'22-23년 충북직할 변전협력회사 총액공사","신중부S/S 345kV #5 Sh.R 1차 GIS(7A71) 보통점검","2023-06-14 10:00","2023-06-14 18:00","2023-06-14 10:00","2023-06-14 18:00","연속"]
[140,"충북","직할","신중부S/S #5 Sh.R CB","'22-23년 충북직할 변전협력회사 총액공사","신중부S/S 345kV #5 Sh.R 개폐용 GIS(7A79) 보통점검","2023-06-15 10:00","2023-06-15 18:00","2023-06-15 10:00","2023-06-15 18:00","연속"]
[141,"충북","직할","신중부S/S #1 BUS","신중부S/S 345kV GIS DS Pin 교체공사","345kV GIS DS부 부분방전 발생에 따른 #1BUS DS Pin 교체공사 대상 : 7951, 7A51, 7B51, 7C51DS(4대)","2023-06-19 10:00","2023-06-22 18:00","2023-06-19 10:00","2023-06-22 18:00","연속"]
[142,"충북","직할","신중부S/S CB 7A00","'22-23년 충북직할 변전협력회사 총액공사","345kV 신중부-신진천#2T/L-#5 Sh.R TIE GIS 보통점검","2023-06-05 10:00","2023-06-05 18:00","2023-06-05 10:00","2023-06-05 18:00","연속"]
[143,"충북","직할","서안성신진천#2 T/L","2023년 충북직할 변전협력회사 총액공사","신진천S/S 345kV 서안성-신진천#2T/L 보호배전반 대체공사","2023-06-14 09:00","2023-06-16 18:00","2023-06-14 09:00","2023-06-16 18:00","연속"]
[144,"충북","직할","신진천S/S CB 7171","'22-23년 충북직할 변전협력회사 총액공사","신진천S/S 345kV 신중부-신진천#1T/L GIS 장기사용 PT 대체","2023-06-01 10:00","2023-06-02 18:00","2023-06-01 10:00","2023-06-02 18:00","연속"]
[145,"충북","직할","신진천S/S #3 M.Tr","23년도 상반기 충북본부 직할 154kV GIS 정밀점검공사","신진천변전소 154kV #3M.Tr 2차 GIS 정밀점검","2023-06-10 09:00","2023-06-13 18:00","2023-06-10 09:00","2023-06-13 18:00","연속"]
[146,"충북","청주","남청주S/S #3 M.Tr","남청주S/S 장기사용 감시제어반 대체공사","감시/제어/경보 포인트 (구)모자익 → (신)집감반 이설 (즉시가압 가능)","2023-06-19 09:00","2023-06-20 18:00","2023-06-19 09:00","2023-06-20 18:00","연속"]
[147,"충북","청주","신중부남청주#2 T/L","2022~2023년 청주전력지사 송전협력회사 총액공사(추락방지시설 설치)","345kV 신중부-남청주#2T/L 수평 추락방지시설 설치(No.1~74, 52기)","2023-06-12 07:00","2023-06-17 18:00","취소","취소","매일"]
[148,"충북","청주","남청주S/S #4 M.Tr","남청주S/S 장기사용 감시제어반 대체공사","#4 M.Tr 보호반 노후대체 감시/제어/경보 포인트 (구)모자익 → (신)집감반 이설","2023-06-12 09:00","2023-06-14 18:00","2023-06-12 09:00","2023-06-14 18:00","연속"]
[149,"충북","청주","남청주S/S #2 M.Tr","남청주S/S 장기사용 감시제어반 대체공사","감시/제어/경보 포인트 (구)모자익 → (신)집감반 이설 (즉시가압 가능)","2023-06-15 09:00","2023-06-16 18:00","2023-06-15 09:00","2023-06-16 18:00","연속"]
[150,"충북","청주","신중부남청주#1 T/L","2022~2023년 청주전력지사 송전협력회사 총액공사(추락방지시설 설치)","345kV 신중부-남청주#1T/L 수평 추락방지시설 설치(No.1~74, 52기)","2023-06-19 07:00","2023-06-24 18:00","취소","취소","매일"]
[151,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","60-61 BUS SEC GIS 교체 (안전이격확보)","2023-06-09 09:00","2023-06-09 18:00","2023-06-09 09:00","2023-06-09 18:00","연속"]
[152,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","60-61 BUS SEC GIS 교체 (안전이격확보)","2023-06-03 09:00","2023-06-05 18:00","2023-06-03 09:00","2023-06-05 18:00","연속"]
[153,"대전세종충남","대전","신옥천신계룡 T/L","(5월취소시)[송전]345kV신옥천-청양등2개T/L추락방지장치설치공사","(5월 취소시)[송전] 345V 신옥천-신계룡T/L 추락방지장치 설치공사","2023-06-05 08:00","2023-06-09 18:00","취소","취소","매일"]
[154,"대전세종충남","대전","신계룡청양 T/L","(5월취소시)[송전]345kV신옥천-청양등2개T/L추락방지장치설치공사","(5월 취소시)[송전] 345V 신계룡-청양T/L 추락방지장치 설치공사","2023-06-12 08:00","2023-06-15 18:00","취소","취소","매일"]
[155,"대전세종충남","서산","당진T/P #71 Tie-Tr","'23년 장기 미동작 차단기 조작시험","당진화력S/S 345kV #71 Tie.Tr 1, 2차 GIS(7171, 7100, 6144) 조작시험","2023-06-28 09:00","2023-06-28 18:00","취소","취소","연속"]
[156,"대전세종충남","서산","신당진개폐소S/S CB 7C72","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 7C72 GIS 보통점검","2023-06-20 09:00","2023-06-20 18:00","2023-06-20 09:00","2023-06-20 18:00","연속"]
[157,"대전세종충남","서산","신당진개폐소S/S CB 7C71","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 7C71 GIS 보통점검","2023-06-15 09:00","2023-06-15 18:00","2023-06-15 09:00","2023-06-15 18:00","연속"]
[158,"대전세종충남","서산","신당진개폐소S/S SEC CB 7A7B0","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 7A-7B-0 GIS 보통점검","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[159,"대전세종충남","서산","신당진개폐소S/S CB 7C00","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 7C00 GIS 보통점검","2023-06-13 09:00","2023-06-13 18:00","2023-06-13 09:00","2023-06-13 18:00","연속"]
[160,"대전세종충남","서산","신당진개폐소S/S SEC CB 7C7D0","23년 서산P/O 345kV GIS 보통점검공사","신당진개폐소 345kV 7C-7D-0 GIS 보통점검","2023-06-08 09:00","2023-06-08 18:00","2023-06-08 09:00","2023-06-08 18:00","연속"]
[161,"대전세종충남","서산","신서산신당진#2 T/L","23년 서산P/O 장기사용 노후 배전반 대체공사","(신서산-신중부#2T/L 휴전 불가시) 신서산S/S 345kV 77B/F 보호반 대체","2023-06-12 09:00","2023-06-16 18:00","2023-06-12 09:00","2023-06-16 18:00","연속"]
[162,"대전세종충남","서산","신서산S/S #2 BUS","23년 서산P/O 장기사용 노후 배전반 대체공사","(신서산S/S 345kV #1BUS 휴전불가시) 신서산S/S 345kV #2BUS 보호반 대체","2023-06-19 09:00","2023-06-23 18:00","취소","취소","연속"]
[163,"대전세종충남","서산","신서산S/S #4 Sh.R CB","23년 서산P/O 장기사용 노후 배전반 대체공사","(신서산-신중부#2T/L 휴전 불가시) 신서산S/S 345kV 77B/F 보호반 대체","2023-06-12 09:00","2023-06-16 18:00","취소","취소","연속"]
[164,"대전세종충남","서산","신서산S/S #1 BUS","23년 서산P/O 장기사용 노후 배전반 대체공사","신서산S/S 345kV #1BUS 보호반 대체","2023-06-19 09:00","2023-06-23 18:00","취소","취소","연속"]
[165,"대전세종충남","서산","태안T/P CB 7972","23년 서산P/O 345kV GIS 보통점검공사","GIS 보통점검","2023-06-29 09:00","2023-06-29 18:00","2023-06-29 09:00","2023-06-29 18:00","연속"]
[166,"대전세종충남","서산","태안T/P CB 7900","23년 서산P/O 345kV GIS 보통점검공사","GIS 보통점검","2023-06-27 09:00","2023-06-27 18:00","2023-06-27 09:00","2023-06-27 18:00","연속"]
[167,"대전세종충남","서산","태안T/P CB 7971","23년 서산P/O 345kV GIS 보통점검공사","GIS 보통점검","2023-06-22 09:00","2023-06-22 18:00","2023-06-22 09:00","2023-06-22 18:00","연속"]
[168,"대전세종충남","천안","신온양S/S CB 7571, 7500","345kV 75Bay 차단기 동작실패 보호반 교체","345kV 75Bay 차단기 동작실패 보호반 교체","2023-06-12 09:00","2023-06-16 18:00","2023-06-12 09:00","2023-06-16 18:00","연속"]
[169,"대전세종충남","천안","신온양서서울#2 T/L","345kV 77Bay 차단기 동작실패 보호반 교체","345kV 77Bay 차단기 동작실패 보호반 교체","2023-06-19 09:00","2023-06-23 18:00","취소","취소","연속"]
[170,"대전세종충남","천안","신온양S/S #4 M.Tr","345kV 77Bay 차단기 동작실패 보호반 교체","345kV 77Bay 차단기 동작실패 보호반 교체","2023-06-19 09:00","2023-06-23 18:00","2023-06-19 09:00","2023-06-23 18:00","연속"]
[171,"대전세종충남","천안","신온양서서울#1 T/L","345kV 78Bay 차단기 동작실패 보호반 교체","345kV 78Bay 차단기 동작실패 보호반 교체","2023-06-26 09:00","2023-06-30 18:00","취소","취소","연속"]
[172,"대전세종충남","천안","신온양S/S #3 M.Tr","345kV 75Bay 차단기 동작실패 보호반 교체","345kV 75Bay 차단기 동작실패 보호반 교체","2023-06-12 09:00","2023-06-16 18:00","2023-06-12 09:00","2023-06-16 18:00","연속"]
[173,"대전세종충남","천안","신온양S/S #3 M.Tr","신온양S/S 345kV #3M.Tr 1,2차 부싱절연유 채유","신온양S/S 345kV #3 M.Tr 1,2차 부싱절연유 채유","2023-06-09 09:00","2023-06-09 18:00","취소","취소","연속"]
[174,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S #4M.Tr 2차 6444GIS 보통점검","신온양S/S #4M.Tr 2차 6444GIS 보통점검","2023-06-30 09:00","2023-06-30 18:00","취소","취소","연속"]
[175,"대전세종충남","천안","신온양신탕정#2 T/L","345kV 78Bay 차단기 동작실패 보호반 교체","345kV 78Bay 차단기 동작실패 보호반 교체","2023-06-26 09:00","2023-06-30 18:00","2023-06-26 09:00","2023-06-30 18:00","연속"]
[176,"대전세종충남","천안","청양신탕정#2 T/L","[5월 휴전 미승인시]´22~23년 천안전력지사 송전협력회사 총액공사","- 345kV 청양-신탕정 #2T/L 피뢰기 설치(우기 대비 긴급 시행) - 345kV 청양-신탕정 #2T/L 이도 조정 - 345kV 청양-신탕정 #2T/L 추락방지장치 설치 ※ 주말작업 없음","2023-06-01 08:00","2023-06-15 18:00","취소","취소","매일"]
[177,"대전세종충남","천안","신탕정S/S #1 M.Tr","345kV 신탕정S/S 345kV #1M.Tr 배기팬 불량 교체","345kV 신탕정S/S 345kV #1M.Tr 배기팬 불량 교체","2023-06-08 09:00","2023-06-08 18:00","2023-06-08 09:00","2023-06-08 18:00","연속"]
[178,"대전세종충남","천안","신서산아산#1 T/L","345kV 신서산-아산#1T/L GIS,LA,CVT 보통점검","345kV 신서산-아산#1T/L GIS,LA,CVT 보통점검","2023-06-12 09:00","2023-06-12 18:00","취소","취소","연속"]
[179,"대전세종충남","천안","아산S/S #1 M.Tr","아산S/S 345kV #1 M.Tr 2차 부싱절연유 채유","아산S/S 345kV #1 M.Tr 2차 부싱절연유 채유","2023-06-12 09:00","2023-06-12 18:00","2023-06-12 09:00","2023-06-12 18:00","연속"]
[180,"대전세종충남","천안","아산S/S CB 7800","아산S/S 345kV 7800, 7872 GIS 보통점검","아산S/S 345kV 7800, 7872 GIS 보통점검","2023-06-15 09:00","2023-06-15 14:00","2023-06-15 09:00","2023-06-15 14:00","연속"]
[181,"대전세종충남","천안","아산S/S CB 7872","아산S/S 345kV 7800, 7872 GIS 보통점검","아산S/S 345kV 7800, 7872 GIS 보통점검","2023-06-15 14:00","2023-06-15 18:00","2023-06-15 14:00","2023-06-15 18:00","연속"]
[182,"대전세종충남","천안","신서산아산#2 T/L","345kV 신서산-아산#2T/L GIS,LA,CVT 보통점검","345kV 신서산-아산#2T/L GIS,LA,CVT 보통점검","2023-06-20 09:00","2023-06-20 18:00","취소","취소","연속"]
[183,"대전세종충남","천안","아산화성#2 T/L","345kV 아산-화성#2/L GIS 보통점검","345kV 아산-화성#2/L GIS 보통점검","2023-06-23 09:00","2023-06-23 18:00","취소","취소","연속"]
[184,"대전세종충남","천안","아산S/S CB 7500","아산S/S 345kV 7500, 7400 GIS 보통점검","아산S/S 345kV 7500, 7400 GIS 보통점검","2023-06-27 09:00","2023-06-27 14:00","2023-06-27 09:00","2023-06-27 14:00","연속"]
[185,"대전세종충남","천안","아산보령TP#2 T/L","345kV 아산-보령화력#2/L GIS 보통점검","345kV 아산-보령화력#2/L GIS 보통점검","2023-06-30 09:00","2023-06-30 18:00","2023-06-30 09:00","2023-06-30 18:00","연속"]
[186,"대전세종충남","천안","아산S/S CB 7400","아산S/S 345kV 7500, 7400 GIS 보통점검","아산S/S 345kV 7500, 7400 GIS 보통점검","2023-06-27 14:00","2023-06-27 18:00","2023-06-27 14:00","2023-06-27 18:00","연속"]
[187,"대전세종충남","청양","보령C/C CB 7400","청양P/O 362kV GIS 보통점검공사","362kV GIS 보통점검","2023-06-07 09:00","2023-06-07 14:00","취소","취소","연속"]
[188,"대전세종충남","청양","보령C/C CB 7472","청양P/O 362kV GIS 보통점검공사","362kV GIS 보통점검","2023-06-07 14:00","2023-06-07 18:00","취소","취소","연속"]
[189,"대전세종충남","청양","보령T/P CB 7272","(5월취소시)청양P/O 362kV GIS 보통점검공사","362kV GIS 보통점검","2023-06-09 10:00","2023-06-09 18:00","취소","취소","연속"]
[190,"대전세종충남","청양","보령T/P CB 7200","청양P/O 362kV GIS 보통점검공사","362kV GIS 보통점검","2023-06-08 10:00","2023-06-08 18:00","취소","취소","연속"]
[191,"대전세종충남","청양","청양군산#2 T/L","(73BAY 휴전 불가시)청양P/O 변전협력회사 총액공사","LA 하자점검(A,B,C), PT 보통점검(A,B,C) 362kV GIS 7372 보통점검","2023-06-16 10:00","2023-06-16 18:00","취소","취소","연속"]
[192,"대전세종충남","청양","청양신탕정#1 T/L","(73BAY 휴전 불가시)청양P/O 변전협력회사 총액공사","345kV 청양-신탕정#1T/L 보호반 대체 362kV GIS 보통점검(7371) 청양-신탕정#1T/L LA 보통점검(A,B,C) 및 PT 보통점검(A,B,C)","2023-06-19 08:00","2023-06-24 18:00","취소","취소","연속"]
[193,"대전세종충남","청양","청양신탕정#1 T/L","청양P/O 변전협력회사 총액공사","345kV 73BAY B/F 보호반 대체 및 청양-신탕정#1T/L 보호반 대체 362kV GIS 보통점검(7371) 청양-신탕정#1T/L LA 보통점검(A,B,C) 및 PT 보통점검(A,B,C)","2023-06-19 08:00","2023-06-27 18:00","취소","취소","연속"]
[194,"대전세종충남","청양","청양군산#2 T/L","청양P/O 변전협력회사 총액공사","345kV 73BAY B/F 보호반 대체 362kV GIS 보통점검(7372) 청양-군산#2T/L LA 하자점검(A,B,C) 및 PT 보통점검(A,B,C)","2023-06-19 08:00","2023-06-27 18:00","취소","취소","연속"]
[195,"대전세종충남","청양","청양S/S CB 7172","청양P/O 362kV GIS 보통점검공사","362kV GIS 보통점검","2023-06-28 10:00","2023-06-28 18:00","2023-06-28 10:00","2023-06-28 18:00","연속"]
[196,"대전세종충남","청양","청양S/S CB 7171","청양P/O 362kV GIS 보통점검공사","362kV GIS 보통점검","2023-06-29 10:00","2023-06-29 18:00","취소","취소","연속"]
[197,"대전세종충남","청양","청양S/S CB 7672","(청양-보령화력#2T/L 취소시)청양P/O 362kV GIS 보통점검공사","362kV GIS 보통점검","2023-06-14 10:00","2023-06-14 18:00","2023-06-14 10:00","2023-06-14 18:00","연속"]
[198,"대전세종충남","청양","청양보령TP#2 T/L","청양P/O 변전협력회사 총액공사","청양S/S 345kV 청양-보령화력#2T/L 보호반 대체공사 - 7300CB 부동작예방 조작시험, LA 및 PT 초기점검","2023-06-09 09:00","2023-06-14 18:00","2023-06-09 09:00","2023-06-14 18:00","연속"]
[199,"대전세종충남","청양","청양S/S CB 7100","청양P/O 362kV GIS 보통점검공사","362kV GIS 보통점검","2023-06-05 10:00","2023-06-05 18:00","취소","취소","연속"]
[200,"대전세종충남","청양","청양군산#1 T/L","청양P/O 변전협력회사 총액공사","LA 하자점검(A,B,C) 및 PT 보통점검(A,B,C) 362kV GIS 보통점검","2023-06-01 09:00","2023-06-01 18:00","취소","취소","연속"]
[201,"대전세종충남","청양","신옥천청양 T/L","(5월취소시)[송전]345kV신옥천-청양등2개T/L추락방지장치설치공사","(5월 취소시)[송전] 345V 신옥천-청양T/L 추락방지장치 설치공사","2023-06-16 08:00","2023-06-28 18:00","취소","취소","매일"]
[202,"전북","군산","군산신김제#1 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-06-11 07:00","2023-06-19 18:00","취소","취소","연속"]
[203,"전북","군산","군산S/S #4 M.Tr","군산S/S 154kV #4M.Tr 2차 GIS 정밀점검","군산S/S 154kV #4M.Tr 2차 GIS 정밀점검","2023-06-12 09:00","2023-06-14 18:00","2023-06-12 09:00","2023-06-14 18:00","연속"]
[204,"전북","군산","군산신김제#2 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-06-10 07:00","2023-06-10 18:00","취소","취소","연속"]
[205,"전북","군산","군산신김제#2 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-06-20 07:00","2023-06-28 18:00","취소","취소","연속"]
[206,"전북","군산","군산신김제#1 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-06-29 07:00","2023-07-07 18:00","취소","취소","연속"]
[207,"전북","군산","새만금S/S #2 M.Tr","군산P/O 주변압기 점검공사","군산P/O 주변압기 점검공사","2023-06-07 09:00","2023-06-08 18:00","취소","취소","연속"]
[208,"전북","군산","새만금S/S #3 M.Tr","군산P/O 주변압기 점검공사","군산P/O 주변압기 점검공사","2023-06-19 09:00","2023-06-20 18:00","취소","취소","연속"]
[209,"전북","김제","신김제S/S #4 M.Tr","신김제S/S 345kV #4M.Tr 2차 차단기 정밀점검","신김제S/S 345kV #4M.Tr 2차 차단기 정밀점검(6.20~22, 연속)","2023-06-20 09:00","2023-06-22 18:00","2023-06-20 09:00","2023-06-22 18:00","연속"]
[210,"전북","김제","신김제S/S #3 M.Tr","신김제S/S 345kV #3M.Tr 2차 차단기 정밀점검","신김제S/S 345kV #3M.Tr 2차 차단기 정밀점검(6.15~17, 연속)","2023-06-15 09:00","2023-06-17 18:00","2023-06-15 09:00","2023-06-17 18:00","연속"]
[211,"전북","직할","신남원S/S CB 7100","23년 전북직할 변전협력 총액공사","362kV GIS 보통점검(단일차단기)","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[212,"전북","직할","신남원광양#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원S/S #75Bay BF반 대체공사","2023-06-12 09:00","2023-06-16 18:00","취소","취소","연속"]
[213,"전북","직할","신남원광양#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원S/S #76Bay BF반 대체공사","2023-06-19 09:00","2023-06-23 18:00","취소","취소","연속"]
[214,"전북","직할","신남원S/S CB 7371","23년 전북직할 변전협력 총액공사","362kV GIS 보통점검(단일차단기)","2023-06-07 09:00","2023-06-08 18:00","2023-06-07 09:00","2023-06-08 18:00","연속"]
[215,"광주전남","광주","신광주S/S CB 7572","7579 GIS 하자점검","7579 GIS 하자점검","2023-06-09 09:00","2023-06-09 14:00","취소","취소","연속"]
[216,"광주전남","광주","신광주신화순#1 T/L","345kV 신광주-신화순T/L 추락방지시설설치공사","수평장치 설치 107기","2023-06-12 07:00","2023-06-19 18:00","취소","취소","연속"]
[217,"광주전남","광주","신광주S/S CB 7171","7171 GIS 보통점검","7171 GIS 보통점검","2023-06-05 09:00","2023-06-05 18:00","취소","취소","연속"]
[218,"광주전남","광주","신광주S/S #1 Sh.R CB","7579 GIS 하자점검관련 휴전","7579 GIS 하자점검관련 휴전","2023-06-08 09:00","2023-06-09 18:00","2023-06-08 09:00","2023-06-09 18:00","연속"]
[219,"광주전남","광주","신광주S/S CB 7572","7572 GIS 하자점검","7572 GIS 하자점검","2023-06-08 09:00","2023-06-08 18:00","2023-06-08 09:00","2023-06-09 14:00","연속"]
[220,"광주전남","광주","신광주S/S #1 M.Tr","23년 광주전력지사 변전협력회사 총액공사","- 362kV GIS(7472,7400) 조작시험 - #2M.Tr 3차 차단기 교체(3차 Main)","2023-06-08 09:00","2023-06-09 18:00","취소","취소","연속"]
[221,"광주전남","광주","신광주S/S #3 M.Tr","23년 광주전력지사 변전협력회사 총액공사","- 345kV M.Tr 보통점검 - 362kV GIS 조작시험(7600,7672) - #3M.Tr 3차 차단기 교체(3차 Main, #1,2Sh.R, S.Tr) - 3차측 DS 점검","2023-06-26 09:00","2023-06-30 18:00","취소","취소","연속"]
[222,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2023-06-26 09:00","2023-06-29 18:00","취소","취소","연속"]
[223,"광주전남","광주","신광주신화순#2 T/L","345kV 신광주-신화순T/L 추락방지시설설치공사","수평장치 설치 107기","2023-06-20 07:00","2023-06-27 18:00","취소","취소","연속"]
[224,"광주전남","광주","신광주S/S #1 M.Tr","23년 광주전력지사 변전협력회사 총액공사(신광주 #1M.Tr)","- #1M.Tr 3차측 차단기 교체(3차 Main, S.Tr) - 362kV GIS(7172 CB) 보통점검","2023-06-19 09:00","2023-06-21 18:00","취소","취소","연속"]
[225,"광주전남","광주","신광주S/S CB 7172","7172 GIS 보통점검","7172 GIS 보통점검","2023-06-19 09:00","2023-06-19 18:00","취소","취소","연속"]
[226,"광주전남","광주","신광주S/S CB 7400","7400 CB 조작시험","7400 CB 조작시험","2023-06-15 09:00","2023-06-15 18:00","2023-06-15 09:00","2023-06-15 18:00","연속"]
[227,"광주전남","광주","신광주S/S CB 7471","7471 CB 조작시험","7471 CB 조작시험","2023-06-14 09:00","2023-06-14 18:00","2023-06-14 09:00","2023-06-14 18:00","연속"]
[228,"광주전남","광주","신남원신광주#1 T/L","7471·7400 조작시험,현수애자점검","7471·7400 조작시험,현수애자점검","2023-06-14 09:00","2023-06-15 18:00","취소","취소","연속"]
[229,"광주전남","광주","신광주S/S CB 7800","7800 조작시험","7800 조작시험","2023-06-13 09:00","2023-06-13 18:00","2023-06-13 09:00","2023-06-13 18:00","연속"]
[230,"광주전남","광주","신광주S/S CB 7872","7872 조작시험","7872 조작시험","2023-06-12 09:00","2023-06-12 18:00","2023-06-12 09:00","2023-06-12 18:00","연속"]
[231,"광주전남","광주","신광주S/S #4 M.Tr","7872·7800 조작시험,현수애자점검,2차 LA 교체","7872·7800 조작시험,현수애자점검,2차 LA 교체","2023-06-12 09:00","2023-06-13 18:00","취소","취소","연속"]
[232,"광주전남","광주","신광주S/S CB 7500","7500 CB 조작시험","7500 CB 조작시험","2023-06-09 14:00","2023-06-09 18:00","2023-06-09 14:00","2023-06-09 18:00","연속"]
[233,"광주전남","광주","신화순S/S CB 7A00","7A00 CB 조작시험","7A00 CB 조작시험","2023-06-01 13:00","2023-06-01 18:00","취소","취소","연속"]
[234,"광주전남","광주","신화순S/S CB 7A71","7A71 CB 조작시험","7A71 CB 조작시험","2023-06-01 09:30","2023-06-01 13:00","취소","취소","연속"]
[235,"광주전남","광주","신화순신강진#1 T/L","7A71·7A00 조작시험,현수애자점검,LA보통점검","7A71·7A00 조작시험,현수애자점검,LA보통점검","2023-06-01 09:30","2023-06-01 18:00","2023-06-01 09:30","2023-06-01 18:00","연속"]
[236,"광주전남","광주","신화순S/S CB 7900","7900 CB 조작시험","7900 CB 조작시험","2023-06-02 09:30","2023-06-02 13:00","2023-06-02 09:30","2023-06-02 13:00","연속"]
[237,"광주전남","광주","신화순신강진#2 T/L","7971·7900 조작시험,현수애자점검,CVT보통점검","7971·7900 조작시험,현수애자점검,CVT보통점검","2023-06-02 09:30","2023-06-02 18:00","취소","취소","연속"]
[238,"광주전남","광주","신화순S/S CB 7971","7971 CB 조작시험","7971 CB 조작시험","2023-06-02 13:00","2023-06-02 18:00","2023-06-02 13:00","2023-06-02 18:00","연속"]
[239,"광주전남","목포","한빛1NP한빛2NP#2 T/L","22-23년 목포전력지사 변전협력회사 총액공사","한빛#1S/Y 7472, 7400 GIS 보통점검","2023-06-26 09:00","2023-06-27 18:00","취소","취소","연속"]
[240,"광주전남","목포","한빛1NP한빛2NP#1 T/L","22-23년 목포전력지사 변전협력회사 총액공사","한빛#1S/Y 7372, 7300 GIS 보통점검","2023-06-21 09:00","2023-06-22 18:00","취소","취소","연속"]
[241,"광주전남","목포","신김제한빛NP#2 T/L","22-23년 목포전력지사 변전협력회사 총액공사","345kV PT 보통점검","2023-06-20 09:00","2023-06-20 18:00","취소","취소","연속"]
[242,"광주전남","목포","신김제한빛NP#1 T/L","22-23년 목포전력지사 변전협력회사 총액공사","345kV GIS 보통점검 PT 보통점검","2023-06-19 09:00","2023-06-19 18:00","취소","취소","연속"]
[243,"광주전남","순천","광양CC여수TP#2 T/L","345kV 광양CC-신여수 지중T/L 운영시스템 설치공사","지중송전선로와 부대설비에 대한 실시간 감시, 제어를 통한 안정적인 전력공급(휴전작업공정 : EBA,EBG 센서 및 카메라 설치작업) 즉시가압여부 : 가능, 소요시간 20분","2023-06-14 09:00","2023-06-15 18:00","취소","취소","매일"]
[244,"광주전남","순천","광양CC여수TP#1 T/L","345kV 광양CC-신여수 지중T/L 운영시스템 설치공사","지중송전선로와 부대설비에 대한 실시간 감시, 제어를 통한 안정적인 전력공급(휴전작업공정 : EBA,EBG 센서 및 카메라 설치작업) 즉시가압여부 : 가능, 소요시간 20분","2023-06-12 09:00","2023-06-13 18:00","취소","취소","매일"]
[245,"광주전남","순천","신강진광양#1 T/L","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY] - BUS 무부하 가압","2023-06-28 18:00","2023-06-29 18:00","2023-06-28 18:00","2023-06-29 18:00","연속"]
[246,"광주전남","순천","광양광양CC#2 T/L","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY] - BUS 교체시 CVT, LA 임시철거 필요","2023-06-21 08:00","2023-06-26 08:00","2023-06-21 08:00","2023-06-26 08:00","연속"]
[247,"광주전남","순천","광양S/S SEC CB 70710","'22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 70-71 BUS-SEC GIS 하자점검(즉시가압가능)","2023-06-01 09:00","2023-06-01 18:00","취소","취소","연속"]
[248,"광주전남","순천","광양S/S #71 BUS","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY]","2023-06-02 08:00","2023-06-15 18:00","2023-06-02 08:00","2023-06-15 18:00","연속"]
[249,"광주전남","순천","광양광양제철#1 T/L","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY] - BUS 교체시 CVT, LA 임시철거 필요","2023-06-02 08:00","2023-06-07 08:00","2023-06-02 08:00","2023-06-07 08:00","연속"]
[250,"광주전남","순천","광양S/S SEC CB 75760","'22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 75-76 BUS-SEC GIS 하자점검(즉시가압 가능)","2023-06-02 09:00","2023-06-02 18:00","취소","취소","연속"]
[251,"광주전남","순천","광양여수TP T/L","345kV 광양-여수TP T/L 일부구간 지중화 공사","345kV 광양-여수TP 일부 지중화 관련 C/T 설치공사","2023-06-05 07:00","2023-06-09 18:00","취소","취소","연속"]
[252,"광주전남","순천","신강진광양#1 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 신강진-광양 #1T/L LA 보통점검(즉시가압 가능)","2023-06-05 09:00","2023-06-05 18:00","취소","취소","연속"]
[253,"광주전남","순천","광양광양제철#2 T/L","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY] - BUS 교체시 CVT, LA 임시철거 필요","2023-06-07 08:00","2023-06-12 08:00","2023-06-07 08:00","2023-06-12 08:00","연속"]
[254,"광주전남","순천","신강진광양#2 T/L","'22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 신강진-광양 #2T/L LA 보통점검(즉시가압 가능)","2023-06-07 09:00","2023-06-07 18:00","취소","취소","연속"]
[255,"광주전남","순천","신강진광양#1 T/L","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY] - BUS 무부하 가압","2023-06-13 18:00","2023-06-14 18:00","2023-06-13 18:00","2023-06-14 18:00","연속"]
[256,"광주전남","순천","광양S/S #76 BUS","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY]","2023-06-16 08:00","2023-06-30 18:00","2023-06-16 08:00","2023-06-30 18:00","연속"]
[257,"광주전남","순천","광양광양CC#1 T/L","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY] - BUS 교체시 CVT, LA 임시철거 필요","2023-06-16 08:00","2023-06-21 08:00","2023-06-16 08:00","2023-06-21 08:00","연속"]
[258,"광주전남","순천","여수T/P #1 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S #1M.Tr A,B상 1차 부싱교체, 2차 GIS 정밀점검, 1,2차 LA 초기점검 및 4184,4179-1 타임측정(즉시가압 불가)","2023-06-26 09:00","2023-06-30 18:00","2023-06-26 09:00","2023-06-30 18:00","연속"]
[259,"광주전남","순천","여수T/P CB 7171","'22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 광양C/C-여수TP #1T/L(7171) 보통점검(즉시가압 가능)","2023-06-01 09:00","2023-06-01 18:00","2023-06-01 09:00","2023-06-01 18:00","연속"]
[260,"광주전남","순천","여수T/P CB 7271","'22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 광양CC-여수TP #2T/L(7271) 보통점검(즉시가압 가능)","2023-06-02 09:00","2023-06-02 18:00","2023-06-02 09:00","2023-06-02 18:00","연속"]
[261,"광주전남","순천","여수T/P CB 7200","'22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 광양CC-여수TP #2T/L TIE (7200) 보통점검(즉시가압가능)","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[262,"광주전남","순천","여수T/P CB 7371","'22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 율촌C/C-여수T/P T/L(7371) 하자점검","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[263,"광주전남","순천","여수T/P SEC CB 70710","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 70-71 BUS-SEC GIS 하자점검(즉시가압가능)","2023-06-08 09:00","2023-06-08 18:00","2023-06-08 09:00","2023-06-08 18:00","연속"]
[264,"광주전남","순천","여수T/P #4 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력 #4M.Tr 7400 GIS 하자점검 1,2,3차 GIS 하자점검 #4M.Tr LA 2차 M.Tr 상부 하자점검(즉시가압 가능)","2023-06-19 09:00","2023-06-23 18:00","2023-06-19 09:00","2023-06-23 18:00","연속"]
[265,"광주전남","순천","여수T/P SEC CB 75760","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 75-76 BUS-SEC GIS 하자점검(즉시가압 가능)","2023-06-09 09:00","2023-06-09 18:00","2023-06-09 09:00","2023-06-09 18:00","연속"]
[266,"광주전남","순천","여수T/P #2 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S #2M.Tr 보통점검 OFU 필터교체, 및 1차 GIS 보통점검, 7200 GIS 보통점검, 2차 GIS 정밀점검, #2M.Tr 2차 LA 보통점검(즉시가압 불가)","2023-06-12 09:00","2023-06-16 18:00","2023-06-12 09:00","2023-06-16 18:00","연속"]
[267,"광주전남","순천","율촌C/C CB 7271","22-23년 순천전력지사 변전협력회사 총액공사","율촌C/C 광양-율촌C/C T/L(7171), 율촌C/C 율촌C/C-여수T/P T/L(7271) CB 타임측정(즉시가압가능)","2023-06-08 14:00","2023-06-08 18:00","2023-06-08 14:00","2023-06-08 18:00","연속"]
[268,"광주전남","순천","율촌C/C CB 7171","22-23년 순천전력지사 변전협력회사 총액공사","율촌C/C 광양-율촌C/C T/L(7171), 율촌C/C 율촌C/C-여수T/P T/L(7271) CB 타임측정(즉시가압가능)","2023-06-08 09:00","2023-06-08 14:00","2023-06-08 09:00","2023-06-08 14:00","연속"]
[269,"대구","달성","고령S/S #4 M.Tr","#4M.Tr 휴전","- 부싱절연유 채유 및 절연열화 측정 - #2S.Tr VCB 초기점검","2023-06-01 09:00","2023-06-01 18:00","2023-06-01 09:00","2023-06-01 18:00","연속"]
[270,"대구","달성","대구S/S CB 7100","7100 GIS보통점검","7100 GIS보통점검","2023-06-14 09:00","2023-06-14 18:00","2023-06-14 09:00","2023-06-14 18:00","연속"]
[271,"대구","달성","대구S/S #2 BUS","#2BUS 모선보호반 대체공사","#2BUS 모선보호반 대체공사","2023-06-26 09:00","2023-06-30 18:00","2023-06-26 09:00","2023-06-30 18:00","연속"]
[272,"대구","달성","대구S/S #1 BUS","#1BUS 모선보호반 대체공사","#1BUS 모선보호반 대체공사","2023-06-19 09:00","2023-06-23 18:00","2023-06-19 09:00","2023-06-23 18:00","연속"]
[273,"대구","달성","대구S/S CB 7200","7200 GIS보통점검","7200 GIS보통점검","2023-06-15 09:00","2023-06-15 18:00","2023-06-15 09:00","2023-06-15 18:00","연속"]
[274,"대구","칠곡","북대구S/S #1 Sh.R CB","북대구S/S 345kV #1Sh.R 보통점검","북대구S/S 345kV #1Sh.R 보통점검","2023-06-02 09:30","2023-06-02 18:00","2023-06-02 09:30","2023-06-02 18:00","연속"]
[275,"대구","포항","선산신포항 T/L","345kV 신포항-북대구T/L 지장송전선로 이설공사","44.2~45호 및 47~48호 전력선 설치 기설 44.2~48호 전력선 철거","2023-06-14 07:30","2023-06-29 18:00","2023-06-14 07:30","2023-06-29 18:00","연속"]
[276,"경북","구미","서대구선산#2 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","71Bay GIS 교체","2023-05-06 09:00","2023-07-18 18:00","취소","취소","연속"]
[277,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","#75BUS 교체관련 무부하가압","2023-06-01 09:00","2023-06-02 09:00","2023-06-05 09:00","2023-06-06 09:00","연속"]
[278,"경북","영주","신제천신영주#2 T/L","2023년 가공송전 순시점검 위탁공사 정밀점검","345kV신영주-신제천T/L 정밀점검","2023-06-19 09:00","2023-06-23 18:00","2023-06-19 09:00","2023-06-23 18:00","매일"]
[279,"경북","영주","신제천신영주#1 T/L","2023년 가공송전 순시점검 위탁공사 정밀점검","345kV신영주-신제천T/L 정밀점검","2023-06-12 09:00","2023-06-16 18:00","2023-06-12 09:00","2023-06-16 18:00","매일"]
[280,"경북","영주","신영주S/S #1 M.Tr","2022-23년 영주전력지사 변전협력회사 총액공사","1차 CB 보통점검 회로개선","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[281,"경북","직할","안동C/C CB 7100","22~23년 경북본부 직할 변전협력회사 총액공사","GIS 보통점검","2023-06-07 10:00","2023-06-07 18:00","2023-06-07 10:00","2023-06-07 18:00","연속"]
[282,"부산울산","동부산","고리1NP고리2NP#2 T/L","고리NP S/Y 345kV CLR 보통점검","1. 고리NP S/Y 345kV #2CLR 보통점검 2. 7677 GIS 보통점검, 7577GIS 차단기 동작시험","2023-06-26 09:00","2023-06-29 18:00","2023-06-26 09:00","2023-06-29 18:00","연속"]
[283,"부산울산","동부산","고리1NP고리2NP#1 T/L","고리NP S/Y 345kV CLR 보통점검","1. 고리NP S/Y 345kV #1CLR 보통점검 2. 7177 GIS 보통점검, 7077GIS 차단기 동작시험","2023-06-19 09:00","2023-06-22 18:00","2023-06-19 09:00","2023-06-22 18:00","연속"]
[284,"부산울산","동부산","신고리고리NP#1 T/L","765kV북경남-신고리 등 7개T/L 추락방지장치 설치공사","345kV 신고리-고리#1T/L 수평추락방지장치 설치 8기","2023-06-10 07:00","2023-06-10 18:00","2023-06-10 07:00","2023-06-10 18:00","연속"]
[285,"부산울산","동부산","신양산S/S #1 M.Tr","신양산S/S #1M.Tr 주변압기 보통점검","신양산S/S #1M.Tr 주변압기 보통점검","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[286,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S #2M.Tr 주변압기 보통점검","신양산S/S #2M.Tr 주변압기 보통점검","2023-06-08 09:00","2023-06-09 18:00","2023-06-08 09:00","2023-06-09 18:00","연속"]
[287,"부산울산","동부산","신양산S/S #3 M.Tr","신양산S/S #3M.Tr 주변압기 보통점검","신양산S/S #3M.Tr 주변압기 보통점검","2023-06-12 09:00","2023-06-13 18:00","2023-06-12 09:00","2023-06-13 18:00","연속"]
[288,"부산울산","동부산","신양산S/S #4 M.Tr","신양산S/S #4M.Tr 주변압기 보통점검","신양산S/S #4M.Tr 주변압기 보통점검","2023-06-14 09:00","2023-06-15 18:00","2023-06-14 09:00","2023-06-15 18:00","연속"]
[289,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-신울산#2T/L 수평추락방지장치 설치 : 1~110호, 87기","2023-06-04 08:00","2023-06-11 18:00","2023-06-04 08:00","2023-06-11 18:00","연속"]
[290,"부산울산","북부산","북부산S/S #2 M.Tr","22-23년 북부산전력지사 변전총액공사","북부산S/S #2-1Sh.R 시험가압","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[291,"부산울산","북부산","북부산S/S SEC CB 70710","22-23년 북부산전력지사 변전총액공사","북부산S/S 345kV #70-71 SEC 차단기 조작시험","2023-06-12 09:00","2023-06-12 14:00","2023-06-12 09:00","2023-06-12 14:00","연속"]
[292,"부산울산","북부산","북부산S/S SEC CB 75760","22-23년 북부산전력지사 변전총액공사","북부산S/S 345kV #75-76 SEC 차단기 조작시험","2023-06-12 14:00","2023-06-12 18:00","2023-06-12 14:00","2023-06-12 18:00","연속"]
[293,"부산울산","북부산","북부산S/S #1 Sh.R CB","2023년 북부산전력지사 345kV Sh.R 정밀점검","북부산S/S 345kV 서부산-북부산#1T/L Sh.R (#1Sh.R) 정밀점검","2023-06-19 09:00","2023-06-23 18:00","취소","취소","연속"]
[294,"부산울산","북부산","서부산북부산#1 T/L","2023년 북부산전력지사 345kV Sh.R 정밀점검","북부산S/S 345kV 서부산-북부산#1T/L Sh.R (#1Sh.R) 정밀점검 시험가압","2023-06-23 17:00","2023-06-23 18:00","취소","취소","연속"]
[295,"부산울산","북부산","북부산S/S #3 Sh.R CB","2023년 북부산전력지사 345kV Sh.R 정밀점검","북부산S/S 345kV 서부산-북부산#3T/L Sh.R (#3Sh.R) 정밀점검","2023-06-26 09:00","2023-06-30 18:00","2023-06-26 09:00","2023-06-30 18:00","연속"]
[296,"부산울산","북부산","북부산S/S #2 Sh.R CB","북부산S/S #2,4Sh.R 부싱절연유 채유","북부산S/S #2,4Sh.R 부싱절연유 채유","2023-06-27 10:00","2023-06-27 13:00","2023-06-27 10:00","2023-06-27 13:00","연속"]
[297,"부산울산","북부산","북부산S/S #4 Sh.R CB","북부산S/S #2,4Sh.R 부싱절연유 채유","북부산S/S #2,4Sh.R 부싱절연유 채유","2023-06-27 13:00","2023-06-27 17:00","2023-06-27 13:00","2023-06-27 17:00","연속"]
[298,"부산울산","북부산","북부산S/S CB 7972","북부산S/S #2,4Sh.R 부싱절연유 채유","북부산S/S #2,4Sh.R 부싱절연유 채유","2023-06-27 13:00","2023-06-27 17:00","2023-06-27 13:00","2023-06-27 17:00","연속"]
[299,"부산울산","북부산","북부산S/S CB 7900","북부산S/S #2,4Sh.R 부싱절연유 채유","북부산S/S #2,4Sh.R 부싱절연유 채유","2023-06-27 13:00","2023-06-27 17:00","2023-06-27 13:00","2023-06-27 17:00","연속"]
[300,"부산울산","북부산","서부산북부산#3 T/L","2023년 북부산전력지사 345kV Sh.R 정밀점검","북부산S/S 345kV 서부산-북부산#3T/L Sh.R (#3Sh.R) 정밀점검 시험가압","2023-06-30 17:00","2023-06-30 18:00","2023-06-30 17:00","2023-06-30 18:00","연속"]
[301,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-신울산#1T/L 수평추락방지장치 설치 : 1~110호, 87기","2023-06-22 08:00","2023-06-30 18:00","2023-06-22 08:00","2023-06-30 18:00","연속"]
[302,"부산울산","북부산","신김해북부산#1 T/L","2022~23년 북부산전력지사 가공송전 협력회사 총액공사","철탑도장 ○ 공사구간 : 345kV 신김해-북부산T/L 26,27호","2023-06-08 07:00","2023-06-09 18:00","취소","취소","연속"]
[303,"부산울산","북부산","신김해북부산#2 T/L","2022~23년 북부산전력지사 가공송전 협력회사 총액공사","철탑도장 ○ 공사구간 : 345kV 신김해-북부산T/L 26,27호","2023-06-28 07:00","2023-06-29 18:00","2023-06-28 07:00","2023-06-29 18:00","연속"]
[304,"부산울산","울산","남울산S/S CB 7400","345kV 남울산S/S 울산GPS 신규수용공사","362kV 63kA 6,300A GIS x 3CB 설치(7472,7200,7272) - 7400CB 휴전","2023-06-14 09:00","2023-06-16 18:00","2023-06-14 09:00","2023-06-16 18:00","연속"]
[305,"부산울산","울산","남울산울산TP#2 T/L","2023년 가공송전순시점검 위탁공사","[안전이격] 345KV 북부산-울산TP #1T/L 초기점검 관련 345KV 남울산-울산TP #2T/L 하단선로 안전이격 휴전","2023-06-08 08:00","2023-06-08 18:00","2023-06-08 08:00","2023-06-08 18:00","연속"]
[306,"부산울산","울산","남울산S/S #1 BUS","345kV 남울산S/S 울산GPS 신규수용공사","362kV 63kA 6,300A GIS x 3CB 설치(7472,7200,7272)","2023-06-12 15:00","2023-06-13 18:00","2023-06-12 15:00","2023-06-13 18:00","연속"]
[307,"부산울산","울산","남울산S/S #2 BUS","345kV 남울산S/S 울산GPS 신규수용공사","362kV 63kA 6,300A GIS x 3CB 설치(7472,7200,7272)","2023-06-12 09:00","2023-06-12 15:00","2023-06-12 09:00","2023-06-12 15:00","연속"]
[308,"부산울산","울산","남울산S/S 울산GPS#1T/L CB","345kV 남울산S/S 울산GPS 신규수용공사","362kV 63kA 6,300A GIS x 3CB 설치(7472,7200,7272) - 7472CB 휴전","2023-06-14 09:00","2023-06-16 18:00","2023-06-14 09:00","2023-06-16 18:00","연속"]
[309,"부산울산","울산","남울산S/S #2 M.Tr","345kV 남울산S/S 울산GPS 신규수용공사","362kV GIS 3CB 신설(7200,7272,7472)","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[310,"부산울산","울산","동울산S/S #2 M.Tr","22~23년 변전협력회사 총액공사","- M.Tr 보통점검 - 2차(6244) GIS 차단기 동작시험 - #2S.Tr 보통점검 - 3차 GIS 보통점검 - 3차 LA 보통점검","2023-06-26 09:00","2023-06-27 18:00","2023-06-26 09:00","2023-06-27 18:00","연속"]
[311,"부산울산","울산","동울산S/S #3 M.Tr","22~23년 변전협력회사 총액공사","- M.Tr 보통점검 - 1차(7372) 차단기 동작시험 - 2차(6344) GIS 보통점검 - 3차 LA 보통점검","2023-06-28 09:00","2023-06-29 18:00","2023-06-28 09:00","2023-06-29 18:00","연속"]
[312,"부산울산","울산","동울산S/S #1 M.Tr","22~23년 변전협력회사 총액공사","- 2차(6244) GIS 보통점검 - #1S.Tr 보통점검 - 3차 GIS 보통점검 - 3차 LA 보통점검","2023-06-30 09:00","2023-06-30 18:00","2023-06-30 09:00","2023-06-30 18:00","연속"]
[313,"부산울산","울산","신온산S/S #3 M.Tr","22~23년 변전협력회사 총액공사","- S-Oil#1T/L GIS 누기보수 관련 안전이격","2023-06-22 09:00","2023-06-24 18:00","2023-06-22 09:00","2023-06-24 18:00","연속"]
[314,"부산울산","울산","울산C/C #2,3ST 주변압기 (CB 7771, 7700)","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-06-26 09:00","2023-06-26 18:00","2023-06-26 09:00","2023-06-26 18:00","연속"]
[315,"부산울산","울산","울산C/C #4ST 주변압기 (CB 7A00, 7A72)","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-06-30 09:00","2023-06-30 18:00","2023-06-30 09:00","2023-06-30 18:00","연속"]
[316,"부산울산","울산","울산C/C #3,4GT 주변압기 (CB 7700, 7772)","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-06-28 09:00","2023-06-28 18:00","2023-06-28 09:00","2023-06-28 18:00","연속"]
[317,"부산울산","울산","울산C/C #7,8GT 주변압기 (CB 7100, 7172)","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-06-23 09:00","2023-06-23 18:00","2023-06-23 09:00","2023-06-23 18:00","연속"]
[318,"부산울산","울산","남울산울산TP#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-06-14 07:00","2023-06-15 18:00","취소","취소","연속"]
[319,"부산울산","울산","북부산울산TP#2 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-06-12 07:00","2023-06-27 18:00","취소","취소","연속"]
[320,"부산울산","울산","울산C/C #1 BUS","울산복합 전담운영 공사","- 모선보호반 이설","2023-06-07 09:00","2023-06-07 23:59","취소","취소","연속"]
[321,"부산울산","울산","울산C/C CB 7700","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-06-27 09:00","2023-06-27 18:00","2023-06-27 09:00","2023-06-27 18:00","연속"]
[322,"경남","직할","신김해북부산#2 T/L","OPGW 금구류 정비 공사","OPGW 금구류 취약개소 정비","2023-06-01 07:00","2023-06-02 18:00","취소","취소","매일"]
[323,"경남","직할","창원삼천포TP#2 T/L","345kV 창원-신고성#2T/L 추락방지장치 설치공사","345kV 창원-신고성#2T/L 추락방지장치 설치","2023-06-12 08:00","2023-06-25 18:00","취소","취소","매일"]
[324,"경남","진주","의령신마산#2 T/L","의령S/S 345kV 의령-신마산#2T/L LA초기점검","의령S/S 345kV 의령-신마산#2T/L LA초기점검","2023-06-14 09:00","2023-06-14 18:00","취소","취소","연속"]
[325,"경남","진주","의령S/S #3 M.Tr","의령S/S #3M.Tr 3차 PT 보통점검","의령S/S #3M.Tr 3차 PT 보통점검, 1,2차 부싱채유 등","2023-06-23 09:00","2023-06-23 18:00","2023-06-23 09:00","2023-06-23 18:00","연속"]
[326,"경남","진주","의령산청양수#2 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 - 345kV 의령-산청양수#2T/L측 수직,수평 추락방지장치 설치 2. 작업구간 - 추락방지장치 : No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2023-06-21 07:00","2023-07-16 18:00","2023-06-21 07:00","2023-07-16 18:00","매일"]
[327,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력등 2개T/L 수평 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : No.1~152","2023-06-16 07:00","2023-06-30 18:00","취소","취소","매일"]
[328,"경남","진주","의령S/S #2 M.Tr","의령S/S #2M.Tr 2차 LA초기점검","의령S/S #2M.Tr 2차 LA초기점검, 1,2차 부싱채유 등","2023-06-15 09:00","2023-06-15 18:00","2023-06-15 09:00","2023-06-15 18:00","연속"]
[329,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력등 2개T/L 수평 추락방지장치 설치공사","1. 작업내용 - 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 - 345kV 의령-하동화력#1T/L측 가공지선 항공장애표시구 설치 2. 작업구간 : - 추락방지장치 : No.1~152 - 항공장애표시구 : No.2,6.7,15,19,61","2023-06-01 07:00","2023-06-15 18:00","취소","취소","매일"]
[330,"경남","진주","의령산청양수#1 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 - 345kV 의령-산청양수#1T/L측 수직,수평 추락방지장치 설치 2.작업구간 - 추락방지장치 : No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2023-06-01 07:00","2023-06-20 18:00","2023-06-01 07:00","2023-06-20 18:00","매일"]
[331,"경남","함안","신마산신김해#1 T/L","OPGW 금구류 정비공사","OPGW 금구류 취약개소 정비","2023-06-03 07:00","2023-06-03 18:00","취소","취소","연속"]
[332,"대전세종충남","천안","신탕정S/S CB 7571","신탕정S/S 7500, 7571 GIS 보통점검","신탕정S/S 7500, 7571 GIS 보통점검","2023-06-09 09:00","2023-06-09 14:00","2023-06-09 09:00","2023-06-09 14:00","연속"]
[333,"대전세종충남","천안","신탕정S/S CB 7500","신탕정S/S 7500, 7571 GIS 보통점검","신탕정S/S 7500, 7571 GIS 보통점검","2023-06-09 14:00","2023-06-09 18:00","2023-06-09 14:00","2023-06-09 18:00","연속"]
[334,"경기북부",null,"동두천C/C #3GT 주변압기 (CB 7500, 7572)","#2호기 계획예방정비","#2호기 계획예방정비","2023-06-05 09:00","2023-06-07 18:00","2023-06-05 09:00","2023-06-07 18:00","연속"]
[335,"경기북부",null,"동두천C/C #2ST 주변압기 (CB 7400, 7472)","#2호기 계획예방정비","#2호기 계획예방정비","2023-06-05 09:00","2023-06-14 18:00","2023-06-05 09:00","2023-06-14 18:00","연속"]
[336,"경기북부",null,"동두천C/C #4GT 주변압기 (CB 7600, 7672)","#2호기 계획예방정비","#2호기 계획예방정비","2023-06-08 09:00","2023-06-10 18:00","2023-06-08 09:00","2023-06-10 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":634,"n_cols":11,"rows_kept":634,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 6월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","화양광장 T/L","2022~2023년 가공송전 협력회사 총액공사","장기사용애자 교체작업","2023-06-19 07:00","2023-06-21 18:00","2023-06-19 07:00","2023-06-21 18:00","연속"]
[2,"서울","성동","군자성수 T/L","2023년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2023-06-15 09:00","2023-06-16 18:00","취소","취소","연속"]
[3,"서울","성동","수유S/S CB 6100","2023년 성동P/O 변전 협력회사 총액공사","154kV GIS 하자점검","2023-06-01 09:30","2023-06-01 17:00","2023-06-01 09:30","2023-06-01 17:00","연속"]
[4,"서울","성동","양주쌍문#2 T/L","2022~2023년 가공송전 협력회사 총액공사","장기사용애자 교체작업 및 레일형 수평추락방지장치 설치","2023-06-14 07:00","2023-06-16 14:00","취소","취소","연속"]
[5,"서울","성동","양주쌍문#1 T/L","2022~2023년 가공송전 협력회사 총액공사","레일형 수평추락방지장치 설치","2023-06-16 14:00","2023-06-16 18:00","취소","취소","연속"]
[6,"서울","성동","용두안암#1 T/L","2023년 성동P/O 변전정비회사 총액공사","154kV GIS 조작시험","2023-06-21 10:00","2023-06-21 14:00","2023-06-21 10:00","2023-06-21 14:00","연속"]
[7,"서울","성동","용두안암#2 T/L","2023년 성동P/O 변전정비회사 총액공사","154kV GIS 조작시험","2023-06-21 14:00","2023-06-21 18:00","2023-06-21 14:00","2023-06-21 18:00","연속"]
[8,"서울","성동","왕십리용두 T/L","2023년 성동P/O 170kV GIS 정밀점검","- 170kV GIS 정밀점검","2023-06-07 09:00","2023-06-09 18:00","2023-06-07 09:00","2023-06-09 18:00","연속"]
[9,"서울","중부","중부당인리#2 T/L","23년 중부 개폐장치 정밀점검","GIS 정밀점검","2023-06-29 10:00","2023-06-30 18:00","2023-06-29 10:00","2023-06-30 18:00","연속"]
[10,"서울","중부","중부당인리#1 T/L","23년 중부 개폐장치 정밀점검","GIS 정밀점검","2023-06-27 10:00","2023-06-28 18:00","2023-06-27 10:00","2023-06-28 18:00","연속"]
[11,"서울","중부","상암등촌#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 상암-등촌T/L No.1(1기) 수평 추락방지시설 설치공사","2023-06-26 07:00","2023-06-26 13:00","2023-06-26 07:00","2023-06-26 13:00","연속"]
[12,"서울","중부","상암등촌#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","- 공사내용 : 상암-등촌T/L No.1(1기) 수평 추락방지시설 설치공사","2023-06-26 13:00","2023-06-26 18:00","2023-06-26 13:00","2023-06-26 18:00","연속"]
[13,"서울","중부","세종로옥인#2 T/L","154kV 세종로옥인#2T/L OF케이블 절연유 채유","154kV 세종로옥인#2T/L OF케이블 절연유 분석 시료 채유","2023-06-07 10:00","2023-06-07 16:00","2023-06-07 10:00","2023-06-07 16:00","연속"]
[14,"서울","중부","양주은평#1 T/L","'23년 중부PO 170kV GIS 정밀점검","170kV GIS 정밀점검","2023-06-19 09:00","2023-06-21 18:00","2023-06-19 09:00","2023-06-21 18:00","연속"]
[15,"서울","중부","양주은평#2 T/L","'23년 중부PO 170kV GIS 정밀점검","170kV GIS 정밀점검","2023-06-22 09:00","2023-06-24 18:00","2023-06-22 09:00","2023-06-24 18:00","연속"]
[16,"서울","중부","중부용산#1 T/L","23년 변전협력회사 총액공사","GIS 보통점검","2023-06-02 10:00","2023-06-02 18:00","2023-06-02 10:00","2023-06-02 18:00","연속"]
[17,"서울","중부","지축현저#1 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","레일형 수평추락방지장치 설치 : 지축현저 N0.4, 4.1 (강관주)","2023-06-22 07:00","2023-06-22 14:00","2023-06-22 07:00","2023-06-22 14:00","연속"]
[18,"서울","중부","지축현저#2 T/L","2022~2023년 서울본부 가공송전협력회사 총액공사","레일형 수평추락방지장치 설치 : 지축현저 N0.4, 4.1 (강관주)","2023-06-22 14:00","2023-06-22 18:00","2023-06-22 14:00","2023-06-22 18:00","연속"]
[19,"서울","직할","운니S/S #1 BUS","'23년 직할 변전협력회사 총액공사","154kV GIS PT 점검","2023-06-05 10:00","2023-06-05 14:00","2023-06-05 10:00","2023-06-05 14:00","연속"]
[20,"서울","직할","운니S/S #2 BUS","'23년 직할 변전협력회사 총액공사","154kV GIS PT 점검","2023-06-05 14:00","2023-06-05 18:00","2023-06-05 14:00","2023-06-05 18:00","연속"]
[21,"남서울","강남","논일역삼#2 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 :#1M.Tr 1차, 논일-역삼#2T/L GIS","2023-06-21 09:00","2023-06-23 18:00","2023-06-21 09:00","2023-06-23 18:00","연속"]
[22,"남서울","강남","논일역삼#1 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 : 논일-역삼#1T/L GIS","2023-06-19 09:00","2023-06-20 18:00","2023-06-19 09:00","2023-06-20 18:00","연속"]
[23,"남서울","강남","동빙고반포#1 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","GIS 조작시험","2023-06-12 09:00","2023-06-12 14:00","2023-06-12 09:00","2023-06-12 14:00","연속"]
[24,"남서울","강남","동빙고반포#2 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","GIS 조작시험","2023-06-12 14:00","2023-06-12 18:00","2023-06-12 14:00","2023-06-12 18:00","연속"]
[25,"남서울","강남","신양재사당#1 T/L","'22-'23년 가공송전 협력회사 총액공사","- 피뢰기설치","2023-06-01 07:00","2023-06-09 17:00","2023-06-01 07:00","2023-06-09 17:00","연속"]
[26,"남서울","강남","신양재신사#3 T/L","23~24년 지중송전설비 위탁정비공사","OF케이블 절연유채유 및 접지선 교체","2023-06-13 20:00","2023-06-23 08:00","2023-06-13 20:00","2023-06-23 08:00","연속"]
[27,"남서울","강남","신양재신사#1 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","-신양재 : GIS 조작시험 -신사 : GIS 조작시험","2023-06-01 09:00","2023-06-01 14:00","2023-06-01 09:00","2023-06-01 14:00","연속"]
[28,"남서울","강남","신양재신사#2 T/L","22-23년도 강남전력지사 변전협력회사 총액공사","-신양재 : GIS 조작시험 -신사 : GIS 조작시험","2023-06-01 14:00","2023-06-01 18:00","2023-06-01 14:00","2023-06-01 18:00","연속"]
[29,"남서울","동서울","강동풍납#2 T/L","2023년 동서울전력 170kV GIS 정밀점검","2023년 동서울전력 170kV GIS 정밀점검 - 대상 : 강동S/S 강동-풍납#2T/L","2023-06-19 09:00","2023-06-20 18:00","2023-06-19 09:00","2023-06-20 18:00","연속"]
[30,"남서울","동서울","강동천호#1 T/L","2023년 동서울전력 170kV GIS 정밀점검","2023년 동서울전력 170kV GIS 정밀점검 - 대상 : 강동S/S 강동-천호#1T/L","2023-06-17 09:00","2023-06-18 18:00","2023-07-01 09:00","2023-07-02 18:00","연속"]
[31,"남서울","동서울","강동풍납#1 T/L","2023년 동서울전력 170kV GIS 정밀점검","2023년 동서울전력 170kV GIS 정밀점검 - 대상 : 강동S/S 강동-풍납#1T/L","2023-06-21 09:00","2023-06-22 18:00","2023-06-21 09:00","2023-06-22 18:00","연속"]
[32,"남서울","동서울","강동천호#2 T/L","2023년 동서울전력 170kV GIS 정밀점검","2023년 동서울전력 170kV GIS 정밀점검 - 대상 : 강동S/S 강동-천호#2T/L","2023-06-24 09:00","2023-06-25 18:00","2023-06-24 09:00","2023-06-25 18:00","연속"]
[33,"남서울","동서울","신양재개포 T/L","154kV 개포-신양재,도곡T/L 지장이설공사","양재대로 구조개선 사업(지하차도 건설)에 따른 전력설비 이설 □ 사업구간 : 154kV 신양재-개포T/L J/B#20 ~ M/H#19 □ 주요공정 - 케이블 철거 : XLPE 2,000㎟, 1C-0.32km(기설전력구+관로) - 케이블 설치 : XLPE 2,000㎟, 1C-0.35km(신설전력구+관로) - 케이블 접속 : 2개소","2023-06-07 07:00","2023-06-30 18:00","2023-06-07 07:00","2023-06-30 18:00","연속"]
[34,"남서울","동서울","동서울S/S 동서울탄천#1T/L CB","동서울S/S 동서울-탄천#1T/L 하자점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-06-13 09:00","2023-06-13 18:00","2023-06-13 09:00","2023-06-13 18:00","연속"]
[35,"남서울","동서울","탄천선릉#2 T/L","선릉S/S 탄천-선릉#2T/L 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-06-10 14:00","2023-06-10 18:00","2023-06-10 14:00","2023-06-10 18:00","연속"]
[36,"남서울","동서울","탄천선릉#1 T/L","선릉S/S 탄천-선릉#1T/L 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-06-10 09:00","2023-06-10 14:00","2023-06-10 09:00","2023-06-10 14:00","연속"]
[37,"남서울","동서울","논현선릉#2 T/L","선릉S/S 논현-선릉#2T/L 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-06-09 09:00","2023-06-09 18:00","2023-06-09 09:00","2023-06-09 18:00","연속"]
[38,"남서울","동서울","신장S/S CB 6100","신장S/S 154kV 모선 통합","신장S/S 154kV 모선 통합 - 사유 : 신장S/S #1,2,3M.Tr 및 1,2차 GIS 보통점검","2023-06-19 09:00","2023-06-23 18:00","2023-06-19 09:00","2023-06-23 18:00","연속"]
[39,"남서울","동서울","동서울신장#2 T/L","154kV 동서울-신장 지중T/L 선종교체공사","(신설)XLPE 2500㎟, 2C-0.3km (철거)XLPE 1200㎟, 2C(D)-0.3km","2023-06-07 09:00","2023-07-07 18:00","2023-06-03 15:00","2023-07-07 18:00","연속"]
[40,"남서울","동서울","동서울신장#2 T/L","154kV 강일S/S 건설관련 GIS 설치공사","- 154kV GIS 2CCT 설치 - 기타 부대공사 1식","2023-06-03 15:00","2023-06-04 15:00","취소","취소","연속"]
[41,"남서울","동서울","탄천대치#1 T/L","영동대로 지하공간 복합개발 지장송전선로 이설공사","154kV 탄천-대치T/L 일부구간 지장이설공사","2023-06-05 09:00","2023-06-30 18:00","2023-06-05 09:00","2023-06-30 18:00","연속"]
[42,"남서울","동서울","탄천대치#2 T/L","영동대로 지하공간 복합개발 지장송전선로 이설공사","154kV 탄천-대치T/L 일부구간 지장이설공사","2023-06-05 09:00","2023-07-21 18:00","2023-06-05 09:00","2023-07-21 18:00","연속"]
[43,"남서울","영등포","광명S/S #2 BUS","광명S/S 154kV 장기사용 GIS 교체공사","5차분(신광명-광명#1T/L GIS) 철거 및 설치 - #2BUS DS 설치, 준공시험","2023-06-12 18:00","2023-06-15 18:00","2023-06-12 18:00","2023-06-15 18:00","연속"]
[44,"남서울","영등포","광명S/S #2 BUS","광명S/S 154kV 장기사용 GIS 교체공사","5차분(신광명-광명#1T/L GIS) 철거 및 설치 - #2BUS DS 설치, 준공시험","2023-06-27 18:00","2023-07-07 18:00","2023-06-27 18:00","2023-07-07 18:00","연속"]
[45,"남서울","영등포","신광명광명#2 T/L","광명S/S 154kV 장기사용 GIS 교체공사","5차분(신광명-구공#1T/L) 철거 및 설치 관련 감압","2023-06-15 18:00","2023-06-21 18:00","취소","취소","연속"]
[46,"남서울","영등포","광명S/S #1 BUS","광명S/S 154kV 장기사용 GIS 교체공사","5차분(신광명-광명#1T/L GIS) 철거 및 설치 - #1BUS 구형BUS 철거, 신형BUS, CB, 인출모선 설치","2023-06-15 18:00","2023-06-27 18:00","2023-06-15 18:00","2023-06-27 18:00","연속"]
[47,"남서울","영등포","신광명광명#2 T/L","광명S/S 154kV 장기사용 GIS 교체공사","5차분(신광명-구공#1T/L) 철거 및 설치 관련 감압","2023-06-12 09:00","2023-06-15 18:00","2023-06-12 09:00","2023-06-21 18:00","연속"]
[48,"남서울","영등포","신광명광명#1 T/L","광명S/S 154kV 장기사용 GIS 교체공사","5차분(신광명-구공#1T/L) 철거 및 설치","2023-06-12 09:00","2023-07-07 18:00","2023-06-12 09:00","2023-07-07 18:00","연속"]
[49,"남서울","영등포","신광명시흥#2 T/L","'23년 가공송전 순시점검 위탁공사","신광명시흥#2 T/L 정밀점검","2023-06-08 09:00","2023-06-09 18:00","2023-06-08 09:00","2023-06-09 18:00","연속"]
[50,"남서울","영등포","신광명시흥#1 T/L","'23년 가공송전 순시점검 위탁공사","신광명시흥#1 T/L 정밀점검","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[51,"남서울","영등포","오류S/S CB 6100","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2023-06-01 09:00","2023-06-01 18:00","2023-06-01 09:00","2023-06-01 18:00","연속"]
[52,"남서울","직할","여의노량진 T/L","154kV 노량진S/S #4M.Tr 증설공사","154kV 노량진S/S #4M.Tr 증설공사 - 170kV GIS 설치(6433) 무부하","2023-06-28 17:00","2023-06-29 17:00","2023-06-28 17:00","2023-06-29 17:00","연속"]
[53,"남서울","직할","신문래노량진 T/L","OF케이블 절연유 채유밸브 설치","OF케이블 절연유 채유밸브 설치(SJ/B#0 등 3개소)","2023-06-03 09:00","2023-06-04 18:00","2023-06-03 09:00","2023-06-04 18:00","연속"]
[54,"남서울","직할","여의노량진 T/L","154kV 노량진S/S #4M.Tr 증설공사","154kV 노량진S/S #4M.Tr 증설공사 - 170kV GIS 설치(6433) 무부하","2023-06-22 17:00","2023-06-23 17:00","2023-06-22 17:00","2023-06-23 17:00","연속"]
[55,"남서울","직할","사당신림 T/L","OF케이블 절연유 채유밸브 설치","OF케이블 절연유 채유밸브 설치(SJ/B#4 등 4개소)","2023-06-12 09:00","2023-06-14 18:00","2023-06-12 09:00","2023-06-14 18:00","연속"]
[56,"인천","부평","신가좌S/S CB 6100"," 신가좌S/S 154kV #60-#65 BUS TIE GIS 보통점검"," 신가좌S/S 154kV #60-#65 BUS TIE GIS 보통점검","2023-06-01 09:00","2023-06-01 18:00","2023-06-01 09:00","2023-06-01 18:00","연속"]
[57,"인천","부평","관교주안 T/L"," 지중송전설비 위탁정비공사 OF케이블 절연유 열화진단"," 지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[58,"인천","직할","인천CC북인천#1 T/L"," 북인천S/S 인천CC북인천#1T/L 조작시험"," 북인천S/S 인천CC북인천#1T/L 조작시험","2023-06-01 09:30","2023-06-01 14:00","2023-06-01 09:30","2023-06-01 14:00","연속"]
[59,"인천","직할","북인천원창 T/L"," 북인천S/S 북인천원창T/L 조작시험"," 북인천S/S 북인천원창T/L 조작시험","2023-06-01 14:00","2023-06-01 18:00","2023-06-07 09:00","2023-06-07 14:00","연속"]
[60,"인천","부평","신가좌S/S CB 6200"," 신가좌S/S 154kV #61-#66 BUS TIE GIS 보통점검"," 신가좌S/S 154kV #61-#66 BUS TIE GIS 보통점검","2023-06-02 09:00","2023-06-02 18:00","2023-06-02 09:00","2023-06-02 18:00","연속"]
[61,"인천","직할","인천CC북인천#2 T/L"," 북인천S/S 인천CC북인천#2T/L 조작시험"," 북인천S/S 인천CC북인천#2T/L 조작시험","2023-06-02 09:30","2023-06-02 18:00","2023-06-01 14:00","2023-06-01 18:00","연속"]
[62,"인천","시흥","시화동시화#1 T/L"," 동시화S/S 154kV 시화동시화#1,2T/L GIS 보통점검"," 동시화S/S 154kV 시화동시화#1,2T/L GIS 보통점검","2023-06-03 09:00","2023-06-03 14:00","취소","취소","연속"]
[63,"인천","부평","주안만수#1 T/L"," 154kV 주안만수#1 T/L GIS 보통점검"," 154kV 주안만수#1 T/L GIS 보통점검","2023-06-03 09:00","2023-06-03 18:00","2023-06-03 09:00","2023-06-03 18:00","연속"]
[64,"인천","직할","신부평고강#1 T/L"," 신부평-고강 #1T/L EBA 비표준형 자기애관 교체공사"," 신부평-고강 #1T/L EBA 비표준형 자기애관 교체공사","2023-06-03 09:00","2023-06-04 18:00","2023-06-03 09:00","2023-06-04 18:00","연속"]
[65,"인천","부평","신경서S/S 청라에너지T/L CB"," 신경서S/S 154kV 청라에너지T/L GIS 보통점검"," 신경서S/S 154kV 청라에너지T/L GIS 보통점검","2023-06-03 09:00","2023-06-03 18:00","취소","취소","연속"]
[66,"인천","직할","부천S/S CB 6100"," 부천S/S 170kV 6100 GIS 보통점검"," 부천S/S 170kV 6100 GIS 보통점검","2023-06-03 09:30","2023-06-03 18:00","2023-06-02 09:00","2023-06-02 18:00","연속"]
[67,"인천","시흥","시화동시화#2 T/L"," 동시화S/S 154kV 시화동시화#1,2T/L GIS 보통점검"," 동시화S/S 154kV 시화동시화#1,2T/L GIS 보통점검","2023-06-03 14:00","2023-06-03 18:00","취소","취소","연속"]
[68,"인천","시흥","서안양소래 T/L","  가공송전 협력회사 총액공사(154kV 서소T/L 추락방지설치)","  가공송전 협력회사 총액공사(154kV 서소T/L 추락방지설치)","2023-06-05 07:00","2023-06-11 18:00","2023-06-22 07:00","2023-06-26 18:00","매일"]
[69,"인천","부평","신가좌S/S SEC CB 60610"," 신가좌S/S 154kV #60-#61 SEC GIS 보통점검"," 신가좌S/S 154kV #60-#61 SEC GIS 보통점검","2023-06-05 09:00","2023-06-05 18:00","취소","취소","연속"]
[70,"인천","시흥","오봉고잔#1 T/L"," 오봉S/S 154kV 오봉고잔#1,2T/L GIS 보통점검"," 오봉S/S 154kV 오봉고잔#1,2T/L GIS 보통점검","2023-06-05 09:00","2023-06-05 14:00","2023-06-05 09:00","2023-06-05 14:00","연속"]
[71,"인천","직할","경서북인천#1 T/L"," 북인천S/S 경서북인천#1T/L 조작시험"," 북인천S/S 경서북인천#1T/L 조작시험","2023-06-05 09:30","2023-06-05 18:00","2023-06-08 09:00","2023-06-08 14:00","연속"]
[72,"인천","부평","영종경서 T/L"," 154kV 을왕S/S 건설공사"," 154kV 을왕S/S 건설공사","2023-06-05 10:00","2023-06-06 10:00","2023-06-05 10:00","2023-06-06 10:00","연속"]
[73,"인천","시흥","오봉고잔#2 T/L"," 오봉S/S 154kV 오봉고잔#1,2T/L GIS 보통점검"," 오봉S/S 154kV 오봉고잔#1,2T/L GIS 보통점검","2023-06-05 14:00","2023-06-05 18:00","2023-06-05 14:00","2023-06-05 18:00","연속"]
[74,"인천","시흥","신시흥도림#2 T/L"," 도림S/S 154kV 신시흥도림#2T/L GIS 보통점검"," 도림S/S 154kV 신시흥도림#2T/L GIS 보통점검","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[75,"인천","부평","신가좌S/S SEC CB 65660"," 신가좌S/S 154kV #65-#66 SEC GIS 보통점검"," 신가좌S/S 154kV #65-#66 SEC GIS 보통점검","2023-06-07 09:00","2023-06-07 18:00","취소","취소","연속"]
[76,"인천","직할","경서북인천#2 T/L"," 북인천S/S 경서북인천#2T/L 조작시험"," 북인천S/S 경서북인천#2T/L 조작시험","2023-06-07 09:30","2023-06-07 18:00","2023-06-08 14:00","2023-06-08 18:00","연속"]
[77,"인천","부평","인천남인천#2 T/L"," 지중송전설비 위탁정비공사 OF케이블 절연유 열화진단"," 지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","2023-06-08 09:00","2023-06-08 18:00","2023-06-08 09:00","2023-06-08 18:00","연속"]
[78,"인천","직할","계양북인천 T/L"," 북인천S/S계양북인천T/L 조작시험"," 북인천S/S계양북인천T/L 조작시험","2023-06-08 09:30","2023-06-08 18:00","2023-06-07 14:00","2023-06-07 18:00","연속"]
[79,"인천","부평","영종경서 T/L"," 154kV 을왕S/S 건설공사"," 154kV 을왕S/S 건설공사","2023-06-08 10:00","2023-06-09 10:00","2023-06-08 10:00","2023-06-09 10:00","연속"]
[80,"인천","직할","신부평임학#1 T/L"," 임학, 부개S/S 154kV GIS 교체공사"," 임학, 부개S/S 154kV GIS 교체공사","2023-06-09 07:30","2023-07-03 18:00","취소","취소","연속"]
[81,"인천","부평","관교만수#2 T/L"," 관교S/S 154kV 관교만수#2 T/L GIS 보통점검"," 관교S/S 154kV 관교만수#2 T/L GIS 보통점검","2023-06-09 09:00","2023-06-09 18:00","2023-06-09 09:00","2023-06-09 18:00","연속"]
[82,"인천","시흥","북시화서시화#3 T/L"," 북시화,서시화S/S 154kV 북시화서시화#3T/L GIS 조작시험"," 북시화,서시화S/S 154kV 북시화서시화#3T/L GIS 조작시험","2023-06-09 09:00","2023-06-09 18:00","2023-06-09 09:00","2023-06-09 18:00","연속"]
[83,"인천","시흥","온수소래 T/L","  가공송전 협력회사 총액공사(154kV 서소T/L 추락방지설치)","  가공송전 협력회사 총액공사(154kV 서소T/L 추락방지설치)","2023-06-10 07:00","2023-06-11 18:00","2023-06-24 07:00","2023-06-25 18:00","매일"]
[84,"인천","직할","신부평고강#1 T/L"," 신부평-고강 #1T/L EBA 비표준형 자기애관 교체공사"," 신부평-고강 #1T/L EBA 비표준형 자기애관 교체공사","2023-06-10 09:00","2023-06-11 18:00","2023-06-10 09:00","2023-06-11 18:00","연속"]
[85,"인천","시흥","동시화서시화 T/L"," 동시화S/S 154kV 동시화서시화T/L GIS 보통점검"," 동시화S/S 154kV 동시화서시화T/L GIS 보통점검","2023-06-10 09:00","2023-06-10 18:00","취소","취소","연속"]
[86,"인천","부평","관교만수#1 T/L"," 154kV 관교만수#1 T/L GIS 보통점검"," 154kV 관교만수#1 T/L GIS 보통점검","2023-06-10 09:00","2023-06-10 18:00","2023-06-10 09:00","2023-06-10 18:00","연속"]
[87,"인천","직할","부개원미#2 T/L"," 원미S/S 부개원미#2T/L 조작시험"," 원미S/S 부개원미#2T/L 조작시험","2023-06-10 09:30","2023-06-10 18:00","2023-06-10 09:30","2023-06-10 18:00","연속"]
[88,"인천","시흥","서서울#2소래 T/L","  가공송전 협력회사 총액공사(154kV 서소T/L 추락방지설치)","  가공송전 협력회사 총액공사(154kV 서소T/L 추락방지설치)","2023-06-12 07:00","2023-06-18 18:00","2023-06-15 07:00","2023-06-21 18:00","매일"]
[89,"인천","부평","남인천학익#2 T/L"," 남인천S/S 154kV 남인천-학익#2T/L GIS 보통점검"," 남인천S/S 154kV 남인천-학익#2T/L GIS 보통점검","2023-06-12 09:00","2023-06-12 18:00","2023-06-12 09:00","2023-06-12 18:00","연속"]
[90,"인천","부평","신현송현#2 T/L"," 송현S/S 154kV 신현-송현#2T/L GIS 보통점검"," 송현S/S 154kV 신현-송현#2T/L GIS 보통점검","2023-06-12 09:00","2023-06-12 18:00","2023-06-12 09:00","2023-06-12 18:00","연속"]
[91,"인천","부평","주안만수#2 T/L"," 154kV 주안-관교등 4개T/L 열경화공법 EBG 보강공사"," 154kV 주안-관교등 4개T/L 열경화공법 EBG 보강공사","2023-06-12 09:00","2023-06-14 18:00","취소","취소","연속"]
[92,"인천","김포","신경서경서#1 T/L"," 경서S/S 170kV 신경서-경서#1T/L GIS 정밀점검"," 경서S/S 170kV 신경서-경서#1T/L GIS 정밀점검","2023-06-12 09:00","2023-06-14 14:00","2023-06-12 09:00","2023-06-14 14:00","연속"]
[93,"인천","직할","갈산부흥#3 T/L"," 부흥S/S 갈산부흥#3T/L 조작시험"," 부흥S/S 갈산부흥#3T/L 조작시험","2023-06-12 09:30","2023-06-12 18:00","2023-06-12 09:30","2023-06-12 18:00","연속"]
[94,"인천","직할","신부평임학#2 T/L"," 임학, 부개S/S 154kV GIS 교체공사"," 임학, 부개S/S 154kV GIS 교체공사","2023-06-12 14:00","2023-06-12 15:00","2023-06-12 14:00","2023-06-12 15:00","연속"]
[95,"인천","시흥","신시흥남동#1 T/L"," 남동S/S 154kV 신시흥남동#1T/L GIS 보통점검"," 남동S/S 154kV 신시흥남동#1T/L GIS 보통점검","2023-06-14 09:00","2023-06-14 18:00","취소","취소","연속"]
[96,"인천","김포","신경서경서#2 T/L"," 경서S/S 170kV 신경서-경서#2T/L GIS 정밀점검"," 경서S/S 170kV 신경서-경서#2T/L GIS 정밀점검","2023-06-14 14:00","2023-06-16 18:00","2023-06-14 14:00","2023-06-16 18:00","연속"]
[97,"인천","시흥","신시흥남동#2 T/L"," 남동S/S 154kV 신시흥남동#2T/L GIS 보통점검"," 남동S/S 154kV 신시흥남동#2T/L GIS 보통점검","2023-06-15 09:00","2023-06-15 18:00","취소","취소","연속"]
[98,"인천","시흥","신시흥S/S CB CB 6300"," 신시흥#2S/S 154kV #62-#67 BUS TIE GIS 조작시험"," 신시흥#2S/S 154kV #62-#67 BUS TIE GIS 조작시험","2023-06-16 09:00","2023-06-16 14:00","2023-06-16 09:00","2023-06-16 14:00","연속"]
[99,"인천","시흥","신시흥S/S CB CB 6400"," 신시흥#2S/S 154kV #63-#68 BUS TIE GIS 조작시험"," 신시흥#2S/S 154kV #63-#68 BUS TIE GIS 조작시험","2023-06-16 14:00","2023-06-16 18:00","2023-06-16 14:00","2023-06-16 18:00","연속"]
[100,"인천","시흥","신광명소래 T/L","  가공송전 협력회사 총액공사(154kV 서소T/L 추락방지설치)","  가공송전 협력회사 총액공사(154kV 서소T/L 추락방지설치)","2023-06-17 07:00","2023-06-18 18:00","2023-06-17 07:00","2023-06-18 18:00","매일"]
[101,"인천","부평","신가좌주안#1 T/L"," 154kV 주안-관교등 4개T/L 열경화공법 EBG 보강공사"," 154kV 주안-관교등 4개T/L 열경화공법 EBG 보강공사","2023-06-17 09:00","2023-06-18 18:00","취소","취소","연속"]
[102,"인천","김포","양촌양곡#1 T/L"," 양곡S/S #5,6M.Tr 증설공사"," 양곡S/S #5,6M.Tr 증설공사","2023-06-18 09:00","2023-06-18 18:00","2023-06-11 09:00","2023-06-11 18:00","연속"]
[103,"인천","부평","인천C/C 현대제철#1T/L CB"," 154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사"," 154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","2023-06-19 08:00","2023-06-25 18:00","취소","취소","연속"]
[104,"인천","부평","송현포스코CC#1 T/L"," 154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사"," 154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","2023-06-19 08:00","2023-06-25 18:00","2023-06-12 09:00","2023-06-16 18:00","연속"]
[105,"인천","부평","인천S/S CB 6100"," 인천S/S 154kV #60-#65 BUS TIE GIS 보통점검"," 인천S/S 154kV #60-#65 BUS TIE GIS 보통점검","2023-06-19 09:00","2023-06-19 18:00","2023-06-19 09:00","2023-06-19 18:00","연속"]
[106,"인천","직할","신부평임학#2 T/L"," 임학, 부개S/S 154kV GIS 교체공사"," 임학, 부개S/S 154kV GIS 교체공사","2023-06-20 09:00","2023-06-21 09:00","취소","취소","연속"]
[107,"인천","부평","인천남인천#1 T/L"," 남인천S/S 154kV 인천남인천#1 T/L 보통점검"," 남인천S/S 154kV 인천남인천#1 T/L 보통점검","2023-06-22 09:00","2023-06-22 18:00","2023-06-15 09:00","2023-06-15 18:00","연속"]
[108,"인천","부평","송현포스코CC#2 T/L"," 154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사"," 154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","2023-06-26 08:00","2023-07-02 18:00","2023-06-19 09:00","2023-06-23 18:00","연속"]
[109,"인천","부평","인천C/C 현대제철#2T/L CB"," 154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사"," 154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","2023-06-26 08:00","2023-07-02 18:00","취소","취소","연속"]
[110,"인천","부평","부개S/S CB 6100"," 부개S/S 154kV 모선보호반 교체공사"," 부개S/S 154kV 모선보호반 교체공사","2023-06-26 09:00","2023-06-30 18:00","2023-06-26 09:00","2023-06-30 18:00","연속"]
[111,"인천","직할","경서북인천#1 T/L"," 북인천S/S #2M.Tr 교체공사"," 북인천S/S #2M.Tr 교체공사","2023-06-27 09:00","2023-06-28 18:00","2023-06-29 09:00","2023-06-30 18:00","연속"]
[112,"인천","직할","신부평임학#2 T/L"," 임학, 부개S/S 154kV GIS 교체공사"," 임학, 부개S/S 154kV GIS 교체공사","2023-06-30 16:00","2023-07-03 12:00","취소","취소","연속"]
[113,"경기북부","고양","양주고양#2 T/L","22~23년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2023-06-19 07:00","2023-06-22 18:00","2023-06-19 07:00","2023-06-22 18:00","연속"]
[114,"경기북부","고양","신덕은금촌#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2023-06-23 07:00","2023-06-23 18:00","2023-06-23 07:00","2023-06-23 18:00","연속"]
[115,"경기북부","고양","양주금촌#2 T/L","22~23년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2023-06-20 07:00","2023-06-30 18:00","2023-06-20 07:00","2023-06-30 18:00","연속"]
[116,"경기북부","고양","양주금촌#2 T/L","22~23년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2023-06-12 07:00","2023-06-12 18:00","2023-06-12 07:00","2023-06-12 18:00","연속"]
[117,"경기북부","고양","문산선유#1 T/L","2023년 고양전력 362, 170kV GIS 보통점검 공사","170kV GIS 점검","2023-06-05 09:00","2023-06-05 18:00","취소","취소","연속"]
[118,"경기북부","고양","문산선유#2 T/L","2023년 고양전력 362, 170kV GIS 보통점검 공사","170kV GIS 점검","2023-06-07 09:00","2023-06-07 18:00","취소","취소","연속"]
[119,"경기북부","고양","신파주원흥#1 T/L","22-23 변전협력회사 총액공사(170kV GIS 보통점검)","170kV GIS 보통점검","2023-06-02 09:00","2023-06-02 18:00","2023-06-02 09:00","2023-06-02 18:00","연속"]
[120,"경기북부","고양","일산지도#1 T/L","2023 가공송전 순시점검 위탁공사","송전설비 정밀점검","2023-06-27 07:30","2023-06-30 18:00","2023-06-27 07:30","2023-06-30 18:00","연속"]
[121,"경기북부","고양","고양일산#1 T/L","2023 가공송전 순시점검 위탁공사","송전설비 정밀점검","2023-06-26 07:30","2023-06-29 18:00","2023-06-26 07:30","2023-06-29 18:00","연속"]
[122,"경기북부","구리","신장덕소#2 T/L","'22~23년 구리전력 가공송전협력 총액공사","추락방지장치(수직,수평) 및 피뢰기 설치공사","2023-06-12 08:00","2023-06-16 18:00","취소","취소","연속"]
[123,"경기북부","구리","미금광장 T/L","'22~23년 구리전력 가공송전협력 총액공사(추락방지, 피뢰기)","추락방지장치(수직,수평) 및 피뢰기 설치공사","2023-06-19 08:00","2023-06-22 18:00","2023-06-12 09:00","2023-06-15 18:00","연속"]
[124,"경기북부","구리","신포천동두천#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사 LA 보통점검","2023-06-28 14:00","2023-06-28 18:00","2023-06-28 14:00","2023-06-28 18:00","연속"]
[125,"경기북부","구리","신포천전곡#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","수평추락방지시설 설치공사(No.6~40,46)","2023-06-22 07:30","2023-06-27 18:00","2023-06-22 07:30","2023-06-27 18:00","연속"]
[126,"경기북부","구리","신포천덕계#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","신포천-전곡#1T/L 수평추락방지시설 설치공사(No.6~7)_병가구간","2023-06-22 07:30","2023-06-22 18:00","2023-06-22 07:30","2023-06-22 18:00","연속"]
[127,"경기북부","구리","신포천전곡#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","피뢰기설치공사(No.6~46)","2023-06-02 07:30","2023-06-09 18:00","2023-06-02 07:30","2023-06-09 18:00","연속"]
[128,"경기북부","구리","신포천덕계#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","154kV 신포천-전곡#2T/L No.6~7 피뢰기설치_병가구간","2023-06-02 07:30","2023-06-02 18:00","2023-06-02 07:30","2023-06-02 18:00","연속"]
[129,"경기북부","구리","신포천포천#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사 LA 보통점검","2023-06-29 14:00","2023-06-29 18:00","2023-06-29 14:00","2023-06-29 18:00","연속"]
[130,"경기북부","구리","신포천동두천#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사 LA 보통점검","2023-06-28 09:00","2023-06-28 14:00","2023-06-28 09:00","2023-06-28 14:00","연속"]
[131,"경기북부","구리","신포천포천#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사 LA 보통점검","2023-06-29 09:00","2023-06-29 14:00","2023-06-29 09:00","2023-06-29 14:00","연속"]
[132,"경기북부","구리","덕소진건#2 T/L","'22~23년 구리 가공송전협력 총액공사(추락 수평와이어)","추락방지장치(수평) 설치공사 / 11기","2023-06-01 08:00","2023-06-01 18:00","2023-06-26 08:00","2023-06-26 18:00","연속"]
[133,"경기북부","구리","청평HP의암HP T/L","구리전력 추락방지장치 설치공사(별도발주)","추락방지장치(수직,수평) 설치공사 / 항공구 교체공사","2023-06-07 08:00","2023-06-09 18:00","2023-06-26 08:00","2023-06-28 18:00","연속"]
[134,"경기북부","구리","청평H/P #4 M.TR 2차 CB","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사 차단기 보통점검","2023-06-13 09:00","2023-06-13 18:00","2023-06-13 09:00","2023-06-13 18:00","연속"]
[135,"경기북부","구리","청평P/P CB 6100","'22-'23년 구리전력지사 변전협력회사 총액공사","장기사용 배전반 교체공사 - 청평P/P 154kV 모선보호반 교체","2023-06-12 09:00","2023-06-16 18:00","2023-06-12 09:00","2023-06-16 18:00","연속"]
[136,"경기북부","구리","포천운천#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","병가선로(운천전곡#1T/L No.2~12 피뢰기설치공사)","2023-06-20 07:30","2023-06-21 18:00","2023-06-20 07:30","2023-06-21 18:00","연속"]
[137,"경기북부","직할","신의정부송우#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 신의정부-송우T/L No.1~4","2023-06-19 07:00","2023-06-19 18:00","2023-06-19 07:00","2023-06-19 18:00","연속"]
[138,"경기북부","직할","신의정부내촌#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 신의정부-내촌T/L No.5,7,9~41","2023-06-12 07:00","2023-06-20 18:00","2023-06-12 07:00","2023-06-20 18:00","연속"]
[139,"경기북부","직할","양주금촌#2 T/L","양주HVDC 154kV 및 25.8kV GIS 설치공사","#62-67BUS 무부하 가압용 휴전 신청","2023-06-13 15:00","2023-06-17 15:00","2023-06-13 15:00","2023-06-17 15:00","연속"]
[140,"경기북부","직할","양주녹양#1 T/L","22~23년 고양전력 가공송전협력회사 총액공사","성능저하 지지애자 교체","2023-06-21 07:00","2023-06-21 12:00","2023-06-15 07:00","2023-06-15 12:00","연속"]
[141,"경기북부","직할","양주쌍문#2 T/L","2023 가공송전 순시점검 위탁공사","송전설비 정밀점검","2023-06-19 07:30","2023-06-23 18:00","2023-06-12 07:30","2023-06-16 18:00","연속"]
[142,"경기북부","직할","양주쌍문#1 T/L","2023 가공송전 순시점검 위탁공사","송전설비 정밀점검","2023-06-12 07:30","2023-06-16 18:00","2023-06-19 07:30","2023-06-23 18:00","연속"]
[143,"경기북부","직할","운천전곡#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","154kV 운천-전곡#2T/L No.1~76 수평추락방지시설 설치","2023-06-26 07:30","2023-06-30 18:00","2023-06-26 07:30","2023-06-30 18:00","연속"]
[144,"경기북부","직할","양주S/S #62 BUS","양주 HVDC 용 170kV GIS 설치공사"," 170kV GIS 2CCT 설치 ","2023-06-12 09:00","2023-06-14 15:00","2023-06-12 09:00","2023-06-14 15:00","연속"]
[145,"경기북부","직할","양주S/S #67 BUS","양주 HVDC 용 170kV GIS 설치공사"," 170kV GIS 2CCT 설치 ","2023-06-14 15:00","2023-06-17 15:00","2023-06-14 15:00","2023-06-17 15:00","연속"]
[146,"경기북부","직할","운천전곡#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","154kV 운천-전곡#1T/L No.1~76 피뢰기설치","2023-06-08 07:30","2023-06-21 18:00","2023-06-08 07:30","2023-06-21 18:00","연속"]
[147,"경기","군포","서서울산본#1 T/L","서서울S/S 서서울-산본#1T/L GIS 보통점검","서서울S/S 서서울-산본#1T/L GIS 보통점검","2023-06-12 09:00","2023-06-12 18:00","2023-06-12 09:00","2023-06-12 18:00","연속"]
[148,"경기","군포","신안산성포#3 T/L","신안산S/S 154kV 신안산-성포#3T/L GIS 정밀점검","신안산S/S 154kV 신안산-성포#3T/L GIS 정밀점검","2023-06-07 09:00","2023-06-09 18:00","2023-06-07 09:00","2023-06-09 18:00","연속"]
[149,"경기","군포","산본안양#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 10기","2023-06-27 07:00","2023-06-28 17:00","2023-06-27 07:00","2023-06-28 17:00","연속"]
[150,"경기","군포","산본안양#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 10기","2023-06-29 07:00","2023-06-30 17:00","2023-06-29 07:00","2023-06-30 17:00","연속"]
[151,"경기","군포","서서울#2일동#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 24기","2023-06-01 07:00","2023-06-09 18:00","2023-06-01 07:00","2023-06-09 18:00","연속"]
[152,"경기","군포","서서울#2일동#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 24기","2023-06-12 07:00","2023-06-17 18:00","2023-06-12 07:00","2023-06-17 18:00","연속"]
[153,"경기","군포","수촌조암#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 11기","2023-06-24 07:00","2023-06-25 17:00","2023-06-24 07:00","2023-06-25 17:00","연속"]
[154,"경기","군포","조암구문천#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 6기","2023-06-21 07:00","2023-06-23 17:00","2023-06-21 07:00","2023-06-23 17:00","연속"]
[155,"경기","군포","수촌조암#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 11기","2023-06-21 07:00","2023-06-23 17:00","2023-06-21 07:00","2023-06-23 17:00","연속"]
[156,"경기","군포","조암구문천#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 6기","2023-06-24 07:00","2023-06-25 17:00","2023-06-24 07:00","2023-06-25 17:00","연속"]
[157,"경기","군포","장덕마도 T/L","장덕S/S 장덕-마도T/L 이설작업","장덕S/S 장덕-마도T/L 이설작업 및 OPGW 증설공사","2023-06-12 09:00","2023-06-19 13:00","취소","취소","연속"]
[158,"경기","군포","화성마도 T/L","장덕S/S 화성-마도T/L 이설작업","장덕S/S 장덕-마도T/L 이설작업 및 OPGW 증설공사","2023-06-19 09:00","2023-07-05 18:00","취소","취소","연속"]
[159,"경기","군포","화성수촌#1 T/L","154kV 화성-장덕T/L OPGW 증설공사","154kV 화성-장덕T/L OPGW 증설공사","2023-06-24 09:00","2023-06-26 18:00","취소","취소","연속"]
[160,"경기","군포","화성발안#1 T/L","154kV 화성-장덕T/L OPGW 증설공사","154kV 화성-장덕T/L OPGW 증설공사","2023-06-24 09:00","2023-06-26 18:00","취소","취소","연속"]
[161,"경기","군포","화성장덕 T/L","154kV 화성-장덕T/L OPGW 증설공사","154kV 화성-장덕T/L OPGW 증설공사","2023-06-24 09:00","2023-06-26 18:00","취소","취소","연속"]
[162,"경기","동부","곤지암S/S SEC CB 60610","23년 동부 변전협력 총액공사","곤지암:60-65 모선보호반대체(~22) 6100, 60-61, 65-66","2023-06-19 09:00","2023-06-22 18:00","2023-06-19 09:00","2023-06-22 18:00","연속"]
[163,"경기","동부","곤지암S/S CB 6100","23년 동부 변전협력 총액공사","곤지암:60-65 모선보호반대체(~22) 6100, 60-61, 65-66","2023-06-19 09:00","2023-06-22 18:00","2023-06-19 09:00","2023-06-22 18:00","연속"]
[164,"경기","동부","곤지암S/S SEC CB 65660","23년 동부 변전협력 총액공사","곤지암:60-65 모선보호반대체(~22) 6100, 60-61, 65-66","2023-06-19 09:00","2023-06-22 18:00","2023-06-19 09:00","2023-06-22 18:00","연속"]
[165,"경기","동부","곤지암S/S #60 BUS","23년 동부 170kV GIS 정밀점검","곤지암:곤지암-용문#2T/L(정밀)","2023-06-01 09:00","2023-06-02 13:00","2023-06-01 09:00","2023-06-02 13:00","연속"]
[166,"경기","동부","곤지암S/S #65 BUS","23년 동부 170kV GIS 정밀점검","곤지암:곤지암-용문#2T/L(정밀)","2023-06-02 13:00","2023-06-03 18:00","2023-06-02 13:00","2023-06-03 18:00","연속"]
[167,"경기","동부","곤지암S/S #66 BUS","23년 동부 170kV GIS 정밀점검","곤지암:#62 M.Tr 1차 6233(정밀)","2023-06-08 13:00","2023-06-09 18:00","2023-06-08 13:00","2023-06-09 18:00","연속"]
[168,"경기","동부","곤지암S/S #61 BUS","23년 동부 170kV GIS 정밀점검","곤지암:#62 M.Tr 1차 6233(정밀)","2023-06-07 09:00","2023-06-08 13:00","2023-06-07 09:00","2023-06-08 13:00","연속"]
[169,"경기","동부","동판교S/S 판교열병합#2T/L CB","23년 동부 변전협력 총액공사","동판교:판교열병합#2T/L(보통) 순간압력상승계 설치","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[170,"경기","동부","동판교S/S 판교열병합#2T/L CB","23년 동부 변전협력총액공사","동판교:판교열병합#2T/L(보통) 순간압력상승계 설치","2023-06-02 09:30","2023-06-02 18:00","2023-06-02 09:30","2023-06-02 18:00","연속"]
[171,"경기","동부","분당S/S SEC CB 60610","23년 동부 변전협력총액공사","분당:60-61(보통,전자변교체)","2023-06-19 09:30","2023-06-19 18:00","2023-06-19 09:30","2023-06-19 18:00","연속"]
[172,"경기","동부","성현산성#2 T/L","성현S/S 장기사용 154kV GIS 교체공사","성현S/S 장기사용 154kV GIS 교체공사(1차) - 상체크 산성-성현#3, 성현-분당#2, 야탑-성현#1T/L, #4M.Tr 1차 대체 60-61,65-66 B/S, 6200 B/T, 61-66 PT 설치","2023-06-16 09:00","2023-06-18 18:00","2023-06-15 09:00","2023-06-17 18:00","연속"]
[173,"경기","동부","야탑성현#2 T/L","성현S/S 장기사용 154kV GIS 교체공사(2차)","성현S/S 장기사용 154kV GIS 교체공사(2차) 야탑-성현#1T/L대체","2023-06-19 09:00","2023-07-09 18:00","2023-06-19 09:00","2023-07-09 18:00","연속"]
[174,"경기","동부","성현산성#2 T/L","성현S/S 장기사용 154kV GIS 교체공사","성현S/S 장기사용 154kV GIS 교체공사(1차) - 무부하가압 산성-성현#3, 성현-분당#2, 야탑-성현#1T/L, #4M.Tr 1차 대체 60-61,65-66 B/S, 6200 B/T, 61-66 PT 설치","2023-06-01 09:00","2023-06-03 18:00","2023-06-10 09:00","2023-06-12 18:00","연속"]
[175,"경기","동부","이천율현#2 T/L","23년 동부 변전협력 총액공사","이천:이천-율현#2T/L(보통) 순간압력상승계 설치 율현:이천-율현#2T/L(보통) 순간압력상승계 설치","2023-06-16 09:30","2023-06-16 18:00","2023-06-16 09:30","2023-06-16 18:00","연속"]
[176,"경기","동부","이천율현#1 T/L","23년 동부 변전협력 총액공사","이천:이천-율현#1T/L(보통) 율현:이천-율현#1T/L(보통) 순간압력상승계 설치","2023-06-09 09:30","2023-06-09 18:00","2023-06-09 09:30","2023-06-09 18:00","연속"]
[177,"경기","동부","초월S/S CB 6100","23년 동부 변전협력 총액공사","초월:6100(2DS 누기보수) (~15)","2023-06-14 09:30","2023-06-15 18:00","2023-06-14 09:30","2023-06-15 18:00","연속"]
[178,"경기","동부","초월성현#1 T/L","초월SS 5M.Tr 증설공사","초월:#5M.Tr 증설관련 무부하선로","2023-06-10 09:00","2023-06-11 18:00","2023-06-10 09:00","2023-06-11 18:00","연속"]
[179,"경기","성남","신수원화성열병#2 T/L","23년 성남전력지사 변전협력회사 총액공사","- T/L 보호반 대체 - GIS 조작시험","2023-06-12 09:00","2023-06-16 18:00","2023-06-12 09:00","2023-06-16 18:00","연속"]
[180,"경기","성남","신수원북동탄#2 T/L","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-06-02 14:00","2023-06-02 18:00","2023-06-02 14:00","2023-06-02 18:00","연속"]
[181,"경기","성남","신수원북동탄#1 T/L","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-06-02 09:00","2023-06-02 14:00","2023-06-02 09:00","2023-06-02 14:00","연속"]
[182,"경기","직할","동수원우만#2 T/L","22-23 경기본부 직할 변전협력회사 총액공사","동수원S/S 동수원-우만#2T/L GIS 보통점검 우만S/S 동수원-우만#2T/L GIS 보통점검","2023-06-12 18:00","2023-06-13 18:00","2023-06-12 18:00","2023-06-13 18:00","연속"]
[183,"경기","직할","동수원우만#1 T/L","22-23 경기본부 직할 변전협력회사 총액공사","동수원S/S 동수원-우만#1T/L GIS 보통점검 우만S/S 동수원-우만#1T/L GIS 보통점검","2023-06-12 09:00","2023-06-12 18:00","2023-06-12 09:00","2023-06-12 18:00","연속"]
[184,"경기","직할","과천동안양#2 T/L","2023년 가공송전 순시점검 위탁공사","안전이격확보(의왕동안양TL 정밀점검)","2023-06-21 09:00","2023-06-21 18:00","2023-06-21 09:00","2023-06-21 18:00","연속"]
[185,"경기","직할","서수원율전#1 T/L","154kV 서수원S/S #5M.Tr용 GIS 증설공사","-#2BUS 무부하 가압선로","2023-06-15 09:00","2023-06-16 18:00","2023-06-15 09:00","2023-06-16 18:00","연속"]
[186,"경기","직할","서수원율전#1 T/L","154kV 서수원S/S #5M.Tr용 GIS 증설공사","-#1BUS 무부하 가압선로","2023-06-07 09:00","2023-06-08 14:00","2023-06-07 09:00","2023-06-08 14:00","연속"]
[187,"경기","직할","율전의왕#1 T/L","2023년 가공송전 순시점검 위탁공사","안전이격확보(의왕동안양#2T/L 정밀점검)","2023-06-22 09:00","2023-06-22 18:00","2023-06-22 09:00","2023-06-22 18:00","연속"]
[188,"경기","직할","율전의왕#2 T/L","2023년 가공송전 순시점검 위탁공사","안전이격확보(의왕동안양T/L 정밀점검)","2023-06-19 09:00","2023-06-19 18:00","2023-06-19 09:00","2023-06-19 18:00","연속"]
[189,"경기","직할","의왕동안양#2 T/L","2023년 가공송전 순시점검 위탁공사","154kV 의왕동안양#1T/L 정밀점검","2023-06-22 09:00","2023-06-26 18:00","2023-06-22 09:00","2023-06-26 18:00","연속"]
[190,"경기","직할","의왕동안양#1 T/L","2023년 가공송전 순시점검 위탁공사","154kV 의왕동안양#1T/L 정밀점검","2023-06-19 09:00","2023-06-21 18:00","2023-06-19 09:00","2023-06-21 18:00","연속"]
[191,"경기","직할","이의S/S #2 BUS","2023년 직할 154kV GIS 정밀점검공사","이의S/S 신봉-이의#2T/L GIS 정밀점검 - 무부하가압","2023-06-19 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[192,"경기","직할","이의S/S #2 BUS","2023년 직할 154kV GIS 정밀점검공사","이의S/S 이의-열병합#2T/L GIS 정밀점검 - 무부하가압","2023-06-06 09:00","2023-06-07 18:00","2023-06-06 09:00","2023-06-07 18:00","연속"]
[193,"경기","직할","이의S/S #2 BUS","2023년 직할 154kV GIS 정밀점검공사","이의S/S 이의-열병합#1T/L GIS 정밀점검 - 무부하가압","2023-06-14 09:00","2023-06-15 18:00","2023-06-14 09:00","2023-06-15 18:00","연속"]
[194,"경기","직할","이의광교열병합#1 T/L","2023년 직할 154kV GIS 정밀점검공사","이의S/S 이의-열병합#1T/L GIS 정밀점검","2023-06-07 09:00","2023-06-15 09:00","2023-06-07 09:00","2023-06-15 09:00","연속"]
[195,"경기","직할","신봉이의#1 T/L","2023년 직할 154kV GIS 정밀점검공사","이의S/S 신봉-이의#1T/L GIS 정밀점검","2023-06-08 09:00","2023-06-10 18:00","2023-06-08 09:00","2023-06-10 18:00","연속"]
[196,"경기","직할","이의S/S #2 BUS","2023년 직할 154kV GIS 정밀점검공사","이의S/S 신봉-이의#1T/L GIS 정밀점검 - 무부하가압","2023-06-09 09:00","2023-06-10 18:00","2023-06-09 09:00","2023-06-10 18:00","연속"]
[197,"경기","직할","안양평촌#1 T/L","22-23 경기본부 직할 변전협력회사 총액공사","평촌S/S 안양-평촌#1T/L GIS 조작시험","2023-06-09 09:00","2023-06-09 14:00","2023-06-09 09:00","2023-06-09 14:00","연속"]
[198,"경기","직할","안양평촌#2 T/L","22-23 경기본부 직할 변전협력회사 총액공사","평촌S/S 안양-평촌#2T/L GIS 보통점검","2023-06-09 14:00","2023-06-09 18:00","2023-06-09 14:00","2023-06-09 18:00","연속"]
[199,"경기","직할","화성수촌#2 T/L","345kV 아산-화성#1 T/L 이도조정(4회선병가)","345kV 아산-화성#1 T/L 이도조정 : 132~136호 345kV 아산-화성#1 T/L 136호 154kV 화성-수촌#2 T/L No.11 병가","2023-06-03 07:00","2023-06-03 18:00","2023-06-03 07:00","2023-06-03 18:00","연속"]
[200,"경기","직할","화성S/S #65 BUS","화성S/S 345kV GIS 용량대체공사","73Bay 무부하가압(7300, 7372 CB) / 2차측 앵글측정","2023-06-18 07:00","2023-06-18 08:00","2023-06-18 07:00","2023-06-18 08:00","연속"]
[201,"경기","직할","화성S/S #61 BUS","2023년 직할 154kV GIS 정밀점검공사","화성S/S 154kV #64Sh.C GIS 정밀점검 - 정밀점검 후 무부하가압","2023-06-25 11:00","2023-06-25 16:00","2023-06-25 11:00","2023-06-25 16:00","연속"]
[202,"경기","평택","서안성S/S #1 EM.Tr CB","23년 평택전력지사 변전협력회사 총액공사","서안성S/S #1EM.Tr 변압기 보통점검, 1,2,차 GIS 보통점검, 세니온제 보호반 성능개선","2023-06-21 09:00","2023-06-22 18:00","2023-06-21 09:00","2023-06-22 18:00","연속"]
[203,"경기","평택","송탄소사벌 T/L","2022-23 평택전력 가공송전 협력회사 총액공사","점퍼지지 설치 작업대상 : 2회선 No.6, 6.1","2023-06-12 07:00","2023-06-13 18:00","취소","취소","연속"]
[204,"경기","평택","송탄안성 T/L","154kV 송탄안성T/L 정밀점검(구간 1~56호)","154kV 송탄안성T/L 정밀점검(구간 1~56호)","2023-06-14 09:00","2023-06-17 18:00","취소","취소","연속"]
[205,"경기","평택","소사벌안성 T/L","154kV 소사벌안성T/L 정밀점검(구간 15~56호)","154kV 소사벌안성T/L 정밀점검(구간 15~56호)","2023-06-07 09:00","2023-06-09 18:00","취소","취소","연속"]
[206,"경기","평택","서운삼죽 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치","2023-06-12 09:00","2023-06-22 18:00","2023-06-12 09:00","2023-06-22 18:00","매일"]
[207,"경기","평택","원정평택TP#1 T/L","2023년 평택전력지사 170kV GIS 정밀점검공사","원정S/S 원정-평택TP#1T/L GIS 정밀점검","2023-06-01 09:00","2023-06-02 18:00","취소","취소","연속"]
[208,"경기","평택","원정평택TP#2 T/L","2023년 평택전력지사 170kV GIS 정밀점검공사","원정S/S 원정-평택TP#2T/L GIS 정밀점검","2023-06-05 09:00","2023-06-06 18:00","취소","취소","연속"]
[209,"경기","평택","원정만호#1 T/L","2023년 평택전력지사 170kV GIS 정밀점검공사","원정S/S 6100 BUSTIE 무부하가압용","2023-06-08 14:00","2023-06-08 18:00","취소","취소","연속"]
[210,"경기","평택","평택추팔#1 T/L","23년 평택전력지사 변전협력회사 총액공사","평택S/S 평택-추팔#1T/L GCB 조작시험, PT&LA 보통점검","2023-06-22 09:00","2023-06-22 18:00","2023-06-22 09:00","2023-06-22 18:00","연속"]
[211,"경기","평택","평택추팔#2 T/L","23년 평택전력지사 변전협력회사 총액공사","평택S/S 평택-추팔#2T/L GCB 조작시험, LA 보통점검","2023-06-23 09:00","2023-06-23 18:00","2023-06-23 09:00","2023-06-23 18:00","연속"]
[212,"강원","강릉","속초간성#1 T/L","2022~2023년 강릉전력지사 가공송전협력회사 총액공사","○ 전선접속개소 해소공사(154kV 간성T/L No.40~42)","2023-06-01 07:00","2023-06-01 18:00","취소","취소","연속"]
[213,"강원","강릉","북평영동TP#2 T/L","영동화력S/Y 170kV 장기사용 GIS 대체공사","영동TP 154kV 북평-영동TP #2T/L 6396 ES 조작기 교체, 상부 BUS ES 내부 동작시험, 진공, Gas 주입","2023-06-01 08:00","2023-06-02 18:00","2023-06-01 08:00","2023-06-02 18:00","연속"]
[214,"강원","직할","춘천북춘천#2 T/L","2022~2023년 강원직할 가공송전협력회사 총액공사","피뢰기 설치","2023-06-01 08:00","2023-06-09 18:00","2023-06-01 08:00","2023-06-09 18:00","매일"]
[215,"강원","직할","화천화천HP#2 T/L","2023년 가공송전 순시점검 위탁공사","154kV 철원화천 T/L 정밀점검","2023-06-01 08:00","2023-06-02 18:00","2023-06-01 08:00","2023-06-02 18:00","연속"]
[216,"강원","강릉","영동T/P #1 BUS","강릉전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 (시험가압) ","2023-06-02 09:00","2023-06-02 18:00","2023-06-02 09:00","2023-06-02 18:00","연속"]
[217,"강원","강릉","속초간성#2 T/L","2022~2023년 강릉전력지사 가공송전협력회사 총액공사","○ 전선접속개소 해소공사(154kV 간성T/L No.40~42)","2023-06-02 07:00","2023-06-02 18:00","취소","취소","연속"]
[218,"강원","원주","북원주횡성#2 T/L","'22~23년 추락방지시설 설치공사","- 와이어형 추락방지장치 설치","2023-06-03 07:00","2023-06-05 18:00","2023-06-03 07:00","2023-06-05 18:00","매일"]
[219,"강원","원주","횡성홍천#1 T/L","'22~23년 추락방지시설 설치공사","- 와이어형 추락방지장치 설치","2023-06-03 07:00","2023-06-05 18:00","2023-06-03 07:00","2023-06-05 18:00","매일"]
[220,"강원","원주","신제천남원주#1 T/L","22~23년 원주전력지사 가공송전협력회사 총액공사 "," 154kV 신제천-남원주T/L 불량애자교체","2023-06-03 07:00","2023-06-04 18:00","2023-06-03 07:00","2023-06-04 18:00","매일"]
[221,"강원","원주","신제천남원주#2 T/L","22~23년 원주전력지사 가공송전협력회사 총액공사 "," 154kV 신제천-남원주T/L 불량애자교체","2023-06-10 07:00","2023-06-11 18:00","2023-06-10 07:00","2023-06-11 18:00","매일"]
[222,"강원","강릉","강릉북강릉#2 T/L","23년 가공송전 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 강릉-북강릉#2T/L No.37~45","2023-06-05 08:00","2023-06-05 18:00","2023-06-05 08:00","2023-06-05 18:00","연속"]
[223,"강원","강릉","북강릉주문진#1 T/L","23년 가공송전 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 북강릉-주문진#1T/L No.북강릉S/S ~ 주문진SA","2023-06-05 08:00","2023-06-09 18:00","2023-06-05 08:00","2023-06-09 18:00","매일"]
[224,"강원","원주","횡성홍천#2 T/L","'22~23년 추락방지시설 설치공사","- 와이어형 추락방지장치 설치","2023-06-06 07:00","2023-06-06 18:00","2023-06-06 07:00","2023-06-06 18:00","연속"]
[225,"강원","원주","북원주횡성#1 T/L","'22~23년 추락방지시설 설치공사","- 와이어형 추락방지장치 설치","2023-06-06 07:00","2023-06-06 18:00","2023-06-06 07:00","2023-06-06 18:00","연속"]
[226,"강원","원주","상남인제#1 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 양구 T/L 철탑 추락방지장치 설치","2023-06-07 09:00","2023-06-09 18:00","2023-06-07 09:00","2023-06-09 18:00","매일"]
[227,"강원","직할","인제양구#1 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 양구 T/L 철탑 추락방지장치 설치","2023-06-07 09:00","2023-06-23 18:00","2023-06-07 09:00","2023-06-23 18:00","매일"]
[228,"강원","강릉","동해영동TP T/L","영동화력S/Y 170kV 장기사용 GIS 대체공사","영동TP 154kV 6383 GIS ~ 탈황설비용 M.Tr 전력케이블 설치, CHD 해체, 도체조립, CHD 설치, 진공, Gas 주입","2023-06-08 08:00","2023-06-14 18:00","2023-06-08 08:00","2023-06-14 18:00","매일"]
[229,"강원","강릉","강릉영동TP T/L","영동화력S/Y 170kV 장기사용 GIS 대체공사","영동TP 154kV 6383 GIS ~ 탈황설비용 M.Tr 전력케이블 설치, CHD 해체, 도체조립, CHD 설치, 진공, Gas 주입","2023-06-08 08:00","2023-06-14 18:00","2023-06-08 08:00","2023-06-14 18:00","매일"]
[230,"강원","원주","북원주횡성#1 T/L","'22~23년 추락방지시설 설치공사","- 와이어형 추락방지장치 설치","2023-06-10 07:00","2023-06-11 18:00","2023-06-10 07:00","2023-06-11 18:00","매일"]
[231,"강원","원주","횡성홍천#2 T/L","'22~23년 추락방지시설 설치공사","- 와이어형 추락방지장치 설치","2023-06-10 07:00","2023-06-11 18:00","2023-06-10 07:00","2023-06-11 18:00","매일"]
[232,"강원","강릉","북강릉주문진#2 T/L","23년 가공송전 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 북강릉-주문진#2T/L No.북강릉S/S ~ 주문진SA","2023-06-12 08:00","2023-06-16 18:00","2023-06-12 08:00","2023-06-16 18:00","매일"]
[233,"강원","강릉","강릉북강릉#1 T/L","23년 가공송전 순시점검 위탁공사","○ 철탑정밀점검 : 154kV 강릉-북강릉#1T/L No.37~45","2023-06-12 08:00","2023-06-12 18:00","2023-06-12 08:00","2023-06-12 18:00","연속"]
[234,"강원","직할","화천화천HP#1 T/L","2022~2023년 강원직할 가공송전협력회사 총액공사","추락방지장치 설치","2023-06-12 08:00","2023-06-23 18:00","2023-06-12 08:00","2023-06-23 18:00","연속"]
[235,"강원","동해","이원동해TP T/L","2023년 154kV 이원변전소 외장재 교체공사","외장재 교체공사 시행","2023-06-12 09:00","2023-06-18 18:00","2023-06-03 109:00","2023-06-09 18:00","연속"]
[236,"강원","태백","태백고한 T/L","2023년 태백전력지사 변전협력회사 총액공사","154kV 태백-고한T/L 보호반 교체","2023-06-12 09:00","2023-06-14 18:00","취소","취소","연속"]
[237,"강원","강릉","강릉횡계#2 T/L","2023년 강릉전력 변전협력회사 총액공사","장기미동작 차단기 조작시험","2023-06-12 13:00","2023-06-12 18:00","2023-06-12 13:00","2023-06-12 18:00","연속"]
[238,"강원","강릉","횡계평창 T/L","2023년 강릉전력 변전협력회사 총액공사","장기미동작 차단기 조작시험","2023-06-16 10:00","2023-06-16 18:00","2023-06-16 10:00","2023-06-16 18:00","연속"]
[239,"강원","강릉","영동T/P #1 BUS","영동화력S/Y 170kV 장기사용 GIS 대체공사","영동TP 154kV 6383 GIS ~ 탈황설비용 M.Tr 전력케이블 시험가압","2023-06-19 09:00","2023-06-25 18:00","2023-06-19 09:00","2023-06-25 18:00","연속"]
[240,"강원","동해","이원도계 T/L","2023년 154kV 이원변전소 외장재 교체공사","외장재 교체공사 시행","2023-06-19 09:00","2023-06-25 18:00","취소","취소","연속"]
[241,"강원","원주","신제천남원주#2 T/L","2023년 원주전력지사 154kV GIS 정밀점검","GIS 정밀점검","2023-06-22 09:00","2023-06-24 18:00","2023-06-22 09:00","2023-06-24 18:00","연속"]
[242,"강원","직할","화천화천HP#2 T/L","2022~2023년 강원직할 가공송전협력회사 총액공사","추락방지장치 설치","2023-06-26 08:00","2023-07-03 18:00","2023-06-26 08:00","2023-07-03 18:00","연속"]
[243,"강원","동해","도계태백 T/L","22~23 동해전력지사 변전정비 협력회사 공사","1. GIS 보통점검 2. LA 대체","2023-06-26 09:00","2023-06-26 18:00","2023-06-15 09:00","2023-06-15 18:00","연속"]
[244,"강원","동해","이원태백 T/L","2023년 154kV 이원변전소 외장재 교체공사","외장재 교체공사 시행","2023-06-26 09:00","2023-07-05 18:00","2023-06-25 09:00","2023-06-28 18:00","연속"]
[245,"강원","태백","영월영월CC T/L","22-23년 태백전력지사 변전협력회사 총액공사","영월S/S 154kV 영월-영월CC T/L GIS 조작시험","2023-06-27 10:00","2023-06-27 18:00","2023-06-27 10:00","2023-06-27 18:00","연속"]
[246,"강원","동해","이원도계 T/L","2023년 154kV 이원S/S 외장재 교체공사","건물 마감재 교체공사 시행","2023-06-28 09:00","2023-07-05 18:00","2023-06-25 09:00","2023-06-28 18:00","연속"]
[247,"강원","태백","영월S/S CB 6100","22-23년 태백전력지사 변전협력회사 총액공사","영월S/S 154kV BUS TIE GIS 보통점검","2023-06-28 10:00","2023-06-28 16:00","2023-06-28 10:00","2023-06-28 16:00","연속"]
[248,"강원","태백","신제천영월CC#2 T/L","2023년 태백전력지사 변전협력회사 총액공사","영월C/C S/Y 154kV 신제천-영월C/C#2T/L GIS 보통점검","2023-06-29 10:00","2023-06-29 18:00","2023-06-29 10:00","2023-06-29 18:00","연속"]
[249,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","임시회로 구성 원복 및 무부하가압 (즉시가압 가능)","2023-06-29 09:00","2023-06-30 18:00","취소","취소","매일"]
[250,"충북","직할","광혜원S/S #1 Sh.C CB","광혜원S/S 154kV 장기사용 GIS 대체공사","임시회로 구성 (154kV 삼죽-광혜원T/L ↔ #1 Sh.C)","2023-06-01 09:00","2023-06-30 18:00","취소","취소","연속"]
[251,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","임시회로 구성 및 무부하가압 (즉시가압 가능)","2023-06-07 09:00","2023-06-07 18:00","취소","취소","연속"]
[252,"충북","직할","삼죽광혜원 T/L","광혜원S/S 154kV 장기사용 GIS 대체공사","중장비 사용에 따른 안전이격거리 확보 (즉시가압 가능)","2023-06-11 09:00","2023-06-11 18:00","취소","취소","연속"]
[253,"충북","직할","신진천진천#1 T/L","23년도 상반기 충북본부 직할 154kV GIS 정밀점검공사","신진천변전소 154kV 신진천진천#1T/L GIS 정밀점검공사","2023-06-03 09:00","2023-06-05 18:00","취소","취소","연속"]
[254,"충북","직할","신진천S/S SEC CB 61620","23년도 충북본부 상반기 154kV GIS 정밀점검 공사","154kV #2Sh.C GIS 정밀점검 후 무부하가압을 위한 휴전","2023-06-03 13:00","2023-06-03 14:00","취소","취소","연속"]
[255,"충북","직할","신진천오창#1 T/L","23년도 상반기 충북본부 직할 154kV GIS 정밀점검공사","신진천변전소 154kV 신진천오창#1T/L 정밀점검","2023-06-06 09:00","2023-06-08 18:00","취소","취소","연속"]
[256,"충북","직할","신진천S/S SEC CB 65660","'22-23년 충북직할 변전협력회사 총액공사","신진천S/S 154kV #65-#66 SEC GIS 보통점검","2023-06-07 10:00","2023-06-07 15:00","취소","취소","연속"]
[257,"충북","청주","오창국사#1 T/L","22~23년 청주전력 변전총액공사","170kV GIS 보통점검","2023-06-19 09:00","2023-06-19 18:00","2023-06-19 09:00","2023-06-19 18:00","연속"]
[258,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","60-61 BUS SEC GIS 교체","2023-06-04 09:00","2023-06-09 14:00","취소","취소","연속"]
[259,"충북","청주","남청주S/S #60 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","60-61 BUS SEC GIS 교체","2023-06-03 09:00","2023-06-04 09:00","취소","취소","연속"]
[260,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주#1, 4T/L, #62 M.Tr 1차 GIS 대체","2023-06-25 14:00","2023-06-30 18:00","취소","취소","연속"]
[261,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주#1, 4T/L, #62 M.Tr 1차 GIS 대체","2023-06-16 14:00","2023-06-25 14:00","취소","취소","연속"]
[262,"충북","청주","남청주S/S CB 6200","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주#1, 4T/L, #62 M.Tr 1차 GIS 대체","2023-06-13 09:00","2023-06-30 18:00","2023-06-02 09:00","2023-06-02 18:00","연속"]
[263,"충북","청주","남청주S/S #60 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","60-61 BUS SEC GIS 교체","2023-06-09 14:00","2023-06-11 18:00","취소","취소","연속"]
[264,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주#1, 4T/L, #62 M.Tr 1차 GIS 대체","2023-06-13 09:00","2023-06-16 14:00","취소","취소","연속"]
[265,"충북","청주","남청주S/S SEC CB 60610","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","60-61 BUS SEC GIS 교체","2023-06-03 09:00","2023-06-11 18:00","취소","취소","연속"]
[266,"충북","청주","남청주청주#1 T/L","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주#1, 4T/L, #62 M.Tr 1차 GIS 대체","2023-06-13 14:00","2023-06-30 18:00","취소","취소","연속"]
[267,"충북","청주","서청주사직#1 T/L","23년 청주전력 170kV GIS 정밀점검","사직SS 서청주-사직#1T/L GIS 정밀점검","2023-06-17 09:00","2023-06-18 18:00","2023-06-17 09:00","2023-06-18 18:00","연속"]
[268,"충북","청주","서청주사직#1 T/L","23년 청주전력 170kV GIS 정밀점검","서청주SS 서청주사직#1T/L GIS 차단부 정밀점검","2023-06-10 09:00","2023-06-11 18:00","2023-06-10 09:00","2023-06-11 18:00","연속"]
[269,"충북","청주","남청주죽림#2 T/L","23년 청주전력 170kV GIS 정밀점검","죽림SS 남청주-죽림#2T/L 차단부 정밀점검","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[270,"충북","충주","감곡가남#1 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV감곡가남#1 T/L No.1 ~ 22","2023-06-10 07:30","2023-06-11 18:00","취소","취소","매일"]
[271,"충북","충주","감곡가남#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV감곡가남#2 T/L No.1 ~ 22","2023-06-17 07:30","2023-06-18 18:00","취소","취소","매일"]
[272,"충북","충주","금왕남음성#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV 금왕남음성T/L No.2 ~ 26","2023-06-12 07:30","2023-06-15 18:00","2023-06-12 07:30","2023-06-15 18:00","매일"]
[273,"충북","충주","금왕남음성#1 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV 금왕남음성T/L No.2 ~ 26","2023-06-16 07:30","2023-06-21 18:00","2023-06-16 07:30","2023-06-21 18:00","매일"]
[274,"충북","충주","신제천왕암#1 T/L","345kV 신제천-신충주 등 6개 T/L 송전피뢰기 설치공사","154kV 신제천-왕암#1 T/L No.6~37 송전피뢰기 설치공사(2차)","2023-06-17 07:00","2023-06-19 18:00","취소","취소","매일"]
[275,"충북","충주","신제천제천#1 T/L","345kV 신제천-신충주 등 6개 T/L 송전피뢰기 설치공사","154kV 신제천-제천#1 T/L No.6~27.91 송전피뢰기 설치공사(1차)","2023-06-10 07:00","2023-06-11 18:00","취소","취소","매일"]
[276,"충북","충주","신제천왕암#1 T/L","345kV 신제천-신충주 등 6개 T/L 송전피뢰기 설치공사","154kV 신제천-왕암#1 T/L No.6~37 송전피뢰기 설치공사(1차)","2023-06-10 07:00","2023-06-11 18:00","취소","취소","매일"]
[277,"충북","충주","신제천제천#1 T/L","345kV 신제천-신충주 등 6개 T/L 송전피뢰기 설치공사","154kV 신제천-제천#1 T/L No.6~27.91 송전피뢰기 설치공사(2차)","2023-06-16 07:00","2023-06-17 18:00","취소","취소","매일"]
[278,"충북","충주","신충주음성#2 T/L","22-23년 충주전력지사 변전정비총액공사","신충주,음성S/S 신충주음성#2T/L GIS 보통점검","2023-06-22 10:00","2023-06-22 18:00","취소","취소","연속"]
[279,"충북","충주","신충주음성#1 T/L","22-23년 충주전력지사 변전정비총액공사","신충주,음성S/S 신충주음성#1T/L GIS 보통점검","2023-06-21 10:00","2023-06-21 18:00","취소","취소","연속"]
[280,"충북","충주","신충주감곡#2 T/L","22-23년 충주전력지사 변전정비총액공사","신충주S/S 신충주감곡#2T/L GIS 보통점검","2023-06-23 10:00","2023-06-23 18:00","2023-06-15 10:00","2023-06-15 18:00","연속"]
[281,"충북","충주","왕암여주#2 T/L","345kV 신제천-신충주 등 6개 T/L 송전피뢰기 설치공사","154kV 왕암-여주#2 T/L No.11~54, 99~132 송전피뢰기 설치공사(주말작업 없음)","2023-06-07 07:00","2023-06-15 18:00","2023-06-07 07:00","2023-06-15 18:00","매일"]
[282,"충북","충주","왕암충주 T/L","2022~23년 충주전력지사 송전협력회사 총액공사","불량압축인류클램프 교체공사","2023-06-13 07:00","2023-06-16 18:00","2023-06-16 07:00","2023-06-21 18:00","매일"]
[283,"충북","충주","음성금왕#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV 음성금왕T/L No.40 ~ 64","2023-06-16 07:30","2023-06-21 18:00","2023-06-16 07:30","2023-06-21 18:00","매일"]
[284,"충북","충주","음성금왕#1 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV 음성-금왕T/L No.40 ~ 64","2023-06-12 07:30","2023-06-15 18:00","2023-06-12 07:30","2023-06-15 18:00","매일"]
[285,"충북","충주","음성사리 T/L","음성 천연가스 발전소 154kV 송전선로 건설공사(동서발전 시행)","- 가선로 구성을 위한 휴전(가철탑 6기 구성)","2023-06-06 09:00","2023-06-11 18:00","2023-06-06 09:00","2023-06-11 18:00","연속"]
[286,"충북","충주","충주S/S CB 6200","22-23년 충주전력지사 변전정비 총액공사","충주S/S 154kV #60-#65 모선보호반 대체","2023-06-07 09:00","2023-06-09 18:00","2023-06-07 09:00","2023-06-09 18:00","연속"]
[287,"충북","충주","충주S/S CB 6100","22-23년 충주전력지사 변전정비 총액공사","충주S/S 154kV #60-#65 모선보호반 대체","2023-06-07 09:00","2023-06-09 18:00","2023-06-07 09:00","2023-06-09 18:00","연속"]
[288,"충북","충주","풍동음성#2 T/L","음성 천연가스 발전소 154kV 송전선로 건설공사(동서발전 시행)","- 가선로 구성을 위한 휴전(가철탑 6기 구성)","2023-06-06 09:00","2023-06-11 18:00","2023-06-06 09:00","2023-06-11 18:00","연속"]
[289,"대전세종충남","대전","신옥천남대전#1 T/L","(5월 취소시)[송전]345kV신옥천-청양 등7개T/L추락방지장치설치공사","(5월 취소시)[송전] 154kV 신옥천-남대전T/L 추락방지장치 설치공사","2023-06-01 08:00","2023-06-14 18:00","2023-06-01 08:00","2023-06-14 18:00","매일"]
[290,"대전세종충남","대전","신옥천남대전#4 T/L","(5월취소시)[송전]345kV신옥천-청양 등7개T/L추락방지장치설치공사","(5월취소시)[송전] 154kV 신옥천-남대전삼사T/L 추락방지장치 설치공사","2023-06-15 08:00","2023-06-27 18:00","2023-06-15 08:00","2023-06-27 18:00","매일"]
[291,"대전세종충남","대전","팔봉두마#1 T/L","(5월 취소시)[송전] 154kV 팔봉-두마T/L 정밀점검","(5월 취소시)[송전] 154kV 팔봉-두마#1T/L 정밀점검","2023-06-12 08:00","2023-06-16 18:00","취소","취소","매일"]
[292,"대전세종충남","대전","남대전신흥#2 T/L","신흥S/S 170kV GIS 보통점검(남대전-신흥#2)","신흥S/S 170kV GIS 보통점검(남대전-신흥#2)","2023-06-08 09:00","2023-06-08 18:00","2023-06-08 09:00","2023-06-08 18:00","연속"]
[293,"대전세종충남","대전","남대전신흥#1 T/L","신흥S/S 170kV GIS 보통점검(남대전-신흥#1)","신흥S/S 170kV GIS 보통점검(남대전-신흥#1)","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[294,"대전세종충남","대전","신옥천용운#1 T/L","154kV 신옥천-용운#1T/L, 용운-대화#2T/L 정밀점검","154kV 신옥천-용운, 용운-대화 정밀점검 - 154kV 신옥천-용운 #1T/L 정밀점검 (6/16일 : 154kV 용운-대화 #2T/L 정밀점검 목적 휴전예정(4회선병가))","2023-06-12 08:00","2023-06-16 18:00","2023-06-12 08:00","2023-06-16 18:00","매일"]
[295,"대전세종충남","대전","신옥천용운#2 T/L","154kV 신옥천-용운#2T/L, 용운-대화#1T/L 정밀점검","154kV 신옥천-용운, 용운-대화 정밀점검 - 154kV 신옥천-용운 #2T/L 정밀점검 (6/23일 : 154kV 용운-대화 #1T/L 정밀점검 목적 휴전예정(4회선병가))","2023-06-19 08:00","2023-06-23 18:00","2023-06-19 08:00","2023-06-23 18:00","매일"]
[296,"대전세종충남","대전","신옥천추부#2 T/L","(5월 취소시)[송전]345kV신옥천-청양 등7개T/L추락방지장치설치공사","(5월 취소시)[송전] 154kV 신옥천-추부T/L 추락방지장치 설치공사","2023-06-01 08:00","2023-06-15 18:00","취소","취소","매일"]
[297,"대전세종충남","대전","추부금산#1 T/L","(5월 취소시)[송전]345kV신옥천-청양 등7개T/L추락방지장치설치공사","(5월 취소시)[송전] 154kV 추부-금산T/L 추락방지장치 설치공사","2023-06-09 08:00","2023-07-07 18:00","취소","취소","매일"]
[298,"대전세종충남","서산","대산석문#1 T/L","154kV 대산-석문T/L 항공장애표시구 설치","154kV 대산-석문T/L 항공장애표시구 설치(6경간) No.19~20,32~34,35~36,38~40","2023-06-27 08:00","2023-06-29 18:00","취소","취소","매일"]
[299,"대전세종충남","서산","신당진당진#1 T/L","154kV 합덕-송악#1T/L 점퍼지지애자교체","154kV 합덕-송악#1T/L 점퍼지지애자교체(5기) (No.2,8,54,58,59)","2023-06-15 07:00","2023-06-16 18:00","2023-06-15 07:00","2023-06-16 18:00","매일"]
[300,"대전세종충남","서산","태안태안화력 T/L","태안화력S/Y 옥외 노출설비 GIS 내장화공사","태풍대비 태안화력S/Y 옥외 노출설비 긴급 GIS 내장화공사 (LA, CVT 등)","2023-06-12 09:00","2023-06-15 18:00","취소","취소","연속"]
[301,"대전세종충남","서산","서산태안화력 T/L","태안화력S/Y 옥외 노출설비 GIS 내장화공사","태풍대비 태안화력S/Y 옥외 노출설비 긴급 GIS 내장화공사 (LA, CVT 등)","2023-06-05 09:00","2023-06-08 18:00","2023-06-05 09:00","2023-06-08 18:00","연속"]
[302,"대전세종충남","서산","합덕송악#1 T/L","154kV 합덕-송악#1T/L 피뢰기 설치공사","154kV 합덕-송악#1T/L 피뢰기 설치공사(38기) (No.1~28,49,50,52~59)","2023-06-13 08:00","2023-06-20 18:00","2023-06-13 08:00","2023-06-20 18:00","매일"]
[303,"대전세종충남","서산","해미홍성 T/L","154kV 해미-홍성T/L 정밀점검","(변전) 6/5~8 154kV 해미-홍성T/L 보호반 대체_연속 (송전) 6/9~6/15 154kV 해미-홍성T/L 정밀점검(S/T~No.64)_매일_주말제외","2023-06-05 08:00","2023-06-15 18:00","취소","취소","연속"]
[304,"대전세종충남","세종","부강대청HP T/L","[송전]154kV 부강-대청HPT/L 추락방지시설 설치공사","[송전]154kV 부강-대청HPT/L 추락방지시설 설치공사 - No.C/T, 1~42 (43기)","2023-06-14 07:00","2023-06-23 18:00","2023-06-14 07:00","2023-06-23 18:00","매일"]
[305,"대전세종충남","세종","부강신탄진 T/L","[송전]154kV 부강-신탄진T/L 추락방지시설 설치공사","[송전]154kV 부강-신탄진T/L 추락방지시설 설치공사 - No.41~57, 62 (18기)","2023-06-05 07:00","2023-06-13 18:00","2023-06-05 07:00","2023-06-13 18:00","매일"]
[306,"대전세종충남","세종","조치원월산 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험 -조치원,월산S/S 양단 조작시험","2023-06-08 10:00","2023-06-08 18:00","2023-06-08 10:00","2023-06-08 18:00","연속"]
[307,"대전세종충남","세종","서세종조치원 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험(조치원)","2023-06-09 10:00","2023-06-09 18:00","2023-06-09 10:00","2023-06-09 18:00","연속"]
[308,"대전세종충남","세종","월산서세종 T/L","[변전]'23년 세종전력지사 변전협력회사 총액공사","○154kV GIS 보통점검 -LA 보통점검 병행","2023-06-12 10:00","2023-06-12 18:00","2023-06-12 10:00","2023-06-12 18:00","연속"]
[309,"대전세종충남","직할","둔곡송강#1 T/L","(5월 취소 시)2023년 직할 170kV GIS 정밀점검 공사","(5월 취소 시2023년 직할 170kV GIS 정밀점검 공사","2023-06-03 09:00","2023-06-04 18:00","취소","취소","연속"]
[310,"대전세종충남","직할","송강신일#1 T/L","(5월 취소 시)2023년 직할 170kV GIS 정밀점검 공사","(5월 취소 시)2023년 직할 170kV GIS 정밀점검 공사","2023-06-05 09:00","2023-06-06 18:00","취소","취소","연속"]
[311,"대전세종충남","직할","신탄진대청HP T/L","[송전]154kV 신탄진-대청HPT/L 추락방지시설 설치공사","[송전]154kV 신탄진-대청HPT/L 추락방지시설 설치공사 - No.1~7, 42~56, 62 (23기)","2023-06-26 07:00","2023-06-28 18:00","2023-06-26 07:00","2023-06-28 18:00","매일"]
[312,"대전세종충남","천안","둔포추팔#1 T/L","154kV 둔포-추팔#1T/L GIS 전자변 교체","154kV 둔포-추팔#1T/L GIS 전자변 교체","2023-06-13 09:00","2023-06-13 18:00","2023-06-13 09:00","2023-06-13 18:00","연속"]
[313,"대전세종충남","천안","서천안탕정#1 T/L","154kV 서천안-탕정#1/L 보호배전반 성능개선","154kV 서천안-탕정#1/L 보호배전반 성능개선","2023-06-15 09:00","2023-06-15 18:00","취소","취소","연속"]
[314,"대전세종충남","천안","서천안S/S SEC CB 60610","서천안S/S 154kV #60-61 SEC GIS 보통점검","서천안S/S 154kV #60-61 SEC GIS 보통점검","2023-06-16 09:00","2023-06-16 18:00","2023-06-16 09:00","2023-06-16 18:00","매일"]
[315,"대전세종충남","천안","서천안S/S SEC CB 65660","서천안S/S 154kV B/S 65-66 GIS 보통점검","서천안S/S 154kV B/S 65-66 GIS 보통점검","2023-06-30 09:00","2023-06-30 18:00","2023-06-30 09:00","2023-06-30 18:00","매일"]
[316,"대전세종충남","천안","신온양S/S CB 6400","신온양S/S 154kV #63-68 BUS TIE GIS 보통점검","신온양S/S 154kV #63-68 BUS TIE GIS 보통점검","2023-06-23 09:00","2023-06-23 18:00","2023-06-23 09:00","2023-06-23 18:00","연속"]
[317,"대전세종충남","천안","신탕정S/S CB 7571","신탕정S/S 7500, 7571 GIS 보통점검","신탕정S/S 7500, 7571 GIS 보통점검","2023-06-09 09:00","2023-06-09 14:00","취소","취소","연속"]
[318,"대전세종충남","천안","신탕정S/S CB 7500","신탕정S/S 7500, 7571 GIS 보통점검","신탕정S/S 7500, 7571 GIS 보통점검","2023-06-09 14:00","2023-06-09 18:00","취소","취소","연속"]
[319,"대전세종충남","천안","서천안S/S CB 6200","서천안S/S 154kV B/T6200 GIS 보통점검","서천안S/S 154kV B/T6200 GIS 보통점검","2023-06-23 09:00","2023-06-23 18:00","2023-06-23 09:00","2023-06-23 18:00","매일"]
[320,"대전세종충남","천안","서천안탕정#2 T/L","154kV 서천안-탕정#2/L 보호배전반 성능개선","154kV 서천안-탕정#2/L 보호배전반 성능개선","2023-06-16 09:00","2023-06-16 18:00","취소","취소","연속"]
[321,"대전세종충남","천안","아산온양#2 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-26 07:00","2023-06-29 18:00","취소","취소","매일"]
[322,"대전세종충남","천안","아산온양#1 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-19 07:00","2023-06-22 18:00","취소","취소","매일"]
[323,"대전세종충남","천안","아산온양#2 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-12 07:00","2023-06-13 18:00","취소","취소","매일"]
[324,"대전세종충남","천안","아산인주#1 T/L","154kV 아산-인주#1T/L 보호배전반 교체","154kV 아산-인주#1T/L 보호배전반 교체","2023-06-01 09:00","2023-06-08 18:00","취소","취소","연속"]
[325,"대전세종충남","천안","아산인주#2 T/L","154kV 아산-인주#2T/L 보호배전반 교체","154kV 아산-인주#2T/L 보호배전반 교체","2023-06-01 09:00","2023-06-08 18:00","취소","취소","연속"]
[326,"대전세종충남","천안","아산온양#1 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-05 07:00","2023-06-06 18:00","취소","취소","매일"]
[327,"대전세종충남","천안","아산예산#2 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-05 07:00","2023-06-09 18:00","취소","취소","매일"]
[328,"대전세종충남","천안","아산예산#1 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-12 07:00","2023-06-16 18:00","취소","취소","매일"]
[329,"대전세종충남","천안","예산응봉#1 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-09 07:00","2023-06-09 18:00","취소","취소","연속"]
[330,"대전세종충남","천안","예산응봉#2 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-16 07:00","2023-06-16 18:00","취소","취소","연속"]
[331,"대전세종충남","천안","장재천안#1 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-23 07:00","2023-06-23 18:00","2023-06-23 07:00","2023-06-23 18:00","연속"]
[332,"대전세종충남","천안","장재천안#2 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-30 07:00","2023-06-30 18:00","2023-06-30 07:00","2023-06-30 18:00","연속"]
[333,"대전세종충남","천안","한샘직산#1 T/L","154kV 직산S/S #1M.Tr 증설공사","154kV 직산S/S #1M.Tr 증설공사 무부하가압","2023-06-08 09:00","2023-06-09 17:00","2023-06-08 09:00","2023-06-09 17:00","연속"]
[334,"대전세종충남","천안","온양풍세#2 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-21 07:00","2023-06-22 18:00","2023-06-21 07:00","2023-06-22 18:00","매일"]
[335,"대전세종충남","천안","온양풍세#1 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-29 07:00","2023-06-29 18:00","2023-06-29 07:00","2023-06-29 18:00","매일"]
[336,"대전세종충남","천안","풍세장재#2 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-30 07:00","2023-06-30 18:00","2023-06-30 07:00","2023-06-30 18:00","매일"]
[337,"대전세종충남","천안","풍세장재#1 T/L","'22~'23년 천안전력지사 가공송전 협력회사 총액공사","6월 수평 추락방지장치 설치 - 154kV 아산-온양T/L 등 7개T/L - 345kV 신온양-서서울T/L","2023-06-23 07:00","2023-06-26 18:00","2023-06-23 07:00","2023-06-26 18:00","매일"]
[338,"대전세종충남","청양","청양S/S CB 6200","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","170kV GIS 보통점검 및 노후보호계전기 교체","2023-06-14 10:00","2023-06-15 18:00","2023-06-14 10:00","2023-06-15 18:00","연속"]
[339,"대전세종충남","청양","청양S/S CB 6100","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","170kV GIS 보통점검 및 노후보호계전기 교체","2023-06-12 10:00","2023-06-13 18:00","2023-06-12 10:00","2023-06-13 18:00","연속"]
[340,"대전세종충남","청양","청양신풍#1 T/L","[송전] 154kV 청양-신풍#1T/L 수평 추락방지장치 설치공사","345kV 청양-보령 등 11개T/L 철탑 추락방지장치 설치공사","2023-06-12 08:00","2023-06-16 18:00","2023-06-12 08:00","2023-06-16 18:00","매일"]
[341,"대전세종충남","청양","청양S/S SEC CB 65660","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","170kV GIS 보통점검 및 노후보호계전기 교체","2023-06-21 10:00","2023-06-22 18:00","2023-06-21 10:00","2023-06-22 18:00","연속"]
[342,"대전세종충남","청양","청양신풍#1 T/L","청양P/O 변전협력회사 총액공사","청양S/S 170kV GIS 조작시험 및 LA 초기점검 (A,B,C), PT 보통점검","2023-06-15 10:00","2023-06-15 18:00","취소","취소","연속"]
[343,"대전세종충남","청양","청양신풍#2 T/L","청양P/O 변전협력회사 총액공사","청양S/S 170kV GIS 조작시험 및 LA 초기점검 (A,B,C)","2023-06-16 10:00","2023-06-16 18:00","취소","취소","연속"]
[344,"대전세종충남","청양","청양신풍#2 T/L","[송전] 154kV 청양-신풍#2T/L 수평 추락방지장치 설치공사","345kV 청양-보령 등 11개T/L 철탑 추락방지장치 설치공사","2023-06-19 08:00","2023-06-21 18:00","2023-06-19 08:00","2023-06-21 18:00","매일"]
[345,"대전세종충남","청양","청양S/S SEC CB 60610","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","170kV GIS 보통점검 및 노후보호계전기 교체","2023-06-19 10:00","2023-06-20 18:00","2023-06-19 10:00","2023-06-20 18:00","연속"]
[346,"전북","군산","군공군산CC#2 T/L","154kV 군공-군산복합T/L OF 절연유 체유작업","154kV 군공-군산복합T/L OF 절연유 체유작업","2023-06-05 09:00","2023-06-09 18:00","2023-06-05 09:00","2023-06-09 18:00","매일"]
[347,"전북","군산","동군산군산CC#1 T/L","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사(시험가압)","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-06-11 08:00","2023-06-12 08:00","2023-06-11 09:00","2023-06-12 09:00","연속"]
[348,"전북","군산","동군산군산CC#1 T/L","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사(시험가압)","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-06-15 08:00","2023-06-16 08:00","2023-06-15 09:00","2023-06-16 09:00","연속"]
[349,"전북","군산","군산S/S CB 6300","군산S/S 154kV #4M.Tr 2차 GIS 정밀점검","군산S/S 154kV #4M.Tr 2차 GIS 정밀점검","2023-06-12 09:00","2023-06-14 18:00","2023-06-12 09:00","2023-06-14 18:00","연속"]
[350,"전북","군산","군산S/S #62 BUS","군산S/S 154kV #4M.Tr 2차 GIS 정밀점검","군산S/S 154kV #4M.Tr 2차 GIS 정밀점검","2023-06-13 14:00","2023-06-14 18:00","2023-06-13 14:00","2023-06-14 18:00","연속"]
[351,"전북","군산","군산영등#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-06-08 07:00","2023-06-13 18:00","취소","취소","매일"]
[352,"전북","군산","군산이리#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-06-08 07:00","2023-06-15 18:00","취소","취소","매일"]
[353,"전북","군산","군산동군산#2 T/L","군산P/O 154kV 차단기 정밀점검 공사","군산S/S 154kV #4M.Tr 2차 차단기 정밀점검","2023-06-14 11:00","2023-06-14 14:00","2023-06-14 11:00","2023-06-14 14:00","연속"]
[354,"전북","군산","군산이리#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-06-24 07:00","2023-06-26 18:00","취소","취소","매일"]
[355,"전북","군산","군산S/S #62 BUS","154kV 서군산S/S 옥내화 공사 외","154kV 군산-서군산 #2TL 지중화_No65호-서군산","2023-06-22 09:00","2023-06-23 18:00","취소","취소","연속"]
[356,"전북","군산","군산동군산#2 T/L","군산P/O 154kV 차단기 정밀점검 공사","군산S/S 154kV #4M.Tr 2차 차단기 정밀점검","2023-06-13 11:00","2023-06-13 14:00","2023-06-13 11:00","2023-06-13 14:00","연속"]
[357,"전북","군산","군산S/S #67 BUS","군산S/S 154kV #4M.Tr 2차 GIS 정밀점검","군산S/S 154kV #4M.Tr 2차 GIS 정밀점검","2023-06-12 09:00","2023-06-13 14:00","2023-06-12 09:00","2023-06-13 14:00","연속"]
[358,"전북","군산","군산영등#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-06-19 07:00","2023-06-26 18:00","취소","취소","매일"]
[359,"전북","군산","동군산장항#2 T/L","동군산S/S SA혼용시스템 제어케이블 정비공사","동군산S/S 154kV 동군산-장항#2/L SA 혼용시스템 제어케이블 정비 공사","2023-06-12 09:00","2023-06-13 18:00","취소","취소","연속"]
[360,"전북","군산","동군산장항#1 T/L","군산P/O 154kV 차단기 정밀점검 공사","동군산S/S 154kV 동군산-장항#1T/L 차단기 정밀점검","2023-06-14 09:00","2023-06-16 18:00","취소","취소","연속"]
[361,"전북","군산","군산동군산#2 T/L","동군산S/S 154kV BUS-TIE 차단기 정밀점검","동군산S/S 154kV BUS-TIE 차단기 정밀점검","2023-06-09 15:00","2023-06-09 18:00","2023-06-09 18:00","2023-06-09 19:00","연속"]
[362,"전북","군산","군산서군산#2 T/L","154kV 군산-서군산T/L 등 2개T/L 일부 지중화 공사 외","1. 154kV 군산-서군산 #2TL 지중화_No65호-서군산 2. 154kV 서군산SS 옥내화 3. 154kV 서군산-소룡 #2TL 인출변경","2023-06-16 09:00","2023-06-26 18:00","2023-06-01 09:00","2023-06-09 18:00","연속"]
[363,"전북","군산","서군산소룡#2 T/L","154kV 서군산S/S 옥내화 공사 외","1. 154kV 군산-서군산 #2TL 지중화_No65호-서군산 2. 154kV 서군산SS 옥내화 3. 154kV 서군산-소룡 #2TL 인출변경","2023-06-16 10:00","2023-06-20 18:00","2023-06-01 09:00","2023-06-09 18:00","연속"]
[364,"전북","군산","영등낭산#2 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2023-06-19 07:00","2023-06-27 18:00","취소","취소","연속"]
[365,"전북","군산","영등낭산#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-06-20 07:00","2023-06-20 18:00","취소","취소","매일"]
[366,"전북","군산","영등낭산#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-06-21 07:00","2023-06-23 18:00","취소","취소","매일"]
[367,"전북","군산","영등낭산#1 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2023-06-08 07:00","2023-06-16 18:00","취소","취소","연속"]
[368,"전북","군산","영등낭산#2 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2023-06-07 07:00","2023-06-07 18:00","취소","취소","연속"]
[369,"전북","군산","영등팔봉#1 T/L","군산P/O 154kV 차단기 정밀점검 공사","팔봉S/S 154kV #4M.Tr 1차 차단기 정밀점검","2023-06-22 17:00","2023-06-22 20:00","2023-06-22 17:00","2023-06-22 20:00","연속"]
[370,"전북","군산","영등팔봉#1 T/L","군산P/O 154kV 차단기 정밀점검 공사","팔봉S/S 154kV #4M.Tr 1차 차단기 정밀점검","2023-06-20 17:00","2023-06-20 20:00","2023-06-20 17:00","2023-06-20 20:00","연속"]
[371,"전북","군산","팔봉두마#2 T/L","군산P/O 노후배전반 대체공사","영등S/S 팔봉-두마#2T/L 보호반 대체","2023-06-19 09:00","2023-06-22 18:00","취소","취소","연속"]
[372,"전북","군산","팔봉S/S CB 6100","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀점검","2023-06-19 09:00","2023-06-22 18:00","2023-06-19 09:00","2023-06-22 18:00","연속"]
[373,"전북","군산","팔봉S/S #65 BUS","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀점검","2023-06-21 09:00","2023-06-22 20:00","2023-06-21 09:00","2023-06-22 20:00","연속"]
[374,"전북","군산","팔봉두마#1 T/L","군산P/O 노후배전반 대체공사","영등S/S 팔봉-두마#1T/L 보호반 대체","2023-06-12 09:00","2023-06-15 18:00","취소","취소","연속"]
[375,"전북","군산","팔봉S/S #60 BUS","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀점검","2023-06-19 09:00","2023-06-20 20:00","2023-06-19 09:00","2023-06-20 20:00","연속"]
[376,"전북","김제","신김제남전주#2 T/L","신김제S/S 154kV #61-#62SEC 차단기 정밀점검","신김제S/S 154kV #61-#62SEC 차단기 정밀점검","2023-06-28 11:00","2023-06-28 13:00","2023-06-28 11:00","2023-06-28 13:00","연속"]
[377,"전북","김제","신김제전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-06-03 08:00","2023-06-09 18:00","취소","취소","연속"]
[378,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-06-03 08:00","2023-06-08 18:00","취소","취소","연속"]
[379,"전북","김제","신김제남전주#2 T/L","신김제S/S 345kV #3M.Tr 2차 차단기 정밀점검","신김제S/S 345kV #3M.Tr 2차 차단기 정밀점검","2023-06-16 11:00","2023-06-17 13:00","2023-06-13 11:00","2023-06-14 13:00","매일"]
[380,"전북","김제","신김제남전주#2 T/L","신김제S/S 345kV #4M.Tr 2차 차단기 정밀점검","신김제S/S 345kV #4M.Tr 2차 차단기 정밀점검","2023-06-21 11:00","2023-06-22 13:00","2023-06-21 11:00","2023-06-22 13:00","매일"]
[381,"전북","김제","신김제S/S SEC CB 60610","신김제S/S 154kV #61-#62SEC 차단기 정밀점검","신김제S/S 154kV #61-#62SEC 차단기 정밀점검(6.26~28, 연속)","2023-06-26 09:00","2023-06-27 18:00","2023-06-26 09:00","2023-06-27 18:00","연속"]
[382,"전북","김제","신김제S/S SEC CB 61620","신김제S/S 154kV #61-#62SEC 차단기 정밀점검","신김제S/S 154kV #61-#62SEC 차단기 정밀점검(6.26~28, 연속)","2023-06-26 09:00","2023-06-28 18:00","2023-06-26 09:00","2023-06-28 18:00","연속"]
[383,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-06-09 08:00","2023-06-09 18:00","취소","취소","연속"]
[384,"전북","김제","신김제남전주#1 T/L","신김제S/S 154kV #61-#62SEC 차단기 정밀점검","신김제S/S 154kV #61-#62SEC 차단기 정밀점검","2023-06-27 11:00","2023-06-27 13:00","2023-06-27 11:00","2023-06-27 13:00","연속"]
[385,"전북","직할","무주진안 T/L","'22년~'23년 가공송전 협력회사 총액공사","□ 작업대상 ○ 154kV 무주분기(무주-진안)T/L No.1~45 ○ 154kV 북전주-진안(무주-진안)T/L No.105~175 □ 작업내용 : 피뢰기 설치","2023-06-12 07:00","2023-06-23 18:00","취소","취소","매일"]
[386,"전북","직할","북전주봉동#1 T/L","154kV 봉동S/S #4M.Tr 개폐장치 설치공사(전문)","- GIS(170kV, 50kA, 1250A) × 1CCT 설치 - GIS(25.8kV, 25kA, 2000/630A) × 5BAY(5CCT) 설치 - 기타 부대공사 × 1식","2023-06-14 09:00","2023-06-14 18:00","취소","취소","연속"]
[387,"전북","직할","왕궁봉동#1 T/L","154kV 봉동S/S #4M.Tr 개폐장치 설치공사(전문)","- GIS(170kV, 50kA, 1250A) × 1CCT 설치 - GIS(25.8kV, 25kA, 2000/630A) × 5BAY(5CCT) 설치 - 기타 부대공사 × 1식","2023-06-14 09:00","2023-06-14 18:00","취소","취소","연속"]
[388,"전북","직할","왕궁봉동#1 T/L","154kV 봉동S/S #4M.Tr 개폐장치 설치공사(전문)","- GIS(170kV, 50kA, 1250A) × 1CCT 설치 - GIS(25.8kV, 25kA, 2000/630A) × 5BAY(5CCT) 설치 - 기타 부대공사 × 1식","2023-06-07 15:00","2023-06-08 11:00","취소","취소","연속"]
[389,"전북","직할","북전주봉동#1 T/L","154kV 봉동S/S #4M.Tr 개폐장치 설치공사(전문)","- GIS(170kV, 50kA, 1250A) × 1CCT 설치 - GIS(25.8kV, 25kA, 2000/630A) × 5BAY(5CCT) 설치 - 기타 부대공사 × 1식","2023-06-07 15:00","2023-06-08 11:00","취소","취소","연속"]
[390,"전북","직할","북전주봉동#1 T/L","북전주S/S 북전주-봉동#1T/L 조작시험","GIS 조작시험","2023-06-27 16:00","2023-06-27 20:00","취소","취소","연속"]
[391,"전북","직할","북전주봉동#2 T/L","북전주S/S 북전주-봉동#2T/L 조작시험","GIS 조작시험","2023-06-28 16:00","2023-06-28 20:00","취소","취소","연속"]
[392,"전북","직할","서곡S/S 전주파워T/L CB","서곡S/S 전주파워T/L 보통점검공사","GIS 보통점검","2023-06-29 09:00","2023-06-29 18:00","2023-06-29 09:00","2023-06-29 18:00","연속"]
[393,"전북","직할","전주서곡#1 T/L","전주-서곡#1T/L 보호반 대체공사","전주-서곡#1T/L 보호반 대체 및 차단기 양단 보통점검","2023-06-26 09:00","2023-06-28 14:00","취소","취소","연속"]
[394,"전북","직할","전주서곡#2 T/L","전주-서곡#2T/L 보호반 대체공사","전주-서곡#2T/L 보호반 대체 및 차단기 양단 보통점검","2023-06-28 14:00","2023-06-30 18:00","취소","취소","연속"]
[395,"광주전남","강진","강진남창#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","154kV 신강진-강진 피뢰기 설치공사 4회선 병가선로 휴전","2023-06-22 07:00","2023-06-23 18:00","취소","취소","매일"]
[396,"광주전남","강진","나주금천#2 T/L","세니온 보호계전기 일제 성능개선 시행(나주,금천)","세니온 보호계전기 일제 성능개선 시행 - 나주S/S 나주-금천#1,2T/L","2023-06-01 14:00","2023-06-01 18:00","2023-06-01 14:00","2023-06-01 18:00","연속"]
[397,"광주전남","강진","나주금천#1 T/L","세니온 보호계전기 일제 성능개선 시행(나주,금천)","세니온 보호계전기 일제 성능개선 시행 - 나주S/S 나주-금천#1,2T/L","2023-06-01 09:00","2023-06-01 14:00","2023-06-01 09:00","2023-06-01 14:00","연속"]
[398,"광주전남","강진","남창완도#1 T/L","154KV 남창-완도T/L 용량증대 전선교체공사","ㅇ구간 : 154kV 남창-완도 #1T/L No.1~48 ㅇ경간 : 16.9km 전선교체 ㅇ시공사 : 신한전력(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 520SQ로 전량교체)","2023-06-01 09:00","2023-07-04 18:00","2023-06-01 09:00","2023-07-04 18:00","연속"]
[399,"광주전남","강진","남창해남CS#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","추락방지장치 및 폴리머점퍼지지애자 설치","2023-06-19 07:00","2023-06-21 18:00","2023-06-19 07:00","2023-06-21 18:00","매일"]
[400,"광주전남","강진","남창해남CS#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","철탑 추락방지장치 설치 및 폴리머점퍼지지애자 설치","2023-06-29 07:00","2023-06-30 18:00","2023-06-29 07:00","2023-06-30 18:00","매일"]
[401,"광주전남","강진","강진남창#2 T/L","22~23년 철탑 추락방지장치 설치 공사","작업명 : 22~23년 철탑 추락방지장치 설치 공사 작업구간 : 신강진강진#2 38~42 (강진남창#2 1~5 병가)","2023-06-27 07:00","2023-06-28 18:00","취소","취소","연속"]
[402,"광주전남","강진","해남진도#2 T/L","23년도 강진전력지사 GIS 정밀점검 공사","진도S/S 해남-진도#2T/L GIS 정밀점검(효성제 차단부 주접점이탈 제작사 S/V 입회 점검)(비상시 즉시가압 불가능)","2023-06-14 14:00","2023-06-16 18:00","2023-06-14 14:00","2023-06-16 18:00","연속"]
[403,"광주전남","강진","해남진도#1 T/L","23년도 강진전력지사 GIS 정밀점검 공사","진도S/S 해남-진도#1T/L GIS 정밀점검(효성제 차단부 주접점이탈 제작사 S/V 입회 점검)(비상시 즉시가압 불가능)","2023-06-21 14:00","2023-06-23 18:00","2023-06-21 14:00","2023-06-23 18:00","연속"]
[404,"광주전남","강진","해남해남CS#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","수직, 수평 철탑 추락방지장치 설치","2023-06-12 07:00","2023-06-21 18:00","취소","취소","매일"]
[405,"광주전남","강진","해남진도#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","폴리머 점퍼지지애자 설치","2023-06-16 07:00","2023-06-16 18:00","2023-06-16 07:00","2023-06-16 18:00","매일"]
[406,"광주전남","강진","해남해남CS#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","수직, 수평 철탑 추락방지장치 설치","2023-06-26 07:00","2023-06-30 18:00","취소","취소","매일"]
[407,"광주전남","광주","계림S/S CB 6200","23년 광주전력지사 변전협력회사 총액공사","170kV GIS 조작시험 - 계림S/S BUS-TIE(#6200)","2023-06-05 09:00","2023-06-05 13:00","2023-06-05 09:00","2023-06-05 13:00","연속"]
[408,"광주전남","광주","계림S/S SEC CB 65660","23년 광주전력지사 변전협력회사 총액공사","170kV GIS 조작시험 - 계림S/S BUS-SEC(#65-66)","2023-06-07 14:00","2023-06-07 18:00","2023-06-07 14:00","2023-06-07 18:00","연속"]
[409,"광주전남","광주","계림S/S SEC CB 60610","23년 광주전력지사 변전협력회사 총액공사","170kV GIS 조작시험 - 계림S/S BUS-SEC(#60-61)","2023-06-07 09:00","2023-06-07 14:00","2023-06-07 09:00","2023-06-07 14:00","연속"]
[410,"광주전남","광주","담양S/S #61 BUS","담양S/S 170kV GIS 교체공사(5차분)","담양S/S 170kV GIS 교체공사(5차분)","2023-06-27 11:30","2023-07-06 10:00","2023-06-27 11:30","2023-07-06 10:00","연속"]
[411,"광주전남","광주","담양S/S #1 BUS","담양S/S 154kV GIS 교체공사(4차)","담양S/S 154kV GIS 교체공사(4차)","2023-06-06 14:00","2023-06-06 17:00","취소","취소","연속"]
[412,"광주전남","광주","담양S/S #2 BUS","담양S/S 154kV GIS 교체공사(4차)","담양S/S 154kV GIS 교체공사(4차)","2023-05-29 09:00","2023-06-06 18:00","취소","취소","연속"]
[413,"광주전남","광주","담양김제 T/L","담양S/S 154kV GIS 교체공사(4차)","담양S/S 154kV GIS 교체공사(4차)","2023-05-27 18:00","2023-05-28 18:00","취소","취소","연속"]
[414,"광주전남","광주","담양일곡#2 T/L","담양S/S 170kV GIS 교체공사(5차분)","담양S/S 170kV GIS 교체공사(5차분)","2023-06-26 08:00","2023-07-11 18:00","2023-06-26 08:00","2023-07-11 18:00","연속"]
[415,"광주전남","광주","담양S/S #66 BUS","담양S/S 170kV GIS 교체공사(5차분)","담양S/S 170kV GIS 교체공사(5차분)","2023-06-26 08:00","2023-06-27 10:00","2023-06-26 08:00","2023-06-27 10:00","연속"]
[416,"광주전남","광주","담양김제 T/L","담양S/S 154kV GIS 교체공사(4차)","담양S/S 154kV GIS 교체공사(4차)","2023-06-20 14:00","2023-06-21 14:00","2023-06-20 14:00","2023-06-21 14:00","연속"]
[417,"광주전남","광주","담양김제 T/L","담양S/S 154kV GIS 교체공사(4차)","담양S/S 154kV GIS 교체공사(4차)","2023-06-21 16:00","2023-06-21 17:00","2023-06-21 16:00","2023-06-21 17:00","연속"]
[418,"광주전남","광주","신광주일곡#2 T/L","154kV 신광주-일곡T/L C/T이설공사","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 전선교체 : ACSR 410(2회선), 0.360km - 임시선로 구성 : 임시철탑 1기, ACSR 410㎟ 0.547km","2023-06-03 08:00","2023-06-04 18:00","2023-06-03 08:00","2023-06-04 18:00","연속"]
[419,"광주전남","광주","신광주일곡#1 T/L","154kV 신광주-일곡T/L C/T이설공사","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 전선교체 : ACSR 410(2회선), 0.360km","2023-06-10 08:00","2023-06-11 18:00","2023-06-10 08:00","2023-06-11 18:00","연속"]
[420,"광주전남","광주","신광주일곡#2 T/L","154kV 신광주-일곡T/L No.3~10.1호 가공 임시선로 구성공사","ㅇ 사유 : 국제고 주변 지중화사업이 송전선로 휴전시 과부하 문제로 휴전기간 단축을 위한 가공 임시선로 구성 ㅇ 공사내용 - 철탑공사 : [신설] 산형강 2기, [철거] 산형강 2기 - ACSR 410㎟ ✕ 2B(2회선), 0.275km","2023-06-17 08:00","2023-06-18 18:00","2023-06-17 08:00","2023-06-18 18:00","연속"]
[421,"광주전남","광주","신광주계림#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","170kV GIS 보통점검, PT보통점검, LA보통점검","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[422,"광주전남","광주","장성영광#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","장성S/S 장성-영광#1T/L GIS 보통점검 장성S/S 장성-영광#1T/L 공기배출밸브 설치","2023-06-01 09:00","2023-06-01 18:00","취소","취소","연속"]
[423,"광주전남","목포","나주엄다#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체공사","- MGIS 설치시 안전거리 확보","2023-06-01 10:00","2023-06-01 17:00","2023-06-01 10:00","2023-06-01 17:00","연속"]
[424,"광주전남","목포","영광S/S #1 Sh.R CB","22-23년 목포전력지사 변전협력회사 총액공사","154kV Sh.R GIS 장기미동작 차단기 조작시험","2023-06-12 09:00","2023-06-12 18:00","취소","취소","연속"]
[425,"광주전남","목포","장성영광#1 T/L","22-23년 목포전력지사 변전협력회사 총액공사","장기미동작 차단기 조작시험 피뢰기 점검","2023-06-13 09:00","2023-06-13 18:00","취소","취소","연속"]
[426,"광주전남","목포","장성영광#2 T/L","22-23년 목포전력지사 변전협력회사 총액공사","장기미동작 차단기 조작시험 피뢰기 점검","2023-06-14 09:00","2023-06-14 18:00","취소","취소","연속"]
[427,"광주전남","목포","고창영광 T/L","22-23년 목포전력지사 변전협력회사 총액공사","장기미동작 차단기 조작시험 피뢰기 점검","2023-06-15 09:00","2023-06-15 18:00","2023-06-15 09:00","2023-06-15 18:00","연속"]
[428,"광주전남","목포","영광홍농 T/L","22-23년 목포전력지사 변전협력회사 총액공사","장기미동작 차단기 조작시험 피뢰기 점검","2023-06-16 09:00","2023-06-16 18:00","2023-06-16 09:00","2023-06-16 18:00","연속"]
[429,"광주전남","순천","광양하동#1 T/L","154kV 광양-하동#1T/L 추락방지시설 설치공사","154kV 광양-하동#1T/L 수평 추락방지시설 설치","2023-06-07 07:00","2023-06-14 18:00","2023-06-07 07:00","2023-06-14 18:00","매일"]
[430,"광주전남","순천","광양하동#2 T/L","154kV 광양-하동#2T/L 추락방지시설 설치공사","154kV 광양-하동#2T/L 수평 추락방지시설 설치","2023-06-15 07:00","2023-06-20 18:00","2023-06-15 07:00","2023-06-20 18:00","매일"]
[431,"광주전남","순천","서순천주암HP T/L","154kV 주암분기T/L 추락방지시설 설치공사","154kV 주암분기T/L 수직,수평 추락방지시설 설치","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[432,"광주전남","순천","승주주암HP T/L","154kV 주암분기T/L 추락방지시설 설치공사","154kV 주암분기T/L 수직,수평 추락방지시설 설치","2023-06-06 09:00","2023-06-06 18:00","2023-06-06 09:00","2023-06-06 18:00","연속"]
[433,"광주전남","순천","여수소라#1 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-06-12 09:00","2023-06-13 18:00","취소","취소","연속"]
[434,"광주전남","순천","여수소라#2 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-06-14 09:00","2023-06-15 18:00","취소","취소","연속"]
[435,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP-여수TP#2T/L 추락방지시설 설치공사","154kV 호남TP-여수TP#2T/L 수평 추락방지시설 설치 - 설치 구간 : No.1~13.1, 14기","2023-06-23 07:00","2023-06-23 18:00","취소","취소","연속"]
[436,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP-여수TP#1T/L 추락방지시설 설치공사","154kV 호남TP-여수TP#1T/L 수평 추락방지시설 설치 - 설치 구간 : No.1~13.1, 14기","2023-06-21 07:00","2023-06-22 18:00","취소","취소","매일"]
[437,"광주전남","순천","여수TP화치#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","화치S/S 여수TP-화치#2T/L GIS CB 타임측정 여수화력S/S 여수TP-화치#2T/L GIS 상시여자 보조계전기 교체(즉시가압 가능)","2023-06-19 09:00","2023-06-19 18:00","2023-06-19 09:00","2023-06-19 18:00","연속"]
[438,"광주전남","순천","여수TP여천#1 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-06-19 09:00","2023-06-22 18:00","취소","취소","연속"]
[439,"광주전남","순천","여수TP여천#2 T/L","가공송전 위탁공사 정밀점검(여수TP-여천#2 T/L)","가공송전 위탁공사 정밀점검(여수TP-여천#2 T/L) : 8기","2023-06-16 08:00","2023-06-16 18:00","취소","취소","연속"]
[440,"광주전남","순천","여수TP여천#1 T/L","가공송전 위탁공사 정밀점검(여수TP-여천#1 T/L)","가공송전 위탁공사 정밀점검(여수TP-여천#1 T/L) : 8기","2023-06-15 08:00","2023-06-15 18:00","취소","취소","연속"]
[441,"광주전남","순천","여수TP용성#2 T/L","가공송전 위탁공사 정밀점검(여수TP-용성#2 T/L)","가공송전 위탁공사 정밀점검(여수TP-용성#2 T/L) : 4기","2023-06-14 08:00","2023-06-14 18:00","취소","취소","연속"]
[442,"광주전남","순천","여수TP용성#1 T/L","가공송전 위탁공사 정밀점검(여수TP-용성#1 T/L)","가공송전 위탁공사 정밀점검(여수TP-용성#1 T/L) : 4기","2023-06-13 08:00","2023-06-13 18:00","취소","취소","연속"]
[443,"광주전남","순천","여수TP화치#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","화치S/S 여수TP-화치#1T/L GIS CB 타임측정 여수화력S/S 여수TP-화치#1T/L GIS 상시여자 보조계전기 교체(즉시가압 불가)","2023-06-12 09:00","2023-06-13 18:00","2023-06-12 09:00","2023-06-13 18:00","연속"]
[444,"광주전남","순천","호남TP여수TP#2 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-06-28 09:00","2023-06-29 18:00","취소","취소","연속"]
[445,"광주전남","순천","호남TP여수TP#1 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-06-26 09:00","2023-06-27 18:00","취소","취소","연속"]
[446,"광주전남","순천","용성여수산단#1 T/L","가공송전 위탁공사 정밀점검(용성여수산단#1 T/L)","가공송전 위탁공사 정밀점검(용성여수산단#1 T/L) : 16","2023-06-13 09:00","2023-06-13 18:00","취소","취소","연속"]
[447,"광주전남","순천","용성여수산단#2 T/L","가공송전 위탁공사 정밀점검(용성여수산단#2 T/L)","가공송전 위탁공사 정밀점검(용성여수산단#2 T/L) : 16","2023-06-14 09:00","2023-06-14 18:00","취소","취소","연속"]
[448,"광주전남","순천","순천율촌#2 T/L","154kV 율촌-화치#1T/L 추락방지시설 설치공사","154kV 율촌-화치#1T/L 수직,수평 추락방지시설 설치 - 설치 구간 : No.68, 1기(병가구간)","2023-06-28 09:00","2023-06-28 11:00","취소","취소","연속"]
[449,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단#2T/L 추락방지시설 설치공사","154kV 율촌-여수산단#2T/L 수직,수평 추락방지시설 설치 - 설치 구간 : No.1~51, 51기","2023-06-29 07:00","2023-07-05 18:00","취소","취소","매일"]
[450,"광주전남","순천","율촌화치#1 T/L","154kV 율촌-화치#1T/L 추락방지시설 설치공사","154kV 율촌-화치#1T/L 수직,수평 추락방지시설 설치 - 설치 구간 : No.1~68, 54기","2023-06-26 07:00","2023-07-03 18:00","2023-06-26 07:00","2023-07-03 18:00","매일"]
[451,"광주전남","순천","순천율촌#1 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-06-01 09:00","2023-06-02 18:00","취소","취소","연속"]
[452,"광주전남","순천","순천율촌#2 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검","2023-06-07 09:00","2023-06-08 18:00","취소","취소","연속"]
[453,"광주전남","직할","하남장성#1 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (비아-하남 29~74호, 하남-장성T/L 병가)","2023-06-12 09:00","2023-06-16 18:00","2023-06-12 09:00","2023-06-16 18:00","연속"]
[454,"광주전남","직할","비아하남#1 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (비아-하남 29~74호, 하남-장성T/L 병가)","2023-06-12 08:00","2023-06-22 18:00","2023-06-12 08:00","2023-06-22 18:00","연속"]
[455,"대구","경산","금호아화#1 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","(안전확보)수평추락방지장치 설치 - 작업구간 : No.1 ~ 58","2023-06-19 07:00","2023-06-28 18:00","2023-06-19 07:00","2023-06-28 18:00","연속"]
[456,"대구","경산","대구범물#2 T/L","'23년 경산P/O GIS 정밀점검 및 보통점검 공사","GIS 정밀점검 - #4M.Tr 1차 GIS 무부하 가압용 선로","2023-06-29 15:00","2023-06-29 18:00","2023-06-29 15:00","2023-06-29 18:00","연속"]
[457,"대구","경산","대구범물#1 T/L","'23년 경산P/O GIS 정밀점검 및 보통점검 공사","GIS 정밀점검 - #3M.Tr 1차 GIS 무부하 가압용 선로","2023-06-27 15:00","2023-06-27 18:00","2023-06-27 15:00","2023-06-27 18:00","연속"]
[458,"대구","경산","아화영천#2 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","(안전확보)수평추락방지장치 설치 - 작업구간 : No.1 ~ 64","2023-06-02 07:00","2023-06-13 18:00","2023-06-02 07:00","2023-06-13 18:00","연속"]
[459,"대구","경산","진량노변 T/L","진량S/S 6179 GIS 주접점 교체","(TEST선로)진량S/S 6179 GIS 주접점 교체관련 무부하가압","2023-06-16 16:00","2023-06-16 18:00","2023-06-16 16:00","2023-06-16 18:00","연속"]
[460,"대구","경산","신경산청통#2 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","(안전확보)수평추락방지장치 설치 - 작업구간 : No.1 ~ 63","2023-06-30 07:00","2023-07-12 18:00","2023-06-30 07:00","2023-07-12 18:00","연속"]
[461,"대구","달성","논공달성#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 논공-달성T/L 수평 추락방지장치 설치공사(안전확보)","2023-06-19 07:00","2023-06-22 18:00","2023-06-19 07:00","2023-06-22 18:00","연속"]
[462,"대구","달성","논공달성#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 논공-달성T/L 수평 추락방지장치 설치공사(안전확보)","2023-06-26 07:00","2023-06-29 18:00","2023-06-26 07:00","2023-06-29 18:00","연속"]
[463,"대구","달성","다사달서 T/L","달서S/S 다사-달서T/L GIS정밀점검","달서S/S 다사-달서T/L GIS정밀점검","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[464,"대구","달성","대구봉덕#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-봉덕T/L 수평 추락방지장치 설치공사(안전확보)","2023-06-15 07:00","2023-06-16 18:00","2023-06-15 07:00","2023-06-16 18:00","연속"]
[465,"대구","달성","대구봉덕#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-봉덕T/L 수평 추락방지장치 설치공사(안전확보)","2023-06-12 07:00","2023-06-14 18:00","2023-06-12 07:00","2023-06-14 18:00","연속"]
[466,"대구","달성","상인봉덕#1 T/L","GIS차단기동작특성시험","GIS차단기동작특성시험","2023-06-07 09:00","2023-06-07 14:00","2023-06-07 09:00","2023-06-07 14:00","연속"]
[467,"대구","달성","상인봉덕#2 T/L","GIS차단기동작특성시험","GIS차단기동작특성시험","2023-06-07 14:00","2023-06-07 18:00","2023-06-07 14:00","2023-06-07 18:00","연속"]
[468,"대구","달성","고령쌍림#2 T/L","GIS보통점검","GIS보통점검 및 상시여자보조계전기 교체","2023-06-09 11:00","2023-06-09 18:00","2023-06-09 11:00","2023-06-09 18:00","연속"]
[469,"대구","달성","고령쌍림#1 T/L","GIS차단기동작특성시험","GIS차단기동작특성시험","2023-06-09 09:00","2023-06-09 11:00","2023-06-09 09:00","2023-06-09 11:00","연속"]
[470,"대구","달성","현풍유가#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 현풍-유가T/L 수평 추락방지장치 설치공사","2023-06-01 07:00","2023-06-01 18:00","2023-06-01 07:00","2023-06-01 18:00","연속"]
[471,"대구","달성","논공현풍#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 현풍-유가T/L 수평 추락방지장치 설치공사(병가선로)","2023-06-01 07:00","2023-06-01 18:00","2023-06-01 07:00","2023-06-01 18:00","연속"]
[472,"대구","칠곡","농소김천#1 T/L","'22~23년 칠곡전력 가공송전협력 총액공사","관형지지물용 가이드레일 설치","2023-06-14 07:30","2023-06-14 18:00","2023-06-14 07:30","2023-06-14 18:00","연속"]
[473,"대구","포항","건천천북#1 T/L","건천S/S 170kV GIS 정밀점검","건천S/S 6B7 GIS 정밀점검","2023-06-04 09:00","2023-06-06 18:00","취소","취소","연속"]
[474,"대구","포항","건천천북#2 T/L","건천S/S 170kV GIS 정밀점검","건천S/S 677 GIS 정밀점검","2023-06-09 09:00","2023-06-11 18:00","취소","취소","연속"]
[475,"대구","포항","건천천북#1 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","(안전확보)수평추락방지장치 설치 - 작업구간 : No.1 ~4, 17, 20","2023-07-01 07:00","2023-07-01 18:00","2023-07-01 07:00","2023-07-01 18:00","연속"]
[476,"대구","포항","북포항남포항 T/L","154kV 남포항분기T/L 건설사업","- 154kV 왕신-남포항T/L No.36 ~ 41(C/H) (전력선 신설 및 공중이동) - 154kV 왕신-남포항T/L ST ~ No.1(전력선 공중이동) - 154kV 왕신-남포항T/L No.37 철탑보강 - ACSR/AW 410㎟×2B×2C – 1.238km","2023-06-01 08:00","2023-06-28 18:00","2023-06-07 08:00","2023-07-04 18:00","연속"]
[477,"대구","포항","상정양북 T/L","양북변전소 등 3개소 외벽마감재 교체공사","(안전확보)양북변전소 등 3개소 외벽마감재 교체공사","2023-06-08 09:00","2023-06-19 18:00","취소","취소","매일"]
[478,"대구","포항","울주외동#2 T/L","2022~23년 포항전력지사 변전총액공사","외동S/S 627 GIS 조작시험","2023-06-08 14:00","2023-06-08 18:00","2023-06-08 14:00","2023-06-08 18:00","연속"]
[479,"대구","포항","옥동외동#1 T/L","2022~23년 포항전력지사 변전총액공사","외동S/S 687 GIS 조작시험","2023-06-07 09:00","2023-06-07 14:00","2023-06-07 09:00","2023-06-07 14:00","연속"]
[480,"대구","포항","옥동외동#2 T/L","2022~23년 포항전력지사 변전총액공사","외동S/S 657 GIS 조작시험","2023-06-07 14:00","2023-06-07 18:00","2023-06-07 14:00","2023-06-07 18:00","연속"]
[481,"대구","포항","울주외동#1 T/L","2022~23년 포항전력지사 변전총액공사","외동S/S 617 GIS 조작시험","2023-06-08 09:00","2023-06-08 14:00","2023-06-08 09:00","2023-06-08 14:00","연속"]
[482,"경북","구미","구미광평#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- GIS 보통점검","2023-06-19 14:00","2023-06-19 18:00","2023-06-19 14:00","2023-06-19 18:00","연속"]
[483,"경북","구미","구미광평#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- GIS 보통점검","2023-06-19 09:00","2023-06-19 14:00","2023-06-19 09:00","2023-06-19 14:00","연속"]
[484,"경북","구미","선산청리#1 T/L","154kV 선산-청리T/L 임시이설공사","○ 154kV 선산-청리T/L 임시이설공사\n- 6기 설치(신설8~9호, 임시1~4호) 및 5기 철거(기설 8호~12호)","2023-06-12 09:00","2023-06-28 18:00","2023-06-12 09:00","2023-06-28 18:00","연속"]
[485,"경북","구미","선산청리#2 T/L","154kV 선산-청리T/L 임시이설공사","○ 154kV 선산-청리T/L 임시이설공사\n- 6기 설치(신설8~9호, 임시1~4호) 및 5기 철거(기설 8호~12호)","2023-06-12 09:00","2023-06-28 18:00","2023-06-12 09:00","2023-06-28 18:00","연속"]
[486,"경북","영주","예천점촌#1 T/L","2022-23년 영주전력지사 가공송전정비 협력회사 총액공사","ㅇ 154kV 예천-점촌#1T/L 수평추락방지장치 설치(95기) ㅇ 154kV 신영주-예천#1T/L 수평추락방지장치 설치(병가9기, 63-71호)","2023-06-03 09:00","2023-06-04 18:00","2023-06-03 09:00","2023-06-04 18:00","매일"]
[487,"경북","영주","예천점촌#1 T/L","2022-23년 영주전력지사 가공송전정비 협력회사 총액공사","ㅇ 154kV 예천-점촌#1T/L 수평추락방지장치 설치(95기)","2023-06-10 09:00","2023-06-11 18:00","2023-06-17 09:00","2023-06-18 18:00","매일"]
[488,"경북","영주","예천점촌#2 T/L","2022-23년 영주전력지사 가공송전정비 협력회사 총액공사","ㅇ 154kV 예천-점촌#2T/L 수평추락방지장치 설치(95기) ㅇ 154kV 신영주-예천#2T/L 수평추락방지장치 설치(병가9기, 63-71호)","2023-06-17 09:00","2023-06-18 18:00","2023-06-10 09:00","2023-06-11 18:00","매일"]
[489,"경북","영주","예천점촌#2 T/L","2022-23년 영주전력지사 가공송전정비 협력회사 총액공사","ㅇ 154kV 예천-점촌#2T/L 수평추락방지장치 설치(95기)","2023-06-24 09:00","2023-06-25 18:00","2023-06-24 09:00","2023-06-25 18:00","매일"]
[490,"경북","영주","점촌문경 T/L","2022-23년 영주전력지사 가공송전정비 협력회사 총액공사","ㅇ 154kV 예천-점촌#2T/L 수평추락방지장치 설치 * 72-104호(33기, 2조4회선) 점촌-단양 병가휴전","2023-06-24 09:00","2023-06-25 18:00","2023-06-24 09:00","2023-06-25 18:00","매일"]
[491,"경북","영주","동상주점촌#1 T/L","2022-23년 영주전력지사 가공송전정비 협력회사 총액공사","ㅇ 154kV 예천-점촌#1T/L 수평추락방지장치 설치 * 예점105호, 동상주-점촌2호 병가로 인한 휴전","2023-06-04 09:00","2023-06-04 18:00","2023-06-04 09:00","2023-06-04 18:00","연속"]
[492,"경북","영주","점촌단양 T/L","2022-23년 영주전력지사 가공송전정비 협력회사 총액공사","ㅇ 154kV 예천-점촌#1T/L 수평추락방지장치 설치 * 72-104호(33기, 2조4회선) 점촌-단양 병가휴전","2023-06-10 09:00","2023-06-11 18:00","2023-06-17 09:00","2023-06-18 18:00","매일"]
[493,"경북","영주","동상주점촌#2 T/L","2022-23년 영주전력지사 가공송전정비 협력회사 총액공사","ㅇ 154kV 예천-점촌#2T/L 수평추락방지장치 설치 * 예점105호, 동상주-점촌2호 병가로 인한 휴전","2023-06-18 09:00","2023-06-18 18:00","2023-06-11 09:00","2023-06-11 18:00","연속"]
[494,"경북","영주","신영주예천#2 T/L","2022-23년 영주전력지사 가공송전정비 협력회사 총액공사","154kV 신영주-예천#2T/L 수평추락방지장치 설치(70기)","2023-06-10 09:00","2023-06-20 18:00","2023-06-10 09:00","2023-06-20 18:00","매일"]
[495,"경북","직할","안동안동HP T/L","2023년 경북직할 가공송전 위탁공사","154kV 안동-안동HPT/L 정밀점검 No.1~12","2023-06-22 09:00","2023-06-23 18:00","취소","취소","매일"]
[496,"경북","직할","울진삼척GP#1 T/L","울진S/S 장기사용 GIS 교체공사","울진S/S 장기사용 GIS 교체공사(4차수) - #2BUS END COVER 처리 후 무부하 가압","2023-06-28 09:00","2023-06-29 18:00","2023-06-28 09:00","2023-06-29 18:00","연속"]
[497,"경북","직할","울진삼척GP#1 T/L","울진S/S 장기사용 GIS 교체공사","65BUS 무부하 가압용 (2DS부)","2023-06-21 09:00","2023-06-22 18:00","2023-06-21 09:00","2023-06-22 18:00","연속"]
[498,"경북","직할","울진삼척GP#1 T/L","울진S/S 장기사용 GIS 교체공사","60BUS 무부하 가압용","2023-06-14 09:00","2023-06-15 18:00","2023-06-14 09:00","2023-06-15 18:00","연속"]
[499,"경북","직할","울진삼척GP#1 T/L","울진S/S 장기사용 GIS 교체공사","65BUS 무부하 가압용","2023-06-01 09:00","2023-06-02 18:00","2023-06-01 09:00","2023-06-02 18:00","연속"]
[500,"경북","직할","울진현종산풍력 T/L","울진S/S 장기사용 GIS 교체공사","울진S/S 장기사용 GIS 교체공사_4차수","2023-06-26 09:00","2023-07-19 18:00","2023-06-26 09:00","2023-07-19 18:00","연속"]
[501,"경북","직할","영덕진보#2 T/L","154kV 동안동-진보 T/L 증설공사","154kV GIS 설치(무부하가압)","2023-06-22 10:00","2023-06-30 14:00","2023-06-26 10:00","2023-06-27 14:00","연속"]
[502,"경북","직할","영덕진보#1 T/L","154kV 동안동-진보 T/L 증설공사","154kV GIS 설치(무부하가압)","2023-06-14 10:00","2023-06-15 14:00","2023-06-14 10:00","2023-06-15 14:00","연속"]
[503,"경북","직할","안동풍산 T/L","2023년 경북직할 가공송전 위탁공사","154kV 안동-풍산T/L 정밀점검 No.1~100","2023-06-22 09:00","2023-06-30 18:00","취소","취소","연속"]
[504,"경북","직할","현종산풍력평해#2 T/L","22-23년 경북직할 송전협력회사 총액공사","154kV 현종산풍력-평해T/L 수평 추락방지장치 설치 No.14~87","2023-06-15 08:00","2023-06-27 18:00","2023-06-15 08:00","2023-06-27 18:00","매일"]
[505,"부산울산","동부산","신양산구서#1 T/L","154kV 구서S/S 장기사용 GIS 교체공사","○ 무부하 시험가압(1Hr)","2023-06-06 17:00","2023-06-06 18:00","취소","취소","연속"]
[506,"부산울산","동부산","노포정관#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-06-12 08:00","2023-06-16 18:00","2023-06-12 08:00","2023-06-16 18:00","연속"]
[507,"부산울산","동부산","구서노포#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","추락방지장치 및 피뢰기 설치","2023-06-12 08:00","2023-06-16 18:00","2023-06-12 08:00","2023-06-16 18:00","연속"]
[508,"부산울산","동부산","구서노포#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-06-19 08:00","2023-06-23 18:00","2023-06-19 08:00","2023-06-23 18:00","연속"]
[509,"부산울산","동부산","노포정관#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-06-19 08:00","2023-06-23 18:00","2023-06-19 08:00","2023-06-23 18:00","연속"]
[510,"부산울산","동부산","명례장안 T/L","22~23년 동부산전력지사 가공송전협력회사 총액공사","추락방지(수평레일) 설치","2023-06-02 08:00","2023-06-02 18:00","취소","취소","연속"]
[511,"부산울산","동부산","명례고리NP T/L","22~23년 동부산전력지사 가공송전협력회사 총액공사","추락방지(수평레일) 설치","2023-06-01 08:00","2023-06-01 18:00","취소","취소","연속"]
[512,"부산울산","동부산","장안고리NP T/L","22~23년 동부산전력지사 가공송전협력회사 총액공사","추락방지(수평레일) 설치","2023-06-05 08:00","2023-06-05 18:00","취소","취소","연속"]
[513,"부산울산","북부산","학장개금#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","개금S/S 154kV 학장-개금#2T/L GIS 정밀점검","2023-06-05 08:00","2023-06-06 18:00","2023-06-05 08:00","2023-06-06 18:00","연속"]
[514,"부산울산","북부산","학장개금#1 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","개금S/S 154kV 학장-개금#1T/L GIS 정밀점검","2023-06-01 08:00","2023-06-02 18:00","2023-06-01 08:00","2023-06-02 18:00","연속"]
[515,"부산울산","북부산","북부산구포#2 T/L","구포S/S 154kV 장기사용 GIS 대체공사(4차)","구포S/S 154kV 장기사용 GIS 대체공사(4차)_#2BUS 종커버 시험가압","2023-06-15 19:00","2023-06-15 20:00","2023-06-16 19:00","2023-06-16 20:00","연속"]
[516,"부산울산","북부산","구포S/S #2 BUS","구포S/S 154kV 장기사용 GIS 대체공사(4차)","구포S/S 154kV 장기사용 GIS 대체공사(4차)","2023-06-12 09:00","2023-06-15 20:00","2023-06-15 13:00","2023-06-16 20:00","연속"]
[517,"부산울산","북부산","구포대저#2 T/L","구포S/S 154kV 장기사용 GIS 대체공사(4차)","구포S/S 154kV 장기사용 GIS 대체공사(4차)","2023-06-07 08:30","2023-07-07 18:00","2023-06-12 08:30","2023-07-14 18:00","연속"]
[518,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV 장기사용 GIS대체공사(3차)","구포S/S 154kV 장기사용 GIS대체공사(3차)","2023-06-01 16:00","2023-06-01 18:00","2023-06-01 16:00","2023-06-01 18:00","연속"]
[519,"부산울산","북부산","구포대저#2 T/L","구포S/S 154kV 장기사용 GIS 대체공사(3차)","구포S/S 154kV 장기사용 GIS 대체공사(3차)_시험가압","2023-06-03 10:30","2023-06-04 10:30","2023-06-03 10:30","2023-06-04 10:30","연속"]
[520,"부산울산","북부산","구포대저#2 T/L","구포S/S 154kV 장기사용 GIS 대체공사(3차)","구포S/S 154kV 장기사용 GIS 대체공사(3차)_시험가압","2023-06-01 10:30","2023-06-02 10:30","2023-06-01 10:30","2023-06-02 10:30","연속"]
[521,"부산울산","북부산","구포S/S #2 BUS","구포S/S 154kV 장기사용 GIS 대체공사(4차)","구포S/S 154kV 장기사용 GIS 대체공사(4차)","2023-06-24 09:00","2023-07-02 12:00","2023-06-27 09:00","2023-07-03 13:00","연속"]
[522,"부산울산","북부산","북부산구포#2 T/L","구포S/S 154kV 장기사용 GIS 대체공사(4차)","구포S/S 154kV 장기사용 GIS 대체공사(4차)_#1BUS 시험가압","2023-06-22 18:00","2023-06-23 18:00","2023-06-25 18:00","2023-06-26 18:00","연속"]
[523,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV 장기사용 GIS 대체공사(4차)","구포S/S 154kV 장기사용 GIS 대체공사(4차)","2023-06-16 09:00","2023-06-23 18:00","2023-06-19 09:00","2023-06-26 18:00","연속"]
[524,"부산울산","북부산","모라엄궁#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 모라-엄궁#2T/L GIS 정밀점검","2023-06-26 08:00","2023-06-28 18:00","2023-06-26 08:00","2023-06-28 18:00","연속"]
[525,"부산울산","북부산","모라S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 모라-엄궁#2T/L GIS 정밀점검 휴전설비 : #1BUS","2023-06-26 08:00","2023-06-26 18:00","2023-06-26 08:00","2023-06-26 18:00","연속"]
[526,"부산울산","북부산","모라S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 모라-엄궁#2T/L GIS 정밀점검 휴전설비 : #2BUS","2023-06-27 08:00","2023-06-28 18:00","2023-06-27 08:00","2023-06-28 18:00","연속"]
[527,"부산울산","북부산","모라S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 모라-엄궁#1T/L GIS 정밀점검 휴전설비 : #2BUS","2023-06-22 08:00","2023-06-23 18:00","2023-06-22 08:00","2023-06-23 18:00","연속"]
[528,"부산울산","북부산","모라엄궁#1 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 모라-엄궁#1T/L GIS 정밀점검","2023-06-21 08:00","2023-06-23 18:00","2023-06-21 08:00","2023-06-23 18:00","연속"]
[529,"부산울산","북부산","모라S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 모라-엄궁#1T/L GIS 정밀점검 휴전설비 : #1BUS","2023-06-21 08:00","2023-06-21 18:00","2023-06-21 08:00","2023-06-21 18:00","연속"]
[530,"부산울산","북부산","호포물금 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","물금S/S 154kV 호포-물금T/L GIS 정밀점검","2023-06-07 08:00","2023-06-09 18:00","2023-06-07 08:00","2023-06-09 18:00","연속"]
[531,"부산울산","북부산","물금삼랑진PP#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","물금S/S 154kV 물금-삼랑진PP#2T/L GIS 정밀점검","2023-06-19 08:00","2023-06-20 18:00","2023-06-19 08:00","2023-06-20 18:00","연속"]
[532,"부산울산","북부산","물금삼랑진PP#1 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","물금S/S 154kV 물금-삼랑진PP#1T/L GIS 정밀점검","2023-06-14 08:00","2023-06-16 18:00","2023-06-14 08:00","2023-06-16 18:00","연속"]
[533,"부산울산","북부산","북부산물금 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","물금S/S 154kV 북부산-물금T/L GIS 정밀점검","2023-06-12 08:00","2023-06-13 18:00","2023-06-12 08:00","2023-06-13 18:00","연속"]
[534,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 북부산-삼랑진T/L 1~46호 수평 추락방지장치 설치(2회선 철탑 12기, 4회선 철탑 33기)","2023-06-17 08:30","2023-06-18 18:00","취소","취소","연속"]
[535,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치설치 안전확보","154kV 북부산-삼랑진T/L 1~46호 수평 추락방지장치 설치 4회선 병가구간 안전확보(2회선 철탑 12기, 4회선 철탑 33기)","2023-06-03 08:30","2023-06-04 18:00","취소","취소","연속"]
[536,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치설치 안전확보","154kV 북부산-삼랑진T/L 1~46호 수평 추락방지장치 설치 4회선 구간 안전확보(2회선 철탑 12기, 4회선 철탑 33기)","2023-06-17 08:30","2023-06-18 18:00","취소","취소","연속"]
[537,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치설치 안전확보","154kV 북부산-삼랑진T/L 1~46호 수평 추락방지장치 설치 4회선 구간 안전확보(2회선 철탑 12기, 4회선 철탑 33기)","2023-06-10 08:30","2023-06-11 18:00","취소","취소","연속"]
[538,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 북부산-삼랑진T/L 1~46호 수평 추락방지장치 설치(2회선 철탑 12기, 4회선 철탑 33기)","2023-06-10 08:30","2023-06-11 18:00","취소","취소","연속"]
[539,"부산울산","북부산","북부산구포#3 T/L","22-23년 북부산전력지사 변전총액공사","북부산S/S 154kV 북부산-구포#3T/L 보통점검","2023-06-05 09:00","2023-06-05 18:00","2023-06-05 09:00","2023-06-05 18:00","연속"]
[540,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 북부산-삼랑진T/L 1~46호 수평 추락방지장치 설치(2회선 철탑 12기, 4회선 철탑 33기)","2023-06-03 08:30","2023-06-04 18:00","취소","취소","연속"]
[541,"부산울산","북부산","언양산막#1 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 언양-산막T/L 36~66호 수평 추락방지장치 설치(30기)","2023-06-19 08:30","2023-06-23 18:00","2023-06-19 08:30","2023-06-23 18:00","연속"]
[542,"부산울산","북부산","언양산막#2 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 언양-산막T/L 36~66호 수평 추락방지장치 설치(30기)","2023-06-12 08:30","2023-06-16 18:00","2023-06-12 08:30","2023-06-16 18:00","연속"]
[543,"부산울산","북부산","양산산막#2 T/L","154kV 양산-산막T/L 2호 지장철탑 이설공사","154kV 양산-산막T/L 지장철탑 이설공사 본선로 구성 ○ 공사구간 : 154kV 양산-산막T/L 1~3호 ○ 작업내용 : #2T/L 전력선 연·긴선, OPGW 이설, 인수점검","2023-06-12 07:00","2023-06-16 18:00","2023-06-12 07:00","2023-06-16 18:00","연속"]
[544,"부산울산","북부산","양산산막#1 T/L","154kV 양산-산막T/L 2호 지장철탑 이설공사","154kV 양산-산막T/L 지장철탑 이설공사 본선로 구성 ○ 공사구간 : 154kV 양산-산막T/L 1~3호 ○ 작업내용 : #1T/L 전력선 연·긴선, OPGW 이설, 인수점검","2023-06-05 07:00","2023-06-09 18:00","2023-06-05 07:00","2023-06-09 18:00","연속"]
[545,"부산울산","북부산","서부산엄궁#1 T/L","22-23년 북부산전력지사 변전총액공사","엄궁S/S 154kV 서부산-엄궁1T/L 차단기 조작시험","2023-06-15 09:00","2023-06-15 18:00","2023-06-15 09:00","2023-06-15 18:00","연속"]
[546,"부산울산","북부산","서부산엄궁#2 T/L","22-23년 북부산전력지사 변전총액공사","엄궁S/S 154kV 서부산-엄궁2T/L 차단기 조작시험","2023-06-16 09:00","2023-06-16 18:00","2023-06-16 09:00","2023-06-16 18:00","연속"]
[547,"부산울산","북부산","호포매리#1 T/L","154kV 호포-매리T/L OPGW 증설공사","1. OPGW 교체(24C→48C) : 7.9km 2. 비금속광케이블 시설 : 3km","2023-06-23 09:00","2023-07-01 18:00","2023-06-23 09:00","2023-07-01 18:00","연속"]
[548,"부산울산","서부산","서부산S/S 부산#3ST CB","서부산S/S 154kV #3 S/T GIS 점검","부산발전본부 #3CC 수세정에 따른 병행작업 - 서부산S/S 154kV #3 S/T GIS 점검","2023-06-12 09:00","2023-06-13 18:00","2023-06-12 09:00","2023-06-13 18:00","연속"]
[549,"부산울산","서부산","서부산S/S #60 BUS","154kV GIS 정밀점검 - #1BUS-TIE","154kV GIS 정밀점검 - #1BUS-TIE 시험가압 모선휴전","2023-06-02 15:00","2023-06-02 18:00","2023-06-02 15:00","2023-06-02 18:00","연속"]
[550,"부산울산","서부산","서부산S/S CB 6100","154kV GIS 정밀점검 - #1BUS-TIE","154kV GIS 정밀점검 - #1BUS-TIE","2023-06-01 10:00","2023-06-02 18:00","2023-06-01 10:00","2023-06-02 18:00","연속"]
[551,"부산울산","서부산","서부산S/S SEC CB 60610","154kV GIS 정밀점검 - #1BUS-TIE","154kV GIS 정밀점검 - #1BUS-TIE 시험가압 모선휴전","2023-06-02 15:00","2023-06-02 18:00","2023-06-02 15:00","2023-06-02 18:00","연속"]
[552,"부산울산","울산","남울산용연#2 T/L","154kV 추락방지장치 설치공사","- 수평 추락방지장치 설치 1, 2, 3[3기]","2023-06-01 07:30","2023-06-02 18:00","2023-06-01 07:30","2023-06-02 18:00","연속"]
[553,"부산울산","울산","남울산신온산#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-06-19 07:00","2023-06-23 18:00","2023-06-19 07:00","2023-06-23 18:00","연속"]
[554,"부산울산","울산","남울산처용#2 T/L","154kV 추락방지장치 설치공사","ㅇ 추락방지장치 설치 - 수평10, 수직1(관형수직수평1 포함)","2023-06-26 07:30","2023-06-28 18:00","2023-06-26 07:30","2023-06-28 18:00","연속"]
[555,"부산울산","울산","남울산처용#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-06-15 07:00","2023-06-16 18:00","2023-06-15 07:00","2023-06-16 18:00","연속"]
[556,"부산울산","울산","남울산신온산#2 T/L","345kV 남울산S/S 울산GPS 신규수용공사","362kV 63kA 6,300A GIS x 3CB 설치(7472,7200,7272)","2023-06-12 09:00","2023-06-13 18:00","취소","취소","연속"]
[557,"부산울산","울산","산하효문#1 T/L","154kV 추락방지장치 설치공사","ㅇ 추락방지장치 설치 - 11 12 13 20 24 25 26 27 28 29 30 31 32 수평(13기)","2023-06-13 07:30","2023-06-16 18:00","2023-06-13 07:30","2023-06-16 18:00","연속"]
[558,"부산울산","울산","산하방어진#1 T/L","154kV 추락방지장치 설치공사","ㅇ 추락방지장치 설치 - 10 ~ 32호 수평","2023-06-19 07:30","2023-06-23 18:00","2023-06-19 07:30","2023-06-23 18:00","연속"]
[559,"부산울산","울산","성암울산TP#2 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-06-13 07:00","2023-06-14 18:00","2023-06-13 07:00","2023-06-14 18:00","연속"]
[560,"부산울산","울산","성암울산TP#1 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-06-05 07:00","2023-06-06 18:00","2023-06-05 07:00","2023-06-06 18:00","연속"]
[561,"부산울산","울산","신온산온산#3 T/L","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검 - 692DS 누기보수 - 디지털축소형모자익 제어케이블 이설","2023-06-25 09:00","2023-06-27 18:00","2023-06-25 09:00","2023-06-27 18:00","연속"]
[562,"부산울산","울산","신울산명례#2 T/L","22~23년 동부산전력지사 가공송전협력회사 총액공사","폴리머지지애자 설치 및 추락방지(수평) 설치","2023-06-22 08:00","2023-06-23 18:00","2023-06-22 08:00","2023-06-23 18:00","연속"]
[563,"부산울산","울산","신울산명례#1 T/L","22~23년 동부산전력지사 가공송전협력회사 총액공사","폴리머지지애자 설치 및 추락방지(수평) 설치","2023-06-21 08:00","2023-06-21 18:00","2023-06-21 08:00","2023-06-21 18:00","연속"]
[564,"부산울산","울산","신울산S/S CB 6200","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-06-19 09:00","2023-06-19 18:00","2023-06-19 09:00","2023-06-19 18:00","연속"]
[565,"부산울산","울산","신울산S/S CB 6100","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-06-12 09:00","2023-06-12 18:00","2023-06-12 09:00","2023-06-12 18:00","연속"]
[566,"부산울산","울산","신울산S/S SEC CB 60610","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[567,"부산울산","울산","신울산S/S #66G BUS","신울산S/S 154kV 현대화공사","#5M.Tr 2차 C/H 시험가압","2023-06-02 14:00","2023-06-03 14:00","2023-06-02 14:00","2023-06-03 14:00","연속"]
[568,"부산울산","울산","신울산S/S SEC CB 65660","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[569,"부산울산","울산","온산처용#2 T/L","154kV 추락방지장치 설치공사","ㅇ 추락방지장치 설치 - 수평10기","2023-06-29 07:30","2023-06-30 18:00","2023-06-29 07:30","2023-06-30 18:00","연속"]
[570,"부산울산","울산","용연울산TP#3 T/L","345kV 동울산-월성NP등 6개T/L 추락방지장치 설치공사","추락방지장치 설치","2023-06-12 07:00","2023-06-12 18:00","2023-06-12 07:00","2023-06-12 18:00","연속"]
[571,"부산울산","울산","용연울산TP#2 T/L","22~23년 변전협력회사 총액공사","- 용연측 피뢰기 보통점검 - 화력측 가공지선 철거관련 안전이격 - 화력측 애자 코팅","2023-06-08 09:00","2023-06-08 18:00","2023-06-08 09:00","2023-06-08 18:00","연속"]
[572,"부산울산","울산","용연울산TP#1 T/L","22~23년 변전협력회사 총액공사","- 화력측 애자 코팅","2023-06-07 09:00","2023-06-07 18:00","2023-06-07 09:00","2023-06-07 18:00","연속"]
[573,"부산울산","울산","신울산웅촌#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-06-08 08:00","2023-06-08 18:00","2023-06-08 08:00","2023-06-08 18:00","연속"]
[574,"부산울산","울산","웅촌서창#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-06-08 08:00","2023-06-09 18:00","취소","취소","연속"]
[575,"부산울산","울산","웅촌서창#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-06-05 08:00","2023-06-07 18:00","취소","취소","연속"]
[576,"부산울산","울산","신울산웅촌#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-06-05 08:00","2023-06-05 18:00","2023-06-05 08:00","2023-06-05 18:00","연속"]
[577,"부산울산","울산","직동반천#1 T/L","22~23년 동부산전력지사 가공송전협력회사 총액공사","추락방지(수평) 설치","2023-06-08 08:00","2023-06-08 18:00","2023-06-08 08:00","2023-06-08 18:00","연속"]
[578,"부산울산","울산","직동반천#2 T/L","22~23년 동부산전력지사 가공송전협력회사 총액공사","추락방지(수평) 설치","2023-06-09 08:00","2023-06-09 18:00","2023-06-09 08:00","2023-06-09 18:00","연속"]
[579,"부산울산","직할","정보대연 T/L","345kV 신양산-신대연 등 7개T/L 자기애관교체공사","자기애관을 폴리머애관으로 교체","2023-06-12 09:00","2023-06-21 18:00","2023-06-12 09:00","2023-06-21 18:00","연속"]
[580,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV 장기사용 GIS 대체공사(3차)","구포S/S 154kV 장기사용 GIS 대체공사(3차)","2023-06-02 12:00","2023-06-04 18:00","2023-06-02 12:00","2023-06-04 18:00","연속"]
[581,"부산울산","북부산","구포S/S #2 BUS","구포S/S 154kV 장기사용 GIS 대체공사(3차)","구포S/S 154kV 장기사용 GIS 대체공사(3차)","2023-06-09 09:00","2023-06-09 11:00","2023-06-09 09:00","2023-06-09 11:00","연속"]
[582,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV 장기사용 GIS 대체공사(3차)","구포S/S 154kV 장기사용 GIS 대체공사(3차)","2023-06-09 11:00","2023-06-09 14:00","2023-06-09 11:00","2023-06-09 14:00","연속"]
[583,"경남","직할","신김해주촌#1 T/L","OPGW 금구류 정비 공사","OPGW 금구류 취약개소 정비","2023-06-02 07:00","2023-06-02 18:00","2023-06-02 07:00","2023-06-02 18:00","연속"]
[584,"경남","직할","주촌삼계#2 T/L","주촌S/S 주촌-삼계#2T/L 627 GIS 보통점검","주촌S/S 주촌-삼계#2T/L 627 GIS 보통점검","2023-06-27 09:30","2023-06-27 18:00","2023-06-27 09:30","2023-06-27 18:00","연속"]
[585,"경남","직할","신김해주촌#2 T/L","2022-2023년 경남 직할 가공송전협력회사 총액공사","154kV 신김해-주촌T/L 1~37호 구간 수평 추락방지장치 설치","2023-06-07 07:00","2023-06-16 18:00","2023-06-16 07:00","2023-06-26 18:00","매일"]
[586,"경남","직할","주촌삼계#1 T/L","2022-2023년 경남 직할 가공송전협력회사 총액공사","154kV 주촌-삼계T/L 1~30, 38호 구간 수평 추락방지장치 설치","2023-06-09 07:00","2023-06-16 18:00","2023-06-20 07:00","2023-06-26 18:00","매일"]
[587,"경남","직할","진례진영#1 T/L","진례S/S 진례-진영#1T/L 667 GIS 하자점검","진례S/S 진례-진영#1T/L 667 GIS 하자점검","2023-06-20 09:30","2023-06-20 18:00","2023-06-20 09:30","2023-06-20 18:00","연속"]
[588,"경남","직할","신김해진례#1 T/L","진례S/S 신김해-진례#1T/L 637 하자점검","진례S/S 신김해-진례#1T/L 637 하자점검 (병행)신김해S/S 신김해-진례#1T/L 617 조작시험","2023-06-05 09:30","2023-06-05 18:00","2023-06-05 09:30","2023-06-05 18:00","연속"]
[589,"경남","직할","신김해진례#2 T/L","진례S/S 신김해-진례#2T/L 657 GIS 하자점검","진례S/S 신김해-진례#2T/L 657 GIS 하자점검 (병행)신김해S/S 신김해-진례#1T/L 627 조작시험","2023-06-16 09:30","2023-06-16 18:00","2023-06-15 09:30","2023-06-15 18:00","연속"]
[590,"경남","직할","천선진해#1 T/L","154kV 천선-진해#1T/L 송전선로 정밀점검","154kV 천선-진해#1T/L 송전선로 정밀점검","2023-06-05 08:00","2023-06-07 18:00","2023-06-05 08:00","2023-06-07 18:00","매일"]
[591,"경남","직할","천선진해#2 T/L","송전선로 정밀점검 안전작업거리 확보","154kV 천선-진해#1T/L 송전선로 정밀점검 안전작업거리 확보","2023-06-06 08:00","2023-06-06 18:00","2023-06-06 08:00","2023-06-06 18:00","연속"]
[592,"경남","진주","하동남해#2 T/L","154kV 하동-남해T/L 가공송전선로 정밀점검","154kV 하동-남해T/L 가공송전선로 정밀점검(60~113호, 53기)","2023-06-26 08:30","2023-06-30 18:00","2023-06-26 08:30","2023-06-30 18:00","매일"]
[593,"경남","진주","사봉개양#1 T/L","154kV 사봉-개양T/L 정밀점검(1~56호)","154kV 사봉-개양T/L 정밀점검(1~56호)","2023-06-17 09:00","2023-06-18 18:00","취소","취소","매일"]
[594,"경남","진주","사봉개양#1 T/L","154kV 사봉-개양T/L 정밀점검(1~56호)","154kV 사봉-개양T/L 정밀점검(1~56호)","2023-06-24 09:00","2023-06-25 18:00","취소","취소","매일"]
[595,"경남","진주","의령산청 T/L","154kV 의령-산천T/L 가공송전선로 정밀점검","154kV 의령-산청T/L 가공송전선로 정밀점검","2023-06-19 09:00","2023-06-23 18:00","2023-06-19 09:00","2023-06-23 18:00","매일"]
[596,"경남","진주","산청함양 T/L","154kV 의령-함양T/L 가공송전선로 정밀점검","154kV 의령-함양T/L 가공송전선로 정밀점검","2023-06-12 09:00","2023-06-16 18:00","2023-06-12 09:00","2023-06-16 18:00","매일"]
[597,"경남","진주","의령S/S CB 6100","의령S/S 6100,6200 GIS 조작시험","의령S/S 6100,6200 GIS 조작시험","2023-06-07 10:00","2023-06-07 13:00","2023-06-07 10:00","2023-06-07 13:00","연속"]
[598,"경남","진주","동진주진주#2 T/L","진주S/S 154lkV 옥외철구 설비 GIS화 공사관련 안전이격거리 확보","송전선로 GIS화 이설관련 안전이격거리 확보","2023-06-03 08:00","2023-06-03 18:00","2023-06-11 08:00","2023-06-11 18:00","연속"]
[599,"경남","진주","동진주진주#2 T/L","진주S/S 154lkV 옥외철구 설비 GIS화 공사관련 안전이격거리 확보","송전선로 GIS화 이설관련 안전이격거리 확보","2023-06-03 08:00","2023-06-18 16:00","2023-06-15 07:00","2023-06-17 16:00","매일"]
[600,"경남","진주","진주개양#2 T/L","진주S/S 옥외철구 설비 GIS화 공사 관련 안전이격거리 확보","송전선로 GIS화 이설관련 안전이격거리 확보","2023-06-19 08:00","2023-07-02 16:00","2023-06-29 07:00","2023-07-01 16:00","매일"]
[601,"경남","진주","산청함양 T/L","154kV 거창-합천 등 14개 T/L 수평 추락방지시설 설치","1. 154kV 산청-함양SA T/L 철탑 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : 산청분기 No.1~17(17기), 산청-함양SA T/L No.64~132(69기) - 평일작업","2023-06-26 07:00","2023-06-30 18:00","2023-06-26 07:00","2023-06-30 18:00","매일"]
[602,"경남","진주","쌍림합천#2 T/L","합천S/S 쌍림-합천#2T/L GIS 보통점검 및 LA,PT대체","[병행] 쌍림S/S 쌍림-합천#2T/L GIS 보통점검","2023-06-08 09:00","2023-06-08 18:00","2023-06-11 09:00","2023-06-11 18:00","연속"]
[603,"경남","통영","신고성거제#2 T/L","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","154kV 진동-안정#2T/L 추락방지장치 설치공사 안전작업거리 확보","2023-06-17 07:00","2023-06-18 18:00","2023-06-17 07:00","2023-06-18 18:00","매일"]
[604,"경남","통영","신고성통영 T/L","신고성S/S 154kV신고성-통영T/L GIS 정밀점검","신고성S/S 154kV신고성-통영T/L GIS 정밀점검 신고성S/S 154kV신고성-통영T/L GIS CB Airing v/v 교체 신고성S/S 154kV신고성-통영T/L LA, CVT 보통점검","2023-06-17 09:30","2023-06-18 18:00","2023-06-17 09:30","2023-06-18 18:00","연속"]
[605,"경남","통영","신고성삼천포#1 T/L","신고성S/S 154kV신고성-삼천포#1T/L GIS 보통점검","신고성S/S 154kV신고성-삼천포#1T/L GIS 보통점검 신고성S/S 154kV신고성-삼천포#1T/L LA, CVT 보통점검 삼천포S/S 154kV신고성-삼천포#1T/L GIS WHWKRTLGJA","2023-06-24 09:30","2023-06-24 18:00","2023-06-24 09:30","2023-06-24 18:00","연속"]
[606,"경남","통영","진동안정#2 T/L","154kV 진동-안정#2T/L 추락방지장치 설치공사","154kV 진동-안정#2T/L 추락방지장치 설치공사","2023-06-12 07:00","2023-06-23 18:00","2023-06-12 07:00","2023-06-23 18:00","매일"]
[607,"경남","함안","매리김해#1 T/L","김해S/S 매리김해#1 T/L GIS 조작시험","김해S/S 매리김해#1 T/L GIS 조작시험","2023-06-02 09:30","2023-06-02 17:30","2023-06-02 09:30","2023-06-02 17:30","연속"]
[608,"경남","함안","김해S/S CB 6100","김해S/S 154kV #1-#2 BUS TIE GIS 조작시험","김해S/S 154kV #1-#2 BUS TIE","2023-06-01 09:30","2023-06-01 17:30","2023-06-01 09:30","2023-06-01 17:30","연속"]
[609,"경남","함안","매리김해#1 T/L","154kV 호포-매리T/L OPGW 증설공사","OPGW 7.92km 및 OFC 2.91km 포설","2023-06-23 07:00","2023-06-25 18:00","2023-06-23 07:00","2023-06-25 18:00","연속"]
[610,"경남","함안","청도밀양#1 T/L","154kV 부북분기T/L 건설공사","154kV 청도-밀양T/L No.76호 철탑 신설(초동-밀양T/L No.35호) 및 전력선 공중이동(#1,2T/L 수직배열에 따른 동시 휴전 필요)","2023-06-06 07:00","2023-06-09 18:00","2023-06-08 07:00","2023-06-13 18:00","연속"]
[611,"경남","함안","초동밀양#1 T/L","154kV 부북분기T/L 건설공사","154kV 청도-밀양T/L No.76호 철탑 신설(초동-밀양T/L No.35호) 및 전력선 공중이동(#1,2T/L 수직배열에 따른 동시 휴전 필요)","2023-06-01 07:00","2023-06-05 18:00","2023-06-01 07:00","2023-06-07 18:00","연속"]
[612,"경남","함안","청도밀양#2 T/L","154kV 부북분기T/L 건설공사","154kV 청도-밀양T/L No.76호 철탑 신설(초동-밀양T/L No.35호) 및 전력선 공중이동(#1,2T/L 수직배열에 따른 동시 휴전 필요)","2023-06-06 07:00","2023-06-09 18:00","2023-06-08 07:00","2023-06-13 18:00","연속"]
[613,"경남","함안","초동밀양#2 T/L","154kV 부북분기T/L 건설공사","154kV 청도-밀양T/L No.76호 철탑 신설(초동-밀양T/L No.35호) 및 전력선 공중이동(#1,2T/L 수직배열에 따른 동시 휴전 필요)","2023-06-01 07:00","2023-06-05 18:00","2023-06-01 07:00","2023-06-07 18:00","연속"]
[614,"경남","함안","서마산진동 T/L","154kV 서마산분기T/L 증설사업","154kV 서마산분기T/L 증설사업","2023-06-27 06:00","2023-07-09 18:00","2023-06-27 06:00","2023-07-09 18:00","연속"]
[615,"경남","함안","수산S/S #60 BUS","154kV 수산S/S #1M.Tr 증설공사(상체크,시험가압)","1. 154kV M.Tr × 1Bank, 154kV GIS × 1CCT, 23kV GIS × 9Bay 설치 2. 전력케이블, 보호배전반 등 기타부대공사 × 1식","2023-06-22 09:00","2023-06-23 18:00","2023-06-22 09:00","2023-06-23 18:00","연속"]
[616,"경남","함안","진영수산#1 T/L","154kV 수산S/S #1M.Tr 증설공사(상체크,시험가압)","1. 154kV M.Tr × 1Bank, 154kV GIS × 1CCT, 23kV GIS × 9Bay 설치 2. 전력케이블, 보호배전반 등 기타부대공사 × 1식","2023-06-22 09:00","2023-06-24 18:00","2023-06-22 09:00","2023-06-24 18:00","연속"]
[617,"경남","함안","수산S/S #65 BUS","154kV 수산S/S #1M.Tr 증설공사(상체크,시험가압)","1. 154kV M.Tr × 1Bank, 154kV GIS × 1CCT, 23kV GIS × 9Bay 설치 2. 전력케이블, 보호배전반 등 기타부대공사 × 1식","2023-06-23 09:00","2023-06-24 18:00","2023-06-23 09:00","2023-06-24 18:00","연속"]
[618,"경남","함안","신마산S/S SEC CB 60610","신마산S/S 154kV #60-#61 SEC GCB 조작시험","신마산S/S 154kV #60-#61 SEC GCB 조작시험","2023-06-12 09:30","2023-06-12 13:30","2023-06-12 09:30","2023-06-12 13:30","연속"]
[619,"경남","함안","신마산S/S CB 6200","신마산S/S 154kV #61-#66 BUS TIE GCB 조작시험","신마산S/S 154kV #61-#66 BUS TIE GCB 조작시험","2023-06-07 13:30","2023-06-07 17:30","2023-06-07 13:30","2023-06-07 17:30","연속"]
[620,"경남","함안","신마산S/S CB 6100","신마산S/S 154kV #60-#65 BUS TIE GCB 조작시험","신마산S/S 154kV #60-#65 BUS TIE GCB 조작시험","2023-06-07 09:30","2023-06-07 13:30","2023-06-07 09:30","2023-06-07 13:30","연속"]
[621,"경남","함안","신마산S/S SEC CB 65660","신마산S/S 154kV #65-#66 SEC GCB 조작시험","신마산S/S 154kV #65-#66 SEC GCB 조작시험","2023-06-12 13:30","2023-06-12 17:30","2023-06-12 13:30","2023-06-12 17:30","연속"]
[622,"경남","함안","진례진영#2 T/L","154kV 진례-진영#2T/L 정밀점검","154kV 진례-진영#2T/L 1호~4호 정밀점검","2023-06-03 13:00","2023-06-03 17:00","2023-06-03 13:00","2023-06-03 17:00","연속"]
[623,"경남","함안","진례진영#1 T/L","154kV 진례-진영#1T/L 정밀점검","154kV 진례-진영#1T/L 1호~4호 정밀점검","2023-06-03 09:00","2023-06-03 13:00","2023-06-03 09:00","2023-06-03 13:00","연속"]
[624,"강원","태백","동해이원#2 T/L","2023년 154kV 이원변전소 외장재 교체공사","외장재 교체공사 시행","2023-06-21 09:00","2023-06-24 18:00","2023-06-21 09:00","2023-06-24 18:00","연속"]
[625,"경기",null,"성현분당#1 T/L","성현S/S 장기사용 154kV GIS 교체공사","성현산성 #3T/L 설치 시 안전이격거리 확보","2023-06-12 09:00","2023-06-15 18:00","2023-06-12 09:00","2023-06-15 18:00","연속"]
[626,"경기",null,"왕암여주#1 T/L","22-23 동부전력지사 송전협력 총액공사","수평 추락방지장치 설치 및 불량애자 교체공사 ","2023-06-01 09:00","2023-06-13 18:00","2023-06-01 09:00","2023-06-13 18:00","연속"]
[627,"경기",null,"왕암여주#2 T/L","22-23 동부전력지사 송전협력 총액공사","수평 추락방지장치 설치 및 불량애자 교체공사 ","2023-06-14 09:00","2023-06-20 18:00","2023-06-14 09:00","2023-06-20 18:00","연속"]
[628,"부산울산","동부산","구서S/S #1 BUS","154kV 구서S/S 장기사용 GIS 교체공사","○ 무부하 시험가압(1Hr)","2023-06-02 18:00","2023-06-02 19:00","2023-06-02 18:00","2023-06-02 19:00","연속"]
[629,"경남","진주","동진주진주#2 T/L","진주S/S 154lkV 옥외철구 설비 GIS화 공사","○미사용 CVT 철거 및 비계설치 안전이격거리 확보\n  (휴전일정 축소를 위한 휴전작업 분리)","2023-06-05 07:00","2023-06-06 18:00","2023-06-05 07:00","2023-06-06 18:00","매일"]
[630,"경남","진주","진주개양#2 T/L","진주S/S 154lkV 옥외철구 설비 GIS화 공사","○미사용 CVT 철거 및 비계설치 안전이격거리 확보\n  (휴전일정 축소를 위한 휴전작업 분리)","2023-06-19 07:00","2023-06-20 18:00","2023-06-19 07:00","2023-06-20 18:00","매일"]