{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":13,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":4,"n_cols":11,"rows_kept":4,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 7월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]

{"sheet":"345설비","index":1,"n_rows":109,"n_cols":11,"rows_kept":109,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2023년도 7월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","시흥","영흥T/P CB 7400","GIS 보통점검","GIS 보통점검","2023-07-03 10:00","2023-07-03 18:00","취소","취소","연속"]
[2,"인천","김포","신김포S/S #1 M.Tr","2차 GIB 접지본드 교체","2차 GIB 접지본드 교체","2023-07-03 10:00","2023-07-03 18:00","2023-07-03 10:00","2023-07-03 18:00","연속"]
[3,"인천","김포","신김포S/S #2 M.Tr","2차 GIB 접지본드 교체","2차 GIB 접지본드 교체","2023-07-04 10:00","2023-07-04 18:00","2023-07-04 10:00","2023-07-04 18:00","연속"]
[4,"인천","부평","신경서S/S #1 Sh.R CB","GIS 정밀점검","GIS 정밀점검","2023-07-04 10:00","2023-07-07 18:00","2023-07-04 10:00","2023-07-07 18:00","연속"]
[5,"경기북부","구리","미금S/S #1 Sh.R CB","2022~23 구리전력 변전협력회사 총액공사","미금S/S 345kV #1Sh.R 초기점검","2023-07-05 09:00","2023-07-05 18:00","취소","취소","연속"]
[6,"경기북부","구리","미금S/S #1 Sh.R CB","2022~23 구리전력 변전협력회사 총액공사","미금S/S 345kV #1Sh.R 초기점검","2023-07-05 09:00","2023-07-05 18:00","취소","취소","연속"]
[7,"경기북부","구리","미금S/S CB 7079","2022~23 구리전력 변전협력회사 총액공사","미금S/S 345kV #1Sh.R 초기점검","2023-07-05 09:00","2023-07-05 18:00","취소","취소","연속"]
[8,"경기북부","직할","신의정부S/S #2 Sh.R CB","'22~23년 직할 변전 협력 총액공사","Sh.R 물청소 및 보통점검시행","2023-07-11 09:00","2023-07-12 18:00","2023-07-11 09:00","2023-07-12 18:00","연속"]
[9,"경기북부","직할","신의정부S/S CB 7700","'22~23년 직할 변전 협력 총액공사","Sh.R 물청소 및 보통점검시행","2023-07-11 09:00","2023-07-12 18:00","2023-07-11 09:00","2023-07-12 18:00","연속"]
[10,"경기북부","직할","신의정부S/S CB 7772","'22~23년 직할 변전 협력 총액공사","Sh.R 물청소 및 보통점검시행","2023-07-11 09:00","2023-07-12 18:00","2023-07-11 09:00","2023-07-12 18:00","연속"]
[11,"경기북부","직할","신의정부S/S #1 Sh.R CB","'22~23년 직할 변전 협력 총액공사","Sh.R 물청소 시행","2023-07-10 09:00","2023-07-10 14:00","2023-07-10 09:00","2023-07-10 14:00","연속"]
[12,"경기북부","직할","신의정부S/S #3 Sh.R CB","'22~23년 직할 변전 협력 총액공사","Sh.R 물청소 시행","2023-07-10 14:00","2023-07-10 18:00","2023-07-10 14:00","2023-07-10 18:00","연속"]
[13,"경기","동부","곤지암여주복합#1 T/L","2022-2023년 성남전력지사 가공송전 협력회사 총액공사","345kV 곤지암-여주복합T/L 53~54호 가공지선 교체","2023-07-04 07:00","2023-07-06 18:00","취소","취소","연속"]
[14,"경기","성남","신안성S/S #6 Sh.R CB","23년 성남전력 170, 362kV GIS 보통점검공사","-GIS 보통점검","2023-07-13 09:00","2023-07-13 18:00","2023-07-13 09:00","2023-07-13 18:00","연속"]
[15,"경기","성남","신안성S/S #7 Sh.R CB","23년 성남전력 170, 362kV GIS 보통점검공사","-GIS 보통점검","2023-07-14 09:00","2023-07-14 18:00","2023-07-14 09:00","2023-07-14 18:00","연속"]
[16,"경기","성남","신안성S/S #5 Sh.R CB","23년 성남전력 170, 362kV GIS 보통점검공사","-GIS 보통점검","2023-07-12 09:00","2023-07-12 18:00","2023-07-12 09:00","2023-07-12 18:00","연속"]
[17,"경기","성남","신용인S/S #1 Sh.R CB","23년 성남전력지사 변전협력회사 총액공사","-Sh.R 하자점검","2023-07-10 09:00","2023-07-10 18:00","2023-07-10 09:00","2023-07-10 18:00","연속"]
[18,"경기","평택","고덕#2S/S #1 M.Tr","345kV 고덕2S/S 건설공사","M.Tr GIB 2차측 과열로 인한 제작사 접지보강공사","2023-07-05 09:00","2023-07-05 18:00","2023-07-05 09:00","2023-07-05 18:00","연속"]
[19,"경기","평택","고덕#2S/S #2 M.Tr","345kV 고덕2S/S 건설공사","M.Tr GIB 2차측 과열로 인한 제작사 접지보강공사","2023-07-06 09:00","2023-07-06 18:00","2023-07-06 09:00","2023-07-06 18:00","연속"]
[20,"경기","평택","고덕#2S/S #3 M.Tr","345kV 고덕2S/S 건설공사","M.Tr GIB 2차측 과열로 인한 제작사 접지보강공사","2023-07-07 09:00","2023-07-07 18:00","2023-07-07 09:00","2023-07-07 18:00","연속"]
[21,"강원","강릉","안인개폐소신양양 T/L","22~23년 강릉전력지사 가공송전협력회사 총액공사","○ 수직, 수평 추락방지장치 설치(345kV 안인개폐소-신양양T/L(No.4~55, 146~193)","2023-07-03 07:00","2023-07-12 18:00","2023-07-03 07:00","2023-07-12 18:00","매일"]
[22,"강원","강릉","안인개폐소양양PP T/L","22~23년 강릉전력지사 가공송전협력회사 총액공사","○ 수평 추락방지장치 설치(345kV 안인개폐소-양양PPT/L(No.4~180)","2023-07-13 07:00","2023-07-31 18:00","2023-07-13 07:00","2023-07-31 18:00","매일"]
[23,"강원","강릉","양양P/P CB 7300","2023년 362kV GIS 정밀점검","7372GIS 정밀점검 시 유도전압 관계로 동시휴전","2023-07-03 09:00","2023-07-07 18:00","2023-07-03 09:00","2023-07-07 18:00","연속"]
[24,"강원","강릉","양양P/P CB 7372","2023년 362kV GIS 정밀점검","362kV GIS 정밀점검(7372)","2023-07-03 09:00","2023-07-07 18:00","2023-07-03 09:00","2023-07-07 18:00","연속"]
[25,"강원","동해","동해S/S #3 M.Tr","동해S/S 345kV 용량부족차단기 대체공사","345kV 76Bay 용량부족차단기 3CB 대체","2023-07-17 09:00","2023-09-27 18:00","취소","취소","연속"]
[26,"강원","동해","동해삼척GP#2 T/L","동해S/S 345kV 용량부족차단기 대체공사","345kV 76Bay 용량부족차단기 3CB 대체","2023-07-17 09:00","2023-09-27 18:00","취소","취소","연속"]
[27,"대전세종충남","대전","신계룡S/S #2 M.Tr","신계룡S/S #2M.Tr 1,2차 LA 초기점검","신계룡S/S #2M.Tr 1,2차 LA 초기점검","2023-07-11 09:00","2023-07-11 18:00","2023-07-11 09:00","2023-07-11 18:00","연속"]
[28,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S 345kV 77Bay BF반 교체 및 결상회로 보완작업","신온양S/S 345kV 77Bay BF반 교체 및 결상회로 보완작업","2023-07-03 09:00","2023-07-07 18:00","취소","취소","연속"]
[29,"대전세종충남","천안","신온양서서울#1 T/L","신온양S/S 345kV 78Bay BF반 교체 및 결상회로 보완작업","신온양S/S 345kV 78Bay BF반 교체 및 결상회로 보완작업","2023-07-10 09:00","2023-07-14 18:00","취소","취소","연속"]
[30,"대전세종충남","천안","신온양신탕정#2 T/L","신온양S/S 345kV 78Bay BF반 교체 및 결상회로 보완작업","신온양S/S 345kV 78Bay BF반 교체 및 결상회로 보완작업","2023-07-10 09:00","2023-07-14 18:00","취소","취소","연속"]
[31,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S 345kV 77Bay BF반 교체 및 결상회로 보완작업","신온양S/S 345kV 77Bay BF반 교체 및 결상회로 보완작업","2023-07-03 09:00","2023-07-07 18:00","취소","취소","연속"]
[32,"대전세종충남","천안","청양신탕정#2 T/L","´22~23년 천안전력지사 송전협력회사 총액공사","- 345kV 청양-신탕정 #2T/L 피뢰기 설치(우기 대비 긴급 시행) - 345kV 청양-신탕정 #2T/L 이도 조정 - 345kV 청양-신탕정 #2T/L 추락방지장치 설치 ※ 주말작업 없음","2023-07-03 08:00","2023-07-14 18:00","2023-07-03 05:30","2023-07-12 16:00","매일"]
[33,"대전세종충남","천안","청양신탕정#1 T/L","345kV 아산-화성 등 15개T/L 추락방지장치 설치공사","345kV 청양-신탕정 #1T/L 수평 추락방지장치 설치 ※ 주말작업 없음","2023-07-17 08:00","2023-07-26 18:00","2023-06-21 05:30","2023-06-30 16:00","매일"]
[34,"대전세종충남","천안","신탕정S/S #2 M.Tr","신탕정S/S 345kV #2M.Tr 부싱관련 배관 누유보수","신탕정S/S 345kV #2M.Tr 부싱관련 배관 누유보수(유사시 30분내 가압가능)","2023-07-12 09:00","2023-07-13 18:00","2023-07-12 09:00","2023-07-13 18:00","연속"]
[35,"대전세종충남","천안","아산S/S #2 M.Tr","아산S/S 345kV #2M.Tr 부싱절연유 채유","아산S/S 345kV #2M.Tr 부싱절연유 채유","2023-07-10 09:00","2023-07-10 18:00","취소","취소","연속"]
[36,"대전세종충남","청양","청양신탕정#1 T/L","(6월취소시)청양P/O 변전협력회사 총액공사","345kV 청양-신탕정#1T/L 보호반 대체 청양-신탕정#1T/L LA 보통점검(A,B,C) 및 PT 보통점검(A,B,C)","2023-07-03 09:00","2023-07-08 18:00","취소","취소","연속"]
[37,"전북","군산","청양군산#2 T/L","군산S/S 345KV 장기사용 GIS 대체공사(일반)","○ 송전선로 보호반 이설(청양-군산#2T/L) ○ 인출송전선로 이설(74Bay →75Bay) ○ LA, CVT 이설(74Bay →75Bay)","2023-07-05 09:00","2023-07-13 18:00","2023-07-05 09:00","2023-07-13 18:00","연속"]
[38,"전북","군산","군산S/S CB 7200","고장파급방지장치반 설치공사","- 군산-신김제1,2T/L 2회선 동시고장 및 호남지역 과전압 대비 SPS 설치 - SPE X 2면 설치","2023-07-21 13:00","2023-07-21 14:30","취소","취소","연속"]
[39,"전북","군산","군산새만금#1 T/L","군산P/O 노후배전반 대체공사","- 군산S/S 78BAY B/F반 대체 - 새만금S/S 72BAY B/F반 대체","2023-07-10 09:00","2023-07-14 18:00","2023-07-10 09:00","2023-07-14 18:00","연속"]
[40,"전북","군산","군산S/S #70 BUS","군산변전소 345KV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2023-07-17 09:00","2023-07-18 18:00","2023-07-17 09:00","2023-07-18 18:00","연속"]
[41,"전북","군산","군산S/S #1 Sh.R CB","고장파급방지장치반 설치공사","- 군산-신김제1,2T/L 2회선 동시고장 및 호남지역 과전압 대비 SPS 설치 - SPE X 2면 설치","2023-07-14 09:00","2023-07-14 11:30","2023-07-14 09:00","2023-07-14 11:30","연속"]
[42,"전북","군산","군산S/S CB 7271","고장파급방지장치반 설치공사","- 군산-신김제1,2T/L 2회선 동시고장 및 호남지역 과전압 대비 SPS 설치 - SPE X 2면 설치","2023-07-21 09:00","2023-07-21 11:30","취소","취소","연속"]
[43,"전북","군산","군산S/S #2 M.Tr","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2023-07-19 09:00","2023-10-16 18:00","2023-07-19 09:00","2023-10-16 18:00","연속"]
[44,"전북","군산","군산S/S #75 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2023-07-19 09:00","2023-07-20 18:00","2023-07-19 09:00","2023-07-20 18:00","연속"]
[45,"전북","군산","군산S/S CB 7400","고장파급방지장치반 설치공사","- 청양-군산1,2T/L 2회선 동시고장 대비 SPS 설치 - SPE X 2면 설치","2023-07-24 16:00","2023-07-24 17:30","취소","취소","연속"]
[46,"전북","군산","군산S/S CB 7471","고장파급방지장치반 설치공사","- 청양-군산1,2T/L 2회선 동시고장 대비 SPS 설치 - SPE X 2면 설치","2023-07-24 14:30","2023-07-24 16:00","취소","취소","연속"]
[47,"전북","군산","군산S/S CB 7300","고장파급방지장치반 설치공사","- 청양-군산1,2T/L 2회선 동시고장 대비 SPS 설치 - SPE X 2면 설치","2023-07-24 13:00","2023-07-24 14:30","취소","취소","연속"]
[48,"전북","군산","군산S/S CB 7371","고장파급방지장치반 설치공사","- 청양-군산1,2T/L 2회선 동시고장 대비 SPS 설치 - SPE X 2면 설치","2023-07-24 09:00","2023-07-24 11:30","취소","취소","연속"]
[49,"전북","군산","군산S/S CB 7100","고장파급방지장치반 설치공사","- 군산-신김제1,2T/L 2회선 동시고장 및 호남지역 과전압 대비 SPS 설치 - SPE X 2면 설치","2023-07-21 16:00","2023-07-21 17:30","취소","취소","연속"]
[50,"전북","군산","군산S/S CB 7171","고장파급방지장치반 설치공사","- 군산-신김제1,2T/L 2회선 동시고장 및 호남지역 과전압 대비 SPS 설치 - SPE X 2면 설치","2023-07-21 14:30","2023-07-21 16:00","취소","취소","연속"]
[51,"전북","군산","군산S/S #4 M.Tr","군산P/O 노후배전반 대체공사","- 군산S/S 78BAY B/F반 대체 - 새만금S/S 72BAY B/F반 대체","2023-07-10 09:00","2023-07-14 18:00","2023-07-10 09:00","2023-07-14 18:00","연속"]
[52,"전북","군산","새만금S/S #3 M.Tr","군산P/O 노후배전반 대체공사","- 새만금S/S 73BAY B/F반 대체","2023-07-17 09:00","2023-07-19 18:00","2023-07-17 09:00","2023-07-19 18:00","연속"]
[53,"전북","군산","새만금S/S #2 M.Tr","군산P/O 노후배전반 대체공사","- 군산S/S 78BAY B/F반 대체 - 새만금S/S 72BAY B/F반 대체","2023-07-10 09:00","2023-07-14 18:00","2023-07-10 09:00","2023-07-14 18:00","연속"]
[54,"전북","군산","군산새만금#2 T/L","군산P/O 노후배전반 대체공사","- 새만금S/S 73BAY B/F반 대체","2023-07-17 09:00","2023-07-19 18:00","2023-07-17 09:00","2023-07-19 18:00","연속"]
[55,"전북","군산","새만금S/S #1 Sh.R CB","고장파급방지장치반 설치공사","- 호남지역 과전압 대비 조상설비제어 SPS 설치 - SPS X 2면 설치","2023-07-25 09:00","2023-07-25 11:30","취소","취소","연속"]
[56,"전북","직할","신남원광양#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 76Bay BF 보호배전반 대체","2023-07-24 09:00","2023-07-28 18:00","취소","취소","연속"]
[57,"전북","직할","신남원S/S #1 M.Tr","'22-23 전북직할 변전협력 총액공사","345kV 1,2차 차단기 보통점검","2023-07-24 09:00","2023-07-25 18:00","2023-07-24 09:00","2023-07-25 18:00","연속"]
[58,"전북","직할","신옥천신남원#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 72Bay BF 보호배전반 대체 및 LA 보통점검","2023-07-31 09:00","2023-08-04 18:00","취소","취소","연속"]
[59,"전북","직할","신남원한빛NP#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 72Bay BF 보호배전반 대체 및 LA 보통점검","2023-07-31 09:00","2023-08-04 18:00","취소","취소","연속"]
[60,"전북","직할","신남원광양#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 75Bay BF 보호배전반 대체","2023-07-17 09:00","2023-07-21 18:00","취소","취소","연속"]
[61,"전북","직할","신남원의령#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 74Bay BF 보호배전반 대체","2023-07-10 09:00","2023-07-14 18:00","취소","취소","연속"]
[62,"전북","직할","신남원한빛NP#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 71Bay BF 보호배전반 대체","2023-07-03 09:00","2023-07-07 18:00","취소","취소","연속"]
[63,"전북","직할","신옥천신남원#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 71Bay BF 보호배전반 대체 및 CVT 보통점검","2023-07-03 09:00","2023-07-07 18:00","취소","취소","연속"]
[64,"광주전남","강진","신강진S/S #1 M.Tr","부싱 유증가스 분석장치 설치를 위한 신강진S/S 1M.Tr 사전 휴전","부싱 유증가스 분석장치 설치를 위한 신강진S/S 1M.Tr 사전 휴전","2023-07-04 10:00","2023-07-04 12:00","2023-07-04 10:00","2023-07-04 12:00","연속"]
[65,"광주전남","강진","신강진S/S #4 M.Tr","부싱 유증가스 분석장치 설치를 위한 신강진S/S 4M.Tr 사전 휴전","부싱 유증가스 분석장치 설치를 위한 신강진S/S 4M.Tr 사전 휴전","2023-07-04 16:00","2023-07-04 18:00","2023-07-04 16:00","2023-07-04 18:00","연속"]
[66,"광주전남","강진","신강진S/S #3 M.Tr","부싱 유증가스 분석장치 설치를 위한 신강진S/S 3M.Tr 사전 휴전","부싱 유증가스 분석장치 설치를 위한 신강진S/S 3M.Tr 사전 휴전","2023-07-04 14:00","2023-07-04 16:00","2023-07-04 14:00","2023-07-04 16:00","연속"]
[67,"광주전남","강진","신강진S/S #2 M.Tr","부싱 유증가스 분석장치 설치를 위한 신강진S/S 2M.Tr 사전 휴전","1차, 2차 부싱 유증가스 분석장치 설치를 위한 신강진S/S 2M.Tr 사전 휴전","2023-07-04 12:00","2023-07-04 14:00","2023-07-04 12:00","2023-07-04 14:00","연속"]
[68,"광주전남","광주","신광주S/S CB 7371","7371 CB 조작시험","7371 CB 조작시험","2023-07-03 09:00","2023-07-03 18:00","2023-07-03 09:00","2023-07-03 18:00","연속"]
[69,"광주전남","광주","신광주S/S CB 7300","7300 CB 조작시험","7300 CB 조작시험","2023-07-04 09:00","2023-07-04 18:00","2023-07-04 09:00","2023-07-04 18:00","연속"]
[70,"광주전남","광주","신광주S/S CB 7200","7200 CB 조작시험","7200 CB 조작시험","2023-07-05 09:00","2023-07-05 18:00","취소","취소","연속"]
[71,"광주전남","광주","신광주S/S CB 7271","7271 GIS 보통점검","7271 GIS 보통점검","2023-07-06 09:00","2023-07-06 18:00","2023-07-06 09:00","2023-07-06 18:00","연속"]
[72,"광주전남","순천","광양광양CC#2 T/L","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY] - BUS 교체시 CVT, LA 임시철거 필요","2023-07-19 08:00","2023-07-25 08:00","2023-07-19 08:00","2023-07-25 08:00","연속"]
[73,"광주전남","순천","광양광양CC#1 T/L","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY] - BUS 교체시 CVT, LA 임시철거 필요","2023-07-13 08:00","2023-07-19 08:00","2023-07-13 08:00","2023-07-19 08:00","연속"]
[74,"광주전남","순천","광양S/S #76 BUS","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY]","2023-07-13 08:00","2023-07-28 18:00","2023-07-13 08:00","2023-07-28 18:00","연속"]
[75,"광주전남","순천","신강진광양#1 T/L","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY] - BUS 무부하 가압","2023-07-26 08:00","2023-07-27 08:00","2023-07-26 08:00","2023-07-27 08:00","연속"]
[76,"광주전남","순천","신강진광양#1 T/L","광양S/S 362kV 용량부족 GIS 교체공사(BUS)","광양S/S #71,#76BUS 교체공사[79,7A BAY] - BUS 무부하 가압","2023-07-10 08:00","2023-07-11 18:00","2023-07-10 08:00","2023-07-11 18:00","연속"]
[77,"대구","포항","신포항S/S #3 M.Tr","2022~23년 포항전력지사 변전총액공사","신포항S/S #3M.Tr 33Q 동작관련 OLTC 절연유 보충","2023-07-03 09:00","2023-07-03 18:00","2023-07-03 09:00","2023-07-03 18:00","연속"]
[78,"대구","포항","월성N/P CB 7500","월성S/Y 7500,7572 GIS 정밀점검","월성S/Y 7500,7572 GIS 정밀점검","2023-07-31 09:00","2023-08-05 18:00","취소","취소","연속"]
[79,"대구","포항","월성N/P CB 7572","월성S/Y 7500,7572 GIS 정밀점검","월성S/Y 7500,7572 GIS 정밀점검","2023-07-31 09:00","2023-08-05 18:00","취소","취소","연속"]
[80,"경북","구미","선산S/S #75 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","71Bay 신설 GIS 위상확인 및 무부하가압","2023-07-13 11:00","2023-07-14 18:00","2023-07-13 11:00","2023-07-14 18:00","연속"]
[81,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사","71Bay 신설 GIS 위상확인 및 무부하가압","2023-07-13 09:00","2023-07-14 18:00","2023-07-13 09:00","2023-07-14 18:00","연속"]
[82,"경북","구미","선산S/S #70 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사","71Bay 신설 GIS 위상확인","2023-07-13 09:00","2023-07-13 11:00","2023-07-13 09:00","2023-07-13 11:00","연속"]
[83,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-신울산#2T/L 수평추락방지장치 설치 : 1~110호, 87기","2023-07-18 08:00","2023-07-25 18:00","취소","취소","연속"]
[84,"부산울산","북부산","북부산울산TP#2 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-울산TP#2T/L 수평추락방지장치 설치 : 28~148호, 104기","2023-07-26 08:00","2023-08-01 18:00","취소","취소","연속"]
[85,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-신울산#1T/L 수평추락방지장치 설치 : 1~110호, 87기","2023-07-01 08:00","2023-07-08 18:00","취소","취소","연속"]
[86,"부산울산","북부산","북부산울산TP#1 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-울산TP#1T/L 수평추락방지장치 설치 : 28~148호, 104기","2023-07-09 08:00","2023-07-17 18:00","취소","취소","연속"]
[87,"부산울산","서부산","신김해신녹산#2 T/L","신녹산S/S 신김해-신녹산#2 T/L 휴전작업","신녹산S/S 345kV 72371, 7300 GIS 보통점검","2023-07-11 09:00","2023-07-11 18:00","2023-07-11 09:00","2023-07-11 18:00","연속"]
[88,"부산울산","서부산","신김해신녹산#1 T/L","신녹산S/S 신김해-신녹산#1 T/L 휴전작업","신녹산S/S 345kV 7271, 7200 GIS 보통점검","2023-07-10 09:00","2023-07-10 18:00","2023-07-10 09:00","2023-07-10 18:00","연속"]
[89,"부산울산","울산","남울산울산TP#2 T/L","345kV 남울산S/S 울산GPS 신규수용공사","74BAY 송전선로 보호반간 PT,CB,DS 방간결선 시험","2023-07-03 09:00","2023-07-06 18:00","2023-07-03 09:00","2023-07-06 18:00","연속"]
[90,"부산울산","울산","신온산남울산#1 T/L","2023년 가공송전 순시점검 위탁공사","-공사내용: 345kV 신온산-남울산#1T/L 정밀점검 및 초기점검 -작업구간: No.17 ~ S/T","2023-07-03 09:00","2023-07-07 18:00","취소","취소","연속"]
[91,"부산울산","울산","남울산S/S #1 BUS","345kV 남울산S/S 울산GPS 신규수용공사","72Bay GIS개체시험","2023-07-07 09:00","2023-07-07 18:00","2023-07-07 09:00","2023-07-07 13:00","연속"]
[92,"부산울산","울산","신온산남울산#2 T/L","345kV 남울산S/S 울산GPS 신규수용공사","72BAY 신규설비 시험가압 선로","2023-07-07 09:00","2023-07-08 18:00","2023-07-07 09:00","2023-07-08 18:00","연속"]
[93,"부산울산","울산","남울산S/S #2 BUS","345kV 남울산S/S 울산GPS 신규수용공사","72Bay 신규설비 개체시험 및 시험가압","2023-07-07 09:00","2023-07-08 18:00","2023-07-07 13:00","2023-07-08 18:00","연속"]
[94,"부산울산","울산","신온산남울산#2 T/L","2023년 가공송전 순시점검 위탁공사","-공사내용: 345kV 신온산-남울산#2T/L 정밀점검 및 초기점검 -작업구간: No.17 ~ S/T","2023-07-10 09:00","2023-07-14 18:00","취소","취소","연속"]
[95,"부산울산","울산","남울산S/S CB 7400","345kV 남울산S/S 울산GPS 신규수용공사","울산GPS#1T/L 송전선로 보호반 준공시험","2023-07-20 09:00","2023-07-25 18:00","2023-07-20 09:00","2023-07-25 18:00","연속"]
[96,"부산울산","울산","남울산S/S 울산GPS#1T/L CB","345kV 남울산S/S 울산GPS 신규수용공사","울산GPS#1 T/L 보호반 준공시험","2023-07-20 09:00","2023-07-25 18:00","2023-07-20 09:00","2023-07-25 18:00","연속"]
[97,"부산울산","울산","신온산S/S #3 M.Tr","22~23년 변전협력회사 총액공사","- #2Sh.C Main GIS SF6 Gas 누기보수 관련 안전이격","2023-07-05 09:00","2023-07-06 18:00","2023-07-05 09:00","2023-07-06 18:00","연속"]
[98,"부산울산","울산","신온산S/S #2 M.Tr","22~23년 변전협력회사 총액공사","- 신온산-온산#3T/L GIS SF6 Gas 누기보수 관련 안전이격","2023-07-03 09:00","2023-07-04 18:00","2023-07-03 09:00","2023-07-04 18:00","연속"]
[99,"부산울산","울산","울주고리NP#1 T/L","고리NP S/Y 345kV GIS 보통점검","고리NP S/Y 345kV GIS 보통점검(7B71)","2023-07-03 09:30","2023-07-03 17:00","취소","취소","연속"]
[100,"경남","통영","신고성S/S #2 M.Tr","신고성S/S #2M.Tr 부싱절연유채유","신고성S/S #2M.Tr 부싱절연유채유","2023-07-26 09:00","2023-07-26 18:00","취소","취소","연속"]
[101,"대구",null,"월성N/P #3호기 주변압기 (CB 7500, 7572)","주변압기 점검","주변압기 점검","2023-07-27 09:00","2023-08-14 18:00","2023-07-27 09:00","2023-08-14 18:00","연속"]
[102,"전북","군산","청양군산#1 T/L","SPS 설치 작업","SPS 설치 작업","2023-07-10 09:00","2023-07-10 18:00","2023-07-10 09:00","2023-07-10 18:00","연속"]
[103,"전북","군산","청양군산#2 T/L","SPS 설치 작업","SPS 설치 작업","2023-07-11 09:00","2023-07-11 18:00","2023-07-11 09:00","2023-07-11 18:00","연속"]
[104,"남서울","영등포","신광명신문래#1 T/L","신광명S/S GIS 용량대체 및 S/W 증설공사","362kV 63kA GIS 24CB 설치","2023-07-29 10:00","2023-07-30 10:00","2023-07-29 07:00","2023-07-30 07:00","연속"]
[105,"남서울","영등포","신광명신문래#2 T/L","신광명S/S GIS 용량대체 및 S/W 증설공사","362kV 63kA GIS 24CB 설치","2023-07-30 10:00","2023-07-31 10:00","2023-07-30 07:00","2023-07-31 07:00","연속"]

{"sheet":"154설비","index":2,"n_rows":111,"n_cols":11,"rows_kept":111,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 7월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","상계노원열병합 T/L","'23년 성동P/O 노후 보호배전반 교체공사","상계S/S 154kV 노원열병합T/L 보호배전반 노후대체","2023-07-24 10:00","2023-07-27 17:00","2023-07-24 10:00","2023-07-27 17:00","연속"]
[2,"서울","중부","옥인운니#1 T/L","23 중부P/O 총액공사","송전선로 보호반 대체","2023-07-03 10:00","2023-07-06 18:00","2023-07-11 10:00","2023-07-14 13:00","연속"]
[3,"서울","중부","옥인운니#2 T/L","23 중부P/O 총액공사","송전선로 보호반 대체","2023-07-10 10:00","2023-07-13 18:00","2023-07-17 10:00","2023-07-20 18:00","연속"]
[4,"서울","직할","서대문세종로 T/L","154kV 서대문세종로T/L EBG 가스 채취밸브 취부","154kV 서대문세종로T/L 세종로 EBG 가스 채취밸브 취부","2023-07-03 09:00","2023-07-05 18:00","취소","취소","연속"]
[5,"남서울","동서울","강동천호#1 T/L","2023년 동서울전력 170kV GIS 정밀점검","2023년 동서울전력 170kV GIS 정밀점검 - 대상 : 강동S/S 강동-천호#1T/L","2023-07-01 09:00","2023-07-02 18:00","2023-07-01 09:00","2023-07-02 18:00","연속"]
[6,"남서울","동서울","잠실수서#1 T/L","'22~23년 동서울전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-07-03 07:00","2023-07-04 17:30","2023-07-03 07:00","2023-07-04 17:30","연속"]
[7,"남서울","동서울","잠실수서#2 T/L","'22~23년 동서울전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-07-05 07:00","2023-07-06 17:30","2023-07-05 07:00","2023-07-06 17:30","연속"]
[8,"남서울","동서울","산성수서#2 T/L","'22~23년 동서울전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-07-07 07:00","2023-07-07 17:30","2023-07-07 07:00","2023-07-07 17:30","연속"]
[9,"남서울","동서울","산성수서#1 T/L","'22~23년 동서울전력지사 가공송전 협력회사 총액공사","추락방지장치(수평) 설치","2023-07-08 07:00","2023-07-08 17:30","2023-07-08 07:00","2023-07-08 17:30","연속"]
[10,"남서울","영등포","천왕S/S #2 BUS","154kV 천왕-구로#2T/L 긴급복구공사 무부하 및 상시험","154kV 천왕-구로#2T/L 긴급복구공사 무부하 및 상시험","2023-07-03 09:00","2023-07-04 18:00","취소","취소","연속"]
[11,"남서울","영등포","신광명신문래#1 T/L","신광명S/S GIS 용량대체 및 S/W 증설공사","362kV 63kA GIS 24CB 설치","2023-07-29 10:00","2023-07-30 10:00","취소","취소","연속"]
[12,"남서울","영등포","신광명신문래#2 T/L","신광명S/S GIS 용량대체 및 S/W 증설공사","362kV 63kA GIS 24CB 설치","2023-07-30 10:00","2023-07-31 10:00","취소","취소","연속"]
[13,"남서울","직할","신문래구로#2 T/L","OF케이블 절연유 채유밸브 설치","OF케이블 절연유 채유밸브 설치(SJ/B#1)","2023-07-03 09:00","2023-07-04 18:00","2023-07-03 09:00","2023-07-04 18:00","연속"]
[14,"인천","시흥","서시화S/S KGETS T/L CB","GIS 보통점검","GIS 보통점검","2023-07-29 08:00","2023-07-29 18:00","2023-07-29 08:00","2023-07-29 18:00","연속"]
[15,"경기북부","구리","용정포천#2 T/L","154kV 포천변전소 옥내화 토건공사","H-PILE 인발을 위한 안전이격거리 확보","2023-07-04 09:00","2023-07-04 18:00","2023-07-04 09:00","2023-07-04 18:00","연속"]
[16,"경기북부","구리","포천운천#1 T/L","154kV 포천변전소 옥내화 토건공사","H-PILE 인발을 위한 안전이격거리 확보","2023-07-03 09:00","2023-07-03 18:00","2023-07-03 09:00","2023-07-03 18:00","연속"]
[17,"경기북부","구리","용정포천#1 T/L","154kV 포천변전소 옥내화 토건공사","H-PILE 인발을 위한 안전이격거리 확보","2023-07-03 09:00","2023-07-03 18:00","2023-07-03 09:00","2023-07-03 18:00","연속"]
[18,"경기북부","직할","양주고양#1 T/L","22-23년 경기북부 직할 변전협력회사 총액공사","양주고양#1TL 보호반 43PDA 불량분 교체","2023-07-03 09:00","2023-07-03 18:00","2023-07-03 09:00","2023-07-03 18:00","연속"]
[19,"대전세종충남","대전","가수원서대전#2 T/L","서대전S/S 가수원-서대전#2T/L GIS 초기점검","서대전S/S 가수원-서대전#2T/L GIS 초기점검","2023-07-18 09:00","2023-07-18 18:00","취소","취소","연속"]
[20,"대전세종충남","대전","신옥천남대전#1 T/L","남대전S/S 신옥천-남대전#1T/L GIS 초기점검","남대전S/S 신옥천-남대전#1T/L GIS 초기점검","2023-07-12 09:00","2023-07-12 18:00","취소","취소","연속"]
[21,"대전세종충남","대전","신옥천남대전#4 T/L","남대전S/S 신옥천-남대전#4T/L GIS 초기점검","남대전S/S 신옥천-남대전#4T/L GIS 초기점검","2023-07-13 09:00","2023-07-13 18:00","취소","취소","연속"]
[22,"대전세종충남","대전","팔봉두마#1 T/L","(6월 취소시)[송전] 154kV 팔봉-두마T/L 정밀점검","(6월 취소시)[송전] 154kV 팔봉-두마#1T/L 정밀점검","2023-07-10 08:00","2023-07-14 18:00","2023-07-10 07:00","2023-07-14 18:00","매일"]
[23,"대전세종충남","대전","신옥천서대전 T/L","서대전S/S 신옥천-서대전T/L GIS 초기점검","서대전S/S 신옥천-서대전T/L GIS 초기점검","2023-07-17 09:00","2023-07-17 18:00","취소","취소","연속"]
[24,"대전세종충남","대전","신계룡두마#2 T/L","신계룡-두마#2T/L 송전선로 보호반 교체(양단)","신계룡-두마#2T/L 송전선로 보호반 교체(양단)","2023-07-05 13:00","2023-07-07 18:00","취소","취소","연속"]
[25,"대전세종충남","대전","신계룡두마#1 T/L","신계룡-두마#1T/L 송전선로 보호반 교체(양단)","신계룡-두마#1T/L 송전선로 보호반 교체(양단)","2023-07-03 09:00","2023-07-05 13:00","취소","취소","연속"]
[26,"대전세종충남","대전","신옥천유천 T/L","유천S/S 신옥천-유천T/L GIS 보통점검","유천S/S 신옥천-유천T/L GIS 보통점검","2023-07-14 09:00","2023-07-14 18:00","취소","취소","연속"]
[27,"대전세종충남","대전","추부금산#1 T/L","(6월취소시[송전]345kV신옥천-청양등17개T/L추락방지시설 설치공사","(6월취소시) [송전] 154kV 추부-금산T/L 추락방지시설 설치공사","2023-07-10 08:00","2023-08-07 18:00","취소","취소","매일"]
[28,"대전세종충남","대전","신옥천추부#2 T/L","(6월취소시[송전]345kV신옥천-청양등17개T/L추락방지시설 설치공사","(6월취소시) [송전] 154kV 신옥천-추부T/L 추락방지시설 설치공사","2023-07-03 08:00","2023-07-14 18:00","취소","취소","매일"]
[29,"대전세종충남","천안","서천안S/S CB 6100","서천안S/S 154kV BUS TIE 6100 GIS 보통점검","서천안S/S 154kV BUS TIE 6100 GIS 보통점검","2023-07-07 09:00","2023-07-07 18:00","2023-07-07 09:00","2023-07-07 18:00","연속"]
[30,"대전세종충남","천안","신온양석곡#2 T/L","신온양S/S 154kV 신온양-석곡#2T/L 보호배전반 성능개선","신온양S/S 154kV 신온양-석곡#2T/L 보호배전반 성능개선","2023-07-14 09:00","2023-07-14 18:00","2023-07-14 09:00","2023-07-14 18:00","연속"]
[31,"대전세종충남","천안","신온양S/S #63 BUS","신온양S/S 154kV 신온양-석곡#1T/L #1DS 누기보수","신온양S/S 154kV 신온양-석곡#1T/L #1DS 누기보수","2023-07-11 09:00","2023-07-13 18:00","2023-07-11 09:00","2023-07-13 18:00","연속"]
[32,"대전세종충남","천안","신온양석곡#1 T/L","신온양S/S 154kV 신온양-석곡#1T/L #1DS 누기보수","신온양S/S 154kV 신온양-석곡#1T/L #1DS 누기보수","2023-07-11 09:00","2023-07-13 18:00","2023-07-11 09:00","2023-07-13 18:00","연속"]
[33,"대전세종충남","천안","아산인주#1 T/L","아산,인주S/S 154kV 아산-인주#1T/L 노후 보호배전반 대체","아산,인주S/S 154kV 아산-인주#1T/L 노후 보호배전반 대체","2023-07-03 09:00","2023-07-07 18:00","취소","취소","연속"]
[34,"대전세종충남","천안","아산S/S SEC CB 65660","아산S/S 154kV #65-66 BUS SEC GIS 초기점검","아산S/S 154kV #65-66 BUS SEC GIS 초기점검","2023-07-14 09:00","2023-07-14 18:00","취소","취소","연속"]
[35,"대전세종충남","천안","아산인주#2 T/L","아산,인주S/S 154kV 아산-인주#2T/L 노후 보호배전반 대체","아산,인주S/S 154kV 아산-인주#2T/L 노후 보호배전반 대체","2023-07-10 09:00","2023-07-14 18:00","취소","취소","연속"]
[36,"대전세종충남","천안","아산S/S SEC CB 60610","아산S/S 154kV #60-61 BUS SEC GIS 초기점검","아산S/S 154kV #60-61 BUS SEC GIS 초기점검","2023-07-13 09:00","2023-07-13 18:00","취소","취소","연속"]
[37,"대전세종충남","청양","은하홍성#2 T/L","[송전] 154kV 은하-홍성#2T/L 수평 추락방지장치 설치공사","공사명 : 345kV 청양-보령 등 11개T/L 철탑 추락방지장치 설치공사","2023-07-03 07:00","2023-07-06 18:00","취소","취소","매일"]
[38,"대전세종충남","청양","청양은하#2 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","170kV GIS 보통점검 및 노후보조계전기교체","2023-07-04 09:00","2023-07-04 18:00","2023-07-04 09:00","2023-07-04 18:00","연속"]
[39,"대전세종충남","청양","청양은하#1 T/L","[송전] 154kV 청양-은하#1T/L 수평 추락방지장치 설치공사","공사명 : 345kV 청양-보령 등 11개T/L 철탑 추락방지장치 설치공사 * 7.5~7.6 : 4회선 구간(은하홍성, 청양은하)","2023-07-05 07:00","2023-07-12 18:00","취소","취소","매일"]
[40,"전북","군산","동군산장항#1 T/L","군산P/O 노후배전반 대체 등","- 동군산-장항#1T/L 보호반 대체(양단) - 효성제 베어링 발청분 교체(병행) - 170kV GIS 정밀점검공사(병행) - 동군산-장항#1T/L 차단기 주접점 이탈 관련 점검(병행) - SA혼용시스템 관련 제어케이블 이설(병행)","2023-07-25 09:00","2023-07-28 18:00","취소","취소","연속"]
[41,"전북","군산","군산영등#1 T/L","군산P/O 154kV GIS 보통점검","영등S/S 154kV 군산-영등#1T/L GIS 보통점검","2023-07-03 09:00","2023-07-03 18:00","2023-07-03 09:00","2023-07-03 18:00","연속"]
[42,"전북","군산","군산영등#2 T/L","군산P/O 154kV GIS 보통 점검","영등S/S 154kV 군산-영등#2T/L GIS 보통점검","2023-07-04 09:00","2023-07-04 18:00","2023-07-04 09:00","2023-07-04 18:00","연속"]
[43,"전북","군산","팔봉왕궁#1 T/L","고장파급방지장치반 설치공사","- 군산-신김제1,2T/L 2회선 동시고장 대비 SPS 설치 - SPE X 2면 설치","2023-07-03 09:00","2023-07-03 12:00","취소","취소","연속"]
[44,"전북","군산","팔봉왕궁#2 T/L","고장파급방지장치반 설치공사","- 군산-신김제1,2T/L 2회선 동시고장 대비 SPS 설치 - SPE X 2면 설치","2023-07-03 13:00","2023-07-03 15:00","취소","취소","연속"]
[45,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-07-29 08:00","2023-07-29 18:00","2023-07-18 08:00","2023-07-18 18:00","연속"]
[46,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-07-23 08:00","2023-07-28 18:00","2023-07-12 08:00","2023-07-17 18:00","연속"]
[47,"전북","김제","신김제전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-07-23 08:00","2023-07-29 18:00","2023-07-12 08:00","2023-07-18 18:00","연속"]
[48,"전북","김제","신김제남전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-07-16 08:00","2023-07-22 18:00","2023-07-05 08:00","2023-07-11 18:00","연속"]
[49,"전북","김제","신김제전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-07-16 08:00","2023-07-22 18:00","2023-07-05 08:00","2023-07-11 18:00","연속"]
[50,"전북","김제","신김제전주#2 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-07-14 08:00","2023-07-15 18:00","2023-07-03 08:00","2023-07-04 18:00","연속"]
[51,"전북","김제","신김제남전주#1 T/L","154kV 신김제-남전주T/L No.25호 노후취약 지지물 교체공사","신김제-남전주T/L No.25호 철탑교체 및 No.26호 철탑보강","2023-07-14 08:00","2023-07-15 18:00","2023-07-03 08:00","2023-07-04 18:00","연속"]
[52,"전북","김제","정공정주#1 T/L","154kV 정공-정주#1T/L 계전기 성능개선","세니온제 계전기 업그레이드 및 개선","2023-07-06 10:00","2023-07-06 18:00","취소","취소","연속"]
[53,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","No.33∼36 전력선 연긴선","2023-07-25 08:00","2023-07-28 17:00","2023-07-25 08:00","2023-07-28 17:00","연속"]
[54,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","No.33∼36 전력선 연긴선","2023-07-31 08:00","2023-08-03 17:00","2023-07-31 08:00","2023-08-03 17:00","연속"]
[55,"전북","직할","무주진안 T/L","23년 전북직할 변전협력회사 총액공사","무주-진안T/L LA 보통점검","2023-07-07 09:00","2023-07-07 18:00","취소","취소","연속"]
[56,"전북","직할","북전주봉동#2 T/L","전북직할 154kV 차단기 조작시험","전북직할 154kV 차단기 조작시험","2023-07-21 16:00","2023-07-21 20:00","2023-07-21 16:00","2023-07-21 20:00","연속"]
[57,"전북","직할","북전주봉동#1 T/L","전북직할 154kV 차단기 조작시험","전북직할 154kV 차단기 조작시험","2023-07-20 16:00","2023-07-20 20:00","2023-07-20 16:00","2023-07-20 20:00","연속"]
[58,"전북","직할","북전주진안 T/L","23년 전북직할 변전협력회사 총액공사","북전주-진안T/L LA, CVT 보통점검","2023-07-06 09:00","2023-07-06 18:00","취소","취소","연속"]
[59,"전북","직할","신남원S/S #1 BUS","신남원S/S ESS 건설공사","- 154kV GIS 9Bay 증설 - 154kV M.Tr 60MVA 6bank 설치 - 모선보호반 추가 및 제어케이블 포설/결선 등","2023-07-05 09:30","2023-07-21 17:00","2023-07-05 09:30","2023-07-21 17:00","연속"]
[60,"전북","직할","신남원S/S #2 BUS","신남원S/S ESS 건설공사","- 154kV GIS 9Bay 증설 - 154kV M.Tr 60MVA 6bank 설치 - 모선보호반 추가 및 제어케이블 포설/결선 등","2023-07-24 09:30","2023-08-10 17:00","2023-07-24 09:30","2023-08-10 17:00","연속"]
[61,"전북","직할","전주서곡#2 T/L","'22-23 전북직할 변전협력 총액공사","전주-서곡T/L 보호반 대체공사","2023-07-26 14:00","2023-07-28 18:00","취소","취소","연속"]
[62,"전북","직할","전주서곡#1 T/L","'22-23 전북직할 변전협력 총액공사","전주-서곡T/L 보호반 대체공사","2023-07-24 09:00","2023-07-26 14:00","취소","취소","연속"]
[63,"광주전남","광주","계림남광주 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-07-24 09:00","2023-08-25 18:00","취소","취소","연속"]
[64,"광주전남","광주","계림S/S CB 6100","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-07-24 09:00","2023-08-25 18:00","취소","취소","연속"]
[65,"광주전남","광주","계림충장#2 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-07-24 09:00","2023-08-25 18:00","취소","취소","연속"]
[66,"광주전남","광주","담양S/S #66 BUS","담양S/S 170kV GIS 교체공사(5차분)","담양S/S 170kV GIS 교체공사(5차분)","2023-07-10 08:00","2023-07-18 14:00","2023-07-10 08:00","2023-07-18 14:00","연속"]
[67,"광주전남","광주","담양김제 T/L","담양S/S 170kV GIS 교체공사(5차분)","담양S/S 170kV GIS 교체공사(5차분)","2023-07-07 14:00","2023-07-08 14:00","2023-07-07 14:00","2023-07-08 14:00","연속"]
[68,"광주전남","광주","담양S/S #61 BUS","담양S/S 170kV GIS 교체공사(5차분)","담양S/S 170kV GIS 교체공사(5차분)","2023-07-11 10:00","2023-07-11 17:00","2023-07-11 10:00","2023-07-11 17:00","연속"]
[69,"광주전남","목포","고창홍농 T/L","[변전] 154kV 홍농S/S #1M.Tr 교체공사","- 인하선 철구 분리를 위한 안전이격 휴전 (즉시 가압 가능)","2023-07-03 09:00","2023-07-03 18:00","2023-07-03 09:00","2023-07-03 18:00","연속"]
[70,"광주전남","목포","고창홍농 T/L","[변전] 154kV 홍농S/S #1M.Tr 교체공사","- 인하선 철구 결선를 위한 안전이격 휴전 (즉시 가압 가능)","2023-07-10 09:00","2023-07-10 18:00","2023-07-10 09:00","2023-07-10 18:00","연속"]
[71,"광주전남","목포","고창홍농 T/L","[변전] 154kV 홍농S/S #1M.Tr 교체공사","- #1M.Tr 무부하가압 (즉시가압 가능)","2023-07-13 16:00","2023-07-14 16:00","2023-07-13 16:00","2023-07-14 16:00","연속"]
[72,"광주전남","순천","서순천벌교#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","서순천S/S 서순천-벌교#2T/L GIS CB 타임측정(즉시가압가능","2023-07-19 09:00","2023-07-19 14:00","2023-07-19 09:00","2023-07-19 14:00","연속"]
[73,"광주전남","순천","여수소라#1 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검(즉시가압 불가)","2023-07-03 09:00","2023-07-04 18:00","2023-07-03 09:00","2023-07-04 18:00","연속"]
[74,"광주전남","순천","여수소라#2 T/L","23년 순천전력지사 170kV GIS 정밀점검","GIS 정밀점검(즉시가압 불가)","2023-07-05 09:00","2023-07-06 18:00","2023-07-05 09:00","2023-07-06 18:00","연속"]
[75,"광주전남","순천","율촌S/S #61 BUS","율촌S/S 154kV #3M.Tr 증설공사[무부하 가압]","율촌S/S 154kV #3M.Tr 증설공사 무부하 가압","2023-07-04 14:00","2023-07-05 14:00","2023-07-04 14:00","2023-07-05 14:00","연속"]
[76,"광주전남","순천","순천율촌#2 T/L","율촌S/S 154kV #3M.Tr 증설공사[무부하 가압]","율촌S/S 154kV #3M.Tr 증설공사 무부하 가압","2023-07-04 14:00","2023-07-05 14:00","2023-07-04 14:00","2023-07-05 14:00","연속"]
[77,"대구","경산","대구청도#1 T/L","22~23년 경산PO 변전협력회사 총액공사","- GIS 초기점검","2023-07-14 09:30","2023-07-14 14:00","2023-07-14 09:30","2023-07-14 14:00","연속"]
[78,"대구","달성","달성S/S CB 6100","GIS차단기동작특성시험","GIS차단기동작특성시험","2023-07-04 09:00","2023-07-04 12:00","2023-07-04 09:00","2023-07-04 12:00","연속"]
[79,"경북","직할","울진삼척GP#1 T/L","울진S/S 장기사용 GIS 교체공사 (4차수)","울진S/S 장기사용 GIS 교체공사 (4차수) _ 무부하 가압용","2023-07-11 09:00","2023-07-12 18:00","취소","취소","연속"]
[80,"경북","직할","울진삼척GP#1 T/L","울진S/S 장기사용 GIS 교체공사 (4차수)","울진S/S 장기사용 GIS 교체공사 (4차수) _ 무부하 가압용","2023-07-18 09:00","2023-07-19 18:00","취소","취소","연속"]
[81,"부산울산","동부산","신양산구서#2 T/L","2022~2023년 동부산전력지사 가공송전 협력회사 총액공사","폴리머지지애자 설치","2023-07-12 08:00","2023-07-14 18:00","2023-07-12 08:00","2023-07-14 18:00","연속"]
[82,"부산울산","동부산","신양산구서#1 T/L","2022~2023년 동부산전력지사 가공송전 협력회사 총액공사","폴리머지지애자 설치","2023-07-10 08:00","2023-07-11 18:00","2023-07-10 08:00","2023-07-11 18:00","연속"]
[83,"부산울산","북부산","구포S/S #1 BUS","구포S/S 154kV 장기사용 GIS 대체공사(4차)","구포S/S 154kV 장기사용 GIS 대체공사(4차)","2023-07-14 12:00","2023-07-14 15:00","2023-07-14 12:00","2023-07-14 15:00","연속"]
[84,"부산울산","북부산","북부산구포#2 T/L","구포S/S 154kV 장기사용 GIS 대체공사(4차)","구포S/S 154kV 장기사용 GIS 대체공사(4차)_#2BUS 시험가압","2023-07-02 13:00","2023-07-03 13:00","2023-07-02 13:00","2023-07-03 13:00","연속"]
[85,"부산울산","북부산","구포S/S #2 BUS","구포S/S 154kV 장기사용 GIS 대체공사(4차)","구포S/S 154kV 장기사용 GIS 대체공사(4차)","2023-07-07 13:00","2023-07-08 13:00","2023-07-07 13:00","2023-07-08 13:00","연속"]
[86,"부산울산","북부산","모라S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#2T/L GIS 정밀점검 휴전설비 : #2BUS","2023-07-20 08:00","2023-07-20 18:00","2023-07-20 08:00","2023-07-20 18:00","연속"]
[87,"부산울산","북부산","모라S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#2T/L GIS 정밀점검 휴전설비 : #1BUS","2023-07-21 08:00","2023-07-22 18:00","2023-07-21 08:00","2023-07-22 18:00","연속"]
[88,"부산울산","북부산","대저모라#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#2T/L GIS 정밀점검","2023-07-20 08:00","2023-07-22 18:00","2023-07-20 08:00","2023-07-22 18:00","연속"]
[89,"부산울산","북부산","모라S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#1T/L GIS 정밀점검 휴전설비 : #1BUS","2023-07-18 08:00","2023-07-19 18:00","2023-07-18 08:00","2023-07-19 18:00","연속"]
[90,"부산울산","북부산","대저모라#1 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#1T/L GIS 정밀점검","2023-07-17 08:00","2023-07-19 18:00","2023-07-17 08:00","2023-07-19 18:00","연속"]
[91,"부산울산","북부산","모라S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#1T/L GIS 정밀점검 휴전설비 : #2BUS","2023-07-17 08:00","2023-07-17 18:00","2023-07-17 08:00","2023-07-17 18:00","연속"]
[92,"부산울산","북부산","북부산물금 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치","154kV 북부산-물금T/L 수평 추락방지장치 설치(1~9,37~39호 12기, 2회선철탑)","2023-07-10 08:30","2023-07-11 18:00","2023-07-10 08:30","2023-07-11 18:00","연속"]
[93,"부산울산","북부산","북부산호포 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 북부산-물금, 호포분기T/L 수평 추락방지장치 설치(북부산-물금 9기, 호포분기 5기)-총 14기 2회선철탑","2023-07-05 08:30","2023-07-06 18:00","2023-07-05 08:30","2023-07-06 18:00","연속"]
[94,"부산울산","북부산","호포물금 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치","154kV 북부산-물금, 호포분기T/L 수평 추락방지장치 설치(북부산-물금 3기, 호포분기 5기)-총 8기","2023-07-12 08:30","2023-07-13 18:00","2023-07-12 08:30","2023-07-13 18:00","연속"]
[95,"부산울산","서부산","녹공마천#2 T/L","녹공S/S 154kV 녹공-마천#2T/L GIS 휴전작업","녹공S/S 154kV 녹공-마천#2T/L GIS VX 계전기 교체","2023-07-05 09:00","2023-07-05 18:00","2023-07-05 09:00","2023-07-05 18:00","연속"]
[96,"부산울산","울산","남울산신온산#1 T/L","2023년 가공송전순시점검 위탁공사","[안전이격]345KV 신온산-남울산#2T/L 정밀점검 및 초기점검 관련","2023-07-10 09:00","2023-07-11 18:00","취소","취소","연속"]
[97,"부산울산","울산","남울산신온산#2 T/L","2023년 가공송전순시점검 위탁공사","[안전이격]345KV 신온산-남울산#1T/L 정밀점검 및 초기점검 관련","2023-07-03 09:00","2023-07-04 18:00","취소","취소","연속"]
[98,"부산울산","울산","신온산온산#3 T/L","23년 울산전력지사 개폐장치 보통점검공사","- GIS(697) 보통점검 - 692DS SF6 Gas 누기보수","2023-07-03 09:00","2023-07-04 18:00","2023-07-03 09:00","2023-07-04 18:00","연속"]
[99,"부산울산","울산","신울산S/S SEC CB 65660","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-07-11 09:00","2023-07-11 18:00","2023-07-11 09:00","2023-07-11 18:00","연속"]
[100,"부산울산","울산","신울산S/S 임시연락T/L CB","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-07-03 09:00","2023-07-03 18:00","2023-07-03 09:00","2023-07-03 18:00","연속"]
[101,"부산울산","울산","신울산S/S SEC CB 60610","23년 울산전력지사 개폐장치 보통점검공사","- GIS 보통점검","2023-07-10 09:00","2023-07-10 18:00","2023-07-10 09:00","2023-07-10 18:00","연속"]
[102,"부산울산","울산","신온산온산#1 T/L","22~23년 변전협력회사 총액공사","- 차단기 동작시험","2023-07-05 09:00","2023-07-05 18:00","2023-07-05 09:00","2023-07-05 18:00","연속"]
[103,"부산울산","울산","온산처용#1 T/L","2023년 가공송전순시점검 위탁공사","-공사내용: 154kV 온산처용#1T/L 정밀점검 -작업구간: S/T~No.9","2023-07-12 09:00","2023-07-14 18:00","취소","취소","연속"]
[104,"부산울산","울산","온산처용#2 T/L","2023년 가공송전순시점검 위탁공사","-공사내용: 154kV 온산처용#2T/L 정밀점검 -작업구간: S/T~No.9","2023-07-05 09:00","2023-07-07 18:00","취소","취소","연속"]
[105,"부산울산","직할","부산수정#2 T/L","23-24년 서부산전력지사 지중송전 위탁정비공사","OF케이블 접속함 절연유 채유작업","2023-07-15 09:00","2023-07-16 18:00","2023-07-15 09:00","2023-07-16 18:00","연속"]
[106,"부산울산","직할","부산수정#1 T/L","23-24년 서부산전력지사 지중송전 위탁정비공사","OF케이블 접속함 절연유 채유작업","2023-07-08 09:00","2023-07-09 18:00","2023-07-08 09:00","2023-07-09 18:00","연속"]
[107,"경남","진주","진주개양#2 T/L","진주S/S 옥외철구 설비 GIS화 공사 관련 안전이격거리 확보","송전선로 GIS화 이설관련 안전이격거리 확보","2023-07-06 07:00","2023-07-08 16:00","2023-07-09 07:00","2023-07-09 12:00","연속"]