{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":13,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":5,"n_cols":11,"rows_kept":5,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 8월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"부산울산","동부산","신고리N/P #1 BUS","신고리 5,6호기 접속설비공사","87BAY(8771,8700) #1BUS 연결작업","2023-08-28 09:00","2023-09-10 18:00","취소","취소","연속"]

{"sheet":"345설비","index":1,"n_rows":47,"n_cols":11,"rows_kept":47,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2023년도 8월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","신성남신양재#2 T/L","2023년 강남전력지사 362kV GIS 정밀점검공사","- 대상설비 : 7279 GIS - 무부하가압용","2023-08-11 18:00","2023-08-11 21:00","취소","취소","연속"]
[2,"남서울","강남","신양재S/S #2 Sh.R (CB 7279)","2023년 강남전력지사 362kV GIS 정밀점검공사","- 대상설비 : 7279 GIS","2023-08-07 09:00","2023-08-11 21:00","취소","취소","연속"]
[3,"남서울","강남","신성남신양재#1 T/L","2023년 강남전력지사 362kV GIS 정밀점검공사","- 대상설비 : 7179 GIS - 무부하가압용","2023-08-04 18:00","2023-08-04 21:00","취소","취소","연속"]
[4,"남서울","동서울","동서울S/S SVC CB","2023년 동서울S/S SVC 보통점검","동서울S/S SVC 설비 보통점검","2023-08-07 09:00","2023-08-18 18:00","2023-08-07 09:00","2023-08-18 18:00","연속"]
[5,"경기북부","고양","신파주S/S SVC CB","신파주S/S SVC 냉각설비 점검공사","신파주S/S SVC 냉각설비 점검공사","2023-08-28 09:00","2023-09-01 18:00","2023-08-28 09:00","2023-09-01 18:00","연속"]
[6,"경기북부","구리","신가평S/S #4 Sh.R CB","신가평S/S 345kV #4Sh.R 유중가스 이상 관련 절연유 여과","신가평S/S 345kV #4Sh.R 유중가스 이상관련 절연유 여과","2023-08-21 09:00","2023-08-24 18:00","2023-08-21 09:00","2023-08-24 18:00","연속"]
[7,"경기","평택","북당진고덕HVDC#1 Pole CB","북당진-고덕 2단계 HVDC 건설사업","#1POLE Bipole 구성(제어기~현장설비),#1,2POLE 및 Bipole 부하시험(23.10.16~12.15),시운전(2023.12.16~2024.02.15)","2023-08-16 09:00","2024-02-15 18:00","2023-08-16 09:00","2024-02-15 18:00","연속"]
[8,"경기","평택","고덕S/S STATCOM CB","고덕STATCOM 운전정보 통합관리 시스템 구축용역","FACTS설비 운전정보 통합관리 시스템 구축관련 작업 - Lan cable 포설 및 결선 - operation PNL 내부 모듈작업 등 - STATCOM Valve, Yard Door 인터록키 작업","2023-08-21 09:00","2023-08-25 18:00","2023-08-21 09:00","2023-08-25 18:00","연속"]
[9,"충북","충주","신제천S/S #4 M.Tr","345kV 신제천S/S #4 M.Tr 대체공사","#4 M.Tr 무부하가압용","2023-08-28 09:00","2023-08-29 09:00","2023-08-28 09:00","2023-08-29 09:00","연속"]
[10,"대전세종충남","대전","신계룡S/S #1 BUS","신계룡S/S SPS 설치 관련 345kV 모선 PT전압 인출","신계룡S/S SPS 설치 관련 345kV 모선 PT전압 인출 -한빛NP 배후계통 고장파급방지시스템 구성 관련 사전작업","2023-08-01 09:00","2023-08-01 12:00","2023-08-01 09:00","2023-08-01 12:00","연속"]
[11,"대전세종충남","대전","신계룡S/S #2 BUS","신계룡S/S SPS 설치 관련 345kV 모선 PT전압 인출","신계룡S/S SPS 설치 관련 345kV 모선 PT전압 인출 -한빛NP 배후계통 고장파급방지시스템 구성 관련 사전작업","2023-08-01 13:00","2023-08-01 18:00","2023-08-01 13:00","2023-08-01 18:00","연속"]
[12,"대전세종충남","천안","아산보령TP#1 T/L","아산S/S 23kV Sh.R 교체작업 안전이격 확보","아산S/S 23kV Sh.R 교체작업 안전이격 확보","2023-08-21 09:00","2023-08-21 18:00","취소","취소","연속"]
[13,"대전세종충남","천안","아산S/S #1 M.Tr","아산S/S 23kV #1-2Sh.R 설치 관련 무부하가압","아산S/S 23kV #1-2Sh.R 설치 관련 무부하가압","2023-08-30 16:00","2023-08-31 16:00","취소","취소","연속"]
[14,"대전세종충남","청양","신옥천청양 T/L","[송전] 345kV 신옥천-청양등 2개TL추락방지 설치공사","[송전] 345kV 신옥천-청양T/L 추락방지장치 설치공사","2023-08-28 08:00","2023-09-08 18:00","2023-08-28 08:00","2023-09-08 18:00","매일"]
[15,"전북","군산","군산신김제#2 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-08-23 07:00","2023-08-31 18:00","취소","취소","연속"]
[16,"전북","군산","군산S/S #75 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2023-08-09 09:00","2023-08-10 18:00","2023-08-09 09:00","2023-08-10 18:00","연속"]
[17,"전북","군산","군산S/S #2 M.Tr","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2023-08-09 09:00","2023-11-06 18:00","2023-08-09 09:00","2023-11-06 18:00","연속"]
[18,"전북","군산","군산S/S #70 BUS","군산변전소 345KV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2023-08-07 09:00","2023-08-08 18:00","2023-08-07 09:00","2023-08-08 18:00","연속"]
[19,"전북","군산","군산신김제#2 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-08-13 07:00","2023-08-13 18:00","2023-08-13 07:00","2023-08-13 18:00","연속"]
[20,"전북","군산","군산신김제#1 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-08-25 07:00","2023-09-02 18:00","취소","취소","연속"]
[21,"전북","군산","새만금S/S #1 Sh.R CB","고장파급방지장치반 설치공사","- 호남지역 과전압 대비 조상설비제어 SPS 설치 - SPS X 2면 설치","2023-08-08 09:00","2023-08-08 11:30","2023-08-08 09:00","2023-08-08 11:30","연속"]
[22,"전북","김제","신김제S/S CB 7100","신김제S/S 고장파급방지장치반 설치공사","신김제S/S 고장파급방지장치반 설치공사","2023-08-10 14:30","2023-08-10 15:00","2023-08-10 14:30","2023-08-10 15:00","연속"]
[23,"전북","김제","신김제S/S CB 7200","신김제S/S 고장파급방지장치반 설치공사","신김제S/S 고장파급방지장치반 설치공사","2023-08-10 13:30","2023-08-10 14:00","취소","취소","연속"]
[24,"전북","김제","신김제S/S CB 7271","신김제S/S 고장파급방지장치반 설치공사","신김제S/S 고장파급방지장치반 설치공사","2023-08-10 13:00","2023-08-10 13:30","취소","취소","연속"]
[25,"전북","김제","신김제S/S #2 BUS","신김제S/S 고장파급방지장치반 설치공사","신김제S/S 고장파급방지장치반 설치공사","2023-08-10 11:00","2023-08-10 12:00","2023-08-10 11:00","2023-08-10 12:00","연속"]
[26,"전북","김제","신김제S/S #1 BUS","신김제S/S 고장파급방지장치반 설치공사","신김제S/S 고장파급방지장치반 설치공사","2023-08-10 10:00","2023-08-10 11:00","2023-08-10 10:00","2023-08-10 11:00","연속"]
[27,"전북","김제","신김제S/S CB 7171","신김제S/S 고장파급방지장치반 설치공사","신김제S/S 고장파급방지장치반 설치공사","2023-08-10 14:00","2023-08-10 14:30","취소","취소","연속"]
[28,"대구","포항","월성N/P CB 7672","월성S/Y 7672 GIS 정밀점검","월성S/Y 7672 GIS 정밀점검","2023-08-16 09:00","2023-08-18 18:00","취소","취소","연속"]
[29,"대구","포항","울주월성NP#1 T/L","월성S/Y 7500,7572 GIS 정밀점검 무부하가압[TEST]","월성S/Y 7500,7572 GIS 정밀점검 무부하가압[TEST]","2023-08-04 17:00","2023-08-05 18:00","2023-08-04 17:00","2023-08-05 18:00","연속"]
[30,"대구","포항","월성N/P CB 7600","월성S/Y 7672 GIS 정밀점검","월성S/Y 7672 GIS 정밀점검","2023-08-16 09:00","2023-08-18 18:00","취소","취소","연속"]
[31,"대구","포항","울주월성NP#1 T/L","월성S/Y 7672 GIS 정밀점검","월성S/Y 7672 GIS 정밀점검[TEST]","2023-08-18 17:00","2023-08-18 18:00","2023-08-18 17:00","2023-08-18 18:00","연속"]
[32,"대구","포항","월성N/P #71 BUS","월성S/Y 7672 GIS 정밀점검","월성S/Y 7672 GIS 정밀점검[TEST]","2023-08-18 17:00","2023-08-18 18:00","2023-08-18 17:00","2023-08-18 18:00","연속"]
[33,"대구","포항","월성N/P CB 7671","월성S/Y 7672 GIS 정밀점검","월성S/Y 7672 GIS 정밀점검[TEST]","2023-08-18 17:00","2023-08-18 18:00","2023-08-18 17:00","2023-08-18 18:00","연속"]
[34,"부산울산","동부산","신양산S/S #3 M.Tr","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 74BAY 자재반입(안전이격)","2023-08-13 08:00","2023-08-13 18:00","2023-08-13 08:00","2023-08-13 18:00","연속"]
[35,"부산울산","동부산","신양산S/S #3 M.Tr","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 74BAY GIS 설치(안전이격)","2023-08-28 08:00","2023-08-31 18:00","2023-08-28 08:00","2023-08-31 18:00","매일"]
[36,"부산울산","울산","남울산S/S CB 7600","22~23년 변전협력회사 총액공사","- GIS(7600) 일진제 하자조치","2023-08-28 09:00","2023-08-30 18:00","2023-08-28 09:00","2023-08-30 18:00","연속"]
[37,"부산울산","울산","남울산S/S CB 7400","345kV 남울산S/S 울산GPS 신규수용공사","345kV 남울산S/S 울산GPS #1T/L 사용전검사","2023-08-16 09:00","2023-08-17 18:00","2023-08-16 09:00","2023-08-17 18:00","연속"]
[38,"부산울산","울산","남울산S/S CB 7472","345kV 남울산S/S 울산GPS 신규수용공사","남울산S/S GPS#1T/L 사용전검사","2023-08-16 09:00","2023-08-17 18:00","2023-08-16 09:00","2023-08-17 18:00","연속"]
[39,"부산울산","울산","신온산신울산#2 T/L","신울산S/S 345kV 용량대체공사","- 345kV GIS 대체 관련 송전선로 접속지점 변경(구 79BAY → 신 77BAY) - 345kV GIS 대체 관련 보호배전반 이설 및 연동시험","2023-08-16 09:00","2023-10-20 18:00","2023-08-16 09:00","2023-10-20 18:00","연속"]
[40,"부산울산","울산","동울산신울산 T/L","신울산S/S 345kV 용량대체공사","- 345kV GIS 대체 관련 송전선로 접속지점 변경(구 79BAY → 신 78BAY) - 345kV GIS 대체 관련 보호배전반 이설 및 연동시험","2023-08-16 09:00","2023-10-20 18:00","2023-08-16 09:00","2023-10-20 18:00","연속"]
[41,"부산울산","울산","신울산월성NP#1 T/L","신울산S/S 345kV 용량대체공사","- 345kV GIS 대체 관련 송전선로 접속지점 변경(구 78BAY → 신 79BAY) - 345kV GIS 대체 관련 보호배전반 이설 및 연동시험","2023-08-16 09:00","2023-10-20 18:00","2023-08-16 09:00","2023-10-20 18:00","연속"]
[42,"대구",null,"월성N/P #3 기동용변압기 (CB 7600, 7672)","월성3호기 20차 O/H 중 기동변압기 점검 * 조작차단기 : CB 7600, 7672","○ 기동용변압기 점검","2023-08-14 18:00","2023-08-23 18:00","2023-08-14 18:00","2023-08-23 18:00","연속"]
[43,"경북",null,"한울N/P #6호기 주변압기 (CB 7C00, 7C72)","6호기 13차 계획예방정비 * 조작차단기 : CB 7C00, 7C72","○ 주변압기 C상 정밀점검 ○ 주/소내보조/여자변압기 일반점검 ","2023-08-17 17:00","2023-09-14 16:00","2023-08-17 17:00","2023-09-14 16:00","연속"]

{"sheet":"154설비","index":2,"n_rows":95,"n_cols":11,"rows_kept":95,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 8월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","직할","중앙서소문 T/L","23년 직할 변전협력회사 총액공사","1. 공압식 전자변 교체","2023-08-01 10:00","2023-08-01 18:00","취소","취소","연속"]
[2,"남서울","동서울","도곡개포 T/L","154kV 개포-신양재,도곡T/L 지장이설공사","양재대로 구조개선 사업(지하차도 건설)에 따른 전력설비 이설 □ 사업구간 : 154kV 도곡-개포T/L J/B#1 ~ M/H#2 □ 주요공정 - 케이블 철거 : XLPE 2,000㎟, 1C-0.32km(기설전력구+관로) - 케이블 설치 : XLPE 2,000㎟, 1C-0.35km(신설전력구+관로) - 케이블 접속 : 2개소","2023-08-21 07:00","2023-09-03 18:00","취소","취소","연속"]
[3,"남서울","동서울","신양재개포 T/L","154kV 개포-신양재,도곡T/L 지장이설공사","양재대로 구조개선 사업(지하차도 건설)에 따른 전력설비 이설 □ 사업구간 : 154kV 신양재-개포T/L J/B#20 ~ M/H#19 □ 주요공정 - 케이블 철거 : XLPE 2,000㎟, 1C-0.32km(기설전력구+관로) - 케이블 설치 : XLPE 2,000㎟, 1C-0.35km(신설전력구+관로) - 케이블 접속 : 2개소","2023-08-21 07:00","2023-09-03 18:00","취소","취소","연속"]
[4,"남서울","동서울","풍납S/S CB 6100","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-08-28 09:00","2023-10-25 18:00","2023-08-28 09:00","2023-10-25 18:00","연속"]
[5,"남서울","동서울","풍납석촌#1 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-08-28 09:00","2023-10-13 18:00","2023-08-28 09:00","2023-10-13 18:00","연속"]
[6,"남서울","동서울","강동풍납#2 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-08-28 09:00","2023-10-25 18:00","2023-08-28 09:00","2023-10-25 18:00","연속"]
[7,"남서울","동서울","풍납S/S #1 BUS","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-08-28 09:00","2023-09-08 13:00","2023-08-28 09:00","2023-09-08 13:00","연속"]
[8,"남서울","동서울","풍납S/S #2 M.Tr CB","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-08-28 09:00","2023-10-25 18:00","취소","취소","연속"]
[9,"남서울","영등포","광명S/S #1 BUS","광명S/S 154kV 장기사용 GIS 교체공사","6차분(신광명-광명#2T/L, #1M.Tr GIS, TIE, PT) 철거 및 설치 - #1, 2DS, CB, CHD, 인출 설치 및 준공시험","2023-08-28 09:00","2023-09-21 18:00","2023-08-22 18:00","2023-09-21 18:00","연속"]
[10,"남서울","영등포","광명구공#1 T/L","광명S/S 154kV 장기사용 GIS 교체공사","6차분(신광명-광명#2T/L, #1M.Tr GIS, TIE, PT) 철거 및 설치 - #1BUS 무부하 가압 선로","2023-08-25 18:00","2023-08-26 18:00","2023-08-21 18:00","2023-08-22 18:00","연속"]
[11,"남서울","영등포","광명S/S #2 BUS","광명S/S 154kV 장기사용 GIS 교체공사","6차분(신광명-광명#2T/L, #1M.Tr GIS) 철거 및 설치 - #2BUS END Cover 설치","2023-08-23 09:00","2023-08-26 18:00","2023-08-21 10:00","2023-08-26 18:00","연속"]
[12,"남서울","영등포","신광명광명#2 T/L","광명S/S 154kV 장기사용 GIS 교체공사","6차분(신광명-광명#2T/L, #1M.Tr GIS, TIE, PT) 철거 및 설치 - #1, 2DS, CB, CHD, 인출 설치 및 준공시험","2023-08-23 09:00","2023-09-26 18:00","2023-08-21 10:00","2023-09-26 18:00","연속"]
[13,"인천","김포","양촌양곡#1 T/L","154kV 양곡S/S #5, 6M.Tr 증설공사","- #5, 6M.Tr 설치관련 안전이격거리 확보","2023-08-19 09:00","2023-08-20 18:00","2023-08-19 09:00","2023-08-20 18:00","연속"]
[14,"경기","직할","화성S/S #66 BUS","화성S/S 154kV SW증설(화성전철)","#66Sh.C #2BUS 철거 후 임시마감 처리","2023-08-05 09:00","2023-08-06 18:00","취소","취소","연속"]
[15,"경기","직할","화성S/S #67 BUS","화성S/S 154kV SW증설(화성전철)","#69Sh.C #2BUS 철거 후 임시마감 처리","2023-08-05 09:00","2023-08-06 18:00","취소","취소","연속"]
[16,"경기","직할","화성남양#1 T/L","화성S/S 154kV SW증설(화성전철)","#2BUS 임시마감 부 무부하가압","2023-08-06 13:00","2023-08-06 18:00","취소","취소","연속"]
[17,"경기","직할","화성S/S #62 BUS","화성S/S 154kV SW증설(화성전철)","#69Sh.C #1BUS 철거 후 화성전철GIS 설치","2023-08-06 18:00","2023-08-14 18:00","취소","취소","연속"]
[18,"경기","직할","화성S/S #61 BUS","화성S/S 154kV SW증설(화성전철)","#66Sh.C #1BUS 철거 후 화성전철 #1T/L #1BUS 및 CB 설치","2023-08-06 18:00","2023-08-14 18:00","취소","취소","연속"]
[19,"경기","직할","화성남양#1 T/L","화성S/S 154kV SW증설(화성전철)","#1BUS 무부하가압","2023-08-13 18:00","2023-08-14 18:00","취소","취소","연속"]
[20,"경기","직할","화성S/S #66 BUS","화성S/S 154kV SW증설(화성전철)","화성전철GIS #2BUS 설치","2023-08-14 18:00","2023-08-21 18:00","취소","취소","연속"]
[21,"경기","직할","화성S/S #67 BUS","화성S/S 154kV SW증설(화성전철)","화성전철GIS #2BUS 설치","2023-08-14 18:00","2023-08-21 18:00","취소","취소","연속"]
[22,"경기","직할","화성남양#1 T/L","화성S/S 154kV SW증설(화성전철)","#2BUS 무부하가압(DS투입)","2023-08-20 18:00","2023-08-21 18:00","취소","취소","연속"]
[23,"경기","직할","화성남양#1 T/L","화성S/S 154kV SW증설(화성전철)","#1BUS 무부하가압(DS투입)","2023-08-21 18:00","2023-08-22 18:00","취소","취소","연속"]
[24,"경기","직할","화성S/S #61 BUS","화성S/S 154kV SW증설(화성전철)","화성전철GIS #1BUS 무부하가압(DS투입)","2023-08-21 18:00","2023-08-22 18:00","취소","취소","연속"]
[25,"경기","직할","화성S/S #62 BUS","화성S/S 154kV SW증설(화성전철)","화성전철GIS #1BUS 무부하가압(DS투입)","2023-08-21 18:00","2023-08-22 18:00","취소","취소","연속"]
[26,"경기","평택","오산향남#1 T/L","(직할)철탑추락방지장치(수평) 설치공사","오산-향남, 오산-평택 병가 4회선 구간 철탑추락방지장치 설치","2023-08-07 07:00","2023-08-09 18:00","취소","취소","연속"]
[27,"경기","평택","오산평택#1 T/L","(직할)철탑추락방지장치(수평) 설치공사","오산-향남, 오산-평택 병가 4회선 구간 철탑추락방지장치 설치","2023-08-07 07:00","2023-08-09 18:00","취소","취소","연속"]
[28,"경기","평택","오산향남#2 T/L","(직할)철탑추락방지장치(수평) 설치공사","오산-향남, 오산-평택 병가 4회선 구간 철탑추락방지장치 설치","2023-08-10 07:00","2023-08-11 18:00","취소","취소","연속"]
[29,"경기","평택","오산평택#2 T/L","(직할)철탑추락방지장치(수평) 설치공사","오산-향남, 오산-평택 병가 4회선 구간 철탑추락방지장치 설치","2023-08-10 07:00","2023-08-11 18:00","취소","취소","연속"]
[30,"경기","평택","서운안성#1 T/L","세종-포천간 도로개설 관련 지장이설공사(154kV 1T/L)","철탑 5기 신설, 8기 철거","2023-08-28 07:00","2023-09-09 18:00","취소","취소","연속"]
[31,"강원","동해","동해T/P #2 BUS","23년 동해전력지사 변전정비팀 총액공사","PT 집합반 대체","2023-08-07 09:00","2023-08-08 18:00","취소","취소","매일"]
[32,"강원","동해","동해T/P #1 BUS","23년 동해전력지사 변전정비팀 총액공사","PT 집합반 대체","2023-08-07 09:00","2023-08-08 18:00","취소","취소","매일"]
[33,"강원","직할","남춘천춘천열병합#1 T/L","2023년 을지연습 실제훈련","○ 훈련명 : 2023년 을지연습 실제훈련 ○ 훈련내용 : 전력시설 긴급 피해복구 훈련 ○ 휴전대상 : 남춘천S/S 154kV 남춘천-춘천열병합 #1T/L","2023-08-02 09:00","2023-08-03 18:00","2023-08-02 09:00","2023-08-03 18:00","연속"]
[34,"강원","직할","남춘천춘천열병합#1 T/L","2023년 을지연습 실제훈련","○ 훈련명 : 2023년 을지연습 실제훈련 ○ 훈련내용 : 전력시설 긴급 피해복구 훈련 ○ 휴전대상 : 남춘천S/S 154kV 남춘천-춘천열병합 #1T/L","2023-08-21 09:00","2023-08-23 18:00","2023-08-21 09:00","2023-08-23 18:00","연속"]
[35,"강원","태백","영월영월에코윈드#2 T/L","154kV 태백T/L 선종 교체공사","전력선 교체: 영월S/S ~ No.77[37.22C-kM, ACMR/TW 240SQ*S)","2023-08-28 09:00","2023-11-30 18:00","2023-08-28 09:00","2023-11-30 18:00","연속"]
[36,"충북","충주","신제천S/S #62 BUS","345kV 신제천S/S #4 M.Tr 대체공사","#4 M.Tr 대체분 154kV 위상체크용","2023-08-28 14:00","2023-08-28 15:00","2023-08-28 14:00","2023-08-28 15:00","연속"]
[37,"대전세종충남","대전","금산무주#2 T/L","금산S/S 154kV 장기사용 GIS 교체공사","6333,657 GIS 교체 - 안전이격","2023-08-21 09:00","2023-08-21 15:00","취소","취소","연속"]
[38,"대전세종충남","대전","금산무주#2 T/L","금산S/S 154kV 장기사용 GIS 교체공사","6333,657 GIS 교체 - 안전이격 및 무부하","2023-08-10 09:00","2023-08-10 15:00","취소","취소","연속"]
[39,"대전세종충남","대전","금산무주#2 T/L","금산S/S 154kV 장기사용 GIS 교체공사","6333,657 GIS 교체 - 안전이격","2023-08-22 09:00","2023-08-22 15:00","취소","취소","연속"]
[40,"대전세종충남","대전","신옥천추부#2 T/L","(7월 취소시)[송전]345kV신옥천-청양 등7개T/L추락방지장치설치공사","(7월 취소시)[송전] 154kV 신옥천-추부T/L 추락방지장치 설치공사","2023-08-14 08:00","2023-08-25 18:00","2023-08-14 08:00","2023-08-25 18:00","매일"]
[41,"대전세종충남","대전","추부금산#1 T/L","(7월 취소시)[송전]345kV신옥천-청양 등7개T/L추락방지장치설치공사","(7월 취소시)[송전] 154kV 추부-금산T/L 추락방지장치 설치공사","2023-08-21 08:00","2023-08-25 18:00","2023-08-21 08:00","2023-08-25 18:00","매일"]
[42,"대전세종충남","세종","월산S/S #2 BUS","월산S/S 남부열병합#1,2T/L 증설공사","월산S/S 남부열병합#1,2T/L 증설 - 증설 선로 상회전 검사","2023-08-18 08:00","2023-08-18 18:00","취소","취소","연속"]
[43,"대전세종충남","세종","월산S/S CB 6100","월산S/S 남부열병합#1,2T/L 증설공사","월산S/S 남부열병합#1,2T/L 증설 - 모선보호반 연동시험","2023-08-17 08:00","2023-08-17 18:00","취소","취소","연속"]
[44,"대전세종충남","세종","세종월산#1 T/L","월산S/S 남부열병합#1,2T/L 증설공사","월산S/S 남부열병합#1,2T/L 증설 - 증설 선로 상회전 검사","2023-08-18 08:00","2023-08-18 18:00","취소","취소","연속"]
[45,"대전세종충남","세종","월산S/S #1 BUS","월산S/S 남부열병합#1,2T/L 증설공사","월산S/S 남부열병합#1,2T/L 증설 - 증설 선로 상회전 검사","2023-08-18 08:00","2023-08-18 18:00","취소","취소","연속"]
[46,"대전세종충남","청양","장항S/S CB 6100","장항S/S 154kV 장기사용 GIS 교체공사","154kV 한솔제지T/L GIS 교체","2023-08-31 14:00","2023-09-01 14:00","2023-08-31 14:00","2023-09-01 14:00","연속"]
[47,"대전세종충남","청양","장항S/S CB 6100","장항S/S 154kV 장기사용 GIS 교체공사","154kV 한솔제지T/L GIS 교체","2023-08-18 14:00","2023-08-19 14:00","2023-08-18 14:00","2023-08-19 14:00","연속"]
[48,"대전세종충남","청양","옥산장항#2 T/L","장항S/S 154kV 장기사용 GIS 교체공사","154kV 한솔제지T/L GIS 교체","2023-08-21 09:00","2023-08-23 14:00","취소","취소","연속"]
[49,"대전세종충남","청양","옥산장항#2 T/L","장항S/S 154kV 장기사용 GIS 교체공사","154kV 한솔제지T/L GIS 교체","2023-08-31 14:00","2023-09-01 14:00","취소","취소","연속"]
[50,"대전세종충남","청양","장항S/S 한솔제지T/L CB","장항S/S 154kV 장기사용 GIS 교체공사","154kV 한솔제지T/L GIS 교체","2023-08-28 09:00","2023-09-01 14:00","2023-08-28 09:00","2023-09-01 14:00","연속"]
[51,"대전세종충남","청양","장항S/S CB 6100","장항S/S 154kV 장기사용 GIS 교체공사","154kV 한솔제지T/L GIS 교체","2023-08-22 14:00","2023-08-23 14:00","2023-08-22 14:00","2023-08-23 14:00","연속"]
[52,"전북","군산","군산동군산#1 T/L","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사(시험가압)","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-08-26 09:00","2023-08-27 09:00","취소","취소","연속"]
[53,"전북","군산","군산동군산#1 T/L","154kV 동군산S/S-군산CC T/L 개폐장치 증설공사(시험가압)","170kV GIS X 2CCT (동군산 1CCT, 군산CC 1CCT)","2023-08-19 09:00","2023-08-20 09:00","취소","취소","연속"]
[54,"전북","김제","정주고창#2 T/L","고창S/S 고장파급방지장치반 설치공사","고창S/S 고장파급방지장치반 설치공사","2023-08-04 11:00","2023-08-04 12:00","2023-08-02 18:00","2023-08-02 20:00","연속"]
[55,"전북","김제","정주고창#1 T/L","고창S/S 고장파급방지장치반 설치공사","고창S/S 고장파급방지장치반 설치공사","2023-08-04 10:00","2023-08-04 11:00","2023-08-02 16:00","2023-08-02 18:00","연속"]
[56,"전북","김제","서고창S/S 해상풍력T/L CB","서고창S/S 고장파급방지장치반 설치공사","서고창S/S 고장파급방지장치반 설치공사","2023-08-23 10:00","2023-08-23 12:00","2023-08-07 09:00","2023-08-07 18:00","연속"]
[57,"전북","김제","정주고창#1 T/L","정주S/S 154kV 정주-고창#1T/L 보통점검","정주S/S 154kV 정주-고창#1T/L 보통점검","2023-08-28 09:00","2023-08-28 18:00","2023-08-28 15:00","2023-08-28 19:00","연속"]
[58,"전북","김제","정주고창#2 T/L","정주S/S 154kV 정주-고창#2T/L 보통점검","정주S/S 154kV 정주-고창#2T/L 보통점검","2023-08-29 09:00","2023-08-29 18:00","2023-08-29 15:00","2023-08-29 19:00","연속"]
[59,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","No.33∼36 전력선 연긴선","2023-08-21 08:00","2023-08-24 17:00","취소","취소","연속"]
[60,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","No.33∼36 전력선 연긴선","2023-08-28 08:00","2023-08-31 17:00","취소","취소","연속"]
[61,"전북","군산","팔봉S/S CB 6100"," 팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검"," 팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","2023-08-22 09:00","2023-08-24 18:00","2023-08-22 09:00","2023-08-24 18:00","연속"]
[62,"전북","군산","팔봉S/S #60 BUS"," 팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검"," 팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","2023-08-22 09:00","2023-08-23 18:00","2023-08-22 09:00","2023-08-23 18:00","연속"]
[63,"전북","군산","영등팔봉#1 T/L"," 팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검"," 팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","2023-08-23 17:00","2023-08-23 18:00","2023-08-23 17:00","2023-08-23 18:00","연속"]
[64,"전북","군산","팔봉S/S #65 BUS"," 팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검"," 팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","2023-08-24 09:00","2023-08-24 18:00","2023-08-24 09:00","2023-08-24 18:00","연속"]
[65,"전북","군산","영등팔봉#1 T/L"," 팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검"," 팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","2023-08-24 17:00","2023-08-24 18:00","2023-08-24 17:00","2023-08-24 18:00","연속"]
[66,"광주전남","강진","완도강진 T/L","154kV 남창-완도1π분기T/L 건설공사","ㅁ 사업목적 : #3HVDC 완도변환소 AC 배후 전력계통 연계 ㅁ 사업구간 : 기설 154kV 남창-완도T/L No.42호 - 신설 완도변환소 ㅁ 사업규모 : ASCC/TW 520㎟×S×2C×2.0㎞×철탑 6기(C/T 1기 포함)","2023-08-25 08:00","2023-08-27 18:00","2023-08-25 08:00","2023-08-27 18:00","연속"]
[67,"광주전남","광주","신광주일곡#1 T/L","22년 광주전력 철탑추락방지장치 설치공사","154kV 신광주-일곡T/L 철탑추락방지장치(수평) 설치 공사구간 : No.16~21호(6기)","2023-08-28 07:00","2023-08-28 18:00","취소","취소","연속"]
[68,"광주전남","광주","신광주일곡#2 T/L","22년 광주전력 철탑추락방지장치 설치공사","154kV 신광주-일곡T/L 철탑추락방지장치(수평) 설치 공사구간 : No.16~21호(6기)","2023-08-29 07:00","2023-08-29 18:00","취소","취소","연속"]
[69,"광주전남","광주","신광주장성#1 T/L","22년 광주전력 철탑추락방지장치 설치공사","154kV 신광주-장성T/L 철탑추락방지장치(수평) 설치 공사구간 : No.7~72호(65기)","2023-08-21 07:00","2023-08-28 18:00","2023-08-21 07:00","2023-08-28 15:00","매일"]
[70,"광주전남","광주","신광주장성#2 T/L","22년 광주전력 철탑추락방지장치 설치공사","154kV 신광주-장성T/L 철탑추락방지장치(수평) 설치 공사구간 : No.7~72호(65기)","2023-08-29 07:00","2023-09-03 18:00","2023-08-29 07:00","2023-09-03 15:00","매일"]
[71,"광주전남","목포","영광S/S 함구미태양광T/L CB","[변전] 영광S/S 임시 SPS반 설치","- [즉시가압가능] 광전본(계통)-8153 관련 임시 SPS반 설치","2023-08-10 15:00","2023-08-10 18:00","2023-08-07 09:00","2023-08-07 18:00","연속"]
[72,"광주전남","목포","장성영광#1 T/L","[변전] 영광S/S 임시 SPS반 설치","- [즉시가압가능] 광전본(계통)-8153 관련 임시 SPS반 설치","2023-08-10 09:00","2023-08-10 13:00","2023-08-04 16:00","2023-08-04 18:00","연속"]
[73,"광주전남","목포","장성영광#2 T/L","[변전] 영광S/S 임시 SPS반 설치","- [즉시가압가능] 광전본(계통)-8153 관련 임시 SPS반 설치","2023-08-10 13:00","2023-08-10 18:00","2023-08-04 18:00","2023-08-04 20:00","연속"]
[74,"광주전남","목포","영광S/S 백수풍력T/L CB","[변전] 영광S/S 임시 SPS반 설치","- [즉시가압가능] 광전본(계통)-8153 관련 임시 SPS반 설치","2023-08-10 15:00","2023-08-10 18:00","2023-08-07 09:00","2023-08-07 18:00","연속"]
[75,"광주전남","목포","영광S/S 재원태양광T/L CB","[변전] 영광S/S 임시 SPS반 설치","- [즉시가압가능] 광전본(계통)-8153 관련 임시 SPS반 설치","2023-08-10 15:00","2023-08-10 18:00","2023-08-07 09:00","2023-08-07 18:00","연속"]
[76,"대구","달성","구지서구지#2 T/L","154kV 서구지S/S 엘앤에프 신규수용공사","170kV GIS * 2CCT 설치 무부하 가압[TEST 선로]","2023-08-29 09:00","2023-08-30 18:00","2023-08-29 09:00","2023-08-30 18:00","연속"]
[77,"대구","달성","서구지S/S #61 BUS","154kV 서구지S/S 엘앤에프 신규수용공사","170kV GIS * 2CCT 설치","2023-08-28 09:00","2023-08-30 18:00","2023-08-28 09:00","2023-08-30 18:00","연속"]
[78,"대구","달성","구지서구지#1 T/L","154kV 서구지S/S 엘앤에프 신규수용공사","170kV GIS * 2CCT 설치 무부하 가압[TEST 선로]","2023-08-11 09:00","2023-08-12 18:00","2023-08-11 09:00","2023-08-12 18:00","연속"]
[79,"대구","달성","서구지S/S #60 BUS","154kV 서구지S/S 엘앤에프 신규수용공사","170kV GIS * 2CCT 설치","2023-08-07 09:00","2023-08-09 18:00","2023-08-07 09:00","2023-08-09 18:00","연속"]
[80,"대구","달성","구지서구지#1 T/L","154kV 서구지S/S 엘앤에프 신규수용공사","170kV GIS * 2CCT 설치 무부하 가압[TEST 선로]","2023-08-08 09:00","2023-08-09 18:00","2023-08-08 09:00","2023-08-09 18:00","연속"]
[81,"대구","달성","서구지S/S #66 BUS","154kV 서구지S/S 엘앤에프 신규수용공사","170kV GIS * 2CCT 설치","2023-08-31 09:00","2023-09-02 18:00","2023-08-31 09:00","2023-09-02 18:00","연속"]
[82,"대구","달성","서구지S/S #65 BUS","154kV 서구지S/S 엘앤에프 신규수용공사","170kV GIS * 2CCT 설치","2023-08-10 09:00","2023-08-12 18:00","2023-08-10 09:00","2023-08-12 18:00","연속"]
[83,"대구","달성","강창성서#2 T/L","154kV 성서S/S 지역난방 신규수용공사","○ 170kV GIS 2CCT 증설 무부하 가압[Test 선로]","2023-08-26 14:00","2023-08-27 18:00","취소","취소","연속"]
[84,"대구","달성","성서S/S #2 BUS","154kV 성서S/S 지역난방 신규수용공사","○ 170kV GIS 2CCT 증설","2023-08-28 09:00","2023-09-03 18:00","취소","취소","연속"]
[85,"대구","달성","성서S/S #1 BUS","154kV 성서S/S 지역난방 신규수용공사","○ 170kV GIS 2CCT 증설","2023-08-23 09:00","2023-08-27 18:00","취소","취소","연속"]
[86,"대구","달성"," 팔달S/S 대구염색T/L CB","구역전기사업자 정기검사","구역전기사업자 정기검사","2023-08-13 09:00","2023-08-15 14:00","취소","취소","연속"]
[87,"대구","포항","영일입실 T/L","입실S/S 154kV 60-61 GIS 점검","입실S/S 154kV 60-61 GIS 점검[TEST]","2023-08-23 18:00","2023-08-24 18:00","취소","취소","연속"]
[88,"경남","통영","진동안정#2 T/L","154kV 통영복합S/Y 건설공사","154kV 통영복합S/Y 건설 - 154kV GIS 13CCT 설치 - 보호배전반이설 및 신설 - 기타부대공사 154kV 고성-안정1T/L 선로분기 작업","2023-08-31 09:00","2023-09-03 18:00","취소","취소","연속"]
[89,"경남","통영","고성안정#1 T/L","154kV 통영복합S/Y 건설공사","154kV 통영복합S/Y 건설 - 154kV GIS 13CCT 설치 - 보호배전반이설 및 신설 - 기타부대공사 154kV 고성-안정1T/L 선로분기 작업","2023-08-31 09:00","2023-09-03 18:00","취소","취소","연속"]
[90,"경남","통영","고성안정#2 T/L","154kV 통영복합S/Y 건설공사","154kV 통영복합S/Y 건설 - 154kV GIS 13CCT 설치 - 보호배전반이설 및 신설 - 기타부대공사","2023-08-24 09:00","2023-08-30 18:00","취소","취소","연속"]
[91,"경남","통영","진동안정#1 T/L","154kV 통영복합S/Y 건설공사","154kV 통영복합S/Y 건설 - 154kV GIS 13CCT 설치 - 보호배전반이설 및 신설 - 기타부대공사 154kV 고성-안정2T/L 선로분기 작업","2023-08-24 09:00","2023-08-27 18:00","취소","취소","연속"]