{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":25,"n_cols":11,"rows_kept":25,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2023년도 10월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신태백신가평#2 T/L","송전선로 단상재폐로 결상회로 개선","송운(변전)-1085 (21.10.19) 「송전선로 단상 자동재투입용 GIS 결상회로 개선 시행 알림」 관련 유사고장 재발방지","2023-10-19 09:00","2023-10-19 18:00","취소","취소","연속"]
[2,"경기북부","구리","신가평S/S #4 M.Tr","23년도 신가평S/S 765kV M.Tr 보통점검공사","신가평S/S 765kV #4M.Tr 보통점검","2023-10-30 09:00","2023-11-03 18:00","2023-10-30 09:00","2023-11-03 18:00","연속"]
[3,"경기","성남","신안성S/S #4 M.Tr","23년 성남전력 765kV M.Tr 보통점검공사","- #4M.Tr 보통점검","2023-10-18 09:00","2023-10-31 18:00","2023-10-18 09:00","2023-10-31 18:00","연속"]
[4,"경기","성남","신안성신가평 T/L","2022-2023년 성남전력지사 가공송전 협력회사 총액공사(도장)","항공장애표지도장 33호 등 26기","2023-10-14 09:00","2023-10-28 18:00","취소","취소","매일"]
[5,"강원","태백","신태백신가평#1 T/L","22~23년 태백전력지사 가공송전 협력회사 총액공사","항공순시번호찰 교체","2023-10-23 09:00","2023-10-25 18:00","취소","취소","매일"]
[6,"충북","직할","신중부S/S #3 M.Tr","신중부S/S 765kV #3M.Tr 주변압기 휴전","권선온도계 동작, 변압기 상부 누유여부 확인 등 현장점검 시행","2023-10-05 10:00","2023-10-06 18:00","2023-10-05 10:00","2023-10-06 18:00","연속"]
[7,"충북","직할","신중부S/S #5 M.Tr","신중부S/S 345kV DS 내부부품 교체 작업","345kV GIS DS부 부분방전 발생에 따른 DS 내부부품 교체공사 대상 : 7B61, 7B01DS(2대)","2023-10-25 09:00","2023-10-26 18:00","2023-10-25 09:00","2023-10-26 18:00","연속"]
[8,"충북","직할","신중부S/S #4 M.Tr","신중부S/S 345kV DS 내부부품 교체 작업","345kV GIS DS부 부분방전 발생에 따른 DS 내부부품 교체공사 대상 : 7961, 7901DS(2대)","2023-10-23 09:00","2023-10-24 18:00","2023-10-23 09:00","2023-10-24 18:00","연속"]
[9,"대전세종충남","서산","당진T/P CB 8571","23년 서산P/O 765kV GIS 보통점검공사","당진화력S/S 765kV 8571 GIS 보통점검","2023-10-27 09:00","2023-10-27 18:00","2023-10-27 09:00","2023-10-27 18:00","연속"]
[10,"대전세종충남","서산","당진T/P Tie-Tr","당진화력S/S 765kV #1TIE-Tr B상 교체공사","(9월 휴전 취소시) 당진화력S/S 765kV #1TIE-Tr B상 교체공사 (병행) 당진화력S/S 765kV #1TIE-Tr B상 1,2차 GIB 교체공사 (장대현)","2023-10-01 09:00","2023-10-27 18:00","2023-10-29 09:00","2023-11-24 18:00","연속"]
[11,"대전세종충남","서산","신서산당진TP#1 T/L","당진화력S/S 765kV #1TIE-Tr B상 교체공사","(9월 휴전 취소시) 안전이격거리 확보를 위한 신서산-당진화력#1T/L 휴전","2023-10-01 09:00","2023-10-01 18:00","2023-10-29 09:00","2023-10-29 18:00","연속"]
[12,"대전세종충남","서산","당진T/P CB 8372","23년 서산P/O 765kV GIS 보통점검공사","당진화력S/S 765kV 8372 GIS 보통점검","2023-10-23 09:00","2023-10-23 18:00","2023-10-23 09:00","2023-10-23 18:00","연속"]
[13,"대전세종충남","서산","신서산신중부#2 T/L","'23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 765kV 86BAY B/F반 대체 (병행) 신서산S/S 765kV 8671, 8600 GIS 보통점검","2023-10-16 09:00","2023-10-20 18:00","취소","취소","연속"]
[14,"대전세종충남","서산","신서산당진TP#1 T/L","765kV 신서산-당진화력#1T/L 정밀점검","765kV 신서산-당진화력#1T/L 정밀점검[주말제외,매일]","2023-10-16 08:00","2023-10-27 18:00","취소","취소","매일"]
[15,"대전세종충남","서산","신서산S/S #3 M.Tr","'23년 서산P/O 변전협력회사 총액공사","신서산S/S 765kV #3M.Tr C상 Left 유면계 교체","2023-10-28 09:00","2023-10-29 18:00","2023-10-28 09:00","2023-10-29 18:00","연속"]
[16,"대전세종충남","서산","신서산S/S #2 BUS","'23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 765kV #2BUS 보호반 대체 (병행) 신서산S/S 765kV #2BUS 가스누기 보수공사","2023-10-30 09:00","2023-11-03 18:00","2023-10-30 09:00","2023-11-03 18:00","연속"]
[17,"부산울산","동부산","신고리N/P #1 Tie-Tr","신고리S/S 종합예방진단시스템 대체공사","- #1M.Tr 부싱누설전류 어댑터 설치 및 감도시험 - #1M.Tr OLTC 구동부 감시센서 설치, TAP 모듈 교체, 시험 - 유중가스 배관 및 후렌치 설치 - 차단기 동작분석장치 시험(GIS 차단기 투/개방 시험)","2023-10-16 09:00","2023-10-24 18:00","취소","취소","연속"]
[18,"부산울산","동부산","신고리N/P #4 Tie-Tr","신고리S/S 765kV #4M.Tr 하자점검","신고리S/S 765kV #4M.Tr 하자점검","2023-10-10 09:00","2023-10-14 18:00","취소","취소","연속"]
[19,"경남","함안","북경남S/S #4 M.Tr","북경남S/S 765kV #4 M.Tr 보통점검","북경남S/S 765kV #4 M.Tr 보통점검","2023-10-16 09:00","2023-10-20 18:00","취소","취소","연속"]
[20,"경남","함안","북경남S/S #5 M.Tr","북경남S/S 765kV #5 M.Tr 보통점검","북경남S/S 765kV #5 M.Tr 보통점검","2023-10-09 09:00","2023-10-13 18:00","취소","취소","연속"]
[21,"경남","함안","북경남S/S #3 M.Tr","북경남S/S 765kV #3 M.Tr 보통점검","북경남S/S 765kV #3 M.Tr 보통점검","2023-10-23 09:00","2023-10-27 18:00","취소","취소","연속"]

{"sheet":"345설비","index":1,"n_rows":395,"n_cols":11,"rows_kept":395,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2023년도 10월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #1 M.Tr","2023년 성동P/O 변전협력회사 총액공사","- M.Tr, 3차 LA, 3차 PT 보통점검 - 170kV GIS 조작시험 - 변압기실 공조 FAN 교체 - M.Tr PNL 교체","2023-10-10 10:00","2023-11-17 18:00","2023-10-10 10:00","2023-11-17 18:00","연속"]
[2,"서울","성동","성동S/S #4 M.Tr","2023년 성동P/O 변전협력회사 총액공사","- M.Tr, 3차 LA, 3차 PT 보통점검 - 170kV GIS 조작시험","2023-10-19 10:00","2023-10-20 18:00","취소","취소","연속"]
[3,"서울","성동","미금성동#2 T/L","2023년 성동P/O 변전협력회사 총액공사","-B/F PNL 교체","2023-10-30 09:00","2023-11-01 18:00","취소","취소","연속"]
[4,"서울","성동","성동S/S #2 M.Tr","2023년 성동P/O 변전협력회사 총액공사","- M.Tr, 3차 LA, 3차 PT 보통점검 - 170kV GIS 조작시험 - 변압기실 공조 FAN 교체 - M.Tr PNL 교체","2023-10-30 10:00","2023-11-07 18:00","취소","취소","연속"]
[5,"서울","성동","미금성동#1 T/L","2023년 성동P/O 변전협력회사 총액공사","-B/F PNL 교체","2023-10-10 09:00","2023-10-12 18:00","2023-10-10 09:00","2023-10-12 18:00","연속"]
[6,"서울","중부","중부S/S CB 7171","22-23 중부P/O 총액공사","보통점검","2023-10-23 10:00","2023-10-23 17:00","취소","취소","연속"]
[7,"서울","중부","중부S/S #2 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(시험가압)","- #3M.Tr 2차, 중부용산#2T/L GIS 교체 - #61BUS 시험가압","2023-10-21 16:00","2023-10-23 09:00","취소","취소","연속"]
[8,"서울","중부","중부S/S #1 Sh.R CB","22-23 중부P/O 총액공사","1차 GIS 스탑밸브 교체","2023-10-12 10:00","2023-10-12 17:00","2023-10-24 10:00","2023-10-24 17:00","연속"]
[9,"서울","중부","중부S/S #2 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(시험가압)","- #3M.Tr 2차, 중부용산#2T/L GIS 교체 - #66BUS 시험가압","2023-10-11 09:00","2023-10-11 18:00","취소","취소","연속"]
[10,"서울","중부","중부S/S #3 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사","- #3M.Tr 2차, 중부용산#2T/L GIS 교체 - #3M.Tr 2차 LA 설치","2023-10-10 09:00","2023-11-03 18:00","2023-10-10 09:00","2023-11-03 18:00","연속"]
[11,"서울","중부","중부S/S CB 7100","22-23 중부P/O 총액공사","보통점검","2023-10-23 10:00","2023-10-23 17:00","취소","취소","연속"]
[12,"서울","중부","중부S/S CB 7271","22-23 중부P/O 총액공사","보통점검","2023-10-24 10:00","2023-10-24 17:00","취소","취소","연속"]
[13,"서울","중부","중부S/S CB 7200","22-23 중부P/O 총액공사","조작시험","2023-10-24 10:00","2023-10-24 17:00","취소","취소","연속"]
[14,"서울","중부","중부S/S #2 M.Tr","22-23 중부P/O 총액공사","보통점검","2023-10-25 10:00","2023-10-25 17:00","취소","취소","연속"]
[15,"서울","중부","중부S/S CB 7400","22-23 중부P/O 총액공사","조작시험","2023-10-26 10:00","2023-10-26 17:00","취소","취소","연속"]
[16,"서울","중부","중부S/S CB 7471","22-23 중부P/O 총액공사","보통점검","2023-10-26 10:00","2023-10-26 17:00","취소","취소","연속"]
[17,"남서울","강남","신양재S/S #1 M.Tr","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 : #1M.Tr 2차 GIS","2023-10-04 09:00","2023-10-05 18:00","2023-10-04 09:00","2023-10-05 18:00","연속"]
[18,"남서울","강남","신양재S/S #3 M.Tr","22-23년도 강남전력지사 변전협력회사 총액공사","- #3M.Tr 1차 GIS 보통점검(7300, 7372) - #3M.Tr 2차 GIS 조작시험","2023-10-10 08:00","2023-10-11 17:00","2023-10-10 08:00","2023-10-11 17:00","연속"]
[19,"남서울","강남","신성남신양재#1 T/L","345kV 신성남-신양재#1,2T/L(S) 유지접속함(7상) 교체공사","345kV 신성남-신양재#1,2T/L(S) 유지접속함(7상) 교체","2023-10-04 09:00","2023-11-30 18:00","2023-10-04 09:00","2023-11-30 18:00","연속"]
[20,"남서울","동서울","곤지암동서울#1 T/L","22~23 동서울전력지사 가공송전 협력회사 총액공사","추락방지시설 설치(수직,수평) 25기","2023-10-16 07:00","2023-10-19 17:00","2023-10-16 07:00","2023-10-19 17:00","연속"]
[21,"남서울","동서울","곤지암동서울#2 T/L","22~23 동서울전력지사 가공송전 협력회사 총액공사","추락방지시설 설치(수직,수평) 25기","2023-10-23 07:00","2023-10-26 17:00","2023-10-23 07:00","2023-10-26 17:00","연속"]
[22,"남서울","동서울","동서울S/S SEC CB 70710","동서울S/S 70-71 SEC GIS 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-10-19 09:00","2023-10-19 18:00","2023-10-19 09:00","2023-10-19 18:00","연속"]
[23,"남서울","동서울","동서울S/S SEC CB 75760","동서울S/S 70-71 SEC GIS 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[24,"남서울","영등포","서서울신광명#1 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지설치, 피뢰기설치","2023-10-16 07:00","2023-10-27 18:00","취소","취소","연속"]
[25,"남서울","영등포","신광명S/S #3 M.Tr","2022~23년 영등포전력지사 변전협력회사 총액공사","- 345kV #3M.Tr 보호배전반 교체공사","2023-10-10 09:00","2023-10-18 18:00","2023-10-10 09:00","2023-10-18 18:00","연속"]
[26,"남서울","영등포","신광명S/S #4 M.Tr","2022~23년 영등포전력지사 변전협력회사 총액공사","#4M.Tr 초기점검","2023-10-25 09:00","2023-10-27 18:00","2023-10-25 09:00","2023-10-27 18:00","연속"]
[27,"남서울","영등포","신시흥신광명#1 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지설치","2023-10-01 07:00","2023-10-03 18:00","2023-10-01 07:00","2023-10-03 18:00","연속"]
[28,"남서울","영등포","신광명S/S #1 M.Tr","2022~23년 영등포전력지사 변전협력회사 총액공사","- 345kV #1M.Tr 보통점검 - 170kV GIS 보통점검 - 23kV VCB 교체 및 점검","2023-10-04 09:00","2023-10-06 18:00","2023-10-04 09:00","2023-10-06 18:00","연속"]
[29,"인천","김포","신김포신인천CC T/L","345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사","추락방지시설 설치공사","2023-10-10 09:00","2023-10-13 18:00","2023-10-10 09:00","2023-10-13 18:00","연속"]
[30,"인천","김포","신김포서인천CC T/L","345kV 신김포-서(신)인천CCT/L 추락방지시설 설치공사","추락방지시설 설치공사","2023-10-04 09:00","2023-10-07 18:00","취소","취소","연속"]
[31,"인천","부평","서인천C/C CB 7100","서인천C/C 7100 GIS 보통점검","신김포서인천CCT/L-#1M.Tr 1차 TIE 7100 GIS 보통점검 (전자변L 교체)","2023-10-05 09:00","2023-10-05 18:00","2023-10-05 09:00","2023-10-05 18:00","연속"]
[32,"인천","부평","서인천C/C CB 7171","서인천C/C 신김포-서인천CC T/L 7171 GIS 보통점검","서인천C/C 신김포-서인천CC T/L 7171 GIS 보통점검 (전자변L 교체)","2023-10-04 09:00","2023-10-04 18:00","2023-10-04 09:00","2023-10-04 18:00","연속"]
[33,"인천","부평","서인천C/C CB 7172","서인천C/C #1 M.Tr 1차 7172 GIS 보통점검","서인천C/C #1 M.Tr 1차 7172 GIS 보통점검 (전자변 L 교체)","2023-10-02 09:00","2023-10-02 18:00","2023-10-20 09:00","2023-10-20 18:00","연속"]
[34,"인천","부평","서인천C/C #2 M.Tr","서인천C/C 345kV #2 M.Tr 보통점검","서인천C/C 345kV #2 M.Tr 보통점검","2023-10-16 09:00","2023-10-18 18:00","2023-10-16 09:00","2023-10-18 18:00","연속"]
[35,"인천","부평","서인천C/C #1 Sh.R CB","서인천C/C 345kV #1 Sh.R 보통점검","서인천C/C 345kV #1 Sh.R 보통점검","2023-10-19 09:00","2023-10-20 18:00","취소","취소","연속"]
[36,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S 345kV #1 M.Tr 휴전작업","345kV #1 M.Tr 보호반 대체 345kV #1 M.Tr 2,3차 GIS 보통점검 신가좌S/S 23kV #1-1 Sh.R 및 전용 CB 보통점검","2023-10-09 09:00","2023-10-13 18:00","2023-10-09 09:00","2023-10-13 18:00","연속"]
[37,"인천","부평","신가좌가정#1 T/L","신가좌S/S 345kV #2CLR 보통점검","신가좌S/S 345kV #2CLR 보통점검","2023-10-14 09:00","2023-10-14 18:00","2023-10-14 09:00","2023-10-14 18:00","연속"]
[38,"인천","부평","신가좌가정#2 T/L","신가좌S/S 345kV #1CLR 보통점검","신가좌S/S 345kV #1CLR 보통점검","2023-10-21 09:00","2023-10-21 18:00","2023-10-21 09:00","2023-10-21 18:00","연속"]
[39,"인천","부평","신가좌S/S CB 7200","신가좌S/S 7200 GIS 보통점검","신가좌가정#1-신가좌신시흥#1T/L TIE 7200 GIS 보통점검","2023-10-23 09:00","2023-10-23 18:00","2023-10-23 09:00","2023-10-23 18:00","연속"]
[40,"인천","부평","신가좌S/S CB 7371","신가좌S/S 신가좌신시흥#1T/L 7371 GIS 하자점검","345kV 신가좌신시흥#1T/L 7371 GIS 하자점검","2023-10-06 09:00","2023-10-06 18:00","2023-10-06 09:00","2023-10-06 18:00","연속"]
[41,"인천","부평","신가좌가정#1 T/L","신가좌S/S 신가좌-가정#1T/L 7271 GIS 하자점검","신가좌S/S 신가좌-가정#1T/L 7271 GIS 하자점검","2023-10-04 09:00","2023-10-04 18:00","취소","취소","연속"]
[42,"인천","부평","신가좌신시흥#1 T/L","신가좌S/S 345kV 신가좌-신시흥#1T/L 7272GIS 보통점검","신가좌S/S 345kV 신가좌-신시흥#1T/L 7272GIS 보통점검","2023-10-05 09:00","2023-10-05 18:00","취소","취소","연속"]
[43,"인천","부평","신경서S/S #2 M.Tr","신경서S/S 345kV #2 M.Tr 휴전작업","신경서S/S 345kV #2 M.Tr 3차 4289CB 보통점검 신경서S/S 345kV #2 M.Tr 1차 7272GIS 조작시험","2023-10-13 09:00","2023-10-13 18:00","2023-10-13 09:00","2023-10-13 18:00","연속"]
[44,"인천","부평","신경서S/S #3 M.Tr","신경서S/S 345kV #3 M.Tr OFU 필터교체 공사","신경서S/S 345kV #3 M.Tr OFU 필터교체 공사","2023-10-14 09:00","2023-10-14 18:00","2023-10-14 09:00","2023-10-14 18:00","연속"]
[45,"인천","부평","신경서신인천CC T/L","신인천C/C 신경서-신인천C/C T/L 7871GIS 보통점검","신경서-신인천C/C T/L 7871GIS (전자변 L 교체)","2023-10-06 09:00","2023-10-06 18:00","2023-10-06 09:00","2023-10-06 18:00","연속"]
[46,"인천","부평","인천C/C CB 7271","인천CC S/Y 345kV 7251DS PD 발생 관련 내부점검","인천CC S/Y 345kV 7251DS PD 발생 관련 내부점검","2023-10-01 09:00","2023-10-03 18:00","취소","취소","연속"]
[47,"인천","부평","인천C/C #70 BUS","인천CC S/Y 345kV 7251DS PD 발생 관련 내부점검","인천CC S/Y 345kV 7251DS PD 발생 관련 내부점검","2023-10-01 09:00","2023-10-03 18:00","취소","취소","연속"]
[48,"인천","부평","인천C/C CB 7472","인천CC S/Y 345kV 가정-인천CC#1T/L 7472GIS 보통점검","인천CC S/Y 345kV 가정-인천CC#1T/L 7472GIS 보통점검 (전자변L 교체)","2023-10-09 09:00","2023-10-09 18:00","2023-10-09 09:00","2023-10-09 18:00","연속"]
[49,"인천","부평","인천C/C CB 7571","인천CC345kV 인천복합 #3,4 G/T 7571GIS 보통점검","인천CC 345kV 인천복합 #3,4 G/T 7571GIS 보통점검","2023-10-24 09:00","2023-10-24 18:00","2023-10-24 09:00","2023-10-24 18:00","연속"]
[50,"인천","부평","인천C/C #1 Tie-Tr","인천CC S/Y 345kV #1 TIE TR 휴전작업","인천CC S/Y 345kV #1 TIE Tr 보통점검 인천CC S/Y 345kV #1 TIE Tr 3차측 CT 결선 변경 인천CC S/Y 345kV #1 TIE Tr 1차 7171GIS 조작시험","2023-10-25 09:00","2023-10-27 18:00","취소","취소","연속"]
[51,"인천","부평","인천C/C CB 7400","인천C/C 7400 GIS 보통점검","신경서인천CC#2-가정인천CC#1T/L TIE 7400 GIS 보통점검 (전자변 L 교체)","2023-10-10 09:00","2023-10-10 18:00","2023-10-10 09:00","2023-10-10 18:00","연속"]
[52,"인천","시흥","신시흥영흥TP#3 T/L","345kV 신시화분기T/L 건설공사","1) 기설 345kV 영흥T/L No.55 - 신설No.1 C/T 2) 기설 345kV 영흥T/L No.58 - 신설No.2 C/T 3) 기설 345kV 영흥T/L No.72 - 기설 345kV 신시흥S/S 인출정비","2023-10-14 07:00","2023-11-03 18:00","2023-10-14 07:00","2023-11-03 18:00","연속"]
[53,"인천","시흥","신시흥#1S/S #2 M.Tr","효성제 170kV GIS 베어링 발청 관련 부품 교체","신시흥S/S #2M.Tr 2차 GIS 베어링 부품 교체","2023-10-20 09:00","2023-10-20 14:00","취소","취소","연속"]
[54,"인천","시흥","신시흥S/S #70 BUS","345kV 신시화S/S 건설공사","345kV 신시화S/S 초기가압","2023-10-10 09:00","2023-10-11 09:00","2023-10-10 09:00","2023-10-11 09:00","연속"]
[55,"인천","시흥","신시흥신안산#2 T/L","345kV 신시화S/S 건설공사","345kV 신시화S/S 초기가압","2023-10-10 09:00","2023-10-11 09:00","2023-10-10 09:00","2023-10-11 09:00","연속"]
[56,"인천","시흥","신시흥영흥TP#1 T/L","345kV 신시화분기T/L 건설공사","1) 기설 345kV 영흥T/L No.55 - 신설No.1 C/T 2) 기설 345kV 영흥T/L No.58 - 신설No.2 C/T 3) 기설 345kV 영흥T/L No.72 - 기설 345kV 신시흥S/S 인출정비","2023-10-14 07:00","2023-11-03 18:00","2023-10-14 07:00","2023-11-03 18:00","연속"]
[57,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥S/S #4 S.Tr 대체공사","신시흥S/S #4 S.Tr 대체공사(#6M.Tr 휴전)","2023-10-25 09:00","2023-10-31 18:00","2023-10-25 09:00","2023-10-31 18:00","연속"]
[58,"인천","시흥","영흥T/P CB 7271","영흥S/Y 7271 A상 포지션 밸브 점검","영흥S/Y 7271 A상 포지션 밸브 점검","2023-10-10 09:00","2023-10-10 18:00","취소","취소","연속"]
[59,"인천","직할","서인천CC신부평#1 T/L","서인천-신부평T/L 절연유 급유","서인천-신부평T/L 절연유 급유","2023-10-24 09:00","2023-10-24 18:00","2023-10-24 09:00","2023-10-24 18:00","연속"]
[60,"인천","직할","서인천CC신부평#2 T/L","서인천-신부평T/L 절연유 급배유","서인천-신부평T/L 절연유 급배유","2023-10-25 09:00","2023-10-25 18:00","2023-10-25 09:00","2023-10-25 18:00","연속"]
[61,"인천","직할","서인천CC신부평#4 T/L","서인천-신부평T/L 급유","서인천-신부평T/L 급유","2023-10-28 09:00","2023-10-28 18:00","2023-10-28 09:00","2023-10-28 18:00","연속"]
[62,"경기북부","고양","신덕은S/S #3 M.Tr","22~23년 고양전력지사 변전협력회사 총액공사","신덕은S/S 73B/F반 불량관련 교체공사","2023-10-02 09:00","2023-10-06 18:00","2023-10-02 09:00","2023-10-06 18:00","연속"]
[63,"경기북부","고양","신덕은파주문산CC#2 T/L","22~23년 고양전력지사 변전협력회사 총액공사","신덕은S/S 73B/F반 불량관련 교체공사","2023-10-02 09:00","2023-10-06 18:00","2023-10-02 09:00","2023-10-06 18:00","연속"]
[64,"경기북부","고양","신파주S/S #3 M.Tr","22~23년 고양전력지사 변전협력회사 총액공사","362kV GIS 보통점검(7472)","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[65,"경기북부","고양","신김포신파주#2 T/L","2022~2023년 고양전력지사 가공송전 협력회사 총액공사","철탑추락방지시설 설치, 불량애자교체, 항공장애표시구 설치","2023-10-16 07:00","2023-10-20 18:00","2023-10-16 07:00","2023-10-20 18:00","연속"]
[66,"경기북부","고양","신파주S/S #2 M.Tr","신파주S/S 345kV 주변압기 보통점검공사","신파주S/S #2M.Tr A,B,C상 보통점검 및 절연유 여과","2023-10-30 09:00","2023-11-03 18:00","2023-10-30 09:00","2023-11-03 18:00","연속"]
[67,"경기북부","고양","신파주S/S #1 M.Tr","신파주S/S 345kV 주변압기 보통점검공사","신파주S/S #1M.Tr A,B,C상 보통점검 및 절연유 여과","2023-10-23 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-10-27 18:00","연속"]
[68,"경기북부","고양","신김포신파주#1 T/L","2022~2023년 고양전력지사 가공송전 협력회사 총액공사","철탑추락방지시설 설치","2023-10-23 07:00","2023-10-27 18:00","2023-10-23 07:00","2023-10-27 18:00","연속"]
[69,"경기북부","구리","미금S/S #3 VSR CB","2022~23 구리전력 변전협력회사 총액공사","미금S/S 345kV #3VSR 초기점검","2023-10-04 09:00","2023-10-04 18:00","2023-10-04 09:00","2023-10-04 18:00","연속"]
[70,"경기북부","구리","미금S/S #3 M.Tr","345kV 미금S/S #4M.Tr 증설공사","○ #4M.Tr용 Gantry Tower 설치 ○ 중성점 모선 이설 ○ 예비모선 설치","2023-10-10 09:00","2023-10-25 18:00","2023-10-16 09:00","2023-10-31 18:00","연속"]
[71,"경기북부","구리","신가평S/S CB 7700","2022~23 구리전력 변전협력 총액공사","신가평S/S #3 M.Tr 2차-신가평-미금#1T/L GIS 7700 보통점검","2023-10-04 09:00","2023-10-04 18:00","취소","취소","연속"]
[72,"경기북부","구리","신포천S/S CB 7500","2022~23 구리전력 변전협력 총액공사","신포천S/S 345kV신포천-동두천CC #1T/L GIS 보통점검 7500","2023-10-05 09:00","2023-10-05 18:00","2023-10-05 09:00","2023-10-05 18:00","연속"]
[73,"경기북부","직할","신의정부양주#1 T/L","345kV 신의정부S/S CLR용 GIS 설치공사","신의정부-양주#1TL GIS ↔ #2CLR 2차측 GIB 연결용 LA, 단상GIB 설치 등","2023-10-30 09:00","2023-11-18 18:00","2023-11-02 09:00","2023-11-24 18:00","연속"]
[74,"경기북부","직할","양주S/S #1 M.Tr","양주 HVDC GIS 설치공사","23kV GIS 1CCT 설치및 KP 접속","2023-10-04 09:00","2023-10-13 18:00","2023-10-04 09:00","2023-10-13 18:00","연속"]
[75,"경기북부","직할","양주S/S #3 M.Tr","345kV M.Tr 3차 SIS 구조개선 공사","345kV M.Tr 3차 SIS 구조개선 공사 및 ES부 내부점검","2023-10-25 09:00","2023-10-27 18:00","2023-10-25 09:00","2023-10-27 18:00","연속"]
[76,"경기북부","직할","양주S/S #4 M.Tr","345kV M.Tr 3차 SIS 구조개선 공사","345kV M.Tr 3차 SIS 구조개선 공사","2023-10-30 09:00","2023-11-01 18:00","2023-10-30 09:00","2023-11-01 18:00","연속"]
[77,"경기북부","직할","양주S/S #2 M.Tr","23년 직할 345kV M.Tr 및 OLTC 정밀점검 공사","345kV M.Tr 및 OLTC 정밀점검 공사 #2M.Tr A,B,C상 보통점검, OLTC B상 정밀점검","2023-10-16 09:00","2023-10-24 18:00","2023-10-16 09:00","2023-10-24 18:00","연속"]
[78,"경기","군포","서서울#2신시흥#1 T/L","서서울2S/S 345kV #1BUS 가스누기 보수(무부하선로)","서서울2S/S 345kV #1BUS 가스누기 보수(무부하선로)","2023-10-19 09:00","2023-10-20 18:00","2023-10-19 09:00","2023-10-20 18:00","연속"]
[79,"경기","군포","서서울#2S/S CB 7D71","서서울2S/S 345kV #1BUS 가스누기 보수(무부하선로)","서서울2S/S 345kV #1BUS 가스누기 보수(무부하선로)","2023-10-19 09:00","2023-10-20 18:00","2023-10-19 09:00","2023-10-20 18:00","연속"]
[80,"경기","군포","서서울#2S/S #1 BUS","서서울2S/S 345kV #1BUS 가스누기 보수","서서울2S/S 345kV #1BUS 가스누기 보수","2023-10-16 09:00","2023-10-20 18:00","2023-10-16 09:00","2023-10-20 18:00","연속"]
[81,"경기","군포","서서울S/S #4 M.Tr","서서울S/S #4M.Tr 보통점검 및 1,2차 GIS 점검 등","서서울S/S #4M.Tr 보통점검 및 7800,7872 GIS 조작시험, 2차 GIS(6444) 보통, 1,2,3차 LA 보통, 1차 PT 보통점검","2023-10-05 09:00","2023-10-06 18:00","2023-10-05 09:00","2023-10-06 18:00","연속"]
[82,"경기","군포","서서울S/S #1 M.Tr","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-10-04 09:00","2023-10-04 18:00","2023-10-04 09:00","2023-10-04 18:00","연속"]
[83,"경기","군포","서서울S/S #2 M.Tr","M.Tr 1차측 EBA 자기애관 교체공사","M.Tr 1차측 EBA 자기애관 교체공사","2023-10-23 08:00","2023-10-26 14:00","2023-10-23 08:00","2023-10-26 14:00","연속"]
[84,"경기","군포","서서울S/S #3 M.Tr","M.Tr 1차측 EBA 자기애관 교체공사","M.Tr 1차측 EBA 자기애관 교체공사","2023-10-30 08:00","2023-11-02 14:00","2023-10-30 08:00","2023-11-02 14:00","연속"]
[85,"경기","군포","화성서서울#1 T/L","2023년 가공송전순시점검 위탁공사","화성서서울#1T/L 초기점검","2023-10-10 09:00","2023-10-11 18:00","2023-10-10 09:00","2023-10-11 18:00","매일"]
[86,"경기","군포","화성서서울#2 T/L","2023년 가공송전순시점검 위탁공사","화성서서울#2T/L 초기점검","2023-10-12 09:00","2023-10-13 18:00","2023-10-12 09:00","2023-10-13 18:00","매일"]
[87,"경기","군포","화성신안산#1 T/L","2023년 가공송전순시점검 위탁공사","화성신안산#1T/L 초기점검","2023-10-16 09:00","2023-10-17 18:00","2023-10-16 09:00","2023-10-17 18:00","매일"]
[88,"경기","군포","신시흥신안산#1 T/L","2023년 가공송전순시점검 위탁공사","신시흥신안산#1T/L 초기점검","2023-10-23 08:00","2023-10-23 12:00","취소","취소","연속"]
[89,"경기","군포","화성신안산#2 T/L","2023년 가공송전순시점검 위탁공사","화성신안산#2T/L 초기점검","2023-10-18 09:00","2023-10-19 18:00","2023-10-18 09:00","2023-10-19 18:00","매일"]
[90,"경기","군포","신시흥신안산#2 T/L","2023년 가공송전순시점검 위탁공사","신시흥신안산#2T/L 초기점검","2023-10-23 13:00","2023-10-23 17:00","2023-10-23 13:00","2023-10-23 17:00","연속"]
[91,"경기","동부","곤지암S/S #2 M.Tr","23년 동부 변전협력총액공사","곤지암:#2M.Tr(보통), 1.2차부싱절연유채유 7372,6244,4289(보통) #2S.Tr(보통) #2M.Tr 2차 LA(A,B,C)(대체) #2M.Tr 3차 LA(A,B,C)(보통)","2023-10-05 09:00","2023-10-06 18:00","2023-10-05 09:00","2023-10-06 18:00","연속"]
[92,"경기","동부","곤지암S/S CB 7300","23년 동부 변전협력총액공사","곤지암:동서울#1T/L TIE(보통)7300 동서울#2T/L TIE(보통)7400","2023-10-17 09:30","2023-10-17 14:00","2023-10-17 09:30","2023-10-17 14:00","연속"]
[93,"경기","동부","곤지암S/S CB 7400","23년 동부 변전협력총액공사","곤지암:동서울#1T/L TIE(보통)7300 동서울#2T/L TIE(보통)7400","2023-10-17 14:00","2023-10-17 18:00","2023-10-17 14:00","2023-10-17 18:00","연속"]
[94,"경기","동부","곤지암S/S CB 7271","23년 동부 변전협력총액공사","곤지암:여주SY#1T/L(보통)","2023-10-18 09:30","2023-10-18 18:00","2023-10-18 09:30","2023-10-18 18:00","연속"]
[95,"경기","동부","곤지암여주복합#2 T/L","추락방지장치(수평) 설치공사","추락방지장치 설치 86기","2023-10-22 07:00","2023-10-25 18:00","취소","취소","연속"]
[96,"경기","동부","곤지암S/S CB 7371","23년 동부 변전협력총액공사","곤지암:곤지암-동서울#2T/L(보통) 전자변교체-I(C상) 곤지암-동서울#1T/L(보통)","2023-10-19 09:30","2023-10-19 14:00","2023-10-19 09:30","2023-10-19 14:00","연속"]
[97,"경기","동부","곤지암S/S CB 7200","23년 동부 변전협력총액공사","곤지암:여주SY#1T/L TIE(보통)7200","2023-10-26 09:30","2023-10-26 14:00","2023-10-26 09:30","2023-10-26 14:00","연속"]
[98,"경기","동부","곤지암여주복합#1 T/L","추락방지장치(수평) 설치공사","추락방지장치 설치 86기","2023-10-14 07:00","2023-10-21 18:00","취소","취소","연속"]
[99,"경기","동부","곤지암S/S CB 7471","23년 동부 변전협력총액공사","곤지암:곤지암-동서울#2T/L(보통) 전자변교체-I(C상) 곤지암-동서울#1T/L(보통)","2023-10-19 14:00","2023-10-19 18:00","2023-10-19 14:00","2023-10-19 18:00","연속"]
[100,"경기","동부","여주C/C CB 7100","23년 동부 변전협력총액공사","여주SY:신제천-여주SY#1(초기) 신제천-여주SY TIE(초기) 7171,7100","2023-10-10 14:00","2023-10-10 18:00","2023-10-10 14:00","2023-10-10 18:00","연속"]
[101,"경기","동부","여주C/C CB 7171","23년 동부 변전협력총액공사","여주SY:신제천-여주SY#1(초기) 신제천-여주SY TIE(초기) 7171,7100","2023-10-10 09:30","2023-10-10 14:00","2023-10-10 09:30","2023-10-10 14:00","연속"]
[102,"경기","동부","여주C/C CB 7271","23년 동부 변전협력총액공사","여주SY:신충주-여주SY#2(초기) 신충주-여주SY#2 TIE(초기) 7271,7200","2023-10-11 09:30","2023-10-11 14:00","2023-10-11 09:30","2023-10-11 14:00","연속"]
[103,"경기","동부","여주C/C CB 7200","23년 동부 변전협력총액공사","여주SY:신충주-여주SY#2(초기) 신충주-여주SY#2 TIE(초기) 7271,7200","2023-10-11 14:00","2023-10-11 18:00","2023-10-11 14:00","2023-10-11 18:00","연속"]
[104,"경기","동부","여주C/C CB 7472","23년 동부 변전협력총액공사","여주SY:#3STEP-UP TR(초기) 7472","2023-10-05 09:30","2023-10-05 14:00","2023-10-05 09:30","2023-10-05 14:00","연속"]
[105,"경기","동부","여주C/C CB 7272","23년 동부 변전협력총액공사","여주SY:#1STEP-UP TR(초기) 7272 #2STEP-UP TR(초기) 7372","2023-10-04 09:30","2023-10-04 14:00","2023-10-04 09:30","2023-10-04 14:00","연속"]
[106,"경기","동부","여주C/C CB 7372","23년 동부 변전협력총액공사","여주SY:#1STEP-UP TR(초기) 7272 #2STEP-UP TR(초기) 7372","2023-10-04 14:00","2023-10-04 18:00","2023-10-04 14:00","2023-10-04 18:00","연속"]
[107,"경기","동부","여주C/C CB 7371","23년 동부 변전협력총액공사","여주SY:곤지암-여주SY#2(초기)7371 곤지암-여주SY#2 TIE(초기) 7371,7300","2023-10-12 09:30","2023-10-12 14:00","2023-10-12 09:30","2023-10-12 14:00","연속"]
[108,"경기","동부","여주C/C CB 7300","23년 동부 변전협력총액공사","여주SY:곤지암-여주SY#2(초기)7371 곤지암-여주SY#2 TIE(초기) 7371,7300","2023-10-12 14:00","2023-10-12 18:00","2023-10-12 14:00","2023-10-12 18:00","연속"]
[109,"경기","동부","여주C/C CB 7400","23년 동부 변전협력총액공사","여주SY:곤지암-여주SY#1(초기) 곤지암-여주SY#1 TIE(초기) 7471,7400","2023-10-13 14:00","2023-10-13 18:00","2023-10-13 14:00","2023-10-13 18:00","연속"]
[110,"경기","동부","여주C/C CB 7471","23년 동부 변전협력총액공사","여주SY:곤지암-여주SY#1(초기) 곤지암-여주SY#1 TIE(초기) 7471,7400","2023-10-13 09:30","2023-10-13 14:00","2023-10-13 09:30","2023-10-13 14:00","연속"]
[111,"경기","성남","신성남S/S #6 M.Tr","23년 성남전력 345, 154kV M.Tr 보통점검공사","- 주변압기 보통점검","2023-10-10 09:00","2023-10-11 18:00","2023-10-10 09:00","2023-10-11 18:00","연속"]
[112,"경기","성남","신성남동서울#1 T/L","345kV EBA 자기애관 교체공사","345kV EBA 자기애관 교체공사","2023-10-02 08:00","2023-10-05 18:00","2023-10-02 08:00","2023-10-05 18:00","연속"]
[113,"경기","성남","신성남동서울#2 T/L","추락방지장치(수평) 설치공사","41기(신안성신성남 병가 1기, 서서울2신성남 병가 4기)","2023-10-06 07:00","2023-10-09 18:00","2023-10-06 07:00","2023-10-09 18:00","연속"]
[114,"경기","성남","신수원S/S #3 M.Tr","23년 성남전력 345, 154kV M.Tr 보통점검공사","- 주변압기 보통점검","2023-10-25 09:00","2023-10-26 18:00","2023-10-25 09:00","2023-10-26 18:00","연속"]
[115,"경기","성남","신안성신수원#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)","2023-10-07 08:00","2023-10-13 18:00","취소","취소","연속"]
[116,"경기","성남","신안성서안성#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)","2023-10-10 08:00","2023-10-18 18:00","취소","취소","연속"]
[117,"경기","성남","신안성신수원#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)","2023-10-19 08:00","2023-10-31 18:00","2023-10-19 08:00","2023-10-31 18:00","연속"]
[118,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울T/L(고산2지구) 지중화 공사","○ 광주 고산2지구 택지개발지구내 지장송전선로 지중화 ○ 사업구간 : 345kV 신용인-동서울T/L No.55~56","2023-10-30 08:00","2023-11-17 18:00","2023-10-30 08:00","2023-11-17 18:00","연속"]
[119,"경기","성남","신용인삼성 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간/휴일제외)","2023-10-05 08:00","2023-10-09 18:00","2023-10-05 08:00","2023-10-09 18:00","매일"]
[120,"경기","성남","신용인S/S #2 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- 2차 GIS 조작시험 - 1차 CVT 하자점검 - 1차 LA 보통점검 - 부싱절연유 채유","2023-10-17 09:00","2023-10-17 18:00","2023-10-17 09:00","2023-10-17 18:00","연속"]
[121,"경기","성남","신용인S/S #1 M.Tr","23년 성남전력 345, 154kV M.Tr 보통점검공사","- 주변압기 보통점검 - 2차 GIS 조작시험 - 1, 2차 LA 보통점검","2023-10-19 09:00","2023-10-20 18:00","2023-10-19 09:00","2023-10-20 18:00","연속"]
[122,"경기","성남","신용인S/S #3 M.Tr","23년 성남전력 345, 154kV M.Tr 보통점검공사","- 주변압기 보통점검","2023-10-23 09:00","2023-10-24 18:00","2023-10-23 09:00","2023-10-24 18:00","연속"]
[123,"경기","직할","화성평택TP#1 T/L","154kV 화성-장덕T/L 등 2개 선로 OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-10-21 07:00","2023-10-22 18:00","취소","취소","연속"]
[124,"경기","직할","아산화성#2 T/L","154kV 화성-장덕T/L 등 2개 선로 OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-10-21 07:00","2023-10-22 18:00","취소","취소","연속"]
[125,"경기","직할","화성평택TP#2 T/L","154kV 화성-장덕T/L 등 2개 선로 OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-10-17 07:00","2023-10-19 18:00","취소","취소","연속"]
[126,"경기","직할","화성S/S #70 BUS","화성S/S 345kV GIS 용량대체공사","345kV #70BUS 용량대체(63kA)","2023-10-23 09:00","2023-11-30 18:00","2023-10-23 09:00","2023-11-30 18:00","연속"]
[127,"경기","직할","화성신평택CC#1 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 화성-신평택CC#1T/L 7171,7100 GIS 보통점검","2023-10-12 09:00","2023-10-12 18:00","2023-10-12 09:00","2023-10-12 18:00","연속"]
[128,"경기","직할","아산화성#1 T/L","화성S/S 345kV GIS 용량대체공사","345kV #70BUS 용량대체(63kA) 안전이격거리 확보","2023-10-28 07:00","2023-10-29 18:00","2023-10-28 07:00","2023-10-29 18:00","연속"]
[129,"경기","직할","화성신평택CC#2 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 화성-신평택CC#2T/L 7271,7200 GIS 보통점검","2023-10-13 09:00","2023-10-13 18:00","2023-10-13 09:00","2023-10-13 18:00","연속"]
[130,"경기","평택","서안성신진천#2 T/L","세종-포천간 도로개설 관련 지장이설공사(345kV 2T/L)","철탑 5기 신설, 8기 철거","2023-10-16 07:00","2023-11-04 18:00","2023-10-18 07:00","2023-11-07 18:00","연속"]
[131,"경기","평택","평택T/P #70 BUS","23년 평택전력 변전협력회사 총액공사","평택T/P 7771CB 누기보수","2023-10-14 09:00","2023-10-15 18:00","2023-10-14 09:00","2023-10-15 18:00","연속"]
[132,"경기","평택","평택T/P CB 7771","23년 평택전력 변전협력회사 총액공사","평택T/P 7771CB 누기보수","2023-10-14 09:00","2023-10-15 18:00","2023-10-14 09:00","2023-10-15 18:00","연속"]
[133,"강원","강릉","강릉T/P CB 7172","강릉TP S/Y 1호기 주변압기 휴전","강릉TP S/Y 345kV GIS 과열부 스페이서 교체 주변압기 HVN 부싱 코팅 작업","2023-10-05 09:00","2023-10-20 18:00","2023-10-05 09:00","2023-10-20 18:00","연속"]
[134,"강원","강릉","강릉T/P CB 7100","강릉TP S/Y 1호기 주변압기 휴전","강릉TP S/Y 345kV GIS 과열부 스페이서 교체 주변압기 HVN 부싱 코팅 작업","2023-10-05 09:00","2023-10-20 18:00","2023-10-05 09:00","2023-10-20 18:00","연속"]
[135,"강원","강릉","신양양S/S CB 7271","2022-23 변전협력회사 총액공사","신양양S/S 안인-신양양T/L 7271장기미동작 차단기 동작시험","2023-10-06 10:00","2023-10-06 13:00","2023-10-06 10:00","2023-10-06 13:00","연속"]
[136,"강원","강릉","신양양S/S CB 7200","2022-23 변전협력회사 총액공사","신양양S/S 안인-신양양T/L-TIE CB(7200) 장기미동작 차단기 동작시험","2023-10-06 13:00","2023-10-06 15:30","2023-10-06 13:00","2023-10-06 15:30","연속"]
[137,"강원","강릉","신양양S/S CB 7171","2022-23 변전협력회사 총액공사","신양양S/S 신양양-양양PPT/L CB(7171) 장기미동작 차단기 동작시험","2023-10-06 15:30","2023-10-06 18:00","2023-10-06 15:30","2023-10-06 18:00","연속"]
[138,"강원","동해","동해안인개폐소#2 T/L","송전팀 345kV 동해 등 2개T/L 인출변경공사","송전팀 345kV 동해 등 2개T/L 인출변경공사","2023-10-02 08:00","2023-10-25 18:00","2023-10-02 08:00","2023-10-25 18:00","연속"]
[139,"강원","동해","신제천동해#2 T/L","송전팀 345kV 동해 등 2개T/L 인출변경공사","송전팀 345kV 동해 등 2개T/L 인출변경공사","2023-10-03 08:00","2023-10-12 18:00","2023-10-03 08:00","2023-10-12 18:00","연속"]
[140,"강원","동해","동해S/S STATCOM CB","STATCOM 냉각설비 보수","냉각설비 소프트스타터 교체, 벨브 교체","2023-10-23 09:00","2023-10-23 18:00","취소","취소","연속"]
[141,"강원","동해","신제천동해#1 T/L","송전팀 345kV 동해 등 2개T/L 인출변경공사","송전팀 345kV 동해 등 2개T/L 인출변경공사","2023-10-13 08:00","2023-10-25 18:00","2023-10-13 08:00","2023-10-25 18:00","연속"]
[142,"강원","동해","동해안인개폐소#1 T/L","송전팀 345kV 동해 등 2개T/L 인출변경공사","송전팀 345kV 동해 등 2개T/L 인출변경공사","2023-10-05 08:00","2023-10-12 18:00","2023-10-05 08:00","2023-10-12 18:00","매일"]
[143,"강원","동해","동해S/S #2 M.Tr","22~23 동해전력지사 변전정비팀 총액공사","M.Tr 3차 피뢰기 점검","2023-10-31 09:30","2023-10-31 14:00","2023-10-31 09:30","2023-10-31 14:00","연속"]
[144,"강원","동해","동해S/S #3 M.Tr","22~23 동해전력지사 변전정비팀 총액공사","M.Tr 3차 피뢰기 점검","2023-10-31 14:00","2023-10-31 18:00","2023-10-31 14:00","2023-10-31 18:00","연속"]
[145,"강원","동해","북평T/P CB 7100","22~23 동해전력지사 변전정비팀 총액공사","GIS 보통점검","2023-10-17 14:00","2023-10-17 18:00","2023-10-17 14:00","2023-10-17 18:00","연속"]
[146,"강원","동해","북평T/P CB 7371","22~23 동해전력지사 변전정비팀 총액공사","GIS 보통점검","2023-10-19 09:30","2023-10-19 14:00","2023-10-19 09:30","2023-10-19 14:00","연속"]
[147,"강원","동해","북평T/P CB 7171","22~23 동해전력지사 변전정비팀 총액공사","GIS 보통점검","2023-10-17 09:30","2023-10-17 14:00","2023-10-17 09:30","2023-10-17 14:00","연속"]
[148,"강원","동해","북평T/P CB 7200","22~23 동해전력지사 변전정비팀 총액공사","GIS 보통점검","2023-10-18 14:00","2023-10-18 18:00","2023-10-18 14:00","2023-10-18 18:00","연속"]
[149,"강원","동해","북평T/P CB 7271","22~23 동해전력지사 변전정비팀 총액공사","GIS 보통점검","2023-10-18 09:30","2023-10-18 14:00","2023-10-18 09:30","2023-10-18 14:00","연속"]
[150,"강원","동해","북평T/P CB 7300","22~23 동해전력지사 변전정비팀 총액공사","GIS 보통점검","2023-10-19 14:00","2023-10-19 18:00","2023-10-19 14:00","2023-10-19 18:00","연속"]
[151,"강원","동해","삼척G/P CB 7671","22~23 동해전력지사 변전정비팀 총액공사","GIS 보통점검","2023-10-11 09:30","2023-10-11 18:00","2023-10-11 09:30","2023-10-11 18:00","연속"]
[152,"강원","동해","삼척G/P CB 7700","22~23 동해전력지사 변전정비팀 총액공사","GIS 보통점검","2023-10-10 09:30","2023-10-10 18:00","2023-10-10 09:30","2023-10-10 18:00","연속"]
[153,"강원","동해","삼척G/P CB 7771","22~23 동해전력지사 변전정비팀 총액공사","GIS 보통점검","2023-10-06 09:30","2023-10-06 18:00","2023-10-06 09:30","2023-10-06 18:00","연속"]
[154,"강원","동해","삼척G/P #1 Tie-Tr","22~23 동해전력지사 변전정비팀 총액공사","2차 GIS 정밀점검 2차.3차 LA 보통점검(윤재호,정성훈)","2023-10-04 09:30","2023-10-06 18:00","2023-10-04 09:30","2023-10-06 18:00","연속"]
[155,"강원","동해","삼척GP한울NP#2 T/L","2023년 가공송전선로 순시점검 위탁공사","애자절연저항측정","2023-10-30 08:00","2023-10-31 18:00","2023-10-30 08:00","2023-10-31 18:00","매일"]
[156,"강원","동해","삼척G/P #2 Tie-Tr","22~23 동해전력지사 변전정비팀 총액공사","2차,3차 LA 점검","2023-10-24 09:30","2023-10-24 18:00","2023-10-24 09:30","2023-10-24 18:00","연속"]
[157,"강원","동해","삼척G/P #3 Tie-Tr","22~23 동해전력지사 변전정비팀 총액공사","2차,3차 LA 점검","2023-10-25 09:30","2023-10-25 18:00","2023-10-25 09:30","2023-10-25 18:00","연속"]
[158,"강원","동해","삼척GP한울NP#1 T/L","2023년 가공송전선로 순시점검 위탁공사","애자절연저항측정","2023-10-26 08:00","2023-10-27 18:00","2023-10-26 08:00","2023-10-27 18:00","매일"]
[159,"강원","강릉","안인개폐소신양양 T/L","안인개폐소 362kV GIS 제작사 점검","- 설비 이음 관련 제작사(효성) 설비 내부 점검","2023-10-18 09:00","2023-10-25 18:00","2023-10-18 09:00","2023-10-25 18:00","연속"]
[160,"강원","강릉","안인개폐소강릉TP#1 T/L","안인개폐소 362kV GIS 제작사 점검","- 설비 이음 관련 제작사(효성) 설비 내부 점검","2023-10-04 09:00","2023-10-17 18:00","2023-10-04 09:00","2023-10-17 18:00","연속"]
[161,"강원","강릉","안인개폐소S/S #2 BUS","안인개폐소 362kV GIS 제작사 점검","- 설비 이음 관련 제작사(효성) 설비 내부 점검","2023-10-04 09:00","2023-10-17 18:00","2023-10-04 09:00","2023-10-17 18:00","연속"]
[162,"충북","직할","신중부S/S #5 Sh.R CB","신중부S/S 345kV DS 내부부품 교체 작업","345kV GIS DS부 부분방전 발생에 따른 DS 내부부품 교체공사 대상 : 7A01, 7A61DS(2대)","2023-10-16 09:00","2023-10-17 18:00","2023-10-16 09:00","2023-10-17 18:00","연속"]
[163,"충북","직할","신중부S/S #6 Sh.R CB","신중부S/S 345kV DS 내부부품 교체 작업","345kV GIS DS부 부분방전 발생에 따른 DS 내부부품 교체공사 대상 : 7C01, 7C61DS(2대)","2023-10-18 09:00","2023-10-19 18:00","2023-10-18 09:00","2023-10-19 18:00","연속"]
[164,"충북","직할","신중부S/S #2 BUS","신중부S/S 345kV DS 내부부품 교체 작업","345kV GIS DS부 부분방전 발생에 따른 #2BUS DS 내부부품 교체공사 대상 : 7952, 7A52, 7B52, 7C52DS(4대)","2023-10-30 09:00","2023-11-02 18:00","2023-10-30 09:00","2023-11-02 18:00","연속"]
[165,"충북","직할","신중부남청주#2 T/L","345kV 신중부-남청주T/L 지장이설공사(요정차시행)","철탑 4기 신설, 인틀로징 1기, 가철탑 3기","2023-10-04 08:00","2023-10-10 18:00","취소","취소","연속"]
[166,"충북","직할","신중부남청주#1 T/L","345kV 신중부-남청주T/L 지장이설공사(요정차시행)","철탑 4기 신설, 인틀로징 1기, 가철탑 3기","2023-10-11 08:00","2023-10-17 18:00","취소","취소","연속"]
[167,"충북","직할","신진천S/S #1 M.Tr","22-23년 충북직할 변전협력회사 총액공사","신진천S/S 23kV #1S.Tr 4189 VCB 대체","2023-10-15 09:00","2023-10-17 18:00","2023-10-15 09:00","2023-10-17 18:00","연속"]
[168,"충북","청주","남청주S/S #4 M.Tr","22-23년 변전협력회사 총액공사","1. 7800 차단기 전자변교체 2. 7872 차단기 전자변교체","2023-10-02 09:00","2023-10-02 18:00","2023-10-02 09:00","2023-10-02 18:00","연속"]
[169,"충북","청주","남청주S/S #3 M.Tr","22-23년 변전협력회사 총액공사","1. 7672 GIS 초기점검(#3M.Tr 1차) 2. 7600 GIS 초기점검(#3M.Tr 1차-세종남청주#1T/L TIE) * 제작사 유압매커니즘 점검","2023-10-04 09:00","2023-10-06 18:00","2023-10-04 09:00","2023-10-06 18:00","연속"]
[170,"충북","청주","남청주S/S #2 M.Tr","22-23년 청주전력지사 변전협력회사 총액공사","#2M.Tr 보통점검","2023-10-10 09:00","2023-10-13 18:00","2023-10-10 09:00","2023-10-13 18:00","연속"]
[171,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사 (1차)","#66-65 SEC GIS 대체 (안전이격 확보)","2023-10-18 09:00","2023-10-20 18:00","2023-10-23 09:00","2023-10-25 18:00","연속"]
[172,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사 (1차)","#66-65 SEC GIS 대체 (안전이격 확보)","2023-10-25 14:00","2023-10-27 18:00","2023-10-30 14:00","2023-11-01 18:00","연속"]
[173,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","#66-65 SEC GIS 대체 (안전이격 확보)","2023-10-30 09:00","2023-11-01 18:00","취소","취소","연속"]
[174,"충북","청주","신옥천북경남 T/L","22-23년 청주전력지사 변전협력회사 총액공사","362kV GIS 보통점검","2023-10-25 08:00","2023-10-25 17:00","취소","취소","연속"]
[175,"충북","청주","신옥천세종#1 T/L","22-23년 청주전력지사 변전협력회사 총액공사","362kV GIS 보통점검","2023-10-16 08:00","2023-10-17 18:00","취소","취소","연속"]
[176,"충북","청주","신옥천S/S #1 M.Tr","22-23년 청주전력지사 변전협력회사 총액공사","362kV GIS 보통점검","2023-10-18 08:00","2023-10-18 18:00","2023-10-18 08:00","2023-10-18 18:00","연속"]
[177,"충북","청주","신옥천세종#2 T/L","22-23년 청주전력지사 변전협력회사 총액공사","362kV GIS 보통점검","2023-10-23 08:00","2023-10-24 17:00","취소","취소","연속"]
[178,"충북","충주","신제천신영주#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 [No.1~165(162기)]","2023-10-25 08:00","2023-11-13 17:00","취소","취소","매일"]
[179,"대전세종충남","서산","당진T/P CB 7171","'23년 장기 미동작 차단기 조작시험","당진화력변전소 장기 미동작 차단기 조작시험(공압)","2023-10-20 09:00","2023-10-20 14:00","2023-10-20 09:00","2023-10-20 14:00","연속"]
[180,"대전세종충남","서산","당진T/P CB 7100","'23년 장기 미동작 차단기 조작시험","당진화력변전소 장기 미동작 차단기 조작시험(공압)","2023-10-20 14:00","2023-10-20 18:00","2023-10-20 14:00","2023-10-20 18:00","연속"]
[181,"대전세종충남","서산","당진T/P #72 Tie-Tr","'23년 서산P/O 변전협력회사 총액공사","당진화력S/S 345kV #72TIE-Tr 보통점검 (병행1) 당진화력S/S 345kV #72M.Tr 1차 CB 조작시험 (병행2) 당진화력S/S 345kV #72M.Tr 2,3차 GIS 보통점검 (병행3) 당진화력S/S 23kV #2S.Tr 보통점검","2023-10-16 09:00","2023-10-19 18:00","취소","취소","연속"]
[182,"대전세종충남","서산","북당진S/S CB 7772","23년 서산P/O 345kV GIS 보통점검공사","북당진S/S 345kV 7772 GIS 보통점검","2023-10-24 09:00","2023-10-24 18:00","2023-10-24 09:00","2023-10-24 18:00","연속"]
[183,"대전세종충남","서산","북당진S/S CB 7200","23년 서산P/O 345kV GIS 보통점검공사","북당진S/S 345kV 7200 GIS 보통점검","2023-10-05 09:00","2023-10-05 18:00","2023-10-05 09:00","2023-10-05 18:00","연속"]
[184,"대전세종충남","서산","북당진S/S CB 7800","23년 서산P/O 345kV GIS 보통점검공사","북당진S/S 345kV 7800 GIS 보통점검","2023-10-25 09:00","2023-10-25 18:00","2023-10-25 09:00","2023-10-25 18:00","연속"]
[185,"대전세종충남","서산","북당진S/S CB 7872","23년 서산P/O 345kV GIS 보통점검공사","북당진S/S 345kV 7872 GIS 보통점검","2023-10-26 09:00","2023-10-26 18:00","2023-10-26 09:00","2023-10-26 18:00","연속"]
[186,"대전세종충남","서산","신당진개폐소북당진 T/L","345kV 신당진개폐소-북당진T/L 점퍼지지애자 설치","고정형 점퍼지지애자 설치 : No.44,59","2023-10-12 08:00","2023-10-13 18:00","2023-10-12 08:00","2023-10-13 18:00","매일"]
[187,"대전세종충남","서산","신당진S/S #1 M.Tr","23년 서산P/O 345kV이하 변압기 보통점검공사","(9월 휴전 취소시) 신당진S/S 345kV #1M.Tr 보통점검 및 누유보수","2023-10-23 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-10-27 18:00","연속"]
[188,"대전세종충남","서산","신당진S/S #2 M.Tr","23년 서산P/O 345kV이하 변압기 보통점검공사","(9월 휴전 취소시) 신당진S/S 345kV #2M.Tr 보통점검 및 누유보수","2023-10-30 09:00","2023-11-03 18:00","2023-10-30 09:00","2023-11-03 18:00","연속"]
[189,"대전세종충남","서산","신서산신당진#2 T/L","'23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 345kV 77BAY B/F반 대체","2023-10-10 09:00","2023-10-13 18:00","취소","취소","연속"]
[190,"대전세종충남","서산","신서산S/S #4 Sh.R CB","'23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 345kV 77BAY B/F반 대체","2023-10-10 09:00","2023-10-13 18:00","취소","취소","연속"]
[191,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","태안화력S/Y 345kV 옥외설비 GIS 내장화공사","태안화력S/Y 345kV 개폐소-태안화력#2T/L 옥외설비 GIS 내장화공사 (병행) 345kV 개폐소-태안화력#2T/L 보호반 대체","2023-10-23 09:00","2023-11-10 18:00","취소","취소","연속"]
[192,"대전세종충남","서산","태안T/P #2 Tie-Tr","'23년 서산P/O 변전협력회사 총액공사","태안화력S/S 345kV #2M.Tr 보통점검 (병행1) 태안화력S/S 345kV #2M.Tr 1,2,3차 GIS 보통점검 (병행2) 태안화력S/S 345kV #2M.Tr 2차 LA 보통점검 (병행3) 태안화력S/S 23kV #2S.Tr 보통점검","2023-10-30 09:00","2023-11-03 18:00","2023-10-30 09:00","2023-11-03 18:00","연속"]
[193,"대전세종충남","천안","신온양서서울#2 T/L","(9월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","(9월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","2023-10-23 09:00","2023-10-26 18:00","취소","취소","연속"]
[194,"대전세종충남","천안","신온양신탕정#2 T/L","(9취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","(9취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","2023-10-30 09:00","2023-11-02 18:00","2023-10-30 09:00","2023-11-02 18:00","연속"]
[195,"대전세종충남","천안","신온양S/S #4 M.Tr","(9월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","(9월취소시)신온양S/S 345kV 77B/F 교체 및 결상회로 보완작업","2023-10-23 09:00","2023-10-26 18:00","2023-10-23 09:00","2023-10-26 18:00","연속"]
[196,"대전세종충남","천안","신온양서서울#1 T/L","(9월취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","(9월취소시)신온양S/S 345kV 78B/F 교체 및 결상회로 보완작업","2023-10-30 09:00","2023-11-02 18:00","취소","취소","연속"]
[197,"대전세종충남","천안","아산화성#2 T/L","(9월취소시)아산S/S 345kV 아산-화성#2T/L CVT 보통점검","(9월취소시)아산S/S 345kV 아산-화성#2T/L LA,CVT 보통점검","2023-10-26 09:00","2023-10-26 18:00","취소","취소","연속"]
[198,"대전세종충남","천안","신서산아산#1 T/L","'22~'23년 천안전력지사 송전협력회사 총액공사","추락방지장치 설치","2023-10-26 07:00","2023-10-31 18:00","취소","취소","매일"]
[199,"대전세종충남","천안","신서산아산#2 T/L","'22~'23년 천안전력지사 송전협력회사 총액공사","추락방지장치 설치","2023-10-26 07:00","2023-10-31 18:00","취소","취소","매일"]
[200,"대전세종충남","천안","아산보령TP#2 T/L","(9월취소시)아산S/S 345kV 아산-보령화력#2T/L CVT 보통점검","(9월취소시)아산S/S 345kV 아산-보령화력#2T/L LA,CVT 보통점검","2023-10-25 09:00","2023-10-25 18:00","취소","취소","연속"]
[201,"대전세종충남","천안","신서산아산#1 T/L","(9월취소시)아산S/S 345kV 신서산-아산#1T/L CVT 보통점검","(9월취소시)아산S/S 345kV 신서산-아산#1T/L LA,CVT 보통점검","2023-10-24 09:00","2023-10-24 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[202,"대전세종충남","천안","아산보령TP#1 T/L","345kV 아산-보령화력T/L 추락방지장치 설치공사","345kV 아산-보령화력T/L No. 124~190 수직, 수평 추락방지장치 설치 ※ 주말작업 없음.","2023-10-19 07:00","2023-10-31 18:00","2023-10-19 07:00","2023-10-31 18:00","매일"]
[203,"대전세종충남","청양","보령C/C CB 7272","청양P/O 변전협력회사 총액공사","보령C/C 345kV 7272 보통점검","2023-10-26 10:00","2023-10-26 18:00","2023-10-26 10:00","2023-10-26 18:00","연속"]
[204,"대전세종충남","청양","보령C/C CB 7200","청양P/O 변전협력회사 총액공사","보령C/C 345kV 7200 보통점검","2023-10-25 10:00","2023-10-25 18:00","2023-10-25 10:00","2023-10-25 18:00","연속"]
[205,"대전세종충남","청양","청양S/S #2 M.Tr","(9월취소시)청양P/O 변전협력회사 총액공사","(9월취소시)청양S/S 345kV #2M.Tr - 345kV 7772(화), 7700(수) GIS 보통점검(병행) - 170kV 6244 GIS 보통점검(목~금 병행) - 25.8kV VCB 부동작예방 조작시험(4279-1, 4279-2) / 4279 VCB 하자점검 / 4276 DS 보통점검 - 23kV #2-1, #2-2 Sh.R 보통점검","2023-10-23 07:30","2023-10-26 18:00","2023-10-23 07:30","2023-10-26 18:00","연속"]
[206,"대전세종충남","청양","청양S/S 예비 M.Tr CB","(9월취소시)청양P/O 변전협력회사 총액공사","(9월취소시)청양S/S 345kV #1M.Tr - #1M.Tr 보통점검(예비변압기 포함) / 7671, 7600 차단기 부동작예방 조작시험 / 170kV 6144 GIS 보통점검(병행,화~수) - 3차측 VCB 대체(4179, 4189, 4179-1) / 4179-2 VCB 조작시험 / 4176, 4186, 4176-1 DS 보통점검 - AC, DC 분전반 대체","2023-10-16 07:30","2023-10-20 18:00","취소","취소","연속"]
[207,"대전세종충남","청양","청양S/S #1 M.Tr","(9월취소시)청양P/O 변전협력회사 총액공사","(9월취소시)청양S/S 345kV #1M.Tr - #1M.Tr 보통점검(예비변압기 포함) / 7671, 7600 차단기 부동작예방 조작시험 / 170kV 6144 GIS 보통점검(병행,화~수) - 3차측 VCB 대체(4179, 4189, 4179-1) / 4179-2 VCB 조작시험 / 4176, 4186, 4176-1 DS 보통점검 - AC, DC 분전반 대체","2023-10-16 07:30","2023-10-20 18:00","2023-10-16 07:30","2023-10-20 18:00","연속"]
[208,"전북","군산","군산S/S #2 M.Tr","군산S/S 170kV GIS 대체공사(군산-영등#2T/L)","군산S/S 170kV GIS 대체공사(군산-영등#2T/L) 무부하가압용","2023-10-11 16:00","2023-10-11 18:00","취소","취소","연속"]
[209,"전북","군산","군산S/S #1 M.Tr","군산S/S 170kV GIS 대체공사(군산-이리#1T/L 등)","군산S/S 170kV GIS 대체공사(군산-이리#1T/L, 6100, #1PT) 무부하가압용","2023-10-11 16:00","2023-10-11 18:00","취소","취소","연속"]
[210,"전북","군산","군산신김제#2 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-10-22 07:00","2023-10-30 18:00","2023-10-22 07:00","2023-10-30 18:00","연속"]
[211,"전북","군산","군산S/S #2 M.Tr","군산S/S 170kV GIS 대체공사(군산-영등#2T/L)","군산S/S 170kV GIS 대체공사(군산-영등#2T/L) 무부하가압용","2023-10-15 18:00","2023-10-16 18:00","취소","취소","연속"]
[212,"전북","군산","군산S/S #1 M.Tr","군산S/S 170kV GIS 대체공사(군산-이리#1T/L 등)","군산S/S 170kV GIS 대체공사(군산-이리#1T/L, 6100, #1PT) 무부하가압용","2023-10-20 18:00","2023-10-21 18:00","취소","취소","연속"]
[213,"전북","군산","군산신김제#1 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-10-31 07:00","2023-11-08 18:00","2023-10-31 07:00","2023-11-08 18:00","연속"]
[214,"전북","군산","군산S/S #1 Sh.R CB","군산S/S 345kV #1Sh.R 가스발생 관련 점검공사","군산S/S 345kV #1Sh.R 가스발생 관련 점검공사 - 분로리액터 내부 점검 및 절연유 여과 공사","2023-10-23 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-10-27 18:00","연속"]
[215,"전북","군산","군산S/S #2 M.Tr","군산S/S 170kV GIS 대체공사(군산-영등#2T/L)","군산S/S 170kV GIS 대체공사(군산-영등#2T/L) 무부하가압용","2023-10-23 18:00","2023-10-24 18:00","취소","취소","연속"]
[216,"전북","군산","군산S/S #4 M.Tr","군산P/O 주변압기 점검공사","군산P/O 주변압기 점검공사","2023-10-30 09:00","2023-10-31 18:00","취소","취소","연속"]
[217,"전북","군산","군산신김제#2 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-10-12 07:00","2023-10-12 18:00","2023-10-12 07:00","2023-10-12 18:00","연속"]
[218,"전북","군산","군산S/S CB 7700","군산PO 공압식 차단기 전자변 교체공사","- 7700 CB 전자변 교체, 조작시험","2023-10-10 09:00","2023-10-10 18:00","취소","취소","연속"]
[219,"전북","군산","군산신김제#1 T/L","345kV 군산-신김제T/L 지장철탑이설공사","새만금-전주 고속도로 건설관련 송전선로 지장철탑 이설 ○ 공사개요 - 철탑교체 : 설치 2기, 철거 2기, 임시 1기【군산-신김제T/L №31∼32】 - 전력선 교체 : 1.508C-km[ACSR 480㎟×4B] - 금구류 교체 및 기타 부대공사","2023-10-13 07:00","2023-10-21 18:00","2023-10-13 07:00","2023-10-21 18:00","연속"]
[220,"전북","군산","군산S/S CB 7772","군산PO 공압식 차단기 전자변 교체공사","- 7772 CB 전자변 교체, 조작시험","2023-10-11 09:00","2023-10-11 18:00","2023-10-11 09:00","2023-10-11 18:00","연속"]
[221,"전북","김제","신김제한빛NP#2 T/L","345kV 신김제-한빛T/L 조류착지방지장치 설치공사","#2T/L 조류착지방지장치 설치 : No.26~221(52기)","2023-10-04 09:00","2023-10-06 18:00","2023-10-04 09:00","2023-10-06 18:00","연속"]
[222,"전북","직할","북경남무주양수 T/L","북경남-무주양수T/L 차단기 조작시험(즉시가압가능)","북경남-무주양수T/L 차단기 조작시험(즉시가압가능)","2023-10-05 09:00","2023-10-05 18:00","취소","취소","연속"]
[223,"전북","직할","신남원한빛NP#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 71Bay BF 보호배전반 대체","2023-10-02 09:00","2023-10-06 18:00","취소","취소","연속"]
[224,"전북","직할","신남원S/S #1 M.Tr","신남원S/S #1M.Tr 주변압기 점검(GIS 포함)","신남원S/S #1M.Tr 주변압기 점검(GIS 포함)","2023-10-30 09:00","2023-11-03 18:00","2023-10-30 09:00","2023-11-03 18:00","연속"]
[225,"전북","직할","신옥천신남원#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 72Bay BF 보호배전반 대체","2023-10-09 09:00","2023-10-13 18:00","취소","취소","연속"]
[226,"전북","직할","신남원한빛NP#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 72Bay BF 보호배전반 대체","2023-10-09 09:00","2023-10-13 18:00","취소","취소","연속"]
[227,"전북","직할","신남원의령#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 74Bay BF 보호배전반 대체","2023-10-16 09:00","2023-10-20 18:00","취소","취소","연속"]
[228,"전북","직할","신남원광양#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 75Bay BF 보호배전반 대체","2023-10-23 09:00","2023-10-27 18:00","취소","취소","연속"]
[229,"전북","직할","신옥천신남원#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 71Bay BF 보호배전반 대체","2023-10-02 09:00","2023-10-06 18:00","취소","취소","연속"]
[230,"전북","직할","신남원신광주#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원S/S 345kV 신남원-신광주 #2T/L LA 보통점검","2023-10-24 09:00","2023-10-24 18:00","취소","취소","연속"]
[231,"전북","직할","신남원S/S CB 7700","23년 전북직할 362kV GIS 정밀점검 (단독차단기)","23년 전북직할 362kV GIS 정밀점검 (단독차단기)","2023-10-02 09:00","2023-10-06 18:00","2023-10-02 09:00","2023-10-06 18:00","연속"]
[232,"전북","직할","신남원광양#2 T/L","23년 전북직할 변전협력회사 총액공사","신남원SS 76Bay BF 보호배전반 대체","2023-10-10 09:00","2023-10-14 18:00","취소","취소","연속"]
[233,"전북","직할","신남원S/S CB 7600","신남원S/S 신남원-광양#2T/L GIS 보통점검","신남원S/S 신남원-광양#2T/L GIS 보통점검","2023-10-10 09:00","2023-10-10 18:00","2023-10-10 09:00","2023-10-10 18:00","연속"]
[234,"전북","직할","신남원S/S CB 7100","신남원S/S 7100 GIS 보통점검","신남원S/S 7100 GIS 보통점검","2023-10-30 09:00","2023-10-30 18:00","취소","취소","연속"]
[235,"전북","직할","신남원신광주#1 T/L","23년 전북직할 변전협력회사 총액공사","신남원S/S 345kV 신남원-신광주 #1T/L LA, CVT 보통점검","2023-10-02 09:00","2023-10-02 18:00","취소","취소","연속"]
[236,"광주전남","강진","신강진S/S #1 M.Tr","23년도 강진전력지사 GIS 보통점검 공사","신강진S/S #1M.Tr 2차 GIS 보통점검","2023-10-23 09:00","2023-10-23 18:00","2023-10-23 09:00","2023-10-23 18:00","연속"]
[237,"광주전남","강진","신강진S/S #2 M.Tr","23년도 강진전력지사 GIS 보통점검 공사","신강진S/S #2M.Tr 2차 GIS 보통점검","2023-10-24 09:00","2023-10-24 18:00","2023-10-24 09:00","2023-10-24 18:00","연속"]
[238,"광주전남","강진","신강진S/S #3 M.Tr","23년도 강진전력지사 GIS 보통점검 공사","신강진S/S #3M.Tr 2차 GIS 보통점검","2023-10-24 09:00","2023-10-24 18:00","2023-10-25 09:00","2023-10-25 18:00","연속"]
[239,"광주전남","강진","신화순신강진#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","추락방지장치 설치공사 신화순-신강진 114기","2023-10-19 07:00","2023-10-27 18:00","취소","취소","매일"]
[240,"광주전남","광주","신광주신화순#1 T/L","22~23년 송전협력회사 총액공사","신광주-신화순T/L 추락방지장치 설치공사(No.1~121)","2023-10-16 09:00","2023-10-21 18:00","취소","취소","매일"]
[241,"광주전남","광주","신광주S/S CB 7172","7172 GIS 보통점검","7172 GIS 보통점검","2023-10-23 08:00","2023-10-23 18:00","취소","취소","연속"]
[242,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2023-10-23 08:00","2023-10-26 18:00","취소","취소","연속"]
[243,"광주전남","광주","신광주S/S CB 7672","7672 CB 조작시험","7672 CB 조작시험","2023-10-16 08:00","2023-10-16 18:00","취소","취소","연속"]
[244,"광주전남","광주","신광주한빛NP#1 T/L","2023년 가공송전선로 순시점검 위탁공사(과열정비)","345kV 신광주-한빛NP #1T/L 73, 100, 134호 과열개소 정비","2023-10-10 09:00","2023-10-10 18:00","취소","취소","연속"]
[245,"광주전남","광주","신광주신화순#2 T/L","22~23년 송전협력회사 총액공사","신광주-신화순T/L 추락방지장치 설치공사(No.1~121)","2023-10-23 09:00","2023-10-28 18:00","취소","취소","매일"]
[246,"광주전남","광주","신광주신화순#1 T/L","23년 광주전력지사 변전협력회사 총액공사","- 76BAY 차단실패보호반 교체","2023-10-10 09:00","2023-10-20 18:00","취소","취소","연속"]
[247,"광주전남","광주","신광주S/S #3 M.Tr","23년 광주전력지사 변전협력회사 총액공사","- 76BAY 차단실패보호반 교체 - 345kV M.Tr 보통점검 - 362kV GIS 조작시험(7600,7672) - #3M.Tr 3차 차단기 교체(3차 Main, #1,2Sh.R, S.Tr) - 3차측 DS 점검","2023-10-10 09:00","2023-10-20 18:00","취소","취소","연속"]
[248,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체","2023-10-30 08:00","2023-11-02 18:00","취소","취소","연속"]
[249,"광주전남","광주","신광주S/S CB 7200","7200 CB 조작시험","7200 CB 조작시험","2023-10-25 08:00","2023-10-25 18:00","취소","취소","연속"]
[250,"광주전남","광주","신광주한빛NP#2 T/L","신광주 7200 CB 조작시험,CVT보통점검","신광주 7200 CB 조작시험,CVT보통점검","2023-10-25 08:00","2023-10-25 18:00","취소","취소","연속"]
[251,"광주전남","광주","신광주S/S CB 7171","7171 GIS 보통점검","7171 GIS 보통점검","2023-10-24 08:00","2023-10-24 18:00","취소","취소","연속"]
[252,"광주전남","광주","신화순신강진#2 T/L","'22~23년 광주 변전협력회사 총액공사","신화순-신강진#2T/L CVT 보통점검","2023-10-23 09:00","2023-10-23 18:00","취소","취소","연속"]
[253,"광주전남","순천","광양C/C CB 7171","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험(즉시가압 가능)","2023-10-04 09:00","2023-10-04 12:00","2023-10-04 09:00","2023-10-04 12:00","연속"]
[254,"광주전남","순천","광양C/C CB 7100","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험(즉시가압 가능)","2023-10-04 12:00","2023-10-04 15:00","2023-10-04 12:00","2023-10-04 15:00","연속"]
[255,"광주전남","순천","광양C/C CB 7172","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험(즉시가압 가능)","2023-10-04 15:00","2023-10-04 18:00","2023-10-04 15:00","2023-10-04 18:00","연속"]
[256,"광주전남","순천","광양C/C CB 7271","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험(즉시가압 가능)","2023-10-05 09:00","2023-10-05 12:00","2023-10-05 09:00","2023-10-05 12:00","연속"]
[257,"광주전남","순천","광양C/C CB 7200","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험(즉시가압 가능)","2023-10-05 12:00","2023-10-05 15:00","2023-10-05 12:00","2023-10-05 15:00","연속"]
[258,"광주전남","순천","광양C/C CB 7272","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험(즉시가압 가능)","2023-10-05 15:00","2023-10-05 18:00","2023-10-05 15:00","2023-10-05 18:00","연속"]
[259,"광주전남","순천","광양CC여수TP#2 T/L","345kV 광양CC-신여수 지중T/L 운영시스템,온라인PD 설치공사","지중송전선로와 부대설비에 대한 실시간 감시, 제어를 통한 안정적인 전력공급(휴전작업공정 : EBA,EBG 센서 및 카메라 설치작업) 즉시가압여부 : 가능, 소요시간 20분","2023-10-12 09:00","2023-10-13 18:00","취소","취소","매일"]
[260,"광주전남","순천","광양CC여수TP#1 T/L","345kV 광양CC-신여수 지중T/L 운영시스템,온라인PD 설치공사","지중송전선로와 부대설비에 대한 실시간 감시, 제어를 통한 안정적인 전력공급(휴전작업공정 : EBA,EBG 센서 및 카메라 설치작업) 즉시가압여부 : 가능, 소요시간 20분","2023-10-10 09:00","2023-10-11 18:00","취소","취소","매일"]
[261,"광주전남","순천","광양S/S CB 7300","22-23년 순천전력지사 변전정비회사 총액공사","광양-율촌CC T/L CB GIS 보통점검(7371)","2023-10-25 08:00","2023-10-25 18:00","취소","취소","연속"]
[262,"광주전남","순천","광양광양제철#1 T/L","345kV 광양-광양CC #1T/L 피뢰기 설치공사","345kV 광양-광양CC #1T/L 피뢰기 설치공사를 위한 병가선로(광양제철#1T/L) 휴전","2023-10-23 08:00","2023-10-31 18:00","취소","취소","연속"]
[263,"광주전남","순천","광양여수TP T/L","22-23년 순천전력지사 변전협력회사 총액공사","LA 및 CVT 보통점검(즉시가압 가능)","2023-10-06 08:00","2023-10-06 18:00","취소","취소","연속"]
[264,"광주전남","순천","광양S/S #1 M.Tr","22-23년 순천전력지사 변전협력회사 총액공사","#1M.Tr 3차 MAIN VCB 대체(즉시가압 불가)","2023-10-10 08:00","2023-10-11 18:00","취소","취소","연속"]
[265,"광주전남","순천","신강진광양#2 T/L","345kV 광양S/S 362kV GIS 용량변경 교체공사(인출변경)","345kV 광양S/S 362kV GIS 용량변경 교체공사(인출변경) - 신강진-광양#2선로 철거 및 광양하동TP #2선로 인출변경 - 362kV GIS(하동TP 76, 75BAY) 교체공사","2023-10-16 08:00","2024-05-31 18:00","2023-10-16 08:00","2024-05-31 18:00","연속"]
[266,"광주전남","순천","신강진광양#2 T/L","345kV 신강진-광양T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.140~286호, 147기","2023-10-16 08:00","2023-10-27 18:00","취소","취소","매일"]
[267,"광주전남","순천","광양광양CC#1 T/L","345kV 광양-광양CC #1T/L 피뢰기 설치공사","345kV 광양-광양CC #1T/L 피뢰기 설치공사(No.1~60호)","2023-10-23 08:00","2023-10-31 18:00","취소","취소","연속"]
[268,"광주전남","순천","광양하동TP#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","GIS 보통점검(7571, 7500) 및 LA, CVT 보통점검(즉시가압 가능)","2023-10-23 08:00","2023-10-24 18:00","취소","취소","연속"]
[269,"광주전남","순천","광양S/S CB 7371","22-23년 순천전력지사 변전정비회사 총액공사","광양-율촌CC T/L CB GIS 보통점검(7371)","2023-10-20 08:00","2023-10-20 18:00","취소","취소","연속"]
[270,"광주전남","순천","광양하동TP#2 T/L","광양S/S 345kV 광양-하동TPT/L 인출변경공사","광양S/S 362kV GIS 대체 관련 345kV 광양-하동TPT/L 인출변경 - 23.10 : 신강진-광양#2 철거 및 광양-하동TP#2 공중이동(신강진-광양#1 안전이격 휴전 필요) - 24.03 : 광양-하동TP#1 공중이동 - 24.05 : 선로 원상복구","2023-10-19 09:00","2023-10-27 18:00","취소","취소","연속"]
[271,"광주전남","순천","신강진광양#1 T/L","광양S/S 345kV 광양-하동TPT/L 인출변경공사","광양S/S 362kV GIS 대체 관련 345kV 광양-하동TPT/L 인출변경 - 23.10 : 신강진-광양#2 철거 및 광양-하동TP#2 공중이동(신강진-광양#1 안전이격 휴전 필요) - 24.03 : 광양-하동TP#1 공중이동 - 24.05 : 선로 원상복구","2023-10-19 09:00","2023-10-27 18:00","2023-10-19 09:00","2023-10-27 18:00","매일"]
[272,"광주전남","순천","광양하동TP#2 T/L","345kV 광양S/S 362kV GIS 용량변경 교체공사(인출변경)","345kV 광양S/S 362kV GIS 용량변경 교체공사(인출변경) - 신강진-광양#2선로 철거 및 광양하동TP #2선로 인출변경 - 362kV GIS(하동TP 76, 75BAY) 교체공사","2023-10-19 08:00","2023-11-02 18:00","2023-10-19 08:00","2023-11-02 18:00","연속"]
[273,"광주전남","순천","광양S/S CB 7200","22-23년 순천전력지사 변전정비회사 총액공사","신남원-광양#1T/L TIE GIS 보통점검(7200)","2023-10-19 08:00","2023-10-19 18:00","취소","취소","연속"]
[274,"광주전남","순천","광양S/S CB 7271","22-23년 순천전력지사 변전정비회사 총액공사","신남원-광양#1T/L GIS 보통점검","2023-10-18 08:00","2023-10-18 18:00","취소","취소","연속"]
[275,"광주전남","순천","신강진광양#2 T/L","광양S/S 345kV 광양-하동TPT/L 인출변경공사","광양S/S 362kV GIS 대체 관련 345kV 광양-하동TPT/L 인출변경 - 23.10 : 신강진-광양#2 철거 및 광양-하동TP#2 공중이동(신강진-광양#1 안전이격 휴전 필요) - 24.03 : 광양-하동TP#1 공중이동 - 24.05 : 선로 원상복구","2023-10-16 09:00","2024-05-31 18:00","취소","취소","연속"]
[276,"광주전남","순천","광양S/S #2 M.Tr","22-23년 순천전력지사 변전협력회사 총액공사","#2M.Tr 3차 MAIN VCB 대체(즉시가압 불가)","2023-10-16 08:00","2023-10-17 18:00","취소","취소","연속"]
[277,"광주전남","순천","여수T/P #1 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","M.Tr 부싱교체, 2차 GIS 정밀점검(즉시가압 불가)","2023-10-16 09:00","2023-10-20 18:00","2023-10-16 09:00","2023-10-20 18:00","연속"]
[278,"광주전남","순천","여수T/P #2 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","#2M.Tr 보통점검, 1차 GIS 보통점검, 2차 GIS 정밀점검(23~24일 즉시가압 불가)","2023-10-23 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-10-27 18:00","연속"]
[279,"광주전남","순천","여수T/P 예비 M.TR CB","22-23년 순천전력지사 변전협력회사 총액공사","M.Tr 부싱교체(즉시가압 불가)","2023-10-16 09:00","2023-10-20 18:00","취소","취소","연속"]
[280,"광주전남","순천","광양율촌CC T/L","345kV 율촌CC분기 T/L EBA 자기애관 교체공사","광양-율촌CC 3상, 율촌CC-여수TP 3상 애관교체(자기애관 → 폴리머애관)","2023-10-10 09:00","2023-10-12 18:00","취소","취소","연속"]
[281,"광주전남","순천","율촌CC여수TP T/L","345kV 율촌CC분기 T/L EBA 자기애관 교체공사","광양-율촌CC 3상, 율촌CC-여수TP 3상 애관교체(자기애관 → 폴리머애관)","2023-10-04 09:00","2023-10-06 18:00","2023-10-04 09:00","2023-10-06 18:00","연속"]
[282,"대구","달성","고령의령#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 서대구-고령T/L 수평 추락방지장치 설치공사(345kV 고령-의령,154kV 서대구-남구미 T/L 병가선로)(안전확보)","2023-10-04 07:00","2023-10-04 18:00","2023-10-04 07:00","2023-10-04 18:00","연속"]
[283,"대구","달성","고령S/S #3 M.Tr","#3M.Tr OLTC정밀, M.Tr 및 기타설비 보통점검","-OLTC 정밀점검 -1·2차GIS, M.Tr, S.Tr VCB, S.Tr, 1·2차LA, 3차PT 정기검사 -부싱절연유 채유","2023-10-16 09:00","2023-10-20 18:00","2023-10-16 09:00","2023-10-20 18:00","연속"]
[284,"대구","달성","고령S/S #2 M.Tr","#2M.Tr 보통점검 및 누유보수","-M.Tr 및 3차 PT 보통점검 -3차 부싱 누유보수 -부싱절연유 채유","2023-10-11 09:00","2023-10-13 18:00","2023-10-11 09:00","2023-10-13 18:00","연속"]
[285,"대구","달성","서대구고령#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 서대구-고령T/L 수평 추락방지장치 설치공사(345kV 고령-의령,154kV 서대구-남구미 T/L 병가선로)(안전확보)","2023-10-04 07:00","2023-10-13 18:00","2023-10-04 07:00","2023-10-13 18:00","연속"]
[286,"대구","달성","신경산대구#2 T/L","T/L GIS 정밀점검","T/L GIS 정밀점검","2023-10-30 09:00","2023-11-02 18:00","2023-10-30 09:00","2023-11-02 18:00","연속"]
[287,"대구","달성","북경남대구#1 T/L","T/L, TIE GIS 정밀점검","T/L, TIE GIS 정밀점검","2023-10-10 09:00","2023-10-14 18:00","2023-10-10 09:00","2023-10-14 18:00","연속"]
[288,"대구","달성","대구S/S #1 BUS","[TEST]T/L GIS 정밀점검","[TEST]T/L GIS 정밀점검","2023-10-14 17:00","2023-10-14 18:00","2023-10-14 17:00","2023-10-14 18:00","연속"]
[289,"대구","달성","대구S/S #2 M.Tr","#2M.Tr 휴전작업","-OLTC 정밀점검 -1·2·3차 GIS, 2차LA, S.Tr 정기점검 -M.Tr 보호반 대체 -부싱절연유 채유","2023-10-23 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-10-27 18:00","연속"]
[290,"대구","달성","대구S/S #1 BUS","[TEST]T/L GIS 정밀점검","[TEST]T/L GIS 정밀점검","2023-10-19 17:00","2023-10-19 18:00","2023-10-19 17:00","2023-10-19 18:00","연속"]
[291,"대구","달성","신경산대구#1 T/L","T/L GIS 정밀점검","T/L GIS 정밀점검","2023-10-16 09:00","2023-10-19 18:00","2023-10-16 09:00","2023-10-19 18:00","연속"]
[292,"대구","칠곡","북대구S/S #3 M.Tr","23년 하반기 154kV GIS 정밀점검(안전이격 확보용)","23년 하반기 154kV GIS 정밀점검(안전이격 확보용)","2023-10-31 09:30","2023-11-02 18:00","2023-10-31 09:30","2023-11-02 18:00","연속"]
[293,"대구","칠곡","북대구S/S #4 M.Tr","23년 하반기 154kV GIS 정밀점검","23년 하반기 154kV GIS 정밀점검","2023-10-11 09:30","2023-10-13 18:00","2023-10-11 09:30","2023-10-13 18:00","연속"]
[294,"대구","칠곡","서대구고령#1 T/L","서대구S/S 345kV 주변압기측 현대화 공사","345kV 송전선로 인출측 CVT, LA 이설 작업","2023-10-19 08:00","2023-10-20 18:00","2023-10-19 08:00","2023-10-20 18:00","연속"]
[295,"대구","칠곡","북대구서대구#1 T/L","서대구S/S 345kV 주변압기측 현대화 공사","345kV 송전선로 인출측 CVT, LA 이설 작업","2023-10-23 08:00","2023-10-24 18:00","2023-10-23 08:00","2023-10-24 18:00","연속"]
[296,"대구","칠곡","북경남서대구#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치공사(345kV 북경남-무주양수T/L 병가선로)(안전확보)","2023-10-16 07:00","2023-11-10 18:00","취소","취소","연속"]
[297,"대구","포항","신영일S/S #3 M.Tr","2022~23년도 포항전력지사 변전총액공사","신영일S/S #3M.Tr 보통점검","2023-10-18 09:00","2023-10-19 18:00","2023-10-18 09:00","2023-10-19 18:00","연속"]
[298,"대구","포항","신포항신영일 T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","기설철탑 수평 추락방지장치 설치","2023-10-23 08:00","2023-10-31 18:00","2023-10-24 09:00","2023-10-25 18:00","연속"]
[299,"대구","포항","신포항신월성NP#3 T/L","‘23년 포항전력지사 하반기 154kV GIS 기기점검공사","신포항S/S 7371 GCB조작시험, 7300 GCB 보통점검[발주]","2023-10-19 09:00","2023-10-19 18:00","2023-10-19 09:00","2023-10-19 18:00","연속"]
[300,"대구","포항","신포항신월성NP#1 T/L","‘23년 포항전력지사 하반기 154kV GIS 기기점검공사","신포항S/S 7572 GCB 보통점검[발주]","2023-10-26 09:00","2023-10-27 18:00","2023-10-26 09:00","2023-10-27 18:00","연속"]
[301,"대구","포항","신포항S/S #4 M.Tr","신포항S/S 345kV 주변압기측 현대화 공사","신포항S/S 345kV 주변압기측 현대화 공사","2023-10-16 08:00","2023-10-27 17:00","2023-10-16 08:00","2023-10-27 17:00","연속"]
[302,"대구","포항","신포항신월성NP#2 T/L","‘23년 포항전력지사 하반기 154kV GIS 기기점검공사","신포항S/S 7472 GCB 보통점검[발주]","2023-10-30 09:00","2023-10-31 18:00","2023-10-30 09:00","2023-10-31 18:00","연속"]
[303,"대구","포항","신포항신월성NP#4 T/L","‘23년 포항전력지사 하반기 154kV GIS 기기점검공사","신포항S/S 7272 GCB 보통점검[발주]","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[304,"대구","포항","신포항S/S #3 M.Tr","신포항S/S 345kV 주변압기측 현대화 공사","신포항S/S 345kV 주변압기측 현대화 공사","2023-10-30 08:00","2023-11-10 17:00","2023-10-30 08:00","2023-11-10 17:00","연속"]
[305,"대구","포항","월성N/P SEC CB 70710","‘23년 포항전력지사 하반기 154kV GIS 기기점검공사","월성S/Y 70-71 GIS 보통점검[발주]","2023-10-20 09:00","2023-10-20 14:00","2023-10-20 09:00","2023-10-20 14:00","연속"]
[306,"대구","포항","월성NP신월성NP#2 T/L","‘23년 포항전력지사 하반기 154kV GIS 기기점검공사","월성S/Y 7871GIS 보통점검[발주]","2023-10-13 09:00","2023-10-13 18:00","2023-10-13 09:00","2023-10-13 18:00","연속"]
[307,"대구","포항","월성N/P SEC CB 75760","‘23년 포항전력지사 하반기 154kV GIS 기기점검공사","월성S/Y 75-76 GIS 보통점검[발주]","2023-10-20 14:00","2023-10-20 18:00","2023-10-20 14:00","2023-10-20 18:00","연속"]
[308,"경북","구미","선산S/S #70 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 70BAY GIS 교체(70BUS 교체)","2023-10-04 09:00","2023-10-10 09:00","2023-10-04 09:00","2023-10-10 09:00","연속"]
[309,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 70BAY GIS 교체(70BUS 무부하 가압)","2023-10-09 09:00","2023-10-10 09:00","2023-10-09 09:00","2023-10-10 09:00","연속"]
[310,"경북","구미","선산S/S #1 M.Tr","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 70BAY GIS 교체(75BUS 교체)","2023-10-10 09:00","2023-12-19 18:00","2023-10-10 09:00","2023-12-19 18:00","연속"]
[311,"경북","구미","선산S/S #75 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 70BAY GIS 교체(75BUS 교체)","2023-10-10 09:00","2023-10-25 09:00","2023-10-10 09:00","2023-10-27 09:00","연속"]
[312,"경북","구미","서대구선산#1 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 70BAY GIS 교체(70BUS 교체)","2023-10-04 09:00","2023-12-19 18:00","2023-10-04 09:00","2023-12-19 18:00","연속"]
[313,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 70BAY GIS 교체(75BUS 무부하 가압)","2023-10-24 09:00","2023-10-25 09:00","2023-10-26 09:00","2023-10-27 09:00","연속"]
[314,"경북","영주","신영주한울NP#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","TCSC 냉각설비 보통점검 72BAY B/F 보호반 대체","2023-10-26 09:00","2023-11-08 18:00","2023-10-26 09:00","2023-11-08 18:00","연속"]
[315,"경북","영주","신영주S/S #1 TCSC CB","2022-23년 영주전력지사 변전협력회사 총액공사","TCSC 냉각설비 보통점검","2023-10-26 09:00","2023-11-08 18:00","2023-10-26 09:00","2023-11-08 18:00","연속"]
[316,"경북","영주","신영주S/S #2 M.Tr","2022-23년 영주전력지사 변전협력회사 총액공사","부싱절연유 채유","2023-10-26 09:00","2023-10-26 18:00","2023-10-25 09:00","2023-10-25 18:00","연속"]
[317,"경북","영주","한울1NP한울2NP#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","초고압애자 절연 코팅","2023-10-05 09:00","2023-10-06 18:00","2023-10-05 09:00","2023-10-06 18:00","연속"]
[318,"부산울산","동부산","고리N/P #75 BUS","고리NP S/Y 74BAY 이음관련 점검","고리NP S/Y 74BAY 이음관련 점검","2023-10-30 09:00","2023-11-10 18:00","취소","취소","연속"]
[319,"부산울산","동부산","신양산고리NP#1 T/L","신양산고리NP#1 T/L","신양산S/S 345kV 용량부족차단기 교체공사(3차) 사전작업 - 신양산-고리#1T/L 인출BAY 변경을 위한 사전작업 (76BAY -> 75BAY) - 신양산-고리#1T/L 외장 LA 이설","2023-10-26 08:00","2023-11-01 18:00","취소","취소","연속"]
[320,"부산울산","동부산","신양산신대연#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","154kV 시랑-좌동#2T/L 피뢰기 설치 관련 안전이격확보 휴전","2023-10-04 08:00","2023-10-05 18:00","2023-10-04 08:00","2023-10-05 18:00","연속"]
[321,"부산울산","동부산","신양산S/S #3 M.Tr","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(3차) - 75BAY GIS 50kA 3CCT 철거 - 75BAY GIS 63kA 3CCT 설치","2023-10-16 08:00","2024-03-08 18:00","취소","취소","연속"]
[322,"부산울산","동부산","신양산S/S CB 7571","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(3차) ※ 휴전대상 : 7571CB - 75BAY GIS 50kA 3CCT 철거 - 75BAY GIS 63kA 3CCT 설치","2023-10-16 08:00","2024-03-08 18:00","취소","취소","연속"]
[323,"부산울산","북부산","북부산S/S #1 M.Tr","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 345kV #1M.Tr 2차 GIS(6144) 메커니즘 보강공사","2023-10-19 09:00","2023-10-19 18:00","취소","취소","연속"]
[324,"부산울산","북부산","북부산S/S #2 M.Tr","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 345kV #2M.Tr 2차 GIS(6244) 메커니즘 보강공사","2023-10-04 09:00","2023-10-04 18:00","2023-10-04 09:00","2023-10-04 18:00","연속"]
[325,"부산울산","북부산","북부산신울산#2 T/L","북부산S/S STATCOM용 345kV GIS 설치공사","STATCOM용 345kV GIS 2CB 설치 - 신설차단기 BUS 연결(#1) 관련 안전작업차 휴전","2023-10-26 09:00","2023-10-26 18:00","2023-10-26 09:00","2023-10-26 18:00","연속"]
[326,"부산울산","북부산","북부산S/S CB 7871","23년 북부산전력지사 345kV GIS 보통점검","북부산S/S 345kV 7871 차단기 보통점검","2023-10-02 08:00","2023-10-02 18:00","2023-10-02 08:00","2023-10-02 18:00","연속"]
[327,"부산울산","북부산","북부산S/S #71 BUS","북부산S/S STATCOM용 345kV GIS 설치공사","STATCOM용 345kV GIS 2CB 설치 - 신설차단기 BUS 연결(#1)","2023-10-23 09:00","2023-11-05 18:00","2023-10-23 09:00","2023-11-05 18:00","연속"]
[328,"부산울산","북부산","북부산S/S #3 M.Tr","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 345kV #3M.Tr 2차 GIS(6344) 메커니즘 보강공사","2023-10-20 09:00","2023-10-20 18:00","2023-10-20 09:00","2023-10-20 18:00","연속"]
[329,"부산울산","북부산","북부산신울산#2 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-신울산#2T/L 수평추락방지장치 설치 : 1~110호, 87기","2023-10-26 08:00","2023-11-04 18:00","2023-10-26 08:00","2023-11-04 18:00","연속"]
[330,"부산울산","북부산","북부산S/S #3 Sh.R CB","23년 북부산전력지사 345kV GIS 보통점검","북부산S/S 345kV #3Sh.R 차단기(7877) 보통점검","2023-10-13 08:00","2023-10-13 18:00","2023-10-13 08:00","2023-10-13 18:00","연속"]
[331,"부산울산","북부산","북부산S/S #76 BUS","북부산S/S STATCOM용 345kV GIS 설치공사","- STATCOM용 345kV GIS 2CB 설치 - 신설 차단기 BUS 연결(#2)","2023-10-05 09:00","2023-10-18 18:00","2023-10-05 09:00","2023-10-18 18:00","연속"]
[332,"부산울산","북부산","북부산S/S #4 M.Tr","23년 북부산전력지사 345kV GIS 정밀점검공사","북부산S/S 345kV #4M.Tr GIS 정밀점검 - 점검대상 : 7872, 7800 GIS","2023-10-30 08:00","2023-11-04 18:00","2023-10-30 08:00","2023-11-04 18:00","연속"]
[333,"부산울산","북부산","북부산S/S #4 Sh.R CB","23년 북부산전력지사 345kV GIS 보통점검","북부산S/S 345kV #4Sh.R 차단기(7A77) 보통점검","2023-10-11 08:00","2023-10-11 18:00","2023-10-11 08:00","2023-10-11 18:00","연속"]
[334,"부산울산","북부산","북부산S/S CB 7972","23년 북부산전력지사 345kV GIS 보통점검","북부산S/S 345kV #4Sh.R 차단기(7972) 보통점검","2023-10-12 08:00","2023-10-12 18:00","2023-10-12 08:00","2023-10-12 18:00","연속"]
[335,"부산울산","북부산","북부산S/S #2 Sh.R CB","22-23년 북부산전력지사 총액공사","북부산S/S 345kV #2Sh.R 부싱 절연유 채유","2023-10-12 10:00","2023-10-12 12:00","2023-10-12 10:00","2023-10-12 12:00","연속"]
[336,"부산울산","서부산","서부산S/S #3,4GT CB","서부산S/S 345kV #3,4 G/T GIS 보통점검","서부산S/S 345kV #3,4 G/T GIS 보통점검 (부산복합 3,4G/T 법정검사 예정)","2023-10-13 09:00","2023-10-13 18:00","2023-10-13 09:00","2023-10-13 18:00","연속"]
[337,"부산울산","서부산","신김해신녹산#1 T/L","23년 서부산전력지사 가공송전 순시점검 위탁공사","154kV 미음-녹산#1T/L 정밀점검간 안전이격","2023-10-16 08:00","2023-10-16 18:00","2023-10-16 08:00","2023-10-16 18:00","연속"]
[338,"부산울산","서부산","신김해신녹산#2 T/L","23년 서부산전력지사 가공송전 순시점검 위탁공사","154kV 미음-녹산#2T/L 정밀점검간 안전이격","2023-10-18 08:00","2023-10-18 18:00","2023-10-18 08:00","2023-10-18 18:00","연속"]
[339,"부산울산","서부산","신녹산S/S CB 7372","신녹산S/S 345kV #3 M.Tr 1차 GIS(7372) 보통점검","신녹산S/S 345kV #3 M.Tr 1차 GIS(7372) 보통점검","2023-10-20 09:00","2023-10-20 18:00","2023-10-20 09:00","2023-10-20 18:00","연속"]
[340,"부산울산","서부산","신녹산S/S CB 7272","신녹산S/S 345kV #2 M.Tr 1차 GIS(7272) 보통점검","신녹산S/S 345kV #2 M.Tr 1차 GIS(7272) 보통점검","2023-10-19 09:00","2023-10-19 18:00","2023-10-19 09:00","2023-10-19 18:00","연속"]
[341,"부산울산","울산","남울산울산TP#1 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-10-30 07:00","2023-11-01 18:00","2023-10-30 07:00","2023-11-01 18:00","연속"]
[342,"부산울산","울산","동울산S/S #1 M.Tr","23년 울산전력지사 개폐장치 보통점검공사","- 2차 GIS 보통점검 - #1S.Tr 보통점검 - 3차 GIS(4184) 보통점검 - 3차 LA 보통점검","2023-10-27 09:00","2023-10-27 18:00","2023-10-27 09:00","2023-10-27 18:00","연속"]
[343,"부산울산","울산","신온산S/S #1 M.Tr","22~23년 변전협력회사 총액공사","- M.Tr 보통점검 - 부싱 절연유 채유 - 2차 GIS(6144) 보통점검, - 1,2차 피뢰기 보통점검","2023-10-30 09:00","2023-10-31 18:00","2023-10-30 09:00","2023-10-31 18:00","연속"]
[344,"부산울산","울산","신온산S/S SOIL#5 T/L CB","22~23년 변전협력회사 총액공사","- 7172 GIS 보통점검","2023-10-26 09:00","2023-10-26 18:00","2023-10-26 09:00","2023-10-26 18:00","연속"]
[345,"부산울산","울산","신울산S/S #4 M.Tr","23년 울산전력지사 개폐장치 보통점검공사","- 2차 GIS(6464) 보통점검","2023-10-30 09:00","2023-10-30 18:00","2023-10-30 09:00","2023-10-30 18:00","연속"]
[346,"부산울산","울산","신울산S/S CB 7800","신울산S/S 345kV 용량대체공사","- 78BAY B/F 보호반 결선 - 신울산-동울산T/L 차단기(7871, 7800CB) 연동시험","2023-10-05 09:00","2023-10-06 18:00","2023-10-05 09:00","2023-10-06 18:00","연속"]
[347,"부산울산","울산","신울산S/S CB 7871","신울산S/S 345kV 용량대체공사","- 78BAY B/F 보호반 결선 - 신울산-동울산T/L 차단기(7871, 7800CB) 연동시험","2023-10-05 09:00","2023-10-06 18:00","2023-10-05 09:00","2023-10-06 18:00","연속"]
[348,"부산울산","울산","신울산S/S CB 7871","신울산S/S 345kV 용량대체공사","- 동울산-신울산T/L 무부하가압 - 7871, 7800CB 개방(즉시가압가능)","2023-10-10 09:00","2023-10-11 18:00","2023-10-10 09:00","2023-10-11 18:00","연속"]
[349,"부산울산","울산","신울산S/S CB 7800","신울산S/S 345kV 용량대체공사","- 동울산-신울산T/L 무부하가압 - 7871, 7800CB 개방(즉시가압가능)","2023-10-10 09:00","2023-10-11 18:00","2023-10-10 09:00","2023-10-11 18:00","연속"]
[350,"부산울산","울산","신울산S/S CB 7900","신울산S/S 345kV 용량대체공사","- 79BAY B/F 보호반 결선 - 신울산-월성NP T/L 차단기(7971, 7900CB) 연동시험","2023-10-17 09:00","2023-10-18 18:00","2023-10-17 09:00","2023-10-18 18:00","연속"]
[351,"부산울산","울산","신울산S/S CB 7971","신울산S/S 345kV 용량대체공사","- 79BAY B/F 보호반 결선 - 신울산-월성NP T/L 차단기(7971, 7900CB) 연동시험","2023-10-17 09:00","2023-10-18 18:00","2023-10-17 09:00","2023-10-18 18:00","연속"]
[352,"부산울산","울산","신울산S/S CB 7971","신울산S/S 345kV 용량대체공사","- 신울산-월성NP T/L 무부하가압 - 7971, 7900CB 개방(즉시가압가능)","2023-10-19 09:00","2023-10-20 18:00","2023-10-19 09:00","2023-10-20 18:00","연속"]
[353,"부산울산","울산","신울산S/S CB 7900","신울산S/S 345kV 용량대체공사","- 신울산-월성NP T/L 무부하가압 - 7971, 7900CB 개방(즉시가압가능)","2023-10-19 09:00","2023-10-20 18:00","2023-10-19 09:00","2023-10-20 18:00","연속"]
[354,"부산울산","울산","울산C/C CB 7A00","23년 울산전력지사 개폐장치 보통점검공사","- 7A00 GIS 보통점검","2023-10-06 09:00","2023-10-06 18:00","취소","취소","연속"]
[355,"부산울산","직할","신대연S/S CB 7272","22-23년 직할 변전협력회사 총액공사","신대연S/S 7272 GIS 보통점검","2023-10-10 09:30","2023-10-10 18:00","2023-10-10 09:30","2023-10-10 18:00","연속"]
[356,"부산울산","직할","신양산신대연#2 T/L","23년 직할 345kV GIS 정밀점검공사","신대연S/S 7271, 7200 GIS 정밀점검","2023-10-30 09:30","2023-11-04 18:00","2023-10-30 09:30","2023-11-04 18:00","연속"]
[357,"부산울산","직할","신양산신대연#1 T/L","23년 직할 345kV GIS 정밀점검공사","신대연S/S 7171, 7100 GIS 정밀점검","2023-10-16 09:30","2023-10-21 18:00","2023-10-16 09:30","2023-10-21 18:00","연속"]
[358,"경남","직할","신김해창원#1 T/L","신김해S/S 345kV 신김해-창원#1T/L 선로 휴전","신김해S/S 345kV 신김해-창원#1T/L(7100,7172) GIS 보통점검 7100,7172 GIS 공기조작부 점검, 보조계전기, 전자변 교체 PT,LA 보통점검","2023-10-10 09:00","2023-10-13 18:00","2023-10-10 09:00","2023-10-13 18:00","연속"]
[359,"경남","직할","신김해S/S #2 M.Tr","신김해S/S 345kV #2M.Tr C상 고장복구 공사","신김해S/S 345kV #2M.Tr C상 고장복구 공사","2023-10-23 09:00","2023-11-17 18:00","2023-10-23 09:00","2023-11-17 18:00","연속"]
[360,"경남","직할","신김해S/S #4 M.Tr","신김해S/S #4M.Tr 1,2,3차 GIS 점검","신김해S/S #4M.Tr 1,2,3차 GIS 점검 7872,4479 차단기 조작, 6444 GIS 베어링교체, 부싱절연유 채유","2023-10-06 08:00","2023-10-06 18:00","2023-10-06 08:00","2023-10-06 18:00","연속"]
[361,"경남","직할","창원신고성#2 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-10-07 07:00","2023-10-07 14:00","취소","취소","연속"]
[362,"경남","진주","의령산청양수#1 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2023-10-02 07:00","2023-10-25 18:00","취소","취소","매일"]
[363,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치설치 2. 작업구간 : 수평 추락방지장치 No.134~151","2023-10-15 07:00","2023-10-15 18:00","취소","취소","연속"]
[364,"경남","진주","의령신마산#1 T/L","의령S/S 345kV 의령-신마산#1T/L 7571 GIS 보통 등","[주] 의령S/S 345kV 의령-신마산#1T/L 7571 GIS 보통 7900, 7971 [병행] LA 초기점검, PT 보통점검","2023-10-10 08:30","2023-10-11 18:00","취소","취소","연속"]
[365,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151","2023-10-08 07:00","2023-10-08 18:00","취소","취소","연속"]
[366,"경남","진주","의령신마산#2 T/L","의령S/S 345kV 의령-신마산#2T/L LA 초기점검","의령S/S 345kV 의령-신마산#2T/L LA 초기점검","2023-10-12 08:30","2023-10-12 18:00","취소","취소","연속"]
[367,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151","2023-10-29 07:00","2023-10-29 18:00","취소","취소","연속"]
[368,"경남","진주","의령산청양수#2 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#2T/L측 수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2023-10-26 07:00","2023-11-15 18:00","취소","취소","매일"]
[369,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치설치 2. 작업구간 : 수평 추락방지장치 No.134~151","2023-10-22 07:00","2023-10-22 18:00","취소","취소","연속"]
[370,"경남","진주","하동T/P CB 7372","하동T/P 345kV 7372 GIS 보통점검","하동T/P 345kV 7372 GIS 보통점검 - 3호기 O/H 기간 10/13 ~ 11/2","2023-10-13 09:00","2023-10-13 18:00","2023-10-13 09:00","2023-10-13 18:00","연속"]
[371,"경남","진주","하동T/P CB 7300","하동T/P 345kV 7300 GIS 보통점검","하동T/P 345kV 7300 GIS 보통점검 - 3호기 O/H 기간 10/13 ~ 11/2","2023-10-13 09:00","2023-10-13 18:00","2023-10-13 09:00","2023-10-13 18:00","연속"]
[372,"경남","진주","하동T/P CB 7600","하동T/P 345kV 7600 GIS 조작시험","하동T/P 345kV 7600 GIS 조작시험 - 6호기 O/H 기간 10/19 ~ 11/6","2023-10-20 10:00","2023-10-20 18:00","2023-10-25 10:00","2023-10-25 18:00","연속"]
[373,"경남","진주","하동T/P CB 7672","하동T/P 345kV 7672 GIS 조작시험","하동T/P 345kV 7672 GIS 조작시험 - 6호기 O/H 기간 10/19 ~ 11/6","2023-10-20 10:00","2023-10-20 18:00","2023-10-25 10:00","2023-10-25 18:00","연속"]
[374,"경남","진주","하동T/P SEC CB 70710","하동T/P 345kV #70-71 GIS 조작시험","하동T/P 345kV #70-71 GIS 조작시험","2023-10-10 10:00","2023-10-10 14:00","2023-10-10 10:00","2023-10-10 14:00","연속"]
[375,"경남","진주","하동T/P SEC CB 75760","하동T/P 345kV #75-76 GIS 조작시험","하동T/P 345kV #75-76 GIS 조작시험","2023-10-10 14:00","2023-10-10 18:00","2023-10-10 14:00","2023-10-10 18:00","연속"]
[376,"경남","통영","고성T/P CB 7271","고성하이S/Y 345kV 신고성-고성하이#1TL GIS 7271 보통점검","고성하이S/Y 345kV 신고성-고성하이#1T/L GIS 7271 보통점검","2023-10-04 10:00","2023-10-04 18:00","취소","취소","연속"]
[377,"경남","통영","신고성S/S #3 M.Tr","신고성S/S #3M.Tr LA 교체 등","1. 신고성S/S #3M.Tr 2차 LA A,B,C 교체 2. 신고성S/S #3M.Tr 3차 LA A,B,C 보통점검 3. 신고성S/S #3S.Tr VCB 조작시험","2023-10-30 09:00","2023-10-30 18:00","2023-10-30 09:00","2023-10-30 18:00","연속"]
[378,"경남","통영","신고성S/S #4 M.Tr","신고성S/S #4M.Tr 1차 GIS 보통점검 등","1. #4M.Tr 1차 GIS 보통점검(7672, 7600) 2. #4M.Tr 2차 GIS 보통점검 및 전자변 교체 3. #4M.Tr 3차 VCB 보통점검 및 3차 모선 보통점검 4. #4M.Tr 1,2,3차 LA 교체 5. #4-1,2,3 Sh.R 및 VCB 보통점검 6. #4Sh.R PNL 정기점검 7. C상 H1 부싱절연유 채유 및 도블","2023-10-31 09:00","2023-11-03 18:00","2023-10-31 09:00","2023-11-03 18:00","연속"]
[379,"경남","통영","신마산신고성#1 T/L","삼천포S/Y, 신고성S/S 345kV GIS 철거공사","1. 345kV GIS 40kA 4,000A x 30CB 가스회수 및 철거 2. 기타 부대서식","2023-10-23 09:00","2023-10-27 18:00","취소","취소","연속"]
[380,"경남","함안","북경남무주양수 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치공사(345kV 북경남-무주양수T/L 병가선로)(안전확보)","2023-10-16 07:00","2023-11-07 18:00","취소","취소","연속"]
[381,"경남","함안","북경남S/S CB 7771","북경남S/S #5Sh.R 1차 선로측 GIS(7771CB) 보통점검","북경남S/S 345kV #5Sh.R 1차 선로측 GIS(7771CB) 보통점검","2023-10-05 09:30","2023-10-05 17:30","2023-10-05 09:30","2023-10-05 17:30","연속"]
[382,"경남","함안","신마산신김해#2 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-10-11 07:00","2023-10-11 18:00","취소","취소","연속"]
[383,"경북",null,"한울N/P #1호기 주변압기 (CB 7100, 7172)","한울1호기 제 25차 계획예방정비 * 조작차단기: 7100, 7172","주/보조변압기 및 발전기 점검","2023-10-06 16:00","2023-12-06 16:00","2023-10-06 16:00","2023-12-06 16:00","연속"]
[384,"광주전남",null,"한빛N/P #2호기 기동변압기 X02 (CB 7F71, 7F00)","한빛2호기 26차 계획예방정비 수행 * 조작차단기 : CB 7F00, 7F71","○ 기동변압기(X02) 점검 ○ 4.16kV 차단기반 교체 공사 수행","2023-10-05 09:00","2023-11-08 09:00","2023-10-05 09:00","2023-11-08 09:00","연속"]
[385,"경기북부",null,"동두천C/C #1GT 주변압기 (CB 7100, 7172)","발전기 계획예방정비","발전기 계획예방정비","2023-10-16 09:00","2023-10-18 18:00","2023-10-16 09:00","2023-10-18 18:00","연속"]
[386,"경기북부",null,"동두천C/C #2GT 주변압기 (CB 7200, 7272)","발전기 계획예방정비","발전기 계획예방정비","2023-10-19 09:00","2023-10-21 18:00","2023-10-19 09:00","2023-10-21 18:00","연속"]
[387,"경기북부",null,"동두천C/C #1ST 주변압기 (CB 7300, 7372)","발전기 계획예방정비","발전기 계획예방정비","2023-10-16 09:00","2023-10-25 18:00","2023-10-16 09:00","2023-10-25 18:00","연속"]
[388,"서울",null,"중부서울CC#2 T/L","#2호기 주변압기 및 보조변압기 점검","#2호기 주변압기 및 보조변압기 점검","2023-10-11 10:00","2023-10-26 15:00","2023-10-11 10:00","2023-10-26 15:00","연속"]
[389,"서울",null,"중부서울CC#2 T/L","전기설비 정기검사 수검","전기설비 정기검사 수검","2023-11-10 09:00","2023-11-10 16:00","2023-11-10 09:00","2023-11-10 16:00","연속"]
[390,"강원",null,"양양P/P #3호기 주변압기 (CB 7200, 7272)","#3호기 계획중간정비","양양P/P No.3 Main TR 휴전 (#3 UCB Operating Rod 측정)","2023-10-05 09:00","2023-10-05 18:00","2023-10-05 09:00","2023-10-05 18:00","연속"]
[391,"강원",null,"양양P/P #4호기 주변압기 (CB 7300, 7372)","#4호기 계획중간정비","양양P/P No.4 Main Tr 휴전","2023-10-19 09:00","2023-10-19 18:00","2023-10-19 09:00","2023-10-19 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":804,"n_cols":11,"rows_kept":804,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2023년도 10월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의S/S CB 6100","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T)","2023-10-04 09:00","2023-11-02 18:00","취소","취소","연속"]
[2,"서울","성동","구의광장#2 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T)","2023-10-04 09:00","2023-11-02 18:00","취소","취소","연속"]
[3,"서울","성동","구의광장#1 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 1BUS, CB, 1DS 무부하가압","2023-10-23 16:00","2023-10-24 16:00","취소","취소","연속"]
[4,"서울","성동","구의광장#1 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 2BUS 무부하가압","2023-10-10 10:00","2023-10-10 16:00","취소","취소","연속"]
[5,"서울","성동","금오상계#1 T/L","23년 성동P/O 노후 보호배전반 교체공사","금오,상계S/S 154kV 금오상계#1T/L 보호배전반 노후대체","2023-10-23 09:00","2023-10-25 18:00","2023-10-23 09:00","2023-10-25 18:00","연속"]
[6,"서울","성동","성동휘경#1 T/L","2023년 성동P/O 변전정비회사 총액공사","154kV GIS 보통점검","2023-10-26 09:00","2023-10-26 18:00","2023-10-26 09:00","2023-10-26 18:00","연속"]
[7,"서울","성동","성동휘경#2 T/L","2023년 성동P/O 변전정비회사 총액공사","154kV GIS 조작시험","2023-10-27 09:00","2023-10-27 18:00","2023-10-27 09:00","2023-10-27 18:00","연속"]
[8,"서울","성동","양주쌍문#2 T/L","2023년 성동P/O 변전정비회사 총액공사","170kV GIS 보통점검","2023-10-24 09:00","2023-10-24 18:00","2023-10-24 09:00","2023-10-24 18:00","연속"]
[9,"서울","성동","휘경종암#1 T/L","2023년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2023-10-05 10:00","2023-10-05 18:00","2023-10-05 10:00","2023-10-05 18:00","연속"]
[10,"서울","성동","휘경종암#2 T/L","2023년 성동P/O 변전협력회사 총액공사","154kV GIS 보통점검","2023-10-06 10:00","2023-10-06 18:00","2023-10-06 10:00","2023-10-06 18:00","연속"]
[11,"서울","성동","창동쌍문#1 T/L","창동S/S 154kV 창동쌍문#1,2T/L 제어케이블 이설(SA)","창동S/S 154kV 창동쌍문#1,2T/L 케이블 이설(RTU → LID)","2023-10-10 09:00","2023-10-11 18:00","2023-10-10 09:00","2023-10-11 18:00","연속"]
[12,"서울","성동","창동쌍문#2 T/L","창동S/S 154kV 창동쌍문#1,2T/L 제어케이블 이설(SA)","창동S/S 154kV 창동쌍문#1,2T/L 케이블 이설(RTU → LID)","2023-10-12 09:00","2023-10-13 18:00","2023-10-12 09:00","2023-10-13 18:00","연속"]
[13,"서울","성동","창동쌍문#2 T/L","창동S/S 154kV 장기사용 GIS 교체공사","154kV GIS 1차분 교체 - 상계창동#1T/L, #1M.Tr 1차, 6100B/T - #2BUS 시험가압선로","2023-10-19 09:00","2023-10-20 18:00","2023-10-19 09:00","2023-10-20 18:00","연속"]
[14,"서울","성동","상계창동#1 T/L","창동S/S 154kV 장기사용 GIS 교체공사","154kV GIS 1차분 교체 - 상계창동#1T/L, #1M.Tr 1차, 6100B/T","2023-10-16 09:00","2023-11-19 18:00","2023-10-16 09:00","2023-11-19 18:00","연속"]
[15,"서울","성동","화양광장 T/L","'22~'23년 구리 가공송전협력 총액공사_추락방지, 피뢰기","추락방지장치(No.31), 피뢰기 설치(No.32)","2023-10-11 08:00","2023-10-11 18:00","2023-10-11 08:00","2023-10-11 18:00","연속"]
[16,"서울","중부","중부용산#2 T/L","중부S/S 154kV 장기사용 GIS 교체공사","- #3M.Tr 2차, 중부용산#2T/L GIS 교체 - #3M.Tr 2차 LA 설치","2023-10-10 09:00","2023-11-03 18:00","2023-10-10 09:00","2023-11-03 18:00","연속"]
[17,"서울","중부","중부아현 T/L","154kV 중부아현T/L EBG 가스 채취밸브 취부","154kV 중부아현T/L 중부EBG 가스 채취밸브 취부","2023-10-23 09:00","2023-10-24 18:00","취소","취소","연속"]
[18,"서울","직할","종로서소문 T/L","서소문S/S 디지털화","서소문S/S 디지털화 ㅇ 현장정보처리반 - SA LID반 제어케이블 이설 (GIS, T/L 보호반 감시,제어,계측) ㅇ 현장 - SCADA 간 이설포인트 연동시험 등","2023-10-23 09:00","2023-10-25 18:00","취소","취소","매일"]
[19,"서울","직할","중앙서소문 T/L","서소문S/S 디지털화","서소문S/S 디지털화 ㅇ 현장정보처리반 - SA LID반 제어케이블 이설 (GIS, T/L 보호반 감시,제어,계측) ㅇ 현장 - SCADA 간 이설포인트 연동시험 등","2023-10-30 09:00","2023-11-01 18:00","취소","취소","매일"]
[20,"남서울","강남","논현논일#1 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 :논현-논일#1,2T/L GIS","2023-10-07 07:00","2023-10-08 12:00","2023-10-07 07:00","2023-10-08 12:00","연속"]
[21,"남서울","강남","논현논일#2 T/L","2023년 강남전력지사 170kV GIS 정밀점검공사","- 대상설비 :논현-논일#1,2T/L GIS","2023-10-08 12:00","2023-10-09 18:00","2023-10-08 12:00","2023-10-09 18:00","연속"]
[22,"남서울","동서울","염곡개포#2 T/L","154kV 개포인출 OF케이블 선종교체공사","○ 공사구간 : 개포S/S∼J/B#38(4구간) ○ 대상선로 : 154kV 염곡-개포#1,2T/L ○ 선종 및 길이 : 154kV OF 2,000㎟ → XLPE 1,200, 2,000㎟, 1.57km × 2C ○ 케이블 포설 및 접속개소 : 8구간(2회선×4구간), 10개소(2회선 : 중간 8, 종단 2)","2023-10-23 09:00","2024-01-15 18:00","2023-10-23 09:00","2024-01-15 18:00","연속"]
[23,"남서울","동서울","도곡개포 T/L","154kV 개포-신양재,도곡T/L 지장이설공사","양재대로 구조개선 사업(지하차도 건설)에 따른 전력설비 이설 □ 사업구간 : 154kV 도곡-개포T/L J/B#1 ~ M/H#2 □ 주요공정 - 케이블 철거 : XLPE 2,000㎟, 1C-0.32km(기설전력구+관로) - 케이블 설치 : XLPE 2,000㎟, 1C-0.35km(신설전력구+관로) - 케이블 접속 : 2개소","2023-10-04 07:00","2023-10-17 18:00","2023-10-04 07:00","2023-10-17 18:00","연속"]
[24,"남서울","동서울","동서울강동#2 T/L","22~23 동서울전력지사 가공송전 협력회사 총액공사","추락방지시설 설치(수직,수평) 11기","2023-10-21 07:00","2023-10-22 18:00","취소","취소","연속"]
[25,"남서울","동서울","동서울강동#1 T/L","22~23 동서울전력지사 가공송전 협력회사 총액공사","추락방지시설 설치(수직,수평) 11기","2023-10-14 07:00","2023-10-15 18:00","취소","취소","연속"]
[26,"남서울","동서울","산성수서#1 T/L","동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 - DS부 O-ring 추가 교체 시행","2023-10-19 09:00","2023-10-19 14:00","2023-10-30 09:00","2023-10-30 14:00","연속"]
[27,"남서울","동서울","가락수서#1 T/L","동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 -#1M.Tr 무부하가압용","2023-10-27 17:00","2023-10-27 18:00","2023-10-27 17:00","2023-10-27 18:00","연속"]
[28,"남서울","동서울","가락수서#1 T/L","동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 -의료#2T/L #1BUS측 무부하가압용","2023-10-25 17:00","2023-10-25 18:00","2023-10-25 17:00","2023-10-25 18:00","연속"]
[29,"남서울","동서울","수서S/S #1 BUS","동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 -의료#2T/L #1BUS측 정밀점검","2023-10-24 13:00","2023-10-25 18:00","2023-10-24 13:00","2023-10-25 18:00","연속"]
[30,"남서울","동서울","가락수서#1 T/L","동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 -의료#2T/L #2BUS측 무부하가압용","2023-10-24 12:00","2023-10-24 13:00","2023-10-24 12:00","2023-10-24 13:00","연속"]
[31,"남서울","동서울","수서S/S #2 BUS","동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 -의료#2T/L #2BUS측 정밀점검","2023-10-23 09:00","2023-10-24 13:00","2023-10-23 09:00","2023-10-24 13:00","연속"]
[32,"남서울","동서울","가락수서#1 T/L","동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 - DS부 O-ring 추가 교체 시행","2023-10-20 09:00","2023-10-20 14:00","2023-10-20 09:00","2023-10-20 14:00","연속"]
[33,"남서울","동서울","산성수서#2 T/L","동서울전력지사 170kV GIS 정밀점검","2023년 동서울전력지사 170kV GIS 정밀점검 - DS부 O-ring 추가 교체 시행","2023-10-19 14:00","2023-10-19 18:00","2023-10-30 14:00","2023-10-30 18:00","연속"]
[34,"남서울","동서울","신장S/S CB 6100","신장S/S 모선보호반 대체","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-10-26 09:00","2023-11-01 18:00","2023-10-26 09:00","2023-11-01 18:00","연속"]
[35,"남서울","동서울","동서울신장#2 T/L","23~24년 동서울 지중송전 위탁 총액공사","신장C/T EBA 절연유 채유","2023-10-04 08:00","2023-10-04 18:00","2023-10-04 08:00","2023-10-04 18:00","연속"]
[36,"남서울","동서울","풍납석촌#1 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-10-31 18:00","2023-11-01 18:00","2023-10-31 18:00","2023-11-01 18:00","연속"]
[37,"남서울","동서울","풍납석촌#1 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-10-23 09:00","2023-10-23 10:00","2023-10-23 09:00","2023-10-23 10:00","연속"]
[38,"남서울","동서울","풍납석촌#1 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-10-19 18:00","2023-10-20 18:00","2023-10-19 18:00","2023-10-20 18:00","연속"]
[39,"남서울","동서울","풍납S/S #1 BUS","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-10-23 09:00","2023-11-01 18:00","2023-10-23 09:00","2023-11-01 18:00","연속"]
[40,"남서울","영등포","신광명광명#1 T/L","광명S/S 154kV 가스변압기 교체공사","#1M.Tr 교체 완료 후 무부하가압용(신광명-광명#1T/L & 60BUS 사용)","2023-10-16 09:00","2023-10-17 18:00","2023-10-16 09:00","2023-10-17 18:00","연속"]
[41,"남서울","영등포","신광명광명#1 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지설치","2023-10-30 07:00","2023-10-31 18:00","2023-10-30 07:00","2023-10-31 18:00","연속"]
[42,"남서울","영등포","가양등촌#1 T/L","대한전선제 열경화공법 EBG 보강공사","고장 재발방지대책 보강공사 - 가스채취밸브 설치 - 스프링유니트 점검","2023-10-30 09:00","2023-11-03 18:00","2023-10-30 09:00","2023-11-03 18:00","연속"]
[43,"남서울","영등포","화곡마곡#2 T/L","세니온제 IED 성능개선","마곡변전소 170kV GIS IED 성능개선","2023-10-14 14:00","2023-10-14 18:00","2023-10-14 14:00","2023-10-14 18:00","연속"]
[44,"남서울","영등포","화곡마곡#1 T/L","세니온제 IED 성능개선","마곡변전소 170kV GIS IED 성능개선","2023-10-14 09:00","2023-10-14 14:00","2023-10-14 09:00","2023-10-14 14:00","연속"]
[45,"남서울","영등포","신광명시흥#2 T/L","'23년 가공송전 순시점검 위탁공사","정밀점검","2023-10-18 08:00","2023-10-19 18:00","2023-10-18 08:00","2023-10-19 18:00","연속"]
[46,"남서울","영등포","신광명시흥#1 T/L","'23년 가공송전 순시점검 위탁공사","정밀점검","2023-10-16 08:00","2023-10-17 18:00","2023-10-16 08:00","2023-10-17 18:00","연속"]
[47,"남서울","영등포","신광명소래 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지설치, 초기점검","2023-10-14 07:00","2023-10-14 16:00","취소","취소","연속"]
[48,"남서울","영등포","부천신정#1 T/L","영등포전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 - 신정 6100 BUS-TIE - 무부하가압용","2023-10-15 13:00","2023-10-15 18:00","취소","취소","연속"]
[49,"남서울","영등포","신정S/S CB 6100","영등포전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 - 신정 6100 BUS-TIE","2023-10-14 09:00","2023-10-15 18:00","취소","취소","연속"]
[50,"남서울","영등포","신정S/S #1 BUS","영등포전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 - 신정 6100 BUS-TIE - 무부하가압용","2023-10-14 09:00","2023-10-15 18:00","취소","취소","연속"]
[51,"남서울","영등포","신광명온수 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지설치, 피뢰기설치","2023-10-09 07:00","2023-10-13 18:00","2023-10-09 07:00","2023-10-13 18:00","연속"]
[52,"남서울","영등포","온수소래 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지설치, 초기점검","2023-10-14 16:00","2023-10-15 18:00","취소","취소","연속"]
[53,"남서울","직할","대림독산 T/L","직할 EBG 취약개소 가스채취밸브 설치공사","EBG 취약개소 열화진단용 가스채취밸브 설치 및 스프링 유니트 점검","2023-10-09 09:00","2023-10-15 18:00","2023-10-23 09:00","2023-10-29 18:00","연속"]
[54,"남서울","직할","사당신림 T/L","OF케이블 절연유 채유밸브 설치(선종교체 취소로 인한 추가분)","OF케이블 절연유 채유밸브 설치(사당-신림T/L 사당S/S 내 SJ)","2023-10-03 09:00","2023-10-04 18:00","2023-10-26 09:00","2023-10-27 18:00","연속"]
[55,"남서울","직할","신문래양평#1 T/L","직할 EBG 취약개소 가스채취밸브 설치공사","EBG 취약개소 열화진단용 가스채취밸브 설치 및 스프링 유니트 점검","2023-10-16 09:00","2023-10-22 18:00","2023-10-10 09:00","2023-10-15 18:00","연속"]
[56,"남서울","직할","신문래양평#2 T/L","직할 EBG 취약개소 가스채취밸브 설치공사","EBG 취약개소 열화진단용 가스채취밸브 설치 및 스프링 유니트 점검","2023-10-23 09:00","2023-10-29 18:00","2023-10-16 09:00","2023-10-22 18:00","연속"]
[57,"인천","김포","경서북인천#1 T/L","154kV 경서-북인천 #1T/L 케이블,접속함 점검","154kV 경서-북인천 #1T/L 하반기 케이블,접속함 점검 관련 선로 실부하 가압","2023-10-23 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-10-27 18:00","연속"]
[58,"인천","김포","경서북인천#2 T/L","154kV 경서-북인천 #2T/L 케이블,접속함 점검","154kV 경서-북인천 #2T/L 하반기 케이블,접속함 점검 관련 선로 실부하 가압","2023-10-23 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-10-27 18:00","연속"]
[59,"인천","김포","경서양촌#1 T/L","양촌S/S 154kV 경서-양촌#1T/L GIS 보통점검","양촌S/S 154kV 경서-양촌#1T/L GIS 보통점검","2023-10-27 10:00","2023-10-27 18:00","2023-10-27 10:00","2023-10-27 18:00","연속"]
[60,"인천","김포","경서양촌#2 T/L","154kV 경서-양촌T/L 한들CT 초기점검","154kV 경서-양촌T/L 한들CT 초기점검","2023-10-26 09:00","2023-10-26 18:00","2023-10-26 09:00","2023-10-26 18:00","연속"]
[61,"인천","김포","왕길양촌#1 T/L","154kV 왕길-양촌#1T/L 왕길-양촌#1,2C/T 및 피뢰기 점검","154kV 왕길-양촌#1T/L 왕길-양촌#1,2C/T 및 피뢰기 점검","2023-10-16 09:00","2023-10-17 18:00","2023-10-16 09:00","2023-10-17 18:00","연속"]
[62,"인천","김포","왕길양촌#2 T/L","154kV 왕길-양촌#2T/L 왕길-양촌#1,2C/T 및 피뢰기 점검","154kV 왕길-양촌#2T/L 왕길-양촌#1,2C/T 및 피뢰기 점검","2023-10-18 09:00","2023-10-19 18:00","2023-10-18 09:00","2023-10-19 18:00","연속"]
[63,"인천","김포","신경서왕길#2 T/L","22~23년도 김포, 부평전력지사 가공송전 협력회사 총액공사","추락방지장치 설치","2023-10-11 07:00","2023-10-13 18:00","2023-10-11 07:00","2023-10-13 18:00","연속"]
[64,"인천","김포","신경서왕길#1 T/L","22~23년도 김포, 부평전력지사 가공송전 협력회사 총액공사","추락방지장치 설치 및 상간스페이서 설치","2023-10-24 07:00","2023-10-26 18:00","2023-10-24 07:00","2023-10-26 18:00","연속"]
[65,"인천","부평","신가좌부개#2 T/L","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -#2M.Tr 1차 GIS 교체 관련 최종 무부하가압","2023-10-05 12:00","2023-10-06 18:00","2023-10-05 12:00","2023-10-06 18:00","연속"]
[66,"인천","부평","부개S/S #1 BUS","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -#1BUS 인터록시험, 상체크","2023-10-06 12:00","2023-10-06 18:00","2023-10-06 12:00","2023-10-06 18:00","연속"]
[67,"인천","부평","부흥부개#1 T/L","부개S/S 154kV 부흥-부개#1T/L GIS 보통점검","부개S/S 154kV 부흥-부개#1T/L GIS 보통점검","2023-10-07 09:00","2023-10-07 18:00","2023-10-07 09:00","2023-10-07 18:00","연속"]
[68,"인천","부평","부개S/S CB 6100","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -BUS-TIE GIS 교체","2023-10-12 08:00","2023-11-12 10:00","2023-10-12 08:00","2023-11-12 10:00","연속"]
[69,"인천","부평","부개S/S #2 BUS","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -#1M.Tr 1차 GIS 교체 -BUS-TIE GIS 교체 -PT&ES 교체","2023-10-12 08:00","2023-10-19 14:00","2023-10-12 08:00","2023-10-19 14:00","연속"]
[70,"인천","부평","부개S/S #2 BUS","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -무부하가압용","2023-10-29 10:00","2023-11-12 10:00","2023-10-29 10:00","2023-11-12 10:00","연속"]
[71,"인천","부평","신가좌부개#2 T/L","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -무부하가압용","2023-10-28 10:00","2023-10-29 10:00","2023-10-28 10:00","2023-10-29 10:00","연속"]
[72,"인천","부평","신가좌부개#2 T/L","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -무부하가압용","2023-10-18 14:00","2023-10-19 14:00","2023-10-18 14:00","2023-10-19 14:00","연속"]
[73,"인천","부평","부개S/S #1 BUS","임학, 부개S/S 154kV GIS 교체공사","부개S/S 154kV GIS 교체공사 -#1M.Tr 1차 GIS -BUS-TIE GIS -PT&ES GIS","2023-10-19 14:00","2023-10-29 10:00","2023-10-19 14:00","2023-10-29 10:00","연속"]
[74,"인천","부평","송현포스코CC#1 T/L","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","- 추락방지시설 설치 - 고광도 항공장애표시등 위치변경 및 신규설치","2023-10-16 08:00","2023-10-18 18:00","2023-10-16 08:00","2023-10-18 18:00","연속"]
[75,"인천","부평","송현포스코CC#2 T/L","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","- 추락방지시설 설치 - 고광도 항공장애표시등 위치변경 및 신규설치","2023-10-19 08:00","2023-10-21 18:00","2023-10-19 08:00","2023-10-21 18:00","연속"]
[76,"인천","부평","신가좌주안#2 T/L","22~23년도 김포, 부평전력지사 가공송전 협력회사 총액공사","추락방지장치 설치","2023-10-28 07:00","2023-10-29 18:00","2023-10-28 07:00","2023-10-29 18:00","연속"]
[77,"인천","부평","신가좌S/S SEC CB 66670","신가좌S/S 154kV #66-#67 SEC GIS 보통점검","신가좌S/S 154kV #66-#67 SEC GIS 보통점검","2023-10-10 09:00","2023-10-10 18:00","2023-10-10 09:00","2023-10-10 18:00","연속"]
[78,"인천","부평","신가좌S/S SEC CB 60610","신가좌S/S 154kV #60-#61 SEC GIS 보통점검","신가좌S/S 154kV #60-#61 SEC GIS 보통점검","2023-10-11 09:00","2023-10-11 18:00","취소","취소","연속"]
[79,"인천","부평","신가좌S/S SEC CB 65660","신가좌S/S 154kV #65-#66 SEC GIS 보통점검","신가좌S/S 154kV #65-#66 SEC GIS 보통점검","2023-10-12 09:00","2023-10-12 18:00","취소","취소","연속"]
[80,"인천","부평","신가좌신현#1 T/L","22~23년도 김포, 부평전력지사 가공송전 협력회사 총액공사","추락방지장치 설치","2023-10-21 07:00","2023-10-22 18:00","2023-10-21 07:00","2023-10-22 18:00","연속"]
[81,"인천","부평","신가좌주안#1 T/L","22~23년도 김포, 부평전력지사 가공송전 협력회사 총액공사","추락방지장치 설치","2023-10-21 07:00","2023-10-22 18:00","2023-10-21 07:00","2023-10-22 18:00","연속"]
[82,"인천","부평","신가좌신현#2 T/L","22~23년도 김포, 부평전력지사 가공송전 협력회사 총액공사","추락방지장치 설치","2023-10-28 07:00","2023-10-29 18:00","2023-10-28 07:00","2023-10-29 18:00","연속"]
[83,"인천","부평","신경서경서#3 T/L","신경서S/S 154kV 신경서-경서#3T/L GIS 보통점검","신경서S/S 154kV 신경서-경서#3T/L GIS 보통점검","2023-10-26 09:00","2023-10-26 18:00","2023-10-26 09:00","2023-10-26 18:00","연속"]
[84,"인천","부평","신현포스코CC#2 T/L","SVL 교체공사","구형 SVL을 신형 SVL로 교체(난연성 확보)","2023-10-27 09:00","2023-10-27 18:00","2023-10-27 09:00","2023-10-27 18:00","연속"]
[85,"인천","부평","신현포스코CC#1 T/L","SVL 교체공사","구형 SVL을 신형 SVL로 교체(난연성 확보)","2023-10-26 09:00","2023-10-26 18:00","2023-10-26 09:00","2023-10-26 18:00","연속"]
[86,"인천","부평","인천C/C 현대제철#2T/L CB","154kV 현대제철T/L 추락방지시설 설치공사","- 추락방지시설 설치","2023-10-19 08:00","2023-10-21 18:00","2023-10-19 08:00","2023-10-21 18:00","연속"]
[87,"인천","부평","인천C/C 현대제철#1T/L CB","154kV 현대제철T/L 추락방지시설 설치공사","- 추락방지시설 설치","2023-10-16 08:00","2023-10-18 18:00","2023-10-16 08:00","2023-10-18 18:00","연속"]
[88,"인천","부평","주안S/S CB 6100","주안S/S 154kV #60-65 BUS-TIE GIS 인터록 회로보완","주안S/S 154kV #60-65 BUS-TIE GIS 인터록 회로보완","2023-10-02 09:00","2023-10-02 18:00","2023-10-02 09:00","2023-10-02 18:00","연속"]
[89,"인천","부평","학익연수#2 T/L","학익S/S 154kV 학익연수#2 T/L GIS SA 혼용화","학익S/S 154kV 학익연수#2 T/L GIS SA 혼용화","2023-10-05 09:00","2023-10-05 18:00","2023-10-05 09:00","2023-10-05 18:00","연속"]
[90,"인천","부평","남인천학익#2 T/L","학익S/S 154kV 남인천학익#2 T/L GIS SA 혼용화","학익S/S 154kV 남인천학익#2 T/L GIS SA 혼용화","2023-10-21 09:00","2023-10-21 18:00","2023-10-21 09:00","2023-10-21 18:00","연속"]
[91,"인천","부평","학익연수#1 T/L","학익S/S 154kV 학익연수#1 T/L GIS SA 혼용화","학익S/S 154kV 학익연수#1 T/L GIS SA 혼용화","2023-10-06 09:00","2023-10-06 18:00","2023-10-06 09:00","2023-10-06 18:00","연속"]
[92,"인천","시흥","신시흥남동#2 T/L","154kV 신시흥-남동T/L 용량증대 선종교체공사","154kV 신시흥-남동(D)#1,2 T/L 5.2 C-km","2023-10-14 09:00","2023-11-24 18:00","취소","취소","연속"]
[93,"인천","시흥","남동동춘 T/L","대한제 EBG 가스채취밸브 설치공사","대한제 EBG 가스채취밸브 설치공사","2023-10-04 09:00","2023-10-09 18:00","2023-10-04 09:00","2023-10-09 18:00","연속"]
[94,"인천","시흥","도림오봉#2 T/L","EBA 절연유 채유","EBA 절연유 채유","2023-10-28 09:00","2023-10-30 18:00","2023-10-28 09:00","2023-10-30 18:00","연속"]
[95,"인천","시흥","도림오봉#1 T/L","EBA 절연유 채유","EBA 절연유 채유","2023-10-21 09:00","2023-10-23 18:00","취소","취소","연속"]
[96,"인천","시흥","신시흥북시화#1 T/L","변전소 인출 애자장치 점검용 안전장치 설치","북시화변전소 인출 애자장치 점검용 안전장치 설치","2023-10-05 07:00","2023-10-05 18:00","2023-10-05 07:00","2023-10-05 18:00","연속"]
[97,"인천","시흥","북시화서시화#1 T/L","효성제 170kV GIS 베어링 발청 관련 부품 교체","북시화,서시화S/S 154kV 북시화서시화#1T/L GIS 베어링 부품 교체","2023-10-04 09:00","2023-10-04 18:00","2023-10-04 09:00","2023-10-04 18:00","연속"]
[98,"인천","시흥","북시화서시화#2 T/L","효성제 170kV GIS 베어링 발청 관련 부품 교체","북시화,서시화S/S 154kV 북시화서시화#2T/L GIS 베어링 부품 교체","2023-10-11 09:00","2023-10-11 18:00","2023-10-11 09:00","2023-10-11 18:00","연속"]
[99,"인천","시흥","서서울#2소래 T/L","가공송전 협력회사 총액공사(154kV 서소T/L 추락방지장치 설치)","송전철탑 추락방지장치 수평 설치 - 대상 : No.48~82","2023-10-14 07:00","2023-10-20 18:00","2023-10-14 07:00","2023-10-20 18:00","매일"]
[100,"인천","시흥","서안양소래 T/L","가공송전 협력회사 총액공사(154kV 서소T/L 추락방지장치 설치)","송전철탑 추락방지장치 수평 설치 - 대상 : No.54~82, 서안양분기 1기","2023-10-07 07:00","2023-10-13 18:00","2023-10-07 07:00","2023-10-13 18:00","매일"]
[101,"인천","시흥","신광명소래 T/L","가공송전 협력회사 총액공사(154kV 서소T/L 추락방지장치 설치)","송전철탑 추락방지장치 수평 설치 - 대상 : No.76~82","2023-10-14 07:00","2023-10-15 18:00","2023-10-14 07:00","2023-10-15 18:00","매일"]
[102,"인천","시흥","온수소래 T/L","가공송전 협력회사 총액공사(154kV 서소T/L 추락방지장치 설치)","송전철탑 추락방지장치 수평 설치 - 대상 : No.76~82","2023-10-07 07:00","2023-10-09 18:00","2023-10-07 07:00","2023-10-09 18:00","매일"]
[103,"인천","시흥","신시흥시화#1 T/L","효성제 170kV GIS 베어링 발청 관련 부품 교체","신시흥S/S 154kV 신시흥시화#1T/L GIS 베어링 부품 교체","2023-10-02 14:00","2023-10-02 18:00","2023-10-02 14:00","2023-10-02 18:00","연속"]
[104,"인천","시흥","신시흥시화#2 T/L","효성제 170kV GIS 베어링 발청 관련 부품 교체","신시흥S/S 154kV 신시흥시화#2T/L GIS 베어링 부품 교체","2023-10-06 09:00","2023-10-06 18:00","2023-10-06 09:00","2023-10-06 18:00","연속"]
[105,"인천","시흥","신시흥북시화#2 T/L","효성제 170kV GIS 베어링 발청 관련 부품 교체","신시흥S/S 154kV 신시흥북시화#2T/L GIS 베어링 부품 교체","2023-10-10 09:00","2023-10-10 14:00","2023-10-10 09:00","2023-10-10 14:00","연속"]
[106,"인천","시흥","신시흥S/S SEC CB 67680","효성제 170kV GIS 베어링 발청 관련 부품 교체","신시흥S/S 154kV 67-68 Sec. GIS 베어링 부품 교체","2023-10-10 14:00","2023-10-10 18:00","2023-10-10 14:00","2023-10-10 18:00","연속"]
[107,"인천","시흥","신시흥S/S SEC CB 62630","효성제 170kV GIS 베어링 발청 관련 부품 교체","신시흥S/S 154kV 62-63 Sec. GIS 베어링 부품 교체","2023-10-05 14:00","2023-10-05 18:00","2023-10-05 14:00","2023-10-05 18:00","연속"]
[108,"인천","시흥","오봉남동#2 T/L","대한제 EBG 가스채취밸브 설치공사","대한제 EBG 가스채취밸브 설치공사","2023-10-13 09:00","2023-10-15 18:00","취소","취소","연속"]
[109,"인천","시흥","오봉남동#1 T/L","대한제 EBG 가스채취밸브 설치공사","대한제 EBG 가스채취밸브 설치공사","2023-10-10 09:00","2023-10-12 18:00","취소","취소","연속"]
[110,"인천","직할","갈산부흥#1 T/L","154kV 신부평-고강T/L 등 4개T/L 구형 SVL 교체공사","154kV 신부평-고강T/L 등 4개T/L 구형 SVL(피뢰기) 및 접지설비 교체공사","2023-10-02 09:00","2023-10-06 18:00","2023-10-10 09:00","2023-10-12 18:00","연속"]
[111,"인천","직할","갈산부흥#2 T/L","154kV 신부평-고강T/L 등 4개T/L 구형 SVL 교체공사","154kV 신부평-고강T/L 등 4개T/L 구형 SVL(피뢰기) 및 접지설비 교체공사","2023-10-20 18:00","2023-10-22 18:00","2023-10-20 18:00","2023-10-22 18:00","연속"]
[112,"인천","직할","계양김포#2 T/L","계양S/S 154kV 계양-김포#2T/L GIS SA 혼용공사","계양S/S 154kV 계양-김포#2T/L GIS SA 혼용공사","2023-10-28 09:30","2023-10-28 18:00","취소","취소","연속"]
[113,"인천","직할","계양김포#1 T/L","154kV 불로분기 지중T/L 건설공사","○ 사업목적 : 인천검단신도시 내 신설 불로S/S 신규부하 공급 및 계양S/S, 김포S/S 부하분담 ○ 구 간 : 신설 154kV 불로S/S - 기설 154kV 계양-김포T/L 분기점(M/H#7~#8) ○ 선종,회선길이 : 154kV XLPE 2000㎟ 4C(D) - 0.3km","2023-10-12 09:00","2023-11-19 18:00","2023-10-12 09:00","2023-11-19 18:00","연속"]
[114,"인천","직할","임학계양#1 T/L","154kV 신부평-청천 등 2개T/L 대한제 EBG 보강공사","가스채취밸브 설치 및 스프링 유니트 점검","2023-10-17 09:00","2023-10-17 18:00","취소","취소","연속"]
[115,"인천","직할","임학계양#2 T/L","154kV 신부평-청천 등 2개T/L 대한제 EBG 보강공사","가스채취밸브 설치 및 스프링 유니트 점검","2023-10-18 09:00","2023-10-18 18:00","취소","취소","연속"]
[116,"인천","직할","신부평고강#2 T/L","22~23년도 김포, 부평전력지사 가공송전 협력회사 총액공사","추락방지장치 설치","2023-10-14 07:00","2023-10-15 18:00","2023-10-14 07:00","2023-10-15 18:00","연속"]
[117,"인천","직할","갈산부흥#3 T/L","부흥S/S 갈산-부흥#3T/L GIS 하자점검","부흥S/S 갈산-부흥#3T/L GIS 하자점검","2023-10-13 10:00","2023-10-13 18:00","2023-10-13 10:00","2023-10-13 18:00","연속"]
[118,"인천","직할","북인천원창 T/L","북인천S/S 북인천원창T/L 조작시험","북인천S/S 북인천원창T/L 조작시험","2023-10-14 14:00","2023-10-14 18:00","취소","취소","연속"]
[119,"인천","직할","계양북인천 T/L","북인천S/S 계양북인천T/L 조작시험","북인천S/S 계양북인천T/L 조작시험","2023-10-14 10:00","2023-10-14 14:00","취소","취소","연속"]
[120,"인천","직할","신부평고강#1 T/L","신부평-고강 #1T/L EBA 비표준형 자기애관 교체공사","비표준형 자기애관을 폴리머애관으로 교체","2023-10-07 09:00","2023-10-09 18:00","2023-10-07 09:00","2023-10-09 18:00","연속"]
[121,"경기북부","고양","능곡S/S 능곡전철#1T/L CB","22~23년 고양P/O 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2023-10-25 10:00","2023-10-25 14:00","취소","취소","연속"]
[122,"경기북부","고양","능곡S/S 능곡전철#2T/L CB","22~23년 고양P/O 변전협력회사 총액공사","170kV GIS 차단기 조작시험","2023-10-26 10:00","2023-10-26 14:00","취소","취소","연속"]
[123,"경기북부","고양","신포천백학#1 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2023-10-10 09:00","2023-10-10 18:00","2023-10-10 09:00","2023-10-10 18:00","연속"]
[124,"경기북부","고양","신포천백학#2 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2023-10-11 09:00","2023-10-11 18:00","2023-10-11 09:00","2023-10-11 18:00","연속"]
[125,"경기북부","고양","백학남면#1 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2023-10-12 09:00","2023-10-12 18:00","2023-10-12 09:00","2023-10-12 18:00","연속"]
[126,"경기북부","고양","백학남면#2 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2023-10-16 09:00","2023-10-16 18:00","2023-10-16 09:00","2023-10-16 18:00","연속"]
[127,"경기북부","고양","신파주송포#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2023-10-05 09:00","2023-10-05 18:00","2023-10-05 09:00","2023-10-05 18:00","연속"]
[128,"경기북부","고양","신파주원흥#1 T/L","2023년 가공송전 순시점검 위탁공사","초기점검","2023-10-11 07:30","2023-10-11 12:00","취소","취소","연속"]
[129,"경기북부","고양","신파주원흥#2 T/L","2023년 가공송전 순시점검 위탁공사","초기점검","2023-10-11 13:00","2023-10-11 17:00","취소","취소","연속"]
[130,"경기북부","고양","원흥S/S #2 BUS","원흥S/S 154kV GTX-A노선 SW증설공사","- 154kV T/L GIS(50kA, 1250A) × 2CCT 설치 - 154kV 고객선로 보호IED반 × 2면 설치 - 기타 부대공사 1식. 끝.","2023-10-23 09:00","2023-11-08 18:00","2023-10-23 09:00","2023-11-08 18:00","연속"]
[131,"경기북부","고양","원흥S/S #1 BUS","원흥S/S 154kV GTX-A노선 SW증설공사","- 154kV T/L GIS(50kA, 1250A) × 2CCT 설치 - 154kV 고객선로 보호IED반 × 2면 설치 - 기타 부대공사 1식. 끝.","2023-10-16 08:00","2023-10-20 18:00","2023-10-16 08:00","2023-10-20 18:00","연속"]
[132,"경기북부","고양","신파주원흥#2 T/L","원흥S/S 154kV GTX-A노선 SW증설공사","- 154kV T/L GIS(50kA, 1250A) × 2CCT 설치 - 154kV 고객선로 보호IED반 × 2면 설치 - 기타 부대공사 1식. 끝.","2023-10-19 09:00","2023-10-20 18:00","2023-10-19 09:00","2023-10-20 18:00","연속"]
[133,"경기북부","고양","덕이호수#1 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2023-10-17 09:00","2023-10-17 18:00","2023-10-17 09:00","2023-10-17 18:00","연속"]
[134,"경기북부","고양","덕이호수#2 T/L","22-23년 변전협력회사 총액공사","170kV GIS 보통점검","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[135,"경기북부","구리","덕소마석#1 T/L","22~23년 구리 가공송전협력 총액공사_추락방지장치","추락방지장치 설치(No.4~46 / 40기)","2023-10-30 08:00","2023-11-03 18:00","2023-10-30 08:00","2023-11-03 18:00","연속"]
[136,"경기북부","구리","신장덕소#2 T/L","22~23년 구리 가공송전협력 총액공사_추락방지, 피뢰기","추락방지장치 설치 (No.3~19,25,26), 피뢰기 (No.1~26)","2023-10-19 08:00","2023-10-24 18:00","2023-10-19 08:00","2023-10-24 18:00","연속"]
[137,"경기북부","구리","덕소진건#1 T/L","154kV 덕소-진건T/L 덕진#3C/T EBA 절연유 분석(추적관리)","EBA 절연유 분석(#1T/L B상, #2T/L A,C상)","2023-10-12 09:00","2023-10-12 14:00","2023-10-12 09:00","2023-10-12 18:00","연속"]
[138,"경기북부","구리","덕소진건#2 T/L","154kV 덕소-진건T/L 덕진#3C/T EBA 절연유 분석(추적관리)","EBA 절연유 분석(#1T/L B상, #2T/L A,C상)","2023-10-12 14:00","2023-10-12 18:00","취소","취소","연속"]
[139,"경기북부","구리","미금화양 T/L","22~23년 구리 가공송전협력 총액공사_추락방지","추락방지장치 설치","2023-10-04 08:00","2023-10-06 18:00","2023-10-04 08:00","2023-10-06 18:00","연속"]
[140,"경기북부","구리","미금S/S #66 BUS","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-30 16:00","2023-10-31 16:00","2023-10-30 16:00","2023-10-31 16:00","연속"]
[141,"경기북부","구리","미금화양 T/L","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-30 16:00","2023-10-31 16:00","2023-10-30 16:00","2023-10-31 16:00","연속"]
[142,"경기북부","구리","미금S/S SEC CB 66670","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-30 16:00","2023-10-31 16:00","2023-10-30 16:00","2023-10-31 16:00","연속"]
[143,"경기북부","구리","미금S/S #67 BUS","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-30 09:00","2023-10-31 18:00","2023-10-30 09:00","2023-10-31 18:00","연속"]
[144,"경기북부","구리","미금S/S SEC CB 61620","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-26 16:00","2023-10-27 16:00","2023-10-26 16:00","2023-10-27 16:00","연속"]
[145,"경기북부","구리","미금S/S #61 BUS","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-26 16:00","2023-10-27 16:00","2023-10-26 16:00","2023-10-27 16:00","연속"]
[146,"경기북부","구리","미금화양 T/L","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-26 16:00","2023-10-27 16:00","2023-10-26 16:00","2023-10-27 16:00","연속"]
[147,"경기북부","구리","미금S/S #62 BUS","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-17 10:00","2023-10-27 18:00","2023-10-17 10:00","2023-10-27 18:00","연속"]
[148,"경기북부","구리","미금S/S SEC CB 66670","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-16 10:00","2023-10-17 10:00","2023-10-16 10:00","2023-10-17 10:00","연속"]
[149,"경기북부","구리","미금화양 T/L","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS(Main) 설치 ⅹ 1CCT","2023-10-16 10:00","2023-10-17 10:00","2023-10-16 10:00","2023-10-17 10:00","연속"]
[150,"경기북부","구리","미금S/S #66 BUS","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-16 10:00","2023-10-17 10:00","2023-10-16 10:00","2023-10-17 10:00","연속"]
[151,"경기북부","구리","미금S/S #67 BUS","345kV 미금S/S #4M.Tr용 개폐장치 설치공사(전문)","○ 154kV GIS 설치 ⅹ 1CCT","2023-10-11 09:00","2023-10-17 10:00","2023-10-11 09:00","2023-10-17 10:00","연속"]
[152,"경기북부","구리","별내진접 T/L","22~23년 구리 가공송전협력 총액공사_추락방지","추락방지장치 설치_수평형","2023-10-02 08:00","2023-10-02 18:00","2023-10-02 08:00","2023-10-02 18:00","연속"]
[153,"경기북부","구리","서종청평PP#2 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","추락방지시설 설치 : 서종S/S ~ 청평PP","2023-10-26 07:00","2023-10-31 18:00","취소","취소","연속"]
[154,"경기북부","구리","서종청평PP#1 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","추락방지시설 설치 : 서종S/S ~ 청평PP","2023-10-16 07:00","2023-10-25 18:00","취소","취소","연속"]
[155,"경기북부","구리","동서울서종#1 T/L","22~23년 구리 가공송전협력 총액공사_추락방지","추락방지장치 설치(수직9기, 수평 52기)","2023-10-16 08:00","2023-10-20 18:00","2023-10-16 08:00","2023-10-20 18:00","연속"]
[156,"경기북부","구리","신포천전곡#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","신포천-전곡#1T/L No.6~46 수평추락방지장치 설치","2023-10-04 08:00","2023-10-10 18:00","2023-10-04 08:00","2023-10-10 18:00","연속"]
[157,"경기북부","구리","내촌용정#2 T/L","23-24년 지중송전설비 위탁정비공사 (피뢰기 및 C/T 점검)","피뢰기 Doble Test 및 C/T 점검","2023-10-17 14:00","2023-10-17 18:00","2023-10-17 14:00","2023-10-17 18:00","연속"]
[158,"경기북부","구리","용정포천#2 T/L","23-24년 지중송전설비 위탁정비공사 (피뢰기 및 C/T 점검)","피뢰기 Doble Test 및 C/T 점검","2023-10-16 14:00","2023-10-16 18:00","2023-10-16 14:00","2023-10-16 18:00","연속"]
[159,"경기북부","구리","용정포천#1 T/L","23-24년 지중송전설비 위탁정비공사(피뢰기 및 C/T점검)","피뢰기 Doble Test 및 C/T 점검","2023-10-16 09:00","2023-10-16 14:00","2023-10-16 09:00","2023-10-16 14:00","연속"]
[160,"경기북부","구리","내촌용정#1 T/L","23-24년 지중송전설비 위탁정비공사 (피뢰기 및 C/T 점검)","피뢰기 Doble Test 및 C/T 점검","2023-10-17 09:00","2023-10-17 14:00","2023-10-17 09:00","2023-10-17 14:00","연속"]
[161,"경기북부","구리","운천철원#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","운천-철원#1T/L No.11,13,18,57,67 지지애자교체","2023-10-23 08:00","2023-10-25 18:00","2023-10-23 08:00","2023-10-25 18:00","연속"]
[162,"경기북부","구리","운천전곡#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-10-06 09:00","2023-10-06 18:00","2023-10-06 09:00","2023-10-06 18:00","연속"]
[163,"경기북부","구리","운천철원#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","운천-철원#2T/L No.9,12,24 지지애자교체 및 No.31~35 항공구 설치","2023-10-26 08:00","2023-10-30 18:00","2023-10-26 08:00","2023-10-30 18:00","연속"]
[164,"경기북부","구리","장암진접#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사 - 170 GIS 보통점검","2023-10-07 09:00","2023-10-07 18:00","2023-10-07 09:00","2023-10-07 18:00","연속"]
[165,"경기북부","구리","청평HP의암HP T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","추락방지시설 설치공사 : 청평HP~No.32","2023-10-10 07:00","2023-10-13 18:00","취소","취소","매일"]
[166,"경기북부","구리","청평H/P #1 M.Tr 2차 CB","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-10-12 09:00","2023-10-12 18:00","2023-10-12 09:00","2023-10-12 18:00","연속"]
[167,"경기북부","구리","청평H/P #3 M.Tr 2차 CB","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-10-13 09:00","2023-10-13 18:00","2023-10-13 09:00","2023-10-13 18:00","연속"]
[168,"경기북부","구리","마석청평HP#2 T/L","22~23년 구리 가공송전협력 총액공사_추락방지장치","추락방지장치 설치 (No.1~35), SB댐퍼 설치(No.24)","2023-10-25 08:00","2023-10-30 18:00","2023-10-25 08:00","2023-10-30 18:00","연속"]
[169,"경기북부","구리","청평P/P #2 M.Tr 2차 CB","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-10-20 09:00","2023-10-20 18:00","2023-10-20 09:00","2023-10-20 18:00","연속"]
[170,"경기북부","구리","포천운천#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","포천-운천#1T/L No.49,51,53~64 수평추락방지 설치 및 지지애자교체","2023-10-18 08:00","2023-10-20 18:00","2023-10-18 08:00","2023-10-20 18:00","연속"]
[171,"경기북부","직할","금오상계#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","금오-상계#2T/L No.17,30 수평추락방지장치 설치","2023-10-31 08:00","2023-11-01 18:00","2023-10-31 08:00","2023-11-01 18:00","연속"]
[172,"경기북부","직할","신포천동두천#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 신포천-동두천T/L No.24,28,31~35","2023-10-13 07:00","2023-10-13 18:00","2023-10-13 07:00","2023-10-13 18:00","연속"]
[173,"경기북부","직할","백석덕계#1 T/L","23년도 경기북부 직할 170kV GIS 초기점검 및 정밀점검 공사","170kV GIS 정밀점검","2023-10-16 09:00","2023-10-20 18:00","2023-10-16 09:00","2023-10-20 18:00","연속"]
[174,"경기북부","직할","녹양백석#1 T/L","23년도 경기북부 직할 170kV GIS 초기점검 및 정밀점검 공사","170kV GIS 정밀점검","2023-10-23 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-10-27 18:00","연속"]
[175,"경기북부","직할","신의정부송우#1 T/L","2023년 가공송전 순시점검 위탁공사","초기점검 - 154kV 신의정부-송우#1 T/L No.37, 48호","2023-10-05 09:00","2023-10-05 18:00","2023-10-05 09:00","2023-10-05 18:00","연속"]
[176,"경기북부","직할","신의정부송우#2 T/L","2023년 가공송전 순시점검 위탁공사","초기점검 - 154kV 신의정부-송우#2 T/L No.37, 48호","2023-10-06 09:00","2023-10-06 18:00","2023-10-06 09:00","2023-10-06 18:00","연속"]
[177,"경기북부","직할","양주고양#1 T/L","2023년 가공송전 순시점검 위탁공사","휴전작업 병행선로","2023-10-23 07:30","2023-10-27 18:00","2023-10-04 07:30","2023-10-13 18:00","연속"]
[178,"경기북부","직할","양주금촌#1 T/L","2023년 가공송전 순시점검 위탁공사","송전설비 정밀점검","2023-10-23 07:30","2023-10-31 18:00","2023-10-04 07:30","2023-10-13 18:00","연속"]
[179,"경기북부","직할","양주녹양#2 T/L","2022~2023년 고양전력지사 가공송전 협력회사 총액공사","철탑추락방지시설 설치","2023-10-30 07:00","2023-11-07 18:00","2023-10-23 07:00","2023-10-31 18:00","연속"]
[180,"경기북부","직할","옥정송우#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 옥정-송우T/L No.2~8,12","2023-10-11 07:00","2023-10-11 18:00","2023-10-11 07:00","2023-10-11 18:00","연속"]
[181,"경기북부","직할","옥정동두천#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 옥정-동두천T/L No.2~11,17~24,28,31~36","2023-10-11 07:00","2023-10-13 18:00","2023-10-11 07:00","2023-10-13 18:00","연속"]
[182,"경기북부","직할","용현장암#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","용현-장암T/L No.17,30,31~35 수평추락방지시설설치","2023-10-31 08:00","2023-11-01 18:00","2023-10-31 08:00","2023-11-01 18:00","연속"]
[183,"경기북부","직할","장암방학#2 T/L","’23년도 경기북부 직할 170kV GIS 초기 및 정밀점검 공사","170kV GIS 초기점검","2023-10-06 09:00","2023-10-06 18:00","2023-10-06 09:00","2023-10-06 18:00","연속"]
[184,"경기북부","직할","장암방학#1 T/L","’23년도 경기북부 직할 170kV GIS 초기 및 정밀점검 공사","170kV GIS 초기점검","2023-10-05 09:00","2023-10-05 18:00","2023-10-05 09:00","2023-10-05 18:00","연속"]
[185,"경기북부","직할","운천전곡#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","154kV 운천-전곡#2T/L No.1,13~70 수평추락방지시설 설치","2023-10-10 08:00","2023-10-19 18:00","2023-10-10 08:00","2023-10-19 18:00","연속"]
[186,"경기","군포","화성마도 T/L","장덕S/S 170kV GIS 증설공사","장덕S/S 170kV GIS 증설공사","2023-10-15 13:00","2023-10-31 18:00","취소","취소","연속"]
[187,"경기","군포","목내안산복합#2 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-10-06 13:00","2023-10-06 18:00","2023-10-06 13:00","2023-10-06 18:00","연속"]
[188,"경기","군포","목내안산복합#1 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-10-06 09:00","2023-10-06 13:00","2023-10-06 09:00","2023-10-06 13:00","연속"]
[189,"경기","군포","서서울산본#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 14기","2023-10-24 12:00","2023-10-25 18:00","2023-10-24 12:00","2023-10-25 18:00","연속"]
[190,"경기","군포","서서울산본#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 14기","2023-10-23 07:00","2023-10-24 12:00","2023-10-23 07:00","2023-10-24 12:00","연속"]
[191,"경기","군포","서서울#2서안양 T/L","가공송전 협력회사 총액공사(추락방지장치 설치)","송전철탑 추락방지장치 설치 - 대상 : No.48~53(6기), 서안양분기 1기","2023-10-04 07:00","2023-10-06 18:00","2023-10-04 07:00","2023-10-06 18:00","매일"]
[192,"경기","군포","신시흥시화#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 8기","2023-10-18 07:00","2023-10-20 18:00","2023-10-18 07:00","2023-10-20 18:00","연속"]
[193,"경기","군포","신시흥시화#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 13기","2023-10-30 07:00","2023-11-01 18:00","2023-10-30 07:00","2023-11-01 18:00","연속"]
[194,"경기","군포","반월시화#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 13기","2023-10-30 07:00","2023-11-01 18:00","2023-10-30 07:00","2023-11-01 18:00","연속"]
[195,"경기","군포","반월시화#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 13기","2023-10-18 07:00","2023-10-20 18:00","2023-10-18 07:00","2023-10-20 18:00","연속"]
[196,"경기","군포","안산안산복합#1 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-10-24 09:00","2023-10-24 13:00","2023-10-24 09:00","2023-10-24 13:00","연속"]
[197,"경기","군포","안산안산복합#3 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-10-26 09:00","2023-10-26 13:00","2023-10-26 09:00","2023-10-26 13:00","연속"]
[198,"경기","군포","안산안산복합#2 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-10-25 09:00","2023-10-25 13:00","2023-10-25 09:00","2023-10-25 13:00","연속"]
[199,"경기","군포","서서울#2일동#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 24기","2023-10-02 07:00","2023-10-05 18:00","2023-10-02 07:00","2023-10-05 18:00","연속"]
[200,"경기","군포","서서울#2일동#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 24기","2023-10-10 07:00","2023-10-13 18:00","2023-10-10 07:00","2023-10-15 18:00","연속"]
[201,"경기","군포","장덕마도 T/L","장덕S/S 170kV GIS 증설공사","장덕S/S 170kV GIS 증설공사","2023-10-09 18:00","2023-10-15 18:00","취소","취소","연속"]
[202,"경기","동부","곤지암S/S SEC CB 65660","23년 동부 변전협력총액공사","곤지암:65-66(보통)","2023-10-13 09:30","2023-10-13 18:00","2023-10-13 09:30","2023-10-13 18:00","연속"]
[203,"경기","동부","곤지암율현#1 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사, 1~53호 (곤지암-이천 4회선 병가구간)","2023-10-30 08:00","2023-11-10 18:00","취소","취소","연속"]
[204,"경기","동부","곤지암이천#1 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사, 1~53호","2023-10-30 08:00","2023-11-10 18:00","취소","취소","연속"]
[205,"경기","동부","곤지암S/S SEC CB 60610","23년 동부 변전협력총액공사","곤지암:60-61(보통)","2023-10-12 09:30","2023-10-12 18:00","2023-10-05 09:30","2023-10-05 18:00","연속"]
[206,"경기","동부","신용인동백#2 T/L","2023~2024년 지중송전설비 위탁정비공사(경기본부 성남전력지사)","154kV신용인동백#2T/L C/T 및 LA점검","2023-10-25 08:00","2023-10-27 17:00","2023-10-25 08:00","2023-10-27 17:00","연속"]
[207,"경기","동부","모현용인#2 T/L","추락방지시설 설치공사","추락방지시설 설치(수평)1~51호(35기)","2023-10-02 07:00","2023-10-04 18:00","2023-10-02 07:00","2023-10-04 18:00","연속"]
[208,"경기","동부","성현분당#1 T/L","성현S/S 장기사용 154kV GIS 교체공사(4차)","성현S/S 장기사용 154kV GIS 교체공사(4차) 성현분당#1, #3M.Tr 1차 대체","2023-10-12 09:00","2023-11-03 18:00","2023-10-05 09:00","2023-10-27 18:00","연속"]
[209,"경기","동부","왕암여주#2 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치 및 지지애자 교체공사, 158~203호","2023-10-17 08:00","2023-10-27 18:00","2023-10-17 08:00","2023-10-27 18:00","연속"]
[210,"경기","동부","여주문막#2 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치 및 지지애자 교체공사, 3~9호(왕암-여주 4회선 병가구간)","2023-10-12 08:00","2023-10-16 18:00","2023-10-12 08:00","2023-10-16 18:00","연속"]
[211,"경기","동부","왕암여주#1 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치 및 지지애자 교체공사, 158~203호","2023-10-02 08:00","2023-10-16 18:00","2023-10-02 08:00","2023-10-16 18:00","연속"]
[212,"경기","동부","여주문막#1 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치 및 지지애자 교체공사, 3~9호(왕암-여주 4회선 병가구간)","2023-10-25 08:00","2023-10-27 18:00","2023-10-25 08:00","2023-10-27 18:00","연속"]
[213,"경기","동부","이천율현#2 T/L","23년 동부 변전협력총액공사","이천:이천-율현#2T/L(보통) 순간압력상승계 설치 율현:이천-율현#2T/L(보통) 순간압력상승계 설치","2023-10-27 09:30","2023-10-27 18:00","2023-10-27 09:30","2023-10-27 18:00","연속"]
[214,"경기","동부","이천율현#1 T/L","23년 동부 변전협력총액공사","이천:이천-율현#1T/L(보통) 율현:이천-율현#1T/L(보통) 순간압력상승계 설치","2023-10-06 09:30","2023-10-06 18:00","2023-10-06 09:30","2023-10-06 18:00","연속"]
[215,"경기","동부","이천가남#2 T/L","23년 동부 변전협력총액공사","이천:이천-가남#2T/L(보통) 가남:순간압력상승계 설치","2023-10-23 09:30","2023-10-25 18:00","취소","취소","연속"]
[216,"경기","동부","이천S/S SEC CB 65660","23년 동부 변전협력총액공사","이천:65-66(보통) 65-66#2DS 순간압력계 교체","2023-10-07 09:30","2023-10-07 18:00","2023-10-07 09:30","2023-10-07 18:00","연속"]
[217,"경기","성남","덕성남사#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(6회선 구간)","2023-10-28 08:00","2023-10-28 18:00","2023-10-28 08:00","2023-10-28 18:00","매일"]
[218,"경기","성남","서안성남사#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(6회선 구간)","2023-10-28 08:00","2023-10-28 18:00","2023-10-28 08:00","2023-10-28 18:00","매일"]
[219,"경기","성남","진위동탄#2 T/L","세니온제 계전기 성능개선","- 제작사 입회하 계전기 성능개선","2023-10-26 14:00","2023-10-26 18:00","2023-10-26 14:00","2023-10-26 18:00","연속"]
[220,"경기","성남","진위동탄#1 T/L","세니온제 계전기 성능개선","- 제작사 입회하 계전기 성능개선","2023-10-26 09:00","2023-10-26 14:00","2023-10-26 09:00","2023-10-26 14:00","연속"]
[221,"경기","성남","신봉이의#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","154kV 신봉-이의T/L 수직수평추락방지장치 설치","2023-10-25 07:00","2023-10-27 18:00","2023-10-25 07:00","2023-10-27 18:00","연속"]
[222,"경기","성남","신봉이의#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","154kV 신봉-이의T/L 수직수평추락방지장치 설치","2023-10-30 07:00","2023-10-31 18:00","2023-10-30 07:00","2023-10-31 18:00","연속"]
[223,"경기","성남","신용인기흥#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간) 실제작업 : 10/7 및 10/12","2023-10-05 08:00","2023-10-05 18:00","2023-10-05 08:00","2023-10-05 18:00","매일"]
[224,"경기","성남","신용인기흥#1 T/L","23년 성남전력지사 변전협력회사 총액공사","- GIS 조작시험","2023-10-12 14:00","2023-10-12 18:00","2023-10-12 14:00","2023-10-12 18:00","연속"]
[225,"경기","성남","신용인용인#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간)","2023-10-24 08:00","2023-10-24 18:00","2023-10-24 08:00","2023-10-24 18:00","매일"]
[226,"경기","성남","정자동판교#1 T/L","23년 성남전력지사 변전협력회사 총액공사","- T/L 보호반교체 - GIS 보통점검","2023-10-11 09:00","2023-10-13 18:00","2023-10-11 09:00","2023-10-13 18:00","연속"]
[227,"경기","성남","정자동판교#2 T/L","23년 성남전력지사 변전협력회사 총액공사","- T/L 보호반교체 - GIS 보통점검","2023-10-04 09:00","2023-10-06 18:00","2023-10-04 09:00","2023-10-06 18:00","연속"]
[228,"경기","직할","관양평촌#1 T/L","154kV 관양S/S #4M.Tr 증설공사(무부하용)","154kV 관양S/S #4M.Tr 증설공사(무부하용)","2023-10-05 09:00","2023-10-07 18:00","2023-10-05 09:00","2023-10-07 18:00","연속"]
[229,"경기","직할","발안구문천#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","관형지지물용 가이드레일 설치공사(수평)","2023-10-01 08:00","2023-10-01 18:00","2023-10-01 08:00","2023-10-02 18:00","매일"]
[230,"경기","직할","남수원발안#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(수평) 및 애자교체 공사 [4회선 병가 구간]","2023-10-15 08:00","2023-10-15 18:00","취소","취소","매일"]
[231,"경기","직할","발안향남#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(수평) 및 애자교체 공사 [4회선 병가 구간]","2023-10-15 08:00","2023-10-15 18:00","취소","취소","매일"]
[232,"경기","직할","남수원발안#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(수평) 및 애자교체 공사 [4회선 병가 구간]","2023-10-14 08:00","2023-10-14 18:00","취소","취소","매일"]
[233,"경기","직할","발안향남#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(수평) 및 애자교체 공사 [4회선 병가 구간]","2023-10-14 08:00","2023-10-14 18:00","취소","취소","매일"]
[234,"경기","직할","발안구문천#1 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","발안,구문천S/S 발안-구문천#1T/L 보호반대체","2023-10-07 09:00","2023-10-09 18:00","2023-10-07 09:00","2023-10-09 18:00","연속"]
[235,"경기","직할","발안구문천#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","관형지지물용 가이드레일 설치공사(수평)","2023-10-09 08:00","2023-10-09 18:00","취소","취소","매일"]
[236,"경기","직할","서서울#2봉담#2 T/L","세니온제 IED 성능개선(유사고장)","봉담S/S 서서울2-봉담#2T/L 세니온제 IED 성능개선(유사고장)","2023-10-22 14:00","2023-10-22 18:00","취소","취소","연속"]
[237,"경기","직할","서서울#2봉담#1 T/L","세니온제 IED 성능개선(유사고장)","봉담S/S 서서울2-봉담#1T/L 세니온제 IED 성능개선(유사고장)","2023-10-22 09:00","2023-10-22 14:00","취소","취소","연속"]
[238,"경기","직할","봉담남수원#2 T/L","세니온제 IED 성능개선(유사고장)","봉담,남수원S/S 봉담-남수원#2T/L 세니온제 IED성능개선(유사고장)","2023-10-21 14:00","2023-10-21 18:00","취소","취소","연속"]
[239,"경기","직할","봉담남수원#1 T/L","세니온제 IED 성능개선(유사고장)","봉담,남수원S/S 봉담-남수원#1T/L 세니온제 IED성능개선(유사고장)","2023-10-21 09:00","2023-10-21 14:00","취소","취소","연속"]
[240,"경기","직할","서수원율전#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","154kV 서수원-율전#2 4호, 17호 수평추락방지장치 설치","2023-10-13 07:00","2023-10-13 18:00","2023-10-13 07:00","2023-10-13 18:00","연속"]
[241,"경기","직할","수촌조암#1 T/L","2023년 가공송전순시점검 위탁공사","수촌조암#1T/L 초기점검","2023-10-26 09:00","2023-10-26 12:00","2023-10-26 09:00","2023-10-26 12:00","연속"]
[242,"경기","직할","수촌조암#2 T/L","2023년 가공송전순시점검 위탁공사","수촌조암#2T/L 초기점검","2023-10-26 13:00","2023-10-26 17:00","2023-10-26 13:00","2023-10-26 17:00","연속"]
[243,"경기","직할","서서울율전#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 15기","2023-10-26 07:00","2023-10-27 12:00","2023-10-26 07:00","2023-10-27 12:00","연속"]
[244,"경기","직할","율전의왕#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 8기","2023-10-17 07:00","2023-10-17 18:00","2023-10-17 07:00","2023-10-17 18:00","연속"]
[245,"경기","직할","율전의왕#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 8기","2023-10-16 07:00","2023-10-16 18:00","2023-10-16 07:00","2023-10-16 18:00","연속"]
[246,"경기","직할","서서울율전#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 15기","2023-10-27 12:00","2023-10-28 18:00","2023-10-27 12:00","2023-10-28 18:00","연속"]
[247,"경기","직할","오산향남#2 T/L","세니온제 IED 성능개선(유사고장)","향남S/S 오산-향남#2T/L 세니온제 IED 성능개선(유사고장)","2023-10-07 14:00","2023-10-07 18:00","취소","취소","연속"]
[248,"경기","직할","오산향남#1 T/L","세니온제 IED 성능개선(유사고장)","향남S/S 오산-향남#1T/L 세니온제 IED 성능개선(유사고장)","2023-10-07 09:00","2023-10-07 14:00","취소","취소","연속"]
[249,"경기","직할","화성S/S #61 BUS","화성S/S 154kV 신규수용공사(화성전철)","화성전철#1T/L GIS 증설","2023-10-09 13:00","2023-10-09 18:00","2023-10-09 13:00","2023-10-09 18:00","연속"]
[250,"경기","직할","화성수촌#2 T/L","화성S/S 154kV 신규수용공사(화성전철)","화성전철#1T/L GIS 증설 - 61,66BUS 무부하가압","2023-10-08 09:00","2023-10-09 18:00","2023-10-08 09:00","2023-10-09 18:00","연속"]
[251,"경기","직할","화성수촌#2 T/L","화성S/S 154kV 신규수용공사(화성전철)","화성전철#1T/L GIS 증설 - 61,66BUS 무부하가압","2023-10-23 09:00","2023-10-24 18:00","2023-10-23 09:00","2023-10-24 18:00","연속"]
[252,"경기","직할","화성남양#1 T/L","화성S/S 154kV 신규수용공사(화성전철)","화성전철#2T/L GIS 증설 - 61,66BUS 무부하가압","2023-10-24 09:00","2023-10-25 18:00","2023-10-24 09:00","2023-10-25 18:00","연속"]
[253,"경기","평택","서운안성#1 T/L","세종-포천간 도로개설 관련 지장이설공사(154kV 1T/L)","철탑 5기 신설, 8기 철거","2023-10-16 07:00","2023-11-04 18:00","2023-10-18 07:00","2023-11-14 18:00","연속"]
[254,"경기","평택","서운안성#2 T/L","세종-포천간 도로개설 관련 지장이설공사(154kV 2T/L)","철탑 5기 신설, 8기 철거","2023-10-02 07:00","2023-10-14 18:00","2023-10-04 07:00","2023-10-17 18:00","연속"]
[255,"경기","평택","서안성안성#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(수평) 및 애자교체 공사 [4회선 병가 구간]","2023-10-29 08:00","2023-10-29 18:00","취소","취소","매일"]
[256,"경기","평택","송탄안성 T/L","2022-23 평택전력 가공송전 협력회사 총액공사","폴리머점퍼지지애자 설치 작업대상 : 2회선 No.25, 4회선(모 송탄-오성CC/자 송탄안성) No.4(No.25) 추락방지장치 설치 작업대상 : 2회선 No.16~18 총 3기 소도체 이도조정 작업대상 : 2회선 No.54~55","2023-10-14 07:00","2023-10-15 18:00","2023-10-14 07:00","2023-10-15 18:00","연속"]
[257,"경기","평택","서안성안성#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(수평) 및 애자교체 공사 [4회선 병가 구간]","2023-10-03 08:00","2023-10-03 18:00","취소","취소","매일"]
[258,"경기","평택","오산평택#1 T/L","23년 평택전력 변전협력회사 총액공사","오산S/S 오산-평택#1T/L GIS 보통점검","2023-10-02 09:00","2023-10-02 18:00","취소","취소","연속"]
[259,"경기","평택","오산평택#2 T/L","23년 평택전력 변전협력회사 총액공사","오산S/S 오산-평택#2T/L GIS 보통점검","2023-10-03 09:00","2023-10-03 18:00","취소","취소","연속"]
[260,"경기","평택","송탄오성CC#2 T/L","2022-23 평택전력 가공송전 협력회사 총액공사","폴리머점퍼지지애자 설치 작업대상 : 4회선(모 송탄-오성CC/자 송탄안성) No.25(No.4)","2023-10-14 07:00","2023-10-15 18:00","2023-10-14 07:00","2023-10-15 18:00","연속"]
[261,"경기","평택","송탄오성CC#1 T/L","2022-23 평택전력 가공송전 협력회사 총액공사","폴리머점퍼지지애자 설치 작업대상 : 2회선 No.9,15","2023-10-16 07:00","2023-10-17 18:00","2023-10-16 07:00","2023-10-17 18:00","연속"]
[262,"경기","평택","원정만호#2 T/L","23년 평택전력 변전협력회사 총액공사","원정S/S 원정-만호#2T/L GIS 조작시험","2023-10-27 09:00","2023-10-27 18:00","2023-10-27 09:00","2023-10-27 18:00","연속"]
[263,"경기","평택","평택오성CC#2 T/L","23년 평택전력 변전협력회사 총액공사","평택S/S 평택-오성CC#2T/L GCB 조작시험(오성CC오버홀)","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[264,"경기","평택","평택오성CC#1 T/L","23년 평택전력 변전협력회사 총액공사","평택S/S 평택-오성CCT/L GIS 정밀점검(오성CC오버홀), PT&LA 보통점검","2023-10-10 09:00","2023-10-11 18:00","2023-10-10 09:00","2023-10-11 18:00","연속"]
[265,"강원","강릉","동해강릉 T/L","2022~2023년 가공송전협력회사 총액공사","○ Rail형 수평 가이드레일 설치(No.67)","2023-10-06 08:00","2023-10-06 18:00","2023-10-06 08:00","2023-10-06 18:00","매일"]
[266,"강원","강릉","강릉횡계#2 T/L","2023년 가공송전선로 순시점검 위탁공사","○ 154kV 강릉수력T/L 정밀점검 시행(No.10~36)","2023-10-16 08:00","2023-10-18 18:00","2023-10-16 08:00","2023-10-18 18:00","매일"]
[267,"강원","강릉","강릉영동TP T/L","2022~2023년 가공송전협력회사 총액공사","○ Rail형 수평 가이드레일 설치(No.67)","2023-10-16 08:00","2023-10-16 18:00","2023-10-16 08:00","2023-10-16 18:00","매일"]
[268,"강원","강릉","강릉횡계#1 T/L","2023년 가공송전선로 순시점검 위탁공사","○ 154kV 강릉수력T/L 정밀점검 시행(No.10~36)","2023-10-04 08:00","2023-10-06 18:00","취소","취소","매일"]
[269,"강원","강릉","속초간성#1 T/L","2022~2023년 가공송전협력회사 총액공사","○ 전선접속개소 해소공사(No.40~41) ○ Rail형 수평 가이드레일 설치(No.1)","2023-10-18 07:00","2023-10-18 18:00","2023-10-18 07:00","2023-10-18 18:00","연속"]
[270,"강원","강릉","속초간성#2 T/L","2022~2023년 가공송전협력회사 총액공사","○ 전선접속개소 해소공사(No.40~42) ○ Rail형 수평 가이드레일 설치(No.1)","2023-10-19 07:00","2023-10-19 18:00","2023-10-19 07:00","2023-10-19 18:00","연속"]
[271,"강원","강릉","북평영동TP#1 T/L","2023 변전협력회사 총액공사","- 170kV GIS 초기점검","2023-10-19 10:00","2023-10-19 18:00","2023-10-19 10:00","2023-10-19 18:00","연속"]
[272,"강원","강릉","북평영동TP#2 T/L","2023 변전협력회사 총액공사","- 170kV GIS 초기점검","2023-10-20 10:00","2023-10-20 18:00","2023-10-20 10:00","2023-10-20 18:00","연속"]
[273,"강원","강릉","횡계올림픽 T/L","2022~2023년 가공송전협력회사 총액공사","○ Rail형 수평 가이드레일 설치(No.1)","2023-10-31 08:00","2023-10-31 13:00","2023-10-31 08:00","2023-10-31 13:00","연속"]
[274,"강원","강릉","평창올림픽 T/L","2022~2023년 가공송전협력회사 총액공사","○ Rail형 수평 가이드레일 설치(No.91, 92, 93, 94)","2023-10-31 13:00","2023-11-01 18:00","2023-10-31 13:00","2023-11-01 18:00","매일"]
[275,"강원","강릉","횡계평창 T/L","2022~2023년 가공송전협력회사 총액공사","○ Rail형 수평 가이드레일 설치(No.1, 91, 92, 93, 94)","2023-10-12 08:00","2023-10-13 18:00","2023-10-12 08:00","2023-10-13 18:00","매일"]
[276,"강원","동해","동해영동TP T/L","2022-23년 동해전력지사 송전협력회사 총액공사","수직수평추락방지장치 설치","2023-10-20 08:00","2023-10-20 18:00","2023-10-20 08:00","2023-10-20 18:00","연속"]
[277,"강원","동해","삼척동해TP T/L","154kV 동해화력T/L OPGW 교체공사","OPGW(OP-S-L48) 9.072km 교체","2023-10-10 08:00","2023-10-18 18:00","2023-10-10 08:00","2023-10-18 18:00","연속"]
[278,"강원","동해","이원삼척 T/L","154kV 동해화력T/L OPGW 교체공사","OPGW(OP-S-L48) 9.072km 교체","2023-10-20 08:00","2023-10-23 18:00","2023-10-20 08:00","2023-10-23 18:00","연속"]
[279,"강원","동해","동해이원#1 T/L","22~23 동해전력지사 변전정비팀 총액공사","LA ABC상 보통점검","2023-10-27 09:30","2023-10-27 18:00","2023-10-27 09:30","2023-10-27 18:00","연속"]
[280,"강원","동해","동해이원#2 T/L","154kV 동해화력T/L OPGW 교체공사","OPGW(OP-S-L48) 9.072km 교체","2023-10-20 08:00","2023-10-23 18:00","2023-10-20 08:00","2023-10-23 18:00","연속"]
[281,"강원","동해","정선영월CC T/L","22~23 동해전력지사 변전정비팀 총액공사","GIS 정밀점검 LA ABC상 보통점검","2023-10-16 10:00","2023-10-18 14:00","2023-10-16 10:00","2023-10-18 14:00","연속"]
[282,"강원","동해","동해정선 T/L","22~23 동해전력지사 변전정비팀 총액공사","GIS 정밀점검, LA ABC상 보통점검","2023-10-25 14:00","2023-10-27 18:00","2023-10-25 14:00","2023-10-27 18:00","연속"]
[283,"강원","원주","남원주원주#1 T/L","'22~23년 원주전력지사 가공송전협력회사 총액공사","- 추락방지장치 설치","2023-10-28 07:00","2023-10-29 18:00","2023-10-28 07:00","2023-10-29 18:00","연속"]
[284,"강원","원주","남원주원주#2 T/L","'22~23년 원주전력지사 가공송전협력회사 총액공사","- 피뢰기 및 추락방지장치 설치","2023-10-21 07:00","2023-10-22 18:00","2023-10-21 07:00","2023-10-22 18:00","연속"]
[285,"강원","원주","신제천남원주#2 T/L","2023년 원주전력지사 170kV GIS 정밀점검공사","GIS 정밀점검","2023-10-28 09:00","2023-10-29 18:00","2023-10-28 09:00","2023-10-29 18:00","연속"]
[286,"강원","원주","원주북원주#2 T/L","북원주S/S 외장재 교체공사","○ 변전소 외장재 교체 : 1,768㎡ (드라이비트 → 메탈판넬) ○ 시스템비계 설치 : 1,668㎡ ○ 외벽도장 : 238㎡","2023-10-17 09:00","2023-10-22 18:00","2023-10-17 09:00","2023-10-22 18:00","매일"]
[287,"강원","원주","북원주횡성#2 T/L","북원주S/S 외장재 교체공사","○ 변전소 외장재 교체 : 1,768㎡ (드라이비트 → 메탈판넬) ○ 시스템비계 설치 : 1,668㎡ ○ 외벽도장 : 238㎡","2023-10-14 09:00","2023-10-18 18:00","2023-10-14 09:00","2023-10-18 18:00","매일"]
[288,"강원","원주","북원주횡성#1 T/L","북원주S/S 외장재 교체공사","○ 변전소 외장재 교체 : 1,768㎡ (드라이비트 → 메탈판넬) ○ 시스템비계 설치 : 1,668㎡ ○ 외벽도장 : 238㎡","2023-10-10 09:00","2023-10-15 18:00","2023-10-10 09:00","2023-10-15 18:00","매일"]
[289,"강원","원주","원주북원주#1 T/L","북원주S/S 외장재 교체공사","○ 변전소 외장재 교체 : 1,768㎡ (드라이비트 → 메탈판넬) ○ 시스템비계 설치 : 1,668㎡ ○ 외벽도장 : 238㎡","2023-10-21 09:00","2023-10-25 18:00","2023-10-21 09:00","2023-10-25 18:00","매일"]
[290,"강원","원주","횡성홍천#1 T/L","'22~23년 원주전력지사 가공송전 협력회사 총액공사","- 폴리머 지지애자설치(4회선구간 하단부분 휴전필요함)","2023-10-17 07:00","2023-10-18 18:00","2023-10-17 07:00","2023-10-18 18:00","매일"]
[291,"강원","직할","홍천남춘천 T/L","강원 관내 OPGW 불량개소 정비공사","- 154kV 소양T/L No.76호 OPGW 접지선 시설","2023-10-14 08:00","2023-10-14 18:00","2023-10-14 08:00","2023-10-14 18:00","연속"]
[292,"강원","직할","춘천북춘천#1 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-10-10 08:00","2023-10-14 18:00","취소","취소","매일"]
[293,"강원","직할","춘천북춘천#2 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-10-16 08:00","2023-10-20 18:00","취소","취소","매일"]
[294,"강원","직할","북춘천화천HP T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-10-16 08:00","2023-10-20 18:00","2023-10-16 08:00","2023-10-20 18:00","연속"]
[295,"강원","직할","인제양구#2 T/L","22~23년 강원본부 직할 변전협력회사 총액공사","인제양구#2T/L 장기미동작 차단기 조작시험(양구)","2023-10-10 14:00","2023-10-10 18:00","취소","취소","연속"]
[296,"강원","직할","인제양구#1 T/L","22~23년 강원본부 직할 변전협력회사 총액공사","인제양구#1T/L 장기미동작 차단기 조작시험(인제,양구)","2023-10-10 10:00","2023-10-10 14:00","취소","취소","연속"]
[297,"강원","직할","상남인제#1 T/L","2023년 가공송전 순시점검 위탁공사","154kV 상제 T/L 수목벌채","2023-10-06 09:00","2023-10-06 18:00","취소","취소","연속"]
[298,"강원","직할","신양양인제#1 T/L","22~23년 강원본부 직할 변전협력회사 총액공사","신양양인제#1T/L 장기미동작 차단기 조작시험(인제)","2023-10-11 10:00","2023-10-11 14:00","취소","취소","연속"]
[299,"강원","직할","신양양인제#2 T/L","22~23년 강원본부 직할 변전협력회사 총액공사","신양양인제#2T/L 장기미동작 차단기 조작시험(인제)","2023-10-11 14:00","2023-10-11 18:00","취소","취소","연속"]
[300,"강원","직할","인제S/S CB 6100","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사 - 인제S/S 154kV #1-#2 BUS TIE CB 정밀점검","2023-10-30 09:00","2023-11-02 18:00","2023-10-30 09:00","2023-11-02 18:00","연속"]
[301,"강원","직할","상남인제#2 T/L","2023년 가공송전 순시점검 위탁공사","154kV 상제 T/L 수목벌채","2023-10-04 09:00","2023-10-05 18:00","취소","취소","매일"]
[302,"강원","직할","철원화천#2 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-10-23 08:00","2023-11-03 18:00","2023-10-23 08:00","2023-11-03 18:00","매일"]
[303,"강원","직할","철원화천#1 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-10-23 08:00","2023-11-03 18:00","2023-10-23 08:00","2023-11-03 18:00","매일"]
[304,"강원","직할","북춘천춘천HP T/L","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사 - 춘천HP 154kV 북춘천춘천HP T/L GIS 정밀점검","2023-10-04 09:00","2023-10-06 18:00","취소","취소","연속"]
[305,"강원","직할","화천화천HP#2 T/L","2022~23년 직할 변전정비 총액공사","○ 화천HP 154kV 화천-화천hp #2T/L 장기미동작 차단기 조작시험","2023-10-03 13:00","2023-10-03 16:00","2023-10-03 13:00","2023-10-03 16:00","연속"]
[306,"강원","직할","화천H/P CB 6100","22~23년 강원본부 직할 변전협력회사 총액공사","화천H/P 154kV 모선보호반 대체","2023-10-24 10:00","2023-10-27 18:00","2023-10-24 10:00","2023-10-27 18:00","연속"]
[307,"강원","직할","화천화천HP#1 T/L","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사 - 화천HP 154kV 화천화천HP#1 T/L GIS 정밀점검","2023-10-10 09:00","2023-10-13 18:00","2023-10-10 09:00","2023-10-13 18:00","연속"]
[308,"강원","직할","화천S/S CB 6100","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사 - 화천S/S 154kV #1-#2 BUS TIE CB 정밀점검","2023-10-16 09:00","2023-10-19 18:00","2023-10-16 09:00","2023-10-19 18:00","연속"]
[309,"강원","직할","화천S/S #2 BUS","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사 - 화천S/S 154kV #2M.Tr 1차 GIS 정밀점검 - 무부하 가압","2023-10-27 14:00","2023-10-27 18:00","2023-10-27 14:00","2023-10-27 18:00","연속"]
[310,"강원","직할","화천S/S #1 BUS","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사 - 화천S/S 154kV #1M.Tr 1차 GIS 정밀점검 - 무부하 가압","2023-10-25 09:00","2023-10-25 14:00","2023-10-25 09:00","2023-10-25 14:00","연속"]
[311,"강원","태백","신제천영월CC#2 T/L","영월C/C 154kV 신제천-영월CC #2T/L 가스누기 보수공사","영월C/C 154kV 신제천-영월CC #2T/L 가스누기 보수공사","2023-10-10 09:00","2023-10-12 18:00","2023-10-10 09:00","2023-10-12 18:00","연속"]
[312,"강원","태백","영월에코윈드S/S SEC CB 60610","2023년 태백전력지사 변전협력회사 총액공사","영월에코윈드S/Y 154kV #60-#61 SEC GIS 초기점검","2023-10-19 10:00","2023-10-19 18:00","2023-10-19 10:00","2023-10-19 18:00","연속"]
[313,"강원","태백","영월에코윈드S/S CB 6200","2023년 태백전력지사 변전협력회사 총액공사","영월에코윈드S/Y 154kV #61-#66 BUS TIE GIS 초기점검","2023-10-18 14:00","2023-10-18 18:00","2023-10-18 14:00","2023-10-18 18:00","연속"]
[314,"강원","태백","영월에코윈드S/S CB 6100","2023년 태백전력지사 변전협력회사 총액공사","영월에코윈드S/Y 154kV #60-#65 BUS TIE GIS 초기점검","2023-10-18 09:00","2023-10-18 14:00","2023-10-18 09:00","2023-10-18 14:00","연속"]
[315,"강원","태백","영월에코윈드S/S SEC CB 65660","2023년 태백전력지사 변전협력회사 총액공사","영월에코윈드S/Y 154kV #65-#66 SEC GIS 초기점검","2023-10-16 10:00","2023-10-16 18:00","2023-10-16 10:00","2023-10-16 18:00","연속"]
[316,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치(#65BUS 무부하가압)","2023-10-19 10:00","2023-10-20 18:00","취소","취소","연속"]
[317,"강원","태백","태백삼척GP#2 T/L","2023년 가공송전 순시점검 위탁공사","송전선로 선하지 지장수목 벌채","2023-10-22 08:00","2023-10-22 15:00","2023-10-22 08:00","2023-10-22 15:00","연속"]
[318,"강원","태백","태백S/S #65 BUS","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치","2023-10-16 10:00","2023-10-20 18:00","2023-10-30 09:00","2023-11-03 18:00","연속"]
[319,"강원","태백","태백S/S CB 6100","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치","2023-10-16 10:00","2023-10-27 18:00","2023-10-30 09:00","2023-11-10 18:00","연속"]
[320,"강원","태백","태백영월에코윈드 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치","2023-10-16 10:00","2023-10-18 18:00","2023-10-30 09:00","2023-11-10 18:00","연속"]
[321,"강원","태백","태백S/S #60 BUS","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치","2023-10-23 10:00","2023-10-27 18:00","취소","취소","연속"]
[322,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치(#60BUS 무부하가압)","2023-10-26 10:00","2023-10-27 18:00","취소","취소","연속"]
[323,"충북","직할","신진천S/S SEC CB 65660","22-23년 충북직할 변전협력회사 총액공사","- 신진천S/S 154kV GIS 보통점검","2023-10-05 10:00","2023-10-05 18:00","취소","취소","연속"]
[324,"충북","직할","신진천S/S CB 6200","22-23년 충북직할 변전협력회사 총액공사","- 신진천S/S 154kV GIS 보통점검","2023-10-12 10:00","2023-10-12 18:00","취소","취소","연속"]
[325,"충북","직할","신진천S/S SEC CB 60610","직할 변전협력회사 총액공사","장기미동작 차단기 조작시험","2023-10-06 13:00","2023-10-06 18:00","취소","취소","연속"]
[326,"충북","직할","신진천S/S SEC CB 66670","22-23년 충북직할 변전협력회사 총액공사","- 신진천S/S 효성제 154kV GIS 노후 전자변 교체","2023-10-06 10:00","2023-10-06 18:00","취소","취소","연속"]
[327,"충북","직할","신진천S/S CB 6200","22-23년 충북직할 변전협력회사 총액공사","- 신진천S/S 효성제 154kV 공압식 GIS 노후 전자변 교체","2023-10-13 10:00","2023-10-13 18:00","취소","취소","연속"]
[328,"충북","직할","신진천진천#1 T/L","22-23년 충북직할 변전협력회사 총액공사","- 신진천S/S 154kV GIS 보통점검","2023-10-21 10:00","2023-10-21 18:00","2023-10-21 10:00","2023-10-21 18:00","연속"]
[329,"충북","직할","신진천진천#2 T/L","22-23년 충북직할 변전협력회사 총액공사","- 신진천S/S 효성제 154kV GIS 노후 전자변 교체","2023-10-14 10:00","2023-10-14 18:00","취소","취소","연속"]
[330,"충북","청주","국사봉명#1 T/L","154kV 국사-봉명T/L No.3 지장철탑이설공사","154kV 국사-봉명T/L 3호 철탑이설, 2~5호 전력선교체(1.904C-km)","2023-10-02 08:00","2023-10-06 18:00","2023-10-06 07:30","2023-10-10 18:00","연속"]
[331,"충북","청주","국사봉명#1 T/L","154kV 국사-봉명T/L No.3 지장철탑이설공사","154kV 국사-봉명T/L 3호 철탑이설, 2~5호 전력선교체(1.904C-km)","2023-10-12 08:00","2023-10-17 18:00","2023-10-18 07:30","2023-10-22 18:00","연속"]
[332,"충북","청주","국사봉명#2 T/L","154kV 국사-봉명T/L No.3 지장철탑이설공사","154kV 국사-봉명T/L 3호 철탑이설, 2~5호 전력선교체(1.904C-km)","2023-10-07 08:00","2023-10-11 18:00","2023-10-11 07:30","2023-10-17 18:00","연속"]
[333,"충북","청주","남청주S/S #65 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (1차)","#66-65 SEC GIS 대체","2023-10-25 14:00","2023-10-27 18:00","2023-10-30 14:00","2023-11-01 18:00","연속"]
[334,"충북","청주","남청주청주#4 T/L","`22~`23년 청주전력지사 송전협력회사 총액공사","아킹혼 48기, 폴리머지지애자 7기 설치","2023-10-05 08:00","2023-10-12 18:00","취소","취소","매일"]
[335,"충북","청주","남청주청주#2 T/L","`22~`23년 청주전력지사 송전협력회사 총액공사","아킹혼 48기, 폴리머지지애자 7기 설치","2023-10-05 08:00","2023-10-12 18:00","취소","취소","매일"]
[336,"충북","청주","남청주S/S SEC CB 60610","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","#61-60 SEC GIS 대체","2023-10-30 09:00","2023-11-07 18:00","2023-11-03 09:00","2023-11-11 18:00","연속"]
[337,"충북","청주","남청주S/S SEC CB 65660","남청주S/S 154kV 장기사용 GIS 대체공사 (1차)","#66-65 SEC GIS 대체","2023-10-18 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-11-01 18:00","연속"]
[338,"충북","청주","남청주S/S #65 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (1차)","#66-65 SEC GIS 대체","2023-10-18 09:00","2023-10-19 10:00","2023-10-23 09:00","2023-10-24 10:00","연속"]
[339,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (1차)","#66-65 SEC GIS 대체","2023-10-19 10:00","2023-10-25 14:00","2023-10-24 10:00","2023-10-30 14:00","연속"]
[340,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","#61-60 SEC GIS 대체","2023-10-31 10:00","2023-11-05 14:00","2023-11-03 09:00","2023-11-05 18:00","연속"]
[341,"충북","청주","남청주S/S #60 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","#61-60 SEC GIS 대체","2023-10-30 09:00","2023-10-31 10:00","2023-11-03 09:00","2023-11-04 10:00","연속"]
[342,"충북","청주","화동보은 T/L","`22~`23년 청주전력지사 송전협력회사 총액공사","No.25~29 추락방지장치 수평 시공","2023-10-11 08:00","2023-10-13 18:00","취소","취소","연속"]
[343,"충북","청주","동천안북오송#2 T/L","154kV 북오송분기T/L 하자처리 공사","154kV 북오송-전의(동천안-북오송)T/L 하자처리 공사","2023-10-18 09:00","2023-10-19 18:00","2023-10-18 09:00","2023-10-19 18:00","매일"]
[344,"충북","청주","북오송전의#1 T/L","154kV 북오송분기T/L 하자처리 공사","154kV 북오송-전의(동천안-북오송)T/L 하자처리 공사","2023-10-18 09:00","2023-10-19 18:00","2023-10-18 09:00","2023-10-19 18:00","매일"]
[345,"충북","청주","서청주사직#2 T/L","대한전선제 열경화공법 EBG 보강공사","서청주S/S, 사직S/S 154kV 서청주-사직T/L EBG 보강공사","2023-10-07 09:00","2023-10-08 18:00","취소","취소","연속"]
[346,"충북","청주","서청주사직#1 T/L","대한전선제 열경화공법 EBG 보강공사","서청주S/S, 사직S/S 154kV 서청주-사직T/L EBG 보강공사","2023-10-28 09:00","2023-10-29 18:00","2023-10-28 09:00","2023-10-29 18:00","연속"]
[347,"충북","청주","옥천영동 T/L","`22~`23년 청주전력지사 송전협력회사 총액공사","화동T/L 추락방지 43기, 폴리머지지애자2기 영동분기T/L 추락방지 61기, 폴리머지지애자1기 설치","2023-10-30 08:00","2023-11-10 18:00","취소","취소","매일"]
[348,"충북","청주","옥천보은 T/L","`22~`23년 청주전력지사 송전협력회사 총액공사","화동T/L 추락방지 43기, 아킹혼8기, 폴리머지지애자6기, 피뢰기1기 설치 보은분기T/L 추락방지 29기, 아킹혼 17기, 폴리머지지애자4기 설치","2023-10-16 08:00","2023-10-28 18:00","취소","취소","매일"]
[349,"충북","청주","초정청주#2 T/L","154kV 초정변전소 외장재 교체공사","드라이비트 마감재 철거 / 신규 알루미늄시트판넬 설치","2023-10-20 09:00","2023-11-03 18:00","취소","취소","연속"]
[350,"충북","청주","초정청주#1 T/L","154kV 초정변전소 외장재 교체공사","드라이비트 마감재 철거 / 신규 알루미늄시트판넬 설치","2023-10-20 09:00","2023-11-03 18:00","취소","취소","연속"]
[351,"충북","충주","감곡가남#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV감곡가남#2 T/L No.1 ~ 22","2023-10-20 07:30","2023-10-21 18:00","취소","취소","매일"]
[352,"충북","충주","금왕남음성#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV금왕남음성#2 T/L No.42","2023-10-25 07:30","2023-10-26 18:00","취소","취소","매일"]
[353,"충북","충주","금왕남음성#1 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV금왕남음성#1 T/L No.42","2023-10-27 07:30","2023-10-27 18:00","취소","취소","연속"]
[354,"충북","충주","남음성덕산#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV 남음성덕산#2 T/L No.1~21","2023-10-26 07:30","2023-10-28 18:00","취소","취소","매일"]
[355,"충북","충주","남음성덕산#1 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV 남음성덕산#1 T/L No.1~21","2023-10-22 07:30","2023-10-25 18:00","취소","취소","매일"]
[356,"충북","충주","단양영월CC#2 T/L","22-23년 충주전력지사 변전협력회사 총액공사","단양S/S 단양영월CC#2T/L GIS 초기점검","2023-10-17 09:00","2023-10-17 18:00","2023-10-17 09:00","2023-10-17 18:00","연속"]
[357,"충북","충주","단양영월CC#1 T/L","22-23년 충주전력지사 변전협력회사 총액공사","단양S/S 단양영월CC#1T/L GIS 초기점검","2023-10-16 09:00","2023-10-16 18:00","2023-10-16 09:00","2023-10-16 18:00","연속"]
[358,"충북","충주","점촌단양 T/L","345kV 신제천-신충주 등 6개T/L 송전피뢰기 설치공사","154kV 점촌-단양T/L 송전피뢰기 설치(주말작업 있음)","2023-10-07 07:00","2023-10-08 18:00","취소","취소","매일"]
[359,"충북","충주","점촌단양 T/L","345kV 신제천-신충주 등 6개T/L 송전피뢰기 설치공사","154kV 점촌-단양T/L 송전피뢰기 설치(주말작업 있음)","2023-10-14 07:00","2023-10-15 18:00","취소","취소","매일"]
[360,"충북","충주","신제천왕암#2 T/L","22-23년 충주전력지사 변전협력회사 총액공사","신제천S/S 신제천왕암#2T/L GIS 보통점검","2023-10-30 09:00","2023-10-30 14:00","2023-10-30 09:00","2023-10-30 14:00","연속"]
[361,"충북","충주","신제천제천#1 T/L","345kV 신제천-신충주 등 6개T/L 송전피뢰기 설치공사","154kV 신제천-제천T/L 송전피뢰기 설치(주말작업 있음)","2023-10-19 07:00","2023-10-22 18:00","취소","취소","매일"]
[362,"충북","충주","신제천왕암#1 T/L","345kV 신제천-신충주 등 6개T/L 송전피뢰기 설치공사","154kV 신제천-왕암T/L 송전피뢰기 설치(주말작업 있음)","2023-10-20 07:00","2023-10-23 18:00","취소","취소","매일"]
[363,"충북","충주","신제천S/S SEC CB 60610","22-23년 충주전력지사 변전협력회사 총액공사","신제천S/S #60-61 BUS SEC GIS 보통점검","2023-10-30 14:00","2023-10-30 18:00","2023-10-30 14:00","2023-10-30 18:00","연속"]
[364,"충북","충주","음성사리 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","풍동-음성T/L 추락방지장치 설치 154kV 풍동음성T/L No. 54 ~ 92 (병행선로 휴전)","2023-10-01 07:30","2023-10-08 18:00","2023-10-01 07:30","2023-10-08 18:00","매일"]
[365,"충북","충주","음성괴산 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","풍동-음성T/L 추락방지장치 설치 154kV 풍동음성T/L No. 54 ~ 92 (병행선로 휴전)","2023-10-09 07:30","2023-10-15 18:00","2023-10-09 07:30","2023-10-15 18:00","매일"]
[366,"충북","충주","풍동음성#1 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","풍동-음성T/L 추락방지장치 설치 154kV 풍동음성T/L No. 1 ~ 92","2023-10-09 07:30","2023-10-15 18:00","2023-10-09 07:30","2023-10-15 18:00","매일"]
[367,"충북","충주","음성금왕#1 T/L","22-23년 충주전력지사 변전협력회사 총액공사","음성,금왕S/S 음성금왕#1T/L GIS 보통점검","2023-10-19 09:00","2023-10-19 18:00","취소","취소","연속"]
[368,"충북","충주","장연S/S #1 BUS","장연S/S 154, 23kV 장기사용 GIS 대체공사(SA 병행)","154kV 장기사용 GIS 대체 (#2 M.Tr 1차 GIS 등 6Bay)","2023-10-31 09:00","2023-11-17 18:00","2023-10-31 09:00","2023-11-17 18:00","연속"]
[369,"충북","충주","장연S/S #2 BUS","장연S/S 154, 23kV 장기사용 GIS 대체공사(SA 병행)","154kV 장기사용 GIS 대체 (#2 M.Tr 1차 GIS 등 6Bay)","2023-10-31 09:00","2023-11-17 18:00","2023-10-31 09:00","2023-11-17 18:00","연속"]
[370,"충북","충주","충주장연 T/L","장연S/S 154, 23kV 장기사용 GIS 대체공사(SA 병행)","154kV 장기사용 GIS 대체 (#2 M.Tr 1차 GIS 등 6Bay)","2023-10-31 09:00","2023-11-17 18:00","2023-10-31 09:00","2023-11-17 18:00","연속"]
[371,"충북","충주","제천영월#1 T/L","22-23년 충주전력지사 변전협력회사 총액공사","제천S/S 제천영월#1T/L GIS 보통점검","2023-10-18 09:00","2023-10-18 14:00","2023-10-18 09:00","2023-10-18 14:00","연속"]
[372,"충북","충주","제천영월#2 T/L","22-23년 충주전력지사 변전협력회사 총액공사","제천S/S 제천영월#2T/L GIS 보통점검","2023-10-18 14:00","2023-10-18 18:00","2023-10-18 14:00","2023-10-18 18:00","연속"]
[373,"충북","충주","충주S/S SEC CB 60610","22-23년 충주전력지사 변전협력회사 총액공사","충주S/S #60-61 BUS SEC GIS 보통점검","2023-10-11 09:00","2023-10-11 14:00","2023-10-11 09:00","2023-10-11 14:00","연속"]
[374,"충북","충주","충주S/S CB 6100","22-23년 충주전력지사 변전협력회사 총액공사","충주S/S #60-65 BUS TIE GIS 초기점검","2023-10-11 14:00","2023-10-11 18:00","2023-10-11 14:00","2023-10-11 18:00","연속"]
[375,"충북","충주","풍동음성#2 T/L","23년 충북본부 직할 송전정비 협력회사 총액공사","풍동-음성T/L 추락방지장치 설치 154kV 풍동음성T/L No. 1 ~ 92 총 78기","2023-10-01 07:30","2023-10-08 18:00","2023-10-01 07:30","2023-10-08 18:00","매일"]
[376,"대전세종충남","대전","금산무주#2 T/L","금산S/S 154kV 장기사용 GIS 교체공사","금산S/S 154kV 장기사용 GIS 교체공사(6333,657 GIS 교체) - 안전이격, 상시 환원 가능조건","2023-10-24 08:00","2023-10-24 12:00","2023-10-31 07:00","2023-10-31 10:00","연속"]
[377,"대전세종충남","대전","금산무주#2 T/L","금산S/S 154kV 장기사용 GIS 교체공사","금산S/S 154kV 장기사용 GIS 교체공사(6333,657 GIS 교체) - 안전이격, 상시 환원 가능조건","2023-10-12 08:00","2023-10-12 12:00","2023-10-19 07:00","2023-10-19 10:00","연속"]
[378,"대전세종충남","대전","금산무주#2 T/L","금산S/S 154kV 장기사용 GIS 교체공사","금산S/S 154kV 장기사용 GIS 교체공사(6333,657 GIS 교체) - 안전이격, 상시 환원 가능조건","2023-10-23 08:00","2023-10-23 12:00","2023-10-30 07:00","2023-10-30 10:00","연속"]
[379,"대전세종충남","대전","신옥천남대전#1 T/L","(9월 취소시)[송전]345kV신옥천-청양등17개T/L추락방지설치공사","(9월 취소시)[송전]345kV신옥천-청양등17개T/L추락방지시설 설치공사","2023-10-02 08:00","2023-10-17 18:00","취소","취소","매일"]
[380,"대전세종충남","대전","신옥천남대전#4 T/L","(9월 취소시)[송전]345kV신옥천-청양등17개T/L추락방지설치공사","(9월 취소시)[송전]345kV신옥천-청양등17개T/L추락방지시설 설치공사","2023-10-18 08:00","2023-10-31 18:00","2023-10-18 08:00","2023-10-31 18:00","매일"]
[381,"대전세종충남","대전","팔봉두마#2 T/L","두마S/S 154kV 팔봉-두마#2T/L 보호반 교체","두마S/S 154kV 팔봉-두마#2T/L 보호반 교체 -두마S/S 154kV 팔봉-두마#2T/L LA(A,B,C) 초기점검 -두마S/S 154kV 팔봉-두마#2T/L 차단기 부동작 예방 조작시험","2023-10-10 09:00","2023-10-12 18:00","2023-10-11 16:00","2023-10-11 20:00","연속"]
[382,"대전세종충남","대전","팔봉두마#1 T/L","두마S/S 154kV 팔봉-두마#1T/L 보호반 교체","두마S/S 154kV 팔봉-두마#1T/L 보호반 교체 -두마S/S 154kV 팔봉-두마#1T/L LA(A,B,C) 초기점검 -두마S/S 154kV 팔봉-두마#1T/L 차단기 부동작 예방 조작시험","2023-10-04 09:00","2023-10-06 18:00","2023-10-05 16:00","2023-10-05 20:00","연속"]
[383,"대전세종충남","대전","신옥천서대전 T/L","서대전S/S 154kV 신옥천-서대전T/L 보호반 교체","서대전S/S 154kV 신옥천-서대전T/L 보호반 교체 -[병행]서대전S/S 154kV 신옥천-서대전T/L GIS 초기점검","2023-10-30 09:00","2023-11-02 18:00","취소","취소","연속"]
[384,"대전세종충남","대전","신옥천서대전 T/L","[송전] 154kV 가수원-서대전 등 5개T/L 추락방지시설 설치공사","[송전] 154kV 신옥천-서대전T/L 추락방지시설 설치공사","2023-10-26 08:00","2023-11-10 18:00","2023-10-26 08:00","2023-11-10 18:00","연속"]
[385,"대전세종충남","대전","신옥천유천 T/L","[송전] 154kV 가수원-서대전 등 5개T/L 추락방지시설 설치공사","[송전] 154kV 신옥천-유천T/L 추락방지시설 설치공사","2023-10-02 08:00","2023-10-19 18:00","2023-10-16 08:00","2023-11-02 18:00","매일"]
[386,"대전세종충남","서산","대산S/S SEC CB 60610","154kV 대산변전소 대호호수상태양광T/L GIS 증설공사","- 대호호수상태양광T/L 모선보호반 연동시험 - #4M.Tr 증설대비 모선보호반 Feeder 증설 * 일정변경가능","2023-10-19 09:00","2023-10-19 18:00","취소","취소","연속"]
[387,"대전세종충남","서산","서산대산#4 T/L","'23년 서산P/O 변전협력회사 총액공사","대산S/S 154kV 서산-대산#4T/L 6G7 GIS 보통점검","2023-10-25 09:00","2023-10-25 18:00","취소","취소","연속"]
[388,"대전세종충남","서산","대산석문#2 T/L","'23년 서산P/O 변전협력회사 총액공사","대산S/S 154kV 대산-석문#2T/L CB 전자변, 에어링밸브 교체 (병행1) 대산S/S 154kV 대산-석문#2T/L CVT 대체 (병행2) 석문S/S 154kV 대산-석문#2T/L IED 성능개선","2023-10-23 09:00","2023-10-23 18:00","취소","취소","연속"]
[389,"대전세종충남","서산","대산S/S CB 6200","154kV 대산변전소 대호호수상태양광T/L GIS 증설공사","- 대호호수상태양광T/L 모선보호반 연동시험 - #4M.Tr 증설대비 모선보호반 Feeder 증설 * 일정변경가능","2023-10-19 09:00","2023-10-19 18:00","취소","취소","연속"]
[390,"대전세종충남","서산","대산S/S SEC CB 65660","154kV 대산변전소 대호호수상태양광T/L GIS 증설공사","- 대호호수상태양광T/L 모선보호반 연동시험 - #4M.Tr 증설대비 모선보호반 Feeder 증설 * 일정변경가능","2023-10-19 09:00","2023-10-19 18:00","취소","취소","연속"]
[391,"대전세종충남","서산","대산석문#1 T/L","154kV 대산-석문T/L 항공장애표시구 설치 공사","가공지선 항공장애표시구 설치 No.19~20,29~30,31~34,35~36,38~40 (9월 휴전 취소시)","2023-10-04 08:00","2023-10-06 18:00","취소","취소","매일"]
[392,"대전세종충남","서산","서산태안 T/L","2023년도 가공송전 순시점검 위탁공사","154kV 서산-태안T/L 조류착지방지장치 설치","2023-10-04 08:00","2023-10-06 18:00","취소","취소","매일"]
[393,"대전세종충남","서산","서산태안화력 T/L","154kV 태안분기T/L 건설공사","154kV 서산-태안화력T/L No.51,57~No.58 전력선 교체 및 점퍼선 연결","2023-10-12 07:00","2023-10-19 18:00","2023-10-19 07:00","2023-10-26 18:00","연속"]
[394,"대전세종충남","서산","서산성연 T/L","154kV 태안분기T/L 건설공사","154kV 서산-성연T/L No.1 C6, C4 전력선 교체 및 서산S/S 인출변경","2023-10-16 07:00","2023-10-16 18:00","2023-10-23 07:00","2023-10-23 18:00","연속"]
[395,"대전세종충남","서산","서산태안화력 T/L","2023년도 가공송전 순시점검 위탁공사","154kV 서산-태안화력T/L 조류착지방지장치 설치[매일,주말제외]","2023-10-16 08:00","2023-10-27 18:00","취소","취소","매일"]
[396,"대전세종충남","서산","합덕송악#2 T/L","154kV 합덕-송악 등 2개 T/L 상간스페이서 설치 및 이도조정","상간스페이서 설치 : No.85~86 이도조정 : No.85~87","2023-10-16 08:00","2023-10-20 18:00","취소","취소","매일"]
[397,"대전세종충남","서산","당진송악#1 T/L","154kV 합덕-송악 등 2개 T/L 상간스페이서 설치 및 이도조정","상간스페이서 설치 : No.27~28 이도조정 : No.27~29","2023-10-16 08:00","2023-10-20 18:00","취소","취소","매일"]
[398,"대전세종충남","서산","신당진당진#1 T/L","23년 서산P/O 154kV이하 개폐장치 보통점검공사","신당진S/S 154kV 647 GIS 보통점검 (병행) 신당진S/S 154kV 신당진-당진#1T/L CVT 대체","2023-10-13 09:00","2023-10-13 18:00","취소","취소","연속"]
[399,"대전세종충남","서산","신당진S/S SEC CB 65660","23년 서산P/O 154kV이하 개폐장치 보통점검공사","신당진S/S 65-66-0 CB 보통점검","2023-10-12 09:00","2023-10-12 18:00","취소","취소","연속"]
[400,"대전세종충남","서산","신당진S/S SEC CB 60610","23년 서산P/O 154kV이하 개폐장치 보통점검공사","신당진S/S 60-61-0 CB 보통점검","2023-10-11 09:00","2023-10-11 18:00","취소","취소","연속"]
[401,"대전세종충남","서산","태안태안화력 T/L","2023년도 가공송전 순시점검 위탁공사","154kV 태안-태안화력T/L 조류착지방지장치 설치","2023-10-10 08:00","2023-10-13 18:00","취소","취소","매일"]
[402,"대전세종충남","서산","서산태안화력 T/L","154kV 태안화력T/L 전선접속개소 전선교체공사","154kV 태안-태안화력T/L 전력선 교체공사(3개소) - No.2~6, 11~13","2023-10-16 08:00","2023-10-19 18:00","취소","취소","연속"]
[403,"대전세종충남","서산","아산합덕#1 T/L","합덕S/S 154kV 당진전철#1,2T/L 상확인 및 실부하가압","합덕S/S 154kV 당진전철#1,2T/L 상확인 및 실부하가압","2023-10-20 09:00","2023-10-20 18:00","2023-10-20 09:00","2023-10-20 18:00","연속"]
[404,"대전세종충남","세종","세종부강#2 T/L","[변전]'23년 세종전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검 시행(11BAY)","2023-10-25 09:00","2023-10-26 18:00","취소","취소","연속"]
[405,"대전세종충남","세종","세종서세종#1 T/L","[변전]세니온제 보호계전기 성능개선","○세니온제 보호계전기 성능개선 -F/W 업데이트 및 보호계전기 시험(계통시험팀 입회)","2023-10-17 10:00","2023-10-17 18:00","2023-10-17 10:00","2023-10-17 18:00","연속"]
[406,"대전세종충남","세종","세종서세종#2 T/L","[변전]세니온제 보호계전기 성능개선","○세니온제 보호계전기 성능개선 -F/W 업데이트 및 보호계전기 시험(계통시험팀 입회)","2023-10-25 10:00","2023-10-25 18:00","2023-10-25 10:00","2023-10-25 18:00","연속"]
[407,"대전세종충남","세종","천안전의#2 T/L","[송전]154kV 천안-전의#2T/L 추락방지시설 설치공사","[송전]154kV 천안-전의#2T/L 추락방지시설 설치공사 - No.1~32, 34(32기)","2023-10-25 07:00","2023-10-31 18:00","2023-10-25 07:00","2023-10-31 18:00","매일"]
[408,"대전세종충남","세종","천안전의#1 T/L","[송전]154kV 천안-전의#1T/L 추락방지시설 설치공사","[송전]154kV 천안-전의#1T/L 추락방지시설 설치공사 - No.0.1(C/H), 1~8, 10~34(33기)","2023-10-10 07:00","2023-10-24 18:00","2023-10-10 07:00","2023-10-24 18:00","매일"]
[409,"대전세종충남","직할","둔곡송강#1 T/L","'22-23년 직할 변전협력회사 총액공사","- 170kV GIS 보통점검 - 세니온제 보호계전기 성능개선","2023-10-01 09:00","2023-10-01 18:00","2023-10-01 09:00","2023-10-01 18:00","연속"]
[410,"대전세종충남","직할","신탄진대청HP T/L","154kV 신탄진S/S 미래화 관련 전력구 설치공사(토목)","- 가시설물 설치 관련 안전이격 확보 - 비상 시 30분 이내 가압예정","2023-10-10 09:00","2023-10-13 18:00","2023-10-10 09:00","2023-10-13 18:00","매일"]
[411,"대전세종충남","천안","둔포직산#1 T/L","둔포S/S 154kV 직산-둔포#1T/L CB 개폐타임 측정","둔포S/S 154kV 직산-둔포#1T/L CB 개폐타임 측정","2023-10-16 09:00","2023-10-16 18:00","2023-10-16 09:00","2023-10-16 18:00","연속"]
[412,"대전세종충남","천안","서천안S/S SEC CB 60610","서천안S/S 154kV #60-61 SEC GIS 보통점검","서천안S/S 154kV #60-61 SEC GIS 보통점검","2023-10-17 09:00","2023-10-17 18:00","2023-10-28 14:00","2023-10-28 18:00","연속"]
[413,"대전세종충남","천안","서천안S/S SEC CB 65660","서천안S/S 154kV #65-#66 SEC GIS 보통점검","서천안S/S 154kV #65-#66 SEC GIS 보통점검","2023-10-16 09:00","2023-10-16 18:00","2023-10-28 09:00","2023-10-28 14:00","연속"]
[414,"대전세종충남","천안","서천안탕정#2 T/L","[송전]추락방지장치 설치공사","[안전이격거리확보]154kV 인주-불당T/L 추락방지장치 설치공사","2023-10-16 07:00","2023-10-16 17:00","2023-10-29 09:00","2023-10-29 18:00","연속"]
[415,"대전세종충남","천안","서천안탕정#1 T/L","[송전]추락방지장치 설치공사","[안전이격거리확보]154kV 인주-불당T/L 추락방지장치 설치공사","2023-10-17 07:00","2023-10-17 17:00","2023-10-14 09:00","2023-10-14 18:00","연속"]
[416,"대전세종충남","천안","성거S/S #2 BUS","성거S/S 154kV 모선구분차단기 증설공사","성거S/S 154kV 모선구분차단기 증설공사","2023-10-17 09:00","2023-10-27 14:00","2023-10-17 09:00","2023-10-27 14:00","연속"]
[417,"대전세종충남","천안","성거S/S #1 BUS","성거S/S 154kV 모선구분차단기 증설공사","성거S/S 154kV 모선구분차단기 증설공사","2023-10-05 09:00","2023-10-14 14:00","2023-10-05 09:00","2023-10-14 14:00","연속"]
[418,"대전세종충남","천안","신온양석곡#2 T/L","신온양S/S 154kV 신온양-석곡#2T/L GIS 보통점검","신온양S/S 154kV 신온양-석곡#2T/L GIS 보통점검","2023-10-11 09:00","2023-10-11 18:00","2023-10-11 09:00","2023-10-11 18:00","연속"]
[419,"대전세종충남","천안","아산예산#2 T/L","'22~'23년 천안전력지사 송전협력회사 총액공사","추락방지장치 설치","2023-10-23 07:00","2023-10-25 18:00","취소","취소","매일"]
[420,"대전세종충남","천안","아산예산#1 T/L","'22~'23년 천안전력지사 송전협력회사 총액공사","추락방지장치 설치","2023-10-23 07:00","2023-10-25 18:00","취소","취소","매일"]
[421,"대전세종충남","천안","아산인주#2 T/L","[송전]추락방지장치 설치공사","154kV 아산-인주 #2T/L 추락방지장치 설치","2023-10-21 07:00","2023-10-24 17:00","취소","취소","매일"]
[422,"대전세종충남","천안","아산인주#2 T/L","(9월취소시)아산,인주S/S 아산-인주#2T/L 보호반 교체","(9월취소시)아산,인주S/S 아산-인주#2T/L 보호반 교체","2023-10-16 09:00","2023-10-19 18:00","취소","취소","연속"]
[423,"대전세종충남","천안","아산인주#1 T/L","[송전]추락방지장치 설치공사","154kV 아산-인주 #1T/L 추락방지장치 설치","2023-10-05 07:00","2023-10-10 17:00","취소","취소","매일"]
[424,"대전세종충남","천안","아산S/S SEC CB 65660","아산S/S 154kV 65-66 GIS 초기점검","아산S/S 154kV 65-66GIS 초기점검","2023-10-13 09:00","2023-10-13 18:00","취소","취소","연속"]
[425,"대전세종충남","천안","아산S/S SEC CB 60610","아산S/S 154kV 60-61 GIS 초기점검","아산S/S 154kV 60-61 GIS 초기점검","2023-10-12 09:00","2023-10-12 18:00","취소","취소","연속"]
[426,"대전세종충남","천안","아산인주#1 T/L","(9월취소시)아산,인주S/S 아산-인주#1T/L 보호반 교체","(9월취소시)아산,인주S/S 아산-인주#1T/L 보호반 교체","2023-10-10 09:00","2023-10-13 18:00","취소","취소","연속"]
[427,"대전세종충남","천안","아산합덕#2 T/L","'22~'23년 천안전력지사 송전협력회사 총액공사","추락방지장치 설치","2023-10-26 07:00","2023-10-31 18:00","취소","취소","매일"]
[428,"대전세종충남","천안","아산합덕#1 T/L","'22~'23년 천안전력지사 송전협력회사 총액공사","추락방지장치 설치","2023-10-26 07:00","2023-10-31 18:00","취소","취소","매일"]
[429,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 154kV 온양-풍세#1T/L CB 개폐타임 측정","온양S/S 154kV 온양-풍세#1T/L CB 개폐타임 측정","2023-10-17 09:00","2023-10-17 18:00","취소","취소","연속"]
[430,"대전세종충남","천안","인주불당#1 T/L","[송전]154kV 인주-불당T/L 지장송전선로 이설공사","No.23~26 2기설치, 2기철거, ACSR/AW 410㎟ x 2B x 2C x 0.655km","2023-10-23 07:00","2023-10-28 18:00","취소","취소","연속"]
[431,"대전세종충남","천안","인주불당#2 T/L","[송전]154kV 인주-불당T/L 지장송전선로 이설공사","ACSR/AW 410㎟ x 2B x 2C x 0.655km, No.23~26 2기 설치, 2기 철거","2023-10-29 07:00","2023-11-03 18:00","취소","취소","연속"]
[432,"대전세종충남","천안","장재천안#1 T/L","장재,천안S/S 154kV 장재-천안#1T/L 보호배전반 교체","장재,천안S/S 154kV 장재-천안#1T/L 보호배전반 교체","2023-10-23 09:00","2023-10-27 18:00","취소","취소","연속"]
[433,"대전세종충남","천안","장재천안#2 T/L","장재,천안S/S 154kV 장재-천안#2T/L 보호배전반 교체","장재,천안S/S 154kV 장재-천안#2T/L 보호배전반 교체","2023-10-30 09:00","2023-11-03 18:00","취소","취소","연속"]
[434,"대전세종충남","청양","관창대천#2 T/L","(9월 취소시)청양P/O 변전협력회사 총액공사","154kV 관창-대천#2TL 관창S/S 차단기 조작시험","2023-10-11 09:00","2023-10-11 18:00","2023-10-11 09:00","2023-10-11 18:00","연속"]
[435,"대전세종충남","청양","관창대천#2 T/L","[송전] 2023년 가공송전 순시점검 위탁공사(청양전력)","154kV 관창-대천T/L 전선접속개소 과열 정비 1. 작업내역 : 과열개소 정비 2. 작업개소 : No.25","2023-10-09 08:00","2023-10-09 18:00","2023-10-09 08:00","2023-10-09 18:00","연속"]
[436,"대전세종충남","청양","관창보령TP T/L","청양P/O 변전협력회사 총액공사","154kV 관창-보령화력#T/L 보호반 대체공사 - 관창S/S 차단기 조작시험 - 보령T/P 차단기 조작시험","2023-10-04 10:00","2023-10-06 18:00","취소","취소","연속"]
[437,"대전세종충남","청양","관창대천#1 T/L","(9월 취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","- 관창S/S GIS 보통점검 및 노후보조계전기 교체","2023-10-12 09:00","2023-10-13 18:00","2023-10-12 09:00","2023-10-13 18:00","연속"]
[438,"대전세종충남","청양","보령C/C CB 6100","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","보령C/C 154kV BUS-TIE(6100) GIS 정밀점검","2023-10-16 09:00","2023-10-18 18:00","2023-10-16 09:00","2023-10-18 18:00","연속"]
[439,"대전세종충남","청양","관창보령CC T/L","청양P/O 변전협력회사 총액공사","154kV 관창-보령복합#T/L - 관창S/S 차단기 조작시험 / - 보령T/P 차단기 조작시험","2023-10-10 09:00","2023-10-10 18:00","취소","취소","연속"]
[440,"대전세종충남","청양","보령TP보령CC T/L","(9월취소시)청양P/O 변전협력회사 총액공사","(9월취소시) 154kV 보령복합T/L - 보령T/P 차단기 조작시험","2023-10-12 10:00","2023-10-12 18:00","취소","취소","연속"]
[441,"대전세종충남","청양","보령T/P CB 6100","청양P/O 변전협력회사 총액공사","보령T/P 154kV 6100 BUS TIE 모선보호반 대체 - GIS 보통점검","2023-10-10 09:00","2023-10-13 18:00","2023-10-05 09:00","2023-10-05 18:00","연속"]
[442,"대전세종충남","청양","신서천옥산#1 T/L","[송전] 2023년 가공송전 순시점검 위탁공사(청양전력)","154kV 옥산-서천T/L 전선접속개소 과열 정비 1. 작업내역 : 과열개소 정비 2. 작업개소 : No.5","2023-10-04 08:00","2023-10-05 18:00","2023-10-04 08:00","2023-10-05 18:00","매일"]
[443,"대전세종충남","청양","신서천대천#2 T/L","[송전] 2023년 가공송전 순시점검 위탁공사(청양전력)","154kV 대천-서천T/L 전선접속개소 과열 정비 1. 작업내역 : 과열개소 정비 2. 작업개소 : No.12, 35","2023-10-06 08:00","2023-10-06 18:00","2023-10-06 08:00","2023-10-06 18:00","연속"]
[444,"대전세종충남","청양","신서천옥산#2 T/L","[송전] 2023년 가공송전 순시점검 위탁공사(청양전력)","154kV 대천-서천T/L 전선접속개소 과열 정비 (병가철탑 휴전) 1. 작업내역 : 과열개소 정비 2. 작업개소 : No.12, 35","2023-10-06 08:00","2023-10-06 18:00","2023-10-06 08:00","2023-10-06 18:00","연속"]
[445,"대전세종충남","청양","신서천대천#1 T/L","[송전] 2023년 가공송전 순시점검 위탁공사(청양전력)","154kV 대천-서천T/L 전선접속개소 과열 정비 1. 작업내역 : 과열개소 정비 2. 작업개소 : No.1, 5, 8, 10, 12, 22, 35, 91","2023-10-04 08:00","2023-10-05 18:00","2023-10-04 08:00","2023-10-05 18:00","매일"]
[446,"대전세종충남","청양","옥산장항#1 T/L","[송전] 154kV 옥산-장항#1T/L 철탑 추락방지장치 설치공사(수평)","154kV 옥산-장항#1T/L 철탑 추락방지장치 설치공사(수평) * 주말, 공휴일 제외","2023-10-16 08:00","2023-10-27 18:00","2023-10-16 08:00","2023-10-27 18:00","매일"]
[447,"대전세종충남","청양","청양은하#2 T/L","(9월취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(9월취소시)154kV 청양-은하 #2T/L - 은하S/S GIS 보통점검 및 노후보조계전기 교체 - 청양S/S 차단기 조작시험","2023-10-06 10:00","2023-10-06 18:00","2023-10-06 10:00","2023-10-06 18:00","연속"]
[448,"대전세종충남","청양","동군산장항#2 T/L","[송전] 154kV 옥산-장항#1T/L 철탑 추락방지장치 설치공사(수평)","154kV 옥산-장항#1T/L 철탑 추락방지장치 설치공사(수평) * 4회선 병가구간","2023-10-25 08:00","2023-10-27 18:00","2023-10-25 08:00","2023-10-27 18:00","매일"]
[449,"대전세종충남","청양","청양신풍#2 T/L","[송전] 154kV 청양-신풍#2T/L 철탑 추락방지장치 설치공사(수평)","154kV 청양-신풍#2T/L 철탑 추락방지장치 설치공사(수평)","2023-10-30 08:00","2023-11-03 18:00","2023-10-30 08:00","2023-11-03 18:00","매일"]
[450,"대전세종충남","청양","청양관창#1 T/L","(9월취소시)청양P/O 변전협력회사 총액공사","(9월취소시) 154kV 청양-관창#1T/L - 청양, 관창S/S 차단기 조작시험(양단) - LA 초기점검(A,B,C, 양단)","2023-10-02 08:00","2023-10-02 13:00","2023-10-16 08:00","2023-10-16 18:00","연속"]
[451,"대전세종충남","청양","청양신풍#1 T/L","[송전] 154kV 청양-신풍#1T/L 철탑 추락방지장치 설치공사(수평)","154kV 청양-신풍#1T/L 철탑 추락방지장치 설치공사(수평) * 주말, 공휴일 제외","2023-10-04 08:00","2023-10-13 18:00","2023-10-04 08:00","2023-10-13 18:00","매일"]
[452,"대전세종충남","청양","청양S/S SEC CB 65660","(9월취소시) 청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(9월취소시) 청양S/S 154kV 65-66-0 B/S - 170kV GIS 보통점검 및 노후보조계전기 교체","2023-10-12 10:00","2023-10-13 18:00","2023-10-12 10:00","2023-10-13 18:00","연속"]
[453,"대전세종충남","청양","청양관창#2 T/L","(9월취소시)청양P/O 변전협력회사 총액공사","(9월취소시) 154kV 청양-관창#2T/L - 청양, 관창S/S 차단기 조작시험(양단) - LA 초기점검(A,B,C, 양단)","2023-10-02 13:00","2023-10-02 18:00","2023-10-17 08:00","2023-10-17 18:00","연속"]
[454,"대전세종충남","청양","은하홍성#1 T/L","(9월 취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(9월 취소시)154kV 은하-홍성 #1T/L (양단) - 은하,홍성S/S GIS 보통점검 및 노후보조계전기 교체 - 홍성S/S LA(A,B,C) 보통점검","2023-10-10 08:00","2023-10-11 18:00","2023-10-10 08:00","2023-10-11 18:00","연속"]
[455,"전북","군산","내초SE열병합#1 T/L","SE열병합 154kV 내초-SE열병합#1T/L 차단기 정밀점검","SE열병합 154kV 내초-SE열병합#1T/L 차단기 정밀점검","2023-10-16 09:00","2023-10-17 18:00","2023-10-16 09:00","2023-10-17 18:00","연속"]
[456,"전북","군산","동군산군산CC#2 T/L","군산P/O 차단기 보통점검공사","군산복합 동군산-군산복합#2T/L 차단기 보통점검","2023-10-02 14:00","2023-10-02 18:00","취소","취소","연속"]
[457,"전북","군산","동군산군산CC#1 T/L","군산P/O 차단기 보통점검공사","군산복합 동군산-군산복합#1T/L 차단기 보통점검","2023-10-02 09:00","2023-10-02 14:00","취소","취소","연속"]
[458,"전북","군산","군산S/S #61 BUS","군산S/S 170kV GIS 대체공사(군산-영등#2T/L)","군산S/S 170kV GIS 대체공사(군산-영등#2T/L)","2023-10-12 09:00","2023-10-16 18:00","취소","취소","연속"]
[459,"전북","군산","군산영등#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-10-23 07:00","2023-10-30 18:00","취소","취소","매일"]
[460,"전북","군산","군산이리#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-10-28 07:00","2023-10-30 18:00","취소","취소","매일"]
[461,"전북","군산","군산서군산#1 T/L","군산P/O 차단기 보통점검공사","군산S/S 군산-서군산#1T/L GIS 보통점검","2023-10-30 09:00","2023-10-30 14:00","취소","취소","연속"]
[462,"전북","군산","군산S/S #65 BUS","군산S/S 170kV GIS 대체공사(군산-이리#1T/L 등)","군산S/S 170kV GIS 대체공사(군산-이리#1T/L, 6100, #1PT)","2023-10-09 09:00","2023-10-11 18:00","취소","취소","연속"]
[463,"전북","군산","군산이리#1 T/L","154kV 군산-이리T/L 정밀점검","154kV 군산-이리T/L 정밀점검 ○ 병가구간 동시 휴전신청 (군산-영등, 군산-이리T/L)","2023-10-04 07:30","2023-10-12 18:00","취소","취소","매일"]
[464,"전북","군산","군산이리#2 T/L","154kV 군산-이리T/L 정밀점검","154kV 군산-이리T/L 정밀점검 ○ 병가구간 동시 휴전신청 (군산-영등, 군산-이리T/L)","2023-10-04 07:30","2023-10-12 18:00","취소","취소","매일"]
[465,"전북","군산","군산영등#2 T/L","군산S/S 170kV GIS 대체공사(군산-영등#2T/L)","군산S/S 170kV GIS 대체공사(군산-영등#2T/L)","2023-10-09 09:00","2023-10-24 18:00","취소","취소","연속"]
[466,"전북","군산","군산S/S CB 6100","군산S/S 170kV GIS 대체공사(군산-이리#1T/L 등)","군산S/S 170kV GIS 대체공사(군산-이리#1T/L, 6100, #1PT)","2023-10-09 09:00","2023-11-03 18:00","취소","취소","연속"]
[467,"전북","군산","군산S/S #66 BUS","군산S/S 170kV GIS 대체공사(군산-영등#2T/L)","군산S/S 170kV GIS 대체공사(군산-영등#2T/L)","2023-10-09 09:00","2023-10-11 18:00","취소","취소","연속"]
[468,"전북","군산","군산S/S CB 6100","군산S/S 170kV GIS 대체공사(군산-이리#1T/L 등)","군산S/S 170kV GIS 대체공사(군산-이리#1T/L, 6100, #1PT)","2023-10-09 09:00","2023-11-03 18:00","취소","취소","연속"]
[469,"전북","군산","군산이리#1 T/L","군산S/S 170kV GIS 대체공사(군산-이리#1T/L 등)","군산S/S 170kV GIS 대체공사(군산-이리#1T/L, 6100, #1PT)","2023-10-09 09:00","2023-11-03 18:00","취소","취소","연속"]
[470,"전북","군산","군산S/S #60 BUS","군산S/S 170kV GIS 대체공사(군산-이리#1T/L 등)","군산S/S 170kV GIS 대체공사(군산-이리#1T/L, 6100, #1PT)","2023-10-12 09:00","2023-10-21 18:00","취소","취소","연속"]
[471,"전북","군산","군산영등#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-10-12 07:00","2023-10-17 18:00","취소","취소","매일"]
[472,"전북","군산","군산이리#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-10-12 07:00","2023-10-19 18:00","취소","취소","매일"]
[473,"전북","군산","군산서군산#2 T/L","군산P/O 차단기 보통점검공사","군산S/S 군산-서군산#2T/L GIS 보통점검","2023-10-30 14:00","2023-10-30 18:00","취소","취소","연속"]
[474,"전북","군산","군산동군산#2 T/L","154kV 군산-동군산T/L 정밀점검","154kV 군산-동군산T/L 정밀점검","2023-10-23 07:30","2023-10-31 18:00","취소","취소","매일"]
[475,"전북","군산","군산동군산#1 T/L","154kV 동군산S/S 6100BUS-TIE 차단기 정밀점검","동군산S/S 6100BUS-TIE 차단기 정밀점검","2023-10-20 16:00","2023-10-20 17:00","2023-10-20 16:00","2023-10-20 17:00","연속"]
[476,"전북","군산","군산동군산#1 T/L","154kV 군산-동군산T/L 정밀점검","154kV 군산-동군산T/L 정밀점검","2023-10-23 07:30","2023-10-31 18:00","취소","취소","매일"]
[477,"전북","군산","영등낭산#2 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2023-10-02 07:00","2023-10-02 18:00","취소","취소","연속"]
[478,"전북","군산","영등낭산#1 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2023-10-04 07:00","2023-10-13 18:00","취소","취소","연속"]
[479,"전북","군산","영등낭산#2 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2023-10-16 07:00","2023-10-24 18:00","취소","취소","연속"]
[480,"전북","군산","영등낭산#1 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-10-24 07:00","2023-10-24 18:00","취소","취소","매일"]
[481,"전북","군산","영등낭산#2 T/L","154kV 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2023-10-25 07:00","2023-10-27 18:00","취소","취소","매일"]
[482,"전북","군산","이리백산#2 T/L","154kV 백산-김제T/L 정밀점검","154kV 백산-김제T/L 정밀점검 ○ 병가구간 동시 휴전신청 (백산-김제, 이리-백산T/L)","2023-10-16 07:30","2023-10-20 18:00","취소","취소","매일"]
[483,"전북","군산","이리백산#1 T/L","154kV 백산-김제T/L 정밀점검","154kV 백산-김제T/L 정밀점검 ○ 병가구간 동시 휴전신청 (백산-김제, 이리-백산T/L)","2023-10-16 07:30","2023-10-20 18:00","취소","취소","매일"]
[484,"전북","군산","영등팔봉#2 T/L","군산P/O LA,CVT 보통점검공사","군산P/O LA,CVT 보통점검공사","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[485,"전북","군산","영등팔봉#1 T/L","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 차단기 정밀점검","2023-10-24 17:00","2023-10-24 18:00","2023-10-24 17:00","2023-10-24 18:00","연속"]
[486,"전북","군산","팔봉S/S CB 6100","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀점검","2023-10-24 17:00","2023-10-24 18:00","2023-10-24 17:00","2023-10-24 18:00","연속"]
[487,"전북","군산","팔봉S/S #60 BUS","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀 점검","팔봉S/S 154kV #4M.Tr 1차 GIS 정밀점검","2023-10-24 17:00","2023-10-24 18:00","2023-10-24 17:00","2023-10-24 18:00","연속"]
[488,"전북","김제","담양김제 T/L","김제S/S 170kV 담양-김제T/L 보통점검공사","김제S/S 170kV 담양-김제T/L 보통점검공사","2023-10-30 08:30","2023-10-30 18:00","취소","취소","연속"]
[489,"전북","김제","백산김제#2 T/L","154kV 백산-김제T/L 정밀점검","154kV 백산-김제T/L 정밀점검 ○ 병가구간 동시 휴전신청 (백산-김제, 이리-백산T/L)","2023-10-16 07:30","2023-10-20 18:00","취소","취소","매일"]
[490,"전북","김제","백산김제#1 T/L","154kV 백산-김제T/L 정밀점검","154kV 백산-김제T/L 정밀점검 ○ 병가구간 동시 휴전신청 (백산-김제, 이리-백산T/L)","2023-10-16 07:30","2023-10-20 18:00","취소","취소","매일"]
[491,"전북","김제","김제S/S #1 EM.Tr CB","김제 FR-ESS 정밀점검","김제 FR-ESS 정밀점검","2023-10-10 09:00","2023-10-20 18:00","2023-10-10 09:00","2023-10-20 18:00","연속"]
[492,"전북","김제","신김제S/S #1 EM.Tr CB","신김제 FR-ESS 정밀점검","신김제 FR-ESS 정밀점검","2023-10-23 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-10-27 18:00","연속"]
[493,"전북","김제","신김제남전주#2 T/L","신김제S/S 170kV #61-#62SEC GIS 정밀점검공사","신김제S/S 170kV #61-#62SEC GIS 정밀점검공사","2023-10-05 15:00","2023-10-05 16:00","2023-10-06 15:00","2023-10-06 16:00","연속"]
[494,"전북","김제","신김제S/S SEC CB 61620","신김제S/S 170kV #61-#62SEC GIS 정밀점검공사","신김제S/S 170kV #61-#62SEC GIS 정밀점검공사","2023-10-04 08:30","2023-10-06 18:00","2023-10-04 08:30","2023-10-06 18:00","연속"]
[495,"전북","김제","신김제남전주#1 T/L","신김제S/S 170kV #61-#62SEC GIS 정밀점검공사","신김제S/S 170kV #61-#62SEC GIS 정밀점검공사","2023-10-04 13:00","2023-10-04 14:00","2023-10-05 13:00","2023-10-05 14:00","연속"]
[496,"전북","김제","신김제정공#1 T/L","신김제S/S 170kV #1EM.Tr 1차 GIS 정밀점검공사","신김제S/S 170kV #1EM.Tr 1차 GIS 정밀점검공사","2023-10-27 15:00","2023-10-27 16:00","2023-10-24 15:00","2023-10-24 16:00","연속"]
[497,"전북","김제","신김제S/S SEC CB 60610","신김제S/S 170kV #61-#62SEC GIS 정밀점검공사","신김제S/S 170kV #61-#62SEC GIS 정밀점검공사","2023-10-04 08:30","2023-10-05 13:00","2023-10-04 08:30","2023-10-05 13:00","연속"]
[498,"전북","김제","정공정주#2 T/L","정공S/S 170kV 정공-정주#2T/L GIS 보통점검공사","정공S/S 170kV 정공-정주#2T/L GIS 보통점검공사","2023-10-20 09:00","2023-10-20 18:00","취소","취소","연속"]
[499,"전북","김제","신김제정공#1 T/L","정공S/S 170kV 신김제-정공#1T/L 정밀점검공사","정공S/S 170kV 신김제-정공#1T/L 정밀점검공사","2023-10-31 08:30","2023-11-01 18:00","취소","취소","연속"]
[500,"전북","김제","김제칠보HP T/L","칠보H/P 170kV 김체-칠보수력T/L GIS 정밀점검공사","칠보H/P 170kV 김체-칠보수력T/L GIS 정밀점검공사","2023-10-16 08:30","2023-10-17 18:00","취소","취소","연속"]
[501,"전북","김제","칠보H/P CB 6100","칠보H/P 170kV #1BUS-TIE GIS 정밀점검공사","칠보H/P 170kV #1BUS-TIE GIS 정밀점검공사","2023-10-25 08:30","2023-10-26 18:00","2023-10-25 08:30","2023-10-26 18:00","연속"]
[502,"전북","김제","김제칠보HP T/L","칠보H/P 170kV #1BUS-TIE GIS 정밀점검공사","칠보H/P 170kV #1BUS-TIE GIS 정밀점검공사","2023-10-26 15:00","2023-10-26 16:00","2023-10-26 15:00","2023-10-26 16:00","연속"]
[503,"전북","김제","김제칠보HP T/L","칠보H/P 170kV #1M.Tr 1차 GIS 정밀점검공사","칠보H/P 170kV #1M.Tr 1차 GIS 정밀점검공사","2023-10-11 15:00","2023-10-11 16:00","2023-10-11 15:00","2023-10-11 16:00","연속"]
[504,"전북","김제","칠보H/P CB 6100","칠보H/P 170kV #1M.Tr 1차 GIS 정밀점검공사","칠보H/P 170kV #1M.Tr 1차 GIS 정밀점검공사","2023-10-11 15:00","2023-10-11 16:00","2023-10-11 15:00","2023-10-11 16:00","연속"]
[505,"전북","김제","김제칠보HP T/L","칠보H/P 170kV #2M.Tr 1차 GIS 정밀점검공사","칠보H/P 170kV #2M.Tr 1차 GIS 정밀점검공사","2023-10-13 15:00","2023-10-13 16:00","2023-10-13 15:00","2023-10-13 16:00","연속"]
[506,"전북","김제","정공칠보HP T/L","칠보H/P 170kV 정공-칠보수력T/L GIS 정밀점검공사","칠보H/P 170kV 정공-칠보수력T/L GIS 정밀점검공사","2023-10-18 08:30","2023-10-19 18:00","취소","취소","연속"]
[507,"전북","김제","칠보H/P CB 6100","칠보H/P 170kV #2M.Tr 1차 GIS 정밀점검공사","칠보H/P 170kV #2M.Tr 1차 GIS 정밀점검공사","2023-10-13 15:00","2023-10-13 16:00","2023-10-13 15:00","2023-10-13 16:00","연속"]
[508,"전북","직할","무주진안 T/L","'22~'23년 전북직할 가공송전 협력회사 총액공사","□ 피뢰기 설치 : 116기 348set (무주-진안T/L 회선) □ 설치대상 ○ 154kV 무주-진안T/L No.105~175 (71기) ○ 154kV 무주분기T/L No.1~45 (45기)","2023-10-16 08:00","2023-10-27 18:00","취소","취소","매일"]
[509,"전북","직할","북전주봉동#1 T/L","154kV 북전주S/S 디지털 혼용시스템 설치공사","○ 제어케이블 이설공사(RTU → 디지털 혼용장치반)","2023-10-04 09:00","2023-10-04 18:00","2023-10-04 09:00","2023-10-04 18:00","연속"]
[510,"전북","직할","북전주봉동#2 T/L","154kV 북전주S/S 디지털 혼용시스템 설치공사","○ 제어케이블 이설공사(RTU → 디지털 혼용장치반)","2023-10-05 09:00","2023-10-05 18:00","2023-10-05 09:00","2023-10-05 18:00","연속"]
[511,"전북","직할","신남원S/S #2 BUS","신남원S/S ESS 건설공사","- 154kV GIS 9Bay 증설 - 154kV M.Tr 60MVA 6bank 설치 - 모선보호반 추가 및 제어케이블 포설/결선 등","2023-10-10 09:30","2023-10-27 15:00","2023-10-10 09:30","2023-10-27 15:00","연속"]
[512,"전북","직할","전주서곡#2 T/L","전주-서곡#2T/L 보호반 대체공사(보통점검포함)","전주-서곡#2T/L 보호반 대체공사(보통점검포함)","2023-10-04 14:00","2023-10-06 18:00","2023-10-14 09:00","2023-10-15 18:00","연속"]
[513,"전북","직할","전주서곡#1 T/L","전주-서곡#1T/L 보호반 대체공사(보통점검포함)","전주-서곡#1T/L 보호반 대체공사(보통점검포함)","2023-10-02 09:00","2023-10-04 14:00","2023-10-07 09:00","2023-10-08 18:00","연속"]
[514,"광주전남","강진","완도강진 T/L","154kV 강진-남창T/L 용량증대 전선교체공사","ㅇ용량증대 직결해제 작업 - 154kV 강진-남창 #1T/L No.128~ 남창S/S S/T - 154kV 남창-완도 #2T/L No.1~남창S/S S/T ㅇ시공사 :삼부토건(주), 대동전기(주) ㅇ작업내용 : 용량증대 전선교체 직결해제","2023-10-04 07:00","2023-10-07 18:00","2023-10-02 07:00","2023-10-06 18:00","연속"]
[515,"광주전남","강진","강진남창#2 T/L","154kV 강진-남창T/L 용량증대 전선교체공사","ㅇ구간 : 용량증대 전선교체 작업 - 154kV 강진-남창 #2T/L No.1~128 ㅇ시공사 :삼부토건(주), 대동전기(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 520SQ로 전량교체) - 수직,수평와이어 설치","2023-10-09 07:00","2023-11-30 18:00","2023-10-10 07:00","2023-11-30 18:00","연속"]
[516,"광주전남","강진","나주금천#1 T/L","세니온 보호계전기 일제 성능개선 시행(나주,금천)","세니온 보호계전기 일제 성능개선 시행 - 나주S/S 나주-왕곡#1,2T/L - 보호반 IED 펌웨어 업데이트","2023-10-19 10:00","2023-10-19 14:00","취소","취소","연속"]
[517,"광주전남","강진","나주금천#2 T/L","세니온 보호계전기 일제 성능개선 시행(나주,금천)","세니온 보호계전기 일제 성능개선 시행 - 나주S/S 나주-왕곡#1,2T/L - 보호반 IED 펌웨어 업데이트","2023-10-19 14:00","2023-10-19 18:00","취소","취소","연속"]
[518,"광주전남","강진","남창해남CS#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","4회선 구간 추락방지장치 설치 및 고정형 폴리머 점퍼지지애자 교체공사 추락방지- 2~14호, 애자교체 - 2,14,ST호","2023-10-10 07:00","2023-10-12 18:00","취소","취소","매일"]
[519,"광주전남","강진","남창완도#1 T/L","154kV 남창S/S GIS화 공사(전문)","강진-남창#2T/L, 남창-완도#1T/L GIS 챔버 복도체화 공사","2023-10-04 14:00","2023-10-06 18:00","취소","취소","연속"]
[520,"광주전남","강진","강진남창#2 T/L","154kV 남창S/S GIS화 공사(전문)","강진-남창#2T/L, 남창-완도#1T/L GIS 챔버 복도체화 공사","2023-10-02 09:00","2023-10-04 14:00","취소","취소","연속"]
[521,"광주전남","강진","신강진대불#1 T/L","23년도 강진전력지사 GIS 보통점검 공사","신강진S/S 신강진-대불 #1T/L GIS 보통점검","2023-10-16 09:00","2023-10-16 18:00","2023-10-16 09:00","2023-10-16 14:00","연속"]
[522,"광주전남","강진","신강진대불#2 T/L","23년도 강진전력지사 GIS 보통점검 공사","신강진S/S 신강진-대불 #2T/L GIS 보통점검","2023-10-16 09:00","2023-10-16 18:00","2023-10-16 14:00","2023-10-16 18:00","연속"]
[523,"광주전남","강진","서제주진도HVDC(2연계선) #1 Pole CB","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) #1Pole 연차점검","2023-10-04 09:00","2023-10-18 18:00","2023-10-04 09:00","2023-10-18 18:00","연속"]
[524,"광주전남","강진","진도C/S P2+FF2 CB 6479","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) Bipole 연차점검","2023-10-09 09:00","2023-10-18 18:00","2023-10-09 09:00","2023-10-18 18:00","연속"]
[525,"광주전남","강진","서제주진도HVDC(2연계선) #1 Pole CB","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) Bipole 연차점검","2023-10-09 09:00","2023-10-18 18:00","2023-10-09 09:00","2023-10-18 18:00","연속"]
[526,"광주전남","강진","진도C/S P1+FF1 CB 6179","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) Bipole 연차점검","2023-10-09 09:00","2023-10-18 18:00","2023-10-09 09:00","2023-10-18 18:00","연속"]
[527,"광주전남","강진","진도C/S P2+FF1 CB 6379","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) Bipole 연차점검","2023-10-09 09:00","2023-10-18 18:00","2023-10-09 09:00","2023-10-18 18:00","연속"]
[528,"광주전남","강진","진도C/S P1+FF2 CB 6279","'22~'23년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) Bipole 연차점검","2023-10-09 09:00","2023-10-18 18:00","2023-10-09 09:00","2023-10-18 18:00","연속"]
[529,"광주전남","강진","해남진도#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","4회선 병가구간 추락방지장치 설치 (해남진도 2,3호)","2023-10-18 07:00","2023-10-18 18:00","2023-10-18 07:00","2023-10-18 18:00","매일"]
[530,"광주전남","강진","해남해남CS#2 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","추락방지장치 설치공사 79기","2023-10-10 07:00","2023-10-18 18:00","취소","취소","매일"]
[531,"광주전남","광주","계림S/S CB 6200","23년 광주 변전협력회사 총액공사","6200 BUS-TIE 누기개소 조치(#2DS부)","2023-10-06 09:00","2023-10-06 18:00","2023-10-06 09:00","2023-10-06 18:00","연속"]
[532,"광주전남","광주","계림충장#2 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-10-09 09:00","2023-11-10 18:00","취소","취소","연속"]
[533,"광주전남","광주","계림S/S CB 6100","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-10-09 09:00","2023-11-10 18:00","취소","취소","연속"]
[534,"광주전남","광주","계림승주#1 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","-BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #65BUS 신설분 및 BAY 무부하 가압","2023-10-19 13:00","2023-10-20 18:00","취소","취소","연속"]
[535,"광주전남","광주","계림승주#1 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","-BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #60BUS 신설분 무부하 가압","2023-10-20 13:00","2023-10-21 13:00","취소","취소","연속"]
[536,"광주전남","광주","계림남광주 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-10-09 09:00","2023-11-10 18:00","취소","취소","연속"]
[537,"광주전남","광주","정공담양 T/L","2022~23년 광주전력지사 변전협력회사 총액공사","담양S/S 154kV 정공-담양T/L LA 리드선 장력조절","2023-10-06 09:00","2023-10-06 18:00","취소","취소","연속"]
[538,"광주전남","광주","신광주계림#2 T/L","'22~23년 광주 변전협력회사 총액공사","신광주, 계림S/S 신광주-계림#2T/L PNL 대체","2023-10-30 09:00","2023-11-03 18:00","취소","취소","연속"]
[539,"광주전남","광주","신광주일곡#1 T/L","154kV 신광주-일곡T/L C/T이설공사","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-10-21 07:00","2023-10-22 18:00","취소","취소","연속"]
[540,"광주전남","광주","신광주S/S #66 BUS","154kV 신광주-일곡T/L C/T이설공사 무부하가압","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-10-15 13:00","2023-10-15 18:00","취소","취소","연속"]
[541,"광주전남","광주","신광주순창#2 T/L","154kV 신광주-일곡T/L C/T이설공사 무부하가압","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-10-15 13:00","2023-10-15 18:00","취소","취소","연속"]
[542,"광주전남","광주","신광주S/S #65 BUS","154kV 신광주-일곡T/L C/T이설공사 무부하가압","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-10-22 13:00","2023-10-22 18:00","취소","취소","연속"]
[543,"광주전남","광주","신광주순창#1 T/L","154kV 신광주-일곡T/L C/T이설공사 무부하가압","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-10-22 13:00","2023-10-22 18:00","취소","취소","연속"]
[544,"광주전남","광주","신광주일곡#1 T/L","154kV 신광주-일곡T/L C/T이설공사","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-10-07 07:00","2023-10-08 18:00","2023-10-28 07:00","2023-10-29 18:00","연속"]
[545,"광주전남","광주","신광주일곡#2 T/L","154kV 신광주-일곡T/L C/T이설공사","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-10-14 07:00","2023-10-15 18:00","취소","취소","연속"]
[546,"광주전남","광주","신화순매월#2 T/L","'22~23년 광주 변전협력회사 총액공사","신화순-매월#2T/L LA, CVT 보통점검","2023-10-10 14:00","2023-10-10 18:00","취소","취소","연속"]
[547,"광주전남","광주","신화순나주#1 T/L","광주전력지사 세니온 보호계전기 일제 성능개선 시행","신화순-나주#1,2T/L 세니온 보호계전기 성능개선","2023-10-26 09:00","2023-10-26 14:00","취소","취소","연속"]
[548,"광주전남","광주","신화순매월#1 T/L","'22~23년 광주 변전협력회사 총액공사","신화순-매월#1T/L LA 보통점검","2023-10-10 09:00","2023-10-10 14:00","취소","취소","연속"]
[549,"광주전남","광주","신화순나주#2 T/L","광주전력지사 세니온 보호계전기 일제 성능개선 시행","신화순-나주#1,2T/L 세니온 보호계전기 성능개선","2023-10-26 14:00","2023-10-26 18:00","취소","취소","연속"]
[550,"광주전남","광주","하남장성#2 T/L","'22~23년 광주 변전협력회사 총액공사","하남-장성#2T/L LA 보통점검","2023-10-04 14:00","2023-10-04 18:00","취소","취소","연속"]
[551,"광주전남","광주","하남장성#1 T/L","'22~23년 광주 변전협력회사 총액공사","하남-장성#1T/L LA 보통점검","2023-10-04 09:00","2023-10-04 14:00","취소","취소","연속"]
[552,"광주전남","목포","남악북항#1 T/L","북항S/S 154kV 장기사용 GIS 교체공사(2차)","- 남악-북항#1T/L GIS 교체","2023-10-04 09:00","2023-11-03 18:00","2023-10-04 09:00","2023-11-03 18:00","연속"]
[553,"광주전남","순천","서순천주암HP T/L","22-23년 순천전력지사 변전협력회사 총액공사","GIS 차단기 조작시험(즉시가압 가능)","2023-10-19 09:00","2023-10-19 18:00","취소","취소","연속"]
[554,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.1~171호, 87기","2023-10-04 08:00","2023-10-13 18:00","2023-10-04 08:00","2023-10-13 18:00","매일"]
[555,"광주전남","순천","계림승주#2 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - No.2~9호(4회선)","2023-10-06 08:00","2023-10-06 18:00","2023-10-06 08:00","2023-10-06 18:00","연속"]
[556,"광주전남","순천","승주주암HP T/L","22-23년 순천전력지사 변전협력회사 총액공사","GIS 보통점검 및 상시여자보조계전기 교체(즉시가압 가능)","2023-10-18 09:00","2023-10-18 18:00","취소","취소","연속"]
[557,"광주전남","순천","호남TP여수TP#1 T/L","순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검(즉시가압 불가)","2023-10-10 09:00","2023-10-11 18:00","취소","취소","연속"]
[558,"광주전남","순천","여수TP용성#1 T/L","가공송전 위탁공사 정밀점검(여수TP-용성#1 T/L)","가공송전 위탁공사 정밀점검(여수TP-용성#1 T/L) : 4기","2023-10-23 09:00","2023-10-23 18:00","취소","취소","연속"]
[559,"광주전남","순천","여수TP화치#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","PNL 대체(즉시가압 불가)","2023-10-16 09:00","2023-10-20 18:00","2023-10-16 09:00","2023-10-20 18:00","연속"]
[560,"광주전남","순천","호남TP여수TP#2 T/L","순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검(즉시가압 불가)","2023-10-12 09:00","2023-10-13 18:00","취소","취소","연속"]
[561,"광주전남","순천","여수TP여천#1 T/L","여수TP-여천#1T/L PNL 43PDA 교체 공사","불량 43PDA 교체(즉시가압 가능)","2023-10-28 10:00","2023-10-28 14:00","취소","취소","연속"]
[562,"광주전남","순천","여수TP여천#2 T/L","가공송전 위탁공사 정밀점검(여수TP-여천#2 T/L)","가공송전 위탁공사 정밀점검(여수TP-여천#2 T/L) : 8기","2023-10-26 08:00","2023-10-26 18:00","취소","취소","연속"]
[563,"광주전남","순천","여수TP여천#1 T/L","순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검(즉시가압 불가)","2023-10-25 09:00","2023-10-27 18:00","취소","취소","연속"]
[564,"광주전남","순천","여수TP여천#1 T/L","가공송전 위탁공사 정밀점검(여수TP-여천#1 T/L)","가공송전 위탁공사 정밀점검(여수TP-여천#1 T/L) : 8기","2023-10-25 08:00","2023-10-25 18:00","취소","취소","연속"]
[565,"광주전남","순천","여수TP용성#2 T/L","가공송전 위탁공사 정밀점검(여수TP-용성#2 T/L)","가공송전 위탁공사 정밀점검(여수TP-용성#2 T/L) : 4기","2023-10-24 09:00","2023-10-24 18:00","취소","취소","연속"]
[566,"광주전남","순천","여천호남TP#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","GIS 차단기 조작시험(즉시가압 가능)","2023-10-05 09:00","2023-10-05 14:00","취소","취소","연속"]
[567,"광주전남","순천","여천호남TP#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","GIS 차단기 조작시험(즉시가압 가능)","2023-10-05 14:00","2023-10-05 18:00","취소","취소","연속"]
[568,"광주전남","순천","용성여수산단#2 T/L","가공송전 위탁공사 정밀점검(용성여수산단#2 T/L)","가공송전 위탁공사 정밀점검(용성여수산단#2 T/L) : 16기","2023-10-24 09:00","2023-10-24 18:00","취소","취소","연속"]
[569,"광주전남","순천","용성여수산단#1 T/L","가공송전 위탁공사 정밀점검(용성여수산단#1 T/L)","가공송전 위탁공사 정밀점검(용성여수산단#1 T/L) : 16기","2023-10-23 09:00","2023-10-23 18:00","취소","취소","연속"]
[570,"광주전남","순천","순천율촌#2 T/L","가공송전 위탁공사 정밀점검(광양-율촌CC T/L) 11기","가공송전 위탁공사 정밀점검(광양-율촌CC T/L) 11기 -율촌CC분기 4회선 병가 구간 휴전(순천-율촌#2)","2023-10-11 09:00","2023-10-11 18:00","취소","취소","연속"]
[571,"광주전남","순천","순천율촌#1 T/L","가공송전 위탁공사 정밀점검(율촌CC-여수TP T/L) 11기","가공송전 위탁공사 정밀점검(율촌CC-여수TP T/L) 11기 -율촌CC분기 4회선 병가 구간 휴전(순천-율촌#1)","2023-10-04 09:00","2023-10-04 18:00","취소","취소","연속"]
[572,"광주전남","순천","율촌여수산단#2 T/L","가공송전 위탁공사 정밀점검(율촌여수산단#2 T/L) : 51기","가공송전 위탁공사 정밀점검(율촌여수산단#2 T/L) : 51기","2023-10-10 09:00","2023-10-10 18:00","취소","취소","매일"]
[573,"광주전남","순천","율촌여수산단#1 T/L","가공송전 위탁공사 정밀점검(율촌여수산단#1 T/L)","가공송전 위탁공사 정밀점검(율촌여수산단#1 T/L) : 51기","2023-10-09 09:00","2023-10-09 18:00","취소","취소","매일"]
[574,"광주전남","순천","율촌화치#2 T/L","순천전력지사 170kV GIS 정밀점검공사","GIS 유압유 레벨 조정(즉시가압 가능)","2023-10-04 10:00","2023-10-04 14:00","2023-10-04 10:00","2023-10-04 14:00","연속"]
[575,"광주전남","순천","순천율촌#2 T/L","순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검(즉시가압 불가)","2023-10-05 09:00","2023-10-06 18:00","2023-10-23 09:00","2023-10-24 18:00","연속"]
[576,"광주전남","순천","호남TP여수TP#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","LA 대체(즉시가압 가능)","2023-10-11 09:00","2023-10-11 18:00","취소","취소","연속"]
[577,"광주전남","순천","호남TP여수TP#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","LA 대체(즉시가압 가능)","2023-10-12 09:00","2023-10-12 18:00","취소","취소","연속"]
[578,"광주전남","직할","농성화정#1 T/L","'23년 직할 170kV GIS 정밀 및 보통점검 공사","○ 농성S/S 농성-화정 #1,2T/L 170kV GIS 보통점검 - 휴일작업 없음 ○ 농성-화정#1T/L 송전선로 보호반 임시점검 - 후비보호 COM Fail 해소","2023-10-10 09:00","2023-10-10 18:00","취소","취소","연속"]
[579,"광주전남","직할","농성화정#2 T/L","'23년 직할 170kV GIS 정밀 및 보통점검 공사","○ 농성S/S 농성-화정 #1,2T/L 170kV GIS 보통점검 - 휴일작업 없음","2023-10-11 09:00","2023-10-11 18:00","취소","취소","연속"]
[580,"광주전남","직할","신화순매월#1 T/L","'23년 직할 170kV GIS 정밀 및 보통점검 공사","○ 매월S/S 신화순-매월 #1,2T/L 170kV GIS 보통점검 - 휴일작업 없음","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[581,"광주전남","직할","신화순매월#2 T/L","'23년 직할 170kV GIS 정밀 및 보통점검 공사","○ 매월S/S 신화순-매월 #1,2T/L 170kV GIS 보통점검 - 휴일작업 없음","2023-10-19 09:00","2023-10-19 18:00","2023-10-19 09:00","2023-10-19 18:00","연속"]
[582,"광주전남","직할","수완S/S 수완열병합 ST CB","'23년 직할 170kV GIS 정밀 및 보통점검 공사","○ 수완S/S STG T/L 170kV GIS 정밀점검","2023-10-29 09:00","2023-10-31 18:00","2023-10-29 09:00","2023-10-31 18:00","연속"]
[583,"광주전남","직할","덕림평동#2 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (덕림-평동T/L 1~62호, 하남-덕림 8~40호 병가, 평동-왕곡 1~3호 병가)","2023-10-05 08:00","2023-10-18 18:00","취소","취소","연속"]
[584,"광주전남","직할","평동왕곡#2 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (평동-왕곡T/L 1~94호, 덕림-평동 59~61호 병가)","2023-10-18 08:00","2023-11-02 18:00","취소","취소","연속"]
[585,"광주전남","직할","하남덕림#1 T/L","22~23년 직할 가공송전 협력회사 총액공사(수평 추락방지장치 설치)","수평 추락방지장치 설치 (하남-덕림 1~40호, 덕림-평동T/L 1~33호 병가)","2023-10-05 08:00","2023-10-13 18:00","취소","취소","연속"]
[586,"대구","달성","강창성서#1 T/L","2022~23년 달성전력지사 가공송전협력회사 총액공사","폴리머 점퍼지지애자 교체공사(성서-달성#2T/L 1호 병가철탑 작업)","2023-10-24 07:00","2023-10-24 18:00","2023-10-24 07:00","2023-10-24 18:00","연속"]
[587,"대구","달성","논공현풍#1 T/L","[안전확보]154kV 논공-현풍-유가T/L OPGW 광코어 용량 증설공사","[안전확보]○ 논공-현풍-유가T/L OPGW 광코어 증설 - 현풍분기T/L OPGW 증설","2023-10-11 07:00","2023-10-11 18:00","2023-10-11 07:00","2023-10-11 18:00","연속"]
[588,"대구","달성","왜관다사#1 T/L","2023년 가공송전 순시점검 위탁공사","154k 왜관-다사T/L 초기점검","2023-10-25 08:00","2023-10-25 18:00","2023-10-25 08:00","2023-10-25 18:00","연속"]
[589,"대구","달성","왜관다사#2 T/L","2023년 가공송전 순시점검 위탁공사","154k 왜관-다사T/L 초기점검","2023-10-26 08:00","2023-10-26 18:00","2023-10-26 08:00","2023-10-26 18:00","연속"]
[590,"대구","달성","달서와룡#2 T/L","달서S/S 장기사용 170kV GIS 교체공사","달서S/S 장기사용 170kV GIS 교체공사","2023-10-10 09:00","2023-10-27 18:00","2023-10-25 09:00","2023-11-10 18:00","연속"]
[591,"대구","달성","달서와룡#1 T/L","달서S/S 장기사용 170kV GIS 교체공사","달서S/S 장기사용 170kV GIS 교체공사","2023-10-30 09:00","2023-11-10 18:00","취소","취소","연속"]
[592,"대구","달성","구지서구지#1 T/L","154kV 서구지S/S 엘앤에프 신규수용공사","무부하가압","2023-10-04 09:00","2023-10-06 18:00","2023-10-04 09:00","2023-10-06 18:00","연속"]
[593,"대구","달성","성서달성#2 T/L","2022~23년 달성전력지사 가공송전협력회사 총액공사","폴리머 점퍼지지애자 교체공사","2023-10-24 07:00","2023-10-24 18:00","2023-10-24 07:00","2023-10-24 18:00","연속"]
[594,"대구","달성","성서달성#1 T/L","2022~23년 달성전력지사 가공송전협력회사 총액공사","폴리머 점퍼지지애자 교체공사","2023-10-23 07:00","2023-10-23 18:00","2023-10-23 07:00","2023-10-23 18:00","연속"]
[595,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체(TEST선로)","○ #1BUS 무부하가압(2H)","2023-10-26 14:00","2023-10-26 16:00","2023-10-28 14:00","2023-10-28 16:00","연속"]
[596,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체(TEST선로)","○ #2BUS 무부하가압(24H)","2023-10-24 16:00","2023-10-25 16:00","2023-10-26 16:00","2023-10-27 16:00","연속"]
[597,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체(TEST선로)","○ #1BUS 무부하가압(24H)","2023-10-16 16:00","2023-10-17 16:00","2023-10-17 16:00","2023-10-18 16:00","연속"]
[598,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체(TEST선로)","○ #2BUS 무부하가압(2H)","2023-10-06 14:00","2023-10-06 16:00","2023-10-07T14:00:00","2023-10-07T16:00:00","연속"]
[599,"대구","직할","공평서침산 T/L","서침산S/S 공평-서침산T/L GIS 보통점검","서침산S/S 공평-서침산T/L GIS 보통점검","2023-10-10 09:30","2023-10-10 18:00","2023-10-10 09:30","2023-10-10 18:00","연속"]
[600,"대구","직할","효목안심#2 T/L","효목S/S 효목-안심 #2T/L GIS 보통점검","효목S/S 효목-안심 #2T/L GIS 보통점검","2023-10-31 09:30","2023-10-31 18:00","2023-10-31 09:30","2023-10-31 18:00","연속"]
[601,"대구","직할","효목안심#1 T/L","효목S/S 효목-안심 #1T/L GIS 보통점검","효목S/S 효목-안심 #1T/L GIS 보통점검","2023-10-30 09:30","2023-10-30 18:00","2023-10-30 09:30","2023-10-30 18:00","연속"]
[602,"대구","칠곡","관음구암#1 T/L","관음S/S 154kV GIS 대체공사","관음S/S 154kV GIS 대체공사(1차) -대상: 관음-구암#1, #1M.Tr 1차, Sh.C","2023-10-11 09:00","2023-11-02 18:00","2023-10-11 09:00","2023-11-02 18:00","연속"]
[603,"대구","칠곡","관음구암#2 T/L","관음S/S 154kV GIS 대체공사(안전확보)","관음S/S 154kV GIS 대체공사(1차) -대상: 관음-구암#1, #1M.Tr 1차, Sh.C","2023-10-25 09:00","2023-10-26 18:00","2023-10-25 09:00","2023-10-26 18:00","연속"]
[604,"대구","칠곡","관음구암#2 T/L","도남지구 지중화관련 OPGW 이설 및 광케이블 시설공사","[안전확보] 도남지구 지중화관련 관음-구암T/L OPGW 증설 ○ 작업구간 : 관음-구암T/L No.10~22호","2023-10-16 07:00","2023-10-21 18:00","2023-10-25 09:00","2023-10-26 18:00","연속"]
[605,"대구","칠곡","관음S/S #1 Sh.C CB","관음S/S 154kV GIS 대체공사","관음S/S 154kV GIS 대체공사(1차) -대상: 관음-구암#1, #1M.Tr 1차, Sh.C","2023-10-11 09:00","2023-11-02 18:00","2023-10-11 09:00","2023-11-02 18:00","연속"]
[606,"대구","칠곡","남구미광평#1 T/L","22-23년 칠곡전력 가공송전협력 총액공사","수평 추락방지장치 설치","2023-10-30 07:30","2023-10-31 18:00","2023-10-30 07:30","2023-10-31 18:00","연속"]
[607,"대구","칠곡","남구미광평#2 T/L","22-23년 칠곡전력 가공송전협력 총액공사","수평 추락방지장치 설치","2023-10-30 07:30","2023-10-31 18:00","2023-10-30 07:30","2023-10-31 18:00","연속"]
[608,"대구","칠곡","성주금릉#1 T/L","22-23년 칠곡전력 가공송전협력 총액공사","관형지지물용 가이드레일 설치","2023-10-07 07:30","2023-10-07 18:00","2023-10-07 07:30","2023-10-07 18:00","연속"]
[609,"대구","칠곡","성주금릉#2 T/L","22-23년 칠곡전력 가공송전협력 총액공사","관형지지물용 가이드레일 설치","2023-10-07 07:30","2023-10-07 18:00","2023-10-07 07:30","2023-10-07 18:00","연속"]
[610,"대구","포항","아화건천#1 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","(안전확보) 철탑추락방지장치 설치(관형지지물 포함) - 작업구간 : No.1~51","2023-10-26 07:00","2023-11-02 18:00","2023-10-26 07:00","2023-11-02 18:00","연속"]
[611,"대구","포항","아화건천#2 T/L","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 637 GIS 정밀점검","2023-10-07 09:00","2023-10-09 18:00","2023-10-07 09:00","2023-10-09 18:00","연속"]
[612,"대구","포항","건천천북#2 T/L","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 677 GIS 정밀점검","2023-10-10 09:00","2023-10-12 18:00","2023-10-10 09:00","2023-10-12 18:00","연속"]
[613,"대구","포항","건천천북#1 T/L","'23년 상반기 포항전력지사 154kV GIS 기기점검공사","건천S/S 6B7 GIS 정밀점검","2023-10-04 09:00","2023-10-06 18:00","2023-10-04 09:00","2023-10-06 18:00","연속"]
[614,"대구","포항","건천천북#2 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","(안전확보) 철탑추락방지장치 설치(관형지지물 포함) - 작업구간 : No.1 ~ 4, 6, ,8, 17, 20","2023-10-28 07:00","2023-10-29 18:00","2023-10-28 07:00","2023-10-29 18:00","연속"]
[615,"대구","포항","신영일천북#1 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","정밀점검","2023-10-15 08:00","2023-10-26 18:00","2023-10-15 08:00","2023-10-26 18:00","연속"]
[616,"대구","포항","신영일천북#2 T/L","2023년 포항전력지사 가공송전 순시점검 위탁공사","정밀점검","2023-10-27 08:00","2023-11-09 18:00","2023-10-27 08:00","2023-11-09 18:00","연속"]
[617,"경북","구미","남인동인동#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","[남인동S/S] - GIS 하자점검 - LA 초기점검 [인동S/S] - GIS 조작시험 - LA 교체","2023-10-05 09:00","2023-10-05 14:00","취소","취소","연속"]
[618,"경북","구미","남인동인동#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","[남인동S/S] - GIS 하자점검 - LA 초기점검 [인동S/S] - GIS 조작시험 - LA 교체","2023-10-05 09:00","2023-10-05 14:00","취소","취소","연속"]
[619,"경북","구미","동상주점촌#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- IED F/W 업그레이드 [세니온]","2023-10-20 09:00","2023-10-20 18:00","2023-10-20 09:00","2023-10-20 18:00","연속"]
[620,"경북","구미","동상주점촌#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- IED F/W 업그레이드 [세니온]","2023-10-20 09:00","2023-10-20 18:00","2023-10-20 09:00","2023-10-20 18:00","연속"]
[621,"경북","구미","남인동인동#1 T/L","2022-23년도 구미전력지사 가공송전정비 협력회사 총액공사","154kV 남인동-인동T/L 철탑 추락방지장치 설치공사(No.1~17, 19~36, 49)","2023-10-25 08:00","2023-11-01 17:00","2023-10-25 08:00","2023-11-01 17:00","매일"]
[622,"경북","구미","청리상주#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- #60-65 모선보호반 교체","2023-10-13 14:30","2023-10-13 15:00","2023-10-13 14:30","2023-10-13 15:00","연속"]
[623,"경북","구미","선산청리#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- LA 교체","2023-10-31 09:00","2023-10-31 14:00","2023-10-31 09:00","2023-10-31 14:00","연속"]
[624,"경북","구미","선산청리#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- LA 교체","2023-10-31 14:00","2023-10-31 18:00","2023-10-31 14:00","2023-10-31 18:00","연속"]
[625,"경북","구미","청리상주#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- #60-65 모선보호반 교체","2023-10-13 14:00","2023-10-13 14:30","2023-10-13 14:00","2023-10-13 14:30","연속"]
[626,"경북","구미","선산청리#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- #60-65 모선보호반 교체","2023-10-13 13:00","2023-10-13 13:30","2023-10-13 13:00","2023-10-13 13:30","연속"]
[627,"경북","구미","선산청리#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- #60-65 모선보호반 교체","2023-10-13 13:30","2023-10-13 14:00","2023-10-13 13:30","2023-10-13 14:00","연속"]
[628,"경북","영주","점촌문경 T/L","154kV 점촌-문경T/L 수평 추락방지장치 및 폴리머지지애자 설치공사","154kV 점촌-문경T/L 수평 추락방지장치 및 폴리머지지애자 설치","2023-10-07 09:00","2023-10-09 18:00","2023-10-21 09:00","2023-10-22 18:00","매일"]
[629,"경북","영주","문경단양 T/L","154kV 문경-단양T/L 수평 추락방지장치 및 폴리머지지애자 설치공사","154kV 문경-단양T/L 수평 추락방지장치 및 폴리머지지애자 설치","2023-10-14 09:00","2023-10-15 18:00","2023-10-28 09:00","2023-10-29 18:00","매일"]
[630,"경북","영주","신영주영주#1 T/L","154kV 신영주-영주#1T/L 수평 추락방지장치 설치공사","154kV 신영주-영주#1T/L 수평 추락방지장치 설치","2023-10-27 09:00","2023-11-04 18:00","2023-10-27 09:00","2023-11-04 18:00","매일"]
[631,"경북","영주","신영주영주#1 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","GIS,LA 보통점검","2023-10-12 09:00","2023-10-12 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[632,"경북","영주","신영주영주#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","GIS,LA 보통점검","2023-10-13 09:00","2023-10-13 18:00","2023-10-19 09:00","2023-10-19 18:00","연속"]
[633,"경북","직할","안동동안동#2 T/L","동안동S/S 154kV SW 증설 및 GIS 교체공사","○ 154kV GIS 7CCT 철거, 11CCT 설치 - 1차수(10.11~17) : 154kV GIS 1CCT 설치","2023-10-13 10:00","2023-10-14 10:00","2023-10-13 10:00","2023-10-14 10:00","연속"]
[634,"경북","직할","안동동안동#2 T/L","동안동S/S 154kV SW 증설 및 GIS 교체공사","○ 154kV GIS 7CCT 철거, 11CCT 설치 - 1차수(10.11~17) : 154kV GIS 1CCT 설치","2023-10-16 16:00","2023-10-17 16:00","2023-10-16 16:00","2023-10-17 16:00","연속"]
[635,"경북","직할","울진현종산풍력 T/L","울진S/S 장기사용 GIS 교체공사(4차분)","울진S/S 장기사용 GIS 교체공사(4차분)","2023-10-04 09:00","2023-11-01 18:00","2023-10-04 09:00","2023-11-01 18:00","연속"]
[636,"경북","직할","울진삼척GP#1 T/L","울진S/S 장기사용 GIS 교체공사(4차분)","울진S/S 장기사용 GIS 교체공사(4차분) -#2BUS 무부하 가압용","2023-10-04 18:00","2023-10-05 09:00","2023-10-04 18:00","2023-10-05 09:00","연속"]
[637,"경북","직할","울진S/S #1 BUS","울진S/S 장기사용 GIS 교체공사(4차분)","울진S/S 장기사용 GIS 교체공사(4차분)","2023-10-12 09:00","2023-10-27 18:00","2023-10-12 09:00","2023-10-27 18:00","연속"]
[638,"경북","직할","울진삼척GP#1 T/L","울진S/S 장기사용 GIS 교체공사(4차분)","울진S/S 장기사용 GIS 교체공사(4차분) -#1BUS 무부하 가압용","2023-10-26 09:00","2023-10-27 18:00","2023-10-26 09:00","2023-10-27 18:00","연속"]
[639,"경북","직할","현종산풍력평해#1 T/L","2022~2023년 경북직할 송전협력회사 총액공사","154kV 현종산풍력-평해#1T/L - 추락방지장치(수평) 및 고정형 폴리머 점퍼지지애자 설치","2023-10-20 09:00","2023-10-28 18:00","2023-10-20 09:00","2023-10-28 18:00","매일"]
[640,"경북","직할","현종산풍력평해#2 T/L","2022-2023년 경북직할 송전협력회사 총액공사","154kV 현종산풍력-평해#2T/L 고정형 폴리머 점퍼지지애자 설치","2023-10-18 09:00","2023-10-19 18:00","2023-10-18 09:00","2023-10-19 18:00","매일"]
[641,"부산울산","동부산","구서S/S #1 BUS","154kV 구서S/S 장기사용 GIS 교체공사(2차)","○ 154kV 구서-명장#1T/L GIS 교체 → #1BUS 상체크","2023-10-26 17:00","2023-10-26 18:00","2023-10-26 17:00","2023-10-26 18:00","연속"]
[642,"부산울산","동부산","신양산구서#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","구서-명장#2T/L 피뢰기 설치 관련 안전이격확보 휴전","2023-10-26 08:00","2023-10-27 18:00","2023-10-26 08:00","2023-10-27 18:00","연속"]
[643,"부산울산","동부산","구서노포#2 T/L","154kV 구서S/S 장기사용 GIS 교체공사(2차)","○ #2BUS 시험가압(24Hr)","2023-10-25 18:00","2023-10-26 18:00","2023-10-25 18:00","2023-10-26 18:00","연속"]
[644,"부산울산","동부산","구서S/S #2 BUS","154kV 구서S/S 장기사용 GIS 교체공사(2차)","○ 154kV 구서-명장#1T/L GIS 교체 → #2DS, 상부BUS 설치","2023-10-13 09:00","2023-10-26 18:00","2023-10-13 09:00","2023-10-26 18:00","연속"]
[645,"부산울산","동부산","구서노포#1 T/L","154kV 구서S/S 장기사용 GIS 교체공사(2차)","○ #1BUS 시험가압(24Hr)","2023-10-11 18:00","2023-10-12 18:00","2023-10-11 18:00","2023-10-12 18:00","연속"]
[646,"부산울산","동부산","구서S/S #2 BUS","154kV 구서S/S 장기사용 GIS 교체공사(2차)","○ 154kV 구서-명장#1T/L #2DS 철거 및 고깔처리","2023-10-02 09:00","2023-10-04 18:00","2023-10-02 09:00","2023-10-04 18:00","연속"]
[647,"부산울산","동부산","구서노포#2 T/L","154kV 구서S/S 장기사용 GIS 교체공사(2차)","○ #2BUS 시험가압(1Hr)","2023-10-04 17:00","2023-10-04 18:00","2023-10-04 17:00","2023-10-04 18:00","연속"]
[648,"부산울산","동부산","구서S/S #1 BUS","154kV 구서S/S 장기사용 GIS 교체공사(2차)","○ 154kV 구서-명장#1T/L GIS 교체 → CB, #1DS 철거 및 설치","2023-10-05 09:00","2023-10-12 18:00","2023-10-05 09:00","2023-10-12 18:00","연속"]
[649,"부산울산","동부산","구서명장#1 T/L","154kV 구서S/S 장기사용 GIS 교체공사(2차)","○ 154kV 구서-명장#1T/L GIS 교체","2023-10-02 09:00","2023-10-26 18:00","2023-10-02 09:00","2023-10-26 18:00","연속"]
[650,"부산울산","동부산","노포정관#2 T/L","노포S/S 170GIS 정밀점검관련 시험가압","노포S/S 170GIS 정밀점검관련 시험가압(고속철도#1)","2023-10-11 17:00","2023-10-11 18:00","2023-10-11 17:00","2023-10-11 18:00","연속"]
[651,"부산울산","동부산","노포정관#2 T/L","노포S/S 170GIS 정밀점검관련 시험가압","노포S/S 170GIS 정밀점검관련 시험가압(노포지하철)","2023-10-22 17:00","2023-10-22 18:00","2023-10-22 17:00","2023-10-22 18:00","연속"]
[652,"부산울산","동부산","노포정관#2 T/L","노포S/S 170GIS 정밀점검관련 시험가압","노포S/S 170GIS 정밀점검관련 시험가압(고속철도#2)","2023-10-13 17:00","2023-10-13 18:00","2023-10-13 17:00","2023-10-13 18:00","연속"]
[653,"부산울산","동부산","노포정관#2 T/L","노포S/S 170GIS 정밀점검관련 시험가압","노포S/S 170GIS 정밀점검관련 시험가압(#2M.Tr)","2023-10-19 17:00","2023-10-19 18:00","2023-10-19 17:00","2023-10-19 18:00","연속"]
[654,"부산울산","동부산","노포정관#2 T/L","노포S/S 170GIS 정밀점검관련 시험가압","노포S/S 170GIS 정밀점검관련 시험가압(#1M.Tr)","2023-10-17 17:00","2023-10-17 18:00","2023-10-17 17:00","2023-10-17 18:00","연속"]
[655,"부산울산","동부산","정관장안#1 T/L","154kV 구서-노포-정관-장안T/L OPGW 증설공사","OPGW 교체(24C→48C) : 21.4km","2023-10-16 08:00","2023-10-21 18:00","2023-10-16 08:00","2023-10-21 18:00","연속"]
[656,"부산울산","동부산","정관장안#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 및 피뢰기 설치, 금구류교체","2023-10-10 08:00","2023-10-13 18:00","2023-10-10 08:00","2023-10-13 18:00","연속"]
[657,"부산울산","동부산","정관장안#2 T/L","정관S/S 170GIS 정밀점검관련 시험가압","정관S/S 170GIS 정밀점검관련 시험가압(정관-열병합)","2023-10-07 17:00","2023-10-07 18:00","2023-10-07 17:00","2023-10-07 18:00","연속"]
[658,"부산울산","동부산","구서노포#1 T/L","노포S/S 170GIS 정밀점검","노포S/S 170GIS 정밀점검","2023-10-31 17:00","2023-11-01 18:00","2023-10-31 17:00","2023-11-01 18:00","연속"]
[659,"부산울산","북부산","북부산구포#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV #3M.Tr 1차 GIS 정밀점검 휴전설비 : 북부산-구포#2T/L(시험가압선로)","2023-10-11 17:00","2023-10-11 18:00","2023-10-11 17:00","2023-10-11 18:00","연속"]
[660,"부산울산","북부산","구포S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV #3M.Tr 1차 GIS 정밀점검 휴전설비 : #1BUS","2023-10-12 08:00","2023-10-13 18:00","2023-10-12 08:00","2023-10-13 18:00","연속"]
[661,"부산울산","북부산","북부산구포#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV 지하철2호선T/L GIS 정밀점검 휴전설비 : 북부산-구포#2T/L(시험가압선로)","2023-10-08 12:00","2023-10-08 13:00","2023-10-08 12:00","2023-10-08 13:00","연속"]
[662,"부산울산","북부산","북부산구포#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV 지하철3호선T/L GIS 정밀점검 휴전설비 : 북부산-구포#2T/L(시험가압선로)","2023-10-15 12:00","2023-10-15 13:00","2023-10-15 12:00","2023-10-15 13:00","연속"]
[663,"부산울산","북부산","구포S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV 지하철3호선T/L GIS 정밀점검 휴전설비 : #2BUS","2023-10-15 12:00","2023-10-15 13:00","2023-10-15 12:00","2023-10-15 13:00","연속"]
[664,"부산울산","북부산","구포S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV #3M.Tr 1차 GIS 정밀점검 휴전설비 : #2BUS","2023-10-11 08:00","2023-10-11 18:00","2023-10-11 08:00","2023-10-11 18:00","연속"]
[665,"부산울산","북부산","구포S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV 지하철2호선T/L GIS 정밀점검 휴전설비 : #2BUS","2023-10-08 12:00","2023-10-08 13:00","2023-10-08 12:00","2023-10-08 13:00","연속"]
[666,"부산울산","북부산","모라S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#2T/L GIS 정밀점검 휴전설비 : #1BUS","2023-10-24 08:00","2023-10-25 18:00","2023-10-03 08:00","2023-10-04 18:00","연속"]
[667,"부산울산","북부산","모라S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#2T/L GIS 정밀점검 휴전설비 : #2BUS","2023-10-23 08:00","2023-10-23 18:00","2023-10-02 08:00","2023-10-02 18:00","연속"]
[668,"부산울산","북부산","대저모라#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","모라S/S 154kV 대저-모라#2T/L GIS 정밀점검","2023-10-23 08:00","2023-10-25 18:00","2023-10-02 08:00","2023-10-04 18:00","연속"]
[669,"부산울산","북부산","북부산호포 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치공사","154kV 북부산-물금T/L, 호포분기T/L 수평 추락방지장치 설치(북부산물금 9기, 호포분기 5기)","2023-10-05 08:30","2023-10-07 18:00","2023-10-30T08:30:00","2023-11-03T18:00:00","연속"]
[670,"부산울산","북부산","북부산물금 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치(안전확보)","154kV 북부산-물금T/L 수평 추락방지장치 설치 4회선 병가구간 안전확보(북부산물금 15기)","2023-10-07 08:30","2023-10-07 18:00","2023-10-30 08:30","2023-10-31 18:00","연속"]
[671,"부산울산","북부산","북부산물금 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치","154kV 북부산-물금T/L 수평 추락방지장치 설치(북부산물금 24-1~46호, 19기)","2023-10-08 08:30","2023-10-09 18:00","2023-10-10 08:30","2023-10-13 18:00","연속"]
[672,"부산울산","북부산","북부산구포#2 T/L","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 북부산-구포#2T/L GIS 메커니즘 보강공사","2023-10-13 09:00","2023-10-13 18:00","2023-10-13 09:00","2023-10-13 18:00","연속"]
[673,"부산울산","북부산","북부산구포#1 T/L","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 북부산-구포#1T/L GIS 메커니즘 보강공사","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[674,"부산울산","북부산","북부산S/S CB 6100","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 154kV 6100 GIS 메커니즘 보강공사","2023-10-27 09:00","2023-10-27 18:00","2023-10-27 09:00","2023-10-27 18:00","연속"]
[675,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(북부산양산T/L 측 2회선 철탑 12기)","2023-10-10 08:30","2023-10-11 18:00","2023-10-23T08:30:00","2023-10-25T18:00:00","연속"]
[676,"부산울산","북부산","북부산구포#3 T/L","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 154kV 북부산-구포#3T/L GIS 메커니즘 보강공사","2023-10-30 09:00","2023-10-31 18:00","2023-10-30 09:00","2023-10-31 18:00","연속"]
[677,"부산울산","북부산","북부산물금 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치","154kV 북부산-물금T/L 수평 추락방지장치 설치(북부산물금 24-1~46호, 19기)","2023-10-28 08:30","2023-10-29 18:00","취소","취소","연속"]
[678,"부산울산","북부산","북부산S/S CB 6300","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 154kV 6300 GIS 메커니즘 보강공사","2023-10-26 09:00","2023-10-26 18:00","2023-10-26 09:00","2023-10-26 18:00","연속"]
[679,"부산울산","북부산","북부산S/S SEC CB 61620","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 154kV 61-62-0 GIS 메커니즘 보강공사","2023-10-25 09:00","2023-10-25 18:00","2023-10-25 09:00","2023-10-25 18:00","연속"]
[680,"부산울산","북부산","북부산S/S SEC CB 65660","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 154kV 65-66-0 GIS 메커니즘 보강공사","2023-10-24 09:00","2023-10-24 18:00","2023-10-24 09:00","2023-10-24 18:00","연속"]
[681,"부산울산","북부산","언양산막#1 T/L","산막S/S 154kV GIS 교체공사","산막S/S 154kV GIS 교체공사 - 시험가압 선로","2023-10-18 18:00","2023-10-19 18:00","취소","취소","연속"]
[682,"부산울산","북부산","언양산막#2 T/L","산막S/S 154kV GIS 교체공사","산막S/S 154kV GIS 교체공사 - 시험가압 선로","2023-10-24 18:00","2023-10-25 19:00","취소","취소","연속"]
[683,"부산울산","북부산","양산산막#2 T/L","154kV 산막S/S 장기사용 GIS 교체공사","154kV 산막S/S 장기사용 GIS 교체공사 - 양산-산막#2T/L 대체 - 서창-산막#2T/L 대체","2023-10-12 09:00","2023-10-25 18:00","취소","취소","연속"]
[684,"부산울산","북부산","언양산막#2 T/L","산막S/S 154kV GIS 교체공사","산막S/S 154kV GIS 교체공사 - 시험가압 선로","2023-10-14 17:00","2023-10-14 18:00","취소","취소","연속"]
[685,"부산울산","북부산","언양산막#1 T/L","산막S/S 154kV GIS 교체공사","산막S/S 154kV GIS 교체공사 -언양-산막#1T/LGIS 대체","2023-10-26 09:00","2023-11-15 19:00","취소","취소","연속"]
[686,"부산울산","북부산","양산산막#2 T/L","154kV 산막S/S 장기사용GIS 교체공사","154kV 산막S/S 장기사용GIS 교체공사 - 서창-산막#2T/L 대체 시험가압선로","2023-10-28 17:00","2023-10-28 18:00","취소","취소","연속"]
[687,"부산울산","북부산","호포물금 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치(안전확보)","154kV 북부산-물금T/L 수평 추락방지장치 설치 4회선 구간 안전확보(북부산물금 24-1~46호, 19기)","2023-10-28 08:30","2023-10-29 18:00","취소","취소","연속"]
[688,"부산울산","북부산","호포물금 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV #2M.Tr 1차 GIS 정밀점검 - 휴전설비 : 호포-물금T/L(시험가압 선로)","2023-10-20 17:00","2023-10-20 18:00","2023-10-20 17:00","2023-10-20 18:00","연속"]
[689,"부산울산","북부산","호포S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV #2M.Tr 1차 GIS 정밀점검 - 휴전설비 : #1BUS","2023-10-19 08:00","2023-10-20 18:00","2023-10-19 08:00","2023-10-20 18:00","연속"]
[690,"부산울산","북부산","호포물금 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV #2M.Tr 1차 GIS 정밀점검 - 휴전설비 : 호포-물금T/L(시험가압 선로)","2023-10-18 17:00","2023-10-18 18:00","2023-10-18 17:00","2023-10-18 18:00","연속"]
[691,"부산울산","북부산","호포S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV #2M.Tr 1차 GIS 정밀점검 - 휴전설비 : #2BUS","2023-10-18 08:00","2023-10-18 18:00","2023-10-18 08:00","2023-10-18 18:00","연속"]
[692,"부산울산","북부산","호포S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV #3M.Tr 1차 GIS 유사고장 조치 - 휴전설비 : #1BUS","2023-10-17 17:00","2023-10-17 18:00","2023-10-17 17:00","2023-10-17 18:00","연속"]
[693,"부산울산","북부산","호포매리#2 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치","154kV 호포-매리#2T/L 수평 추락방지장치 설치(1호 등 10기)","2023-10-14 08:30","2023-10-15 18:00","2023-10-14 08:30","2023-10-15 18:00","연속"]
[694,"부산울산","북부산","호포물금 T/L","154kV 북부산-삼랑진 등 8개T/L 수평추락방지장치 설치(안전확보)","154kV 북부산-물금T/L 수평 추락방지장치 설치 4회선 구간 안전확보(북부산물금 24-1~46호, 19기)","2023-10-08 08:30","2023-10-09 18:00","2023-10-10 08:30","2023-10-13 18:00","연속"]
[695,"부산울산","북부산","호포물금 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV #3M.Tr 1차 GIS 유사고장 조치 - 휴전설비 : 호포-물금T/L(시험가압 선로)","2023-10-17 18:00","2023-10-17 19:00","2023-10-17 18:00","2023-10-17 19:00","연속"]
[696,"부산울산","북부산","호포S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV 북부산-호포T/L GIS 정밀점검 - 휴전설비 : #1BUS","2023-10-05 08:00","2023-10-06 18:00","2023-10-05 08:00","2023-10-06 18:00","연속"]
[697,"부산울산","서부산","서부산S/S #2ST CB","서부산S/S 154kV #2 S/T GIS 동작시험","서부산S/S 154kV #2 S/T GIS 동작시험 (부산복합 3,4G/T 법정검사 예정)","2023-10-13 09:00","2023-10-13 18:00","2023-10-13 09:00","2023-10-13 18:00","연속"]
[698,"부산울산","서부산","서부산엄궁#2 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 345kV 차단기 용량부족 대체공사 관련 집중감시제어반 DB 수용","2023-10-23 09:00","2023-10-27 18:00","2023-10-23 09:00","2023-10-27 18:00","연속"]
[699,"부산울산","서부산","서부산다대#2 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 345kV 차단기 용량부족 대체공사 관련 집중감시제어반 DB 수용","2023-10-16 09:00","2023-10-20 18:00","2023-10-16 09:00","2023-10-20 18:00","연속"]
[700,"부산울산","서부산","서부산S/S CB 6100","서부산S/S 154kV 6100 BUS TIE GIS 보통점검[전문공사]","서부산S/S 154kV 6100 BUS TIE GIS 보통점검[전문공사]","2023-10-17 09:00","2023-10-17 18:00","2023-10-17 09:00","2023-10-17 18:00","연속"]
[701,"부산울산","서부산","서부산S/S CB 6200","서부산S/S 154kV 6200 BUS TIE GIS 보통점검[전문공사]","서부산S/S 154kV 6200 BUS TIE GIS 보통점검[전문공사]","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[702,"부산울산","울산","남울산용연#2 T/L","154kV 추락방지장치 설치공사","ㅇ 남울산-용연#2 - 추락방지장치 수평3기 설치 1 2 3 호","2023-10-04 07:30","2023-10-05 18:00","2023-10-04 07:30","2023-10-05 18:00","연속"]
[703,"부산울산","울산","남울산용연#1 T/L","154kV 추락방지장치 설치공사","ㅇ 남울산-용연#1 - 추락방지장치 수평1기 설치 1 2 3 호","2023-10-06 07:30","2023-10-06 18:00","2023-10-06 07:30","2023-10-06 18:00","연속"]
[704,"부산울산","울산","동울산산하#1 T/L","154kV 추락방지장치 설치공사","ㅇ 동울산-산하#1 - 추락방지장치 수평 8기 1~8호","2023-10-30 07:30","2023-11-01 18:00","2023-10-30 07:30","2023-11-01 18:00","연속"]
[705,"부산울산","울산","두왕울산#1 T/L","22~23년 변전협력회사 총액공사","- 양단 세니온제 보호반 성능개선","2023-10-17 09:00","2023-10-17 18:00","2023-10-17 09:00","2023-10-17 18:00","연속"]
[706,"부산울산","울산","두왕울산#2 T/L","22~23년 변전협력회사 총액공사","- 양단 세니온제 보호반 성능개선","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[707,"부산울산","울산","반천언양#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치, 피뢰기 설치","2023-10-06 09:00","2023-10-06 18:00","2023-10-06 09:00","2023-10-06 18:00","연속"]
[708,"부산울산","울산","반천언양#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치, 피뢰기 설치","2023-10-05 08:00","2023-10-05 18:00","2023-10-05 08:00","2023-10-05 18:00","연속"]
[709,"부산울산","울산","신울산명례#2 T/L","2022~2023년 동부산 가공송전 협력회사 총액공사","-폴리머점퍼지지애자 설치 및 추락방지장치 설치","2023-10-17 07:00","2023-10-18 18:00","2023-10-17 07:00","2023-10-18 18:00","연속"]
[710,"부산울산","울산","신울산S/S SEC CB 67680","22~23년 변전협력회사 총액공사","- GIS 차단기 동작시험","2023-10-04 09:00","2023-10-04 18:00","2023-10-04 09:00","2023-10-04 18:00","연속"]
[711,"부산울산","울산","신울산S/S #66G BUS","신울산S/S 154kV 현대화공사","신울산-매암#3T/L C/H설치관련 시험가압","2023-10-31 14:00","2023-11-01 14:00","2023-10-31 14:00","2023-11-01 14:00","연속"]
[712,"부산울산","울산","신울산명례#1 T/L","2022~2023년 동부산 가공송전 협력회사 총액공사","-폴리머점퍼지지애자 설치 및 추락방지장치 설치","2023-10-16 07:00","2023-10-16 18:00","2023-10-16 07:00","2023-10-16 18:00","연속"]
[713,"부산울산","울산","신울산S/S #65G BUS","신울산S/S 154kV 현대화공사","신울산-매암#1,2T/L C/H설치관련 시험가압","2023-10-30 14:00","2023-10-31 14:00","2023-10-30 14:00","2023-10-31 14:00","연속"]
[714,"부산울산","울산","언양산막#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","반천-언양#2T/L 휴전작업 관련 안전이격확보 휴전","2023-10-06 08:00","2023-10-06 18:00","2023-10-06 08:00","2023-10-06 18:00","연속"]
[715,"부산울산","울산","언양산막#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","반천-언양#1T/L 휴전작업 관련 안전이격확보 휴전","2023-10-05 08:00","2023-10-05 18:00","2023-10-05 08:00","2023-10-05 18:00","연속"]
[716,"부산울산","울산","옥동외동#2 T/L","154kV 추락방지장치 설치공사","ㅇ 울주-외동#1 - 추락방지장치 수평 42기(4회선 1~4, 16~43) - 외동-옥동#2 16~43호 병가선로 포함","2023-10-17 07:30","2023-10-25 18:00","2023-10-17 07:30","2023-10-25 18:00","연속"]
[717,"부산울산","울산","신울산옥동#2 T/L","154kV 추락방지장치 설치공사","ㅇ 신울산-옥동#2 - 추락방지장치 수평 12기(4회선 2기 포함) 1~13호","2023-10-10 07:30","2023-10-13 18:00","2023-10-10 07:30","2023-10-13 18:00","연속"]
[718,"부산울산","울산","신온산온산#1 T/L","22~23년 변전협력회사 총액공사","- 차단기 동작시험","2023-10-16 09:00","2023-10-16 18:00","2023-10-16 09:00","2023-10-16 18:00","연속"]
[719,"부산울산","울산","용연울산TP#3 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-10-30 07:00","2023-11-01 18:00","2023-10-30 07:00","2023-11-01 18:00","연속"]
[720,"부산울산","울산","울산T/P #61 BUS","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 154kV 6200 BUS-TIE, #61-66BUS PT, 용연-울산TP#2T/L GIS 교체 → #61BUS, #1DS, CB, #61BUS PT 철거 및 신규 GIS 설치","2023-10-02 09:00","2023-10-17 18:00","2023-10-02 09:00","2023-10-17 18:00","연속"]
[721,"부산울산","울산","용연울산TP#1 T/L","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 울산화력S/Y #61BUS 시험가압(24Hr)","2023-10-16 18:00","2023-10-17 18:00","2023-10-16 18:00","2023-10-17 18:00","연속"]
[722,"부산울산","울산","울산T/P #66 BUS","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 154kV 6200 BUS-TIE, #61-66BUS PT, 용연-울산TP#2T/L GIS 교체 → #66BUS 철거 및 신규 GIS 설치, 준공시험, 시험가압 및 실부하가압","2023-10-18 09:00","2023-11-04 18:00","2023-10-18 09:00","2023-11-04 18:00","연속"]
[723,"부산울산","울산","용연울산TP#3 T/L","울산화력S/Y 장기사용 GIS 교체공사(5차)","안전이격거리확보 -154kV 6200 BUS-TIE 철거 및 설치","2023-10-02 09:00","2023-10-06 18:00","2023-10-02 09:00","2023-10-06 18:00","연속"]
[724,"부산울산","울산","울주외동#1 T/L","154kV 추락방지장치 설치공사","ㅇ 울주-외동#1 - 추락방지장치 수평 42기(4회선 1~4, 16~43) - 1~4 울주입실#1 병가(포항전력지사 선로) - 16~43 외동옥동#2 병가","2023-10-16 07:30","2023-10-27 18:00","2023-10-16 07:30","2023-10-27 18:00","연속"]
[725,"부산울산","울산","울주입실#1 T/L","154kV 추락방지장치 설치공사","ㅇ 울주-외동#1 - 추락방지장치 수평 42기(4회선 1~4, 16~43) - 1~4 울주입실#1 병가(포항전력지사 선로)","2023-10-16 07:30","2023-10-16 18:00","2023-10-16 07:30","2023-10-16 18:00","연속"]
[726,"부산울산","울산","웅촌서창#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-10-18 08:00","2023-10-20 18:00","2023-10-18 08:00","2023-10-20 18:00","연속"]
[727,"부산울산","울산","신울산웅촌#1 T/L","154kV 추락방지장치 설치공사(안전이격)","ㅇ 신울산-웅촌#1 - 추락방지장치 수평 2기(4회선 2기 포함) 3,4호 구간(신울산-옥동2,3호 병가구간)","2023-10-10 07:30","2023-10-11 18:00","2023-10-10 07:30","2023-10-11 18:00","연속"]
[728,"부산울산","울산","신울산웅촌#1 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-10-18 08:00","2023-10-18 18:00","2023-10-18 08:00","2023-10-18 18:00","연속"]
[729,"부산울산","울산","신울산웅촌#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-10-23 08:00","2023-10-23 18:00","2023-10-23 08:00","2023-10-23 18:00","연속"]
[730,"부산울산","울산","웅촌서창#2 T/L","154kV 추락방지장치(수평) 및 피뢰기 설치공사","수평 추락방지장치 설치","2023-10-23 08:00","2023-10-25 18:00","2023-10-23 08:00","2023-10-25 18:00","연속"]
[731,"부산울산","울산","직동반천#1 T/L","22~23년 변전협력회사 총액공사","- 피뢰기 대체","2023-10-18 09:00","2023-10-18 18:00","2023-10-18 09:00","2023-10-18 18:00","연속"]
[732,"부산울산","울산","직동반천#2 T/L","22~23년 변전협력회사 총액공사","- 피뢰기 대체","2023-10-20 09:00","2023-10-20 18:00","2023-10-20 09:00","2023-10-20 18:00","연속"]
[733,"부산울산","울산","남울산처용#2 T/L","22~23년 변전협력회사 총액공사","- 피뢰기 대체","2023-10-26 09:00","2023-10-26 18:00","2023-10-26 09:00","2023-10-26 18:00","연속"]
[734,"부산울산","직할","정보대연 T/L","345kV 신양산-신대연 등 7개T/L 자기애관교체공사","자기애관을 폴리머애관으로 교체","2023-10-27 09:00","2023-10-31 18:00","2023-10-27 09:00","2023-10-31 18:00","연속"]
[735,"부산울산","직할","범일서면#1 T/L","22-23년 직할 변전협력회사 총액공사","범일S/S 범일-서면#1,2T/L GIS 조작시험","2023-10-04 09:30","2023-10-04 18:00","2023-10-04 09:30","2023-10-04 18:00","연속"]
[736,"부산울산","직할","범일서면#2 T/L","154kV 범일S/S #3M.Tr 증설공사","154kV 범일S/S #3M.Tr 1차측 GIS 설치 - 가스 회수 관련 감압 필요","2023-10-12 09:00","2023-10-13 18:00","취소","취소","연속"]
[737,"부산울산","직할","수정범일#2 T/L","154kV 범일S/S #3M.Tr 증설공사","154kV 범일S/S #3M.Tr 1차측 GIS 설치 - 무부하 시험가압","2023-10-24 09:00","2023-10-25 18:00","취소","취소","연속"]
[738,"부산울산","직할","수정범일#1 T/L","154kV 범일S/S #3M.Tr 증설공사","154kV 범일S/S #3M.Tr 1차측 GIS 설치 - 무부하 시험가압","2023-10-14 09:00","2023-10-15 18:00","취소","취소","연속"]
[739,"부산울산","직할","범일서면#2 T/L","154kV 범일S/S #3M.Tr 증설공사","154kV 범일S/S #3M.Tr 1차측 GIS 설치 - 가스 회수 관련 감압 필요","2023-10-15 09:00","2023-10-16 18:00","취소","취소","연속"]
[740,"부산울산","직할","부산수정#2 T/L","23-24년 서부산전력지사 지중송전 위탁정비공사","OF케이블 접속함 절연유 채유작업","2023-10-21 09:00","2023-10-22 18:00","2023-10-21 09:00","2023-10-22 18:00","연속"]
[741,"부산울산","직할","부산수정#1 T/L","23-24년 서부산전력지사 지중송전 위탁정비공사","OF케이블 접속함 절연유 채유작업","2023-10-28 09:00","2023-10-29 18:00","2023-10-28 09:00","2023-10-29 18:00","연속"]
[742,"경남","직할","신김해지사#1 T/L","154kV 신김해-지사T/L 수평 추락방지장치 설치공사","154kV 신김해-지사T/L 수평 추락방지장치 설치공사","2023-10-16 07:00","2023-10-18 18:00","2023-10-16 07:00","2023-10-18 18:00","매일"]
[743,"경남","직할","신김해지사#2 T/L","154kV 신김해-지사T/L 수평 추락방지장치 설치공사","154kV 신김해-지사T/L 수평 추락방지장치 설치공사","2023-10-19 07:00","2023-10-21 18:00","2023-10-19 07:00","2023-10-21 18:00","매일"]
[744,"경남","직할","신김해주촌#2 T/L","효성제 154kV GIS 베어링발청보수 작업","신김해S/S 신김해-주촌#2T/L(6A7) 베어링발청보수","2023-10-16 09:00","2023-10-16 18:00","2023-10-16 09:00","2023-10-16 18:00","연속"]
[745,"경남","직할","신김해진례#2 T/L","OPGW 취약개소 금구류 정비공사","OPGW 댐퍼 2개 교체 및 3개 정비 등","2023-10-11 07:00","2023-10-11 18:00","2023-10-11 07:00","2023-10-11 18:00","연속"]
[746,"경남","직할","신월삼정#2 T/L","154kV 신월-동읍 등 2개T/L OF케이블 절연유 채유공사","OF케이블 절연유 채유공사","2023-10-21 09:00","2023-10-21 12:00","2023-10-21 09:00","2023-10-21 12:00","연속"]
[747,"경남","직할","신월동읍#1 T/L","154kV 신월-동읍T/L 수평 추락방지장치 설치공사","154kV 신월-동읍T/L 수평 추락방지장치 설치공사","2023-10-23 07:00","2023-10-28 18:00","2023-10-23 07:00","2023-10-28 18:00","매일"]
[748,"경남","직할","신월삼정#1 T/L","154kV 신월-삼정T/L 수평 추락방지장치 설치공사","154kV 신월-삼정T/L 수평 추락방지장치 설치공사","2023-10-28 07:00","2023-10-28 18:00","2023-10-28 07:00","2023-10-28 18:00","연속"]
[749,"경남","직할","신월동읍#2 T/L","154kV 신월-동읍 등 2개T/L OF케이블 절연유 채유공사","OF케이블 절연유 채유공사","2023-10-21 09:00","2023-10-21 12:00","2023-10-21 09:00","2023-10-21 12:00","연속"]
[750,"경남","직할","신월동읍#2 T/L","154kV 신월-동읍T/L 수평 추락방지장치 설치공사","154kV 신월-동읍T/L 수평 추락방지장치 설치공사","2023-10-30 07:00","2023-11-04 18:00","2023-10-30 07:00","2023-11-04 18:00","매일"]
[751,"경남","직할","장유마천#2 T/L","154kV 장유-마천T/L 수평 추락방지장치 설치공사","154kV 장유-마천T/L 수평 추락방지장치 설치공사","2023-10-21 07:00","2023-10-21 18:00","2023-10-21 07:00","2023-10-21 18:00","연속"]
[752,"경남","직할","장유마천#1 T/L","154kV 장유-마천T/L 수평 추락방지장치 설치공사","154kV 장유-마천T/L 수평 추락방지장치 설치공사","2023-10-21 07:00","2023-10-21 18:00","2023-10-21 07:00","2023-10-21 18:00","연속"]
[753,"경남","직할","장유마천#1 T/L","154kV 장유-마천T/L 수평 추락방지장치 설치공사","154kV 장유-마천T/L 수평 추락방지장치 설치공사","2023-10-18 07:00","2023-10-18 18:00","2023-10-18 07:00","2023-10-18 18:00","연속"]
[754,"경남","직할","장유마천#2 T/L","154kV 장유-마천T/L 수평 추락방지장치 설치공사","154kV 장유-마천T/L 수평 추락방지장치 설치공사","2023-10-18 07:00","2023-10-18 18:00","2023-10-18 07:00","2023-10-18 18:00","연속"]
[755,"경남","직할","주촌삼계#2 T/L","154kV 주촌-삼계T/L 수평 추락방지장치 설치공사","154kV 주촌-삼계T/L 수평 추락방지장치 설치공사","2023-10-04 07:00","2023-10-10 18:00","2023-10-04 07:00","2023-10-10 18:00","매일"]
[756,"경남","직할","신김해주촌#1 T/L","주촌S/S 154kV 신김해-주촌#1T/L(687) GIS 정밀점검","CB 내부 정밀점검 (병행)신김해S/S 신김해-주촌#1T/L(697) 하자점검 및 PT,LA 보통점검","2023-10-23 09:00","2023-10-24 18:00","2023-10-23 09:00","2023-10-24 18:00","연속"]
[757,"경남","직할","신김해주촌#1 T/L","154kV 신김해-주촌T/L 수평 추락방지장치 설치공사","154kV 신김해-주촌T/L 수평 추락방지장치 설치공사","2023-10-04 07:00","2023-10-10 18:00","2023-10-04 07:00","2023-10-10 18:00","매일"]
[758,"경남","직할","천선진해#2 T/L","154kV 천선-진해T/L 수평 추락방지장치 설치공사","154kV 천선-진해T/L 수평 추락방지장치 설치공사","2023-10-12 07:00","2023-10-13 18:00","2023-10-12 07:00","2023-10-13 18:00","매일"]
[759,"경남","직할","천선진해#1 T/L","154kV 천선-진해T/L 수평 추락방지장치 설치공사","154kV 천선-진해T/L 수평 추락방지장치 설치공사","2023-10-11 07:00","2023-10-12 18:00","2023-10-11 07:00","2023-10-12 18:00","매일"]
[760,"경남","진주","진주개양#2 T/L","154kV 사봉-개양T/L 가공송전선로 정밀점검[#1병가]","154kV 사봉-개양T/L 가공송전선로 정밀점검 #1T/L 52~55호 4회선 철탑 병가구간","2023-10-21 08:30","2023-10-22 18:00","취소","취소","매일"]
[761,"경남","진주","사천개양#1 T/L","[안전작업거리확보 휴전] 154kV 삼천포-사천 추락방지시설 설치공사","154kV 삼천포-사천 #1T /L 병가구간 안전작업거리 확보 휴전 1. 휴전설비 : 삼천포-사천 #1 T/L, 사천-개양 #1T/L 2. 설치대상 - 154kV 삼천포-사천T/L No.13~72호(60호 병가구간) - No.60 작업시 사천-개양 #1 T/L 안전작업거리확보 휴전 필요","2023-10-16 07:30","2023-10-16 18:00","2023-10-16 07:30","2023-10-16 18:00","연속"]
[762,"경남","진주","의령산청 T/L","[안전작업거리확보 휴전] 154kV 의령-동진주 추락방지시설 설치공사","154kV 의령-동진주 #2 T/L 병가구간 안전작업거리 확보 휴전 1. 휴전설비 : 의령-동진주 #2T/L, 의령-산청 T/L 2. 설치대상 - 154kV 의령-동진주T/L No.1~73호(67~73호 병가구간) - No.67~73 작업시 의령-산청 T/L 안전작업거리확보 휴전 필요","2023-10-11 07:30","2023-10-11 18:00","취소","취소","연속"]
[763,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주 #1,2 T/L 철탑 추락방지장치 설치","154kV 의령-동진주 #2 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.1~73 (73기) - 병가구간 : 의령-산청 T/L No.1~7 (10.11 안전작업거리 확보휴전 예정)","2023-10-11 07:30","2023-10-16 18:00","취소","취소","매일"]
[764,"경남","진주","의령동진주#1 T/L","154kV 의령-동진주 #1,2 T/L 철탑 추락방지장치 설치","154kV 의령-동진주 #1 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 수평 추락방지장치 설치 : No.1~73 (73기) - 병가구간 : 의령-함양 T/L No.1~7 (10.4 안전작업거리 확보휴전 예정)","2023-10-04 07:30","2023-10-10 18:00","취소","취소","매일"]
[765,"경남","진주","의령함양 T/L","[안전작업거리확보 휴전] 154kV 의령-동진주 추락방지시설 설치공사","154kV 의령-동진주 #1 T/L 병가구간 안전작업거리 확보 휴전 1. 휴전설비 : 의령-동진주 #1T/L, 의령-함양SA T/L 2. 설치대상 - 154kV 의령-동진주T/L No.1~73호(67~73호 병가구간) - No.67~73 작업시 의령-함양 T/L 안전작업거리확보 휴전 필요","2023-10-04 07:30","2023-10-04 18:00","취소","취소","연속"]
[766,"경남","진주","진주개양#2 T/L","진주S/S 154lkV 옥외철구 설비 GIS화 관련 송전선로 인출변경","진주-개양 #2T/L 송전선로 인출변경(옥외철구 → GIS)","2023-10-23 08:00","2023-10-27 18:00","2023-10-23 08:00","2023-10-27 18:00","연속"]
[767,"경남","진주","동진주진주#2 T/L","진주S/S 154lkV 옥외철구 설비 GIS화 관련 송전선로 인출변경","동진주-진주 #2T/L 송전선로 인출변경(옥외철구 → GIS)","2023-10-23 08:00","2023-10-27 18:00","2023-10-23 08:00","2023-10-27 18:00","연속"]
[768,"경남","진주","광양하동#1 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-10-04 07:00","2023-10-04 14:00","2023-10-04 07:00","2023-10-04 14:00","연속"]
[769,"경남","진주","하동개양#1 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-10-04 14:00","2023-10-05 18:00","2023-10-04 14:00","2023-10-05 18:00","매일"]
[770,"경남","진주","하동개양#1 T/L","'22~'23년 가공송전 협력회사 총액공사","154kV 하동-개양T/L 수평추락방지장치 설치 시행","2023-10-16 07:00","2023-10-22 18:00","2023-10-16 07:00","2023-10-22 18:00","매일"]
[771,"경남","진주","하동개양#2 T/L","'22~'23년 가공송전 협력회사 총액공사","154kV 하동-개양T/L 수평추락방지장치 설치 시행","2023-10-21 07:00","2023-10-22 18:00","2023-10-21 07:00","2023-10-22 18:00","매일"]
[772,"경남","진주","하동개양#2 T/L","'22~'23년 가공송전 협력회사 총액공사","154kV 하동-개양T/L 수평추락방지장치 설치 시행","2023-10-30 07:00","2023-10-31 18:00","2023-10-30 07:00","2023-10-31 18:00","매일"]
[773,"경남","진주","합천합천수력#1 T/L","[안전작업거리확보 휴전] 154kV 거창-합천 추락방지시설 설치공사","154kV 거창-합천 T/L 병가구간 안전작업거리 확보 휴전 1. 휴전설비 : 거창-합천 #2T/L, 합천수력 #1T/L 2. 설치대상 - 154kV 거창-합천T/L No.1~3, 5~74.1, 76~82호(5호 병가구간) - No.5 작업시 합천수력 #1 T/L 안전작업거리확보 휴전 필요","2023-10-11 09:00","2023-10-11 18:00","취소","취소","연속"]
[774,"경남","진주","합천합천수력#2 T/L","[안전작업거리확보 휴전] 154kV 거창-합천 추락방지시설 설치공사","154kV 거창-합천 T/L 병가구간 안전작업거리 확보 휴전 1. 휴전설비 : 거창-합천 #1T/L, 합천수력 #2T/L 2. 설치대상 - 154kV 거창-합천T/L No.1~3, 5~74.1, 76~82호(5호 병가구간) - No.5 작업시 합천수력 #2 T/L 안전작업거리확보 휴전 필요","2023-10-04 09:00","2023-10-04 18:00","취소","취소","연속"]
[775,"경남","통영","신고성거제#2 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-10-07 14:00","2023-10-08 18:00","2023-10-07 14:00","2023-10-08 18:00","매일"]
[776,"경남","통영","고성안정#2 T/L","통영복합S/Y 154kV 한국가스공사T/L 신규수용공사","1. GIS(170kV 50kA 1,250A) x 1CCT 설치 2. 기타 부대공사 x 1식\n(안정통영복합#2T/L)","2023-10-31 09:00","2023-11-03 18:00","2023-10-31 09:00","2023-11-03 18:00","연속"]
[777,"경남","함안","동읍진영#1 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-10-12 14:00","2023-10-12 18:00","2023-10-12 14:00","2023-10-12 18:00","연속"]
[778,"경남","함안","동읍진영#2 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-10-12 07:00","2023-10-12 14:00","2023-10-12 07:00","2023-10-12 14:00","연속"]
[779,"경남","함안","매리김해#1 T/L","154kV 매리-김해T/L 수평 추락방지장치 설치공사","154kV 매리-김해T/L 수평 추락방지장치 설치공사","2023-10-14 07:00","2023-10-15 18:00","2023-10-14 07:00","2023-10-15 18:00","매일"]
[780,"경남","함안","호포매리#1 T/L","154kV 호포-매리T/L 수평 추락방지장치 설치공사","154kV 호포-매리T/L 수평 추락방지장치 설치공사","2023-10-14 07:00","2023-10-15 18:00","2023-10-14 07:00","2023-10-15 18:00","매일"]
[781,"경남","함안","한림정삼계#1 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9-14호 이도 재조정 및 14호 철탑암 교체 공사","2023-10-14 07:00","2023-10-15 18:00","취소","취소","연속"]
[782,"경남","함안","삼계어방#2 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9-14호 이도 재조정 및 14호 철탑암 교체 공사","2023-10-14 07:00","2023-10-15 18:00","취소","취소","연속"]
[783,"경남","함안","삼계어방#1 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9-14호 이도 재조정 및 14호 철탑암 교체 공사","2023-10-21 07:00","2023-10-22 18:00","취소","취소","연속"]
[784,"경남","함안","한림정삼계#2 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9-14호 이도 재조정 및 14호 철탑암 교체 공사","2023-10-21 07:00","2023-10-22 18:00","취소","취소","연속"]
[785,"경남","함안","진영수산#2 T/L","수산S/S 154kV 진영수산#2 T/L 발청보수","154kV GIS 발청베어링 보수","2023-10-16 09:30","2023-10-16 13:30","2023-10-16 09:30","2023-10-16 13:30","연속"]
[786,"경남","함안","진영수산#1 T/L","수산S/S 154kV 진영수산#1 T/L 발청보수","154kV GIS 발청베어링 보수","2023-10-13 13:30","2023-10-13 17:30","2023-10-13 13:30","2023-10-13 17:30","연속"]
[787,"경남","함안","진영수산#1 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-10-12 14:00","2023-10-12 18:00","2023-10-12 14:00","2023-10-12 18:00","연속"]
[788,"경남","함안","진영수산#2 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-10-12 07:00","2023-10-12 14:00","2023-10-12 07:00","2023-10-12 14:00","연속"]
[789,"경남","함안","창녕구지#1 T/L","창녕S/S 154kV GIS화 공사(창녕-구지#1T/L 인출변경)","○창녕S/S 154kV GIS화 공사(창녕-구지#1T/L 인출변경) ○창녕-구지#1T/L 보호반 개조공사","2023-10-07 08:30","2023-10-11 18:00","2023-10-16 08:30","2023-10-20 18:00","연속"]
[790,"경남","함안","칠서창녕#1 T/L","창녕S/S 154kV GIS화 공사(칠서-창녕#1,2T/L 인출변경)","창녕S/S 154kV GIS화 공사(칠서-창녕#1,2T/L 동시 휴전 후 인출변경) ○칠서-창녕#1,2T/L 보호반 개조공사","2023-10-02 08:30","2023-10-06 18:00","2023-10-09 08:30","2023-10-13 18:00","연속"]
[791,"경남","함안","창녕구지#2 T/L","창녕S/S 154kV GIS화 공사(창녕-구지#2T/L 인출변경)","○창녕S/S 154kV GIS화 공사(창녕-구지#2T/L 인출변경) ○20호 철탑 창녕~구지 점퍼선 분리작업","2023-10-07 08:30","2023-10-07 14:00","2023-10-14 08:30","2023-10-29 15:00","연속"]
[792,"경남","함안","창녕초동#1 T/L","2022~23년도 함안전력 송전정비회사 총액공사 피뢰기 설치","154kV 창녕-초동#1T/L 피뢰기 설치(1~7호)","2023-10-14 08:30","2023-10-15 15:00","2023-10-14 08:30","2023-10-15 15:00","연속"]
[793,"경남","함안","창녕초동#1 T/L","창녕S/S 154kV GIS화 공사(창녕-초동#1,2T/L 인출변경)","창녕S/S 154kV GIS화 공사(창녕-초동#1,2T/L 동시 휴전 후 인출변경) ○창녕-초동 #1,2T/L PNL 교체공사","2023-10-16 08:30","2023-10-20 18:00","2023-10-30 08:30","2023-11-03 08:30","연속"]
[794,"경남","함안","창녕초동#2 T/L","창녕S/S 154kV GIS화 공사(창녕-초동#1,2T/L 인출변경)","창녕S/S 154kV GIS화 공사(창녕-초동#1,2T/L 동시 휴전 후 인출변경) ○창녕-초동 #1,2T/L PNL 교체공사","2023-10-16 08:30","2023-10-20 18:00","2023-10-30 08:30","2023-11-03 18:00","연속"]
[795,"경남","함안","칠서창녕#2 T/L","창녕S/S 154kV GIS화 공사(칠서-창녕#1,2T/L 인출변경)","창녕S/S 154kV GIS화 공사(칠서-창녕#1,2T/L 동시 휴전 후 인출변경) ○칠서-창녕#1,2T/L 보호반 개조공사","2023-10-02 08:30","2023-10-06 18:00","2023-10-09 08:30","2023-10-13 18:00","연속"]
[796,"경남","함안","진영한림정#2 T/L","한림정S/S 154kV 진영한림정#2 T/L 발청보수","154kV GIS 발청베어링 보수","2023-10-07 13:30","2023-10-07 17:30","2023-10-07 13:30","2023-10-07 17:30","연속"]
[797,"경남","함안","진영한림정#1 T/L","한림정S/S 154kV 진영한림정#1 T/L 발청보수","154kV GIS 발청베어링 보수","2023-10-07 09:30","2023-10-07 13:30","2023-10-07 09:30","2023-10-07 13:30","연속"]
[798,"경남","함안","한림정삼계#2 T/L","한림정S/S 154kV 한림정삼계#2 T/L 발청보수","154kV GIS 발청베어링 보수","2023-10-06 09:30","2023-10-06 17:30","2023-10-06 09:30","2023-10-06 17:30","연속"]
[799,"경남","함안","한림정삼계#1 T/L","한림정S/S 154kV 한림정삼계#1 T/L 발청보수","154kV GIS 발청베어링 보수","2023-10-05 13:30","2023-10-05 17:30","2023-10-05 13:30","2023-10-05 17:30","연속"]
[800,"부산울산",null,"명례고리NP T/L","고리1호기 제3차 영구정지 정기검사 ○ 조작차단기 : CB-617, DS-616, DS-615, ES-101, CB-6183, DS-6185, ES-102","○ 고리1발전소 154kV 스위치야드 설비 일반점검","2023-10-04 09:00","2023-11-03 18:00","2023-10-04 09:00","2023-11-03 18:00","연속"]