{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":13,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"765설비","index":0,"n_rows":18,"n_cols":11,"rows_kept":18,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 11월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신태백신가평#2 T/L","송전선로 단상재폐로 결상회로 개선","송운(변전)-1085 (21.10.19) 「송전선로 단상 자동재투입용 GIS 결상회로 개선 시행 알림」 관련 유사고장 재발방지","2023-11-28 09:00","2023-11-29 18:00","취소","취소","연속"]
[2,"경기북부","구리","신가평S/S #3 M.Tr","23년도 신가평S/S 765kV M.Tr 보통점검공사","신가평S/S 765kV #3M.Tr 보통점검","2023-11-13 09:00","2023-11-24 18:00","2023-11-13 09:00","2023-11-24 18:00","연속"]
[3,"경기북부","구리","신가평S/S #2 M.Tr","765kV #2M.Tr 예방진단시스템 부싱어댑터 설치","765kV #2M.Tr 예방진단시스템 부싱어댑터 설치","2023-11-29 09:00","2023-11-30 18:00","2023-11-29 09:00","2023-11-30 18:00","연속"]
[4,"경기북부","구리","신가평S/S #1 M.Tr","23년도 신가평S/S 765kV M.Tr 보통점검공사","신가평S/S 765kV #1M.Tr 보통점검","2023-11-06 09:00","2023-11-10 18:00","2023-11-06 09:00","2023-11-10 18:00","연속"]
[5,"경기","성남","신안성S/S #2 M.Tr","23년 성남전력 765kV M.Tr 보통점검공사","- #2M.Tr 보통점검","2023-11-01 09:00","2023-11-14 18:00","2023-11-01 09:00","2023-11-14 18:00","연속"]
[6,"강원","태백","신태백S/S #3 M.Tr","2023년 태백전력지사 변전협력회사 총액공사","신태백S/S 345kV 76BAY B/F 보호반 교체","2023-11-23 09:00","2023-12-08 18:00","취소","취소","연속"]
[7,"강원","태백","신태백S/S #2 BUS","2023년 태백전력지사 변전협력회사 총액공사","신태백S/S 765kV #2BUS B/P PNL 교체","2023-11-01 10:00","2023-11-08 18:00","취소","취소","연속"]
[8,"강원","태백","신태백S/S #1 BUS","2023년 태백전력지사 변전협력회사 총액공사","신태백S/S 765kV #1BUS B/P PNL 교체","2023-11-09 10:00","2023-11-16 18:00","취소","취소","연속"]
[9,"대전세종충남","서산","당진T/P Tie-Tr","당진화력S/S 765kV #1TIE-Tr B상 교체공사","(10월 휴전 취소시) 당진화력S/S 765kV #1TIE-Tr B상 교체공사 (병행) 당진화력S/S 765kV #1TIE-Tr B상 1,2차 GIB 교체공사 (장대현)","2023-11-01 09:00","2023-12-01 18:00","2023-10-29 09:00","2023-11-24 18:00","연속"]
[10,"대전세종충남","서산","신서산당진TP#1 T/L","당진화력S/S 765kV #1TIE-Tr B상 교체공사","(10월 휴전 취소시) 안전이격거리 확보를 위한 신서산-당진화력#1T/L 휴전","2023-11-01 09:00","2023-11-01 18:00","2023-10-29 09:00","2023-10-29 18:00","연속"]
[11,"대전세종충남","서산","신서산신중부#1 T/L","23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 765kV 85Bay B/F 보호반 대체","2023-11-23 09:00","2023-12-01 18:00","취소","취소","연속"]
[12,"대전세종충남","서산","신서산S/S #4 M.Tr","23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 765kV 85Bay, 345kV 78 Bay B/F 보호반 대체","2023-11-13 09:00","2023-12-01 18:00","취소","취소","연속"]
[13,"대전세종충남","서산","신서산당진TP#1 T/L","2023년도 가공송전 순시점검 위탁공사","765kV 신서산-당진화력#1T/L 정밀점검(주말제외) - No.1~90","2023-11-06 08:00","2023-11-17 18:00","취소","취소","매일"]
[14,"대전세종충남","서산","신서산S/S #1 BUS","'23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 765kV #1BUS 보호반 대체","2023-11-06 09:00","2023-11-10 18:00","취소","취소","연속"]

{"sheet":"345설비","index":1,"n_rows":396,"n_cols":11,"rows_kept":396,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]],"flags":["formulas_cached_only"]}
["2023년도 11월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #4 M.Tr","2023년 성동P/O 변전협력회사 총액공사","- M.Tr, 3차 LA, 3차 PT 보통점검 - 170kV GIS 조작시험","2023-11-15 10:00","2023-11-16 18:00","2023-11-23 10:00","2023-11-24 18:00","연속"]
[2,"서울","성동","성동S/S #1 Sh.R CB","2023년 성동P/O 변전협력회사 총액공사","- 불량 공조 FAN 교체","2023-11-07 10:00","2023-11-10 18:00","취소","취소","연속"]
[3,"서울","중부","중부S/S #1 Sh.R CB","22-23년 중부P/O 총액공사","1Sh.R 스탑밸브 보수","2023-11-22 10:00","2023-11-22 14:00","2023-11-22 10:00","2023-11-22 14:00","연속"]
[4,"서울","중부","중부S/S #2 Sh.R CB","22-23년 중부P/O 총액공사","2Sh.R 1차 GIS 유면계 교체","2023-11-22 14:00","2023-11-22 18:00","2023-11-22 14:00","2023-11-22 18:00","연속"]
[5,"서울","중부","중부S/S #1 M.Tr","22-23년 중부P/O 총액공사","6161 DS 전자변 누기보수","2023-11-20 10:00","2023-11-20 18:00","2023-11-20 10:00","2023-11-20 18:00","연속"]
[6,"남서울","동서울","동서울S/S #4 M.Tr","동서울S/S #4M.Tr 보통점검","2023년 주변압기 점검공사","2023-11-20 09:00","2023-11-21 18:00","2023-11-20 09:00","2023-11-21 18:00","연속"]
[7,"남서울","동서울","신성남동서울#2 T/L","22~23년 동서울 가공송전 협력회사 총액공사","(병가철탑)추락방지장치/피뢰기 설치","2023-11-14 07:00","2023-11-15 18:00","2023-11-14 07:00","2023-11-15 18:00","매일"]
[8,"남서울","동서울","동서울S/S #3 M.Tr","동서울S/S #3M.Tr 보통점검","2023년 주변압기 점검공사","2023-11-06 09:00","2023-11-08 14:00","2023-11-06 09:00","2023-11-08 14:00","연속"]
[9,"남서울","동서울","동서울미금#2 T/L","'23~'24년 동서울 지중 위탁 총액공사","#16C/T 피뢰기 점검","2023-11-01 08:00","2023-11-01 18:00","2023-11-01 08:00","2023-11-01 18:00","연속"]
[10,"남서울","동서울","신성남동서울#1 T/L","22~23년 동서울 가공송전 협력회사 총액공사","(병가철탑)추락방지장치/피뢰기 설치","2023-11-22 07:00","2023-11-23 18:00","2023-11-22 07:00","2023-11-23 18:00","매일"]
[11,"남서울","동서울","동서울미금#1 T/L","'23~'24년 동서울 지중 위탁 총액공사","#16C/T 피뢰기 점검","2023-11-01 08:00","2023-11-01 18:00","2023-11-01 08:00","2023-11-01 18:00","연속"]
[12,"남서울","영등포","서서울신광명#1 T/L","345kV 서서울-신광명T/L 지장송전선로 이설공사","이설구간 : 철탑No.38~42, 2.2km(이설 1기, 인클로징 2기, 보강 2기) 전력선 : STACIR 480㎟ × 2B × 2C 가공선 : ACSR 120㎟ 1조, OPGW 100㎟ 1조","2023-11-21 09:00","2023-11-30 18:00","취소","취소","연속"]
[13,"남서울","영등포","서서울신광명#2 T/L","345kV 서서울-신광명T/L 지장송전선로 이설공사","이설구간 : 철탑No.38~42, 2.2km(이설 1기, 인클로징 2기, 보강 2기) 전력선 : STACIR 480㎟ × 2B × 2C 가공선 : ACSR 120㎟ 1조, OPGW 100㎟ 1조","2023-11-11 09:00","2023-11-20 18:00","취소","취소","연속"]
[14,"남서울","영등포","신광명S/S #4 M.Tr","신광명S/S 4M.Tr 3차측 23kV EGIS 설치공사","- 4M.Tr 3차측 EGIS 설치공사 - 전력케이블 포설 및 접속공사 - 4M.Tr 3차측 철거 및 기기기초 등 일반공사","2023-11-01 09:00","2023-11-15 18:00","취소","취소","연속"]
[15,"남서울","영등포","신광명S/S #70 BUS","신광명S/S 345kV Sh.R 설치 관련 가공지선 이설","신광명S/S 345kV Sh.R 설치 관련 가공지선 이설","2023-11-04 09:00","2023-11-05 18:00","2023-11-04 09:00","2023-11-05 18:00","연속"]
[16,"남서울","영등포","신시흥신광명#2 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지설치, 피뢰기설치","2023-11-01 07:00","2023-11-09 18:00","취소","취소","연속"]
[17,"인천","김포","신김포신파주#2 T/L","23년 가공송전 협력회사 총액공사","수평 추락방지시설 설치","2023-11-05 08:00","2023-11-05 18:00","2023-11-05 08:00","2023-11-05 18:00","연속"]
[18,"인천","김포","신김포S/S #1 M.Tr","신김포S/S 345kV #1M.Tr 보통점검","신김포S/S 345kV #1M.Tr 보통점검","2023-11-07 09:00","2023-11-08 18:00","2023-11-07 09:00","2023-11-08 18:00","연속"]
[19,"인천","김포","신김포S/S #2 M.Tr","신김포S/S 345kV #2M.Tr 보통점검","신김포S/S 345kV #2M.Tr 보통점검","2023-11-09 09:00","2023-11-10 18:00","2023-11-09 09:00","2023-11-10 18:00","연속"]
[20,"인천","김포","신김포S/S #2 Sh.R CB","신김포S/S 345kV #2Sh.R 보통점검","신김포S/S 345kV #2Sh.R 보통점검","2023-11-13 09:00","2023-11-14 18:00","취소","취소","연속"]
[21,"인천","김포","신김포신파주#1 T/L","23년 가공송전 협력회사 총액공사","수평 추락방지시설 설치","2023-11-04 08:00","2023-11-04 18:00","2023-11-04 08:00","2023-11-04 18:00","연속"]
[22,"인천","김포","신김포S/S CB 7471","신김포S/S 345kV 신김포-신인천CC T/L GIS 보통점검","신김포S/S 345kV 신김포-신인천CC T/L(7471) GIS 보통점검","2023-11-22 09:00","2023-11-22 18:00","2023-11-22 09:00","2023-11-22 18:00","연속"]
[23,"인천","김포","신김포S/S #4 Sh.R CB","신김포S/S 345kV #4Sh.R 보통점검","신김포S/S 345kV #4Sh.R 보통점검","2023-11-22 09:00","2023-11-23 18:00","취소","취소","연속"]
[24,"인천","김포","신김포S/S CB 7400","신김포S/S 345kV 7400 GIS 보통점검","신김포S/S 345kV 신김포신인천CC T/L-#2M.Tr 1차 TIE(7400) GIS 보통점검","2023-11-23 09:00","2023-11-23 18:00","2023-11-23 09:00","2023-11-23 18:00","연속"]
[25,"인천","김포","신김포S/S #3 Sh.R CB","신김포S/S 345kV #3Sh.R 보통점검","신김포S/S 345kV #3Sh.R 보통점검","2023-11-20 09:00","2023-11-21 18:00","취소","취소","연속"]
[26,"인천","부평","서인천C/C CB 7271","서인천C/C 345kV 신경서-서인천CC T/L 7271GIS 조작시험","서인천C/C 345kV 신경서-서인천CC T/L 7271GIS 조작시험","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[27,"인천","부평","서인천C/C #1 Sh.R CB","서인천C/C 345kV #1 Sh.R 1차 7379GIS 조작시험","서인천C/C 345kV #1 Sh.R 1차 7379GIS 조작시험","2023-11-06 09:00","2023-11-06 18:00","2023-11-06 09:00","2023-11-06 18:00","연속"]
[28,"인천","부평","서인천C/C CB 7471","서인천C/C 345kV 서인천CC-신부평#3T/L 7471GIS 조작시험","서인천C/C 345kV 서인천CC-신부평#3T/L 7471GIS 조작","2023-11-06 09:00","2023-11-06 18:00","2023-11-06 09:00","2023-11-06 18:00","연속"]
[29,"인천","부평","서인천C/C #2 Sh.R CB","서인천C/C 345kV #2 Sh.R 1차 7479GIS 조작시험","서인천C/C 345kV #2 Sh.R 1차 7479GIS 조작시험","2023-11-09 09:00","2023-11-09 12:00","2023-11-09 09:00","2023-11-09 12:00","연속"]
[30,"인천","부평","서인천C/C #4 Sh.R CB","서인천C/C 345kV #4 Sh.R 1차 7A79 GIS 조작시험","서인천C/C 345kV #4 Sh.R 1차 7A79 GIS 조작시험","2023-11-09 13:00","2023-11-09 18:00","2023-11-09 13:00","2023-11-09 18:00","연속"]
[31,"인천","부평","서인천C/C #3 Sh.R CB","서인천C/C 345kV #3 Sh.R 1차 7B79GIS 조작시험","서인천C/C 345kV #3 Sh.R 1차 7B79GIS 조작시험","2023-11-10 09:00","2023-11-10 18:00","2023-11-10 09:00","2023-11-10 18:00","연속"]
[32,"인천","부평","서인천CC신인천CC#1 T/L","서인천C/C 345kV #70-72 CLR #7077 GIS 조작시험","서인천C/C 345kV #70-72 CLR #7077 GIS 조작시험","2023-11-13 09:00","2023-11-13 18:00","2023-11-13 09:00","2023-11-13 18:00","연속"]
[33,"인천","부평","서인천C/C CB 7277","서인천C/C 345kV #70-72 CLR #7277 GIS 조작시험","서인천C/C 345kV #70-72 CLR #7277 GIS 조작시험","2023-11-13 09:00","2023-11-13 18:00","취소","취소","연속"]
[34,"인천","부평","서인천CC신인천CC#2 T/L","서인천C/C 345kV #75-77 CLR #7577 GIS 조작시험","서인천C/C 345kV #75-77 CLR #7577 GIS 조작시험","2023-11-14 09:00","2023-11-14 18:00","2023-11-14 09:00","2023-11-14 18:00","연속"]
[35,"인천","부평","서인천C/C CB 7777","서인천C/C 345kV #75-77 CLR #7777 GIS 조작시험","서인천C/C 345kV #75-77 CLR #7777 GIS 조작시험","2023-11-14 09:00","2023-11-14 18:00","취소","취소","연속"]
[36,"인천","부평","신가좌S/S CB 7471","신가좌S/S 345kV 신가좌-신시흥#2T/L 7471 GIS 조작시험","신가좌S/S 345kV 신가좌-신시흥#2T/L 7471 GIS 조작시험","2023-11-15 09:00","2023-11-15 18:00","취소","취소","연속"]
[37,"인천","부평","신가좌S/S CB 7400","신가좌신시흥#2T/L-#3 M.Tr 1차 TIE 7400GIS 조작시험","신가좌신시흥#2T/L-#3 M.Tr 1차 TIE 7400GIS 조작시험","2023-11-15 09:00","2023-11-15 18:00","취소","취소","연속"]
[38,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S 345kV #3 M.Tr 휴전작업","신가좌S/S 345kV #3 M.Tr 휴전작업","2023-11-01 09:00","2023-11-03 18:00","취소","취소","연속"]
[39,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S 345kV #4 M.Tr 휴전작업","신가좌S/S 345kV #4 M.Tr 휴전작업","2023-11-04 09:00","2023-11-05 18:00","취소","취소","연속"]
[40,"인천","부평","신가좌S/S #1 M.Tr","신가좌S/S 345kV #1 M.Tr 보호반 대체공사","신가좌S/S 345kV #1 M.Tr 보호반 대체공사","2023-11-20 09:00","2023-11-24 18:00","취소","취소","연속"]
[41,"인천","부평","신경서S/S #2 M.Tr","신경서S/S 345kV #2 M.Tr 3차 4289CB 보통점검","신경서S/S 345kV #2 M.Tr 3차 4289CB 보통점검","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[42,"인천","부평","신경서S/S CB 7172","신경서S/S 345kV #1 M.Tr 1차 7172GIS 보통점검","신경서S/S 345kV #1 M.Tr 1차 7172GIS 보통점검","2023-11-01 09:00","2023-11-01 18:00","2023-11-01 09:00","2023-11-01 18:00","연속"]
[43,"인천","부평","신인천C/C CB 7872","신인천C/C 345kV 4MT201 7872GIS 조작시험","신인천C/C 345kV 4MT201 7872GIS 조작시험","2023-11-11 13:00","2023-11-11 18:00","2023-11-11 13:00","2023-11-11 18:00","연속"]
[44,"인천","부평","신인천C/C CB 7900","신인천C/C 345kV 4MT001 TIE 7900GIS 조작시험","신인천C/C 345kV 4MT001 TIE 7900GIS 조작시험","2023-11-11 09:00","2023-11-11 13:00","2023-11-11 09:00","2023-11-11 13:00","연속"]
[45,"인천","부평","신인천C/C CB 7772","신인천C/C 345kV 4MT101 7772GIS 조작시험","신인천C/C 345kV 4MT101 7772GIS 조작시험","2023-11-10 09:00","2023-11-10 18:00","2023-11-10 09:00","2023-11-10 18:00","연속"]
[46,"인천","부평","신인천C/C CB 7972","신인천C/C 345kV 4MT001 7972 GIS 조작시험","신인천C/C 345kV 4MT001 7972 GIS 조작시험","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[47,"인천","부평","신인천C/C SEC CB 71720","신인천C/C 345kV #71-#72 SEC GIS 조작시험","신인천C/C 345kV #71-#72 SEC GIS 조작시험","2023-11-25 09:00","2023-11-25 18:00","2023-11-25 09:00","2023-11-25 18:00","연속"]
[48,"인천","부평","신인천C/C SEC CB 76770","신인천C/C 345kV #76-#77 SEC GIS 조작시험","신인천C/C 345kV #76-#77 SEC GIS 조작시험","2023-11-22 13:00","2023-11-22 18:00","2023-11-22 13:00","2023-11-22 18:00","연속"]
[49,"인천","부평","신인천C/C SEC CB 75760","신인천C/C 345kV #75-#76 SEC GIS 조작시험","신인천C/C 345kV #75-#76 SEC GIS 조작시험","2023-11-22 09:00","2023-11-22 13:00","2023-11-22 09:00","2023-11-22 13:00","연속"]
[50,"인천","부평","신인천C/C SEC CB 70710","신인천C/C 345kV #70-#71 SEC GIS 조작시험","신인천C/C 345kV #70-#71 SEC GIS 조작시험","2023-11-21 09:00","2023-11-21 18:00","2023-11-21 09:00","2023-11-21 18:00","연속"]
[51,"인천","부평","신김포신인천CC T/L","신인천CC 345kV 신김포신인천T/L 보호반 대체 공사","신인천CC 345kV 신김포신인천T/L 보호반 대체 공사","2023-11-20 09:00","2023-11-24 18:00","취소","취소","연속"]
[52,"인천","부평","인천C/C SEC CB 70710","인천CC S/Y 345kV #70-#71 SEC GIS 조작시험","인천CC S/Y 345kV #70-#71 SEC GIS 조작시험","2023-11-21 13:00","2023-11-21 18:00","2023-11-21 13:00","2023-11-21 18:00","연속"]
[53,"인천","부평","인천C/C SEC CB 75760","인천CC S/Y 345kV #75-#76 SEC GIS 조작시험","인천CC S/Y 345kV #75-#76 SEC GIS 조작시험","2023-11-21 09:00","2023-11-21 13:00","2023-11-21 09:00","2023-11-21 13:00","연속"]
[54,"인천","부평","인천C/C CB 7C71","인천CC S/Y가정-인천CC#2T/L 7C71 GIS 조작시험","인천CC S/Y 345kV 가정-인천CC#2T/L 7C71 GIS 조작시험","2023-11-20 13:00","2023-11-20 18:00","2023-11-20 13:00","2023-11-20 18:00","연속"]
[55,"인천","부평","인천C/C CB 7471","인천CC 345kV 신경서-인천CC#2T/L 7471GIS 조작시험","인천CC 345kV 신경서-인천CC#2T/L 7471GIS 조작시험","2023-11-23 09:00","2023-11-23 18:00","2023-11-23 09:00","2023-11-23 18:00","연속"]
[56,"인천","부평","인천C/C CB 7B00","인천CC S/Y 345kV TIE 7B00GIS 조작시험","인천CC S/Y 345kV TIE 7B00GIS 조작시험","2023-11-24 09:00","2023-11-24 18:00","2023-11-24 09:00","2023-11-24 18:00","연속"]
[57,"인천","부평","인천C/C CB 7A72","인천CC S/Y포스코S/Y-인천CC#2T/L 7A72GIS 조작시험","인천CC S/Y포스코S/Y-인천CC#2T/L 7A72GIS 조작시험","2023-11-24 09:00","2023-11-24 18:00","2023-11-24 09:00","2023-11-24 18:00","연속"]
[58,"인천","부평","인천C/C CB 7A00","인천CC포스코S/Y인천CC#1-#2T/L TIE 7a00GIS 조작시험","인천CC포스코S/Y인천CC#1-#2T/L TIE 7a00GIS 조작시험","2023-11-23 09:00","2023-11-23 18:00","2023-11-23 09:00","2023-11-23 18:00","연속"]
[59,"인천","부평","인천C/C CB 7B72","인천CC S/Y 345kV 인천복합 #3S/T 7B72GIS 조작시험","인천CC S/Y 345kV 인천복합 #3S/T 7B72GIS 조작시험","2023-11-20 09:00","2023-11-20 12:00","2023-11-20 09:00","2023-11-20 12:00","연속"]
[60,"인천","시흥","신시화S/S CB 7400","345kV 신시화S/S 건설공사","최초가압","2023-11-01 09:00","2023-11-03 18:00","2023-11-01 09:00","2023-11-03 18:00","연속"]
[61,"인천","시흥","신시화S/S # 3 M.Tr","345kV 신시화S/S 건설공사","#1S.Tr 전력케이블 설치","2023-11-13 09:00","2023-11-15 09:00","2023-11-13 09:00","2023-11-15 09:00","연속"]
[62,"인천","시흥","신시화S/S #1 BUS","345kV 신시화S/S 건설공사","345kV 신시화S/S 초기가압","2023-11-01 09:00","2023-11-02 09:00","2023-11-01 09:00","2023-11-02 09:00","연속"]
[63,"인천","시흥","신시화S/S CB 7471","345kV 신시화S/S 건설공사","최초가압","2023-11-01 09:00","2023-11-03 18:00","2023-11-01 09:00","2023-11-03 18:00","연속"]
[64,"인천","시흥","신가좌신시흥#1 T/L","345kV 시흥장현지구 C/T 건설공사","○ 공사내용 - 철탑신설 : 2기(No.58, 59) - C/T신설 : 동측, 서측 - 전력선 가선 : No.57~동측C/T, 서측C/T~No.61","2023-11-06 07:00","2023-11-13 18:00","2023-11-06 07:00","2023-11-13 18:00","연속"]
[65,"인천","시흥","신시흥신광명#1 T/L","345kV 시흥장현지구 C/T 건설공사","○ 공사내용 - 철탑신설 : 2기(No.58, 59) - C/T신설 : 동측, 서측 - 전력선 가선 : No.57~동측C/T, 서측C/T~No.61","2023-11-06 07:00","2023-11-13 18:00","2023-11-06 07:00","2023-11-13 18:00","연속"]
[66,"인천","시흥","신가좌신시흥#2 T/L","345kV 시흥장현지구 C/T 건설공사","○ 공사내용 - 철탑신설 : 2기(No.58, 59) - C/T신설 : 동측, 서측 - 전력선 가선 : No.57~동측C/T, 서측C/T~No.61","2023-11-14 07:00","2023-11-21 18:00","2023-11-14 07:00","2023-11-21 18:00","연속"]
[67,"인천","시흥","신시흥신광명#2 T/L","345kV 시흥장현지구 C/T 건설공사","○ 공사내용 - 철탑신설 : 2기(No.58, 59) - C/T신설 : 동측, 서측 - 전력선 가선 : No.57~동측C/T, 서측C/T~No.61","2023-11-14 07:00","2023-11-21 18:00","2023-11-14 07:00","2023-11-21 18:00","연속"]
[68,"인천","시흥","신시흥신안산#2 T/L","345kV 신시화S/S 건설공사","345kV 신시화S/S 초기가압","2023-11-01 09:00","2023-11-02 09:00","2023-10-26 09:00","2023-10-27 09:00","연속"]
[69,"인천","시흥","신시흥S/S #70 BUS","345kV 신시화S/S 건설공사","345kV 신시화S/S 초기가압","2023-11-01 09:00","2023-11-02 09:00","2023-10-26 09:00","2023-10-27 09:00","연속"]
[70,"인천","직할","서인천CC신부평#4 T/L","345kV 서인천CC-신부평#4T/L OF케이블 절연유 채유","345kV 서인천CC-신부평#4T/L OF케이블 절연유 채유 - 서인천EBG ~ J/B#20(17개소)","2023-11-11 09:00","2023-11-12 18:00","취소","취소","연속"]
[71,"경기북부","고양","신덕은S/S LG디스플레이1T/L CB","22~23년 변전협력회사 총액공사","362kV GIS 보통점검(7071, 7000 GIS)","2023-11-06 09:00","2023-11-07 18:00","2023-11-06 09:00","2023-11-07 18:00","연속"]
[72,"경기북부","고양","신덕은S/S LG디스플레이2T/L CB","22~23년 변전협력회사 총액공사","362kV GIS 보통점검(7072 GIS)","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[73,"경기북부","고양","신파주S/S #3 M.Tr","신파주S/S 345kV 주변압기 보통점검공사","신파주S/S #3M.Tr A,B,C상 보통점검 및 절연유 여과","2023-11-06 09:00","2023-11-10 18:00","2023-11-20 08:30","2023-11-30 18:00","연속"]
[74,"경기북부","구리","미금S/S #3 M.Tr","미금S/S 154kV #62-67 모선보호반 교체공사","미금S/S 154kV #62-67 모선보호반 교체공사","2023-11-20 09:00","2023-11-24 18:00","2023-11-20 09:00","2023-11-24 18:00","연속"]
[75,"경기북부","구리","신포천S/S CB 7571","2022~23 구리전력 변전협력 총액공사","신포천S/S 345kV신포천-동두천CC #1T/L GIS 보통점검 7571","2023-11-01 09:00","2023-11-01 18:00","2023-11-01 09:00","2023-11-01 18:00","연속"]
[76,"경기북부","구리","신포천S/S CB 7372","2022~23 구리전력 변전협력 총액공사","신포천S/S #1Sh.R GIS 보통점검 7379","2023-11-02 09:00","2023-11-02 18:00","2023-11-02 09:00","2023-11-02 18:00","연속"]
[77,"경기북부","구리","신가평포천LNGCC#2 T/L","22~23년 구리전력 변전협력 총액공사","포천LNG 345kV 신가평-포천LNG #2T/L GIS 방수처리 - 부싱 인출부 방수처리","2023-11-27 09:00","2023-11-28 18:00","2023-11-27 09:00","2023-11-28 18:00","연속"]
[78,"경기북부","구리","신포천포천LNGCC#2 T/L","22~23년 구리전력 변전협력 총액공사","포천LNG 345kV 신포천-포천LNG #2T/L GIS 방수처리 - 부싱 인출부 방수처리","2023-11-20 09:00","2023-11-21 18:00","2023-11-20 09:00","2023-11-21 18:00","연속"]
[79,"경기북부","구리","신포천포천LNGCC#1 T/L","22~23년 구리전력 변전협력 총액공사","포천LNG 345kV 신포천-포천LNG #1T/L GIS 방수처리 - 부싱 인출부 방수처리","2023-11-22 09:00","2023-11-23 18:00","2023-11-22 09:00","2023-11-23 18:00","연속"]
[80,"경기북부","직할","신의정부S/S #3 M.Tr","22-23년 경기북부 직할 변전 협력 총액공사","345kV M.Tr 보통점검","2023-11-06 09:00","2023-11-13 18:00","취소","취소","연속"]
[81,"경기북부","직할","신의정부양주#1 T/L","345kV 신의정부S/S CLR용 GIS 설치공사","신의정부-양주#1TL GIS ↔ #2CLR 2차측 GIB 연결용 LA, 단상GIB 설치 등","2023-11-02 09:00","2023-11-24 18:00","2023-11-02 09:00","2023-11-24 18:00","연속"]
[82,"경기북부","직할","신의정부S/S CB 7772","22-23년 경기북부 직할 변전 협력 총액공사","345kV Sh.R 보통점검","2023-11-14 09:00","2023-11-15 18:00","2023-11-14 09:00","2023-11-15 18:00","매일"]
[83,"경기북부","직할","신의정부S/S #2 Sh.R CB","22-23년 경기북부 직할 변전 협력 총액공사","345kV Sh.R 보통점검","2023-11-14 09:00","2023-11-15 18:00","2023-11-14 09:00","2023-11-15 18:00","매일"]
[84,"경기북부","직할","신의정부S/S CB 7700","22-23년 경기북부 직할 변전 협력 총액공사","345kV Sh.R 보통점검","2023-11-14 09:00","2023-11-15 18:00","2023-11-14 09:00","2023-11-15 18:00","매일"]
[85,"경기북부","직할","양주S/S STATCOM (CB 7700, 7771)","2023년 양주S/S 345kV STATCOM 초기점검공사","1. 공사목적 : 345kV STATCOM 점검을 통한 계통안정 및 전력공급 2. 공사개요 : 345kV 200MVar MMC STATCOM 점검공사 3. 휴전일정 : 2023.11.20-2023.12.07","2023-11-27 09:00","2023-12-15 18:00","2023-11-27 09:00","2023-12-15 18:00","연속"]
[86,"경기북부","직할","양주S/S CB 7771","2023년 양주S/S 345kV STATCOM 초기점검공사","1. 공사목적 : 345kV STATCOM 점검을 통한 계통안정 및 전력공급 2. 공사개요 : 345kV 200MVar MMC STATCOM 점검공사 3. 휴전일정 : 2023.11.20-2023.12.07","2023-11-27 09:00","2023-12-15 18:00","취소","취소","연속"]
[87,"경기북부","고양","신덕은S/S #4 M.Tr","22~23년 고양전력지사 변전협력회사 총액공사","신덕은S/S #4M.Tr 3차 피뢰기 A,B,C상 보통점검","2023-11-21 09:00","2023-11-21 18:00","2023-11-21 09:00","2023-11-21 18:00","연속"]
[88,"경기북부","직할","동두천C/C CB 7472","동두천CC 7472 CB B상 유압조작기 교체","동두천CC 7472 CB B상 유압조작기 교체","2023-11-06 09:00","2023-11-07 18:00","2023-11-07 09:00","2023-11-08 18:00","연속"]
[89,"경기북부","직할","양주중부#1 T/L","2022~2023년 고양전력지사 가공송전협력회사 총액공사","지지애자 교체","2023-11-09 07:00","2023-11-09 18:00","2023-11-09 07:00","2023-11-09 18:00","연속"]
[90,"경기","군포","서서울#2신시흥#1 T/L","345kV 영흥T/L 추락방지시설 설치공사","송전철탑 추락방지장치 설치 - 대상 : No.184","2023-11-03 07:00","2023-11-03 18:00","2023-11-03 07:00","2023-11-03 18:00","연속"]
[91,"경기","군포","서서울#2신시흥#2 T/L","345kV 영흥T/L 추락방지시설 설치공사","송전철탑 추락방지장치 설치 - 대상 : No.184","2023-11-04 07:00","2023-11-04 18:00","취소","취소","연속"]
[92,"경기","군포","서서울S/S CB 7772","서서울S/S 신온양-서서울#2T/L 7772 GIS 보통점검","서서울S/S 신온양-서서울#2T/L 7772 GIS 보통점검","2023-11-07 14:00","2023-11-07 18:00","2023-11-07 14:00","2023-11-07 18:00","연속"]
[93,"경기","군포","서서울S/S CB 7770","서서울S/S 신온양-서서울#2T/L 7770 GIS 보통점검","서서울S/S 신온양-서서울#2T/L 7770 GIS 보통점검","2023-11-07 09:00","2023-11-07 14:00","2023-11-07 09:00","2023-11-07 14:00","연속"]
[94,"경기","군포","서서울S/S CB 7472","서서울S/S 신온양-서서울#1T/L 7472 GIS 보통점검","서서울S/S 신온양-서서울#1T/L 7472 GIS 보통점검","2023-11-03 14:00","2023-11-03 18:00","2023-11-03 14:00","2023-11-03 18:00","연속"]
[95,"경기","군포","서서울S/S CB 7400","서서울S/S 신온양-서서울#1T/L 7400 GIS 보통점검","서서울S/S 신온양-서서울#1T/L 7400 GIS 보통점검","2023-11-03 09:00","2023-11-03 14:00","2023-11-03 09:00","2023-11-03 14:00","연속"]
[96,"경기","군포","신시흥신안산#2 T/L","345kV 영흥T/L 추락방지시설 설치공사","송전철탑 추락방지장치 설치 - 대상 : No.183","2023-11-02 07:00","2023-11-02 18:00","2023-11-03 07:00","2023-11-03 18:00","연속"]
[97,"경기","군포","서서울#2S/S #1 BUS","서서울2S/S 345kV #1BUS 가스누기 보수","서서울2S/S 345kV #1BUS 가스누기 보수","2023-11-24 09:00","2023-12-01 18:00","취소","취소","연속"]
[98,"경기","군포","서서울#2신시흥#1 T/L","서서울2S/S 345kV #1BUS 가스누기 보수(무부하용)","서서울2S/S 345kV #1BUS 가스누기 보수(무부하용)","2023-11-30 09:00","2023-12-01 18:00","취소","취소","연속"]
[99,"경기","군포","서서울#2S/S CB 7D71","서서울2S/S 345kV #1BUS 가스누기 보수(무부하용)","서서울2S/S 345kV #1BUS 가스누기 보수(무부하용)","2023-11-30 09:00","2023-12-01 18:00","취소","취소","연속"]
[100,"경기","동부","곤지암S/S #3 M.Tr","23년 동부 변전협력총액공사","곤지암:#3M.Tr 보호반대체","2023-11-13 09:00","2023-11-17 18:00","2023-11-13 09:00","2023-11-17 18:00","연속"]
[101,"경기","동부","곤지암S/S 하이닉스#1T/L CB","23년 동부 변전정비회사 총액공사","곤지암:SK하이닉스#1(초기)","2023-11-07 09:30","2023-11-07 18:00","2023-11-07 09:30","2023-11-07 18:00","연속"]
[102,"경기","동부","곤지암S/S 하이닉스#2T/L CB","23년 동부 변전정비회사 총액공사","곤지암:SK하이닉스#2(초기)","2023-11-09 09:30","2023-11-09 18:00","2023-11-09 09:30","2023-11-09 18:00","연속"]
[103,"경기","동부","신충주여주복합#2 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.97 ~ 139 (2회선 철탑 39기)","2023-11-11 07:00","2023-11-12 18:00","취소","취소","연속"]
[104,"경기","동부","신충주T여주복합#1 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.97 ~ 139 (2회선 철탑 39기)","2023-11-26 07:00","2023-11-26 18:00","취소","취소","연속"]
[105,"경기","동부","신충주여주복합#2 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.97 ~ 139 (2회선 철탑 39기)","2023-11-18 07:00","2023-11-19 18:00","취소","취소","연속"]
[106,"경기","동부","신충주여주복합#2 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.97 ~ 139 (2회선 철탑 39기)","2023-11-25 07:00","2023-11-25 18:00","취소","취소","연속"]
[107,"경기","성남","신성남S/S #4 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- #2공기압축기 대체 관련 안전거리 확보","2023-11-11 09:00","2023-11-11 18:00","2023-11-11 09:00","2023-11-11 18:00","연속"]
[108,"경기","성남","신성남S/S #2 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- 부싱 절연유 채유 - 4287SIS 보통점검","2023-11-04 09:00","2023-11-04 14:00","2023-11-04 09:00","2023-11-04 14:00","연속"]
[109,"경기","성남","신성남S/S STATCOM CB","23년 성남전력지사 STATCOM 보통점검공사","- STATCOM 보통점검","2023-11-27 09:00","2023-12-15 18:00","2023-11-27 09:00","2023-12-15 18:00","연속"]
[110,"경기","성남","신성남S/S #3 M.Tr","23년 성남전력지사 변전협력회사 총액공사","- B상 2차 과열보수","2023-11-04 14:00","2023-11-04 18:00","2023-11-04 14:00","2023-11-04 18:00","연속"]
[111,"경기","성남","신수원S/S #4 M.Tr","신수원S/S #4M.Tr 1차측 EBA 자기애관 교체공사","- EBA 자기애관 교체 - 1차 하우징 누유 보수","2023-11-06 09:00","2023-11-09 18:00","2023-11-06 09:00","2023-11-09 18:00","연속"]
[112,"경기","성남","신안성신수원#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)","2023-11-11 08:00","2023-11-26 18:00","2023-11-11 08:00","2023-11-26 18:00","연속"]
[113,"경기","성남","신용인신수원 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간)","2023-11-25 08:00","2023-11-28 18:00","2023-11-25 08:00","2023-11-28 18:00","매일"]
[114,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울T/L(고산2지구) 지중화 공사","○ 광주 고산2지구 택지개발지구내 지장송전선로 지중화 ○ 사업구간 : 345kV 신용인-동서울T/L No.55~56","2023-11-27 09:00","2023-12-15 18:00","2023-11-27 09:00","2023-12-15 18:00","연속"]
[115,"경기","성남","신안성신용인#1 T/L","23년 성남전력지사 변전협력회사 총액공사","- CVT 보통점검","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[116,"경기","직할","화성S/S #2 CLR (CB 7577, 7677)","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 345kV #2CLR 정기검사","2023-11-28 09:00","2023-11-28 18:00","2023-11-28 09:00","2023-11-28 18:00","연속"]
[117,"경기","직할","화성S/S CB 7677","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 345kV #2CLR 정기검사","2023-11-28 09:00","2023-11-28 18:00","취소","취소","연속"]
[118,"경기","직할","화성평택TP#2 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 345kV 화성-평택TP#2T/L LA,CVT 보통점검","2023-11-24 09:00","2023-11-24 18:00","취소","취소","연속"]
[119,"경기","직할","화성S/S SEC CB 75760","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 75-76 SEC GIS 보통점검","2023-11-30 09:00","2023-11-30 18:00","2023-11-30 09:00","2023-11-30 18:00","연속"]
[120,"경기","직할","화성S/S #2 M.Tr","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 345kV #2M.Tr GIS 초기점검(7400,7472) - 아산화성#2T/L 휴전 병행","2023-11-04 09:00","2023-11-05 18:00","2023-10-21 09:00","2023-10-22 18:00","연속"]
[121,"경기","직할","화성S/S #3 M.Tr","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 345kV #3M.Tr 보통점검","2023-11-13 09:00","2023-11-14 18:00","2023-10-30 09:00","2023-10-31 18:00","연속"]
[122,"경기","직할","화성서서울#2 T/L","화성S/S 345kV GIS 용량대체공사","345kV #70BUS 무부하 가압","2023-11-29 15:00","2023-11-30 18:00","2023-11-17 15:00","2023-11-18 18:00","연속"]
[123,"경기","직할","화성평택TP#2 T/L","OPGW 증설공사","OPGW 증설공사","2023-11-22 07:00","2023-11-24 18:00","2023-11-22 07:00","2023-11-24 18:00","연속"]
[124,"경기","직할","화성평택TP#1 T/L","OPGW 증설공사","OPGW 증설공사","2023-11-25 07:00","2023-11-26 18:00","2023-11-25 07:00","2023-11-26 18:00","연속"]
[125,"경기","직할","아산화성#2 T/L","OPGW 증설공사","OPGW 증설공사","2023-11-25 07:00","2023-11-26 18:00","취소","취소","연속"]
[126,"경기","평택","서안성신진천#2 T/L","세종-포천간 도로개설 관련 지장이설공사(345kV 2T/L)","철탑 5기 신설, 8기 철거","2023-11-15 07:00","2023-11-18 18:00","2023-11-15 07:00","2023-11-18 18:00","연속"]
[127,"경기","평택","신안성서안성#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사 ","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항) ","2023-11-08 07:00","2023-11-10 18:00","2023-11-08 07:00","2023-11-10 18:00","연속"]
[128,"경기","평택","신안성서안성#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사 ","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항) ","2023-11-20 07:00","2023-11-22 18:00","2023-11-20 07:00","2023-11-22 18:00","연속"]
[129,"경기","평택","서안성신진천#1 T/L","세종-포천간 도로개설 관련 지장이설공사(345kV 1T/L)","철탑 5기 신설, 8기 철거","2023-11-08 07:00","2023-11-14 18:00","2023-11-08 07:00","2023-11-14 18:00","연속"]
[130,"경기","평택","신안성서안성#1 T/L","23년 평택전력 변전협력회사 총액공사","서안성S/S 신안성-서안성#1T/L GIS 보수","2023-11-30 09:00","2023-11-30 18:00","2023-11-30 09:00","2023-11-30 18:00","연속"]
[131,"경기","평택","평택T/P #2 TIE Tr","23년 평택전력 변전협력회사 총액공사","평택T/P #2Tie-Tr 3차 GIS 조작시험 및 A상 부싱센서모니터 교체","2023-11-27 14:00","2023-11-27 18:00","2023-11-27 14:00","2023-11-27 18:00","연속"]
[132,"경기","평택","평택T/P #1 TIE Tr","23년 평택전력 변전협력회사 총액공사","평택T/P #1Tie-Tr 3차 GIS 조작시험","2023-11-27 09:00","2023-11-27 14:00","2023-11-27 09:00","2023-11-27 14:00","연속"]
[133,"강원","강릉","안인개폐소양양PP T/L","2022~2023년 가공송전협력회사 총액공사","○ 철탑 추락방지장치 설치(No.4~137)","2023-11-09 07:30","2023-11-29 18:00","2023-11-09 07:30","2023-11-29 18:00","매일"]
[134,"강원","강릉","안인개폐소신양양 T/L","2022~2023년 가공송전협력회사 총액공사","○ 철탑 추락방지장치 설치(No.4~55)","2023-11-30 07:30","2023-12-15 18:00","취소","취소","매일"]
[135,"강원","강릉","양양P/P CB 7371","2023년 강릉전력 변전협력회사 총액공사","차단기 조작시험","2023-11-06 13:00","2023-11-06 18:00","2023-11-06 13:00","2023-11-06 18:00","연속"]
[136,"강원","동해","동해삼척GP#2 T/L","2023년 가공송전선로 순시점검 위탁공사","345kV 동해-삼척GP #2T/L 불량애자 절연저항측정","2023-11-01 08:00","2023-11-02 18:00","2023-11-01 08:00","2023-11-02 18:00","매일"]
[137,"강원","동해","동해삼척GP#1 T/L","2022~23년 동해전력지사 가공송전협력회사 총액공사","No.77~78 항공장애표시구 민원개소 교체 작업","2023-11-03 08:00","2023-11-03 18:00","2023-11-03 08:00","2023-11-03 18:00","연속"]
[138,"강원","태백","신태백한울NP#2 T/L","345kV 신태백-한울NP2T/L 산불피해개소 전선교체공사","산불피해개소 전선교체공사","2023-11-23 09:00","2023-12-08 18:00","취소","취소","연속"]
[139,"충북","직할","신중부남청주#1 T/L","345kV 신중부-남청주T/L 지장송전선로 이설공사","오창테크노폴리스 산업단지 조성에 따른 지장이설 - 설치 4기, 인클로징 1기, 가철탑 3기","2023-11-26 08:00","2023-12-01 18:00","2023-11-26 08:00","2023-12-01 18:00","연속"]
[140,"충북","직할","신중부남청주#2 T/L","345kV 신중부-남청주T/L 지장송전선로 이설공사","오창테크노폴리스 산업단지 조성에 따른 지장이설 - 설치 4기, 인클로징 1기, 가철탑 3기","2023-11-20 08:00","2023-11-25 18:00","2023-11-20 08:00","2023-11-25 18:00","연속"]
[141,"충북","직할","신진천S/S CB 7100","'22-23년 충북직할 변전협력회사 총액공사","신진천변전소 345kV 신중부-신진천 #1T/L TIE GIS 보통점검","2023-11-14 14:00","2023-11-14 18:00","2023-11-15 09:00","2023-11-15 14:00","연속"]
[142,"충북","직할","신진천S/S CB 7171","'22-23년 충북직할 변전협력회사 총액공사","신진천변전소 345kV 신중부-신진천 #1T/L GIS 보통점검","2023-11-14 09:00","2023-11-14 14:00","2023-11-15 14:00","2023-11-15 18:00","연속"]
[143,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사 (1차)","#66-65 SEC GIS 대체 (안전이격 확보)","2023-11-03 09:00","2023-11-05 18:00","2023-11-03 09:00","2023-11-05 18:00","연속"]
[144,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방) OLTC 조작 라인 시험 등","2023-11-20 09:00","2023-11-20 18:00","취소","취소","연속"]
[145,"충북","청주","남청주S/S CB 7300","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-13 17:00","2023-11-13 18:00","2023-11-13 17:00","2023-11-13 18:00","연속"]
[146,"충북","청주","남청주S/S CB 7671","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-13 15:00","2023-11-13 17:00","2023-11-13 15:00","2023-11-13 17:00","연속"]
[147,"충북","청주","남청주S/S CB 7471","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-13 13:00","2023-11-13 15:00","2023-11-13 13:00","2023-11-13 15:00","연속"]
[148,"충북","청주","남청주S/S CB 7371","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-13 11:00","2023-11-13 13:00","2023-11-13 11:00","2023-11-13 13:00","연속"]
[149,"충북","청주","남청주S/S CB 7171","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-13 09:00","2023-11-13 11:00","2023-11-13 09:00","2023-11-13 11:00","연속"]
[150,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","#61-60 SEC GIS 대체 (안전이격 확보)","2023-11-09 14:00","2023-11-11 18:00","2023-11-09 14:00","2023-11-11 18:00","연속"]
[151,"충북","청주","남청주S/S #3 M.Tr","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방) OLTC 조작 라인 시험 등","2023-11-22 09:00","2023-11-22 18:00","2023-11-15 09:00","2023-11-15 18:00","연속"]
[152,"충북","청주","남청주S/S #4 M.Tr","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방) OLTC 조작 라인 시험 등","2023-11-23 09:00","2023-11-23 18:00","2023-11-17 09:00","2023-11-17 18:00","연속"]
[153,"충북","청주","남청주S/S #5 M.Tr","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방) OLTC 조작 라인 시험 등","2023-11-24 09:00","2023-11-24 18:00","2023-11-18 09:00","2023-11-18 18:00","연속"]
[154,"충북","청주","남청주S/S #1 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","#66-65 SEC GIS 대체 (안전이격 확보)","2023-11-03 09:00","2023-11-05 18:00","취소","취소","연속"]
[155,"충북","청주","남청주S/S #2 M.Tr","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방) OLTC 조작 라인 시험 등","2023-11-21 09:00","2023-11-21 18:00","2023-11-14 09:00","2023-11-14 18:00","연속"]
[156,"충북","청주","신옥천신남원#2 T/L","22-23년 청주전력 변전협력회사 총액공사","362kV GIS 보통점검","2023-11-09 09:00","2023-11-10 18:00","취소","취소","연속"]
[157,"충북","청주","신옥천S/S #2 M.Tr","22-23년 청주전력 변전협력회사 총액공사","362kV GIS 보통점검","2023-11-06 09:00","2023-11-07 18:00","2023-11-06 09:00","2023-11-07 18:00","연속"]
[158,"충북","청주","신옥천무주양수 T/L","345kV 신옥천-북경남 등 8개T/L 추락방지장치 설치공사","345kV 신옥천-무주양수T/L 수직 및 수평 추락방지장치 설치 - 설치개소 : No.278~369 (92기 중 42기 설치예정)","2023-11-13 09:00","2023-11-18 18:00","취소","취소","매일"]
[159,"충북","청주","신옥천S/S #3 M.Tr","22-23년 청주전력 변전협력회사 총액공사","362kV GIS 보통점검","2023-11-17 08:00","2023-11-17 18:00","2023-11-17 08:00","2023-11-17 18:00","연속"]
[160,"충북","청주","신옥천신계룡 T/L","22-23년 청주전력 변전협력회사 총액공사","362kV GIS 보통점검","2023-11-22 08:00","2023-11-23 18:00","2023-11-22 08:00","2023-11-23 18:00","연속"]
[161,"충북","충주","신제천S/S #2 M.Tr","22-23년 충주전력지사 변전정비 총액공사","신제천S/S #2M.Tr 1,2차 GIS 보통점검 및 1,2차 부싱절연유 채유 및 #6S.Tr 보통점검 및 4275,4485,4685DS 보통점검 / 1차 CVT 하자점검 / 4279,4489,4689 VCB 보통점검","2023-11-20 09:00","2023-11-22 18:00","2023-11-20 09:00","2023-11-22 18:00","연속"]
[162,"충북","충주","신제천S/S #4 M.Tr","345kV 신제천S/S #4 M.Tr 대체공사","11.03 ~ 11.04 : #4 M.Tr 무부하가압용 11.07 ~ 11.08 : #4 M.Tr 실부하가압용","2023-11-03 09:00","2023-11-08 18:00","2023-11-03 09:00","2023-11-08 18:00","연속"]
[163,"충북","충주","신제천S/S #3 M.Tr","22-23년 충주전력지사 변전정비 총액공사","신제천S/S #3M.Tr 및 1,2차 GIS 보통점검/ 1,2차 부싱절연유 채유,#1,3S.Tr 보통점검/1차 CVT 하자점검","2023-11-23 09:00","2023-11-25 18:00","2023-11-23 09:00","2023-11-25 18:00","연속"]
[164,"충북","충주","신제천S/S SVC CB","신제천S/S 345kV SVC 불량사항 조치","○ #1TSC A상 투입 불가에 따른 점검 ○ Valve룸 내 항온항습센서 교체 및 위치 변경","2023-11-23 09:00","2023-11-25 18:00","2023-11-23 09:00","2023-11-25 18:00","연속"]
[165,"충북","충주","신충주S/S #1 M.Tr","22-23년 충주전력지사 변전정비 총액공사","신충주S/S 345kV #1M.Tr 1,2차 및 예비M.Tr 부싱절연유 채유","2023-11-13 09:00","2023-11-13 13:00","2023-11-13 09:00","2023-11-13 13:00","연속"]
[166,"충북","충주","신충주S/S STATCOM CB","신충주S/S 345kV STATCOM 제어기 통신절체 불량조치","1. #2Unit Controller - Linux Ethernet Port 통신절체 불량조치 2. 운전정보 통합관리 시스템 구축 용역 관련 SCADA 연동시험","2023-11-27 09:00","2023-11-29 18:00","2023-11-27 09:00","2023-11-29 18:00","연속"]
[167,"대전세종충남","대전","신계룡S/S #3 M.Tr","신계룡S/S #3M.Tr 보호반 교체","신계룡S/S #3M.Tr 보호반 교체 -[병행]신계룡S/S #3M.Tr 2차 LA(A,B,C) 교체 -[병행]신계룡S/S #3M.Tr 1차 차단기 부동작 예방 조작시험(7600,7672)","2023-11-13 09:00","2023-11-17 18:00","2023-11-13 09:00","2023-11-17 18:00","연속"]
[168,"대전세종충남","대전","신계룡S/S #1 M.Tr","신계룡S/S #1M.Tr 1차 차단기조작시험(7272)","신계룡S/S #1M.Tr 1차 차단기조작시험(7272)","2023-11-20 09:00","2023-11-20 18:00","2023-11-20 09:00","2023-11-20 18:00","연속"]
[169,"대전세종충남","서산","신당진개폐소북당진 T/L","345kV 신당진개폐소-북당진T/L 점퍼지지애자 설치","고정형 점퍼지지애자 설치 : No.44,59 (10월 휴전 취소시)","2023-11-02 08:00","2023-11-03 18:00","취소","취소","매일"]
[170,"대전세종충남","서산","신당진S/S #2 M.Tr","23년 서산P/O 345kV이하 변압기 보통점검공사","(9, 10월 휴전 취소시) 신당진S/S 345kV #2M.Tr 보통점검 및 누유보수","2023-11-06 09:00","2023-11-10 18:00","취소","취소","연속"]
[171,"대전세종충남","서산","신서산아산#1 T/L","2023년도 가공송전 순시점검 위탁공사","[서산] 345kV 신서산-아산#1T/L 정밀점검(주말제외) - No.1~73 [서산] 345kV 신서산-아산#1T/L 이도조정, 점퍼지지애자 교체 - No.48~50(이도조정), No.69~70(이도조정), No.73(점퍼지지애자 교체) [천안] 수평추락방지장치 설치공사","2023-11-20 08:00","2023-12-01 18:00","취소","취소","매일"]
[172,"대전세종충남","서산","신서산S/S #4 Sh.R CB","23년 서산P/O 변전협력회사 총액공사","신서산S/S 345kV #4Sh.R 하자점검 및 절연유 여과","2023-11-20 09:00","2023-11-22 18:00","취소","취소","연속"]
[173,"대전세종충남","서산","신서산신당진#2 T/L","2023년도 가공송전 순시점검 위탁공사","345kV 신서산-신당진#2T/L 정밀점검(주말제외) - No.1~42(7~32 신서산-아산 병가구간)","2023-11-23 08:00","2023-11-29 18:00","취소","취소","매일"]
[174,"대전세종충남","서산","신서산신당진#1 T/L","23년 서산P/O 장기사용 배전반 교체공사","신서산S/S 345kV 78Bay B/F 보호반 대체","2023-11-13 09:00","2023-11-22 18:00","취소","취소","연속"]
[175,"대전세종충남","서산","태안T/P SEC CB 71720","태안화력S/Y 345kV 옥외설비 GIS 내장화공사","(무부하가압) 태안화력S/Y 345kV 신서산-태안화력#2T/L 옥외설비 GIS 내장화공사","2023-11-30 14:00","2023-12-01 14:00","2023-11-30 14:00","2023-12-01 14:00","연속"]
[176,"대전세종충남","서산","태안T/P #72 BUS","태안화력S/Y 345kV 옥외설비 GIS 내장화공사","(무부하가압) 태안화력S/Y 345kV 신서산-태안화력#2T/L 옥외설비 GIS 내장화공사","2023-11-30 14:00","2023-12-01 14:00","2023-11-30 14:00","2023-12-01 14:00","연속"]
[177,"대전세종충남","서산","신서산태안TP#2 T/L","태안화력S/Y 345kV 옥외설비 GIS 내장화공사","태안화력S/Y 345kV 신서산-태안화력#2T/L 옥외설비 GIS 내장화공사","2023-11-13 09:00","2023-12-01 18:00","2023-11-13 09:00","2023-12-01 18:00","연속"]
[178,"대전세종충남","서산","태안T/P #72 BUS","태안화력S/Y 345kV 옥외설비 GIS 내장화공사","(무부하가압) 태안화력S/Y 345kV 개폐소-태안화력#2T/L 옥외설비 GIS 내장화공사","2023-11-09 14:00","2023-11-10 14:00","2023-11-09 14:00","2023-11-10 14:00","연속"]
[179,"대전세종충남","서산","태안T/P SEC CB 71720","태안화력S/Y 345kV 옥외설비 GIS 내장화공사","(무부하가압) 태안화력S/Y 345kV 개폐소-태안화력#2T/L 옥외설비 GIS 내장화공사","2023-11-09 14:00","2023-11-10 14:00","2023-11-09 14:00","2023-11-10 14:00","연속"]
[180,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S 345kV 신온양-서서울#2T/L 결상회로 개선","신온양S/S 345kV 신온양-서서울#2T/L 결상회로 개선","2023-11-21 09:00","2023-11-21 18:00","취소","취소","연속"]
[181,"대전세종충남","천안","신온양S/S CB 7771","신온양S/S 345kV 7771,7772 CB 개폐타임 측정","신온양S/S 345kV 7771,7772 CB 개폐타임 측정","2023-11-21 09:00","2023-11-21 14:00","2023-11-21 09:00","2023-11-21 14:00","연속"]
[182,"대전세종충남","천안","신온양서서울#2 T/L","(10월취소시)신온양S/S 345kV 77B/F 교체, 결상회로 보완작업","(10월취소시)신온양S/S 345kV 77B/F 교체, 결상회로 보완작업","2023-11-21 09:00","2023-11-24 18:00","취소","취소","연속"]
[183,"대전세종충남","천안","신온양S/S #4 M.Tr","(10월취소시)신온양S/S 345kV 77B/F 교체, 결상회로 보완작업","(10월취소시)신온양S/S 345kV 77B/F 교체, 결상회로 보완작업","2023-11-21 09:00","2023-11-24 18:00","2023-11-21 09:00","2023-11-24 18:00","연속"]
[184,"대전세종충남","천안","신온양서서울#1 T/L","(10월취소시)신온양S/S 345kV 78B/F 교체, 결상회로 보완작업","(10월취소시)신온양S/S 345kV 78B/F 교체, 결상회로 보완작업","2023-11-28 09:00","2023-12-01 18:00","취소","취소","연속"]
[185,"대전세종충남","천안","신온양서서울#1 T/L","신온양S/S 345kV 신온양-서서울#1T/L 결상회로 개선","신온양S/S 345kV 신온양-서서울#1T/L 결상회로 개선","2023-11-28 09:00","2023-11-28 18:00","취소","취소","연속"]
[186,"대전세종충남","천안","신온양신탕정#2 T/L","(10월취소시)신온양S/S 345kV 78B/F 교체, 결상회로 보완작업","(10월취소시)신온양S/S 345kV 78B/F 교체, 결상회로 보완작업","2023-11-28 09:00","2023-12-01 18:00","2023-11-28 09:00","2023-12-01 18:00","연속"]
[187,"대전세종충남","천안","신온양S/S CB 7872","신온양S/S 345kV 7872 CB 개폐타임 측정","신온양S/S 345kV 7872 CB 개폐타임 측정","2023-11-28 09:00","2023-11-28 18:00","2023-11-28 09:00","2023-11-28 18:00","연속"]
[188,"대전세종충남","천안","신온양S/S CB 7772","신온양S/S 345kV 7771,7772 CB 개폐타임 측정","신온양S/S 345kV 7771,7772 CB 개폐타임 측정","2023-11-21 14:00","2023-11-21 18:00","2023-11-21 14:00","2023-11-21 18:00","연속"]
[189,"대전세종충남","천안","아산보령TP#2 T/L","345kV 아산-보령화력T/L 추락방지장치 설치공사","345kV 아산-보령화력T/L No. 124~190 수평 추락방지장치 설치 ※ 주말작업 없음.","2023-11-13 07:00","2023-11-20 18:00","취소","취소","매일"]
[190,"대전세종충남","천안","아산보령TP#1 T/L","(10월 취소시)345kV 아산-보령화력T/L 추락방지장치 설치공사","345kV 아산-보령화력T/L No. 124~190 수직, 수평 추락방지장치 설치 ※ 주말작업 없음.","2023-11-01 07:00","2023-11-10 18:00","취소","취소","매일"]
[191,"대전세종충남","청양","보령C/C CB 7472","(발전소 병행휴전 불가 시)청양P/O 362kV GIS 보통점검공사","보령C/C 362kV 7472 GIS 보통점검","2023-11-10 09:00","2023-11-10 18:00","2023-11-10 09:00","2023-11-10 18:00","연속"]
[192,"대전세종충남","청양","보령C/C CB 7200","(10월 취소시)청양P/O 변전협력회사 총액공사","보령C/C 345kV 7200 보통점검(10월 발전소 휴전 취소시)","2023-11-13 10:00","2023-11-13 18:00","취소","취소","연속"]
[193,"대전세종충남","청양","보령C/C CB 7272","(10월 취소시)청양P/O 변전협력회사 총액공사","보령C/C 345kV 7272 보통점검(10월 발전소 휴전 취소시)","2023-11-14 10:00","2023-11-14 18:00","취소","취소","연속"]
[194,"대전세종충남","청양","보령C/C CB 7471","(9월 취소시)청양P/O 362kV GIS 보통점검공사","보령C/C 362kV 7471 GIS 보통점검","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[195,"대전세종충남","청양","보령C/C CB 7400","(발전소 병행휴전 불가 시)청양P/O 362kV GIS 보통점검공사","보령C/C 362kV 7400 GIS 보통점검","2023-11-09 09:00","2023-11-09 18:00","2023-11-09 09:00","2023-11-09 18:00","연속"]
[196,"대전세종충남","청양","청양S/S CB 7772","청양P/O 362kV GIS 보통점검공사","362kV 7772 GIS 보통점검","2023-11-07 08:00","2023-11-07 18:00","2023-11-07 08:00","2023-11-07 18:00","연속"]
[197,"대전세종충남","청양","청양S/S SEC CB 70710","(10월 취소시)청양P/O 변전협력회사 총액공사","362kV GIS 차단기 조작시험 - 70-71-0, 75-76-0 (9월 조건부 승인 취소시)","2023-11-16 08:00","2023-11-16 12:00","2023-11-16 08:00","2023-11-16 12:00","연속"]
[198,"대전세종충남","청양","청양S/S SEC CB 75760","(10월 취소시)청양P/O 변전협력회사 총액공사","362kV GIS 차단기 조작시험 - 70-71-0, 75-76-0 (9월 조건부 승인 취소시)","2023-11-16 13:00","2023-11-16 18:00","2023-11-16 13:00","2023-11-16 18:00","연속"]
[199,"대전세종충남","청양","청양신보령TP T/L","청양P/O 변전협력회사 총액공사","345kV 청양-신보령T/L - 청양S/S LA 초기점검(A,B,C) 및 CVT 대체공사","2023-11-02 08:00","2023-11-02 18:00","취소","취소","연속"]
[200,"대전세종충남","청양","청양S/S CB 7372","청양P/O 362kV GIS 보통점검공사","청양S/S 362kV 7372 GIS 보통점검","2023-11-02 08:00","2023-11-02 18:00","2023-11-02 08:00","2023-11-02 18:00","연속"]
[201,"대전세종충남","청양","청양S/S CB 7371","청양P/O 362kV GIS 보통점검공사","청양S/S 362kV 7371 GIS 보통점검","2023-11-03 08:00","2023-11-03 18:00","2023-11-03 08:00","2023-11-03 18:00","연속"]
[202,"대전세종충남","청양","청양S/S CB 7172","청양P/O 변전협력회사 총액공사","청양S/S 345kV 청양-보령화력#1T/L CB (7172) C상 전자변 교체","2023-11-10 09:00","2023-11-10 18:00","2023-11-10 09:00","2023-11-10 18:00","연속"]
[203,"대전세종충남","청양","청양S/S CB 7700","청양P/O 362kV GIS 보통점검공사","362kV 7700 GIS 보통점검","2023-11-06 08:00","2023-11-06 18:00","2023-11-06 08:00","2023-11-06 18:00","연속"]
[204,"전북","군산","군산S/S #70 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2023-11-21 08:00","2023-11-28 18:00","2023-11-17 09:00","2023-11-24 18:00","연속"]
[205,"전북","군산","군산신김제#1 T/L","345kV 군산-신김제T/L CVT 점검","345kV 군산-신김제T/L CVT A,B,C상 점검","2023-11-15 09:00","2023-11-15 18:00","2023-11-15 09:00","2023-11-15 18:00","연속"]
[206,"전북","군산","군산S/S #75 BUS","군산변전소 345kV GIS 대체공사","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2023-12-11 08:00","2023-12-18 18:00","2023-11-27 08:00","2023-12-04 18:00","연속"]
[207,"전북","군산","군산S/S #4 M.Tr","군산P/O 주변압기 점검공사","군산P/O 주변압기 점검공사","2023-11-27 09:00","2023-11-28 18:00","2023-11-27 09:00","2023-11-28 18:00","연속"]
[208,"전북","군산","군산S/S #1 M.Tr","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-03 16:00","2023-11-03 18:00","취소","취소","연속"]
[209,"전북","군산","군산S/S #1 M.Tr","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-06 16:00","2023-11-06 18:00","취소","취소","연속"]
[210,"전북","군산","군산S/S #1 M.Tr","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-21 18:00","2023-11-22 18:00","취소","취소","연속"]
[211,"전북","군산","군산S/S #1 M.Tr","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-25 18:00","2023-11-26 18:00","취소","취소","연속"]
[212,"전북","군산","군산S/S CB 7700","군산PO 공압식 차단기 전자변 교체공사","- 7700 CB 전자변 교체, 조작시험","2023-11-29 09:00","2023-11-29 18:00","2023-11-29 09:00","2023-11-29 18:00","연속"]
[213,"전북","군산","새만금S/S #3 M.Tr","새만금S/S #3M.Tr OLTC 예방진단장치 TD 및 TPI 설치","새만금S/S #3M.Tr OLTC 예방진단장치 탭 표시용 TD 및 TPI 설치","2023-11-13 09:00","2023-11-14 18:00","2023-11-13 09:00","2023-11-14 18:00","연속"]
[214,"전북","군산","새만금S/S CB 7400","군산P/O 154kV 이상 차단기 조작시험","새만금S/S #1Sh.R TIE 차단기 조작시험","2023-11-07 13:00","2023-11-07 17:00","2023-11-07 13:00","2023-11-07 17:00","연속"]
[215,"전북","군산","새만금S/S CB 7472","군산P/O 154kV 이상 차단기 조작시험","새만금S/S #1Sh.R 1차 차단기 조작시험","2023-11-07 09:00","2023-11-07 13:00","2023-11-07 09:00","2023-11-07 13:00","연속"]
[216,"전북","김제","신김제S/S #2 M.Tr","신김제S/S 장기사용 개폐장치 대체공사","345kV 신김제S/S 345kV #1,2M.Tr 3차측 노후 VCB 4대 교체 - #1M.Tr 3차 CB, #2M.Tr 3차 CB, 23kv #2S.Tr CB, 23kV #2Sh.R CB","2023-11-15 09:00","2023-11-17 18:00","취소","취소","연속"]
[217,"전북","김제","신김제S/S CB 7471","김제PO 154kV이상 차단기 조작시험","차단기 동작특성시험","2023-11-06 09:30","2023-11-06 13:00","2023-11-06 09:30","2023-11-06 13:00","연속"]
[218,"전북","김제","신김제S/S CB 7400","김제PO 154kV이상 차단기 조작시험","차단기 동작특성시험","2023-11-06 13:00","2023-11-06 18:00","2023-11-06 13:00","2023-11-06 18:00","연속"]
[219,"전북","김제","신김제S/S #4 M.Tr","23년 김제P/O 345kV M.Tr 보통점검공사","345kV 신김제S/S 345kV #4M.Tr 보통점검","2023-11-08 09:00","2023-11-09 18:00","2023-11-08 09:00","2023-11-09 18:00","연속"]
[220,"전북","김제","신김제S/S #1 M.Tr","신김제S/S 장기사용 개폐장치 대체공사","345kV 신김제S/S 345kV #1,2M.Tr 3차측 노후 VCB 4대 교체 - #1M.Tr 3차 CB, #2M.Tr 3차 CB, 23kv #2S.Tr CB, 23kV #2Sh.R CB","2023-11-13 09:00","2023-11-14 18:00","2023-11-13 09:00","2023-11-14 18:00","연속"]
[221,"전북","직할","신남원광양#1 T/L","'22~'23년 전북직할 송전협력회사 총액공사","○ 수직 수평 추락방지시설 설치 : No.214 (1기)","2023-11-01 09:00","2023-11-01 18:00","취소","취소","연속"]
[222,"전북","직할","신남원광양#2 T/L","'22~'23년 전북직할 송전협력회사 총액공사","○ 수직 수평 추락방지시설 설치 No.214 (1기)","2023-11-02 09:00","2023-11-02 18:00","취소","취소","연속"]
[223,"전북","직할","신남원S/S CB 7771","23년 전북직할 362kV GIS 정밀점검 (단독차단기)","23년 전북직할 362kV GIS 정밀점검 (단독차단기)","2023-11-20 09:00","2023-11-24 18:00","취소","취소","연속"]
[224,"전북","직할","신남원신광주#1 T/L","23년 전북직할 362kV GIS 정밀점검 (무부하가압용 선로)","23년 전북직할 362kV GIS 정밀점검 (무부하가압용 선로)","2023-11-24 17:00","2023-11-24 18:00","취소","취소","연속"]
[225,"전북","직할","신남원S/S CB 7100","신남원S/S 7100 GIS 보통점검(병행)","신남원S/S 7100 GIS 보통점검(병행)","2023-11-27 09:00","2023-11-27 18:00","취소","취소","연속"]
[226,"전북","직할","신남원S/S CB 7871","23년 전북직할 362kV GIS 정밀점검 (단독차단기)","23년 전북직할 362kV GIS 정밀점검 (단독차단기)","2023-11-06 09:00","2023-11-10 18:00","2023-11-06 09:00","2023-11-10 18:00","연속"]
[227,"전북","직할","신남원신광주#2 T/L","23년 전북직할 362kV GIS 정밀점검 (무부하가압용 선로)","23년 전북직할 362kV GIS 정밀점검 (무부하가압용 선로)","2023-11-17 17:00","2023-11-17 18:00","2023-11-17 17:00","2023-11-17 18:00","연속"]
[228,"전북","직할","신남원신광주#1 T/L","23년 전북직할 362kV GIS 정밀점검 (무부하가압용 선로)","23년 전북직할 362kV GIS 정밀점검 (무부하가압용 선로)","2023-11-03 17:00","2023-11-03 18:00","2023-11-03 17:00","2023-11-03 18:00","연속"]
[229,"전북","직할","신남원신광주#2 T/L","23년 전북직할 362kV GIS 정밀점검 (무부하가압용 선로)","23년 전북직할 362kV GIS 정밀점검 (무부하가압용 선로)","2023-11-10 17:00","2023-11-10 18:00","2023-11-10 17:00","2023-11-10 18:00","연속"]
[230,"전북","직할","신남원S/S CB 7800","23년 전북직할 362kV GIS 정밀점검 (단독차단기)","23년 전북직할 362kV GIS 정밀점검 (단독차단기)","2023-11-13 09:00","2023-11-17 18:00","2023-11-13 09:00","2023-11-17 18:00","연속"]
[231,"광주전남","강진","신화순신강진#1 T/L","2022~23년 강진전력지사 송전 협력회사 총액공사","수직, 수평 추락방지장치 설치","2023-11-20 07:00","2023-11-30 18:00","취소","취소","매일"]
[232,"광주전남","광주","신광주S/S #3 M.Tr","23년 광주전력지사 변전협력회사 총액공사","- 76BAY 차단실패보호반 교체 - 345kV M.Tr 보통점검 - 362kV GIS 조작시험(7600,7672) - #3M.Tr 3차 차단기 교체(3차 Main, #1,2Sh.R, S.Tr) - 3차측 DS 점검","2023-11-01 09:00","2023-11-10 18:00","취소","취소","연속"]
[233,"광주전남","광주","신광주신화순#1 T/L","22~23년 송전협력회사 총액공사","신광주-신화순T/L 추락방지장치 설치공사(No.1~121)","2023-11-06 08:00","2023-11-10 18:00","취소","취소","매일"]
[234,"광주전남","광주","신광주한빛NP#2 T/L","7200 CB 조작시험,CVT 보통점검","7200 CB 조작시험,CVT 보통점검,즉시가압가능","2023-11-10 08:00","2023-11-10 18:00","취소","취소","연속"]
[235,"광주전남","광주","신광주S/S CB 7172","7172 GIS 보통점검","7172 GIS 보통점검,즉시가압가능","2023-11-13 08:00","2023-11-13 18:00","취소","취소","연속"]
[236,"광주전남","광주","신광주S/S CB 7200","7200 CB 조작시험","7200 CB 조작시험,즉시가압가능","2023-11-17 08:00","2023-11-17 18:00","취소","취소","연속"]
[237,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체,즉시가압불가","2023-11-13 08:00","2023-11-16 18:00","취소","취소","연속"]
[238,"광주전남","광주","신광주S/S CB 7171","7171 GIS 보통점검","7171 GIS 보통점검,즉시가압가능","2023-11-16 08:00","2023-11-16 18:00","취소","취소","연속"]
[239,"광주전남","광주","신남원신광주#2 T/L","'22~23년 광주 변전협력회사 총액공사","신남원-신광주#2T/L CVT 교체","2023-11-21 09:00","2023-11-21 18:00","2023-11-21 09:00","2023-11-21 18:00","연속"]
[240,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체,즉시가압불가","2023-11-20 08:00","2023-11-23 18:00","취소","취소","연속"]
[241,"광주전남","광주","신광주신화순#1 T/L","23년 광주전력지사 변전협력회사 총액공사","- 76BAY 차단실패보호반 교체","2023-11-01 09:00","2023-11-10 18:00","취소","취소","연속"]
[242,"광주전남","광주","신광주신화순#2 T/L","22~23년 송전협력회사 총액공사","신광주-신화순T/L 추락방지장치 설치공사(No.1~121)","2023-11-13 08:00","2023-11-17 18:00","취소","취소","매일"]
[243,"광주전남","광주","신화순신강진#2 T/L","신화순S/S 345kV 신화순-신강진 #2T/L (성능개선)","세니온제 345kV 송전선로 보호배전반 성능개선(유사고장)","2023-11-20 09:30","2023-11-20 18:00","2023-11-20 09:30","2023-11-20 18:00","연속"]
[244,"광주전남","광주","신화순신강진#2 T/L","'22~23년 광주 변전협력회사 총액공사","신화순-신강진#2T/L CVT 보통점검","2023-11-06 09:00","2023-11-06 14:00","2023-11-06 09:00","2023-11-06 14:00","연속"]
[245,"광주전남","순천","광양C/C CB 7172","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험","2023-11-01 15:00","2023-11-01 18:00","2023-11-01 15:00","2023-11-01 18:00","연속"]
[246,"광주전남","순천","광양C/C CB 7271","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험(즉시가압 가능)","2023-11-02 09:00","2023-11-02 12:00","2023-11-02 09:00","2023-11-02 12:00","연속"]
[247,"광주전남","순천","광양C/C CB 7200","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험","2023-11-02 12:00","2023-11-02 15:00","2023-11-02 12:00","2023-11-02 15:00","연속"]
[248,"광주전남","순천","광양C/C CB 7272","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험","2023-11-02 15:00","2023-11-02 18:00","2023-11-02 15:00","2023-11-02 18:00","연속"]
[249,"광주전남","순천","광양CC여수TP#1 T/L","345kV 광양CC-여수TPT/L 추락방지시설 설치공사","수직,수평 추락방지시설 설치 - 대 상 : No.1~19호, 19기","2023-11-15 07:00","2023-11-21 18:00","취소","취소","매일"]
[250,"광주전남","순천","광양CC여수TP#2 T/L","345kV 광양CC-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.1~19호, 19기","2023-11-22 07:00","2023-11-28 18:00","2023-11-23 07:00","2023-11-28 18:00","매일"]
[251,"광주전남","순천","광양C/C CB 7100","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험","2023-11-01 12:00","2023-11-01 15:00","2023-11-01 12:00","2023-11-01 15:00","연속"]
[252,"광주전남","순천","광양C/C CB 7171","22-23년 순천전력지사 변전협력회사 총액공사","차단기 조작시험","2023-11-01 09:00","2023-11-01 12:00","2023-11-01 09:00","2023-11-01 12:00","연속"]
[253,"광주전남","순천","광양하동TP#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","GIS 보통점검(7571, 7500) 및 LA, CVT 보통점검","2023-11-20 08:00","2023-11-21 18:00","2023-11-20 08:00","2023-11-21 18:00","연속"]
[254,"광주전남","순천","광양S/S CB 7300","22-23년 순천전력지사 변전정비회사 총액공사","광양-율촌CC T/L TIE CB GIS 보통점검(7300)","2023-11-16 08:00","2023-11-16 18:00","2023-11-16 08:00","2023-11-16 18:00","연속"]
[255,"광주전남","순천","광양율촌CC T/L","22-23년 순천전력지사 변전협력회사 총액공사","율촌C/C 광양-율촌C/C T/L(7171) GIS 타임측정 광양S/S 광양-율촌CC GIS 보통점검 광양-율촌C/C TIE GIS 보통점검,LA 보통점검 및 CVT 하자점검","2023-11-15 08:00","2023-11-16 18:00","취소","취소","연속"]
[256,"광주전남","순천","광양S/S CB 7371","22-23년 순천전력지사 변전정비회사 총액공사","광양-율촌CC T/L CB GIS 보통점검(7371)","2023-11-15 08:00","2023-11-15 18:00","2023-11-15 08:00","2023-11-15 18:00","연속"]
[257,"광주전남","순천","광양S/S CB 7200","22-23년 순천전력지사 변전협력회사 총액공사","GIS 보통점검","2023-11-14 09:00","2023-11-14 18:00","2023-11-14 09:00","2023-11-14 18:00","연속"]
[258,"광주전남","순천","광양율촌CC T/L","2022~23년 순천전력지사 가공송전 협력회사 총액공사","○ 코타핀 교체 : 신남원-광양 #2 T/L : 109, 111, 113, 120, 125호 ○ 불량애자 교체 : 신남원-광양 #2 T/L : S/T ○ 횡진고장방지장치 설치 : 신남원-광양 #2 T/L : 22호","2023-11-13 09:00","2023-11-16 18:00","취소","취소","매일"]
[259,"광주전남","순천","신남원광양#2 T/L","2022~23년 순천전력지사 가공송전 협력회사 총액공사","○ 코타핀 교체 : 신남원-광양 #2 T/L : 109, 111, 113, 120, 125호 ○ 불량애자 교체 : 신남원-광양 #2 T/L : S/T ○ 횡진고장방지장치 설치 : 신남원-광양 #2 T/L : 22호","2023-11-13 09:00","2023-11-17 18:00","취소","취소","매일"]
[260,"광주전남","순천","광양S/S CB 7271","22-23년 순천전력지사 변전협력회사 총액공사","GIS 보통점검","2023-11-13 08:00","2023-11-13 18:00","2023-11-13 08:00","2023-11-13 18:00","연속"]
[261,"광주전남","순천","신남원광양#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","광양S/S 신남원-광양 #1T/L GIS, TIE GIS 보통점검, LA 보통점검 및 CVT C상 초기점검","2023-11-13 08:00","2023-11-14 18:00","취소","취소","연속"]
[262,"광주전남","순천","광양광양제철#1 T/L","345kV 광양-광양CC #1T/L 피뢰기 설치공사","345kV 광양-광양CC #1T/L 피뢰기 설치공사를 위한 병가선로(광양제철#1T/L) 휴전","2023-11-13 07:00","2023-11-21 18:00","취소","취소","매일"]
[263,"광주전남","순천","광양광양CC#1 T/L","345kV 광양-광양CC #1T/L 피뢰기 설치공사","345kV 광양-광양CC #1T/L 피뢰기 설치공사(No.1~60호)","2023-11-13 07:00","2023-11-21 18:00","취소","취소","매일"]
[264,"광주전남","순천","광양S/S #2 M.Tr","22-23년 순천전력지사 변전협력회사 총액공사","#2M.Tr 3차 MAIN VCB 대체","2023-11-08 08:00","2023-11-09 18:00","2023-11-08 08:00","2023-11-09 18:00","연속"]
[265,"광주전남","순천","신남원광양#1 T/L","2022~23년 순천전력지사 가공송전 협력회사 총액공사","○ 코타핀 교체 : 신남원-광양 #1 T/L : 104, 107, 111, 123호 ○ 불량애자 교체 : 신남원-광양 #1 T/L : S/T , 103, 104, 105호 ○ 횡진고장방지장치 설치 : 신남원-광양 #1 T/L : 22호","2023-11-06 09:00","2023-11-08 18:00","취소","취소","매일"]
[266,"광주전남","순천","광양S/S #1 M.Tr","22-23년 순천전력지사 변전협력회사 총액공사","#1M.Tr 3차 MAIN VCB 대체","2023-11-06 08:00","2023-11-07 18:00","2023-11-06 08:00","2023-11-07 18:00","연속"]
[267,"광주전남","순천","광양여수TP T/L","22-23년 순천전력지사 변전협력회사 총액공사","LA 및 CVT 보통점검","2023-11-03 08:00","2023-11-03 18:00","2023-11-03 08:00","2023-11-03 18:00","연속"]
[268,"광주전남","순천","광양여수TP T/L","2022~23년 순천전력지사 가공송전 협력회사 총액공사","○ 코타핀 교체 : 신남원-광양 #1 T/L : 104, 107, 111, 123호 ○ 불량애자 교체 : 신남원-광양 #1 T/L : S/T , 103, 104, 105호 ○ 횡진고장방지장치 설치 : 신남원-광양 #1 T/L : 22호 - 345kV 신남원-광양 병가선로로 인해 휴전","2023-11-06 09:00","2023-11-08 18:00","취소","취소","매일"]
[269,"광주전남","순천","여수T/P CB 7172","22-23년 순천전력지사 변전협력회사 총액공사","GIS 타임측정","2023-11-14 09:00","2023-11-14 18:00","2023-11-14 09:00","2023-11-14 18:00","연속"]
[270,"광주전남","순천","여수T/P CB 7100","22-23년 순천전력지사 변전협력회사 총액공사","GIS 타임측정","2023-11-13 09:00","2023-11-13 18:00","2023-11-13 09:00","2023-11-13 18:00","연속"]
[271,"광주전남","순천","여수T/P #1 Tie-Tr","22-23년 순천전력지사 변전협력회사 총액공사","M.Tr 부싱교체, 2차 GIS 정밀점검","2023-11-13 09:00","2023-11-17 18:00","취소","취소","연속"]
[272,"광주전남","순천","여수T/P 예비 M.TR CB","22-23년 순천전력지사 변전협력회사 총액공사","M.Tr 부싱교체","2023-11-13 09:00","2023-11-17 18:00","취소","취소","연속"]
[273,"광주전남","순천","율촌C/C CB 7271","22-23년 순천전력지사 변전협력회사 총액공사","GIS 타임측정","2023-11-22 09:00","2023-11-22 18:00","2023-11-22 09:00","2023-11-22 18:00","연속"]
[274,"광주전남","순천","율촌CC여수TP T/L","345kV 율촌CC분기 T/L EBA 자기애관 교체공사","광양-율촌CC 3상, 율촌CC-여수TP 3상 애관교체(자기애관 → 폴리머애관)","2023-11-20 09:00","2023-11-22 18:00","2023-11-20 09:00","2023-11-22 18:00","연속"]
[275,"광주전남","순천","광양율촌CC T/L","345kV 율촌CC분기 T/L EBA 자기애관 교체공사","광양-율촌CC 3상, 율촌CC-여수TP 3상 애관교체(자기애관 → 폴리머애관)","2023-11-13 09:00","2023-11-15 18:00","취소","취소","연속"]
[276,"대구","경산","신경산S/S #4 M.Tr","22~23년 경산PO 변전협력회사 총액공사","- #2S.Tr VCB 대체, 4285 DS 보통점검","2023-11-10 09:30","2023-11-10 18:00","2023-11-10 09:30","2023-11-10 18:00","연속"]
[277,"대구","경산","신경산S/S #2 M.Tr","22~23년 경산PO 변전협력회사 총액공사","- #1S.Tr VCB 대체, 4185 DS 보통점검","2023-11-09 09:30","2023-11-09 18:00","2023-11-09 09:30","2023-11-09 18:00","연속"]
[278,"대구","달성","북경남고령#2 T/L","2023년 가공송전 순시점검 위탁공사","345kV 북경남-고령#2T/L 정밀점검","2023-11-13 08:00","2023-11-17 18:00","2023-11-13 08:00","2023-11-17 18:00","연속"]
[279,"대구","달성","북경남고령#1 T/L","2023년 가공송전 순시점검 위탁공사","345kV 북경남-고령#1T/L 정밀점검","2023-11-07 08:00","2023-11-10 18:00","2023-11-07 08:00","2023-11-10 18:00","연속"]
[280,"대구","달성","대구S/S #2 BUS","모선보호반 대체","모선보호반 대체","2023-11-27 09:00","2023-11-30 18:00","2023-11-27 09:00","2023-11-30 18:00","연속"]
[281,"대구","달성","대구S/S #1 BUS","모선보호반 대체","모선보호반 대체","2023-11-20 09:00","2023-11-23 18:00","2023-11-20 09:00","2023-11-23 18:00","연속"]
[282,"대구","달성","대구S/S #1 BUS","[TEST]T/L GIS 정밀점검","[TEST]T/L GIS 정밀점검","2023-11-02 17:00","2023-11-02 18:00","2023-11-02 17:00","2023-11-02 18:00","연속"]
[283,"대구","칠곡","북대구서대구#2 T/L","북대구S/S 345kV GIS 보통점검","북대구S/S 345kV GIS * 10대 보통점검","2023-11-29 08:30","2023-12-01 18:00","2023-11-29 08:30","2023-12-01 18:00","연속"]
[284,"대구","칠곡","북대구선산 T/L","22-23년 칠곡전력 가공송전협력 총액공사","수평 추락방지장치 설치","2023-11-27 07:30","2023-12-15 18:00","2023-11-27 07:30","2023-12-15 18:00","연속"]
[285,"대구","칠곡","북대구S/S #2 M.Tr","북대구S/S 345kV GIS 보통점검","북대구S/S 345kV GIS * 10대 보통점검","2023-11-20 09:30","2023-11-21 12:00","2023-11-20 09:30","2023-11-21 12:00","연속"]
[286,"대구","칠곡","북대구S/S #3 M.Tr","북대구S/S 345kV GIS 보통점검","북대구S/S 345kV GIS * 10대 보통점검","2023-11-21 13:00","2023-11-23 18:00","2023-11-21 13:00","2023-11-23 18:00","연속"]
[287,"대구","칠곡","북대구S/S #1 Sh.R CB","북대구S/S 345kV GIS 보통점검","북대구S/S 345kV GIS * 10대 보통점검","2023-11-27 09:30","2023-11-28 18:00","2023-11-27 09:30","2023-11-28 18:00","연속"]
[288,"대구","칠곡","북대구S/S #1 M.Tr","북대구S/S 345kV GIS 보통점검","북대구S/S 345kV GIS * 10대 보통점검","2023-11-13 09:00","2023-11-14 18:00","2023-11-13 09:00","2023-11-14 18:00","연속"]
[289,"대구","칠곡","북경남서대구#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치공사(345kV 북경남-무주양수T/L 병가선로)(안전확보)","2023-11-01 07:00","2023-11-29 18:00","2023-11-20 07:00","2023-11-24 18:00","연속"]
[290,"대구","칠곡","북경남서대구#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치공사(345kV 신옥천-북경남T/L 병가선로)(안전확보)","2023-11-30 07:00","2023-12-22 18:00","취소","취소","연속"]
[291,"대구","포항","신영일안동CC T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","기설철탑 수평 추락방지장치 설치","2023-11-20 08:00","2023-11-27 18:00","2023-11-20 08:00","2023-11-27 18:00","연속"]
[292,"대구","포항","신영일S/S #4 M.Tr","포항전력지사 하반기 M.Tr 점검공사","신영일S/S #4M.Tr 보통점검","2023-11-13 09:00","2023-11-14 18:00","2023-11-13 09:00","2023-11-14 18:00","연속"]
[293,"대구","포항","월성NP신월성NP#1 T/L","포항전력지사 하반기 GIS, GCB 점검공사","신월성S/Y 7371 GIS 보통점검","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[294,"대구","포항","신포항S/S #2 M.Tr","신포항S/S 345kV 주변압기측 현대화 공사","신포항S/S 345kV 주변압기측 현대화 공사","2023-11-13 08:00","2023-11-24 17:00","2023-11-27 08:00","2023-12-08 17:00","연속"]
[295,"대구","포항","신포항신월성NP#1 T/L","‘23년 포항전력지사 하반기 154kV GIS 기기점검공사","신포항S/S 7572 GCB 보통점검[발주]","2023-11-08 09:00","2023-11-15 18:00","2023-11-08 09:00","2023-11-15 18:00","연속"]
[296,"대구","포항","신포항신월성NP#2 T/L","‘23년 포항전력지사 하반기 154kV GIS 기기점검공사","신포항S/S 7472 GCB 보통점검[발주]","2023-11-08 09:00","2023-11-15 18:00","2023-11-08 09:00","2023-11-15 18:00","연속"]
[297,"대구","포항","신포항청송PP T/L","345kV 영포 외 15개 T/L 추락방지장치 설치 등 송전정비공사","345kV 영포 T/L 추락방지장치 설치","2023-11-06 07:00","2023-11-15 18:00","2023-11-06 07:00","2023-11-15 18:00","연속"]
[298,"대구","포항","신포항S/S #1 M.Tr","신포항S/S 345kV 주변압기측 현대화 공사","신포항S/S 345kV 주변압기측 현대화 공사","2023-11-27 08:00","2023-12-08 17:00","2023-12-11 08:00","2023-12-27 17:00","연속"]
[299,"대구","포항","신울산월성NP#1 T/L","포항전력지사 하반기 GIS, GCB 점검공사","월성S/Y 7771 GIS 보통점검","2023-11-20 09:00","2023-11-20 18:00","취소","취소","연속"]
[300,"경북","구미","북대구선산 T/L","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 70BUS 재연결 후 무부하 가압","2023-11-30 16:00","2023-12-01 18:00","취소","취소","연속"]
[301,"경북","구미","선산S/S #70 BUS","선산S/S 345kV 장기사용 GIS 용량교체공사(4차)","○ 70BAY GIS 교체(70BUS 재연결)","2023-11-27 09:00","2023-12-01 18:00","취소","취소","연속"]
[302,"경북","영주","신영주한울NP#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","TCSC 냉각설비 보통점검 71BAY B/F 보호반 대체","2023-11-09 09:00","2023-11-22 18:00","2023-11-09 09:00","2023-11-22 18:00","연속"]
[303,"경북","영주","신영주S/S #2 TCSC CB","2022-23년 영주전력지사 변전협력회사 총액공사","TCSC 냉각설비 보통점검","2023-11-09 09:00","2023-11-22 18:00","2023-11-09 09:00","2023-11-22 18:00","연속"]
[304,"경북","영주","신영주한울NP#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","TCSC 냉각설비 보통점검 71BAY B/F 보호반 대체","2023-11-09 09:00","2023-11-22 18:00","취소","취소","연속"]
[305,"경북","영주","신제천신영주#1 T/L","2023년 가공송전 순시점검 위탁공사 정밀점검","345kV 신제천-신영주T/L 정밀점검","2023-11-06 09:00","2023-11-10 18:00","취소","취소","매일"]
[306,"경북","영주","신영주S/S #2 TCSC CB","2022-23년 영주전력지사 변전협력회사 총액공사","TCSC 냉각설비 보통점검","2023-11-09 09:00","2023-11-22 18:00","취소","취소","연속"]
[307,"경북","영주","신영주S/S #3 M.Tr","2022-23년 영주전력지사 변전협력회사 총액공사","M.Tr,LA,PT 보통점검","2023-11-27 09:00","2023-11-28 18:00","2023-11-27 09:00","2023-11-28 18:00","연속"]
[308,"경북","영주","신영주S/S #1 M.Tr","2022-23년 영주전력지사 변전협력회사 총액공사","71BAY B/F 대체 96PDT 경보 이설 1차 CB 어큐물레이터 교체 M.Tr,LA 보통점검 부싱절연유 채유","2023-11-13 09:00","2023-11-22 18:00","취소","취소","연속"]
[309,"경북","영주","신제천신영주#2 T/L","2023년 가공송전 순시점검 위탁공사 정밀점검","345kV 신영주-신제천T/L 정밀점검","2023-11-13 09:00","2023-11-17 18:00","취소","취소","매일"]
[310,"부산울산","동부산","고리N/P CB 7872","고리NP S/Y 7872GIS 보통점검","고리NP S/Y 7872GIS 보통점검","2023-11-01 09:00","2023-11-01 18:00","2023-11-01 09:00","2023-11-01 18:00","연속"]
[311,"부산울산","동부산","고리N/P CB 7400","고리NP S/Y 7400GIS 하자점검","고리NP S/Y 7400GIS 하자점검","2023-11-28 09:00","2023-11-28 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[312,"부산울산","동부산","고리N/P CB 7472","고리NP S/Y 7472GIS 하자점검","고리NP S/Y 7472GIS 하자점검","2023-11-27 09:00","2023-11-27 18:00","2023-11-07 09:00","2023-11-07 18:00","연속"]
[313,"부산울산","동부산","고리N/P CB 7971","고리NP S/Y 7971GIS 보통점검","고리NP S/Y 7971GIS 보통점검","2023-11-09 09:00","2023-11-09 18:00","2023-11-09 09:00","2023-11-09 18:00","연속"]
[314,"부산울산","동부산","고리N/P CB 7800","고리NP S/Y 7800GIS 보통점검","고리NP S/Y 7800GIS 보통점검","2023-11-02 09:00","2023-11-02 18:00","취소","취소","연속"]
[315,"부산울산","동부산","신양산S/S #3 M.Tr","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(3차) - 75BAY GIS 50kA 3CCT 철거 - 75BAY GIS 63kA 3CCT 설치","2023-11-06 08:00","2024-04-05 18:00","2023-11-07 08:00","2024-04-05 18:00","연속"]
[316,"부산울산","동부산","신양산고리NP#1 T/L","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(3차) 사전작업 - 신양산-고리#1T/L 인출BAY 변경을 위한 사전작업(76BAY -> 75BAY) - 신양산-고리#1T/L 외장 LA 이설","2023-11-11 08:00","2023-11-12 18:00","2023-11-11 08:00","2023-11-12 18:00","연속"]
[317,"부산울산","동부산","신양산S/S CB 7671","신양산S/S 7671 GIS 보통점검","신양산S/S 7671 GIS 보통점검","2023-11-20 09:00","2023-11-20 18:00","취소","취소","연속"]
[318,"부산울산","동부산","신양산S/S CB 7571","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(3차) ※ 휴전대상 : 7571CB - 75BAY GIS 50kA 3CCT 철거 - 75BAY GIS 63kA 3CCT 설치","2023-11-06 08:00","2024-04-05 18:00","2023-11-07 08:00","2024-04-05 18:00","연속"]
[319,"부산울산","북부산","북부산울산TP#1 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-울산TP#1T/L 수평추락방지장치 설치 : 28~148호, 104기","2023-11-06 08:00","2023-11-17 18:00","취소","취소","연속"]
[320,"부산울산","북부산","북부산S/S #1 M.Tr","북부산전력지사 154kV 효성제 전동스프링 메커니즘 보강공사","북부산S/S 345kV #1M.Tr 2차 GIS(6144) 메커니즘 보강공사","2023-11-06 09:00","2023-11-06 18:00","2023-11-06 09:00","2023-11-06 18:00","연속"]
[321,"부산울산","북부산","북부산신울산#1 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-울산TP#2T/L 수평추락방지장치 설치 : 28~148호, 104기","2023-11-30 08:00","2023-12-09 18:00","취소","취소","연속"]
[322,"부산울산","북부산","신김해북부산#1 T/L","154kV 호포-물금T/L 정밀점검(안전확보 휴전)","154kV 호포-물금T/L정밀점검 다회선 철탑 작업 안전확보 휴전(345kV 신김해-북부산T/L 17호)","2023-11-09 09:00","2023-11-09 18:00","취소","취소","연속"]
[323,"부산울산","북부산","북부산S/S Sh.R CB","22-23년 북부산전력지사 변전총액공사","북부산S/S 345kV #1Sh.R 보통점검","2023-11-08 09:00","2023-11-08 18:00","2023-11-10 09:00","2023-11-10 18:00","연속"]
[324,"부산울산","북부산","신김해북부산#2 T/L","154kV 북부산-호포T/L 정밀점검(안전확보 휴전)","154kV 북부산-호포T/L 정밀점검 다회선 철탑 작업 안전확보 휴전(345kV 신김해-북부산T/L 17호)","2023-11-07 09:00","2023-11-07 18:00","2023-11-07 09:00","2023-11-07 18:00","연속"]
[325,"부산울산","북부산","북부산울산TP#2 T/L","345kV 북부산-신울산 등 3개T/L 수평추락방지장치 설치공사","345kV 북부산-울산TP#2T/L 수평추락방지장치 설치 : 28~148호, 104기","2023-11-18 08:00","2023-11-29 18:00","취소","취소","연속"]
[326,"부산울산","서부산","신녹산S/S #2 M.Tr","신녹산S/S 345kV #2 M.Tr 보호PNL 대체작업","신녹산S/S 345kV #2 M.Tr 보호PNL 대체작업","2023-11-27 09:00","2023-11-30 18:00","2023-11-27 09:00","2023-11-30 18:00","연속"]
[327,"부산울산","서부산","신김해신녹산#2 T/L","345kV 신김해-신녹산 등 5개T/L 철탑보강공사","항공구 설치 전 철탑 상부재 보강공사","2023-11-06 08:00","2023-11-10 18:00","취소","취소","연속"]
[328,"부산울산","서부산","신김해신녹산#1 T/L","345kV 신김해-신녹산 등 5개T/L 철탑보강공사","항공구 설치 전 철탑 상부재 보강공사 및 가공지선 교체","2023-11-13 08:00","2023-11-17 18:00","2023-11-13 08:00","2023-11-17 18:00","연속"]
[329,"부산울산","울산","신온산남울산#1 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-11-15 07:00","2023-11-20 18:00","2023-11-15 07:00","2023-11-20 18:00","연속"]
[330,"부산울산","울산","신온산남울산#2 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-11-29 07:00","2023-12-08 18:00","2023-11-29 07:00","2023-12-08 18:00","연속"]
[331,"부산울산","울산","동울산월성NP T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 및 폴리머지지애자 설치","2023-11-01 07:00","2023-11-15 18:00","취소","취소","연속"]
[332,"부산울산","울산","신온산S/S #2 M.Tr","22~23년 변전협력회사 총액공사","- 1,2차 부싱 절연유 채유","2023-11-13 09:00","2023-11-13 18:00","2023-11-13 09:00","2023-11-13 18:00","연속"]
[333,"부산울산","울산","북부산신울산#2 T/L","22~23년 변전협력회사 총액공사","- 피뢰기 보통점검","2023-11-15 09:00","2023-11-15 18:00","2023-11-15 09:00","2023-11-15 18:00","연속"]
[334,"부산울산","울산","신울산S/S #2 M.Tr","22~23년 변전협력회사 총액공사","- 1차 피뢰기 대체","2023-11-29 09:00","2023-11-29 18:00","2023-11-29 09:00","2023-11-29 18:00","연속"]
[335,"부산울산","울산","신울산고리NP#2 T/L","765kV북경남-신고리 등 7개T/L 추락방지장치 설치공사","345kV 신울산-고리NP#2T/L 68기 추락방지장치 설치","2023-11-13 07:00","2023-11-23 18:00","취소","취소","연속"]
[336,"부산울산","울산","신울산S/S #70G BUS","신울산S/S 345kV 용량대체공사","- 71BAY 무부하가압","2023-11-21 09:00","2023-11-22 18:00","2023-11-21 09:00","2023-11-22 18:00","연속"]
[337,"부산울산","울산","신온산신울산#2 T/L","신울산S/S 345kV 용량대체공사","- 71BAY 무부하가압","2023-11-21 09:00","2023-11-22 18:00","2023-11-21 09:00","2023-11-22 18:00","연속"]
[338,"부산울산","울산","울산C/C #3 Tie-Tr","22~23년 변전협력회사 총액공사","- M.Tr 보통점검 - 1차 GIS(7271, 7200) 보통점검 - 2차 GIS 차단기 동작시험","2023-11-19 09:00","2023-11-19 18:00","2023-11-19 09:00","2023-11-19 18:00","연속"]
[339,"부산울산","울산","울산C/C CB 7A72","23년 울산전력지사 개폐장치 보통점검공사","- 7A72 GIS 보통점검","2023-11-01 09:00","2023-11-01 18:00","2023-11-01 09:00","2023-11-01 18:00","연속"]
[340,"부산울산","울산","울산C/C #1 Tie-Tr","22~23년 변전협력회사 총액공사","- M.Tr 보통점검 - 1차 GIS(7471, 7400) 보통점검 - 2차 GIS 차단기 동작시험 - 3차 GIS(4184) 보통점검 - #1S.Tr 보통점검","2023-11-05 09:00","2023-11-05 18:00","2023-11-05 09:00","2023-11-05 18:00","연속"]
[341,"부산울산","울산","울주고리NP#1 T/L","765kV북경남-신고리 등 7개T/L 추락방지장치 설치공사","345kV 울주-고리NP#1T/L 35기 추락방지장치 설치","2023-11-01 07:00","2023-11-10 18:00","취소","취소","연속"]
[342,"부산울산","울산","울주S/S CB 7A71","22~23년 변전협력회사 총액공사","- 7A71 GIS 보통점검","2023-11-15 09:00","2023-11-15 18:00","2023-11-15 09:00","2023-11-15 18:00","연속"]
[343,"부산울산","울산","울주S/S CB 7900","22~23년 변전협력회사 총액공사","- 7900 GIS 보통점검","2023-11-14 09:00","2023-11-14 18:00","2023-11-14 09:00","2023-11-14 18:00","연속"]
[344,"부산울산","울산","울주S/S CB 7971","22~23년 변전협력회사 총액공사","- 7971 GIS 보통점검","2023-11-13 09:00","2023-11-13 18:00","2023-11-13 09:00","2023-11-13 18:00","연속"]
[345,"부산울산","울산","울주고리NP#2 T/L","765kV북경남-신고리 등 7개T/L 추락방지장치 설치공사","345kV 울주-고리NP#2T/L 35기 추락방지장치 설치","2023-11-24 07:00","2023-12-05 18:00","취소","취소","연속"]
[346,"부산울산","직할","신대연S/S #2 M.Tr","22~23년 직할 변전협력회사 총액공사","신대연S/S #2S.Tr 보통점검","2023-11-09 09:00","2023-11-09 18:00","2023-11-09 09:00","2023-11-09 18:00","연속"]
[347,"경남","직할","신김해S/S CB 7771","신김해S/S 신김해-신녹산#1T/L(7771) GIS 조작시험","신김해S/S 신김해-신녹산#1T/L(7771) GIS 조작시험","2023-11-02 14:00","2023-11-02 18:00","2023-11-02 14:00","2023-11-02 18:00","연속"]
[348,"경남","직할","신김해S/S #1 M.Tr","신김해S/S 345kV #1M.Tr 보통점검 및 보호반 대체작업","신김해S/S 345kV #1M.Tr 보통점검 및 보호반 대체작업 (병행)7372,7300 GIS 보통점검 4179 조작시험 (병행)1,2,3차 LA 보통점검 및 부싱 절연유 채유","2023-11-20 09:00","2023-11-23 18:00","2023-11-20 09:00","2023-11-23 18:00","연속"]
[349,"경남","직할","신김해S/S #5 M.Tr","신김해S/S #5M.Tr 1,2차 CB 점검","신김해S/S #5M.Tr 1차 7600 GIS 보통점검, 7672 GIS 조작시험 (병행)6544 공기조작부 점검","2023-11-13 09:00","2023-11-14 18:00","2023-11-27 09:00","2023-11-28 18:00","연속"]
[350,"경남","직할","신김해S/S CB 7271","신김해S/S 신마산-신김해#1T/L(7271) GIS 조작시험","신김해S/S 신마산-신김해#1T/L(7271) GIS 조작시험","2023-11-02 09:00","2023-11-02 14:00","2023-11-02 09:00","2023-11-02 14:00","연속"]
[351,"경남","직할","신김해북부산#2 T/L","[안전거리] 신김해-진례#1T/L 휴전작업 관련 안전거리 확보차","신김해-진례#1T/L 9호 휴전작업 관련 안전거리 확보차","2023-11-23 07:00","2023-11-23 18:00","취소","취소","연속"]
[352,"경남","직할","신김해북부산#1 T/L","345kV 신김해-북부산T/L 송전선로 초기점검","345kV 신김해-북부산T/L 송전선로 초기점검(78,79,94호)","2023-11-08 08:00","2023-11-08 18:00","2023-11-08 08:00","2023-11-08 18:00","연속"]
[353,"경남","직할","신김해북부산#2 T/L","345kV 신김해-북부산T/L 송전선로 초기점검","345kV 신김해-북부산T/L 송전선로 초기점검(78,79,94호)","2023-11-09 08:00","2023-11-09 18:00","취소","취소","연속"]
[354,"경남","직할","창원신고성#1 T/L","345kV 창원-신고성T/L 추락방지장치 설치공사","345kV 창원-신고성T/L 추락방지장치 설치공사","2023-11-06 08:00","2023-11-26 18:00","2023-11-09 07:00","2023-11-11 18:00","매일"]
[355,"경남","직할","창원신고성#2 T/L","345kV 창원-신고성T/L 추락방지장치 설치공사","345kV 창원-신고성T/L 추락방지장치 설치공사","2023-11-27 08:00","2023-12-10 18:00","2023-11-12 07:00","2023-11-13 18:00","매일"]
[356,"경남","진주","의령S/S #3 M.Tr","의령S/S 345kV #3M.Tr 3차 PT 보통점검","의령S/S 345kV #3M.Tr 3차 PT 보통점검","2023-11-09 09:00","2023-11-09 18:00","2023-11-09 09:00","2023-11-09 18:00","연속"]
[357,"경남","진주","의령S/S #2 M.Tr","의령S/S 345kV #2M.Tr 2차 LA 초기, 1,2차 부싱유 채유","의령S/S 345kV #2M.Tr 2차 LA 초기점검, 1,2차 부싱유 채유 [병행] 2차 GIS 6244 조작 [병행] 3차 VCB 4279 조작 [병행] 4284 조작,427-1,427-2보통","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[358,"경남","진주","신남원의령#2 T/L","의령S/S 345kV 신남원-의령#2T/L 7771,7700 보통점검","의령S/S 345kV 신남원-의령#1T/L 7871,7800 보통점검 [병행] LA 초기, PT 하자점검","2023-11-06 09:00","2023-11-07 18:00","취소","취소","연속"]
[359,"경남","진주","의령하동화력#1 T/L","하동T/P 의령-하동화력#1T/L GIS 조작시험 등","하동T/P 의령-하동화력#1T/L GIS 조작시험 등 [병행] LA 보통점검, PT 대체","2023-11-05 07:00","2023-11-05 18:00","취소","취소","연속"]
[360,"경남","진주","신남원의령#1 T/L","의령S/S 345kV 신남원-의령#1T/L 7871,7800 보통점검","의령S/S 345kV 신남원-의령#1T/L 7871,7800 보통점검 [병행] LA 초기, PT 하자점검","2023-11-02 09:00","2023-11-03 18:00","취소","취소","연속"]
[361,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151","2023-11-26 07:00","2023-11-26 18:00","2023-11-26 07:00","2023-11-26 18:00","연속"]
[362,"경남","진주","의령신마산#2 T/L","의령S/S 345kV 의령-신마산#2T/L LA 초기점검","의령S/S 345kV 의령-신마산#2T/L LA 초기점검","2023-11-24 09:00","2023-11-24 18:00","2023-11-24 09:00","2023-11-24 18:00","연속"]
[363,"경남","진주","의령신마산#1 T/L","의령S/S 345kV 의령-신마산#1T/L GIS 7900,7971 보통","의령S/S 345kV 의령-신마산#1T/L GIS 7900,7971 보통 [병행] LA 초기점검, PT 보통점검","2023-11-22 09:00","2023-11-23 18:00","2023-11-22 09:00","2023-11-23 18:00","연속"]
[364,"경남","진주","고령의령#2 T/L","의령S/S 345kV 고령-의령#2T/L GIS 7571 보통점검","의령S/S 345kV 고령-의령#2T/L GIS 7571 보통점검 [병행] PT 하자점검","2023-11-21 09:00","2023-11-21 18:00","2023-11-21 09:00","2023-11-21 18:00","연속"]
[365,"경남","진주","고령의령#1 T/L","의령S/S 345kV 고령-의령#1T/L GIS 7671 보통점검","의령S/S 345kV 고령-의령#1T/L GIS 7671 보통점검","2023-11-20 09:00","2023-11-20 18:00","2023-11-20 09:00","2023-11-20 18:00","연속"]
[366,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.134~151","2023-11-19 07:00","2023-11-19 18:00","2023-11-19 07:00","2023-11-19 18:00","연속"]
[367,"경남","진주","의령산청양수#1 T/L","345lkV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수직,수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.1~130 (345kV 의령-하동화력 T/L과 병가 구간 No.112~129)","2023-11-17 07:00","2023-12-15 18:00","취소","취소","매일"]
[368,"경남","진주","신남원의령#2 T/L","OPGW 취약개소 금구류 보강공사","OPGW 클램프 3개 교체 등","2023-11-13 07:00","2023-11-15 18:00","취소","취소","매일"]
[369,"경남","진주","고령의령#1 T/L","OPGW 취약개소 금구류 정비공사","OPGW 금구류 3개소 교체","2023-11-11 07:00","2023-11-11 18:00","취소","취소","연속"]
[370,"경남","진주","의령하동화력#2 T/L","OPGW 취약개소 금구류 보강공사","OPGW 현수클램프 11개 교체","2023-11-12 07:00","2023-11-12 18:00","취소","취소","매일"]
[371,"경남","통영","고성하이T/P CB 7171","고성하이S/Y 345kV 신고성-고성하이발전#2T/L CB 7171 휴전","GIS 보통점검(7171CB)","2023-11-06 09:00","2023-11-06 18:00","취소","취소","연속"]
[372,"경남","통영","신고성S/S CB 7500","신고성S/S 345kV #3M.Tr-G5호기 CB 7500 휴전","GIS 보통점검(7500CB)","2023-11-08 09:00","2023-11-08 18:00","취소","취소","연속"]
[373,"경남","통영","신고성S/S CB 7571","신고성S/S 345kV G5호기 1차 CB 7571 휴전","GIS 보통점검(7571CB)","2023-11-07 09:00","2023-11-07 18:00","취소","취소","연속"]
[374,"경남","통영","신고성S/S #3 M.Tr","삼천포S/Y, 신고성S/S 345kV GIS 철거공사","1. 345kV GIS 40kA 4,000A x 30CB 가스회수 및 철거 2. 기타 부대서식","2023-11-06 09:00","2023-11-08 18:00","2023-11-06 09:00","2023-11-08 18:00","연속"]
[375,"경남","함안","북경남무주양수 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치공사(345kV 북경남-무주양수T/L 병가선로)(안전확보)","2023-11-01 07:00","2023-11-29 18:00","2023-11-20 09:00","2023-11-25 18:00","매일"]
[376,"경남","함안","신옥천북경남 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치공사(345kV 신옥천-북경남T/L 병가선로)(안전확보)","2023-11-30 07:00","2023-12-22 18:00","취소","취소","연속"]
[377,"경남","함안","신마산신고성#2 T/L","신마산S/S 345KV GIS 고장관련 점검","신마산s/s 345KV GIS 76BAY 고장관련 인근 동일 생산, 설치 설비 건전성 확인","2023-11-03 13:30","2023-11-03 17:30","2023-11-03 13:30","2023-11-03 17:30","연속"]
[378,"경남","함안","신마산신고성#1 T/L","신마산S/S 345KV GIS 고장관련 점검","신마산s/s 345KV GIS 76BAY 고장관련 인근 동일 생산, 설치 설비 건전성 확인","2023-11-03 09:00","2023-11-03 13:30","2023-11-03 09:00","2023-11-03 13:30","연속"]
[379,"경남","함안","신마산신고성#1 T/L","345kV 신마산-신고성T/L 추락방지장치 설치공사","345kV 신마산-신고성T/L 추락방지장치 설치 83호~177호 (11월11일(토), 12일(일) 주말작업 없음)","2023-11-06 08:00","2023-11-14 18:00","취소","취소","매일"]
[380,"경남","함안","신마산S/S #5 M.Tr","신마산S/S 345KV GIS 고장관련 점검","신마산s/s 345KV GIS 76BAY 고장관련 인근 동일 생산, 설치 설비 건전성 확인","2023-11-07 09:30","2023-11-07 13:30","2023-11-07 09:30","2023-11-07 13:30","연속"]
[381,"경남","함안","의령신마산#2 T/L","신마산S/S 345KV GIS 고장관련 점검","신마산s/s 345KV GIS 76BAY 고장관련 인근 동일 생산, 설치 설비 건전성 확인","2023-11-07 13:30","2023-11-07 17:30","취소","취소","연속"]
[382,"경남","함안","신마산신고성#2 T/L","345kV 신마산-신고성T/L 추락방지장치 설치공사","345kV 신마산-신고성T/L 추락방지장치 설치 83호~177호 (11월 16일(수능), 18일(토), 19일(일), 24일(휴무일), 25일(토), 26일(일) 작업 없음)","2023-11-15 08:00","2023-11-27 18:00","2023-11-07 08:00","2023-11-08 18:00","매일"]
[383,"강원","강릉","신양양S/S #3 M.Tr","2023년 강릉전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2023-11-10 10:00","2023-11-10 18:00","2023-11-10 10:00","2023-11-10 18:00","연속"]
[384,"광주전남",null,"한빛N/P #2호기 기동변압기 X01 (CB 7300, 7371)","한빛2호기 26차 계획예방정비 수행 * 조작차단기 : CB 7300, 7371","○ 기동변압기(X01) 점검","2023-11-14 08:00","2023-11-28 09:00","2023-11-14 08:00","2023-11-28 09:00","연속"]
[385,"강원",null,"양양P/P #3호기 주변압기 (CB 7200, 7272)","#3 계획중간정비","양양 P/P No.3 Main TR 휴전 (#3 동기차단기 교체)","2023-11-01 09:00","2023-12-14 23:59","2023-11-01 09:00","2023-12-14 23:59","연속"]
[386,"강원",null,"양양P/P #1,2,4호기 주변압기 (CB 7100, 7172, 7271, 7200, 7300, 7372)","자체기동 발전기 예비시험(개방 차단기 : 7100, 7271, 7300)","자체기동 발전기 예비시험(개방 차단기 : 7100, 7271, 7300)","2023-11-16 14:00","2023-11-16 16:00","2023-11-16 14:00","2023-11-16 16:00","연속"]
[387,"강원",null,"양양P/P #1,2,4호기 주변압기 (CB 7100, 7172, 7271, 7200, 7300, 7372)","자체기동 발전기 정기시험(개방 차단기 : 7100, 7271, 7300)","자체기동 발전기 정기시험(개방 차단기 : 7100, 7271, 7300)","2023-11-17 14:00","2023-11-17 16:00","2023-11-17 14:00","2023-11-17 16:00","연속"]
[388,"부산울산",null,"북부산신울산#2 T/L","북부산 STATCOM 설치관련\n71BUS 무부하시험","북부산 STATCOM 설치관련\n71BUS 무부하시험","2023-11-04 18:00","2023-11-05 18:00","2023-11-04 18:00","2023-11-05 18:00","연속"]
[389,"전북",null,"신옥천신남원#1 T/L","신남원S/S 72BAY BF 보호반 대체공사","신남원S/S 72BAY BF 보호반 대체공사","2023-11-20 09:00","2023-11-23 18:00","2023-11-20 09:00","2023-11-23 18:00","연속"]
[390,"전북",null,"신옥천신남원#2 T/L","신남원S/S 71BAY BF 보호반 대체공사","신남원S/S 71BAY BF 보호반 대체공사","2023-11-27 09:00","2023-11-30 18:00","2023-11-27 09:00","2023-11-30 18:00","연속"]
[391,"전북",null,"신남원한빛NP#1 T/L","신남원S/S 72BAY BF 보호반 대체공사","신남원S/S 72BAY BF 보호반 대체공사","2023-11-20 09:00","2023-11-23 18:00","2023-11-20 09:00","2023-11-23 18:00","연속"]
[392,"전북",null,"신남원한빛NP#2 T/L","신남원S/S 71BAY BF 보호반 대체공사","신남원S/S 71BAY BF 보호반 대체공사","2023-11-27 09:00","2023-11-30 18:00","2023-11-27 09:00","2023-11-30 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":804,"n_cols":11,"rows_kept":804,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]],"flags":["formulas_cached_only"]}
["2023년도 11월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#2 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T)","2023-11-02 13:00","2023-12-12 18:00","2023-11-02 13:00","2023-12-12 18:00","연속"]
[2,"서울","성동","구의S/S #2 BUS","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 2BUS 부 교체","2023-11-30 09:00","2023-12-12 18:00","2023-11-30 18:00","2023-12-12 18:00","연속"]
[3,"서울","성동","구의광장#1 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 구의-광장#2T/L, B/T 무부하가압 ○ 구의-광장#1T/L 광장S/S측 조작시험 병행","2023-11-29 09:00","2023-11-30 18:00","2023-11-29 09:00","2023-11-30 18:00","연속"]
[4,"서울","성동","천호구의#2 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 구의-광장#2T/L, B/T 무부하가압","2023-11-30 09:00","2023-11-30 18:00","2023-11-30 13:00","2023-11-30 18:00","연속"]
[5,"서울","성동","천호구의#1 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 구의-광장#2T/L, B/T 무부하가압","2023-11-30 09:00","2023-11-30 18:00","2023-11-30 09:00","2023-11-30 13:00","연속"]
[6,"서울","성동","천호구의#2 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 구의-광장#2T/L, B/T 무부하가압","2023-11-16 09:00","2023-11-16 18:00","2023-11-16 13:00","2023-11-16 18:00","연속"]
[7,"서울","성동","천호구의#1 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 구의-광장#2T/L, B/T 무부하가압","2023-11-16 09:00","2023-11-16 18:00","2023-11-16 09:00","2023-11-16 13:00","연속"]
[8,"서울","성동","구의S/S #1 BUS","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 1DS 분리, CB,1DS 부 교체","2023-11-16 09:00","2023-11-30 18:00","2023-11-16 09:00","2023-11-30 18:00","연속"]
[9,"서울","성동","구의광장#1 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 2BUS 무부하가압","2023-11-14 09:00","2023-11-16 16:00","2023-11-14 09:00","2023-11-16 16:00","연속"]
[10,"서울","성동","구의S/S CB 6100","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T)","2023-11-13 09:00","2023-12-12 18:00","2023-11-13 09:00","2023-12-12 18:00","연속"]
[11,"서울","성동","구의광장#1 T/L","구의S/S 154kV 장기사용 GIS 교체공사(전문)","○ 154kV GIS 교체 × 2Bay(구의-광장#2T/L, B/T) - 1BUS, CB, 1DS 무부하가압","2023-11-14 09:00","2023-11-16 18:00","2023-11-14 09:00","2023-11-16 18:00","연속"]
[12,"서울","성동","노원종암 T/L","'23년 성동P/O 노후 보호배전반 교체공사","노원, 종암S/S 154kV 노원-종암T/L 보호배전반 노후대체","2023-11-20 09:00","2023-11-23 18:00","2023-11-20 09:00","2023-11-23 18:00","연속"]
[13,"서울","성동","창동S/S #1 BUS","창동S/S 154kV 장기사용 GIS 교체공사","상계창동#2T/L, #2M.Tr 1차, PT&ES GIS 교체(2차분) - GIS CB, #1DS, 상부, C/H 철거 및 신품GIS 설치 후 #1BUS 가압","2023-11-24 09:00","2023-12-14 18:00","2023-11-25 09:00","2023-12-09 18:00","연속"]
[14,"서울","성동","방학창동#2 T/L","창동S/S 154kV 장기사용 GIS 교체공사","154kV GIS 1차분 교체 - 상계창동#1T/L, #1M.Tr 1차, 6100B/T - #1BUS 시험가압선로","2023-11-16 09:00","2023-11-17 18:00","2023-11-16 09:00","2023-11-17 18:00","연속"]
[15,"서울","성동","상계창동#2 T/L","창동S/S 154kV 장기사용 GIS 교체공사","상계창동#2T/L, #2M.Tr 1차, PT&ES GIS 교체(2차분)","2023-11-20 09:00","2023-12-22 18:00","2023-11-20 09:00","2023-12-22 18:00","연속"]
[16,"서울","성동","상계창동#1 T/L","창동S/S 154kV 장기사용 GIS 교체공사(전문)","상계창동#2T/L, #2M.Tr 1차, BUS PT&ES GIS 교체(2차분) - #2BUS 무부하가압 시험가압선로","2023-11-23 09:00","2023-11-24 18:00","2023-11-23 09:00","2023-11-24 18:00","연속"]
[17,"서울","성동","방학창동#2 T/L","창동S/S 154kV 장기사용 GIS 교체공사","154kV GIS 1차분 교체 - 상계창동#1T/L, #1M.Tr 1차, 6100B/T - #1BUS 시험가압선로","2023-11-09 09:00","2023-11-10 18:00","2023-11-03 09:00","2023-11-04 18:00","연속"]
[18,"서울","중부","원흥상암 T/L","154kV 원흥상암T/L EBA 절연유 채유","154kV 원흥상암T/L EBA 절연유 채유(수색S/S)","2023-11-29 09:00","2023-11-30 18:00","2023-11-29 09:00","2023-11-30 18:00","연속"]
[19,"서울","중부","수색상암 T/L","154kV 수색상암T/L EBA 절연유 채유","154kV 수색상암T/L EBA 절연유 채유(수색S/S)","2023-11-27 09:00","2023-11-28 18:00","2023-11-27 09:00","2023-11-28 18:00","연속"]
[20,"서울","중부","중부아현 T/L","23 중부P/O 총액공사","초기점검","2023-11-28 10:00","2023-11-28 18:00","2023-11-28 10:00","2023-11-28 18:00","연속"]
[21,"서울","중부","마장한남 T/L","23 중부P/O 총액공사","PT 보통점검","2023-11-20 10:00","2023-11-20 18:00","2023-11-20 10:00","2023-11-20 18:00","연속"]
[22,"서울","직할","현저서대문#1 T/L","154kV 현저서대문#1T/L EBG 가스 채취밸브 취부","154kV 현저서대문#1T/L 서대문EBG 가스 채취밸브 취부","2023-11-06 09:00","2023-11-07 18:00","2023-11-06 09:00","2023-11-07 18:00","연속"]
[23,"서울","직할","현저서대문#2 T/L","154kV 현저서대문#2T/L EBG 가스 채취밸브 취부","154kV 현저서대문#2T/L 서대문EBG 가스 채취밸브 취부","2023-11-08 09:00","2023-11-09 18:00","2023-11-08 09:00","2023-11-09 18:00","연속"]
[24,"서울","직할","종로서소문 T/L","154kV 종로서소문T/L EBG 가스 채취밸브 취부","154kV 종로서소문T/L 서소문EBG 가스 채취밸브 취부","2023-12-04 09:00","2023-12-07 18:00","취소","취소","연속"]
[25,"서울","직할","중앙서소문 T/L","154kV 중앙서소문T/L EBG 가스 채취밸브 취부","154kV 중앙서소문T/L 서소문EBG 가스 채취밸브 취부","2023-11-20 09:00","2023-11-23 18:00","2023-11-20 09:00","2023-11-23 18:00","연속"]
[26,"서울","직할","신촌S/S #2 BUS","신촌S/S 154kV 장기사용 GIS 교체공사","154kV #3M.Tr 1차 GIS 교체작업","2023-11-27 09:00","2023-12-07 18:00","2023-11-27 09:00","2023-12-07 18:00","연속"]
[27,"서울","직할","중앙서소문 T/L","서소문S/S 디지털화","서소문S/S 디지털화","2023-11-20 09:00","2023-11-21 18:00","취소","취소","연속"]
[28,"남서울","강남","신양재신사#3 T/L","154kV 신성남-염곡 등 4개 T/L EBG 가스채취밸브 설치공사","열경화공법 대한전선제 EBG 가스채취밸브 설치","2023-11-01 09:00","2023-11-03 18:00","취소","취소","연속"]
[29,"남서울","동서울","논현선릉#1 T/L","선릉S/S 논현-선릉#1T/L GIS 보통점검","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-11-13 09:00","2023-11-13 18:00","2023-11-13 09:00","2023-11-13 18:00","연속"]
[30,"남서울","동서울","동서울송파#2 T/L","'23~'24년 동서울 지중 위탁 총액공사","거여C/T 피뢰기 점검","2023-11-02 12:00","2023-11-02 17:00","2023-11-02 12:00","2023-11-02 17:00","연속"]
[31,"남서울","동서울","동서울송파#1 T/L","'23~'24년 동서울 지중 위탁 총액공사","거여C/T 피뢰기 점검","2023-11-02 08:00","2023-11-02 12:00","2023-11-02 08:00","2023-11-02 12:00","연속"]
[32,"남서울","동서울","잠실수서#1 T/L","수서S/S 잠실-수서#1T/L 피뢰기누설전류계 교체","2022~2023년도 동서울전력지사 변전협력회사 총액공사","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[33,"남서울","동서울","탄천선릉#2 T/L","154kV 탄천-선릉#2T/L 위치조정공사","영동대로 지하공간 복합개발 사업에 따른 전력설비 이설 □ 사업구간 : 154kV 탄천-선릉#2T/L J/B#1 ~ J/B#2, 약 50m □ 작업내용 : 신설전력구 공사를 위한 케이블 위치조정","2023-11-08 09:00","2023-11-10 18:00","2023-11-08 09:00","2023-11-10 18:00","연속"]
[34,"남서울","동서울","탄천선릉#1 T/L","23~24년 동서울 지중위탁 총액공사","선릉 EBG 가스채취밸브 설치공사","2023-11-06 08:00","2023-11-07 18:00","2023-11-06 08:00","2023-11-07 18:00","연속"]
[35,"남서울","동서울","풍납S/S #1 BUS","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-11-06 09:00","2023-11-09 13:00","취소","취소","연속"]
[36,"남서울","동서울","강동풍납#1 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-11-06 09:00","2023-12-14 18:00","취소","취소","연속"]
[37,"남서울","동서울","풍납석촌#1 T/L","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-11-08 13:00","2023-11-09 13:00","취소","취소","연속"]
[38,"남서울","동서울","풍납S/S #2 BUS","풍납S/S 장기사용 154kV GIS 교체공사","- 154kV GIS 5CCT 철거 및 설치 - 기타부대공사","2023-11-09 13:00","2023-12-07 18:00","취소","취소","연속"]
[39,"남서울","영등포","광명구공#2 T/L","광명S/S 154kV #4M.Tr 증설공사","○개요:154kV M.Tr x 1Bank, 170kV GIS x 1CCT, 23kV GIS x 3CCT 설치 - 무부하가압용","2023-11-01 16:00","2023-11-02 16:00","2023-11-01 16:00","2023-11-02 16:00","연속"]
[40,"남서울","영등포","신광명광명#1 T/L","광명S/S 154kV 장기사용 GIS 교체공사","154kV GIS 교체공사 완료에 따른 최종 CID 입력","2023-11-06 15:30","2023-11-06 16:00","2023-11-06 15:30","2023-11-06 16:00","연속"]
[41,"남서울","영등포","신광명광명#2 T/L","광명S/S 154kV 장기사용 GIS 교체공사","154kV GIS 교체공사 완료에 따른 최종 CID 입력","2023-11-06 16:00","2023-11-06 16:30","2023-11-06 16:00","2023-11-06 16:30","연속"]
[42,"남서울","영등포","신정목동#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-11-04 09:00","2023-11-04 14:00","취소","취소","연속"]
[43,"남서울","영등포","신정목동#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-11-04 14:00","2023-11-04 18:00","취소","취소","연속"]
[44,"남서울","영등포","신광명온수 T/L","'22-'23년 가공송전 협력회사 총액공사","추락방지설치, 피뢰기설치","2023-11-09 07:00","2023-11-14 18:00","2023-11-09 07:00","2023-11-14 18:00","연속"]
[45,"남서울","영등포","신정S/S #1 BUS","영등포전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 - 신정 6100 BUS-TIE - 무부하가압용","2023-11-18 09:00","2023-11-19 18:00","2023-11-18 09:00","2023-11-19 18:00","연속"]
[46,"남서울","영등포","부천신정#1 T/L","영등포전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 - 신정 6100 BUS-TIE - 무부하가압용","2023-11-19 13:00","2023-11-19 18:00","2023-11-19 13:00","2023-11-19 18:00","연속"]
[47,"남서울","영등포","신정S/S CB 6100","영등포전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검 - 신정 6100 BUS-TIE","2023-11-18 09:00","2023-11-19 18:00","2023-11-18 09:00","2023-11-19 18:00","연속"]
[48,"남서울","영등포","중동화곡#1 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-11-04 09:00","2023-11-04 14:00","2023-11-04 09:00","2023-11-04 14:00","연속"]
[49,"남서울","영등포","중동화곡#2 T/L","2022~23년 영등포전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2023-11-04 14:00","2023-11-04 18:00","2023-11-04 14:00","2023-11-04 18:00","연속"]
[50,"인천","김포","경서양촌#1 T/L","검단3구역 전력구 운영시스템 설치공사","-CCTV 및 부분방전 측정단자함, ILS, 다기능진단장치, 출입자 감시·제어, 부대설비 제어 등 설치 등","2023-11-23 09:00","2023-11-23 18:00","2023-11-21 09:00","2023-11-22 18:00","연속"]
[51,"인천","김포","경서양촌#2 T/L","검단3구역 전력구 운영시스템 설치공사","-CCTV 및 부분방전 측정단자함, ILS, 다기능진단장치, 출입자 감시·제어, 부대설비 제어 등 설치 등","2023-11-24 09:00","2023-11-24 18:00","2023-11-23 09:00","2023-11-24 18:00","연속"]
[52,"인천","김포","김포장기#1 T/L","154kV 불로S/S 건설공사","신규 불로변전소 건설 - 154kV M.Tr 2 Bank - 154kV GIS 10CCT - 23kV EGIS 13CCT - 기타 부대공사","2023-11-13 09:00","2023-11-14 18:00","2023-11-13 09:00","2023-11-14 18:00","연속"]
[53,"인천","김포","양촌양곡#1 T/L","23년 가공송전 협력회사 총액공사","수평 추락방지시설 설치","2023-11-11 08:00","2023-11-12 18:00","취소","취소","연속"]
[54,"인천","김포","양촌양곡#2 T/L","23년 가공송전 협력회사 총액공사","수평 추락방지시설 설치","2023-11-13 08:00","2023-11-14 18:00","취소","취소","연속"]
[55,"인천","김포","김포장기#1 T/L","장기S/S 154kV 김포-장기#1T/L GIS 보통점검","장기S/S 154kV 김포-장기#1T/L GIS 보통점검","2023-11-22 09:00","2023-11-22 18:00","2023-11-22 09:00","2023-11-22 18:00","연속"]
[56,"인천","김포","신김포장기#1 T/L","장기S/S 154kV 신김포-장기#1T/L GIS 보통점검","장기S/S 154kV 신김포-장기#1T/L GIS 보통점검","2023-11-21 10:00","2023-11-21 18:00","2023-11-21 10:00","2023-11-21 18:00","연속"]
[57,"인천","부평","서인천C/C SEC CB 60610","서인천C/C 154kV #60-#61 SEC GIS 조작시험","서인천C/C 154kV #60-#61 SEC GIS 조작시험","2023-11-23 09:00","2023-11-23 12:00","2023-11-23 09:00","2023-11-23 12:00","연속"]
[58,"인천","부평","서인천CC신경서 T/L","서인천C/C 154kV 서인천CC-신경서T/L GIS 조작시험","서인천C/C 154kV 서인천CC-신경서T/L GIS 조작시험","2023-11-18 09:00","2023-11-18 18:00","2023-11-18 09:00","2023-11-18 18:00","연속"]
[59,"인천","부평","서인천C/C SEC CB 65660","서인천C/C 154kV #65-#66 SEC GIS 조작시험","서인천C/C 154kV #65-#66 SEC GIS 조작시험","2023-11-23 12:00","2023-11-23 18:00","2023-11-23 12:00","2023-11-23 18:00","연속"]
[60,"인천","부평","송현포스코CC#1 T/L","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","- 추락방지시설 설치 - 고광도 항공장애표시등 위치변경 및 신규설치","2023-11-01 08:00","2023-11-03 18:00","취소","취소","연속"]
[61,"인천","부평","송현포스코CC#2 T/L","154kV 송현-포스코CCT/L 추락방지시설 및 항공시설물 정비공사","- 추락방지시설 설치 - 고광도 항공장애표시등 위치변경 및 신규설치","2023-11-08 08:00","2023-11-10 18:00","취소","취소","연속"]
[62,"인천","부평","신가좌부개#2 T/L","'23~'24년 지중송전위탁정비공사(인천본부 직할)","신가좌-부개T/L 요주의 개소 절연유 채취","2023-11-10 13:00","2023-11-12 18:00","2023-11-11 07:00","2023-11-12 18:00","연속"]
[63,"인천","부평","신가좌S/S SEC CB 65660","신가좌S/S 154kV #65-#66 SEC GIS 보통점검","신가좌S/S 154kV #65-#66 SEC GIS 보통점검","2023-11-13 13:00","2023-11-13 18:00","취소","취소","연속"]
[64,"인천","부평","신가좌S/S SEC CB 60610","신가좌S/S 154kV #60-#61 SEC GIS 보통점검","신가좌S/S 154kV #60-#61 SEC GIS 보통점검","2023-11-13 09:00","2023-11-13 12:00","취소","취소","연속"]
[65,"인천","부평","신가좌인천#2 T/L","신가좌S/S 154kV 신가좌-인천#2T/L GIS 조작시험","신가좌S/S 154kV 신가좌-인천#2T/L GIS 조작 (에어누기 확인)","2023-11-07 13:00","2023-11-07 18:00","취소","취소","연속"]
[66,"인천","부평","신가좌주안#2 T/L","154kV 신가좌-주안#2T/L GIS 조작시험 및 피뢰기 절연열화 측정","154kV 신가좌-주안#2T/L GIS 조작시험 및 피뢰기 절연열화 측정","2023-11-18 13:00","2023-11-18 18:00","취소","취소","연속"]
[67,"인천","부평","신가좌신현#2 T/L","154kV 신가좌-신현#2T/L GIS 피뢰기 절연열화 측정","154kV 신가좌-신현#2T/L GIS 피뢰기 절연열화 측정","2023-11-06 13:00","2023-11-06 18:00","취소","취소","연속"]
[68,"인천","부평","신가좌신현#1 T/L","154kV 신가좌-신현#1T/L GIS 피뢰기 절연열화 측정","154kV 신가좌-신현#1T/L GIS 피뢰기 절연열화 측정","2023-11-06 09:00","2023-11-06 13:00","취소","취소","연속"]
[69,"인천","부평","신가좌인천#3 T/L","154kV 신가좌인천#3 T/L GIS 보통점검","신가좌S/S 154kV 신가좌인천#3 T/L GIS 보통점검 - 주 인천S/S 154kV 신가좌인천#3 T/L GIS 보통점검 - 병행","2023-11-14 09:00","2023-11-14 18:00","취소","취소","연속"]
[70,"인천","부평","신가좌주안#1 T/L","신가좌S/S 154kV 신가좌-주안#1T/L GIS 휴전작업","154kV 신가좌-주안#1T/L GIS 조작시험, 피뢰기 절연열화","2023-11-18 09:00","2023-11-18 12:00","취소","취소","연속"]
[71,"인천","부평","신가좌인천#1 T/L","신가좌S/S 154kV 신가좌-인천#1T/L GIS 조작시험","신가좌S/S 154kV 신가좌-인천#1T/L GIS 조작 (에어누기 확인)","2023-11-07 09:00","2023-11-07 13:00","취소","취소","연속"]
[72,"인천","부평","신경서S/S SEC CB 65660","신경서S/S 154kV #61-66BUS 모선보호반 대체","신경서S/S 154kV #61-66BUS 모선보호반 대체","2023-11-13 09:00","2023-11-17 18:00","취소","취소","연속"]
[73,"인천","부평","신경서S/S SEC CB 60610","신경서S/S 154kV #61-66BUS 모선보호반 대체","신경서S/S 154kV #61-66BUS 모선보호반 대체","2023-11-13 09:00","2023-11-17 18:00","취소","취소","연속"]
[74,"인천","부평","신경서S/S CB 6200","신경서S/S 154kV #61-66BUS 모선보호반 대체","신경서S/S 154kV #61-66BUS 모선보호반 대체","2023-11-13 09:00","2023-11-17 18:00","취소","취소","연속"]
[75,"인천","부평","인천C/C 현대제철#2T/L CB","154kV 현대제철T/L 추락방지시설 설치공사","- 추락방지시설 설치","2023-11-08 08:00","2023-11-10 18:00","취소","취소","연속"]
[76,"인천","부평","인천C/C 현대제철#1T/L CB","154kV 현대제철T/L 추락방지시설 설치공사","- 추락방지시설 설치","2023-11-01 08:00","2023-11-03 18:00","취소","취소","연속"]
[77,"인천","부평","남인천학익#1 T/L","154kV 남인천-학익#1T/L SA혼용화 / 조작시험","154kV 남인천-학익#1T/L SA혼용화 / 조작시험","2023-11-02 09:00","2023-11-02 18:00","2023-11-20 09:00","2023-11-20 18:00","연속"]
[78,"인천","시흥","오봉남동#2 T/L","남동S/S 154kV 오봉남동#2T/L GIS 조작시험","남동S/S 154kV 오봉남동#2T/L GIS 조작시험","2023-11-01 14:00","2023-11-01 18:00","2023-11-17 09:00","2023-11-17 18:00","연속"]
[79,"인천","시흥","도림오봉#2 T/L","가공송전 협력회사 총액공사(추락방지장치 설치)","추락방지장치 설치 - 대상 : No.28~31","2023-11-04 07:00","2023-11-05 18:00","취소","취소","매일"]
[80,"인천","시흥","시화동시화#1 T/L","동시화S/S 154kV 시화동시화#1T/L 보호반 대체","동시화S/S 154kV 시화동시화#1T/L 보호반 대체","2023-11-27 09:00","2023-12-01 18:00","2023-11-27 09:00","2023-12-01 18:00","연속"]
[81,"인천","시흥","시화동시화#2 T/L","동시화S/S 154kV 시화동시화#2T/L 보호반 대체","동시화S/S 154kV 시화동시화#2T/L 보호반 대체","2023-11-20 09:00","2023-11-23 18:00","2023-11-20 09:00","2023-11-23 18:00","연속"]
[82,"인천","시흥","서안양소래 T/L","가공송전 협력회사 총액공사(애자련 교체)","성능저하 애자련 교체공사 - 대상 : 서안양-소래T/L No.75,75-1,76,86","2023-11-03 07:00","2023-11-06 18:00","2023-11-03 07:00","2023-11-06 18:00","매일"]
[83,"인천","시흥","서서울#2소래 T/L","가공송전 협력회사 총액공사(애자련 교체)","성능저하 애자련 교체공사 - 대상 : 서서울2-소래T/L No.75,75-1","2023-11-07 07:00","2023-11-08 18:00","2023-11-07 07:00","2023-11-08 18:00","매일"]
[84,"인천","시흥","온수소래 T/L","가공송전 협력회사 총액공사(추락방지장치 설치)","추락방지장치 설치공사 - 대상 : 서소T/L No.76~82","2023-11-04 07:00","2023-11-05 18:00","취소","취소","매일"]
[85,"인천","시흥","신시화S/S #60 BUS","345kV 신시화S/S 건설공사","345kV 신시화S/S 초기가압","2023-11-20 09:00","2023-11-21 18:00","2023-11-20 09:00","2023-11-21 18:00","연속"]
[86,"인천","시흥","신시화남정왕#2 T/L","345kV 신시화S/S 건설공사","345kV 신시화S/S 초기가압","2023-11-20 09:00","2023-11-21 18:00","2023-11-20 09:00","2023-11-21 18:00","연속"]
[87,"인천","시흥","신시화S/S #61 BUS","345kV 신시화S/S 건설공사","345kV 신시화S/S 초기가압","2023-11-20 09:00","2023-11-21 18:00","2023-11-20 09:00","2023-11-21 18:00","연속"]
[88,"인천","시흥","신시흥남동#2 T/L","가공송전 협력회사 총액공사(추락방지장치 설치)","추락방지장치 설치 - 대상 : 신시흥-남동 No.1~ 21","2023-11-04 07:00","2023-11-05 18:00","취소","취소","매일"]
[89,"인천","시흥","신시흥북시화#2 T/L","가공송전 협력회사 총액공사(소도체 이도조정)","소도체 이도조정 공사 - 대상 : 신시흥-시화#2T/L No.5~6, No.12~13","2023-11-11 07:00","2023-11-12 18:00","취소","취소","매일"]
[90,"인천","시흥","신시흥시화#2 T/L","가공송전 협력회사 총액공사(소도체 이도조정)","소도체 이도조정 공사 - 대상 : 신시흥-시화#2T/L No.5~6, No.12~13","2023-11-11 07:00","2023-11-12 18:00","취소","취소","매일"]
[91,"인천","직할","갈산도당#1 T/L","154kV 신부평-고강T/L 등 4개T/L 구형 SVL 교체공사","154kV 신부평-고강T/L 등 4개T/L 구형 SVL(피뢰기) 및 접지설비 교체공사","2023-11-06 09:00","2023-11-10 11:00","2023-11-06 09:00","2023-11-10 11:00","연속"]
[92,"인천","직할","계양김포#2 T/L","계양S/S 154kV 계양-김포#2T/L GIS SA 혼용공사","계양S/S 154kV 계양-김포#2T/L GIS SA 혼용공사","2023-11-20 09:30","2023-11-20 18:00","취소","취소","연속"]
[93,"인천","직할","임학계양#1 T/L","154kV 불로S/S 건설공사","신규 불로변전소 건설 - 154kV M.Tr 2 Bank - 154kV GIS 10CCT - 23kV EGIS 13CCT - 기타 부대공사","2023-11-13 09:00","2023-11-14 18:00","2023-11-13 09:00","2023-11-14 18:00","연속"]
[94,"인천","직할","갈산부흥#3 T/L","부흥S/S 갈산-부흥#3T/L GIS 하자점검","부흥S/S 갈산-부흥#3T/L GIS 하자점검","2023-11-17 10:00","2023-11-17 18:00","2023-11-17 10:00","2023-11-17 18:00","연속"]
[95,"인천","직할","부흥부개#1 T/L","154kV 신부평-고강T/L 등 4개T/L 구형 SVL 교체공사","154kV 신부평-고강T/L 등 4개T/L 구형 SVL(피뢰기) 및 접지설비 교체공사","2023-11-18 09:00","2023-11-19 18:00","2023-11-18 09:00","2023-11-19 18:00","연속"]
[96,"인천","직할","부흥부개#2 T/L","154kV 신부평-고강T/L 등 4개T/L 구형 SVL 교체공사","154kV 신부평-고강T/L 등 4개T/L 구형 SVL(피뢰기) 및 접지설비 교체공사","2023-11-04 09:00","2023-11-05 18:00","취소","취소","연속"]
[97,"인천","직할","신부평임학#2 T/L","임학S/S 신부평임학#2T/L 조작시험","임학S/S 신부평임학#2T/L 조작시험","2023-11-25 14:00","2023-11-25 18:00","2023-11-25 14:00","2023-11-25 18:00","연속"]
[98,"인천","직할","신부평임학#1 T/L","임학S/S 신부평임학#1T/L 조작시험","임학S/S 신부평임학#1T/L 조작시험","2023-11-25 09:30","2023-11-25 14:00","2023-11-25 09:30","2023-11-25 14:00","연속"]
[99,"경기북부","고양","양주고양#1 T/L","고양전력 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-11-20 13:00","2023-11-20 15:00","2023-11-20 13:00","2023-11-20 15:00","연속"]
[100,"경기북부","고양","양주고양#2 T/L","고양전력 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-11-21 07:00","2023-11-21 18:00","2023-11-21 07:00","2023-11-21 18:00","연속"]
[101,"경기북부","고양","신덕은금촌#1 T/L","고양전력 가공송전협력회사 총액공사","수평 추락방지장치 설치, 피뢰기 설치","2023-11-20 15:00","2023-11-20 18:00","2023-11-20 15:00","2023-11-20 18:00","연속"]
[102,"경기북부","고양","신덕은금촌#2 T/L","고양전력 가공송전협력회사 총액공사","수평 추락방지장치 설치, 피뢰기 설치","2023-11-20 07:00","2023-11-20 13:00","2023-11-20 07:00","2023-11-20 13:00","연속"]
[103,"경기북부","고양","양주금촌#1 T/L","고양전력 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-11-20 07:00","2023-11-20 13:00","2023-11-20 07:00","2023-11-20 13:00","연속"]
[104,"경기북부","고양","원흥상암 T/L","23-24년 지중송전설비 위탁정비공사","154kV 원흥#1,2C/T 피뢰기점검","2023-11-15 09:00","2023-11-15 18:00","2023-11-15 09:00","2023-11-15 18:00","연속"]
[105,"경기북부","고양","원흥S/S #1 BUS","원흥S/S 154kV GTX-A노선 SW증설공사","- 154kV T/L GIS(50kA, 1250A) × 2CCT 설치 - 154kV 고객선로 보호IED반 × 2면 설치 - 기타 부대공사 1식. 끝.","2023-11-09 09:00","2023-11-10 18:00","2023-11-09 09:00","2023-11-10 18:00","연속"]
[106,"경기북부","고양","신파주원흥#2 T/L","고양전력 가공송전협력회사 총액공사","피뢰기 설치","2023-11-20 07:00","2023-11-20 13:00","2023-11-20 07:00","2023-11-20 13:00","연속"]
[107,"경기북부","고양","신파주원흥#1 T/L","고양전력 가공송전협력회사 총액공사","수평 추락방지장치 설치, 피뢰기 설치","2023-11-20 13:00","2023-11-20 16:00","2023-11-20 13:00","2023-11-20 16:00","연속"]
[108,"경기북부","고양","신파주원흥#2 T/L","원흥S/S 154kV GTX-A노선 SW증설공사","- 154kV T/L GIS(50kA, 1250A) × 2CCT 설치 - 154kV 고객선로 보호IED반 × 2면 설치 - 기타 부대공사 1식. 끝.","2023-11-07 09:00","2023-11-10 18:00","2023-11-07 09:00","2023-11-10 18:00","연속"]
[109,"경기북부","고양","원흥수색#1 T/L","23-24년 지중송전설비 위탁정비공사","154kV 원흥#1,2C/T 피뢰기점검","2023-11-14 09:00","2023-11-14 18:00","2023-11-14 09:00","2023-11-14 18:00","연속"]
[110,"경기북부","고양","문산월롱#2 T/L","154kV 월롱S/S #1,2M.Tr 증설공사","월롱S/S #1,2M.Tr용 170kV GIS 개폐장치 설치 - 문산-월롱#2T/L 신규설치 M.Tr측 스페이서 교체 - 170kV GIS #1,2 BUS 측 조립시 인근Bay 가스 감압 - 무부하 가압선로","2023-11-21 09:00","2023-12-15 18:00","2023-11-21 09:00","2023-12-15 18:00","연속"]
[111,"경기북부","고양","월롱S/S #1 BUS","154kV 월롱S/S #1,2M.Tr 증설공사","154kV 월롱S/S #1,2M.Tr용 170kV GIS 설치 - 모선연장 및 #2M.Tr용 기설 모선 대체 - #1BUS CB, DS부 조립","2023-11-21 09:00","2023-12-01 18:00","2023-11-21 09:00","2023-12-01 18:00","연속"]
[112,"경기북부","고양","일산지도#2 T/L","22-23 변전협력회사 총액공사","피뢰기 보통점검","2023-11-17 09:00","2023-11-17 18:00","2023-11-17 09:00","2023-11-17 18:00","연속"]
[113,"경기북부","고양","일산지도#1 T/L","22-23 변전협력회사 총액공사","피뢰기 보통점검","2023-11-13 09:00","2023-11-13 18:00","2023-11-13 09:00","2023-11-13 18:00","연속"]
[114,"경기북부","구리","가평춘천HP T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[115,"경기북부","구리","가평청평HP#1 T/L","22-23 구리전력 변전협력 총액공사","#1,2M.Tr 장기사용 현수애자 교체 이격거리 확보","2023-11-06 09:00","2023-11-07 18:00","2023-11-06 09:00","2023-11-07 18:00","연속"]
[116,"경기북부","구리","가평화천HP T/L","22-23 구리전력 변전협력 총액공사","#1,2M.Tr 장기사용 현수애자 교체 이격거리 확보","2023-11-06 09:00","2023-11-07 18:00","2023-11-06 09:00","2023-11-07 18:00","연속"]
[117,"경기북부","구리","덕소마석#2 T/L","22~23년 구리전력 가공송전협력총액_추락방지장치,피뢰기","추락방지장치, 피뢰기 설치","2023-11-20 08:00","2023-11-23 18:00","2023-11-20 08:00","2023-11-23 18:00","연속"]
[118,"경기북부","구리","신장덕소#1 T/L","22~23년 구리전력 가공송전협력총액_추락방지장치","추락방지장치 설치","2023-11-10 08:00","2023-11-14 18:00","2023-11-10 08:00","2023-11-14 18:00","연속"]
[119,"경기북부","구리","미금S/S SEC CB 66670","미금S/S 154kV #62-67 모선보호반 교체공사","미금S/S 154kV #62-67 모선보호반 교체공사","2023-11-06 09:00","2023-11-10 18:00","2023-11-06 09:00","2023-11-10 18:00","연속"]
[120,"경기북부","구리","미금S/S SEC CB 61620","미금S/S 154kV #62-67 모선보호반 교체공사","미금S/S 154kV #62-67 모선보호반 교체공사","2023-11-06 09:00","2023-11-10 18:00","2023-11-06 09:00","2023-11-10 18:00","연속"]
[121,"경기북부","구리","미금광장 T/L","22~23년 구리전력 가공송전협력총액_추락방지장치,피뢰기","추락방지장치, 피뢰기 설치","2023-11-07 08:00","2023-11-09 18:00","2023-11-07 08:00","2023-11-09 18:00","연속"]
[122,"경기북부","구리","미금S/S #60 BUS","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-11-03 09:00","2023-11-03 14:00","2023-11-03 09:00","2023-11-03 14:00","연속"]
[123,"경기북부","구리","미금S/S #65 BUS","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-11-03 14:00","2023-11-03 18:00","2023-11-03 14:00","2023-11-03 18:00","연속"]
[124,"경기북부","구리","미금S/S CB 6300","미금S/S 154kV #62-67 모선보호반 교체공사","미금S/S 154kV #62-67 모선보호반 교체공사","2023-11-06 09:00","2023-11-10 18:00","2023-11-06 09:00","2023-11-10 18:00","연속"]
[125,"경기북부","구리","서종청평PP#1 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","추락방지시설 설치 : 서종S/S ~ 청평PP","2023-11-14 07:00","2023-11-24 18:00","2023-11-14 07:00","2023-11-24 18:00","연속"]
[126,"경기북부","구리","동서울서종#2 T/L","22~23년 구리전력 가공송전협력총액_추락방지장치","추락방지장치 설치","2023-11-13 08:00","2023-11-17 18:00","2023-11-13 08:00","2023-11-17 18:00","연속"]
[127,"경기북부","구리","서종청평PP#2 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","추락방지시설 설치 : 서종S/S ~ 청평PP","2023-11-27 07:00","2023-12-01 18:00","2023-11-27 07:00","2023-12-01 18:00","연속"]
[128,"경기북부","구리","신포천포천#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","ㅇ 대상 : 포천-운천T/L 병가선로 ㅇ 내용 : 지지애자교체","2023-11-08 07:00","2023-11-08 18:00","2023-11-08 07:00","2023-11-08 18:00","연속"]
[129,"경기북부","구리","운천철원#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 운천-철원T/L No.59~66","2023-11-20 12:00","2023-11-21 18:00","2023-11-20 12:00","2023-11-21 18:00","연속"]
[130,"경기북부","구리","운천철원#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 철탑추락방지시설 설치 - 대상 : 154kV 운천-철원T/L No.65,66","2023-11-20 07:00","2023-11-20 12:00","2023-11-20 07:00","2023-11-20 12:00","연속"]
[131,"경기북부","구리","장암진접#1 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-11-11 09:00","2023-11-11 18:00","2023-11-11 09:00","2023-11-11 18:00","연속"]
[132,"경기북부","구리","별내진접 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-11-18 09:00","2023-11-18 18:00","2023-11-18 09:00","2023-11-18 18:00","연속"]
[133,"경기북부","구리","가평청평HP#2 T/L","22-23년 구리전력지사 변전협력회사 총액공사","22-23년 구리전력지사 변전협력회사 총액공사","2023-11-09 09:00","2023-11-09 18:00","2023-11-09 09:00","2023-11-09 18:00","연속"]
[134,"경기북부","구리","포천운천#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","ㅇ 대상 : 포천-운천T/L ㅇ 내용 : 추락방지시설 설치 및 지지애자교체","2023-11-17 13:00","2023-11-17 18:00","2023-11-17 13:00","2023-11-17 18:00","연속"]
[135,"경기북부","구리","포천운천#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","ㅇ 대상 : 포천-운천T/L ㅇ 내용 : 추락방지시설 설치 및 지지애자교체","2023-11-14 07:00","2023-11-17 13:00","2023-11-14 07:00","2023-11-17 13:00","연속"]
[136,"경기북부","직할","금오상계#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","금오-상계#1T/L No.17,30 수평추락방지장치 설치","2023-11-02 07:00","2023-11-03 18:00","2023-11-02 07:00","2023-11-03 18:00","연속"]
[137,"경기북부","직할","녹양백석#2 T/L","고양전력 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-11-17 07:00","2023-11-17 18:00","2023-11-17 07:00","2023-11-17 18:00","연속"]
[138,"경기북부","직할","양주녹양#2 T/L","고양전력 가공송전협력회사 총액공사","추락방지장치(수평) 설치","2023-11-13 07:00","2023-11-24 18:00","2023-11-13 07:00","2023-11-24 18:00","연속"]
[139,"경기북부","직할","녹양백석#1 T/L","고양전력 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-11-09 07:00","2023-11-09 18:00","2023-11-09 07:00","2023-11-09 18:00","연속"]
[140,"경기북부","직할","양주녹양#1 T/L","고양전력 가공송전협력회사 총액공사","수평 추락방지장치 설치","2023-11-01 07:00","2023-11-10 18:00","2023-11-01 07:00","2023-11-10 18:00","연속"]
[141,"경기북부","직할","신포천덕계#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","ㅇ 대상 : 신포천-덕계T/L 항공장애표시구 설치 ㅇ 내용 : 백석-덕계T/L 병가선로","2023-11-06 07:00","2023-11-06 18:00","2023-11-06 07:00","2023-11-06 18:00","연속"]
[142,"경기북부","직할","백석덕계#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","ㅇ 대상 : 백석-덕계T/L ㅇ 내용 : 항공장애표시구 설치","2023-11-06 07:00","2023-11-06 18:00","2023-11-06 07:00","2023-11-06 18:00","연속"]
[143,"경기북부","직할","양주금촌#2 T/L","2023년 가공송전 순시점검 위탁공사","송전설비 정밀점검","2023-11-20 16:30","2023-11-24 18:00","2023-11-20 16:30","2023-11-24 18:00","연속"]
[144,"경기북부","직할","양주금촌#2 T/L","양주S/S HVDC #1,2C.Tr 무부하가압","HVDC #1,2C.Tr","2023-11-01 10:00","2023-11-02 10:00","취소","취소","연속"]
[145,"경기북부","직할","양주금촌#2 T/L","양주S/S HVDC #1,2C.Tr 실부하가압","HVDC #1,2C.Tr","2023-11-08 13:00","2023-11-08 15:00","취소","취소","연속"]
[146,"경기북부","직할","양주지축#2 T/L","양주S/S HVDC #1,2C.Tr 실부하가압","HVDC #1,2C.Tr","2023-11-08 13:00","2023-11-08 15:00","취소","취소","연속"]
[147,"경기북부","직할","양주지축#1 T/L","고양전력 가공송전협력회사 총액공사","추락방지장치(수평)설치","2023-11-10 07:00","2023-11-10 12:00","2023-11-10 07:00","2023-11-10 12:00","연속"]
[148,"경기북부","직할","양주지축#2 T/L","양주S/S HVDC #1,2C.Tr 무부하가압","HVDC #1,2C.Tr","2023-11-01 10:00","2023-11-02 10:00","2023-11-02 10:00","2023-11-03 10:00","연속"]
[149,"경기북부","직할","양주지축#2 T/L","고양전력 가공송전협력회사 총액공사","추락방지장치(수평)설치","2023-11-10 12:00","2023-11-10 18:00","2023-11-10 12:00","2023-11-10 18:00","연속"]
[150,"경기북부","직할","양주은평#1 T/L","고양전력 가공송전협력회사 총액공사","추락방지장치(수평)설치","2023-11-10 12:00","2023-11-10 18:00","2023-11-10 12:00","2023-11-10 18:00","연속"]
[151,"경기북부","직할","양주은평#2 T/L","고양전력 가공송전협력회사 총액공사","추락방지장치(수평)설치","2023-11-10 07:00","2023-11-10 12:00","2023-11-10 07:00","2023-11-10 12:00","연속"]
[152,"경기북부","직할","옥정동두천#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","ㅇ 대상 : 옥정-동두천T/L ㅇ 내용 : 추락방지시설 설치 및 지지애자교체","2023-11-07 07:00","2023-11-07 14:00","2023-11-07 07:00","2023-11-07 14:00","연속"]
[153,"경기북부","직할","옥정동두천#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","ㅇ 대상 : 옥정-동두천T/L ㅇ 내용 : 추락방지시설 설치","2023-11-07 14:00","2023-11-07 18:00","2023-11-07 14:00","2023-11-07 18:00","연속"]
[154,"경기북부","직할","용현장암#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","용현-장암T/L No.17,30,31~35 수평추락방지시설설치","2023-11-02 07:00","2023-11-03 18:00","2023-11-02 07:00","2023-11-03 18:00","연속"]
[155,"경기북부","직할","운천전곡#2 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","ㅇ 대상 : 운천-전곡T/L ㅇ 내용 : 추락방지시설 설치","2023-11-20 07:00","2023-11-22 18:00","2023-11-20 07:00","2023-11-22 18:00","연속"]
[156,"경기북부","직할","운천전곡#1 T/L","2022~2023년 경기북부 직할 가공송전 협력회사 총액공사","ㅇ 대상 : 운천-전곡T/L ㅇ 내용 : 추락방지시설 설치 및 지지애자교체","2023-11-08 07:00","2023-11-13 18:00","2023-11-08 07:00","2023-11-13 18:00","연속"]
[157,"경기","군포","화성남양#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 13기","2023-11-04 07:00","2023-11-04 18:00","2023-11-04 07:00","2023-11-04 18:00","연속"]
[158,"경기","군포","화성남양#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 13기","2023-11-05 07:00","2023-11-05 18:00","2023-11-05 07:00","2023-11-05 18:00","연속"]
[159,"경기","군포","마도사강#1 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-11-01 09:00","2023-11-02 16:00","취소","취소","연속"]
[160,"경기","군포","마도사강#2 T/L","154kV 화성-장덕T/L 등 2개 선로 OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-11-06 07:00","2023-11-18 18:00","취소","취소","연속"]
[161,"경기","군포","목내성곡#2 T/L","목내,성곡S/S 목내-성곡#2T/L 보호반대체","목내,성곡S/S 목내-성곡#2T/L 보호반대체","2023-11-06 09:00","2023-11-09 18:00","2023-11-06 09:00","2023-11-09 18:00","연속"]
[162,"경기","군포","산본안양#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 10기","2023-11-20 07:00","2023-11-20 18:00","2023-11-20 07:00","2023-11-20 18:00","연속"]
[163,"경기","군포","산본안양#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 10기","2023-11-21 07:00","2023-11-21 18:00","2023-11-21 07:00","2023-11-21 18:00","연속"]
[164,"경기","군포","서서울#2서안양 T/L","가공송전 협력회사 총액공사(154kV 서안양T/L 추락방지)","송전철탑 추락방지장치 수평 설치 - 대상 : No.48~53, 서안양분기 No.1","2023-11-18 07:00","2023-11-19 18:00","2023-11-18 07:00","2023-11-19 18:00","매일"]
[165,"경기","군포","장덕마도 T/L","154kV 화성-장덕T/L 등 2개 선로 OPGW 증설공사","* OPGW 증설(OP-S-L24→OP-S-L48) 17.991km * 광케이블 증설(FOFC-24C→FOFC-48C) 0.638km * 항공장애표시구 교체 71개 * 광코어 접속, 광케이블 최종시험 및 기타 부대공사 1식","2023-11-06 07:00","2023-11-08 18:00","취소","취소","연속"]
[166,"경기","군포","안산안산복합#2 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-11-20 09:00","2023-11-20 18:00","2023-11-20 09:00","2023-11-20 18:00","연속"]
[167,"경기","군포","안산안산복합#3 T/L","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023년 군포전력지사 하반기 170kV GIS 보통점검","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[168,"경기","동부","가남S/S CB 6100","23년 동부 변전정비회사 총액공사","가남:모선보호반 대체(~23)","2023-11-20 09:30","2023-11-23 18:00","2023-11-20 09:30","2023-11-23 18:00","연속"]
[169,"경기","동부","곤지암이천#1 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사, 1~53호","2023-11-01 08:00","2023-11-07 18:00","2023-11-01 08:00","2023-11-07 18:00","연속"]
[170,"경기","동부","곤지암율현#2 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사(1~28호 : 곤지암-이천 4회선 병가구간)","2023-11-09 08:00","2023-11-11 18:00","2023-11-09 08:00","2023-11-11 18:00","연속"]
[171,"경기","동부","곤지암이천#2 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사, 1~53호","2023-11-13 08:00","2023-11-19 18:00","2023-11-13 08:00","2023-11-19 18:00","연속"]
[172,"경기","동부","곤지암이천#2 T/L","22-23 동부전력지사 송전협력회사 총액공사","수평 추락방지장치 설치공사, 1~53호","2023-11-08 08:00","2023-11-08 18:00","2023-11-08 08:00","2023-11-08 18:00","연속"]
[173,"경기","동부","성현산성#1 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차) 산성#1,2T/L 대체","2023-11-01 09:00","2023-11-24 18:00","2023-11-01 09:00","2023-11-24 18:00","연속"]
[174,"경기","동부","성현산성#2 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차) 산성#1,2T/L 대체","2023-11-01 09:00","2023-11-24 18:00","2023-11-01 09:00","2023-11-24 18:00","연속"]
[175,"경기","동부","성현분당#1 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 안전이격) - 즉시가압 가능","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[176,"경기","동부","초월성현#2 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 안전이격) - 즉시가압 가능","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[177,"경기","동부","성현산성#3 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 무부하) - 즉시가압 가능","2023-11-04 09:00","2023-11-04 18:00","2023-11-04 09:00","2023-11-04 18:00","연속"]
[178,"경기","동부","성현분당#1 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 안전이격) - 즉시가압 가능","2023-11-06 09:00","2023-11-06 18:00","2023-11-06 09:00","2023-11-06 18:00","연속"]
[179,"경기","동부","초월성현#2 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 안전이격) - 즉시가압 가능","2023-11-06 09:00","2023-11-06 18:00","2023-11-06 09:00","2023-11-06 18:00","연속"]
[180,"경기","동부","성현분당#1 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 안전이격) - 즉시가압 가능","2023-11-06 09:00","2023-11-06 18:00","취소","취소","연속"]
[181,"경기","동부","초월성현#2 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 안전이격) - 즉시가압 가능","2023-11-06 09:00","2023-11-06 18:00","취소","취소","연속"]
[182,"경기","동부","성현산성#3 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 무부하) - 즉시가압 가능","2023-11-10 14:00","2023-11-11 14:00","2023-11-10 14:00","2023-11-11 14:00","연속"]
[183,"경기","동부","성현분당#1 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 안전이격) - 즉시가압 가능","2023-11-13 09:00","2023-11-14 18:00","2023-11-13 09:00","2023-11-14 18:00","연속"]
[184,"경기","동부","초월성현#2 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 안전이격) - 즉시가압 가능","2023-11-13 09:00","2023-11-14 18:00","2023-11-13 09:00","2023-11-14 18:00","연속"]
[185,"경기","동부","성현산성#3 T/L","성현S/S 장기사용 154kV GIS 교체공사(5차)","성현S/S 장기사용 154kV GIS 교체공사(5차, 무부하) - 즉시가압 가능","2023-11-23 14:00","2023-11-24 14:00","2023-11-23 14:00","2023-11-24 14:00","연속"]
[186,"경기","동부","오천용인#1 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.1 ~ 58 (2회선 철탑 47기)","2023-11-20 07:00","2023-11-24 18:00","2023-11-20 07:00","2023-11-24 18:00","연속"]
[187,"경기","동부","오천용인#2 T/L","345kV 신용인-동서울 등 16개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치 No.1 ~ 58 (2회선 철탑 47기)","2023-11-27 07:00","2023-11-28 18:00","2023-11-27 07:00","2023-11-28 18:00","연속"]
[188,"경기","동부","오포모현#1 T/L","2023년 가공송전 순시점검 위탁공사(성남)","8-9호 전력선 정밀점검","2023-11-27 09:00","2023-11-27 18:00","2023-11-27 09:00","2023-11-27 18:00","연속"]
[189,"경기","동부","분당오포#1 T/L","23년 동부전력 변전협력 총액공사 ","분당-오포#1TL 보호반대체","2023-11-28 09:00","2023-11-30 18:00","취소","취소","연속"]
[190,"경기","성남","기흥신갈#1 T/L","2023~2024년 지중송전설비 위탁정비공사(경기본부 성남전력지사)","154kV기흥신갈#1T/L C/T 및 LA점검","2023-11-20 08:00","2023-11-20 17:00","2023-11-20 08:00","2023-11-20 17:00","연속"]
[191,"경기","성남","기흥신갈#2 T/L","2023~2024년 지중송전설비 위탁정비공사(경기본부 성남전력지사)","154kV기흥신갈#2T/L C/T 및 LA점검","2023-11-22 08:00","2023-11-22 17:00","2023-11-22 08:00","2023-11-22 17:00","연속"]
[192,"경기","성남","서안성남사#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(6회선 구간)","2023-11-12 08:00","2023-11-12 18:00","취소","취소","연속"]
[193,"경기","성남","덕성남사#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(6회선 구간)","2023-11-12 08:00","2023-11-12 18:00","취소","취소","연속"]
[194,"경기","성남","남사동탄#1 T/L","오산-평택T/L 등 13개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치","2023-11-20 07:00","2023-11-21 18:00","취소","취소","연속"]
[195,"경기","성남","진위동탄#1 T/L","오산-평택T/L 등 13개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치","2023-11-13 07:00","2023-11-14 18:00","취소","취소","연속"]
[196,"경기","성남","진위동탄#2 T/L","오산-평택T/L 등 13개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치","2023-11-15 07:00","2023-11-16 18:00","취소","취소","연속"]
[197,"경기","성남","남사동탄#2 T/L","오산-평택T/L 등 13개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치","2023-11-22 07:00","2023-11-23 18:00","취소","취소","연속"]
[198,"경기","성남","서판교중원#1 T/L","23년 성남전력지사 변전협력회사 총액공사","-line사/활 감시 불량 보수","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[199,"경기","성남","신봉이의#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","154kV 신봉-이의T/L 수직수평추락방지장치 설치","2023-11-01 07:00","2023-11-02 18:00","2023-11-01 07:00","2023-11-02 18:00","연속"]
[200,"경기","성남","신봉이의#2 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","154kV 신봉-이의T/L 수직수평추락방지장치 설치","2023-11-20 07:00","2023-11-24 18:00","2023-11-20 07:00","2023-11-24 18:00","연속"]
[201,"경기","성남","신봉이의#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","154kV 신봉-이의T/L 수직수평추락방지장치 설치","2023-11-27 07:00","2023-11-30 18:00","2023-11-27 07:00","2023-11-30 18:00","연속"]
[202,"경기","성남","신수원북동탄#1 T/L","23년 성남전력지사 변전협력회사 총액공사","- GIS 보통점검","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[203,"경기","성남","신용인용인#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간)","2023-11-19 08:00","2023-11-19 18:00","2023-11-19 08:00","2023-11-19 18:00","연속"]
[204,"경기","성남","신용인용인#2 T/L","154kV 신용인-동백-마북T/L 광선로 증설공사","OPGW 교체 2.948km, 항공구 교체 6개, 기타 부대공사 1식 - 신용인-동백T/L No.1 병가철탑 작업 관련으로 휴전 필요","2023-11-02 07:00","2023-11-05 18:00","2023-11-02 07:00","2023-11-05 18:00","연속"]
[205,"경기","성남","신용인동백#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간) 및 성능저하 애자교체공사","2023-11-30 08:00","2023-11-30 12:00","취소","취소","연속"]
[206,"경기","성남","신용인S/S #1 EM.Tr CB","23년 성남전력 154, 345kV 주변압기 보통점검공사","-변압기 보통점검","2023-11-13 09:00","2023-11-14 18:00","2023-11-13 09:00","2023-11-14 18:00","연속"]
[207,"경기","성남","신용인동백#1 T/L","154kV 신용인-동백-마북T/L 광선로 증설공사","OPGW 교체 2.948km, 항공구 교체 6개, 기타 부대공사 1식","2023-11-02 07:00","2023-11-05 18:00","취소","취소","연속"]
[208,"경기","성남","신용인용인#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간) 및 성능저하 애자교체공사","2023-11-29 08:00","2023-11-30 18:00","취소","취소","연속"]
[209,"경기","성남","신용인기흥#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간) 및 성능저하 애자교체공사","2023-11-28 08:00","2023-11-29 18:00","2023-11-28 08:00","2023-11-29 18:00","연속"]
[210,"경기","성남","용인덕성#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간) 성능저하 애자교체공사","2023-11-19 08:00","2023-11-19 18:00","2023-11-19 08:00","2023-11-19 18:00","연속"]
[211,"경기","성남","용인덕성#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(4회선 구간)","2023-11-30 12:00","2023-11-30 18:00","2023-11-30 12:00","2023-11-30 18:00","연속"]
[212,"경기","직할","화성발안#1 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 154kV 화성-발안#1T/L GIS 하자점검 발안S/S 154kV 화성-발안#1T/L GIS 보통점검","2023-11-18 09:00","2023-11-18 18:00","2023-11-18 09:00","2023-11-18 18:00","연속"]
[213,"경기","직할","화성발안#2 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 154kV 화성-발안#2T/L GIS 하자점검 발안S/S 154kV 화성-발안#2T/L GIS 보통점검","2023-11-19 09:00","2023-11-19 18:00","2023-11-19 09:00","2023-11-19 18:00","연속"]
[214,"경기","직할","화성수촌#1 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 154kV 화성-수촌#1T/L GIS 하자점검","2023-11-26 09:00","2023-11-26 14:00","2023-11-26 09:00","2023-11-26 14:00","연속"]
[215,"경기","직할","화성수촌#2 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 154kV 화성-수촌#2T/L GIS 하자점검","2023-11-26 14:00","2023-11-26 18:00","2023-11-26 14:00","2023-11-26 18:00","연속"]
[216,"경기","직할","화성장덕 T/L","OPGW 증설공사","OPGW 증설공사","2023-11-22 09:00","2023-11-24 18:00","취소","취소","연속"]
[217,"경기","직할","화성장덕 T/L","2022-23년 경기본부 직할 변전협력회사 총액공사","화성S/S 154kV 화성-장덕T/L 세니온제 IED 성능개선(유사고장)","2023-11-25 09:00","2023-11-26 18:00","2023-11-25 09:00","2023-11-26 18:00","연속"]
[218,"경기","직할","조암구문천#1 T/L","조암,구문천S/S 조암-구문천#1T/L 보호반대체 ","조암,구문천S/S 조암-구문천#1T/L 보호반대체 ","2023-11-11 09:00","2023-11-13 18:00","취소","취소","연속"]
[219,"경기","직할","발안구문천#1 T/L","154kV 신성남-신봉 등 8개T/L 추락방지장치 설치공사","154kV 조암-구문천T/L 수직수평추락방지장치 설치(병가구간)","2023-11-12 09:00","2023-11-12 18:00","2023-11-12 09:00","2023-11-12 18:00","연속"]
[220,"경기","평택","평택추팔#2 T/L","가공송전 긴선장비 개발 관련 시연회 ","장비사용 시연 위한 긴선 해체 및 재설치 ","2023-11-01 09:00","2023-11-03 18:00","2023-11-01 09:00","2023-11-03 18:00","연속"]
[221,"경기","평택","둔포추팔#1 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","둔포-추팔#1T/L 추락방지시설 설치","2023-11-18 09:00","2023-11-19 18:00","2023-11-18 09:00","2023-11-19 18:00","연속"]
[222,"경기","평택","둔포추팔#1 T/L","2022-23 평택전력지사 가공송전 협력회사 총액공사","둔포-추팔#1T/L 추락방지시설 설치","2023-11-18 09:00","2023-11-19 18:00","취소","취소","연속"]
[223,"경기","평택","원정만호#2 T/L","23년 평택전력 변전협력회사 총액공사","원정-만호#2T/L GIS 보통점검","2023-11-13 09:00","2023-11-13 18:00","취소","취소","연속"]
[224,"경기","평택","만호청북#1 T/L","154kV 만호청북T/L 불량스페이서 정비(구간 No.9~10)","가154kV 만호청북T/L 불량스페이서 1개 정비(구간 No.9~10)","2023-11-07 09:00","2023-11-07 18:00","취소","취소","연속"]
[225,"경기","평택","서운안성#2 T/L","세종-포천간 도로개설 관련 지장이설공사(154kV 2T/L)","철탑 5기 신설, 8기 철거","2023-11-15 07:00","2023-11-18 18:00","2023-11-15 07:00","2023-11-18 18:00","연속"]
[226,"경기","평택","소사벌안성 T/L","23년 평택전력 변전협력회사 총액공사","소사벌S/S 소사벌-안성T/L 보호배전반 대체","2023-11-25 09:00","2023-11-27 18:00","취소","취소","연속"]
[227,"경기","평택","서안성안성#1 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(수평) 및 애자교체 공사 [4회선 병가 구간]","2023-11-04 08:00","2023-11-04 18:00","취소","취소","연속"]
[228,"경기","평택","서안성안성#2 T/L","22-23년 경기직할 가공송전 협력회사 총액공사","철탑추락방지장치 설치공사(수평) 및 애자교체 공사 [4회선 병가 구간]","2023-11-18 08:00","2023-11-18 18:00","취소","취소","연속"]
[229,"경기","평택","포승청북 T/L","23년 평택전력 변전협력회사 총액공사","포승S/S 포승-청북T/L GIS 보통점검 및 PT&LA 보통점검","2023-11-06 09:00","2023-11-06 18:00","취소","취소","연속"]
[230,"강원","강릉","북강릉주문진#1 T/L","2022~2023년 가공송전협력회사 총액공사","○ 관형지지물용 가이드 레일 설치(No.2)","2023-11-08 07:30","2023-11-08 18:00","2023-11-08 07:30","2023-11-08 18:00","연속"]
[231,"강원","강릉","북강릉주문진#2 T/L","2022~2023년 가공송전협력회사 총액공사","○ 관형지지물용 가이드 레일 설치(No.1, 2)","2023-11-06 07:30","2023-11-07 18:00","2023-11-06 07:30","2023-11-07 18:00","매일"]
[232,"강원","강릉","강릉북강릉#1 T/L","2022~2023년 가공송전협력회사 총액공사","○ 관형지지물용 가이드 레일 설치(No.2, 45)","2023-11-06 07:30","2023-11-07 18:00","2023-11-06 07:30","2023-11-07 18:00","매일"]
[233,"강원","강릉","강릉북강릉#2 T/L","2022~2023년 가공송전협력회사 총액공사","○ 관형지지물용 가이드 레일 설치(No.2)","2023-11-08 07:30","2023-11-08 18:00","2023-11-08 07:30","2023-11-08 18:00","연속"]
[234,"강원","강릉","신양양양양#1 T/L","170kV GIS 매커니즘 점검","170kV GIS 매커니즘 점검","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[235,"강원","강릉","신제천주진#2 T/L","345kV 동해 등 5개T/L 추락방지 설치공사","○ 추락방지장치 수평구명줄 설치 115기","2023-11-20 07:00","2023-11-29 18:00","2023-11-20 07:00","2023-11-29 18:00","매일"]
[236,"강원","강릉","신제천주진#1 T/L","345kV 동해 등 5개T/L 추락방지 설치공사","○ 추락방지장치 수평구명줄 설치 115기","2023-11-10 07:00","2023-11-19 18:00","2023-11-10 07:00","2023-11-19 18:00","매일"]
[237,"강원","강릉","주진평창#1 T/L","2023년 강릉전력 변전협력회사 총액공사","170kV GIS,LA 보통점검","2023-11-08 10:00","2023-11-08 18:00","2023-11-08 10:00","2023-11-08 18:00","연속"]
[238,"강원","강릉","주진평창#2 T/L","2023년 강릉전력 변전협력회사 총액공사","차단기 조작시험","2023-11-07 10:00","2023-11-07 18:00","2023-11-07 10:00","2023-11-07 18:00","연속"]
[239,"강원","동해","도계태백 T/L","22~23 동해전력지사 변전정비팀 총액공사","LA 대체","2023-11-01 09:30","2023-11-01 18:00","2023-11-01 09:30","2023-11-01 18:00","연속"]
[240,"강원","동해","이원도계 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 태원T/L 정밀점검","2023-11-13 08:00","2023-11-17 18:00","2023-11-13 08:00","2023-11-17 18:00","연속"]
[241,"강원","직할","상남인제#2 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 상제 T/L 수목벌채","2023-11-06 09:00","2023-11-07 18:00","2023-11-06 09:00","2023-11-07 18:00","매일"]
[242,"강원","직할","상남인제#1 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 상제 T/L 수목벌채","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[243,"강원","강릉","신양양S/S #3 M.Tr","2023년 강릉전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2023-11-10 10:00","2023-11-10 18:00","취소","취소","연속"]
[244,"강원","직할","철원화천#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사 ","ㅇ 철탑추락방지시설 설치 병가선로 - 대상 : 154kV 운천-철원T/L No.65,66 - 병가선로 : 154kV 철원-화천T/L No.2,3","2023-11-20 07:00","2023-11-20 12:00","2023-11-20 07:00","2023-11-20 12:00","연속"]
[245,"강원","직할","철원화천#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사 ","ㅇ 철탑추락방지시설 설치 병가선로 - 대상 : 154kV 운천-철원T/L No.65,66 - 병가선로 : 154kV 철원-화천T/L No.2,3","2023-11-20 12:00","2023-11-20 18:00","2023-11-20 12:00","2023-11-20 18:00","연속"]
[246,"강원","강릉","평창올림픽 T/L","2023년 변전협력회사 총액공사","올림픽S/S 170kV GIS, LA 보통점검","2023-11-22 10:00","2023-11-22 18:00","2023-11-22 10:00","2023-11-22 18:00","연속"]
[247,"강원","강릉","횡계올림픽 T/L","2023년 변전협력회사 총액공사","올림픽S/S 170kV GIS, LA 보통점검","2023-11-23 10:00","2023-11-23 18:00","2023-11-23 10:00","2023-11-23 18:00","연속"]
[248,"강원","동해","이원태백 T/L","2023년 가공송전선로 순시점검 위탁공사","154kV 태원T/L 정밀점검","2023-11-20 08:00","2023-11-24 18:00","2023-11-20 08:00","2023-11-24 18:00","연속"]
[249,"강원","원주","남원주원주#1 T/L","'22~23년 원주전력지사 가공송전협력회사 총액공사","- 수평형 추락방지장치 설치","2023-11-11 07:00","2023-11-12 18:00","2023-11-11 07:00","2023-11-12 18:00","매일"]
[250,"강원","원주","남원주원주#1 T/L","'22~23년 원주전력지사 가공송전협력회사 총액공사","- 수평형 추락방지장치 설치","2023-11-04 07:00","2023-11-05 18:00","2023-11-04 07:00","2023-11-05 18:00","매일"]
[251,"강원","원주","홍천상남#2 T/L","345kV 동해 등 5개T/L 추락방지 설치공사","○ 추락방지장치 수평구명줄 설치 147기","2023-11-01 07:00","2023-11-09 18:00","2023-11-01 07:00","2023-11-09 18:00","연속"]
[252,"강원","원주","홍천소양강HP T/L","신재생 발전설비 송전선로 정기검사","신재생 발전설비 송전선로 정기검사","2023-11-08 00:08","2023-11-08 18:00","2023-11-08 00:08","2023-11-08 18:00","연속"]
[253,"강원","직할","홍천남춘천 T/L","22~23년 강원본부 직할 변전협력회사 총액공사","남춘천S/S 154kV 홍천-남춘천T/L 보호배전반 대체","2023-11-20 09:00","2023-11-23 18:00","2023-11-20 09:00","2023-11-23 18:00","연속"]
[254,"강원","직할","남춘천춘천열병합#2 T/L","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","2023년 강원본부 직할 154kV GIS, GCB 정밀점검 공사 - 옆 베이(홍천-남춘천 T/L) 작업시 이격거리 확보","2023-11-20 09:00","2023-11-21 18:00","2023-11-20 09:00","2023-11-21 18:00","연속"]
[255,"강원","직할","남춘천춘천 T/L","22~23년 강원본부 직할 변전협력회사 총액공사","- 남춘천S/S 154kV 남춘천-춘천T/L 보호배전반 대체 - 춘천S/S 154kV 남춘천-춘천T/L 보호배전반 대체","2023-11-13 09:00","2023-11-17 18:00","2023-11-13 09:00","2023-11-17 18:00","연속"]
[256,"강원","직할","춘천북춘천#1 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","추락방지장치 설치","2023-11-20 07:30","2023-11-26 18:00","2023-11-20 07:30","2023-11-26 18:00","매일"]
[257,"강원","직할","북춘천S/S #1 BUS","22~23년 강원본부 직할 변전협력회사 총액공사","154kV #1,2BUS PT 보통점검","2023-11-08 10:00","2023-11-08 14:00","2023-11-08 10:00","2023-11-08 14:00","연속"]
[258,"강원","직할","북춘천S/S CB 6100","22~23년 강원본부 직할 변전협력회사 총액공사","북춘천S/S 154kV 모선보호반 대체","2023-11-27 10:00","2023-12-01 18:00","2023-11-27 10:00","2023-12-01 18:00","연속"]
[259,"강원","직할","북춘천S/S #2 BUS","22~23년 강원본부 직할 변전협력회사 총액공사","154kV #1,2BUS PT 보통점검","2023-11-08 14:00","2023-11-08 18:00","2023-11-08 14:00","2023-11-08 18:00","연속"]
[260,"강원","직할","서홍천춘천열병합 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","추락방지장치 설치","2023-11-13 08:00","2023-11-18 18:00","2023-11-13 08:00","2023-11-18 18:00","매일"]
[261,"강원","직할","서홍천청평PP T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","추락방지장치 설치","2023-11-06 08:00","2023-11-11 18:00","2023-11-06 08:00","2023-11-11 18:00","연속"]
[262,"강원","직할","인제S/S #2 BUS","22~23년 강원본부 직할 변전협력회사 총액공사","- 인제S/S 154kV #2BUS PT GIS 보통점검 - 인제S/S 154kV #2BUS PT 보통점검","2023-11-08 13:00","2023-11-08 16:00","2023-11-08 13:00","2023-11-08 16:00","연속"]
[263,"강원","직할","인제S/S #1 BUS","22~23년 강원본부 직할 변전협력회사 총액공사","- 인제S/S 154kV #1BUS PT GIS 보통점검 - 인제S/S 154kV #1BUS PT 보통점검","2023-11-08 10:00","2023-11-08 13:00","2023-11-08 10:00","2023-11-08 13:00","연속"]
[264,"강원","직할","춘천소양강HP T/L","신재생 발전설비 송전선로 정기검사","신재생 발전설비 송전선로 정기검사","2023-11-06 09:00","2023-11-07 18:00","2023-11-06 09:00","2023-11-07 18:00","연속"]
[265,"강원","직할","춘천열병합 #1 BUS","22~23년 강원본부 직할 변전협력회사 총액공사","- 춘천열병합 154kV #1BUS PT GIS 보통점검 - 춘천열병합 154kV #1BUS PT 보통점검","2023-11-03 10:00","2023-11-03 14:00","2023-11-03 10:00","2023-11-03 14:00","연속"]
[266,"강원","직할","춘천열병합 #2 BUS","22~23년 강원본부 직할 변전협력회사 총액공사","- 춘천열병합 154kV #2BUS PT GIS 보통점검 - 춘천열병합 154kV #2BUS PT 보통점검","2023-11-03 14:00","2023-11-03 18:00","2023-11-03 14:00","2023-11-03 18:00","연속"]
[267,"강원","직할","청평PP춘천열병합 T/L","2022~2023년 강원본부 직할 가공송전협력회사 총액공사","추락방지장치 설치","2023-11-27 08:00","2023-12-06 18:00","2023-11-27 08:00","2023-12-06 18:00","연속"]
[268,"강원","직할","화천H/P #4 M.Tr 2차 CB","22~23년 강원본부 직할 변전협력회사 총액공사","- 화천HP 154kV #4M.Tr 2차 GCB 보통점검 - 화천HP 154kV #4M.Tr 2차 DS A, B 보통점검","2023-11-01 10:00","2023-11-01 18:00","2023-11-01 10:00","2023-11-01 18:00","연속"]
[269,"강원","직할","화천H/P #2 BUS","22~23년 강원본부 직할 변전협력회사 총액공사","- 화천HP 154kV #2 BUS CVT 보통점검","2023-11-02 14:00","2023-11-02 17:00","2023-11-02 14:00","2023-11-02 17:00","연속"]
[270,"강원","직할","화천H/P #1 BUS","22~23년 강원본부 직할 변전협력회사 총액공사","- 화천HP 154kV #1 BUS CVT 보통점검","2023-11-02 10:00","2023-11-02 14:00","2023-11-02 10:00","2023-11-02 14:00","연속"]
[271,"강원","태백","제천영월#2 T/L","154kV 태백T/L 선종교체공사","전선교체 : 영월에코윈드-영월#2T/L 37.22c-km(104기) 휴전사유 : 인출선로 작업시 작업자 안전이격거리 확보","2023-11-01 09:00","2023-11-03 18:00","2023-11-01 09:00","2023-11-03 18:00","연속"]
[272,"강원","태백","영월S/S #1 BUS","154kV 태백T/L 선종교체공사","전선교체 : 영월에코윈드-영월#2T/L No.1~77(37.2c-km)","2023-11-30 09:00","2023-11-30 18:00","2023-11-30 09:00","2023-11-30 18:00","연속"]
[273,"강원","태백","영월영월에코윈드#1 T/L","2023년 태백전력지사 변전협력회사 총액공사","영월에코윈드S/Y 154kV 영월에코윈드-영월#1T/L GIS 초기점검","2023-11-21 10:00","2023-11-21 18:00","2023-11-21 10:00","2023-11-21 18:00","연속"]
[274,"강원","태백","고한영월에코윈드 T/L","2023년 태백전력지사 변전협력회사 총액공사","영월에코윈드S/Y 154kV 고한-영월에코윈드T/L GIS 초기점검","2023-11-20 10:00","2023-11-20 18:00","2023-11-20 10:00","2023-11-20 18:00","연속"]
[275,"강원","태백","태백S/S #65 BUS","154kV 태백S/S #2M.Tr 증설공사","- 신설 #2M.Tr 최초 가압","2023-11-21 14:00","2023-11-22 14:00","2023-11-21 14:00","2023-11-22 14:00","연속"]
[276,"강원","태백","태백S/S #60 BUS","154kV 태백S/S #2M.Tr 증설공사","- 신설 #2M.Tr 최초 가압","2023-11-20 14:00","2023-11-21 14:00","2023-11-20 14:00","2023-11-21 14:00","연속"]
[277,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사","- 신설 #2M.Tr 최초 가압","2023-11-20 14:00","2023-11-22 14:00","2023-11-20 14:00","2023-11-22 14:00","연속"]
[278,"강원","태백","태백삼척GP#2 T/L","2023년 가공송전 순시점검 위탁공사","송전선로 선하지 지장수목 벌채","2023-11-19 08:00","2023-11-19 16:00","2023-11-19 08:00","2023-11-19 16:00","연속"]
[279,"강원","태백","태백영월에코윈드 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치","2023-11-06 10:00","2023-11-09 18:00","2023-11-06 10:00","2023-11-09 18:00","연속"]
[280,"충북","직할","진천광혜원#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","서운삼죽 병가선로 휴전 및 애자교체, 아킹혼 설지 No.38 전력선 애자교체, no. 45, 50 지지애자교체 (폴리머), No.38 아킹혼 설치","2023-11-20 07:30","2023-11-21 18:00","2023-11-20 07:30","2023-11-21 18:00","매일"]
[281,"충북","직할","진천광혜원#1 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","서운삼죽 병가선로 휴전 및 애자교체, 아킹혼 설지 No.38 전력선 애자교체, no. 45, 50 지지애자교체 (폴리머), No.38 아킹혼 설치","2023-11-22 07:30","2023-11-23 18:00","2023-11-22 07:30","2023-11-23 18:00","매일"]
[282,"충북","직할","서운광혜원 T/L","2022년 가공 송전선로 추락방지장치 설치공사","서운광혜원TL 추락방지장치 설치","2023-11-27 07:30","2023-11-30 18:00","2023-11-27 07:30","2023-11-30 18:00","매일"]
[283,"충북","직할","신진천진천#2 T/L","154kV 신진천-오창T/L OPGW 증설공사","154kV 신진천-오창#2T/L No.2(30)~3호(신진천-진천 병가)","2023-11-19 07:00","2023-11-19 18:00","취소","취소","연속"]
[284,"충북","직할","신진천진천#1 T/L","154kV 신진천-오창T/L OPGW 증설공사","신진천-진천#1T/L No.29~30(2호) OPGW 교체(신진천-오창T/L 병가)","2023-11-18 07:00","2023-11-18 18:00","취소","취소","연속"]
[285,"충북","직할","신진천오창#2 T/L","154kV 신진천-오창T/L OPGW 증설공사","신진천-진천 No.29~30(2)호(병가), 신진천-오창 No.2~3호 OPGW 교체","2023-11-18 07:00","2023-11-19 18:00","취소","취소","연속"]
[286,"충북","직할","신진천S/S SEC CB 66670","22-23년 충북직할 변전협력회사 총액공사","신진천S/S 154kV #66-#67 SEC GIS 보통점검","2023-11-20 09:00","2023-11-20 18:00","취소","취소","연속"]
[287,"충북","직할","신진천S/S SEC CB 60610","22-23년 충북직할 변전협력회사 총액공사","장기 미동작 차단기 조작시험","2023-11-21 09:00","2023-11-21 18:00","취소","취소","연속"]
[288,"충북","직할","신진천S/S CB 6200","22-23년 충북직할 변전협력회사 총액공사","신진천S/S 154kV #61-66 TIE GIS 보통점검","2023-11-22 09:00","2023-11-22 18:00","취소","취소","연속"]
[289,"충북","직할","신진천S/S SEC CB 65660","22-23년 충북직할 변전협력회사 총액공사","신진천S/S 154kV #65-66 SEC GIS 보통점검","2023-11-23 09:00","2023-11-23 18:00","취소","취소","연속"]
[290,"충북","직할","신진천S/S SEC CB 61620","22-23년 충북직할 변전협력회사 총액공사","신진천S/S 154kV #61-62 SEC GIS 보통점검","2023-11-24 09:00","2023-11-24 18:00","취소","취소","연속"]
[291,"충북","직할","신진천진천#2 T/L","22-23년 충북직할 변전협력회사 총액공사","신진천S/S 154kV 신진천-진천 #2T/L GIS 노후 전자변 교체","2023-11-27 09:00","2023-11-27 18:00","취소","취소","연속"]
[292,"충북","직할","진천덕산#2 T/L","2023년 가공송전 순시점검 위탁공사","진천덕산#2 No.1~2,5,8,9,15,27 현수애자 절연저항 측정","2023-11-17 09:00","2023-11-17 18:00","2023-11-17 09:00","2023-11-17 18:00","매일"]
[293,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주 #1,4 T/L, #62 M.Tr 1차 GIS 대체","2023-11-14 08:00","2023-11-16 14:00","2023-11-14 08:00","2023-11-16 14:00","연속"]
[294,"충북","청주","남청주S/S #60 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","#61-60 SEC GIS 대체","2023-11-09 14:00","2023-11-11 18:00","2023-11-09 14:00","2023-11-11 18:00","연속"]
[295,"충북","청주","남청주S/S CB 6200","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주 #1,4 T/L, #62 M.Tr 1차 GIS 대체","2023-11-14 08:00","2023-11-29 18:00","2023-11-14 08:00","2023-11-29 18:00","연속"]
[296,"충북","청주","남청주청주#1 T/L","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주 #1,4 T/L, #62 M.Tr 1차 GIS 대체","2023-11-14 14:00","2023-11-29 18:00","2023-11-14 14:00","2023-11-29 18:00","연속"]
[297,"충북","청주","남청주청주#4 T/L","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주 #1,4 T/L, #62 M.Tr 1차 GIS 대체","2023-11-14 14:00","2023-11-29 18:00","2023-11-14 14:00","2023-11-29 18:00","연속"]
[298,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주 #1,4 T/L, #62 M.Tr 1차 GIS 대체","2023-11-16 14:00","2023-11-23 14:00","2023-11-16 14:00","2023-11-23 14:00","연속"]
[299,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (3차)","#61-66 BUS TIE, 남청주청주 #1,4 T/L, #62 M.Tr 1차 GIS 대체","2023-11-23 14:00","2023-11-29 14:00","2023-11-23 14:00","2023-11-29 14:00","연속"]
[300,"충북","청주","남청주죽림#1 T/L","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-30 09:00","2023-11-30 10:00","2023-11-30 09:00","2023-11-30 10:00","연속"]
[301,"충북","청주","남청주죽림#2 T/L","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-30 10:00","2023-11-30 11:00","2023-11-30 10:00","2023-11-30 11:00","연속"]
[302,"충북","청주","남청주오송#1 T/L","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-30 11:00","2023-11-30 12:00","2023-11-30 11:00","2023-11-30 12:00","연속"]
[303,"충북","청주","남청주오송#2 T/L","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-30 13:00","2023-11-30 14:00","2023-11-30 13:00","2023-11-30 14:00","연속"]
[304,"충북","청주","남청주S/S CB 6300","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-30 14:00","2023-11-30 15:00","2023-11-30 14:00","2023-11-30 15:00","연속"]
[305,"충북","청주","남청주S/S CB 6100","남청주S/S 장기사용 감시제어반 대체공사","신설 모자익반 제어시험 (CB 및 DS 투입/개방)","2023-11-30 15:00","2023-11-30 16:00","2023-11-30 15:00","2023-11-30 16:00","연속"]
[306,"충북","청주","남청주S/S #60 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","#61-60 SEC GIS 대체","2023-11-03 09:00","2023-11-04 10:00","2023-11-03 09:00","2023-11-04 10:00","연속"]
[307,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","#61-60 SEC GIS 대체","2023-11-04 10:00","2023-11-09 14:00","2023-11-04 10:00","2023-11-09 14:00","연속"]
[308,"충북","청주","남청주S/S SEC CB 60610","남청주S/S 154kV 장기사용 GIS 대체공사 (2차)","#61-60 SEC GIS 대체","2023-11-03 09:00","2023-11-11 18:00","2023-11-03 09:00","2023-11-11 18:00","연속"]
[309,"충북","청주","서청주사직#2 T/L","22-23년 변전협력회사 총액공사","차단기용 전자변 교체","2023-11-05 09:00","2023-11-05 16:00","2023-11-05 09:00","2023-11-05 16:00","연속"]
[310,"충북","청주","화동영동 T/L","`22~`23년 청주전력지사 송전협력회사 총액공사","화동T/L 추락방지 43기, 폴리머지지애자2기 영동분기T/L 추락방지 61기, 폴리머지지애자1기 설치","2023-11-13 08:00","2023-11-25 18:00","취소","취소","매일"]
[311,"충북","청주","초정청주#1 T/L","154kV 초정변전소 외장재 교체공사","드라이비트 마감재 철거 / 신규 알루미늄시트판넬 설치","2023-11-19 09:00","2023-11-25 18:00","취소","취소","연속"]
[312,"충북","청주","사리초정#1 T/L","154kV 초정변전소 외장재 교체공사","드라이비트 마감재 철거 / 신규 알루미늄시트판넬 설치","2023-11-04 09:00","2023-11-25 18:00","취소","취소","연속"]
[313,"충북","청주","사리초정#2 T/L","154kV 초정변전소 외장재 교체공사","드라이비트 마감재 철거 / 신규 알루미늄시트판넬 설치","2023-11-04 09:00","2023-11-18 18:00","취소","취소","연속"]
[314,"충북","충주","감곡가남#1 T/L","2022년 가공 송전선로 추락방지장치 설치공사","감곡가남#1T/L NO.1~19 추락방지장치 설치","2023-11-06 07:30","2023-11-09 18:00","취소","취소","매일"]
[315,"충북","충주","감곡가남#2 T/L","2022년 가공 송전선로 추락방지장치 설치공사","감곡가남#2T/L NO.1~19 추락방지장치 설치","2023-11-12 07:30","2023-11-14 18:00","취소","취소","매일"]
[316,"충북","충주","금왕남음성#1 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV금왕남음성#1 T/L No.1~42","2023-11-09 07:30","2023-11-15 18:00","취소","취소","매일"]
[317,"충북","충주","금왕남음성#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV금왕남음성#2 T/L No.1~42","2023-11-01 07:30","2023-11-08 18:00","취소","취소","매일"]
[318,"충북","충주","점촌단양 T/L","22-23년 충주전력지사 변전정비 총액공사","단양S/S 154kV 점촌-단양T/L GIS,LA 보통점검 및 보호배전반 대체","2023-11-11 09:00","2023-11-11 13:00","취소","취소","연속"]
[319,"충북","충주","문경단양 T/L","22-23년 충주전력지사 변전정비 총액공사","단양S/S 154kV 문경-단양T/L GIS,LA 보통점검 및 보호배전반 대체","2023-11-04 09:00","2023-11-04 13:00","취소","취소","연속"]
[320,"충북","충주","신제천제천#2 T/L","충주전력지사 가공송전 순시점검 위탁공사","신제천-왕암#2T/L 정밀점검","2023-11-01 07:00","2023-11-07 18:00","취소","취소","매일"]
[321,"충북","충주","신제천제천#1 T/L","345kV 신제천-신충주 등 6개T/L 송전피뢰기 설치공사","154kV 신제천-제천T/L 송전피뢰기 설치(주말작업 있음)","2023-11-18 07:00","2023-11-21 18:00","2023-11-18 07:00","2023-11-21 18:00","매일"]
[322,"충북","충주","신제천S/S #62 BUS","345kV 신제천S/S #4 M.Tr 대체공사","#4 M.Tr 대체분 154kV 무부하가압 및 실부하 위상체크용","2023-11-03 09:00","2023-11-08 18:00","2023-11-03 09:00","2023-11-08 18:00","연속"]
[323,"충북","충주","신충주감곡#1 T/L","2023년 가공송전 순시점검 위탁공사","154kV 신충주감곡#1T/L No.86,87 초기점검","2023-11-03 08:00","2023-11-04 18:00","2023-11-03 08:00","2023-11-04 18:00","매일"]
[324,"충북","충주","신충주감곡#2 T/L","2023년 가공송전 순시점검 위탁공사","154kV 신충주감곡#2T/L No.86,87 초기점검","2023-11-01 08:00","2023-11-02 18:00","2023-11-01 08:00","2023-11-02 18:00","매일"]
[325,"충북","충주","음성금왕#1 T/L","22-23년 충주전력지사 변전정비 총액공사","음성S/S 154kV 음성-금왕#1T/L GIS 초기점검","2023-11-06 09:00","2023-11-06 13:00","취소","취소","연속"]
[326,"충북","충주","음성금왕#2 T/L","22-23년 충주전력지사 변전정비 총액공사","음성S/S 154kV 음성-금왕#2T/L GIS 보통점검","2023-11-06 13:00","2023-11-06 18:00","취소","취소","연속"]
[327,"충북","충주","음성금왕#2 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV음성금왕#2 T/L No.8~65","2023-11-05 07:30","2023-11-05 18:00","취소","취소","매일"]
[328,"충북","충주","음성괴산 T/L","2023년 가공송전 순시점검 위탁공사","음성괴산T/L 음성~괴산S/S 정밀점검(풍동음성#1 병가선로)","2023-11-20 08:00","2023-11-24 18:00","취소","취소","매일"]
[329,"충북","충주","풍동음성#2 T/L","2023년 가공송전 순시점검 위탁공사","풍동음성#2 풍동S/S~No.73,76~음성S/S 정밀점검","2023-11-27 08:00","2023-12-01 18:00","취소","취소","매일"]
[330,"충북","충주","음성사리 T/L","2023년 가공송전 순시점검 위탁공사","음성사리T/L 음성~사리S/S 정밀점검(풍동음성#2 병가선로)","2023-11-27 08:00","2023-12-01 18:00","취소","취소","매일"]
[331,"충북","충주","신충주음성#1 T/L","22-23년 충주전력지사 변전정비 총액공사","음성,신충주S/S 154kV 신충주-음성#1T/L GIS 보통,초기점검","2023-11-02 09:00","2023-11-02 13:00","취소","취소","연속"]
[332,"충북","충주","음성금왕#1 T/L","2022~2023년 충북본부 직할 송전협력회사 총액공사","추락방지장치 설치 154kV음성금왕#1 T/L No.8~65","2023-11-01 07:30","2023-11-04 18:00","취소","취소","매일"]
[333,"충북","충주","신충주음성#2 T/L","22-23년 충주전력지사 변전정비 총액공사","음성,신충주S/S 154kV 신충주-음성#2T/L GIS 보통 및 초기점검","2023-11-02 13:00","2023-11-02 18:00","취소","취소","연속"]
[334,"충북","충주","왕암충주 T/L","154kV 왕암-충주T/L No.69 지장철탑이설공사","산척산업단지 조성에 지장이되는 철탑이설 - 실설 1기, 가철탑 1기, 철거 1기","2023-11-12 08:00","2023-11-18 18:00","취소","취소","연속"]
[335,"충북","충주","북충주충주 T/L","154kV 왕암-충주T/L No.69 지장철탑이설공사","산척산업단지 조성에 지장이되는 철탑이설 - 실설 1기, 가철탑 1기, 철거 1기","2023-11-19 08:00","2023-11-23 18:00","취소","취소","연속"]
[336,"충북","충주","북충주충주 T/L","154kV 왕암-충주T/L No.69 지장철탑이설공사","산척산업단지 조성에 지장이되는 철탑이설 - 실설 1기, 가철탑 1기, 철거 1기","2023-11-07 08:00","2023-11-11 18:00","취소","취소","연속"]
[337,"충북","충주","풍동음성#1 T/L","2023년 가공송전 순시점검 위탁공사","풍동음성#1 풍동S/S~No.73,76~음성S/S 정밀점검","2023-11-20 08:00","2023-11-24 18:00","취소","취소","매일"]
[338,"대전세종충남","대전","가수원대전서남부 T/L","가수원S/S 154kV LH열병합 T/L 차단기 조작시험","가수원S/S 154kV LH열병합 T/L 차단기 조작시험","2023-11-16 09:00","2023-11-16 18:00","취소","취소","연속"]
[339,"대전세종충남","대전","신옥천남대전#3 T/L","[송전]345kV신옥천-청양등17개T/L추락방지시설 설치공사","[송전] 154kV 신옥천-남대전삼사T/L 추락방지시설 설치공사","2023-11-28 08:00","2023-12-04 18:00","2023-11-29 08:00","2023-12-04 18:00","매일"]
[340,"대전세종충남","대전","신옥천남대전#2 T/L","[송전]345kV신옥천-청양등17개T/L추락방지시설 설치공사","[송전] 154kV 신옥천-남대전T/L 추락방지시설 설치공사","2023-11-22 08:00","2023-11-28 18:00","2023-11-22 08:00","2023-11-28 18:00","매일"]
[341,"대전세종충남","대전","논산은진#2 T/L","[송전] 154kV 논산-은진T/L 정밀점검","[송전] 154kV 논산-은진#2T/L 정밀점검","2023-11-13 08:00","2023-11-17 18:00","취소","취소","매일"]
[342,"대전세종충남","대전","부여논산#1 T/L","[송전] 154kV 논산-은진T/L 정밀점검","[송전] 154kV 논산-은진#1T/L 정밀점검 안전 확보차","2023-11-06 08:00","2023-11-06 18:00","취소","취소","매일"]
[343,"대전세종충남","대전","논산은진#1 T/L","[송전] 154kV 논산-은진T/L 정밀점검","[송전] 154kV 논산-은진#1T/L 정밀점검","2023-11-06 08:00","2023-11-10 18:00","2023-11-20 08:00","2023-12-01 18:00","매일"]
[344,"대전세종충남","대전","부여논산#2 T/L","[송전] 154kV 논산-은진T/L 정밀점검","[송전] 154kV 논산-은진#2T/L 정밀점검 안전 확보차","2023-11-13 08:00","2023-11-13 18:00","2023-11-27 08:00","2023-11-28 18:00","매일"]
[345,"대전세종충남","대전","신옥천서대전 T/L","[송전] 154kV 가수원-서대전 등 5개T/L 추락방지시설 설치공사","[송전] 154kV 신옥천-서대전T/L 추락방지시설 설치공사","2023-11-09 08:00","2023-11-24 18:00","2023-11-09 08:00","2023-11-24 18:00","매일"]
[346,"대전세종충남","대전","신계룡유성#2 T/L","[송전취소시]신계룡S/S 신계룡-유성#2T/L CVT 하자점검","[송전취소시]신계룡S/S 신계룡-유성#2T/L CVT 하자점검","2023-11-15 09:00","2023-11-15 18:00","2023-11-15 09:00","2023-11-15 18:00","연속"]
[347,"대전세종충남","대전","신계룡은진#1 T/L","[송전] 154kV 신계룡-은진 등 개T/L 노후금구류 교체공사","[송전] 154kV 신계룡-은진 등 개T/L 노후금구류 교체공사","2023-11-02 08:00","2023-11-03 18:00","2023-11-02 08:00","2023-11-03 18:00","매일"]
[348,"대전세종충남","대전","신옥천유천 T/L","[송전취소시]유천S/S 154kV 신옥천-유천T/L GIS 보통점검","[송전취소시]유천S/S 154kV 신옥천-유천T/L GIS 보통점검","2023-11-07 09:00","2023-11-07 18:00","2023-11-07 09:00","2023-11-07 18:00","연속"]
[349,"대전세종충남","서산","석문당진화력#2 T/L","서산P/O 154kV 효성제 CB 베어링 교체공사","당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 베어링 교체 (병행1) 석문S/S 687 GIS IED 성능개선 (병행2) 당진화력S/S 627 GIS 보통점검 (병행3) 석문S/S 687 GIS 보통점검","2023-11-08 09:00","2023-11-09 18:00","취소","취소","매일"]
[350,"대전세종충남","서산","석문당진화력#1 T/L","서산P/O 154kV 효성제 CB 베어링 교체공사","당진화력S/S 154kV 석문-당진화력#1T/L 617 CB 베어링 교체 (병행1) 석문S/S 617 GIS IED 성능개선 (병행2) 당진화력S/S 617 GIS 보통점검 (병행3) 석문S/S 617 GIS 보통점검","2023-11-06 09:00","2023-11-07 18:00","취소","취소","매일"]
[351,"대전세종충남","서산","대산석문#1 T/L","154kV 대산S/S #4M.Tr 증설공사","- 170kV GIS 설치관련 안전이격거리 확보 및 무부하가압","2023-11-20 08:00","2023-11-27 18:00","취소","취소","연속"]
[352,"대전세종충남","서산","서산대산#4 T/L","'23년 서산P/O 변전협력회사 총액공사","(10월 휴전 취소시) 대산S/S 154kV 서산-대산#4T/L 6G7 GIS 보통점검","2023-11-29 09:00","2023-11-29 18:00","취소","취소","연속"]
[353,"대전세종충남","서산","서산대산#4 T/L","154kV 대산S/S #4M.Tr 증설공사","- 170kV GIS 설치관련 무부하가압","2023-11-22 18:00","2023-11-24 08:00","취소","취소","연속"]
[354,"대전세종충남","서산","서산대산#4 T/L","154kV 대산S/S #4M.Tr 증설공사","- 170kV GIS 설치관련 무부하가압","2023-11-26 18:00","2023-11-27 18:00","취소","취소","연속"]
[355,"대전세종충남","서산","대산석문#2 T/L","'23년 서산P/O 변전협력회사 총액공사","(10월 휴전 취소시) 대산S/S 154kV 대산-석문#2T/L CB 전자변, 에어링밸브 교체 (병행1) 대산S/S 154kV 대산-석문#2T/L CVT 대체 (병행2) 석문S/S 154kV 대산-석문#2T/L IED 성능개선","2023-11-28 09:00","2023-11-28 18:00","취소","취소","연속"]
[356,"대전세종충남","서산","서산홍성 T/L","23년 서산P/O 장기사용 배전반 교체공사","(신서산S/S 80BUS 휴전 취소시) 154kV 서산-홍성T/L 보호반 대체공사","2023-11-08 09:00","2023-11-10 18:00","2023-11-08 09:00","2023-11-10 18:00","연속"]
[357,"대전세종충남","서산","서산해미 T/L","23년 서산P/O 장기사용 배전반 교체공사","(신서산S/S #4M.Tr 휴전 취소시) 154kV 서산-해미T/L 보호반 대체공사","2023-11-13 09:00","2023-11-15 18:00","2023-11-13 09:00","2023-11-15 18:00","연속"]
[358,"대전세종충남","서산","서산대산 T/L","23년 서산P/O 장기사용 배전반 교체공사","(신서산S/S #4M.Tr 휴전 취소시) 154kV 서산-대산T/L 보호반 대체공사","2023-11-27 09:00","2023-11-29 18:00","취소","취소","연속"]
[359,"대전세종충남","서산","합덕송악#2 T/L","154kV 합덕-송악 등 2개 T/L 상간스페이서 설치 및 이도조정","상간스페이서 설치 : No.85~86 이도조정 : No.85~87 (10월 휴전 취소시)","2023-11-06 08:00","2023-11-10 18:00","2023-11-06 08:00","2023-11-10 18:00","매일"]
[360,"대전세종충남","서산","합덕송악#1 T/L","154kV 합덕-송악 T/L 상간스페이서 설치 및 이도조정,지지애자교체","상간스페이서 설치 : No.85~86 이도조정 : No.85~87 점퍼지지애자 교체 : No.2,8 345kV 신서산-아산T/L 소도체 이도조정(병가선로) No.25~27,5~6(3경간) (주말제외)","2023-11-13 08:00","2023-11-24 18:00","취소","취소","매일"]
[361,"대전세종충남","서산","당진송악#2 T/L","154kV 합덕-송악 등 2개 T/L 상간스페이서 설치 및 이도조정","상간스페이서 설치 : No.27~28 이도조정 : No.27~29","2023-11-13 08:00","2023-11-17 18:00","2023-11-13 08:00","2023-11-17 18:00","매일"]
[362,"대전세종충남","서산","당진송악#1 T/L","154kV 합덕-송악 등 2개 T/L 상간스페이서 설치 및 이도조정","상간스페이서 설치 : No.27~28 이도조정 : No.27~29 (10월 휴전 취소시)","2023-11-06 08:00","2023-11-10 18:00","2023-11-06 08:00","2023-11-10 18:00","매일"]
[363,"대전세종충남","서산","신당진당진#2 T/L","23년 서산P/O 154kV 이하 개폐장치 보통점검공사","신당진S/S 154kV 신당진-당진#2T/L 647 GIS 보통점검","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[364,"대전세종충남","서산","서산태안 T/L","태안S/S 154kV 모선구분차단기 설치공사","- (신)6333Bay 1,2DS 상확인 및 24h 무부하가압","2023-11-29 09:00","2023-11-30 15:00","취소","취소","연속"]
[365,"대전세종충남","서산","서산태안 T/L","태안S/S 154kV 모선구분차단기 설치공사","#2BUS 무부하가압","2023-11-23 14:00","2023-11-24 14:00","취소","취소","연속"]
[366,"대전세종충남","서산","서산태안 T/L","태안S/S 154kV 모선구분차단기 설치공사","#1BUS 무부하가압","2023-11-09 14:00","2023-11-10 14:00","취소","취소","연속"]
[367,"대전세종충남","서산","서산태안화력 T/L","태안화력S/Y 154kV 옥외 기타설비 내장화공사","태안화력S/Y 154kV 서산-태안화력T/L 옥외 기타설비(LA, CVT) 내장화공사","2023-11-13 09:00","2023-11-17 18:00","취소","취소","연속"]
[368,"대전세종충남","서산","서산태안화력 T/L","154kV 태안화력T/L 전선접속개소 전선교체공사","154kV 서산-태안화력T/L 전력선 교체공사(2개소) - No.2~6, 11~13","2023-11-13 08:00","2023-11-17 18:00","취소","취소","연속"]
[369,"대전세종충남","서산","태안태안화력 T/L","154kV 태안화력T/L 전선접속개소 전선교체공사","154kV 태안-태안화력T/L 전력선 교체공사(3개소) - No.2~6, 6~8, 11~13","2023-11-20 08:00","2023-11-24 18:00","취소","취소","연속"]
[370,"대전세종충남","서산","태안태안화력 T/L","태안화력S/Y 154kV 옥외 기타설비 내장화공사","태안화력S/Y 154kV 태안-태안화력T/L 옥외 기타설비(LA, CVT) 내장화공사","2023-11-06 09:00","2023-11-10 18:00","취소","취소","연속"]
[371,"대전세종충남","서산","해미홍성 T/L","23년 서산P/O 장기사용 배전반 교체공사","(신서산S/S #4M.Tr 휴전 취소시) 154kV 해미-홍성T/L 보호반 대체공사","2023-11-20 09:00","2023-11-22 18:00","2023-11-20 09:00","2023-11-22 18:00","연속"]
[372,"대전세종충남","세종","덕진공주#1 T/L","154kV 덕진공주, 덕진유성 절연저항 측정","덕진공주#1T/L 현수애자 절연진단 불량 3개철탑(6장) 절연저항 측정","2023-11-20 08:00","2023-11-21 17:00","2023-11-20 08:00","2023-11-21 17:00","매일"]
[373,"대전세종충남","세종","덕진공주#2 T/L","154kV 덕진공주, 덕진유성 절연저항 측정","덕진공주#2T/L 현수애자 절연진단 불량 5개철탑(7장) 절연저항 측정","2023-11-22 08:00","2023-11-23 17:00","2023-11-22 08:00","2023-11-23 17:00","매일"]
[374,"대전세종충남","세종","부강대청HP T/L","[송전]154kV 부강대청HPT/L 추락방지시설 설치공사","[송전]154kV 부강대청HPT/L 추락방지시설 설치공사 - No.1~42 (42기)","2023-11-22 07:00","2023-11-29 18:00","2023-11-13 07:00","2023-11-21 18:00","매일"]
[375,"대전세종충남","세종","부강신탄진 T/L","[송전]154kV 부강-신탄진T/L 추락방지시설 설치공사","[송전]154kV 부강-신탄진T/L 추락방지시설 설치공사 - No.41~57, 62 (18기)","2023-11-30 07:00","2023-12-04 18:00","취소","취소","매일"]
[376,"대전세종충남","세종","서세종조치원 T/L","[송전]154kV 서세종-조치원T/L 추락방지시설 설치공사","[송전]154kV 서세종-조치원T/L 추락방지시설 설치공사 - No1~14, 16~19, (18기)","2023-11-08 07:00","2023-11-10 18:00","2023-11-08 07:00","2023-11-10 18:00","매일"]
[377,"대전세종충남","세종","조치원월산 T/L","[송전]154kV 조치원-월산T/L 추락방지시설 설치공사","[송전]154kV 조치원-월산T/L 추락방지시설 설치공사 - No1~14, 16~20, (19기)","2023-11-01 07:00","2023-11-08 18:00","2023-11-01 07:00","2023-11-07 18:00","매일"]
[378,"대전세종충남","직할","대화둔산#1 T/L","대화S/S 170kV GIS 주기도래점검","O 대화S/S 170kV GIS 조작시험","2023-11-02 09:00","2023-11-02 14:00","2023-11-03 09:00","2023-11-03 14:00","연속"]
[379,"대전세종충남","직할","대덕둔지 T/L","'23년 직할 주기도래 보통점검","'23년 직할 주기도래 보통점검","2023-11-14 09:00","2023-11-14 18:00","2023-11-14 09:00","2023-11-14 18:00","연속"]
[380,"대전세종충남","직할","신탄진대청HP T/L","[송전]154kV 신탄진-대청HP/L 추락방지시설 설치공사","[송전]154kV 신탄진-대청HP/L 추락방지시설 설치공사 - No1~7, 42~56, 62 (25기)","2023-11-13 07:00","2023-11-21 18:00","취소","취소","매일"]
[381,"대전세종충남","천안","둔포직산#1 T/L","추락방지장치 설치공사","154kV 직산-둔포 #1T/L 추락방지장치 설치","2023-11-03 07:00","2023-11-03 17:00","2023-11-22 07:00","2023-11-23 15:00","연속"]
[382,"대전세종충남","천안","둔포직산#2 T/L","추락방지장치 설치공사","154kV 직산-둔포 #2T/L 추락방지장치 설치","2023-11-06 07:00","2023-11-06 17:00","2023-11-24 07:00","2023-11-24 15:00","연속"]
[383,"대전세종충남","천안","서천안탕정#2 T/L","(10월취소시)서천안S/S 서천안-탕정#2T/L GIS 보통점검","(10월취소시)서천안S/S 서천안-탕정#2T/L GIS 보통점검","2023-11-10 09:00","2023-11-10 18:00","취소","취소","연속"]
[384,"대전세종충남","천안","서천안S/S SEC CB 65660","(10월취소시)서천안S/S B/S 65-66-0GIS 보통점검","(10월취소시)서천안S/S B/S 65-66-0GIS 보통점검","2023-11-02 09:00","2023-11-02 18:00","2023-11-02 09:00","2023-11-02 18:00","연속"]
[385,"대전세종충남","천안","서천안S/S SEC CB 60610","(10월취소시)서천안S/S B/S 60-61-0GIS 보통점검","(10월취소시)서천안S/S B/S 60-61-0GIS 보통점검","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[386,"대전세종충남","천안","서천안탕정#1 T/L","(10월취소시)서천안S/S 서천안-탕정#1T/L GIS 보통점검","(10월취소시)서천안S/S 서천안-탕정#1T/L GIS 보통점검","2023-11-06 09:00","2023-11-06 18:00","취소","취소","연속"]
[387,"대전세종충남","천안","서천안S/S CB 6100","서천안S/S 154kV 6100 GIS 보통점검","서천안S/S 154kV 6100 GIS 보통점검","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[388,"대전세종충남","천안","둔포석곡#2 T/L","추락방지장치 설치공사","154kV 둔포-석곡 #2T/L 추락방지장치 설치","2023-11-02 07:00","2023-11-02 17:00","2023-11-28 07:00","2023-11-28 17:00","연속"]
[389,"대전세종충남","천안","둔포석곡#1 T/L","추락방지장치 설치공사","154kV 둔포-석곡 #1T/L 추락방지장치 설치","2023-11-01 07:00","2023-11-01 17:00","2023-11-27 07:00","2023-11-27 17:00","연속"]
[390,"대전세종충남","천안","신온양석곡#2 T/L","(10월취소시)신온양S/S 154kV 신온양-석곡#2TL GIS 보통점검","(10월취소시)신온양S/S 154kV 신온양-석곡#2TL GIS 보통점검","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[391,"대전세종충남","천안","아산인주#2 T/L","(10월취소시)아산,인주S/S 아산-인주#2T/L 보호반 교체","(10월취소시)아산,인주S/S 아산-인주#2T/L 보호반 교체","2023-11-14 09:00","2023-11-17 18:00","취소","취소","연속"]
[392,"대전세종충남","천안","아산예산#1 T/L","[송전]'22~'23년도 천안전력지사 가공송전협력회사 총액공사","추락방지장치","2023-11-13 07:00","2023-11-17 18:00","2023-11-13 07:00","2023-11-17 18:00","매일"]
[393,"대전세종충남","천안","아산예산#2 T/L","[송전]'22~'23년도 천안전력지사 가공송전협력회사 총액공사","추락방지장치","2023-11-06 07:00","2023-11-10 18:00","2023-11-06 07:00","2023-11-10 18:00","매일"]
[394,"대전세종충남","천안","아산합덕#1 T/L","[송전]'22~'23년도 천안전력지사 가공송전협력회사 총액공사","추락방지장치 설치","2023-11-20 07:00","2023-12-01 18:00","취소","취소","매일"]
[395,"대전세종충남","천안","아산온양#1 T/L","[송전]'22~'23년도 천안전력지사 가공송전협력회사 총액공사","추락방지장치","2023-11-01 07:00","2023-11-07 18:00","2023-11-01 07:00","2023-11-07 18:00","매일"]
[396,"대전세종충남","천안","아산인주#1 T/L","(10월취소시)아산,인주S/S 아산-인주#1T/L 보호반 교체","(10월취소시)아산,인주S/S 아산-인주#1T/L 보호반 교체","2023-11-07 09:00","2023-11-10 18:00","취소","취소","연속"]
[397,"대전세종충남","천안","아산온양#2 T/L","[송전]'22~'23년도 천안전력지사 가공송전협력회사 총액공사","추락방지장치","2023-11-16 07:00","2023-11-22 18:00","취소","취소","매일"]
[398,"대전세종충남","천안","아산인주#2 T/L","154kV 아산-인주#2T/L GIS 초기점검 및 LA 보통점검","154kV 아산-인주#2T/L GIS 초기점검 및 LA 보통점검","2023-11-14 09:00","2023-11-14 18:00","취소","취소","연속"]
[399,"대전세종충남","천안","아산인주#1 T/L","154kV 아산-인주#1T/L GIS 초기점검 및 LA 보통점검","154kV 아산-인주#1T/L GIS 초기점검 및 LA 보통점검","2023-11-07 09:00","2023-11-07 18:00","취소","취소","연속"]
[400,"대전세종충남","천안","온양풍세#2 T/L","[송전]'22~'23년도 천안전력지사 가공송전협력회사 총액공사","추락방지장치","2023-11-21 07:00","2023-11-22 18:00","2023-11-21 07:00","2023-11-22 18:00","매일"]
[401,"대전세종충남","천안","온양풍세#1 T/L","온양S/S 154kV 온양-풍세#1T/L CB 개폐타임 측정","온양S/S 154kV 온양-풍세#1T/L CB 개폐타임 측정","2023-11-20 07:00","2023-11-20 18:00","2023-11-20 07:00","2023-11-20 18:00","연속"]
[402,"대전세종충남","천안","인주불당#1 T/L","(10월취소시)[송전]154kV 인주-불당T/L 지장송전선로 이설공사","No.23~26 2기설치, 2기철거, ACSR/AW 410㎟ x 2B x 2C x 0.655km","2023-11-01 07:00","2023-11-05 18:00","2023-11-11 07:00","2023-11-12 18:00","연속"]
[403,"대전세종충남","천안","인주불당#2 T/L","인주S/S 154kV 인주-불당#1,2T/L CB 개폐타임 측정","인주S/S 154kV 인주-불당#1,2T/L CB 개폐타임 측정","2023-11-13 14:00","2023-11-13 18:00","취소","취소","연속"]
[404,"대전세종충남","천안","인주불당#1 T/L","인주S/S 154kV 인주-불당#1,2T/L CB 개폐타임 측정","인주S/S 154kV 인주-불당#1,2T/L CB 개폐타임 측정","2023-11-13 09:00","2023-11-13 14:00","취소","취소","연속"]
[405,"대전세종충남","천안","인주불당#2 T/L","(10월취소시)[송전]154kV 인주-불당T/L 지장송전선로 이설공사","No.23~26 2기설치, 2기철거, ACSR/AW 410㎟ x 2B x 2C x 0.655km","2023-11-06 07:00","2023-11-10 18:00","2023-11-18 07:00","2023-11-19 18:00","연속"]
[406,"대전세종충남","천안","장재천안#2 T/L","(10월취소시) 154kV 장재-천안#2T/L 보호배전반 교체","장재,천안S/S 154kV 장재-천안#2T/L 보호배전반 교체","2023-11-28 09:00","2023-12-01 18:00","취소","취소","연속"]
[407,"대전세종충남","천안","장재천안#1 T/L","(10월취소시) 154kV 장재-천안#1T/L 보호배전반 교체","장재,천안S/S 154kV 장재-천안#1T/L 보호배전반 교체","2023-11-21 09:00","2023-11-24 18:00","취소","취소","연속"]
[408,"대전세종충남","천안","서천안탕정#1 T/L","154kV 서천안-탕정T/L 인출변경 공사","154kV 서천안-탕정T/L No.28 ~ 탕정S/S (인출변경)","2023-11-27 09:00","2023-11-30 18:00","취소","취소","연속"]
[409,"대전세종충남","천안","풍세장재#1 T/L","154kV 풍세-장재#1T/L 보호배전반 성능개선","154kV 풍세-장재#1T/L 보호배전반 성능개선","2023-11-29 09:00","2023-11-29 18:00","취소","취소","연속"]
[410,"대전세종충남","천안","풍세장재#2 T/L","154kV 풍세-장재#2T/L 보호배전반 성능개선","154kV 풍세-장재#2T/L 보호배전반 성능개선","2023-11-30 09:00","2023-11-30 18:00","취소","취소","연속"]
[411,"대전세종충남","천안","한샘직산#2 T/L","추락방지장치 설치공사","154kV 한샘-직산 #2T/L 추락방지장치 설치","2023-11-08 07:00","2023-11-08 17:00","2023-11-24 15:00","2023-11-24 18:00","연속"]
[412,"대전세종충남","천안","한샘직산#1 T/L","추락방지장치 설치공사","154kV 한샘-직산 #1T/L 추락방지장치 설치","2023-11-07 07:00","2023-11-07 17:00","2023-11-23 15:00","2023-11-23 18:00","연속"]
[413,"대전세종충남","청양","청양관창#2 T/L","(10월 취소시)청양P/O 변전협력회사 총액공사","(10월취소시) 154kV 청양-관창#2T/L - 청양, 관창S/S 차단기 조작시험(양단) - LA 초기점검(A,B,C, 양단)","2023-11-09 10:00","2023-11-09 18:00","취소","취소","연속"]
[414,"대전세종충남","청양","관창대천#1 T/L","(10월 취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(10월취소시)154kV 관창-대천#1T/L - 관창S/S GIS 보통점검 및 노후보조계전기 교체","2023-11-01 10:00","2023-11-02 18:00","취소","취소","연속"]
[415,"대전세종충남","청양","관창보령TP T/L","(10월취소시) 청양P/O 변전협력회사 총액공사","(10월취소시) 154kV 관창-보령화력#T/L 보호반 대체공사 - 관창S/S 차단기 조작시험 / - 보령T/P 차단기 조작시험","2023-11-01 10:00","2023-11-03 18:00","2023-11-01 10:00","2023-11-03 18:00","연속"]
[416,"대전세종충남","청양","관창대천#2 T/L","(10월 취소시)청양P/O 변전협력회사 총액공사","(10월취소시)154kV 관창-대천#2TL - 관창S/S 차단기 조작시험","2023-11-03 10:00","2023-11-03 14:00","취소","취소","연속"]
[417,"대전세종충남","청양","관창보령TP T/L","(10월 취소시)청양P/O 변전협력회사 총액공사","(10월 취소시) 154kV 관창-보령복합#T/L - 관창S/S 차단기 조작시험 - 보령T/P 차단기 조작시험","2023-11-06 10:00","2023-11-06 18:00","2023-11-06 10:00","2023-11-06 18:00","연속"]
[418,"대전세종충남","청양","청양관창#1 T/L","(10월 취소시)청양P/O 변전협력회사 총액공사","(10월취소시) 154kV 청양-관창#1T/L - 청양, 관창S/S 차단기 조작시험(양단) - LA 초기점검(A,B,C, 양단)","2023-11-08 10:00","2023-11-08 18:00","취소","취소","연속"]
[419,"대전세종충남","청양","보령TP보령CC T/L","(10월 취소시)청양P/O 변전협력회사 총액공사","(10월 취소시) 154kV 보령복합T/L - 보령T/P 차단기 조작시험","2023-11-13 10:00","2023-11-13 18:00","2023-11-13 10:00","2023-11-13 18:00","연속"]
[420,"대전세종충남","청양","보령C/C CB 6100","(10월취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(10월취소시) 보령C/C 154kV BUS-TIE(6100) GIS 정밀점검","2023-11-06 10:00","2023-11-08 18:00","2023-11-06 10:00","2023-11-08 18:00","연속"]
[421,"대전세종충남","청양","보령T/P CB 6100","(10월 취소시)청양P/O 변전협력회사 총액공사","(10월취소시) 보령T/P 154kV 6100 BUS TIE GIS 보통점검","2023-11-07 10:00","2023-11-07 18:00","2023-11-07 10:00","2023-11-07 18:00","연속"]
[422,"대전세종충남","청양","옥산부여#1 T/L","청양P/O 변전협력회사 총액공사","154kV 옥산-부여#1T/L 세니온제 보호계전기 성능개선(양단)","2023-11-23 10:00","2023-11-23 18:00","2023-11-23 10:00","2023-11-23 18:00","연속"]
[423,"대전세종충남","청양","청양신풍#2 T/L","(10월 취소시)청양P/O 변전협력회사 총액공사","154kV 청양-신풍#2TL - 청양S/S 차단기 조작시험 및 LA 초기점검(A,B,C)","2023-11-02 10:00","2023-11-02 18:00","2023-11-02 10:00","2023-11-02 18:00","연속"]
[424,"대전세종충남","청양","옥산장항#1 T/L","(10월 취소시)청양P/O 변전협력회사 총액공사","(10월 취소시)154kV 옥산-장항#1T/L - 옥산S/S 차단기 조작시험 - 장항S/S LA 초기점검(A,B,C) 및 CVT 초기점검","2023-11-23 10:00","2023-11-23 18:00","취소","취소","연속"]
[425,"대전세종충남","청양","옥산장항#2 T/L","[송전] 154kV 옥산-장항#2T/L 철탑 추락방지장치 설치공사(수평)","154kV 옥산-장항#2T/L 철탑 추락방지장치 설치공사(수평) * 주말 제외","2023-11-06 08:00","2023-11-13 18:00","취소","취소","매일"]
[426,"대전세종충남","청양","신서천옥산#1 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","154kV 옥산-서천#1T/L - 옥산S/S 170kV GIS 보통점검 및 노후보조계전기 교체 - 옥산S/S LA 보통점검(A,B,C)","2023-11-20 10:00","2023-11-21 18:00","취소","취소","연속"]
[427,"대전세종충남","청양","신서천옥산#2 T/L","청양P/O 변전협력회사 총액공사","154kV 옥산-서천#2T/L - 옥산S/S 차단기 조작시험","2023-11-22 10:00","2023-11-22 18:00","취소","취소","연속"]
[428,"대전세종충남","청양","은하홍성#2 T/L","[송전] 154kV 은하-홍성#2T/L 철탑 추락방지장치 설치공사(수평)","154kV 은하-홍성#2T/L 철탑 추락방지장치 설치공사(수평) * 154kV 청양-은하#1T/L 4회선 병가구간","2023-11-20 08:00","2023-11-24 18:00","2023-11-20 08:00","2023-11-24 18:00","매일"]
[429,"대전세종충남","청양","청양은하#2 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","154kV 청양-은하 #2T/L - 은하S/S GIS 보통점검 및 노후보조계전기 교체 - 청양S/S 차단기 조작시험 및 LA(A,B,C) 초기점검","2023-11-03 10:00","2023-11-03 18:00","2023-11-03 10:00","2023-11-03 18:00","연속"]
[430,"대전세종충남","청양","청양은하#1 T/L","[송전] 154kV 청양-은하#1T/L 철탑 추락방지장치 설치공사(수평)","154kV 청양-은하#1T/L 철탑 추락방지장치 설치공사(수평) * 154kV 은하-홍성#2T/L 4회선 병가구간","2023-11-20 08:00","2023-11-24 18:00","2023-11-20 08:00","2023-11-24 18:00","매일"]
[431,"대전세종충남","청양","응봉홍성#2 T/L","[송전] 154kV 응봉-홍성#2T/L 철탑 추락방지장치 설치공사(수평)","154kV 응봉-홍성#2T/L 철탑 추락방지장치 설치공사(수평)","2023-11-14 08:00","2023-11-15 18:00","2023-11-14 08:00","2023-11-15 18:00","매일"]
[432,"대전세종충남","청양","응봉홍성#1 T/L","[송전] 154kV 응봉-홍성#1T/L 철탑 추락방지장치 설치공사(수평)","154kV 응봉-홍성#1T/L 철탑 추락방지장치 설치공사(수평)","2023-11-16 08:00","2023-11-17 18:00","2023-11-16 08:00","2023-11-17 18:00","매일"]
[433,"대전세종충남","청양","동군산장항#2 T/L","(10월 취소시)청양P/O 변전협력회사 총액공사","(10월 취소시)154kV 동군산-장항#2T/L - 장항S/S GIS 보통점검 및 CVT 보통점검","2023-11-16 10:00","2023-11-16 18:00","취소","취소","연속"]
[434,"대전세종충남","청양","동군산장항#1 T/L","[송전] 154kV 옥산-장항#2T/L 철탑 추락방지장치 설치공사(수평)","154kV 옥산-장항#2T/L 철탑 추락방지장치 설치공사(수평) * 4회선 병가구간","2023-11-10 08:00","2023-11-13 18:00","취소","취소","매일"]
[435,"대전세종충남","청양","청양S/S SEC CB 65660","(10월 취소시)청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","(10월취소시) 청양S/S 154kV 65-66-0 B/S - 170kV GIS 보통점검 및 노후보조계전기 교체","2023-11-01 10:00","2023-11-02 18:00","취소","취소","연속"]
[436,"대전세종충남","청양","서산홍성 T/L","청양전력지사 170kV GIS 정밀점검 및 보통점검 공사","- 170kV GIS 보통점검 및 LA(A,B,C) 보통점검","2023-11-08 10:00","2023-11-08 18:00","2023-11-08 10:00","2023-11-08 18:00","연속"]
[437,"전북","군산","군공소룡#1 T/L","군산P/O 154kV 차단기 보통점검","군공S/S 154kV 군공-소룡#1T/L 차단기 보통점검","2023-11-01 09:00","2023-11-01 14:00","2023-11-01 09:00","2023-11-01 14:00","연속"]
[438,"전북","군산","군공S/S CB 6100","군산P/O 154kV GIS 보통점검","군공 154kV 6100 BUS-TIE GIS 보통점검","2023-11-28 09:00","2023-11-28 14:00","2023-11-28 09:00","2023-11-28 14:00","연속"]
[439,"전북","군산","동군산군산CC#2 T/L","154kV 동군산-군산복합2T/L 차단기 보통점검","154kV 동군산-군산복합2T/L 차단기 보통점검","2023-11-30 14:00","2023-11-30 18:00","취소","취소","연속"]
[440,"전북","군산","동군산군산CC#1 T/L","154kV 동군산-군산복합1T/L 차단기 보통점검","154kV 동군산-군산복합1T/L 차단기 보통점검","2023-11-30 09:00","2023-11-30 14:00","취소","취소","연속"]
[441,"전북","군산","군산S/S #60 BUS","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-23 09:00","2023-11-26 18:00","취소","취소","연속"]
[442,"전북","군산","군산S/S #65 BUS","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-19 09:00","2023-11-22 18:00","취소","취소","연속"]
[443,"전북","군산","군산S/S #60 BUS","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-04 09:00","2023-11-06 18:00","취소","취소","연속"]
[444,"전북","군산","군산S/S #3 Sh.C CB","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-01 09:00","2023-11-26 18:00","취소","취소","연속"]
[445,"전북","군산","군산S/S CB 6100","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-01 09:00","2023-11-26 18:00","취소","취소","연속"]
[446,"전북","군산","군산이리#1 T/L","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-01 09:00","2023-11-26 18:00","취소","취소","연속"]
[447,"전북","군산","군산S/S #2 Sh.C CB","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-01 09:00","2023-11-26 18:00","취소","취소","연속"]
[448,"전북","군산","군산서군산#1 T/L","군산P/O 차단기 보통점검공사","군산S/S 군산-서군산#1T/L GIS 보통점검","2023-11-29 09:00","2023-11-29 14:00","취소","취소","연속"]
[449,"전북","군산","군산S/S CB 6100","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-01 09:00","2023-11-26 18:00","취소","취소","연속"]
[450,"전북","군산","군산S/S #65 BUS","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-01 09:00","2023-11-03 18:00","취소","취소","연속"]
[451,"전북","군산","군산S/S #1 Sh.C CB","군산S/S 170kV 장기사용 GIS 대체공사","군산-이리#1T/L, BUSTIE, PT BAY 대체","2023-11-01 09:00","2023-11-26 18:00","취소","취소","연속"]
[452,"전북","군산","군산서군산#2 T/L","군산P/O 차단기 보통점검공사","군산S/S 군산-서군산#2T/L GIS 보통점검","2023-11-29 09:00","2023-11-29 18:00","취소","취소","연속"]
[453,"전북","군산","내초SE열병합#2 T/L","내초S/S 154kV 내초-SE열병합#1T/L 차단기 보통점검","내초S/S 154kV 내초-SE열병합#1T/L 차단기 보통점검","2023-11-15 09:00","2023-11-15 18:00","2023-11-15 09:00","2023-11-15 18:00","연속"]
[454,"전북","군산","동군산장항#1 T/L","군산P/O 노후배전반 대체 등","- 동군산-장항#1T/L 보호반 대체(양단) - 효성제 베어링 발청분 교체(병행) - 170kV GIS 정밀점검공사(병행) - 동군산-장항#1T/L 차단기 주접점 이탈 관련 점검(병행) - SA혼용시스템 관련 제어케이블 이설(병행)","2023-11-14 09:00","2023-11-15 18:00","취소","취소","연속"]
[455,"전북","군산","비응군장#1 T/L","#1M.Tr 시험가압 및 앵글측정","#1M.Tr 증설분 무부하가압 및 앵글측정","2023-11-16 15:00","2023-11-17 15:00","2023-11-16 15:00","2023-11-17 15:00","연속"]
[456,"전북","군산","비응군장#2 T/L","직매식 지중송전선로 케이블 방식층 시험","직매구간 케이블 방식층 절연저항 측정 및 TDR 시험","2023-11-30 09:00","2023-11-30 18:00","취소","취소","연속"]
[457,"전북","군산","비응군장#1 T/L","직매식 지중송전선로 케이블 방식층 시험","직매구간 케이블 방식층 절연저항 측정 및 TDR 시험","2023-11-29 09:00","2023-11-29 18:00","취소","취소","연속"]
[458,"전북","군산","새만금비응#2 T/L","직매식 지중송전선로 케이블 방식층 시험","직매구간 케이블 방식층 절연저항 측정 및 TDR 시험","2023-11-16 09:00","2023-11-16 18:00","취소","취소","연속"]
[459,"전북","군산","새만금비응#1 T/L","직매식 지중송전선로 케이블 방식층 시험","직매구간 케이블 방식층 절연저항 측정 및 TDR 시험","2023-11-15 09:00","2023-11-15 18:00","취소","취소","연속"]
[460,"전북","군산","새만금소룡#2 T/L","직매식 지중송전선로 케이블 방식층 시험","직매구간 케이블 방식층 절연저항 측정 및 TDR 시험","2023-11-28 09:00","2023-11-28 18:00","2023-11-28 09:00","2023-11-28 18:00","연속"]
[461,"전북","군산","새만금소룡#1 T/L","직매식 지중송전선로 케이블 방식층 시험","직매구간 케이블 방식층 절연저항 측정 및 TDR 시험","2023-11-27 09:00","2023-11-27 18:00","2023-11-27 09:00","2023-11-27 18:00","연속"]
[462,"전북","군산","탄소이리#1 T/L","345kV 군산-새만금 등 8개T/L 추락방지장치 설치공사","□ 공사개요 ○ 설치 철탑 : 154kV 이리-탄소#1T/L No.1~63 (관형주 제외) ○ 추락방지장치 : 수평설치(51기)","2023-11-06 09:00","2023-11-10 18:00","취소","취소","연속"]
[463,"전북","군산","이리백산#2 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2023-11-27 08:00","2023-12-01 18:00","취소","취소","연속"]
[464,"전북","군산","탄소이리#2 T/L","345kV 군산-새만금 등 8개T/L 추락방지장치 설치공사","□ 공사개요 ○ 설치 철탑 : 154kV 이리-탄소#2T/L No.1~63 (관형주 제외) ○ 추락방지장치 : 수평설치(51기)","2023-11-13 09:00","2023-11-17 18:00","취소","취소","연속"]
[465,"전북","군산","이리백산#1 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2023-12-02 08:00","2023-12-09 18:00","취소","취소","연속"]
[466,"전북","군산","이리백산#2 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2023-12-10 08:00","2023-12-14 18:00","취소","취소","연속"]
[467,"전북","군산","팔봉왕궁#1 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2023-11-06 09:00","2023-11-10 18:00","취소","취소","연속"]
[468,"전북","군산","영등팔봉#2 T/L","군산P/O LA,CVT 보통점검공사","군산P/O LA,CVT 보통점검공사","2023-11-02 09:00","2023-11-02 18:00","취소","취소","연속"]
[469,"전북","군산","팔봉왕궁#2 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2023-11-13 09:00","2023-11-17 18:00","취소","취소","연속"]
[470,"전북","김제","담양김제 T/L","김제S/S 170kV 담양-김제T/L 보통점검공사","김제S/S 170kV 담양-김제T/L 보통점검공사","2023-11-01 09:00","2023-11-01 15:00","2023-11-01 09:00","2023-11-01 15:00","연속"]
[471,"전북","김제","남전주임실#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","신김제-동전주T/L 교차구간 안전이격거리 확보차 양회선 휴전","2023-11-13 08:00","2023-11-17 17:00","2023-11-10 07:00","2023-11-16 17:00","연속"]
[472,"전북","김제","남전주임실#1 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","신김제-동전주T/L 교차구간 안전이격거리 확보차 양회선 휴전","2023-11-13 08:00","2023-11-17 17:00","2023-11-10 07:00","2023-11-16 17:00","연속"]
[473,"전북","김제","백산김제#2 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2023-12-02 08:00","2023-12-09 18:00","취소","취소","연속"]
[474,"전북","김제","백산김제#1 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2023-11-27 08:00","2023-12-01 18:00","취소","취소","연속"]
[475,"전북","김제","백산김제#1 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2023-12-10 08:00","2023-12-14 18:00","취소","취소","연속"]
[476,"전북","김제","정공S/S SEC CB  60610","정공S/S 170kV #60-#61 SEC GIS 보통점검","정공S/S 170kV #60-#61 SEC GIS 보통점검","2023-11-10 09:00","2023-11-10 18:00","2023-11-10 09:00","2023-11-10 18:00","연속"]
[477,"전북","김제","신김제정공#1 T/L","정공S/S 170kV 신김제-정공#1T/L 정밀점검공사","정공S/S 170kV 신김제-정공#1T/L 정밀점검공사","2023-11-20 09:00","2023-11-21 18:00","취소","취소","연속"]
[478,"전북","김제","정공정주#2 T/L","정공S/S 170kV 정공-정주#2T/L 보통점검공사","정공S/S 170kV 정공-정주#2T/L 보통점검공사","2023-11-28 09:00","2023-11-28 15:00","취소","취소","연속"]
[479,"전북","김제","정공S/S SEC CB 65660","정공S/S 170kV #65-#66 SEC GIS 보통점검","정공S/S 170kV #65-#66 SEC GIS 보통점검","2023-11-09 09:00","2023-11-09 18:00","2023-11-09 09:00","2023-11-09 18:00","연속"]
[480,"전북","김제","정공S/S CB 6100","정공S/S 170kV 6100 GIS 보통점검","정공S/S 170kV 6100 GIS 보통점검","2023-11-07 09:00","2023-11-07 18:00","2023-11-07 09:00","2023-11-07 18:00","연속"]
[481,"전북","김제","정공담양 T/L","정공S/S 정공-담양T/L 154kV LA 대체","정공S/S 정공-담양T/L 154kV LA 대체","2023-11-30 09:00","2023-11-30 18:00","취소","취소","연속"]
[482,"전북","김제","정공S/S CB 6200","정공S/S 170kV 6200 GIS 보통점검","정공S/S 170kV 6200 GIS 보통점검","2023-11-08 09:00","2023-11-08 18:00","2023-11-08 09:00","2023-11-08 18:00","연속"]
[483,"전북","김제","정공칠보HP T/L","154kV 칠보분기T/L 추락방지시설 설치공사","-154kV 칠보분기T/L 추락방지시설 설치(4기) -조류착지방지장치 설치(4기)","2023-11-28 07:30","2023-11-29 18:00","2023-11-28 07:30","2023-11-29 18:00","연속"]
[484,"전북","김제","김제칠보HP T/L","154kV 칠보분기T/L 추락방지시설 설치공사","-154kV 칠보분기T/L 추락방지시설 설치(4기) -조류착지방지장치 설치(4기)","2023-11-30 07:30","2023-12-01 18:00","2023-11-30 07:30","2023-12-01 18:00","연속"]
[485,"전북","직할","남원임실#2 T/L","'22~'23년 전북직할 송전협력회사 총액공사","○ 수평추락방지장치 설치 : No.11","2023-11-09 09:00","2023-11-09 18:00","2023-11-09 09:00","2023-11-09 18:00","연속"]
[486,"전북","직할","신김제동전주#1 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","No.33∼36 전력선 연긴선","2023-11-20 08:00","2023-11-23 17:00","2023-11-17 07:00","2023-11-20 17:00","연속"]
[487,"전북","직할","신김제동전주#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","No.33∼36 전력선 연긴선","2023-11-24 08:00","2023-11-27 17:00","2023-11-21 07:00","2023-11-24 17:00","연속"]
[488,"전북","직할","북전주용담수력 T/L","'22~'23년 전북직할 송전협력회사 총액공사","○ 항공장애표시구 설치 : No.46~47 등 20경간","2023-11-20 09:00","2023-11-22 18:00","취소","취소","매일"]
[489,"전북","직할","전주서곡#2 T/L","전주-서곡#2T/L 보호반대체(보통점검 병행)","전주-서곡#2T/L 보호반대체(보통점검 병행)","2023-11-11 09:00","2023-11-12 18:00","취소","취소","연속"]
[490,"광주전남","강진","남창해남CS#1 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","남창S/S 남창-해남CS#1T/L GIS 차단기 조작시험","2023-11-06 09:00","2023-11-06 18:00","취소","취소","연속"]
[491,"광주전남","강진","삼호화원#2 T/L","154kV 삼호-화원 #2T/L EBA 절연유채유","○ 154kV 삼호-화원 #1T/L No.1 C/T EBA 절연유채유 - EBA 절연유 가스분석","2023-11-07 09:00","2023-11-07 18:00","2023-11-07 06:00","2023-11-07 11:00","연속"]
[492,"광주전남","강진","삼호화원#1 T/L","154kV 삼호-화원 #1T/L EBA 절연유채유 및 집합반 교체","○ 154kV 삼호-화원 #1T/L No.1 C/T EBA 절연유채유 및 집합반 교체 - EBA 절연유 가스분석 - 낙뢰소손으로 인한 집합반 CT 및 케이블교체","2023-11-06 09:00","2023-11-06 18:00","2023-11-08 06:00","2023-11-08 11:00","연속"]
[493,"광주전남","강진","화원진도#2 T/L","2022~23년 강진전력지사 변전협력회사 총액공사","진도S/S 화원-진도#2T/L GIS 차단기 조작시험","2023-11-01 09:00","2023-11-01 18:00","취소","취소","연속"]
[494,"광주전남","강진","해남해남CS#1 T/L","2022~23년 강진전력지사 송전 협력회사 총액공사","수직, 수평 추락방지장치 설치","2023-11-06 07:00","2023-11-17 18:00","취소","취소","매일"]
[495,"광주전남","강진","남창해남CS#1 T/L","2022~23년 강진전력지사 송전협력회사 총액공사","수직, 수평 추락방지장치 설치","2023-11-06 07:00","2023-11-08 18:00","취소","취소","매일"]
[496,"광주전남","강진","화원진도#2 T/L","22~23년 목포 송전 협력회사 총액공사(추락방지)","154kV 화원-진도#2T/L 수평추락방지장치 설치 1~39호","2023-11-27 07:00","2023-11-30 18:00","취소","취소","매일"]
[497,"광주전남","광주","계림S/S CB 6100","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-11-06 09:00","2023-12-08 18:00","취소","취소","연속"]
[498,"광주전남","광주","계림남광주 T/L","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교채공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-11-06 09:00","2023-12-08 18:00","취소","취소","연속"]
[499,"광주전남","광주","계림충장#2 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차) - BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2 T/L 교체","2023-11-06 09:00","2023-12-08 18:00","취소","취소","연속"]
[500,"광주전남","광주","계림승주#1 T/L","계림S/S 154kV 이하 장기사용 GIS 교체공사(1차)","-BUS TIE, #1M.Tr 1차, 계림남광주, 계림충장#2T/L #60BUS 신설분 무부하 가압","2023-11-17 13:00","2023-11-18 13:00","취소","취소","연속"]
[501,"광주전남","광주","북광주계림#1 T/L","22~23년 광주전력지사 변전협력회사 총액공사","계림S/S 북광주-계림#1T/L 170kV GIS 에어누기 조치 - Air Tank 부 에어누기 조치 (볼트조임, 오링 교체 등)","2023-11-30 09:00","2023-11-30 18:00","2023-11-30 09:00","2023-11-30 18:00","연속"]
[502,"광주전남","광주","신광주S/S #66 BUS","154kV 신광주-일곡T/L C/T이설공사 무부하가압","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-11-05 13:00","2023-11-05 18:00","2023-11-12 13:00","2023-11-12 18:00","연속"]
[503,"광주전남","광주","신광주순창#2 T/L","154kV 신광주-일곡T/L C/T이설공사 무부하가압","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-11-05 13:00","2023-11-05 18:00","2023-11-12 13:00","2023-11-12 18:00","연속"]
[504,"광주전남","광주","신광주일곡#1 T/L","154kV 신광주-일곡T/L C/T이설공사","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-11-11 07:00","2023-11-12 18:00","2023-11-18 07:00","2023-11-19 18:00","연속"]
[505,"광주전남","광주","신광주S/S #65 BUS","154kV 신광주-일곡T/L C/T이설공사 무부하가압","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-11-12 13:00","2023-11-12 18:00","2023-11-19 13:00","2023-11-19 18:00","연속"]
[506,"광주전남","광주","신광주일곡#2 T/L","154kV 신광주-일곡T/L C/T이설공사","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-11-04 07:00","2023-11-05 18:00","2023-11-11 07:00","2023-11-12 18:00","연속"]
[507,"광주전남","광주","신광주계림#2 T/L","신광주-계림#2T/L 장기사용 보호반 교체","신광주, 계림S/S 신광주-계림#2T/L 장기사용 보호반 교체, 즉시가압불가","2023-11-27 09:00","2023-12-01 18:00","취소","취소","연속"]
[508,"광주전남","광주","신광주계림#2 T/L","'22~23년 광주 변전협력회사 총액공사","신광주, 계림S/S 신광주-계림#2T/L PNL 대체","2023-11-27 09:00","2023-12-01 18:00","취소","취소","연속"]
[509,"광주전남","광주","신광주순창#1 T/L","154kV 신광주-일곡T/L C/T이설공사 무부하가압","ㅇ 사유 : 기설 송전선로 교육시설 인접으로 광주시 지중화 요청 ㅇ 공사내용 - 철탑이설 : [신설] 케이블타워 1기, [철거] 케이블타워 1기, 관형지지물 2기 - 임시선로 구성 : 임시철탑 3기, ACSR 410㎟X2B","2023-11-12 13:00","2023-11-12 18:00","2023-11-19 13:00","2023-11-19 18:00","연속"]
[510,"광주전남","광주","신화순매월#2 T/L","'22~23년 광주 변전협력회사 총액공사","신화순-매월#2T/L LA 보통점검","2023-11-07 14:00","2023-11-07 18:00","취소","취소","연속"]
[511,"광주전남","광주","신화순매월#1 T/L","'22~23년 광주 변전협력회사 총액공사","신화순-매월#1T/L LA 보통점검","2023-11-07 09:00","2023-11-07 14:00","취소","취소","연속"]
[512,"광주전남","광주","하남장성#1 T/L","'22~23년 광주 변전협력회사 총액공사","하남-장성#1T/L LA 보통점검","2023-11-14 09:00","2023-11-14 14:00","취소","취소","연속"]
[513,"광주전남","광주","하남장성#1 T/L","154KV 장성-영광T/L 선종교체공사(NO.1～NO.126)","※No.15~21 4회선 구간 관련으로 하남-장성#1T/L 안전휴전 시행 ㅇ구간 : 154kV 장성-영광 #2T/L No.1~126 ㅇ경간 : 35.9km 전선교체 ㅇ시공사 : 청보전설(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 430SQ로 전량교체)","2023-11-01 08:00","2023-11-10 18:00","2023-11-29 08:00","2023-12-08 18:00","연속"]
[514,"광주전남","광주","장성영광#2 T/L","154KV 장성-영광T/L 선종교체공사(NO.1～NO.126)","ㅇ구간 : 154kV 장성-영광 #2T/L No.1~126 ㅇ경간 : 35.9km 전선교체 ㅇ시공사 : 청보전설(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 430SQ로 전량교체)","2023-11-01 08:00","2023-12-15 18:00","2023-11-01 08:00","2023-12-15 18:00","연속"]
[515,"광주전남","광주","하남장성#2 T/L","154KV 장성-영광T/L 선종교체공사(NO.1～NO.126)","※No.15~21 4회선 구간 관련으로 하남-장성#1T/L 안전휴전 시행 ※No.1~2, 15~21 장성-영광T/L과 하남-장성T/L 양회선 교차로 안전휴전 필요 ㅇ : 154kV 장성-영광 #2T/L No.1~126 ㅇ경간 : 35.9km 전선교체 ㅇ시공사 : 청보전설(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 430SQ로 전량교체)","2023-11-03 08:00","2023-11-07 18:00","2023-12-01 08:00","2023-12-06 18:00","연속"]
[516,"광주전남","광주","하남장성#2 T/L","'22~23년 광주 변전협력회사 총액공사","하남-장성#2T/L LA 보통점검","2023-11-14 14:00","2023-11-14 18:00","취소","취소","연속"]
[517,"광주전남","목포","무한햇빛개폐소S/S 무안햇빛발전소 T/L CB","23년도 목포전력지사 변전협력회사 총액공사","무안햇빛발전소T/L GIS 하자점검 20분내 즉시가압 가능","2023-11-14 09:00","2023-11-14 18:00","2023-11-14 09:00","2023-11-14 18:00","연속"]
[518,"광주전남","목포","무안햇빛개폐소S/S 무안솔라파크 T/L CB","23년도 목포전력지사 변전협력회사 총액공사","무안솔라파크T/L GIS 하자점검 20분내 즉시가압 가능","2023-11-13 09:00","2023-11-13 18:00","2023-11-13 09:00","2023-11-13 18:00","연속"]
[519,"광주전남","목포","엄다무안햇빛#2 T/L","2022~23년 광주전남본부 직할 지중송전협력회사 총액공사","154kV 엄다-무안햇빛T/L 장기사용 지중피뢰기 교체공사","2023-11-23 08:00","2023-11-24 18:00","2023-11-23 08:00","2023-11-24 18:00","연속"]
[520,"광주전남","목포","엄다무안햇빛#1 T/L","2022~23년 광주전남본부 직할 지중송전협력회사 총액공사","154kV 엄다-무안햇빛T/L 장기사용 지중피뢰기 교체공사","2023-11-21 08:00","2023-11-22 18:00","2023-11-21 08:00","2023-11-22 18:00","연속"]
[521,"광주전남","목포","목포북항#1 T/L","북항S/S 154kV 장기사용 GIS 교체공사(3차)","목포-북항#1T/L GIS 교체(즉시가압불가)","2023-11-06 09:00","2023-12-08 18:00","2023-11-06 09:00","2023-12-08 18:00","연속"]
[522,"광주전남","목포","고창영광 T/L","154kV 영광-홍농 등 4개T/L 선종교체공사","1. 공사명 : 154kV 영광-홍농 등 4개T/L 선종교체공사 2. 공사내용 ○ 23.11.01~11.28 추락방지장치 설치 (목포전력지사 송전팀) ○ 23.11.01~11.28 (4회선 상단) 장성-영광#2 선종교체공사를 위한 안전휴전 (연속휴전_송전운영부)","2023-11-01 07:00","2023-11-28 18:00","2023-11-01 07:00","2023-11-28 18:00","연속"]
[523,"광주전남","목포","고창영광 T/L","154KV 장성-영광T/L 선종교체공사(NO.1～NO.126)","※No.126 4회선 구간 관련으로 하남-장성#1T/L 안전휴전 시행 ㅇ : 154kV 장성-영광 #2T/L No.1~126 ㅇ경간 : 35.9km 전선교체 ㅇ시공사 : 청보전설(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 430SQ로 전량교체)","2023-11-01 08:00","2023-11-01 18:00","취소","취소","연속"]
[524,"광주전남","순천","장흥벌교 T/L","22~23년 철탑 추락방지장치 설치공사","공사명 : 22~23년 철탑 추락방지장치 설치공사 공사구간 : 장흥-벌교 T/L 1~121","2023-11-30 07:00","2023-12-14 18:00","2023-11-30 07:00","2023-12-14 18:00","매일"]
[525,"광주전남","순천","소라서순천#2 T/L","2022~23년 순천전력지사 지중송전협력회사 총액공사","154kV 소라-서순천T/L, M/H #3~#5 병행지선 설치작업 안전확보 차 (즉시가압 가능)","2023-11-16 14:00","2023-11-16 16:00","2023-11-16 14:00","2023-11-16 16:00","연속"]
[526,"광주전남","순천","서순천주암HP T/L","154kV 승주-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.13~25호, 13기","2023-11-13 07:00","2023-11-14 18:00","2023-11-13 07:00","2023-11-14 18:00","매일"]
[527,"광주전남","순천","소라서순천#1 T/L","2022~23년 순천전력지사 지중송전협력회사 총액공사","154kV 소라-서순천T/L, M/H #3~#5 병행지선 설치작업 안전확보 차 (즉시가압 가능)","2023-11-16 12:00","2023-11-16 14:00","2023-11-16 12:00","2023-11-16 14:00","연속"]
[528,"광주전남","순천","계림승주#1 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.2~9호, 8기(4회선)","2023-11-06 07:00","2023-11-06 18:00","2023-11-06 07:00","2023-11-06 18:00","매일"]
[529,"광주전남","순천","계림승주#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","GIS 보통점검 및 상시여자 보조계전기 교체","2023-11-10 09:00","2023-11-10 18:00","취소","취소","연속"]
[530,"광주전남","순천","승주주암HP T/L","154kV 승주-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.26~96호, 71기","2023-11-15 07:00","2023-11-21 18:00","2023-11-15 07:00","2023-11-21 18:00","매일"]
[531,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.1~171호, 87기","2023-11-03 07:00","2023-11-10 18:00","2023-11-03 07:00","2023-11-10 18:00","매일"]
[532,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치 - 대 상 : No.13~96호, 82기","2023-11-22 07:00","2023-11-30 18:00","2023-11-22 07:00","2023-11-30 18:00","매일"]
[533,"광주전남","순천","율촌여수산단#1 T/L","2022~23년 순천전력지사 지중송전협력회사 총액공사","154kV 율촌-여수산단T/L, M/H #6~#8 병행지선 설치작업 안전확보 차 (즉시가압 가능)","2023-11-15 12:00","2023-11-15 14:00","취소","취소","연속"]
[534,"광주전남","순천","율촌여수산단#2 T/L","2022~23년 순천전력지사 지중송전협력회사 총액공사","154kV 율촌-여수산단T/L, M/H #6~#8 병행지선 설치작업 안전확보 차 (즉시가압 가능)","2023-11-15 14:00","2023-11-15 16:00","취소","취소","연속"]
[535,"광주전남","순천","여수T/P SEC CB 60610","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-11-30 15:20","2023-11-30 15:40","2023-11-30 15:20","2023-11-30 15:40","연속"]
[536,"광주전남","순천","여수T/P SEC CB 65660","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-11-30 15:00","2023-11-30 15:20","2023-11-30 15:00","2023-11-30 15:20","연속"]
[537,"광주전남","순천","여수T/P #65 BUS","22-23년 순천전력지사 변전협력회사 총액공사","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","2023-11-28 09:00","2023-11-29 18:00","취소","취소","연속"]
[538,"광주전남","순천","여수TP용성#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 여수TP-용성#2T/L GIS 보통점검 및 보조계전기 교체 용성S/S 여수TP-용성#2T/L GIS 보통점검, LA(A, B, C) 보통점검 및 상시여자 보조계전기 교체","2023-11-27 09:00","2023-11-27 18:00","취소","취소","연속"]
[539,"광주전남","순천","여수T/P CB 6100","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-11-23 15:40","2023-11-23 16:00","2023-11-23 15:40","2023-11-23 16:00","연속"]
[540,"광주전남","순천","여수T/P SEC CB 60610","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-11-23 15:20","2023-11-23 15:40","2023-11-23 15:20","2023-11-23 15:40","연속"]
[541,"광주전남","순천","여수T/P SEC CB 65660","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-11-23 15:00","2023-11-23 15:20","2023-11-23 15:00","2023-11-23 15:20","연속"]
[542,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP-여수TPT/L No.1 안전이격확보공사 관련 하자처리","○ #1, 2T/L S/T, 1, 2호 애자련 롯트 배열 불량 ○ #1, 2T/L 가공지선 및 OPGW 이도불량","2023-11-22 09:00","2023-11-22 18:00","취소","취소","연속"]
[543,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP-여수TPT/L No.1 안전이격확보공사 관련 하자처리","○ #1, 2T/L S/T, 1, 2호 애자련 롯트 배열 불량 ○ #1, 2T/L 가공지선 및 OPGW 이도불량 ○ #1T/L 상, 중, 하단 전력선 소도체간 불평형 ○ #1T/L 상, 중, 하단 피뢰기 설치간격 불량","2023-11-20 09:00","2023-11-21 18:00","취소","취소","매일"]
[544,"광주전남","순천","여수TP용성#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여수화력S/S 여수TP-용성#1T/L GIS 보통점검 및 보조계전기 교체 용성S/S 여수TP-용성#1T/L GIS 보통점검, LA(A, B, C) 보통점검 및 상시여자 보조계전기 교체 및 압력계 교체(즉시가압 불가)","2023-11-20 09:00","2023-11-21 18:00","취소","취소","연속"]
[545,"광주전남","순천","여수TP여천#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","GIS 보통점검 및 불량 43PDA 교체","2023-11-18 10:00","2023-11-18 14:00","취소","취소","연속"]
[546,"광주전남","순천","호남TP여수TP#1 T/L","순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검","2023-11-06 09:00","2023-11-07 18:00","취소","취소","연속"]
[547,"광주전남","순천","호남TP여수TP#2 T/L","순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검","2023-11-08 09:00","2023-11-09 18:00","취소","취소","연속"]
[548,"광주전남","순천","여수TP화치#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","TL 보호반(즉시가압 불가) 및 AC,DC 분전반 교체(안전이격)","2023-11-06 09:00","2023-11-10 18:00","2023-11-13 09:00","2023-11-17 18:00","연속"]
[549,"광주전남","순천","여수TP용성#1 T/L","'2022~23년 가공송전 협력회사 총액공사","SB댐퍼 설치 (여수TP-용성#1 T/L) : 5기","2023-11-02 08:00","2023-11-02 18:00","취소","취소","연속"]
[550,"광주전남","순천","여수T/P CB 6200","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2023-11-30 15:40","2023-11-30 16:00","2023-11-30 15:40","2023-11-30 16:00","연속"]
[551,"광주전남","순천","여천호남TP#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","GIS 차단기 조작시험","2023-11-02 09:00","2023-11-02 14:00","취소","취소","연속"]
[552,"광주전남","순천","여천호남TP#2 T/L","154kV 호남TP-여수TPT/L No.1 안전이격확보공사 관련 하자처리","○ #1, 2T/L S/T, 1, 2호 애자련 롯트 배열 불량 ○ #1, 2T/L 가공지선 및 OPGW 이도불량","2023-11-22 09:00","2023-11-22 18:00","취소","취소","연속"]
[553,"광주전남","순천","여천호남TP#1 T/L","154kV 호남TP-여수TPT/L No.1 안전이격확보공사 관련 하자처리","○ #1, 2T/L S/T, 1, 2호 애자련 롯트 배열 불량 ○ #1, 2T/L 가공지선 및 OPGW 이도불량 ○ #1T/L 상, 중, 하단 전력선 소도체간 불평형 ○ #1T/L 상, 중, 하단 피뢰기 설치간격 불량","2023-11-20 09:00","2023-11-21 18:00","취소","취소","매일"]
[554,"광주전남","순천","여수TP여천#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","여천S/S 여수TP-여천#2T/L GIS 타임측정","2023-11-09 09:00","2023-11-09 18:00","취소","취소","연속"]
[555,"광주전남","순천","여천호남TP#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","GIS 차단기 조작시험","2023-11-02 14:00","2023-11-02 18:00","취소","취소","연속"]
[556,"광주전남","순천","용성여수산단#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","#1DS 가스누기 해소공사","2023-11-22 09:00","2023-11-23 18:00","취소","취소","연속"]
[557,"광주전남","순천","용성여수산단#2 T/L","'2022~23년 가공송전 협력회사 총액공사","SB댐퍼 설치 (여수TP-용성#1 T/L) : 5기","2023-11-02 08:00","2023-11-02 18:00","취소","취소","연속"]
[558,"광주전남","순천","여수TP용성#2 T/L","'2022~23년 가공송전 협력회사 총액공사","SB댐퍼 설치 (여수TP-용성#2 T/L) : 5기","2023-11-03 08:00","2023-11-03 18:00","취소","취소","연속"]
[559,"광주전남","순천","용성여수산단#1 T/L","'2022~23년 가공송전 협력회사 총액공사","SB댐퍼 설치 (여수TP-용성#2 T/L) : 5기","2023-11-03 08:00","2023-11-03 18:00","취소","취소","연속"]
[560,"광주전남","순천","율촌화치#2 T/L","순천전력지사 170kV GIS 정밀점검공사","GIS 유압유 레벨 조정","2023-11-01 10:00","2023-11-01 14:00","취소","취소","연속"]
[561,"광주전남","순천","순천율촌#1 T/L","154kV 순천-승주 등 2개T/L 피뢰기 설치공사","○순천-율촌 #1 T/L 피뢰기 설치 : 1~69호(24기)","2023-11-20 08:00","2023-11-22 18:00","2023-11-20 08:00","2023-11-22 18:00","매일"]
[562,"광주전남","순천","율촌여수산단#2 T/L","가공송전 위탁공사 정밀점검(율촌여수산단#2 T/L) : 51기","가공송전 위탁공사 정밀점검(율촌여수산단#2 T/L) : 51기","2023-11-13 09:00","2023-11-16 18:00","취소","취소","매일"]
[563,"광주전남","순천","율촌여수산단#1 T/L","가공송전 위탁공사 정밀점검(율촌여수산단#1 T/L)","가공송전 위탁공사 정밀점검(율촌여수산단#1 T/L) : 51기","2023-11-06 09:00","2023-11-09 18:00","취소","취소","매일"]
[564,"광주전남","순천","순천율촌#2 T/L","순천전력지사 170kV GIS 정밀점검공사","GIS 정밀점검","2023-11-02 09:00","2023-11-03 18:00","취소","취소","연속"]
[565,"광주전남","순천","호남TP여수TP#1 T/L","22-23년 순천전력지사 변전협력회사 총액공사","LA 대체","2023-11-07 09:00","2023-11-07 18:00","취소","취소","연속"]
[566,"광주전남","순천","호남TP여수TP#2 T/L","22-23년 순천전력지사 변전협력회사 총액공사","LA 대체","2023-11-08 09:00","2023-11-08 18:00","취소","취소","연속"]
[567,"광주전남","직할","남광주금천#1 T/L","2022~23년 광주전남본부 직할 지중송전협력회사 총액공사","154kV 남광주-금천T/L, M/H #3~#5 , 154kV 금천분기T/L(M/H#3~C/T) 병행지선 설치작업 안전확보 차(즉시가압 가능) 11/15 12:00 ~ 14:00 11/16 12:00 ~ 14:00","2023-11-15 12:00","2023-11-16 14:00","2023-11-15 11:00","2023-11-16 13:00","매일"]
[568,"광주전남","직할","남광주금천#2 T/L","2022~23년 광주전남본부 직할 지중송전협력회사 총액공사","154kV 남광주-금천T/L, M/H #3~#5 , 154kV 금천분기T/L(M/H#3~C/T) 병행지선 설치작업 안전확보 차(즉시가압 가능) 11/15 14:00 ~ 16:00 11/16 14:00 ~ 16:00","2023-11-15 14:00","2023-11-16 16:00","2023-11-15 13:00","2023-11-16 15:00","매일"]
[569,"광주전남","직할","나주금천#2 T/L","22~23년 철탑 추락방지장치 설치공사","공사명 : 22~23년 철탑 추락방지장치 설치공사 공사구간 : 나주-영암 T/L 1~82","2023-11-16 07:00","2023-11-16 18:00","취소","취소","연속"]
[570,"광주전남","직할","나주금천#1 T/L","2022~23년 광주전남본부 직할 지중송전협력회사 총액공사","154kV 금천분기T/L(M/H#3~C/T) 병행지선 설치작업 안전확보 차 (즉시가압 가능)","2023-11-16 14:00","2023-11-16 16:00","2023-11-16 13:00","2023-11-16 15:00","연속"]
[571,"광주전남","직할","나주금천#2 T/L","2022~23년 광주전남본부 직할 지중송전협력회사 총액공사","154kV 금천분기T/L(M/H#3~C/T) 병행지선 설치작업 안전확보 차 (즉시가압 가능)","2023-11-16 12:00","2023-11-16 14:00","2023-11-16 11:00","2023-11-16 13:00","연속"]
[572,"광주전남","직할","농성화정#1 T/L","'23년 직할 170kV GIS 정밀 및 보통점검 공사","○ 농성S/S 농성-화정 #1,2T/L 170kV GIS 보통점검 - 휴일작업 없음 ○ 화정S/S 농성-화정#1T/L 170kV GIS 보통점검","2023-11-01 09:00","2023-11-01 14:00","2023-11-20 09:00","2023-11-20 14:00","연속"]
[573,"광주전남","직할","농성화정#2 T/L","'23년 직할 170kV GIS 정밀 및 보통점검 공사","○ 농성S/S 농성-화정 #1,2T/L 170kV GIS 보통점검 - 휴일작업 없음","2023-11-01 14:00","2023-11-01 18:00","2023-11-21 09:00","2023-11-21 14:00","연속"]
[574,"광주전남","직할","비아하남#2 T/L","154KV 장성-영광T/L 선종교체공사(NO.1～NO.126)","※고려시멘트T/L 횡단 구간(5~6, 9~10) 관련으로 T분기 분리 시행 ㅇ구간 : 154kV 장성-영광 #2T/L No.1~126 ㅇ경간 : 35.9km 전선교체 ㅇ시공사 : 청보전설(주) ㅇ작업내용 : 용량증대 전선교체(ASCC 430SQ로 전량교체)","2023-11-03 08:00","2023-11-05 18:00","취소","취소","연속"]
[575,"광주전남","직할","수완흑석#2 T/L","2022~23년 광주전남본부 직할 지중송전협력회사 총액공사","154kV 수완-흑석T/L, M/H #6~#7 병행지선 설치작업 안전확보 차 (즉시가압 가능)","2023-11-14 14:00","2023-11-14 16:00","2023-11-14 14:00","2023-11-14 16:00","연속"]
[576,"광주전남","직할","수완흑석#1 T/L","2022~23년 광주전남본부 직할 지중송전협력회사 총액공사","154kV 수완-흑석T/L, M/H #6~#7 병행지선 설치작업 안전확보 차 (즉시가압 가능)","2023-11-14 12:00","2023-11-14 14:00","2023-11-14 12:00","2023-11-14 14:00","연속"]
[577,"광주전남","직할","농성화정#1 T/L","23년 직할 170kV GIS 정밀 및 보통점검 공사 ","○ 농성S/S 농성-화정 #1,2T/L 170kV GIS 보통점검\n- 휴일작업 없음\n○ 농성-화정#1T/L 송전선로 보호반 임시점검\n- 후비보호 COM Fail 해소 ","2023-11-01 09:00","2023-11-01 14:00","취소","취소","연속"]
[578,"광주전남","직할","농성화정#2 T/L","23년 직할 170kV GIS 정밀 및 보통점검 공사 ","○ 농성S/S 농성-화정 #1,2T/L 170kV GIS 보통점검\n- 휴일작업 없음\n○ 농성-화정#1T/L 송전선로 보호반 임시점검\n- 후비보호 COM Fail 해소 ","2023-11-01 14:00","2023-11-01 18:00","취소","취소","연속"]
[579,"대구","경산","경산자인#1 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치공사(안전확보)","2023-11-21 07:30","2023-11-24 17:00","2023-11-21 07:30","2023-11-24 17:00","연속"]
[580,"대구","경산","경산자인#2 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","(안전확보)수평 추락방지장치 설치공사","2023-11-21 07:30","2023-11-24 17:00","2023-11-21 07:30","2023-11-24 17:00","연속"]
[581,"대구","경산","경산자인#1 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","(안전확보)수평 추락방지장치 설치공사","2023-11-27 07:30","2023-12-01 18:00","2023-11-27 07:30","2023-12-01 18:00","연속"]
[582,"대구","경산","금호아화#1 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","(안전확보) 철탑추락방지장치 설치 - 수평 - 작업구간 : No.1~58","2023-11-09 07:00","2023-11-17 18:00","2023-11-09 07:00","2023-11-17 18:00","연속"]
[583,"대구","경산","아화영천#1 T/L","154kV 아화-영천T/L 지장송전선로 이설공사(요청자시행)","No.34~39 임시철탑 설치 및 기설철탑 철거, 전력선 설치","2023-11-30 08:00","2023-12-02 18:00","2023-11-30 08:00","2023-12-02 18:00","연속"]
[584,"대구","경산","청도밀양#2 T/L","2022~23년 달성전력지사 가공송전협력회사 총액공사","폴리머 점퍼지지애자 교체공사(154kV 대구-청도#1T/L 병가선로)","2023-11-29 07:00","2023-11-30 18:00","2023-11-29 07:00","2023-11-30 18:00","연속"]
[585,"대구","경산","청도밀양#1 T/L","2022~23년 달성전력지사 가공송전협력회사 총액공사","폴리머 점퍼지지애자 교체공사(154kV 대구-청도#2T/L 병가선로)","2023-11-27 07:00","2023-11-28 18:00","2023-11-27 07:00","2023-11-28 18:00","연속"]
[586,"대구","달성","고령다산#1 T/L","2023년 가공송전 순시점검 위탁공사","154kV 고령-다산T/L 초기점검","2023-11-02 08:00","2023-11-02 14:00","2023-11-02 08:00","2023-11-02 14:00","연속"]
[587,"대구","달성","고령쌍림#1 T/L","2023년 가공송전 순시점검 위탁공사","(안전확보)154kV 고령-다산T/L 초기점검 병행선로 휴전","2023-11-02 08:00","2023-11-02 14:00","2023-11-02 08:00","2023-11-02 14:00","연속"]
[588,"대구","달성","고령다산#2 T/L","2023년 가공송전 순시점검 위탁공사","154kV 고령-다산T/L 초기점검","2023-11-03 08:00","2023-11-03 14:00","2023-11-03 08:00","2023-11-03 14:00","연속"]
[589,"대구","달성","고령서구지#2 T/L","[TEST]6179GIS 차단부 정밀점검","[TEST]6179GIS 차단부 정밀점검","2023-11-07 17:00","2023-11-07 18:00","2023-11-07 17:00","2023-11-07 18:00","연속"]
[590,"대구","달성","고령서구지#2 T/L","[TEST]6279GIS 차단부 정밀점검","[TEST]6279GIS 차단부 정밀점검","2023-11-09 17:00","2023-11-09 18:00","2023-11-09 17:00","2023-11-09 18:00","연속"]
[591,"대구","달성","고령논공#1 T/L","[TEST]#3Sh.C 자단기 정밀점검","[TEST]#3Sh.C 자단기 정밀점검","2023-11-02 17:00","2023-11-02 18:00","2023-11-02 17:00","2023-11-02 18:00","연속"]
[592,"대구","달성","고령쌍림#2 T/L","2023년 가공송전 순시점검 위탁공사","(안전확보)154kV 고령-다산T/L 초기점검 병행선로 휴전","2023-11-03 08:00","2023-11-03 14:00","2023-11-03 08:00","2023-11-03 14:00","연속"]
[593,"대구","달성","달서와룡#1 T/L","달서S/S 장기사용 170kV GIS 교체공사","달서S/S 장기사용 170kV GIS 교체공사","2023-11-13 09:00","2023-11-24 18:00","2023-11-13 09:00","2023-11-24 18:00","연속"]
[594,"대구","달성","대구자인#1 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","(안전확보)수평 추락방지장치 설치공사","2023-11-27 07:30","2023-12-01 18:00","2023-11-27 07:30","2023-12-01 18:00","연속"]
[595,"대구","달성","대구자인#1 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","(안전확보)수평 추락방지장치 설치공사","2023-11-16 07:30","2023-11-20 17:00","2023-11-17 07:30","2023-11-20 17:00","연속"]
[596,"대구","달성","대구자인#2 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","(안전확보)수평 추락방지장치 설치공사","2023-11-16 07:30","2023-11-20 17:00","2023-11-17 07:30","2023-11-20 17:00","연속"]
[597,"대구","달성","대구범물#2 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","(안전확보)수평 추락방지장치 설치공사","2023-11-10 07:30","2023-11-15 17:00","2023-11-10 07:30","2023-11-15 17:00","연속"]
[598,"대구","달성","대구범물#1 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","(안전확보)수평 추락방지장치 설치공사","2023-11-06 07:30","2023-11-09 17:00","2023-11-06 07:30","2023-11-09 17:00","연속"]
[599,"대구","달성","두류봉덕#1 T/L","GIS 차단기 동작특성시험","GIS 차단기 동작특성시험","2023-11-12 09:00","2023-11-12 11:00","2023-11-12 09:00","2023-11-12 11:00","연속"]
[600,"대구","달성","두류봉덕#2 T/L","GIS 차단기 동작특성시험","GIS 차단기 동작특성시험","2023-11-19 09:00","2023-11-19 11:00","2023-11-19 09:00","2023-11-19 11:00","연속"]
[601,"대구","달성","대구봉덕#1 T/L","GIS 차단기 동작특성시험","GIS 차단기 동작특성시험","2023-11-12 11:00","2023-11-12 16:00","2023-11-12 11:00","2023-11-12 16:00","연속"]
[602,"대구","달성","대구봉덕#2 T/L","GIS 차단기 동작특성시험","GIS 차단기 동작특성시험","2023-11-19 11:00","2023-11-19 16:00","2023-11-19 11:00","2023-11-19 16:00","연속"]
[603,"대구","달성","강창성서#2 T/L","154kV 성서S/S 지역난방 신규수용공사","○ 170kV GIS 무부하가압","2023-11-02 09:00","2023-11-03 18:00","2023-11-02 09:00","2023-11-03 18:00","연속"]
[604,"대구","달성","쌍림합천#2 T/L","변전소 외벽 보강공사","(안전확보)변전소 외벽 보강공사","2023-11-06 09:00","2023-11-17 18:00","취소","취소","연속"]
[605,"대구","달성","쌍림합천#1 T/L","변전소 외벽 보강공사","(안전확보)변전소 외벽 보강공사","2023-11-06 09:00","2023-12-01 18:00","취소","취소","연속"]
[606,"대구","달성","고령쌍림#1 T/L","변전소 외벽 보강공사","(안전확보)변전소 외벽 보강공사","2023-11-20 09:00","2023-12-15 18:00","취소","취소","연속"]
[607,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체(TEST선로)","○ #2BUS 무부하가압(2H)","2023-11-03 14:00","2023-11-03 16:00","2023-11-03 14:00","2023-11-03 16:00","연속"]
[608,"대구","직할","범물남대구#2 T/L","남대구S/S 154kV GIS 교체 및 증설공사","○ 170kV GIS(50kA 1,250A) M.Tr 및 T/L Bay 철거․설치 ○ 제어(광)케이블 포설 및 결선","2023-11-01 09:00","2023-11-23 16:00","2023-11-01 09:00","2023-11-23 16:00","연속"]
[609,"대구","직할","범물남대구#1 T/L","23-24년 대구본부 직할 지중송전 위탁정비공사","EBA절연유 채유(3상)","2023-11-04 09:00","2023-11-04 14:00","취소","취소","연속"]
[610,"대구","직할","범물남대구#2 T/L","23-24년 대구본부 직할 지중송전 위탁정비공사","EBA절연유 채유(3상)","2023-11-04 14:00","2023-11-04 18:00","취소","취소","연속"]
[611,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체(TEST선로)","○ #1BUS 무부하가압(24H)","2023-11-13 16:00","2023-11-14 16:00","2023-11-13 16:00","2023-11-14 16:00","연속"]
[612,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체(TEST선로)","○ #2BUS 무부하가압(24H)","2023-11-21 16:00","2023-11-22 16:00","2023-11-21 16:00","2023-11-22 16:00","연속"]
[613,"대구","직할","남대구동인#1 T/L","남대구S/S 154kV GIS 교체(TEST선로)","○ #1BUS 무부하가압(2H)","2023-11-23 14:00","2023-11-23 16:00","2023-11-23 14:00","2023-11-23 16:00","연속"]
[614,"대구","직할","동인내당#1 T/L","23-24년 대구본부 직할 지중송전 위탁정비공사","OF케이블 절연유 채유(15상)","2023-11-18 09:00","2023-11-18 18:00","2023-11-18 09:00","2023-11-18 18:00","연속"]
[615,"대구","직할","동인내당#2 T/L","23-24년 대구본부 직할 지중송전 위탁정비공사","OF케이블 절연유 채유(15상)","2023-11-19 09:00","2023-11-19 18:00","2023-11-19 09:00","2023-11-19 18:00","연속"]
[616,"대구","칠곡","관음구암#1 T/L","관음S/S 154kV GIS 대체공사(안전확보)","관음S/S 154kV GIS 대체공사(2차) -대상: 관음-구암#2, #2M.Tr 1차, SEC DS","2023-11-30 09:00","2023-12-01 18:00","취소","취소","연속"]
[617,"대구","칠곡","관음구암#1 T/L","관음S/S 154kV GIS 대체공사(안전확보)","관음S/S 154kV GIS 대체공사(2차) -대상: 관음-구암#2, #2M.Tr 1차, SEC DS","2023-11-20 09:00","2023-11-21 18:00","취소","취소","연속"]
[618,"대구","칠곡","관음구암#2 T/L","관음S/S 154kV GIS 대체공사","관음S/S 154kV GIS 대체공사(2차) -대상: 관음-구암#2, #2M.Tr 1차, SEC DS","2023-11-13 09:00","2023-12-15 18:00","2023-11-13 09:00","2023-12-15 18:00","연속"]
[619,"대구","칠곡","구암검단#1 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치공사","2023-11-05 07:30","2023-11-05 18:00","2023-11-05 07:30","2023-11-05 18:00","연속"]
[620,"대구","칠곡","구암검단#2 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치공사","2023-11-05 07:30","2023-11-05 18:00","2023-11-05 07:30","2023-11-05 18:00","연속"]
[621,"대구","칠곡","어모김천#1 T/L","154kV 김천S/S 현대화공사","○ 송전선로 인출변경","2023-11-08 08:00","2024-06-30 18:00","2023-11-08 08:00","2024-06-30 18:00","연속"]
[622,"대구","칠곡","북대구구암#2 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치공사 병가선로","2023-11-05 07:30","2023-11-05 18:00","2023-11-05 07:30","2023-11-05 18:00","연속"]
[623,"대구","칠곡","북대구구암#1 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치공사 병가선로","2023-11-05 07:30","2023-11-05 18:00","2023-11-05 07:30","2023-11-05 18:00","연속"]
[624,"대구","칠곡","칠곡인동#2 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치공사","2023-11-01 07:30","2023-11-01 17:00","2023-11-09 07:30","2023-11-09 17:00","연속"]
[625,"대구","칠곡","칠곡인동#1 T/L","2022~23년 대구직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치공사","2023-11-01 07:30","2023-11-01 17:00","2023-11-09 07:30","2023-11-09 17:00","연속"]
[626,"대구","포항","건천천북#1 T/L","154kV 건천-천북T/L 지장송전선로 이설공사","No.49~50 철탑 설치/철거, 전력선 임시이설","2023-11-04 08:00","2023-11-27 18:00","2023-10-30 08:00","2023-11-27 18:00","연속"]
[627,"대구","포항","건천천북#2 T/L","154kV 건천-천북T/L 지장송전선로 이설공사","No.49~50 철탑 설치/철거, 전력선 임시이설","2023-11-04 08:00","2023-11-27 18:00","2023-10-30 08:00","2023-11-27 18:00","연속"]
[628,"대구","포항","아화건천#2 T/L","2022-23년 경산전력지사 가공송전 협력회사 총액공사","(안전확보)철탑추락방지장치 설치-수평 - 작업구간 : No.1 ~ 51","2023-11-04 07:00","2023-11-11 18:00","취소","취소","연속"]
[629,"대구","포항","신포항대송#2 T/L","22~23년도 포항전력지사 변전총액공사","대송S/S 신포항-대송T#2T/L LA 대체","2023-11-09 09:00","2023-11-09 18:00","2023-11-09 09:00","2023-11-09 18:00","연속"]
[630,"경북","구미","남인동인동#1 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","[남인동S/S] - GIS 하자점검 - LA 초기점검 [인동S/S] - GIS 조작시험 - LA 교체","2023-11-10 09:00","2023-11-10 14:00","2023-11-10 09:00","2023-11-10 14:00","연속"]
[631,"경북","구미","남인동인동#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","[남인동S/S] - GIS 하자점검 - LA 초기점검 [인동S/S] - GIS 조작시험 - LA 교체","2023-11-10 14:00","2023-11-10 18:00","2023-11-10 14:00","2023-11-10 18:00","연속"]
[632,"경북","구미","동상주점촌#2 T/L","2022-23년도 구미전력지사 가공송전정비 협력회사 총액공사","154kV 동상주-점촌T/L 철탑 추락방지장치 설치(No.1, 3~66) 52기","2023-11-06 08:00","2023-11-17 17:00","2023-11-06 08:00","2023-11-17 17:00","연속"]
[633,"경북","구미","동상주점촌#1 T/L","2022-23년도 구미전력지사 가공송전정비 협력회사 총액공사","154kV 동상주-점촌T/L 철탑 추락방지장치 설치(No.1, 3~66) 52기","2023-11-06 08:00","2023-11-17 17:00","2023-11-06 08:00","2023-11-17 17:00","연속"]
[634,"경북","구미","남인동인동#2 T/L","2022-23년도 구미전력지사 가공송전정비 협력회사 총액공사","154kV 남인동-인동T/L 철탑 추락방지장치 설치공사(No.1~17, 19~36, 49)","2023-11-02 08:00","2023-11-08 17:00","2023-11-02 08:00","2023-11-08 17:00","매일"]
[635,"경북","구미","금전인동#2 T/L","2022-23년 구미전력지사 변전협력업체 총액공사","- LA 교체","2023-11-13 14:00","2023-11-13 18:00","취소","취소","연속"]
[636,"경북","영주","봉화울진 T/L","154kV 봉화분기T/L 수평 추락방지장치 설치공사","154kV 봉화분기T/L 수평 추락방지장치 설치공사","2023-11-29 08:00","2023-12-07 17:00","2023-11-29 08:00","2023-12-07 17:00","연속"]
[637,"경북","영주","봉화현종산풍력 T/L","154kV 봉화분기T/L 수평 추락방지장치 설치공사","154kV 봉화분기T/L 수평 추락방지장치 설치공사","2023-11-20 08:00","2023-11-28 17:00","2023-11-20 08:00","2023-11-28 17:00","연속"]
[638,"경북","영주","신영주영주#2 T/L","154kV 신영주-영주T/L 수평 추락방지장치 설치공사","154kV 신영주-영주T/L 수평 추락방지장치 설치공사","2023-11-05 08:00","2023-11-10 17:00","2023-11-05 08:00","2023-11-10 17:00","연속"]
[639,"경북","영주","예천점촌#2 T/L","2022-23년 영주전력지사 변전협력회사 총액공사","LA 대체 보호계전기 성능개선","2023-11-10 09:00","2023-11-10 18:00","2023-11-10 09:00","2023-11-10 18:00","연속"]
[640,"경북","영주","예천점촌#1 T/L","세니온제 보호계전기 성능개선","계전기 성능개선","2023-11-09 09:00","2023-11-09 18:00","2023-11-09 09:00","2023-11-09 18:00","연속"]
[641,"경북","직할","동안동임하HP T/L","154kV 진보-동안동T/L 건설공사","□ 목 적 : 154kV 진보, 동안동S/S 단일계통 해소 □ 위 치 : 경북 안동시, 청송군 □ 규 모 : 154kV ACSR 410㎟×B×2C×37.353㎞, 철탑 93기 □ 사업기간 : 2018년 7월 ~ 2024년 3월","2023-11-13 07:00","2023-11-15 18:00","2023-11-13 07:00","2023-11-15 18:00","연속"]
[642,"경북","직할","안동동안동#2 T/L","154kV 진보-동안동T/L 건설공사","□ 목 적 : 154kV 진보, 동안동S/S 단일계통 해소 □ 위 치 : 경북 안동시, 청송군 □ 규 모 : 154kV ACSR 410㎟×B×2C×37.353㎞, 철탑 93기 □ 사업기간 : 2018년 7월 ~ 2024년 3월","2023-11-13 07:00","2023-11-21 18:00","2023-11-13 07:00","2023-11-21 18:00","연속"]
[643,"경북","직할","안동동안동#1 T/L","154kV 진보-동안동T/L 건설공사","□ 목 적 : 154kV 진보, 동안동S/S 단일계통 해소 □ 위 치 : 경북 안동시, 청송군 □ 규 모 : 154kV ACSR 410㎟×B×2C×37.353㎞, 철탑 93기 □ 사업기간 : 2018년 7월 ~ 2024년 3월","2023-11-17 07:00","2024-02-10 18:00","2023-11-17 07:00","2024-02-10 18:00","연속"]
[644,"경북","직할","동안동임하HP T/L","154kV 진보-동안동T/L 건설공사","□ 목 적 : 154kV 진보, 동안동S/S 단일계통 해소 □ 위 치 : 경북 안동시, 청송군 □ 규 모 : 154kV ACSR 410㎟×B×2C×37.353㎞, 철탑 93기 □ 사업기간 : 2018년 7월 ~ 2024년 3월","2023-11-17 07:00","2023-11-21 18:00","2023-11-17 07:00","2023-11-21 18:00","연속"]
[645,"경북","직할","안동동안동#2 T/L","동안동S/S 154kV SW 증설 및 GIS 교체공사","154kV GIS 2CCT 교체 - #2M.Tr, 동안동-임하HP T/L(동안동-진보#2), PT&ES","2023-11-22 09:00","2023-11-23 18:00","2023-11-22 09:00","2023-11-23 18:00","연속"]
[646,"경북","직할","안동동안동#2 T/L","동안동S/S 154kV SW 증설 및 GIS 교체공사","154kV GIS 2CCT 교체 - #2M.Tr, 동안동-임하HP T/L(동안동-진보#2), PT&ES","2023-11-29 09:00","2023-11-30 18:00","2023-11-29 09:00","2023-11-30 18:00","연속"]
[647,"경북","직할","안동동안동#1 T/L","154kV 진보-동안동T/L 건설공사","□ 목 적 : 154kV 진보, 동안동S/S 단일계통 해소 □ 위 치 : 경북 안동시, 청송군 □ 규 모 : 154kV ACSR 410㎟×B×2C×37.353㎞, 철탑 93기 □ 사업기간 : 2018년 7월 ~ 2024년 3월","2023-11-13 07:00","2023-11-15 18:00","2023-11-13 07:00","2023-11-15 18:00","연속"]
[648,"경북","직할","현종산풍력평해#1 T/L","22-23년 경북직할 송전협력회사 총액공사","154kV 현종산풍력-평해T/L 수평 추락방지장치 및 고정형 폴리머 설치","2023-11-22 08:00","2023-11-30 18:00","2023-11-22 08:00","2023-11-30 18:00","연속"]
[649,"부산울산","동부산","구서노포#2 T/L","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ #2BUS 시험가압(24Hr)","2023-11-24 18:00","2023-11-25 18:00","2023-11-23 15:00","2023-11-23 18:00","연속"]
[650,"부산울산","동부산","신양산구서#2 T/L","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#2T/L GIS 교체, (구)BUS-TIE GIS 철거, 신규 BUS-PT 설치","2023-11-06 09:00","2023-12-01 18:00","취소","취소","연속"]
[651,"부산울산","동부산","구서노포#2 T/L","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ #2BUS 시험가압(1Hr)","2023-11-08 17:00","2023-11-08 18:00","2023-11-15 15:00","2023-11-15 18:00","연속"]
[652,"부산울산","동부산","구서S/S #2 BUS","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#2T/L GIS 교체 → #2DS, 상부BUS 설치","2023-11-20 09:00","2023-12-01 18:00","취소","취소","연속"]
[653,"부산울산","동부산","구서노포#2 T/L","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ #1BUS 시험가압(24Hr)","2023-11-17 18:00","2023-11-18 18:00","2023-11-21 15:00","2023-11-21 18:00","연속"]
[654,"부산울산","동부산","구서S/S #2 BUS","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#2T/L GIS 교체 → #2DS 철거 및 고깔처리","2023-11-06 09:00","2023-11-08 18:00","취소","취소","연속"]
[655,"부산울산","동부산","구서S/S #1 BUS","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#2T/L GIS 교체 → CB, #1DS 철거 및 설치","2023-11-09 09:00","2023-11-18 18:00","취소","취소","연속"]
[656,"부산울산","동부산","구서노포#2 T/L","노포S/S 170GIS 정밀점검","노포S/S 170GIS 정밀점검","2023-11-02 09:00","2023-11-03 18:00","2023-11-02 09:00","2023-11-03 18:00","연속"]
[657,"부산울산","동부산","노포정관#1 T/L","154kV 구서-노포-정관-장안T/L OPGW 증설공사","노포-정관T/L #8 ~ 정관C/H간 OPGW 교체","2023-11-02 09:00","2023-11-11 18:00","2023-11-04 09:00","2023-11-13 18:00","연속"]
[658,"부산울산","동부산","수영우동 T/L","우동S/S 170GIS 정밀점검","우동S/S 170GIS 정밀점검","2023-11-11 09:00","2023-11-12 18:00","2023-11-11 09:00","2023-11-12 18:00","연속"]
[659,"부산울산","북부산","개금범천#1 T/L","개금S/S 154kV GIS 교체공사","개금S/S 154kV GIS 교체공사 - 개금-범천#1T/L 11/1~11/15 - 개금-범천#2T/L 11/20~12/6","2023-11-01 09:00","2023-11-22 18:00","2023-11-01 09:00","2023-11-22 18:00","연속"]
[660,"부산울산","북부산","학장개금#2 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","지중송전 OF케이블 절연유 열화진단용 시료 채취","2023-11-24 09:00","2023-11-24 18:00","2023-11-24 09:00","2023-11-24 18:00","연속"]
[661,"부산울산","북부산","개금범천#2 T/L","개금S/S 154kV GIS 교체공사","개금S/S 154kV GIS 교체공사 - 개금-범천#1T/L 11/1~11/15 - 개금-범천#2T/L 11/20~12/6","2023-11-27 09:00","2023-12-15 18:00","2023-11-27 09:00","2023-12-15 18:00","연속"]
[662,"부산울산","북부산","학장개금#1 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","지중송전 OF케이블 절연유 열화진단용 시료 채취","2023-11-23 09:00","2023-11-23 18:00","2023-11-23 09:00","2023-11-23 18:00","연속"]
[663,"부산울산","북부산","구포S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV 지하철2호선T/L GIS 정밀점검 휴전설비 : #2BUS","2023-11-05 12:00","2023-11-05 13:00","2023-11-05 12:00","2023-11-05 13:00","연속"]
[664,"부산울산","북부산","구포S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV 지하철3호선T/L GIS 정밀점검 휴전설비 : #2BUS","2023-11-12 12:00","2023-11-12 13:00","2023-11-12 12:00","2023-11-12 13:00","연속"]
[665,"부산울산","북부산","북부산구포#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV 지하철3호선T/L GIS 정밀점검 휴전설비 : 북부산-구포#2T/L(시험가압선로)","2023-11-12 12:00","2023-11-12 13:00","2023-11-12 12:00","2023-11-12 13:00","연속"]
[666,"부산울산","북부산","구포S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV #3M.Tr 1차 GIS 정밀점검 휴전설비 : #2BUS","2023-11-20 08:00","2023-11-20 18:00","2023-11-20 08:00","2023-11-20 18:00","연속"]
[667,"부산울산","북부산","북부산구포#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV #3M.Tr 1차 GIS 정밀점검 휴전설비 : 북부산-구포#2T/L(시험가압선로)","2023-11-20 17:00","2023-11-20 18:00","2023-11-20 17:00","2023-11-20 18:00","연속"]
[668,"부산울산","북부산","구포S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV #3M.Tr 1차 GIS 정밀점검 휴전설비 : #1BUS","2023-11-21 08:00","2023-11-22 18:00","2023-11-21 08:00","2023-11-22 18:00","연속"]
[669,"부산울산","북부산","북부산구포#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV #3M.Tr 1차 GIS 정밀점검 휴전설비 : 북부산-구포#2T/L(시험가압선로)","2023-11-22 17:00","2023-11-22 18:00","2023-11-22 17:00","2023-11-22 18:00","연속"]
[670,"부산울산","북부산","북부산구포#2 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","구포S/S 154kV 지하철2호선T/L GIS 정밀점검 휴전설비 : 북부산-구포#2T/L(시험가압선로)","2023-11-05 12:00","2023-11-05 13:00","2023-11-05 12:00","2023-11-05 13:00","연속"]
[671,"부산울산","북부산","북부산물금 T/L","154kV 북부산-호포T/L 정밀점검(안전확보)","154kV 북부산-호포T/L 정밀점검 다회선 철탑 안전확보 휴전(북부산-물금T/L 24-1호) 11월7일, 11월9일 이틀","2023-11-07 09:00","2023-11-09 18:00","2023-11-07 09:00","2023-11-09 18:00","매일"]
[672,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치(안전확보)","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(4회선 병가구간 안전확보)","2023-11-04 08:30","2023-11-05 18:00","취소","취소","연속"]
[673,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(1~46호 45기,2회선 철탑 편측 12기, 4회선 철탑 편측 33기)","2023-11-04 08:30","2023-11-08 18:00","취소","취소","연속"]
[674,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(1~46호 45기,2회선 철탑 편측 12기, 4회선 철탑 편측 33기)","2023-11-10 08:30","2023-11-12 18:00","취소","취소","연속"]
[675,"부산울산","북부산","북부산양산 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치(안전확보)","154kV 북부산-삼랑진T/L 수평 추락방지장치 설치(4회선 병가구간 안전확보)","2023-11-10 08:30","2023-11-12 18:00","취소","취소","연속"]
[676,"부산울산","북부산","서창산막#1 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 서창-산막T/L 수평 추락방지장치 및 관형지지물 가이드레일 설치(25~69호 32기)","2023-11-25 08:30","2023-11-26 18:00","2023-11-25 08:30","2023-11-26 18:00","연속"]
[677,"부산울산","북부산","언양산막#2 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치","154kV 언양-산막T/L 수평 추락방지장치 설치(36~66호 30기)","2023-11-27 08:30","2023-12-01 18:00","2023-11-27 08:30","2023-12-01 18:00","연속"]
[678,"부산울산","북부산","서창산막#1 T/L","154kV 북부산-삼랑진 등 8개T/L 수평 추락방지장치 설치공사","154kV 서창-산막T/L 수평 추락방지장치 및 관형지지물 가이드레일 설치(25~69호 32기)","2023-11-18 08:30","2023-11-19 18:00","2023-11-18 08:30","2023-11-19 18:00","연속"]
[679,"부산울산","북부산","양산삼랑진PP T/L","22-23년 북부산전력지사 변전총액공사","삼랑진양수S/Y 154kV 양산-삼랑진PPT/L 누기조치","2023-11-01 09:00","2023-11-01 18:00","2023-11-13 09:00","2023-11-13 18:00","연속"]
[680,"부산울산","북부산","양산산막#1 T/L","양산S/S 154kV GIS 누기조치","양산S/S 154kV 양산-산막#1T/L 누기조치","2023-11-13 09:00","2023-11-14 18:00","2023-11-14 09:00","2023-11-15 18:00","연속"]
[681,"부산울산","북부산","북부산호포 T/L","154kV 북부산-호포T/L 송전선로 정밀점검","154kV 북부산-호포T/L 송전선로 정밀점검","2023-11-07 09:00","2023-11-08 18:00","2023-11-07 09:00","2023-11-08 18:00","연속"]
[682,"부산울산","북부산","호포물금 T/L","154kV 호포-물금T/L 송전선로 정밀점검","154kV 호포-물금T/L 송전선로 정밀점검","2023-11-09 09:00","2023-11-10 18:00","2023-11-09 09:00","2023-11-10 18:00","연속"]
[683,"부산울산","북부산","호포물금 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV #2M.Tr 1차 GIS 정밀점검 - 휴전설비 : 호포-물금T/L(시험가압 선로)","2023-11-29 17:00","2023-11-29 18:00","2023-11-29 17:00","2023-11-29 18:00","연속"]
[684,"부산울산","북부산","호포S/S #1 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV #2M.Tr 1차 GIS 정밀점검 - 휴전설비 : #1BUS","2023-11-28 08:00","2023-11-29 18:00","2023-11-28 08:00","2023-11-29 18:00","연속"]
[685,"부산울산","북부산","호포물금 T/L","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV #2M.Tr 1차 GIS 정밀점검 - 휴전설비 : 호포-물금T/L(시험가압 선로)","2023-11-27 17:00","2023-11-27 18:00","2023-11-27 17:00","2023-11-27 18:00","연속"]
[686,"부산울산","북부산","호포S/S #2 BUS","23년 북부산전력지사 154kV GIS 정밀점검 공사","호포S/S 154kV #2M.Tr 1차 GIS 정밀점검 - 휴전설비 : #2BUS","2023-11-27 08:00","2023-11-27 18:00","2023-11-27 08:00","2023-11-27 18:00","연속"]
[687,"부산울산","북부산","호포매리#1 T/L","154kV 호포-매리T/L OPGW 증설공사","호포S/S-매리S/S간 OPGW 교체 및 증설","2023-11-20 09:00","2023-11-25 18:00","2023-11-20 09:00","2023-11-25 18:00","연속"]
[688,"부산울산","서부산","녹공마천#1 T/L","녹공S/S 154kV 녹공-마천#1T/L GIS 보통점검[전문공사]","녹공S/S 154kV 녹공-마천#1T/L GIS 보통점검[전문공사]","2023-11-01 09:00","2023-11-01 18:00","2023-11-01 09:00","2023-11-01 18:00","연속"]
[689,"부산울산","서부산","녹공마천#2 T/L","녹공S/S 154kV 녹공-마천#2T/L GIS 보통점검[전문공사]","녹공S/S 154kV 녹공-마천#2T/L GIS 보통점검[전문공사]","2023-11-02 09:00","2023-11-02 18:00","2023-11-02 09:00","2023-11-02 18:00","연속"]
[690,"부산울산","서부산","용원녹공#1 T/L","녹공S/S 용원-녹공#1T/L GIS 휴전작업","녹공S/S 용원-녹공#1T/L GIS 휴전작업 - 전자변 교체","2023-11-09 09:00","2023-11-09 18:00","2023-11-09 09:00","2023-11-09 18:00","연속"]
[691,"부산울산","서부산","신녹산녹산#2 T/L","녹산S/S 154kV 신녹산-녹산#2T/L GIS 보통점검[전문공사]","녹산S/S 154kV 신녹산-녹산#2T/L GIS 보통점검[전문공사]","2023-11-06 09:00","2023-11-06 18:00","2023-11-06 09:00","2023-11-06 18:00","연속"]
[692,"부산울산","서부산","신녹산녹산#1 T/L","신녹산, 녹산S/S 154kV 신녹산-녹산#1T/L 보호PNL 대체작업","신녹산, 녹산S/S 154kV 신녹산-녹산#1T/L 보호PNL 대체작업","2023-11-14 09:00","2023-11-17 18:00","2023-11-14 09:00","2023-11-17 18:00","연속"]
[693,"부산울산","서부산","용원녹공#2 T/L","용원, 녹공S/S 용원-녹공#2T/L 보호PNL 대체작업","용원, 녹공S/S 용원-녹공#2T/L 보호PNL 대체작업","2023-11-20 09:00","2023-11-22 18:00","2023-11-20 09:00","2023-11-22 18:00","연속"]
[694,"부산울산","서부산","신김해지사#2 T/L","345kV 신김해-신녹산 등 5개T/L 철탑보강공사","항공장애표시구 설치 전 철탑보강공사","2023-11-03 08:00","2023-11-03 18:00","2023-11-03 08:00","2023-11-03 18:00","연속"]
[695,"부산울산","서부산","신김해지사#1 T/L","345kV 신김해-신녹산 등 5개T/L 철탑보강공사","항공장애표시구 설치 전 철탑보강공사","2023-11-02 08:00","2023-11-02 18:00","2023-11-02 08:00","2023-11-02 18:00","연속"]
[696,"부산울산","울산","남울산신온산#2 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-11-13 07:00","2023-11-17 18:00","2023-11-13 07:00","2023-11-17 18:00","연속"]
[697,"부산울산","울산","남울산처용#1 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-11-20 07:00","2023-11-23 18:00","2023-11-20 07:00","2023-11-23 18:00","연속"]
[698,"부산울산","울산","남울산처용#2 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-11-08 07:00","2023-11-10 18:00","2023-11-08 07:00","2023-11-10 18:00","연속"]
[699,"부산울산","울산","남울산신온산#1 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-11-23 07:00","2023-12-30 18:00","2023-11-23 07:00","2023-12-30 18:00","연속"]
[700,"부산울산","울산","동울산산하#2 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ 동울산-산하 #2 추락방지장치 설치 - 1~8 호","2023-11-02 07:30","2023-11-03 18:00","2023-11-02 07:30","2023-11-03 18:00","연속"]
[701,"부산울산","울산","성암울산TP#1 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-11-08 07:00","2023-11-10 18:00","2023-11-08 07:00","2023-11-10 18:00","연속"]
[702,"부산울산","울산","성암울산TP#2 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-11-20 07:00","2023-11-21 18:00","2023-11-20 07:00","2023-11-21 18:00","연속"]
[703,"부산울산","울산","신울산매암#2 T/L","23년 울산전력지사 개폐장치 보통점검공사","- 신울산측 GIS 보통점검, 피뢰기 보통점검 - 매암측 GIS 보통점검","2023-11-17 09:00","2023-11-17 18:00","2023-11-17 09:00","2023-11-17 18:00","연속"]
[704,"부산울산","울산","신울산S/S SEC CB 61620","22~23년 변전협력회사 총액공사","- GIS 보통점검","2023-11-28 09:00","2023-11-28 18:00","2023-11-28 09:00","2023-11-28 18:00","연속"]
[705,"부산울산","울산","신울산S/S SEC CB 66670","22~23년 변전협력회사 총액공사","- GIS 보통점검","2023-11-27 09:00","2023-11-27 18:00","2023-11-27 09:00","2023-11-27 18:00","연속"]
[706,"부산울산","울산","신울산매암#1 T/L","22~23년 변전협력회사 총액공사","- 신울산측 GIS, LA, CVT 보통점검 - 매암측 GIS 보통점검","2023-11-29 09:00","2023-11-29 18:00","2023-11-29 09:00","2023-11-29 18:00","연속"]
[707,"부산울산","울산","신울산매암#3 T/L","22~23년 변전협력회사 총액공사","- 신울산측 GIS, LA, CVT 보통점검 - 매암측 GIS 보통점검","2023-11-20 09:00","2023-11-20 18:00","2023-11-20 09:00","2023-11-20 18:00","연속"]
[708,"부산울산","울산","옥동외동#2 T/L","154kV 옥동S/S 장기사용GIS 대체공사","옥동S/S 154kV 외동-옥동#2T/L GIS대체공사","2023-11-27 09:00","2023-12-15 18:00","2023-11-27 09:00","2023-12-15 18:00","연속"]
[709,"부산울산","울산","신울산옥동#1 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ 신울산-옥동#1 추락방지장치 수평{1 [2 3] 5 6 7 8 9 10 11 12 13} 신울산-웅촌#2 병가 : [2,3]","2023-11-20 07:30","2023-11-21 18:00","2023-11-20 07:30","2023-11-22 18:00","연속"]
[710,"부산울산","울산","옥동외동#1 T/L","옥동S/S 154kV 장기사용 GIS 대체공사","옥동S/S 외동-옥동#1T/L GIS 장기사용 GIS 대체공사","2023-11-01 09:00","2023-11-24 18:00","2023-11-01 09:00","2023-11-24 18:00","연속"]
[711,"부산울산","울산","신울산옥동#2 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ 신울산-옥동#2 추락방지장치 수평 1~13(4회선 2,3) - 신울산-웅촌#1 병가","2023-11-15 07:30","2023-11-17 18:00","취소","취소","연속"]
[712,"부산울산","울산","온산처용#2 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-11-15 07:00","2023-11-20 18:00","2023-11-15 07:00","2023-11-20 18:00","연속"]
[713,"부산울산","울산","용연울산TP#3 T/L","345kv 동울산-월성NP등 6개T/L 추락방지장치 등 설치공사","철탑 추락방지장치 설치","2023-11-25 07:00","2023-11-25 18:00","2023-11-25 07:00","2023-11-25 18:00","연속"]
[714,"부산울산","울산","울산T/P #61 BUS","울산화력S/Y 장기사용 GIS 교체공사(6차)","○ 용연-울산TP#1T/L GIS 교체 → #61BUS 시험가압","2023-11-29 17:00","2023-11-29 18:00","2023-11-29 17:00","2023-11-29 18:00","연속"]
[715,"부산울산","울산","울산T/P #66 BUS","울산화력S/Y 장기사용 GIS 교체공사(6차)","○ 용연-울산TP#1T/L GIS 교체 → #66BUS 철거 및 신규 GIS 설치, 시험가압","2023-11-20 09:00","2023-11-29 17:00","2023-11-20 09:00","2023-11-29 17:00","연속"]
[716,"부산울산","울산","울산T/P #61 BUS","울산화력S/Y 장기사용 GIS 교체공사(6차)","○ 용연-울산TP#1T/L GIS 교체 → #61BUS 철거 및 신규 GIS 설치, 시험가압","2023-11-08 09:00","2023-11-18 18:00","2023-11-08 09:00","2023-11-18 18:00","연속"]
[717,"부산울산","울산","용연울산TP#2 T/L","울산화력S/Y 장기사용 GIS 교체공사(6차)","○ 용연-울산TP#1T/L GIS 교체 → #61BUS 시험가압 (1DS 개방상태) 24시간","2023-11-17 17:00","2023-11-18 17:00","2023-11-17 17:00","2023-11-18 17:00","연속"]
[718,"부산울산","울산","울산T/P #61 BUS","울산화력S/Y 장기사용 GIS 교체공사(5차)","○ 154kV 6200 BUS-TIE, #61-66BUS PT, 용연-울산TP#2T/L GIS 교체 → #61BUS 시험가압 (1DS, CB 투입상태) 1시간","2023-11-04 18:00","2023-11-04 19:00","2023-11-04 18:00","2023-11-04 19:00","연속"]
[719,"부산울산","울산","울산T/P CB 6100","울산화력S/Y 장기사용 GIS 교체공사(7차)","○ #6100BUS-TIE, 60-65 PT&ES GIS 교체 →#6100BUS-TIE, 60-65 PT&ES GIS 철거 및 신규 GIS 설치, 시험가압","2023-11-30 09:00","2023-12-22 18:00","2023-11-30 09:00","2023-12-22 18:00","연속"]
[720,"부산울산","울산","울산T/P #65 BUS","울산화력S/Y 장기사용 GIS 교체공사(7차)","○ #6100BUS-TIE, 60-65 PT&ES GIS 교체 →#6100BUS-TIE, 60-65 PT&ES GIS 철거 및 신규 GIS 설치, 시험가압","2023-11-30 09:00","2023-12-01 18:00","2023-11-30 09:00","2023-12-01 18:00","연속"]
[721,"부산울산","울산","울산T/P #66 BUS","울산화력S/Y 장기사용 GIS 교체공사(6차)","○ 용연-울산TP#1T/L GIS 교체 → #66BUS 철거 및 신규 GIS 설치, 시험가압","2023-11-06 09:00","2023-11-07 18:00","2023-11-06 09:00","2023-11-07 18:00","연속"]
[722,"부산울산","울산","용연울산TP#2 T/L","울산화력S/Y 장기사용 GIS 교체공사(6차)","○ 용연-울산TP#1T/L GIS 교체 → #66BUS 시험가압","2023-11-07 17:00","2023-11-07 18:00","2023-11-07 17:00","2023-11-07 18:00","연속"]
[723,"부산울산","울산","용연울산TP#1 T/L","울산화력S/Y 장기사용 GIS 교체공사(6차)","○ 용연-울산TP#1T/L GIS 교체 → 647 GIS 철거 및 신규 GIS 설치, 시험가압","2023-11-06 09:00","2023-11-29 18:00","2023-11-06 09:00","2023-11-29 18:00","연속"]
[724,"부산울산","울산","울산S/S #1 EM.Tr CB","23년 울산전력지사 개폐장치 보통점검공사","- 1차 GIS 보통점검","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[725,"부산울산","울산","울주입실#2 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ 울주-외동#2 - 추락방지장치 수평 42기(4회선 1~4, 16~43) - 1~4 울주입실#2 병가(포항전력지사 선로)","2023-11-06 07:30","2023-11-06 18:00","2023-11-06 07:30","2023-11-06 18:00","연속"]
[726,"부산울산","울산","울주직동#2 T/L","765kV북경남-신고리 등 7개T/L 추락방지장치 설치공사","154kV 울주-직동#2T/L 38기 추락방지장치 설치 345kV 울주-고리NP#1T/L과 병가","2023-11-01 07:00","2023-11-10 18:00","2023-11-01 07:00","2023-11-10 18:00","연속"]
[727,"부산울산","울산","울주직동#1 T/L","765kV북경남-신고리 등 7개T/L 추락방지장치 설치공사","154kV 울주-직동#1T/L 38기 추락방지장치 설치 345kV 울주-고리NP#2T/L과 병가","2023-11-24 07:00","2023-12-05 18:00","2023-11-24 07:00","2023-12-05 18:00","연속"]
[728,"부산울산","울산","울주외동#2 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ 울주-외동#2 추락방지장치 설치 - 1~44 호","2023-11-06 07:30","2023-11-14 18:00","2023-11-06 07:30","2023-11-14 18:00","연속"]
[729,"부산울산","울산","신울산웅촌#2 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ 신울산-웅촌#2 - 추락방지장치 수평 25기 및 - 신울산-옥동#1 병가구간(신-옥2,3호)","2023-11-21 07:30","2023-11-28 18:00","2023-11-21 07:30","2023-11-28 18:00","연속"]
[730,"부산울산","울산","신울산웅촌#1 T/L","154kV 추락방지장치 설치공사(수평)","ㅇ 신울산-옥동#2 추락방지장치 수평 : 4회선 2,3호 - 신울산-웅촌#1 병가 2기 물량 설치","2023-11-15 07:30","2023-11-15 18:00","2023-11-15 07:30","2023-11-15 18:00","연속"]
[731,"부산울산","직할","우동대연 T/L","345kV 신양산-신대연 등 7개T/L 자기애관교체공사","자기애관을 폴리머애관으로 교체","2023-11-01 09:00","2023-11-05 18:00","취소","취소","연속"]
[732,"부산울산","직할","범일서면#2 T/L","154kV 범일S/S #3M.Tr 증설공사","154kV 범일S/S #3M.Tr 1차측 GIS 설치 - 가스 회수 관련 감압 필요","2023-11-02 09:00","2023-11-03 18:00","2023-11-02 09:00","2023-11-03 18:00","연속"]
[733,"부산울산","직할","수정범일#1 T/L","154kV 범일S/S #3M.Tr 증설공사","154kV 범일S/S #3M.Tr 1차측 GIS 설치 - 무부하 시험가압","2023-11-04 09:00","2023-11-05 14:00","2023-11-04 09:00","2023-11-05 14:00","연속"]
[734,"부산울산","직할","범일서면#2 T/L","154kV 범일S/S #3M.Tr 증설공사","154kV 범일S/S #3M.Tr 1차측 GIS 설치 - 가스 회수 관련 감압 필요","2023-11-05 14:00","2023-11-06 18:00","2023-11-05 14:00","2023-11-06 18:00","연속"]
[735,"부산울산","직할","수정범일#2 T/L","154kV 범일S/S #3M.Tr 증설공사","154kV 범일S/S #3M.Tr 1차측 GIS 설치 - 무부하 시험가압","2023-11-14 09:00","2023-11-15 18:00","2023-11-14 09:00","2023-11-15 18:00","연속"]
[736,"경남","직할","마천진해#1 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2023-11-25 07:00","2023-11-25 18:00","2023-11-25 07:00","2023-11-25 18:00","연속"]
[737,"경남","직할","장유마천#1 T/L","154kV 장유-마천T/L 추락방지장치 설치 및 교체공사","154kV 장유-마천T/L 추락방지장치 설치 및 교체공사","2023-11-06 07:00","2023-11-15 18:00","2023-11-06 07:00","2023-11-15 18:00","매일"]
[738,"경남","직할","녹공마천#1 T/L","154kV 녹공-마천T/L 추락방지장치 설치 및 교체공사","154kV 녹공-마천T/L 추락방지장치 설치 및 교체공사","2023-11-20 07:00","2023-11-20 18:00","2023-11-20 07:00","2023-11-20 18:00","연속"]
[739,"경남","직할","녹공마천#2 T/L","154kV 녹공-마천T/L 추락방지장치 설치 및 교체공사","154kV 녹공-마천T/L 추락방지장치 설치 및 교체공사","2023-11-21 07:00","2023-11-21 18:00","2023-11-21 07:00","2023-11-21 18:00","연속"]
[740,"경남","직할","마천진해#2 T/L","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해T/L 추락방지장치 설치 및 교체공사","2023-11-22 07:00","2023-11-25 18:00","2023-11-22 07:00","2023-11-25 18:00","매일"]
[741,"경남","직할","장유마천#2 T/L","154kV 장유-마천T/L 추락방지장치 설치 및 교체공사","154kV 장유-마천T/L 추락방지장치 설치 및 교체공사","2023-11-23 07:00","2023-12-04 18:00","2023-11-23 07:00","2023-12-04 18:00","매일"]
[742,"경남","직할","신김해지사#1 T/L","154kV 신김해-지사T/L 추락방지장치 설치 및 교체공사","154kV 신김해-지사T/L 추락방지장치 설치 및 교체공사","2023-11-08 07:00","2023-11-10 18:00","2023-11-08 07:00","2023-11-10 18:00","매일"]
[743,"경남","직할","신김해진례#1 T/L","신김해-진례#1T/L 성능저하 점퍼지지애자 교체공사","신김해-진례#1T/L 9호 성능저하 점퍼지지애자 교체공사","2023-11-23 07:00","2023-11-23 18:00","2023-11-23 07:00","2023-11-23 18:00","연속"]
[744,"경남","직할","신김해지사#2 T/L","154kV 신김해-지사T/L 추락방지장치 설치 및 교체공사","154kV 신김해-지사T/L 추락방지장치 설치 및 교체공사","2023-11-27 07:00","2023-11-29 18:00","2023-11-27 07:00","2023-11-29 18:00","매일"]
[745,"경남","직할","신월삼정#2 T/L","154kV 신월-삼정T/L 수평 추락방지장치 설치공사","154kV 신월-삼정T/L 수평 추락방지장치 설치공사","2023-11-04 07:00","2023-11-04 18:00","2023-11-04 07:00","2023-11-04 18:00","연속"]
[746,"경남","직할","안민천선#1 T/L","154kV 안민-천선T/L 수평 추락방지장치 설치공사","154kV 안민-천선T/L 수평 추락방지장치 설치공사","2023-11-15 07:00","2023-11-15 18:00","2023-11-15 07:00","2023-11-15 18:00","연속"]
[747,"경남","직할","안민천선#2 T/L","154kV 안민-천선T/L 수평 추락방지장치 설치공사","154kV 안민-천선T/L 수평 추락방지장치 설치공사","2023-11-22 07:00","2023-11-22 18:00","2023-11-22 07:00","2023-11-22 18:00","연속"]
[748,"경남","진주","가야사봉#2 T/L","154kV 가야-사봉 #1, 2 T/L 철탑 추락방지장치 설치","154kV 가야-사봉 #2 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 철탑 수평 추락방지장치 설치 : No.14~43, 50(31기)","2023-11-29 07:30","2023-11-30 18:00","2023-11-29 07:30","2023-11-30 18:00","매일"]
[749,"경남","진주","가야사봉#1 T/L","154kV 가야-사봉 #1, 2 T/L 철탑 추락방지장치 설치","154kV 가야-사봉 #1 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 철탑 수평 추락방지장치 설치 : No.14~43, 50(31기)","2023-11-27 07:30","2023-11-28 18:00","2023-11-27 07:30","2023-11-28 18:00","매일"]
[750,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주T/L 피뢰기 열화진단","154kV 의령-동진주#2T/L 피뢰기 열화진단","2023-11-03 09:00","2023-11-03 18:00","2023-11-03 09:00","2023-11-03 18:00","연속"]
[751,"경남","진주","의령동진주#1 T/L","154kV 의령-동진주T/L 피뢰기 열화진단","154kV 의령-동진주#1T/L 피뢰기 열화진단","2023-11-02 09:00","2023-11-02 18:00","2023-11-02 09:00","2023-11-02 18:00","연속"]
[752,"경남","진주","사봉개양#2 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-11-10 07:00","2023-11-10 18:00","2023-11-10 07:00","2023-11-10 18:00","연속"]
[753,"경남","진주","사천개양#2 T/L","154kV 사천-개양T/L 피뢰기 설치 관련 안전이격확보 휴전","154kV 사천-개양T/L 피뢰기 설치 관련 안전이격확보 휴전","2023-11-18 09:00","2023-11-19 18:00","2023-11-18 09:00","2023-11-19 18:00","매일"]
[754,"경남","진주","사천개양#2 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-11-04 07:00","2023-11-04 18:00","2023-11-04 07:00","2023-11-04 18:00","연속"]
[755,"경남","진주","사천개양#2 T/L","154kV 사천-개양T/L 피뢰기 설치 관련 안전이격확보 휴전","154kV 사천-개양T/L 피뢰기 설치 관련 안전이격확보 휴전","2023-11-12 09:00","2023-11-12 18:00","취소","취소","연속"]
[756,"경남","진주","사천개양#1 T/L","22~23년 진주전력 가공송전 협력회사 총액공사","154kV 사천-개양T/L 피뢰기 설치공사 시행","2023-11-12 09:00","2023-11-15 18:00","취소","취소","매일"]
[757,"경남","진주","사천개양#1 T/L","22~23년 진주전력 가공송전 협력회사 총액공사","154kV 사천-개양T/L 피뢰기 설치공사 시행","2023-11-17 09:00","2023-11-19 18:00","2023-11-17 09:00","2023-11-19 18:00","매일"]
[758,"경남","진주","하동개양#2 T/L","154kV 하동-개양T/L 수평추락방지장치 설치공사","154kV 하동-개양T/L 수평추락방지장치 설치공사","2023-11-01 07:00","2023-11-08 18:00","취소","취소","매일"]
[759,"경남","진주","하동개양#1 T/L","154kV 하동-개양T/L 수평추락방지장치 설치공사","154kV 하동-개양T/L 수평추락방지장치 설치공사 (하동-개양#1,2T/L 수직배열로 인한 동시휴전 신청)","2023-11-04 07:00","2023-11-05 18:00","취소","취소","매일"]
[760,"경남","진주","쌍림합천#2 T/L","[안전작업거리확보휴전] 합천수력 #1T/L 철탑 추락방지장치 설치","[안전작업거리확보휴전] 합천수력T/L 추락방지장치 설치공사(당일) - 철탑 수평 추락방지장치 설치 : No.54~56(2기) - 4회선 철탑 작업으로 인한 안전작업거리확보 휴전신청(합천수력 #1, 쌍림-합천 #2)","2023-11-20 07:30","2023-11-20 18:00","취소","취소","연속"]
[761,"경남","진주","합천합천수력#1 T/L","154kV 합천수력 #1, 2 T/L 철탑 추락방지장치 설치","154kV 합천수력 #1 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 철탑 수평 추락방지장치 설치 : No.1~35(35기) - 4회선 철탑은 동시 작업 예정(거창-합천 #2) - 4회선 철탑 작업으로 안전작업거리확보휴전 신청(쌍림-합천#2)","2023-11-20 07:30","2023-11-22 18:00","2023-11-20 07:30","2023-11-22 18:00","매일"]
[762,"경남","진주","쌍림합천#1 T/L","[안전작업거리확보휴전] 합천수력 #2 T/L 철탑 추락방지장치 설치","[안전작업거리확보휴전] 합천수력T/L 추락방지장치 설치공사(당일) - 철탑 수평 추락방지장치 설치 : No.54~56(2기) - 4회선 철탑 작업으로 인한 안전작업거리확보 휴전신청(합천수력 #2, 쌍림-합천 #1)","2023-11-23 07:30","2023-11-23 18:00","취소","취소","연속"]
[763,"경남","진주","합천합천수력#2 T/L","154kV 합천수력 #1, 2 T/L 철탑 추락방지장치 설치","154kV 합천수력 #2 T/L 철탑 수평 추락방지장치 설치공사 (매일) - 철탑 수평 추락방지장치 설치 : No.1~35(35기) - 4회선 철탑은 동시 작업 예정(거창-합천 #1) - 4회선 철탑 작업으로 안전작업거리확보휴전 신청(쌍림-합천#1)","2023-11-23 07:30","2023-11-25 18:00","2023-11-23 07:30","2023-11-25 18:00","매일"]
[764,"경남","통영","신고성거제#2 T/L","154kV 진동-안정#2T/L 추락방지장치 설치공사(안전작업거리 확보)","154kV 진동-안정#2T/L 추락방지장치 설치공사(안전작업거리 확보)","2023-11-18 07:00","2023-11-19 18:00","2023-11-18 07:00","2023-11-19 18:00","매일"]
[765,"경남","통영","안정통영복합#2 T/L CB","통영복합S/Y 154kV 한국가스공사T/L 신규수용공사","1. GIS(170kV 50kA 1,250A) x 1CCT 설치 2. 기타 부대공사 x 1식","2023-11-10 09:00","2023-11-11 18:00","2023-11-10 09:00","2023-11-11 18:00","연속"]
[766,"경남","통영","안정통영복합#2 T/L CB","통영복합S/Y 154kV 한국가스공사T/L 신규수용공사","1. GIS(170kV 50kA 1,250A) x 1CCT 설치 2. 기타 부대공사 x 1식","2023-11-24 09:00","2023-11-25 18:00","2023-11-24 09:00","2023-11-25 18:00","연속"]
[767,"경남","함안","매리김해#2 T/L","154kV 매리-김해T/L 수평 추락방지장치 설치공사","154kV 매리-김해T/L 수평 추락방지장치 설치공사","2023-11-04 07:00","2023-11-05 18:00","2023-11-04 07:00","2023-11-05 18:00","매일"]
[768,"경남","함안","호포매리#2 T/L","154kV 호포-매리T/L 수평 추락방지장치 설치공사","154kV 호포-매리T/L 수평 추락방지장치 설치공사","2023-11-04 07:00","2023-11-05 18:00","2023-11-04 07:00","2023-11-05 18:00","매일"]
[769,"경남","함안","청도밀양#2 T/L","추락방지장치(수평) 설치공사","○ 추락방지장치(수평) 설치 : 청도-밀양#2T/L 57~74, 78~80호","2023-11-12 07:00","2023-11-12 18:00","취소","취소","매일"]
[770,"경남","함안","청도밀양#1 T/L","송전선로용 피뢰기 및 추락방지장치(수평) 설치공사","○ [피뢰기 설치] 청도-밀양#1T/L 30~74, 78~80호, [추락방지장치(수평) 설치] 청도-밀양#1T/L 57~74, 78~80호","2023-11-18 07:00","2023-11-19 18:00","2023-11-18 07:00","2023-11-19 18:00","매일"]
[771,"경남","함안","청도밀양#2 T/L","추락방지장치(수평) 설치공사","○ 추락방지장치(수평) 설치 : 청도-밀양#2T/L 57~74, 78~80호","2023-11-18 07:00","2023-11-19 18:00","취소","취소","매일"]
[772,"경남","함안","초동밀양#1 T/L","추락방지장치(수평) 설치공사","○ 추락방지장치(수평) 설치공사 : 초동-밀양#1T/L 16~33, 37~39호","2023-11-04 07:00","2023-11-05 18:00","취소","취소","매일"]
[773,"경남","함안","청도밀양#1 T/L","송전선로용 피뢰기 및 추락방지장치(수평) 설치공사","○ [피뢰기 설치] 청도-밀양#1T/L 30~74, 78~80호, [추락방지장치(수평) 설치] 청도-밀양#1T/L 57~74, 78~80호","2023-11-12 07:00","2023-11-12 18:00","2023-11-12 07:00","2023-11-12 18:00","매일"]
[774,"경남","함안","초동밀양#2 T/L","송전선로용 피뢰기 설치 및 성능저하 점퍼지지애자 교체공사","○ [피뢰기 설치] 초동-밀양#2T/L 7~33, 37~39호, [점퍼지지애자 교체] 초동-밀양#2T/L 2호","2023-11-04 07:00","2023-11-05 18:00","2023-11-04 07:00","2023-11-05 18:00","매일"]
[775,"경남","함안","초동밀양#1 T/L","추락방지장치(수평) 설치공사","○ 추락방지장치(수평) 설치공사 : 초동-밀양#1T/L 16~33, 37~39호","2023-11-11 07:00","2023-11-11 18:00","취소","취소","매일"]
[776,"경남","함안","초동밀양#2 T/L","송전선로용 피뢰기 설치 및 성능저하 점퍼지지애자 교체공사","○ [피뢰기 설치] 초동-밀양#2T/L 7~33, 37~39호, [점퍼지지애자 교체] 초동-밀양#2T/L 2호","2023-11-11 07:00","2023-11-11 18:00","2023-11-11 07:00","2023-11-11 18:00","매일"]
[777,"경남","함안","삼계어방#2 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9-14호 이도 재조정 및 14호 철탑암 교체 공사","2023-11-25 07:00","2023-11-26 18:00","2023-11-25 07:00","2023-11-26 18:00","연속"]
[778,"경남","함안","한림정삼계#2 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9-14호 이도 재조정 및 14호 철탑암 교체 공사","2023-11-18 07:00","2023-11-19 18:00","2023-11-18 07:00","2023-11-19 18:00","연속"]
[779,"경남","함안","한림정삼계#1 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9-14호 이도 재조정 및 14호 철탑암 교체 공사","2023-11-25 07:00","2023-11-26 18:00","2023-11-25 07:00","2023-11-26 18:00","연속"]
[780,"경남","함안","삼계어방#1 T/L","154kV 삼계-어방T/L 9-14호 지장송전선로 이설","9-14호 이도 재조정 및 14호 철탑암 교체 공사","2023-11-18 07:00","2023-11-19 18:00","2023-11-18 07:00","2023-11-19 18:00","연속"]
[781,"경남","함안","신마산중리#2 T/L","154kV 신마산-중리#2T/L 용량증대 전선교체공사","1. 신마산S/S~중리S/S(8.439km) ACSR330SQ-ASCC/TW430SQ 용량증대 전선교체 2. 수평 와이어형 추락방지장치 설치[신마산-중리(23~32), 중리-가야(1~6)]","2023-11-04 07:00","2023-11-09 18:00","2023-11-04 07:00","2023-11-09 18:00","연속"]
[782,"경남","함안","신마산중리#1 T/L","154kV 신마산-중리#1T/L 용량증대 전선교체공사","1. 신마산S/S~중리S/S(8.439km) ACSR330SQ-ASCC/TW430SQ 용량증대 전선교체 2. 수평 와이어형 추락방지장치 설치","2023-11-10 07:00","2023-11-15 18:00","취소","취소","연속"]
[783,"경남","함안","신마산중리#1 T/L","154kV 신마산-중리#1T/L 용량증대 전선교체공사","1. 신마산S/S~중리S/S(8.439km) ACSR330SQ-ASCC/TW430SQ 용량증대 전선교체 2. 수평 와이어형 추락방지장치 설치","2023-11-17 07:00","2023-11-25 18:00","2023-11-17 07:00","2023-11-25 18:00","연속"]
[784,"경남","함안","신마산마산#2 T/L","[안전거리] 신마산-서마산T/L 휴전작업 안전거리 확보차","신마산-서마산T/L 성능저하 점퍼지지애자 교체공사 작업시 안전거리 확보휴전","2023-11-20 07:00","2023-11-21 18:00","2023-11-20 07:00","2023-11-21 18:00","매일"]
[785,"경남","함안","신마산마산#1 T/L","[안전거리] 신마산-서마산T/L 휴전작업 안전거리 확보차","신마산-서마산T/L 성능저하 점퍼지지애자 교체공사 작업시 안전거리 확보휴전","2023-11-20 07:00","2023-11-21 18:00","2023-11-20 07:00","2023-11-21 18:00","매일"]
[786,"경남","함안","신마산중리#2 T/L","154kV 신마산-중리#2T/L 용량증대 전선교체공사","1. 신마산S/S~중리S/S(8.439km) ACSR330SQ-ASCC/TW430SQ 용량증대 전선교체 2. 수평 와이어형 추락방지장치 설치","2023-11-27 07:00","2023-12-06 18:00","2023-11-27 07:00","2023-12-06 18:00","연속"]
[787,"경남","함안","신마산칠서#1 T/L","OPGW 항공장애표시구 설치공사","항공장애표시구 211개 설치","2023-11-09 07:00","2023-11-09 18:00","2023-11-09 07:00","2023-11-09 18:00","연속"]
[788,"경남","함안","중리가야#1 T/L","154kV 신마산-중리#2T/L 용량증대 전선교체공사 안전이격거리확보","1. 신마산S/S~중리S/S(8.439km) ACSR330SQ-ASCC/TW430SQ 용량증대 전선교체 안전확보 2. 수평 와이어형 추락방지장치 설치[신마산-중리(23~32), 중리-가야(1~6)]","2023-11-04 07:00","2023-11-09 18:00","2023-11-04 07:00","2023-11-09 18:00","연속"]
[789,"경남","함안","중리가야#1 T/L","154kV 신마산-중리#1T/L 용량증대 전선교체공사 안전이격거리확보","1. 신마산S/S~중리S/S(8.439km) ACSR330SQ-ASCC/TW430SQ 용량증대 전선교체","2023-11-12 07:00","2023-11-12 18:00","취소","취소","연속"]
[790,"경남","함안","중리가야#2 T/L","154kV 신마산-중리#1T/L 용량증대 전선교체공사 안전이격거리확보","1. 신마산S/S~중리S/S(8.439km) ACSR330SQ-ASCC/TW430SQ 용량증대 전선교체 2. 수평 와이어형 추락방지장치 설치[신마산-중리(23~32), 중리-가야(1~6)]","2023-11-10 07:00","2023-11-15 18:00","취소","취소","연속"]
[791,"경남","함안","진영한림정#2 T/L","[안전거리] 진영-수산#1T/L 휴전작업 안전거리 확보차","진영-수산#1T/L 피뢰기 설치 및 성능저하 점퍼지지애자 교체공사 휴전작업 안전거리 확보차","2023-11-26 07:00","2023-11-26 12:00","2023-11-26 07:00","2023-11-26 12:00","연속"]
[792,"경남","함안","진영수산#1 T/L","진영-수산#1T/L 피뢰기 설치 및 성능저하 점퍼지지애자 교체공사","진영-수산#1T/L 1~27호 피뢰기, 추락방지장치 설치공사 및 1, 27호 성능저하 점퍼지지애자 교체공사","2023-11-26 07:00","2023-11-29 18:00","2023-11-26 07:00","2023-11-29 18:00","매일"]
[793,"경남","함안","진영한림정#2 T/L","[안전거리] 진영-수산#1T/L 휴전작업 안전거리 확보차","진영-수산#1T/L 피뢰기 설치 및 성능저하 점퍼지지애자 교체공사 휴전작업 안전거리 확보차","2023-11-26 07:00","2023-11-26 12:00","취소","취소","연속"]
[794,"경남","함안","진영수산#2 T/L","진영-수산#2T/L 성능저하 점퍼지지애자 교체공사","진영-수산#2T/L 30호 성능저하 점퍼지지애자 교체공사","2023-11-23 07:00","2023-11-23 18:00","2023-11-23 07:00","2023-11-23 18:00","연속"]
[795,"경남","함안","창녕초동#1 T/L","초동-밀양#2T/L 성능저하 점퍼지지애자 교체공사 관련 안전거리 확보","초동-밀양#2T/L 2호 성능저하 점퍼지지애자 교체공사 관련 안전거리 확보","2023-11-04 07:00","2023-11-04 12:00","2023-11-04 07:00","2023-11-04 12:00","연속"]
[796,"부산울산",null,"장안고리NP T/L","고리1호기 제3차 영구정지 정기검사 ○ 조작차단기 : CB-627, DS-626, DS-625, ES-103, CB-6283, DS-6285, ES-104","○ 고리1발전소 154kV 스위치야드 설비 일반점검","2023-11-13 09:00","2023-12-13 18:00","2023-11-13 09:00","2023-12-13 18:00","연속"]
[797,"서울",null,"창동S/S #2 BUS","창동S/S 154kV 장기사용 GIS 교체공사","상계창동#2T/L, #2M.Tr 1차, PT&ES GIS 교체(2차분) - GIS CB, #1DS, 상부, C/H 철거 및 신품GIS 설치 후 #1BUS 가압","2023-11-05 09:00","2023-11-19 18:00","2023-11-05 09:00","2023-11-19 18:00","연속"]
[798,"서울",null,"방학창동#2 T/L","창동S/S 154kV 장기사용 GIS 교체공사","상계창동#2T/L, #2M.Tr 1차, PT&ES GIS 교체(2차분) - GIS CB, #1DS, 상부, C/H 철거 및 신품GIS 설치 후 #1BUS 가압","2023-11-24 09:00","2023-11-24 18:00","2023-11-24 09:00","2023-11-24 18:00","연속"]
[799,"대전세종충남","천안","인주불당#2 T/L","(10월취소시)[송전]154kV 인주-불당T/L 지장송전선로 이설공사","No.23~26 2기설치, 2기철거, ACSR/AW 410㎟ x 2B x 2C x 0.655km","2023-11-26 07:00","2023-11-26 18:00","2023-11-26 07:00","2023-11-26 18:00","연속"]
[800,"대전세종충남","천안","인주불당#1 T/L","(10월취소시)[송전]154kV 인주-불당T/L 지장송전선로 이설공사","No.23~26 2기설치, 2기철거, ACSR/AW 410㎟ x 2B x 2C x 0.655km","2023-11-25 07:00","2023-11-25 18:00","2023-11-25 07:00","2023-11-25 18:00","연속"]