{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":22,"n_cols":11,"rows_kept":22,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 10월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신안성신가평 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","765kV 신안성-신가평T/L 항공장애등 설치 : No.131,132,146,147","2024-10-05 07:00","2024-10-06 18:00","취소","취소","연속"]
[2,"경기북부","구리","신안성신가평 T/L","송전선로 단상재폐로 결상회로 개선","송운(변전)-1085 (21.10.19) 「송전선로 단상 자동재투입용 GIS 결상회로 개선 시행 알림」 관련 유사고장 재발방지","2024-10-08 09:00","2024-10-08 18:00","취소","취소","연속"]
[3,"경기북부","구리","신태백신가평#2 T/L","송전선로 단상재폐로 결상회로 개선","송운(변전)-1085 (21.10.19) 「송전선로 단상 자동재투입용 GIS 결상회로 개선 시행 알림」 관련 유사고장 재발방지","2024-10-09 09:00","2024-10-09 18:00","취소","취소","연속"]
[4,"경기북부","구리","신안성신가평 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","765kV 신안성-신가평T/L 항공장애등 설치 : No.131,132,146,147","2024-10-19 07:00","2024-10-20 18:00","취소","취소","연속"]
[5,"경기","성남","신안성S/S CB 8700","2024년 성남전력 765kV GIS 보통, 345kV GIS 정밀점검","8700 GIS 보통점검","2024-10-21 09:00","2024-10-21 18:00","2024-10-21 09:00","2024-10-21 18:00","연속"]
[6,"경기","성남","신안성S/S CB 8500","2024년 성남전력 765kV GIS 보통, 345kV GIS 정밀점검","8500 GIS 보통점검","2024-10-14 09:00","2024-10-14 18:00","2024-10-14 09:00","2024-10-14 18:00","연속"]
[7,"경기","성남","신중부신안성#2 T/L","2024년 성남전력 765kV GIS 정밀점검공사","8671 차단기 정밀점검 무부하가압용","2024-10-02 13:00","2024-10-02 15:00","2024-10-02 13:00","2024-10-02 15:00","연속"]
[8,"경기","성남","신안성S/S #1 BUS","2024년 성남전력 765kV GIS 정밀점검공사","8671 차단기 정밀점검 무부하가압용","2024-10-02 13:00","2024-10-02 15:00","2024-10-02 13:00","2024-10-02 15:00","연속"]
[9,"경기","성남","신안성S/S CB 8872","2024년 성남전력 765 GIS 보통, 345 GIS 정밀점검공사","8872 GIS 보통점검","2024-10-28 09:00","2024-10-28 18:00","2024-10-28 09:00","2024-10-28 18:00","연속"]
[10,"경기","성남","신안성S/S CB 8572","2024년 성남전력 765kV GIS 보통, 345kV GIS 정밀점검","8572 GIS 보통점검","2024-10-15 09:00","2024-10-15 18:00","2024-10-15 09:00","2024-10-15 18:00","연속"]
[11,"경기","성남","신안성신가평 T/L","2024-2025년 성남전력지사 가공송전 협력회사공사","항공장애표시도장[33~37호(5기)]","2024-10-17 00:07","2024-10-23 18:00","취소","취소","연속"]
[12,"경기","성남","신안성S/S CB 8772","2024년 성남전력 765kV GIS 보통, 345kV GIS 정밀점검","8772 GIS 보통점검","2024-10-22 09:00","2024-10-22 18:00","2024-10-22 09:00","2024-10-22 18:00","연속"]
[13,"대전세종충남","서산","당진T/P CB 8771","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 당진화력S/S 765kV 8771 CB 보통점검 및 보호계전기 교체","2024-10-21 09:30","2024-10-22 18:00","2024-10-21 14:00","2024-10-22 18:00","연속"]
[14,"대전세종충남","서산","신서산S/S CB 8372","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 765kV 8372 CB 보통점검 및 보호계전기 교체","2024-10-17 09:30","2024-10-18 18:00","2024-10-17 09:30","2024-10-18 18:00","연속"]
[15,"대전세종충남","서산","신서산S/S CB 8600","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 765kV 8600 CB 보통점검 및 보호계전기 교체","2024-10-07 09:30","2024-10-08 18:00","2024-10-07 09:30","2024-10-08 18:00","연속"]
[16,"대전세종충남","서산","신서산S/S CB 8571","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 765kV 8571 CB 보통점검 및 보호계전기 교체","2024-10-10 09:30","2024-10-11 18:00","2024-10-10 09:30","2024-10-11 18:00","연속"]
[17,"대전세종충남","서산","신서산S/S CB 8300","24년 서산P/O 765kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 765kV 8300 CB 보통점검 및 보호계전기 교체","2024-10-14 09:30","2024-10-15 18:00","2024-10-14 09:30","2024-10-15 18:00","연속"]
[18,"경북","영주","신한울N/P #2 Tie-Tr","신한울S/S 765kV #1,2M.Tr 보통점검 공사","신한울S/S 765kV #2M.Tr 보통점검 공사","2024-10-07 09:00","2024-10-11 18:00","취소","취소","연속"]

{"sheet":"345설비","index":1,"n_rows":351,"n_cols":11,"rows_kept":351,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2024년도 10월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 BUS","24년 성동P/O 변전협력회사 공사","CT 집합반 대체","2024-10-01 15:00","2024-10-02 12:00","2024-10-01 15:00","2024-10-02 12:00","연속"]
[2,"서울","성동","성동S/S #1 BUS","24년 성동P/O 변전협력회사 공사","CT 집합반 대체","2024-10-02 12:00","2024-10-02 18:00","2024-10-02 12:00","2024-10-02 18:00","연속"]
[3,"서울","성동","성동S/S #2 M.Tr","2024~25년 성동전력지사 변전협력회사 공사","B/F PNL 대체","2024-10-21 10:00","2024-10-24 18:00","취소","취소","연속"]
[4,"서울","성동","미금성동#2 T/L","2024~25년 성동전력지사 변전협력회사 공사","- B/F PNL 대체","2024-10-21 10:00","2024-10-24 18:00","취소","취소","연속"]
[5,"서울","성동","미금성동#1 T/L","2024~25년 성동전력지사 변전협력회사 공사","- 345kV GIS 보통점검","2024-10-25 09:00","2024-10-25 18:00","2024-10-25 09:00","2024-10-25 18:00","연속"]
[6,"서울","성동","성동S/S #1 BUS","24년 성동P/O 변전협력회사 공사","CT 집합반 대체","2024-10-01 10:00","2024-10-01 15:00","2024-10-01 10:00","2024-10-01 15:00","연속"]
[7,"서울","중부","양주중부#2 T/L","수색S/S 옥내화관련 송전선로 지중화 정비공사","철탑 2기(154kV 수색은평 No.22,23) 신설, 9기(154kV 수색은평 No.22~27, 원흥수색 No.3~5) 철거, 향동C/H(345kV 양주중부 No,27.99) 높이 상향","2024-10-07 07:00","2024-11-30 18:00","2024-10-07 07:00","2024-11-30 18:00","연속"]
[8,"서울","중부","중부S/S CB 7171","2024년 중부전력지사 변전정비 협력회사 총액공사","GIS 보통점검","2024-10-04 10:00","2024-10-04 18:00","취소","취소","연속"]
[9,"서울","중부","중부S/S CB 7300","2024년 중부전력지사 변전정비 협력회사 총액공사","유압동작카운터 교체","2024-10-02 10:00","2024-10-02 18:00","2024-10-02 10:00","2024-10-02 18:00","연속"]
[10,"서울","중부","중부S/S #3 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(4차)","- 154kV GIS 교체(중부용산#2T/L) 관련 시험가압 설비","2024-10-22 17:00","2024-10-23 09:00","2024-10-22 17:00","2024-10-23 09:00","연속"]
[11,"서울","중부","중부S/S #3 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(4차)","- 154kV GIS 교체(중부용산#2T/L) 관련 시험가압 설비","2024-10-30 17:00","2024-10-31 09:00","2024-10-30 17:00","2024-10-31 09:00","연속"]
[12,"서울","중부","중부S/S #3 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV GIS 교체(#2M.Tr 2차, 중부연대T/L, 중부마포T/L) 관련 시험가압 설비","2024-10-02 17:00","2024-10-04 09:00","2024-10-04 17:00","2024-10-07 09:00","연속"]
[13,"서울","중부","중부S/S #2 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(4차)","SEC DS 개방 후 #61, #66BUS 절체용 휴전","2024-10-21 09:00","2024-10-21 09:10","2024-10-21 09:00","2024-10-21 09:10","연속"]
[14,"서울","중부","중부S/S #2 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(4차)","SEC DS 개방 후 #61, #66BUS 절체용 휴전","2024-10-31 09:00","2024-10-31 09:10","2024-10-31 09:00","2024-10-31 09:10","연속"]
[15,"서울","중부","중부S/S #2 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(4차)","SEC DS 개방 후 #61, #66BUS 절체용 휴전","2024-10-23 09:00","2024-10-23 09:10","2024-10-23 09:00","2024-10-23 09:10","연속"]
[16,"남서울","강남","신성남신양재#1 T/L","345kV 신성남-신양재T/L 유지접속함(8상) 교체공사 2차분","○ 345kV 신성남-신양재T/L 잔여 유지접속함 8상 추가 교체 - J/B#24번 : #1T/L A,B,C상(완료) - J/B#18번 : #2T/L A,B,C상(9~10월), #1T/L B,C상(10~12월)","2024-10-21 09:00","2024-12-06 18:00","2024-10-21 09:00","2024-11-30 18:00","연속"]
[17,"남서울","동서울","동서울S/S #2 M.Tr","345kV 동서울#2S/S 건설공사","변압기 권선온도계 및 3차 EGIS 점검","2024-10-21 09:00","2024-10-22 18:00","2024-10-21 09:00","2024-10-22 18:00","연속"]
[18,"남서울","동서울","동서울S/S #3 M.Tr","24~25년도 동서울전력지사 변전협력회사 총액공사","동서울S/S #3M.Tr 부싱절연유 채유","2024-10-17 10:00","2024-10-17 11:00","2024-10-17 10:00","2024-10-17 11:00","연속"]
[19,"남서울","동서울","동서울S/S SEC CB 70710","345kV 동서울S/S 종합정비공사","○ 500kV 동서울변환소 부지확보 관련 사전정비공사 - 345kV GIS 제어케이블 이설","2024-10-01 09:00","2024-10-31 18:00","2024-10-04 09:00","2024-10-31 18:00","연속"]
[20,"남서울","동서울","신성남동서울#2 T/L","345kV 동서울S/S 종합정비공사","○ 500kV 동서울변환소 부지확보 관련 사전정비공사 - 345kV GIS 제어케이블 이설","2024-10-01 09:00","2024-10-31 18:00","2024-10-04 09:00","2024-10-31 18:00","연속"]
[21,"남서울","영등포","신시흥신광명#2 T/L","345kV 시흥장현 지중화 관련공사","동측,서측C/T건물 가공선로 애자장치 지지용 H빔 보강작업","2024-10-14 09:00","2024-10-18 18:00","취소","취소","연속"]
[22,"남서울","영등포","신광명S/S CB 7172","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","- 345kV 63kA GIS 27CB 설치 - 기타 부대공사","2024-10-19 09:00","2025-03-31 18:00","취소","취소","연속"]
[23,"남서울","영등포","신광명S/S #2 M.Tr","2024~25년 영등포전력지사 변전협력회사 총액공사","신광명SS #2M.TR 하자점검","2024-10-28 09:00","2024-11-01 18:00","2024-09-30 09:00","2024-10-02 18:00","연속"]
[24,"남서울","영등포","신광명S/S #75 BUS","345kV 신광명S/S GIS 용량대체 및 S/W 증설공사","- 345kV 63kA GIS 대체 27CB - 옥외 철구 모선 및 차단기, 단로기 철거 - 기기기초 등 기타 부대공사 1식","2024-10-19 09:00","2024-12-27 18:00","취소","취소","연속"]
[25,"남서울","영등포","신시흥신광명#1 T/L","345kV 시흥장현 지중화 관련공사","동측,서측C/T건물 가공선로 애자장치 지지용 H빔 보강작업","2024-10-19 09:00","2024-10-23 18:00","2024-10-19 09:00","2024-10-23 18:00","연속"]
[26,"남서울","직할","신문래S/S #3 M.Tr","345kV GIS 제작사 점검 및 보수","345kV GIS 제작사 점검 및 보수","2024-10-29 09:00","2024-10-30 18:00","2024-10-29 09:00","2024-10-30 18:00","연속"]
[27,"인천","김포","가정개폐소 CB 7472","가정개폐소 345kV 가정-갈산#1T/L GIS 보통점검","가정개폐소 345kV 가정-갈산#1T/L GIS 보통점검 (7472)","2024-10-15 10:00","2024-10-15 18:00","2024-10-15 10:00","2024-10-15 18:00","연속"]
[28,"인천","김포","가정개폐소 CB 7200","가정개폐소 345kV 가정-갈산#3T/L TIE GIS 보통점검","가정개폐소 345kV 가정-갈산#3T/L TIE GIS 보통점검 (7200)","2024-10-14 10:00","2024-10-14 18:00","2024-10-14 10:00","2024-10-14 18:00","연속"]
[29,"인천","김포","가정개폐소 CB 7400","가정개폐소 345kV 가정-갈산#1T/L TIE GIS 보통점검","가정개폐소 345kV 가정-갈산#1T/L TIE GIS 보통점검 (7400)","2024-10-16 10:00","2024-10-16 18:00","2024-10-16 10:00","2024-10-16 18:00","연속"]
[30,"인천","김포","신김포S/S #2 M.Tr","신김포S/S 345kV #2 M.Tr 1차 GIS 보통점검","신김포S/S 345kV #2 M.Tr 1차 GIS 보통점검 (병행) M.Tr 3차 피뢰기 절연열화 측정","2024-10-10 10:00","2024-10-10 18:00","2024-10-10 10:00","2024-10-10 18:00","연속"]
[31,"인천","김포","신김포신파주#2 T/L","24년 가공송전설비 순시점검 위탁공사","가공송전설비 정밀점검","2024-10-16 09:00","2024-10-16 18:00","2024-10-16 09:00","2024-10-16 18:00","연속"]
[32,"인천","김포","신김포S/S #1 M.Tr","신김포S/S 345kV #1M.Tr 1차 GIS 보통점검","신김포S/S 345kV #1M.Tr 1차 GIS 보통점검","2024-10-08 09:00","2024-10-08 18:00","2024-10-08 09:00","2024-10-08 18:00","연속"]
[33,"인천","김포","신김포신파주#1 T/L","24년 가공송전설비 순시점검 위탁공사","가공송전설비 정밀점검","2024-10-17 09:00","2024-10-18 18:00","2024-10-17 09:00","2024-10-18 18:00","연속"]
[34,"인천","김포","신김포S/S CB 7572","신김포S/S 345kV 신김포-서인천CC T/L GIS 보통점검","신김포S/S 345kV 신김포-서인천CC T/L GIS 보통점검 (7572)","2024-10-22 10:00","2024-10-22 18:00","2024-10-22 10:00","2024-10-22 18:00","연속"]
[35,"인천","부평","서인천CC신부평#1 T/L","서인천C/C 7A BaY B/F 보호반 대체공사","서인천C/C 7A BaY B/F 보호반 대체공사","2024-10-08 09:00","2024-10-11 18:00","2024-10-08 09:00","2024-10-11 18:00","연속"]
[36,"인천","부평","서인천CC신부평#4 T/L","서인천S/Y 7A Bay B/F보호반 대체공사","서인천S/Y 7A Bay B/F보호반 대체공사","2024-10-08 09:00","2024-10-11 18:00","2024-10-08 09:00","2024-10-11 18:00","연속"]
[37,"인천","부평","신가좌S/S CB 7272","신가좌S/S 345kV 신가좌신시흥#1T/L 7272GIS 조작시험","신가좌S/S 345kV 신가좌신시흥#1T/L 7272GIS 조작시험","2024-10-24 09:00","2024-10-24 18:00","2024-10-24 09:00","2024-10-24 18:00","연속"]
[38,"인천","부평","신가좌가정#2 T/L","신가좌S/S 신가좌가정#2T/L CLR TOP HAY 볼트교체","신가좌S/S 신가좌가정#2T/L CLR TOP HAY 볼트교체","2024-10-25 09:00","2024-10-25 18:00","2024-10-25 09:00","2024-10-25 18:00","연속"]
[39,"인천","부평","신가좌S/S CB 7200","신가좌S/S 345kV 7200GIS 조작시험","신가좌가정#1-신가좌신시흥#1T/L TIE 7200GIS 조작시험","2024-10-14 12:00","2024-10-14 18:00","2024-10-14 12:00","2024-10-14 18:00","연속"]
[40,"인천","부평","신가좌S/S CB 7472","신가좌S/S #3 M.Tr 1차 7472GIS 조작시험","신가좌S/S #3 M.Tr 1차 7472GIS 조작시험","2024-10-14 09:00","2024-10-14 12:00","2024-10-14 09:00","2024-10-14 12:00","연속"]
[41,"인천","부평","신가좌S/S CB 7271","신가좌S/S 345kV 신가좌-가정#1T/L GIS 조작시험","신가좌S/S 345kV 신가좌-가정#1T/L GIS 조작시험","2024-10-05 09:00","2024-10-05 18:00","2024-10-05 09:00","2024-10-05 18:00","연속"]
[42,"인천","부평","신경서인천CC#2 T/L","신경서S/S 신경서인천CC#2T/L CLR TOP HAY 볼트교체","신경서S/S 신경서인천CC#2T/L CLR TOP HAY 볼트교체","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[43,"인천","부평","신경서S/S CB 7171","신경서S/S 345kV 신경서-신인천CCT/L 7171GIS 조작시험","신경서S/S 345kV 신경서-신인천CCT/L 7171GIS 조작시험","2024-10-26 09:00","2024-10-26 18:00","2024-10-26 09:00","2024-10-26 18:00","연속"]
[44,"인천","부평","신경서포스코CC#2 T/L","신경서포스코SY#2 T/L 보호반 대체 공사","신경서포스코SY#2 T/L 보호반 대체 공사","2024-10-21 09:00","2024-10-25 18:00","2024-10-21 09:00","2024-10-25 18:00","연속"]
[45,"인천","부평","신경서포스코CC#1 T/L","신경서포스코SY#1 T/L 보호반 대체 공사","신경서포스코SY#1 T/L 보호반 대체 공사","2024-10-14 09:00","2024-10-18 18:00","2024-10-14 09:00","2024-10-18 18:00","연속"]
[46,"인천","부평","신인천C/C CB 7772","신인천C/C 345kV 4MT101 7772GIS 조작시험","신인천C/C 345kV 4MT101 7772GIS 조작시험","2024-10-19 12:00","2024-10-19 15:00","2024-10-19 12:00","2024-10-19 15:00","연속"]
[47,"인천","부평","신인천C/C SEC CB 71720","신인천C/C 345kV #71-#72 SEC GIS 조작시험","신인천C/C 345kV #71-#72 SEC GIS 조작시험","2024-10-05 09:00","2024-10-05 18:00","2024-10-05 09:00","2024-10-05 18:00","연속"]
[48,"인천","부평","신인천C/C CB 7672","신인천C/C 345kV 3MT201 7672GIS 조작시험","신인천C/C 345kV 3MT201 GIS 조작시험","2024-10-19 09:00","2024-10-19 12:00","2024-10-19 09:00","2024-10-19 12:00","연속"]
[49,"인천","시흥","신시화S/S #2 BUS","신시화S/S 345kV GIS 설치공사","345kV #4M.Tr, #2Sh.R용 차단기 설치 - 63kA, 6,300A 차단기 2CB 설치 - GIB 설치 및 기타부대공사","2024-10-01 09:00","2024-11-10 18:00","2024-10-01 09:00","2024-11-10 18:00","연속"]
[50,"인천","시흥","신시흥신광명#1 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","암교체, 고정형폴리머점퍼지지애자 설치 ＊ 하자조치 병행작업","2024-10-19 07:30","2024-10-23 18:00","취소","취소","매일"]
[51,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥S/S #2M.Tr 2차 GIS 베어링 교체","신시흥S/S #2M.Tr 2차 GIS 베어링 부품 교체","2024-10-01 09:00","2024-10-01 18:00","2024-10-01 09:00","2024-10-01 18:00","연속"]
[52,"인천","시흥","신가좌신시흥#1 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","암교체, 고정형폴리머점퍼지지애자 설치 ＊ 하자조치 병행작업","2024-10-19 07:30","2024-10-23 18:00","2024-10-19 07:30","2024-10-23 18:00","매일"]
[53,"인천","시흥","신시흥신광명#2 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","암교체, 고정형폴리머점퍼지지애자, 피뢰기 설치 ＊ 하자조치 병행작업","2024-10-26 07:30","2024-10-31 18:00","2024-10-26 07:30","2024-10-31 18:00","매일"]
[54,"인천","시흥","신가좌신시흥#2 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","암교체, 고정형폴리머점퍼지지애자, 피뢰기 설치 ＊ 하자조치 병행작업","2024-10-26 07:30","2024-10-31 18:00","2024-10-26 07:30","2024-10-31 18:00","매일"]
[55,"인천","직할","서인천CC신부평#3 T/L","23~24년 지중송전설비 위탁정비공사","구형 SVL 교체","2024-10-21 08:00","2024-10-25 18:00","2024-10-21 08:00","2024-10-25 18:00","연속"]
[56,"인천","부평","신가좌신시흥#2 T/L"," 신가좌S/S 신가좌-신시흥#2T/L GIS 정밀점검","신가좌S/S 신가좌-신시흥#2T/L GIS 정밀점검","2024-10-02 08:00","2024-10-06 18:00","취소","취소","연속"]
[57,"인천","부평","포스코CC인천CC#2 T/L"," 포스코S/Y 72Bay B/F 보호반대체","포스코S/Y #72Bay B/F 보호반 대체 공사 (포스코5,6호기 휴전 병행)","2024-10-04 09:00","2024-10-07 18:00","2024-10-04 09:00","2024-10-07 18:00","연속"]
[58,"인천","부평","포스코C/C CB 7272"," 포스코S/Y #72Bay B/F 보호반 대체 공사","포스코S/Y #72Bay B/F 보호반대체 (포스코5,6호기 휴전 병행)","2024-10-04 09:00","2024-10-07 18:00","2024-10-04 09:00","2024-10-07 18:00","연속"]
[59,"경기북부","고양","신덕은S/S #1 M.Tr","24-25년 고양변전협력 총액공사","#1S.Tr 교체 공사 관련 주변압기 휴전","2024-10-01 09:00","2024-10-02 18:00","2024-10-17 09:00","2024-10-18 18:00","연속"]
[60,"경기북부","구리","포천C/C CB 7200","2024~25년 구리전력 변전협력회사 공사","포천C/C #2S/U - #3S/U 7200 SF6가스압력계 불량분 교체 및 조작시험","2024-10-02 09:00","2024-10-02 18:00","2024-10-02 09:00","2024-10-02 18:00","연속"]
[61,"경기북부","구리","신가평포천LNGCC#1 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 74bay 측 주모선 철거 안전이격 345kV #7452 DS 철거 안전이격","2024-10-02 13:00","2024-10-07 08:00","2024-10-02 13:00","2024-10-07 08:00","연속"]
[62,"경기북부","직할","양주S/S STATCOM CB","24-25년 변전 직할 협력회사 총액공사","STATCOM 1차 절연열화 측정(절연열화 와트값 기준치 초과)","2024-10-04 10:00","2024-10-04 17:00","2024-10-04 10:00","2024-10-04 17:00","연속"]
[63,"경기북부","직할","양주S/S #1 BUS","24-25년 변전 직할 협력회사 총액공사","STATCOM 1차 GIS(절연열화 측정) 인접설비 휴전","2024-10-04 10:00","2024-10-04 17:00","2024-10-04 10:00","2024-10-04 17:00","연속"]
[64,"경기북부","구리","신가평포천LNGCC#2 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 73bay 측 주모선 철거 및 설치 안전이격 345kV #7352 DS 철거 및 설치 안전이격","2024-10-07 08:00","2024-10-14 08:00","2024-10-07 08:00","2024-10-14 08:00","연속"]
[65,"경기북부","고양","신덕은S/S #2 M.Tr","24-25년 고양변전협력 총액공사","#2S.Tr 교체 공사 관련 주변압기 휴전","2024-10-07 09:00","2024-10-08 18:00","2024-10-21 09:00","2024-10-22 18:00","연속"]
[66,"경기북부","직할","신의정부양주#1 T/L","24-25년 직할 변전협력회사 총액공사","신의정부S/S 신의정부-양주#1T/L #1CLR GIS 초기점검","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[67,"경기북부","직할","신의정부양주#2 T/L","24-25년 직할 변전협력회사 총액공사","신의정부S/S 신의정부-양주#2T/L #2CLR GIS 초기점검","2024-10-08 09:00","2024-10-08 18:00","2024-10-08 09:00","2024-10-08 18:00","연속"]
[68,"경기북부","구리","신가평포천LNGCC#1 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 74bay 측 주모선 설치 안전이격 345kV #7452 DS 설치 안전이격","2024-10-14 08:00","2024-10-18 08:00","2024-10-14 08:00","2024-10-18 08:00","연속"]
[69,"경기북부","구리","신가평신의정부#2 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 75bay 측 주모선 설치 안전이격 345kV #7552 DS 설치 안전이격","2024-10-14 08:00","2024-10-23 08:00","2024-10-14 08:00","2024-10-23 08:00","연속"]
[70,"경기북부","직할","신포천동두천CC#1 T/L","24-25년 직할 변전협력회사 총액공사","- 동두천C/C 362kV GIS 7500 보통점검 - 동두천C/C 신포천-동두천CC#1T/L CLR 보통점검","2024-10-14 09:00","2024-10-15 18:00","2024-10-14 09:00","2024-10-15 18:00","연속"]
[71,"경기북부","직할","동두천C/C CB 7572","24-25년 직할 변전협력회사 총액공사","동두천C/C 362kV GIS 7572 보통점검","2024-10-14 09:00","2024-10-15 18:00","2024-10-14 09:00","2024-10-15 18:00","연속"]
[72,"경기북부","고양","신파주S/S #1 M.Tr","신파주S/S 장기사용 노후 배전반 교체","신파주S/S #1M.Tr 보호반, 72 Bay B/F 보호반 교체","2024-10-14 09:00","2024-10-18 18:00","2024-10-14 09:00","2024-10-18 18:00","연속"]
[73,"경기북부","직할","양주S/S #1 M.Tr","24-25년 변전협력회사 총액공사","보통점검 및 OLTC 절연유 교체","2024-10-14 09:00","2024-10-18 18:00","2024-10-14 09:00","2024-10-18 18:00","연속"]
[74,"경기북부","직할","신덕은동두천CC#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 불량애자교체","2024-10-15 07:00","2024-10-15 13:00","취소","취소","연속"]
[75,"경기북부","직할","신포천동두천CC#2 T/L","24-25년 직할 변전협력회사 총액공사","- 동두천C/C 362kV GIS 7600 보통점검 - 동두천C/C 신포천-동두천CC#2T/L CLR 보통점검","2024-10-17 09:00","2024-10-18 18:00","2024-10-17 09:00","2024-10-18 18:00","연속"]
[76,"경기북부","직할","동두천C/C CB 7672","24-25년 직할 변전협력회사 총액공사","- 동두천C/C 362kV GIS 7672 보통점검","2024-10-17 09:00","2024-10-18 18:00","2024-10-17 09:00","2024-10-18 18:00","연속"]
[77,"경기북부","고양","신덕은동두천CC#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치(수평) 설치","2024-10-21 07:00","2024-10-31 17:00","취소","취소","매일"]
[78,"경기북부","고양","신파주양주#2 T/L","신파주S/S 장기사용 노후 배전반 교체","신파주S/S #3M.Tr 보호반, 74 Bay B/F, 신파주-양주#2T/L 보호반 교체","2024-10-21 09:00","2024-10-30 18:00","취소","취소","연속"]
[79,"경기북부","고양","신파주S/S #3 M.Tr","신파주S/S 장기사용 노후 배전반 교체","신파주S/S #3M.Tr 보호반, 74 Bay B/F, 신파주-양주#2T/L 보호반 교체","2024-10-21 09:00","2024-10-30 18:00","2024-10-21 09:00","2024-10-30 18:00","연속"]
[80,"경기북부","구리","신가평신의정부#1 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 76bay 측 주모선 설치 안전이격 345kV #7652 DS 설치 안전이격","2024-10-23 08:00","2024-10-28 08:00","2024-10-23 08:00","2024-10-28 08:00","연속"]
[81,"경기북부","구리","신가평미금#1 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 77bay 측 주모선 설치 안전이격 345kV #7752 DS 설치 안전이격","2024-10-28 08:00","2024-11-01 08:00","2024-10-28 08:00","2024-11-01 08:00","연속"]
[82,"경기","군포","서서울#2S/S #6 M.Tr","서서울2S/S #6M.Tr 본체, 2차 GIS 보통점검 등","서서울2S/S #6M.Tr 본체 보통점검, 96D 커버 설치, CVT 하자점검, 2차 GIS(6644) 보통점검, 3차 VCB(4679) 보통점검, 3차 PT 보통점검","2024-10-19 09:00","2024-10-20 18:00","2024-10-19 09:00","2024-10-20 18:00","연속"]
[83,"경기","군포","서서울#2S/S #5 M.Tr","서서울2S/S #5M.Tr 본체, 2차 GIS 보통점검 등","서서울2S/S #5M.Tr 본체 보통점검, 96D 커버 설치, CVT 하자점검, 2차 GIS(6544) 보통점검","2024-10-12 09:00","2024-10-13 18:00","2024-10-12 09:00","2024-10-13 18:00","연속"]
[84,"경기","군포","서서울S/S #1 M.Tr","서서울S/S #1M.Tr 1차 GIS(7300,7372) 조작시험 등","서서울S/S #1M.Tr 1차 GIS(7300,7372) 조작시험, 3차 VCB(4179) 조작, S.Tr VCB(4189) 보통점검, 3차 PT 대체, #1-1Sh.R 보통점검, 23kV #1S.Tr 대체","2024-10-30 09:00","2024-10-31 18:00","2024-10-30 09:00","2024-10-31 18:00","연속"]
[85,"경기","군포","서서울S/S CB 7472","서서울S/S 신온양-서서울#1T/L 7472 GIS 조작시험","서서울S/S 신온양-서서울#1T/L 7472 GIS 조작시험 및 결상회로개선","2024-10-25 09:00","2024-10-25 14:00","2024-10-25 09:00","2024-10-25 14:00","연속"]
[86,"경기","군포","화성서서울#2 T/L","24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 345kV 화성-서서울#2T/L 62기 186SET","2024-10-16 07:00","2024-10-25 18:00","2024-10-16 07:00","2024-10-25 18:00","연속"]
[87,"경기","군포","화성서서울#1 T/L","24-25년 군포 가공송전협력회사 공사","이도조정(No.38~40, 49~50)","2024-10-28 07:00","2024-10-29 18:00","2024-10-28 07:00","2024-10-29 18:00","연속"]
[88,"경기","군포","신시흥신안산#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 5기","2024-10-07 07:00","2024-10-07 18:00","2024-10-07 07:00","2024-10-07 18:00","연속"]
[89,"경기","군포","화성신안산#1 T/L","24-25년 군포 가공송전협력회사 공사","이도조정(No.25~27)","2024-10-23 07:00","2024-10-25 18:00","2024-10-23 07:00","2024-10-25 18:00","연속"]
[90,"경기","군포","신시흥신안산#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 5기","2024-10-08 07:00","2024-10-08 18:00","2024-10-08 07:00","2024-10-08 18:00","연속"]
[91,"경기","동부","곤지암여주복합#2 T/L","345kV 신용인-동서울등 16개T/L 추락방지장치 설치공사","추락방지장치 설치 80기(잔여 7기)","2024-10-27 07:00","2024-10-27 18:00","취소","취소","연속"]
[92,"경기","동부","곤지암여주복합#1 T/L","345kV 신용인-동서울등 16개T/L 추락방지장치 설치공사","추락방지장치 설치 80기(잔여 18기)","2024-10-26 07:00","2024-10-26 18:00","취소","취소","연속"]
[93,"경기","동부","곤지암S/S #4 M.Tr","24-25년 동부 변전정비 총액공사","곤지암:6444(메커니즘 점검))","2024-10-16 09:30","2024-10-16 14:00","2024-10-16 09:30","2024-10-16 14:00","연속"]
[94,"경기","동부","신충주T신충주 T/L","2024-2025년 성남전력지사 가공송전 협력회사공사","가공지선 정비 신제천-여주복합T/L(신충주T분기) 33~34, 35~36호","2024-10-03 09:00","2024-10-04 18:00","취소","취소","연속"]
[95,"경기","동부","신충주T신충주 T/L","2024-2025년 성남전력지사 가공송전 협력회사공사","가공지선 정비 신제천-여주복합T/L(신충주T분기) 33~34, 35~36호","2024-10-03 09:00","2024-10-04 18:00","취소","취소","연속"]
[96,"경기","동부","신충주여주복합#2 T/L","345kV 신용인-동서울등 16개T/L 추락방지장치 설치공사","추락방지장치 설치 39기","2024-10-05 07:00","2024-10-06 18:00","취소","취소","연속"]
[97,"경기","성남","신성남S/S #2 M.Tr","신성남S/S 154kV #1,2,3,4Sh.R 설치사업","· 기초매트 철근, 거푸집, 방호벽 설치 · 공사 시 활선 안전이격 확보","2024-10-29 16:00","2024-11-29 16:00","2024-11-01 16:00","2024-11-29 16:00","연속"]
[98,"경기","성남","신안성신수원#2 T/L","24-25년 경기본부 직할 송전협력회사 공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)","2024-10-10 07:00","2024-10-30 18:00","2024-10-10 07:00","2024-10-30 18:00","연속"]
[99,"경기","성남","신안성서안성#1 T/L","24-25년 경기본부 직할 송전협력회사 공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)","2024-10-10 07:00","2024-10-16 18:00","2024-10-10 07:00","2024-10-16 18:00","연속"]
[100,"경기","성남","신안성S/S CB 7C71","2024년 성남전력 변전협력회사 총액공사","7C71 GIS 절연열화 측정","2024-10-02 09:00","2024-10-02 11:00","2024-10-02 09:00","2024-10-02 11:00","연속"]
[101,"경기","성남","신안성서안성#2 T/L","24-25년 경기본부 직할 송전협력회사 공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)","2024-10-31 07:00","2024-11-05 18:00","2024-10-31 07:00","2024-11-05 18:00","연속"]
[102,"경기","성남","신안성신수원#1 T/L","24-25년 경기본부 직할 송전협력회사 공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)","2024-10-31 07:00","2024-11-13 18:00","2024-10-31 07:00","2024-11-13 18:00","연속"]
[103,"경기","성남","신용인S/S #4 M.Tr","2024년 성남전력 345, 154 GIS 보통점검공사","7800, 7872 GIS 보통점검","2024-10-16 09:00","2024-10-17 18:00","취소","취소","연속"]
[104,"경기","성남","신안성신용인#1 T/L","2024년 성남전력 765 GIS 보통, 345 GIS 정밀점검공사","7471, 7400 GIS 정밀점검","2024-10-01 09:00","2024-10-08 18:00","2024-10-01 09:00","2024-10-08 18:00","연속"]
[105,"경기","직할","화성S/S #1 M.Tr","2024-25년 경기본부 직할 변전협력회사 공사","화성: #1M.Tr 보호반 대체(~20)","2024-10-17 09:00","2024-10-20 18:00","2024-10-17 09:00","2024-10-20 18:00","연속"]
[106,"경기","평택","고덕#2서안성#2 T/L","345kV 고덕2서안성#2 TL 조류착지방지장치 설치(1~29호)","2024~2025 평택전력 송전정비 협력회사 공사 조류착지방지장치설치 345kV 고덕2서안성#2 TL 조류착지방지장치 설치(1~29호)","2024-10-23 13:00","2024-10-25 18:00","2024-10-23 13:00","2024-10-25 18:00","연속"]
[107,"경기","평택","고덕#2서안성#1 T/L","345kV 고덕2서안성#1 TL 조류착지방지장치 설치(1~29호)","2024~2025 평택전력 송전정비 협력회사 공사 조류착지방지장치설치 345kV 고덕2서안성#1 TL 조류착지방지장치 설치(1~29호)","2024-10-21 08:00","2024-10-23 13:00","2024-10-21 08:00","2024-10-23 13:00","연속"]
[108,"경기","평택","평택T/P CB 7571","평택T/P 345kV GIS 보통점검","평택T/P 345kV 화성-평택T/P#2T/L 1차 GIS(7571) 보통점검","2024-10-02 09:00","2024-10-02 14:00","2024-10-02 09:00","2024-10-02 14:00","연속"]
[109,"경기","평택","평택T/P CB 7572","평택T/P 345kV GIS 보통점검","평택T/P 345kV #1-2ST-Tr 1차 GIS(7572) 보통점검","2024-10-02 14:00","2024-10-02 18:00","2024-10-02 14:00","2024-10-02 18:00","연속"]
[110,"강원","강릉","안인개폐소신양양 T/L","2024-2025년 강릉전력지사 송전협력회사 공사","○ 수평 추락방지장치 설치 : 345kV 양양양수T/L No.4~192","2024-10-14 08:00","2024-10-31 18:00","2024-10-14 08:00","2024-10-31 18:00","매일"]
[111,"강원","강릉","신양양양양PP T/L","2024-2025년 강릉전력지사 송전협력회사 공사","○ 수평 추락방지장치 설치 : 345kV 양양양수T/L No.1, 2","2024-10-07 08:00","2024-10-07 18:00","취소","취소","연속"]
[112,"강원","동해","동해S/S CB 7200","2024~2025년 동해전력지사 변전협력회사 공사","균압콘덴서측정, CB조작시험","2024-10-16 11:00","2024-10-16 14:00","2024-10-16 11:00","2024-10-16 14:00","연속"]
[113,"강원","동해","동해안인개폐소#2 T/L","345kV 동해-안인개폐소T/L 국산불량애자교체공사","○ 국산불량애자교체공사","2024-10-07 07:00","2024-10-12 18:00","2024-10-07 07:00","2024-10-12 18:00","연속"]
[114,"강원","동해","동해S/S CB 7371","2024~2025년 동해전력지사 변전협력회사 공사","균압콘덴서측정, CB조작시험","2024-10-16 14:00","2024-10-16 16:00","2024-10-16 14:00","2024-10-16 16:00","연속"]
[115,"강원","동해","동해S/S CB 7472","2024~2025년 동해전력지사 변전협력회사 공사","균압콘덴서측정, CB조작시험","2024-10-16 16:00","2024-10-16 18:00","취소","취소","연속"]
[116,"강원","동해","동해S/S CB 7171","2024~2025년 동해전력지사 변전협력회사 공사","균압콘덴서측정, CB조작시험","2024-10-16 09:00","2024-10-16 11:00","취소","취소","연속"]
[117,"강원","동해","삼척G/P #2 Tie-Tr","2024~2025년 동해전력지사 변전협력회사 공사","2차GIS 보통점검","2024-10-14 09:00","2024-10-15 18:00","취소","취소","연속"]
[118,"강원","동해","삼척G/P #3 Tie-Tr","2024~2025년 동해전력지사 변전협력회사 공사","2차GIS 보통점검","2024-10-21 09:00","2024-10-22 18:00","취소","취소","연속"]
[119,"강원","태백","신태백S/S CB 7372","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S 345kV 7372CB 보통점검","2024-10-21 09:00","2024-10-21 18:00","2024-10-21 09:00","2024-10-21 18:00","연속"]
[120,"강원","태백","신태백S/S CB 7472","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S 345kV 7472CB 보통점검","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[121,"강원","태백","신태백S/S CB 7400","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S 345kV 7400CB 보통점검","2024-10-01 09:00","2024-10-01 18:00","2024-10-01 09:00","2024-10-01 18:00","연속"]
[122,"강원","태백","신태백S/S CB 7672","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S 345kV 7672CB 보통점검","2024-10-22 09:00","2024-10-22 18:00","2024-10-22 09:00","2024-10-22 18:00","연속"]
[123,"충북","직할","신중부남청주#1 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-10-07 07:00","2024-10-11 18:00","2024-10-07 07:00","2024-10-11 18:00","연속"]
[124,"충북","직할","신중부남청주#1 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-10-14 07:00","2024-10-18 18:00","2024-10-14 07:00","2024-10-18 18:00","연속"]
[125,"충북","직할","신중부남청주#2 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-10-21 07:00","2024-10-25 18:00","2024-10-21 07:00","2024-10-25 18:00","연속"]
[126,"충북","직할","신중부남청주#2 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-10-28 07:00","2024-11-01 18:00","2024-10-28 07:00","2024-11-01 18:00","연속"]
[127,"충북","직할","신진천S/S #4 M.Tr","24-25년 충북 직할 변전협력회사 공사","- 신진천S/S 345kV #4M.Tr 및 관련기기 보통점검","2024-10-14 09:00","2024-10-17 18:00","2024-10-14 09:00","2024-10-17 18:00","연속"]
[128,"충북","직할","신진천S/S #4 M.Tr","'24년 충북본부 직할 154kV GIS 정밀점검공사","신진천S/S 154kV #4Sh.C GIS 정밀점검 후 무부하가압용","2024-10-18 09:00","2024-10-18 10:00","2024-10-18 09:00","2024-10-18 10:00","연속"]
[129,"충북","청주","남청주S/S #2 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-10-01 08:00","2024-10-19 18:00","취소","취소","연속"]
[130,"충북","청주","신옥천세종#2 T/L","345kV 신옥천-북경남등 8개T/L 추락방지장치 설치공사","공사개요 : 신옥천세종#2T/L 추락방지장치 수평설치 공사장소 : 신옥천세종#2T/L No.1~48(55기)","2024-10-15 07:00","2024-10-19 18:00","취소","취소","매일"]
[131,"충북","청주","신옥천세종#1 T/L","345kV 신옥천-북경남등 8개T/L 추락방지장치 설치공사","공사개요 : 신옥천세종#1T/L 추락방지장치 수평설치 공사장소 : 신옥천세종#1T/L No.1~48(55기)","2024-10-07 07:00","2024-10-14 18:00","취소","취소","매일"]
[132,"충북","충주","신제천S/S CB 7271","'24-25년 충주전력지사 변전정비 총액공사","GIS 보통점검 및 [유사고장]345kV 차단기 콘덴서 절연열화 측정[7271 CB]","2024-10-18 09:00","2024-10-18 18:00","2024-10-18 09:00","2024-10-18 18:00","연속"]
[133,"충북","충주","신제천S/S CB 7971","[유사고장]345kV 차단기 콘덴서 절연열화 측정[7971 CB]","[유사고장]345kV 차단기 콘덴서 절연열화 측정[7971 CB]","2024-10-21 09:00","2024-10-21 14:00","2024-10-21 09:00","2024-10-21 14:00","연속"]
[134,"충북","충주","신제천S/S CB 7900","[유사고장]345kV 차단기 콘덴서 절연열화 측정[7900 CB]","[유사고장]345kV 차단기 콘덴서 절연열화 측정[7900 CB]","2024-10-21 14:00","2024-10-21 18:00","2024-10-21 14:00","2024-10-21 18:00","연속"]
[135,"충북","충주","신제천S/S CB 7200","'24-25년 충주전력지사 변전정비 총액공사","GIS 보통점검 및 [유사고장]345kV 차단기 콘덴서 절연열화 측정[7200 CB]","2024-10-22 14:00","2024-10-22 18:00","2024-10-22 14:00","2024-10-22 18:00","연속"]
[136,"충북","충주","신제천S/S #2 M.Tr","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 345kV #2M.Tr 부싱 절연열화 측정 및 부싱절연유 채유","2024-10-04 10:00","2024-10-04 14:00","2024-10-04 10:00","2024-10-04 14:00","연속"]
[137,"충북","충주","신제천S/S #4 M.Tr","[유사고장]362kV GIS 차단부 콘덴서 절연열화 측정","[유사고장]362kV GIS 차단부 콘덴서 절연열화 측정[7A00,7A72CB]","2024-10-31 10:00","2024-10-31 17:00","2024-10-31 10:00","2024-10-31 17:00","연속"]
[138,"충북","충주","신제천신영주#2 T/L","345kV 신제천-신영주T/L OPGW 낙뢰소손 관련 교체공사","#2T/L No.5~12호 OPGW 3.057km 교체 및 항공구 31개 설치","2024-10-24 09:00","2024-10-27 18:00","취소","취소","연속"]
[139,"충북","충주","신제천S/S #3 M.Tr","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 345kV #3M.Tr 부싱 절연열화 측정 및 부싱절연유 채유","2024-10-04 14:00","2024-10-04 18:00","2024-10-04 14:00","2024-10-04 18:00","연속"]
[140,"충북","충주","신충주S/S #2 M.Tr","'24-25년 충주전력지사 변전정비 총액공사","신충주S/S 345kV #2M.Tr 보통점검","2024-10-28 09:00","2024-10-29 18:00","2024-10-28 09:00","2024-10-29 18:00","연속"]
[141,"대전세종충남","대전","신계룡S/S 예비 M.Tr CB","[즉시가압O]신계룡S/S 345kV 예비 M.Tr 보통점검","[즉시가압O]신계룡S/S 345kV 예비 M.Tr 보통점검","2024-10-14 09:00","2024-10-15 18:00","취소","취소","연속"]
[142,"대전세종충남","대전","신옥천신계룡 T/L","345kV 신옥천-신계룡T/L 지장수목 전지 및 벌채","345kV 신옥천-신계룡T/L 지장수목 전지 및 벌채","2024-10-21 14:00","2024-10-21 18:00","2024-10-21 14:00","2024-10-21 18:00","연속"]
[143,"대전세종충남","서산","당진T/P #71 Tie-Tr","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능)당진화력S/S 345kV #71 Tie.Tr 염해지역 애자코팅 - 병행1 : #71Tie-Tr 1, 2차 LA 초기점검 - 병행2 : #71Tie-Tr 부싱절연유 채유 및 절연열화 진단","2024-10-07 09:30","2024-10-08 18:00","2024-10-07 09:30","2024-10-08 18:00","연속"]
[144,"대전세종충남","서산","북당진S/S #1 BUS","북당진S/S 345kV 북당진-신탕정T/L GIS 설치공사","72BAY 1CB(7271) 설치 73BAY 2CB(7371,7300) 설치","2024-10-21 14:00","2024-10-22 14:00","2024-10-21 14:00","2024-10-22 14:00","연속"]
[145,"대전세종충남","서산","북당진S/S CB 7671","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 북당진S/S 345kV 7671 GIS 보통점검","2024-10-16 09:30","2024-10-17 18:00","2024-10-16 09:30","2024-10-17 18:00","연속"]
[146,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","345kV 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.44~45,64~65,82~85,112~113,123~127(10경간) *즉시가압가능(20분이내) *9월 휴전 승인시 취소 요청 *평일 휴전 불가시 주말만 휴전 요청 주말 휴전 불가시 평일만 휴전 요청","2024-10-14 08:00","2024-10-20 18:00","취소","취소","매일"]
[147,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","‘23년 서산P/O 장기사용 노후 배전반 교체공사","(즉시가압불가)345kV 신당진개폐소-태안화력#1T/L 보호반 교체공사","2024-10-28 09:00","2024-11-01 18:00","2024-10-28 09:00","2024-11-01 18:00","연속"]
[148,"대전세종충남","서산","신당진개폐소북당진 T/L","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능)신당진개폐소 345kV 개폐소-북당진T/L LA 보통점검 - 병행 : CVT 보통점검","2024-10-25 09:30","2024-10-25 18:00","취소","취소","연속"]
[149,"대전세종충남","서산","신당진S/S CB 7772","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신당진S/S 345kV 7772 CB 정밀점검","2024-10-21 09:30","2024-10-25 18:00","2024-10-21 09:30","2024-10-25 18:00","연속"]
[150,"대전세종충남","서산","신당진S/S CB 7700","신당진S/S 345kV 차단기 조작시험","신당진S/S 신당진 연락#2T/L-신서산#2T/L TIE 7700 CB 조작시험","2024-10-08 10:00","2024-10-08 14:00","2024-10-08 10:00","2024-10-08 14:00","연속"]
[151,"대전세종충남","서산","신당진S/S CB 7771","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신당진S/S 345kV 7771 CB 정밀점검","2024-10-14 09:30","2024-10-18 18:00","2024-10-14 09:30","2024-10-18 18:00","연속"]
[152,"대전세종충남","서산","신당진S/S CB 7100","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신당진S/S 345kV 7100 CB 정밀점검","2024-10-28 09:30","2024-11-01 18:00","2024-10-28 09:30","2024-11-01 18:00","연속"]
[153,"대전세종충남","서산","신서산S/S CB 7600","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7600 GIS 보통점검","2024-10-01 09:30","2024-10-02 18:00","2024-10-01 09:30","2024-10-02 18:00","연속"]
[154,"대전세종충남","서산","신서산태안TP#2 T/L","'24~'25년 서산전력지사 송전협력회사 공사","345kV 신서산-태안화력#2T/L 항공구 설치공사 No.39~40, 107~108, 123~124, 131~132 (4경간) *즉시가압가능(20분이내) *평일 휴전 불가시 주말만 휴전 요청 주말 휴전 불가시 평일만 휴전 요청","2024-10-23 08:00","2024-10-27 18:00","2024-10-23 08:00","2024-10-27 18:00","매일"]
[155,"대전세종충남","서산","신서산아산#1 T/L","345kV 신서산-아산#1T/L 항공장애표시구 설치공사","(9월 휴전신청 취소시)[즉시가압가능] 1. 공사대상 : 345kV 신서산-아산#1T/L No. 2~3 항공장애표시구 5개 설치 2. 기타사항 : 미설치 시 항공시설법 위반으로 과태료 부과 대상","2024-10-21 07:00","2024-10-22 17:00","취소","취소","매일"]
[156,"대전세종충남","서산","신서산S/S CB 7671","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신서산S/S 345kV 7671 CB 정밀점검","2024-10-07 09:30","2024-10-11 18:00","2024-10-07 09:30","2024-10-11 18:00","연속"]
[157,"대전세종충남","서산","신서산S/S CB 7500","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7500 GIS 보통점검","2024-10-07 09:30","2024-10-08 18:00","2024-10-07 09:30","2024-10-08 18:00","연속"]
[158,"대전세종충남","서산","신서산신당진#1 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","345kV 신서산-신당진#1T/L 항공장애표시구 설치공사 No.4~6, 35~36 (3경간) *즉시가압가능(20분이내) *9월 휴전 승인시 취소 요청","2024-10-07 08:00","2024-10-08 18:00","취소","취소","매일"]
[159,"대전세종충남","서산","신서산S/S CB 7A00","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7A00 GIS 보통점검","2024-10-10 09:30","2024-10-11 18:00","2024-10-10 09:30","2024-10-11 18:00","연속"]
[160,"대전세종충남","서산","신서산S/S #4 Sh.R CB","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신서산S/S 345kV 7779 GIS 보통점검","2024-10-14 09:30","2024-10-15 18:00","2024-10-14 09:30","2024-10-15 18:00","매일"]
[161,"대전세종충남","서산","태안T/P CB 7A72","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 태안화력S/S 345kV 7A72 GIS 보통점검","2024-10-31 09:30","2024-11-01 18:00","2024-10-31 09:30","2024-11-01 18:00","연속"]
[162,"대전세종충남","서산","태안T/P CB 7772","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7772 CB 균압콘덴서 절연열화 진단","2024-10-11 09:30","2024-10-11 13:00","2024-10-11 09:30","2024-10-11 13:00","연속"]
[163,"대전세종충남","서산","태안T/P CB 7A71","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 태안화력S/S 345kV 7A71 GIS 보통점검","2024-10-23 09:30","2024-10-24 18:00","취소","취소","연속"]
[164,"대전세종충남","서산","태안T/P CB 7A00","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 태안화력S/S 345kV 7A00 GIS 보통점검","2024-10-29 09:30","2024-10-30 18:00","취소","취소","연속"]
[165,"대전세종충남","서산","태안T/P #71 BUS","21년 서산P/O 현대제 345kV GIS 조작로드 교체공사","(즉시가압 불가, 주말작업 포함) 태안화력S/S 345kV 71-72-0 CB 조작로드 교체공사 - * 병행작업 : 7551DS C상 가스누기 보수작업","2024-10-07 09:30","2024-10-18 18:00","2024-10-07 09:30","2024-10-18 18:00","연속"]
[166,"대전세종충남","서산","신서산태안TP#1 T/L","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능, 휴일작업포함)태안T/P 345kV 신서산-태안화력#1T/L LA, CVT 염해지역 애자코팅 -병행1 : 신서산-태안화력#1T/L LA 보통점검 -병행2 : 신서산-태안화력#1T/L CVT 보통점검","2024-10-04 09:30","2024-10-04 18:00","취소","취소","연속"]
[167,"대전세종충남","서산","태안T/P CB 7571","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 태안화력S/S 345kV 7571 GIS 보통점검","2024-10-21 09:30","2024-10-22 18:00","2024-10-21 09:30","2024-10-22 18:00","연속"]
[168,"대전세종충남","서산","태안T/P CB 7300","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7300 CB 균압콘덴서 절연열화 진단","2024-10-18 13:30","2024-10-18 16:30","2024-10-18 13:30","2024-10-18 16:30","연속"]
[169,"대전세종충남","서산","태안T/P CB 7372","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7372 CB 균압콘덴서 절연열화 진단","2024-10-18 09:30","2024-10-18 13:00","2024-10-18 09:30","2024-10-18 13:00","연속"]
[170,"대전세종충남","서산","태안T/P CB 7200","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7200 CB 균압콘덴서 절연열화 진단","2024-10-17 13:30","2024-10-17 16:30","2024-10-17 13:30","2024-10-17 16:30","연속"]
[171,"대전세종충남","서산","태안T/P CB 7272","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7272 CB 균압콘덴서 절연열화 진단","2024-10-17 09:30","2024-10-17 13:00","2024-10-17 09:30","2024-10-17 13:00","연속"]
[172,"대전세종충남","서산","태안T/P CB 7700","24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7700 CB 균압콘덴서 절연열화 진단","2024-10-11 13:30","2024-10-11 16:30","2024-10-11 13:30","2024-10-11 16:30","연속"]
[173,"대전세종충남","세종","세종S/S CB 7371","[변전]2024년-2025년 세종전력지사 변전협력회사 공사","○345kV GIS 보통점검","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[174,"대전세종충남","세종","세종S/S CB 7300","[변전]2024년-2025년 세종전력지사 변전협력회사 공사","○345kV GIS 보통점검","2024-10-08 09:00","2024-10-08 18:00","2024-10-08 09:00","2024-10-08 18:00","연속"]
[175,"대전세종충남","세종","세종S/S CB 7471","[변전]2024년-2025년 세종전력지사 변전협력회사 공사","○345kV GIS 보통점검","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[176,"대전세종충남","세종","세종S/S CB 7400","[변전]2024년-2025년 세종전력지사 변전협력회사 공사","○345kV GIS 보통점검","2024-10-11 09:00","2024-10-11 18:00","2024-10-11 09:00","2024-10-11 18:00","연속"]
[177,"대전세종충남","세종","세종S/S CB 7571","[변전]2024년-2025년 세종전력지사 변전협력회사 공사","○345kV GIS 보통점검","2024-10-14 09:00","2024-10-14 18:00","2024-10-14 09:00","2024-10-14 18:00","연속"]
[178,"대전세종충남","세종","세종S/S CB 7500","[변전]2024년-2025년 세종전력지사 변전협력회사 공사","○345kV GIS 보통점검","2024-10-15 09:00","2024-10-15 18:00","2024-10-15 09:00","2024-10-15 18:00","연속"]
[179,"대전세종충남","세종","세종S/S CB 7200","[변전]2024년-2025년 세종전력지사 변전협력회사 공사","○345kV GIS 보통점검","2024-10-18 09:00","2024-10-18 18:00","2024-10-18 09:00","2024-10-18 18:00","연속"]
[180,"대전세종충남","세종","세종S/S CB 7271","[변전]2024년-2025년 세종전력지사 변전협력회사 공사","○345kV GIS 보통점검","2024-10-17 09:00","2024-10-17 18:00","2024-10-17 09:00","2024-10-17 18:00","연속"]
[181,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S 345kV 77Bay 노후 B/F 보호반 대체","(9월취소시)(즉시가압불가)신온양S/S 345kV 77Bay 노후 B/F 보호반 대체","2024-10-21 09:00","2024-10-24 18:00","취소","취소","연속"]
[182,"대전세종충남","천안","신온양S/S CB 7771","신온양S/S 345kV 7771 CB 개폐타임측정","(#4M.Tr 휴전 취소시)(즉시가압가능)신온양S/S 345kV 7771 CB 개폐타임측정","2024-10-22 09:00","2024-10-22 18:00","2024-10-22 09:00","2024-10-22 18:00","연속"]
[183,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S 345kV 77Bay 노후 B/F 보호반 대체","(9월취소시)(즉시가압불가)신온양S/S 345kV 77Bay 노후 B/F 보호반 대체","2024-10-21 09:00","2024-10-24 18:00","취소","취소","연속"]
[184,"대전세종충남","천안","신온양서서울#2 T/L","345kV 신온양-서서울T/L 추락방지장치 설치공사","[즉시가압가능, 주말작업없음]345kV 신온양-서서울T/L No. 1 ~ 25 추락방지장치 설치 [병행작업] 조류착지방지장치 설치","2024-10-21 07:00","2024-10-23 18:00","취소","취소","매일"]
[185,"대전세종충남","천안","신온양신탕정#1 T/L","신온양S/S 345kV 신온양-신탕정#1T/L 노후 보호배전반 대체","(즉시가압불가)신온양S/S 345kV 신온양-신탕정#1T/L 노후 보호배전반 대체","2024-10-28 09:00","2024-10-31 18:00","2024-10-28 09:00","2024-10-31 18:00","연속"]
[186,"대전세종충남","천안","신온양서서울#1 T/L","신온양S/S 345kV 78Bay 노후 B/F 보호반 대체","(9월취소시)(즉시가압불가)신온양S/S 345kV 78Bay 노후 B/F 보호반 대체","2024-10-14 09:00","2024-10-17 18:00","취소","취소","연속"]
[187,"대전세종충남","천안","신온양신탕정#2 T/L","신온양S/S 345kV 78Bay 노후 B/F 보호반 대체","(9월취소시)(즉시가압불가)신온양S/S 345kV 78Bay 노후 B/F 보호반 대체","2024-10-14 09:00","2024-10-17 18:00","취소","취소","연속"]
[188,"대전세종충남","천안","신온양S/S #2 M.Tr","신온양S/S 345kV #2M.Tr 보통점검","(즉시가압불가)신온양S/S 345kV #2M.Tr 보통점검","2024-10-07 09:00","2024-10-08 18:00","2024-10-07 09:00","2024-10-08 18:00","연속"]
[189,"대전세종충남","천안","청양신탕정#1 T/L","345kV 청양-신탕정T/L 항공장애표시구 설치공사","[즉시가압가능]345kV 청양-신탕정#1T/L No.7~8 등 33경간 항공구 설치 [병행]No.82 불량애자 교체","2024-10-01 07:00","2024-10-04 18:00","취소","취소","매일"]
[190,"대전세종충남","천안","청양신탕정#2 T/L","345kV 청양-신탕정T/L 항공장애표시구 설치공사","[즉시가압가능]345kV 청양-신탕정#1T/L No.7~8 등 33경간 항공구 설치 [병행]No.116~124 송전선로용 피뢰기 설치","2024-10-07 07:00","2024-10-11 18:00","취소","취소","매일"]
[191,"대전세종충남","천안","신탕정S/S #1 M.Tr","신탕정S/S 345kV #1M.Tr 노후 보호배전반 대체","(9월취소시)(즉시가압불가)신탕정S/S 345kV #1M.Tr 노후 보호배전반 대체","2024-10-07 09:00","2024-10-10 18:00","2024-10-07 09:00","2024-10-10 18:00","연속"]
[192,"대전세종충남","천안","신탕정S/S #2 M.Tr","신탕정S/S 345kV #2M.Tr 노후 보호배전반 대체","(9월취소시)(즉시가압불가)신탕정S/S 345kV #2M.Tr 노후 보호배전반 대체","2024-10-21 09:00","2024-10-24 18:00","2024-10-21 09:00","2024-10-24 18:00","연속"]
[193,"대전세종충남","천안","아산보령TP#2 T/L","항공장애표시구 설치공사","[즉시가압가능]345kV 아산-보령화력T/L No.123~124 등 12경간 항공구 설치 [병행] 불량애자 정비 No.144 [병행] 조류착지방지장치 설치","2024-10-30 07:00","2024-10-31 17:00","취소","취소","매일"]
[194,"대전세종충남","천안","신서산아산#2 T/L","345kV 신서산-아산T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신서산-아산T/L No. 74 ~ 123 추락방지장치 설치 [병가철탑](상단)신서산-아산#2No.74~113,(하단)아산-합덕#2No.13~52 [병행작업] 조류착지방지장치 설치","2024-10-10 07:00","2024-10-16 17:00","취소","취소","매일"]
[195,"대전세종충남","천안","아산화성#2 T/L","345kV 아산-화성T/L 항공장애표시구 설치공사","[즉시가압가능]345kV 아산-화성T/L No.5~6 등 3경간 항공구 설치 [#1T/L 환원 후 #2T/L 휴전시행]","2024-10-18 12:00","2024-10-18 17:00","2024-10-18 12:00","2024-10-18 17:00","매일"]
[196,"대전세종충남","천안","아산보령TP#1 T/L","항공장애표시구 설치공사","[즉시가압가능]345kV 아산-보령화력T/L No.123~124 등 12경간 항공구 설치 [병행] 항공장애표시구 정비 No.187~188 [병행] 조류착지방지장치 설치","2024-10-28 07:00","2024-10-29 17:00","취소","취소","매일"]
[197,"대전세종충남","천안","아산화성#1 T/L","345kV 아산-화성T/L 항공장애표시구 설치공사","[즉시가압가능]345kV 아산-화성#1T/L No.5~6 등 3경간 항공구 설치","2024-10-18 07:00","2024-10-18 12:00","2024-10-18 07:00","2024-10-18 12:00","매일"]
[198,"대전세종충남","청양","아산보령TP#1 T/L","보령T/P 345kV LA,PT GIS 내장화공사(아산-보령화력#1)","보령T/P 345kV LA,PT GIS 내장화공사(아산-보령화력#1) - 즉시가압 불가","2024-10-14 09:00","2024-10-25 18:00","취소","취소","연속"]
[199,"대전세종충남","청양","보령T/P CB 7571","청양P/O 전문 발주공사(화력 7571 보통)","청양P/O 변전전문업체 발주공사 - 보령T/P 아산-보령화력#2T/L GIS 7571 보통점검 - 즉시가압 가능","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[200,"대전세종충남","청양","청양보령TP#1 T/L","[9월 취소시] 345kV 청양-보령T/L 항공장애표시구 설치공사","1. 공사대상 : 345kV 청양-보령T/L No.1~1-1 (5개) 2. 기타사항 ㅇ 345kV 아산-보령화력#1T/L과 병가구간으로 2개 회선 동시휴전 필요 ㅇ 미설치 시 항공시설법 위반으로 과태료 부과 대상","2024-10-29 08:00","2024-10-29 18:00","취소","취소","연속"]
[201,"대전세종충남","청양","아산보령TP#1 T/L","[9월 취소시] 345kV 청양-보령T/L 항공장애표시구 설치공사","1. 공사대상 : 345kV 청양-보령T/L No.1~1-1 (적색 4개) 2. 기타사항 ㅇ 345kV 아산-보령화력#1T/L과 병가구간으로 2개 회선 동시휴전 필요 ㅇ 미설치 시 항공시설법 위반으로 과태료 부과 대상","2024-10-29 08:00","2024-10-29 18:00","취소","취소","연속"]
[202,"대전세종충남","청양","보령T/P #75 BUS","보령T/P 345kV LA,PT GIS 내장화공사(모선 무부하가압)","보령T/P 345kV LA,PT GIS 내장화공사 - 345kV 아산-보령화력#1 무부하가압 관련 75BUS 모선휴전 - 즉시가압 가능","2024-10-24 09:00","2024-10-25 18:00","2024-10-24 09:00","2024-10-25 18:00","연속"]
[203,"대전세종충남","청양","청양S/S #1 M.Tr","(9월취소시)청양P/O 변전협력 총액공사(청양 #1M.Tr)","(9월취소시)청양P/O 변전협력 총액공사 - 청양S/S #1M.Tr 휴전 - 1차 GIS 보통, 2차 GIS 조작, 3차 VCB 초기 - PT 하자, 부싱절연유 채유 (즉시가압 가능)","2024-10-08 09:00","2024-10-08 18:00","취소","취소","연속"]
[204,"대전세종충남","청양","신온양청양#2 T/L CB","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-10-14 08:00","2024-10-16 18:00","취소","취소","연속"]
[205,"대전세종충남","청양","신옥천청양 T/L","345kV 신옥천-청양 T/L 지장수목 전지 및 벌채","345kV 신옥천-청양 T/L 지장수목 전지 및 벌채","2024-10-21 07:00","2024-10-21 14:00","2024-10-21 07:00","2024-10-21 14:00","연속"]
[206,"대전세종충남","청양","신온양청양#1 T/L CB","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-10-21 08:00","2024-10-25 18:00","취소","취소","연속"]
[207,"대전세종충남","청양","청양신탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-10-21 08:00","2024-11-28 18:00","취소","취소","연속"]
[208,"대전세종충남","청양","청양신탕정#2 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-10-14 08:00","2024-10-25 18:00","취소","취소","연속"]
[209,"전북","군산","청양군산#1 T/L","군산PO 154kV 이상 차단기 점검공사","군산PO 154kV 이상 차단기 점검공사","2024-10-10 09:00","2024-10-10 18:00","취소","취소","연속"]
[210,"전북","군산","군산S/S CB 7771","군산P/O 154kV이상 차단기 조작시험","군산P/O 154kV이상 차단기 조작시험","2024-10-07 13:00","2024-10-07 18:00","2024-10-07 13:00","2024-10-07 18:00","연속"]
[211,"전북","군산","청양군산#2 T/L","군산PO 154kV 이상 차단기 점검공사","군산PO 154kV 이상 차단기 점검공사","2024-10-11 09:00","2024-10-11 18:00","취소","취소","연속"]
[212,"전북","군산","군산신김제#1 T/L","군산P/O 154kV이상 차단기 점검공사","군산P/O 154kV이상 차단기 점검공사","2024-10-02 09:00","2024-10-02 18:00","2024-10-02 09:00","2024-10-02 18:00","연속"]
[213,"전북","군산","군산S/S #2 M.Tr","군산P/O 변압기 부싱유 채유공사","군산P/O 변압기 부싱유 채유공사","2024-10-04 09:00","2024-10-04 18:00","2024-10-04 09:00","2024-10-04 18:00","연속"]
[214,"전북","군산","군산S/S CB 7871","군산P/O 154kV이상 차단기 조작시험","군산P/O 154kV이상 차단기 조작시험","2024-10-07 09:00","2024-10-07 13:00","2024-10-07 09:00","2024-10-07 13:00","연속"]
[215,"전북","군산","군산S/S #1 M.Tr","군산P/O 변압기 추락방지장지설치 공사","군산P/O 변압기 추락방지장지설치 공사","2024-10-01 09:00","2024-10-01 18:00","2024-10-01 09:00","2024-10-01 18:00","연속"]
[216,"전북","군산","새만금S/S CB 7371","군산P/O 154kV이상 차단기 조작시험","군산P/O 154kV이상 차단기 조작시험","2024-10-08 13:00","2024-10-08 18:00","2024-10-08 13:00","2024-10-08 18:00","연속"]
[217,"전북","군산","새만금S/S CB 7271","군산P/O 154kV이상 차단기 조작시험","군산P/O 154kV이상 차단기 조작시험","2024-10-08 09:00","2024-10-08 13:00","2024-10-08 09:00","2024-10-08 13:00","연속"]
[218,"전북","김제","신김제S/S #3 M.Tr","'24년 김제전력지사 주변압기 보통점검공사","김제전력지사 주변압기 보통점검공사","2024-10-14 09:00","2024-10-16 18:00","2024-10-14 09:00","2024-10-16 18:00","연속"]
[219,"전북","김제","신김제한빛NP#2 T/L","24년 김제전력지사 기타설비 점검공사","24년 김제전력지사 기타설비 점검공사","2024-10-01 09:00","2024-10-01 18:00","취소","취소","연속"]
[220,"전북","직할","신남원광양#1 T/L","345kV 신남원-광양#1T/L CVT 교체","345kV 신남원-광양#1T/L CVT C상 교체","2024-10-04 09:00","2024-10-04 18:00","2024-10-04 09:00","2024-10-04 18:00","연속"]
[221,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","345kV 신남원-신광주T/L No.1~115 수평 추락방지장치 및 조류착지방지장치 설치","2024-10-10 07:00","2024-10-17 17:00","취소","취소","매일"]
[222,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","345kV 신남원-신광주T/L No.1~115 수평 추락방지장치 및 조류착지방지장치 설치","2024-10-01 07:00","2024-10-08 17:00","취소","취소","매일"]
[223,"광주전남","광주","신남원신광주#1 T/L","24년 광주전력지사 변전협력회사 총액공사","신광주S/S 신남원-신광주 #1T/L LA(A,B,C상) 및 CVT 보통점검","2024-10-10 09:00","2024-10-10 18:00","취소","취소","연속"]
[224,"광주전남","광주","신광주S/S #2 M.Tr","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-10-01 08:00","2024-10-31 18:00","2024-10-14 08:00","2024-11-15 18:00","연속"]
[225,"광주전남","광주","신광주S/S CB 7472","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-10-01 08:00","2024-10-31 18:00","2024-10-14 08:00","2024-11-15 18:00","연속"]
[226,"광주전남","광주","신광주S/S CB 7400","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체","2024-10-01 08:00","2024-10-31 18:00","2024-10-14 08:00","2024-11-15 18:00","연속"]
[227,"광주전남","광주","신남원신광주#1 T/L","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체 무부하가압용","2024-10-28 08:00","2024-10-29 18:00","취소","취소","연속"]
[228,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체","2024-10-21 08:00","2024-10-25 18:00","취소","취소","연속"]
[229,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2024-10-14 08:00","2024-10-18 18:00","취소","취소","연속"]
[230,"광주전남","광주","신남원신광주#2 T/L","24년 광주전력지사 변전협력회사 총액공사","신광주S/S 신남원-신광주 #2T/L LA(A,B,C상) 보통점검 및 CVT 초기점검","2024-10-11 09:00","2024-10-11 18:00","2024-10-11 09:00","2024-10-11 18:00","연속"]
[231,"광주전남","광주","신화순신강진#2 T/L","24년 광주전력지사 변전협력회사 총액공사","신화순S/S 신화순-신강진 #2T/L LA(A,B,C상) 보통점검","2024-10-14 09:00","2024-10-14 18:00","취소","취소","연속"]
[232,"광주전남","목포","신김제한빛NP#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","한빛#3S/Y 7D00, 7D72 GIS 조작시험 및 균압콘덴서 절연열화 측정","2024-10-30 09:00","2024-10-30 18:00","취소","취소","연속"]
[233,"광주전남","순천","여수T/P #1 Tie-Tr","24~25년 순천전력지사 변전협력회사 공사","여수화력#1M.Tr A,B상 1차 부싱 대체, 3차 LA, MAIN VCB,#1-1Sh.R, VCB 보통점검 및 추락방지장치 설치","2024-10-21 09:00","2024-10-25 18:00","취소","취소","연속"]
[234,"광주전남","순천","여수T/P #2 Tie-Tr","#2M.Tr 3차 VCB 부 과열개소 조치","#2M.Tr 3차 VCB 부 과열개소 조치","2024-10-07 09:00","2024-10-07 18:00","취소","취소","연속"]
[235,"대구","경산","신경산S/S #3 M.Tr","2024년 신경산 154kV GIS 교체공사","66-67-0 GIS 교체작업 안전확보","2024-10-08 11:00","2024-10-16 17:00","2024-10-07 09:00","2024-10-15 17:00","연속"]
[236,"대구","경산","신경산S/S #4 M.Tr","2024년 신경산 154kV GIS 교체공사","6444 GIS 교체작업","2024-10-23 09:00","2024-11-11 09:00","2024-10-23 09:00","2024-11-11 09:00","연속"]
[237,"대구","달성","고령S/S #1 M.Tr","CVT 하자점검","CVT 하자점검","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[238,"대구","달성","고령S/S #2 M.Tr","1차 GIS 보통,부싱절연유채유","1차 GIS 보통,부싱절연유채유","2024-10-08 09:00","2024-10-08 18:00","2024-10-08 09:00","2024-10-08 18:00","연속"]
[239,"대구","달성","고령S/S #3 M.Tr","3차 LA 보통,부싱절연유채유","3차 LA 보통,부싱절연유채유","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[240,"대구","달성","고령S/S #4 M.Tr","#2S.Tr 보통,부싱절연유채유","#2S.Tr 보통,부싱절연유채유","2024-10-11 09:00","2024-10-11 18:00","2024-10-11 09:00","2024-10-11 18:00","연속"]
[241,"대구","칠곡","신포항북대구 T/L","24~25년 칠곡전력지사 가공송전 협력회사 총액공사","345kV 신포항-북대구T/L 수평 추락방지장치 설치","2024-10-01 08:00","2024-10-07 18:00","2024-10-01 08:00","2024-10-07 18:00","연속"]
[242,"대구","칠곡","북경남서대구#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 북경남-서대구T/L 수평 추락방지장치 설치공사","2024-10-10 07:00","2024-10-23 18:00","2024-10-10 07:00","2024-10-23 18:00","연속"]
[243,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 안전확보","2024-10-21 07:00","2024-10-25 18:00","2024-10-21 07:00","2024-10-25 18:00","연속"]
[244,"대구","칠곡","서대구S/S #2 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업","2024-10-21 07:00","2024-11-06 18:00","2024-10-21 07:00","2024-11-06 18:00","연속"]
[245,"대구","포항","신포항신월성NP#1 T/L","24~25년도 포항전력지사 변전총액공사","신월성S/Y 7571,7500,7572 GIS 조작시험, 송전선로 보호반 대체","2024-10-21 09:00","2024-11-01 18:00","2024-10-21 09:00","2024-11-01 18:00","연속"]
[246,"대구","포항","신포항신월성NP#2 T/L","24~25년도 포항전력지사 변전총액공사","신월성S/Y 7571,7500,7572 GIS 조작시험, 송전선로 보호반 대체","2024-10-21 09:00","2024-11-01 18:00","2024-10-21 09:00","2024-11-01 18:00","연속"]
[247,"대구","포항","선산신포항 T/L","24~25년 칠곡전력지사 가공송전 협력회사 총액공사","345kV 선산-신포항T/L 수평 추락방지장치 설치","2024-10-08 08:00","2024-10-11 18:00","2024-10-08 08:00","2024-10-11 18:00","연속"]
[248,"대구","포항","신포항S/S #2 M.Tr","2024~25년도 포항전력지사 변전총액공사","신포항S/S #2M.Tr, 2차 LA,PT, 3차 LA,PT 초기점검 신포항S/S #2M.Tr 1차 LA,PT 보통점검","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[249,"대구","포항","신포항S/S #4 M.Tr","2024~25년도 포항전력지사 변전총액공사","신포항S/S #4M.Tr, 2차 LA,PT, 3차 LA,PT 초기점검 신포항S/S #4M.Tr 1차 LA,PT 보통점검","2024-10-25 09:00","2024-10-25 18:00","2024-10-25 09:00","2024-10-25 18:00","연속"]
[250,"대구","포항","신포항S/S #1 M.Tr","2024~25년도 포항전력지사 변전총액공사","신포항S/S #1M.Tr, 2차 LA,PT, 3차 LA,PT 초기점검 신포항S/S #1M.Tr 1차 LA,PT 보통점검","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[251,"경북","구미","서대구선산#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사","345kV 서대구-선산#2T/L 추락방지시설 설치(수평 32기 No.1~29, 102, 103, 106)","2024-10-07 07:30","2024-10-15 18:00","2024-10-07 07:30","2024-10-15 18:00","매일"]
[252,"경북","구미","선산신포항 T/L","2024-2025년 구미전력지사 송전협력회사 공사","345kV 선산-신포항T/L 추락방지시설 설치(수평 3기 No.102, 103, 106)","2024-10-10 07:30","2024-10-11 18:00","2024-10-10 07:30","2024-10-11 18:00","매일"]
[253,"경북","구미","선산S/S #3 M.Tr","2024-25년 구미전력지사 변전협력회사 공사","- 1차 A상, 2차 A,B,C상 부싱 절연유 채유 - 1차 7472 GIS 초기점검 - 2차 6344 GIS 보통점검[정밀] - 1차 LA, 2차 LA 보통점검 ■ 선산S/S #2S.Tr - #2S.Tr 보통점검 - #2S.Tr VCB 대체","2024-10-14 09:00","2024-10-16 18:00","2024-10-16 09:00","2024-10-18 18:00","연속"]
[254,"경북","영주","신영주한울NP#1 T/L","345kV 신영주-한울NP2T/L 불량 금구류 설비","345kV 신영주-한울NP2T/L 불량 금구류 설비","2024-10-28 08:00","2024-10-29 17:00","취소","취소","매일"]
[255,"경북","영주","신영주한울NP#2 T/L","345kV 신영주-한울NP2T/L 불량 금구류 설비","345kV 신영주-한울NP2T/L 불량 금구류 설비","2024-10-30 08:00","2024-10-31 17:00","취소","취소","매일"]
[256,"경북","영주","신영주S/S #3 M.Tr","2024-25년 영주전력지사 변전협력회사 공사","OLTC MDU 리미트 접점 교체","2024-10-31 09:00","2024-10-31 18:00","2024-10-31 09:00","2024-10-31 18:00","연속"]
[257,"경북","영주","한울#1N/P CB 7171","2024~25년 영주전력지사 변전협력회사 총액공사","2024~25년 영주전력지사 변전협력회사 총액공사","2024-10-18 09:00","2024-10-18 18:00","2024-10-18 09:00","2024-10-18 18:00","연속"]
[258,"경북","영주","한울#1N/P CB 7371","2024~25년 영주전력지사 변전협력회사 총액공사","2024~25년 영주전력지사 변전협력회사 총액공사","2024-10-17 09:00","2024-10-17 18:00","2024-10-17 09:00","2024-10-17 18:00","연속"]
[259,"경북","영주","한울#1N/P CB 7271","2024~25년 영주전력지사 변전협력회사 총액공사","2024~25년 영주전력지사 변전협력회사 총액공사","2024-10-17 09:00","2024-10-17 18:00","2024-10-17 09:00","2024-10-17 18:00","연속"]
[260,"경북","영주","한울#2N/P CB 7G72","2024~25년 영주전력지사 변전협력회사 총액공사","2024~25년 영주전력지사 변전협력회사 총액공사","2024-10-15 09:00","2024-10-15 18:00","2024-10-15 09:00","2024-10-15 18:00","연속"]
[261,"경북","영주","한울#2N/P CB 7G00","2024~25년 영주전력지사 변전협력회사 총액공사","2024~25년 영주전력지사 변전협력회사 총액공사","2024-10-15 09:00","2024-10-15 18:00","2024-10-15 09:00","2024-10-15 18:00","연속"]
[262,"경북","영주","한울#2N/P CB 7F72","2024~25년 영주전력지사 변전협력회사 총액공사","2024~25년 영주전력지사 변전협력회사 총액공사","2024-10-16 09:00","2024-10-16 18:00","2024-10-16 09:00","2024-10-16 18:00","연속"]
[263,"경북","영주","한울#2N/P CB 7F00","2024~25년 영주전력지사 변전협력회사 총액공사","2024~25년 영주전력지사 변전협력회사 총액공사","2024-10-16 09:00","2024-10-16 18:00","2024-10-16 09:00","2024-10-16 18:00","연속"]
[264,"경북","직할","신영주안동CC T/L","'24~25년 경북 직할 가공송전 협력회사 공사","345kV 안동복합분기T/L 추락방지장치 설치공사","2024-10-14 08:00","2024-10-18 18:00","취소","취소","연속"]
[265,"경북","직할","신영일안동CC T/L","345kV 신영일-안동CC T/L 정밀점검","345kV 신영일-안동CC T/L 정밀점검 No.26 ~ 77","2024-10-21 09:00","2024-10-29 18:00","취소","취소","연속"]
[266,"경북","영주","신제천신영주#1 T/L","  345kV 신제천-신영주T/L 송전선로 정밀점검","  345kV 신제천-신영주T/L 송전선로 정밀점검","2024-10-14 08:00","2024-10-18 17:00","취소","취소","연속"]
[267,"경북","영주","신제천신영주#2 T/L","  345kV 신제천-신영주T/L 송전선로 정밀점검","  345kV 신제천-신영주T/L 송전선로 정밀점검","2024-10-21 08:00","2024-10-25 17:00","취소","취소","연속"]
[268,"경북","영주","신영주S/S #1 M.Tr"," 2024-25년 영주전력지사 변전협력회사 공사"," 2024-25년 영주전력지사 변전협력회사 공사","2024-10-28 09:00","2024-10-28 14:00","2024-10-28 09:00","2024-10-28 14:00","연속"]
[269,"경북","영주","신영주S/S #2 M.Tr"," 2024-25년 영주전력지사 변전협력회사 공사"," 2024-25년 영주전력지사 변전협력회사 공사","2024-10-28 14:00","2024-10-30 18:00","2024-10-28 14:00","2024-10-30 18:00","연속"]
[270,"부산울산","직할","신대연S/S #2 M.Tr","24~25년 직할 변전협력회사 총액공사","신대연S/S #2M.Tr 3차 GIS 조작시험","2024-10-08 09:30","2024-10-08 18:00","2024-10-08 09:30","2024-10-08 18:00","연속"]
[271,"부산울산","직할","신대연S/S #1 M.Tr","24~25년 직할 변전협력회사 총액공사","신대연S/S #1M.Tr 3차 GIS 조작시험","2024-10-07 09:30","2024-10-07 18:00","2024-10-07 09:30","2024-10-07 18:00","연속"]
[272,"부산울산","울산","남울산울산TP#2 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#1T/L(S/T~28호) 154kV 성암-울산TP#1T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#2T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#2T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#2T/L (S/T~16호) / 병가 울주-울산TP 15~26호","2024-10-15 08:00","2024-10-15 18:00","2024-10-15 08:00","2024-10-15 18:00","연속"]
[273,"부산울산","울산","남울산S/S #2 M.Tr","24년 울산전력지사 변전협력회사 총액공사","- 7300,7372 2점절 균압콘덴서 절연열화 측정 - 일진제 7391DS 발청보수 - 7300 유압조작기 교체 -6571,6500 효성제 조작부 발청보수","2024-10-29 09:00","2024-10-31 18:00","2024-10-29 09:00","2024-10-31 18:00","연속"]
[274,"부산울산","울산","남울산울산TP#1 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#2T/L(S/T~28호) 154kV 용연-울산TP#3T/L (4호)_작업없음 / 병가 울주-울산TP#2 4호 154kV 성암-울산TP#2T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#1T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#1T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#1T/L(S/T~16호 / 병가 울주-울산TP 15~26호)","2024-10-22 08:00","2024-10-22 18:00","2024-10-22 08:00","2024-10-22 18:00","연속"]
[275,"부산울산","울산","울주S/S CB 7971","24~25년 변전협력회사 총액공사","- 7921DS 모터 교체","2024-10-25 09:00","2024-10-25 14:00","2024-10-25 09:00","2024-10-25 14:00","연속"]
[276,"부산울산","울산","동울산S/S CB 7472","24년 울산전력지사 변전협력회사 총액공사","- 차단기 동작시험","2024-10-07 09:00","2024-10-08 18:00","2024-10-07 09:00","2024-10-08 18:00","연속"]
[277,"부산울산","울산","울산C/C #2 Tie-Tr","24년 울산전력지사 변전협력회사 총액공사","-1,2차 LA 보통점검 -부싱절연유 채유","2024-10-28 09:00","2024-10-28 18:00","2024-10-28 09:00","2024-10-28 18:00","연속"]
[278,"부산울산","울산","신온산S/S #1 M.Tr","24년 울산전력지사 변전협력회사 총액공사","- 1,2차 부싱절연유 채유 - 3차 GIS 하자점검","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[279,"부산울산","울산","신온산S/S #2 M.Tr","24년 울산전력지사 변전협력회사 총액공사","- C상 OLTC 웜기어 내부 보수(그리스 부족)","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[280,"부산울산","울산","울주울산TP#1 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#1T/L(S/T~28호) 154kV 성암-울산TP#1T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#2T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#2T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#2T/L(S/T~16호 / 병가 울주-울산TP 15~26호)","2024-10-14 08:00","2024-10-17 18:00","2024-10-14 08:00","2024-10-17 18:00","연속"]
[281,"부산울산","울산","울주울산TP#2 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#2T/L(S/T~28호) 154kV 용연-울산TP#3T/L (4호)_작업없음 / 병가 울주-울산TP#2 4호 154kV 성암-울산TP#2T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#1T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#1T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#1T/L(S/T~16호 / 병가 울주-울산TP 15~26호)","2024-10-21 08:00","2024-10-24 18:00","2024-10-21 08:00","2024-10-24 18:00","연속"]
[282,"부산울산","북부산","북부산S/S #2 M.Tr","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #3M.Tr 변압기추락방지장치 설치","2024-10-28 09:00","2024-10-30 18:00","2024-10-28 09:00","2024-10-30 18:00","연속"]
[283,"부산울산","북부산","서부산북부산#3 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","1. 대 상 : 345kV 서부산-북부산#3T/L 2. 작업내용 : 접속함 절연유채유 3. 업체명 : 공영전력","2024-10-14 08:00","2024-10-16 18:00","2024-10-14 08:00","2024-10-16 18:00","연속"]
[284,"부산울산","북부산","북부산S/S #3 M.Tr","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #3M.Tr 변압기추락방지장치 설치","2024-10-23 09:00","2024-10-25 18:00","2024-10-23 09:00","2024-10-25 18:00","연속"]
[285,"부산울산","북부산","북부산고리NP#2 T/L","2024-2025년 동부산 가공송전협력회사 공사","- 가공지선 불량정비 및 애자련증결 작업","2024-10-16 07:00","2024-10-17 18:00","2024-10-16 07:00","2024-10-17 18:00","연속"]
[286,"부산울산","북부산","북부산고리NP#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","- 가공지선 불량정비 및 애자련증결 작업","2024-10-18 07:00","2024-10-19 18:00","2024-10-18 07:00","2024-10-19 18:00","연속"]
[287,"부산울산","동부산","고리N/P #2 CLR (CB 7577, 7677)","고리NP S/Y 345kV #2CLR T/L PNL 대체","고리NP S/Y 345kV #2CLR T/L PNL 대체 병행) 고리NP S/Y 75-76 SEC B/F PNL 대체 병행) 7577GIS 차단기 동작시험 병행)7577,7677GIS 절연열화 측정 병행)#2CLR 지지애자 세정","2024-10-21 09:00","2024-10-25 18:00","2024-10-21 09:00","2024-10-25 18:00","연속"]
[288,"부산울산","동부산","신고리고리NP#4 T/L","2024-2025년 동부산 가공송전협력회사 공사","- 암 지선 철거","2024-10-11 07:00","2024-10-11 18:00","취소","취소","연속"]
[289,"부산울산","동부산","신고리고리NP#1 T/L","345kV 신고리-고리NP#1T/L EBG 가스채취밸브 설치공사","1. 선로명 : 345kV 신고리-고리NP#1T/L 2. 작업구간 : 신고리EBG 6상 3. 작업내용 : EBG 가스채취밸브 설치","2024-10-21 09:00","2024-10-25 18:00","취소","취소","연속"]
[290,"부산울산","동부산","고리N/P #1 CLR (CB 7077, 7177)","고리NP S/Y 345kV CLR 보호반 대체","1. 고리NP S/Y 345kV #1CLR B/F PNL 2. 고리NP S/Y 345kV #1CLR #1 1ST,2ND PNL, #1CLR #2 1ST,2ND PNL 3. 7077GIS 차단기 동작시험 4. 7077,7177GIS 절연열화 측정","2024-10-14 09:00","2024-10-18 18:00","2024-10-14 09:00","2024-10-18 18:00","연속"]
[291,"부산울산","동부산","신양산신대연#2 T/L","신양산S/S 345kV 용량부족차단기 교체공사(5차)","신양산S/S 345kV 용량부족차단기 교체공사(5차) - 대상설비 : 7171,7100,7172CB","2024-10-28 08:00","2025-03-13 18:00","2024-10-28 08:00","2025-03-13 18:00","연속"]
[292,"부산울산","동부산","신양산S/S #1 M.Tr","신양산S/S 345kV 용량부족차단기 교체공사(5차)","신양산S/S 345kV 용량부족차단기 교체공사(5차) - 대상설비 : 7171,7100,7172CB","2024-10-28 08:00","2025-03-13 18:00","2024-10-28 08:00","2025-03-13 18:00","연속"]
[293,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S STATCOM 건설사업(#2S.Tr용 SIS 시험가압)","○ #2M.Tr 3차측 STATCOM #2S.Tr용 25.8kV SIS 1Bay 시험가압","2024-10-24 17:00","2024-10-25 17:00","2024-10-24 17:00","2024-10-25 17:00","연속"]
[294,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S #2M.Tr 추락방지 장치 설치","신양산S/S #2M.Tr 추락방지 장치 설치 병행) 부싱절연유 채유 병행) 6471GIS 보통점검","2024-10-22 09:00","2024-10-22 18:00","2024-10-22 09:00","2024-10-22 18:00","연속"]
[295,"부산울산","동부산","신양산S/S #1 M.Tr","신양산S/S STATCOM 건설사업(#1S.Tr용 SIS 시험가압)","○ #1M.Tr 3차측 STATCOM #1S.Tr용 25.8kV SIS 1Bay 시험가압","2024-10-19 14:00","2024-10-20 14:00","취소","취소","연속"]
[296,"부산울산","동부산","신양산고리NP#1 T/L","신양산S/S 345kV 용량부족차단기 교체공사(4차)","신양산S/S 345kV #4M.Tr 시험가압(자기 선로) - 시험가압 대상 : 75BAY #4M.Tr","2024-10-14 08:00","2024-10-15 09:00","2024-10-14 08:00","2024-10-15 09:00","연속"]
[297,"부산울산","서부산","서부산S/S CB 7172","서부산S/S 345kV 7172 GIS(2MTR) 불량 보조계전기 교체","서부산S/S 345kV 7172 GIS(2MTR) 불량 보조계전기 교체","2024-10-02 09:00","2024-10-02 18:00","2024-10-30 09:00","2024-10-30 18:00","연속"]
[298,"부산울산","서부산","서부산S/S CB 7100","서부산S/S 7100 GIS 불량 보조계전기 교체","서부산S/S 7100 GIS 불량 보조계전기 교체","2024-10-01 09:00","2024-10-01 18:00","2024-10-01 09:00","2024-10-01 18:00","연속"]
[299,"부산울산","서부산","서부산북부산#1 T/L","서부산S/S 서부산-북부산#1T/L GIS 불량 보조계전기 교체","서부산S/S 서부산-북부산#1T/L GIS 불량 보조계전기 교체","2024-10-01 09:00","2024-10-01 18:00","2024-10-29 09:00","2024-10-29 18:00","연속"]
[300,"부산울산","서부산","서부산S/S #1 Sh.R CB","서부산S/S 345kV #1Sh.R GIS 불량 보조계전기 교체-7177","서부산S/S 345kV #1Sh.R GIS 불량 보조계전기 교체-7177","2024-10-01 09:00","2024-10-01 18:00","2024-10-29 09:00","2024-10-29 18:00","연속"]
[301,"부산울산","서부산","신김해신녹산#2 T/L","24~25년 서부산전력지사 가공송전협력회사 공사","345kV 신김해-신녹산T/L 31~32호 항공장애표시구 설치","2024-10-02 08:00","2024-10-02 18:00","2024-10-02 08:00","2024-10-02 18:00","연속"]
[302,"경남","김해송변전부","신마산신김해#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-06 07:00","2024-10-06 18:00","2024-10-06 07:00","2024-10-06 18:00","매일"]
[303,"경남","김해송변전부","신김해북부산#1 T/L","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2024-10-05 07:00","2024-10-06 18:00","2024-10-05 07:00","2024-10-06 18:00","매일"]
[304,"경남","김해송변전부","신김해북부산#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-03 07:00","2024-10-03 18:00","2024-10-03 07:00","2024-10-03 18:00","매일"]
[305,"경남","김해송변전부","신마산신김해#1 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사 (6일은 작업없음)","2024-10-02 07:00","2024-10-08 18:00","2024-10-02 07:00","2024-10-08 18:00","매일"]
[306,"경남","김해송변전부","신마산신김해#1 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-18 07:00","2024-10-18 18:00","2024-10-18 07:00","2024-10-18 18:00","연속"]
[307,"경남","김해송변전부","신김해신녹산#2 T/L","신김해S/S 신김해-신녹산#2T/L 휴전","[시험가압]신김해S/S #4M.Tr 1차 GIS(7872) 시험가압용","2024-10-11 16:00","2024-10-12 16:00","2024-10-11 16:00","2024-10-12 16:00","연속"]
[308,"경남","김해송변전부","신김해S/S CB 7872","신김해S/S #4M.Tr 1차 GIS(7872) 정밀점검","신김해S/S #4M.Tr 1차 GIS(7872) 정밀점검","2024-10-09 09:30","2024-10-12 16:00","2024-10-09 09:30","2024-10-12 16:00","연속"]
[309,"경남","김해송변전부","신김해북부산#2 T/L","345kV 신김해-북부산#2T/L 철탑추락방지장치 설치공사","345kV 신김해-북부산#2T/L 107~129호(22기) 수평형 철탑추락방지장치 및 110,113,118,119호(4기) 고정형 폴리머 점퍼지지애자 설치","2024-10-09 07:00","2024-10-09 18:00","2024-10-09 07:00","2024-10-09 18:00","연속"]
[310,"경남","김해송변전부","신김해S/S #2 M.Tr","신김해S/S 345kV 용량부족 GIS 교체(안전이격)","신김해S/S 345kV 용량부족 GIS 교체(안전이격)","2024-10-01 08:00","2024-10-03 18:00","2024-10-01 08:00","2024-10-03 18:00","매일"]
[311,"경남","김해송변전부","신김해S/S #3 M.Tr","신김해S/S 신김해-신녹산#1T/L 휴전","[시험가압]신김해S/S 345kV #3 M.Tr 1차 GIS 시험가압용","2024-10-19 16:00","2024-10-20 16:00","2024-10-19 16:00","2024-10-20 16:00","연속"]
[312,"경남","김해송변전부","신김해신녹산#1 T/L","신김해S/S 신김해-신녹산#1T/L 휴전","[시험가압]신김해S/S 345kV #3 M.Tr 1차 GIS 시험가압용","2024-10-19 16:00","2024-10-20 16:00","2024-10-19 16:00","2024-10-20 16:00","연속"]
[313,"경남","김해송변전부","신김해S/S #4 M.Tr","신김해S/S #4M.Tr 휴전","[시험가압]신김해S/S #4M.Tr 1차 GIS(7872) 시험가압용","2024-10-11 16:00","2024-10-12 16:00","2024-10-11 16:00","2024-10-12 16:00","연속"]
[314,"경남","김해송변전부","신김해창원#1 T/L","154kV 마천-진해TL등 16개TL 추락방지장치 설치 및 교체공사","154kV 마천-진해TL등 16개TL 추락방지장치 설치 및 교체공사","2024-10-12 07:00","2024-10-12 18:00","2024-10-12 07:00","2024-10-12 18:00","매일"]
[315,"경남","김해송변전부","신김해창원#2 T/L","154kV 마천-진해TL등 16개TL 추락방지장치 설치 및 교체공사","154kV 마천-진해TL등 16개TL 추락방지장치 설치 및 교체공사","2024-10-13 07:00","2024-10-13 18:00","2024-10-13 07:00","2024-10-13 18:00","매일"]
[316,"경남","김해송변전부","신김해S/S CB 7700","신김해S/S 345kV GIS(7700) 정밀점검","신김해S/S 345kV GIS(7700) 정밀점검","2024-10-13 09:30","2024-10-16 16:00","2024-10-13 09:30","2024-10-16 16:00","연속"]
[317,"경남","김해송변전부","신김해신녹산#1 T/L","신김해S/S 신김해-신녹산#1T/L 휴전","[시험가압]신김해S/S 345kV GIS(7700) 시험가압용","2024-10-15 16:00","2024-10-16 16:00","2024-10-15 16:00","2024-10-16 16:00","연속"]
[318,"경남","김해송변전부","신김해S/S CB 7772","신김해S/S 345kV #3 M.Tr 1차 GIS(7772) 정밀점검","신김해S/S 345kV #3 M.Tr 1차 GIS(7772) 정밀점검","2024-10-17 09:30","2024-10-20 16:00","2024-10-17 09:30","2024-10-20 16:00","연속"]
[319,"경남","직할","창원신고성#1 T/L","24~25년 직할 송전협력회사 공사","압축인류클램프 교체","2024-10-17 07:00","2024-10-17 18:00","2024-10-17 07:00","2024-10-17 18:00","연속"]
[320,"경남","직할","창원신고성#2 T/L","24~25년 직할 송전협력회사 공사","압축인류클램프 교체","2024-10-18 07:00","2024-10-18 18:00","2024-10-18 07:00","2024-10-18 18:00","연속"]
[321,"경남","직할","창원신고성#2 T/L","154kV 마천-진해TL등 16개TL 추락방지장치 설치 및 교체공사","154kV 마천-진해TL등 16개TL 추락방지장치 설치 및 교체공사","2024-10-12 07:00","2024-10-12 18:00","2024-10-12 07:00","2024-10-12 18:00","매일"]
[322,"경남","직할","창원신고성#1 T/L","154kV 마천-진해TL등 16개TL 추락방지장치 설치 및 교체공사","154kV 마천-진해TL등 16개TL 추락방지장치 설치 및 교체공사","2024-10-13 07:00","2024-10-13 18:00","2024-10-13 07:00","2024-10-13 18:00","매일"]
[323,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-10-01 07:30","2024-10-15 18:00","2024-10-01 07:30","2024-10-15 18:00","매일"]
[324,"경남","진주","신남원의령#2 T/L","345kV 신남원-의령T/L 추락방지장치 설치 공사","345kV 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2024-10-21 07:00","2024-10-25 18:00","2024-10-21 07:00","2024-10-25 18:00","매일"]
[325,"경남","진주","의령산청양수#1 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.112~129 (345kV 의령-하동화력 T/L과 병가 구간)","2024-10-16 07:30","2024-10-20 18:00","2024-10-16 07:30","2024-10-20 18:00","매일"]
[326,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-10-16 07:30","2024-10-31 18:00","2024-10-16 07:30","2024-10-31 18:00","매일"]
[327,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 추락방지장치 설치 공사","345kV 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2024-10-14 07:00","2024-10-18 18:00","2024-10-14 07:00","2024-10-18 18:00","매일"]
[328,"경남","진주","의령산청양수#2 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#2T/L측 수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.112~129 (345kV 의령-하동화력 T/L과 병가 구간)","2024-10-10 07:30","2024-10-15 18:00","2024-10-10 07:30","2024-10-15 18:00","매일"]
[329,"경남","진주","하동T/P SEC CB 75760","하동T/P 345kV 70-71-0, 75-76-0 GIS 보통점검","하동T/P 345kV 70-71-0, 75-76-0 GIS 보통점검","2024-10-17 14:00","2024-10-17 17:00","2024-10-17 14:00","2024-10-17 17:00","연속"]
[330,"경남","진주","하동T/P SEC CB 70710","하동T/P 345kV 70-71-0, 75-76-0 GIS 보통점검","하동T/P 345kV 70-71-0, 75-76-0 GIS 보통점검","2024-10-17 10:00","2024-10-17 14:00","2024-10-17 10:00","2024-10-17 14:00","연속"]
[331,"경남","진주","하동T/P CB 7100","하동T/P 345kV 7100 GIS 컨트롤 블록 교체","하동T/P 345kV 7100 GIS 컨트롤 블록 교체","2024-10-10 10:00","2024-10-11 18:00","2024-10-10 10:00","2024-10-11 18:00","연속"]
[332,"경남","진주","하동T/P CB 7172","하동T/P 345kV 7172 GIS 컨트롤 블록 교체","하동T/P 345kV 7172 GIS 컨트롤 블록 교체","2024-10-07 10:00","2024-10-08 18:00","2024-10-07 10:00","2024-10-08 18:00","연속"]
[333,"경남","함안","신옥천북경남 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","345kV 신옥천-북경남T/L 수평 추락방지장치 설치공사","2024-10-10 07:00","2024-10-23 18:00","2024-10-10 07:00","2024-10-23 18:00","연속"]
[334,"경남","함안","신마산신김해#2 T/L","345kV 신마산-신김해#2T/L 철탑추락방지장치 설치공사","추락재해 예방을 위한 수평형 철탑추락방지장치 설치공사 (대상개소 : 345kV 신마산-신김해#2T/L 42~46, 51, 53~56, 65~72, 74~77, 79, 80, 83~86, 88, 89, 92, 93, 95, 97호)","2024-10-09 07:00","2024-10-17 18:00","2024-10-09 07:00","2024-10-17 18:00","매일"]
[335,"경남","함안","신마산S/S #4 M.Tr","신마산S/S #4M.Tr 1차 EBG 해체점검","신마산S/S #4M.Tr 1차 EBG 해체점검","2024-10-10 09:00","2024-10-18 18:00","2024-10-10 09:00","2024-10-18 18:00","연속"]
[336,"경남","함안","신마산S/S CB 7271","신마산S/S 345kV 신마산-신김해#1T/L GIS 보통점검","신마산S/S 345kV 신마산-신김해#1T/L GIS(7271) 보통점검[단독휴전]","2024-10-21 09:30","2024-10-21 17:30","2024-10-21 09:30","2024-10-21 17:30","연속"]
[337,"경남","함안","신마산S/S CB 7200","신마산S/S 345kV 신김해#1TL TIE GIS보통점검","신마산S/S 345kV 신김해#1T/L-#2 M.Tr 1차 TIE GIS(7200) 보통점검[단독휴전]","2024-10-22 09:30","2024-10-22 17:30","2024-10-22 09:30","2024-10-22 17:30","연속"]
[338,"경남","함안","신마산신고성#2 T/L","345kV 신마산-신고성#2T/L 철탑추락방지장치 하자처리","345kV 신마산-신고성#2T/L 156,164호 가공지선암 철탑추락방지장치 하자처리(와이어 단말처리 불량)","2024-10-28 08:00","2024-10-28 18:00","2024-10-28 08:00","2024-10-28 18:00","연속"]
[339,"경남","함안","신마산S/S #2 M.Tr","신마산S/S 345kV #2 M.Tr 1차 GIS 보통점검 외","신마산S/S 345kV #2 M.Tr 1차 GIS 보통점검 외","2024-10-30 09:30","2024-10-31 17:30","2024-10-30 09:30","2024-10-31 17:30","연속"]
[340,"대전세종충남",null,"보령T/P #72 BUS","#78Bay GIS 정밀점검 및 보호계전기 시험 등","#78Bay GIS 정밀점검 및 보호계전기 시험 등","2024-10-21 09:00","2024-11-01 17:00","2024-10-21 09:00","2024-11-01 17:00","연속"]
[341,"대전세종충남",null,"보령T/P #77 BUS","#78Bay GIS 정밀점검 및 보호계전기 시험 등","#78Bay GIS 정밀점검 및 보호계전기 시험 등","2024-10-21 09:00","2024-11-01 17:00","2024-10-21 09:00","2024-11-01 17:00","연속"]
[342,"대전세종충남",null,"보령TP보령CC#2 T/L","#78Bay GIS 정밀점검 및 보호계전기 시험 등","#78Bay GIS 정밀점검 및 보호계전기 시험 등","2024-10-21 09:00","2024-11-01 17:00","2024-10-21 09:00","2024-11-01 17:00","연속"]
[343,"강원","동해","동해S/S CB 7700","동해S/S 362kV GIS 정밀점검공사","362kV GIS 정밀점검","2024-10-14 09:00","2024-10-18 18:00","2024-10-14 09:00","2024-10-18 18:00","연속"]
[344,"강원","동해","동해S/S CB 7772","동해S/S 362kV GIS 정밀점검공사","345kV GIS 정밀점검","2024-10-21 09:00","2024-10-25 18:00","2024-10-21 09:00","2024-10-25 18:00","연속"]
[345,"부산울산","서부산","서부산S/S #1 M.Tr","서부산S/S 345kV #1M.Tr 2차 GIS 동작시험","서부산S/S 345kV #1M.Tr 2차 GIS 동작시험","2024-10-21 09:00","2024-10-21 18:00","2024-10-21 09:00","2024-10-21 18:00","연속"]
[346,"경기북부",null,"포천C/C #3 M.Tr (CB 7200, 7272)","주,보조변압기 계획예방정비공사","주,보조변압기 계획예방정비공사","2024-10-01 09:00","2024-10-13 16:00","2024-10-01 09:00","2024-10-13 16:00","연속"]
[347,"경기북부",null,"포천C/C #4 M.Tr (CB 7300, 7372)","주,보조변압기 계획예방정비공사","주,보조변압기 계획예방정비공사","2024-10-14 09:00","2024-10-21 16:00","2024-10-14 09:00","2024-10-21 16:00","연속"]

{"sheet":"154설비","index":2,"n_rows":822,"n_cols":11,"rows_kept":822,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 10월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금광장 T/L","효성제 170kV GIS 스프링조작기 부품교체 공사","- 스프링 조작기 부품교체 공사","2024-10-22 09:00","2024-10-22 14:00","2024-10-22 09:00","2024-10-22 14:00","연속"]
[2,"서울","성동","화양광장 T/L","효성제 170kV GIS 스프링조작기 부품교체 공사","- 스프링 조작기 부품교체 공사","2024-10-23 09:00","2024-10-23 14:00","2024-10-23 09:00","2024-10-23 14:00","연속"]
[3,"서울","성동","광장뚝도#2 T/L","효성제 170kV GIS 스프링조작기 부품교체 공사","- 스프링 조작기 부품교체 공사","2024-10-21 14:00","2024-10-21 18:00","2024-10-21 14:00","2024-10-21 18:00","연속"]
[4,"서울","성동","광장뚝도#1 T/L","효성제 170kV GIS 스프링조작기 부품교체 공사","- 스프링 조작기 부품교체 공사","2024-10-21 09:00","2024-10-21 14:00","2024-10-21 09:00","2024-10-21 14:00","연속"]
[5,"서울","성동","천호구의#1 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#2T/L, BUS PT GIS 교체","2024-10-24 15:00","2024-10-25 15:00","2024-10-24 15:00","2024-10-25 15:00","연속"]
[6,"서울","성동","천호구의#2 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#2T/L, BUS PT GIS 교체","2024-10-21 09:00","2024-11-15 18:00","2024-10-21 09:00","2024-11-15 18:00","연속"]
[7,"서울","성동","구의S/S #1 BUS","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","구의-광장#1T/L, #2M.Tr 1차 GIS 교체","2024-10-10 15:00","2024-10-11 18:00","2024-10-10 15:00","2024-10-11 18:00","연속"]
[8,"서울","성동","구의광장#2 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","구의-광장#1T/L, #2M.Tr 1차 GIS 교체","2024-10-08 13:00","2024-10-10 18:00","2024-10-08 13:00","2024-10-10 18:00","연속"]
[9,"서울","성동","구의S/S CB 6100","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#2T/L, BUS PT GIS 교체","취소","취소","취소","취소","연속"]
[10,"서울","성동","구의S/S CB 6100","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#2T/L, BUS PT GIS 교체","2024-10-21 09:00","2024-11-15 18:00","2024-10-21 09:00","2024-11-15 18:00","연속"]
[11,"서울","성동","구의S/S #2 BUS","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#2T/L, BUS PT GIS 교체","2024-10-21 09:00","2024-10-25 15:00","2024-10-21 09:00","2024-10-25 15:00","연속"]
[12,"서울","성동","안암노원#1 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","취소","취소","취소","취소","연속"]
[13,"서울","성동","상계노원#1 T/L","24년 성동P/O 변전협력회사 공사","LA 보통점검","취소","취소","취소","취소","연속"]
[14,"서울","성동","상계노원#2 T/L","24년 성동P/O 변전협력회사 공사","LA 보통점검","취소","취소","취소","취소","연속"]
[15,"서울","성동","노원S/S CB 6100","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-10-22 10:00","2024-10-22 18:00","2024-10-22 10:00","2024-10-22 18:00","연속"]
[16,"서울","성동","금오상계#2 T/L","2023-2024년 성동전력지사 지중송전설비 위탁정비공사","기중종단접속함(EBA) 절연유 채취","2024-10-15 09:00","2024-10-18 18:00","2024-10-15 09:00","2024-10-18 18:00","연속"]
[17,"서울","성동","금오상계#1 T/L","2023-2024년 성동전력지사 지중송전설비 위탁정비공사","기중종단접속함(EBA) 절연유 채취","2024-10-15 09:00","2024-10-18 18:00","2024-10-15 09:00","2024-10-18 18:00","연속"]
[18,"서울","성동","성동S/S #60 BUS","성동S/S 154kV Sh.R 설치공사","1. 154kV Sh.R(20MVAR×3) × 2조 설치 2. 154kV Sh.R 1차 GIS × 2Bay 설치 3. 기타 부대공사 × 1식","2024-10-28 09:00","2024-11-11 18:00","2024-10-28 09:00","2024-11-11 18:00","연속"]
[19,"서울","성동","신내상봉 T/L","신내중계 170kV GIS 증설공사","- 170kV GIS 정밀점검(#2BUS 시험가압)","2024-10-05 15:00","2024-10-05 18:00","2024-10-05 15:00","2024-10-05 18:00","연속"]
[20,"서울","성동","신내상봉 T/L","24년 성동P/O 주변압기 및 OLTC 정밀점검공사","- 1BUS 시험가압","2024-10-03 15:00","2024-10-03 16:00","2024-10-03 15:00","2024-10-03 16:00","연속"]
[21,"서울","성동","신내상봉 T/L","신내중계 170kV GIS 증설공사","- 170kV GIS 정밀점검(#1BUS 시험가압)","2024-10-02 15:00","2024-10-02 18:00","2024-10-02 15:00","2024-10-02 18:00","연속"]
[22,"서울","성동","신내상봉 T/L","24년 성동P/O 주변압기 및 OLTC 정밀점검공사","- 2BUS 시험가압","2024-10-18 17:00","2024-10-21 10:00","2024-10-18 17:00","2024-10-21 10:00","연속"]
[23,"서울","성동","노원종암 T/L","종암S/S 디지털화 공사","종암S/S 디지털화 공사","2024-10-28 09:00","2024-10-29 18:00","취소","취소","연속"]
[24,"서울","성동","휘경종암#1 T/L","종암S/S 디지털화 공사","종암S/S 디지털화 공사","2024-10-30 09:00","2024-10-31 18:00","취소","취소","연속"]
[25,"서울","성동","중계상봉 T/L","신내중계 170kV GIS 증설공사","- 170kV GIS 증설 (시험가압)","취소","취소","취소","취소","연속"]
[26,"서울","성동","중계상봉 T/L","신내중계 170kV GIS 증설공사","- 170kV GIS 증설 (시험가압)","취소","취소","취소","취소","연속"]
[27,"서울","중부","동빙고반포#2 T/L","동빙고반포#2 T/L OF케이블 절연유 채유","동빙고반포#2 T/L OF케이블 절연유 분석 시료채취","2024-10-23 09:00","2024-10-23 14:00","2024-10-23 09:00","2024-10-23 14:00","연속"]
[28,"서울","중부","원흥상암 T/L","원흥상암 T/L EBG 가스채취밸브 설치","원흥상암 T/L 상암EBG 가스채취밸브 설치","2024-10-21 09:00","2024-10-23 18:00","2024-10-21 09:00","2024-10-23 18:00","연속"]
[29,"서울","중부","옥인운니#2 T/L","2024년 중부전력지사 170kV GIS 정밀점검","GIS 보통점검","2024-10-18 10:00","2024-10-18 18:00","2024-10-18 10:00","2024-10-18 18:00","연속"]
[30,"서울","중부","옥인운니#1 T/L","2024년 중부전력지사 170kV GIS 정밀점검","GIS 보통점검","2024-10-17 10:00","2024-10-17 18:00","2024-10-17 10:00","2024-10-17 18:00","연속"]
[31,"서울","중부","양주은평#1 T/L","은평S/S SA설비개선 관련 내진가대 설치 및 제어케이블 이설공사","은평S/S SA설비개선 관련 제어케이블 이설작업 ㅇ RTU - LID 제어케이블 이설 (170kV GIS 감시/제어/계측) ㅇ 현장 - SCADA 간 이설포인트 연동시험 등","2024-10-04 09:00","2024-10-04 18:00","2024-10-04 09:00","2024-10-04 18:00","연속"]
[32,"서울","중부","양주은평#2 T/L","은평S/S SA설비개선 관련 내진가대 설치 및 제어케이블 이설공사","은평S/S SA설비개선 관련 제어케이블 이설작업 ㅇ RTU - LID 제어케이블 이설 (170kV GIS, T/L 보호반 감시/제어/계측) ㅇ 현장 - SCADA 간 이설포인트 연동시험 등","2024-10-01 09:00","2024-10-02 18:00","2024-10-01 09:00","2024-10-02 18:00","연속"]
[33,"서울","중부","중부마포 T/L","중부S/S 154kV 장기사용 GIS 교체공사(4차)","SEC DS 개방 후 #61, #66BUS 절체용 휴전","2024-10-31 09:20","2024-10-31 09:30","2024-10-31 09:20","2024-10-31 09:30","연속"]
[34,"서울","중부","중부연대 T/L","중부S/S 154kV 장기사용 GIS 교체공사(4차)","SEC DS 개방 후 #61, #66BUS 절체용 휴전","2024-10-31 09:10","2024-10-31 09:20","2024-10-31 09:10","2024-10-31 09:20","연속"]
[35,"서울","중부","중부마포 T/L","중부S/S 154kV 장기사용 GIS 교체공사(4차)","SEC DS 개방 후 #61, #66BUS 절체용 휴전","2024-10-23 09:20","2024-10-23 09:30","2024-10-23 09:20","2024-10-23 09:30","연속"]
[36,"서울","중부","중부연대 T/L","중부S/S 154kV 장기사용 GIS 교체공사(4차)","SEC DS 개방 후 #61, #66BUS 절체용 휴전","2024-10-23 09:10","2024-10-23 09:20","2024-10-23 09:10","2024-10-23 09:20","연속"]
[37,"서울","중부","중부마포 T/L","중부S/S 154kV 장기사용 GIS 교체공사(4차)","SEC DS 개방 후 #61, #66BUS 절체용 휴전","2024-10-21 09:20","2024-10-21 09:30","2024-10-21 09:20","2024-10-21 09:30","연속"]
[38,"서울","중부","중부연대 T/L","중부S/S 154kV 장기사용 GIS 교체공사(4차)","SEC DS 개방 후 #61, #66BUS 절체용 휴전","2024-10-21 09:10","2024-10-21 09:20","2024-10-21 09:10","2024-10-21 09:20","연속"]
[39,"서울","중부","중부S/S #61 BUS","중부S/S 154kV 장기사용 GIS 교체공사(4차)","- 154kV GIS 교체(중부용산#2T/L) - 기타 부대공사","2024-10-23 09:00","2024-10-31 09:00","2024-10-23 09:00","2024-10-31 09:00","연속"]
[40,"서울","중부","중부S/S #66 BUS","중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV GIS 교체(#2M.Tr 2차, 중부연대T/L, 중부마포T/L) - 기타 부대공사","2024-10-04 09:00","2024-10-18 18:00","2024-10-04 09:00","2024-10-18 18:00","연속"]
[41,"서울","중부","중부S/S #66 BUS","중부S/S 154kV 장기사용 GIS 교체공사(4차)","- 154kV GIS 교체(중부용산#2T/L) - 기타 부대공사","2024-10-21 09:00","2024-10-23 09:00","2024-10-21 09:00","2024-10-23 09:00","연속"]
[42,"서울","중부","중부용산#2 T/L","중부S/S 154kV 장기사용 GIS 교체공사(4차)","- 154kV GIS 교체(중부용산#2T/L) - 기타 부대공사","2024-10-21 09:00","2024-11-08 18:00","2024-10-21 09:00","2024-11-08 18:00","연속"]
[43,"서울","중부","중부S/S #66 BUS","중부S/S 154kV 장기사용 GIS 교체공사(4차)","- 154kV GIS 교체(중부용산#2T/L) - 기타 부대공사","2024-10-31 09:00","2024-11-08 18:00","2024-10-31 09:00","2024-11-08 18:00","연속"]
[44,"서울","직할","성동마장#3 T/L","24년 서울본부 직할 154KV GIS 정밀점검공사","마장용두T/L 시험가압 및 154kV GIS 정밀점검","취소","취소","취소","취소","연속"]
[45,"서울","직할","마장용두 T/L","24년 서울본부 직할 154KV GIS 정밀점검공사","154kV GIS 정밀점검","2024-10-07 09:00","2024-10-09 14:00","2024-10-07 09:00","2024-10-09 14:00","연속"]
[46,"서울","직할","용두S/S #1 BUS","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-10-16 09:00","2024-10-17 18:00","2024-10-16 09:00","2024-10-17 18:00","연속"]
[47,"서울","직할","용두S/S #2 BUS","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 인터록, 상체크 확인용 휴전","2024-10-07 09:00","2024-10-07 18:00","취소","취소","연속"]
[48,"서울","직할","용두안암#1 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사(시험가압 선로)","2024-10-31 17:00","2024-10-31 18:00","2024-10-31 17:00","2024-10-31 18:00","연속"]
[49,"서울","직할","용두안암#2 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사(시험가압 선로)","2024-10-24 17:00","2024-10-24 18:00","2024-10-24 17:00","2024-10-24 18:00","연속"]
[50,"서울","직할","용두S/S #2 BUS","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-10-25 09:00","2024-10-25 18:00","2024-10-25 09:00","2024-10-25 18:00","연속"]
[51,"서울","직할","용두안암#2 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사(시험가압 선로)","2024-10-25 17:00","2024-10-25 18:00","2024-10-25 17:00","2024-10-25 18:00","연속"]
[52,"서울","직할","용두S/S CB 6100","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-10-28 09:00","2024-10-31 18:00","2024-10-28 09:00","2024-10-31 18:00","연속"]
[53,"서울","직할","용두S/S #1 BUS","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-10-29 09:00","2024-10-30 18:00","2024-10-29 09:00","2024-10-30 18:00","연속"]
[54,"서울","직할","용두안암#1 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사(시험가압 선로)","2024-10-30 17:00","2024-10-30 18:00","2024-10-30 17:00","2024-10-30 18:00","연속"]
[55,"서울","직할","용두S/S #2 BUS","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-10-31 09:00","2024-10-31 18:00","2024-10-31 09:00","2024-10-31 18:00","연속"]
[56,"서울","직할","용두안암#1 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사(시험가압 선로)","2024-10-18 17:00","2024-10-18 18:00","2024-10-18 17:00","2024-10-18 18:00","연속"]
[57,"서울","직할","용두S/S #2 BUS","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-10-18 09:00","2024-10-18 18:00","2024-10-18 09:00","2024-10-18 18:00","연속"]
[58,"서울","직할","용두S/S #1 BUS","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-10-23 09:00","2024-10-24 18:00","2024-10-23 09:00","2024-10-24 18:00","연속"]
[59,"서울","직할","용두안암#1 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사(시험가압 선로)","2024-10-17 17:00","2024-10-17 18:00","2024-10-17 17:00","2024-10-17 18:00","연속"]
[60,"남서울","강남","탄천대치#1 T/L","강남P/O 170kV GIS 정밀점검","대치S/S 대치-탄천#1T/L 정밀점검","2024-10-14 09:00","2024-10-15 18:00","2024-10-14 09:00","2024-10-15 18:00","연속"]
[61,"남서울","강남","대치논현#2 T/L","강남P/O 170kV GIS 정밀점검","대치S/S 논현-대치#2T/L 정밀점검","2024-10-10 09:00","2024-10-11 18:00","2024-10-09 09:00","2024-10-10 18:00","연속"]
[62,"남서울","강남","탄천대치#2 T/L","강남P/O 170kV GIS 정밀점검","대치S/S 대치-탄천#2T/L 정밀점검","2024-10-16 09:00","2024-10-17 18:00","2024-10-17 09:00","2024-10-18 18:00","연속"]
[63,"남서울","강남","대치논현#1 T/L","강남P/O 170kV GIS 정밀점검","대치S/S 논현-대치#1T/L 정밀점검","2024-10-07 09:00","2024-10-08 18:00","2024-10-07 09:00","2024-10-08 18:00","연속"]
[64,"남서울","강남","동빙고반포#2 T/L","24-25년도 강남전력지사 변전협력회사 총액공사","반포S/S 동빙고-반포#2T/L 조작시험","2024-10-21 14:00","2024-10-21 18:00","2024-10-21 14:00","2024-10-21 18:00","연속"]
[65,"남서울","강남","동빙고반포#1 T/L","24-25년도 강남전력지사 변전협력회사 총액공사","반포S/S 동빙고-반포#1T/L 조작시험","2024-10-21 10:00","2024-10-21 14:00","2024-10-21 10:00","2024-10-21 14:00","연속"]
[66,"남서울","강남","신양재신사#1 T/L","강남P/O 170kV GIS 정밀점검","신사S/S 신양재-신사#1T/L 정밀점검 신양재S/S 신양재-신사#1T/L 조작시험 신양재-신사#1T/L 접지선 보강공사","2024-10-30 15:00","2024-11-02 15:00","2024-10-30 15:00","2024-11-02 15:00","연속"]
[67,"남서울","동서울","강동상일#2 T/L","24~25년도 동서울전력지사 변전협력회사 총액공사","강동,상일S/S 강동-상일#2T/L 송변전선로보호반 대체","2024-10-14 09:00","2024-10-16 18:00","2024-10-14 09:00","2024-10-16 18:00","연속"]
[68,"남서울","동서울","강동상일#1 T/L","24~25년도 동서울전력지사 변전협력회사 총액공사","강동,상일S/S 강동-상일#1T/L 송전선로보호반 대체","2024-10-07 09:00","2024-10-10 18:00","2024-10-07 09:00","2024-10-10 18:00","연속"]
[69,"남서울","동서울","동서울서종#1 T/L","세종-포천 고속도로 건설 지장선로 지중화공사","신설CH - No.93호 철탑간 가공지선 추가 건설","2024-10-28 08:00","2024-10-28 18:00","2024-10-28 08:00","2024-10-28 18:00","연속"]
[70,"남서울","동서울","동서울강동#1 T/L","세종-포천 고속도로 건설 지장선로 지중화공사","신설CH - No.3호 철탑간 가공지선 추가 건설","2024-10-29 08:00","2024-10-29 18:00","2024-10-31 08:00","2024-10-31 18:00","연속"]
[71,"남서울","동서울","동서울서종#2 T/L","세종-포천 고속도로 건설 지장선로 지중화공사","신설CH - No.93호 철탑간 가공지선 추가 건설","2024-10-28 08:00","2024-10-28 18:00","2024-10-28 08:00","2024-10-28 18:00","연속"]
[72,"남서울","동서울","동서울강동#2 T/L","세종-포천 고속도로 건설 지장선로 지중화공사","신설CH - No.3호 철탑간 가공지선 추가 건설","2024-10-29 08:00","2024-10-29 18:00","2024-10-31 08:00","2024-10-31 18:00","연속"]
[73,"남서울","동서울","풍납석촌#2 T/L","2024년동 동서울전력지사 170kV GIS 정밀점검","석촌S/S 154kV 풍납-석촌#2T/L GIS 정밀점검","2024-10-14 09:00","2024-10-18 18:00","2024-10-14 09:00","2024-10-18 18:00","연속"]
[74,"남서울","동서울","동서울위례#1 T/L","24~25년도 동서울전력지사 변전협력회사 총액공사","154kV 동서울-위례1T/L GIS 하자점검","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[75,"남서울","동서울","잠실S/S #2 BUS","2024년동 동서울전력지사 170kV GIS 정밀점검","잠실S/S #3M.Tr 1차 GIS 정밀점검","2024-10-21 09:00","2024-10-22 14:00","2024-10-21 09:00","2024-10-22 14:00","연속"]
[76,"남서울","동서울","잠실S/S #1 BUS","2024년동 동서울전력지사 170kV GIS 정밀점검","잠실S/S #3M.Tr 및 1차 GIS 정밀점검","2024-10-22 14:00","2024-10-25 18:00","2024-10-22 14:00","2024-10-25 18:00","연속"]
[77,"남서울","동서울","송파잠실#3 T/L","2024년동 동서울전력지사 170kV GIS 정밀점검","잠실S/S #3M.Tr 및 1차 GIS 정밀점검 관련 무부하가압용","2024-10-25 09:00","2024-10-25 18:00","2024-10-25 09:00","2024-10-25 18:00","연속"]
[78,"남서울","동서울","송파잠실#3 T/L","2024년동 동서울전력지사 170kV GIS 정밀점검","잠실S/S #3M,Tr 1차 GIS 정밀점검 관련 무부하가압용","2024-10-22 09:00","2024-10-22 14:00","2024-10-22 09:00","2024-10-22 14:00","연속"]
[79,"남서울","동서울","강동천호#1 T/L","24~25년도 동서울전력지사 변전협력회사 총액공사","천호S/S 154kV 강동-천호#1T/L GIS 보통점검","2024-10-13 09:00","2024-10-13 14:00","2024-10-13 09:00","2024-10-13 14:00","연속"]
[80,"남서울","동서울","강동천호#2 T/L","24~25년도 동서울전력지사 변전협력회사 총액공사","천호S/S 154kV 강동-천호#2/L GIS 보통점검","2024-10-13 14:00","2024-10-13 18:00","2024-10-13 14:00","2024-10-13 18:00","연속"]
[81,"남서울","영등포","가양등촌#1 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 가양S/S #1M.Tr 1차 -무부하가압용","2024-10-11 16:00","2024-10-11 18:00","2024-10-11 16:00","2024-10-11 18:00","연속"]
[82,"남서울","영등포","가양등촌#1 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 가양S/S #2M.Tr 1차 - 무부하가압용","2024-10-08 16:00","2024-10-08 18:00","2024-10-08 16:00","2024-10-08 18:00","연속"]
[83,"남서울","영등포","가양등촌#2 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 가양S/S 가양-등촌#2T/L GIS","2024-10-14 09:00","2024-10-15 18:00","2024-10-14 09:00","2024-10-15 18:00","연속"]
[84,"남서울","영등포","구공S/S #66 BUS","구공S/S 154kV 장기사용 GIS 교체공사","구공-독산T/L GIS 철거 및 신품 설치","2024-10-14 09:00","2024-10-24 18:00","2024-10-14 09:00","2024-10-24 18:00","연속"]
[85,"남서울","영등포","신광명구공#1 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 가산S/S #5M.Tr 1차 GIS - 무부하가압용","2024-10-31 16:00","2024-10-31 18:00","2024-10-31 16:00","2024-10-31 18:00","연속"]
[86,"남서울","영등포","마곡S/S #1 BUS","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 마곡S/S 마곡-공항T/L - 무부하가압용","2024-10-03 09:00","2024-10-03 11:00","2024-10-03 09:00","2024-10-03 11:00","연속"]
[87,"남서울","영등포","마곡가양#1 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 마곡S/S 마곡-공항T/L - 무부하가압용","2024-10-03 09:00","2024-10-03 11:00","2024-10-03 09:00","2024-10-03 11:00","연속"]
[88,"남서울","직할","봉천신길#2 T/L","170kV GIS 조작시험","170kV GIS 조작시험","2024-10-14 09:00","2024-10-14 18:00","2024-10-14 09:00","2024-10-14 18:00","연속"]
[89,"남서울","직할","사당신림 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2024-10-27 09:00","2024-10-27 18:00","2024-10-27 09:00","2024-10-27 18:00","연속"]
[90,"남서울","직할","신문래구로#2 T/L","직할 지중송전 위탁전문회사 총액공사","OF케이블 열화진단용 절연유 채유(SJ/B#1, TJ/B#13)","2024-10-18 09:00","2024-10-18 18:00","2024-10-18 09:00","2024-10-18 18:00","연속"]
[91,"인천","김포","영종경서 T/L","경서S/S 154kV 영종-경서T/L GIS 보통점검","경서S/S 154kV 영종-경서T/L GIS 보통점검","2024-10-21 10:00","2024-10-21 18:00","2024-10-21 10:00","2024-10-21 18:00","연속"]
[92,"인천","김포","신경서경서#2 T/L","23~24년 지중송전설비 위탁정비공사","구형 SVL 교체","2024-10-07 08:00","2024-10-11 17:00","2024-10-07 08:00","2024-10-11 17:00","연속"]
[93,"인천","김포","경서양촌#1 T/L","검암플라시아 지장송전선로 지중화공사","○ XLPE 1,200㎟ 1.64 C-km ○ 케이블 포설 4구간, 케이블 접속 6개소","2024-10-05 09:00","2024-10-29 18:00","2024-10-05 09:00","2024-10-29 18:00","연속"]
[94,"인천","김포","신경서경서#1 T/L","23~24년 지중송전설비 위탁정비공사","구형 SVL 교체","2024-10-01 08:00","2024-10-04 17:00","2024-10-01 08:00","2024-10-04 17:00","연속"]
[95,"인천","김포","김포불로#1 T/L","김포S/S 154kV 불로-김포#1T/L GIS 정밀점검","김포S/S 154kV 불로-김포#1T/L GIS 정밀점검 (병행) 불로S/S 154kV 불로-김포#1T/L GIS 초기점검","2024-10-28 09:00","2024-10-30 18:00","2024-10-28 09:00","2024-10-30 18:00","연속"]
[96,"인천","김포","김포불로#2 T/L","김포S/S 154kV 불로-김포#2T/L GIS 보통점검","김포S/S 154kV 불로-김포#2T/L GIS 보통점검","2024-10-11 10:00","2024-10-11 18:00","취소","취소","연속"]
[97,"인천","김포","신김포장기#1 T/L","신김포S/S 154kV 신김포-장기#1T/L GIS 정밀점검","신김포S/S 154kV 신김포-장기#1T/L GIS 정밀점검","2024-10-21 09:00","2024-10-23 14:00","2024-10-21 09:00","2024-10-23 14:00","연속"]
[98,"인천","김포","신김포S/S CB 6100","신김포S/S 154kV #60-#65 BUS TIE GIS 보통점검","신김포S/S 154kV #60-#65 BUS TIE GIS 보통점검 (6100)","2024-10-07 10:00","2024-10-07 18:00","2024-10-07 10:00","2024-10-07 18:00","연속"]
[99,"인천","김포","신김포장기#2 T/L","신김포S/S 154kV 신김포-장기#2T/L GIS 정밀점검","신김포S/S 154kV 신김포-장기#2T/L GIS 정밀점검","2024-10-23 14:00","2024-10-25 18:00","2024-10-23 14:00","2024-10-25 18:00","연속"]
[100,"인천","김포","신김포양곡#2 T/L","양곡S/S 154kV 신김포-양곡#2T/L GIS(옥외) 초기점검","양곡S/S 154kV 신김포-양곡#2T/L GIS(옥외) 초기점검 (병행) 신김포S/S 154kV 신김포-양곡#2T/L GIS 보통점검","2024-10-31 10:00","2024-10-31 18:00","취소","취소","연속"]
[101,"인천","김포","양곡S/S CB 6200","양곡S/S 154kV #61-#66 BUS TIE GIS 초기점검","양곡S/S 154kV #61-#66 BUS TIE GIS 초기점검","2024-10-10 10:00","2024-10-10 18:00","2024-10-10 10:00","2024-10-10 18:00","연속"]
[102,"인천","김포","양촌양곡#2 T/L","양곡S/S 154kV 양촌-양곡#2T/L GIS SA 혼용화 공사","양곡S/S 154kV 양촌-양곡#2T/L GIS SA 혼용화 공사 (병행) GIS 조작시험 (병행) 양촌S/S 154kV 양촌-양곡#2T/L GIS 보통점검","2024-10-04 09:00","2024-10-04 18:00","2024-10-04 09:00","2024-10-04 18:00","연속"]
[103,"인천","김포","양곡연락 T/L","양곡S/S 154kV 양곡연락T/L GIS SA 혼용화 공사","양곡S/S 154kV 양곡연락T/L GIS SA 혼용화 공사 (병행) 옥내 GIS 조작시험 (병행) 옥외 GIS 초기점검","2024-10-05 09:00","2024-10-05 18:00","2024-10-05 09:00","2024-10-05 18:00","연속"]
[104,"인천","김포","왕길양촌#2 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","고정형폴리머점퍼지지애자 설치","2024-10-16 07:30","2024-10-16 18:00","2024-10-16 07:30","2024-10-16 18:00","연속"]
[105,"인천","부평","신가좌S/S SEC CB 65660","신가좌S/S 154kV #65-#66 SEC 보통점검","신가좌S/S 154kV #65-#66 SEC 보통점검","2024-10-24 09:00","2024-10-24 18:00","취소","취소","연속"]
[106,"인천","부평","신가좌S/S SEC CB 66670","신가좌S/S 154kV #66-#67 SEC GIS 보통점검","신가좌S/S 154kV #66-#67 SEC GIS 보통점검","2024-10-25 09:00","2024-10-25 18:00","취소","취소","연속"]
[107,"인천","부평","신가좌신현#1 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","수평추락 설치","2024-10-12 07:30","2024-10-12 18:00","취소","취소","매일"]
[108,"인천","부평","신가좌신현#2 T/L","24-25년 부평,김포전력지사 가공송전 협력회사 공사","수평추락 설치","2024-10-14 07:30","2024-10-14 18:00","취소","취소","매일"]
[109,"인천","부평","을왕중산 T/L","을왕S/S 154kV 을왕-중산T/L GIS 초기점검","을왕S/S 154kV 을왕-중산T/L GIS 초기점검","2024-10-16 09:00","2024-10-16 18:00","2024-10-16 09:00","2024-10-16 18:00","연속"]
[110,"인천","부평","영종을왕 T/L","을왕S/S 154kV 영종-을왕T/L GIS 초기점검","을왕S/S 154kV 영종-을왕T/L GIS 초기점검","2024-10-15 09:00","2024-10-15 18:00","2024-10-15 09:00","2024-10-15 18:00","연속"]
[111,"인천","부평","신가좌주안#2 T/L","154kV 주안-관교 등 4개T/L EBG 가스채취밸브 설치공사","EBG 가스채취밸브 설치 및 스프링 유니트 점검 시행","2024-10-14 09:00","2024-10-16 18:00","취소","취소","매일"]
[112,"인천","부평","관교주안 T/L","154kV 주안-관교 등 4개T/L EBG 가스채취밸브 설치공사","EBG 가스채취밸브 설치 및 스프링 유니트 점검 시행","2024-10-17 09:00","2024-10-18 18:00","취소","취소","매일"]
[113,"인천","부평","주안S/S CB 6100","주안S/S 주안S/S 154kV #1-#2 BUS TIE GIS 보통점검","주안S/S 주안S/S 154kV #1-#2 BUS TIE GIS 보통점검","2024-10-23 09:00","2024-10-23 18:00","취소","취소","연속"]
[114,"인천","부평","신가좌주안#1 T/L","154kV 주안-관교 등 4개T/L EBG 가스채취밸브 설치공사","EBG 가스채취밸브 설치 및 스프링 유니트 점검 시행","2024-10-10 09:00","2024-10-12 18:00","취소","취소","매일"]
[115,"인천","부평","주안만수#1 T/L","23~24년 지중송전설비 위탁정비공사","OF 케이블 절연유의 열화정도 확인","2024-10-28 09:00","2024-10-28 18:00","취소","취소","연속"]
[116,"인천","시흥","오봉고잔#1 T/L","고잔S/S 154kV 오봉고잔#1T/L GIS 정밀점검","고잔S/S 154kV 오봉고잔#1T/L GIS CB 정밀점검","2024-10-01 08:00","2024-10-02 18:00","취소","취소","연속"]
[117,"인천","시흥","오봉고잔#2 T/L","고잔S/S 154kV 오봉고잔#1T/L GIS 정밀점검","고잔S/S 154kV 오봉고잔#1T/L GIS CB 정밀점검","2024-10-07 09:00","2024-10-08 18:00","취소","취소","연속"]
[118,"인천","시흥","오봉남동#1 T/L","대한전선제 EBG 가스채취밸브 보강공사","대한전선제 EBG 가스채취밸브 보강공사","2024-10-21 08:00","2024-10-23 18:00","취소","취소","연속"]
[119,"인천","시흥","오봉남동#2 T/L","대한전선제 EBG 가스채취밸브 보강공사","대한전선제 EBG 가스채취밸브 보강공사","2024-10-24 08:00","2024-10-26 18:00","취소","취소","연속"]
[120,"인천","시흥","신시화남정왕#1 T/L","154kV 남정왕S/S #3M.Tr용 GIS 설치공사","154kV 남정왕S/S #3M.Tr 1차 GIS 설치 및 무부하가압","2024-10-10 09:00","2024-10-11 18:00","2024-10-10 09:00","2024-10-11 18:00","연속"]
[121,"인천","시흥","도림오봉#1 T/L","케이블타워 피뢰기교체공사 및 EBA 절연유 채취","- C/T 피뢰기교체 및 EBA 절연유 채취","2024-10-28 08:00","2024-10-29 18:00","취소","취소","연속"]
[122,"인천","시흥","도림오봉#2 T/L","케이블타워 피뢰기교체공사 및 EBA 절연유 채취","- C/T 피뢰기교체 및 EBA 절연유 채취","2024-10-30 08:00","2024-10-31 18:00","취소","취소","연속"]
[123,"인천","시흥","서안양소래 T/L","케이블타워 피뢰기 교체공사","154kV 서안양소래T/L 피뢰기 교체공사(소래C/T)","2024-10-19 08:00","2024-10-20 18:00","취소","취소","연속"]
[124,"인천","시흥","서서울#2소래 T/L","케이블타워 피뢰기 교체공사","154kV 서서울2소래T/L 피뢰기 교체공사(소래C/T)","2024-10-12 08:00","2024-10-13 18:00","취소","취소","연속"]
[125,"인천","시흥","송도송도열병합#1 T/L","송도S/S 154kV 인천종합#1T/L 가스압력계 점검","송도S/S 154kV 인천종합#1T/L 가스압력계 점검","2024-10-08 09:00","2024-10-08 18:00","취소","취소","연속"]
[126,"인천","시흥","신시흥S/S CB 6100","신시흥S/S 154kV 6100 B/T GIS 조작시험","신시흥S/S 154kV 6100(60-65) B/T GIS 조작시험","2024-10-11 09:00","2024-10-11 12:00","2024-10-11 09:00","2024-10-11 12:00","연속"]
[127,"인천","시흥","신시흥S/S SEC CB 60610","신시흥S/S 154kV 60-61 Sec. GIS 조작시험","신시흥S/S 154kV 60-61 Sec. GIS 조작시험","2024-10-11 12:00","2024-10-11 15:00","2024-10-11 12:00","2024-10-11 15:00","연속"]
[128,"인천","시흥","신시흥S/S SEC CB 66670","신시흥S/S 154kV 66-67 Sec. GIS 보통점검","신시흥S/S 154kV 66-67 Sec. GIS 보통점검","2024-10-07 09:00","2024-10-07 14:00","2024-10-07 09:00","2024-10-07 14:00","연속"]
[129,"인천","시흥","신시흥S/S SEC CB 65660","신시흥S/S 154kV 65-66 Sec. GIS 조작시험","신시흥S/S 154kV 65-66 Sec. GIS 조작시험","2024-10-11 15:00","2024-10-11 18:00","2024-10-11 15:00","2024-10-11 18:00","연속"]
[130,"인천","시흥","신시흥S/S CB 6400","신시흥S/S 154kV 6400 B/T GIS 조작시험","신시흥S/S 154kV 6400(63-68) B/T GIS 조작시험","2024-10-07 14:00","2024-10-07 18:00","2024-10-07 14:00","2024-10-07 18:00","연속"]
[131,"인천","시흥","신시흥S/S CB 6300","신시흥S/S 154kV 6300 B/T GIS 보통점검","신시흥S/S 154kV 6300(62-67) B/T GIS 보통점검 - 전자변 교체","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[132,"인천","시흥","신시흥북시화#1 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 : No.1~17 (17기) 소도체 이도조정 : No.6,7,14,17 (4기)","2024-10-22 07:30","2024-10-25 18:00","2024-10-22 07:30","2024-10-25 18:00","매일"]
[133,"인천","시흥","신시흥시화#2 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 : No.1~17 (17기) 소도체 이도조정 : No.6,7,14,17 (4기)","2024-10-28 07:30","2024-10-31 18:00","2024-10-28 07:30","2024-10-31 18:00","매일"]
[134,"인천","시흥","신시흥북시화#2 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 : No.1~17 (17기) 소도체 이도조정 : No.6,7,14,17 (4기)","2024-10-28 07:30","2024-10-31 18:00","2024-10-28 07:30","2024-10-31 18:00","매일"]
[135,"인천","시흥","신시흥시화#1 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 : No.1~17 (17기) 소도체 이도조정 : No.6,7,14,17 (4기)","2024-10-22 07:30","2024-10-25 18:00","2024-10-22 07:30","2024-10-25 18:00","매일"]
[136,"인천","직할","부흥부개#2 T/L","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 무부하가압","2024-10-28 09:00","2024-10-30 18:00","2024-10-28 09:00","2024-10-30 18:00","연속"]
[137,"인천","직할","인천CC북인천#2 T/L","북인천S/S 170kV 인천CC북인천#2T/L GIS 보통점검","북인천S/S 170kV 인천CC북인천#2T/L GIS 보통점검","2024-10-24 09:30","2024-10-24 18:00","2024-10-24 09:30","2024-10-24 18:00","연속"]
[138,"인천","직할","인천CC북인천#1 T/L","북인천S/S 170kV 인천CC북인천#1T/L GIS 보통점검","북인천S/S 170kV 인천CC북인천#1T/L GIS 보통점검","2024-10-23 09:30","2024-10-23 18:00","2024-10-23 09:30","2024-10-23 18:00","연속"]
[139,"인천","직할","신부평임학#2 T/L","신부평S/S 신부평임학#2T/L 정밀점검","신부평S/S 신부평임학#2T/L 정밀점검","2024-10-16 14:00","2024-10-18 18:00","2024-10-16 14:00","2024-10-18 18:00","연속"]
[140,"인천","직할","신부평임학#1 T/L","신부평S/S 신부평임학#1T/L 정밀점검","신부평S/S 신부평임학#1T/L 정밀점검","2024-10-14 09:00","2024-10-16 14:00","2024-10-14 09:00","2024-10-16 14:00","연속"]
[141,"인천","직할","부천원미#2 T/L","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 170KV GIS 설치 및 무부하가압","2024-10-07 09:00","2024-10-08 18:00","2024-10-07 09:00","2024-10-08 18:00","연속"]
[142,"인천","직할","부천원미#2 T/L","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 170KV GIS 설치 및 무부하가압","2024-10-14 09:00","2024-10-15 18:00","2024-10-14 09:00","2024-10-15 18:00","연속"]
[143,"인천","직할","중동S/S 부천복합 #3G/T CB 6313","중동S/S 154kV G/T#3 GIS 보통점검","중동S/S 154kV G/T#3 GIS 보통점검","2024-10-14 09:00","2024-10-14 18:00","2024-10-14 09:00","2024-10-14 18:00","연속"]
[144,"인천","직할","부흥S/S CB 6100","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 모선보호반 내부회로 증설","2024-10-03 09:00","2024-10-04 18:00","2024-10-03 09:00","2024-10-04 18:00","연속"]
[145,"인천","직할","계양북인천 T/L"," 북인천S/S 170kV 계양북인천T/L GIS 정밀점검"," 북인천S/S 170kV 계양북인천T/L GIS 정밀점검","2024-10-06 09:00","2024-10-08 18:00","2024-10-06 09:00","2024-10-08 18:00","연속"]
[146,"인천","직할","신부평고강#2 T/L","신부평고강#2 T/L 보호반대체 및 GIS 보통점검(양단)","신부평고강#2 T/L 보호반대체 및 GIS 보통점검(양단)","2024-10-12 09:00","2024-10-13 18:00","취소","취소","연속"]
[147,"인천","직할","신부평고강#1 T/L","23~24년 지중송전설비 위탁정비공사","EBA 절연유채취 및 피뢰기 C/T점검","2024-10-19 09:00","2024-10-20 18:00","취소","취소","연속"]
[148,"인천","직할","부흥S/S #60 BUS","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 170KV GIS 설치 및 무부하가압","2024-10-28 09:00","2024-10-29 09:00","취소","취소","연속"]
[149,"인천","직할","부흥S/S #65 BUS","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 170KV GIS 설치 및 무부하가압","2024-10-29 09:00","2024-10-30 18:00","2024-10-29 09:00","2024-10-30 18:00","연속"]
[150,"경기북부","구리","지제용문#2 T/L","용문S/S 154kV 장기사용 GIS 교체공사(1차분) 시험가압 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) 시험가압 휴전 ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 휴전사유 : #2BUS 신규 GIS 시험가압 진행하기 위해 무부하가압용 T/L 필요(지제-용문#2T/L)","2024-10-07 15:00","2024-10-09 15:00","2024-10-07 15:00","2024-10-09 15:00","연속"]
[151,"경기북부","구리","신포천백학#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 신포천-백학#1T/L No.1~3,6,9~74","2024-10-01 07:00","2024-10-07 18:00","2024-10-02 07:00","2024-10-08 18:00","연속"]
[152,"경기북부","직할","옥정동두천#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 피뢰기설치공사","2024-10-01 07:00","2024-10-01 13:00","2024-10-08 07:00","2024-10-08 13:00","연속"]
[153,"경기북부","직할","옥정송우#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 피뢰기설치공사","2024-10-01 07:00","2024-10-01 18:00","2024-10-08 07:00","2024-10-08 18:00","연속"]
[154,"경기북부","고양","백학남면#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 백학-남면#2T/L No.2~35","2024-10-01 07:00","2024-10-07 18:00","2024-10-02 07:00","2024-10-08 18:00","연속"]
[155,"경기북부","직할","신의정부송우#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 피뢰기설치공사","2024-10-01 13:00","2024-10-01 18:00","2024-10-08 13:00","2024-10-08 18:00","연속"]
[156,"경기북부","직할","옥정송우#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 피뢰기설치공사","2024-10-02 07:00","2024-10-02 13:00","2024-10-02 07:00","2024-10-02 13:00","연속"]
[157,"경기북부","직할","옥정동두천#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 피뢰기설치공사","2024-10-02 07:00","2024-10-07 18:00","2024-10-02 07:00","2024-10-07 18:00","연속"]
[158,"경기북부","직할","신포천동두천#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 피뢰기설치공사","2024-10-02 13:00","2024-10-07 18:00","2024-10-02 13:00","2024-10-07 18:00","연속"]
[159,"경기북부","구리","미금화양 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 점검","2024-10-04 09:00","2024-10-04 18:00","2024-10-04 09:00","2024-10-04 18:00","연속"]
[160,"경기북부","직할","장암진접#1 T/L","24-25 변전협력 총액공사","170kV GIS 하자점검","2024-10-05 09:00","2024-10-05 18:00","2024-10-06 09:00","2024-10-06 18:00","연속"]
[161,"경기북부","고양","원흥수색#1 T/L","23-24년 지중송전설비 위탁정비공사","154kV 원흥-수색T/L M/H#1 C상 SVL 교체","2024-10-07 09:00","2024-10-08 18:00","2024-10-07 09:00","2024-10-08 18:00","연속"]
[162,"경기북부","직할","옥정양주열병합#1 T/L","경기북부 직할 및 양주전력TF 362, 170kV GIS 보통점검 공사","옥정SS 옥정-양주CC #1TL GIS 보통점검","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[163,"경기북부","구리","진건별내#1 T/L","(주)세니온 보호계전기 성능개선 시행","유사 불량사례 발생 가능성 사전 제거를 위한 성능개선","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[164,"경기북부","구리","신포천덕계#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 신포천-덕계#1T/L No.65~70","2024-10-08 07:00","2024-10-08 18:00","2024-10-21 07:00","2024-10-21 18:00","연속"]
[165,"경기북부","직할","백석덕계#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154kV 백석-덕계#1T/L No.22~28","2024-10-08 07:00","2024-10-08 18:00","2024-10-21 07:00","2024-10-21 18:00","연속"]
[166,"경기북부","구리","진건별내#2 T/L","(주)세니온 보호계전기 성능개선 시행","유사 불량사례 발생 가능성 사전 제거를 위한 성능개선","2024-10-08 09:00","2024-10-08 18:00","2024-10-08 09:00","2024-10-08 18:00","연속"]
[167,"경기북부","직할","옥정양주열병합#2 T/L","경기북부 직할 및 양주전력TF 362, 170kV GIS 보통점검 공사","옥정SS 옥정-양주CC #2TL GIS 보통점검","2024-10-08 09:00","2024-10-08 18:00","2024-10-08 09:00","2024-10-08 18:00","연속"]
[168,"경기북부","구리","용문S/S #1 BUS","용문S/S 154kV 장기사용 GIS 교체공사(1차분)","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 모선 휴전순서 : #60 → #65 → #60 → #65BUS ○ 휴전사유 : #1DS, CB부, 상부BUS 신규 GIS 설치 및 LCP 결선","2024-10-09 09:00","2024-10-23 18:00","2024-10-09 09:00","2024-10-23 18:00","연속"]
[169,"경기북부","직할","용현장암#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 용현-장암#2T/L No.2~29","2024-10-10 07:00","2024-10-15 18:00","2024-10-10 07:00","2024-10-15 18:00","연속"]
[170,"경기북부","직할","금오상계#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 금오-상계#1T/L No.2~29","2024-10-10 07:00","2024-10-15 18:00","2024-10-10 07:00","2024-10-15 18:00","연속"]
[171,"경기북부","구리","신포천동두천#2 T/L","24-25년 구리전력지사 변전협력회사 공사","신포천-동두천#2T/L 보호반 대체","2024-10-10 09:00","2024-10-16 18:00","2024-10-10 09:00","2024-10-16 18:00","연속"]
[172,"경기북부","구리","운천철원#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[173,"경기북부","구리","곤지암용문#2 T/L","용문S/S 154kV 장기사용 GIS 교체공사(1차분) 이격거리 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) 이격거리 휴전 ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 휴전사유 : 곤지암-용문#1T/L 월부싱 설치 시 이격거리 휴전 필요(곤지암-용문#2T/L, 지제-용문#2T/L)","2024-10-12 09:00","2024-10-12 13:00","2024-10-12 09:00","2024-10-12 13:00","연속"]
[174,"경기북부","구리","지제용문#2 T/L","용문S/S 154kV 장기사용 GIS 교체공사(1차분) 이격거리 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) 이격거리 휴전 ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 휴전사유 : 곤지암-용문#1T/L 월부싱 설치 시 이격거리 휴전 필요(곤지암-용문#2T/L, 지제-용문#2T/L)","2024-10-12 09:00","2024-10-12 13:00","2024-10-12 09:00","2024-10-12 13:00","연속"]
[175,"경기북부","구리","신포천전곡#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 추락방지시설 설치","2024-10-14 07:00","2024-10-14 18:00","2024-10-14 07:00","2024-10-14 18:00","연속"]
[176,"경기북부","구리","신포천덕계#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 불량애자교체","2024-10-14 07:00","2024-10-14 18:00","2024-10-14 07:00","2024-10-14 18:00","연속"]
[177,"경기북부","구리","포천운천#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-10-14 09:00","2024-10-14 18:00","2024-10-14 09:00","2024-10-14 18:00","연속"]
[178,"경기북부","고양","고양S/S #1 BUS","154kV 고양S/S #4M.Tr 증설공사","154kV 고양S/S #4M.Tr 170kV GIS 개폐장치 설치 - 170kV GIS #1BUS측 조립 - 무부하 가압","2024-10-14 09:00","2024-10-19 20:00","2024-10-14 09:00","2024-10-19 20:00","연속"]
[179,"경기북부","직할","양주S/S #1 HVDC CB","24~25년 변전협력회사 총액공사","170kV GIS 분해가스 확산방지 자동차단밸브 설치","2024-10-14 09:00","2024-10-14 18:00","취소","취소","연속"]
[180,"경기북부","직할","양주금촌#1 T/L","24~25년 변전협력회사 총액공사","170kV GIS 분해가스 확산방지 자동차단밸브 설치","2024-10-15 09:00","2024-10-15 14:00","2024-10-15 09:00","2024-10-15 14:00","연속"]
[181,"경기북부","구리","신포천전곡#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 170kV GIS 점검","2024-10-15 09:00","2024-10-15 18:00","2024-10-15 09:00","2024-10-15 18:00","연속"]
[182,"경기북부","구리","덕소S/S CB 6200","덕소S/S #4M.Tr용 개폐장치 증설공사(전문)","덕소S/S #4M.Tr용 개폐장치 증설공사(전문) - 170kV #1BUS 증설","2024-10-15 09:00","2024-10-18 18:00","취소","취소","연속"]
[183,"경기북부","구리","덕소S/S SEC CB 65660","덕소S/S #4M.Tr용 개폐장치 증설공사(전문)","덕소S/S #4M.Tr용 개폐장치 증설공사(전문) - 170kV #2BUS 증설","2024-10-15 09:00","2024-10-18 18:00","취소","취소","연속"]
[184,"경기북부","구리","덕소진건#1 T/L","덕소S/S #4M.Tr용 개폐장치 증설공사(전문)","덕소S/S #4M.Tr용 개폐장치 증설공사(전문) - 170kV #1BUS 증설","2024-10-15 09:00","2024-10-18 18:00","2024-10-15 09:00","2024-10-18 18:00","연속"]
[185,"경기북부","구리","덕소진건#2 T/L","덕소S/S #4M.Tr용 개폐장치 증설공사(전문)","덕소S/S #4M.Tr용 개폐장치 증설공사(전문) - 170kV #1BUS 증설","2024-10-15 09:00","2024-10-18 18:00","2024-10-15 09:00","2024-10-18 18:00","연속"]
[186,"경기북부","구리","덕소S/S #66 BUS","덕소S/S #4M.Tr용 개폐장치 증설공사(전문)","덕소S/S #4M.Tr용 개폐장치 증설공사(전문) - 170kV #2BUS 증설","2024-10-15 09:00","2024-10-18 18:00","2024-10-15 09:00","2024-10-18 18:00","연속"]
[187,"경기북부","직할","운천전곡#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 지지애자교체","2024-10-15 13:00","2024-10-15 18:00","2024-10-15 13:00","2024-10-15 18:00","연속"]
[188,"경기북부","직할","양주금촌#2 T/L","24~25년 변전협력회사 총액공사","170kV GIS 분해가스 확산방지 자동차단밸브 설치","2024-10-15 14:00","2024-10-15 18:00","2024-10-15 14:00","2024-10-15 18:00","연속"]
[189,"경기북부","직할","신의정부내촌#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-내촌#1T/L No.24~41","2024-10-16 08:00","2024-10-18 18:00","2024-10-16 08:00","2024-10-18 18:00","연속"]
[190,"경기북부","직할","양주고양#1 T/L","24~25년 변전협력회사 총액공사","170kV GIS 분해가스 확산방지 자동차단밸브 설치","2024-10-16 09:00","2024-10-16 14:00","2024-10-16 09:00","2024-10-16 14:00","연속"]
[191,"경기북부","직할","양주고양#2 T/L","24~25년 변전협력회사 총액공사","170kV GIS 분해가스 확산방지 자동차단밸브 설치","2024-10-16 14:00","2024-10-16 18:00","2024-10-16 14:00","2024-10-16 18:00","연속"]
[192,"경기북부","구리","포천운천#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 피뢰기설치공사","2024-10-17 07:00","2024-10-31 18:00","2024-10-17 07:00","2024-10-31 18:00","연속"]
[193,"경기북부","구리","신포천포천#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 피뢰기설치공사","2024-10-17 07:00","2024-10-21 18:00","2024-10-17 07:00","2024-10-21 18:00","연속"]
[194,"경기북부","구리","미금S/S CB 6100","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 점검","2024-10-17 09:00","2024-10-17 18:00","2024-10-17 09:00","2024-10-17 18:00","연속"]
[195,"경기북부","구리","미금S/S CB 6300","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 점검","2024-10-18 09:00","2024-10-18 18:00","2024-10-18 09:00","2024-10-18 18:00","연속"]
[196,"경기북부","구리","미금S/S CB 6200","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 점검","2024-10-18 09:00","2024-10-18 18:00","2024-10-18 09:00","2024-10-18 18:00","연속"]
[197,"경기북부","고양","양주고양#2 T/L","154kV 고양S/S #4M.Tr 증설공사","154kV 고양S/S #4M.Tr 170kV GIS 개폐장치 설치 - 170kV GIS #1BUS측 조립시 인근Bay 가스 감압 - 무부하가압선로","2024-10-18 09:00","2024-10-19 20:00","2024-10-18 09:00","2024-10-19 20:00","연속"]
[198,"경기북부","직할","금오상계#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 금오-상계#2T/L No.2~29","2024-10-21 07:00","2024-10-31 18:00","2024-10-21 07:00","2024-10-31 18:00","연속"]
[199,"경기북부","직할","양주녹양#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평추락방지장치 설치 - 154kV 녹양-백석#2T/L No.5~11","2024-10-21 07:00","2024-10-21 18:00","취소","취소","연속"]
[200,"경기북부","고양","남면백석#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치(수평) 설치","2024-10-21 07:00","2024-10-25 17:00","2024-10-21 07:00","2024-10-25 17:00","매일"]
[201,"경기북부","직할","녹양백석#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평추락방지장치 설치 - 154kV 녹양-백석#2T/L No.1~11","2024-10-21 07:00","2024-10-21 18:00","취소","취소","연속"]
[202,"경기북부","구리","덕소S/S SEC CB 60610","덕소S/S #4M.Tr용 개폐장치 증설공사(전문)","덕소S/S #4M.Tr용 개폐장치 증설공사(전문) - 170kV #1BUS 증설","2024-10-21 09:00","2024-10-30 18:00","취소","취소","연속"]
[203,"경기북부","구리","덕소S/S #61 BUS","덕소S/S #4M.Tr용 개폐장치 증설공사(전문)","덕소S/S #4M.Tr용 개폐장치 증설공사(전문) - 170kV #1BUS 증설","2024-10-21 09:00","2024-10-30 18:00","2024-10-21 09:00","2024-10-30 18:00","연속"]
[204,"경기북부","고양","고양S/S #2 BUS","154kV 고양S/S #4M.Tr 증설공사","154kV 고양S/S #4M.Tr 170kV GIS 개폐장치 설치 - 170kV GIS #2BUS측 조립 - 무부하가압","2024-10-21 09:00","2024-10-26 20:00","2024-10-21 09:00","2024-10-26 20:00","연속"]
[205,"경기북부","구리","덕소진건#2 T/L","덕소S/S #4M.Tr용 개폐장치 증설공사(전문)","덕소S/S #4M.Tr용 개폐장치 증설공사(전문) - 170kV #2BUS 증설","2024-10-21 09:00","2024-10-30 18:00","2024-10-21 09:00","2024-10-30 18:00","연속"]
[206,"경기북부","구리","덕소S/S CB 6200","덕소S/S #4M.Tr용 개폐장치 증설공사(전문)","덕소S/S #4M.Tr용 개폐장치 증설공사(전문) - 170kV #2BUS 증설","2024-10-21 09:00","2024-10-30 18:00","취소","취소","연속"]
[207,"경기북부","구리","덕소진건#1 T/L","덕소S/S #4M.Tr용 개폐장치 증설공사(전문)","덕소S/S #4M.Tr용 개폐장치 증설공사(전문) - 170kV #2BUS 증설","2024-10-21 09:00","2024-10-30 18:00","2024-10-21 09:00","2024-10-30 18:00","연속"]
[208,"경기북부","구리","내촌용정#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 내촌-용정#2T/L No.32,33","2024-10-22 07:00","2024-10-22 18:00","2024-10-22 07:00","2024-10-22 18:00","연속"]
[209,"경기북부","구리","용정포천#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 포천-용정#1T/L No.1~4","2024-10-22 07:00","2024-10-22 18:00","2024-10-22 07:00","2024-10-22 18:00","연속"]
[210,"경기북부","직할","신의정부내촌#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-내촌#1T/L No.24~41","2024-10-23 07:00","2024-10-25 18:00","2024-10-23 07:00","2024-10-25 18:00","연속"]
[211,"경기북부","구리","청평H/P #1 M.TR 2차 CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 점검","2024-10-23 09:00","2024-10-23 18:00","2024-10-23 09:00","2024-10-23 18:00","연속"]
[212,"경기북부","구리","청평P/P #1 M.Tr 2차 CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 점검","2024-10-24 09:00","2024-10-24 18:00","2024-10-24 09:00","2024-10-24 18:00","연속"]
[213,"경기북부","구리","지제용문#2 T/L","용문S/S 154kV GIS 교체공사(1차분) 시험가압, DS절체 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) 시험가압 및 DS절체 조작 휴전 ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 휴전사유 - #1BUS 신규 GIS 시험가압 진행하기 위해 무부하가압용 T/L 필요(지제-용문#2T/L) - #2BUS 휴전을 위해 양DS 무부하가압용 T/L","2024-10-24 09:00","2024-10-24 11:00","2024-10-24 09:00","2024-10-24 11:00","연속"]
[214,"경기북부","구리","용문S/S #2 BUS","용문S/S 154kV 장기사용 GIS 교체공사(1차분) 인터록 시험","□ 용문S/S 154kV 장기사용 GIS 교체공사(1차분) 인터록 시험 ○ 1차분 교체개소 : #2M.Tr 1차, 곤지암-용문#1T/L, BUS-TIE, PT&ES ○ 휴전사유 : BUS ES ↔ 2DS 인터록, LCP 접점 시험 진행하기 위해 #2BUS 휴전 필요","2024-10-24 09:00","2024-10-24 18:00","2024-10-24 09:00","2024-10-24 18:00","연속"]
[215,"경기북부","고양","양주고양#2 T/L","154kV 고양S/S #4M.Tr 증설공사","154kV 고양S/S #4M.Tr 170kV GIS 개폐장치 설치 - 170kV GIS #2BUS측 조립시 인근Bay 가스 감압 - 무부하가압선로","2024-10-25 09:00","2024-10-26 20:00","2024-10-25 09:00","2024-10-26 20:00","연속"]
[216,"경기북부","구리","서종청평PP#1 T/L","154kV 서종분기T/L 설비개선공사","- 목적 : 기설철탑 부재보강으로 안전도 향상을 통한 안정적 전력공급 및 경기도 양평군 서종면 문호4리 길곡마을 장기 민원(154kV C/T 철탑높이 축소) 해소를 통한 합의서 이행 - 사업구간 : 154kV 동서울-서종T/L No.1,2 ~ 154kV 서종-청평PP T/L No.63,64 - 경과지역 : 경기도 양평군 서종면 문호리 일원 - 회선길이 : 2B, 0.447km - 지 지 물 : 154kV 4회선 C/T 1기 높이 축소(47m→34m) - 전 력 선 : ACSR 410㎟ × 2B × 2C - 0.447km","2024-10-25 09:00","2024-10-31 18:00","2024-10-28 09:00","2024-11-01 18:00","연속"]
[217,"경기북부","구리","서종청평PP#2 T/L","154kV 서종분기T/L 설비개선공사","- 목적 : 기설철탑 부재보강으로 안전도 향상을 통한 안정적 전력공급 및 경기도 양평군 서종면 문호4리 길곡마을 장기 민원(154kV C/T 철탑높이 축소) 해소를 통한 합의서 이행 - 사업구간 : 154kV 동서울-서종T/L No.1,2 ~ 154kV 서종-청평PP T/L No.63,64 - 경과지역 : 경기도 양평군 서종면 문호리 일원 - 회선길이 : 2B, 0.447km - 지 지 물 : 154kV 4회선 C/T 1기 높이 축소(47m→34m) - 전 력 선 : ACSR 410㎟ × 2B × 2C - 0.447km","2024-10-25 09:00","2024-10-31 18:00","2024-10-28 09:00","2024-11-01 18:00","연속"]
[218,"경기북부","구리","동서울서종#2 T/L","154kV 서종분기T/L 설비개선공사","- 목적 : 기설철탑 부재보강으로 안전도 향상을 통한 안정적 전력공급 및 경기도 양평군 서종면 문호4리 길곡마을 장기 민원(154kV C/T 철탑높이 축소) 해소를 통한 합의서 이행 - 사업구간 : 154kV 동서울-서종T/L No.1,2 ~ 154kV 서종-청평PP T/L No.63,64 - 경과지역 : 경기도 양평군 서종면 문호리 일원 - 회선길이 : 2B, 0.447km - 지 지 물 : 154kV 4회선 C/T 1기 높이 축소(47m→34m) - 전 력 선 : ACSR 410㎟ × 2B × 2C - 0.447km","2024-10-25 09:00","2024-10-31 18:00","2024-10-28 09:00","2024-11-01 18:00","연속"]
[219,"경기북부","구리","동서울서종#1 T/L","154kV 서종분기T/L 설비개선공사","- 목적 : 기설철탑 부재보강으로 안전도 향상을 통한 안정적 전력공급 및 경기도 양평군 서종면 문호4리 길곡마을 장기 민원(154kV C/T 철탑높이 축소) 해소를 통한 합의서 이행 - 사업구간 : 154kV 동서울-서종T/L No.1,2 ~ 154kV 서종-청평PP T/L No.63,64 - 경과지역 : 경기도 양평군 서종면 문호리 일원 - 회선길이 : 2B, 0.447km - 지 지 물 : 154kV 4회선 C/T 1기 높이 축소(47m→34m) - 전 력 선 : ACSR 410㎟ × 2B × 2C - 0.447km","2024-10-25 09:00","2024-10-31 18:00","2024-10-28 09:00","2024-11-01 18:00","연속"]
[220,"경기북부","직할","용현장암#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 용현-장암#1T/L No.2~29","2024-10-28 07:00","2024-10-31 18:00","2024-10-28 07:00","2024-10-31 18:00","연속"]
[221,"경기북부","구리","신장덕소#2 T/L","24~25년 구리송전협력회사공사_피뢰기설치(신장덕소2)","송전선로용 피뢰기 설치, 애자련교체","2024-10-28 08:00","2024-11-01 18:00","2024-10-22 08:00","2024-10-28 18:00","연속"]
[222,"경기","군포","서서울S/S CB 6300","서서울S/S #62-67 BUS 세니온제 모선보호반 콘덴서 개선품 취부","서서울S/S 154kV #62-67 BUS 세니온제 모선보호반 콘덴서 개선품 취부","2024-10-08 09:00","2024-10-08 18:00","2024-10-08 09:00","2024-10-08 18:00","연속"]
[223,"경기","군포","서서울S/S CB 6200","서서울S/S #61-66 BUS 세니온제 모선보호반 콘덴서 개선품 취부","서서울S/S 154kV #61-66 BUS 세니온제 모선보호반 콘덴서 개선품 취부","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[224,"경기","군포","장덕마도 T/L","장덕S/S 154kV SW 증설공사","장덕S/S 장덕-마도T/L 이설작업(신규GIS-철탑분기) - 변전 : 보호반이설 작업 - 송전 : 송전선 철탑 인입변경 - 제어 : OPGW 분기작업","2024-10-01 09:00","2024-10-06 18:00","2024-10-01 09:00","2024-10-06 18:00","연속"]
[225,"경기","군포","화성장덕 T/L","장덕S/S 화성-장덕T/L GIS 일진제 볼스톱퍼 교체(05-08년)","장덕S/S 화성-장덕T/L GIS 일진제 볼스톱퍼 교체(05-08년)","2024-10-23 14:00","2024-10-23 18:00","2024-10-23 14:00","2024-10-23 18:00","연속"]
[226,"경기","동부","곤지암용문#2 T/L","24-25 동부전력지사 송전협력회사 공사","수평 추락방지장치 설치공사(13~83호)","2024-10-07 07:30","2024-10-08 18:00","2024-10-07 07:30","2024-10-08 18:00","연속"]
[227,"경기","동부","곤지암S/S CB 6300","24-25년 동부 변전정비 총액공사","곤지암:6300(메커니즘 점검)","2024-10-15 09:30","2024-10-15 18:00","2024-10-15 09:30","2024-10-15 18:00","연속"]
[228,"경기","동부","곤지암S/S SEC CB 66670","24-25년 동부 변전정비 총액공사","곤지암:곤지암-전철#1T/L(보통) (메커니즘 점검) 곤지암:66-67(메커니즘 점검))","2024-10-11 09:30","2024-10-11 18:00","취소","취소","연속"]
[229,"경기","동부","곤지암S/S SEC CB 61620","24-25년 동부 변전정비 총액공사","곤지암:6444(메커니즘 점검),61-62(메커니즘 점검)","2024-10-16 14:00","2024-10-16 18:00","취소","취소","연속"]
[230,"경기","동부","곤지암율현#1 T/L","24-25 동부전력지사 송전협력회사 공사","수평 추락방지장치 설치공사(29~52호, 2회선 구간)","2024-10-10 07:30","2024-10-14 18:00","2024-10-10 07:30","2024-10-14 18:00","연속"]
[231,"경기","동부","산성수서#2 T/L","24-25년 동부 변전정비 총액공사","산성:산성-수서#2T/L(보통) LA,CVT(보통)","2024-10-25 09:30","2024-10-25 18:00","2024-10-25 09:30","2024-10-25 18:00","연속"]
[232,"경기","동부","산성수서#1 T/L","24-25년 동부 변전정비 총액공사","산성:산성-수서#1T/L(보통) LA,CVT(보통)","2024-10-23 09:30","2024-10-23 18:00","2024-10-23 09:30","2024-10-23 18:00","연속"]
[233,"경기","동부","성현분당#1 T/L","24-25년 동부 변전정비 총액공사","성현:성현-분당#1T/L(초기) 분당:성현-분당#1T/L(보통)","2024-10-02 09:30","2024-10-02 18:00","취소","취소","연속"]
[234,"경기","동부","오천용인#1 T/L","24-25년 가공송전협력회사 총액공사(피뢰기 설치)","154kV 용인-오천#1T/L 송전선로용 피뢰기 설치 대상 : No.1~58(총 58기)","2024-10-03 07:00","2024-10-12 18:00","취소","취소","연속"]
[235,"경기","동부","초월성현#2 T/L","24-25 동부전력지사 송전협력회사 공사","수평 추락방지장치 설치공사(1~59호, 곤지암-초월#2T/L 일부병가)","2024-10-15 07:30","2024-10-25 18:00","2024-10-15 07:30","2024-10-25 18:00","연속"]
[236,"경기","동부","곤지암초월#2 T/L","24-25 동부전력지사 송전협력회사 공사","수평 추락방지장치 설치공사(44~58호, 초월-성현#2T/L 4회선 병가구간)","2024-10-23 07:30","2024-10-25 18:00","2024-10-23 07:30","2024-10-25 18:00","연속"]
[237,"경기","동부","초월성현#1 T/L","24-25 동부전력지사 송전협력회사 공사","수평 추락방지장치 설치공사(44~58호, 곤지암-초월#1T/L 4회선 병가)","2024-10-28 07:30","2024-10-31 18:00","2024-10-28 07:30","2024-10-31 18:00","연속"]
[238,"경기","동부","곤지암초월#1 T/L","24-25 동부전력지사 송전협력회사 공사","수평 추락방지장치 설치공사(44~58호, 초월-성현#1T/L 4회선 병가)","2024-10-28 07:30","2024-10-31 18:00","2024-10-28 07:30","2024-10-31 18:00","연속"]
[239,"경기","성남","서안성남사#1 T/L","24-25년 경기본부 직할 송전협력회사 공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)[6회선 병가]","2024-10-18 07:00","2024-10-18 12:00","취소","취소","연속"]
[240,"경기","성남","덕성남사#2 T/L","24-25년 경기본부 직할 송전협력회사 공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)[6회선 병가]","2024-10-18 07:00","2024-10-18 12:00","취소","취소","연속"]
[241,"경기","성남","용인덕성#2 T/L","154kV 덕성S/S #1M.Tr용 170kV GIS 증설공사","M.Tr, 전력케이블 무부하가압용","2024-10-29 10:00","2024-10-30 10:00","2024-10-29 10:00","2024-10-30 10:00","연속"]
[242,"경기","성남","서판교중원#1 T/L","23-24년 지중송전설비 위탁정비공사(성남전력지사)","대한전선 열경화공법 EBG 가스채취밸브 설치","2024-10-10 09:00","2024-10-11 18:00","2024-10-10 09:00","2024-10-11 18:00","연속"]
[243,"경기","성남","신성남서판교#2 T/L","2024년 성남전력 변전협력회사 총액공사","(신성남) 가스압력계 교체","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[244,"경기","성남","신수원S/S #61 BUS","2024년 성남전력 170kV GIS 정밀점검공사","6433 GIS 무부하가압용","2024-10-08 17:00","2024-10-08 18:00","2024-10-08 17:00","2024-10-08 18:00","연속"]
[245,"경기","성남","신수원S/S #60 BUS","신수원S/S 154kV 동반#1,2T/L GIS 교체공사","154kV 동반#2T/L GIS 무부하가압","2024-10-23 10:00","2024-10-23 12:00","2024-10-23 10:00","2024-10-23 12:00","연속"]
[246,"경기","성남","신수원S/S #66 BUS","2024년 성남전력 170kV GIS 정밀점검공사","6133 GIS 무부하가압용","2024-10-11 17:00","2024-10-11 18:00","2024-10-11 17:00","2024-10-11 18:00","연속"]
[247,"경기","성남","신수원S/S #65 BUS","신수원S/S 154kV 동반#1,2T/L GIS 교체공사","154kV 동반#2T/L GIS 무부하가압","2024-10-23 12:00","2024-10-24 12:00","2024-10-23 12:00","2024-10-24 12:00","연속"]
[248,"경기","성남","신수원S/S #66 BUS","2024년 성남전력 170kV GIS 정밀점검공사","6333 GIS 무부하 가압용","2024-10-18 17:00","2024-10-18 18:00","2024-10-18 17:00","2024-10-18 18:00","연속"]
[249,"경기","성남","신용인용인#2 T/L","24-25년 경기본부 직할 송전협력회사 공사","철탑추락방지장치 설치 및 스페이서 간격조정(본사지시사항)[4회선 병가]","2024-10-24 07:00","2024-10-25 18:00","2024-10-24 07:00","2024-10-25 18:00","연속"]
[250,"경기","직할","관양동안양#1 T/L","동안양S/S 지중송전선로 인출정비 공사","154kV 관양-동안양T/L 인출정비 - 선종/길이 : XLPE 2000 / 0.426km","2024-10-19 08:00","2024-11-11 18:00","2024-10-19 08:00","2024-11-11 18:00","연속"]
[251,"경기","직할","동안양안양CC#1 T/L","154kV 연락T/L 설치관련 안전이격 휴전","154kV 연락T/L 전력케이블 포설을 위한 기초파쇄작업 안전이격","2024-10-20 08:00","2024-10-20 18:00","2024-10-20 08:00","2024-10-20 18:00","연속"]
[252,"경기","직할","동안양안양CC#2 T/L","154kV 연락T/L 설치관련 안전이격 휴전","154kV 연락T/L 전력케이블 포설을 위한 기초파쇄작업 안전이격","2024-10-20 08:00","2024-10-20 18:00","2024-10-20 08:00","2024-10-20 18:00","연속"]
[253,"경기","평택","원정만호#2 T/L","23-24년 지중송전설비 위탁정비공사(평택전력)","피뢰기 절연열화 측정 및 부싱청소","2024-10-22 08:00","2024-10-22 18:00","2024-10-22 08:00","2024-10-22 18:00","연속"]
[254,"경기","평택","서운삼죽 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","접속개소 전선교체(3.248C-km), 수평 추락방지장치 설치(61기)","2024-10-24 07:00","2024-11-07 18:00","취소","취소","연속"]
[255,"경기","평택","서운삼죽 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","접속개소 전선교체(3.248C-km), 수평 추락방지장치 설치(61기)","2024-10-24 07:00","2024-11-07 18:00","취소","취소","연속"]
[256,"경기","평택","송탄소사벌 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사)","EBA 절연유 채유, 피뢰기 절연열화 측정 및 부싱청소","2024-10-01 08:00","2024-10-02 18:00","2024-10-01 08:00","2024-10-02 18:00","연속"]
[257,"경기","평택","서안성안성#1 T/L","24년도 평택전력 변전협력회사 총액공사","안성S/S 서안성-안성#1T/L 170kV GIS 보통점검","2024-10-17 09:00","2024-10-17 14:00","취소","취소","연속"]
[258,"경기","평택","서안성안성#2 T/L","24년도 평택전력 변전협력회사 총액공사","안성S/S 서안성-안성#2T/L 170kV GIS 보통점검","2024-10-17 14:00","2024-10-17 18:00","취소","취소","연속"]
[259,"경기","평택","소사벌안성 T/L","154kV소사벌안성T/L 이도조정 및 조류착지방지설치(No.25~55)","2024~2025 송전정비 협력회사 총액공사 154kV 소사벌안성T/L 이도조정(54~55호), 조류착지방지설치(25~30호 6기)","2024-10-30 13:00","2024-11-01 18:00","취소","취소","연속"]
[260,"경기","평택","송탄안성 T/L","154kV 송탄안성T/L 이도조정 및 조류착지방지설치(No.25~55)","2024~2025 송전정비 협력회사 총액공사 154kV 송탄안성T/L 이도조정(54~55호), 조류착지방지설치(25~30호 6기)","2024-10-28 08:00","2024-10-30 13:00","취소","취소","연속"]
[261,"경기","평택","오산향남#1 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사)","피뢰기 절연열화진단 및 EBA가스채취","2024-10-04 08:00","2024-10-04 13:00","2024-10-04 08:00","2024-10-04 13:00","연속"]
[262,"경기","평택","오산향남#2 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사)","피뢰기 절연열화진단 및 EBA가스채취","2024-10-04 13:00","2024-10-04 18:00","2024-10-04 13:00","2024-10-04 18:00","연속"]
[263,"경기","평택","오산평택#1 T/L","23-24년 지중송전설비 위탁정비공사(평택전력지사)","피뢰기 절연열화진단 및 EBA가스채취","2024-10-26 08:00","2024-10-27 18:00","2024-10-26 08:00","2024-10-27 18:00","연속"]
[264,"경기","평택","평택추팔#1 T/L","24년도 평택전력 변전협력회사 총액공사","평택S/S GCB 보통점검","2024-10-16 09:00","2024-10-16 18:00","2024-10-16 09:00","2024-10-16 18:00","연속"]
[265,"경기","평택","평택추팔#2 T/L","24년도 평택전력 변전협력회사 총액공사","평택S/S GCB 보통점검","2024-10-17 09:00","2024-10-17 18:00","2024-10-17 09:00","2024-10-17 18:00","연속"]
[266,"경기","평택","포승평택TP#1 T/L","154kV 포승S/S #4M.TR 용 GIS 및 E-GIS 증설공사","- 154kV #4M.TR GIS 무부하가압","2024-10-03 09:00","2024-10-04 18:00","2024-10-03 09:00","2024-10-04 18:00","연속"]
[267,"경기","평택","포승평택TP#1 T/L","154kV 포승S/S #4M.TR 용 GIS 및 E-GIS 증설공사","- 154kV #4M.TR GIS 무부하가압","2024-10-14 09:00","2024-10-15 18:00","2024-10-14 09:00","2024-10-15 18:00","연속"]
[268,"경기","성남","신봉이의#2 T/L","(6월 순연) 24-25년 경기직할 가공송전 협력회사 총액공사","불량애자 교체공사[4회선 병가]","2024-10-04 07:00","2024-10-04 18:00","2024-10-04 07:00","2024-10-04 18:00","연속"]
[269,"경기","성남","남사동탄#1 T/L"," 추락방지장치(수평) 설치공사","154kV 남사-동탄#1T/L 12기","2024-10-14 08:00","2024-10-15 18:00","2024-10-14 08:00","2024-10-15 18:00","연속"]
[270,"경기","성남","남사동탄#2 T/L"," 추락방지장치(수평) 설치공사","154kV 남사-동탄#2T/L 12기","2024-10-16 08:00","2024-10-17 18:00","2024-10-16 08:00","2024-10-17 18:00","연속"]
[271,"경기","성남","신수원북동탄#1 T/L","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검 ","2024-10-01 09:00","2024-10-02 18:00","취소","취소","연속"]
[272,"경기","성남","신수원북동탄#2 T/L","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검 ","2024-10-03 09:00","2024-10-04 18:00","취소","취소","연속"]
[273,"경기","평택","원정평택TP#1 T/L"," 24년도 평택전력 변전협력회사 총액공사","평택T/P 평택TP-원정#1T/L GIS 보통점검 및 원정S/S 평택TP-원정#2T/L GIS 조작시험 및 PT&LA 보통점검","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[274,"경기","평택","원정평택TP#2 T/L"," 24년도 평택전력 변전협력회사 총액공사","평택T/P 평택TP-원정#1T/L GIS 보통점검 및 원정S/S 평택TP-원정#2T/L GIS 조작시험 및 PT&LA 보통점검","2024-10-11 09:00","2024-10-11 18:00","2024-10-11 09:00","2024-10-11 18:00","연속"]
[275,"강원","강릉","속초간성#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","무부하 시험가압","2024-10-24 16:00","2024-10-25 18:00","2024-10-24 16:00","2024-10-25 18:00","연속"]
[276,"강원","강릉","간성S/S CB 6100","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","154kV 모선구분차단기 대체공사","2024-10-28 09:00","2024-11-19 18:00","2024-10-28 09:00","2024-11-19 18:00","연속"]
[277,"강원","강릉","속초간성#1 T/L","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","무부하 시험가압","2024-10-17 16:00","2024-10-18 18:00","2024-10-17 16:00","2024-10-18 18:00","연속"]
[278,"강원","강릉","간성S/S #1 BUS","간성SA 154kV 모선구분차단기 설치 및 장기사용 GIS 대체공사","1. #61-66 B/T 설치 2. 간성인제#2T/L 대체 3. 154kV PT GIS 설치 4. 154kV Sh.C GIS 철거","2024-10-21 09:00","2024-10-25 18:00","2024-10-21 09:00","2024-10-25 18:00","연속"]
[279,"강원","강릉","신양양양양#2 T/L","2024년 강릉전력지사 변전협력회사 공사","154kV 장기미동작 차단기 동작시험","2024-10-17 14:00","2024-10-17 18:00","2024-10-17 14:00","2024-10-17 18:00","연속"]
[280,"강원","강릉","신양양양양#1 T/L","2024년 강릉전력지사 변전협력회사 공사","154kV 장기미동작 차단기 동작시험","2024-10-17 10:00","2024-10-17 14:00","2024-10-17 10:00","2024-10-17 14:00","연속"]
[281,"강원","강릉","북강릉주문진#2 T/L","2024년 강릉전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2024-10-21 09:00","2024-10-23 18:00","취소","취소","연속"]
[282,"강원","강릉","주진평창#1 T/L","2024년 가공송전 순시점검 위탁공사","○ 정밀점검 - 154kV 주진-평창T/L No.1~57 정밀점검 시행","2024-10-14 08:00","2024-10-18 18:00","2024-10-14 08:00","2024-10-18 18:00","매일"]
[283,"강원","강릉","주진평창#2 T/L","2024년 가공송전 순시점검 위탁공사","○ 정밀점검 - 154kV 주진-평창T/L No.1~57 정밀점검 시행","2024-10-21 08:00","2024-10-25 18:00","2024-10-21 08:00","2024-10-25 18:00","매일"]
[284,"강원","강릉","평창올림픽 T/L","2024-2025년 강릉전력지사 송전협력회사 공사","○ 상간스페이서 설치 : 154kV 횡계-평창T/L No.80~81","2024-10-02 13:00","2024-10-02 18:00","2024-10-11 13:00","2024-10-11 18:00","연속"]
[285,"강원","강릉","횡계평창 T/L","2024-2025년 강릉전력지사 송전협력회사 공사","○ 상간스페이서 설치 : 154kV 횡계-평창T/L No.80~81","2024-10-02 08:00","2024-10-02 13:00","2024-10-11 08:00","2024-10-11 13:00","연속"]
[286,"강원","동해","이원도계 T/L","2024~2025년 동해전력지사 변전협력회사 공사","도계 디지털화, LA초기점검, 차단기조작시험","2024-10-10 09:00","2024-10-11 18:00","취소","취소","연속"]
[287,"강원","동해","동해T/P #1 G.Tr 2차 CB","2024~2025년 동해전력지사 변전협력회사 공사","메커니즘점검","2024-10-28 09:00","2024-10-28 18:00","취소","취소","연속"]
[288,"강원","동해","이원동해TP T/L","2024~2025년 동해전력지사 변전협력회사 공사","차단기조작시험","2024-10-28 09:00","2024-10-28 18:00","취소","취소","연속"]
[289,"강원","동해","동해동영월 T/L","154kV 영월화력 등 3개T/L 철탑추락방지장치(수평) 설치공사","○ 추락방지장치(수평) 설치 ○ 송전선로 정밀점검 ○ 10/14~17 태백전력지사 GIS 정밀점검(연속)","2024-10-07 07:00","2024-10-22 18:00","2024-10-07 07:00","2024-10-22 18:00","매일"]
[290,"강원","동해","삼척G/P 기동#2T/L CB","2024∼2025년 동해전력지사 변전협력회사 공사","GIS 보통점검","2024-10-08 09:00","2024-10-08 18:00","2024-10-08 09:00","2024-10-08 18:00","연속"]
[291,"강원","동해","삼척G/P 기동#1T/L CB","2024∼2025년 동해전력지사 변전협력회사 공사","GIS 보통점검","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[292,"강원","동해","삼척G/P 기동#1T/L CB","2024∼2025년 동해전력지사 변전협력회사 공사","GIS 보통점검","2024-10-07 09:00","2024-10-07 18:00","취소","취소","연속"]
[293,"강원","동해","삼척G/P 기동#2T/L CB","2024∼2025년 동해전력지사 변전협력회사 공사","GIS 보통점검","2024-10-08 09:00","2024-10-08 18:00","취소","취소","연속"]
[294,"강원","동해","이원삼척 T/L","2024~2025년 동해전력지사 변전협력회사 공사","차단기조작시험","2024-10-30 09:00","2024-10-30 18:00","2024-10-30 09:00","2024-10-30 18:00","연속"]
[295,"강원","동해","정선영월CC T/L","154kV 영월화력 등 3개T/L 철탑추락방지장치(수평) 설치공사","○추락방지장치(수평) 설치 ○송전선로 정밀점검","2024-10-23 07:00","2024-10-25 18:00","2024-10-23 07:00","2024-10-25 18:00","매일"]
[296,"강원","동해","동해정선 T/L","154kV 영월화력 등 3개T/L 철탑추락방지장치(수평) 설치공사","○추락방지장치(수평) 설치 ○송전선로 정밀점검","2024-10-28 07:00","2024-11-12 18:00","2024-10-28 07:00","2024-11-12 18:00","매일"]
[297,"강원","원주","남원주원주#2 T/L","24-25년 원주전력지사 변전협력회사 총액공사","남원주S/S 디지털화 공사 - 감시제어용 케이블 이설 및 SCADA 준공시험","2024-10-21 09:00","2024-10-25 18:00","2024-10-21 09:00","2024-10-25 18:00","연속"]
[298,"강원","원주","신제천남원주#2 T/L","24-25년 원주전력지사 변전협력회사 총액공사","남원주S/S 디지털화 공사 - 감시제어용 케이블 이설 및 SCADA 준공시험","2024-10-28 09:00","2024-11-01 18:00","2024-10-28 09:00","2024-11-01 18:00","연속"]
[299,"강원","원주","남원주원주#1 T/L","24-25년 원주전력지사 변전협력회사 총액공사","남원주S/S 디지털화 공사 - 감시제어용 케이블 이설 및 SCADA 준공시험","2024-10-14 09:00","2024-10-18 18:00","2024-10-14 09:00","2024-10-18 18:00","연속"]
[300,"강원","원주","남원주원주#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 병가구간 안전확보","2024-10-28 09:00","2024-10-28 18:00","2024-10-28 09:00","2024-10-28 18:00","연속"]
[301,"강원","직할","남춘천춘천 T/L","남춘천S/S 154kV 장기사용 GIS 대체공사","■ 1차 공정 - 양DS 투입 후 GIS 모선절체용","2024-10-04 09:00","2024-10-04 18:00","2024-10-10 09:00","2024-10-11 18:00","연속"]
[302,"강원","직할","남춘천S/S #2 BUS","남춘천S/S 154kV 장기사용 GIS 대체공사","■ 1차 공정 - 154kV 홍천-남춘천T/L GIS 대체 - 154kV #2M.Tr 1차 GIS 대체","2024-10-14 09:00","2024-10-23 18:00","2024-10-30 09:00","2024-10-31 18:00","연속"]
[303,"강원","직할","남춘천춘천 T/L","남춘천S/S 154kV 장기사용 GIS 대체공사","■ 1차 공정 - 양DS 투입 후 GIS 모선절체용","2024-10-14 09:00","2024-10-14 18:00","2024-10-28 09:00","2024-10-31 18:00","연속"]
[304,"강원","직할","남춘천S/S #1 BUS","남춘천S/S 154kV 장기사용 GIS 대체공사","※2024. 10. 14 이후 즉시가압 가능 ■ 1차 공정 - 154kV 홍천-남춘천T/L GIS 대체 - 154kV #2M.Tr 1차 GIS 대체","2024-10-04 09:00","2024-11-06 18:00","2024-10-14 09:00","2024-10-29 18:00","연속"]
[305,"강원","직할","춘천북춘천#2 T/L","북춘천S/S 및 도계S/S 외장재 교체공사","노후 외장재(드라이비트) 철거 및 메탈판넬 설치","2024-10-14 08:00","2024-10-25 18:00","2024-10-14 08:00","2024-10-25 18:00","연속"]
[306,"강원","직할","북춘천춘천HP T/L","북춘천S/S 및 도계S/S 외장재 교체공사","노후 외장재(드라이비트) 철거 및 메탈판넬 설치","2024-10-18 08:00","2024-10-31 18:00","취소","취소","연속"]
[307,"강원","직할","춘천북춘천#1 T/L","북춘천S/S 및 도계S/S 외장재 교체공사","노후 외장재(드라이비트) 철거 및 메탈판넬 설치","2024-10-14 08:00","2024-10-17 18:00","2024-10-14 08:00","2024-10-17 18:00","연속"]
[308,"강원","직할","북춘천화천HP T/L","북춘천S/S 및 도계S/S 외장재 교체공사","노후 외장재(드라이비트) 철거 및 메탈판넬 설치","2024-10-28 08:00","2024-10-31 18:00","취소","취소","연속"]
[309,"강원","직할","인제양구#1 T/L","154kV 상제 등 3개 T/L 추락방지장치 설치공사","154kV 양구 T/L 수평추락방지장치 설칙오사","2024-10-28 09:00","2024-11-08 18:00","2024-10-28 09:00","2024-11-08 18:00","매일"]
[310,"강원","직할","인제양구#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","인제양구#2 T/L 차단기 조작시험(양단) 양구S/S LA 하자점검","2024-10-04 10:00","2024-10-04 18:00","2024-10-04 10:00","2024-10-04 18:00","연속"]
[311,"강원","직할","청평HP의암HP T/L","의암HP 154kV 청평HP-의암HP T/L 보호배전반 교체공사","- 의암HP 154kV 청평HP-의암HP T/L 보호배전반 교체공사 - 의암HP 154kV 청평HP-의암HP T/L GCB 정밀점검 등","2024-10-28 09:00","2024-11-01 18:00","2024-10-28 09:00","2024-11-01 18:00","연속"]
[312,"강원","직할","간성인제#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","간성인제#1T/L 차단기 조작시험","2024-10-15 12:00","2024-10-15 15:00","2024-10-15 12:00","2024-10-15 15:00","연속"]
[313,"강원","직할","인제S/S CB 6100","2024년~2025년 강원본부 직할 변전협력회사 공사","154kV #1BUS-TIE 차단기 조작시험","2024-10-15 10:00","2024-10-15 12:00","2024-10-15 10:00","2024-10-15 12:00","연속"]
[314,"강원","직할","양구화천HP#2 T/L","2024년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","□ 화천HP 154kV 양구-화천HP#2 T/L GIS 정밀점검","2024-10-14 09:00","2024-10-16 13:00","2024-10-23 13:00","2024-10-25 18:00","연속"]
[315,"강원","직할","화천화천HP#2 T/L","2024년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","□ 화천HP 154kV 북춘천-화천HP T/L GCB 정밀점검","2024-10-16 13:00","2024-10-18 18:00","2024-10-14 09:00","2024-10-16 13:00","연속"]
[316,"강원","직할","북춘천화천HP T/L","2024년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","□ 화천HP 154kV 북춘천-화천HP T/L GCB 정밀점검","2024-10-04 09:00","2024-10-08 18:00","2024-10-10 09:00","2024-10-11 18:00","연속"]
[317,"강원","직할","화천H/P #1 BUS","2024년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","  □ 화천HP 154kV #3M.Tr 2차 GCB 정밀점검 후 무부하가압 ","2024-10-11 09:00","2024-10-11 18:00","취소","취소","연속"]
[318,"강원","동해","동해S/S CB 7700","동해S/S 362kV GIS 정밀점검공사","362kV GIS 정밀점검","2024-10-14 09:00","2024-10-18 18:00","취소","취소","연속"]
[319,"강원","동해","동해S/S CB 7772","동해S/S 362kV GIS 정밀점검공사","345kV GIS 정밀점검","2024-10-21 09:00","2024-10-25 18:00","취소","취소","연속"]
[320,"강원","직할","화천화천HP#1 T/L","2024~2025년 강원본부 직할 송전협력회사 공사","애자련 교체","2024-10-21 08:00","2024-10-23 18:00","2024-10-21 08:00","2024-10-23 18:00","연속"]
[321,"강원","태백","영월에코윈드S/S 영월에코윈드발전소 #1M.Tr 1차 CB","영월에코윈드SY 분기DS 하자점검","#1Step-Up.Tr 6136 DS 하자점검","2024-10-30 09:00","2024-10-31 18:00","2024-10-30 09:00","2024-10-31 18:00","연속"]
[322,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사","- 무부하가압 및 사용전검사(실부하가압)","2024-10-21 14:00","2024-10-24 18:00","2024-10-21 14:00","2024-10-24 18:00","연속"]
[323,"강원","태백","태백S/S #65 BUS","154kV 태백S/S #2M.Tr 증설공사(준공시험)","준공시험, 인터록 시험","2024-10-15 14:00","2024-10-15 18:00","2024-10-15 14:00","2024-10-15 18:00","연속"]
[324,"강원","태백","태백S/S #60 BUS","154kV 태백S/S #2M.Tr 증설공사(준공시험)","준공시험, 인터록 시험","2024-10-15 09:00","2024-10-15 14:00","2024-10-15 09:00","2024-10-15 14:00","연속"]
[325,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-10-03 10:00","2024-10-04 18:00","2024-10-03 10:00","2024-10-04 18:00","연속"]
[326,"강원","태백","태백삼척GP#1 T/L","2024~2025년 태백전력지사 송전 협력회사 공사","154kV 태백-삼척GP#1 T/L 수평추락방지장치 설치","2024-10-07 09:00","2024-10-11 18:00","2024-10-10 09:00","2024-10-18 18:00","매일"]
[327,"강원","태백","태백S/S #65 BUS","154kV 태백S/S #2M.Tr 증설공사","- 무부하가압 및 사용전검사(실부하가압)","2024-10-22 14:00","2024-10-24 18:00","2024-10-22 14:00","2024-10-24 18:00","연속"]
[328,"강원","태백","태백S/S #60 BUS","154kV 태백S/S #2M.Tr 증설공사","- 무부하가압 및 사용전검사(실부하가압)","2024-10-21 14:00","2024-10-22 14:00","2024-10-21 14:00","2024-10-22 14:00","연속"]
[329,"충북","직할","진천광혜원#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","접속개소 전선교체(1.707C-km), 수평 추락방지장치 설치(36기)","2024-10-24 07:00","2024-11-01 18:00","2024-10-24 07:00","2024-11-01 18:00","연속"]
[330,"충북","직할","서운광혜원 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","접속개소 전선교체(3.248C-km), 수평 추락방지장치 설치(44기), 피뢰기 설치(64기)","2024-10-07 07:00","2024-10-22 18:00","2024-10-07 07:00","2024-10-22 18:00","연속"]
[331,"충북","직할","진천광혜원#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","접속개소 전선교체(1.707C-km), 수평 추락방지장치 설치(39기), 피뢰기 설치(39기)","2024-10-14 07:00","2024-10-22 18:00","2024-10-14 07:00","2024-10-22 18:00","연속"]
[332,"충북","직할","삼죽광혜원 T/L","24-25년 충북 직할 변전협력회사 공사","- 광혜원S/S 154kV 삼죽-광혜원T/L GIS 초기점검","2024-10-04 09:00","2024-10-04 18:00","2024-10-04 09:00","2024-10-04 18:00","연속"]
[333,"충북","직할","신진천S/S SEC CB 60610","24-25년 충북 직할 변전협력회사 공사","- 154kV 효성제 GIS 전자변 교체","2024-10-14 09:00","2024-10-14 18:00","취소","취소","연속"]
[334,"충북","직할","신진천진천#2 T/L","'24년 충북본부 직할 154kV GIS 정밀점검공사","신진천S/S 154kV 신진천-진천#2T/L GIS 정밀점검","2024-10-19 07:00","2024-10-20 18:00","취소","취소","연속"]
[335,"충북","직할","신진천S/S #67 BUS","'24년 충북본부 직할 154kV GIS 정밀점검공사","신진천S/S 154kV #4Sh.C GIS 정밀점검 후 무부하가압용","2024-10-18 09:00","2024-10-18 10:00","2024-10-18 09:00","2024-10-18 10:00","연속"]
[336,"충북","직할","신진천S/S SEC CB 66670","24-25년 충북 직할 변전협력회사 공사","- 154kV 효성제 GIS 전자변 교체 - 154kV GIS 보통점검","2024-10-17 09:00","2024-10-17 18:00","취소","취소","연속"]
[337,"충북","직할","신진천S/S SEC CB 65660","24-25년 충북 직할 변전협력회사 공사","- 154kV GIS 보통점검","2024-10-16 09:00","2024-10-16 18:00","취소","취소","연속"]
[338,"충북","직할","신진천진천#1 T/L","'24년 충북본부 직할 154kV GIS 정밀점검공사","신진천S/S 154kV 신진천-진천#1T/L GIS 정밀점검","2024-10-12 07:00","2024-10-13 18:00","취소","취소","연속"]
[339,"충북","직할","신진천S/S SEC CB 61620","24-25년 충북 직할 변전협력회사 공사","- 154kV GIS 보통점검 - 154kV 효성제 GIS 전자변 교체","2024-10-15 09:00","2024-10-15 18:00","취소","취소","연속"]
[340,"충북","직할","신진천진천#2 T/L","'24년 충북본부 직할 154kV GIS 정밀점검공사","진천S/S 154kV 신진천-진천#2T/L GIS 정밀점검","2024-10-05 07:00","2024-10-06 18:00","취소","취소","연속"]
[341,"충북","직할","진천S/S SEC CB 60610","'24년 충북본부 직할 154kV GIS 정밀점검공사","진천S/S 154kV #2 M.Tr GIS 정밀점검 후 무부하가압용","2024-10-03 09:00","2024-10-03 10:00","2024-10-03 09:00","2024-10-03 10:00","연속"]
[342,"충북","직할","진천S/S CB 6100","24년 충북본부 직할 154kV GIS 정밀점검공사","진천S/S 154kV #1 BUS TIE GIS 정밀점검","2024-10-07 08:00","2024-10-09 12:00","2024-10-07 08:00","2024-10-09 12:00","연속"]
[343,"충북","직할","진천S/S #60 BUS","'24년 충북본부 직할 154kV GIS 정밀점검공사","진천S/S 154kV #2M.Tr GIS 정밀점검 후 무부하가압용","2024-10-03 09:00","2024-10-03 10:00","2024-10-03 09:00","2024-10-03 10:00","연속"]
[344,"충북","직할","신진천진천#1 T/L","'24년 충북본부 직할 154kV GIS 정밀점검공사","진천S/S 154kV 신진천-진천#1T/L GIS 정밀점검","2024-10-26 07:00","2024-10-27 18:00","취소","취소","연속"]
[345,"충북","직할","진천S/S #60 BUS","'24년 충북본부 직할 154kV GIS 정밀점검공사","진천S/S 154kV #1 BUS-TIE GIS 정밀점검 후 무부하가압용","2024-10-09 09:00","2024-10-09 10:00","2024-10-09 09:00","2024-10-09 10:00","연속"]
[346,"충북","직할","진천S/S SEC CB 60610","'24년 충북본부 직할 154kV GIS 정밀점검공사","진천S/S 154kV #1 BUS-TIE GIS 정밀점검 후 무부하가압용","2024-10-09 09:00","2024-10-09 10:00","2024-10-09 09:00","2024-10-09 10:00","연속"]
[347,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-10-01 08:00","2024-10-04 14:00","취소","취소","연속"]
[348,"충북","청주","남청주청주#2 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-10-01 08:00","2024-10-19 18:00","취소","취소","연속"]
[349,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-10-04 14:00","2024-10-12 14:00","취소","취소","연속"]
[350,"충북","청주","남청주S/S CB 6200","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 초기점검","2024-10-11 10:00","2024-10-11 18:00","2024-10-11 10:00","2024-10-11 18:00","연속"]
[351,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-10-12 14:00","2024-10-19 18:00","취소","취소","연속"]
[352,"충북","청주","남청주오송#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검(양단 작업)","2024-10-21 10:00","2024-10-21 18:00","2024-10-21 10:00","2024-10-21 18:00","연속"]
[353,"충북","청주","남청주오송#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검(양단 작업)","2024-10-22 10:00","2024-10-21 18:00","2024-10-22 10:00","2024-10-22 18:00","연속"]
[354,"충북","청주","남청주S/S SEC CB 60610","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 초기점검","2024-10-23 10:00","2024-10-23 18:00","2024-10-23 10:00","2024-10-23 18:00","연속"]
[355,"충북","청주","남청주S/S SEC CB 65660","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 초기점검","2024-10-24 10:00","2024-10-24 18:00","2024-10-24 10:00","2024-10-24 18:00","연속"]
[356,"충북","청주","남청주S/S SEC CB 62610","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검","2024-10-28 10:00","2024-10-28 18:00","취소","취소","연속"]
[357,"충북","청주","남청주S/S SEC CB 67660","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검","2024-10-29 10:00","2024-10-29 18:00","취소","취소","연속"]
[358,"충북","청주","남청주S/S #62 BUS","24년 청주전력지사 170kV GIS 정밀점검","남청주S/S 154kV #2Sh.C GIS 정밀점검 후 무부하 가압","2024-10-30 16:00","2024-10-30 18:00","2024-10-30 16:00","2024-10-30 18:00","연속"]
[359,"충북","청주","남청주S/S SEC CB 62610","24년 청주전력지사 170kV GIS 정밀점검","남청주S/S 154kV #2Sh.C GIS 정밀점검 후 무부하 가압","2024-10-30 16:00","2024-10-30 18:00","2024-10-30 16:00","2024-10-30 18:00","연속"]
[360,"충북","청주","남청주S/S CB 6300","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 초기점검","2024-10-18 10:00","2024-10-18 18:00","2024-10-18 10:00","2024-10-18 18:00","연속"]
[361,"충북","청주","서청주사직#2 T/L","대한전선제 열경화공법 EBG 보강공사","서청주S/S, 사직S/S 154kV 서청주-사직T/L EBG 보강공사","2024-10-12 09:00","2024-10-13 18:00","2024-10-12 09:00","2024-10-13 18:00","연속"]
[362,"충북","청주","서청주사직#1 T/L","대한전선제 열경화공법 EBG 보강공사","서청주S/S, 사직S/S 154kV 서청주-사직T/L EBG 보강공사","2024-10-10 09:00","2024-10-11 18:00","2024-10-10 09:00","2024-10-11 18:00","연속"]
[363,"충북","청주","화동영동 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 화동-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 화동-영동T/L 수평 추락방지장치 설치 2. 구간 : 154kV 영동분기T/L 1~61호","2024-10-22 08:00","2024-10-30 18:00","취소","취소","매일"]
[364,"충북","청주","문백오창#1 T/L","154kV 신청주-문백T/L 건설공사","154kV 문백-오창#1T/L No.18-20 임시선로 구성","2024-10-26 07:00","2024-10-27 18:00","2024-10-26 07:00","2024-10-27 18:00","연속"]
[365,"충북","청주","문백오창#2 T/L","154kV 신청주-문백T/L 건설공사","154kV 문백-오창#2T/L No.18-20 임시선로 구성","2024-10-19 07:00","2024-10-20 18:00","2024-10-19 07:00","2024-10-20 18:00","연속"]
[366,"충북","청주","오창국사#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","오창S/S 154kV 오창-국사#1T/L GIS 정밀점검","2024-10-07 08:00","2024-10-08 18:00","2024-10-07 08:00","2024-10-08 18:00","연속"]
[367,"충북","청주","청주율량#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검","2024-10-14 10:00","2024-10-14 18:00","2024-10-18 10:00","2024-10-18 18:00","연속"]
[368,"충북","청주","청주율량#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검(청주,율량 양단 작업)","2024-10-25 10:00","2024-10-25 18:00","2024-10-25 10:00","2024-10-25 18:00","연속"]
[369,"충북","청주","율량봉명#1 T/L","24-25년 청주전력지사 변전협력회사 총액공사","봉명율량#1T/L 보호배전반 대체(양단)","2024-10-14 09:00","2024-10-16 18:00","2024-10-14 09:00","2024-10-16 18:00","연속"]
[370,"충북","충주","감곡가남#1 T/L","감곡S/S 23kV 장기사용 GIS 대체공사","RTU철거로 인한 제어케이블 SA LID 이설 및 시험","2024-10-01 09:00","2024-10-01 18:00","취소","취소","연속"]
[371,"충북","충주","감곡S/S #2 BUS","'24-25년 충주전력지사 변전정비티 총액공사[PT 집합반 대체]","'24-25년 충주전력지사 변전정비티 총액공사[PT 집합반 대체]","2024-10-02 09:00","2024-10-02 18:00","2024-10-02 09:00","2024-10-02 18:00","연속"]
[372,"충북","충주","신충주감곡#1 T/L","감곡S/S 23kV 장기사용 GIS 대체공사","RTU철거로 인한 제어케이블 SA LID 이설 및 시험","2024-10-15 09:00","2024-10-15 18:00","2024-10-15 09:00","2024-10-15 18:00","연속"]
[373,"충북","충주","신충주감곡#2 T/L","감곡S/S 23kV 장기사용 GIS 대체공사","RTU철거로 인한 제어케이블 SA LID 이설 및 시험","2024-10-16 09:00","2024-10-16 18:00","2024-10-16 09:00","2024-10-16 18:00","연속"]
[374,"충북","충주","감곡가남#2 T/L","감곡S/S 23kV 장기사용 GIS 대체공사","RTU철거로 인한 제어케이블 SA LID 이설 및 시험","2024-10-02 09:00","2024-10-02 18:00","취소","취소","연속"]
[375,"충북","충주","감곡S/S #1 BUS","'24-25년 충주전력지사 변전정비티 총액공사[PT 집합반 대체]","'24-25년 충주전력지사 변전정비티 총액공사[PT 집합반 대체]","2024-10-01 09:00","2024-10-01 18:00","2024-10-01 09:00","2024-10-01 18:00","연속"]
[376,"충북","충주","단양영월CC#1 T/L","'24-25년 충주전력지사 변전정비 총액공사","'24-25년 충주전력지사 변전정비 총액공사[단양영월#1T/L PNL 대체]","2024-10-23 09:00","2024-10-29 18:00","2024-10-23 09:00","2024-10-29 18:00","연속"]
[377,"충북","충주","충주충주HP#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 고정형 폴리머점퍼지지애자 설치","2024-10-30 07:00","2024-10-31 18:00","2024-10-30 07:00","2024-10-31 18:00","매일"]
[378,"충북","충주","충주충주HP#1 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 고정형 폴리머점퍼지지애자 설치","2024-10-28 07:00","2024-10-29 18:00","2024-10-28 07:00","2024-10-29 18:00","매일"]
[379,"대전세종충남","대전","신옥천남대전#4 T/L","154kV 신옥천-남대전삼사 T/L 지장수목 허가벌채","154kV 신옥천-남대전삼사 T/L 지장수목 허가벌채","2024-10-10 07:00","2024-10-11 12:00","2024-10-10 07:00","2024-10-11 12:00","매일"]
[380,"대전세종충남","대전","신옥천남대전#3 T/L","154kV 신옥천-남대전삼사 T/L 지장수목 허가벌채","154kV 신옥천-남대전삼사 T/L 지장수목 허가벌채","2024-10-11 12:00","2024-10-11 18:00","2024-10-11 12:00","2024-10-11 18:00","연속"]
[381,"대전세종충남","대전","신옥천남대전#1 T/L","154kV 신옥천-남대전 T/L 지장수목 허가벌채","154kV 신옥천-남대전 T/L 지장수목 허가벌채","2024-10-07 07:00","2024-10-08 12:00","2024-10-07 07:00","2024-10-08 12:00","매일"]
[382,"대전세종충남","대전","신옥천남대전#2 T/L","154kV 신옥천-남대전 T/L 지장수목 허가벌채","154kV 신옥천-남대전 T/L 지장수목 허가벌채","2024-10-08 12:00","2024-10-08 18:00","2024-10-08 12:00","2024-10-08 18:00","연속"]
[383,"대전세종충남","대전","논산은진#2 T/L","[즉시가압O]논산S/S 154kV 논산-은진#2T/L GIS 보통점검","[즉시가압O]논산S/S 154kV 논산-은진#2T/L GIS 보통점검","2024-10-23 09:00","2024-10-23 18:00","2024-10-23 09:00","2024-10-23 18:00","연속"]
[384,"대전세종충남","대전","논산은진#1 T/L","[즉시가압O]논산S/S 154kV 논산-은진#1T/L GIS 보통점검","[즉시가압O]논산S/S 154kV 논산-은진#1T/L GIS 보통점검","2024-10-22 09:00","2024-10-22 18:00","2024-10-22 09:00","2024-10-22 18:00","연속"]
[385,"대전세종충남","대전","부여논산#1 T/L","[송전][즉시가압O]2023년 가공송전 순시점검 위탁공사","[송전][즉시가압O]2023년 가공송전 순시점검 위탁공사 지장수목 벌채작업","2024-10-10 07:00","2024-10-10 11:00","2024-10-10 07:00","2024-10-10 11:00","연속"]
[386,"대전세종충남","대전","신옥천서대전 T/L","[송전][즉시가압O]2023년 가공송전 순시점검 위탁공사","[송전][즉시가압O]2023년 가공송전 순시점검 위탁공사 지장수목 벌채작업","2024-10-29 08:00","2024-10-30 18:00","2024-10-29 08:00","2024-10-30 18:00","매일"]
[387,"대전세종충남","대전","신계룡두마#1 T/L","[송전][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","2024-10-14 07:00","2024-10-22 18:00","취소","취소","매일"]
[388,"대전세종충남","대전","신계룡은진#1 T/L","[송전][즉시가압]345kV신옥천-청양등8개T/L추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV신옥천-청양등8개T/L추락방지설치공사","2024-10-16 07:00","2024-11-06 18:00","취소","취소","매일"]
[389,"대전세종충남","대전","남대전신흥#2 T/L","[송전] 154kV 대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2024-10-14 09:00","2024-10-17 18:00","취소","취소","연속"]
[390,"대전세종충남","대전","남대전신흥#3 T/L","[송전] 154kV 대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2024-10-21 09:00","2024-10-24 18:00","취소","취소","연속"]
[391,"대전세종충남","대전","신옥천용운#2 T/L","154kV 신옥천-용운 T/L 지장수목 전지 및 벌채","154kV 신옥천-용운 T/L 지장수목 전지 및 벌채","2024-10-16 07:00","2024-10-16 14:00","2024-10-16 07:00","2024-10-16 14:00","연속"]
[392,"대전세종충남","대전","신옥천용운#1 T/L","154kV 신옥천-용운 T/L 지장수목 전지 및 벌채","154kV 신옥천-용운 T/L 지장수목 전지 및 벌채","2024-10-16 14:00","2024-10-16 18:00","2024-10-16 14:00","2024-10-16 18:00","연속"]
[393,"대전세종충남","대전","신옥천유천 T/L","[송전][즉시가압O]2023년 가공송전 순시점검 위탁공사","[송전][주말작업제외][즉시가압O]2023년 가공송전 순시점검 위탁공사 지장수목 벌채작업","2024-10-31 08:00","2024-11-06 18:00","2024-10-31 08:00","2024-11-06 18:00","매일"]
[394,"대전세종충남","대전","추부S/S #2 BUS","추부S/S 154kV #3M.Tr 증설공사","- M.Tr 무부하 가압","2024-10-21 18:00","2024-10-22 09:00","2024-10-21 18:00","2024-10-22 09:00","매일"]
[395,"대전세종충남","대전","추부S/S CB 6100","추부S/S 154kV #3M.Tr 증설공사(무부하)","- M.Tr 무부하 가압","2024-10-21 16:00","2024-10-22 09:00","2024-10-21 16:00","2024-10-22 09:00","연속"]
[396,"대전세종충남","대전","추부S/S CB 6100","추부S/S 154kV #3M.Tr 증설공사","- 154kV 모선보호반 연동시험","2024-10-17 09:00","2024-10-17 18:00","2024-10-17 09:00","2024-10-17 18:00","연속"]
[397,"대전세종충남","대전","추부S/S #1 BUS","추부S/S 154kV #3M.Tr 증설공사","- 신규 23kV GIS 상체크 및 M.Tr 최초가압","2024-10-21 16:00","2024-10-21 18:00","2024-10-21 16:00","2024-10-21 18:00","연속"]
[398,"대전세종충남","서산","석문당진화력#1 T/L","서산P/O 효성제 170kV GIS 베어링 교체공사","(9월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력#1T/L 617 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#1T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#1T/L 617 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#1T/L 617CB 보통점검","2024-10-14 09:30","2024-10-15 18:00","2024-10-14 09:30","2024-10-15 18:00","매일"]
[399,"대전세종충남","서산","석문당진화력#2 T/L","서산P/O 효성제 170kV GIS 베어링 교체공사","(9월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#2T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#2T/L 687 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 보통점검","2024-10-16 09:30","2024-10-17 18:00","2024-10-16 09:30","2024-10-17 18:00","매일"]
[400,"대전세종충남","서산","서산대산#4 T/L","대산S/S 154kV 대호호수상태양광T/L 무부하가압 및 최초가압","(즉시가압가능)대산S/S 154kV 대호호수상태양광T/L 무부하가압 및 최초가압","2024-10-18 10:00","2024-10-19 10:00","2024-10-18 10:00","2024-10-19 10:00","연속"]
[401,"대전세종충남","서산","서산대산 T/L","'24~'25년 서산전력지사 송전협력회사 공사","154kV 서산-대산T/L 항공구 설치공사 No.9~10, 11~12(2경간) *즉시가압가능(20분이내) *9월 휴전 승인시 취소 요청 *154kV 서산-태안#1T/L 병가선로, 154kV 서산-태안#1T/L 휴전 미승인시 휴전 취소 요청","2024-10-05 05:00","2024-10-06 09:00","취소","취소","매일"]
[402,"대전세종충남","서산","서산대산#3 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.65~76) , 즉시가압(20분 이내) 가능","2024-10-07 08:00","2024-10-07 18:00","2024-10-07 08:00","2024-10-07 18:00","연속"]
[403,"대전세종충남","서산","신당진서산#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.54~60) , 즉시가압(20분 이내) 가능","2024-10-08 08:00","2024-10-08 18:00","2024-10-08 08:00","2024-10-08 18:00","연속"]
[404,"대전세종충남","서산","서산태안#1 T/L","'24~'25년 서산전력지사 송전협력회사 공사","154kV 서산-대산T/L 항공구 설치공사 No.9~10, 11~12(2경간) *즉시가압가능(20분이내) *9월 휴전 승인시 취소 요청 *154kV 서산-대산T/L 병가선로, 154kV 서산-대산T/L 휴전 미승인시 휴전 취소 요청","2024-10-05 05:00","2024-10-06 09:00","취소","취소","매일"]
[405,"대전세종충남","서산","서산홍성 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.1~135 등 83기) , 즉시가압(20분 이내) 가능, 주말작업 없음","2024-10-10 09:00","2024-10-18 18:00","취소","취소","매일"]
[406,"대전세종충남","서산","합덕송악#1 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","154kV 당진-송악#2T/L 항공장애표시구 설치공사 No.34~35 (1경간) *즉시가압가능(20분이내) *9월 휴전 승인시 취소 요청 *154kV 당진-송악#2T/L 병가선로, 154kV 당진-송악#2T/L 휴전 미승인시 휴전 취소 요청","2024-10-12 08:00","2024-10-13 18:00","2024-10-12 08:00","2024-10-13 18:00","매일"]
[407,"대전세종충남","서산","당진송악#2 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","154kV 당진-송악#2T/L 항공장애표시구 설치공사 No.34~35 (1경간) *즉시가압가능(20분이내) *9월 휴전 승인시 취소 요청 *154kV 합덕-송악#1T/L 병가선로, 154kV 합덕-송악#1T/L 휴전 미승인시 휴전 취소 요청","2024-10-12 08:00","2024-10-13 18:00","2024-10-12 08:00","2024-10-13 18:00","매일"]
[408,"대전세종충남","서산","신당진당진#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.1~5,14~35) , 즉시가압(20분 이내) 가능, 휴일작업 없음","2024-10-01 08:00","2024-10-04 18:00","취소","취소","매일"]
[409,"대전세종충남","서산","신당진당진#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.1~5,14~35) , 즉시가압(20분 이내) 가능","2024-10-30 08:00","2024-10-31 18:00","취소","취소","매일"]
[410,"대전세종충남","서산","태안태안화력#1 T/L","24년 서산P/O 변전협력회사 총액공사","태안S/S 154kV 태안-태안화력#1T/L 687GIS 보통점검","2024-10-10 09:30","2024-10-10 18:00","2024-10-10 09:30","2024-10-10 18:00","연속"]
[411,"대전세종충남","서산","서산태안#2 T/L","태안S/S 154kV 차단기 조작시험","태안S/S 서산-태안#2T/L 637 CB 조작시험","2024-10-22 10:00","2024-10-22 14:00","취소","취소","연속"]
[412,"대전세종충남","서산","태안태안화력#2 T/L","24년 서산P/O 변전협력회사 총액공사","태안S/S 154kV 태안-태안화력#2T/L 657GIS 보통점검","2024-10-11 09:30","2024-10-11 18:00","2024-10-11 09:30","2024-10-11 18:00","연속"]
[413,"대전세종충남","서산","아산합덕#2 T/L","24년 서산P/O 154kV GIS 정밀점검공사","(즉시가압 불가) 합덕S/S 154kV 아산-합덕#2T/L 617 GIS 정밀점검공사","2024-10-14 09:30","2024-10-16 18:00","취소","취소","연속"]
[414,"대전세종충남","서산","아산합덕#1 T/L","24년 서산P/O 154kV GIS 정밀점검공사","(즉시가압 불가) 합덕S/S 154kV 아산-합덕#1T/L 627 GIS 정밀점검공사","2024-10-07 09:30","2024-10-09 18:00","취소","취소","연속"]
[415,"대전세종충남","서산","해미홍성 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.1,13~64) , 즉시가압(20분 이내) 가능, 주말작업 없음","2024-10-21 08:00","2024-10-29 18:00","2024-10-21 08:00","2024-10-29 18:00","매일"]
[416,"대전세종충남","세종","신풍공주#2 T/L","154kV 신풍-공주#2T/L 철구추락방지 설치공사","154kV 신풍-공주#2T/L 철구추락방지 설치공사","2024-10-07 07:00","2024-10-08 18:00","취소","취소","매일"]
[417,"대전세종충남","세종","덕진공주#1 T/L","154kV덕진-공주T/L 지장수목 허가벌채","154kV덕진-공주T/L 지장수목 허가벌채","2024-10-17 14:00","2024-10-17 18:00","2024-10-17 14:00","2024-10-17 18:00","연속"]
[418,"대전세종충남","세종","덕진공주#2 T/L","154kV덕진-공주T/L 지장수목 허가벌채","154kV덕진-공주T/L 지장수목 허가벌채","2024-10-17 07:00","2024-10-17 14:00","2024-10-17 07:00","2024-10-17 14:00","연속"]
[419,"대전세종충남","세종","부강신탄진 T/L","154kV 부강-신탄진T/L 피뢰기 설치공사","154kV 부강-신탄진T/L 피뢰기 설치공사 - 대상 : No.1~62(62기) - 58~61호는 수직배열이므로 신탄진-대청T/L 양회선 휴전 필요 - 주말 및 공휴일은 작업 미시행","2024-10-07 07:00","2024-10-15 18:00","2024-10-07 07:00","2024-10-15 18:00","매일"]
[420,"대전세종충남","세종","세종서세종#1 T/L","[변전]'24년 세종P/O 154kV GIS 정밀점검공사","○154kV GIS 정밀점검공사 -즉시가압 불가","2024-10-14 09:00","2024-10-16 18:00","취소","취소","연속"]
[421,"대전세종충남","세종","세종서세종#2 T/L","[변전]'24년 세종P/O 154kV GIS 정밀점검공사","○154kV GIS 정밀점검공사 -즉시가압 불가","2024-10-21 09:00","2024-10-23 18:00","취소","취소","연속"]
[422,"대전세종충남","세종","조치원월산 T/L","154kV 조치원-월산T/L 피뢰기 설치공사","154kV 조치원-월산T/L 피뢰기 설치공사 - 대상 : No.1~35(35기) - 2~4호는 수평배열이므로 서세종-조치원T/L과 양회선 휴전 필요","2024-10-28 07:00","2024-10-31 18:00","2024-10-28 07:00","2024-10-31 18:00","매일"]
[423,"대전세종충남","세종","천안전의#1 T/L","154kV 천안-전의T/L 지장수목 제거","154kV 천안-전의T/L 지장수목 제거","2024-10-21 07:00","2024-10-22 18:00","2024-10-21 07:00","2024-10-22 18:00","매일"]
[424,"대전세종충남","세종","천안전의#2 T/L","154kV 천안-전의T/L 지장수목 제거","154kV 천안-전의T/L 지장수목 제거","2024-10-23 09:00","2024-10-24 18:00","2024-10-23 09:00","2024-10-24 18:00","매일"]
[425,"대전세종충남","세종","서세종조치원 T/L","[안전상 휴전요청] 154kV 조치원-월산T/L 피뢰기 설치공사","154kV 조치원-월산T/L 피뢰기 설치공사 - 대상 : No.1~35(35기) - 154kV 조치원-월산T/L No. 2~4호는 수평배열이므로 서세종-조치원T/L과 양회선 휴전 필요(즉시가압 가능)","2024-10-28 07:00","2024-10-29 18:00","2024-10-28 07:00","2024-10-29 18:00","매일"]
[426,"대전세종충남","직할","동대전신탄진#1 T/L","154kV 동대전-신탄진T/L 용량증대 선종교체, 안전이격 확보공사","154kV 동대전-신탄진T/L 용량증대 선종교체, 안전이격 확보공사 -지지물:4기교체(No.10,12,15,17) -전력선:HSTACIR/AW240㎟ 4km교체 (No.1~6, 9~12, 14~18, 27~31) #1,#2 양회선 동시휴전 신청","2024-10-21 08:00","2024-12-06 18:00","2024-10-21 08:00","2024-12-06 18:00","연속"]
[427,"대전세종충남","직할","동대전신탄진#2 T/L","154kV 동대전-신탄진T/L 용량증대 선종교체, 안전이격 확보공사","154kV 동대전-신탄진T/L 용량증대 선종교체, 안전이격 확보공사 -지지물:4기교체(No.10,12,15,17) -전력선:HSTACIR/AW240㎟ 4km교체 (No.1~6, 9~12, 14~18, 27~31) #1,#2 양회선 동시휴전 신청","2024-10-21 08:00","2024-12-06 18:00","2024-10-21 08:00","2024-12-06 18:00","연속"]
[428,"대전세종충남","직할","둔곡송강#2 T/L","154kV 둔곡-송강T/L 지장수목 전지 및 벌채","154kV 둔곡-송강T/L 지장수목 전지 및 벌채","2024-10-22 07:00","2024-10-23 12:00","취소","취소","매일"]
[429,"대전세종충남","직할","둔곡송강#1 T/L","154kV 둔곡-송강T/L 지장수목 전지 및 벌채","154kV 둔곡-송강T/L 지장수목 전지 및 벌채","2024-10-23 12:00","2024-10-23 18:00","취소","취소","연속"]
[430,"대전세종충남","직할","신탄진대청HP T/L","154kV 신탄진S/S 미래화공사","옥외철구 → 신설GIS 인출변경","2024-10-17 09:00","2024-10-18 18:00","취소","취소","연속"]
[431,"대전세종충남","직할","신탄진S/S CB 6100","154kV 신탄진S/S 미래화공사(옥외철구BUSTIE운휴)","기설 옥외철구 BUSTIE 운휴","2024-10-14 09:00","2025-10-14 18:00","취소","취소","연속"]
[432,"대전세종충남","직할","부강신탄진 T/L","154kV 동대전-신탄진T/L 용량증대 선종교체, 안전이격 확보공사","154kV 동대전-신탄진T/L 용량증대 선종교체, 안전이격 확보공사 -지지물:4기교체(No.10,12,15,17) -전력선:HSTACIR/AW240㎟ 4km교체 (No.1~6, 9~12, 14~18, 27~31) #1,#2 양회선 동시휴전 신청 No.27 분기철탑 작업시 부강-신탄진T/L 휴전 必","2024-10-21 08:00","2024-10-25 18:00","2024-10-21 08:00","2024-10-25 18:00","연속"]
[433,"대전세종충남","직할","부강신탄진 T/L","154kV 신탄진S/S 미래화공사","옥외철구 → 신설GIS 인출변경","2024-10-16 09:00","2024-10-16 18:00","취소","취소","연속"]
[434,"대전세종충남","천안","둔포직산#2 T/L","둔포S/S 154kV 직산-둔포#1, 2T/L CB 개폐타임측정","(즉시가압가능)둔포S/S 154kV 직산-둔포#1, 2T/L CB 개폐타임측정","2024-10-31 14:00","2024-10-31 18:00","2024-10-31 14:00","2024-10-31 18:00","연속"]
[435,"대전세종충남","천안","둔포직산#1 T/L","둔포S/S 154kV 직산-둔포#1, 2T/L CB 개폐타임측정","(즉시가압가능)둔포S/S 154kV 직산-둔포#1, 2T/L CB 개폐타임측정","2024-10-31 09:00","2024-10-31 14:00","2024-10-31 09:00","2024-10-31 14:00","연속"]
[436,"대전세종충남","천안","둔포추팔#2 T/L","(9월 취소시)둔포S/S 154kV 둔포-추팔#2T/L GIS 보통점검","(9월 취소시)둔포S/S 154kV 둔포-추팔#2T/L GIS 보통점검","2024-10-04 09:00","2024-10-04 18:00","취소","취소","연속"]
[437,"대전세종충남","천안","장재불당#2 T/L","불당S/S 154kV 장재-불당#1, 2T/L CB 개폐타임측정","(9월취소시)(즉시가압가능)불당S/S 154kV 장재-불당#1, 2T/L CB 개폐타임측정","2024-10-04 14:00","2024-10-04 18:00","취소","취소","연속"]
[438,"대전세종충남","천안","장재불당#1 T/L","불당S/S 154kV 장재-불당#1, 2T/L CB 개폐타임측정","(9월취소시)(즉시가압가능)불당S/S 154kV 장재-불당#1, 2T/L CB 개폐타임측정","2024-10-04 09:00","2024-10-04 14:00","취소","취소","연속"]
[439,"대전세종충남","천안","서천안탕정#2 T/L","154kV 서천안-탕정T/L 추락방지장치 설치공사","[즉시가압가능, 주말작업없음]154kV 서천안-탕정T/L No. 3 ~ 23 추락방지장치 설치 [병행작업] 조류착지방지장치 설치","2024-10-17 07:00","2024-10-18 18:00","2024-10-17 07:00","2024-10-18 18:00","매일"]
[440,"대전세종충남","천안","신온양S/S SEC CB 67680","신온양S/S 154kV #67-#68 SEC GIS 보통점검","신온양S/S 154kV #67-#68 SEC GIS 보통점검","2024-10-11 09:00","2024-10-11 18:00","2024-10-11 09:00","2024-10-11 18:00","연속"]
[441,"대전세종충남","천안","신온양S/S SEC CB 62630","신온양S/S 154kV #62-#63 SEC GIS 보통점검","신온양S/S 154kV #62-#63 SEC GIS 보통점검","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[442,"대전세종충남","천안","신온양S/S CB 6200","신온양S/S 154kV 6200 BUS TIE GIS 보통점검","신온양S/S 154kV 6200 BUS TIE GIS 보통점검","2024-10-15 09:00","2024-10-15 18:00","2024-10-15 09:00","2024-10-15 18:00","연속"]
[443,"대전세종충남","천안","신온양석곡#1 T/L","신온양S/S 154kV 신온양-석곡#1T/L 세니온제 보호반 성능개선","(9월취소시)(즉시가압불가)신온양S/S 154kV 신온양-석곡#1T/L 세니온제 보호반 성능개선","2024-10-22 09:00","2024-10-22 18:00","취소","취소","연속"]
[444,"대전세종충남","천안","신온양석곡#2 T/L","신온양S/S 154kV 신온양-석곡#2T/L 세니온제 보호반 성능개선","(9월취소시)(즉시가압불가)신온양S/S 154kV 신온양-석곡#2T/L 세니온제 보호반 성능개선","2024-10-23 09:00","2024-10-23 18:00","취소","취소","연속"]
[445,"대전세종충남","천안","아산예산#2 T/L","아산,예산S/S 154kV 아산-예산#2T/L 노후 보호반 대체","(9월취소시)(즉시가압불가)아산,예산S/S 154kV 아산-예산#2T/L 노후 보호반 대체","2024-10-28 09:00","2024-11-01 18:00","취소","취소","연속"]
[446,"대전세종충남","천안","아산온양#1 T/L","항공장애표시구 설치공사","[즉시가압가능]154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 불량애자 교체 No.23 [병행] 피뢰기 설치 1~13, 51~56 [병행] 고정형폴리머 점퍼지지애자 교체 6","2024-10-20 07:00","2024-10-20 17:00","취소","취소","매일"]
[447,"대전세종충남","천안","아산예산#2 T/L","항공장애표시구 설치공사","[즉시가압가능]154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치공사 [주말작업없음]","2024-10-27 07:00","2024-10-27 17:00","취소","취소","연속"]
[448,"대전세종충남","천안","아산인주#2 T/L","아산,인주S/S 154kV 아산-인주#2T/L 노후 보호반 대체","(9월취소시)(즉시가압불가)아산,인주S/S 154kV 아산-인주#2T/L 노후 보호반 대체","2024-10-19 09:00","2024-10-21 18:00","취소","취소","연속"]
[449,"대전세종충남","천안","아산온양#2 T/L","항공장애표시구 설치공사","[즉시가압가능]154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-10-06 07:00","2024-10-06 17:00","취소","취소","연속"]
[450,"대전세종충남","천안","아산온양#1 T/L","항공장애표시구 설치공사","[즉시가압가능]154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-10-27 07:00","2024-10-27 17:00","취소","취소","연속"]
[451,"대전세종충남","천안","아산온양#2 T/L","항공장애표시구 설치공사","[즉시가압가능]154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-10-13 07:00","2024-10-13 17:00","취소","취소","매일"]
[452,"대전세종충남","천안","아산예산#1 T/L","항공장애표시구 설치공사","[즉시가압가능]154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-10-06 07:00","2024-10-06 17:00","취소","취소","연속"]
[453,"대전세종충남","천안","아산예산#1 T/L","아산,예산S/S 154kV 아산-예산#1T/L 노후 보호반 대체","(9월취소시)(즉시가압불가)아산,예산S/S 154kV 아산-예산#1T/L 노후 보호반 대체","2024-10-21 09:00","2024-10-25 18:00","취소","취소","연속"]
[454,"대전세종충남","천안","아산S/S SEC CB 65660","아산S/S 154kV BUS SEC 65-66-0 불량 PD센서 보수","(9월취소시)(즉시가압불가)아산S/S 154kV BUS SEC 65-66-0 불량 PD센서 보수","2024-10-10 09:00","2024-10-11 18:00","취소","취소","연속"]
[455,"대전세종충남","천안","아산S/S CB 6100","아산S/S 154kV BUS TIE 6100 GIS 보통점검","(9월취소시)(즉시가압가능)아산S/S 154kV BUS TIE 6100 GIS 보통점검","2024-10-15 09:00","2024-10-15 18:00","2024-10-15 09:00","2024-10-15 18:00","연속"]
[456,"대전세종충남","천안","아산인주#1 T/L","아산,인주S/S 154kV 아산-인주#1T/L 노후 보호반 대체","(9월취소시)(즉시가압불가)아산,인주S/S 154kV 아산-인주#1T/L 노후 보호반 대체","2024-10-12 09:00","2024-10-14 18:00","취소","취소","연속"]
[457,"대전세종충남","천안","아산합덕#2 T/L","154kV 아산-합덕T/L 추락방지장치 설치공사","[즉시가압가능]154kV 아산-합덕T/L No. 1 ~ 53 추락방지장치 설치 [병가철탑](상단)신서산-아산#2No.74~113,(하단)아산-합덕#2No.13~52 [병행작업] 조류착지방지장치 설치","2024-10-10 07:00","2024-10-16 17:00","취소","취소","매일"]
[458,"대전세종충남","천안","아산S/S SEC CB 60610","아산S/S 154kV BUS SEC 60-61-0 GIS 보통점검","(9월취소시)(즉시가압가능)아산S/S 154kV BUS SEC 60-61-0 GIS 보통점검","2024-10-07 09:00","2024-10-07 18:00","취소","취소","연속"]
[459,"대전세종충남","천안","인주불당#2 T/L","154kV 아산-인주 등 2개 T/L 송전선로 정비공사","1. 구 간 ○ 아산-인주T/L 정비(1.264km) 기28호∼기32호 가선(연긴선, 공중이동) ○ 인주-불당T/L 정비(0.828km) 기3∼기5호 조립,가선(연긴선, 공중이동) ○ 아산-인주T/L 기설32호 철탑보강 2. 지 지 물 ○ 신설 : 설치 2기[가철탑 1기(4C), 산형강 철탑 1기(2C), ○ 철거 : 철거 4기[가철탑","2024-10-05 07:00","2024-10-22 18:00","2024-10-05 07:00","2024-10-22 18:00","연속"]
[460,"대전세종충남","천안","인주불당#1 T/L","154kV 아산-인주 등 2개 T/L 송전선로 정비공사","1. 구 간 ○ 아산-인주T/L 정비(1.264km) 기28호∼기32호 가선(연긴선, 공중이동) ○ 인주-불당T/L 정비(0.828km) 기3∼기5호 조립,가선(연긴선, 공중이동) ○ 아산-인주T/L 기설32호 철탑보강 2. 지 지 물 ○ 신설 : 설치 2기[가철탑 1기(4C), 산형강 철탑 1기(2C), ○ 철거 : 철거 4기[가철탑","2024-10-23 07:00","2024-10-28 18:00","2024-10-23 07:00","2024-10-28 18:00","연속"]
[461,"대전세종충남","천안","아산인주#2 T/L","154kV 아산-인주 등 2개 T/L 송전선로 정비공사","1. 구 간 ○ 아산-인주T/L 정비(1.264km) 기28호∼기32호 가선(연긴선, 공중이동) ○ 인주-불당T/L 정비(0.828km) 기3∼기5호 조립,가선(연긴선, 공중이동) ○ 아산-인주T/L 기설32호 철탑보강 2. 지 지 물 ○ 신설 : 설치 2기[가철탑 1기(4C), 산형강 철탑 1기(2C), ○ 철거 : 철거 4기[가철탑","2024-10-17 07:00","2024-10-28 18:00","2024-10-17 07:00","2024-10-28 18:00","연속"]
[462,"대전세종충남","천안","인주불당#1 T/L","인주S/S 154kV 인주-불당#1T/L CB 개폐타임측정","(9월취소시)(즉시가압가능)인주S/S 154kV 인주-불당#1T/L CB 개폐타임측정","2024-10-25 09:00","2024-10-25 18:00","취소","취소","연속"]
[463,"대전세종충남","천안","아산인주#1 T/L","154kV 아산-인주 등 2개 T/L 송전선로 정비공사","1. 구 간 ○ 아산-인주T/L 정비(1.264km) 기28호∼기32호 가선(연긴선, 공중이동) ○ 인주-불당T/L 정비(0.828km) 기3∼기5호 조립,가선(연긴선, 공중이동) ○ 아산-인주T/L 기설32호 철탑보강 2. 지 지 물 ○ 신설 : 설치 2기[가철탑 1기(4C), 산형강 철탑 1기(2C), ○ 철거 : 철거 4기[가철탑","2024-10-10 07:00","2024-10-16 18:00","2024-10-10 07:00","2024-10-16 18:00","연속"]
[464,"대전세종충남","천안","인주불당#2 T/L","인주S/S 154kV 인주-불당#2T/L CB 개폐타임측정","(9월취소시)(즉시가압가능)인주S/S 154kV 인주-불당#2T/L CB 개폐타임측정","2024-10-16 09:00","2024-10-16 18:00","취소","취소","연속"]
[465,"대전세종충남","천안","장재천안#1 T/L","장재,천안S/S 154kV 장재-천안#1T/L 노후 보호반 대체","(9월취소시)(즉시가압불가)장재,천안S/S 154kV 장재-천안#1T/L 노후 보호반 대체","2024-10-07 09:00","2024-10-10 18:00","2024-10-07 09:00","2024-10-10 18:00","연속"]
[466,"대전세종충남","천안","장재천안#2 T/L","장재,천안S/S 154kV 장재-천안#2T/L 노후 보호반 대체","(9월취소시)(즉시가압불가)장재,천안S/S 154kV 장재-천안#2T/L 노후 보호반 대체","2024-10-14 09:00","2024-10-16 18:00","2024-10-14 09:00","2024-10-16 18:00","연속"]
[467,"대전세종충남","천안","장재천안#2 T/L","154kV 장재-천안T/L 추락방지장치 설치공사","[즉시가압가능,주말작업없음]154kV 장재-천안T/L No. 4 ~ 14 추락방지장치 설치 [병가철탑](상단)풍세-장재#1No.18~23,(하단)장재-천안#2No.4~9 [병행작업] 조류착지방지장치 설치","2024-10-15 07:00","2024-10-15 18:00","취소","취소","매일"]
[468,"대전세종충남","천안","신탕정탕정#2 T/L","탕정S/S 154kV 신탕정-탕정#1, 2T/L CB 개폐타임측정","(9월취소시)(즉시가압가능)탕정S/S 154kV 신탕정-탕정#1, 2T/L CB 개폐타임측정","2024-10-11 14:00","2024-10-11 18:00","취소","취소","연속"]
[469,"대전세종충남","천안","신탕정탕정#1 T/L","탕정S/S 154kV 신탕정-탕정#1, 2T/L CB 개폐타임측정","(9월취소시)(즉시가압가능)탕정S/S 154kV 신탕정-탕정#1, 2T/L CB 개폐타임측정","2024-10-11 09:00","2024-10-11 14:00","취소","취소","연속"]
[470,"대전세종충남","천안","온양풍세#1 T/L","항공장애표시구 설치공사","[즉시가압가능]154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-10-20 07:00","2024-10-20 17:00","취소","취소","연속"]
[471,"대전세종충남","천안","풍세장재#1 T/L","154kV 풍세-장재T/L 추락방지장치 설치공사","[즉시가압가능]154kV 풍세-장재T/L No. 18 ~ 23 추락방지장치 설치 [병가철탑](상단)풍세-장재#1No.18~23,(하단)장재-천안#2No.4~9 [병행작업] 조류착지방지장치 설치","2024-10-15 07:00","2024-10-15 18:00","취소","취소","매일"]
[472,"대전세종충남","천안","온양풍세#2 T/L","항공장애표시구 설치공사","[즉시가압가능]154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-10-13 07:00","2024-10-13 17:00","취소","취소","연속"]
[473,"대전세종충남","청양","관창보령TP T/L","보령T/P 154kV LA,PT GIS 내장화공사(관창-보령화력)","보령T/P 154kV LA,PT GIS 내장화공사(관창-보령화력) - 즉시가압 불가","2024-10-28 09:00","2024-11-05 18:00","2024-10-28 09:00","2024-11-05 18:00","연속"]
[474,"대전세종충남","청양","관창보령TP T/L","청양P/O 변전협력 총액공사(보령 관보)","청양P/O 변전협력 총액공사(보령 관보) - 154kV 관창-보령화력 T/L - 보령T/P GIS 보통점검 - 즉시가압 가능","2024-10-10 09:00","2024-10-10 18:00","2024-10-10 09:00","2024-10-10 18:00","연속"]
[475,"대전세종충남","청양","옥산부여#2 T/L","[송전] 154KV 옥산부여T/L 수평추락방지장치 설치","No.1~65 수평추락방지장치 설치","2024-10-14 09:00","2024-10-25 18:00","2024-10-14 09:00","2024-10-25 18:00","매일"]
[476,"대전세종충남","청양","옥산부여#1 T/L","[송전] 154KV 옥산부여T/L 수평추락방지장치 설치","No.1~65 수평추락방지장치 설치","2024-10-28 09:00","2024-11-07 18:00","2024-10-28 09:00","2024-11-07 18:00","매일"]
[477,"대전세종충남","청양","청양신풍#2 T/L","청양P/O 변전협력 총액공사(청양-신풍#2)","청양P/O 변전협력 총액공사(청양-신풍#2) - 보호반 대체 (주작업) 3일 - 신풍S/S 154kV GIS 보통점검(병행) - 청양S/S 154kV GIS 조작시험(병행) - 즉시가압 불가","2024-10-28 10:00","2024-10-30 18:00","2024-10-28 10:00","2024-10-30 18:00","연속"]
[478,"대전세종충남","청양","청양신풍#1 T/L","청양P/O 변전협력 총액공사(청양-신풍#1)","청양P/O 변전협력 총액공사(청양-신풍#1) - 보호반 대체 (주작업) 3일 - 신풍S/S 154kV GIS 보통점검(병행) - 청양S/S 154kV GIS 조작시험(병행) - 즉시가압 불가","2024-10-14 10:00","2024-10-16 18:00","2024-10-14 10:00","2024-10-16 18:00","연속"]
[479,"대전세종충남","청양","옥산부여#1 T/L","(송전취소시)청양P/O 전문 발주공사(옥부#1 정밀)","(송전취소시)청양P/O 변전전문업체 발주공사 - 옥산S/S 옥산-부여#1T/L GIS 정밀점검 - 즉시가압 불가","2024-10-28 10:00","2024-10-30 18:00","취소","취소","연속"]
[480,"대전세종충남","청양","신서천옥산#2 T/L","(송전 옥부 취소시)청양P/O 전문 공사(옥산 옥서2 정밀)","(송전 옥장 취소시) 청양P/O 변전전문업체 발주공사 - 옥산S/S 옥산-서천#2T/L GIS 627 정밀점검 - 즉시가압 불가","2024-10-16 14:00","2024-10-18 18:00","취소","취소","연속"]
[481,"대전세종충남","청양","옥산장항#2 T/L","(송전 옥부 취소시)청양P/O 전문 공사(옥산 옥장#2 정밀)","(송전 옥부 취소시)청양P/O 변전전문업체 발주공사 - 옥산S/S 옥산-장항#2T/L GIS 정밀점검 - 즉시가압 불가","2024-10-22 10:00","2024-10-24 18:00","취소","취소","연속"]
[482,"대전세종충남","청양","옥산부여#2 T/L","(송전취소시)청양P/O 전문 발주공사(옥부#2 정밀)","(송전취소시)청양P/O 변전전문업체 발주공사 - 옥산S/S 옥산-부여#2T/L GIS 정밀점검 - 즉시가압 불가","2024-10-14 10:00","2024-10-16 18:00","취소","취소","연속"]
[483,"전북","군산","동군산군산CC#1 T/L","군산PO 154kV 이상 차단기 점검공사","군산PO 154kV 이상 차단기 점검공사","2024-10-29 09:00","2024-10-29 18:00","2024-10-29 09:00","2024-10-29 18:00","연속"]
[484,"전북","군산","동군산군산CC#2 T/L","군산PO 154kV 이상 차단기 점검공사","군산PO 154kV 이상 차단기 점검공사","2024-10-30 09:00","2024-10-30 18:00","2024-10-30 09:00","2024-10-30 18:00","연속"]
[485,"전북","군산","군산S/S SEC CB 66670","군산PO 154kV 이상 차단기 점검공사","군산PO 154kV 이상 차단기 점검공사","2024-10-30 09:00","2024-10-30 18:00","2024-10-30 09:00","2024-10-30 18:00","연속"]
[486,"전북","군산","군산S/S CB 6100","군산PO 154kV이상 차단기 점검공사","군산PO 154kV이상 차단기 점검공사","2024-10-08 09:00","2024-10-08 14:00","2024-10-08 09:00","2024-10-08 14:00","연속"]
[487,"전북","군산","군산S/S #61 BUS","군산S/S 170kV GIS 대체공사(6차)","- 군산S/S 군산-영등#2T/L 대체","2024-10-04 17:00","2024-10-04 18:00","2024-10-04 17:00","2024-10-04 18:00","연속"]
[488,"전북","군산","군산서군산#1 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2024-10-14 09:00","2024-10-15 18:00","취소","취소","연속"]
[489,"전북","군산","군산이리#1 T/L","군산PO 154kV이상 차단기 점검공사","군산PO 154kV이상 차단기 점검공사","2024-10-08 14:00","2024-10-08 18:00","2024-10-08 14:00","2024-10-08 18:00","연속"]
[490,"전북","군산","군산S/S SEC CB 61620","군산PO 154kV 이상 차단기 점검공사","군산PO 154kV 이상 차단기 점검공사","2024-10-31 09:00","2024-10-31 14:00","2024-10-31 09:00","2024-10-31 14:00","연속"]
[491,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2024-10-16 09:00","2024-10-17 18:00","취소","취소","연속"]
[492,"전북","군산","함열낭산#2 T/L","154kV 낭산-함열T/L 초기점검","□ 공사개요 □ 초기점검 : 철탑 12기 □ 철탑 및 전선 접속개소 점검","2024-10-02 07:00","2024-10-04 18:00","2024-10-02 07:00","2024-10-04 18:00","매일"]
[493,"전북","군산","새만금비응#2 T/L","군산PO 154kV이상 차단기 점검공사","군산PO 154kV이상 차단기 점검공사","2024-10-17 09:00","2024-10-17 18:00","2024-10-17 09:00","2024-10-17 18:00","연속"]
[494,"전북","군산","새만금소룡#1 T/L","군산PO 154kV이상 차단기 점검공사","군산PO 154kV이상 차단기 점검공사","2024-10-18 09:00","2024-10-18 18:00","2024-10-18 09:00","2024-10-18 18:00","연속"]
[495,"전북","군산","영등팔봉#2 T/L","154kV 영등-팔봉T/L 일부 지중화공사","1) 선종 및 길이 : XLPE 2000㎟, 1.4km 2) 케이블 접속구간 ○ 종단접속 : 4개소【EBA 2개소, EBG 2개소】 ○ 중간접속 : 4개소【PMIJ 4개소】","2024-10-14 09:00","2024-10-23 18:00","취소","취소","연속"]
[496,"전북","군산","영등팔봉#1 T/L","154kV 영등-팔봉T/L 일부 지중화공사","1) 선종 및 길이 : XLPE 2000㎟, 1.4km 2) 케이블 접속구간 ○ 종단접속 : 4개소【EBA 2개소, EBG 2개소】 ○ 중간접속 : 4개소【PMIJ 4개소】","2024-10-24 09:00","2024-11-02 18:00","취소","취소","연속"]
[497,"전북","군산","팔봉왕궁#2 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2024-10-21 09:00","2024-10-25 18:00","취소","취소","연속"]
[498,"전북","군산","팔봉왕궁#1 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2024-10-14 09:00","2024-10-18 18:00","취소","취소","연속"]
[499,"전북","군산","은진함열#1 T/L","군산P/O 노후배전반 대체공사","은진-함열#1T/L PNL 대체","2024-10-23 09:00","2024-10-25 18:00","취소","취소","연속"]
[500,"전북","군산","은진함열#2 T/L","군산P/O 노후배전반 대체공사","은진-함열#2T/L PNL대체","2024-10-28 09:00","2024-10-30 18:00","취소","취소","연속"]
[501,"전북","군산","동군산장항#1 T/L","효성제 170kv gis 부품 교체 시행","효성제 170kv gis 부품 교체 시행(즉시가압 불가)","2024-10-21 09:00","2024-10-23 18:00","2024-10-21 09:00","2024-10-23 18:00","연속"]
[502,"전북","김제","남전주임실#1 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","신김제-동전주T/L 교차구간 안전이격거리 확보차 양회선 휴전","2024-10-07 08:00","2024-10-11 17:00","2024-10-15 08:00","2024-10-19 17:00","매일"]
[503,"전북","김제","남전주임실#2 T/L","154kV 신김제-동전주 등 2개T/L 지장철탑 이설공사","신김제-동전주T/L 교차구간 안전이격거리 확보차 양회선 휴전","2024-10-07 08:00","2024-10-11 17:00","2024-10-15 08:00","2024-10-19 17:00","매일"]
[504,"전북","김제","김제부안#1 T/L","부안S/S 김제-부안#1T/L 차단기 정밀점검(10.14~15, 연속)","부안S/S 김제-부안#1T/L 차단기 정밀점검(10.14~15, 연속)","2024-10-07 09:00","2024-10-08 18:00","2024-10-07 09:00","2024-10-08 18:00","연속"]
[505,"전북","김제","김제부안#2 T/L","부안S/S 김제-부안#2T/L 차단기 정밀점검(10.16~17, 연속)","부안S/S 김제-부안#2T/L 차단기 정밀점검(10.16~17, 연속)","2024-10-10 09:00","2024-10-11 18:00","2024-10-10 09:00","2024-10-11 18:00","연속"]
[506,"전북","김제","정주동부안#1 T/L","부안S/S 정주-부안#1T/L GIS 정밀점검(10.23~24, 연속)","부안S/S 정주-부안#1T/L 차단기,단로기 정밀점검(10.23~24, 연속)","2024-10-23 08:00","2024-10-24 18:00","2024-10-23 08:00","2024-10-24 18:00","연속"]
[507,"전북","김제","정주동부안#2 T/L","부안S/S 정주-부안#2T/L GIS 정밀점검(10.28~30, 연속)","부안S/S 정주-부안#2T/L 차단기,단로기 정밀점검(10.28~30, 연속)","2024-10-28 08:00","2024-10-30 18:00","2024-10-28 08:00","2024-10-30 18:00","연속"]
[508,"전북","김제","신김제S/S #1 EM.Tr CB","신김제FR-ESS 정밀점검","신김제FR-ESS 정밀점검","2024-10-21 09:00","2024-10-25 18:00","2024-10-21 09:00","2024-10-25 18:00","연속"]
[509,"전북","김제","신김제동전주#1 T/L","154kV 완산분기T/L 건설공사","- 작업내용 : #1T/L 가선로 구성 - 위 치 : 전주시 완산구 석구동 일원 - 규 모 : ACSR410㎟ × 2B × 4C(0.81km, 지지물 4기)","2024-10-21 07:00","2024-10-25 18:00","2024-10-21 07:00","2024-10-25 18:00","연속"]
[510,"전북","김제","신김제동전주#2 T/L","154kV 완산분기T/L 건설공사","- 작업내용 : #2T/L 가선로 구성 - 위 치 : 전주시 완산구 석구동 일원 - 규 모 : ACSR410㎟ × 2B × 4C(0.81km, 지지물 4기)","2024-10-28 07:00","2024-11-01 18:00","2024-10-28 07:00","2024-11-01 18:00","연속"]
[511,"전북","김제","신김제전주#1 T/L","관내S/S 154kV 차단기 조작시험","관내S/S 154kV 차단기 조작시험","2024-10-04 09:00","2024-10-04 16:00","2024-10-04 09:00","2024-10-04 16:00","연속"]
[512,"전북","김제","정주동부안#2 T/L","정주S/S 154kV #60-#65 BUS-TIE 차단기 정밀점검","정주S/S 154kV #60-#65 BUS-TIE 차단기 정밀점검(09.30~10.01, 연속)","2024-10-01 16:00","2024-10-01 16:30","2024-10-01 16:00","2024-10-01 16:30","연속"]
[513,"전북","김제","정주고창#1 T/L","154kV 소성S/S 및 분기T/L 건설공사","○ 송전분야[작업기간 : 9.30 ~ 10.04 (5일간 연속)] - 작업내용 : 변전소 인입, 전선이동, 가철탑 철거 등 ○ 변전분야[작업기간 : 10.07 ~ 10.11 (5일간 연속)] - 작업내용 : 보호반 이설·설치, 대국시험, 변전기기 무부하 가압 및 PD측정, 실부하 가압","2024-10-07 07:00","2024-10-23 18:00","2024-10-07 07:00","2024-10-23 18:00","연속"]
[514,"전북","김제","정주동부안#2 T/L","정주S/S #65-#66 SEC 차단기 정밀점검(10.7~8, 연속)","정주S/S #65-#66 SEC 차단기 정밀점검(10.7~8, 연속)","2024-10-22 16:00","2024-10-22 16:30","2024-10-22 16:00","2024-10-22 16:30","연속"]
[515,"전북","김제","정주고창#2 T/L","154kV 소성S/S 및 분기T/L 건설공사","○ 송전분야[작업기간 : 10.14 ~ 10.16 (3일간 연속)] - 작업내용 : 변전소 인입, 전선이동, 가철탑 철거 등 ○ 변전분야[작업기간 : 10.17 ~ 10.22 (6일간 연속)] - 작업내용 : 보호반 이설·설치, 대국시험, 변전기기 무부하 가압 및 PD측정, 실부하 가압","2024-10-24 07:00","2024-11-03 18:00","2024-10-24 07:00","2024-11-03 18:00","연속"]
[516,"전북","직할","무주진안 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","○ 154kV 무주-진안T/L No.104~175 수평 추락방지시설 설치 ○ 154kV 무주분기(무주-진안)T/L No.1~45 수평 추락방지시설 설치","2024-10-12 07:00","2024-10-19 17:00","2024-10-12 07:00","2024-10-19 17:00","매일"]
[517,"전북","직할","북전주봉동#2 T/L","2024년 전북직할 170kV GIS 정밀점검공사","북전주-봉동#2TL GIS 정밀점검","2024-10-14 09:00","2024-10-17 18:00","취소","취소","연속"]
[518,"전북","직할","북전주진안 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","○ 154kV 북전주-진안T/L No.1~175 수평 추락방지시설 설치","2024-10-21 07:00","2024-10-29 17:00","2024-10-21 07:00","2024-10-29 17:00","매일"]
[519,"전북","직할","진안장수#2 T/L","2024년 전북직할 170kV GIS 정밀점검공사","장수-진안#2TL GIS 정밀점검","2024-10-14 09:00","2024-10-18 18:00","2024-10-14 09:00","2024-10-18 18:00","연속"]
[520,"전북","직할","진안장수#1 T/L","2024년 전북직할 170kV GIS 정밀점검공사","장수-진안#1TL GIS 정밀점검","2024-10-07 09:00","2024-10-10 18:00","2024-10-07 09:00","2024-10-10 18:00","연속"]
[521,"전북","직할","진안장수#1 T/L","장수 6233 GIS 정밀점검 1DS 무부하 가압","장수 6233 GIS 정밀점검 1DS, CB부 무부하가압","2024-10-29 17:00","2024-10-29 17:30","2024-10-29 17:00","2024-10-29 17:30","연속"]
[522,"전북","직할","진안장수#1 T/L","장수 6233 GIS 정밀점검 2DS 무부하 가압","장수 6233 GIS 정밀점검 2DS부 무부하가압","2024-10-31 17:00","2024-10-31 17:30","2024-10-31 17:00","2024-10-31 17:30","연속"]
[523,"전북","직할","진안장수#1 T/L","장수 6100 GIS 정밀점검 2DS 무부하 가압","장수 6100 GIS 정밀점검 2DS 부 무부하가압","2024-10-24 17:00","2024-10-24 17:30","2024-10-24 17:00","2024-10-24 17:30","연속"]
[524,"전북","직할","진안장수#1 T/L","장수 6100 GIS 정밀점검 1DS 무부하 가압","장수 6100 GIS 정밀점검 1DS, CB 부 무부하가압","2024-10-22 17:00","2024-10-22 17:30","2024-10-22 17:00","2024-10-22 17:30","연속"]
[525,"광주전남","강진","나주금천#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 신화순-나주#2TL 피뢰기 및 항공표시구, 추락방지장치 설치(병가구간) 작업구간 : 신화순-나주 40~63호(나주-금천 77~100호 子선로)","2024-10-14 07:00","2024-10-16 18:00","2024-10-14 07:00","2024-10-16 18:00","매일"]
[526,"광주전남","강진","나주금천#1 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-10-21 08:00 ~ 2024-10-25 18:00 ○ 작업구간 : 154kV 나주-금천#1T/L No.1~7, 77~110-1 ○ 작업내용 : 정밀점검","2024-10-21 08:00","2024-10-25 18:00","2024-10-21 08:00","2024-10-25 18:00","매일"]
[527,"광주전남","강진","나주금천#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 신화순-나주#1TL 항공표시구 및 추락방지장치 설치(병가구간) 작업구간 : 신화순-나주 44~45, 53호(나주-금천 子선로)","2024-10-21 07:00","2024-10-21 18:00","취소","취소","연속"]
[528,"광주전남","강진","나주엄다#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 신화순-나주#2TL 피뢰기 설치(병가구간) 작업구간 : 신화순-나주 65~72호(나주-엄다 1~7.1호 子선로)","2024-10-17 07:00","2024-10-18 18:00","취소","취소","매일"]
[529,"광주전남","강진","나주금천#2 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-10-14 08:00 ~ 2024-10-18 18:00 ○ 작업구간 : 154kV 나주-금천#2T/L No.1~7, 77~110-1 ○ 작업내용 : 정밀점검","2024-10-14 08:00","2024-10-18 18:00","취소","취소","매일"]
[530,"광주전남","강진","강진남창#1 T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 초기점검","2024-10-11 09:00","2024-10-11 14:00","2024-10-11 09:00","2024-10-11 14:00","연속"]
[531,"광주전남","강진","남창완도 T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 하자점검","2024-10-10 09:00","2024-10-10 14:00","2024-10-10 09:00","2024-10-10 14:00","연속"]
[532,"광주전남","강진","남창완도CS T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 초기점검","2024-10-10 14:00","2024-10-10 18:00","2024-10-10 14:00","2024-10-10 18:00","연속"]
[533,"광주전남","강진","강진남창#2 T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 초기점검","2024-10-11 14:00","2024-10-11 18:00","2024-10-11 14:00","2024-10-11 18:00","연속"]
[534,"광주전남","강진","신강진대불#1 T/L","2024년 가공송전 순시점검 위탁공사","신강진-해남#2T/L 정밀점검 4회선 병가구간 휴전","2024-10-17 08:00","2024-10-18 18:00","취소","취소","매일"]
[535,"광주전남","강진","신강진대불#2 T/L","2024년 가공송전 순시점검 위탁공사","신강진-해남#1T/L 정밀점검 4회선 병가구간 휴전","2024-10-01 08:00","2024-10-02 18:00","취소","취소","매일"]
[536,"광주전남","강진","강진장흥#1 T/L","2024년 가공송전 순시점검 위탁공사","장흥-보성T/L 1~64호 정밀점검 4회선 구간 휴전","2024-10-21 08:00","2024-10-21 18:00","취소","취소","매일"]
[537,"광주전남","강진","장흥보성 T/L","2024년 가공송전 순시점검 위탁공사","장흥-보성T/L 1~64호 정밀점검","2024-10-21 08:00","2024-10-25 18:00","취소","취소","매일"]
[538,"광주전남","강진","화원진도#2 T/L","'24년 강진전력지사 효성제 170kV GIS 개선 공사","진도S/S 효성제 #5M.Tr 1차 GIS 주접점 이탈 관련 차단부 교체 관련 무부하 가압","2024-10-23 09:00","2024-10-24 18:00","취소","취소","연속"]
[539,"광주전남","강진","화원진도#2 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 화원-진도#2 T/L 40~78호 39기","2024-10-15 08:00","2024-10-18 18:00","취소","취소","매일"]
[540,"광주전남","강진","해남진도#1 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 해남-진도#1 T/L 1, 4~8, 16~74, 87~95, 102~104호 78기","2024-10-01 08:00","2024-10-14 18:00","취소","취소","매일"]
[541,"광주전남","강진","진도진도CS#1 T/L","2024-2025년 강진전력지사 변전협력회사 공사","유압조작기 유면계 와셔 교체","2024-10-21 09:00","2024-10-21 18:00","2024-10-21 09:00","2024-10-21 18:00","연속"]
[542,"광주전남","강진","진도진도CS#2 T/L","2024-2025년 강진전력지사 변전협력회사 공사","유압조작기 유면계 와셔 교체","2024-10-22 09:00","2024-10-22 18:00","2024-10-22 09:00","2024-10-22 18:00","연속"]
[543,"광주전남","강진","해남진도#2 T/L","'24년 강진전력지사 효성제 170kV GIS 개선 공사","진도S/S 효성제 #5M.Tr 1차 GIS 주접점 이탈 관련 차단부 교체 관련 무부하 가압","2024-10-23 09:00","2024-10-24 18:00","취소","취소","연속"]
[544,"광주전남","강진","진도C/S P1+FF2 CB","'24~'25년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) Bipole 연차점검","2024-10-20 09:00","2024-10-29 18:00","2024-10-20 09:00","2024-10-29 18:00","연속"]
[545,"광주전남","강진","진도C/S P2+FF2 CB","'24~'25년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) Bipole 연차점검","2024-10-20 09:00","2024-10-29 18:00","2024-10-20 09:00","2024-10-29 18:00","연속"]
[546,"광주전남","강진","서제주진도HVDC(2연계선) #1 Pole CB","'24~'25년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) #1Pole 연차점검","2024-10-15 09:00","2024-10-29 18:00","2024-10-15 09:00","2024-10-29 18:00","연속"]
[547,"광주전남","강진","진도C/S P1+FF1 CB","'24~'25년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) Bipole 연차점검","2024-10-20 09:00","2024-10-29 18:00","2024-10-20 09:00","2024-10-29 18:00","연속"]
[548,"광주전남","강진","진도C/S P2+FF1 CB","'24~'25년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) Bipole 연차점검","2024-10-20 09:00","2024-10-29 18:00","2024-10-20 09:00","2024-10-29 18:00","연속"]
[549,"광주전남","강진","서제주진도HVDC(2연계선) #2 Pole CB","'24~'25년도 #2HVDC 변환설비 위탁정비공사","#2HVDC(진도,서제주C/S) Bipole 연차점검","2024-10-20 09:00","2024-10-29 18:00","2024-10-20 09:00","2024-10-29 18:00","연속"]
[550,"광주전남","광주","계림승주#2 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 계림-승주T/L 추락방지장치설치공사 No.2~107호 중 84기","2024-10-21 07:00","2024-10-25 18:00","취소","취소","매일"]
[551,"광주전남","광주","계림S/S SEC CB 65660","24년 광주전력지사 170kV 이상 GIS 보통점검","- 170kV GIS 보통점검","2024-10-23 09:00","2024-10-23 18:00","2024-10-23 09:00","2024-10-23 18:00","연속"]
[552,"광주전남","광주","계림승주#1 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 계림-승주T/L 추락방지장치설치공사 No.2~107호 중 84기","2024-10-14 07:00","2024-10-18 18:00","취소","취소","매일"]
[553,"광주전남","광주","남광주금천#2 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-10-21 08:00 ~ 2024-10-25 18:00 ○ 작업구간 : 154kV 나주-금천#1T/L No.1~7, 77~110-1 ○ 작업내용 : 정밀점검 ○ 비고 : 21일 남광주-금천#2T/L 병가구간 작업 시 휴전요청(1~7호)","2024-10-21 08:00","2024-10-21 18:00","2024-10-18 08:00","2024-10-21 18:00","연속"]
[554,"광주전남","광주","남광주금천#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 신화순-나주#2TL 피뢰기 설치(병가구간) 작업구간 : 신화순-나주 38호(남광주-금천75호 子선로)","2024-10-11 07:00","2024-10-11 18:00","취소","취소","연속"]
[555,"광주전남","광주","남광주금천#1 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-10-14 08:00 ~ 2024-10-18 18:00 ○ 작업구간 : 154kV 나주-금천#2T/L No.1~7, 77~110-1 ○ 작업내용 : 정밀점검 ○ 비고 : 14일 남광주-금천#1T/L 병가구간 작업 시 휴전요청(1~7호)","2024-10-14 08:00","2024-10-14 18:00","취소","취소","연속"]
[556,"광주전남","광주","남광주금천#2 T/L","2024년 광주전력 변전협력회사 총액공사","□작업명 : 남광주SS 남광주금천#2TL 보통점검","2024-10-31 09:00","2024-10-31 18:00","취소","취소","연속"]
[557,"광주전남","광주","담양S/S SEC CB 60610","24년 광주전력지사 170kV 이상 GIS 보통점검","- 170kV GIS 보통점검","2024-10-21 09:00","2024-10-21 18:00","2024-10-21 09:00","2024-10-21 18:00","연속"]
[558,"광주전남","광주","담양S/S SEC CB 65660","24년 광주전력지사 170kV 이상 GIS 보통점검","- 170kV GIS 보통점검","2024-10-22 09:00","2024-10-22 18:00","2024-10-22 09:00","2024-10-22 18:00","연속"]
[559,"광주전남","광주","신화순매월#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 신화순-나주#1TL 조류착지 방지장치 설치(병가구간) 작업구간 : 신화순-나주 6호(나주-금천 6호 子선로)","2024-10-21 07:00","2024-10-21 18:00","2024-10-21 07:00","2024-10-21 18:00","연속"]
[560,"광주전남","광주","신화순매월#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 신화순-나주#2TL 피뢰기 및 조류착지방지장치 설치(병가구간) 작업구간 : 신화순-나주 6~9호(신화순-매월6~9호 子선로)","2024-10-07 07:00","2024-10-07 18:00","2024-10-07 07:00","2024-10-07 18:00","연속"]
[561,"광주전남","광주","계림충장#3 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 154kV 계림-충장#3T/L GIS 조작시험","2024-10-08 09:00","2024-10-08 14:00","2024-10-08 09:00","2024-10-08 14:00","연속"]
[562,"광주전남","광주","계림충장#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 154kV 계림-충장#2T/L GIS 조작시험","2024-10-07 14:00","2024-10-07 18:00","2024-10-07 14:00","2024-10-07 18:00","연속"]
[563,"광주전남","광주","계림충장#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 154kV 계림-충장#1T/L GIS 조작시험","2024-10-07 09:00","2024-10-07 14:00","2024-10-07 09:00","2024-10-07 14:00","연속"]
[564,"광주전남","목포","목포북항#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","목포S/S 154kV 목포-북항#1T/L GIS 보통점검 북항S/S 154kV 목포-북항#1T/L GIS 조작시험, LA 점검","2024-10-21 09:00","2024-10-21 18:00","2024-10-21 09:00","2024-10-21 18:00","연속"]
[565,"광주전남","목포","목포북항#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","목포S/S 154kV 목포-북항#2T/L GIS 보통점검","2024-10-22 09:00","2024-10-22 18:00","2024-10-22 09:00","2024-10-22 18:00","연속"]
[566,"광주전남","목포","남악북항#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","북항S/S 154kV 남악-북항#2T/L GIS 조작시험, LA 점검","2024-10-24 09:00","2024-10-24 18:00","2024-10-24 09:00","2024-10-24 18:00","연속"]
[567,"광주전남","목포","남악북항#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","북항S/S 154kV 남악-북항#1T/L GIS 조작시험, LA 점검 남악S/S 154kV 남악-북항#1T/L GIS 보통점검","2024-10-23 09:00","2024-10-23 18:00","2024-10-23 09:00","2024-10-23 18:00","연속"]
[568,"광주전남","목포","엄다S/S #1 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L, #3M.Tr 1차 #1BUS측 철거 및 설치","2024-10-16 14:00","2024-11-05 14:00","2024-10-16 14:00","2024-11-05 14:00","연속"]
[569,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L, #3M.Tr 1차 #1BUS측 무부하가압용","2024-10-31 14:00","2024-11-01 14:00","2024-10-31 14:00","2024-11-01 14:00","연속"]
[570,"광주전남","목포","엄다목포#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L, #3M.Tr 1차 GIS 교체","2024-10-14 09:00","2024-11-29 18:00","2024-10-14 09:00","2024-11-29 18:00","연속"]
[571,"광주전남","목포","엄다목포#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다-목포#1T/L GIS 교체작업","2024-07-23 09:00","2024-09-10 18:00","취소","취소","연속"]
[572,"광주전남","목포","장성영광#1 T/L","154kV 영광-홍농 등 4개T/L 선종교체공사","1. 공사명 : 154kV 영광-홍농 등 4개T/L 선종교체공사 2. 공사내용 ○ 24.10.14~24.11.22 (4회선 하단) 영광-홍농T/L 선종교체공사(연속휴전 송전운영부) ※ 4회선구간 : 영황-홍농 선종교체공사를 위해 장성-영광#1 안전휴전 (매일휴전_송전운영부)","2024-10-14 07:00","2024-11-08 18:00","취소","취소","연속"]
[573,"광주전남","목포","영광홍농 T/L","154kV 영광-홍농 등 4개T/L 선종교체공사","1. 공사명 : 154kV 영광-홍농 등 4개T/L 선종교체공사 2. 공사내용 ○ 24.10.14~24.11.22 (4회선 하단) 영광-홍농T/L 선종교체공사(연속휴전 송전운영부) ※ 4회선구간 : 영황-홍농 선종교체공사를 위해 장성-영광#1 안전휴전 (매일휴전_송전운영부)","2024-10-14 07:00","2024-11-22 18:00","취소","취소","연속"]
[574,"광주전남","목포","장성영광#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","GIS 조작시험","2024-10-08 09:00","2024-10-08 18:00","취소","취소","연속"]
[575,"광주전남","목포","장성영광#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","GIS 조작시험","2024-10-10 09:00","2024-10-10 18:00","취소","취소","연속"]
[576,"광주전남","순천","광양백운#1 T/L","24~25년 순천전력지사 변전협력회사 공사","광양S/S 광양-백운#1T/L LA 보통점검","2024-10-07 14:00","2024-10-07 18:00","2024-10-07 14:00","2024-10-07 18:00","연속"]
[577,"광주전남","순천","광양순천#2 T/L","24~25년 순천전력지사 변전협력회사 공사","광양S/S 광양-순천#2T/L LA 보통점검","2024-10-07 09:00","2024-10-07 14:00","2024-10-07 09:00","2024-10-07 14:00","연속"]
[578,"광주전남","순천","백운세풍#1 T/L","154kV 광양바이오매스발전소 접속설비 연계공사","154kV 백운-세풍- 황금개폐소 간 2파이 분기 접속설비 연계를 위한 공용송전망 Y분기 접속공사 및 시험","2024-10-09 09:00","2024-10-30 18:00","2024-10-09 09:00","2024-10-30 18:00","연속"]
[579,"광주전남","순천","서순천벌교#1 T/L","벌교S/S 170kV GIS 순도불량조치(17:00~10:00 매일휴전)","벌교S/S 170kV GIS 순도불량 조치 공사(17:00 ~ 10:00 매일 휴전)","2024-10-14 17:00","2024-10-18 10:00","2024-10-14 17:00","2024-10-18 10:00","매일"]
[580,"광주전남","순천","소라서순천#1 T/L","도로 횡단개소 애자련 보강 및 금구류 교체공사(순천 가공협력)","○ 도로 횡단개소 애자련 보강 → 소라-서순천 #1 T/L No. 63, 121호","2024-10-16 07:00","2024-10-17 18:00","취소","취소","매일"]
[581,"광주전남","순천","순천율촌#1 T/L","도로 횡단개소 애자련 보강(순천 가공협력)","○ 도로 횡단개소 애자련 보강 → 순천-율촌 #1,2 T/L No. 67호","2024-10-15 07:00","2024-10-15 14:00","취소","취소","연속"]
[582,"광주전남","순천","순천율촌#2 T/L","도로 횡단개소 애자련 보강(순천 가공협력)","○ 도로 횡단개소 애자련 보강 → 순천-율촌 #1,2 T/L No. 67호","2024-10-15 14:00","2024-10-15 18:00","취소","취소","연속"]
[583,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-31 07:00","2024-10-31 18:00","취소","취소","연속"]
[584,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-01 07:00","2024-10-02 18:00","취소","취소","매일"]
[585,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2024-10-28 09:00","2024-10-29 18:00","취소","취소","연속"]
[586,"광주전남","순천","여수T/P CB 6200","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-10-25 15:40","2024-10-25 16:00","취소","취소","연속"]
[587,"광주전남","순천","여수T/P SEC CB 60610","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-10-25 15:20","2024-10-25 15:40","취소","취소","연속"]
[588,"광주전남","순천","여수T/P SEC CB 65660","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-10-25 15:00","2024-10-25 15:20","취소","취소","연속"]
[589,"광주전남","순천","여수TP용성#2 T/L","SB댐퍼 설치공사(순천 가공협력)","○ SB댐퍼 설치공사 → 여수TP-용성#2 T/L No. 0.01~3.99호","2024-10-24 07:00","2024-10-25 18:00","2024-10-17 07:00","2024-10-18 18:00","매일"]
[590,"광주전남","순천","여수TP용성#1 T/L","SB댐퍼 설치공사(순천 가공협력)","○ SB댐퍼 설치공사 → 여수TP-용성#1 T/L No. 0.01~3.99호","2024-10-22 07:00","2024-10-23 18:00","취소","취소","매일"]
[591,"광주전남","순천","여수T/P CB 6100","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-10-18 15:40","2024-10-18 16:00","취소","취소","연속"]
[592,"광주전남","순천","여수T/P SEC CB 60610","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-10-18 15:20","2024-10-18 15:40","취소","취소","연속"]
[593,"광주전남","순천","여수T/P SEC CB 65660","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-10-18 15:00","2024-10-18 15:20","취소","취소","연속"]
[594,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-14 13:00","2024-10-14 18:00","취소","취소","연속"]
[595,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-14 07:00","2024-10-14 13:00","취소","취소","연속"]
[596,"광주전남","순천","호남TP여수TP#2 T/L","154kV 호남TP-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-11 07:00","2024-10-11 18:00","취소","취소","연속"]
[597,"광주전남","순천","호남TP여수TP#1 T/L","154kV 호남TP-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-10 07:00","2024-10-10 18:00","취소","취소","연속"]
[598,"광주전남","순천","여수TP여천#2 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-07 07:00","2024-10-08 18:00","취소","취소","매일"]
[599,"광주전남","순천","여천호남TP#2 T/L","24년 가공송전 위탁공사(애자 오염시스템 설치)","○애자 오염시스템 설치 No. 1,10호 총2기","2024-10-24 09:00","2024-10-25 18:00","2024-10-24 09:00","2024-10-25 18:00","매일"]
[600,"광주전남","순천","여천호남TP#1 T/L","24년 가공송전 위탁공사(애자 오염시스템 설치)","○애자 오염시스템 설치 No. 1,10호 총2기","2024-10-22 09:00","2024-10-23 18:00","2024-10-22 09:00","2024-10-23 18:00","매일"]
[601,"광주전남","순천","용성여수산단#2 T/L","154kV 용성-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-16 07:00","2024-10-16 18:00","취소","취소","매일"]
[602,"광주전남","순천","여수TP용성#1 T/L","용성S/S 여수TP-용성#1T/L GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2024-10-01 09:00","2024-10-02 18:00","취소","취소","연속"]
[603,"광주전남","순천","용성여수산단#1 T/L","SB댐퍼 설치공사(순천 가공협력)","○ SB댐퍼 설치공사 → 여수TP-용성#1 T/L No. 0.01~3.99호","2024-10-22 07:00","2024-10-23 18:00","2024-10-22 07:00","2024-10-23 18:00","매일"]
[604,"광주전남","순천","용성여수산단#2 T/L","SB댐퍼 설치공사(순천 가공협력)","○ SB댐퍼 설치공사 → 여수TP-용성#2 T/L No. 0.01~3.99호","2024-10-24 07:00","2024-10-25 18:00","2024-10-24 07:00","2024-10-25 18:00","매일"]
[605,"광주전남","순천","율촌민자#1 T/L","154kV 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-28 07:00","2024-10-28 18:00","2024-10-28 07:00","2024-10-28 18:00","연속"]
[606,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-23 07:00","2024-10-24 18:00","취소","취소","매일"]
[607,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-21 07:00","2024-10-22 18:00","취소","취소","매일"]
[608,"광주전남","순천","율촌여수산단#2 T/L","율촌-여수산단#2T/L GIS #1DS 가스누기","율촌-여수산단#2T/L GIS #1DS 가스누기(즉시가압 불가)","2024-10-11 09:00","2024-10-12 18:00","취소","취소","연속"]
[609,"광주전남","순천","율촌S/S #60 BUS","율촌-여수산단#2T/L GIS #1DS 가스누기","율촌-여수산단#2T/L GIS #1DS 가스누기(즉시가압 불가)","2024-10-11 09:00","2024-10-12 18:00","취소","취소","연속"]
[610,"광주전남","순천","율촌S/S #66 BUS","순천-율촌#1T/L GIS #1,2DS 가스누기","순천-율촌#1T/L GIS #1,2DS 가스누기(즉시가압 불가)","2024-10-05 09:00","2024-10-06 18:00","취소","취소","연속"]
[611,"광주전남","순천","율촌민자#2 T/L","154kV 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-10-29 07:00","2024-10-29 18:00","2024-10-29 07:00","2024-10-29 18:00","연속"]
[612,"광주전남","순천","순천율촌#1 T/L","순천-율촌#1T/L GIS #1,2DS 가스누기","순천-율촌#1T/L GIS #1,2DS 가스누기(즉시가압 불가)","2024-10-04 09:00","2024-10-06 18:00","취소","취소","연속"]
[613,"광주전남","순천","율촌S/S #61 BUS","순천-율촌#1T/L GIS #1,2DS 가스누기","순천-율촌#1T/L GIS #1,2DS 가스누기(즉시가압 불가)","2024-10-04 09:00","2024-10-05 18:00","취소","취소","연속"]
[614,"광주전남","순천","태금하동화력 T/L","효성제 170kv gis 부품 교체 시행","효성제 170kv gis 부품 교체 시행(즉시가압 불가)","2024-10-21 09:00","2024-10-21 18:00","2024-10-21 09:00","2024-10-21 18:00","연속"]
[615,"광주전남","순천","호남T/P 린데코리아T/L CB","24-25 순천전력지사 협력회사공사","호남T/P 154kV 린데코리아 #1DS 실플렌지 교체(즉시가압불가)","2024-10-14 09:00","2024-10-15 18:00","취소","취소","연속"]
[616,"광주전남","직할","일곡비아#2 T/L","`24년 직할 170kV GIS 정밀 및 보통점검공사","170kV GIS 보통점검","2024-10-21 09:00","2024-10-21 18:00","2024-10-21 09:00","2024-10-21 18:00","연속"]
[617,"광주전남","직할","비아하남#2 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-10-01 08:00 ~ 2024-10-11 18:00 ○ 작업구간 : 154kV 비아-하남#2T/L No.28~74 ○ 작업내용 : 정밀점검","2024-10-01 08:00","2024-10-11 18:00","2024-10-01 08:00","2024-10-11 18:00","매일"]
[618,"광주전남","직할","비아하남#1 T/L","`24년 직할 170kV GIS 정밀 및 보통점검공사","하남 : 170kV GIS 정밀점검 비아 : 170kV GIS 보통점검","2024-10-16 14:00","2024-10-18 18:00","2024-10-16 14:00","2024-10-18 18:00","연속"]
[619,"광주전남","직할","하남장성#2 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-10-01 08:00 ~ 2024-10-11 18:00 ○ 작업구간 : 154kV 비아-하남#2T/L No.28~74 ○ 작업내용 : 정밀점검 ○ 비고 : 7~11일 하남-장성T/L 병가구간 작업 시 휴전요청(55~73호)","2024-10-07 08:00","2024-10-11 18:00","2024-10-07 08:00","2024-10-11 18:00","매일"]
[620,"대구","경산","경산S/S #1 EM.Tr CB","24년 경산FR-ESS(PCS,BAT) 정기점검","24년 경산FR-ESS(PCS,BAT) 정기점검","2024-10-14 09:00","2024-10-25 18:00","2024-10-14 09:00","2024-10-25 18:00","연속"]
[621,"대구","경산","영천S/S #1 EM.Tr CB","24~25년 경산P/O 변전협력회사 총액공사","ESS 변전설비 초기점검","2024-10-21 09:30","2024-10-25 18:00","2024-10-28 09:30","2024-11-01 18:00","연속"]
[622,"대구","경산","영천S/S #2 EM.Tr CB","24~25년 경산P/O 변전협력회사 총액공사","ESS 변전설비 초기점검","2024-10-28 09:30","2024-11-01 18:00","2024-11-04 09:30","2024-11-08 18:00","연속"]
[623,"대구","달성","강창다사 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 강창-다사T/L 수평 추락방지장치 설치공사","2024-10-24 07:00","2024-10-24 18:00","2024-10-24 07:00","2024-10-24 18:00","연속"]
[624,"대구","달성","달서강창 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 강창-달서T/L 수평 추락방지장치 설치공사","2024-10-24 07:00","2024-10-25 18:00","2024-10-24 07:00","2024-10-25 18:00","연속"]
[625,"대구","달성","다사달서 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 다사-달서T/L 수평 추락방지장치 설치공사","2024-10-30 07:00","2024-10-30 18:00","2024-10-30 07:00","2024-10-30 18:00","연속"]
[626,"대구","달성","달성S/S CB 6100","차단기동작시험","차단기동작시험","2024-10-04 09:00","2024-10-04 13:00","2024-10-04 09:00","2024-10-04 13:00","연속"]
[627,"대구","달성","성서달성#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 성서-달성T/L 수평 추락방지장치 설치공사","2024-10-21 07:00","2024-10-22 18:00","2024-10-21 07:00","2024-10-22 18:00","연속"]
[628,"대구","달성","성서달성#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 성서-달성T/L 수평 추락방지장치 설치공사","2024-10-17 07:00","2024-10-18 18:00","2024-10-17 07:00","2024-10-18 18:00","연속"]
[629,"대구","달성","상인봉덕#2 T/L","154kV 상인-봉덕 지중T/L 지장송전선로 이설공사","154kV 상인-봉덕 지중T/L 지장송전선로 이설공사","2024-10-18 09:00","2024-11-12 18:00","2024-10-18 09:00","2024-11-12 18:00","연속"]
[630,"대구","달성","팔달내당#2 T/L","154kV 팔달-서침산 지중T/L 건설사업","□ 구 간 : 154㎸ 팔달-내당T/L (M/H#9) ∼ 154kV 서침산S/S □ 사업규모 : 154㎸ XLPE 2,000㎟×2C - 4.5km (M/H#9 ∼ 서침산S/S) ※ 기설 설비 활용 : 154㎸ XLPE 2,000㎟×2C - 3.0km (팔달S/S ∼ M/H#9)","2024-10-14 09:00","2024-12-05 18:00","2024-10-14 09:00","2024-12-05 18:00","연속"]
[631,"대구","달성","팔달내당#1 T/L","154kV 팔달-서침산 지중T/L 건설사업","□ 구 간 : 154㎸ 팔달-내당T/L (M/H#9) ∼ 154kV 서침산S/S □ 사업규모 : 154㎸ XLPE 2,000㎟×2C - 4.5km (M/H#9 ∼ 서침산S/S) ※ 기설 설비 활용 : 154㎸ XLPE 2,000㎟×2C - 3.0km (팔달S/S ∼ M/H#9)","2024-10-14 09:00","2024-12-05 18:00","2024-10-14 09:00","2024-12-05 18:00","연속"]
[632,"대구","직할","시지효목#2 T/L","시지효목 #2T/L 절연유 채유","154kV 시지-효목 #2T/L 3상 EBA 절연유 채유","2024-10-23 10:00","2024-10-23 17:00","2024-10-23 10:00","2024-10-23 17:00","연속"]
[633,"대구","칠곡","북대구왜관#1 T/L","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 154kV 인출측 정비","2024-10-28 07:30","2024-11-01 18:00","2024-10-28 07:30","2024-11-01 18:00","연속"]
[634,"대구","칠곡","북대구연락#1 T/L","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 154kV 인출측 정비","2024-10-28 07:30","2024-11-01 18:00","2024-10-28 07:30","2024-11-01 18:00","연속"]
[635,"대구","칠곡","북대구구암#1 T/L","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 154kV 인출측 정비","2024-10-28 07:30","2024-10-29 18:00","2024-10-28 07:30","2024-10-29 18:00","연속"]
[636,"대구","칠곡","북대구왜관#2 T/L","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 154kV 인출측 정비","2024-10-28 07:30","2024-11-01 18:00","2024-10-28 07:30","2024-11-01 18:00","연속"]
[637,"대구","포항","옥동외동#2 T/L","2024~25년도 포항전력지사 변전총액공사","외동S/S 687, 657 GIS 조작시험","2024-10-17 14:00","2024-10-17 18:00","2024-10-17 14:00","2024-10-17 18:00","연속"]
[638,"대구","포항","옥동외동#1 T/L","2024~25년도 포항전력지사 변전총액공사","외동S/S 687, 657 GIS 조작시험","2024-10-17 09:00","2024-10-17 14:00","2024-10-17 09:00","2024-10-17 14:00","연속"]
[639,"대구","포항","울주입실#2 T/L","2024~25년도 포항전력지사 변전총액공사","입실S/S 637 GIS 보통점검","2024-10-16 09:00","2024-10-16 18:00","2024-10-16 09:00","2024-10-16 18:00","연속"]
[640,"대구","포항","울주입실#1 T/L","2024~25년도 포항전력지사 변전총액공사","입실S/S 617 GIS 보통점검","2024-10-15 09:00","2024-10-15 18:00","2024-10-15 09:00","2024-10-15 18:00","연속"]
[641,"대구","포항","건천천북#1 T/L","2024~25년도 포항전력지사 변전총액공사","천북S/S 677 GIS 하자점검, LA,PT 보통점검","2024-10-14 09:00","2024-10-14 18:00","2024-10-14 09:00","2024-10-14 18:00","연속"]
[642,"경북","구미","청리상주#2 T/L","2024-25년 구미전력지사 변전협력회사 공사","[상주S/S] - PNL 교체 [청리S/S] - PNL 교체 - LA 보통점검","2024-10-28 09:00","2024-11-01 18:00","2024-10-28 09:00","2024-11-01 18:00","연속"]
[643,"경북","구미","청리상주#1 T/L","2024-25년 구미전력지사 변전협력회사 공사","[상주S/S] - PNL 교체 [청리S/S] - PNL 교체 - LA 보통점검","2024-10-22 09:00","2024-10-25 18:00","2024-10-22 09:00","2024-10-25 18:00","연속"]
[644,"경북","구미","선산청리#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사","154kV 선산-청리#1T/L 조류착지방지장치 교체(총 19기. No.22~132)","2024-10-28 07:30","2024-10-30 18:00","2024-10-28 07:30","2024-10-30 18:00","매일"]
[645,"경북","구미","선산청리#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사","154kV 선산-청리#2T/L 조류착지방지장치 교체(총 47기. No.40~132)","2024-10-23 07:30","2024-10-25 18:00","2024-10-23 07:30","2024-10-25 18:00","매일"]
[646,"경북","구미","남인동인동#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사","1. 154kV 남인동-인동#2T/L 암플레이트 교체(No.22) 2. 154kV 남인동-인동#2T/L SB댐퍼 교체(No.39, 40, 47, 48)","2024-10-21 07:30","2024-10-23 18:00","2024-10-21 07:30","2024-10-23 18:00","매일"]
[647,"경북","구미","남인동인동#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사","1. 154kV 남인동-인동#1T/L 암플레이트 교체(No.22) 2. 154kV 남인동-인동#1T/L SB댐퍼 교체(No.2, 13, 39, 47, 48)","2024-10-16 07:30","2024-10-18 18:00","2024-10-16 07:30","2024-10-18 18:00","매일"]
[648,"경북","영주","영주S/S #1 EM.Tr CB","2024-25년 영주전력지사 변전협력회사 공사","초기점검","2024-10-28 09:00","2024-11-01 18:00","2024-10-28 09:00","2024-11-01 18:00","연속"]
[649,"경북","영주","신영주영주#1 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압","2024-10-17 16:00","2024-10-17 18:00","2024-10-17 16:00","2024-10-17 18:00","연속"]
[650,"경북","영주","예천점촌#2 T/L","154kV 예천-점촌T/L 추락방지장치 설치공사","154kV 예천-점촌T/L 추락방지장치 설치공사","2024-10-05 08:00","2024-10-13 17:00","2024-10-05 08:00","2024-10-13 17:00","매일"]
[651,"경북","영주","예천점촌#1 T/L","154kV 예천-점촌#1T/L 피뢰기 및 수평추락방지장치 설치공사","154kV 예천-점촌#1T/L 피뢰기 및 수평추락방지장치 설치공사","2024-10-14 08:00","2024-10-22 17:00","2024-10-14 08:00","2024-10-22 17:00","매일"]
[652,"경북","영주","동상주점촌#1 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-10-18 09:00","2024-10-19 18:00","2024-10-18 09:00","2024-10-19 18:00","연속"]
[653,"경북","영주","예천점촌#1 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-10-25 09:00","2024-10-26 18:00","취소","취소","연속"]
[654,"경북","영주","예천점촌#2 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-10-27 09:00","2024-10-28 18:00","취소","취소","연속"]
[655,"경북","영주","동상주점촌#2 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-10-20 14:00","2024-10-21 18:00","2024-10-20 09:00","2024-10-21 18:00","연속"]
[656,"경북","영주","점촌문경 T/L","154kV 단양T/L 수평추락방지장치 설치공사","154kV 단양T/L 수평추락방지장치 설치공사","2024-10-05 08:00","2024-10-06 17:00","2024-10-05 08:00","2024-10-06 17:00","매일"]
[657,"경북","영주","동상주점촌#2 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압","2024-10-23 09:00","2024-10-24 18:00","2024-10-23 18:00","2024-10-24 10:00","연속"]
[658,"경북","영주","점촌문경 T/L","154kV 단양T/L수평추락방지장치 설치공사","154kV 단양T/L 수평추락방지장치 설치공사","2024-10-12 08:00","2024-10-13 17:00","2024-10-12 08:00","2024-10-13 17:00","매일"]
[659,"경북","영주","점촌단양 T/L","154kV 단양T/L 피뢰기 및 수평추락방지장치 설치공사","154kV 단양T/L 피뢰기 및 수평추락방지장치 설치공사","2024-10-18 08:00","2024-10-26 17:00","2024-10-18 08:00","2024-10-26 17:00","매일"]
[660,"경북","영주","동상주점촌#2 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","GIS 정밀점검 후 무부하가압","2024-10-30 18:00","2024-10-31 10:00","2024-10-30 18:00","2024-10-31 10:00","연속"]
[661,"경북","직할","동안동임하HP T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","154kV 안동-동안동T/L #2T/L No.18~23 선종교체작업(안전이격확보)","2024-10-01 09:00","2024-10-04 18:00","2024-10-01 09:00","2024-10-04 18:00","연속"]
[662,"경북","직할","안동동안동#2 T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","154kV 안동-동안동T/L #2T/L No.18~23 선종교체","2024-10-01 09:00","2024-10-04 18:00","2024-10-01 09:00","2024-10-04 18:00","연속"]
[663,"경북","직할","안동동안동#1 T/L","154kV 안동-동안동T/L 용량증대 선종교체공사","154kV 안동-동안동T/L #2T/L No.18~23 선종교체","2024-10-01 09:00","2024-10-04 18:00","2024-10-01 09:00","2024-10-04 18:00","연속"]
[664,"경북","직할","영덕평해#2 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","점퍼선 횡진방지 절연가드 설치","2024-10-07 09:00","2024-10-07 18:00","취소","취소","연속"]
[665,"경북","직할","울진삼척GP#2 T/L","`24~25년 경북본부 직할 변전협력회사 공사","GIS 초기점검","2024-10-08 09:00","2024-10-08 18:00","2024-10-08 09:00","2024-10-08 18:00","연속"]
[666,"경북","직할","울진삼척GP#1 T/L","`24~25년 경북본부 직할 변전협력회사 공사","GIS 초기점검","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[667,"경북","직할","현종산풍력평해#2 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","154kV 울진-현종산T/L 추락방지장치 설치","2024-10-28 09:00","2024-10-30 18:00","2024-10-28 09:00","2024-10-30 18:00","연속"]
[668,"경북","직할","울진현종산풍력 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","울진-현종산T/L 추락방지장치 설치","2024-10-28 08:00","2024-10-30 18:00","2024-10-28 08:00","2024-10-30 18:00","연속"]
[669,"경북","직할","봉화현종산풍력 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","154kV 울진-현종산T/L 추락방지장치 설치공사","2024-10-31 09:00","2024-11-04 18:00","2024-10-31 09:00","2024-11-04 18:00","연속"]
[670,"경북","직할","현종산풍력평해#1 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","154kV 울진-현종산T/L 추락방지장치 설치공사","2024-10-31 09:00","2024-11-04 18:00","2024-10-31 09:00","2024-11-04 18:00","연속"]
[671,"부산울산","직할","부산수정#1 T/L","24년 하반기 직할 170kV GIS 정밀점검공사","수정S/S 항만청#1T/L 정밀점검공사 시험가압용","2024-10-08 16:00","2024-10-08 18:00","2024-10-08 16:00","2024-10-08 18:00","연속"]
[672,"부산울산","직할","부산수정#1 T/L","수정S/S 154kV #1,2,3 M.Tr 교체공사","#1M.Tr 교체공사 시험가압 선로","2024-10-31 18:00","2024-11-01 18:00","2024-10-24 18:00","2024-10-25 18:00","연속"]
[673,"부산울산","울산","반천언양#1 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치, 수평추락방지장치 설치","2024-10-07 07:30","2024-10-09 18:00","2024-10-07 07:30","2024-10-09 18:00","연속"]
[674,"부산울산","울산","남울산신온산#1 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#2T/L(S/T~28호) 154kV 용연-울산TP#3T/L (4호)_작업없음 / 병가 울주-울산TP#2 4호 154kV 성암-울산TP#2T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#1T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#1T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#1T/L(S/T~16호 / 병가 울주-울산TP 15~26호)","2024-10-22 08:00","2024-10-24 18:00","2024-10-22 08:00","2024-10-24 18:00","연속"]
[675,"부산울산","울산","남울산처용#1 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#2T/L(S/T~28호) 154kV 용연-울산TP#3T/L (4호)_작업없음 / 병가 울주-울산TP#2 4호 154kV 성암-울산TP#2T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#1T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#1T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#1T/L(S/T~16호 / 병가 울주-울산TP 15~26호)","2024-10-22 08:00","2024-10-22 18:00","2024-10-22 08:00","2024-10-22 18:00","연속"]
[676,"부산울산","울산","남울산신온산#2 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#1T/L(S/T~28호) 154kV 성암-울산TP#1T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#2T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#2T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#2T/L(S/T~16호 / 병가 울주-울산TP 15~26호)","2024-10-15 08:00","2024-10-17 18:00","2024-10-15 08:00","2024-10-17 18:00","연속"]
[677,"부산울산","울산","남울산처용#2 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#1T/L(S/T~28호) 154kV 성암-울산TP#1T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#2T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#2T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#2T/L(S/T~16호 / 병가 울주-울산TP 15~26호)","2024-10-15 08:00","2024-10-15 18:00","2024-10-15 08:00","2024-10-15 18:00","연속"]
[678,"부산울산","울산","신울산명례#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-10-09 07:30","2024-10-10 18:00","2024-10-09 07:30","2024-10-10 18:00","연속"]
[679,"부산울산","울산","신울산명례#1 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-10-03 07:30","2024-10-04 18:00","2024-10-03 07:30","2024-10-04 18:00","연속"]
[680,"부산울산","울산","언양산막#2 T/L","154kV 석계분기T/L 건설공사","지지물 : 154kV 산형강철탑 5기 전력선 : ACSR 410 * 2B * 4C","2024-10-03 07:00","2024-10-05 18:00","2024-10-03 07:00","2024-10-05 18:00","연속"]
[681,"부산울산","울산","남울산용연#2 T/L","24년 울산전력지사 변전협력회사 총액공사","-용연측 효성제 조작부 발청보수","2024-10-11 09:00","2024-10-11 18:00","2024-10-11 09:00","2024-10-11 18:00","연속"]
[682,"부산울산","울산","울주직동#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-10-21 09:00","2024-10-21 18:00","2024-10-21 09:00","2024-10-21 18:00","연속"]
[683,"부산울산","울산","울주직동#2 T/L","24년도 울산전력지사 주변압기 정밀점검","- 1차 GIS 정밀점검 시험가압(1H)","2024-10-16 17:00","2024-10-16 18:00","2024-10-12 17:00","2024-10-12 18:00","연속"]
[684,"부산울산","울산","울주S/S #1 EM.Tr CB","24년도 울산전력지사 주변압기 정밀점검","- 1차 GIS 정밀점검 - 주변압기 보통점검 - OLTC 정밀점검","2024-10-14 09:00","2024-10-16 18:00","2024-10-10 09:00","2024-10-12T18:00:00","연속"]
[685,"부산울산","울산","직동반천#2 T/L","2024년 가공송전 순시점검 위탁공사","154kV 직동-반천T/L 정밀점검","2024-10-17 09:00","2024-10-18 18:00","2024-10-17 09:00","2024-10-18 18:00","연속"]
[686,"부산울산","울산","웅촌서창#2 T/L","2024-2025년 동부산 가공송전협력회사 공사","- 레일형 수평추락방지장치 설치","2024-10-30 07:00","2024-10-31 18:00","취소","취소","연속"]
[687,"부산울산","울산","웅촌서창#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","- 레일형 수평추락방지장치 설치","2024-10-28 07:00","2024-10-29 18:00","취소","취소","연속"]
[688,"부산울산","울산","신울산매암#1 T/L","24년 울산전력지사 개폐장치 정밀 및 보통점검 공사","- GIS 정밀점검 시험가압(1h)","2024-10-23 17:00","2024-10-23 18:00","2024-10-23 17:00","2024-10-23 18:00","연속"]
[689,"부산울산","울산","성암울산TP#2 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#2T/L(S/T~28호) 154kV 용연-울산TP#3T/L (4호)_작업없음 / 병가 울주-울산TP#2 4호 154kV 성암-울산TP#2T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#1T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#1T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#1T/L(S/T~16호 / 병가 울주-울산TP 15~26호)","2024-10-21 08:00","2024-10-21 18:00","2024-10-21 08:00","2024-10-21 18:00","연속"]
[690,"부산울산","울산","용연울산TP#3 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#2T/L(S/T~28호) 154kV 용연-울산TP#3T/L (4호)_작업없음 / 병가 울주-울산TP#2 4호 154kV 성암-울산TP#2T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#1T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#1T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#1T/L(S/T~16호 / 병가 울주-울산TP 15~26호)","2024-10-21 08:00","2024-10-21 18:00","2024-10-21 08:00","2024-10-21 18:00","연속"]
[691,"부산울산","울산","성암울산TP#1 T/L","2024년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 시행 345kV 울주-울산TP#1T/L(S/T~28호) 154kV 성암-울산TP#1T/L (4~9호) / 병가 울주-울산TP 5~9호 345kV 남울산-울산TP#2T/L(8호~S/T) / 병가 울주-울산TP 10호 154kV 남울산-처용#2T/L(S/T~6호) / 병가 울주-울산TP 11~14호 154kV 남울산-신온산#2T/L(S/T~16호 / 병가 울주-울산TP 15~26호)","2024-10-14 08:00","2024-10-14 18:00","2024-10-14 08:00","2024-10-14 18:00","연속"]
[692,"부산울산","울산","산하방어진#1 T/L","효성제GIS 조작부 발청보수","효성제GIS 조작부 발청보수","2024-10-05 09:00","2024-10-05 14:00","2024-10-05 09:00","2024-10-05 14:00","연속"]
[693,"부산울산","울산","반천언양#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치, 수평추락방지장치 설치, 피뢰기 설치","2024-10-10 07:30","2024-10-11 18:00","2024-10-10 07:30","2024-10-11 18:00","연속"]
[694,"부산울산","울산","반천언양#1 T/L","2024년 가공송전 순시점검 위탁공사","154kV 직동-반천T/L 정밀점검 안전이격","2024-10-18 09:00","2024-10-18 18:00","2024-10-18 09:00","2024-10-18 18:00","연속"]
[695,"부산울산","북부산","개금범천#2 T/L","개금S/S 개금-범천#1,2T/L GIS 교체공사","개금-범천#2T/L GIS 교체","2024-10-11 09:00","2024-10-30 18:00","2024-10-02 14:00","2024-10-02 18:00","연속"]
[696,"부산울산","북부산","북부산미남#2 T/L","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 북부산-미남#1,2T/L LA 대체","2024-10-31 13:00","2024-10-31 18:00","2024-10-31 13:00","2024-10-31 18:00","연속"]
[697,"부산울산","북부산","북부산미남#1 T/L","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 북부산-미남#1,2T/L LA 대체","2024-10-31 09:00","2024-10-31 13:00","2024-10-31 09:00","2024-10-31 13:00","연속"]
[698,"부산울산","북부산","북부산삼랑진PP T/L","154kV 북부산-양산T/L OPGW 증설공사","OPGW 교체 : 21.5km","2024-10-06 09:00","2024-10-25 18:00","2024-10-06 09:00","2024-10-25 18:00","연속"]
[699,"부산울산","북부산","북부산양산 T/L","154kV 북부산-양산T/L OPGW 증설공사","OPGW 교체 : 21.5km","2024-10-06 09:00","2024-10-25 18:00","2024-10-06 09:00","2024-10-25 18:00","연속"]
[700,"부산울산","북부산","서부산엄궁#2 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","엄궁S/S 154kV 서부산-엄궁#2T/L GIS 정밀점검","2024-10-28 09:00","2024-10-29 18:00","2024-10-28 09:00","2024-10-29 18:00","연속"]
[701,"부산울산","북부산","서부산엄궁#1 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","엄궁S/S 154kV 서부산-엄궁#1T/L GIS 정밀점검","2024-10-24 09:00","2024-10-25 18:00","2024-10-24 09:00","2024-10-25 18:00","연속"]
[702,"부산울산","북부산","모라엄궁#2 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","엄궁S/S 154kV 모라-엄궁#2T/L GIS 정밀점검","2024-10-21 09:00","2024-10-22 18:00","2024-10-21 09:00","2024-10-22 18:00","연속"]
[703,"부산울산","북부산","모라엄궁#2 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","모라S/S #4M.Tr 1차 GIS 정밀점검 -시험가압 선로:#2BUS, 모라-엄궁#2T/L","2024-10-18 17:00","2024-10-18 18:00","2024-10-18 17:00","2024-10-18 18:00","연속"]
[704,"부산울산","북부산","모라엄궁#1 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","모라S/S #3M.Tr 1차 GIS 정밀점검 -시험가압 선로:#1BUS, 모라-엄궁#1T/L","2024-10-15 17:00","2024-10-15 18:00","2024-10-15 17:00","2024-10-15 18:00","연속"]
[705,"부산울산","북부산","모라엄궁#2 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","모라S/S #2M.Tr 1차 GIS 정밀점검 -시험가압 선로:#2BUS, 모라-엄궁#2T/L","2024-10-11 17:00","2024-10-11 18:00","2024-10-11 17:00","2024-10-11 18:00","연속"]
[706,"부산울산","북부산","모라엄궁#1 T/L","대한전선제 열경화공법 EBG 보강공사","EBG 해체, 가스채취밸브 설치, 스프링유닛 점검 등","2024-10-09 09:00","2024-10-10 18:00","취소","취소","연속"]
[707,"부산울산","북부산","모라엄궁#1 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","모라S/S #1M.Tr 1차 GIS 정밀점검 -시험가압 선로:#1BUS, 모라-엄궁#1T/L","2024-10-08 17:00","2024-10-08 18:00","2024-10-08 17:00","2024-10-08 18:00","연속"]
[708,"부산울산","북부산","호포매리#2 T/L","23-24년 북부산전력 지중송전 위탁정비공사","호포 케이블타워 지중송전케이블 고정와이어 탈락개소 재정비","2024-10-13 09:00","2024-10-13 18:00","2024-10-12 09:00","2024-10-12 18:00","연속"]
[709,"부산울산","북부산","호포매리#1 T/L","23-24년 북부산전력 지중송전 위탁정비공사","호포 케이블타워 지중송전케이블 고정와이어 탈락개소 재정비","2024-10-12 09:00","2024-10-12 18:00","2024-10-13 09:00","2024-10-13 18:00","연속"]
[710,"부산울산","북부산","서창산막#1 T/L","산막S/S 장기사용 154kV GIS 대체공사","산막S/S 언양-산막#1T/L 대체 -시험가압선로 : 서창-산막#1T/L","2024-10-27 14:00","2024-10-27 16:00","2024-10-27 14:00","2024-10-27 16:00","연속"]
[711,"부산울산","북부산","양산산막#1 T/L","산막S/S 장기사용 154kV GIS 대체공사","산막S/S 언양-산막#1T/L 대체 -시험가압선로 : 양산-산막#1T/L","2024-10-27 14:00","2024-10-27 16:00","취소","취소","연속"]
[712,"부산울산","북부산","언양산막#1 T/L","산막S/S 장기사용 154kV GIS 대체공사","산막S/S 언양-산막#1T/L 대체","2024-10-26 09:00","2024-11-09 20:00","2024-10-26 09:00","2024-11-09 20:00","연속"]
[713,"부산울산","북부산","양산산막#1 T/L","24-25년 북부산전력지사 변전총액공사","산막S/S 양산-산막#1T/L GIS 보통점검","2024-10-04 09:00","2024-10-04 18:00","2024-10-04 09:00","2024-10-04 18:00","연속"]
[714,"부산울산","동부산","신양산구서#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","- 갠트리타워 안전발판 설치","2024-10-21 07:00","2024-10-21 18:00","2024-10-21 07:00","2024-10-21 18:00","연속"]
[715,"부산울산","동부산","장안고리NP T/L","2024년 가공송전 순시점검 위탁공사","154kV 정관-장안, 장안분기T/L 초기점검","2024-10-22 09:00","2024-10-23 18:00","2024-10-22 09:00","2024-10-23 18:00","연속"]
[716,"부산울산","동부산","구서S/S #2 BUS","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#2T/L GIS #2DS 철거 및 고깔처리 ○ (구)BUS-TIE GIS #2DS 철거 및 고깔처리","2024-10-30 09:00","2024-11-01 18:00","2024-10-30 09:00","2024-11-01 18:00","연속"]
[717,"부산울산","동부산","구서노포#1 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-10-14 07:30","2024-10-15 18:00","2024-10-14 07:30","2024-10-15 18:00","연속"]
[718,"부산울산","동부산","구서노포#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-10-11 07:30","2024-10-11 18:00","2024-10-11 07:30","2024-10-11 18:00","연속"]
[719,"부산울산","동부산","수영정보#1 T/L","정보S/S 6100 GIS 정밀점검 시험가압 선로","정보S/S 6100 GIS 정밀점검 시험가압 선로","2024-10-06 17:00","2024-10-06 18:00","2024-10-20 17:00","2024-10-20 18:00","연속"]
[720,"부산울산","동부산","정보S/S CB 6100","정보S/S 6100 GIS 정밀점검","정보S/S 6100 GIS 정밀점검","2024-10-05 09:00","2024-10-06 18:00","2024-10-19 09:00","2024-10-20 18:00","연속"]
[721,"부산울산","동부산","신양산구서#2 T/L","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#2T/L GIS 교체 ○ BUS-SEC DS 설치","2024-10-30 09:00","2024-11-29 18:00","2024-10-30 09:00","2024-11-29 18:00","연속"]
[722,"부산울산","동부산","명례장안 T/L","2024년 가공송전 순시점검 위탁공사","154kV 정관-장안, 장안분기T/L 초기점검","2024-10-24 09:00","2024-10-24 18:00","2024-10-24 09:00","2024-10-24 18:00","연속"]
[723,"부산울산","동부산","정관장안#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","- 레일형 수평추락방지장치 설치","2024-10-22 07:00","2024-10-22 18:00","2024-10-22 09:00","2024-10-23 18:00","연속"]
[724,"부산울산","동부산","정관장안#2 T/L","2024-2025년 동부산 가공송전협력회사 공사","- 레일형 수평추락방지장치 설치","2024-10-25 07:00","2024-10-25 18:00","2024-10-25 07:00","2024-10-25 18:00","연속"]
[725,"부산울산","동부산","서창산막#1 T/L","서창S/S 667GIS 차단기 동작시험","서창S/S 667GIS 차단기 동작시험","2024-10-05 09:30","2024-10-05 14:00","2024-10-05 09:30","2024-10-05 14:00","연속"]
[726,"부산울산","동부산","서창산막#2 T/L","서창S/S 687GIS 차단기 동작시험","서창S/S 687GIS 차단기 동작시험","2024-10-05 14:00","2024-10-05 17:00","2024-10-05 14:00","2024-10-05 17:00","연속"]
[727,"부산울산","동부산","노포정관#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-10-28 09:00","2024-10-29 18:00","2024-10-28 09:00","2024-10-29 18:00","연속"]
[728,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○1차분 (미음-녹산#2T/L, #2M.Tr 1차 대체, PT&ES설치) - 미음-녹산#2T/L, #2M.Tr 1차 1DS, CB 철거 및 신규GIS 설치 - 모선 PT&ES 설치 - #1BUS 시험가압 (1DS 개방상태) 24시간 - 시험가압선로 (신녹산-녹산#1T/L)","2024-10-04 18:00","2024-10-05 18:00","2024-10-04 18:00","2024-10-05 18:00","연속"]
[729,"부산울산","서부산","녹공마천#2 T/L","녹공S/S154kV 녹공-마천#2T/L GIS 동작시험","녹공S/S154kV 녹공-마천#2T/L GIS 동작시험","2024-10-08 09:00","2024-10-08 18:00","2024-10-08 09:00","2024-10-08 18:00","연속"]
[730,"부산울산","서부산","녹공마천#1 T/L","녹공S/S154kV 녹공-마천#1T/L GIS 동작시험","녹공S/S154kV 녹공-마천#1T/L GIS 동작시험","2024-10-07 09:00","2024-10-07 18:00","2024-10-07 09:00","2024-10-07 18:00","연속"]
[731,"부산울산","서부산","신녹산용원#1 T/L","용원S/S154kV 신녹산-용원#1T/L GIS 보통점검","용원S/S154kV 신녹산-용원#1T/L GIS 보통점검","2024-10-23 09:00","2024-10-23 18:00","2024-10-23 09:00","2024-10-23 18:00","연속"]
[732,"부산울산","서부산","신녹산명지#2 T/L","345kV 신녹산S/S #1M.Tr 증설공사","○ 154kV 신녹산-명지#2T/L GIS 이설 및 송전선로 구내 인출변경","2024-10-21 09:00","2024-11-29 18:00","2024-10-21 09:00","2024-11-29 18:00","연속"]
[733,"부산울산","서부산","신녹산용원#2 T/L","용원S/S154kV 신녹산-용원#2T/L GIS 보통점검","용원S/S154kV 신녹산-용원#2T/L GIS 보통점검","2024-10-24 09:00","2024-10-24 18:00","2024-10-24 09:00","2024-10-24 18:00","연속"]
[734,"부산울산","서부산","서부산S/S #1 M.Tr","서부산S/S 345kV #1M.Tr 2차 GIS 동작시험","서부산S/S 345kV #1M.Tr 2차 GIS 동작시험","2024-10-21 09:00","2024-10-21 18:00","취소","취소","연속"]
[735,"부산울산","서부산","미음녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○1차분 (미음-녹산#2T/L, #2M.Tr 1차 대체, PT&ES설치) - 미음-녹산#2T/L, #2M.Tr 1차 2DS 철거 및 신규GIS 설치 - #2BUS PT&ES 설치 - #2BUS 시험가압 (2DS, CB 개방상태) 24시간 - 안전거리이격확보(미음-녹산#1T/L) 미음-녹산#2T/L 부싱설치","2024-10-09 09:00","2024-10-10 18:00","2024-10-09 09:00","2024-10-10 18:00","연속"]
[736,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○1차분 (미음-녹산#2T/L, #2M.Tr 1차 대체, PT&ES설치) - 미음-녹산#2T/L, #2M.Tr 1차 2DS 철거 및 신규GIS 설치 - #2BUS PT&ES 설치 - #2BUS 시험가압 (2DS, CB 개방상태) 24시간 - 시험가압선로(신녹산-녹산#1T/L)","2024-10-11 18:00","2024-10-12 18:00","2024-10-11 18:00","2024-10-12 18:00","연속"]
[737,"부산울산","서부산","녹산S/S #1 BUS","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○2차분 (기존 BUS PT&ES 철거, 신규 BUS-TIE 설치) - #1BUS PT&ES 철거 - 신규 BUS-TIE 설치 (CB, #1DS)","2024-10-21 09:00","2024-10-26 18:00","2024-10-21 09:00","2024-10-26 18:00","연속"]
[738,"부산울산","서부산","녹산S/S CB 6100","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○2차분 (기존 BUS PT 철거, BUS-TIE 설치) - 기존 BUS BUS PT&ES 철거 - 신규 BUS-TIE 설치","2024-10-21 09:00","2024-11-06 18:00","2024-10-21 09:00","2024-11-06 18:00","연속"]
[739,"부산울산","서부산","녹산S/S #2 BUS","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○2차분 (기존 BUS PT&ES 철거, 신규 BUS-TIE 설치) - #2BUS PT&ES 철거 - 신규 BUS-TIE 설치 (#2DS, 상부BUS) - 중공시험 -시험가압 (#2DS, CB 투입상태) 24시간","2024-10-28 09:00","2024-11-06 17:00","2024-10-28 09:00","2024-11-06 17:00","연속"]
[740,"부산울산","서부산","녹산S/S #2 BUS","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○1차분 (미음-녹산#2T/L, #2M.Tr 1차 대체, PT&ES설치) - 미음-녹산#2T/L, #2M.Tr 1차 2DS 철거 및 신규GIS 설치 - #2BUS PT&ES 설치 - #2BUS 시험가압 (2DS, CB 개방상태) 24시간","2024-10-06 09:00","2024-10-12 18:00","2024-10-06 09:00","2024-10-12 18:00","연속"]
[741,"경남","김해송변전부","매리김해#2 T/L","154kV 김해S/S 주변압기 대체공사(시험가압)","154kV 김해S/S 주변압기 대체공사(#4M.Tr) - #4M.Tr 철거 및 설치 - 전력케이블, NGR, 유효접지용 DS, 제어케이블 철거 및 설치 - 변압기실 흡음재 철거 및 설치 - 기타 부대공사 1식. 끝.","2024-10-16 09:00","2024-10-17 09:00","2024-10-16 09:00","2024-10-17 09:00","연속"]
[742,"경남","김해송변전부","김해S/S #2 M.Tr CB","154kV 김해S/S 주변압기 대체공사","154kV 김해S/S 주변압기 대체공사(#2M.Tr) - #2M.Tr 철거 및 설치 - 전력케이블, NGR, 유효접지용 DS, 제어케이블 철거 및 설치 - 변압기실 흡음재 철거 및 설치 - 기타 부대공사 1식. 끝.","2024-10-20 09:00","2024-11-29 18:00","2024-10-31 09:00","2024-12-13 18:00","연속"]
[743,"경남","김해송변전부","호포매리#2 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ 인수점검 불량사항 조치","2024-10-12 09:00","2024-10-12 18:00","2024-10-12 09:00","2024-10-12 18:00","연속"]
[744,"경남","김해송변전부","매리김해#1 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ 인수점검 불량사항 조치","2024-10-12 09:00","2024-10-12 18:00","취소","취소","연속"]
[745,"경남","김해송변전부","매리김해#2 T/L","154kV 호포-매리T/L 24호 변위철탑 교체공사","○ 인수점검 불량사항 조치","2024-10-12 09:00","2024-10-12 18:00","2024-10-12 09:00","2024-10-12 18:00","연속"]
[746,"경남","김해송변전부","신김해주촌#2 T/L","345kV 신김해-북부산#1T/L 철탑추락방지장치 설치공사","154kV 신김해-주촌#2T/L 4~6호(3기) 수평형 철탑추락방지장치 설치","2024-10-06 07:00","2024-10-06 18:00","2024-10-06 07:00","2024-10-06 18:00","연속"]
[747,"경남","김해송변전부","신김해진례#2 T/L","345kV 신김해-북부산#1T/L 철탑추락방지장치 설치공사","154kV 신김해-진례#2T/L 9~14,24호(7기) 수평형 철탑추락방지장치 및 24호(1기) 고정형 폴리머 점퍼지지애자 설치","2024-10-05 07:00","2024-10-05 18:00","2024-10-05 07:00","2024-10-05 18:00","연속"]
[748,"경남","김해송변전부","신김해진례#1 T/L","345kV 신김해-북부산#2T/L 철탑추락방지장치 설치공사","154kV 신김해-진례#1T/L 9~14,24호(7기) 수평형 철탑추락방지장치 및 14호(1기) 고정형 폴리머 점퍼지지애자 설치","2024-10-03 07:00","2024-10-03 18:00","2024-10-03 07:00","2024-10-03 18:00","연속"]
[749,"경남","김해송변전부","신김해주촌#1 T/L","345kV 신김해-북부산#2T/L 철탑추락방지장치 설치공사","154kV 신김해-주촌#1T/L 4~6호(3기) 수평형 철탑추락방지장치 설치","2024-10-09 07:00","2024-10-09 18:00","2024-10-09 07:00","2024-10-09 18:00","연속"]
[750,"경남","김해송변전부","삼계어방#2 T/L","24-25년 함안전력지사 송전협력회사 총액공사(안전이격)","24-25년 함안전력지사 송전협력회사 총액공사(안전이격)","2024-10-27 07:00","2024-10-27 18:00","2024-10-27 07:00","2024-10-27 18:00","매일"]
[751,"경남","김해송변전부","주촌삼계#1 T/L","24-25년 함안전력지사 송전협력회사 총액공사(안전이격)","24-25년 함안전력지사 송전협력회사 총액공사(안전이격)","2024-10-27 07:00","2024-10-27 18:00","2024-10-27 07:00","2024-10-27 18:00","연속"]
[752,"경남","김해송변전부","진례진영#1 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-05 07:00","2024-10-05 18:00","2024-10-05 07:00","2024-10-05 18:00","매일"]
[753,"경남","김해송변전부","진례진영#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-05 14:00","2024-10-05 18:00","2024-10-05 14:00","2024-10-05 18:00","매일"]
[754,"경남","김해송변전부","진례진영#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-09 07:00","2024-10-09 18:00","2024-10-09 07:00","2024-10-09 18:00","매일"]
[755,"경남","김해송변전부","진영수산#1 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-26 07:00","2024-10-26 18:00","2024-10-26 07:00","2024-10-26 18:00","매일"]
[756,"경남","김해송변전부","진례진영#2 T/L","154kV 진례-진영#2T/L 철탑 추락방지장치 설치공사","작업자 추락재해 예방을 위한 수평형 철탑추락방지장치 설치공사 (대상개소 : 154kV 진례-진영#2T/L 7호) ※ 대상개소는 154kV 동읍-진영#2T/L 40호에 병가(수직배치)","2024-10-21 07:00","2024-10-21 18:00","2024-10-21 07:00","2024-10-21 18:00","연속"]
[757,"경남","김해송변전부","진영한림정#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-26 07:00","2024-10-26 18:00","2024-10-26 07:00","2024-10-26 18:00","매일"]
[758,"경남","김해송변전부","한림정삼계#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-28 07:00","2024-10-28 18:00","2024-10-28 07:00","2024-10-28 18:00","매일"]
[759,"경남","김해송변전부","한림정삼계#1 T/L","24-25년 함안전력지사 송전협력회사 총액공사(피뢰기설치공사)","24-25년 함안전력지사 송전협력회사 총액공사(피뢰기설치공사)","2024-10-27 07:00","2024-10-27 18:00","2024-10-27 07:00","2024-10-27 18:00","매일"]
[760,"경남","김해송변전부","한림정삼계#1 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-26 11:00","2024-10-26 18:00","2024-10-26 11:00","2024-10-26 18:00","매일"]
[761,"경남","김해송변전부","한림정삼계#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-10-26 07:00","2024-10-26 11:00","2024-10-26 07:00","2024-10-26 11:00","연속"]
[762,"경남","직할","신월삼정#2 T/L","154kV 신월-삼정T/L OF 케이블 절연유 채유","154kV 신월-삼정#2T/L OF 케이블 절연유 채유","2024-10-12 09:00","2024-10-12 18:00","2024-10-12 09:00","2024-10-12 18:00","연속"]
[763,"경남","직할","신월동읍#2 T/L","신월S/S 신월-동읍#2T/L GIS 정밀점검","신월S/S 신월-동읍#2T/L GIS 정밀점검","2024-10-10 09:30","2024-10-12 18:00","2024-10-10 09:30","2024-10-12 18:00","연속"]
[764,"경남","직할","신월동읍#1 T/L","154kV 신월-동읍T/L OF 케이블 절연유 채유","154kV 신월-동읍#1T/L OF 케이블 절연유 채유","2024-10-19 09:00","2024-10-19 18:00","2024-10-19 09:00","2024-10-19 18:00","연속"]
[765,"경남","직할","신월삼정#1 T/L","154kV 신월-삼정T/L OF 케이블 절연유 채유","154kV 신월-삼정#1T/L OF 케이블 절연유 채유","2024-10-19 09:00","2024-10-19 18:00","2024-10-19 09:00","2024-10-19 18:00","연속"]
[766,"경남","직할","안민천선#2 T/L","154kV 안민-천선T/L 피뢰기 열화진단","154kV 안민-천선#2T/L 피뢰기 열화진단","2024-10-18 09:00","2024-10-18 18:00","2024-10-18 09:00","2024-10-18 18:00","연속"]
[767,"경남","직할","안민천선#1 T/L","154kV 안민-천선T/L 피뢰기 열화진단","154kV 안민-천선#1T/L 피뢰기 열화진단","2024-10-17 09:00","2024-10-17 18:00","2024-10-17 09:00","2024-10-17 18:00","연속"]
[768,"경남","직할","진해S/S #1 M.Tr CB","154kV 진해S/S #1M.Tr 구내이설","○ 154kV 진해S/S 옥내화 건설공사 - #1M.Tr 구내이설 및 OLTC 정밀점검 - #1M.Tr 무부하 시험가압 - 사용 전 검사","2024-10-23 09:00","2024-11-08 15:00","2024-10-23 09:00","2024-11-08 15:00","연속"]
[769,"경남","직할","마천진해#2 T/L","154kV 마천-진해#2T/L 인출변경공사","○ 154kV 진해S/S 옥내화 건설공사 - 154kV 마천-진해#2T/L 인출변경공사(10/21 ~ 11/6) - 마천-진해#2T/L GIS 사용 전 검사 (11/7 ~ 8)","2024-10-21 09:00","2024-11-08 15:00","2024-10-21 09:00","2024-11-08 15:00","연속"]
[770,"경남","직할","진해S/S 군항#1T/L CB","154kV 군항#1T/L 인출변경공사","○ 154kV 진해S/S 옥내화 건설공사 - 154kV 군항#1T/L 인출변경공사(10/1 ~ 10/20) - 군항#1T/L GIS 사용 전 검사 (10/21)","2024-10-01 09:00","2024-10-21 15:00","취소","취소","연속"]
[771,"경남","진주","의령동진주#2 T/L","154kV 의령-동진주T/L EBA 절연유 채유","154kV 의령-동진주#2T/L EBA 절연유 채유","2024-10-31 09:00","2024-10-31 18:00","취소","취소","연속"]
[772,"경남","진주","의령동진주#1 T/L","154kV 의령-동진주T/L EBA 절연유 채유","154kV 의령-동진주#1T/L EBA 절연유 채유","2024-10-30 09:00","2024-10-30 18:00","취소","취소","연속"]
[773,"경남","진주","사봉개양#1 T/L","사봉, 개양S/S 사봉-개양#1T/L 보호반 대체","사봉S/S 사봉-개양#1T/L 보호반 대체 [감독 : 김도연] 개양S/S 사봉-개양#1T/L 보호반 대체 [감독 : 박재면]","2024-10-23 10:00","2024-10-25 18:00","2024-10-23 10:00","2024-10-25 18:00","연속"]
[774,"경남","진주","의령함양 T/L","154kV 의령-함양/L 피뢰기 설치 공사 등","154kV 의령-함양/L 피뢰기 설치 공사 등 - №1~132 (132기)","2024-10-05 07:00","2024-10-11 18:00","2024-10-05 07:00","2024-10-11 18:00","매일"]
[775,"경남","진주","진주개양#1 T/L","154kV 진주-개양T/L EBA 절연유 채유","154kV 진주-개양#1T/L EBA 절연유 채유","2024-10-21 09:00","2024-10-22 14:00","2024-10-21 09:00","2024-10-22 14:00","매일"]
[776,"경남","진주","진주개양#2 T/L","154kV 진주-개양T/L EBA 절연유 채유","154kV 진주-개양#2T/L EBA 절연유 채유","2024-10-22 14:00","2024-10-24 18:00","2024-10-22 14:00","2024-10-24 18:00","매일"]
[777,"경남","진주","동진주진주#2 T/L","154kV 동진주-진주T/L EBA 절연유 채유","154kV 동진주-진주#2T/L EBA 절연유 채유","2024-10-28 14:00","2024-10-29 18:00","취소","취소","매일"]
[778,"경남","진주","동진주진주#1 T/L","154kV 동진주-진주T/L EBA 절연유 채유","154kV 동진주-진주#1T/L EBA 절연유 채유","2024-10-28 09:00","2024-10-28 14:00","취소","취소","연속"]
[779,"경남","진주","하동개양#1 T/L","하동S/S 154kV 하동-개양#1T/L GIS 조작시험","하동S/S 154kV 하동-개양#1T/L GIS 조작시험","2024-10-18 10:00","2024-10-18 14:00","취소","취소","연속"]
[780,"경남","진주","하동하동화력 T/L","하동S/S 154kV 하동-하동화력T/L GIS 하자점검","하동S/S 154kV 하동-하동화력T/L GIS 하자점검 [병행] LA(A,B,C) 보통 / PT(A) 대체","2024-10-31 10:00","2024-10-31 17:00","2024-10-31 10:00","2024-10-31 17:00","연속"]
[781,"경남","진주","광양하동#2 T/L","하동S/S 154kV 광양-하동#2T/L GIS 조작시험","하동S/S 154kV 광양-하동#2T/L GIS 조작시험 [병행] LA(C) 대체","2024-10-30 14:00","2024-10-30 17:00","2024-10-30 14:00","2024-10-30 17:00","연속"]
[782,"경남","진주","광양하동#1 T/L","하동S/S 154kV 광양-하동#1T/L GIS 조작시험","하동S/S 154kV 광양-하동#1T/L GIS 조작시험","2024-10-30 10:00","2024-10-30 14:00","2024-10-30 10:00","2024-10-30 14:00","연속"]
[783,"경남","진주","하동개양#2 T/L","하동S/S 154kV 하동-개양#2T/L GIS 조작시험","하동S/S 154kV 하동-개양#2T/L GIS 조작시험","2024-10-18 14:00","2024-10-18 17:00","취소","취소","연속"]
[784,"경남","진주","쌍림합천#2 T/L","합천S/S 154kV 쌍림-합천#2T/L GIS 조작시험","합천S/S 154kV 쌍림-합천#2T/L GIS 조작시험","2024-10-15 10:00","2024-10-15 15:00","2024-10-15 10:00","2024-10-15 15:00","연속"]
[785,"경남","통영","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-10-03 07:00","2024-10-03 18:00","2024-10-03 07:00","2024-10-03 18:00","연속"]
[786,"경남","통영","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-10-05 07:00","2024-10-06 18:00","2024-10-05 07:00","2024-10-06 18:00","매일"]
[787,"경남","통영","거류거제#1 T/L","154kV 거류-거제#1T/L 추락방지장치 설치공사","154kV 거류-거제#1T/L 추락방지장치 설치공사","2024-10-26 07:00","2024-10-27 18:00","2024-10-26 07:00","2024-10-27 18:00","매일"]
[788,"경남","통영","거류거제#1 T/L","154kV 거류-거제#1T/L 추락방지장치 설치공사","154kV 거류-거제#1T/L 추락방지장치 설치공사","2024-10-19 07:00","2024-10-20 18:00","2024-10-19 07:00","2024-10-20 18:00","매일"]
[789,"경남","통영","거류거제#1 T/L","154kV 거류-거제#1T/L 추락방지장치 설치공사","154kV 거류-거제#1T/L 추락방지장치 설치공사","2024-10-13 07:00","2024-10-13 18:00","2024-10-13 07:00","2024-10-13 18:00","연속"]
[790,"경남","통영","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-10-12 07:00","2024-10-12 18:00","2024-10-12 07:00","2024-10-12 18:00","연속"]
[791,"경남","통영","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-10-09 07:00","2024-10-09 18:00","2024-10-09 07:00","2024-10-09 18:00","연속"]
[792,"경남","통영","사천개양#1 T/L","154kV 사천-개양T/L 주수애자청소 안전이격확보","154kV 사천-개양T/L 주수애자청소 안전이격확보","2024-10-10 07:00","2024-10-11 18:00","2024-10-10 07:00","2024-10-11 18:00","매일"]
[793,"경남","통영","사천개양#2 T/L","154kV 사천-개양TL OPGW 정비공사","○ OPGW 48C 교체 : 2.594km ○ 광접속함체 교체 : 15개","2024-10-15 09:00","2024-10-17 18:00","2024-10-15 09:00","2024-10-17 18:00","연속"]
[794,"경남","통영","사천개양#1 T/L","154kV 사천-개양#1,2 T/L 추락방지장치 설치공사","154kV 사천-개양#1,2 T/L 추락방지장치 설치공사 No.74~ 86 수평배열로 인한 #1, 2T/L 동시휴전 필요","2024-10-02 07:00","2024-10-02 18:00","취소","취소","연속"]
[795,"경남","통영","삼천포사천#1 T/L","154kV 삼천포사천#1T/L 추락방지장치 설치공사","154kV 삼천포사천#1T/L 추락방지장치 설치공사","2024-10-07 07:00","2024-10-08 18:00","2024-10-07 07:00","2024-10-08 18:00","매일"]
[796,"경남","통영","삼천포사천#2 T/L","154kV 삼천포사천#2 T/L 추락방지장치 설치공사","154kV 삼천포사천#2 T/L 추락방지장치 설치공사","2024-10-10 07:00","2024-10-11 18:00","2024-10-10 07:00","2024-10-11 18:00","매일"]
[797,"경남","통영","사천개양#1 T/L","154kV 사천-개양T/L 주수애자청소 안전이격확보","154kV 사천-개양T/L 주수애자청소 안전이격확보","2024-10-26 07:00","2024-10-27 18:00","2024-10-26 07:00","2024-10-27 18:00","매일"]
[798,"경남","통영","사천개양#2 T/L","154kV 사천-개양#1,2 T/L 추락방지장치 설치공사","154kV 사천-개양#1,2 T/L 추락방지장치 설치공사 No.74~ 86 수평배열로 인한 #1, 2T/L 동시휴전 필요","2024-10-02 07:00","2024-10-02 18:00","취소","취소","연속"]
[799,"경남","통영","삼천포사천#2 T/L","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사","2024-10-01 07:00","2024-10-01 18:00","취소","취소","연속"]
[800,"경남","통영","삼천포사천#1 T/L","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사 (No.60~72 수평배열로 동시휴전 필요)","2024-10-01 07:00","2024-10-01 18:00","취소","취소","연속"]
[801,"경남","통영","삼천포사천#2 T/L","154kV 삼천포-사천T/L 주수애자청소 안전이격확보","154kV 삼천포-사천T/L 주수애자청소 안전이격확보","2024-10-26 07:00","2024-10-27 18:00","2024-10-26 07:00","2024-10-27 18:00","매일"]
[802,"경남","통영","신고성삼천포#2 T/L","154kV 신고성-삼천포#2T/L GIS 조작시험","154kV 신고성-삼천포#2T/L GIS 조작시험","2024-10-14 14:00","2024-10-14 18:00","2024-10-14 14:00","2024-10-14 18:00","연속"]
[803,"경남","통영","신고성삼천포#1 T/L","154kV 신고성-삼천포#1T/L GIS 조작시험","154kV 신고성-삼천포#1T/L GIS 조작시험","2024-10-14 10:00","2024-10-14 14:00","2024-10-14 10:00","2024-10-14 14:00","연속"]
[804,"경남","통영","신고성삼천포#1 T/L","154kV 신고성-삼천포#1T/L GIS 조작시험","154kV 신고성-삼천포#1T/L GIS 조작시험","2024-10-16 10:00","2024-10-16 18:00","2024-10-16 10:00","2024-10-16 18:00","연속"]
[805,"경남","통영","신고성삼천포#2 T/L","154kV 신고성-삼천포#2T/L GIS 조작시험","154kV 신고성-삼천포#2T/L GIS 조작시험","2024-10-17 10:00","2024-10-17 18:00","2024-10-17 10:00","2024-10-17 18:00","연속"]
[806,"경남","통영","진동안정#1 T/L","154kV 진동-안정#1T/L 철탑추락방지장치 설치공사","154kV 진동-안정#1T/L 2~7호(6기) 수평형 추락방지장치","2024-10-12 07:00","2024-10-12 18:00","2024-10-12 07:00","2024-10-12 18:00","연속"]
[807,"경남","통영","서마산진동#2 T/L","진동SS 154kV 서마산-진동#2T/L ES조작함 저항 교체","진동SS 154kV 서마산-진동#2T/L ES조작함 저항 교체","2024-10-10 10:00","2024-10-10 18:00","2024-10-10 10:00","2024-10-10 18:00","연속"]
[808,"경남","통영","서마산진동#2 T/L","진동SS 154kV 서마산-진동#2T/L ES조작함 저항 교체","진동SS 154kV 서마산-진동#2T/L ES조작함 저항 교체","2024-10-10 10:00","2024-10-10 18:00","2024-10-10 10:00","2024-10-10 18:00","연속"]
[809,"경남","통영","진동안정#2 T/L","154kV 진동-안정#2T/L 철탑추락방지장치 설치공사","154kV 진동-안정#2T/L 2~7호(6기) 수평형 추락방지장치 설치","2024-10-19 07:00","2024-10-19 18:00","2024-10-19 07:00","2024-10-19 18:00","연속"]
[810,"경남","통영","안정통영CC#1 T/L","154kV 안정-통영복합T/L GIS 보통점검 등","154kV 안정-통영복합T/L GIS 보통점검 등","2024-10-15 09:30","2024-10-15 18:00","2024-10-15 09:30","2024-10-15 18:00","연속"]
[811,"경남","통영","고성통영CC#1 T/L","154kV 고성-통영복합#1T/L GIS 하자점검 등","154kV 고성-통영복합#1T/L GIS 하자점검 등","2024-10-18 09:30","2024-10-18 18:00","2024-10-18 09:30","2024-10-18 18:00","연속"]
[812,"경남","통영","안정통영CC#2 T/L","154kV 안정-통영복합#2T/L GIS 보통점검 등","154kV 안정-통영복합#2T/L GIS 보통점검 등","2024-10-16 09:30","2024-10-16 18:00","2024-10-16 09:30","2024-10-16 18:00","연속"]
[813,"경남","함안","가야사봉#2 T/L","154kV 가야-사봉#1,2T/L 철탑추락방지장치 설치공사","추락재해 예방을 위한 수평형 철탑추락방지장치 설치공사 (대상개소 : 154kV 가야-사봉#1,2T/L 1~13호)","2024-10-19 07:00","2024-10-20 18:00","취소","취소","매일"]
[814,"경남","함안","가야사봉#1 T/L","154kV 가야-사봉#1,2T/L 철탑추락방지장치 설치공사","추락재해 예방을 위한 수평형 철탑추락방지장치 설치공사 (대상개소 : 154kV 가야-사봉#1,2T/L 1~13호)","2024-10-19 07:00","2024-10-20 18:00","취소","취소","매일"]
[815,"경남","함안","진영수산#1 T/L","154kV 진영-수산#1T/L 철탑 추락방지장치 설치공사","작업자 추락재해 예방을 위한 수평형 철탑추락방지장치 설치공사 (대상개소 : 154kV 진영-수산#1T/L 27호) ※ 대상개소는 154kV 동읍-진영#2T/L 15호에 병가(수직배치)","2024-10-24 12:00","2024-10-24 18:00","2024-10-24 12:00","2024-10-24 18:00","연속"]
[816,"경남","함안","진영수산#2 T/L","154kV 진영-수산#2T/L 철탑 추락방지장치 설치공사","작업자 추락재해 예방을 위한 수평형 철탑추락방지장치 설치공사 (대상개소 : 154kV 진영-수산#2T/L 1~27호) ※ 대상개소는 154kV 동읍-진영#2T/L 15~39호에 병가(수직배치)","2024-10-21 07:00","2024-10-24 12:00","2024-10-21 07:00","2024-10-24 12:00","매일"]
[817,"경남","함안","신마산마산#1 T/L","154kV 신마산-마산#1T/L 철탑추락방지장치 설치공사","154kV 신마산-마산#1T/L 1~44호(44기) 수평형 추락방지장치 설치","2024-10-07 07:00","2024-10-10 18:00","2024-10-07 07:00","2024-10-10 18:00","매일"]
[818,"경남","함안","신마산마산#2 T/L","154kV 신마산-마산#2T/L 철탑추락방지장치 설치공사","154kV 신마산-마산#2T/L 2~8호(7기) 수평형 추락방지장치 설치(6회선 구간)","2024-10-07 07:00","2024-10-07 18:00","2024-10-07 07:00","2024-10-07 18:00","연속"]