{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":6,"n_cols":11,"rows_kept":6,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 11월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신안성신가평 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","765kV 신안성-신가평T/L 항공장애등 설치 : No.131,132,146,147","2024-11-02 07:00","2024-11-02 18:00","취소","취소","연속"]
[2,"경기","성남","신안성S/S #3 M.Tr","2024년 성남전력 변전협력회사 총액공사","-78BAY B/F반 교체 -(병행) C-1 Tank 송유펌프 누유보수","2024-11-18 09:00","2024-11-26 18:00","2024-11-18 09:00","2024-11-26 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":342,"n_cols":11,"rows_kept":342,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2024년도 11월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#2 T/L","24년 성동P/O 변전전문회사 공사","345kV GIS 정밀점검","2024-11-11 10:00","2024-11-15 18:00","취소","취소","연속"]
[2,"서울","성동","성동S/S #2 M.Tr","24년 성동P/O 변전전문회사 공사","345kV M.Tr 정밀점검","2024-11-18 10:00","2024-11-29 18:00","2024-11-18 10:00","2024-11-29 18:00","연속"]
[3,"서울","성동","성동S/S #4 M.Tr","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-11-12 10:00","2024-11-12 18:00","2024-11-12 10:00","2024-11-12 18:00","연속"]
[4,"서울","성동","미금성동#1 T/L","24년 성동P/O 변전협력회사 공사","345kV GIS 보통점검","2024-11-05 10:00","2024-11-06 18:00","2024-11-05 10:00","2024-11-06 18:00","연속"]
[5,"서울","성동","성동S/S #3 M.Tr","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-11-08 10:00","2024-11-08 18:00","2024-11-08 10:00","2024-11-08 18:00","연속"]
[6,"서울","성동","성동S/S #1 M.Tr","24년 성동P/O 변전협력회사 공사","345kV GIS 보통점검, 154kV GIS 조작시험","2024-11-05 10:00","2024-11-06 18:00","2024-11-05 10:00","2024-11-06 18:00","연속"]
[7,"서울","중부","중부S/S #3 M.Tr","중부S/S 154kV 장기사용 GIS 교체공사(4차)","- 154kV GIS 교체(중부용산#2T/L) 관련 시험가압 설비","2024-11-07 17:00","2024-11-08 18:00","2024-11-07 17:00","2024-11-08 18:00","연속"]
[8,"남서울","동서울","곤지암동서울#2 T/L","2024년 가공송전 순시점검 위탁공사","○ 가공송전선로 초기점검 - 세종-포천 지장이설구간 신설 송전설비 초기점검","2024-11-09 13:00","2024-11-09 18:00","2024-11-09 13:00","2024-11-09 18:00","연속"]
[9,"남서울","동서울","동서울S/S #71 BUS","'24~25년도 동서울전력지사 변전협력회사 총액공사","동서울S/S 7A71, 7A00 절연열화값 불량으로 재측정","2024-11-01 09:00","2024-11-01 18:00","2024-11-02 09:00","2024-11-02 18:00","연속"]
[10,"남서울","동서울","동서울S/S SEC CB 75760","345kV 동서울S/S 종합정비공사","○ 500kV 동서울변환소 부지확보 관련 사전정비공사 - 345kV GIS 제어케이블 이설","2024-11-01 09:00","2024-11-29 18:00","2024-11-03 09:00","2024-11-29 18:00","연속"]
[11,"남서울","동서울","곤지암동서울#1 T/L","2024년 가공송전 순시점검 위탁공사","○ 가공송전선로 초기점검 - 세종-포천 지장이설구간 신설 송전설비 초기점검","2024-11-09 08:00","2024-11-09 13:00","2024-11-09 08:00","2024-11-09 13:00","연속"]
[12,"인천","부평","서인천C/C #70 BUS","서인천C/C 345kV #70 BUS 보호반 교체","서인천C/C 345kV #70 BUS 보호반 교체","2024-11-02 09:00","2024-11-05 18:00","취소","취소","연속"]
[13,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S 345kV #3 M.Tr 2차 GIS 보통점검","신가좌S/S 345kV #3 M.Tr 2차 GIS 보통점검","2024-11-02 09:00","2024-11-02 18:00","2024-11-02 09:00","2024-11-02 18:00","연속"]
[14,"인천","부평","신경서인천CC#2 T/L","신경서S/S 신경서인천CC#2T/L CLR TOP HAY 볼트교체","신경서S/S 신경서인천CC#2T/L CLR TOP HAY 볼트교체","2024-11-06 09:00","2024-11-06 18:00","2024-11-06 09:00","2024-11-06 18:00","연속"]
[15,"인천","부평","인천C/C #2 Tie-Tr","인천CC S/Y 345kV #2 TIE Tr 3차측 메커니즘 보강 공사","인천CC S/Y 345kV #2 TIE Tr 3차측 메커니즘 보강 공사","2024-11-04 09:00","2024-11-04 18:00","2024-11-04 09:00","2024-11-04 18:00","연속"]
[16,"인천","부평","인천C/C #1 Tie-Tr","인천CC S/Y 345kV #1 TIE Tr 3차측 메커니즘 보강 공사","인천CC S/Y 345kV #1 TIE Tr 3차측 메커니즘 보강 공사","2024-11-01 09:00","2024-11-01 18:00","2024-11-01 09:00","2024-11-01 18:00","연속"]
[17,"인천","시흥","신시화S/S CB 7300","신시화S/S 362kV GIS 유압조작기 체크밸브 설치","신시화S/S 362kV GIS 유압조작기 체크밸브 설치(7300)","2024-11-11 09:00","2024-11-11 18:00","취소","취소","연속"]
[18,"인천","시흥","신시흥신시화#2 T/L","신시화S/S 345kV #4M.Tr, #2Sh.R 증설공사","신시화S/S 75, 76BAY BF계전기 추가설치 및 시험","2024-11-05 09:00","2024-11-06 18:00","2024-11-05 09:00","2024-11-06 18:00","연속"]
[19,"인천","시흥","신시화S/S #1Sh.R CB","신시화S/S 345kV #4M.Tr, #2Sh.R 증설공사","신시화S/S 75, 76BAY BF계전기 추가설치 및 시험","2024-11-07 09:00","2024-11-08 18:00","2024-11-07 09:00","2024-11-08 18:00","매일"]
[20,"인천","시흥","신시흥신시화#2 T/L","신시화S/S 345kV GIS 설치공사(무부하가압)","345kV #4M.Tr, #2Sh.R용 차단기 설치 - 63kA, 6,300A 차단기 2CB 설치 - GIB 설치 및 기타부대공사","2024-11-09 18:00","2024-11-10 18:00","2024-11-09 18:00","2024-11-10 18:00","연속"]
[21,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥S/S 154kV Sh.R 증설공사","- 154kV Sh.R용 GIS 3Bay 설치 - 345kV #1M.Tr 2차 GIS 이설","2024-11-01 09:00","2024-12-31 18:00","취소","취소","연속"]
[22,"인천","시흥","신시흥영흥TP#1 T/L","24~25년 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 : No.13~26(8기), 113~126 (12기)","2024-11-11 07:30","2024-11-13 18:00","2024-11-11 07:30","2024-11-13 18:00","연속"]
[23,"인천","시흥","신시흥#2S/S #4 M.Tr","신시흥S/S #4M.Tr 2차 GIS 정밀점검","신시흥S/S #4M.Tr 2차 GIS CB 정밀점검","2024-11-15 08:00","2024-11-17 18:00","2024-11-15 08:00","2024-11-17 18:00","연속"]
[24,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥S/S #4S.Tr 초기점검","신시흥S/S #4S.Tr 초기점검 - #4S.Tr VCB 조작시험 병행","2024-11-22 09:00","2024-11-22 18:00","2024-11-22 09:00","2024-11-22 18:00","연속"]
[25,"인천","시흥","신시흥#2S/S #5 M.Tr","신시흥S/S #3S.Tr 대체","신시흥S/S #3S.Tr 대체","2024-11-11 09:00","2024-11-13 18:00","취소","취소","연속"]
[26,"인천","시흥","신시화영흥TP#1 T/L","24~25년 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 : No.13~26(8기), 113~126 (12기)","2024-11-11 07:30","2024-11-13 18:00","2024-11-11 07:30","2024-11-13 18:00","연속"]
[27,"인천","시흥","신시흥영흥TP#2 T/L","24~25년 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 : No.13~26(8기), 113~126 (12기)","2024-11-15 07:30","2024-11-17 18:00","2024-11-15 07:30","2024-11-17 18:00","연속"]
[28,"인천","시흥","신시화영흥TP#2 T/L","24~25년 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 : No.13~26(8기), 113~126 (12기)","2024-11-15 07:30","2024-11-17 18:00","2024-11-15 07:30","2024-11-17 18:00","연속"]
[29,"인천","시흥","영흥T/P CB 7172","영흥S/Y 345kV #71Bay B/F 보호반 대체","영흥S/Y 345kV #71Bay B/F 보호반 대체","2024-11-18 09:00","2024-11-22 18:00","2024-11-18 09:00","2024-11-22 18:00","연속"]
[30,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥S/Y 345kV #71Bay B/F 보호반 대체","영흥S/Y 345kV #71Bay B/F 보호반 대체","2024-11-18 09:00","2024-11-22 18:00","2024-11-18 09:00","2024-11-22 18:00","연속"]
[31,"인천","시흥","영흥T/P CB 7272","영흥S/Y 345kV #72Bay B/F 보호반 대체","영흥S/Y 345kV #72Bay B/F 보호반 대체","2024-11-25 09:00","2024-11-29 18:00","2024-11-25 09:00","2024-11-29 18:00","연속"]
[32,"인천","시흥","영흥1TP영흥2TP#2 T/L","영흥S/Y 345kV #72Bay B/F 보호반 대체","영흥S/Y 345kV #72Bay B/F 보호반 대체","2024-11-25 09:00","2024-11-29 18:00","2024-11-25 09:00","2024-11-29 18:00","연속"]
[33,"인천","직할","갈산S/S #4 M.Tr","갈산S/S 종합예방 증설공사 및 #4M.Tr, 1,2차 GIS초기점검","종합예방진단시스템 MLU,GLU 설치 및 부싱누설전류 진단장치 설치 등 #4M.Tr, 1,2차 GIS(7772, 7700, 6444) 초기점검","2024-11-04 09:00","2024-11-29 18:00","2024-11-04 09:00","2024-11-29 18:00","연속"]
[34,"인천","직할","서인천CC신부평#3 T/L","23~24년 지중송전설비 위탁정비공사","구형 SVL 교체","2024-11-18 08:00","2024-11-22 18:00","취소","취소","연속"]
[35,"인천","직할","서인천CC신부평#2 T/L","23~24년 지중송전설비 위탁정비공사","구형 SVL 교체","2024-11-11 08:00","2024-11-15 17:00","취소","취소","연속"]
[36,"인천","직할","신부평S/S #1 M.Tr","신부평S/S 345kV #1 M.Tr A,B,C상 절연유 여과","신부평S/S 345kV #1 M.Tr A,B,C상 절연유 여과","2024-11-18 09:00","2024-11-21 18:00","2024-11-18 09:00","2024-11-21 18:00","연속"]
[37,"경기북부","고양","신덕은동두천CC#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","-피뢰기설치공사 병가구간","2024-11-25 07:00","2024-11-28 18:00","취소","취소","연속"]
[38,"경기북부","고양","신김포신파주#1 T/L","24~25년 고양전력지사 가공송전 협력회사 총액공사","추락방지장치 설치, 불량애자 교체","2024-11-18 07:00","2024-11-22 18:00","2024-11-18 07:00","2024-11-22 18:00","연속"]
[39,"경기북부","고양","신김포신파주#2 T/L","24~25년 고양전력지사 가공송전 협력회사 총액공사","추락방지장치 설치, 불량애자 교체","2024-11-04 07:00","2024-11-08 18:00","2024-11-04 07:00","2024-11-08 18:00","연속"]
[40,"경기북부","고양","신파주S/S #70 BUS","신파주S/S 장기사용 노후 배전반 교체","신파주S/S 70BUS PRO 보호반 교체","2024-11-04 09:00","2024-11-08 18:00","2024-11-04 09:00","2024-11-08 18:00","연속"]
[41,"경기북부","고양","신파주S/S SEC CB 75760","신파주S/S 장기사용 노후 배전반 교체","신파주S/S SEC B/F 보호반 교체","2024-11-25 09:00","2024-11-29 18:00","2024-11-25 09:00","2024-11-29 18:00","연속"]
[42,"경기북부","고양","신파주S/S #75 BUS","신파주S/S 장기사용 노후 배전반 교체","신파주S/S 75BUS PRO 보호반 교체","2024-11-18 09:00","2024-11-22 18:00","2024-11-18 09:00","2024-11-22 18:00","연속"]
[43,"경기북부","고양","신파주S/S SEC CB 70710","신파주S/S 장기사용 노후 배전반 교체","신파주S/S SEC B/F 보호반 교체","2024-11-25 09:00","2024-11-29 18:00","2024-11-25 09:00","2024-11-29 18:00","연속"]
[44,"경기북부","고양","신파주양주#1 T/L","24~25년 고양전력지사 가공송전 협력회사 총액공사","추락방지장치 설치, 불량애자 교체","2024-11-04 07:00","2024-11-15 18:00","2024-11-04 07:00","2024-11-15 18:00","연속"]
[45,"경기북부","고양","신파주S/S #2 M.Tr","신파주S/S 장기사용 노후 배전반 교체","신파주S/S #2M.Tr 보호반, 73 Bay B/F 보호반 교체","2024-11-10 09:00","2024-11-15 18:00","2024-11-10 09:00","2024-11-15 18:00","연속"]
[46,"경기북부","고양","신파주양주#2 T/L","24~25년 고양전력지사 가공송전 협력회사 총액공사","추락방지장치 설치, 불량애자 교체","2024-11-18 07:00","2024-11-22 18:00","2024-11-18 07:00","2024-11-22 18:00","연속"]
[47,"경기북부","구리","미금S/S #5 Sh.R CB","24-25 구리전력 변전협력 총액공사","345kV Sh.R 보통점검","2024-11-11 09:00","2024-11-11 18:00","2024-11-11 09:00","2024-11-11 18:00","연속"]
[48,"경기북부","구리","신가평포천LNGCC#1 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 무부하가압 선로","2024-11-27 10:00","2024-11-29 18:00","2024-11-27 10:00","2024-11-29 18:00","연속"]
[49,"경기북부","구리","신가평포천LNGCC#2 T/L","765kV 신안성-신가평 등 12개T/L 추락방지 설치공사","신가평-포천LNG#1 추락방지 설치(177기) : No.1~177","2024-11-11 07:00","2024-11-26 18:00","2024-11-11 07:00","2024-11-26 18:00","연속"]
[50,"경기북부","구리","신가평미금#1 T/L","765kV 신안성-신가평 등 12개T/L 추락방지 설치공사","신가평-미금#1 추락방지 설치(90기) : No.1~101","2024-11-06 10:00","2024-11-08 18:00","취소","취소","연속"]
[51,"경기북부","구리","신가평미금#2 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 78bay 측 주모선 설치 안전이격 345kV #7852 DS 설치 안전이격","2024-11-01 08:00","2024-11-06 10:00","2024-11-01 08:00","2024-11-06 10:00","연속"]
[52,"경기북부","구리","포천C/C #1 BUS","2024~25 구리전력 변전협력 총액공사","포천C/C 신포천-포천CC #1T/L 7171 - #1BUS 휴전 후 균압콘덴서 절연열화 재측정","2024-11-11 09:00","2024-11-11 18:00","2024-11-11 09:00","2024-11-11 18:00","연속"]
[53,"경기북부","직할","신포천동두천CC#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신포천-동두천CC#1T/L No.1~5","2024-11-26 07:00","2024-11-26 18:00","2024-11-26 07:00","2024-11-26 18:00","연속"]
[54,"경기북부","직할","신포천동두천CC#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신포천-동두천CC#2T/L No.1~5","2024-11-20 07:00","2024-11-20 18:00","2024-11-20 07:00","2024-11-20 18:00","연속"]
[55,"경기북부","직할","신가평신의정부#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신가평-신의정부#2T/L No.120~134,136,138","2024-11-15 07:00","2024-11-19 18:00","취소","취소","연속"]
[56,"경기북부","직할","신가평신의정부#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신가평-신의정부#1T/L No.120~134,136,138","2024-11-21 07:00","2024-11-25 18:00","취소","취소","연속"]
[57,"경기북부","직할","신의정부양주#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신의정부-양주#2T/L No.1~97","2024-11-26 07:00","2024-12-04 18:00","취소","취소","연속"]
[58,"경기북부","직할","신의정부양주#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신의정부-양주#1T/L No.1~97","2024-11-01 07:00","2024-11-13 18:00","취소","취소","연속"]
[59,"경기","군포","서서울S/S #2 M.Tr","서서울S/S #2M.Tr 3차 VCB 대체 등","서서울S/S #2M.Tr 3차 VCB, #2-1,2 Sh.R VCB 대체 서서울S/S #2M.Tr 3차 PT 대체","2024-11-28 09:00","2024-11-29 18:00","2024-11-28 09:00","2024-11-29 18:00","연속"]
[60,"경기","군포","화성서서울#2 T/L","24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 345kV 화성-서서울#2T/L 62기 186SET","2024-11-10 07:00","2024-11-10 18:00","취소","취소","연속"]
[61,"경기","군포","서서울S/S #4 M.Tr","서서울S/S #4M.Tr 부싱절연유 채유, 추락방지장치 설치","서서울S/S #4M.Tr 부싱절연유 채유, 추락방지장치 설치","2024-11-30 09:00","2024-12-01 18:00","2024-11-30 09:00","2024-12-01 18:00","연속"]
[62,"경기","군포","서서울S/S #3 M.Tr","서서울S/S #3M.Tr 3차 VCB 대체 등","서서울S/S #3M.Tr 3차, #3-2 Sh.R, #2S.Tr VCB 대체 서서울S/S #3M.Tr 3차 PT 대체, 변압기 추락방지장치장치 설치","2024-11-11 09:00","2024-11-13 18:00","2024-11-11 09:00","2024-11-13 18:00","연속"]
[63,"경기","동부","곤지암여주복합#1 T/L","2024-2025년 성남전력지사 가공송전 협력회사공사","소도체 이도조정 곤지암여주복합#1,2 No.63~69, 85~88","2024-11-02 09:00","2024-11-03 18:00","2024-11-02 09:00","2024-11-03 18:00","연속"]
[64,"경기","동부","곤지암여주복합#2 T/L","2024-2025년 성남전력지사 가공송전 협력회사공사","소도체 이도조정 곤지암여주복합#1,2 No.63~69, 85~88","2024-11-09 09:00","2024-11-10 18:00","2024-11-09 09:00","2024-11-10 18:00","연속"]
[65,"경기","동부","여주C/C #1 BUS","24-25년 동부 변전협력총액공사","여주CC:DS 조작 시 surge 유입 조사","2024-11-12 09:00","2024-11-12 18:00","2024-11-12 09:00","2024-11-12 18:00","연속"]
[66,"경기","동부","신제천신충주T#1 T/L","2024-2025년 성남전력지사 가공송전 협력회사공사","345kV 신제천여주복합T/L No.33~34,35~36 가공지선 및 항공구교체","2024-11-16 09:00","2024-11-17 18:00","취소","취소","연속"]
[67,"경기","성남","신성남S/S #2 M.Tr","신성남S/S 154kV #1,2,3,4Sh.R 설치사업","· 기초매트 철근, 거푸집, 방호벽 설치 · 공사 시 활선 안전이격 확보","2024-10-29 16:00","2024-11-29 16:00","2024-11-04 09:00","2024-11-29 16:00","연속"]
[68,"경기","성남","신성남S/S STATCOM CB","2024년 성남전력 변전협력회사 총액공사","냉각설비점검, HMI 교체(제작사)","2024-11-25 09:00","2024-12-06 18:00","2024-11-25 09:00","2024-12-06 18:00","연속"]
[69,"경기","성남","신성남S/S #3 M.Tr","2024년 성남전력 변전협력회사 총액공사","추락방지시설 설치, 부싱절연유 채유","2024-11-02 09:00","2024-11-03 18:00","2024-11-02 09:00","2024-11-03 18:00","연속"]
[70,"경기","성남","신성남S/S #1 M.Tr","신성남S/S 154kV Sh.R 설치공사","#1~4Sh.R 매트 1차 타설 안전이격","2024-11-18 09:00","2024-12-10 09:00","취소","취소","연속"]
[71,"경기","성남","신수원S/S CB 7400","2024년 성남전력 345, 154 GIS 보통점검공사","7400 보통점검, 절연열화","2024-11-05 09:00","2024-11-05 18:00","2024-11-05 09:00","2024-11-05 18:00","연속"]
[72,"경기","성남","신수원S/S CB 7471","2024년 성남전력 345, 154 GIS 보통점검공사","7471 보통점검, 절연열화","2024-11-04 09:00","2024-11-04 18:00","2024-11-04 09:00","2024-11-04 18:00","연속"]
[73,"경기","성남","신수원S/S CB 7372","2024년 성남전력 345, 154 GIS 보통점검공사","7372 보통점검, 절연열화","2024-11-06 09:00","2024-11-06 18:00","2024-11-06 09:00","2024-11-06 18:00","연속"]
[74,"경기","성남","신수원삼성#2 T/L","2024년 성남전력 변전협력회사 총액공사","보호반 대체","2024-11-25 09:00","2024-11-29 18:00","2024-11-25 09:00","2024-11-29 18:00","연속"]
[75,"경기","성남","신수원S/S #4 M.Tr","2024년 성남전력 변전협력회사 총액공사","2차 GIS 보통점검, 1차 LA 하자점검, 부싱절연유 채유","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[76,"경기","성남","신수원S/S #2 M.Tr","2024년 성남전력 변전협력회사 총액공사","방호벽 사다리 철거, 투광등 교체","2024-11-21 09:00","2024-11-21 18:00","2024-11-21 09:00","2024-11-21 18:00","연속"]
[77,"경기","성남","신안성신성남#1 T/L","2024년 성남전력 변전협력회사 총액공사","Line PT 누기보수, 7500, 7572 GIS 절연열화 측정","2024-11-11 09:00","2024-11-13 18:00","2024-11-11 09:00","2024-11-13 18:00","연속"]
[78,"경기","성남","신안성신성남#2 T/L","345kV 신용인-동서울 No.7-1 항공도장작업(고객시행)","345kV 신용인-동서울 No.7-1 항공주간장애표지 탈색에 따른 재도장 - 이천오산고속도로 지장철탑이설공사시 시행한 항공도장 하자발생 보완 - 화성광주고속도로(주) 직접시행(요청자측 부담공사) - 4회선구간(신용인-동서울7-1호, 신성남-동서울 64-1호)","2024-11-15 07:00","2024-11-15 18:00","2024-11-15 07:00","2024-11-15 18:00","연속"]
[79,"경기","성남","신안성신용인#2 T/L","2024년 성남전력 변전협력회사 총액공사","(신안성) 78BAY B/F PNL 대체 [병행](신용인)7571, 7500 보통점검","2024-11-18 09:00","2024-11-26 18:00","2024-11-18 09:00","2024-11-26 18:00","연속"]
[80,"경기","성남","신안성S/S #5 Sh.R CB 7779","2024년 성남전력 변전협력회사 총액공사","7779 GIS 절연열화 재측정","2024-11-28 09:00","2024-11-28 18:00","2024-11-28 09:00","2024-11-28 18:00","연속"]
[81,"경기","성남","신안성신성남#1 T/L","345kV 신용인-동서울 No.7-1 항공도장작업(고객시행)","345kV 신용인-동서울 No.7-1 항공주간장애표지 탈색에 따른 재도장 - 이천오산고속도로 지장철탑이설공사시 시행한 항공도장 하자발생 보완 - 화성광주고속도로(주) 직접시행(요청자측 부담공사) - 4회선구간(신용인-동서울7-1호, 신성남-동서울 64-1호)","2024-11-13 07:00","2024-11-13 18:00","취소","취소","연속"]
[82,"경기","성남","신용인동서울#2 T/L","345kV 신용인-동서울 No.7-1 항공도장작업(고객시행)","345kV 신용인-동서울 No.7-1 항공주간장애표지 탈색에 따른 재도장 - 이천오산고속도로 지장철탑이설공사시 시행한 항공도장 하자발생 보완 - 화성광주고속도로(주) 직접시행(요청자측 부담공사) - 4회선구간(신용인-동서울7-1호, 신성남-동서울 64-1호)","2024-11-15 07:00","2024-11-15 18:00","2024-11-15 07:00","2024-11-15 18:00","연속"]
[83,"경기","성남","신용인동서울#1 T/L","345kV 신용인-동서울 No.7-1 항공도장작업(고객시행)","345kV 신용인-동서울 No.7-1 항공주간장애표지 탈색에 따른 재도장 - 이천오산고속도로 지장철탑이설공사시 시행한 항공도장 하자발생 보완 - 화성광주고속도로(주) 직접시행(요청자측 부담공사) - 4회선구간(신용인-동서울7-1호, 신성남-동서울 64-1호)","2024-11-13 07:00","2024-11-13 18:00","2024-11-13 07:00","2024-11-13 18:00","연속"]
[84,"경기","성남","신용인S/S #1 M.Tr","2024년 성남전력 변전협력회사 총액공사","2차 GIS 조작시험, 3차 VCB 대체, 부싱절연유 채유 등","2024-11-15 09:00","2024-11-16 18:00","2024-11-15 09:00","2024-11-16 18:00","연속"]
[85,"경기","성남","신용인S/S #2 M.Tr","2024년 성남전력 변전협력회사 총액공사","2차 GIS 조작시험, 3차 VCB 대체, 부싱절연유 채유 등","2024-11-18 09:00","2024-11-19 18:00","2024-11-18 09:00","2024-11-19 18:00","연속"]
[86,"경기","성남","신용인S/S #3 M.Tr","2024년 성남전력 변전협력회사 총액공사","방호벽 사다리 철거, 투광등 교체","2024-11-22 09:00","2024-11-22 18:00","2024-11-22 09:00","2024-11-22 18:00","연속"]
[87,"경기","직할","화성신안산#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 7기","2024-11-11 07:00","2024-11-11 18:00","2024-11-11 07:00","2024-11-11 18:00","연속"]
[88,"경기","직할","화성신안산#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 7기","2024-11-12 07:00","2024-11-12 18:00","2024-11-12 07:00","2024-11-12 18:00","연속"]
[89,"경기","직할","화성S/S #3 M.Tr","24년 경기본부 직할 345kV M.Tr 정밀점검","화성: #3M.Tr 정밀점검","2024-11-15 09:00","2024-11-27 18:00","취소","취소","연속"]
[90,"경기","직할","화성신안산#1 T/L","24-25년 군포 가공송전협력회사 공사","345kV 화성-서서울#2T/L 피뢰기 설치공사 병가구간 안전이격거리 확보","2024-11-10 11:00","2024-11-10 17:00","2024-11-10 11:00","2024-11-10 17:00","연속"]
[91,"경기","직할","화성평택TP#1 T/L","24-25년 군포 가공송전협력회사 공사","345kV 화성-서서울#2T/L 피뢰기 설치공사 병가구간 안전이격거리 확보","2024-11-10 07:00","2024-11-10 11:00","2024-11-10 07:00","2024-11-10 11:00","연속"]
[92,"경기","평택","북당진고덕HVDC#1 Pole CB","24-25년 북당진-고덕 변환설비 위탁정비공사","24년도 연차점검 시행(Bi-Pole) - Valve, C.Tr, Filter, DC Hall 등 연차점검 시행","2024-11-04 09:00","2024-11-29 18:00","2024-11-04 09:00","2024-11-29 18:00","연속"]
[93,"경기","평택","북당진고덕HVDC#2 Pole CB","24-25년 북당진-고덕 변환설비 위탁정비공사","24년도 연차점검 시행(Bi-Pole) - Valve, C.Tr, Filter, DC Hall 등 연차점검 시행","2024-11-04 09:00","2024-11-29 18:00","2024-11-04 09:00","2024-11-29 18:00","연속"]
[94,"경기","평택","고덕S/S STATCOM CB","고덕S/S 345kV STATCOM 보통점검","고덕S/S 345kV STATCOM 보통점검","2024-11-04 09:00","2024-11-29 18:00","2024-11-04 09:00","2024-11-29 18:00","연속"]
[95,"경기","평택","고덕S/S #1 M.Tr","24년 평택전력지사 변전협력회사 총액공사","고덕S/S 345kV #1M.Tr 변압기 유압펌프 교체","2024-11-04 09:00","2024-11-06 18:00","2024-11-04 09:00","2024-11-06 18:00","연속"]
[96,"경기","평택","고덕S/S #3 M.Tr","24년 평택전력지사 변전협력회사 총액공사","고덕S/S 345kV #3M.Tr 변압기 유압펌프 교체","2024-11-11 09:00","2024-11-13 18:00","2024-11-11 09:00","2024-11-13 18:00","연속"]
[97,"경기","평택","서안성S/S #3 M.Tr","24년도 평택전력 변전협력회사 총액공사","서안성S/S #3M.Tr 부싱절연유 채유","2024-11-01 09:00","2024-11-01 13:00","2024-11-01 09:00","2024-11-01 13:00","연속"]
[98,"경기","평택","서안성S/S #4 M.Tr","서안성S/S #4M.Tr 사다리 등받이울 시공","서안성S/S #4M.Tr 사다리 등받이울 시공","2024-11-01 13:00","2024-11-01 18:00","2024-11-01 13:00","2024-11-01 18:00","연속"]
[99,"경기","동부","여주C/C CB 7472","24-25년 동부 변전협력총액공사","여주CC:7472(조작함 히터 설치)","2024-11-04 09:00","2024-11-04 18:00","2024-11-04 09:00","2024-11-04 18:00","연속"]
[100,"경기","동부","여주C/C CB 7271","24-25년 동부 변전협력총액공사","여주CC:7271,7200(조작함 히터 설치)(신충주-여주복합#2TL)","2024-11-06 09:00","2024-11-06 14:00","2024-11-06 09:00","2024-11-06 14:00","연속"]
[101,"경기","동부","여주C/C CB 7200","24-25년 동부 변전협력총액공사","여주CC:7271,7200(조작함 히터 설치)(신충주-여주복합#2TL)","2024-11-06 14:00","2024-11-06 18:00","2024-11-06 14:00","2024-11-06 18:00","연속"]
[102,"경기","동부","여주C/C CB 7372","24-25년 동부 변전협력총액공사","여주CC:7272,7372(조작함 히터 설치)(#2,3STEP-UP TR)","2024-11-08 09:00","2024-11-08 14:00","2024-11-08 09:00","2024-11-08 14:00","연속"]
[103,"경기","동부","여주C/C CB 7272","24-25년 동부 변전협력총액공사","여주CC:7272,7372(조작함 히터 설치)(#2,3STEP-UP TR)","2024-11-08 14:00","2024-11-08 18:00","2024-11-08 14:00","2024-11-08 18:00","연속"]
[104,"강원","강릉","강릉T/P CB 7272","2024년 강릉전력지사 변전협력회사 공사","362kV GIS 하자점검","2024-11-08 14:00","2024-11-08 18:00","2024-11-08 14:00","2024-11-08 18:00","연속"]
[105,"강원","강릉","강릉T/P CB 7200","2024년 강릉전력지사 변전협력회사 공사","362kV GIS 하자점검","2024-11-08 10:00","2024-11-08 14:00","2024-11-08 10:00","2024-11-08 14:00","연속"]
[106,"강원","강릉","신양양S/S CB 7171","2024년 강릉전력지사 변전협력회사 공사","균압콘덴서 재점검","2024-11-01 10:00","2024-11-01 18:00","취소","취소","연속"]
[107,"강원","강릉","신양양S/S #1 BUS","2024년 강릉전력지사 변전협력회사 공사","균압콘덴서 재점검","2024-11-01 10:00","2024-11-01 18:00","2024-11-01 10:00","2024-11-01 18:00","연속"]
[108,"강원","강릉","안인개폐소양양PP T/L","2024-2025년 강릉전력지사 송전협력회사 공사","○ 수평 추락방지장치 설치 : 345kV 양양양수T/L No.35 등","2024-11-04 08:00","2024-11-22 18:00","2024-11-04 08:00","2024-11-22 18:00","매일"]
[109,"강원","동해","동해S/S #2 M.Tr","2024~25년 동해전력지사 변전협력회사 공사","부싱 절연유 채유","2024-11-01 09:00","2024-11-01 18:00","2024-11-01 09:00","2024-11-01 18:00","연속"]
[110,"강원","동해","동해S/S CB 7271","2024~25년 동해전력지사 변전협력회사 공사","7271CB 차단기조작시험","2024-11-07 09:00","2024-11-07 17:00","2024-11-07 09:00","2024-11-07 17:00","연속"]
[111,"강원","동해","동해S/S #3 M.Tr","2024~25년 동해전력지사 변전협력회사 공사","부싱 절연유 채유","2024-11-08 09:00","2024-11-08 18:00","2024-11-08 09:00","2024-11-08 18:00","연속"]
[112,"강원","동해","동해S/S CB 7200","2024~25년 동해전력지사 변전협력회사 공사","7200CB 차단기조작시험","2024-11-08 09:00","2024-11-08 14:00","2024-11-08 09:00","2024-11-08 14:00","연속"]
[113,"강원","동해","동해S/S CB 7671","2024~25년 동해전력지사 변전협력회사 공사","7671CB 차단기조작시험","2024-11-21 09:00","2024-11-21 12:00","2024-11-21 09:00","2024-11-21 12:00","연속"]
[114,"강원","동해","동해S/S CB 7772","2024년 동해STATCOM 점검공사","STATCOM 점검","2024-11-18 09:00","2024-11-27 18:00","취소","취소","연속"]
[115,"강원","동해","동해S/S CB 7300","2024~25년 동해전력지사 변전협력회사 공사","7300CB 차단기조작시험","2024-11-08 13:00","2024-11-08 18:00","2024-11-08 13:00","2024-11-08 18:00","연속"]
[116,"강원","동해","동해S/S CB 7371","2024~25년 동해전력지사 변전협력회사 공사","7371CB 차단기조작시험","2024-11-21 13:00","2024-11-21 17:00","2024-11-21 13:00","2024-11-21 17:00","연속"]
[117,"강원","동해","동해S/S CB 7172","2024~25년 동해전력지사 변전협력회사 공사","7172CB 차단기조작시험","2024-11-27 09:00","2024-11-27 12:00","2024-11-27 09:00","2024-11-27 12:00","연속"]
[118,"강원","동해","동해S/S CB 7100","2024~25년 동해전력지사 변전협력회사 공사","7100CB 차단기조작시험","2024-11-27 13:00","2024-11-27 17:00","2024-11-27 13:00","2024-11-27 17:00","연속"]
[119,"강원","동해","동해S/S CB 7500","2024~25년 동해전력지사 변전협력회사 공사","7500CB 차단기조작시험","2024-11-28 09:00","2024-11-28 12:00","2024-11-28 09:00","2024-11-28 12:00","연속"]
[120,"강원","동해","삼척G/P CB 7700","2024~25년 동해전력지사 변전협력회사 공사","7700CB 차단기조작시험","2024-11-26 13:00","2024-11-26 17:00","2024-11-26 13:00","2024-11-26 17:00","연속"]
[121,"강원","동해","삼척G/P CB 7600","2024~25년 동해전력지사 변전협력회사 공사","7600CB 차단기조작시험","2024-11-26 09:00","2024-11-26 12:00","2024-11-26 09:00","2024-11-26 12:00","연속"]
[122,"강원","동해","삼척G/P #2 Tie-Tr","삼척GP 주변압기 점검공사","주변압기 보통점검","2024-11-11 09:00","2024-11-13 18:00","2024-11-11 09:00","2024-11-13 18:00","연속"]
[123,"강원","동해","삼척G/P #3 Tie-Tr","삼척GP 주변압기 점검공사","주변압기 정밀점검","2024-11-18 09:00","2024-11-22 18:00","2024-11-18 09:00","2024-11-22 18:00","연속"]
[124,"강원","태백","신태백한울NP#1 T/L","2024~2025년 태백전력지사 송전 협력회사 공사","345kV 신태백-한울NP2T/L 수평추락방지장치 설치","2024-11-25 08:00","2024-11-29 18:00","2024-11-25 08:00","2024-11-29 18:00","매일"]
[125,"충북","직할","신중부남청주#1 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-11-04 07:00","2024-11-08 18:00","2024-11-04 07:00","2024-11-08 18:00","연속"]
[126,"충북","직할","신중부남청주#2 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-11-11 07:00","2024-11-16 18:00","2024-11-11 07:00","2024-11-16 18:00","연속"]
[127,"충북","직할","신중부남청주#2 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-11-25 07:00","2024-11-29 18:00","2024-11-25 07:00","2024-11-29 18:00","연속"]
[128,"충북","직할","신중부남청주#1 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-11-18 07:00","2024-11-22 18:00","2024-11-18 07:00","2024-11-22 18:00","연속"]
[129,"충북","직할","서안성신진천#2 T/L","2024년 가공송전선로 순시점검 위탁공사(초기점검)","345kV 서안성-신진천 No.2~5 초기점검","2024-11-06 08:00","2024-11-06 18:00","2024-11-06 08:00","2024-11-06 18:00","연속"]
[130,"충북","직할","서안성신진천#1 T/L","2024년 가공송전선로 순시점검 위탁공사(초기점검)","345kV 서안성-신진천 No.2~5 초기점검","2024-11-05 08:00","2024-11-05 18:00","2024-11-05 08:00","2024-11-05 18:00","연속"]
[131,"충북","직할","신진천S/S #3 M.Tr","신진천S/S 345kV GIS DS(7602) 점검","신진천S/S 345kV GIS DS(7602) 조작 불량에 따른 제작사 점검","2024-11-04 09:00","2024-11-04 18:00","2024-11-04 09:00","2024-11-04 18:00","연속"]
[132,"충북","청주","남청주S/S #2 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-11-30 08:00","2024-12-18 18:00","2024-11-30 08:00","2024-12-18 18:00","연속"]
[133,"충북","청주","신옥천S/S CB 7372","2024~2025년 청주전력지사 변전협력회사 공사","345kV GIS 보통점검","2024-11-05 08:00","2024-11-05 18:00","2024-11-05 08:00","2024-11-05 18:00","연속"]
[134,"충북","청주","신옥천S/S CB 7272","2024~2025년 청주전력지사 변전협력회사 공사","345kV GIS 보통점검","2024-11-04 08:00","2024-11-04 18:00","2024-11-04 08:00","2024-11-04 18:00","연속"]
[135,"충북","청주","신옥천S/S CB 7300","2024~2025년 청주전력지사 변전협력회사 공사","345kV GIS 보통점검","2024-11-06 08:00","2024-11-06 18:00","2024-11-06 08:00","2024-11-06 18:00","연속"]
[136,"충북","청주","신옥천세종#2 T/L","345kV 신옥천-북경남등 8개T/L 추락방지장치 설치공사","공사개요 : 신옥천세종#2T/L 추락방지장치 수평설치 공사장소 : 신옥천세종#2T/L No.1~48(55기) ※ 주말 휴전 제외","2024-11-25 07:00","2024-11-29 18:00","취소","취소","매일"]
[137,"충북","청주","신옥천세종#1 T/L","345kV 신옥천북경남 등 8개T/L 추락방지장치 설치공사","공사개요 : 신옥천세종#1T/L 추락방지장치 수평설치 공사장소 : 신옥천세종#1T/L No.1~48(55기) ※ 주말 휴전 제외","2024-10-31 07:00","2024-11-08 18:00","취소","취소","매일"]
[138,"충북","충주","신제천신영주#2 T/L","345kV 신제천-신영주T/L No.55 취약철탑 교체공사","철탑교체 (신설1기, 철거2기)","2024-11-20 07:00","2024-12-05 16:00","2024-11-20 07:00","2024-12-05 16:00","연속"]
[139,"충북","충주","신제천신영주#1 T/L","345kV 신제천-신영주T/L No.55 취약철탑 교체공사","철탑교체 (신설1기, 철거2기)","2024-11-15 07:00","2024-11-19 16:00","2024-11-15 07:00","2024-11-19 16:00","연속"]
[140,"충북","충주","신충주T신충주 T/L","2024-2025년 성남전력지사 가공송전 협력회사공사","345kV 신제천여주복합T/L No.33~34,35~36 가공지선 및 항공구교체 (병행휴전) 신충주T분기T/L","2024-11-22 09:00","2024-11-24 18:00","2024-11-22 09:00","2024-11-24 18:00","연속"]
[141,"대전세종충남","대전","신계룡S/S CB 7272","[즉시가압O] 신계룡S/S 345kV GIS 차단기 부동작 시험","신계룡S/S 345kV #1 M.Tr 1차 GIS 차단기 부동작 시험","2024-11-18 15:00","2024-11-18 18:00","2024-11-18 15:00","2024-11-18 18:00","연속"]
[142,"대전세종충남","대전","신계룡S/S CB 7600","[즉시가압O]신계룡S/S #3 M.Tr 1차 TIE CB 부동작 시험","신계룡S/S 345kV #3 M.Tr 1차 TIE CB 부동작 시험","2024-11-18 09:00","2024-11-18 13:00","2024-11-18 09:00","2024-11-18 13:00","연속"]
[143,"대전세종충남","대전","신계룡S/S CB 7200","[가압O]신계룡S/S 345kV GIS 차단기 부동작 시험","[즉시가압O]신계룡S/S 신옥천-신계룡T/L-#1 M.Tr 1차 TIE GIS 차단기 부동작 시험","2024-11-18 13:00","2024-11-18 15:00","2024-11-18 13:00","2024-11-18 15:00","연속"]
[144,"대전세종충남","서산","당진T/P CB 7271","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 당진화력S/S 345kV 7271 GIS 보통점검공사","2024-11-18 09:30","2024-11-19 18:00","2024-11-18 09:30","2024-11-19 18:00","연속"]
[145,"대전세종충남","서산","당진T/P #71 Tie-Tr","24년 서산P/O 변전협력회사 총액공사","(10월 휴전 취소시) (즉시가압가능)당진화력S/S 345kV #71 Tie.Tr 염해지역 애자코팅 - 병행1 : #71Tie-Tr 1, 2차 LA 초기점검 - 병행2 : #71Tie-Tr 부싱절연유 채유 및 절연열화 진단","2024-11-18 09:30","2024-11-19 18:00","취소","취소","연속"]
[146,"대전세종충남","서산","당진T/P CB 7172","'24년 서산전력지사 변전협력회사 총액공사","(즉시가압가능) 당진화력S/S 345kV 7172 CB 균압콘덴서 절연열화 측정","2024-11-07 09:30","2024-11-07 12:30","취소","취소","연속"]
[147,"대전세종충남","서산","북당진S/S CB 7500","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 북당진S/S 345kV 7500CB A,B,C상 조작유 누유점검","2024-11-04 09:30","2024-11-04 18:00","2024-11-04 09:30","2024-11-04 18:00","연속"]
[148,"대전세종충남","서산","신당진개폐소 CB 7D71","'24년 서산전력지사 변전협력회사 총액공사","(즉시가압가능) 신당진개폐소 345kV 7C72, 7D71 CB 균압콘덴서 절연열화 측정","2024-11-15 12:30","2024-11-15 15:00","2024-11-15 12:30","2024-11-15 15:00","연속"]
[149,"대전세종충남","서산","신당진개폐소북당진 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","(10월 휴전 취소시)수평 추락방지장치 설치공사 (No.49~65) , 즉시가압(20분 이내) 가능","2024-11-18 08:00","2024-11-19 18:00","2024-11-18 08:00","2024-11-19 18:00","매일"]
[150,"대전세종충남","서산","신당진개폐소현대제철 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.1~44) , 즉시가압(20분 이내) 가능","2024-11-11 08:00","2024-11-15 18:00","2024-11-11 08:00","2024-11-15 18:00","매일"]
[151,"대전세종충남","서산","신당진개폐소 CB 7C72","'24년 서산전력지사 변전협력회사 총액공사","(즉시가압가능) 신당진개폐소 345kV 7C72, 7D71 CB 균압콘덴서 절연열화 측정","2024-11-15 09:30","2024-11-15 12:00","2024-11-15 09:30","2024-11-15 12:00","연속"]
[152,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","345kV 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) *345kV 신당진개폐소-현대제철T/L 병가선로, 345kV 신당진개폐소-현대제철T/L 휴전 미승인시 휴전 취소 요청","2024-11-11 08:00","2024-11-12 18:00","2024-11-11 08:00","2024-11-12 18:00","매일"]
[153,"대전세종충남","서산","신당진S/S CB 7400","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신당진S/S 345kV 7400 GIS 보통점검공사","2024-11-27 09:30","2024-11-28 18:00","2024-11-27 09:30","2024-11-28 18:00","연속"]
[154,"대전세종충남","서산","신당진S/S CB 7772","24년 서산P/O 345kV GIS 정밀점검공사","(10월 휴전 취소시) (즉시가압 불가) 신당진S/S 345kV 7772 CB 정밀점검","2024-11-25 09:30","2024-11-29 18:00","취소","취소","연속"]
[155,"대전세종충남","서산","신당진S/S SEC CB 75760","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신당진S/S 345kV 75-76-0 GIS 보통점검공사","2024-11-25 09:30","2024-11-26 18:00","2024-11-25 09:30","2024-11-26 18:00","연속"]
[156,"대전세종충남","서산","신당진S/S #1 M.Tr","'24년 서산전력지사 변전협력회사 총액공사","(즉시가압 불가) 신당진S/S 345kV #1M.Tr 부싱절연유 채유, 부싱절연열화진단","2024-11-08 10:00","2024-11-08 18:00","2024-11-08 10:00","2024-11-08 18:00","연속"]
[157,"대전세종충남","서산","신당진S/S CB 7171","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 신당진S/S 345kV 7171 GIS 보통점검공사","2024-11-20 09:30","2024-11-21 18:00","2024-11-20 09:30","2024-11-21 18:00","연속"]
[158,"대전세종충남","서산","신서산S/S CB 7671","24년 서산P/O 345kV GIS 정밀점검공사","(10월 휴전 취소시) (즉시가압 불가) 신서산S/S 345kV 7671 CB 정밀점검","2024-11-11 09:30","2024-11-15 18:00","취소","취소","연속"]
[159,"대전세종충남","서산","신서산S/S #1 BUS","'24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 345kV 차단기 균압콘덴서 절연열화 UST 모드 재측정 - 7871","2024-11-26 09:00","2024-11-26 18:00","2024-11-26 09:00","2024-11-26 18:00","연속"]
[160,"대전세종충남","서산","신서산태안TP#2 T/L","'24~'25년 서산전력지사 송전협력회사 공사","345kV 신서산-태안화력#2T/L 항공구 설치공사 No.16~19, 21~22, 39~40, 56~62, 70~72, 107~108, 123~124, 131~132 (16경간) *즉시가압가능(20분이내) *10월 휴전 승인시 취소 요청","2024-11-04 08:00","2024-11-08 18:00","취소","취소","매일"]
[161,"대전세종충남","서산","신서산S/S #4 Sh.R CB","'23년 서산P/O 장기사용 배전반 교체공사","(즉시가압불가) 신서산S/S 345kV 77Bay B/F PNL 교체 - 345kV 신서산-신당진#2T/L, 신서산S/S 345kV #4Sh.R 휴전 필요","2024-11-11 09:00","2024-11-15 18:00","취소","취소","연속"]
[162,"대전세종충남","서산","신서산S/S #2 BUS","'24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 345kV 차단기 균압콘덴서 절연열화 UST 모드 재측정 - 7672, 7A72, 7572","2024-11-25 09:00","2024-11-25 18:00","2024-11-25 09:00","2024-11-25 18:00","연속"]
[163,"대전세종충남","서산","신서산신당진#2 T/L","'23년 서산P/O 장기사용 배전반 교체공사","(즉시가압불가) 신서산S/S 345kV 77Bay B/F PNL 교체 - 345kV 신서산-신당진#2T/L, 신서산S/S 345kV #4Sh.R 휴전 필요","2024-11-11 09:00","2024-11-15 18:00","취소","취소","연속"]
[164,"대전세종충남","서산","신서산S/S CB 7972","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신서산S/S 345kV 7972 CB 정밀점검","2024-11-04 09:30","2024-11-08 18:00","2024-11-04 09:30","2024-11-08 18:00","연속"]
[165,"대전세종충남","서산","신서산S/S #5 Sh.R CB","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신서산S/S 345kV 7979 CB 정밀점검 - 병행 : #5Sh.R 과진동 관련 GIB 분해 및 재조립","2024-11-18 09:30","2024-11-22 18:00","취소","취소","연속"]
[166,"대전세종충남","서산","태안T/P CB 7972","'24년 서산전력지사 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7572, 7871, 7972 CB 균압콘덴서 절연열화 측정","2024-11-20 15:30","2024-11-20 18:00","2024-11-20 15:30","2024-11-20 18:00","연속"]
[167,"대전세종충남","서산","태안T/P CB 7871","'24년 서산전력지사 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7572, 7871, 7972 CB 균압콘덴서 절연열화 측정","2024-11-20 13:00","2024-11-20 15:30","2024-11-20 13:00","2024-11-20 15:30","연속"]
[168,"대전세종충남","서산","태안T/P SEC CB 76770","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 태안화력S/S 345kV 76-77-0 SEC GIS 보통점검공사","2024-11-04 09:30","2024-11-05 18:00","취소","취소","연속"]
[169,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","'24~'25년도 송전협력회사 공사","항공구 교체공사 No.88~90(2경간) *20분 이내 즉시가압 불가 *345kV 신서산-태안화력#1T/L 휴전 우선 *345kV 신서산-태안화력#1T/L 휴전취소시 해당선로 휴전 취소요청(병가)","2024-11-13 07:30","2024-11-14 18:00","취소","취소","매일"]
[170,"대전세종충남","서산","신서산태안TP#1 T/L","'24~'25년도 송전협력회사 공사","항공구 교체공사 No.70~72(2경간) *즉시가압 불가 *345kV 신당진개폐소-태안화력#1T/L 보다 휴전 우선(병행작업존재)","2024-11-13 07:30","2024-11-14 18:00","2024-11-13 07:30","2024-11-14 18:00","연속"]
[171,"대전세종충남","서산","태안T/P #1 Tie-Tr","태안화력S/S 154kV 차단기 조작시험","태안화력S/S #1M.Tr 2차 6144 CB 조작시험","2024-11-12 10:00","2024-11-12 18:00","취소","취소","연속"]
[172,"대전세종충남","서산","태안T/P CB 7100","'24년 서산전력지사 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7100, 7172 CB 균압콘덴서 절연열화 측정","2024-11-05 09:30","2024-11-05 12:00","2024-11-05 09:30","2024-11-05 12:00","연속"]
[173,"대전세종충남","서산","태안T/P CB 7172","'24년 서산전력지사 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7100, 7172 CB 균압콘덴서 절연열화 측정","2024-11-05 13:00","2024-11-05 15:30","2024-11-05 13:00","2024-11-05 15:30","연속"]
[174,"대전세종충남","서산","태안T/P SEC CB 75760","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 태안화력S/S 345kV 75-76-0 SEC GIS 보통점검공사","2024-11-11 09:30","2024-11-12 18:00","2024-11-11 09:30","2024-11-12 18:00","연속"]
[175,"대전세종충남","서산","태안T/P CB 7572","'24년 서산전력지사 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV 7572, 7871, 7972 CB 균압콘덴서 절연열화 측정","2024-11-20 09:30","2024-11-20 12:00","2024-11-20 09:30","2024-11-20 12:00","연속"]
[176,"대전세종충남","서산","태안T/P SEC CB 70710","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압 가능) 태안화력S/S 345kV 70-71-0 SEC GIS 보통점검공사","2024-11-06 09:30","2024-11-07 18:00","2024-11-06 09:30","2024-11-07 18:00","연속"]
[177,"대전세종충남","천안","신온양신탕정#1 T/L","신온양,신탕정S/S 345kV 신온양-신탕정#1T/L 노후 보호반 대체","(10월취소시)(즉시가압불가)신온양,신탕정S/S 345kV 신온양-신탕정#1T/L 노후 보호반 대체","2024-11-05 09:00","2024-11-08 18:00","취소","취소","연속"]
[178,"대전세종충남","천안","신온양S/S CB 7400","신온양S/S 345kV 7400 GIS 보통점검","(즉시가압 가능)신온양S/S 345kV 7400 GIS 보통점검","2024-11-15 09:00","2024-11-15 18:00","2024-11-15 09:00","2024-11-15 18:00","연속"]
[179,"대전세종충남","천안","신온양S/S CB 7472","신온양S/S 345kV 7472 GIS 보통점검","(즉시가압 가능)신온양S/S 345kV 7472 GIS 보통점검","2024-11-14 09:00","2024-11-14 18:00","2024-11-14 09:00","2024-11-14 18:00","연속"]
[180,"대전세종충남","천안","신온양서서울#1 T/L","신온양S/S 345kV 78Bay B/F PNL 대체","(10월취소시)(즉시가압불가)신온양S/S 345kV 78Bay B/F PNL 대체","2024-11-19 09:00","2024-11-22 18:00","취소","취소","연속"]
[181,"대전세종충남","천안","신온양신탕정#2 T/L","신온양S/S 345kV 78Bay B/F PNL 대체","(10월취소시)(즉시가압불가)신온양S/S 345kV 78Bay B/F PNL 대체","2024-11-19 09:00","2024-11-22 18:00","취소","취소","연속"]
[182,"대전세종충남","천안","신온양서서울#1 T/L","345kV 신온양-서서울T/L 추락방지장치 설치공사","[즉시가압가능]345kV 신온양-서서울T/L #T/L No. 1 ~ 25 추락방지장치 설치","2024-11-19 07:00","2024-11-21 18:00","취소","취소","매일"]
[183,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S 345kV 77Bay B/F PNL 대체","(10월취소시)(즉시가압불가)신온양S/S 345kV 77Bay B/F PNL 대체","2024-11-26 09:00","2024-11-29 18:00","취소","취소","연속"]
[184,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S 345kV 77Bay B/F PNL 대체","(10월취소시)(즉시가압불가)신온양S/S 345kV 77Bay B/F PNL 대체","2024-11-26 09:00","2024-11-29 18:00","취소","취소","연속"]
[185,"대전세종충남","천안","신탕정S/S #1 M.Tr","신탕정S/S 345kV #1M.Tr 노후 보호배전반 대체","(10월취소시)(즉시가압불가)신탕정S/S 345kV #1M.Tr 노후 보호배전반 대체","2024-11-11 09:00","2024-11-15 18:00","취소","취소","연속"]
[186,"대전세종충남","천안","아산보령TP#2 T/L","[즉시가압O][전일작업불가시 10:00~16:00제외]항공구 설치공사","[10월취소시][즉시가압가능][전일작업불가시 10:00~16:00제외] 345kV 아산-보령화력T/L No.123~124 등 12경간 항공구 설치 [병행] 항공장애표시구 정비 No.187~188 [병행] 조류착지방지장치 설치","2024-11-06 06:00","2024-11-08 19:00","2024-11-06 06:00","2024-11-08 19:00","매일"]
[187,"대전세종충남","천안","신서산아산#1 T/L","345kV 신서산-아산T/L 추락방지장치 설치공사","[즉시가압가능,주말작업없음]345kV 신서산-아산T/L No. 74 ~ 123 추락방지장치 설치 [병가철탑](상단)신서산-아산#1 No.74~113,(하단)아산-합덕#1 No.13~52","2024-11-01 07:00","2024-11-08 18:00","취소","취소","매일"]
[188,"대전세종충남","천안","아산보령TP#1 T/L","[즉시가압O][전일작업불가시 10:00~16:00제외]항공구 설치공사","[10월취소시][즉시가압가능][전일작업불가시 10:00~16:00제외] 345kV 아산-보령화력T/L No.123~124 등 12경간 항공구 설치 [병행] 항공장애표시구 정비 No.187~188 [병행] 조류착지방지장치 설치","2024-11-01 06:00","2024-11-05 19:00","2024-11-01 06:00","2024-11-05 19:00","매일"]
[189,"대전세종충남","천안","아산화성#2 T/L","[즉시가압O]345kV 아산-화성T/L 추락방지장치 설치공사","[즉시가압O]345kV 아산-화성#1T/L No.25,26호 [병행]항공구설치공사 No.5~6 등 3경간","2024-11-28 07:00","2024-11-29 18:00","취소","취소","매일"]
[190,"대전세종충남","천안","아산화성#1 T/L","[즉시가압O]345kV 아산-화성T/L 추락방지장치 설치공사","[즉시가압O]345kV 아산-화성#1T/L No.25,26호 [병행]항공구설치공사 No.5~6 등 3경간","2024-11-26 07:00","2024-11-27 18:00","취소","취소","매일"]
[191,"대전세종충남","청양","보령TP보령CC#1 T/L","345kV LA,PT GIS 내장화(보령T/P 보령연락#1)","345kV LA,PT GIS 내장화(보령T/P 보령연락#1) (즉시가압불가)","2024-11-25 09:00","2024-12-06 18:00","취소","취소","연속"]
[192,"대전세종충남","청양","보령TP보령CC#1 T/L","청양P/O 변전협력 총액공사(화력 LA)","345kV 청양-보령화력#2T/L - 청양S/S LA A,B,C상 보통점검 (즉시가압 가능)","2024-11-26 09:00","2024-11-26 12:00","2024-11-26 09:00","2024-11-26 12:00","연속"]
[193,"대전세종충남","청양","청양군산#1 T/L","[송전]345kV 청양군산#1T/L 가공지선 교체","No.131~137, 162~165 가공지선 교체","2024-11-23 08:00","2024-11-28 18:00","취소","취소","연속"]
[194,"대전세종충남","청양","청양신탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-11-18 08:00","2024-11-22 18:00","2024-11-18 08:00","2024-11-22 18:00","연속"]
[195,"대전세종충남","청양","신온양청양#1 T/L CB","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-11-18 08:00","2024-11-22 18:00","2024-11-18 08:00","2024-11-22 18:00","연속"]
[196,"대전세종충남","청양","청양군산#2 T/L","[송전]345KV 청양군산#2T/L 애자련 보강","345KV 청양군산#1T/L 애자련 보강","2024-11-29 08:00","2024-12-03 18:00","취소","취소","연속"]
[197,"대전세종충남","청양","청양보령TP#2 T/L","청양P/O 변전협력 총액공사(청양 PT)","345kV 청양-보령화력#2T/L - 청양S/S PT C상 (즉시가압 가능)","2024-11-04 09:00","2024-11-04 10:30","취소","취소","연속"]
[198,"대전세종충남","청양","신온양청양#2 T/L CB","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-11-11 08:00","2024-11-12 18:00","2024-11-11 08:00","2024-11-12 18:00","연속"]
[199,"대전세종충남","청양","청양신탕정#2 T/L","345kV 북당진-신탕정T/L 건설공사","345kV 북당진-신탕정T/L 최초가압전 선로정비 ㅇ정비대상 : 345kV 청양-신탕정T/L → 345kV 청양-신온양T/L 원복","2024-11-11 08:00","2024-11-22 18:00","2024-11-11 08:00","2024-11-22 18:00","연속"]
[200,"전북","군산","군산S/S #4 M.Tr","군산S/S #4M.Tr 노후배전반 대체공사","군산S/S #4M.Tr 노후배전반 대체공사 -(병행) 부싱유채유, 추락방지장치설치, 소내반대체, 차단기 조작시험, LA점검","2024-11-04 09:00","2024-11-08 18:00","2024-11-18 09:00","2024-11-23 18:00","연속"]
[201,"전북","군산","군산S/S #3 M.Tr","군산S/S #3M.Tr 주변압기 정밀점검공사","군산S/S #3M.Tr 주변압기 정밀점검공사","2024-11-18 09:00","2024-12-01 18:00","2024-11-25 09:00","2024-12-08 118:00","연속"]
[202,"전북","군산","새만금S/S #3 M.Tr","새만금S/S #3M.Tr 2차 부싱 점검공사","2차 부싱 누설전류 과다에 따른 점검","2024-11-13 09:00","2024-11-14 18:00","2024-11-13 09:00","2024-11-14 18:00","연속"]
[203,"전북","김제","군산신김제#2 T/L","김제전력지사 기타설비 점검공사","김제전력지사 기타설비 점검공사","2024-11-14 09:00","2024-11-14 18:00","취소","취소","연속"]
[204,"전북","직할","신옥천신남원#2 T/L","'24년 가공송전 순시점검 위탁공사","섬락애자 교체","2024-11-06 09:00","2024-11-06 18:00","취소","취소","연속"]
[205,"전북","직할","신남원광양#1 T/L","345kV 신남원-광양#1T/L CVT C상 교체","345kV 신남원-광양#1T/L CVT C상 교체","2024-11-05 09:00","2024-11-05 18:00","2024-11-05 09:00","2024-11-05 18:00","연속"]
[206,"광주전남","강진","신화순신강진#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","가이드레일형 추락방지장치 설치","2024-11-27 07:00","2024-11-27 18:00","2024-11-27 07:00","2024-11-27 18:00","매일"]
[207,"광주전남","강진","신화순신강진#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","가이드레일형 추락방지장치 설치","2024-11-28 07:00","2024-11-28 18:00","2024-11-28 07:00","2024-11-28 18:00","매일"]
[208,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체","2024-11-18 08:00","2024-11-22 18:00","취소","취소","연속"]
[209,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2024-11-11 08:00","2024-11-15 18:00","취소","취소","연속"]
[210,"광주전남","광주","신남원신광주#1 T/L","24년 광주전력지사 변전협력회사 총액공사","신광주S/S 신남원-신광주 #1T/L LA(A,B,C상) 및 CVT 보통점검","2024-11-11 09:00","2024-11-11 18:00","2024-11-11 09:00","2024-11-11 18:00","연속"]
[211,"광주전남","광주","신남원신광주#1 T/L","345kV 신광주S/S #2M.Tr 교체공사","- 신광주S/S #2M.Tr 교체 무부하가압용","2024-11-18 08:00","2024-11-19 18:00","2024-11-18 08:00","2024-11-19 18:00","연속"]
[212,"광주전남","광주","신남원신광주#2 T/L","24년 광주전력지사 변전협력회사 총액공사","신광주S/S 신남원-신광주 #2T/L LA(A,B,C상) 보통점검 및 CVT 초기점검","2024-11-12 09:00","2024-11-12 18:00","2024-11-12 09:00","2024-11-12 18:00","연속"]
[213,"광주전남","광주","신화순S/S #3 M.Tr","2024~2025년 광주전력지사 변전협력회사 공사","-주변압기 보통점검 -345kV GIS 조작시험(7500, 7572CB)","2024-11-19 09:00","2024-11-22 18:00","2024-11-19 09:00","2024-11-22 18:00","연속"]
[214,"광주전남","목포","한빛1NP한빛2NP#1 T/L","24-25년 목포전력지사 변전협력회사 공사","한빛연락#1T/L 보호반 대체","2024-11-04 08:00","2024-11-08 18:00","취소","취소","연속"]
[215,"광주전남","목포","신광주한빛NP#1 T/L","2024년도 가공송전선로 순시점검 위탁공사","345kV 신광주-한빛T/L 조류착지방지장치 설치작업","2024-11-04 09:00","2024-11-04 18:00","취소","취소","연속"]
[216,"광주전남","목포","한빛1NP한빛2NP#2 T/L","24-25년 목포전력지사 변전협력회사 공사","한빛연락#2T/L 보호반 대체","2024-11-11 08:00","2024-11-15 18:00","취소","취소","연속"]
[217,"광주전남","목포","신광주한빛NP#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","한빛#1S/Y 345kV 신광주-한빛#2T/L GIS(7272) 인출부싱 염해방지 코팅제 도포","2024-11-26 09:00","2024-11-27 18:00","취소","취소","매일"]
[218,"광주전남","목포","신광주한빛NP#2 T/L","2024년도 가공송전선로 순시점검 위탁공사","345kV 신광주-한빛T/L 조류착지방지장치 설치작업","2024-11-05 09:00","2024-11-05 18:00","취소","취소","연속"]
[219,"광주전남","목포","신김제한빛NP#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","한빛#3S/Y 7D00, 7D72 GIS 조작시험 및 균압콘덴서 절연열화 측정","2024-11-28 09:00","2024-11-28 18:00","취소","취소","연속"]
[220,"광주전남","순천","광양C/C CB 7271","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","광양C/C 광양-광양CC#1T/L(7271) GIS 보통점검","2024-11-05 09:00","2024-11-05 18:00","2024-11-05 09:00","2024-11-05 18:00","연속"]
[221,"광주전남","순천","광양광양CC#1 T/L","24-25년 순천전력지사 변전협력회사 공사","광양CC #1T/L CVT,LA 보통점검","2024-11-05 09:00","2024-11-05 18:00","2024-11-05 09:00","2024-11-05 18:00","연속"]
[222,"광주전남","순천","광양광양CC#2 T/L","광양-광양CC#2T/L GIS(7171) 절연열화 측정","광양-광양CC#2T/L GIS(7171) 절연열화 측정","2024-11-06 09:00","2024-11-06 18:00","2024-11-06 09:00","2024-11-06 18:00","연속"]
[223,"광주전남","순천","광양C/C CB 7171","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","광양C/C 광양-광양CC#2T/L(7171) GIS 보통점검","2024-11-06 09:00","2024-11-06 18:00","2024-11-06 09:00","2024-11-06 18:00","연속"]
[224,"광주전남","순천","광양하동TP#2 T/L","345kV 광양-하동TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-29 07:00","2024-12-02 18:00","2024-11-29 07:00","2024-12-02 18:00","매일"]
[225,"광주전남","순천","신강진광양#1 T/L","24-25년 순천전력지사 변전협력회사 공사","광양S/S 신강진-광양#1T/L LA,CVT 대체","2024-11-18 09:00","2024-11-19 18:00","2024-11-18 09:00","2024-11-19 18:00","연속"]
[226,"광주전남","순천","광양율촌CC T/L","345kV 광양-여수TPT/L 일부구간 지중화 공사","345kV 광양-여수TPT/L 일부 지중화 관련 C/T 설치공사","2024-11-18 07:30","2024-11-28 18:00","2024-11-18 07:30","2024-11-28 18:00","연속"]
[227,"광주전남","순천","신강진광양#1 T/L","345kV 신강진-광양T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-18 07:00","2024-11-20 18:00","2024-11-18 07:00","2024-11-20 18:00","매일"]
[228,"광주전남","순천","광양여수TP T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 설치","2024-11-12 07:00","2024-11-12 18:00","2024-11-12 07:00","2024-11-12 18:00","연속"]
[229,"광주전남","순천","광양S/S #3 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #3M.Tr 2차 LA 대체, 1차 LA 대체, 3차 LA 대체","2024-11-11 09:00","2024-11-13 18:00","2024-11-11 09:00","2024-11-13 18:00","연속"]
[230,"광주전남","순천","신남원광양#1 T/L","24-25년 순천전력지사 변전협력회사 공사","광양S/S 신남원 광양 #1T/L LA 보통점검","2024-11-01 09:00","2024-11-01 18:00","2024-11-01 09:00","2024-11-01 18:00","연속"]
[231,"광주전남","순천","광양여수TP T/L","345kV 광양-여수TPT/L 일부구간 지중화 공사","345kV 광양-여수TPT/L 일부 지중화 관련 C/T 설치공사","2024-11-04 07:30","2024-11-15 18:00","2024-11-04 07:30","2024-11-15 18:00","연속"]
[232,"광주전남","순천","신남원광양#2 T/L","24-25년 순천전력지사 변전협력회사 공사","광양S/S 신남원 광양 #2T/L LA,CVT 보통점검","2024-11-04 09:00","2024-11-04 18:00","2024-11-04 09:00","2024-11-04 18:00","연속"]
[233,"광주전남","순천","여수T/P #1 Tie-Tr","24~25년 순천전력지사 변전협력회사 공사","여수화력#1M.Tr A,B상 1차 부싱 대체, 3차 LA, MAIN VCB,#1-1Sh.R, VCB 보통점검 및 추락방지장치 설치","2024-11-25 09:00","2024-11-29 18:00","2024-11-25 09:00","2024-11-29 18:00","연속"]
[234,"광주전남","순천","여수T/P #3 Tie-Tr","24~25년 순천전력지사 변전협력회사 공사","여수화력#3M.Tr 2차 LA 보통점검","2024-11-21 09:00","2024-11-21 18:00","2024-11-21 09:00","2024-11-21 18:00","연속"]
[235,"광주전남","순천","여수T/P #2 Tie-Tr","#2M.Tr 3차 VCB 부 과열개소 조치","#2M.Tr 3차 VCB 부 과열개소 조치","2024-11-11 09:00","2024-11-11 18:00","2024-11-11 09:00","2024-11-11 18:00","연속"]
[236,"대구","칠곡","북대구서대구#1 T/L","북대구S/S 7471 GIS 보통점검 및 Aux. Ry 전량교체","북대구S/S 7471 GIS 보통점검 및 Aux. Ry 전량교체","2024-11-11 09:30","2024-11-12 18:00","2024-11-11 09:30","2024-11-12 18:00","연속"]
[237,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 안전확보","2024-11-07 07:00","2024-11-13 18:00","2024-11-07 07:00","2024-11-13 18:00","연속"]
[238,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","#1M.Tr 2차측 모선 정비 작업","2024-11-25 07:30","2024-11-29 18:00","2024-11-25 07:30","2024-11-29 18:00","연속"]
[239,"대구","칠곡","서대구S/S #3 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업","2024-11-07 07:00","2024-11-22 18:00","2024-11-07 07:00","2024-11-22 18:00","연속"]
[240,"대구","포항","신영일S/S #3 M.Tr","2024~25년도 포항전력지사 변전총액공사","신영일S/S 7500 GCB 공기압력계 교체 및 1차 부싱 절연열화측정, 부싱절연유 채유","2024-11-13 09:00","2024-11-13 18:00","2024-11-13 09:00","2024-11-13 18:00","연속"]
[241,"대구","포항","신영일S/S #4 M.Tr","2024~25년도 포항전력지사 변전총액공사","신영일S/S #4M.Tr 1차 부싱 절연열화측정, 부싱절연유 채유","2024-11-14 09:00","2024-11-14 18:00","2024-11-14 09:00","2024-11-14 18:00","연속"]
[242,"대구","포항","신포항신월성NP#4 T/L","24~25년도 포항전력지사 변전총액공사","신월성S/Y 7171 GIS 조작시험","2024-11-07 09:00","2024-11-07 18:00","2024-11-07 09:00","2024-11-07 18:00","연속"]
[243,"대구","포항","선산신포항 T/L","345kV 신포항-북대구T/L 임시 지장송전선로 이설공사","- 임시철탑 2기 설치, 기설철탑 3기 철거 - 전력선 설치 및 철거(재사용)","2024-11-15 07:00","2024-11-22 18:00","2024-11-15 07:00","2024-11-22 18:00","연속"]
[244,"대구","포항","신포항북대구 T/L","345kV 신포항-북대구T/L 임시 지장송전선로 이설공사","- 임시철탑 2기 설치, 기설철탑 3기 철거 - 전력선 설치 및 철거(재사용)","2024-11-23 07:00","2024-11-30 18:00","2024-11-23 07:00","2024-11-30 18:00","연속"]
[245,"경북","구미","선산S/S #2 M.Tr","2024-25년 구미전력지사 변전협력회사 공사","- M.Tr B상 절연열화 측정 - 1,2차 부싱 절연유 채유 - 1차 7172 GIS 초기점검 - 2차 6244 GIS 보통점검[정밀] - 154kV GIS DS 방압변 점검 - 1차, 2차 LA 교체 - 3차 LA 초기점검","2024-11-04 09:00","2024-11-06 18:00","2024-11-04 09:00","2024-11-06 18:00","연속"]
[246,"경북","구미","서대구선산#2 T/L","2024-25년 구미전력지사 변전협력회사 공사","- 7171,7100 GIS 초기점검 - LA 교체","2024-11-27 09:00","2024-11-27 18:00","2024-11-27 09:00","2024-11-27 18:00","연속"]
[247,"경북","구미","서대구선산#1 T/L","2024-25년 구미전력지사 변전협력회사 공사","- LA 교체","2024-11-29 09:00","2024-11-29 18:00","2024-11-29 09:00","2024-11-29 18:00","연속"]
[248,"경북","영주","신영주S/S #3 M.Tr","2024-25년 영주전력지사 변전협력회사 공사","B/F PNL 대체","2024-11-04 09:00","2024-11-07 18:00","2024-11-04 09:00","2024-11-07 18:00","연속"]
[249,"경북","영주","한울#2N/P CB 7A71","2024~25년 영주전력지사 변전협력회사 총액공사","7A71 GIS 보통점검","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[250,"경북","영주","한울#2N/P CB 7G71","2024~25년 영주전력지사 변전협력회사 총액공사","7G71 GIS 보통점검","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[251,"경북","영주","한울#2N/P CB 7F71","2024~25년 영주전력지사 변전협력회사 총액공사","7F71 GIS 보통점검","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[252,"경북","영주","한울#2N/P CB 7671","2024~25년 영주전력지사 변전협력회사 총액공사","7671 GIS 보통점검","2024-11-18 09:00","2024-11-18 18:00","2024-11-18 09:00","2024-11-18 18:00","연속"]
[253,"경북","영주","한울#2N/P CB 7571","2024~25년 영주전력지사 변전협력회사 총액공사","7571 GIS 보통점검","2024-11-18 09:00","2024-11-18 18:00","2024-11-18 09:00","2024-11-18 18:00","연속"]
[254,"경북","직할","신영주청송PP T/L","24년 가공송전 순시점검 위탁공사 정밀점검","정밀점검:345kV 신영주-청송PPT/L No.49~82","2024-11-05 08:00","2024-11-13 18:00","2024-11-05 08:00","2024-11-13 18:00","연속"]
[255,"부산울산","동부산","고리N/P SEC CB 76770","고리NP S/Y 76-77-0GIS 절연열화 측정","고리NP S/Y 76-77-0GIS 절연열화 측정","2024-11-12 14:00","2024-11-12 17:00","2024-11-12 14:00","2024-11-12 17:00","연속"]
[256,"부산울산","동부산","고리N/P CB 7271","고리NP S/Y 7271CB 차단기 동작시험","고리NP S/Y 7271CB 차단기 동작시험","2024-11-04 09:30","2024-11-04 14:00","2024-11-04 09:30","2024-11-04 14:00","연속"]
[257,"부산울산","동부산","고리N/P SEC CB 71720","고리NP S/Y 71-72-0GIS 절연열화 측정","고리NP S/Y 71-72-0GIS 절연열화 측정","2024-11-12 09:30","2024-11-12 14:00","2024-11-12 09:30","2024-11-12 14:00","연속"]
[258,"부산울산","동부산","신양산S/S #1 BUS","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(5차) - 71BAY GIS 철거시 #1모선DS 엔드커버 설치","2024-11-11 10:00","2024-11-11 14:00","2024-11-11 10:00","2024-11-11 14:00","연속"]
[259,"부산울산","동부산","신양산북부산#1 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-11-04 07:30","2024-11-05 18:00","2024-11-04 07:30","2024-11-05 18:00","연속"]
[260,"부산울산","동부산","신양산S/S #2 BUS","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(5차) - 71BAY GIS 철거시 #2모선DS 엔드커버 설치","2024-11-01 10:00","2024-11-01 14:00","2024-11-01 10:00","2024-11-01 14:00","연속"]
[261,"부산울산","동부산","신양산북부산#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-11-06 07:30","2024-11-07 18:00","2024-11-06 07:30","2024-11-07 18:00","연속"]
[262,"부산울산","동부산","신양산고리NP#2 T/L","신양산S/S 신양산-고리NP #2T/L 보호반대체","신양산S/S 신양산-고리NP #2T/L 보호반대체 병행) 고리NP S/Y 신양산-고리NP #2T/L 보호반대체","2024-11-07 09:00","2024-11-13 18:00","2024-11-07 09:00","2024-11-13 18:00","연속"]
[263,"부산울산","동부산","신양산신대연#1 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-11-08 07:30","2024-11-08 12:00","2024-11-08 07:30","2024-11-08 12:00","연속"]
[264,"부산울산","동부산","신양산신대연#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-11-08 13:00","2024-11-08 18:00","2024-11-08 13:00","2024-11-08 18:00","연속"]
[265,"부산울산","북부산","북부산S/S #76 BUS","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S #76BUS PRO PNL 대체공사","2024-11-04 09:00","2024-11-08 18:00","2024-11-04 09:00","2024-11-08 18:00","연속"]
[266,"부산울산","북부산","신김해북부산#1 T/L","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #73BAY B/F PNL 대체공사","2024-11-18 09:00","2024-11-22 18:00","취소","취소","연속"]
[267,"부산울산","북부산","북부산S/S CB 7572","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #2M.Tr 1차 7572 GIS 조작시험","2024-11-04 09:00","2024-11-04 18:00","2024-11-04 09:00","2024-11-04 18:00","연속"]
[268,"부산울산","북부산","북부산신울산#2 T/L","2024년 북부산전력지사 가공송전 순시점검 위탁공사","345kV 북부산-신울산#2T/L 정밀점검 -점검대상 : 총 115기(No.1 ~ 110호 113기 및 S/T 2기)","2024-11-01 09:00","2024-11-13 18:00","2024-11-01 09:00","2024-11-13 18:00","연속"]
[269,"부산울산","북부산","북부산고리NP#2 T/L","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #73BAY B/F PNL 대체공사","2024-11-18 09:00","2024-11-22 18:00","2024-11-18 09:00","2024-11-22 18:00","연속"]
[270,"부산울산","서부산","서부산S/S CB 7472","서부산S/S 7472 GIS 동작시험","서부산S/S 7472 GIS 동작시험","2024-11-05 09:00","2024-11-05 18:00","2024-11-05 09:00","2024-11-05 18:00","연속"]
[271,"부산울산","서부산","서부산S/S CB 7572","서부산S/S 7572 GIS 동작시험","서부산S/S 7572 GIS 동작시험","2024-11-05 09:00","2024-11-05 18:00","2024-11-05 09:00","2024-11-05 18:00","연속"]
[272,"부산울산","서부산","서부산S/S CB 7400","서부산S/S 7400 GIS 동작시험","서부산S/S 7400 GIS 동작시험","2024-11-04 09:00","2024-11-04 13:00","2024-11-04 09:00","2024-11-04 13:00","연속"]
[273,"부산울산","서부산","서부산S/S CB 7471","서부산S/S 7471 GIS 동작시험","서부산S/S 7471 GIS 동작시험","2024-11-04 13:00","2024-11-04 18:00","2024-11-04 13:00","2024-11-04 18:00","연속"]
[274,"부산울산","울산","남울산S/S #3 M.Tr","종합예방진단 관련 불량조치","- C상 1차부싱 종합예방진단 관련 불량조치","2024-11-06 09:00","2024-11-06 18:00","2024-11-06 09:00","2024-11-06 18:00","연속"]
[275,"부산울산","울산","신온산S/S #3 M.Tr","24년 울산전력지사 변전협력회사 총액공사","- 1,2차 부싱 절연유 채유","2024-11-05 09:00","2024-11-05 18:00","2024-11-05 09:00","2024-11-05 18:00","연속"]
[276,"부산울산","울산","신온산신울산#2 T/L","신울산S/S 345kV SECTION 설치 및 변압기 인출변경공사","- 71BAY 증설(무부하가압 선로)","2024-11-08 09:00","2024-11-09 18:00","2024-11-08 09:00","2024-11-09 18:00","연속"]
[277,"부산울산","울산","신울산S/S #75 BUS","신울산S/S 345kV SECTION 설치 및 변압기 인출변경공사","- 7A BAY 모선 DS 및 상부 BUS 무부하가압","2024-11-21 09:00","2024-11-22 18:00","2024-11-21 09:00","2024-11-22 18:00","연속"]
[278,"부산울산","울산","신온산신울산#2 T/L","신울산S/S 345kV SECTION 설치 및 변압기 인출변경공사","- 7A BAY 모선 DS 및 상부 BUS 무부하가압(시험가압선로)","2024-11-21 09:00","2024-11-22 18:00","2024-11-21 09:00","2024-11-22 18:00","연속"]
[279,"부산울산","울산","신울산고리NP#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-11-27 07:30","2024-11-28 18:00","2024-11-27 07:30","2024-11-28 18:00","연속"]
[280,"부산울산","울산","신울산고리NP#1 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-11-25 07:30","2024-11-26 18:00","2024-11-25 07:30","2024-11-26 18:00","연속"]
[281,"부산울산","울산","신울산S/S #75 BUS","신울산S/S 345kV SECTION 설치 및 변압기 인출변경공사","- 7A BAY 증설(7A72, 7A00CB)","2024-11-04 09:00","2024-11-09 18:00","2024-11-04 09:00","2024-11-09 18:00","연속"]
[282,"부산울산","울산","신울산S/S #70 BUS","신울산S/S 345kV SECTION 설치 및 변압기 인출변경공사","- 7A BAY 증설(7A72, 7A00CB)","2024-11-11 09:00","2024-11-14 18:00","2024-11-11 09:00","2024-11-14 18:00","연속"]
[283,"부산울산","울산","신온산신울산#2 T/L","신울산S/S 345kV SECTION 설치 및 변압기 인출변경공사","- 71BAY 증설(무부하가압 선로)","2024-11-13 09:00","2024-11-14 18:00","2024-11-13 09:00","2024-11-14 18:00","연속"]
[284,"부산울산","울산","울산C/C #1 Tie-Tr","24년 울산전력지사 주변압기 및 OLTC 정밀점검 공사","- OLTC 정밀점검 - 1,2차 피뢰기 보통점검 - 부싱절연유 채유","2024-11-18 09:00","2024-11-19 18:00","2024-11-18 09:00","2024-11-19 18:00","연속"]
[285,"부산울산","울산","울산C/C #3 Tie-Tr","24년 울산전력지사 주변압기 및 OLTC 정밀점검 공사","- OLTC 정밀점검","2024-11-20 09:00","2024-11-21 18:00","2024-11-20 09:00","2024-11-21 18:00","연속"]
[286,"부산울산","울산","울주S/S #4 M.Tr","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정 - 2차 GIS 보통점검 - 3차 피뢰기 보통점검 - #4S.Tr 보통점검","2024-11-14 09:00","2024-11-15 18:00","2024-11-14 09:00","2024-11-15 18:00","연속"]
[287,"부산울산","울산","울주울산TP#2 T/L","2024년 가공송전 순시점검 위탁공사","154kV 직동-반천T/L 정밀점검 안전이격","2024-11-04 09:00","2024-11-04 18:00","2024-11-04 09:00","2024-11-04 18:00","연속"]
[288,"부산울산","울산","울주S/S #3 M.Tr","24년 울산전력지사 변전협력회사 총액공사","- 2점절 균압콘덴서 절연열화 측정 - 2차 GIS 보통점검 - 2,3차 피뢰기 보통점검 - 1,2차 부싱절연유 채유 - 3차 GIS 보통점검 - #3S.Tr 보통점검","2024-11-12 09:00","2024-11-13 18:00","2024-11-12 09:00","2024-11-13 18:00","연속"]
[289,"경남","김해송변전부","신김해S/S #5 M.Tr","신김해S/S #5M.Tr 부싱절연유 채취 및 AC반 대체","신김해S/S #5M.Tr 부싱절연유 채취 및 AC반 대체","2024-11-30 08:00","2024-11-30 18:30","2024-11-30 08:00","2024-11-30 18:30","연속"]
[290,"경남","김해송변전부","신김해창원#2 T/L","2024-2025년 경남본부 직할 가공송전협력회사 총액공사","압축인류클램프 교체","2024-11-21 07:00","2024-11-21 18:00","2024-11-21 07:00","2024-11-21 18:00","연속"]
[291,"경남","김해송변전부","신김해S/S #4 M.Tr","신김해S/S #4M.Tr 정밀점검","신김해S/S #4M.Tr 정밀점검","2024-11-20 09:30","2024-11-29 17:30","2024-11-20 09:30","2024-11-29 17:30","연속"]
[292,"경남","김해송변전부","신김해창원#1 T/L","2024-2025년 경남본부 직할 가공송전협력회사 총액공사","압축인류클램프 교체","2024-11-18 07:00","2024-11-20 18:00","2024-11-18 07:00","2024-11-20 18:00","매일"]
[293,"경남","김해송변전부","신김해S/S #1 M.Tr","신김해S/S 345kV 용량부족 GIS 교체공사(인출변경)","신김해S/S 345kV 용량부족 GIS 교체공사(인출변경)","2024-11-11 09:00","2024-11-19 18:00","2024-11-11 09:00","2024-11-19 18:00","연속"]
[294,"경남","김해송변전부","신김해북부산#1 T/L","신김해S/S 345kV 용량부족 GIS 교체공사(인출변경)","신김해S/S 345kV 용량부족 GIS 교체공사(인출변경)","2024-11-11 09:00","2024-11-19 18:00","2024-11-11 09:00","2024-11-19 18:00","연속"]
[295,"경남","김해송변전부","신김해북부산#2 T/L","신김해S/S 345kV 용량부족 GIS 교체공사(시험가압)","신김해S/S 345kV 용량부족 GIS 교체공사(시험가압)","2024-11-09 09:00","2024-11-10 18:00","2024-11-09 09:00","2024-11-10 18:00","연속"]
[296,"경남","김해송변전부","신김해S/S #1 BUS","신김해S/S 345kV 용량부족 GIS 교체공사","신김해S/S 345kV 용량부족 GIS 교체공사","2024-11-01 09:00","2024-11-10 18:00","2024-11-01 09:00","2024-11-10 18:00","연속"]
[297,"경남","김해송변전부","신김해북부산#2 T/L","신김해S/S 345kV 용량부족 GIS 교체공사(안전이격)","신김해S/S 345kV 용량부족 GIS 교체공사(안전이격)","2024-11-02 09:00","2024-11-04 18:00","2024-11-02 09:00","2024-11-04 18:00","매일"]
[298,"경남","직할","창원S/S #2 M.Tr","창원S/S 154kV 한국철강T/L 신규수용공사(안전이격거리)","1. GIS(170kV 50kA 2,000A) x 1CCT 설치 2. 기타 부대공사 x 1식 3. 안전이격거리 확보","2024-11-18 08:00","2024-11-18 18:00","취소","취소","연속"]
[299,"경남","직할","창원S/S #2 M.Tr","창원S/S 154kV 한국철강T/L 신규수용공사(안전이격거리)","1. GIS(170kV 50kA 2,000A) x 1CCT 설치 2. 기타 부대공사 x 1식 3. 안전이격거리 확보","2024-11-11 08:00","2024-11-16 18:00","2024-11-25 08:00","2024-11-30 18:00","연속"]
[300,"경남","직할","창원S/S #2 M.Tr","창원S/S 154kV 한국철강T/L 신규수용공사(안전이격거리)","1. GIS(170kV 50kA 2,000A) x 1CCT 설치 2. 기타 부대공사 x 1식 3. 안전이격거리 확보","2024-11-04 08:00","2024-11-08 18:00","2024-11-18 08:00","2024-11-22 18:00","연속"]
[301,"경남","직할","창원S/S #2 M.Tr","창원S/S 154kV 한국철강T/L 신규수용공사(안전이격거리)","1. GIS(170kV 50kA 2,000A) x 1CCT 설치 2. 기타 부대공사 x 1식 3. 안전이격거리 확보","2024-11-26 08:00","2024-11-29 18:00","취소","취소","매일"]
[302,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-11-11 07:30","2024-11-15 18:00","취소","취소","매일"]
[303,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-11-09 07:30","2024-11-10 18:00","2024-11-09 07:30","2024-11-10 18:00","매일"]
[304,"경남","진주","의령산청양수#2 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#2T/L측 수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.112~129 (345kV 의령-하동화력 T/L과 병가 구간)","2024-11-09 07:30","2024-11-10 18:00","2024-11-09 07:30","2024-11-10 18:00","매일"]
[305,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 추락방지장치 설치 공사","345kV 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2024-11-09 07:00","2024-11-10 18:00","취소","취소","매일"]
[306,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-11-04 07:30","2024-11-08 18:00","취소","취소","매일"]
[307,"경남","진주","의령산청양수#2 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#2T/L측 수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.112~129 (345kV 의령-하동화력 T/L과 병가 구간)","2024-11-02 07:30","2024-11-03 18:00","2024-11-02 07:30","2024-11-03 18:00","매일"]
[308,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 추락방지장치 설치 공사","345kV 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2024-11-02 07:00","2024-11-03 18:00","취소","취소","매일"]
[309,"경남","진주","의령S/S #2 M.Tr","예비변압기 절체 관련 #2M.Tr 케이블 신규/재포설","예비변압기 절체 관련 #2M.Tr 케이블 신규/재포설","2024-11-11 09:00","2024-11-13 18:00","2024-11-11 09:00","2024-11-13 18:00","연속"]
[310,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 추락방지장치 설치 공사","345kV 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2024-11-15 07:00","2024-11-17 18:00","취소","취소","매일"]
[311,"경남","진주","의령산청양수#1 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.112~129 (345kV 의령-하동화력 T/L과 병가 구간)","2024-11-16 07:30","2024-11-17 18:00","2024-11-16 07:30","2024-11-17 18:00","매일"]
[312,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-11-16 07:30","2024-11-17 18:00","2024-11-16 07:30","2024-11-17 18:00","매일"]
[313,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-11-18 07:30","2024-11-22 18:00","취소","취소","매일"]
[314,"경남","진주","의령신마산#2 T/L","의령S/S 345kV 의령-신마산#2T/L 휴전작업","의령S/S 345kV 의령-신마산#2T/L 휴전작업 7A71, 7A00 GIS 보통점검 [병행] 의령-신마산#2T/L PT 보통점검","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[315,"경남","진주","신남원의령#1 T/L","의령S/S 345kV 신남원-의령#1T/L 휴전작업","의령S/S 345kV 7871, 7800 GIS 보통점검 [병행] 신남원-의령#1T/L PT(A,B,C) 하자점검","2024-11-21 09:00","2024-11-21 18:00","취소","취소","연속"]
[316,"경남","진주","의령S/S CB 7271","의령S/S 345kV 7271 GIS 보통점검(차단기 단독)","의령S/S 345kV 7271 GIS 보통점검(차단기 단독)","2024-11-22 09:00","2024-11-22 13:00","2024-11-22 09:00","2024-11-22 13:00","연속"]
[317,"경남","진주","의령S/S CB 7200","의령S/S 345kV 7200 GIS 보통점검(차단기 단독)","의령S/S 345kV 7200 GIS 보통점검(차단기 단독)","2024-11-22 13:00","2024-11-22 17:00","2024-11-22 13:00","2024-11-22 17:00","연속"]
[318,"경남","진주","신남원의령#1 T/L","345kV 신남원-의령T/L 추락방지장치 설치 공사","345kV 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2024-11-23 07:00","2024-11-24 18:00","취소","취소","매일"]
[319,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-11-23 07:30","2024-11-24 18:00","2024-11-23 07:30","2024-11-24 18:00","매일"]
[320,"경남","진주","의령산청양수#1 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 : 345kV 의령-산청양수#1T/L측 수평 추락방지장치 설치 2.작업구간 : 345kV 의령-산청양수T/L No.112~129 (345kV 의령-하동화력 T/L과 병가 구간)","2024-11-23 07:30","2024-11-24 18:00","2024-11-23 07:30","2024-11-24 18:00","매일"]
[321,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-11-25 07:30","2024-11-29 18:00","취소","취소","매일"]
[322,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-11-02 07:30","2024-11-03 18:00","2024-11-02 07:30","2024-11-03 18:00","매일"]
[323,"경남","진주","하동T/P CB 7600","하동T/P 7600 GIS 정밀점검","하동T/P 7600 GIS 정밀점검 [병행, 협력] Control Block 교체","2024-11-11 10:00","2024-11-15 18:00","2024-11-11 10:00","2024-11-15 18:00","연속"]
[324,"경남","진주","하동T/P CB 7571","하동T/P 의령-하동화력#2T/L GIS(7571) 보통점검","하동T/P 의령-하동화력#2T/L GIS(7571) 보통점검","2024-11-28 10:00","2024-11-28 15:00","2024-11-28 10:00","2024-11-28 15:00","연속"]
[325,"경남","진주","하동T/P CB 7672","하동T/P 7672 GIS 보통, 컨트롤 블럭 교체 등","하동T/P 7672 GIS 보통 [병행] Control Block 교체 7600 GIS 시험가압 GIS","2024-11-11 10:00","2024-11-15 18:00","2024-11-11 10:00","2024-11-15 18:00","연속"]
[326,"경남","진주","하동T/P CB 7200","하동T/P 7200 GIS 조작시험(차단기 단독)","하동T/P 7200 GIS 조작시험(차단기 단독)","2024-11-07 15:00","2024-11-07 18:00","2024-11-07 15:00","2024-11-07 18:00","연속"]
[327,"경남","진주","하동T/P CB 7272","하동T/P #2M.Tr 1차(7272) GIS 보통점검(차단기 단독)","하동T/P #2M.Tr 1차(7272) GIS 보통점검(차단기 단독)","2024-11-07 10:00","2024-11-07 15:00","2024-11-07 10:00","2024-11-07 15:00","연속"]
[328,"경남","진주","하동T/P CB 7671","하동T/P 345kV 7671 GIS 보통점검(차단기 단독)","하동T/P 345kV 7671 GIS 보통점검(차단기 단독)","2024-11-01 10:00","2024-11-01 15:00","2024-11-01 10:00","2024-11-01 15:00","연속"]
[329,"경남","함안","북경남S/S CB 7B71","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전 외","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전 및 7B71 GIS 보통점검","2024-11-14 09:30","2024-11-14 17:30","2024-11-14 09:30","2024-11-14 17:30","연속"]
[330,"경남","함안","북경남S/S #7 Sh.R CB","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전 외","북경남S/S 345kV GIS 균압콘덴서 재측정 관련 휴전 및 #7Sh.R 초기점검","2024-11-14 09:30","2024-11-14 17:30","2024-11-14 09:30","2024-11-14 17:30","연속"]
[331,"경남","함안","신마산S/S #3 M.Tr","신마산S/S 345kV #3 M.Tr 1차 GIS 보통점검 외","신마산S/S 345kV #3 M.Tr 1차 GIS 보통점검 외","2024-11-11 09:30","2024-11-12 17:30","2024-11-11 09:30","2024-11-12 17:30","연속"]
[332,"경남","함안","신마산S/S CB 7471","신마산S/S 345kV 의령-신마산#2T/L GIS 보통점검[단독]","신마산S/S 345kV 의령-신마산#2T/L GIS 보통점검[단독]","2024-11-07 09:30","2024-11-07 17:30","2024-11-07 09:30","2024-11-07 17:30","연속"]
[333,"경남","함안","신마산S/S #1 M.Tr","신마산S/S 345kV #1 M.Tr 1차 GIS 보통점검 외","신마산S/S 345kV #1 M.Tr 1차 GIS 보통점검 외","2024-11-13 09:30","2024-11-13 17:30","2024-11-13 09:30","2024-11-13 17:30","연속"]
[334,"부산울산",null,"고리N/P #4호기 기동변압기#1 (CB 7C00, 7C72)","고리4호기 기동변압기 #1 정기점검 ○ 기동변압기, GIB, 갑종보호계전기 등 일반점검 수행","고리4호기 기동변압기 #1 정기점검 ○ 기동변압기, GIB, 갑종보호계전기 등 일반점검 수행","2024-11-01 10:00","2024-11-10 18:00","2024-11-01 10:00","2024-11-10 18:00","연속"]
[335,"부산울산",null,"고리N/P #4호기 기동변압기#2 (CB 7600, 7672)","고리4호기 기동변압기 #2 정기점검 ○ 기동변압기, GIB, 갑종보호계전기 등 일반점검 수행","고리4호기 기동변압기 #2 정기점검 ○ 기동변압기, GIB, 갑종보호계전기 등 일반점검 수행","2024-11-11 10:00","2024-11-22 18:00","2024-11-11 10:00","2024-11-22 18:00","연속"]
[336,"경북",null,"한울N/P #2호기 주변압기 (CB 7400, 7472)","○ 주변압기 점검 ○ 갑종보호계전기 점검","○ 주변압기 점검 ○ 갑종보호계전기 점검","2024-11-05 15:00","2024-12-03 14:00","2024-11-05 15:00","2024-12-03 14:00","연속"]
[337,"경북",null,"한울N/P #4 대기보조변압기 SAT#1 (CB 7700, 7772)","한울4호기 제17차 계획예방정비 * 대기보조변압기 등 일반점검","한울4호기 제17차 계획예방정비 * 대기보조변압기 등 일반점검","2024-11-20 16:00","2024-11-29 14:00","2024-11-20 16:00","2024-11-29 14:00","연속"]
[338,"경북",null,"한울N/P #4 대기보조변압기 SAT#2 (CB 7800, 7872)","한울4호기 제17차 계획예방정비 * 대기보조변압기 등 일반점검","한울4호기 제17차 계획예방정비 * 대기보조변압기 등 일반점검","2024-11-20 16:00","2024-11-29 14:00","2024-11-20 16:00","2024-11-29 14:00","연속"]

{"sheet":"154설비","index":2,"n_rows":813,"n_cols":11,"rows_kept":813,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 11월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의광장#1 T/L","2024년 성동전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2024-11-12 10:00","2024-11-12 18:00","취소","취소","연속"]
[2,"서울","성동","구의S/S CB 6100","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#1T/L, #1M.Tr 1차 GIS 교체","2024-11-15 15:00","2024-12-13 15:00","2024-11-09 09:00","2024-11-30 18:00","연속"]
[3,"서울","성동","천호구의#2 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#1T/L, #1M.Tr 1차 GIS 교체","2024-11-29 15:00","2024-12-02 15:00","2024-11-19 15:00","2024-11-20 18:00","연속"]
[4,"서울","성동","천호구의#1 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#2T/L, BUS PT GIS 교체","2024-11-13 15:00","2024-11-14 15:00","2024-11-07 15:00","2024-11-08 15:00","연속"]
[5,"서울","성동","구의S/S #1 BUS","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#2T/L, BUS PT GIS 교체","2024-11-14 15:00","2024-11-15 15:00","2024-11-08 15:00","2024-11-08 18:00","연속"]
[6,"서울","성동","구의S/S #2 BUS","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#1T/L, #1M.Tr 1차 GIS 교체","2024-11-15 15:00","2024-11-21 15:00","2024-11-09 09:00","2024-11-12 15:00","연속"]
[7,"서울","성동","천호구의#1 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#1T/L, #1M.Tr 1차 GIS 교체","2024-11-15 15:00","2024-12-13 15:00","2024-11-09 09:00","2024-11-30 18:00","연속"]
[8,"서울","성동","천호구의#2 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#1T/L, #1M.Tr 1차 GIS 교체","2024-11-20 15:00","2024-11-21 15:00","2024-11-11 15:00","2024-11-12 15:00","연속"]
[9,"서울","성동","구의S/S #1 BUS","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#1T/L, #1M.Tr 1차 GIS 교체","2024-11-21 15:00","2024-12-02 15:00","2024-11-12 15:00","2024-11-20 15:00","연속"]
[10,"서울","성동","안암노원#1 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-11-25 09:00","2024-11-25 14:00","2024-11-25 09:00","2024-11-25 14:00","연속"]
[11,"서울","성동","금오상계#2 T/L","24년 성동P/O 주변압기 및 OLTC 정밀점검공사","- 주변압기 정밀점검 #2BUS 시험가압","2024-11-01 17:00","2024-11-04 10:00","2024-11-01 16:00","2024-11-01 17:00","연속"]
[12,"서울","성동","성동왕십리#1 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-11-04 10:00","2024-11-04 18:00","취소","취소","연속"]
[13,"서울","성동","성동흥인 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-11-04 10:00","2024-11-04 18:00","취소","취소","연속"]
[14,"서울","성동","성동군자#1 T/L","성동S/S 154kV Sh.R 설치공사(무부하가압 선로)","1. 154kV Sh.R(20MVAR×3) × 2조 설치 2. 154kV Sh.R 1차 GIS × 2Bay 설치 3. 기타 부대공사 × 1식","2024-11-11 14:00","2024-11-11 18:00","2024-11-11 14:00","2024-11-11 18:00","연속"]
[15,"서울","성동","성동S/S #65 BUS","성동S/S 154kV Sh.R 설치공사","1. 154kV Sh.R(20MVAR×3) × 2조 설치 2. 154kV Sh.R 1차 GIS × 2Bay 설치 3. 기타 부대공사 × 1식","2024-11-12 09:00","2024-11-19 18:00","2024-11-12 09:00","2024-11-19 18:00","연속"]
[16,"서울","성동","성동군자#1 T/L","성동S/S 154kV Sh.R 설치공사(무부하가압 선로)","1. 154kV Sh.R(20MVAR×3) × 2조 설치 2. 154kV Sh.R 1차 GIS × 2Bay 설치 3. 기타 부대공사 × 1식","2024-11-19 14:00","2024-11-19 18:00","2024-11-19 14:00","2024-11-19 18:00","연속"]
[17,"서울","성동","신내상봉 T/L","24년 성동P/O 주변압기 및 OLTC 정밀점검공사","- 2BUS 시험가압","2024-11-15 16:00","2024-11-15 17:00","2024-11-22 16:00","2024-11-22 17:00","연속"]
[18,"서울","성동","구리신내#1 T/L","2024년 성동전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-11-04 10:00","2024-11-04 18:00","2024-11-04 10:00","2024-11-04 18:00","연속"]
[19,"서울","성동","왕십리용두 T/L","24년 성동P/O 주변압기 및 OLTC 정밀점검공사","- 무부하 시험가압","2024-11-08 16:00","2024-11-08 17:00","2024-11-08 16:00","2024-11-08 17:00","연속"]
[20,"서울","성동","노원종암 T/L","종암S/S 디지털화 공사","종암S/S 디지털화 공사","2024-11-25 09:00","2024-11-26 18:00","2024-11-25 09:00","2024-11-26 18:00","연속"]
[21,"서울","성동","휘경종암#1 T/L","종암S/S 디지털화 공사","종암S/S 디지털화 공사","2024-11-27 09:00","2024-11-28 18:00","2024-11-27 09:00","2024-11-28 18:00","연속"]
[22,"서울","성동","휘경종암#2 T/L","종암S/S 디지털화 공사","종암S/S 디지털화 공사","2024-11-04 09:00","2024-11-05 18:00","2024-11-04 09:00","2024-11-05 18:00","연속"]
[23,"서울","성동","화양S/S CB 6100","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-11-11 10:00","2024-11-11 18:00","2024-11-11 10:00","2024-11-11 18:00","연속"]
[24,"서울","성동","화양상봉#1 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-11-07 10:00","2024-11-07 18:00","2024-11-07 10:00","2024-11-07 18:00","연속"]
[25,"서울","성동","미금화양 T/L","24년 성동P/O 변전협력회사 공사","154kV GIS 조작시험","2024-11-07 10:00","2024-11-07 18:00","2024-11-07 10:00","2024-11-07 18:00","연속"]
[26,"서울","중부","원흥상암 T/L","원흥상암 T/L EBG 가스채취밸브 설치","원흥상암 T/L 상암EBG 가스채취밸브 설치","2024-11-04 09:00","2024-11-06 18:00","2024-11-04 09:00","2024-11-06 18:00","연속"]
[27,"서울","중부","상암S/S #1 BUS","상암S/S #4M.Tr 증설공사","상암S/S #4M.Tr 증설공사","2024-11-27 09:00","2024-11-28 09:00","취소","취소","연속"]
[28,"서울","중부","능곡상암#1 T/L","상암S/S #4M.Tr 증설공사","상암S/S #4M.Tr 증설공사","2024-11-27 09:00","2024-11-29 09:00","취소","취소","연속"]
[29,"서울","중부","상암S/S #2 BUS","상암S/S #4M.Tr 증설공사","상암S/S #4M.Tr 증설공사","2024-11-18 09:00","2024-11-22 18:00","취소","취소","연속"]
[30,"서울","중부","능곡상암#1 T/L","상암S/S #4M.Tr 증설공사","상암S/S #4M.Tr 증설공사","2024-11-21 15:00","2024-11-22 18:00","취소","취소","연속"]
[31,"서울","중부","상암S/S #2 BUS","상암S/S #4M.Tr 증설공사","상암S/S #4M.Tr 증설공사","2024-11-28 09:00","2024-11-29 09:00","취소","취소","연속"]
[32,"서울","중부","상암S/S 상암난방#2 T/L CB","상암S/S #4M.Tr 증설공사","상암S/S #4M.Tr 증설공사","2024-11-11 09:00","2024-11-22 18:00","취소","취소","연속"]
[33,"서울","중부","상암S/S #1 BUS","상암S/S #4M.Tr 증설공사","상암S/S #4M.Tr 증설공사","2024-11-11 09:00","2024-11-15 18:00","취소","취소","연속"]
[34,"서울","중부","능곡상암#1 T/L","상암S/S #4M.Tr 증설공사","상암S/S #4M.Tr 증설공사","2024-11-14 15:00","2024-11-15 18:00","취소","취소","연속"]
[35,"서울","중부","수색상암 T/L","154kV 수색상암T/L LA 도블점검","154kV 수색상암T/L LA 도블점검","2024-11-01 09:00","2024-11-01 16:00","2024-11-01 09:00","2024-11-01 16:00","연속"]
[36,"서울","중부","신촌순화 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 보통점검","2024-11-25 10:00","2024-11-26 18:00","2024-11-25 10:00","2024-11-26 18:00","매일"]
[37,"서울","중부","중부신촌 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 보통점검","2024-11-22 10:00","2024-11-22 18:00","2024-11-22 10:00","2024-11-22 18:00","연속"]
[38,"서울","중부","중부신촌 T/L","신촌S/S 154kV 장기사용 GIS 교체공사","신촌S/S 154kV 장기사용 GIS 교체공사 - 대상 : #4M.Tr 1차 GIS - 기타 : GIS~M.Tr 1차간 접속방법 변경(GIB to Power Cable)","2024-11-10 16:00","2024-11-10 18:00","2024-11-10 16:00","2024-11-10 18:00","연속"]
[39,"서울","중부","연대신촌 T/L","2024년 중부전력지사 170kV GIS 정밀점검","170kV GIS 보통점검","2024-11-11 10:00","2024-11-11 18:00","2024-11-11 10:00","2024-11-11 18:00","연속"]
[40,"서울","중부","중부신촌 T/L","신촌S/S 154kV 장기사용 GIS 교체공사","신촌S/S 154kV 장기사용 GIS 교체공사 - 대상 : #4M.Tr 1차 GIS - 기타 : GIS~M.Tr 1차간 접속방법 변경(GIB to Power Cable)","2024-11-18 18:00","2024-11-19 18:00","2024-11-18 18:00","2024-11-19 18:00","연속"]
[41,"서울","중부","중부신촌 T/L","신촌S/S 154kV 장기사용 GIS 교체공사","신촌S/S 154kV 장기사용 GIS 교체공사 - 대상 : #4M.Tr 1차 GIS - 기타 : GIS~M.Tr 1차간 접속방법 변경(GIB to Power Cable)","2024-11-28 18:00","2024-11-29 18:00","2024-11-28 18:00","2024-11-29 18:00","연속"]
[42,"서울","중부","중부용산#1 T/L","2024년 중부전력지사 변전정비 협력회사 총액공사","GIS 조작시험","2024-11-22 10:00","2024-11-22 18:00","2024-11-08 15:00","2024-11-08 18:00","연속"]
[43,"서울","직할","서대문세종로 T/L","24년 서울본부 직할 154kV GIS 정밀점검공사","154kV GIS 정밀점검공사","2024-11-04 09:00","2024-11-06 18:00","취소","취소","연속"]
[44,"서울","직할","용두S/S #2 BUS","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 인터록, 상체크 확인용 휴전","2024-11-29 09:00","2024-11-29 18:00","2024-11-29 09:00","2024-11-29 18:00","연속"]
[45,"서울","직할","용두S/S #1 BUS","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 설치 관련 #2BUS 휴전(도킹)","2024-11-25 09:00","2024-11-28 18:00","2024-11-25 09:00","2024-11-28 18:00","연속"]
[46,"서울","직할","용두안암#1 T/L","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 설치 관련 모선도킹시 무부하가압 시험가압선로","2024-11-20 09:00","2024-11-21 18:00","2024-11-20 09:00","2024-11-21 18:00","연속"]
[47,"서울","직할","용두S/S #2 BUS","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 설치 관련 #2BUS 휴전(도킹)","2024-11-18 09:00","2024-11-21 18:00","2024-11-18 09:00","2024-11-21 18:00","연속"]
[48,"서울","직할","용두안암#1 T/L","용두S/S 154kV #3M.Tr 증설공사","용두S/S 154kV #3M.Tr 1차 GIS 설치 관련 모선도킹시 무부하가압 시험가압선로","2024-11-28 09:00","2024-11-29 18:00","2024-11-28 09:00","2024-11-29 18:00","연속"]
[49,"남서울","강남","논일S/S #2 BUS","154kV 논일S/S #4M.Tr GIS 증설공사","○ 154kV 논일S/S #4M.Tr 1차 GIS 증설공사 - #2DS 시험을 위한 모선휴전","2024-11-25 09:00","2024-11-25 18:00","2024-11-25 09:00","2024-11-25 18:00","연속"]
[50,"남서울","강남","논일S/S #1 BUS","154kV 논일S/S #4M.Tr GIS 증설공사","○ 154kV 논일S/S #4M.Tr 1차 GIS 증설공사","2024-11-20 14:00","2024-11-23 18:00","2024-11-20 14:00","2024-11-23 18:00","연속"]
[51,"남서울","강남","논일S/S #2 BUS","154kV 논일S/S #4M.Tr GIS 증설공사","○ 154kV 논일S/S #4M.Tr 1차 GIS 증설공사","2024-11-18 09:00","2024-11-20 14:00","2024-11-18 09:00","2024-11-20 14:00","연속"]
[52,"남서울","강남","신사반포#2 T/L","강남P/O 170kV GIS 정밀점검공사","신사S/S 신사-반포#2T/L 정밀점검 반포S/S 신사-반포#2T/L 보통점검","2024-11-13 15:00","2024-11-15 18:00","2024-11-13 15:00","2024-11-15 18:00","연속"]
[53,"남서울","강남","신사반포#1 T/L","강남P/O 170kV GIS 정밀점검공사","신사S/S 신사-반포#1T/L 정밀점검 반포S/S 신사-반포#1T/L 보통점검","2024-11-11 09:00","2024-11-13 15:00","2024-11-11 09:00","2024-11-13 15:00","연속"]
[54,"남서울","강남","신사S/S #1 BUS","강남P/O 170kV GIS 정밀점검공사","신사S/S 정밀점검 관련 CB 무부하가압용","2024-11-09 10:00","2024-11-09 12:00","2024-11-09 10:00","2024-11-09 12:00","연속"]
[55,"남서울","강남","신양재신사#2 T/L","강남P/O 170kV GIS 정밀점검공사","신사S/S 신양재-신사#2T/L 정밀점검 신양재S/S 신양재-신사#2T/L 조작시험","2024-11-04 09:00","2024-11-07 15:00","2024-11-04 09:00","2024-11-07 15:00","연속"]
[56,"남서울","강남","신양재신사#3 T/L","세니온제 송전선로 보호반 성능개선","세니온제 송전선로 보호반 성능개선","2024-11-08 10:00","2024-11-08 18:00","2024-11-08 10:00","2024-11-08 18:00","연속"]
[57,"남서울","동서울","위례S/S SEC CB 65660","2024-2025년도 동서울전력지사 변전협력회사 총액공사","위례S/S 65-66 SEC GIS 보통점검","2024-11-11 09:00","2024-11-11 18:00","2024-11-11 09:00","2024-11-11 18:00","연속"]
[58,"남서울","동서울","위례S/S CB 6100","2024-2025년도 동서울전력지사 변전협력회사 총액공사","위례S/S 6100 BUS-TIE GIS 보통점검","2024-11-12 09:00","2024-11-12 18:00","2024-11-12 09:00","2024-11-12 18:00","연속"]
[59,"남서울","동서울","위례S/S CB 6200","2024-2025년도 동서울전력지사 변전협력회사 총액공사","위례S/S 6200 BUS-TIE GIS 보통점검","2024-11-13 09:00","2024-11-13 18:00","2024-11-13 09:00","2024-11-13 18:00","연속"]
[60,"남서울","동서울","위례S/S #61 BUS","2024-2025년도 동서울전력지사 변전협력회사 총액공사","위례S/S 60-61SEC GIS #2DS부 내부점검","2024-11-04 09:00","2024-11-05 18:00","2024-11-04 09:00","2024-11-05 18:00","연속"]
[61,"남서울","동서울","위례S/S SEC CB 60610","2024-2025년도 동서울전력지사 변전협력회사 총액공사","위례S/S 60-61SEC GIS #2DS부 내부점검","2024-11-04 09:00","2024-11-05 18:00","2024-11-04 09:00","2024-11-05 18:00","연속"]
[62,"남서울","영등포","구공대림#2 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 가산S/S #6M.Tr 1차 GIS -무부하가압용","2024-11-05 16:00","2024-11-05 18:00","2024-11-05 16:00","2024-11-05 18:00","연속"]
[63,"남서울","영등포","구공대림#2 T/L","24년도 영등포전력지사 154kV GIS 정밀점검공사","24년도 영등포전력지사 154kV GIS 정밀점검공사 대상 : 가산S/S #5M.Tr 1차 GIS - 무부하가압용","2024-11-07 16:00","2024-11-07 18:00","2024-11-07 16:00","2024-11-07 18:00","연속"]
[64,"남서울","영등포","시흥독산#1 T/L","2024~2025년 영등포전력지사 변전협력회사 총액공사","2024~2025년 영등포전력지사 변전협력회사 총액공사 공사내용: Air 누기관련 Drain V/V 불량교체","2024-11-12 09:00","2024-11-12 18:00","2024-11-12 09:00","2024-11-12 18:00","연속"]
[65,"남서울","영등포","온수소래 T/L","2024~2025년 영등포전력지사 변전협력회사 총액공사","온수SS 온수-소래T/L 전자변교체 및 조작시험","2024-11-09 09:00","2024-11-09 18:00","2024-11-16 09:00","2024-11-16 18:00","연속"]
[66,"남서울","영등포","천왕오류#1 T/L","2024~2025년 영등포전력지사 변전협력회사 총액공사","2024~2025년 영등포전력지사 변전협력회사 총액공사 공사내용 : 천왕-오류#1T/L 보호배전반 대체","2024-11-04 09:00","2024-11-06 14:00","2024-11-04 09:00","2024-11-06 14:00","연속"]
[67,"남서울","영등포","천왕오류#2 T/L","2024~2025년 영등포전력지사 변전협력회사 총액공사","2024~2025년 영등포전력지사 변전협력회사 총액공사 공사내용 : 천왕-오류#2T/L 보호배전반 대체","2024-11-06 14:00","2024-11-08 18:00","2024-11-06 14:00","2024-11-08 18:00","연속"]
[68,"남서울","영등포","화곡S/S CB 6100","2024~2025년 영등포전력지사 변전협력회사 총액공사","2024~2025년 영등포전력지사 변전협력회사 총액공사 공사내용 : GIS AC Fail 불량조치(러버히터 전원단자대 재시공)","2024-11-11 09:00","2024-11-11 18:00","2024-11-11 09:00","2024-11-11 18:00","연속"]
[69,"남서울","직할","신림봉천 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2024-11-02 09:00","2024-11-02 18:00","2024-11-02 09:00","2024-11-02 18:00","연속"]
[70,"인천","김포","경서북인천#2 T/L","'23~'24년 지중송전설비 위탁정비공사","맨홀점검","2024-11-04 08:00","2024-11-08 18:00","2024-11-04 08:00","2024-11-08 18:00","연속"]
[71,"인천","김포","경서북인천#1 T/L","'23~'24년 지중송전설비 위탁정비공사","맨홀점검","2024-11-04 08:00","2024-11-08 18:00","2024-11-04 08:00","2024-11-08 18:00","연속"]
[72,"인천","김포","김포장기#2 T/L","김포S/S 154kV 김포-장기#2T/L GIS 보통점검","김포S/S 154kV 김포-장기#2T/L GIS 보통점검","2024-11-21 10:00","2024-11-21 18:00","2024-11-21 10:00","2024-11-21 18:00","연속"]
[73,"인천","김포","김포불로#1 T/L","김포S/S 154kV 불로-김포#1T/L GIS 보통점검","김포S/S 154kV 불로-김포#1T/L GIS 보통점검","2024-11-17 09:00","2024-11-17 18:00","취소","취소","연속"]
[74,"인천","김포","김포장기#1 T/L","김포S/S 154kV 김포-장기#1T/L GIS 보통점검","김포S/S 154kV 김포-장기#1T/L GIS 보통점검","2024-11-15 10:00","2024-11-15 18:00","2024-11-15 10:00","2024-11-15 18:00","연속"]
[75,"인천","김포","계양불로#1 T/L","불로S/S 154kV 계양-불로#1T/L GIS 초기점검","불로S/S 154kV 계양-불로#1T/L GIS 초기점검","2024-11-16 09:00","2024-11-16 18:00","취소","취소","연속"]
[76,"인천","김포","양촌양곡#1 T/L","양곡S/S 154kV 양촌-양곡#1T/L GIS SA 혼용화 공사","양곡S/S 154kV 양촌-양곡#1T/L GIS SA 혼용화 공사 (병행)양촌S/S 154kV 양촌-양곡#1T/L GIS 보통점검 (병행)양곡S/S 154kV 양촌-양곡#1T/L GIS 보통점검 (병행)양촌S/S 154kV 양촌-양곡#1T/L 보호배전반 대체 (병행)양곡S/S 154kV 양촌-양곡#1T/L 보호배전반 대체","2024-11-06 09:00","2024-11-08 18:00","2024-11-16 09:00","2024-11-16 18:00","연속"]
[77,"인천","김포","신김포양곡#1 T/L","양곡S/S 154kV 신김포-양곡#1T/L GIS SA 혼용화 공사","양곡S/S 154kV 신김포-양곡#1T/L GIS SA 혼용화 공사 (병행)양촌S/S 154kV 신김포-양곡#1T/L GIS 보통점검 (병행)양곡S/S 154kV 신김포-양곡#1T/L GIS 보통점검","2024-11-01 09:00","2024-11-01 18:00","2024-11-23 09:00","2024-11-23 18:00","연속"]
[78,"인천","김포","양촌양곡#2 T/L","24-25년 가공송전 협력회사 공사 (추락방지시설 설치)","수평 추락방지시설 설치","2024-11-09 08:00","2024-11-10 18:00","2024-11-10 08:00","2024-11-10 18:00","연속"]
[79,"인천","부평","관교만수#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2024-11-15 09:00","2024-11-15 18:00","취소","취소","연속"]
[80,"인천","부평","관교만수#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2024-11-29 09:00","2024-11-29 18:00","2024-11-29 09:00","2024-11-29 18:00","연속"]
[81,"인천","부평","송월남인천#2 T/L","154kV 남인천-학익 등 2개T/L 지장이설 및 선종교체","케이블 선종교체 (OF 2,000㎟ → XLPE 2,000㎟)","2024-11-14 09:00","2024-11-15 09:00","2024-11-14 09:00","2024-11-15 09:00","연속"]
[82,"인천","부평","남인천S/S #2 BUS","154kV 남인천-학익 등 2개T/L 지장이설 및 선종교체","케이블 선종교체 (OF 2,000㎟ → XLPE 2,000㎟)","2024-11-14 09:00","2024-11-15 09:00","2024-11-14 09:00","2024-11-15 09:00","연속"]
[83,"인천","부평","남인천학익#1 T/L","남인천S/S 남인천학익#1 T/L GIS SA혼용화 공사","남인천S/S 남인천학익#1 T/L GIS SA혼용화 공사","2024-11-16 09:00","2024-11-16 18:00","2024-11-16 09:00","2024-11-16 18:00","연속"]
[84,"인천","부평","송현송월#2 T/L","송월S/S 송현-송월#2T/L GIS 조작시험","송월S/S 송현-송월#2T/L GIS 조작시험","2024-11-07 09:00","2024-11-07 18:00","2024-11-07 09:00","2024-11-07 18:00","연속"]
[85,"인천","부평","송현포스코CC#2 T/L","154kV 주안-관교 등 4개T/L EBG 가스채취밸브 설치공사","EBG 가스채취밸브 설치 및 스프링 유니트 점검 시행","2024-11-23 09:00","2024-11-25 18:00","취소","취소","연속"]
[86,"인천","부평","신가좌인천#3 T/L","인천S/S 154kV 신가좌-인천#3T/L GIS","인천S/S 154kV 신가좌-인천#3T/L GIS","2024-11-12 09:00","2024-11-12 18:00","2024-11-12 09:00","2024-11-12 18:00","연속"]
[87,"인천","부평","신가좌S/S SEC CB 66670","신가좌S/S 154kV #66-#67 SEC GIS 보통점검","신가좌S/S 154kV #66-#67 SEC GIS 보통점검","2024-11-11 09:00","2024-11-11 18:00","취소","취소","연속"]
[88,"인천","부평","신가좌S/S SEC CB 65660","신가좌S/S 154kV #65-#66 SEC 보통점검","신가좌S/S 154kV #65-#66 SEC 보통점검","2024-11-10 09:00","2024-11-10 18:00","취소","취소","연속"]
[89,"인천","부평","신가좌신현#1 T/L","154kV 남동-관교 등 4개 T/L 노후 피뢰기 교체공사","피뢰기 교체공사(3상)","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[90,"인천","부평","신가좌부개#2 T/L","23~24년 지중송전위탁정비공사","절연유 채취","2024-11-18 09:00","2024-11-19 18:00","취소","취소","연속"]
[91,"인천","부평","신가좌신현#2 T/L","154kV 남동-관교 등 4개 T/L 노후 피뢰기 교체공사","피뢰기 교체공사(3상)","2024-11-22 09:00","2024-11-22 18:00","2024-11-22 09:00","2024-11-22 18:00","연속"]
[92,"인천","부평","신가좌부개#1 T/L","23~24년 지중송전위탁정비공사","절연유 채취","2024-11-20 09:00","2024-11-22 18:00","취소","취소","연속"]
[93,"인천","부평","신가좌인천#1 T/L","신가좌S/S 154kV 신가좌인천#1T/L GIS 정밀점검","신가좌S/S 154kV 신가좌인천#1T/L GIS 정밀점검","2024-11-01 09:00","2024-11-03 18:00","2024-11-01 09:00","2024-11-03 18:00","연속"]
[94,"인천","부평","신경서S/S SEC CB 60610","신경서S/S 154kV #60-#61 SEC GIS 정밀점검","신경서S/S 154kV #60-#61 SEC GIS 정밀점검","2024-11-11 09:00","2024-11-13 18:00","2024-11-11 09:00","2024-11-13 18:00","연속"]
[95,"인천","부평","신경서S/S #60 BUS","신경서S/S #60-#61 SEC GIS 정밀점검 관련 무부하가압","신경서S/S #60-#61 SEC GIS 정밀점검 관련 무부하가압","2024-11-13 09:00","2024-11-13 18:00","2024-11-13 09:00","2024-11-13 18:00","연속"]
[96,"인천","부평","신경서경서#3 T/L","신경서S/S #60-#61 SEC GIS 정밀점검 관련 무부하가압","신경서S/S #60-#61 SEC GIS 정밀점검 관련 무부하가압","2024-11-13 09:00","2024-11-13 18:00","2024-11-13 09:00","2024-11-13 18:00","연속"]
[97,"인천","부평","주안만수#1 T/L","주안S/S 주안만수#1T/L GIS 보통점검","주안S/S 주안만수#1T/L GIS 보통점검","2024-11-30 14:00","2024-11-30 18:00","2024-11-30 14:00","2024-11-30 18:00","연속"]
[98,"인천","부평","관교주안 T/L","주안S/S 154kV 주안관교 T/L GIS 모자익 배선 철거","주안S/S 154kV 주안관교 T/L GIS 모자익 배선 철거","2024-11-30 09:00","2024-11-30 14:00","2024-11-30 09:00","2024-11-30 14:00","연속"]
[99,"인천","부평","주안S/S CB 6100","주안S/S 154kV #1-#2 BUS TIE GIS 모자익 배선 철거","주안S/S 154kV #1-#2 BUS TIE GIS 모자익 배선 철거 및 보통점검","2024-11-24 09:00","2024-11-24 18:00","2024-11-24 09:00","2024-11-24 18:00","연속"]
[100,"인천","부평","신가좌주안#2 T/L","주안S/S 154kV 신가좌-주안#2T/L GIS 모자익 배선 철거","주안S/S 154kV 신가좌-주안#2T/L GIS 모자익 배선 철거","2024-11-17 14:00","2024-11-17 18:00","취소","취소","연속"]
[101,"인천","부평","신가좌주안#1 T/L","주안S/S 154kV 신가좌-주안#1T/L GIS 모자익 배선 철거","주안S/S 154kV 신가좌-주안#1T/L GIS 모자익 배선 철거","2024-11-17 09:00","2024-11-17 14:00","취소","취소","연속"]
[102,"인천","부평","학익S/S #2 BUS","154kV 남인천-학익 등 2개T/L 지장이설 및 선종교체","케이블 선종교체 (OF 2,000㎟ → XLPE 2,000㎟)","2024-11-14 09:00","2024-11-15 09:00","2024-11-14 09:00","2024-11-15 09:00","연속"]
[103,"인천","시흥","남동동춘 T/L","남동S/S 154kV 남동동춘T/L GIS 조작시험","남동S/S 154kV 남동동춘T/L GIS 조작시험 - 세니온제 보호IED 성능개선 병행","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[104,"인천","시흥","신시흥남동#1 T/L","남동S/S 154kV 신시흥남동#1T/L GIS 조작시험","남동S/S 154kV 신시흥남동#1T/L GIS 조작시험","2024-11-16 09:00","2024-11-16 12:00","취소","취소","연속"]
[105,"인천","시흥","신시흥남동#2 T/L","남동S/S 154kV 신시흥남동#2T/L GIS 조작시험","남동S/S 154kV 신시흥남동#2T/L GIS 조작시험","2024-11-16 12:00","2024-11-16 15:00","취소","취소","연속"]
[106,"인천","시흥","오봉남동#1 T/L","대한전선제 EBG 가스채취밸브 보강공사","대한전선제 EBG 가스채취밸브 보강공사","2024-11-18 08:00","2024-11-20 18:00","2024-11-18 08:00","2024-11-20 18:00","연속"]
[107,"인천","시흥","오봉남동#2 T/L","대한전선제 EBG 가스채취밸브 보강공사","대한전선제 EBG 가스채취밸브 보강공사","2024-11-21 08:00","2024-11-23 18:00","2024-11-21 08:00","2024-11-23 18:00","연속"]
[108,"인천","시흥","남시화남정왕#1 T/L","남정왕 154kV 남시화남정왕#1T/L 세니온제 제어IED 성능개선","남정왕 154kV 남시화남정왕#1T/L 세니온제 제어IED 성능개선 - 세니온제 보호IED 성능개선 병행","2024-11-13 09:00","2024-11-13 18:00","2024-11-13 09:00","2024-11-13 18:00","연속"]
[109,"인천","시흥","신시화남정왕#1 T/L","154kV 남정왕S/S #3M.Tr 증설공사","154kV #3M.Tr 무부하가압 및 상체크","2024-11-22 09:00","2024-11-23 18:00","2024-11-22 09:00","2024-11-23 18:00","연속"]
[110,"인천","시흥","도림오봉#1 T/L","케이블타워 피뢰기교체공사 및 EBA 절연유 채취","- C/T 피뢰기교체 및 EBA 절연유 채취","2024-11-25 08:00","2024-11-26 18:00","취소","취소","연속"]
[111,"인천","시흥","도림오봉#2 T/L","케이블타워 피뢰기교체공사 및 EBA 절연유 채취","- C/T 피뢰기교체 및 EBA 절연유 채취","2024-11-27 08:00","2024-11-28 18:00","취소","취소","연속"]
[112,"인천","시흥","서안양소래 T/L","광명시흥 일반산업단지 송전선로 이설공사","* 철탑 5기 설치, 기설철탑 6기 철거","2024-11-07 07:00","2024-11-11 18:00","취소","취소","연속"]
[113,"인천","시흥","서서울#2소래 T/L","광명시흥 일반산업단지 송전선로 이설공사","* 철탑 5기 설치, 기설철탑 6기 철거","2024-11-01 07:00","2024-11-06 18:00","2024-11-01 07:00","2024-11-06 18:00","연속"]
[114,"인천","시흥","신시흥도림#1 T/L","신시흥S/S 154kV 신시흥도림#1T/L GIS 조작시험","신시흥S/S 154kV 신시흥도림#1T/L GIS 조작시험","2024-11-16 15:00","2024-11-16 18:00","취소","취소","연속"]
[115,"인천","직할","계양원창 T/L","효성도시개발지구 지장선로 이설","철탑 1기 철거 및 이설","2024-11-16 07:00","2024-11-23 18:00","취소","취소","연속"]
[116,"인천","직할","계양북인천 T/L","효성도시개발지구 지장선로 이설","철탑 1기 철거 및 이설","2024-11-24 07:00","2024-11-30 18:00","취소","취소","연속"]
[117,"인천","직할","신부평고강#2 T/L","3기신도시 부천대장주택지구 지장철탑 이설공사","* 철탑 14기 및 전선 이설","2024-11-09 07:00","2024-11-09 18:00","2024-11-09 07:00","2024-11-09 18:00","연속"]
[118,"인천","직할","신부평고강#1 T/L","3기신도시 부천대장주택지구 지장철탑 이설공사","* 철탑 14기 및 전선 이설","2024-11-10 07:00","2024-11-10 18:00","2024-11-10 07:00","2024-11-10 18:00","연속"]
[119,"인천","직할","부천도당#2 T/L","154kV 도당S/S #4M.Tr 증설공사","도당S/S 170kV GIS(#4M.Tr 1차) 무부하가압","2024-11-06 09:00","2024-11-07 09:00","2024-11-06 09:00","2024-11-07 09:00","연속"]
[120,"인천","직할","부천도당#2 T/L","154kV 도당S/S #4M.Tr 증설공사","도당S/S 170kV GIS(#4M.Tr 1차) 무부하가압","2024-11-12 09:00","2024-11-13 09:00","2024-11-12 09:00","2024-11-13 09:00","연속"]
[121,"인천","직할","부흥S/S #60 BUS","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 부흥-원미T/L 무부하가압","2024-11-15 09:00","2024-11-16 09:00","2024-11-15 09:00","2024-11-16 09:00","연속"]
[122,"인천","직할","부흥부개#2 T/L","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 무부하가압","2024-11-15 09:00","2024-11-17 18:00","2024-11-15 09:00","2024-11-17 18:00","연속"]
[123,"인천","직할","부흥S/S #65 BUS","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 부흥-원미T/L 무부하가압","2024-11-16 09:00","2024-11-17 09:00","2024-11-16 09:00","2024-11-17 09:00","연속"]
[124,"인천","직할","중동S/S 부천복합 #3G/T CB 6313","중동S/S 154kV G/T#3 GIS 보통점검","중동S/S 154kV G/T#3 GIS 보통점검","2024-11-18 09:00","2024-11-18 18:00","2024-11-18 09:00","2024-11-18 18:00","연속"]
[125,"인천","직할","중동화곡#2 T/L","3기신도시 부천대장주택지구 지장철탑 이설공사","* 철탑 14기 및 전선 이설","2024-11-17 07:00","2024-11-17 18:00","2024-11-17 07:00","2024-11-17 18:00","연속"]
[126,"인천","직할","중동화곡#1 T/L","3기신도시 부천대장주택지구 지장철탑 이설공사","* 철탑 14기 및 전선 이설","2024-11-16 07:00","2024-11-16 18:00","2024-11-16 07:00","2024-11-16 18:00","연속"]
[127,"인천","직할","부흥S/S CB 6100"," 154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 모선보호반 내부회로 증설","2024-11-04 09:00","2024-11-05 18:00","2024-11-04 09:00","2024-11-05 18:00","연속"]
[128,"인천","직할","원미S/S #1 BUS","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 무부하가압","2024-11-15 09:00","2024-11-16 09:00","2024-11-15 09:00","2024-11-16 09:00","연속"]
[129,"인천","직할","원미S/S #2 BUS","154kV 부흥-원미T/L SW 증설공사","154kV 부흥-원미T/L SW 증설공사 관련 무부하가압","2024-11-16 09:00","2024-11-17 09:00","2024-11-16 09:00","2024-11-17 09:00","연속"]
[130,"인천","직할","도당S/S #61 BUS","154kV 도당S/S #4M.Tr 증설공사","도당S/S 170kV GIS(#4M.Tr 1차) 무부하가압","2024-11-04 09:00","2024-11-07 09:00","2024-11-04 09:00","2024-11-07 09:00","연속"]
[131,"인천","직할","도당S/S #66 BUS","154kV 도당S/S #4M.Tr 증설공사","도당S/S 170kV GIS(#4M.Tr 1차) 무부하가압","2024-11-07 09:00","2024-11-13 09:00","2024-11-07 09:00","2024-11-13 09:00","연속"]
[132,"인천","시흥","남정왕S/S #61 BUS","154kV 남정왕S/S #3M.Tr 증설공사","154kV #3M.Tr 무부하가압 및 상체크","2024-11-22 13:00","2024-11-23 18:00","2024-11-22 13:00","2024-11-23 18:00","연속"]
[133,"인천","시흥","남정왕S/S #66 BUS","154kV 남정왕S/S #3M.Tr 증설공사","154kV #3M.Tr 무부하가압 및 상체크","2024-11-22 09:00","2024-11-22 13:00","2024-11-22 09:00","2024-11-22 13:00","연속"]
[134,"경기북부","고양","덕이호수#1 T/L","24-25 변전협력 총액공사","170kV GIS 점검","2024-11-04 09:00","2024-11-04 18:00","2024-11-07 09:00","2024-11-07 18:00","연속"]
[135,"경기북부","구리","가평청평HP#1 T/L","24~25년 구리전력 가공송전협력공사_피뢰기 설치","송전선로용 피뢰기 설치","2024-11-04 08:00","2024-11-04 18:00","2024-11-04 08:00","2024-11-04 18:00","연속"]
[136,"경기북부","구리","구리S/S #1 BUS","154kV 미금-구리#3T/L 증설공사","○154kV GIS 이설 × 1CCT(미금S/S →구리S/S) - 기존 미금 아리수#2T/L 활용 ○ #1BUS ~ 차단부 무부하 가압","2024-11-27 09:00","2024-11-28 18:00","취소","취소","연속"]
[137,"경기북부","구리","미금구리#1 T/L","154kV 미금-구리#3T/L 증설공사","○ #1BUS 무부하 가압선로 ○154kV GIS 이설 × 1CCT(미금S/S →구리S/S) - 기존 미금 아리수#2T/L 활용 ○ 증설구간 #1BUS 대체, #1DS 및 차단부 설치","2024-11-27 09:00","2024-11-28 18:00","취소","취소","연속"]
[138,"경기북부","구리","미금구리#2 T/L","154kV 미금-구리#3T/L 증설공사","○ #2BUS 무부하 가압선로 ○154kV GIS 이설 × 1CCT(미금S/S →구리S/S) - 기존 미금 아리수#2T/L 활용 ○ 증설구간 #2BUS 대체, #2DS 설치","2024-11-22 09:00","2024-11-23 18:00","취소","취소","연속"]
[139,"경기북부","구리","구리S/S #2 BUS","154kV 미금-구리#3T/L 증설공사","○154kV GIS 이설 × 1CCT(미금S/S →구리S/S) - 기존 미금 아리수#2T/L 활용 - 무부하 가압 포함","2024-11-20 09:00","2024-11-23 18:00","2024-11-18 09:00","2024-11-22 18:00","연속"]
[140,"경기북부","구리","미금구리#1 T/L","154kV 미금-구리#3T/L 증설공사","○ #1BUS 무부하 가압선로 ○154kV GIS 이설 × 1CCT(미금S/S →구리S/S) - 기존 미금 아리수#2T/L 활용 ○ 증설구간 #1BUS 대체, #1DS 및 차단부 설치","2024-11-18 09:00","2024-11-19 18:00","취소","취소","연속"]
[141,"경기북부","구리","구리S/S #1 BUS","154kV 미금-구리#3T/L 증설공사","○154kV GIS 이설 × 1CCT(미금S/S →구리S/S) - 기존 미금 아리수#2T/L 활용 ○ 증설구간 #1BUS 대체, #1DS 및 차단부 설치","2024-11-12 09:00","2024-11-19 18:00","2024-11-11 09:00","2024-11-16 18:00","연속"]
[142,"경기북부","구리","내촌용정#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","-불량애자교체","2024-11-20 13:00","2024-11-20 18:00","2024-11-20 13:00","2024-11-20 18:00","연속"]
[143,"경기북부","구리","내촌용정#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 피뢰기설치","2024-11-15 13:00","2024-11-20 13:00","2024-11-15 13:00","2024-11-20 13:00","연속"]
[144,"경기북부","구리","신장덕소#1 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 금구류 교체","2024-11-21 09:00","2024-11-21 18:00","2024-11-21 09:00","2024-11-21 18:00","연속"]
[145,"경기북부","구리","덕소진건#2 T/L","덕소S/S #4M.Tr 증설공사","덕소S/S #4M.Tr 증설공사 - 최종 무부하가압","2024-11-18 10:00","2024-11-19 10:00","2024-11-18 10:00","2024-11-19 10:00","연속"]
[146,"경기북부","구리","덕소마석#2 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 금구류 교체","2024-11-28 09:00","2024-11-28 18:00","2024-11-28 09:00","2024-11-28 18:00","연속"]
[147,"경기북부","구리","덕소마석#1 T/L","23~24년 직할 지중송전설비 위탁정비공사","C/T 금구류 교체","2024-11-27 09:00","2024-11-27 18:00","2024-11-27 09:00","2024-11-27 18:00","연속"]
[148,"경기북부","구리","미금S/S #66 BUS","154kV 미금-구리#3T/L 증설공사","○154kV GIS 이설 × 1CCT(미금S/S →구리S/S) - 기존 미금 아리수#2T/L 활용 ○ #2DS 철거 및 모선마감","2024-11-04 09:00","2024-11-05 18:00","2024-11-04 09:00","2024-11-05 18:00","연속"]
[149,"경기북부","구리","별내장암 T/L","23~24년 직할 지중송전설비 위탁정비공사","EBA 절연유 채유","2024-11-07 09:00","2024-11-07 18:00","2024-11-07 09:00","2024-11-07 18:00","연속"]
[150,"경기북부","구리","신포천동두천#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 신포천-포천#1T/L 압축인류클램프 교체 병가구간","2024-11-11 07:00","2024-11-11 18:00","2024-11-11 07:00","2024-11-11 18:00","연속"]
[151,"경기북부","구리","신포천덕계#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","ㅇ 피뢰기 설치 - 대상 : 154kV 백석-덕계#1T/L No.22~28(병가구간)","2024-11-22 07:00","2024-11-22 18:00","2024-11-22 07:00","2024-11-22 18:00","연속"]
[152,"경기북부","구리","신포천포천#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 신포천-동두천#1T/L 압축인류클램프 교체 병가구간","2024-11-12 07:00","2024-11-12 18:00","2024-11-12 07:00","2024-11-12 18:00","연속"]
[153,"경기북부","구리","신포천백학#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신포천-백학#2T/L No.4,5","2024-11-20 07:00","2024-11-20 18:00","2024-11-20 07:00","2024-11-20 18:00","연속"]
[154,"경기북부","구리","신포천동두천#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 압축인류클램프 교체","2024-11-12 07:00","2024-11-12 18:00","2024-11-12 07:00","2024-11-12 18:00","연속"]
[155,"경기북부","구리","용문S/S #1 BUS","용문S/S 154kV 장기사용 GIS 교체공사(2차분)","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 모선 휴전순서 : #60 → #65 → #60 → #65BUS ○ 휴전사유 : #60BUS 신규 벨로우즈 설치","2024-11-20 09:00","2024-11-22 18:00","2024-11-20 09:00","2024-11-22 18:00","연속"]
[156,"경기북부","구리","곤지암용문#1 T/L","용문S/S 154kV 장기사용 GIS 교체공사(2차분) 이격거리 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) 이격거리 휴전 ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 휴전사유 : 곤지암-용문#2T/L 월부싱 설치 시 이격거리 휴전 필요(곤지암-용문#1T/L)","2024-11-23 09:00","2024-11-23 13:00","2024-11-23 09:00","2024-11-23 18:00","연속"]
[157,"경기북부","구리","지제용문#2 T/L","용문S/S 154kV GIS 교체공사(2차분) 건전성 확인 시험가압","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) 건전성 확인 시험가압 ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 휴전사유 : #2BUS 벨로우즈 철거 후 엔드커버 설치, 기존 #2BUS(엔드커버 설치부위) 건전성 확인을 위해 시험가압","2024-11-10 16:00","2024-11-11 09:00","2024-11-10 16:00","2024-11-11 09:00","연속"]
[158,"경기북부","구리","곤지암용문#1 T/L","용문S/S 154kV 장기사용 GIS 교체공사(2차분) 이격거리 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) 이격거리 휴전 ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 휴전사유 : 곤지암-용문#2T/L 월부싱, 외장형 LA 철거 시 이격거리 휴전 필요(곤지암-용문#1T/L)","2024-11-09 09:00","2024-11-09 13:00","2024-11-09 09:00","2024-11-09 16:00","연속"]
[159,"경기북부","구리","지제용문#2 T/L","용문S/S 154kV GIS 교체공사(2차분) 건전성 확인 시험가압","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) 건전성 확인 시험가압 ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 휴전사유 : #1BUS 벨로우즈 철거 후 엔드커버 설치, 기존 #1BUS(엔드커버 설치부위) 건전성 확인을 위해 시험가압","2024-11-08 16:00","2024-11-09 09:00","2024-11-08 16:00","2024-11-09 09:00","연속"]
[160,"경기북부","구리","지제용문#2 T/L","용문S/S 154kV 장기사용 GIS 교체공사(2차분) 시험가압 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) 시험가압 휴전 ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 휴전사유 : #2BUS 신규 GIS 시험가압 진행하기 위해 무부하가압용 T/L 필요(지제-용문#2T/L)","2024-11-26 15:00","2024-11-27 15:00","2024-11-26 15:00","2024-11-27 15:00","연속"]
[161,"경기북부","구리","용문S/S #1 BUS","용문S/S 154kV 장기사용 GIS 교체공사(2차분)","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 모선 휴전순서 : #60 → #65 → #60 → #65BUS ○ 휴전사유 : #60BUS 임시 벨로우즈 철거","2024-11-07 09:00","2024-11-09 09:00","2024-11-07 09:00","2024-11-09 09:00","연속"]
[162,"경기북부","구리","곤지암용문#2 T/L","용문S/S 154kV 장기사용 GIS 교체공사(2차분)","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 모선 휴전순서 : #60 → #65 → #60 → #65BUS ○ 휴전사유 : 154kV GIS 교체","2024-11-07 09:00","2024-11-27 18:00","2024-11-07 09:00","2024-11-27 18:00","연속"]
[163,"경기북부","구리","지제용문#2 T/L","용문S/S 154kV 장기사용 GIS 교체공사(2차분) 시험가압 휴전","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) 시험가압 휴전 ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 휴전사유 : #1BUS 신규 GIS 시험가압 진행하기 위해 무부하가압용 T/L 필요(지제-용문#2T/L)","2024-11-21 15:00","2024-11-22 15:00","2024-11-21 15:00","2024-11-22 15:00","연속"]
[164,"경기북부","구리","용문S/S #2 BUS","용문S/S 154kV 장기사용 GIS 교체공사(2차분)","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 모선 휴전순서 : #60 → #65 → #60 → #65BUS ○ 휴전사유 : #65BUS 신규 벨로우즈 설치","2024-11-25 09:00","2024-11-27 18:00","2024-11-25 09:00","2024-11-27 18:00","연속"]
[165,"경기북부","구리","용문S/S #2 BUS","용문S/S 154kV 장기사용 GIS 교체공사(2차분)","□ 용문S/S 154kV 장기사용 GIS 교체공사(2차분) ○ 2차분 교체개소 : #1M.Tr 1차, 곤지암-용문#2T/L ○ 모선 휴전순서 : #60 → #65 → #60 → #65BUS ○ 휴전사유 : #65BUS 임시 벨로우즈 철거","2024-11-09 09:00","2024-11-11 09:00","2024-11-09 09:00","2024-11-11 09:00","연속"]
[166,"경기북부","구리","지제용문#1 T/L","24~25년 구리송전협력회사공사_피뢰기설치","송전선로용 피뢰기 설치","2024-11-28 08:00","2024-12-04 18:00","2024-11-28 08:00","2024-12-04 18:00","연속"]
[167,"경기북부","구리","청평HP의암HP T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","154kV 청평-의암 추락방지시설 설치 : 36기","2024-11-27 07:00","2024-12-02 18:00","2024-11-27 07:00","2024-12-02 18:00","매일"]
[168,"경기북부","구리","청평H/P #2 M.TR 2차 CB","24-25년 구리전력지사 변전협력회사 총액공사","#2BUS CVT, LA 보통점검, 모선점검","2024-11-05 14:00","2024-11-05 18:00","2024-11-05 14:00","2024-11-05 18:00","연속"]
[169,"경기북부","구리","용정포천#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","-불량애자교체","2024-11-20 07:00","2024-11-20 18:00","2024-11-20 07:00","2024-11-20 18:00","연속"]
[170,"경기북부","구리","포천운천#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","-지지애자교체","2024-11-15 07:00","2024-11-15 13:00","2024-11-15 07:00","2024-11-15 13:00","연속"]
[171,"경기북부","구리","신포천포천#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 압축인류클램프 교체 및 가공지선 보수","2024-11-08 07:00","2024-11-11 18:00","2024-11-08 07:00","2024-11-11 18:00","연속"]
[172,"경기북부","구리","포천운천#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 피뢰기설치공사","2024-11-01 07:00","2024-11-08 18:00","취소","취소","연속"]
[173,"경기북부","직할","녹양백석#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","ㅇ 피뢰기설치 - 대상 : 154kV 백석-덕계#1T/L No.1~8","2024-11-21 07:00","2024-11-21 18:00","2024-11-21 07:00","2024-11-21 18:00","연속"]
[174,"경기북부","직할","백석덕계#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","-피뢰기설치공사","2024-11-21 07:00","2024-11-22 18:00","2024-11-21 07:00","2024-11-22 18:00","연속"]
[175,"경기북부","직할","신의정부내촌#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지시설 설치 - 대상 : 154V 신의정부-내촌#2T/L No.5,7,9~23","2024-11-15 07:00","2024-11-19 18:00","2024-11-15 07:00","2024-11-19 18:00","연속"]
[176,"경기북부","직할","신의정부내촌#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 154kV 신의정부-내촌#1T/L No.5,7,9~23","2024-11-21 07:00","2024-11-25 18:00","2024-11-21 07:00","2024-11-25 18:00","연속"]
[177,"경기북부","직할","신의정부송우#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","- 가공지선보수","2024-11-13 07:00","2024-11-13 18:00","2024-11-13 07:00","2024-11-13 18:00","연속"]
[178,"경기북부","직할","옥정송우#2 T/L","23~24년 직할 지중송전설비 위탁정비공사","EBA 절연유 채유","2024-11-05 09:00","2024-11-05 18:00","2024-11-05 09:00","2024-11-05 18:00","연속"]
[179,"경기북부","고양","백학남면#1 T/L"," 24~25년 경기북부 직할 가공송전협력회사 공사 ","피뢰기설치공사 ","2024-11-25 07:00","2024-11-28 18:00","2024-11-25 07:00","2024-11-28 18:00","연속"]
[180,"경기북부","고양","신포천백학#2 T/L"," 24~25년 경기북부 직할 가공송전협력회사 공사 ","피뢰기설치공사 병가구간 ","2024-11-26 07:00","2024-11-26 18:00","2024-11-26 07:00","2024-11-26 18:00","연속"]
[181,"경기","군포","목내성곡#1 T/L","목내S/S 목내-성곡#1T/L GIS 조작시험","목내S/S 목내-성곡#1T/L GIS 조작시험","2024-11-25 09:00","2024-11-25 14:00","2024-11-25 09:00","2024-11-25 14:00","연속"]
[182,"경기","군포","목내성곡#2 T/L","목내S/S 목내-성곡#2T/L GIS 조작시험","목내S/S 목내-성곡#2T/L GIS 조작시험","2024-11-25 14:00","2024-11-25 18:00","2024-11-25 14:00","2024-11-25 18:00","연속"]
[183,"경기","군포","산본안양#1 T/L","[GIS 정밀점검]산본S/S 산본-안양#1T/L GIS 정밀점검","산본S/S 산본-안양#1T/L GIS 정밀점검 시행","2024-11-04 09:00","2024-11-06 18:00","2024-11-04 09:00","2024-11-06 18:00","연속"]
[184,"경기","군포","서서울산본#2 T/L","[GIS 정밀점검]산본S/S 서서울-산본#2T/L GIS 정밀점검","산본S/S 서서울-산본#2T/L GIS 정밀점검 시행","2024-11-07 09:00","2024-11-08 18:00","2024-11-07 09:00","2024-11-08 18:00","연속"]
[185,"경기","군포","서서울#2서안양 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","추락방지장치(수평)설치 No.76~82 (7기), 소래C/T 추락방지 수직레일 설치, 성능저하 애자련 교체 No.76,86 (2기)","2024-11-23 07:30","2024-11-23 18:00","2024-11-23 07:30","2024-11-23 18:00","매일"]
[186,"경기","군포","시화성곡 T/L","성곡S/S, 시화S/S 시화-성곡T/L GIS 보통점검 및 조작시험","성곡S/S, 시화S/S 시화-성곡T/L GIS 보통점검 및 조작시험","2024-11-01 09:00","2024-11-01 18:00","2024-11-01 09:00","2024-11-01 18:00","연속"]
[187,"경기","군포","시화중시화 T/L","시화,중시화SS 시화-중시화T/L GIS 세니온 성능개선","시화,중시화SS 송전선로보호반(단거리) 세니온 성능개선(F/W 업데이트)","2024-11-04 09:00","2024-11-04 18:00","2024-11-04 09:00","2024-11-04 18:00","연속"]
[188,"경기","동부","이천가남#1 T/L","가남S/S 154kV #4M.Tr 증설공사","#4M.tr 무부하가압 및 상체크","2024-11-11 09:00","2024-11-12 18:00","2024-11-11 09:00","2024-11-12 18:00","연속"]
[189,"경기","동부","곤지암율현#2 T/L","2024년 가공송전 순시점검 위탁공사","과열개소 보수(압축인류클램프) 154kV 곤지암-이천#2T/L과 병가구간","2024-11-13 09:00","2024-11-13 18:00","취소","취소","연속"]
[190,"경기","동부","곤지암이천#2 T/L","2024년 가공송전 순시점검 위탁공사","과열개소 보수(압축인류클램프) - 안전이격 휴전 154kV 곤지암-율현#2T/L과 병가구간","2024-11-13 09:00","2024-11-13 18:00","취소","취소","연속"]
[191,"경기","동부","오포모현#1 T/L","24-25년 동부 변전협력총액공사","모현:오포-모현#1TL(보통)","2024-11-01 09:00","2024-11-01 18:00","취소","취소","연속"]
[192,"경기","동부","분당오포#1 T/L","24-25년 동부 변전협력총액공사","분당-오포#1TL 모선보호반대체 분당:분당-오포#1TL(보통),LA(보통)","2024-11-18 09:00","2024-11-20 18:00","2024-11-18 09:00","2024-11-20 18:00","연속"]
[193,"경기","동부","분당S/S CB 6200","24-25년 동부 변전협력총액공사","분당:6200(하자),효성제 GIS 발청조치","2024-11-05 09:00","2024-11-05 18:00","2024-11-05 09:00","2024-11-05 18:00","연속"]
[194,"경기","동부","성현분당#1 T/L","24-25 동부전력지사 송전협력회사 공사","수평 추락방지장치 설치공사(1~41호, 야탑-성현#1T/L과 8기 병가)","2024-11-04 07:30","2024-11-05 18:00","2024-11-04 07:30","2024-11-05 18:00","연속"]
[195,"경기","동부","성현분당#2 T/L","24-25 동부전력지사 송전협력회사 공사","수평 추락방지장치 설치공사(1~41호, 야탑-성현#2T/L과 8기 병가)","2024-11-06 07:30","2024-11-07 18:00","2024-11-06 07:30","2024-11-07 18:00","연속"]
[196,"경기","동부","왕암여주#1 T/L","24-25년 동부 변전협력총액공사","효성제 GIS 발청 여주:왕암-여주#1,2TL","2024-11-21 09:00","2024-11-21 14:00","2024-11-21 09:00","2024-11-21 14:00","연속"]
[197,"경기","동부","왕암여주#2 T/L","24-25년 동부 변전협력총액공사","효성제 GIS 발청 여주:왕암-여주#1,2TL","2024-11-21 14:00","2024-11-21 18:00","2024-11-21 14:00","2024-11-21 18:00","연속"]
[198,"경기","동부","오천율현#2 T/L","24-25년 동부 변전협력총액공사","오천:오천-율현#2T/L(보통) 율현:오천-율현#2T/L(보통)","2024-11-15 09:00","2024-11-15 18:00","2024-11-15 09:00","2024-11-15 18:00","연속"]
[199,"경기","동부","중원야탑 T/L","23-24년 지중송전설비 위탁정비공사(성남전력지사)","대한전선 열경화공법 EBG 가스채취밸브 설치","2024-11-04 08:00","2024-11-07 18:00","2024-11-04 08:00","2024-11-07 18:00","연속"]
[200,"경기","동부","곤지암초월#2 T/L","24-25년 동부 변전협력총액공사","초월:6100(정밀) 무부하가압용","2024-11-02 14:00","2024-11-02 18:00","2024-11-02 14:00","2024-11-02 18:00","연속"]
[201,"경기","동부","초월S/S CB 6100","24-25년 동부 변전협력총액공사","초월:6100(정밀)","2024-11-01 09:00","2024-11-02 18:00","2024-11-01 09:00","2024-11-02 18:00","연속"]
[202,"경기","성남","기흥신갈#1 T/L","23-24년 지중송전설비 위탁정비공사(성남전력지사)","피뢰기 점검","2024-11-18 09:00","2024-11-18 18:00","2024-11-18 09:00","2024-11-18 18:00","연속"]
[203,"경기","성남","남사동탄#2 T/L","2024년 성남전력 345, 154 GIS 보통점검공사","GIS 보통점검","2024-11-01 14:00","2024-11-01 18:00","2024-11-01 14:00","2024-11-01 18:00","연속"]
[204,"경기","성남","남사동탄#1 T/L","2024년 성남전력 345, 154 GIS 보통점검공사","GIS 보통점검","2024-11-01 09:00","2024-11-01 14:00","2024-11-01 09:00","2024-11-01 14:00","연속"]
[205,"경기","성남","덕성남사#2 T/L","덕성S/S 덕성남사#2T/L GIS 누기보수","GIS 누기보수","2024-11-06 14:00","2024-11-07 18:00","2024-11-06 14:00","2024-11-07 18:00","연속"]
[206,"경기","성남","진위동탄#1 T/L","추락방지장치(수평) 설치공사","154kV 동탄-진위#1T/L 12기","2024-11-18 08:00","2024-11-19 18:00","취소","취소","연속"]
[207,"경기","성남","진위동탄#2 T/L","추락방지장치(수평) 설치공사","154kV 동탄-진위#2T/L 12기","2024-11-20 08:00","2024-11-21 18:00","취소","취소","연속"]
[208,"경기","성남","기흥신갈#2 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","소도체 이도조정","2024-11-22 07:00","2024-11-22 18:00","2024-11-22 07:00","2024-11-22 18:00","연속"]
[209,"경기","성남","신성남서판교#3 T/L","세니온제 송전선로 보호반 성능개선","세니온제 IED 성능개선","2024-11-07 09:00","2024-11-07 18:00","2024-11-07 09:00","2024-11-07 18:00","연속"]
[210,"경기","성남","신수원S/S SEC CB 66670","2024년 성남전력 변전협력회사 총액공사","GIS 조작시험","2024-11-01 14:00","2024-11-01 18:00","취소","취소","연속"]
[211,"경기","성남","신수원S/S CB 6300","2024년 성남전력 변전협력회사 총액공사","GIS 조작시험","2024-11-01 09:00","2024-11-01 14:00","취소","취소","연속"]
[212,"경기","성남","신수원S/S #60 BUS","신수원S/S 154kV 동반T/L GIS 교체공사","154kV 동반#1T/L GIS 교체 - 1DS,60BUS,CB 철거 및 설치","2024-11-30 14:00","2024-12-05 14:00","2024-11-30 14:00","2024-12-05 14:00","연속"]
[213,"경기","성남","신수원S/S #65 BUS","신수원S/S 154kV 동반T/L GIS 교체공사","154kV 동반#1T/L GIS 교체 - 2DS, 상부BUS 철거","2024-11-28 09:00","2024-11-30 14:00","2024-11-28 09:00","2024-11-30 14:00","연속"]
[214,"경기","성남","신수원S/S #65 BUS","신수원S/S 154kV 동반T/L GIS 교체공사","154kV 동반#2T/L 무부하가압","2024-11-21 14:00","2024-11-22 14:00","2024-11-21 14:00","2024-11-22 14:00","연속"]
[215,"경기","성남","신수원S/S SEC CB 60610","2024년 성남전력 변전협력회사 총액공사","GIS 보통점검","2024-11-13 09:00","2024-11-13 18:00","취소","취소","연속"]
[216,"경기","성남","신수원S/S #60 BUS","신수원S/S 154kV 동반T/L GIS 교체공사","154kV 동반#2T/L 무부하가압","2024-11-21 10:00","2024-11-21 14:00","2024-11-21 10:00","2024-11-21 14:00","연속"]
[217,"경기","성남","신용인기흥#2 T/L","[9월 취소분] 24-25년 경기직할 가공송전 협력회사 총액공사","[9월 취소분] 피뢰기 설치공사","2024-11-26 07:00","2024-11-27 18:00","2024-11-26 07:00","2024-11-27 18:00","연속"]
[218,"경기","성남","신용인용인#2 T/L","[9월 취소분] 24-25년 경기직할 가공송전 협력회사 총액공사","[9월 취소분] 피뢰기 설치공사","2024-11-28 07:00","2024-11-30 18:00","2024-11-28 07:00","2024-11-30 18:00","연속"]
[219,"경기","성남","신용인기흥#1 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","불량애자 교체공사[4회선 병가 안전거리 휴전]","2024-11-30 07:00","2024-11-30 13:00","2024-11-30 07:00","2024-11-30 13:00","연속"]
[220,"경기","성남","신용인S/S SEC CB 61620","2024년 성남전력 변전협력회사 총액공사","GIS 조작시험","2024-11-05 09:00","2024-11-05 14:00","취소","취소","연속"]
[221,"경기","성남","신용인S/S SEC CB 66670","2024년 성남전력 변전협력회사 총액공사","GIS 조작시험","2024-11-05 14:00","2024-11-05 18:00","취소","취소","연속"]
[222,"경기","성남","신용인S/S SEC CB 60610","2024년 성남전력 변전협력회사 총액공사","GIS 조작시험","2024-11-06 09:00","2024-11-06 14:00","취소","취소","연속"]
[223,"경기","성남","신용인동백#2 T/L","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검","2024-11-19 09:00","2024-11-20 18:00","2024-11-19 09:00","2024-11-20 18:00","연속"]
[224,"경기","성남","신용인S/S SEC CB 65660","2024년 성남전력 변전협력회사 총액공사","GIS 조작시험","2024-11-06 14:00","2024-11-06 18:00","취소","취소","연속"]
[225,"경기","성남","모현용인#1 T/L","2024년 성남전력 변전협력회사 총액공사","보호반 대체","2024-11-21 09:00","2024-11-23 18:00","2024-11-21 09:00","2024-11-23 18:00","연속"]
[226,"경기","성남","용인덕성#2 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","피뢰기 설치공사[4회선 병가 안전거리 휴전]","2024-11-30 13:00","2024-11-30 18:00","2024-11-30 13:00","2024-11-30 18:00","연속"]
[227,"경기","성남","모현용인#2 T/L","2024년 성남전력 변전협력회사 총액공사","보호반 대체","2024-11-25 09:00","2024-11-27 18:00","2024-11-25 09:00","2024-11-27 18:00","연속"]
[228,"경기","직할","조암구문천#2 T/L","24-25년 경기직할 가공송전 협력회사 총액공사","추락방지장치 설치공사","2024-11-21 07:00","2024-11-21 18:00","2024-11-21 07:00","2024-11-21 18:00","연속"]
[229,"경기","직할","봉담남수원#1 T/L","2024-25년 경기본부 직할 변전협력회사 총액공사","남수원: 남수원-봉담#1T/L 보통점검 봉담: 봉담-남수원#1T/L 보통점검 (양측 세니온 성능개선)","2024-11-16 09:00","2024-11-16 18:00","2024-11-16 09:00","2024-11-16 18:00","연속"]
[230,"경기","직할","봉담남수원#2 T/L","2024-25년 경기본부 직할 변전협력회사 총액공사","남수원: 남수원-봉담#2T/L 보통점검 봉담: 봉담-남수원#2T/L 보통점검 (양측 세니온 성능개선)","2024-11-17 09:00","2024-11-17 18:00","2024-11-17 09:00","2024-11-17 18:00","연속"]
[231,"경기","직할","과천동안양#2 T/L","154kV 과천-동안양T/L 지중화공사(과천지식정보타운)","과천지식정보타운 사업지구 내 지장송전선로 지중화","2024-11-04 09:00","2025-03-03 18:00","2024-11-04 09:00","2025-03-03 18:00","연속"]
[232,"경기","직할","의왕동안양#1 T/L","24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 의왕-동안양#1T/L 40기 120SET","2024-11-22 07:00","2024-11-27 17:00","2024-11-22 07:00","2024-11-27 17:00","연속"]
[233,"경기","직할","동안양안양CC#2 T/L","동안양S/S 지중송전선로 인출정비 공사","154kV 동안양-안열T/L 인출정비 - 선종/길이 : XLPE 2000 / 0.404km","2024-11-12 08:00","2024-12-08 18:00","취소","취소","연속"]
[234,"경기","직할","서서울#2봉담#1 T/L","24년 경기본부 직할 170kV GIS 정밀점검공사","봉담: 서서울-봉담#1T/L GIS 정밀점검","2024-11-09 09:00","2024-11-10 18:00","취소","취소","연속"]
[235,"경기","직할","수촌조암#2 T/L","24년 경기본부 직할 170kV GIS 정밀점검공사","수촌: 수촌-조암#2T/L GIS 정밀점검","2024-11-04 09:00","2024-11-05 18:00","2024-11-04 09:00","2024-11-05 18:00","연속"]
[236,"경기","직할","율전의왕#2 T/L","24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 율전-의왕#2T/L 1기 3SET","2024-11-18 13:00","2024-11-18 17:00","2024-11-18 13:00","2024-11-18 17:00","연속"]
[237,"경기","직할","서수원율전#1 T/L","24-25년 군포 가공송전협력회사 공사","율전-의왕#2T/L 피뢰기 설치공사 병가구간 안전이격거리 확보","2024-11-18 07:00","2024-11-18 17:00","2024-11-18 07:00","2024-11-18 17:00","연속"]
[238,"경기","직할","서서울율전#1 T/L","24-25년 군포 가공송전협력회사 공사","율전-의왕#2T/L 피뢰기 설치공사 병가구간 안전이격거리 확보","2024-11-18 13:00","2024-11-18 17:00","2024-11-18 13:00","2024-11-18 17:00","연속"]
[239,"경기","직할","율전의왕#2 T/L","24-25년 군포 가공송전협력회사 공사","피뢰기 설치공사 : 154kV 율전-의왕#2T/L 13기 39SET","2024-11-25 07:00","2024-11-26 17:00","2024-11-25 07:00","2024-11-26 17:00","연속"]
[240,"경기","직할","의왕동안양#2 T/L","24년 경기본부 직할 170kV GIS 정밀점검공사","의왕: 의왕-동안양#2T/L GIS 정밀점검","2024-11-20 09:00","2024-11-21 18:00","2024-11-20 09:00","2024-11-21 18:00","연속"]
[241,"경기","직할","이의S/S CB 6100","2024-25년 경기본부 직할 변전협력회사 공사","이의: 모선보호반 대체","2024-11-04 09:00","2024-11-08 18:00","2024-11-04 09:00","2024-11-08 18:00","연속"]
[242,"경기","직할","신봉이의#2 T/L","2024-25년 경기본부 직할 변전협력회사 공사","이의: 신봉-이의#2T/L 보호반 대체","2024-11-11 09:00","2024-11-15 18:00","2024-11-11 09:00","2024-11-15 18:00","연속"]
[243,"경기","직할","안양평촌#2 T/L","2024-25년 경기본부 직할 변전협력회사 공사","평촌: 안양-평촌#1,#2T/L 조작시험","2024-11-28 14:00","2024-11-28 18:00","2024-11-28 14:00","2024-11-28 18:00","연속"]
[244,"경기","직할","안양평촌#1 T/L","2024-25년 경기본부 직할 변전협력회사 공사","평촌: 안양-평촌#1,#2T/L 조작시험","2024-11-28 09:00","2024-11-28 14:00","2024-11-28 09:00","2024-11-28 14:00","연속"]
[245,"경기","직할","화성수촌#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 13기, 4회선 7기","2024-11-03 07:00","2024-11-03 18:00","2024-11-03 07:00","2024-11-03 18:00","연속"]
[246,"경기","직할","화성남양#1 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 7기","2024-11-07 07:00","2024-11-07 18:00","2024-11-07 07:00","2024-11-07 18:00","연속"]
[247,"경기","직할","화성남양#2 T/L","(군포)철탑추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 4회선 7기","2024-11-08 07:00","2024-11-08 18:00","2024-11-08 07:00","2024-11-08 18:00","연속"]
[248,"경기","직할","화성수촌#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 13기, 4회선 7기","2024-11-02 07:00","2024-11-02 18:00","2024-11-02 07:00","2024-11-02 18:00","연속"]
[249,"경기","평택","원정만호#2 T/L","23-24년 지중송전설비 위탁정비공사(평택전력)","피뢰기 절연열화 측정 및 부싱청소","2024-11-04 08:00","2024-11-04 18:00","취소","취소","연속"]
[250,"경기","평택","서운삼죽 T/L","24년도 평택전력 변전협력회사 총액공사","서운,삼죽S/S 서운-삼죽T/L 보호배전반 대체공사 및 삼죽S/S 170kV GIS 보통점검","2024-11-04 09:00","2024-11-06 18:00","2024-11-04 09:00","2024-11-06 18:00","연속"]
[251,"경기","평택","서안성S/S #1 EM.Tr CB","24년 평택전력지사 변전협력회사 총액공사","서안성S/S ESS점검 ( #1EM.Tr 휴전)","2024-11-25 09:00","2024-11-29 18:00","2024-11-25 09:00","2024-11-29 18:00","연속"]
[252,"경기","평택","서운안성#2 T/L","추락방지장치(수평) 설치공사","154kV 서운-안성#2T/L No.11~15, 18~22(No.43~61-4회선) 24기 154kV 서운-삼죽T/L No.1~19","2024-11-07 08:00","2024-11-08 18:00","2024-11-07 08:00","2024-11-08 18:00","연속"]
[253,"경기","평택","서운안성#1 T/L","추락방지장치(수평) 설치공사","154kV 서운-안성#1T/L No.37~61(No.43~61-4회선) 20기 154kV 서운-광혜원T/L No.1~19","2024-11-15 08:00","2024-11-15 18:00","2024-11-15 08:00","2024-11-15 18:00","연속"]
[254,"경기","평택","서안성안성#1 T/L","24년도 평택전력 변전협력회사 총액공사","안성S/S 서안성-안성#1T/L 170kV GIS 보통점검","2024-11-25 09:00","2024-11-25 18:00","취소","취소","연속"]
[255,"경기","평택","서안성안성#2 T/L","24년도 평택전력 변전협력회사 총액공사","안성S/S 서안성-안성#2T/L 170kV GIS 보통점검","2024-11-26 09:00","2024-11-26 18:00","취소","취소","연속"]
[256,"경기","평택","오산평택#2 T/L","154kV 오산-평택 등 2개T/L 지중화공사_가공","-가철탑 설치 2기 -전력선 설치 : ACSR 330 0.428 km-C -전력선 이설 : ACSR 330 1.322 km-C","2024-11-30 07:00","2024-12-04 18:00","2024-11-30 07:00","2024-12-04 18:00","연속"]
[257,"경기","평택","원정평택TP#2 T/L","24년도 평택전력 변전협력회사 총액공사","평택T/P 평택TP-원정#2T/L GIS 보통점검 및 원정S/S 평택TP-원정#2T/L GIS 조작시험 및 PT&LA 보통점검","2024-11-21 09:00","2024-11-21 18:00","취소","취소","연속"]
[258,"경기","평택","원정평택TP#1 T/L","24년도 평택전력 변전협력회사 총액공사","평택T/P 평택TP-원정#1T/L GIS 보통점검 및 원정S/S 평택TP-원정#2T/L GIS 조작시험 및 PT&LA 보통점검","2024-11-20 09:00","2024-11-20 18:00","취소","취소","연속"]
[259,"경기","평택","청북평택#1 T/L","추락방지장치(수평) 설치공사","154kV 청북-평택T/L No.17~22 2회선 6기 : 추락방지장치 설치 (주작업) 154kV 청북-평택#1T/L No.14~21 : 상단 소도체 이도조정 (병행작업)","2024-11-27 08:00","2024-11-29 18:00","취소","취소","연속"]
[260,"경기","평택","청북평택#2 T/L","추락방지장치(수평) 설치공사","154kV 청북-평택T/L No.10~22 9기","2024-11-25 08:00","2024-11-26 18:00","취소","취소","연속"]
[261,"경기","평택","둔포추팔#2 T/L","154kV 둔포추팔#2T/L 철탑암부재정비(No.9)","2024~2025년 가공송전 송전정비 협력회사 공사 154kV 둔포추팔#2T/L 철탑암부재정비(No.9호 중단 부재교체)","2024-11-22 08:00","2024-11-22 18:00","취소","취소","연속"]
[262,"경기","성남","신용인용인#1 T/L","  24-25년 경기본부 직할 송전협력회사 공사","철탑추락방지장치 설치[4회선 병가]","2024-11-13 07:00","2024-11-13 18:00","2024-11-13 07:00","2024-11-13 18:00","연속"]
[263,"경기","성남","신수원북동탄#2 T/L","2024년 성남전력 170kV GIS 정밀점검공사 ","GIS 정밀점검 ","2024-11-11 09:00","2024-11-12 18:00","2024-11-11 09:00","2024-11-12 18:00","연속"]
[264,"경기","성남","신수원북동탄#1 T/L","2024년 성남전력 170kV GIS 정밀점검공사 ","GIS 정밀점검","2024-11-15 09:00","2024-11-16 18:00","2024-11-15 09:00","2024-11-16 18:00","연속"]
[265,"경기","직할","남수원발안#1 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 7기, 4회선 21기","2024-11-18 09:00","2024-11-19 18:00","2024-11-18 09:00","2024-11-19 18:00","연속"]
[266,"경기","직할","남수원발안#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 7기, 4회선 21기","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[267,"경기","직할","봉담남수원#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 7기, 4회선 21기","2024-11-23 09:00","2024-11-23 18:00","2024-11-23 09:00","2024-11-23 18:00","연속"]
[268,"경기","직할","남수원발안#2 T/L","(군포)추락방지장치(수평) 설치공사","철탑추락방지장치(수평) 설치 : 2회선 7기, 4회선 21기","2024-11-24 09:00","2024-11-24 18:00","2024-11-24 09:00","2024-11-24 18:00","연속"]
[269,"강원","강릉","영동T/P #2 BUS","2024년 강릉전력지사 170kV GIS 정밀점검공사","#2SU.Tr GIS 무부하가압","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[270,"강원","강릉","영동T/P #2 BUS","2024년 강릉전력지사 170kV GIS 정밀점검공사","#2M.Tr GIS 무부하가압","2024-11-08 09:00","2024-11-08 18:00","2024-11-08 09:00","2024-11-08 18:00","연속"]
[271,"강원","강릉","신제천주진#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 낙뢰로 인한 고장점 피뢰기 교체","2024-11-07 08:00","2024-11-07 18:00","2024-11-07 08:00","2024-11-07 18:00","연속"]
[272,"강원","강릉","횡계평창 T/L","2024년 강릉전력지사 변전협력회사 공사","154kV LA 대체 (A,B,C상)","2024-11-07 10:00","2024-11-07 18:00","2024-11-07 10:00","2024-11-07 18:00","연속"]
[273,"강원","동해","이원도계 T/L","2024~25년 동해전력지사 변전협력회사공사","도계S/S 디지털화","2024-11-06 09:00","2024-11-07 18:00","2024-11-21 09:00","2024-11-24 18:00","연속"]
[274,"강원","동해","도계태백 T/L","2024~25년 동해전력지사 변전협력회사공사","도계S/S 디지털화","2024-11-04 09:00","2024-11-05 18:00","2024-11-17 09:00","2024-11-20 18:00","연속"]
[275,"강원","동해","삼척동해TP T/L","154kV 동해화력T/L EBG 가스밸브 설치공사","154kV 동해화력T/L EBG 12상 가스채취밸브 설치","2024-11-20 09:00","2024-11-21 18:00","2024-11-20 09:00","2024-11-21 18:00","연속"]
[276,"강원","동해","동해T/P #1 G.Tr CB","2024~25년 동해전력지사 변전협력회사 공사","메커니즘점검","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[277,"강원","동해","이원동해TP T/L","154kV 동해화력T/L EBG 가스밸브 설치공사","154kV 동해화력T/L EBG 12상 가스채취밸브 설치","2024-11-18 09:00","2024-11-19 18:00","2024-11-18 09:00","2024-11-19 18:00","연속"]
[278,"강원","동해","동해T/P CB 6100","2024~25년 동해전력지사 변전협력회사 공사","차단기 조작시험","2024-11-04 09:00","2024-11-04 18:00","취소","취소","연속"]
[279,"강원","동해","북평영동TP#2 T/L","`23~24년 강원본부 지중송전설비 위탁정비공사","작업내용 : 154kV 북평-영동T/L 영동C/T 피뢰기 점검 작업기간 - 북평-영동T/P #1T/L : `24.11.13 08:00 ~ 13:00 - 북평-영동T/P #2T/L : `24.11.13 13:00 ~ 18:00","2024-11-13 13:00","2024-11-13 18:00","2024-11-13 13:00","2024-11-13 18:00","연속"]
[280,"강원","동해","북평영동TP#1 T/L","`23~24년 강원본부 지중송전설비 위탁정비공사","작업내용 : 154kV 북평-영동T/L 영동C/T 피뢰기 점검 작업기간 - 북평-영동T/P #1T/L : `24.11.13 08:00 ~ 13:00 - 북평-영동T/P #2T/L : `24.11.13 13:00 ~ 18:00","2024-11-13 08:00","2024-11-13 13:00","2024-11-13 08:00","2024-11-13 13:00","연속"]
[281,"강원","원주","남원주원주#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 피뢰기 및 폴리머점퍼지지애자 설치","2024-11-04 08:00","2024-11-04 18:00","2024-11-09 08:00","2024-11-09 18:00","연속"]
[282,"강원","원주","신제천남원주#1 T/L","24-25년 원주전력지사 변전협력회사 총액공사","남원주S/S 디지털화 공사 - 감시제어용 케이블 이설 및 SCADA 준공시험","2024-11-04 08:00","2024-11-06 18:00","2024-11-09 08:00","2024-11-10 18:00","연속"]
[283,"강원","원주","북원주횡성#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 송전선로용 피뢰기 철거(전력연구원 시험예정)","2024-11-08 08:00","2024-11-08 18:00","취소","취소","연속"]
[284,"강원","원주","횡성홍천#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 성능저하 국산애자 교체","2024-11-06 08:00","2024-11-06 18:00","취소","취소","연속"]
[285,"강원","원주","횡성홍천#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 성능저하 국산애자 교체","2024-11-05 00:08","2024-11-05 18:00","취소","취소","연속"]
[286,"강원","원주","홍천남춘천 T/L","24-25년 원주전력지사 변전협력회사 총액공사","피뢰기 초기점검 CVT 보통점검","2024-11-01 09:00","2024-11-01 18:00","2024-11-12 10:00","2024-11-12 18:00","연속"]
[287,"강원","직할","남춘천춘천 T/L","남춘천S/S 154kV 장기사용 GIS 대체공사","■ 1차 공정 - 무부하 가압용","2024-11-27 09:00","2024-11-29 18:00","2024-11-27 09:00","2024-11-29 18:00","매일"]
[288,"강원","직할","남춘천춘천 T/L","남춘천S/S 154kV 장기사용 GIS 대체공사","■ 1차 공정 - 양DS 투입 후 GIS 모선절체용 - 무부하 가압용","2024-11-20 09:00","2024-11-22 18:00","2024-11-20 09:00","2024-11-22 18:00","매일"]
[289,"강원","직할","춘천북춘천#1 T/L","2024년 가공송전 순시점검 위탁공사","154kV 춘천-북춘천T/L No.53~54 수목벌채 시행","2024-11-07 08:00","2024-11-12 18:00","취소","취소","매일"]
[290,"강원","직할","서홍천청평PP T/L","2024년 가공송전 순시점검 위탁공사","현수애자 절연성능진단 불량애자 절연저항 측정","2024-11-26 09:00","2024-11-27 18:00","취소","취소","매일"]
[291,"강원","직할","상남인제#2 T/L","2024년 가공송전 순시점검 위탁공사","154kV 상제T/L No.37~38 수목벌채 시행","2024-11-04 07:00","2024-11-06 18:00","2024-11-04 07:00","2024-11-06 18:00","매일"]
[292,"강원","직할","춘천북춘천#2 T/L","2024~2025년 강원본부 직할 송전협력회사 공사","피뢰기 설치","2024-11-25 08:00","2024-11-29 18:00","취소","취소","매일"]
[293,"강원","직할","청평PP춘천열병합 T/L","2024년 가공송전 순시점검 위탁공사","현수애자 절연성능진단 불량애자 절연저항 측정","2024-11-18 09:00","2024-11-20 18:00","취소","취소","매일"]
[294,"강원","직할","서홍천춘천열병합 T/L","2024년 가공송전 순시점검 위탁공사","현수애자 절연성능진단 불량애자 절연저항 측정","2024-11-21 09:00","2024-11-25 18:00","취소","취소","매일"]
[295,"강원","직할","화천S/S CB 6100","2024~2025년 강원본부 직할 변전협력회사 공사","154kV B/T 차단기 조작시험","2024-11-15 10:00","2024-11-15 13:00","2024-11-15 10:00","2024-11-15 13:00","연속"]
[296,"강원","태백","동영월영월CC T/L","2024년 태백전력지사 154kV GIS 정밀점검 공사","동영월S/S 154kV 동영월-영월CC T/L GIS 정밀점검","2024-11-18 09:00","2024-11-20 18:00","2024-11-18 09:00","2024-11-20 18:00","연속"]
[297,"강원","태백","동해동영월 T/L","2024년 태백전력지사 154kV GIS 정밀점검 공사","동영월S/S 154kV 동해-동영월T/L GIS 정밀점검","2024-11-21 09:00","2024-11-22 18:00","2024-11-21 09:00","2024-11-22 18:00","연속"]
[298,"강원","태백","영월S/S #1 BUS","2024년 태백전력지사 154kV GIS 정밀점검 공사","영월S/S 154kV #2M.Tr 1차 GIS 정밀점검","2024-11-25 09:00","2024-11-26 18:00","취소","취소","연속"]
[299,"강원","태백","영월S/S #2 BUS","2024년 태백전력지사 154kV GIS 정밀점검 공사","영월S/S 154kV #2M.Tr 1차 GIS 정밀점검","2024-11-27 09:00","2024-11-28 18:00","취소","취소","연속"]
[300,"강원","태백","영월영월에코윈드#1 T/L","영월군 팔흥교 건설","영월군 팔흥교 건설 관련 안전확보를 위한 휴전 (시공사 요청사항)","2024-11-13 07:00","2024-11-13 18:00","2024-11-29 07:00","2024-11-29 18:00","연속"]
[301,"강원","태백","영월영월에코윈드#2 T/L","영월군 팔흥교 건설","영월군 팔흥교 건설 관련 안전확보를 위한 휴전(시공사 요청사항)","2024-11-13 07:00","2024-11-13 18:00","2024-11-29 07:00","2024-11-29 18:00","연속"]
[302,"강원","태백","영월영월에코윈드#2 T/L","영월에코윈드SY GIS 불량개소 하자보수","154kV 영월에코윈드-영월#2T/L GIS 하자보수","2024-11-04 09:00","2024-11-05 18:00","2024-11-04 09:00","2024-11-05 18:00","연속"]
[303,"강원","태백","영월영월에코윈드#1 T/L","영월에코윈드SY GIS 불량개소 하자보수","154kV 영월에코윈드-영월#1T/L GIS 하자보수","2024-11-01 09:00","2024-11-01 18:00","2024-11-01 09:00","2024-11-01 18:00","연속"]
[304,"강원","태백","태백영월에코윈드 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-11-04 10:00","2024-11-13 18:00","2024-11-04 10:00","2024-11-13 18:00","연속"]
[305,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-11-12 10:00","2024-11-13 18:00","2024-11-12 10:00","2024-11-13 18:00","연속"]
[306,"강원","태백","태백고한 T/L","2024년 태백전력지사 변전협력회사 공사","154kV 태백고한 T/L PNL 대체공사 고한S/S 154kV 태백-고한T/L GIS 보통점검 (병행) 고한S/S 154kV 태백-고한T/L LA 초기점검 (병행)","2024-11-25 09:00","2024-11-28 18:00","2024-11-25 09:00","2024-11-28 18:00","연속"]
[307,"강원","태백","태백S/S #60 BUS","154kV 태백S/S #2M.Tr 증설공사(준공시험)","준공시험, 인터록 시험","2024-11-26 09:00","2024-11-26 14:00","취소","취소","연속"]
[308,"강원","태백","태백S/S #65 BUS","154kV 태백S/S #2M.Tr 증설공사(준공시험)","준공시험, 인터록 시험","2024-11-26 14:00","2024-11-26 18:00","취소","취소","연속"]
[309,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-11-06 10:00","2024-11-07 18:00","2024-11-06 10:00","2024-11-07 18:00","연속"]
[310,"강원","태백","태백S/S #65 BUS","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-11-04 10:00","2024-11-07 18:00","2024-11-04 10:00","2024-11-07 18:00","연속"]
[311,"강원","태백","태백S/S #60 BUS","154kV 태백S/S #2M.Tr 증설공사(GIS 전문)","- 170kV GIS 1Bay 설치 - 기타 부대공사","2024-11-08 10:00","2024-11-13 18:00","2024-11-08 10:00","2024-11-13 18:00","연속"]
[312,"충북","직할","진천광혜원#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","접속개소 전선교체(1.707C-km), 수평 추락방지장치 설치(39기), 피뢰기 설치(39기)","2024-11-15 07:00","2024-11-22 18:00","취소","취소","연속"]
[313,"충북","직할","서운광혜원 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","접속개소 전선교체(1.221C-km), 수평 추락방지장치 설치(39기), 피뢰기 설치(39기)","2024-11-15 07:00","2024-11-22 18:00","취소","취소","연속"]
[314,"충북","직할","진천광혜원#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","접속개소 전선교체(1.707C-km), 수평 추락방지장치 설치(36기)","2024-11-04 07:00","2024-11-12 18:00","취소","취소","연속"]
[315,"충북","직할","진천S/S SEC CB 60610","'24년 충북본부 직할 154kV GIS 정밀점검공사","진천S/S 154kV #2 M.Tr GIS 정밀점검 후 무부하가압용","2024-11-02 09:00","2024-11-02 10:00","2024-11-02 09:00","2024-11-02 10:00","연속"]
[316,"충북","직할","진천S/S #60 BUS","'24년 충북본부 직할 154kV GIS 정밀점검공사","진천S/S 154kV #2M.Tr GIS 정밀점검 후 무부하가압용","2024-11-02 09:00","2024-11-02 10:00","2024-11-02 09:00","2024-11-02 10:00","연속"]
[317,"충북","청주","남청주청주#2 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-11-30 08:00","2024-12-18 18:00","취소","취소","연속"]
[318,"충북","청주","남청주S/S SEC CB 66650","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 초기점검","2024-11-26 10:00","2024-11-26 18:00","2024-11-26 10:00","2024-11-26 18:00","연속"]
[319,"충북","청주","남청주S/S SEC CB 67660","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검","2024-11-27 10:00","2024-11-27 18:00","2024-11-27 10:00","2024-11-27 18:00","연속"]
[320,"충북","청주","남청주S/S #62 BUS","24년 청주전력지사 170kV GIS 정밀점검","남청주S/S 154kV #7Sh.C GIS 정밀점검 후 무부하 가압","2024-11-01 16:00","2024-11-01 18:00","2024-11-01 16:00","2024-11-01 18:00","연속"]
[321,"충북","청주","남청주S/S SEC CB 62610","24년 청주전력지사 170kV GIS 정밀점검","남청주S/S 154kV #7Sh.C GIS 정밀점검 후 무부하 가압","2024-11-01 16:00","2024-11-01 18:00","2024-11-01 16:00","2024-11-01 18:00","연속"]
[322,"충북","청주","남청주청주#4 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 남청주-청주#2,#4T/L(아킹혼, 폴리머지지애자 설치) 1. 내용 : 아킹혼, 폴리머지지애자 설치 2. 구간 : 남청주S/S~청주S/S","2024-11-04 08:00","2024-11-15 18:00","2024-11-04 08:00","2024-11-15 18:00","매일"]
[323,"충북","청주","남청주청주#2 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 남청주-청주#2,#4T/L(아킹혼, 폴리머지지애자 설치) 1. 내용 : 아킹혼, 폴리머지지애자 설치 2. 구간 : 남청주S/S~청주S/S","2024-11-04 08:00","2024-11-15 18:00","2024-11-04 08:00","2024-11-15 18:00","매일"]
[324,"충북","청주","남청주S/S #62 BUS","24년 청주전력지사 170kV GIS 정밀점검","남청주S/S 154kV #2Sh.C GIS 정밀점검 후 무부하 가압","2024-11-05 16:00","2024-11-05 18:00","2024-11-05 16:00","2024-11-05 18:00","연속"]
[325,"충북","청주","남청주S/S SEC CB 62610","24년 청주전력지사 170kV GIS 정밀점검","남청주S/S 154kV #2Sh.C GIS 정밀점검 후 무부하 가압","2024-11-05 16:00","2024-11-05 18:00","2024-11-05 16:00","2024-11-05 18:00","연속"]
[326,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-11-30 08:00","2024-12-03 14:00","취소","취소","연속"]
[327,"충북","청주","화동보은 T/L","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검","2024-11-22 10:00","2024-11-22 18:00","2024-11-22 10:00","2024-11-22 18:00","연속"]
[328,"충북","청주","사직북청주#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","북청주S/S 154kV 사직-북청주#1T/L GIS 정밀점검","2024-11-20 08:00","2024-11-21 18:00","2024-11-20 08:00","2024-11-21 18:00","연속"]
[329,"충북","청주","사직북청주#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","사직S/S 154kV 사직-북청주#1T/L GIS 정밀점검","2024-11-11 08:00","2024-11-12 18:00","취소","취소","연속"]
[330,"충북","청주","화동영동 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 화동-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 화동-영동T/L 수평 추락방지장치 설치 2. 구간 : 154kV 화동-영동T/L 60~110호 154kV 영동분기T/L 1~61호","2024-11-18 08:00","2024-11-28 18:00","취소","취소","매일"]
[331,"충북","청주","오송북청주#2 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km ※ No.37 철탑(4회선 병가, 하단) 활선으로 인하여, 작업 상 안전이격상 휴전 신청","2024-11-25 07:00","2024-11-29 18:00","2024-11-25 07:00","2024-11-29 18:00","연속"]
[332,"충북","청주","문백오창#1 T/L","24년 청주전력지사 170kV GIS 정밀점검","오창S/S 154kV 문백-오창#1T/L GIS 정밀점검","2024-11-02 08:00","2024-11-03 18:00","2024-11-02 08:00","2024-11-03 18:00","연속"]
[333,"충북","청주","오창국사#2 T/L","154kV 신청주-문백T/L 건설공사(임시선로구성)","154kV 오창-국사T/L No.13~17 임시선로 구성 - 작업구간 : No.13~17 - 철탑 : 가철탑 2기 설치 - 가선 : No.13~17","2024-11-18 08:00","2024-11-22 18:00","2024-11-18 08:00","2024-11-22 18:00","연속"]
[334,"충북","청주","오창국사#1 T/L","154kV 신청주-문백T/L 건설공사(임시선로구성)","154kV 오창-국사T/L No.13~17 임시선로 구성 - 작업구간 : No.13~17 - 철탑 : 가철탑 2기 설치 - 가선 : No.13~17","2024-11-25 08:00","2024-11-29 18:00","2024-11-25 08:00","2024-11-29 18:00","연속"]
[335,"충북","청주","신옥천옥천#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검","2024-11-19 10:00","2024-11-19 18:00","2024-11-19 10:00","2024-11-19 18:00","연속"]
[336,"충북","청주","옥천보은 T/L","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검(양단)","2024-11-21 10:00","2024-11-21 18:00","2024-11-21 10:00","2024-11-21 18:00","연속"]
[337,"충북","청주","신옥천옥천#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검","2024-11-18 10:00","2024-11-18 18:00","2024-11-18 10:00","2024-11-18 18:00","연속"]
[338,"충북","청주","옥천영동 T/L","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검(양단)","2024-11-20 10:00","2024-11-20 18:00","2024-11-20 10:00","2024-11-20 18:00","연속"]
[339,"충북","충주","감곡가남#1 T/L","'24-25년 충주전력지사 변전정비 총액공사","감곡S/S 154kV 감곡-가남#1T/L GIS 보통점검","2024-11-08 10:00","2024-11-08 16:00","취소","취소","연속"]
[340,"충북","충주","감곡가남#2 T/L","'24-25년 충주전력지사 변전정비 총액공사","감곡S/S 154kV 감곡-가남#2T/L GIS 보통점검","2024-11-11 10:00","2024-11-11 18:00","취소","취소","연속"]
[341,"충북","충주","음성금왕#1 T/L","'24-25년 충주전력지사 변전정비 총액공사","금왕S/S 154kV 음성금왕#1 T/L 세니온제 성능개선","2024-11-15 09:00","2024-11-15 18:00","2024-11-15 09:00","2024-11-15 18:00","연속"]
[342,"충북","충주","음성금왕#2 T/L","'24-25년 충주전력지사 변전정비 총액공사","금왕S/S 154kV 음성금왕#2 T/L LA,CVT 보통점검 및 세니온제 성능개선","2024-11-18 09:00","2024-11-18 18:00","2024-11-18 09:00","2024-11-18 18:00","연속"]
[343,"충북","충주","금왕남음성#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치(23기), 피뢰기 설치(25기)","2024-11-26 07:30","2024-11-28 18:00","취소","취소","매일"]
[344,"충북","충주","금왕남음성#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기)","2024-11-29 07:30","2024-12-03 18:00","취소","취소","매일"]
[345,"충북","충주","점촌단양 T/L","효성제 170kV 전동스프링 GIS 발청베어링 교체공사","단양S/S 154kV 점촌-단양TL GIS 발청베어링 교체공사","2024-11-01 10:00","2024-11-01 14:00","2024-11-01 10:00","2024-11-01 14:00","연속"]
[346,"충북","충주","문경단양 T/L","효성제 170kV 전동스프링 GIS 발청베어링 교체공사","단양S/S 154kV 문경-단양TL GIS 발청베어링 교체공사","2024-11-01 14:00","2024-11-01 18:00","취소","취소","연속"]
[347,"충북","충주","단양영월CC#2 T/L","'24-25년 충주전력지사 변전정비 총액공사","단양S/S 154kV 단양영월CC#2 T/L PNL 대체","2024-11-19 09:00","2024-11-26 18:00","2024-11-19 09:00","2024-11-26 18:00","연속"]
[348,"충북","충주","신제천S/S SEC CB 60610","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 154kV #60-#61 SEC GIS 보통점검","2024-11-07 10:00","2024-11-07 16:00","취소","취소","연속"]
[349,"충북","충주","신제천S/S SEC CB 61620","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 154kV #61-#62 SEC GIS 보통점검","2024-11-08 10:00","2024-11-08 18:00","취소","취소","연속"]
[350,"충북","충주","신제천S/S SEC CB 66670","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 154kV #66-#67 SEC GIS 보통점검","2024-11-06 10:00","2024-11-06 16:00","취소","취소","연속"]
[351,"충북","충주","신충주S/S SEC CB 65660","'24-25년 충주전력지사 변전정비 총액공사","신충주S/S 154kV #65-#66 SEC GIS 보통점검","2024-11-12 14:00","2024-11-12 18:00","2024-11-12 14:00","2024-11-12 18:00","연속"]
[352,"충북","충주","신충주S/S SEC CB 60610","'24-25년 충주전력지사 변전정비 총액공사","신충주S/S 154kV #60-#61 SEC GIS 보통점검","2024-11-12 08:00","2024-11-12 13:00","2024-11-12 08:00","2024-11-12 13:00","연속"]
[353,"충북","충주","신충주음성#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","피뢰기 설치(7기), 애자교체(3기)","2024-11-25 07:30","2024-11-25 18:00","취소","취소","매일"]
[354,"충북","충주","신충주음성#2 T/L","'24-25년 충주전력지사 변전정비 총액공사","신충주,음성S/S 154kV 신충주음성#2 T/L GIS 보통점검 및 세니온제 성능개선","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[355,"충북","충주","신충주음성#1 T/L","'24-25년 충주전력지사 변전정비 총액공사","신충주,음성S/S 154kV 신충주음성#1 T/L 보통점검 및 세니온제 성능개선","2024-11-19 09:00","2024-11-19 18:00","2024-11-19 09:00","2024-11-19 18:00","연속"]
[356,"충북","충주","신충주S/S CB 6200","'24-25년 충주전력지사 변전정비 총액공사","신충주S/S 154kV #61-#66 BUS TIE GIS 보통점검","2024-11-18 10:00","2024-11-18 18:00","2024-11-18 10:00","2024-11-18 18:00","연속"]
[357,"충북","충주","신제천왕암#1 T/L","'24-25년 충주전력지사 변전정비 총액공사","왕암S/S 154kV 신제천-왕암#1T/L GIS 보통점검 및 세니온제 성능개선","2024-11-12 09:00","2024-11-12 18:00","2024-11-12 09:00","2024-11-12 18:00","연속"]
[358,"충북","충주","신제천왕암#2 T/L","'24-25년 충주전력지사 변전정비 총액공사","왕암S/S 154kV 신제천-왕암#2T/L GIS 보통점검 및 세니온제 성능개선","2024-11-13 09:00","2024-11-13 18:00","2024-11-13 09:00","2024-11-13 18:00","연속"]
[359,"충북","충주","음성금왕#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(30기), 애자교체(2기)","2024-11-29 07:30","2024-12-04 18:00","취소","취소","매일"]
[360,"충북","충주","음성금왕#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기), 피뢰기 설치(32기), 애자교체(3기)","2024-11-25 07:30","2024-11-28 18:00","취소","취소","매일"]
[361,"충북","충주","충주충주HP#1 T/L","154kV 충주-충주HP T/L 전선접속개소 교체공사","154kV 충주-충주HP #1 No.9~16 전선전속개소교체공사(주말작업없음)","2024-11-04 09:00","2024-11-15 18:00","2024-11-04 09:00","2024-11-15 18:00","연속"]
[362,"충북","충주","북충주충주 T/L","154kV 충주-충주HP T/L 전선접속개소 교체공사","154kV 충주-충주HP #2 No.9~16 전선전속개소교체공사 안전확보를 위한 병가구간 휴전","2024-11-18 09:00","2024-11-29 18:00","2024-11-18 09:00","2024-11-29 18:00","연속"]
[363,"충북","충주","충주충주HP#2 T/L","154kV 충주-충주HP T/L 전선접속개소 교체공사","154kV 충주-충주HP #2 No.9~16 전선전속개소교체공사(주말작업없음)","2024-11-18 09:00","2024-11-29 18:00","2024-11-18 09:00","2024-11-29 18:00","연속"]
[364,"충북","충주","왕암충주 T/L","154kV 충주-충주HP T/L 전선접속개소 교체공사","154kV 충주-충주HP #1 No.9~16 전선전속개소교체공사 안전확보를 위한 병가구간 휴전","2024-11-04 09:00","2024-11-15 18:00","2024-11-04 09:00","2024-11-15 18:00","연속"]
[365,"대전세종충남","대전","남대전신흥#3 T/L","[취소시][즉시가압X]남대전SA 남대전-신흥#3T/L 가스교체","남대전SA 154kV 남대전-신흥#3T/L GIS 가스교체","2024-11-25 09:00","2024-11-26 18:00","2024-11-25 09:00","2024-11-26 18:00","연속"]
[366,"대전세종충남","대전","부여논산#1 T/L","[즉시가압X] 논산S/S 154kV 부여-논산#1T/L GIS 정밀점검","논산S/S 154kV 부여-논산#1T/L GIS 정밀점검","2024-11-11 09:00","2024-11-12 18:00","2024-11-11 09:00","2024-11-12 18:00","연속"]
[367,"대전세종충남","대전","부여논산#2 T/L","[즉시가압X] 논산S/S 154kV 부여-논산#2T/L GIS 정밀점검","논산S/S 154kV 부여-논산#2T/L GIS 정밀점검","2024-11-13 09:00","2024-11-14 18:00","2024-11-13 09:00","2024-11-14 18:00","연속"]
[368,"대전세종충남","대전","신계룡두마#1 T/L","[즉시가압X]두마S/S 신계룡-두마#1T/L 보호반대체","두마S/S 신계룡-두마#1T/L 보호반대체","2024-11-18 09:00","2024-11-20 12:00","2024-11-18 09:00","2024-11-20 12:00","연속"]
[369,"대전세종충남","대전","신계룡두마#2 T/L","[즉시가압X]두마S/S 신계룡-두마#2T/L 보호반대체","두마S/S 신계룡-두마#2T/L 보호반대체","2024-11-20 13:00","2024-11-22 18:00","2024-11-20 13:00","2024-11-22 18:00","연속"]
[370,"대전세종충남","대전","신계룡은진#2 T/L","[송전][즉시가압O]345kV신옥천-청양등8개T/L 추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV신옥천-청양등8개T/L 추락방지설치공사","2024-11-05 07:00","2024-11-17 13:00","취소","취소","매일"]
[371,"대전세종충남","대전","신계룡S/S #61 BUS","[즉시가압X]신계룡S/S 154kV 6200 BUS TIE 정밀점검","[즉시가압X]신계룡S/S 154kV 6200 BUS TIE 정밀점검","2024-11-04 09:00","2024-11-06 12:00","취소","취소","연속"]
[372,"대전세종충남","대전","신계룡S/S CB 6200","[즉시가압X] 신계룡S/S 154kV 6200 BUS TIE 정밀점검","신계룡S/S 154kV 6200 BUS TIE 정밀점검","2024-11-04 09:00","2024-11-08 18:00","취소","취소","연속"]
[373,"대전세종충남","대전","신계룡S/S SEC CB 60610","[즉시가압X] 신계룡S/S 6200 BUS TIE 정밀점검","신계룡S/S 6200 BUS TIE 정밀점검","2024-11-06 09:00","2024-11-06 12:00","취소","취소","연속"]
[374,"대전세종충남","대전","신계룡두마#2 T/L","[송전][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","2024-11-04 07:00","2024-11-12 13:00","취소","취소","매일"]
[375,"대전세종충남","대전","신계룡S/S #66 BUS","[즉시가압X]신계룡S/S 154kV 6200 BUS TIE 정밀점검공사","신계룡S/S 154kV 6200 BUS TIE 정밀점검공사","2024-11-06 12:00","2024-11-08 18:00","취소","취소","연속"]
[376,"대전세종충남","대전","신계룡S/S SEC CB 65660","[즉시가압X] 신계룡S/S 6200 BUS TIE 정밀점검","신계룡S/S 6200 BUS TIE 정밀점검","2024-11-08 12:00","2024-11-08 18:00","취소","취소","연속"]
[377,"대전세종충남","대전","신옥천유천 T/L","[즉시가압X] 유천S/S 154kV 신옥천-유천T/L 보호반대체","[즉시가압X] 유천S/S 154kV 신옥천-유천T/L 보호반대체","2024-11-04 09:00","2024-11-07 18:00","2024-11-04 09:00","2024-11-07 18:00","연속"]
[378,"대전세종충남","대전","은진함열#1 T/L","[송전][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지 설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지 설치공사","2024-11-22 07:00","2024-11-29 18:00","2024-11-22 07:00","2024-11-29 18:00","매일"]
[379,"대전세종충남","대전","논산은진#2 T/L","[취소시][즉시가압O]은진S/S 논산-은진#2T/L GIS 보통점검","은진S/S 논산-은진#2T/L GIS 보통점검","2024-11-26 09:00","2024-11-26 18:00","취소","취소","연속"]
[380,"대전세종충남","대전","논산은진#1 T/L","[취소시][즉시가압O]은진S/S 논산-은진#1T/L GIS 보통점검","은진S/S 논산-은진#1T/L GIS 보통점검","2024-11-25 09:00","2024-11-25 18:00","취소","취소","연속"]
[381,"대전세종충남","대전","신옥천추부#1 T/L","[즉시가압O] 추부S/S 신옥천-추부#1T/L GIS 차단기 부동작시험","추부S/S 신옥천-추부#1T/L GIS 차단기 부동작시험","2024-11-28 16:00","2024-11-28 18:00","2024-11-28 16:00","2024-11-28 18:00","연속"]
[382,"대전세종충남","대전","신옥천추부#2 T/L","[즉시가압O]추부S/S 신옥천-추부#2T/L GIS 차단기 부동작시험","추부S/S 신옥천-추부#2T/L GIS 차단기 부동작시험","2024-11-28 18:00","2024-11-28 20:00","2024-11-28 18:00","2024-11-28 20:00","연속"]
[383,"대전세종충남","대전","추부금산#2 T/L","[즉시가압O]추부S/S 추부-금산#2T/L GIS 차단기 부동작시험","추부S/S 추부-금산#2T/L GIS 차단기 부동작시험","2024-11-27 18:00","2024-11-27 20:00","2024-11-27 18:00","2024-11-27 20:00","연속"]
[384,"대전세종충남","대전","추부금산#1 T/L","[즉시가압O]추부S/S 추부-금산#1T/L GIS 차단기 부동작 시험","추부S/S 154kV 추부-금산#1T/L GIS 차단기 부동작 시험","2024-11-27 16:00","2024-11-27 18:00","2024-11-27 16:00","2024-11-27 18:00","연속"]
[385,"대전세종충남","서산","석문당진화력#2 T/L","서산P/O 효성제 170kV GIS 베어링 교체공사","(10월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#2T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#2T/L 687 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#2T/L 627 CB 보통점검","2024-11-13 09:30","2024-11-14 18:00","취소","취소","매일"]
[386,"대전세종충남","서산","석문당진화력#1 T/L","서산P/O 효성제 170kV GIS 베어링 교체공사","(10월 휴전신청 취소시) (즉시가압 가능) 당진화력S/S 154kV 석문-당진화력#1T/L 617 CB 베어링 교체 (병행) 석문S/S 154kV 석문-당진화력#1T/L IED 성능개선 (병행) 석문S/S 154kV 석문-당진화력#1T/L 617 CB 보통점검 (병행) 당진화력S/S 154kV 석문-당진화력#1T/L 617CB 보통점검","2024-11-11 09:30","2024-11-12 18:00","취소","취소","매일"]
[387,"대전세종충남","서산","서산대산#4 T/L","154kV 대산개폐소분기T/L 건설공사 외 1건","1. 154kV 대산개폐소분기T/L 건설공사 휴전작업 개요(서산-대산#4T/L) ○ No.74 ~ 75 전력선 공중이동 ○ 가철탑 조립 ○ No.75 그라운드암, 3번암 보강 2. 154kV 신성연-대산개폐소T/L 건설공사 ○ No.23-1 임시선로 구성(#4T/L)","2024-11-19 06:00","2024-11-22 18:00","2024-11-19 06:00","2024-11-22 18:00","연속"]
[388,"대전세종충남","서산","서산대산 T/L","'24~'25년 서산전력지사 송전협력회사 공사","154kV 서산-대산T/L 항공구 설치공사 No.9~10, 11~12(2경간) *즉시가압가능(20분이내) *10월 휴전 승인시 취소 요청 *154kV 서산-태안#1T/L 병가선로, 154kV 서산-태안#1T/L 휴전 미승인시 휴전 취소 요청","2024-11-02 05:00","2024-11-03 11:00","2024-11-02 05:00","2024-11-03 11:00","매일"]
[389,"대전세종충남","서산","서산대산#4 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","154kV 서산-대산#4T/L 항공장애표시구 설치공사 No.3~4(1경간) *즉시가압가능(20분이내) *주말작업 없음","2024-11-19 08:00","2024-11-20 18:00","취소","취소","매일"]
[390,"대전세종충남","서산","서산해미 T/L","'23년 서산P/O 장기사용 배전반 교체공사","(즉시가압불가) 154kV 서산-해미T/L 송전선로 보호반 교체공사","2024-11-07 16:00","2024-11-08 18:00","2024-11-07 16:00","2024-11-08 18:00","연속"]
[391,"대전세종충남","서산","서산대산#3 T/L","154kV 대산개폐소분기T/L 건설공사 외 1건","1. 154kV 대산개폐소분기T/L 건설공사 휴전작업 개요(서산-대산#3T/L) ○ No.74-1 조립 ○ No.75 1번암 교체보강 2. 154kV 신성연-대산개폐소T/L 건설공사 ○ No.23-1 임시선로 구성(#3T/L)","2024-11-23 06:00","2024-11-26 18:00","2024-11-23 06:00","2024-11-26 18:00","연속"]
[392,"대전세종충남","서산","서산대산#4 T/L","154kV 대산개폐소분기T/L 건설공사","154kV 대산개폐소분기T/L 건설공사 휴전작업 개요(서산-대산#4T/L) ○ No.74~No.75 전력선 공중이동 연,긴선 ○ 가철탑 철거","2024-11-27 06:00","2024-11-29 18:00","2024-11-27 06:00","2024-11-29 18:00","연속"]
[393,"대전세종충남","서산","서산홍성 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","(10월 휴전 취소시)수평 추락방지장치 설치공사 (서산T/L No.1~135) , 즉시가압(20분 이내) 가능","2024-11-27 08:00","2024-12-05 18:00","취소","취소","매일"]
[394,"대전세종충남","서산","서산태안#1 T/L","'24~'25년 서산전력지사 송전협력회사 공사","154kV 서산-대산T/L 항공구 설치공사 No.9~10, 11~12(2경간) *즉시가압가능(20분이내) *10월 휴전 승인시 취소 요청 *154kV 서산-대산T/L 병가선로, 154kV 서산-대산T/L 휴전 미승인시 휴전 취소 요청","2024-11-02 05:00","2024-11-03 11:00","2024-11-02 05:00","2024-11-03 11:00","매일"]
[395,"대전세종충남","서산","합덕송악#1 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","154kV 당진-송악#2T/L 항공장애표시구 설치공사 No.34~35 (1경간) *즉시가압가능(20분이내) *10월 휴전 승인시 취소 요청 *154kV 당진-송악#2T/L 병가선로, 154kV 당진-송악#2T/L 휴전 미승인시 휴전 취소 요청","2024-11-09 08:00","2024-11-10 18:00","취소","취소","매일"]
[396,"대전세종충남","서산","당진송악#2 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","154kV 당진-송악#2T/L 항공장애표시구 설치공사 No.34~35 (1경간) *즉시가압가능(20분이내) *10월 휴전 승인시 취소 요청 *154kV 합덕-송악#1T/L 병가선로, 154kV 합덕-송악#1T/L 휴전 미승인시 휴전 취소 요청","2024-11-09 08:00","2024-11-10 18:00","취소","취소","매일"]
[397,"대전세종충남","서산","신당진당진#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","(10월 휴전 취소시) 수평 추락방지장치 설치공사 (No.1~5,14~35) , 즉시가압(20분 이내) 가능","2024-11-26 08:00","2024-11-27 18:00","2024-11-26 08:00","2024-11-27 18:00","매일"]
[398,"대전세종충남","서산","신당진당진#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","(10월 휴전 취소시) 수평 추락방지장치 설치공사 (No.1~5,14~35) , 즉시가압(20분 이내) 가능","2024-11-22 08:00","2024-11-25 18:00","2024-11-22 08:00","2024-11-25 18:00","매일"]
[399,"대전세종충남","서산","신당진서산#2 T/L","24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 신당진S/S 154kV 신당진-서산#2T/L GIS 하자점검 (병행) 서산S/S 154kV 신당진-서산#2T/L GIS 보통점검 (병행) 신당진S/S 신당진-서산#2T/L CVT 대체 (병행) 서산S/S 154kV 신당진-서산#2T/L LA 보통점검 (송전병행) 154kV 신당진-서산#2T/L 수평 추락방지 설치","2024-11-21 09:30","2024-11-21 18:00","2024-11-21 09:30","2024-11-21 18:00","연속"]
[400,"대전세종충남","서산","아산합덕#2 T/L","24년 서산P/O 154kV GIS 정밀점검공사","(즉시가압 불가) 합덕S/S 154kV 아산-합덕#2T/L 617 GIS 정밀점검공사","2024-11-18 09:30","2024-11-20 18:00","취소","취소","연속"]
[401,"대전세종충남","서산","합덕송악#1 T/L","24년 서산P/O 154kV GIS 정밀점검공사","(즉시가압 불가) 합덕S/S 154kV 합덕-송악#1T/L 657 GIS 정밀점검공사","2024-11-25 09:30","2024-11-27 18:00","취소","취소","연속"]
[402,"대전세종충남","서산","합덕송악#2 T/L","24년 서산P/O 154kV GIS 정밀점검공사","(즉시가압 불가) 합덕S/S 154kV 합덕-송악#2T/L 687 GIS 정밀점검공사","2024-11-11 09:30","2024-11-13 18:00","취소","취소","연속"]
[403,"대전세종충남","세종","덕진대화#1 T/L","[변전]'24년 세종전력지사 변전협력회사 총액공사","○154kV GIS 차단기 조작시험 -전자변 교체 병행 -즉시가압 불가","2024-11-01 10:00","2024-11-01 18:00","2024-11-01 10:00","2024-11-01 18:00","연속"]
[404,"대전세종충남","세종","부강대청HP T/L","[안전목적 휴전][즉시가압O] 세종-부강#1T/L 애자 교체공사","[안전목적 휴전][즉시가압O] 154kV 세종-부강#1T/L 불량애자 교체공사 - 154kV 세종-부강#1T/L 상단의 154kV 부강-대청H/P T/L의 휴전","2024-11-14 07:00","2024-11-14 18:00","2024-11-14 07:00","2024-11-14 18:00","매일"]
[405,"대전세종충남","세종","세종서세종#1 T/L","[변전]'24년 세종P/O 154kV GIS 정밀점검공사(10월 취소시)","○154kV GIS 정밀점검공사 -PNL 43PDA 교체 병행 -즉시가압 불가","2024-11-04 09:00","2024-11-06 18:00","2024-11-04 09:00","2024-11-06 18:00","연속"]
[406,"대전세종충남","세종","세종서세종#2 T/L","[변전]'24년 세종P/O 154kV GIS 정밀점검공사(10월 취소시)","○154kV GIS 정밀점검공사 -즉시가압 불가","2024-11-11 09:00","2024-11-13 18:00","2024-11-11 09:00","2024-11-13 18:00","연속"]
[407,"대전세종충남","세종","세종월산#1 T/L","[즉시가압X] 154kV 세종-월산#1T/L 불량애자 교체공사","[즉시가압X] 154kV 세종-월산#1T/L 불량애자 교체공사 - 1시간 이내 가압 가능","2024-11-11 07:00","2024-11-11 18:00","2024-11-11 07:00","2024-11-11 18:00","매일"]
[408,"대전세종충남","세종","세종부강#2 T/L","[즉시가압X] 154kV 세종-부강#2T/L 불량애자 교체공사","[즉시가압X] 154kV 세종-부강#2T/L 불량애자 교체공사 - 요청 시 1시간 이내 가압 가능","2024-11-07 07:00","2024-11-08 18:00","취소","취소","매일"]
[409,"대전세종충남","세종","세종부강#1 T/L","[즉시가압X] 154kV 세종-부강#1T/L 불량애자 교체공사","[즉시가압X] 154kV 세종-부강#1T/L 불량애자 교체공사 - 요청 시 1시간 이내 가압 가능","2024-11-14 07:00","2024-11-15 18:00","취소","취소","매일"]
[410,"대전세종충남","세종","세종월산#2 T/L","[즉시가압X] 154kV 세종-월산#2T/L 불량애자 교체공사","[즉시가압X] 154kV 세종-월산#2T/L 불량애자 교체공사 - 1시간 이내 가압 가능","2024-11-12 07:00","2024-11-13 18:00","2024-11-12 07:00","2024-11-13 18:00","매일"]
[411,"대전세종충남","세종","천안전의#1 T/L","[변전]'24년 세종전력지사 변전협력회사 총액공사","○ 154kV GIS 보통점검 -즉시가압 가능","2024-11-04 10:00","2024-11-04 18:00","2024-11-04 10:00","2024-11-04 18:00","연속"]
[412,"대전세종충남","세종","조치원전의#1 T/L","[주말작업O][즉시가압X] 154kV 조치원-전의T/L 안전이격확보 공사","[주말작업O][즉시가압X] 154kV 조치원-전의T/L 안전이격확보 공사 - No.12~17","2024-11-28 07:00","2024-12-04 18:00","2024-11-28 07:00","2024-12-04 18:00","연속"]
[413,"대전세종충남","세종","조치원전의#1 T/L","[주말작업O][즉시가압X] 154kV 조치원-전의T/L 안전이격확보 공사","[주말작업O][즉시가압X] 154kV 조치원-전의T/L 안전이격확보 공사 - No.12~17","2024-11-01 07:00","2024-11-03 18:00","2024-11-01 07:00","2024-11-03 18:00","연속"]
[414,"대전세종충남","세종","조치원전의#2 T/L","[주말작업O][즉시가압X] 154kV 조치원-전의T/L 안전이격확보 공사","[주말작업O][즉시가압X] 154kV 조치원-전의T/L 안전이격확보 공사 - No.12~17","2024-11-04 07:00","2024-11-27 18:00","2024-11-04 07:00","2024-11-27 18:00","연속"]
[415,"대전세종충남","직할","덕진대화#2 T/L","덕진,대화S/S 덕진-대화#2T/L 송전선로 보호반 대체공사","O 덕진,대화S/S 덕진-대화#2T/L 송전선로 보호반 대체","2024-11-09 09:00","2024-11-11 18:00","2024-11-09 09:00","2024-11-11 18:00","연속"]
[416,"대전세종충남","직할","대덕둔지 T/L","둔지S/S 디지털 유압력계 교체공사","둔지S/S 디지털 유압력계 교체공사","2024-11-22 09:00","2024-11-22 18:00","2024-11-22 09:00","2024-11-22 18:00","연속"]
[417,"대전세종충남","직할","둔곡송강#1 T/L","(오동작 관련) 세니온제 보호계전기 성능개선 공사","ㅁ (오동작 관련) 세니온제 보호계전기 성능개선공사 ㅁ 기타사항 : 20분이내 가압조건가능, 휴전시간 최소화(09:00 ~ 14:00)","2024-11-24 09:00","2024-11-24 14:00","2024-11-24 09:00","2024-11-24 14:00","연속"]
[418,"대전세종충남","직할","송강신일#2 T/L","송강,신일S/S 송강-신일#2T/L 송전선로 보호반 대체공사","송강,신일S/S 송강-신일#2T/L 송전선로 보호반 대체","2024-11-02 09:00","2024-11-04 18:00","취소","취소","연속"]
[419,"대전세종충남","직할","부강신탄진 T/L","154kV 신탄진S/S 미래화공사(GIS로 인출변경)","154kV 신탄진S/S 미래화공사(GIS로 인출변경) - 송전정비팀 동대전신탄진#1,2T/L 11/26이전 조기종료 시 부강신탄진T/L 인출변경작업 11/27 시행예정","2024-11-27 09:00","2024-11-27 18:00","2024-11-27 09:00","2024-11-27 18:00","연속"]
[420,"대전세종충남","직할","신탄진대청HP T/L","154kV 신탄진S/S 미래화공사(GIS로 인출변경)","154kV 신탄진S/S 미래화공사(GIS로 인출변경) - 송전정비팀 동대전신탄진#1,2T/L 11/26이전 조기종료 시 신탄진대청HPT/L 인출변경작업 11/28~29 시행예정","2024-11-28 09:00","2024-11-29 18:00","2024-11-28 09:00","2024-11-29 18:00","연속"]
[421,"대전세종충남","천안","둔포직산#2 T/L","둔포S/S 154kV 직산-둔포#1, 2T/L CB 개폐타임측정","(10월취소시)(즉시가압가능)둔포S/S 154kV 직산-둔포#1, 2T/L CB 개폐타임측정","2024-11-07 14:00","2024-11-07 18:00","취소","취소","연속"]
[422,"대전세종충남","천안","둔포직산#1 T/L","둔포S/S 154kV 직산-둔포#1, 2T/L CB 개폐타임측정","(10월취소시)(즉시가압가능)둔포S/S 154kV 직산-둔포#1, 2T/L CB 개폐타임측정","2024-11-07 09:00","2024-11-07 14:00","취소","취소","연속"]
[423,"대전세종충남","천안","불당서천안#1 T/L","[송전] 154kV 대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2024-11-12 09:00","2024-11-15 18:00","취소","취소","연속"]
[424,"대전세종충남","천안","서천안탕정#2 T/L","[10월 취소시] 154kV 서천안-탕정T/L 추락방지장치 설치공사","[즉시가압가능,주말작업없음]154kV 서천안-탕정T/L No. 3 ~ 23 추락방지장치 설치 [병행작업] 항공장애표시구 설치공사 (7경간)","2024-11-18 07:00","2024-11-19 18:00","취소","취소","매일"]
[425,"대전세종충남","천안","서천안탕정#1 T/L","154kV 서천안-탕정T/L 추락방지장치 설치공사","[즉시가압가능]154kV 서천안-탕정T/L No. 3 ~ 23 추락방지장치 설치 [병행작업] 항공장애표시구 설치공사 (7경간)","2024-11-13 07:00","2024-11-14 18:00","취소","취소","매일"]
[426,"대전세종충남","천안","신온양한샘#1 T/L","154kV 북아산분기T/L 임시선로 설치공사","가. 철탑 : 임시철탑 1기 설치 및 철거 나. 전력선 : ACSR/AW 410㎟ x 2B x 2C(0.554km)","2024-11-04 07:00","2024-11-08 18:00","2024-11-04 07:00","2024-11-08 18:00","연속"]
[427,"대전세종충남","천안","신온양S/S CB 6200","신온양S/S 154kV 6200 BUS TIE GIS 보통점검","(즉시가압 가능)신온양S/S 154kV 6200 BUS TIE GIS 보통점검","2024-11-19 09:00","2024-11-19 18:00","취소","취소","연속"]
[428,"대전세종충남","천안","신온양석곡#2 T/L","신온양S/S 154kV 신온양-석곡#2T/L 보호반 성능개선","(10월취소시)(즉시가압불가)신온양S/S 154kV 신온양-석곡#2T/L 보호반 성능개선","2024-11-26 09:00","2024-11-26 18:00","2024-11-26 09:00","2024-11-26 18:00","연속"]
[429,"대전세종충남","천안","신온양한샘#2 T/L","154kV 북아산분기T/L 임시선로 설치공사","가. 철탑 : 임시철탑 1기 설치 및 철거 나. 전력선 : ACSR/AW 410㎟ x 2B x 2C(0.554km)","2024-11-11 07:00","2024-11-15 18:00","2024-11-11 07:00","2024-11-15 18:00","연속"]
[430,"대전세종충남","천안","신온양석곡#1 T/L","신온양S/S 154kV 신온양-석곡#1T/L 보호반 성능개선","(10월취소시)(즉시가압불가)신온양S/S 154kV 신온양-석곡#1T/L 보호반 성능개선","2024-11-25 09:00","2024-11-25 18:00","2024-11-25 09:00","2024-11-25 18:00","연속"]
[431,"대전세종충남","천안","신탕정S/S SEC CB 60610","신탕정S/S 154kV #60-65BUS 모선보호반 대체","(즉시가압불가)신탕정S/S 154kV #60-65BUS 모선보호반 대체","2024-11-26 09:00","2024-11-29 18:00","취소","취소","연속"]
[432,"대전세종충남","천안","신탕정S/S CB 6100","신탕정S/S 154kV #60-65BUS 모선보호반 대체","(즉시가압불가)신탕정S/S 154kV #60-65BUS 모선보호반 대체","2024-11-26 09:00","2024-11-29 18:00","취소","취소","연속"]
[433,"대전세종충남","천안","신탕정S/S CB 6200","신탕정S/S 154kV BUS TIE 6200 GIS 보통점검","(즉시가압가능)신탕정S/S 154kV BUS TIE 6100 GIS 보통점검","2024-11-20 09:00","2024-11-20 18:00","2024-11-20 09:00","2024-11-20 18:00","연속"]
[434,"대전세종충남","천안","신탕정S/S SEC CB 65660","신탕정S/S 154kV #60-65BUS 모선보호반 대체","(즉시가압불가)신탕정S/S 154kV #60-65BUS 모선보호반 대체","2024-11-26 09:00","2024-11-29 18:00","취소","취소","연속"]
[435,"대전세종충남","천안","아산온양#2 T/L","[10월취소시][즉시가압O]항공장애표시구 설치공사","[10월취소시][즉시가압O] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-11-17 07:00","2024-11-17 17:00","취소","취소","연속"]
[436,"대전세종충남","천안","아산예산#1 T/L","[10월취소시][즉시가압O]항공장애표시구 설치공사","[10월취소시][즉시가압O] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-11-17 07:00","2024-11-17 17:00","취소","취소","연속"]
[437,"대전세종충남","천안","아산인주#1 T/L","아산, 인주S/S 154kV 아산-인주#1T/L 노후 보호반 대체","(10월취소시)(즉시가압불가)아산, 인주S/S 154kV 아산-인주#1T/L 노후 보호반 대체","2024-11-16 09:00","2024-11-17 18:00","취소","취소","연속"]
[438,"대전세종충남","천안","아산예산#1 T/L","아산, 예산S/S 154kV 아산-예산#1T/L 노후 보호반 대체","(10월취소시)(즉시가압불가)아산, 예산S/S 154kV 아산-예산#1T/L 노후 보호반 대체","2024-11-17 09:00","2024-11-22 18:00","취소","취소","연속"]
[439,"대전세종충남","천안","아산S/S SEC CB 60610","아산S/S 154kV BUS SEC 60-61 GIS 하자점검","(10월취소시)(즉시가압가능)아산S/S 154kV BUS SEC 60-61 GIS 하자점검","2024-11-22 09:00","2024-11-22 18:00","2024-11-22 09:00","2024-11-22 18:00","연속"]
[440,"대전세종충남","천안","아산온양#2 T/L","[10월취소시][즉시가압O]항공장애표시구 설치공사","[10월취소시][즉시가압O] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-11-24 07:00","2024-11-24 17:00","2024-11-24 07:00","2024-11-24 17:00","연속"]
[441,"대전세종충남","천안","아산온양#1 T/L","[10월취소시][즉시가압O]항공장애표시구 설치공사","[10월취소시][즉시가압가능] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-11-10 07:00","2024-11-10 17:00","취소","취소","연속"]
[442,"대전세종충남","천안","아산S/S #66 BUS","아산S/S 154kV BUS SEC 65-66 GIS PD센서 보수","(10월취소시)(즉시가압불가)아산S/S 154kV BUS SEC 65-66 GIS PD센서 보수","2024-11-11 09:00","2024-11-12 18:00","취소","취소","연속"]
[443,"대전세종충남","천안","아산S/S SEC CB 65660","아산S/S 154kV BUS SEC 65-66 GIS PD센서 보수","(10월취소시)(즉시가압불가)아산S/S 154kV BUS SEC 65-66 GIS PD센서 보수","2024-11-11 09:00","2024-11-12 18:00","취소","취소","연속"]
[444,"대전세종충남","천안","아산S/S CB 6100","아산S/S 154kV BUS TIE 6100 GIS 하자점검","(10월취소시)(즉시가압가능)아산S/S 154kV BUS TIE 6100 GIS 하자점검","2024-11-14 09:00","2024-11-14 18:00","2024-11-14 09:00","2024-11-14 18:00","연속"]
[445,"대전세종충남","천안","아산합덕#1 T/L","154kV 아산-합덕T/L 추락방지장치 설치공사","[즉시가압가능,주말작업없음]154kV 아산-합덕T/L No. 13 ~ 52 추락방지장치 설치 [병가철탑](상단)신서산-아산#1 No.74~113,(하단)아산-합덕#1 No.13~52","2024-11-01 07:00","2024-11-07 18:00","2024-11-01 07:00","2024-11-07 18:00","매일"]
[446,"대전세종충남","천안","아산합덕#1 T/L","아산S/S 154kV 아산-합덕#1T/L GIS PD센서 불량 보수","(10월취소시)(즉시가압불가)아산S/S 154kV 아산-합덕#1T/L GIS PD센서 불량 보수","2024-11-28 09:00","2024-11-29 18:00","2024-11-28 09:00","2024-11-29 18:00","연속"]
[447,"대전세종충남","천안","아산S/S #65 BUS","아산S/S 154kV 아산-합덕#1T/L GIS PD센서 불량 보수","(10월취소시)(즉시가압불가)아산S/S 154kV 아산-합덕#1T/L GIS PD센서 불량 보수","2024-11-28 09:00","2024-11-29 18:00","2024-11-28 09:00","2024-11-29 18:00","연속"]
[448,"대전세종충남","천안","아산예산#2 T/L","아산, 예산S/S 154kV 아산-예산#2T/L 노후 보호반 대체","(10월취소시)(즉시가압불가)아산, 예산S/S 154kV 아산-예산#2T/L 노후 보호반 대체","2024-11-13 09:00","2024-11-15 18:00","취소","취소","연속"]
[449,"대전세종충남","천안","아산온양#1 T/L","[10월취소시][즉시가압O]항공장애표시구 설치공사","[10월취소시][즉시가압가능] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-11-03 07:00","2024-11-03 17:00","2024-11-03 07:00","2024-11-03 17:00","연속"]
[450,"대전세종충남","천안","아산예산#2 T/L","[10월취소시][즉시가압O]항공장애표시구 설치공사","[10월취소시][즉시가압O] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-11-03 07:00","2024-11-03 17:00","2024-11-03 07:00","2024-11-03 17:00","연속"]
[451,"대전세종충남","천안","온양풍세#2 T/L","온양S/S 온양-풍세#2T/L CB 개폐타임 측정, 전자변 교쳬","온양S/S 온양-풍세#2T/L CB 개폐타임 측정, 전자변 교쳬","2024-11-14 09:00","2024-11-14 18:00","취소","취소","연속"]
[452,"대전세종충남","천안","장재천안#1 T/L","154kV 장재-천안T/L 추락방지장치 설치공사","[즉시가압가능]154kV 장재-천안T/L No. 4 ~ 14 추락방지장치 설치 [병가철탑](상단)풍세-장재#2 No.18~23,(하단) 장재-천안#1 No.4~14 [병행작업] 항공장애표시구 설치 풍세-장재#2(3경간) 장재-천안#1 (2경간)","2024-11-26 07:00","2024-11-26 18:00","취소","취소","연속"]
[453,"대전세종충남","천안","장재불당#2 T/L","불당S/S 154kV 장재-불당#1, 2T/L CB 개폐타임측정","(10월취소시)(즉시가압가능)불당S/S 154kV 장재-불당#1, 2T/L CB 개폐타임측정개폐타임측정","2024-11-21 14:00","2024-11-21 18:00","취소","취소","연속"]
[454,"대전세종충남","천안","장재천안#2 T/L","[10월 취소시] 154kV 장재-천안T/L 추락방지장치 설치공사","[즉시가압가능]154kV 장재-천안T/L No. 4 ~ 14 추락방지장치 설치 [병가철탑](상단)풍세-장재#1 No.18~23,(하단) 장재-천안#2 No.4~14 [병행작업] 항공장애표시구 설치 풍세-장재#1(3경간) 장재-천안#2 (2경간)","2024-11-04 07:00","2024-11-04 18:00","취소","취소","연속"]
[455,"대전세종충남","천안","장재천안#2 T/L","장재, 천안S/S 154kV 장재-천안#1, 2T/L 노후 보호반 대체","(10월취소시)(즉시가압불가)장재, 천안S/S 154kV 장재-천안#1, 2T/L 노후 보호반 대체","2024-11-04 09:00","2024-11-06 18:00","2024-11-04 09:00","2024-11-06 18:00","연속"]
[456,"대전세종충남","천안","장재천안#1 T/L","장재, 천안S/S 154kV 장재-천안#1, 2T/L 노후 보호반 대체","(10월취소시)(즉시가압불가)장재, 천안S/S 154kV 장재-천안#1, 2T/L 노후 보호반 대체","2024-11-26 09:00","2024-11-29 18:00","취소","취소","연속"]
[457,"대전세종충남","천안","장재불당#1 T/L","불당S/S 154kV 장재-불당#1, 2T/L CB 개폐타임측정","(10월취소시)(즉시가압가능)불당S/S 154kV 장재-불당#1, 2T/L CB 개폐타임측정개폐타임측정","2024-11-21 09:00","2024-11-21 14:00","취소","취소","연속"]
[458,"대전세종충남","천안","신탕정탕정#2 T/L","탕정S/S 154kV 신탕정-탕정#1, 2T/L CB 개폐타임측정","(10월취소시)(즉시가압가능)탕정S/S 154kV 신탕정-탕정#1, 2T/L CB 개폐타임측정","2024-11-22 14:00","2024-11-22 18:00","취소","취소","연속"]
[459,"대전세종충남","천안","신탕정탕정#1 T/L","탕정S/S 154kV 신탕정-탕정#1, 2T/L CB 개폐타임측정","(10월취소시)(즉시가압가능)탕정S/S 154kV 신탕정-탕정#1, 2T/L CB 개폐타임측정","2024-11-22 09:00","2024-11-22 14:00","취소","취소","연속"]
[460,"대전세종충남","천안","풍세장재#2 T/L","154kV 풍세-장재T/L 추락방지장치 설치공사","[즉시가압가능]154kV 풍세-장재T/L No. 18 ~ 23 추락방지장치 설치 [병가철탑](상단)풍세-장재#2 No.18~23,(하단) 장재-천안#1 No.4~14 [병행작업] 항공장애표시구 설치 풍세-장재#2(3경간) 장재-천안#1 (2경간)","2024-11-26 07:00","2024-11-26 18:00","2024-11-26 07:00","2024-11-26 18:00","연속"]
[461,"대전세종충남","천안","온양풍세#2 T/L","[10월취소시][즉시가압O]항공장애표시구 설치공사","[10월취소시][즉시가압가능] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-11-24 07:00","2024-11-24 17:00","2024-11-24 07:00","2024-11-24 17:00","연속"]
[462,"대전세종충남","천안","온양풍세#1 T/L","[10월취소시][즉시가압O]항공장애표시구 설치공사","[10월취소시][즉시가압가능] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-11-10 07:00","2024-11-10 17:00","2024-11-10 07:00","2024-11-10 17:00","연속"]
[463,"대전세종충남","천안","풍세장재#1 T/L","[10월 취소시] 154kV 풍세-장재T/L 추락방지장치 설치공사","[즉시가압가능]154kV 풍세-장재T/L No. 18 ~ 23 추락방지장치 설치 [병가철탑](상단)풍세-장재#1 No.18~23,(하단) 장재-천안#2 No.4~14 [병행작업] 항공장애표시구 설치 풍세-장재#1(3경간) 장재-천안#2 (2경간)","2024-11-04 07:00","2024-11-04 18:00","2024-11-04 07:00","2024-11-04 18:00","연속"]
[464,"대전세종충남","청양","관창보령CC T/L","청양P/O 발주 및 협력공사(170 관창-보령복합)","154kV 관창-보령복합T/L GIS - 관창S/S 170kV GIS 정밀점검(본상) - 보령T/P 170kV GIS 보통점검(동규)","2024-11-05 09:00","2024-11-07 18:00","2024-11-25 09:00","2024-11-27 18:00","연속"]
[465,"대전세종충남","청양","청양관창#1 T/L","청양P/O 변전협력 총액공사(청관 LA)","154kV 청양-관창#1T/L - 관창S/S LA A,B,C상 보통 (즉시가압 가능)","2024-11-05 09:00","2024-11-05 14:00","2024-11-05 09:00","2024-11-05 14:00","연속"]
[466,"대전세종충남","청양","보령T/P CB 6100","청양P/O 변전협력 총액공사(보령T/P 6100 조작)","청양P/O 변전협력 총액공사(보령T/P 6100 조작) 보령T/P 154kV BUS TIE GIS - 6100 차단기 조작시험 (즉시가압가능)","2024-11-12 10:00","2024-11-12 14:00","2024-11-12 10:00","2024-11-12 14:00","연속"]
[467,"대전세종충남","청양","옥산부여#2 T/L","[송전] (10월 취소시)154KV 옥산부여T/L 수평추락방지장치 설치","No.1~65 수평추락방지장치 설치","2024-11-05 08:00","2024-11-15 18:00","취소","취소","매일"]
[468,"대전세종충남","청양","옥산부여#1 T/L","[송전] (10월 취소시)154KV 옥산부여T/L 수평추락방지장치 설치","No.1~65 수평추락방지장치 설치","2024-11-18 09:00","2024-11-25 18:00","취소","취소","매일"]
[469,"대전세종충남","청양","청양S/S SEC CB 60610","청양P/O 변전협력 총액공사(청양 60610 조작)","청양P/O 변전협력 총액공사(청양 60610 조작) 청양S/S 154kV SEC GIS - 60610 차단기 조작시험 (즉시가압가능)","2024-11-07 09:00","2024-11-07 14:00","2024-11-07 09:00","2024-11-07 14:00","연속"]
[470,"대전세종충남","청양","청양S/S SEC CB 65660","청양P/O 변전협력 총액공사(청양 65660 조작)","청양P/O 변전협력 총액공사(청양 65660 조작) 청양S/S 154kV SEC GIS - 65660 차단기 조작시험 (즉시가압가능)","2024-11-07 14:00","2024-11-07 18:00","2024-11-07 14:00","2024-11-07 18:00","연속"]
[471,"대전세종충남","청양","청양S/S CB 6100","청양P/O 변전협력 총액공사(청양 6100 조작)","청양P/O 변전협력 총액공사(청양 6100 조작) 청양S/S 154kV BUS TIE GIS - 6100 차단기 조작시험 (즉시가압가능)","2024-11-06 09:00","2024-11-06 14:00","2024-11-06 09:00","2024-11-06 14:00","연속"]
[472,"대전세종충남","청양","청양S/S CB 6200","청양P/O 변전협력 총액공사(청양 6200 조작)","청양P/O 변전협력 총액공사(청양 6200 조작) 청양S/S 154kV BUS TIE GIS - 6200 차단기 조작시험 (즉시가압가능)","2024-11-06 14:00","2024-11-06 18:00","2024-11-06 14:00","2024-11-06 18:00","연속"]
[473,"전북","군산","군산이리#1 T/L","군산P/O LA,CVT 점검공사","군산-이리#1TL LA, CVT 점검 -(병행)차단기 보통점검","2024-11-06 13:00","2024-11-06 18:00","취소","취소","연속"]
[474,"전북","군산","군산이리#2 T/L","군산P/O LA,CVT 점검공사","군산-이리#1TL LA, CVT 점검 -(병행)차단기 보통점검","2024-11-07 13:00","2024-11-07 18:00","취소","취소","연속"]
[475,"전북","군산","비응군장#2 T/L","군산P/O 차단기 보통점검공사","비응S/S 비응-군장#2T/L GIS 보통점검","2024-11-12 14:00","2024-11-12 18:00","2024-11-12 14:00","2024-11-12 18:00","연속"]
[476,"전북","군산","비응군장#1 T/L","군산P/O 차단기 보통점검공사","비응S/S 비응-군장#1T/L GIS 보통점검","2024-11-12 09:00","2024-11-12 14:00","2024-11-12 09:00","2024-11-12 14:00","연속"]
[477,"전북","군산","영등S/S #60 BUS","군산P/O 170kV GIS 정밀점검공사(무부하 가압용)","영등S/S #3M.Tr 1차 GIS 정밀점검공사(무부하 가압용)","2024-11-07 17:30","2024-11-07 18:00","2024-11-07 17:30","2024-11-07 18:00","연속"]
[478,"전북","군산","영등팔봉#1 T/L","군산P/O 170kV GIS 정밀점검공사(무부하 가압용)","영등S/S #3M.Tr 1차 GIS 정밀점검공사(무부하 가압용)","2024-11-07 17:30","2024-11-07 18:00","2024-11-07 17:30","2024-11-07 18:00","연속"]
[479,"전북","군산","영등팔봉#1 T/L","군산P/O 170kV GIS 정밀점검공사","팔봉S/S #3M.Tr 1차 GIS 정밀점검공사","2024-11-05 17:30","2024-11-05 18:00","2024-11-05 17:30","2024-11-05 18:00","연속"]
[480,"전북","김제","정주고창#2 T/L","고창S/S #2M.Tr 1차 GIS 정밀점검(11.25~27,연속)","고창S/S 154kV #2M.Tr 1차 GIS 차단기,단로기 정밀점검(11.25~27,연속)","2024-11-26 16:00","2024-11-27 18:00","취소","취소","매일"]
[481,"전북","김제","고창영광 T/L","고창S/S 고창-영광T/L GIS 정밀점검(11.04~06, 연속)","고창S/S 고창-영광T/L GIS 차단기,단로기 정밀점검(11.04~06, 연속)","2024-11-04 09:00","2024-11-06 18:00","취소","취소","연속"]
[482,"전북","김제","정주고창#1 T/L","고창S/S 고창-영광T/L GIS 정밀점검(11.04~06, 연속)","고창S/S 고창-영광T/L GIS 차단기,단로기 정밀점검(11.04~06, 연속)","2024-11-05 16:00","2024-11-06 18:00","취소","취소","매일"]
[483,"전북","김제","고창홍농 T/L","고창S/S 고창-홍농T/L GIS 정밀점검(11.11~13, 연속)","고창S/S 고창-홍농T/L GIS 차단기,단로기 정밀점검(11.11~13, 연속)","2024-11-11 09:00","2024-11-13 18:00","취소","취소","연속"]
[484,"전북","김제","정주고창#2 T/L","고창S/S 고창-홍농T/L GIS 정밀점검(11.11~13, 연속)","고창S/S 고창-홍농T/L GIS 차단기,단로기 정밀점검(11.11~13, 연속)","2024-11-12 16:00","2024-11-13 18:00","취소","취소","매일"]
[485,"전북","김제","정주고창#1 T/L","고창S/S 154kV BUS-TIE 정밀점검(11.18~20,연속)","고창S/S #1-#2BUS-TIE GIS 차단기,단로기 정밀점검(11.18~20, 연속)","2024-11-19 16:00","2024-11-20 18:00","취소","취소","매일"]
[486,"전북","김제","백산김제#2 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-11-20 08:00","2024-11-20 18:00","취소","취소","매일"]
[487,"전북","김제","백산김제#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-11-19 08:00","2024-11-19 18:00","취소","취소","매일"]
[488,"전북","김제","정공정주#2 T/L","154kV 정공-정주T/L 용량증대 전선교체공사(No.13~정주S/S)","- 공사구간 : 154kV 정공-정주T/L No.13~정주S/S) - 전력선 교체 : 10.828C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, SB댐퍼 등]","2024-11-16 07:00","2024-11-30 17:00","2024-11-16 07:00","2024-11-30 17:00","연속"]
[489,"전북","김제","정공칠보HP T/L","154kV 정공-정주T/L 용량증대 전선교체공사(No.13~정주S/S)","- 공사구간 : 154kV 정공-정주T/L No.13~정주S/S) - 전력선 교체 : 10.828C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, SB댐퍼 등]","2024-11-12 07:00","2024-11-15 17:00","2024-11-12 07:00","2024-11-15 17:00","연속"]
[490,"전북","김제","정공정주#1 T/L","154kV 정공-정주T/L 용량증대 전선교체공사(No.13~정주S/S)","- 공사구간 : 154kV 정공-정주T/L No.13~정주S/S) - 전력선 교체 : 10.828C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, SB댐퍼 등]","2024-11-01 07:00","2024-11-15 17:00","2024-11-01 07:00","2024-11-15 17:00","연속"]
[491,"전북","김제","정공담양 T/L","154kV 정공-정주T/L 용량증대 전선교체공사(No.13~정주S/S)","- 공사구간 : 154kV 정공-정주T/L No.13~정주S/S) - 전력선 교체 : 10.828C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, SB댐퍼 등]","2024-11-27 07:00","2024-11-30 17:00","2024-11-27 07:00","2024-11-30 17:00","연속"]
[492,"전북","직할","무주진안 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","○ 154kV 무주-진안T/L No.104~175 수평 추락방지시설 설치 ○ 154kV 무주분기(무주-진안)T/L No.1~45 수평 추락방지시설 설치","2024-11-01 07:00","2024-11-08 17:00","2024-11-01 07:00","2024-11-08 17:00","매일"]
[493,"전북","직할","북전주S/S CB 6100","북전주S/S 6100BUSTIE GIS 정밀점검","북전주S/S 6100BUSTIE GIS 정밀점검","2024-11-04 09:00","2024-11-07 18:00","2024-11-04 09:00","2024-11-07 18:00","연속"]
[494,"전북","직할","북전주봉동#1 T/L","북전주S/S 6100BUSTIE 1DS 무부하가압 선로 휴전","북전주S/S 6100BUSTIE 1DS 무부하가압 선로 휴전","2024-11-05 16:00","2024-11-05 16:30","2024-11-05 16:00","2024-11-05 16:30","연속"]
[495,"전북","직할","북전주봉동#1 T/L","북전주S/S 6100BUSTIE 2DS 무부하가압 선로 휴전","북전주S/S 6100BUSTIE 2DS 무부하가압 선로 휴전","2024-11-07 16:00","2024-11-07 16:30","2024-11-07 16:00","2024-11-07 16:30","연속"]
[496,"전북","직할","북전주진안 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","○ 154kV 북전주-진안T/L No.1~175 수평 추락방지시설 설치","2024-11-11 07:00","2024-11-19 17:00","2024-11-11 07:00","2024-11-19 17:00","매일"]
[497,"전북","직할","전주서곡#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-11-12 08:00","2024-11-13 18:00","취소","취소","매일"]
[498,"전북","직할","전주서곡#2 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-11-14 08:00","2024-11-15 18:00","취소","취소","매일"]
[499,"전북","직할","진안장수#1 T/L","진안S/S #1BUSTIE 무부하가압 선로 휴전","진안S/S #1BUSTIE 무부하가압 선로 휴전","2024-11-26 16:00","2024-11-26 16:30","2024-11-26 16:00","2024-11-26 16:30","연속"]
[500,"전북","직할","진안장수#1 T/L","진안S/S #3M.Tr 6333GIS 무부하가압 선로 휴전","진안S/S #3M.Tr 6333GIS 무부하가압 선로 휴전","2024-11-28 16:00","2024-11-28 16:30","2024-11-26 16:00","2024-11-26 16:30","연속"]
[501,"전북","군산","팔봉S/S #60 BUS","군산P/O 170kV GIS 정밀점검공사(무부하 가압용)","팔봉S/S #3M.Tr 1차 GIS 정밀점검공사(무부하가압용)","2024-11-05 17:30","2024-11-05 18:00","2024-11-05 17:30","2024-11-05 18:00","연속"]
[502,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2024-11-06 09:00","2024-11-08 18:00","2024-11-06 09:00","2024-11-08 18:00","연속"]
[503,"전북","직할","봉동S/S CB 6100","봉동변전소 6100BUSTIE GIS 정밀점검공사","봉동변전소 6100BUSTIE GIS 정밀점검공사","2024-11-11 09:00","2024-11-14 18:00","2024-11-11 09:00","2024-11-14 18:00","연속"]
[504,"전북","김제","김제S/S CB 6100","김제S/S 154kV 모선보호반 대체","김제S/S 154kV 모선보호반 대체","2024-11-11 09:00","2024-11-15 18:00","2024-11-11 09:00","2024-11-15 18:00","연속"]
[505,"전북","직할","북전주봉동#1 T/L","봉동변전소 6100 GIS 정밀점검 1DS 무부하가압","봉동변전소 6100 GIS 정밀점검 1DS 무부하가압","2024-11-12 16:30","2024-11-12 17:00","2024-11-12 16:30","2024-11-12 17:00","연속"]
[506,"전북","직할","북전주봉동#1 T/L","봉동변전소 6100 GIS 정밀점검 2DS 무부하가압","봉동변전소 6100 GIS 정밀점검 2DS 무부하가압","2024-11-14 11:00","2024-11-14 11:30","2024-11-14 11:00","2024-11-14 11:30","연속"]
[507,"전북","직할","탄소전주#1 T/L","전주변전소 전주-탄소#1TL GIS 정밀점검공사","전주변전소 전주-탄소#1TL GIS 정밀점검공사","2024-11-18 09:00","2024-11-19 18:00","취소","취소","연속"]
[508,"전북","직할","동전주북전주#1 T/L","동전주변전소 6333 GIS 정밀점검 1DS,CB 무부하가압","동전주변전소 6333 GIS 정밀점검 1DS,CB 무부하가압","2024-11-21 16:30","2024-11-21 17:00","2024-11-21 16:30","2024-11-21 17:00","연속"]
[509,"광주전남","강진","강진남창#1 T/L","154kV 영신분기T/L 건설공사","○ 임시선로 → 본선로 공중이동 - (NO.53 - 가철탑 - NO.54) → (NO.53 - C/T#1 , C/T#2 - NO.54) ○ 무부하 시험 및 사용 전 검사","2024-11-18 07:00","2024-11-30 18:00","취소","취소","연속"]
[510,"광주전남","강진","나주금천#2 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-11-08(금) 08:00 ~ 2024-11-11(월) 18:00 ○ 작업구간 : 154kV 남광주-금천#1T/L No.7~21, 23~52, 82 ○ 작업내용 : 정밀점검 ○ 비고 : 11/8(금) ~ 11/11(월) 4회선 구간 병행휴전 시행 (나주-금천#2T/L)","2024-11-08 08:00","2024-11-11 18:00","취소","취소","매일"]
[511,"광주전남","강진","나주금천#1 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-11-12(화) 08:00 ~ 2024-11-18(월) 18:00 ○ 작업구간 : 154kV 남광주-금천#2T/L No.7~21, 23~52, 82 ○ 작업내용 : 정밀점검 ○ 비고 : 11/15(금)~11/18(월) 4회선 구간 병행휴전 시행 (나주-금천#1T/L)","2024-11-15 08:00","2024-11-18 18:00","취소","취소","매일"]
[512,"광주전남","강진","나주엄다#1 T/L","154kV 나주-엄다T/L 피뢰기 절연열화진단","작업내용 : 지중송전설비 피뢰기 절연열화진단 작업구간 : 나주S/S 인출","2024-11-18 09:00","2024-11-18 18:00","취소","취소","연속"]
[513,"광주전남","강진","나주엄다#2 T/L","154kV 나주-엄다T/L 피뢰기 절연열화진단","작업내용 : 지중송전설비 피뢰기 절연열화진단 작업구간 : 나주S/S 인출","2024-11-19 09:00","2024-11-19 18:00","취소","취소","연속"]
[514,"광주전남","강진","대불남악#1 T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 하자점검","2024-11-22 09:00","2024-11-22 14:00","취소","취소","매일"]
[515,"광주전남","강진","대불남악#2 T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 하자점검","2024-11-22 14:00","2024-11-22 18:00","2024-11-22 14:00","2024-11-22 18:00","연속"]
[516,"광주전남","강진","신강진대불#2 T/L","2024년 하반기 강진전력지사 170kV GIS 정밀점검 공사(가칭)","170kV GIS 정밀점검(CB)","2024-11-13 14:00","2024-11-15 18:00","취소","취소","연속"]
[517,"광주전남","강진","신강진대불#1 T/L","2024년 하반기 강진전력지사 170kV GIS 정밀점검 공사(가칭)","170kV GIS 정밀점검(CB)","2024-11-11 09:00","2024-11-13 18:00","취소","취소","연속"]
[518,"광주전남","강진","대불남악#2 T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 하자점검","2024-11-06 14:00","2024-11-06 18:00","2024-11-06 14:00","2024-11-06 18:00","연속"]
[519,"광주전남","강진","대불삼호#1 T/L","2024년 하반기 강진전력지사 170kV GIS 정밀점검 공사(가칭)","170kV GIS 정밀점검(CB)","2024-11-25 09:00","2024-11-27 18:00","취소","취소","연속"]
[520,"광주전남","강진","대불삼호#2 T/L","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","대불S/S 대불삼호#2T/L GIS 보통점검","2024-11-01 10:00","2024-11-01 18:00","취소","취소","연속"]
[521,"광주전남","강진","대불남악#1 T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 하자점검","2024-11-06 09:00","2024-11-06 14:00","2024-11-06 09:00","2024-11-06 14:00","연속"]
[522,"광주전남","강진","삼호화원#1 T/L","154kV 삼호-화원 지중T/L(복도체화) 건설공사","154kV XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2024-11-04 09:00","2024-11-29 18:00","취소","취소","연속"]
[523,"광주전남","강진","신강진강진#2 T/L","'24년 하반기 강진전력지사 효성제 170kV GIS 개선","170kV GIS 개선","2024-11-21 14:00","2024-11-21 18:00","취소","취소","연속"]
[524,"광주전남","강진","신강진해남#2 T/L","'24년 하반기 강진전력지사 효성제 170kV GIS 개선","170kV GIS 개선","2024-11-05 14:00","2024-11-05 18:00","취소","취소","연속"]
[525,"광주전남","강진","화원진도#2 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 화원-진도#2 T/L 40~78호호 39기","2024-11-14 06:00","2024-11-19 18:00","2024-11-14 06:00","2024-11-19 18:00","매일"]
[526,"광주전남","강진","해남진도#1 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 해남-진도#1 T/L 1,4~8,16~74,87~95,102~104호 78기","2024-11-04 06:00","2024-11-13 18:00","2024-11-04 06:00","2024-11-13 18:00","매일"]
[527,"광주전남","강진","해남해남CS#1 T/L","'24년 하반기 강진전력지사 효성제 170kV GIS 개선","170kV GIS 개선","2024-11-19 14:00","2024-11-19 18:00","2024-11-19 14:00","2024-11-19 18:00","연속"]
[528,"광주전남","강진","해남진도#1 T/L","'24년 하반기 강진전력지사 효성제 170kV GIS 개선","170kV GIS 개선","2024-11-06 10:00","2024-11-06 18:00","취소","취소","연속"]
[529,"광주전남","강진","해남진도#2 T/L","'24년 하반기 강진전력지사 효성제 170kV GIS 개선","170kV GIS 개선","2024-11-07 10:00","2024-11-07 18:00","취소","취소","연속"]
[530,"광주전남","강진","해남해남CS#2 T/L","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 보통점검","2024-11-19 09:00","2024-11-19 14:00","2024-11-19 09:00","2024-11-19 14:00","연속"]
[531,"광주전남","광주","신광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 154kV 신광주-계림 #2T/L GIS 조작시험(즉시가압 가능)","2024-11-08 14:00","2024-11-08 18:00","2024-11-08 14:00","2024-11-08 18:00","연속"]
[532,"광주전남","광주","계림승주#1 T/L","154kV 계림-승주T/L 지장송전선로 이설공사","106호~승주변전소간 전선교체, 107호 철탑신설,107호 기설철탑","2024-11-11 07:00","2024-11-13 18:00","2024-11-11 07:00","2024-11-13 18:00","연속"]
[533,"광주전남","광주","계림승주#2 T/L","154kV 계림-승주T/L 지장송전선로 이설공사","106호~승주변전소간 전선교체, 107호 철탑신설,107호 기설철탑","2024-11-14 07:00","2024-11-16 18:00","2024-11-14 07:00","2024-11-16 18:00","연속"]
[534,"광주전남","광주","계림S/S CB 6100","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 154kV #60-65BUSTIE GIS 조작시험","2024-11-06 09:00","2024-11-06 14:00","2024-11-06 09:00","2024-11-06 14:00","연속"]
[535,"광주전남","광주","계림승주#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 154kV 계림-승주 #1T/L GIS 조작시험","2024-11-06 14:00","2024-11-06 18:00","2024-11-06 14:00","2024-11-06 18:00","연속"]
[536,"광주전남","광주","북광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 154kV 북광주-계림 #1T/L GIS 조작시험(즉시가압 가능)","2024-11-07 09:00","2024-11-07 14:00","2024-11-07 09:00","2024-11-07 14:00","연속"]
[537,"광주전남","광주","북광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 154kV 북광주-계림 #2T/L GIS 조작시험(즉시가압 가능)","2024-11-07 14:00","2024-11-07 18:00","2024-11-07 14:00","2024-11-07 18:00","연속"]
[538,"광주전남","광주","신광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 154kV 신광주-계림 #1T/L GIS 조작시험(즉시가압 가능)","2024-11-08 09:00","2024-11-08 14:00","2024-11-08 09:00","2024-11-08 14:00","연속"]
[539,"광주전남","광주","남광주금천#1 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-11-05(화) 08:00 ~ 2024-11-11(월) 18:00 ○ 작업구간 : 154kV 남광주-금천#1T/L No.7~21, 23~52, 82 ○ 작업내용 : 정밀점검","2024-11-05 08:00","2024-11-11 18:00","취소","취소","매일"]
[540,"광주전남","광주","남광주화순#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 남광주-화순#2TL 수평추락방지 설치 작업구간 : 남광주-화순(2~8호), 화순-승주(290~296호) 7기 병가","2024-11-11 07:00","2024-11-11 18:00","취소","취소","연속"]
[541,"광주전남","광주","남광주금천#2 T/L","2024년 광주전력 변전협력회사 총액공사","□작업명 : 남광주SS 남광주금천#2TL 보통점검","2024-11-29 09:00","2024-11-29 18:00","취소","취소","연속"]
[542,"광주전남","광주","남광주금천#2 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-11-12(화) 08:00 ~ 2024-11-18(월) 18:00 ○ 작업구간 : 154kV 남광주-금천#2T/L No.7~21, 23~52, 82 ○ 작업내용 : 정밀점검","2024-11-12 08:00","2024-11-18 18:00","취소","취소","매일"]
[543,"광주전남","광주","신광주일곡#2 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 신광주-일곡T/L 수평 추락방지장치 설치 No. 2,3,12~15(7기)","2024-11-26 07:00","2024-11-26 18:00","2024-11-26 07:00","2024-11-26 18:00","매일"]
[544,"광주전남","광주","신광주계림#1 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 신광주-계림T/L 수평 추락방지장치 설치 No. 16~27.2(8기)","2024-11-27 07:00","2024-11-27 18:00","2024-11-27 07:00","2024-11-27 18:00","매일"]
[545,"광주전남","광주","신광주계림#2 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 신광주-계림T/L 수평 추락방지장치 설치 No. 16~27.2(8기)","2024-11-27 14:00","2024-11-28 18:00","2024-11-27 14:00","2024-11-28 18:00","매일"]
[546,"광주전남","광주","신광주일곡#1 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 신광주-일곡T/L 수평 추락방지장치 설치 No. 2,3,12~15(7기)","2024-11-25 07:00","2024-11-25 18:00","2024-11-25 07:00","2024-11-25 18:00","매일"]
[547,"광주전남","광주","신화순S/S #1 EM.Tr CB","신화순 FR-ESS 정기점검","신화순 FR-ESS 정기점검","2024-11-11 09:00","2024-11-15 18:00","2024-11-11 09:00","2024-11-15 18:00","연속"]
[548,"광주전남","광주","신화순S/S #1 EM.Tr CB","신화순 FR-ESS 정기점검","신화순 FR-ESS 정기점검","2024-11-11 09:00","2024-11-15 18:00","취소","취소","연속"]
[549,"광주전남","광주","신화순매월#1 T/L","2024년 직할 가공송전 순시점검 위탁공사","○ 작업일시 : 2024-11-19(화) 08:00 ~ 11-20(수) 18:00 ○ 작업구간 : 154kV 신화순-매월#1T/L No.1, 10~17, 69, 69.1 (11기) ○ 작업내용 : 정밀점검","2024-11-19 08:00","2024-11-20 18:00","2024-11-19 08:00","2024-11-20 18:00","매일"]
[550,"광주전남","광주","화순승주#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 남광주-화순#2TL 수평추락방지 설치 작업구간 : 남광주-화순(2~8호), 화순-승주(290~296호) 7기 병가","2024-11-11 07:00","2024-11-11 18:00","취소","취소","연속"]
[551,"광주전남","목포","대불남악#1 T/L","24~25년 송전협력회사 공사(항공장애구 설치)","154kV 대불-남악T/L OPGW 항공장애표시구 설치공사","2024-11-04 09:00","2024-11-08 18:00","2024-11-04 09:00","2024-11-08 18:00","매일"]
[552,"광주전남","목포","목포북항#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","목포S/S 154kV 목포-북항#2T/L GIS 보통점검","2024-11-19 09:00","2024-11-19 18:00","취소","취소","연속"]
[553,"광주전남","목포","목포북항#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","목포S/S 154kV 목포-북항#1T/L GIS 보통점검 북항S/S 154kV 목포-북항#1T/L GIS 조작시험, LA 점검","2024-11-18 09:00","2024-11-18 18:00","취소","취소","연속"]
[554,"광주전남","목포","남악북항#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","북항S/S 154kV 남악-북항#1T/L GIS 조작시험, LA 점검 남악S/S 154kV 남악-북항#1T/L GIS 보통점검","2024-11-20 09:00","2024-11-20 18:00","취소","취소","연속"]
[555,"광주전남","목포","남악북항#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","북항S/S 154kV 남악-북항#2T/L GIS 조작시험, LA 점검","2024-11-21 09:00","2024-11-21 18:00","취소","취소","연속"]
[556,"광주전남","목포","엄다S/S #2 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","2024-11-19 09:00","2024-12-13 18:00","2024-11-19 09:00","2024-12-13 18:00","연속"]
[557,"광주전남","목포","나주엄다#1 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)","154kV 나주-엄다T/L 피뢰기 설치(116기)","2024-11-11 08:00","2024-11-27 18:00","취소","취소","매일"]
[558,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","2차분 무부하가압용 T/L","2024-11-18 09:00","2024-11-19 18:00","2024-11-18 09:00","2024-11-19 18:00","연속"]
[559,"광주전남","목포","엄다목포#2 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)","154kV 나주-엄다T/L 피뢰기 설치 병가구간 휴전 및 154kV 엄다-목포T/L 피뢰기 설치","2024-11-21 08:00","2024-12-06 18:00","취소","취소","매일"]
[560,"광주전남","목포","장성영광#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","GIS 조작시험","2024-11-13 09:00","2024-11-13 18:00","취소","취소","연속"]
[561,"광주전남","목포","장성영광#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","GIS 조작시험","2024-11-14 09:00","2024-11-14 18:00","취소","취소","연속"]
[562,"광주전남","목포","장성영광#1 T/L","154kV 영광-홍농 등 4개T/L 선종교체공사","1. 공사명 : 154kV 영광-홍농 등 4개T/L 선종교체공사 2. 공사내용 ○ 24.11.11~11.29일 (고창-홍농T/L) ○ 24.11.11~11.29일 (4회선 상단) 장성-영광#1 선종교체공사를 위한 안전휴전 (연속휴전_송전운영부)","2024-11-11 07:00","2024-11-29 18:00","취소","취소","연속"]
[563,"광주전남","목포","영광S/S 재원태양광T/L CB","2024~2025년 목포전력지사 변전협력회사 공사","GIS 보통점검","2024-11-13 09:00","2024-11-13 18:00","2024-11-13 09:00","2024-11-13 18:00","연속"]
[564,"광주전남","목포","장성영광#2 T/L","2024년도 가공송전선로 순시점검 위탁공사","154kV 장성-영광T/L 조류착지방지장치 설치작업","2024-11-07 09:00","2024-11-07 18:00","취소","취소","연속"]
[565,"광주전남","목포","장성영광#1 T/L","2024년도 가공송전선로 순시점검 위탁공사","154kV 장성-영광T/L 조류착지방지장치 설치작업","2024-11-06 09:00","2024-11-06 18:00","취소","취소","연속"]
[566,"광주전남","목포","운남S/S CB 6100","154kV 운남S/S 170kV GIS 증설공사(신안S/S 건설사업)","170kV GIS 2Bay 증설 - 운남-신안#1,2T/L (지중)","2024-11-11 09:00","2024-11-23 14:00","2024-11-11 09:00","2024-11-23 14:00","연속"]
[567,"광주전남","목포","고창홍농 T/L","154kV 영광-홍농 등 4개T/L 선종교체공사","1. 공사명 : 154kV 영광-홍농 등 4개T/L 선종교체공사 2. 공사내용 ○ 24.11.11~11.29일 (고창-홍농T/L) ○ 24.11.11~11.29일 (4회선 상단) 장성-영광#2 선종교체공사를 위한 안전휴전 (연속휴전_송전운영부)","2024-11-11 07:00","2024-11-29 18:00","2024-11-11 07:00","2024-11-29 18:00","연속"]
[568,"광주전남","순천","벌교고흥#1 T/L","24~25년 순천전력지사 변전협력회사 공사","고흥S/S 벌교-고흥#1T/L LA, CVT 보통점검 벌교S/S 벌교-고흥#1T/L GIS 타임측정","2024-11-28 09:00","2024-11-28 18:00","취소","취소","연속"]
[569,"광주전남","순천","벌교고흥#2 T/L","24~25년 순천전력지사 변전협력회사 공사","고흥S/S 벌교-고흥#2T/L LA, CVT 보통점검 벌교S/S 벌교-고흥#2T/L GIS 타임측정","2024-11-29 09:00","2024-11-29 18:00","취소","취소","연속"]
[570,"광주전남","순천","광양태금#1 T/L","24-25년 순천전력지사 변전협력회사 공사","광양S/S 광양-태금#1T/L LA 보통점검","2024-11-01 09:00","2024-11-01 18:00","2024-11-01 09:00","2024-11-01 18:00","연속"]
[571,"광주전남","순천","승주서순천 T/L","24~25년 순천전력지사 변전협력회사 공사","서순천S/S 승주-서순천T/L GIS 타임측정","2024-11-05 09:00","2024-11-05 18:00","취소","취소","연속"]
[572,"광주전남","순천","세풍율촌#1 T/L","24~25년 순천전력지사 변전협력회사 공사","율촌, 세풍S/S 세풍율촌#1 T/L GIS 초기점검","2024-11-20 09:00","2024-11-20 18:00","취소","취소","연속"]
[573,"광주전남","순천","백운세풍#2 T/L","24~25년 순천전력지사 변전협력회사 공사","백운, 세풍S/S 백운세풍#2 T/L GIS 초기점검","2024-11-19 09:00","2024-11-19 18:00","취소","취소","연속"]
[574,"광주전남","순천","세풍율촌#2 T/L","24~25년 순천전력지사 변전협력회사 공사","율촌, 세풍S/S 세풍율촌#2 T/L GIS 초기점검","2024-11-21 09:00","2024-11-21 18:00","취소","취소","연속"]
[575,"광주전남","순천","백운세풍#1 T/L","24~25년 순천전력지사 변전협력회사 공사","백운, 세풍S/S 백운세풍#1 T/L GIS 초기점검","2024-11-18 09:00","2024-11-18 18:00","취소","취소","연속"]
[576,"광주전남","순천","소라서순천#2 T/L","순천전력 가공협력회사 공사(애자련보강, 금구류 교체)","소라-서순천 #2 No.63,121,호 금구류 보강 No. 119호 애자련보강","2024-11-25 07:00","2024-11-26 18:00","2024-11-25 07:00","2024-11-26 18:00","매일"]
[577,"광주전남","순천","소라서순천#1 T/L","순천전력 가공협력회사 공사(애자련보강, 금구류 교체)","소라-서순천 #1 No.63,121,호 금구류 보강 No. 119호 애자련보강","2024-11-21 07:00","2024-11-22 18:00","2024-11-21 07:00","2024-11-22 18:00","매일"]
[578,"광주전남","순천","순천율촌#1 T/L","345kV 광양-여수TPT/L 일부구간 지중화 공사","345kV - 154kV 선로 횡단에 따른 휴전 - 154kV 선로 작업 없음","2024-11-06 07:30","2024-11-11 18:00","2024-11-20 07:30","2024-11-25 18:00","연속"]
[579,"광주전남","순천","순천율촌#2 T/L","345kV 광양-여수TPT/L 일부구간 지중화 공사","345kV - 154kV 선로 횡단에 따른 휴전 - 154kV 선로 작업 없음","2024-11-06 07:30","2024-11-11 18:00","2024-11-20 07:30","2024-11-25 18:00","연속"]
[580,"광주전남","순천","순천율촌#2 T/L","345kV 광양-여수TPT/L 일부구간 지중화 공사","345kV - 154kV 선로 횡단에 따른 휴전 - 154kV 선로 작업 없음","2024-11-18 07:30","2024-11-22 18:00","취소","취소","연속"]
[581,"광주전남","순천","순천율촌#1 T/L","345kV 광양-여수TPT/L 일부구간 지중화 공사","345kV - 154kV 선로 횡단에 따른 휴전 - 154kV 선로 작업 없음","2024-11-18 07:30","2024-11-22 18:00","취소","취소","연속"]
[582,"광주전남","순천","순천승주#1 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","순천S/S 순천-승주#1T/L GIS 보통점검","2024-11-18 09:00","2024-11-18 18:00","2024-11-18 09:00","2024-11-18 18:00","연속"]
[583,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주T/L 지중화 연장공사(요청자 직접시행)","154kV 순천-승주T/L 지중화 연장공사(요청자 직접시행) ○ 요청자 : 그린산업개발 주식회사 ○ 시공사 : 주식회사 한백 ○ 감리사 : 더원엔지니어링 주식회사","2024-11-25 08:00","2024-11-27 18:00","취소","취소","연속"]
[584,"광주전남","순천","순천율촌#1 T/L","154kV 송전선로 보호반 세니온제 유사고장","154kV 송전선로 보호반 세니온제 유사고장","2024-11-27 09:00","2024-11-27 18:00","취소","취소","연속"]
[585,"광주전남","순천","순천승주#1 T/L","안전이격확보(154kV 계림-승주T/L 지장송전선로 이설공사)","106호~승주변전소간 전선교체, 107호 철탑신설,107호 기설철탑","2024-11-11 07:00","2024-11-13 18:00","2024-11-11 07:00","2024-11-13 18:00","매일"]
[586,"광주전남","순천","순천승주#2 T/L","안전이격거리확보(154kV 계림-승주T/L 지장송전선로 이설공사)","106호~승주변전소간 전선교체, 107호 철탑신설,107호 기설철탑","2024-11-14 07:00","2024-11-16 18:00","2024-11-14 07:00","2024-11-16 18:00","매일"]
[587,"광주전남","순천","승주서순천 T/L","154kV 승주-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-20 07:00","2024-11-20 18:00","2024-11-20 07:00","2024-11-20 18:00","연속"]
[588,"광주전남","순천","용성여수산단#2 T/L","154kV 용성-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-11 07:00","2024-11-11 18:00","2024-11-11 07:00","2024-11-11 18:00","연속"]
[589,"광주전남","순천","용성여수산단#1 T/L","154kV 용성-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-08 07:00","2024-11-08 18:00","2024-11-08 07:00","2024-11-08 18:00","연속"]
[590,"광주전남","순천","여수TP여천#2 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-06 07:00","2024-11-07 18:00","2024-11-06 07:00","2024-11-07 18:00","매일"]
[591,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-04 07:00","2024-11-05 18:00","2024-11-04 07:00","2024-11-05 18:00","매일"]
[592,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-08 07:00","2024-11-08 18:00","2024-11-08 07:00","2024-11-08 18:00","연속"]
[593,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-11 07:00","2024-11-11 18:00","2024-11-11 07:00","2024-11-11 18:00","연속"]
[594,"광주전남","순천","호남TP여수TP#2 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 설치","2024-11-12 07:00","2024-11-12 12:00","2024-11-12 07:00","2024-11-12 12:00","연속"]
[595,"광주전남","순천","여수T/P SEC CB 60610","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-11-15 15:20","2024-11-15 15:40","취소","취소","연속"]
[596,"광주전남","순천","여수T/P SEC CB 65660","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-11-15 15:00","2024-11-15 15:20","취소","취소","연속"]
[597,"광주전남","순천","여수TP화치#1 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 설치","2024-11-12 12:00","2024-11-12 18:00","2024-11-12 12:00","2024-11-12 18:00","연속"]
[598,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2024-11-27 09:00","2024-11-28 18:00","취소","취소","연속"]
[599,"광주전남","순천","여수T/P #66 BUS","호남T/P-여수T/P #2TL #2DS 가스누기","호남T/P-여수T/P #2TL #2DS 가스누기(즉시가압 불가)","2024-11-25 09:00","2024-11-26 18:00","취소","취소","연속"]
[600,"광주전남","순천","호남TP여수TP#2 T/L","호남T/P-여수T/P #2TL #2DS 가스누기","호남T/P-여수T/P #2TL #2DS 가스누기(즉시가압 불가)","2024-11-25 09:00","2024-11-26 18:00","취소","취소","연속"]
[601,"광주전남","순천","여수T/P CB 6200","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-11-22 15:40","2024-11-22 16:00","취소","취소","연속"]
[602,"광주전남","순천","여수T/P SEC CB 60610","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-11-22 15:20","2024-11-22 15:40","취소","취소","연속"]
[603,"광주전남","순천","여수T/P SEC CB 65660","154kV #61-66 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-11-22 15:00","2024-11-22 15:20","취소","취소","연속"]
[604,"광주전남","순천","여수T/P CB 6100","154kV #60-65 모선보호반 대체(즉시가압 가능)","CB접점 확인, DS 절체시험(기계적 접점 확인용) TIE-SEC 동시휴전 아님","2024-11-15 15:40","2024-11-15 16:00","취소","취소","연속"]
[605,"광주전남","순천","여천여수#2 T/L","24~25년 순천전력지사 변전협력회사 공사","여수S/S GIS 보통점검 및 여천S/S GIS 보통점검 및 전자변교체","2024-11-07 09:00","2024-11-07 18:00","2024-11-07 09:00","2024-11-07 18:00","연속"]
[606,"광주전남","순천","여천여수#1 T/L","24~25년 순천전력지사 변전협력회사 공사","여수S/S GIS 보통점검 및 여천S/S GIS 타임측정","2024-11-06 09:00","2024-11-06 18:00","2024-11-06 09:00","2024-11-06 18:00","연속"]
[607,"광주전남","순천","여천여수산단#2 T/L","24~25년 순천전력지사 변전협력회사 공사","여천-여수산단#2T/L CB 개폐타임측정","2024-11-08 09:00","2024-11-08 14:00","2024-11-08 09:00","2024-11-08 14:00","연속"]
[608,"광주전남","순천","여수TP용성#1 T/L","용성S/S 여수TP-용성#1T/L GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2024-11-04 09:00","2024-11-05 18:00","취소","취소","연속"]
[609,"광주전남","순천","용성여수산단#2 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","여수산단,용성S/S 용성-여수산단#2T/L GIS 보통점검","2024-11-13 09:00","2024-11-14 18:00","취소","취소","매일"]
[610,"광주전남","순천","순천율촌#1 T/L","순천-율촌#1T/L GIS #1,2DS 가스누기","순천-율촌#1T/L GIS #1,2DS 가스누기(즉시가압 불가)","2024-11-18 09:00","2024-11-20 18:00","취소","취소","연속"]
[611,"광주전남","순천","율촌S/S #66 BUS","순천-율촌#1T/L GIS #1,2DS 가스누기","순천-율촌#1T/L GIS #1,2DS 가스누기(즉시가압 불가)","2024-11-19 14:00","2024-11-20 18:00","취소","취소","연속"]
[612,"광주전남","순천","율촌S/S #65 BUS","#2M.Tr 1차 GIS #2DS 가스누기조치","#2M.Tr 1차 GIS #2DS 가스누기조치(즉시가압불가)","2024-11-13 09:00","2024-11-14 18:00","취소","취소","연속"]
[613,"광주전남","순천","율촌화치#2 T/L","순천전력 가공협력회사 공사(피뢰기,애자련보강,압축인류클램프)","순천-율촌 #1 No.1호 피뢰기 설치 순천-율촌 #1 No.119호 애자련 보강 율촌-화치 #2 No.46호 압축인류클램프 정비","2024-11-27 07:00","2024-11-28 18:00","2024-11-27 07:00","2024-11-28 18:00","매일"]
[614,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-25 07:00","2024-11-26 18:00","취소","취소","매일"]
[615,"광주전남","순천","율촌S/S #61 BUS","순천-율촌#1T/L GIS #1,2DS 가스누기","순천-율촌#1T/L GIS #1,2DS 가스누기(즉시가압 불가)","2024-11-18 09:00","2024-11-19 14:00","취소","취소","연속"]
[616,"광주전남","순천","율촌S/S #66 BUS","순천-율촌#1T/L GIS #1,2DS 가스누기","순천-율촌#1T/L GIS #1,2DS 가스누기(즉시가압 불가)","2024-11-19 14:00","2024-11-20 18:00","취소","취소","연속"]
[617,"광주전남","순천","율촌여수산단#2 T/L","율촌-여수산단#2T/L GIS #1DS 가스누기","율촌-여수산단#2T/L GIS #1DS 가스누기(즉시가압 불가)","2024-11-25 09:00","2024-11-26 18:00","취소","취소","연속"]
[618,"광주전남","순천","율촌화치#1 T/L","순천전력 가공협력회사 공사(피뢰기,애자련보강,압축인류클램프)","율촌-화치 #1 No.42호 압축인류클램프 정비","2024-11-29 07:00","2024-11-29 18:00","2024-11-29 07:00","2024-11-29 18:00","연속"]
[619,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-11-27 07:00","2024-11-28 18:00","취소","취소","매일"]
[620,"광주전남","순천","율촌여수산단#1 T/L","순천전력 가공협력회사 공사(피뢰기,애자련보강,압축인류클램프)","율촌-화치 #2 No.46호 압축인류클램프 정비","2024-11-28 07:00","2024-11-28 18:00","취소","취소","연속"]
[621,"광주전남","순천","태금하동화력 T/L","효성제 170kv gis 부품 교체 시행","효성제 170kv gis 부품 교체 시행(즉시가압 불가)","2024-11-08 14:00","2024-11-08 18:00","취소","취소","연속"]
[622,"광주전남","순천","호남TP여수TP#1 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","호남T/P, 여수T/P 호남TP-여수TP#1T/L GIS 보통점검","2024-11-07 09:00","2024-11-08 18:00","2024-11-07 09:00","2024-11-08 18:00","매일"]
[623,"광주전남","순천","호남TP여수TP#2 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","호남T/P, 여수T/P 호남TP-여수TP#2T/L GIS 보통점검","2024-11-11 09:00","2024-11-12 18:00","2024-11-11 09:00","2024-11-12 18:00","매일"]
[624,"광주전남","순천","여수TP화치#2 T/L","2024년 순천전력지사 362,170kV GIS 정밀,보통점검공사","화치S/S 여수TP-화치#2T/L GIS 보통점검","2024-11-15 09:00","2024-11-15 18:00","2024-11-15 09:00","2024-11-15 18:00","연속"]
[625,"광주전남","직할","남광주금천#2 T/L","154kV 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 임시철탑 1기 설치 ○ 전력선 철거 : 2.6C-km ○ 전력선 신설 : 2.4C-km □ 기 타 : 토요일 작업 예정","2024-11-18 07:30","2024-11-23 18:00","2024-11-18 07:30","2024-11-23 18:00","연속"]
[626,"광주전남","직할","나주금천#2 T/L","154kV 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 임시철탑 1기 설치 ○ 전력선 철거 : 2.6C-km ○ 전력선 신설 : 2.4C-km □ 기 타 : 토요일 작업 예정","2024-11-25 07:00","2024-11-30 18:00","2024-11-25 07:00","2024-11-30 18:00","연속"]
[627,"광주전남","직할","남광주금천#1 T/L","154kV 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 임시철탑 1기 설치 ○ 전력선 철거 : 2.6C-km ○ 전력선 신설 : 2.4C-km □ 기 타 : 토요일 작업 예정","2024-11-25 07:30","2024-11-30 18:00","2024-11-25 07:30","2024-11-30 18:00","연속"]
[628,"광주전남","직할","나주금천#1 T/L","154kV 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 임시철탑 1기 설치 ○ 전력선 철거 : 2.6C-km ○ 전력선 신설 : 2.4C-km □ 기 타 : 토요일 작업 예정","2024-11-18 07:00","2024-11-23 18:00","2024-11-18 07:00","2024-11-23 18:00","연속"]
[629,"광주전남","직할","일곡비아#1 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검 상부 BUS 가스 누기 개소 조치","2024-11-18 09:00","2024-11-20 18:00","2024-11-18 09:00","2024-11-20 18:00","연속"]
[630,"광주전남","직할","수완흑석#1 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검 T/L 보호반 대체","2024-11-04 09:00","2024-11-06 14:00","2024-11-04 09:00","2024-11-06 14:00","연속"]
[631,"광주전남","직할","수완흑석#2 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검 T/L 보호반 대체","2024-11-06 14:00","2024-11-08 18:00","2024-11-06 14:00","2024-11-08 18:00","연속"]
[632,"광주전남","직할","수완흑석#2 T/L","수완S/S 154kV 수완-하남T/L GIS 증설공사","#1BUS 무부하가압용","2024-11-14 14:00","2024-11-15 14:00","2024-11-14 14:00","2024-11-15 14:00","연속"]
[633,"광주전남","직할","수완흑석#2 T/L","수완S/S 154kV 수완-하남T/L GIS 증설공사","#2BUS 무부하가압용","2024-11-20 14:00","2024-11-21 14:00","2024-11-20 14:00","2024-11-21 14:00","연속"]
[634,"대구","경산","영천S/S #2 EM.Tr CB","24~25년 경산P/O 변전협력회사 총액공사","ESS 변전설비 초기점검","2024-11-04 09:30","2024-11-08 18:00","2024-11-04 09:30","2024-11-08 18:00","연속"]
[635,"대구","경산","자인S/S #1 BUS","자인S/S 154kV GIS 증설공사(모선구분)","[#60-61 BUS SECTION 설치] ○ #60BUS GIB 철거및 COVER 설치 (모선분리) ○ 철거구간 : #2M.Tr 좌측 (공정도참조) ○ 무부하가압 완료후 : #60BUS 운전 (61BUS 휴전) ○ #60-61 BUS-SECTION 설치 및 시험 ○ #1BUS END COVER 철거 및 BELLOWS 설치 (모선연결)","2024-11-25 09:00","2024-12-05 16:00","2024-11-25 09:00","2024-12-05 16:00","연속"]
[636,"대구","경산","대구자인#1 T/L","자인S/S 154kV GIS 증설공사(모선구분)","[#60-61 BUS SECTION 설치] ○ GIS 설치기간 휴전수반 ○ BELLOWS, SECTION 설치부 무부하가압(24H) [#65-66 BUS SECTION 설치] ○ GIS 설치기간 휴전수반 ○ BELLOWS, SECTION 설치부 무부하가압(24H)","2024-11-25 09:00","2024-12-17 16:00","2024-11-25 09:00","2024-12-17 16:00","연속"]
[637,"대구","경산","경산자인#2 T/L","자인변전소 외벽마감재 교체공사","자인변전소 외벽마감재 교체공사","2024-11-27 08:00","2024-12-05 17:00","취소","취소","매일"]
[638,"대구","경산","대구자인#1 T/L","자인변전소 외벽마감재 교체공사","자인변전소 외벽마감재 교체공사","2024-11-11 08:00","2024-11-21 17:00","취소","취소","매일"]
[639,"대구","경산","대구자인#2 T/L","자인S/S 154kV GIS 증설공사(모선구분)","[BUS-TIE, PT&ES 설치] ○ GIS 설치기간 휴전수반 ○ 대구-자인 #2T/L LID 케이블 이설","2024-11-07 09:00","2024-11-21 16:00","2024-11-07 09:00","2024-11-21 16:00","연속"]
[640,"대구","달성","왜관다사#1 T/L","(토건)다사S/S 외벽마감재 교체공사","(토건)다사S/S 외벽마감재 교체공사","2024-11-25 08:00","2024-12-01 17:00","취소","취소","연속"]
[641,"대구","달성","왜관다사#2 T/L","(토건)다사S/S 외벽마감재 교체공사","(토건)다사S/S 외벽마감재 교체공사","2024-11-25 08:00","2024-12-01 17:00","취소","취소","연속"]
[642,"대구","달성","왜관다사#1 T/L","(토건)다사S/S 외벽마감재 교체공사","(토건)다사S/S 외벽마감재 교체공사","2024-11-18 08:00","2024-11-21 17:00","취소","취소","연속"]
[643,"대구","달성","왜관다사#2 T/L","(토건)다사S/S 외벽마감재 교체공사","(토건)다사S/S 외벽마감재 교체공사","2024-11-18 08:00","2024-11-21 17:00","취소","취소","연속"]
[644,"대구","칠곡","김천금릉#1 T/L","금릉S/S 154kV GIS 노후 보조계전기 교체","금릉S/S 154kV GIS 노후 보조계전기 교체","2024-11-20 09:30","2024-11-20 14:00","2024-11-20 09:30","2024-11-20 14:00","연속"]
[645,"대구","칠곡","김천금릉#2 T/L","금릉S/S 154kV GIS 노후 보조계전기 교체","금릉S/S 154kV GIS 노후 보조계전기 교체","2024-11-20 14:00","2024-11-20 18:00","2024-11-20 14:00","2024-11-20 18:00","연속"]
[646,"대구","칠곡","어모김천#1 T/L","김천SA 어모-김천SA#1T/L 6A7 GIS 하자점검","김천SA 어모-김천SA#1T/L 6A7 GIS 하자점검","2024-11-22 09:30","2024-11-22 14:00","2024-11-22 09:30","2024-11-22 14:00","연속"]
[647,"대구","칠곡","농소김천#2 T/L","2024년 칠곡전력 가공송전순시점검 위탁공사","154kV 농소-김천#2T/L 정밀점검 - No.1~19","2024-11-23 09:00","2024-11-24 18:00","2024-11-23 09:00","2024-11-24 18:00","연속"]
[648,"대구","칠곡","농소김천#1 T/L","2024년 칠곡전력 가공송전순시점검 위탁공사","154kV 농소-김천#1T/L 정밀점검 No1~19","2024-11-02 09:00","2024-11-03 18:00","2024-11-02 09:00","2024-11-03 18:00","연속"]
[649,"대구","칠곡","북대구연락#2 T/L","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 154kV 인출측 정비","2024-11-15 07:30","2024-11-19 18:00","2024-11-15 07:30","2024-11-19 18:00","연속"]
[650,"대구","칠곡","서대구남인동#2 T/L","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 154kV 인출측 정비","2024-11-26 07:30","2024-11-28 18:00","2024-11-26 07:30","2024-11-28 18:00","연속"]
[651,"대구","칠곡","서대구칠곡#1 T/L","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 154kV 인출측 정비","2024-11-26 07:30","2024-11-28 18:00","2024-11-26 07:30","2024-11-28 18:00","연속"]
[652,"대구","칠곡","서대구남인동#1 T/L","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 154kV 인출측 정비","2024-11-15 07:30","2024-11-19 18:00","2024-11-15 07:30","2024-11-19 18:00","연속"]
[653,"대구","칠곡","왜관S/S #1 BUS","154kV #3M.Tr 증설공사","154kV #3M.Tr 1차 및 SEC 60-61-0 GIS 설치","2024-11-04 09:00","2024-11-13 18:00","2024-11-04 09:00","2024-11-13 18:00","연속"]
[654,"대구","칠곡","북대구왜관#2 T/L","154kV #3M.Tr 증설공사","154kV GIS 설치관련 안전이격거리 확보","2024-11-15 09:00","2024-11-16 18:00","2024-11-15 09:00","2024-11-16 18:00","연속"]
[655,"대구","칠곡","왜관S/S #2 BUS","154kV #3M.Tr 증설공사","154kV #3M.Tr 1차 및 SEC 60-61-0 GIS 설치","2024-11-15 09:00","2024-11-23 18:00","2024-11-15 09:00","2024-11-23 18:00","연속"]
[656,"대구","칠곡","북대구왜관#2 T/L","154kV #3M.Tr 증설공사","154kV GIS 설치관련 안전이격거리 확보","2024-11-04 09:00","2024-11-05 18:00","2024-11-04 09:00","2024-11-05 18:00","연속"]
[657,"대구","포항","울주외동#2 T/L","2024~25년 포항전력지사 변전총액공사","외동S/S 627 GIS 조작시험","2024-11-12 09:00","2024-11-12 18:00","2024-11-12 09:00","2024-11-12 18:00","연속"]
[658,"대구","포항","울주외동#1 T/L","2024~25년 포항전력지사 변전총액공사","외동S/S 울주-외동#1T/L LA 보통점검","2024-11-11 09:00","2024-11-11 18:00","2024-11-11 09:00","2024-11-11 18:00","연속"]
[659,"경북","구미","상주화동#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사","154kV 상주-화동#2T/L 추락방지시설 설치(수평 52기 No.3~54)","2024-11-13 07:30","2024-11-21 18:00","2024-11-13 07:30","2024-11-21 16:30","매일"]
[660,"경북","구미","상주화동#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사","154kV 상주-화동#1T/L 추락방지시설 설치(수평 52기 No.3~54)","2024-11-04 07:30","2024-11-12 18:00","2024-11-04 07:30","2024-11-12 16:30","매일"]
[661,"경북","구미","선산청리#2 T/L","2024-25년 구미전력지사 변전협력회사 공사","- 6442 DS 내부점검","2024-11-11 14:00","2024-11-12 18:00","2024-11-11 14:00","2024-11-12 18:00","연속"]
[662,"경북","구미","화동영동 T/L","2024-2025년 구미전력지사 송전협력회사 공사","154kV 화동-영동T/L 추락방지시설 설치(수평 27기 No.111~137)","2024-11-27 07:30","2024-12-03 18:00","취소","취소","매일"]
[663,"경북","구미","화동보은 T/L","2024-2025년 구미전력지사 송전협력회사 공사","154kV 화동-보은T/L 추락방지시설 설치(수평 27기 No.111~137)","2024-11-22 07:30","2024-11-27 18:00","취소","취소","매일"]
[664,"경북","영주","문경단양 T/L","2024-25년 영주전력지사 변전협력회사 공사","보호반 성능개선","2024-11-02 09:00","2024-11-02 18:00","2024-11-15 09:00","2024-11-15 18:00","연속"]
[665,"경북","영주","봉화현종산풍력 T/L","2024-25년 영주전력지사 가공송전정비 협력회사 총액공사","상간스페이서 설치","2024-11-11 08:00","2024-11-14 17:00","2024-11-11 08:00","2024-11-14 17:00","연속"]
[666,"경북","영주","봉화울진 T/L","2024-25년 영주전력지사 가공송전정비 협력회사 총액공사","상간스페이서 설치","2024-11-20 08:00","2024-11-22 17:00","2024-11-20 08:00","2024-11-22 17:00","연속"]
[667,"경북","영주","예천점촌#2 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-11-10 09:00","2024-11-11 18:00","취소","취소","연속"]
[668,"경북","영주","동상주점촌#2 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-11-06 09:00","2024-11-07 18:00","취소","취소","연속"]
[669,"경북","영주","예천점촌#1 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-11-08 09:00","2024-11-09 18:00","취소","취소","연속"]
[670,"경북","영주","동상주점촌#1 T/L","2024년 영주전력지사 154kV GIS 정밀점검공사","154kV GIS 정밀점검","2024-11-04 09:00","2024-11-05 18:00","취소","취소","연속"]
[671,"경북","직할","동안동임하HP T/L","`24~25년 경북본부 직할 변전협력회사 공사","동안동S/S 동안동-임하HP T/L 보호반 교체","2024-11-04 09:00","2024-11-08 18:00","2024-11-04 09:00","2024-11-08 18:00","연속"]
[672,"경북","직할","안동풍산 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","추락방지장치 설치공사","2024-11-14 08:00","2024-11-20 18:00","2024-11-14 08:00","2024-11-20 18:00","연속"]
[673,"경북","직할","안동안동HP T/L","'24~25년 경북 직할 가공송전 협력회사 공사","추락방지장치설치공사","2024-11-18 08:00","2024-11-19 18:00","2024-11-18 08:00","2024-11-19 18:00","매일"]
[674,"경북","직할","영덕진보#1 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","추락방지장치 설치공사","2024-11-21 08:00","2024-11-29 18:00","2024-11-21 08:00","2024-11-29 18:00","연속"]
[675,"경북","직할","울진현종산풍력 T/L","`24~25년 경북본부 직할 변전협력회사 공사","현종산S/Y 울진-현종산풍력T/L GIS 보통점검 울진S/S 울진-현종산풍력T/L GIS 초기점검","2024-11-19 09:00","2024-11-19 18:00","2024-11-19 09:00","2024-11-19 18:00","매일"]
[676,"경북","직할","봉화현종산풍력 T/L","`24~25년 경북본부 직할 변전협력회사 공사","현종산S/Y 봉화-현종산T/L GIS 보통점검","취소","취소","취소","취소","연속"]
[677,"부산울산","동부산","구서S/S #1 BUS","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#2T/L GIS CB, #1DS, #1BUS 철거 및 신규 GIS 설치 ○ (구)BUS-TIE GIS CB, #1DS, #1BUS 철거 및 #60-61BUS-SEC DS 설치","2024-11-04 09:00","2024-11-16 18:00","2024-11-04 09:00","2024-11-16 18:00","연속"]
[678,"부산울산","동부산","구서S/S #2 BUS","154kV 구서S/S 장기사용 GIS 교체공사(3차)","○ 154kV 신양산-구서#2T/L GIS #2BUS 철거 및 신규 GIS 설치 ○ (구)BUS-TIE GIS #2BUS 철거 및 #65-66BUS-SEC DS 설치","2024-11-18 09:00","2024-11-29 18:00","2024-11-18 09:00","2024-11-29 18:00","연속"]
[679,"부산울산","동부산","노포정관#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","-고정형 폴리머점퍼지지애자 설치","2024-11-02 07:00","2024-11-03 18:00","2024-11-02 07:00","2024-11-03 18:00","연속"]
[680,"부산울산","동부산","신울산명례#1 T/L","명례S/S 154kV 기장연구로 신규수용공사","○ 170kV GIS 1CCT 증설 - 시험가압선로 (#2BUS #2DS투입상태_24시간) - 시험가압선로 (#1BUS #1DS투입상태_1시간)","2024-11-20 13:00","2024-11-21 17:00","2024-11-20 13:00","2024-11-21 17:00","연속"]
[681,"부산울산","동부산","명례장안 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-11-30 07:30","2024-11-30 18:00","2024-11-30 07:30","2024-11-30 18:00","연속"]
[682,"부산울산","동부산","신울산명례#1 T/L","명례S/S 154kV 기장연구로 신규수용공사","○ 170kV GIS 1CCT 증설 - 시험가압선로 (#2BUS #2DS개방상태_24시간)","2024-11-12 17:00","2024-11-13 17:00","2024-11-12 17:00","2024-11-13 17:00","연속"]
[683,"부산울산","동부산","신울산명례#1 T/L","명례S/S 154kV 기장연구로 신규수용공사","○ 170kV GIS 1CCT 증설 - 시험가압선로 (#1BUS #1DS개방상태_24시간)","2024-11-07 17:00","2024-11-08 17:00","2024-11-07 17:00","2024-11-08 17:00","연속"]
[684,"부산울산","동부산","수영우동 T/L","수영S/S 627GIS 보통점검","수영S/S 627GIS 보통점검 병행) 우동S/S 617GIS 차단기 동작시험","2024-11-09 09:30","2024-11-09 17:00","2024-11-09 09:30","2024-11-09 17:00","연속"]
[685,"부산울산","동부산","신양산구서#1 T/L","철탑현장 실측 및 도면작성용역","154kV 신양산-구서#1T/L 30호 현장실측","2024-11-30 09:00","2024-11-30 18:00","2024-11-30 09:00","2024-11-30 18:00","연속"]
[686,"부산울산","동부산","우동대연 T/L","우동S/S 627GIS 차단기 동작시험","우동S/S 627GIS 차단기 동작시험","2024-11-16 09:30","2024-11-16 17:00","2024-11-16 09:30","2024-11-16 17:00","연속"]
[687,"부산울산","동부산","장안고리NP T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-11-15 07:30","2024-11-15 18:00","취소","취소","연속"]
[688,"부산울산","북부산","양산산막#1 T/L","산막S/S 장기사용 154kV GIS 대체공사","산막S/S 언양-산막#1T/L 대체 -시험가압선로 : 양산-산막#1T/L","2024-11-01 18:00","2024-11-02 18:00","2024-11-01 18:00","2024-11-02 18:00","연속"]
[689,"부산울산","북부산","서창산막#1 T/L","2024년 북부산전력지사 가공송전 순시점검 위탁공사","154kV 서창-산막#1T/L 정밀점검 -점검대상 : 총 82기(No.1 ~ 87-1호 80기 및 S/T 2기)","2024-11-18 09:00","2024-11-22 18:00","2024-11-18 09:00","2024-11-22 18:00","연속"]
[690,"부산울산","북부산","서창산막#2 T/L","2024년 북부산전력지사 가공송전 순시점검 위탁공사","154kV 서창-산막#2T/L 정밀점검 -점검대상 : 총 82기(No.1 ~ 87-1호 80기 및 S/T 2기)","2024-11-25 09:00","2024-11-29 18:00","2024-11-25 09:00","2024-11-29 18:00","연속"]
[691,"부산울산","북부산","엄궁학장#1 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","1. 대 상 : 154kV 엄궁-학장#1T/L 2. 작업내용 : 접속함 절연유채유 3. 업체명 : 공영전력","2024-11-18 09:00","2024-11-18 18:00","취소","취소","연속"]
[692,"부산울산","북부산","엄궁학장#2 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","1. 대 상 : 154kV 엄궁-학장#2T/L 2. 작업내용 : 접속함 절연유채유 3. 업체명 : 공영전력","2024-11-19 09:00","2024-11-19 18:00","취소","취소","연속"]
[693,"부산울산","북부산","학장개금#1 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","1. 대 상 : 154kV 학장-개금#1T/L 2. 작업내용 : 접속함 절연유채유 3. 업체명 : 공영전력","2024-11-13 09:00","2024-11-13 18:00","취소","취소","연속"]
[694,"부산울산","북부산","학장개금#2 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","1. 대 상 : 154kV 학장-개금#2T/L 2. 작업내용 : 접속함 절연유채유 3. 업체명 : 공영전력","2024-11-14 09:00","2024-11-14 18:00","2024-11-14 09:00","2024-11-14 18:00","연속"]
[695,"부산울산","북부산","호포매리#2 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","호포S/S 154kV 호포-매리#2T/L GIS 정밀점검","2024-11-16 09:00","2024-11-17 18:00","2024-11-16 09:00","2024-11-17 18:00","연속"]
[696,"부산울산","북부산","호포물금 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","호포S/S 154kV 호포-물금T/L GIS 정밀점검","2024-11-11 09:00","2024-11-12 18:00","2024-11-11 09:00","2024-11-12 18:00","연속"]
[697,"부산울산","북부산","호포물금 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","호포S/S 6100B/T GIS 정밀점검 -시험가압선로 : 호포S/S 154kV #1BUS, 호포-물금T/L","2024-11-05 17:00","2024-11-05 18:00","취소","취소","연속"]
[698,"부산울산","북부산","호포매리#1 T/L","24년 하반기 북부산전력지사 154kV GIS 정밀점검공사","호포S/S 154kV 호포-매리#1T/L GIS 정밀점검","2024-11-30 09:00","2024-12-01 18:00","취소","취소","연속"]
[699,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 신녹산-녹산#1T/L GIS 동작시험","녹산S/S 신녹산-녹산#1T/L GIS 동작시험","2024-11-11 09:00","2024-11-11 18:00","2024-11-11 09:00","2024-11-11 18:00","연속"]
[700,"부산울산","서부산","신녹산녹산#2 T/L","녹산S/S 신녹산-녹산#2T/L GIS 동작시험","녹산S/S 신녹산-녹산#2T/L GIS 동작시험","2024-11-12 09:00","2024-11-12 18:00","2024-11-12 09:00","2024-11-12 18:00","연속"]
[701,"부산울산","서부산","서부산다대#1 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 345kV 차단기 용량부족 대체공사 관련 모자익반 수용","2024-11-04 09:00","2024-11-08 18:00","2024-11-04 09:00","2024-11-08 18:00","연속"]
[702,"부산울산","서부산","서부산엄궁#1 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 345kV 차단기 용량부족 대체공사 관련 모자익반 수용","2024-11-27 09:00","2024-11-28 18:00","2024-11-18 09:00","2024-11-22 18:00","연속"]
[703,"부산울산","서부산","서부산엄궁#2 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 345kV 차단기 용량부족 대체공사 관련 모자익반 수용","2024-11-25 09:00","2024-11-29 18:00","2024-11-25 09:00","2024-11-29 18:00","연속"]
[704,"부산울산","서부산","서부산다대#2 T/L","서부산S/S 345kV 차단기 용량부족 대체공사","서부산S/S 345kV 차단기 용량부족 대체공사 관련 모자익반 수용","2024-11-11 09:00","2024-11-15 18:00","2024-11-11 09:00","2024-11-15 18:00","연속"]
[705,"부산울산","서부산","신녹산S/S #2 BUS","신녹산S/S 345kV #1M.Tr 증설공사","154kV 65-66/60-61SEC, 6200BT, 61-66PT&ES 증설","2024-11-18 09:00","2024-11-29 18:00","2024-11-18 09:00","2024-11-29 18:00","연속"]
[706,"부산울산","울산","반천언양#2 T/L","2024년 가공송전 순시점검 위탁공사","154kV 직동-반천T/L 정밀점검 안전이격","2024-11-05 09:00","2024-11-05 18:00","2024-11-05 09:00","2024-11-05 18:00","연속"]
[707,"부산울산","울산","방어진영남TP#2 T/L","24년 울산전력지사 변전협력회사 총액공사","-SA 시스템화","2024-11-11 09:00","2024-11-12 18:00","2024-11-11 09:00","2024-11-12 18:00","연속"]
[708,"부산울산","울산","방어진영남TP#1 T/L","24년 울산전력지사 변전협력회사 총액공사","-SA 시스템화","2024-11-13 09:00","2024-11-14 18:00","2024-11-13 09:00","2024-11-14 18:00","연속"]
[709,"부산울산","울산","신온산온산#2 T/L","24년 울산전력지사 변전협력회사 총액공사","- 신온산-온산#2T/L 616DS 누기보수 작업","2024-11-01 09:00","2024-11-02 18:00","2024-11-01 09:00","2024-11-02 18:00","연속"]
[710,"부산울산","울산","신울산S/S CB 6972G","24년 울산전력지사 변전협력회사 총액공사","- GIS 하자점검 -효성제 조작부 발청보수","2024-11-15 09:00","2024-11-15 18:00","2024-11-15 09:00","2024-11-15 18:00","연속"]
[711,"부산울산","울산","신울산울산#2 T/L","2024-2025년 울산전력지사 가공송전협력회사 공사","[국산불량애자 교체공사] -작업개소: 154kV 신울산-울산#2T/L S/T, No.1,10 -시공업체: 한일전력(주) -감리업체: 대승전력기술(주)","2024-11-04 08:00","2024-11-05 18:00","2024-11-04 08:00","2024-11-05 18:00","연속"]
[712,"부산울산","울산","신울산언양#2 T/L","세니온제 보호반 성능개선","- 세니온제 보호반 성능개선(펌웨어 업데이트, 43PDA 동작이상 수정)","2024-11-15 09:00","2024-11-15 18:00","2024-11-15 09:00","2024-11-15 18:00","연속"]
[713,"부산울산","울산","신온산온산#2 T/L","온산S/S 154kV 장기사용 GIS 교체공사","□ 154kV 온산-처용#1T/L GIS 1CCT 교체 - #2BUS 무부하시험가압 선로(24Hr)","2024-11-22 16:00","2024-11-23 16:00","2024-11-22 16:00","2024-11-23 16:00","연속"]
[714,"부산울산","울산","신온산온산#2 T/L","온산S/S 154kV 장기사용 GIS 교체공사","□ 154kV 온산-처용#1T/L GIS 1CCT 교체 - #1BUS 무부하시험가압 선로(24Hr)","2024-11-15 16:00","2024-11-16 16:00","2024-11-15 16:00","2024-11-16 16:00","연속"]
[715,"부산울산","울산","신온산온산#2 T/L","온산S/S 154kV 장기사용 GIS 교체공사","□ 154kV 온산-처용#1T/L GIS 1CCT 교체 - #2DS 고깔 무부하시험가압 선로(1Hr)","2024-11-07 15:00","2024-11-07 16:00","2024-11-07 15:00","2024-11-07 16:00","연속"]
[716,"부산울산","울산","온산처용#1 T/L","온산S/S 154kV 장기사용 GIS 교체공사","154kV 온산-처용#1T/L GIS 1CCT 교체","2024-11-05 09:00","2024-11-30 18:00","2024-11-05 09:00","2024-11-30 18:00","연속"]
[717,"부산울산","울산","울산영남TP#2 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","1. 대 상 : 154kV 울산-영남TP#2T/L 2. 작업내용 : 접속함 절연유채유 3. 업체명 : 공영전력","2024-11-26 09:00","2024-11-26 18:00","2024-11-26 09:00","2024-11-26 18:00","연속"]
[718,"부산울산","울산","울산영남TP#1 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","1. 대 상 : 154kV 울산-영남TP#1T/L 2. 작업내용 : 접속함 절연유채유 3. 업체명 : 공영전력","2024-11-25 09:00","2024-11-25 18:00","2024-11-25 09:00","2024-11-25 18:00","연속"]
[719,"부산울산","울산","직동반천#1 T/L","2024년 가공송전 순시점검 위탁공사","154kV 직동-반천T/L 정밀점검","2024-11-04 09:00","2024-11-05 18:00","2024-11-04 09:00","2024-11-05 18:00","연속"]
[720,"부산울산","울산","직동반천#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-11-11 07:30","2024-11-11 18:00","2024-11-11 07:30","2024-11-11 18:00","연속"]
[721,"부산울산","울산","남울산처용#2 T/L","24년 울산전력지사 변전협력회사 총액공사","효성제 조작부 발청보수","2024-11-04 09:00","2024-11-04 14:00","2024-11-04 09:00","2024-11-04 14:00","연속"]
[722,"부산울산","울산","남울산처용#1 T/L","24년 울산전력지사 변전협력회사 총액공사","- GIS 보통점검 - 효성제 조작부 발청보수 - 피뢰기 대체","2024-11-01 09:00","2024-11-01 18:00","2024-11-01 09:00","2024-11-01 18:00","연속"]
[723,"부산울산","울산","동울산효문#1 T/L","154kV 효문S/S GIS 교체공사","154kV 동울산-효문#1T/L(657) GIS 대체 154kV 신)BUS-TIE(6100) GIS 설치 154kV SEC. DS 설치. 끝.","2024-11-11 09:00","2024-12-06 18:00","2024-11-11 09:00","2024-12-06 18:00","연속"]
[724,"경남","김해송변전부","호포매리#2 T/L","154kV 대동S/S 및 분기T/L 건설사업","- 154kV 호포-매리#2T/L 보호반 대체작업(11/29~11/30) - 154kV 대동분기T/L 지중전력케이블 작업(11/29~11/30) - 신규설비(송전선로 및 변전소) 사용전검사(12/3) - 무부하가압(12/1~12/2), 실부하가압(12/3)","2024-11-29 20:00","2024-12-03 18:00","2024-11-29 20:00","2024-12-03 18:00","연속"]
[725,"경남","김해송변전부","삼계어방#2 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-02 07:00","2024-11-03 18:00","2024-11-23 07:00","2024-11-23 18:00","매일"]
[726,"경남","김해송변전부","한림정삼계#2 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-24 07:00","2024-11-24 18:00","2024-11-24 07:00","2024-11-24 18:00","연속"]
[727,"경남","김해송변전부","삼계어방#1 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-16 07:00","2024-11-17 18:00","취소","취소","매일"]
[728,"경남","김해송변전부","삼계어방#1 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-24 07:00","2024-11-24 18:00","2024-11-24 07:00","2024-11-24 18:00","연속"]
[729,"경남","김해송변전부","주촌삼계#1 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-02 07:00","2024-11-03 18:00","2024-11-23 07:00","2024-11-23 18:00","매일"]
[730,"경남","김해송변전부","주촌삼계#2 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-24 07:00","2024-11-24 18:00","2024-11-24 07:00","2024-11-24 18:00","연속"]
[731,"경남","김해송변전부","한림정삼계#1 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-09 07:00","2024-11-09 18:00","취소","취소","연속"]
[732,"경남","김해송변전부","삼계어방#2 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-09 07:00","2024-11-09 18:00","취소","취소","연속"]
[733,"경남","김해송변전부","한림정삼계#2 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-16 07:00","2024-11-17 18:00","취소","취소","매일"]
[734,"경남","김해송변전부","주촌삼계#2 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-16 07:00","2024-11-16 18:00","취소","취소","연속"]
[735,"경남","김해송변전부","신김해지사#2 T/L","2024-2025년 경남본부 직할 가공송전협력회사 총액공사","성능저하 애자교체","2024-11-15 07:00","2024-11-15 18:00","2024-11-15 07:00","2024-11-15 18:00","연속"]
[736,"경남","김해송변전부","신김해지사#1 T/L","2024-2025년 경남본부 직할 가공송전협력회사 총액공사","성능저하 애자교체","2024-11-08 07:00","2024-11-08 18:00","취소","취소","연속"]
[737,"경남","김해송변전부","삼계어방#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","안전이격거리확보","2024-11-11 11:00","2024-11-11 18:00","취소","취소","연속"]
[738,"경남","김해송변전부","장유마천#1 T/L","장유S/S 6333 정밀점검","시험가압용 선로","2024-11-20 14:00","2024-11-20 15:00","2024-11-20 14:00","2024-11-20 15:00","연속"]
[739,"경남","김해송변전부","장유마천#2 T/L","2024-2025년 경남본부 직할 가공송전협력회사 총액공사","성능저하 애자교체","2024-11-15 07:00","2024-11-15 18:00","2024-11-15 07:00","2024-11-15 18:00","연속"]
[740,"경남","김해송변전부","장유마천#2 T/L","장유S/S 6433 정밀점검","시험가압용 선로","2024-11-22 14:00","2024-11-22 15:00","2024-11-22 14:00","2024-11-22 15:00","연속"]
[741,"경남","김해송변전부","장유마천#1 T/L","2024-2025년 경남본부 직할 가공송전협력회사 총액공사","성능저하 애자교체","2024-11-08 07:00","2024-11-08 18:00","2024-11-08 07:00","2024-11-08 18:00","연속"]
[742,"경남","김해송변전부","주촌삼계#1 T/L","주촌S/S 6333 정밀점검","시험가압용 선로","2024-11-15 14:00","2024-11-15 15:00","2024-11-15 14:00","2024-11-15 15:00","연속"]
[743,"경남","김해송변전부","주촌삼계#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","안전이격거리확보","2024-11-11 11:00","2024-11-11 18:00","취소","취소","연속"]
[744,"경남","김해송변전부","신김해진례#2 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-21 07:00","2024-11-21 18:00","2024-11-21 07:00","2024-11-21 18:00","연속"]
[745,"경남","김해송변전부","신김해진례#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치 설치공사","2024-11-26 11:00","2024-11-26 18:00","2024-11-26 11:00","2024-11-26 18:00","연속"]
[746,"경남","김해송변전부","신김해진례#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치 설치공사","2024-11-25 11:00","2024-11-25 18:00","2024-11-25 11:00","2024-11-25 18:00","연속"]
[747,"경남","김해송변전부","진례진영#1 T/L","154kV 진례-진영#1T/L 철탑추락방지장치 설치공사","154kV 진례-진영#1T/L 철탑추락방지장치 설치[7호(1기)]","2024-11-25 07:00","2024-11-25 18:00","2024-11-25 07:00","2024-11-25 18:00","연속"]
[748,"경남","김해송변전부","신김해진례#1 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-20 07:00","2024-11-20 18:00","2024-11-20 07:00","2024-11-20 18:00","연속"]
[749,"경남","김해송변전부","진영수산#1 T/L","OPGW 항공장애표시구 설치공사","동읍-진영#1T/L No.39~40 항공구 1개 설치(안전이격 휴전)","2024-11-05 10:00","2024-11-05 12:00","2024-11-11 14:00","2024-11-11 18:00","연속"]
[750,"경남","김해송변전부","진영수산#2 T/L","OPGW 항공장애표시구 설치공사","동읍-진영#2T/L No.39~40 항공구 1개 설치(안전이격 휴전)","2024-11-05 08:00","2024-11-05 10:00","2024-11-11 07:00","2024-11-11 14:00","연속"]
[751,"경남","김해송변전부","한림정삼계#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지공사","2024-11-10 07:00","2024-11-10 11:00","취소","취소","연속"]
[752,"경남","김해송변전부","진영한림정#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지공사","2024-11-09 07:00","2024-11-10 18:00","취소","취소","매일"]
[753,"경남","김해송변전부","한림정삼계#1 T/L","154kV 마천-진해등 16개T/L 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-11-02 07:00","2024-11-03 18:00","2024-11-23 07:00","2024-11-23 18:00","매일"]
[754,"경남","김해송변전부","한림정삼계#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","폴리머 점퍼지지애자 설치공사","2024-11-10 11:00","2024-11-12 18:00","취소","취소","매일"]
[755,"경남","직할","장유마천#1 T/L","24~25년 경남본부 직할 송전협력회사 공사","154kV 마천S/S 오손애자교체 등","2024-11-01 07:00","2024-11-01 18:00","취소","취소","연속"]
[756,"경남","직할","장유마천#2 T/L","24~25년 경남본부 직할 송전협력회사 공사","154kV 마천S/S 오손애자교체 등","2024-11-01 07:00","2024-11-06 18:00","취소","취소","연속"]
[757,"경남","진주","하동개양#1 T/L","154kV 정촌분기T/L 건설공사","ㅇ 154kV 하동-개양T/L 기설 No.18 철거 및 No.18(C/H) 신설, 전력선 공중이동","2024-11-07 06:00","2024-11-08 18:00","2024-11-07 06:00","2024-11-08 18:00","연속"]
[758,"경남","진주","사천개양#2 T/L","154kV 사천-개양T/L 점퍼지지애자 설치","154kV 사천-개양T/L 점퍼지지애자 설치","2024-11-07 07:00","2024-11-13 18:00","취소","취소","매일"]
[759,"경남","진주","사천개양#1 T/L","154kV 사천-개양#1T/L 점퍼지지애자 설치","154kV 사천-개양#1T/L 점퍼지지애자 설치","2024-11-04 07:00","2024-11-06 18:00","취소","취소","매일"]
[760,"경남","진주","하동개양#2 T/L","154kV 정촌분기T/L 건설공사","ㅇ 154kV 하동-개양T/L 기설 No.18 철거 및 No.18(C/H) 신설, 전력선 공중이동","2024-11-04 06:00","2024-11-06 18:00","2024-11-04 06:00","2024-11-06 18:00","연속"]
[761,"경남","진주","의령S/S #1 EM.Tr CB","의령S/S ESS 정기검사","의령S/S ESS 정기검사 [병행] EM.Tr 보통점검 [병행] NGR, LA, 1차 GIS, 2차 SIS 등 보통점검 [병행] 변압기 추락방지 안전장치 설치","2024-11-04 10:00","2024-11-08 18:00","2024-11-04 10:00","2024-11-08 18:00","연속"]
[762,"경남","진주","동진주진주#2 T/L","154kV 동진주-진주T/L 피뢰기 설치작업 등","154kV 동진주-진주T/L 피뢰기 설치작업 등 - 1~4호(4기)","2024-11-16 07:00","2024-11-16 18:00","취소","취소","매일"]
[763,"경남","진주","진주개양#1 T/L","154kV 진주-개양T/L 추락방지장치 설치","154kV 진주-개양T/L 11호 추락방지장치 설치","2024-11-10 07:00","2024-11-10 18:00","취소","취소","매일"]
[764,"경남","진주","진주개양#1 T/L","154kV 진주-개양T/L 추락방지장치 설치","154kV 진주-개양T/L 11호 추락방지장치 설치","2024-11-10 07:00","2024-11-10 18:00","취소","취소","매일"]
[765,"경남","진주","동진주진주#1 T/L","154kV 동진주-진주T/L 피뢰기 설치작업 등","154kV 동진주-진주T/L 피뢰기 설치작업 등 - 1~4호(4기)","2024-11-09 07:00","2024-11-09 18:00","취소","취소","매일"]
[766,"경남","진주","동진주진주#2 T/L","154kV 동진주-진주T/L 피뢰기 설치작업 등","154kV 동진주-진주T/L 피뢰기 설치작업 등 - 1~4호(4기)","2024-11-09 07:00","2024-11-09 18:00","취소","취소","매일"]
[767,"경남","진주","진주개양#2 T/L","154kV 진주-개양T/L 추락방지장치 설치","154kV 진주-개양T/L 11호 추락방지장치 설치","2024-11-17 07:00","2024-11-17 18:00","취소","취소","매일"]
[768,"경남","진주","진주개양#1 T/L","154kV 진주-개양T/L 추락방지장치 설치","154kV 진주-개양T/L 11호 추락방지장치 설치","2024-11-17 07:00","2024-11-17 18:00","취소","취소","매일"]
[769,"경남","진주","동진주진주#1 T/L","154kV 동진주-진주T/L 피뢰기 설치작업 등","154kV 동진주-진주T/L 피뢰기 설치작업 등 - 1~4호(4기)","2024-11-16 07:00","2024-11-16 18:00","취소","취소","매일"]
[770,"경남","진주","하동개양#2 T/L","154kV 정촌S/S 및 분기T/L 건설사업","- 154kV 하동-개양#2T/L 보호반 대체작업(11/25~11/26) - 154kV 정촌분기 지중T/L 지중전력케이블 작업(11/25~11/26) - 154kV 정촌분기T/L 송전선 연결 및 일부구간 철거 작업(11/25~11/29) - 154kV 정촌S/S 통신설비공사(11/25~11/29) - 무부하가압(11/30~12/01) - 신규설비(송전선로 및 변전소) 사용전검사(12/02~12/04) - 실부하가압(12/04)","2024-11-25 09:00","2024-12-04 18:00","2024-11-25 09:00","2024-12-04 18:00","연속"]
[771,"경남","진주","하동하동화력 T/L","154kV 하동-남해T/L 점퍼지지애자 설치공사 관련 안전거리확보","154kV 하동-남해T/L 점퍼지지애자 설치공사 관련 안전거리확보","2024-11-18 07:00","2024-11-19 18:00","2024-11-18 07:00","2024-11-19 18:00","매일"]
[772,"경남","통영","거류거제#1 T/L","154kV 거류-거제#1T/L 추락방지장치 설치공사","154kV 거류-거제#1T/L 추락방지장치 설치공사","2024-11-17 07:30","2024-11-17 18:00","2024-11-17 07:30","2024-11-17 18:00","연속"]
[773,"경남","통영","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-11-16 07:30","2024-11-16 18:00","2024-11-16 07:30","2024-11-16 18:00","연속"]
[774,"경남","통영","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-11-09 07:30","2024-11-10 18:00","2024-11-09 07:30","2024-11-10 18:00","매일"]
[775,"경남","통영","거류거제#2 T/L","154kV 거류-거제#2T/L 추락방지장치 설치공사","154kV 거류-거제#2T/L 추락방지장치 설치공사","2024-11-02 07:30","2024-11-03 18:00","2024-11-02 07:30","2024-11-03 18:00","매일"]
[776,"경남","통영","거류거제#1 T/L","154kV 거류-거제#1T/L 추락방지장치 설치공사","154kV 거류-거제#1T/L 추락방지장치 설치공사","2024-11-23 07:30","2024-11-24 18:00","2024-11-23 07:30","2024-11-24 18:00","매일"]
[777,"경남","통영","거류거제#1 T/L","154kV 거류-거제#1T/L 추락방지장치 설치공사","154kV 거류-거제#1T/L 추락방지장치 설치공사","2024-11-30 07:30","2024-11-30 18:00","2024-11-30 07:30","2024-11-30 18:00","연속"]
[778,"경남","통영","사천개양#1 T/L","154kV 사천-개양 #1,2 T/L 추락방지장치 설치공사","154kV 사천-개양#1,2 T/L 추락방지장치 설치공사 No.74~ 86 수평배열로 인한 #1, 2T/L 동시휴전 필요","2024-11-13 07:00","2024-11-13 18:00","취소","취소","연속"]
[779,"경남","통영","삼천포사천#2 T/L","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사 No.60~ 72 수평배열로 인한 #1, 2T/L 동시휴전 필요","2024-11-12 07:00","2024-11-12 18:00","취소","취소","연속"]
[780,"경남","통영","삼천포사천#1 T/L","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사","154kV 삼천포사천#1,2 T/L 추락방지장치 설치공사 No.60~ 72 수평배열로 인한 #1, 2T/L 동시휴전 필요","2024-11-12 07:00","2024-11-12 18:00","취소","취소","연속"]
[781,"경남","통영","사천개양#2 T/L","154kV 사천-개양 #1,2 T/L 추락방지장치 설치공사","154kV 사천-개양#1,2 T/L 추락방지장치 설치공사 No.74~ 86 수평배열로 인한 #1, 2T/L 동시휴전 필요","2024-11-13 07:00","2024-11-13 18:00","취소","취소","연속"]
[782,"경남","통영","삼천포사천#2 T/L","154kV 삼천포-사천#2T/L 추락방지장치 설치공사","154kV 삼천포-사천#2T/L 추락방지장치 설치공사","2024-11-21 07:30","2024-11-22 18:00","취소","취소","매일"]
[783,"경남","통영","삼천포사천#1 T/L","154kV 삼천포-사천#1T/L 추락방지장치 설치공사","154kV 삼천포-사천#1T/L 추락방지장치 설치공사","2024-11-18 07:30","2024-11-19 18:00","취소","취소","매일"]
[784,"경남","통영","신고성삼천포#2 T/L","154kV 신고성-삼천포#2T/L 추락방지장치 설치공사","154kV 신고성-삼천포#2T/L 추락방지장치 설치공사","2024-11-20 07:30","2024-11-22 18:00","취소","취소","매일"]
[785,"경남","통영","신고성삼천포#1 T/L","154kV 신고성-삼천포#1T/L 추락방지장치 설치공사","154kV 신고성-삼천포#1T/L 추락방지장치 설치공사","2024-11-18 07:30","2024-11-19 18:00","취소","취소","매일"]
[786,"경남","통영","신고성거류#2 T/L","154kV 신고성-거류#2T/L 추락방지장치 설치공사","154kV 신고성-거류#2T/L 추락방지장치 설치공사","2024-11-11 07:30","2024-11-11 18:00","2024-11-11 07:30","2024-11-11 18:00","연속"]
[787,"경남","통영","신고성삼천포#1 T/L","154kV 신고성-삼천포#1T/L 추락방지장치 설치공사","154kV 신고성-삼천포#1T/L 추락방지장치 설치공사","2024-11-15 07:30","2024-11-15 18:00","취소","취소","연속"]
[788,"경남","통영","진동안정#2 T/L","154kV 진동-안정#2T/L 추락방지장치 설치공사","154kV 진동-안정#2T/L 추락방지장치 설치공사","2024-11-11 07:30","2024-11-11 18:00","2024-11-11 07:30","2024-11-11 18:00","연속"]
[789,"경남","통영","고성통영CC#1 T/L","154kV 고성-통영복합#1T/L GIS 초기점검 등","고성S/S, 통영복합S/S 154kV 고성-통영복합#1T/L GIS 초기점검 등","2024-11-13 09:30","2024-11-13 18:00","2024-11-13 09:30","2024-11-13 18:00","연속"]
[790,"경남","통영","안정통영CC#2 T/L","154kV 안정-통영복합#2T/L GIS 초기점검 등","안정S/S, 통영복합S/S 154kV 고성-통영복합#2T/L GIS 초기점검 등","2024-11-12 09:30","2024-11-12 18:00","2024-11-12 09:30","2024-11-12 18:00","연속"]
[791,"경남","함안","가야사봉#1 T/L","154kV 가야-사봉#1,2T/L 철탑추락방지장치 설치공사","추락재해 예방을 위한 수평형 철탑추락방지장치 설치공사 (대상개소 : 154kV 가야-사봉#1,2T/L 1~13호)","2024-11-23 07:00","2024-11-24 18:00","취소","취소","매일"]
[792,"경남","함안","가야사봉#2 T/L","154kV 가야-사봉#1,2T/L 철탑추락방지장치 설치공사","추락재해 예방을 위한 수평형 철탑추락방지장치 설치공사 (대상개소 : 154kV 가야-사봉#1,2T/L 1~13호)","2024-11-23 07:00","2024-11-24 18:00","취소","취소","매일"]
[793,"경남","함안","가야사봉#1 T/L","가야S/S 154kV 가야사봉#1 T/L 보호반대체","가야S/S 154kV 가야사봉#1 T/L 보호반대체","2024-11-23 09:30","2024-11-24 17:30","2024-11-23 09:30","2024-11-24 17:30","연속"]
[794,"경남","함안","중리가야#2 T/L","가야S/S 154kV 중리가야#2 T/L GIS 조작시험 외","가야S/S 154kV 중리가야#2 T/L GIS 조작시험 및 LA 초기점검","2024-11-02 09:30","2024-11-02 17:30","2024-11-02 09:30","2024-11-02 17:30","연속"]
[795,"경남","함안","가야사봉#2 T/L","가야S/S 154kV 가야사봉#2 T/L GIS 조작시험 외","가야S/S 154kV 가야사봉#2 T/L GIS 조작시험 및 LA 보통점검, PT 초기점검","2024-11-03 09:30","2024-11-03 17:30","2024-11-03 09:30","2024-11-03 17:30","연속"]
[796,"경남","함안","동읍진영#1 T/L","OPGW 항공장애표시구 설치공사","동읍-진영#1T/L No.39~40 항공구 1개 설치","2024-11-05 10:00","2024-11-05 12:00","2024-11-11 14:00","2024-11-11 18:00","연속"]
[797,"경남","함안","진영수산#2 T/L","154kV 진영-수산#2T/L 철탑추락방지장치 설치공사","154kV 진영-수산#2T/L 철탑추락방지장치 설치[1,61호(2기)]","2024-11-08 07:00","2024-11-09 18:00","2024-11-15 07:00","2024-11-15 18:00","매일"]
[798,"경남","함안","진영수산#1 T/L","154kV 진영-수산#1T/L 철탑추락방지장치 설치공사","154kV 진영-수산#1T/L 철탑추락방지장치 설치[2~27,61호(27기)] ※주말 제외","2024-11-19 07:00","2024-11-25 18:00","2024-11-19 07:00","2024-11-25 18:00","매일"]
[799,"경남","함안","초동수산#1 T/L","154kV 수산-초동#1T/L 철탑추락방지장치 설치공사","154kV 수산-초동#1T/L 철탑추락방지장치 설치[1~13호(13기)]","2024-11-22 07:00","2024-11-22 18:00","2024-11-22 07:00","2024-11-22 18:00","연속"]
[800,"경남","함안","초동수산#2 T/L","154kV 수산-초동#2T/L 철탑추락방지장치 설치공사","154kV 수산-초동#2T/L 철탑추락방지장치 설치[1~13호(13기)]","2024-11-08 07:00","2024-11-08 18:00","취소","취소","연속"]
[801,"경남","함안","신마산S/S CB 6100","신마산S/S 154kV #60-#65 BUS TIE CB 조작시험","신마산S/S 154kV #60-#65 BUS TIE CB 조작시험","2024-11-01 09:30","2024-11-01 13:30","취소","취소","연속"]
[802,"경남","함안","신마산S/S CB 6200","신마산S/S 154kV #61-#66 BUS TIE CB 조작시험","신마산S/S 154kV #61-#66 BUS TIE CB 조작시험","2024-11-01 13:30","2024-11-01 17:30","취소","취소","연속"]
[803,"경남","함안","신마산의창#1 T/L","신마산S/S 154kV, 23kV 옥외철구설비 GIS화 공사","- 154kV 임시GIS, #61M.Tr, 23kV EGIS 시험가압(24H)","2024-11-28 13:00","2024-11-29 18:00","2024-11-28 13:00","2024-11-29 18:00","연속"]
[804,"경남","함안","신마산의창#1 T/L","신마산S/S 154kV, 23kV 옥외철구설비 GIS화 공사","- 154kV 임시GIS, #61M.Tr, 23kV EGIS 시험가압(24H)","2024-11-26 13:00","2024-11-27 18:00","2024-11-26 13:00","2024-11-27 18:00","연속"]
[805,"경남","함안","신마산칠서#1 T/L","OPGW 항공장애표시구 설치 공사","신마산-칠서 No.3~4 항공구 2개 설치","2024-11-05 14:00","2024-11-05 18:00","취소","취소","연속"]
[806,"경남","함안","신마산S/S SEC CB 65660","신마산S/S 154kV #65-#66 SEC CB 조작시험","신마산S/S 154kV #65-#66 SEC CB 조작시험","2024-11-05 13:30","2024-11-05 17:30","취소","취소","연속"]
[807,"경남","함안","신마산S/S SEC CB 60610","신마산S/S 154kV #60-#61 SEC CB 조작시험","신마산S/S 154kV #60-#61 SEC CB 조작시험","2024-11-05 09:30","2024-11-05 13:30","취소","취소","연속"]
[808,"경남","함안","창녕초동#1 T/L","154kV 창녕-구지#2T/L 폴리머 지지애자 설치(안전이격거리확보)","154kV 창녕-구지#2T/L 2~5호(3기) 고정형 폴리머 지지애자 설치 관련 안전이격거리확보","2024-11-27 07:00","2024-11-27 18:00","2024-11-27 07:00","2024-11-27 18:00","연속"]
[809,"경남","함안","창녕구지#2 T/L","154kV 창녕-구지#2T/L 철탑추락방지장치 설치공사","154kV 창녕-구지#2T/L 수평형 철탑추락방지장치[8~81호(76기) 및 고정형 폴리머 점퍼지지애자[2~81(19기)] 설치 ※ T분기선로로 휴전기간 일요일마다 점퍼선 분리 및 복귀작업 시행 예정이며, 휴전기간 중이라도 고객사(화인베스틸)에 전력을 공급해야함(편측 변전소 CB 투입)","2024-11-17 07:00","2024-12-01 18:00","2024-11-17 07:00","2024-12-01 18:00","연속"]