{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":10,"n_cols":11,"rows_kept":10,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 12월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"대전세종충남","서산","당진T/P Tie-Tr","'24년 서산P/O 변전협력회사 총액공사","(즉시가압 불가) 당진화력S/S 765kV #1Tre-Tr 보통점검","2024-12-16 09:00","2024-12-22 18:00","취소","취소","연속"]
[2,"대전세종충남","서산","신서산S/S #3 M.Tr","'24년 서산P/O 변전협력회사 총액공사","(즉시가압 불가) 신서산S/S 765kV #3M.Tr 보통점검","2024-12-02 09:00","2024-12-13 18:00","취소","취소","연속"]
[3,"대전세종충남","서산","신서산S/S #4 M.Tr","'24년 서산P/O 변전협력회사 총액공사","(즉시가압 불가) 신서산S/S 765kV #4M.Tr 보통점검","2024-12-23 09:00","2025-01-03 18:00","취소","취소","연속"]
[4,"부산울산","동부산","신고리N/P #2 BUS","신고리 5,6호기 접속설비공사","- 87BAY #2BUS 연결작업 - 모선보호반 대체(동부산전력지사)","2024-12-31 09:00","2025-01-22 18:00","2024-12-31 09:00","2025-01-22 18:00","연속"]
[5,"부산울산","동부산","신고리N/P #1 BUS","신고리 5,6호기 접속설비공사","- 87BAY #1BUS 연결작업 - 모선보호반 대체(동부산전력지사)","2024-12-16 09:00","2024-12-31 18:00","2024-12-16 09:00","2024-12-31 18:00","연속"]
[6,"부산울산","동부산","북경남신고리NP#2 T/L","신고리S/S #1BUS 가수 누기 조치관련 안전이격 확보","신고리S/S #1BUS 가수 누기 조치관련 안전이격 확보","2024-12-16 09:00","2024-12-17 18:00","2024-12-16 09:00","2024-12-17 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":156,"n_cols":11,"rows_kept":156,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2024년도 12월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","동서울","동서울S/S CB 7472","'24~'25년도 동서울전력지사 변전협력회사 총액공사","동서울S/S 7472 GIS조작시험","2024-12-02 09:00","2024-12-02 18:00","2024-12-02 09:00","2024-12-02 18:00","연속"]
[2,"남서울","동서울","동서울S/S #3 Sh.R CB","345kV 동서울S/S 종합정비공사","500kV 동서울 변환소 부지확보 관련 사전정비 시행 - 345kV GIS 및 Sh.R 제어케이블 이설","2024-12-02 09:00","2024-12-31 18:00","2024-12-02 09:00","2024-12-13 18:00","연속"]
[3,"인천","김포","가정개폐소 #2 Sh.R CB","가정개폐소 345kV #2 Sh.R 추락방지장치 설치차","가정개폐소 345kV #2 Sh.R 추락방지장치 설치차","2024-12-10 09:00","2024-12-10 18:00","2024-12-10 09:00","2024-12-10 18:00","연속"]
[4,"인천","김포","가정개폐소 #1 Sh.R CB","가정개폐소 345kV #1 Sh.R 추락방지장치 설치차","가정개폐소 345kV #1 Sh.R 추락방지장치 설치차","2024-12-09 09:00","2024-12-09 18:00","2024-12-09 09:00","2024-12-09 18:00","연속"]
[5,"인천","김포","가정개폐소 #3 Sh.R CB","가정개폐소 345kV #3 Sh.R 추락방지장치 설치차","가정개폐소 345kV #3 Sh.R 추락방지장치 설치차","2024-12-11 09:00","2024-12-11 18:00","2024-12-11 09:00","2024-12-11 18:00","연속"]
[6,"인천","시흥","신시화S/S CB 7600","신시화S/S 345kV #4M.Tr, #2Sh.R GIS 증설공사","- 345kV 7572, 7672 차단기 증설 - #4M.Tr 1, 2차 GIB 접속 - #2Sh.R 1차 GIB 접속","2024-12-09 09:00","2024-12-20 18:00","2024-12-09 09:00","2024-12-20 18:00","연속"]
[7,"인천","시흥","신시화S/S CB 7500","신시화S/S 345kV #4M.Tr, #2Sh.R GIS 증설공사","- 345kV 7572, 7672 차단기 증설 - #4M.Tr 1, 2차 GIB 접속 - #2Sh.R 1차 GIB 접속","2024-12-09 09:00","2024-12-20 18:00","2024-12-09 09:00","2024-12-20 18:00","연속"]
[8,"인천","시흥","신시화S/S CB 7672","신시화S/S 345kV #4M.Tr, #2Sh.R GIS 증설공사","- 345kV 7572, 7672 차단기 증설 - #4M.Tr 1, 2차 GIB 접속 - #2Sh.R 1차 GIB 접속","2024-12-09 09:00","2024-12-20 18:00","2024-12-09 09:00","2024-12-20 18:00","연속"]
[9,"인천","시흥","신시화S/S CB 7572","신시화S/S 345kV #4M.Tr, #2Sh.R GIS 증설공사","- 345kV 7572, 7672 차단기 증설 - #4M.Tr 1, 2차 GIB 접속 - #2Sh.R 1차 GIB 접속","2024-12-09 09:00","2024-12-20 18:00","2024-12-09 09:00","2024-12-20 18:00","연속"]
[10,"인천","시흥","신시화S/S CB 7600","신시화S/S #4M.Tr, #2Sh.R 증설공사","신시화S/S #2Sh.R 사용전검사 관련 시험","2024-12-26 09:00","2024-12-27 18:00","2024-12-26 09:00","2024-12-27 18:00","연속"]
[11,"인천","시흥","신시화S/S CB 7500","신시화S/S #4M.Tr, #2Sh.R 증설공사","신시화S/S #4M.Tr 사용전검사 관련 시험","2024-12-30 09:00","2024-12-31 18:00","2024-12-30 09:00","2024-12-31 18:00","연속"]
[12,"경기북부","고양","신파주S/S SVC CB","신파주 SVC 불량사항 보수 및 안전장치 설치","1. 작업기간 : 2024. 12. 10 ~ 2024. 12. 12 2. 작업내용 - #1사이리스터 밸브실 C상 사이리스터 1EA 불량으로 교체 - C.Tr 변압기 3EA 추락방지장치 설치","2024-12-10 09:00","2024-12-12 18:00","2024-12-10 09:00","2024-12-12 18:00","연속"]
[13,"경기북부","구리","미금S/S STATCOM CB","미금S/S STATCOM 제어동 냉난방기 설치","- 냉난방기 전원선 철거 및 신규설치 - 냉난방기 철거 및 신규설치","2024-12-02 09:00","2024-12-06 18:00","2024-12-02 09:00","2024-12-10 18:00","연속"]
[14,"경기북부","구리","미금S/S #5 Sh.R CB","24-25 구리전력 변전협력 총액공사","345kV Sh.R 보통점검","2024-12-02 09:00","2024-12-02 18:00","2024-12-02 09:00","2024-12-02 18:00","연속"]
[15,"경기북부","구리","신가평포천LNGCC#1 T/L","신가평S/S 345kV GIS 모선 용량대체 공사(전문)","345kV #75BUS 무부하가압 선로","2024-12-04 09:00","2024-12-06 18:00","2024-12-04 09:00","2024-12-06 18:00","연속"]
[16,"경기","군포","신온양서서울#1 T/L","서서울SS 신온양-서서울#2T/L GIS 송전선로 결상회로 개선","서서울SS 신온양-서서울#2T/L GIS 송전선로 결상회로 개선, 7700 조작시험, CVT, LA 보통점검","2024-12-01 09:00","2024-12-01 18:00","2024-12-01 09:00","2024-12-01 18:00","연속"]
[17,"경기","성남","신성남S/S #2 M.Tr","신성남S/S 154kV Sh.R 설치공사","#3,4Sh.R 방호벽 설치 안전이격 확보","2024-12-10 09:00","2024-12-11 16:00","2024-12-10 09:00","2024-12-11 16:00","연속"]
[18,"경기","성남","신성남S/S #1 M.Tr","신성남S/S 154kV Sh.R 설치공사","#1,2Sh.R 방호벽설치 안전이격확보","2024-12-11 16:00","2024-12-24 18:00","2024-12-11 16:00","2024-12-24 18:00","연속"]
[19,"경기","성남","신수원삼성#1 T/L","2024년 성남전력 변전협력회사 총액공사","보호반 대체","2024-12-02 09:00","2024-12-06 18:00","취소","취소","연속"]
[20,"경기","성남","신안성S/S CB 7C00","2024년 성남전력 변전협력회사 총액공사","7C00 GIS 절연열화 측정","2024-12-05 15:00","2024-12-05 17:00","취소","취소","연속"]
[21,"경기","성남","신안성S/S CB 7C72","2024년 성남전력 변전협력회사 총액공사","7C72 GIS 절연열화 측정","2024-12-05 13:00","2024-12-05 15:00","2024-12-05 13:00","2024-12-05 15:00","연속"]
[22,"경기","성남","신안성S/S CB 7B72","2024년 성남전력 변전협력회사 총액공사","7B72 GIS 절연열화 측정","2024-12-05 11:00","2024-12-05 13:00","2024-12-05 11:00","2024-12-05 13:00","연속"]
[23,"경기","성남","신안성S/S CB 7972","2024년 성남전력 변전협력회사 총액공사","7972 GIS 절연열화 측정","2024-12-05 09:00","2024-12-05 11:00","취소","취소","연속"]
[24,"경기","성남","신용인S/S #4 M.Tr","2024년 성남전력 변전협력회사 총액공사","M.Tr 보통점검, 2차 GIS 보통점검, 1,2,3차 LA 보통점검, 추락방지시설 설치, 방호벽 사다리 철거, 투광등 교체 (병행) 7800, 7872 GIS 보통점검, 절연열화 측정","2024-12-03 09:00","2024-12-04 18:00","취소","취소","연속"]
[25,"경기","직할","화성S/S #4 M.Tr","2024-25년 경기본부 직할 변전협력회사 공사","화성: #4M.Tr 보통점검(~28) - 1차 CVT 하자 1,2차 LA 대체 - 1, 2차 부싱절연유 채유 - 3차 LA A,B,C 하자, 3차 PT A,B,C, 보통 - 3차 MAIN VCB 대체 - #2S.Tr 대체 - #4-1,2Sh.R 보통, VCB 초기","2024-12-02 09:00","2024-12-04 18:00","취소","취소","연속"]
[26,"경기","직할","화성S/S #1 M.Tr","2024-25년 경기본부 직할 변전협력회사 공사","화성: #1M.Tr 보호반 대체(~20) - 1차 GIS 초기, 1차 CVT 하자 - 3차 MAIN VCB 대체 - #1S.Tr 대체 - #1,2Sh.R VCB 조작 - 3차 LA A,B,C 하자 - 1차 B,C 2차 A,B,C 부싱절연유","2024-12-09 09:00","2024-12-13 18:00","취소","취소","연속"]
[27,"경기","직할","화성평택TP#2 T/L","154kV 화성-장덕T/L OPGW 증설공사","154kV 화성-장덕 OPGW 증설공사 - OPGW 증설교체(OP-S-L24 → L48) 7.797km(해당구간 2km) - 광코어 접속, 최종시험 및 기타 부대공사 1식","2024-12-13 07:00","2024-12-15 18:00","취소","취소","연속"]
[28,"강원","강릉","신양양S/S #3 M.Tr","신양양S/S 345kV GIS 설치공사","345kV GIS 현장 반입 및 설치","2024-12-03 08:00","2024-12-05 18:00","2024-12-03 08:00","2024-12-05 18:00","매일"]
[29,"강원","태백","신태백한울NP#1 T/L","2024~2025년 태백전력지사 송전 협력회사 공사","345kV 신태백-한울NP2T/L 수평추락방지장치 설치","2024-12-02 08:00","2024-12-06 18:00","2024-12-02 08:00","2024-12-06 18:00","매일"]
[30,"충북","직할","신중부남청주#2 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-12-23 09:00","2024-12-27 18:00","2024-12-23 09:00","2024-12-27 18:00","연속"]
[31,"충북","직할","신중부남청주#2 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-12-09 07:00","2024-12-13 18:00","2024-12-09 07:00","2024-12-13 18:00","연속"]
[32,"충북","직할","신중부남청주#1 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-12-16 09:00","2024-12-20 18:00","2024-12-16 09:00","2024-12-20 18:00","연속"]
[33,"충북","직할","신중부남청주#1 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 시공내용 : 전력선 교체(용량증대 전선용 금구류 교체 포함) 27경간, 10km","2024-12-02 09:00","2024-12-06 18:00","2024-12-02 09:00","2024-12-06 18:00","연속"]
[34,"충북","청주","신옥천세종#1 T/L","345kV 신옥천북경남 등 8개T/L 추락방지장치 설치공사","1. 공사개요 : 신옥천세종#1T/L 추락방지장치 수평설치 2. 공사장소 : 신옥천세종#1T/L No.1~48 (55기) [토,일 제외]","2024-12-04 09:00","2024-12-10 18:00","취소","취소","매일"]
[35,"충북","충주","신제천신영주#1 T/L","345kV 신제천-신영주T/L No.55 취약철탑 교체공사","철탑교체 (신설1기, 철거2기)","2024-12-06 07:00","2024-12-14 16:00","2024-12-06 07:00","2024-12-14 16:00","연속"]
[36,"대전세종충남","대전","신계룡S/S #2 M.Tr","[즉시가압O]신계룡S/S 345kV #2 M.Tr 2차 GIS 보통점검","[즉시가압O]신계룡S/S 345kV #2 M.Tr 2차 GIS 보통점검","2024-12-10 09:00","2024-12-11 18:00","2024-12-10 09:00","2024-12-11 18:00","연속"]
[37,"대전세종충남","서산","당진T/P #72 Tie-Tr","'24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 당진화력S/S 345kV #72Tie-Tr 3차 GIS 온도감시형 LPS 설치","2024-12-06 09:30","2024-12-06 18:00","2024-12-06 09:30","2024-12-06 18:00","연속"]
[38,"대전세종충남","서산","북당진S/S CB 7671","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압가능) 북당진S/S 345kV 7671GIS 보통점검","2024-12-09 09:30","2024-12-10 18:00","2024-12-09 09:30","2024-12-10 18:00","연속"]
[39,"대전세종충남","서산","신당진개폐소북당진 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","(11월 휴전 취소시)수평 추락방지장치 설치공사 (No.49~65) , 즉시가압(20분 이내) 가능","2024-12-12 08:00","2024-12-13 18:00","취소","취소","매일"]
[40,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","345kV 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) *345kV 신당진개폐소-현대제철T/L 병가선로, 345kV 신당진개폐소-현대제철T/L 휴전 미승인시 휴전 취소 요청 *11월 휴전 승인시 취소 요청","2024-12-21 08:00","2024-12-22 18:00","취소","취소","매일"]
[41,"대전세종충남","서산","신당진개폐소현대제철 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","(11월 휴전 취소시)수평 추락방지장치 설치공사 (No.1~44) , 즉시가압(20분 이내) 가능","2024-12-16 08:00","2024-12-22 18:00","취소","취소","매일"]
[42,"대전세종충남","서산","신당진S/S CB 7172","'24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진S/S 345kV 신서산-신당진#1T/L 7172 CB 균압콘덴서 절연열화 진단","2024-12-02 09:30","2024-12-02 12:30","2024-12-02 09:30","2024-12-02 12:30","연속"]
[43,"대전세종충남","서산","신당진S/S #1 M.Tr","'24년 서산전력지사 변전협력회사 총액공사","(11월 휴전불가 시) (즉시가압 불가) 신당진S/S 345kV #1M.Tr 부싱절연유채유, 절연열화진단","2024-12-13 10:00","2024-12-13 18:00","취소","취소","연속"]
[44,"대전세종충남","서산","신서산S/S #5 Sh.R CB","'24년 서산P/O 345kV GIS 정밀점검공사","(11월 휴전 취소시) (즉시가압불가) 신서산S/S 345kV 7979GIS 정밀점검","2024-12-09 09:30","2024-12-13 18:00","2024-12-09 09:30","2024-12-13 18:00","연속"]
[45,"대전세종충남","서산","신서산아산#1 T/L","345kV 신서산-아산#1T/L 항공장애표시구 설치공사","(11월 휴전신청 취소시)[즉시가압가능] 1. 공사대상 : 345kV 신서산-아산#1T/L No. 2~3 항공장애표시구 5개 설치 2. 기타사항 : 미설치 시 항공시설법 위반으로 과태료 부과 대상","2024-12-14 08:00","2024-12-15 18:00","2024-12-14 08:00","2024-12-15 18:00","매일"]
[46,"대전세종충남","서산","신서산S/S CB 7500","'24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 신서산S/S 345kV #3Sh.R 보통점검 - (병행) : 7571GIS 보통점검 - Sh.R 점검시 7579 CB 보호기능이 없으므로, 경보시험 중 7571, 7500 트립되므로 7571, 7500 휴전 필요","2024-12-16 09:30","2024-12-17 18:00","2024-12-16 09:30","2024-12-17 18:00","연속"]
[47,"대전세종충남","서산","신서산S/S CB 7571","'24년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 신서산S/S 345kV #3Sh.R 보통점검 - (병행) : 7571GIS 보통점검 - Sh.R 점검시 7579 CB 보호기능이 없으므로, 경보시험 중 7571, 7500 트립되므로 7571, 7500 휴전 필요","2024-12-16 09:30","2024-12-17 18:00","2024-12-16 09:30","2024-12-17 18:00","연속"]
[48,"대전세종충남","서산","신서산S/S CB 7972","'24년 서산P/O 345kV GIS 정밀점검공사","(11월 휴전 취소시) (즉시가압불가) 신서산S/S 345kV 7972GIS 정밀점검","2024-12-02 09:30","2024-12-06 18:00","취소","취소","연속"]
[49,"대전세종충남","서산","태안T/P #1 Tie-Tr","'24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 345kV #1M.Tr 2차 LA 장기사용 교체","2024-12-09 09:30","2024-12-09 18:00","취소","취소","연속"]
[50,"대전세종충남","서산","태안T/P CB 7A00","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압가능) 태안화력S/S 345kV 7A00GIS 보통점검","2024-12-04 09:30","2024-12-05 18:00","취소","취소","연속"]
[51,"대전세종충남","서산","태안T/P CB 7A71","'24년 서산P/O 345kV GIS 보통점검공사","(즉시가압가능) 태안화력S/S 345kV 7A71GIS 보통점검","2024-12-02 09:30","2024-12-03 18:00","취소","취소","연속"]
[52,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S 345kV 77Bay B/F PNL 대체","(즉시가압불가)(11월취소시)신온양S/S 345kV 77Bay B/F PNL 대체","2024-12-23 09:00","2024-12-27 18:00","취소","취소","연속"]
[53,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S 345kV 77Bay B/F PNL 대체","(즉시가압불가)(11월취소시)신온양S/S 345kV 77Bay B/F PNL 대체","2024-12-23 09:00","2024-12-27 18:00","취소","취소","연속"]
[54,"대전세종충남","천안","아산화성#2 T/L","[11월취소시][즉시가압O][주말작업X] 추락방지장치 설치공사","[11월취소시][즉시가압O][주말작업X]345kV 아산-화성#1T/L No.25,26호","2024-12-05 07:00","2024-12-06 18:00","취소","취소","매일"]
[55,"대전세종충남","천안","아산S/S #2 M.Tr","아산S/S 345kV #2M.Tr 부싱절연유 채유","(즉시가압가능)아산S/S 345kV #2M.Tr 부싱절연유 채유","2024-12-12 09:00","2024-12-12 18:00","취소","취소","연속"]
[56,"대전세종충남","천안","아산S/S #1 M.Tr","아산S/S 345kV #1M.Tr 부싱절연유 채유","(즉시가압가능)아산S/S 345kV #1M.Tr 부싱절연유 채유","2024-12-05 09:00","2024-12-05 18:00","취소","취소","연속"]
[57,"대전세종충남","천안","아산보령TP#2 T/L","[즉시가압O][전일작업불가시 10:00~16:00제외]항공구 설치공사","[11월취소시][즉시가압가능][전일작업불가시 10:00~16:00제외] 345kV 아산-보령화력T/L No.123~124 등 12경간 항공구 설치 [병행] 항공장애표시구 정비 No.187~188","2024-12-23 06:00","2024-12-27 19:00","취소","취소","매일"]
[58,"대전세종충남","천안","아산보령TP#1 T/L","[즉시가압O][전일작업불가시 10:00~16:00제외]항공구 설치공사","[11월취소시][즉시가압가능][전일작업불가시 10:00~16:00제외] 345kV 아산-보령화력T/L No.123~124 등 12경간 항공구 설치 [병행] 항공장애표시구 정비 No.187~188 [병행] 조류착지방지장치 설치","2024-12-09 06:00","2024-12-13 19:00","취소","취소","매일"]
[59,"대전세종충남","천안","아산화성#1 T/L","[11월취소시][즉시가압O]아산-화성T/L 추락방지장치 설치공사","[11월취소시][즉시가압O]345kV 아산-화성#1T/L No.25,26호","2024-12-02 07:00","2024-12-04 18:00","취소","취소","매일"]
[60,"대전세종충남","청양","보령T/P #75 BUS","345kV LA, PT GIS 내장화공사(아산-보령화력#1)","345kV LA, PT GIS 내장화공사 - 345 아산-보령화력#1 무부하가압 #75BUS 휴전 (즉시가압가능)","2024-12-19 09:00","2024-12-20 18:00","취소","취소","연속"]
[61,"대전세종충남","청양","아산보령TP#1 T/L","345kV LA, PT GIS 내장화공사(아산-보령화력#1)","345kV LA, PT GIS 내장화공사 - 345 아산-보령화력#1 (즉시가압불가)","2024-12-09 06:00","2024-12-20 18:00","취소","취소","연속"]
[62,"대전세종충남","청양","보령T/P #70 BUS","345kV LA,PT GIS 내장화(무부하가압)","345kV LA,PT GIS 내장화(보령T/P 보령연락#1) 무부하가압용 모선 (즉시가압가능)","2024-12-05 09:00","2024-12-06 18:00","취소","취소","연속"]
[63,"대전세종충남","청양","청양S/S #2 M.Tr","청양P/O 변전협력 총액공사(청양 #2M.Tr 2차 조작)","청양P/O 변전협력 총액공사 (청양 #2M.Tr 2차 6244 조작) - 즉시가압 가능","2024-12-04 09:00","2024-12-04 12:00","2024-12-04 09:00","2024-12-04 12:00","연속"]
[64,"대전세종충남","청양","청양군산#1 T/L","[11월 미승인시]345kV 청양군산#1T/L 가공지선 교체","No.131~137, 162~165 가공지선 교체","2024-12-28 08:00","2024-12-29 18:00","취소","취소","연속"]
[65,"대전세종충남","청양","청양S/S CB 7372","청양P/O 변전협력 총액공사(청군#2 7372 조작)","청양P/O 변전협력 총액공사(청군#2 7372 조작) (즉시가압 가능)","2024-12-03 13:00","2024-12-03 18:00","2024-12-03 13:00","2024-12-03 18:00","연속"]
[66,"대전세종충남","청양","청양군산#2 T/L","[11월 미휴전시]345KV 청양군산#2T/L 애자련 보강","345KV 청양군산#1T/L 애자련 보강","2024-12-30 08:00","2024-12-31 18:00","취소","취소","연속"]
[67,"대전세종충남","청양","청양S/S SEC CB 70710","청양P/O 변전협력 총액공사(청양 섹션 절연열화)","청양P/O 변전협력 총액공사 - 청양S/S 섹션 절연열화 재측정","2024-12-03 08:00","2024-12-03 10:00","2024-12-03 08:00","2024-12-03 10:00","연속"]
[68,"대전세종충남","청양","청양S/S SEC CB 75760","청양P/O 변전협력 총액공사(청양 섹션 절연열화)","청양P/O 변전협력 총액공사 - 청양S/S 섹션 절연열화 재측정","2024-12-03 10:00","2024-12-03 12:00","2024-12-03 10:00","2024-12-03 12:00","연속"]
[69,"전북","군산","군산S/S #1 Sh.R CB","군산S/S 345kV GIS 절연열화 측정","군산S/S 345kV GIS 절연열화 측정","2024-12-09 09:00","2024-12-09 18:00","2024-12-09 09:00","2024-12-09 18:00","연속"]
[70,"전북","군산","군산S/S #1 Sh.R CB","군산변전소 345kV GIS 대체공사(기기) (중복)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2024-12-23 15:00","2024-12-24 15:00","2024-12-23 15:00","2024-12-24 15:00","연속"]
[71,"전북","군산","군산S/S #75 BUS","군산변전소 345kV GIS 대체공사 (중복)","○ 362kV GIS 40kA 4000A × 10CB(4Bay) 철거 ○ 362kV GIS 50kA 4000A × 10CB(4Bay) 신설 ○ 기타부대공사 × 1식","2024-12-17 09:00","2024-12-24 18:00","2024-12-17 09:00","2024-12-24 18:00","연속"]
[72,"전북","군산","군산S/S #1 Sh.R CB","군산변전소 345kV GIS 대체공사(기기) (중복)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2024-12-15 15:00","2024-12-16 15:00","2024-12-15 15:00","2024-12-16 15:00","연속"]
[73,"전북","군산","군산신김제#2 T/L","군산P/O 154kV 이상 차단기 점검공사","군산P/O 154kV 이상 차단기 점검공사","2024-12-02 09:00","2024-12-02 18:00","2024-12-02 09:00","2024-12-02 18:00","연속"]
[74,"전북","군산","군산신김제#1 T/L","군산P/O 154kV 이상 차단기 점검공사","군산P/O 154kV 이상 차단기 점검공사","2024-12-03 09:00","2024-12-03 18:00","2024-12-03 09:00","2024-12-03 18:00","연속"]
[75,"전북","군산","청양군산#1 T/L","군산S/S 154kV이상 차단기 점검공사","군산S/S 154kV이상 차단기 점검공사","2024-12-04 09:00","2024-12-04 18:00","2024-12-04 09:00","2024-12-04 18:00","연속"]
[76,"전북","군산","청양군산#2 T/L","군산S/S 154kV이상 차단기 점검공사","군산S/S 154kV이상 차단기 점검공사","2024-12-05 09:00","2024-12-05 18:00","2024-12-05 09:00","2024-12-05 18:00","연속"]
[77,"전북","군산","군산S/S CB 7272","군산P/O 154kV이상 차단기 점검공사","군산P/O 154kV이상 차단기 점검공사","2024-12-26 09:00","2024-12-26 18:00","2024-12-26 09:00","2024-12-26 18:00","연속"]
[78,"전북","군산","군산S/S #70 BUS","군산변전소 345kV GIS 대체공사 (중복)","○ 362kV GIS 40kA 4000A × 10CB(4Bay) 철거 ○ 362kV GIS 50kA 4000A × 10CB(4Bay) 신설 ○ 기타부대공사 × 1식","2024-12-09 09:00","2024-12-16 18:00","2024-12-09 09:00","2024-12-16 18:00","연속"]
[79,"전북","김제","신김제S/S #1 M.Tr","24년 김제전력지사 부싱유 채유공사","부싱유 채유공사","2024-12-18 08:00","2024-12-18 18:00","2024-11-27 08:00","2024-11-27 18:00","연속"]
[80,"전북","김제","신김제S/S #2 M.Tr","24년 김제전력지사 부싱유 채유공사","부싱유 채유공사","2024-12-19 08:00","2024-12-19 18:00","2024-11-28 08:00","2024-11-28 18:00","연속"]
[81,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(중복)","345kV 신남원-신광주T/L No.1~115 수평 추락방지장치 및 조류착지방지장치 설치","2024-12-10 07:00","2024-12-17 17:00","2024-12-10 07:00","2024-12-17 17:00","매일"]
[82,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(중복)","345kV 신남원-신광주T/L No.1~115 수평 추락방지장치 및 조류착지방지장치 설치","2024-12-02 07:00","2024-12-09 17:00","2024-12-02 07:00","2024-12-09 17:00","매일"]
[83,"광주전남","강진","신화순신강진#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","산형강 가이드레일 추락방지장치 설치","2024-12-12 07:00","2024-12-12 18:00","2024-12-12 07:00","2024-12-12 18:00","연속"]
[84,"광주전남","강진","신강진S/S #1 M.Tr","24~25년 강진전력지사 변전협력회사 공사","신강진S/S #1M.Tr 방호벽 사다리 철거","2024-12-09 08:00","2024-12-09 10:00","2024-12-09 08:00","2024-12-09 10:00","연속"]
[85,"광주전남","강진","신강진S/S #3 M.Tr","24~25년 강진전력지사 변전협력회사 공사","신강진S/S #3M.Tr 방호벽 사다리 철거","2024-12-09 13:00","2024-12-09 15:00","2024-12-09 13:00","2024-12-09 15:00","연속"]
[86,"광주전남","강진","신강진S/S #2 M.Tr","24~25년 강진전력지사 변전협력회사 공사","신강진S/S #2M.Tr 방호벽 사다리 철거","2024-12-09 10:00","2024-12-09 12:00","2024-12-09 10:00","2024-12-09 12:00","연속"]
[87,"광주전남","강진","신화순신강진#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","산형강 가이드레일 추락방지장치 설치","2024-12-11 07:00","2024-12-11 18:00","2024-12-11 07:00","2024-12-11 18:00","연속"]
[88,"광주전남","강진","신강진S/S #4 M.Tr","24~25년 강진전력지사 변전협력회사 공사","신강진S/S #4M.Tr 방호벽 사다리 철거","2024-12-09 15:00","2024-12-09 17:00","2024-12-09 15:00","2024-12-09 17:00","연속"]
[89,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2024-12-02 08:00","2024-12-06 18:00","취소","취소","연속"]
[90,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체","2024-12-09 08:00","2024-12-13 18:00","취소","취소","연속"]
[91,"광주전남","광주","신남원신광주#2 T/L","'24년 광주전력지사 변전협력회사 공사","신광주S/S 신남원-신광주 #2T/L LA 보통점검 및 CVT 초기점검","2024-12-10 09:00","2024-12-10 18:00","2024-12-10 09:00","2024-12-10 18:00","연속"]
[92,"광주전남","광주","신남원신광주#1 T/L","'24년 광주전력지사 변전협력회사 공사","신광주S/S 신남원-신광주 #1T/L LA 및 CVT 보통점검","2024-12-09 09:00","2024-12-09 18:00","2024-12-09 09:00","2024-12-09 18:00","연속"]
[93,"광주전남","광주","신화순S/S CB 7672","24년 광주전력지사 변전협력회사 총액공사","- 362kV GIS 하자보수","2024-12-11 09:00","2024-12-13 18:00","2024-12-11 09:00","2024-12-13 18:00","연속"]
[94,"광주전남","광주","신화순S/S #1 Sh.R CB","24년 광주전력지사 변전협력회사 총액공사","- 362kV GIS 하자보수","2024-12-11 09:00","2024-12-13 18:00","2024-12-11 09:00","2024-12-13 18:00","연속"]
[95,"광주전남","광주","신화순S/S CB 7600","24년 광주전력지사 변전협력회사 총액공사","- 362kV GIS 하자보수","2024-12-11 09:00","2024-12-13 18:00","2024-12-11 09:00","2024-12-13 18:00","연속"]
[96,"광주전남","광주","신화순S/S #3 M.Tr","24년 광주전력지사 변전협력회사 총액공사","- #3M.Tr 보호반 대체","2024-12-02 08:00","2024-12-06 18:00","2024-12-02 08:00","2024-12-06 18:00","연속"]
[97,"광주전남","목포","신광주한빛NP#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","한빛#1S/Y 345kV 신광주-한빛#2T/L GIS(7272) 인출부싱 염해방지 코팅제 도포","2024-12-16 09:00","2024-12-17 18:00","2024-12-16 09:00","2024-12-17 18:00","매일"]
[98,"광주전남","목포","한빛#1N/P CB 7F71","2024~2025년 목포전력지사 변전협력회사 공사","한빛#1S/Y 7F71 GIS 조작시험","2024-12-19 14:00","2024-12-19 18:00","2024-12-19 14:00","2024-12-19 18:00","연속"]
[99,"광주전남","목포","한빛#1N/P CB 7371","2024~2025년 목포전력지사 변전협력회사 공사","한빛#1S/Y 7371 GIS 조작시험","2024-12-19 09:00","2024-12-19 14:00","2024-12-19 09:00","2024-12-19 14:00","연속"]
[100,"광주전남","목포","한빛#1N/P CB 7471","2024~2025년 목포전력지사 변전협력회사 공사","한빛#1S/Y 7471 GIS 조작시험","2024-12-19 14:00","2024-12-19 18:00","2024-12-19 14:00","2024-12-19 18:00","연속"]
[101,"광주전남","목포","한빛#3N/P CB 7D00","2024~2025년 목포전력지사 변전협력회사 공사","한빛#3S/Y 7D00 GIS 조작시험 및 균압콘덴서 절연열화 측정","2024-12-12 14:00","2024-12-12 18:00","2024-12-12 14:00","2024-12-12 18:00","연속"]
[102,"광주전남","목포","한빛#3N/P CB 7D71","2024~2025년 목포전력지사 변전협력회사 공사","한빛#3S/Y 7D71 GIS 조작시험 및 균압콘덴서 절연열화 측정","2024-12-12 09:00","2024-12-12 14:00","2024-12-12 09:00","2024-12-12 14:00","연속"]
[103,"광주전남","목포","신김제한빛NP#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","한빛#3S/Y 7D00, 7D72 GIS 조작시험 및 균압콘덴서 절연열화 측정","2024-12-11 09:00","2024-12-11 18:00","2024-12-11 09:00","2024-12-11 18:00","연속"]
[104,"광주전남","목포","한빛#3N/P CB 7B71","2024~2025년 목포전력지사 변전협력회사 공사","한빛#3S/Y 7B71 GIS 하자점검","2024-12-10 09:00","2024-12-10 18:00","2024-12-10 09:00","2024-12-10 18:00","연속"]
[105,"광주전남","목포","한빛#3N/P CB 7D72","2024~2025년 목포전력지사 변전협력회사 공사","한빛#3S/Y 7D72 GIS 조작시험 및 균압콘덴서 절연열화 측정","2024-12-13 09:00","2024-12-13 14:00","2024-12-13 09:00","2024-12-13 14:00","연속"]
[106,"광주전남","순천","신강진광양#1 T/L","345kV 신강진-광양T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-12-09 07:00","2024-12-12 18:00","2024-12-09 07:00","2024-12-12 18:00","매일"]
[107,"광주전남","순천","신강진광양#1 T/L","345kV 신강진-광양T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-12-09 07:00","2024-12-11 18:00","2024-12-09 07:00","2024-12-11 18:00","매일"]
[108,"광주전남","순천","광양율촌CC T/L","345kV 광양-여수TPT/L 일부구간 지중화 공사","345kV 광양-여수TPT/L 일부 지중화 관련 C/T 설치공사","2024-12-02 07:30","2024-12-12 18:00","2024-12-02 07:30","2024-12-12 18:00","연속"]
[109,"광주전남","순천","광양하동TP#2 T/L","345kV 광양-하동TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-12-26 07:00","2024-12-27 18:00","2024-12-26 07:00","2024-12-27 18:00","매일"]
[110,"광주전남","순천","율촌CC여수TP T/L","율촌CC 여수TP T/L PNL DC접지 해소작업","율촌CC 여수TP T/L PNL DC접지 해소작업","2024-12-09 09:00","2024-12-09 18:00","2024-12-09 09:00","2024-12-09 18:00","연속"]
[111,"광주전남","순천","여수T/P #2 Tie-Tr","#2M.Tr 3차 VCB 부 과열개소 조치","#2M.Tr 3차 VCB 부 과열개소 조치","2024-12-02 09:00","2024-12-02 18:00","2024-12-02 09:00","2024-12-02 18:00","연속"]
[112,"광주전남","순천","광양여수TP T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-12-13 07:00","2024-12-13 18:00","2024-12-13 07:00","2024-12-13 18:00","연속"]
[113,"광주전남","순천","여수T/P #1 Tie-Tr","345kV 3차 DS 과열개소 조치","345kV 3차 DS 과열개소 조치","2024-12-03 09:00","2024-12-03 18:00","2024-12-03 09:00","2024-12-03 18:00","연속"]
[114,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업","2024-12-02 07:30","2024-12-20 18:00","2024-12-02 07:30","2024-12-20 18:00","연속"]
[115,"대구","포항","신포항S/S 예비 M.Tr CB","2024~25년도 포항전력지사 변전총액공사","신포항S/S 예비M.Tr 초기점검","2024-12-12 09:00","2024-12-12 18:00","취소","취소","연속"]
[116,"대구","포항","울주월성NP#2 T/L","2024~25년도 포항전력지사 변전총액공사","월성S/Y 7200,7272 GIS 보통점검, 7671,7271 GIS 조작시험, 울주-월성#2T/L PT 보통점검","2024-12-17 09:00","2024-12-18 18:00","2024-12-17 09:00","2024-12-18 18:00","연속"]
[117,"대구","포항","월성N/P CB 7671","24~25년도 포항전력지사 변전총액공사","월성S/Y 7671 GIS 조작시험","2024-12-18 09:00","2024-12-18 18:00","2024-12-18 09:00","2024-12-18 18:00","연속"]
[118,"대구","포항","월성N/P CB 7272","24~25년도 포항전력지사 변전총액공사","월성S/Y 7272 GIS 보통점검","2024-12-17 09:00","2024-12-17 18:00","2024-12-17 09:00","2024-12-17 18:00","연속"]
[119,"경북","영주","신영주S/S #1 M.Tr","2024-25년 영주전력지사 변전협력회사 공사","3차 LA 대체","2024-12-03 09:00","2024-12-03 18:00","2024-12-03 09:00","2024-12-03 18:00","연속"]
[120,"경북","영주","신영주S/S #2 M.Tr","2024-25년 영주전력지사 변전협력회사 공사","M.TR 보통점검","2024-12-04 09:00","2024-12-05 18:00","2024-12-04 09:00","2024-12-05 18:00","연속"]
[121,"경북","영주","한울#1N/P CB 7471","2024~25년 영주전력지사 변전협력회사 총액공사","7471 GIS 보통점검","2024-12-02 09:00","2024-12-02 18:00","2024-12-02 09:00","2024-12-02 18:00","연속"]
[122,"경북","직할","신영일안동CC T/L","'24~25년 경북 직할 가공송전 협력회사 공사","345kV 안동복합분기T/L 추락방지장치 설치공사","2024-12-16 08:00","2024-12-24 18:00","2024-12-16 08:00","2024-12-24 18:00","연속"]
[123,"경북","직할","신영주안동CC T/L","'24~25년 경북 직할 가공송전 협력회사 공사","345kV 안동복합분기T/L 추락방지장치 설치공사","2024-12-05 08:00","2024-12-13 18:00","2024-12-05 08:00","2024-12-13 18:00","연속"]
[124,"부산울산","북부산","북부산S/S #2 Sh.R CB","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #2Sh.R 부싱절연유채유","2024-12-06 09:00","2024-12-06 14:00","2024-12-06 09:00","2024-12-06 14:00","연속"]
[125,"부산울산","북부산","북부산S/S #4 Sh.R CB","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S 345kV #4Sh.R 부싱절연유채유","2024-12-06 14:00","2024-12-06 18:00","2024-12-06 14:00","2024-12-06 18:00","연속"]
[126,"부산울산","서부산","서부산S/S CB 7271","서부산S/S 345kV 7271 GIS 불량 보조계전기 교체","서부산S/S 345kV 7271 GIS 불량 보조계전기 교체","2024-12-05 09:00","2024-12-05 18:00","2024-12-05 09:00","2024-12-05 18:00","연속"]
[127,"부산울산","서부산","신김해신녹산#1 T/L","24~25년 서부산전력지사 가공송전협력회사 공사","154kV 미음-녹산T/L 항공장애표시구 설치 안전이격","2024-12-09 09:00","2024-12-09 18:00","2024-12-09 09:00","2024-12-09 18:00","연속"]
[128,"부산울산","울산","남울산S/S CB 7671","남울산S/S 일진제 345kV GIS 하자보수","- 7671 3상 유압조작기 교체","2024-12-18 09:00","2024-12-20 18:00","2024-12-18 09:00","2024-12-20 18:00","연속"]
[129,"부산울산","울산","남울산S/S CB 7371","남울산S/S 일진제 345kV GIS 하자보수","- 7371 3상 유압조작기 교체","2024-12-04 09:00","2024-12-06 18:00","2024-12-04 09:00","2024-12-06 18:00","연속"]
[130,"부산울산","울산","동울산S/S #3 M.Tr","24년 울산전력지사 변전협력회사 총액공사","- 1차 7472 차단기 동작시험","2024-12-02 09:00","2024-12-02 18:00","2024-12-02 09:00","2024-12-02 18:00","연속"]
[131,"부산울산","울산","신온산신울산#2 T/L","24년 울산전력지사 변전협력회사 총액공사","- 신울산,신온산측 송전선로 보호반 대체","2024-12-09 09:00","2024-12-13 18:00","2024-12-09 09:00","2024-12-13 18:00","연속"]
[132,"부산울산","울산","울주S/S CB 7900","24년 울산전력지사 변전협력회사 총액공사","- 7900 투입불량관련 현장확인 및 조치작업","2024-12-03 09:00","2024-12-03 18:00","2024-12-03 09:00","2024-12-03 18:00","연속"]
[133,"경남","김해송변전부","신김해신녹산#1 T/L","신김해S/S 신김해-신녹산#1T/L 휴전","[시험가압]신김해S/S 345kV #3 M.Tr 1차 GIS 시험가압용","2024-12-07 19:00","2024-12-08 06:30","2024-12-07 19:00","2024-12-08 06:30","연속"]
[134,"경남","김해송변전부","신김해S/S CB 7772","신김해S/S 345kV #3 M.Tr 1차 GIS(7772) 정밀점검","신김해S/S 345kV #3 M.Tr 1차 GIS(7772) 정밀점검","2024-12-07 19:00","2024-12-08 06:30","2024-12-07 19:00","2024-12-08 06:30","연속"]
[135,"경남","김해송변전부","신김해북부산#1 T/L","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2024-12-14 07:00","2024-12-14 18:00","2024-12-14 07:00","2024-12-14 18:00","매일"]
[136,"경남","김해송변전부","신마산신김해#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-12-14 07:00","2024-12-15 18:00","2024-12-14 07:00","2024-12-15 18:00","매일"]
[137,"경남","김해송변전부","신마산신김해#1 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사 (9일작업없음, 10일~13일까지는 함안전력지사관할지역)","2024-12-07 07:00","2024-12-13 18:00","2024-12-07 07:00","2024-12-13 18:00","매일"]
[138,"경남","김해송변전부","신김해S/S #1 M.Tr","신김해S/S 6333 정밀점검 시험가압용","신김해S/S 6333 정밀점검 시험가압용","2024-12-08 16:00","2024-12-08 17:00","2024-12-08 16:00","2024-12-08 17:00","연속"]
[139,"경남","김해송변전부","신김해S/S #4 M.Tr","신김해S/S 66-67-0 GIS 정밀점검 시험가압선로","신김해S/S 66-67-0 GIS 정밀점검 시험가압선로","2024-12-14 16:00","2024-12-14 17:00","2024-12-14 16:00","2024-12-14 17:00","연속"]
[140,"경남","김해송변전부","신김해S/S #3 M.Tr","신김해S/S 61-62-0 GIS 정밀점검 시험가압선로","신김해S/S 61-62-0 GIS 정밀점검 시험가압선로","2024-12-11 16:00","2024-12-11 17:00","2024-12-11 16:00","2024-12-11 17:00","연속"]
[141,"경남","김해송변전부","신김해북부산#1 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-12-08 07:00","2024-12-08 18:00","2024-12-08 07:00","2024-12-08 18:00","연속"]
[142,"경남","김해송변전부","신김해북부산#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-12-07 07:00","2024-12-07 18:00","2024-12-07 07:00","2024-12-07 18:00","연속"]
[143,"경남","김해송변전부","신김해S/S #3 M.Tr","[시험가압]신김해S/S 345kV #3 M.Tr 1차 GIS 시험가압용","[시험가압]신김해S/S 345kV #3 M.Tr 1차 GIS 시험가압용","2024-12-07 19:00","2024-12-08 06:30","2024-12-07 19:00","2024-12-08 06:30","연속"]
[144,"경남","직할","창원S/S #2 M.Tr","창원S/S 154kV 한국철강T/L 신규수용공사","1. GIS(170kV 50kA 2,000A) x 1CCT 설치 2. 기타 부대공사 x 1식 3. 안전이격거리 확보","2024-12-10 08:00","2024-12-13 18:00","2024-12-10 08:00","2024-12-13 18:00","연속"]
[145,"경남","직할","창원S/S #2 M.Tr","창원S/S 154kV 한국철강T/L 신규수용공사","1. GIS(170kV 50kA 2,000A) x 1CCT 설치 2. 기타 부대공사 x 1식 3. 안전이격거리 확보","2024-12-02 08:00","2024-12-02 18:00","2024-12-02 08:00","2024-12-02 18:00","연속"]
[146,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-12-07 07:00","2024-12-08 18:00","2024-12-07 07:00","2024-12-08 18:00","매일"]
[147,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-12-28 07:00","2024-12-29 18:00","2024-12-28 07:00","2024-12-29 18:00","매일"]
[148,"경남","진주","의령하동화력#1 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-12-14 07:00","2024-12-15 18:00","2024-12-14 07:00","2024-12-15 18:00","매일"]
[149,"경남","진주","의령S/S CB 7271","의령S/S 345kV 7271 GIS 보통점검(차단기 단독)","의령S/S 345kV 7271 GIS 보통점검(차단기 단독)","2024-12-11 09:00","2024-12-11 14:00","2024-12-11 09:00","2024-12-11 14:00","연속"]
[150,"경남","진주","의령S/S CB 7200","의령S/S 345kV 7200 GIS 보통점검(차단기 단독)","의령S/S 345kV 7200 GIS 보통점검(차단기 단독)","2024-12-11 14:00","2024-12-11 18:00","2024-12-11 14:00","2024-12-11 18:00","연속"]
[151,"경남","진주","의령하동화력#2 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 : 345kV 의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(345kV의령-산청양수와 병가135~152)","2024-12-21 07:00","2024-12-22 18:00","2024-12-21 07:00","2024-12-22 18:00","매일"]
[152,"경남","진주","하동T/P CB 7571","하동T/P 345kV 7571 GIS 보통점검(차단기 단독)","하동T/P 345kV 7571 GIS 보통점검(차단기 단독)","2024-12-10 10:00","2024-12-10 15:00","2024-12-10 10:00","2024-12-10 15:00","연속"]

{"sheet":"154설비","index":2,"n_rows":329,"n_cols":11,"rows_kept":329,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2024년도 12월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","구의S/S #2 BUS","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#1T/L, #1M.Tr 1차 GIS 교체","2024-12-02 15:00","2024-12-12 15:00","2024-11-29 15:00","2024-11-29 18:00","연속"]
[2,"서울","성동","천호구의#2 T/L","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#1T/L, #1M.Tr 1차 GIS 교체","2024-12-11 15:00","2024-12-12 15:00","2024-11-28 15:00","2024-11-29 18:00","연속"]
[3,"서울","성동","구의S/S #1 BUS","2024년도 구의S/S 154kV 장기사용 GIS 교체공사","천호-구의#1T/L, #1M.Tr 1차 GIS 교체","2024-12-12 15:00","2024-12-13 15:00","2024-11-22 15:00","2024-11-29 15:00","연속"]
[4,"서울","성동","성동S/S #60 BUS","성동S/S 154kV Sh.R 설치공사(시험가압)","1. 154kV Sh.R(20MVAR×3) × 2조 설치 2. 154kV Sh.R 1차 GIS × 2Bay 설치 3. 기타 부대공사 × 1식","2024-12-05 14:00","2024-12-06 14:00","2024-12-05 14:00","2024-12-06 14:00","연속"]
[5,"서울","성동","성동군자#1 T/L","성동S/S 154kV Sh.R 설치공사(무부하가압 선로)","1. 154kV Sh.R(20MVAR×3) × 2조 설치 2. 154kV Sh.R 1차 GIS × 2Bay 설치 3. 기타 부대공사 × 1식","2024-12-05 14:00","2024-12-06 14:00","2024-12-03 16:00","2024-12-03 18:00","연속"]
[6,"서울","중부","당인리S/S CB 6100","2024년 중부전력지사 변전정비 협력회사 총액공사","불량개소 보수","2024-12-05 10:00","2024-12-05 18:00","2024-12-05 10:00","2024-12-05 18:00","연속"]
[7,"서울","중부","옥인운니#2 T/L","2024년 중부전력지사 170kV GIS 정밀점검","GIS 보통점검","2024-12-03 10:00","2024-12-03 18:00","2024-12-03 10:00","2024-12-03 18:00","연속"]
[8,"서울","중부","옥인운니#1 T/L","2024년 중부전력지사 170kV GIS 정밀점검","GIS 보통점검","2024-12-02 10:00","2024-12-02 18:00","2024-12-02 10:00","2024-12-02 18:00","연속"]
[9,"남서울","강남","신양재신사#3 T/L","EBG 해체점검 및 가스채취밸브 설치공사","○ 대상 : 154kV 신양재-개포 등 4개 T/L ○ 내용 : EBG 해체점검 및 가스채취밸브 설치","2024-12-02 08:00","2024-12-03 18:00","2024-12-02 08:00","2024-12-03 18:00","연속"]
[10,"남서울","영등포","시흥독산#2 T/L","2024~2025년 영등포전력지사 변전협력회사 총액공사","공사내용: 러버히터,전원케이블 추가 시공","2024-12-02 09:00","2024-12-02 18:00","2024-12-02 09:00","2024-12-02 18:00","연속"]
[11,"인천","부평","남인천학익#1 T/L","남인천S/S 남인천학익#1 T/L GIS SA혼용화 공사","남인천S/S 남인천학익#1 T/L GIS SA혼용화 공사","2024-12-01 09:00","2024-12-01 18:00","취소","취소","연속"]
[12,"인천","부평","서인천CC신경서 T/L","서인천CC신경서 T/L GIS 조작시험","서인천CC신경서 T/L GIS 조작시험","2024-12-10 09:00","2024-12-10 18:00","2024-12-10 09:00","2024-12-10 18:00","연속"]
[13,"인천","부평","서인천C/C CB 6200","서인천C/C 154kV #61-#66 BUS TIE GIS 조작시험","서인천C/C 154kV #61-#66 BUS TIE GIS 조작시험","2024-12-04 12:00","2024-12-04 18:00","2024-12-04 12:00","2024-12-04 18:00","연속"]
[14,"인천","부평","서인천C/C CB 6100","서인천C/C 154kV #60-#65 BUS TIE GIS 조작시험","서인천C/C 154kV #60-#65 BUS TIE GIS 조작시험","2024-12-04 09:00","2024-12-04 12:00","2024-12-04 09:00","2024-12-04 12:00","연속"]
[15,"인천","부평","서인천C/C SEC CB 60610","서인천C/C 154kV #60-#61 SEC GIS 조작시험","서인천C/C 154kV #60-#61 SEC GIS 조작시험","2024-12-05 12:00","2024-12-05 18:00","2024-12-05 12:00","2024-12-05 18:00","연속"]
[16,"인천","부평","서인천C/C SEC CB 65660","서인천C/C 154kV #65-#66 SEC GIS 조작시험","서인천C/C 154kV #65-#66 SEC GIS 조작시험","2024-12-05 09:00","2024-12-05 12:00","2024-12-05 09:00","2024-12-05 12:00","연속"]
[17,"인천","부평","신가좌S/S SEC CB 66670","신가좌S/S 154kV #66-#67 SEC GIS 보통점검","신가좌S/S 154kV #66-#67 SEC GIS 보통점검","2024-12-02 09:00","2024-12-02 12:00","취소","취소","연속"]
[18,"인천","부평","신가좌신현#2 T/L","신가좌S/S 신가좌신현#2 T/L GIS 조작시험","신가좌S/S 신가좌신현#2 T/L GIS 조작시험","2024-12-06 12:00","2024-12-06 18:00","취소","취소","연속"]
[19,"인천","부평","신가좌신현#1 T/L","신가좌S/S 신가좌신현#1 T/L GIS 조작시험","신가좌S/S 신가좌신현#1 T/L GIS 조작시험","2024-12-06 09:00","2024-12-06 12:00","취소","취소","연속"]
[20,"인천","부평","신가좌S/S SEC CB 65660","신가좌S/S 154kV #65-#66 SEC 보통점검","신가좌S/S 154kV #65-#66 SEC 보통점검","2024-12-02 12:00","2024-12-02 18:00","취소","취소","연속"]
[21,"인천","부평","인천CC북인천#1 T/L","인천C/C 인천CC북인천#1 T/L GIS 조작시험","인천C/C 인천CC북인천#1 T/L GIS 조작시험","2024-12-03 09:00","2024-12-03 12:00","취소","취소","연속"]
[22,"인천","부평","인천C/C CB 6100","인천CC S/Y 154kV #60-#65 BUS TIE GIS 조작시험","인천CC S/Y 154kV #60-#65 BUS TIE GIS 조작시험","2024-12-02 09:00","2024-12-02 18:00","취소","취소","연속"]
[23,"인천","부평","인천CC북인천#2 T/L","인천C/C 인천CC북인천#2 T/L GIS 조작시험","인천C/C 인천CC북인천#2 T/L GIS 조작시험","2024-12-03 12:00","2024-12-03 18:00","취소","취소","연속"]
[24,"인천","직할","신부평도당#2 T/L","154kV 도당S/S #4M.Tr 증설공사","- 154kV #4M.Tr 무부하가압 및 상체크","2024-12-29 09:00","2024-12-31 18:00","2024-12-29 09:00","2024-12-31 18:00","연속"]
[25,"인천","직할","도당S/S #61 BUS","154kV 도당S/S #4M.Tr 증설공사","- 154kV #4M.Tr 무부하가압 및 상체크","2024-12-29 09:00","2024-12-31 18:00","2024-12-29 09:00","2024-12-31 18:00","연속"]
[26,"인천","직할","도당S/S #66 BUS","154kV 도당S/S #4M.Tr 증설공사","- 154kV #4M.Tr 무부하가압 및 상체크","2024-12-29 09:00","2024-12-31 18:00","2024-12-29 09:00","2024-12-31 18:00","연속"]
[27,"경기북부","고양","양주고양#2 T/L","154kV 고양S/S #4M.Tr 증설공사(최초가압)","12/09(월)~12/10(화) : 양주고양#2 - 60BUS - #4M.Tr - 4243BUS무부하(24Hr) 12/10(화)~12/10(수) : 양주고양#2 - 60BUS - #4M.Tr - 4748BUS무부하(24Hr) 12/11(수) : 양주고양#2 - 65BUS - #4M.Tr - 43BUS 상체크 & 48BUS 상체크","2024-12-09 09:00","2024-12-11 18:00","2024-12-05 09:00","2024-12-07 18:00","연속"]
[28,"경기북부","직할","양주지축#2 T/L","2024년 가공송전 순시점검 위탁공사(고양)","수목전지","2024-12-03 09:00","2024-12-03 18:00","2024-12-03 09:00","2024-12-03 18:00","연속"]
[29,"경기","군포","남군포의왕#2 T/L","남군포S/S 남군포-의왕#2T/L 샤프트링 점검","남군포S/S 남군포-의왕#2T/L 샤프트링 점검","2024-12-02 09:00","2024-12-02 18:00","2024-12-02 09:00","2024-12-02 18:00","연속"]
[30,"경기","군포","남군포산본#2 T/L","154kV 남군포S/S #4M.Tr 증설공사_무부하가압","154kV 남군포S/S #4M.Tr 증설공사_무부하가압","2024-12-03 09:00","2024-12-04 18:00","2024-12-03 09:00","2024-12-04 18:00","연속"]
[31,"경기","군포","장덕마도#2 T/L","2024년도 가공송전 순시점검 위탁공사","154kV 장덕분기T/L 계통보강공사 관련 인수점검 시행","2024-12-04 13:00","2024-12-04 17:00","2024-12-04 13:00","2024-12-04 17:00","연속"]
[32,"경기","군포","장덕마도#1 T/L","2024년도 가공송전 순시점검 위탁공사","154kV 장덕분기T/L 계통보강공사 관련 인수점검 시행","2024-12-04 09:00","2024-12-04 13:00","취소","취소","연속"]
[33,"경기","동부","곤지암S/S SEC CB 65660","24-25년 동부 변전협력 총액공사","곤지암:65-66(보통)","2024-12-06 09:30","2024-12-06 18:00","취소","취소","연속"]
[34,"경기","동부","동판교야탑 T/L","23-24년 지중송전설비 위탁정비공사(성남전력지사)","대한전선 열경화공법 EBG 가스채취밸브 설치","2024-12-09 09:00","2024-12-12 18:00","취소","취소","연속"]
[35,"경기","동부","이천S/S SEC CB 65660","24-25년 동부 변전협력 총액공사","이천:65-66(보통)","2024-12-04 09:30","2024-12-04 18:00","취소","취소","연속"]
[36,"경기","동부","중원야탑 T/L","23-24년 지중송전설비 위탁정비공사(성남전력지사)","대한전선 열경화공법 EBG 가스채취밸브 설치","2024-12-02 09:00","2024-12-05 18:00","취소","취소","연속"]
[37,"경기","성남","오천용인#1 T/L","2024년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검 (병행) IED 성능개선 (병행) CVT, LA 보통점검","2024-12-02 09:00","2024-12-03 18:00","2024-12-02 09:00","2024-12-03 18:00","연속"]
[38,"경기","직할","관양동안양#2 T/L","154kV #3M.Tr 무부하 가압선로","154kV #3M.Tr 24시간 무부하 가압선로","2024-12-23 10:00","2024-12-24 18:00","2024-12-23 10:00","2024-12-24 18:00","연속"]
[39,"경기","직할","서서울율전#2 T/L","2024-25년 경기본부 직할 변전협력회사 공사","율전: 서서울-율전#2T/L 보통점검","2024-12-02 09:00","2024-12-02 18:00","취소","취소","연속"]
[40,"경기","직할","화성장덕#2 T/L","154kV 화성-장덕T/L OPGW 증설공사","154kV 화성-장덕T/L OPGW 증설공사 - OPGW 증설교체(OP-S-L24 → L48) 7.797km(해당구간 2km) - 광코어 접속, 최종시험 및 기타 부대공사 1식","2024-12-13 07:00","2024-12-15 18:00","취소","취소","연속"]
[41,"경기","직할","화성S/S SEC CB 66670","2024-25년 경기본부 직할 변전협력회사 공사","화성: 61-62, 66-67SEC 보통점검","2024-12-06 09:00","2024-12-06 14:00","취소","취소","연속"]
[42,"경기","직할","화성S/S CB 6300","2024-25년 경기본부 직할 변전협력회사 공사","화성: 6300 보통점검(+전자변) - 에어링밸브 교체.","2024-12-05 09:00","2024-12-05 18:00","취소","취소","연속"]
[43,"경기","직할","화성남양#2 T/L","2024-25년 경기본부 직할 변전협력회사 공사","화성: 화성-남양#2T/L 보통점검 - LA, CVT 보통점검","2024-12-01 14:00","2024-12-01 18:00","2024-12-01 14:00","2024-12-01 18:00","연속"]
[44,"경기","직할","화성남양#1 T/L","2024-25년 경기본부 직할 변전협력회사 공사","화성: 화성-남양#1T/L 보통점검 - LA, CVT 보통점검","2024-12-01 09:00","2024-12-01 14:00","2024-12-01 09:00","2024-12-01 14:00","연속"]
[45,"경기","직할","화성S/S SEC CB 61620","2024-25년 경기본부 직할 변전협력회사 공사","화성: 61-62, 66-67SEC 보통점검","2024-12-06 09:00","2024-12-06 14:00","취소","취소","연속"]
[46,"경기","평택","오산평택#1 T/L","154kV 오산-평택 등 2개T/L 지중화공사_가공","-가철탑 설치 2기 -전력선 설치 : ACSR 330 0.428 km-C -전력선 이설 : ACSR 330 1.322 km-C","2024-12-05 07:00","2024-12-08 18:00","2024-12-05 07:00","2024-12-08 18:00","연속"]
[47,"경기","평택","포승청북 T/L","추락방지장치(수평) 설치공사","154kV 포승-청북T/L No.32~46 2회선 12기","2024-12-09 08:00","2024-12-10 18:00","취소","취소","연속"]
[48,"경기","평택","포승평택TP#1 T/L","154kV 포승S/S #4M.TR 설치공사","- 154kV #4M.TR 무부하가압","2024-12-10 16:00","2024-12-11 18:00","2024-12-10 16:00","2024-12-11 18:00","연속"]
[49,"강원","동해","동해T/P CB 6100","2024~25년 동해전력지사 변전협력회사 공사","차단기 조작시험","2024-12-11 09:00","2024-12-11 18:00","2024-12-11 09:00","2024-12-11 18:00","연속"]
[50,"강원","직할","남춘천춘천열병합#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","남춘천춘천열병합#1 T/L 차단기 조작시험","2024-12-03 10:00","2024-12-03 13:00","취소","취소","연속"]
[51,"강원","직할","남춘천춘천 T/L","2024~2025년 강원본부 직할 송전협력회사 공사","피뢰기 설치","2024-12-02 00:08","2024-12-13 18:00","2024-12-04 08:00","2024-12-08 18:00","매일"]
[52,"강원","직할","청평HP의암HP T/L","2024년 가공송전선로 순시점검 위탁공사 수목벌채(직할)","154kV 의암T/L No.13 등 선하지 수목벌채 시행","2024-12-09 09:00","2024-12-10 18:00","취소","취소","매일"]
[53,"강원","직할","청평HP의암HP T/L","2024년 강원본부 직할 154kV GIS, GCB 정밀점검 공사","□ 154kV #1M.Tr 2차 GCB 무부하가압","2024-12-02 09:00","2024-12-02 18:00","2024-12-02 09:00","2024-12-02 18:00","연속"]
[54,"강원","직할","철원S/S #60 BUS","2024~2025년 강원본부 직할 변전협력회사 공사","철원S/S 154kV #60-#65 BUS PT GIS 보통점검","2024-12-09 10:00","2024-12-09 12:00","2024-12-09 10:00","2024-12-09 12:00","연속"]
[55,"강원","직할","철원S/S #65 BUS","2024~2025년 강원본부 직할 변전협력회사 공사","철원S/S 154kV #60-#65 BUS PT GIS 보통점검","2024-12-09 12:00","2024-12-09 14:00","2024-12-09 12:00","2024-12-09 14:00","연속"]
[56,"강원","직할","가평춘천HP T/L","2024~2025년 강원본부 직할 변전협력회사 공사","춘천HP 가평-춘천HP T/L 차단기 조작시험","2024-12-03 13:00","2024-12-03 18:00","취소","취소","연속"]
[57,"강원","직할","춘천북춘천#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","춘천-북춘천#1 T/L 보호배전반 대체(양단)","2024-12-03 09:00","2024-12-06 18:00","취소","취소","연속"]
[58,"강원","직할","춘천북춘천#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","춘천-북춘천#2 T/L 보호배전반 대체(양단)","2024-12-10 09:00","2024-12-13 18:00","취소","취소","연속"]
[59,"강원","직할","가평화천HP T/L","2024~2025년 강원본부 직할 변전협력회사 공사","가평화천HP T/L LA 보통점검 및 DS 보통점검","2024-12-02 10:00","2024-12-02 18:00","2024-12-02 10:00","2024-12-02 18:00","연속"]
[60,"강원","태백","태백S/S #60 BUS","154kV 태백S/S #2M.Tr 증설공사","#2M.Tr 최초가압","2024-12-16 14:00","2024-12-17 14:00","2024-12-16 14:00","2024-12-17 14:00","연속"]
[61,"강원","태백","태백삼척GP#1 T/L","154kV 태백S/S #2M.Tr 증설공사","#2M.Tr 최초가압","2024-12-16 14:00","2024-12-18 14:00","2024-12-16 14:00","2024-12-18 14:00","연속"]
[62,"강원","태백","태백S/S #65 BUS","154kV 태백S/S #2M.Tr 증설공사","#2M.Tr 최초가압","2024-12-17 14:00","2024-12-18 14:00","2024-12-17 14:00","2024-12-18 14:00","연속"]
[63,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-12-11 14:00","2024-12-18 18:00","취소","취소","연속"]
[64,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2024-12-03 14:00","2024-12-11 14:00","취소","취소","연속"]
[65,"충북","청주","남청주S/S SEC CB 62610","2024~2025년 청주전력지사 변전협력회사 공사","154kV GIS 보통점검","2024-12-02 10:00","2024-12-02 18:00","2024-12-02 10:00","2024-12-02 18:00","연속"]
[66,"충북","청주","남청주청주#2 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 남청주-청주#2,#4T/L(아킹혼, 폴리머지지애자 설치) 1. 내용 : 아킹혼, 폴리머지지애자 설치 2. 구간 : 남청주S/S~청주S/S","2024-12-02 08:00","2024-12-13 18:00","취소","취소","매일"]
[67,"충북","청주","남청주청주#4 T/L","2024~2025년 송전정비 협력회사 총액공사","154kV 남청주-청주#2,#4T/L(아킹혼, 폴리머지지애자 설치) 1. 내용 : 아킹혼, 폴리머지지애자 설치 2. 구간 : 남청주S/S~청주S/S","2024-12-02 08:00","2024-12-13 18:00","취소","취소","매일"]
[68,"충북","청주","오송북청주#2 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","No.37(4회선 철탑) 충전부 접촉 우려로 안전이격상 154kV 송전선로 휴전 - 전력선 교체 작업 구간 : No.32 ~ 37","2024-12-02 07:00","2024-12-06 18:00","취소","취소","매일"]
[69,"충북","청주","오송북청주#1 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","No.37(4회선 철탑) 충전부 접촉 우려로 안전이격상 154kV 송전선로 휴전 - 전력선 교체 작업 구간 : No.32 ~ 37","2024-12-02 07:00","2024-12-06 18:00","취소","취소","매일"]
[70,"대전세종충남","대전","금산무주#2 T/L","154kV 금산S/S #3M.Tr 교체공사","154kV #3M.Tr 1차 모선 교체 관련 안전이격 휴전","2024-12-03 17:00","2024-12-03 21:00","2024-12-03 17:00","2024-12-03 21:00","연속"]
[71,"대전세종충남","대전","팔봉두마#2 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","선종교체 구간 내 철탑 안전이격공사(3기)","2024-12-02 07:00","2024-12-03 18:00","2024-12-02 07:00","2024-12-03 18:00","연속"]
[72,"대전세종충남","대전","신계룡두마#2 T/L","[송전취소시][가압O]두마S/S 신계룡-두마#2T/L CB 부동작시험","[송전취소시][가압O]두마S/S 신계룡-두마#2T/L CB 부동작시험 -송전 신계룡-두마#2T/L 휴전취소 시 해당일에 작업예정","2024-12-30 09:00","2024-12-30 11:00","2024-12-30 09:00","2024-12-30 11:00","연속"]
[73,"대전세종충남","대전","팔봉두마#1 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","선종교체 구간 내 철탑 안전이격공사(3기)","2024-12-04 07:00","2024-12-10 18:00","2024-12-04 07:00","2024-12-10 18:00","연속"]
[74,"대전세종충남","대전","팔봉두마#2 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","선종교체 구간 내 철탑 안전이격공사(3기)","2024-12-11 07:00","2024-12-13 18:00","2024-12-11 07:00","2024-12-13 18:00","연속"]
[75,"대전세종충남","대전","신계룡S/S SEC CB 60610","[즉시가압O]신계룡S/S 154kV 60-61 BUS SEC 하자점검","[즉시가압O]신계룡S/S 154kV 60-61 BUS SEC 하자점검","2024-12-04 09:00","2024-12-04 14:00","2024-12-04 09:00","2024-12-04 14:00","연속"]
[76,"대전세종충남","대전","신계룡S/S SEC CB 65660","[즉시가압O]신계룡S/S 154kV 65-66 GIS 하자점검","[즉시가압O]신계룡S/S 154kV 65-66 GIS 하자점검","2024-12-05 09:00","2024-12-05 18:00","2024-12-05 09:00","2024-12-05 18:00","연속"]
[77,"대전세종충남","대전","신계룡S/S CB 6100","[즉시가압O]신계룡S/S 154kV 6100 GIS 하자점검","[즉시가압O]신계룡S/S 154kV 6100 GIS 하자점검","2024-12-04 14:00","2024-12-04 18:00","2024-12-04 14:00","2024-12-04 18:00","연속"]
[78,"대전세종충남","대전","남대전신흥#2 T/L","[즉시가압O]신흥S/S 154kV 남대전-신흥#2T/L CB 부동작 시험","[즉시가압O]신흥S/S 154kV 남대전-신흥#2T/L GIS 차단기 부동작 시험","2024-12-09 09:00","2024-12-09 12:00","취소","취소","연속"]
[79,"대전세종충남","대전","은진함열#2 T/L","[송전취소시]은진S/S 154kV 은진-함열#2T/L GIS 보통점검","[송전취소시]은진S/S 154kV 은진-함열#2T/L GIS 보통점검 - 송전작업 및 변전정비 보호반대체 작업 취소대비 당일 작업 신청","2024-12-17 08:00","2024-12-17 17:00","취소","취소","연속"]
[80,"대전세종충남","대전","은진함열#1 T/L","[송전취소시]은진S/S 154kV 은진-함열#1T/L GIS 보통점검","[송전취소시]은진S/S 154kV 은진-함열#1T/L GIS 보통점검 -송전휴전 및 변전정비 보호반대체 작업 취소대비 당일 휴전작업 신청","2024-12-16 15:00","2024-12-16 21:00","취소","취소","연속"]
[81,"대전세종충남","대전","은진함열#2 T/L","[송전][즉시가압O]신옥천-청양등8개T/L추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","2024-12-17 08:00","2024-12-27 17:00","취소","취소","매일"]
[82,"대전세종충남","대전","신옥천추부#2 T/L","[송전][즉시가압O]신옥천-청양등8개T/L추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","2024-12-04 08:00","2024-12-12 13:00","취소","취소","매일"]
[83,"대전세종충남","대전","추부금산#1 T/L","[송전][즉시가압O]신옥천-청양등8개T/L추락방지설치공사","[송전][주말작업제외][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","2024-12-05 08:00","2024-12-13 13:00","취소","취소","매일"]
[84,"대전세종충남","서산","서산태안#1 T/L","'24~'25년 서산전력지사 송전협력회사 공사","154kV 서산-대산T/L 항공구 설치공사 No.9~10, 11~12(2경간) *즉시가압가능(20분이내) *11월 휴전 승인시 취소 요청 *154kV 서산-대산T/L 병가선로, 154kV 서산-대산T/L 휴전 미승인시 휴전 취소 요청","2024-12-07 05:00","2024-12-08 11:00","취소","취소","매일"]
[85,"대전세종충남","서산","서산대산 T/L","'24~'25년 서산전력지사 송전협력회사 공사","154kV 서산-대산T/L 항공구 설치공사 No.9~10, 11~12(2경간) *즉시가압가능(20분이내) *11월 휴전 승인시 취소 요청 *154kV 서산-태안#1T/L 병가선로, 154kV 서산-태안#1T/L 휴전 미승인시 휴전 취소 요청","2024-12-07 05:00","2024-12-08 11:00","취소","취소","매일"]
[86,"대전세종충남","서산","서산대산#4 T/L","'24~'25년도 서산전력지사 송전협력회사 공사","154kV 서산-대산#4T/L 항공장애표시구 설치공사 No.3~4(1경간) *즉시가압가능(20분이내) *주말작업 없음 *11월 휴전 승인시 취소 요청","2024-12-12 08:00","2024-12-13 18:00","취소","취소","매일"]
[87,"대전세종충남","서산","신당진당진#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","(11월 휴전취소시)수평 추락방지장치 설치공사 (No.1~5,14~35) , 즉시가압(20분 이내) 가능","2024-12-10 08:00","2024-12-11 18:00","취소","취소","매일"]
[88,"대전세종충남","서산","신당진서산#2 T/L","24년 서산P/O 변전협력회사 총액공사","(11월 휴전 취소시) (즉시가압 가능) 신당진S/S 154kV 신당진-서산#2T/L GIS 하자점검 (병행) 서산S/S 154kV 신당진-서산#2T/L GIS 보통점검 (병행) 신당진S/S 신당진-서산#2T/L CVT 대체 (병행) 서산S/S 154kV 신당진-서산#2T/L LA 보통점검 (송전병행) 154kV 신당진-서산#2T/L 수평 추락방지","2024-12-05 09:30","2024-12-05 18:00","취소","취소","연속"]
[89,"대전세종충남","서산","신당진당진#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","(11월 휴전취소시)수평 추락방지장치 설치공사 (No.1~5,14~35) , 즉시가압(20분 이내) 가능, 주말작업 없음","2024-12-06 08:00","2024-12-09 18:00","취소","취소","매일"]
[90,"대전세종충남","서산","서산태안#2 T/L","(즉시가압가능)태안S/S 154kV 차단기 조작시험","(즉시가압가능)태안S/S태안S/S 서산-태안#2T/L 637 CB 조작시험","2024-12-20 18:00","2024-12-20 22:00","2024-12-20 18:00","2024-12-20 22:00","연속"]
[91,"대전세종충남","서산","태안T/P 이원호 수상태양T/L CB","'24년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S 154kV 이원호 수상태양광 6333 GIS 하자점검","2024-12-03 09:30","2024-12-03 18:00","2024-12-03 09:30","2024-12-03 18:00","연속"]
[92,"대전세종충남","세종","세종서세종#2 T/L","[변전]'24년 세종P/O 154kV GIS 정밀점검공사(11월 취소시)","○154kV GIS 정밀점검공사 -즉시가압 불가","2024-12-12 09:00","2024-12-14 18:00","취소","취소","연속"]
[93,"대전세종충남","세종","세종서세종#1 T/L","[변전]'24년 세종P/O 154kV GIS 정밀점검공사(11월 취소시)","○154kV GIS 정밀점검공사 -PNL 43PDA 교체 병행 -즉시가압 불가","2024-12-09 09:00","2024-12-11 18:00","취소","취소","연속"]
[94,"대전세종충남","세종","조치원전의#2 T/L","[주말작업O][즉시가압X] 154kV 조치원-전의T/L 안전이격확보 공사","[주말작업O][즉시가압X] 154kV 조치원-전의T/L 안전이격확보 공사 - No.12~17","2024-12-01 07:00","2024-12-20 18:00","취소","취소","연속"]
[95,"대전세종충남","세종","조치원전의#1 T/L","[11월 휴전 취소시] 154kV 조치원-전의T/L 안전이격확보공사","[즉시가압X][주말작업O] 154kV 조치원-전의T/L 안전이격확보공사","2024-12-05 09:00","2024-12-13 18:00","취소","취소","연속"]
[96,"대전세종충남","세종","조치원전의#1 T/L","[주말작업O][즉시가압X] 154kV 조치원-전의T/L 안전이격확보 공사","[주말작업O][즉시가압X] 154kV 조치원-전의T/L 안전이격확보 공사 - No.12~17","2024-12-21 07:00","2024-12-26 18:00","취소","취소","연속"]
[97,"대전세종충남","직할","덕진대화#2 T/L","(11월 취소시)덕진,대화S/S 덕진-대화#2T/L 보호반 대체공사","O 덕진,대화S/S 덕진-대화#2T/L 송전선로 보호반 대체","2024-12-14 09:00","2024-12-16 18:00","취소","취소","연속"]
[98,"대전세종충남","직할","둔곡송강#2 T/L","154kV 둔곡-송강T/L 지장수목 전지 및 벌채","154kV 둔곡-송강T/L 지장수목 전지 및 벌채","2024-12-11 08:00","2024-12-11 18:00","취소","취소","연속"]
[99,"대전세종충남","직할","둔곡송강#1 T/L","154kV 둔곡-송강T/L 지장수목 전지 및 벌채","154kV 둔곡-송강T/L 지장수목 전지 및 벌채","2024-12-09 08:00","2024-12-10 18:00","취소","취소","매일"]
[100,"대전세종충남","직할","송강신일#2 T/L","(11월 취소시)송강,신일S/S 송강-신일#2T/L 보호반 대체공사","송강,신일S/S 송강-신일#2T/L 송전선로 보호반 대체","2024-12-07 08:00","2024-12-08 18:00","취소","취소","연속"]
[101,"대전세종충남","직할","부강신탄진 T/L","154kV 신탄진S/S 미래화공사(GIS로 인출변경)","154kV 신탄진S/S 미래화공사(GIS로 인출변경) - 송전정비팀 동대전신탄진#1,2T/L 기존계획대로 11/29 종료 시 부강신탄진T/L 인출변경작업 12/2 시행예정","2024-12-02 09:00","2024-12-02 18:00","취소","취소","연속"]
[102,"대전세종충남","직할","신탄진대청HP T/L","154kV 신탄진S/S 미래화공사(GIS로 인출변경)","154kV 신탄진S/S 미래화공사(GIS로 인출변경) - 송전정비팀 동대전신탄진#1,2T/L 기존계획대로 11/29 종료 시 신탄진대청HPT/L 인출변경작업 12/3~4 시행예정","2024-12-03 09:00","2024-12-04 18:00","취소","취소","연속"]
[103,"대전세종충남","직할","동대전신탄진#1 T/L","154kV 신탄진S/S 미래화공사","#3M.Tr 인출변경 관련 상확인 및 무부하가압","2024-12-19 14:00","2024-12-20 14:00","2024-12-19 14:00","2024-12-20 14:00","연속"]
[104,"대전세종충남","천안","불당서천안#1 T/L","[11월취소시] 154kV 대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2024-12-09 09:00","2024-12-12 18:00","2024-12-09 09:00","2024-12-12 18:00","연속"]
[105,"대전세종충남","천안","불당서천안#2 T/L","[송전] 154kV 대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2024-12-02 09:00","2024-12-05 18:00","2024-12-02 09:00","2024-12-05 18:00","연속"]
[106,"대전세종충남","천안","신온양석곡#1 T/L","신온양, 석곡S/S 154kV 신온양-석곡#1, 2T/L 보호반 성능개선","(즉시가압가능)신온양, 석곡S/S 154kV 신온양-석곡#1, 2T/L 보호반 성능개선","2024-12-09 09:00","2024-12-09 18:00","취소","취소","연속"]
[107,"대전세종충남","천안","신온양석곡#2 T/L","신온양, 석곡S/S 154kV 신온양-석곡#1, 2T/L 보호반 성능개선","(즉시가압불가)신온양, 석곡S/S 154kV 신온양-석곡#1, 2T/L 보호반 성능개선","2024-12-10 09:00","2024-12-10 18:00","취소","취소","연속"]
[108,"대전세종충남","천안","신탕정S/S CB 6200","신탕정S/S 154kV BUS TIE 6200 GIS 보통점검","(즉시가압가능)신탕정S/S 154kV BUS TIE 6200 GIS 보통점검","2024-12-03 09:00","2024-12-03 18:00","2024-12-03 09:00","2024-12-03 18:00","연속"]
[109,"대전세종충남","천안","신탕정S/S CB 6100","신탕정S/S 154kV #60-65 모선보호반 대체","(즉시가압불가)신탕정S/S 154kV #60-65 모선보호반 대체","2024-12-09 09:00","2024-12-13 18:00","취소","취소","연속"]
[110,"대전세종충남","천안","신탕정S/S SEC CB 60610","신탕정S/S 154kV #60-65 모선보호반 대체","(즉시가압불가)신탕정S/S 154kV #60-65 모선보호반 대체","2024-12-09 09:00","2024-12-13 18:00","취소","취소","연속"]
[111,"대전세종충남","천안","신탕정S/S SEC CB 65660","신탕정S/S 154kV #60-65 모선보호반 대체","(즉시가압불가)신탕정S/S 154kV #60-65 모선보호반 대체","2024-12-09 09:00","2024-12-13 18:00","취소","취소","연속"]
[112,"대전세종충남","천안","아산온양#1 T/L","[11월취소시][즉시가압O]항공장애표시구 설치공사","[11월취소시][즉시가압O] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-12-15 07:00","2024-12-15 17:00","취소","취소","연속"]
[113,"대전세종충남","천안","아산합덕#2 T/L","아산S/S 154kV 아산-합덕#2T/L GIS 하자점검","(즉시가압가능)아산S/S 154kV 아산-합덕#2T/L GIS 하자점검","2024-12-13 09:00","2024-12-13 18:00","취소","취소","연속"]
[114,"대전세종충남","천안","아산S/S SEC CB 65660","아산S/S 154kV BUS SEC 65-66 GIS 불량 PD센서 교체","(즉시가압불가)아산S/S 154kV BUS SEC 65-66 GIS 불량 PD센서 교체","2024-12-18 09:00","2024-12-19 18:00","취소","취소","연속"]
[115,"대전세종충남","천안","아산S/S #66 BUS","아산S/S 154kV BUS SEC 65-66 GIS 불량 PD센서 교체","(즉시가압불가)아산S/S 154kV BUS SEC 65-66 GIS 불량 PD센서 교체","2024-12-18 09:00","2024-12-19 18:00","취소","취소","연속"]
[116,"대전세종충남","천안","아산합덕#2 T/L","(즉시가압가능)항공구 설치공사","(즉시가압가능)항공구 설치공사","2024-12-04 07:00","2024-12-04 18:00","2024-12-04 07:00","2024-12-04 18:00","연속"]
[117,"대전세종충남","천안","아산S/S #65 BUS","아산S/S 154kV 아산-합덕#1T/L GIS 불량 PD센서 보수","(즉시가압불가)아산S/S 154kV 아산-합덕#1T/L GIS 불량 PD센서 보수","2024-12-16 09:00","2024-12-17 18:00","취소","취소","연속"]
[118,"대전세종충남","천안","아산온양#2 T/L","[11월취소시][즉시가압O]항공장애표시구 설치공사","[11월취소시][즉시가압O] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-12-22 07:00","2024-12-22 17:00","취소","취소","연속"]
[119,"대전세종충남","천안","아산온양#1 T/L","[11월취소시][즉시가압O]항공장애표시구 설치공사","[11월취소시][즉시가압가능] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-12-01 07:00","2024-12-01 17:00","취소","취소","연속"]
[120,"대전세종충남","천안","아산예산#2 T/L","[11월취소시][즉시가압O]항공장애표시구 설치공사","[11월취소시][즉시가압O] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-12-01 07:00","2024-12-01 17:00","취소","취소","연속"]
[121,"대전세종충남","천안","아산온양#2 T/L","[11월취소시][즉시가압O]항공장애표시구 설치공사","[11월취소시][즉시가압가능] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단) [병행] 추락방지장치 설치 No.1~57 [병행] 고정형폴리머 점퍼지지애자 교체 6 [병행] S/T 추락방지장치 설치","2024-12-08 07:00","2024-12-08 17:00","취소","취소","연속"]
[122,"대전세종충남","천안","아산예산#1 T/L","[11월취소시][즉시가압O]항공장애표시구 설치공사","[11월취소시][즉시가압O] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-12-08 07:00","2024-12-08 17:00","취소","취소","연속"]
[123,"대전세종충남","천안","아산S/S SEC CB 60610","아산S/S 154kV BUS SEC 60-61 GIS 하자점검","(즉시가압가능)아산S/S 154kV BUS SEC 60-61 GIS 하자점검","2024-12-24 09:00","2024-12-24 18:00","취소","취소","연속"]
[124,"대전세종충남","천안","아산합덕#1 T/L","아산S/S 154kV 아산-합덕#1T/L GIS 불량 PD센서 교체","(즉시가압불가)아산S/S 154kV 아산-합덕#1T/L GIS 불량 PD센서 교체","2024-12-16 09:00","2024-12-17 18:00","취소","취소","연속"]
[125,"대전세종충남","천안","장재천안#1 T/L","24년 천안P/O GIS 정밀 및 보통점검공사","(11월 취소시)(즉시가압가능)(보호반교체휴전취소시) 천안, 장재S/S 154kV 장재-천안#1T/L GIS 보통점검","2024-12-07 09:00","2024-12-08 18:00","취소","취소","매일"]
[126,"대전세종충남","천안","장재천안#2 T/L","24년 천안P/O GIS 정밀 및 보통점검공사","(11월 취소시)(즉시가압가능)(보호반교체휴전취소시) 천안, 장재S/S 154kV 장재-천안#2T/L GIS 보통점검","2024-12-14 09:00","2024-12-15 18:00","취소","취소","매일"]
[127,"대전세종충남","천안","풍세장재#1 T/L","[즉시가압가능]154kV 풍세-장재T/L 항공구 설치공사","[즉시가압가능]154kV 풍세-장재T/L No. 18 ~ 23 항공구 설치","2024-12-02 07:00","2024-12-02 18:00","취소","취소","연속"]
[128,"대전세종충남","천안","풍세장재#2 T/L","[즉시가압가능]154kV 풍세-장재T/L 항공구 설치공사","[즉시가압가능]154kV 풍세-장재T/L No. 18 ~ 23 항공구 설치","2024-12-03 07:00","2024-12-03 18:00","취소","취소","연속"]
[129,"대전세종충남","천안","온양풍세#1 T/L","[11월취소시][즉시가압O]항공장애표시구 설치공사","[11월취소시][즉시가압가능] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-12-15 07:00","2024-12-15 17:00","취소","취소","연속"]
[130,"대전세종충남","천안","온양풍세#2 T/L","[11월취소시][즉시가압O]항공장애표시구 설치공사","[11월취소시][즉시가압가능] 154kV 아산-온양T/L No.2~3 등 15경간 항공구 설치 [4회선 병가철탑] No.2~14아산온양(상단)아산예산(하단), No.51~56아산온양(상단)온양풍세(하단)","2024-12-22 07:00","2024-12-22 17:00","취소","취소","연속"]
[131,"대전세종충남","청양","옥산부여#2 T/L","청양P/O 전문 발주공사(옥부#2 정밀)","청양P/O 변전전문업체 발주공사 - 옥산S/S 옥산-부여#2T/L GIS 정밀점검 - 즉시가압 불가","2024-12-18 14:00","2024-12-20 18:00","취소","취소","연속"]
[132,"대전세종충남","청양","신서천옥산#2 T/L","청양P/O 전문 공사(옥산 옥서2 정밀)","청양P/O 변전전문업체 발주공사 - 옥산S/S 옥산-서천#2T/L GIS 627 정밀점검 - 즉시가압 불가","2024-12-02 09:00","2024-12-04 14:00","취소","취소","연속"]
[133,"대전세종충남","청양","옥산장항#2 T/L","청양P/O 전문 공사(옥산 옥장#2 정밀)","청양P/O 변전전문업체 발주공사 - 옥산S/S 옥산-장항#2T/L GIS 정밀점검 - 즉시가압 불가","2024-12-04 14:00","2024-12-06 18:00","취소","취소","연속"]
[134,"대전세종충남","청양","옥산부여#1 T/L","청양P/O 전문 발주공사(옥부#1 정밀)","청양P/O 변전전문업체 발주공사 - 옥산S/S 옥산-부여#1T/L GIS 정밀점검 - 즉시가압 불가","2024-12-16 09:00","2024-12-18 14:00","취소","취소","연속"]
[135,"대전세종충남","청양","은하홍성#2 T/L","청양P/O 변전협력 총액공사(은홍#2 보호반 대체)","청양P/O 변전협력 총액공사(은하-홍성#2 보호반 대체) - 즉시가압 불가","2024-12-09 09:00","2024-12-11 18:00","취소","취소","연속"]
[136,"전북","군산","군공군산CC#1 T/L","군산PO 154kV이상 차단기 보통점검","군산PO 154kV이상 차단기 보통점검","2024-12-19 09:00","2024-12-19 18:00","2024-12-19 09:00","2024-12-19 18:00","연속"]
[137,"전북","군산","군공군산CC#2 T/L","군산PO 154kV이상 차단기 보통점검","군산PO 154kV이상 차단기 보통점검","2024-12-20 09:00","2024-12-20 18:00","2024-12-20 09:00","2024-12-20 18:00","연속"]
[138,"전북","군산","군산이리#1 T/L","군산PO 154kV이상 차단기 점검공사","군산PO 154kV이상 차단기 점검공사","2024-12-26 14:00","2024-12-26 18:00","2024-12-26 14:00","2024-12-26 18:00","연속"]
[139,"전북","군산","군산S/S CB 6100","군산PO 154kV이상 차단기 점검공사","군산PO 154kV이상 차단기 점검공사","2024-12-24 09:00","2024-12-24 14:00","2024-12-24 09:00","2024-12-24 14:00","연속"]
[140,"전북","군산","군산서군산#1 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2024-12-09 09:00","2024-12-10 18:00","취소","취소","연속"]
[141,"전북","군산","군산이리#2 T/L","군산P/O 154kV이상 차단기 점검공사","657 차단기 보통점검","2024-12-27 09:00","2024-12-27 14:00","2024-12-27 09:00","2024-12-27 14:00","연속"]
[142,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2024-12-11 09:00","2024-12-12 18:00","취소","취소","연속"]
[143,"전북","군산","군산S/S SEC CB 60610","군산P/O 154kV이상 차단기 점검공사","60-61-0 차단기 보통점검","2024-12-23 09:00","2024-12-23 14:00","취소","취소","연속"]
[144,"전북","군산","군산S/S SEC CB 65660","군산P/O 154kV이상 차단기 점검공사","65-66-0 차단기 보통점검","2024-12-23 14:00","2024-12-23 18:00","취소","취소","연속"]
[145,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사","효성제 170kV GIS 차단기 주접점 교체공사","2024-12-16 09:00","2024-12-18 18:00","2024-12-16 09:00","2024-12-18 18:00","연속"]
[146,"전북","군산","군산동군산#1 T/L","군산P/O 170kV GIS 정밀점검공사(무부하 가압용)","동군산S/S 6333 차단기 정밀점검","2024-12-17 17:00","2024-12-17 18:00","2024-12-17 17:00","2024-12-17 18:00","연속"]
[147,"전북","군산","비응군장#2 T/L","군산P/O 154kV 이상 차단기 점검공사","군산P/O 154kV 이상 차단기 점검공사","2024-12-10 09:00","2024-12-10 18:00","2024-12-10 09:00","2024-12-10 18:00","연속"]
[148,"전북","군산","비응군장#1 T/L","군산P/O 154kV 이상 차단기 점검공사","군산P/O 154kV 이상 차단기 점검공사","2024-12-09 09:00","2024-12-09 18:00","2024-12-09 09:00","2024-12-09 18:00","연속"]
[149,"전북","군산","영등낭산#2 T/L","154kV 영등S/S SA혼용운영시스템 설치공사","영등S/S SA화 관련 변전설비 제어케이블 이설 시행 [현장설비 ↔ RTU] → [현장설비 ↔ 현장정보처리반]","2024-12-16 09:00","2024-12-16 18:00","취소","취소","연속"]
[150,"전북","군산","영등S/S CB 6100","154kV 영등S/S SA혼용운영시스템 설치공사","영등S/S SA화 관련 변전설비 제어케이블 이설 시행 [현장설비 ↔ RTU] → [현장설비 ↔ 현장정보처리반]","2024-12-23 09:00","2024-12-23 18:00","취소","취소","연속"]
[151,"전북","군산","영등팔봉#2 T/L","154kV 영등S/S SA혼용운영시스템 설치공사","영등S/S SA화 관련 변전설비 제어케이블 이설 시행 [현장설비 ↔ RTU] → [현장설비 ↔ 현장정보처리반]","2024-12-12 09:00","2024-12-12 18:00","취소","취소","연속"]
[152,"전북","군산","영등팔봉#1 T/L","154kV 영등S/S SA혼용운영시스템 설치공사","영등S/S SA화 관련 변전설비 제어케이블 이설 시행 [현장설비 ↔ RTU] → [현장설비 ↔ 현장정보처리반]","2024-12-11 09:00","2024-12-11 18:00","취소","취소","연속"]
[153,"전북","군산","영등낭산#1 T/L","154kV 영등S/S SA혼용운영시스템 설치공사","영등S/S SA화 관련 변전설비 제어케이블 이설 시행 [현장설비 ↔ RTU] → [현장설비 ↔ 현장정보처리반]","2024-12-13 09:00","2024-12-13 18:00","취소","취소","연속"]
[154,"전북","군산","군산영등#1 T/L","154kV 영등S/S SA혼용운영시스템 설치공사","영등S/S SA화 관련 변전설비 제어케이블 이설 시행 [현장설비 ↔ RTU] → [현장설비 ↔ 현장정보처리반]","2024-12-17 09:00","2024-12-17 18:00","취소","취소","연속"]
[155,"전북","군산","팔봉두마#2 T/L","154kV 팔봉두마T/L No.14~17 일부구간지중화 C/T설치공사","지중화 : No.14~17 약 400m 전선교체 : 1.524C-km 철탑설치철거 : 15,16호","2024-12-24 08:00","2024-12-28 18:00","2024-12-24 08:00","2024-12-28 18:00","연속"]
[156,"전북","군산","팔봉왕궁#1 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2024-12-23 09:00","2024-12-24 18:00","취소","취소","연속"]
[157,"전북","군산","팔봉왕궁#2 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2024-12-26 09:00","2024-12-27 18:00","취소","취소","연속"]
[158,"전북","군산","팔봉두마#1 T/L","154kV 팔봉두마T/L No.14~17 일부구간지중화 C/T설치공사","지중화 : No.14~17 약 400m 전선교체 : 1.524C-km 철탑설치철거 : 15,16호","2024-12-19 08:00","2024-12-23 18:00","2024-12-19 08:00","2024-12-23 18:00","연속"]
[159,"전북","군산","은진함열#1 T/L","군산P/O 154kV이상 차단기 점검공사","군산P/O 154kV이상 차단기 점검공사","2024-12-27 09:00","2024-12-27 14:00","취소","취소","연속"]
[160,"전북","김제","정공정주#1 T/L","154kV 정공-정주T/L 용량증대 전선교체공사(No.13~정주S/S)","- 공사구간 : 154kV 정공-정주T/L No.13~정주S/S)(중복) - 전력선 교체 : 10.828C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, SB댐퍼 등]","2024-12-01 07:00","2024-12-15 17:00","2024-12-01 07:00","2024-12-15 17:00","연속"]
[161,"전북","김제","정공칠보HP T/L","154kV 정공-정주T/L 용량증대 전선교체공사(No.13~정주S/S)","- 공사구간 : 154kV 정공-정주T/L No.13~정주S/S)(중복) - 전력선 교체 : 10.828C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, SB댐퍼 등]","2024-12-12 07:00","2024-12-15 17:00","2024-12-12 07:00","2024-12-15 17:00","연속"]
[162,"전북","김제","정공정주#2 T/L","154kV 정공-정주T/L 용량증대 전선교체공사(No.13~정주S/S)","- 공사구간 : 154kV 정공-정주T/L No.13~정주S/S)(중복) - 전력선 교체 : 10.828C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, SB댐퍼 등]","2024-12-16 07:00","2024-12-30 17:00","2024-12-16 07:00","2024-12-30 17:00","연속"]
[163,"전북","김제","정공담양 T/L","154kV 정공-정주T/L 용량증대 전선교체공사(No.13~정주S/S)","- 공사구간 : 154kV 정공-정주T/L No.13~정주S/S)(중복) - 전력선 교체 : 10.828C-km [ACSR 330㎟ × S → ASCC/TW 430㎟ × S] - 금구류 교체 : 신전선용 금구류 적용 [압축인류클램프, SB댐퍼 등]","2024-12-16 07:00","2024-12-19 17:00","2024-12-16 07:00","2024-12-19 17:00","연속"]
[164,"전북","김제","정주동부안#1 T/L","정주S/S 정주-동부안#1T/L GIS 정밀점검(12.09~10, 연속)","정주S/S 정주-동부안#1T/L GIS 정밀점검(12.09~10, 연속)","2024-12-23 09:00","2024-12-24 18:00","취소","취소","연속"]
[165,"전북","김제","정주동부안#2 T/L","정주S/S 정주-동부안#2T/L GIS 정밀점검(12.11~12, 연속)","정주S/S 정주-동부안#2T/L GIS 정밀점검(12.11~12, 연속)","2024-12-26 09:00","2024-12-27 18:00","취소","취소","연속"]
[166,"전북","직할","왕궁봉동#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-12-02 08:00","2024-12-02 18:00","2024-12-02 08:00","2024-12-02 18:00","매일"]
[167,"전북","직할","북전주봉동#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-12-20 08:00","2024-12-20 18:00","2024-12-20 08:00","2024-12-20 18:00","매일"]
[168,"전북","직할","왕궁봉동#2 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-12-03 08:00","2024-12-03 18:00","2024-12-03 08:00","2024-12-03 18:00","매일"]
[169,"전북","직할","북전주봉동#2 T/L","북전주변전소 북전주-봉동#2TL GIS 정밀점검공사","북전주변전소 북전주-봉동#2TL GIS 정밀점검공사","2024-12-16 09:00","2024-12-19 18:00","2024-12-16 09:00","2024-12-19 18:00","연속"]
[170,"전북","직할","북전주진안 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사","○ 154kV 북전주-진안T/L No.1~175 수평 추락방지시설 설치","2024-12-03 07:00","2024-12-11 17:00","2024-12-03 07:00","2024-12-11 17:00","매일"]
[171,"전북","직할","신남원S/S #6 EM.Tr CB","ESS EM.Tr 96TC IED 업데이트","작업사유 : 전압이상 경보 설정값 변경 작업내용 : 제작사 IED 업데이트 후 계통시험팀 시험 소요시간 : EM.Tr당 1시간(즉시 가압가능). 끝.","2024-12-03 15:00","2024-12-03 16:00","2024-12-03 15:00","2024-12-03 16:00","연속"]
[172,"전북","직할","신남원S/S #5 EM.Tr CB","ESS EM.Tr 96TC IED 업데이트","작업사유 : 전압이상 경보 설정값 변경 작업내용 : 제작사 IED 업데이트 후 계통시험팀 시험 소요시간 : EM.Tr당 1시간(즉시 가압가능). 끝.","2024-12-03 14:00","2024-12-03 15:00","2024-12-03 14:00","2024-12-03 15:00","연속"]
[173,"전북","직할","신남원S/S #4 EM.Tr CB","ESS EM.Tr 96TC IED 업데이트","작업사유 : 전압이상 경보 설정값 변경 작업내용 : 제작사 IED 업데이트 후 계통시험팀 시험 소요시간 : EM.Tr당 1시간(즉시 가압가능). 끝.","2024-12-03 13:00","2024-12-03 14:00","2024-12-03 13:00","2024-12-03 14:00","연속"]
[174,"전북","직할","신남원S/S #2 EM.Tr CB","ESS EM.Tr 96TC IED 업데이트","작업사유 : 전압이상 경보 설정값 변경 작업내용 : 제작사 IED 업데이트 후 계통시험팀 시험 소요시간 : EM.Tr당 1시간(즉시 가압가능). 끝.","2024-12-03 10:00","2024-12-03 11:00","2024-12-03 10:00","2024-12-03 11:00","연속"]
[175,"전북","직할","신남원S/S #1 EM.Tr CB","ESS EM.Tr 96TC IED 업데이트","작업사유 : 전압이상 경보 설정값 변경 작업내용 : 제작사 IED 업데이트 후 계통시험팀 시험 소요시간 : EM.Tr당 1시간(즉시 가압가능). 끝.","2024-12-03 09:00","2024-12-03 10:00","2024-12-03 09:00","2024-12-03 10:00","연속"]
[176,"전북","직할","신남원S/S #3 EM.Tr CB","ESS EM.Tr 96TC IED 업데이트","작업사유 : 전압이상 경보 설정값 변경 작업내용 : 제작사 IED 업데이트 후 계통시험팀 시험 소요시간 : EM.Tr당 1시간(즉시 가압가능). 끝.","2024-12-03 11:00","2024-12-03 12:00","2024-12-03 11:00","2024-12-03 12:00","연속"]
[177,"전북","직할","전주서곡#2 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-12-26 08:00","2024-12-27 18:00","2024-12-26 08:00","2024-12-27 18:00","매일"]
[178,"전북","직할","탄소전주#1 T/L","전주변전소 전주-탄소#1TL GIS 정밀점검공사","전주변전소 전주-탄소#1TL GIS 정밀점검공사","2024-12-19 09:00","2024-12-20 18:00","2024-12-19 09:00","2024-12-20 18:00","연속"]
[179,"전북","직할","전주서곡#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2024-12-23 08:00","2024-12-24 18:00","2024-12-23 08:00","2024-12-24 18:00","매일"]
[180,"전북","직할","진안장수#1 T/L","진안변전소 진안-장수#1TL GIS 정밀점검공사","진안변전소 진안-장수#1TL GIS 정밀점검공사","2024-12-02 09:00","2024-12-05 18:00","2024-12-02 09:00","2024-12-05 18:00","연속"]
[181,"전북","직할","진안장수#2 T/L","진안변전소 진안-장수#2TL GIS 정밀점검공사","진안변전소 진안-장수#2TL GIS 정밀점검공사","2024-12-09 09:00","2024-12-12 18:00","2024-12-09 09:00","2024-12-12 18:00","연속"]
[182,"광주전남","강진","남창 모선연계T/L CB","2024-2025년 강진전력지사 변전협력회사 공사","170kV GIS 하자점검(연내 남창-해남C/S #1, 2T/L 이설 시 시행)","2024-12-20 14:00","2024-12-20 18:00","2024-12-20 14:00","2024-12-20 18:00","연속"]
[183,"광주전남","강진","남창해남CS#1 T/L","154kV 남창S/S GIS화 공사","○ 남창-해남C/S #1,2T/L 인출변경","2024-12-18 09:00","2024-12-24 18:00","2024-12-18 09:00","2024-12-24 18:00","연속"]
[184,"광주전남","강진","남창해남CS#2 T/L","154kV 남창S/S GIS화 공사","○ 남창-해남C/S #1,2T/L 인출변경","2024-12-16 09:00","2024-12-18 18:00","2024-12-16 09:00","2024-12-18 18:00","연속"]
[185,"광주전남","강진","남창해남CS#2 T/L","2024-2025년 강진전력지사 변전협력회사 공사","LA 및 PT 점검","2024-12-03 14:00","2024-12-03 18:00","취소","취소","연속"]
[186,"광주전남","강진","남창해남CS#1 T/L","2024-2025년 강진전력지사 변전협력회사 공사","LA 및 PT 점검","2024-12-03 09:00","2024-12-03 14:00","취소","취소","연속"]
[187,"광주전남","강진","대불남악#1 T/L","2024-2025년 강진전력지사 변전협력회사 공사","(야간 작업 가능) 170kV GIS 하자점검","2024-12-17 09:00","2024-12-17 14:00","2024-12-17 09:00","2024-12-17 14:00","연속"]
[188,"광주전남","강진","신강진대불#2 T/L","2024년 하반기 강진전력지사 170kV GIS 정밀점검 공사(가칭)","(3일 휴전 불가 시 보통점검 가능) (보통점검 소요 시간 0.5일 / 야간 작업 가능) 170kV GIS 정밀점검(CB)","2024-12-11 14:00","2024-12-13 18:00","취소","취소","연속"]
[189,"광주전남","강진","대불삼호#2 T/L","'24년 강진전력지사 170kV 이상 GIS 보통점검 공사","(야간 작업, 즉시 가압 가능) 대불S/S 대불삼호#2T/L GIS 보통점검","2024-12-02 13:00","2024-12-02 18:00","2024-12-02 13:00","2024-12-02 18:00","연속"]
[190,"광주전남","강진","대불남악#2 T/L","2024-2025년 강진전력지사 변전협력회사 공사","(야간 작업 가능) 170kV GIS 하자점검","2024-12-17 14:00","2024-12-17 18:00","2024-12-17 14:00","2024-12-17 18:00","연속"]
[191,"광주전남","강진","대불삼호#1 T/L","2024년 하반기 강진전력지사 170kV GIS 정밀점검 공사(가칭)","(3일 휴전 불가 시 보통점검 가능) (보통점검 소요 시간 0.5일 / 야간 작업 가능) 170kV GIS 정밀점검(CB)","2024-12-18 09:00","2024-12-20 18:00","2024-12-18 09:00","2024-12-20 18:00","연속"]
[192,"광주전남","강진","신강진대불#1 T/L","2024년 하반기 강진전력지사 170kV GIS 정밀점검 공사(가칭)","(3일 휴전 불가 시 보통점검 가능) (보통점검 소요 시간 0.5일 / 야간 작업 가능) 170kV GIS 정밀점검(CB)","2024-12-09 09:00","2024-12-11 13:00","취소","취소","연속"]
[193,"광주전남","강진","장흥보성 T/L","24년 강진전력지사 170kV GIS 보통점검 공사","(야간 작업, 즉시 가압 가능) 보성S/S 장흥-보성T/L GIS 보통점검","2024-12-02 10:00","2024-12-02 17:00","취소","취소","연속"]
[194,"광주전남","강진","보성벌교 T/L","2024~2025년 강진전력지사 송전협력회사 공사","장흥-벌교T/L 정밀점검 적출사항 조치","2024-12-12 07:00","2024-12-13 18:00","2024-12-12 07:00","2024-12-13 18:00","매일"]
[195,"광주전남","강진","삼호화원#2 T/L","154kV 삼호-화원 지중T/L(복도체화) 건설공사","154kV XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2024-12-02 09:00","2024-12-27 18:00","취소","취소","연속"]
[196,"광주전남","강진","신강진해남#2 T/L","2024년 가공송전 순시점검 위탁공사","신강진-해남#2T/L 정밀점검","2024-12-16 08:00","2024-12-20 18:00","2024-12-16 08:00","2024-12-20 18:00","매일"]
[197,"광주전남","강진","신강진해남#2 T/L","'24년 하반기 강진전력지사 효성제 170kV GIS 개선","(아간 작업 가능) 170kV GIS 개선","2024-12-03 14:00","2024-12-03 18:00","취소","취소","연속"]
[198,"광주전남","강진","신강진대불#2 T/L","2024년 가공송전 순시점검 위탁공사","신강진-해남#1T/L 정밀점검 4회선 병가구간 휴전","2024-12-09 08:00","2024-12-10 18:00","2024-12-09 08:00","2024-12-10 18:00","매일"]
[199,"광주전남","강진","신강진대불#1 T/L","2024년 가공송전 순시점검 위탁공사","신강진-해남#2T/L 정밀점검 4회선 병가구간 휴전","2024-12-16 08:00","2024-12-17 18:00","2024-12-16 08:00","2024-12-17 18:00","매일"]
[200,"광주전남","강진","신강진해남#1 T/L","2024년 가공송전 순시점검 위탁공사","신강진-해남#1T/L 정밀점검","2024-12-09 08:00","2024-12-13 18:00","2024-12-09 08:00","2024-12-13 18:00","매일"]
[201,"광주전남","강진","장흥벌교 T/L","2024~2025년 강진전력지사 송전협력회사 공사","장흥-벌교T/L 정밀점검 적출사항 조치","2024-12-09 07:00","2024-12-11 18:00","2024-12-09 07:00","2024-12-11 18:00","매일"]
[202,"광주전남","강진","장흥보성 T/L","2024년 가공송전 순시점검 위탁공사","장흥-보성T/L 1~64호 정밀점검","2024-12-04 08:00","2024-12-06 18:00","2024-12-04 08:00","2024-12-06 18:00","매일"]
[203,"광주전남","강진","강진장흥#1 T/L","2024년 가공송전 순시점검 위탁공사","장흥-보성T/L 1~64호 정밀점검 4회선 구간 휴전","2024-12-04 08:00","2024-12-04 18:00","2024-12-04 08:00","2024-12-04 18:00","연속"]
[204,"광주전남","강진","강진장흥#2 T/L","2024-2025년 강진전력지사 변전협력회사 공사","LA 점검","2024-12-02 09:00","2024-12-02 18:00","2024-12-02 09:00","2024-12-02 18:00","연속"]
[205,"광주전남","강진","해남진도#1 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 해남-진도#1 T/L 1, 4~8, 16~74, 87~95, 102~104호 78기","2024-12-02 07:00","2024-12-11 18:00","취소","취소","매일"]
[206,"광주전남","강진","해남진도#1 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 해남-진도#1 T/L 1,4~8,16~74,87~95,102~104호 78기","2024-12-02 06:00","2024-12-11 18:00","취소","취소","매일"]
[207,"광주전남","강진","화원진도#2 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 화원-진도#2 T/L 40~78호호 39기","2024-12-16 06:00","2024-12-19 18:00","취소","취소","매일"]
[208,"광주전남","강진","진도S/S #2 BUS","'24년 강진전력지사 효성제 170kV GIS 개선 공사","진도S/S 효성제 #5M.Tr 1차 GIS 주접점 이탈 관련 차단부 교체 관련 무부하 가압 시 사용","2024-12-04 09:00","2024-12-05 18:00","2024-12-04 09:00","2024-12-05 18:00","연속"]
[209,"광주전남","강진","해남진도#2 T/L","'24년 강진전력지사 효성제 170kV GIS 개선 공사","진도S/S 효성제 #5M.Tr 1차 GIS 주접점 이탈 관련 차단부 교체 관련 무부하 가압","2024-12-04 09:00","2024-12-05 18:00","취소","취소","연속"]
[210,"광주전남","강진","화원진도#2 T/L","'24년 강진전력지사 효성제 170kV GIS 개선 공사","진도S/S 효성제 #5M.Tr 1차 GIS 주접점 이탈 관련 차단부 교체 관련 무부하 가압","2024-12-04 09:00","2024-12-05 18:00","취소","취소","연속"]
[211,"광주전남","강진","화원진도#2 T/L","22~23년 철탑 추락방지장치 설치공사","22~23년 철탑 추락방지장치 설치공사 공사대상 : 화원-진도#2 T/L 40~78호 39기","2024-12-12 07:00","2024-12-17 18:00","2024-12-12 07:00","2024-12-17 18:00","매일"]
[212,"광주전남","강진","해남진도#2 T/L","'24년 강진전력지사 효성제 170kV GIS 개선 공사","(야간작업 가능) 진도S/S 효성제 #5M.Tr 1차 GIS 주접점 이탈 관련 차단부 교체 관련 무부하 가압","2024-12-05 09:00","2024-12-05 18:00","취소","취소","연속"]
[213,"광주전남","강진","해남진도#1 T/L","'24년 하반기 강진전력지사 효성제 170kV GIS 개선","(야간작업 가능) 170kV GIS 개선","2024-12-04 10:00","2024-12-04 18:00","취소","취소","연속"]
[214,"광주전남","광주","남광주금천#2 T/L","2024년 광주전력 변전협력회사 총액공사","□작업명 : 남광주SS 남광주금천#2TL 보통점검","2024-12-16 09:00","2024-12-16 18:00","2024-12-16 09:00","2024-12-16 18:00","연속"]
[215,"광주전남","광주","담양김제 T/L","'24년 광주전력지사 변전협력회사 공사","담양S/S 담양-김제T/L LA 보통점검","2024-12-11 09:00","2024-12-11 18:00","취소","취소","연속"]
[216,"광주전남","광주","신광주계림#1 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 신광주-계림T/L 수평 추락방지장치 설치 No. 16~27.2(8기)","2024-12-03 07:00","2024-12-03 18:00","취소","취소","매일"]
[217,"광주전남","광주","신광주계림#2 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 신광주-계림T/L 수평 추락방지장치 설치 No. 16~27.2(8기)","2024-12-04 07:00","2024-12-04 18:00","취소","취소","매일"]
[218,"광주전남","광주","신광주일곡#2 T/L","2024~25년 광주전력지사 송전협력회사공사(추락방지)","154kV 신광주-일곡T/L 수평 추락방지장치 설치 No. 2,3,12~15(7기)","2024-12-02 07:00","2024-12-02 18:00","취소","취소","매일"]
[219,"광주전남","목포","안좌읍동 T/L CB","2024~2025년 목포전력지사 변전협력회사 공사","154kV GIS 하자점검","2024-12-05 09:00","2024-12-05 18:00","취소","취소","연속"]
[220,"광주전남","목포","엄다S/S #1 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","나주-엄다#1T/L, #2M.Tr 1차 GIS 교체작업","2024-12-18 09:00","2025-01-11 18:00","2024-12-18 09:00","2025-01-11 18:00","연속"]
[221,"광주전남","목포","나주엄다#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","나주-엄다#1T/L, #2M.Tr 1차 GIS 교체","2024-12-16 09:00","2025-01-24 18:00","2024-12-16 09:00","2025-01-24 18:00","연속"]
[222,"광주전남","목포","엄다목포#2 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)","154kV 나주-엄다T/L 피뢰기 설치 병가구간 휴전 및 154kV 엄다-목포T/L 피뢰기 설치","2024-12-12 08:00","2024-12-20 18:00","취소","취소","매일"]
[223,"광주전남","목포","나주엄다#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","154kV LA 보통점검","2024-12-09 09:00","2024-12-09 14:00","취소","취소","연속"]
[224,"광주전남","목포","나주엄다#1 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)","154kV 나주-엄다T/L 피뢰기 설치","2024-12-02 08:00","2024-12-18 18:00","취소","취소","매일"]
[225,"광주전남","목포","나주엄다#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","154kV LA 보통점검","2024-12-09 14:00","2024-12-09 18:00","취소","취소","연속"]
[226,"광주전남","목포","영광S/S 재원태양광T/L CB","2024~2025년 목포전력지사 변전협력회사 공사","GIS 보통점검","2024-12-23 09:00","2024-12-23 18:00","취소","취소","연속"]
[227,"광주전남","목포","고창영광 T/L","2024~2025년 목포전력지사 변전협력회사 공사","GIS 조작시험","2024-12-17 09:00","2024-12-17 18:00","취소","취소","연속"]
[228,"광주전남","목포","장성영광#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","GIS 조작시험","2024-12-16 09:00","2024-12-16 14:00","취소","취소","연속"]
[229,"광주전남","목포","장성영광#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","GIS 조작시험","2024-12-16 14:00","2024-12-16 18:00","취소","취소","연속"]
[230,"광주전남","목포","고창홍농 T/L","2024~2025년 목포전력지사 변전협력회사 공사","154kV LA 보통점검","2024-12-10 14:00","2024-12-10 18:00","취소","취소","연속"]
[231,"광주전남","순천","백운세풍#2 T/L","154kV 광양바이오매스발전소 접속설비 연계공사","154kV 백운-세풍- 황금개폐소 간 2파이 분기 접속설비 연계를 위한 공용송전망 Y분기 접속공사 및 시험","2024-12-02 09:00","2024-12-27 18:00","2024-12-02 09:00","2024-12-27 18:00","연속"]
[232,"광주전남","순천","순천율촌#2 T/L","345kV 광양-여수TPT/L 일부구간 지중화 공사","345kV - 154kV 선로 횡단에 따른 휴전 - 154kV 선로 작업 없음","2024-12-02 07:30","2024-12-06 18:00","2024-12-16 07:30","2024-12-20 18:00","연속"]
[233,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주T/L 지중화 연장공사(요청자 직접시행)","154kV 순천-승주T/L 지중화 연장공사(요청자 직접시행) ○ 요청자 : 그린산업개발 주식회사 ○ 시공사 : 주식회사 한백 ○ 감리사 : 더원엔지니어링 주식회사","2024-12-02 08:00","2024-12-12 18:00","취소","취소","연속"]
[234,"광주전남","순천","순천율촌#1 T/L","345kV 광양-여수TPT/L 일부구간 지중화 공사","345kV - 154kV 선로 횡단에 따른 휴전 - 154kV 선로 작업 없음","2024-12-02 07:30","2024-12-06 18:00","2024-12-16 07:30","2024-12-20 18:00","연속"]
[235,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주T/L 지중화 연장공사(요청자 직접시행)","154kV 순천-승주T/L 지중화 연장공사(요청자 직접시행) ○ 요청자 : 그린산업개발 주식회사 ○ 시공사 : 주식회사 한백 ○ 감리사 : 더원엔지니어링 주식회사","2024-12-13 08:00","2024-12-24 18:00","취소","취소","연속"]
[236,"광주전남","순천","호남TP여수TP#2 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 추락방지시설 설치","2024-12-13 07:00","2024-12-13 18:00","취소","취소","연속"]
[237,"광주전남","순천","여수TP화치#1 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 추락방지시설 설치","2024-12-13 07:00","2024-12-13 18:00","2024-12-13 07:00","2024-12-13 18:00","연속"]
[238,"광주전남","순천","여수TP여천#1 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-12-16 07:00","2024-12-17 18:00","취소","취소","매일"]
[239,"광주전남","순천","여수TP여천#2 T/L","154kV 여수TP-여천T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-12-18 07:00","2024-12-18 18:00","취소","취소","연속"]
[240,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-12-02 12:00","2024-12-02 16:00","취소","취소","연속"]
[241,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-12-02 07:00","2024-12-02 12:00","취소","취소","연속"]
[242,"광주전남","순천","율촌여수산단#1 T/L","율촌S/S 154kV 포스코퓨처엠T/L GIS 증설공사(즉시가압 가능)","1CCT 증설, 즉시가압 가능","2024-12-16 09:00","2024-12-20 18:00","2024-12-16 09:00","2024-12-20 18:00","연속"]
[243,"광주전남","순천","율촌화치#2 T/L","율촌S/S 154kV 포스코퓨처엠T/L GIS 증설공사(즉시가압 가능)","1CCT 증설, 즉시가압 가능","2024-12-13 09:00","2024-12-14 18:00","2024-12-13 09:00","2024-12-14 18:00","연속"]
[244,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-12-05 07:00","2024-12-06 18:00","취소","취소","매일"]
[245,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2024-12-03 07:00","2024-12-04 18:00","취소","취소","매일"]
[246,"광주전남","순천","율촌화치#2 T/L","율촌S/S 154kV 포스코퓨처엠T/L GIS 증설공사(즉시가압 가능)","1CCT 증설, 즉시가압 가능","2024-12-30 09:00","2024-12-31 18:00","2024-12-30 09:00","2024-12-31 18:00","연속"]
[247,"광주전남","순천","율촌화치#2 T/L","율촌S/S 154kV 포스코퓨처엠T/L GIS 증설공사(즉시가압 가능)","1CCT 증설, 즉시가압 가능","2024-12-19 09:00","2024-12-20 18:00","2024-12-19 09:00","2024-12-20 18:00","연속"]
[248,"광주전남","순천","태금하동화력 T/L","24-25년 순천전력지사 변전회사 총액공사","효성제 170kv gis 부품 교체 시행(즉시가압 불가)","2024-12-05 14:00","2024-12-05 18:00","취소","취소","연속"]
[249,"광주전남","순천","황금세풍#2 T/L CB","154kV 광양바이오매스발전소 접속설비 연계공사","154kV 백운-세풍- 황금개폐소 간 2파이 분기 접속설비 연계를 위한 공용송전망 Y분기 접속공사 및 시험","2024-12-26 09:00","2024-12-27 09:00","2024-12-26 09:00","2024-12-27 09:00","연속"]
[250,"광주전남","직할","일곡비아#1 T/L","`24년 직할 170kV GIS 정밀 및 보통점검 공사","상부 가스 누기 조치 170kV GIS 보통점검(불가 시 하루 공정단축 가능&하루휴전시 즉시가압 가능)","2024-12-11 09:00","2024-12-13 18:00","취소","취소","연속"]
[251,"광주전남","직할","하남S/S #1 BUS","하남S/S 154kV 수완-하남T/L GIS 증설공사","#1DS, CB부 설치","2024-12-03 14:00","2024-12-13 14:00","2024-12-03 14:00","2024-12-13 14:00","연속"]
[252,"대구","경산","자인S/S #2 BUS","자인S/S 154kV GIS 증설공사(모선구분)","[#65-66 BUS SECTION 설치] ○ #65BUS GIB 철거 및 END COVER 설치 (모선분리) ○ 철거구간 : #2M.Tr 좌측 (공정도참조) ○ 무부하가압 완료후 : #65BUS 운전 (66BUS 휴전) ○ #65-66 BUS-SECTION 설치 및 시험 ○ #2BUS END COVER 철거 및 BELLOWS 설치 (모선연결)","2024-12-06 09:00","2024-12-17 16:00","2024-12-06 09:00","2024-12-17 16:00","연속"]
[253,"대구","달성","달서강창 T/L","2024년 가공송전 순시점검 위탁공사","154kV 강창분기(강창-달서T/L) 초기점검","2024-12-06 07:00","2024-12-06 18:00","2024-12-06 07:00","2024-12-06 18:00","연속"]
[254,"대구","달성","강창다사 T/L","2024년 가공송전 순시점검 위탁공사","154kV 강창분기(강창-다사T/L) 초기점검","2024-12-05 07:00","2024-12-05 18:00","2024-12-05 07:00","2024-12-05 18:00","연속"]
[255,"대구","달성","논공달성#1 T/L","2024~2025년 달성전력지사 가공송전협력회사 공사","폴리머 점퍼지지애자 교체공사(No.1)","2024-12-02 07:30","2024-12-02 18:00","2024-12-02 07:30","2024-12-02 18:00","연속"]
[256,"대구","달성","논공S/S #1 EM.Tr CB","논공S/S FR-ESS 정기점검","논공S/S FR-ESS 정기점검","2024-12-02 09:00","2024-12-06 18:00","2024-12-02 09:00","2024-12-06 18:00","연속"]
[257,"대구","달성","대구봉덕#2 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-봉덕T/L 수평 추락방지장치 설치공사","2024-12-10 07:00","2024-12-12 18:00","2024-12-10 07:00","2024-12-12 18:00","연속"]
[258,"대구","달성","대구봉덕#1 T/L","345kV 북경남-서대구 등 24개 T/L 추락방지장치 설치공사","154kV 대구-봉덕T/L 수평 추락방지장치 설치공사","2024-12-05 07:00","2024-12-09 18:00","2024-12-05 07:00","2024-12-09 18:00","연속"]
[259,"대구","달성","고령쌍림#2 T/L","2024년 가공송전 순시점검 위탁공사","154kV 고령-쌍림T/L 초기점검(26,49호)","2024-12-10 09:00","2024-12-10 18:00","2024-12-10 09:00","2024-12-10 18:00","연속"]
[260,"대구","달성","고령쌍림#1 T/L","2024년 가공송전 순시점검 위탁공사","154kV 고령-쌍림T/L 초기점검(26,49호)","2024-12-09 09:00","2024-12-09 18:00","2024-12-09 09:00","2024-12-09 18:00","연속"]
[261,"대구","직할","공평서침산 T/L","서침산S/S 154kV SW증설공사","송전선로 원격 제어/감시 LID 이설","2024-12-11 09:00","2024-12-12 18:00","2024-12-11 09:00","2024-12-12 18:00","연속"]
[262,"대구","칠곡","어모김천#1 T/L","154kV 김천S/S 현대화공사","○ #4M.Tr 1차 모선연결관련 안전이격확보","2024-12-23 08:00","2024-12-23 12:00","2024-12-23 08:00","2024-12-23 12:00","연속"]
[263,"대구","칠곡","농소김천#1 T/L","154kV 김천S/S 현대화공사","○ 송전선로 인출변경","2024-12-19 08:00","2024-12-20 18:00","2024-12-19 08:00","2024-12-20 18:00","연속"]
[264,"대구","칠곡","서대구칠곡#1 T/L","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 154kV 인출측 정비","2024-12-09 07:30","2024-12-11 18:00","2024-12-09 07:30","2024-12-11 18:00","연속"]
[265,"대구","칠곡","서대구칠곡#2 T/L","서대구S/S 345kV 주변압기측 현대화 공사","주변압기 부하전환 작업에 따른 154kV 인출측 정비","2024-12-09 07:30","2024-12-12 18:00","2024-12-09 07:30","2024-12-12 18:00","연속"]
[266,"대구","포항","옥동외동#1 T/L","2024~25년도 포항전력지사 변전총액공사","외동S/S 687 GIS 조작시험","2024-12-06 09:00","2024-12-06 14:00","2024-12-06 09:00","2024-12-06 14:00","연속"]
[267,"경북","구미","남인동인동#2 T/L","2024-25년 구미전력지사 변전협력회사 공사","[남인동S/S] - PNL 교체 [인동S/S] - GIS 보통점검[정밀] - PNL 교체 - 전자변 교체, 공기조작부 정밀점검","2024-12-16 09:00","2024-12-19 18:00","2024-12-16 09:00","2024-12-19 18:00","연속"]
[268,"경북","구미","남인동인동#1 T/L","2024-25년 구미전력지사 변전협력회사 공사","[남인동S/S] - B상 누설전류계 교체 - PNL 교체 [인동S/S] - GIS 보통점검[정밀] - PNL 교체 - 전자변 교체, 공기조작부 정밀점검","2024-12-09 09:00","2024-12-12 18:00","2024-12-23 09:00","2024-12-26 18:00","연속"]
[269,"경북","구미","선산청리#1 T/L","2024-25년 구미전력지사 변전협력회사 공사","[선산S/S] - GIS 보통점검[정밀] - LA 하자점검 - 154kV GIS DS 방압변 점검 [청리S/S] - LA 교체","2024-12-04 09:00","2024-12-04 18:00","2024-12-05 09:00","2024-12-05 18:00","연속"]
[270,"경북","영주","점촌문경 T/L","2024-25년 영주전력지사 가공송전협력회사 총액공사","154kV 점촌-문경T/L 수평추락방지장치 설치공사","2024-12-16 09:00","2024-12-24 18:00","취소","취소","연속"]
[271,"경북","영주","문경단양 T/L","2024-25년 영주전력지사 가공송전협력회사 총액공사","154kV 문경-단양T/L 수평추락방지장치 설치공사","2024-12-07 09:00","2024-12-15 18:00","취소","취소","연속"]
[272,"경북","영주","예천점촌#2 T/L","2024-25년 영주전력지사 변전협력회사 공사","GIS 보통점검, CVT 초기점검","2024-12-09 09:00","2024-12-10 18:00","취소","취소","매일"]
[273,"경북","영주","예천점촌#1 T/L","2024-25년 영주전력지사 변전협력회사 공사","GIS 보통점검","2024-12-11 09:00","2024-12-11 18:00","취소","취소","연속"]
[274,"경북","직할","동안동임하HP T/L","'24~25년 경북 직할 가공송전 협력회사 공사","154kV 동안동-임하HPT/L 추락방지장치 설치공사","2024-12-02 08:00","2024-12-04 18:00","2024-12-02 08:00","2024-12-04 18:00","연속"]
[275,"경북","직할","동안동임하HP T/L","`24~25년 경북본부 직할 변전협력회사 공사","동안동S/S 동안동-임하HP T/L 보호반 교체","2024-12-09 09:00","2024-12-13 18:00","취소","취소","연속"]
[276,"경북","직할","안동동안동#2 T/L","`24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2024-12-09 09:00","2024-12-09 18:00","2024-12-09 09:00","2024-12-09 18:00","연속"]
[277,"경북","직할","영덕진보#2 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","154kV 영덕-진보#2T/L 추락방지장치 설치공사","2024-12-02 08:00","2024-12-10 18:00","2024-12-02 08:00","2024-12-10 18:00","연속"]
[278,"부산울산","동부산","신양산구서#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","154kV 신양산-수영#1T/L 휴전작업 관련 안전이격 확보차","2024-12-02 07:00","2024-12-03 18:00","2024-12-02 07:00","2024-12-03 18:00","연속"]
[279,"부산울산","동부산","정보대연 T/L","지중송전 OF케이블 절연유 보충","1. 선로명 : 154kV 정보-대연T/L 2. 작업장소 : 수영C/H 3. 작업내용 : OF케이블 절연유 보충","2024-12-07 09:00","2024-12-07 18:00","취소","취소","연속"]
[280,"부산울산","북부산","양산산막#1 T/L","24-25년 북부산전력지사 변전총액공사","산막S/S 양산-산막#1T/L GIS 보통점검","2024-12-07 09:00","2024-12-07 18:00","2024-12-07 09:00","2024-12-07 18:00","연속"]
[281,"부산울산","북부산","양산삼랑진PP T/L","154kV 북부산-양산T/L OPGW 증설공사","양산S/S ~ 양산분기 No.1간 OPGW 시설","2024-12-02 09:00","2024-12-06 18:00","2024-12-02 09:00","2024-12-06 18:00","연속"]
[282,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○3차분 (미음-녹산#1T/L, #1M.Tr 1차 대체, 기존BUS-TIE 철거) - 기존BUS-TIE #6202DS 철거 및 ENDCOVER 취부 - #2BUS 시험가압 (2DS 개방상태) 1시간 - 시험가압선로 (신녹산-녹산#1T/L)","2024-12-05 17:00","2024-12-05 18:00","2024-12-05 17:00","2024-12-05 18:00","연속"]
[283,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○3차분 (미음-녹산#1T/L, #1M.Tr 1차 대체, 기존BUS-TIE 철거) - #1BUS 시험가압 (1DS 개방상태) 24시간 - 시험가압선로 (신녹산-녹산#1T/L)","2024-12-21 17:00","2024-12-22 17:00","2024-12-21 17:00","2024-12-22 17:00","연속"]
[284,"부산울산","서부산","미음녹산#2 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 154kV GIS 7BAY 대체 ○3차분 (미음-녹산#1T/L, #1M.Tr 1차 대체, 기존 BUS-TIE 철거) - 안전거리이격확보(미음-녹산#2T/L) 미음-녹산#1T/L 부싱제거","2024-12-09 09:00","2024-12-12 18:00","2024-12-09 09:00","2024-12-12 18:00","연속"]
[285,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○3차분 (미음-녹산#1T/L, #1M.Tr 1차 대체, 기존BUS-TIE 철거) - #2BUS 시험가압 (2DS 개방상태) 24시간 - 시험가압선로 (신녹산-녹산#1T/L)","2024-12-27 17:00","2024-12-28 17:00","2024-12-27 17:00","2024-12-28 17:00","연속"]
[286,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○3차분 (미음-녹산#1T/L, #1M.Tr 1차 대체, 기존BUS-TIE 철거) - 기존BUS-TIE #6202DS 철거 및 ENDCOVER 취부 - #2BUS 시험가압 (2DS 개방상태) 1시간 - 시험가압선로 (신녹산-녹산#1T/L)","2024-12-03 17:00","2024-12-03 18:00","2024-12-03 17:00","2024-12-03 18:00","연속"]
[287,"부산울산","서부산","미음녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 - 3차분 (미음-녹산 #1T/L, #1M.Tr 1차 대체, 기존BUS-TIE 철거)","2024-12-02 09:00","2025-01-03 18:00","2024-12-02 09:00","2025-01-03 18:00","연속"]
[288,"부산울산","서부산","미음녹산#2 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○3차분 (미음-녹산#1T/L, #1M.Tr 1차 대체, 기존 BUS-TIE 철거) - 안전거리이격확보(미음-녹산#2T/L) 미음-녹산#1T/L 부싱설치","2024-12-23 09:00","2024-12-24 18:00","2024-12-23 09:00","2024-12-24 18:00","연속"]
[289,"부산울산","서부산","서부산S/S 부산#1ST CB","서부산S/S 154kV #1ST GIS 동작시험","서부산S/S 154kV #1ST GIS 동작시험","2024-12-09 09:00","2024-12-09 18:00","2024-12-09 09:00","2024-12-09 18:00","연속"]
[290,"부산울산","서부산","신녹산S/S #1 BUS","신녹산S/S 345kV #1M.Tr 증설공사","154kV 65-66/60-61SEC, 6200BT, 61-66PT&ES 증설","2024-12-02 09:00","2024-12-13 18:00","취소","취소","연속"]
[291,"부산울산","서부산","용원녹공#2 T/L","용원S/S 용원-녹공#2T/L ES 기계적 인터록 접점 보수","용원S/S 용원-녹공#2T/L ES 기계적 인터록 접점 보수","2024-12-02 13:00","2024-12-02 18:00","취소","취소","연속"]
[292,"부산울산","서부산","용원녹공#2 T/L","용원S/S 용원-녹공#2T/L GIS 휴전작업","용원S/S 용원-녹공#2T/L GIS 휴전작업 (기계적 접점 보수)","2024-09-26 09:00","2024-09-26 18:00","취소","취소","연속"]
[293,"부산울산","서부산","용원녹공#1 T/L","용원S/S 용원-녹공#1T/L ES 기계적 인터록 접점 보수","용원S/S 용원-녹공#1T/L ES 기계적 인터록 접점 보수","2024-12-02 13:00","2024-12-02 18:00","취소","취소","연속"]
[294,"부산울산","울산","반천언양#1 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치, 수평추락방지장치 설치","2024-12-09 07:30","2024-12-11 18:00","2024-12-09 07:30","2024-12-11 18:00","연속"]
[295,"부산울산","울산","반천언양#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치, 수평추락방지장치 설치, 피뢰기 설치","2024-12-06 07:30","2024-12-07 18:00","2024-12-06 07:30","2024-12-07 18:00","연속"]
[296,"부산울산","울산","신울산명례#1 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-12-02 07:30","2024-12-03 18:00","2024-12-02 07:30","2024-12-03 18:00","연속"]
[297,"부산울산","울산","신울산명례#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-12-04 07:30","2024-12-05 18:00","2024-12-04 07:30","2024-12-05 18:00","연속"]
[298,"부산울산","울산","언양산막#2 T/L","#2DS 조작불량 관련 메커니즘 보수","- #2DS 조작불량 관련 메커니즘 보수","2024-12-14 09:00","2024-12-14 18:00","2024-12-14 09:00","2024-12-14 18:00","연속"]
[299,"부산울산","울산","웅촌서창#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-12-18 07:30","2024-12-19 18:00","2024-12-18 07:30","2024-12-19 18:00","연속"]
[300,"부산울산","울산","웅촌서창#1 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","고정형 폴리머점퍼지지애자 설치","2024-12-20 07:30","2024-12-20 18:00","2024-12-20 07:30","2024-12-20 18:00","연속"]
[301,"부산울산","직할","우동대연 T/L","24~25년 서부산전력지사 가공송전협력회사 공사","우동-대연T/L 태풍취약철탑 보강","2024-12-08 13:00","2024-12-08 18:00","2024-12-08 13:00","2024-12-08 18:00","연속"]
[302,"부산울산","직할","양정범천 T/L","24~25년 직할 변전협력회사 총액공사","범천S/S 154kV 양정-범천T/L GIS 메커니즘 발청 조치","2024-12-04 09:30","2024-12-04 18:00","2024-12-04 09:30","2024-12-04 18:00","연속"]
[303,"경남","김해송변전부","호포매리#1 T/L","154kV 대동S/S 및 분기T/L 건설사업","- 154kV 호포-매리#1T/L 보호반 대체작업(12/13~12/17) - 154kV 대동분기T/L 가공 및 지중 작업(12/13~12/15) - 신규설비(송전선로 및 변전소) 사용전검사(12/17) - 무부하가압(12/15~12/16), 실부하가압(12/17)","2024-12-13 20:00","2024-12-16 09:00","2024-12-13 20:00","2024-12-16 09:00","연속"]
[304,"경남","김해송변전부","호포매리#2 T/L","154kV 대동S/S 및 분기T/L 건설사업","- 154kV 호포-매리#2T/L 보호반 대체작업(12/6~12/8) - 154kV 대동분기T/L 가공 및 지중 작업(12/7~12/9) - 신규설비(송전선로 및 변전소) 사용전검사(12/10) - 무부하가압(12/8~12/9), 실부하가압(12/10)","2024-12-06 20:00","2024-12-09 09:00","2024-12-06 20:00","2024-12-09 09:00","연속"]
[305,"경남","김해송변전부","삼계어방#2 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-12-21 07:00","2024-12-21 18:00","2024-12-21 07:00","2024-12-21 18:00","연속"]
[306,"경남","김해송변전부","삼계어방#1 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-12-21 07:00","2024-12-21 18:00","2024-12-21 07:00","2024-12-21 18:00","연속"]
[307,"경남","김해송변전부","신김해진례#2 T/L","345kV 신김해-북부산 8개T/L 철탑추락방지장치 설치공사","345kV 신김해-북부산 8개T/L 철탑추락방지장치 설치공사","2024-12-08 07:00","2024-12-08 18:00","2024-12-08 07:00","2024-12-08 18:00","연속"]
[308,"경남","김해송변전부","신김해진례#1 T/L","345kV 신김해-북부산 8개T/L 철탑추락방지장치 설치공사","345kV 신김해-북부산 8개T/L 철탑추락방지장치 설치공사","2024-12-07 07:00","2024-12-07 18:00","2024-12-07 07:00","2024-12-07 18:00","연속"]
[309,"경남","김해송변전부","신김해S/S CB 6300","신김해S/S 6300 보통점검","신김해S/S 6300 보통점검","2024-12-01 14:30","2024-12-01 18:30","2024-12-01 14:30","2024-12-01 18:30","연속"]
[310,"경남","김해송변전부","신김해S/S CB 6100","신김해S/S 6100 보통점검","신김해S/S 6100 보통점검","2024-12-01 09:30","2024-12-01 14:30","2024-12-01 09:30","2024-12-01 14:30","연속"]
[311,"경남","김해송변전부","김해어방#2 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-12-22 07:00","2024-12-22 18:00","2024-12-22 07:00","2024-12-22 18:00","연속"]
[312,"경남","김해송변전부","김해어방#1 T/L","154kV 마천-진해TL 등 16개 TL 추락방지장치 설치 및 교체공사","추락방지장치 설치 및 교체공사","2024-12-22 07:00","2024-12-22 18:00","2024-12-22 07:00","2024-12-22 18:00","연속"]
[313,"경남","김해송변전부","진례진영#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2024-12-15 07:00","2024-12-15 18:00","2024-12-15 07:00","2024-12-15 18:00","매일"]
[314,"경남","직할","안민천선#2 T/L","EBG 가스채취밸브 설치공사","대한전선 EBG 가스채취밸브 설치공사","2024-12-28 07:00","2024-12-30 07:00","2024-12-28 07:00","2024-12-30 07:00","연속"]
[315,"경남","직할","안민천선#1 T/L","EBG 가스채취밸브 설치공사","대한전선 EBG 가스채취밸브 설치공사","2024-12-21 07:00","2024-12-23 09:00","2024-12-21 07:00","2024-12-23 09:00","연속"]
[316,"경남","진주","하동개양#2 T/L","154kV 정촌S/S 및 분기T/L 건설사업","- 154kV 하동-개양#2T/L 보호반 대체작업(11/25~11/26) - 154kV 정촌분기 지중T/L 지중전력케이블 작업(11/25~11/26) - 154kV 정촌분기T/L 송전선 연결 및 일부구간 철거 작업(11/25~11/29) - 154kV 정촌S/S 통신설비공사(11/25~11/29) - 무부하가압(11/30~12/01) - 신규설비(송전선로 및 변전소) 사용전검사(12/02~12/04) - 실부하가압(12/04)","2024-12-04 09:00","2024-12-13 18:00","취소","취소","연속"]
[317,"경남","진주","하동개양#1 T/L","154kV 정촌S/S 및 분기T/L 건설사업","- 154kV 하동-개양#1T/L 보호반 대체작업(12/05~12/06) - 154kV 정촌분기 지중T/L 지중전력케이블 작업(12/05~12/06) - 154kV 정촌분기T/L 송전선 연결 및 일부구간 철거 작업(12/05~12/09) - 154kV 정촌S/S 통신설비공사(12/05~12/09) - 무부하가압(12/10~12/11) - 신규설비(송전선로 및 변전소) 사용전검사(12/12~12/13) - 실부하가압(12/13)","2024-12-16 09:00","2024-12-24 18:00","2024-12-09 09:00","2024-12-13 18:00","연속"]
[318,"경남","통영","거제S/S #1 Sh.C CB","거제S/S 154kV #1Sh.C 보호배전반 대체","거제S/S 154kV #1Sh.C 보호배전반 대체","2024-12-16 09:00","2024-12-20 18:00","취소","취소","연속"]
[319,"경남","통영","거류거제#1 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행)(2차)","○ 154kV 거류-거제#1T/L 78호 ~ 가철탑 2호 전선 설치, 거제S/T ~ EBA 인하선 설치, 기설 78호 ~ 거제S/T 전선 철거","2024-12-08 07:00","2024-12-08 18:00","2024-12-08 07:00","2024-12-08 18:00","연속"]
[320,"경남","통영","통영거제#2 T/L","거제S/S 인출 송전선로 임시선로 구성(요청자시행)(2차,안전거리 확보)","○ 154kV 거류-거제#1T/L 휴전작업 관련 안전거리 확보 휴전 ○ 154kV 거류-거제#1T/L 78호 ~ 가철탑 2호 전선 설치, 거제S/T ~ EBA 인하선 설치, 기설 78호 ~ 거제S/T 전선 철거","2024-12-08 07:00","2024-12-08 18:00","2024-12-08 07:00","2024-12-08 18:00","연속"]
[321,"경남","통영","통영거제#2 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행)(1차)","○ 154kV 통영-거제#2T/L 70호 ~ 가철탑 2호 전선(중,하단) 설치, 거제S/T ~ EBA 인하선 설치(C,A상), 기설 70호 ~ 거제S/T 전선 철거","2024-12-01 07:00","2024-12-01 18:00","2024-12-01 07:00","2024-12-01 18:00","연속"]
[322,"경남","통영","거류거제#1 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행)(1차)","○ 154kV 거류-거제#1T/L 78호 ~ 가철탑 2호 전선 설치, 거제S/T ~ EBA 인하선 설치, 기설 78호 ~ 거제S/T 전선 철거","2024-12-01 07:00","2024-12-01 18:00","2024-12-01 07:00","2024-12-01 18:00","연속"]
[323,"경남","함안","가야사봉#2 T/L","154kV 가야-사봉#1,2T/L 철탑추락방지장치 설치공사","추락재해 예방을 위한 수평형 철탑추락방지장치 설치공사 (대상개소 : 154kV 가야-사봉#1,2T/L 1~13호)","2024-12-21 07:00","2024-12-22 18:00","2024-12-21 07:00","2024-12-22 18:00","매일"]
[324,"경남","함안","가야사봉#1 T/L","154kV 가야-사봉#1,2T/L 철탑추락방지장치 설치공사","추락재해 예방을 위한 수평형 철탑추락방지장치 설치공사 (대상개소 : 154kV 가야-사봉#1,2T/L 1~13호)","2024-12-21 07:00","2024-12-22 18:00","2024-12-21 07:00","2024-12-22 18:00","매일"]
[325,"경남","함안","서마산진동#1 T/L","서마산S/S 서마산-진동#1T/L GIS 조작시험 외","서마산S/S 서마산-진동#1T/L GIS 조작시험 및 전자변 교체","2024-12-07 09:30","2024-12-07 17:30","2024-12-07 09:30","2024-12-07 17:30","연속"]