{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":4,"n_cols":11,"rows_kept":4,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 1월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]

{"sheet":"345설비","index":1,"n_rows":30,"n_cols":11,"rows_kept":30,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2025년도 1월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #1 M.Tr","25년 성동P/O 변전협력회사 공사","#1S.Tr 보호계전기 교체","2025-01-08 10:00","2025-01-08 18:00","취소","취소","연속"]
[2,"남서울","강남","신양재S/S #4 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사","- #74Bay B/F PNL 대체공사","2025-01-13 09:00","2025-01-17 18:00","취소","취소","연속"]
[3,"남서울","강남","신양재S/S #3 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사","- #74Bay B/F PNL 대체공사","2025-01-13 09:00","2025-01-17 18:00","취소","취소","연속"]
[4,"인천","부평","신가좌S/S CB 7200","신가좌S/S 345kV 7200CB 조작시험 및 절연열화 측정","신가좌S/S 345kV 7200CB 조작시험 및 절연열화 측정","2025-01-06 09:00","2025-01-06 18:00","취소","취소","연속"]
[5,"충북","직할","신중부남청주#1 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 한국전기안전공사 사용 전 검사 수검(#1T/L)","2025-01-07 09:00","2025-01-08 18:00","2025-01-07 09:00","2025-01-08 18:00","연속"]
[6,"충북","직할","신중부남청주#2 T/L","345kV 신중부-신청주T/L 용량증대 전선교체공사","○ 한국전기안전공사 사용 전 검사 수검 (#2T/L)","2025-01-09 09:00","2025-01-10 18:00","2025-01-09 09:00","2025-01-10 18:00","연속"]
[7,"대전세종충남","서산","신서산S/S #5 Sh.R CB","24년 서산P/O 345kV GIS 정밀점검공사","(즉시가압 불가) 신서산S/S 345kV 7979 CB 정밀점검","2025-01-06 09:30","2025-01-10 18:00","2025-01-06 09:30","2025-01-10 18:00","연속"]
[8,"대전세종충남","서산","태안T/P CB 7571","효성제 345kV CB 주요 메커니즘 부품 교체 공사","(즉시가압불가) 태안화력S/S 345kV 개폐소-태안화력#1T/L 7571 CB 메커니즘 부품 교체","2025-01-07 09:30","2025-01-08 18:00","2025-01-07 09:30","2025-01-08 18:00","연속"]
[9,"대전세종충남","서산","태안T/P CB 7572","효성제 345kV CB 주요 메커니즘 부품 교체 공사","(즉시가압불가) 태안화력S/S 345kV #5GEN 7572 CB 메커니즘 부품 교체","2025-01-09 09:30","2025-01-10 18:00","2025-01-09 09:30","2025-01-10 18:00","연속"]
[10,"대전세종충남","서산","태안T/P CB 7671","효성제 345kV CB 주요 메커니즘 부품 교체 공사","(즉시가압불가) 태안화력S/S 345kV 신서산-태안화력#1T/L 7671 CB 메커니즘 부품 교체","2025-01-14 09:30","2025-01-15 18:00","2025-01-14 09:30","2025-01-15 18:00","연속"]
[11,"대전세종충남","서산","태안T/P CB 7672","효성제 345kV CB 주요 메커니즘 부품 교체 공사","(즉시가압불가) 태안화력S/S 345kV #6GEN 7672 CB 메커니즘 부품 교체","2025-01-20 09:30","2025-01-21 18:00","2025-01-20 09:30","2025-01-21 18:00","연속"]
[12,"대전세종충남","서산","태안T/P CB 7600","효성제 345kV CB 주요 메커니즘 부품 교체 공사","(즉시가압불가) 태안화력S/S 345kV 신서산#1T/L-#6GEN TIE 7600 CB 메커니즘 부품 교체","2025-01-16 09:30","2025-01-17 18:00","2025-01-16 09:30","2025-01-17 18:00","연속"]
[13,"전북","군산","군산S/S #1 M.Tr","군산S/S #1M.Tr 2차 GIS점검","군산S/S #1M.Tr 2차 GIS점검","2025-01-10 09:00","2025-01-10 18:00","2025-01-10 09:00","2025-01-10 18:00","연속"]
[14,"광주전남","광주","신광주S/S #2 BUS","장기사용 345kV #2BUS 모선보호반 교체","장기사용 345kV #2BUS 모선보호반 교체","2025-01-13 08:00","2025-01-17 18:00","취소","취소","연속"]
[15,"광주전남","광주","신광주S/S #1 BUS","장기사용 345kV #1BUS 모선보호반 교체","장기사용 345kV #1BUS 모선보호반 교체","2025-01-06 08:00","2025-01-10 18:00","취소","취소","연속"]
[16,"광주전남","광주","신화순S/S CB 7600","'25년 광주전력지사 변전협력회사 총액공사","- 362kV GIS 하자보수","2025-01-13 09:00","2025-01-15 18:00","2025-01-13 09:00","2025-01-15 18:00","연속"]
[17,"광주전남","광주","신화순S/S CB 7672","'25년 광주전력지사 변전협력회사 총액공사","- 362kV GIS 하자보수","2025-01-13 09:00","2025-01-15 18:00","2025-01-13 09:00","2025-01-15 18:00","연속"]
[18,"광주전남","광주","신화순S/S #1 Sh.R CB","'25년 광주전력지사 변전협력회사 총액공사","- 362kV GIS 하자보수","2025-01-13 09:00","2025-01-15 18:00","2025-01-13 09:00","2025-01-15 18:00","연속"]
[19,"대구","경산","신경산S/S #3 M.Tr","24~25년 경산P/O 변전협력회사 총액공사","- 보호반 교체","2025-01-13 09:30","2025-01-17 18:00","2025-01-13 09:30","2025-01-17 18:00","연속"]
[20,"대구","경산","신경산S/S #4 M.Tr","24~25년 경산P/O 변전협력회사 총액공사","- 보호반 교체","2025-01-20 09:30","2025-01-24 18:00","2025-01-20 09:30","2025-01-24 18:00","연속"]
[21,"대구","경산","신경산S/S #2 M.Tr","24~25년 경산P/O 변전협력회사 총액공사","- 보호반 교체","2025-01-06 09:30","2025-01-10 18:00","2025-01-06 09:30","2025-01-10 18:00","연속"]
[22,"경북","영주","신영주한울NP#1 T/L","345kV 신영주-한울NP2T/L 불량 금구류 정비","345kV 신영주-한울NP2T/L 불량 금구류 정비","2025-01-13 09:00","2025-01-14 18:00","취소","취소","매일"]
[23,"경북","영주","신영주한울NP#2 T/L","345kV 신영주-한울NP2T/L 불량 금구류 정비","345kV 신영주-한울NP2T/L 불량 금구류 정비","2025-01-15 09:00","2025-01-16 18:00","취소","취소","매일"]
[24,"부산울산","동부산","신양산S/S STATCOM CB","345kV 신양산S/S STATCOM 건설사업(사용전검사, 부하시험 등)","○ 345kV 신양산S/S STATCOM 건설사업 - 1월 : 사용전검사 및 C.Tr 무부하가압 - 2월 : STATCOM 부하가압 및 시운전(~4월)","2025-01-07 09:00","2025-04-25 18:00","2025-01-07 09:00","2025-04-25 18:00","연속"]
[25,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S #2M.Tr 부싱절연유 추적분석","신양산S/S #2M.Tr 부싱절연유 채유(부싱절연유 채유 분석결과 이상에 따른 추적 분석)","2025-01-12 06:00","2025-01-12 09:00","2025-01-12 06:00","2025-01-12 09:00","연속"]
[26,"부산울산","서부산","서부산북부산#2 T/L","서부산S/S #1M.TR 1차 부싱교체공사(시험가압선로)","서부산S/S #1M.TR 부싱교체공사(시험가압선로)","2025-01-18 09:00","2025-01-19 09:00","2025-01-18 09:00","2025-01-19 09:00","연속"]

{"sheet":"154설비","index":2,"n_rows":42,"n_cols":11,"rows_kept":42,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 1월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","부평","남인천S/S #2 BUS","154kV 남인천-학익 등 2개T/L 지장이설 및 선종교체","케이블 선종교체 (OF 2,000㎟ → XLPE 2,000㎟)","2025-01-30 09:00","2025-01-31 09:00","2025-01-30 09:00","2025-01-31 09:00","연속"]
[2,"인천","부평","송월남인천#2 T/L","154kV 남인천-학익 등 2개T/L 지장이설 및 선종교체","케이블 선종교체 (OF 2,000㎟ → XLPE 2,000㎟)","2025-01-30 09:00","2025-01-31 09:00","2025-01-30 09:00","2025-01-31 09:00","연속"]
[3,"인천","부평","학익S/S #2 BUS","154kV 남인천-학익 등 2개T/L 지장이설 및 선종교체","케이블 선종교체 (OF 2,000㎟ → XLPE 2,000㎟)","2025-01-30 09:00","2025-01-31 09:00","2025-01-30 09:00","2025-01-31 09:00","연속"]
[4,"대전세종충남","대전","팔봉두마#1 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","선종교체 구간 내 철탑 안전이격공사(3기)","2025-01-08 07:00","2025-01-14 18:00","취소","취소","연속"]
[5,"대전세종충남","대전","팔봉두마#2 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","선종교체 구간 내 철탑 안전이격공사(3기)","2025-01-15 07:00","2025-01-17 18:00","취소","취소","연속"]
[6,"대전세종충남","대전","팔봉두마#2 T/L","154kV 팔봉-두마T/L No.67~109 선종교체공사","선종교체 구간 내 철탑 안전이격공사(3기)","2025-01-06 07:00","2025-01-07 18:00","취소","취소","연속"]
[7,"전북","군산","군산서군산#1 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-01-06 09:00","2025-01-07 18:00","취소","취소","연속"]
[8,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-01-08 09:00","2025-01-09 18:00","취소","취소","연속"]
[9,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2025-01-20 09:00","2025-01-22 18:00","취소","취소","연속"]
[10,"전북","군산","서군산소룡#1 T/L","154kV 서군산-소룡#1T/L 구형 공법 EBA 구조개선 공사","일진제 구형 공법 EBA 구조개선 공사","2025-01-13 09:00","2025-01-17 18:00","취소","취소","연속"]
[11,"전북","군산","팔봉두마#1 T/L","154kV 팔봉두마T/L No.14~17 일부구간지중화 C/T설치공사","지중화 : No.14~17 약 400m 전선교체 : 1.524C-km 철탑설치철거 : 15,16호","2025-01-17 08:00","2025-01-21 18:00","2025-01-17 08:00","2025-01-21 18:00","연속"]
[12,"전북","군산","팔봉왕궁#2 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-01-15 09:00","2025-01-16 18:00","2025-01-15 09:00","2025-01-16 18:00","연속"]
[13,"전북","군산","팔봉왕궁#1 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-01-13 09:00","2025-01-14 18:00","2025-01-13 09:00","2025-01-14 18:00","연속"]
[14,"전북","군산","팔봉두마#2 T/L","154kV 팔봉두마T/L No.14~17 일부구간지중화 C/T설치공사","지중화 : No.14~17 약 400m 전선교체 : 1.524C-km 철탑설치철거 : 15,16호","2025-01-22 08:00","2025-01-26 18:00","2025-01-22 08:00","2025-01-26 18:00","연속"]
[15,"전북","김제","김제칠보HP T/L","154kV 정공-정주 등 3개T/L 추락방지장치 설치공사","- 공사구간 : 154kV 담양-김제T/L No.1~No.119) - 수평 추락방지장치 설치 154kV 김제-칠보T/L No.1~83","2025-01-11 07:00","2025-01-18 18:00","2025-01-20 07:00","2025-01-27 18:00","연속"]
[16,"전북","김제","담양김제 T/L","154kV 정공-정주 등 3개T/L 추락방지장치 설치공사","- 공사구간 : 154kV 담양-김제T/L No.1~No.119) - 수평 추락방지장치 설치 154kV 담양-김제T/L","2025-01-01 07:00","2025-01-09 18:00","2025-01-06 07:00","2025-01-16 18:00","연속"]
[17,"전북","김제","백산김제#1 T/L","백산S/S 154kV 백산-김제#1T/L 차단기 보통점검","백산S/S 154kV 백산-김제#1T/L 차단기 보통점검","2025-01-20 09:00","2025-01-20 15:00","2025-01-20 09:00","2025-01-20 15:00","연속"]
[18,"전북","김제","백산김제#2 T/L","백산S/S 154kV 백산-김제#2T/L 차단기 보통점검","백산S/S 154kV 백산-김제#2T/L 차단기 보통점검","2025-01-21 09:00","2025-01-21 15:00","2025-01-21 09:00","2025-01-21 15:00","연속"]
[19,"전북","김제","신김제정공#1 T/L","관내S/S 154kV 차단기 조작시험","관내S/S 154kV 차단기 조작시험(즉시가압 가능)","2025-01-22 09:00","2025-01-22 14:00","2025-01-22 09:00","2025-01-22 14:00","연속"]
[20,"전북","김제","신김제정공#2 T/L","관내S/S 154kV 차단기 조작시험","관내S/S 154kV 차단기 조작시험(즉시가압 가능)","2025-01-22 14:00","2025-01-22 18:00","2025-01-22 14:00","2025-01-22 18:00","연속"]
[21,"전북","직할","북전주봉동#1 T/L","북전주-봉동#1T/L 송전선로 보호반 대체공사","북전주-봉동#1T/L 송전선로 보호반 대체공사","2025-01-06 09:00","2025-01-06 18:00","2025-01-06 09:00","2025-01-06 18:00","연속"]
[22,"광주전남","강진","삼호화원#2 T/L","154kV 삼호-화원 지중T/L(복도체화) 건설공사","154kV XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2025-01-13 09:00","2025-02-21 18:00","취소","취소","연속"]
[23,"광주전남","광주","계림S/S SEC CB 61600","'25년 광주전력지사 변전협력회사 총액공사","- 모선보호반 대체(60-65)","2025-01-06 09:00","2025-01-10 18:00","취소","취소","연속"]
[24,"광주전남","광주","계림S/S CB 6100","'25년 광주전력지사 변전협력회사 총액공사","- 모선보호반 대체(60-65)","2025-01-06 09:00","2025-01-10 18:00","취소","취소","연속"]
[25,"광주전남","광주","계림S/S SEC CB 66650","'25년 광주전력지사 변전협력회사 총액공사","- 모선보호반 대체(60-65)","2025-01-06 09:00","2025-01-10 18:00","취소","취소","연속"]
[26,"광주전남","목포","엄다목포#2 T/L","엄다S/S 154kV 장기사용 GIS 교체공사(3차)","나주-엄다#1T/L, #2M.Tr 1차 GIS 교체","2025-01-10 10:00","2025-01-11 10:00","취소","취소","연속"]
[27,"광주전남","목포","엄다S/S #2 BUS","엄다S/S 154kV 장기사용 GIS 교체공사(3차)","나주-엄다#1T/L, #2M.Tr 1차 GIS 교체","2025-01-13 09:00","2025-01-24 18:00","취소","취소","연속"]
[28,"광주전남","순천","율촌여수산단#1 T/L","율촌S/S 154kV 포스코퓨처엠T/L GIS 증설공사(즉시가압 가능)","1CCT 증설, 즉시가압 가능","2025-01-08 09:00","2025-01-17 18:00","취소","취소","연속"]
[29,"광주전남","직할","남광주금천#2 T/L","154kV 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 임시철탑 1기 설치 ○ 전력선 철거 : 2.6C-km ○ 전력선 신설 : 2.4C-km □ 기 타 : 토요일 작업 예정, 13~15일 연속휴전 16일~ 18일 매일휴전","2025-01-13 09:00","2025-01-18 18:00","취소","취소","연속"]
[30,"광주전남","직할","나주금천#1 T/L","154kV 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 임시철탑 1기 설치 ○ 전력선 철거 : 2.6C-km ○ 전력선 신설 : 2.4C-km □ 기 타 : 토요일 작업 예정, 13~15일 매일휴전 16일~ 18일 연속휴전","2025-01-13 09:00","2025-01-18 18:00","취소","취소","연속"]
[31,"광주전남","직할","나주금천#2 T/L","154kV 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 임시철탑 1기 설치 ○ 전력선 철거 : 2.6C-km ○ 전력선 신설 : 2.4C-km □ 기 타 : 토요일 작업 예정, 20~22일 매일휴전 23일~ 25일 연속휴전","2025-01-20 09:00","2025-01-25 18:00","취소","취소","연속"]
[32,"광주전남","직할","남광주금천#1 T/L","154kV 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 임시철탑 1기 설치 ○ 전력선 철거 : 2.6C-km ○ 전력선 신설 : 2.4C-km □ 기 타 : 토요일 작업 예정, 20~22일 연속휴전 23일~ 25일 매일휴전","2025-01-20 09:00","2025-01-25 18:00","취소","취소","연속"]
[33,"광주전남","직할","비아하남#1 T/L","154kV 첨단분기 T/L 건설공사","ㅁ 154kV 첨단분기 T/L No.33호 가철탑 건설공사 ㅇ 가철탑 조립 및 전력선 공중이동","2025-01-16 07:00","2025-01-18 18:00","2025-01-16 07:00","2025-01-18 18:00","연속"]
[34,"광주전남","직할","비아하남#2 T/L","154kV 첨단분기 T/L 건설공사","ㅁ 154kV 첨단분기 T/L No.33호 가철탑 건설공사 - 가철탑 조립 및 전력선 공중이동","2025-01-13 07:00","2025-01-15 18:00","2025-01-13 07:00","2025-01-15 18:00","연속"]
[35,"대구","칠곡","어모김천#1 T/L","154kV 김천S/S 현대화공사","○ #4M.Tr 1차 모선연결관련 안전이격확보","2025-01-13 08:00","2025-01-13 18:00","2025-01-13 08:00","2025-01-13 18:00","연속"]
[36,"경북","영주","문경단양 T/L","2024-25년 영주전력지사 가공송전협력회사 총액공사","154kV 문경-단양T/L 수평추락방지장치 및 조류착지방지장치 설치공사","2025-01-04 09:00","2025-01-12 18:00","취소","취소","연속"]
[37,"경북","영주","문경단양 T/L","문경S/S 154kV 문경-단양T/L 보호반 21 Ry 배터리 교체","문경S/S 154kV 문경-단양T/L 보호반 21 Ry 배터리 교체","2025-01-15 10:00","2025-01-15 11:00","취소","취소","연속"]
[38,"경북","영주","점촌문경 T/L","2024-25년 영주전력지사 가공송전협력회사 총액공사","154kV 점촌-문경T/L 수평추락방지장치 및 조류착지방지장치 설치공사","2025-01-20 09:00","2025-01-28 18:00","취소","취소","연속"]