{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":8,"n_cols":11,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 2월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #1 M.Tr","신가평S/S 765kV #1M.Tr 부싱탭어댑터 설치","신가평S/S 765kV #1M.Tr 부싱탭어댑터 설치 - 부싱탭커버 제거 - 부싱탭어댑터 설치","2025-02-04 09:00","2025-02-04 18:00","2025-02-04 09:00","2025-02-04 18:00","연속"]
[2,"경기북부","구리","신가평S/S #3 M.Tr","신가평S/S 765kV M.Tr 고장복구공사","신가평S/S 765kV M.Tr 고장복구공사 - #3M.Tr 2차 부싱 교체 - #3M.Tr 2Tank 운전","2025-02-17 09:00","2025-03-02 18:00","2025-02-17 09:00","2025-03-02 18:00","연속"]
[3,"경북","영주","신한울N/P #2 Tie-Tr","신한울S/S 345kV GIS 용량교체공사","동해안변환소 건설 관련 기존설비 용량증대(345kV GIS x 2식 교체)","2025-02-06 08:00","2025-03-13 18:00","2025-02-06 08:00","2025-03-13 18:00","연속"]
[4,"부산울산","동부산","신고리N/P #1 Tie-Tr","신고리S/S #1M.Tr GAS 누기조치","신고리S/S #1M.Tr GAS 누기조치","2025-02-17 09:00","2025-02-21 18:00","2025-02-17 09:00","2025-02-21 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":46,"n_cols":11,"rows_kept":46,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2025년도 2월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","직할","신문래S/S #1 Sh.R CB","신문래S/S 362kV #1Sh.R 보통점검","신문래S/S 362kV #1Sh.R 보통점검","2025-02-24 08:00","2025-02-25 18:00","취소","취소","연속"]
[2,"남서울","직할","신문래S/S #3 Sh.R CB","신문래S/S 362kV #3Sh.R 정밀점검","신문래S/S 362kV #3Sh.R 정밀점검","2025-02-10 08:00","2025-02-21 18:00","취소","취소","연속"]
[3,"인천","시흥","신시화S/S CB 7400","신시화S/S 362kV 7400 GIS 점검","신시화S/S 362kV 7400 GIS 점검","2025-02-10 09:00","2025-02-10 18:00","2025-02-10 09:00","2025-02-10 18:00","연속"]
[4,"경기북부","구리","미금S/S #6 Sh.R CB","미금 용량부족 차단기 대체공사","#6Sh.R 인출변경","2025-02-24 09:00","2025-03-21 18:00","2025-02-24 09:00","2025-03-21 18:00","연속"]
[5,"경기북부","구리","미금성동#2 T/L","미금 용량부족 차단기 대체공사","#6Sh.R 인출변경","2025-02-28 09:00","2025-02-28 18:00","2025-02-28 09:00","2025-02-28 18:00","연속"]
[6,"경기북부","직할","양주S/S STATCOM CB","양주S/S STATCOM 하자점검공사","양주S/S STATCOM 밸브 및 수냉각설비 점검 양주S/S STATCOM C.Tr 및 부속설비 점검","2025-02-19 09:00","2025-03-07 18:00","2025-02-19 09:00","2025-03-07 18:00","연속"]
[7,"경기북부","직할","양주S/S STATCOM CB","양주S/S STATCOM 하자점검 공사","양주S/S STATCOM 밸브 및 수냉각설비 점검 양주S/S STATCOM C.Tr 및 부속설비 점검","2025-02-19 09:00","2025-03-07 18:00","취소","취소","연속"]
[8,"충북","청주","남청주S/S #2 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2025-02-24 08:00","2025-03-14 18:00","2025-02-24 08:00","2025-03-14 18:00","연속"]
[9,"대전세종충남","대전","신계룡S/S CB 7200","[즉시가압O] 신계룡S/S 345kV 7200 GIS 동작점검","[즉시가압O] 신계룡S/S 345kV 7200 GIS 동작점검 - 7200 GIS OCO 동작확인","2025-02-25 14:00","2025-02-25 18:00","2025-02-25 14:00","2025-02-25 18:00","연속"]
[10,"대전세종충남","대전","신계룡S/S CB 7271","[즉시가압O]신계룡S/S 345kV 신옥천-신계룡T/L GIS 조작점검","[즉시가압O]신계룡S/S 345kV 신옥천-신계룡T/L GIS 조작점검 - CB OCO 동작 확인","2025-02-25 09:00","2025-02-25 14:00","2025-02-25 09:00","2025-02-25 14:00","연속"]
[11,"대전세종충남","천안","신온양S/S CB 7571","345kV 북당진-신탕정T/L 건설공사(계통복원)","○ 공사 개요 : 345kV 북당진-신탕정T/L 건설공사의 장기지연에 따라 아산, 천안 지역 전력계통 안정화 대책으로 시행한「345kV 청양-신탕정T/L 임시선로」의 원상복구 및 345kV 북당진-신탕정#T/L 최초가압 ○ 공사 위치 : 신온양S/S","2025-02-10 07:00","2025-02-19 18:00","취소","취소","연속"]
[12,"대전세종충남","천안","신온양S/S CB 7500","345kV 북당진-신탕정T/L 건설공사(계통복원)","○ 공사 개요 : 345kV 북당진-신탕정T/L 건설공사의 장기지연에 따라 아산, 천안 지역 전력계통 안정화 대책으로 시행한「345kV 청양-신탕정T/L 임시선로」의 원상복구 및 345kV 북당진-신탕정#T/L 최초가압 ○ 공사 위치 : 신온양S/S","2025-02-10 07:00","2025-02-19 18:00","취소","취소","연속"]
[13,"대전세종충남","천안","청양신탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사(계통복원)","○ 공사 개요 : 345kV 북당진-신탕정T/L 건설공사의 장기지연에 따라 아산‧천안 지역 전력계통 안정화 대책으로 시행한「345kV 청양-신탕정T/L 임시선로」의 원상복구 및 345kV 북당진-신탕정#2 T/L 최초가압 ○ 공사 위치 : 신탕정S/S, 청양S/S, 청양-신탕정#1T/L No.149 북당진-신탕정#2T/L No.84~85","2025-02-10 07:00","2025-02-19 18:00","취소","취소","연속"]
[14,"대전세종충남","천안","북당진신탕정#2 T/L","345kV 북당진-신탕정T/L 건설공사(계통복원)","○ 공사 개요 : 345kV 북당진-신탕정T/L 건설공사의 장기지연에 따라 아산‧천안 지역 전력계통 안정화 대책으로 시행한「345kV 청양-신탕정T/L 임시선로」의 원상복구 및 345kV 북당진-신탕정#2 T/L 최초가압 ○ 공사 위치 : 북당진S/S, 신탕정S/S, 북당진-신탕정#2T/L No.84","2025-02-19 07:00","2025-02-19 18:00","취소","취소","연속"]
[15,"대전세종충남","천안","북당진신탕정#1 T/L","345kV 북당진-신탕정T/L 건설공사(계통복원)","○ 공사 개요 : 345kV 북당진-신탕정T/L 건설공사의 장기지연에 따라 아산‧천안 지역 전력계통 안정화 대책으로 시행한「345kV 청양-신탕정T/L 임시선로」의 원상복구 및 345kV 북당진-신탕정#2 T/L 최초가압 ○ 공사 위치 : 북당진S/S, 신탕정S/S, 청양-신탕정#1T/L No.149~150 북당진-신탕정#2T/L No.84~85","2025-02-15 07:00","2025-02-18 18:00","취소","취소","연속"]
[16,"대전세종충남","청양","청양보령CC T/L","보령복합S/Y 345kV 장기사용 GIS 교체 및 SW 증설","무부하가압 : BUS SEC #70-71-0 GIS, #71BUS PT","2025-02-28 14:00","2025-03-01 14:00","취소","취소","연속"]
[17,"대전세종충남","청양","보령C/C #71 BUS","보령복합S/Y 345kV 장기사용 GIS 교체 및 SW 증설","BUS SEC #70-71-0 GIS 설치, #71BUS PT 교체","2025-02-03 09:00","2025-03-05 18:00","취소","취소","연속"]
[18,"전북","군산","군산S/S #1 M.Tr","군산P/O 주변압기 점검공사","군산P/O 주변압기 점검공사","2025-02-18 09:00","2025-02-19 18:00","2025-02-18 09:00","2025-02-19 18:00","연속"]
[19,"전북","군산","군산신김제#2 T/L","345kV 군산-신김제#2T/L 품질불량 의심 접속함 교체공사","345kV 군산-신김제#2T/L(D) J/B#4 A상 중간접속함 해체 및 재접속","2025-02-10 09:00","2025-02-14 18:00","2025-02-10 09:00","2025-02-14 18:00","연속"]
[20,"전북","김제","신김제S/S #3 M.Tr","신김제S/S #2S.Tr 교체공사 관련 안전거리 확보 휴전","소내변압기 철거 및 설치 시 #3M.Tr 3차측 모선 동대와 크레인간 안전이격 거리 확보 휴전","2025-02-28 09:00","2025-02-28 18:00","취소","취소","연속"]
[21,"전북","직할","신남원S/S CB 7272","25년 전북직할 변전협력회사 공사","신남원 345kV GIS 보통점검","2025-02-26 09:00","2025-02-27 18:00","2025-02-26 09:00","2025-02-27 18:00","연속"]
[22,"전북","직할","신남원S/S CB 7200","25년 전북직할 변전협력회사 공사","신남원 345kV GIS 보통점검","2025-02-24 09:00","2025-02-25 18:00","2025-02-24 09:00","2025-02-25 18:00","연속"]
[23,"전북","직할","신남원신광주#2 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.1~115","2025-02-18 07:30","2025-02-25 18:00","2025-02-18 07:30","2025-02-25 18:00","매일"]
[24,"전북","직할","신남원신광주#1 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.1~115","2025-02-10 07:30","2025-02-17 18:00","취소","취소","매일"]
[25,"전북","직할","신남원광양#1 T/L","25년 전북직할 변전협력 총액공사","신남원-광양 #1 T/L LA A, B, C상 교체","2025-02-03 09:00","2025-02-03 18:00","2025-02-03 09:00","2025-02-03 18:00","연속"]
[26,"전북","직할","신옥천신남원#1 T/L","25년 전북직할 변전협력 총액공사","345kV 신옥천-신남원 #1 T/L LA A상 교체","2025-02-04 09:00","2025-02-04 18:00","2025-02-04 09:00","2025-02-04 18:00","연속"]
[27,"광주전남","순천","광양여수TP T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 설치","2025-02-17 07:00","2025-02-17 18:00","2025-02-17 07:00","2025-02-17 18:00","연속"]
[28,"대구","달성","고령S/S #2 M.Tr","고령S/S #2M.Tr 휴전","고령S/S #2M.Tr 휴전","2025-02-05 09:00","2025-02-05 18:00","2025-02-05 09:00","2025-02-05 18:00","연속"]
[29,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S 345kV 주변압기측 현대화 공사","#1M.Tr SA 수용작업","2025-02-10 09:00","2025-02-28 18:00","2025-02-10 09:00","2025-02-28 18:00","연속"]
[30,"경북","영주","신영주S/S #1 M.Tr","345kV #1M.Tr 보호배전반 DTCR 제거","345kV #1M.Tr 보호배전반 DTCR 제거","2025-02-12 09:00","2025-02-12 18:00","2025-02-12 09:00","2025-02-12 18:00","연속"]
[31,"경북","영주","신한울한울#2 T/L","500kV 동해안변환소 AC배후계통 연결T/L 건설공사","- 구간 : 500kV 동해안변환소~345kV 한울NP3S/Y-신한울NP1S/Y, 345kV 신영주~NP3S/Y - 선종 : ACSR/AW 480(C) - 철탑 : 신설 10기(산형강 6기, CT 4기), 철거 5기(산형강 5기)","2025-02-06 09:00","2025-02-14 18:00","2025-02-06 09:00","2025-02-14 18:00","매일"]
[32,"부산울산","동부산","신양산S/S #2 BUS","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(5차) - 71BAY GIS #2BUS측 설치","2025-02-15 10:00","2025-02-16 18:00","2025-02-15 10:00","2025-02-16 18:00","연속"]
[33,"부산울산","동부산","신양산북부산#2 T/L","345kV 신양산S/S STATCOM 건설사업(C.Tr 무부하가압선로)","345kV 신양산S/S STATCOM 건설사업(C.Tr 무부하가압선로) - 24시간 무부하가압 시행 - 신양산-북부산#2T/L, 345kV #1BUS 휴전","2025-02-06 17:00","2025-02-07 17:00","2025-02-22 09:00","2025-02-23 09:00","연속"]
[34,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S #2M.Tr 부싱절연유 추적분석","신양산S/S #2M.Tr 부싱절연유 채유(부싱절연유 채유 분석결과 이상에 따른 추적 분석)","2025-02-09 06:00","2025-02-09 09:00","취소","취소","연속"]
[35,"부산울산","동부산","신양산S/S #1 BUS","345kV 신양산S/S STATCOM 건설사업(C.Tr 무부하가압)","345kV 신양산S/S STATCOM 건설사업(C.Tr 무부하가압 모선휴전) - 24시간 무부하가압 - 신양산-북부산#2T/L, 345kV #1BUS 휴전","2025-02-06 17:00","2025-02-07 17:00","2025-02-22 09:00","2025-02-23 09:00","연속"]
[36,"부산울산","동부산","신양산S/S #1 BUS","신양산S/S 345kV 용량부족차단기 교체공사","신양산S/S 345kV 용량부족차단기 교체공사(5차) - 71BAY GIS #1BUS측 설치","2025-02-08 10:00","2025-02-09 18:00","2025-02-08 10:00","2025-02-09 18:00","연속"]
[37,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S 345kV #1M.Tr 증설공사","154kV 65-66/60-61SEC, 6200BT, 61-66PT&ES 증설(감압)","2025-02-17 09:00","2025-02-17 18:00","취소","취소","연속"]
[38,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S 345kV #1M.Tr 증설공사","154kV 65-66/60-61SEC, 6200BT, 61-66PT&ES 증설(감압)","2025-02-03 09:00","2025-02-03 18:00","취소","취소","연속"]
[39,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S 345kV #1M.Tr 증설공사","154kV 65-66/60-61SEC, 6200BT, 61-66PT&ES 증설(감압)","2025-02-21 09:00","2025-02-23 18:00","취소","취소","연속"]
[40,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S 345kV #1M.Tr 증설공사","154kV 65-66/60-61SEC, 6200BT, 61-66PT&ES 증설(감압)","2025-02-07 09:00","2025-02-09 18:00","취소","취소","연속"]
[41,"부산울산","울산","신온산남울산#1 T/L","25년 울산전력지사 변전협력회사공사","- 7471,7400 GIS 하자점검","2025-02-24 09:00","2025-02-24 18:00","2025-02-24 09:00","2025-02-24 18:00","연속"]
[42,"부산울산","울산","신온산남울산#2 T/L","25년 울산전력지사 변전협력회사공사","- 7371,7300 GIS 하자점검","2025-02-25 09:00","2025-02-25 18:00","2025-02-25 09:00","2025-02-25 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":137,"n_cols":11,"rows_kept":137,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 2월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","화양S/S #1 BUS","154kV 화양-성수#2T/L SW 증설공사","154kV BUSTIE, 군자-화양#1T/L 대체 154kV 화양-성수#2T/L 증설","2025-02-06 14:00","2025-02-20 14:00","취소","취소","연속"]
[2,"서울","성동","화양상봉#2 T/L","154kV 화양-성수#2T/L SW 증설공사","- #65BUS 휴전을 위한 부하절체용 휴전(BUSTIE 이용불가)","2025-02-20 14:00","2025-02-20 14:05","취소","취소","연속"]
[3,"서울","성동","화양S/S #2 BUS","154kV 화양-성수#2T/L SW 증설공사","154kV BUSTIE, 군자-화양#1T/L 대체 154kV 화양-성수#2T/L 증설","2025-02-20 14:00","2025-03-05 14:00","취소","취소","연속"]
[4,"서울","성동","화양상봉#1 T/L","154kV 화양-성수#2T/L SW 증설공사","- #60BUS 무부하 시험가압","2025-02-19 14:00","2025-02-20 14:05","취소","취소","연속"]
[5,"서울","성동","화양S/S #2 BUS","154kV 화양-성수#2T/L SW 증설공사","154kV BUSTIE, 군자-화양#1T/L 대체 154kV 화양-성수#2T/L 증설","2025-02-03 09:00","2025-02-06 14:00","취소","취소","연속"]
[6,"서울","성동","미금화양 T/L","154kV 화양-성수#2T/L SW 증설공사","- #60BUS 휴전을 위한 부하절체용 휴전(BUSTIE 이용불가)","2025-02-06 14:00","2025-02-06 14:05","취소","취소","연속"]
[7,"서울","성동","화양상봉#2 T/L","154kV 화양-성수#2T/L SW 증설공사","- #60BUS 휴전을 위한 부하절체용 휴전(BUSTIE 이용불가)","2025-02-06 14:00","2025-02-06 14:05","취소","취소","연속"]
[8,"서울","성동","화양상봉#1 T/L","154kV 화양-성수#2T/L SW 증설공사","- #65BUS 무부하 시험가압","2025-02-05 14:00","2025-02-06 14:05","취소","취소","연속"]
[9,"서울","직할","용두안암#2 T/L","'25년 직할 변전협력회사 공사","안암용두 #2T/L 에어 누기 보수","2025-02-26 09:00","2025-02-26 18:00","2025-02-26 09:00","2025-02-26 18:00","연속"]
[10,"남서울","동서울","산성수서#1 T/L","위례선 도시철도(트램) 건설공사","위례선 도시철도(트램) 건설(발주처:서울시 도시기반시설본부) - 고도제한 저지상고개소 공사현장의 이용시민 안전확보","2025-02-03 09:00","2025-06-30 18:00","2025-02-03 09:00","2025-06-30 18:00","연속"]
[11,"경기북부","고양","일산지도#1 T/L","손해배상 청구소송 관련 현장감정","사건번호 2021가합59625","2025-02-26 09:00","2025-02-26 18:00","취소","취소","연속"]
[12,"경기북부","구리","신포천포천#1 T/L","25-26년 지중송전 협력회사 공사","포천S/S 인입철구 보강을 위한 부재 실측","2025-02-27 09:00","2025-02-27 17:00","2025-02-27 09:00","2025-02-27 17:00","연속"]
[13,"경기북부","구리","포천운천#1 T/L","25-26년 지중송전 협력회사 공사","포천S/S 인입철구 보강을 위한 부재 실측","2025-02-27 09:00","2025-02-27 17:00","2025-02-27 09:00","2025-02-27 17:00","연속"]
[14,"충북","직할","삼죽광혜원 T/L","광혜원S/S 23kV 장기사용 GIS 대체공사(SA병행)","제어/감시/경보 제어케이블 RTU → LID 이설","2025-02-26 10:00","2025-02-27 12:00","2025-02-26 10:00","2025-02-27 12:00","연속"]
[15,"충북","청주","남청주S/S #66 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2025-02-24 08:00","2025-02-27 14:00","2025-02-24 08:00","2025-02-27 14:00","연속"]
[16,"충북","청주","남청주S/S #61 BUS","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2025-02-27 14:00","2025-03-07 14:00","2025-02-27 14:00","2025-03-07 14:00","연속"]
[17,"충북","청주","남청주청주#2 T/L","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2025-02-24 08:00","2025-03-14 18:00","2025-02-24 08:00","2025-03-14 18:00","연속"]
[18,"충북","청주","오창국사#2 T/L","154kV 신청주-문백T/L 건설공사","154kV 오창-국사 #2 T/L No.13~17 임시선로 구성 (임시철탑 설치 2기, 기설철탑 철거 3기 전력선 및 OPGW 이설, 4경간)","2025-02-24 07:00","2025-02-28 18:00","2025-02-24 07:00","2025-02-28 18:00","연속"]
[19,"대전세종충남","대전","신계룡두마#2 T/L","[송전][즉시가압O]345kV신옥천-청양등8개T/L 추락방지설치공사","[송전][즉시가압O]345kV 신옥천-청양 등 8개 T/L 추락방지 설치공사","2025-02-10 08:00","2025-02-14 12:00","2025-02-10 08:00","2025-02-14 12:00","매일"]
[20,"대전세종충남","대전","신계룡은진#2 T/L","[송전][즉시가압O]345kV신옥천-청양등8개T/L 추락방지설치공사","[송전][즉시가압O]345kV 신옥천-청양 등 8개 T/L 추락방지 설치공사","2025-02-10 08:00","2025-02-21 12:00","2025-02-10 08:00","2025-02-21 12:00","매일"]
[21,"대전세종충남","대전","은진함열#2 T/L","[송전][즉시가압O]345kV신옥천-청양등8개T/L 추락방지설치공사","[송전][즉시가압O]345kV 신옥천-청양 등 8개 T/L 추락방지 설치공사","2025-02-24 08:00","2025-02-28 17:00","2025-02-24 08:00","2025-02-28 17:00","매일"]
[22,"대전세종충남","대전","신옥천추부#2 T/L","[송전][즉시가압O]345kV신옥천-청양등8개T/L 추락방지설치공사","[송전][즉시가압O]345kV 신옥천-청양 등 8개 T/L 추락방지 설치공사","2025-02-03 08:00","2025-02-07 12:00","2025-02-03 08:00","2025-02-07 12:00","매일"]
[23,"대전세종충남","세종","덕진공주#2 T/L","154kV 덕진-공주T/L No.6-7 허가벌채","154kV 덕진-공주T/L No.6-7 허가벌채","2025-02-27 08:00","2025-02-27 18:00","2025-02-27 08:00","2025-02-27 18:00","연속"]
[24,"대전세종충남","세종","덕진공주#1 T/L","154kV 덕진-공주T/L No.6-7 허가벌채","154kV 덕진-공주T/L No.6-7 허가벌채","2025-02-28 08:00","2025-02-28 18:00","2025-02-28 08:00","2025-02-28 18:00","연속"]
[25,"대전세종충남","세종","세종월산#1 T/L","월산S/S 154kV 장기사용 GIS 교체공사","월산S/S 154kV 장기사용 GIS 교체공사(무부하가압)","2025-02-27 09:00","2025-02-28 18:00","취소","취소","연속"]
[26,"대전세종충남","세종","세종월산#1 T/L","월산S/S 154kV 장기사용 GIS 교체공사","월산S/S 154kV 장기사용 GIS 교체공사(무부하가압)","2025-02-20 09:00","2025-02-21 18:00","취소","취소","연속"]
[27,"대전세종충남","직할","둔곡송강#2 T/L","154kV 둔곡-송강T/L 지장수목전지 및 벌채","154kV 둔곡-송강#2T/L 지장수목전지 및 벌채","2025-02-25 09:00","2025-02-26 18:00","취소","취소","매일"]
[28,"대전세종충남","직할","둔곡송강#1 T/L","154kV 둔곡-송강T/L 지장수목전지 및 벌채(주말 제외)","154kV 둔곡-송강#1T/L 지장수목전지 및 벌채","2025-02-21 09:00","2025-02-24 18:00","취소","취소","매일"]
[29,"전북","군산","군산서군산#1 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-02-24 09:00","2025-02-25 18:00","취소","취소","연속"]
[30,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검공사","군산P/O 170kV GIS 정밀점검공사","2025-02-26 09:00","2025-02-27 18:00","취소","취소","연속"]
[31,"전북","군산","내초군장#2 T/L","군산P/O 154kV이상 차단기 점검공사","군산P/O 154kV이상 차단기 점검공사","2025-02-06 09:00","2025-02-06 18:00","2025-02-06 09:00","2025-02-06 18:00","연속"]
[32,"전북","군산","내초군장#1 T/L","군산P/O 154kV이상 차단기 점검공사","군산P/O 154kV이상 차단기 점검공사","2025-02-05 09:00","2025-02-05 18:00","2025-02-05 09:00","2025-02-05 18:00","연속"]
[33,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2025-02-25 09:00","2025-02-27 18:00","취소","취소","연속"]
[34,"전북","군산","서군산소룡#2 T/L","군산P/O 154kV이상 차단기 점검공사","군산P/O 154kV이상 차단기 점검공사","2025-02-28 09:00","2025-02-28 18:00","취소","취소","연속"]
[35,"전북","군산","서군산소룡#1 T/L","154kV 서군산-소룡#1T/L 구형 공법 EBA 구조개선 공사","일진제 구형 공법 EBA 구조개선 공사","2025-02-17 09:00","2025-02-21 18:00","취소","취소","연속"]
[36,"전북","군산","영등낭산#2 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2025-02-03 07:00","2025-02-03 18:00","2025-02-10 07:00","2025-02-11 18:00","연속"]
[37,"전북","군산","영등팔봉#2 T/L","154kV 영등-팔봉T/L 일부 지중화공사","1) 선종 및 길이 : XLPE 2000㎟, 1.4km 2) 케이블 접속구간 ○ 종단접속 : 4개소【EBA 2개소, EBG 2개소】 ○ 중간접속 : 4개소【PMIJ 4개소】","2025-02-03 09:00","2025-02-12 18:00","취소","취소","연속"]
[38,"전북","군산","영등낭산#1 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2025-02-04 07:00","2025-02-12 18:00","2025-02-12 07:00","2025-02-22 18:00","연속"]
[39,"전북","군산","영등낭산#2 T/L","154kV 영등-낭산T/L 안전이격 확보공사","□ 공사개요 □ 철탑공사 : 설치(6기), 철거(7기) □ 전력선 교체 : 0.732C-㎞ □ 임시선로 철거 및 기타 부대공사","2025-02-13 07:00","2025-02-21 18:00","2025-02-23 07:00","2025-03-02 18:00","연속"]
[40,"전북","군산","영등팔봉#1 T/L","154kV 영등-팔봉T/L 일부 지중화공사","1) 선종 및 길이 : XLPE 2000㎟, 1.4km 2) 케이블 접속구간 ○ 종단접속 : 4개소【EBA 2개소, EBG 2개소】 ○ 중간접속 : 4개소【PMIJ 4개소】","2025-02-13 09:00","2025-02-22 18:00","취소","취소","연속"]
[41,"전북","군산","이리백산#2 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-02-03 08:00","2025-02-07 18:00","취소","취소","연속"]
[42,"전북","군산","이리백산#1 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-02-08 08:00","2025-02-15 18:00","취소","취소","연속"]
[43,"전북","군산","탄소이리#1 T/L","군산P/O 154kV이상 차단기 점검공사","군산P/O 154kV이상 차단기 점검공사","2025-02-24 15:00","2025-02-24 18:00","2025-02-24 15:00","2025-02-24 18:00","연속"]
[44,"전북","군산","이리백산#2 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-02-16 08:00","2025-02-20 18:00","취소","취소","연속"]
[45,"전북","군산","탄소이리#2 T/L","군산P/O 154kV이상 차단기 점검공사","군산P/O 154kV이상 차단기 점검공사","2025-02-25 15:00","2025-02-25 18:00","2025-02-25 15:00","2025-02-25 18:00","연속"]
[46,"전북","군산","팔봉왕궁#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-02-11 08:00","2025-02-11 18:00","취소","취소","매일"]
[47,"전북","군산","팔봉왕궁#2 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-02-12 08:00","2025-02-12 18:00","취소","취소","매일"]
[48,"전북","군산","팔봉두마#2 T/L","154kV 팔봉두마T/L No.14~17 일부구간지중화 C/T설치공사","지중화 : No.14~17 약 400m 전선교체 : 1.524C-km 철탑설치철거 : 15,16호","2025-02-01 08:00","2025-02-05 18:00","취소","취소","연속"]
[49,"전북","군산","은진함열#1 T/L","'24~25년 군산전력지사 변전협력회사 총액공사","-노후배전반 대체공사","2025-02-26 09:00","2025-02-28 18:00","취소","취소","연속"]
[50,"전북","김제","소성고창#1 T/L","고창S/S 고창-영광T/L GIS 정밀점검(연속)","고창S/S 고창-영광T/L GIS 정밀점검 단로기포함(연속)","2025-02-04 10:00","2025-02-05 18:00","취소","취소","매일"]
[51,"전북","김제","고창영광 T/L","고창S/S 고창-영광T/L GIS 정밀점검(연속)","고창S/S 고창-영광T/L GIS 정밀점검 단로기포함(연속)","2025-02-03 09:00","2025-02-05 18:00","취소","취소","연속"]
[52,"전북","김제","소성고창#2 T/L","고창S/S 고창-홍농T/L GIS 정밀점검(연속)","고창S/S 고창-홍농T/L GIS 정밀점검 단로기포함(연속)","2025-02-11 10:00","2025-02-12 18:00","취소","취소","매일"]
[53,"전북","김제","고창홍농 T/L","고창S/S 고창-홍농T/L GIS 정밀점검(연속)","고창S/S 고창-홍농T/L GIS 정밀점검 단로기포함(연속)","2025-02-10 09:00","2025-02-12 18:00","취소","취소","연속"]
[54,"전북","김제","담양김제 T/L","154kV 정공-정주 등 3개T/L 추락방지장치 설치공사","- 공사구간 : 154kV 담양-김제T/L No.92 수평 추락방지장치 설치공사","2025-02-27 07:00","2025-02-27 17:00","2025-02-27 07:00","2025-02-27 17:00","연속"]
[55,"전북","김제","백산김제#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-02-20 08:00","2025-02-20 18:00","2025-02-20 08:00","2025-02-20 18:00","매일"]
[56,"전북","김제","김제칠보HP T/L","154kV 정공-정주 등 3개T/L 추락방지장치 설치공사","- 공사구간 : 154kV 담양-김제(김제-칠보)T/L No.83 수평 추락방지장치 설치공사","2025-02-26 07:00","2025-02-26 17:00","2025-02-26 07:00","2025-02-26 17:00","연속"]
[57,"전북","김제","백산김제#2 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-02-21 08:00","2025-02-21 18:00","2025-02-21 08:00","2025-02-21 18:00","매일"]
[58,"전북","김제","부안동부안#2 T/L","부안S/S 동부안-부안#2T/L GIS 정밀점검(연속)","부안S/S 동부안-부안#2T/L GIS 정밀점검 단로기포함(연속)","2025-02-17 09:00","2025-02-19 18:00","2025-02-17 09:00","2025-02-19 18:00","연속"]
[59,"전북","김제","백산김제#1 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-02-16 08:00","2025-02-20 18:00","취소","취소","연속"]
[60,"전북","김제","백산김제#2 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-02-08 08:00","2025-02-15 18:00","취소","취소","연속"]
[61,"전북","김제","백산김제#1 T/L","154kV 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-02-03 08:00","2025-02-07 18:00","취소","취소","연속"]
[62,"전북","김제","신김제동전주#2 T/L","154kV 완산분기T/L 건설공사","- 작업내용 : #2T/L 본선로 구성 - 위 치 : 전주시 완산구 석구동 일원 - 규 모 : ACSR410㎟ × 2B × 4C (0.81km, 지지물 4기)","2025-02-26 07:00","2025-02-28 18:00","2025-02-26 07:00","2025-02-28 18:00","연속"]
[63,"전북","김제","남원임실#2 T/L","임실S/S 154kV 남원-임실#2T/L 차단기 보통점검","임실S/S 154kV 남원-임실#2T/L 차단기 보통점검","2025-02-07 09:00","2025-02-07 18:00","취소","취소","연속"]
[64,"전북","김제","남원임실#1 T/L","임실S/S 154kV 남원-임실#1T/L 차단기 보통점검","임실S/S 154kV 남원-임실#1T/L 차단기 보통점검","2025-02-06 09:00","2025-02-06 18:00","취소","취소","연속"]
[65,"전북","김제","정공칠보HP T/L","154kV 정공-정주 등 3개T/L 추락방지장치 설치공사","- 공사구간 : 154kV 정공분기(정공칠보)T/L No.0.1~13 수평 추락방지장치 설치공사","2025-02-24 07:00","2025-02-26 17:00","2025-02-24 07:00","2025-02-26 17:00","연속"]
[66,"전북","김제","정공담양 T/L","154kV 정공-정주 등 3개T/L 추락방지장치 설치공사","- 공사구간 : 154kV 담양-김제(정공-담양)T/L No.92~118 수평 추락방지장치 설치공사","2025-02-27 07:00","2025-03-01 17:00","2025-02-27 07:00","2025-03-01 17:00","연속"]
[67,"전북","김제","정공정주#1 T/L","154kV 정공-정주 등 3개T/L 추락방지장치 설치공사","- 공사구간 : 154kV 정공-정주#1T/L No.0.1~13 수평 추락방지장치 설치공사","2025-02-24 07:00","2025-02-26 17:00","취소","취소","연속"]
[68,"전북","김제","정주동부안#1 T/L","정주S/S 정주-동부안#1T/L GIS 정밀점검(연속)","정주S/S 정주-동부안#1T/L GIS 정밀점검(연속)","2025-02-24 09:00","2025-02-25 18:00","2025-02-20 09:00","2025-02-21 18:00","연속"]
[69,"전북","김제","정주동부안#2 T/L","정주S/S 정주-동부안#2T/L GIS 정밀점검(연속)","정주S/S 정주-동부안#2T/L GIS 정밀점검(연속)","2025-02-26 09:00","2025-02-27 18:00","2025-02-11 09:00","2025-02-12 18:00","연속"]
[70,"전북","직할","동전주북전주#1 T/L","25년도 직할 변전협력회사 총액공사(기타기기)","25년도 직할 변전협력회사 총액공사(기타기기) LA A, B, C상 보통점검","2025-02-24 09:00","2025-02-24 18:00","취소","취소","연속"]
[71,"전북","직할","동전주북전주#2 T/L","25년도 직할 변전협력회사 총액공사(기타기기)","25년도 직할 변전협력회사 총액공사(기타기기) LA A, B, C상 보통점검","2025-02-25 09:00","2025-02-25 18:00","취소","취소","연속"]
[72,"전북","직할","금산무주#2 T/L","25년도 직할 변전협력회사 총액공사(기타기기)","25년도 직할 변전협력회사 총액공사(기타기기) LA A, B, C상 보통점검","2025-02-19 15:00","2025-02-19 18:00","2025-02-19 15:00","2025-02-19 18:00","연속"]
[73,"전북","직할","무주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.50~104","2025-02-20 07:30","2025-02-22 18:00","취소","취소","연속"]
[74,"전북","직할","금산무주#1 T/L","25년도 직할 변전협력회사 총액공사(기타기기)","25년도 직할 변전협력회사 총액공사(기타기기) LA A, B, C상 보통점검","2025-02-20 15:00","2025-02-20 18:00","2025-02-20 15:00","2025-02-20 18:00","연속"]
[75,"전북","직할","왕궁봉동#2 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-02-25 08:00","2025-02-25 18:00","취소","취소","매일"]
[76,"전북","직할","왕궁봉동#1 T/L","154kV 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-02-24 08:00","2025-02-24 18:00","취소","취소","매일"]
[77,"전북","직할","북전주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.1~50","2025-02-17 07:30","2025-02-19 18:00","취소","취소","연속"]
[78,"전북","직할","북전주봉동#1 T/L","북전주-봉동#1T/L 송전선로 보호반 대체공사","북전주-봉동#1T/L 송전선로 보호반 대체공사","2025-02-03 09:00","2025-02-07 18:00","취소","취소","연속"]
[79,"전북","직할","북전주봉동#2 T/L","북전주-봉동#2T/L 송전선로 보호반 대체공사","북전주-봉동#2T/L 송전선로 보호반 대체공사","2025-02-10 09:00","2025-02-14 18:00","취소","취소","연속"]
[80,"전북","직할","북전주S/S CB 6100","북전주변전소 모선보호반 교체공사","북전주변전소 모선보호반 교체공사","2025-02-24 09:00","2025-02-28 18:00","2025-02-24 09:00","2025-02-28 18:00","연속"]
[81,"전북","직할","신남원남원#2 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.1~115 ○ No.3~6 4회선 구간 작업안전을 위한 휴전","2025-02-24 07:30","2025-02-25 18:00","2025-02-06 07:30","2025-02-07 18:00","매일"]
[82,"전북","직할","신남원S/S #2 EM.Tr CB","신남원 ESS 변전설비 #2EM.Bank 초기점검","변압기 1대, 170gis 1대, 23kV gis 8대, EP.Tr 7대","2025-02-17 09:00","2025-02-21 18:00","2025-02-17 09:00","2025-02-21 18:00","연속"]
[83,"전북","직할","신남원S/S #1 EM.Tr CB","신남원 ESS 변전설비 #1EM.Bank 초기점검","변압기 1대, 170gis 1대, 23kV gis 8대, EP.Tr 7대","2025-02-10 09:00","2025-02-14 18:00","2025-02-10 09:00","2025-02-14 18:00","연속"]
[84,"전북","직할","탄소전주#1 T/L","탄소S/S 세니온제 IED 유사고장 성능개선","불량소자(MAX488) 취부된 H/W 보드 교체 및 IED Fail 출력 로직 수정","2025-02-13 14:30","2025-02-13 16:00","취소","취소","연속"]
[85,"전북","직할","탄소이리#2 T/L","탄소S/S 세니온제 IED 유사고장 성능개선","불량소자(MAX488) 취부된 H/W 보드 교체 및 IED Fail 출력 로직 수정","2025-02-13 13:00","2025-02-13 14:30","취소","취소","연속"]
[86,"전북","직할","탄소이리#1 T/L","탄소S/S 세니온제 IED 유사고장 성능개선","불량소자(MAX488) 취부된 H/W 보드 교체 및 IED Fail 출력 로직 수정","2025-02-13 10:00","2025-02-13 11:30","취소","취소","연속"]
[87,"전북","직할","탄소전주#2 T/L","탄소S/S 세니온제 IED 유사고장 성능개선","불량소자(MAX488) 취부된 H/W 보드 교체 및 IED Fail 출력 로직 수정","2025-02-13 16:00","2025-02-13 17:30","취소","취소","연속"]
[88,"광주전남","강진","강진남창#2 T/L","154kV 영신분기T/L 건설공사","○ 임시선로 → 본선로 공중이동 - (NO.53 - 가철탑 - NO.54) → (NO.53 - C/T#1 , C/T#2 - NO.54) ○ 무부하 시험 및 사용 전 검사","2025-02-17 07:00","2025-02-28 18:00","2025-02-17 07:00","2025-02-28 18:00","연속"]
[89,"광주전남","강진","강진남창#1 T/L","154kV 영신분기T/L 건설공사","○ 임시선로 → 본선로 공중이동 - (NO.53 - 가철탑 - NO.54) → (NO.53 - C/T#1 , C/T#2 - NO.54) ○ 무부하 시험 및 사용 전 검사","2025-02-03 07:00","2025-02-14 18:00","2025-02-03 07:00","2025-02-14 18:00","연속"]
[90,"광주전남","강진","삼호화원#1 T/L","154kV 삼호-화원 지중T/L(복도체화) 건설공사","154kV XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2025-02-24 09:00","2025-03-31 18:00","취소","취소","연속"]
[91,"광주전남","목포","화원안좌#2 T/L","화원-안좌 #2T/L OPGW 신설 공사","가. OPGW 교체구간 : 화원-안좌 T/L No.24-47호 나. 공사내역 1) OPGW 연선 : 2.781km(200SQ, 48C), 6.801km(200SQ, 48C) 2) OPGW 긴선 긴선 철거 : 현수 철탑 14기, 내장 12기 3) 접속함체 교체 : 5개소 4) 항공장애표시구 시설 : 25조 다. 기타 사항","2025-02-10 09:00","2025-02-18 18:00","취소","취소","연속"]
[92,"광주전남","목포","엄다목포#1 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","#1BUS측 무부하가압용","2025-02-21 10:00","2025-02-22 10:00","2025-02-21 10:00","2025-02-22 10:00","연속"]
[93,"광주전남","목포","나주엄다#2 T/L","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","나주-엄다#2T/L, #1M.Tr 1차 GIS 교체","2025-02-03 09:00","2025-03-12 18:00","2025-02-03 09:00","2025-03-12 18:00","연속"]
[94,"광주전남","목포","엄다S/S #1 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","#1DS, CB, #1BUS 철거 및 설치","2025-02-05 14:00","2025-02-21 18:00","2025-02-05 14:00","2025-02-21 18:00","연속"]
[95,"광주전남","목포","엄다S/S #2 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","#2DS측 철거","2025-02-03 09:00","2025-02-05 14:00","2025-02-03 09:00","2025-02-05 14:00","연속"]
[96,"광주전남","목포","엄다S/S #2 BUS","엄다S/S 154kV 이하 장기사용 GIS 교체(Digital화)공사","#2DS, #2BUS 설치","2025-02-24 09:00","2025-03-12 10:00","2025-02-24 09:00","2025-03-12 10:00","연속"]
[97,"광주전남","목포","영광홍농 T/L","154kV 영광-홍농 등 4개T/L 선종교체공사","1. 공사명 : 154kV 영광-홍농 등 4개T/L 선종교체공사 2. 공사내용 ○ 24.10.14~24.11.22 (4회선 하단) 영광-홍농T/L 선종교체공사(연속휴전 송전운영부) ※ 4회선구간 : 영황-홍농 선종교체공사를 위해 장성-영광#1 안전휴전 (매일휴전_송전운영부)","2025-02-03 07:00","2025-03-07 18:00","취소","취소","연속"]
[98,"광주전남","목포","장성영광#1 T/L","154kV 영광-홍농 등 4개T/L 선종교체공사","1. 공사명 : 154kV 영광-홍농 등 4개T/L 선종교체공사 2. 공사내용 ○ 24.10.14~24.11.22 (4회선 하단) 영광-홍농T/L 선종교체공사(연속휴전 송전운영부) ※ 4회선구간 : 영황-홍농 선종교체공사를 위해 장성-영광#1 안전휴전 (매일휴전_송전운영부)","2025-02-03 07:00","2025-02-26 18:00","취소","취소","연속"]
[99,"광주전남","순천","순천승주#2 T/L","154kV 순천-승주T/L 지중화 연장공사(요청자 직접시행)","154kV 순천-승주T/L 지중화 연장공사(요청자 직접시행) ○ 요청자 : 그린산업개발 주식회사 ○ 시공사 : 주식회사 한백 ○ 감리사 : 더원엔지니어링 주식회사","2025-02-24 09:00","2025-03-09 18:00","2025-02-24 09:00","2025-03-09 18:00","연속"]
[100,"광주전남","순천","순천승주#1 T/L","154kV 순천-승주T/L 지중화 연장공사(요청자 직접시행)","154kV 순천-승주T/L 지중화 연장공사(요청자 직접시행) ○ 요청자 : 그린산업개발 주식회사 ○ 시공사 : 주식회사 한백 ○ 감리사 : 더원엔지니어링 주식회사","2025-02-10 09:00","2025-02-23 18:00","2025-02-10 09:00","2025-02-23 18:00","연속"]
[101,"광주전남","순천","호남TP여수TP#2 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 설치","2025-02-17 07:00","2025-02-17 12:00","취소","취소","연속"]
[102,"광주전남","순천","여수TP화치#1 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 설치","2025-02-17 12:00","2025-02-17 18:00","취소","취소","연속"]
[103,"광주전남","순천","용성여수산단#1 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-02-13 07:00","2025-02-13 13:00","2025-02-13 07:00","2025-02-13 13:00","연속"]
[104,"광주전남","순천","여수TP용성#2 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-02-13 13:00","2025-02-13 18:00","취소","취소","연속"]
[105,"광주전남","순천","용성여수산단#2 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-02-13 13:00","2025-02-13 18:00","2025-02-13 13:00","2025-02-13 18:00","연속"]
[106,"광주전남","순천","여수TP용성#1 T/L","154kV 여수TP-용성T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-02-13 07:00","2025-02-13 13:00","취소","취소","연속"]
[107,"광주전남","순천","율촌여수산단#1 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-02-03 07:00","2025-02-05 18:00","취소","취소","매일"]
[108,"광주전남","순천","율촌여수산단#1 T/L","율촌S/S 154kV 포스코퓨처엠T/L GIS 증설공사(즉시가압 가능)","1CCT 증설, 즉시가압 가능","2025-02-03 09:00","2025-02-14 18:00","취소","취소","연속"]
[109,"광주전남","순천","율촌민자#1 T/L","154kV 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-02-10 07:00","2025-02-10 18:00","2025-02-10 07:00","2025-02-10 18:00","연속"]
[110,"광주전남","순천","율촌민자#2 T/L","154kV 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-02-11 07:00","2025-02-11 18:00","2025-02-11 07:00","2025-02-11 18:00","연속"]
[111,"광주전남","순천","율촌여수산단#2 T/L","154kV 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-02-06 07:00","2025-02-07 18:00","취소","취소","매일"]
[112,"대구","달성","다사달서 T/L","[안전확보]2024년 가공송전 순시점검 위탁공사","154kV 강창분기(강창-다사T/L) 초기점검 강창-분기 No.5호 작업 관련 안전확보","2025-02-18 09:00","2025-02-19 13:00","2025-02-18 09:00","2025-02-19 13:00","매일"]
[113,"대구","칠곡","고아어모#2 T/L","154kV 고아-어모T/L No.64 안전이격확보공사","154kV 고아-어모T/L No.64 가선로 구성에 따른 전선 공중이동","2025-02-24 07:00","2025-02-26 18:00","2025-02-24 07:00","2025-02-26 18:00","연속"]
[114,"대구","칠곡","고아어모#1 T/L","154kV 고아-어모T/L No.64 안전이격확보공사","154kV 고아-어모T/L No.64 가선로 구성에 따른 전선 공중이동","2025-02-27 07:00","2025-02-28 18:00","2025-02-27 07:00","2025-02-28 18:00","연속"]
[115,"경북","직할","봉화현종산풍력 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","154kV 봉화-현종산풍력T/L 철탑 암 이동용 안전발판설치","2025-02-19 08:00","2025-02-20 18:00","2025-02-19 08:00","2025-02-20 18:00","연속"]
[116,"경북","직할","울진현종산풍력 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","154kV 울진-현종산풍력T/L 철탑암이동용 안전발판설치공사","2025-02-17 08:00","2025-02-18 18:00","2025-02-17 08:00","2025-02-18 18:00","연속"]
[117,"경북","직할","현종산풍력평해#1 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","154kV 현종산풍력-평해T/L 철탑암이동용 안전발판설치공사","2025-02-24 08:00","2025-02-25 18:00","2025-02-24 08:00","2025-02-25 18:00","연속"]
[118,"경북","직할","현종산풍력평해#2 T/L","'24~25년 경북 직할 가공송전 협력회사 공사","154kV 현종산풍력-평해T/L 철탑암이동용 안전발판설치공사","2025-02-26 08:00","2025-02-27 18:00","2025-02-26 08:00","2025-02-27 18:00","연속"]
[119,"부산울산","동부산","정관장안#2 T/L","정관, 장안S/S 정관-장안#2T/L 세니온제 성능개선 시행","정관, 장안S/S 정관-장안#2T/L 세니온제 성능개선 시행","2025-02-12 09:30","2025-02-12 17:00","2025-02-12 09:30","2025-02-12 17:00","연속"]
[120,"부산울산","동부산","정관장안#1 T/L","정관, 장안S/S 정관-장안#1T/L 세니온제 성능개선 시행","정관, 장안S/S 정관-장안#1T/L 세니온제 성능개선 시행","2025-02-11 09:30","2025-02-11 17:00","2025-02-11 09:30","2025-02-11 17:00","연속"]
[121,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○3차분 (미음-녹산#1T/L, #1M.Tr 1차 대체, 기존BUS-TIE 철거) - 기존BUS-TIE #6202DS 철거 및 ENDCOVER 취부 - #2BUS 시험가압 (2DS 개방상태) 1시간 - 시험가압선로 (신녹산-녹산#1T/L)","2025-02-06 17:00","2025-02-06 18:00","2025-02-27 17:00","2025-02-27 18:00","연속"]
[122,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○3차분 (미음-녹산#1T/L, #1M.Tr 1차 대체, 기존BUS-TIE 철거) - 기존BUS-TIE #6202DS 철거 및 ENDCOVER 취부 - #2BUS 시험가압 (2DS 개방상태) 1시간 - 시험가압선로 (신녹산-녹산#1T/L)","2025-02-04 17:00","2025-02-04 18:00","2025-02-25 17:00","2025-02-25 18:00","연속"]
[123,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○3차분 (미음-녹산#1T/L, #1M.Tr 1차 대체, 기존BUS-TIE 철거) - #1BUS 시험가압 (1DS 개방상태) 24시간 - 시험가압선로 (신녹산-녹산#1T/L)","2025-02-25 17:00","2025-02-26 17:00","취소","취소","연속"]
[124,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 ○3차분 (미음-녹산#1T/L, #1M.Tr 1차 대체, 기존BUS-TIE 철거) - #2BUS 시험가압 (2DS 개방상태) 24시간 - 시험가압선로 (신녹산-녹산#1T/L)","2025-02-28 17:00","2025-03-01 17:00","취소","취소","연속"]
[125,"부산울산","서부산","미음녹산#1 T/L","녹산S/S 154kV 장기사용 GIS 교체공사","154kV GIS 7BAY 대체 - 3차분 (미음-녹산 #1T/L, #1M.Tr 1차 대체, 기존BUS-TIE 철거)","2025-02-03 09:00","2025-03-07 18:00","2025-02-24 09:00","2025-03-28 18:00","연속"]
[126,"부산울산","서부산","신녹산S/S #1 Sh.C CB","신녹산S/S 345kV #1M.Tr 증설공사","154kV 65-66/60-61SEC, 6200BT, 61-66PT&ES 증설(감압)","2025-02-03 09:00","2025-02-23 18:00","취소","취소","연속"]
[127,"부산울산","서부산","신녹산S/S #1 BUS","신녹산S/S 345kV #1M.Tr 증설공사","154kV 65-66/60-61SEC, 6200BT, 61-66PT&ES 증설","2025-02-17 09:00","2025-02-28 18:00","취소","취소","연속"]
[128,"부산울산","서부산","신녹산S/S #2 BUS","신녹산S/S 345kV #1M.Tr 증설공사","154kV 65-66/60-61SEC, 6200BT, 61-66PT&ES 증설","2025-02-03 09:00","2025-02-14 18:00","취소","취소","연속"]
[129,"경남","김해송변전부","김해S/S #1 M.Tr CB","김해S/S 변압기실 수직도어 교체공사","김해S/S 변압기실 수직도어 교체공사","2025-02-03 09:00","2025-02-21 18:00","취소","취소","연속"]
[130,"경남","함안","부북밀양#2 T/L","부북S/S 154kV 부북-밀양#2T/L GIS 초기점검","부북S/S 154kV 부북-밀양#2T/L GIS 초기점검","2025-02-11 09:30","2025-02-11 17:30","2025-02-11 09:30","2025-02-11 17:30","연속"]
[131,"경남","함안","부북밀양#1 T/L","부북S/S 154kV 부북-밀양#1T/L GIS 초기점검","부북S/S 154kV 부북-밀양#1T/L GIS 초기점검","2025-02-10 09:30","2025-02-10 17:30","2025-02-10 09:30","2025-02-10 17:30","연속"]
[132,"경남","함안","청도부북#1 T/L","부북S/S 154kV 청도-부북#1T/L GIS 초기점검","부북S/S 154kV 청도-부북#1T/L GIS 초기점검","2025-02-12 09:30","2025-02-12 17:30","2025-02-12 09:30","2025-02-12 17:30","연속"]
[133,"경남","함안","청도부북#2 T/L","부북S/S 154kV 청도-부북#2T/L GIS 초기점검","부북S/S 154kV 청도-부북#2T/L GIS 초기점검","2025-02-13 09:30","2025-02-13 17:30","2025-02-13 09:30","2025-02-13 17:30","연속"]