{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":11,"n_cols":12,"rows_kept":11,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 4월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #4 M.Tr","신가평S/S kV #4M.Tr 복구공사","신가평S/S kV #4M.Tr 복구공사 - M.Tr 반입","2025-04-23 09:00","2025-05-07 18:00","2025-04-23 09:00","2025-05-07 18:00","연속"]
[2,"경기북부","구리","신안성신가평 T/L","\"\"kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","신안성-신가평T/L 고광도 항공장애등 설치 : No.131,132,146,147","2025-04-07 07:00","2025-04-10 18:00","취소","취소","연속"]
[3,"대전세종충남","서산","당진T/P CB 8471","25년 서산P/O \"\"kV GIS 보통점검공사","(즉시가압가능) 당진TP  신서산-당진TP 8471 GIS 보통점검","2025-04-08 09:30","2025-04-09 18:00","2025-04-08 09:30","2025-04-09 18:00","연속"]
[4,"대전세종충남","서산","당진T/P CB 8400","25년 서산P/O \"\"kV GIS 보통점검공사","(즉시가압가능) 당진TP  신서산#2TL-4호기 TIE 8400 GIS 보통점검","2025-04-10 09:30","2025-04-11 18:00","2025-04-10 09:30","2025-04-11 18:00","연속"]
[5,"대전세종충남","서산","신서산S/S CB 8400","25년 서산P/O \"\"kV GIS 보통점검공사","(즉시가압가능) 신서산S/S  신서산-당진화력#1T/L TIE 8400 GIS 보통점검","2025-04-24 09:30","2025-04-25 18:00","2025-04-24 09:30","2025-04-25 18:00","연속"]
[6,"대전세종충남","서산","신서산S/S CB 8371","25년 서산P/O \"\"kV GIS 보통점검공사","(즉시가압가능) 신서산S/S  신서산-당진화력#2T/L 8371 GIS 보통점검","2025-04-22 09:30","2025-04-23 18:00","2025-04-22 09:30","2025-04-23 18:00","연속"]
[7,"부산울산","동부산","신고리N/P #3 M.Tr","동부산전력지사 변전총액공사","고리NP S/Y 신양산-고리#2T/L, 7A B/F PNL 대체","2025-04-01 09:00","2025-04-05 18:00","취소","취소","연속"]

{"sheet":"345설비","index":1,"n_rows":323,"n_cols":12,"rows_kept":323,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2025년도 4월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr","2025년 성동P/O 변전협력회사 공사","- GIB 가스누기 개소 조치","2025-04-14 09:00","2025-04-17 18:00","2025-04-14 09:00","2025-04-17 18:00","연속"]
[2,"서울","중부","중부S/S #4 M.Tr","2025년 중부S/S 154kV 장기사용 GIS 교체공사(1차)","- 154kV #65BUS 모선 무부하가압용","2025-04-04 17:00","2025-04-07 09:00","2025-04-08 17:00","2025-04-09 09:00","연속"]
[3,"서울","중부","중부S/S #3 M.Tr","2025년 중부전력지사 변전협력회사 공사","- 1차 GIS 보통점검(7452,7462,7422) - 2차 GIS 초기점검","2025-04-08 10:00","2025-04-08 18:00","2025-04-08 10:00","2025-04-08 18:00","연속"]
[4,"서울","중부","중부S/S #4 M.Tr","2025년 중부S/S 154kV 장기사용 GIS 교체공사(1차)","- 154kV #60BUS 모선 무부하가압용","2025-04-18 17:00","2025-04-21 09:00","2025-04-21 17:00","2025-04-22 09:00","연속"]
[5,"서울","중부","중부S/S #1 M.Tr","2025년 중부전력지사 변전협력회사 공사","- #1 M.Tr 보통점검 - 1차 GIS 조작시험(7152,7162,7122) - 2차 GIS 조작시험","2025-04-09 10:00","2025-04-11 18:00","2025-04-09 10:00","2025-04-11 18:00","연속"]
[6,"서울","중부","중부S/S #2 M.Tr","2025년 중부전력지사 변전협력회사 공사","- 1차 GIS 보통점검(7252,7262,7222,7228) - 2차 GIS 초기점검","2025-04-07 10:00","2025-04-07 18:00","2025-04-07 10:00","2025-04-07 18:00","연속"]
[7,"남서울","동서울","동서울S/S #2 M.Tr","24-25년도 동서울전력지사 변전협력회사 총액공사","동서울S/S  #2M.Tr 하자점검, 1차 GIS(7272)초기점검","2025-04-14 09:00","2025-04-18 18:00","2025-04-14 09:00","2025-04-18 18:00","연속"]
[8,"남서울","동서울","동서울S/S #1 M.Tr","24-25년도 동서울전력지사 변전협력회사 총액공사","동서울S/S  #1M.Tr 하자점검, 1차 GIS(7172)초기점검","2025-04-07 09:00","2025-04-11 18:00","2025-04-07 09:00","2025-04-11 18:00","연속"]
[9,"남서울","동서울","동서울S/S #3 M.Tr","24-25년도 동서울전력지사 변전협력회사 총액공사","동서울S/S  #3M.Tr 하자점검, 1차 GIS(7572)조작시험","2025-04-21 09:00","2025-04-25 18:00","2025-04-21 09:00","2025-04-25 18:00","연속"]
[10,"남서울","직할","신문래S/S #2 M.Tr","170kV GIS 정밀점검공사","신문래S/S #2M.Tr 2차 GIS 정밀점검","2025-04-07 09:00","2025-04-09 18:00","2025-04-07 09:00","2025-04-09 14:00","연속"]
[11,"남서울","직할","신문래S/S #1 M.Tr","170kV GIS 정밀점검공사","신문래S/S #1M.Tr 2차 GIS 정밀점검","2025-04-01 09:00","2025-04-03 18:00","취소","취소","연속"]
[12,"남서울","직할","신문래S/S #3 M.Tr","170kV GIS 정밀점검공사","신문래S/S #3M.Tr 2차 GIS 정밀점검","2025-04-09 09:00","2025-04-11 18:00","2025-04-09 14:00","2025-04-11 18:00","연속"]
[13,"인천","김포","신김포S/S #1 M.Tr","신김포S/S  #1 M.Tr 보호반 대체","신김포S/S  #1 M.Tr 보호반 대체 (병행) #1S.Tr 1차 GIS 조작시험","2025-04-07 09:00","2025-04-11 18:00","2025-04-07 09:00","2025-04-11 18:00","연속"]
[14,"인천","김포","신김포S/S #2 M.Tr","신김포S/S  #2 M.Tr 보호반 대체","신김포S/S  #2 M.Tr 보호반 대체 (병행) #2S.Tr 1차 GIS 조작시험","2025-04-14 09:00","2025-04-17 18:00","2025-04-14 09:00","2025-04-17 18:00","연속"]
[15,"인천","부평","서인천C/C #1 CLR CB","#70-72 CLR # #7077 GIS 조작시험, 전자변교체","#70-72 CLR # #7077 GIS 조작시험, 전자변교체","2025-04-17 09:00","2025-04-17 18:00","2025-04-17 09:00","2025-04-17 18:00","연속"]
[16,"인천","부평","서인천C/C #1 CLR CB","#70-72 CLR #7277 GIS 조작시험, 전자변교체","#70-72 CLR #7277 GIS 조작시험, 전자변교체","2025-04-17 09:00","2025-04-17 18:00","2025-04-17 09:00","2025-04-17 18:00","연속"]
[17,"인천","부평","서인천C/C #1 M.Tr","서인천C/C  #1 M.Tr 보통점검","서인천C/C  #1 M.Tr 보통점검","2025-04-23 09:00","2025-04-25 18:00","2025-04-23 09:00","2025-04-25 18:00","연속"]
[18,"인천","부평","서인천C/C CB 7172","#1 M.Tr 1차 7172 GIS 조작시험, 전자변교체","#1 M.Tr 1차 7172 GIS 조작시험, 전자변교체","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","연속"]
[19,"인천","부평","서인천C/C #2 CLR CB","#75-77 CLR #7777 GIS 조작시험, 전자변교체","#75-77 CLR #7777 GIS 조작시험, 전자변교체","2025-04-30 09:00","2025-04-30 18:00","2025-04-30 09:00","2025-04-30 18:00","연속"]
[20,"인천","부평","서인천C/C #2 CLR CB","#75-77 CLR #7577 GIS 조작시험, 전자변교체","#75-77 CLR #7577 GIS 조작시험, 전자변교체","2025-04-30 09:00","2025-04-30 18:00","2025-04-30 09:00","2025-04-30 18:00","연속"]
[21,"인천","부평","서인천C/C CB 7471"," 서인천CC-신부평#3T/L 7471 GIS 보통점검"," 서인천CC-신부평#3T/L 7471 GIS 보통점검","2025-04-11 09:00","2025-04-11 18:00","2025-04-11 09:00","2025-04-11 18:00","연속"]
[22,"인천","부평","서인천C/C CB 7100","신김포서인천CCT/L-#1M.Tr 1차 TIE 7100 GIS 조작시험","신김포서인천CCT/L-#1M.Tr 1차 TIE 7100 GIS 조작시험","2025-04-01 09:00","2025-04-01 12:00","2025-04-01 09:00","2025-04-01 12:00","연속"]
[23,"인천","부평","서인천C/C CB 7171","신김포-서인천CC T/L 7171 GIS 조작시험","신김포-서인천CC T/L 7171 GIS 조작시험","2025-04-01 13:00","2025-04-01 18:00","2025-04-01 13:00","2025-04-01 18:00","연속"]
[24,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S  #2 M.Tr 하자 점검","신가좌S/S  #2 M.Tr 하자 점검","2025-04-16 09:00","2025-04-18 18:00","취소","취소","연속"]
[25,"인천","부평","신가좌S/S #4 M.Tr","#4M.Tr 보호반 대체 및 보통점검","#4M.Tr 보호반 대체 및 보통점검","2025-04-28 09:00","2025-05-02 18:00","취소","취소","연속"]
[26,"인천","부평","신가좌가정#1 T/L","'24~'25년 가공송전 협력회사 공사","수평 추락방지시설 및 고정형폴리머점퍼지지애자 설치","2025-04-19 07:00","2025-04-20 18:00","취소","취소","매일"]
[27,"인천","부평","신가좌가정#2 T/L","'24~'25년 가공송전 협력회사 공사","수평 추락방지시설 및 고정형폴리머점퍼지지애자 설치","2025-04-26 07:00","2025-04-27 18:00","취소","취소","매일"]
[28,"인천","부평","신경서S/S CB 7571"," 신경서-포스코S/Y#2T/L 7571 GIS 보통점검"," 신경서-포스코S/Y#2T/L 7571 GIS 보통점검 및 절연열화","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[29,"인천","부평","신경서S/S CB 7371"," 신경서-포스코SY#1T/L 7371 GIS 조작시험"," 신경서-포스코SY#1T/L 7371 GIS 조작시험","2025-04-21 09:00","2025-04-21 18:00","2025-04-21 09:00","2025-04-21 18:00","연속"]
[30,"인천","부평","신인천C/C CB 7600","#76Bay B/F 보호반대체","#76Bay B/F 보호반대체","2025-04-28 09:00","2025-05-02 18:00","2025-04-28 09:00","2025-05-02 18:00","연속"]
[31,"인천","부평","신인천C/C SEC CB 71720","신인천C/C  #71-#72 SEC GIS 보통점검","신인천C/C  #71-#72 SEC GIS 보통점검","2025-04-07 09:00","2025-04-07 18:00","2025-04-07 09:00","2025-04-07 18:00","연속"]
[32,"인천","부평","신인천C/C SEC CB 70710","신인천C/C  #70-#71 SEC GIS 보통점검","신인천C/C  #70-#71 SEC GIS 보통점검","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[33,"인천","부평","신인천C/C SEC CB 75760","신인천C/C  75-#76 SEC GIS 보통점검 및 절연열화","신인천C/C  75-#76 SEC GIS 보통점검 및 절연열화","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[34,"인천","부평","신인천C/C CB 7600","신인천C/C 3MT001-3MT201 7600 TIE GIS 조작시험","신인천C/C 3MT001-3MT201 7600 TIE GIS 조작시험","2025-04-22 09:00","2025-04-22 12:00","2025-04-22 09:00","2025-04-22 12:00","연속"]
[35,"인천","부평","신인천C/C CB 7672","신인천C/C  3MT201 7672 GIS 조작시험","신인천C/C  3MT201 7672 GIS 조작시험","2025-04-22 13:00","2025-04-22 18:00","2025-04-22 13:00","2025-04-22 18:00","연속"]
[36,"인천","부평","신인천C/C CB 7800","신경서신인천T/L-4MT201 TIE 7800 GIS 조작시험","신경서신인천T/L-4MT201 TIE 7800 GIS 조작시험","2025-04-23 09:00","2025-04-23 13:00","2025-04-23 09:00","2025-04-23 13:00","연속"]
[37,"인천","부평","신인천C/C CB 7871","신경서-신인천C/C T/L 7871 GIS 조작시험","신경서-신인천C/C T/L 7871 GIS 조작시험","2025-04-23 13:00","2025-04-23 18:00","2025-04-23 13:00","2025-04-23 18:00","연속"]
[38,"인천","부평","신인천C/C CB 7671"," 3MT101 7572 GIS 조작시험, 전자변교체"," 3MT101 7572 GIS 조작시험. 전자변교체","2025-04-25 09:00","2025-04-25 18:00","2025-04-25 09:00","2025-04-25 18:00","연속"]
[39,"인천","부평","신인천C/C CB 7500"," 3MT101 TIE 7500 GIS 조작시험"," 3MT101 TIE 7500 GIS 조작시험","2025-04-26 09:00","2025-04-26 18:00","2025-04-26 09:00","2025-04-26 18:00","연속"]
[40,"인천","부평","신인천C/C CB 7672","#76Bay B/F 보호반대체","#76Bay B/F 보호반대체","2025-04-28 09:00","2025-05-02 18:00","2025-04-28 09:00","2025-05-02 18:00","연속"]
[41,"인천","부평","신인천C/C CB 7671","#76Bay B/F 보호반대체","#76Bay B/F 보호반대체","2025-04-28 09:00","2025-05-02 18:00","2025-04-28 09:00","2025-05-02 18:00","연속"]
[42,"인천","부평","인천C/C CB 7C00","가정인천CC#2T/L-#2 TIE Tr 1차 TIE GIS 보통점검","가정인천CC#2T/L-#2 TIE Tr 1차 TIE 7C00 GIS 보통점검","2025-04-28 09:00","2025-04-28 18:00","2025-04-28 09:00","2025-04-28 18:00","연속"]
[43,"인천","부평","인천C/C CB 7200"," 신경서인천CC#1T/L TIE 7200 GIS 보통점검"," 신경서인천CC#1T/L TIE 7200 GIS 보통점검 및 절연열화측정","2025-04-01 09:00","2025-04-01 18:00","2025-04-01 09:00","2025-04-01 18:00","연속"]
[44,"인천","부평","가정인천CC#1 T/L","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수 관련 이격거리확보 CLR 바이패스 조작","2025-04-19 07:00","2025-04-19 09:00","취소","취소","연속"]
[45,"인천","부평","인천C/C #1 Sh.R CB","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수","2025-04-14 09:00","2025-04-16 18:00","2025-04-14 09:00","2025-04-16 18:00","연속"]
[46,"인천","부평","가정인천CC#1 T/L","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수 관련 이격거리확보 CLR 바이패스 조작","2025-04-12 07:00","2025-04-12 09:00","취소","취소","연속"]
[47,"인천","부평","인천C/C CB 7C72","#2 TIE Tr 1차 7C72 GIS 보통점검, 절연열화측정","#2 TIE Tr 1차 7C72 GIS 보통점검, 절연열화측정","2025-04-29 09:00","2025-04-29 18:00","2025-04-29 09:00","2025-04-29 18:00","연속"]
[48,"인천","부평","인천C/C CB 7B72"," 인천복합 #3S/T 7B72GIS 보통점검"," 인천복합 #3S/T 7B72GIS 보통점검","2025-04-22 09:00","2025-04-22 18:00","2025-04-22 09:00","2025-04-22 18:00","연속"]
[49,"인천","부평","인천C/C CB 7B71","인천복합 #5,6G/T GIS 7B71 GIS 보통점검","인천복합 #5,6G/T GIS 7B71 GIS 보통점검","2025-04-18 13:00","2025-04-18 18:00","2025-04-18 13:00","2025-04-18 18:00","연속"]
[50,"인천","부평","인천C/C CB 7171"," #1 TIE Tr 1차 7171 GIS 보통점검"," #1 TIE Tr 1차 7171 GIS 보통점검","2025-04-17 09:00","2025-04-17 18:00","2025-04-17 09:00","2025-04-17 18:00","연속"]
[51,"인천","부평","인천C/C CB 7100"," #1 TIE Tr 1차 7100 TIE GIS 보통점검"," #1 TIE Tr 1차 7100 TIE GIS 보통점검","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[52,"인천","부평","인천CC포스코CC#1 T/L","#71Bay B/F 보호반 대체","#71Bay B/F 보호반 대체","2025-04-21 09:00","2025-04-25 18:00","취소","취소","연속"]
[53,"인천","부평","포스코C/C CB 7172","#71Bay B/F 보호반 대체","#71Bay B/F 보호반 대체","2025-04-21 09:00","2025-04-25 18:00","취소","취소","연속"]
[54,"인천","시흥","신시화S/S #3 M.Tr"," 신시화S/S #2,3M.Tr 2차 GIB 교체공사","GIB 과열로 #2,3M.Tr 2차 단상 GIB 교체","2025-04-17 10:00","2025-05-02 18:00","2025-04-17 10:00","2025-05-02 18:00","연속"]
[55,"인천","시흥","신시화S/S #1Sh.R CB","신시화S/S 362kV 7671 GIS 점검","신시화S/S 362kV 7671 GIS 점검 -유압조작기 모터 과동작 조치 관련","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[56,"인천","시흥","신시화영흥TP#1 T/L","영흥#2S/Y  7871, 7800 GIS 보통점검","영흥#2S/Y  영흥TP신시화# 1T/L(7871, 7800) GIS 보통점검","2025-04-14 09:00","2025-04-15 18:00","취소","취소","연속"]
[57,"인천","시흥","영흥T/P CB 7772","영흥#2T/P  #6G.Tr 1차 GIS(7772) 보통점검","영흥#2T/P  #6G.Tr 1차 GIS(7772) 보통점검","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[58,"인천","시흥","영흥T/P CB 7672","영흥#2T/P  #5G.Tr 1차 GIS(7672) 보통점검","영흥#2T/P  #5G.Tr 1차 GIS(7672) 보통점검","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[59,"인천","직할","갈산S/S CB 7371","갈산S/S 가정신광명#2T/L(7371) GIS 보통점검","갈산S/S 가정신광명#2T/L(7371) GIS 보통점검","2025-04-07 09:30","2025-04-07 18:00","취소","취소","연속"]
[60,"인천","직할","갈산S/S CB 7172","갈산S/S 가정신광명#1T/L(7172) GIS 보통점검","갈산S/S 가정신광명#1T/L(7172) GIS 보통점검","2025-04-04 09:30","2025-04-04 18:00","취소","취소","연속"]
[61,"인천","직할","갈산S/S #2 Sh.R CB","갈산S/S  #2Sh.R 방열판 청소","갈산S/S  #2Sh.R 방열판 청소","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[62,"인천","직할","갈산S/S CB 7500","갈산S/S 7500B/T, 6100B/T GIS 보통점검","갈산S/S 7500B/T, 6100B/T GIS 보통점검","2025-04-08 09:30","2025-04-08 18:00","취소","취소","연속"]
[63,"인천","직할","갈산S/S CB 7471","갈산S/S 가정갈산#3T/L(7471) GIS 보통점검","갈산S/S 가정갈산#3T/L(7471) GIS 보통점검","2025-04-03 09:30","2025-04-03 18:00","취소","취소","연속"]
[64,"인천","직할","갈산S/S #3 M.Tr","갈산S/S #3M.Tr, 7472,7400,6344 GIS 보통점검","갈산S/S #3M.Tr 보통점검, 7472,7400,6344 GIS 보통점검","2025-04-01 09:30","2025-04-02 18:00","취소","취소","연속"]
[65,"인천","직할","갈산S/S #1 Sh.R CB","갈산S/S  #1Sh.R 방열판 청소","갈산S/S  #1Sh.R 방열판 청소","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[66,"인천","직할","서인천CC신부평#1 T/L","’25∼26년 인천본부 김포전력지사 지중송전 협력회사 공사","절연유 채유","2025-04-21 09:00","2025-04-26 18:00","2025-04-21 09:00","2025-04-26 18:00","연속"]
[67,"경기북부","고양","신덕은동두천CC#2 T/L"," 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신덕은-동두천CC#2T/L No.32~50 (子 : 154kV 신포천-백학#1T/L No.21~39)","2025-04-01 07:00","2025-04-03 18:00","취소","취소","연속"]
[68,"경기북부","고양","신파주신덕은#1 T/L","24~25년 고양전력지사 가공송전 협력회사 총액공사","수평추락방지장치 설치","2025-04-17 07:00","2025-04-23 18:00","2025-04-17 07:00","2025-04-23 18:00","연속"]
[69,"경기북부","고양","신덕은S/S #4 M.Tr","24-25년 고양전력 변전협력회사 공사"," #4M.Tr C상 보통점검","2025-04-22 09:00","2025-04-24 18:00","2025-04-22 09:00","2025-04-24 18:00","연속"]
[70,"경기북부","고양","신김포신파주#1 T/L","24~25년 고양전력지사 가공송전 협력회사 총액공사","불량애자 교체, 수평추락방지장치 설치","2025-04-07 07:00","2025-04-11 18:00","2025-04-07 07:00","2025-04-11 18:00","연속"]
[71,"경기북부","고양","신파주S/S #3 M.Tr","신파주S/S 장기사용 노후 배전반 교체","신파주S/S #3M.Tr 보호반, 74 Bay B/F, 신파주-양주#2T/L 보호반 교체","2025-04-07 09:00","2025-04-18 18:00","2025-04-07 09:00","2025-04-18 18:00","연속"]
[72,"경기북부","고양","신파주양주#1 T/L","24~25년 고양전력지사 가공송전 협력회사 총액공사","불량애자 교체, 수평추락방지장치 설치","2025-04-01 07:00","2025-04-04 18:00","2025-04-01 07:00","2025-04-04 18:00","연속"]
[73,"경기북부","고양","신파주양주#2 T/L","신파주S/S 장기사용 노후배전반 교체","신파주S/S #3M.Tr 보호반, 74 Bay B/F, 신파주-양주#2T/L 보호반 교체","2025-04-07 07:00","2025-04-18 18:00","2025-04-07 07:00","2025-04-18 18:00","연속"]
[74,"경기북부","고양","신김포신파주#2 T/L","24~25년 고양전력지사 가공송전 협력회사 총액공사","불량애자 교체, 수평추락방지장치 설치","2025-04-01 07:00","2025-04-04 18:00","2025-04-01 07:00","2025-04-04 18:00","연속"]
[75,"경기북부","구리","미금S/S #6 Sh.R CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7679)","2025-04-14 09:00","2025-04-14 18:00","2025-04-14 09:00","2025-04-14 18:00","연속"]
[76,"경기북부","구리","미금S/S #4 Sh.R CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7479)","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[77,"경기북부","구리","미금S/S #3 Sh.R CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7379)","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[78,"경기북부","구리","미금S/S #1 Sh.R CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7179)","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[79,"경기북부","구리","미금S/S CB 7079","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7079)","2025-04-07 09:00","2025-04-07 18:00","2025-04-07 09:00","2025-04-07 18:00","연속"]
[80,"경기북부","구리","미금S/S CB 7200","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7200)","2025-04-02 09:00","2025-04-02 18:00","2025-04-02 09:00","2025-04-02 18:00","연속"]
[81,"경기북부","구리","미금S/S CB 7271","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7271)","2025-04-01 09:00","2025-04-01 18:00","2025-04-01 09:00","2025-04-01 18:00","연속"]
[82,"경기북부","구리","신가평S/S CB 7471","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7471)","2025-04-17 09:00","2025-04-17 18:00","2025-04-17 09:00","2025-04-17 18:00","연속"]
[83,"경기북부","구리","신가평S/S CB 7300","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7300)","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[84,"경기북부","구리","신가평S/S CB 7371","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7371)","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","연속"]
[85,"경기북부","구리","신가평미금#1 T/L","구리송전협력회사 공사_추락방지장치 및 피뢰기 설치","신가평-신의정부#2(신가평-미금#1 병가구간) No.2~7추락방지 및 피뢰기 설치(6기)","2025-04-26 07:00","2025-04-27 18:00","2025-04-26 07:00","2025-04-27 18:00","연속"]
[86,"경기북부","구리","신가평S/S CB 7800","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7800)","2025-04-23 09:00","2025-04-23 18:00","2025-04-23 09:00","2025-04-23 18:00","연속"]
[87,"경기북부","구리","신가평S/S CB 7872","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7872)","2025-04-22 09:00","2025-04-22 18:00","2025-04-22 09:00","2025-04-22 18:00","연속"]
[88,"경기북부","구리","신가평S/S CB 7671","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7671)","2025-04-21 09:00","2025-04-21 18:00","2025-04-21 09:00","2025-04-21 18:00","연속"]
[89,"경기북부","구리","신포천S/S CB 7271","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7271)","2025-04-30 09:00","2025-04-30 18:00","2025-04-30 09:00","2025-04-30 18:00","연속"]
[90,"경기북부","구리","신포천S/S CB 7172","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7172)","2025-04-29 09:00","2025-04-29 18:00","2025-04-29 09:00","2025-04-29 18:00","연속"]
[91,"경기북부","구리","신포천S/S CB 7171","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7171)","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","연속"]
[92,"경기북부","구리","신포천S/S CB 7100","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검 (CB 7100)","2025-04-28 09:00","2025-04-28 18:00","2025-04-28 09:00","2025-04-28 18:00","연속"]
[93,"경기북부","구리","신포천S/S #4 M.TR","24~25년 경기북부 직할 가공송전협력회사 공사"," 신포천-동두천CC#2T/L 불량애자교체공사","2025-04-07 07:00","2025-04-07 18:00","취소","취소","연속"]
[94,"경기북부","직할","신포천동두천CC#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 신포천-동두천CC#2T/L 불량애자교체공사","2025-04-07 07:00","2025-04-07 18:00","취소","취소","연속"]
[95,"경기북부","직할","신의정부양주#2 T/L"," 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-양주#2 T/L No.1~97","2025-04-21 07:00","2025-05-08 18:00","취소","취소","연속"]
[96,"경기북부","직할","신의정부S/S #1 Sh.R CB","24-25년도 변전 협력회사 총액공사","신의정부SS 7472 GIS 개폐타임 측정","2025-04-02 09:00","2025-04-02 18:00","2025-04-02 09:00","2025-04-02 18:00","연속"]
[97,"경기북부","직할","신의정부S/S #3 Sh.R CB","24-25년도 변전 협력회사 총액공사","신의정부SS 7872 GIS 개폐타임 측정","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[98,"경기북부","직할","신의정부S/S CB 7400","24-25년도 변전 협력회사 총액공사","신의정부SS 7400 TIE GIS 개폐타임 측정","2025-04-01 09:00","2025-04-01 18:00","2025-04-01 09:00","2025-04-01 18:00","연속"]
[99,"경기북부","직할","신의정부S/S CB 7800","24-25년도 변전 협력회사 총액공사","신의정부SS 7800 TIE GIS 개폐타임 측정","2025-04-07 09:00","2025-04-07 18:00","2025-04-07 09:00","2025-04-07 18:00","연속"]
[100,"경기북부","직할","신의정부S/S #2 Sh.R CB","24-25년도 변전 협력회사 총액공사","신의정부SS 7772 GIS 개폐타임 측정","2025-04-03 09:00","2025-04-03 18:00","2025-04-03 09:00","2025-04-03 18:00","연속"]
[101,"경기북부","직할","양주S/S #2 M.Tr","24-25년 변전협력회사 총액공사","부싱채유 및 #2Sh.R 보통점검","2025-04-21 09:00","2025-04-23 18:00","2025-04-21 09:00","2025-04-23 18:00","연속"]
[102,"경기북부","직할","양주S/S #6 Sh.R CB","24-25 변전협력 총액공사","362kV GIS 개폐타임 측정 및 절연열화 측정","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","연속"]
[103,"경기북부","직할","양주S/S #5 Sh.R CB","24-25 변전협력 총액공사","362kV GIS 개폐타임 측정 및 절연열화 측정","2025-04-22 09:00","2025-04-22 18:00","2025-04-22 09:00","2025-04-22 18:00","연속"]
[104,"경기","군포","서서울신광명#1 T/L","서서울S/S  서서울-신광명#1T/L GIS 보통점검","서서울S/S  서서울-신광명#1T/L 7571,7500 GIS 보통점검,CVT,LA 보통점검","2025-04-07 09:00","2025-04-08 18:00","취소","취소","연속"]
[105,"경기","군포","신온양서서울#2 T/L","서서울S/S  신온양-서서울#2T/L GIS 보통점검","서서울S/S  신온양-서서울#2T/L 7772 GIS 보통점검,CVT 대체","2025-04-17 09:00","2025-04-18 18:00","취소","취소","연속"]
[106,"경기","군포","서서울S/S #4 M.Tr","서서울S/S  #4 M.Tr 1차 GIS 보통점검","서서울S/S  #4 M.Tr 1차 GIS 보통점검(7800,7872),1차부싱 절연유채유,CVT 대체,3차 GPT 교체,추락방지장치 설치,방호벽 사다리 철거","2025-04-28 09:00","2025-04-30 18:00","취소","취소","연속"]
[107,"경기","군포","신온양서서울#1 T/L","서서울S/S  신온양-서서울#1T/L GIS 보통점검","서서울S/S  신온양-서서울#1T/L 7472 GIS 보통점검,7400 GIS 조작시험,CVT 대체","2025-04-10 09:00","2025-04-11 18:00","취소","취소","연속"]
[108,"경기","군포","신안산S/S #4 M.Tr","신안산S/S  #4M.Tr 2차 GIS 조작시험","신안산S/S  #4M.Tr 2차 GIS 조작시험 시행","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[109,"경기","동부","곤지암S/S #1 M.Tr","24-25년 동부 변전협력회사 총액공사","[곤지암S/S #1M.Tr 휴전작업] 곤지암:7172(조작) 4189(조작),#1S.Tr(초기) * #1M.Tr 부싱절연유 채유(A,B,C상) * 추락방지장치 설치","2025-04-14 09:00","2025-04-15 18:00","2025-04-14 09:00","2025-04-15 18:00","연속"]
[110,"경기","동부","곤지암S/S #3 M.Tr","24-25년 동부 변전협력회사 총액공사","[곤지암S/S #3M.Tr 휴전작업] 곤지암:7500(조작),7572(조작) * 부싱절연유 채유(A,B,C상) * 추락방지장치 설치","2025-04-24 09:00","2025-04-25 18:00","2025-04-24 09:00","2025-04-25 18:00","연속"]
[111,"경기","동부"," 곤지암S/S CB 7671","24-25년 동부 변전협력회사 총액공사","[곤지암-SK하이닉스#2] 곤지암:7371(조작),7671(하자)","2025-04-17 13:00","2025-04-17 18:00","2025-04-17 13:00","2025-04-17 18:00","연속"]
[112,"경기","동부"," 곤지암S/S CB 7571","24-25년 동부 변전협력회사 총액공사","[곤지암-SK하이닉스#1] 곤지암:7300(조작),7571(하자)","2025-04-16 13:00","2025-04-16 18:00","2025-04-16 13:00","2025-04-16 18:00","연속"]
[113,"경기","동부","곤지암S/S CB 7500","24-25년 동부 변전협력회사 총액공사","[곤지암S/S #3M.Tr 휴전작업] 곤지암:7500(조작),7572(조작) * 부싱절연유 채유(A,B,C상) * 추락방지장치 설치","2025-04-24 09:00","2025-04-25 18:00","2025-04-24 09:00","2025-04-25 18:00","연속"]
[114,"경기","동부","곤지암S/S #2 M.Tr","24-25년 동부 변전협력회사 총액공사","[곤지암S/S #2M.Tr 휴전작업] 곤지암:7372(조작),4289(조작) * #2M.Tr 부싱절연유 채유(A,B,C상) * 추락방지장치 설치 * #2S.Tr 대체","2025-04-21 09:00","2025-04-23 18:00","취소","취소","연속"]
[115,"경기","동부","곤지암S/S CB 7372","24-25년 동부 변전 협력회사 총액공사","[곤지암S/S #2M.Tr 휴전작업] 곤지암:7372(조작),4289(조작) * #2M.Tr 부싱절연유 채유(A,B,C상) * 추락방지장치 설치 * #2S.Tr 대체","2025-04-21 09:00","2025-04-23 18:00","취소","취소","연속"]
[116,"경기","동부","곤지암S/S CB 7400","24-25년 동부 변전협력회사 총액공사","[곤지암-동서울#2T/L] 곤지암:7471(조작),7400(조작)","2025-04-18 14:00","2025-04-18 18:00","2025-04-18 14:00","2025-04-18 18:00","연속"]
[117,"경기","동부","곤지암S/S CB 7471","24-25년 동부 변전협력회사 총액공사","[곤지암-동서울#2T/L] 곤지암:7471(조작),7400(조작)","2025-04-18 09:00","2025-04-18 14:00","2025-04-18 09:00","2025-04-18 14:00","연속"]
[118,"경기","동부","곤지암S/S CB 7371","24-25년 동부 변전협력회사 총액공사","[곤지암-동서울#1T/L] 곤지암:,7371(조작),7671(하자)","2025-04-17 09:00","2025-04-17 13:00","2025-04-17 09:00","2025-04-17 13:00","연속"]
[119,"경기","동부","곤지암S/S CB 7300","24-25년 동부 변전협력회사 총액공사","곤지암:7300(조작),7571(하자)","2025-04-16 09:00","2025-04-16 13:00","2025-04-16 09:00","2025-04-16 13:00","연속"]
[120,"경기","동부","곤지암여주복합#2 T/L"," 신용인-동서울등 16개T/L 추락방지장치 설치공사","곤지암여주CC #2T/L 추락방지장치 설치 80기(잔여 7기)","2025-04-13 07:00","2025-04-13 18:00","취소","취소","연속"]
[121,"경기","동부","곤지암여주복합#1 T/L"," 신용인-동서울등 16개T/L 추락방지장치 설치공사","곤지암여주CC #1T/L 추락방지장치 설치 80기(잔여 18기)","2025-04-12 07:00","2025-04-12 18:00","취소","취소","연속"]
[122,"경기","동부","신제천신충주T#1 T/L"," 신용인-동서울등 16개T/L 추락방지장치 설치공사","신제천 여주CC 추락방지장치 설치 39기","2025-04-26 07:00","2025-04-27 18:00","취소","취소","연속"]
[123,"경기","동부","신충주여주복합#2 T/L"," 신용인-동서울등 16개T/L 추락방지장치 설치공사","신충주여주복합#2T/L 추락방지장치 설치 39기","2025-04-19 07:00","2025-04-20 18:00","취소","취소","연속"]
[124,"경기","성남","신성남S/S #5 M.Tr","2025년 성남전력 170kV GIS 정밀점검공사","- 2차 gis 정밀점검","2025-04-28 09:00","2025-04-29 18:00","2025-04-28 09:00","2025-04-29 18:00","연속"]
[125,"경기","성남","신성남신양재#1 T/L","2025년 성남전력 변전협력회사 총액공사","- 7871, 7800 조작시험, 절연열화","2025-04-01 09:00","2025-04-01 18:00","2025-04-01 09:00","2025-04-01 18:00","연속"]
[126,"경기","성남","신성남S/S #2 M.Tr","2025년 성남전력 M.Tr 보통,154kV 정밀/보통점검공사","- M.Tr, NGR 보통 - 7200, 7272 조작시험, 절연열화","2025-04-02 09:00","2025-04-03 18:00","2025-04-02 09:00","2025-04-03 18:00","연속"]
[127,"경기","성남","신수원S/S #3 M.Tr","2025년 성남전력 변전협력회사 총액공사","- m.tr, ngr 보통점검 - 2차 GIS 조작시험","2025-04-04 09:00","2025-04-04 18:00","2025-04-04 09:00","2025-04-04 18:00","연속"]
[128,"경기","성남","신수원S/S #1 M.Tr","2025년 성남전력 M.Tr  보통,154kV 정밀/보통점검공사","- m.tr, ngr 보통점검 - 2차 LA 보통점검","2025-04-24 09:00","2025-04-25 18:00","2025-04-24 09:00","2025-04-25 18:00","연속"]
[129,"경기","성남","신수원S/S #4 M.Tr","2025년 성남전력 변전협력회사 총액공사","- 보호반대체 - A,B상 플랜지 누유","2025-04-14 09:00","2025-04-23 18:00","2025-04-14 09:00","2025-04-23 18:00","연속"]
[130,"경기","성남","신안성신성남#1 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사(교체수량 3,385개) - 사전작업 : 추락방지장치 설치시행(수직, 수평) ※  신안성-신용인T/L 4회선 구간","2025-04-04 09:00","2025-04-18 18:00","2025-04-04 09:00","2025-04-18 18:00","연속"]
[131,"경기","성남","신안성신용인#1 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사(교체수량 3,385개) - 사전작업 : 추락방지장치 설치시행(수직, 수평) ※  신안성-신성남T/L 4회선 구간","2025-04-04 09:00","2025-04-18 18:00","2025-04-04 09:00","2025-04-18 18:00","연속"]
[132,"경기","성남","신안성신용인#2 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사(교체수량 3,385개) - 사전작업 : 추락방지장치 설치시행(수직, 수평) ※  신안성-신성남T/L 4회선 구간","2025-04-19 09:00","2025-05-03 18:00","2025-04-19 09:00","2025-05-03 18:00","연속"]
[133,"경기","성남","신안성신성남#2 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사(교체수량 3,385개) - 사전작업 : 추락방지장치 설치시행(수직, 수평) ※  신안성-신용인T/L 4회선 구간","2025-04-19 09:00","2025-05-03 18:00","2025-04-19 09:00","2025-05-03 18:00","연속"]
[134,"경기","성남","신용인S/S #2 M.Tr","2025년 성남전력 170kV GIS 정밀점검공사","- 2차 GIS 정밀점검","2025-04-07 09:00","2025-04-08 18:00","2025-04-07 09:00","2025-04-08 18:00","연속"]
[135,"경기","성남","신용인S/S #3 M.Tr","2025년 성남전력 변전협력회사 총액공사","- 3차 LA 보토어 - 2차 GIS 보통","2025-04-25 09:00","2025-04-25 18:00","2025-04-30 09:00","2025-04-30 18:00","연속"]
[136,"경기","성남","신용인신수원 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","- 7771 보통점검 절연열화 - 7171 보통점검 절연열화(신수원)","2025-04-10 09:00","2025-04-11 18:00","2025-04-10 09:00","2025-04-11 18:00","연속"]
[137,"경기","직할","화성S/S #1 M.Tr","2024-25년 경기본부 직할 변전협력회사 총액공사","화성 : #1M.Tr 보호반 대체 및 보통점검(~25) - 1차 GIS 초기점검 - LA 1,2차 A,B,C 보통점검 및 3차 A,B,C 하자 점검 - CVT 1차 하자점검 - 추락방지장치 설치","2025-04-19 09:00","2025-04-25 18:00","2025-04-19 09:00","2025-04-25 18:00","연속"]
[138,"경기","직할","화성신안산#1 T/L","2024-25년 경기본부 직할 변전협력회사 총액공사","화성 : 화성-신안산#1T/L - 화성-신안산#1T/L GIS(7971) 보통점검 - LA A,B,C 보통점검 / CVT A,B,C 보통점검 - GIS 콘덴서 절연열화 측정","2025-04-28 09:00","2025-04-28 18:00","2025-04-28 09:00","2025-04-28 18:00","연속"]
[139,"경기","직할","화성S/S CB 7371","2024-25년 경기본부 직할 변전협력회사 총액공사","화성 : 아산-화성#1T/L GIS 하자점검(7371) - GIS 콘덴서 절연열화 측정","2025-04-11 09:00","2025-04-11 18:00","2025-04-11 09:00","2025-04-11 18:00","연속"]
[140,"경기","평택","고덕#2서안성#1 T/L"," 고덕2-서안성 #1T/L 초기점검","2025년도 가공송전 순시점검 위탁공사  고덕2-서안성 #1T/L 초기점검 및 현수애자절연성능 진단","2025-04-01 09:00","2025-04-02 18:00","취소","취소","연속"]
[141,"경기","평택","고덕#2서안성#2 T/L"," 고덕2-서안성 #2T/L 초기점검","2025년도 가공송전 순시점검 위탁공사  고덕2-서안성 #2T/L 초기점검 및 현수애자절연성능 진단","2025-04-03 09:00","2025-04-04 18:00","취소","취소","연속"]
[142,"경기","평택","고덕#2서안성#1 T/L","고덕#2S/S  #4M.Tr 증설공사 (1차측)"," #4M.Tr 1차측 7572CB 증설 무부하가압","2025-04-29 09:00","2025-04-30 18:00","2025-04-29 09:00","2025-04-30 18:00","연속"]
[143,"경기","평택","고덕#2S/S #2 BUS","고덕#2S/S  #4M.Tr 증설공사 (1차측)"," #4M.Tr 1차측 7572CB 증설","2025-04-21 09:00","2025-05-02 18:00","2025-04-21 09:00","2025-05-02 18:00","연속"]
[144,"경기","평택","고덕#2S/S CB 7500","고덕#2S/S  #4M.Tr 증설공사 (1차측)"," #4M.Tr 1차측 7572CB 증설","2025-04-21 09:00","2025-05-16 18:00","2025-04-21 09:00","2025-05-16 18:00","연속"]
[145,"경기","평택","북당진고덕#2 HVDC CB","24-25년 북당진-고덕 HVDC 변환설비 위탁정비공사","1. 공사명 : 24-25년 북당진-고덕 HVDC 변환설비 위탁정비공사 2. 휴전설비 : 북당진-고덕#1T/L(#2Pole) 3. 작업내용 : Bi-Pole 변환설비 연차점검 - #2Pole C.Tr, Valve, 냉각, 공조설비","2025-04-21 09:00","2025-05-02 18:00","2025-04-21 09:00","2025-05-02 18:00","연속"]
[146,"경기","평택","북당진고덕#1 HVDC CB","24-25년 북당진-고덕 HVDC 변환설비 위탁정비공사","1. 공사명 : 24-25년 북당진-고덕 HVDC 변환설비 위탁정비공사 2. 휴전설비 : 북당진-고덕#1T/L(#1Pole) 3. 작업내용 : #1Pole 변환설비 연차점검 - #1Pole C.Tr, Valve, 냉각, 공조설비","2025-04-07 09:00","2025-04-18 18:00","2025-04-07 09:00","2025-04-18 18:00","연속"]
[147,"경기","평택","서안성S/S #3 M.Tr","2025년 평택전력 변전협력회사 총액공사","서안성S/S  #3 M.Tr 2차 GIS 보통점검","2025-04-14 09:00","2025-04-14 18:00","2025-04-14 09:00","2025-04-14 18:00","연속"]
[148,"경기","평택","평택T/P #1 CLR #7177 CB","2025년 평택전력 GIS 보통 및 정밀점검공사","평택T/P  #1 CLR #7177 GIS 보통점검","2025-04-23 14:00","2025-04-23 18:00","2025-04-23 14:00","2025-04-23 18:00","연속"]
[149,"경기","평택","평택T/P #1 CLR #7077 CB","2025년 평택전력 GIS 보통 및 정밀점검공사","평택T/P  #1 CLR #7077 GIS 보통점검","2025-04-23 09:00","2025-04-23 14:00","2025-04-23 09:00","2025-04-23 14:00","연속"]
[150,"경기","평택","평택T/P #2 CLR #7577 CB","2025년 평택전력 GIS 보통 및 정밀점검공사","평택T/P  #2 CLR #7577 GIS 보통점검","2025-04-24 09:00","2025-04-24 14:00","2025-04-24 09:00","2025-04-24 14:00","연속"]
[151,"경기","평택","평택T/P #2 CLR #7677 CB","2025년 평택전력 GIS 보통 및 정밀점검공사","평택T/P  #2 CLR #7677 GIS 보통점검","2025-04-24 14:00","2025-04-24 18:00","2025-04-24 14:00","2025-04-24 18:00","연속"]
[152,"경기","평택","평택T/P SEC CB 75760","2025년 평택전력 GIS 보통 및 정밀점검공사","평택T/P  #75-#76 SEC GIS 보통점검","2025-04-21 09:00","2025-04-21 18:00","2025-04-21 09:00","2025-04-21 18:00","연속"]
[153,"경기","평택","평택T/P SEC CB 70710","2025년 평택전력 GIS 보통 및 정밀점검공사","평택T/P  #70-#71 SEC GIS 보통점검","2025-04-21 09:00","2025-04-21 18:00","2025-04-21 09:00","2025-04-21 18:00","연속"]
[154,"경기","평택","평택T/P CB 7700","2025년 평택전력 GIS 보통 및 정밀점검공사","평택T/P  평택T/P-#1 G/T 1차 TIE GIS(7700) 보통점검","2025-04-22 09:00","2025-04-22 18:00","2025-04-22 09:00","2025-04-22 18:00","연속"]
[155,"경기","평택","평택T/P CB 7771","2025년 평택전력 GIS 보통 및 정밀점검공사","평택T/P  #1 G/T 1차 GIS(7771) 보통점검","2025-04-22 09:00","2025-04-22 18:00","2025-04-22 09:00","2025-04-22 18:00","연속"]
[156,"경기","평택","평택T/P CB 7871","2025년 평택전력 GIS 보통 및 정밀점검공사","평택T/P  #2 G/T 1차 GIS(7871) 보통점검","2025-04-25 09:00","2025-04-25 18:00","2025-04-25 09:00","2025-04-25 18:00","연속"]
[157,"경기","평택","평택T/P CB 7800","2025년 평택전력 GIS 보통 및 정밀점검공사","평택T/P  #2 G/T-#1 S/T 1차 TIE GIS(7800) 보통점검","2025-04-25 09:00","2025-04-25 18:00","2025-04-25 09:00","2025-04-25 18:00","연속"]
[158,"강원","강릉","신양양S/S #3 M.Tr","2025년 강릉전력지사 변전협력회사 공사","362kV CB 조작시험(7472, 7400)","2025-04-18 10:00","2025-04-18 18:00","2025-04-18 10:00","2025-04-18 18:00","연속"]
[159,"강원","강릉","안인개폐소신양양 T/L","2025년 강릉전력지사 변전협력회사 공사","362kV GIS 보통점검(7271, 7200CB)","2025-04-28 10:00","2025-04-29 18:00","2025-04-28 10:00","2025-04-29 18:00","연속"]
[160,"강원","강릉","신양양S/S #2 M.Tr","2025년 강릉전력지사 변전협력회사 공사","주변압기, 362kV GIS, 170kV GIS, 3차 PT 보통점검, 3차 LA 초기점검","2025-04-21 10:00","2025-04-25 18:00","2025-04-21 10:00","2025-04-25 18:00","연속"]
[161,"강원","강릉","신양양S/S CB 7400","2025년 강릉전력지사 변전협력회사 공사","362kV CB 조작시험(7400CB)","2025-04-18 14:00","2025-04-18 18:00","2025-04-18 14:00","2025-04-18 18:00","연속"]
[162,"강원","강릉","신양양S/S CB 7472","2025년 강릉전력지사 변전협력회사 공사","362kV CB 조작시험(7472CB)","2025-04-18 10:00","2025-04-18 14:00","2025-04-18 10:00","2025-04-18 14:00","연속"]
[163,"강원","강릉","안인개폐소양양PP T/L","2025년 강릉전력지사 변전협력회사 공사","362kV CB 특성시험, PT, LA 하자점검","2025-04-11 10:00","2025-04-11 18:00","2025-04-11 10:00","2025-04-11 18:00","연속"]
[164,"강원","강릉","양양P/P CB 7272","2025년 강릉전력지사 변전협력회사 공사","72Bay 차단실패 보호반 대체","2025-04-21 14:00","2025-04-25 18:00","2025-04-21 14:00","2025-04-25 18:00","연속"]
[165,"강원","동해","삼척GP한울NP#1 T/L"," 삼척GP-한울NP1T/L 산불피해개소 전력선교체 공사","산불피해개소 전력선교체","2025-04-14 07:00","2025-04-22 18:00","2025-04-14 07:00","2025-04-22 18:00","연속"]
[166,"강원","동해","삼척GP한울NP#2 T/L"," 삼척GP-한울NP1T/L 산불피해개소 전력선교체 공사","산불피해개소 전력선교체","2025-04-23 07:00","2025-05-02 18:00","2025-04-23 07:00","2025-05-02 18:00","연속"]
[167,"강원","태백","신태백S/S #3 Sh.R CB","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S  #3Sh.R GIS(7579CB) 보통점검","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[168,"강원","태백","신태백S/S CB 7500","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S  #3Sh.R GIS(7579CB) 보통점검","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[169,"강원","태백","신태백S/S #2 Sh.R CB","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S  #2Sh.R GIS(7479CB) 보통점검","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[170,"강원","태백","신태백S/S CB 7400","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S  #2Sh.R GIS(7479CB) 보통점검","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[171,"강원","태백","신태백S/S CB 7471","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S  #2Sh.R GIS(7479CB) 보통점검","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[172,"강원","태백","신태백S/S CB 7571","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S  #3Sh.R GIS(7579CB) 보통점검","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[173,"충북","직할","신진천S/S #2 M.Tr","24~25 직할 변전협력회사공사(부싱절연유채유)","신진천S/S  #2 M.Tr 부싱절연유 채유","2025-04-01 14:00","2025-04-01 18:00","2025-04-01 14:00","2025-04-01 18:00","연속"]
[174,"충북","직할","신진천S/S #1 M.Tr","24~25 직할 변전협력회사공사(부싱절연유채유)","신진천S/S  #1 M.Tr A 부싱절연유 채유","2025-04-01 10:00","2025-04-01 14:00","2025-04-01 10:00","2025-04-01 14:00","연속"]
[175,"충북","청주","남청주S/S #2 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2025-04-01 08:00","2025-04-19 18:00","2025-04-01 08:00","2025-04-19 18:00","연속"]
[176,"충북","청주","신옥천S/S #2 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사","M.Tr 2차측 GIS 보통점검, 3차측 VCB 보통점검 23kV 2-1, 2-2 VCB 초기점검, #1S.Tr 하자점검","2025-04-01 10:00","2025-04-03 18:00","2025-04-01 10:00","2025-04-03 18:00","연속"]
[177,"충북","청주","신옥천S/S #3 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사","M.Tr 2차측 GIS 보통점검 #2S.Tr 하자점검","2025-04-29 09:00","2025-04-29 18:00","2025-04-29 09:00","2025-04-29 18:00","연속"]
[178,"충북","충주","신제천S/S #2 BUS","신제천S/S 362KV GIS PD 제작사 하자보수","신제천S/S  #2BUS DS(7252,7352,7452)DS PD 하자보수","2025-04-14 09:00","2025-04-18 18:00","취소","취소","연속"]
[179,"충북","충주","신제천S/S #2 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #2BUS DS(7652,7752,7952,7A52)하자보수","2025-04-28 09:00","2025-05-03 18:00","취소","취소","연속"]
[180,"충북","충주","신제천신영주#2 T/L"," 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.1-165)","2025-04-01 07:00","2025-04-21 16:00","2025-04-01 07:00","2025-04-21 16:00","매일"]
[181,"충북","충주","신제천S/S #1 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #1BUS DS(7251,7351,7451) PD 하자보수","2025-04-07 09:00","2025-04-11 18:00","취소","취소","연속"]
[182,"충북","충주","신제천S/S #2 M.Tr","24-25년 충주전력지사 변전협력회사 총액공사","신제천S/S  #2M.Tr 본체 및 2차 GIS 보통점검","2025-04-03 10:00","2025-04-04 18:00","취소","취소","연속"]
[183,"충북","충주","신제천S/S #1 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #1BUS DS(7651,7751,7951,7A51) PD 하자보수","2025-04-21 09:00","2025-04-26 18:00","취소","취소","연속"]
[184,"충북","충주","신충주S/S #4 M.Tr","안전한국훈련 시범훈련(신충주S/S)","신충주S/S #4M.Tr C상 고장복구훈련","2025-04-30 09:00","2025-04-30 18:00","2025-04-30 09:00","2025-04-30 18:00","연속"]
[185,"충북","충주","신제천신충주T#1 T/L"," 신용인-동서울 등 16개 T/L 추락방지장치 설치공사"," 신제천-여주CC T/L 추락방지장치 설치공사 - 신제천-여주CC 연계선로로 인한 휴전(신충주 T분기 실작업 없음)","2025-04-26 07:00","2025-04-27 18:00","취소","취소","매일"]
[186,"대전세종충남","대전","신계룡S/S #1 M.Tr","[즉시가압O]신계룡S/S  #1M.Tr 보통점검","[즉시가압O]신계룡S/S  #1M.Tr 보통점검","2025-04-14 09:00","2025-04-16 18:00","2025-04-14 09:00","2025-04-16 18:00","연속"]
[187,"대전세종충남","서산","북당진신탕정#2 T/L"," 아산-화성T/L 레일형 추락방지장치 설치공사(4회선)(주말x)","[즉시가압가능] 아산-화성T/L No. 25 ~26 추락방지장치 설치 [병가철탑] (상단)북당진-신탕정T/L No.59~60 / (하단)아산-화성T/L No.25,26","2025-04-01 07:00","2025-04-03 18:00","취소","취소","매일"]
[188,"대전세종충남","서산","북당진신탕정#1 T/L"," 아산-화성T/L 레일형 추락방지장치 설치공사(4회선)(주말x)","[즉시가압가능] 아산-화성T/L No. 25 ~26 추락방지장치 설치 [병가철탑] (상단)북당진-신탕정T/L No.59~60 / (하단)아산-화성T/L No.25,26","2025-04-04 07:00","2025-04-08 18:00","취소","취소","매일"]
[189,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) *3월 휴전 승인 시 취소요청 * 신당진개폐소-태안화력#2T/L 병가선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청","2025-04-25 08:00","2025-04-25 18:00","2025-04-25 08:00","2025-04-25 18:00","연속"]
[190,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","'24~'25 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 점퍼지지애자 교체공사[매일] - No.47, 104, 106 (20분 이내 즉시가압 가능) [서산변전 병행] 태안화력S/S  개폐소-태안화력#1T/L LA, CVT 보통점검 신당진개폐소  개폐소-태안화력#1T/L LA, CVT 보통점검","2025-04-28 07:30","2025-04-30 18:00","2025-04-28 07:30","2025-04-30 18:00","매일"]
[191,"대전세종충남","서산","신당진개폐소북당진 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#1T/L 병가선로,  신당진개폐소-태안화력#1T/L 휴전 미승인시 휴전 취소 요청","2025-04-30 08:00","2025-04-30 18:00","2025-04-30 08:00","2025-04-30 18:00","연속"]
[192,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) *3월 휴전 승인 시 취소요청 * 신당진개폐소-현대제철T/L 병가선로,  신당진개폐소-현대제철T/L 휴전 미승인시 휴전 취소 요청","2025-04-25 08:00","2025-04-25 18:00","2025-04-25 08:00","2025-04-25 18:00","연속"]
[193,"대전세종충남","서산","신당진S/S #1 M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진S/S  #1M.Tr 2차 GIS DS 및 ES 코일불량 하자조치","2025-04-01 09:30","2025-04-01 18:00","2025-04-01 09:30","2025-04-01 18:00","연속"]
[194,"대전세종충남","서산","신당진S/S #3 M.Tr","25년 서산P/O  이하 M.Tr 보통점검공사","(즉시가압가능) 신당진S/S  #3M.Tr 보통점검","2025-04-14 09:30","2025-04-18 18:00","2025-04-14 09:30","2025-04-18 18:00","연속"]
[195,"대전세종충남","서산","신서산태안TP#1 T/L","'24~'25년도 서산전력지사 송전협력회사"," 신서산-태안화력#1T/L 항공구 교체공사[매일] No.21~22 *비상시 20분 이내 가압가능 및 No.35,66 점퍼지지애자 교체공사[매일]","2025-04-22 07:30","2025-04-24 18:00","2025-04-22 07:30","2025-04-24 18:00","매일"]
[196,"대전세종충남","서산","신서산태안TP#2 T/L","태안화력S/S  옥외 기타설비 내장화공사","(즉시가압불가) 태안화력S/S  신서산-태안화력#2T/L CVT 내장화공사","2025-04-07 09:00","2025-04-21 18:00","취소","취소","연속"]
[197,"대전세종충남","서산","태안T/P #70 BUS","태안화력S/S  7151DS 가스누기보수공사","(즉시가압불가) 태안화력S/S  7151DS 가스누기 보수공사","2025-04-01 09:30","2025-04-04 18:00","2025-04-01 09:30","2025-04-04 18:00","연속"]
[198,"대전세종충남","천안","신온양신탕정#2 T/L","(3월 취소시)신온양S/S  #78Bay B/F PNL 대체","(즉시가압불가)신온양S/S  #78Bay 노후 B/F PNL 대체","2025-04-28 09:00","2025-05-02 18:00","취소","취소","연속"]
[199,"대전세종충남","천안","신온양서서울#1 T/L","(3월취소시)신온양S/S  #78Bay 노후 B/F PNL 대체","(즉시가압불가)신온양S/S  #78Bay 노후 B/F PNL 대체","2025-04-28 09:00","2025-05-02 18:00","취소","취소","연속"]
[200,"대전세종충남","천안","신온양S/S #3 M.Tr","신온양S/S  #3M.Tr 부싱절연유 채유","신온양S/S  #3M.Tr 부싱절연유 채유","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[201,"대전세종충남","천안","신탕정S/S #2 BUS","(3월 취소시)신탕정S/S  #75BUS 노후 PNL 대체","(즉시가압불가)신탕정S/S  #75BUS 노후 보호배전반 대체","2025-04-22 09:00","2025-04-25 18:00","2025-04-22 09:00","2025-04-25 18:00","연속"]
[202,"대전세종충남","천안","신탕정S/S #1 BUS","(3월 취소시)신탕정S/S  #70BUS 노후 보호배전반 대체","(즉시가압불가)신탕정S/S  #70BUS 노후 보호배전반 대체","2025-04-14 09:00","2025-04-18 18:00","2025-04-14 09:00","2025-04-18 18:00","연속"]
[203,"대전세종충남","천안","아산화성#2 T/L"," 아산-화성T/L 레일형 추락방지장치 설치공사(4회선)(주말x)","[즉시가압가능] 아산-화성T/L No. 25 ~26 추락방지장치 설치 [병가철탑] (상단)북당진-신탕정T/L No.59~60 / (하단)아산-화성T/L No.25,26","2025-04-04 07:00","2025-04-11 18:00","취소","취소","매일"]
[204,"대전세종충남","천안","아산화성#1 T/L"," 아산-화성T/L 레일형 추락방지장치 설치공사(4회선구간)","[즉시가압가능] 아산-화성T/L No. 25 ~26 추락방지장치 설치 [병가철탑] (상단)북당진-신탕정T/L No.59~60 / (하단)아산-화성T/L No.25,26","2025-04-01 07:00","2025-04-03 18:00","취소","취소","매일"]
[205,"대전세종충남","천안","아산S/S #4 M.Tr","아산S/S  #4M.Tr 부싱절연유 채유","아산S/S  #4M.Tr 부싱절연유 채유","2025-04-14 09:00","2025-04-14 18:00","2025-04-14 09:00","2025-04-14 18:00","연속"]
[206,"대전세종충남","청양","보령C/C #71 BUS","보령복합S/Y  장기사용 GIS 교체 및 SW 증설","- (기설)BUS SEC 70-71-0 철거 및 GIB 설치, 7351, 7551 DS 도킹","2025-04-16 09:00","2025-05-16 18:00","2025-04-16 09:00","2025-05-16 18:00","연속"]
[207,"대전세종충남","청양","청양군산#2 T/L","[송전]  청양군산#2 T/L 애자련 보강"," 청양군산#2 TL 애자련 보강","2025-04-14 07:30","2025-04-15 18:00","취소","취소","연속"]
[208,"대전세종충남","청양","청양군산#1 T/L","[송전]  청양군산#1 T/L 가공지선, 항공구 교체"," 청양군산#1 TL 가공지선, 항공구 교체 및 애자련 보강","2025-04-07 07:30","2025-04-11 18:00","취소","취소","연속"]
[209,"전북","군산","군산새만금#2 T/L","군산P/O 154kV이상 차단기 점검공사","군산, 새만금S/S 양단 차단기 점검 군산S/S 차단기 절연열화 측정","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[210,"전북","군산","군산새만금#1 T/L","군산P/O 154kV이상 차단기 점검공사","군산, 새만금S/S 양단 차단기 점검 군산S/S 차단기 절연열화 측정","2025-04-07 09:00","2025-04-07 18:00","2025-04-07 09:00","2025-04-07 18:00","연속"]
[211,"전북","군산","군산S/S #1 M.Tr","군산P/O 변압기 부싱 절연유 채유공사","#1M.Tr 2차 A,B상 절연유 채유 7172 차단기 조작시험 4189 차단기 하자점검","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[212,"전북","군산","군산S/S #1 Sh.R CB","군산P/O 154kV이상 차단기 조작시험 및 피엔씨테크제 IED 성능개선","- 군산S/S #1Sh.R 차단기 조작시험 및 절연열화 측정 - 피엔씨테크제 IED 성능개선","2025-04-01 09:00","2025-04-01 18:00","2025-04-01 09:00","2025-04-01 18:00","연속"]
[213,"전북","군산","군산신김제#2 T/L","군산P/O 154kV이상 차단기 조작시험","군산-신김제#2T/L 차단기 조작시험","2025-04-30 09:00","2025-04-30 14:00","2025-04-30 09:00","2025-04-30 14:00","연속"]
[214,"전북","군산","군산신김제#1 T/L","군산P/O 154kV이상 차단기 조작시험","군산-신김제#1T/L 차단기 조작시험","2025-04-30 14:00","2025-04-30 18:00","2025-04-30 14:00","2025-04-30 18:00","연속"]
[215,"전북","군산","새만금S/S #2 M.Tr","새만금S/S #2M.Tr 추락방지장치 설치공사","새만금S/S #2M.Tr 추락방지장치 설치공사","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","연속"]
[216,"전북","김제","신김제S/S #2 M.Tr","25년 김제전력지사 변압기 부싱유 채유"," #2M.Tr 부싱유 채유(추적관리 분석용)","2025-04-02 09:00","2025-04-02 12:00","2025-04-02 09:00","2025-04-02 12:00","연속"]
[217,"전북","김제","신김제S/S #1 M.Tr","25년 김제전력지사 변압기 부싱유 채유"," #1M.Tr 부싱유 채유(추적관리 분석용)","2025-04-01 09:00","2025-04-01 12:00","2025-04-01 09:00","2025-04-01 12:00","연속"]
[218,"전북","김제","신김제S/S #3 M.Tr","신김제S/S #2S.Tr 교체공사 관련 안전거리 확보 휴전","신김제S/S #2S.Tr 교체공사 관련 안전이격 거리 확보 휴전","2025-04-04 09:00","2025-04-04 18:00","2025-04-04 09:00","2025-04-04 18:00","연속"]
[219,"전북","직할","신남원의령#1 T/L","'25년 전북 직할 가공송전 순시점검 위탁공사","○ 정밀점검 : No.137~180","2025-04-01 08:00","2025-04-04 18:00","취소","취소","매일"]
[220,"전북","직할","신남원S/S CB 7471","신남원S/S 신남원-의령 #2T/L GIS 보통점검","신남원S/S 신남원-의령 #2T/L GIS 보통점검","2025-04-08 09:00","2025-04-09 18:00","2025-04-08 09:00","2025-04-09 18:00","연속"]
[221,"전북","직할","신남원의령#2 T/L","'25년 전북 직할 가공송전 순시점검 위탁공사","○ 정밀점검 : No.137~180","2025-04-07 08:00","2025-04-11 18:00","취소","취소","매일"]
[222,"전북","직할","신남원광양#1 T/L","2025년 전북직할 362kV GIS 정밀점검공사(무부하가압선로)","7500 차단기 정밀점검(무부하가압선로)","2025-04-18 18:00","2025-04-18 18:30","2025-04-18 18:00","2025-04-18 18:30","연속"]
[223,"전북","직할","신남원S/S CB 7500","2025년 전북직할 362kV GIS 정밀점검공사","7500 차단기 정밀점검(단일차단기)","2025-04-15 09:00","2025-04-18 18:00","2025-04-15 09:00","2025-04-18 18:00","연속"]
[224,"전북","직할","신옥천신남원#2 T/L","신남원S/S 신옥천-신남원#2T/L CVT(A,B,C상) 초기점검","신남원S/S 신옥천-신남원#2T/L CVT(A,B,C상) 초기점검","2025-04-14 09:00","2025-04-14 18:00","2025-04-26 09:00","2025-04-26 18:00","연속"]
[225,"전북","직할","신남원S/S CB 7400","2025년 전북직할 362kV GIS 정밀점검공사","7400 차단기 정밀점검(단일차단기 정밀)","2025-04-08 09:00","2025-04-11 18:00","2025-04-08 09:00","2025-04-11 18:00","연속"]
[226,"전북","직할","신남원의령#1 T/L","2025년 전북직할 362kV GIS 정밀점검공사(무부하가압선로)","7300 차단기 정밀점검(무부하가압선로)","2025-04-04 18:00","2025-04-04 18:30","2025-04-04 18:00","2025-04-04 18:30","연속"]
[227,"전북","직할","신남원S/S CB 7300","2025년 전북직할 362kV GIS 정밀점검공사","7300 차단기 정밀점검(단일차단기 정밀)","2025-04-01 09:00","2025-04-04 18:00","2025-04-01 09:00","2025-04-04 18:00","연속"]
[228,"전북","직할","신남원신광주#1 T/L"," 신남원-신광주T/L 피뢰기 설치공사(계속)","○ #1T/L 피뢰기 설치공사 : No.1~115","2025-04-21 07:30","2025-04-28 18:00","취소","취소","매일"]
[229,"전북","직할","신남원의령#2 T/L","2025년 전북직할 362kV GIS 정밀점검공사(무부하가압선로)","7400 차단기 정밀점검(무부하가압 선로)","2025-04-11 18:00","2025-04-11 18:30","2025-04-11 18:00","2025-04-11 18:30","연속"]
[230,"광주전남","강진","신화순신강진#2 T/L","2024~2025년 강진전력지사 송전협력회사","철탑 추락방지장치 설치","2025-04-28 07:00","2025-05-02 18:00","2025-04-28 07:00","2025-05-02 18:00","매일"]
[231,"광주전남","강진","신화순신강진#1 T/L","2024~2025년 강진전력지사 송전협력회사","철탑 추락방지장치 설치","2025-04-21 07:00","2025-04-25 18:00","취소","취소","매일"]
[232,"광주전남","광주","신광주신화순#2 T/L","2024~25년 광주전력지사 송전 협력회사공사(추락방지)"," 신광주-신화순T/L 추락방지장치설치공사 No.41~57호","2025-04-28 07:00","2025-04-28 18:00","취소","취소","연속"]
[233,"광주전남","광주","신광주S/S #1 BUS","장기사용  #1BUS 모선보호반 교체","장기사용  #1BUS 모선보호반 교체","2025-04-01 08:00","2025-04-03 18:00","취소","취소","연속"]
[234,"광주전남","광주","신광주S/S #2 BUS","장기사용  #2BUS 모선보호반 교체","장기사용  #2BUS 모선보호반 교체","2025-04-04 08:00","2025-04-06 18:00","취소","취소","연속"]
[235,"광주전남","광주","신남원신광주#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 시행","2025-04-07 08:00","2025-04-11 18:00","취소","취소","매일"]
[236,"광주전남","광주","신남원신광주#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 시행","2025-04-14 08:00","2025-04-18 18:00","취소","취소","매일"]
[237,"광주전남","목포","신김제한빛NP#1 T/L","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사 7D Bay 3CB 교체(71,72,00) #2 BUS 교체(모선측 DS 포함) 주말, 휴일작업 있음","2025-04-12 07:00","2025-06-06 18:00","취소","취소","연속"]
[238,"광주전남","목포","한빛#3N/P CB 7B71","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사 7D Bay 3CB 교체(71,72,00) #2 BUS 교체(모선측 DS 포함) 주말, 휴일작업 있음","2025-04-12 07:00","2025-06-06 18:00","2025-04-12 07:00","2025-06-06 18:00","연속"]
[239,"광주전남","순천","광양S/S #2 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #2M.Tr 3차 MAIN VCB 초기점검","2025-04-04 09:00","2025-04-04 18:00","2025-04-04 09:00","2025-04-04 18:00","연속"]
[240,"광주전남","순천","광양하동TP#2 T/L"," 광양-하동TP T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-04-08 07:00","2025-04-08 18:00","취소","취소","연속"]
[241,"광주전남","순천","광양S/S #3 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #3M.Tr 보통점검 및 1,2,3차 LA(A,B,C, 총 9EA) 대체, 추락방지장치설치","2025-04-07 09:00","2025-04-11 18:00","2025-04-28 09:00","2025-05-02 18:00","연속"]
[242,"광주전남","순천","광양S/S #1 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #1M.Tr 3차 MAIN VCB 조작시험, #1-1,1-2Sh.R 및 #1S.Tr VCB 초기점검","2025-04-01 09:00","2025-04-03 18:00","2025-04-01 09:00","2025-04-03 18:00","연속"]
[243,"광주전남","순천","신남원광양#1 T/L","가스누기관련 누기개소 파악","가스누기관련 누기개소 파악","2025-04-21 09:00","2025-04-23 18:00","취소","취소","매일"]
[244,"광주전남","순천","광양여수TP T/L"," 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 추락방지시설 설치","2025-04-21 07:00","2025-04-21 18:00","2025-04-25 07:00","2025-04-25 18:00","연속"]
[245,"광주전남","순천","신강진광양#1 T/L"," 신강진-광양T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-04-07 07:00","2025-04-11 18:00","취소","취소","매일"]
[246,"광주전남","순천","신강진광양#2 T/L"," 신강진-광양T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-04-14 07:00","2025-04-18 18:00","취소","취소","매일"]
[247,"광주전남","순천","여수T/P #4 M.Tr","여수화력S/Y  #4M.Tr 종합예방진단시스템 설치공사","1. 작업명 : 여수화력S/Y  #4M.Tr 종합예방진단시스템 설치공사 2. 작업일시 : 2025. 4. 23(수) 13:00 ~ 4. 25(목) 17:00 3. 작업장소 : 여수T/P  #4 M.Tr A","2025-04-23 13:00","2025-04-25 17:00","취소","취소","연속"]
[248,"광주전남","순천","여수T/P #2 M.Tr","여수화력S/Y  #2M.Tr 종합예방진단시스템 설치공사","1. 작업명 : 여수화력S/Y  #2M.Tr 종합예방진단시스템 설치공사 2. 작업일시 : 2025. 4. 21(월) 09:00 ~ 4. 23(수) 13:00 3. 작업장소 : 여수T/P  #2 M.Tr A","2025-04-21 09:00","2025-04-23 13:00","취소","취소","연속"]
[249,"광주전남","순천","여수T/P #3 M.Tr","24-25년 순천전력지사 변전협력회사 공사","여수화력S/S #3M.Tr 1차 GIS(7300,7372) 및 1차 LA(A,B,C) 보통점검, 추락방지장치설치","2025-04-14 09:00","2025-04-18 18:00","취소","취소","연속"]
[250,"광주전남","순천","율촌CC여수TP T/L"," 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 추락방지시설 설치","2025-04-22 07:00","2025-04-22 18:00","2025-04-29 07:00","2025-04-29 18:00","연속"]
[251,"대구","달성","고령의령#1 T/L","7300, 7371 CB 정밀점검, LA,PT보통점검","7300, 7371 CB 정밀점검, LA,PT보통점검","2025-04-21 09:00","2025-04-25 18:00","취소","취소","연속"]
[252,"대구","달성","고령S/S #1 BUS","[TEST]T/L GIS 정밀점검","[TEST]T/L GIS 정밀점검","2025-04-25 17:00","2025-04-25 18:00","취소","취소","연속"]
[253,"대구","달성","북경남대구#2 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 북경남-대구 #2T/L 52,54-56호 초기점검","2025-03-07 13:00","2025-03-07 17:00","2025-03-07 13:00","2025-03-07 17:00","연속"]
[254,"대구","달성","대구S/S #2 M.Tr","M.Tr 방호벽 사다리 철거","M.Tr 방호벽 사다리 철거","2025-04-23 09:00","2025-04-23 18:00","2025-04-23 09:00","2025-04-23 18:00","연속"]
[255,"대구","달성","대구S/S #3 M.Tr","M.Tr 방호벽 사다리 철거","M.Tr 방호벽 사다리 철거","2025-04-24 09:00","2025-04-25 18:00","2025-04-24 09:00","2025-04-25 18:00","연속"]
[256,"대구","칠곡","신포항북대구 T/L","2024~2025년도 대구본부 칠곡전력지사 송전협력회사 공사"," 신포항-북대구T/L 수평 추락방지장치 설치 - No.14~28.1, 42~44.1","2025-04-03 07:00","2025-04-07 18:00","2025-04-03 07:00","2025-04-07 18:00","연속"]
[257,"대구","칠곡","북대구S/S #2 M.Tr","24~25년 칠곡전력지사 변전협력회사 공사","부싱 절연열화 측정, 2차 LA 보통점검,  GIS 조작시험","2025-04-07 09:30","2025-04-08 18:00","2025-04-07 09:30","2025-04-08 18:00","연속"]
[258,"대구","칠곡","북대구S/S #3 M.Tr","24~25년 칠곡전력지사 변전협력회사 공사","부싱 절연열화 측정, 2차 LA 보통점검,  GIS 조작시험","2025-04-09 09:30","2025-04-10 18:00","2025-04-09 09:30","2025-04-10 18:00","연속"]
[259,"대구","칠곡","서대구고령#2 T/L"," 서대구-고령#2T/L PT 보통점검, GCB 조작시험"," 서대구-고령#2T/L PT 보통점검, GCB 조작시험","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[260,"대구","포항","신포항신월성NP#4 T/L","154kV 신포항-천북 등 19개T/L 추락방지장치 설치공사"," 신포항-신월성NP#4T/L 추락방지장치(수평) 설치공사","2025-04-14 08:00","2025-04-18 18:00","2025-04-14 08:00","2025-04-18 18:00","연속"]
[261,"대구","포항","신포항신월성NP#3 T/L","154kV 신포항-천북 등 19개T/L 추락방지장치 설치공사"," 신포항-신월성NP#3T/L 추락방지장치(수평) 설치공사","2025-04-03 08:00","2025-04-11 18:00","2025-04-03 08:00","2025-04-11 18:00","연속"]
[262,"대구","포항","월성N/P SEC CB 75760","2024~25년도 포항전력지사 변전총액공사","월성S/Y 75-76 GIS 조작시험","2025-04-10 14:00","2025-04-10 18:00","2025-04-10 14:00","2025-04-10 18:00","연속"]
[263,"대구","포항","월성N/P SEC CB 70710","2024~25년도 포항전력지사 변전총액공사","월성S/Y 70-71 GIS 조작시험","2025-04-10 09:00","2025-04-10 14:00","2025-04-10 09:00","2025-04-10 14:00","연속"]
[264,"경북","구미","북대구선산 T/L","2024-2025년 구미전력지사 송전협력회사 공사","[병가]  서대구-선산#1T/L No.30~107 수평추락방지장치설치","2025-04-25 07:30","2025-05-02 17:30","2025-04-25 07:30","2025-05-02 17:30","연속"]
[265,"경북","구미","서대구선산#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 서대구-선산#1T/L No.30~107 수평추락방지장치설치","2025-04-14 07:30","2025-05-02 17:30","2025-04-14 07:30","2025-05-02 17:30","연속"]
[266,"경북","구미","선산S/S #1 M.Tr","2024-25년 구미전력지사 변전협력회사 공사","- M.Tr 보통점검[정밀] - 변압기 상부추락방지장치 설치 - 1차 7072 GIS 보통점검[정밀] - 1차 LA, 2차 LA 보통점검 - 96P,D 절체스위치 설치","2025-04-21 09:00","2025-04-22 18:00","2025-04-21 09:00","2025-04-22 18:00","연속"]
[267,"경북","구미","선산S/S #4 M.Tr","2024-25년 구미전력지사 변전협력회사 공사","- 7772,7700 GIS 하자점검 - 1차 A,B상 부싱절연유 채유 - 2차 부싱절연유 채유 - 96P,D 절체스위치 설치 - 변압기 상부추락방지장치 설치","2025-04-23 09:00","2025-04-24 18:00","2025-04-23 09:00","2025-04-24 18:00","연속"]
[268,"경북","영주","신한울한울#1 T/L","500kV 동해안변환소 AC배후계통 연결T/L 건설공사","- 구간 : 500kV 동해안변환소~ 한울NP3S/Y-신한울NP1S/Y,  신영주~NP3S/Y - 선종 : ACSR/AW 480(C) - 철탑 : 신설 10기(산형강 6기, CT 4기), 철거 5기(산형강 5기)","2025-04-18 07:00","2025-04-25 18:00","2025-04-18 07:00","2025-04-25 18:00","연속"]
[269,"경북","영주","신한울한울#2 T/L","500kV 동해안변환소 AC배후계통 연결T/L 건설공사","- 구간 : 500kV 동해안변환소~ 한울NP3S/Y-신한울NP1S/Y,  신영주~NP3S/Y - 선종 : ACSR/AW 480(C) - 철탑 : 신설 10기(산형강 6기, CT 4기), 철거 5기(산형강 5기)","2025-04-26 07:00","2025-05-03 18:00","2025-04-26 07:00","2025-05-03 18:00","연속"]
[270,"경북","직할","신영일안동CC T/L","'24-25년 경북직할 송전협력회사 공사"," 신영일안동CC T/L 추락방지장치, 고정형폴리머 점퍼지지애자 설치","2025-04-09 08:00","2025-04-30 18:00","취소","취소","연속"]
[271,"경북","직할","신영주청송PP T/L","'24-25년 경북직할 송전협력회사 공사"," 신영주청송pp T/L 추락방지장치, 고정형폴리머 점퍼지지애자 설치","2025-04-09 08:00","2025-04-30 18:00","취소","취소","연속"]
[272,"부산울산","동부산","고리N/P #1 CLR CB","고리NP S/Y  #1CLR T/L PNL 대체","고리NP S/Y  #1CLR T/L PNL 대체 병행)SEC B/F PNL 대체 병행) 7077GIS 보통점검 및 절연열화 측정","2025-04-14 09:00","2025-04-18 18:00","2025-04-14 09:00","2025-04-18 18:00","연속"]
[273,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S  용량부족 차단기 교체공사(6차)","73BAY(7371, 7300, 7372CB) 교체","2025-04-07 08:00","2025-08-29 18:00","2025-04-21 08:00","2025-09-30 18:00","연속"]
[274,"부산울산","동부산","신양산고리NP#2 T/L","동부산전력지사 변전총액공사","고리NP S/Y 신양산-고리#2T/L, 7A B/F PNL 대체","2025-04-01 09:00","2025-04-05 18:00","취소","취소","연속"]
[275,"부산울산","동부산","신양산북부산#2 T/L","신양산S/S  용량부족 차단기 교체공사(6차)","73BAY(7371, 7300, 7372CB) 교체","2025-04-07 08:00","2025-08-29 18:00","2025-04-21 08:00","2025-09-30 18:00","연속"]
[276,"부산울산","동부산","신양산S/S #2 BUS","신양산S/S  용량부족 차단기 교체공사(6차)","73BAY(7371, 7300, 7372CB) 교체 안전이격 휴전(7352DS 접속부 분리)","2025-04-14 08:00","2025-04-14 18:00","2025-04-28 08:00","2025-04-28 18:00","연속"]
[277,"부산울산","동부산","신양산S/S #1 BUS","신양산S/S  용량부족 차단기 교체공사(6차)","73BAY(7371, 7300, 7372CB) 교체 안전이격 휴전(7351DS 접속부 분리)","2025-04-16 08:00","2025-04-16 18:00","2025-04-30 08:00","2025-04-30 18:00","연속"]
[278,"부산울산","북부산","신김해북부산#2 T/L","24-25년 북부산전력지사 가공송전 협력회사공사","○ 압축인류클램프 교체 : No.4,50(2기)","2025-04-10 08:00","2025-04-10 18:00","2025-04-26 08:00","2025-04-26 18:00","연속"]
[279,"부산울산","북부산","신김해북부산#1 T/L","24-25년 북부산전력지사 가공송전 협력회사공사","○ 압축인류클램프 교체 : No.4,22,40,43,50(5기)","2025-04-28 08:00","2025-04-29 18:00","2025-04-19 08:00","2025-04-20 18:00","연속"]
[280,"부산울산","북부산","북부산신울산#1 T/L"," 북부산-신울산T/L 지장송전선로 지중화공사"," 북부산-울산T/L No.50~53호간 지장송전선로 지중화 공사 - 임시선로 구성","2025-04-02 08:00","2025-04-05 18:00","2025-04-02 08:00","2025-04-05 18:00","연속"]
[281,"부산울산","북부산","북부산S/S #2 M.Tr","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S  75BAY B/F PRO 대체공사","2025-04-14 09:00","2025-04-18 18:00","2025-04-21 09:00","2025-04-23 18:00","연속"]
[282,"부산울산","북부산","북부산고리NP#1 T/L","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S  75BAY B/F PRO 대체공사","2025-04-14 09:00","2025-04-18 18:00","취소","취소","연속"]
[283,"부산울산","북부산","북부산S/S #71 BUS","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S  71BUS PRO 대체공사","2025-04-23 09:00","2025-04-25 18:00","2025-04-14 09:00","2025-04-18 18:00","연속"]
[284,"부산울산","북부산","북부산고리NP#2 T/L","24-25년 북부산전력지사 가공송전 협력회사공사","○ 압축인류클램프 교체 : No.81,119,120,145(4기) ○ 폴리머애자 설치 : No.138(1기)","2025-04-21 08:00","2025-04-22 18:00","취소","취소","연속"]
[285,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S  #1M.Tr 증설공사","모선구분차단기 설치 후 모선보호반 이설(60-65 → 61-66)","2025-04-23 09:00","2025-04-23 18:00","2025-04-23 09:00","2025-04-23 18:00","연속"]
[286,"부산울산","울산","남울산S/S #3 M.Tr","25년 울산전력지사 변전협력회사 공사","- 변압기 추락방지장치 설치 - 7572 GIS 보통점검","2025-04-04 09:00","2025-04-04 18:00","2025-04-04 09:00","2025-04-04 18:00","연속"]
[287,"부산울산","울산","남울산S/S CB 7600","남울산S/S 일진제 345GIS 하자보수","- 7600 일진제 하자보수 유압조작기 교체","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","연속"]
[288,"부산울산","울산","신온산S/S #1 M.Tr","25년 울산전력지사 변전협력회사 공사","- 1,2차 부싱절연유 채유","2025-04-29 09:00","2025-04-29 18:00","2025-04-29 09:00","2025-04-29 18:00","연속"]
[289,"부산울산","울산","신온산신울산#1 T/L","25년 울산전력지사 변전협력회사 공사","- 피뢰기 보통점검","2025-04-02 09:00","2025-04-02 18:00","2025-04-02 09:00","2025-04-02 18:00","연속"]
[290,"부산울산","울산","신온산S/S #2 M.Tr","25년 울산전력지사 변전협력회사 공사","- 1,2차 부싱절연유 채유 - 7472 GIS 하자점검 - 2차 GIS 보통점검 - 1,2차 LA 보통점검 - 변압기 추락방지장치 설치","2025-04-10 09:00","2025-04-11 18:00","2025-04-17 09:00","2025-04-18 18:00","연속"]
[291,"부산울산","울산","신울산S/S #4 M.Tr","25년 울산전력지사 변전협력회사 공사","- 1,2차 부싱절연유 채유 - 7872 GIS 하자점검","2025-04-01 09:00","2025-04-01 18:00","2025-04-01 09:00","2025-04-01 18:00","연속"]
[292,"부산울산","울산","울산C/C #1 M.Tr","25년 울산전력지사 변전협력회사 공사","- 1,2차 부싱절연유 채유","2025-04-28 09:00","2025-04-28 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[293,"부산울산","울산","울산C/C #2 M.Tr","25년 울산전력지사 변전협력회사 공사","- 1,2차 부싱절연유 채유","2025-04-29 09:00","2025-04-29 18:00","2025-04-30 09:00","2025-04-30 18:00","연속"]
[294,"부산울산","직할","신대연S/S #1 M.Tr","24~25년 직할 변전협력회사 총액공사","신대연S/S #1M.Tr, 71BAY BF 보호반 대체, 4189 GIS 보통점검","2025-04-07 09:30","2025-04-16 18:00","2025-04-13 09:30","2025-04-17 18:00","연속"]
[295,"부산울산","직할","신양산신대연#1 T/L","24~25년 직할 변전협력회사 총액공사","신대연S/S #1M.Tr, 71BAY BF 보호반 대체, 4189 GIS 보통점검","2025-04-07 09:30","2025-04-16 18:00","취소","취소","연속"]
[296,"경남","김해송변전부","신마산신김해#1 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2025-04-05 07:00","2025-04-05 18:00","2025-04-05 07:00","2025-04-05 18:00","연속"]
[297,"경남","김해송변전부","신마산신김해#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2025-04-06 07:00","2025-04-06 18:00","2025-04-06 07:00","2025-04-06 18:00","연속"]
[298,"경남","김해송변전부","신김해창원#2 T/L","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-04-16 07:00","2025-04-16 18:00","2025-04-16 07:00","2025-04-16 18:00","연속"]
[299,"경남","김해송변전부","신김해창원#1 T/L","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-04-20 07:00","2025-04-20 18:00","2025-04-20 07:00","2025-04-20 18:00","연속"]
[300,"경남","김해송변전부","신김해신녹산#1 T/L","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-04-13 07:00","2025-04-15 18:00","2025-04-13 07:00","2025-04-15 18:00","매일"]
[301,"경남","김해송변전부","신김해신녹산#2 T/L","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-04-17 07:00","2025-04-19 18:00","2025-04-17 07:00","2025-04-19 18:00","매일"]
[302,"경남","김해송변전부","신김해S/S #5 M.Tr","신김해S/S #5M.Tr 보통점검","신김해S/S #5M.Tr 보통점검 - 7600, 7672 GIS 보통점검 / 2차 LA 보통점검","2025-04-28 09:30","2025-05-02 17:30","2025-04-28 09:30","2025-05-02 17:30","연속"]
[303,"경남","직할","창원신고성#2 T/L","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","154kV 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-04-20 07:00","2025-04-20 18:00","2025-04-20 07:00","2025-04-20 18:00","연속"]
[304,"경남","진주","의령하동화력#2 T/L"," 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 :  의령-하동화력#2T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(의령-산청양수#1T/L 병가있음, 하동기준 No.135~152 산청기준 No.112~129)","2025-04-11 07:00","2025-04-18 18:00","2025-04-17 07:00","2025-04-24 18:00","매일"]
[305,"경남","진주","의령산청양수#1 T/L"," 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 :  의령-산청양수#1T/L측 수평 추락방지장치 설치 2.작업구간 :  의령-산청양수T/L No.112~129( 의령-하동화력 #2 T/L과 병가있음, 산청기준 No.112~129 하동기준 No.135~152)","2025-04-11 07:00","2025-04-18 18:00","2025-04-17 07:00","2025-04-18 18:00","매일"]
[306,"경남","진주","의령산청양수#2 T/L"," 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1.작업내용 :  의령-산청양수#2T/L측 수평 추락방지장치 설치 2.작업구간 :  의령-산청양수T/L No.112~129( 의령-하동화력 #1 T/L과 병가있음, 산청기준 No.112~129 하동기준 No.135~152)","2025-04-03 07:00","2025-04-10 18:00","2025-04-16 07:00","2025-04-17 18:00","매일"]
[307,"경남","진주","의령하동화력#1 T/L"," 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 :  의령-하동화력#1T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1~152(의령-산청양수#2T/L 병가있음, 하동기준 No.135~152 산청기준 No.112~129)","2025-04-03 07:00","2025-04-10 18:00","2025-04-10 07:00","2025-04-17 18:00","매일"]
[308,"경남","진주","하동T/P CB 7500","하동T/P  7500 GIS 컨트롤 블록 교체","하동T/P  7500 GIS 컨트롤 블록 교체 [병행] 7500 CB 조작시험","2025-04-16 14:00","2025-04-18 18:00","2025-04-16 14:00","2025-04-18 18:00","연속"]
[309,"경남","진주","하동T/P CB 7572","하동T/P  7572 GIS 컨트롤 블록 교체","하동T/P  7572 GIS 컨트롤 블록 교체 [병행] 7572 CB 조작시험","2025-04-14 10:00","2025-04-16 14:00","2025-04-14 10:00","2025-04-16 14:00","연속"]
[310,"경남","진주","하동T/P CB 7200","하동T/P  7200 GIS 컨트롤 블록 교체","하동T/P  7200 GIS 컨트롤 블록 교체 [병행] 7200 GIS 보통점검","2025-04-09 14:00","2025-04-11 18:00","2025-04-09 14:00","2025-04-11 18:00","연속"]
[311,"경남","진주","하동T/P CB 7272","하동T/P  7272 GIS 컨트롤 블록 교체","하동T/P  7272 GIS 컨트롤 블록 교체 [병행] 7272 CB 조작시험","2025-04-07 09:00","2025-04-09 14:00","2025-04-07 09:00","2025-04-09 14:00","연속"]
[312,"경남","진주","하동T/P CB 7400","하동T/P  7400 GIS 컨트롤 블록 교체","하동T/P  7400 GIS 컨트롤 블록 교체 [병행] 7400 CB 조작시험","2025-04-21 10:00","2025-04-23 18:00","2025-04-07 09:00","2025-04-09 14:00","연속"]
[313,"경남","통영","신고성고성하이TP#2 T/L","고성하이S/Y 신고성-고성하이발전 #2T/L GIS 보통점검","고성하이S/Y 신고성-고성하이발전 #2T/L GIS 보통점검","2025-04-10 09:30","2025-04-10 18:00","2025-04-10 09:30","2025-04-10 18:00","연속"]
[314,"경남","통영","신고성S/S CB 7371","신고성S/S  3호기 7371 GIS 보통점검","신고성S/S  3호기 7371 GIS 보통점검","2025-04-15 09:30","2025-04-15 18:00","2025-04-15 09:30","2025-04-15 18:00","연속"]
[315,"경남","통영","신고성S/S CB 7300","신고성S/S  3호기 7300 GIS 보통점검","신고성S/S  3호기 7300 GIS 보통점검","2025-04-14 09:30","2025-04-14 18:00","2025-04-14 09:30","2025-04-14 18:00","연속"]
[316,"경남","통영","신고성S/S #2 M.Tr","신고성S/S #2M.Tr 3차측 현대화 공사","신고성S/S #2M.Tr 3차측 현대화 공사 1. #2M.Tr 3차 측 옥외철구 철거 2. #2M.Tr 3차 측 SIS 설치","2025-04-21 10:00","2025-05-16 18:00","취소","취소","연속"]
[317,"경남","함안","신옥천북경남 T/L"," 신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 신옥천-북경남T/L 수평 추락방지장치 설치공사 - No.114~229","2025-04-10 07:00","2025-04-28 18:00","취소","취소","연속"]
[318,"경남","함안","신마산신김해#2 T/L"," 신마산-신김해#2T/L 철탑추락방지장치 설치공사"," 신마산-신김해#2T/L 75호(1기) 수평형(레일) 추락방지장치 설치","2025-04-12 13:00","2025-04-12 18:00","2025-04-12 13:00","2025-04-12 18:00","연속"]
[319,"경남","함안","신마산신김해#1 T/L"," 신마산-신김해#1T/L 철탑추락방지장치 설치공사"," 신마산-신김해#1T/L 75호(1기) 수평형(레일) 추락방지장치 설치","2025-04-12 07:00","2025-04-12 13:00","2025-04-12 07:00","2025-04-12 13:00","연속"]

{"sheet":"154설비","index":2,"n_rows":890,"n_cols":12,"rows_kept":890,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","군자성수 T/L","화양, 상봉S/S  GIS 설치공사"," 화양성수#2T/L 증설 - 군자성수T/L의 보호반 이설(군자 → 화양) - 화양성수#2T/L 보호반으로 활용","2025-04-21 09:00","2025-04-25 18:00","2025-04-21 09:00","2025-04-25 18:00","연속"]
[2,"서울","성동","광장뚝도#1 T/L","뚝도변전소 인출 OF케이블 선종교체공사","OF케이블 선종교체(→XLPE) : 뚝도EBG ∼ J/B#13(7) - 대상선로 : 광장뚝도#1, 광장뚝도#2, 성수뚝도#1T/L (3C×0.085㎞)","2025-04-01 09:00","2025-05-14 18:00","2025-04-01 09:00","2025-05-14 18:00","연속"]
[3,"서울","성동","장암방학#1 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 보통점검","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[4,"서울","성동","장암방학#2 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 보통점검","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[5,"서울","성동","금오상계#1 T/L","'25~'26년 서울본부 성동전력지사 지중송전 협력회사 공사","기중종단접속함(EBA) 절연유 채취","2025-04-21 07:00","2025-04-23 18:00","2025-04-21 07:00","2025-04-23 18:00","연속"]
[6,"서울","성동","금오상계#2 T/L","'25~'26년 서울본부 성동전력지사 지중송전 협력회사 공사","기중종단접속함(EBA) 절연유 채취","2025-04-21 07:00","2025-04-23 18:00","2025-04-21 07:00","2025-04-23 18:00","연속"]
[7,"서울","성동","상봉S/S #2 BUS","상봉S/S  구리상봉T/L SW 증설공사","구리상봉T/L 증설용 GIS 설치 × 1BAY(, 50kA, 2,000A)","2025-04-01 09:00","2025-05-12 18:00","취소","취소","연속"]
[8,"서울","성동","상봉휘경#1 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 보통점검","2025-04-29 09:00","2025-04-29 18:00","2025-04-29 09:00","2025-04-29 18:00","연속"]
[9,"서울","성동","상봉휘경#2 T/L","상봉S/S  구리상봉T/L SW 증설공사","구리상봉T/L 증설용 GIS 설치 × 1BAY 시험가압선로","2025-04-30 13:00","2025-05-01 13:00","취소","취소","연속"]
[10,"서울","성동","상봉휘경#2 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 보통점검","2025-04-30 09:00","2025-04-30 18:00","2025-04-30 09:00","2025-04-30 18:00","연속"]
[11,"서울","성동","신내상봉 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 보통점검","2025-04-25 09:00","2025-04-25 18:00","2025-04-25 09:00","2025-04-25 18:00","연속"]
[12,"서울","성동","화양상봉#1 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-21 10:30","2025-04-21 10:40","2025-04-28T10:30:00","2025-04-28T10:40:00","연속"]
[13,"서울","성동","군자화양#2 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 신규 GIS 설치 후 무부하가압 선로","2025-04-30 15:00","2025-05-02 18:00","2025-05-14 14:00","2025-05-15 14:00","연속"]
[14,"서울","성동","화양성수 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-21 10:10","2025-04-21 10:20","2025-04-28T10:10:00","2025-04-28T10:20:00","연속"]
[15,"서울","성동","화양광장 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-21 10:00","2025-04-21 10:10","2025-04-28T10:00:00","2025-04-28T10:10:00","연속"]
[16,"서울","성동","중랑하수#2 T/L CB","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-21 09:50","2025-04-21 10:00","2025-04-28T09:50:00","2025-04-28T10:00:00","연속"]
[17,"서울","성동","화양S/S #2 BUS","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 측 휴전 및 신규 GIS 설치(2DS, 상부 GIS, 챔버)","2025-04-21 09:00","2025-05-02 15:00","2025-04-28 09:00","2025-05-15 15:00","연속"]
[18,"서울","성동","군자화양#2 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 측 휴전 및 고깔 설치 후 무부하가압 시험선로","2025-04-21 09:00","2025-04-21 09:10","2025-04-28T09:00:00","2025-04-28T09:10:00","연속"]
[19,"서울","성동","군자화양#2 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #1BUS 측 신규 GIS 설치 후 무부하가압 시험선로","2025-04-17 15:00","2025-04-18 18:00","2025-04-26 10:00","2025-04-28 18:00","연속"]
[20,"서울","성동","화양S/S #1 BUS"," SW(화양-성수#2T/L) 증설공사"," GIS 2CCT 교체  GIS 1CCT 설치","2025-04-09 15:00","2025-04-09 18:00","2025-04-09 15:00","2025-04-09 18:00","연속"]
[21,"서울","성동","군자화양#2 T/L"," SW(화양-성수#2T/L) 증설공사"," GIS 2CCT 교체  GIS 1CCT 설치","2025-04-08 15:00","2025-04-09 18:00","2025-04-08 15:00","2025-04-09 18:00","연속"]
[22,"서울","성동","화양상봉#2 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #1BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-02 16:30","2025-04-02 16:40","2025-04-16T16:30:00","2025-04-16T16:40:00","연속"]
[23,"서울","성동","화양상봉#1 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #1BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-02 16:20","2025-04-02 16:30","2025-04-16T16:20:00","2025-04-16T16:30:00","연속"]
[24,"서울","성동","미금화양 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #1BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-02 16:10","2025-04-02 16:20","2025-04-16T16:10:00","2025-04-16T16:20:00","연속"]
[25,"서울","성동","화양성수 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #1BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-02 16:00","2025-04-02 16:10","2025-04-16T16:00:00","2025-04-16T16:10:00","연속"]
[26,"서울","성동","화양광장 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #1BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-02 15:50","2025-04-02 16:00","2025-04-16 15:50","2025-04-16 16:00","연속"]
[27,"서울","성동","중랑하수#2 T/L CB","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #1BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-02 15:40","2025-04-02 15:50","2025-04-16 15:40","2025-04-16 15:50","연속"]
[28,"서울","성동","화양S/S #1 BUS","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #1BUS 측 휴전 및 기설 GIS 철거, 신규 GIS 설치","2025-04-02 15:00","2025-04-18 18:00","2025-04-16 15:00","2025-04-28 18:00","연속"]
[29,"서울","성동","군자화양#2 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 측 휴전 및 고깔 설치 후 무부하가압 시험선로","2025-04-02 09:00","2025-04-02 15:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[30,"서울","성동","화양상봉#1 T/L","화양, 상봉S/S  T/L GIS 설치공사"," 화양성수#2T/L 증설 및 기설 GIS 교체(2BAY) - #2BUS측 신규 GIS 설치 후 무부하가압 시험가압선로","2025-04-30 09:00","2025-05-02 18:00","2025-04-30 09:00","2025-05-02 18:00","연속"]
[31,"서울","성동","화양상봉#1 T/L","화양, 상봉S/S  T/L GIS 설치공사"," 화양성수#2T/L 증설 및 기설 GIS 교체(2BAY) - #1BUS측 신규 GIS 설치 후 무부하가압 시험가압선로","2025-04-17 09:00","2025-04-18 18:00","취소","취소","연속"]
[32,"서울","성동","화양상봉#1 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L GIS 증설(1BAY) 및 기설 GIS 교체(2BAY) - #2BUS측 고깔설치후 무부하가압 시험가압선로","2025-04-02 09:00","2025-04-02 18:00","취소","취소","연속"]
[33,"서울","성동","화양상봉#2 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-21 10:40","2025-04-21 10:50","2025-04-28T10:40:00","2025-04-28T10:50:00","연속"]
[34,"서울","성동","미금화양 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 휴전 및 설비 모선절체를 위한 휴전","2025-04-21 10:20","2025-04-21 10:30","2025-04-28T10:20:00","2025-04-28T10:30:00","연속"]
[35,"서울","중부","순화동빙고 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","GIS 점검","2025-04-28 10:00","2025-04-30 18:00","2025-04-29 09:00","2025-04-29 18:00","연속"]
[36,"서울","중부","동빙고반포#1 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","GIS 점검","2025-04-28 10:00","2025-04-30 18:00","2025-04-28 10:00","2025-04-30 18:00","연속"]
[37,"서울","중부","동빙고S/S #2 BUS","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-04-30 10:00","2025-04-30 18:00","2025-04-30 10:00","2025-04-30 18:00","연속"]
[38,"서울","중부","동빙고반포#2 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","GIS 점검","2025-04-14 10:00","2025-04-16 18:00","2025-04-14 10:00","2025-04-16 18:00","연속"]
[39,"서울","중부","상암S/S CB 6100"," 상암S/S #4M.Tr용 GIS 설치공사(전문)","○ 170kV GIS 1CCT 설치 ○ 23kV EGIS 1CCT 설치","2025-04-23 09:00","2025-04-24 18:00","2025-04-23 09:00","2025-04-24 18:00","연속"]
[40,"서울","중부","능곡상암#1 T/L"," 상암S/S #4M.Tr용 GIS 설치공사(전문)","○ 170kV GIS 1CCT 설치 ○ 23kV EGIS 1CCT 설치","2025-04-23 15:00","2025-04-24 15:00","2025-04-23 15:00","2025-04-24 15:00","연속"]
[41,"서울","중부","수색상암 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","GIS 점검","2025-04-28 10:00","2025-04-29 18:00","2025-04-28 10:00","2025-04-29 18:00","연속"]
[42,"서울","중부","능곡상암#1 T/L"," 상암S/S #4M.Tr용 GIS 설치공사(전문)","○ 170kV GIS 1CCT 설치 ○ 23kV EGIS 1CCT 설치","2025-04-10 15:00","2025-04-11 15:00","2025-04-10 15:00","2025-04-11 15:00","연속"]
[43,"서울","중부","상암S/S 상암난방#2 T/L CB"," 상암S/S #4M.Tr용 GIS 설치공사(전문)","○ 170kV GIS 1CCT 설치 ○ 23kV EGIS 1CCT 설치","2025-04-01 09:00","2025-04-02 18:00","2025-04-01 09:00","2025-04-02 18:00","연속"]
[44,"서울","중부","상암S/S #2 BUS"," 상암S/S #4M.Tr용 GIS 설치공사(전문)","○ 170kV GIS 1CCT 설치 ○ 23kV EGIS 1CCT 설치","2025-04-03 15:00","2025-04-11 18:00","2025-04-03 15:00","2025-04-11 18:00","연속"]
[45,"서울","중부","능곡상암#1 T/L"," 상암S/S #4M.Tr용 GIS 설치공사(전문)","○ 170kV GIS 1CCT 설치 ○ 23kV EGIS 1CCT 설치","2025-04-03 15:00","2025-04-04 15:00","2025-04-03 15:00","2025-04-04 15:00","연속"]
[46,"서울","중부","상암S/S 상암난방#2 T/L CB"," 상암S/S #4M.Tr용 GIS 설치공사(전문)","○ 170kV GIS 1CCT 설치 ○ 23kV EGIS 1CCT 설치","2025-04-03 09:00","2025-04-04 18:00","2025-04-03 09:00","2025-04-04 18:00","연속"]
[47,"서울","중부","상암S/S #1 BUS"," 상암S/S #4M.Tr용 GIS 설치공사(전문)","○ 170kV GIS 1CCT 설치 ○ 23kV EGIS 1CCT 설치","2025-04-01 09:00","2025-04-03 15:00","2025-04-01 09:00","2025-04-03 15:00","연속"]
[48,"서울","중부","상암S/S CB 6100"," 상암S/S #4M.Tr용 GIS 설치공사(전문)","○ 170kV GIS 1CCT 설치 ○ 23kV EGIS 1CCT 설치","2025-04-01 09:00","2025-04-11 18:00","2025-04-01 09:00","2025-04-11 18:00","연속"]
[49,"서울","중부","은평녹번#2 T/L","은평S/S 설비개선 관련 제어케이블 철거 작업","은평S/S 설비개선 관련 제어케이블 철거 작업 ㅇ I/O BOX - LID 제어케이블 철거(I/O BOX 철거 관련) ㅇ 제어 및 보호 IED CID 변경 ㅇLID - IED 인터록 시험 및 연동시험 등","2025-04-01 14:00","2025-04-01 18:00","2025-04-01 14:00","2025-04-01 18:00","연속"]
[50,"서울","중부","양주은평#1 T/L","은평S/S 설비개선 관련 제어케이블 철거 작업","은평S/S 설비개선 관련 제어케이블 철거 작업 ㅇ I/O BOX - LID 제어케이블 철거(I/O BOX 철거 관련) ㅇ 제어 및 보호 IED CID 변경 ㅇLID - IED 인터록 시험 및 연동시험 등","2025-04-02 09:00","2025-04-02 11:00","2025-04-02 09:00","2025-04-02 11:00","연속"]
[51,"서울","중부","중부용산#1 T/L","2025년 중부S/S  장기사용 GIS 교체공사(1차)","-  GIS 교체(중부당인리#1, 중부당인리#2, 중부용산#1T/L) - 기타 부대공사","2025-04-02 09:00","2025-05-13 18:00","2025-04-02 09:00","2025-05-13 18:00","연속"]
[52,"서울","중부","중부당인리#2 T/L","2025년 중부S/S  장기사용 GIS 교체공사(1차)","-  GIS 교체(중부당인리#1, 중부당인리#2, 중부용산#1T/L) - 기타 부대공사","2025-04-02 09:00","2025-05-13 18:00","2025-04-02 09:00","2025-05-13 18:00","연속"]
[53,"서울","중부","중부S/S #65 BUS","2025년 중부S/S  장기사용 GIS 교체공사(1차)","-  GIS 교체(중부당인리#1, 중부당인리#2, 중부용산#1T/L) - 기타 부대공사","2025-04-02 09:00","2025-04-07 09:00","2025-04-02 09:00","2025-04-07 09:00","연속"]
[54,"서울","중부","중부당인리#1 T/L","2025년 중부S/S  장기사용 GIS 교체공사(1차)","-  GIS 교체(중부당인리#1, 중부당인리#2, 중부용산#1T/L) - 기타 부대공사","2025-04-02 09:00","2025-05-13 18:00","2025-04-02 09:00","2025-05-13 18:00","연속"]
[55,"서울","중부","중부S/S #60 BUS","2025년 중부S/S  장기사용 GIS 교체공사(1차)","-  GIS 교체(중부당인리#1, 중부당인리#2, 중부용산#1T/L) - 기타 부대공사","2025-04-07 09:00","2025-04-21 09:00","2025-04-07 09:00","2025-04-21 09:00","연속"]
[56,"서울","중부","중부S/S #65 BUS","2025년 중부S/S  장기사용 GIS 교체공사(1차)","-  GIS 교체(중부당인리#1, 중부당인리#2, 중부용산#1T/L) - 기타 부대공사","2025-04-21 09:00","2025-05-13 18:00","2025-04-21 09:00","2025-05-13 18:00","연속"]
[57,"서울","중부","현저서대문#1 T/L","2025년 중부전력지사 변전협력회사 공사","GIS 점검","2025-04-17 10:00","2025-04-17 18:00","2025-04-17 10:00","2025-04-17 18:00","연속"]
[58,"서울","중부","현저서대문#2 T/L","2025년 중부전력지사 변전협력회사 공사","GIS 점검","2025-04-18 10:00","2025-04-18 18:00","2025-04-18 10:00","2025-04-18 18:00","연속"]
[59,"서울","중부","지축현저#1 T/L","2025년 중부전력지사 변전협력회사 공사","GIS 점검","2025-04-21 10:00","2025-04-21 18:00","2025-04-21 10:00","2025-04-21 18:00","연속"]
[60,"서울","중부","지축현저#2 T/L","2025년 중부전력지사 변전협력회사 공사","GIS 점검","2025-04-22 10:00","2025-04-22 18:00","2025-04-22 10:00","2025-04-22 18:00","연속"]
[61,"서울","직할","창동돈암 T/L","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사","2025-04-28 09:00","2025-04-30 18:00","2025-04-28 09:00","2025-04-30 18:00","연속"]
[62,"서울","직할","마장용두 T/L","25년 직할 변전정비협력회사 총액공사","GIS 조작시험","2025-04-28 10:00","2025-04-28 17:00","2025-04-28 10:00","2025-04-28 17:00","연속"]
[63,"서울","직할","서소문S/S #2 BUS","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-04-21 09:00","2025-05-02 18:00","2025-04-21 09:00","2025-05-02 18:00","연속"]
[64,"서울","직할","서소문S/S #2 BUS","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-04-09 09:00","2025-04-10 18:00","2025-04-09 09:00","2025-04-10 18:00","연속"]
[65,"서울","직할","중앙서소문 T/L","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-04-10 16:00","2025-04-10 18:00","2025-04-10 16:00","2025-04-10 18:00","연속"]
[66,"서울","직할","서소문S/S #1 BUS","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-04-14 09:00","2025-04-18 18:00","2025-04-14 09:00","2025-04-18 18:00","연속"]
[67,"서울","직할","중앙서소문 T/L","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-04-17 18:00","2025-04-18 18:00","2025-04-17 18:00","2025-04-18 18:00","연속"]
[68,"서울","직할","서대문세종로 T/L","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사","2025-04-07 09:00","2025-04-09 18:00","2025-04-07 09:00","2025-04-09 18:00","연속"]
[69,"서울","직할","돈암안암#2 T/L","25년 직할 변전정비협력회사 총액공사","GIS 보통점검","2025-04-24 10:00","2025-04-24 17:00","2025-04-24 10:00","2025-04-24 17:00","연속"]
[70,"서울","직할","용두안암#1 T/L","25년 직할 변전정비협력회사 총액공사","GIS 조작시험","2025-04-25 10:00","2025-04-25 17:00","2025-04-25 10:00","2025-04-25 17:00","연속"]
[71,"서울","직할","돈암안암#1 T/L","25년 직할 변전정비협력회사 총액공사","GIS 보통점검","2025-04-23 10:00","2025-04-23 17:00","2025-04-23 10:00","2025-04-23 17:00","연속"]
[72,"서울","직할","용두안암#1 T/L","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사","2025-04-15 09:00","2025-04-17 18:00","2025-04-15 09:00","2025-04-17 18:00","연속"]
[73,"서울","직할","용두S/S #2 BUS","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 2DS 점검 및 시험가압","2025-04-19 14:00","2025-04-20 18:00","2025-04-19 14:00","2025-04-20 18:00","연속"]
[74,"서울","직할","용두안암#2 T/L","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사","2025-04-18 09:00","2025-04-20 18:00","2025-04-18 09:00","2025-04-20 18:00","연속"]
[75,"서울","직할","용두S/S #1 BUS","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 1DS 점검 및 시험가압","2025-04-18 09:00","2025-04-19 14:00","2025-04-18 09:00","2025-04-19 14:00","연속"]
[76,"서울","직할","용두S/S #2 BUS","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 2DS 점검 및 시험가압","2025-04-16 14:00","2025-04-17 18:00","2025-04-16 14:00","2025-04-17 18:00","연속"]
[77,"서울","직할","용두S/S #1 BUS","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 1DS 점검 및 시험가압","2025-04-15 09:00","2025-04-16 14:00","2025-04-15 09:00","2025-04-16 14:00","연속"]
[78,"서울","직할","원남S/S CB 6100","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사","2025-04-22 09:00","2025-04-24 18:00","2025-04-22 09:00","2025-04-24 18:00","연속"]
[79,"서울","직할","원남미아#1 T/L","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 시험가압선로","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","연속"]
[80,"서울","직할","원남S/S #1 BUS","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 시험가압모선","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","연속"]
[81,"서울","직할","운니원남#1 T/L","2025년 서울직할  GIS 정밀점검공사","2025년 서울직할  GIS 정밀점검공사 시험가압선로","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","연속"]
[82,"남서울","강남","신양재과천#1 T/L","2025년도 강남전력지사 변전 총액공사","GIS 보통점검","2025-04-02 09:00","2025-04-02 18:00","2025-04-02 09:00","2025-04-02 18:00","연속"]
[83,"남서울","강남","논일S/S #1 BUS","논일S/S  #4M.Tr용 GIS 설치공사"," GIS 1대 설치","2025-04-16 14:00","2025-04-19 18:00","2025-04-16 14:00","2025-04-19 18:00","연속"]
[84,"남서울","강남","논현논일#1 T/L","논일S/S  #4M.Tr용 GIS 설치공사","#2BUS 무부하가압","2025-04-15 14:00","2025-04-16 14:00","2025-04-15 14:00","2025-04-16 14:00","연속"]
[85,"남서울","강남","논현논일#1 T/L","논일S/S  #4M.Tr용 GIS 설치공사","#1BUS 무부하가압","2025-04-18 16:00","2025-04-19 18:00","2025-04-18 16:00","2025-04-19 18:00","연속"]
[86,"남서울","강남","논일S/S #2 BUS","논일S/S  #4M.Tr용 GIS 설치공사"," GIS 1대 설치 시험","2025-04-24 09:00","2025-04-25 18:00","2025-04-24 09:00","2025-04-25 18:00","연속"]
[87,"남서울","강남","논일S/S #2 BUS","논일S/S  #4M.Tr용 GIS 설치공사"," GIS 1대 설치","2025-04-14 09:00","2025-04-16 14:00","2025-04-14 09:00","2025-04-16 14:00","연속"]
[88,"남서울","강남","사당봉천#1 T/L","24-25년도 강남전력지사 변전협력 총액공사","GIS 조작시험, 전자변 교체","2025-04-04 09:00","2025-04-04 18:00","2025-04-04 09:00","2025-04-04 18:00","연속"]
[89,"남서울","강남","사당봉천#2 T/L","24-25년도 강남전력지사 변전협력 총액공사","GIS 조작시험","2025-04-03 09:00","2025-04-03 18:00","2025-04-03 09:00","2025-04-03 18:00","연속"]
[90,"남서울","강남","사당신림 T/L","24-25년도 강남전력지사 변전협력 총액공사","GIS 조작시험","2025-04-06 09:00","2025-04-06 14:00","2025-04-06 09:00","2025-04-06 14:00","연속"]
[91,"남서울","강남","신사반포#1 T/L","2025년도 강남전력지사 변전 총액공사","GIS 조작시험, 전자변 교체","2025-04-01 09:00","2025-04-01 14:00","2025-04-01 09:00","2025-04-01 14:00","연속"]
[92,"남서울","강남","신사반포#2 T/L","2025년도 강남전력지사 변전 총액공사","GIS 조작시험, 전자변 교체","2025-04-01 14:00","2025-04-01 18:00","2025-04-01 14:00","2025-04-01 18:00","연속"]
[93,"남서울","강남","신양재역삼#3 T/L","24-25년도 강남전력지사 변전협력 총액공사","GIS 보통점검, 전자변 교체","2025-04-03 09:00","2025-04-03 18:00","2025-04-03 09:00","2025-04-03 18:00","연속"]
[94,"남서울","동서울","가락수서#1 T/L","가락S/S 가락-수서 #1T/L 보통점검","(병행)수서S/S 가락-수서#1 조작시험","2025-04-28 09:00","2025-04-28 18:00","2025-04-28 09:00","2025-04-28 18:00","연속"]
[95,"남서울","동서울","가락수서#2 T/L","가락S/S 가락-수서 #1T/L 보통점검","(병행) 수서S/S 가락-수서#1 조작시험","2025-04-29 09:00","2025-04-29 18:00","2025-04-29 09:00","2025-04-29 18:00","연속"]
[96,"남서울","동서울","동서울신장#1 T/L","세종-포천 고속도로 건설 지장송전선로 지중화공사","신장C/T내 친환경펜스 설치","2025-04-01 07:30","2025-04-15 17:30","2025-04-01 07:30","2025-04-15 17:30","매일"]
[97,"남서울","동서울","동서울신장#2 T/L","세종-포천 고속도로 건설 지장송전선로 지중화공사","신장C/T내 친환경펜스 설치","2025-04-16 07:30","2025-04-30 17:30","2025-04-16 07:30","2025-04-30 17:30","매일"]
[98,"남서울","동서울","동서울서종#1 T/L","'25년 가공송전 순시점검 위탁공사","지장이설 송전선로 구간(No.93C/T~No.92) 초기점검 시행","2025-04-21 09:00","2025-04-21 18:00","2025-04-21 09:00","2025-04-21 18:00","연속"]
[99,"남서울","동서울","동서울서종#2 T/L","'25년 가공송전 순시점검 위탁공사","지장이설 송전선로 구간(No.93C/T~No.92) 초기점검 시행","2025-04-22 09:00","2025-04-22 18:00","2025-04-22 09:00","2025-04-22 18:00","연속"]
[100,"남서울","동서울","동서울송파#1 T/L","송파S/S 동서울-송파 #1T/L GIS 조작시험","송파S/S 동서울-송파 #1T/L GIS 조작시험","2025-04-09 09:00","2025-04-09 14:00","2025-04-09 09:00","2025-04-09 14:00","연속"]
[101,"남서울","동서울","동서울송파#2 T/L","송파S/S 동서울-송파#2T/L GIS 조작시험","송파S/S 동서울-송파#2T/L GIS 조작시험","2025-04-09 14:00","2025-04-09 18:00","2025-04-09 14:00","2025-04-09 18:00","연속"]
[102,"남서울","동서울","산성수서#1 T/L"," 산성-수서T/L 지중화공사(2단계)"," 산성-수서#1T/L 지중화(2단계) - 발주처 : LH - 지중화공사에 따른 케이블 철거 및 포설, 접속","2025-04-01 09:00","2025-05-31 18:00","2025-04-01 09:00","2025-05-31 18:00","연속"]
[103,"남서울","동서울","신장강일#2 T/L","신장S/S 신장-강일#2T/L 하자점검","신장S/S 신장-강일#2T/L 하자점검 (병행) 강일S/S 신장-강일#2 초기점검","2025-04-03 09:00","2025-04-03 18:00","취소","취소","연속"]
[104,"남서울","동서울","신장강일#1 T/L","신장S/S 신장-강일#1T/L 하자점검","신장S/S 신장-강일#1T/L 하자점검 (병행) 강일S/S 신장-강일#1 초기점검","2025-04-02 09:00","2025-04-02 18:00","취소","취소","연속"]
[105,"남서울","영등포","구공S/S CB 6200","2024~25년 영등포전력지사 변전협력회사 공사","구공S/S #61-#66 모선보호반 교체공사","2025-04-01 09:00","2025-04-04 18:00","2025-04-01 09:00","2025-04-04 18:00","연속"]
[106,"남서울","영등포","구공S/S SEC CB 65660","2024~25년 영등포전력지사 변전협력회사 공사","구공S/S #61-#66 모선보호반 교체공사","2025-04-01 09:00","2025-04-04 18:00","2025-04-01 09:00","2025-04-04 18:00","연속"]
[107,"남서울","영등포","구공S/S SEC CB 66670","2024~25년 영등포전력지사 변전협력회사 공사","구공S/S #61-#66 모선보호반 교체공사","2025-04-01 09:00","2025-04-04 18:00","2025-04-01 09:00","2025-04-04 18:00","연속"]
[108,"남서울","영등포","구공S/S SEC CB 61620","2024~25년 영등포전력지사 변전협력회사 공사","구공S/S #61-#66 모선보호반 교체공사","2025-04-01 09:00","2025-04-04 18:00","2025-04-01 09:00","2025-04-04 18:00","연속"]
[109,"남서울","영등포","구공S/S SEC CB 60610","2024~25년 영등포전력지사 변전협력회사 공사","구공S/S #61-#66 모선보호반 교체공사","2025-04-01 09:00","2025-04-04 18:00","2025-04-01 09:00","2025-04-04 18:00","연속"]
[110,"남서울","영등포","독산대방#2 T/L","2025년 영등포전력지사 변전협력회사 총액공사","독산S/S 독산-대방#2T/L 보통점검","2025-04-12 14:00","2025-04-12 18:00","취소","취소","연속"]
[111,"남서울","영등포","독산대방#1 T/L","2025년 영등포전력지사 변전협력회사 총액공사","독산S/S 독산-대방#1T/L 보통점검","2025-04-12 09:00","2025-04-12 14:00","취소","취소","연속"]
[112,"남서울","영등포","대림독산 T/L","2025년 영등포전력지사 변전협력회사 총액공사","독산S/S 대림-독산T/L 보통점검","2025-04-07 09:00","2025-04-07 18:00","2025-04-07 09:00","2025-04-07 18:00","연속"]
[113,"남서울","영등포","상암등촌#1 T/L","2025년 영등포전력지사 변전협력회사 총액공사","등촌S/S 상암-등촌#1T/L 보통점검","2025-04-05 09:00","2025-04-05 18:00","2025-04-05 09:00","2025-04-05 18:00","연속"]
[114,"남서울","영등포","마곡가양#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","24년도 영등포전력지사  GIS 정밀점검공사 대상 :  마곡-가양#1T/L","2025-04-08 09:00","2025-04-09 18:00","취소","취소","연속"]
[115,"남서울","영등포","마곡가양#2 T/L","25년도 영등포전력지사  GIS 정밀점검공사","24년도 영등포전력지사  GIS 정밀점검공사 대상 :  마곡-가양#2T/L","2025-04-10 09:00","2025-04-11 18:00","취소","취소","연속"]
[116,"남서울","영등포","화곡마곡#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","24년도 영등포전력지사  GIS 정밀점검공사 대상 :  화곡-마곡#1T/L","2025-04-12 09:00","2025-04-13 18:00","2025-04-12 09:00","2025-04-13 18:00","연속"]
[117,"남서울","영등포","마곡가양#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","24년도 영등포전력지사  GIS 정밀점검공사 내용 : #1M.Tr 1차 정밀점검 후 무부하 가압","2025-04-22 16:00","2025-04-22 18:00","취소","취소","연속"]
[118,"남서울","영등포","마곡가양#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","24년도 영등포전력지사  GIS 정밀점검공사 내용 : #2M.Tr 1차 정밀점검 후 무부하 가압","2025-04-24 16:00","2025-04-24 18:00","취소","취소","연속"]
[119,"남서울","영등포","화곡마곡#2 T/L","25년도 영등포전력지사  GIS 정밀점검공사","24년도 영등포전력지사  GIS 정밀점검공사 대상 :  화곡-마곡#1T/L","2025-04-26 09:00","2025-04-27 18:00","2025-04-26 09:00","2025-04-27 18:00","연속"]
[120,"남서울","영등포","마곡가양#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","24년도 영등포전력지사  GIS 정밀점검공사 내용 : BUSTIE 정밀점검 후 무부하 가압","2025-04-29 16:00","2025-04-29 18:00","취소","취소","연속"]
[121,"남서울","영등포","마곡S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","24년도 영등포전력지사  GIS 정밀점검공사 내용 : #1M.Tr 1차 정밀점검 후 무부하 가압","2025-04-22 16:00","2025-04-22 18:00","취소","취소","연속"]
[122,"남서울","영등포","마곡S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","24년도 영등포전력지사  GIS 정밀점검공사 내용 : BUS TIE 정밀점검 후 무부하 가압","2025-04-28 09:00","2025-04-29 18:00","취소","취소","연속"]
[123,"남서울","영등포","마곡S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","24년도 영등포전력지사  GIS 정밀점검공사 내용 : #2M.Tr 1차 정밀점검 후 무부하 가압","2025-04-24 16:00","2025-04-24 18:00","취소","취소","연속"]
[124,"남서울","영등포","신문래목동#2 T/L","24~25년 영등포전력지사 변전협력 총액공사","목동S/S 신문래-목동#2T/L 보통점검","2025-04-19 09:00","2025-04-19 18:00","취소","취소","연속"]
[125,"남서울","영등포","시흥독산#2 T/L","170kV GIS 조작시험(직영)","시흥S/S 시흥-독산#1, #2T/L 조작시험","2025-04-08 14:00","2025-04-08 18:00","2025-04-08 14:00","2025-04-08 18:00","연속"]
[126,"남서울","영등포","신광명시흥#1 T/L","170kV GIS 조작시험(직영)","시흥S/S 신광명-시흥#1, #2T/L 조작시험","2025-04-09 09:00","2025-04-09 14:00","2025-04-09 09:00","2025-04-09 14:00","연속"]
[127,"남서울","영등포","신광명시흥#2 T/L","170kV GIS 조작시험(직영)","시흥S/S 신광명-시흥#1, #2T/L 조작시험","2025-04-09 14:00","2025-04-09 18:00","2025-04-09 14:00","2025-04-09 18:00","연속"]
[128,"남서울","영등포","시흥독산#1 T/L","170kV GIS 조작시험(직영)","시흥S/S 시흥-독산#1, #2T/L 조작시험","2025-04-08 09:00","2025-04-08 14:00","2025-04-08 09:00","2025-04-08 14:00","연속"]
[129,"남서울","영등포","신광명소래 T/L","'25-'26년 영등포전력지사 지중송전 협력회사 공사"," 신광명-소래T/L 소래C/T EBA 가스채취","2025-04-06 09:00","2025-04-06 18:00","2025-04-06 09:00","2025-04-06 18:00","연속"]
[130,"남서울","영등포","신정목동#2 T/L","25년 영등포전력지사 170kV GIS 정밀점검","신정S/S 신정-목동#2T/L 정밀점검","2025-04-19 09:00","2025-04-20 18:00","취소","취소","연속"]
[131,"남서울","영등포","온수소래 T/L"," 온수-소래T/L 피뢰기설치 공사","1.피뢰기 설치 2. 금구류 교체 3. 조류퇴치기 설치 4. 보수형 클램프 설치","2025-04-05 09:00","2025-04-06 18:00","취소","취소","연속"]
[132,"남서울","직할","봉천신길#1 T/L","170kV GIS 보통점검","170kV GIS 보통점검 - 신길 측 170kV GIS 보통점검 병행","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[133,"남서울","직할","대방신길#2 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[134,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사","신문래S/S 신문래-목동#1T/L GIS 정밀점검 무부하 가압용","2025-04-22 09:00","2025-04-22 18:00","2025-04-22 09:00","2025-04-22 18:00","연속"]
[135,"남서울","직할","신문래목동#2 T/L","170kV GIS 정밀점검공사","신문래S/S 신문래-목동#2T/L GIS 정밀점검","2025-04-23 09:00","2025-04-25 18:00","2025-04-23 09:00","2025-04-25 18:00","연속"]
[136,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사","신문래S/S 신문래-목동#2T/L GIS 정밀점검 무부하 가압용","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","연속"]
[137,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사","신문래S/S 60-01SEC GIS 정밀점검 무부하 가압용","2025-04-29 09:00","2025-04-29 18:00","2025-04-29 09:00","2025-04-29 18:00","연속"]
[138,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사","신문래S/S 60-01SEC GIS 정밀점검 무부하 가압용","2025-04-30 09:00","2025-04-30 18:00","2025-04-30 09:00","2025-04-30 18:00","연속"]
[139,"남서울","직할","신문래목동#1 T/L","170kV GIS 정밀점검공사","신문래S/S 신문래-목동#1T/L GIS 정밀점검","2025-04-21 09:00","2025-04-23 18:00","2025-04-21 09:00","2025-04-23 18:00","연속"]
[140,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사","신문래S/S 신문래-구로#2T/L GIS 정밀점검 무부하 가압용","2025-04-17 09:00","2025-04-17 18:00","2025-04-17 09:00","2025-04-17 18:00","연속"]
[141,"남서울","직할","신문래구로#2 T/L","170kV GIS 정밀점검공사","신문래S/S 신문래-구로#2T/L GIS 정밀점검","2025-04-16 09:00","2025-04-18 18:00","2025-04-16 09:00","2025-04-18 18:00","연속"]
[142,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사","신문래S/S 신문래-구로#1T/L GIS 정밀점검 무부하 가압용","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","연속"]
[143,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사","신문래S/S #1M.Tr 2차 GIS 정밀점검 무부하 가압용","2025-04-02 09:00","2025-04-02 18:00","취소","취소","연속"]
[144,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사","신문래S/S #1M.Tr 2차 GIS 정밀점검 무부하 가압용","2025-04-03 09:00","2025-04-03 18:00","취소","취소","연속"]
[145,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사","신문래S/S #2M.Tr 2차 GIS 정밀점검 무부하 가압용","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[146,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사","신문래S/S #2M.Tr 2차 GIS 정밀점검 무부하 가압용","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[147,"남서울","직할","신문래구로#1 T/L","170kV GIS 정밀점검공사","신문래S/S 신문래-구로#1T/L GIS 정밀점검","2025-04-14 09:00","2025-04-16 18:00","2025-04-14 09:00","2025-04-16 18:00","연속"]
[148,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사","신문래S/S #3M.Tr 2차 GIS 정밀점검 무부하 가압용","2025-04-11 09:00","2025-04-11 18:00","2025-04-11 09:00","2025-04-11 18:00","연속"]
[149,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사","신문래S/S #3M.Tr 2차 GIS 정밀점검 무부하 가압용","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[150,"인천","김포","경서S/S #1 BUS","경서S/S  #1M.Tr 1차 GIS 무부하가압","경서S/S  #1M.Tr 1차 GIS 무부하가압 - #1BUS 휴전","2025-04-09 10:00","2025-04-09 18:00","취소","취소","연속"]
[151,"인천","김포","신경서경서#1 T/L","경서S/S  #2M.Tr 1차 GIS 정밀점검 무부하가압","경서S/S  #2M.Tr 1차 GIS 정밀점검 무부하가압","2025-04-11 10:00","2025-04-11 18:00","취소","취소","연속"]
[152,"인천","김포","신경서경서#1 T/L","경서S/S # 4M.Tr 1차 GIS 정밀점검 무부하가압","경서S/S # 4M.Tr 1차 GIS 정밀점검 무부하가압","2025-04-25 10:00","2025-04-25 18:00","취소","취소","연속"]
[153,"인천","김포","신경서경서#1 T/L","경서S/S # 3M.Tr 1차 GIS 정밀점검 무부하가압","경서S/S # 3M.Tr 1차 GIS 정밀점검 무부하가압","2025-04-23 10:00","2025-04-23 18:00","취소","취소","연속"]
[154,"인천","김포","신경서경서#1 T/L","경서S/S  #1M.Tr 1차 GIS 정밀점검 무부하가압","경서S/S  #1M.Tr 1차 GIS 정밀점검 무부하가압","2025-04-09 10:00","2025-04-09 18:00","취소","취소","연속"]
[155,"인천","김포","경서북인천#1 T/L","’25∼’26년 인천본부 김포전력지사 지중송전 협력회사 공사","25년 상반기 맨홀 및 접속함 점검","2025-04-07 09:00","2025-04-11 18:00","2025-04-07 09:00","2025-04-11 18:00","연속"]
[156,"인천","김포","경서북인천#2 T/L","’25∼’26년 인천본부 김포전력지사 지중송전 협력회사 공사","25년 상반기 맨홀 및 접속함 점검","2025-04-07 09:00","2025-04-11 18:00","2025-04-07 09:00","2025-04-11 18:00","연속"]
[157,"인천","김포","양곡S/S #65 BUS","양곡S/S  GIS 교체공사(2차)","- #1M.Tr 1차 GIS 교체","2025-04-23 14:00","2025-05-03 14:00","2025-04-23 14:00","2025-05-03 14:00","연속"]
[158,"인천","김포","양곡S/S CB 6100","양곡S/S  GIS 교체공사(2차)","- BUS-TIE 이용 무부하 가압 - #1M.Tr 1차 GIS 교체","2025-04-22 14:00","2025-04-23 14:00","2025-04-22 14:00","2025-04-23 14:00","연속"]
[159,"인천","김포","양곡S/S CB 6100","양곡S/S  GIS 교체공사(1차)","- BUS-TIE 이용 무부하 가압 - #3M.Tr 1차 GIS 교체 - (구)신김포양곡#2T/L GIS 철거","2025-04-11 14:00","2025-04-12 14:00","2025-04-11 14:00","2025-04-12 14:00","연속"]
[160,"인천","김포","양곡S/S #60 BUS","양곡S/S  GIS 교체공사(1차)","- #1BUS 상체크 및 계통시험 - #3M.Tr 1차 GIS 교체 - (구)신김포양곡#2T/L GIS 철거","2025-04-12 14:00","2025-04-12 18:00","2025-04-12 14:00","2025-04-12 18:00","연속"]
[161,"인천","김포","양곡S/S #1 M.Tr CB","양곡S/S  GIS 교체공사(2차)","- #1M.Tr 1차 GIS 교체","2025-04-13 09:00","2025-05-03 18:00","2025-04-13 09:00","2025-05-03 18:00","연속"]
[162,"인천","김포","양곡S/S #65 BUS","양곡S/S  GIS 교체공사(2차)","- #1M.Tr 1차 GIS 교체","2025-04-13 09:00","2025-04-14 15:00","2025-04-13 09:00","2025-04-14 15:00","연속"]
[163,"인천","김포","양곡S/S #60 BUS","양곡S/S  GIS 교체공사(2차)","- #1M.Tr 1차 GIS 교체","2025-04-14 15:00","2025-04-23 14:00","2025-04-14 15:00","2025-04-23 14:00","연속"]
[164,"인천","김포","양곡S/S CB 6100","양곡S/S  GIS 교체공사(2차)","- BUS-TIE 이용 무부하 가압 - #1M.Tr 1차 GIS 교체","2025-04-14 14:00","2025-04-14 15:00","2025-04-14 14:00","2025-04-14 15:00","연속"]
[165,"인천","김포","양촌양곡#1 T/L","24-25년 가공송전 협력회사 공사 (추락방지시설 설치)","수평 추락방지시설 설치, SB댐퍼 설치","2025-04-21 07:30","2025-04-25 17:00","취소","취소","연속"]
[166,"인천","김포","경서양촌#2 T/L","'24~'25년 부평, 김포전력지사 가공송전 협력회사 총액공사","고정형폴리머점퍼지지애자 설치","2025-04-02 07:00","2025-04-04 18:00","취소","취소","매일"]
[167,"인천","김포","신경서왕길#2 T/L","24-25년 가공송전 협력회사 공사","수평추락방지시설 설치 등","2025-04-16 07:00","2025-04-18 18:00","2025-04-16 07:00","2025-04-18 18:00","매일"]
[168,"인천","김포","신경서왕길#1 T/L","24-25년 가공송전 협력회사 공사","수평추락방지시설 설치 등","2025-04-09 07:00","2025-04-11 18:00","2025-04-09 07:00","2025-04-11 18:00","매일"]
[169,"인천","부평","신가좌부개#2 T/L","부개S/S  GIS 교체공사(1차)(무부하가압)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-04-18 14:00","2025-04-19 15:00","취소","취소","연속"]
[170,"인천","부평","부개S/S #2 BUS","부개S/S  GIS 교체공사(1차)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-04-19 14:00","2025-04-30 14:00","취소","취소","연속"]
[171,"인천","부평","부개S/S #1 BUS","부개S/S  GIS 교체공사(1차)(상체크)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-04-30 14:00","2025-04-30 18:00","취소","취소","연속"]
[172,"인천","부평","부개원미#1 T/L"," 부개-원미#1T/L 657 GIS 보통점검 및 전자변 누기보수"," 부개-원미#1T/L 657 GIS 보통점검 및 전자변 누기보수","2025-04-01 09:00","2025-04-01 18:00","취소","취소","연속"]
[173,"인천","부평","부개S/S CB 6100","부개S/S  GIS 교체공사(1차)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-04-01 09:00","2025-04-30 18:00","2025-04-14 09:00","2025-05-13 18:00","연속"]
[174,"인천","부평","부개S/S #1 M.Tr CB","부개S/S  GIS 교체공사(1차)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-04-01 09:00","2025-04-30 18:00","취소","취소","연속"]
[175,"인천","부평","부개S/S #2 BUS","부개S/S  GIS 교체공사(1차)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-04-01 09:00","2025-04-05 15:00","2025-04-14 09:00","2025-04-18 15:00","연속"]
[176,"인천","부평","부개원미#2 T/L"," 부개-원미#2T/L 667 GIS 보통점검"," 부개-원미#2T/L 667 GIS 보통점검","2025-04-02 09:00","2025-04-02 18:00","취소","취소","연속"]
[177,"인천","부평","신가좌부개#2 T/L","부개S/S  GIS 교체공사(1차)(무부하가압)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-04-04 15:00","2025-04-05 16:00","2025-04-18 14:00","2025-04-18 15:00","연속"]
[178,"인천","부평","부개S/S #1 BUS","부개S/S  GIS 교체공사(1차)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-04-05 15:00","2025-04-19 14:00","2025-04-18 15:00","2025-05-02 14:00","연속"]
[179,"인천","부평","신가좌부개#2 T/L","부개S/S  GIS 교체공사(1차)(무부하가압, 상체크)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-04-29 14:00","2025-04-30 18:00","취소","취소","연속"]
[180,"인천","부평","서인천C/C CB 6433"," #4 G.Tr 1차 6433 GIS 조작시험"," #4 G.Tr 1차 6433 GIS 조작시험","2025-04-07 09:00","2025-04-07 18:00","2025-04-07 09:00","2025-04-07 18:00","연속"]
[181,"인천","부평","서인천C/C CB 6133"," #1 G.Tr 1차 6133 GIS 보통점검"," #1 G.Tr 1차 6133 GIS 보통점검","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[182,"인천","부평","서인천CC신경서 T/L"," 서인천CC-신경서T/L GIS 보통점검"," 서인천CC-신경서T/L GIS 보통점검","2025-04-02 09:00","2025-04-02 18:00","2025-04-02 09:00","2025-04-02 18:00","연속"]
[183,"인천","부평","신현송현#1 T/L"," 신현-송현#1T/L 617 GIS 보통점검"," 신현-송현#1T/L 617 GIS 보통점검","2025-04-28 09:00","2025-04-28 18:00","2025-04-28 09:00","2025-04-28 18:00","연속"]
[184,"인천","부평","송현송월#2 T/L"," 송현-송월#2T/L 627 GIS 보통점검"," 송현-송월#2T/L 627 GIS 보통점검","2025-04-29 09:00","2025-04-29 18:00","2025-04-29 09:00","2025-04-29 18:00","연속"]
[185,"인천","부평","신가좌인천#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","연속"]
[186,"인천","부평","신가좌인천#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2025-04-14 09:00","2025-04-14 18:00","2025-04-14 09:00","2025-04-14 18:00","연속"]
[187,"인천","부평","신가좌신현#2 T/L","신가좌S/S  신가좌-신현#2T/L GIS 조작시험","신가좌S/S  신가좌-신현#2T/L GIS 조작시험","2025-04-13 12:00","2025-04-13 10:08","취소","취소","연속"]
[188,"인천","부평","신가좌신현#1 T/L","신가좌S/S  신가좌-신현#1T/L GIS 조작시험","신가좌S/S  신가좌-신현#1T/L GIS 조작시험","2025-04-13 09:00","2025-04-13 12:00","취소","취소","연속"]
[189,"인천","부평","신가좌인천#3 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[190,"인천","부평","신경서경서#2 T/L"," 신경서-경서#2T/L 667 GIS 보통점검"," 신경서-경서#2T/L 667 GIS 보통점검","2025-04-04 09:00","2025-04-04 18:00","2025-04-04 09:00","2025-04-04 18:00","연속"]
[191,"인천","부평","신경서경서#3 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강 - 열경화공법 적용개소 구조 개선","2025-04-14 08:00","2025-04-20 18:00","2025-04-14 08:00","2025-04-20 18:00","연속"]
[192,"인천","부평","신경서S/S CB 6200"," 61-66 BUS 보호반 대체"," 61-66 BUS 보호반 대체","2025-04-21 09:00","2025-04-25 18:00","취소","취소","연속"]
[193,"인천","부평","신경서경서#1 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-04-21 08:00","2025-04-29 18:00","2025-04-21 08:00","2025-04-29 18:00","연속"]
[194,"인천","부평","신경서S/S SEC CB 65660"," 61-66 BUS 보호반 대체"," 61-66 BUS 보호반 대체","2025-04-21 09:00","2025-04-25 18:00","취소","취소","연속"]
[195,"인천","부평","신경서S/S SEC CB 60610"," 61-66 BUS 보호반 대체"," 61-66 BUS 보호반 대체","2025-04-21 09:00","2025-04-25 18:00","취소","취소","연속"]
[196,"인천","부평","영종S/S CB 6100"," #60-#65 BUS TIE 6100 GIS"," #60-#65 BUS TIE 6100 GIS","2025-04-24 09:00","2025-04-24 18:00","취소","취소","연속"]
[197,"인천","부평","영종S/S CB 6100"," #60-#65 BUS TIE GIS 보통점검"," #60-#65 BUS TIE GIS 보통점검","2025-04-09 09:00","2025-04-09 18:00","취소","취소","연속"]
[198,"인천","부평","신경서영종 T/L"," 신경서-영종T/L 647 GIS 보통점검"," 신경서-영종T/L 647 GIS 보통점검","2025-04-09 09:00","2025-04-09 18:00","취소","취소","연속"]
[199,"인천","부평","영종경서 T/L"," 영종-경서T/L GIS 보통점검"," 영종-경서T/L GIS 보통점검","2025-04-14 09:00","2025-04-14 18:00","취소","취소","연속"]
[200,"인천","부평","영종을왕 T/L"," 영종-을왕T/L GIS 687 GIS 보통점검"," 영종-을왕T/L GIS 687 GIS 보통점검","2025-04-18 09:00","2025-04-18 18:00","취소","취소","연속"]
[201,"인천","부평","북인천원창 T/L"," 북인천-원창T/L GIS 보통점검"," 북인천-원창T/L GIS 보통점검","2025-04-07 09:00","2025-04-07 18:00","취소","취소","연속"]
[202,"인천","부평","인천C/C CB 6100"," #60-#65 BUS TIE 6100 GIS 보통점검"," #60-#65 BUS TIE 6100 GIS 보통점검","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[203,"인천","부평","인천C/C SEC CB 65660","인천CC S/Y  #65-#66 SEC GIS 보통점검","인천CC S/Y  #65-#66 SEC GIS 보통점검","2025-04-18 09:00","2025-04-18 18:00","2025-04-18 09:00","2025-04-18 18:00","연속"]
[204,"인천","부평","인천C/C SEC CB 60610","인천CC S/Y  #60-#61 SEC GIS 보통점검","인천CC S/Y  #60-#61 SEC GIS 보통점검","2025-04-17 09:00","2025-04-17 18:00","2025-04-17 09:00","2025-04-17 18:00","연속"]
[205,"인천","부평","인천남인천#2 T/L","인천S/S  인천남인천#2 T/L GIS조작시험, 보통점검","인천S/S  인천남인천#2 T/L GIS조작시험","2025-04-19 09:00","2025-04-19 18:00","2025-04-19 09:00","2025-04-19 18:00","연속"]
[206,"인천","부평","인천남인천#1 T/L","인천S/S  인천남인천#1 T/L GIS조작시험, 보통점검","인천S/S  인천남인천#1 T/L GIS조작시험","2025-04-12 09:00","2025-04-12 18:00","2025-04-12 09:00","2025-04-12 18:00","연속"]
[207,"인천","부평","학익연수#2 T/L"," 남인천-학익 등 2개T/L 지장이설 및 선종교체공사","지장이설 및 선종교체[학익S/S~연수S/S(OF→XLPE 2,000, 2.7km)]","2025-04-18 09:00","2025-06-08 18:00","2025-04-18 09:00","2025-06-08 18:00","연속"]
[208,"인천","시흥","신시흥남동#2 T/L","인천남동 첨단산업단지  신시흥-남동T/L 지중화공사(가공)","1. 공사구간 :  신시흥-남동T/L No.35～신동C/T 2. 선로길이 : ACSR/AW 410㎟ × 2B × 2C, 0.364km 3. 지 지 물 : C/T 신설 1기, 임시철탑 2기, 철탑철거 2기","2025-04-12 08:00","2025-04-17 18:00","2025-04-12 08:00","2025-04-17 18:00","연속"]
[209,"인천","시흥","신시흥남동#1 T/L","인천남동 첨단산업단지  신시흥-남동T/L 지중화공사(가공)","1. 공사구간 :  신시흥-남동T/L No.35~신동C/T 2. 선로길이 : ACSR/AW 410㎟ × 2B × 2C, 0.364km 3. 지 지 물 : C/T 신설 1기, 임시철탑 2기, 철탑철거 2기","2025-04-07 08:00","2025-04-11 18:00","2025-04-07 08:00","2025-04-11 18:00","연속"]
[210,"인천","시흥","소래S/S CB 6100","소래S/S 60-65 모선보호반 대체공사","소래S/S 60-65 모선보호반 대체공사","2025-04-21 09:00","2025-04-25 18:00","2025-04-21 09:00","2025-04-25 18:00","연속"]
[211,"인천","시흥","신시흥북시화#1 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.1~25(25기) 및 소도체 이도 조정","2025-04-26 07:30","2025-04-27 18:00","2025-04-26 07:30","2025-04-27 18:00","매일"]
[212,"인천","시흥","신시흥시화#1 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.1~25(25기) 및 소도체 이도 조정","2025-04-26 07:30","2025-04-27 18:00","2025-04-26 07:30","2025-04-27 18:00","매일"]
[213,"인천","직할","갈산부흥#1 T/L","갈산,부흥S/S 갈산부흥#1T/L GIS 점검","갈산S/S GIS 보통점검, 부흥S/S GIS 조작시험","2025-04-09 09:30","2025-04-09 18:00","취소","취소","연속"]
[214,"인천","직할","갈산S/S CB 6100","갈산S/S 7500B/T, 6100B/T GIS 보통점검","갈산S/S 7500B/T, 6100B/T GIS 보통점검","2025-04-08 09:30","2025-04-08 18:00","취소","취소","연속"]
[215,"인천","직할","갈산부흥#2 T/L","갈산,부흥S/S 갈산부흥#2T/L GIS 점검","갈산S/S GIS 보통점검, 부흥S/S GIS 조작시험","2025-04-10 09:30","2025-04-10 18:00","취소","취소","연속"]
[216,"인천","직할","갈산도당#1 T/L","갈산S/S 갈산도당#1T/L GIS 보통점검","갈산S/S 갈산도당#1T/L GIS 보통점검","2025-04-11 09:30","2025-04-11 18:00","취소","취소","연속"]
[217,"인천","직할","임학계양#1 T/L","'24-'25년 가공송전 협력회사 공사","수평 추락방지시설 설치","2025-04-05 07:00","2025-04-06 18:00","취소","취소","매일"]
[218,"인천","직할","계양불로#2 T/L","계양S/S  계양-불로#2T/L GIS 정밀점검","계양S/S  계양-불로#2T/L GIS 정밀점검","2025-04-23 13:00","2025-04-25 18:00","취소","취소","연속"]
[219,"인천","직할","계양불로#1 T/L","계양S/S  계양-불로#1T/L GIS 정밀점검","계양S/S  계양-불로#1T/L GIS 정밀점검","2025-04-21 09:00","2025-04-23 13:00","취소","취소","연속"]
[220,"인천","직할","임학계양#2 T/L","'24-'25년 가공송전 협력회사 공사","수평 추락방지시설 설치","2025-04-12 07:00","2025-04-13 18:00","취소","취소","매일"]
[221,"인천","직할","고강화곡#3 T/L","고강S/S  고강-화곡#3T/L GIS 보통점검","고강S/S  고강-화곡#3T/L GIS 보통점검","2025-04-28 09:30","2025-04-28 18:00","2025-04-28 09:30","2025-04-28 18:00","연속"]
[222,"인천","직할","고강화곡#2 T/L","고강S/S  고강-화곡#2T/L GIS 보통점검","고강S/S  고강-화곡#2T/L GIS 보통점검","2025-04-25 09:30","2025-04-25 18:00","2025-04-25 09:30","2025-04-25 18:00","연속"]
[223,"인천","직할","고강화곡#1 T/L","고강S/S  고강-화곡#1T/L GIS 보통점검","고강S/S  고강-화곡#1T/L GIS 보통점검","2025-04-24 09:30","2025-04-24 18:00","2025-04-24 09:30","2025-04-24 18:00","연속"]
[224,"인천","직할","경서북인천#1 T/L","북인천S/S  경서-북인천#1T/L GIS 보통점검","북인천S/S  경서-북인천#1T/L GIS 보통점검","2025-04-03 09:30","2025-04-03 18:00","취소","취소","연속"]
[225,"인천","직할","북인천원창 T/L","무부하가압용(북인천S/S #4M.Tr 1차 GIS 정밀점검)","북인천S/S #4M.Tr 1차 GIS 정밀점검분 무부하가압용 - 무부하가압 시행 후 북인천-원창T/L GIS 조작시험 진행","2025-04-18 09:00","2025-04-18 18:00","취소","취소","연속"]
[226,"인천","직할","경서북인천#2 T/L","북인천S/S  경서-북인천#2T/L GIS 보통점검","북인천S/S  경서-북인천#2T/L GIS 보통점검","2025-04-04 09:30","2025-04-04 18:00","취소","취소","연속"]
[227,"인천","직할","신부평S/S CB 6200","신부평S/S 6200B/T GIS 보통점검","신부평S/S 6200B/T GIS 보통점검","2025-04-18 09:00","2025-04-18 18:00","2025-04-18 09:00","2025-04-18 18:00","연속"]
[228,"경기북부","고양","신덕은금촌#2 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-02 09:00","2025-04-02 18:00","2025-04-02 09:00","2025-04-02 18:00","연속"]
[229,"경기북부","고양","양주금촌#2 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-04 09:00","2025-04-04 18:00","2025-04-04 09:00","2025-04-04 18:00","연속"]
[230,"경기북부","고양","월롱금촌#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","연속"]
[231,"경기북부","고양","양주금촌#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-03 09:00","2025-04-03 18:00","2025-04-04 09:00","2025-04-04 18:00","연속"]
[232,"경기북부","고양","월롱금촌#2 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[233,"경기북부","고양","능곡상암#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-07 09:00","2025-04-07 18:00","2025-04-07 09:00","2025-04-07 18:00","연속"]
[234,"경기북부","고양","능곡상암#2 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[235,"경기북부","고양","신덕은금촌#1 T/L","24~25년 고양전력지사 가공송전 협력회사 총액공사","수평추락방지장치 설치","2025-04-15 07:00","2025-04-18 18:00","2025-04-15 07:00","2025-04-18 18:00","연속"]
[236,"경기북부","고양","신파주송포#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-28 09:00","2025-04-28 18:00","2025-04-28 09:00","2025-04-28 18:00","연속"]
[237,"경기북부","고양","신파주송포#2 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-29 09:00","2025-04-29 18:00","2025-04-29 09:00","2025-04-29 18:00","연속"]
[238,"경기북부","고양","원흥상암 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-17 09:00","2025-04-17 18:00","2025-03-31 09:00","2025-3-31 18:00","연속"]
[239,"경기북부","고양","신파주원흥#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-14 09:00","2025-04-14 18:00","2025-04-14 09:00","2025-04-14 18:00","연속"]
[240,"경기북부","고양","원흥수색#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[241,"경기북부","고양","신파주원흥#2 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","연속"]
[242,"경기북부","고양","일산호수#2 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2025-04-22 09:00","2025-04-22 18:00","2025-04-22 09:00","2025-04-22 18:00","연속"]
[243,"경기북부","고양","일산호수#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2025-04-21 09:00","2025-04-21 18:00","2025-04-21 09:00","2025-04-21 18:00","연속"]
[244,"경기북부","구리","가평청평HP#2 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","가평-청평HP#2(수직설치:36기,수평:36기) : No.1,8~32,34-1,43","2025-04-07 07:00","2025-04-11 18:00","취소","취소","연속"]
[245,"경기북부","구리","미금구리#1 T/L"," 구리-상봉T/L 증설공사","○ #1BUS 무부하 가압선로 ○ GIS 설치 × 1CCT ○ #1DS 및 차단부 설치","2025-04-10 09:00","2025-04-11 18:00","2025-04-10 09:00","2025-04-11 18:00","연속"]
[246,"경기북부","구리","미금구리#2 T/L"," 구리-상봉T/L 증설공사","○ #2BUS 무부하 가압선로 ○ GIS 설치 × 1CCT ○ #2DS 및 GIS 상부 설치","2025-04-21 09:00","2025-04-22 18:00","2025-04-21 09:00","2025-04-22 18:00","연속"]
[247,"경기북부","구리","미금구리#3 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 초기점검","2025-04-28 09:00","2025-04-28 18:00","2025-04-28 09:00","2025-04-28 18:00","연속"]
[248,"경기북부","구리","신장덕소#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-04-28 09:00","2025-04-28 18:00","2025-04-28 09:00","2025-04-28 18:00","연속"]
[249,"경기북부","구리","미금덕소#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-04-25 14:00","2025-04-25 18:00","2025-04-25 14:00","2025-04-25 18:00","연속"]
[250,"경기북부","구리","미금덕소#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-04-25 09:00","2025-04-25 14:00","2025-04-25 09:00","2025-04-25 14:00","연속"]
[251,"경기북부","구리","덕소마석#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-04-30 09:00","2025-04-30 18:00","2025-04-30 09:00","2025-04-30 18:00","연속"]
[252,"경기북부","구리","덕소팔당HP청평HP T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","덕소-팔당HP-청평HP(수직설치:2기,수평:2기) : No.46,68","2025-04-21 07:00","2025-04-21 18:00","2025-04-21 07:00","2025-04-21 18:00","연속"]
[253,"경기북부","구리","신포천전곡#1 T/L","2025년 가공송전 순시점검 위탁공사","정밀점검 작업구간 :  신포천-전곡#1 T/L No.1~46호 병가선로 -  신포천-덕계#2 T/L No.1~7호(4월1일) -  운천-전곡#2 T/L No.71~75호(4월8일)","2025-04-11 09:00","2025-04-18 18:00","2025-04-11 09:00","2025-04-18 18:00","연속"]
[254,"경기북부","구리","신포천백학#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신덕은-동두천CC#2T/L No.32~50 (子 :  신포천-백학#1T/L No.21~39)","2025-04-01 07:00","2025-04-03 18:00","2025-04-01 07:00","2025-04-03 18:00","연속"]
[255,"경기북부","구리","신포천덕계#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신포천-덕계#2 T/L No.65~70 (子 :  백석-덕계#2 T/L No.22~27)","2025-04-11 07:00","2025-04-11 18:00","2025-04-11 07:00","2025-04-11 18:00","연속"]
[256,"경기북부","구리","신포천덕계#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신포천-덕계#1 T/L No.65~70 (子 :  백석-덕계#1 T/L No.22~27)","2025-04-04 07:00","2025-04-04 18:00","2025-04-01 07:00","2025-04-01 18:00","연속"]
[257,"경기북부","구리","용정포천#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  포천-용정#1T/L No.1~4 (자선로 :  내촌-용정#2 T/L No.32~33)","2025-04-14 07:00","2025-04-14 18:00","2025-04-14 07:00","2025-04-14 18:00","연속"]
[258,"경기북부","구리","내촌용정#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  포천-용정#1T/L No.1~4 (자선로 :  내촌-용정#2 T/L No.32~33)","2025-04-14 07:00","2025-04-14 18:00","2025-04-14 07:00","2025-04-14 18:00","연속"]
[259,"경기북부","구리","운천전곡#2 T/L","2025년 가공송전 순시점검 위탁공사","정밀점검 작업구간 :  운천-전곡#2 T/L No.1, 13~76호 병가선로 -  신포천-전곡#1 T/L No.41~45호 (4월8일)","2025-04-18 08:00","2025-04-28 18:00","2025-04-18 08:00","2025-04-28 18:00","연속"]
[260,"경기북부","구리","지제용문#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-04-10 14:00","2025-04-10 18:00","2025-04-10 14:00","2025-04-10 18:00","연속"]
[261,"경기북부","구리","지제용문#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-04-10 09:00","2025-04-10 14:00","2025-04-10 09:00","2025-04-10 14:00","연속"]
[262,"경기북부","구리","별내진접 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-04-22 14:00","2025-04-22 18:00","2025-04-22 14:00","2025-04-22 18:00","연속"]
[263,"경기북부","구리","장암진접#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-04-22 09:00","2025-04-22 14:00","2025-04-22 09:00","2025-04-22 14:00","연속"]
[264,"경기북부","구리","마석청평HP#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","연속"]
[265,"경기북부","구리","마석청평HP#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-04-23 09:00","2025-04-23 18:00","2025-04-23 09:00","2025-04-23 18:00","연속"]
[266,"경기북부","구리","덕소팔당HP T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","덕소-팔당HP(수직설치:35기,수평:39기) : No.1~34,65~68","2025-04-14 07:00","2025-04-18 18:00","2025-04-14 07:00","2025-04-18 18:00","연속"]
[267,"경기북부","구리","신포천포천#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 초기점검","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[268,"경기북부","직할","양주녹양#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","피뢰기 설치(병가구간)","2025-04-08 07:00","2025-04-09 18:00","2025-04-08 07:00","2025-04-09 18:00","연속"]
[269,"경기북부","직할","녹양백석#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  녹양-백석#2 T/L No.1~11","2025-04-18 07:00","2025-04-18 18:00","2025-04-18 07:00","2025-04-18 18:00","연속"]
[270,"경기북부","직할","양주녹양#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 병가구간 - 대상 :  녹양-백석#2 T/L No.1~4","2025-04-18 07:00","2025-04-18 18:00","2025-04-18 07:00","2025-04-18 18:00","연속"]
[271,"경기북부","직할","녹양백석#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 녹양-백석#1T/L 피뢰기 설치","2025-04-08 07:00","2025-04-10 18:00","2025-04-08 07:00","2025-04-10 18:00","연속"]
[272,"경기북부","직할","백석덕계#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사","피뢰기 설치(병가구간)","2025-04-10 07:00","2025-04-11 18:00","2025-04-10 07:00","2025-04-11 18:00","연속"]
[273,"경기북부","직할","백석덕계#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신포천-덕계#1 T/L No.65~70 (子 :  백석-덕계#1 T/L No.22~27,28)","2025-04-04 07:00","2025-04-04 18:00","2025-04-04 07:00","2025-04-04 18:00","연속"]
[274,"경기북부","직할","신의정부내촌#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-내촌#2 T/L No.1~4 (子 :  신의정부-송우#1 T/L No.1~4)","2025-04-24 12:00","2025-04-24 18:00","2025-04-24 12:00","2025-04-24 18:00","연속"]
[275,"경기북부","직할","신의정부송우#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-내촌#2 T/L No.1~4 (子 :  신의정부-송우#1 T/L No.1~4)","2025-04-24 12:00","2025-04-24 18:00","2025-04-24 12:00","2025-04-24 18:00","연속"]
[276,"경기북부","직할","신의정부내촌#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-내촌#1 T/L No.1~4 (子 :  신의정부-송우#2 T/L No.1~4)","2025-04-07 07:00","2025-04-07 12:00","2025-04-07 07:00","2025-04-07 12:00","연속"]
[277,"경기북부","직할","신의정부송우#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-내촌#1 T/L No.1~4 (子 :  신의정부-송우#2 T/L No.1~4)","2025-04-07 07:00","2025-04-07 12:00","2025-04-07 07:00","2025-04-07 12:00","연속"]
[278,"경기북부","직할","양주은평#2 T/L","2024년 가공송전 순시점검 위탁공사(고양)","정밀점검","2025-04-21 09:00","2025-04-24 18:00","2025-04-21 09:00","2025-04-24 18:00","연속"]
[279,"경기북부","직할","양주지축#1 T/L","2024년 가공송전 순시점검 위탁공사(고양)","정밀점검(양주-은평T/L) 관련 병가선로 휴전","2025-04-21 09:00","2025-04-24 18:00","2025-04-21 09:00","2025-04-24 18:00","연속"]
[280,"경기북부","직할","양주은평#1 T/L","2024년 가공송전 순시점검 위탁공사(고양)","정밀점검","2025-04-14 09:00","2025-04-17 18:00","2025-04-14 09:00","2025-04-17 18:00","연속"]
[281,"경기북부","직할","양주지축#2 T/L","2024년 가공송전 순시점검 위탁공사(고양)","정밀점검(양주-은평T/L) 관련 병가선로 휴전","2025-04-14 09:00","2025-04-17 18:00","2025-04-14 09:00","2025-04-17 18:00","연속"]
[282,"경기북부","직할","운천전곡#1 T/L","2025년 경기북부본부 직할 170kV GIS 점검공사","170kV GIS 정밀점검 시험가압용 휴전(점검설비 : 신포천전곡#2TL)","2025-04-30 09:00","2025-04-30 18:00","2025-04-30 09:00","2025-04-30 18:00","연속"]
[283,"경기북부","직할","신포천전곡#2 T/L","2025년 경기북부본부 직할 170kV GIS 점검공사","170kV GIS 정밀점검","2025-04-28 09:00","2025-04-30 18:00","2025-04-28 09:00","2025-04-30 18:00","연속"]
[284,"경기","군포","사강남양#1 T/L"," 남양-사강T/L 지중화공사_가공 임시이설공사"," 남양-사강T/L 지중화공사_가공 임시이설공사","2025-04-21 07:00","2025-04-26 18:00","2025-04-21 07:00","2025-04-26 18:00","연속"]
[285,"경기","군포","서서울산본#1 T/L","산본S/S 서서울-산본#1T/L GIS 보통점검","산본S/S 서서울-산본#1T/L GIS 보통점검","2025-04-11 09:00","2025-04-11 18:00","2025-04-11 09:00","2025-04-11 18:00","연속"]
[286,"경기","군포","서서울#2서안양 T/L","서안양S/S 서서울2-서안양T/L 컨버터 불량교체 공사","서안양S/S 서서울2서안양 T/L 컨버터 불량교체 공사","2025-04-08 09:00","2025-04-08 18:00","취소","취소","연속"]
[287,"경기","군포","산본안양#2 T/L","안양S/S 산본-안양#2T/L GIS 보통점검","안양S/S 산본-안양#2T/L GIS 보통점검 시행","2025-04-14 09:00","2025-04-14 18:00","2025-04-14 09:00","2025-04-14 18:00","연속"]
[288,"경기","군포","산본안양#1 T/L","안양S/S 산본-안양#1T/L GIS 보통점검","안양S/S 산본-안양#1T/L GIS 보통점검 시행","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","연속"]
[289,"경기","군포","신시화중시화#2 T/L","중시화S/S 신시화-중시화#2T/L GIS 하자점검","중시화S/S 신시화-중시화#2T/L GIS 하자점검","2025-04-04 09:00","2025-04-04 18:00","2025-04-04 09:00","2025-04-04 18:00","연속"]
[290,"경기","군포","신시화중시화#1 T/L","중시화S/S 신시화-중시화#1T/L GIS 하자점검","중시화S/S 신시화-중시화#1T/L GIS 하자점검","2025-04-03 09:00","2025-04-03 18:00","2025-04-03 09:00","2025-04-03 18:00","연속"]
[291,"경기","동부","곤지암용문#2 T/L","2025년 가공송전 순시점검 위탁공사"," 곤지암-용문 #2T/L 정밀점검(1~83호)","2025-04-18 09:00","2025-04-30 18:00","2025-04-18 09:00","2025-04-30 18:00","연속"]
[292,"경기","동부","곤지암S/S SEC CB 61620","24-25년 동부 변전협력회사 총액공사","(오전)효성제 GIS 발청점검 곤지암:61-62 (오후)곤지암:61-62(보통)","2025-04-01 09:00","2025-04-01 18:00","2025-04-01 09:00","2025-04-01 18:00","연속"]
[293,"경기","동부","곤지암용문#1 T/L","2025년 가공송전 순시점검 위탁공사"," 곤지암-용문 #1T/L 정밀점검(1~83호)","2025-04-07 09:00","2025-04-17 18:00","2025-04-07 09:00","2025-04-17 18:00","연속"]
[294,"경기","동부","성현분당#2 T/L","25년 분당S/S  장기사용 GIS 교체공사","GIS 무부하가압용 선로 및 안전이격확보","2025-04-10 09:00","2025-04-30 18:00","2025-04-10 09:00","2025-04-30 18:00","연속"]
[295,"경기","동부","왕암여주#2 T/L","24-25년 동부 변전협력회사 총액공사","효성제 GIS 발청 여주:왕암-여주#1,2T/L","2025-04-24 14:00","2025-04-24 18:00","2025-04-24 14:00","2025-04-24 18:00","연속"]
[296,"경기","동부","왕암여주#1 T/L","24-25년 동부 변전협력회사 총액공사","효성제 GIS 발청 여주:왕암-여주#1,2T/L","2025-04-24 09:00","2025-04-24 14:00","2025-04-24 09:00","2025-04-24 14:00","연속"]
[297,"경기","동부","오포모현#2 T/L","24-25년 동부 변전협력회사 총액공사","오포:오포-모현#2T/L(보통)","2025-04-02 09:00","2025-04-02 18:00","2025-04-02 09:00","2025-04-02 18:00","연속"]
[298,"경기","성남","남사동탄#1 T/L"," 중동탄분기 지중T/L 건설공사","공사구간 : 남사-동탄 #1TL (M/H#6 ~ M/H#7 2π 분기) / 긍장 :  XLPE 2,500㎜ 4C×1.55㎞, XLPE 2,000㎜ 4C(D)×0.355㎞ / 포설 (3상 1구간 기준) : 20 구간 / 접속 (3상 1개소 기준) : 20개소 (EB-G 4개소, PMIJ 16개소)","2025-04-21 09:00","2025-06-26 18:00","2025-04-21 09:00","2025-06-26 18:00","연속"]
[299,"경기","성남","신봉이의#1 T/L","광교 A4블록 지장철탑 이설공사(요청자 부담)","광교 A4블록 지장철탑 이설공사(요청자 부담)[4회선 병가]","2025-04-13 07:00","2025-04-25 18:00","2025-04-13 07:00","2025-04-25 18:00","연속"]
[300,"경기","성남","신봉이의#2 T/L","광교 A4블록 지장철탑 이설공사(요청자 부담)","광교 A4블록 지장철탑 이설공사(요청자 부담)[4회선 병가]","2025-04-28 07:00","2025-05-07 18:00","2025-04-28 07:00","2025-05-07 18:00","연속"]
[301,"경기","성남","신성남신봉#1 T/L","24-25년 경기직할 송전협력회사 공사","불량애자 교체공사[4회선 병가]","2025-04-28 07:00","2025-04-28 18:00","2025-04-28 07:00","2025-04-28 18:00","연속"]
[302,"경기","성남","신성남서판교#2 T/L","2025년 성남전력 170kV GIS 정밀점검공사","- gis 정밀점검","2025-04-23 09:00","2025-04-24 18:00","취소","취소","연속"]
[303,"경기","성남","신성남S/S SEC CB 62630","2025년 성남전력 170kV GIS 정밀점검공사","- gis 정밀점검","2025-04-21 09:00","2025-04-22 18:00","2025-04-21 09:00","2025-04-22 18:00","연속"]
[304,"경기","성남","신성남S/S #62 BUS","2025년 성남전력 170kV GIS 정밀점검공사","- 62-63 무부하가압용","2025-04-22 09:00","2025-04-22 18:00","2025-04-22 09:00","2025-04-22 18:00","연속"]
[305,"경기","성남","신성남S/S CB 6400","2025년 성남전력 170kV GIS 정밀점검공사","- gis 정밀점검","2025-04-14 09:00","2025-04-15 18:00","2025-04-14 09:00","2025-04-15 18:00","연속"]
[306,"경기","성남","신성남S/S SEC CB 67680","2025년 성남전력 170kV GIS 정밀점검공사","- gis 정밀점검","2025-04-16 09:00","2025-04-17 18:00","2025-04-16 09:00","2025-04-17 18:00","연속"]
[307,"경기","성남","신성남S/S #67 BUS","2025년 성남전력 170kV GIS 정밀점검공사","- 67-68 무부하가압용","2025-04-17 09:00","2025-04-17 18:00","2025-04-17 09:00","2025-04-17 18:00","연속"]
[308,"경기","성남","신성남S/S #63 BUS","2025년 성남전력 170kV GIS 정밀점검공사","- 6400 무부하가압용","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","연속"]
[309,"경기","성남","신수원북동탄#2 T/L","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-30 14:00","2025-04-30 18:00","2025-04-30 14:00","2025-04-30 18:00","연속"]
[310,"경기","성남","신수원북동탄#1 T/L","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-30 09:00","2025-04-30 14:00","2025-04-30 09:00","2025-04-30 14:00","연속"]
[311,"경기","성남","신수원S/S SEC CB 66670","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-29 14:00","2025-04-29 18:00","취소","취소","연속"]
[312,"경기","성남","신수원S/S SEC CB 61620","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-29 09:00","2025-04-29 14:00","2025-04-29 09:00","2025-04-29 14:00","연속"]
[313,"경기","성남","신수원S/S SEC CB 65660","2025년 성남전력 변전협력회사 총액공사","- gis 보통점검","2025-04-25 09:00","2025-04-25 18:00","2025-04-25 09:00","2025-04-25 18:00","연속"]
[314,"경기","성남","신수원S/S SEC CB 60610","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-22 14:00","2025-04-22 18:00","취소","취소","연속"]
[315,"경기","성남","신수원S/S CB 6300","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-22 09:00","2025-04-22 14:00","취소","취소","연속"]
[316,"경기","성남","신수원화성열병#2 T/L","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-21 14:00","2025-04-21 18:00","2025-04-21 14:00","2025-04-21 18:00","연속"]
[317,"경기","성남","신수원화성열병#1 T/L","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-21 09:00","2025-04-21 14:00","2025-04-21 09:00","2025-04-21 14:00","연속"]
[318,"경기","성남","신수원S/S #65 BUS","신수원S/S  동반#1T/L GIS 교체공사"," 동반#1T/L GIS 교체 - 무부하가압","2025-04-17 13:00","2025-04-18 13:00","취소","취소","연속"]
[319,"경기","성남","신수원S/S #60 BUS","신수원S/S  동반#1T/L GIS 교체공사"," 동반#1T/L GIS 교체 - 무부하가압","2025-04-17 10:00","2025-04-17 13:00","취소","취소","연속"]
[320,"경기","성남","신수원S/S CB 6300","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-15 14:00","2025-04-15 18:00","취소","취소","연속"]
[321,"경기","성남","신수원S/S CB 6200","2025년 성남전력 변전협력회사 총액공사","- gis 보통점검","2025-04-15 09:00","2025-04-15 14:00","취소","취소","연속"]
[322,"경기","성남","신수원S/S CB 6200","2025년 성남전력 변전협력회사 총액공사","- GIS 보통점검","2025-04-03 14:00","2025-04-03 18:00","2025-04-03 14:00","2025-04-03 18:00","연속"]
[323,"경기","성남","신수원S/S CB 6100","2025년 성남전력 변전협력회사 총액공사","- GIS 보통점검","2025-04-03 09:00","2025-04-03 14:00","취소","취소","연속"]
[324,"경기","성남","신용인S/S SEC CB 61620","2025년 성남전력 변전협력회사 총액공사","- gis 보통점검","2025-04-11 09:00","2025-04-11 14:00","취소","취소","연속"]
[325,"경기","성남","신용인S/S SEC CB 65660","2025년 성남전력 170kV GIS 정밀점검공사","- gis 정밀점검","2025-04-09 09:00","2025-04-10 18:00","취소","취소","연속"]
[326,"경기","성남","신용인동백#2 T/L","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-17 14:00","2025-04-17 18:00","2025-04-17 14:00","2025-04-17 18:00","연속"]
[327,"경기","성남","신용인기흥#2 T/L","[11월 순연] 24-25년 경기직할 송전협력회사 공사","[11월 순연] 피뢰기 설치공사","2025-04-01 07:00","2025-04-01 18:00","2025-04-01 07:00","2025-04-01 18:00","연속"]
[328,"경기","성남","신용인S/S SEC CB 60610","2025년 성남전력 170kV GIS 정밀점검공사","- GIS 정밀점검","2025-04-01 09:00","2025-04-02 18:00","취소","취소","연속"]
[329,"경기","성남","신용인S/S #60 BUS","2025년 성남전력 170kV GIS 정밀점검공사","- 60-61 무부하가압용","2025-04-02 09:00","2025-04-02 18:00","취소","취소","연속"]
[330,"경기","성남","신용인S/S CB 6100","2025년 성남전력 변전협력회사 총액공사","- GIS 조작시험","2025-04-04 09:00","2025-04-04 14:00","2025-04-04 09:00","2025-04-04 14:00","연속"]
[331,"경기","성남","신용인S/S CB 6200","2025년 성남전력 변전협력회사 총액공사","- GIS 조작시험","2025-04-04 14:00","2025-04-04 18:00","2025-04-04 14:00","2025-04-04 18:00","연속"]
[332,"경기","성남","신용인동백#1 T/L","2025년 성남전력 변전협력회사 총액공사","- gis 조작시험","2025-04-17 09:00","2025-04-17 14:00","2025-04-17 09:00","2025-04-17 14:00","연속"]
[333,"경기","성남","신용인S/S #65 BUS","2025년 성남전력 170kV GIS 정밀점검공사","- 65-66 무부하가압용","2025-04-10 09:00","2025-04-10 18:00","취소","취소","연속"]
[334,"경기","성남","신용인기흥#1 T/L","[11월 순연] 24-25년 경기직할 송전협력회사 공사","[11월 순연] 불량애자 교체공사(4회선 병가 안전거리 휴전)","2025-04-05 07:00","2025-04-05 13:00","2025-04-05 07:00","2025-04-05 13:00","연속"]
[335,"경기","성남","신용인용인#2 T/L","[11월 순연] 24-25년 경기직할 송전협력회사 공사","[11월 순연] 피뢰기 설치공사","2025-04-02 07:00","2025-04-05 18:00","2025-04-02 07:00","2025-04-05 18:00","연속"]
[336,"경기","성남","용인덕성#2 T/L","[11월 순연] 24-25년 경기직할 송전협력회사 공사","[11월 순연] 피뢰기 설치공사(4회선 병가 안전거리 휴전)","2025-04-05 13:00","2025-04-05 18:00","2025-04-05 13:00","2025-04-05 18:00","연속"]
[337,"경기","직할","관양동안양#2 T/L","2024-25년 경기본부 직할 변전협력회사 총액공사","관양: 관양-동안양#2T/L GIS 보통점검","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[338,"경기","직할","관양동안양#1 T/L","2024-25년 경기본부 직할 변전협력회사 총액공사","관양: 관양-동안양#1T/L GIS 보통점검","2025-04-07 09:00","2025-04-07 18:00","2025-04-07 09:00","2025-04-07 18:00","연속"]
[339,"경기","직할","동안양안양CC#2 T/L","동안양S/S 지중송전선로 인출정비 공사"," 동안양-안열T/L 인출정비 - 선종/길이 : XLPE 2000 / 0.404km","2025-04-01 09:00","2025-04-30 18:00","2025-04-01 09:00","2025-04-30 18:00","연속"]
[340,"경기","직할","과천동안양#2 T/L"," 과천-동안양T/L 지중화공사(과천지식정보타운)","과천지식정보타운 사업지구 내 지장송전선로 지중화","2025-04-01 09:00","2025-08-29 18:00","2025-04-01 09:00","2025-08-29 18:00","연속"]
[341,"경기","직할","발안구문천#2 T/L","2024-25년 경기본부 직할 변전협력회사 총액공사","발안: 발안-구문천#2T/L GIS 보통점검","2025-04-18 09:00","2025-04-18 18:00","2025-04-18 09:00","2025-04-18 18:00","연속"]
[342,"경기","직할","율전동수원#2 T/L","광교 A4블록 지장철탑 이설공사(요청자 부담)","광교 A4블록 지장철탑 이설공사(요청자 부담)[4회선 병가]","2025-04-13 07:00","2025-04-25 18:00","2025-04-13 07:00","2025-04-25 18:00","연속"]
[343,"경기","직할","율전의왕#1 T/L","2024-25년 경기본부 직할 변전협력회사 총액공사","율전: 율전-의왕#1,2T/L 조작시험","2025-04-30 09:00","2025-04-30 14:00","취소","취소","연속"]
[344,"경기","직할","율전의왕#2 T/L","2024-25년 경기본부 직할 변전협력회사 총액공사","율전: 율전-의왕#1,2T/L 조작시험","2025-04-30 14:00","2025-04-30 18:00","취소","취소","연속"]
[345,"경기","직할","율전동수원#1 T/L","광교 A4블록 지장철탑 이설공사(요청자 부담)","광교 A4블록 지장철탑 이설공사(요청자 부담)[4회선 병가]","2025-04-29 07:00","2025-05-07 18:00","2025-04-29 07:00","2025-05-07 18:00","연속"]
[346,"경기","직할","관양평촌#1 T/L","평촌S/S 안양-평촌#3T/L 증설공사","안양-평촌#3T/L GIS 상체크 및 무부하가압","2025-04-28 09:00","2025-04-29 18:00","2025-04-28 09:00","2025-04-29 18:00","연속"]
[347,"경기","직할","화성S/S CB 6300","2024-25년 경기본부 직할 변전협력회사 공사","화성: 62-67 BUS TIE GIS 보통점검","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[348,"경기","직할","화성발안#2 T/L","변전소 구내 활선선로 외물접촉 방지 장치 설치 공사","화성 : 화성-발안#2T/L 외물접촉 방지 장치 설치 공사","2025-04-02 09:00","2025-04-02 18:00","2025-04-02 09:00","2025-04-02 18:00","연속"]
[349,"경기","평택","고덕평택#1 T/L","2025-2026년 경기본부 평택전력지사 지중송전 협력회사 공사","케이블타워 및 피뢰기 점검(피뢰기 절연열화 측정)","2025-04-10 08:00","2025-04-11 18:00","2025-04-10 08:00","2025-04-11 18:00","연속"]
[350,"경기","평택","고덕진위#2 T/L"," 고덕-진위T/L 초기점검","2025년도 가공송전 순시점검 위탁회사  고덕-진위T/L 초기점검","2025-04-03 09:00","2025-04-03 18:00","2025-04-03 09:00","2025-04-03 18:00","연속"]
[351,"경기","평택","서안성S/S CB 6300","2025년 평택전력 변전협력회사 총액공사","서안성S/S  #62-#67 BUS TIE(6300) GIS 보통점검","2025-04-07 09:00","2025-04-07 18:00","2025-04-07 09:00","2025-04-07 18:00","연속"]
[352,"경기","평택","서안성S/S SEC CB 61620","2025년 평택전력 변전협력회사 총액공사","서안성S/S  #61-#62 SEC GIS GIS 보통점검","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[353,"경기","평택","서안성S/S SEC CB 66670","2025년 평택전력 변전협력회사 총액공사","서안성S/S  #66-#67 SEC GIS 보통점검","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[354,"경기","평택","서운안성#1 T/L"," 오산-평택T/L 등 13개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치공사 -작업구간: 4회선 14기","2025-04-07 08:00","2025-04-11 18:00","취소","취소","연속"]
[355,"경기","평택","서운삼죽 T/L"," 오산-평택T/L 등 13개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치공사 -작업구간: 4회선 14기","2025-04-14 08:00","2025-04-18 18:00","2025-04-14 08:00","2025-04-18 18:00","연속"]
[356,"경기","평택","서운광혜원 T/L"," 오산-평택T/L 등 13개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치공사 -작업구간: 4회선 14기","2025-04-07 08:00","2025-04-11 18:00","취소","취소","연속"]
[357,"경기","평택","서운안성#2 T/L"," 오산-평택T/L 등 13개T/L 추락방지장치 설치공사","추락방지장치(수평) 설치공사 -작업구간: 4회선 14기","2025-04-14 08:00","2025-04-18 18:00","2025-04-14 08:00","2025-04-18 18:00","연속"]
[358,"경기","평택","소사벌안성 T/L","2025-2026년 경기본부 평택전력지사 지중송전 협력회사 공사","EBA 절연유 채유, 케이블타워 및 피뢰기 점검","2025-04-01 08:00","2025-04-02 18:00","2025-04-01 08:00","2025-04-02 18:00","연속"]
[359,"경기","평택","평택오성CC#1 T/L","2025년 평택전력 변전협력회사 총액공사","평택S/S 평택-오성C/C #1T/L GCB 조작시험","2025-04-23 09:00","2025-04-23 18:00","2025-04-23 09:00","2025-04-23 18:00","연속"]
[360,"경기","평택","평택오성CC#2 T/L","2025년 평택전력 변전협력회사 총액공사","평택S/S 평택-오성C/C #2T/L GCB 보통점검 및 PT, LA 보통점검","2025-04-09 10:00","2025-04-09 18:00","2025-04-09 10:00","2025-04-09 18:00","연속"]
[361,"경기","평택","송탄오성CC#1 T/L"," 평택-추팔T/L 용량증대 선종교체공사"," 평택-추팔T/L No.13 ~ 추팔S/S [18.2C-km] [ACSR 330㎟×S ⇒ ASCC/TW(탄소-금속) 410㎟×S]","2025-04-19 09:00","2025-04-20 18:00","2025-04-19 09:00","2025-04-20 18:00","연속"]
[362,"경기","평택","청북평택#2 T/L","추락방지장치(수평) 설치공사"," 포승-청북T/L No.47~54 4회선 ( 청북-평택T/L No.2~9 병가) 8기","2025-04-28 08:00","2025-04-30 18:00","2025-04-28 08:00","2025-04-30 18:00","연속"]
[363,"경기","평택","만호청북#1 T/L","추락방지장치(수평) 설치공사"," 포승-청북T/L No.47~54 4회선 ( 청북-평택T/L No.2~9 병가) 8기","2025-04-28 08:00","2025-04-30 18:00","2025-04-28 08:00","2025-04-30 18:00","연속"]
[364,"경기","평택","청북평택#1 T/L","추락방지장치(수평) 설치공사"," 포승-청북T/L No.47~54 4회선( 청북-평택T/L No.2~9 병가) 8기","2025-04-25 08:00","2025-04-27 18:00","2025-04-25 08:00","2025-04-27 18:00","연속"]
[365,"경기","평택","둔포추팔#1 T/L"," 평택-추팔T/L 용량증대 선종교체공사"," 평택-추팔T/L No.13 ~ 추팔S/S [18.2C-km] [ACSR 330㎟×S ⇒ ASCC/TW(탄소-금속) 410㎟×S]","2025-04-06 09:00","2025-04-06 18:00","2025-04-06 09:00","2025-04-06 18:00","연속"]
[366,"경기","평택","둔포추팔#2 T/L"," 평택-추팔T/L 용량증대 선종교체공사"," 평택-추팔T/L No.13 ~ 추팔S/S [18.2C-km] [ACSR 330㎟×S ⇒ ASCC/TW(탄소-금속) 410㎟×S]","2025-04-05 09:00","2025-04-06 18:00","2025-04-05 09:00","2025-04-06 18:00","연속"]
[367,"경기","평택","둔포추팔#1 T/L"," 평택-추팔T/L 용량증대 선종교체공사"," 평택-추팔T/L No.13 ~ 추팔S/S [18.2C-km] [ACSR 330㎟×S ⇒ ASCC/TW(탄소-금속) 410㎟×S]","2025-04-12 09:00","2025-04-13 18:00","2025-04-12 09:00","2025-04-13 18:00","연속"]
[368,"경기","평택","평택추팔#2 T/L"," 평택-추팔T/L 용량증대 선종교체공사"," 평택-추팔T/L No.13 ~ 추팔S/S [18.2C-km] [ACSR 330㎟×S ⇒ ASCC/TW(탄소-금속) 410㎟×S]","2025-04-09 09:00","2025-04-24 18:00","2025-04-09 09:00","2025-04-24 18:00","연속"]
[369,"경기","평택","평택추팔#1 T/L","2025년 평택전력 변전협력회사 총액공사","평택S/S 평택추팔#1 T/L GCB 조작시험","2025-04-01 09:00","2025-04-01 18:00","2025-04-01 09:00","2025-04-01 18:00","연속"]
[370,"경기","평택","평택T/P #60 BUS","평택T/P  해기#2T/L 무부하가압","평택T/P  해기#2T/L 무부하가압","2025-04-11 10:00","2025-04-11 18:00","2025-04-11 10:00","2025-04-11 18:00","연속"]
[371,"경기","평택","평택T/P SEC CB 60610","평택T/P  해기#2T/L 무부하가압","평택T/P  해기#2T/L 무부하가압","2025-04-11 10:00","2025-04-11 18:00","2025-04-11 10:00","2025-04-11 18:00","연속"]
[372,"경기","평택","평택T/P CB 6100","평택T/P  해기#2T/L 무부하가압","평택T/P  해기#2T/L 무부하가압","2025-04-11 10:00","2025-04-11 18:00","2025-04-11 10:00","2025-04-11 18:00","연속"]
[373,"경기","평택","포승청북 T/L","추락방지장치(수평) 설치공사"," 포승-청북T/L No.47~54 4회선 ( 청북-평택T/L No.2~9 병가) 8기","2025-04-25 08:00","2025-04-27 18:00","2025-04-25 08:00","2025-04-27 18:00","연속"]
[374,"경기","성남","통열T/L CB","2025년 성남전력 변전협력회사 총액공사 ","GIS 보통점검 ","2025-04-01 09:00","2025-04-01 18:00","취소","취소","연속"]
[375,"강원","강릉","속초간성#1 T/L","2024~2025년 가공송전협력회사 총액공사","○ 전선접속개소 해소공사(No.40~41) ○ 노후금구류 교체 및 피뢰기 설치(No.49,91)","2025-04-15 07:00","2025-04-16 18:00","2025-04-15 07:00","2025-04-16 18:00","매일"]
[376,"강원","강릉","속초간성#2 T/L","2024~2025년 가공송전협력회사 총액공사","○ 전선접속개소 해소공사(No.40~42)","2025-04-14 07:00","2025-04-14 18:00","2025-04-14 07:00","2025-04-14 18:00","연속"]
[377,"강원","원주","원주북원주#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 수직/수평 추락방지장치 설치 및 기타 정비작업","2025-04-10 07:00","2025-04-16 18:00","2025-04-10 07:00","2025-04-16 18:00","매일"]
[378,"강원","원주","원주북원주#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 수직/수평 추락방지장치 설치 및 기타 정비작업","2025-04-02 07:00","2025-04-08 18:00","2025-04-02 07:00","2025-04-08 18:00","매일"]
[379,"강원","원주","원주서원주#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 수직/수평 추락방지장치 설치 및 기타 정비작업","2025-04-09 07:00","2025-04-11 18:00","2025-04-09 07:00","2025-04-11 18:00","매일"]
[380,"강원","원주","원주서원주#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 수직/수평 추락방지장치 설치 및 기타 정비작업","2025-04-01 07:00","2025-04-03 18:00","2025-04-01 07:00","2025-04-03 18:00","매일"]
[381,"강원","원주","북원주횡성#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 수직/수평 추락방지장치 설치 및 기타 정비작업","2025-04-04 07:00","2025-04-08 18:00","2025-04-04 07:00","2025-04-09 16:00","매일"]
[382,"강원","원주","북원주횡성#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 수직/수평 추락방지장치 설치 및 기타 정비작업","2025-04-14 07:00","2025-04-16 18:00","2025-04-14 07:00","2025-04-16 18:00","매일"]
[383,"강원","직할","남춘천춘천열병합#2 T/L","남춘천S/S  장기사용 GIS 대체공사","● 2차공정 -  홍천-남춘천T/L GIS -  #2M.Tr 1차 GIS","2025-04-29 09:00","2025-04-30 18:00","2025-04-29 09:00","2025-04-30 18:00","연속"]
[384,"강원","직할","남춘천춘천열병합#2 T/L","남춘천S/S  장기사용 GIS 대체공사","● 2차공정 -  홍천-남춘천T/L GIS -  #2M.Tr 1차 GIS 휴전사유 : 월부싱 철거/설치 시 안전이격","2025-04-10 09:00","2025-04-15 18:00","2025-04-10 09:00","2025-04-15 18:00","연속"]
[385,"강원","직할","남춘천춘천열병합#2 T/L","남춘천S/S  장기사용 GIS 대체공사","● 2차공정 -  홍천-남춘천T/L GIS -  #2M.Tr 1차 GIS 휴전사유 : #2BUS 무부하가압(DS부 ENDCOVER 고깔)","2025-04-03 09:00","2025-04-04 18:00","2025-04-03 09:00","2025-04-04 18:00","연속"]
[386,"강원","직할","남춘천S/S #1 BUS","남춘천S/S  장기사용 GIS 대체공사","● 2차공정 -  홍천-남춘천T/L GIS -  #2M.Tr 1차 GIS","2025-04-04 14:00","2025-04-22 14:00","2025-04-04 14:00","2025-04-22 14:00","연속"]
[387,"강원","직할","남춘천춘천열병합#2 T/L","남춘천S/S  장기사용 GIS 대체공사","● 2차공정 -  홍천-남춘천T/L GIS -  #2M.Tr 1차 GIS 휴전사유 : #1BUS 및 #1DS, CB부 무부하가압용","2025-04-21 09:00","2025-04-22 18:00","2025-04-21 09:00","2025-04-22 18:00","연속"]
[388,"강원","직할","남춘천S/S #2 BUS","남춘천S/S  장기사용 GIS 대체공사","● 2차공정 -  홍천-남춘천T/L GIS -  #2M.Tr 1차 GIS","2025-04-22 14:00","2025-05-09 14:00","2025-04-22 14:00","2025-05-09 14:00","연속"]
[389,"강원","직할","인제양구#2 T/L"," 상제 등 3개 T/ L 추락방지장치 설치공사"," 양구 T/L 추락방지장치 설치","2025-04-07 07:00","2025-04-18 18:00","취소","취소","매일"]
[390,"강원","직할","비즌비츠로#1 T/L CB","2024~2025년 강원본부 직할 변전협력회사 공사","철원S/S  비즌비츠로#1T/L GIS 보통점검","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[391,"강원","직할","철원화천#2 T/L","2024년~2025년 강원본부 직할 변전협력회사 공사","철원화천#2 T/L 보호배전반 대체","2025-04-21 10:00","2025-04-25 18:00","2025-04-21 10:00","2025-04-25 18:00","연속"]
[392,"강원","직할","철원화천#1 T/L","2024년~2025년 강원본부 직할 변전협력회사 공사","철원화천#1 T/L 보호배전반 대체","2025-04-14 10:00","2025-04-18 18:00","2025-04-14 10:00","2025-04-18 18:00","연속"]
[393,"강원","태백","영월S/S CB 6100","2024-2025년 태백전력지사 변전협력회사 공사","영월S/S  #1-#2 BUS-TIE GIS 조작시험","2025-04-15 09:00","2025-04-15 14:00","2025-04-15 09:00","2025-04-15 14:00","연속"]
[394,"강원","태백","영월영월에코윈드#2 T/L"," 태백-영월에코윈드 등 2개 T/L 피뢰기 설치공사"," 태백-영월에코윈드 등 2개 T/L 피뢰기 설치공사","2025-04-17 09:00","2025-04-30 18:00","2025-04-17 09:00","2025-04-30 18:00","매일"]
[395,"강원","태백","영월영월CC T/L","2024-2025년 태백전력지사 변전협력회사 공사","영월S/S  영월-영월C/C T/L GIS 조작시험","2025-04-15 14:00","2025-04-15 18:00","2025-04-15 14:00","2025-04-15 18:00","연속"]
[396,"강원","태백","영월에코윈드S/S CB 6200","2024-2025년 태백전력지사 변전협력회사 공사","영월에코윈드S/Y  #61-#66 BUS-TIE GIS 보통점검","2025-04-01 09:00","2025-04-01 18:00","2025-04-01 09:00","2025-04-01 18:00","연속"]
[397,"강원","태백","영월에코윈드S/S SEC CB 60610","2024-2025년 태백전력지사 변전협력회사 공사","영월에코윈드S/Y  #60-#61 SEC GIS 보통점검","2025-04-02 09:00","2025-04-02 18:00","2025-04-02 09:00","2025-04-02 18:00","연속"]
[398,"강원","태백","영월에코윈드S/S SEC CB 65660","2024-2025년 태백전력지사 변전협력회사 공사","영월에코윈드S/Y  #65-#66 SEC GIS 보통점검","2025-04-03 09:00","2025-04-03 18:00","2025-04-03 09:00","2025-04-03 18:00","연속"]
[399,"강원","태백","태백삼척GP#2 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 태백-삼척GP#2 T/L 수평추락방지장치 및 폴리머 점퍼지지애자 설치","2025-04-18 08:00","2025-06-06 18:00","2025-04-18 08:00","2025-06-06 18:00","연속"]
[400,"강원","태백","태백영월에코윈드 T/L"," 태백-영월에코윈드 등 2개 T/L 피뢰기 설치공사"," 태백-영월에코윈드 등 2개 T/L 피뢰기 설치공사","2025-04-07 09:00","2025-04-16 18:00","2025-04-07 09:00","2025-04-16 18:00","매일"]
[401,"충북","직할","삼죽광혜원 T/L","광혜원S/S 23kV 장기사용 GIS 대체공사(병행)","GIS 제어케이블 LID 이설 및 보호반 개조","2025-04-01 10:00","2025-04-02 18:00","2025-04-01 10:00","2025-04-02 18:00","연속"]
[402,"충북","직할","서운광혜원 T/L","광혜원S/S 23kV 장기사용 GIS 대체공사(병행)","GIS 제어케이블 LID 이설 및 보호반 개조","2025-04-03 10:00","2025-04-04 18:00","2025-04-03 10:00","2025-04-04 18:00","연속"]
[403,"충북","직할","진천광혜원#2 T/L","광혜원S/S 23kV 장기사용 GIS 대체공사(병행)","제어/감시/경보 제어케이블 RTU → LID 이설","2025-04-07 10:00","2025-04-08 18:00","취소","취소","연속"]
[404,"충북","직할","진천광혜원#1 T/L","광혜원S/S 23kV 장기사용 GIS 대체공사(병행)","제어/감시/경보 제어케이블 RTU → LID 이설","2025-04-09 10:00","2025-04-10 18:00","취소","취소","연속"]
[405,"충북","직할","진천광혜원#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","접속개소 전선교체(1.707C-km), 수평 추락방지장치 설치(39기), 피뢰기 설치(49기), 아킹혼 설치(1기), 조류착지방지장치 설치(1기)","2025-04-14 07:30","2025-04-25 18:00","취소","취소","연속"]
[406,"충북","직할","서운광혜원 T/L","`","접속개소 전선교체(1.221C-km), 수평 추락방지장치 설치(39기), 피뢰기 설치(39기), 애자교체(1기), 금구류 정비(1기)","2025-04-14 07:30","2025-04-25 18:00","취소","취소","연속"]
[407,"충북","직할","문백오창#2 T/L","345kV 신청주S/S 건설공사","․ GIS 687(신청주-문백#2T/L) Bay 증설 - #61BUS 무부하가압","2025-04-07 13:00","2025-04-08 13:00","2025-04-07 13:00","2025-04-08 13:00","연속"]
[408,"충북","직할","문백오창#1 T/L","345kV 신청주S/S 건설공사"," GIS 617(신청주-문백#1T/L) Bay 증설 - #65BUS 무부하가압","2025-04-02 18:00","2025-04-03 18:00","2025-04-02 18:00","2025-04-03 18:00","연속"]
[409,"충북","직할","문백오창#2 T/L","345kV 신청주S/S 건설공사","․ GIS 687(신청주-문백#2T/L) Bay 증설 - #66BUS 무부하가압","2025-04-10 18:00","2025-04-11 18:00","2025-04-10 18:00","2025-04-11 18:00","연속"]
[410,"충북","직할","문백오창#1 T/L","'24-25년 충북 직할 변전협력회사 공사","문백S/S  문백-오창#1T/L GIS 초기점검","2025-04-17 10:00","2025-04-17 16:00","2025-04-17 10:00","2025-04-17 16:00","연속"]
[411,"충북","직할","문백오창#2 T/L","'24-25년 충북 직할 변전협력회사 공사","문백S/S  문백-오창#2T/L GIS 초기점검","2025-04-18 10:00","2025-04-18 16:00","2025-04-18 10:00","2025-04-18 16:00","연속"]
[412,"충북","직할","신진천문백#1 T/L","24-25년 충북본부 직할 변전협력회사 공사","문백S/S  신진천-문백#1T/L GIS 초기점검","2025-04-22 10:00","2025-04-22 18:00","2025-04-22 10:00","2025-04-22 18:00","연속"]
[413,"충북","직할","신진천진천#2 T/L","2025년 가공송전선로 순시점검 위탁공사","일반인 중장비 사용 공사현장 접근제한장치 설치","2025-04-27 09:00","2025-04-27 18:00","2025-04-27 09:00","2025-04-27 18:00","연속"]
[414,"충북","직할","신진천진천#1 T/L","2025년 가공송전선로 순시점검 위탁공사","일반인 중장비 사용 공사현장 접근제한장치 설치","2025-04-26 09:00","2025-04-26 18:00","2025-04-26 09:00","2025-04-26 18:00","연속"]
[415,"충북","청주","남청주S/S #67 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2025-04-22 14:00","2025-04-27 14:00","취소","취소","연속"]
[416,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIIS 대체 (무부하가압용)","2025-04-26 14:00","2025-04-27 14:00","취소","취소","연속"]
[417,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2025-04-27 14:00","2025-04-29 18:00","취소","취소","연속"]
[418,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIIS 대체 (무부하가압용)","2025-04-28 14:00","2025-04-29 14:00","취소","취소","연속"]
[419,"충북","청주","남청주S/S SEC CB 62610","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체","2025-04-30 08:00","2025-05-08 18:00","취소","취소","연속"]
[420,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62SEC GIS 대체","2025-04-30 08:00","2025-05-01 14:00","취소","취소","연속"]
[421,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIIS 대체 (무부하가압용)","2025-04-21 14:00","2025-04-22 14:00","취소","취소","연속"]
[422,"충북","청주","남청주청주#2 T/L","남청주S/S  장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2025-04-01 08:00","2025-04-19 18:00","2025-04-01 08:00","2025-04-19 18:00","연속"]
[423,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2025-04-01 08:00","2025-04-04 14:00","2025-04-01 08:00","2025-04-04 14:00","연속"]
[424,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2025-04-21 08:00","2025-04-22 14:00","취소","취소","연속"]
[425,"충북","청주","남청주S/S SEC CB 67660","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체","2025-04-21 08:00","2025-04-29 18:00","취소","취소","연속"]
[426,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2025-04-13 14:00","2025-04-20 18:00","2025-04-13 14:00","2025-04-20 18:00","연속"]
[427,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(1차)","#2M.Tr 2차 및 남청주청주#2T/L GIS 대체","2025-04-04 14:00","2025-04-13 14:00","2025-04-04 14:00","2025-04-13 14:00","연속"]
[428,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62SEC GIS 대체","2025-04-02 14:00","2025-04-04 18:00","취소","취소","연속"]
[429,"충북","청주","옥천보은 T/L","2024~2025년 송전정비 협력회사 총액공사"," 보은분기T/L 추락방지장치 설치(수평설치) 1. 내용 :  옥천-보은T/L 수평 추락방지장치 설치 2. 구간 :  옥천-보은T/L 1~29호","2025-04-21 08:00","2025-05-02 18:00","2025-04-21 08:00","2025-05-02 18:00","매일"]
[430,"충북","청주","화동보은 T/L","2024~2025년 송전정비 협력회사 총액공사"," 보은분기T/L 추락방지장치 설치(수평설치) 1. 내용 :  화동-보은T/L 수평 추락방지장치 설치 2. 구간 :  화동-보은T/L 25~29호","2025-04-17 08:00","2025-04-18 18:00","2025-04-17 08:00","2025-04-18 18:00","매일"]
[431,"충북","청주","사직북청주#2 T/L","2025년 청주전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-04-28 09:00","2025-04-30 18:00","2025-04-28 09:00","2025-04-30 18:00","연속"]
[432,"충북","청주","서청주사직#1 T/L"," 서청주-사직T/L 대한전선製 열경화공법 EBG 보강공사","EBG 가스채취 밸브 설치 및 스프링 유니트 점검을 통한 고장예방","2025-04-28 09:00","2025-04-30 18:00","2025-04-28 09:00","2025-04-30 18:00","연속"]
[433,"충북","청주","서청주사직#2 T/L","2025년 청주전력지사 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-04-21 09:00","2025-04-23 18:00","2025-04-21 09:00","2025-04-23 18:00","연속"]
[434,"충북","청주","신옥천S/S SEC CB 60610","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-04-17 10:00","2025-04-17 18:00","2025-04-17 10:00","2025-04-17 18:00","연속"]
[435,"충북","청주","신옥천옥천#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-04-16 10:00","2025-04-16 18:00","2025-04-16 10:00","2025-04-16 18:00","연속"]
[436,"충북","청주","신옥천옥천#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-04-15 10:00","2025-04-15 18:00","2025-04-15 10:00","2025-04-15 18:00","연속"]
[437,"충북","청주","신옥천유천 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-04-10 10:00","2025-04-10 18:00","2025-04-10 10:00","2025-04-10 18:00","연속"]
[438,"충북","청주","신옥천서대전 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-04-09 10:00","2025-04-09 18:00","2025-04-09 10:00","2025-04-09 18:00","연속"]
[439,"충북","청주","신옥천추부#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-04-08 10:00","2025-04-08 18:00","2025-04-08 10:00","2025-04-08 18:00","연속"]
[440,"충북","청주","신옥천S/S SEC CB 66670","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-04-24 10:00","2025-04-24 18:00","2025-04-24 10:00","2025-04-24 18:00","연속"]
[441,"충북","청주","신옥천S/S SEC CB 65660","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-04-23 10:00","2025-04-23 18:00","2025-04-23 10:00","2025-04-23 18:00","연속"]
[442,"충북","청주","신옥천S/S SEC CB 61620","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-04-22 10:00","2025-04-22 18:00","2025-04-22 10:00","2025-04-22 18:00","연속"]
[443,"충북","청주","화동영동 T/L","2024~2025년 송전정비 협력회사 총액공사"," 화동-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 화동-영동T/L 수평 추락방지장치 설치 2. 구간 :  화동-영동T/L 60~110호  영동분기T/L 1~61호","2025-04-07 08:00","2025-04-16 18:00","2025-04-07 08:00","2025-04-16 18:00","매일"]
[444,"충북","청주","초정청주#1 T/L"," 초정-청주 등 2개T/L 추락방지장치 및 피뢰기 설치 공사"," 초정-청주 및  사리-초정T/L 수직,수평 추락방지장치 설치 및 피뢰기설치 아킹혼 철거 시행","2025-04-24 07:00","2025-04-30 18:00","2025-04-24 07:00","2025-04-30 18:00","연속"]
[445,"충북","청주","초정청주#2 T/L"," 초정-청주 등 2개T/L 추락방지장치 및 피뢰기 설치 공사"," 초정-청주 및  사리-초정T/L 수직,수평 추락방지장치 설치 및 피뢰기설치 아킹혼 철거 시행","2025-04-07 07:00","2025-04-16 18:00","2025-04-07 07:00","2025-04-16 18:00","연속"]
[446,"충북","청주","사리초정#1 T/L"," 초정-청주 등 2개T/L 추락방지장치 및 피뢰기 설치 공사"," 초정-청주 및  사리-초정T/L 수직,수평 추락방지장치 설치 및 피뢰기설치 아킹혼 철거 시행","2025-04-14 07:00","2025-04-18 18:00","2025-04-15 07:00","2025-04-19 18:00","연속"]
[447,"충북","청주","사리초정#2 T/L"," 초정-청주 등 2개T/L 추락방지장치 및 피뢰기 설치 공사"," 초정-청주 및  사리-초정T/L 수직,수평 추락방지장치 설치 및 피뢰기설치 아킹혼 철거 시행","2025-04-21 07:00","2025-04-30 18:00","2025-04-21 07:00","2025-04-30 18:00","연속"]
[448,"충북","충주","금왕남음성#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기)","2025-04-08 07:30","2025-04-10 12:00","2025-04-08 07:30","2025-04-10 12:00","매일"]
[449,"충북","충주","금왕남음성#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기), 피뢰기 설치(25기)","2025-04-03 07:30","2025-04-07 18:00","2025-04-03 07:30","2025-04-07 18:00","매일"]
[450,"충북","충주","단양영월CC#1 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 수평추락방지장치 설치( 단양-영월CC#1 T/L No.1~1-4,2~75) 및 폴리머지지애자 교체(No.1.3,1.4,19,41,50,51,58,66) 시행","2025-04-21 07:00","2025-04-29 18:00","2025-04-21 07:00","2025-04-29 18:00","매일"]
[451,"충북","충주","신제천남원주#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.1-37)","2025-04-19 07:00","2025-04-20 16:00","2025-04-19 07:00","2025-04-20 16:00","매일"]
[452,"충북","충주","신제천남원주#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치(No.1-37)","2025-04-26 07:00","2025-04-27 16:00","2025-04-26 07:00","2025-04-27 16:00","매일"]
[453,"충북","충주","신제천영월CC#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 수평추락방지장치 설치( 신제천-영월CC#2 T/L No.15,20,26,27,35~75) 및 폴리머지지애자 설치(26,35,59,62,74) 시행","2025-04-30 07:00","2025-05-13 18:00","2025-04-30 07:00","2025-05-13 18:00","매일"]
[454,"충북","충주","신제천제천#1 T/L","24-25년 충주전력지사 변전협력회사 총액공사","신제천S/S  신제천-제천 #1T/L GIS 보통점검","2025-04-15 10:00","2025-04-15 15:00","2025-04-15 10:00","2025-04-15 15:00","연속"]
[455,"충북","충주","신제천주진#2 T/L","24-25년 충주전력지사 변전협력회사 총액공사","신제천S/S 신제천-주진 #2T/L GIS 보통점검","2025-04-16 10:00","2025-04-16 15:00","2025-04-16 10:00","2025-04-16 15:00","연속"]
[456,"충북","충주","신충주북충주#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.26-69)","2025-04-04 07:00","2025-04-09 16:00","2025-04-04 07:00","2025-04-10 16:00","매일"]
[457,"충북","충주","신충주음성#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","피뢰기 설치(7기), 애자교체(4기), SB댐퍼 설치(2기)","2025-04-01 07:30","2025-04-02 18:00","2025-04-01 07:30","2025-04-02 18:00","매일"]
[458,"충북","충주","신충주감곡#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","상간스페이서 설치(1경간)","2025-04-10 13:00","2025-04-10 18:00","2025-04-10 13:00","2025-04-10 18:00","연속"]
[459,"충북","충주","신충주감곡#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","상간스페이서 설치(1경간)","2025-04-11 07:30","2025-04-11 18:00","2025-04-11 07:30","2025-04-11 18:00","연속"]
[460,"충북","충주","신충주북충주#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.23-25, 58-64, 74-81)","2025-04-12 07:00","2025-04-13 16:00","2025-04-12 07:00","2025-04-13 16:00","매일"]
[461,"충북","충주","신충주북충주#2 T/L","안전한국훈련 임시복구 시범훈련","고장선로 임시복구 훈련(시연)","2025-04-29 09:00","2025-04-30 18:00","2025-04-29 09:00","2025-04-30 18:00","매일"]
[462,"충북","충주","왕암여주#2 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치(No.26-69)","2025-04-04 07:00","2025-04-10 16:00","2025-04-04 07:00","2025-04-10 16:00","매일"]
[463,"충북","충주","왕암여주#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치공사 (No.121-125, 127, 128, 131)","2025-04-11 07:00","2025-04-13 16:00","2025-04-11 07:00","2025-04-13 16:00","매일"]
[464,"충북","충주","음성금왕#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기), 아킹혼 철거(1기)","2025-04-08 07:30","2025-04-10 12:00","2025-04-08 07:30","2025-04-10 12:00","매일"]
[465,"충북","충주","음성금왕#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기), 피뢰기 설치(32기), 애자교체(1기)","2025-04-01 07:30","2025-04-07 18:00","2025-04-01 07:30","2025-04-07 18:00","매일"]
[466,"충북","충주","제천영월#1 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 병가구간으로 인한 안전확보( 단양-영월CC#1 및  신제천-영월CC#2)","2025-04-29 07:00","2025-04-30 18:00","2025-04-29 07:00","2025-04-30 18:00","매일"]
[467,"충북","충주","충주충주HP#1 T/L"," 충주-충주HP T/L 전선접속개소 교체공사"," 충주-충주HP #1 No.9~16 전선전속개소교체공사","2025-04-22 09:00","2025-05-03 18:00","취소","취소","연속"]
[468,"충북","충주","왕암충주 T/L"," 충주-충주HP T/L 전선접속개소 교체공사"," 충주-충주HP #1 No.9~16 전선전속개소교체공사 안전확보를 위한 병가구간 휴전","2025-04-22 09:00","2025-05-03 18:00","취소","취소","매일"]
[469,"충북","충주","풍동장연 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치(No.64-75)","2025-04-01 07:00","2025-04-03 16:00","2025-04-01 07:00","2025-04-03 16:00","매일"]
[470,"충북","충주","풍동음성#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.64-75)","2025-04-01 07:00","2025-04-03 16:00","2025-04-01 07:00","2025-04-03 16:00","매일"]
[471,"대전세종충남","대전","부여논산#1 T/L","[취소시][가압X]논산S/S 부여-논산#1T/L GIS 정밀점검","[취소시][가압X]논산S/S 부여-논산#1T/L GIS 정밀점검","2025-04-14 09:00","2025-04-15 18:00","2025-04-14 09:00","2025-04-15 18:00","연속"]
[472,"대전세종충남","대전","부여논산#2 T/L","[취소시][가압X]논산S/S 부여논산#1T/L GIS 정밀점검","[취소시][가압X]논산S/S 부여논산#1T/L GIS 정밀점검","2025-04-16 09:00","2025-04-17 18:00","2025-04-16 09:00","2025-04-17 18:00","연속"]
[473,"대전세종충남","대전","신계룡두마#1 T/L","[가압X]두마S/S  신계룡두마#1 T/L 송전선로 보호반 대체","[가압X]두마S/S  신계룡두마#1 T/L 송전선로 보호반 대체","2025-04-01 09:00","2025-04-04 18:00","취소","취소","연속"]
[474,"대전세종충남","대전","신계룡두마#2 T/L","[가압X]두마S/S  신계룡두마#2 T/L 송전선로 보호반 대체","[가압X]두마S/S  신계룡두마#2 T/L 송전선로 보호반 대체","2025-04-09 09:00","2025-04-11 18:00","취소","취소","연속"]
[475,"대전세종충남","대전","신옥천용운#2 T/L","[즉시가압O]용운S/S  신옥천-용운#2T/L GIS 보통점검","[즉시가압O]용운S/S  신옥천-용운#2T/L GIS 보통점검","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","당일"]
[476,"대전세종충남","대전","신옥천용운#1 T/L","[즉시가압O]용운S/S 신옥천-용운#1T/L GIS 보통점검","[즉시가압O]용운S/S 신옥천-용운#1T/L GIS 보통점검","2025-04-07 09:00","2025-04-07 18:00","2025-04-07 09:00","2025-04-07 18:00","당일"]
[477,"대전세종충남","대전","신옥천추부#1 T/L","[송전][즉시가압O]신옥천-청양 등 8개T/L 추락방지설치공사","[송전][주말작업제외][즉시가압O][태양광부하 과다시 가압]345kV 신옥천-청양 등 8개 T/L 추락방지 설치공사","2025-04-14 14:00","2025-04-18 12:00","취소","취소","매일"]
[478,"대전세종충남","서산","석문당진화력#2 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [서산송전] 철탑 정밀점검 (김성현대리)","2025-04-16 12:00","2025-04-18 18:00","취소","취소","연속"]
[479,"대전세종충남","서산","석문당진화력#1 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [서산송전] 철탑 정밀점검 (김성현대리)","2025-04-14 09:00","2025-04-16 12:00","취소","취소","연속"]
[480,"대전세종충남","서산","대산석문#1 T/L","'25년도 가공송전 순시점검 위탁공사"," 대산-석문#1T/L 정밀점검 No.1~4, 7~48 [비상시 20분 이내 즉시가압가능] [병가철탑](상단) 석문-당진화력#2 No.1,(하단) 대산-석문#1T/L No.48","2025-04-18 07:30","2025-04-22 17:00","2025-04-18 07:30","2025-04-22 17:00","매일"]
[481,"대전세종충남","서산","대산석문#2 T/L","'25년도 가공송전 순시점검 위탁공사"," 대산-석문#2T/L 정밀점검 No.1~4, 7~48 [비상시 20분 이내 즉시가압가능] [병가철탑](상단) 석문-당진화력#1 No.1,(하단) 대산-석문#2T/L No.48","2025-04-08 07:30","2025-04-14 17:00","2025-04-08 07:30","2025-04-14 17:00","매일"]
[482,"대전세종충남","서산","서산대산#4 T/L"," 신성연-태안T/L 계통변경 외 1개 T/L 건설공사"," 서산-대산#3,4T/L No.14-1 임시선로 구성","2025-04-23 09:00","2025-04-27 18:00","2025-04-23 09:00","2025-04-27 18:00","연속"]
[483,"대전세종충남","서산","서산대산#3 T/L"," 신성연-태안T/L 계통변경 외 1개 T/L 건설공사"," 서산-대산#3,4T/L No.14-1 임시선로 구성","2025-04-28 09:00","2025-05-02 18:00","2025-04-28 09:00","2025-05-02 18:00","연속"]
[484,"대전세종충남","서산","서산성연 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 성연S/S  서산-성연T/L LA 하자점검","2025-04-04 09:30","2025-04-04 18:00","2025-04-04 09:30","2025-04-04 18:00","당일"]
[485,"대전세종충남","서산","당진송악#1 T/L","25년 서산P/O  이하 정밀,보통점검공사","(3월 휴전 취소시)(즉시가압불가) 송악S/S  당진-송악#1T/L GIS 정밀점검","2025-04-21 09:30","2025-04-23 14:00","2025-04-21 09:30","2025-04-23 14:00","연속"]
[486,"대전세종충남","서산","당진송악#2 T/L","25년 서산P/O  이하 정밀,보통점검공사","(3월 휴전 취소시)(즉시가압불가) 송악S/S  당진-송악#2T/L GIS 정밀점검","2025-04-23 14:00","2025-04-25 18:00","2025-04-23 14:00","2025-04-25 18:00","연속"]
[487,"대전세종충남","서산","합덕송악#2 T/L","25년 서산P/O  이하 정밀,보통점검공사","(3월 휴전 취소시)(즉시가압가능) 합덕S/S  합덕-송악#2T/L GIS 보통점검","2025-04-03 09:30","2025-04-03 18:00","2025-04-03 09:30","2025-04-03 18:00","연속"]
[488,"대전세종충남","서산","아산합덕#2 T/L","25년 서산P/O  이하 정밀,보통점검공사","(3월 휴전 취소시)(즉시가압가능) 합덕S/S  아산-합덕#2T/L GIS 보통점검","2025-04-02 09:30","2025-04-02 18:00","2025-04-02 09:30","2025-04-02 18:00","연속"]
[489,"대전세종충남","세종","세종둔곡#1 T/L","[즉시가압O]  세종-둔곡#1T/L 피뢰기 설치공사","[즉시가압O]  세종-둔곡#1T/L 피뢰기 설치공사","2025-04-24 07:00","2025-04-24 13:00","2025-04-24 07:00","2025-04-24 13:00","당일"]
[490,"대전세종충남","세종","세종둔곡#2 T/L","[즉시가압O]  세종-둔곡#2T/L 피뢰기 설치공사","[즉시가압O]  세종-둔곡#2T/L 피뢰기 설치공사","2025-04-24 13:00","2025-04-24 18:00","2025-04-24 13:00","2025-04-24 18:00","당일"]
[491,"대전세종충남","세종","세종둔곡#1 T/L","[즉시가압O]  세종-둔곡#1T/L 피뢰기 설치공사","[즉시가압O]  세종-둔곡#1T/L 피뢰기 설치공사","2025-04-22 07:00","2025-04-23 18:00","2025-04-22 07:00","2025-04-23 18:00","매일"]
[492,"대전세종충남","세종","세종부강#2 T/L","[즉시가압O][안전목적] 부강-신탄진T/L 피뢰기 공사","4회선 병가구간 철탑의 하단 선로의 안전목적상 휴전","2025-04-01 07:00","2025-04-02 18:00","2025-04-01 07:00","2025-04-02 18:00","매일"]
[493,"대전세종충남","세종","부강신탄진 T/L","[즉시가압O][주말작업X]  부강-신탄진T/L 피뢰기 설치공사","[즉시가압O][주말작업X]  부강-신탄진T/L 피뢰기 설치공사","2025-04-01 07:00","2025-04-08 18:00","2025-04-01 07:00","2025-04-08 18:00","매일"]
[494,"대전세종충남","세종","세종월산#1 T/L","[즉시가압X][주말작업X]  세종-월산T/L 불량애자 교체공사","[즉시가압X][주말작업X]  세종-월산T/L 불량애자 교체공사","2025-04-11 07:00","2025-04-15 18:00","취소","취소","매일"]
[495,"대전세종충남","세종","세종월산#2 T/L","[즉시가압X]  세종-월산T/L 불량애자 교체공사","[즉시가압X]  세종-월산T/L 불량애자 교체공사","2025-04-16 07:00","2025-04-17 18:00","취소","취소","매일"]
[496,"대전세종충남","세종","조치원전의#1 T/L","[송전] 조치원-전의T/L 안전이격 및 전력선 교체공사","○  조치원-전의T/L 안전이격 및 전력선 교체공사 - 지지물 교체 : No.25,33,34 - 용량증대 전선교체 : 조치원S/S~전의S/S","2025-04-23 07:00","2025-05-16 18:00","2025-04-23 07:00","2025-05-16 18:00","연속"]
[497,"대전세종충남","세종","천안전의#1 T/L","[즉시가압O][안전목적]  북오송-전의T/L 불량애자 교체","[즉시가압O][안전목적]  북오송-전의T/L 불량애자 교체 - 4회선 병가구간에 의한 안전목적상 휴전","2025-04-17 07:00","2025-04-17 13:00","취소","취소","당일"]
[498,"대전세종충남","세종","조치원전의#2 T/L"," 조치원-전의T/L 안전이격 및 전력선 교체공사","○ 전력선 교체 : ASCC/TW 11.268km","2025-04-28 07:00","2025-05-12 18:00","2025-04-28 07:00","2025-05-12 18:00","연속"]
[499,"대전세종충남","세종","천안전의#2 T/L","[즉시가압O][안전목적]  북오송-전의T/L 불량애자 교체","[즉시가압O][안전목적]  북오송-전의T/L 불량애자 교체 - 4회선 병가구간에 의한 안전목적상 휴전","2025-04-17 13:00","2025-04-17 18:00","취소","취소","당일"]
[500,"대전세종충남","직할","덕진대화#2 T/L"," 덕진-대화T/L 지장수목 전지 및 벌채"," 덕진-대화T/L No.11-12 지장수목 전지 및 벌채(고속도로 횡단개소)","2025-04-03 13:00","2025-04-03 18:00","2025-04-14T13:00:00","2025-04-14T18:00:00","당일"]
[501,"대전세종충남","직할","덕진대화#1 T/L"," 덕진-대화T/L 지장수목 전지 및 벌채"," 덕진-대화T/L No.11-12 지장수목 전지 및 벌채(고속도로 횡단개소)","2025-04-03 08:00","2025-04-03 13:00","2025-04-14T08:00:00","2025-04-14T13:00:00","당일"]
[502,"대전세종충남","직할","송강신일#2 T/L","송강,신일S/S 송강-신일#2T/L 보호반 대체공사","□ 송강,신일S/S 송강-신일#2T/L 송전선로 보호반 대체 □ (병행)송강S/S 송강-신일#2T/L GIS 보통점검 □ (병행)송강,신일S/S 송강-신일#2T/L PITR 교체공사","2025-04-18 08:00","2025-04-20 18:00","취소","취소","연속"]
[503,"대전세종충남","직할","둔곡송강#2 T/L"," 둔곡-송강T/L 지장수목전지 및 벌채"," 둔곡-송강#2T/L 지장수목전지 및 벌채","2025-04-11 09:00","2025-04-11 18:00","취소","취소","매일"]
[504,"대전세종충남","직할","둔곡송강#1 T/L"," 둔곡-송강T/L 지장수목전지 및 벌채"," 둔곡-송강#1T/L 지장수목전지 및 벌채","2025-04-09 09:00","2025-04-10 18:00","취소","취소","매일"]
[505,"대전세종충남","천안","서천안탕정#2 T/L","[3월취소시] 서천안-탕정T/L 추락방지장치 설치공사","[즉시가압가능] 서천안-탕정T/L No. 3 ~ 23 추락방지장치 설치 [병행작업] 항공장애표시구 설치공사 (7경간)","2025-04-26 07:00","2025-04-27 18:00","2025-04-26 07:00","2025-04-27 18:00","매일"]
[506,"대전세종충남","천안","서천안탕정#1 T/L","[3월취소시] 서천안-탕정T/L 추락방지장치 설치공사","[즉시가압가능] 서천안-탕정T/L No. 3 ~ 23 추락방지장치 설치 [병행작업] 항공장애표시구 설치공사 (7경간)","2025-04-05 07:00","2025-04-06 18:00","2025-04-05 07:00","2025-04-06 18:00","매일"]
[507,"대전세종충남","천안","신탕정S/S #61 BUS"," 신탕정-탕정 SW증설 및 삼성디스플레이T/L 신규수용 공사"," 신탕정-탕정 SW증설 및 삼성디스플레이T/L 신규수용 공사","2025-04-03 14:00","2025-04-05 14:00","2025-04-03 14:00","2025-04-05 14:00","연속"]
[508,"대전세종충남","천안","신탕정S/S CB 6200"," 신탕정-탕정 SW증설 및 삼성디스플레이T/L 신규수용 공사"," 신탕정-탕정 SW증설 및 삼성디스플레이T/L 신규수용 공사","2025-04-02 14:00","2025-04-03 14:00","2025-04-02 14:00","2025-04-03 14:00","연속"]
[509,"대전세종충남","천안","신탕정S/S #66 BUS"," 신탕정-탕정 SW증설 및 삼성디스플레이T/L 신규수용 공사"," 신탕정-탕정 SW증설 및 삼성디스플레이T/L 신규수용 공사","2025-04-01 09:00","2025-04-03 14:00","2025-04-01 09:00","2025-04-03 14:00","연속"]
[510,"대전세종충남","천안","신탕정S/S SEC CB 60610","(3월 취소시)신탕정S/S  #60-65BUS 노후 PNL 대체","(즉시가압불가)신탕정S/S  #60-65BUS 노후 보호배전반 대체","2025-04-28 09:00","2025-05-02 18:00","2025-04-28 09:00","2025-05-02 18:00","연속"]
[511,"대전세종충남","천안","신탕정S/S CB 6100","(3월 취소시)신탕정S/S  #60-65BUS 노후 PNL 대체","(즉시가압불가)신탕정S/S  #60-65BUS 노후 보호배전반 대체","2025-04-28 09:00","2025-05-02 18:00","2025-04-28 09:00","2025-05-02 18:00","연속"]
[512,"대전세종충남","천안","신탕정S/S CB 6200"," 신탕정-탕정 SW증설 및 삼성디스플레이T/L 신규수용 공사"," 신탕정-탕정 SW증설 및 삼성디스플레이T/L 신규수용 공사","2025-04-04 14:00","2025-04-05 14:00","2025-04-04 14:00","2025-04-05 14:00","연속"]
[513,"대전세종충남","천안","아산예산#1 T/L"," 아산-예산T/L 추락방지장치 설치공사","[즉시가압가능] 아산-예산T/L No. 1 ~ 42 추락방지장치 설치 [병가철탑] (상단)아산-온양#2T/L No.2~14 / (하단)아산-예산#1T/L No.1~13","2025-04-12 07:00","2025-04-16 18:00","취소","취소","매일"]
[514,"대전세종충남","천안","아산온양#1 T/L"," 아산-예산T/L 추락방지장치 설치공사(4회선구간)","[즉시가압가능] 아산-예산T/L No. 1 ~ 42 추락방지장치 설치 [병가철탑] (상단)아산-온양#2T/L No.2~14 / (하단)아산-예산#1T/L No.1~13","2025-04-19 07:00","2025-04-20 18:00","취소","취소","매일"]
[515,"대전세종충남","천안","아산S/S SEC CB 65660","(3월 취소시) 아산S/S  65-66 GIS PD 센서 교체","(즉시가압불가)아산S/S  65-66-0 GIS 불량 PD 센서 교체","2025-04-15 09:00","2025-04-16 18:00","2025-04-15 09:00","2025-04-16 18:00","연속"]
[516,"대전세종충남","천안","아산예산#2 T/L"," 아산-예산T/L 추락방지장치 설치공사","[즉시가압가능] 아산-예산T/L No. 1 ~ 42 추락방지장치 설치 [병가철탑] (상단)아산-온양#2T/L No.2~14 / (하단)아산-예산#1T/L No.1~13","2025-04-17 07:00","2025-04-21 18:00","취소","취소","매일"]
[517,"대전세종충남","천안","아산온양#2 T/L"," 아산-예산T/L 추락방지장치 설치공사(4회선구간)","[즉시가압가능] 아산-예산T/L No. 1 ~ 42 추락방지장치 설치 [병가철탑] (상단)아산-온양#2T/L No.2~14 / (하단)아산-예산#1T/L No.1~13","2025-04-12 07:00","2025-04-13 18:00","취소","취소","매일"]
[518,"대전세종충남","천안","아산S/S #66 BUS","(3월 취소시) 아산S/S  65-66 GIS PD 센서 교체","(즉시가압불가)아산S/S  65-66-0 GIS 불량 PD 센서 교체","2025-04-15 09:00","2025-04-16 18:00","2025-04-15 09:00","2025-04-16 18:00","연속"]
[519,"대전세종충남","천안","아산예산#2 T/L"," 아산-예산#2T/L 노후 보호배전반 대체(장기미교체 대상)"," 아산-예산#2T/L 노후 보호배전반 대체(장기미교체 대상)","2025-04-17 09:00","2025-04-21 18:00","2025-04-17 09:00","2025-04-21 18:00","연속"]
[520,"대전세종충남","천안","아산인주#1 T/L","(3월 취소시)인주S/S 아산-인주#1T/L CB 개폐타임 측정","(즉시가압가능)인주S/S  아산-인주#1T/L CB 개폐타임 측정","2025-04-25 14:00","2025-04-25 20:00","취소","취소","당일"]
[521,"대전세종충남","천안","아산인주#2 T/L","(3월 취소시)인주S/S 아산-인주#2T/L CB 개폐타임 측정","(즉시가압가능)인주S/S  아산-인주#2T/L CB 개폐타임 측정","2025-04-25 09:00","2025-04-25 14:00","취소","취소","당일"]
[522,"대전세종충남","천안","장재천안#2 T/L"," 장재-천안T/L 추락방지장치 설치공사(4회선)","[즉시가압가능] 장재-천안T/L No. 1 ~ 14 추락방지장치 설치 [병가철탑](상단)풍세-장재 No.18~23,(하단) 장재-천안 No.4~14","2025-04-22 07:00","2025-04-22 18:00","2025-04-22 07:00","2025-04-22 18:00","매일"]
[523,"대전세종충남","천안","풍세장재#1 T/L"," 장재-천안T/L 추락방지장치 설치공사(4회선)","[즉시가압가능] 장재-천안T/L No. 1 ~ 14 추락방지장치 설치 [병가철탑](상단)풍세-장재 No.18~23,(하단) 장재-천안 No.4~14","2025-04-22 07:00","2025-04-22 18:00","2025-04-22 07:00","2025-04-22 18:00","당일"]
[524,"대전세종충남","천안","풍세장재#2 T/L"," 장재-천안T/L 추락방지장치 설치공사(4회선)","[즉시가압가능] 장재-천안T/L No. 1 ~ 14 추락방지장치 설치 [병가철탑](상단)풍세-장재 No.18~23,(하단) 장재-천안 No.4~14","2025-04-23 07:00","2025-04-24 18:00","2025-04-23 07:00","2025-04-24 18:00","매일"]
[525,"대전세종충남","천안","장재천안#1 T/L"," 장재-천안T/L 추락방지장치 설치공사(4회선)","[즉시가압가능] 장재-천안T/L No. 1 ~ 14 추락방지장치 설치 [병가철탑](상단)풍세-장재 No.18~23,(하단) 장재-천안 No.4~14","2025-04-23 07:00","2025-04-24 18:00","2025-04-23 07:00","2025-04-24 18:00","매일"]
[526,"대전세종충남","천안","한샘직산#2 T/L","(3월 취소시)  한샘-직산#2T/L GIS 보통점검","한샘, 직산S/S  한샘-직산#2T/L GIS 보통점검","2025-04-23 09:00","2025-04-24 18:00","2025-04-23 09:00","2025-04-24 18:00","연속"]
[527,"대전세종충남","천안","한샘직산#1 T/L","(3월 취소시)  한샘-직산#1T/L GIS 보통점검","한샘, 직산S/S  한샘-직산#1T/L GIS 보통점검","2025-04-21 09:00","2025-04-22 18:00","2025-04-21 09:00","2025-04-22 18:00","연속"]
[528,"대전세종충남","청양","관창보령TP T/L","청양P/O 변전협력 총액공사(관창 관창-보령화력TL 조작)","청양P/O 변전협력 총액공사(관창-보령화력 조작시험) 관창S/S 관창-보령화력 휴전 - 보령화력 측 GIS 조작시험 병행 - 즉시가압 가능","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","당일"]
[529,"대전세종충남","청양","신서천대천#1 T/L","청양P/O 변전협력 총액공사(서천 대천서천#1 보통)","서천SS 대천-서천#1T/L GIS 보통점검","2025-04-14 09:00","2025-04-14 18:00","2025-04-14 09:00","2025-04-14 18:00","당일"]
[530,"대전세종충남","청양","신서천대천#2 T/L","청양P/O 변전협력 총액공사(서천 대천서천#2 보통)","서천SS 대천-서천#2T/L GIS 보통점검","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","당일"]
[531,"대전세종충남","청양","옥산장항#2 T/L","청양P/O 변전 발주공사(옥산 옥장#2 정밀)","청양P/O 변전 발주공사(옥산 옥부#2 정밀) - 즉시가압 불가","2025-04-07 09:00","2025-04-09 18:00","취소","취소","연속"]
[532,"대전세종충남","청양","옥산부여#1 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-04-28 09:00","2025-05-02 18:00","2025-04-28 09:00","2025-05-02 18:00","연속"]
[533,"대전세종충남","청양","옥산부여#2 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-04-21 09:00","2025-04-25 18:00","2025-04-21 09:00","2025-04-25 18:00","연속"]
[534,"대전세종충남","청양","은하홍성#1 T/L"," 은하-홍성#1T/L 정밀점검","은하S/S - 홍성S/S 간 철탑 48기, 전력선 49경간 철탑,전력선,애자금구류 등 승탑점검","2025-04-21 07:00","2025-04-24 18:00","취소","취소","매일"]
[535,"대전세종충남","청양","은하홍성#2 T/L"," 은하-홍성#2T/L 정밀점검 및 보호배전반교체","은하S/S - 홍성S/S 간 철탑 48기, 전력선 49경간 철탑,전력선,애자금구류 등 승탑점검","2025-04-25 07:00","2025-04-30 18:00","2025-04-25 07:00","2025-04-30 18:00","매일"]
[536,"대전세종충남","청양","청양은하#1 T/L"," 청양-은하#1T/L 정밀점검","청양S/S - 은하S/S 간 철탑 62기, 전력선 63경간 철탑,전력선,애자금구류 등 승탑점검","2025-04-07 07:00","2025-04-11 18:00","2025-04-07 07:00","2025-04-11 18:00","매일"]
[537,"대전세종충남","청양","청양관창#2 T/L","청양P/O 변전협력 총액공사(청양 청관#2 보통)","청양P/O 변전협력 총액공사(청양 청관#2 보통) 청양S/S 청양-관창#2 휴전 - 170kV GIS 보통점검 - 관창 측 GIS 조작시험 병행 - 즉시가압 가능","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","당일"]
[538,"대전세종충남","청양","청양은하#2 T/L"," 청양-은하#2T/L 정밀점검","청양S/S - 은하S/S 간 철탑 62기, 전력선 63경간 철탑,전력선,애자금구류 등 승탑점검","2025-04-14 07:00","2025-04-18 18:00","취소","취소","매일"]
[539,"대전세종충남","청양","청양관창#1 T/L","청양P/O 변전협력 총액공사(청양 청관#1 보통)","청양P/O 변전협력 총액공사(청양 청관#1 보통) 청양S/S 청양-관창#1 휴전 - 170kV GIS 보통점검 - 관창 측 GIS 조작시험 병행 - 즉시가압 가능","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","당일"]
[540,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-04-28 09:00","2025-04-29 18:00","취소","취소","연속"]
[541,"전북","군산","군산이리#1 T/L","군산P/O 이상 차단기 점검공사","군산P/O 이상 차단기 점검공사","2025-04-10 09:00","2025-04-10 18:00","취소","취소","당일"]
[542,"전북","군산","군산영등#2 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-04-14 07:00","2025-04-18 18:00","취소","취소","연속"]
[543,"전북","군산","군산이리#2 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-04-14 07:00","2025-04-18 18:00","취소","취소","연속"]
[544,"전북","군산","군산서군산#1 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-04-24 09:00","2025-04-25 18:00","취소","취소","연속"]
[545,"전북","군산","내초군장#1 T/L","노후배전반 대체공사","노후배전반 대체공사","2025-04-08 09:00","2025-04-10 18:00","2025-04-08 09:00","2025-04-10 18:00","연속"]
[546,"전북","군산","내초군장#2 T/L","노후배전반 대체공사","노후배전반 대체공사","2025-04-15 09:00","2025-04-17 18:00","2025-04-15 09:00","2025-04-17 18:00","연속"]
[547,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사(중복)","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2025-04-21 09:00","2025-04-23 18:00","취소","취소","연속"]
[548,"전북","군산","서군산소룡#1 T/L","군산P/O 이상 차단기 점검공사","군산P/O 이상 차단기 점검공사","2025-04-01 09:00","2025-04-01 18:00","취소","취소","당일"]
[549,"전북","군산","서군산소룡#2 T/L","군산P/O 이상 차단기 점검공사","군산P/O 이상 차단기 점검공사","2025-04-02 09:00","2025-04-02 18:00","취소","취소","당일"]
[550,"전북","군산","팔봉두마#2 T/L","군산P/O  이상 차단기 보통점검공사","차단기 보통점검공사","2025-04-11 09:00","2025-04-11 18:00","2025-04-11 09:00","2025-04-11 18:00","당일"]
[551,"전북","군산","팔봉두마#1 T/L","군산P/O  이상 차단기 보통점검공사","차단기 보통점검공사","2025-04-04 09:00","2025-04-04 18:00","2025-04-04 09:00","2025-04-04 18:00","당일"]
[552,"전북","군산","은진함열#1 T/L","노후배전반 대체공사(중복)","노후배전반 대체공사","2025-04-21 09:00","2025-04-23 18:00","2025-04-21 09:00","2025-04-23 18:00","연속"]
[553,"전북","군산","은진함열#2 T/L","노후배전반 대체공사(중복)","노후배전반 대체공사","2025-04-28 09:00","2025-04-30 18:00","2025-04-28 09:00","2025-04-30 18:00","연속"]
[554,"전북","김제","고창영광 T/L","고창S/S 고창-영광T/L GIS 정밀점검(연속)","고창S/S 고창-영광T/L GIS 정밀점검 단로기포함(연속)","2025-04-28 09:00","2025-04-30 18:00","취소","취소","연속"]
[555,"전북","김제","고창홍농 T/L","고창S/S 고창-홍농T/L GIS 정밀점검(연속)","고창S/S 고창-홍농T/L GIS 정밀점검 단로기포함(연속)","2025-04-21 09:00","2025-04-23 18:00","취소","취소","연속"]
[556,"전북","김제","백산김제#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-04-03 08:00","2025-04-03 18:00","취소","취소","매일"]
[557,"전북","김제","백산김제#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-04-02 08:00","2025-04-02 18:00","취소","취소","매일"]
[558,"전북","김제","부안동부안#2 T/L","부안S/S  모선구분차단기 설치공사(무부하)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-04-26 15:00","2025-04-27 15:00","취소","취소","연속"]
[559,"전북","김제","부안동부안#1 T/L","부안S/S  모선구분차단기 설치공사(무부하)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-04-23 15:00","2025-04-24 15:00","취소","취소","연속"]
[560,"전북","김제","부안동부안#2 T/L","부안S/S  모선구분차단기 설치공사(무부하)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-04-20 15:00","2025-04-21 15:00","취소","취소","연속"]
[561,"전북","김제","부안동부안#1 T/L","부안S/S  모선구분차단기 설치공사(무부하)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-04-16 15:00","2025-04-17 15:00","취소","취소","연속"]
[562,"전북","김제","김제부안#2 T/L","부안S/S  모선구분차단기 설치공사","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-04-15 09:00","2025-04-21 18:00","취소","취소","연속"]
[563,"전북","김제","김제부안#1 T/L","부안S/S  모선구분차단기 설치공사","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-04-22 09:00","2025-04-27 18:00","취소","취소","연속"]
[564,"전북","김제","신김제동전주#1 T/L"," 완산분기T/L 건설공사","- 작업내용 : #1T/L 본선로 구성 및 C/T 조립 - 위 치 : 전주시 완산구 석구동 일원 - 규 모 : ACSR410㎟ × 2B × 4C (0.81km, 지지물 4기)","2025-04-28 07:00","2025-05-03 18:00","2025-04-28 07:00","2025-05-03 18:00","연속"]
[565,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","- 작업내용 : #2T/L 본선로 구성 - 위 치 : 전주시 완산구 석구동 일원 - 규 모 : ACSR410㎟ × 2B × 4C (0.81km, 지지물 4기)","2025-04-21 07:00","2025-04-26 18:00","2025-04-21 07:00","2025-04-26 18:00","연속"]
[566,"전북","김제","신김제전주#1 T/L","'25년 가공송전 순시점검 위탁공사"," 신김제-전주T/L 정밀점검","2025-04-28 09:00","2025-04-28 18:00","취소","취소","당일"]
[567,"전북","김제","신김제남전주#2 T/L","'25년 가공송전 순시점검 위탁공사"," 신김제-전주T/L 정밀점검","2025-04-28 09:00","2025-04-28 18:00","취소","취소","당일"]
[568,"전북","김제","신김제전주#2 T/L","'25년 가공송전 순시점검 위탁공사"," 신김제-전주T/L 정밀점검","2025-04-29 09:00","2025-04-29 18:00","취소","취소","당일"]
[569,"전북","김제","신김제남전주#1 T/L","'25년 가공송전 순시점검 위탁공사"," 신김제-전주T/L 정밀점검","2025-04-29 09:00","2025-04-29 18:00","취소","취소","당일"]
[570,"전북","김제","정공정주#1 T/L"," 정공-정주 등 3개T/L 추락방지장치 설치공사"," 정공-정주#1T/L No.0.1~13 추락방지장치 설치","2025-04-24 09:00","2025-04-25 18:00","취소","취소","연속"]
[571,"전북","김제","정공칠보HP T/L"," 정공-정주 등 3개T/L 추락방지장치 설치공사"," 정공분기(정공-칠보)T/L No.0.1~13 추락방지장치 설치","2025-04-24 09:00","2025-04-25 18:00","취소","취소","연속"]
[572,"전북","김제","정주동부안#1 T/L","정주S/S 정주-동부안#1T/L GIS 정밀점검(연속)","정주S/S 정주-동부안#1T/L GIS 정밀점검(연속)","2025-04-02 09:00","2025-04-03 18:00","2025-04-02 09:00","2025-04-03 18:00","연속"]
[573,"전북","직할","남원임실#2 T/L","남원S/S 남원-임실 #2T/L 보통점검","남원S/S 남원-임실 #2T/L 보통점검","2025-04-04 09:00","2025-04-04 18:00","2025-04-04 09:00","2025-04-04 18:00","당일"]
[574,"전북","직할","남원임실#1 T/L","남원S/S 남원-임실 #1T/L 보통점검","남원S/S 남원-임실 #1T/L 보통점검","2025-04-03 09:00","2025-04-03 18:00","2025-04-03 09:00","2025-04-03 18:00","당일"]
[575,"전북","직할","무주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.50~104","2025-04-05 07:30","2025-04-11 18:00","취소","취소","연속"]
[576,"전북","직할","왕궁봉동#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-04-09 08:00","2025-04-09 18:00","취소","취소","매일"]
[577,"전북","직할","왕궁봉동#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-04-10 08:00","2025-04-10 18:00","취소","취소","매일"]
[578,"전북","직할","북전주봉동#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-04-07 08:00","2025-04-07 18:00","취소","취소","매일"]
[579,"전북","직할","북전주봉동#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-04-08 08:00","2025-04-08 18:00","취소","취소","매일"]
[580,"전북","직할","북전주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.1~50","2025-04-01 07:30","2025-04-04 18:00","취소","취소","연속"]
[581,"전북","직할","북전주진안 T/L","북전주S/S 북전주-진안T/L LA(A,B,C상) 보통점검","북전주S/S 북전주-진안T/L LA(A,B,C상) 보통점검","2025-04-14 09:00","2025-04-14 18:00","취소","취소","당일"]
[582,"전북","직할","서곡태평#1 T/L","서곡S/S 태평-서곡 #1T/L GIS 보통점검","서곡S/S 태평-서곡 #1T/L GIS 보통점검","2025-04-15 09:00","2025-04-16 18:00","2025-04-15 09:00","2025-04-16 18:00","당일"]
[583,"전북","직할","서곡태평#2 T/L","서곡S/S 태평-서곡 #2T/L GIS 보통점검","서곡S/S 태평-서곡 #2T/L GIS 보통점검","2025-04-17 09:00","2025-04-18 18:00","2025-04-17 09:00","2025-04-18 18:00","당일"]
[584,"전북","직할","전주서곡#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-04-21 08:00","2025-04-22 18:00","취소","취소","매일"]
[585,"전북","직할","전주서곡#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-04-23 08:00","2025-04-24 18:00","취소","취소","매일"]
[586,"광주전남","강진","금정강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 설치공사"," 강진-장흥#2T/L No.1~59 피뢰기 설치 - 4회선 구간(2~9호) 작업 시  금정-강진#1T/L 병행휴전","2025-04-28 07:00","2025-04-29 18:00","취소","취소","매일"]
[587,"광주전남","강진","강진장흥#2 T/L"," 장흥-벌교 등 5개T/L 피뢰기 설치공사"," 강진-장흥#2T/L No.1~59 피뢰기 설치 (60기)","2025-04-28 07:00","2025-05-02 18:00","취소","취소","매일"]
[588,"광주전남","강진","나주금천#2 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#1T/L 정밀점검(안전이격확보)","2025-04-29 09:00","2025-05-02 18:00","2025-04-29 09:00","2025-05-02 18:00","매일"]
[589,"광주전남","강진","나주영암#1 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#1T/L 정밀점검","2025-04-23 09:00","2025-05-02 18:00","2025-04-23 09:00","2025-05-02 18:00","매일"]
[590,"광주전남","강진","나주엄다#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 피뢰기 설치 작업구간 : 신화순-나주#2T/L 65~72호[나주-엄다#2T/L 1~7호(병가)]","2025-04-08 07:00","2025-04-10 18:00","취소","취소","매일"]
[591,"광주전남","강진","나주엄다#2 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검","2025-04-04 10:00","2025-04-04 14:00","2025-04-04T17:00:00","2025-04-04T21:00:00","당일"]
[592,"광주전남","강진","나주금천#1 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검","2025-04-28 10:00","2025-04-28 14:00","2025-04-28T10:00:00","2025-04-28 14:00","당일"]
[593,"광주전남","강진","신강진해남#1 T/L","2025년 강진전력지사 효성제 170kV GIS 개선공사","2025년 강진전력지사 효성제 170kV GIS 개선공사 - 베어링 및 레치 신품 교체","2025-04-10 09:00","2025-04-10 14:00","취소","취소","당일"]
[594,"광주전남","강진","신강진해남#2 T/L","2025년 강진전력지사 효성제 170kV GIS 개선공사","2025년 강진전력지사 효성제 170kV GIS 개선공사 - 베어링 및 레치 신품 교체","2025-04-10 14:00","2025-04-10 18:00","취소","취소","당일"]
[595,"광주전남","강진","신강진대불#1 T/L","2025년 강진전력지사 효성제 170kV GIS 개선공사","2025년 강진전력지사 효성제 170kV GIS 개선공사 - 베어링 및 레치 신품 교체","2025-04-09 09:00","2025-04-09 14:00","취소","취소","당일"]
[596,"광주전남","강진","신강진대불#2 T/L","2025년 강진전력지사 효성제 170kV GIS 개선공사","2025년 강진전력지사 효성제 170kV GIS 개선공사 - 베어링 및 레치 신품 교체","2025-04-09 14:00","2025-04-09 18:00","취소","취소","당일"]
[597,"광주전남","강진","완도완도CS T/L"," 완도-완도C/S T/L 세니온제 보호계전기 임시점검"," 완도-완도C/S T/L 세니온제 보호계전기 성능개선 - 성능개선 요소 관련 계전기 개체시험, Trip Time 측정 및 연동시험(시험팀)","2025-04-01 09:00","2025-04-02 18:00","취소","취소","매일"]
[598,"광주전남","강진","장흥벌교 T/L"," 장흥-벌교 등 5개T/L 피뢰기 설치공사"," 강진-장흥#2T/L No.1~59 피뢰기 설치 - 4회선 구간(54~58호) 작업 시  장흥-벌교T/L 병행휴전","2025-04-30 07:00","2025-05-02 18:00","취소","취소","매일"]
[599,"광주전남","강진","해남해남CS#2 T/L","2024~2025년 강진전력지사 송전협력회사","철탑 추락방지장치 설치","2025-04-28 07:00","2025-05-02 18:00","취소","취소","매일"]
[600,"광주전남","강진","해남해남CS#1 T/L","2024~2025년 강진전력지사 송전협력회사","철탑 추락방지장치 설치","2025-04-21 07:00","2025-04-25 18:00","취소","취소","매일"]
[601,"광주전남","강진","화원안좌#2 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검","2025-04-08 14:00","2025-04-08 18:00","취소","취소","당일"]
[602,"광주전남","강진","화원진도#2 T/L","2025년 가공송전 순시점검 위탁공사","화원진도#2T/L 정밀점검(40~78호)","2025-04-09 09:00","2025-04-11 18:00","취소","취소","매일"]
[603,"광주전남","강진","화원안좌#1 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검","2025-04-08 10:00","2025-04-08 14:00","취소","취소","당일"]
[604,"광주전남","강진","화원진도#1 T/L","2025년 가공송전 순시점검 위탁공사","화원진도#1T/L 정밀점검(40~78호)","2025-04-02 09:00","2025-04-04 18:00","취소","취소","매일"]
[605,"광주전남","광주","계림승주#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 계림-승주#2T/L 조작시험","2025-04-23 14:00","2025-04-23 18:00","2025-04-23 14:00","2025-04-23 18:00","당일"]
[606,"광주전남","광주","계림승주#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 계림-승주#1T/L 조작시험","2025-04-23 09:00","2025-04-23 14:00","2025-04-23 09:00","2025-04-23 14:00","당일"]
[607,"광주전남","광주","북광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#2T/L 조작시험","2025-04-22 14:00","2025-04-22 18:00","취소","취소","당일"]
[608,"광주전남","광주","신광주계림#2 T/L","25년도 광주전력지사 변전협력회사 총액공사","신광주계림 #2T/L 보호반 대체 (신광주, 계림S/S)","2025-04-15 09:00","2025-04-17 18:00","취소","취소","연속"]
[609,"광주전남","광주","북광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#1T/L 조작시험","2025-04-22 09:00","2025-04-22 14:00","취소","취소","당일"]
[610,"광주전남","광주","곡성구례#1 T/L","2024~25년 광주전력지사 송전 협력회사공사(추락방지)"," 곡성-구례T/L 추락방지장치설치공사 No.1~120호","2025-04-01 07:00","2025-04-11 18:00","2025-04-01 07:00","2025-04-11 18:00","매일"]
[611,"광주전남","광주","곡성구례#2 T/L","2024~25년 광주전력지사 송전 협력회사공사(추락방지)"," 곡성-구례T/L 추락방지장치설치공사 No.1~120호","2025-04-14 07:00","2025-04-25 18:00","2025-04-14 07:00","2025-04-25 18:00","매일"]
[612,"광주전남","광주","신광주S/S CB 6100","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S #1 BUSTIE 보통점검","2025-04-02 09:00","2025-04-02 18:00","2025-04-02 09:00","2025-04-02 18:00","당일"]
[613,"광주전남","광주","신광주계림#1 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  신광주-계림#1T/L GIS 보통점검","2025-04-29 09:00","2025-04-29 18:00","취소","취소","당일"]
[614,"광주전남","광주","신광주일곡#1 T/L","2024~25년 광주전력지사 송전 협력회사공사(추락방지)"," 신광주-일곡T/L 추락방지장치설치공사 No.2~15호","2025-04-29 07:00","2025-04-29 18:00","2025-04-29 07:00","2025-04-29 18:00","당일"]
[615,"광주전남","광주","신광주계림#1 T/L","2024~25년 광주전력지사 송전 협력회사공사(추락방지)"," 신광주-계림T/L 추락방지장치설치공사 No.16~27.2호","2025-04-29 07:00","2025-04-29 18:00","취소","취소","당일"]
[616,"광주전남","광주","신광주일곡#2 T/L","2024~25년 광주전력지사 송전 협력회사공사(추락방지)"," 신광주-일곡T/L 추락방지장치설치공사 No.2~15호","2025-04-30 07:00","2025-04-30 18:00","2025-04-30 07:00","2025-04-30 18:00","당일"]
[617,"광주전남","광주","신광주S/S CB 6200","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S #2BUSTIE 보통점검","2025-04-03 09:00","2025-04-03 18:00","2025-04-03 09:00","2025-04-03 18:00","당일"]
[618,"광주전남","광주","신광주계림#2 T/L","2024~25년 광주전력지사 송전 협력회사공사(추락방지)"," 신광주-계림T/L 추락방지장치설치공사 No.16~27.2호","2025-04-30 07:00","2025-04-30 18:00","취소","취소","당일"]
[619,"광주전남","광주","신화순나주#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 피뢰기설치 작업구간 - 신화순-나주#2T/L 38호[남광주-금천#2T/L 75호(병가)] - 신화순-나주#2T/L 65~72호[나주-엄다#2T/L 1~7호(병가)]","2025-04-07 07:00","2025-04-10 18:00","취소","취소","매일"]
[620,"광주전남","광주","담양일곡#1 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 일곡S/S  담양-일곡#1T/L GIS 보통점검","2025-04-18 09:00","2025-04-18 18:00","2025-04-18 09:00","2025-04-18 18:00","당일"]
[621,"광주전남","광주","하남장성#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","장성S/S 하남-장성#1T/L 170kV GIS 조작시험","2025-04-14 09:00","2025-04-14 14:00","2025-04-14 09:00","2025-04-14 14:00","당일"]
[622,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 장성S/S  신광주-장성#2T/L GIS","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","당일"]
[623,"광주전남","광주","장성영광#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 장성S/S  장성-영광#2T/L GIS 보통점검","2025-04-25 09:00","2025-04-25 18:00","취소","취소","당일"]
[624,"광주전남","광주","하남장성#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","장성S/S 하남-장성#2T/L 170kV GIS 조작시험","2025-04-14 14:00","2025-04-14 18:00","2025-04-14 14:00","2025-04-14 18:00","당일"]
[625,"광주전남","광주","신광주장성#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","-신광주-장성#1T/L 170kV GIS 조작시험","2025-04-11 09:00","2025-04-11 14:00","2025-04-11 09:00","2025-04-11 14:00","당일"]
[626,"광주전남","광주","장성영광#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","장성S/S 장성-영광#1T/L 170kV GIS 조작시험","2025-04-11 14:00","2025-04-11 18:00","취소","취소","당일"]
[627,"광주전남","광주","계림충장#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 계림-충장#1T/L 170kV GIS 조작시험","2025-04-10 09:00","2025-04-10 18:00","취소","취소","당일"]
[628,"광주전남","광주","충장농성#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 충장-농성#1T/L 170kV GIS 조작시험","2025-04-08 09:00","2025-04-08 14:00","취소","취소","당일"]
[629,"광주전남","광주","충장농성#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 충장-농성#2T/L 170kV GIS 조작시험","2025-04-08 14:00","2025-04-08 18:00","취소","취소","당일"]
[630,"광주전남","광주","계림충장#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 계림-충장S/S #2T/L 170kV GIS 조작시험","2025-04-09 09:00","2025-04-09 14:00","취소","취소","당일"]
[631,"광주전남","광주","계림충장#3 T/L","2024~2025년 광주전력지사 변전협력회사 공사","충장S/S 계림-충장#3T/L 170kV GIS 조작시험","2025-04-09 14:00","2025-04-09 18:00","취소","취소","당일"]
[632,"광주전남","목포","엄다S/S CB 6100","엄다S/S  장기사용 GIS 교체공사","엄다-무안햇빛#2T/L 보호반 엔지니어링 시험","2025-04-01 09:00","2025-04-01 18:00","취소","취소","당일"]
[633,"광주전남","목포","엄다목포#2 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치 병가구간 휴전 및  엄다-목포T/L 피뢰기 설치","2025-04-11 08:00","2025-04-18 18:00","취소","취소","매일"]
[634,"광주전남","목포","나주엄다#1 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치(116기)","2025-04-07 08:00","2025-04-15 18:00","취소","취소","매일"]
[635,"광주전남","순천","광양백운#2 T/L","광양-백운 #2T/L 정밀점검","○ 광양-백운 #2T/L 정밀점검 - 광양S/S ~ 백운S/S , 총 20기","2025-04-24 09:00","2025-04-25 18:00","2025-04-24 09:00","2025-04-25 18:00","매일"]
[636,"광주전남","순천","광양백운#1 T/L","광양-백운 #1T/L 정밀점검","○ 광양-백운 #1T/L 정밀점검 - 광양S/S ~ 백운S/S , 총 20기","2025-04-22 09:00","2025-04-23 18:00","2025-04-22 09:00","2025-04-23 18:00","매일"]
[637,"광주전남","순천","소라서순천#1 T/L","2025년 순천전력지사 362,170kV GIS 정밀,보통점검공사","서순천S/S 소라-서순천#1T/L GIS 정밀점검","2025-04-16 09:00","2025-04-17 18:00","취소","취소","연속"]
[638,"광주전남","순천","소라서순천#2 T/L","2025년 순천전력지사 362,170kV GIS 정밀,보통점검공사","서순천S/S 소라-서순천#2T/L GIS 정밀점검","2025-04-21 09:00","2025-04-22 18:00","취소","취소","연속"]
[639,"광주전남","순천","승주서순천 T/L","2025년 순천전력지사 362,170kV GIS 정밀,보통점검공사","서순천S/S 승주-서순천T/L GIS 정밀점검","2025-04-23 09:00","2025-04-24 18:00","취소","취소","연속"]
[640,"광주전남","순천","승주주암HP T/L"," 승주-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치공사 ※주말(26,27일) 미작업","2025-04-25 07:00","2025-04-30 18:00","취소","취소","연속"]
[641,"광주전남","순천","승주서순천 T/L"," 승주-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치공사","2025-04-21 07:00","2025-04-24 18:00","취소","취소","연속"]
[642,"광주전남","순천","여수소라#1 T/L","여수S/S  이하 장기사용 GIS 교체(Digital화)공사","○ 여수S/S  장기사용 GIS 교체공사(1차) - 여천-여수#1T/L 교체 및 BUS SEC 증설 - 여수-소리#1,2T/L 제어케이블 LID 이설","2025-04-01 10:00","2025-04-02 18:00","2025-04-01T16:00:00","2025-04-02T10:00:00","연속"]
[643,"광주전남","순천","여수소라#2 T/L","여수S/S  GIS 교체공사 관련 안전이격휴전","○ 여수S/S  장기사용 GIS 교체공사(1차) - 안전이격휴전","2025-04-29 09:00","2025-04-29 17:00","취소","취소","당일"]
[644,"광주전남","순천","여수소라#2 T/L","여수S/S  GIS 교체공사 관련 안전이격휴전","○ 여수S/S  장기사용 GIS 교체공사(1차) - 안전이격휴전","2025-04-24 09:00","2025-04-24 17:00","취소","취소","당일"]
[645,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체(Digital화)공사","○ 여수S/S  장기사용 GIS 교체공사(1차) - 여천-여수#1T/L 교체 및 BUS SEC 증설 - BUS-TIE 및 61-66PT&ES 증설","2025-04-07 10:00","2025-06-05 16:00","취소","취소","연속"]
[646,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체(Digital화)공사","○ 여수S/S  장기사용 GIS 교체공사(1차) - 여천-여수#1T/L 교체 및 BUS SEC 증설 - 여수-소리#1,2T/L 제어케이블 LID 이설","2025-04-03 10:00","2025-04-04 18:00","2025-04-03T16:00:00","2025-04-04T10:00:00","연속"]
[647,"광주전남","순천","여천여수#2 T/L"," 여수-소라T/L 추락방지시설 설치공사","4회선 수평 설치","2025-04-03 07:00","2025-04-03 18:00","취소","취소","당일"]
[648,"광주전남","순천","여수소라#2 T/L"," 여수-소라T/L 추락방지시설 설치공사","4회선 수평 설치","2025-04-03 07:00","2025-04-03 18:00","취소","취소","당일"]
[649,"광주전남","순천","여천여수#1 T/L"," 여수-소라T/L 추락방지시설 설치공사","4회선 수평 설치","2025-04-02 07:00","2025-04-02 18:00","취소","취소","당일"]
[650,"광주전남","순천","여수소라#1 T/L"," 여수-소라T/L 추락방지시설 설치공사","4회선 수평 설치","2025-04-02 07:00","2025-04-02 18:00","취소","취소","당일"]
[651,"광주전남","순천","용성여수산단#2 T/L"," 용성-여수산단#2T/L #1DS 가스누기 해소공사"," 용성-여수산단#2T/L #1DS 가스누기 해소공사","2025-04-10 09:00","2025-04-11 18:00","취소","취소","당일"]
[652,"광주전남","순천","여수TP화치#1 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 추락방지시설 설치","2025-04-22 13:00","2025-04-22 18:00","2025-04-22 13:00","2025-04-22 18:00","당일"]
[653,"광주전남","순천","호남TP여수TP#1 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 추락방지시설 설치","2025-04-22 07:00","2025-04-22 13:00","취소","취소","당일"]
[654,"광주전남","순천","여수TP화치#2 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 추락방지시설 설치","2025-04-21 13:00","2025-04-21 18:00","2025-04-21 13:00","2025-04-21 18:00","당일"]
[655,"광주전남","순천","호남TP여수TP#2 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 추락방지시설 설치","2025-04-21 07:00","2025-04-21 13:00","취소","취소","당일"]
[656,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2025-04-17 09:00","2025-04-18 18:00","취소","취소","연속"]
[657,"광주전남","순천","여수T/P #65 BUS","GS 칼텍스 여수#2T/L #2DS 가스누기해소 공사","#2DS 가스누기해소 공사","2025-04-14 09:00","2025-04-15 18:00","취소","취소","당일"]
[658,"광주전남","순천","여수TP화치#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP-화치#2T/L 보호배전반 대체","2025-04-07 09:00","2025-04-11 18:00","2025-04-07 09:00","2025-04-11 18:00","연속"]
[659,"광주전남","순천","여수TP용성#1 T/L"," 여수TP-용성T/L 추락방지시설 설치공사","4회선 수평 설치","2025-04-09 07:00","2025-04-09 18:00","취소","취소","당일"]
[660,"광주전남","순천","여수TP용성#1 T/L","GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2025-04-07 09:00","2025-04-07 18:00","취소","취소","당일"]
[661,"광주전남","순천","용성여수산단#1 T/L"," 여수TP-용성T/L 추락방지시설 설치공사","4회선 수평 설치","2025-04-09 07:00","2025-04-09 18:00","2025-04-09 07:00","2025-04-09 18:00","당일"]
[662,"광주전남","순천","여수TP용성#2 T/L"," 여수TP-용성T/L 추락방지시설 설치공사","4회선 수평 설치","2025-04-10 07:00","2025-04-10 18:00","취소","취소","당일"]
[663,"광주전남","순천","용성여수산단#2 T/L"," 여수TP-용성T/L 추락방지시설 설치공사","4회선 수평 설치","2025-04-10 07:00","2025-04-10 18:00","취소","취소","당일"]
[664,"광주전남","순천","여수TP용성#1 T/L","용성S/S 여수TP-용성#1T/L GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2025-04-29 09:00","2025-04-30 18:00","취소","취소","연속"]
[665,"광주전남","순천","율촌민자#2 T/L"," 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-04-07 07:00","2025-04-07 18:00","취소","취소","당일"]
[666,"광주전남","순천","율촌화치#1 T/L","율촌-여수산단#2 T/L 정밀점검","율촌-여수산단#2 T/L 정밀점검 총 51기 - 병가선로 휴전신청","2025-04-16 09:00","2025-04-18 18:00","2025-04-16 09:00","2025-04-18 18:00","매일"]
[667,"광주전남","순천","율촌민자#1 T/L"," 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-04-04 07:00","2025-04-04 18:00","취소","취소","당일"]
[668,"광주전남","순천","율촌여수산단#2 T/L"," 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-04-16 07:00","2025-04-17 18:00","2025-04-16 07:00","2025-04-17 18:00","매일"]
[669,"광주전남","순천","세풍율촌#2 T/L","율촌S/S 세풍-율촌#2T/L 인출 ES 투입불량 관련 제작사 점검","율촌S/S 세풍-율촌#2T/L 인출 ES 투입불량 관련 제작사 점검","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","당일"]
[670,"광주전남","순천","세풍율촌#1 T/L","율촌S/S 세풍-율촌#1T/L 인출 ES 투입불량 관련 제작사 점검","율촌S/S 세풍-율촌#1T/L 인출 ES 투입불량 관련 제작사 점검","2025-04-14 09:00","2025-04-14 18:00","2025-04-14 09:00","2025-04-14 18:00","당일"]
[671,"광주전남","순천","율촌화치#2 T/L","율촌-여수산단#1 T/L 정밀점검","율촌-여수산단#1 T/L 정밀점검 총 51기 - 병가선로 휴전신청","2025-04-14 09:00","2025-04-15 18:00","2025-04-14 09:00","2025-04-15 18:00","매일"]
[672,"광주전남","순천","율촌여수산단#1 T/L"," 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-04-14 07:00","2025-04-15 18:00","2025-04-14 07:00","2025-04-15 18:00","매일"]
[673,"광주전남","순천","태금하동화력 T/L","효성제 170kv gis 부품 교체 시행","효성제 170kv gis 부품 교체 시행(즉시가압 불가)","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","당일"]
[674,"광주전남","직할","남광주금천#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 피뢰기설치 작업구간 : 신화순-나주#2T/L 38호[남광주-금천#2T/L 75호(병가)]","2025-04-07 07:00","2025-04-07 18:00","취소","취소","당일"]
[675,"광주전남","직할","남광주금천#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 피뢰기설치 작업구간 : 신화순-나주#2T/L 38호[남광주-금천#2T/L 75호(병가)]","2025-04-07 07:00","2025-04-07 18:00","취소","취소","당일"]
[676,"광주전남","직할","덕림평동#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 덕림-평동#2T/L 59~61호[평동-왕곡#2T/L 1~3호(병가)]","2025-04-14 07:00","2025-04-15 18:00","취소","취소","매일"]
[677,"광주전남","직할","덕림평동#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 덕림-평동#2T/L 59~61호[평동-왕곡#2T/L 1~3호(병가)]","2025-04-14 07:00","2025-04-15 18:00","취소","취소","매일"]
[678,"광주전남","직할","신화순매월#1 T/L","2024~2025년 광주전남본부 직할 변전협력회사 공사","선로측 DS 동작점검","2025-04-02 09:00","2025-04-02 14:00","2025-04-02 09:00","2025-04-02 14:00","당일"]
[679,"광주전남","직할","신화순매월#2 T/L","2024~2025년 광주전남본부 직할 변전협력회사 공사","선로측 DS 동작점검","2025-04-02 14:00","2025-04-02 18:00","2025-04-02 14:00","2025-04-02 18:00","당일"]
[680,"광주전남","직할","매월화정#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-04-09 14:00","2025-04-11 18:00","취소","취소","연속"]
[681,"광주전남","직할","신화순매월#1 T/L","2024~2025년 광주전남본부 직할 변전협력회사 공사","선로측 DS 동작점검","2025-04-02 09:00","2025-04-02 14:00","취소","취소","당일"]
[682,"광주전남","직할","매월화정#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-04-09 14:00","2025-04-11 18:00","취소","취소","연속"]
[683,"광주전남","직할","매월화정#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-04-07 09:00","2025-04-09 14:00","취소","취소","연속"]
[684,"광주전남","직할","신화순매월#2 T/L","2024~2025년 광주전남본부 직할 변전협력회사 공사","선로측 DS 동작점검","2025-04-02 14:00","2025-04-02 18:00","취소","취소","당일"]
[685,"광주전남","직할","매월화정#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-04-07 09:00","2025-04-09 14:00","취소","취소","연속"]
[686,"광주전남","직할","수완흑석#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검 송전선로 보호배전반 교체","2025-04-28 09:00","2025-04-30 18:00","2025-04-28 09:00","2025-04-30 18:00","연속"]
[687,"광주전남","직할","수완흑석#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검 송전선로 보호배전반 교체","2025-04-28 09:00","2025-04-30 18:00","취소","취소","연속"]
[688,"광주전남","직할","평동왕곡#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 덕림-평동#2T/L 59~61호[평동-왕곡#2T/L 1~3호(병가)]","2025-04-14 07:00","2025-04-15 18:00","취소","취소","매일"]
[689,"광주전남","직할","평동왕곡#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 덕림-평동#2T/L 59~61호[평동-왕곡#2T/L 1~3호(병가)]","2025-04-14 07:00","2025-04-15 18:00","취소","취소","매일"]
[690,"대구","경산","경산자인#2 T/L","2024~25년 대구본부 직할 가공송전 협력회사 공사","피뢰기 설치, 조류착지방지장치 설치, 위험표시찰 교체, 전선교체 등","2025-04-14 07:30","2025-04-28 18:00","2025-04-14 07:30","2025-04-28 18:00","연속"]
[691,"대구","경산","영천S/S #2 EM.Tr CB","영천S/S ESS설비 정기점검","- ESS 관련 설비(Ep.Tr, PCS, BAT, LPMS) 정기점검","2025-04-03 09:30","2025-04-17 18:00","2025-04-03 09:30","2025-04-17 18:00","연속"]
[692,"대구","경산","와촌하양#1 T/L","24~25년 경산P/O 변전협력회사 총액공사","-모선보호반교체","2025-04-23 15:30","2025-04-23 16:00","2025-04-23 15:30","2025-04-23 16:00","연속"]
[693,"대구","달성","구지서구지#1 T/L","[TEST] 구지S/S #60-65 BUS TIE 정밀점검 무부하가압","○ 구지S/S #60-65 BUS TIE 정밀점검 무부하가압","2025-04-15 17:00","2025-04-15 18:00","2025-04-15 17:00","2025-04-15 18:00","연속"]
[694,"대구","달성","다사달서 T/L","2024~2025년 달성전력지사 가공송전협력회사 공사","폴리머 점퍼지지애자 교체공사","2025-04-29 08:00","2025-04-29 18:00","2025-04-29 08:00","2025-04-29 18:00","연속"]
[695,"대구","달성","달서팔달#2 T/L","2024~2025년 달성전력지사 가공송전협력회사 공사","폴리머 점퍼지지애자 교체공사(No.5)","2025-04-29 08:00","2025-04-29 18:00","2025-04-29 08:00","2025-04-29 18:00","연속"]
[696,"대구","달성","상인S/S #2 BUS","상인S/S  GIS 대체공사(2차)","- 상인봉덕#1TL, BUS TIE GIS, PT&ES 교체","2025-04-21 09:00","2025-05-02 14:00","2025-04-21 09:00","2025-05-02 14:00","연속"]
[697,"대구","달성","상인S/S #1 BUS","상인S/S  GIS 대체공사(2차)","- 상인봉덕#1TL, BUS TIE GIS, PT&ES 교체","2025-04-10 09:00","2025-04-19 16:00","2025-04-10 09:00","2025-04-19 16:00","연속"]
[698,"대구","달성","상인봉덕#1 T/L","상인S/S  GIS 대체공사(2차)","- 상인봉덕#1TL, BUS TIE GIS, PT&ES 교체","2025-04-07 09:00","2025-05-02 16:00","2025-04-07 09:00","2025-05-02 16:00","연속"]
[699,"대구","달성","상인S/S CB 6100","상인S/S  GIS 대체공사(2차)","- 상인봉덕#1TL, BUS TIE GIS, PT&ES 교체","2025-04-07 09:00","2025-05-02 16:00","2025-04-07 09:00","2025-05-02 16:00","연속"]
[700,"대구","달성","구지서구지#1 T/L","[TEST] 서구지S/S #60-61 BUS SEC GIS 정밀 무부하","[TEST] 서구지S/S #60-61 BUS SEC GIS 정밀 무부하","2025-04-25 17:00","2025-04-25 18:00","2025-04-25 17:00","2025-04-25 18:00","연속"]
[701,"대구","달성","구지서구지#1 T/L","[TEST] 서구지S/S #2M.TR 1차 GIS정밀점검 무부하가압","[TEST] 서구지S/S #2M.TR 1차 GIS정밀점검 무부하가압","2025-04-23 17:00","2025-04-23 18:00","2025-04-23 17:00","2025-04-23 18:00","연속"]
[702,"대구","달성","구지서구지#2 T/L","[TEST] 서구지S/S #3M.TR 정밀점검 무부하가압","[TEST] 서구지S/S #3M.TR 정밀점검 무부하가압","2025-04-30 17:00","2025-04-30 18:00","2025-04-30 17:00","2025-04-30 18:00","연속"]
[703,"대구","직할","공평서침산 T/L","공평S/S 공평-서침산T/L GIS 보통점검","공평S/S 공평-서침산T/L GIS 보통점검","2025-04-22 09:00","2025-04-22 18:00","2025-04-22 09:00","2025-04-22 18:00","연속"]
[704,"대구","직할","공평침산 T/L","공평S/S 공평-침산T/L GIS 보통점검","공평S/S 공평-침산T/L GIS 보통점검","2025-04-23 09:00","2025-04-23 18:00","2025-04-23 09:00","2025-04-23 18:00","연속"]
[705,"대구","직할","동인내당#1 T/L","25-26년도 대구직할 지중송전 협력회사 공사","OF케이블 절연유 채유 및 전력구 내 절연유 채유밸브 설치","2025-04-14 09:00","2025-04-15 18:00","2025-04-14 09:00","2025-04-15 18:00","연속"]
[706,"대구","직할","동인내당#2 T/L","25-26년도 대구직할 지중송전 협력회사 공사","OF케이블 절연유 채유 및 전력구 내 절연유 채유밸브 설치","2025-04-16 09:00","2025-04-17 18:00","2025-04-16 09:00","2025-04-17 18:00","연속"]
[707,"대구","칠곡","어모김천#1 T/L"," 김천S/S 현대화공사","○  Sh.C 전력케이블 무부하가압","2025-04-07 14:00","2025-04-08 18:00","2025-04-07 14:00","2025-04-08 18:00","연속"]
[708,"대구","칠곡","김천금릉#2 T/L","(안전확보)345kV 신옥천-북경남 등 8개T/L수평추락방지장치 설치공사"," 성주-금릉#2T/L 수평 추락방지장치 설치공사 안전확보차 - No.101~102 4회선 병가철탑 (2기)","2025-04-03 07:00","2025-04-03 18:00","취소","취소","연속"]
[709,"대구","칠곡","서대구남구미#2 T/L","2024~2025년도 대구본부 칠곡전력지사 송전협력회사 공사"," 서대구-남구미#2T/L 수평 추락방지장치 설치공사 (No.1~8, 10~70)","2025-04-30 07:00","2025-05-13 18:00","2025-04-30 07:00","2025-05-13 18:00","연속"]
[710,"대구","칠곡","고아어모#2 T/L","2024~2025년도 대구본부 칠곡전력지사 송전협력회사 공사"," 고아-어모#2T/L 수평 추락방지장치 설치공사 - No.1~74","2025-04-17 07:00","2025-04-25 18:00","취소","취소","연속"]
[711,"대구","칠곡","어모김천#1 T/L","2024~2025년도 대구본부 칠곡전력지사 송전협력회사 공사","-  어모-김천#1T/L 수평 추락방지장치 설치공사 (No.7~19) -  어모-김천#1T/L 조류착지방지장치 설치공사 (No.10, 11, 13, 15~16)","2025-04-29 07:00","2025-04-29 18:00","2025-04-29 07:00","2025-04-29 18:00","연속"]
[712,"대구","칠곡","어모김천#1 T/L","(안전확보) 2024~2025년도 대구본부 칠곡전력지사 송전협력회사 공사"," 고아-어모#1T/L 수평 추락방지장치 설치공사 - 4회선 병가 구간 안전확보차 어모-김천#1T/L 휴전 (상단 : 고아-어모 No.69~74)","2025-04-10 07:00","2025-04-11 18:00","2025-04-10 07:00","2025-04-11 18:00","연속"]
[713,"대구","칠곡","고아어모#2 T/L"," 고아-어모T/L No.64 안전이격확보공사"," 고아-어모T/L No.64 가선로 구성에 따른 전선 공중이동","2025-04-16 07:00","2025-04-19 18:00","취소","취소","연속"]
[714,"대구","칠곡","고아어모#1 T/L"," 고아-어모T/L No.64 안전이격확보공사"," 고아-어모T/L No.64 본선로 구성에 따른 전선 공중이동","2025-04-14 07:00","2025-04-17 18:00","취소","취소","연속"]
[715,"대구","칠곡","어모김천#2 T/L","(안전확보) 2024~2025년도 대구본부 칠곡전력지사 송전협력회사 공사"," 고아-어모#2T/L 수평 추락방지장치 설치공사 안전확보차 -  어모-김천#2T/L 하단 병가 (No.69 ~ 74)","2025-04-24 07:00","2025-04-28 18:00","2025-04-24 07:00","2025-04-28 18:00","연속"]
[716,"대구","칠곡","고아어모#1 T/L","2024~2025년도 대구본부 칠곡전력지사 송전협력회사 공사"," 고아-어모#1T/L 수평 추락방지장치 설치공사 - No.1 ~ 74","2025-04-08 07:00","2025-04-16 18:00","취소","취소","연속"]
[717,"대구","포항","아화건천#1 T/L","2024~25년도 포항전력지사 변전총액공사","아화, 건천S/S 아화-건천#1T/L 보호반 대체","2025-04-09 09:00","2025-04-11 18:00","2025-04-09 09:00","2025-04-11 18:00","연속"]
[718,"대구","포항","신영일서포항#1 T/L","25년 가공송전 순시점검 위탁공사(포항전력)"," 신영일-서포항 #1,2 T/L 정밀점검 ※ 병행작업:GIS, LA, PT 하자점검 (포항 변전부 허철현)","2025-04-21 09:00","2025-04-23 18:00","취소","취소","연속"]
[719,"대구","포항","신영일서포항#2 T/L","25년 가공송전 순시점검 위탁공사(포항전력)"," 신영일-서포항 #1,2 T/L 정밀점검 ※ 병행작업:GIS, LA, PT 하자점검 (포항 변전부 허철현)","2025-04-28 09:00","2025-04-30 18:00","취소","취소","연속"]
[720,"대구","포항","신영일청하#1 T/L","25년 가공송전 순시점검 위탁공사(포항전력)","정밀점검 관련 병가선로 안전확보 휴전","2025-04-28 09:00","2025-04-29 18:00","취소","취소","연속"]
[721,"대구","포항","신영일청하#2 T/L","25년 가공송전 순시점검 위탁공사(포항전력)","정밀점검 관련 병가선로 안전확보 휴전","2025-04-21 09:00","2025-04-22 18:00","취소","취소","연속"]
[722,"대구","포항","옥동외동#1 T/L","2024~25년도 포항전력지사 변전총액공사","외동S/S 687 GIS, LA 보통점검","2025-04-16 14:00","2025-04-16 18:00","2025-04-15T14:00:00","2025-04-15T18:00:00","연속"]
[723,"대구","포항","옥동외동#2 T/L","2024~25년도 포항전력지사 변전총액공사","외동S/S 657 GIS, LA 보통점검","2025-04-16 09:00","2025-04-16 14:00","2025-04-15T09:00:00","2025-04-15T14:00:00","연속"]
[724,"대구","포항","건천천북#2 T/L","2024~25년도 포항전력지사 변전총액공사","건천-천북#2T/L LA,PT 보통점검","2025-04-08 09:00","2025-04-08 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[725,"대구","포항","천북경주 T/L"," 신포항-천북 등 19개T/L 추락방지장치 설치공사"," 천북-경주T/L 추락방지장치(수평) 설치공사","2025-04-30 08:00","2025-05-02 18:00","2025-04-30 08:00","2025-05-02 18:00","연속"]
[726,"대구","포항","포항경주 T/L"," 신포항-천북 등 19개T/L 추락방지장치 설치공사"," 포항-경주T/L 추락방지장치(수평) 설치공사","2025-04-21 08:00","2025-04-29 18:00","2025-04-21 08:00","2025-04-29 18:00","연속"]
[727,"대구","포항","포항천북 T/L"," 신포항-천북 등 19개T/L 추락방지장치 설치공사"," 포항-천북T/L 추락방지장치(수평) 설치공사","2025-04-21 08:00","2025-04-24 18:00","2025-04-21 08:00","2025-04-24 18:00","연속"]
[728,"경북","구미","남인동인동#1 T/L","2024-25년 구미전력지사 변전협력회사 공사","[남인동S/S] - PT 보통점검 - LA 하자점검 [인동S/S] - B상 누설전류계 교체 - GIS 조작시험 - LA 대체","2025-04-14 09:00","2025-04-14 18:00","2025-04-14 09:00","2025-04-14 18:00","연속"]
[729,"경북","구미","남인동인동#2 T/L","2024-25년 구미전력지사 변전협력회사 공사","[남인동S/S] - PT 보통점검 - LA 하자점검 [인동S/S] - GIS 조작시험 - LA 대체","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","연속"]
[730,"경북","구미","동상주점촌#1 T/L"," 동상주-점촌 등 5개T/L 피뢰기 설치공사"," 동상주-점촌#1T/L 피뢰기 설치(총 41기, No.1~7, 13~14, 16~18, 27~28, 30~39, 41, 43~44, 46, 48~49, 51~52, 54~61, 67)","2025-04-29 07:00","2025-05-02 17:00","2025-04-29 07:00","2025-05-02 17:00","연속"]
[731,"경북","구미","산동군위#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사","[병가] 345kV 서대구-선산#1T/L No.30~107 수평추락방지장치설치","2025-04-22 07:30","2025-04-24 17:30","2025-04-22 07:30","2025-04-24 17:30","연속"]
[732,"경북","구미","칠곡인동#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사","[병가] 345kV 서대구-선산#1T/L No.30~107 수평추락방지장치설치","2025-04-21 07:30","2025-04-22 17:30","2025-04-21 07:30","2025-04-22 17:30","연속"]
[733,"경북","영주","문경단양 T/L"," 문경-단양T/L 송전선로 정밀점검"," 문경-단양T/L 송전선로 정밀점검","2025-04-19 08:00","2025-04-20 18:00","2025-04-19 08:00","2025-04-20 18:00","매일"]
[734,"경북","영주","문경단양 T/L"," 문경-단양T/L 송전선로 정밀점검"," 문경-단양T/L 송전선로 정밀점검","2025-04-26 08:00","2025-04-27 18:00","2025-04-26 08:00","2025-04-27 18:00","매일"]
[735,"경북","영주","문경단양 T/L"," 문경-단양T/L 송전선로 정밀점검"," 문경-단양T/L 송전선로 정밀점검","2025-04-12 08:00","2025-04-13 18:00","2025-04-12 08:00","2025-04-13 18:00","매일"]
[736,"경북","영주","봉화울진 T/L","24~25년 영주전력지사 변전협력회사공사","○봉화-울진T/L 조작시험 ○ LA A,B,C상 하자점검","2025-04-07 09:00","2025-04-07 14:00","2025-04-28T13:00:00","2025-04-28T18:00:00","연속"]
[737,"경북","영주","봉화현종산풍력 T/L","24~25년 영주전력지사 변전협력회사공사","○봉화-현종산풍력T/L 조작시험 ○ LA A,B,C상 하자점검","2025-04-07 14:00","2025-04-07 18:00","2025-04-28T09:00:00","2025-04-28T13:00:00","연속"]
[738,"경북","영주","영주S/S 티앤도촌에너지T/L CB","24-25년 영주전력지사 변전협력회사공사","-하자점검, 조작기구부 점검","2025-04-21 09:00","2025-04-21 18:00","2025-04-21 09:00","2025-04-21 18:00","연속"]
[739,"경북","영주","영주S/S #1 EM.Tr CB","24~25년 영주전력지사 변전협력회사공사","ESS 화재확산방지재 재시공","2025-04-14 09:00","2025-04-18 18:00","2025-04-14 09:00","2025-04-18 18:00","연속"]
[740,"경북","영주","영주S/S #1 EM.Tr CB","24~25년 영주전력지사 변전협력회사공사","ESS 화재확산방지재 재시공","취소","취소","취소","취소","연속"]
[741,"경북","직할","안동풍산 T/L","경북직할 가공송전 협력회사공사"," 안동-풍산T/L 추락방지장치 설치공사","2025-04-18 08:00","2025-04-25 18:00","2025-04-18 08:00","2025-04-25 18:00","연속"]
[742,"경북","직할","울진북면전철#2 T/L CB","24~25년 경북본부 직할 변전협력회사 공사","GIS 초기점검","2025-04-15 09:00","2025-04-15 18:00","2025-04-15 09:00","2025-04-15 18:00","연속"]
[743,"경북","직할","진보S/S 영양풍력T/L CB","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2025-04-21 09:00","2025-04-21 18:00","2025-04-21 09:00","2025-04-21 18:00","연속"]
[744,"경북","직할","현종산풍력평해#2 T/L","'24~25년 경북직할가공송전협력회사 공사","Gantry tower안전발판 설치공사","2025-04-08 08:00","2025-04-08 18:00","2025-04-08 08:00","2025-04-08 18:00","연속"]
[745,"부산울산","동부산","구서S/S #2 BUS"," 구서S/S 장기사용 GIS 교체공사(4차)","○ #2BUS 무부하 시험가압(1h)","2025-04-02 17:00","2025-04-02 18:00","2025-04-02 17:00","2025-04-02 18:00","연속"]
[746,"부산울산","동부산","구서S/S #1 BUS"," 구서S/S 장기사용 GIS 교체공사(4차)","○ #1BUS 무부하 시험가압(24h)","2025-04-01 17:00","2025-04-02 17:00","2025-04-01 17:00","2025-04-02 17:00","연속"]
[747,"부산울산","동부산","구서노포#2 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치, 수평추락방지장치 설치","2025-04-03 07:00","2025-04-06 18:00","2025-04-03 07:00","2025-04-06 18:00","연속"]
[748,"부산울산","동부산","노포정관#1 T/L","345kV 울주-고리NP 등 22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치, 수평추락방지장치 설치","2025-04-03 07:00","2025-04-06 18:00","2025-04-03 07:00","2025-04-06 18:00","연속"]
[749,"부산울산","동부산","좌동우동#2 T/L","좌동S/S  장기사용 GIS 교체공사","1. 장기사용 GIS 교체 2. 좌동-우동#2T/L 인출변경","2025-04-18 09:00","2025-05-03 18:00","취소","취소","연속"]
[750,"부산울산","동부산","좌동S/S #2 BUS","좌동S/S  장기사용 GIS 교체공사","좌동S/S 신규 GIS 2DS, 상부모선 설치(6333,6200,637,647)","2025-04-06 09:00","2025-04-15 18:00","2025-04-06 09:00","2025-04-15 18:00","연속"]
[751,"부산울산","북부산","개금범천#2 T/L","개금S/S  개금-범천#1,2 T/L GIS교체공사","개금S/S  개금-범천#1,2 T/L GIS교체공사","2025-04-02 09:00","2025-04-15 18:00","2025-04-21 09:00","2025-05-08 18:00","연속"]
[752,"부산울산","북부산","북부산구포#2 T/L","24-25년 북부산전력지사 변전협력회사 공사","구포S/S  북부산-구포#2T/L GIS 하자점검","2025-04-15 09:00","2025-04-15 18:00","2025-04-08 09:00","2025-04-08 18:00","연속"]
[753,"부산울산","북부산","구포대저#2 T/L","24-25년 북부산전력지사 변전협력회사 공사","구포S/S  구포-대저#2T/L GIS 하자점검","2025-04-10 09:00","2025-04-10 18:00","2025-04-10 09:00","2025-04-10 18:00","연속"]
[754,"부산울산","북부산","북부산구포#1 T/L","24-25년 북부산전력지사 변전협력회사 공사","구포S/S  북부산-구포#1T/L GIS 하자점검","2025-04-14 09:00","2025-04-14 18:00","2025-04-07 09:00","2025-04-07 18:00","연속"]
[755,"부산울산","북부산","구포대저#1 T/L","24-25년 북부산전력지사 변전협력회사 공사","구포S/S  구포-대저#1T/L GIS 하자점검","2025-04-09 09:00","2025-04-09 18:00","2025-04-09 09:00","2025-04-09 18:00","연속"]
[756,"부산울산","북부산","대저모라#2 T/L","24-25년 북부산전력지사 변전협력회사 공사","모라S/S 대저-모라#2T/L 전자변 교체","2025-04-21 09:00","2025-04-21 18:00","2025-04-21 09:00","2025-04-21 18:00","연속"]
[757,"부산울산","북부산","대저모라#1 T/L","24-25년 북부산전력지사 변전협력회사 공사","모라S/S 대저-모라#1T/L 전자변 교체","2025-04-18 09:00","2025-04-18 18:00","2025-04-18 09:00","2025-04-18 18:00","연속"]
[758,"부산울산","북부산","물금양산열병합#1 T/L","24-25년 북부산전력지사 변전협력회사 공사","물금S/S  양산열병합#1T/L GIS 하자점검","2025-04-07 09:00","2025-04-07 18:00","취소","취소","연속"]
[759,"부산울산","북부산","물금양산열병합#2 T/L","24-25년 북부산전력지사 변전협력회사 공사","물금S/S  양산열병합#2T/L GIS 하자점검","2025-04-08 09:00","2025-04-08 18:00","취소","취소","연속"]
[760,"부산울산","북부산","서창산막#1 T/L","24-25년 북부산전력지사 가공송전 협력회사공사","○ 가공지선 교체 : 산막S/S~인입철탑 구간","2025-04-19 08:00","2025-04-20 18:00","취소","취소","연속"]
[761,"부산울산","북부산","양산산막#1 T/L","24-25년 북부산전력지사 가공송전 협력회사공사","○ 가공지선 교체 : 산막S/S~인입철탑 구간","2025-04-19 08:00","2025-04-20 18:00","취소","취소","연속"]
[762,"부산울산","북부산","서창산막#2 T/L","24-25년 북부산전력지사 가공송전 협력회사공사","○ 가공지선 교체 : 산막S/S~인입철탑 구간","2025-04-26 08:00","2025-04-27 18:00","취소","취소","연속"]
[763,"부산울산","북부산","양산산막#2 T/L","24-25년 북부산전력지사 가공송전 협력회사공사","○ 가공지선 교체 : 산막S/S~인입철탑 구간","2025-04-26 08:00","2025-04-27 18:00","취소","취소","연속"]
[764,"부산울산","북부산","물금삼랑진PP#1 T/L","2025년 가공송전선로 순시점검 위탁공사 정밀점검"," 물금-삼랑진 T/L 정밀점검 -점검대상 : 총 60기(No.1 ~ 58호 58기 및 S/T 6기) -4회선 철탑 점검을 안전이격휴전","2025-04-21 08:00","2025-04-25 18:00","2025-04-21 08:00","2025-04-25 18:00","연속"]
[765,"부산울산","북부산","물금삼랑진PP#1 T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y #1S.Tr 1차 GIS 정밀점검 시험가압선로- 물금삼랑진PP#1T/L,#60BUS","2025-04-15 17:00","2025-04-15 18:00","2025-04-15 17:00","2025-04-15 18:00","연속"]
[766,"부산울산","북부산","물금삼랑진PP#1 T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y #2S.Tr 1차 GIS 정밀점검 시험가압선로- 물금삼랑진PP#1T/L,#65BUS","2025-04-17 17:00","2025-04-17 18:00","2025-04-17 17:00","2025-04-17 18:00","연속"]
[767,"부산울산","북부산","물금삼랑진PP#2 T/L","2025년 가공송전선로 순시점검 위탁공사 정밀점검"," 물금-삼랑진 T/L 정밀점검 -점검대상 : 총 60기(No.1 ~ 58호 58기 및 S/T 6기)","2025-04-21 08:00","2025-04-25 18:00","2025-04-21 08:00","2025-04-25 18:00","연속"]
[768,"부산울산","북부산","양산삼랑진PP T/L","2025년 가공송전선로 순시점검 위탁공사 정밀점검","삼랑진S/Y 양상-삼랑진PP, 북부산-삼랑진PP GIS 정밀점검","2025-04-28 08:00","2025-05-02 18:00","2025-04-28 09:00","2025-04-29 18:00 ","연속"]
[769,"부산울산","북부산","북부산삼랑진PP T/L","2025년 가공송전선로 순시점검 위탁공사 정밀점검","삼랑진S/Y 양상-삼랑진PP, 북부산-삼랑진PP GIS 정밀점검","2025-04-28 08:00","2025-05-02 18:00","2025-04-30 09:00","2025-05-01 18:00 ","연속"]
[770,"부산울산","북부산","북부산삼랑진PP T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y 6100B/T GIS 정밀점검 시험가압선로- 북부산-삼랑진PPT/L,#60BUS","2025-04-29 17:00","2025-04-29 18:00","취소","취소","연속"]
[771,"부산울산","서부산","용원녹공#1 T/L","녹공S/S 용원-녹공#1T/L GIS 동작시험","녹공S/S 용원-녹공#1T/L GIS 동작시험","2025-04-26 09:00","2025-04-26 14:00","2025-04-26 09:00","2025-04-26 14:00","연속"]
[772,"부산울산","서부산","용원녹공#2 T/L","녹공S/S 용원-녹공#2T/L GIS 동작시험","녹공S/S 용원-녹공#2T/L GIS 동작시험","2025-04-26 14:00","2025-04-26 18:00","2025-04-26 14:00","2025-04-26 18:00","연속"]
[773,"부산울산","서부산","신녹산녹산#2 T/L","신녹산S/S 신녹산-녹산#2T/L GIS 보통점검","신녹산S/S 신녹산-녹산#2T/L GIS 보통점검 병행 : 녹산S/S 신녹산-녹산#2T/L GIS 동작시험","2025-04-15T09:00:00","2025-04-15 18:00","2025-04-15T09:00:00","2025-04-15 18:00","연속"]
[774,"부산울산","서부산","신녹산녹산#1 T/L","신녹산S/S 신녹산-녹산#1T/L GIS 보통점검","신녹산S/S 신녹산-녹산#1T/L GIS 보통점검 병행 : 녹산S/S 신녹산-녹산#1T/L GIS 동작시험","2025-04-14 09:00","2025-04-14 18:00","2025-04-14 09:00","2025-04-14 18:00","연속"]
[775,"부산울산","서부산","신녹산용원#1 T/L","신녹산S/S 신녹산-용원#1T/L GIS 보통점검","신녹산S/S 신녹산-용원#1T/L GIS 보통점검","2025-04-27 09:00","2025-04-27 14:00","2025-04-27T09:00:00","2025-04-27 14:00","연속"]
[776,"부산울산","서부산","신녹산용원#2 T/L","신녹산S/S 신녹산-용원#2T/L GIS 보통점검","신녹산S/S 신녹산-용원#2T/L GIS 보통점검","2025-04-27 14:00","2025-04-27 18:00","2025-04-27 14:00","2025-04-27 18:00","연속"]
[777,"부산울산","서부산","신녹산명지#2 T/L","신녹산S/S 345kV #1M.Tr 증설공사"," 신녹산-명지#2T/L 이설","2025-04-28 09:00","2025-05-30 18:00","2025-04-28 09:00","2025-05-30 18:00","연속"]
[778,"부산울산","서부산","신김해지사#1 T/L","지사S/S  신김해-지사#1T/L GIS 정밀점검","지사S/S  신김해-지사#1T/L GIS 정밀점검","2025-04-21 09:00","2025-04-22 18:00","2025-04-21 09:00","2025-04-22 18:00","연속"]
[779,"부산울산","서부산","신김해지사#2 T/L","지사S/S  신김해-지사#2T/L GIS 정밀점검","지사S/S  신김해-지사#2T/L GIS 정밀점검","2025-04-24 09:00","2025-04-25 18:00","2025-04-24 09:00","2025-04-25 18:00","연속"]
[780,"부산울산","울산","남울산S/S CB 6971","25년 울산전력지사 변전협력회사 공사","- 6971 GIS 보통점검","2025-04-16 09:00","2025-04-16 18:00","2025-04-16 09:00","2025-04-16 18:00","연속"]
[781,"부산울산","울산","남울산S/S CB 6772","25년 울산전력지사 변전협력회사 공사","- 6772 GIS 보통점검","2025-04-17 09:00","2025-04-17 18:00","2025-04-17 09:00","2025-04-17 18:00","연속"]
[782,"부산울산","울산","남울산S/S CB 6671","25년 울산전력지사 변전협력회사 공사","- 6671 GIS 보통점검","2025-04-18 09:00","2025-04-18 18:00","2025-04-18 09:00","2025-04-18 18:00","연속"]
[783,"부산울산","울산","남울산S/S CB 6471","25년 울산전력지사 변전협력회사 공사","- 6471 GIS 보통점검","2025-04-21 09:00","2025-04-21 18:00","2025-04-21 09:00","2025-04-21 18:00","연속"]
[784,"부산울산","울산","반천언양#2 T/L","24-25년 북부산전력지사 가공송전 협력회사공사","○ 언양-산막T/L 애자교체 안전이격확보","2025-04-14 08:00","2025-04-15 18:00","취소","취소","연속"]
[785,"부산울산","울산","언양산막#2 T/L"," 석계분기T/L 건설공사","지지물 : 산형강 철탑 5기 전력선 : ACSR 410mm * 2B * 4C, 2.176km","2025-04-01 07:00","2025-04-11 18:00","취소","취소","연속"]
[786,"부산울산","울산","언양산막#1 T/L"," 석계분기T/L 건설공사","지지물 : 산형강 철탑 5기 전력선 : ACSR 410mm * 2B * 4C, 2.176km","2025-04-12 07:00","2025-04-18 18:00","취소","취소","연속"]
[787,"부산울산","울산","옥동외동#2 T/L","2025년 가공송전 순시점검 위탁공사(울산)","○ 신울산-태화T/L 정밀점검 - 대상 : 0.01호 ~37.1호 - 자선로 :  외동-옥동T/L 7호","2025-04-22 08:00","2025-04-22 18:00","취소","취소","연속"]
[788,"부산울산","울산","옥동외동#1 T/L","2025년 가공송전 순시점검 위탁공사(울산)","○ 신울산-태화T/L 정밀점검 - 대상 : 0.01호 ~37.1호 - 자선로 :  외동-옥동T/L 7호","2025-04-15 08:00","2025-04-15 18:00","취소","취소","연속"]
[789,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","온산-처용#2T/L, #3M.Tr 1차 GIS 교체","2025-04-05 09:00","2025-04-05 18:00","2025-04-05 09:00","2025-04-05 18:00","연속"]
[790,"부산울산","울산","신온산온산#2 T/L","온산S/S  장기사용 GIS 교체공사","온산-처용#2T/L, #3M.Tr 1차 GIS 교체","2025-04-02 15:00","2025-04-03 15:00","2025-04-02 15:00","2025-04-03 15:00","연속"]
[791,"부산울산","울산","신온산온산#2 T/L","온산S/S  장기사용 GIS 교체공사","온산-처용#2T/L, #3M.Tr 1차 GIS 교체","2025-04-11 15:00","2025-04-12 15:00","2025-04-11 15:00","2025-04-12 15:00","연속"]
[792,"부산울산","울산","용연울산TP#3 T/L","25년 울산전력지사 변전협력회사 공사","- 용연) 차단기 동작시험 - 울산TP) 차단기 동작시험","2025-04-24 09:00","2025-04-24 18:00","2025-04-24 09:00","2025-04-24 18:00","연속"]
[793,"부산울산","울산","성암울산TP#1 T/L","울산화력S/Y  #667,677 GIS 철거공사","- #667 GIS #2모선부 철거공사","2025-04-14 09:00","2025-04-17 16:00","2025-04-14 09:00","2025-04-17 16:00","연속"]
[794,"부산울산","울산","용연울산TP#1 T/L","울산화력S/Y 접속설비(667,677)GIS 철거공사","- 677 GIS 철거공사","2025-04-10 16:00","2025-04-11 16:00","2025-04-10 16:00","2025-04-11 16:00","연속"]
[795,"부산울산","울산","울산T/P #61 BUS","울산화력S/Y 접속설비(667,677)GIS 철거공사","- 677 GIS 철거공사","2025-04-07 09:00","2025-04-11 16:00","2025-04-07 09:00","2025-04-11 16:00","연속"]
[796,"부산울산","울산","용연울산TP#2 T/L","울산화력S/Y 접속설비(667,677)GIS 철거공사","- 677 GIS 철거공사","2025-04-07 09:00","2025-04-10 16:00","2025-04-07 09:00","2025-04-10 16:00","연속"]
[797,"부산울산","울산","용연울산TP#1 T/L","울산화력S/Y 접속설비(667,677)GIS 철거공사","- 677 GIS 철거공사(시험가압선로 24H)","2025-03-20 16:00","2025-03-21 16:00","2025-04-03 16:00","2025-04-04 16:00","연속"]
[798,"부산울산","울산","성암울산TP#2 T/L","울산화력S/Y  #667,677 GIS 철거공사","- #667 GIS #1모선부 시험가압(24H)","2025-04-24 16:00","2025-04-25 16:00","2025-04-24 16:00","2025-04-25 16:00","연속"]
[799,"부산울산","울산","울산T/P #60 BUS","울산화력S/Y  #667,677 GIS 철거공사","- #667 GIS #1모선부 철거공사","2025-04-21 16:00","2025-04-25 16:00","2025-04-21 16:00","2025-04-25 16:00","연속"]
[800,"부산울산","울산","성암울산TP#1 T/L","울산화력S/Y  #667,677 GIS 철거공사","- #667 GIS #1모선부 철거공사","2025-04-21 09:00","2025-04-24 16:00","2025-04-21 09:00","2025-04-24 16:00","연속"]
[801,"부산울산","울산","성암울산TP#2 T/L","울산화력S/Y  #667,677 GIS 철거공사","- #667 GIS #2모선부 시험가압(24H)","2025-04-17 16:00","2025-04-18 16:00","2025-04-17 16:00","2025-04-18 16:00","연속"]
[802,"부산울산","울산","울산T/P #65 BUS","울산화력S/Y  #667,677 GIS 철거공사","- #667 GIS #2모선부 철거공사","2025-04-14 16:00","2025-04-18 16:00","2025-04-14 16:00","2025-04-18 16:00","연속"]
[803,"부산울산","울산","울주직동#1 T/L","25년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2025-04-25 09:00","2025-04-25 14:00","2025-04-25 09:00","2025-04-25 14:00","연속"]
[804,"부산울산","울산","울주직동#2 T/L","25년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2025-04-25 14:00","2025-04-25 18:00","2025-04-25 14:00","2025-04-25 18:00","연속"]
[805,"부산울산","울산","직동반천#2 T/L","25년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2025-04-16 14:00","2025-04-16 18:00","2025-04-16 14:00","2025-04-16 18:00","연속"]
[806,"부산울산","울산","직동반천#1 T/L","25년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2025-04-16 09:00","2025-04-16 14:00","2025-04-16 09:00","2025-04-16 14:00","연속"]
[807,"부산울산","울산","산하효문#1 T/L"," 효문S/S GIS 교체공사"," 산하-효문T/L(627), #2M.Tr 1차(6233), BUS-PT 대체 및 구)BUS-TIE(6100) GIS 철거. 끝.","2025-04-02 09:00","2025-05-02 18:00","2025-04-02 09:00","2025-05-02 18:00","연속"]
[808,"부산울산","직할","범일서면#2 T/L","25년 직할 상반기 170kV GIS 정밀점검공사","서면S/S 범일-서면#2T/L GIS 정밀점검","2025-04-22 09:30","2025-04-25 18:00","2025-04-22 09:30","2025-04-25 18:00","연속"]
[809,"부산울산","직할","범일서면#1 T/L","25년 직할 상반기 170kV GIS 정밀점검공사","서면S/S 범일-서면#1T/L GIS 정밀점검","2025-04-22 09:30","2025-04-25 18:00","2025-04-22 09:30","2025-04-25 18:00","연속"]
[810,"부산울산","직할","수정범일#1 T/L","25년 직할 상반기 170kV GIS 정밀점검공사","수정S/S #2M.Tr 1차 6233 GIS 정밀점검 시험가압용","2025-04-04 16:00","2025-04-04 18:00","2025-04-04 16:00","2025-04-04 18:00","연속"]
[811,"부산울산","직할","수정범일#1 T/L","25년 직할 상반기 170kV GIS 정밀점검공사","수정S/S #3M.Tr 1차 6333 GIS 정밀점검 시험가압용","2025-04-08 16:00","2025-04-08 18:00","2025-04-08 16:00","2025-04-08 18:00","연속"]
[812,"부산울산","직할","수정범일#1 T/L","25년 직할 상반기 170kV GIS 정밀점검공사","수정S/S #1M.Tr 1차 6133 GIS 정밀점검 시험가압용","2025-04-02 16:00","2025-04-02 18:00","2025-04-02 16:00","2025-04-02 18:00","연속"]
[813,"경남","김해송변전부","대동매리#2 T/L"," 호포-매리T/L 변위철탑 공사"," 호포-매리T/L 24호 수직추락방지장치 설치","2025-04-06 09:00","2025-04-06 18:00","2025-04-06 09:00","2025-04-06 18:00","연속"]
[814,"경남","김해송변전부","매리김해#2 T/L"," 호포-매리T/L 변위철탑 공사"," 호포-매리T/L 24호 수직추락방지장치 설치","2025-04-06 09:00","2025-04-06 18:00","2025-04-06 09:00","2025-04-06 18:00","연속"]
[815,"경남","김해송변전부","매리김해#1 T/L","매리S/S  매리-김해#1T/L 보통점검","매리S/S  매리-김해#1T/L 보통점검 (병행) 김해S/S 매리-김해#1T/L 조작시험","2025-04-05 09:30","2025-04-05 17:30","2025-04-19 09:30","2025-04-19 17:30","연속"]
[816,"경남","김해송변전부","대동매리#1 T/L"," 호포-매리T/L 변위철탑 공사"," 호포-매리T/L 24호 수직추락방지장치 설치","2025-04-05 09:00","2025-04-05 18:00","2025-04-05 09:00","2025-04-05 18:00","연속"]
[817,"경남","김해송변전부","매리김해#1 T/L"," 호포-매리T/L 변위철탑 공사"," 호포-매리T/L 24호 수직추락방지장치 설치","2025-04-05 09:00","2025-04-05 18:00","2025-04-05 09:00","2025-04-05 18:00","연속"]
[818,"경남","김해송변전부","주촌삼계#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","피뢰기 설치 및 점퍼지지애자 교체 공사 안전이격","2025-04-26 07:00","2025-04-26 18:00","2025-04-26 07:00","2025-04-26 18:00","연속"]
[819,"경남","김해송변전부","삼계어방#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","피뢰기 설치 및 점퍼지지애자 교체 공사 안전이격","2025-04-26 07:00","2025-04-27 18:00","2025-04-26 07:00","2025-04-27 18:00","매일"]
[820,"경남","김해송변전부","한림정삼계#2 T/L","삼계S/S  한림정-삼계#2T/L GIS 보통점검","삼계S/S  한림정-삼계#2T/L GIS 보통점검 - LA 보통점검","2025-04-09 09:30","2025-04-09 17:30","2025-04-09 09:30","2025-04-09 17:30","연속"]
[821,"경남","김해송변전부","주촌삼계#2 T/L","삼계S/S 주촌-삼계#2T/L GIS 보통점검","삼계S/S 주촌-삼계#2T/L GIS 보통점검 - LA 보통점검","2025-04-10 09:30","2025-04-10 17:30","2025-04-10 09:30","2025-04-10 17:30","연속"]
[822,"경남","김해송변전부","한림정삼계#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","피뢰기 설치 및 점퍼지지애자 교체 공사","2025-04-26 07:00","2025-04-27 18:00","2025-04-26 07:00","2025-04-27 18:00","매일"]
[823,"경남","김해송변전부","신김해삼정#1 T/L"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-04-19 13:00","2025-04-19 18:00","2025-04-19 13:00","2025-04-19 18:00","연속"]
[824,"경남","김해송변전부","신김해주촌#2 T/L"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-04-19 07:00","2025-04-19 18:00","2025-04-19 07:00","2025-04-19 18:00","연속"]
[825,"경남","김해송변전부","신김해삼정#2 T/L"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-04-13 07:00","2025-04-13 18:00","2025-04-13 07:00","2025-04-13 18:00","연속"]
[826,"경남","김해송변전부","신김해주촌#1 T/L"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-04-13 07:00","2025-04-13 18:00","2025-04-13 07:00","2025-04-13 18:00","연속"]
[827,"경남","김해송변전부","진례진영#1 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2025-04-05 07:00","2025-04-05 18:00","2025-04-05 07:00","2025-04-05 18:00","연속"]
[828,"경남","김해송변전부","진례진영#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2025-04-06 07:00","2025-04-06 18:00","2025-04-06 07:00","2025-04-06 18:00","연속"]
[829,"경남","김해송변전부","진영한림정#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치 및 피뢰기 설치 공사","2025-04-12 07:00","2025-04-13 18:00","2025-04-12 07:00","2025-04-13 18:00","매일"]
[830,"경남","김해송변전부","진영수산#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치 설치 공사","2025-04-13 07:00","2025-04-13 18:00","2025-04-13 07:00","2025-04-13 18:00","연속"]
[831,"경남","김해송변전부","한림정삼계#2 T/L","신마산-신김해 등 13개T/L 추락방지장치 설치공사","신마산-신김해 등 13개T/L 추락방지장치 설치공사","2025-04-12 07:00","2025-04-12 18:00","2025-04-12 07:00","2025-04-12 18:00","연속"]
[832,"경남","직할","월림S/S #1 BUS","월림S/S 170kV GIS 대체공사","월림S/S 170kV GIS 대체공사 - (2차분) #2BUS TIE 증설","2025-04-14 09:00","2025-04-19 18:00","2025-04-14 09:00","2025-04-19 18:00","연속"]
[833,"경남","직할","창원월림#2 T/L","월림S/S 170kV GIS 대체공사","월림S/S 170kV GIS 대체공사 - (2차분) #2BUS TIE 증설","2025-04-14 09:00","2025-04-26 18:00","2025-04-14 09:00","2025-04-26 18:00","연속"]
[834,"경남","직할","수출월림#1 T/L","월림S/S 170kV GIS 대체공사 시험가압용","월림S/S 170kV GIS 대체공사 - (2차분) #2BUS TIE 증설","2025-04-18 09:00","2025-04-19 18:00","2025-04-18 09:00","2025-04-19 18:00","연속"]
[835,"경남","직할","월림S/S #2 BUS","월림S/S 170kV GIS 대체공사","월림S/S 170kV GIS 대체공사 - (2차분) #2BUS TIE 증설","2025-04-21 09:00","2025-04-25 14:00","2025-04-21 09:00","2025-04-25 14:00","연속"]
[836,"경남","직할","월림S/S #1 BUS","월림S/S 170kV GIS 대체공사","월림S/S 170kV GIS 대체공사 - (2차분) #2BUS TIE 증설","2025-04-25 14:00","2025-04-26 18:00","2025-04-25 14:00","2025-04-26 18:00","연속"]
[837,"경남","진주","거창합천#2 T/L","거창S/S  거창-합천#2T/L GIS 보통점검 등","거창S/S  거창-합천#2T/L GIS 보통점검 및 LA(A,B,C) 보통점검, PT 대체","2025-04-01 10:00","2025-04-01 18:00","2025-04-01 10:00","2025-04-01 18:00","연속"]
[838,"경남","진주","거창합천#1 T/L","거창S/S  거창-합천#2T/L PT 대체 관련 안전이격 휴전","거창S/S  거창-합천#2T/L PT 대체 관련 안전이격 휴전","2025-04-01 10:00","2025-04-01 15:00","2025-04-01 10:00","2025-04-01 15:00","연속"]
[839,"경남","진주","산청함양 T/L","산청S/S  산청-함양T/L LA 하자점검","산청S/S  산청-함양T/L LA(A,B,C) 하자점검","2025-04-04 10:00","2025-04-04 15:00","2025-04-04 10:00","2025-04-04 15:00","연속"]
[840,"경남","진주","의령동진주#1 T/L","2025년 가공송전 위탁정비공사"," 의령-함양T/L 1~7호(의령-동진주T/L 67~73호) 구간 정밀점검","2025-04-22 08:00","2025-04-23 18:00","2025-04-22 08:00","2025-04-23 18:00","매일"]
[841,"경남","진주","의령산청 T/L","의령S/S  의령-산청T/L GIS 조작시험 등","의령S/S  의령-산청T/L GIS 조작시험, LA(A,B,C) 보통점검, PT 보통 [병행] 산청S/S  의령-산청T/L LA(A,B,C) 하자","2025-04-03 10:00","2025-04-03 18:00","2025-04-03 10:00","2025-04-03 18:00","연속"]
[842,"경남","진주","의령함양 T/L","2025년 가공송전 순시점검 위탁공사"," 의령-함양T/L 의령S/T ~ 함양S/T(총 132기)","2025-04-07 08:00","2025-04-23 18:00","취소","취소","매일"]
[843,"경남","진주","태금하동#1 T/L","2025년 가공송전 순시점검 위탁공사","345kV 의령-하동화력#2T/L 5~13호 정밀점검  태금-하동T/L 병가구간 안전이격거리 확보","2025-04-17 08:00","2025-04-17 18:00","취소","취소","매일"]
[844,"경남","진주","하동하동화력 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 :  하동-하동화력T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1(345kV의령-하동화력#1T/L 병가)","2025-04-10 07:00","2025-04-10 18:00","2025-04-10 07:00","2025-04-10 18:00","연속"]
[845,"경남","진주","태금하동화력 T/L","345kV 의령-하동화력 등 2개T/L 추락방지장치 설치공사","1. 작업내용 :  태금-하동화력T/L측 수평 추락방지장치 설치 2. 작업구간 : 수평추락방지장치 No.1(345kV의령-하동화력#2T/L 병가)","2025-04-18 07:00","2025-04-18 18:00","2025-04-18 07:00","2025-04-18 18:00","연속"]
[846,"경남","진주","거창합천#2 T/L","합천S/S  거창-합천#2T/L GIS 보통점검 등","합천S/S  거창-합천#2T/L GIS 보통점검, LA(A,B,C) 보통점검, PT 대체","2025-04-02 10:00","2025-04-02 18:00","2025-04-02 10:00","2025-04-02 18:00","연속"]
[847,"경남","통영","거류거제#1 T/L"," 거류-거제#1T/L 추락방지장치 설치공사"," 거류-거제#1T/L 추락방지장치 설치공사","2025-04-12 07:00","2025-04-13 18:00","2025-04-12 07:00","2025-04-13 18:00","매일"]
[848,"경남","통영","신고성거류#2 T/L"," 고성-통영복합#2T/L 추락방지장치 설치공사(안전이격)"," 고성-통영복합#2T/L 추락방지장치 설치공사(안전이격)","2025-04-19 07:00","2025-04-19 18:00","2025-04-19 07:00","2025-04-19 18:00","연속"]
[849,"경남","통영","거류거제#1 T/L"," 거류-거제#1T/L 추락방지장치 설치공사"," 거류-거제#1T/L 추락방지장치 설치공사","2025-04-26 07:00","2025-04-27 18:00","2025-04-26 07:00","2025-04-27 18:00","매일"]
[850,"경남","통영","거류거제#2 T/L"," 고성-통영복합#2T/L 추락방지장치 설치공사(안전이격)"," 고성-통영복합#2T/L 추락방지장치 설치공사(안전이격)","2025-04-19 07:00","2025-04-19 18:00","2025-04-19 07:00","2025-04-19 18:00","연속"]
[851,"경남","통영","거류개폐소 SEC CB 60610","#60-61 SEC GIS 초기점검","#60-61 SEC GIS 초기점검","2025-04-25 09:30","2025-04-25 18:00","2025-04-25 09:30","2025-04-25 18:00","연속"]
[852,"경남","통영","거류거제#1 T/L"," 고성-통영복합#1T/L 추락방지장치 설치공사(안전이격)"," 고성-통영복합#1T/L 추락방지장치 설치공사(안전이격)","2025-04-20 07:00","2025-04-20 18:00","2025-04-20 07:00","2025-04-20 18:00","연속"]
[853,"경남","통영","신고성거류#1 T/L"," 고성-통영복합#1T/L 추락방지장치 설치공사(안전이격)"," 고성-통영복합#1T/L 추락방지장치 설치공사(안전이격)","2025-04-20 07:00","2025-04-20 18:00","2025-04-20 07:00","2025-04-20 18:00","연속"]
[854,"경남","통영","신고성삼천포#1 T/L"," 신고성-삼천포#1T/L 추락방지장치 설치공사"," 신고성-삼천포#1T/L 추락방지장치 설치공사","2025-04-05 07:00","2025-04-06 18:00","2025-04-05 07:00","2025-04-06 18:00","매일"]
[855,"경남","통영","삼천포사천#1 T/L"," 신고성-삼천포#1T/L 추락방지장치 설치공사(안전이격)"," 신고성-삼천포#1T/L 추락방지장치 설치공사(안전이격)","2025-04-05 07:00","2025-04-06 18:00","2025-04-05 07:00","2025-04-06 18:00","매일"]
[856,"경남","통영","신고성거류#2 T/L"," 신고성-거류#2T/L 조작시험 및 초기점검"," 신고성-거류#2T/L 조작시험 및 초기점검 (신고성S/S GIS : 조작시험, 거류개폐소 GIS : 초기점검)","2025-04-02 09:30","2025-04-02 18:00","2025-04-02 09:30","2025-04-02 18:00","연속"]
[857,"경남","통영","신고성거류#3 T/L"," 신고성-거류#3T/L 조작시험 및 초기점검"," 신고성-거류#3T/L 조작시험 및 초기점검 (신고성S/S GIS : 조작시험, 거류개폐소 GIS : 초기점검)","2025-04-07 09:30","2025-04-07 18:00","2025-04-07 09:30","2025-04-07 18:00","연속"]
[858,"경남","통영","신고성S/S SEC CB 65660","신고성S/S #60-61, #65-66 SEC GIS 조작시험","신고성S/S #60-61, #65-66 SEC GIS 조작시험","2025-04-04 14:00","2025-04-04 18:00","2025-04-04 14:00","2025-04-04 18:00","연속"]
[859,"경남","통영","신고성S/S SEC CB 60610","신고성S/S #60-61, #65-66 SEC GIS 조작시험","신고성S/S #60-61, #65-66 SEC GIS 조작시험","2025-04-04 09:30","2025-04-04 14:00","2025-04-04 09:30","2025-04-04 14:00","연속"]
[860,"경남","통영","신고성삼천포#1 T/L"," 신고성-삼천포#1T/L 조작시험 및 초기점검"," 신고성-삼천포#1T/L 조작시험 및 초기점검 (신고성S/S GIS : 조작시험, 삼천포S/S GIS : 보통점검)","취소","취소","취소","취소","연속"]
[861,"경남","통영","신고성거류#1 T/L"," 신고성-거류#1T/L 조작시험 및 초기점검"," 신고성-거류#1T/L 조작시험 및 초기점검 (신고성S/S GIS : 조작시험, 거류개폐소 GIS : 초기점검)","2025-04-01 09:30","2025-04-01 18:00","2025-04-01 09:30","2025-04-01 18:00","연속"]
[862,"경남","통영","신고성삼천포#2 T/L"," 신고성-삼천포#2T/L 조작시험 및 초기점검"," 신고성-삼천포#2T/L 조작시험 및 초기점검 (신고성S/S GIS : 조작시험, 삼천포S/S GIS : 보통점검)","취소","취소","취소","취소","연속"]
[863,"경남","통영","안정통영CC#2 T/L"," 안정-통영복합 #2T/L 조작시험 및 공기압력계 교체"," 안정-통영복합 #2T/L 조작시험 및 공기압력계 교체","2025-04-19 14:00","2025-04-19 18:00","2025-04-19 14:00","2025-04-19 18:00","연속"]
[864,"경남","통영","안정통영CC#1 T/L"," 안정-통영복합 #1T/L 조작시험"," 안정-통영복합 #1T/L 조작시험","2025-04-19 09:30","2025-04-19 14:00","2025-04-19 09:30","2025-04-19 14:00","연속"]
[865,"경남","통영","진동안정#1 T/L"," 진동-안정#1T/L 철탑추락방지장치 설치공사"," 진동-안정#1T/L 2~7호(6기) 수평형 추락방지장치 설치","2025-04-21 07:00","2025-04-21 18:00","취소","취소","연속"]
[866,"경남","통영","진동안정#2 T/L"," 진동-안정#2T/L 철탑추락방지장치 설치공사"," 진동-안정#2T/L 2~7호(6기) 수평형 추락방지장치 설치","2025-04-23 07:00","2025-04-23 18:00","취소","취소","연속"]
[867,"경남","통영","고성통영CC#2 T/L"," 고성-통영복합#2T/L 추락방지장치 설치공사"," 고성-통영복합#2T/L 추락방지장치 설치공사","2025-04-19 07:00","2025-04-19 18:00","2025-04-19 07:00","2025-04-19 18:00","연속"]
[868,"경남","통영","거류통영복합#1 T/L"," 거류-통영복합 #1T/L GIS 초기점검"," 거류-통영복합 #1T/L GIS 초기점검 (거류 개폐소 및 통영복합S/Y GIS : 초기점검)","2025-04-22 09:30","2025-04-22 18:00","2025-04-22 09:30","2025-04-22 18:00","연속"]
[869,"경남","통영","고성통영CC#1 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성-통영복합#1T/L 추락방지장치 설치공사(4/20)  고성분기T/L 추락방지장치 설치공사(4/21~22)","2025-04-20 07:00","2025-04-22 18:00","취소","취소","매일"]
[870,"경남","통영","거류통영복합#2 T/L"," 거류-통영복합 #2T/L GIS 초기점검"," 거류-통영복합 #2T/L GIS 초기점검 (거류 개폐소 및 통영복합S/Y GIS : 초기점검)","2025-04-24 09:30","2025-04-24 18:00","2025-04-24 09:30","2025-04-24 18:00","연속"]
[871,"경남","함안","가야사봉#2 T/L"," 가야-사봉#2T/L 수평 추락방지장치 설치"," 가야-사봉#2T/L 40~52기(13기) 수평형 추락방지장치(와이어형) 설치","2025-04-19 07:00","2025-04-20 18:00","2025-04-19 07:00","2025-04-20 18:00","매일"]
[872,"경남","함안","가야사봉#1 T/L"," 가야-사봉#1T/L 수평 추락방지장치 설치"," 가야-사봉#1T/L 40~52기(13기) 수평형 추락방지장치(와이어형) 설치","2025-04-19 07:00","2025-04-20 18:00","2025-04-19 07:00","2025-04-20 18:00","매일"]
[873,"경남","함안","서마산진동#1 T/L"," 서마산-진동#1T/L 철탑추락방지장치 설치공사"," 서마산-진동#1T/L 1~44호(43기) 수평형 추락방지장치 설치 및 폴리머 점퍼지지애자[9,10,16,33~36,42호(8기)] 설치","2025-04-21 07:00","2025-04-22 18:00","취소","취소","매일"]
[874,"경남","함안","서마산진동#2 T/L"," 서마산-진동#2T/L 철탑추락방지장치 설치공사"," 서마산-진동#2T/L 1~44호(43기) 수평형 추락방지장치 설치 및 폴리머 점퍼지지애자[11,15,16,19,21,25,27,34,39,42호(10기)] 설치","2025-04-23 07:00","2025-04-24 18:00","취소","취소","매일"]
[875,"경남","함안","진영수산#1 T/L"," 진영-수산#1T/L 철탑추락방지장치 설치공사"," 진영-수산#1T/L 27호(1기) 수평형 추락방지장치 설치 ※ 동읍-진영#1,2T/L 병행휴전 필요","2025-04-25 07:00","2025-04-25 18:00","2025-04-25 07:00","2025-04-25 18:00","연속"]
[876,"경남","함안","신마산S/S SEC CB 60610","신마산S/S  #60-#61 SEC CB 보통점검","신마산S/S  #60-#61 SEC CB 보통점검","2025-04-09 09:30","2025-04-09 17:30","2025-04-09 09:30","2025-04-09 17:30","연속"]
[877,"경남","함안","신마산S/S CB 6100","신마산S/S  #60-#65 BUS TIE CB 보통점검","신마산S/S  #60-#65 BUS TIE CB 보통점검","2025-04-25 09:30","2025-04-25 17:30","2025-04-25 09:30","2025-04-25 17:30","연속"]
[878,"경남","함안","신마산중리#1 T/L","신마산S/S 신마산중리#1 T/L GCB 보통점검","신마산S/S 신마산중리#1 T/L GCB 보통점검","2025-04-22 09:30","2025-04-22 17:30","2025-04-22 09:30","2025-04-22 17:30","연속"]
[879,"경남","함안","신마산S/S #61 BUS","신마산S/S 옥외철구설비 GIS화 공사","-  #63M.Tr 이설분 시험가압(24H)","2025-04-22 09:00","2025-04-23 14:00","2025-04-22 09:00","2025-04-23 14:00","연속"]
[880,"경남","함안","신마산S/S SEC CB 65660","신마산S/S  #65-#66 SEC CB 보통점검","신마산S/S  #65-#66 SEC CB 보통점검","2025-04-10 09:30","2025-04-10 17:30","2025-04-10 09:30","2025-04-10 17:30","연속"]
[881,"경남","함안","신마산S/S #61 BUS","신마산S/S 옥외철구설비 GIS화 공사","-  임시GIS, #61M.Tr, 23kV EGIS 시험가압(24H) - #66BUS 및  임시GIS 연결","2025-04-02 08:00","2025-04-03 13:00","2025-04-02 08:00","2025-04-03 13:00","연속"]
[882,"경남","함안","신마산S/S CB 6200","신마산S/S  #61-#66 BUS TIE CB 보통점검","신마산S/S  #61-#66 BUS TIE CB 보통점검","2025-04-28 09:30","2025-04-28 17:30","2025-04-28 09:30","2025-04-28 17:30","연속"]
[883,"경남","함안","신마산S/S #66 BUS","신마산S/S 옥외철구설비 GIS화 공사","-  임시GIS, #61M.Tr, 23kV EGIS 시험가압(24H) - #66BUS 및  임시GIS 연결","2025-04-03 13:00","2025-04-04 18:00","2025-04-03 13:00","2025-04-04 18:00","연속"]
[884,"경남","함안","중리가야#2 T/L"," 중리-가야#2T/L 피뢰기 설치공사"," 중리-가야#2T/L 44호(1기) 피뢰기 설치 및 4회선 병가철탑(수직배열) 동시휴전","2025-04-16 07:00","2025-04-16 18:00","2025-04-16 07:00","2025-04-16 18:00","연속"]
[885,"경남","함안","중리가야#1 T/L"," 중리-가야#1T/L 피뢰기 설치공사"," 중리-가야#1T/L 11~52호(42기) 피뢰기 설치","2025-04-15 07:00","2025-04-18 18:00","2025-04-15 07:00","2025-04-18 18:00","매일"]
[886,"경남","함안","신마산중리#2 T/L"," 신마산-중리#2T/L 피뢰기 설치공사"," 신마산-중리#2T/L 9~32호(24기) 피뢰기 설치","2025-04-14 07:00","2025-04-15 18:00","2025-04-14 07:00","2025-04-15 18:00","매일"]