{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":11,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":16,"n_cols":12,"rows_kept":16,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 5월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #4 M.Tr","신가평S/S  #4M.Tr 복구공사","신가평S/S  #4M.Tr 복구공사 -  M.Tr 반입","2025-05-08 09:00","2025-05-21 18:00","2025-05-08 09:00","2025-05-21 18:00","연속"]
[2,"경기북부","구리","신가평S/S CB 8300","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사 - 신태백#2T/L-#2M.Tr 1차 TIE GIS(8300) 단독차단기 보통점검 - 점검공사 공기 단축 시 시행예정","2025-05-30 09:00","2025-05-31 18:00","2025-05-30 09:00","2025-05-31 18:00","연속"]
[3,"경기북부","구리","신가평S/S CB 8371","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사 - 신태백-신가평#2T/L GIS(8371) 단독차단기 보통점검","2025-05-28 09:00","2025-05-29 18:00","2025-05-28 09:00","2025-05-29 18:00","연속"]
[4,"경기북부","구리","신가평S/S CB 8471","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사 - 신태백-신가평#1T/L GIS(8471) 단독차단기 보통점검","2025-05-26 09:00","2025-05-27 18:00","2025-05-26 09:00","2025-05-27 18:00","연속"]
[5,"경기북부","구리","신안성신가평 T/L"," 신안성-신가평 등 12개T/L 추락방지시설 설치공사"," 신안성-신가평T/L 고광도 항공장애등 설치 : No.131,132,146,147","2025-05-26 07:00","2025-05-29 18:00","취소","취소","연속"]
[6,"경기북부","구리","신가평S/S CB 8571","2025년 신가평S/S  GIS 점검공사","2025년 신가평S/S  GIS 점검공사 - 신안성-신가평T/L GIS(8571) 단독차단기 보통점검","2025-05-22 09:00","2025-05-23 18:00","2025-05-22 09:00","2025-05-23 18:00","연속"]
[7,"충북","직할","신중부S/S #3 M.Tr","신중부S/S  #3M.Tr 보통점검 공사","신중부S/S  #3M.Tr 보통점검","2025-05-26 09:00","2025-05-30 18:00","2025-05-26 09:00","2025-05-30 18:00","연속"]
[8,"대전세종충남","서산","당진T/P CB 8471","25년 서산P/O  GIS 보통점검공사","(4월휴전취소시) (즉시가압가능) 당진TP  신서산-당진TP 8471 GIS 보통점검","2025-05-21 09:30","2025-05-22 18:00","취소","취소","연속"]
[9,"대전세종충남","서산","당진T/P CB 8400","25년 서산P/O  GIS 보통점검공사","(4월 휴전 취소시) (즉시가압가능) 당진TP  신서산#2TL-4호기 TIE 8400 GIS 보통점검","2025-05-19 09:30","2025-05-20 18:00","취소","취소","연속"]
[10,"대전세종충남","서산","당진T/P CB 8100","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 당진TP  #1Tie-Tr Tie 8100 GIS 보통점검","2025-05-14 09:30","2025-05-15 18:00","2025-05-14 09:30","2025-05-15 18:00","연속"]
[11,"대전세종충남","서산","당진T/P CB 8171","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 당진TP  #1Tie-Tr 8171 GIS 보통점검","2025-05-12 09:30","2025-05-13 18:00","2025-05-12 09:30","2025-05-13 18:00","연속"]
[12,"경북","영주","신한울N/P #1 M.Tr","신한울S/S 345kV GIS 용량교체공사","동해안변환소 건설 관련 기존설비 용량증대(345kV GIS x 2식 교체)","2025-05-08 08:00","2025-06-13 18:00","2025-05-08 08:00","2025-06-13 18:00","연속"]

{"sheet":"345설비","index":1,"n_rows":353,"n_cols":12,"rows_kept":353,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2025년도 5월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#4 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 보통점검","2025-05-26 09:00","2025-05-28 18:00","2025-05-26 09:00","2025-05-28 18:00","연속"]
[2,"서울","성동","성동S/S #1 Sh.R CB","2025년 성동P/O 변전협력회사 공사","-  GIS 보통점검","2025-05-20 09:00","2025-05-21 18:00","2025-05-20 09:00","2025-05-21 18:00","연속"]
[3,"서울","성동","성동S/S #3 M.Tr","2025년 성동P/O 변전협력회사 공사","-  GIS 보통점검 - 154kV GIS 조작시험","2025-05-26 09:00","2025-05-28 18:00","2025-05-26 09:00","2025-05-28 18:00","연속"]
[4,"서울","성동","성동S/S #2 M.Tr","2025년 성동P/O 변전협력회사 공사","- 154kV GIS 보통점검","2025-05-19 09:00","2025-05-19 18:00","2025-05-19 09:00","2025-05-19 18:00","연속"]
[5,"서울","성동","성동S/S CB 7400","2025년 성동P/O 변전협력회사 공사","-  GIS 보통점검","2025-05-26 09:00","2025-05-28 18:00","2025-05-26 09:00","2025-05-28 18:00","연속"]
[6,"서울","성동","성동S/S #1 M.Tr","2025년 성동P/O 변전협력회사 공사","-  GIS 보통점검 - 154kV GIS 보통점검","2025-05-22 09:00","2025-05-23 18:00","2025-05-22 09:00","2025-05-23 18:00","연속"]
[7,"서울","중부","중부S/S #4 M.Tr","2025년 중부S/S 154kV 장기사용 GIS 교체공사(2차)","- 154kV #65BUS 모선 무부하가압용","2025-05-21 17:00","2025-05-22 09:00","2025-05-21 17:00","2025-05-22 09:00","연속"]
[8,"서울","중부","중부S/S #4 M.Tr","2025년 중부S/S 154kV 장기사용 GIS 교체공사(2차)","- 154kV #60BUS 모선 무부하가압용","2025-05-30 17:00","2025-06-02 09:00","2025-05-30 17:00","2025-06-02 09:00","연속"]
[9,"남서울","동서울","동서울S/S #2 Sh.R CB","세니온제 Sh.R 보호배전반 성능개선","- Sh.R 보호계전기 펌웨어 업데이트 - 보호계전기 개체 및 연동시험","2025-05-08 13:00","2025-05-08 18:00","2025-05-08 13:00","2025-05-08 18:00","연속"]
[10,"남서울","영등포","신시흥신광명#1 T/L"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-05-01 09:00","2025-06-27 18:00","2025-05-01 09:00","2025-06-27 18:00","연속"]
[11,"남서울","영등포","신광명S/S CB 7272","24~25년 영등포전력지사 변전협력회사 공사"," GCB 조작시험","2025-05-12 09:00","2025-05-13 18:00","2025-05-12 09:00","2025-05-13 18:00","연속"]
[12,"남서울","영등포","신광명S/S #3 M.Tr","신광명S/S #3M.Tr 주변압기 절연유 채유 및 절연열화 측정","1,2차 부싱 절연유 채유 및 절연열화 측정","2025-05-07 09:00","2025-05-07 18:00","2025-05-07 09:00","2025-05-07 18:00","연속"]
[13,"남서울","영등포","신광명S/S #4 M.Tr","24~25년 영등포전력지사 변전협력회사 공사","3차측 EGIS PT Bay 누기 보수","2025-05-01 09:00","2025-05-02 18:00","2025-05-01 09:00","2025-05-02 18:00","연속"]
[14,"남서울","직할","신문래S/S #1 M.Tr","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS)","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS)","2025-05-19 09:00","2025-05-21 14:00","2025-05-19 09:00","2025-05-21 14:00","연속"]
[15,"남서울","직할","신문래S/S #3 M.Tr","170kV GIS 정밀점검 공사(신문래#3M.Tr 2차)","170kV GIS 정밀점검 공사(신문래#3M.Tr 2차)","2025-05-21 14:00","2025-05-23 18:00","2025-05-21 14:00","2025-05-23 18:00","연속"]
[16,"인천","김포","신김포S/S CB 7100","신김포S/S  7100 CB 보통점검","신김포S/S  #1Sh.R-TIE GIS(7100) 보통점검","2025-05-12 10:00","2025-05-12 18:00","2025-05-12 10:00","2025-05-12 18:00","연속"]
[17,"인천","김포","신김포S/S CB 7200","신김포S/S  7200 CB 보통점검","신김포S/S  #2Sh.R-#4Sh.R 1차 TIE GIS(7200) 보통점검","2025-05-07 10:00","2025-05-07 18:00","2025-05-07 10:00","2025-05-07 18:00","연속"]
[18,"인천","김포","신김포S/S CB 7600","신김포S/S  7600 CB 보통점검","신김포S/S  #3Sh.R-TIE GIS(7600) 보통점검","2025-05-08 10:00","2025-05-08 18:00","2025-05-08 10:00","2025-05-08 18:00","연속"]
[19,"인천","김포","신김포S/S CB 7171","신김포S/S  7171 CB 보통점검","신김포S/S  #1 Sh.R 1차 GIS(7171) 보통점검","2025-05-09 10:00","2025-05-09 18:00","2025-05-09 10:00","2025-05-09 18:00","연속"]
[20,"인천","부평","서인천C/C #2 Sh.R CB","서인천복합S/Y #2SH.R 보통점검","서인천복합S/Y #2SH.R 보통점검","2025-05-02 09:00","2025-05-02 18:00","2025-05-02 09:00","2025-05-02 18:00","연속"]
[21,"인천","부평","서인천C/C #3 M.Tr","#3M.Tr 부싱유 채유","#3M.Tr 부싱유 채유","2025-05-30 09:00","2025-05-30 18:00","2025-05-26 09:00","2025-05-26 18:00","연속"]
[22,"인천","부평","서인천C/C CB 7300","서인천신부평#2T/L-#3M.Tr TIE 7300 GIS 보통점검","서인천신부평#2T/L-#3M.Tr TIE 7300 GIS 보통점검","2025-05-29 09:00","2025-05-29 18:00","2025-05-31 09:00","2025-05-31 18:00","연속"]
[23,"인천","부평","서인천C/C CB 7200","신경서서인천CCT/L-#2M.Tr 1차 TIE 7200 GIS 보통점검","신경서서인천CCT/L-#2M.Tr 1차 TIE 7200 GIS 보통점검","2025-05-27 09:00","2025-05-27 18:00","2025-05-27 09:00","2025-05-27 18:00","연속"]
[24,"인천","부평","서인천C/C CB 7271"," 신경서-서인천CC T/L 7271 GIS 보통점검"," 신경서-서인천CC T/L 7271 GIS 보통점검","2025-05-26 09:00","2025-05-26 18:00","2025-05-27 09:00","2025-05-27 18:00","연속"]
[25,"인천","부평","서인천C/C CB 7371"," 서인천CC-신부평#2T/L 7371 GIS 보통점검"," 서인천CC-신부평#2T/L 7371 GIS 보통점검","2025-05-20 09:00","2025-05-20 18:00","2025-05-20 09:00","2025-05-20 18:00","연속"]
[26,"인천","부평","서인천C/C #70 BUS"," #70BUS 모선보호반 교체"," #70BUS 모선보호반 교체","2025-05-19 09:00","2025-05-23 18:00","취소","취소","연속"]
[27,"인천","부평","서인천C/C #2 M.Tr"," #2M.Tr 부싱유 채유, 6244 GIS 보통점검"," #2M.Tr 부싱유 채유, 6244 GIS 보통점검","2025-05-15 09:00","2025-05-15 18:00","2025-05-15 09:00","2025-05-15 18:00","연속"]
[28,"인천","부평","서인천C/C #4 Sh.R CB","서인천C/C  #4 Sh.R 보통점검","서인천C/C  #4 Sh.R 보통점검","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[29,"인천","부평","서인천C/C #1 M.Tr","서인천C/C  #1 M.Tr 휴전작업","서인천C/C  #1 M.Tr 보통점검. 부싱절연유 채유, 기계적보호장치 교체 96P(퀄리트롤), D(퀄리트롤), 누유 보수  #1 M.Tr 1차 7172 GIS 조작시험,  #1 M.Tr 1차 7100 GIS 조작시험 ,서인천C/C  #1 M.Tr 2차 6144 GIS 보통점검, 서인천복합 #1M.Tr 부싱 염해방지도포","2025-05-07 09:00","2025-05-10 18:00","2025-05-07 09:00","2025-05-10 18:00","연속"]
[30,"인천","부평","신가좌신시흥#2 T/L","신가좌S/S 신가좌-신시흥#2T/L 7491ES A상 투입불량 보수","신가좌S/S  신가좌-신시흥#2T/L 7491ES A상 투입불량 보수","2025-05-26 09:00","2025-05-29 18:00","취소","취소","연속"]
[31,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S  #2 M.Tr 보통점검","신가좌S/S  #2 M.Tr 보통점검","2025-05-19 09:00","2025-05-22 18:00","취소","취소","연속"]
[32,"인천","부평","신가좌가정#1 T/L","#70BUS 누기 관련 크레인 이격거리 확보","#70BUS 누기 관련 크레인 이격거리 확보","2025-05-12 09:00","2025-05-12 18:00","취소","취소","연속"]
[33,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S #4M.Tr 점검 작업"," #4M.Tr 보통점검 1차 피뢰기 보통점검, 2차피뢰기, 3차 피뢰기 보통점검, CVT, 3차 PT 보통점검 6444 GIS 보통점검, 베어링 발청 조치 1차, 2차 부싱, CVT 금구류 교체 B상 변압기 누유 보수 3차 4479, 4479-1, 4479-2, 4489 VCB 보통점검","2025-05-03 09:00","2025-05-06 18:00","취소","취소","연속"]
[34,"인천","부평","신가좌S/S #1 BUS","신가좌S/S #70BUS 누기 관련 긴급 조치 공사","신가좌S/S #70BUS 누기 관련 긴급 조치 공사","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[35,"인천","부평","신경서S/S CB 7472"," 신경서-서인천CCT/L 7472 GIS 보통점검"," 신경서-서인천CCT/L 7472 GIS 보통점검, 전자변 교체","2025-05-21 09:00","2025-05-21 18:00","2025-05-21 09:00","2025-05-21 18:00","연속"]
[36,"인천","부평","신경서S/S #1 Sh.R CB","신경서  #1 Sh.R 보통점검","신경서  #1 Sh.R 보통점검","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[37,"인천","부평","신경서인천CC#2 T/L","신경서S/S 신경서인천CC#2T/L용 CLR 볼트 교체","신경서S/S 신경서인천CC#2T/L용 CLR 볼트 교체 신경서S/S 신경서-인천CC#2T/L 7372GIS 조작 인천CC 신경서인천CC#2-가정인천CC#1T/L TIE 7400 GIS 조작","2025-05-30 09:00","2025-05-30 18:00","2025-05-30 09:00","2025-05-30 18:00","연속"]
[38,"인천","부평","신경서S/S CB 7272"," #2 M.Tr 1차 7272 GIS 보통점검"," #2 M.Tr 1차 7272 GIS 보통점검","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[39,"인천","부평","신인천C/C CB 7772","신인천C/C  4MT101 7772 GIS 보통점검","신인천C/C  4MT101 7772 GIS 보통점검","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[40,"인천","부평","신인천C/C CB 7900"," 4MT001 TIE 7900 GIS 보통점검"," 4MT001 TIE 7900 GIS 보통점검","2025-05-07 09:00","2025-05-07 18:00","2025-05-07 09:00","2025-05-07 18:00","연속"]
[41,"인천","부평","신인천C/C CB 7872","신인천C/C  4MT201 7872 GIS 보통점검","신인천C/C  4MT201 7872 GIS 보통점검","2025-05-19 09:00","2025-05-19 18:00","2025-05-19 09:00","2025-05-19 18:00","연속"]
[42,"인천","부평","신인천C/C CB 7972"," 4MT001 7972 GIS 보통점검"," 4MT001 7972 GIS 보통점검","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[43,"인천","부평","신인천C/C CB 7671","신인천C/C  3MT001 7671 GIS 보통점검","신인천C/C  3MT001 7671 GIS 보통점검","2025-05-01 09:00","2025-05-01 18:00","2025-05-01 09:00","2025-05-01 18:00","연속"]
[44,"인천","부평","인천C/C CB 7471","인천복합S/Y  신경서-인천CC#2T/L 7471 정밀점검","인천복합S/Y  신경서-인천CC#2T/L 7471 정밀점검","2025-05-26 09:00","2025-05-30 18:00","취소","취소","연속"]
[45,"인천","부평","가정인천CC#1 T/L"," 가정-인천CC #1T/L 접속함 발열 하자보수공사","접속함(J/B#2) A상 발열 관련 하자보수 공사","2025-05-17 09:00","2025-05-18 18:00","취소","취소","연속"]
[46,"인천","부평","가정인천CC#1 T/L","#1Sh.R 7279 GIS 부싱 C상 누기 보수 bypass 조작","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수 bypass 조작","2025-05-17 09:00","2025-05-17 18:00","2025-05-17 09:00","2025-05-17 18:00","연속"]
[47,"인천","부평","인천C/C SEC CB 70710","인천복합S/Y  #70-71 SEC GIS 정밀점검","인천복합S/Y  #70-71 SEC GIS 정밀점검","2025-05-19 09:00","2025-05-23 18:00","2025-05-19 09:00","2025-05-23 18:00","연속"]
[48,"인천","부평","가정인천CC#2 T/L","가정인천CC#2T/L 염해방지 코팅공사","가정인천CC#2T/L 염해방지 코팅공사","2025-05-24 09:00","2025-05-24 18:00","2025-05-24 09:00","2025-05-24 18:00","연속"]
[49,"인천","부평","인천C/C #70 BUS","인천복합S/Y  #70-71 SEC GIS 정밀점검 무부하가압","인천복합S/Y  #70-71 SEC GIS 정밀점검 무부하가압","2025-05-23 14:00","2025-05-23 18:00","2025-05-23 14:00","2025-05-23 18:00","연속"]
[50,"인천","부평","인천C/C #2 M.Tr","인천CC S/Y  #2 TIE Tr 보통점검","인천CC S/Y  #2 TIE Tr 보통점검","2025-05-26 09:00","2025-05-29 18:00","취소","취소","연속"]
[51,"인천","부평","인천C/C #1 M.Tr","인천복합 #1Tie Tr 부싱유 채유","인천복합 #1Tie Tr 부싱유 채유","2025-05-17 09:00","2025-05-17 18:00","취소","취소","연속"]
[52,"인천","부평","가정인천CC#1 T/L","#1Sh.R 7279 GIS 부싱 C상 누기 보수 bypass 조작","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수 bypass 조작","2025-05-10 09:00","2025-05-10 18:00","2025-05-10 09:00","2025-05-10 18:00","연속"]
[53,"인천","부평","인천C/C #1 Sh.R CB","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수","인천복합S/Y #1Sh.R 7279 GIS 부싱 C상 누기 보수","2025-05-12 09:00","2025-05-14 18:00","취소","취소","연속"]
[54,"인천","부평","신경서포스코CC#2 T/L"," 포스코SY신경서#2T/L CLR용 부싱 염해방지"," 포스코SY신경서#2T/L CLR용 부싱 염해방지","2025-05-09 09:00","2025-05-09 18:00","2025-05-09 09:00","2025-05-09 18:00","연속"]
[55,"인천","부평","포스코C/C CB 7172","포스코S/Y  #71Bay B/F 보호반 교체","포스코S/Y  #71Bay B/F 보호반 교체","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[56,"인천","부평","인천CC포스코CC#1 T/L","포스코S/Y  #71Bay B/F 보호반 교체","포스코S/Y  #71Bay B/F 보호반 교체","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[57,"인천","부평","신경서포스코CC#1 T/L","신경서포스코SY#1 T/L 염해방지 코팅","신경서포스코SY#1 T/L 염해방지 코팅","2025-05-17 09:00","2025-05-17 18:00","2025-05-17 09:00","2025-05-17 18:00","연속"]
[58,"인천","시흥","신시흥#2S/S #4 M.Tr","신시흥S/S #4M.Tr 1차 부싱 부싱유 채유","신시흥S/S #4M.Tr 1차 부싱 부싱유 채유 (A상)","2025-05-12 08:00","2025-05-12 18:00","2025-05-12 08:00","2025-05-12 18:00","연속"]
[59,"인천","시흥","영흥T/P CB 7171","영흥#1S/Y 362kV GIS 정밀점검 공사(7171)","영흥#1S/Y 7171 CB 정밀점검 공사","2025-05-06 08:00","2025-05-09 18:00","2025-05-06 08:00","2025-05-10 18:00","연속"]
[60,"인천","시흥","영흥1TP영흥2TP#1 T/L","영흥#1S/Y 362kV GIS 정밀점검 무부하가압(7171)","영흥#1S/Y 7171 CB 정밀점검 무부하가압","2025-05-09 10:00","2025-05-09 12:00","2025-05-10 08:00","2025-05-10 12:00","연속"]
[61,"인천","시흥","영흥T/P CB 7372","영흥#1S/Y 362kV GIS 정밀점검 공사(7372)","영흥#1S/Y 7372 CB 정밀점검 공사","2025-05-12 08:00","2025-05-16 18:00","2025-05-12 08:00","2025-05-16 18:00","연속"]
[62,"인천","시흥","영흥T/P CB 7371","영흥#1S/Y 362kV GIS 정밀점검 공사(7371)","영흥#1S/Y 7371 CB 정밀점검 공사","2025-05-19 08:00","2025-05-23 18:00","2025-05-19 08:00","2025-05-23 18:00","연속"]
[63,"인천","시흥","신시화영흥TP#2 T/L","영흥#1S/Y 362kV GIS 정밀점검 공사(7571) 무부하가압","영흥#1S/Y 7571 CB 정밀점검 공사 무부하가압","2025-05-29 10:00","2025-05-29 12:00","2025-05-28 12:00","2025-05-28 18:00","연속"]
[64,"인천","시흥","영흥T/P CB 7571","영흥#1S/Y 362kV GIS 정밀점검 공사(7571)","영흥#1S/Y 7571 CB 정밀점검 공사","2025-05-26 08:00","2025-05-29 18:00","2025-05-26 08:00","2025-05-28 18:00","연속"]
[65,"인천","직할","신부평S/S #1 M.Tr","신부평S/S #1M.Tr 여과작업(2일 소요)","신부평S/S #1M.Tr 여과작업(2일 소요)","2025-05-29 09:30","2025-05-30 18:00","2025-05-26 09:30","2025-05-28 18:00","연속"]
[66,"경기북부","고양","신파주신덕은#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치(수평) 설치","2025-05-07 07:00","2025-05-12 17:00","취소","취소","연속"]
[67,"경기북부","고양","신파주S/S #2 M.Tr","신파주S/S 장기사용 노후 배전반 교체","#73 Bay B/F 보호반 교체공사","2025-05-12 09:00","2025-05-16 18:00","2025-05-12 09:00","2025-05-16 18:00","연속"]
[68,"경기북부","고양","신파주양주#1 T/L","신파주S/S 장기사용 노후 배전반 교체","#73 Bay B/F 보호반 교체공사","2025-05-12 09:00","2025-05-16 18:00","2025-05-12 09:00","2025-05-16 18:00","연속"]
[69,"경기북부","고양","신파주S/S #1 M.Tr","24~25년 고양전력지사 변전협력회사 공사","362kV GIS 보통점검(7200TIE,  #1M.Tr 1차(7272))","2025-05-26 09:00","2025-05-28 18:00","2025-05-26 09:00","2025-05-28 18:00","연속"]
[70,"경기북부","구리","미금S/S CB 7572","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검(7572CB)","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[71,"경기북부","구리","신포천S/S CB 7471","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 362kV GIS 점검(7471CB)","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[72,"경기북부","구리","신포천S/S CB 7372","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 362kV GIS 점검(7372CB)","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[73,"경기북부","구리","신포천S/S CB 7300","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 362kV GIS 점검(7300CB)","2025-05-09 09:00","2025-05-09 18:00","2025-05-09 09:00","2025-05-09 18:00","연속"]
[74,"경기북부","구리","신포천S/S CB 7371","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 362kV GIS 점검(7371CB)","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[75,"경기북부","구리","신포천S/S CB 7272","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 362kV GIS 점검(7272CB)","2025-05-07 09:00","2025-05-07 18:00","2025-05-07 09:00","2025-05-07 18:00","연속"]
[76,"경기북부","구리","신포천S/S CB 7200","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 362kV GIS 점검(7200CB)","2025-05-02 09:00","2025-05-02 18:00","2025-05-02 09:00","2025-05-02 18:00","연속"]
[77,"경기북부","구리","신포천S/S #3 M.TR","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  M.Tr 점검","2025-05-14 09:00","2025-05-16 18:00","2025-05-14 09:00","2025-05-16 18:00","연속"]
[78,"경기북부","구리","신포천S/S CB 7672","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소 362kV GIS 점검(7672CB)","2025-05-19 09:00","2025-05-19 18:00","2025-05-19 09:00","2025-05-19 18:00","연속"]
[79,"경기북부","직할","동두천C/C CB 7300","24-25년 직할 변전 협력회사 총액공사","73Bay GIS LCP 및 B/F반 교체","2025-05-14 09:00","2025-06-05 18:00","2025-05-14 09:00","2025-06-05 18:00","연속"]
[80,"경기북부","직할","신덕은동두천CC#2 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 신덕은-동두천CC#2T/L 불량애자 교체, 남면-백석#1T/L 피뢰기 설치 병가구간","2025-05-12 07:00","2025-05-16 18:00","취소","취소","매일"]
[81,"경기북부","직할","신포천동두천CC#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 신덕은-동두천CC#2T/L 불량애자 교체","2025-05-12 07:00","2025-05-12 13:00","취소","취소","연속"]
[82,"경기북부","직할","동두천C/C CB 7272","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","동두천CC 7272 GIS 보통점검 공사","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[83,"경기북부","직할","동두천C/C CB 7172","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","동두천CC 7172 GIS 보통점검 공사","2025-05-19 09:00","2025-05-19 18:00","2025-05-19 09:00","2025-05-19 18:00","연속"]
[84,"경기북부","직할","동두천C/C CB 7372","24-25년 직할 변전 협력회사 총액공사","73Bay GIS LCP 및 B/F반 교체","2025-05-14 09:00","2025-06-05 18:00","2025-05-14 09:00","2025-06-05 18:00","연속"]
[85,"경기북부","직할","동두천C/C CB 7472","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","동두천CC 7472 GIS CB 정밀점검 공사","2025-05-28 14:00","2025-05-30 18:00","2025-05-28 14:00","2025-05-30 18:00","연속"]
[86,"경기북부","직할","동두천C/C CB 7400","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","동두천CC 7400 TIE GIS CB 정밀점검 공사","2025-05-26 09:00","2025-05-28 14:00","2025-05-26 09:00","2025-05-28 14:00","연속"]
[87,"경기북부","직할","신의정부S/S #1 M.Tr","직할 170kV GIS 점검공사","170kV GIS 보통점검","2025-05-26 09:00","2025-05-26 18:00","2025-05-26 09:00","2025-05-26 18:00","연속"]
[88,"경기북부","직할","신의정부S/S #2 M.Tr","직할 170kV GIS 점검공사","170kV GIS 보통점검","2025-05-27 09:00","2025-05-27 18:00","2025-05-27 09:00","2025-05-27 18:00","연속"]
[89,"경기북부","직할","신의정부S/S #3 M.Tr","직할 170kV GIS 점검공사","170kV GIS 보통점검","2025-05-28 09:00","2025-05-28 18:00","2025-05-28 09:00","2025-05-28 18:00","연속"]
[90,"경기북부","직할","신의정부S/S #4 M.Tr","24-25년도 직할 변전협력회사 총액공사","신의정부S/S #4M.Tr 및 예비M.Tr 부싱절연유 채유","2025-05-30 09:00","2025-05-30 18:00","2025-05-30 09:00","2025-05-30 18:00","연속"]
[91,"경기북부","직할","양주중부#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치설치, 불량애자교체","2025-05-19 07:00","2025-05-20 17:00","2025-05-19 07:00","2025-05-20 17:00","연속"]
[92,"경기북부","직할","양주S/S CB 7300","양주S/S 동두천CC-양주T/L 증설공사"," CB 증설 2대, CLR 설치 2조 (CB 7300)","2025-05-26 09:00","2025-12-19 18:00","2025-05-26 09:00","2025-12-19 18:00","연속"]
[93,"경기북부","직할","양주S/S #2 BUS","양주S/S 동두천CC-양주T/L 증설공사"," CB 증설 2대, CLR 설치 2조","2025-05-26 09:00","2025-05-30 18:00","2025-05-26 09:00","2025-05-30 18:00","연속"]
[94,"경기북부","직할","양주S/S #3 M.Tr","양주S/S 동두천CC-양주T/L 증설공사(무부하용)"," CB 증설 2대, CLR 설치 2조","2025-05-30 09:00","2025-05-30 18:00","2025-05-30 09:00","2025-05-30 18:00","연속"]
[95,"경기북부","직할","양주S/S #4 M.Tr","'24-25년 변전협력회사 총액공사","부싱절연유 채유 및 추락방지 안전장치 설치","2025-05-15 08:00","2025-05-16 18:00","2025-05-15 08:00","2025-05-16 18:00","연속"]
[96,"경기북부","직할","신파주양주#2 T/L","양주S/S 동두천CC-양주T/L 증설공사(무부하용)"," CB 증설 2대, CLR 설치 2조","2025-05-30 09:00","2025-05-30 18:00","2025-05-30 09:00","2025-05-30 18:00","연속"]
[97,"경기북부","직할","양주중부#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치설치","2025-05-21 07:00","2025-05-23 17:00","2025-05-21 07:00","2025-05-23 17:00","연속"]
[98,"경기북부","직할","양주S/S #4 Sh.R CB","25-26 변전협력 총액공사","362kV 7672 GIS 개폐타임 측정","2025-05-15 09:00","2025-05-15 18:00","2025-05-15 09:00","2025-05-15 18:00","연속"]
[99,"경기북부","직할","양주S/S #1 M.Tr","'24-25년 변전협력회사 총액공사","부싱절연유 채유 및 ofu필터 교체, 23kV #1Sh.R점검 등","2025-05-12 08:00","2025-05-14 18:00","2025-05-12 08:00","2025-05-14 18:00","연속"]
[100,"경기","군포","서서울#2S/S #1 BUS","서서울#2S/S  #1BUS 가스누기 보수작업","서서울#2S/S  #1BUS 가스누기 보수작업 시행","2025-05-26 09:00","2025-05-30 18:00","2025-05-26 09:00","2025-05-30 18:00","연속"]
[101,"경기","군포","서서울#2S/S #6 M.Tr","서서울#2S/S #6M.Tr 1차GIS 보통,2차GIS 유사고장 점검","서서울#2S/S  #6M.Tr 7B00 GIS 보통점검, 2차 GIS 유사고장 점검(효성제 발청) 시행","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[102,"경기","군포","화성서서울#1 T/L","서서울#2S/S 서서울2-화성#1T/L 7C71,7C00 GIS 보통점검","서서울#2S/S  서서울2-화성#1T/L 7C71,7C00 GIS 보통점검 시행","2025-05-09 09:00","2025-05-09 18:00","취소","취소","연속"]
[103,"경기","군포","화성서서울#2 T/L","서서울#2S/S 서서울2-화성#2T/L 7D71,7D00 GIS 보통점검","서서울#2S/S  서서울2-화성#2T/L 7D71,7D00 GIS 보통점검 시행","2025-05-02 09:00","2025-05-02 18:00","취소","취소","연속"]
[104,"경기","군포","서서울#2S/S #5 M.Tr","서서울#2S/S #5M.Tr 1차GIS 보통, 2차GIS 유사고장 점검","서서울#2S/S  #5M.Tr 7A00 GIS 보통점검, 2차 GIS 유사고장 점검(효성제 발청) 시행","2025-05-07 09:00","2025-05-07 18:00","2025-05-07 09:00","2025-05-07 18:00","연속"]
[105,"경기","군포","서서울S/S #1 M.Tr","서서울S/S #1M.Tr GIS 조작,3차PT 초기,추락방지장치 설치","서서울S/S  #1M.Tr 7300,7372 GIS 조작시험, 3차 GPT 초기점검, 변압기 추락방지장치 설치 시행","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[106,"경기","군포","서서울S/S #3 M.Tr","서서울S/S #3M.Tr 1차GIS 보통,3차PT 초기,CVT 대체","서서울S/S  #3M.Tr 7600,7672 GIS 보통점검 ,3차 GPT 초기점검, CVT 대체, 변압기 추락방지장치 설치 시행","2025-05-15 09:00","2025-05-16 18:00","2025-05-15 09:00","2025-05-16 18:00","연속"]
[107,"경기","군포","서서울S/S #2 M.Tr","서서울S/S #2M.Tr GIS 보통,3차PT 초기,LA,CVT 대체","서서울S/S  #2M.Tr 7572 GIS 보통점검, 3차 GPT 초기점검, 1차 LA 및 CVT 대체 작업 시행","2025-05-13 09:00","2025-05-14 18:00","2025-05-13 09:00","2025-05-14 18:00","연속"]
[108,"경기","동부","곤지암여주복합#2 T/L","추락방지장치 설치공사(곤지암여주CC #2)","곤지암여주CC #2T/L 추락방지장치 설치 80기(잔여 7기)","2025-05-13 07:00","2025-05-13 18:00","취소","취소","연속"]
[109,"경기","동부","곤지암여주복합#1 T/L","추락방지장치 설치공사(곤지암여주CC #1)","곤지암여주CC #1T/L 추락방지장치 설치 80기(잔여 18기)","2025-05-12 07:00","2025-05-12 18:00","취소","취소","연속"]
[110,"경기","동부","여주C/C CB 7472","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #3Strp up Tr 법정검사 수검","2025-05-20 14:00","2025-05-20 18:00","2025-05-20 14:00","2025-05-20 18:00","연속"]
[111,"경기","동부","여주C/C CB 7300","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #2Strp up Tr 법정검사 수검","2025-05-21 09:00","2025-05-21 18:00","2025-05-21 09:00","2025-05-21 18:00","연속"]
[112,"경기","동부","여주C/C CB 7272","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #1Strp up Tr 법정검사 수검","2025-05-20 09:00","2025-05-20 14:00","2025-05-20 09:00","2025-05-20 14:00","연속"]
[113,"경기","동부","여주C/C CB 7100","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #1Strp up Tr 법정검사 수검","2025-05-20 09:00","2025-05-20 14:00","2025-05-20 09:00","2025-05-20 14:00","연속"]
[114,"경기","동부","여주C/C CB 7372","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #2Strp up Tr 법정검사 수검","2025-05-15 09:00","2025-05-17 18:00","2025-05-15 09:00","2025-05-17 18:00","연속"]
[115,"경기","동부","여주C/C CB 7300","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #2Strp up Tr 법정검사 수검","2025-05-15 09:00","2025-05-17 18:00","2025-05-15 09:00","2025-05-17 18:00","연속"]
[116,"경기","동부","신충주여주복합#2 T/L","추락방지장치 설치공사(신충주여주복합#2T/L)","신충주여주복합#2T/L 추락방지장치 설치 39기","2025-05-14 07:00","2025-05-15 18:00","취소","취소","연속"]
[117,"경기","동부","여주C/C CB 7272","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #1Strp up Tr 법정검사 수검","2025-05-12 09:00","2025-05-14 18:00","2025-05-12 09:00","2025-05-14 18:00","연속"]
[118,"경기","동부","여주C/C CB 7200","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #1Strp up Tr 법정검사 수검","2025-05-12 09:00","2025-05-14 18:00","2025-05-12 09:00","2025-05-14 18:00","연속"]
[119,"경기","동부","여주C/C CB 7400","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #3Strp up Tr 법정검사 수검","2025-05-10 09:00","2025-05-17 18:00","2025-05-10 09:00","2025-05-17 18:00","연속"]
[120,"경기","동부","여주C/C CB 7472","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #3Strp up Tr 법정검사 수검","2025-05-10 09:00","2025-05-17 18:00","2025-05-10 09:00","2025-05-17 18:00","연속"]
[121,"경기","동부","신제천신충주T#1 T/L","추락방지장치 설치공사(신제천-여주CC)","신제천 여주CC 추락방지장치 설치 39기","2025-05-08 07:00","2025-05-09 18:00","취소","취소","연속"]
[122,"경기","동부","여주C/C CB 7300","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #2Strp up Tr 법정검사 수검","2025-05-21 09:00","2025-05-21 18:00","2025-05-21 09:00","2025-05-21 18:00","연속"]
[123,"경기","동부","여주C/C CB 7400","여주CC 발전설비 법정검사 수검(고객사요청)","여주CC : #3Strp up Tr 법정검사 수검","2025-05-20 14:00","2025-05-20 18:00","2025-05-20 14:00","2025-05-20 18:00","연속"]
[124,"경기","성남","신성남신양재#1 T/L","추락방지장치 설치공사(신성남신양재#1)","추락방지장치 설치공사(수평) - 대상기수 : 22기(전구간) - 154kV 신성남-염곡#1 19기 병가(4회선) - 154kV 신성남-신봉#2 2기 병가(4회선)","2025-05-19 07:00","2025-05-21 18:00","2025-05-19 07:00","2025-05-21 18:00","연속"]
[125,"경기","성남","신성남신양재#2 T/L","추락방지장치 설치공사(신성남신양재#2)","추락방지장치 설치공사(수평) - 대상기수 : 22기(전구간) - 154kV 신성남-염곡#2 19기 병가(4회선) - 154kV 신성남-신봉#1 2기 병가(4회선)","2025-05-22 07:00","2025-05-24 18:00","2025-05-22 07:00","2025-05-24 18:00","연속"]
[126,"경기","성남","신성남S/S #6 M.Tr","2025년 성남전력 변전협력회사 총액공사","- 7872 조작시험 - 2차 gis 조작시험 - 3차 gis 보통점검 - #6-1,2sh.r 하자점검","2025-05-15 09:00","2025-05-16 18:00","2025-05-15 09:00","2025-05-16 18:00","연속"]
[127,"경기","성남","신성남S/S #2 M.Tr","효성제 불품발청 교체공사","신성남) 2차 GIS 효성제불품 발청공사 병행) M.Tr 보통점검 병행) 7200, 7272 조작시험, 절연열화, 3차 모선 보통점검","2025-05-08 09:00","2025-05-09 18:00","2025-05-08 09:00","2025-05-09 18:00","연속"]
[128,"경기","성남","서서울#2신성남#2 T/L","2025년 성남전력 변전협력회사 총액공사","신성남)7171조작시험, 절연열화, CVT 하자점검 7151 DS 에어누기보수, 결상보수","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[129,"경기","성남","신성남S/S CB 7271","2025년 성남전력 변전협력회사 총액공사","7291-1ES B상 코일교체(3/18휴전시행중 불량발견 긴급조치 필요)","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[130,"경기","성남","신수원S/S #2 M.Tr","25년 성남전력 주변압기  보통, 154kV 정밀/보통점검공사","- m.tr, ngr 보통점검","2025-05-13 09:00","2025-05-14 18:00","2025-05-13 09:00","2025-05-14 18:00","연속"]
[131,"경기","성남","신안성서안성#2 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","- 7B00, 7B72 보통점검, 절연열화","2025-05-19 09:00","2025-05-20 18:00","2025-05-19 09:00","2025-05-20 18:00","연속"]
[132,"경기","성남","신안성서안성#1 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","- 7C00, 7C72 보통점검, 절연열화","2025-05-15 09:00","2025-05-16 18:00","2025-05-15 09:00","2025-05-16 18:00","연속"]
[133,"경기","성남","신안성신수원#2 T/L","24-25년 경기직할 송전협력회사 공사","철탑추락방지장치 설치공사(수평)","2025-05-12 13:00","2025-05-12 18:00","2025-05-12 13:00","2025-05-12 18:00","연속"]
[134,"경기","성남","신안성신수원#1 T/L","24-25년 경기직할 송전협력회사 공사","철탑추락방지장치 설치공사(수평) 및 애자교체 공사","2025-05-12 07:00","2025-05-12 13:00","2025-05-12 07:00","2025-05-12 13:00","연속"]
[135,"경기","성남","신용인S/S #1 M.Tr","2025년 성남전력 변전협력회사 총액공사","-2차 gis 보통점검 - 3차 la 보통점검","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[136,"경기","성남","신용인S/S #2 M.Tr","2025년 성남전력 170kV GIS 정밀점검공사","- 2차 gis 정밀점검","2025-05-19 09:00","2025-05-21 18:00","2025-05-19 09:00","2025-05-21 18:00","연속"]
[137,"경기","성남","신용인동서울#2 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","신용인) 7271, 7200 보통점검, 절연열화","2025-05-07 09:00","2025-05-08 18:00","2025-05-07 09:00","2025-05-08 18:00","연속"]
[138,"경기","직할","화성S/S #2 M.Tr","2024-25년 경기본부 직할 변전협력회사 공사","화성 : #2M.Tr 보통점검(~23) - 1차 GIS 7472 하자점검 - 1,2차 LA A,B,C 보통점검 - CVT 1차 A,B,C 보통점검 - 1,2차 부싱 A,B,C 절연유 채유 - 추락방지장치 설치","2025-05-19 09:00","2025-05-23 18:00","2025-05-19 09:00","2025-05-23 18:00","연속"]
[139,"경기","직할","아산화성#1 T/L","154kV 화성-장덕T/L OPGW 증설공사","154kV 화성-장덕T/L OPGW 증설공사 - OPGW 증설교체(OP-S-L24 → L48) 7.797km(해당구간 2km) - 광코어 접속, 최종시험 및 기타 부대공사 1식","2025-05-24 07:00","2025-05-25 18:00","취소","취소","연속"]
[140,"경기","평택","고덕#2S/S CB 7271","PNC테크 성능개선( #1 M.Tr 1차 7271 GIS)","PNC테크 성능개선( #1 M.Tr 1차 7271 GIS)","2025-05-20 09:30","2025-05-20 09:50","2025-05-20 09:30","2025-05-20 09:50","연속"]
[141,"경기","평택","고덕#2S/S CB 7472","PNC테크 성능개선(고덕#2-서안성#1T/L 1차 7472 GIS)","PNC테크 성능개선(고덕#2-서안성#1T/L 1차 7472 GIS)","2025-05-20 14:00","2025-05-20 14:20","2025-05-20 14:00","2025-05-20 14:20","연속"]
[142,"경기","평택","고덕#2S/S CB 7400","PNC테크 성능개선(고덕#2S/S 74Bay TIE GIS 7400)","PNC테크 성능개선(고덕#2S/S 74Bay TIE GIS 7400)","2025-05-20 13:30","2025-05-20 14:00","2025-05-20 13:30","2025-05-20 14:00","연속"]
[143,"경기","평택","고덕#2S/S CB 7471","PNC테크 성능개선(고덕#2S/S # 3 M.Tr 1차 7471","PNC테크 성능개선(고덕#2S/S # 3 M.Tr 1차 7471","2025-05-20 13:10","2025-05-20 13:30","2025-05-20 13:10","2025-05-20 13:30","연속"]
[144,"경기","평택","고덕#2S/S CB 7372","PNC테크 성능개선(고덕#2S/S  #2 M.Tr1차 7372)","PNC테크 성능개선(고덕#2S/S  #2 M.Tr1차 7372)","2025-05-20 11:20","2025-05-20 11:40","2025-05-20 11:20","2025-05-20 11:40","연속"]
[145,"경기","평택","고덕#2S/S CB 7300","PNC테크 성능개선(고덕2#S/S  73Bay TIE GIS)","PNC테크 성능개선(고덕2#S/S  73Bay TIE GIS)","2025-05-20 11:00","2025-05-20 11:20","2025-05-20 11:00","2025-05-20 11:20","연속"]
[146,"경기","평택","고덕#2S/S CB 7272","PNC테크 성능개선(고덕-고덕#2 #1T/L 1차 7272 GIS)","PNC테크 성능개선(고덕-고덕#2 #1T/L 1차 7272 GIS)","2025-05-20 10:10","2025-05-20 10:30","2025-05-20 10:10","2025-05-20 10:30","연속"]
[147,"경기","평택","고덕#2S/S CB 7200","PNC테크 성능개선(72Bay TIE 7200 GIS)","PNC테크 성능개선(72Bay TIE 7200 GIS)","2025-05-20 09:50","2025-05-20 10:10","2025-05-20 09:50","2025-05-20 10:10","연속"]
[148,"경기","평택","고덕#2S/S CB 7571","PNC테크 성능개선(고덕#2-서안성#2T/L 7571)","PNC테크 성능개선(고덕#2-서안성#2T/L 7571)","2025-05-12 09:30","2025-05-12 09:50","2025-05-12 09:30","2025-05-12 09:50","연속"]
[149,"경기","평택","고덕#2S/S CB 7500","PNC테크 성능개선(고덕#2-서안성#2T/L 7500)","PNC테크 성능개선(고덕#2-서안성#2T/L 7500)","2025-05-12 09:50","2025-05-12 10:10","2025-05-12 09:50","2025-05-12 10:10","연속"]
[150,"경기","평택","고덕S/S STATCOM CB","2025년 평택전력 변전협력회사 총액공사(고덕S/S STATCOM)","고덕S/S  STATCOM M.Tr (A,B,C,예비) 보통점검","2025-05-07 09:00","2025-05-08 18:00","취소","취소","연속"]
[151,"경기","평택","고덕S/S CB 7800","2025년 평택전력 변전협력회사 총액공사(고덕S/S STATCOM)","고덕S/S  STATCOM M.Tr (A,B,C,예비) 보통점검","2025-05-07 09:00","2025-05-08 18:00","취소","취소","연속"]
[152,"경기","평택","서안성S/S CB 7600","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7600)","서안성S/S  고덕2서안성#2 T/L GIS(7600 단독) 보통점검","2025-05-29 14:00","2025-05-29 18:00","2025-06-16 14:00","2025-06-16 18:00","연속"]
[153,"경기","평택","서안성S/S CB 7571","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7571)","서안성S/S  고덕2서안성#1 T/L GIS(7571 단독) 보통점검","2025-05-30 09:00","2025-05-30 14:00","2025-06-17 09:00","2025-06-17 14:00","연속"]
[154,"경기","평택","서안성S/S CB 7500","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7500)","서안성S/S  고덕2서안성#1 T/L GIS(7500 단독) 보통점검","2025-05-30 14:00","2025-05-30 18:00","2025-06-17 14:00","2025-06-17 18:00","연속"]
[155,"경기","평택","서안성S/S CB 7671","2025년 평택전력 GIS 보통 및 정밀점검공사(서안성SS 7671)","서안성S/S  고덕2서안성#2 T/L GIS(7671 단독) 보통점검","2025-05-29 09:00","2025-05-29 14:00","2025-06-16 09:00","2025-06-16 14:00","연속"]
[156,"경기","평택","평택T/P CB 7872","2025년 평택전력 GIS 보통 및 정밀점검공사(평택TP 7872)","평택T/P  #1 S/T 1차 GIS(7872) 보통점검","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[157,"경기","평택","평택T/P CB 7971","2025년 평택전력 GIS 보통 및 정밀점검공사(평택TP 7971)","평택T/P  화성-신평택CC#2T/L GIS(7971) 보통점검","2025-05-15 14:00","2025-05-15 18:00","2025-05-15 14:00","2025-05-15 18:00","연속"]
[158,"경기","평택","평택T/P CB 7A71","2025년 평택전력 GIS 보통 및 정밀점검공사(평택TP 7A71)","평택T/P  화성-신평택CC#1T/L GIS(7A71) 보통점검","2025-05-15 09:00","2025-05-15 14:00","2025-05-15 09:00","2025-05-15 14:00","연속"]
[159,"경기","평택","평택T/P CB 7A72","2025년 평택전력 GIS 보통 및 정밀점검공사(평택TP 7A72)","평택T/P  신평택#2G/T 1차 GIS(7A72) 보통점검","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[160,"경기","평택","평택T/P CB 7A00","2025년 평택전력 GIS 보통 및 정밀점검공사(평택TP 7A00)","평택T/P  신평택#2-화성신평#1T/L GIS(7A00) 보통점검","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[161,"경기","평택","평택T/P CB 7900","2025년 평택전력 GIS 보통 및 정밀점검공사(평택TP 7900)","평택T/P  신평택#1-화성신평#2T/L GIS(7900) 보통점검","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[162,"경기","평택","평택T/P CB 7B72","2025년 평택전력 GIS 보통 및 정밀점검공사(평택TP 7B72)","평택T/P  신평택 #1S/T 1차 GIS(7B72) 보통점검","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[163,"경기","평택","평택T/P CB 7972","2025년 평택전력 GIS 보통 및 정밀점검공사(평택TP 7972)","평택T/P  신평택 #1G/T 1차 GIS(7972) 보통점검","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[164,"경기","평택","평택T/P CB 7B00","2025년 평택전력 GIS 보통 및 정밀점검공사(평택TP 7B00)","평택T/P  신평택 #1S/T 1차 TIE GIS(7B00) 보통점검","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[165,"강원","강릉","신양양양양PP T/L","2024~2025년 가공송전협력회사 총액공사","○ 4회선 병가철탑 휴전작업 작업자 안전을 위한 휴전 -154kV 신양양-인제#1 T/L (No.3~6)","2025-05-27 07:00","2025-05-27 18:00","2025-05-27 07:00","2025-05-27 18:00","연속"]
[166,"강원","강릉","안인개폐소신양양 T/L","2024~2025년 가공송전협력회사 총액공사","○ 4회선 병가철탑 휴전작업 작업자 안전을 위한 휴전 154kV 신양양-인제#2 T/L (No.7~29)","2025-05-28 07:00","2025-05-29 18:00","2025-05-28 07:00","2025-05-29 18:00","매일"]
[167,"강원","동해","동해S/S #1 M.Tr","2024~25년 동해전력지사 변전협력회사공사","#1M.Tr AC, DC 옥외분전반 대체","2025-05-19 09:00","2025-05-20 18:00","2025-05-19 09:00","2025-05-20 18:00","연속"]
[168,"강원","동해","동해S/S #2 M.Tr","2024~25년 동해전력지사 변전협력회사공사","#2M.Tr AC, DC 옥외분전반 대체, 부싱 절연유 채유","2025-05-28 09:00","2025-05-30 18:00","2025-05-28 09:00","2025-05-30 18:00","연속"]
[169,"강원","동해","동해S/S #3 M.Tr","2024~25년 동해전력지사 변전협력회사공사","붓싱 절연유 채유","2025-05-22 09:00","2025-05-23 18:00","2025-05-22 09:00","2025-05-23 18:00","연속"]
[170,"강원","동해","삼척GP한울NP#2 T/L"," 삼척GP-한울NP1T/L 산불피해개소 전력선교체 공사","산불피해개소 전력선교체","2025-05-15 07:00","2025-05-23 18:00","2025-05-15 07:00","2025-05-23 18:00","연속"]
[171,"강원","동해","삼척GP한울NP#1 T/L"," 삼척GP-한울NP1T/L 산불피해개소 전력선교체 공사","산불피해개소 전력선교체","2025-05-26 07:00","2025-06-04 18:00","2025-05-26 07:00","2025-06-04 18:00","연속"]
[172,"강원","태백","신태백삼척BP#1T/L","2024-2025년 태백전력지사 변전협력회사 공사","신태백S/S  7322DS 투입 및 개방용 전자접촉기 교체","2025-05-28 09:00","2025-05-28 18:00","2025-05-28 09:00","2025-05-28 18:00","연속"]
[173,"강원","태백","신태백S/S #1 BUS","신태백S/S  GIS 설치공사","○ 신태백S/S  72Bay #1BUS측 조립 및 도킹","2025-05-05 08:00","2025-05-11 18:00","2025-05-19 08:00","2025-05-23 18:00","연속"]
[174,"강원","태백","신태백삼척BP#2T/L","신태백S/S  GIS 설치공사","○ 신태백S/S  72Bay #2BUS측 도킹 후 무부하가압(24Hr) * 신태백 계통운영방안 관련 신태백-삼척BP#2 T/L 또는 신태백-한울NP2 #2 T/L을 통한 무부하 가압 실시예정","2025-05-15 10:00","2025-05-16 18:00","2025-05-29 08:00","2025-05-30 18:00","연속"]
[175,"강원","태백","신태백한울NP#1 T/L","신태백S/S  GIS 설치공사","○ 신태백S/S  72Bay #2BUS측 도킹 후 무부하가압(24Hr) * 신태백 계통운영방안 관련 신태백-삼척BP#2 T/L 또는 신태백-한울NP2 #2 T/L을 통한 무부하가압 실시예정","2025-05-15 10:00","2025-05-16 18:00","2025-05-29 08:00","2025-05-30 18:00","연속"]
[176,"강원","태백","신태백S/S #2 BUS","신태백S/S  GIS 설치공사","○ 신태백S/S  72Bay #2BUS측 조립 및 도킹","2025-05-12 08:00","2025-05-16 18:00","2025-05-26 08:00","2025-05-30 18:00","연속"]
[177,"충북","직할","신중부남청주#1 T/L"," 신청주S/S 건설사업"," 신중부-신청주 #1T/L,  신청주-남청주#1T/L 계통연계","2025-05-12 09:00","2025-05-17 18:00","취소","취소","연속"]
[178,"충북","직할","신중부남청주#2 T/L"," 신청주S/S 건설사업"," 신중부-신청주 #2T/L,  신청주-남청주#2T/L 계통연계","2025-05-19 09:00","2025-05-23 18:00","2025-05-19 09:00","2025-05-23 18:00","연속"]
[179,"충북","직할","신진천S/S #4 M.Tr","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S 154kV #5Sh.C GIS 정밀점검 후 무부하가압용","2025-05-14 14:00","2025-05-14 15:00","2025-05-14 14:00","2025-05-14 15:00","연속"]
[180,"충북","직할","신진천S/S #4 M.Tr","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S 154kV #6Sh.C GIS 정밀점검 후 무부하가압용","2025-05-16 14:00","2025-05-16 15:00","2025-05-16 14:00","2025-05-16 15:00","연속"]
[181,"충북","직할","신진천S/S #1 M.Tr","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S  #1M.Tr 2차 GIS 정밀점검","2025-05-19 08:00","2025-05-21 16:00","2025-05-19 08:00","2025-05-21 16:00","연속"]
[182,"충북","직할","신진천S/S #5 M.Tr","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #5M.Tr 2차 GIS 보통점검 및 전자변 교체","2025-05-22 10:00","2025-05-22 18:00","2025-05-22 10:00","2025-05-22 18:00","연속"]
[183,"충북","직할","신진천S/S #2 M.Tr","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S  #2M.Tr 2차 GIS 정밀점검 및 #2M.Tr 보통점검","2025-05-26 08:00","2025-05-29 16:00","2025-05-26 08:00","2025-05-29 16:00","연속"]
[184,"충북","청주","신옥천S/S CB 7172","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검(7172)","2025-05-13 08:00","2025-05-13 18:00","2025-05-13 08:00","2025-05-13 18:00","연속"]
[185,"충북","청주","신옥천S/S #1 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사"," M.Tr 보통점검 154kV GIS 보통점검(M.Tr 2차측) 1-1, 1-2Sh.R VCB 초기점검","2025-05-07 08:00","2025-05-09 18:00","2025-05-07 08:00","2025-05-09 18:00","연속"]
[186,"충북","청주","신옥천S/S CB 7271","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검(7271)","2025-05-14 08:00","2025-05-14 18:00","2025-05-14 08:00","2025-05-14 18:00","연속"]
[187,"충북","청주","신옥천세종#1 T/L"," 신옥천-북경남 등 8개T/L 추락방지장치 설치공사","공사명 :  신옥천-북경남 등 8개T/L 추락방지장치 설치공사 장 소 :  신옥천-세종#1T/L No.1~48 (수평 추락방지)","2025-05-19 07:00","2025-05-26 18:00","취소","취소","연속"]
[188,"충북","청주","신옥천세종#2 T/L"," 신옥천-북경남 등 8개T/L 추락방지장치 설치공사","공사명 :  신옥천-북경남 등 8개T/L 추락방지장치 설치공사 장 소 :  신옥천-세종#2T/L No.1~48 (수평 추락방지)","2025-05-27 07:00","2025-05-30 18:00","취소","취소","연속"]
[189,"충북","충주","신제천S/S #1 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #1BUS DS(7251,7351,7451) PD 하자보수","2025-05-05 09:00","2025-05-09 18:00","취소","취소","연속"]
[190,"충북","충주","신제천S/S #2 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #2BUS DS(7652,7752,7952,7A52)하자보수","2025-05-26 09:00","2025-05-31 18:00","취소","취소","연속"]
[191,"충북","충주","신제천신충주#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 압축인류클램프 교체(No.157) 및 항공장애표시구 설치(No.23~No.28)","2025-05-03 07:00","2025-05-03 17:00","취소","취소","연속"]
[192,"충북","충주","신제천S/S #1 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #1BUS DS(7251,7351,7451) PD 하자보수","2025-05-05 09:00","2025-05-09 18:00","취소","취소","연속"]
[193,"충북","충주","신제천신영주#2 T/L"," 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.1~165)","2025-05-12 07:00","2025-05-30 16:00","취소","취소","매일"]
[194,"충북","충주","신제천S/S #2 BUS","신제천S/S 362KV GIS PD 제작사 하자보수","신제천S/S  #2BUS DS(7252,7352,7452)DS PD 하자보수","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[195,"충북","충주","신제천S/S #1 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #1BUS DS(7651,7751,7951,7A51) PD 하자보수","2025-05-19 09:00","2025-05-24 18:00","취소","취소","연속"]
[196,"충북","충주","신제천S/S #4 M.Tr","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S  #4 M.Tr 3차 4479,4589VCB , 4475/4285/4585 옥외DS, #2S.TR 초기점검","2025-05-21 09:00","2025-05-23 18:00","2025-05-21 09:00","2025-05-23 18:00","연속"]
[197,"충북","충주","신제천S/S #2 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #2BUS DS(7652,7752,7952,7A52)하자보수","2025-05-26 09:00","2025-05-31 18:00","취소","취소","연속"]
[198,"충북","충주","신제천신충주#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 압축인류클램프 교체(No.157) 및 항공장애표시구 설치(No.23~No.28)","2025-05-03 07:00","2025-05-03 17:00","취소","취소","연속"]
[199,"충북","충주","신제천S/S #4 M.Tr","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S  #4 M.Tr 3차 4479,4589VCB , 4475/4285/4585 옥외DS, #2S.TR 초기점검","2025-05-21 09:00","2025-05-23 18:00","취소","취소","연속"]
[200,"충북","충주","신제천S/S #1 BUS","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  #1BUS DS(7651,7751,7951,7A51) PD 하자보수","2025-05-19 09:00","2025-05-24 18:00","취소","취소","연속"]
[201,"충북","충주","신제천S/S #2 BUS","신제천S/S 362KV GIS PD 제작사 하자보수","신제천S/S  #2BUS DS(7252,7352,7452)DS PD 하자보수","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[202,"충북","충주","신제천신영주#2 T/L"," 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.1~165)","2025-05-12 07:00","2025-05-30 16:00","취소","취소","매일"]
[203,"충북","충주","신제천신충주T#1 T/L"," 신용인-동서울 등 16개 T/L 추락방지장치 설치공사"," 신제천-여주CC T/L 추락방지장치 설치공사 - 신제천-여주CC 연계선로로 인한 휴전(신충주 T분기 실작업 없음)","2025-05-08 07:00","2025-05-09 18:00","취소","취소","연속"]
[204,"충북","충주","신충주S/S #4 M.Tr","'24-25년 충주전력지사 변전정비 총액공사","신충주S/S  #4M.Tr 보통점검","2025-05-19 09:00","2025-05-20 18:00","2025-05-19 09:00","2025-05-20 18:00","연속"]
[205,"충북","충주","신제천신충주T#1 T/L"," 신용인-동서울 등 16개 T/L 추락방지장치 설치공사"," 신제천-여주CC T/L 추락방지장치 설치공사 - 신제천-여주CC 연계선로로 인한 휴전(신충주 T분기 실작업 없음)","2025-05-08 07:00","2025-05-09 18:00","취소","취소","연속"]
[206,"충북","충주","신충주S/S #4 M.Tr","'24-25년 충주전력지사 변전정비 총액공사","신충주S/S  #4M.Tr 보통점검","2025-05-19 09:00","2025-05-20 18:00","취소","취소","연속"]
[207,"대전세종충남","대전","신계룡청양 T/L","[송전][즉시가압O] 신옥천-청양등8개T/L 추락방지설치공사","[송전][즉시가압O] 신옥천-청양 등 8개T/L 추락방지 설치공사","2025-05-19 07:00","2025-05-25 11:30","취소","취소","매일"]
[208,"대전세종충남","서산","당진T/P #72 M.Tr","'24-25년 서산P/O 변전협력회사 총액공사","(즉시가압 가능) 당진화력S/S  #72Tie Tr 1,2차 CB(7371, 6244) 및 #72Tie Tr 1차 - Tie CB(7300) 차단기 개폐타임 측정","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[209,"대전세종충남","서산","당진T/P #71 M.Tr","2024~2025년 변전협력회사 총액공사","당진T/P #71 Tie-Tr A~C, 예비상 부싱 절연유 채유","2025-05-07 09:00","2025-05-07 18:00","2025-05-07 09:00","2025-05-07 18:00","연속"]
[210,"대전세종충남","서산","북당진현대제철 T/L"," 신송산분기T/L 건설공사","No.70 전선 이동(가철탑→본철탑) No.69∼No.71 전선 교체","2025-05-20 07:00","2025-06-01 18:00","취소","취소","연속"]
[211,"대전세종충남","서산","신당진개폐소현대제철 T/L"," 신송산분기T/L 건설공사","No.70 전선 이동(가철탑→본철탑) No.69∼No.71 전선 교체","2025-05-07 07:00","2025-05-19 18:00","취소","취소","연속"]
[212,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","24~25 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-북당진T/L 병가선로,  신당진개폐소-북당진T/L 휴전 미승인시 휴전 취소 요청 *4월 휴전 승인시 취소 요청","2025-05-19 08:00","2025-05-19 18:00","취소","취소","연속"]
[213,"대전세종충남","서산","신당진개폐소북당진 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#1T/L 병가선로,  신당진개폐소-태안화력#1T/L 휴전 미승인시 휴전 취소 요청 *4월 휴전 승인시 취소 요청","2025-05-19 08:00","2025-05-19 18:00","취소","취소","연속"]
[214,"대전세종충남","서산","신당진개폐소북당진 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신당진개폐소  개폐소-북당진 T/L 인출 GIB 가스누기 보수공사 -북당진변환소 Bipole 연차점검 5.7 ~ 30","2025-05-07 09:30","2025-05-11 18:00","2025-05-07 09:30","2025-05-11 18:00","연속"]
[215,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신당진개폐소-태안화력#1T/L 양단 보호반 교체","2025-05-12 09:00","2025-05-16 18:00","2025-05-12 09:00","2025-05-16 18:00","연속"]
[216,"대전세종충남","서산","신당진S/S #3 M.Tr","25년 서산P/O  이하 M.Tr 보통점검공사","(4월휴전취소시)(즉시가압가능) 신당진S/S  #3M.Tr 보통점검","2025-05-12 09:30","2025-05-16 18:00","취소","취소","연속"]
[217,"대전세종충남","서산","태안T/P CB 7472","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 태안T/P  7472 GIS 보통점검","2025-05-07 09:30","2025-05-08 18:00","2025-05-07 09:30","2025-05-08 18:00","연속"]
[218,"대전세종충남","서산","태안T/P CB 7400","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 태안T/P  7400 GIS 보통점검","2025-05-29 09:30","2025-05-30 18:00","2025-05-29 09:30","2025-05-30 18:00","연속"]
[219,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","태안화력S/S  옥외 기타설비 내장화공사","(즉시가압불가) 태안화력S/S  개폐소-태안화력#2T/L CVT 내장화공사","2025-05-20 09:00","2025-06-03 18:00","2025-05-20 09:00","2025-06-03 18:00","연속"]
[220,"대전세종충남","천안","신온양서서울#1 T/L","(4월 취소시)신온양S/S  #78Bay B/F PNL 대체","(즉시가압불가)신온양S/S  #78Bay 노후 B/F PNL 대체","2025-05-26 09:00","2025-05-30 18:00","취소","취소","연속"]
[221,"대전세종충남","천안","신온양S/S #2 M.Tr","신온양S/S  #2M.Tr 부싱 절연유 채유","신온양S/S  #2M.Tr 부싱 절연유 채유","2025-05-02 09:00","2025-05-02 18:00","취소","취소","연속"]
[222,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S  #77Bay 노후 B/F PNL 대체","(즉시가압불가)신온양S/S  #77Bay 노후 B/F PNL 대체","2025-05-19 09:00","2025-05-23 18:00","취소","취소","연속"]
[223,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S  #77Bay 노후 B/F PNL 대체","(즉시가압불가)신온양S/S  #77Bay 노후 B/F PNL 대체","2025-05-19 09:00","2025-05-23 18:00","취소","취소","연속"]
[224,"대전세종충남","천안","신탕정S/S #3 M.Tr","신탕정S/S  #3M.Tr 보통점검 및 누유보수","신탕정S/S  #3M.Tr 보통점검 및 누유보수","2025-05-13 09:00","2025-05-16 18:00","2025-05-13 09:00","2025-05-16 18:00","연속"]
[225,"대전세종충남","천안","신온양신탕정#2 T/L","(4월 취소시)신탕정S/S  신온양신탕정#2T/L 보호반 대체","(즉시가압불가)(신온양-서서울#1T/L 휴전 취소시)신온양, 신탕정S/S 45kV 신온양신탕정#2T/L 보호반 대체","2025-05-26 09:00","2025-05-30 18:00","취소","취소","연속"]
[226,"대전세종충남","천안","신서산아산#1 T/L"," 신서산-아산T/L 추락방지장치 설치공사, 정밀점검","[즉시가압가능] 신서산-아산T/L No. 74 ~ 113 추락방지장치 설치 [병가철탑](상단)신서산-아산#1No.74~113,(하단)아산-합덕#1No.13~52 [병행작업]  신서산-신당진 등 2개T/L 4회선 병가철탑 정밀점검 (서산전력 송전부)","2025-05-12 07:00","2025-05-18 18:00","2025-05-12 07:00","2025-05-18 18:00","매일"]
[227,"대전세종충남","천안","신서산아산#2 T/L"," 신서산-아산T/L 추락방지장치 설치공사, 정밀점검","[즉시가압가능] 신서산-아산T/L No. 74 ~ 113 추락방지장치 설치 [병가철탑](상단)신서산-아산#2No.74~113,(하단)아산-합덕#2No.13~52 [병행작업]  신서산-신당진 등 2개T/L 4회선 병가철탑 정밀점검 (서산전력 송전부)","2025-05-01 07:00","2025-05-11 18:00","2025-05-01 07:00","2025-05-11 18:00","매일"]
[228,"대전세종충남","청양","보령C/C #70 BUS","보령복합S/Y  장기사용 GIS 교체 및 SW 증설","- (기설)BUS SEC 70-71-0 철거 및 GIB 설치","2025-05-05 09:00","2025-05-16 18:00","2025-05-05 09:00","2025-05-16 18:00","연속"]
[229,"대전세종충남","청양","보령T/P SEC CB 70710","보령T/P  BUS-SEC(70-71-0) GIS 보통점검","보령T/P  BUS-SEC(70-71-0) GIS 보통점검","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[230,"대전세종충남","청양","보령T/P CB 7471","보령T/P  #5,6SU TR 1차 GIS(7471) 보통점검","보령T/P  #5,6SU TR 1차 GIS(7471) 보통점검","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[231,"대전세종충남","청양","보령T/P SEC CB 75760","보령T/P  BUS-SEC(75-76-0) GIS 보통점검","보령T/P  BUS-SEC(75-76-0) GIS 보통점검","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[232,"대전세종충남","청양","청양군산#2 T/L","[송전][주말작업O]  청양-군산#2 T/L 애자련 교체"," 청양-군산#2 TL 애자련 교체","2025-05-30 07:30","2025-05-31 18:00","취소","취소","연속"]
[233,"대전세종충남","청양","청양군산#1 T/L","[송전]  청양-군산#1 T/L 가공지선, 항공구 교체 공사"," 청양-군산#1 TL 가공지선, 항공구 교체 및 애자련 보강","2025-05-26 07:30","2025-05-29 18:00","취소","취소","연속"]
[234,"전북","군산","군산S/S #75 BUS","군산변전소  GIS 대체공사 (중복)","○ 362kV GIS 40kA 4000A × 10CB(4Bay) 철거 ○ 362kV GIS 50kA 4000A × 10CB(4Bay) 신설 ○ 기타부대공사 × 1식","2025-05-31 08:00","2025-06-10 18:00","2025-05-31 08:00","2025-06-10 18:00","연속"]
[235,"전북","군산","군산S/S #1 Sh.R CB","군산변전소  GIS 대체공사(기기) (중복)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2025-05-29 18:00","2025-05-30 18:00","2025-05-29 18:00","2025-05-30 18:00","연속"]
[236,"전북","군산","군산S/S #70 BUS","군산변전소  GIS 대체공사 (중복)","○ 362kV GIS 40kA 4000A × 10CB(4Bay) 철거 ○ 362kV GIS 50kA 4000A × 10CB(4Bay) 신설 ○ 기타부대공사 × 1식","2025-05-22 08:00","2025-05-30 18:00","2025-05-22 08:00","2025-05-30 18:00","연속"]
[237,"전북","군산","군산S/S #4 M.Tr","군산P/O 154kV이상 차단기 조작시험","군산P/O 154kV이상 차단기 조작시험(7872,6444)","2025-05-09 09:00","2025-05-09 18:00","2025-05-09 09:00","2025-05-09 18:00","연속"]
[238,"전북","군산","군산S/S #3 M.Tr","군산P/O 154kV이상 차단기 조작시험","군산P/O 154kV이상 차단기 조작시험","2025-05-08 09:00","2025-05-08 14:00","2025-05-08 09:00","2025-05-08 14:00","연속"]
[239,"전북","군산","새만금S/S #2 M.Tr","새만금S/S #2M.Tr 추락방지장치 설치공사(중복)","새만금S/S #2M.Tr 추락방지장치 설치공사(중복)","2025-05-09 09:00","2025-05-09 18:00","2025-05-09 09:00","2025-05-09 18:00","연속"]
[240,"전북","김제","신김제S/S #3 M.Tr","변압기 부싱유 채유 및 #2S.Tr 교체관련 안전이격거리 확보"," #3M.Tr 부싱유 채유 및 #2S.Tr 교체관련 안전이격거리 확보","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[241,"전북","김제","신김제S/S #1 M.Tr","25년 김제전력지사 변압기 부싱유 채유"," #1M.Tr 부싱유 채유","2025-05-14 09:00","2025-05-14 12:00","2025-05-14 09:00","2025-05-14 12:00","연속"]
[242,"전북","김제","신김제S/S #2 M.Tr","25년 김제전력지사 변압기 부싱유 채유"," #1M.Tr 부싱유 채유","2025-05-15 09:00","2025-05-15 12:00","2025-05-15 09:00","2025-05-15 12:00","연속"]
[243,"전북","직할","신옥천무주양수 T/L","새롬제  송전선로보호반 성능개선","새롬제  송전선로보호반 성능개선","2025-05-19 09:00","2025-05-19 18:00","2025-05-19 09:00","2025-05-19 18:00","연속"]
[244,"전북","직할","신남원신광주#2 T/L","'24~'25년 전북직할 가공송전 협력회사 공사(계속)","○  신남원-신광주T/L 피뢰기 설치공사(계속) - No.1~115","2025-05-07 07:30","2025-05-14 18:00","취소","취소","매일"]
[245,"전북","직할","신남원의령#1 T/L","'25년 전북 직할 가공송전 순시점검 위탁공사(계속)","○ 정밀점검 : No.137~180","2025-05-19 09:00","2025-05-22 18:00","취소","취소","매일"]
[246,"전북","직할","신남원의령#2 T/L","'25년 전북 직할 가공송전 순시점검 위탁공사(계속)","○ 정밀점검 : No.137~180","2025-05-26 09:00","2025-05-30 18:00","취소","취소","매일"]
[247,"전북","직할","신남원한빛NP#1 T/L","신남원-한빛NP#1T/L 기타기기 점검","- LA 및 CVT(A,B,C상) 보통점검","2025-05-13 09:00","2025-05-13 18:00","취소","취소","연속"]
[248,"전북","직할","신남원광양#1 T/L","신남원-광양#1TL 기타기기 대체 및 점검","- LA(A,B,C상), CVT(C상) 대체 - CVT(A,B상) 하자 및 보통점점","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[249,"광주전남","강진","신화순신강진#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","신화순-신강진 추락방지장치 설치공사","2025-05-22 07:00","2025-05-30 18:00","2025-05-22 07:00","2025-05-30 18:00","매일"]
[250,"광주전남","강진","신화순신강진#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","신화순-신강진 추락방지장치 설치공사","2025-05-12 07:00","2025-05-21 18:00","취소","취소","매일"]
[251,"광주전남","강진","신강진S/S #4 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. 신강진S/S #4M.Tr 1차 부싱 절연열화 측정 나. 신강진S/S #4-1, 2Sh.R A,B,C, VCB, DS 보통점검","2025-05-13 08:00","2025-05-13 18:00","2025-05-13 08:00","2025-05-13 18:00","연속"]
[252,"광주전남","강진","신강진S/S #3 M.Tr","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-05-19 09:00","2025-05-30 18:00","취소","취소","연속"]
[253,"광주전남","강진","신강진광양#1 T/L","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-05-19 09:00","2025-05-30 18:00","취소","취소","연속"]
[254,"광주전남","광주","신남원신광주#2 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주S/S 신남원-신광주#2T/L LA A,B,C상, PT A,B,C상 보통점검","2025-05-14 08:00","2025-05-14 18:00","취소","취소","연속"]
[255,"광주전남","광주","신광주한빛NP#1 T/L","2024~25년 광주전력지사 송전 협력회사공사","폴리머점퍼지지애자 설치 및 애자련보강","2025-05-19 07:00","2025-05-21 18:00","취소","취소","매일"]
[256,"광주전남","광주","신광주한빛NP#2 T/L","2024~25년 광주전력지사 송전 협력회사공사","폴리머점퍼지지애자 설치 및 애자련보강","2025-05-22 07:00","2025-05-26 18:00","취소","취소","매일"]
[257,"광주전남","광주","신남원신광주#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 시행","2025-05-13 08:00","2025-05-19 18:00","취소","취소","매일"]
[258,"광주전남","광주","신광주S/S #1 BUS","장기사용  #1BUS 모선보호반 교체","장기사용  #1BUS 모선보호반 교체","2025-05-12 08:00","2025-05-14 18:00","취소","취소","연속"]
[259,"광주전남","광주","신남원신광주#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 시행","2025-05-06 08:00","2025-05-12 18:00","취소","취소","매일"]
[260,"광주전남","광주","신광주S/S #2 BUS","장기사용  #2BUS 모선보호반 교체","장기사용  #2BUS 모선보호반 교체","2025-05-15 08:00","2025-05-17 18:00","취소","취소","연속"]
[261,"광주전남","광주","신화순S/S #3 M.Tr","2024-2025년도 광주전력지사 변전협력회사 총액공사","신화순S/S  #3M.Tr 1차 LA A,B,C상 교체 신화순S/S 154kV #3M.Tr 2차 LA A,B,C상 교체 신화순S/S 23kV #3M.Tr 3차 LA A,B,C상 교체","2025-05-12 08:00","2025-05-13 18:00","2025-05-12 08:00","2025-05-13 18:00","연속"]
[262,"광주전남","목포","한빛1NP한빛2NP#2 T/L","2024~2025년 목포전력지사 변전협력회사 공사","한빛연락#2T/L 송전선로보호반 대체","2025-05-26 09:00","2025-05-30 18:00","2025-05-26 09:00","2025-05-30 18:00","연속"]
[263,"광주전남","목포","한빛1NP한빛2NP#1 T/L","2024~2025년 목포전력지사 변전협력회사 공사","한빛연락#1T/L 송전선로보호반 대체","2025-05-19 09:00","2025-05-23 18:00","2025-05-19 09:00","2025-05-23 18:00","연속"]
[264,"광주전남","목포","한빛2NP한빛3NP#4 T/L","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사 7D Bay 3CB 교체(71,72,00) #2 BUS 교체(모선측 DS 포함) 주말, 휴일작업 있음","2025-05-26 07:00","2025-05-29 18:00","취소","취소","연속"]
[265,"광주전남","목포","한빛3N/P #1 BUS","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사 7D Bay 3CB 교체(71,72,00) ※#2 BUS 휴전 불가시 #1 BUS 교체(모선측 DS 포함) 주말, 휴일작업 있음","2025-05-17 07:00","2025-06-20 18:00","취소","취소","연속"]
[266,"광주전남","목포","한빛3N/P #2 BUS","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사 7D Bay 3CB 교체(71,72,00) #2 BUS 교체(모선측 DS 포함) 주말, 휴일작업 있음","2025-05-17 07:00","2025-06-20 18:00","취소","취소","연속"]
[267,"광주전남","목포","한빛2NP한빛3NP#3 T/L","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사","한빛N/P #3S/Y 362kV 장기사용 GIS 교체공사 7D Bay 3CB 교체(71,72,00) #2 BUS 교체(모선측 DS 포함) 주말, 휴일작업 있음","2025-05-30 07:00","2025-06-02 18:00","취소","취소","연속"]
[268,"광주전남","순천","신강진광양#2 T/L"," 신강진-광양T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-05-21 13:00","2025-05-23 18:00","2025-05-21 13:00","2025-05-23 18:00","매일"]
[269,"광주전남","순천","광양S/S #2 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #2M.Tr 3차 MAIN VCB 초기점검","2025-05-19 09:00","2025-05-19 18:00","2025-05-19 09:00","2025-05-19 18:00","연속"]
[270,"광주전남","순천","광양여수TP T/L"," 신남원-광양 T/L 추락방지시설 설치공사","신남원-광양 수평설치(광양-여수TP, 광양-율촌CC 병가)","2025-05-26 07:00","2025-05-27 18:00","2025-05-26 07:00","2025-05-27 18:00","매일"]
[271,"광주전남","순천","신남원광양#2 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","신남원-광양 수평설치(광양-여수TP, 광양-율촌CC 병가)","2025-05-26 07:00","2025-05-27 18:00","2025-05-26 07:00","2025-05-27 18:00","매일"]
[272,"광주전남","순천","광양율촌CC T/L"," 신남원-광양 T/L 추락방지시설 설치공사","신남원-광양 수평설치(광양-여수TP, 광양-율촌CC 병가)","2025-05-28 07:00","2025-05-29 18:00","2025-05-28 07:00","2025-05-29 18:00","매일"]
[273,"광주전남","순천","신남원광양#1 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","신남원-광양 수평설치(광양-여수TP, 광양-율촌CC 병가)","2025-05-28 07:00","2025-05-29 18:00","2025-05-28 07:00","2025-05-29 18:00","매일"]
[274,"광주전남","순천","신강진광양#1 T/L","24-25년 순천전력지사 변전협력회사 공사","신강진-광양#1T/L 보호배전반 대체, 78BAY B/F반 대체공사","2025-05-19 09:00","2025-05-30 18:00","취소","취소","연속"]
[275,"광주전남","순천","광양S/S #1 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #1M.Tr 3차 MAIN VCB 조작시험, #1-1,1-2Sh.R 및 #1S.Tr VCB 초기점검","2025-05-07 09:00","2025-05-09 18:00","2025-05-07 09:00","2025-05-09 18:00","연속"]
[276,"광주전남","순천","광양S/S #3 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #3M.Tr 보통점검 및 1,2,3차 LA(A,B,C, 총 9EA) 대체, 추락방지장치설치","2025-05-12 09:00","2025-05-16 18:00","2025-05-12 09:00","2025-05-16 18:00","연속"]
[277,"광주전남","순천","신강진광양#1 T/L"," 신강진-광양T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-05-19 07:00","2025-05-21 13:00","2025-05-19 07:00","2025-05-21 13:00","매일"]
[278,"광주전남","순천","광양하동TP#2 T/L"," 광양-하동TP T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-05-16 07:00","2025-05-16 18:00","2025-05-16 07:00","2025-05-16 18:00","연속"]
[279,"광주전남","순천","광양하동TP#2 T/L","24-25년 순천전력지사 변전협력회사 공사","광양S/S 광양-하동TP#2T/L LA,CVT(A,B,C) 보통점검","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[280,"광주전남","순천","신남원광양#1 T/L","가스누기관련 누기개소 조치","가스누기관련 누기개소 조치","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","매일"]
[281,"광주전남","순천","광양하동TP#1 T/L","24-25년 순천전력지사 변전협력회사 공사","광양S/S 광양-하동TP#1T/L LA,CVT(A,B,C) 보통점검","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[282,"광주전남","순천","여수T/P #2 M.Tr","3차 DS과열관련 조치","3차 DS과열관련 조치","2025-05-26 09:00","2025-05-26 18:00","취소","취소","연속"]
[283,"광주전남","순천","여수T/P #3 M.Tr","여수화력  변압기 정밀점검","여수화력  변압기 정밀점검","2025-05-19 09:00","2025-05-23 18:00","취소","취소","연속"]
[284,"광주전남","순천","여수T/P #1 M.Tr","여수화력S/S #1M.Tr A, B상 부싱 교체","여수화력S/S #1M.Tr A, B상 부싱 교체","2025-05-12 10:00","2025-05-16 18:00","취소","취소","연속"]
[285,"대구","달성","고령의령#1 T/L"," 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 고령-의령#1T/L 피뢰기 및 조류착지방지장치 설치 - 주말간 환원(5/24~5/25)","2025-05-19 07:00","2025-05-28 18:00","2025-05-21 17:00","2025-05-21 18:00","연속"]
[286,"대구","달성","고령S/S #1 BUS","[TEST] 정밀점검 관련 무부하선로","[TEST] 정밀점검 관련 무부하선로","2025-05-16 17:00","2025-05-16 18:00","2025-05-17 17:00","2025-05-17 18:00","연속"]
[287,"대구","달성","고령의령#2 T/L","GIS 정밀점검","GIS 정밀점검","2025-05-12 09:00","2025-05-16 18:00","2025-05-14 17:00","2025-05-14 18:00","연속"]
[288,"대구","달성","북경남고령#2 T/L","[TEST] 정밀점검 관련 무부하선로","[TEST] 정밀점검 관련 무부하선로","2025-05-09 17:00","2025-05-09 18:00","2025-05-09 17:00","2025-05-09 18:00","연속"]
[289,"대구","달성","고령S/S #1 BUS","[TEST]T/L GIS 정밀점검","[TEST]T/L GIS 정밀점검","2025-05-23 17:00","2025-05-23 18:00","2025-05-21 17:00","2025-05-21 18:00","연속"]
[290,"대구","달성","고령S/S #1 Sh.R CB","고령 #1SH.R GIS 정밀점검","고령 #1SH.R GIS 정밀점검","2025-05-07 09:00","2025-05-09 18:00","2025-05-07 09:00","2025-05-09 18:00","연속"]
[291,"대구","달성","고령S/S #3 M.Tr","고령S/S #3M.TR 부싱절연유 채유","고령S/S #3M.TR 부싱절연유 채유","2025-05-02 09:00","2025-05-02 18:00","2025-05-02 09:00","2025-05-02 18:00","연속"]
[292,"대구","달성","서대구고령#2 T/L"," 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 고령-의령#1T/L 피뢰기 및 조류착지방지장치 설치 (고령-의령#1T/L 병가선로, 작업자 안전확보차 휴전)","2025-05-28 07:00","2025-05-28 18:00","2025-05-28 07:00","2025-05-28 18:00","연속"]
[293,"대구","달성","고령S/S #1 BUS","[TEST] 정밀점검 관련 무부하선로","[TEST] 정밀점검 관련 무부하선로","2025-05-09 17:00","2025-05-09 18:00","2025-05-09 17:00","2025-05-09 18:00","연속"]
[294,"대구","달성","신경산대구#2 T/L","GIS 하자점검","GIS 하자점검","2025-05-09 09:00","2025-05-09 18:00","2025-05-09 09:00","2025-05-09 18:00","연속"]
[295,"대구","달성","신경산대구#1 T/L","GIS 하자점검","GIS 하자점검","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[296,"대구","칠곡","서대구고령#2 T/L"," 서대구S/S 현대화 관련 전력구공사","(안전확보)신설 전력구설치(1,025m) 중 분기구 구간 가시설(H-PILE) 근입 및 항타","2025-05-07 08:00","2025-05-15 18:00","취소","취소","매일"]
[297,"대구","칠곡","서대구고령#1 T/L"," 서대구S/S 현대화 관련 전력구공사","(안전확보)신설 전력구설치(1,025m) 중 분기구 구간 가시설(H-PILE) 근입 및 항타","2025-05-19 08:00","2025-05-27 18:00","취소","취소","매일"]
[298,"대구","칠곡","북경남서대구#2 T/L","2024~2025년 달성전력지사 가공송전협력회사 공사","압축인류클램프 불량사항 정비(No.37 3번선 전원측 상단 내측)","2025-05-15 09:00","2025-05-16 18:00","2025-05-15 09:00","2025-05-16 18:00","연속"]
[299,"대구","칠곡","북경남서대구#1 T/L","2024~2025년 달성전력지사 가공송전협력회사 공사","압축인류클램프 불량사항 정비(No.37 2번선 전원측 상단 내측)","2025-05-19 09:00","2025-05-20 18:00","2025-05-19 09:00","2025-05-20 18:00","연속"]
[300,"경북","구미","서대구선산#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 서대구-선산#2T/L No.30~107 수평추락방지장치설치","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[301,"경북","구미","선산신포항 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 선산-신포항T/L 수평추락방지장치설치","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[302,"경북","영주","신영주한울NP#1 T/L"," 신영주-한울NP2T/L 수평추락방지장치 설치 공사"," 신영주-한울NP2T/L 수평추락방지장치 설치 공사","2025-05-12 09:00","2025-05-20 18:00","취소","취소","매일"]
[303,"경북","영주","신영주한울NP#2 T/L"," 신영주-한울NP2T/L 수평추락방지장치 설치 공사"," 신영주-한울NP2T/L 수평추락방지장치 설치 공사","2025-05-22 09:00","2025-05-31 18:00","취소","취소","매일"]
[304,"경북","영주","한울2NP한울3NP#3 T/L"," 동해안변환소 AC배후계통(변전) 건설공사","- 362kV GIS 50-&gt63kA 12CB 대체 - 362kV GIS 63kA 6CB 증설 - 기타 부대공사","2025-05-12 10:00","2025-05-14 18:00","2025-05-12 10:00","2025-05-14 18:00","연속"]
[305,"경북","영주","신한울한울#1 T/L","500kV 동해안변환소 AC배후계통 연결T/L 건설공사","- 구간 : 500kV 동해안변환소~ 한울NP3S/Y-신한울NP1S/Y,  신영주~한울NP3S/Y - 선종 : ACSR/AW 480(C) - 철탑 : 신설 10기(산형강 6기, CT 4기), 철거 5기(산형강 5기)","2025-05-08 07:00","2025-05-15 18:00","2025-05-08 07:00","2025-05-15 18:00","연속"]
[306,"경북","영주","한울#3N/P #2 BUS"," 동해안변환소 AC배후계통(변전) 건설공사","- 362kV GIS 50-&gt63kA 12CB 대체 - 362kV GIS 63kA 6CB 증설 - 기타 부대공사","2025-05-03 08:00","2025-05-09 18:00","2025-05-03 08:00","2025-05-09 18:00","연속"]
[307,"경북","직할","신영일안동CC T/L","청송면봉산 풍력발전단지 연계 송전선로 건설공사","○ 작업내용 -  영포T/L 기설 No.198,201 철탑보강 -  청송 면봉산분기T/L 신설 No.6 철탑조립 및 가선작업","2025-05-12 09:00","2025-05-23 18:00","2025-05-12 09:00","2025-05-23 18:00","연속"]
[308,"경북","직할","신영주안동CC T/L","24-25년 경북직할 송전협력회사 공사"," 신영주안동CC T/L 추락방지장치 설치","2025-05-14 08:00","2025-05-16 18:00","취소","취소","연속"]
[309,"경북","직할","신영주청송PP T/L","24-25년 경북직할 송전협력회사 공사"," 신영주-청송PPT/L No.50~225 추락방지장치 설치","2025-05-01 08:00","2025-05-10 18:00","2025-05-01 08:00","2025-05-10 18:00","연속"]
[310,"경북","직할","신포항청송PP T/L","청송면봉산 풍력발전단지 연계 송전선로 건설공사","○ 작업내용 -  영포T/L 기설 No.198,201 철탑보강 -  청송 면봉산분기T/L 신설 No.6 철탑조립 및 가선작업","2025-05-24 09:00","2025-06-04 18:00","2025-05-24 09:00","2025-06-04 18:00","연속"]
[311,"경북","직할","신포항청송PP T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2025-05-15 09:00","2025-05-15 18:00","취소","취소","연속"]
[312,"부산울산","북부산","북부산S/S #3 M.Tr","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S  #3M.Tr 보통점검","2025-05-12 09:00","2025-05-15 18:00","2025-05-26 09:00","2025-05-28 18:00","연속"]
[313,"부산울산","북부산","북부산S/S #2 Sh.R CB","북부산S/S  #2Sh.R 대체공사","북부산S/S  #2Sh.R 대체공사","2025-05-19 09:00","2025-06-05 18:00","2025-05-19 09:00","2025-06-05 18:00","연속"]
[314,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S  #1M.Tr 증설공사","154kV 신녹산-명지#2T/L 설치(감압)","2025-05-12 09:00","2025-05-18 18:00","2025-05-12 09:00","2025-05-18 18:00","연속"]
[315,"부산울산","울산","신온산남울산#2 T/L","2024-2025년 울산전력지사 가공송전협력회사 공사","[불량이도 조정공사] - 작업개소 :  신온산-남울산#2T/L No.12~14(총 2경간) - 작업내용 : 이도 불량개소 조정(이도조정키드 활용) - 시공업체 : 한일전력(주)","2025-05-12 08:00","2025-05-14 18:00","2025-05-12 08:00","2025-05-14 18:00","연속"]
[316,"부산울산","울산","남울산S/S CB 7300","25년 울산전력지사 변전협력회사 공사","- 7300 일진제 하자보수 유압조작기 교체","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[317,"부산울산","울산","신울산S/S #3 M.Tr","25년 울산전력지사 변전협력회사 공사","- 1차 피뢰기 하자점검 - 2차 피뢰기 대체","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[318,"부산울산","울산","남울산울산TP#2 T/L","2025년 가공송전 순시점검 위탁공사(울산)","○ 울주-울산TP#1T/L 등 3개 T/L 초기점검 및 애자오염진단장치 설치 ○ 대상 -  울주-울산TP#1T/L 9~14호 -  남울산-울산TP#2T/L 8,9,S/T - 154kV 남울산-처용#2T/L S/T~6호 ○ 안전이격확보 - 154kV 성암-울산TP#1T/L","2025-05-07 08:00","2025-05-07 18:00","2025-05-07 08:00","2025-05-07 18:00","연속"]
[319,"부산울산","울산","울산C/C #1 M.Tr","25년 울산전력지사 변전협력회사 공사","- 1,2차 부싱절연유 채유","2025-04-28 09:00","2025-04-28 18:00","2025-04-28 09:00","2025-04-28 18:00","연속"]
[320,"부산울산","울산","울주울산TP#1 T/L","2025년 가공송전 순시점검 위탁공사(울산)","○ 울주-울산TP#1T/L 등 3개 T/L 초기점검 및 애자오염진단장치 설치 ○ 대상 -  울주-울산TP#1T/L 9~14호 -  남울산-울산TP#2T/L 8,9,S/T - 154kV 남울산-처용#2T/L S/T~6호 ○ 안전이격확보 - 154kV 성암-울산TP#1T/L","2025-05-07 08:00","2025-05-09 18:00","2025-05-07 08:00","2025-05-09 18:00","연속"]
[321,"부산울산","울산","울주월성NP#1 T/L","25년 울산전력지사 변전협력회사 공사","7900, 79710 동작시험","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[322,"부산울산","울산","울주신경산#1 T/L","25년 울산전력지사 변전협력회사 공사","- 7800 보통점검, 7871 동작시험","2025-05-23 09:00","2025-05-23 18:00","2025-05-23 09:00","2025-05-23 18:00","연속"]
[323,"부산울산","울산","울주신경산#2 T/L","25년 울산전력지사 변전협력회사 공사","- 7700 보통점검, 7771 동작시험","2025-05-20 09:00","2025-05-20 18:00","2025-05-20 09:00","2025-05-20 18:00","연속"]
[324,"부산울산","울산","울주울산TP#2 T/L"," 울주-울산TP 등 22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치","2025-05-26 07:00","2025-05-29 18:00","2025-05-26 07:00","2025-05-29 18:00","연속"]
[325,"부산울산","울산","울주월성NP#2 T/L","25년 울산전력지사 변전협력회사 공사","- 7A00, 7A71 동작시험","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[326,"경남","김해송변전부","신마산신김해#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치및 지지애자교체 공사 안전이격","2025-05-17 07:00","2025-05-17 18:00","2025-05-17 07:00","2025-05-17 18:00","연속"]
[327,"경남","김해송변전부","신김해북부산#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치및 지지애자교체 공사","2025-05-17 07:00","2025-05-18 18:00","취소","취소","매일"]
[328,"경남","김해송변전부","신김해북부산#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치및 지지애자교체 공사","2025-05-24 07:00","2025-05-24 18:00","2025-05-24 07:00","2025-05-24 18:00","연속"]
[329,"경남","김해송변전부","신김해S/S CB 7200","신김해S/S  7200 GIS 보통점검","신김해S/S  7200 GIS 보통점검","2025-05-27 09:30","2025-05-27 17:30","2025-05-27 09:30","2025-05-27 17:30","연속"]
[330,"경남","김해송변전부","신김해S/S CB 7100","신김해S/S  7100 GIS 조작시험","신김해S/S  7100 GIS 조작시험","2025-05-29 09:30","2025-05-29 17:30","2025-05-29 09:30","2025-05-29 17:30","연속"]
[331,"경남","김해송변전부","신김해S/S #3 M.Tr","신김해S/S  #3M.Tr 부싱절연유 채유","신김해S/S  #3M.Tr 부싱절연유 채유 (병행) 7770,7772 GIS 조작시험 / 6344 GIS 보통점검","2025-05-07 09:30","2025-05-08 17:30","2025-05-07 09:30","2025-05-08 17:30","연속"]
[332,"경남","직할","창원S/S #2 M.Tr","창원S/S  #2M.Tr 보통점검","창원S/S  #2M.Tr 보통점검 (병행) 추락방지장치 설치, #2S.Tr 보통점검","2025-05-26 09:00","2025-05-29 18:00","2025-05-26 09:00","2025-05-29 18:00","연속"]
[333,"경남","직할","창원S/S #1 M.Tr","창원S/S  #1M.Tr 보통점검","창원S/S  #1M.Tr 보통점검 (병행) 추락방지장치 설치, #1S.Tr 보통점검","2025-05-19 09:00","2025-05-22 18:00","2025-05-19 09:00","2025-05-22 18:00","연속"]
[334,"경남","진주","신남원의령#2 T/L"," 신남원-의령T/L 추락방지장치 설치 공사"," 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2025-05-24 07:00","2025-05-31 18:00","취소","취소","매일"]
[335,"경남","진주","고령의령#1 T/L"," 고령-의령#1T/L 추락방지장치 및 폴리머 점퍼지지 설치공사"," 고령-의령#1T/L 39~116호(78기) 수평형 추락방지장치 및 8~104호(26기) 폴리머 점퍼지지애자 설치","2025-05-05 07:00","2025-05-09 18:00","취소","취소","매일"]
[336,"경남","진주","신남원의령#1 T/L"," 신남원-의령T/L 추락방지장치 설치 공사"," 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2025-05-17 07:00","2025-05-23 18:00","취소","취소","매일"]
[337,"경남","진주","의령S/S #2 M.Tr","의령S/S  #2M.Tr OLTC 정밀점검","의령S/S  #2M.Tr(A,B,C) OLTC 정밀점검","2025-05-19 09:00","2025-05-23 18:00","2025-05-19 09:00","2025-05-23 18:00","연속"]
[338,"경남","통영","신고성S/S #3 M.Tr","신고성S/S #3M.Tr 3차측 현대화 공사","신고성S/S #3M.Tr 3차측 현대화 공사 1. #3M.Tr 3차 측 옥외설비 및 기초 철거 2. #3M.Tr 3차 측 기초 공사 및 SIS 설치 3. #4-3Sh.R 인출 변경 (#4-3Sh.R → #3-1Sh.R)","2025-05-26 10:00","2025-06-20 18:00","2025-05-26 10:00","2025-06-20 18:00","연속"]
[339,"경남","통영","신고성S/S CB 7500","신고성S/S  5호기 7500 GIS 보통점검 등","신고성S/S  5호기 7500 GIS 보통점검, 2차 PT A~C상 보통점검","2025-05-29 09:30","2025-05-29 18:00","2025-05-29 09:30","2025-05-29 18:00","연속"]
[340,"경남","통영","신고성S/S CB 7571","신고성S/S  5호기 7571 GIS 보통점검","신고성S/S  5호기 7571 GIS 보통점검","2025-05-30 09:30","2025-05-30 18:00","2025-05-30 09:30","2025-05-30 18:00","연속"]
[341,"경남","함안","북경남S/S #71 BUS","765kV 북경남S/S #2M.Tr 증설공사","7571 차단기 증설 작업","2025-05-12 09:00","2025-05-14 18:00","2025-05-12 09:00","2025-05-14 18:00","연속"]
[342,"경남","함안","북경남S/S CB 7500","765kV 북경남S/S #2M.Tr 증설공사","7571 차단기 증설 작업, 75BAY BF PNL 개조 작업","2025-05-12 09:00","2025-11-30 18:00","2025-05-12 09:00","2025-11-30 18:00","연속"]
[343,"경남","함안","북경남고령#1 T/L","2024~2025년 달성전력지사 가공송전협력회사 공사","No.21호 부하측 C상 2번 스페이서 교체","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[344,"경남","함안","북경남대구#2 T/L","765kV 북경남S/S #2M.Tr 증설공사","7571 차단기 증설 작업, BF PNL 개조 작업","2025-05-12 09:00","2025-05-14 18:00","2025-05-12 09:00","2025-05-14 18:00","연속"]
[345,"경남","함안","북경남대구#1 T/L","2024~2025년 달성전력지사 가공송전협력회사 공사","북경남-고령 No.21호 부하측 C상 2번 스페이서 교체를 위한 안전확보","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[346,"경남","함안","신마산S/S #5 M.Tr","신마산S/S  #5 M.Tr 2차 GCB 보통점검 등","신마산S/S  #5 M.Tr 2차 GCB 보통점검 등","2025-05-16 09:30","2025-05-16 17:30","2025-05-16 09:30","2025-05-16 17:30","연속"]
[347,"경남","함안","신마산S/S #2 M.Tr","신마산S/S  #2 M.Tr 2차 GCB 보통점검 등","신마산S/S  #2 M.Tr 2차 GCB 보통점검 등","2025-05-15 09:30","2025-05-15 17:30","2025-05-15 09:30","2025-05-15 17:30","연속"]
[348,"경남","함안","의령신마산#1 T/L","신마산S/S  의령신마산#1 T/L GIS C상 LA 이음 조치","신마산S/S  의령신마산#1 T/L GIS C상 LA 이음 조치","2025-05-13 09:30","2025-05-14 17:30","취소","취소","연속"]
[349,"경남","함안","신옥천북경남 T/L","2024~2025년 달성전력지사 가공송전협력회사 공사","압축인류클램프 불량사항 정비(No.37 1번선 전원측 상단 외측)","2025-05-15 09:00","2025-05-16 18:00","2025-05-15 09:00","2025-05-16 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":845,"n_cols":12,"rows_kept":845,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 5월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","군자성수 T/L"," 화양-성수(증) 지중T/L 건설공사, 군자-성수 철거공사","(설치)  XLPE 1,200㎟ × 1회선 / 1.7km(철거)  XLPE 1,200㎟ × 1회선 / 2.9km","2025-05-05 09:00","2025-12-31 18:00","2025-05-05 09:00","2025-12-31 18:00","연속"]
[2,"서울","성동","광장뚝도#2 T/L","뚝도변전소 인출 OF케이블 선종교체공사","OF케이블 선종교체(→XLPE) : 뚝도EBG ∼ J/B#13(7) - 대상선로 : 광장뚝도#1, 광장뚝도#2, 성수뚝도#1T/L (3C×0.06㎞)","2025-05-15 09:00","2025-06-24 18:00","2025-05-15 09:00","2025-06-24 18:00","연속"]
[3,"서울","성동","상봉휘경#2 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 구리상봉T/L GIS 설치 × 1BAY - #2BUS CB, DS설치 및 무부하가압 시험선로","2025-05-28 15:00","2025-05-29 18:00","2025-05-28 15:00","2025-05-29 18:00","연속"]
[4,"서울","성동","상봉휘경#2 T/L","화양, 상봉S/S  지중T/L GIS 설치공사","상봉S/S  구리상봉T/L GIS 설치 × 1BAY - #1BUS 측 신규 GIS CB, DS 도킹 후 무부하가압 시험선로","2025-05-22 13:00","2025-05-23 13:00","2025-05-22 13:00","2025-05-23 13:00","연속"]
[5,"서울","성동","성동휘경#1 T/L","2025 성동전력지사 변전협력회사 공사","- 170kV GIS 조작시험","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[6,"서울","성동","성동S/S CB 6200","2025년 성동P/O 변전협력회사 공사","-  GIS 보통점검","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[7,"서울","성동","구리신내#1 T/L","2025 성동전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[8,"서울","성동","신내상봉 T/L","2025년도 성동전력지사 170kV GIS 정밀점검 공사","정밀점검공사","2025-05-13 09:00","2025-05-15 18:00","2025-05-13 09:00","2025-05-15 18:00","연속"]
[9,"서울","성동","신내S/S CB 6100","2025년도 성동전력지사 170kV GIS 정밀점검 공사","정밀점검공사","2025-05-19 09:00","2025-05-20 18:00","2025-05-19 09:00","2025-05-20 18:00","연속"]
[10,"서울","성동","구리신내#1 T/L","2025년도 성동전력지사 170kV GIS 정밀점검 공사","GIS 정밀점검","2025-05-21 09:00","2025-05-22 18:00","2025-05-21 09:00","2025-05-22 18:00","연속"]
[11,"서울","성동","창동쌍문#1 T/L","2025 성동전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[12,"서울","성동","창동쌍문#2 T/L","2025 성동전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[13,"서울","성동","쌍문S/S CB 6100","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 보통점검","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[14,"서울","성동","화양S/S #1 BUS","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #1BUS 상측정, 인터록 관련 휴전","2025-05-15 14:00","2025-05-15 18:00","2025-05-15 14:00","2025-05-15 18:00","연속"]
[15,"서울","성동","미금화양 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 조작시험","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[16,"서울","성동","화양광장 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 조작시험","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[17,"서울","성동","군자화양#2 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 조작시험","2025-05-12 14:00","2025-05-12 18:00","2025-05-12 14:00","2025-05-12 18:00","연속"]
[18,"서울","성동","군자화양#1 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 조작시험","2025-05-12 09:00","2025-05-12 14:00","2025-05-12 09:00","2025-05-12 14:00","연속"]
[19,"서울","성동","군자화양#2 T/L","화양, 상봉S/S  지중T/L GIS 설치공사"," 화양성수#2T/L 증설 및 군자화양#1T/L, 6100 BUS TIE GIS 교체 - #2BUS 신규 GIS 설치 후 무부하가압 선로","2025-04-30 15:00","2025-05-02 18:00","2025-04-30 15:00","2025-05-02 18:00","연속"]
[20,"서울","중부","중부당인리#2 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-05-20 10:00","2025-05-20 18:00","취소","취소","연속"]
[21,"서울","중부","당인리S/S #65 BUS","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-05-20 10:00","2025-05-20 18:00","2025-05-20 10:00","2025-05-20 18:00","연속"]
[22,"서울","중부","당인리S/S #60 BUS","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-05-15 10:00","2025-05-15 18:00","2025-05-15 10:00","2025-05-15 18:00","연속"]
[23,"서울","중부","당인리목동#1 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","GIS 점검","2025-05-21 10:00","2025-05-22 18:00","2025-05-19 10:00","2025-05-20 18:00","연속"]
[24,"서울","중부","당인리S/S #61 BUS","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-05-22 10:00","2025-05-22 18:00","취소","취소","연속"]
[25,"서울","중부","당인리목동#2 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","GIS 점검","2025-05-26 10:00","2025-05-27 18:00","2025-05-21 10:00","2025-05-22 18:00","연속"]
[26,"서울","중부","당인리S/S #66 BUS","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-05-27 10:00","2025-05-27 18:00","취소","취소","연속"]
[27,"서울","중부","의사당당인리 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","GIS 점검","2025-05-28 10:00","2025-05-29 18:00","2025-05-26 10:00","2025-05-27 18:00","연속"]
[28,"서울","중부","중부당인리#1 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-05-15 10:00","2025-05-15 18:00","2025-05-15 10:00","2025-05-15 18:00","연속"]
[29,"서울","중부","당인리S/S #61 BUS","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-05-29 10:00","2025-05-29 18:00","취소","취소","연속"]
[30,"서울","중부","용산동빙고 T/L","용산동빙고T/L 나진상가 지장 송전선로 이설공사","1. 휴전구간 :  용산-동빙고T/L 2. 접지개소(2개소) - 용산S/S 619-3ES, 동빙고S/S 619-3ES 3. 작업구간 : 관로구간(맨홀1호~2호) - 케이블포설 : 구간(M/H#1~2), 중간접속 : 2개소(M/H#1, #2) 4. 세부작업내용 - 관로구간 철거(M/H#1~M/H#2, 0.35km), 관로구간 설치 : 이설구간 설치(0.4km)","2025-05-14 09:00","2025-06-30 18:00","2025-05-14 09:00","2025-06-30 18:00","연속"]
[31,"서울","중부","수색중부#1 T/L","2025년 중부S/S  장기사용 GIS 교체공사(2차)","-  GIS 교체(수색중부#1, 수색중부#2T/L) - 기타 부대공사","2025-05-19 09:00","2025-06-17 18:00","2025-05-19 09:00","2025-06-17 18:00","연속"]
[32,"서울","중부","수색중부#2 T/L","2025년 중부S/S  장기사용 GIS 교체공사(2차)","-  GIS 교체(수색중부#1, 수색중부#2T/L) - 기타 부대공사","2025-05-19 09:00","2025-06-17 18:00","2025-05-19 09:00","2025-06-17 18:00","연속"]
[33,"서울","중부","중부S/S #60 BUS","2025년 중부S/S  장기사용 GIS 교체공사(2차)","-  GIS 교체(수색중부#1, 수색중부#2T/L) - 기타 부대공사","2025-05-22 09:00","2025-06-02 09:00","2025-05-22 09:00","2025-06-02 09:00","연속"]
[34,"서울","중부","중부당인리#2 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-05-20 10:00","2025-05-20 18:00","2025-05-20 10:00","2025-05-20 18:00","연속"]
[35,"서울","중부","중부당인리#1 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-05-15 10:00","2025-05-15 18:00","2025-05-15 10:00","2025-05-15 18:00","연속"]
[36,"서울","중부","중부S/S #65 BUS","2025년 중부S/S  장기사용 GIS 교체공사(2차)","-  GIS 교체(수색중부#1, 수색중부#2T/L) - 기타 부대공사","2025-05-19 09:00","2025-05-22 09:00","2025-05-19 09:00","2025-05-22 09:00","연속"]
[37,"서울","직할","서소문S/S #1 BUS","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-05-30 18:00","2025-05-30 19:00","2025-05-30 18:00","2025-05-30 19:00","연속"]
[38,"서울","직할","서소문서대문#1 T/L","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-05-29 18:00","2025-05-30 19:00","2025-05-29 18:00","2025-05-30 19:00","연속"]
[39,"서울","직할","서소문S/S #2 BUS","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-05-19 09:00","2025-05-30 18:00","2025-05-19 09:00","2025-05-30 18:00","연속"]
[40,"서울","직할","서소문서대문#1 T/L","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-05-15 18:00","2025-05-16 18:00","2025-05-15 18:00","2025-05-16 18:00","연속"]
[41,"서울","직할","서소문서대문#1 T/L","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-05-08 16:00","2025-05-08 18:00","2025-05-08 16:00","2025-05-08 18:00","연속"]
[42,"서울","직할","서소문S/S #2 BUS","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-05-07 09:00","2025-05-08 18:00","2025-05-07 09:00","2025-05-08 18:00","연속"]
[43,"서울","직할","서소문S/S #1 BUS","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-05-02 18:00","2025-05-02 19:00","2025-05-02 18:00","2025-05-02 19:00","연속"]
[44,"서울","직할","서소문S/S #1 BUS","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-05-12 09:00","2025-05-16 18:00","2025-05-12 09:00","2025-05-16 18:00","연속"]
[45,"서울","직할","서소문서대문#1 T/L","서소문S/S 154,23kV 장기사용 GIS 교체공사","■ 공사명 : 서소문S/S 154,23kV 장기사용 GIS 교체공사 ○  #3,#4M.Tr 1차 GIS 교체(2Bay) ○ 23kV #3,#4M.Tr Bank GIS 교체(16Bay) ○ 23kV 전력케이블 해체 및 접속(19조) ○ 제어케이블 및 접지장치 설치 등 기타공사(1식)","2025-05-01 18:00","2025-05-02 19:00","2025-05-01 18:00","2025-05-02 19:00","연속"]
[46,"서울","직할","안암S/S CB 6100","25년 직할 변전정비협력회사 총액공사","조작시험, 에어링벨브 교체","2025-05-26 10:00","2025-05-26 18:00","2025-05-26 10:00","2025-05-26 18:00","연속"]
[47,"서울","직할","원남미아#1 T/L","25년 직할 변전정비협력회사 총액공사","조작시험, 에어링벨브 교체","2025-05-21 10:00","2025-05-21 18:00","2025-05-21 10:00","2025-05-21 18:00","연속"]
[48,"남서울","강남","신사논일#2 T/L","논일S/S  #4M.Tr용 GIS 설치공사","신규변압기 무부하가압","2025-05-01 09:00","2025-05-02 14:00","취소","취소","연속"]
[49,"남서울","강남","논일S/S #2 BUS","논일S/S  #4M.Tr용 GIS 설치공사"," GIS 1대 설치 주변압기 무부하 가압","2025-05-24 09:00","2025-05-25 14:00","취소","취소","연속"]
[50,"남서울","강남","신사논일#2 T/L","논일S/S  #4M.Tr용 GIS 설치공사","주변압기 무부하가압","2025-05-24 09:00","2025-05-25 14:00","취소","취소","연속"]
[51,"남서울","강남","대치논현#2 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검, 논현측 보통점검 병행","2025-05-14 09:00","2025-05-15 18:00","2025-05-14 09:00","2025-05-15 18:00","연속"]
[52,"남서울","강남","대치논현#1 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검","2025-05-12 09:00","2025-05-13 18:00","2025-05-12 09:00","2025-05-13 18:00","연속"]
[53,"남서울","강남","탄천대치#2 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검","2025-05-07 09:00","2025-05-09 18:00","2025-05-07 09:00","2025-05-09 18:00","연속"]
[54,"남서울","강남","신양재S/S #65 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 DS점검 및 무부하가압","2025-05-20 14:00","2025-05-21 16:00","2025-05-20 14:00","2025-05-21 16:00","연속"]
[55,"남서울","강남","신양재S/S #60 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 DS 점검 및 무부하가압","2025-05-19 09:00","2025-05-20 14:00","2025-05-19 09:00","2025-05-20 14:00","연속"]
[56,"남서울","강남","신양재과천#2 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검, 과천 측 보통점검 병행","2025-05-19 09:00","2025-05-21 18:00","2025-05-19 09:00","2025-05-21 18:00","연속"]
[57,"남서울","동서울","강일상일#2 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","강일-상일#2T/L 초기점검(상일S/S 하자점검 병행)","2025-05-15 09:00","2025-05-15 18:00","2025-05-15 09:00","2025-05-15 18:00","연속"]
[58,"남서울","동서울","강일상일#1 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","강일-상일#1T/L 초기점검(상일S/S 하자점검 병행)","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[59,"남서울","동서울","상일하남열병합#2T/L","2025년도 동서울전력지사 170kV GIS 정밀점검","하남열병합#2T/L 정밀점검 [고객측 발전기 오버홀 기간(25.05.24~31) 내 작업 시행]","2025-05-28 14:00","2025-05-30 18:00","2025-05-24 09:00","2025-05-25 18:00","연속"]
[60,"남서울","동서울","강동상일#2 T/L","2025년도 동서울전력지사 170kV GIS 정밀점검","무부하가압용(상일S/S 하남열병합 #2T/L 정밀점검)","2025-05-29 15:00","2025-05-29 18:00","2025-05-25 15:00","2025-05-25 18:00","연속"]
[61,"남서울","동서울","강동상일#1 T/L","2025년도 동서울전력지사 170kV GIS 정밀점검","무부하가압용(상일S/S 하남열병합 #1T/L 정밀점검)","2025-05-27 15:00","2025-05-27 18:00","2025-05-27 15:00","2025-05-27 18:00","연속"]
[62,"남서울","동서울","상일하남열병합#1T/L","2025년도 동서울전력지사 170kV GIS 정밀점검","하남열병합#1T/L 정밀점검 [고객측 발전기 오버홀 기간(25.05.24~31) 내 작업 시행]","2025-05-26 09:00","2025-05-28 14:00","2025-05-26 09:00","2025-05-27 18:00","연속"]
[63,"남서울","동서울","상일S/S #1 BUS","2025년도 동서울전력지사 170kV GIS 정밀점검","무부하가압용(상일S/S 하남열병합 #1T/L 정밀점검)","2025-05-27 15:00","2025-05-27 18:00","2025-05-27 15:00","2025-05-27 18:00","연속"]
[64,"남서울","동서울","상일S/S #2 BUS","2025년도 동서울전력지사 170kV GIS 정밀점검","무부하가압용(상일S/S 하남열병합 #2T/L 정밀점검)","2025-05-29 15:00","2025-05-29 18:00","2025-05-25 15:00","2025-05-25 18:00","연속"]
[65,"남서울","동서울","송파잠실#3 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","송파-잠실#3T/L 조작시험(잠실S/S 조작시험 병행)","2025-05-12 14:00","2025-05-12 18:00","2025-05-12 14:00","2025-05-12 18:00","연속"]
[66,"남서울","동서울","송파잠실#4 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","송파-잠실#4T/L 조작시험","2025-05-13 09:00","2025-05-13 14:00","2025-05-13 09:00","2025-05-13 14:00","연속"]
[67,"남서울","동서울","송파잠실#2 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","송파-잠실#2T/L 조작시험(잠실S/S 조작시험 병행)","2025-05-12 09:00","2025-05-12 14:00","2025-05-12 09:00","2025-05-12 14:00","연속"]
[68,"남서울","동서울","신장덕소#1 T/L","2025년도 동서울전력지사 170kV GIS 정밀점검","신장-덕소 #1T/L 정밀점검","2025-05-19 09:00","2025-05-21 14:00","2025-05-19 09:00","2025-05-20 18:00","연속"]
[69,"남서울","동서울","동서울신장#1 T/L","2025년도 동서울전력지사 170kV GIS 정밀점검","무부하가압용(신장S/S 신장-덕소#1T/L 정밀점검)","2025-05-20 15:00","2025-05-20 18:00","취소","취소","연속"]
[70,"남서울","동서울","신장S/S #1 BUS","2025년도 동서울전력지사 170kV GIS 정밀점검","무부하가압용(신장S/S 신장-덕소#1T/L 정밀점검)","2025-05-20 15:00","2025-05-20 18:00","취소","취소","연속"]
[71,"남서울","영등포","대방S/S CB 6100","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 대방S/S #60-#65 BUS TIE","2025-05-28 14:00","2025-05-30 18:00","2025-05-14 09:00","2025-05-16 18:00","연속"]
[72,"남서울","영등포","대방신길#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 대방S/S 6100 정밀점검 후 무부하가압","2025-05-30 16:00","2025-05-30 18:00","2025-05-16 16:00","2025-05-16 18:00","연속"]
[73,"남서울","영등포","대방신길#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 대방S/S 6233 정밀점검 후 무부하가압","2025-05-23 16:00","2025-05-23 18:00","2025-05-23 16:00","2025-05-23 18:00","연속"]
[74,"남서울","영등포","대방S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 1. 대방S/S 6333 정밀점검 후 무부하가압(5/28 09:00~ 14:00) 2. 대방S/S 6100 정밀점검 관련 BUS 휴전(5/28 14:00 ~ 5/30 18:00)","2025-05-28 09:00","2025-05-30 18:00","2025-05-28 09:00","2025-05-30 18:00","연속"]
[75,"남서울","영등포","대방S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 대방S/S 6233 정밀점검 후 무부하가압","2025-05-23 16:00","2025-05-23 18:00","2025-05-23 16:00","2025-05-23 18:00","연속"]
[76,"남서울","영등포","대방S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 대방S/S 6133 정밀점검 후 무부하가압","2025-05-21 09:00","2025-05-21 14:00","2025-05-21 09:00","2025-05-21 14:00","연속"]
[77,"남서울","영등포","대방신길#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 대방S/S 6133 정밀점검 후 무부하가압","2025-05-21 09:00","2025-05-21 14:00","2025-05-21 09:00","2025-05-21 14:00","연속"]
[78,"남서울","영등포","대방신길#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 대방S/S 6333 정밀점검 후 무부하가압","2025-05-28 09:00","2025-05-28 14:00","2025-05-28 09:00","2025-05-28 14:00","연속"]
[79,"남서울","영등포","오류목동 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 오류S/S 6333 정밀점검 후 무부하가압","2025-05-13 16:00","2025-05-13 18:00","2025-05-13 16:00","2025-05-13 18:00","연속"]
[80,"남서울","영등포","오류목동 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 오류S/S 6233 정밀점검 후 무부하가압","2025-05-09 16:00","2025-05-09 18:00","2025-05-09 16:00","2025-05-09 18:00","연속"]
[81,"남서울","영등포","천왕구로#1 T/L","'25~'26년 영등포전력지사 지중송전 협력회사 공사","○  천왕-구로#1,2T/L 비규격 접지선 교체 및 OF채유밸브 설치","2025-05-12 09:00","2025-05-23 18:00","2025-05-12 09:00","2025-05-23 18:00","연속"]
[82,"남서울","영등포","천왕구로#2 T/L","'25~'26년 영등포전력지사 지중송전 협력회사 공사","○  천왕-구로#1,2T/L 비규격 접지선 교체 및 OF채유밸브 설치","2025-05-12 09:00","2025-05-23 18:00","2025-05-12 09:00","2025-05-23 18:00","연속"]
[83,"남서울","영등포","중동화곡#2 T/L","24~25년 영등포전력지사 변전협력회사 공사","170kV GIS 보통점검 : 중동-화곡#1, #2T/L","2025-05-17 14:00","2025-05-17 18:00","2025-05-03 14:00","2025-05-03 18:00","연속"]
[84,"남서울","영등포","중동화곡#1 T/L","24~25년 영등포전력지사 변전협력회사 공사","170kV GIS 보통점검 : 중동-화곡#1, #2T/L","2025-05-17 09:00","2025-05-17 14:00","2025-05-03 09:00","2025-05-03 14:00","연속"]
[85,"남서울","영등포","독산대방#1 T/L","2025년 영등포전력지사 변전협력회사 총액공사","독산S/S 독산-대방#1T/L 보통점검","2025-05-11 09:00","2025-05-11 14:00","2025-05-11 09:00","2025-05-11 14:00","연속"]
[86,"남서울","영등포","독산대방#2 T/L","2025년 영등포전력지사 변전협력회사 총액공사","독산S/S 독산-대방#2T/L 보통점검","2025-05-11 14:00","2025-05-11 18:00","2025-05-11 14:00","2025-05-11 18:00","연속"]
[87,"남서울","직할","신문래노들 T/L","170kV GIS 조작시험, 전자변 교체","170kV GIS 조작시험, 전자변 교체","2025-05-29 09:00","2025-05-29 18:00","취소","취소","연속"]
[88,"남서울","직할","노들노량진 T/L","170kV GIS 보통점검, 전자변 교체","170kV GIS 보통점검, 전자변 교체 - 노들 측 조작시험, 전자변 교체 병행","2025-05-28 09:00","2025-05-28 18:00","2025-05-28 09:00","2025-05-28 18:00","연속"]
[89,"남서울","직할","여의노량진 T/L","170kV GIS 보통점검","170kV GIS 보통점검 - 여의 측 조작시험 병행","2025-05-27 09:00","2025-05-27 18:00","2025-05-27 09:00","2025-05-27 18:00","연속"]
[90,"남서울","직할","신문래노량진 T/L","170kV GIS 조작시험, PITR 결선","170kV GIS 조작시험, PITR 결선","2025-05-26 09:00","2025-05-26 18:00","2025-05-26 09:00","2025-05-26 18:00","연속"]
[91,"남서울","직할","신문래S/S #60 BUS","170kV GIS 정밀점검공사(#3M.Tr 2차 GIS)","신문래S/S #3M.Tr 2차 GIS 정밀점검 DS부 점검용","2025-05-21 14:00","2025-05-22 16:00","취소","취소","연속"]
[92,"남서울","직할","신문래S/S #66 BUS","170kV GIS 정밀점검공사(#2M.Tr 2차 GIS)","신문래S/S #2M.Tr 2차 GIS 정밀점검 DS부 점검용","2025-05-01 16:00","2025-05-02 18:00","취소","취소","연속"]
[93,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검 공사(신문래#3M.Tr 2차)","170kV GIS 정밀점검 공사(신문래#3M.Tr 2차-무부하가압용)","2025-05-23 16:00","2025-05-23 18:00","취소","취소","연속"]
[94,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검 공사(신문래#3M.Tr 2차)","170kV GIS 정밀점검 공사(신문래#3M.Tr 2차-#2DS 점검용)","2025-05-22 16:00","2025-05-23 18:00","취소","취소","연속"]
[95,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검 공사(신문래#3M.Tr 2차)","170kV GIS 정밀점검 공사(신문래#3M.Tr 2차-무부하가압용)","2025-05-22 14:00","2025-05-22 16:00","취소","취소","연속"]
[96,"남서울","직할","신문래S/S #60 BUS","170kV GIS 정밀점검 공사(신문래#3M.Tr 2차)","170kV GIS 정밀점검 공사(신문래#3M.Tr 2차-#1DS 점검용)","2025-05-21 14:00","2025-05-22 16:00","취소","취소","연속"]
[97,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS)","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS 무부하가압용)","2025-05-20 10:00","2025-05-20 12:00","취소","취소","연속"]
[98,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS)","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS #2DS 점검용)","2025-05-20 12:00","2025-05-21 14:00","취소","취소","연속"]
[99,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS)","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS 무부하가압용)","2025-05-21 12:00","2025-05-21 14:00","취소","취소","연속"]
[100,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사","신문래S/S #2M.Tr 2차 GIS 정밀점검 무부하 가압용","2025-05-01 14:00","2025-05-01 16:00","취소","취소","연속"]
[101,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사","신문래S/S #2M.Tr 2차 GIS 정밀점검 무부하 가압용","2025-05-02 14:00","2025-05-02 18:00","취소","취소","연속"]
[102,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(65-66SEC GIS)","신문래S/S 65-66SEC GIS 정밀점검 무부하가압용","2025-05-08 12:00","2025-05-08 14:00","취소","취소","연속"]
[103,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사(65-66SEC GIS)","신문래S/S 65-66SEC GIS 정밀점검 무부하가압용","2025-05-09 14:00","2025-05-09 18:00","취소","취소","연속"]
[104,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(6100 BUS-TIE GIS)","신문래S/S 6100 BUS-TIE GIS 정밀점검 무부하가압용","2025-05-13 10:00","2025-05-13 12:00","취소","취소","연속"]
[105,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(6100 BUS-TIE GIS)","신문래S/S 6100 BUS-TIE GIS 정밀점검 무부하가압용","2025-05-14 12:00","2025-05-14 14:00","취소","취소","연속"]
[106,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사(6200 BUS-TIE GIS)","신문래S/S 6200 BUS-TIE GIS 정밀점검 무부하가압용","2025-05-15 14:00","2025-05-15 16:00","2025-05-20 12:00","2025-05-20 14:00","연속"]
[107,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사(6200 BUS-TIE GIS)","신문래S/S 6200 BUS-TIE GIS 정밀점검 무부하가압용","2025-05-16 14:00","2025-05-16 18:00","2025-05-21 14:00","2025-05-21 18:00","연속"]
[108,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검공사(#3M.Tr 2차 GIS)","신문래S/S #3M.Tr 2차 GIS 정밀점검 DS부 점검용","2025-05-22 16:00","2025-05-23 18:00","취소","취소","연속"]
[109,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검 공사(#65-#66SEC GIS)","170kV GIS 정밀점검 공사(#65-#66SEC GIS #1DS 점검용)","2025-05-07 09:00","2025-05-08 14:00","취소","취소","연속"]
[110,"남서울","직할","신문래S/S #66 BUS","170kV GIS 정밀점검 공사(#65-#66SEC GIS)","170kV GIS 정밀점검 공사(#65-#66SEC GIS #2DS 점검용)","2025-05-08 14:00","2025-05-09 18:00","취소","취소","연속"]
[111,"남서울","직할","신문래S/S #60 BUS","170kV GIS 정밀점검 공사(6100 BUS-TIE GIS)","170kV GIS 정밀점검 공사(6100 BUS-TIE GIS #1DS 점검용)","2025-05-12 09:00","2025-05-13 12:00","취소","취소","연속"]
[112,"남서울","직할","신문래S/S #60 BUS","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS)","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS #1DS 점검용)","2025-05-19 09:00","2025-05-20 12:00","취소","취소","연속"]
[113,"남서울","직할","신문래S/S #61 BUS","170kV GIS 정밀점검 공사(6200 BUS-TIE GIS)","170kV GIS 정밀점검 공사(6200 BUS-TIE GIS #1DS 점검용)","2025-05-14 14:00","2025-05-15 16:00","2025-05-19 09:00","2025-05-20 14:00","연속"]
[114,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검 공사(6100 BUS-TIE GIS)","170kV GIS 정밀점검 공사(6100 BUS-TIE GIS #2DS 점검용)","2025-05-13 12:00","2025-05-14 14:00","취소","취소","연속"]
[115,"남서울","직할","신문래S/S #66 BUS","170kV GIS 정밀점검 공사(6200 BUS-TIE GIS)","170kV GIS 정밀점검 공사(6200 BUS-TIE GIS #2DS 점검용)","2025-05-15 16:00","2025-05-16 18:00","2025-05-20 14:00","2025-05-21 18:00","연속"]
[116,"남서울","직할","신문래여의 T/L","170kV GIS 조작시험, PITR 결선","170kV GIS 조작시험, PITR 결선","2025-05-30 09:00","2025-05-30 18:00","취소","취소","연속"]
[117,"인천","김포","경서S/S #1 BUS","경서S/S  #3M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #3M.Tr 1차 GIS 정밀점검(무부하가압용) -#1BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-05-30 09:00","2025-05-30 16:00","취소","취소","연속"]
[118,"인천","김포","신경서경서#1 T/L","경서S/S  #3M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #3M.Tr 1차 GIS 정밀점검(무부하가압용) -#1BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-05-30 09:00","2025-05-30 16:00","취소","취소","연속"]
[119,"인천","김포","경서북인천#2 T/L","경서S/S  경서-북인천#2T/L GIS 보통점검","경서S/S  경서-북인천#2T/L GIS 보통점검","2025-05-27 10:00","2025-05-27 18:00","2025-05-27 10:00","2025-05-27 18:00","연속"]
[120,"인천","김포","경서북인천#1 T/L","경서S/S  경서-북인천#1T/L GIS 보통점검","경서S/S  경서-북인천#1T/L GIS 보통점검","2025-05-26 10:00","2025-05-26 18:00","2025-05-26 10:00","2025-05-26 18:00","연속"]
[121,"인천","김포","경서북인천#1 T/L","경서S/S  6100 GIS 정밀점검(무부하가압용)","경서S/S  6100 GIS 정밀점검(무부하가압용) -#1BUS, 경서북인천#1T/L 활용 무부하가압 (2시간 이내)","2025-05-24 09:00","2025-05-24 18:00","2025-05-24 09:00","2025-05-24 18:00","연속"]
[122,"인천","김포","경서S/S #1 BUS","경서S/S  경서-양촌#1T/L GIS 정밀점검(무부하가압용)","경서S/S  경서-양촌#1T/L GIS 정밀점검(무부하가압용) -#1BUS, 경서양촌#1T/L 자체 활용 무부하가압 (2시간 이내)","2025-05-21 09:00","2025-05-21 13:00","2025-05-21 09:00","2025-05-21 13:00","연속"]
[123,"인천","김포","경서양촌#1 T/L","경서S/S  경서-양촌#1T/L GIS 정밀점검","경서S/S  경서-양촌#1T/L GIS 정밀점검","2025-05-19 11:00","2025-05-21 13:00","2025-05-19 11:00","2025-05-21 13:00","연속"]
[124,"인천","김포","경서S/S #1 BUS","경서S/S  6100 GIS 정밀점검(무부하가압용)","경서S/S  6100 GIS 정밀점검(무부하가압용) -#1BUS, 경서북인천#1T/L 활용 무부하가압 (2시간 이내)","2025-05-24 09:00","2025-05-24 18:00","2025-05-24 09:00","2025-05-24 18:00","연속"]
[125,"인천","김포","경서S/S CB 6100","경서S/S  #1-#2 BUS TIE GIS 6100 정밀점검","경서S/S  #1-#2 BUS TIE GIS 6100 정밀점검","2025-05-22 09:00","2025-05-24 18:00","취소","취소","연속"]
[126,"인천","김포","신경서경서#1 T/L","경서S/S  #4M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #4M.Tr 1차 GIS 정밀점검(무부하가압용) -#2BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-05-15 18:00","2025-05-15 20:00","2025-05-15 18:00","2025-05-15 20:00","연속"]
[127,"인천","김포","경서S/S #2 BUS","경서S/S  #4M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #4M.Tr 1차 GIS 정밀점검(무부하가압용) -#2BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-05-15 18:00","2025-05-15 20:00","2025-05-15 18:00","2025-05-15 20:00","연속"]
[128,"인천","김포","신경서경서#1 T/L","경서S/S  #2M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #2M.Tr 1차 GIS 정밀점검(무부하가압용) -#2BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-05-28 09:00","2025-05-28 16:00","2025-05-28 09:00","2025-05-28 16:00","연속"]
[129,"인천","김포","경서S/S #2 BUS","경서S/S  #2M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #2M.Tr 1차 GIS 정밀점검(무부하가압용) -#2BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-05-28 09:00","2025-05-28 16:00","2025-05-28 09:00","2025-05-28 16:00","연속"]
[130,"인천","김포","신경서경서#1 T/L","경서S/S  #1M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #1M.Tr 1차 GIS 정밀점검(무부하가압용) -#1BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-05-18 09:00","2025-05-18 16:00","2025-05-18 09:00","2025-05-18 16:00","연속"]
[131,"인천","김포","경서S/S #1 BUS","경서S/S  #1M.Tr 1차 GIS 정밀점검(무부하가압용)","경서S/S  #1M.Tr 1차 GIS 정밀점검(무부하가압용) -#1BUS, 신경서경서#1T/L 활용 무부하가압 (2시간 이내)","2025-05-18 09:00","2025-05-18 16:00","2025-05-18 09:00","2025-05-18 16:00","연속"]
[132,"인천","김포","김포불로#1 T/L","불로S/S  불로-김포#1T/L GIS 하자점검","불로S/S  불로-김포#1T/L GIS 하자점검 (병행) 김포S/S 불로-김포#1T/L GIS 보통점검","2025-05-16 10:00","2025-05-16 18:00","취소","취소","연속"]
[133,"인천","김포","양곡S/S CB 6100","양곡S/S  GIS 교체공사(2차)","- BUS-TIE 이용 무부하 가압 - #1M.Tr 1차 GIS 교체","2025-05-02 14:00","2025-05-03 14:00","2025-05-02 14:00","2025-05-03 14:00","연속"]
[134,"인천","김포","신김포양곡#1 T/L","양곡S/S  GIS 교체공사(2차)","- 신김포양곡#1T/L 이용 무부하 가압 - #1M.Tr 1차 GIS 교체","2025-05-02 14:00","2025-05-03 14:00","취소","취소","연속"]
[135,"인천","김포","양촌양곡#1 T/L","양곡S/S  GIS 교체공사(2차)","- 양촌양곡#1T/L 이용 무부하 가압 - #1M.Tr 1차 GIS 교체","2025-05-02 14:00","2025-05-03 14:00","취소","취소","연속"]
[136,"인천","김포","양곡S/S #60 BUS","양곡S/S  GIS 교체공사(2차)","- #1BUS 상체크 및 계통시험 - #1M.Tr 1차 GIS 교체","2025-05-03 14:00","2025-05-03 18:00","2025-05-03 14:00","2025-05-03 18:00","연속"]
[137,"인천","김포","양곡S/S #65 BUS","양곡S/S  GIS 교체공사(3차)","- #2M.Tr 1차, 신김포양곡#1T/L,  PT&ES GIS 교체","2025-05-16 09:00","2025-05-22 15:00","2025-05-16 09:00","2025-05-22 15:00","연속"]
[138,"인천","김포","신김포양곡#1 T/L","양곡S/S  GIS 교체공사(3차)","- #2M.Tr 1차, 신김포양곡#1T/L,  PT&ES GIS 교체","2025-05-16 09:00","2025-06-15 18:00","2025-05-16 09:00","2025-06-15 18:00","연속"]
[139,"인천","김포","양곡S/S CB 6100","양곡S/S  GIS 교체공사(3차)_B/T(6100)이용무부하","- BUS-TIE(6100) 이용 무부하 가압 - #2M.Tr 1차, 신김포양곡#1T/L,  PT&ES GIS 교체","2025-05-21 15:00","2025-05-22 15:00","2025-05-21 15:00","2025-05-22 15:00","연속"]
[140,"인천","김포","양곡S/S #60 BUS","양곡S/S  GIS 교체공사(3차)","- #2M.Tr 1차, 신김포양곡#1T/L,  PT&ES GIS 교체","2025-05-22 15:00","2025-06-07 14:00","2025-05-22 15:00","2025-06-07 14:00","연속"]
[141,"인천","김포","경서양촌#2 T/L","'24~'25년 부평, 김포전력지사 가공송전 협력회사 총액공사","고정형폴리머점퍼지지애자 설치","2025-05-28 07:30","2025-05-30 18:00","2025-05-12 07:30","2025-05-14 18:00","매일"]
[142,"인천","김포","왕길양촌#2 T/L","24~25년 부평,김포전력지사 가공송전 협력회사 공사","폴리머 설치","2025-05-31 07:30","2025-05-31 18:00","취소","취소","연속"]
[143,"인천","부평","관교주안 T/L","주안-관교 #1T/L 보호반 대체","주안-관교 #1T/L 보호반 대체, 모자익배선 철거 주안-관교#1T/L 677 GIS 보통","2025-05-12 09:00","2025-05-15 18:00","취소","취소","연속"]
[144,"인천","부평","주안만수#2 T/L","만수S/S  주안-만수#2T/L GIS","만수S/S  주안-만수#2T/L GIS","2025-05-30 09:00","2025-05-30 18:00","취소","취소","연속"]
[145,"인천","부평","관교만수#2 T/L","만수S/S  관교-만수#2T/L 637 GIS 보통점검","만수S/S  관교-만수#2T/L 637 GIS 보통점검","2025-05-28 09:00","2025-05-28 18:00","취소","취소","연속"]
[146,"인천","부평","주안만수#1 T/L"," 주안-만수#1T/L 647 GIS 보통점검"," 주안-만수#1T/L 647 GIS 보통점검","2025-05-26 09:00","2025-05-26 18:00","취소","취소","연속"]
[147,"인천","부평","신가좌부개#2 T/L","부개S/S  GIS 교체공사(2차)(무부하가압)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-10 14:00","2025-05-11 14:00","2025-05-20 18:00","2025-05-21 18:00","연속"]
[148,"인천","부평","부개S/S #2 BUS","부개S/S  GIS 교체공사(2차)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-11 14:00","2025-05-21 14:00","2025-05-21 18:00","2025-05-28 16:00","연속"]
[149,"인천","부평","부개S/S #1 BUS","부개S/S  GIS 교체공사(1차)(상체크)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-13 14:00","2025-05-13 18:00","2025-05-14 11:00","2025-05-21 18:00","연속"]
[150,"인천","부평","신가좌부개#2 T/L","부개S/S  GIS 교체공사(2차)(무부하가압, 상체크)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-21 14:00","2025-05-22 18:00","2025-05-27 16:00","2025-05-28 16:00","연속"]
[151,"인천","부평","부개S/S #1 BUS","부개S/S  GIS 교체공사(2차)(상체크)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-22 14:00","2025-05-22 18:00","2025-05-28 14:00","2025-05-28 18:00","연속"]
[152,"인천","부평","신가좌부개#2 T/L","부개S/S  GIS 교체공사(2차)(무부하가압)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-03 14:00","2025-05-03 15:00","2025-05-09 15:00","2025-05-10 15:00","연속"]
[153,"인천","부평","부개S/S #2 BUS","부개S/S  GIS 교체공사(1차)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-02 14:00","2025-05-13 14:00","2025-05-01 14:00","2025-05-10 16:00","연속"]
[154,"인천","부평","신가좌부개#2 T/L","부개S/S  GIS 교체공사(1차)(무부하가압, 상체크)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-12 14:00","2025-05-13 18:00","2025-05-09 15:00","2025-05-10 15:00","연속"]
[155,"인천","부평","부개S/S #1 BUS","부개S/S  GIS 교체공사(2차)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-03 15:00","2025-05-11 14:00","2025-05-10 16:00","2025-05-10 18:00","연속"]
[156,"인천","부평","부개S/S #2 BUS","부개S/S  GIS 교체공사(2차)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-01 09:00","2025-05-03 15:00","2025-05-12 09:00","2025-05-14 11:00","연속"]
[157,"인천","부평","신가좌부개#2 T/L","부개S/S  GIS 교체공사(1차)(무부하가압)","- 1차 : #1M.Tr 1차,  BUS-TIE, PT&ES GIS 교체 - 2차 : #3M.Tr 1차 GIS 교체","2025-05-01 14:00","2025-05-02 15:00","취소","취소","연속"]
[158,"인천","부평","서인천C/C CB 6733"," #7 G.Tr 1차 GIS 조작시험"," #7 G.Tr 1차 GIS 조작시험","2025-05-26 09:00","2025-05-26 18:00","2025-05-26 09:00","2025-05-26 18:00","연속"]
[159,"인천","부평","신가좌신현#2 T/L"," 남동-관교 등 4개 T/L 노후 피뢰기 교체공사","피뢰기 교체공사(3상)","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[160,"인천","부평","신가좌S/S SEC CB 66670"," #66-#67 SEC GIS 보통점검"," #66-#67 SEC GIS 보통점검","2025-05-24 09:00","2025-05-24 18:00","2025-05-24 09:00","2025-05-24 18:00","연속"]
[161,"인천","부평","신가좌S/S SEC CB 65660"," #65-#66 SEC GIS 보통점검"," #65-#66 SEC GIS 보통점검","2025-05-17 09:00","2025-05-17 18:00","2025-05-17 09:00","2025-05-17 18:00","연속"]
[162,"인천","부평","신가좌부개#2 T/L"," 신가좌-부개#2T/L 627 GIS 조작시험"," 신가좌-부개#2T/L 627 GIS 조작시험","2025-05-29 13:00","2025-05-29 18:00","2025-05-27 09:00","2025-05-27 13:00","연속"]
[163,"인천","부평","신가좌부개#1 T/L"," 신가좌-부개#1T/L 617 GIS 조작시험"," 신가좌-부개#1T/L 617 GIS 조작시험","2025-05-29 09:00","2025-05-29 13:00","2025-05-27 09:00","2025-05-27 13:00","연속"]
[164,"인천","부평","신가좌S/S SEC CB 60610"," #60-#61 SEC GIS 조작시험"," #60-#61 SEC GIS 조작시험","2025-05-31 09:00","2025-05-31 13:00","2025-05-31 09:00","2025-05-31 13:00","연속"]
[165,"인천","부평","신가좌S/S SEC CB 61620"," #61-#62 SEC GIS 조작시험"," #61-#62 SEC GIS 조작시험","2025-05-31 13:00","2025-05-31 18:00","2025-05-31 13:00","2025-05-31 18:00","연속"]
[166,"인천","부평","신가좌신현#1 T/L"," 남동-관교 등 4개 T/L 노후 피뢰기 교체공사","피뢰기 교체공사(3상)","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[167,"인천","부평","신가좌인천#3 T/L"," 신가좌-인천#3T/L 637 GIS 조작시험"," 신가좌-인천#3T/L 637 GIS 조작시험","2025-05-31 09:00","2025-05-31 18:00","2025-05-31 09:00","2025-05-31 18:00","연속"]
[168,"인천","부평","신경서S/S #66 BUS","EBG 가스 채취밸브 설치 및 해체점검 공사"," 신경서-청라#2T/L 무부하 시험가압용","2025-05-24 18:00","2025-05-25 18:00","취소","취소","연속"]
[169,"인천","부평","신경서S/S #66 BUS","EBG 가스 채취밸브 설치 및 해체점검 공사"," 신경서-경서#2T/L 무부하 시험가압용","2025-05-31 18:00","2025-06-01 18:00","취소","취소","연속"]
[170,"인천","부평","신경서경서#2 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강 - 열경화공법 적용개소 구조 개선","2025-05-26 08:00","2025-06-01 18:00","취소","취소","연속"]
[171,"인천","부평","신경서S/S #61 BUS","EBG 가스 채취밸브 설치 및 해체점검 공사"," 신경서-청라#1T/L 무부하 시험가압용","2025-05-15 18:00","2025-05-16 18:00","취소","취소","연속"]
[172,"인천","부평","신경서영종 T/L"," 신경서-영종T/L 647 GIS 보통점검"," 신경서-영종T/L 647 GIS 보통점검","2025-05-23 09:00","2025-05-23 18:00","2025-05-23 09:00","2025-05-23 18:00","연속"]
[173,"인천","부평","영종을왕 T/L","영종S/S  영종-을왕T/L 687 GIS 보통점검","영종S/S  영종-을왕T/L 687 GIS 보통점검","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[174,"인천","부평","북인천원창 T/L","원창S/S  북인천-원창T/L 6B7 GIS 보통점검","원창S/S  북인천-원창T/L 6B7 GIS 보통점검","2025-05-15 18:00","2025-05-15 20:00","취소","취소","연속"]
[175,"인천","부평","인천CC포스코CC#2 T/L"," 인천CC-포스코CC#2T/L 677 GIS 조작시험"," 인천CC-포스코CC#2T/L 677 GIS 조작시험","2025-05-28 13:00","2025-05-28 18:00","2025-05-28 13:00","2025-05-28 18:00","연속"]
[176,"인천","부평","인천CC포스코CC#1 T/L"," 인천CC-포스코CC#1T/L 637 GIS 조작시험"," 인천CC-포스코CC#1T/L 637 GIS 조작시험","2025-05-28 09:00","2025-05-28 13:00","2025-05-28 09:00","2025-05-28 13:00","연속"]
[177,"인천","부평","인천남인천#1 T/L"," 인천-남인천#1T/L 647 GIS 보통점검"," 인천-남인천#1T/L 647 GIS 보통점검","2025-05-03 09:00","2025-05-03 18:00","2025-05-03 09:00","2025-05-03 18:00","연속"]
[178,"인천","부평","신가좌주안#1 T/L"," 주안-관교등 4개T/L 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링 유니트점검 시행","2025-05-01 09:00","2025-05-03 18:00","취소","취소","연속"]
[179,"인천","부평","신가좌주안#2 T/L"," 주안-관교등 4개T/L 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링 유니트점검 시행","2025-05-07 09:00","2025-05-09 18:00","취소","취소","연속"]
[180,"인천","부평","주안S/S CB 6100"," 60-65 BUS 보호반 대체"," 60-65 BUS 보호반 대체","2025-05-19 09:00","2025-05-23 18:00","취소","취소","연속"]
[181,"인천","부평","학익연수#1 T/L"," 학익-연수#1T/L 637 GIS 조작시험"," 학익-연수#1T/L 637 GIS 조작시험","2025-05-24 09:00","2025-05-24 13:00","취소","취소","연속"]
[182,"인천","부평","학익연수#2 T/L"," 학익-연수#2T/L 647 GIS 조작시험"," 학익-연수#2T/L 647 GIS 조작시험","2025-05-24 13:00","2025-05-24 18:00","취소","취소","연속"]
[183,"인천","시흥","신시흥남동#1 T/L","인천남동 첨단산업단지  신시흥-남동T/L 지중화공사(가공)","1. 공사구간 :  신시흥-남동T/L No.35~신동C/T 2. 선로길이 : ACSR/AW 410㎟ × 2B × 2C, 0.364km 3. 지 지 물 : C/T 신설 1기, 임시철탑 2기, 철탑철거 2기","2025-05-19 08:00","2025-05-23 18:00","취소","취소","연속"]
[184,"인천","시흥","신시흥남동#2 T/L","인천남동 첨단산업단지  신시흥-남동T/L 지중화공사(가공)","1. 공사구간 :  신시흥-남동T/L No.35~신동C/T 2. 선로길이 : ACSR/AW 410㎟ × 2B × 2C, 0.364km 3. 지 지 물 : C/T 신설 1기, 임시철탑 2기, 철탑철거 2기","2025-05-26 08:00","2025-05-30 18:00","취소","취소","연속"]
[185,"인천","시흥","오봉남동#1 T/L","대한전선제 EBG 가스채취밸브 보강공사","대한전선제 EBG 가스채취밸브 보강공사","2025-05-12 08:00","2025-05-14 18:00","취소","취소","연속"]
[186,"인천","시흥","오봉남동#2 T/L","대한전선제 EBG 가스채취밸브 보강공사","대한전선제 EBG 가스채취밸브 보강공사","2025-05-15 08:00","2025-05-17 18:00","취소","취소","연속"]
[187,"인천","시흥","남정왕S/S CB 6100","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  #1 BUS TIE(6100) GIS 정밀점검 - 정밀점검 및 무부하가압을 위한 휴전","2025-05-20 09:00","2025-05-22 18:00","취소","취소","연속"]
[188,"인천","시흥","남시화남정왕#1 T/L","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  6100 BUS TIE 정밀점검 무부하가압 - 정밀점검 후 무부하가압을 위한 휴전","2025-05-22 09:00","2025-05-22 18:00","취소","취소","연속"]
[189,"인천","시흥","남시화남정왕#2 T/L","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  남시화-남정왕#2T/L GIS 정밀점검 - 정밀점검 및 무부하가압을 위한 휴전","2025-05-28 14:00","2025-05-30 18:00","2025-05-26 09:00","2025-05-28 18:00","연속"]
[190,"인천","시흥","남정왕S/S #60 BUS","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  6100 BUS TIE 정밀점검 무부하가압 - 정밀점검 후 무부하가압을 위한 휴전","2025-05-20 09:00","2025-05-22 18:00","취소","취소","연속"]
[191,"인천","시흥","남시화남정왕#1 T/L","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  남시화-남정왕#1T/L GIS 정밀점검 - 정밀점검 및 무부하가압을 위한 휴전","2025-05-26 09:00","2025-05-28 14:00","2025-05-21 09:00","2025-05-23 14:00","연속"]
[192,"인천","시흥","서서울#2소래 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기)","2025-05-17 07:30","2025-05-18 18:00","취소","취소","매일"]
[193,"인천","시흥","소래S/S CB 6100","소래S/S 60-65 모선보호반 대체공사","소래S/S 60-65 모선보호반 대체공사","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[194,"인천","시흥","온수소래 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","추락방지장치(수평)설치 No.76~82 (7기), 성능저하 애자련 교체 No.76,86 (2기)","2025-05-10 07:30","2025-05-11 18:00","취소","취소","매일"]
[195,"인천","시흥","신광명소래 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기)","2025-05-17 07:30","2025-05-18 18:00","취소","취소","매일"]
[196,"인천","시흥","서안양소래 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","추락방지장치(수평)설치 No.76~82 (7기), 성능저하 애자련 교체 No.76,86 (2기)","2025-05-10 07:30","2025-05-11 18:00","취소","취소","매일"]
[197,"인천","시흥","신시흥북시화#1 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.1~25(25기) 및 소도체 이도 조정","2025-05-17 07:30","2025-05-18 18:00","2025-05-17 07:30","2025-05-18 18:00","매일"]
[198,"인천","시흥","신시흥시화#1 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.1~25(25기) 및 소도체 이도 조정","2025-05-17 07:30","2025-05-18 18:00","2025-05-17 07:30","2025-05-18 18:00","매일"]
[199,"인천","직할","갈산도당#1 T/L","도당S/S  신규수용공사"," GIS x 3CCT 설치","2025-05-29 09:00","2025-05-30 18:00","취소","취소","연속"]
[200,"인천","직할","갈산부흥#3 T/L","갈산S/S 갈산부흥#3T/L GIS 보통점검","갈산S/S 갈산부흥#3T/L GIS 보통점검","2025-05-09 09:30","2025-05-09 18:00","취소","취소","연속"]
[201,"인천","직할","계양불로#1 T/L","계양S/S  계양-불로#1T/L(637) GIS 정밀점검","계양S/S  계양-불로#1T/L(637) GIS 정밀점검","2025-05-19 09:00","2025-05-21 13:00","취소","취소","연속"]
[202,"인천","직할","임학계양#1 T/L","'24-'25년 가공송전 협력회사 공사","수평 추락방지시설 및 고정형폴리머 점퍼지지애자 설치","2025-05-24 07:30","2025-05-25 18:00","취소","취소","매일"]
[203,"인천","직할","계양북인천 T/L"," 계양-원창T/L 지장송전선로 이설공사","철탑 이설","2025-05-10 09:00","2025-05-15 18:00","2025-05-10 09:00","2025-05-15 18:00","연속"]
[204,"인천","직할","계양원창 T/L"," 계양-원창T/L 지장송전선로 이설공사","철탑 이설","2025-05-04 09:00","2025-05-09 18:00","2025-05-04 09:00","2025-05-09 18:00","연속"]
[205,"인천","직할","임학계양#2 T/L","'24-'25년 가공송전 협력회사 공사","수평 추락방지시설 및 고정형폴리머점퍼지지애자 설치","2025-05-26 07:30","2025-05-27 18:00","취소","취소","매일"]
[206,"인천","직할","계양불로#2 T/L","계양S/S  계양-불로#2T/L(647) GIS 정밀점검","계양S/S  계양-불로#2T/L(647) GIS 정밀점검","2025-05-21 13:00","2025-05-23 18:00","취소","취소","연속"]
[207,"인천","직할","도당S/S #60 BUS","도당S/S  신규수용공사"," GIS x 3CCT 설치","2025-05-26 09:00","2025-05-30 18:00","취소","취소","연속"]
[208,"인천","직할","신부평도당#2 T/L"," 갈산도당#2T/L 인출정비공사","가. 공사구간 : (신설) 갈산S/S~J/B#1, (철거) 신부평S/S~J/B#1 나. 선종 및 회선길이 : XLPE2000, 0.4km","2025-05-20 09:00","2025-06-13 18:00","2025-05-20 09:00","2025-06-18 18:00","연속"]
[209,"인천","직할","북인천원창 T/L","무부하가압용(북인천S/S #4M.Tr 1차 GIS 정밀점검)","북인천S/S #4M.Tr 1차 GIS 정밀점검분 무부하가압용 - 무부하가압 시행 후 북인천-원창T/L GIS 조작시험 진행","2025-05-16 09:00","2025-05-16 18:00","취소","취소","연속"]
[210,"인천","직할","북인천S/S #65 BUS","무부하가압용(북인천S/S #4M.Tr 1차 GIS)","무부하가압용(북인천S/S #4M.Tr 1차 GIS) (09:00~11:00)","2025-05-16 09:00","2025-05-16 11:00","취소","취소","연속"]
[211,"경기북부","고양","양주고양#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","병가구간 휴전","2025-05-16 07:00","2025-05-16 17:00","2025-05-16 07:00","2025-05-16 17:00","연속"]
[212,"경기북부","고양","양주금촌#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","불량애자교체","2025-05-15 07:00","2025-05-16 17:00","2025-05-15 07:00","2025-05-16 17:00","연속"]
[213,"경기북부","고양","능곡상암#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-05-09 09:00","2025-05-09 18:00","2025-05-09 09:00","2025-05-09 18:00","연속"]
[214,"경기북부","고양","백학남면#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 백학남면T/L 피뢰기 설치","2025-05-12 10:00","2025-05-16 18:00","2025-05-12 10:00","2025-05-16 18:00","연속"]
[215,"경기북부","고양","신덕은금촌#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치(수평) 설치","2025-05-09 07:00","2025-05-14 17:00","2025-05-09 07:00","2025-05-14 17:00","연속"]
[216,"경기북부","고양","신파주원흥#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치설치","2025-05-26 07:00","2025-05-30 17:00","2025-05-26 07:00","2025-05-30 17:00","연속"]
[217,"경기북부","구리","가평춘천HP T/L"," 운천-철원 등 2개T/L 용량증대 전력선 교체공사","증용량 전선 교체(ACSR → ASCC/TW) 70호~135.99(가평S/S)","2025-05-12 06:00","2025-06-27 18:00","2025-05-12 06:00","2025-06-27 18:00","연속"]
[218,"경기북부","구리","구리신내#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 하자점검","2025-05-20 09:00","2025-05-20 18:00","2025-05-20 09:00","2025-05-20 18:00","연속"]
[219,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사","가선작업(OPGW 이설 포함)","2025-05-22 09:00","2025-05-30 18:00","2025-05-22 09:00","2025-05-30 18:00","연속"]
[220,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사","- 철탑 조립 및 항공도장","2025-05-07 09:00","2025-05-15 18:00","2025-05-07 09:00","2025-05-15 18:00","연속"]
[221,"경기북부","구리","덕소진건#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[222,"경기북부","구리","덕소마석#2 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","C/T 금구류 교체","2025-05-15 09:00","2025-05-15 18:00","2025-05-15 09:00","2025-05-15 18:00","연속"]
[223,"경기북부","구리","미금S/S SEC CB 66670","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-05-21 14:00","2025-05-21 18:00","2025-05-21 14:00","2025-05-21 18:00","연속"]
[224,"경기북부","구리","미금S/S SEC CB 61620","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-05-21 09:00","2025-05-21 14:00","2025-05-21 09:00","2025-05-21 14:00","연속"]
[225,"경기북부","구리","미금S/S CB 6300","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-05-19 14:00","2025-05-19 18:00","2025-05-19 14:00","2025-05-19 18:00","연속"]
[226,"경기북부","구리","미금S/S CB 6200","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-05-19 09:00","2025-05-19 14:00","2025-05-19 09:00","2025-05-19 14:00","연속"]
[227,"경기북부","구리","동서울서종#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사","가선작업(OPGW 이설 포함)","2025-05-22 09:00","2025-05-30 18:00","2025-05-22 09:00","2025-05-30 18:00","연속"]
[228,"경기북부","구리","동서울서종#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사","- 철탑 조립 및 항공도장","2025-05-07 09:00","2025-05-15 18:00","2025-05-07 09:00","2025-05-15 18:00","연속"]
[229,"경기북부","구리","신포천S/S SEC CB 65660","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-05-12 14:00","2025-05-12 18:00","2025-05-12 14:00","2025-05-12 18:00","연속"]
[230,"경기북부","구리","신포천S/S SEC CB 60610","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-05-12 09:00","2025-05-12 14:00","2025-05-12 09:00","2025-05-12 14:00","연속"]
[231,"경기북부","구리","신포천전곡#2 T/L","2025년 가공송전 순시점검 위탁공사","정밀점검 작업구간 :  신포천-전곡#2 T/L No.1~46 병가선로 -  신포천-덕계#1 T/L No.1~7호 (5월7일) -  운천-전곡#1 T/L No.71~75호 (5월14일)","2025-05-19 08:00","2025-05-26 18:00","2025-05-19 08:00","2025-05-26 18:00","연속"]
[232,"경기북부","구리","신포천S/S CB 6100","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-05-13 09:00","2025-05-13 14:00","2025-05-13 09:00","2025-05-13 14:00","연속"]
[233,"경기북부","구리","신포천S/S CB 6200","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-05-13 14:00","2025-05-13 18:00","2025-05-13 14:00","2025-05-13 18:00","연속"]
[234,"경기북부","구리","운천전곡#1 T/L","2025년 가공송전 순시점검 위탁공사","정밀점검 작업구간 :  운천-전곡#1 T/L No.1~76호 병가선로 -  신포천-전곡#2 T/L No.1~7호 (5월14일)","2025-05-07 08:00","2025-05-19 18:00","2025-05-07 08:00","2025-05-19 18:00","연속"]
[235,"경기북부","구리","서홍천청평PP T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","345kV 신가평-포천LNG#1T/L(상),  서홍천-청평양수T/L(하) 4회선 병가구간(No.26~41)철탑추락방지시설 설치","2025-05-19 07:00","2025-05-23 18:00","2025-05-19 07:00","2025-05-23 18:00","연속"]
[236,"경기북부","직할","금오상계#2 T/L","직할 170kV GIS 점검공사","170kV GIS 정밀점검(시험가압용 선로휴전)","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[237,"경기북부","직할","신의정부금오#1 T/L","직할 170kV GIS 점검공사","170kV GIS 정밀점검","2025-05-14 09:00","2025-05-15 18:00","2025-05-14 09:00","2025-05-15 18:00","연속"]
[238,"경기북부","직할","신의정부금오#2 T/L","직할 170kV GIS 점검공사","170kV GIS 정밀점검","2025-05-19 09:00","2025-05-22 18:00","2025-05-19 09:00","2025-05-22 18:00","연속"]
[239,"경기북부","직할","금오상계#1 T/L","직할 170kV GIS 점검공사","170kV GIS 정밀점검(시험가압용 선로휴전)","2025-05-15 09:00","2025-05-15 18:00","2025-05-15 09:00","2025-05-15 18:00","연속"]
[240,"경기북부","직할","신포천덕계#1 T/L","345kV 동두천CC-양주T/L 건설공사","345kV 동두천CC-양주T/L 건설공사","2025-05-15 09:00","2025-06-09 18:00","2025-05-15 09:00","2025-06-09 18:00","연속"]
[241,"경기북부","직할","신포천동두천#1 T/L","345kV 동두천CC-양주T/L 건설공사","345kV 동두천CC-양주T/L 건설공사","2025-05-29 09:00","2025-06-03 18:00","2025-05-29 09:00","2025-06-03 18:00","연속"]
[242,"경기북부","직할","옥정동두천#2 T/L","345kV 동두천CC-양주T/L 건설공사","345kV 동두천CC-양주T/L 건설공사","2025-05-15 09:00","2025-06-09 18:00","2025-05-15 09:00","2025-06-09 18:00","연속"]
[243,"경기북부","직할","신포천동두천#2 T/L","345kV 동두천CC-양주T/L 건설공사","345kV 동두천CC-양주T/L 건설공사","2025-05-12 09:00","2025-05-28 18:00","2025-05-12 09:00","2025-05-28 18:00","연속"]
[244,"경기북부","직할","신의정부용현#2 T/L","(주)영인 보호계전기 성능개선 시행","유사 불량사례 발생 가능성 사전 제거를 위한 성능개선","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[245,"경기북부","직할","신의정부S/S CB 6100","직할 170kV GIS 점검공사","170kV GIS 보통점검","2025-05-29 09:00","2025-05-29 18:00","2025-05-29 09:00","2025-05-29 18:00","연속"]
[246,"경기북부","직할","신의정부용현#1 T/L","(주)영인 보호계전기 성능개선 시행","유사 불량사례 발생 가능성 사전 제거를 위한 성능개선","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[247,"경기북부","직할","양주쌍문#1 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","피뢰기 점검","2025-05-23 09:00","2025-05-23 13:00","2025-05-23 09:00","2025-05-23 13:00","연속"]
[248,"경기북부","직할","양주녹양#2 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","피뢰기 점검","2025-05-22 13:00","2025-05-22 18:00","2025-05-22 13:00","2025-05-22 18:00","연속"]
[249,"경기북부","직할","양주녹양#1 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","피뢰기 점검","2025-05-22 09:00","2025-05-22 13:00","2025-05-22 09:00","2025-05-22 13:00","연속"]
[250,"경기북부","직할","양주쌍문#2 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","피뢰기 점검","2025-05-23 13:00","2025-05-23 18:00","2025-05-23 13:00","2025-05-23 18:00","연속"]
[251,"경기","군포","사강남양#1 T/L"," 남양-사강T/L 지중화공사_가공 임시이설공사"," 남양-사강T/L 지중화공사_가공 임시이설공사","2025-05-07 07:00","2025-05-12 18:00","2025-05-01 07:00","2025-05-05 18:00","연속"]
[252,"경기","군포","화성남양#2 T/L","[무부하가압용]남양S/S #6100TIE GIS 정밀점검","남양S/S #6100TIE GIS 정밀점검 관련 무부하가압용 송전선로","2025-05-30 14:00","2025-05-30 18:00","취소","취소","연속"]
[253,"경기","군포","사강남양#2 T/L"," 남양-사강T/L 지중화공사_가공 임시이설공사"," 남양-사강T/L 지중화공사_가공 임시이설공사","2025-05-13 07:00","2025-05-17 18:00","2025-05-06 07:00","2025-05-08 18:00","연속"]
[254,"경기","군포","목내안산에너지 T/L","목내S/S 안산에너지T/L GIS 조작시험","목내S/S 안산에너지T/L GIS 조작시험 시행","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[255,"경기","군포","서서울#2봉담#2 T/L","25~26년 군포전력지사 지중송전 협력회사 공사","피뢰기,CT점검","2025-05-31 13:00","2025-05-31 17:00","2025-05-31 13:00","2025-05-31 17:00","연속"]
[256,"경기","군포","서서울#2봉담#1 T/L","25~26년 군포전력지사 지중송전 협력회사 공사","피뢰기,CT점검","2025-05-31 08:00","2025-05-31 13:00","2025-05-31 08:00","2025-05-31 13:00","연속"]
[257,"경기","군포","서안양소래 T/L","25~26년 군포전력지사 지중송전 협력회사 공사"," 서안양-소래T/L 대한제 EBG 가스채취밸브 설치","2025-05-10 08:00","2025-05-11 17:00","2025-05-10 08:00","2025-05-11 17:00","연속"]
[258,"경기","군포","서서울#2서안양 T/L","25~26년 군포전력지사 지중송전 협력회사 공사"," 서서울2-서안양T/L 대한제 EBG 가스채취밸브 설치","2025-05-17 08:00","2025-05-18 17:00","2025-05-17 08:00","2025-05-18 17:00","연속"]
[259,"경기","군포","목내성곡#2 T/L","[무부하가압용]성곡S/S #4M.Tr 1차 GIS 정밀점검","성곡S/S #4M.Tr 1차 GIS 정밀점검 관련 무부하가압용 송전선로","2025-05-23 14:00","2025-05-23 18:00","2025-05-23 14:00","2025-05-23 18:00","연속"]
[260,"경기","군포","성포안산#1 T/L","25~26년 군포전력지사 지중송전 협력회사 공사"," 성포-안산#1T/L 대한제 EBG 가스채취밸브 설치","2025-05-26 08:00","2025-05-30 17:00","2025-05-19 08:00","2025-05-23 17:00","연속"]
[261,"경기","군포","시화동시화#1 T/L","시화S/S 시화-동시화#1T/L GIS 보통점검","시화S/S  시화-동시화#1T/L GIS 보통점검 시행","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[262,"경기","군포","시화동시화#2 T/L","시화S/S 시화-동시화#2T/L GIS 보통점검","시화S/S  시화-동시화#2T/L GIS 보통점검 시행","2025-05-23 09:00","2025-05-23 18:00","2025-05-23 09:00","2025-05-23 18:00","연속"]
[263,"경기","군포","안양평촌#1 T/L","안양S/S 안양-평촌#1T/L GIS 보통,유사고장 점검","안양S/S  안양-평촌#1T/L GIS 보통점검, 유사고장 점검(효성제 발청) 시행","2025-05-27 09:00","2025-05-27 18:00","취소","취소","연속"]
[264,"경기","군포","안양평촌#2 T/L","안양S/S 안양-평촌#2T/L GIS 보통,유사고장 점검","안양S/S  안양-평촌#2T/L GIS 보통점검, 유사고장 점검(효성제 발청) 시행","2025-05-26 09:00","2025-05-26 18:00","취소","취소","연속"]
[265,"경기","군포","서서울#2일동#1 T/L","24-25 군포전력지사 가공송전 협력회사 공사"," 서서울-2일동#1 T/L No.4~5호 구간 전력선 꼬임에 따른 긴급 복구작업 시행","2025-05-07 07:00","2025-05-07 17:00","2025-05-07 07:00","2025-05-07 17:00","연속"]
[266,"경기","군포","수촌조암#1 T/L","조암S/S 수촌-조암#1T/L GIS 보통점검","조암S/S  수촌-조암#1T/L GIS 보통점검 시행","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[267,"경기","군포","수촌조암#2 T/L","조암S/S 수촌-조암#2T/L GIS 보통점검","조암S/S  수촌-조암#2T/L GIS 보통점검 시행","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[268,"경기","군포","조암구문천#2 T/L","조암S/S 조암-구문천#2T/L GIS 보통점검","조암S/S 조암-구문천#2T/L GIS 보통점검, 유압계통 육안점검 시행","2025-05-15 09:00","2025-05-15 18:00","2025-05-15 09:00","2025-05-15 18:00","연속"]
[269,"경기","군포","시화중시화 T/L","25~26년 군포전력지사 지중송전 협력회사 공사"," 시화-중시화T/L 대한제 EBG 가스채취밸브 설치","2025-05-15 08:00","2025-05-16 17:00","2025-05-15 08:00","2025-05-16 17:00","연속"]
[270,"경기","군포","성곡중시화 T/L","25~26년 군포전력지사 지중송전 협력회사 공사"," 성곡-중시화T/L 대한제 EBG 가스채취밸브 설치","2025-05-12 08:00","2025-05-13 17:00","취소","취소","연속"]
[271,"경기","동부","곤지암S/S SEC CB 65660","24-25년 동부 변전협력회사 총액공사","곤지암S/S 61-66 모선보호반 대체작업","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[272,"경기","동부","곤지암S/S SEC CB 66670","24-25년 동부 변전협력회사 총액공사","곤지암S/S 61-66 모선보호반 대체작업","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[273,"경기","동부","곤지암율현#1 T/L","24-25년 동부전력지사 송전협력회사 공사","수평추락방지장치 설치(1~25,29~63호. 곤지암-이천, 오천-율현과 병가)","2025-05-01 08:00","2025-05-18 18:00","취소","취소","연속"]
[274,"경기","동부","곤지암이천#1 T/L","24-25년 동부전력지사 송전협력회사 공사","수평추락방지장치 설치(1~25호. 곤지암-율현과 병가)","2025-05-01 08:00","2025-05-12 18:00","취소","취소","연속"]
[275,"경기","동부","곤지암S/S SEC CB 60610","24-25년 동부 변전협력회사 총액공사","곤지암S/S 61-66 모선보호반 대체작업","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[276,"경기","동부","곤지암S/S CB 6200","24-25년 동부 변전협력회사 총액공사","곤지암S/S 61-66 모선보호반 대체작업","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[277,"경기","동부","곤지암S/S SEC CB 61620","24-25년 동부 변전협력회사 총액공사","곤지암S/S 61-66 모선보호반 대체작업","2025-05-12 09:00","2025-05-16 18:00","취소","취소","연속"]
[278,"경기","동부","동판교야탑 T/L","2025년 동부전력 170kV GIS 정밀점검","야탑:동판교-야탑T/L(정밀) *장비이동(야탑 → 동백)","2025-05-26 09:00","2025-05-28 18:00","취소","취소","연속"]
[279,"경기","동부","오천율현#2 T/L","24-25년 동부전력지사 송전협력회사 공사","수평추락방지장치 설치(53~63호. 곤지암-율현과 병가)","2025-05-14 08:00","2025-05-16 18:00","취소","취소","연속"]
[280,"경기","동부","이천가남#1 T/L","이천S/S 하이닉스#1T/L 용량증대공사","하이닉스#1T/L 용량증대(C/H증설) 안전이격확보","2025-05-11 09:00","2025-05-11 18:00","2025-05-11 09:00","2025-05-11 18:00","연속"]
[281,"경기","동부","이천가남#1 T/L","이천S/S 하이닉스#1T/L 용량증대공사","하이닉스#1T/L 용량증대(C/H증설) 안전이격확보","2025-05-03 09:00","2025-05-04 18:00","2025-05-03 09:00","2025-05-04 18:00","연속"]
[282,"경기","동부","서판교중원#1 T/L","2025년 동부전력 170kV GIS 정밀점검","중원:서판교-중원#1T/L(정밀)","2025-05-12 09:00","2025-05-14 18:00","2025-05-12 09:00","2025-05-14 18:00","연속"]
[283,"경기","동부","중원야탑 T/L","2025년 동부전력 170kV GIS 정밀점검","중원:중모T/L(정밀,전용), 야탑:중원-야탑T/L(정밀)","2025-05-18 09:00","2025-05-24 18:00","취소","취소","연속"]
[284,"경기","성남","북동탄린데코리아 T/L CB","2025년 성남전력 변전협력회사 총액공사","- gis 하자점검","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[285,"경기","성남","신성남서판교#3 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","- gis 보통점검 gis 부품교체","2025-05-26 09:00","2025-05-27 18:00","2025-05-26 09:00","2025-05-27 18:00","연속"]
[286,"경기","성남","신성남정자#3 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","- gis 보통점검 gis 부품교체","2025-05-28 09:00","2025-05-29 18:00","2025-05-28 09:00","2025-05-29 18:00","연속"]
[287,"경기","성남","신성남S/S CB 6300","25년 성남전력 효성제 부품발청 교체공사","- 부품교체","2025-05-12 14:00","2025-05-12 18:00","2025-05-12 14:00","2025-05-12 18:00","연속"]
[288,"경기","성남","신성남과천#2 T/L","25년 성남전력 효성제 부품발청 교체공사","- 부품교체","2025-05-15 09:00","2025-05-15 18:00","2025-05-15 09:00","2025-05-15 18:00","연속"]
[289,"경기","성남","신성남S/S CB 6100","25년 성남전력 효성제 부품발청 교체공사","- 부품교체","2025-05-12 09:00","2025-05-12 14:00","2025-05-12 09:00","2025-05-12 14:00","연속"]
[290,"경기","성남","신성남S/S SEC CB 60610","25년 성남전력 효성제 부품발청 교체공사","- 부품교체","2025-05-14 09:00","2025-05-14 14:00","2025-05-14 09:00","2025-05-14 14:00","연속"]
[291,"경기","성남","신성남S/S SEC CB 65660","25년 성남전력 효성제 부품발청 교체공사","- 부품교체","2025-05-14 14:00","2025-05-14 18:00","2025-05-14 14:00","2025-05-14 18:00","연속"]
[292,"경기","성남","신수원S/S #65 BUS","신수원S/S  동반#1T/L GIS 교체공사","동반#1T/L 무부하가압","2025-05-12 13:00","2025-05-13 13:00","2025-05-12 13:00","2025-05-13 13:00","연속"]
[293,"경기","성남","신수원S/S #60 BUS","신수원S/S  동반#1T/L GIS 교체공사","동반#1T/L 무부하가압","2025-05-12 10:00","2025-05-12 13:00","2025-05-12 10:00","2025-05-12 13:00","연속"]
[294,"경기","성남","신수원S/S #61 BUS","화성1공장  인입선로 케이블 교체공사","신수원S/S  신수원-삼반#2T/L 케이블 교체 후 무부하가압","2025-05-08 15:00","2025-05-09 15:00","2025-05-08 15:00","2025-05-09 15:00","연속"]
[295,"경기","성남","신용인S/S #65 BUS","2025년 성남전력 170kV GIS 정밀점검공사","- gis 무부하가압용","2025-05-23 09:00","2025-05-23 18:00","2025-05-23 09:00","2025-05-23 18:00","연속"]
[296,"경기","성남","신용인S/S #60 BUS","2025년 성남전력 170kV GIS 정밀점검공사","- gis 무부하가압용","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[297,"경기","성남","신용인S/S SEC CB 60610","2025년 성남전력 170kV GIS 정밀점검공사","- gis 정밀점검","2025-05-15 09:00","2025-05-16 18:00","2025-05-15 09:00","2025-05-16 18:00","연속"]
[298,"경기","성남","신용인S/S SEC CB 66670","2025년 성남전력 변전협력회사 총액공사","- gis 보통점검","2025-05-13 14:00","2025-05-13 18:00","2025-05-13 14:00","2025-05-13 18:00","연속"]
[299,"경기","성남","신용인S/S CB 6300","2025년 성남전력 변전협력회사 총액공사","- gis 보통점검","2025-05-13 09:00","2025-05-13 14:00","2025-05-13 09:00","2025-05-13 14:00","연속"]
[300,"경기","성남","신용인기흥#2 T/L","2025년 성남전력 변전협력회사 총액공사","- gis보통, la 보통","2025-05-09 14:00","2025-05-09 18:00","취소","취소","연속"]
[301,"경기","성남","신용인기흥#1 T/L","2025년 성남전력 변전협력회사 총액공사","- gis보통, la 보통","2025-05-09 09:00","2025-05-09 14:00","취소","취소","연속"]
[302,"경기","성남","신용인S/S SEC CB 65660","2025년 성남전력 170kV GIS 정밀점검공사","- gis 정밀점검","2025-05-22 09:00","2025-05-23 18:00","2025-05-22 09:00","2025-05-23 18:00","연속"]
[303,"경기","성남","모현용인#2 T/L","용인 은화삼지구 지장송전선로 지중화공사(요청자시행)","○ 철탑 : 6기 설치 및 11기 철거(요청자시행) - 신설 : 임시No.40,41,42,43,44,44-1 (6기) - 철거 : No.40,41,42,43,44 / 임시No.40,41,42,43,44,44-1 ○ 전력선 : ACSR410mm^2*2B*2C*1조(OPGW 100mm^2*1조 전자제어부 별도 시행) ○ 기타 부대공사 : 이도조정추가시공 기설No","2025-05-27 08:00","2025-06-10 18:00","2025-05-27 08:00","2025-06-10 18:00","연속"]
[304,"경기","성남","모현용인#1 T/L","용인 은화삼지구 지장송전선로 지중화공사(요청자시행)","○ 철탑 : 6기 설치 및 11기 철거(요청자시행) - 신설 : 임시No.40,41,42,43,44,44-1 (6기) - 철거 : No.40,41,42,43,44 / 임시No.40,41,42,43,44,44-1 ○ 전력선 : ACSR410mm^2*2B*2C*1조(OPGW 100mm^2*1조 전자제어부 별도 시행) ○ 기타 부대공사 : 이도조정추가시공 기설No","2025-05-19 08:00","2025-05-26 18:00","2025-05-19 08:00","2025-05-26 18:00","연속"]
[305,"경기","직할","동안양안양CC#1 T/L","동안양S/S 지중송전선로 인출정비 공사"," 동안양-안열T/L 인출정비 - 선종/길이 : XLPE 2000 / 0.404km","2025-05-12 09:00","2025-06-13 18:00","2025-05-12 09:00","2025-06-13 18:00","연속"]
[306,"경기","직할","봉담남수원#1 T/L","25~26년 군포전력지사 지중송전 협력회사 공사","피뢰기,CT점검","2025-05-24 08:00","2025-05-24 13:00","2025-05-24 08:00","2025-05-24 13:00","연속"]
[307,"경기","직할","봉담남수원#2 T/L","25~26년 군포전력지사 지중송전 협력회사 공사","피뢰기,CT점검","2025-05-24 13:00","2025-05-24 17:00","2025-05-24 13:00","2025-05-24 17:00","연속"]
[308,"경기","직할","율전의왕#2 T/L"," 의왕S/S 디지털화공사","전력설비 감시·제어·계측 디지털화","2025-05-23 09:00","2025-05-23 18:00","2025-05-23 09:00","2025-05-23 18:00","연속"]
[309,"경기","직할","남군포의왕#2 T/L"," 의왕S/S 디지털화공사","전력설비 감시·제어·계측 디지털화","2025-05-28 09:00","2025-05-28 18:00","2025-05-28 09:00","2025-05-28 18:00","연속"]
[310,"경기","직할","남군포의왕#1 T/L"," 의왕S/S 디지털화공사","전력설비 감시·제어·계측 디지털화","2025-05-27 09:00","2025-05-27 18:00","2025-05-27 09:00","2025-05-27 18:00","연속"]
[311,"경기","직할","율전의왕#1 T/L"," 의왕S/S 디지털화공사","전력설비 감시·제어·계측 디지털화","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[312,"경기","직할","화성장덕#1 T/L","2024-25년 경기본부 직할 변전협력회사 공사","화성: 화성-장덕#2T/L GIS 조작시험","2025-05-28 09:00","2025-05-28 14:00","2025-05-28 09:00","2025-05-28 14:00","연속"]
[313,"경기","직할","화성발안#1 T/L"," 화성-장덕T/L OPGW 증설공사"," 화성-장덕T/L OPGW 증설공사 - OPGW 증설교체(OP-S-L24 → L48) 7.797km(해당구간 2km) - 광코어 접속, 최종시험 및 기타 부대공사 1식","2025-05-24 07:00","2025-05-25 18:00","2025-05-24 07:00","2025-05-25 18:00","연속"]
[314,"경기","직할","화성S/S SEC CB 66670","2024-25년 경기본부 직할 변전협력회사 공사","화성: 66-67SECTION GIS 보통점검","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[315,"경기","직할","화성S/S SEC CB 61620","2024-25년 경기본부 직할 변전협력회사 공사","화성: 61-62 SECTION GIS 보통점검","2025-05-07 09:00","2025-05-07 18:00","2025-05-07 09:00","2025-05-07 18:00","연속"]
[316,"경기","직할","화성장덕#2 T/L"," 화성-장덕T/L OPGW 증설공사"," 화성-장덕T/L OPGW 증설공사 - OPGW 증설교체(OP-S-L24 → L48) 7.797km(해당구간 2km) - 광코어 접속, 최종시험 및 기타 부대공사 1식","2025-05-24 07:00","2025-05-25 18:00","2025-05-24 07:00","2025-05-25 18:00","연속"]
[317,"경기","평택","고덕#2S/S CB 6A71","PNC테크 성능개선(고덕#2-삼성P4 #2T/L 6A71 GIS)","PNC테크 성능개선(고덕#2-삼성P4 #2T/L 6A71 GIS)","2025-05-19 13:10","2025-05-19 13:30","2025-05-19 13:10","2025-05-19 13:30","연속"]
[318,"경기","평택","고덕#2S/S CB 6972","PNC테크 성능개선(고덕#2-삼성P4 #1T/L 6972 GIS)","PNC테크 성능개선(고덕#2-삼성P4 #1T/L 6972 GIS)","2025-05-19 11:20","2025-05-19 11:40","2025-05-19 11:20","2025-05-19 11:40","연속"]
[319,"경기","평택","고덕#2S/S CB 6900","PNC테크 성능개선(69Bay TIE GIS 6900)","PNC테크 성능개선(69Bay TIE GIS 6900)","2025-05-19 11:00","2025-05-19 11:20","2025-05-19 11:00","2025-05-19 11:20","연속"]
[320,"경기","평택","고덕#2S/S CB 6971","PNC테크 성능개선(고덕#2-평택 #2T/L 6971 GIS)","PNC테크 성능개선(고덕#2-평택 #2T/L 6971 GIS)","2025-05-19 10:30","2025-05-19 11:00","2025-05-19 10:30","2025-05-19 11:00","연속"]
[321,"경기","평택","고덕#2S/S CB 6872","PNC테크 성능개선(고덕#2-동평택 #2T/L 6872 GIS)","PNC테크 성능개선(고덕#2-동평택 #2T/L 6872 GIS)","2025-05-19 10:10","2025-05-19 10:30","2025-05-19 10:10","2025-05-19 10:30","연속"]
[322,"경기","평택","고덕#2S/S CB 6800","PNC테크 성능개선(68Bay TIE 6800 GIS)","PNC테크 성능개선(68Bay TIE 6800 GIS)","2025-05-19 09:50","2025-05-19 10:10","2025-05-19 09:50","2025-05-19 10:10","연속"]
[323,"경기","평택","고덕#2S/S CB 6871","PNC테크 성능개선(#3M.Tr 2차 6871 GIS)","PNC테크 성능개선(#3M.Tr 2차 6871 GIS)","2025-05-19 09:30","2025-05-19 09:50","2025-05-19 09:30","2025-05-19 09:50","연속"]
[324,"경기","평택","고덕#2S/S CB 6672","PNC테크 성능개선(고덕#2-삼성P3 #1T/L 6672 GIS)","PNC테크 성능개선(고덕#2-삼성P3 #1T/L 6672 GIS)","2025-05-12 13:30","2025-05-12 14:00","2025-05-12 13:30","2025-05-12 14:00","연속"]
[325,"경기","평택","고덕#2S/S CB 6600","PNC테크 성능개선66Bay TIE GIS 6600)","PNC테크 성능개선66Bay TIE GIS 6600)","2025-05-12 13:10","2025-05-12 13:30","2025-05-12 13:10","2025-05-12 13:30","연속"]
[326,"경기","평택","고덕#2S/S CB 6671","PNC테크 성능개선(#1M.Tr 2차 6671 GIS)","PNC테크 성능개선(#1M.Tr 2차 6671 GIS)","2025-05-12 11:20","2025-05-12 11:40","2025-05-12 11:20","2025-05-12 11:40","연속"]
[327,"경기","평택","고덕#2S/S CB 6572","PNC테크 성능개선(고덕#2-평택 #1T/L GIS 6572 GIS)","PNC테크 성능개선(고덕#2-평택 #1T/L GIS 6572 GIS)","2025-05-12 11:00","2025-05-12 11:20","2025-05-12 11:00","2025-05-12 11:20","연속"]
[328,"경기","평택","고덕#2S/S CB 6500","PNC테크 성능개선(고덕#2-삼성P3 #2T/L 6500 GIS)","PNC테크 성능개선(고덕#2-삼성P3 #2T/L 6500 GIS)","2025-05-12 10:30","2025-05-12 11:00","2025-05-12 10:30","2025-05-12 11:00","연속"]
[329,"경기","평택","고덕#2S/S CB 6571","PNC테크 성능개선(고덕#2-삼성P3 #2T/L 6571 GIS)","PNC테크 성능개선(고덕#2-삼성P3 #2T/L 6571 GIS)","2025-05-12 10:10","2025-05-12 10:30","2025-05-12 10:10","2025-05-12 10:30","연속"]
[330,"경기","평택","고덕#2S/S CB 6A72","고덕#2S/S 345kV #4M.Tr 2차 GIS 설치 (6A72)","#4M.Tr 2차 GIS 설치(6A72)","2025-05-26 09:00","2025-06-13 18:00","2025-05-26 09:00","2025-06-13 18:00","연속"]
[331,"경기","평택","고덕#2S/S CB 6A00","PNC테크 성능개선(6ABay TIE GIS 6A00)","PNC테크 성능개선(6ABay TIE GIS 6A00)","2025-05-19 13:30","2025-05-19 14:00","2025-05-19 13:30","2025-05-19 14:00","연속"]
[332,"경기","평택","고덕S/S CB 6200","2025년 평택전력 변전협력회사 총액공사(고덕S/S 6200)","고덕S/S  #61-#66 BUS TIE GIS(6200) GIS 보통점검","2025-05-08 09:00","2025-05-08 18:00","취소","취소","연속"]
[333,"경기","평택","고덕송탄#2 T/L","2025년 평택전력 변전협력회사 총액공사(송탄S/S 고덕-송탄#2)","송탄S/S  고덕-송탄#2T/L GIS 보통점검","2025-05-09 10:00","2025-05-09 18:00","2025-05-09 10:00","2025-05-09 18:00","연속"]
[334,"경기","평택","고덕송탄#1 T/L","2025년 평택전력 변전협력회사 총액공사(송탄S/S 고덕-송탄#1)","송탄S/S  고덕-송탄#1T/L GIS 보통점검","2025-05-07 10:00","2025-05-07 18:00","2025-05-07 10:00","2025-05-07 18:00","연속"]
[335,"경기","평택","만호청북#1 T/L"," 희곡분기 지중T/L 건설공사","1. 공사구간 -  희곡∼포승 지중T/L M/H#1 ,희곡∼청북 지중T/L M/H#1 -  희곡S/S ∼ 만호S/S 2. 선종/회선길이 -  XLPE 2,000㎟, 2C×4.33㎞[희곡 S/S ~ (포승/청북) 지중T/L M/H#1] -  XLPE 2,000㎟, 2C×3.95㎞[희곡 S/S ~ 만호 S/S]","2025-05-16 09:00","2025-06-30 18:00","2025-05-16 09:00","2025-06-30 18:00","연속"]
[336,"경기","평택","포승평택TP#2 T/L"," 북현덕분기 2차 전력구공사","수직구 2개소, 개착식 전력구157m, semishield 202m 포승변전소 구내 전력구공사 및 LA, CVT 이설 공사","2025-05-01 09:00","2025-05-07 22:00","2025-05-01 09:00","2025-05-07 22:00","연속"]
[337,"경기","평택","포승평택TP#1 T/L"," 북현덕분기 2차 전력구공사","수직구 2개소, 개착식 전력구157m, semishield 202m 포승변전소 구내 전력구공사 및 LA, CVT 이설 공사","2025-05-08 09:00","2025-05-15 22:00","2025-05-08 09:00","2025-05-15 22:00","연속"]
[338,"경기","평택","고덕#2S/S #66 BUS","고덕#2S/S 345kV #4M.Tr 2차 GIS 설치 (6A72)","#4M.Tr 2차 GIS 설치(6A72)","2025-05-26 09:00","2025-06-13 18:00","2025-05-26 09:00","2025-06-13 18:00","연속"]
[339,"경기","동부","오포모현#2 T/L","  24-25년 성남전력지사 가공송전 협력회사"," 오포-모현T/L 고정형 폴리머 점퍼지지애자 교체공사\n- 대상개소 No.23 ","2025-05-29 08:00","2025-05-31 08:00","취소","취소","연속"]
[340,"경기","직할","서수원율전#1 T/L","옥외변전소 활선구간 중장비 접근 방지시스템 구축 공사","옥외변전소 활선구간 중장비 접근 방지시스템 구축 공사","2025-05-12 08:00","2025-05-13 18:00","2025-05-12 08:00","2025-05-13 18:00","연속"]
[341,"강원","강릉","속초간성#1 T/L","2025년 강릉전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검","2025-05-12 09:00","2025-05-16 18:00","2025-05-12 09:00","2025-05-16 18:00","연속"]
[342,"강원","강릉","속초간성#2 T/L","2025년 강릉전력지사 170kV GIS 정밀점검 공사","170kV GIS 정밀점검","2025-05-19 09:00","2025-05-23 18:00","2025-05-19 09:00","2025-05-23 18:00","연속"]
[343,"강원","강릉","신양양양양#2 T/L","2024~2025년 가공송전협력회사 총액공사","○ 피뢰기 설치공사  신양양-양양#2 T/L (No.58~61)","2025-05-26 07:00","2025-05-26 18:00","2025-05-26 07:00","2025-05-26 18:00","연속"]
[344,"강원","강릉","신양양인제#1 T/L","2024~2025년 가공송전협력회사 총액공사","○ 피뢰기 설치공사  신양양-인제#1 T/L (No.3~6)","2025-05-27 07:00","2025-05-27 18:00","2025-05-27 07:00","2025-05-27 18:00","연속"]
[345,"강원","강릉","신양양인제#2 T/L","2024~2025년 가공송전협력회사 총액공사","○ 피뢰기 설치공사  신양양-인제#2 T/L (No.7~29)","2025-05-28 07:00","2025-05-29 18:00","2025-05-28 07:00","2025-05-29 18:00","매일"]
[346,"강원","강릉","주문진양양#1 T/L","2024~2025년 가공송전협력회사 총액공사","○ 4회선 병가철탑 휴전작업 작업자 안전을 위한 휴전  신양양-양양#2 T/L (No.58~61)","2025-05-26 07:00","2025-05-26 18:00","2025-05-26 07:00","2025-05-26 18:00","연속"]
[347,"강원","강릉","북평영동TP#1 T/L","2025년 강릉전력지사 변전협력회사 공사","송전선로 보호반 대체, 170kV GIS 하자점검","2025-05-26 10:00","2025-05-30 18:00","2025-05-26 10:00","2025-05-30 18:00","연속"]
[348,"강원","강릉","북평영동TP#2 T/L","2025년 강릉전력지사 변전협력회사 공사","송전선로 보호반 대체, 170kV GIS 하자점검","2025-05-19 10:00","2025-05-23 18:00","2025-05-19 10:00","2025-05-23 18:00","연속"]
[349,"강원","강릉","주진평창#2 T/L","2025년 강릉전력지사 변전협력회사 공사","CVT, LA 보통점검","2025-05-08 10:00","2025-05-08 18:00","2025-05-08 10:00","2025-05-08 18:00","연속"]
[350,"강원","동해","태백삼척GP#1 T/L","345kV 삼척GP-한울NP1T/L 산불피해개소 전력선교체 공사","산불피해개소 전력선교체 횡단개소 안전확보","2025-05-15 07:00","2025-05-18 18:00","2025-05-15 07:00","2025-05-18 18:00","매일"]
[351,"강원","동해","울진삼척GP#2 T/L","345kV 삼척GP-한울NP1T/L 산불피해개소 전력선교체 공사","산불피해개소 전력선교체 횡단개소 안전확보","2025-05-15 07:00","2025-05-18 18:00","2025-05-15 07:00","2025-05-18 18:00","매일"]
[352,"강원","동해","울진삼척GP#1 T/L","345kV 삼척GP-한울NP1T/L 산불피해개소 전력선교체 공사","산불피해개소 전력선교체 횡단개소 안전확보","2025-05-15 07:00","2025-05-18 18:00","2025-05-15 07:00","2025-05-18 18:00","매일"]
[353,"강원","동해","울진삼척GP#1 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 울진-삼척GP#1 T/L 수평추락방지장치 및 폴리머 점퍼지지애자 설치","2025-05-26 08:00","2025-06-05 18:00","2025-05-26 08:00","2025-06-05 18:00","매일"]
[354,"강원","원주","남원주원주#1 T/L","24-25년 원주전력지사 변전협력회사 총액공사","차단기 동작시험","2025-05-07 10:00","2025-05-07 18:00","2025-05-07 10:00","2025-05-07 18:00","연속"]
[355,"강원","원주","남원주원주#2 T/L","24-25년 원주전력지사 변전협력회사 총액공사","차단기 동작시험","2025-05-08 10:00","2025-05-08 18:00","2025-05-08 10:00","2025-05-08 18:00","연속"]
[356,"강원","원주","문막지제#2 T/L","24-25년 원주전력지사 변전협력회사 총액공사","GIS 보통점검","2025-05-30 10:00","2025-05-30 18:00","2025-05-30 10:00","2025-05-30 18:00","연속"]
[357,"강원","원주","횡성홍천#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 불량애자교체 및 피뢰기 설치","2025-05-13 08:00","2025-05-13 18:00","2025-05-13 08:00","2025-05-13 18:00","연속"]
[358,"강원","원주","횡성홍천#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","○ 불량애자교체","2025-05-12 08:00","2025-05-12 18:00","2025-05-12 08:00","2025-05-12 18:00","연속"]
[359,"강원","직할","남춘천춘천 T/L","남춘천  남춘천-춘천T/L IED IP 변경","- IED IP변경 - CID 변경에 따른 시험","2025-05-16 14:00","2025-05-16 18:00","2025-05-16 14:00","2025-05-16 18:00","연속"]
[360,"강원","직할","인제양구#2 T/L"," 상제 등 3개 T/L 추락방지장치 설치공사"," 양구 T/L 추락방지장치 설치공사","2025-05-07 09:00","2025-05-21 18:00","2025-05-07 09:00","2025-05-21 18:00","매일"]
[361,"강원","직할","상남인제#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","상남인제#2 T/L com fail, 주보호 정지 경보 구성","2025-05-02 10:00","2025-05-02 18:00","2025-05-02 10:00","2025-05-02 18:00","연속"]
[362,"강원","직할","춘천북춘천#2 T/L"," 춘천-북춘천T/L No.42 지장철탑 이설공사","철탑인클로징 설치 : 1기(No.42) / 철탑철거 : 2기(No.42, 43) / 전력선 교체 : ACSR330㎟×S, 2C-1.147km","2025-05-26 09:00","2025-05-26 18:00","2025-05-26 09:00","2025-05-26 18:00","연속"]
[363,"강원","직할","춘천북춘천#1 T/L"," 춘천-북춘천T/L No.42 지장철탑 이설공사","철탑인클로징 설치 : 1기(No.42) / 철탑철거 : 2기(No.42, 43) / 전력선 교체 : ACSR330㎟×S, 2C-1.147km","2025-05-27 09:00","2025-06-02 18:00","2025-05-27 09:00","2025-06-02 18:00","연속"]
[364,"강원","직할","춘천열병합 CB 6100","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","춘천열병합S/Y  BUS-TIE GIS 정밀점검","2025-05-19 09:00","2025-05-22 18:00","2025-05-19 09:00","2025-05-22 18:00","연속"]
[365,"강원","태백","영월영월에코윈드#2 T/L"," 태백-영월에코윈드 등 2개 T/L 피뢰기 설치공사"," 태백-영월에코윈드 등 2개 T/L 피뢰기 설치공사","2025-05-19 09:00","2025-05-30 18:00","2025-05-19 09:00","2025-05-30 18:00","매일"]
[366,"강원","태백","태백영월에코윈드 T/L"," 태백-영월에코윈드 등 2개 T/L 피뢰기 설치공사"," 태백-영월에코윈드 등 2개 T/L 피뢰기 설치공사","2025-05-07 09:00","2025-05-16 18:00","2025-05-07 09:00","2025-05-16 18:00","매일"]
[367,"충북","직할","진천광혜원#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(39기), 피뢰기 설치(49기), 아킹혼 설치(1기), 조류착지방지장치 설치(1기)","2025-05-22 07:30","2025-05-30 18:00","2025-05-22 07:30","2025-05-30 18:00","매일"]
[368,"충북","직할","서운광혜원 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(39기), 피뢰기 설치(39기), 애자교체(1기), 금구류 정비(1기)","2025-05-22 07:30","2025-05-30 18:00","2025-05-22 07:30","2025-05-30 18:00","매일"]
[369,"충북","직할","신진천S/S #67 BUS","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S  #6Sh.C GIS 정밀점검 후 무부하가압용","2025-05-16 14:00","2025-05-16 15:00","2025-05-16 14:00","2025-05-16 15:00","연속"]
[370,"충북","직할","신진천S/S #67 BUS","25년 상반기 충북본부 직할 GIS 정밀점검 공사","신진천S/S  #5Sh.C GIS 정밀점검 후 무부하가압용","2025-05-14 14:00","2025-05-14 15:00","2025-05-14 14:00","2025-05-14 15:00","연속"]
[371,"충북","직할","신진천문백#2 T/L","25년 상반기 충북본부 직할 GIS 정밀점검 공사"," 신진천-문백#2 T/L GIS 정밀점검","2025-05-07 08:00","2025-05-09 16:00","취소","취소","연속"]
[372,"충북","직할","신진천진천#1 T/L","24-25년 충북직할 변전협력회사공사","신진천-진천 #1T/L 가스누기보수","2025-05-03 09:00","2025-05-06 18:00","2025-05-03 09:00","2025-05-06 18:00","연속"]
[373,"충북","직할","진천S/S #60 BUS","24-25년 충북직할 변전협력회사 공사","진천변전소 신진천-진천#1T/L 가스누기보수","2025-05-03 09:00","2025-05-06 18:00","2025-05-03 09:00","2025-05-06 18:00","연속"]
[374,"충북","청주","국사봉명#1 T/L"," 신청주-문백T/L 건설공사","계통변경(오송-북청주 -> 오송-국사) 본선로 구성을 위한 임시선로 구성","2025-05-26 07:00","2025-05-30 18:00","2025-05-26 07:00","2025-05-30 18:00","연속"]
[375,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(5월)","2025-05-05 07:00","2025-05-06 14:00","2025-05-05 07:00","2025-05-06 14:00","연속"]
[376,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_5월)","2025-05-05 07:00","2025-05-06 14:00","취소","취소","연속"]
[377,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62SEC GIS 대체","2025-05-04 14:00","2025-05-06 18:00","2025-05-04 14:00","2025-05-06 18:00","연속"]
[378,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체 (안전이격확보/무부하가압용)","2025-05-01 14:00","2025-05-06 14:00","취소","취소","연속"]
[379,"충북","청주","남청주S/S #62 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체","2025-05-01 14:00","2025-05-06 14:00","2025-05-01 14:00","2025-05-06 14:00","연속"]
[380,"충북","청주","남청주S/S #67 BUS","2025년 청주전력지사 170kV GIS 정밀점검공사","남청주S/S #1Sh.C GIS 정밀점검 후 무부하 가압","2025-05-30 09:00","2025-05-30 18:00","2025-05-30 09:00","2025-05-30 18:00","연속"]
[381,"충북","청주","남청주S/S SEC CB 67660","2025년 청주전력지사 170kV GIS 정밀점검공사","남청주S/S #1Sh.C GIS 정밀점검 후 무부하 가압","2025-05-30 09:00","2025-05-30 18:00","2025-05-30 09:00","2025-05-30 18:00","연속"]
[382,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_5월)","2025-05-29 14:00","2025-05-30 18:00","취소","취소","연속"]
[383,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(5월)","2025-05-25 14:00","2025-05-30 18:00","취소","취소","연속"]
[384,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(안전이격확보/무부하가압용_5월)","2025-05-20 14:00","2025-05-25 14:00","취소","취소","연속"]
[385,"충북","청주","남청주S/S #62 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(5월)","2025-05-20 14:00","2025-05-25 14:00","취소","취소","연속"]
[386,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_5월)","2025-05-19 14:00","2025-05-20 18:00","취소","취소","연속"]
[387,"충북","청주","남청주S/S SEC CB 62610","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(5월)","2025-05-19 07:00","2025-05-30 18:00","2025-05-19 07:00","2025-05-30 18:00","연속"]
[388,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(5월)","2025-05-19 07:00","2025-05-20 14:00","취소","취소","연속"]
[389,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_5월)","2025-05-15 14:00","2025-05-16 18:00","취소","취소","연속"]
[390,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(5월)","2025-05-11 14:00","2025-05-16 18:00","취소","취소","연속"]
[391,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_5월)","2025-05-10 14:00","2025-05-11 14:00","취소","취소","연속"]
[392,"충북","청주","남청주S/S #67 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(5월)","2025-05-06 14:00","2025-05-11 14:00","2025-05-06 14:00","2025-05-11 14:00","연속"]
[393,"충북","청주","남청주S/S SEC CB 67660","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(5월)","2025-05-05 07:00","2025-05-16 18:00","2025-05-05 07:00","2025-05-16 18:00","연속"]
[394,"충북","청주","서청주사직#2 T/L","2025년 청주전력지사 170kV GIS 정밀점검공사","서청주S/S 서청주-사직T/L GIS 정밀점검","2025-05-26 09:00","2025-05-27 18:00","2025-05-26 09:00","2025-05-27 18:00","연속"]
[395,"충북","청주","신옥천남대전#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-05-21 09:00","2025-05-21 18:00","2025-05-21 09:00","2025-05-21 18:00","연속"]
[396,"충북","청주","신옥천남대전#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-05-20 09:00","2025-05-20 18:00","2025-05-20 09:00","2025-05-20 18:00","연속"]
[397,"충북","청주","신옥천남대전#3 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[398,"충북","청주","신옥천남대전#4 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-05-23 09:00","2025-05-23 18:00","2025-05-23 09:00","2025-05-23 18:00","연속"]
[399,"충북","청주","화동영동 T/L","2024~2025년 송전정비 협력회사 총액공사"," 화동-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 화동-영동T/L 수평 추락방지장치 설치 2. 구간 :  화동-영동T/L 60~110호  영동분기T/L 1~61호","2025-05-19 08:00","2025-05-29 18:00","2025-05-19 08:00","2025-05-29 18:00","매일"]
[400,"충북","청주","옥천영동 T/L","2024~2025년 송전정비 협력회사 총액공사"," 옥천-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 옥천-영동T/L 수평 추락방지장치 설치 2. 구간 :  영동분기T/L 1~61호","2025-05-07 08:00","2025-05-16 18:00","2025-05-07 08:00","2025-05-16 18:00","매일"]
[401,"충북","청주","오송북청주#2 T/L"," 신청주-문백T/L 건설공사","- 계통연결(신청주~봉명#1, 신청주~북청주#1) - 계통변경(오송-북청주 → 오송-국사) 본선로 구성을 위한 임시선로 구성","2025-05-31 07:00","2025-06-04 18:00","2025-05-31 07:00","2025-06-04 18:00","연속"]
[402,"충북","청주","오송북청주#1 T/L"," 신청주-문백T/L 건설공사","계통변경(오송-북청주 → 오송-국사) 본선로 구성을 위한 임시선로 구성","2025-05-26 07:00","2025-05-30 18:00","2025-05-26 07:00","2025-05-30 18:00","연속"]
[403,"충북","청주","오창국사#1 T/L"," 신청주-문백T/L 건설사업","계통변경(오송-북청주 → 오송-국사) 관련 4회선 상단(오창-국사#1) 선로 휴전","2025-05-26 13:00","2025-05-27 18:00","2025-05-26 13:00","2025-05-27 18:00","연속"]
[404,"충북","청주","오창국사#2 T/L"," 신청주-문백T/L 건설사업","계통변경(오송-북청주 → 오송-국사) 국사S/S 인출변경 작업 4회선(상단) 휴전","2025-05-26 07:00","2025-05-26 12:00","2025-05-26 07:00","2025-05-26 12:00","연속"]
[405,"충북","충주","감곡S/S CB 6100","감곡S/S 23kV 장기사용 GIS 대체공사","RTU철거로 인한 제어케이블  LID 이설 및 시험","2025-05-01 10:00","2025-05-02 18:00","2025-05-01 10:00","2025-05-02 18:00","연속"]
[406,"충북","충주","감곡S/S #2 BUS","감곡S/S 23kV 장기사용 GIS 대체공사","RTU 철거로 인한 제어케이블  LID 이설 및 시험","2025-05-19 10:00","2025-05-20 18:00","2025-05-19 10:00","2025-05-20 18:00","연속"]
[407,"충북","충주","감곡가남#2 T/L","감곡S/S 23kV 장기사용 GIS 대체공사","RTU철거로 인한 제어케이블  LID 이설 및 시험","2025-05-17 10:00","2025-05-18 18:00","2025-05-17 10:00","2025-05-18 18:00","연속"]
[408,"충북","충주","감곡S/S #1 BUS","감곡S/S 23kV 장기사용 GIS 대체공사","RTU철거로 인한 제어케이블  LID 이설 및 시험","2025-05-14 10:00","2025-05-15 18:00","2025-05-14 10:00","2025-05-15 18:00","연속"]
[409,"충북","충주","감곡가남#1 T/L","감곡S/S 23kV 장기사용 GIS 대체공사","RTU철거로 인한 제어케이블  LID 이설 및 시험","2025-05-10 10:00","2025-05-11 18:00","2025-05-10 10:00","2025-05-11 18:00","연속"]
[410,"충북","충주","금왕남음성#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기)","2025-05-14 07:30","2025-05-16 18:00","2025-05-14 07:30","2025-05-16 18:00","매일"]
[411,"충북","충주","금왕남음성#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기), 피뢰기 설치(25기)","2025-05-19 07:30","2025-05-21 18:00","취소","취소","매일"]
[412,"충북","충주","단양영월CC#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 수평추락방지장치 설치( 단양-영월CC#2 T/L No.1~1-4,2~75) 및 폴리머지지애자 교체(No.1,61) 시행","2025-05-19 07:00","2025-05-26 18:00","2025-05-19 07:00","2025-05-26 18:00","매일"]
[413,"충북","충주","신제천S/S SEC CB 66670","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  66-67 SEC GIS 보통점검","2025-05-20 14:00","2025-05-20 18:00","취소","취소","연속"]
[414,"충북","충주","신제천S/S SEC CB 61620","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  61-62 SEC GIS 보통점검","2025-05-20 10:00","2025-05-20 14:00","취소","취소","연속"]
[415,"충북","충주","신제천S/S SEC CB 65660","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  65-66 SEC GIS 보통점검","2025-05-19 14:00","2025-05-19 18:00","취소","취소","연속"]
[416,"충북","충주","신제천S/S SEC CB 60610","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  60-61 SEC GIS 보통점검","2025-05-19 10:00","2025-05-19 14:00","취소","취소","연속"]
[417,"충북","충주","신제천왕암#1 T/L","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  신제천-왕암#1TL GIS 보통점검","2025-05-12 10:00","2025-05-12 14:00","2025-05-12 10:00","2025-05-12 14:00","연속"]
[418,"충북","충주","신제천남원주#1 T/L","345kV 신제천-신영주 등 9개T/L 수평추락방지장치 설치공사","수평추락방지장치 설치 (No.1-37)","2025-05-03 07:00","2025-05-06 16:00","취소","취소","매일"]
[419,"충북","충주","신제천영월CC#1 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 수평추락방지장치 설치( 신제천-영월CC#1 T/L No.15,20,26,27,35~75) 및 폴리머지지애자 교체(No.40,43,54,66,77) 시행","2025-05-27 07:00","2025-06-03 18:00","2025-05-27 07:00","2025-06-03 18:00","매일"]
[420,"충북","충주","신충주S/S CB 6100","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  60-65 TIE GIS 보통점검","2025-05-02 10:00","2025-05-02 14:00","2025-05-02 10:00","2025-05-02 14:00","연속"]
[421,"충북","충주","신충주음성#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","피뢰기 설치(7기), 애자교체(4기), SB댐퍼 설치(2기)","2025-05-22 07:30","2025-05-23 18:00","2025-05-22 07:30","2025-05-23 18:00","매일"]
[422,"충북","충주","신충주감곡#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","철탑 만곡부재 정비(2기)","2025-05-29 07:30","2025-05-29 18:00","취소","취소","연속"]
[423,"충북","충주","음성금왕#2 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기), 아킹혼 철거(1기)","2025-05-14 07:30","2025-05-16 18:00","취소","취소","매일"]
[424,"충북","충주","음성금왕#1 T/L","2024~2025년 충북본부 직할 가공송전 협력회사 공사","수평 추락방지장치 설치(23기), 피뢰기 설치(32기), 애자교체(1기)","2025-05-19 07:30","2025-05-23 18:00","취소","취소","매일"]
[425,"충북","충주","제천영월#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","2024~2025년 충주전력지사 송전협력회사 공사 병가구간으로 인한 안전확보( 단양-영월CC#2 및  신제천-영월CC#1)","2025-05-26 07:00","2025-05-27 18:00","2025-05-26 07:00","2025-05-27 18:00","매일"]
[426,"충북","충주","충주충주HP#1 T/L"," 충주-충주HP T/L 전선접속개소 교체공사"," 충주-충주HP #1 No.9~20 전선전속개소교체공사","2025-05-16 07:30","2025-05-29 18:00","2025-05-16 07:30","2025-05-29 18:00","연속"]
[427,"충북","충주","왕암충주 T/L"," 충주-충주HP T/L 전선접속개소 교체공사"," 충주-충주HP #1 No.9~20 전선전속개소교체공사 안전확보를 위한 병가구간 휴전","2025-05-16 07:30","2025-05-29 18:00","2025-05-16 07:30","2025-05-29 18:00","매일"]
[428,"충북","충주","충주충주HP#2 T/L"," 충주-충주HP T/L 전선접속개소 교체공사"," 충주-충주HP #2 No.9~20 전선전속개소교체","2025-05-02 07:30","2025-05-15 18:00","2025-05-02 07:30","2025-05-15 18:00","연속"]
[429,"충북","충주","북충주충주 T/L"," 충주-충주HP T/L 전선접속개소 교체공사"," 충주-충주HP #2 No.9~20 전선전속개소교체공사 안전확보를 위한 병가구간 휴전","2025-05-02 07:30","2025-05-15 18:00","2025-05-02 07:30","2025-05-15 18:00","매일"]
[430,"충북","충주","충주S/S SEC CB 65660","25년 충주전력지사 362,170kV GIS 보통점검공사","충주S/S  65-66 SEC GIS 보통점검","2025-05-15 14:00","2025-05-15 18:00","2025-05-15 14:00","2025-05-15 18:00","연속"]
[431,"충북","충주","충주S/S CB 6200","25년 충주전력지사 362,170kV GIS 보통점검공사","충주S/S  61-66 BUS-TIE GIS 보통점검","2025-05-16 10:00","2025-05-16 14:00","2025-05-16 10:00","2025-05-16 14:00","연속"]
[432,"대전세종충남","대전","신옥천남대전#3 T/L"," 신옥천-남대전삼사T/L 지장수목 전지 및 벌채"," 신옥천-남대전삼사T/L 지장수목 전지 및 벌채","2025-05-07 09:00","2025-05-07 14:00","2025-05-07 09:00","2025-05-07 14:00","연속"]
[433,"대전세종충남","대전","신옥천남대전#4 T/L"," 신옥천-남대전삼사T/L 지장수목 전지 및 벌채"," 신옥천-남대전삼사T/L 지장수목 전지 및 벌채","2025-05-07 14:00","2025-05-07 18:00","2025-05-07 14:00","2025-05-07 18:00","연속"]
[434,"대전세종충남","대전","부여논산#2 T/L","[취소시][가압X]논산S/S 부여-논산#2T/L GIS 정밀점검","[취소시][가압X]논산S/S 부여-논산#2T/L GIS 정밀점검","2025-05-14 09:00","2025-05-15 18:00","2025-05-14 09:00","2025-05-15 18:00","연속"]
[435,"대전세종충남","대전","부여논산#1 T/L","[취소시][가압X]논산S/S 부여-논산#1T/L GIS 정밀점검","[취소시][가압X]논산S/S 부여-논산#1T/L GIS 정밀점검","2025-05-12 09:00","2025-05-13 18:00","2025-05-12 09:00","2025-05-13 18:00","연속"]
[436,"대전세종충남","대전","논산은진#2 T/L","[즉시가압O]논산S/S  논산-은진#2T/L CB 부동작시험","[즉시가압O]논산S/S  논산-은진#2T/L CB 부동작시험","2025-05-21 13:00","2025-05-21 16:00","2025-05-21 13:00","2025-05-21 16:00","연속"]
[437,"대전세종충남","대전","논산은진#1 T/L","[즉시가압O]논산S/S  논산-은진#1T/L CB 부동작시험","[즉시가압O]논산S/S  논산-은진#1T/L CB 부동작시험","2025-05-21 09:00","2025-05-21 12:00","2025-05-21 09:00","2025-05-21 12:00","연속"]
[438,"대전세종충남","대전","신계룡두마#1 T/L","[취소시][가압X]신계룡,두마S/S 신계룡-두마#1TL 보호반 대체","[취소시][가압X]신계룡,두마S/S 신계룡-두마#1TL 보호반 대체","2025-05-07 09:00","2025-05-09 18:00","취소","취소","연속"]
[439,"대전세종충남","대전","신계룡두마#2 T/L","[취소시][가압X]신계룡,두마S/S 신계룡-두마#2TL 보호반대체","[취소시][가압X]신계룡,두마S/S 신계룡-두마#2TL 보호반대체","2025-05-12 09:00","2025-05-14 18:00","취소","취소","연속"]
[440,"대전세종충남","대전","신계룡두마#1 T/L","[연속휴전취소시][즉시가압O]345kV신옥천-청양T/L추락방지설치공사","[변전연속휴전취소시][송전][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","2025-05-07 07:00","2025-05-09 11:30","취소","취소","매일"]
[441,"대전세종충남","대전","신계룡은진#1 T/L","[송전][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","[송전][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","2025-05-07 07:00","2025-05-16 11:30","취소","취소","매일"]
[442,"대전세종충남","대전","신옥천용운#2 T/L"," 신옥천-용운T/L 지장수목 전지 및 벌채"," 신옥천-용운T/L 지장수목 전지 및 벌채","2025-05-02 13:00","2025-05-02 18:00","2025-05-02 13:00","2025-05-02 18:00","연속"]
[443,"대전세종충남","대전","신옥천용운#1 T/L"," 신옥천-용운T/L 지장수목 전지 및 벌채"," 신옥천-용운T/L 지장수목 전지 및 벌채","2025-05-02 09:00","2025-05-02 13:00","2025-05-02 09:00","2025-05-02 13:00","연속"]
[444,"대전세종충남","서산","석문당진화력#2 T/L","[4월취소시]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [서산송전] 철탑 정밀점검 (김성현대리)","2025-05-14 12:00","2025-05-16 18:00","취소","취소","연속"]
[445,"대전세종충남","서산","석문당진화력#1 T/L","[4월취소시]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [서산송전] 철탑 정밀점검 (김성현대리)","2025-05-12 09:00","2025-05-14 12:00","취소","취소","연속"]
[446,"대전세종충남","서산","대산석문#2 T/L","25년 서산P/O  이하 정밀,보통점검공사","(4월 휴전 취소시)(즉시가압가능) 대산S/S  대산-석문#2T/L GIS 보통점검","2025-05-20 09:30","2025-05-20 18:00","2025-05-19 09:30","2025-05-19 18:00","연속"]
[447,"대전세종충남","서산","서산대산#4 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 서산S/S  서산-대산#4T/L GIS, LA 보통점검","2025-05-01 09:30","2025-05-01 18:00","2025-05-01 09:30","2025-05-01 18:00","연속"]
[448,"대전세종충남","서산","서산해미 T/L","25년 서산P/O  이하 정밀,보통점검공사","(즉시가압불가) 서산S/S  서산-해미T/L GIS 정밀점검","2025-05-23 09:00","2025-05-26 14:00","2025-05-23 09:00","2025-05-26 14:00","연속"]
[449,"대전세종충남","서산","대산석문#1 T/L","석문S/S  가스공사T/L GIS 증설공사","석문S/S  가스공사T/L #1BUS측 GIS 무부하가압","2025-05-21 10:00","2025-05-22 10:00","취소","취소","연속"]
[450,"대전세종충남","서산","대산석문#1 T/L","석문S/S  가스공사T/L GIS 증설공사","석문S/S  가스공사T/L #2BUS용 GIS 무부하 가압","2025-05-23 10:00","2025-05-24 10:00","취소","취소","연속"]
[451,"대전세종충남","서산","서산태안#2 T/L","25년 서산P/O  이하 정밀,보통점검공사","(즉시가압불가) 태안S/S  서산-태안#2T/L GIS 정밀점검","2025-05-09 09:00","2025-05-11 18:00","취소","취소","연속"]
[452,"대전세종충남","서산","서산태안#2 T/L","25년 서산P/O  이하 정밀,보통점검공사","(즉시가압불가) 서산S/S  서산-태안#2T/L GIS 정밀점검","2025-05-29 09:00","2025-06-01 14:00","취소","취소","연속"]
[453,"대전세종충남","서산","합덕송악#2 T/L","25년 서산P/O  이하 정밀,보통점검공사","(4월 휴전 취소시)(즉시가압가능) 합덕S/S  합덕-송악#2T/L GIS 보통점검","2025-05-28 09:30","2025-05-28 18:00","2025-05-28 09:30","2025-05-28 18:00","연속"]
[454,"대전세종충남","서산","합덕송악#1 T/L","'25년도 가공송전 순시점검 위탁공사"," 합덕-송악#1T/L 정밀점검 No.2~28 [병가철탑](상단)345kV 신서산-아산#1 No.47~73,(하단) 합덕-송악#1T/L No.2~28 [즉시가압가능], 주말작업 포함","2025-05-17 07:00","2025-05-18 18:00","2025-05-17 07:00","2025-05-18 18:00","매일"]
[455,"대전세종충남","서산","합덕송악#2 T/L","'25년도 가공송전 순시점검 위탁공사"," 합덕-송악#2T/L 정밀점검 No.2~28 [병가철탑](상단)345kV 신서산-아산#1 No.47~73,(하단) 합덕-송악#2T/L No.2~28 [즉시가압가능], 주말작업 포함","2025-05-10 07:00","2025-05-11 18:00","2025-05-10 07:00","2025-05-11 18:00","매일"]
[456,"대전세종충남","세종","덕진공주#2 T/L"," 덕진공주T/L 정밀점검"," 덕진공주T/L 정밀점검","2025-05-22 09:00","2025-06-02 18:00","2025-05-22 09:00","2025-06-02 18:00","매일"]
[457,"대전세종충남","세종","덕진공주#1 T/L"," 덕진공주T/L 정밀점검"," 덕진공주T/L 정밀점검","2025-05-12 09:00","2025-05-21 18:00","2025-05-12 09:00","2025-05-21 18:00","매일"]
[458,"대전세종충남","세종","부강대청HP T/L","[즉시가압O]  부강-대청H/P T/L 피뢰기 설치공사","고객선로 인근 철탑으로 낙뢰고장 시 파급효과가 커 피뢰기 설치 필요함. 부강-대청H/P 오전 작업, 신탄진-대청H/P 오후 작업","2025-05-15 07:00","2025-05-15 13:00","2025-05-15 07:00","2025-05-15 13:00","연속"]
[459,"대전세종충남","세종","부강대청HP T/L","[즉시가압O]  부강-대청H/P T/L 피뢰기 설치공사","고객선로 인근 철탑으로 낙뢰고장 시 파급효과가 커 피뢰기 설치 필요함.","2025-05-16 07:00","2025-05-16 18:00","2025-05-16 07:00","2025-05-16 18:00","연속"]
[460,"대전세종충남","세종","세종부강#1 T/L","[즉시가압O][안전목적 휴전]  부강-신탄진T/L 피뢰기 공사","신탄진-대청H/P, 부강-대청H/P 피뢰기 설치 공사 시 4회선 병가철탑 구간에 대한 안전목적상 휴전 필요 개소","2025-05-15 07:00","2025-05-16 18:00","2025-05-15 07:00","2025-05-16 18:00","매일"]
[461,"대전세종충남","세종","조치원전의#2 T/L","[송전] 조치원-전의T/L 안전이격 및 전력선 교체공사","○  조치원-전의T/L 안전이격 및 전력선 교체공사 - 지지물 교체 : No.25,33,34 - 용량증대 전선교체 : 조치원S/S~전의S/S","2025-05-17 07:00","2025-05-31 18:00","2025-05-17 07:00","2025-05-31 18:00","연속"]
[462,"대전세종충남","직할","덕진대화#2 T/L","(4월취소시) 덕진-대화TL 지장수목 전지 및 벌채"," 덕진-대화TL 지장수목 전지 및 벌채(도로횡단 개소)","2025-05-12 08:00","2025-05-12 18:00","2025-05-12 08:00","2025-05-12 18:00","연속"]
[463,"대전세종충남","직할","덕진대화#1 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-05-08 09:00","2025-05-09 18:00","2025-05-08 09:00","2025-05-09 18:00","연속"]
[464,"대전세종충남","직할","송강신일#2 T/L","(4월 취소시)송강,신일S/S 송강-신일#2T/L 보호반 대체공사","송강,신일S/S 송강-신일#2T/L 송전선로 보호반 대체","2025-05-23 08:00","2025-05-25 18:00","취소","취소","연속"]
[465,"대전세종충남","직할","둔곡송강#2 T/L","[4월 휴전 취소시] 둔곡-송강T/L 지장수목 전지 및 벌채","[4월 휴전 취소시] 둔곡-송강T/L 지장수목 전지 및 벌채","2025-05-21 09:00","2025-05-22 18:00","취소","취소","매일"]
[466,"대전세종충남","직할","둔곡송강#1 T/L","[4월 휴전 취소시] 둔곡-송강T/L 지장수목 전지 및 벌채","[4월 휴전 취소시] 둔곡-송강T/L 지장수목 전지 및 벌채","2025-05-19 09:00","2025-05-20 18:00","취소","취소","매일"]
[467,"대전세종충남","직할","신탄진대청HP T/L","[즉시가압O]  신탄진-대청H/P T/L 피뢰기 설치공사","고객선로 인근 철탑으로 낙뢰고장 시 파급효과가 커 피뢰기 설치 필요함. 부강-대청H/P 오전 작업, 신탄진-대청H/P 오후 작업","2025-05-15 13:00","2025-05-15 18:00","2025-05-15 13:00","2025-05-15 18:00","연속"]
[468,"대전세종충남","천안","둔포추팔#2 T/L","둔포S/S  둔포-추팔 #2T/L 차단기 개폐타임 측정","(4월 취소시)[즉시가압 가능]둔포S/S  둔포-추팔 #2T/L 차단기 개폐타임 측정","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[469,"대전세종충남","천안","둔포추팔#1 T/L","둔포S/S  둔포-추팔 #1T/L 차단기 개폐타임 측정","(4월 취소시)[즉시가압 가능]둔포S/S  둔포-추팔 #1T/L 차단기 개폐타임 측정","2025-05-07 09:00","2025-05-07 18:00","2025-05-07 09:00","2025-05-07 18:00","연속"]
[470,"대전세종충남","천안","장재불당#2 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-05-22 09:00","2025-05-24 18:00","2025-05-22 09:00","2025-05-24 18:00","연속"]
[471,"대전세종충남","천안","장재불당#1 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-05-19 09:00","2025-05-21 18:00","2025-05-19 09:00","2025-05-21 18:00","연속"]
[472,"대전세종충남","천안","신온양한샘#2 T/L","신온양S/S 신온양-한샘#2T/L GIS 보통점검","(즉시가압가능)신온양S/S  신온양-한샘#2T/L GIS 보통점검","2025-05-27 09:00","2025-05-27 18:00","2025-05-27 09:00","2025-05-27 18:00","연속"]
[473,"대전세종충남","천안","신온양한샘#1 T/L","신온양S/S 신온양-한샘#1T/L GIS 보통점검","(즉시가압가능)신온양S/S  신온양-한샘#1T/L GIS 보통점검","2025-05-28 09:00","2025-05-28 18:00","2025-05-28 09:00","2025-05-28 18:00","연속"]
[474,"대전세종충남","천안","아산온양#2 T/L"," 아산-온양T/L 추락방지장치 설치공사(주말x)","[즉시가압가능] 아산-온양T/L No. 15 ~ 50 추락방지장치 설치","2025-05-23 07:00","2025-05-28 18:00","취소","취소","매일"]
[475,"대전세종충남","천안","아산온양#1 T/L"," 아산-온양T/L 추락방지장치 설치공사","[즉시가압가능] 아산-온양T/L No. 15 ~ 50 추락방지장치 설치","2025-05-19 07:00","2025-05-22 18:00","취소","취소","매일"]
[476,"대전세종충남","천안","아산합덕#1 T/L","아산S/S  아산-합덕#1T/L GIS 불량 PD 센서 교체","(즉시가압불가)아산S/S  아산-합덕#1T/L GIS 불량 PD 센서 교체","2025-05-15 09:00","2025-05-16 18:00","2025-05-15 09:00","2025-05-16 18:00","연속"]
[477,"대전세종충남","천안","아산S/S #65 BUS","아산S/S  아산-합덕#1T/L GIS 불량 PD 센서 교체","(즉시가압불가)아산S/S  아산-합덕#1T/L GIS 불량 PD 센서 교체","2025-05-15 09:00","2025-05-16 18:00","2025-05-15 09:00","2025-05-16 18:00","연속"]
[478,"대전세종충남","천안","아산S/S SEC CB 65660","아산S/S  65-66 GIS PD 센서 교체","(즉시가압불가)아산S/S  65-66-0 GIS 불량 PD 센서 교체","2025-05-12 09:00","2025-05-13 18:00","2025-05-12 09:00","2025-05-13 18:00","연속"]
[479,"대전세종충남","천안","아산S/S #66 BUS","아산S/S  65-66 GIS PD 센서 교체","(즉시가압불가)아산S/S  65-66-0 GIS 불량 PD 센서 교체","2025-05-12 09:00","2025-05-13 18:00","2025-05-12 09:00","2025-05-13 18:00","연속"]
[480,"대전세종충남","천안","아산합덕#1 T/L"," 아산-합덕T/L 추락방지장치 설치공사(4회선)","[즉시가압가능] 아산-합덕T/L No. 1 ~ 53 추락방지장치 설치 [병가철탑](상단)신서산-아산#1No.74~113,(하단)아산-합덕#1No.13~52","2025-05-12 07:00","2025-05-16 18:00","2025-05-12 07:00","2025-05-16 18:00","매일"]
[481,"대전세종충남","천안","아산합덕#2 T/L"," 아산-합덕T/L 추락방지장치 설치공사(4회선)","[즉시가압가능] 아산-합덕T/L No. 1 ~ 53 추락방지장치 설치 [병가철탑](상단)신서산-아산#2No.74~113,(하단)아산-합덕#2No.13~52","2025-05-01 07:00","2025-05-09 18:00","2025-05-01 07:00","2025-05-09 18:00","매일"]
[482,"대전세종충남","천안","아산예산#2 T/L","(4월취소시) 아산-예산#2T/L 노후 보호배전반 대체","(4월취소시)(즉시가압불가) 아산-예산#2T/L 노후 보호배전반 대체(장기미교체 대상)","2025-05-12 09:00","2025-05-16 18:00","2025-05-20 09:00","2025-05-23 18:00","연속"]
[483,"대전세종충남","천안","인주불당#1 T/L","인주, 불당S/S 인주-불당#1T/L GIS 보통점검","(즉시가압가능)인주, 불당S/S  인주-불당#1T/L GIS 보통점검","2025-05-29 09:00","2025-05-29 18:00","2025-05-29 09:00","2025-05-29 18:00","연속"]
[484,"대전세종충남","천안","인주불당#2 T/L","인주, 불당S/S 인주-불당#2T/L GIS 보통점검","(즉시가압가능)인주, 불당S/S  인주-불당#2T/L GIS 보통점검","2025-05-30 09:00","2025-05-30 18:00","2025-05-30 09:00","2025-05-30 18:00","연속"]
[485,"대전세종충남","천안","서천안탕정#1 T/L","탕정S/S 서천안-탕정#1T/L 전자변 교체 및 CB 개폐타임 측정","탕정S/S  서천안-탕정#1T/L 전자변 교체 및 차단기 개폐타임 측정","2025-05-09 09:00","2025-05-09 18:00","2025-05-09 09:00","2025-05-09 18:00","연속"]
[486,"대전세종충남","청양","신서천대천#1 T/L","[송전] 대천-서천 등 2개T/L 항공구 설치공사","ㅇ 항공구 설치 : 75개 ㅇ 항공구 철거 : 16개","2025-05-20 07:00","2025-05-21 18:00","2025-05-20 07:00","2025-05-21 18:00","매일"]
[487,"대전세종충남","청양","신서천옥산#1 T/L","[송전] 대천-서천 등 2개T/L 항공구 설치공사","ㅇ 항공구 설치 : 75개 ㅇ 항공구 철거 : 16개","2025-05-21 07:00","2025-05-22 18:00","2025-05-21 07:00","2025-05-22 18:00","매일"]
[488,"대전세종충남","청양","옥산부여#1 T/L","[4월취소시]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-05-26 09:00","2025-05-28 12:00","2025-05-26 09:00","2025-05-28 12:00","연속"]
[489,"대전세종충남","청양","옥산부여#2 T/L","[4월취소시]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-05-28 12:00","2025-05-30 18:00","2025-05-28 12:00","2025-05-30 18:00","연속"]
[490,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-05-29 09:00","2025-05-30 18:00","취소","취소","연속"]
[491,"전북","군산","군산동군산#1 T/L","군산P/O 이상 차단기 조작시험","군산P/O 이상 차단기 조작시험","2025-05-07 09:00","2025-05-07 14:00","취소","취소","연속"]
[492,"전북","군산","군산동군산#2 T/L","군산P/O 이상 차단기 조작시험","군산P/O 이상 차단기 조작시험","2025-05-07 14:00","2025-05-07 18:00","취소","취소","연속"]
[493,"전북","군산","군산이리#1 T/L","군산P/O 이상 차단기 조작시험","군산P/O 이상 차단기 조작시험","2025-05-02 09:00","2025-05-02 14:00","취소","취소","연속"]
[494,"전북","군산","군산S/S SEC CB 61620","군산P/O 이상 차단기 조작시험","군산P/O 이상 차단기 조작시험","2025-05-07 09:00","2025-05-07 14:00","2025-05-07 09:00","2025-05-07 14:00","연속"]
[495,"전북","군산","군산S/S SEC CB 66670","군산P/O 이상 차단기 조작시험","군산P/O 이상 차단기 조작시험","2025-05-07 14:00","2025-05-07 18:00","2025-05-07 14:00","2025-05-07 18:00","연속"]
[496,"전북","군산","군산서군산#1 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-05-27 09:00","2025-05-28 18:00","취소","취소","연속"]
[497,"전북","군산","동군산군산CC#1 T/L","군산P/O 이상 차단기 점검공사","군산P/O 이상 차단기 점검공사","2025-05-14 09:00","2025-05-14 18:00","2025-05-14 09:00","2025-05-14 18:00","연속"]
[498,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사(중복)","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2025-05-28 09:00","2025-05-30 18:00","취소","취소","연속"]
[499,"전북","군산","동군산군산CC#2 T/L","군산P/O 이상 차단기 점검공사","군산P/O 이상 차단기 점검공사","2025-05-15 09:00","2025-05-15 18:00","2025-05-15 09:00","2025-05-15 18:00","연속"]
[500,"전북","군산","동군산장항#2 T/L","'25년 가공송전선로 순시점검 위탁공사"," 동군산-장항T/L 정밀점검","2025-05-21 09:00","2025-05-23 18:00","취소","취소","연속"]
[501,"전북","군산","서군산S/S CB 6200","서군산S/S 모선보호반 LOGIC 개선","서군산S/S 모선보호반 LOGIC 개선","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[502,"전북","군산","서군산S/S CB 6100","서군산S/S 모선보호반 LOGIC 개선","서군산S/S 모선보호반 LOGIC 개선","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[503,"전북","군산","서군산S/S SEC CB 65660","서군산S/S 모선보호반 LOGIC 개선","서군산S/S 모선보호반 LOGIC 개선","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[504,"전북","군산","서군산S/S SEC CB 60610","서군산S/S 모선보호반 LOGIC 개선","서군산S/S 모선보호반 LOGIC 개선","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[505,"전북","군산","서군산S/S SEC CB 60610","서군산S/S 모선보호반 LOGIC 개선","서군산S/S 모선보호반 LOGIC 개선","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[506,"전북","군산","서군산S/S SEC CB 65660","서군산S/S 모선보호반 LOGIC 개선","서군산S/S 모선보호반 LOGIC 개선","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[507,"전북","군산","영등낭산#1 T/L"," 영등S/S 혼용운영시스템 설치공사","- 영등S/S 혼용화 관련 제어케이블 이설 [RTU ↔ 현장설비] → [현장정보처리반 ↔ 현장설비","2025-05-08 09:00","2025-05-09 18:00","취소","취소","연속"]
[508,"전북","군산","영등낭산#2 T/L"," 영등S/S 혼용운영시스템 설치공사","- 영등S/S 혼용화 관련 제어케이블 이설 [RTU ↔ 현장설비] → [현장정보처리반 ↔ 현장설비","2025-05-22 09:00","2025-05-23 18:00","취소","취소","연속"]
[509,"전북","군산","이리백산#2 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-05-17 08:00","2025-05-21 18:00","2025-05-17 08:00","2025-05-21 18:00","연속"]
[510,"전북","군산","이리백산#2 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-05-04 08:00","2025-05-08 18:00","2025-05-04 08:00","2025-05-08 18:00","연속"]
[511,"전북","군산","이리백산#1 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-05-09 08:00","2025-05-16 18:00","2025-05-09 08:00","2025-05-16 18:00","연속"]
[512,"전북","군산","은진함열#1 T/L","24~25년 군산P/O 변전협력회사 총액공사(중복)","은진-함열#1T/L 노후보호반 대체(중복)","2025-05-26 09:00","2025-05-28 13:00","취소","취소","연속"]
[513,"전북","군산","은진함열#2 T/L","24~25년 군산P/O 변전협력회사 총액공사(중복)","은진-함열#2T/L 노후보호반 대체(중복)","2025-05-28 13:00","2025-05-30 13:00","취소","취소","연속"]
[514,"전북","김제","부안동부안#2 T/L","부안S/S  모선구분차단기 설치공사(무부하)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-05-05 15:00","2025-05-06 15:00","취소","취소","연속"]
[515,"전북","김제","부안동부안#1 T/L","부안S/S  모선구분차단기 설치공사(무부하)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-05-01 15:00","2025-05-02 15:00","취소","취소","연속"]
[516,"전북","김제","백산김제#1 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-05-04 08:00","2025-05-08 18:00","2025-05-04 08:00","2025-05-08 18:00","연속"]
[517,"전북","김제","백산김제#1 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-05-17 08:00","2025-05-21 18:00","2025-05-17 08:00","2025-05-21 18:00","연속"]
[518,"전북","김제","백산김제#2 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-05-09 08:00","2025-05-16 18:00","2025-05-09 08:00","2025-05-16 18:00","연속"]
[519,"전북","직할","남원임실#2 T/L","남원S/S 남원-임실 #2T/L 보통점검","남원S/S 남원-임실 #2T/L 보통점검","2025-05-09 09:00","2025-05-09 18:00","취소","취소","연속"]
[520,"전북","직할","남원임실#1 T/L","남원S/S 남원-임실 #1T/L 보통점검","남원S/S 남원-임실 #1T/L 보통점검","2025-05-08 09:00","2025-05-08 18:00","취소","취소","연속"]
[521,"전북","직할","무주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 -  북전주-진안T/L No.50~104 -  무주분기T/L No.1~45","2025-05-10 07:30","2025-05-16 18:00","취소","취소","연속"]
[522,"전북","직할","북전주S/S #1 BUS","북전주-봉동#2TL 1DS 모선부 정밀점검","북전주-봉동#2TL 1DS 모선부 정밀점검","2025-05-19 09:00","2025-05-20 18:00","취소","취소","연속"]
[523,"전북","직할","북전주S/S #2 BUS","북전주-봉동#2TL 2DS 모선부 정밀점검","북전주-봉동#2TL 2DS 모선부 정밀점검","2025-05-21 09:00","2025-05-22 18:00","취소","취소","연속"]
[524,"전북","직할","북전주봉동#1 T/L","북전주-봉동#1T/L 송전선로 보호반 대체공사","북전주-봉동#1T/L 송전선로 보호반 대체공사","2025-05-26 09:00","2025-05-29 18:00","취소","취소","연속"]
[525,"전북","직할","북전주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.1~50","2025-05-07 07:30","2025-05-09 18:00","취소","취소","연속"]
[526,"전북","직할","북전주봉동#2 T/L","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-05-19 09:00","2025-05-22 18:00","취소","취소","연속"]
[527,"전북","직할","신남원S/S #4 EM.Tr CB","신남원 ESS 변전설비 #4EM.Bank 초기점검","변압기 1대, 170gis 1대, 23kV gis 8대, EP.Tr 7대","2025-05-19 09:00","2025-05-22 18:00","2025-05-19 09:00","2025-05-22 18:00","연속"]
[528,"전북","직할","탄소전주#2 T/L","세니온제 제어IED 성능개선","세니온제 제어IED 성능개선","2025-05-23 08:00","2025-05-23 12:00","2025-05-23 08:00","2025-05-23 12:00","연속"]
[529,"전북","직할","탄소전주#1 T/L","세니온제 제어IED 성능개선","세니온제 제어IED 성능개선","2025-05-22 16:00","2025-05-22 18:00","2025-05-22 16:00","2025-05-22 18:00","연속"]
[530,"전북","직할","동전주태평#2 T/L","태평S/S  장기사용 GIS 교체공사","170kV GIS × 6CCT 교체(T/L 2CCT, T/R 3CCT, B/T 1CCT)","2025-05-07 09:00","2025-06-17 18:00","2025-05-07 09:00","2025-06-17 18:00","연속"]
[531,"전북","직할","서곡태평#1 T/L","태평S/S  장기사용 GIS 교체공사(시험가압)","170kV GIS × 6CCT 교체(T/L 2CCT, T/R 3CCT, B/T 1CCT)","2025-05-28 18:00","2025-05-29 18:00","2025-05-28 18:00","2025-05-29 18:00","연속"]
[532,"전북","직할","서곡태평#1 T/L","태평S/S  장기사용 GIS 교체공사(시험가압, 고깔)","170kV GIS × 6CCT 교체(T/L 2CCT, T/R 3CCT, B/T 1CCT)","2025-05-12 13:00","2025-05-12 18:00","2025-05-12 13:00","2025-05-12 18:00","연속"]
[533,"광주전남","강진","강진장흥#2 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 강진-장흥#2T/L 피뢰기 설치","2025-05-26 07:00","2025-05-30 18:00","취소","취소","매일"]
[534,"광주전남","강진","금정강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","금정-강진T/L 피뢰기 설치 (장흥-벌교 병가구간 포함)","2025-05-26 07:00","2025-05-27 18:00","취소","취소","매일"]
[535,"광주전남","강진","신강진강진#1 T/L"," 강진-장흥 등 5개T/L 피뢰기 및 추락방지장치 설치공사","신강진-강진T/L 피뢰기 설치","2025-05-12 07:00","2025-05-13 18:00","취소","취소","매일"]
[536,"광주전남","강진","강진남창#1 T/L"," 강진-장흥 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 신강진-강진T/L 피뢰기 설치 (4회선구간 휴전)","2025-05-12 07:00","2025-05-13 18:00","취소","취소","매일"]
[537,"광주전남","강진","나주금천#1 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#2T/L 정밀점검(안전이격 확보)","2025-05-21 09:00","2025-05-23 18:00","2025-05-21 09:00","2025-05-23 18:00","매일"]
[538,"광주전남","강진","나주엄다#1 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","-170kV GIS 보통점검","2025-05-08 10:00","2025-05-08 14:00","2025-05-08 18:00","2025-05-08 22:00","연속"]
[539,"광주전남","강진","나주영암#2 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#2T/L 정밀점검","2025-05-14 09:00","2025-05-23 18:00","2025-05-14 09:00","2025-05-23 18:00","매일"]
[540,"광주전남","강진","강진남창#2 T/L","강진-남창#2T/L 보호계전기 임시점검","세니온제 보호계전기 성능개선(강진-남창#2T/L) - 계전기 성능개선 및 Trip Time 측정, 연동시험 등","2025-05-12 08:00","2025-05-12 20:00","취소","취소","연속"]
[541,"광주전남","강진","삼호화원#2 T/L"," 삼호-화원 지중T/L(복도체화) 건설공사"," XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2025-05-26 09:00","2025-06-30 18:00","취소","취소","연속"]
[542,"광주전남","강진","신강진대불#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","신강진-대불#2T/L 가공지선 교체","2025-05-29 07:00","2025-05-29 18:00","취소","취소","매일"]
[543,"광주전남","강진","영암금정#1 T/L","2025년 가공송전 순시점검 위탁공사","영암-금정#1T/L 정밀점검","2025-05-12 09:00","2025-05-19 18:00","취소","취소","매일"]
[544,"광주전남","강진","장흥벌교 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","장흥-벌교T/L 피뢰기 설치 (강진-장흥 병가구간 포함)","2025-05-28 07:00","2025-06-05 18:00","취소","취소","매일"]
[545,"광주전남","강진","해남진도#2 T/L","2025년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검 - 효성제 170kV GIS 개선 등","2025-05-01 09:00","2025-05-01 18:00","2025-05-01 18:00","2025-05-01 23:00","연속"]
[546,"광주전남","강진","남창해남CS#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","해남-해남CS(4회선구간) 추락방지장치 설치공사","2025-05-29 07:00","2025-05-30 18:00","취소","취소","매일"]
[547,"광주전남","강진","해남해남CS#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","해남-해남CS 추락방지장치 설치공사","2025-05-22 07:00","2025-05-30 18:00","취소","취소","매일"]
[548,"광주전남","강진","남창해남CS#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","해남-해남CS(4회선구간) 추락방지장치 설치공사","2025-05-20 07:00","2025-05-21 18:00","취소","취소","매일"]
[549,"광주전남","강진","해남해남CS#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","해남-해남CS 추락방지장치 설치공사","2025-05-12 07:00","2025-05-21 18:00","취소","취소","매일"]
[550,"광주전남","강진","화원진도#1 T/L","2025년 가공송전 순시점검 위탁공사","화원-진도#1T/L 정밀점검","2025-05-28 09:00","2025-05-30 18:00","취소","취소","매일"]
[551,"광주전남","광주","신광주계림#2 T/L","25년도 광주전력지사 변전협력회사 총액공사","신광주계림 #2T/L 보호반 대체 (신광주, 계림S/S)","2025-05-26 09:00","2025-05-28 18:00","취소","취소","연속"]
[552,"광주전남","광주","계림S/S CB 6200","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 6200BUS-TIE 조작시험","2025-05-09 09:00","2025-05-09 18:00","2025-05-09 09:00","2025-05-09 18:00","연속"]
[553,"광주전남","광주","계림S/S SEC CB 61600","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S #60-61BUS-SEC 조작시험","2025-05-08 14:00","2025-05-08 18:00","2025-05-08 14:00","2025-05-08 18:00","연속"]
[554,"광주전남","광주","계림S/S SEC CB 66650","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S #65-#66 BUS-SEC 조작시험","2025-05-08 09:00","2025-05-08 14:00","2025-05-08 09:00","2025-05-08 14:00","연속"]
[555,"광주전남","광주","남광주소태 T/L"," 남광주C/T 이설공사"," 남광주C/T(58호) 신설시 안전이격확보 휴전","2025-05-29 00:07","2025-05-30 18:00","2025-05-29 00:07","2025-05-30 18:00","매일"]
[556,"광주전남","광주","계림남광주 T/L"," 남광주C/T 이설공사"," 남광주C/T(58호) 신설시 안전이격확보 휴전","2025-05-29 00:07","2025-05-30 18:00","2025-05-29 00:07","2025-05-30 18:00","매일"]
[557,"광주전남","광주","담양김제 T/L","2024~25년 광주전력지사 송전 협력회사공사(피뢰기)"," 담양-김제T/L 1~33호 피뢰기설치","2025-05-01 07:00","2025-05-02 18:00","취소","취소","매일"]
[558,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  신광주-장성#2T/L GIS 정밀점검","2025-05-07 09:00","2025-05-09 18:00","취소","취소","연속"]
[559,"광주전남","광주","신광주순창#2 T/L","2024~25년 광주전력지사 송전 협력회사공사","가공지선 교체공사 56~60호","2025-05-13 07:00","2025-05-13 18:00","취소","취소","연속"]
[560,"광주전남","광주","신광주일곡#1 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사"," 신광주-일곡#1T/L PT 보통점검","2025-05-19 08:00","2025-05-19 13:00","2025-05-19 08:00","2025-05-19 13:00","연속"]
[561,"광주전남","광주","신광주일곡#2 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사"," 신광주-일곡#2T/L PT 보통점검","2025-05-19 13:00","2025-05-19 18:00","2025-05-19 13:00","2025-05-19 18:00","연속"]
[562,"광주전남","광주","신광주장성#2 T/L","2024~25년 광주전력지사 송전 협력회사공사","가공지선 교체공사 63~66호","2025-05-12 07:00","2025-05-12 18:00","취소","취소","연속"]
[563,"광주전남","광주","장성영광#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 장성S/S  장성-영광#2T/L GIS보통점검","2025-05-29 09:00","2025-05-29 18:00","취소","취소","연속"]
[564,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 장성S/S  신광주-장성#2T/L GIS보통점검","2025-05-28 09:00","2025-05-28 18:00","취소","취소","연속"]
[565,"광주전남","광주","남광주화순#1 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평추락방지설치 작업구간 - 화순-승주#2T/L No.290~296(남광주-화순#1T/L No.2~8호(병가)) - 계림-남광주#T/L No.57~58","2025-05-19 07:00","2025-05-20 18:00","2025-05-19 07:00","2025-05-20 18:00","매일"]
[566,"광주전남","광주","화순승주#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 피뢰기설치 작업구간 : 화순-승주#2T/L No.206~297","2025-05-19 07:00","2025-05-28 18:00","2025-05-19 07:00","2025-05-28 18:00","매일"]
[567,"광주전남","광주","신화순화순#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#2T/L GIS 정밀점검","2025-05-19 09:00","2025-05-21 18:00","취소","취소","연속"]
[568,"광주전남","광주","신화순화순#1 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#1T/L GIS 정밀점검","2025-05-14 09:00","2025-05-16 18:00","취소","취소","연속"]
[569,"광주전남","광주","화순승주#1 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.5.2(금) 08:00 ~ 25.5.16(금) 18:00 4. 작업구간 :  화순-승주#1T/L No.1~297 5. 작업내용 : 정밀점검","2025-05-02 08:00","2025-05-16 18:00","2025-05-02 08:00","2025-05-16 18:00","매일"]
[570,"광주전남","목포","장성영광#1 T/L"," 영광-홍농 등 4개T/L 선종교체공사","업 체 명 : 지승건설(주) 대 상 : 고창-영광 No.1~45 (13.10km) 내 용 : 고창-영광T/L 선종교체공사(용량증대) 관련 안전이격 휴전","2025-05-27 07:00","2025-05-30 18:00","취소","취소","연속"]
[571,"광주전남","목포","고창영광 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 장성-영광#2T/L 피뢰기 설치 No.69~125 병가 고창-영광T/L 휴전","2025-05-12 07:00","2025-05-16 17:00","취소","취소","매일"]
[572,"광주전남","목포","장성영광#2 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 장성-영광#2T/L 피뢰기 설치 No.69~125","2025-05-05 07:00","2025-05-16 17:00","취소","취소","매일"]
[573,"광주전남","목포","장성영광#2 T/L"," 영광-홍농 등 4개T/L 선종교체공사","업 체 명 : 지승건설(주) 대 상 : 고창-영광 No.1~45 (13.10km) 내 용 : 고창-영광T/L 선종교체공사(용량증대) 관련 안전이격 휴전","2025-05-07 07:00","2025-05-30 18:00","취소","취소","연속"]
[574,"광주전남","목포","고창영광 T/L"," 영광-홍농 등 4개T/L 선종교체공사","업 체 명 : 지승건설(주) 대 상 : 고창-영광 No.1~45 (13.10km) 내 용 : 고창-영광T/L 선종교체공사(용량증대)","2025-05-07 07:00","2025-05-30 18:00","취소","취소","연속"]
[575,"광주전남","순천","백운황금#1 T/L CB","24-25년 순천전력지사 변전협력회사 공사","백운S/S 백운-황금#1T/L GIS 하자점검","2025-05-02 09:00","2025-05-02 18:00","취소","취소","연속"]
[576,"광주전남","순천","백운세풍#2 T/L","24-25년 순천전력지사 변전협력회사 공사","백운S/S 백운-세풍#2T/L GIS 초기점검","2025-05-07 09:00","2025-05-07 18:00","취소","취소","연속"]
[577,"광주전남","순천","승주서순천 T/L","2025년 순천전력지사 362,170kV GIS 정밀,보통점검공사","서순천S/S 승주-서순천T/L GIS 보통점검 및 전자변 교체","2025-05-26 16:00","2025-05-26 20:00","취소","취소","연속"]
[578,"광주전남","순천","서순천벌교#2 T/L","2025년 순천전력지사 362,170kV GIS 정밀,보통점검공사","서순천S/S 서순천-벌교#2T/L GIS 보통점검 및 전자변 교체","2025-05-30 16:00","2025-05-30 20:00","취소","취소","연속"]
[579,"광주전남","순천","서순천벌교#1 T/L","2025년 순천전력지사 362,170kV GIS 정밀,보통점검공사","서순천S/S 서순천-벌교#1T/L GIS 보통점검 및 전자변 교체","2025-05-29 16:00","2025-05-29 20:00","취소","취소","연속"]
[580,"광주전남","순천","소라서순천#2 T/L","2025년 순천전력지사 362,170kV GIS 정밀,보통점검공사","서순천S/S 소라-서순천#2T/L GIS 보통점검 및 전자변 교체","2025-05-28 16:00","2025-05-28 20:00","취소","취소","연속"]
[581,"광주전남","순천","소라서순천#1 T/L","2025년 순천전력지사 362,170kV GIS 정밀,보통점검공사","서순천S/S 소라-서순천#1T/L GIS 보통점검 및 전자변 교체","2025-05-27 16:00","2025-05-27 20:00","취소","취소","연속"]
[582,"광주전남","순천","순천승주#1 T/L","순천-승주#1 T/L 정밀점검","순천-승주#1 T/L 정밀점검 총 89기","2025-05-26 09:00","2025-05-30 18:00","취소","취소","매일"]
[583,"광주전남","순천","화순승주#2 T/L","24-25년 순천전력지사 변전협력회사 공사","화순-승주#2T/L LA(A,B,C) 보통점검","2025-05-02 09:00","2025-05-02 14:00","2025-05-02 09:00","2025-05-02 14:00","연속"]
[584,"광주전남","순천","순천승주#1 T/L","24-25년 순천전력지사 변전협력회사 공사","순천-승주#1T/L LA(A,B,C) 보통점검","2025-05-01 14:00","2025-05-01 18:00","취소","취소","연속"]
[585,"광주전남","순천","승주주암HP T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.5.14(수) 08:00 ~ 18:00 4. 작업구간 :  승주-주암HP T/L No.1 93~95 5. 작업내용 : 정밀점검","2025-05-14 08:00","2025-05-14 18:00","취소","취소","연속"]
[586,"광주전남","순천","순천승주#1 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평추락방지설치 작업구간 : 화순-승주#2T/L No.1~4(순천-승주#1T/L No.1, 승주-서순천T/L No.93~95(병가))","2025-05-29 07:00","2025-05-30 18:00","취소","취소","매일"]
[587,"광주전남","순천","승주서순천 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평추락방지설치 작업구간 : 화순-승주#2T/L No.1~4(순천-승주#1T/L No.1, 승주-서순천T/L No.93~95(병가))","2025-05-29 07:00","2025-05-30 18:00","취소","취소","매일"]
[588,"광주전남","순천","순천승주#2 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.5.14(수) 08:00 ~ 18:00 4. 작업구간 : 순천-승주#2T/L No.1 5. 작업내용 : 정밀점검","2025-05-14 08:00","2025-05-14 18:00","취소","취소","연속"]
[589,"광주전남","순천","계림승주#2 T/L","24-25년 순천전력지사 변전협력회사 공사","계림-승주#2T/L LA(A,B,C) 보통점검","2025-05-02 14:00","2025-05-02 18:00","2025-05-02 14:00","2025-05-02 18:00","연속"]
[590,"광주전남","순천","승주서순천 T/L"," 승주-서순천T/L 추락방지시설 설치공사","수평 추락방지시설 설치공사","2025-05-30 07:00","2025-05-30 18:00","취소","취소","연속"]
[591,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(1차) - BUS SEC 증설 및 #61-66PT&ES 설치","2025-05-14 10:00","2025-05-15 10:00","2025-05-22 18:00","2025-05-23 09:00","연속"]
[592,"광주전남","순천","여천여수#1 T/L"," 여수-소라T/L 추락방지시설 설치공사","여수-소라T/L 수평 설치 (여천-여수 병가)","2025-05-01 07:00","2025-05-01 13:00","취소","취소","연속"]
[593,"광주전남","순천","여수소라#1 T/L"," 여수-소라T/L 추락방지시설 설치공사","여수-소라T/L 수평 설치 (여천-여수 병가)","2025-05-01 07:00","2025-05-01 13:00","취소","취소","연속"]
[594,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(1차) - BUS SEC 증설 및 #61-66PT&ES 설치 무부하가압용","2025-05-01 10:00","2025-05-02 10:00","2025-05-15 18:00","2025-05-16 09:00","연속"]
[595,"광주전남","순천","여수소라#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(1차) - BUS SEC 증설 및 #61-66PT&ES 설치 무부하가압용","2025-05-01 10:00","2025-05-02 10:00","2025-05-15 18:00","2025-05-16 09:00","연속"]
[596,"광주전남","순천","여수소라#2 T/L"," 여수-소라T/L 추락방지시설 설치공사","여수-소라T/L 수평 설치 (여천-여수 병가)","2025-05-01 13:00","2025-05-01 18:00","취소","취소","연속"]
[597,"광주전남","순천","여천여수#2 T/L"," 여수-소라T/L 추락방지시설 설치공사","여수-소라T/L 수평 설치 (여천-여수 병가)","2025-05-01 13:00","2025-05-01 18:00","취소","취소","연속"]
[598,"광주전남","순천","여수소라#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수,소라S/S 여수-소라#2T/L GIS 조작시험","2025-05-01 16:00","2025-05-01 18:00","2025-05-01 18:00","2025-05-01 20:00","연속"]
[599,"광주전남","순천","여수소라#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여수,소라S/S 여수-소라#1T/L GIS 조작시험","2025-05-02 16:00","2025-05-02 18:00","2025-05-02 18:00","2025-05-02 20:00","연속"]
[600,"광주전남","순천","여수소라#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(1차) - BUS SEC 증설 및 #61-66PT&ES 설치","2025-05-14 10:00","2025-05-15 10:00","2025-05-22 18:00","2025-05-23 09:00","연속"]
[601,"광주전남","순천","용성여수산단#2 T/L"," 용성-여수산단#2T/L #1DS 가스누기 해소공사"," 용성-여수산단#2T/L #1DS 가스누기 해소공사","2025-05-12 09:00","2025-05-13 18:00","취소","취소","연속"]
[602,"광주전남","순천","율촌여수산단#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수산단 율촌-여수산단#2T/L GIS 보통점검","2025-05-01 09:00","2025-05-01 18:00","2025-05-01 09:00","2025-05-01 18:00","연속"]
[603,"광주전남","순천","호남TP여수TP#2 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 추락방지시설 설치","2025-05-27 13:00","2025-05-27 18:00","2025-05-27 13:00","2025-05-27 18:00","연속"]
[604,"광주전남","순천","여수TP화치#1 T/L","2025년 순천전력지사 362,170kV GIS 정밀,보통점검공사","여수화력S/S 여수TP-화치#1T/L GIS 보통점검","2025-05-28 10:00","2025-05-28 18:00","취소","취소","연속"]
[605,"광주전남","순천","여수TP화치#1 T/L","345kV 광양-여수TPT/L 추락방지시설 설치공사","4회선 수평 추락방지시설 설치","2025-05-27 13:00","2025-05-27 18:00","2025-05-27 13:00","2025-05-27 18:00","연속"]
[606,"광주전남","순천","여천호남TP#2 T/L"," 여천-호남TP 추락방지시설 설치공사","여천-호남TP 수평설치","2025-05-12 07:00","2025-05-13 18:00","취소","취소","매일"]
[607,"광주전남","순천","여천여수#2 T/L"," 여천-호남TP 추락방지시설 설치공사","여천-호남TP 수평설치","2025-05-14 07:00","2025-05-15 18:00","취소","취소","매일"]
[608,"광주전남","순천","여천여수#1 T/L"," 여천-호남TP 추락방지시설 설치공사","여천-호남TP 수평설치","2025-05-12 07:00","2025-05-13 18:00","취소","취소","매일"]
[609,"광주전남","순천","여천호남TP#1 T/L"," 여천-호남TP 추락방지시설 설치공사","여천-호남TP 수평설치","2025-05-14 07:00","2025-05-15 18:00","취소","취소","매일"]
[610,"광주전남","순천","여수TP용성#1 T/L","GIS 불량 유압력계 교체","GIS 불량 유압력계 교체","2025-05-07 09:00","2025-05-07 18:00","취소","취소","연속"]
[611,"광주전남","순천","용성여수산단#1 T/L"," 여수TP-용성T/L 추락방지시설 설치공사","여수TP-용성 수평설치(용성-여수산단 병가)","2025-05-07 07:00","2025-05-07 13:00","취소","취소","연속"]
[612,"광주전남","순천","여수TP용성#2 T/L"," 여수TP-용성T/L 추락방지시설 설치공사","여수TP-용성 수평설치(용성-여수산단 병가)","2025-05-07 13:00","2025-05-07 18:00","취소","취소","연속"]
[613,"광주전남","순천","여수TP용성#1 T/L"," 여수TP-용성T/L 추락방지시설 설치공사","여수TP-용성 수평설치(용성-여수산단 병가)","2025-05-07 07:00","2025-05-07 13:00","취소","취소","연속"]
[614,"광주전남","순천","용성여수산단#2 T/L"," 여수TP-용성T/L 추락방지시설 설치공사","여수TP-용성 수평설치(용성-여수산단 병가)","2025-05-07 13:00","2025-05-07 18:00","취소","취소","연속"]
[615,"광주전남","순천","율촌여수산단#1 T/L","율촌-여수산단#1 T/L 정밀점검","율촌-여수산단#1 T/L 정밀점검 총 51기","2025-05-14 09:00","2025-05-16 18:00","2025-05-14 09:00","2025-05-16 18:00","매일"]
[616,"광주전남","순천","율촌여수산단#2 T/L"," 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-05-09 07:00","2025-05-09 18:00","2025-05-09 07:00","2025-05-09 18:00","연속"]
[617,"광주전남","순천","율촌여수산단#1 T/L"," 율촌-여수산단T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-05-08 07:00","2025-05-08 18:00","2025-05-08 07:00","2025-05-08 18:00","연속"]
[618,"광주전남","순천","율촌민자#2 T/L"," 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-05-02 13:00","2025-05-02 18:00","취소","취소","연속"]
[619,"광주전남","순천","율촌민자#1 T/L"," 율촌민자T/L 추락방지시설 설치공사","수평 추락방지시설 설치","2025-05-02 07:00","2025-05-02 13:00","취소","취소","연속"]
[620,"광주전남","순천","율촌여수산단#2 T/L","율촌-여수산단#2 T/L 정밀점검","율촌-여수산단#2 T/L 정밀점검 총 51기","2025-05-19 09:00","2025-05-21 18:00","2025-05-19 09:00","2025-05-21 18:00","매일"]
[621,"광주전남","순천","율촌화치#2 T/L","율촌-여수산단#1 T/L 정밀점검","율촌-여수산단#1 T/L 정밀점검 총 51기 - 병가선로 휴전신청","2025-05-14 09:00","2025-05-16 18:00","2025-05-14 09:00","2025-05-16 18:00","매일"]
[622,"광주전남","순천","율촌화치#1 T/L","율촌-여수산단#2 T/L 정밀점검","율촌-여수산단#2 T/L 정밀점검 총 51기 - 병가선로 휴전신청","2025-05-19 09:00","2025-05-21 18:00","2025-05-19 09:00","2025-05-21 18:00","매일"]
[623,"광주전남","순천","호남TP여수TP#1 T/L","24-25년 순천전력지사 변전협력회사 공사","호남TP-여수TP#1T/L LA(A,B,C) 초기점검","2025-05-07 09:00","2025-05-07 18:00","2025-05-07 09:00","2025-05-07 18:00","연속"]
[624,"광주전남","순천","호남TP여수TP#2 T/L","24-25년 순천전력지사 변전협력회사 공사","호남TP-여수TP#2T/L LA(A,B,C) 초기점검","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[625,"광주전남","직할","나주금천#1 T/L"," 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 관형지지물(No.80) 1기 설치 ○ 연선 및 긴선 ○ 기타 : 병가선로( 남광주-금천T/L)안전이격 휴전","2025-05-12 07:00","2025-05-14 18:00","2025-05-12 07:00","2025-05-14 18:00","연속"]
[626,"광주전남","직할","남광주금천#2 T/L"," 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 관형지지물(No.80) 1기 설치 ○ 연선 및 긴선 ○ 기타 : 안전이격 휴전","2025-05-12 07:00","2025-05-14 18:00","2025-05-12 07:00","2025-05-14 18:00","매일"]
[627,"광주전남","직할","남광주금천#2 T/L"," 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 관형지지물(No.80) 1기 설치 ○ 연선 및 긴선 ○ 기타 : 병가선로( 나주-금천T/L)안전이격 휴전","2025-05-09 07:00","2025-05-11 18:00","2025-05-09 07:00","2025-05-11 18:00","연속"]
[628,"광주전남","직할","나주금천#1 T/L"," 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 관형지지물(No.80) 1기 설치 ○ 연선 및 긴선 ○ 기타 : 안전이격 휴전","2025-05-09 07:00","2025-05-11 18:00","2025-05-09 07:00","2025-05-11 18:00","매일"]
[629,"광주전남","직할","나주금천#2 T/L"," 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 관형지지물(No.80) 1기 설치 ○ 연선 및 긴선 ○ 기타 : 병가선로( 남광주-금천T/L)안전이격 휴전","2025-05-06 07:00","2025-05-08 18:00","2025-05-06 07:00","2025-05-08 18:00","연속"]
[630,"광주전남","직할","남광주금천#1 T/L"," 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 관형지지물(No.80) 1기 설치 ○ 연선 및 긴선 ○ 기타 : 안전이격 휴전","2025-05-06 07:00","2025-05-08 18:00","2025-05-06 07:00","2025-05-08 18:00","매일"]
[631,"광주전남","직할","나주금천#2 T/L"," 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 관형지지물(No.80) 1기 설치 ○ 연선 및 긴선 ○ 기타 : 안전이격 휴전","2025-05-03 07:00","2025-05-05 18:00","2025-05-03 07:00","2025-05-05 18:00","매일"]
[632,"광주전남","직할","남광주금천#1 T/L"," 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 관형지지물(No.80) 1기 설치 ○ 연선 및 긴선 ○ 기타 : 병가선로( 나주-금천T/L) 안전이격 휴전","2025-05-03 07:00","2025-05-05 18:00","2025-05-03 07:00","2025-05-05 18:00","연속"]
[633,"광주전남","직할","남광주금천#1 T/L"," 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 관형지지물(No.80) 조립시행 □ 기 타 : 안전이격 휴전","2025-05-01 07:00","2025-05-02 18:00","2025-05-01 07:00","2025-05-02 18:00","매일"]
[634,"광주전남","직할","나주금천#2 T/L"," 남광주-금천T/L 지장송전선로 이설공사","□ 목적 : 고속도로 건설구간 송전선로 지장해소 □ 공사내용 ○ 관형지지물(No.80) 조립시행 □ 기 타 : 안전이격 휴전","2025-05-01 07:00","2025-05-02 18:00","2025-05-01 07:00","2025-05-02 18:00","매일"]
[635,"광주전남","직할","비아하남#2 T/L","2024 ~ 2025년 광주전남본부 직할 변전협력회사 공사","170kV GIS 차단기 조작시험","2025-05-27 09:00","2025-05-27 18:00","2025-05-27 09:00","2025-05-27 18:00","연속"]
[636,"대구","경산","신경산노변 T/L","'25년 경산전력 GIS 정밀점검공사","GIS 정밀점검","2025-05-14 09:30","2025-05-15 18:00","2025-05-14 09:30","2025-05-15 18:00","연속"]
[637,"대구","경산","신경산진량 T/L","'25년 경산전력 GIS 정밀점검공사","GIS 정밀점검","2025-05-12 09:30","2025-05-13 18:00","2025-05-12 09:30","2025-05-13 18:00","연속"]
[638,"대구","경산","신경산진량 T/L","'25년 경산전력 GIS 정밀점검공사","GIS 정밀점검(무부하 가압선로)","2025-05-20 17:00","2025-05-20 18:00","2025-05-12 09:30","2025-05-13 18:00","연속"]
[639,"대구","달성","논공현풍#1 T/L"," 논공-현풍-유가T/L OPGW 광코어 용량 증설공사","○ 논공-현풍-유가T/L OPGW 광코어 증설 - 현풍분기T/L OPGW 증설","2025-05-19 07:00","2025-05-23 18:00","2025-05-19 07:00","2025-05-23 18:00","연속"]
[640,"대구","달성","대구자인#1 T/L","2024~25년 대구본부 직할 가공송전 협력회사 공사","피뢰기 설치, 조류착지방지장치 설치, 위험표시찰 교체, 전선교체 등","2025-05-12 07:30","2025-05-14 18:00","2025-05-12 07:30","2025-05-14 18:00","연속"]
[641,"대구","달성","대구범물#2 T/L","2024~25년 대구본부 직할 가공송전 협력회사 공사","피뢰기 설치, 조류착지방지장치 설치, 위험표시찰 교체, 전선교체 등","2025-05-14 07:30","2025-05-20 18:00","2025-05-14 07:30","2025-05-20 18:00","연속"]
[642,"대구","달성","대구범물#1 T/L","2024~25년 대구본부 직할 가공송전 협력회사 공사","피뢰기 설치, 조류착지방지장치 설치, 위험표시찰 교체, 전선교체 등","2025-05-14 07:30","2025-05-20 18:00","2025-05-14 07:30","2025-05-20 18:00","연속"]
[643,"대구","달성","대구자인#2 T/L","2024~25년 대구본부 직할 가공송전 협력회사 공사","피뢰기 설치, 조류착지방지장치 설치, 위험표시찰 교체, 전선교체 등","2025-05-12 07:30","2025-05-14 18:00","2025-05-12 07:30","2025-05-14 18:00","연속"]
[644,"대구","달성","상인S/S #2 BUS","상인S/S  GIS 교체공사(3차)","○ 상인S/S  GIS 교체공사(3차) - 달성상인#2T/L, #2M.Tr 1차 GIS 교체","2025-05-21 09:00","2025-05-30 14:00","2025-05-21 09:00","2025-05-30 14:00","연속"]
[645,"대구","달성","달성상인#1 T/L","상인S/S  GIS 교체공사(3차)","○ 상인S/S  GIS 교체공사(3차) - 달성상인#2T/L, #2M.Tr 1차 GIS 교체","2025-05-07 09:00","2025-05-30 16:00","2025-05-07 09:00","2025-05-30 16:00","연속"]
[646,"대구","달성","상인봉덕#1 T/L","(무부하선로)상인S/S  GIS 교체공사(3차)","○ 상인S/S  GIS 교체공사(3차) - 달성상인#2T/L, #2M.Tr 1차 GIS 교체","2025-05-19 16:00","2025-05-20 16:00","2025-05-19 16:00","2025-05-20 16:00","연속"]
[647,"대구","달성","상인봉덕#1 T/L","(무부하선로)상인S/S  GIS 교체공사(3차)","○ 상인S/S  GIS 교체공사(3차) - 달성상인#2T/L, #2M.Tr 1차 GIS 교체","2025-05-09 14:00","2025-05-09 16:00","2025-05-09 14:00","2025-05-09 16:00","연속"]
[648,"대구","달성","서구지S/S SEC CB 65660"," GIS 정밀점검"," GIS 정밀점검","2025-05-07 09:00","2025-05-08 18:00","2025-05-07 09:00","2025-05-08 18:00","연속"]
[649,"대구","달성","고령서구지#2 T/L","[TEST] 정밀점검 관련 무부하휴전","[TEST] 정밀점검 관련 무부하휴전","2025-05-27 17:00","2025-05-27 18:00","2025-05-27 17:00","2025-05-27 18:00","연속"]
[650,"대구","달성","고령서구지#2 T/L","[TEST] 정밀점검 무부하 휴전","[TEST] 정밀점검 무부하 휴전","2025-05-08 17:00","2025-05-08 18:00","2025-05-08 17:00","2025-05-08 18:00","연속"]
[651,"대구","달성","구지서구지#1 T/L","GIS 정밀점검(양단)","GIS 정밀점검(양단)","2025-05-12 09:00","2025-05-16 18:00","2025-05-12 09:00","2025-05-16 18:00","연속"]
[652,"대구","달성","구지서구지#2 T/L","GIS 정밀점검(양단)","GIS 정밀점검(양단)","2025-05-19 09:00","2025-05-23 18:00","2025-05-19 09:00","2025-05-23 18:00","연속"]
[653,"대구","달성","성서달성#2 T/L","GIS 하자점검","GIS 하자점검","2025-05-16 09:00","2025-05-16 18:00","2025-05-24 09:00","2025-05-24 18:00","연속"]
[654,"대구","달성","성서달성#1 T/L","GIS 하자점검","GIS 하자점검","2025-05-15 09:00","2025-05-15 18:00","2025-05-10 09:00","2025-05-10 18:00","연속"]
[655,"대구","달성","현풍유가#2 T/L"," 논공-현풍-유가T/L OPGW 광코어 용량 증설공사","○ 논공-현풍-유가T/L OPGW 광코어 증설 - 현풍S/S ~ 현풍분기T/L OPGW 증설","2025-05-19 07:00","2025-05-23 18:00","2025-05-19 07:00","2025-05-23 18:00","연속"]
[656,"대구","직할","남대구동인#2 T/L","25-26년도 대구직할 지중송전 협력회사 공사","OF케이블 절연유 채유 및 채유밸브 설치","2025-05-13 09:00","2025-05-13 18:00","2025-05-13 09:00","2025-05-13 18:00","연속"]
[657,"대구","직할","범물남대구#1 T/L","25-26년도 대구직할 지중송전 협력회사 공사","EBG 가스채취 밸브 설치","2025-05-23 09:00","2025-05-23 18:00","2025-05-23 09:00","2025-05-23 18:00","연속"]
[658,"대구","직할","범물남대구#2 T/L","25-26년도 대구직할 지중송전 협력회사 공사","EBG 가스채취 밸브 설치","2025-05-24 09:00","2025-05-24 18:00","2025-05-24 09:00","2025-05-24 18:00","연속"]
[659,"대구","직할","남대구동인#1 T/L","25-26년도 대구직할 지중송전 협력회사 공사","OF케이블 절연유 채유 및 채유밸브 설치","2025-05-12 09:00","2025-05-12 18:00","2025-05-12 09:00","2025-05-12 18:00","연속"]
[660,"대구","직할","서침산침산 T/L","25-26년도 대구직할 지중송전 협력회사 공사","절연유 채유, SVL 보강 및 EBG 가스채취밸브 설치","2025-05-19 09:00","2025-05-20 18:00","2025-05-17 09:00","2025-05-18 18:00","연속"]
[661,"대구","직할","시지효목#2 T/L","25-26년도 대구직할 지중송전 협력회사 공사","피뢰기 열화진단 및 EBG 가스 채취밸브 설치","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[662,"대구","직할","시지효목#1 T/L","25-26년도 대구직할 지중송전 협력회사 공사","피뢰기 열화진단 및 EBG 가스 채취밸브 설치","2025-05-21 09:00","2025-05-21 18:00","2025-05-21 09:00","2025-05-21 18:00","연속"]
[663,"대구","칠곡","구미광평#2 T/L","광평S/S 구미-광평#2T/L LA 하자점검, 677 GIS 보통점검","광평S/S 구미-광평#2T/L LA 하자점검, 677 GIS 보통점검","2025-05-15 09:30","2025-05-15 18:00","2025-05-15 09:30","2025-05-15 18:00","연속"]
[664,"대구","칠곡","관음구암#2 T/L","24~25년 칠곡전력지사 변전협력회사 공사","627 GIS 보통점검","2025-05-08 14:00","2025-05-08 18:00","취소","취소","연속"]
[665,"대구","칠곡","서대구S/S #4 Sh.C CB","서대구S/S  GIS 하자보수공사","서대구S/S 6C22 CB 어댑터플랜지 교체작업","2025-05-13 09:00","2025-05-16 18:00","2025-05-13 09:00","2025-05-16 18:00","연속"]
[666,"대구","칠곡","서대구남인동#1 T/L","서대구S/S  GIS 하자보수","서대구S/S 6871, 6800 CB 어댑터 플랜지 교체작업","2025-05-19 09:00","2025-05-26 18:00","2025-05-19 09:00","2025-05-26 18:00","연속"]
[667,"대구","칠곡","서대구S/S #3 Sh.C CB","서대구S/S  GIS 하자보수","서대구S/S 6871 CB 어댑터 플랜지 교체작업","2025-05-23 09:00","2025-05-26 18:00","2025-05-23 09:00","2025-05-26 18:00","연속"]
[668,"대구","칠곡","서대구S/S #61 BUS","서대구S/S  GIS 하자보수","서대구S/S 6871 CB 어댑터 플랜지 교체작업","2025-05-23 09:00","2025-05-26 18:00","2025-05-23 09:00","2025-05-26 18:00","연속"]
[669,"대구","칠곡","서대구S/S #66 BUS","서대구S/S  GIS 하자보수","서대구S/S 6800 CB 어댑터 플랜지 교체작업","2025-05-19 09:00","2025-05-22 18:00","2025-05-19 09:00","2025-05-22 18:00","연속"]
[670,"대구","칠곡","서대구칠곡#1 T/L","서대구S/S  GIS 하자보수공사","서대구S/S 6C22 CB 어댑터플랜지 교체작업","2025-05-13 09:00","2025-05-16 18:00","2025-05-13 09:00","2025-05-16 18:00","연속"]
[671,"대구","칠곡","서대구S/S #4 Sh.C CB","서대구S/S  GIS 하자보수","서대구S/S 6800 CB 어댑터 플랜지 교체작업","2025-05-19 09:00","2025-05-22 18:00","2025-05-19 09:00","2025-05-22 18:00","연속"]
[672,"대구","칠곡","서대구S/S #66 BUS","서대구S/S  GIS 하자보수공사","서대구S/S 6C22 CB 어댑터플랜지 교체작업","2025-05-13 09:00","2025-05-16 18:00","2025-05-13 09:00","2025-05-16 18:00","연속"]
[673,"대구","칠곡","고아어모#2 T/L"," 고아-어모T/L No.64 안전이격확보공사"," 고아-어모T/L No.64 본선로 구성에 따른 전선 공중이동","2025-05-26 07:00","2025-05-28 18:00","2025-05-19 07:00","2025-05-21 18:00","연속"]
[674,"대구","칠곡","고아어모#1 T/L"," 고아-어모T/L No.64 안전이격확보공사"," 고아-어모T/L No.64 본선로 구성에 따른 전선 공중이동","2025-05-28 07:00","2025-05-30 18:00","2025-05-21 07:00","2025-05-23 18:00","연속"]
[675,"대구","포항","신영일천북#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","신영일-천북#1T/L 보호반 대체 677 GIS, LA 보통점검","2025-05-07 09:00","2025-05-07 18:00","취소","취소","연속"]
[676,"대구","포항","울주외동#1 T/L","2024~25년 포항전력지사 변전협력회사 공사","외동S/S 617 GIS 보통점검","2025-05-30 09:00","2025-05-30 14:00","2025-05-30 09:00","2025-05-30 14:00","연속"]
[677,"대구","포항","청하영덕#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","청하S/S 청하-영덕#1T/L GIS 보통점검","2025-05-15 09:00","2025-05-15 14:00","2025-05-15 09:00","2025-05-15 14:00","연속"]
[678,"대구","포항","청하영덕#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","청하S/S 청하-영덕#2T/L GIS 보통점검","2025-05-15 14:00","2025-05-15 18:00","2025-05-15 14:00","2025-05-15 18:00","연속"]
[679,"경북","구미","선산청리#1 T/L","2025년 구미전력지사 154㎸ GIS 정밀점검 및 보통점검 공사","- GIS 보통점검","2025-05-22 09:00","2025-05-22 18:00","2025-05-22 09:00","2025-05-22 18:00","연속"]
[680,"경북","구미","청리상주#1 T/L","2025년 구미전력지사 154㎸ GIS 정밀점검 및 보통점검 공사","- GIS 보통점검","2025-05-20 09:00","2025-05-20 18:00","2025-05-20 09:00","2025-05-20 18:00","연속"]
[681,"경북","구미","청리상주#2 T/L","2025년 구미전력지사 154㎸ GIS 정밀점검 및 보통점검 공사","- GIS 보통점검","2025-05-21 09:00","2025-05-21 18:00","2025-05-21 09:00","2025-05-21 18:00","연속"]
[682,"경북","구미","선산청리#2 T/L","2025년 구미전력지사 154㎸ GIS 정밀점검 및 보통점검 공사","- GIS 보통점검","2025-05-23 09:00","2025-05-23 18:00","2025-05-23 09:00","2025-05-23 18:00","연속"]
[683,"경북","구미","화동영동 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 화동T/L 수평추락방지장치설치","2025-05-26 07:30","2025-05-26 18:00","취소","취소","연속"]
[684,"경북","구미","화동보은 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 화동T/L 수평추락방지장치설치","2025-05-26 07:30","2025-05-30 18:00","취소","취소","연속"]
[685,"경북","영주","신영주영주#2 T/L","2024-25년 영주전력지사 변전협력회사 공사","피뢰기 하자점검","2025-05-07 13:00","2025-05-07 18:00","2025-05-07 13:00","2025-05-07 18:00","연속"]
[686,"경북","영주","신영주영주#1 T/L","2024-25년 영주전력지사 변전협력회사 공사","피뢰기 하자점검","2025-05-07 09:00","2025-05-07 13:00","2025-05-07 09:00","2025-05-07 13:00","연속"]
[687,"경북","영주","영주S/S #1 EM.Tr CB","2024-25년 영주전력지사 변전협력회사 공사","ESS 화재확산방지재 재시공","2025-05-19 09:00","2025-05-23 18:00","2025-05-19 09:00","2025-05-23 18:00","연속"]
[688,"경북","영주","신영주예천#1 T/L","24-25년 영주전력지사 변전협력회사 총액공사","신영주-예천#1T/L LA A,B,C 대체 신영주-예천#1T/L PT A 보통점검","2025-05-23 09:00","2025-05-23 18:00","취소","취소","연속"]
[689,"경북","영주","점촌문경 T/L","24-25년 영주전력지사 변전협력회사 총액공사","-점촌-문경T/L 170kV GIS 조작시험","2025-05-31 09:00","2025-05-31 18:00","2025-05-31 09:00","2025-05-31 18:00","연속"]
[690,"경북","영주","점촌단양 T/L"," 점촌-단양T/L 송전선로 정밀점검"," 점촌-단양T/L 송전선로 정밀점검","2025-05-12 08:00","2025-05-20 18:00","취소","취소","매일"]
[691,"경북","직할","안동풍산 T/L","24-25년 경북직할 송전협력회사 공사"," 안동-풍산T/L 추락방지장치 설치","2025-05-19 08:00","2025-05-27 18:00","2025-05-19 08:00","2025-05-27 18:00","매일"]
[692,"경북","직할","안동안동HP T/L","24-25년 경북직할 송전협력회사 공사"," 안동-풍산T/L 추락방지장치 설치 작업자 안전확보차","2025-05-27 09:00","2025-05-27 18:00","2025-05-27 09:00","2025-05-27 18:00","연속"]
[693,"경북","직할","군위의성#2 T/L","의성S/S  의성황학산풍력T/L 증설공사","의성S/S  의성황학산풍력T/L GIS 설치공사 - 5/12~5/14 : #1BUS, #1DS, CB 설치 - 5/15~5/16 : #60BUS 무부하가압 - 5/19~5/21 : #2BUS, #2DS, 상부BUS, CHD 설치 - 5/23~5/24 : #65BUS 무부하가압","2025-05-12 09:00","2025-05-24 18:00","2025-05-12 09:00","2025-05-24 18:00","연속"]
[694,"경북","직할","풍산동상주개폐소 T/L"," 동상주-풍산T/L 지장이설공사(가공분)"," 동상주-풍산T/L 임시이설 관련 휴전작업","2025-05-28 08:00","2025-06-05 17:00","2025-05-28 08:00","2025-06-05 17:00","연속"]
[695,"부산울산","동부산","신양산구서#1 T/L","2025년 가공송전 순시점검 위탁공사"," 구서-명장#1T/L 정밀점검 안전이격","2025-05-19 09:00","2025-05-21 18:00","2025-05-19 09:00","2025-05-21 18:00","연속"]
[696,"부산울산","동부산","신양산구서#2 T/L","2025년 가공송전 순시점검 위탁공사"," 구서-명장#2T/L 정밀점검 안전이격","2025-05-12 09:00","2025-05-14 18:00","2025-05-12 09:00","2025-05-14 18:00","연속"]
[697,"부산울산","동부산","명례장안 T/L","345kV 울주-울산TP 등 22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치","2025-05-08 07:00","2025-05-08 18:00","취소","취소","연속"]
[698,"부산울산","동부산","명장양정#2 T/L","명장S/S  GIS 교체공사","구서명장#1T/L, 명장-양정#2T/L 교체","2025-05-19 09:00","2025-06-18 18:00","2025-05-19 09:00","2025-06-18 18:00","연속"]
[699,"부산울산","동부산","명장S/S #1 BUS","명장S/S  장기사용 GIS 교체공사","구서-명장#1T/L, 명장-양정#2T/L 대체","2025-05-21 09:00","2025-05-30 18:00","2025-05-21 09:00","2025-05-30 18:00","연속"]
[700,"부산울산","동부산","구서명장#1 T/L","명장S/S  GIS 교체공사","구서명장#1T/L, 명장-양정#2T/L 교체","2025-05-19 09:00","2025-06-18 18:00","2025-05-19 09:00","2025-06-18 18:00","연속"]
[701,"부산울산","동부산","웅촌서창#2 T/L","345kV 울주-울산TP 등 22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치","2025-05-30 07:00","2025-05-30 18:00","2025-05-30 07:00","2025-05-30 18:00","연속"]
[702,"부산울산","동부산","명례장안 T/L","장안S/S  장기사용 GIS 교체공사","170kV GIS 1CCT 증설","2025-05-29 13:00","2025-05-30 18:00","2025-05-29 13:00","2025-05-30 18:00","연속"]
[703,"부산울산","동부산","명례장안 T/L","장안S/S  장기사용 GIS 교체공사","170kV GIS 1CCT 증설","2025-05-22 18:00","2025-05-23 18:00","2025-05-22 18:00","2025-05-23 18:00","연속"]
[704,"부산울산","동부산","노포정관#2 T/L","동부산전력지사  GIS 정밀점검공사","동부산전력지사  GIS 정밀점검공사 시험가압","2025-05-08 17:00","2025-05-08 18:00","2025-05-09 17:00","2025-05-09 18:00","연속"]
[705,"부산울산","동부산","좌동S/S #1 BUS","좌동S/S  장기사용 GIS 교체공사","좌동S/S  60-61-0 GIS 설치","2025-05-07 09:00","2025-05-17 18:00","2025-05-07 17:00","2025-05-17 18:00","연속"]
[706,"부산울산","동부산","좌동S/S #2 BUS","좌동S/S  장기사용 GIS 교체공사","좌동S/S  65-66-0 GIS 설치","2025-05-19 09:00","2025-05-29 18:00","2025-05-19 09:00","2025-05-29 18:00","연속"]
[707,"부산울산","동부산","좌동우동#1 T/L","좌동S/S  장기사용 GIS 교체공사","좌동S/S 좌동-우동#1T/L 인출변경","2025-05-06 09:00","2025-05-28 18:00","2025-05-06 09:00","2025-05-28 18:00","연속"]
[708,"부산울산","북부산","물금삼랑진PP#2 T/L","25년 북부산전력지사  GIS 정밀점검","물금S/S 6433GIS 주접점 교체후 시험가압선로","2025-05-21 18:00","2025-05-22 18:00","2025-05-21 18:00","2025-05-22 18:00","연속"]
[709,"부산울산","북부산","물금양산열병합#2 T/L","24-25년 북부산전력지사 변전총액공사","물금S/S  양산열병합#2T/L GIS 하자점검","2025-05-20 09:00","2025-05-20 18:00","2025-05-20 09:00","2025-05-20 18:00","연속"]
[710,"부산울산","북부산","물금양산열병합#1 T/L","24-25년 북부산전력지사 변전총액공사","물금S/S  양산열병합#1T/L GIS 하자점검","2025-05-19 09:00","2025-05-19 18:00","2025-05-19 09:00","2025-05-19 18:00","연속"]
[711,"부산울산","북부산","북부산삼랑진PP T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","○ 압축인류클램프 교체, 폴리머애자 설치 안전이격","2025-05-07 08:00","2025-05-07 18:00","취소","취소","연속"]
[712,"부산울산","북부산","북부산양산 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","○ 압축인류클램프 교체 : No.46.99(1기),○ 폴리머애자 설치 : No.43(1기)","2025-05-07 08:00","2025-05-07 18:00","취소","취소","연속"]
[713,"부산울산","북부산","서창산막#1 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","○ SB댐퍼 설치 : No.2,9,47(3기)","2025-05-12 08:00","2025-05-12 18:00","2025-05-12 08:00","2025-05-12 18:00","연속"]
[714,"부산울산","북부산","서창산막#2 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","○ 폴리머애자 설치 : No.16,79,85,86(4기), ○ SB댐퍼 설치 : No.2,9,47(3기)","2025-05-13 08:00","2025-05-15 18:00","취소","취소","연속"]
[715,"부산울산","북부산","언양산막#2 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","○ 폴리머애자 설치 안전이격","2025-05-13 08:00","2025-05-15 18:00","취소","취소","연속"]
[716,"부산울산","북부산","양산산막#2 T/L","산막S/S  장기사용 GIS 대체공사","산막S/S  양산-산막#2T/L GIS 대체","2025-05-19 09:00","2025-06-11 18:00","취소","취소","연속"]
[717,"부산울산","북부산","언양산막#2 T/L","산막S/S  장기사용 GIS 대체공사","산막S/S  양산-산막#2T/L GIS 대체 -시험가압선로","2025-05-31 18:00","2025-06-01 18:00","취소","취소","연속"]
[718,"부산울산","북부산","언양산막#2 T/L","산막S/S  장기사용 GIS 대체공사","산막S/S  양산-산막#2T/L GIS 대체 -시험가압선로","2025-05-21 17:00","2025-05-21 18:00","취소","취소","연속"]
[719,"부산울산","북부산","물금삼랑진PP#2 T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y #2S.TR 1차 GIS 정밀점검 시험가압선로","2025-05-13 17:00","2025-05-13 18:00","2025-05-13 17:00","2025-05-13 18:00","연속"]
[720,"부산울산","북부산","물금삼랑진PP#1 T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y #1S.TR 1차 GIS 정밀점검 시험가압선로","2025-05-09 17:00","2025-05-09 18:00","2025-05-09 17:00","2025-05-09 18:00","연속"]
[721,"부산울산","북부산","물금삼랑진PP#1 T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y  물금-삼랑진PP#1T/L GIS 정밀점검","2025-05-16 09:00","2025-05-17 18:00","2025-05-02 09:00","2025-05-03 18:00","연속"]
[722,"부산울산","북부산","북부산양산 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S 6200B/T GIS 정밀점검 시험가압선로","2025-05-27 17:00","2025-05-27 18:00","2025-05-27 17:00","2025-05-27 18:00","연속"]
[723,"부산울산","북부산","북부산양산 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S6 0-61-0 GIS 정밀점검 시험가압선로","2025-05-29 17:00","2025-05-29 18:00","2025-05-24 17:00","2025-05-24 18:00","연속"]
[724,"부산울산","북부산","양산삼랑진PP T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S 양산-삼랑진T/L 정밀점검","2025-05-18 09:00","2025-05-19 18:00","취소","취소","연속"]
[725,"부산울산","북부산","학장개금#2 T/L","24-25년 북부산전력지사 변전총액공사","학장S/S  학장-개금#2T/L GIS 보통점검","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[726,"부산울산","북부산","북부산호포 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","○ 압축인류클램프 교체 : No.3(1기)","2025-05-08 08:00","2025-05-08 18:00","2025-05-08 08:00","2025-05-08 18:00","연속"]
[727,"부산울산","북부산","호포물금 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","○ 압축인류클램프 교체 : No.3(1기)","2025-05-09 08:00","2025-05-09 18:00","2025-05-09 08:00","2025-05-09 18:00","연속"]
[728,"부산울산","서부산","녹공마천#1 T/L","녹공S/S  녹공-마천 #1T/L GIS동작시험","녹공S/S  녹공-마천 #1T/L GIS동작시험","2025-05-07 09:00","2025-05-07 18:00","2025-05-07 09:00","2025-05-07 18:00","연속"]
[729,"부산울산","서부산","녹공마천#2 T/L","녹공S/S  녹공-마천 #2T/L GIS동작시험","녹공S/S  녹공-마천 #2T/L GIS동작시험","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[730,"부산울산","서부산","지사미음#1 T/L"," 세산분기 지중T/L 건설사업"," XLPE 2500, 4C*1.87km  지사-미음#1,2T/L ▶  지사-세산#1,2T/L, 세산-미음#1,2T/L","2025-05-09 16:00","2025-06-12 18:00","2025-05-09 16:00","2025-06-12 18:00","연속"]
[731,"부산울산","서부산","서부산S/S CB 6200","서부산S/S #61-#66BUS-TIE GIS 동작시험","서부산S/S #61-#66BUS-TIE GIS 동작시험","2025-05-07 13:00","2025-05-07 18:00","2025-05-07 13:00","2025-05-07 18:00","연속"]
[732,"부산울산","서부산","서부산S/S CB 6100","서부산S/S #60-#65BUS-TIE GIS 동작시험","서부산S/S #60-#65BUS-TIE GIS 동작시험","2025-05-07 09:00","2025-05-07 12:00","2025-05-07 09:00","2025-05-07 12:00","연속"]
[733,"부산울산","서부산","서부산S/S #61 BUS","25년 서부산전력지사  GIS 정밀점검","#4S/T 차단부 시험가압 모선","2025-05-20 09:00","2025-05-20 18:00","2025-05-20 09:00","2025-05-20 18:00","연속"]
[734,"부산울산","서부산","서부산S/S SEC CB 60610","25년 서부산전력지사  GIS 정밀점검","#4S/T 차단부 시험가압 모선","2025-05-20 09:00","2025-05-20 18:00","2025-05-20 09:00","2025-05-20 18:00","연속"]
[735,"부산울산","서부산","서부산S/S SEC CB 60610","서부산S/S #60-#61 SEC GIS 동작시험","서부산S/S #60-#61 SEC GIS 동작시험","2025-05-08 09:00","2025-05-08 18:00","2025-05-08 09:00","2025-05-08 18:00","연속"]
[736,"부산울산","서부산","서부산S/S SEC CB 65660","서부산S/S #65-#66 SEC GIS 동작시험","서부산S/S #65-#66 SEC GIS 동작시험","2025-05-09 09:00","2025-05-09 18:00","2025-05-09 09:00","2025-05-09 18:00","연속"]
[737,"부산울산","서부산","서부산S/S #4 S/T CB","25년 서부산전력지사  GIS 정밀점검","서부산S/S  #4S/T 차단부 정밀점검","2025-05-19 09:00","2025-05-20 18:00","2025-05-19 09:00","2025-05-20 18:00","연속"]
[738,"부산울산","서부산","서부산S/S CB 6200","25년 서부산전력지사  GIS 정밀점검","#4S/T 차단부 시험가압 모선","2025-05-20 09:00","2025-05-20 18:00","2025-05-20 09:00","2025-05-20 18:00","연속"]
[739,"부산울산","서부산","신녹산용원#1 T/L","신녹산S/S 345kV #1M.Tr 증설공사"," 신녹산-명지#2T/L 철거 관련 무부하시험가압","2025-05-01 18:00","2025-05-02 18:00","취소","취소","연속"]
[740,"부산울산","서부산","신녹산용원#1 T/L","신녹산S/S 345kV #1M.Tr 증설공사"," 신녹산-명지#2T/L 철거 관련 무부하시험가압","2025-05-09 18:00","2025-05-10 18:00","취소","취소","연속"]
[741,"부산울산","울산","남울산처용#2 T/L","2025년 가공송전 순시점검 위탁공사(울산)","○345kV 울주-울산TP#1T/L 등 3개 T/L 초기점검 및 애자오염진단장치 설치 ○ 대상 - 345kV 울주-울산TP#1T/L 9~14호 - 345kV 남울산-울산TP#2T/L 8,9,S/T -  남울산-처용#2T/L S/T~6호 ○ 안전이격확보 -  성암-울산TP#1T/L","2025-05-07 08:00","2025-05-08 18:00","2025-05-07 08:00","2025-05-08 18:00","연속"]
[742,"부산울산","울산","반천언양#1 T/L","345kV 울주-울산TP 등 22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치","2025-05-16 07:00","2025-05-16 18:00","2025-05-16 07:00","2025-05-16 12:00","연속"]
[743,"부산울산","울산","산하방어진#1 T/L","방어진S/S 송전선로 인출입부 마감재 탈락관련 공사시행","방어진S/S 산하-방어진TL인근 외벽 마감재 탈락관련 공사시행","2025-05-02 09:00","2025-05-02 18:00","취소","취소","연속"]
[744,"부산울산","울산","방어진영남TP#2 T/L","25년 울산전력지사 개폐장치 정밀점검 공사","GIS 정밀점검","2025-05-26 09:00","2025-05-27 18:00","2025-05-26 09:00","2025-05-27 18:00","연속"]
[745,"부산울산","울산","방어진영남TP#1 T/L","25년 울산전력지사 개폐장치 정밀점검 공사","GIS 정밀점검","2025-05-28 09:00","2025-05-29 18:00","2025-05-28 09:00","2025-05-29 18:00","연속"]
[746,"부산울산","울산","성암울산TP#2 T/L","25년 울산전력지사 변전협력회사 공사","- GIS 보통점검","2025-05-15 09:00","2025-05-15 18:00","2025-05-15 09:00","2025-05-15 18:00","연속"]
[747,"부산울산","울산","신울산명례#1 T/L","동부산전력 가공송전협력회사 공사","금구류 및 추락방지장치 설치","2025-05-13 07:00","2025-05-14 18:00","취소","취소","연속"]
[748,"부산울산","울산","신울산명례#2 T/L","동부산전력 가공송전협력회사 공사","금구류 및 추락방지장치 설치","2025-05-15 07:00","2025-05-16 18:00","취소","취소","연속"]
[749,"부산울산","울산","신울산태화#1 T/L","신울산-옥동-울주간 OPGW 증설공사","신울산-옥동-울주간 OPGW 교체 및 시설 : 21.7km","2025-05-23 08:00","2025-05-25 18:00","2025-05-23 08:00","2025-05-25 18:00","연속"]
[750,"부산울산","울산","신울산웅촌#1 T/L","신울산-옥동-울주간 OPGW 증설공사","신울산-옥동-울주간 OPGW 교체 및 시설 : 21.7km","2025-05-05 08:00","2025-05-07 18:00","취소","취소","연속"]
[751,"부산울산","울산","신울산옥동#2 T/L","신울산-옥동-울주간 OPGW 증설공사","신울산-옥동-울주간 OPGW 교체 및 시설 : 21.7km","2025-05-01 08:00","2025-05-07 18:00","2025-05-01 08:00","2025-05-07 18:00","연속"]
[752,"부산울산","울산","언양산막#2 T/L","345kV 울주-울산TP 등 22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치( 반천-언양#1 휴전 관련 안전이격확보차)","2025-05-16 07:00","2025-05-16 18:00","2025-05-16 07:00","2025-05-16 18:00","연속"]
[753,"부산울산","울산","옥동외동#2 T/L","신울산-옥동-울주간 OPGW 증설공사","신울산-옥동-울주간 OPGW 교체 및 시설 : 21.7km","2025-05-15 08:00","2025-05-25 18:00","2025-05-15 08:00","2025-05-25 18:00","연속"]
[754,"부산울산","울산","신온산온산#2 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#2T/L 철거 및 임시BUS TIE 설치","2025-05-07 09:00","2025-09-30 18:00","취소","취소","연속"]
[755,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#2T/L 철거 및 임시BUS TIE 설치","2025-05-16 16:00","2025-05-17 16:00","2025-05-16 16:00","2025-05-17 16:00","연속"]
[756,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#2T/L 철거 및 임시BUS TIE 설치","2025-05-23 16:00","2025-05-24 16:00","2025-05-23 16:00","2025-05-24 16:00","연속"]
[757,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#2T/L 철거 및 임시BUS TIE 설치","2025-05-29 16:00","2025-05-30 17:00","2025-05-29 16:00","2025-05-30 17:00","연속"]
[758,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#2T/L 철거 및 임시BUS TIE 설치","2025-05-09 16:00","2025-05-09 17:00","2025-05-09 16:00","2025-05-09 17:00","연속"]
[759,"부산울산","울산","성암울산TP#1 T/L","2025년 가공송전 순시점검 위탁공사(울산)","○345kV 울주-울산TP#1T/L 등 3개 T/L 초기점검 및 애자오염진단장치 설치 ○ 대상 - 345kV 울주-울산TP#1T/L 9~14호 - 345kV 남울산-울산TP#2T/L 8,9,S/T -  남울산-처용#2T/L S/T~6호 ○ 안전이격확보 -  성암-울산TP#1T/L","2025-05-07 08:00","2025-05-09 18:00","2025-05-07 08:00","2025-05-09 18:00","연속"]
[760,"부산울산","울산","울주외동#2 T/L","25년 울산전력지사 변전협력회사 공사","- 6B2 가스누기 조치작업 - LA 보통점검","2025-05-13 09:00","2025-05-13 18:00","2025-05-21 09:00","2025-05-22 18:00","연속"]
[761,"부산울산","울산","울주외동#1 T/L","신울산-옥동-울주간 OPGW 증설공사","신울산-옥동-울주간 OPGW 교체 및 시설 : 21.7km","2025-05-08 08:00","2025-05-15 18:00","2025-05-08 08:00","2025-05-15 18:00","연속"]
[762,"부산울산","울산","울주입실#1 T/L","신울산-옥동-울주간 OPGW 증설공사","신울산-옥동-울주간 OPGW 교체 및 시설 : 21.7km","2025-05-08 08:00","2025-05-10 18:00","2025-05-08 08:00","2025-05-10 18:00","연속"]
[763,"부산울산","울산","울주직동#2 T/L","345kV 울주-울산TP 등 22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치(345kV 울주-울산TP#1 휴전 관련 안전이격확보차)","2025-05-07 07:00","2025-05-09 18:00","2025-05-07 07:00","2025-05-09 18:00","연속"]
[764,"부산울산","울산","울주직동#1 T/L","345kV 울주-울산TP 등 22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치(345kV 울주-울산TP#2 휴전 관련 안전이격확보차)","2025-05-27 07:00","2025-05-29 18:00","2025-05-27 07:00","2025-05-29 18:00","연속"]
[765,"부산울산","울산","신울산웅촌#2 T/L","25년 울산전력지사 변전협력회사 공사","- 세니온제 보호 IED 성능개선 - 차단기 동작시험","2025-05-08 09:00","2025-05-08 18:00","취소","취소","연속"]
[766,"부산울산","울산","직동반천#1 T/L","345kV 울주-울산TP 등 22개T/L 송전철탑 정비공사","폴리머점퍼지지애자 설치(345kV 울주-울산TP#2 휴전 관련 안전이격확보차)","2025-05-26 07:00","2025-05-26 18:00","2025-05-26 07:00","2025-05-26 18:00","연속"]
[767,"부산울산","울산","직동반천#2 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 설치","2025-05-29 07:00","2025-05-29 18:00","취소","취소","연속"]
[768,"부산울산","울산","온산처용#1 T/L","25년 울산전력지사 변전협력회사 공사","- 처용S/S GIS 보통점검","2025-05-21 09:00","2025-05-21 18:00","2025-05-21 09:00","2025-05-21 18:00","연속"]
[769,"부산울산","울산","효문방어진 T/L"," 효문S/S GIS 교체공사"," 방어진-효문T/L(617) GIS 교체. 끝.","2025-05-06 09:00","2025-05-23 18:00","2025-05-07 09:00","2025-05-21 18:00","연속"]
[770,"부산울산","직할","우동대연 T/L","24~25년 서부산전력지사 가공송전협력회사 공사","우동-대연T/L 13호 태풍취약철탑 보강","2025-05-18 13:00","2025-05-18 18:00","2025-05-18 13:00","2025-05-18 18:00","연속"]
[771,"부산울산","직할","정보대연 T/L","24~25년 서부산전력지사 가공송전협력회사 공사","정보-대연T/L 태풍취약철탑 보강","2025-05-18 08:00","2025-05-18 13:00","2025-05-18 08:00","2025-05-18 13:00","연속"]
[772,"부산울산","직할","신대연양정#2 T/L","24~25년 직할 변전협력회사 총액공사","신대연S/S  신대연-양정#2T/L 보호PNL 대체","2025-05-07 09:30","2025-05-09 18:00","2025-05-07 09:30","2025-05-09 18:00","연속"]
[773,"경남","김해송변전부","김해어방#1 T/L","김해S/S  BUS-TIE GIS 정밀점검(시험가압용)","김해S/S  BUS-TIE GIS 정밀점검(시험가압용)","2025-05-31 16:00","2025-05-31 18:00","2025-05-31 16:00","2025-05-31 18:00","연속"]
[774,"경남","김해송변전부","김해어방#1 T/L","김해S/S #3M.Tr 1차 GIS 정밀점검(시험가압용)","김해S/S #3M.Tr 1차 GIS 정밀점검(시험가압용)","2025-05-23 16:00","2025-05-23 18:00","2025-05-23 16:00","2025-05-23 18:00","연속"]
[775,"경남","김해송변전부","김해S/S CB 6100","김해S/S  BUS-TIE GIS 정밀점검","김해S/S  BUS-TIE GIS 정밀점검","2025-05-30 08:00","2025-05-31 18:00","2025-05-30 08:00","2025-05-31 18:00","연속"]
[776,"경남","김해송변전부","김해어방#2 T/L","김해S/S  BUS-TIE GIS 정밀점검(일시절체용)","김해S/S  BUS-TIE GIS 정밀점검(일시절체용) - BUS TIE GIS 정밀점검중이기 때문에 모선절체 불가 / 시험가압 조작전, 모선 절체를 위한 차단기 일시개방","2025-05-31 15:00","2025-05-31 16:00","2025-05-31 15:00","2025-05-31 16:00","연속"]
[777,"경남","김해송변전부","삼계어방#1 T/L"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-05-11 07:00","2025-05-11 18:00","2025-05-11 07:00","2025-05-11 18:00","연속"]
[778,"경남","김해송변전부","한림정삼계#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","피뢰기 설치 공사","2025-05-03 07:00","2025-05-04 18:00","2025-05-03 07:00","2025-05-04 18:00","매일"]
[779,"경남","김해송변전부","삼계어방#2 T/L"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사"," 마천-진해TL 16개T/L 추락방지장치 설치 및 교체공사","2025-05-11 07:00","2025-05-11 18:00","2025-05-11 07:00","2025-05-11 18:00","연속"]
[780,"경남","김해송변전부","신김해진례#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치및 지지애자교체 공사 안전이격","2025-05-24 07:00","2025-05-24 18:00","2025-05-24 07:00","2025-05-24 18:00","연속"]
[781,"경남","김해송변전부","신김해지사#1 T/L","24-25년 가공송전 협력회사 총액공사(직할)","피뢰기 설치(신김해 장유#1T/L 6~13호) 안전이격","2025-05-17 07:00","2025-05-17 18:00","취소","취소","연속"]
[782,"경남","김해송변전부","신김해진례#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","추락방지장치및 지지애자교체 공사 안전이격","2025-05-18 07:00","2025-05-18 18:00","2025-05-18 07:00","2025-05-18 18:00","연속"]
[783,"경남","김해송변전부","김해어방#2 T/L","어방S/S 김해-어방#2T/L GIS 보통점검","어방S/S 김해-어방#2T/L GIS 보통점검","2025-05-25 13:30","2025-05-25 17:30","2025-05-25 13:30","2025-05-25 17:30","연속"]
[784,"경남","김해송변전부","김해어방#1 T/L","어방S/S 김해-어방#1T/L GIS 조작시험","어방S/S 김해-어방#1T/L GIS 조작시험","2025-05-25 09:30","2025-05-25 13:30","2025-05-25 09:30","2025-05-25 13:30","연속"]
[785,"경남","김해송변전부","장유마천#2 T/L","24-25년 가공송전 협력회사 총액공사(직할)","피뢰기 설치(신김해 장유#1T/L 6~13호) 안전이격","2025-05-17 13:00","2025-05-17 18:00","2025-05-17 13:00","2025-05-17 18:00","연속"]
[786,"경남","김해송변전부","장유마천#1 T/L","24-25년 가공송전 협력회사 총액공사(직할)","피뢰기 설치(신김해 장유#1T/L 6~13호) 안전이격","2025-05-17 07:00","2025-05-17 13:00","2025-05-17 07:00","2025-05-17 13:00","연속"]
[787,"경남","김해송변전부","주촌삼계#1 T/L","주촌S/S 주촌-삼계#1T/L 제어IED 교체공사","주촌S/S 주촌-삼계#1T/L 제어IED 교체공사","2025-05-12 09:30","2025-05-12 17:30","취소","취소","연속"]
[788,"경남","김해송변전부","신김해주촌#1 T/L","주촌S/S 신김해-주촌#1T/L 제어IED 교체공사","주촌S/S 신김해-주촌#1T/L 제어IED 교체공사","2025-05-14 09:30","2025-05-14 17:30","취소","취소","연속"]
[789,"경남","김해송변전부","주촌삼계#2 T/L","주촌S/S 주촌-삼계#2T/L 제어IED 교체공사","주촌S/S 주촌-삼계#2T/L 제어IED 교체공사","2025-05-13 09:30","2025-05-13 17:30","취소","취소","연속"]
[790,"경남","김해송변전부","진례진영#1 T/L","진영S/S 진례-진영#1T/L GIS 보통점검","진영S/S 진례-진영#1T/L GIS 보통점검","2025-05-10 09:30","2025-05-10 17:30","2025-05-10 09:30","2025-05-10 17:30","연속"]
[791,"경남","김해송변전부","진영한림정#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사","피뢰기 설치 공사 안전이격","2025-05-03 07:00","2025-05-03 18:00","2025-05-03 07:00","2025-05-03 18:00","연속"]
[792,"경남","직할","녹공마천#1 T/L"," 녹공-마천T/L 피뢰기 열화진단","지중송전협력회사 피뢰기 열화진단 시행","2025-05-30 09:00","2025-05-30 18:00","2025-05-30 09:00","2025-05-30 18:00","연속"]
[793,"경남","직할","신월삼정#2 T/L","24~25년 경남본부 직할 송전협력회사 공사"," 신월-삼정T/L 점퍼지지애자 설치  신월-동읍T/L #2T/L 피뢰기 설치 안전이격","2025-05-10 07:00","2025-05-10 18:00","취소","취소","연속"]
[794,"경남","직할","신월동읍#2 T/L","24~25년 경남본부 직할 송전협력회사 공사"," 신월-동읍T/L 점퍼지지애자 교체 및 설치, 피뢰기 설치  신월-삼정T/L 점퍼지지애자 교체 안전이격(5/11)","2025-05-08 07:00","2025-05-14 18:00","2025-05-08 07:00","2025-05-14 18:00","매일"]
[795,"경남","직할","신월삼정#1 T/L","24~25년 경남본부 직할 송전협력회사 공사"," 신월-삼정T/L 점퍼지지애자 교체 및 설치(5/11)  신월-동읍T/L #2T/L 피뢰기 설치 안전이격(5/10)","2025-05-10 07:00","2025-05-11 18:00","취소","취소","매일"]
[796,"경남","직할","신월동읍#1 T/L","24~25년 경남본부 직할 송전협력회사 공사"," 신월-삼정 #1T/L 점퍼지지애자 교체 안전이격","2025-05-11 07:00","2025-05-11 18:00","2025-05-11 07:00","2025-05-11 18:00","연속"]
[797,"경남","직할","신월동읍#1 T/L","24~25년 경남본부 직할 송전협력회사 공사"," 신월-동읍T/L 점퍼지지애자 교체 및 설치","2025-05-15 07:00","2025-05-16 18:00","2025-05-15 07:00","2025-05-16 18:00","매일"]
[798,"경남","직할","안민천선#2 T/L","안민S/S 안민-천선#2T/L 보통점검","안민S/S 안민-천선#2T/L 보통점검","2025-05-17 09:00","2025-05-17 18:00","2025-05-17 09:00","2025-05-17 18:00","연속"]
[799,"경남","직할","월림S/S CB 6100","월림S/S 170kV GIS 대체공사","월림S/S 170kV GIS 대체공사","2025-05-07 09:00","2025-06-01 18:00","취소","취소","연속"]
[800,"경남","직할","창공월림#2 T/L","월림S/S 170kV GIS 대체공사","월림S/S 170kV GIS 대체공사","2025-05-07 09:00","2025-06-04 18:00","2025-05-07 09:00","2025-06-04 18:00","연속"]
[801,"경남","직할","천선S/S SEC CB 60610","천선S/S #60-61 BUS SEC GIS 유압카운터 교체","천선S/S #60-61 BUS SEC GIS 유압카운터 교체","2025-05-16 09:00","2025-05-16 18:00","2025-05-16 09:00","2025-05-16 18:00","연속"]
[802,"경남","진주","사천개양#1 T/L","개양S/S  사천-개양#1T/L GIS 정밀점검","개양S/S  사천-개양#1T/L GIS 정밀점검","2025-05-31 09:00","2025-06-01 18:00","2025-05-31 09:00","2025-06-01 18:00","연속"]
[803,"경남","진주","함양거창#1 T/L","거창S/S  함양-거창#1T/L GIS 조작시험 및 LA 하자","거창S/S  함양-거창#1T/L GIS 조작시험 및 LA 하자점검","2025-05-08 10:00","2025-05-08 17:00","취소","취소","연속"]
[804,"경남","진주","가야사봉#1 T/L","사봉S/S  가야-사봉#1T/L GIS 정밀점검","사봉S/S  가야-사봉#1T/L GIS 정밀점검","2025-05-17 09:00","2025-05-18 18:00","2025-05-17 09:00","2025-05-18 18:00","연속"]
[805,"경남","진주","의령동진주#1 T/L","2025년 가공송전 순시점검 위탁공사"," 의령-함양T/L 의령S/T~함양S/T(132기) 정밀점검 작업자 안전이격거리 확보","2025-05-19 09:00","2025-05-20 18:00","2025-05-19 09:00","2025-05-20 18:00","매일"]
[806,"경남","진주","진주개양#2 T/L","진주S/S  진주-개양#2T/L GIS 하자점검","진주S/S  진주-개양#2T/L GIS 하자점검","2025-05-28 10:00","2025-05-28 17:00","2025-05-28 10:00","2025-05-28 17:00","연속"]
[807,"경남","진주","동진주진주#2 T/L","진주S/S  동진주-진주#2T/L GIS 하자점검","진주S/S  동진주-진주#2T/L GIS 하자점검","2025-05-14 10:00","2025-05-14 17:00","2025-05-14 10:00","2025-05-14 17:00","연속"]
[808,"경남","진주","진주개양#1 T/L","진주S/S  진주-개양#1T/L GIS 하자점검","진주S/S  진주-개양#1T/L GIS 하자점검","2025-05-15 10:00","2025-05-15 17:00","2025-05-15 10:00","2025-05-15 17:00","연속"]
[809,"경남","진주","동진주진주#1 T/L","진주S/S  동진주-진주#1T/L GIS 하자점검","진주S/S  동진주-진주#1T/L GIS 하자점검","2025-05-13 10:00","2025-05-13 17:00","2025-05-13 10:00","2025-05-13 17:00","연속"]
[810,"경남","진주","태금하동화력 T/L","하동S/S 맵보드 제어케이블 철거작업","하동S/S 맵보드 제어케이블 철거작업","2025-05-12 10:00","2025-05-12 15:00","2025-05-12 10:00","2025-05-12 15:00","연속"]
[811,"경남","진주","하동정촌#1 T/L","하동S/S 맵보드 제어케이블 철거작업","하동S/S 맵보드 제어케이블 철거작업","2025-05-14 10:00","2025-05-14 14:00","2025-05-16 10:00","2025-05-16 14:00","연속"]
[812,"경남","진주","하동정촌#2 T/L","하동S/S 맵보드 제어케이블 철거작업","하동S/S 맵보드 제어케이블 철거작업","2025-05-14 14:00","2025-05-14 17:00","2025-05-16 14:00","2025-05-16 18:00","연속"]
[813,"경남","진주","광양하동#1 T/L","하동S/S 맵보드 제어케이블 철거작업","하동S/S 맵보드 제어케이블 철거작업","2025-05-15 10:00","2025-05-15 14:00","2025-05-15 10:00","2025-05-15 14:00","연속"]
[814,"경남","진주","광양하동#2 T/L","하동S/S 맵보드 제어케이블 철거작업","하동S/S 맵보드 제어케이블 철거작업","2025-05-15 14:00","2025-05-15 17:00","2025-05-15 14:00","2025-05-15 17:00","연속"]
[815,"경남","진주","의령함양 T/L","2025년 가공송전 순시점검 위탁공사"," 의령-함양T/L 의령S/T~함양S/T(132기) 정밀점검","2025-05-19 09:00","2025-05-30 18:00","취소","취소","매일"]
[816,"경남","진주","산청함양 T/L","2025년 가공송전 순시점검 위탁공사","- 지지물 86기(의령-함양T/L 69기, 산청분기 17기), 긍장 : 27.381km","2025-05-12 08:00","2025-05-18 18:00","취소","취소","매일"]
[817,"경남","진주","거창합천#2 T/L","합천S/S  #2M.Tr 1차 GIS 정밀점검 무부하시험가압","합천S/S  #2M.Tr 1차 GIS 정밀점검 무부하시험가압","2025-05-14 17:00","2025-05-14 18:00","취소","취소","연속"]
[818,"경남","통영","거류거제#1 T/L"," 거류-거제T/L 추락방지장치 설치공사"," 거류-거제T/L 추락방지장치 설치공사","2025-05-03 07:00","2025-05-04 18:00","2025-05-03 07:00","2025-05-04 18:00","매일"]
[819,"경남","통영","거류거제#2 T/L"," 거류-거제T/L 추락방지장치 설치공사"," 거류-거제T/L 추락방지장치 설치공사","2025-05-10 07:00","2025-05-11 18:00","2025-05-10 07:00","2025-05-11 18:00","매일"]
[820,"경남","통영","거류거제#2 T/L"," 거류-거제T/L 추락방지장치 설치공사"," 거류-거제T/L 추락방지장치 설치공사","2025-05-17 07:00","2025-05-18 18:00","2025-05-17 07:00","2025-05-18 18:00","매일"]
[821,"경남","통영","거류거제#2 T/L"," 거류-거제T/L 추락방지장치 설치공사"," 거류-거제T/L 추락방지장치 설치공사","2025-05-24 07:00","2025-05-25 18:00","2025-05-24 07:00","2025-05-25 18:00","매일"]
[822,"경남","통영","삼천포사천#2 T/L"," 삼천포사천 T/L 애자성능 및 성능저하 애자교체"," 삼천포사천 T/L 애자성능 및 성능저하 애자교체","2025-05-07 07:00","2025-05-08 18:00","2025-05-07 07:00","2025-05-08 18:00","매일"]
[823,"경남","통영","사천개양#1 T/L"," 사천-개양 T/L 애자성능 및 성능저하 애자교체"," 사천-개양 T/L 애자성능 및 성능저하 애자교체","2025-05-07 07:00","2025-05-09 18:00","2025-05-07 07:00","2025-05-09 18:00","매일"]
[824,"경남","통영","신고성삼천포#2 T/L"," 신고성-삼천포#2T/L GIS 조작시험 및 보통점검"," 신고성-삼천포#2T/L GIS 조작시험 및 보통점검 (신고성S/S : 조작시험, 삼천포S/S : 보통점검)","2025-05-10 09:30","2025-05-10 18:00","취소","취소","연속"]
[825,"경남","통영","신고성삼천포#1 T/L"," 신고성-삼천포#1T/L GIS 조작시험 및 보통점검"," 신고성-삼천포#1T/L GIS 조작시험 및 보통점검 (신고성S/S : 조작시험, 삼천포S/S : 보통점검)","2025-05-24 09:30","2025-05-24 18:00","2025-05-24 09:30","2025-05-24 18:00","연속"]
[826,"경남","통영","신고성거류#3 T/L"," 신고성-거류#3 T/L 추락방지장치 설치공사"," 신고성-거류#3 T/L 추락방지장치 설치공사","2025-05-26 07:00","2025-05-30 18:00","2025-05-26 07:00","2025-05-30 18:00","매일"]
[827,"경남","통영","신고성고성 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성분기T/L 추락방지장치 설치공사","2025-05-31 07:00","2025-05-31 18:00","2025-05-31 07:00","2025-05-31 18:00","연속"]
[828,"경남","통영","통영거제#1 T/L"," 통영-거제#1T/L GIS 보통점검"," 통영-거제#1T/L GIS 보통점검(통영, 거제S/S)","2025-05-31 09:30","2025-05-31 18:00","2025-05-31 09:30","2025-05-31 18:00","연속"]
[829,"경남","통영","고성통영CC#1 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성분기T/L 추락방지장치 설치공사","2025-05-31 07:00","2025-05-31 18:00","2025-05-31 07:00","2025-05-31 18:00","연속"]
[830,"경남","함안","가야사봉#2 T/L"," 가야-사봉#1,2T/L 수평형 추락방지장치 설치"," 가야-사봉#1,2T/L 1~13호 수평형 추락방지장치 설치","2025-05-10 07:00","2025-05-11 18:00","2025-05-10 07:00","2025-05-11 18:00","매일"]
[831,"경남","함안","가야사봉#1 T/L"," 가야-사봉#1,2T/L 수평형 추락방지장치 설치"," 가야-사봉#1,2T/L 1~13호 수평형 추락방지장치 설치","2025-05-10 07:00","2025-05-11 18:00","2025-05-10 07:00","2025-05-11 18:00","매일"]
[832,"경남","함안","초동밀양#2 T/L","밀양S/S  초동밀양#2 T/L GIS 보통점검","밀양S/S  초동밀양#2 T/L GIS 보통점검","2025-05-21 09:30","2025-05-21 17:30","2025-05-21 09:30","2025-05-21 17:30","연속"]
[833,"경남","함안","초동수산#1 T/L"," 수산-초동#1T/L 정밀점검"," 수산-초동#1T/L 1~13호 정밀점검(13기)","2025-05-12 07:00","2025-05-13 18:00","2025-05-12 07:00","2025-05-13 18:00","매일"]
[834,"경남","함안","초동수산#2 T/L"," 수산-초동#2T/L 정밀점검"," 수산-초동#2T/L 1~13호 정밀점검(13기)","2025-05-14 07:00","2025-05-15 18:00","2025-05-14 07:00","2025-05-15 18:00","매일"]
[835,"경남","함안","진영수산#2 T/L"," 진영-수산#2T/L 정밀점검"," 진영-수산#2T/L 61호 정밀점검 ( 수산-초동#2T/L 1호 병행)","2025-05-14 07:00","2025-05-14 18:00","2025-05-14 07:00","2025-05-14 18:00","연속"]
[836,"경남","함안","진영수산#1 T/L"," 진영-수산#1T/L 정밀점검"," 진영-수산#1T/L 61호 정밀점검 ( 수산-초동#1T/L 1호 병행)","2025-05-12 07:00","2025-05-12 18:00","2025-05-12 07:00","2025-05-12 18:00","연속"]
[837,"경남","함안","신마산중리#1 T/L","항공장애구 설치공사","신마산-중리T/L 19~20호 구간(11개 설치)","2025-05-15 07:00","2025-05-15 18:00","취소","취소","연속"]
[838,"경남","함안","신마산중리#2 T/L","항공장애구 설치공사","신마산-중리T/L 19~20호 구간(11개 설치)","2025-05-15 07:00","2025-05-15 18:00","취소","취소","연속"]
[839,"경남","함안","창녕초동#2 T/L","초동S/S  창녕초동#2 T/L GIS 보통점검","초동S/S  창녕초동#2 T/L GIS 보통점검","2025-05-28 09:30","2025-05-28 17:30","2025-05-28 09:30","2025-05-28 17:30","연속"]
[840,"경남","함안","초동밀양#1 T/L","초동S/S  초동밀양#1 T/L GIS 보통점검","초동S/S  초동밀양#1 T/L GIS 보통점검","2025-05-27 09:30","2025-05-27 17:30","2025-05-27 09:30","2025-05-27 17:30","연속"]
[841,"경남","함안","창녕초동#1 T/L","초동S/S  창녕초동#1 T/L GIS 보통점검","초동S/S  창녕초동#1 T/L GIS 보통점검","2025-05-29 09:30","2025-05-29 17:30","2025-05-29 09:30","2025-05-29 17:30","연속"]