{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":23,"n_cols":12,"rows_kept":23,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2025년도 8월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신안성신가평 T/L"," 신안성-신가평 등 12개T/L 추락방지시설 설치공사"," 신안성-신가평T/L 고광도 항공장애등 설치 : No.131,132,146,147","2025-08-04 07:00","2025-08-08 18:00","취소","취소","연속"]
[2,"부산울산","동부산","신고리N/P #1 M.Tr","2025년 하반기 신고리S/S  GIS 정밀보통점검 공사","8471CB 정밀점검 및 시험가압","2025-08-26 09:00","2025-09-05 18:00","2025-08-26 09:00","2025-09-05 18:00","연속"]
{"$rows_empty":16}
[{"$nulls":5}," "]

{"sheet":"345설비","index":1,"n_rows":87,"n_cols":12,"rows_kept":87,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2025년도 8월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","강남","신양재S/S #2 BUS","24-25년도 강남전력지사 변전협력회사 총액공사"," 노후 CT집합반 교체","2025-08-18 14:00","2025-08-18 19:00","2025-08-16 08:00","2025-08-16 19:00","연속"]
[2,"남서울","강남","신양재S/S #1 BUS","24-25년도 강남전력지사 변전협력회사 총액공사"," 노후 CT집합반 교체","2025-08-19 10:00","2025-08-19 18:00","2025-08-17 08:00","2025-08-17 19:00","연속"]
[3,"남서울","강남","신양재S/S #1 BUS","24-25년도 강남전력지사 변전협력회사 총액공사"," 노후 CT집합반 교체","2025-08-18 09:00","2025-08-18 14:00","2025-08-15 09:00","2025-08-15 14:00","연속"]
[4,"남서울","동서울","동서울S/S #2 Sh.R CB","24-25년도 동서울전력지사 변전협력회사 총액공사","동서울S/S #2Sh.R 보통점검 및 인출 CB 정밀점검(7079)","2025-08-18 09:00","2025-08-22 18:00","2025-08-18 09:00","2025-08-22 18:00","연속"]
[5,"남서울","영등포","서서울신광명#1 T/L"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사 1식","2025-08-04 09:00","2025-09-30 18:00","취소","취소","연속"]
[6,"남서울","직할","신문래S/S #3 Sh.R CB","신문래S/S  #3Sh.R 유순환펌프 교체","신문래S/S  #3Sh.R 유순환펌프 교체","2025-08-25 09:00","2025-08-29 18:00","2025-08-25 09:00","2025-08-29 18:00","연속"]
[7,"경기북부","고양","신파주S/S SVC TR CB","신파주S/S  SVC C.Tr 정밀점검공사","□ 신파주S/S  SVC C.Tr 정밀점검공사 - 공사기간: 2025. 08. 18(월) ~ 2025. 08. 29(금) - 작업대상:  SVC C.Tr 3대(A, B, C상) - 작업내용:  변압기 정밀점검","2025-08-18 09:00","2025-08-29 18:00","2025-08-18 09:00","2025-08-29 18:00","연속"]
[8,"경기북부","직할","신포천동두천CC#1 T/L","동두천C/C  동두천CC-양주T/L SW증설공사","- 동두천CC 362kV 2CB 증설 - 인출 GIB 설치 - 기기 기초 및 기타부대공사","2025-08-01 09:00","2025-11-28 18:00","2025-08-01 09:00","2025-11-28 18:00","연속"]
[9,"경기북부","직할","신덕은동두천CC#1 T/L","동두천C/C  동두천CC-양주T/L SW증설공사","- 동두천CC 362kV 2CB 증설 - 인출 GIB 설치 - 기기 기초 및 기타부대공사","2025-08-18 09:00","2025-09-12 18:00","2025-08-18 09:00","2025-09-12 18:00","연속"]
[10,"경기","성남","신성남S/S CB 7671","25년 성남전력지사 변전협력회사 총액공사","신성남) 7671GIS 절연열화 재측정","2025-08-26 09:00","2025-08-26 14:00","2025-08-26 09:00","2025-08-26 14:00","연속"]
[11,"경기","평택","고덕#2S/S #2 BUS","고덕#2S/S #4M.Tr 증설공사(#75BUS)"," 모선보호반 CT 케이블 이설 및  GIS 인터록시험","2025-08-18 09:00","2025-08-20 18:00","2025-09-02 09:00","2025-09-05 18:00","연속"]
[12,"강원","강릉","동해안인개폐소#1 T/L","2025년 강릉전력지사 변전협력회사 공사","안인개폐소 71BAY B/F반 단자 교체","2025-08-19 10:00","2025-08-19 18:00","2025-08-19 10:00","2025-08-19 18:00","연속"]
[13,"강원","강릉","안인개폐소양양PP T/L","2025년 강릉전력지사 변전협력회사 공사","SPS PNL 준공시험","2025-08-18 10:00","2025-08-19 18:00","2025-08-18 10:00","2025-08-19 18:00","연속"]
[14,"강원","강릉","신양양양양PP T/L","2025년 강릉전력지사 변전협력회사 공사","SPS PNL 준공시험","2025-08-20 10:00","2025-08-22 18:00","2025-08-20 10:00","2025-08-22 18:00","연속"]
[15,"충북","청주","세종남청주#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 하자점검(7671,7600) CVT 점검","2025-08-25 10:00","2025-08-26 18:00","2025-08-25 10:00","2025-08-26 18:00","연속"]
[16,"대전세종충남","대전","신계룡청양 T/L","[송전][오전만][즉시가압O] 신옥천-청양 등 추락방지설치공사","[송전][오전만][즉시가압O] 신옥천-청양 등 추락방지설치공사","2025-08-18 07:00","2025-08-22 18:00","2025-08-18 07:00","2025-08-22 18:00","매일"]
[17,"대전세종충남","서산","북당진현대제철 T/L"," 신송산분기T/L 건설공사","No.70 전선 이동(가철탑→본철탑) No.69∼No.71 전선 교체","2025-08-18 07:00","2025-08-30 18:00","취소","취소","연속"]
[18,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~126(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 교차선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청 * 7월 휴전 승인시 취소 요청","2025-08-01 13:00","2025-08-01 18:00","취소","취소","연속"]
[19,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-북당진T/L 병가 및  신당진개폐소-현대제철 교차구간,  신당진개폐소-북당진T/L 및 신당진개폐소-현대제철 모두 휴전 미승인시 휴전 취소 요청 * 7월 휴전 승인시 취소 요청","2025-08-01 08:00","2025-08-01 18:00","취소","취소","연속"]
[20,"대전세종충남","서산","신당진개폐소북당진 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.126~127(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 병가선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청 * 7월 휴전 승인시 취소 요청","2025-08-01 08:00","2025-08-01 13:00","취소","취소","연속"]
[21,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","24~25 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-현대제철T/L 병가선로,  신당진개폐소-현대제철T/L 휴전 미승인시 휴전 취소 요청 * 7월 휴전 승인시 취소 요청","2025-08-04 08:00","2025-08-04 18:00","취소","취소","연속"]
[22,"대전세종충남","서산","신당진개폐소현대제철 T/L"," 신송산분기T/L 건설공사","No.70 전선 이동(가철탑→본철탑) No.69∼No.71 전선 교체","2025-08-04 07:00","2025-08-16 18:00","취소","취소","연속"]
[23,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#1T/L 병가선로,  신당진개폐소-태안화력#1T/L 휴전 미승인시 휴전 취소 요청 * 7월 휴전 승인시 취소 요청","2025-08-04 08:00","2025-08-04 18:00","취소","취소","연속"]
[24,"대전세종충남","서산","신서산태안TP#1 T/L"," 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (No.2~70, 72~136 총 133기), 즉시가압(20분 이내)가능, 주말 및 휴일작업 없음","2025-08-06 08:00","2025-08-27 18:00","취소","취소","매일"]
[25,"대전세종충남","천안","신온양서서울#1 T/L","(7월 취소시)신온양S/S  #78Bay B/F PNL 대체","(7월 취소시)(즉시가압불가)신온양S/S  #78Bay 노후 B/F PNL 대체","2025-08-18 09:00","2025-08-22 18:00","취소","취소","연속"]
[26,"대전세종충남","천안","신온양S/S #4 M.Tr","(7월 취소시) 신온양S/S  #4M.Tr 부싱절연유 채유","(7월 취소시)(즉시가압 가능) 신온양S/S  #4M.Tr 부싱절연유 채유","2025-08-29 09:00","2025-08-29 18:00","취소","취소","연속"]
[27,"대전세종충남","천안","신온양S/S #4 M.Tr","(7월 취소시)신온양S/S  #77Bay B/F PNL 대체","(7월 취소시)(즉시가압불가)(장기미교체 대상)신온양S/S  #77Bay 노후 B/F PNL 대체","2025-08-26 10:00","2025-08-29 18:00","취소","취소","연속"]
[28,"대전세종충남","천안","신온양서서울#2 T/L","(7월 취소시)신온양S/S  #77Bay B/F PNL 대체","(7월 취소시)(즉시가압불가)(장기미교체 대상)신온양S/S  #77Bay 노후 B/F PNL 대체","2025-08-26 10:00","2025-08-29 18:00","취소","취소","연속"]
[29,"대전세종충남","천안","신온양신탕정#2 T/L","(7월 취소시)  신온양신탕정#2T/L 보호반 대체","(7월 취소시)(즉시가압불가)(장기미교체대상)신온양S/S #78B/F 보호반,신온양, 신탕정S/S  신온양신탕정#2T/L 보호반 대체","2025-08-18 09:00","2025-08-22 18:00","취소","취소","연속"]
[30,"대전세종충남","청양","청양군산#1 T/L","[송전][주말작업O]  청양-군산T/L 가공지선보강공사"," 청양-군산#1 TL 가공지선 보강 공사","2025-08-25 17:00","2025-08-26 09:00","2025-08-25 17:00","2025-08-26 09:00","연속"]
[31,"전북","군산","군산신김제#1 T/L","군산S/S  장기사용 GIS 대체공사","○ 송전선로 보호반 이설(군산-신김제#1T/L) ○ 인출송전선로 이설(72Bay →73Bay) ○ LA, CVT 이설(72Bay →73Bay)","2025-08-26 09:00","2025-08-31 18:00","취소","취소","연속"]
[32,"전북","군산","군산S/S #1 Sh.R CB","군산변전소  GIS 대체공사(기기) (중복)","○ 362kV GIS 4000A 40kA × 10CB(50kA) 교체 ○ 기타 부대공사 × 1식","2025-08-01 18:00","2025-08-02 18:00","취소","취소","연속"]
[33,"전북","김제","신김제S/S #4 M.Tr","신김제S/S #4M.Tr 누유개소 보수공사","신김제S/S #4M.Tr 누유개소 보수공사","2025-08-19 09:00","2025-08-19 18:00","취소","취소","연속"]
[34,"전북","직할","신옥천신남원#1 T/L"," 신옥천-신남원 등 3개T/L 수평추락방지시설 설치공사"," 신옥천-신남원#1T/L 1~178호","2025-08-04 07:30","2025-08-14 17:00","취소","취소","연속"]
[35,"전북","직할","신남원의령#2 T/L","'25년도 변전설비 기타기기 점검","- CVT 점검","2025-08-02 09:00","2025-08-02 18:00","취소","취소","연속"]
[36,"전북","직할","신남원신광주#2 T/L","'24~'25년 전북직할 가공송전 협력회사 공사(계속)","○  신남원-신광주T/L 피뢰기 설치공사(계속) - No.1~115","2025-08-13 07:30","2025-08-21 18:00","취소","취소","매일"]
[37,"전북","직할","신옥천신남원#2 T/L"," 신옥천-신남원 등 3개T/L 수평추락방지시설 설치공사"," 신옥천-신남원#2T/L 1~178호","2025-08-15 07:30","2025-08-25 17:00","취소","취소","연속"]
[38,"전북","직할","신남원광양#1 T/L","신남원S/S 75BAY B/F PNL 개조 작업차"," #2M.Tr 설치 관련 75BAY B/F PNL 개조","2025-08-26 09:00","2025-08-30 18:00","2025-08-26 09:00","2025-08-30 18:00","연속"]
[39,"전북","직할","신남원의령#1 T/L","'25년 가공송전 순시점검 위탁공사(중복)","○ 정밀점검 : No.137~180","2025-08-25 08:00","2025-08-28 18:00","2025-08-25 08:00","2025-08-28 18:00","연속"]
[40,"전북","직할","신남원신광주#1 T/L","'24~'25년 전북직할 가공송전 협력회사 공사(계속)","○  신남원-신광주T/L 피뢰기 설치공사(계속) - No.1~115","2025-08-04 07:30","2025-08-12 18:00","취소","취소","매일"]
[41,"광주전남","강진","신강진S/S #1 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. 신강진S/S #1M.Tr,B,C상 보통점검 ※ 거래소 요청 시 휴전일정 협의 가능","2025-08-19 08:00","2025-08-20 18:00","2025-08-19 08:00","2025-08-20 18:00","연속"]
[42,"광주전남","광주","신광주S/S #2 M.Tr","'25년 광주전력지사 변전협력회사 공사","신광주S/S #2M.Tr 주변압기 초기점검","2025-08-06 09:00","2025-08-08 18:00","취소","취소","연속"]
[43,"광주전남","광주","신광주S/S CB 7100","2024~25년 광주전력지사 변전협력회사 공사","2024~25년 광주전력지사 변전협력회사 공사 1. 신광주S/S 7100CB, 7271CB, 7472CB 차단기 조작시험","2025-08-07 09:00","2025-08-07 18:00","2025-08-07 09:00","2025-08-07 18:00","연속"]
[44,"광주전남","광주","신광주S/S CB 7271","2024~25년 광주전력지사 변전협력회사 공사","2024~25년 광주전력지사 변전협력회사 공사 1. 신광주S/S 7100CB, 7271CB, 7472CB 차단기 조작시험","2025-08-07 09:00","2025-08-07 18:00","2025-08-07 09:00","2025-08-07 18:00","연속"]
[45,"광주전남","광주","신광주S/S CB 7472","2024~25년 광주전력지사 변전협력회사 공사","2024~25년 광주전력지사 변전협력회사 공사 1. 신광주S/S 7100CB, 7271CB, 7472CB 차단기 조작시험","2025-08-07 09:00","2025-08-07 18:00","2025-08-07 09:00","2025-08-07 18:00","연속"]
[46,"광주전남","광주","신광주S/S CB 7200","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주변전소 72BAY B/F PNL 대체","2025-08-11 09:00","2025-08-15 18:00","취소","취소","연속"]
[47,"광주전남","광주","신광주S/S CB 7271","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주변전소 72BAY B/F PNL 대체","2025-08-11 09:00","2025-08-15 18:00","취소","취소","연속"]
[48,"광주전남","광주","신광주S/S #1 BUS","장기사용  #1BUS 모선보호반 교체","장기사용  #1BUS 모선보호반 교체","2025-08-18 08:00","2025-08-20 18:00","취소","취소","연속"]
[49,"광주전남","광주","신광주S/S #3 M.Tr","3M.Tr 변압기보호반 장기사용 교체","3M.Tr 변압기보호반 장기사용 교체","2025-08-25 08:00","2025-08-29 18:00","취소","취소","연속"]
[50,"광주전남","광주","신남원신광주#1 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주SS 신남원-신광주1TL LA, CVT A,B,C상 보통점검","2025-08-22 08:00","2025-08-22 18:00","2025-08-22 08:00","2025-08-22 18:00","연속"]
[51,"광주전남","광주","신광주S/S #2 BUS","장기사용  #2BUS 모선보호반 교체","장기사용  #2BUS 모선보호반 교체","2025-08-21 08:00","2025-08-23 18:00","취소","취소","연속"]
[52,"광주전남","광주","신화순S/S #3 M.Tr","2024-2025년도 광주전력지사 변전협력공사 총액공사","신화순변전소 75BAY B/F반 PNL 대체 - 7200, 7572, 6433, 4384, 4389-1,2CB 휴전 - (신)B/F PNL 설치 및 제어케이블 결선 - (주)PNL 철거 - 조작 및 연동시험 등","2025-08-25 08:00","2025-08-29 18:00","취소","취소","연속"]
[53,"광주전남","광주","신화순S/S #2 M.Tr","2024-2025년도 광주전력지사 변전협력회사 총액공사","신화순변전소 2MTr 1,2차 LA A,B,C상 하자점검","2025-08-21 08:00","2025-08-21 18:00","취소","취소","연속"]
[54,"광주전남","순천","광양CC여수TP#2 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #2T/L 폴리머점퍼지지애자 설치","2025-08-14 07:00","2025-08-14 18:00","2025-08-14 07:00","2025-08-14 18:00","연속"]
[55,"광주전남","순천","광양CC여수TP#1 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #1T/L 폴리머점퍼지지애자 설치","2025-08-11 07:00","2025-08-13 18:00","2025-08-11 07:00","2025-08-13 18:00","매일"]
[56,"광주전남","순천","광양여수TP T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가) ※휴일(9,10일) 미작업","2025-08-04 07:00","2025-08-14 18:00","취소","취소","매일"]
[57,"광주전남","순천","신남원광양#2 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가) ※휴일(23,24일) 미작업","2025-08-18 07:00","2025-08-29 18:00","취소","취소","매일"]
[58,"광주전남","순천","신강진광양#2 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치 ※주말(23,24일) 미작업","2025-08-18 07:00","2025-08-29 18:00","취소","취소","매일"]
[59,"광주전남","순천","신강진광양#1 T/L","24-25년 순천전력지사 변전협력회사 공사","신강진-광양#1T/L 보호배전반 대체, 78BAY B/F반 대체공사","2025-08-18 09:00","2025-08-29 18:00","취소","취소","연속"]
[60,"광주전남","순천","광양율촌CC T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가) ※휴일(23,24일) 미작업","2025-08-18 07:00","2025-08-29 18:00","취소","취소","매일"]
[61,"광주전남","순천","신강진광양#1 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치 ※주말(9,10일) 미작업","2025-08-04 07:00","2025-08-14 18:00","취소","취소","매일"]
[62,"광주전남","순천","신남원광양#1 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가) ※휴일(9,10일) 미작업","2025-08-04 07:00","2025-08-14 18:00","취소","취소","매일"]
[63,"대구","달성","서대구고령#2 T/L","[TEST] 고령S/S 서대구-고령#2T/L CB 정밀점검 무부하가압","[TEST] 고령S/S 서대구-고령#2T/L CB 정밀점검 무부하가압","2025-08-08 19:00","2025-08-08 20:00","취소","취소","연속"]
[64,"대구","달성","북경남고령#2 T/L","북경남-고령#2T/L GIS 정밀점검","북경남-고령#2T/L GIS 정밀점검","2025-08-18 09:00","2025-08-24 18:00","2025-08-18 09:00","2025-08-23 18:00","연속"]
[65,"대구","달성","고령S/S CB 7571","고령S/S 서대구-고령#2T/L CB 정밀점검","고령S/S 서대구-고령#2T/L CB 정밀점검","2025-08-04 09:00","2025-08-08 20:00","2025-08-04 09:00","2025-08-08 20:00","연속"]
[66,"대구","달성","고령의령#1 T/L","[TEST] 고령S/S 7300 CB부 정밀 무부하가압선로","[TEST] 고령S/S 7300 CB부 정밀 무부하가압선로","2025-08-01 17:00","2025-08-01 18:00","취소","취소","연속"]
[67,"대구","칠곡","서대구S/S #4 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2025-08-04 08:00","2025-08-12 18:00","2025-08-04 08:00","2025-08-12 18:00","연속"]
[68,"대구","포항","신월성N/P #2 대기보조변압기 (CB 7200, 7272)","2024~25년도 포항전력지사 변전협력회사 공사","7272, 7200 GIS 보통점검","2025-08-18 09:00","2025-08-19 18:00","2025-08-18 09:00","2025-08-19 18:00","연속"]
[69,"대구","포항","월성N/P #76 BUS","월성N/P 연계  GIS 용량대체공사(77Bay 대체)","월성N/P 연계  GIS 용량대체공사 ○  GIS × 18CB 대체 ○ 보호반 설치 및 이설 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기타 부대공사 × 1식","2025-08-01 09:00","2025-08-17 18:00","2025-08-01 09:00","2025-08-17 18:00","연속"]
[70,"대구","포항","월성N/P CB 7371  ","2024~2025년 포항전력지사 변전협력회사 공사","7371 GIS 조작시험, PT 보통점검","2025-08-28 09:00","2025-08-29 18:00","2025-09-08 09:00","2025-09-09 18:00","연속"]
[71,"대구","포항","월성N/P SEC CB 75760","월성N/P 연계  GIS 용량대체공사(77Bay 대체)","월성N/P 연계  GIS 용량대체공사 ○  GIS × 18CB 대체 ○ 보호반 설치 및 이설 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기타 부대공사 × 1식","2025-08-16 18:00","2025-08-17 18:00","2025-08-16 18:00","2025-08-17 18:00","연속"]
[72,"대구","포항","월성N/P #2호기 주변압기 (CB 7300, 7372)","2024~2025년 포항전력지사 변전협력회사 공사","7300, 7372 GIS 보통점검","2025-08-28 09:00","2025-08-29 18:00","2025-09-08 09:00","2025-09-09 18:00","연속"]
[73,"경북","영주","신영주S/S #2 M.Tr","2024-25년 영주전력지사 변전협력회사 총액공사","OFU 불량 및 누유 발생으로 긴급점검 및 보수 필요 2차 LA 하자점검[A,B,C]","2025-08-06 09:00","2025-08-07 18:00","2025-08-09 09:00","2025-08-10 18:00","연속"]
[74,"경북","영주","신영주한울NP#1 T/L"," 신영주-한울NP2T/L 수평추락방지장치 설치"," 신영주-한울NP2T/L 수평추락방지장치 설치","2025-08-11 08:00","2025-08-20 17:00","취소","취소","매일"]
[75,"경북","영주","신영주한울NP#2 T/L"," 신영주-한울NP2T/L 수평추락방지장치 설치"," 신영주-한울NP2T/L 수평추락방지장치 설치","2025-08-21 08:00","2025-08-30 17:00","취소","취소","매일"]
[76,"경북","영주","한울2NP한울3NP#4 T/L","24~25년 영주전력지사 변전협력회사공사","7G02DS 구동부 교체(PD 발생 불량조치)","2025-08-11 09:00","2025-08-14 18:00","취소","취소","연속"]
[77,"경북","직할","청송PP면봉산풍력 T/L"," 청송분기 T/L 불량애자 교체공사","-  청송PP면봉산풍력 T/L 불량애자 교체","2025-08-29 09:00","2025-09-29 18:00","취소","취소","매일"]
[78,"부산울산","동부산","신양산S/S #2 BUS","신양산S/S  용량부족 차단기 교체공사","73BAY 차단기 설치(7372CB-7352DS 도킹)를 위한 안전이격 휴전","2025-08-09 08:00","2025-08-10 18:00","2025-08-09 08:00","2025-08-10 18:00","연속"]
[79,"부산울산","동부산","신양산S/S #1 BUS","신양산S/S  용량부족 차단기 교체공사","73BAY 차단기 설치(7351DS-7371CB 도킹)를 위한 안전이격 휴전","2025-08-02 08:00","2025-08-03 18:00","2025-08-02 08:00","2025-08-03 18:00","연속"]
[80,"부산울산","북부산","북부산S/S CB 7A00","북부산S/S  STATCOM 초기점검","북부산S/S  STATCOM 초기점검","2025-08-04 09:00","2025-08-29 18:00","취소","취소","연속"]
[81,"부산울산","북부산","북부산S/S CB 7A71","북부산S/S  STATCOM 초기점검","북부산S/S  STATCOM 초기점검","2025-08-04 09:00","2025-08-29 18:00","취소","취소","연속"]
[82,"경남","김해송변전부","신김해S/S #4 M.Tr","신김해S/S 종합예방시스템 설치공사","- 신김해S/S  #4M.Tr 부싱시험탭 설치","2025-08-04 09:00","2025-08-05 14:00","취소","취소","연속"]
[83,"경남","김해송변전부","신김해S/S #3 M.Tr","신김해S/S 종합예방시스템 설치공사","- 신김해S/S  #3M.Tr 부싱시험탭 설치","2025-08-01 09:00","2025-08-02 14:00","취소","취소","연속"]

{"sheet":"154설비","index":2,"n_rows":179,"n_cols":12,"rows_kept":179,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 8월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","부평","관교만수#1 T/L"," 지중송전설비 위탁정비공사 OF케이블 절연유 열화진단"," 지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","2025-08-13 09:00","2025-08-13 18:00","취소","취소","연속"]
[2,"인천","부평","관교만수#2 T/L"," 지중송전설비 위탁정비공사 OF케이블 절연유 열화진단"," 지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","2025-08-14 09:00","2025-08-14 18:00","취소","취소","연속"]
[3,"인천","부평","신인천연료전지 T/L CB"," 신경서S/S 신인천 연료전지T/L 보통점검(고객측요청)"," 신경서S/S 신인천 연료전지T/L 보통점검(고객측요청)","2025-08-26 09:00","2025-08-26 18:00","2025-08-26 09:00","2025-08-26 18:00","연속"]
[4,"인천","부평","신가좌주안#1 T/L","  주안-관교등 4개T/L 열경화공법 EBG 보강공사","  주안-관교등 4개T/L 열경화공법 EBG 보강공사","2025-08-04 09:00","2025-08-06 18:00","취소","취소","연속"]
[5,"인천","부평","신가좌주안#2 T/L","  주안-관교등 4개T/L 열경화공법 EBG 보강공사","  주안-관교등 4개T/L 열경화공법 EBG 보강공사","2025-08-07 09:00","2025-08-09 18:00","취소","취소","연속"]
[6,"인천","부평","관교주안 T/L","  주안-관교등 4개T/L 열경화공법 EBG 보강공사","  주안-관교등 4개T/L 열경화공법 EBG 보강공사","2025-08-11 09:00","2025-08-12 18:00","취소","취소","연속"]
[7,"인천","부평","학익S/S #2 BUS","  남인천-학익 등 2개T/L 지장이설 및 선종교체공사","  남인천-학익 등 2개T/L 지장이설 및 선종교체공사","2025-08-30 09:00","2025-08-30 10:00","2025-08-30 09:00","2025-08-30 10:00","연속"]
[8,"인천","시흥","북송도연수#2 T/L","  남인천-학익 등 2개T/L 지장이설 및 선종교체공사","  남인천-학익 등 2개T/L 지장이설 및 선종교체공사","2025-08-30 09:00","2025-08-31 09:00","2025-08-30 09:00","2025-08-31 09:00","연속"]
[9,"인천","시흥","연수S/S #2 BUS","  남인천-학익 등 2개T/L 지장이설 및 선종교체공사","  남인천-학익 등 2개T/L 지장이설 및 선종교체공사","2025-08-30 10:00","2025-08-31 09:00","2025-08-30 10:00","2025-08-31 09:00","연속"]
[10,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신설철타 조립 중 이격거리 필요","2025-08-25 07:00","2025-08-29 18:00","2025-08-25 07:00","2025-08-29 18:00","매일"]
[11,"경기북부","구리","동서울서종#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 철탑 조립공사 (신설 철탑 조립 중 이격거리 필요)","2025-08-25 07:00","2025-08-29 18:00","2025-08-25 07:00","2025-08-29 18:00","매일"]
[12,"경기","직할","과천동안양#1 T/L"," 과천-동안양T/L 지중화공사(과천지식정보타운)","과천지식정보타운 사업지구 내 지장송전선로 지중화","2025-08-27 08:00","2025-08-29 17:00","취소","취소","연속"]
[13,"강원","직할","양구화천HP#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 양구S/S  양구-화천HP#1T/L PNL 43PDA 절체 불량 □ 43PDA 자동 및 원방 절체 불가로 예비품 교체","2025-08-01 09:00","2025-08-01 18:00","2025-08-01 09:00","2025-08-01 18:00","연속"]
[14,"강원","태백","태백S/S CB 6200","2024-2025년 태백전력지사 변전협력회사 공사","태백S/S  #61-#66 BUS TIE GIS 보통점검","2025-08-26 09:00","2025-08-26 18:00","2025-08-26 09:00","2025-08-26 18:00","연속"]
[15,"강원","태백","태백S/S CB 6100","2024-2025년 태백전력지사 변전협력회사 공사","태백S/S  #60-#65 BUS TIE GIS 보통점검","2025-08-25 09:00","2025-08-25 18:00","2025-08-25 09:00","2025-08-25 18:00","연속"]
[16,"강원","태백","태백S/S SEC CB 60610","2024-2025년 태백전력지사 변전협력회사 공사","태백S/S  #60-#61 SEC GIS 보통점검","2025-08-27 09:00","2025-08-27 18:00","2025-08-27 09:00","2025-08-27 18:00","연속"]
[17,"강원","태백","태백S/S SEC CB 65660","2024-2025년 태백전력지사 변전협력회사 공사","태백S/S  #65-#66 SEC GIS 보통점검","2025-08-28 09:00","2025-08-28 18:00","2025-08-28 09:00","2025-08-28 18:00","연속"]
[18,"충북","직할","문백S/S #66 BUS","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-08-27 13:00","2025-08-28 10:00","취소","취소","연속"]
[19,"충북","직할","문백S/S #61 BUS","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-08-27 10:00","2025-08-27 13:00","취소","취소","연속"]
[20,"충북","직할","문백S/S #60 BUS","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-08-26 13:00","2025-08-27 10:00","취소","취소","연속"]
[21,"충북","직할","문백오창#1 T/L","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-08-26 10:00","2025-08-27 10:00","취소","취소","연속"]
[22,"충북","직할","문백S/S #65 BUS","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-08-26 10:00","2025-08-26 13:00","취소","취소","연속"]
[23,"충북","직할","문백오창#2 T/L","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-08-27 10:00","2025-08-28 10:00","취소","취소","연속"]
[24,"충북","청주","신옥천추부#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-08-27 10:00","2025-08-27 18:00","2025-08-27 10:00","2025-08-27 18:00","연속"]
[25,"충북","청주","신옥천추부#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-08-28 10:00","2025-08-28 18:00","2025-08-28 10:00","2025-08-28 18:00","연속"]
[26,"충북","충주","풍동음성#2 T/L"," 풍동S/S 외벽 리모델링 공사","공사 목적 : 화재에 취약한 외벽 드라이비트 마감재를 교체하여 화재 확산 방지 및 설비피해를 예방하고자 함. - 시스템비계 설치 및 해체 : 2,815m2 - 외벽드라이비트 마감재 철거 : 1,808m2 - 신설 마감재 설치 : 1,808m2","2025-08-04 09:00","2025-08-15 18:00","2025-08-04 09:00","2025-08-15 18:00","연속"]
[27,"충북","충주","풍동장연 T/L"," 풍동S/S 외벽 리모델링 공사","공사 목적 : 화재에 취약한 외벽 드라이비트 마감재를 교체하여 화재 확산 방지 및 설비피해를 예방하고자 함. - 시스템비계 설치 및 해체 : 2,815m2 - 외벽드라이비트 마감재 철거 : 1,808m2 - 신설 마감재 설치 : 1,808m2","2025-08-04 09:00","2025-08-15 18:00","2025-08-04 09:00","2025-08-15 18:00","연속"]
[28,"대전세종충남","대전","금산무주#2 T/L","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","2025-08-27 07:00","2025-08-29 18:00","취소","취소","매일"]
[29,"대전세종충남","대전","신계룡두마#1 T/L","[가압X][7월취소시]신계룡,두마S/S 신계룡두마#1T/L 보호반대체","[가압X][7월취소시]신계룡,두마S/S 신계룡두마#1T/L 보호반대체","2025-08-04 09:00","2025-08-07 18:00","취소","취소","연속"]
[30,"대전세종충남","대전","팔봉두마#2 T/L","[즉시가압X]두마S/S 팔봉두마#2T/L 전자변교체","[즉시가압X]두마S/S 팔봉두마#2T/L 전자변교체","2025-08-01 14:00","2025-08-01 18:00","취소","취소","연속"]
[31,"대전세종충남","대전","팔봉두마#1 T/L","[즉시가압x]두마S/S 팔봉-두마#1T/L GIS 전자변 교체","[즉시가압x]두마S/S 팔봉-두마#1T/L GIS 전자변 교체","2025-08-01 09:00","2025-08-01 14:00","취소","취소","연속"]
[32,"대전세종충남","대전","신계룡두마#2 T/L","[가압X][7월취소시]신계룡,두마S/S 신계룡두마#2T/L 보호반대체","[가압X][7월취소시]신계룡,두마S/S 신계룡두마#2T/L 보호반대체","2025-08-11 09:00","2025-08-14 18:00","취소","취소","연속"]
[33,"대전세종충남","대전","신계룡은진#1 T/L","[7월취소시][오전만][즉시가압O]345kV신옥천-청양등추락방지설치공사","[송전][7월취소시][오전만][즉시가압O][주말작업제외] 345kV 신옥천-청양 등 추락방지설치공사","2025-08-04 07:00","2025-08-14 11:00","취소","취소","매일"]
[34,"대전세종충남","서산","서산대산#3 T/L","대산S/S 장기사용  GIS 교체공사(3차)","대산S/S 장기사용  GIS 교체공사(3차) - 무부하가압","2025-08-25 15:00","2025-08-26 15:00","2025-08-25 15:00","2025-08-26 15:00","연속"]
[35,"대전세종충남","서산","서산대산#3 T/L","대산S/S 장기사용  GIS 교체공사(3차)","대산S/S 장기사용  GIS 교체공사(3차) - 무부하가압","2025-08-29 15:00","2025-08-30 15:00","2025-08-29 15:00","2025-08-30 15:00","연속"]
[36,"대전세종충남","세종","천안전의#2 T/L"," 천안-전의T/L 안전이격 및 전력선 교체공사","○ 천안S/S~전의S/S 9.945km 전력선 교체 - ACSR 330㎟ → ASCC/TW 430㎟ X S X 2C ○ 저지상고 개소 안전이격 확보 철탑교체 4기 ○ 기타 부대공사","2025-08-26 07:00","2025-08-30 18:00","2025-08-26 07:00","2025-08-30 18:00","연속"]
[37,"대전세종충남","세종","천안전의#1 T/L"," 천안-전의T/L 안전이격 및 전력선 교체공사","○ 천안S/S~전의S/S 9.945km 전력선 교체 - ACSR 330㎟ → ASCC/TW 430㎟ X S X 2C ○ 저지상고 개소 안전이격 확보 철탑교체 4기 ○ 기타 부대공사","2025-08-25 07:00","2025-08-25 18:00","2025-08-25 07:00","2025-08-25 18:00","연속"]
[38,"대전세종충남","세종","천안전의#1 T/L"," 천안-전의T/L 안전이격 및 전력선 교체공사","○ 천안S/S~전의S/S 9.945km 전력선 교체 - ACSR 330㎟ → ASCC/TW 430㎟ X S X 2C ○ 저지상고 개소 안전이격 확보 철탑교체 4기 ○ 기타 부대공사","2025-08-31 07:00","2025-09-09 18:00","2025-08-31 07:00","2025-09-09 18:00","연속"]
[39,"대전세종충남","세종","서세종조치원 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 서서종-조치원 (찰탑철거 및 설치 : No.20,21,22,23)","2025-08-14 07:00","2025-08-20 18:00","취소","취소","연속"]
[40,"대전세종충남","세종","조치원월산 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 조치원월산 No.20~23호 임시 가선로 구성 (찰탑교체 3기 : No.20,21,23)","2025-08-11 07:00","2025-08-13 18:00","취소","취소","연속"]
[41,"대전세종충남","세종","조치원월산 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 조치원-월산 본선로 구성 (가철탑-&gt본철탑 : No.20,21,23)","2025-08-21 07:00","2025-08-24 18:00","취소","취소","연속"]
[42,"대전세종충남","직할","둔곡송강#2 T/L","송강S/S  둔곡-송강#2T/L GIS 보통점검","송강S/S  둔곡-송강#2T/L GIS 보통점검","2025-08-13 09:00","2025-08-13 18:00","취소","취소","연속"]
[43,"대전세종충남","청양","보령T/P CB 6100","[변전총액] 청양P/O 변전협력 총액공사","보령T/P 170kV 6100 BUS TIE 차단기조작시험 및 전자변 교체","2025-08-06 09:00","2025-08-06 18:00","2025-08-06 09:00","2025-08-06 18:00","연속"]
[44,"대전세종충남","청양","신서천옥산#2 T/L","[송전][주말작업O]  옥산-서천T/L 항공구 설치공사","항공구 설치","2025-08-26 08:00","2025-08-26 18:00","취소","취소","연속"]
[45,"대전세종충남","청양","신서천옥산#1 T/L","[변전총액] 청양P/O 변전협력 총액공사","옥산-서천#1T/L 차단기조작시험 및 보통점검","2025-08-07 09:00","2025-08-07 18:00","취소","취소","연속"]
[46,"대전세종충남","청양","동군산장항#1 T/L","[변전총액]청양P/O 변전협력회사 총액공사"," 동군산-장항#1T/L 차단기 조작시험 - 87보호계전기 통신 오류 점검","2025-08-08 09:00","2025-08-08 18:00","취소","취소","연속"]
[47,"전북","군산","군산영등#2 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-08-18 07:00","2025-08-24 18:00","취소","취소","연속"]
[48,"전북","군산","군산이리#2 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-08-18 07:00","2025-08-22 18:00","취소","취소","연속"]
[49,"전북","군산","군산이리#1 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-08-23 07:00","2025-08-24 18:00","취소","취소","연속"]
[50,"전북","군산","동군산장항#2 T/L","'25년 가공송전 순시점검 위탁공사(옥산-장항 동시휴전 필요)"," 동군산-장항T/L 철탑 정밀점검 No.18~38.99 ※  옥산-장항, 동군산-장항T/L 4회선구간 작업으로 인한 동시휴전 요청","2025-08-13 07:00","2025-08-14 18:00","취소","취소","매일"]
[51,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사(중복)","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2025-08-25 09:00","2025-08-27 18:00","취소","취소","연속"]
[52,"전북","군산","새만금비응#1 T/L","비응S/S  비응-동비응 #1,2T/L GIS 증설공사","170kV GIS × 2CCT (617, 677) - 617 BAY #2BUS 무부하 가압","2025-08-21 18:00","2025-08-22 18:00","2025-08-21 18:00","2025-08-22 18:00","연속"]
[53,"전북","군산","새만금비응#1 T/L","비응S/S  비응-동비응 #1,2T/L GIS 증설공사","170kV GIS × 2CCT (617, 677) - 617 BAY #1BUS 무부하 가압","2025-08-29 18:00","2025-08-30 18:00","2025-08-29 18:00","2025-08-30 18:00","연속"]
[54,"전북","군산","서군산소룡#1 T/L","군산P/O 이상 차단기 하자점검 (중복)","서군산S/S  서군산-소룡#1,2 T/L 차단기 하자점검","2025-08-04 09:00","2025-08-04 18:00","2025-08-04 18:00","2025-08-05 03:00","연속"]
[55,"전북","군산","군산영등#2 T/L","'25년 군산전력지사 가공송전협력회사공사(영등-낭산#1 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-08-25 07:00","2025-08-25 18:00","취소","취소","연속"]
[56,"전북","군산","영등낭산#1 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#2 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선구간으로 동시 휴전 필요","2025-08-25 07:00","2025-08-25 18:00","취소","취소","연속"]
[57,"전북","군산","군산영등#1 T/L","'25년 군산전력지사 가공송전협력회사공사(영등-낭산#2 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-08-01 07:00","2025-08-01 18:00","취소","취소","연속"]
[58,"전북","군산","영등낭산#2 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#1 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-08-01 07:00","2025-08-01 18:00","취소","취소","연속"]
[59,"전북","군산","이리백산#2 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-08-04 07:00","2025-08-07 18:00","취소","취소","연속"]
[60,"전북","군산","탄소이리#1 T/L","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","2025-08-12 17:00","2025-08-12 18:00","2025-08-12 17:00","2025-08-12 18:00","연속"]
[61,"전북","군산","이리백산#2 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-08-15 07:00","2025-08-18 18:00","취소","취소","연속"]
[62,"전북","군산","탄소이리#1 T/L","'24~25년 군산전력 가공송전협력업체 공사"," 이리-탄소T/L 피뢰기 설치공사 No.1~63","2025-08-26 09:00","2025-08-30 18:00","2025-08-26 09:00","2025-08-30 18:00","매일"]
[63,"전북","군산","탄소이리#1 T/L","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","2025-08-05 17:00","2025-08-05 18:00","2025-08-05 17:00","2025-08-05 18:00","연속"]
[64,"전북","군산","탄소이리#1 T/L","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","2025-08-07 17:00","2025-08-07 18:00","2025-08-07 17:00","2025-08-07 18:00","연속"]
[65,"전북","군산","이리백산#1 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-08-08 07:00","2025-08-14 18:00","취소","취소","연속"]
[66,"전북","군산","탄소이리#1 T/L","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","2025-08-14 17:00","2025-08-14 18:00","2025-08-14 17:00","2025-08-14 18:00","연속"]
[67,"전북","군산","팔봉왕궁#1 T/L","전북본부 관내 EBA 자기애관 교체공사","기설 EBA 자기애관 철거 및 폴리머애관 설치","2025-08-18 09:00","2025-08-22 18:00","취소","취소","연속"]
[68,"전북","김제","소성고창#2 T/L"," 고창-영광T/L No.45~142 선종교체공사","○  고창-영광T/L 선종교체공사 - No.45~142 전력선 교체(ACSR 330㎟ -> ASCC 430㎟)","2025-08-13 07:00","2025-08-22 18:00","2025-08-13 07:00","2025-08-22 18:00","연속"]
[69,"전북","김제","고창홍농 T/L"," 고창-영광T/L No.45~142 선종교체공사","○  고창-영광T/L 선종교체공사 - No.45~142 전력선 교체(ACSR 330㎟ -> ASCC 430㎟)","2025-08-13 07:00","2025-08-22 18:00","2025-08-13 07:00","2025-08-22 18:00","연속"]
[70,"전북","김제","소성고창#1 T/L"," 고창-영광T/L No.45~142 선종교체공사","○  고창-영광T/L 선종교체공사 - No.45~142 전력선 교체(ACSR 330㎟ -> ASCC 430㎟)","2025-08-23 07:00","2025-08-23 18:00","2025-08-23 07:00","2025-08-23 18:00","연속"]
[71,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(PT&ES 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-16 15:00","2025-08-17 15:00","취소","취소","연속"]
[72,"전북","김제","부안동부안#2 T/L","모선구분차단기 설치공사(6200 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-12 15:00","2025-08-13 15:00","취소","취소","연속"]
[73,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(6200 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-07 15:00","2025-08-08 15:00","취소","취소","연속"]
[74,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(PT&ES 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-16 15:00","2025-08-17 15:00","취소","취소","연속"]
[75,"전북","김제","부안동부안#2 T/L","모선구분차단기 설치공사(B/S 무부하)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-18 15:00","2025-08-19 15:00","취소","취소","연속"]
[76,"전북","김제","부안동부안#2 T/L","모선구분차단기 설치공사(PT&ES 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-21 15:00","2025-08-22 15:00","취소","취소","연속"]
[77,"전북","김제","부안동부안#2 T/L","모선구분차단기 설치공사(PT&ES 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-21 15:00","2025-08-22 15:00","취소","취소","연속"]
[78,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(B/S 무부하)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-28 15:00","2025-08-29 15:00","취소","취소","연속"]
[79,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(B/S 무부하)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-28 15:00","2025-08-29 15:00","취소","취소","연속"]
[80,"전북","김제","백산김제#2 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-08-08 07:00","2025-08-14 18:00","취소","취소","연속"]
[81,"전북","김제","백산김제#1 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-08-15 07:00","2025-08-18 18:00","취소","취소","연속"]
[82,"전북","김제","백산김제#1 T/L"," 이리-백산등 2개T/L 지장철탑이설공사","이리백산(백산김제) 36~39, 49~50 전력선 교체","2025-08-04 07:00","2025-08-07 18:00","취소","취소","연속"]
[83,"전북","김제","김제부안#1 T/L","모선구분차단기 설치(PT&ES)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-14 09:00","2025-08-22 18:00","취소","취소","연속"]
[84,"전북","김제","김제부안#2 T/L","모선구분차단기 설치(6200)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-08-05 09:00","2025-08-13 18:00","취소","취소","연속"]
[85,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","- 작업내용 : #2T/L 전선이동 (가선로 → 본선로) - 위치 : 전주시 완산구 석구동 일원 - 규모 : ACSR410㎟ × 2B × 4C (0.81km, 지지물4기)","2025-08-18 07:00","2025-08-21 18:00","취소","취소","연속"]
[86,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","- 작업내용 : #2T/L 전선 긴선(케이블타워) - 위치 : 전주시 완산구 석구동 일원 - 규모 : ACSR410㎟ × 2B × 4C (0.81km, 지지물4기)","2025-08-31 07:00","2025-09-03 18:00","취소","취소","연속"]
[87,"전북","김제","신김제동전주#1 T/L"," 완산분기T/L 건설공사","- 작업내용 : #1T/L 전선이동 (가선로 → 본선로), 케이블타워 조립 및 전선긴선 - 위치 : 전주시 완산구 석구동 일원 - 규모 : ACSR410㎟ × 2B × 4C (0.81km, 지지물4기)","2025-08-22 07:00","2025-08-30 18:00","취소","취소","연속"]
[88,"전북","직할","동전주태평#2 T/L","동전주-태평#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-08-25 09:00","2025-08-28 18:00","2025-08-25 09:00","2025-08-28 18:00","연속"]
[89,"전북","직할","동전주태평#1 T/L","동전주-태평#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-08-11 09:00","2025-08-14 18:00","2025-08-11 09:00","2025-08-14 18:00","연속"]
[90,"전북","직할","금산무주#1 T/L"," #1Sh.C GIS 정밀점검 무부하가압","CB 정밀점검","2025-08-27 14:00","2025-08-27 18:00","취소","취소","연속"]
[91,"전북","직할","왕궁봉동#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-08-06 08:00","2025-08-06 18:00","취소","취소","매일"]
[92,"전북","직할","왕궁봉동#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-08-05 08:00","2025-08-05 18:00","취소","취소","매일"]
[93,"전북","직할","북전주S/S #1 BUS","북전주-봉동#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-08-11 09:00","2025-08-12 18:00","취소","취소","연속"]
[94,"전북","직할","북전주봉동#1 T/L","북전주-봉동#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-08-11 09:00","2025-08-14 18:00","취소","취소","연속"]
[95,"전북","직할","북전주S/S #2 BUS","북전주-봉동#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-08-13 09:00","2025-08-14 18:00","취소","취소","연속"]
[96,"전북","직할","북전주S/S #1 BUS","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-08-18 09:00","2025-08-19 18:00","취소","취소","연속"]
[97,"전북","직할","북전주S/S #2 BUS","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-08-20 09:00","2025-08-21 18:00","취소","취소","연속"]
[98,"전북","직할","북전주S/S #1 BUS","북전주S/S 북전주-진안T/L GIS 무부하가압","CB 정밀점검","2025-08-30 14:00","2025-08-30 18:00","취소","취소","연속"]
[99,"전북","직할","북전주봉동#2 T/L","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-08-18 09:00","2025-08-22 18:00","취소","취소","연속"]
[100,"전북","직할","신남원S/S #6 EM.Tr CB","'25년도 변전설비 기타기기 점검","- EM.Tr(1), EP.Tr(7) 점검 -  EGIS(1), 23kV EGIS(9) 점검","2025-08-25 09:00","2025-08-29 18:00","2025-08-25 09:00","2025-08-29 18:00","연속"]
[101,"전북","직할","신남원남원#2 T/L","'24~'25년 전북직할 가공송전 협력회사 공사(계속)","○ 345kV 신남원-신광주T/L 피뢰기 설치 : No.1~115 ○ No.3~6 4회선 구간 작업안전을 위한 휴전","2025-08-20 07:30","2025-08-21 18:00","2025-08-20 07:30","2025-08-21 18:00","매일"]
[102,"전북","직할","신남원S/S #5 EM.Tr CB","'25년도 변전설비 기타기기 점검","- EM.Tr(1), EP.Tr(7) 점검 -  EGIS(1), 23kV EGIS(9) 점검","2025-08-18 09:00","2025-08-22 18:00","2025-08-18 09:00","2025-08-22 18:00","연속"]
[103,"전북","직할","전주서곡#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-08-20 08:00","2025-08-21 18:00","취소","취소","매일"]
[104,"전북","직할","전주서곡#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-08-18 08:00","2025-08-19 18:00","취소","취소","매일"]
[105,"광주전남","강진","삼호화원#2 T/L"," 삼호-화원 지중T/L(복도체화) 건설공사"," XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2025-08-25 09:00","2025-09-12 18:00","취소","취소","연속"]
[106,"광주전남","강진","삼호화원#1 T/L"," 삼호-화원 지중T/L(복도체화) 건설공사"," XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2025-08-04 09:00","2025-08-22 18:00","취소","취소","연속"]
[107,"광주전남","강진","신강진강진#2 T/L","'25년 강진전력지사 효성제 170kV GIS 개선공사","-170kV GIS 개선공사 (2단래치 및 베어링 교체)","2025-08-07 16:00","2025-08-07 20:00","2025-08-07 16:00","2025-08-07 20:00","연속"]
[108,"광주전남","강진","신강진해남#2 T/L","2025년 강진전력지사 효성제 170kV GIS 개선공사","2025년 강진전력지사 효성제 170kV GIS 개선공사 - 베어링 및 레치 신품 교체","2025-08-05 16:00","2025-08-05 20:00","2025-08-05 16:00","2025-08-05 20:00","연속"]
[109,"광주전남","강진","해남해남CS#1 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-08-04 16:00","2025-08-04 20:00","2025-08-05 01:00","2025-08-05 05:00","매일"]
[110,"광주전남","강진","해남해남CS#2 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-08-05 16:00","2025-08-05 20:00","2025-08-06 01:00","2025-08-06 05:00","매일"]
[111,"광주전남","강진","해남진도#2 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","(주)신암전력","2025-08-05 16:00","2025-08-05 20:00","2025-08-05 16:00","2025-08-05 20:00","연속"]
[112,"광주전남","강진","해남해남CS#1 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-08-11 16:00","2025-08-11 20:00","2025-08-12 01:00","2025-08-13 05:00","매일"]
[113,"광주전남","강진","해남해남CS#2 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-08-12 16:00","2025-08-12 20:00","2025-08-13 01:00","2025-08-14 05:00","매일"]
[114,"광주전남","강진","해남진도#2 T/L","2025년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검 - 효성제 170kV GIS 개선 등","2025-08-04 16:00","2025-08-04 20:00","2025-08-04 16:00","2025-08-04 20:00","연속"]
[115,"광주전남","강진","화원안좌#1 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","(주)신암전력","2025-08-04 10:00","2025-08-04 14:00","2025-08-04 18:00","2025-08-04 22:00","연속"]
[116,"광주전남","강진","화원안좌#2 T/L","'25년 강진전력지사 변전협력회사 공사","- 화원-안좌#2T/L 보호반 대체","2025-08-04 09:00","2025-08-06 18:00","취소","취소","연속"]
[117,"광주전남","강진","화원안좌#2 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","(주)신암전력","2025-08-04 14:00","2025-08-04 18:00","2025-08-04 22:00","2025-08-05 02:00","연속"]
[118,"광주전남","강진","화원안좌#1 T/L","'25년 강진전력지사 변전협력회사 공사","- 화원-안좌#1T/L 보호반 대체","2025-08-11 09:00","2025-08-13 18:00","취소","취소","연속"]
[119,"광주전남","광주","계림S/S CB 6200","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 6200BUS-TIE 조작시험","2025-08-28 10:00","2025-08-28 16:00","취소","취소","연속"]
[120,"광주전남","광주","계림S/S SEC CB 65660","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S #65-#66 BUS-SEC 조작시험","2025-08-27 13:00","2025-08-27 16:00","취소","취소","연속"]
[121,"광주전남","광주","계림S/S SEC CB 60610","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S #60-61BUS-SEC 조작시험","2025-08-27 10:00","2025-08-27 13:00","취소","취소","연속"]
[122,"광주전남","광주","신광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 신광주-계림#2T/L 170kV GIS 조작시험","2025-08-26 13:00","2025-08-26 16:00","취소","취소","연속"]
[123,"광주전남","광주","신광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 신광주-계림#1T/L 170kV GIS 조작시험","2025-08-26 10:00","2025-08-26 13:00","취소","취소","연속"]
[124,"광주전남","광주","북광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#2T/L 조작시험","2025-08-25 13:00","2025-08-25 16:00","취소","취소","연속"]
[125,"광주전남","광주","북광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#1T/L 조작시험","2025-08-25 10:00","2025-08-25 13:00","취소","취소","연속"]
[126,"광주전남","광주","계림S/S SEC CB 65660","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-08-18 09:00","2025-08-22 18:00","취소","취소","연속"]
[127,"광주전남","광주","계림S/S CB 6100","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-08-18 09:00","2025-08-22 18:00","취소","취소","연속"]
[128,"광주전남","광주","계림S/S SEC CB 60610","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-08-18 09:00","2025-08-22 18:00","취소","취소","연속"]
[129,"광주전남","광주","담양일곡#1 T/L","2025년 광주전력지사 170kV GIS 점검공사","2025년 광주전력지사 170kV GIS 점검공사 1. 담양-일곡#1T/L 보통점검","2025-08-22 09:00","2025-08-22 18:00","2025-08-22 09:00","2025-08-22 18:00","연속"]
[130,"광주전남","광주","신광주일곡#1 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주-일곡#1,2T/L PT 보통점검","2025-08-21 10:00","2025-08-21 14:00","취소","취소","연속"]
[131,"광주전남","광주","신광주일곡#2 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주-일곡#1,2T/L PT 보통점검","2025-08-21 14:00","2025-08-21 18:00","취소","취소","연속"]
[132,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  신광주-장성#2T/L GIS 정밀점검","2025-08-11 09:00","2025-08-13 18:00","취소","취소","연속"]
[133,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 장성S/S  신광주-장성#2T/L GIS보통점검","2025-08-13 09:00","2025-08-13 18:00","취소","취소","연속"]
[134,"광주전남","광주","장성영광#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 장성S/S  장성-영광#2T/L GIS보통점검","2025-08-25 09:00","2025-08-25 18:00","취소","취소","연속"]
[135,"광주전남","광주","장성영광#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","-장성-영광#1T/L 170kV GIS 조작시험","2025-08-22 15:00","2025-08-22 18:00","취소","취소","연속"]
[136,"광주전남","목포","나주엄다#1 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치(116기)","2025-08-25 08:00","2025-09-05 18:00","취소","취소","매일"]
[137,"광주전남","목포","장성영광#2 T/L"," 영광-홍농 등 4개T/L 선종교체공사","ㅇ대상 : 고창-영광T/L No.1~34 ㅇ내용 : 용량증대 선종교체공사 ㅇ사유 : 고창-영광T/L 선종교체를 위한 안전이격휴전","2025-08-05 07:00","2025-08-24 18:00","2025-08-05 07:00","2025-08-24 18:00","연속"]
[138,"광주전남","순천","승주서순천 T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-서순천, 화순-승주2(통보분) 병가) ※휴일(9,10일) 미작업","2025-08-04 07:00","2025-08-14 18:00","2025-08-04 18:00","2025-08-15 07:00","매일"]
[139,"광주전남","순천","승주주암HP T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-주암HP, 화순-승주1(통보분) 병가) ※휴일(23,24일) 미작업","2025-08-18 07:00","2025-08-29 18:00","2025-08-18 18:00","2025-08-30 07:00","매일"]
[140,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체용 무부하가압","2025-08-13 17:00","2025-08-14 09:00","취소","취소","연속"]
[141,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-08-14 09:00","2025-08-22 09:00","취소","취소","연속"]
[142,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-08-07 17:00","2025-08-07 21:00","취소","취소","연속"]
[143,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-08-06 09:00","2025-08-14 09:00","취소","취소","연속"]
[144,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-08-06 09:00","2025-08-14 09:00","취소","취소","연속"]
[145,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-08-01 09:00","2025-08-06 09:00","취소","취소","연속"]
[146,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-08-08 17:00","2025-08-08 21:00","취소","취소","연속"]
[147,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체 무부하가압용","2025-08-13 17:00","2025-08-14 18:00","취소","취소","연속"]
[148,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-08-01 09:00","2025-08-22 18:00","취소","취소","연속"]
[149,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-08-01 09:00","2025-08-06 09:00","취소","취소","연속"]
[150,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-08-22 09:00","2025-08-22 18:00","취소","취소","연속"]
[151,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-08-22 09:00","2025-08-22 18:00","취소","취소","연속"]
[152,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-08-14 09:00","2025-08-22 09:00","취소","취소","연속"]
[153,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-08-01 09:00","2025-08-22 18:00","취소","취소","연속"]
[154,"광주전남","순천","호남TP여수TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (2호 : 여천-호남TP1, 호남TP-여수TP1 병가)","2025-08-04 07:00","2025-08-04 18:00","취소","취소","연속"]
[155,"광주전남","순천","호남TP여수TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (2호 : 여천-호남TP2, 호남TP-여수TP2 병가)","2025-08-25 07:00","2025-08-25 18:00","취소","취소","연속"]
[156,"광주전남","순천","여천호남TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP2, 여천-여수1 병가) ※휴일(23,24일) 미작업","2025-08-18 07:00","2025-08-29 18:00","취소","취소","매일"]
[157,"광주전남","순천","여천여수#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP2, 여천-여수1 병가) ※휴일(23,24일) 미작업","2025-08-18 07:00","2025-08-21 18:00","취소","취소","매일"]
[158,"광주전남","순천","여천여수#1 T/L","여천S/S  이하 GIS 교체공사","여천S/S  이하 GIS 교체공사 기기기초를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-08-18 09:00","2025-08-22 18:00","2025-08-18 09:00","2025-08-22 18:00","매일"]
[159,"광주전남","순천","여천여수산단#1 T/L","여천S/S  이하 GIS 교체공사","여천S/S  이하 GIS 교체공사 기기기초를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-08-28 09:00","2025-08-29 18:00","2025-08-28 09:00","2025-08-29 18:00","매일"]
[160,"광주전남","순천","여천호남TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP1, 여천-여수2 병가) ※휴일(9,10일) 미작업","2025-08-04 07:00","2025-08-14 18:00","취소","취소","매일"]
[161,"광주전남","순천","여천여수#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP1, 여천-여수2 병가) ※휴일(9,10일) 미작업","2025-08-11 07:00","2025-08-14 18:00","취소","취소","매일"]
[162,"광주전남","순천","여천호남TP#1 T/L","여천S/S  이하 GIS 교체공사","여천S/S  이하 GIS 교체공사 기기기초를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-08-01 09:00","2025-08-08 18:00","2025-08-01 09:00","2025-08-08 16:00","매일"]
[163,"광주전남","순천","여천여수#2 T/L","여천S/S  이하 GIS 교체공사","여천S/S  이하 GIS 교체공사 기기기초를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-08-11 09:00","2025-08-14 18:00","2025-08-11 09:00","2025-08-14 18:00","매일"]
[164,"광주전남","순천","여수TP여천#2 T/L","여천S/S  이하 GIS 교체공사","여천S/S  이하 GIS 교체공사 기기기초를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-08-25 09:00","2025-08-27 18:00","2025-08-25 09:00","2025-08-27 16:00","매일"]
[165,"광주전남","직할","비아하남#1 T/L"," 첨단분기 T/L 건설공사","ㅁ  첨단분기 T/L 건설공사 - 관형지지물(C/T) 상부재(1단) 조립","2025-08-18 07:00","2025-08-18 18:00","2025-08-18 07:00","2025-08-18 18:00","연속"]
[166,"대구","달성","다산강창#1 T/L","GIS 정밀점검","GIS 정밀점검","2025-08-06 09:00","2025-08-07 18:00","2025-08-06 09:00","2025-08-07 18:00","연속"]
[167,"대구","달성","다산강창#2 T/L","GIS 정밀점검","GIS 정밀점검","2025-08-11 09:00","2025-08-12 18:00","2025-08-11 09:00","2025-08-12 18:00","연속"]
[168,"대구","달성","달성S/S CB 6100","GIS 정밀점검","GIS 정밀점검","2025-08-13 09:00","2025-08-13 18:00","2025-08-13 09:00","2025-08-13 18:00","연속"]
[169,"대구","달성","강창성서#1 T/L","[TEST] 성서S/S #3M.Tr GIS 정밀점검 무부하가압","[TEST] 성서S/S #3M.Tr GIS 정밀점검 무부하가압","2025-08-19 17:00","2025-08-19 18:00","취소","취소","연속"]
[170,"대구","달성"," 팔달S/S 대구염색T/L CB","팔달SS 대구염색T/L 고객요청휴전","팔달SS 대구염색T/L 고객요청휴전","2025-08-02 10:00","2025-08-06 15:00","2025-08-02 10:00","2025-08-06 15:00","연속"]
[171,"경북","구미","남인동인동#1 T/L","남인동S/S  LS인동T/L 교체공사","남인동S/S  LS인동T/L 교체공사_무부하가압","2025-08-01 13:00","2025-08-02 13:00","2025-08-01 13:00","2025-08-02 13:00","연속"]
[172,"경북","구미","남인동인동#1 T/L","남인동S/S  LS인동T/L 교체공사","남인동S/S  LS인동T/L 교체공사_무부하가압","2025-08-07 13:00","2025-08-10 18:00","2025-08-07 13:00","2025-08-10 18:00","연속"]
[173,"경남","직할","창공월림#2 T/L","월림S/S  장기사용 대체공사(이격거리)","월림S/S  장기사용 대체공사(이격거리)","2025-08-25 08:00","2025-10-02 18:00","2025-08-25 08:00","2025-10-02 18:00","연속"]
[174,"경남","직할","창공월림#1 T/L","월림S/S  장기사용 대체공사(이격거리)","월림S/S  장기사용 대체공사(이격거리)","2025-08-25 08:00","2025-10-02 18:00","2025-08-25 08:00","2025-10-02 18:00","연속"]
[175,"경남","직할","수출월림#1 T/L","월림S/S  장기사용 대체공사(3-1차분)","월림S/S  장기사용 대체공사(3-1차분) - 수출-월림T/L 인출변경 공사건","2025-08-25 08:00","2025-09-05 18:00","2025-08-25 08:00","2025-09-05 18:00","연속"]