{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":21,"n_cols":12,"rows_kept":21,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 9월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신안성신가평 T/L"," 신안성-신가평 등 12개T/L 추락방지시설 설치공사"," 신안성-신가평T/L 고광도 항공장애등 설치 : No.131,132,146,147","2025-09-01 07:00","2025-09-05 18:00","취소","취소","연속"]
[2,"경기","성남","신안성S/S #5 M.Tr","2025년 성남전력 변전협력회사 총액공사","#5M.Tr 보통점검","2025-09-01 09:00","2025-09-12 18:00","2025-09-01 09:00","2025-09-12 18:00","연속"]
[3,"충북","직할","신중부S/S CB 8872","신중부S/S  GIS 보통점검공사"," GIS 보통점검","2025-09-18 09:00","2025-09-19 18:00","2025-09-18 09:00","2025-09-19 18:00","연속"]
[4,"충북","직할","신중부S/S CB 8572","신중부S/S  GIS 보통점검공사"," GIS 보통점검","2025-09-25 09:00","2025-09-26 18:00","2025-09-25 09:00","2025-09-26 18:00","연속"]
[5,"충북","직할","신중부S/S CB 8771","신중부S/S  GIS 보통점검공사"," GIS 보통점검","2025-09-29 09:00","2025-09-30 18:00","2025-09-29 09:00","2025-09-30 18:00","연속"]
[6,"충북","직할","신서산신중부#2 T/L","신중부S/S  GIS 보통점검공사"," GIS 보통점검","2025-09-22 09:00","2025-09-24 18:00","2025-09-22 09:00","2025-09-24 18:00","연속"]
[7,"충북","직할","신중부신안성#1 T/L","24~25 충북 직할 가공송전 협력회사 총액공사","풍소음 항공장애표시구 교체","2025-09-11 07:00","2025-09-11 18:00","취소","취소","연속"]
[8,"충북","직할","신중부신안성#2 T/L","24~25 충북 직할 가공송전 협력회사 총액공사","풍소음 항공장애표시구 교체","2025-09-12 07:00","2025-09-12 18:00","취소","취소","연속"]
[9,"대전세종충남","서산","신서산S/S CB 8400","신서산 8401 DS 개방불가 공장입고수리","(즉시가압불가) 신서산S/S  8401 DS 개방불가로 인한 제작사 공장입고수리","2025-09-22 09:30","2025-11-28 18:00","2025-09-22 09:30","2025-11-28 18:00","연속"]
[10,"경북","영주","신한울N/P #2 M.Tr","#2M.Tr 불량조치","○ B-2 42A 교체 ○ 220V 역가압 관련 회로개선","2025-09-04 09:00","2025-09-05 18:00","취소","취소","연속"]
[11,"부산울산","동부산","신고리N/P #4 M.Tr","25년 하반기 신고리S/S  GIS 정밀보통점검공사","신고리S/S 8671,8600 보통점검","2025-09-15 09:00","2025-09-19 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[12,"부산울산","동부산","신고리N/P #1 BUS","신고리S/S 모선보호반 86T 교체","신고리S/S 모선보호반 86T 교체","2025-09-08 09:00","2025-09-09 18:00","취소","취소","연속"]
[13,"부산울산","동부산","신고리N/P #2 BUS","신고리S/S 모선보호반 86T 교체","신고리S/S 모선보호반 86T 교체","2025-09-11 09:00","2025-09-12 18:00","취소","취소","연속"]
[14,"부산울산","동부산","북경남신고리NP#2 T/L","북경남-신고리#2T/L, 신고리S/S 83Bay B/F PNL 교체","북경남-신고리#2T/L PNL, 신고리S/S 83Bay B/F PNL 교체","2025-09-22 09:00","2025-10-02 18:00","취소","취소","연속"]
[15,"경남","함안","북경남S/S #4 M.Tr"," 북경남S/S #2M.Tr 증설공사","북경남 소내 변경에 따른 #4M.Tr 3차 전력케이블 분리","2025-09-18 09:00","2025-09-18 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[16,"경남","함안","북경남S/S #1 BUS"," 북경남S/S #2M.Tr 증설공사"," #1BUS 모선 도킹 작업","2025-09-22 09:00","2025-10-04 18:00","2025-09-22 09:00","2025-10-04 18:00","연속"]
[{"$nulls":5}," "]

{"sheet":"345설비","index":1,"n_rows":437,"n_cols":12,"rows_kept":437,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2025년도 9월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","미금성동#3 T/L","2025년 성동P/O 변전협력회사 공사","-  GIS 보통점검","2025-09-22 09:00","2025-09-24 18:00","2025-09-22 09:00","2025-09-24 18:00","연속"]
[2,"서울","성동","성동S/S #4 M.Tr","2025년 성동P/O 변전협력회사 공사","-  M.Tr B상 정밀점검 -  GIS 보통점검 - 154kV GIS 조작시험","2025-09-22 09:00","2025-09-27 18:00","2025-09-22 09:00","2025-09-27 18:00","연속"]
[3,"서울","성동","성동S/S CB 7500","2025년 성동P/O 변전협력회사 공사","-  GIS 보통점검","2025-09-22 09:00","2025-09-24 18:00","2025-09-22 09:00","2025-09-24 18:00","연속"]
[4,"서울","중부","중부S/S CB 7200","2025년 중부전력지사 변전협력회사 공사","GIS 보통점검","2025-09-23 10:00","2025-09-23 18:00","2025-09-23 10:00","2025-09-23 18:00","연속"]
[5,"서울","중부","중부S/S #1 Sh.R CB","2025년 중부전력지사 변전협력회사 공사","유면계 교체","2025-09-22 10:00","2025-09-22 18:00","2025-09-22 10:00","2025-09-22 18:00","연속"]
[6,"서울","중부","중부S/S #1 M.Tr","2025년 중부전력지사 변전협력회사 공사","- 3차 PT 위치 조정 - A상 96G 점검","2025-09-24 10:00","2025-09-25 18:00","2025-09-24 10:00","2025-09-25 18:00","연속"]
[7,"서울","중부","중부S/S #4 M.Tr","2025년 중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV #65BUS 모선 무부하가압용","2025-09-24 17:00","2025-09-25 09:00","2025-09-24 17:00","2025-09-25 09:00","연속"]
[8,"서울","중부","중부S/S #3 M.Tr","2025년 중부전력지사 변전협력회사 공사","- 1차 GIS 보통점검","2025-09-26 10:00","2025-09-26 18:00","2025-09-26 10:00","2025-09-26 18:00","연속"]
[9,"서울","중부","중부S/S CB 7100","2025년 중부전력지사 변전협력회사 공사","GIS 보통점검","2025-09-22 10:00","2025-09-22 18:00","2025-09-22 10:00","2025-09-22 18:00","연속"]
[10,"남서울","강남","신양재S/S #3 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사"," 노후 CT 집합반 교체","2025-09-24 09:00","2025-09-24 18:00","취소","취소","연속"]
[11,"남서울","강남","신양재S/S #1 BUS","24-25년도 강남전력지사 변전협력회사 총액공사"," 노후 CT 집합반 교체","2025-09-24 09:00","2025-09-24 18:00","취소","취소","연속"]
[12,"남서울","강남","신양재S/S #2 BUS","24-25년도 강남전력지사 변전협력회사 총액공사"," 노후 CT 집합반 교체","2025-09-23 09:00","2025-09-23 18:00","취소","취소","연속"]
[13,"남서울","강남","신양재S/S #1 BUS","24-25년도 강남전력지사 변전협력회사 총액공사"," 노후 CT 집합반 교체","2025-09-22 09:00","2025-09-22 18:00","취소","취소","연속"]
[14,"남서울","강남","신양재S/S #3 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사"," 노후 CT 집합반 교체","2025-09-22 09:00","2025-09-22 18:00","취소","취소","연속"]
[15,"남서울","강남","신양재S/S #4 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사"," 노후 CT 집합반 교체","2025-09-23 09:00","2025-09-23 18:00","취소","취소","연속"]
[16,"남서울","동서울","동서울미금#1 T/L","'24~'25년도 동서울전력지사 가공송전 협력회사 공사"," 동서울-미금#1T/L 피뢰기 설치 및 항공장애구 교체 공사","2025-09-29 07:00","2025-09-29 18:00","2025-09-28 07:00","2025-09-28 18:00","연속"]
[17,"남서울","동서울","곤지암동서울#1 T/L"," 동서울변전소 옥내화 전력구공사","동서울변전소 옥내화에 따른 구내 전력구공사 - 활선간섭 구간 약 180m","2025-09-01 08:00","2025-11-03 18:00","취소","취소","연속"]
[18,"남서울","동서울","곤지암동서울#1 T/L","'24~'25년도 동서울전력지사 가공송전 협력회사 공사"," 곤지암-동서울 #1T/L 피뢰기 설치공사 및 이도조정 공사","2025-09-02 07:00","2025-09-08 18:00","2025-09-15 07:00","2025-09-19 18:00","연속"]
[19,"남서울","동서울","곤지암동서울#2 T/L","2025년 가공송전 순시점검 위탁공사","지장이설 송전선로 구간 (No.65~No.67) 초기점검 시행","2025-09-09 07:00","2025-09-09 18:00","2025-09-05 07:00","2025-09-05 18:00","연속"]
[20,"남서울","동서울","동서울미금#2 T/L","'24~'25년도 동서울전력지사 가공송전 협력회사 공사"," 동서울-미금#2T/L 항공장애구 교체 공사","2025-09-30 09:00","2025-09-30 18:00","2025-09-29 09:00","2025-09-29 18:00","연속"]
[21,"남서울","영등포","신광명S/S SEC CB 75760"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-09-02 09:00","2025-11-28 18:00","취소","취소","연속"]
[22,"남서울","영등포","신광명S/S #75 BUS"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-09-02 09:00","2025-11-28 18:00","취소","취소","연속"]
[23,"남서울","영등포","신광명S/S #70 BUS"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-09-01 09:00","2025-09-02 09:00","취소","취소","연속"]
[24,"남서울","영등포","신광명S/S #2 M.Tr","2025년 영등포전력지사 변전협력회사 총액공사","신광명S/S #2M.Tr 3차측 GPT 점검","2025-03-07 09:00","2025-03-07 18:00","취소","취소","연속"]
[25,"남서울","영등포","서서울신광명#2 T/L"," 서서울-신광명T/L 임시철탑 이설 및 보강공사","No.25 철탑보강, No.26 임시이설, No.27 철탑 인클로징","2025-09-21 09:00","2025-09-27 18:00","2025-09-21 09:00","2025-09-27 18:00","연속"]
[26,"남서울","영등포","서서울신광명#1 T/L"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-09-28 09:00","2025-11-28 18:00","2025-09-28 09:00","2025-11-28 18:00","연속"]
[27,"남서울","영등포","신광명S/S #76 BUS"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-09-02 09:00","2025-09-12 18:00","취소","취소","연속"]
[28,"남서울","영등포","신광명S/S #1 M.Tr","신광명S/S #1M.Tr 주변압기 하자점검"," 주변압기 하자점검","2025-09-22 09:00","2025-09-24 18:00","취소","취소","연속"]
[29,"남서울","영등포","신광명S/S #4 M.Tr","신광명S/S #4M.Tr 누기 보수","신광명S/S #4M.Tr 누기 보수","2025-09-25 09:00","2025-09-26 18:00","취소","취소","연속"]
[30,"남서울","영등포","신광명S/S CB 7472","24~25년 영등포전력지사 변전협력회사 공사"," GCB 하자점검(7472)","2025-09-08 09:00","2025-09-09 18:00","2025-09-08 09:00","2025-09-09 18:00","연속"]
[31,"남서울","영등포","신광명S/S CB 7572","24~25년 영등포전력지사 변전협력회사 공사"," GCB 하자점검(7572)","2025-09-10 09:00","2025-09-11 18:00","2025-09-10 09:00","2025-09-11 18:00","연속"]
[32,"남서울","영등포","서서울신광명#1 T/L"," 서서울-신광명T/L 임시철탑 이설 및 보강공사","No.25 철탑보강, No.26 임시이설, No.27 철탑 인클로징","2025-09-13 09:00","2025-09-20 18:00","2025-09-13 09:00","2025-09-20 18:00","연속"]
[33,"인천","김포","가정개폐소 CB 7372","가정개폐소  가정-갈산 #2T/L 1차 GIS 보통점검","가정개폐소  가정-갈산 #2T/L 1차 (7372) GIS 보통점검","2025-09-24 10:00","2025-09-24 18:00","2025-09-24 10:00","2025-09-24 18:00","연속"]
[34,"인천","김포","가정개폐소 CB 7100","가정개폐소  7100 GIS 보통점검","가정개폐소  #2Sh.R - 3Sh.R TIE GIS 보통점검","2025-09-23 10:00","2025-09-23 18:00","2025-09-23 10:00","2025-09-23 18:00","연속"]
[35,"인천","김포","가정개폐소 CB 7172","가정개폐소  7172 GIS 보통점검","가정개폐소  #3Sh.R 1차 GIS 보통점검","2025-09-22 10:00","2025-09-22 18:00","2025-09-22 10:00","2025-09-22 18:00","연속"]
[36,"인천","김포","가정개폐소 CB 7171","가정개폐소  7171 GIS 보통점검","가정개폐소  #2Sh.R 1차 GIS 보통점검","2025-09-19 10:00","2025-09-19 18:00","2025-09-19 10:00","2025-09-19 18:00","연속"]
[37,"인천","김포","신김포S/S CB 7600","신김포S/S  7600 CB 보통점검","신김포S/S  #3Sh.R-TIE GIS(7600) 보통점검 - 비상시, 상시보조계전기 교체 병행","2025-09-15 10:00","2025-09-15 18:00","2025-09-15 10:00","2025-09-15 18:00","연속"]
[38,"인천","김포","신김포S/S CB 7171","신김포S/S  7171 CB 보통점검","신김포S/S  #1 Sh.R 1차 GIS(7171) 보통점검 -비상시, 상시보조계전기 교체","2025-09-16 10:00","2025-09-16 18:00","2025-09-16 10:00","2025-09-16 18:00","연속"]
[39,"인천","김포","신김포S/S CB 7100","신김포S/S  7100 CB 보통점검","신김포S/S  #1 Sh.R TIE GIS(7100) 보통점검","2025-09-17 10:00","2025-09-17 18:00","2025-09-17 10:00","2025-09-17 18:00","연속"]
[40,"인천","김포","신김포S/S CB 7671","신김포S/S  7671 CB 과열 상시여자보조계전기 긴급교체","신김포S/S  7671 CB 과열 상시여자보조계전기 긴급교체","2025-09-12 10:00","2025-09-12 18:00","2025-09-30 10:00","2025-09-30 18:00","연속"]
[41,"인천","김포","신김포S/S CB 7572","신김포S/S  7572 CB 과열 상시여자보조계전기 긴급교체","신김포S/S  7572 CB 과열 상시여자보조계전기 긴급교체","2025-09-11 10:00","2025-09-11 18:00","2025-09-29 10:00","2025-09-29 18:00","연속"]
[42,"인천","김포","신김포S/S #3 M.Tr","신김포S/S  #3M.Tr 1차, 2차 GIS 하자점검","신김포S/S  #3M.Tr 1차, 2차 GIS 하자점검","2025-09-18 10:00","2025-09-18 18:00","2025-09-18 10:00","2025-09-18 18:00","연속"]
[43,"인천","김포","신김포S/S CB 7272","신김포S/S  7272 CB 과열 상시여자보조계전기 긴급교체","신김포S/S  7272 CB 과열 상시여자보조계전기 긴급교체","2025-09-09 10:00","2025-09-09 18:00","2025-09-09 10:00","2025-09-09 18:00","연속"]
[44,"인천","김포","신김포S/S CB 7500","신김포S/S  7500 CB 과열 상시여자보조계전기 긴급교체","신김포S/S  7500 CB 과열 상시여자보조계전기 긴급교체","2025-09-10 10:00","2025-09-10 18:00","2025-09-26 10:00","2025-09-26 18:00","연속"]
[45,"인천","부평","서인천C/C CB 7271"," 신경서-서인천CC T/L 7271 GIS 보통점검"," 신경서-서인천CC T/L 7271 GIS 보통점검","2025-09-20 09:00","2025-09-20 18:00","2025-09-20 09:00","2025-09-20 18:00","연속"]
[46,"인천","부평","서인천C/C CB 7577"," #75-77 CLR #7577 GIS 조작, 전자변(L타입)"," #75-77 CLR #7577 GIS 조작, 전자변(L타입)","2025-09-09 09:00","2025-09-09 18:00","취소","취소","연속"]
[47,"인천","부평","서인천C/C CB 7200","신경서서인천CCT/L-#2M.Tr 1차 TIE 7200 GIS 보통점검","신경서서인천CCT/L-#2M.Tr 1차 TIE 7200 GIS 보통점검","2025-09-21 09:00","2025-09-21 18:00","취소","취소","연속"]
[48,"인천","부평","서인천C/C CB 7272"," #2 M.Tr 1차 7272 GIS 보통점검"," #2 M.Tr 1차 7272 GIS 보통점검","2025-09-10 09:00","2025-09-10 18:00","2025-09-25 09:00","2025-09-25 18:00","연속"]
[49,"인천","부평","서인천C/C CB 7777"," #75-77 CLR #7777 GIS 조작, 전자변(L타입)"," #75-77 CLR #7777 GIS 조작, 전자변(L타입)","2025-09-09 09:00","2025-09-09 18:00","취소","취소","연속"]
[50,"인천","부평","신가좌S/S #1 BUS","신가좌S/S 345㎸ 용량부족 GIS 교체공사","신가좌S/S 345㎸ 용량부족 GIS 교체공사 - 실부하 가압 관련 앵글 측정","2025-09-26 13:00","2025-09-26 16:00","취소","취소","연속"]
[51,"인천","부평","신가좌S/S #2 BUS","신가좌S/S 345㎸ 용량부족 GIS 교체공사","신가좌S/S 345㎸ 용량부족 GIS 교체공사 - 실부하 가압 관련 앵글 측정","2025-09-26 16:00","2025-09-26 18:00","취소","취소","연속"]
[52,"인천","부평","신경서S/S CB 7472"," 신경서-서인천CCT/L 7472 GIS 보통점검"," 신경서-서인천CCT/L 7472 GIS 보통점검","2025-09-22 09:00","2025-09-22 18:00","2025-09-22 09:00","2025-09-22 18:00","연속"]
[53,"인천","부평","신경서S/S CB 7271","신경서S/S 신경서-인천CC#1T/L 7271 GIS 조작시험","신경서S/S 신경서-인천CC#1T/L 7271 GIS 조작시험","2025-09-01 09:00","2025-09-01 18:00","2025-09-01 09:00","2025-09-01 18:00","연속"]
[54,"인천","부평","신경서S/S CB 7472"," 신경서-서인천CCT/L TIE 7400 GIS 보통점검"," 신경서-서인천CCT/L TIE 7400 GIS 보통점검","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[55,"인천","부평","신경서S/S CB 7572"," #3 M.Tr 1차 7572 GIS 보통점검"," #3 M.Tr 1차 7572 GIS 보통점검","2025-09-24 09:00","2025-09-24 18:00","취소","취소","연속"]
[56,"인천","부평","신경서S/S #1 M.Tr"," #1M.Tr 부싱유 채유"," #1M.Tr 부싱유 채유","2025-09-29 09:00","2025-09-29 18:00","취소","취소","연속"]
[57,"인천","부평","신경서S/S CB 7272"," #2 M.Tr 1차 7272 GIS 보통점검"," #2 M.Tr 1차 7272 GIS 보통점검","2025-09-30 09:00","2025-09-30 18:00","취소","취소","연속"]
[58,"인천","부평","신인천C/C CB 7671","신인천C/C  3MT001 7671 GIS 보통점검","신인천C/C  3MT001 7671 GIS 보통점검","2025-09-16 09:00","2025-09-16 18:00","2025-09-16 09:00","2025-09-16 18:00","연속"]
[59,"인천","부평","신인천C/C SEC CB 76770","신인천복합S/Y 75-76, 76-77 SEC B/F 보호반 교체 공사","신인천복합S/Y 75-76, 76-77 SEC B/F 보호반 교체 공사","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[60,"인천","부평","신인천C/C CB 7772","신인천C/C  4MT101 7772 GIS 보통점검","신인천C/C  4MT101 7772 GIS 보통점검","2025-09-08 09:00","2025-09-08 18:00","2025-09-08 09:00","2025-09-08 18:00","연속"]
[61,"인천","부평","신인천C/C SEC CB 75760","신인천복합S/Y 75-76, 76-77 SEC B/F 보호반 교체 공사","신인천복합S/Y 75-76, 76-77 SEC B/F 보호반 교체 공사","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[62,"인천","부평","신인천C/C SEC CB 70710","신인천복합S/Y 70-71, 71-72 SEC B/F 보호반 교체 공사","신인천복합S/Y 70-71, 71-72 SEC B/F 보호반 교체 공사","2025-09-01 09:00","2025-09-05 18:00","취소","취소","연속"]
[63,"인천","부평","신인천C/C SEC CB 71720","신인천복합S/Y 70-71, 71-72 SEC B/F 보호반 교체 공사","신인천복합S/Y 70-71, 71-72 SEC B/F 보호반 교체 공사","2025-09-01 09:00","2025-09-05 18:00","취소","취소","연속"]
[64,"인천","부평","인천C/C CB 7200"," 신경서인천CC#1T/L TIE 7200 GIS 보통점검"," 신경서인천CC#1T/L TIE 7200 GIS 보통점검","2025-09-10 09:00","2025-09-10 18:00","2025-09-10 09:00","2025-09-10 18:00","연속"]
[65,"인천","부평","인천C/C CB 7271"," 신경서-인천CC#1T/L 7271 GIS 보통점검"," 신경서-인천CC#1T/L 7271 GIS 보통점검","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[66,"인천","부평","가정인천CC#2 T/L"," 가정인천CC#2T/L 염해방지 코팅"," 가정인천CC#2T/L 염해방지 코팅","2025-09-27 07:00","2025-09-27 20:00","2025-09-27 07:00","2025-09-27 20:00","연속"]
[67,"인천","부평","가정인천CC#1 T/L"," 가정인천CC#1T/L 염해방지 코팅"," 가정인천CC#1T/L 염해방지 코팅","2025-09-28 07:00","2025-09-28 20:00","2025-09-28 07:00","2025-09-28 20:00","연속"]
[68,"인천","부평","인천C/C #1 Sh.R CB"," #1SH.R 누기 보수"," #1SH.R 누기 보수","2025-09-28 09:00","2025-10-01 18:00","취소","취소","연속"]
[69,"인천","부평","인천C/C #2 M.Tr"," #2 TIE Tr 보통점검"," #2 TIE Tr 보통점검, 기계적보호장치 교체, 2차 6244GIS 조작시험, 3차 4289 GIS 조작시험, 부싱유 채유","2025-09-29 09:00","2025-10-03 18:00","2025-09-29 09:00","2025-10-03 18:00","연속"]
[70,"인천","부평","신경서포스코CC#1 T/L","포스코S/Y 73Bay B/F 보호반 대체","포스코S/Y 73Bay B/F 보호반 대체","2025-09-08 09:00","2025-09-12 18:00","2025-09-08 09:00","2025-09-12 18:00","연속"]
[71,"인천","부평","포스코C/C CB 7372","포스코S/Y 73Bay B/F 보호반 대체","포스코S/Y 73Bay B/F 보호반 대체","2025-09-08 09:00","2025-09-12 18:00","2025-09-08 09:00","2025-09-12 18:00","연속"]
[72,"인천","부평","포스코CC인천CC#2 T/L","인천CC-포스코S/Y #2T/L TOP HAT 볼트교체 및 보통점검","인천CC-포스코S/Y #2T/L TOP HAT 볼트교체,  포스코S/Y-인천CC#2T/L 7A72 GIS 보통","2025-09-21 09:00","2025-09-21 18:00","2025-09-21 09:00","2025-09-21 18:00","연속"]
[73,"인천","부평","포스코C/C #70 BUS"," #70BUS 모선보호반 교체"," #70BUS 모선보호반 교체","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[74,"인천","부평","포스코C/C #75 BUS"," #75BUS 모선보호반 교체"," #75BUS 모선보호반 교체","2025-09-29 09:00","2025-10-03 18:00","2025-09-29 09:00","2025-10-03 18:00","연속"]
[75,"인천","시흥","신시흥영흥TP#1 T/L","신시흥S/S 362kV GIS 정밀점검 공사(7771) 무부하가압","신시흥S/S  7771 CB 정밀점검 공사 무부하가압","2025-09-26 10:00","2025-09-26 14:00","취소","취소","연속"]
[76,"인천","시흥","신시흥#1S/S CB 7771","신시흥S/S 362kV GIS 정밀점검 공사(7771)","신시흥S/S 7771 CB 정밀점검 공사","2025-09-22 08:00","2025-09-26 18:00","2025-09-22 08:00","2025-09-26 18:00","연속"]
[77,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥S/S - 신송도S/S 전력구공사","개착식전력구 282m","2025-09-01 09:00","2025-11-30 18:00","취소","취소","연속"]
[78,"인천","시흥","신시흥영흥TP#2 T/L","영흥#1S/Y 362kV GIS 정밀점검 공사(7472) 무부하가압","영흥#1S/Y  7472 CB 정밀점검 공사 무부하가압","2025-09-19 10:00","2025-09-19 14:00","취소","취소","연속"]
[79,"인천","시흥","영흥T/P CB 7472","영흥#1S/Y 362kV GIS 정밀점검 공사(7472)","영흥#1S/Y  7472 CB 정밀점검 공사","2025-09-15 08:00","2025-09-19 18:00","2025-09-15 08:00","2025-09-19 18:00","연속"]
[80,"인천","시흥","영흥T/P CB 7372","영흥#1S/Y 362kV GIS 정밀점검 공사(7372)","영흥#1S/Y  7372 CB 정밀점검 공사","2025-09-08 08:00","2025-09-12 18:00","2025-09-08 08:00","2025-09-12 18:00","연속"]
[81,"인천","시흥","영흥1TP영흥2TP#2 T/L","영흥#1S/Y 362kV GIS 정밀점검 공사(7371) 무부하가압","영흥#1S/Y  7371 CB 정밀점검 공사 무부하가압","2025-09-05 10:00","2025-09-05 14:00","취소","취소","연속"]
[82,"인천","시흥","영흥T/P #70 BUS","영흥#1S/Y 362kV GIS 정밀점검 공사(7371) 무부하가압","영흥#1S/Y  7371 CB 정밀점검 공사 무부하가압(#1Bus)","2025-09-05 10:00","2025-09-05 14:00","취소","취소","연속"]
[83,"인천","시흥","영흥T/P CB 7371","영흥#1S/Y 362kV GIS 정밀점검 공사(7371)","영흥#1S/Y  7371 CB 정밀점검 공사","2025-09-01 08:00","2025-09-05 18:00","취소","취소","연속"]
[84,"인천","직할","갈산S/S #2 M.Tr","갈산S/S #2M.Tr, 2차 GIS, 3차 GIS 보통점검","갈산S/S #2M.Tr 보통점검, 2차 GIS 보통점검, #1S.Tr GIS 보통점검, #1S.Tr 보통점검 및 예비전원D/L 보통점검","2025-09-17 09:30","2025-09-18 18:00","2025-09-17 09:30","2025-09-18 18:00","연속"]
[85,"인천","직할","갈산S/S #3 M.Tr","갈산S/S #3M.Tr, 2차 GIS, 3차 GIS 보통점검","갈산S/S #3M.Tr 보통점검, 2차 GIS 보통점검, #2S.Tr GIS 보통점검 및 #2S.Tr 보통점검","2025-09-29 09:30","2025-09-30 18:00","2025-09-29 09:30","2025-09-30 18:00","연속"]
[86,"인천","직할","갈산S/S #1 M.Tr","갈산S/S #1M.Tr 보통점검 및 2차 GIS 보통점검","갈산S/S #1M.Tr 보통점검 및 2차 GIS 보통점검","2025-09-15 09:30","2025-09-16 18:00","2025-09-15 09:30","2025-09-16 18:00","연속"]
[87,"인천","직할","갈산S/S #4 M.Tr","갈산S/S 종합예방증설 관련 부싱 시험탭 규격측정","부싱누설전류 진단장치 제작관련 현장 설비확인","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[88,"인천","직할","서인천CC신부평#1 T/L","신부평S/S 71 Bay B/F PNL 교체공사","신부평S/S 71 Bay B/F PNL 교체공사","2025-09-15 09:00","2025-09-18 18:00","2025-09-15 09:00","2025-09-18 18:00","연속"]
[89,"인천","직할","서인천CC신부평#4 T/L","신부평S/S 74 Bay B/F PNL 등 교체공사","신부평S/S 74 Bay B/F PNL 및 서인천CC신부평#4T/L 보호배전반 교체공사","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[90,"인천","직할","서인천CC신부평#2 T/L","신부평S/S 72 Bay B/F PNL 교체공사","신부평S/S 72 Bay B/F PNL 교체공사","2025-09-08 09:00","2025-09-11 18:00","2025-09-08 09:00","2025-09-11 18:00","연속"]
[91,"인천","직할","신부평S/S #2 M.Tr","신부평S/S 72 Bay B/F PNL 교체공사","신부평S/S 72 Bay B/F PNL 교체공사","2025-09-08 09:00","2025-09-11 18:00","2025-09-08 09:00","2025-09-11 18:00","연속"]
[92,"인천","직할","서인천CC신부평#3 T/L","신부평S/S 73 Bay B/F PNL 교체공사","신부평S/S 73 Bay B/F PNL 교체공사","2025-09-29 09:00","2025-10-02 18:00","2025-09-29 09:00","2025-10-02 18:00","연속"]
[93,"인천","직할","신부평S/S #3 M.Tr","신부평S/S 73 Bay B/F PNL 교체공사","신부평S/S 73 Bay B/F PNL 교체공사","2025-09-29 09:00","2025-10-02 18:00","2025-09-29 09:00","2025-10-02 18:00","연속"]
[94,"인천","직할","신부평S/S #4 M.Tr","신부평S/S 74 Bay B/F PNL 등 교체공사","신부평S/S 74 Bay B/F PNL 및 서인천CC신부평#4T/L 보호배전반 교체공사","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[95,"인천","직할","신부평S/S #1 M.Tr","신부평S/S 71 Bay B/F PNL 교체공사","신부평S/S 71 Bay B/F PNL 교체공사","2025-09-15 09:00","2025-09-18 18:00","2025-09-15 09:00","2025-09-18 18:00","연속"]
[96,"경기북부","고양","신덕은S/S #3 M.Tr","24-25년 고양전력 변전협력회사 공사","신덕은S/S  #3M.Tr GPT 보통점검","2025-09-22 09:00","2025-09-22 18:00","2025-09-08 09:00","2025-09-08 18:00","연속"]
[97,"경기북부","고양","신덕은동두천CC#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치(수평) 설치, 폴리머점퍼지지애자 설치","2025-09-22 07:00","2025-09-26 17:00","2025-09-22 07:00","2025-09-26 17:00","연속"]
[98,"경기북부","고양","신덕은S/S #2 M.Tr","24-25년 고양전력 변전협력회사 공사","신덕은S/S  #2M.Tr 3차 LA 보통점검","2025-09-04 09:00","2025-09-04 18:00","2025-09-04 09:00","2025-09-04 18:00","연속"]
[99,"경기북부","고양","신덕은S/S #4 M.Tr","24~25년 고양전력지사 변전협력회사 공사","362kV GIS 보통점검(7400)","2025-09-23 09:00","2025-09-23 18:00","2025-09-17 09:00","2025-09-17 18:00","연속"]
[100,"경기북부","고양","신덕은S/S #1 M.Tr","24-25년 고양전력 변전협력회사 공사","신덕은S/S  #1M.Tr,B상 보통점검","2025-09-02 09:00","2025-09-03 18:00","2025-09-02 09:00","2025-09-03 18:00","연속"]
[101,"경기북부","고양","신파주신덕은#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치설치","2025-09-29 07:00","2025-10-01 17:00","2025-09-29 07:00","2025-10-01 17:00","연속"]
[102,"경기북부","구리","신의정부미금#2 T/L","24~25년도 동서울전력지사 가공송전 협력회사 공사"," 동서울-미금#1T/L 피뢰기 설치 및 항공장애구 교체공사","2025-09-29 07:00","2025-09-29 18:00","2025-09-28 07:00","2025-09-28 18:00","연속"]
[103,"경기북부","구리","미금성동#1 T/L"," 미금 용량부족 차단기 대체공사(#1,2Sh.R 직결)"," #1,2Sh.R - 미금성동#1T/L 직결","2025-09-15 09:00","2025-09-30 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[104,"경기북부","구리","미금S/S CB 7400","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검(7400)","2025-09-30 09:00","2025-09-30 18:00","2025-09-30 09:00","2025-09-30 18:00","연속"]
[105,"경기북부","구리","미금S/S CB 7471","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검(7471)","2025-09-29 09:00","2025-09-29 18:00","2025-09-29 09:00","2025-09-29 18:00","연속"]
[106,"경기북부","구리","미금S/S CB 7079"," 미금 용량부족 차단기 대체공사(#1,2Sh.R 직결)"," #1,2Sh.R - 미금성동#1T/L 직결","2025-09-15 09:00","2025-09-19 18:00","2025-09-08 09:00","2025-09-12 18:00","연속"]
[107,"경기북부","구리","미금S/S #1 Sh.R CB"," 미금 용량부족 차단기 대체공사(#1,2Sh.R 직결)"," #1,2Sh.R - 미금성동#1T/L 직결","2025-09-15 09:00","2025-09-30 18:00","2025-09-08 09:00","2025-09-26 18:00","연속"]
[108,"경기북부","구리","미금S/S #2 Sh.R CB"," 미금 용량부족 차단기 대체공사(#1,2Sh.R 직결)"," #1,2Sh.R - 미금성동#1T/L 직결","2025-09-15 09:00","2025-09-30 18:00","2025-09-08 09:00","2025-09-26 18:00","연속"]
[109,"경기북부","구리","미금S/S #5 Sh.R CB"," 미금 용량부족 차단기 대체공사(#1,2Sh.R 직결)"," #1,2Sh.R - 미금성동#1T/L 직결","2025-09-15 09:00","2025-09-19 18:00","2025-09-08 09:00","2025-09-12 18:00","연속"]
[110,"경기북부","구리","신가평S/S CB 7671","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검(7671)","2025-09-24 09:00","2025-09-24 18:00","2025-09-24 09:00","2025-09-24 18:00","연속"]
[111,"경기북부","구리","신가평미금#1 T/L"," 신가평-미금T/L 용량대체공사","(지중)  XLPE 2500 2C-0.9KM (가공)  HCSC/TW 37.2KM (전력구) 동이패, 서이패C/T 인출전력구 공사","2025-09-01 09:00","2025-11-30 18:00","취소","취소","연속"]
[112,"경기북부","구리","신가평신의정부#1 T/L","신가평S/S  GIS 인출변경공사(#73, 76BAY)","신가평S/S  GIS 인출변경공사(#73, 76BAY)","2025-09-02 09:00","2025-12-05 18:00","2025-09-02 09:00","2025-12-05 18:00","연속"]
[113,"경기북부","구리","신가평S/S CB 7371","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검(7371)","2025-09-25 09:00","2025-09-25 18:00","2025-09-25 09:00","2025-09-25 18:00","연속"]
[114,"경기북부","구리","신포천S/S #3 M.Tr","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  M.Tr 점검","2025-09-25 09:00","2025-09-29 18:00","2025-09-25 09:00","2025-09-29 18:00","연속"]
[115,"경기북부","구리","신포천S/S #2 M.Tr","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  M.Tr 점검","2025-09-22 09:00","2025-09-24 18:00","2025-09-22 09:00","2025-09-24 18:00","연속"]
[116,"경기북부","구리","신포천S/S CB 7271","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검(7271)","2025-09-16 09:00","2025-09-16 18:00","2025-09-16 09:00","2025-09-16 18:00","연속"]
[117,"경기북부","구리","신포천S/S #4 M.Tr","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  M.Tr 점검","2025-09-30 09:00","2025-10-02 18:00","2025-09-30 09:00","2025-10-02 18:00","연속"]
[118,"경기북부","구리","신포천S/S #1 M.Tr","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  M.Tr 점검","2025-09-17 09:00","2025-09-19 18:00","2025-09-17 09:00","2025-09-19 18:00","연속"]
[119,"경기북부","직할","신포천동두천CC#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 신덕은-동두천CC#2T/L 불량애자 교체","2025-09-22 07:00","2025-09-22 16:00","2025-09-21 07:00","2025-09-21 16:00","연속"]
[120,"경기북부","직할","신덕은동두천CC#1 T/L","동두천C/C  동두천CC-양주T/L SW증설공사","- 동두천CC 362kV 2CB 증설 - 인출 GIB 설치 - 기기 기초 및 기타부대공사","2025-09-01 09:00","2025-09-19 18:00","2025-09-01 09:00","2025-09-19 18:00","연속"]
[121,"경기북부","직할","신의정부S/S CB 7200","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7200 GIS 보통점검","2025-09-05 09:00","2025-09-05 18:00","2025-09-05 09:00","2025-09-05 18:00","연속"]
[122,"경기북부","직할","신의정부S/S CB 7300","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7300 GIS 보통점검","2025-09-09 09:00","2025-09-09 18:00","2025-09-09 09:00","2025-09-09 18:00","연속"]
[123,"경기북부","직할","신의정부S/S CB 7600","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7600 TIE GIS 보통점검 및 전자변 교체","2025-09-02 09:00","2025-09-02 18:00","2025-09-02 09:00","2025-09-02 18:00","연속"]
[124,"경기북부","직할","신의정부S/S CB 7372","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7372 GIS 보통점검","2025-09-10 09:00","2025-09-10 18:00","2025-09-10 09:00","2025-09-10 18:00","연속"]
[125,"경기북부","직할","신의정부S/S CB 7471","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7471 GIS 보통점검","2025-09-11 09:00","2025-09-11 18:00","2025-09-11 09:00","2025-09-11 18:00","연속"]
[126,"경기북부","직할","신의정부S/S CB 7672","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7672 GIS 보통점검","2025-09-15 09:00","2025-09-15 18:00","2025-09-15 09:00","2025-09-15 18:00","연속"]
[127,"경기북부","직할","신의정부S/S #1 Sh.R CB","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7479 GIS 보통점검","2025-09-16 09:00","2025-09-16 18:00","2025-09-16 09:00","2025-09-16 18:00","연속"]
[128,"경기북부","직할","신의정부S/S #2 Sh.R CB","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7779 GIS 보통점검","2025-09-17 09:00","2025-09-17 18:00","2025-09-17 09:00","2025-09-17 18:00","연속"]
[129,"경기북부","직할","신의정부S/S #3 Sh.R CB","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7879 GIS 보통점검","2025-09-18 09:00","2025-09-18 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[130,"경기북부","직할","신의정부S/S #3 M.Tr","24~25년 직할 변전협력회사 공사"," M.Tr 보호배전반 노후대체","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[131,"경기북부","직할","신의정부양주#2 T/L"," 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-양주#2 T/L No.1~97","2025-09-01 07:00","2025-09-12 18:00","2025-09-01 07:00","2025-09-12 18:00","연속"]
[132,"경기북부","직할","신의정부S/S CB 7371","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7371 GIS 보통점검","2025-09-04 09:00","2025-09-04 18:00","2025-09-04 09:00","2025-09-04 18:00","연속"]
[133,"경기북부","직할","신의정부S/S CB 7272","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7272 GIS 보통점검","2025-09-08 09:00","2025-09-08 18:00","2025-09-08 09:00","2025-09-08 18:00","연속"]
[134,"경기북부","직할","신의정부S/S CB 7771","경기북부 직할 및 양주전력TF 362kV GIS 정밀, 보통점검 공사","신의정부SS 7771 GIS 보통점검 및 전자변 교체","2025-09-01 09:00","2025-09-01 18:00","2025-09-01 09:00","2025-09-01 18:00","연속"]
[135,"경기북부","직할","신의정부양주#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 신의정부-양주T/L 피뢰기 설치","2025-09-15 07:00","2025-10-02 18:00","2025-09-15 07:00","2025-10-02 18:00","연속"]
[136,"경기북부","직할","양주중부#2 T/L","25년 경기북부 직할,양주TF 362kV GIS 보통점검공사","362kV GIS 7671, 7600 보통점검 및 전자변 교체","2025-09-24 09:00","2025-09-25 18:00","2025-09-24 09:00","2025-09-25 18:00","연속"]
[137,"경기북부","직할","양주중부#1 T/L","25년 경기북부 직할,양주TF 362kV GIS 보통점검공사","362kV GIS 7571, 7500 보통점검 및 전자변 교체","2025-09-22 09:00","2025-09-23 18:00","2025-09-29 09:00","2025-09-30 18:00","연속"]
[138,"경기","군포","서서울#2S/S CB 7D71","서서울2S/S 서서울2-화성#2T/L 7D71 GIS 보통점검","서서울2S/S 서서울2-화성#2T/L 7D71 GIS 보통점검","2025-09-02 09:00","2025-09-02 18:00","2025-09-02 09:00","2025-09-02 18:00","연속"]
[139,"경기","군포","서서울#2S/S CB 7C71","서서울2S/S 서서울2-화성#1T/L 7C71 GIS 보통점검","서서울2S/S 서서울2-화성#1T/L 7C71 GIS 보통점검","2025-09-01 09:00","2025-09-01 18:00","2025-09-01 09:00","2025-09-01 18:00","연속"]
[140,"경기","군포","화성서서울#2 T/L","서서울S/S 화성서서울#2T/L 7771GIS 보통점검,CVT및보호반대체","서서울S/S 화성-서서울#2T/L 7771 GIS 보통점검,CVT 대체,송전선로 보호반(1st,2nd) 대체","2025-09-01 09:00","2025-09-05 18:00","2025-09-01 09:00","2025-09-05 18:00","연속"]
[141,"경기","군포","신온양서서울#2 T/L","서서울S/S  신온양-서서울#2T/L GIS 보통점검,CVT대체","서서울S/S  신온양-서서울#2T/L 7772,7700 GIS 보통점검, CVT 대체","2025-09-29 09:00","2025-09-30 18:00","취소","취소","연속"]
[142,"경기","군포","서서울S/S #1 M.Tr","서서울S/S #1M.Tr GIS 조작,3차PT 초기,추락방지장치 설치","서서울S/S  #1M.Tr 7300,7372 GIS 조작시험, 3차 GPT 초기점검, 변압기 추락방지장치 설치 시행","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[143,"경기","군포","신시흥신안산#1 T/L"," 신시흥-신안산 #1 T/L 지장수목 벌채작업"," 신시흥-신안산 T/L 지장수목 벌채작업","2025-09-22 08:00","2025-09-22 17:00","2025-09-22 08:00","2025-09-22 17:00","연속"]
[144,"경기","군포","신시흥신안산#2 T/L"," 신시흥-신안산 #2 T/L 지장수목 벌채작업"," 신시흥-신안산 T/L 지장수목 벌채작업","2025-09-25 08:00","2025-09-25 17:00","2025-09-25 08:00","2025-09-25 17:00","연속"]
[145,"경기","동부","곤지암여주복합#1 T/L","추락방지장치 설치공사(곤지암여주CC #1)","곤지암여주CC #1T/L 추락방지장치 설치 80기(잔여 18기)","2025-09-04 07:00","2025-09-05 18:00","취소","취소","연속"]
[146,"경기","동부","곤지암여주복합#2 T/L","추락방지장치 설치공사(곤지암여주CC #2)","곤지암여주CC #2T/L 추락방지장치 설치 80기(잔여 7기)","2025-09-12 07:00","2025-09-12 18:00","취소","취소","연속"]
[147,"경기","동부","여주C/C CB 7171","여주CC 362kV GIS 7171,7100 PNL 내 히터설치","여주CC 362kV GIS 7171,7100 PNL 내 히터설치","2025-09-10 09:00","2025-09-10 14:00","2025-09-10 09:00","2025-09-10 16:00","연속"]
[148,"경기","동부","여주C/C CB 7100","여주CC 362kV GIS 7171,7100 PNL 내 히터설치","여주CC 362kV GIS 7171,7100 PNL 내 히터설치","2025-09-10 14:00","2025-09-10 18:00","2025-09-10 16:00","2025-09-10 20:00","연속"]
[149,"경기","성남","신성남S/S #5 M.Tr","2025년 성남전력 170kV GIS 정밀점검공사","gis 정밀점검","2025-09-06 09:00","2025-09-08 18:00","2025-09-06 09:00","2025-09-08 18:00","연속"]
[150,"경기","성남","신성남S/S #4 M.Tr","25년 성남전력 주변압기  보통, 154kV 정밀/보통점검공사","신성남) m.tr 보통점검","2025-09-13 09:00","2025-09-14 18:00","2025-09-13 09:00","2025-09-14 18:00","연속"]
[151,"경기","성남","서서울신광명#2 T/L","2025년 성남전력 변전협력회사 총액공사","7171 조작시험, 절연열화 7171 CVT A,B 하자점검","2025-09-24 09:00","2025-09-24 18:00","취소","취소","연속"]
[152,"경기","성남","신수원S/S #4 M.Tr","신수원S/S 154kV 계통조정공사(토목)"," #2M.Tr용 신규GIB 기초작업(토목) (자재반입 안전이격용 휴전필요)","2025-09-15 09:00","2025-09-28 18:00","2025-09-15 09:00","2025-09-28 18:00","연속"]
[153,"경기","성남","신안성S/S CB 7771","2025년 성남전력 362, 170kV GIS 보통점검공사","7771 gis 보통점검, 절연열화","2025-09-03 09:00","2025-09-03 18:00","2025-09-03 09:00","2025-09-03 18:00","연속"]
[154,"경기","성남","신안성신용인#1 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사 - 대상구간 :  신안성-신용인#1T/L No.49~66 ※  신안성-신성남T/L 4회선 구간","2025-09-15 07:00","2025-09-17 18:00","2025-09-15 07:00","2025-09-17 18:00","연속"]
[155,"경기","성남","신안성신성남#2 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사 - 대상구간 :  신안성-신성남#2T/L No.4~66 - 사전작업 : 추락방지장치 설치시행(수평) ※  신안성-신용인T/L 4회선 구간","2025-09-18 07:00","2025-09-30 18:00","2025-09-18 07:00","2025-09-30 18:00","연속"]
[156,"경기","성남","신안성신용인#2 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사 - 대상구간 :  신안성-신용인#2T/L No.4~66 - 사전작업 : 추락방지장치 설치시행(수평) ※  신안성-신성남T/L 4회선 구간","2025-09-18 07:00","2025-09-30 18:00","2025-09-18 07:00","2025-09-30 18:00","연속"]
[157,"경기","성남","신안성신성남#1 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사 - 대상구간 :  신안성-신성남#1T/L No.49~66 ※  신안성-신용인T/L 4회선 구간","2025-09-15 07:00","2025-09-17 18:00","2025-09-15 07:00","2025-09-17 18:00","연속"]
[158,"경기","직할","화성평택TP#2 T/L"," 화성-평택TP #2T/L 지장수목 벌채작업"," 화성-평택TP #2T/L 지장수목 벌채작업 (19~20호)","2025-09-12 08:00","2025-09-12 17:00","2025-09-12 08:00","2025-09-12 17:00","연속"]
[159,"경기","직할","화성S/S #3 M.Tr","화성S/S #3M.Tr 보통점검","화성 : #3M.Tr 보통점검(~12) - 1차 GIS 하자점검, 2차 보통점검 - LA 1,2,3차 A,B,C 초기 점검 - 추락방지장치 설치","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[160,"경기","직할","화성평택TP#1 T/L"," 화성-평택TP #1T/L 지장수목 벌채작업"," 화성-평택TP #1T/L 지장수목 벌채작업 (19~20호)","2025-09-11 08:00","2025-09-11 17:00","2025-09-11 08:00","2025-09-11 17:00","연속"]
[161,"경기","직할","화성서서울#1 T/L"," 화성-서서울 #1T/L 지장수목 벌채작업"," 화성-서서울 #1T/L 지장수목 벌채작업 (1~2호)","2025-09-19 08:00","2025-09-19 17:00","2025-09-19 08:00","2025-09-19 17:00","연속"]
[162,"경기","평택","고덕고덕2#2 T/L","고덕#2S/S #4M.Tr 증설공사","앵글측정","2025-09-23 09:00","2025-09-23 14:00","2025-09-27 09:00","2025-09-27 16:00","연속"]
[163,"경기","평택","고덕#2서안성#1 T/L","고덕#2S/S #4M.Tr 증설공사","앵글측정 및 전설비 무부하가압","2025-09-23 14:00","2025-09-24 18:00","2025-09-27 16:00","2025-09-28 18:00","연속"]
[164,"경기","평택","고덕#2S/S #2 BUS","고덕#2S/S #4M.Tr 증설공사","앵글측정 및 #4M.Tr 관련 전설비 무부하가압","2025-09-23 14:00","2025-09-24 18:00","2025-09-27 16:00","2025-09-28 18:00","연속"]
[165,"경기","평택","고덕#2S/S #2 BUS","고덕#2S/S #4M.Tr 증설공사(#75BUS)"," 모선보호반 CT 케이블 이설 및  GIS 인터록시험","2025-09-02 09:00","2025-09-05 18:00","2025-09-01 09:00","2025-09-04 18:00","연속"]
[166,"경기","평택","고덕#2S/S #1 BUS","고덕#2S/S #4M.Tr 증설공사","앵글측정","2025-09-23 09:00","2025-09-23 14:00","2025-09-28 09:00","2025-09-28 16:00","연속"]
[167,"경기","평택","고덕#2서안성#2 T/L"," 고덕2-서안성#2T/L 피뢰기 설치공사","No.1~29 피뢰기 설치","2025-09-08 08:00","2025-09-12 18:00","2025-09-08 08:00","2025-09-12 18:00","연속"]
[168,"경기","평택","고덕#2서안성#2 T/L","고덕#2S/S #4M.Tr 증설공사","앵글측정","2025-09-23 09:00","2025-09-23 14:00","2025-09-27 09:00","2025-09-27 16:00","연속"]
[169,"경기","평택","서안성S/S #4 M.Tr","M.Tr 보통, 정밀점검 공사(서안성S/S #4M.Tr)","서안성S/S  #4 M.Tr 보통점검","2025-09-02 09:00","2025-09-04 18:00","2025-09-02 09:00","2025-09-04 18:00","연속"]
[170,"경기","평택","평택T/P #2 M.Tr","2025년 평택전력 변전협력회사 총액공사(평택TP 2TIE-Tr)","평택T/P  2TIE-Tr OFU 압력계 교체 및 #2S.Tr 대체","2025-09-29 09:00","2025-09-30 18:00","2025-09-29 09:00","2025-09-30 18:00","연속"]
[171,"경기","평택","평택T/P CB 7872","2025년 평택전력 GIS 보통 및 정밀점검공사(평택TP 7872)","평택T/P  #1 S/T 1차 GIS(7872) 보통점검","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[172,"경기","평택","평택T/P CB 7700","2025년 평택전력 GIS 보통 및 정밀점검공사(평택화력 7700)","평택T/P  평택T/P-#1 G/T 1차 TIE GIS(7700) 보통점검","2025-09-22 09:00","2025-09-22 18:00","2025-09-22 09:00","2025-09-22 18:00","연속"]
[173,"경기","평택","평택T/P #3 M.Tr","2025년 평택전력 변전협력회사 총액공사(평택TP 3TIE-Tr)","평택T/P  #3TIE-Tr 6341 DS 누기보수","2025-09-06 09:00","2025-09-10 18:00","2025-09-06 09:00","2025-09-10 18:00","연속"]
[174,"경기","평택","화성신평택CC#1 T/L","2025년 평택전력 GIS 보통 및 정밀점검공사(화성-신평택#1)","평택T/P  화성-신평택#1T/L 회로 점검(7A71 DS 제어전원 불량)","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[175,"강원","강릉","신양양S/S #1 BUS","신양양S/S STATCOM용  GIS 설치공사","○ 7500CB 및 C.Tr 무부하가압","2025-09-28 08:00","2025-09-28 17:00","취소","취소","연속"]
[176,"강원","강릉","신양양S/S #1 BUS","신양양S/S STATCOM용  GIS 설치공사","○ STATCOM용 75Bay ~  #1BUS 연동시험 ○ 7500CB 무부하가압","2025-09-01 09:00","2025-09-01 18:00","2025-09-01 09:00","2025-09-01 18:00","연속"]
[177,"강원","강릉","안인개폐소신양양 T/L","신양양S/S STATCOM용  GIS 설치공사","○ 7500CB 무부하가압","2025-09-28 08:00","2025-09-29 17:00","취소","취소","매일"]
[178,"강원","강릉","신양양S/S #2 BUS","신양양S/S STATCOM용  GIS 설치공사","○ STATCOM용 75Bay ~  #2BUS 연동시험 ○ 7572CB 무부하가압","2025-09-02 09:00","2025-09-02 09:00","2025-09-02 09:00","2025-09-02 09:00","연속"]
[179,"강원","강릉","신양양S/S #3 M.Tr","신양양S/S 수리풍력TL 증설공사","수리풍력TL BUS 접속 인접 설비 안전조치 휴전","2025-09-22 08:00","2025-09-26 18:00","2025-09-22 08:00","2025-09-26 18:00","연속"]
[180,"강원","강릉","신양양S/S #3 M.Tr","신양양S/S 수리풍력TL 증설공사","170kV GIS 기기반입 안전이격 확보","2025-09-08 08:00","2025-09-08 18:00","2025-09-08 08:00","2025-09-08 18:00","연속"]
[181,"강원","강릉","신양양S/S #2 BUS","신양양S/S STATCOM용  GIS 설치공사","○ 7572CB 및 C.Tr 무부하가압","2025-09-29 08:00","2025-09-29 17:00","취소","취소","연속"]
[182,"강원","강릉","양양P/P #2 BUS","2025년 강릉전력 변전협력 총액공사"," 75BUS 모선보호반 대체","2025-09-15 10:00","2025-09-19 18:00","2025-09-15 10:00","2025-09-19 18:00","연속"]
[183,"강원","동해","신제천동해#1 T/L","2024~25년 동해전력지사 가공송전 협력회사 공사","전선접속개소 전력선 교체","2025-09-23 07:00","2025-09-30 18:00","2025-09-23 07:00","2025-09-30 18:00","연속"]
[184,"강원","태백","신태백S/S #2 BUS","신태백S/S STATCOM  B/F 연동시험","- 신태백 STATCOM 72BAY B/F 증설관련 모선보호반 연동시험","2025-09-01 09:00","2025-09-05 18:00","2025-09-01 09:00","2025-09-05 18:00","연속"]
[185,"강원","태백","신태백삼척BP#2T/L","신태백S/S STATCOM  GIS 설치공사","- 신태백 STATCOM C.Tr 및 GIS 무부하가압(24hr) * 신태백-삼척BP#2 T/L 또는 신태백-한울NP2 #2 T/L을 통한 무부하가압","2025-09-15 09:00","2025-09-16 18:00","취소","취소","연속"]
[186,"강원","태백","신태백S/S #2 BUS","신태백S/S STATCOM  GIS 설치공사","- 신태백 STATCOM C.Tr 및 GIS 무부하가압, 사용전검사","2025-09-15 09:00","2025-09-19 18:00","취소","취소","연속"]
[187,"강원","태백","신태백한울NP#1 T/L","신태백S/S STATCOM  GIS 설치공사","- 신태백 STATCOM C.Tr 및 GIS 무부하가압(24hr) * 신태백-삼척BP#2 T/L 또는 신태백-한울NP2 #2 T/L을 통한 무부하가압","2025-09-15 09:00","2025-09-16 18:00","취소","취소","연속"]
[188,"강원","태백","신태백한울NP#1 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 신태백-한울NP2 #1 T/L 수평추락방지장치 및 폴리머 점퍼지지애자 설치","2025-09-22 07:00","2025-09-30 18:00","2026-09-22 07:00","2026-09-30 18:00","매일"]
[189,"강원","태백","신태백S/S #1 BUS","신태백S/S STATCOM  B/F 연동시험","- 신태백 STATCOM 72BAY B/F 증설관련 모선보호반 연동시험","2025-09-01 09:00","2025-09-05 18:00","2025-09-01 09:00","2025-09-05 18:00","연속"]
[190,"강원","태백","신태백S/S #1 BUS","신태백S/S STATCOM  GIS 설치공사","- 신태백 STATCOM C.Tr 및 GIS 무부하가압, 사용전검사","2025-09-15 09:00","2025-09-19 18:00","취소","취소","연속"]
[191,"충북","직할","신진천S/S #4 M.Tr","25년 충북본부 직할 GIS 정밀점검 공사","신진천S/S 154kV #6Sh.C GIS 정밀점검 후 무부하가압용","2025-09-27 17:00","2025-09-27 18:00","2025-09-27 17:00","2025-09-27 18:00","연속"]
[192,"충북","직할","신진천S/S #1 M.Tr","25년 충북본부 직할 GIS 정밀점검 공사","신진천S/S  #1M.Tr 2차 GIS 정밀점검","2025-09-15 08:00","2025-09-17 18:00","2025-09-15 08:00","2025-09-17 18:00","연속"]
[193,"충북","직할","신진천S/S #4 M.Tr","25년 충북본부 직할 GIS 정밀점검 공사","신진천S/S 154kV #3Sh.C GIS 정밀점검 후 무부하가압용","2025-09-24 17:00","2025-09-24 18:00","2025-09-24 17:00","2025-09-24 18:00","연속"]
[194,"충북","직할","신중부신진천#2 T/L","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  신중부-신진천#2T/L LA 보통점검","2025-09-25 10:00","2025-09-25 18:00","2025-09-25 10:00","2025-09-25 18:00","연속"]
[195,"충북","직할","신청주S/S #1 M.Tr"," 신청주S/S 건설공사","#1 M.Tr 실부하가압(2차측)","2025-09-16 10:00","2025-09-16 11:00","2025-09-16 10:00","2025-09-16 11:00","연속"]
[196,"충북","직할","신청주S/S #2 M.Tr"," 신청주S/S 건설공사","#2 M.Tr 실부하가압(2차측)","2025-09-16 11:00","2025-09-16 12:00","2025-09-16 11:00","2025-09-16 12:00","연속"]
[197,"충북","직할","신청주S/S #3 M.Tr"," 신청주S/S 건설공사","#3 M.Tr 실부하가압(2차측)","2025-09-16 13:00","2025-09-16 14:00","2025-09-16 13:00","2025-09-16 14:00","연속"]
[198,"충북","청주","세종남청주#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 하자점검(7671) LA, CVT 점검","2025-09-02 09:00","2025-09-02 18:00","2025-09-02 09:00","2025-09-02 18:00","연속"]
[199,"충북","청주","신옥천청양 T/L","2024~2025년 청주전력지사 변전협력회사 공사","LA교체 및 CVT 점검","2025-09-11 08:00","2025-09-11 18:00","2025-09-11 08:00","2025-09-11 18:00","연속"]
[200,"충북","청주","신옥천세종#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","LA교체 및 CVT 점검","2025-09-10 08:00","2025-09-10 18:00","2025-09-10 08:00","2025-09-10 18:00","연속"]
[201,"충북","청주","신옥천세종#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","LA교체 및 CVT 점검","2025-09-09 08:00","2025-09-09 18:00","2025-09-09 08:00","2025-09-09 18:00","연속"]
[202,"충북","청주","신옥천S/S #1 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사"," M.Tr 3차측 과열개소 점검","2025-09-01 08:00","2025-09-01 18:00","2025-09-01 08:00","2025-09-01 18:00","연속"]
[203,"충북","청주","신옥천신계룡 T/L","2024~2025년 청주전력지사 변전협력회사 공사","LA교체 및 CVT 점검","2025-09-12 08:00","2025-09-12 18:00","2025-09-12 08:00","2025-09-12 18:00","연속"]
[204,"충북","충주","신제천S/S CB 7971","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  신제천동해#1T/L DS(7961,7901) PD 하자보수","2025-09-23 09:00","2025-09-25 18:00","2025-09-23 09:00","2025-09-25 18:00","연속"]
[205,"충북","충주","신제천S/S #1 TCSC CB","2025년 신제천S/S  TCSC 보통점검공사","2025년 신제천S/S  TCSC 보통점검공사","2025-09-23 07:00","2025-09-30 18:00","2025-09-23 07:00","2025-09-30 18:00","연속"]
[206,"충북","충주","신제천S/S CB 7471","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  신제천여주복합T/L DS(7461,7401) PD 하자보수","2025-09-04 09:00","2025-09-06 18:00","2025-09-04 09:00","2025-09-06 18:00","연속"]
[207,"충북","충주","신제천S/S CB 7371","신제천S/S 362KV GIS PD 제작사 하자보수","신제천S/S 신제천신충주 #2T/L DS(7361,7301) PD 하자보수","2025-09-01 09:00","2025-09-03 18:00","2025-09-01 09:00","2025-09-03 18:00","연속"]
[208,"충북","충주","신제천동해#2 T/L","'24-25년 충주전력지사 변전협력회사 총액공사","신제천S/S  신제천동해#2 T/L LA 대체공사","2025-09-03 09:00","2025-09-03 18:00","취소","취소","연속"]
[209,"충북","충주","신제천S/S CB 7A71","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  신제천동해#2T/L DS(7A61,7A01) PD 하자보수","2025-09-15 09:00","2025-09-17 18:00","2025-09-15 09:00","2025-09-17 18:00","연속"]
[210,"충북","충주","신제천S/S CB 7771","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  신제천신영주#2T/L DS(7761,7701) PD 하자보수","2025-09-08 09:00","2025-09-10 18:00","2025-09-08 09:00","2025-09-10 18:00","연속"]
[211,"충북","충주","신제천신영주#1 T/L","2025년 가공송전 순시점검 위탁공사"," 신제천-신영주T/L 정밀점검","2025-09-08 07:00","2025-09-19 18:00","취소","취소","매일"]
[212,"충북","충주","신충주S/S #3 M.Tr","2025년 충주전력지사 345, 154kV M.Tr 보통점검공사","신충주S/S  #3M.Tr 주변압기 보통점검","2025-09-08 09:00","2025-09-09 18:00","2025-09-08 09:00","2025-09-09 18:00","연속"]
[213,"충북","충주","신제천신충주T#1 T/L"," 신용인-동서울 등 16개 T/L 추락방지장치 설치공사"," 신제천-여주CC T/L 추락방지장치 설치공사 - 신제천-여주CC 연계선로로 인한 휴전(신충주 T분기 실작업 없음)","2025-09-15 07:00","2025-09-17 18:00","취소","취소","연속"]
[214,"대전세종충남","대전","신계룡S/S #3 M.Tr","신계룡S/S  #3 M.Tr 보통점검","신계룡S/S  #3 M.Tr 보통점검","2025-09-23 09:00","2025-09-26 18:00","2025-09-23 09:00","2025-09-26 18:00","연속"]
[215,"대전세종충남","대전","신계룡청양 T/L","[송전][오전만][즉시가압O] 신옥천-청양 등 추락방지설치공사","[송전][오전만][즉시가압O] 신옥천-청양 등 추락방지설치공사","2025-09-22 07:00","2025-09-30 11:00","취소","취소","매일"]
[216,"대전세종충남","서산","당진T/P CB 7172","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 당진T/P 7172 GIS 보통점검","2025-09-22 09:30","2025-09-23 18:00","2025-09-22 09:30","2025-09-23 18:00","연속"]
[217,"대전세종충남","서산","당진T/P #71 M.Tr","2024~2025년 변전협력회사 총액공사","당진T/P #71 Tie.Tr A, B, C, S 상부싱 절연유 채유 및 절열열화 진단 [8월 휴전 미승인시]","2025-09-27 08:00","2025-09-27 18:00","2025-09-27 08:00","2025-09-27 18:00","연속"]
[218,"대전세종충남","서산","당진T/P #72 M.Tr","당진화력S/S 차단기 조작시험 및 전자변 교체","(8월 휴전취소시) (즉시가압 불가) 당진화력S/S 차단기 조작시험 -  #72Tie Tr 1차 CB(7371) 개폐타임 측정 -  #72Tie Tr 2차 CB(6244) 개폐타임 측정 및 전자변 교체 -  #72Tie Tr 1차 - Tie CB(7300) 개폐타임 측정","2025-09-28 09:00","2025-09-28 18:00","2025-09-28 09:00","2025-09-28 18:00","연속"]
[219,"대전세종충남","서산","북당진S/S CB 7371","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 북당진S/S 7371 GIS 보통점검","2025-09-24 09:30","2025-09-25 14:00","2025-09-24 09:30","2025-09-25 14:00","연속"]
[220,"대전세종충남","서산","북당진S/S CB 7300","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 북당진S/S 7300 GIS 보통점검","2025-09-25 14:00","2025-09-26 18:00","2025-09-25 14:00","2025-09-26 18:00","연속"]
[221,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~126(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 교차선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청 * 8월 휴전 승인시 취소 요청","2025-09-30 13:00","2025-09-30 18:00","취소","취소","연속"]
[222,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-북당진T/L 병가 및  신당진개폐소-현대제철 교차구간,  신당진개폐소-북당진T/L 및 신당진개폐소-현대제철 모두 휴전 미승인시 휴전 취소 요청 * 8월 휴전 승인시 취소 요청","2025-09-30 08:00","2025-09-30 18:00","취소","취소","연속"]
[223,"대전세종충남","서산","신당진개폐소북당진 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.126~127(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 병가선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청 * 8월 휴전 승인시 취소 요청","2025-09-30 08:00","2025-09-30 13:00","취소","취소","연속"]
[224,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","24~25 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-현대제철T/L 병가선로,  신당진개폐소-현대제철T/L 휴전 미승인시 휴전 취소 요청 * 8월 휴전 승인시 취소 요청","2025-09-29 08:00","2025-09-29 18:00","취소","취소","연속"]
[225,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#1T/L 병가선로,  신당진개폐소-태안화력#1T/L 휴전 미승인시 휴전 취소 요청 * 8월 휴전 승인시 취소 요청","2025-09-29 08:00","2025-09-29 18:00","취소","취소","연속"]
[226,"대전세종충남","서산","신당진S/S #2 M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신당진S/S  #2M.Tr 보호반 교체","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[227,"대전세종충남","서산","신당진S/S #1 M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신당진S/S  #1M.Tr 보호반 교체","2025-09-08 09:00","2025-09-12 18:00","2025-09-08 09:00","2025-09-12 18:00","연속"]
[228,"대전세종충남","서산","신서산S/S CB 7579","신서산S/S  차단기 조작시험","(즉시가압 가능) 신서산S/S  #3 Sh.R 7579CB 개폐타임 측정","2025-09-24 09:00","2025-09-24 18:00","2025-09-24 09:00","2025-09-24 18:00","연속"]
[229,"대전세종충남","서산","신서산S/S CB 7700","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신서산S/S  7700 GIS 차단기 유압스위치 불량교체","2025-09-24 09:30","2025-09-24 18:00","2025-09-24 09:30","2025-09-24 18:00","연속"]
[230,"대전세종충남","서산","태안T/P CB 7400","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 태안T/P 7400 GIS 보통점검","2025-09-29 09:30","2025-09-30 18:00","2025-09-29 09:30","2025-09-30 18:00","연속"]
[231,"대전세종충남","서산","태안T/P #1 M.Tr","2024~2025년 변전협력회사 총액공사","태안T/P  #1 M.Tr, B, C, S상 부싱 절연유 채유 및 절연열화 진단","2025-09-11 09:00","2025-09-11 18:00","2025-09-11 09:00","2025-09-11 18:00","연속"]
[232,"대전세종충남","서산","신서산태안TP#2 T/L","태안화력S/S  옥외 기타설비 내장화공사","(즉시가압불가) 태안화력S/S  신서산-태안화력#2T/L CVT 내장화공사","2025-09-15 09:00","2025-09-25 18:00","2025-09-15 09:00","2025-09-25 18:00","연속"]
[233,"대전세종충남","천안","신온양서서울#2 T/L"," 신온양-서서울T/L 추락방지장치 설치공사","[즉시가압가능] 신온양-서서울T/L #T/L No. 1 ~ 25 추락방지장치 설치","2025-09-08 07:00","2025-09-11 18:00","취소","취소","매일"]
[234,"대전세종충남","천안","신온양S/S #2 M.Tr","'25년 천안P/O GIS 정밀 및 보통점검공사","(즉시가압불가)신온양S/S 154kV #4Sh.C 1차 GIS 정밀점검 관련  #2M.Tr 휴전","2025-09-29 09:00","2025-10-01 18:00","취소","취소","연속"]
[235,"대전세종충남","천안","신온양S/S #4 M.Tr","(8월 취소시)신온양S/S  #77Bay B/F PNL 대체","(8월 취소시)(즉시가압불가)(장기미교체 대상)신온양S/S  #77Bay 노후 B/F PNL 대체","2025-09-08 09:00","2025-09-11 18:00","취소","취소","연속"]
[236,"대전세종충남","천안","신온양서서울#2 T/L","(8월 취소시)신온양S/S  #77Bay B/F PNL 대체","(8월 취소시)(즉시가압불가)(장기미교체 대상)신온양S/S  #77Bay 노후 B/F PNL 대체","2025-09-08 09:00","2025-09-11 18:00","취소","취소","연속"]
[237,"대전세종충남","천안","신온양S/S #4 M.Tr","(8월 취소시)(즉시가압 가능)신온양S/S #4M.Tr 부싱절연유 채유","(8월 취소시)신온양S/S  #4M.Tr 부싱절연유 채유","2025-09-08 09:00","2025-09-08 18:00","취소","취소","연속"]
[238,"대전세종충남","천안","신탕정S/S CB 7371","신탕정S/S  #3M.Tr 1차 7371 CB 메니폴드 교체","신탕정S/S  #3M.Tr 1차 7371 CB 메니폴드 교체","2025-09-05 09:00","2025-09-05 18:00","2025-09-05 09:00","2025-09-05 18:00","연속"]
[239,"대전세종충남","천안","신온양신탕정#1 T/L","신탕정S/S  #71bay B/F 노후 보호배전반 대체","(즉시가압불가)(장기미교체대상)신탕정S/S  #71bay B/F 노후 보호배전반 대체","2025-09-01 09:00","2025-09-04 18:00","2025-09-01 09:00","2025-09-04 18:00","연속"]
[240,"대전세종충남","천안","신탕정S/S #2 M.Tr","신탕정S/S  #71bay B/F 노후 보호배전반 대체","(즉시가압불가)(장기미교체대상)신탕정S/S  71bay B/F 노후 보호배전반 대체","2025-09-01 09:00","2025-09-04 18:00","2025-09-01 09:00","2025-09-04 18:00","연속"]
[241,"대전세종충남","천안","아산S/S CB 7400","(즉시가압가능)아산S/S  7400 CB 개폐타임 측정","아산S/S  아산-화성#1T/L-TIE 7400 CB 개폐타임 측정","2025-09-21 09:00","2025-09-21 18:00","취소","취소","연속"]
[242,"대전세종충남","천안","아산S/S CB 7371","'25년 천안P/O 정밀 및 보통점검공사","(즉시가압가능)아산S/S  신서산-아산#2T/L GIS(7371) 보통점검","2025-09-27 09:00","2025-09-27 18:00","2025-09-27 09:00","2025-09-27 18:00","연속"]
[243,"대전세종충남","천안","아산S/S CB 7300","'25년 천안P/O 정밀 및 보통점검공사","(즉시가압가능)아산S/S  #3M.Tr TIE GIS(7700) 보통점검","2025-09-20 09:00","2025-09-20 18:00","취소","취소","연속"]
[244,"대전세종충남","천안","아산S/S CB 7200","(즉시가압가능)아산S/S  7200 CB 개폐타임 측정","아산S/S 아산-화성 #2T/L - 아산-보령화력#1T/L TIE 7200 CB 개폐타임측정","2025-09-21 09:00","2025-09-21 14:00","취소","취소","연속"]
[245,"대전세종충남","천안","아산S/S CB 7271","(즉시가압가능)아산S/S  7271 CB 개폐타임 측정","아산S/S 아산-화성 #2T/L 7271 CB 개폐타임측정","2025-09-28 14:00","2025-09-28 18:00","취소","취소","연속"]
[246,"대전세종충남","천안","아산S/S #2 M.Tr","(즉시가압가능)아산S/S  #2M.Tr 부싱절연유 채유","아산S/S  #2M.Tr 부싱절연유 채유","2025-09-30 09:00","2025-09-30 18:00","2025-09-30 09:00","2025-09-30 18:00","연속"]
[247,"대전세종충남","청양","아산보령TP#1 T/L","[변전내장화공사]보령화력  GIS LA & PT 내장화 공사","[변전내장화공사]보령화력  GIS LA & PT 내장화 공사 대상 : 보령연락#1T/L, 아산-보령화력#1T/L","2025-09-15 09:00","2025-09-23 18:00","2025-09-21 20:00","2025-09-27 10:00","연속"]
[248,"대전세종충남","청양","아산보령TP#2 T/L","[송전][즉시가압O] 아산-보령 등 4개T/L 항공구 설치공사"," 아산-보령화력#2T/L 항공구 설치공사","2025-09-12 08:00","2025-09-14 18:00","2025-09-12 08:00","2025-09-14 18:00","매일"]
[249,"대전세종충남","청양","청양보령TP#1 T/L","[송전][즉시가압O] 아산-보령 등 4개T/L 항공구 설치공사"," 청양-보령화력#1T/L 항공구 설치공사","2025-09-05 08:00","2025-09-07 18:00","2025-09-05 08:00","2025-09-07 18:00","매일"]
[250,"대전세종충남","청양","보령TP보령CC#1 T/L","[변전내장화공사]보령화력  GIS LA & PT 내장화 공사","[변전내장화공사]보령화력  GIS LA & PT 내장화 공사 대상 : 보령연락#1T/L, 아산-보령화력#1T/L","2025-09-24 09:00","2025-10-02 18:00","2025-09-14 20:00","2025-09-20 10:00","연속"]
[251,"대전세종충남","청양","청양S/S #2 M.Tr","[변전총액] 청양P/O 변전협력 총액공사"," 77BAY BF PNL 교체작업","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[252,"전북","군산","군산S/S #1 M.Tr","군산변전소  GIS 대체공사(17차)","○ 362kV GIS 40kA 4000A × 10CB(PT Bay 포함) 철거 ○ 362kV GIS 50kA 4000A × 10CB(PT Bay 포함) 설치 ○ 기초 BaseChennel × 4Bay분 설치 ○ 기타부대공사 × 1식","2025-09-03 09:00","2025-12-06 18:00","2025-09-03 09:00","2025-12-06 18:00","연속"]
[253,"전북","군산","군산S/S #70 BUS","군산S/S  GIS 대체공사(16차)","○  #1BUS측 72Bay 7251DS 철거 및 END 커버 설치 ○ 기타부대공사 * 1식","2025-09-01 08:00","2025-09-02 17:00","2025-09-01 08:00","2025-09-02 17:00","연속"]
[254,"전북","군산","군산S/S #1 Sh.R CB","군산S/S  GIS 대체공사(16차)","○  #1BUS측 72Bay 주모선 무부하가압 -7251DS측 END커버 설치분 건전성 확인","2025-09-01 17:00","2025-09-02 17:00","2025-09-01 17:00","2025-09-02 17:00","연속"]
[255,"전북","군산","군산S/S #75 BUS","군산S/S  GIS 대체공사(18차)","○  #2BUS측 72Bay 7252DS 철거 및 END 커버 설치 ○ 기타부대공사 * 1식","2025-09-03 08:00","2025-09-04 17:00","2025-09-03 08:00","2025-09-04 17:00","연속"]
[256,"전북","군산","군산S/S #1 Sh.R CB","군산S/S  GIS 대체공사(18차)","○  #2BUS측 72Bay 주모선 무부하가압 - 7252DS측 END커버 설치분 건전성 확인","2025-09-03 17:00","2025-09-04 17:00","2025-09-03 17:00","2025-09-04 17:00","연속"]
[257,"전북","군산","새만금S/S #3 M.Tr","군산P/O  차단기 보통점검","○ 7372 CB 보통점검","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[258,"전북","군산","새만금S/S CB 7300","24~25년 군산전력지사 변전협력회사 총액공사","- 공압식차단기 전자변 교체","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[259,"전북","군산","새만금S/S CB 7371","24~25년 군산전력지사 변전협력회사 총액공사","- 공압식차단기 전자변 교체","2025-09-16 09:00","2025-09-16 18:00","2025-09-16 09:00","2025-09-16 18:00","연속"]
[260,"전북","김제","신김제S/S #1 M.Tr","김제전력지사 주변압기 보통점검","신김제S/S  #1M.Tr 보통점검 및 추락방지 장치 설치","2025-09-22 09:00","2025-09-24 18:00","2025-09-22 09:00","2025-09-24 18:00","연속"]
[261,"전북","김제","신김제S/S #2 M.Tr","김제전력지사 주변압기 보통점검","신김제S/S  #2M.Tr 보통점검 및 추락방지장치 설치","2025-09-29 09:00","2025-10-01 18:00","2025-09-29 09:00","2025-10-01 18:00","연속"]
[262,"전북","김제","신김제S/S #3 M.Tr","김제전력지사 기타설비 점검공사","신김제S/S #3M.Tr 2차 피뢰기 초기점검","2025-09-01 09:00","2025-09-01 18:00","2025-09-01 09:00","2025-09-01 18:00","연속"]
[263,"전북","직할","신남원신광주#2 T/L","'24~'25년 전북직할 가공송전 협력회사 공사(계속)","○  신남원-신광주T/L 피뢰기 설치공사(계속) - No.1~115","2025-09-17 07:30","2025-09-25 18:00","취소","취소","연속"]
[264,"전북","직할","신남원의령#1 T/L","'25년 가공송전 순시점검 위탁공사(중복)","○ 정밀점검 : No.137~180","2025-09-29 08:00","2025-10-03 18:00","취소","취소","연속"]
[265,"전북","직할","신옥천신남원#1 T/L"," 신옥천-신남원 등 3개T/L 수평추락방지시설 설치공사(계속)"," 신옥천-신남원#1T/L 1~178호","2025-09-01 07:30","2025-09-11 17:00","취소","취소","연속"]
[266,"전북","직할","신옥천신남원#2 T/L"," 신옥천-신남원 등 3개T/L 수평 추락방지시설 설치공사(계속)"," 신옥천-신남원#1T/L 1~178호","2025-09-12 07:30","2025-09-22 17:00","취소","취소","연속"]
[267,"광주전남","강진","신화순신강진#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","수직,수평 추락방지장치 설치공사, 즉시가압 불가하나, 1시간 내 가압가능","2025-09-02 07:00","2025-09-26 18:00","2025-09-02 07:00","2025-09-26 18:00","매일"]
[268,"광주전남","강진","신강진S/S #4 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. 신강진S/S #4M.Tr 보호반 기계적 보호장치 회로변경 ※ 거래소 요청 시 휴전일정 협의 가능","2025-09-01 08:00","2025-09-01 18:00","취소","취소","연속"]
[269,"광주전남","강진","신화순신강진#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","수평 추락방지장치 설치공사, 즉시가압 불가하나, 1시간 내 가압가능","2025-09-29 07:00","2025-10-24 18:00","2025-09-29 07:00","2025-10-24 18:00","매일"]
[270,"광주전남","강진","신강진S/S #2 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. 신강진S/S #2M.Tr 1차 부싱 절연열화 측정 ※ 거래소 요청 시 휴전일정 협의 가능","2025-09-10 08:00","2025-09-10 18:00","2025-09-22 08:00","2025-09-22 18:00","연속"]
[271,"광주전남","강진","신강진광양#1 T/L","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-09-08 08:00","2025-09-19 18:00","취소","취소","연속"]
[272,"광주전남","강진","신강진S/S #1 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. 신강진S/S #1M.Tr,B,C상 보통점검 ※ 거래소 요청 시 휴전일정 협의 가능","2025-09-08 08:00","2025-09-09 18:00","2025-09-01 08:00","2025-09-02 18:00","연속"]
[273,"광주전남","강진","신강진S/S #3 M.Tr","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-09-08 08:00","2025-09-19 18:00","2025-09-08 08:00","2025-09-19 18:00","연속"]
[274,"광주전남","광주","신남원신광주#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#1T/L 116~164호","2025-09-02 08:00","2025-09-08 18:00","취소","취소","매일"]
[275,"광주전남","광주","신남원신광주#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#2T/L 116~164호","2025-09-09 08:00","2025-09-15 18:00","취소","취소","매일"]
[276,"광주전남","광주","신광주S/S CB 7672","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-09-23 08:00","2025-09-23 18:00","2025-09-23 08:00","2025-09-23 18:00","연속"]
[277,"광주전남","광주","신광주S/S CB 7600","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-09-23 08:00","2025-09-23 18:00","2025-09-23 08:00","2025-09-23 18:00","연속"]
[278,"광주전남","광주","신광주S/S CB 7671","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-09-23 08:00","2025-09-23 18:00","2025-09-23 08:00","2025-09-23 18:00","연속"]
[279,"광주전남","광주","신광주S/S #3 M.Tr","3M.Tr 변압기보호반 장기사용 교체","3M.Tr 변압기보호반 장기사용 교체","2025-09-22 08:00","2025-09-26 18:00","2025-09-22 08:00","2025-09-26 18:00","연속"]
[280,"광주전남","광주","신광주한빛NP#2 T/L","신광주변전소 72BAY BF반 대체","신광주변전소 72BAY BF반 대체","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[281,"광주전남","광주","신광주S/S #2 M.Tr","'25년 광주전력지사 변전협력회사 공사","신광주S/S #2M.Tr 초기점검, 1차 GIS 조작시험, 2차 GIS 보통점검 1,3차 PT 초기점검, 1,2,3차 LA 보통점검, 2-1,2 Sh.R 보통점검","2025-09-15 09:00","2025-09-18 18:00","2025-09-15 09:00","2025-09-18 18:00","연속"]
[282,"광주전남","광주","신광주S/S #2 BUS","장기사용  #2BUS 모선보호반 교체","장기사용  #2BUS 모선보호반 교체","2025-09-11 08:00","2025-09-13 18:00","취소","취소","연속"]
[283,"광주전남","광주","신광주S/S #1 BUS","장기사용  #1BUS 모선보호반 교체","장기사용  #1BUS 모선보호반 교체","2025-09-08 08:00","2025-09-10 18:00","취소","취소","연속"]
[284,"광주전남","광주","신화순S/S #3 M.Tr","신화순변전소 75BAY BF반 대체","신화순변전소 75BAY BF반 대체","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[285,"광주전남","순천","광양CC여수TP#2 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #2T/L 폴리머점퍼지지애자 설치","2025-09-12 07:00","2025-09-12 18:00","2025-09-12 07:00","2025-09-12 18:00","연속"]
[286,"광주전남","순천","광양CC여수TP#1 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #1T/L 폴리머점퍼지지애자 설치","2025-09-08 07:00","2025-09-11 18:00","2025-09-08 07:00","2025-09-11 18:00","매일"]
[287,"광주전남","순천","광양S/S #2 M.Tr","25년 순천전력지사 부싱절연유 채유","광양변전소 #2M.Tr 부싱절연유 이상 관련 절연유 채유","2025-09-30 09:00","2025-09-30 18:00","2025-09-30 09:00","2025-09-30 18:00","연속"]
[288,"광주전남","순천","광양S/S #1 M.Tr","24-25년 순천전력지사 변전협력회사 공사","광양S/S #1M.Tr 보호배전반 대체","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[289,"광주전남","순천","신강진광양#2 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치 ※주말(20,21일) 미작업","2025-09-15 07:00","2025-09-26 18:00","취소","취소","매일"]
[290,"광주전남","순천","광양율촌CC T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가) ※휴일(20,21일) 미작업","2025-09-15 07:00","2025-09-26 18:00","취소","취소","매일"]
[291,"광주전남","순천","신남원광양#2 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가) ※휴일(20,21일) 미작업","2025-09-15 07:00","2025-09-26 18:00","취소","취소","매일"]
[292,"광주전남","순천","광양광양CC#1 T/L","24-25년 순천전력지사 변전협력회사 공사","광양-광양CC#1T/L 보호배전반 대체","2025-09-01 09:00","2025-09-05 18:00","2025-09-01 09:00","2025-09-05 18:00","연속"]
[293,"광주전남","순천","광양여수TP T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가) ※휴일(6,7일) 미작업","2025-09-01 07:00","2025-09-12 18:00","2025-09-01 07:00","2025-09-12 18:00","매일"]
[294,"광주전남","순천","신강진광양#1 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치 ※주말(6,7일) 미작업","2025-09-01 07:00","2025-09-12 18:00","취소","취소","매일"]
[295,"광주전남","순천","신남원광양#1 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가) ※휴일(6,7일) 미작업","2025-09-01 07:00","2025-09-12 18:00","2025-09-01 07:00","2025-09-12 18:00","매일"]
[296,"광주전남","순천","여수T/P #3 M.Tr","2025년 순천전력지사  M.Tr 정밀점검공사","여수화력S/S  #3M.Tr 정밀점검","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[297,"광주전남","순천","여수T/P #1 M.Tr","24-25년 순천전력지사 변전협력회사 공사","여수화력S/S #1M.Tr,B상 1차부싱 대체","2025-09-08 09:00","2025-09-12 18:00","2025-09-08 09:00","2025-09-12 18:00","연속"]
[298,"광주전남","순천","여수T/P #2 M.Tr","3차 DS과열관련 조치","3차 DS과열관련 조치","2025-09-01 09:00","2025-09-01 18:00","2025-09-01 09:00","2025-09-01 18:00","연속"]
[299,"대구","경산","신경산대구#1 T/L","2024-2025년 경산전력지사 송전협력회사 공사"," 신경산-대구T/L SB댐퍼 설치","2025-09-17 07:00","2025-09-17 18:00","2025-09-17 07:00","2025-09-17 18:00","연속"]
[300,"대구","경산","신경산S/S #3 M.Tr","24~25년 경산P/O 변전협력회사 총액공사","- 누기개소보수","2025-09-15 09:30","2025-09-16 18:00","2025-09-15 09:30","2025-09-16 18:00","연속"]
[301,"대구","경산","신경산대구#2 T/L","2024-2025년 경산전력지사 송전협력회사 공사"," 신경산-대구T/L 폴리머점퍼지지애자 및 SB댐퍼 설치","2025-09-15 07:00","2025-09-16 18:00","2025-09-15 07:00","2025-09-16 18:00","연속"]
[302,"대구","경산","울주신경산#1 T/L","24~25년 경산P/O 변전협력회사 총액공사","- 누기개소보수","2025-09-18 09:30","2025-09-19 18:00","2025-09-18 09:30","2025-09-19 18:00","연속"]
[303,"대구","경산","신경산S/S #1 M.Tr","24~25년 경산P/O 변전협력회사 총액공사","- 연동시험","2025-09-11 09:30","2025-09-11 18:00","2025-09-11 09:30","2025-09-11 18:00","연속"]
[304,"대구","달성","고령S/S CB 7371","고령S/S 고령-의령#1T/L CB 정밀점검","고령S/S 고령-의령#1T/L CB 정밀점검","2025-09-01 09:00","2025-09-05 18:00","2025-09-01 09:00","2025-09-05 18:00","연속"]
[305,"대구","달성","고령S/S CB 7300","고령S/S 고령-의령#1T/L TIE CB 정밀점검","고령S/S 고령-의령#1T/L TIE CB 정밀점검","2025-09-08 09:00","2025-09-12 18:00","2025-09-08 09:00","2025-09-12 18:00","연속"]
[306,"대구","달성","고령의령#1 T/L","[TEST] 고령S/S 고령-의령#1T/L 무부하가압선로","[TEST] 고령S/S 고령-의령#1T/L 무부하가압선로","2025-09-12 17:00","2025-09-12 18:00","2025-09-12 17:00","2025-09-12 18:00","연속"]
[307,"대구","달성","고령S/S CB 7571","고령S/S 서대구-고령#2T/L CB 정밀점검","고령S/S 서대구-고령#2T/L CB 정밀점검","2025-09-29 17:00","2025-10-03 18:00","2025-09-29 17:00","2025-10-03 18:00","연속"]
[308,"대구","달성","고령S/S CB 7471","GIS 정밀점검","GIS 정밀점검","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[309,"대구","달성","서대구고령#2 T/L"," 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 고령-의령#1T/L 피뢰기 및 조류착지방지장치 설치 - 작업자 안전확보 휴전","2025-09-06 07:00","2025-09-06 18:00","2025-09-06 07:00","2025-09-06 18:00","연속"]
[310,"대구","달성","북경남고령#1 T/L","[TEST] 고령S/S #4M.TR 정밀점검 무부하가압선로","[TEST] 고령S/S #4M.TR 정밀점검 무부하가압선로","2025-09-21 17:00","2025-09-21 18:00","2025-09-21 17:00","2025-09-21 18:00","연속"]
[311,"대구","달성","고령의령#1 T/L","2025년 달성전력 가공송전 순시점검 위탁공사"," 고령-의령 #1T/L 정밀점검(117~157호)","2025-09-01 09:00","2025-09-13 18:00","2025-09-01 09:00","2025-09-05 18:00","연속"]
[312,"대구","달성","고령S/S #4 M.Tr","M.TR 정밀점검","M.TR 정밀점검","2025-09-15 09:00","2025-09-21 18:00","2025-09-15 09:00","2025-09-21 18:00","연속"]
[313,"대구","달성","고령의령#1 T/L","고령-의령#1T/L 정밀점검","고령-의령#1T/L 단일 CB 무부하가압선로","2025-09-05 17:00","2025-09-05 18:00","2025-09-05 17:00","2025-09-05 18:00","연속"]
[314,"대구","달성","고령S/S #3 M.Tr","M.Tr 부싱절연유 채유","M.Tr 부싱절연유 채유","2025-09-25 14:00","2025-09-25 18:00","2025-09-23 14:00","2025-09-23 18:00","연속"]
[315,"대구","달성","고령S/S #2 M.Tr","M.Tr 부싱절연유 채유","M.Tr 부싱절연유 채유","2025-09-25 09:00","2025-09-25 14:00","2025-09-23 09:00","2025-09-23 14:00","연속"]
[316,"대구","달성","고령의령#2 T/L","[TEST] 고령S/S 7471CB 정밀점검 관련 무부하가압 선로","[TEST] 고령S/S 7471CB 정밀점검 관련 무부하가압 선로","2025-09-26 17:00","2025-09-26 18:00","2025-09-26 17:00","2025-09-26 18:00","연속"]
[317,"대구","달성","대구S/S #3 M.Tr","M.TR LA 초기점검","M.TR LA 초기점검","2025-09-12 09:00","2025-09-12 18:00","2025-09-12 09:00","2025-09-12 18:00","연속"]
[318,"대구","칠곡","북대구S/S #1 M.Tr","24~25년 칠곡전력지사 변전협력회사 공사","7172 LCP 보조Ry교체","2025-09-08 09:30","2025-09-09 18:00","2025-09-08 09:30","2025-09-09 18:00","연속"]
[319,"대구","칠곡","북대구S/S #3 M.Tr","24~25년 칠곡전력지사 변전협력회사 공사","2차 LA 교체","2025-09-11 09:30","2025-09-11 18:00","2025-09-11 09:30","2025-09-11 18:00","연속"]
[320,"대구","칠곡","북대구S/S CB 7471","24~25년 칠곡전력지사 변전협력회사 공사"," GIS 조작시험","2025-09-24 15:30","2025-09-24 18:00","2025-09-24 15:30","2025-09-24 18:00","연속"]
[321,"대구","칠곡","북대구S/S CB 7371","24~25년 칠곡전력지사 변전협력회사 공사"," GIS 조작시험","2025-09-24 13:00","2025-09-24 15:30","2025-09-24 13:00","2025-09-24 15:30","연속"]
[322,"대구","칠곡","북대구S/S CB 7172","24~25년 칠곡전력지사 변전협력회사 공사"," GIS 조작시험","2025-09-24 09:30","2025-09-24 12:00","2025-09-24 09:30","2025-09-24 12:00","연속"]
[323,"대구","칠곡","북대구S/S #2 M.Tr","24~25년 칠곡전력지사 변전협력회사 공사","2차 LA 교체","2025-09-10 09:30","2025-09-10 18:00","2025-09-10 09:30","2025-09-10 18:00","연속"]
[324,"대구","칠곡","서대구S/S #4 M.Tr","서대구S/S  #4M.Tr, LA, 3차 SIS 초기점검","서대구S/S  #4M.Tr, LA, 3차 SIS 초기점검","2025-09-29 09:00","2025-10-01 18:00","2025-09-29 09:00","2025-10-01 18:00","연속"]
[325,"대구","칠곡","서대구S/S #2 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2025-09-17 08:00","2025-09-25 18:00","2025-09-17 08:00","2025-09-25 18:00","연속"]
[326,"대구","칠곡","서대구고령#2 T/L","24~25년 달성전력지사 가공송전 협력회사 공사[안전확보]","[24~25년 달성전력지사 가공송전 협력회사 공사] 09.10(수)  고령-의령 #1T/L 소도체 이도조정(155~156호) 관련 안전확보","2025-09-13 08:00","2025-09-13 18:00","2025-09-13 08:00","2025-09-13 18:00","연속"]
[327,"대구","칠곡","서대구S/S #3 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2025-09-08 08:00","2025-09-16 18:00","2025-09-08 08:00","2025-09-16 18:00","연속"]
[328,"대구","칠곡","북경남서대구#2 T/L","2024~2025년 대구본부 칠곡전력지사 송전협력회사 공사"," 북경남-서대구#2T/L 수평 추락방지장치, 조류착지방지장치, 피뢰기 설치 (No.114~164호)","2025-09-01 07:00","2025-09-11 18:00","2025-09-01 07:00","2025-09-11 18:00","연속"]
[329,"대구","포항","신포항신월성NP#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","신월성S/Y, 신포항S/S 보호반 대체공사","2025-09-01 09:00","2025-09-12 18:00","2025-09-01 09:00","2025-09-12 18:00","연속"]
[330,"대구","포항","신포항신월성NP#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","신월성S/Y, 신포항S/S 보호반 대체공사","2025-09-15 09:00","2025-09-26 18:00","2025-09-15 09:00","2025-09-26 18:00","연속"]
[331,"대구","포항","선산신포항 T/L","2025년 칠곡전력지사 가공송전 순시점검 위탁공사"," 선산분기T/L 정밀점검 No.1~64 -  선산-신포항T/L No.98~35","2025-09-15 09:00","2025-10-02 18:00","2025-09-15 09:00","2025-10-02 18:00","연속"]
[332,"대구","포항","신포항S/S #1 M.Tr","신포항S/S #5M.Tr 증설공사(일반도급)","#5M.Tr 증설공사 파일시공 관련 안전이격거리 확보","2025-09-01 09:00","2025-09-05 18:00","2025-09-01 09:00","2025-09-05 18:00","연속"]
[333,"대구","포항","신포항S/S #2 M.Tr","신포항S/S #5M.Tr 증설공사(일반도급)","#5M.Tr 증설공사 파일시공 관련 안전이격거리 확보","2025-09-08 09:00","2025-09-12 18:00","2025-09-08 09:00","2025-09-12 18:00","연속"]
[334,"대구","포항","신포항S/S #3 M.Tr","2024~25년도 포항전력지사 송전협력회사 공사","신포항S/S #3M.Tr 애자청소[안전확보]","2025-09-15 09:00","2025-09-15 13:00","2025-09-15 09:00","2025-09-15 13:00","연속"]
[335,"대구","포항","신포항S/S #4 M.Tr","2024~25년도 포항전력지사 송전협력회사 공사","신포항S/S #4M.Tr 애자청소[안전확보]","2025-09-15 13:00","2025-09-15 16:00","2025-09-15 13:00","2025-09-15 16:00","연속"]
[336,"대구","포항","월성N/P #76 BUS","월성N/P 연계  GIS 용량대체공사(77Bay 대체)","월성N/P 연계  GIS 용량대체공사 ○  GIS × 18CB 대체 ○ 보호반 설치 및 이설 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기타 부대공사 × 1식","2025-09-11 10:00","2025-09-12 10:00","2025-09-11 10:00","2025-09-12 10:00","연속"]
[337,"대구","포항","월성N/P #71 BUS","월성N/P 연계  GIS 용량대체공사(77Bay 대체)","월성N/P 연계  GIS 용량대체공사 ○  GIS × 18CB 대체 ○ 보호반 설치 및 이설 × 1식 ○ 제어케이블 포설 및 결선 × 1식 ○ 기타 부대공사 × 1식","2025-09-12 10:00","2025-09-13 10:00","2025-09-12 10:00","2025-09-13 10:00","연속"]
[338,"대구","포항","월성N/P CB 7472","2024~2025년 포항전력지사 변전협력회사 공사","월성S/Y 7471 GIS 조작시험 및 7400, 7472 GIS 보통점검","2025-09-29 09:00","2025-09-30 18:00","2025-09-29 09:00","2025-09-30 18:00","연속"]
[339,"대구","포항","월성N/P CB 7371","2024~2025년 포항전력지사 변전협력회사 공사","7371 GIS 조작시험, PT 보통점검","2025-09-04 09:00","2025-09-05 18:00","2025-09-04 09:00","2025-09-05 18:00","연속"]
[340,"대구","포항","월성N/P CB 7372","2024~2025년 포항전력지사 변전협력회사 공사","7300, 7372 GIS 보통점검","2025-09-04 09:00","2025-09-05 18:00","2025-09-04 09:00","2025-09-05 18:00","연속"]
[341,"대구","포항","월성N/P CB 7872","2024~2025년 포항전력지사 변전협력회사 공사","월성S/Y 7871 GIS 조작시험 및 7800, 7872 GIS 보통점검","2025-09-19 09:00","2025-09-19 18:00","2025-09-19 09:00","2025-09-19 18:00","연속"]
[342,"대구","포항","월성NP신월성NP#2 T/L","2024~2025년 포항전력지사 변전협력회사 공사","월성S/Y 7871 GIS 조작시험 및 7800 GIS 보통점검 신월성S/Y 7271 GIS 조작시험","2025-09-12 09:00","2025-09-12 18:00","2025-09-12 09:00","2025-09-12 18:00","연속"]
[343,"대구","포항","월성N/P CB 7272","2024~25년도 포항전력지사 변전협력회사 공사","7271 GIS 조작시험, 7200, 7272 GIS, PT 보통점검","2025-09-22 09:00","2025-09-23 18:00","2025-09-22 09:00","2025-09-23 18:00","연속"]
[344,"대구","포항","울주월성NP#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","7271 GIS 조작시험, 7200, 7272 GIS, PT 보통점검","2025-09-22 09:00","2025-09-23 18:00","2025-09-22 09:00","2025-09-23 18:00","연속"]
[345,"대구","포항","울주월성NP#1 T/L","154kV 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 울주-월성NP#1T/L 추락방지장치 설치공사","2025-09-28 07:00","2025-10-02 18:00","2025-09-28 07:00","2025-10-02 18:00","연속"]
[346,"대구","포항","월성NP신월성NP#1 T/L","2024~2025년 포항전력지사 변전협력회사 공사","월성S/Y 7471 GIS 조작시험 및 7400, 7472 GIS 보통점검","2025-09-27 09:00","2025-09-27 18:00","2025-09-27 09:00","2025-09-27 18:00","연속"]
[347,"경북","구미","선산S/S #2 M.Tr","2024-25년 구미전력지사 변전협력회사 공사","- 1차,2차 LA 대체 - 1,2차 부싱절연유 채유 - #1S.Tr 대체 - #1S.Tr VCB 초기점검 - 1차,2차 LA 초기점검","2025-09-08 09:00","2025-09-10 18:00","2025-09-08 09:00","2025-09-10 18:00","연속"]
[348,"경북","구미","서대구선산#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 서대구-선산, 선산분기T/L 수직 및 수평추락방지장치 설치공사 -  서대구-선산T/L No.106~31 -  선산분기T/L No.107","2025-09-15 07:00","2025-10-02 18:00","2025-09-15 07:00","2025-10-02 18:00","연속"]
[349,"경북","구미","선산S/S #4 M.Tr","2024-25년 구미전력지사 변전협력회사 공사","- 1차 A,B상 부싱절연유 채유 - 2차 부싱절연유 채유 - 부싱 절연열화 측정","2025-09-23 09:00","2025-09-23 18:00","2025-09-05 09:00","2025-09-05 18:00","연속"]
[350,"경북","영주","신영주예천PP#1 T/L","2025년 영주전력지사  GIS 정밀점검","-7671, 7600CB GIS 정밀점검, 점검 후 신영주-예천PP#1T/L 이용 무부하가압","2025-09-01 09:00","2025-09-05 18:00","2025-09-01 09:00","2025-09-05 18:00","연속"]
[351,"경북","영주","신영주S/S #3 M.Tr","2025년 영주전력지사  GIS 정밀점검공사","-7772CB 정밀점검 후 #3M.Tr이용 무부하가압","2025-09-22 09:00","2025-09-25 18:00","2025-09-22 09:00","2025-09-25 18:00","연속"]
[352,"경북","영주","한울2NP한울3NP#4 T/L","24~25년 영주전력지사 변전협력회사 공사","7G02DS ASSY 교체","2025-09-08 09:00","2025-09-12 18:00","취소","취소","연속"]
[353,"경북","영주","신영주한울NP#1 T/L","2025년 가공송전 순시점검 위탁공사"," 신영주-한울NP2 T/L#1 T/L 정밀점검","2025-09-15 00:08","2025-09-23 18:00","취소","취소","연속"]
[354,"경북","영주","신영주한울NP#2 T/L","2025년 가공송전 순시점검 위탁공사"," 신영주-한울NP2 #2T/L 정밀점검","2025-09-24 08:00","2025-10-02 18:00","취소","취소","연속"]
[355,"경북","직할","안동C/C CB 7271","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[356,"경북","직할","안동C/C CB 7371","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2025-09-24 09:00","2025-09-24 18:00","2025-09-24 09:00","2025-09-24 18:00","연속"]
[357,"경북","직할","안동C/C CB 7200","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2025-09-22 09:00","2025-09-22 18:00","2025-09-22 09:00","2025-09-22 18:00","연속"]
[358,"경북","직할","안동C/C #1 M.Tr","24~25년 경북본부 직할 변전협력회사 공사","#1M.Tr 1,2차 GIS 및 3차 SIS 보통점검 변압기 추락방지장치 설치","2025-09-17 10:00","2025-09-19 18:00","2025-09-17 10:00","2025-09-19 18:00","연속"]
[359,"경북","직할","안동C/C #2 M.Tr","24~25년 경북본부 직할 변전협력회사 공사","#2M.Tr 1,2차 GIS 및 3차 SIS 보통점검 변압기 추락방지장치 설치","2025-09-09 10:00","2025-09-11 18:00","2025-09-09 10:00","2025-09-11 18:00","연속"]
[360,"경북","직할","청송PP면봉산풍력 T/L"," 청송분기 T/L 불량애자 교체공사","-  청송PP면봉산풍력 T/L 불량애자 교체","2025-09-22 09:00","2025-10-17 18:00","취소","취소","매일"]
[361,"경북","영주","신영주S/S CB 7571","2025년 영주전력지사  GIS 정밀점검공사","2025년 영주전력지사  GIS 정밀점검공사","2025-09-08 09:00","2025-09-10 19:00","2025-09-08 09:00","2025-09-10 19:00","연속"]
[362,"경북","영주","신영주예천PP#2 T/L","2025년 영주전력지사  GIS 정밀점검공사","2025년 영주전력지사  GIS 정밀점검공사","2025-09-10 14:00","2025-09-10 18:30","2025-09-10 14:00","2025-09-10 18:30","연속"]
[363,"경북","영주","신영주S/S CB 7500","2025년 영주전력지사  GIS 정밀점검공사","2025년 영주전력지사  GIS 정밀점검공사","2025-09-11 09:00","2025-09-13 19:00","2025-09-11 09:00","2025-09-13 19:00","연속"]
[364,"경북","영주","신영주예천PP#2 T/L","2025년 영주전력지사  GIS 정밀점검공사","2025년 영주전력지사  GIS 정밀점검공사","2025-09-13 14:00","2025-09-13 18:30","2025-09-13 14:00","2025-09-13 18:30","연속"]
[365,"경북","영주","신영주S/S CB 7671","2025년 영주전력지사  GIS 정밀점검공사","2025년 영주전력지사  GIS 정밀점검공사","2025-09-15 09:00","2025-09-17 19:00","2025-09-15 09:00","2025-09-17 19:00","연속"]
[366,"경북","영주","신영주예천PP#1 T/L","2025년 영주전력지사  GIS 정밀점검공사","2025년 영주전력지사  GIS 정밀점검공사","2025-09-17 14:00","2025-09-17 18:30","2025-09-17 14:00","2025-09-17 18:30","연속"]
[367,"경북","영주","신영주S/S CB 7600","2025년 영주전력지사  GIS 정밀점검공사","2025년 영주전력지사  GIS 정밀점검공사","2025-09-18 09:00","2025-09-20 19:00","2025-09-18 09:00","2025-09-20 19:00","연속"]
[368,"경북","영주","신영주예천PP#1 T/L","2025년 영주전력지사  GIS 정밀점검공사","2025년 영주전력지사  GIS 정밀점검공사","2025-09-20 14:00","2025-09-20 18:30","2025-09-20 14:00","2025-09-20 18:30","연속"]
[369,"경북","영주","신한울한울#1 T/L","2025년 영주전력지사 송전협력회사 공사"," 신한울-한울연락1T/L 수평추락방지장치 설치","2025-09-22 08:00","2025-09-22 17:00","취소","취소","연속"]
[370,"경북","영주","신한울한울#2 T/L","2025년 영주전력지사 송전협력회사 공사","  신한울-한울연락2T/L 수평추락방지장치 설치","2025-09-23 08:00","2025-09-22 17:00","취소","취소","연속"]
[371,"경북","영주","한울1NP한울2NP#1 T/L","2025년 영주전력지사 송전협력회사 공사","  한울연락1T/L 수평추락방지장치 설치","2025-09-24 08:00","2025-09-24 17:00","취소","취소","연속"]
[372,"경북","영주","한울1NP한울2NP#2 T/L","2025년 영주전력지사 송전협력회사 공사","  한울연락2T/L 수평추락방지장치 설치","2025-09-25 08:00","2025-09-25 17:00","취소","취소","연속"]
[373,"경북","영주","한울2NP한울3NP#3 T/L","2025년 영주전력지사 송전협력회사 공사","  한울연락3T/L 수평추락방지장치 설치","2025-09-26 08:00","2025-09-26 17:00","취소","취소","연속"]
[374,"경북","영주","한울2NP한울3NP#4 T/L","2025년 영주전력지사 송전협력회사 공사","  한울연락4T/L 수평추락방지장치 설치","2025-09-29 08:00","2025-09-29 17:00","취소","취소","연속"]
[375,"부산울산","동부산","신고리고리NP#4 T/L","25-26년 직할 지중송전 협력회사 공사","고리통합#2C/T 및 신고리#2C/T 내 해당 선로의 피뢰기 휨, 볼트 체결 상태 등 설비 확인","2025-09-02 09:00","2025-09-02 18:00","2025-09-02 09:00","2025-09-02 18:00","연속"]
[376,"부산울산","북부산","서부산북부산#2 T/L","북부산S/S  #2Sh.R 대체공사","북부산S/S  #2Sh.R 대체공사 시험가압 (#2SH.R + 서부산-북부산#2T/L)","2025-09-01 09:00","2025-09-01 18:00","2025-09-13 08:00","2025-09-14 08:00","연속"]
[377,"부산울산","북부산","북부산S/S #3 M.Tr","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S #3M.Tr 보통점검","2025-09-29 09:00","2025-10-01 18:00","2025-09-29 09:00","2025-10-01 18:00","연속"]
[378,"부산울산","서부산","서부산북부산#3 T/L"," 서부산-북부산#3T/L 유지접속함 교체공사"," 서부산-북부산#3T/L 유지접속함 교체공사 - J/B#1-2, 33, 42, 50, 54","2025-09-02 09:00","2026-01-30 18:00","2025-09-20 09:00","2025-12-19 18:00","연속"]
[379,"부산울산","울산","동울산신울산 T/L","2024-2025년 울산전력지사 가공송전협력회사 공사"," 동울산-신울산 지반변위 감시용 CCTV 가공지선 보조 전원설치 ○ 대상 :  동울산-신울산T/L ○ 구간 :  동울산-신울산T/L 25호","2025-09-15 09:00","2025-09-16 18:00","2025-09-27 09:00","2025-09-28 18:00","연속"]
[380,"부산울산","울산","동울산S/S CB 7272","'24~'25년 울산전력 변전협력회사 총액공사","7272 GIS 보통점검","2025-09-18 10:00","2025-09-18 16:00","2025-09-18 10:00","2025-09-18 16:00","연속"]
[381,"부산울산","울산","동울산S/S CB 7200","'24~'25년 울산전력 변전협력회사 총액공사","7200 GIS 보통점검","2025-09-17 10:00","2025-09-17 16:00","2025-10-22 10:00","2025-10-22 16:00","연속"]
[382,"부산울산","울산","동울산S/S CB 7271","'24~'25년 울산전력 변전협력회사 총액공사","7271 GIS 보통점검","2025-09-22 10:00","2025-09-22 16:00","2025-09-22 10:00","2025-09-22 16:00","연속"]
[383,"부산울산","울산","동울산S/S CB 7472","'24~'25년 울산전력 변전협력회사 총액공사","7472 GIS 보통점검","2025-09-19 10:00","2025-09-19 16:00","2025-09-19 10:00","2025-09-19 16:00","연속"]
[384,"부산울산","울산","신온산S/S #3 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","- 1, 2차 부싱절연유 채유 - 변압기 추락방지장치 설치","2025-09-29 09:00","2025-09-29 18:00","2025-09-29 09:00","2025-09-29 18:00","연속"]
[385,"부산울산","울산","신온산S/S CB 7472","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-09-22 09:00","2025-09-22 18:00","2025-09-22 09:00","2025-09-22 18:00","연속"]
[386,"부산울산","울산","신온산S/S CB 7400","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[387,"부산울산","울산","신온산S/S CB 7471","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-09-24 09:00","2025-09-24 18:00","2025-09-24 09:00","2025-09-24 18:00","연속"]
[388,"부산울산","울산","신온산S/S CB 7300","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-09-25 09:00","2025-09-25 18:00","2025-09-25 09:00","2025-09-25 18:00","연속"]
[389,"부산울산","울산","신온산S/S CB 7400","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[390,"부산울산","울산","신온산S/S #1 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","- 변압기 추락방지장치 설치","2025-09-30 09:00","2025-09-30 18:00","2025-09-30 09:00","2025-09-30 18:00","연속"]
[391,"부산울산","울산","신울산S/S #1 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#1M.Tr) 1차측 개착식 관로(L=269m) 구간 굴착 및 가시설 설치","2025-09-20 09:00","2025-09-28 18:00","2025-09-20 09:00","2025-09-28 18:00","연속"]
[392,"부산울산","울산","신울산S/S #5 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#5M.Tr) 1차측 개착식 관로(L=269m) 구간 굴착 및 가시설 설치","2025-09-27 09:00","2025-10-04 18:00","2025-09-27 09:00","2025-10-04 18:00","연속"]
[393,"부산울산","울산","신울산S/S CB 7A72"," 신울산S/S STATCOM 설치공사"," 신울산S/S STATCOM 피뢰기 이설 공사","2025-09-08 09:00","2025-11-07 18:00","2025-09-08 09:00","2025-11-07 18:00","연속"]
[394,"부산울산","울산","신울산S/S #3 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#3M.Tr) 1차측 개착식 관로(L=269m) 구간 굴착 및 가시설 설치","2025-09-05 09:00","2025-09-14 18:00","2025-09-05 09:00","2025-09-14 18:00","연속"]
[395,"부산울산","울산","신울산S/S CB 7A00"," 신울산S/S STATCOM 설치공사"," 신울산S/S STATCOM 피뢰기 이설 공사","2025-09-08 09:00","2025-11-07 18:00","2025-09-08 09:00","2025-11-07 18:00","연속"]
[396,"부산울산","울산","신울산S/S #4 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#4M.Tr) 1차측 개착식 관로(L=269m) 구간 굴착 및 가시설 설치","2025-09-13 09:00","2025-09-21 18:00","2025-09-13 09:00","2025-09-21 18:00","연속"]
[397,"부산울산","울산","울주S/S #2 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","2차 GIS 부분방전관련 조치작업","2025-09-01 09:00","2025-09-02 18:00","2025-09-01 09:00","2025-09-02 18:00","연속"]
[398,"부산울산","울산","울주S/S #4 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","#4M.Tr 3차 현대화 공사","2025-09-10 09:00","2025-11-07 18:00","2025-09-10 09:00","2025-11-07 18:00","연속"]
[399,"부산울산","울산","울주S/S CB 7971","'24~'25년 울산전력 변전협력회사 총액공사","7971 GIS 동작시험","2025-09-09 08:00","2025-09-09 10:00","2025-09-09 08:00","2025-09-09 10:00","연속"]
[400,"부산울산","울산","울주S/S CB 7900","'24~'25년 울산전력 변전협력회사 총액공사","7900 GIS 동작시험","2025-09-08 08:00","2025-09-08 10:00","2025-09-08 08:00","2025-09-08 10:00","연속"]
[401,"경남","김해송변전부","신김해S/S #1 M.Tr","신김해S/S  #1M.Tr 3차측 현대화공사","신김해S/S  #1M.Tr 3차측 현대화공사","2025-09-01 08:00","2025-10-17 18:00","취소","취소","연속"]
[402,"경남","직할","신김해창원#2 T/L","2025년 직할  GIS 정밀점검 시험가압용","2025년 직할  GIS 정밀점검 시험가압용 - 창원S/S 7400 GIS 시험가압용","2025-09-26 09:00","2025-09-26 18:00","취소","취소","연속"]
[403,"경남","직할","창원신고성#2 T/L"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사"," 창원-신고성T/L 155~158호 등 3개 구간 전력선 교체공사","2025-09-26 07:00","2025-10-04 18:00","2025-09-26 07:00","2025-10-04 18:00","연속"]
[404,"경남","직할","창원S/S CB 7471","2025년 직할  GIS 정밀점검(단독휴전)","2025년 직할  GIS 정밀점검(단독휴전) - 신김해-창원#2T/L 7471 GIS 선로휴전(시험가압 : 자단)","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[405,"경남","직할","신김해창원#2 T/L","2025년 직할  GIS 정밀점검 시험가압용","2025년 직할  GIS 정밀점검 시험가압용 - 신김해-창원#2T/L 7471 GIS 선로휴전(시험가압 : 자단)","2025-09-19 09:00","2025-09-19 18:00","2025-09-19 09:00","2025-09-19 18:00","연속"]
[406,"경남","직할","창원S/S CB 7400","2025년 직할  GIS 정밀점검(단독휴전)","2025년 직할  GIS 정밀점검(단독휴전) - 창원S/S 7400 GIS 단독휴전 - 시험가압 : 신김해-창원#2T/L 7471 GIS","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[407,"경남","직할","창원S/S CB 7300","2025년 직할  GIS 정밀점검(단독휴전)","2025년 직할  GIS 정밀점검(단독휴전) - 창원S/S 7300 GIS 단독휴전 - 시험가압 : 창원-신고성#1T/L 7371 GIS","2025-09-29 09:00","2025-10-03 18:00","2025-09-29 09:00","2025-10-03 18:00","연속"]
[408,"경남","직할","창원신고성#1 T/L"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사"," 창원-신고성T/L 155~158호 등 3개 구간 전력선 교체공사","2025-09-16 07:00","2025-09-24 18:00","2025-09-16 07:00","2025-09-24 18:00","연속"]
[409,"경남","직할","신김해창원#1 T/L","2025년 직할  GIS 정밀점검 시험가압용","2025년 직할  GIS 정밀점검 시험가압용 - 창원S/S 7100 GIS 시험가압용","2025-09-12 09:00","2025-09-12 18:00","2025-09-12 09:00","2025-09-12 18:00","연속"]
[410,"경남","직할","창원S/S CB 7100","2025년 직할  GIS 정밀점검(단독휴전)","2025년 직할  GIS 정밀점검(단독휴전) - 창원S/S 7100 GIS 단독휴전 - 시험가압 : 신김해-창원#1T/L 7171 GIS","2025-09-08 09:00","2025-09-12 18:00","2025-09-08 09:00","2025-09-12 18:00","연속"]
[411,"경남","직할","창원S/S CB 7171","2025년 직할  GIS 정밀점검(단독휴전)","2025년 직할  GIS 정밀점검(단독휴전) - 신김해-창원#1T/L 7171 GIS 선로휴전 (시험가압 : 자단)","2025-09-01 09:00","2025-09-05 18:00","2025-09-01 09:00","2025-09-05 18:00","연속"]
[412,"경남","직할","신김해창원#1 T/L","2025년 직할  GIS 정밀점검 시험가압용","2025년 직할  GIS 정밀점검 시험가압용 - 신김해-창원#1T/L 7171 GIS 선로휴전 (시험가압 : 자단)","2025-09-05 09:00","2025-09-05 18:00","2025-09-05 09:00","2025-09-05 18:00","연속"]
[413,"경남","진주","의령산청양수#2 T/L","산청P/P 의령-산청양수#2T/L 7172 조작 및 7200 보통 등","산청P/P 의령-산청양수#2T/L 7172 조작 및 7200 보통, LA(A,B,C) 하자, PT(A) 하자점검 [병행, 의령]  의령-산청양수#2T/L LA(A,B,C) 하자","2025-09-16 09:00","2025-09-16 18:00","2025-09-16 09:00","2025-09-16 18:00","연속"]
[414,"경남","진주","고령의령#2 T/L"," 고령-의령#2T/L 수평 추락방지장치 설치공사"," 고령-의령#2T/L 39호 등 48기 와이어형 수평 추락방지장치 설치공사","2025-09-08 07:00","2025-09-14 18:00","취소","취소","매일"]
[415,"경남","진주","고령의령#1 T/L"," 고령-의령#1T/L 수평 추락방지장치 설치공사"," 고령-의령#1T/L 39호 등 48기 와이어형 수평 추락방지장치 설치공사","2025-09-01 07:00","2025-09-07 18:00","취소","취소","매일"]
[416,"경남","진주","고령의령#2 T/L"," 고령-의령#2T/L 수평 추락방지장치 설치공사"," 고령-의령#2T/L 82호 등 24기 와이어형 수평 추락방지장치 설치공사","2025-09-27 07:00","2025-09-28 18:00","취소","취소","매일"]
[417,"경남","진주","신남원의령#2 T/L"," 신남원-의령T/L 추락방지장치 설치 공사"," 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2025-09-22 07:00","2025-09-26 18:00","2025-09-22 07:00","2025-09-26 18:00","매일"]
[418,"경남","진주","의령S/S CB 7A71","의령S/S  의령-신마산#2T/L LA 하자, PT 보통","의령S/S  의령-신마산#2T/L LA 하자, PT 보통","2025-09-18 09:00","2025-09-18 15:00","취소","취소","연속"]
[419,"경남","진주","의령S/S CB 7971","의령S/S  의령-신마산#1T/L LA 하자","의령S/S  의령-신마산#1T/L LA 하자","2025-09-18 15:00","2025-09-18 18:00","2025-09-18 15:00","2025-09-18 18:00","연속"]
[420,"경남","진주","신남원의령#1 T/L"," 신남원-의령T/L 추락방지장치 설치 공사"," 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2025-09-19 07:00","2025-09-19 18:00","취소","취소","매일"]
[421,"경남","진주","의령S/S CB 7871","의령S/S  신남원-의령#1T/L LA 하자,PT하자","의령S/S  신남원-의령#1T/L LA 하자,PT하자","2025-09-19 09:00","2025-09-19 15:00","2025-09-19 09:00","2025-09-19 15:00","연속"]
[422,"경남","진주","고령의령#1 T/L"," 고령-의령#1T/L 수평 추락방지장치 설치공사"," 고령-의령#1T/L 82호 등 24기 와이어형 수평 추락방지장치 설치공사","2025-09-20 07:00","2025-09-21 18:00","취소","취소","매일"]
[423,"경남","진주","의령S/S CB 7671","의령S/S  고령-의령#1T/L LA,PT 보통점검","의령S/S  고령-의령#1T/L LA(A,B,C),PT(A,B,C) 보통점검","2025-09-11 09:00","2025-09-11 15:00","2025-09-11 09:00","2025-09-11 15:00","연속"]
[424,"경남","진주","의령S/S CB 7571","의령S/S  고령-의령#2T/L LA 보통점검 등","의령S/S  고령-의령#2T/L LA 보통점검 유압저하경보(B,C상) 확인","2025-09-12 09:00","2025-09-12 15:00","2025-09-12 09:00","2025-09-12 15:00","연속"]
[425,"경남","진주","하동T/P CB 7671","하동T/P  광양-하동화력#2T/L GIS 보통점검 등","하동T/P  광양-하동화력#2T/L GIS 보통점검, LA(A,B,C) 보통","2025-09-15 10:00","2025-09-15 18:00","2025-09-15 10:00","2025-09-15 18:00","연속"]
[426,"경남","진주","하동T/P CB 7371","하동T/P  7371,7300,7372 GIS 조작시험","하동T/P  7371,7300,7372 GIS 조작시험","2025-09-30 10:00","2025-09-30 12:00","2025-09-30 10:00","2025-09-30 12:00","연속"]
[427,"경남","진주","하동T/P CB 7372","하동T/P  7371,7300,7372 GIS 조작시험","하동T/P  7371,7300,7372 GIS 조작시험","2025-09-30 15:00","2025-09-30 17:00","2025-09-30 12:00","2025-09-30 15:00","연속"]
[428,"경남","진주","하동T/P CB 7300","하동T/P  7371,7300,7372 GIS 조작시험","하동T/P  7371,7300,7372 GIS 조작시험","2025-09-30 12:00","2025-09-30 15:00","취소","취소","연속"]
[429,"경남","통영","신고성S/S #3 M.Tr","신고성S/S #3M.Tr 2차 GIS 보통점검, 부싱절연유 채유 등","#3M.Tr 2차 GIS 보통점검, 부싱절연유 채유 및 도블 측정, 1,2차 LA 대체","2025-09-16 09:30","2025-09-17 18:00","2025-09-16 09:30","2025-09-17 18:00","연속"]
[430,"경남","함안","신마산S/S #1 M.Tr","신마산S/S  #1 M.Tr 2차 GCB 보통점검 등","신마산S/S  #1 M.Tr 2차 GCB 보통점검 등","2025-09-16 09:30","2025-09-17 17:30","2025-09-16 09:30","2025-09-17 17:30","연속"]
[431,"경남","함안","신마산S/S #3 M.Tr","신마산S/S  #3 M.Tr 2차 GCB 보통점검 등","신마산S/S  #3 M.Tr 2차 GCB 보통점검 등","2025-09-18 09:30","2025-09-19 17:30","2025-09-18 09:30","2025-09-19 17:30","연속"]
[432,"경남","함안","신마산S/S #4 M.Tr","신마산S/S  #4 M.Tr 보통점검 등","신마산S/S  #4 M.Tr 보통점검 등","2025-09-23 09:30","2025-09-26 17:30","2025-09-23 09:30","2025-09-26 17:30","연속"]
[433,"경남","함안","신마산S/S #5 M.Tr","신마산S/S  #5 M.Tr 2차 GCB 보통점검 등","신마산S/S  #5 M.Tr 2차 GCB 보통점검 등","2025-09-29 09:30","2025-09-30 17:30","2025-09-29 09:30","2025-09-30 17:30","연속"]

{"sheet":"154설비","index":2,"n_rows":899,"n_cols":12,"rows_kept":899,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 9월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","천호구의#1 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 하자점검","2025-09-25 09:00","2025-09-25 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[2,"서울","성동","천호구의#2 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 하자점검","2025-09-26 09:00","2025-09-26 18:00","2025-09-19 09:00","2025-09-19 18:00","연속"]
[3,"서울","성동","군자성수 T/L"," 군자성수T/L 보호반 이설(화양성수#2T/L 재사용)"," 군자성수T/L 보호반(군자S/S 측) 이설작업 - 화양성수#2T/L용 보호반으로 재사용","2025-09-24 09:00","2025-09-26 18:00","2025-09-24 09:00","2025-09-26 18:00","연속"]
[4,"서울","성동","성수뚝도#1 T/L","2025년 성동P/O 변전협력회사 공사","43PDA 교체","2025-09-08 09:00","2025-09-08 18:00","취소","취소","연속"]
[5,"서울","성동","성수뚝도#1 T/L","뚝도변전소 인출 OF케이블 선종교체공사","OF케이블 선종교체(→XLPE) : 뚝도EBG ∼ J/B#13(7) - 대상선로 : 광장뚝도#1, 광장뚝도#2, 성수뚝도#1T/L (3C×0.06㎞)","2025-09-08 09:00","2025-10-28 18:00","2025-09-22 09:00","2025-11-07 18:00","연속"]
[6,"서울","성동","방학창동#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-26 09:00","2025-09-26 14:00","2025-09-27 09:00","2025-09-28 18:00","연속"]
[7,"서울","성동","장암방학#1 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검","2025-09-25 09:00","2025-09-27 18:00","2025-09-25 09:00","2025-09-27 18:00","연속"]
[8,"서울","성동","방학창동#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-27 14:00","2025-09-27 18:00","2025-09-27 14:00","2025-09-27 18:00","연속"]
[9,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검","2025-09-29 09:00","2025-10-01 18:00","2025-09-29 09:00","2025-10-01 18:00","연속"]
[10,"서울","성동","방학창동#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-30 09:00","2025-09-30 14:00","2025-09-30 09:00","2025-09-30 14:00","연속"]
[11,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-09 09:00","2025-09-09 14:00","2025-09-09 09:00","2025-09-09 14:00","연속"]
[12,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-10 14:00","2025-09-10 18:00","2025-09-10 14:00","2025-09-10 18:00","연속"]
[13,"서울","성동","방학창동#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검","2025-09-11 09:00","2025-09-13 18:00","2025-09-11 09:00","2025-09-13 18:00","연속"]
[14,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-24 14:00","2025-09-24 18:00","2025-09-24 14:00","2025-09-24 18:00","연속"]
[15,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-23 09:00","2025-09-23 14:00","2025-09-23 09:00","2025-09-23 14:00","연속"]
[16,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-18 14:00","2025-09-18 18:00","2025-09-18 14:00","2025-09-18 18:00","연속"]
[17,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-17 09:00","2025-09-17 14:00","2025-09-17 09:00","2025-09-17 14:00","연속"]
[18,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-13 14:00","2025-09-13 18:00","2025-09-12 09:00","2025-09-12 14:00","연속"]
[19,"서울","성동","장암방학#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-09-12 09:00","2025-09-12 14:00","2025-09-12 09:00","2025-09-12 14:00","연속"]
[20,"서울","성동","창동쌍문#2 T/L","2025 성동전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2025-09-30 09:00","2025-09-30 18:00","2025-09-30 09:00","2025-09-30 18:00","연속"]
[21,"서울","성동","창동쌍문#1 T/L","2025 성동전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2025-09-29 09:00","2025-09-29 18:00","2025-09-29 09:00","2025-09-29 18:00","연속"]
[22,"서울","중부","동빙고반포#2 T/L","OF 케이블 절연유 시료채취","- 채유개소 : TIJ1, 보광EBA","2025-09-10 09:00","2025-09-10 18:00","2025-09-10 09:00","2025-09-10 18:00","연속"]
[23,"서울","중부","동빙고반포#1 T/L","OF 케이블 절연유 시료채취","- 채유개소 : TIJ1, 보광EBG","2025-09-09 09:00","2025-09-09 18:00","2025-09-09 09:00","2025-09-09 18:00","연속"]
[24,"서울","중부","수색상암 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","GIS 정밀점검","2025-09-27 09:00","2025-09-28 18:00","2025-09-27 09:00","2025-09-28 18:00","연속"]
[25,"서울","중부","원흥상암 T/L"," 수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : '25.2.25~26.10.23","2025-09-09 09:00","2025-10-31 18:00","취소","취소","연속"]
[26,"서울","중부","중부아현 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","GIS 정밀점검","2025-09-24 09:00","2025-09-26 18:00","2025-09-24 09:00","2025-09-26 18:00","연속"]
[27,"서울","중부","중부용산#2 T/L","OF 케이블 절연유 시료채취","- 채유개소 : 용산EBG, SJ1, SJ13, Sj26, 중부EBG","2025-09-11 09:00","2025-09-11 18:00","2025-09-11 09:00","2025-09-11 18:00","연속"]
[28,"서울","중부","중부S/S CB 6100","2025년 중부S/S  장기사용 GIS 교체공사(3차)","-  GIS 교체(#6100BUS-TIE, #62M.Tr 1차) - 기타 부대공사","2025-09-22 09:00","2025-10-24 18:00","취소","취소","연속"]
[29,"서울","중부","중부S/S #65 BUS","2025년 중부S/S  장기사용 GIS 교체공사(3차)","-  GIS 교체(#6100BUS-TIE, #62M.Tr 1차) - 기타 부대공사","2025-09-22 09:00","2025-09-25 09:00","취소","취소","연속"]
[30,"서울","중부","중부S/S #60 BUS","2025년 중부S/S  장기사용 GIS 교체공사(3차)","-  GIS 교체(#6100BUS-TIE, #62M.Tr 1차) - 기타 부대공사","2025-09-25 09:00","2025-10-14 09:00","취소","취소","연속"]
[31,"서울","중부","중부마포 T/L","2025년 중부전력지사 변전협력회사 공사","GIS 초기점검","2025-09-29 10:00","2025-09-29 18:00","2025-09-24 09:00","2025-09-26 18:00","연속"]
[32,"서울","중부","중부연대 T/L","2025년 중부전력지사 변전협력회사 공사","GIS 초기점검","2025-09-30 10:00","2025-09-30 18:00","2025-09-24 09:00","2025-09-26 18:00","연속"]
[33,"서울","직할","원남미아#1 T/L"," 원남-미아T/L(미아S/S 측) 선종교체공사","OF케이블 선종교체(→XLPE) : 미아S/S EBG ~ J/B#5 (2C x 1.8 km)","2025-09-01 09:30","2026-01-09 18:00","2025-09-01 09:30","2026-01-09 18:00","연속"]
[34,"서울","직할","돈암안암#2 T/L","25년 직할 변전정비협력회사 총액공사","돈암,안암S/S 돈암안암#2T/L 보호반 대체","2025-09-29 10:00","2025-10-03 17:00","2025-09-29 10:00","2025-10-03 17:00","연속"]
[35,"서울","직할","중앙서소문 T/L","25년 변전협력회사 공사"," GIS 조작시험 ","2025-09-29 09:00","2025-09-29 18:00","2025-09-29 09:00","2025-09-29 18:00","연속"]
[36,"남서울","강남","동빙고반포#1 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검 무부하가압","2025-09-26 14:00","2025-09-26 16:00","2025-09-26 14:00","2025-09-26 16:00","연속"]
[37,"남서울","강남","신사반포#2 T/L","24-25년도 강남전력 변전협력회사 총액공사","170kV GIS 전자변교체, 조작시험 포함","2025-09-29 14:00","2025-09-29 18:00","2025-09-29 14:00","2025-09-29 18:00","연속"]
[38,"남서울","강남","동빙고반포#2 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검 무부하가압","2025-09-23 14:00","2025-09-23 16:00","2025-09-23 14:00","2025-09-23 16:00","연속"]
[39,"남서울","강남","반포S/S #2 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #2DS 점검","2025-09-26 16:00","2025-09-27 18:00","2025-09-26 16:00","2025-09-27 18:00","연속"]
[40,"남서울","강남","동빙고반포#2 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검","2025-09-25 09:00","2025-09-27 18:00","2025-09-25 09:00","2025-09-27 18:00","연속"]
[41,"남서울","강남","반포S/S #2 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #2DS 점검","2025-09-23 16:00","2025-09-24 18:00","2025-09-23 16:00","2025-09-24 18:00","연속"]
[42,"남서울","강남","반포S/S #1 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #1DS 점검","2025-09-22 09:00","2025-09-23 16:00","2025-09-22 09:00","2025-09-23 16:00","연속"]
[43,"남서울","강남","동빙고반포#1 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검","2025-09-22 09:00","2025-09-24 18:00","2025-09-22 09:00","2025-09-24 18:00","연속"]
[44,"남서울","강남","반포S/S CB 6100","24-25년도 강남전력지사 변전협력회사 총액공사","GIS 조작시험 및 전자변 교체","2025-09-19 09:00","2025-09-19 18:00","2025-09-19 09:00","2025-09-19 18:00","연속"]
[45,"남서울","강남","반포S/S #1 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #1DS 점검","2025-09-25 09:00","2025-09-26 16:00","2025-09-25 09:00","2025-09-26 16:00","연속"]
[46,"남서울","강남","신사반포#1 T/L","24-25년도 강남전력 변전협력회사 총액공사","170kV GIS 전자변 교체공사 및 조작시험","2025-09-29 09:00","2025-09-29 14:00","2025-09-29 09:00","2025-09-29 14:00","연속"]
[47,"남서울","강남","사당봉천#2 T/L","사당S/S  공사 관련 LID 이설공사","사당S/S  공사 관련 LID 이설공사","2025-09-18 09:00","2025-09-18 18:00","취소","취소","연속"]
[48,"남서울","강남","사당봉천#1 T/L","사당S/S  공사 관련 LID 이설공사","사당S/S  공사 관련 LID 이설공사","2025-09-17 09:00","2025-09-17 18:00","취소","취소","연속"]
[49,"남서울","강남","사당신림 T/L","사당S/S  공사 관련 LID 이설공사","사당S/S  공사 관련 LID 이설공사","2025-09-16 09:00","2025-09-16 18:00","취소","취소","연속"]
[50,"남서울","강남","신양재S/S #65 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #2DS 점검","2025-09-30 16:00","2025-10-01 18:00","취소","취소","연속"]
[51,"남서울","강남","신양재신사#3 T/L","강남전력지사  GIS 정밀점검","OF 케이블 절연유 채유 및  GIS 정밀점검 무부하가압","2025-09-30 09:00","2025-09-30 16:00","취소","취소","연속"]
[52,"남서울","강남","신양재S/S #60 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #1DS 점검","2025-09-29 09:00","2025-09-30 16:00","취소","취소","연속"]
[53,"남서울","강남","신양재과천#2 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검","2025-09-29 09:00","2025-10-01 18:00","취소","취소","연속"]
[54,"남서울","강남","신양재역삼#3 T/L","송전선로 OF 케이블 절연유 채유","OF 케이블 절연유 채유","2025-09-22 09:00","2025-09-22 13:00","취소","취소","연속"]
[55,"남서울","동서울","강동천호#2 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","강동S/S 강동-천호#2T/L GIS 조작시험","2025-09-19 14:00","2025-09-19 18:00","취소","취소","연속"]
[56,"남서울","동서울","강동천호#1 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","강동S/S 강동-천호#1T/L GIS 조작시험","2025-09-19 09:00","2025-09-19 14:00","취소","취소","연속"]
[57,"남서울","동서울","동서울강동#2 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","동서울S/S 동서울-강동#2T/L PITR 인터록 회로 구성(강동측 병행)","2025-09-11 09:00","2025-09-11 18:00","2025-09-11 09:00","2025-09-11 18:00","연속"]
[58,"남서울","동서울","동서울강동#1 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","동서울S/S 동서울-강동#1T/L PITR 인터록 회로 구성(강동측 병행)","2025-09-10 09:00","2025-09-10 18:00","2025-09-10 09:00","2025-09-10 18:00","연속"]
[59,"남서울","동서울","논현선릉#2 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","선릉S/S 논현-선릉#2T/L GIS 조작시험","2025-09-05 14:00","2025-09-05 18:00","2025-09-05 14:00","2025-09-05 18:00","연속"]
[60,"남서울","동서울","논현선릉#1 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","선릉S/S 논현-선릉#1T/L GIS 조작시험","2025-09-05 09:00","2025-09-05 14:00","2025-09-05 09:00","2025-09-05 14:00","연속"]
[61,"남서울","동서울","산성수서#2 T/L"," 산성-수서T/L 지중화공사(2단계)"," 산성-수서#2T/L 지중화(2단계) - 발주처 : LH - 지중화공사에 따른 케이블 철거 및 포설, 접속","2025-09-16 09:00","2025-10-15 18:00","2025-09-16 09:00","2025-10-15 18:00","연속"]
[62,"남서울","동서울","동서울신장#2 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","신장S/S 동서울-신장#2T/L 보통점검, PITR 인터록 회로 구성(동서울측 병행)","2025-09-09 09:00","2025-09-09 18:00","2025-09-09 09:00","2025-09-09 18:00","연속"]
[63,"남서울","동서울","동서울신장#1 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","신장S/S 동서울-신장#1T/L 보통점검, PITR 인터록 회로 구성(동서울측 병행)","2025-09-08 09:00","2025-09-08 18:00","2025-09-08 09:00","2025-09-08 18:00","연속"]
[64,"남서울","동서울","잠실탄천#2 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","잠실S/S 잠실-탄천#2T/L GIS 보통점검(탄천측 보통점검 병행)","2025-09-02 09:00","2025-09-02 18:00","취소","취소","연속"]
[65,"남서울","동서울","잠실탄천#1 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","잠실S/S 잠실-탄천#1T/L GIS 보통점검(탄천측 보통점검 병행)","2025-09-01 09:00","2025-09-01 18:00","취소","취소","연속"]
[66,"남서울","영등포","구공독산 T/L","2025년 영등포전력지사 변전협력회사 총액공사","구공S/S 170kV GIS 초기점검(구공-독산T/L) 독산S/S 170kV GIS 보통점검(구공-독산T/L)","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[67,"남서울","영등포","상암등촌#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 등촌S/S 6433 정밀점검 후 무부하가압","2025-09-30 16:00","2025-09-30 18:00","취소","취소","연속"]
[68,"남서울","영등포","등촌S/S #60 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 등촌S/S 611 내부 점검","2025-09-22 16:00","2025-09-26 18:00","취소","취소","연속"]
[69,"남서울","영등포","가양등촌#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","등촌S/S 611 내부 점검","2025-09-22 09:00","2025-09-26 18:00","취소","취소","연속"]
[70,"남서울","영등포","등촌S/S #60 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 등촌S/S 6433 정밀점검 후 무부하 가압용","2025-09-30 16:00","2025-09-30 18:00","취소","취소","연속"]
[71,"남서울","영등포","오류목동 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 오류-목동","2025-09-29 09:00","2025-10-01 18:00","2025-09-29 09:00","2025-10-01 18:00","연속"]
[72,"남서울","영등포","신문래목동#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신문래-목동#1","2025-09-23 09:00","2025-09-25 18:00","2025-09-23 09:00","2025-09-25 18:00","연속"]
[73,"남서울","영등포","신문래목동#2 T/L","2025년 영등포전력지사 변전협력회사 총액공사","목동S/S 신문래-목동#2T/L 보통점검","2025-09-19 09:00","2025-09-19 18:00","2025-09-19 09:00","2025-09-19 18:00","연속"]
[74,"남서울","영등포","신정목동#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 부천-신정#2 정밀점검 후 무부하가압(2DS+CB)","2025-09-20 12:00","2025-09-20 18:00","2025-09-20 12:00","2025-09-20 18:00","연속"]
[75,"남서울","영등포","신정S/S #2 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 부천-신정#2 정밀점검 및 무부하가압(2DS+CB)","2025-09-19 14:00","2025-09-20 18:00","2025-09-19 14:00","2025-09-20 18:00","연속"]
[76,"남서울","영등포","신정목동#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 부천-신정#2 정밀점검 후 무부하가압(1DS)","2025-09-19 10:00","2025-09-19 14:00","2025-09-19 10:00","2025-09-19 14:00","연속"]
[77,"남서울","영등포","부천신정#2 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 부천-신정#2","2025-09-18 09:00","2025-09-20 18:00","2025-09-18 09:00","2025-09-20 18:00","연속"]
[78,"남서울","영등포","신정S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 부천-신정#2 정밀점검 및 무부하가압(1DS)","2025-09-18 09:00","2025-09-19 14:00","2025-09-18 09:00","2025-09-19 14:00","연속"]
[79,"남서울","영등포","신정목동#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 부천-신정#1 정밀점검 후 무부하가압(2DS+CB)","2025-09-17 12:00","2025-09-17 18:00","2025-09-17 12:00","2025-09-17 18:00","연속"]
[80,"남서울","영등포","신정S/S #2 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 부천-신정#1 정밀점검 및 무부하가압(2DS+CB)","2025-09-16 14:00","2025-09-17 18:00","2025-09-16 14:00","2025-09-17 18:00","연속"]
[81,"남서울","영등포","신정목동#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 부천-신정#1 정밀점검 후 무부하가압(1DS)","2025-09-16 10:00","2025-09-16 14:00","2025-09-16 10:00","2025-09-16 14:00","연속"]
[82,"남서울","영등포","신정S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 부천-신정#1 정밀점검 및 무부하가압(1DS)","2025-09-15 09:00","2025-09-16 14:00","2025-09-15 09:00","2025-09-16 14:00","연속"]
[83,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 부천-신정#1","2025-09-15 09:00","2025-09-17 18:00","2025-09-15 09:00","2025-09-17 18:00","연속"]
[84,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신정-목동#2 정밀점검 후 무부하가압(2DS+CB)","2025-09-13 12:00","2025-09-13 18:00","2025-09-13 12:00","2025-09-13 18:00","연속"]
[85,"남서울","영등포","신정S/S #2 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신정-목동#2 정밀점검 및 무부하가압(2DS+CB)","2025-09-12 14:00","2025-09-13 18:00","2025-09-12 14:00","2025-09-13 18:00","연속"]
[86,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신정-목동#2 정밀점검 후 무부하가압(1DS)","2025-09-12 10:00","2025-09-12 14:00","2025-09-12 10:00","2025-09-12 14:00","연속"]
[87,"남서울","영등포","신정목동#2 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신정-목동#2","2025-09-11 09:00","2025-09-13 18:00","2025-09-11 09:00","2025-09-13 18:00","연속"]
[88,"남서울","영등포","신정S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신정-목동#2 정밀점검 및 무부하가압(1DS)","2025-09-11 09:00","2025-09-12 14:00","2025-09-11 09:00","2025-09-12 14:00","연속"]
[89,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신정-목동#1 정밀점검 후 무부하가압(2DS+CB)","2025-09-10 12:00","2025-09-10 18:00","취소","취소","연속"]
[90,"남서울","영등포","신정S/S #2 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신정-목동#1 정밀점검 및 무부하가압(2DS+CB)","2025-09-09 14:00","2025-09-10 18:00","취소","취소","연속"]
[91,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신정-목동#1 정밀점검 후 무부하가압(1DS)","2025-09-09 10:00","2025-09-09 14:00","취소","취소","연속"]
[92,"남서울","영등포","신정S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신정-목동#1 정밀점검 및 무부하가압(1DS)","2025-09-08 09:00","2025-09-09 14:00","취소","취소","연속"]
[93,"남서울","영등포","신정목동#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 신정-목동#1","2025-09-08 09:00","2025-09-10 18:00","취소","취소","연속"]
[94,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6233 정밀점검 후 무부하가압(2DS+CB)","2025-09-06 12:00","2025-09-06 18:00","취소","취소","연속"]
[95,"남서울","영등포","신정S/S #2 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6233 정밀점검 및 무부하가압(2DS+CB)","2025-09-05 14:00","2025-09-06 18:00","취소","취소","연속"]
[96,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6233 정밀점검 후 무부하가압(1DS)","2025-09-05 10:00","2025-09-05 14:00","취소","취소","연속"]
[97,"남서울","영등포","신정S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6233 정밀점검 및 무부하가압(1DS)","2025-09-04 09:00","2025-09-05 14:00","취소","취소","연속"]
[98,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6133 정밀점검 후 무부하가압(2DS+CB)","2025-09-03 12:00","2025-09-03 18:00","취소","취소","연속"]
[99,"남서울","영등포","신정S/S #2 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6133 정밀점검 및 무부하가압(2DS+CB)","2025-09-02 14:00","2025-09-03 18:00","취소","취소","연속"]
[100,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6133 정밀점검 후 무부하가압(1DS)","2025-09-02 10:00","2025-09-02 14:00","취소","취소","연속"]
[101,"남서울","영등포","신정S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6133 정밀점검 및 무부하가압(1DS)","2025-09-01 09:00","2025-09-02 14:00","취소","취소","연속"]
[102,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검공사(6100BUS-TIE, DS점검용)","170kV GIS 정밀점검공사(6100BUS-TIE, DS점검용)","2025-09-30 14:00","2025-10-01 18:00","2025-09-30 14:00","2025-10-01 18:00","연속"]
[103,"남서울","직할","신문래S/S #60 BUS","170kV GIS 정밀점검공사(6100BUS-TIE, DS점검용)","170kV GIS 정밀점검공사(6100BUS-TIE, DS점검용)","2025-09-29 09:00","2025-09-30 14:00","2025-09-29 09:00","2025-09-30 14:00","연속"]
[104,"남서울","직할","신문래S/S #66 BUS","170kV GIS 정밀점검공사(65-66SEC, DS점검용)","170kV GIS 정밀점검공사(65-66SEC, DS점검용)","2025-09-26 14:00","2025-09-27 18:00","2025-09-26 14:00","2025-09-27 18:00","연속"]
[105,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검공사(65-66SEC, DS점검용)","170kV GIS 정밀점검공사(65-66SEC, DS점검용)","2025-09-25 09:00","2025-09-26 14:00","2025-09-25 09:00","2025-09-26 14:00","연속"]
[106,"남서울","직할","신문래S/S #61 BUS","170kV GIS 정밀점검공사(60-61SEC, DS점검용)","170kV GIS 정밀점검공사(60-61SEC, DS점검용)","2025-09-23 14:00","2025-09-24 18:00","2025-09-23 14:00","2025-09-24 18:00","연속"]
[107,"남서울","직할","신문래S/S #60 BUS","170kV GIS 정밀점검공사(60-61SEC, DS점검용)","170kV GIS 정밀점검공사(60-61SEC, DS점검용)","2025-09-22 09:00","2025-09-23 14:00","2025-09-22 09:00","2025-09-23 14:00","연속"]
[108,"남서울","직할","신문래S/S SEC CB 60610","170kV GIS 정밀점검공사(60-61SEC)","170kV GIS 정밀점검공사(60-61SEC)","2025-09-22 09:00","2025-09-24 18:00","2025-09-22 09:00","2025-09-24 18:00","연속"]
[109,"남서울","직할","신문래S/S CB 6100","170kV GIS 정밀점검공사(6100BUS-TIE)","170kV GIS 정밀점검공사(6100BUS-TIE)","2025-09-29 09:00","2025-10-01 18:00","2025-09-29 09:00","2025-10-01 18:00","연속"]
[110,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사(65-66SEC, 무부하가압용)","170kV GIS 정밀점검공사(65-66SEC, 무부하가압용)","2025-09-27 14:00","2025-09-27 18:00","2025-09-27 14:00","2025-09-27 18:00","연속"]
[111,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(65-66SEC, 무부하가압용)","170kV GIS 정밀점검공사(65-66SEC, 무부하가압용)","2025-09-26 10:00","2025-09-26 14:00","2025-09-26 10:00","2025-09-26 14:00","연속"]
[112,"남서울","직할","신문래S/S SEC CB 65660","170kV GIS 정밀점검공사(65-66SEC)","170kV GIS 정밀점검공사(65-66SEC)","2025-09-25 09:00","2025-09-27 18:00","2025-09-25 09:00","2025-09-27 18:00","연속"]
[113,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사(60-61SEC, 무부하가압용)","170kV GIS 정밀점검공사(60-61SEC, 무부하가압용)","2025-09-24 14:00","2025-09-24 18:00","2025-09-24 14:00","2025-09-24 18:00","연속"]
[114,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(60-61SEC, 무부하가압용)","170kV GIS 정밀점검공사(60-61SEC, 무부하가압용)","2025-09-23 10:00","2025-09-23 14:00","2025-09-23 10:00","2025-09-23 14:00","연속"]
[115,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(6100BUS-TIE, 무부하가압용)","170kV GIS 정밀점검공사(6100BUS-TIE, 무부하가압용)","2025-09-30 10:00","2025-09-30 14:00","2025-09-30 10:00","2025-09-30 14:00","연속"]
[116,"인천","김포","영종경서 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-09-22 08:00","2025-09-25 18:00","2025-09-22 08:00","2025-09-25 18:00","연속"]
[117,"인천","김포","신경서경서#2 T/L","경서S/S  신경서-경서#2T/L GIS 조작시험","경서S/S  신경서-경서#2T/L GIS 조작시험","2025-09-25 10:00","2025-09-25 18:00","2025-09-25 10:00","2025-09-25 18:00","연속"]
[118,"인천","김포","신경서경서#3 T/L","경서S/S  신경서-경서#3T/L GIS 조작시험","경서S/S  신경서-경서#3T/L GIS 조작시험","2025-09-26 10:00","2025-09-26 18:00","2025-09-26 10:00","2025-09-26 18:00","연속"]
[119,"인천","김포","김포불로#2 T/L","불로S/S  불로-김포#2T/L GIS 하자점검","불로S/S  불로-김포#2T/L GIS 하자점검","2025-09-09 10:00","2025-09-09 18:00","취소","취소","연속"]
[120,"인천","김포","김포불로#1 T/L","불로S/S  불로-김포#1T/L GIS 하자점검","불로S/S  불로-김포#1T/L GIS 하자점검 (병행) 김포S/S 불로-김포#1T/L GIS 보통점검","2025-09-08 10:00","2025-09-08 18:00","취소","취소","연속"]
[121,"인천","김포","신김포양곡#1 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-09-08 08:00","2025-09-10 18:00","취소","취소","연속"]
[122,"인천","김포","신김포양곡#2 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-09-11 08:00","2025-09-12 18:00","취소","취소","연속"]
[123,"인천","김포","양촌양곡#2 T/L","양곡S/S  GIS 교체공사(4차)","- 양촌양곡#1T/L GIS 교체관련 송전선로 인하선 및 월부싱 철거작업 크레인 안전이격거리 확보","2025-09-19 04:00","2025-09-19 08:00","취소","취소","연속"]
[124,"인천","김포","양곡S/S #65 BUS","양곡S/S  GIS 교체공사(4차)","- 양촌양곡#1T/L GIS 교체","2025-09-21 15:00","2025-10-02 15:00","2025-09-21 15:00","2025-10-02 15:00","연속"]
[125,"인천","김포","양곡S/S CB 6100","양곡S/S  GIS 교체공사(4차)_B/T(6100)이용무부하","- BUS-TIE(6100) 이용 무부하 가압 - 양촌양곡#1T/L GIS 교체","2025-09-15 08:00","2025-09-15 09:00","2025-09-15 08:00","2025-09-15 09:00","연속"]
[126,"인천","김포","양촌양곡#1 T/L","양곡S/S  GIS 교체공사(4차)","- 양촌양곡#1T/L GIS 교체","2025-09-13 07:00","2025-10-02 18:00","2025-09-13 07:00","2025-10-02 18:00","연속"]
[127,"인천","김포","양곡S/S #65 BUS","양곡S/S  GIS 교체공사(4차)","- 양촌양곡#1T/L GIS 교체","2025-09-13 07:00","2025-09-15 09:00","2025-09-13 07:00","2025-09-15 09:00","연속"]
[128,"인천","김포","양곡S/S #60 BUS","양곡S/S  GIS 교체공사(4차)","- 양촌양곡#1T/L GIS 교체","2025-09-15 09:00","2025-09-20 15:00","2025-09-15 09:00","2025-09-20 15:00","연속"]
[129,"인천","김포","양곡S/S CB 6100","양곡S/S  GIS 교체공사(4차)_B/T(6100)이용무부하","- BUS-TIE(6100) 이용 무부하 가압 - 양촌양곡#1T/L GIS 교체","2025-09-20 15:00","2025-09-21 15:00","2025-09-20 15:00","2025-09-21 15:00","연속"]
[130,"인천","김포","왕길양촌#2 T/L","24~25년 부평,김포전력지사 가공송전 협력회사 공사","고정형폴리머점퍼지지애자 설치","2025-09-15 07:30","2025-09-15 18:00","취소","취소","연속"]
[131,"인천","부평","관교만수#1 T/L"," 관교-만수#1T/L  혼용화"," 관교-만수#1T/L  혼용화","2025-09-13 09:00","2025-09-13 18:00","취소","취소","연속"]
[132,"인천","부평","인천남인천#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2025-09-03 09:00","2025-09-03 18:00","2025-09-11 09:00","2025-09-11 18:00","연속"]
[133,"인천","부평","관교만수#2 T/L"," 관교-만수#2T/L 637 GIS 보통점검(오후), 혼용화"," 관교-만수#2T/L 637 GIS 보통점검(오후) 관교S/S 관교만수#2T/L  혼용화","2025-09-27 13:00","2025-09-27 18:00","취소","취소","연속"]
[134,"인천","부평","주안만수#2 T/L"," 주안-만수#2T/L 647 GIS 보통점검(오전)"," 주안-만수#2T/L 647 GIS 보통점검(오전)","2025-09-27 09:00","2025-09-27 13:00","취소","취소","연속"]
[135,"인천","부평","송현포스코CC#2 T/L"," 주안-관교등 4개T/L 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링 유니트점검 시행","2025-09-17 09:00","2025-09-19 18:00","2025-09-17 09:00","2025-09-19 18:00","연속"]
[136,"인천","부평","신가좌S/S Sh.R CB","신가좌S/S  #1Sh.R 보호IED 성능개선","신가좌S/S  #1Sh.R 보호IED 성능개선 - 피앤씨테크제 보호IED 펌웨어 업데이트","2025-09-17 09:00","2025-09-17 18:00","2025-09-17 09:00","2025-09-17 18:00","연속"]
[137,"인천","부평","신가좌인천#1 T/L"," 신가좌-인천#1T/L 627 GIS 조작, 전자변교체C"," 신가좌-인천#1T/L 627 GIS 조작, 전자변교체C","2025-09-20 09:00","2025-09-20 18:00","2025-09-20 09:00","2025-09-20 18:00","연속"]
[138,"인천","부평","원창포스코CC#1 T/L"," 원창-포스코CC #1T/L 보호반 대체"," 원창-포스코CC #1T/L 보호반 대체","2025-09-22 09:00","2025-09-26 18:00","취소","취소","연속"]
[139,"인천","부평","원창포스코CC#2 T/L"," 원창-포스코CC #2T/L 보호반 대체"," 원창-포스코CC #2T/L 보호반 대체","2025-09-29 09:00","2025-10-03 18:00","취소","취소","연속"]
[140,"인천","부평","영종을왕 T/L"," 영종-을왕T/L 접속함 해체점검","영종-을왕T/L J/B#4 C상 접속함 해체점검 (수분침투 원인 분석)","2025-09-29 09:00","2025-09-30 18:00","2025-09-29 09:00","2025-09-30 18:00","연속"]
[141,"인천","부평","신가좌주안#2 T/L"," 주안-관교등 4개T/L 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링 유니트점검 시행","2025-09-25 09:00","2025-09-27 18:00","취소","취소","연속"]
[142,"인천","부평","관교주안 T/L"," 주안-관교등 4개T/L 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링 유니트점검 시행","2025-09-29 09:00","2025-09-30 18:00","취소","취소","연속"]
[143,"인천","부평","주안만수#1 T/L"," 주안-만수#1T/L 667 GIS 보통점검"," 주안-만수#1T/L 667 GIS 보통점검","2025-09-21 09:00","2025-09-21 18:00","취소","취소","연속"]
[144,"인천","부평","주안S/S CB 6100"," #60-#65 BUS TIE 6100 GIS 보통,모자익철거"," #60-#65 BUS TIE 6100 GIS 보통점검","2025-09-21 09:00","2025-09-21 18:00","취소","취소","연속"]
[145,"인천","부평","신가좌주안#1 T/L"," 주안-관교등 4개T/L 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링 유니트점검 시행","2025-09-22 09:00","2025-09-24 18:00","취소","취소","연속"]
[146,"인천","시흥","오봉남동#2 T/L","남동S/S 혼용화공사","남동S/S 혼용화공사 관련 휴전","2025-09-23 09:00","2025-09-23 18:00","2025-09-07 09:00","2025-09-07 18:00","연속"]
[147,"인천","시흥","오봉남동#1 T/L","남동S/S 혼용화공사","남동S/S 혼용화공사 관련 휴전","2025-09-22 09:00","2025-09-22 18:00","2025-09-06 09:00","2025-09-06 18:00","연속"]
[148,"인천","시흥","남동연수#2 T/L","남동S/S 혼용화공사","남동S/S 혼용화공사 관련 휴전","2025-09-19 09:00","2025-09-19 18:00","2025-09-10 09:00","2025-09-10 18:00","연속"]
[149,"인천","시흥","남동연수#1 T/L","남동S/S 혼용화공사","남동S/S 혼용화공사 관련 휴전","2025-09-18 09:00","2025-09-18 18:00","2025-09-09 09:00","2025-09-09 18:00","연속"]
[150,"인천","시흥","신시흥남동#2 T/L","인천남동 첨단산업단지  신시흥-남동T/L 지중화공사","1. 공사구간 :  신시흥-남동T/L No.35～신동C/T 2. 선로길이 : ACSR/AW 410㎟ × 2B × 2C, 0.364km  XLPE 2000㎟ / 2C(D) x 0.6km (M/H#7 ~ 신설C/T) 3. 지 지 물 : C/T 신설 1기, 임시철탑 2기, 철탑철거 2기","2025-09-06 08:00","2025-10-14 18:00","2025-09-13 08:00","2025-10-14 18:00","연속"]
[151,"인천","시흥","남동동춘 T/L","남동S/S 혼용화공사","남동S/S 혼용화공사 관련 휴전","2025-09-17 09:00","2025-09-17 18:00","2025-09-08 09:00","2025-09-08 18:00","연속"]
[152,"인천","시흥","신시흥도림#1 T/L","도림SS  신시흥도림#1T/L GIS 보통점검","도림SS  신시흥도림#1T/L GIS 보통점검","2025-09-24 14:00","2025-09-24 18:00","취소","취소","연속"]
[153,"인천","시흥","도림오봉#1 T/L","도림SS  도림오봉#1T/L GIS 보통점검","도림SS  도림오봉#1T/L GIS 보통점검","2025-09-24 09:00","2025-09-24 14:00","취소","취소","연속"]
[154,"인천","시흥","북시화서시화#3 T/L","2025년 시흥전력지사 170kV GIS 정밀점검 공사","북시화, 서시화S/S  북시화-서시화#3T/L GIS 정밀점검 - 정밀점검 및 시험가압을 위한 휴전","2025-09-22 08:00","2025-09-27 18:00","2025-09-22 08:00","2025-09-27 18:00","연속"]
[155,"인천","시흥","동시화서시화 T/L","2025년 시흥전력지사 170kV GIS 정밀점검 공사","서시화S/S  동시화-서시화T/L GIS 정밀점검 - 정밀점검 및 시험가압을 위한 휴전","2025-09-29 08:00","2025-10-01 18:00","2025-09-29 08:00","2025-10-01 18:00","연속"]
[156,"인천","시흥","서서울#2소래 T/L","피뢰기 열화진단 및 EBA 가스채취","- 피뢰기 열화진단 : 목감#41C/T, 목감#45C/T - EBA 가스채취 : 소래C/T","2025-09-27 08:00","2025-09-28 18:00","2025-09-27 08:00","2025-09-28 18:00","연속"]
[157,"인천","시흥","온수소래 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기)","2025-09-20 07:00","2025-09-21 18:00","취소","취소","매일"]
[158,"인천","시흥","서안양소래 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기)","2025-09-20 07:00","2025-09-21 18:00","취소","취소","매일"]
[159,"인천","시흥","신시흥#2S/S #68 BUS","2025년 시흥전력지사 170kV GIS 정밀점검 공사","신시흥S/S  #63-#68(6400) BUS TIE GIS 정밀점검 시험가압 - 정밀점검 후 시험가압을 위한 휴전","2025-09-15 08:00","2025-09-17 13:00","2025-09-15 08:00","2025-09-17 13:00","연속"]
[160,"인천","시흥","신시흥#2S/S CB 6400","2025년 시흥전력지사 170kV GIS 정밀점검 공사","신시흥S/S  #63-#68(6400) BUS TIE GIS 정밀점검 - 정밀점검 및 시험가압을 위한 휴전","2025-09-15 08:00","2025-09-17 13:00","2025-09-15 08:00","2025-09-17 13:00","연속"]
[161,"인천","시흥","신시흥S/S #65 Sh.C CB","2025년 시흥전력지사 170kV GIS 정밀점검 공사","신시흥S/S  #65 Sh.C GIS 정밀점검 - 정밀점검 및 시험가압을 위한 휴전","2025-09-17 13:00","2025-09-19 18:00","2025-09-17 13:00","2025-09-19 18:00","연속"]
[162,"인천","시흥","신시흥#2S/S #63 BUS","2025년 시흥전력지사 170kV GIS 정밀점검 공사","신시흥S/S  #65 Sh.C GIS 정밀점검 시험가압 - 정밀점검 후 시험가압을 위한 휴전","2025-09-18 13:00","2025-09-19 13:00","2025-09-18 13:00","2025-09-19 13:00","연속"]
[163,"인천","시흥","학익연수#1 T/L","연수S/S  학익연수#1 T/L GIS 보통점검","연수S/S  학익연수#1 T/L GIS 보통점검","2025-09-26 09:00","2025-09-26 18:00","취소","취소","연속"]
[164,"인천","직할","고강S/S #60 BUS"," 고강S/S #4M.Tr 증설공사","고강S/S  GIS(#4M.Tr 1차) 설치 및 무부하가압","2025-09-27 09:00","2025-09-28 09:00","취소","취소","연속"]
[165,"인천","직할","고강화곡#1 T/L"," 고강S/S #4M.Tr 증설공사","고강S/S  GIS(#4M.Tr 1차) 설치 및 무부하가압","2025-09-20 09:00","2025-09-21 18:00","취소","취소","연속"]
[166,"인천","직할","고강S/S #65 BUS"," 고강S/S #4M.Tr 증설공사","고강S/S  GIS(#4M.Tr 1차) 설치 및 무부하가압","2025-09-21 09:00","2025-09-21 18:00","취소","취소","연속"]
[167,"인천","직할","고강S/S #60 BUS"," 고강S/S #4M.Tr 증설공사","고강S/S  GIS(#4M.Tr 1차) 설치 및 무부하가압","2025-09-20 09:00","2025-09-21 09:00","취소","취소","연속"]
[168,"인천","직할","고강화곡#1 T/L"," 고강S/S #4M.Tr 증설공사","고강S/S  GIS(#4M.Tr 1차) 설치 및 무부하가압","2025-09-27 09:00","2025-09-28 18:00","취소","취소","연속"]
[169,"인천","직할","고강S/S #65 BUS"," 고강S/S #4M.Tr 증설공사","고강S/S  GIS(#4M.Tr 1차) 설치 및 무부하가압","2025-09-28 09:00","2025-09-28 18:00","취소","취소","연속"]
[170,"인천","직할","도당S/S #65 BUS","도당S/S  신규수용 SW 증설공사(GS파워)","#60BUS #1,2T/L 2DS부 설치","2025-09-11 09:00","2025-09-18 18:00","2025-09-11 09:00","2025-09-18 18:00","연속"]
[171,"인천","직할","부천도당#1 T/L","도당S/S  신규수용 SW증설공사(GS파워)","#60BUS #1,2T/L 1DS부 무부하 가압","2025-09-09 09:00","2025-09-10 18:00","2025-09-09 09:00","2025-09-10 18:00","연속"]
[172,"인천","직할","도당S/S #60 BUS","도당S/S  신규수용 SW 증설공사(GS파워)","#60BUS #1,2T/L 1DS부 설치","2025-09-08 09:00","2025-09-10 18:00","2025-09-08 09:00","2025-09-10 18:00","연속"]
[173,"인천","직할","부천도당#2 T/L","도당S/S  신규수용 SW증설공사(GS파워)","#66BUS #3T/L 2DS부 무부하 가압","2025-09-25 17:00","2025-09-26 17:00","2025-09-25 17:00","2025-09-26 17:00","연속"]
[174,"인천","직할","도당S/S #66 BUS","도당S/S  신규수용 SW 증설공사(GS파워)","#66BUS #3T/L 2DS부 설치","2025-09-21 09:00","2025-09-26 17:00","2025-09-21 09:00","2025-09-26 17:00","연속"]
[175,"인천","직할","도당S/S #66 BUS","도당S/S  신규수용 SW증설공사(GS파워)","#61BUS #3T/L 1DS부 무부하 가압","2025-09-19 17:00","2025-09-20 17:00","2025-09-19 17:00","2025-09-20 17:00","연속"]
[176,"인천","직할","도당S/S #61 BUS","도당S/S  신규수용 SW 증설공사(GS파워)","#61BUS #3T/L 1DS부 설치","2025-09-18 10:00","2025-09-20 17:00","2025-09-18 10:00","2025-09-20 17:00","연속"]
[177,"인천","직할","부천도당#1 T/L","도당S/S  신규수용 SW증설공사(GS파워)","#65BUS #1,2T/L 2DS부 무부하 가압","2025-09-17 10:00","2025-09-18 10:00","2025-09-17 10:00","2025-09-18 10:00","연속"]
[178,"인천","직할","신부평임학#2 T/L","임학S/S 신부평임학#2T/L GIS 조작시험","임학S/S 신부평임학#2T/L GIS 조작시험","2025-09-12 14:00","2025-09-12 18:00","2025-09-12 14:00","2025-09-12 18:00","연속"]
[179,"인천","직할","신부평임학#1 T/L","임학S/S 신부평임학#1T/L GIS 조작시험","임학S/S 신부평임학#1T/L GIS 조작시험","2025-09-12 09:00","2025-09-12 14:00","2025-09-12 09:00","2025-09-12 14:00","연속"]
[180,"경기북부","고양","백학남면#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 백학남면T/L 피뢰기 설치","2025-09-22 10:00","2025-09-26 18:00","2025-09-22 10:00","2025-09-26 18:00","연속"]
[181,"경기북부","구리","가평춘천HP T/L"," 운천-철원 등 2개T/L 용량증대 전력선 교체공사","※ 11차 장기송변전설비계획(용량증대 전력선 교체)  가평-춘천HPT/L No.70~135.99","2025-09-01 06:00","2025-10-02 18:00","2025-09-01 06:00","2025-10-02 18:00","연속"]
[182,"경기북부","구리","가평청평HP#2 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","가평-청평HP#2(수직설치:36기,수평:36기) : No.1,8~32,34-1,43","2025-09-22 07:00","2025-09-26 18:00","2025-09-22 07:00","2025-09-26 18:00","연속"]
[183,"경기북부","구리","미금구리#3 T/L","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 초기점검","2025-09-24 14:00","2025-09-24 18:00","2025-09-24 14:00","2025-09-24 18:00","연속"]
[184,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신설철탑 조립 관련 중장비 이격거리 필요","2025-09-08 07:00","2025-09-12 18:00","2025-09-08 07:00","2025-09-12 18:00","연속"]
[185,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개T/L 지장송전선로 이설공사"," 신장-덕소 등 2개T/L 지장송전선로 이설공사 동서울서종#1T/L 가선공사 및 OPGW 이설","2025-09-22 07:00","2025-10-02 18:00","2025-09-22 07:00","2025-10-02 18:00","연속"]
[186,"경기북부","구리","덕소팔당HP청평HP T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","덕소-팔당HP-청평HP(수직설치:2기,수평:2기) : No.46,68","2025-09-29 07:00","2025-09-29 18:00","2025-09-29 07:00","2025-09-29 18:00","연속"]
[187,"경기북부","구리","미금S/S SEC CB 65660","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-09-26 14:00","2025-09-26 18:00","2025-09-26 14:00","2025-09-26 18:00","연속"]
[188,"경기북부","구리","미금S/S SEC CB 66670","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 보통점검","2025-09-25 14:00","2025-09-25 18:00","2025-09-25 14:00","2025-09-25 18:00","연속"]
[189,"경기북부","구리","미금S/S SEC CB 60610","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-09-26 09:00","2025-09-26 14:00","2025-09-26 09:00","2025-09-26 14:00","연속"]
[190,"경기북부","구리","미금S/S SEC CB 61620","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 보통점검","2025-09-25 09:00","2025-09-25 14:00","2025-09-25 09:00","2025-09-25 14:00","연속"]
[191,"경기북부","구리","동서울서종#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신설철탑 조립 관련 중장비 이격거리 필요","2025-09-08 07:00","2025-09-12 18:00","2025-09-08 07:00","2025-09-12 18:00","연속"]
[192,"경기북부","구리","동서울서종#1 T/L"," 신장-덕소 등 2개T/L 지장송전선로 이설공사"," 신장-덕소 등 2개T/L 지장송전선로 이설공사 동서울서종#1T/L 및 OPGW 이설","2025-09-22 07:00","2025-10-02 18:00","2025-09-22 07:00","2025-10-02 18:00","연속"]
[193,"경기북부","구리","신포천덕계#2 T/L","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 보통점검","2025-09-19 09:00","2025-09-19 18:00","2025-09-19 09:00","2025-09-19 18:00","연속"]
[194,"경기북부","구리","신포천덕계#1 T/L","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 보통점검","2025-09-18 09:00","2025-09-18 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[195,"경기북부","구리","신포천전곡#2 T/L","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 보통점검","2025-09-17 09:00","2025-09-17 18:00","2025-09-17 09:00","2025-09-17 18:00","연속"]
[196,"경기북부","구리","신포천전곡#1 T/L","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 보통점검","2025-09-16 09:00","2025-09-16 18:00","2025-09-16 09:00","2025-09-16 18:00","연속"]
[197,"경기북부","구리","신포천동두천#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-09-15 09:00","2025-09-15 18:00","2025-09-15 09:00","2025-09-15 18:00","연속"]
[198,"경기북부","구리","신포천백학#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신덕은-동두천CC#1 T/L No.18~19 (子 :  신포천-백학#2 T/L No.7~8)","2025-09-12 12:00","2025-09-12 18:00","2025-09-12 12:00","2025-09-12 18:00","연속"]
[199,"경기북부","구리","신포천백학#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신덕은-동두천CC#2 T/L No.18~19,32~50 (子 :  신포천-백학#1 T/L No.7~8,21~39)","2025-09-22 07:00","2025-09-24 12:00","2025-09-22 07:00","2025-09-24 12:00","연속"]
[200,"경기북부","구리","신포천S/S SEC CB 65660","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 보통점검","2025-09-22 09:00","2025-09-22 18:00","2025-09-22 09:00","2025-09-22 18:00","연속"]
[201,"경기북부","구리","운천전곡#1 T/L","2025년 가공송전 순시점검 위탁공사","정밀점검 작업구간 :  운천-전곡#1 T/L 59~70호","2025-09-29 07:00","2025-09-30 18:00","2025-09-29 07:00","2025-09-30 18:00","연속"]
[202,"경기북부","구리","진건별내#2 T/L","구리갈매역세권 공공주택지구 지장송전선로 이설공사"," 진건-별내T/L M/H#3~M/H#5 구간 이설","2025-09-15 09:00","2025-10-29 18:00","2025-09-15 09:00","2025-10-29 18:00","연속"]
[203,"경기북부","구리","덕소팔당HP T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","덕소-팔당HP(수직설치:35기,수평:39기) : No.1~34,65~68","2025-09-15 07:00","2025-09-19 18:00","2025-09-15 07:00","2025-09-19 18:00","연속"]
[204,"경기북부","직할","양주녹양#2 T/L","녹양S/S 호이스트 교체관련 구조보강","녹양S/S 호이스트 교체관련 구조보강","2025-09-15 09:00","2025-09-21 18:00","2025-09-15 09:00","2025-09-21 18:00","연속"]
[205,"경기북부","직할","녹양백석#2 T/L","녹양S/S 호이스트 교체관련 구조보강","녹양S/S 호이스트 교체관련 구조보강","2025-09-29 09:00","2025-10-05 18:00","2025-09-29 09:00","2025-10-05 18:00","연속"]
[206,"경기북부","직할","녹양백석#1 T/L","녹양S/S 호이스트 교체관련 구조보강","녹양S/S 호이스트 교체관련 구조보강","2025-09-22 09:00","2025-09-28 18:00","2025-09-22 09:00","2025-09-28 18:00","연속"]
[207,"경기북부","직할","양주녹양#1 T/L","녹양S/S 호이스트 교체관련 구조보강","녹양S/S 호이스트 교체관련 구조보강","2025-09-08 09:00","2025-09-14 18:00","2025-09-08 09:00","2025-09-14 18:00","연속"]
[208,"경기북부","직할","신의정부내촌#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신가평-신의정부#1 T/L No.120~134,136,138 (子 :  신의정부-내촌#1 T/L No.23~9,7,5)","2025-09-08 07:00","2025-09-10 18:00","2025-09-08 07:00","2025-09-10 18:00","연속"]
[209,"경기북부","직할","신의정부S/S SEC CB 61620","2025년 경기북부 직할 170kV GIS 점검공사","170kV GIS 보통점검","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[210,"경기북부","직할","신의정부S/S SEC CB 66670","2025년 경기북부 직할 170kV GIS 점검공사","170kV GIS 보통점검","2025-09-22 09:00","2025-09-22 18:00","2025-09-22 09:00","2025-09-22 18:00","연속"]
[211,"경기북부","직할","신의정부S/S SEC CB 65660","2025년 경기북부 직할 170kV GIS 점검공사","170kV GIS 보통점검","2025-09-25 09:00","2025-09-25 18:00","2025-09-25 09:00","2025-09-25 18:00","연속"]
[212,"경기북부","직할","용현장암#2 T/L","2025년 가공송전 순시점검 위탁공사","초기점검 -  용현-장암 #2T/L No.36호","2025-09-25 13:00","2025-09-25 18:00","2025-09-25 13:00","2025-09-25 18:00","연속"]
[213,"경기북부","직할","용현장암#1 T/L","2025년 가공송전 순시점검 위탁공사","초기점검 -  용현-장암 #1T/L No.36호","2025-09-25 07:00","2025-09-25 13:00","2025-09-25 07:00","2025-09-25 13:00","연속"]
[214,"경기","군포","화성남양#1 T/L","남양S/S  화성-남양#1T/L 627 GIS 보통점검","남양S/S  화성-남양#1T/L 627 GIS 보통점검","2025-09-03 09:00","2025-09-03 18:00","2025-09-03 09:00","2025-09-03 18:00","연속"]
[215,"경기","군포","화성남양#2 T/L","남양S/S  화성-남양#2T/L 647 GIS 보통점검","남양S/S  화성-남양#2T/L 647 GIS 보통점검","2025-09-04 09:00","2025-09-04 18:00","2025-09-04 09:00","2025-09-04 18:00","연속"]
[216,"경기","군포","사강남양#1 T/L","사강S/S  남양-사강#1T/L GIS 인출 접지개폐기 취부","사강S/S  남양-사강#1T/L GIS 인출 접지개폐기 취부","2025-09-27 09:00","2025-09-27 18:00","2025-09-27 09:00","2025-09-27 18:00","연속"]
[217,"경기","군포","산본안양#1 T/L"," 산본-안양T/L 지장수목 벌채작업"," 산본-안양T/L 지장수목 벌채작업 (1~3호)","2025-09-15 08:00","2025-09-16 17:00","2025-09-15 08:00","2025-09-16 17:00","연속"]
[218,"경기","군포","서서울#2S/S #63 BUS","[정밀무부하]서서울2S/S #63-#64 SEC GIS 정밀점검","서서울2S/S  #63-#64 SEC GIS 정밀점검 무부하가압용","2025-09-30 16:00","2025-09-30 18:00","2025-09-30 16:00","2025-09-30 18:00","연속"]
[219,"경기","군포","서서울#2S/S #68 BUS","[정밀무부하]서서울2S/S #6500 BUS TIE GIS 정밀점검","서서울2S/S  #63-#68(6500) BUS-TIE GIS 정밀점검 전 #68BUS 휴전 및 무부하가압용","2025-09-22 09:00","2025-09-23 18:00","2025-09-22 09:00","2025-09-23 18:00","연속"]
[220,"경기","군포","서서울#2S/S CB 6500","[정밀]서서울2S/S #6500 BUS TIE GIS 정밀점검","서서울2S/S  #63-#68(6500) BUS-TIE GIS 정밀점검 시행","2025-09-22 09:00","2025-09-23 18:00","2025-09-22 09:00","2025-09-23 18:00","연속"]
[221,"경기","군포","서서울#2일동#1 T/L","[정밀무부하]서서울2S/S #6500 BUS TIE GIS 정밀점검","서서울2S/S  #63-#68(6500) BUS-TIE GIS 정밀점검 무부하가압용","2025-09-23 16:00","2025-09-23 18:00","2025-09-23 16:00","2025-09-23 18:00","연속"]
[222,"경기","군포","서서울#2S/S #64 BUS","[정밀무부하]서서울2S/S #6600 BUS TIE GIS 정밀점검","서서울2S/S  #64-#69(6600) BUS-TIE GIS 정밀점검 전 #64BUS 휴전 및 무부하가압용","2025-09-24 09:00","2025-09-25 18:00","취소","취소","연속"]
[223,"경기","군포","서서울#2S/S CB 6600","[정밀]서서울2S/S #6600 BUS TIE GIS 정밀점검","서서울2S/S  #64-#69(6600) BUS-TIE GIS 정밀점검 시행","2025-09-24 09:00","2025-09-25 18:00","취소","취소","연속"]
[224,"경기","군포","서서울#2일동#1 T/L","[정밀무부하]서서울2S/S #6600 BUS TIE GIS 정밀점검","서서울2S/S  #64-#69(6600) BUS-TIE GIS 정밀점검 무부하가압용","2025-09-25 09:00","2025-09-25 18:00","취소","취소","연속"]
[225,"경기","군포","서서울#2일동#1 T/L","[정밀무부하]서서울2S/S #63-#64 SEC GIS 정밀점검","서서울2S/S  #63-#64 SEC GIS 정밀점검 무부하가압용","2025-09-30 16:00","2025-09-30 18:00","2025-09-30 16:00","2025-09-30 18:00","연속"]
[226,"경기","군포","서서울#2소래 T/L"," 서서울2-소래T/L 지장수목 벌채작업"," 서서울2-소래T/L 지장수목 벌채작업 (1~2호)","2025-09-15 08:00","2025-09-19 17:00","취소","취소","연속"]
[227,"경기","군포","서서울#2S/S SEC CB 63640","[정밀]서서울2S/S #63-#64 SEC GIS 정밀점검","서서울2S/S  #63-#64 SEC GIS 정밀점검 시행","2025-09-29 09:00","2025-09-30 18:00","2025-09-29 09:00","2025-09-30 18:00","연속"]
[228,"경기","군포","서서울#2봉담#2 T/L"," 서서울2-봉담T/L 지장수목 벌채작업"," 서서울2-봉담T/L 지장수목 벌채작업 (14호)","2025-09-26 08:00","2025-09-26 17:00","2025-09-27 08:00","2025-09-27 17:00","연속"]
[229,"경기","군포","서서울#2S/S #63 BUS","[정밀무부하]서서울2S/S #6600 BUS TIE GIS 정밀점검","서서울2S/S  #64-#69(6600) BUS-TIE GIS 정밀점검 무부하가압용","2025-09-25 16:00","2025-09-25 18:00","2025-09-25 16:00","2025-09-25 18:00","연속"]
[230,"경기","군포","성포안산#1 T/L","[정밀] 안산S/S 성포-안산#1T/L GIS 정밀점검","안산S/S  성포-안산#1T/L GIS 정밀점검 시행","2025-09-29 09:00","2025-09-30 18:00","2025-09-29 09:00","2025-09-30 18:00","연속"]
[231,"경기","동부","감곡가남#1 T/L"," 이천-가남 등 2개T/L 용량증대 선종교체공사"," 감곡-가남T/L No.25~가남S/S 18.2km, 선종교체 ACSR240㎟→ASCC310㎟","2025-09-08 07:00","2025-10-02 18:00","2025-09-08 07:00","2025-10-02 18:00","연속"]
[232,"경기","동부","곤지암S/S SEC CB 60610","곤지암S/S #61-66 모선보호반 대체작업","곤지암S/S 61-66 모선보호반 대체작업","2025-09-01 09:00","2025-09-05 18:00","취소","취소","연속"]
[233,"경기","동부","곤지암S/S SEC CB 65660","곤지암S/S #61-66 모선보호반 대체작업","곤지암S/S 61-66 모선보호반 대체작업","2025-09-01 09:00","2025-09-05 18:00","취소","취소","연속"]
[234,"경기","동부","곤지암S/S SEC CB 61620","곤지암S/S #61-66 모선보호반 대체작업","곤지암S/S 61-66 모선보호반 대체작업","2025-09-01 09:00","2025-09-05 18:00","취소","취소","연속"]
[235,"경기","동부","곤지암S/S CB 6200","곤지암S/S #61-66 모선보호반 대체작업","곤지암S/S 61-66 모선보호반 대체작업","2025-09-01 09:00","2025-09-05 18:00","취소","취소","연속"]
[236,"경기","동부","곤지암S/S SEC CB 66670","곤지암S/S #61-66 모선보호반 대체작업","곤지암S/S 61-66 모선보호반 대체작업","2025-09-01 09:00","2025-09-05 18:00","취소","취소","연속"]
[237,"경기","동부","분당S/S SEC CB 60610","분당S/S 170kV G/T#1, 60-61 GIS 조작시험","분당S/S 170kV G/T#1T/L, 60-61 SEC GIS 조작시험 [G/T#1 O/H:09.16~09.23]","2025-09-18 09:00","2025-09-18 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[238,"경기","동부","성현S/S CB 6100","성현S/S 170kV GIS 6100조작시험 외","성현:6100(조작),성현:초월-성현#2T/L(조작) 초월:초월-성현#2T/L(보통) *LA(보통)","2025-09-29 14:00","2025-09-29 18:00","2025-09-29 14:00","2025-09-29 18:00","연속"]
[239,"경기","동부","동판교야탑 T/L","야탑S/S 170kV GIS 동판교-야탑T/L 보통점검","야탑:동판교-야탑T/L(보통)","2025-09-03 09:00","2025-09-03 18:00","취소","취소","연속"]
[240,"경기","동부","왕암여주#2 T/L","여주S/S 170kV GIS 왕암-여주#1,2T/L 효성제 발청 점검","여주S/S 170kV GIS 왕암-여주#1,2T/L 효성제 발청 점검","2025-09-03 14:00","2025-09-03 18:00","2025-09-03 14:00","2025-09-03 18:00","연속"]
[241,"경기","동부","왕암여주#1 T/L","여주S/S 170kV GIS 왕암-여주#1,2T/L 효성제 발청 점검","여주S/S 170kV GIS 왕암-여주#1,2T/L 효성제 발청 점검","2025-09-03 09:00","2025-09-03 14:00","2025-09-03 09:00","2025-09-03 14:00","연속"]
[242,"경기","동부","오포모현#1 T/L","오포S/S 170kV GIS 오포-모현#1/L 보통점검","오포:오포-모현#1T/L(보통)","2025-09-02 09:00","2025-09-02 18:00","2025-09-02 09:00","2025-09-02 18:00","연속"]
[243,"경기","동부","초월성현#2 T/L","초월S/S 170kV GIS 초월-성현#2T/L 보통점검 외","초월:초월-성현#2T/L(보통) *LA(보통) 성현:초월-성현#2T/L(조작) 성현:6100(조작)","2025-09-29 09:00","2025-09-29 18:00","2025-09-29 09:00","2025-09-29 18:00","연속"]
[244,"경기","성남","서안성남사#2 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","GIS 보통점검","2025-09-01 14:00","2025-09-01 18:00","취소","취소","연속"]
[245,"경기","성남","남사동탄#1 T/L"," 중동탄분기 지중T/L 건설공사","공사구간 : 남사-동탄 #1TL (M/H#6 ~ M/H#7 2π 분기) / 긍장 :  XLPE 2,500㎜ 4C×1.55㎞, XLPE 2,000㎜ 4C(D)×0.5㎞ / 포설 (3상 1구간 기준) : 20 구간 / 접속 (3상 1개소 기준) : 20개소 (EB-G 4개소, PMIJ 16개소)","2025-09-15 09:00","2025-11-20 18:00","2025-09-15 09:00","2025-11-20 18:00","연속"]
[246,"경기","성남","덕성남사#2 T/L","2025년 성남전력 변전협력회사 총액공사","gis 보통점검","2025-09-05 14:00","2025-09-05 18:00","2025-09-05 14:00","2025-09-05 18:00","연속"]
[247,"경기","성남","덕성남사#1 T/L","2025년 성남전력 변전협력회사 총액공사","gis 보통점검","2025-09-05 09:00","2025-09-05 14:00","2025-09-05 09:00","2025-09-05 14:00","연속"]
[248,"경기","성남","서안성남사#1 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","GIS 보통점검","2025-09-01 09:00","2025-09-01 14:00","취소","취소","연속"]
[249,"경기","성남","삼미동탄2열병합#1 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","삼미,동탄열 gis 보통점검","2025-09-18 09:00","2025-09-19 18:00","2025-09-18 09:00","2025-09-19 18:00","연속"]
[250,"경기","성남","삼미동탄2열병합#2 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","삼미, 동탄열 gis 보통점검","2025-09-22 09:00","2025-09-23 14:00","2025-09-22 09:00","2025-09-23 14:00","연속"]
[251,"경기","성남","삼미동탄2열병합#3 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","삼미, 동탄열 gis 보통점검","2025-09-23 14:00","2025-09-24 18:00","2025-09-23 14:00","2025-09-24 18:00","연속"]
[252,"경기","성남","신성남서판교#1 T/L","2025년 성남전력 변전협력회사 총액공사","gis 조작시험 신성남,서판교 보호반대체","2025-09-16 09:00","2025-09-18 18:00","2025-09-16 09:00","2025-09-18 18:00","연속"]
[253,"경기","성남","신성남서판교#2 T/L","2025년 성남전력 변전협력회사 총액공사","신성남, 서판교 보호반대체","2025-09-23 09:00","2025-09-25 18:00","2025-09-23 09:00","2025-09-25 18:00","연속"]
[254,"경기","성남","신수원S/S CB 6300","2025년 성남전력 변전협력회사 총액공사","gis 조작시험","2025-09-17 14:00","2025-09-17 18:00","취소","취소","연속"]
[255,"경기","성남","신수원S/S CB 6100","2025년 성남전력 변전협력회사 총액공사","gis 보통점검","2025-09-17 09:00","2025-09-17 14:00","취소","취소","연속"]
[256,"경기","성남","신용인S/S #65 BUS","2025년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검","2025-09-18 09:00","2025-09-18 18:00","취소","취소","연속"]
[257,"경기","성남","신용인S/S SEC CB 65660","2025년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검","2025-09-17 09:00","2025-09-18 18:00","취소","취소","연속"]
[258,"경기","성남","신용인기흥#2 T/L","2025년 성남전력 변전협력회사 총액공사","gis 보통점검 667 LA 보통점검","2025-09-25 14:00","2025-09-25 18:00","2025-09-25 14:00","2025-09-25 18:00","연속"]
[259,"경기","성남","신용인기흥#1 T/L","2025년 성남전력 변전협력회사 총액공사","gis 보통점검 657 LA 보통점검","2025-09-25 09:00","2025-09-25 14:00","2025-09-25 09:00","2025-09-25 14:00","연속"]
[260,"경기","성남","신용인용인#1 T/L","2025년 성남전력 변전협력회사 총액공사","gis 조작시험 cvt 대체","2025-09-08 09:00","2025-09-08 18:00","2025-09-08 09:00","2025-09-08 18:00","연속"]
[261,"경기","성남","신용인S/S #60 BUS","2025년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검 무부하가압용","2025-09-16 09:00","2025-09-16 18:00","취소","취소","연속"]
[262,"경기","성남","신용인S/S SEC CB 60610","2025년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검","2025-09-15 09:00","2025-09-16 18:00","취소","취소","연속"]
[263,"경기","성남","신용인동백#2 T/L","2025년 성남전력 변전협력회사 총액공사","gis 조작시험","2025-09-11 14:00","2025-09-11 18:00","2025-09-11 14:00","2025-09-11 18:00","연속"]
[264,"경기","성남","신용인동백#1 T/L","2025년 성남전력 변전협력회사 총액공사","gis 조작시험","2025-09-11 09:00","2025-09-11 14:00","2025-09-11 09:00","2025-09-11 14:00","연속"]
[265,"경기","성남","신용인용인#2 T/L","피뢰기 설치공사","24-25년 경기직할 송전협력회사 공사(피뢰기 설치공사)","2025-09-12 07:00","2025-09-12 18:00","2025-09-13 07:00","2025-09-13 18:00","연속"]
[266,"경기","성남","용인덕성#2 T/L","피뢰기 설치공사 및 소도체 이도조정","24-25년 경기직할 송전협력회사 공사[피뢰기 설치공사(4회선 안전거리) 및 소도체 이도조정]","2025-09-12 07:00","2025-09-12 18:00","2025-09-13 07:00","2025-09-13 18:00","연속"]
[267,"경기","성남","용인덕성#1 T/L","2025년 성남전력 변전협력회사 총액공사","cvt 대체","2025-09-11 09:00","2025-09-11 18:00","2025-09-12 09:00","2025-09-12 18:00","연속"]
[268,"경기","성남","신성남정자#1 T/L","현대제 170kV GIS 제작사 점검","제작사) GIS 유압밸브시트 교체","2025-09-13 09:00","2025-09-13 18:00","2025-09-13 09:00","2025-09-13 18:00","연속"]
[269,"경기","직할","과천동안양#2 T/L","24-25년 군포전력지사 가공송전협력회사 공사","의왕-동안양#1T/L 병가구간 안전이격거리 확보","2025-09-05 07:00","2025-09-05 17:00","2025-09-05 07:00","2025-09-05 17:00","연속"]
[270,"경기","직할","발안구문천#2 T/L","발안S/S 발안-구문천#2T/L 보통점검","발안 : 발안-구문천#2T/L 보통점검","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[271,"경기","직할","서서울#2봉담#1 T/L","봉담S/S 서서울2-봉담#1T/L 보통점검","봉담 : 서서울2-봉담#1T/L 보통점검","2025-09-19 09:00","2025-09-19 18:00","2025-09-20 09:00","2025-09-20 18:00","연속"]
[272,"경기","직할","서수원율전#2 T/L","율전S/S 서수원-율전#2T/L 보통점검","율전 : 서수원-율전#2T/L 보통점검","2025-09-30 09:00","2025-09-30 18:00","2025-09-30 09:00","2025-09-30 18:00","연속"]
[273,"경기","직할","율전의왕#2 T/L","24-25년 군포전력지사 가공송전협력회사 공사","율전-의왕#2T/L 송전선로용 피뢰기 설치 (39SET)","2025-09-01 07:00","2025-09-03 17:00","2025-09-01 07:00","2025-09-03 17:00","연속"]
[274,"경기","직할","율전의왕#1 T/L"," 율전-의왕#1 T/L 지장수목 벌채작업"," 율전-의왕#1 T/L 지장수목 벌채작업","2025-09-18 08:00","2025-09-19 17:00","2025-09-18 08:00","2025-09-19 17:00","연속"]
[275,"경기","직할","의왕동안양#2 T/L"," 의왕-동안양#2 T/L 지장수목 벌채작업"," 의왕-동안양#2 T/L 지장수목 벌채작업 17~39호","2025-09-08 08:00","2025-09-12 17:00","취소","취소","연속"]
[276,"경기","직할","의왕동안양#1 T/L","24-25년 군포전력지사 가공송전협력회사 공사","의왕-동안양#1T/L 송전선로용 피뢰기 설치 (123SET)","2025-09-01 07:00","2025-09-05 17:00","취소","취소","연속"]
[277,"경기","직할","안양평촌#1 T/L","평촌S/S 안양-평촌#1T/L 보통점검","평촌 : 안양-평촌#1T/L 보통점검","2025-09-29 09:00","2025-09-29 14:00","2025-09-29 09:00","2025-09-29 14:00","연속"]
[278,"경기","직할","안양평촌#2 T/L","평촌S/S 안양-평촌#2T/L 조작시험","평촌 : 안양-평촌#2T/L 조작시험","2025-09-29 14:00","2025-09-29 18:00","2025-09-29 14:00","2025-09-29 18:00","연속"]
[279,"경기","직할","화성수촌#1 T/L"," 화성-수촌T/L 지장수목 벌채작업"," 화성-수촌T/L 지장수목 벌채작업 (14~15호)","2025-09-29 08:00","2025-09-29 17:00","2025-09-29 08:00","2025-09-29 17:00","연속"]
[280,"경기","직할","화성수촌#2 T/L"," 화성-수촌T/L 지장수목 벌채작업"," 화성-수촌T/L 지장수목 벌채작업 (14~15호)","2025-09-30 08:00","2025-09-30 17:00","2025-09-30 08:00","2025-09-30 17:00","연속"]
[281,"경기","평택","고덕#2삼성P4#2 T/L CB","고덕#2S/S #4M.Tr 증설공사","앵글측정","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[282,"경기","평택","고덕#2S/S #66 BUS","고덕#2S/S #4M.Tr 증설공사(#66BUS)"," 모선보호반 CT 케이블 이설 및  GIS 인터록시험","2025-09-08 09:00","2025-09-11 18:00","2025-09-08 09:00","2025-09-11 18:00","연속"]
[283,"경기","평택","고덕#2S/S #66 BUS","고덕#2S/S #4M.Tr 증설공사","앵글측정 및 #4M.Tr 관련 전설비 무부하가압","2025-09-23 14:00","2025-09-24 18:00","2025-09-23 14:00","2025-09-24 18:00","연속"]
[284,"경기","평택","고덕#2S/S #61 BUS","고덕#2S/S #4M.Tr 증설공사","앵글측정","2025-09-23 09:00","2025-09-23 14:00","2025-09-23 09:00","2025-09-23 14:00","연속"]
[285,"경기","평택","고덕진위#2 T/L","345kV 고덕2-서안성#2T/L 피뢰기 설치공사(병가선로 안전이격)","345kV 고덕2-서안성#2T/L 피뢰기 설치공사 4회선 병가구간 안전이격","2025-09-09 08:00","2025-09-09 18:00","2025-09-09 08:00","2025-09-09 18:00","연속"]
[286,"경기","평택","서안성S/S SEC CB 66670","2025년 평택전력 변전협력회사 총액공사(서안성 66-67)","서안성S/S  #66-#67 SEC GIS 보통점검","2025-09-18 09:00","2025-09-18 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[287,"경기","평택","서안성S/S SEC CB 61620","2025년 평택전력 변전협력회사 총액공사(서안성 61-62 SEC)","서안성S/S  #61-#62 SEC GIS GIS 보통점검","2025-09-05 09:00","2025-09-05 18:00","2025-09-05 09:00","2025-09-05 18:00","연속"]
[288,"경기","평택","송탄안성 T/L","2025년 평택전력 변전협력회사 총액공사(송탄안성)","보호반 대체 / GIS 보통점검 / LA 보통점검 / CVT 대체","2025-09-06 09:00","2025-09-08 18:00","2025-09-06 09:00","2025-09-08 18:00","연속"]
[289,"경기","평택","오산향남#2 T/L","2025년 평택전력 변전협력회사 총액공사(오산향남2)","오산S/S 오산향남#2T/L GIS 보통점검","2025-09-12 09:00","2025-09-12 18:00","취소","취소","연속"]
[290,"경기","평택","오산향남#1 T/L","2025년 평택전력 변전협력회사 총액공사(오산향남1)","오산S/S 오산향남#1T/L GIS 보통점검","2025-09-11 09:00","2025-09-11 18:00","취소","취소","연속"]
[291,"경기","평택","청북평택#1 T/L","2024-2025년 평택전력지사 송전정비 협릭회사"," 청북-평택 #1T/L No.14 ~ 21호 소도체 이도조정","2025-09-25 09:00","2025-09-26 18:00","2025-09-25 09:00","2025-09-26 18:00","연속"]
[292,"경기","평택","둔포추팔#2 T/L","2025년 GIS 보통 및 정밀점검공사(둔포-추팔#2)","추팔S/S  둔포-추팔#2T/L GIS 정밀점검","2025-09-18 09:00","2025-09-19 18:00","2025-09-18 09:00","2025-09-19 18:00","연속"]
[293,"경기","평택","둔포추팔#1 T/L","2025년 GIS 보통 및 정밀점검공사(둔포-추팔#1)","추팔S/S  둔포-추팔#1T/L GIS 정밀점검","2025-09-16 09:00","2025-09-17 18:00","2025-09-16 09:00","2025-09-17 18:00","연속"]
[294,"경기","평택","원정평택TP#1 T/L","2025년 평택전력 변전협력회사 총액공사(원정-평택 #1)","평택화력S/Y 원정-평택T/P #1T/L GIS 보통점검","2025-09-15 09:00","2025-09-15 18:00","2025-09-15 09:00","2025-09-15 18:00","연속"]
[295,"경기","평택","원정평택TP#2 T/L","2025년 평택전력 변전협력회사 총액공사(원정평택TP#2)","평택T/P 345kV #3TIE-Tr 6341 DS 누기보수 관련 인접설비 휴전 / GIS 보통점검","2025-09-06 09:00","2025-09-10 18:00","취소","취소","연속"]
[296,"경기","평택","평택T/P #61BUS","2025년 평택전력 변전협력회사 총액공사(#61BUS)","평택T/P 345kV #3TIE-Tr 6341 DS 누기보수 관련 인접설비 휴전 / GIS 보통점검 ","2025-09-06 09:00","2025-09-10 18:00","취소","취소","연속"]
[297,"강원","강릉","속초간성#2 T/L","2025년 강릉전력 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-09-29 09:00","2025-10-02 18:00","2025-09-29 09:00","2025-10-02 18:00","연속"]
[298,"강원","강릉","속초간성#1 T/L","2025년 강릉전력 170kV GIS 정밀점검","170kV GIS 정밀점검","2025-09-22 09:00","2025-09-25 18:00","2025-09-22 09:00","2025-09-25 18:00","연속"]
[299,"강원","강릉","신양양양양#1 T/L","2025년 강릉전력 변전협력 총액공사","170kV GIS, LA 보통점검","2025-09-12 10:00","2025-09-12 18:00","취소","취소","연속"]
[300,"강원","강릉","영동T/P CB 6100","2025년 강릉전력 변전협력 총액공사","170kV GIS 하자점검","2025-09-19 10:00","2025-09-19 18:00","2025-09-19 10:00","2025-09-19 18:00","연속"]
[301,"강원","강릉","신제천주진#1 T/L","2025년 강릉전력 변전협력 총액공사","송전선로 LA 대체","2025-09-26 10:00","2025-09-26 14:00","2025-09-26 10:00","2025-09-26 14:00","연속"]
[302,"강원","강릉","신제천주진#2 T/L","2025년 강릉전력 변전협력 총액공사","송전선로 LA 대체","2025-09-26 14:00","2025-09-26 18:00","2025-09-26 14:00","2025-09-26 18:00","연속"]
[303,"강원","강릉","주진평창#1 T/L","평창S/S 디지털화 공사","주진평창#1T/L 디지털화 결선 변경","2025-09-29 10:00","2025-09-29 18:00","취소","취소","연속"]
[304,"강원","강릉","주진평창#2 T/L","평창S/S 디지털화 공사","주진평창#2T/L 디지털화 결선 변경","2025-09-30 10:00","2025-09-30 18:00","취소","취소","연속"]
[305,"강원","동해","북평영동TP#1 T/L","2024~25년 동해전력지사 가공송전 협력회사 공사","SB댐퍼 교체","2025-09-22 07:00","2025-09-22 14:00","2025-09-22 07:00","2025-09-22 14:00","연속"]
[306,"강원","동해","이원S/S #2 BUS","2025년 동해전력지사 170kV GIS 정밀점검공사","#2Sh.C 무부하가압용","2025-09-17 09:00","2025-09-17 13:00","2025-09-17 09:00","2025-09-17 13:00","연속"]
[307,"강원","동해","동해이원#2 T/L","2025년 동해전력지사 170kV GIS 정밀점검공사","#2Sh.C 정밀점검 무부하가압용","2025-09-17 09:00","2025-09-17 13:00","2025-09-17 09:00","2025-09-17 13:00","연속"]
[308,"강원","동해","이원S/S #1 BUS","2025년 동해전력지사 170kV GIS 정밀점검공사","#1Sh.C 무부하가압용","2025-09-19 09:00","2025-09-19 18:00","2025-09-19 09:00","2025-09-19 18:00","연속"]
[309,"강원","동해","동해이원#1 T/L","2025년 동해전력지사 170kV GIS 정밀점검공사","#1Sh.C 정밀점검 무부하가압용","2025-09-19 09:00","2025-09-19 18:00","2025-09-19 09:00","2025-09-19 18:00","연속"]
[310,"강원","동해","이원태백 T/L","2025년 동해전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-09-22 09:00","2025-09-24 13:00","2025-09-22 09:00","2025-09-24 13:00","연속"]
[311,"강원","동해","동해이원#1 T/L","2025년 동해전력지사 가공송전순시점검 위탁공사","불량애자교체","2025-09-22 10:00","2025-09-22 15:00","2025-09-22 10:00","2025-09-22 15:00","연속"]
[312,"강원","동해","이원도계 T/L","2025년 동해전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-09-24 13:00","2025-09-26 18:00","2025-09-24 13:00","2025-09-26 18:00","연속"]
[313,"강원","원주","남원주원주#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","수평레일설치 및 항공번호찰 교체","2025-09-22 07:30","2025-09-22 18:00","2025-09-22 07:30","2025-09-22 18:00","연속"]
[314,"강원","원주","신제천남원주#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","수평레일 및 항공번호찰 교체","2025-09-23 07:30","2025-09-23 18:00","2025-09-23 07:30","2025-09-23 18:00","연속"]
[315,"강원","원주","신제천남원주#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","수평레일 및 항공번호찰 교체","2025-09-22 07:30","2025-09-22 18:00","2025-09-22 07:30","2025-09-22 18:00","연속"]
[316,"강원","원주","남원주원주#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","수평레일설치","2025-09-23 07:30","2025-09-23 18:00","2025-09-23 07:30","2025-09-23 18:00","연속"]
[317,"강원","원주","서원주문막#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","수직수평추락방지장치 설치","2025-09-26 07:30","2025-10-01 18:00","2025-09-26 07:30","2025-10-01 18:00","매일"]
[318,"강원","원주","홍천소양강HP T/L"," 소양T/L No.76, 77 안전이격 확보공사(협력회사공사)","- No.76, 77  2C 철탑 2기 교체(인클로징) - No.74~79, ASCC/TW 430㎟×S, 3.681C-㎞ 전선교체","2025-09-26 09:00","2025-10-02 18:00","취소","취소","연속"]
[319,"강원","원주","홍천소양강HP T/L"," 소양T/L No.76, 77 안전이격 확보공사(협력회사공사)","- No.76, 77  2C 철탑 2기 교체(인클로징) - No.74~79, ASCC/TW 430㎟×S, 3.681C-㎞ 전선교체","2025-09-15 09:00","2025-09-15 14:00","취소","취소","연속"]
[320,"강원","직할","홍천남춘천 T/L"," 소양T/L No.76, 77 안전이격 확보공사(협력회사공사)","- No.76, 77  2C 철탑 2기 교체(인클로징) - No.74~79, ASCC/TW 430㎟×S, 3.681C-㎞ 전선교체","2025-09-15 14:01","2025-09-25 18:00","취소","취소","연속"]
[321,"강원","직할","인제양구#2 T/L"," 상제 등 3개 T/L 추락방지장치 설치공사"," 상제 T/L 추락방지장치 설치공사","2025-09-22 07:00","2025-10-02 18:00","2025-09-22 07:00","2025-10-02 18:00","매일"]
[322,"강원","직할","상남인제#2 T/L"," 상제 등 3개 T/L 추락방지장치 설치공사"," 상제 T/L 추락방지장치 설치공사","2025-09-22 07:00","2025-09-22 18:00","2025-09-22 07:00","2025-09-22 18:00","연속"]
[323,"강원","태백","태백고한 T/L","2024-2025 태백전력지사 변전협력회사 공사","고한S/S  태백-고한T/L LA A상 피뢰기누설카운터 교체","2025-09-29 09:00","2025-09-29 18:00","2025-09-29 09:00","2025-09-29 18:00","연속"]
[324,"강원","태백","단양영월CC#2 T/L","2024-2025 태백전력지사 변전협력회사 공사","영월C/C  단양영월CC #2TL GIS 보통점검","2025-09-15 09:00","2025-09-15 18:00","2025-09-15 09:00","2025-09-15 18:00","연속"]
[325,"강원","태백","영월에코윈드S/S 영월에코윈드발전소 #1M.Tr 1차 CB","2024-2025 태백전력지사 변전협력회사 공사","영월에코윈드S/Y  영월에코윈드 #1 M.Tr GIS","2025-09-11 09:00","2025-09-11 18:00","2025-09-11 09:00","2025-09-11 18:00","연속"]
[326,"강원","태백","도계태백 T/L","2024-2025 태백전력지사 변전협력회사 공사","태백S/S  GIS 보통점검","2025-09-30 09:00","2025-09-30 18:00","2025-09-30 09:00","2025-09-30 18:00","연속"]
[327,"충북","직할","서운광혜원 T/L","24~25 충북 직할 가공송전 협력회사 총액공사","전선교체공사","2025-09-22 07:00","2025-09-28 18:00","2025-09-22 07:00","2025-09-28 18:00","연속"]
[328,"충북","직할","진천광혜원#1 T/L","24~25 충북 직할 가공송전 협력회사 총액공사","전선교체공사","2025-09-22 07:00","2025-09-28 18:00","2025-09-22 07:00","2025-09-28 18:00","연속"]
[329,"충북","직할","진천덕산#1 T/L","25년 충북직할  GIS 정밀점검공사","덕산변전소  진천-덕산#1T/L GIS 정밀점검","2025-09-29 08:00","2025-09-30 18:00","2025-09-29 08:00","2025-09-30 18:00","연속"]
[330,"충북","직할","문백S/S #65 BUS","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-09-02 10:00","2025-09-02 13:00","2025-09-02 10:00","2025-09-02 13:00","연속"]
[331,"충북","직할","문백S/S #66 BUS","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-09-03 13:00","2025-09-04 10:00","2025-09-03 13:00","2025-09-04 10:00","연속"]
[332,"충북","직할","문백오창#2 T/L","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-09-03 10:00","2025-09-04 10:00","2025-09-03 10:00","2025-09-04 10:00","연속"]
[333,"충북","직할","문백S/S #61 BUS","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-09-03 10:00","2025-09-03 13:00","2025-09-03 10:00","2025-09-03 13:00","연속"]
[334,"충북","직할","문백S/S #60 BUS","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-09-02 13:00","2025-09-03 10:00","2025-09-02 13:00","2025-09-03 10:00","연속"]
[335,"충북","직할","문백오창#1 T/L","345kV 신청주S/S 건설사업","신청주-문백T/L GIS 증설","2025-09-02 10:00","2025-09-03 10:00","2025-09-02 10:00","2025-09-03 10:00","연속"]
[336,"충북","직할","신진천S/S #67 BUS","25년 충북본부 직할 GIS 정밀점검 공사","신진천S/S  #6Sh.C GIS 정밀점검 후 무부하가압용","2025-09-27 17:00","2025-09-27 18:00","2025-09-24 17:00","2025-09-24 18:00","연속"]
[337,"충북","직할","신진천S/S #67 BUS","25년 충북본부 직할 GIS 정밀점검 공사","신진천S/S  #3Sh.C GIS 정밀점검 후 무부하가압용","2025-09-24 17:00","2025-09-24 18:00","2025-09-24 17:00","2025-09-24 18:00","연속"]
[338,"충북","직할","신진천S/S SEC CB 66670","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #66-67 BUS SEC GIS 보통점검 및 전자변 교체","2025-09-19 10:00","2025-09-19 18:00","취소","취소","연속"]
[339,"충북","직할","신진천S/S CB 6200","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #61-66 BUS TIE GIS 전자변 교체","2025-09-25 10:00","2025-09-25 16:00","2025-09-25 10:00","2025-09-25 16:00","연속"]
[340,"충북","직할","신진천S/S SEC CB 61620","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #61-62 BUS SEC GIS 보통점검 및 전자변 교체","2025-09-17 10:00","2025-09-17 18:00","취소","취소","연속"]
[341,"충북","직할","신진천S/S SEC CB 60610","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #60-61 BUS SEC GIS 보통점검 및 전자변 교체","2025-09-16 10:00","2025-09-16 18:00","취소","취소","연속"]
[342,"충북","직할","신진천진천#2 T/L","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  신진천-진천#2T/L GIS 전자변 교체","2025-09-28 10:00","2025-09-28 16:00","2025-09-28 10:00","2025-09-28 16:00","연속"]
[343,"충북","직할","신진천S/S SEC CB 65660","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #65-66 BUS SEC GIS 보통점검 및 전자변 교체","2025-09-18 10:00","2025-09-18 18:00","취소","취소","연속"]
[344,"충북","청주","국사봉명#2 T/L"," 신청주-문백T/L 건설공사","오송-국사#2 직결을 위한 임시선로 구성","2025-09-17 07:00","2025-09-21 18:00","2025-09-17 07:00","2025-09-21 18:00","연속"]
[345,"충북","청주","국사봉명#1 T/L"," 신청주-문백T/L 건설공사","계통변경(오송-북청주 -> 오송-국사) 본선로 구성을 위한 임시선로 구성","2025-09-06 07:00","2025-09-10 18:00","2025-09-06 07:00","2025-09-10 18:00","연속"]
[346,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_9월)","2025-09-19 14:00","2025-09-20 14:00","취소","취소","연속"]
[347,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_9월)","2025-09-05 07:00","2025-09-06 14:00","취소","취소","연속"]
[348,"충북","청주","남청주S/S SEC CB 67660","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(9월)","2025-09-05 07:00","2025-09-16 18:00","취소","취소","연속"]
[349,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(9월)","2025-09-05 07:00","2025-09-06 14:00","취소","취소","연속"]
[350,"충북","청주","남청주S/S #67 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(9월)","2025-09-06 14:00","2025-09-11 14:00","취소","취소","연속"]
[351,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_9월)","2025-09-10 14:00","2025-09-11 14:00","취소","취소","연속"]
[352,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(9월)","2025-09-11 14:00","2025-09-16 18:00","취소","취소","연속"]
[353,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_9월)","2025-09-15 14:00","2025-09-16 18:00","취소","취소","연속"]
[354,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_9월)","2025-09-29 14:00","2025-09-30 18:00","취소","취소","연속"]
[355,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(9월)","2025-09-25 14:00","2025-09-30 18:00","취소","취소","연속"]
[356,"충북","청주","남청주S/S #62 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(9월)","2025-09-20 14:00","2025-09-25 14:00","취소","취소","연속"]
[357,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(안전이격확보/무부하가압용_9월)","2025-09-20 14:00","2025-09-25 14:00","취소","취소","연속"]
[358,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(9월)","2025-09-19 07:00","2025-09-20 14:00","취소","취소","연속"]
[359,"충북","청주","남청주S/S SEC CB 62610","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(9월)","2025-09-19 07:00","2025-09-30 18:00","취소","취소","연속"]
[360,"충북","청주","화동보은 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검 및 LA, CVT 교체","2025-09-16 10:00","2025-09-16 18:00","2025-09-16 10:00","2025-09-16 18:00","연속"]
[361,"충북","청주","서청주사직#1 T/L","대한전선제 열경화공법 EBG 보강공사","서청주S/S , 사직S/S  서청주-사직 #1T/L EBG 보강공사","2025-09-17 09:00","2025-09-19 18:00","취소","취소","연속"]
[362,"충북","청주","서청주사직#2 T/L","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-09-09 09:00","2025-09-10 18:00","취소","취소","연속"]
[363,"충북","청주","신옥천S/S SEC CB 61620","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-09-03 10:00","2025-09-03 18:00","취소","취소","연속"]
[364,"충북","청주","신옥천S/S SEC CB 66670","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-09-04 10:00","2025-09-04 18:00","취소","취소","연속"]
[365,"충북","청주","신옥천추부#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-09-24 10:00","2025-09-24 18:00","2025-09-24 10:00","2025-09-24 18:00","연속"]
[366,"충북","청주","신옥천추부#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-09-25 10:00","2025-09-25 18:00","2025-09-25 10:00","2025-09-25 18:00","연속"]
[367,"충북","청주","화동영동 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검 및 LA, CVT 교체","2025-09-17 10:00","2025-09-17 18:00","취소","취소","연속"]
[368,"충북","청주","오송북청주#2 T/L"," 신청주-문백T/L 건설공사"," 신청주-북청주#2, 신청주-봉명#1 선로망 구성(계통변경)","2025-09-11 07:00","2025-09-15 18:00","2025-09-11 07:00","2025-09-15 18:00","연속"]
[369,"충북","청주","오송북청주#1 T/L"," 신청주-문백T/L 건설공사","계통변경(오송-북청주 → 오송-국사) 본선로 구성을 위한 임시선로 구성","2025-09-06 07:00","2025-09-10 18:00","2025-09-06 07:00","2025-09-10 18:00","연속"]
[370,"충북","청주","오송국사#2 T/L"," 신청주-문백T/L 건설공사","오송-국사#2 본선로 구성","2025-09-24 07:00","2025-09-30 18:00","2025-09-24 07:00","2025-09-30 18:00","연속"]
[371,"충북","청주","오창국사#1 T/L"," 신청주-문백T/L 건설공사","오송-국사#2T/L 직결(전선 공중이동) 작업대상 선로 4회선 구간 상단 휴전","2025-09-20 07:00","2025-09-21 18:00","2025-09-20 07:00","2025-09-21 18:00","매일"]
[372,"충북","청주","오창국사#1 T/L"," 신청주-문백T/L 건설사업","계통변경(오송-북청주 → 오송-국사) 관련 4회선 상단(오창-국사#1) 선로 휴전","2025-09-06 13:00","2025-09-07 18:00","2025-09-06 13:00","2025-09-07 18:00","연속"]
[373,"충북","청주","오창국사#2 T/L"," 신청주-문백T/L 건설사업","계통변경(오송-북청주 → 오송-국사) 국사S/S 인출변경 작업 4회선(상단) 휴전","2025-09-06 07:00","2025-09-06 12:00","2025-09-06 07:00","2025-09-06 12:00","연속"]
[374,"충북","청주","신옥천옥천#1 T/L","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검 무부하가압용","2025-09-05 15:00","2025-09-05 18:00","2025-09-05 15:00","2025-09-05 18:00","연속"]
[375,"충북","청주","옥천고속철도#1 T/L CB","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-09-04 09:00","2025-09-05 18:00","2025-09-04 09:00","2025-09-05 18:00","연속"]
[376,"충북","청주","옥천영동 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검 및 LA, CVT 교체(양단)","2025-09-18 10:00","2025-09-19 18:00","2025-09-16 10:00","2025-09-16 18:00","매일"]
[377,"충북","청주","옥천S/S #1 BUS","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검 무부하가압용","2025-09-05 15:00","2025-09-05 18:00","2025-09-05 15:00","2025-09-05 18:00","연속"]
[378,"충북","청주","남청주죽림#1 T/L","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-09-24 09:00","2025-09-25 18:00","2025-09-24 09:00","2025-09-25 18:00","연속"]
[379,"충북","충주","금왕남음성#1 T/L","24~25 충북 직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치","2025-09-29 07:00","2025-10-01 18:00","취소","취소","매일"]
[380,"충북","충주","음성금왕#2 T/L","24~25 충북 직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치 / 풍소음 항공장애표시구 교체","2025-09-29 07:00","2025-10-01 18:00","취소","취소","매일"]
[381,"충북","충주","금왕성본#2 T/L"," 성본S/S 건설공사","성본S/S 최초 무부하가압 및 전압 앵극측정 시행 ○  M.Tr(60MVA) 2BANK 설치 ○ 170kV GIS 9CCT 설치 ○ 23kV EGIS 15CCT 설치 ○ 기타 부대공사 1식 설치","2025-09-23 10:00","2025-09-23 18:00","취소","취소","연속"]
[382,"충북","충주","금왕성본#1 T/L"," 성본S/S 건설공사","성본S/S 최초 무부하가압 및 전압 앵극측정 시행 ○  M.Tr(60MVA) 2BANK 설치 ○ 170kV GIS 9CCT 설치 ○ 23kV EGIS 15CCT 설치 ○ 기타 부대공사 1식 설치","2025-09-23 10:00","2025-09-23 18:00","취소","취소","연속"]
[383,"충북","충주","금왕남음성#2 T/L","2025 가공송전선로 순시점검 위탁공사"," 금왕-남음성T/L 정밀점검","2025-09-22 08:00","2025-09-25 18:00","취소","취소","매일"]
[384,"충북","충주","금왕남음성#2 T/L"," 성본S/S 건설공사","성본S/S 최초 무부하가압 및 전압 앵극측정 시행 ○  M.Tr(60MVA) 2BANK 설치 ○ 170kV GIS 9CCT 설치 ○ 23kV EGIS 15CCT 설치 ○ 기타 부대공사 1식 설치","2025-09-22 10:00","2025-09-23 18:00","취소","취소","연속"]
[385,"충북","충주","성본대소 T/L"," 성본S/S 건설공사","성본S/S 최초 무부하가압 및 전압 앵극측정 시행 ○  M.Tr(60MVA) 2BANK 설치 ○ 170kV GIS 9CCT 설치 ○ 23kV EGIS 15CCT 설치 ○ 기타 부대공사 1식 설치","2025-09-25 10:00","2025-09-25 18:00","취소","취소","연속"]
[386,"충북","충주","광혜원대소#2 T/L"," 성본S/S 건설공사","성본S/S 최초 무부하가압 및 전압 앵극측정 시행 ○  M.Tr(60MVA) 2BANK 설치 ○ 170kV GIS 9CCT 설치 ○ 23kV EGIS 15CCT 설치 ○ 기타 부대공사 1식 설치","2025-09-24 10:00","2025-09-25 18:00","취소","취소","연속"]
[387,"충북","충주","북충주충주 T/L","25년 충주전력지사 362,170kV GIS 보통점검공사","북충주,충주S/S  북충주-충주T/L GIS 보통점검","2025-09-29 09:00","2025-09-29 18:00","2025-09-29 09:00","2025-09-29 18:00","연속"]
[388,"충북","충주","북충주S/S CB 6100","25년 충주전력지사 362,170kV GIS 보통점검공사","북충주S/S  #6100 BUS-TIE GIS 보통점검","2025-09-30 09:00","2025-09-30 14:00","2025-09-30 09:00","2025-09-30 14:00","연속"]
[389,"충북","충주","신제천S/S CB 6100","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  #6100 BUS-TIE GIS 보통점검","2025-09-16 14:00","2025-09-16 18:00","취소","취소","연속"]
[390,"충북","충주","신제천남원주#2 T/L","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  신제천-남원주 #2 T/L GIS 보통점검","2025-09-16 09:00","2025-09-16 14:00","2025-09-22 07:30","2025-09-22 18:00","연속"]
[391,"충북","충주","신제천왕암#1 T/L","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  신제천-왕암 #1 T/L GIS 보통점검","2025-09-15 14:00","2025-09-15 18:00","취소","취소","연속"]
[392,"충북","충주","신제천S/S CB 6444","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  #4 M.Tr 2차 GIS 보통점검","2025-09-15 09:00","2025-09-15 14:00","취소","취소","연속"]
[393,"충북","충주","신제천S/S SEC CB 60610","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  60-61 BUS-SEC GIS보통점검","2025-09-18 09:00","2025-09-18 14:00","취소","취소","연속"]
[394,"충북","충주","신제천S/S CB 6300","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  #6300 BUS-TIE GIS보통점검","2025-09-17 14:00","2025-09-17 18:00","취소","취소","연속"]
[395,"충북","충주","신제천S/S CB 6200","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  #6200 BUS-TIE GIS 보통점검","2025-09-17 09:00","2025-09-17 14:00","취소","취소","연속"]
[396,"충북","충주","신제천제천#2 T/L","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S  신제천-제천#2T/L LA 하자점검","2025-09-22 09:00","2025-09-22 18:00","2025-09-22 09:00","2025-09-22 18:00","연속"]
[397,"충북","충주","신제천S/S SEC CB 66670","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  66-67 BUS-SEC GIS 보통점검","2025-09-19 14:00","2025-09-19 18:00","취소","취소","연속"]
[398,"충북","충주","신제천S/S SEC CB 61620","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  61-62 BUS-SEC GIS 보통점검","2025-09-19 09:00","2025-09-19 14:00","취소","취소","연속"]
[399,"충북","충주","신제천S/S SEC CB 65660","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  65-66 BUS-SEC GIS보통점검","2025-09-18 14:00","2025-09-18 18:00","취소","취소","연속"]
[400,"충북","충주","신충주감곡#1 T/L","24~25 충북직할 가공송전 협력회사 총액공사","#1T/L No.45 애자교체","2025-09-18 07:00","2025-09-18 18:00","2025-09-18 07:00","2025-09-18 18:00","연속"]
[401,"충북","충주","신충주감곡#2 T/L","24~25 충북 직할 가공송전 협력회사 총액공사","#2T/L 암 측 만곡부재 및 사재 정비","2025-09-19 07:00","2025-09-19 18:00","2025-09-19 07:00","2025-09-19 18:00","연속"]
[402,"충북","충주","신충주S/S CB 6100","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  #6100 BUS-TIE GIS 보통점검","2025-09-25 09:00","2025-09-25 14:00","2025-09-24 10:00","2025-09-24 18:00","연속"]
[403,"충북","충주","신충주북충주#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","상간스페이서 설치( 신충주-북충주#2T/L No.71~72)","2025-09-01 07:00","2025-09-03 18:00","2025-09-01 07:00","2025-09-03 18:00","매일"]
[404,"충북","충주","신충주북충주#1 T/L","2024~2025년 충주전력지사 송전협력회사 공사","상간스페이서 설치( 신충주-북충주#1 T/L No.71~72)","2025-09-04 07:00","2025-09-05 18:00","2025-09-04 07:00","2025-09-05 18:00","매일"]
[405,"충북","충주","신충주북충주#2 T/L","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주,북충주S/S  신충주-북충주 #2 T/L GIS 보통점검","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[406,"충북","충주","신충주북충주#1 T/L","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  신충주-북충주 #1 T/L GIS 보통점검","2025-09-25 14:00","2025-09-25 18:00","2025-09-25 14:00","2025-09-25 18:00","연속"]
[407,"충북","충주","왕암여주#1 T/L","왕암S/S 옥상방수공사","왕암S/S 옥상방수공사 안전이격거리 확보","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","매일"]
[408,"충북","충주","왕암여주#2 T/L","왕암S/S 옥상방수공사","왕암S/S 옥상방수공사 안전이격거리 확보","2025-09-29 09:00","2025-10-03 18:00","2025-09-29 09:00","2025-10-03 18:00","매일"]
[409,"충북","충주","풍동음성#1 T/L","'24-25년 충주전력지사 변전정비 총액공사","풍동S/S  풍동음성#1 T/L GIS 보통점검 및 CVT 대체","2025-09-12 09:00","2025-09-12 18:00","2025-09-12 09:00","2025-09-12 18:00","연속"]
[410,"대전세종충남","대전","금산무주#1 T/L","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","[송전][오전만][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","2025-09-15 07:00","2025-09-19 11:00","취소","취소","매일"]
[411,"대전세종충남","대전","남대전신흥#2 T/L","남대전S/S  남대전-신흥#2T/L GIS 흡습제 교체","남대전S/S  남대전-신흥#2T/L GIS 흡습제 교체","2025-09-29 09:00","2025-09-30 18:00","2025-09-29 09:00","2025-09-30 18:00","연속"]
[412,"대전세종충남","대전","남대전신흥#1 T/L","남대전S/S  남대전-신흥#1T/L GIS 흡습제 교체","남대전S/S  남대전-신흥#1T/L GIS 흡습제 교체 및 병행작업","2025-09-22 09:00","2025-09-23 18:00","2025-09-22 09:00","2025-09-23 18:00","연속"]
[413,"대전세종충남","대전","부여논산#1 T/L","논산S/S  부여-논산#1T/L GIS 정밀점검","논산S/S  부여-논산#1T/L GIS 정밀점검","2025-09-22 09:00","2025-09-23 18:00","2025-09-22 09:00","2025-09-23 18:00","연속"]
[414,"대전세종충남","대전","부여논산#2 T/L","논산S/S  부여-논산#2T/L GIS 정밀점검","논산S/S  부여-논산#2T/L GIS 정밀점검","2025-09-24 09:00","2025-09-25 18:00","2025-09-24 09:00","2025-09-25 18:00","연속"]
[415,"대전세종충남","대전","서대전유천#2 T/L","[송전]  서대전-유천T/L OF케이블 선종교체공사","○ 공사구간 :  서대전-유천#2T/L 서대전S/S ~유천S/S ○ 선종교체 :  OF 2000㎟ →  XLPE 2000㎟ (2.72km)","2025-09-01 09:00","2025-11-30 18:00","2025-09-01 09:00","2025-11-30 18:00","연속"]
[416,"대전세종충남","대전","신계룡은진#1 T/L","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","[송전][오전만][즉시가압O]345kV 신옥천-청양등8개T/L 추락방지설치공사","2025-09-01 07:00","2025-09-12 11:00","취소","취소","매일"]
[417,"대전세종충남","대전","신계룡두마#1 T/L","[보호반취소시]신계룡S/S 신계룡-두마#1T/L GIS 보통점검","[보호반취소시]신계룡S/S 신계룡-두마#1T/L GIS 보통점검","2025-09-15 09:00","2025-09-15 18:00","취소","취소","연속"]
[418,"대전세종충남","대전","신계룡두마#1 T/L","신계룡,두마S/S 신계룡-두마#1T/L 송전선로 보호반 대체","신계룡,두마S/S 신계룡-두마#1T/L 송전선로 보호반 대체","2025-09-15 09:00","2025-09-17 14:00","취소","취소","연속"]
[419,"대전세종충남","대전","신계룡두마#2 T/L","[보호반취소시]신계룡S/S  신계룡-두마#2T/L 보통점검","[보호반취소시]신계룡S/S  신계룡-두마#2T/L 보통점검","2025-09-17 09:00","2025-09-17 18:00","취소","취소","연속"]
[420,"대전세종충남","대전","신계룡두마#2 T/L","신계룡,두마S/S 신계룡-두마#2T/L 송전선로 보호반 대체","신계룡,두마S/S 신계룡-두마#2T/L 송전선로 보호반 대체","2025-09-17 14:00","2025-09-19 18:00","취소","취소","연속"]
[421,"대전세종충남","대전","신옥천용운#1 T/L","(즉시가압O)용운S/S  신옥천-용운#1T/L ES 락핀 점검","용운S/S  신옥천-용운#1T/L ES 락핀 점검","2025-09-08 09:00","2025-09-08 18:00","2025-09-08 09:00","2025-09-08 18:00","연속"]
[422,"대전세종충남","대전","추부S/S CB 6100","추부S/S  모선 보호배전반 교체공사","추부S/S  모선 보호배전반 교체공사","2025-09-08 09:00","2025-09-12 18:00","2025-09-08 09:00","2025-09-12 18:00","연속"]
[423,"대전세종충남","대전","신옥천추부#1 T/L","[즉시가압O] 추부S/S 신옥천-추부#1T/L GIS 차단기 부동작시험","[즉시가압O] 추부S/S 신옥천-추부#1T/L GIS 차단기 부동작시험","2025-09-22 16:00","2025-09-22 18:00","취소","취소","연속"]
[424,"대전세종충남","대전","신옥천추부#2 T/L","[즉시가압O] 추부S/S 신옥천-추부#2T/L GIS 차단기 부동작시험","추부S/S 신옥천-추부#2T/L GIS 차단기 부동작시험","2025-09-22 18:00","2025-09-22 20:00","취소","취소","연속"]
[425,"대전세종충남","서산","서산대산 T/L","대산S/S 장기사용  GIS 교체공사(4차)","대산S/S 장기사용  GIS 교체공사(4차) - 서산-대산#1T/L, #1M.Tr 1차 GIS 교체","2025-09-08 08:00","2025-09-26 18:00","2025-09-08 08:00","2025-09-26 18:00","연속"]
[426,"대전세종충남","서산","대산석문#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 대산S/S 대산석문#2T/L GIS, LA 보통점검","2025-09-30 09:30","2025-09-30 18:00","취소","취소","연속"]
[427,"대전세종충남","서산","대산석문#1 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 대산S/S 대산석문#1T/L GIS, LA 보통점검","2025-09-29 09:30","2025-09-29 18:00","취소","취소","연속"]
[428,"대전세종충남","서산","서산태안#2 T/L","25년 서산P/O  이하 GIS 정밀점검공사","(즉시가압가능) 서산, 태안S/S 서산태안#2T/L GIS, LA 보통점검","2025-09-27 09:30","2025-09-28 18:00","2025-09-27 09:30","2025-09-28 18:00","매일"]
[429,"대전세종충남","서산","신당진당진#1 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신당진S/S 신당진당진#1T/L CVT 대체","2025-09-30 09:30","2025-09-30 18:00","취소","취소","연속"]
[430,"대전세종충남","서산","신당진당진#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 당진S/S 신당진당진#2T/L GIS 보통점검","2025-09-29 09:30","2025-09-29 18:00","취소","취소","연속"]
[431,"대전세종충남","서산","태안태안화력#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안S/S 태안태안화력#2T/L 차단기 리미트스위치 불량보수","2025-09-26 09:30","2025-09-26 18:00","2025-09-26 09:30","2025-09-26 18:00","연속"]
[432,"대전세종충남","세종","신풍공주#1 T/L","[변전]25년 세종전력지사 변전협력회사 공사","[즉시가압○] GIS 보통점검 ○ GIS 보통점검 -LA 보통점검 병행 -즉시가압 가능","2025-09-18 10:00","2025-09-18 18:00","2025-09-18 10:00","2025-09-18 18:00","연속"]
[433,"대전세종충남","세종","신풍공주#2 T/L","[변전]25년 세종전력지사 변전협력회사 공사","[즉시가압○]  GIS 보통점검 ○ GIS 보통점검 -LA 보통점검 병행 -즉시가압 가능","2025-09-19 09:00","2025-09-19 18:00","2025-09-19 09:00","2025-09-19 18:00","연속"]
[434,"대전세종충남","세종","둔곡송강#2 T/L"," 둔곡-송강T/L 피뢰기 및 추락방지장치 설치공사"," 둔곡-송강T/L 피뢰기 및 추락방지장치 설치공사","2025-09-13 08:00","2025-09-14 18:00","취소","취소","매일"]
[435,"대전세종충남","세종","둔곡송강#1 T/L"," 둔곡-송강T/L 피뢰기 및 추락방지장치 설치공사"," 둔곡-송강T/L 피뢰기 및 추락방지장치 설치공사","2025-09-06 08:00","2025-09-07 18:00","취소","취소","매일"]
[436,"대전세종충남","세종","세종둔곡#1 T/L","[즉시가압O]  세종-둔곡T/L 추락방지장치 설치공사","승탑 작업자의 안전을 위해 추락방지장치를 설치하며, 고정형 클램프를 체결하여 단선시 전력선과 접촉 고장을 방지하고자 함.","2025-09-22 07:00","2025-09-26 18:00","2025-09-22 07:00","2025-09-26 18:00","매일"]
[437,"대전세종충남","세종","부강대청HP T/L","[안전목적][즉시가압O]  세종-부강T/L 불량애자 교체공사"," 세종-부강T/L 불량애자 교체공사 대상 중 4회선 병가철탑의 안전목적상 휴전을 위해 시행","2025-09-01 07:00","2025-09-01 18:00","취소","취소","연속"]
[438,"대전세종충남","세종","세종부강#1 T/L","[즉시가압O]  세종-부강T/L 불량애자 교체공사","하자사항이 발생한 동일 Lot 애자에 대한 교체를 통해 애자 절연파괴로 인한 고장사고 예방","2025-09-01 07:00","2025-09-01 18:00","취소","취소","연속"]
[439,"대전세종충남","세종","세종부강#2 T/L","[즉시가압O]  세종-부강T/L 불량애자 교체공사","하자사항이 발생한 동일 Lot 애자에 대한 교체를 통해 애자 절연파괴로 인한 고장사고 예방","2025-09-02 07:00","2025-09-03 18:00","취소","취소","매일"]
[440,"대전세종충남","세종","부강신탄진 T/L","[즉시가압O]  부강-신탄진T/L 추락방지장치 설치공사","승탑 작업자의 안전을 위해 추락방지장치를 설치하며, 고정형 클램프를 체결하여 단선시 전력선과 접촉 고장을 방지하고자 함.","2025-09-19 07:00","2025-09-19 18:00","취소","취소","연속"]
[441,"대전세종충남","세종","천안소정#2 T/L"," 천안-전의T/L 안전이격 및 전력선 교체공사","○ 천안S/S ~전의S/S 9.945km 전력선 교체 - ACSR 330㎟ → ASCC/TW 430㎟ X S X 2C ○ 저지상고 개소 안전이격 확보 철탑교체 4기 ○ 기타 부대공사","2025-09-15 07:00","2025-10-02 18:00","2025-09-22 07:00","2025-10-09 18:00","연속"]
[442,"대전세종충남","세종","천안소정#1 T/L"," 천안-전의T/L 안전이격 및 전력선 교체공사","○ 천안S/S ~전의S/S 9.945km 전력선 교체 - ACSR 330㎟ → ASCC/TW 430㎟ X S X 2C ○ 저지상고 개소 안전이격 확보 철탑교체 4기 ○ 기타 부대공사","2025-09-15 07:00","2025-10-02 18:00","2025-09-22 07:00","2025-10-09 18:00","연속"]
[443,"대전세종충남","세종","조치원월산 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 조치원월산 No.20~23호 임시 가선로 구성 (찰탑교체 3기 : No.20,21,23)","2025-09-01 07:00","2025-09-03 18:00","2025-09-29 07:00","2025-10-01 18:00","연속"]
[444,"대전세종충남","세종","서세종조치원 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 서서종-조치원 (찰탑철거 및 설치 : No.20,21,22,23)","2025-09-04 07:00","2025-09-10 18:00","2025-10-02 07:00","2025-10-08 18:00","연속"]
[445,"대전세종충남","세종","조치원월산 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 조치원-월산 본선로 구성 (가철탑-&gt본철탑 : No.20,21,23)","2025-09-11 07:00","2025-09-14 18:00","2025-10-09 07:00","2025-10-12 18:00","연속"]
[446,"대전세종충남","직할","대덕둔지 T/L","2024~2025년 직할 변전협력회사 공사"," GIS 보통점검","2025-09-30 09:00","2025-09-30 18:00","2025-09-30 09:00","2025-09-30 18:00","연속"]
[447,"대전세종충남","직할","신흥동대전#3 T/L","2025년 직할 관내S/S 170kV GIS 정밀점검공사","□ 170kV GIS × 12CCT 공압식 정밀점검 □ 전자변 × 12개 교체 □ 기타 : 보조계전기 교체 □ 170kV GIS × 12CCT BUS DS 공압식 보통점검","2025-09-08 08:00","2025-09-10 13:00","2025-09-08 08:00","2025-09-10 13:00","연속"]
[448,"대전세종충남","직할","신흥동대전#2 T/L","2025년 직할 관내S/S 170kV GIS 정밀점검공사","□ 170kV GIS × 12CCT 공압식 정밀점검 □ 전자변 × 12개 교체 □ 기타 : 보조계전기 교체 □ 170kV GIS × 12CCT BUS DS 공압식 보통점검","2025-09-03 13:00","2025-09-05 18:00","2025-09-03 13:00","2025-09-05 18:00","연속"]
[449,"대전세종충남","직할","신흥동대전#1 T/L","2025년 직할 관내S/S 170kV GIS 정밀점검공사","□ 170kV GIS × 12CCT 공압식 정밀점검 □ 전자변 × 12개 교체 □ 기타 : 보조계전기 교체 □ 170kV GIS × 12CCT BUS DS 공압식 보통점검","2025-09-01 08:00","2025-09-03 13:00","2025-09-01 08:00","2025-09-03 13:00","연속"]
[450,"대전세종충남","직할","둔곡송강#2 T/L","24-25 직할변전협력회사 총액공사","송강S/S 둔곡-송강#2T/L 보통점검","2025-09-13 09:00","2025-09-14 18:00","취소","취소","연속"]
[451,"대전세종충남","직할","송강신일#2 T/L","송강,신일S/S 송강-신일#2T/L 보호반 대체공사","송강,신일S/S 송강-신일#2T/L 송전선로 보호반 대체 (병행1) 송강S/S 170kV GIS 보통점검 (병행2) 송강,신일S/S PITR 교체공사","2025-09-20 08:00","2025-09-21 18:00","취소","취소","연속"]
[452,"대전세종충남","천안","둔포직산#1 T/L","'25년 천안P/O 정밀 및 보통점검공사","(즉시가압가능)둔포S/S  직산-둔포#1T/L GIS 보통점검","2025-09-17 09:00","2025-09-17 18:00","2025-09-17 09:00","2025-09-17 18:00","연속"]
[453,"대전세종충남","천안","둔포석곡#2 T/L"," 둔포-석곡#2T/L 노후 보호배전반 대체","(즉시가압불가) 둔포-석곡#2T/L 노후 보호배전반 대체","2025-09-29 09:00","2025-10-04 18:00","취소","취소","연속"]
[454,"대전세종충남","천안","둔포석곡#1 T/L"," 둔포-석곡#1T/L 노후 보호배전반 대체","(즉시가압불가) 둔포-석곡#1T/L 노후 보호배전반 대체","2025-09-23 09:00","2025-09-26 18:00","취소","취소","연속"]
[455,"대전세종충남","천안","둔포직산#2 T/L","'25년 천안P/O 정밀 및 보통점검공사","(즉시가압가능)둔포S/S  직산-둔포#2T/L GIS 보통점검","2025-09-18 09:00","2025-09-18 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[456,"대전세종충남","천안","불당서천안#1 T/L","(즉시가압가능) 불당-서천안#1T/L CB 개폐타임 측정","(즉시가압가능) 불당-서천안#1T/L CB 개폐타임 측정","2025-09-01 09:00","2025-09-01 18:00","2025-09-01 09:00","2025-09-01 18:00","연속"]
[457,"대전세종충남","천안","불당서천안#2 T/L","'25년 천안P/O 정밀 및 보통점검공사","(즉시가압가능)서천안S/S  불당-서천안#2T/L GIS 보통점검","2025-09-09 09:00","2025-09-09 18:00","2025-09-09 09:00","2025-09-09 18:00","연속"]
[458,"대전세종충남","천안","신온양석곡#2 T/L","'25년 천안P/O 정밀 및 보통점검공사","(즉시가압가능)석곡S/S  신온양-석곡#2T/L GIS 보통점검","2025-09-05 09:00","2025-09-05 18:00","취소","취소","연속"]
[459,"대전세종충남","천안","신온양석곡#1 T/L","'25년 천안P/O 정밀 및 보통점검공사","(즉시가압가능)석곡S/S  신온양-석곡#1T/L GIS 보통점검","2025-09-04 09:00","2025-09-04 18:00","취소","취소","연속"]
[460,"대전세종충남","천안","아산인주#2 T/L","인주S/S 아산-인주#2T/L CB 개폐타임 측정","인주S/S 아산-인주#2T/L CB 전자변 교체 및 개폐타임 측정","2025-09-27 09:00","2025-09-27 18:00","취소","취소","연속"]
[461,"대전세종충남","천안","아산예산#1 T/L"," 아산-예산T/L 추락방지장치 설치공사","[즉시가압가능] 아산-예산T/L No. 1 ~ 48 추락방지장치 설치","2025-09-03 07:00","2025-09-05 18:00","취소","취소","매일"]
[462,"대전세종충남","천안","아산예산#2 T/L"," 아산-예산#2T/L 노후 보호배전반 대체","(즉시가압불가)(장기미교체 대상) 아산-예산#2T/L 노후 보호배전반 대체","2025-09-29 09:00","2025-10-04 18:00","취소","취소","연속"]
[463,"대전세종충남","천안","아산예산#1 T/L"," 아산-예산#1T/L 노후 보호배전반 대체","(즉시가압불가)(장기미교체 대상) 아산-예산#1T/L 노후 보호배전반 대체","2025-09-02 09:00","2025-09-05 18:00","취소","취소","연속"]
[464,"대전세종충남","천안","온양풍세#1 T/L","'25년 천안P/O 정밀 및 보통점검공사","(즉시가압가능)온양,풍세S/S  온양-풍세#1T/L GIS 보통점검","2025-09-11 09:00","2025-09-12 18:00","2025-09-11 09:00","2025-09-12 18:00","매일"]
[465,"대전세종충남","천안","온양풍세#2 T/L","'25년 천안P/O 정밀 및 보통점검공사","(즉시가압가능)온양,풍세S/S  온앙-풍세#2T/L GIS 보통점검","2025-09-22 09:00","2025-09-23 18:00","2025-09-22 09:00","2025-09-23 18:00","연속"]
[466,"대전세종충남","천안","장재천안#1 T/L","'25년 천안P/O 정밀 및 보통점검공사","(즉시가압가능)장재,천안S/S  장재-천안#1T/L GIS 보통점검","2025-09-25 09:00","2025-09-26 18:00","2025-09-25 09:00","2025-09-26 18:00","매일"]
[467,"대전세종충남","천안","장재천안#1 T/L"," 장재-천안#1T/L 노후 보호배전반 대체","(즉시가압불가)(장기미교체 대상) 장재-천안#1T/L 노후 보호배전반 대체","2025-09-23 09:00","2025-09-26 18:00","2025-09-23 09:00","2025-09-26 18:00","연속"]
[468,"대전세종충남","청양","관창대천#1 T/L","[변전총액]청양P/O 변전협력회사 총액공사"," 관창-대천#1T/L 차단기 조작시험 및 LA보통점검","2025-09-30 09:00","2025-09-30 18:00","취소","취소","연속"]
[469,"대전세종충남","청양","관창보령CC T/L","[변전총액]청양P/O 변전협력회사 총액공사"," 관창-대천#1T/L 차단기 조작시험 및 전자변교체","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[470,"대전세종충남","청양","보령C/C 보령LNGT/L CB","[변전총액]청양P/O 변전협력회사 총액공사"," 보령복합T/L 차단기 조작시험 및 전자변 교체","2025-09-25 09:00","2025-09-25 18:00","2025-09-25 09:00","2025-09-25 18:00","연속"]
[471,"대전세종충남","청양","보령T/P CB 6100","[변전총액]청양P/O 변전협력회사 총액공사","6100 BUS TIE 차단기조작시험 및 전자변 교체","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[472,"대전세종충남","청양","청양은하#2 T/L","[송전] 청양은하#2T/L 정밀점검","철탑, 전력선, 애자금구류 승탑점검 (4회선 구간)","2025-09-23 08:00","2025-09-23 18:00","2025-09-23 08:00","2025-09-23 18:00","연속"]
[473,"대전세종충남","청양","은하홍성#2 T/L","[변전총액] 청양P/O 변전협력 총액공사","ㅁ은하-홍성#2T/L 보호배전반 교체(은하S/S , 홍성S/S )","2025-09-09 09:00","2025-09-12 18:00","2025-09-09 09:00","2025-09-12 18:00","연속"]
[474,"대전세종충남","청양","은하홍성#1 T/L","[송전] 은하-홍성#1T/L 정밀점검","철탑, 전력선, 애자금구류 승탑점검 (4회선 구간)","2025-09-23 08:00","2025-09-23 18:00","2025-09-23 08:00","2025-09-23 18:00","연속"]
[475,"대전세종충남","청양","동군산장항#1 T/L","[변전총액]청양P/O 변전협력회사 총액공사"," 동군산-장항#1T/L 차단기 조작시험 및 CVT 하자점검 - 87보호계전기 통신 오류 점검","2025-09-18 09:00","2025-09-18 18:00","취소","취소","연속"]
[476,"대전세종충남","청양","동군산장항#2 T/L","[변전총액]청양P/O 변전협력회사 총액공사"," 동군산-장항#2T/L 차단기 조작시험 및 LA보통점검, CVT 하자점검","2025-09-19 09:00","2025-09-19 18:00","취소","취소","연속"]
[477,"대전세종충남","청양","청양S/S SEC CB 65660","[변전총액] 청양P/O 변전협력 총액공사","청양SS  #60-#65모선보호반 교체공사","2025-09-15 09:00","2025-09-19 18:00","취소","취소","연속"]
[478,"대전세종충남","청양","청양S/S CB 6100","[변전총액] 청양P/O 변전협력 총액공사","청양SS  #60-#65모선보호반 교체공사","2025-09-15 09:00","2025-09-19 18:00","취소","취소","연속"]
[479,"대전세종충남","청양","청양S/S SEC CB 60610","[변전총액] 청양P/O 변전협력 총액공사","청양SS  #60-#65모선보호반 교체공사","2025-09-15 09:00","2025-09-19 18:00","취소","취소","연속"]
[480,"전북","군산","군산동군산#1 T/L","군산P/O 이상 차단기 조작시험","군산P/O 이상 차단기 조작시험","2025-09-12 09:00","2025-09-12 14:00","2025-09-12 09:00","2025-09-12 14:00","연속"]
[481,"전북","군산","군산동군산#2 T/L","군산P/O 이상 차단기 조작시험","군산P/O 이상 차단기 조작시험","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[482,"전북","군산","내초군장#1 T/L","24~25년 군산전력지사 변전협력회사 총액공사","-송전선로 노후배전반 대체공사(중복)","2025-09-29 09:00","2025-10-01 18:00","2025-09-29 09:00","2025-10-01 18:00","연속"]
[483,"전북","군산","동군산장항#2 T/L","'25년 가공송전 순시점검 위탁공사(옥산-장항 동시휴전 필요)"," 동군산-장항T/L 철탑 정밀점검 No.18~38.99 ※  옥산-장항, 동군산-장항T/L 4회선구간 작업으로 인한 동시휴전 요청","2025-09-15 07:00","2025-09-16 18:00","취소","취소","매일"]
[484,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사(중복)","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2025-09-22 09:00","2025-09-25 18:00","취소","취소","연속"]
[485,"전북","군산","비응군장#2 T/L","비응S/S  비응-동비응 #1,2T/L GIS 증설공사","170kV GIS × 2CCT (617, 677) - 677 BAY #2BUS 무부하 가압","2025-09-03 18:00","2025-09-04 18:00","2025-09-03 18:00","2025-09-04 18:00","연속"]
[486,"전북","군산","비응군장#2 T/L","비응S/S  비응-동비응 #1,2T/L GIS 증설공사","170kV GIS × 2CCT (617, 677) - 677 BAY #1BUS 무부하 가압","2025-09-11 18:00","2025-09-12 18:00","2025-09-11 18:00","2025-09-12 18:00","연속"]
[487,"전북","군산","군산영등#1 T/L","'25년 군산전력지사 가공송전협력회사공사(영등-낭산#2 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-09-10 07:00","2025-09-10 18:00","취소","취소","연속"]
[488,"전북","군산","영등낭산#1 T/L","'25년 군산전력지사 가공송전협력회사공사(영등-낭산#2 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-09-11 07:00","2025-09-11 18:00","취소","취소","연속"]
[489,"전북","군산","영등낭산#2 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#1 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-09-10 07:00","2025-09-10 18:00","취소","취소","연속"]
[490,"전북","군산","군산영등#2 T/L","'25년 군산전력지사 가공송전협력회사공사(영등-낭산#2 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-09-11 07:00","2025-09-11 18:00","취소","취소","연속"]
[491,"전북","군산","팔봉S/S CB 6100","팔봉S/S 혼용운영시스템 설치공사(재)","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[492,"전북","군산","팔봉S/S CB 6100","팔봉S/S 혼용운영시스템 설치공사(재)","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2025-09-23 09:00","2025-09-23 18:00","취소","취소","연속"]
[493,"전북","군산","은진함열#2 T/L","'25년 가공송전 순시점검 위탁공사"," 은진-함열T/L 14기 조류착지방지장치 설치","2025-09-17 07:00","2025-09-18 18:00","취소","취소","연속"]
[494,"전북","김제","백산김제#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-09-15 08:00","2025-09-15 18:00","취소","취소","매일"]
[495,"전북","김제","김제칠보HP T/L","철탑 안전도 검토 관련 기설철탑 실측","기설철탑 안전도 검토를 위한 승탑 및 실측","2025-09-02 09:00","2025-09-03 18:00","2025-09-02 09:00","2025-09-03 18:00","매일"]
[496,"전북","김제","담양김제 T/L","'25년 가공송전 순시점검 위탁공사","정밀점검","2025-09-17 09:00","2025-09-17 18:00","취소","취소","연속"]
[497,"전북","김제","백산김제#2 T/L","김제전력지사 장기사용 배전반 대체","김제,백산S/S 백산-김제#2T/L 보호반 대체","2025-09-16 09:00","2025-09-18 18:00","취소","취소","연속"]
[498,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(6200 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-09-11 15:00","2025-09-12 15:00","취소","취소","연속"]
[499,"전북","김제","부안동부안#2 T/L","모선구분차단기 설치공사(6200 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-09-16 15:00","2025-09-17 15:00","취소","취소","연속"]
[500,"전북","김제","부안동부안#2 T/L","모선구분차단기 설치공사(PT&ES 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-09-25 15:00","2025-09-26 15:00","취소","취소","연속"]
[501,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(PT&ES 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-09-20 15:00","2025-09-21 15:00","취소","취소","연속"]
[502,"전북","김제","김제부안#2 T/L","모선구분차단기 설치(6200)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-09-09 09:00","2025-09-17 18:00","취소","취소","연속"]
[503,"전북","김제","김제부안#1 T/L","모선구분차단기 설치(PT&ES)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-09-18 09:00","2025-09-26 18:00","취소","취소","연속"]
[504,"전북","김제","신김제정공#2 T/L","'25년 가공송전 순시점검 위탁공사","가공지선 보수작업","2025-09-25 09:00","2025-09-25 18:00","취소","취소","연속"]
[505,"전북","김제","신김제전주#2 T/L","'25년 가공송전 순시점검 위탁공사"," 신김제-전주T/L 정밀점검","2025-09-24 09:00","2025-09-24 18:00","취소","취소","연속"]
[506,"전북","김제","신김제전주#1 T/L","'25년 가공송전 순시점검 위탁공사"," 신김제-전주T/L 정밀점검","2025-09-23 09:00","2025-09-23 18:00","취소","취소","연속"]
[507,"전북","김제","신김제동전주#1 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #1T/L 전선이동 (가선로 → 본선로), 케이블타워 조립 및 긴선 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-09-19 07:00","2025-09-27 18:00","취소","취소","연속"]
[508,"전북","김제","신김제남전주#2 T/L"," 신김제-남전주 #2T/L 차단기 조작시험","차단기 조작시험","2025-09-09 09:00","2025-09-09 18:00","2025-09-09 09:00","2025-09-09 18:00","연속"]
[509,"전북","김제","신김제남전주#1 T/L"," 신김제-남전주 #1T/L 차단기 조작시험","차단기 조작시험","2025-09-08 09:00","2025-09-08 18:00","2025-09-08 09:00","2025-09-08 18:00","연속"]
[510,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #2T/L 전선이동 (가선로 → 본선로) 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-09-15 07:00","2025-09-18 18:00","취소","취소","연속"]
[511,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #2T/L 긴선(케이블타워) 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-09-28 09:00","2025-10-01 18:00","취소","취소","연속"]
[512,"전북","김제","정주동부안#1 T/L","정주S/S 정주-동부안#1T/L GIS 정밀점검(연속)","정주S/S 정주-동부안#1T/L GIS 정밀점검(연속)","2025-09-29 09:00","2025-09-30 18:00","취소","취소","연속"]
[513,"전북","직할","동전주태평#1 T/L","6433 GIS 정밀점검 관련 무부하가압","CB, DS 정밀점검","2025-09-25 14:00","2025-09-25 18:00","2025-09-25 14:00","2025-09-25 18:00","연속"]
[514,"전북","직할","동전주태평#1 T/L","6433 GIS 정밀점검 관련 무부하가압","CB, DS 정밀점검","2025-09-23 14:00","2025-09-23 18:00","2025-09-23 14:00","2025-09-23 18:00","연속"]
[515,"전북","직할","왕궁봉동#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-09-09 08:00","2025-09-09 18:00","취소","취소","매일"]
[516,"전북","직할","왕궁봉동#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-09-08 08:00","2025-09-08 18:00","취소","취소","매일"]
[517,"전북","직할","북전주S/S CB 6100","북전주S/S 장기사용 모선 보호반 대체 공사","- 북전주S/S 모선보호반 대체","2025-09-15 09:00","2025-09-19 18:00","취소","취소","연속"]
[518,"전북","직할","신남원S/S #6 EM.Tr CB","신남원 ESS 변전설비 #6EM.Bank 초기점검","- EM.Tr(1), EP.Tr(7) 점검 -  EGIS(1), 23kV EGIS(9) 점검","2025-09-29 09:00","2025-10-03 18:00","2025-09-29 09:00","2025-10-03 18:00","연속"]
[519,"전북","직할","신남원S/S #5 EM.Tr CB","신남원 ESS 변전설비 #5EM.Bank 초기점검","- EM.Tr(1), EP.Tr(7) 점검 -  EGIS(1), 23kV EGIS(9) 점검","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[520,"전북","직할","전주서곡#1 T/L","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","2025-09-05 14:00","2025-09-05 18:00","취소","취소","연속"]
[521,"전북","직할","전주서곡#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-09-23 08:00","2025-09-24 18:00","취소","취소","매일"]
[522,"전북","직할","전주서곡#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-09-01 08:00","2025-09-02 18:00","취소","취소","매일"]
[523,"전북","직할","전주서곡#1 T/L","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","2025-09-03 14:00","2025-09-03 18:00","취소","취소","연속"]
[524,"전북","직할","진안장수#1 T/L","진안S/S 6233 GIS 정밀점검 관련 무부하가압","진안S/S 6233 GIS 정밀점검 관련 무부하가압","2025-09-10 14:00","2025-09-10 18:00","2025-09-10 14:00","2025-09-10 18:00","연속"]
[525,"전북","직할","동전주태평#2 T/L","태평S/S  장기사용 GIS 교체공사 (무부하가압, 2H)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-09-12 16:00","2025-09-12 18:00","2025-09-12 16:00","2025-09-12 18:00","연속"]
[526,"전북","직할","동전주태평#2 T/L","태평S/S  장기사용 GIS 교체공사 (모선절체용 임시 TIE)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-09-22 09:00","2025-09-22 10:00","2025-09-22 09:00","2025-09-22 10:00","연속"]
[527,"전북","직할","동전주태평#2 T/L","태평S/S  장기사용 GIS 교체공사 (모선절체용 임시 TIE)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-09-13 09:00","2025-09-13 10:00","2025-09-13 09:00","2025-09-13 10:00","연속"]
[528,"전북","직할","동전주태평#2 T/L","태평S/S  장기사용 GIS 교체공사 (무부하가압)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-09-20 18:00","2025-09-21 18:00","2025-09-20 18:00","2025-09-21 18:00","연속"]
[529,"전북","직할","동전주태평#2 T/L","태평S/S  장기사용 GIS 교체공사 (무부하가압)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-09-28 14:00","2025-09-29 18:00","2025-09-28 14:00","2025-09-29 18:00","연속"]
[530,"광주전남","강진","강진장흥#2 T/L","강진-장흥#2T/L 피뢰기 절연열화측정","강진-장흥#2T/L 피뢰기 절연열화측정","2025-09-10 14:00","2025-09-10 18:00","2025-09-11 20:00","2025-09-12 00:00","연속"]
[531,"광주전남","강진","강진남창#1 T/L","'25년 강진전력지사 170kV 이상 GIS 보통점검 공사","- 170kV GIS 보통점검","2025-09-19 10:00","2025-09-19 15:00","취소","취소","연속"]
[532,"광주전남","강진","강진남창#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 신강진-강진#1T/L 피뢰기 및 추락방지장치 설치 (강진-남창#1T/L 안전이격휴전 병행)","2025-09-22 07:00","2025-09-23 18:00","취소","취소","매일"]
[533,"광주전남","강진","신강진강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 신강진-강진#1T/L 피뢰기 및 추락방지장치 설치 (강진-남창#1T/L 안전이격휴전 병행)","2025-09-22 07:00","2025-09-23 18:00","취소","취소","매일"]
[534,"광주전남","강진","강진장흥#1 T/L","강진-장흥#1T/L 피뢰기 절연열화측정","강진-장흥#1T/L 피뢰기 절연열화측정","2025-09-10 09:00","2025-09-10 14:00","2025-09-24 16:00","2025-09-24 20:00","연속"]
[535,"광주전남","강진","금정강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 금정-강진#1 피뢰기 및 추락방지장치 설치 (강진-장흥#2 4회선 구간 안전이격휴전 병행)","2025-09-08 07:00","2025-09-09 18:00","2025-09-08 16:00","2025-09-09 03:00","매일"]
[536,"광주전남","강진","강진장흥#2 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 강진-장흥#2T/L 피뢰기 및 추락방지장치 설치","2025-09-08 07:00","2025-09-12 18:00","2025-09-08 16:00","2025-09-13 03:00","매일"]
[537,"광주전남","강진","나주금천#1 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#2T/L 정밀점검(안전이격 확보) (나주-영암#2T/L 병가선로)(1시간 내 가압 가능)","2025-09-23 07:00","2025-09-26 18:00","취소","취소","매일"]
[538,"광주전남","강진","나주영암#2 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#2T/L 정밀점검 (영암-금정#1T/L, 나주-금천#1T/L 병가선로)(1시간 내 가압 가능)","2025-09-16 07:00","2025-09-26 18:00","취소","취소","매일"]
[539,"광주전남","강진","남창완도 T/L","'24-25년 강진전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2025-09-16 10:00","2025-09-16 14:00","2025-09-30 10:00","2025-09-30 14:00","연속"]
[540,"광주전남","강진","남창완도 T/L","'24-25년 강진전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2025-09-16 10:00","2025-09-16 14:00","취소","취소","연속"]
[541,"광주전남","강진","남창S/S 모선연계T/L CB","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-09-10 07:00","2025-09-14 15:00","취소","취소","연속"]
[542,"광주전남","강진","남창해남CS#1 T/L","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-09-10 07:00","2025-09-14 15:00","취소","취소","연속"]
[543,"광주전남","강진","남창해남CS#2 T/L","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-09-08 09:00","2025-09-10 15:00","취소","취소","연속"]
[544,"광주전남","강진","대불KC T/L CB","남창S/S 남창-해남C/S 인출변경 공사","대불-KCT/L 피뢰기 절연열화측정","2025-09-11 09:00","2025-09-11 18:00","취소","취소","연속"]
[545,"광주전남","강진","대불남악#1 T/L","2024~2025년 강진전력지사 변전협력회사 공사","대불S/S 대불-남악#1T/L CVT 보통점검","2025-09-05 09:00","2025-09-05 13:00","취소","취소","연속"]
[546,"광주전남","강진","대불남악#2 T/L","2024~2025년 강진전력지사 변전협력회사 공사","대불S/S 대불-남악#2T/L LA A,B,C 보통점검","2025-09-05 13:00","2025-09-05 17:00","취소","취소","연속"]
[547,"광주전남","강진","신강진대불#1 T/L","신강진-대불#1T/L 피뢰기 절연열화측정","신강진-대불#1T/L 피뢰기 절연열화측정","2025-09-09 09:00","2025-09-09 18:00","취소","취소","연속"]
[548,"광주전남","강진","삼호화원#1 T/L"," 삼호-화원 지중T/L(복도체화) 건설공사"," XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2025-09-01 09:00","2025-09-18 18:00","취소","취소","연속"]
[549,"광주전남","강진","삼호화원#2 T/L"," 삼호-화원 지중T/L(복도체화) 건설공사"," XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2025-09-22 09:00","2025-10-09 18:00","취소","취소","연속"]
[550,"광주전남","강진","신강진대불#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","신강진-대불#2 가공지선 교체공사","2025-09-26 07:00","2025-09-26 18:00","취소","취소","연속"]
[551,"광주전남","강진","영암금정#1 T/L","2025년 가공송전 순시점검 위탁공사","영암-금정#1T/L 정밀점검 (나주-영암#2T/L 병가선로)(1시간 내 가압 가능)","2025-09-15 07:00","2025-09-22 18:00","취소","취소","매일"]
[552,"광주전남","강진","장흥벌교 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 장흥-벌교/L 피뢰기 및 추락방지장치 설치","2025-09-10 07:00","2025-09-18 18:00","2025-09-10 07:00","2025-09-18 18:00","매일"]
[553,"광주전남","강진","화원진도#2 T/L","'24-25년 강진전력지사 변전협력회사 공사","- 차단기 조작시험 및 공기배출밸브 구조 개선","2025-09-22 14:00","2025-09-22 18:00","취소","취소","연속"]
[554,"광주전남","강진","화원진도#1 T/L","'24-25년 강진전력지사 변전협력회사 공사","- 차단기 조작시험 및 공기배출밸브 구조 개선","2025-09-22 10:00","2025-09-22 14:00","취소","취소","연속"]
[555,"광주전남","강진","해남진도#2 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-09-11 16:00","2025-09-11 20:00","2025-09-11 16:00","2025-09-11 20:00","매일"]
[556,"광주전남","강진","해남해남CS#2 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-09-10 16:00","2025-09-10 20:00","2025-09-10 16:00","2025-09-10 20:00","매일"]
[557,"광주전남","강진","해남해남CS#1 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-09-09 16:00","2025-09-09 20:00","2025-09-09 16:00","2025-09-09 20:00","매일"]
[558,"광주전남","강진","화원진도#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","OPGW 백색 항공장애표시구 교체(민원 발생개소)","2025-09-30 07:00","2025-09-30 18:00","취소","취소","연속"]
[559,"광주전남","강진","화원진도#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","항공장애표시구 (강진전(송전)-1431)로 인한 철거분 재설치","2025-09-29 07:00","2025-09-29 18:00","취소","취소","연속"]
[560,"광주전남","강진","화원안좌#1 T/L","'25년 강진전력지사 170kV 이상 GIS 보통점검 공사","- 170kV GIS 보통점검","2025-09-15 16:00","2025-09-15 20:00","2025-09-15 18:00","2025-09-15 22:00","연속"]
[561,"광주전남","강진","화원진도#1 T/L","2025년 가공송전 순시점검 위탁공사","화원-진도#1T/L 정밀점검 (1시간 내 가압 가능)","2025-09-09 08:00","2025-09-12 18:00","취소","취소","매일"]
[562,"광주전남","강진","화원안좌#2 T/L","'25년 강진전력지사 170kV 이상 GIS 보통점검 공사","- 170kV GIS 보통점검","2025-09-16 16:00","2025-09-16 20:00","2025-09-16 18:00","2025-09-16 22:00","연속"]
[563,"광주전남","광주","계림S/S SEC CB 66650","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-09-10 09:00","2025-09-12 18:00","취소","취소","연속"]
[564,"광주전남","광주","계림S/S CB 6100","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-09-08 09:00","2025-09-12 18:00","취소","취소","연속"]
[565,"광주전남","광주","계림S/S SEC CB 61600","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-09-08 09:00","2025-09-10 18:00","취소","취소","연속"]
[566,"광주전남","광주","계림승주#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","1. 작업내용 : 고정형 폴리머 점퍼지지애자 및 금구 설치 □ 작업구간 ○ 계림-남광주T/L No.1~2, 34.1(계림-소태,계림-승주T/L(병가철탑)) ○ 계림-소태T/L No.1(계림-남광주T/L(병가철탑)) 2. 작업내용 : 수평 추락방지장치 설치 □ 작업구간 : 계림-소태T/L No.36","2025-09-04 07:00","2025-09-04 18:00","2025-09-04 07:00","2025-09-04 18:00","연속"]
[567,"광주전남","광주","계림소태 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","1. 작업내용 : 고정형 폴리머 점퍼지지애자 및 금구 설치 □ 작업구간 ○ 계림-남광주T/L No.1~2, 34.1(계림-소태,계림-승주T/L(병가철탑)) ○ 계림-소태T/L No.1(계림-남광주T/L(병가철탑)) 2. 작업내용 : 수평 추락방지장치 설치 □ 작업구간 : 계림-소태T/L No.36","2025-09-04 07:00","2025-09-04 18:00","2025-09-12 07:00","2025-09-12 18:00","연속"]
[568,"광주전남","광주","계림남광주 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","1. 작업내용 : 고정형 폴리머 점퍼지지애자 및 금구 설치 □ 작업구간 ○ 계림-남광주T/L No.1~2, 34.1(계림-소태,계림-승주T/L(병가철탑)) ○ 계림-소태T/L No.1(계림-남광주T/L(병가철탑)) 2. 작업내용 : 수평 추락방지장치 설치 □ 작업구간 : 계림-소태T/L No.36","2025-09-04 07:00","2025-09-04 18:00","2025-09-12 07:00","2025-09-12 18:00","연속"]
[569,"광주전남","광주","계림승주#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 계림-승주#2 T/L 피뢰기 설치 - 대상 : 1~3, 17~107호 (총 99기) - 병가구간 : 3호 (신광주-계림#1,#2 병가), 99~106호(순천-승주#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-09-01 07:00","2025-09-11 18:00","2025-09-01 07:00","2025-09-11 18:00","매일"]
[570,"광주전남","광주","계림승주#2 T/L","계림-승주#2T/L 피뢰기 절연열화측정","계림-승주#2T/L 피뢰기 절연열화측정","2025-09-19 09:00","2025-09-19 14:00","2025-09-19 09:00","2025-09-19 14:00","연속"]
[571,"광주전남","광주","계림S/S CB 6200","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 6200BUS-TIE 조작시험","2025-09-18 10:00","2025-09-18 16:00","2025-09-18 10:00","2025-09-18 16:00","연속"]
[572,"광주전남","광주","계림S/S SEC CB 66650","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S #65-#66 BUS-SEC 조작시험","2025-09-17 13:00","2025-09-17 16:00","2025-09-17 13:00","2025-09-17 16:00","연속"]
[573,"광주전남","광주","계림S/S SEC CB 61600","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S #60-61BUS-SEC 조작시험","2025-09-17 10:00","2025-09-17 13:00","2025-09-17 10:00","2025-09-17 13:00","연속"]
[574,"광주전남","광주","신광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 신광주-계림#2T/L 170kV GIS 조작시험","2025-09-16 13:00","2025-09-16 16:00","취소","취소","연속"]
[575,"광주전남","광주","신광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 신광주-계림#1T/L 170kV GIS 조작시험","2025-09-16 10:00","2025-09-16 13:00","취소","취소","연속"]
[576,"광주전남","광주","북광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#2T/L 조작시험","2025-09-15 13:00","2025-09-15 16:00","취소","취소","연속"]
[577,"광주전남","광주","북광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#1T/L 조작시험","2025-09-15 10:00","2025-09-15 13:00","취소","취소","연속"]
[578,"광주전남","광주","곡성구례#1 T/L","24~25년 광주전력지사 송전협력회사 공사(폴리머점퍼지지애자)"," 곡성-구례#1T/L 폴리머점퍼지지애자 설치 29기","2025-09-08 07:00","2025-09-12 18:00","2025-09-08 07:00","2025-09-12 18:00","매일"]
[579,"광주전남","광주","곡성구례#2 T/L","24~25년 광주전력지사 송전협력회사 공사(폴리머점퍼지지애자)"," 곡성-구례#2T/L 폴리머점퍼지지애자 설치 32기","2025-09-15 07:00","2025-09-19 18:00","2025-09-15 07:00","2025-09-19 18:00","매일"]
[580,"광주전남","광주","담양김제 T/L","24~25년 광주전력지사 송전협력회사 공사(피뢰기)"," 담양-김제T/L 피뢰기 설치 33기","2025-09-22 07:00","2025-09-24 18:00","취소","취소","매일"]
[581,"광주전남","광주","담양일곡#1 T/L","2024~25년 광주전력지사 송전협력회사공사(피뢰기) 안전이격 확보"," 담양-김제T/L 피뢰기설치공사 4회선 안전이격 확보 휴전","2025-09-23 07:00","2025-09-24 18:00","취소","취소","매일"]
[582,"광주전남","광주","정공담양 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 (병가) - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-09-15 07:00","2025-09-16 18:00","취소","취소","매일"]
[583,"광주전남","광주","신광주계림#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  신광주-계림#2T/L GIS 보통점검","2025-09-29 09:00","2025-09-29 18:00","취소","취소","연속"]
[584,"광주전남","광주","신광주장성#2 T/L","신광주-장성#2T/L 피뢰기 절연열화측정","신광주-장성#2T/L 피뢰기 절연열화측정","2025-09-12 09:00","2025-09-12 14:00","취소","취소","연속"]
[585,"광주전남","광주","신광주장성#2 T/L","24~25년 광주전력지사 송전협력회사 공사(가공지선교체)"," 신광주-장성T/L 가공지선교체공사 63~66호 3경간","2025-09-26 07:00","2025-09-26 18:00","취소","취소","매일"]
[586,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  신광주-장성#2T/L GIS 정밀점검","2025-09-30 09:00","2025-10-02 18:00","취소","취소","연속"]
[587,"광주전남","광주","신화순S/S #1 EM.Tr CB","2025년 신화순S/S FR-ESS 정기점검","2025년 신화순S/S FR-ESS 정기점검","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[588,"광주전남","광주","신화순화순#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 피뢰기 갭혼 교체 -  신화순-화순#1T/L 1~5, 10~57호","2025-09-23 08:00","2025-09-30 18:00","취소","취소","매일"]
[589,"광주전남","광주","신화순화순#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 -  신화순-화순#1T/L 1~5, 10~57호","2025-09-16 08:00","2025-09-22 18:00","취소","취소","매일"]
[590,"광주전남","광주","신화순S/S #1 EM.Tr CB","2025년 신화순S/S FR-ESS 정기점검","2025년 신화순S/S FR-ESS 정기점검","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[591,"광주전남","광주","담양일곡#1 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  담양-일곡#1T/L GIS 보통점검","2025-09-19 09:00","2025-09-19 18:00","취소","취소","연속"]
[592,"광주전남","광주","담양일곡#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-09-15 07:00","2025-09-19 18:00","취소","취소","매일"]
[593,"광주전남","광주","일곡S/S CB 6100","2025년 광주전력지사 170kV GIS 점검공사","2025년 광주전력지사 170kV GIS 점검공사 1. 일곡S/S BUSTIE 정밀점검","2025-09-30 09:00","2025-10-02 18:00","2025-09-30 09:00","2025-10-02 18:00","연속"]
[594,"광주전남","광주","장성영광#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치 - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-09-22 07:00","2025-09-26 18:00","취소","취소","매일"]
[595,"광주전남","광주","하남장성#1 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치(병가) - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-09-22 07:00","2025-09-23 18:00","취소","취소","매일"]
[596,"광주전남","광주","장성영광#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","-장성-영광#1T/L 170kV GIS 조작시험","2025-09-19 15:00","2025-09-19 18:00","취소","취소","연속"]
[597,"광주전남","광주","충장농성#1 T/L","충장-농성T/L OF케이블 절연유 채유","충장-농성T/L OF케이블 절연유 채유","2025-09-17 09:00","2025-09-17 18:00","2025-09-17 09:00","2025-09-17 18:00","연속"]
[598,"광주전남","광주","충장농성#2 T/L","충장-농성T/L OF케이블 절연유 채유","충장-농성T/L OF케이블 절연유 채유","2025-09-18 09:00","2025-09-18 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[599,"광주전남","광주","신화순화순#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#2T/L GIS 정밀점검","2025-09-10 09:00","2025-09-12 18:00","취소","취소","연속"]
[600,"광주전남","광주","신화순화순#1 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#1T/L GIS 정밀점검","2025-09-15 09:00","2025-09-17 18:00","취소","취소","연속"]
[601,"광주전남","광주","화순승주#2 T/L","2024~2025년 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 피뢰기설치 작업구간 : 화순-승주#2T/L No.208~213","2025-09-09 07:00","2025-09-09 18:00","취소","취소","연속"]
[602,"광주전남","목포","목포북항#2 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-09-22 10:00","2025-09-22 18:00","취소","취소","연속"]
[603,"광주전남","목포","안좌신안그린 T/L CB","2024~2025년 목포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-09-25 10:00","2025-09-25 18:00","2025-09-25 10:00","2025-09-25 18:00","연속"]
[604,"광주전남","목포","화원안좌#2 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-09-24 10:00","2025-09-24 18:00","취소","취소","연속"]
[605,"광주전남","목포","화원안좌#1 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-09-23 10:00","2025-09-23 18:00","취소","취소","연속"]
[606,"광주전남","목포","엄다목포#1 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-09-30 10:00","2025-09-30 18:00","취소","취소","연속"]
[607,"광주전남","목포","나주엄다#1 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치(116기)","2025-09-08 08:00","2025-09-17 18:00","취소","취소","매일"]
[608,"광주전남","목포","나주엄다#1 T/L","나주엄다#1T/L 피뢰기 절연열화측정","나주엄다#1T/L 피뢰기 절연열화측정","2025-09-08 09:00","2025-09-08 14:00","취소","취소","연속"]
[609,"광주전남","목포","나주엄다#2 T/L","나주엄다#2T/L 피뢰기 절연열화측정","나주엄다#2T/L 피뢰기 절연열화측정","2025-09-08 14:00","2025-09-08 18:00","취소","취소","연속"]
[610,"광주전남","목포","엄다목포#2 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치 병가구간 휴전 및  엄다-목포T/L 피뢰기 설치","2025-09-15 08:00","2025-09-24 18:00","취소","취소","매일"]
[611,"광주전남","목포","엄다목포#2 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-09-26 10:00","2025-09-23 18:00","취소","취소","연속"]
[612,"광주전남","목포","엄다무안햇빛#2 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  엄다-무안햇빛T/L 고정형폴리머 점퍼지지애자 설치 3. 공사구간  엄다-무안햇빛#1 No.4~39(13기)","2025-09-25 07:30","2025-09-30 17:00","취소","취소","매일"]
[613,"광주전남","목포","엄다무안햇빛#1 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  엄다-무안햇빛T/L 고정형폴리머 점퍼지지애자 설치 3. 공사구간  엄다-무안햇빛#1 No.4~39(13기)","2025-09-22 07:30","2025-09-24 17:00","취소","취소","매일"]
[614,"광주전남","목포","장성영광#1 T/L","2024~2025년 목포전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-09-29 10:00","2025-09-29 18:00","취소","취소","연속"]
[615,"광주전남","목포","장성영광#1 T/L","2025년도 가공송전선로 순시점검 위탁공사","조류착지방지장치 설치","2025-09-02 09:00","2025-09-03 18:00","취소","취소","매일"]
[616,"광주전남","목포","장성영광#2 T/L","2025년도 가공송전선로 순시점검 위탁공사","조류착지방지장치 설치","2025-09-02 09:00","2025-09-03 18:00","취소","취소","매일"]
[617,"광주전남","목포","영광홍농 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  영광-홍농T/L 고정형폴리머점퍼지지애자 설치 3. 공사구간  영광-홍농 No.7~68(17기) ( 장성-영광T/L 병가구간 포함)","2025-09-22 07:30","2025-09-26 17:00","취소","취소","매일"]
[618,"광주전남","목포","고창홍농 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  고창-홍농T/L 고정형폴리머점퍼지지애자 설치 3. 공사구간  고창-홍농 No.42~66(6기)","2025-09-15 07:30","2025-09-17 17:00","취소","취소","매일"]
[619,"광주전남","순천","벌교고흥#1 T/L","24-25년 순천전력지사 변전협력회사 공사","벌교,고흥S/S 벌교-고흥#1T/L GIS 보통점검 및 벌교S/S 벌교-고흥#1T/L GIS 전자변대체","2025-09-01 09:00","2025-09-01 18:00","2025-09-01 09:00","2025-09-01 18:00","연속"]
[620,"광주전남","순천","벌교고흥#2 T/L","24-25년 순천전력지사 변전협력회사 공사","고흥S/S 벌교-고흥#2T/L GIS 보통점검 및 벌교S/S 벌교-고흥#2T/L GIS 전자변대체","2025-09-02 09:00","2025-09-02 18:00","2025-09-02 09:00","2025-09-02 18:00","연속"]
[621,"광주전남","순천","광양백운#2 T/L","SB댐퍼 설치(광양-백운T/L)","SB댐퍼 설치","2025-09-24 13:00","2025-09-24 18:00","2025-09-15 13:00","2025-09-15 18:00","연속"]
[622,"광주전남","순천","광양백운#1 T/L","SB댐퍼 설치(광양-백운T/L)","SB댐퍼 설치","2025-09-24 07:00","2025-09-24 13:00","2025-09-24 07:00","2025-09-24 13:00","연속"]
[623,"광주전남","순천","광양태금#1 T/L","광양-백운 #1T/L 및 광양-태금 #1T/L 정밀점검","○ 광양-백운 #1T/L 정밀점검 병가선로 요청 - 광양S/S ~ 백운S/S , 총 20기 - 주말작업 제외","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","매일"]
[624,"광주전남","순천","광양백운#1 T/L","광양-백운 #1T/L 정밀점검","○ 광양-백운 #1T/L 정밀점검 - 광양S/S ~ 백운S/S , 총 20기","2025-09-22 09:00","2025-09-24 18:00","2025-09-22 09:00","2025-09-24 18:00","매일"]
[625,"광주전남","순천","광양태금#2 T/L","광양-백운 #2T/L 및 광양-태금 #2T/L 정밀점검","○ 광양-백운 #2T/L 정밀점검 병가선로 휴전 ○ 광양-태금 #2T/L정밀점검 - 광양S/S ~ 백운S/S , 총 20기","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","매일"]
[626,"광주전남","순천","광양백운#2 T/L","광양-백운 #2T/L 정밀점검","○ 광양-백운 #2T/L 정밀점검 - 광양S/S ~ 백운S/S , 총 20기","2025-09-15 09:00","2025-09-17 18:00","2025-09-15 09:00","2025-09-17 18:00","매일"]
[627,"광주전남","순천","장흥벌교 T/L","24-25년 순천전력지사 변전협력회사 공사","벌교S/S 장흥-벌교T/L GIS 전자변대체","2025-09-03 09:00","2025-09-03 18:00","취소","취소","연속"]
[628,"광주전남","순천","보성벌교 T/L","24-25년 순천전력지사 변전협력회사 공사","벌교S/S 보성-벌교T/L GIS 전자변대체","2025-09-04 09:00","2025-09-04 18:00","2025-09-03 09:00","2025-09-03 18:00","연속"]
[629,"광주전남","순천","벌교고흥#1 T/L","피뢰기 설치(벌교-고흥#1T/L)","피뢰기 설치","2025-09-15 07:00","2025-09-16 18:00","취소","취소","매일"]
[630,"광주전남","순천","장흥벌교 T/L","피뢰기 설치(장흥-벌교T/L)","피뢰기 설치","2025-09-15 07:00","2025-09-16 18:00","취소","취소","매일"]
[631,"광주전남","순천","소라서순천#2 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 소라-서순천#2T/L GIS 정밀점검","2025-09-08 16:00","2025-09-09 10:00","2025-09-13 16:00","2025-09-14 10:00","연속"]
[632,"광주전남","순천","서순천벌교#2 T/L","피뢰기 설치(서순천-벌교#2T/L)","피뢰기 설치","2025-09-08 07:00","2025-09-12 18:00","취소","취소","매일"]
[633,"광주전남","순천","소라서순천#1 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 소라-서순천#1T/L GIS 정밀점검","2025-09-04 16:00","2025-09-05 10:00","2025-09-04 16:00","2025-09-05 10:00","연속"]
[634,"광주전남","순천","승주서순천 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 승주-서순천T/L GIS 정밀점검","2025-09-11 16:00","2025-09-12 10:00","2025-09-01 18:00","2025-09-02 10:00","연속"]
[635,"광주전남","순천","세풍율촌#2 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-09-24 14:00","2025-09-24 18:00","2025-09-24 14:00","2025-09-24 18:00","연속"]
[636,"광주전남","순천","황금세풍#1 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-09-23 14:00","2025-09-23 18:00","2025-09-23 14:00","2025-09-23 18:00","연속"]
[637,"광주전남","순천","세풍율촌#1 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-09-24 10:00","2025-09-24 14:00","2025-09-24 10:00","2025-09-24 14:00","연속"]
[638,"광주전남","순천","백운황금#2 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-09-23 10:00","2025-09-23 14:00","2025-09-23 10:00","2025-09-23 14:00","연속"]
[639,"광주전남","순천","여수소라#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수,소라S/S 여수-소라#2T/L GIS 조작시험","2025-09-09 09:00","2025-09-09 18:00","취소","취소","연속"]
[640,"광주전남","순천","여수소라#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여수,소라S/S 여수-소라#1T/L GIS 조작시험","2025-09-10 09:00","2025-09-10 18:00","취소","취소","연속"]
[641,"광주전남","순천","승주서순천 T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-서순천, 화순-승주2(통보분) 병가) ※휴일(20,21일) 미작업","2025-09-15 07:00","2025-09-26 18:00","취소","취소","매일"]
[642,"광주전남","순천","승주주암HP T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-주암HP, 화순-승주1(통보분) 병가) ※휴일(6,7일) 미작업","2025-09-01 07:00","2025-09-12 18:00","취소","취소","매일"]
[643,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체용 무부하가압","2025-09-17 17:00","2025-09-18 09:00","취소","취소","연속"]
[644,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-09-04 09:00","2025-09-26 18:00","취소","취소","연속"]
[645,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-09-04 09:00","2025-09-10 09:00","취소","취소","연속"]
[646,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-09-04 09:00","2025-09-26 18:00","취소","취소","연속"]
[647,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-09-04 09:00","2025-09-10 09:00","취소","취소","연속"]
[648,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-09-10 09:00","2025-09-18 09:00","취소","취소","연속"]
[649,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-09-10 09:00","2025-09-18 09:00","취소","취소","연속"]
[650,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-09-11 17:00","2025-09-11 21:00","2025-09-11 17:00","2025-09-11 21:00","연속"]
[651,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-09-12 17:00","2025-09-12 21:00","2025-09-12 17:00","2025-09-12 21:00","연속"]
[652,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체 무부하가압용","2025-09-17 17:00","2025-09-18 09:00","취소","취소","연속"]
[653,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-09-18 09:00","2025-09-26 09:00","취소","취소","연속"]
[654,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-09-18 09:00","2025-09-26 09:00","취소","취소","연속"]
[655,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-09-26 09:00","2025-09-26 18:00","취소","취소","연속"]
[656,"광주전남","순천","율촌여수산단#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수산단 율촌-여수산단#2T/L GIS 보통점검, 율촌S/S 율촌-여수산단#2T/L LA 보통점검","2025-09-05 09:00","2025-09-05 18:00","취소","취소","연속"]
[657,"광주전남","순천","여수TP화치#1 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","여수화력S/S 여수TP-화치#1T/L GIS 정밀점검","2025-09-29 09:00","2025-09-30 18:00","취소","취소","연속"]
[658,"광주전남","순천","호남TP여수TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (2호 : 여천-호남TP2, 호남TP-여수TP2 병가)","2025-09-22 07:00","2025-09-22 18:00","취소","취소","연속"]
[659,"광주전남","순천","여수TP용성#1 T/L","SB댐퍼 설치(여수TP-용성T/L)","SB댐퍼 설치","2025-09-22 07:00","2025-09-22 18:00","취소","취소","연속"]
[660,"광주전남","순천","여수TP화치#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP-화치#2T/L 보호배전반 대체","2025-09-22 09:00","2025-09-26 18:00","취소","취소","연속"]
[661,"광주전남","순천","여수TP용성#2 T/L","SB댐퍼 설치(여수TP-용성T/L)","SB댐퍼 설치","2025-09-23 07:00","2025-09-23 18:00","취소","취소","연속"]
[662,"광주전남","순천","호남TP여수TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (2호 : 여천-호남TP1, 호남TP-여수TP1 병가)","2025-09-05 07:00","2025-09-05 18:00","취소","취소","연속"]
[663,"광주전남","순천","여천호남TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP2, 여천-여수1 병가) (2호 : 여천-호남TP2, 호남TP-여수TP2 병가) ※휴일(20,21일) 미작업","2025-09-15 07:00","2025-09-26 18:00","취소","취소","매일"]
[664,"광주전남","순천","여천여수#1 T/L","여천S/S  GIS 기기기초공사","여천S/S  이하 GIS 교체공사 기기기초 터파기를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-09-08 10:00","2025-09-12 18:00","2025-09-08 10:00","2025-09-12 18:00","매일"]
[665,"광주전남","순천","여천여수#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP1, 여천-여수2 병가)","2025-09-08 07:00","2025-09-12 18:00","취소","취소","매일"]
[666,"광주전남","순천","여천호남TP#1 T/L","여천S/S  GIS 기기기초공사","여천S/S  이하 GIS 교체공사 기기기초 터파기를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-09-01 10:00","2025-09-05 18:00","취소","취소","매일"]
[667,"광주전남","순천","여천호남TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가) ※휴일(6,7일) 미작업","2025-09-01 07:00","2025-09-12 18:00","취소","취소","매일"]
[668,"광주전남","순천","여수TP여천#2 T/L","여천S/S  GIS 기기기초공사","여천S/S  이하 GIS 교체공사 기기기초 터파기를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-09-25 10:00","2025-09-30 18:00","2025-09-25 10:00","2025-09-30 18:00","매일"]
[669,"광주전남","순천","여수TP여천#1 T/L","여천S/S  GIS 기기기초공사","여천S/S  이하 GIS 교체공사 기기기초 터파기를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-09-22 10:00","2025-09-24 18:00","2025-09-22 10:00","2025-09-24 18:00","매일"]
[670,"광주전남","순천","여천여수#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (여천-호남TP2, 여천-여수1 병가) ※휴일(20,21일) 미작업","2025-09-15 07:00","2025-09-19 18:00","취소","취소","매일"]
[671,"광주전남","순천","여천여수#2 T/L","여천S/S  GIS 기기기초공사","여천S/S  이하 GIS 교체공사 기기기초 터파기를 위한 안전이격 휴전 신청 매일휴전 / 즉시가압 가능 조건임","2025-09-15 10:00","2025-09-19 18:00","2025-09-15 10:00","2025-09-19 18:00","매일"]
[672,"광주전남","순천","여수TP용성#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP,용성S/S 여수TP-용성#2T/L GIS 보통점검","2025-09-12 09:00","2025-09-12 18:00","취소","취소","연속"]
[673,"광주전남","순천","여수TP용성#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP,용성S/S 여수TP-용성#1T/L GIS 보통점검","2025-09-11 09:00","2025-09-11 18:00","취소","취소","연속"]
[674,"광주전남","순천","용성여수산단#2 T/L"," 용성-여수산단T/L 폴리머점퍼지지애자 설치공사","용성-여수산단#2T/L 폴리머점퍼지지애자 설치","2025-09-29 07:00","2025-09-30 18:00","2025-09-25 07:00","2025-09-26 18:00","매일"]
[675,"광주전남","순천","율촌여수산단#1 T/L","율촌-여수산단#1 T/L 정밀점검","율촌-여수산단#1 T/L 정밀점검 총 51기","2025-09-08 09:00","2025-09-12 18:00","취소","취소","매일"]
[676,"광주전남","순천","율촌화치#2 T/L","율촌-여수산단#1 T/L 정밀점검","율촌-여수산단#1 T/L 정밀점검 총 51기 - 병가선로 휴전신청","2025-09-08 09:00","2025-09-12 18:00","취소","취소","매일"]
[677,"광주전남","순천","율촌여수산단#2 T/L","율촌-여수산단#2 T/L 정밀점검","율촌-여수산단#2 T/L 정밀점검 총 51기","2025-09-01 09:00","2025-09-05 18:00","취소","취소","매일"]
[678,"광주전남","순천","율촌화치#1 T/L","율촌-여수산단#2 T/L 정밀점검","율촌-여수산단#2 T/L 정밀점검 총 51기 - 병가선로 휴전신청","2025-09-01 09:00","2025-09-05 18:00","취소","취소","매일"]
[679,"광주전남","순천","광양태금#1 T/L","24-25년 순천전력지사 변전협력회사 공사","태금S/S 광양-태금#1T/L GIS 조작시험","2025-09-08 09:00","2025-09-08 18:00","취소","취소","연속"]
[680,"광주전남","순천","율촌화치#2 T/L","24-25년 순천전력지사 변전협력회사 공사","화치S/S 율촌-화치#2T/L GIS 조작시험","2025-09-17 09:00","2025-09-17 18:00","취소","취소","연속"]
[681,"광주전남","순천","율촌화치#1 T/L","24-25년 순천전력지사 변전협력회사 공사","화치S/S 율촌-화치#1T/L GIS 조작시험","2025-09-16 09:00","2025-09-16 18:00","취소","취소","연속"]
[682,"광주전남","직할","나주금천#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 나주-금천#2T/L 0.01호","2025-09-03 14:00","2025-09-03 18:00","취소","취소","연속"]
[683,"광주전남","직할","매월화정#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2025-09-17 09:00","2025-09-18 18:00","취소","취소","연속"]
[684,"광주전남","직할","매월화정#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2025-09-15 09:00","2025-09-16 18:00","취소","취소","연속"]
[685,"광주전남","직할","비아하남#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 애자련 보강 작업구간 : 하남-장성#1T/L 2호(비아-하남#1T/L 73호(병가철탑))","2025-09-05 07:00","2025-09-05 18:00","2025-09-05 07:00","2025-09-05 18:00","연속"]
[686,"광주전남","직할","일곡비아#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검 및 상부모선 가스 누기개소 조치","2025-09-22 09:00","2025-09-26 18:00","취소","취소","연속"]
[687,"광주전남","직할","왕곡나주#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 왕곡-나주#2T/L 20.99호","2025-09-03 10:00","2025-09-03 13:00","취소","취소","연속"]
[688,"광주전남","직할","왕곡나주#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 왕곡-나주#1T/L 20.99호","2025-09-03 07:00","2025-09-03 10:00","취소","취소","연속"]
[689,"광주전남","직할","비아하남#1 T/L","2024 ~ 2025년 광주전남본부 직할 변전협력회사 공사","CVT 하자, LA 초기(1차 A,B,C) 점검","2025-09-12 09:00","2025-09-12 18:00","취소","취소","연속"]
[690,"광주전남","직할","하남장성#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2025-09-29 09:00","2025-09-29 18:00","취소","취소","연속"]
[691,"광주전남","직할","하남장성#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2025-09-30 09:00","2025-09-30 18:00","2025-09-30 09:00","2025-09-30 18:00","연속"]
[692,"광주전남","직할","하남장성#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 애자련 보강 작업구간 : 하남-장성#1T/L 2호(비아-하남#1T/L 73호(병가철탑))","2025-09-05 07:00","2025-09-05 18:00","2025-09-05 07:00","2025-09-05 18:00","연속"]
[693,"대구","경산","진량노변 T/L","2024-2025년 경산전력지사 송전협력회사 공사"," 진량-노변T/L SB댐퍼 설치","2025-09-23 07:00","2025-09-23 18:00","2025-09-23 07:00","2025-09-23 18:00","연속"]
[694,"대구","경산","신경산진량 T/L","2024-2025년 경산전력지사 송전협력회사 공사"," 신경산-진량T/L 고정형폴리머 및 SB댐퍼 설치","2025-09-24 07:00","2025-09-24 18:00","2025-09-24 07:00","2025-09-24 18:00","연속"]
[695,"대구","달성","논공현풍#1 T/L","24~25년 달성전력지사 가공송전 협력회사 공사","[24~25년 달성전력지사 가공송전 협력회사 공사]  논공-현풍 #1 9.17(수)~18(목)(2일) 금구류 교체공사(1~6호)","2025-09-17 08:00","2025-09-18 18:00","2025-09-10 08:00","2025-09-11 18:00","연속"]
[696,"대구","달성","고령논공#2 T/L","24~25년 달성전력지사 가공송전 협력회사 공사","[24~25년 달성전력지사 가공송전 협력회사 공사]  고령-논공 #2 9.26(금) 14:00~16:00 압축인류클램프 부풀음 보수(고령-논공#2 ST)","2025-09-26 14:00","2025-09-26 16:00","2025-09-05 14:00","2025-09-05 16:00","연속"]
[697,"대구","달성","논공달성#1 T/L","24~25년 달성전력지사 가공송전 협력회사 공사","[24~25년 달성전력지사 가공송전 협력회사 공사]  논공-달성#1 T/L 9.26(금) 12:00~14:00 압축인류클램프 부풀음 보수(논공-달성#1 ST)","2025-09-26 12:00","2025-09-26 14:00","2025-09-05 12:00","2025-09-05 14:00","연속"]
[698,"대구","달성","논공달성#2 T/L","24~25년 달성전력지사 가공송전 협력회사 공사","[24~25년 달성전력지사 가공송전 협력회사 공사]  논공-달성 #2 9.26(금) 10:00~12:00 압축인류클램프 부풀음 보수(논공-달성#2 ST)","2025-09-26 10:00","2025-09-26 12:00","2025-09-05 10:00","2025-09-05 12:00","연속"]
[699,"대구","달성","논공현풍#2 T/L","24~25년 달성전력지사 가공송전 협력회사 공사","[24~25년 달성전력지사 가공송전 협력회사 공사]  논공-현풍 #2 1)9.24(수)~25(목)(2일) 금구류 교체공사(1~6호) 2)9.26(금) ~10:00 압축인류클램프 부풀음 보수(논공-현풍#2 ST)","2025-09-24 08:00","2025-09-26 10:00","2025-09-03 08:00","2025-09-05 10:00","연속"]
[700,"대구","달성","다사달서 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사(안전확보)"," 왜관-다사 #1T/L 정밀점검 관련 안전확보","2025-09-24 06:00","2025-09-25 18:00","취소","취소","연속"]
[701,"대구","달성","강창다사 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사(안전확보)"," 왜관-다사 #2T/L 정밀점검 관련 안전확보","2025-09-17 06:00","2025-09-18 18:00","취소","취소","연속"]
[702,"대구","달성","왜관다사#1 T/L","345kV 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 왜관-다사#1/L 피뢰기 및 조류착지방지장치 설치","2025-09-03 09:00","2025-09-03 18:00","2025-09-03 09:00","2025-09-03 18:00","연속"]
[703,"대구","달성","대구자인#2 T/L","[TEST] 대구S/S #60-65 BUS TIE 정밀점검 무부하가압","[TEST] 대구S/S #60-65 BUS TIE 정밀점검 무부하가압","2025-09-02 17:00","2025-09-02 18:00","2025-09-02 17:00","2025-09-02 18:00","연속"]
[704,"대구","달성","대구청도#2 T/L","[TEST] 대구S/S #61-66 BUS TIE 정밀점검 무부하가압","[TEST] 대구S/S #61-66 BUS TIE 정밀점검 무부하가압","2025-09-04 17:00","2025-09-04 18:00","2025-09-04 17:00","2025-09-04 18:00","연속"]
[705,"대구","달성","상인봉덕#1 T/L","봉덕S/S #4M.Tr 증설 관련 M.Tr 무부하가압","봉덕S/S #4M.Tr 증설 관련 M.Tr 무부하가압","2025-09-25 16:00","2025-09-26 18:00","2025-09-25 16:00","2025-09-26 18:00","연속"]
[706,"대구","달성","상인봉덕#1 T/L","봉덕S/S #4M.Tr 증설 관련 GIS 무부하가압","봉덕S/S #4M.Tr 증설 관련 GIS 무부하가압","2025-09-11 16:00","2025-09-12 18:00","2025-09-11 16:00","2025-09-12 18:00","연속"]
[707,"대구","달성","상인봉덕#2 T/L","봉덕S/S #4M.Tr 증설 관련 GIS 무부하가압","봉덕S/S #4M.Tr 증설 관련 GIS 무부하가압","2025-09-16 16:00","2025-09-17 18:00","2025-09-16 16:00","2025-09-17 18:00","연속"]
[708,"대구","달성","상인봉덕#2 T/L","345kV 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 상인-봉덕#2T/L 피뢰기 및 조류착지방지장치 설치","2025-09-03 07:00","2025-09-05 18:00","2025-09-03 07:00","2025-09-05 18:00","연속"]
[709,"대구","달성","강창성서#1 T/L","[TEST] 성서S/S #3M.Tr GIS 정밀점검 무부하가압","[TEST] 성서S/S #3M.Tr GIS 정밀점검 무부하가압","2025-09-09 17:00","2025-09-09 18:00","2025-09-09 17:00","2025-09-09 18:00","연속"]
[710,"대구","직할","효목안심#1 T/L","효목S/S 효목-안심#1T/L 차단기 동작시간 측정","효목S/S 효목-안심#1T/L 차단기 동작시간 측정(공압식)","2025-09-18 09:00","2025-09-18 14:00","2025-09-18 09:00","2025-09-18 14:00","연속"]
[711,"대구","직할","효목안심#2 T/L","효목S/S 효목-안심#2T/L 차단기 동작시간 측정","효목S/S 효목-안심#2T/L 차단기 동작시간 측정(공압식)","2025-09-18 14:00","2025-09-18 18:00","2025-09-18 14:00","2025-09-18 18:00","연속"]
[712,"대구","칠곡","어모김천#1 T/L"," 김천S/S 현대화공사","○  김천-금릉#2/L GIS PD발생관련 현장확인","2025-09-18 09:00","2025-09-18 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[713,"대구","칠곡","김천금릉#2 T/L","(안전확보)신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 성주-금릉#1T/L 수평 추락방지장치 설치공사 안전확보차 - 서대구-성주No.101~102 병가","2025-09-24 07:00","2025-09-25 18:00","2025-09-11 07:00","2025-09-12 18:00","연속"]
[714,"대구","칠곡","김천금릉#1 T/L","(안전확보)신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 성주-금릉#1T/L 수평 추락방지장치 설치공사 안전확보차 - 서대구-성주No.101~102 병가","2025-09-11 07:00","2025-09-12 18:00","2025-09-24 07:00","2025-09-25 18:00","연속"]
[715,"대구","칠곡","서대구남구미#2 T/L","남구미S/S  장기사용 #1,2M.Tr 교체공사","#1M.Tr 1차측 모선 설치 안전이격확보","2025-09-15 09:00","2025-09-16 18:00","2025-09-15 09:00","2025-09-16 18:00","연속"]
[716,"대구","칠곡","남구미농소#1 T/L","(안전확보)신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 농소-김천#1T/L 수평 추락방지장치 설치공사 안전확보차 - 농소-김천#1T/L No.2 병가선로","2025-09-30 07:00","2025-09-30 18:00","2025-09-30 07:00","2025-09-30 18:00","연속"]
[717,"대구","칠곡","서대구남구미#2 T/L","남구미S/S  장기사용 #1,2M.Tr 교체공사","#1M.Tr 무부하 가압","2025-09-26 16:00","2025-09-27 16:00","2025-09-26 16:00","2025-09-27 16:00","연속"]
[718,"대구","칠곡","남구미농소#2 T/L","(안전확보)신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 농소-김천#1T/L 수평 추락방지장치 설치공사 안전확보차 - 농소-김천#1T/L No.2 병가선로","2025-09-29 07:00","2025-09-29 18:00","2025-09-29 07:00","2025-09-29 18:00","연속"]
[719,"대구","칠곡","서대구남구미#2 T/L","남구미S/S  장기사용 #1,2M.Tr 교체공사","#1M.Tr 1차측 모선 임시철거 안전이격확보","2025-09-01 09:00","2025-09-02 18:00","2025-09-01 09:00","2025-09-02 18:00","연속"]
[720,"대구","칠곡","농소김천#1 T/L","신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 농소-김천#1T/L 수평 추락방지장치 설치공사 안전확보차","2025-09-29 07:00","2025-09-29 18:00","2025-09-29 07:00","2025-09-29 18:00","연속"]
[721,"대구","칠곡","농소김천#2 T/L","농소S/S  627 GIS 정밀점검공사","농소S/S  627 GIS 정밀점검공사","2025-09-30 09:00","2025-10-02 18:00","2025-09-30 09:00","2025-10-02 18:00","연속"]
[722,"대구","칠곡","북대구왜관#1 T/L","24~25년 칠곡전력지사 변전협력회사 공사"," GIS 보통점검","2025-09-22 09:30","2025-09-22 18:00","2025-09-22 09:30","2025-09-22 18:00","연속"]
[723,"대구","칠곡","서대구성주#2 T/L","(안전확보)신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 성주-금릉#2T/L 수평 추락방지장치 설치공사 안전확보차 - 서대구-성주No.2 병가","2025-09-15 07:00","2025-09-15 18:00","2025-09-03 07:00","2025-09-03 18:00","연속"]
[724,"대구","칠곡","서대구성주#1 T/L","(안전확보)신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 성주-금릉#1T/L 수평 추락방지장치 설치공사 안전확보차 - 서대구-성주No.2 병가","2025-09-02 07:00","2025-09-02 18:00","2025-09-17 07:00","2025-09-19 18:00","연속"]
[725,"대구","칠곡","성주금릉#1 T/L","신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 성주-금릉#1T/L 수평 추락방지장치 설치공사","2025-09-02 07:00","2025-09-12 18:00","2025-09-15 07:00","2025-09-25 18:00","연속"]
[726,"대구","칠곡","성주금릉#2 T/L","신옥천-북경남 등 8개T/L 수평 추락방지장치 설치공사"," 성주-금릉#2T/L 수평 추락방지장치 설치공사","2025-09-15 07:00","2025-09-25 18:00","2025-09-02 07:00","2025-09-12 18:00","연속"]
[727,"대구","칠곡","고아어모#1 T/L"," 고아-어모T/L No.64 안전이격확보공사"," 고아-어모T/L No.64 본선로 구성에 따른 전선 공중이동","2025-09-25 07:00","2025-09-29 18:00","취소","취소","연속"]
[728,"대구","칠곡","고아어모#2 T/L"," 고아-어모T/L No.64 안전이격확보공사"," 고아-어모T/L No.64 본선로 구성에 따른 전선 공중이동","2025-09-30 07:00","2025-10-02 18:00","취소","취소","연속"]
[729,"대구","칠곡","고아어모#2 T/L","어모S/S  677 GIS 정밀점검공사","어모S/S  677 GIS 정밀점검공사","2025-09-03 13:00","2025-09-05 18:00","2025-09-03 13:00","2025-09-05 18:00","연속"]
[730,"대구","칠곡","어모김천#2 T/L","어모S/S  677 GIS 정밀점검공사(무부하가압)","어모S/S  677 GIS 정밀점검공사(무부하가압)","2025-09-05 14:00","2025-09-05 18:00","취소","취소","연속"]
[731,"대구","칠곡","북대구왜관#2 T/L","345kV 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 왜관-다사#1/L 피뢰기 및 조류착지방지장치 설치 - 작업자 안전확보 휴전","2025-09-03 14:00","2025-09-03 18:00","2025-09-03 14:00","2025-09-03 18:00","연속"]
[732,"대구","포항","아화건천#1 T/L","2024-2025년 경산전력지사 송전협력회사 공사"," 아화-건천#1T/L No.4, 12, 14 고정형폴리머 설치","2025-09-06 07:00","2025-09-06 18:00","2025-09-06 07:00","2025-09-06 18:00","연속"]
[733,"대구","포항","아화건천#2 T/L","2024-2025년 경산전력지사 송전협력회사 공사"," 아화-건천#2T/L No.16, 29 고정형폴리머 설치","2025-09-13 07:00","2025-09-13 18:00","2025-09-07 07:00","2025-09-0718:00","연속"]
[734,"대구","포항","울주외동#2 T/L","2024~25년 포항전력지사 변전협력회사 공사","외동S/S 627 GIS 및 LA 보통점검","2025-09-30 09:00","2025-09-30 14:00","2025-09-30 09:00","2025-09-30 14:00","연속"]
[735,"대구","포항","옥동외동#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","외동S/S 657 GIS, LA 보통점검","2025-09-30 14:00","2025-09-30 18:00","2025-09-30 14:00","2025-09-30 18:00","연속"]
[736,"대구","포항","울주입실#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","모선보호반 대체","2025-09-19 15:00","2025-09-19 16:00","2025-09-19 15:00","2025-09-19 16:00","연속"]
[737,"대구","포항","울주입실#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","모선보호반 대체","2025-09-19 13:00","2025-09-19 14:00","2025-09-19 13:00","2025-09-19 14:00","연속"]
[738,"대구","포항","울주입실#1 T/L"," 신영일-천북 등 19개 T/L 추락방지장치 설치공사","345kV 울주-월성NP#1T/L 추락방지장치 설치[안전확보]","2025-09-26 07:00","2025-09-30 18:00","2025-09-28 07:00","2025-09-30 18:00","연속"]
[739,"대구","포항","영일입실 T/L"," 신영일-천북 등 19개 T/L 추락방지장치 설치공사","345kV 울주-월성NP#1T/L 추락방지장치 설치[안전확보]","2025-09-22 07:00","2025-09-28 18:00","2025-09-22 07:00","2025-09-26 18:00","연속"]
[740,"대구","포항","서포항흥해#1 T/L"," 영일-입실 등 11개 T/L 피뢰기 설치공사"," 서포항-흥해#1T/L 피뢰기 설치공사","2025-09-29 09:00","2025-09-30 18:00","2025-09-29 09:00","2025-09-30 18:00","연속"]
[741,"대구","포항","흥해북포항#2 T/L"," 영일-입실 등 11개 T/L 피뢰기 설치공사"," 흥해-북포항#2T/L 피뢰기 설치공사","2025-09-29 09:00","2025-09-30 18:00","2025-09-29 09:00","2025-09-30 18:00","연속"]
[742,"경북","구미","동상주점촌#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 동상주-점촌T/L 관형지지물 수직/수평 레일 설치공사 (No.8,12,67)","2025-09-05 13:00","2025-09-05 18:00","취소","취소","연속"]
[743,"경북","구미","동상주점촌#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 동상주-점촌T/L 관형지지물 수직/수평 레일 설치공사 (No.8,12,67)","2025-09-05 07:00","2025-09-05 13:00","취소","취소","연속"]
[744,"경북","구미","청리상주#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 청리-상주T/L 관형지지물 수직/수평 레일 설치공사 No.58, 84","2025-09-25 13:00","2025-09-25 18:00","취소","취소","연속"]
[745,"경북","구미","청리상주#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 청리-상주T/L 관형지지물 수직/수평 레일 설치공사 No.58, 84","2025-09-25 07:00","2025-09-25 13:00","취소","취소","연속"]
[746,"경북","영주","점촌문경 T/L","문경S/S  #3M.Tr 부싱 교체","문경S/S  #3M.Tr 부싱 교체 후 무부하가압","2025-09-12 09:00","2025-09-12 18:00","2025-09-12 09:00","2025-09-12 18:00","연속"]
[747,"경북","영주","점촌문경 T/L","2025년 가공송전 순시점검 위탁공사(영주)"," 점촌-문경T/L 정밀점검 -  점촌-문경T/L No.111-156 ※ 점촌-문경T/L No.124-No.156이 예천-점촌 No.72-104 #2T/L 병가","2025-09-08 08:00","2025-09-14 18:00","2025-09-08 08:00","2025-09-14 18:00","매일"]
[748,"경북","영주","문경단양 T/L","2025년 영주전력지사  GIS 정밀점검공사","GIS 정밀점검 후 무부하가압","2025-09-27 09:00","2025-09-27 18:00","2025-09-27 09:00","2025-09-27 18:00","연속"]
[749,"경북","영주","봉화현종산풍력 T/L"," 봉화S/S 리모델링 공사","○ 외벽 마감재 교체(드라이비트 -> AL복합판넬, 화강석, 징크판넬)","2025-09-02 08:00","2025-09-12 17:00","2025-09-02 08:00","2025-09-12 17:00","연속"]
[750,"경북","영주","봉화울진 T/L"," 봉화S/S 리모델링 공사","○ 외벽 마감재 교체(드라이비트 -> AL복합판넬, 화강석, 징크판넬)","2025-09-02 08:00","2025-09-26 17:00","2025-09-02 08:00","2025-09-26 17:00","연속"]
[751,"경북","영주","봉화S/S 춘양전철#1T/L CB"," 봉화S/S 리모델링 공사","○ 외벽 마감재 교체(드라이비트 -> AL복합판넬, 화강석, 징크판넬)","2025-09-15 08:00","2025-09-26 17:00","2025-09-15 08:00","2025-09-26 17:00","연속"]
[752,"경북","영주","신영주영주#2 T/L","2024-25년 영주전력지사 변전협력회사 공사","피뢰기 하자점검","2025-09-26 13:00","2025-09-26 18:00","취소","취소","연속"]
[753,"경북","영주","신영주영주#1 T/L","2024-25년 영주전력지사 변전협력회사 공사","피뢰기 하자점검","2025-09-26 09:00","2025-09-26 13:00","취소","취소","연속"]
[754,"경북","영주","점촌단양 T/L","2025년 가공송전 순시점검 위탁공사(영주)"," 점촌-단양T/L 정밀점검 -  점촌-단양T/L No.48-156 ※ 점촌-단양T/L No.124-No.156이 예천-점촌 No.72-104 #1T/L 병가","2025-09-01 08:00","2025-09-07 18:00","취소","취소","매일"]
[755,"경북","영주","점촌단양 T/L","2024-2025년 영주전력지사 변전협력회사 총액공사","점촌-단양T/L GIS 조작시험","2025-09-20 10:00","2025-09-20 18:00","2025-09-20 10:00","2025-09-20 18:00","연속"]
[756,"경북","영주","예천점촌#1 T/L","2025년 가공송전 순시점검 위탁공사(영주)"," 점촌-단양T/L 정밀점검 -  점촌-단양T/L No.48-156 ※ 점촌-단양T/L No.124-No.156이 예천-점촌 No.72-104 #1T/L 병가","2025-09-01 08:00","2025-09-03 18:00","취소","취소","매일"]
[757,"경북","영주","예천점촌#2 T/L","2025년 가공송전 순시점검 위탁공사(영주)"," 점촌-문경T/L 정밀점검 -  점촌-문경T/L No.111-156 ※ 점촌-문경T/L No.124-No.156이 예천-점촌 No.72-104 #2T/L 병가","2025-09-08 08:00","2025-09-10 18:00","2025-09-08 08:00","2025-09-10 18:00","매일"]
[758,"경북","직할","안동풍산 T/L","24-25년 경북직할 송전협력회사 공사","수평 추락방지장치 설치공사","2025-09-02 07:00","2025-09-08 18:00","취소","취소","연속"]
[759,"경북","직할","안동안동HP T/L","안동S/S #4M.Tr 증설 및 모선보강사업"," GIS 설치","2025-09-19 09:00","2025-09-26 18:00","2025-09-19 09:00","2025-09-26 18:00","연속"]
[760,"경북","직할","신영주안동#1 T/L","안동S/S #4M.Tr 증설 및 모선보강사업"," GIS 설치","2025-09-30 15:00","2025-10-01 15:00","2025-09-30 15:00","2025-10-01 15:00","연속"]
[761,"경북","직할","신영주안동#1 T/L","안동S/S #4M.Tr 증설 및 모선보강사업"," GIS 설치","2025-09-22 16:00","2025-09-23 16:00","2025-09-22 16:00","2025-09-23 16:00","연속"]
[762,"경북","직할","신영주안동#1 T/L","안동S/S #4M.Tr 증설 및 모선보강사업"," GIS 설치","2025-09-25 12:00","2025-09-26 12:00","2025-09-25 12:00","2025-09-26 12:00","연속"]
[763,"경북","직할","의성풍백풍력 T/L CB ","`24~25년 경북본부 직할 변전협력회사 공사","GIS 초기점검","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[764,"경북","직할","영덕진보#1 T/L"," 24-25년 경북 직할 송전협력회사 공사"," 24-25년 경북 직할 송전협력회사 공사","2025-09-17 07:00","2025-09-17 12:00","2025-09-17 07:00","2025-09-17 12:00","연속"]
[765,"경북","직할","영덕진보#2 T/L"," 24-25년 경북 직할 송전협력회사 공사"," 24-25년 경북 직할 송전협력회사 공사","2025-09-17 12:00","2025-09-17 18:00","2025-09-17 12:00","2025-09-17 18:00","연속"]
[766,"경북","직할","울진현종산풍력 T/L"," 24-25년 경북 직할 송전협력회사 공사"," 24-25년 경북 직할 송전협력회사 공사","2025-09-01 07:00","2025-09-01 12:00","2025-09-01 07:00","2025-09-01 12:00","연속"]
[767,"경북","직할","현종산풍력평해#2 T/L"," 24-25년 경북 직할 송전협력회사 공사"," 24-25년 경북 직할 송전협력회사 공사","2025-09-01 07:00","2025-09-01 18:00","2025-09-01 07:00","2025-09-01 18:00","연속"]
[768,"부산울산","동부산","명례고리NP T/L","345kV 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치","2025-09-22 07:00","2025-09-22 18:00","2025-09-22 07:00","2025-09-22 18:00","연속"]
[769,"부산울산","동부산","명례장안 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 및 금구류 설치","2025-09-22 07:00","2025-09-23 18:00","2025-09-22 07:00","2025-09-23 18:00","연속"]
[770,"부산울산","동부산","구서명장#2 T/L","명장S/S  GIS 교체공사","구서-명장#2T/L, #3M.Tr 1차 GIS 교체","2025-09-01 09:00","2025-09-26 18:00","2025-09-01 09:00","2025-09-26 18:00","연속"]
[771,"부산울산","동부산","서창산막#2 T/L","서창S/S 687GIS 보통점검","서창S/S 687GIS 보통점검","2025-09-20 14:00","2025-09-20 18:00","2025-09-20 14:00","2025-09-20 18:00","연속"]
[772,"부산울산","동부산","서창산막#1 T/L","서창S/S 667GIS 차단기 동작시험","서창S/S 667GIS 차단기 동작시험","2025-09-20 09:30","2025-09-20 14:00","2025-09-20 09:30","2025-09-20 14:00","연속"]
[773,"부산울산","동부산","시랑좌동#2 T/L","동부산전력 가공송전협력회사 공사","철탑 금구 설치","2025-09-16 07:00","2025-09-16 18:00","취소","취소","연속"]
[774,"부산울산","동부산","신양산시랑#2 T/L","동부산전력 가공송전협력회사 공사","철탑 금구 설치","2025-09-17 07:00","2025-09-17 18:00","취소","취소","연속"]
[775,"부산울산","동부산","신양산구서#1 T/L","동부산전력 가공송전협력회사 공사","애자 설치","2025-09-18 07:00","2025-09-18 18:00","취소","취소","연속"]
[776,"부산울산","동부산","신양산수영#1 T/L","동부산전력 가공송전협력회사 공사","애자 설치","2025-09-24 07:00","2025-09-26 18:00","취소","취소","연속"]
[777,"부산울산","동부산","신양산구서#2 T/L","동부산전력 가공송전협력회사 공사","애자 설치","2025-09-24 07:00","2025-09-26 18:00","취소","취소","연속"]
[778,"부산울산","동부산","우동대연 T/L","2025년 서부산전력지사 가공송전 순시점검 위탁공사","정보T/L 송전선로 정밀점검, 조류착지방지장치 설치","2025-09-21 08:00","2025-09-21 18:00","취소","취소","연속"]
[779,"부산울산","동부산","장안고리NP T/L","345kV 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치","2025-09-30 07:00","2025-09-30 18:00","2025-09-30 07:00","2025-09-30 18:00","연속"]
[780,"부산울산","동부산","명례장안 T/L","장안S/S  기장연구로 신규수용공사","시험가압선로","2025-09-01 14:00","2025-09-02 18:00","2025-09-24 15:00","2025-09-25 18:00","연속"]
[781,"부산울산","동부산","수영정보#1 T/L","정보S/S 627 GIS 차단기 동작시험","정보S/S 627 GIS 차단기 동작시험","2025-09-28 09:00","2025-09-28 15:00","2025-09-28 09:00","2025-09-28 15:00","연속"]
[782,"부산울산","동부산","정보대연 T/L","2025년 서부산전력지사 가공송전 순시점검 위탁공사","정보T/L 송전선로 정밀점검, 조류착지방지장치 설치","2025-09-20 08:00","2025-09-20 18:00","취소","취소","연속"]
[783,"부산울산","동부산","수영정보#2 T/L","정보S/S 637 GIS 보통점검","정보S/S 637 GIS 보통점검","2025-09-27 09:00","2025-09-27 15:00","2025-09-27 09:00","2025-09-27 15:00","연속"]
[784,"부산울산","동부산","좌동S/S SEC CB 65660","좌동S/S #60-65 모선보호반 설치","좌동S/S #60-65 모선보호반 설치","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[785,"부산울산","동부산","좌동S/S CB 6200","좌동S/S #61-66 모선보호반 설치","좌동S/S #61-66 모선보호반 설치","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[786,"부산울산","동부산","좌동S/S SEC CB 65660","좌동S/S #61-66 모선보호반 설치","좌동S/S #61-66 모선보호반 설치","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[787,"부산울산","동부산","좌동S/S SEC CB 60610","좌동S/S #61-66 모선보호반 설치","좌동S/S #61-66 모선보호반 설치","2025-09-22 09:00","2025-09-26 18:00","2025-09-22 09:00","2025-09-26 18:00","연속"]
[788,"부산울산","동부산","좌동S/S SEC CB 60610","좌동S/S #60-65 모선보호반 설치","좌동S/S #60-65 모선보호반 설치","2025-09-15 09:00","2025-09-19 18:00","2025-09-15 09:00","2025-09-19 18:00","연속"]
[789,"부산울산","북부산","북부산미남#2 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 미남-덕포#2T/L 송전용피뢰기 설치(No.1~10) 하단  북부산-미남#2T/L 안전이격","2025-09-22 08:00","2025-09-22 12:00","2025-09-22 08:00","2025-09-22 12:00","연속"]
[790,"부산울산","북부산","서창산막#1 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 서창-산막#1T/L 송전용피뢰기 설치 : No.25~44","2025-09-06 08:00","2025-09-07 18:00","2025-09-06 08:00","2025-09-07 18:00","연속"]
[791,"부산울산","북부산","서창산막#2 T/L","산막S/S  장기사용 GIS 대체공사","산막S/S  석계-산막#2T/L GIS 대체 -시험가압선로","2025-09-15 18:00","2025-09-16 18:00","2025-09-15 18:00","2025-09-16 18:00","연속"]
[792,"부산울산","북부산","서창산막#2 T/L","산막S/S  장기사용 GIS 대체공사","산막S/S  석계-산막#2T/L GIS 대체 -시험가압선로","2025-09-10 17:00","2025-09-10 18:00","2025-09-10 17:00","2025-09-10 18:00","연속"]
[793,"부산울산","북부산","석계산막#2 T/L","산막S/S  장기사용 GIS 대체공사","산막S/S  석계-산막#2T/L GIS 대체","2025-09-09 09:00","2025-09-23 18:00","2025-09-09 09:00","2025-09-23 18:00","연속"]
[794,"부산울산","북부산","물금삼랑진PP#2 T/L","25년 북부산전력지사  GIS 정밀점검","삼랑진S/Y #2M.Tr 1차 GIS 시험가압(즉시가압가능)","2025-09-08 17:00","2025-09-08 18:00","2025-09-08 17:00","2025-09-08 18:00","연속"]
[795,"부산울산","북부산","석계산막#1 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 석계-산막#1T/L 송전용피뢰기 설치 : No.6~29","2025-09-29 08:00","2025-09-30 18:00","2025-09-29 08:00","2025-09-30 18:00","연속"]
[796,"부산울산","북부산","북부산양산 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S 60-61-0B/S 시험가압선로(즉시가압가능)","2025-09-05 17:00","2025-09-05 18:00","2025-09-05 17:00","2025-09-05 18:00","연속"]
[797,"부산울산","북부산","북부산양산 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S 65-66-0B/S 시험가압선로(즉시가압가능)","2025-09-02 17:00","2025-09-02 18:00","2025-09-02 17:00","2025-09-02 18:00","연속"]
[798,"부산울산","북부산","양산산막#1 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S #1M.Tr 1차 GIS 정밀점검 관련 시험가압선로","2025-09-30 17:00","2025-09-30 18:00","취소","취소","연속"]
[799,"부산울산","북부산","양산산막#1 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S #6100 GIS 시험가압(즉시가압가능)","2025-09-24 17:00","2025-09-24 18:00","2025-09-24 17:00","2025-09-24 18:00","연속"]
[800,"부산울산","북부산","양산삼랑진PP T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S ,삼랑진S/Y 양산-삼랑진PPT/L GIS 정밀점검","2025-09-25 09:00","2025-09-28 18:00","2025-09-25 09:00","2025-09-28 18:00","연속"]
[801,"부산울산","서부산","서부산다대#1 T/L","다대S/S  장기사용 GIS 대체공사","다대S/S  장기사용 GIS 대체공사","2025-09-08 09:00","2025-12-12 18:00","2025-09-08 09:00","2025-12-12 18:00","연속"]
[802,"부산울산","서부산","서부산다대#2 T/L"," 서부산-다대T/L OF케이블 선종교체공사"," 서부산-다대T/L OF케이블 선종교체공사 보완사항 조치 조치내용 : 전력구 본선구간 中 상습 침수구간 행거 교체 및 케이블 설치높이 상향 공사개요(기완료) 교체선종 :  OF 2,000㎟ →  XLPE 1,200㎟ 회선수 및 길이 : 2회선 - 0.7km 공사구간 : 다대S/S EBG ~J/B#10","2025-09-02 09:00","2025-09-03 18:00","2025-09-02 09:00","2025-09-03 18:00","연속"]
[803,"부산울산","서부산","신녹산녹산#1 T/L","신녹산S/S 345kV #1M.Tr 증설공사","345kV #1M.Tr 2차측 GIS #1DS, CB, 6DS 설치(감압 및 무부하시험가압)","2025-09-20 09:00","2025-09-24 18:00","2025-09-20 09:00","2025-09-24 18:00","연속"]
[804,"부산울산","서부산","신녹산용원#2 T/L","신녹산S/S 345kV #1M.Tr 증설공사","345kV #1M.Tr 2차측 GIS #2DS설치(감압)","2025-09-13 09:00","2025-09-14 18:00","2025-09-13 09:00","2025-09-14 18:00","연속"]
[805,"부산울산","서부산","신녹산녹산#1 T/L","신녹산S/S 345kV #1M.Tr 증설공사","345kV #1M.Tr 2차측 GIS #2DS 설치(감압 및 무부하시험가압)","2025-09-13 09:00","2025-09-16 18:00","2025-09-13 09:00","2025-09-16 18:00","연속"]
[806,"부산울산","서부산","신녹산용원#2 T/L","신녹산S/S 345kV #1M.Tr 증설공사","345kV #1M.Tr 2차측 GIS #1DS, CB, 6DS 설치(감압)","2025-09-20 09:00","2025-09-21 18:00","2025-09-20 09:00","2025-09-21 18:00","연속"]
[807,"부산울산","서부산","신김해지사#1 T/L","24~25년 서부산전력지사 가공송전협력회사 공사","1. 고정형 폴리머 점퍼지지애자 30,37,39호 상중하단 설치 2. 30호 중단 내측 점퍼선 인류클램프 교체","2025-09-29 08:00","2025-09-30 18:00","2025-09-29 08:00","2025-09-30 18:00","연속"]
[808,"부산울산","울산","신울산언양#1 T/L"," 추락방지장치(수평) 및 폴리머지지애자 설치공사","ㅇ 추락방지장치(수평) 설치 1기 (No.44) ㅇ 폴리머지지애자 설치 16기 (No.1, 9, 13, 16~18, 25, 27, 31, 34, 38, 44, 46, 49, 59, 65)","2025-09-22 07:00","2025-09-29 18:00","취소","취소","연속"]
[809,"부산울산","울산","신울산웅촌#1 T/L","'24~'25년 울산전력 변전협력회사 총액공사","- 신울산)GIS 동작시험 - 웅촌)GIS 동작시험","2025-09-26 09:00","2025-09-26 18:00","2025-09-26 09:00","2025-09-26 18:00","연속"]
[810,"부산울산","울산","신울산언양#2 T/L"," 추락방지장치(수평) 및 폴리머지지애자 설치공사","ㅇ 추락방지장치(수평) 설치 1기 (No.44) ㅇ 폴리머지지애자 설치 21기 (No.1, 2, 7, 9, 14~16, 18, 27, 31, 34, 36, 38, 41, 44, 49, 56, 59, 64, 66, 66-1)","2025-09-30 07:00","2025-10-08 18:00","2025-09-30 07:00","2025-10-08 18:00","연속"]
[811,"부산울산","울산","신울산웅촌#1 T/L","345kV 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치 병가철탑 작업 안전확보차( 웅촌-서창#2)","2025-09-23 07:00","2025-09-23 18:00","취소","취소","연속"]
[812,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","임시BUS TIE 철거 및 신온산-온산#2T/L 설치","2025-09-26 16:00","2025-09-27 16:00","2025-09-26 16:00","2025-09-27 16:00","연속"]
[813,"부산울산","울산","온산처용#2 T/L","'24~'25년 울산전력 변전협력회사 총액공사","보호반 87 계전기 수리","2025-09-02 09:00","2025-09-02 18:00","2025-09-03 09:00","2025-09-03 18:00","연속"]
[814,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","임시BUS TIE 철거 및 신온산-온산#2T/L 설치","2025-09-15 16:00","2025-09-15 17:00","2025-09-15 16:00","2025-09-15 17:00","연속"]
[815,"부산울산","울산","온산처용#1 T/L","온산S/S  장기사용 GIS 교체공사","임시BUS TIE 철거 및 신온산-온산#2T/L 설치","2025-09-19 16:00","2025-09-20 16:00","2025-09-19 16:00","2025-09-20 16:00","연속"]
[816,"부산울산","울산","울주외동#1 T/L","345kV 울주S/S 장기사용 GIS 교체공사","집감반 실규설치 관련 6C7 Bay 결선 및 시험작업","2025-09-15 08:00","2025-09-15 18:00","2025-09-15 08:00","2025-09-15 18:00","연속"]
[817,"부산울산","울산","울주외동#2 T/L","345kV 울주S/S 장기사용 GIS 교체공사","집감반 실규설치 관련 6B7 Bay 결선 및 시험작업","2025-09-16 08:00","2025-09-16 18:00","2025-09-16 08:00","2025-09-16 18:00","연속"]
[818,"부산울산","울산","울주직동#1 T/L","345kV 울주S/S 장기사용 GIS 교체공사","집감반 실규설치 관련 687 Bay 결선 및 시험작업","2025-09-19 08:00","2025-09-19 18:00","2025-09-19 08:00","2025-09-19 18:00","연속"]
[819,"부산울산","울산","울주직동#2 T/L","345kV 울주S/S 장기사용 GIS 교체공사","집감반 실규설치 관련 677 Bay 결선 및 시험작업","2025-09-22 08:00","2025-09-22 18:00","2025-09-22 08:00","2025-09-22 18:00","연속"]
[820,"부산울산","울산","웅촌서창#2 T/L","345kV 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치","2025-09-23 07:00","2025-09-23 18:00","취소","취소","연속"]
[821,"부산울산","울산","온산처용#1 T/L","'24~'25년 울산전력 변전협력회사 총액공사","- GIS 보통점검","2025-09-03 09:00","2025-09-03 18:00","2025-09-02 09:00","2025-09-02 18:00","연속"]
[822,"부산울산","직할","범일서면#2 T/L","24~25년 직할 변전협력회사 총액공사","범일S/S 범일-서면#2T/L GIS 보통점검","2025-09-18 09:00","2025-09-18 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[823,"부산울산","직할","수정범일#2 T/L","24~25년 직할 변전협력회사 총액공사","범일S/S 수정-범일#2T/L GIS 보통점검","2025-09-22 09:00","2025-09-22 18:00","2025-09-22 09:00","2025-09-22 18:00","연속"]
[824,"부산울산","직할","수정범일#1 T/L","24~25년 직할 변전협력회사 총액공사","범일S/S 수정-범일#1T/L GIS 보통점검","2025-09-22 09:00","2025-09-22 18:00","2025-09-22 09:00","2025-09-22 18:00","연속"]
[825,"부산울산","직할","범일서면#1 T/L","24~25년 직할 변전협력회사 총액공사","범일S/S 범일-서면#1T/L GIS 보통점검","2025-09-18 09:00","2025-09-18 18:00","2025-09-18 09:00","2025-09-18 18:00","연속"]
[826,"부산울산","직할","개금범천#1 T/L","24~25년 직할 변전협력회사 총액공사","범천S/S 개금-범천#1T/L GIS 보통점검","2025-09-29 09:00","2025-09-29 18:00","2025-09-29 09:00","2025-09-29 18:00","연속"]
[827,"부산울산","직할","개금범천#2 T/L","24~25년 직할 변전협력회사 총액공사","범천S/S 개금-범천#2T/L GIS 보통점검","2025-09-30 09:00","2025-09-30 18:00","2025-09-30 09:00","2025-09-30 18:00","연속"]
[828,"부산울산","직할","부산수정#2 T/L","24~25년 직할 변전협력회사 총액공사","부산S/S 부산-수정#2T/L GIS 보통점검","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[829,"부산울산","직할","부산수정#1 T/L","24~25년 직할 변전협력회사 총액공사","부산S/S 부산-수정#1T/L GIS 보통점검","2025-09-23 09:00","2025-09-23 18:00","2025-09-23 09:00","2025-09-23 18:00","연속"]
[830,"경남","김해송변전부","매리김해#2 T/L","2025년도 가공송전 순시점검 위탁회사","초기점검(No.1)","2025-09-07 08:00","2025-09-07 18:00","2025-09-07 08:00","2025-09-07 18:00","연속"]
[831,"경남","김해송변전부","매리김해#1 T/L","2025년도 가공송전 순시점검 위탁회사","초기점검(No.1)","2025-09-06 08:00","2025-09-06 18:00","2025-09-06 08:00","2025-09-06 18:00","연속"]
[832,"경남","김해송변전부","대동매리#1 T/L","2025년도 가공송전 순시점검 위탁회사","초기점검(No.19,20)","2025-09-06 08:00","2025-09-06 18:00","2025-09-06 08:00","2025-09-06 18:00","연속"]
[833,"경남","김해송변전부","대동매리#2 T/L","2025년도 가공송전 순시점검 위탁회사","초기점검(No.19,20)","2025-09-07 08:00","2025-09-07 18:00","2025-09-07 08:00","2025-09-07 18:00","연속"]
[834,"경남","김해송변전부","삼계어방#1 T/L","2025년도 가공송전 순시점검 위탁회사","초기점검(No.9,10,11,12,12.1,13,14)","2025-09-13 08:00","2025-09-14 18:00","2025-09-13 08:00","2025-09-14 18:00","매일"]
[835,"경남","김해송변전부","한림정삼계#2 T/L","2025년도 가공송전 순시점검 위탁회사","초기점검(No.22,23,23.1,24,25,26,27)","2025-09-13 08:00","2025-09-14 18:00","2025-09-13 08:00","2025-09-14 18:00","매일"]
[836,"경남","김해송변전부","주촌삼계#2 T/L","삼계S/S  주촌-삼계#2T/L GIS 보통점검","삼계S/S  주촌-삼계#2T/L GIS 보통점검","2025-09-10 09:00","2025-09-10 18:00","취소","취소","연속"]
[837,"경남","김해송변전부","삼계어방#2 T/L","2025년도 가공송전 순시점검 위탁회사","초기점검(No.9,10,11,12,12.1,13,14)","2025-09-20 08:00","2025-09-21 18:00","2025-09-20 08:00","2025-09-21 18:00","매일"]
[838,"경남","김해송변전부","한림정삼계#1 T/L","2025년도 가공송전 순시점검 위탁회사","초기점검(No.22,23,23.1,24,25,26,27)","2025-09-20 08:00","2025-09-21 18:00","2025-09-20 08:00","2025-09-21 18:00","매일"]
[839,"경남","김해송변전부","진영한림정#2 T/L"," 진영-수산#1T/L 정밀점검"," 진영-수산#1T/L 1호 안전거리 확보","2025-09-27 07:00","2025-09-27 18:00","2025-09-27 07:00","2025-09-27 18:00","연속"]
[840,"경남","김해송변전부","진영한림정#1 T/L"," 진영-수산#2T/L 정밀점검"," 진영-수산#2T/L 1호 안전거리 확보","2025-09-28 07:00","2025-09-28 18:00","2025-09-28 07:00","2025-09-28 18:00","연속"]
[841,"경남","직할","녹공마천#2 T/L","24~25년 경남본부 직할 송전협력회사 공사","오전(07~12시) :  녹공-마천#1T/L 폴리머점퍼지지애자 설치 오후(12~18시) :  녹공-마천#2T/L 폴리머점퍼지지애자 설치","2025-09-26 12:00","2025-09-26 18:00","2025-09-26 12:00","2025-09-26 18:00","연속"]
[842,"경남","직할","녹공마천#1 T/L","24~25년 경남본부 직할 송전협력회사 공사","오전(07~12시) :  녹공-마천#1T/L 폴리머점퍼지지애자 설치 오후(12~18시) :  녹공-마천#2T/L 폴리머점퍼지지애자 설치","2025-09-26 07:00","2025-09-26 12:00","2025-09-26 07:00","2025-09-26 12:00","연속"]
[843,"경남","직할","신김해삼정#2 T/L","24~25년 경남본부 직할 송전협력회사 공사","폴리머지지애자 설치 및 성능저하 지지애자 교체(No.1 등 19기)","2025-09-15 08:00","2025-09-18 18:00","2025-09-15 08:00","2025-09-18 18:00","매일"]
[844,"경남","직할","신김해삼정#1 T/L","24~25년 경남본부 직할 송전협력회사 공사","폴리머지지애자 설치 및 성능저하 지지애자 교체(No.2,3,4,30,31,32,33,35,37,신김해S/T)","2025-09-19 08:00","2025-09-23 18:00","2025-09-19 08:00","2025-09-23 18:00","매일"]
[845,"경남","직할","신월삼정#1 T/L","24~25년 경남본부 직할 송전협력회사 공사","9.17 :  신월-삼정#1T/L 성능저하 국산애자 교체, 폴리머점퍼지지애자 설치 9.18 : 안전이격","2025-09-17 07:00","2025-09-18 18:00","2025-09-17 07:00","2025-09-18 18:00","매일"]
[846,"경남","직할","신월삼정#2 T/L","24~25년 경남본부 직할 송전협력회사 공사"," 신월-삼정#2T/L 폴리머점퍼지지애자 설치","2025-09-23 07:00","2025-09-23 18:00","2025-09-23 07:00","2025-09-23 18:00","연속"]
[847,"경남","직할","안민천선#1 T/L","안민S/S 안민-천선#1T/L GIS 조작시험","안민S/S 안민-천선#1T/L GIS 조작시험","2025-09-09 09:00","2025-09-09 18:00","2025-09-09 09:00","2025-09-09 18:00","연속"]
[848,"경남","직할","수출월림#2 T/L","월림S/S  장기사용 대체공사(4차분)","월림S/S  장기사용 대체공사(4차분) - 대상설비 : 수출-월림#2T/L, SEC GIS","2025-09-06 09:00","2025-10-01 18:00","2025-09-06 09:00","2025-10-01 18:00","연속"]
[849,"경남","직할","월림S/S #1 BUS","월림S/S  장기사용 대체공사(4차분)","월림S/S  장기사용 대체공사(4차분) - 대상설비 : 수출-월림#2T/L, SEC GIS","2025-09-10 14:00","2025-09-20 14:00","2025-09-10 14:00","2025-09-20 14:00","연속"]
[850,"경남","진주","진주개양#1 T/L","2025년 가공송전 순시점검 위탁공사"," 사봉-개양#2T/L 정밀점검 안전거리 확보","2025-09-29 08:00","2025-09-30 18:00","취소","취소","매일"]
[851,"경남","진주","진주개양#1 T/L"," 진주-개양#1T/L EBA 절연유 채유"," 진주-개양#1T/L EBA 절연유 채유","2025-09-13 09:00","2025-09-13 18:00","2025-09-13 09:00","2025-09-13 18:00","연속"]
[852,"경남","진주","진주개양#2 T/L","2025년 가공송전 순시점검 위탁공사"," 사봉-개양#1T/L 정밀점검 안전거리 확보","2025-09-19 08:00","2025-09-20 18:00","취소","취소","매일"]
[853,"경남","진주","거창합천#1 T/L","거창S/S 거창-합천#1T/L GIS 조작시험 등","거창S/S 거창-합천#1T/L GIS 조작시험 및 PT 하자","2025-09-09 10:00","2025-09-09 14:00","취소","취소","연속"]
[854,"경남","진주","가야사봉#2 T/L","2025년 가공송전 순시점검 위탁공사"," 사봉-개양#1T/L 정밀점검 안전거리 확보","2025-09-23 08:00","2025-09-24 18:00","취소","취소","매일"]
[855,"경남","진주","가야사봉#1 T/L","2025년 가공송전 순시점검 위탁공사"," 사봉-개양#2T/L 정밀점검 안전거리 확보","2025-09-25 08:00","2025-09-26 18:00","취소","취소","매일"]
[856,"경남","진주","사봉개양#2 T/L","2025년 가공송전 순시점검 위탁공사"," 사봉-개양#2T/L 전구간 정밀점검(1~56호)","2025-09-25 08:00","2025-09-30 18:00","취소","취소","매일"]
[857,"경남","진주","사봉개양#1 T/L","2025년 가공송전 순시점검 위탁공사"," 사봉-개양#1T/L 전구간 정밀점검(1~56호)","2025-09-19 08:00","2025-09-24 18:00","취소","취소","매일"]
[858,"경남","진주","의령동진주#1 T/L","2025년 가공송전 순시점검 위탁공사"," 의령-함양T/L 1~7호 구간 정밀점검시 안전거리확보","2025-09-09 08:00","2025-09-10 18:00","취소","취소","매일"]
[859,"경남","진주","의령S/S CB 6200","의령S/S  #61-66 GIS 보통점검 및 전자변교체","의령S/S  #61-66 GIS 보통점검 및 전자변교체","2025-09-26 10:00","2025-09-26 15:00","2025-09-26 10:00","2025-09-26 15:00","연속"]
[860,"경남","진주","의령S/S CB 6100","의령S/S  #60-65 GIS 조작시험","의령S/S  #60-65 GIS 조작시험","2025-09-26 15:00","2025-09-26 17:00","2025-09-26 15:00","2025-09-26 17:00","연속"]
[861,"경남","진주","의령S/S CB 6100","하동S/S  #60-65 모선보호반 대체","하동S/S  #60-65 모선보호반 대체","2025-09-03 10:00","2025-09-05 18:00","2025-09-03 10:00","2025-09-05 18:00","연속"]
[862,"경남","진주","산청함양 T/L","2025년 가공송전 순시점검 위탁공사"," 산청-함양T/L 전구간 정밀점검(산청분기 17기, 의령-함양T/L 64~132호)","2025-09-01 08:00","2025-09-08 18:00","취소","취소","매일"]
[863,"경남","진주","의령함양 T/L","2025년 가공송전 순시점검 위탁공사"," 의령-함양T/L 전구간 정밀점검(1~132호)","2025-09-09 08:00","2025-09-18 18:00","취소","취소","매일"]
[864,"경남","진주","거창합천#1 T/L","합천S/S 거창-합천#1T/L GIS 보통점검 등","합천S/S 거창-합천#1T/L GIS 보통 및 LA(A,B,C) 보통, PT 하자","2025-09-08 09:00","2025-09-08 18:00","취소","취소","연속"]
[865,"경남","진주","거창합천#2 T/L","합천S/S  쌍림-합천#2T/L GIS 조작시험 등","합천S/S  쌍림-합천#2T/L GIS 조작시험, LA(A,B,C) 하자, PT 하자","2025-09-17 10:00","2025-09-17 18:00","취소","취소","연속"]
[866,"경남","통영","거류거제#2 T/L"," 거류-거제#2T/L 수평추락방지장치설치공사"," 거류-거제#2T/L 수평추락방지장치설치공사","2025-09-06 07:00","2025-09-07 18:00","2025-09-06 07:00","2025-09-07 18:00","매일"]
[867,"경남","통영","거류거제#1 T/L"," 거류-거제#1T/L 수평추락방지장치설치공사"," 거류-거제#1T/L 수평추락방지장치설치공사","2025-09-13 07:00","2025-09-14 18:00","2025-09-13 07:00","2025-09-14 18:00","매일"]
[868,"경남","통영","고성거류 T/L"," 고성-거류T/L 초기점검 및 보통점검 등"," 고성-거류T/L 초기점검 및 보통점검 등 1. 고성S/S : GIS 보통점검 및 LA A~C상 보통점검 2. 거류개폐소 : GIS 초기점검","2025-09-08 09:30","2025-09-08 18:00","2025-09-08 09:30","2025-09-08 18:00","연속"]
[869,"경남","통영","통영거제#2 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행)"," 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) ○  통영-거제#2T/L 70호 ~ 가철탑 2호 전선(가공지선 포함) 설치 ○  통영-거제#2T/L 거제S/T ~ EBA 인하선 설치 ○  통영-거제#2T/L 기설 70호 ~ 거제S/T (가공지선 포함) 철거","2025-09-20 07:00","2025-09-21 18:00","2025-09-20 07:00","2025-09-21 18:00","매일"]
[870,"경남","통영","거류거제#1 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행)"," 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) ○  신고성-거제#1T/L 196호(現 거류-거제#1T/L 78호) ~ 가철탑 2호 전선(가공지선 포함) 설치 ○  거류-거제#1T/L 거제S/T ~ EBA 인하선 설치 ○   신고성-거제#1T/L 196호(現 거류-거제#1T/L 78호) ~","2025-09-20 07:00","2025-09-21 18:00","2025-09-20 07:00","2025-09-21 18:00","매일"]
[871,"경남","통영","통영거제#2 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행)"," 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) ○  통영-거제#2T/L 70호 ~ 가철탑 2호 전선(가공지선 포함) 설치 ○  통영-거제#2T/L 거제S/T ~ EBA 인하선 설치 ○  통영-거제#2T/L 기설 70호 ~ 거제S/T (가공지선 포함) 철거","2025-09-13 07:00","2025-09-14 18:00","2025-09-13 07:00","2025-09-14 18:00","매일"]
[872,"경남","통영","거류거제#1 T/L","거제S/S 인출 송전선로 임시선로 구성공사(요청자시행)"," 거제S/S 인출 송전선로 지중이설공사(임시선로 구성)(요청자시행) ○  신고성-거제#1T/L 196호(現 거류-거제#1T/L 78호) ~ 가철탑 2호 전선(가공지선 포함) 설치 ○  거류-거제#1T/L 거제S/T ~ EBA 인하선 설치 ○   신고성-거제#1T/L 196호(現 거류-거제#1T/L 78호) ~","2025-09-13 07:00","2025-09-14 18:00","2025-09-13 07:00","2025-09-14 18:00","매일"]
[873,"경남","통영","사천S/S #1 Sh.C CB","사천S/S  #1Sh.C MAIN GIS 조작시험 등","사천S/S  #1Sh.C MAIN GIS 조작시험 등 1. MAIN GIS 조작시험 2. 1-1 SR A~C상 보통점검 3. 1-1 GCB 보통점검 4. 1-1 GCB 공기압축기 보통점검","2025-09-25 09:30","2025-09-26 18:00","2025-09-25 09:30","2025-09-26 18:00","연속"]
[874,"경남","통영","사천개양#2 T/L","사천S/S  사천-개양 #2T/L GIS 보통점검 등","사천S/S  사천-개양 #2T/L GIS 보통점검 등 1. GIS 보통점검 2. LA A~C상 하자점검","2025-09-13 09:30","2025-09-13 18:00","2025-09-13 09:30","2025-09-13 18:00","연속"]
[875,"경남","통영","사천개양#1 T/L","사천S/S  사천-개양 #1T/L GIS 보통점검 등","사천S/S  사천-개양 #1T/L GIS 보통점검 등 1. GIS 보통점검 2. LA A~C상 하자점검 3. 87Ry 내부 모듈 이상상태 조치(운영)","2025-09-07 09:30","2025-09-07 18:00","취소","취소","연속"]
[876,"경남","통영","신고성삼천포#1 T/L"," 신고성-삼천포#1T/L 조작시험 및 보통점검"," 신고성-삼천포#1T/L 조작시험 및 보통점검 1. 신고성S/S : 조작시험 2. 삼천포S/S : 보통점검","2025-09-06 07:30","2025-09-06 18:00","2025-09-06 07:30","2025-09-06 18:00","연속"]
[877,"경남","통영","신고성고성 T/L"," 신고성-고성T/L GIS 조작시험 및 보통점검 등"," 신고성-고성T/L GIS 조작시험 및 보통점검 등 1. 신고성S/S : GIS 조작시험 2. 고성S/S : GIS 보통점검 및 LA 보통점검","2025-09-23 09:30","2025-09-23 18:00","2025-09-23 09:30","2025-09-23 18:00","연속"]
[878,"경남","통영","통영거제#2 T/L"," 통영-거제T/L GIS 보통점검"," 통영-거제T/L GIS 보통점검 1. 통영S/S : GIS 보통점검 2. 거제S/S : GIS 보통점검","2025-09-27 09:30","2025-09-27 18:00","2025-09-27 09:30","2025-09-27 18:00","연속"]
[879,"경남","통영","거류통영복합#1 T/L"," 거류-통영복합 #1T/L GIS 초기점검"," 거류-통영복합 #1T/L GIS 초기점검 1. 거류개폐소 : GIS 초기 2. 통영복합S/Y : GIS 초기점검","2025-09-28 09:30","2025-09-28 18:00","2025-09-28 09:30","2025-09-28 18:00","연속"]
[880,"경남","함안","중리가야#2 T/L","가야S/S 중리가야#2 T/L GIS 보통점검","가야S/S 중리가야#2 T/L GIS 보통점검","2025-09-12 09:30","2025-09-12 17:30","취소","취소","연속"]
[881,"경남","함안","가야사봉#2 T/L","가야S/S 가야-사봉#2T/L 피뢰기 대체작업","가야S/S  가야-사봉#2T/L 피뢰기 대체작업","2025-09-11 09:30","2025-09-11 17:30","취소","취소","연속"]
[882,"경남","함안","가야사봉#1 T/L","가야S/S 가야-사봉#1T/L 피뢰기 대체작업","가야S/S  가야-사봉#1T/L 피뢰기 대체작업","2025-09-10 09:30","2025-09-10 17:30","취소","취소","연속"]
[883,"경남","함안","부북밀양#2 T/L","밀양S/S  부북밀양#2 T/L LID 이설 작업","밀양S/S  부북밀양#2 T/L LID 이설 작업","2025-09-12 09:30","2025-09-12 17:30","2025-09-12 09:30","2025-09-12 17:30","연속"]
[884,"경남","함안","부북밀양#1 T/L","밀양S/S  부북밀양#1 T/L LID 이설 작업","밀양S/S  부북밀양#1 T/L LID 이설 작업","2025-09-11 09:30","2025-09-11 17:30","2025-09-11 09:30","2025-09-11 17:30","연속"]
[885,"경남","함안","초동밀양#2 T/L","밀양S/S  초동밀양#2 T/L LID 이설 작업","밀양S/S  초동밀양#2 T/L LID 이설 작업","2025-09-10 09:30","2025-09-10 17:30","2025-09-10 09:30","2025-09-10 17:30","연속"]
[886,"경남","함안","초동밀양#1 T/L","밀양S/S  초동밀양#1 T/L LID 이설 작업","밀양S/S  초동밀양#1 T/L LID 이설 작업","2025-09-09 09:30","2025-09-09 17:30","2025-09-09 09:30","2025-09-09 17:30","연속"]
[887,"경남","함안","진영수산#1 T/L"," 진영-수산#1T/L 정밀점검"," 진영-수산#1T/L 1호, 28-60호 정밀점검","2025-09-25 07:00","2025-09-27 18:00","2025-09-25 07:00","2025-09-27 18:00","매일"]
[888,"경남","함안","진영수산#2 T/L"," 진영-수산#2T/L 정밀점검"," 진영-수산#2T/L 1호, 28-60호 정밀점검","2025-09-28 07:00","2025-09-30 18:00","2025-09-28 07:00","2025-09-30 18:00","매일"]
[889,"경남","함안","중리가야#2 T/L"," 중리-가야#1T/L 피뢰기 설치공사(안전이격거리확보)"," 중리-가야#1T/L 40~51호 피뢰기 설치 시 4회선 병가철탑(수직배열)으로 동시휴전 필요","2025-09-19 07:00","2025-09-19 18:00","취소","취소","연속"]
[890,"경남","함안","신마산중리#2 T/L"," 신마산-중리#2T/L 피뢰기 설치공사"," 신마산-중리#2T/L 1,24~32호(10기) 피뢰기 설치","2025-09-18 07:00","2025-09-18 18:00","취소","취소","연속"]
[891,"경남","함안","중리가야#1 T/L"," 중리-가야#1T/L 피뢰기 설치공사"," 중리-가야#1T/L 40~51호(8기) 피뢰기 설치","2025-09-18 07:00","2025-09-19 18:00","취소","취소","매일"]
[892,"경남","함안","창녕초동#1 T/L"," 창녕-구지#2T/L 폴리머 점퍼지지애자 설치공사(안전이격거리)"," 창녕-구지#2T/L 고정형 폴리머 점퍼지지애자 설치[2~5호(3기) 시 4회선 병가철탑(수직배열)으로 동시휴전 필요","2025-09-14 07:00","2025-09-14 18:00","2025-09-14 07:00","2025-09-14 18:00","연속"]
[893,"경남","함안","창녕구지#2 T/L"," 창녕-구지#2T/L 고정형 폴리머 점퍼지지애자 설치공사"," 창녕-구지#2T/L 고정형 폴리머 점퍼지지애자 설치[2~81호(18기) ※ T분기선로로 휴전기간 일요일마다 점퍼선 분리 및 복귀작업 시행 예정이며, 휴전기간 중이라도 고객사(화인베스틸)에 전력을 공급해야함(편측 변전소 CB 투입)","2025-09-14 07:00","2025-09-28 18:00","2025-09-14 07:00","2025-09-28 18:00","연속"]
[894,"경남","함안","초동밀양#1 T/L"," 초동-밀양#1T/L 철탑 부재 현장실측 작업","철탑 보강재(산형강) 물량 산출을 위한 철탑 부재 현장실측용역 시행 (9, 10, 13, 14, 15호)","2025-09-23 07:00","2025-09-24 18:00","2025-09-15 07:00","2025-09-16 18:00","매일"]
[895,"경남","함안","초동밀양#2 T/L"," 초동-밀양#2T/L 철탑 부재 현장실측 작업","철탑 보강재(산형강) 물량 산출을 위한 철탑 부재 현장실측용역 시행 (9, 10, 13, 14, 15호)","2025-09-25 07:00","2025-09-26 18:00","2025-09-17 07:00","2025-09-18 18:00","매일"]