{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":21,"n_cols":11,"rows_kept":21,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 10월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #4 M.Tr","신가평S/S #4M.Tr 복구공사","신가평S/S #4M.Tr 복구공사 - #4M.Tr 설치 - 1,2차측 GIB 연결 - LCP 대체","2025-10-13 09:00","2025-11-21 18:00","2025-10-13 09:00","2025-11-21 18:00","연속"]
[2,"강원","태백","신태백S/S #4 M.Tr","2025년  신태백S/S #4M.Tr 보통점검 공사","신태백S/S  #4 M.Tr 보통점검","2025-10-20 09:00","2025-10-31 18:00","2025-10-20 09:00","2025-10-31 18:00","연속"]
[3,"강원","태백","신태백S/S #3 M.Tr","2024-2025 태백전력지사 변전협력회사 공사","신태백S/S  #3M.Tr A-2 LCP 상시여자형계전기 교체","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[4,"충북","직할","신중부신안성#2 T/L","신중부S/S  GIS 보통점검공사"," GIS 보통점검","2025-10-13 09:00","2025-10-14 18:00","취소","취소","연속"]
[5,"충북","직할","신중부S/S CB 8800","신중부S/S  GIS 보통점검공사"," GIS 보통점검","2025-10-15 09:00","2025-10-16 18:00","2025-10-15 09:00","2025-10-16 18:00","연속"]
[6,"충북","직할","신중부S/S #4 M.Tr","신중부S/S  GIS 보통점검공사"," GIS 보통점검","2025-10-20 09:00","2025-10-21 18:00","2025-10-20 09:00","2025-10-21 18:00","연속"]
[7,"충북","직할","신중부S/S CB 8700","신중부S/S  GIS 보통점검공사"," GIS 보통점검","2025-10-01 09:00","2025-10-02 18:00","2025-10-01 09:00","2025-10-02 18:00","연속"]
[8,"대전세종충남","서산","신서산S/S #4 M.Tr","[변전운영부]신서산S/S  #4M.Tr 및 OLTC 정밀점검공사","○ 신서산S/S  #4M.Tr 및 OLTC 정밀점검공사(즉시가압 불가) - 점검전후 시험, OLTC 점검, 졀연유 배유, 내부점검, 절연유 여과 등 - 보조계전기, 냉각팬 베어링, 기계적 보호장치, OFU, 온도계 교체 등 - [서산P/O] #4M.Tr 보호배전반 교체 병행","2025-10-13 09:00","2025-11-14 18:00","2025-10-13 09:00","2025-11-14 18:00","연속"]
[9,"경북","영주","신한울N/P #2 M.Tr","#2M.Tr 불량조치","○ 220V 역가압 관련 회로개선 ○ 권선온도계 점검","2025-10-13 09:00","2025-10-14 18:00","취소","취소","연속"]
[10,"부산울산","동부산","신고리N/P #3 M.Tr","2025년 하반기 신고리S/S  GIS 정밀보통점검 공사","8500CB 정밀점검 및 시험가압","2025-10-20 09:00","2025-10-24 18:00","2025-10-20 09:00","2025-10-24 18:00","연속"]
[11,"부산울산","동부산","신고리N/P #2 M.Tr","2025년 하반기 신고리S/S  GIS 정밀보통점검 공사","8771,8700 보통점검","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[12,"부산울산","동부산","북경남신고리NP#2 T/L","북경남-신고리#2T/L, 신고리S/S 83Bay B/F PNL 교체","북경남-신고리#2T/L, 신고리S/S 83Bay B/F PNL 교체","2025-10-10 09:00","2025-10-17 18:00","2025-11-03 09:00","2025-11-11 18:00","연속"]
[13,"경남","함안","북경남신고리NP#2 T/L"," 북경남S/S #2M.Tr 증설공사"," #1BUS 도킹에 따른 안전이격거리 확보","2025-10-20 09:00","2025-10-22 18:00","취소","취소","연속"]
[14,"경남","함안","북경남S/S #1 BUS"," 북경남S/S #2M.Tr 증설공사"," #1BUS 도킹 작업","2025-10-20 09:00","2025-11-01 18:00","취소","취소","연속"]
[15,"경남","함안","북경남S/S #5 M.Tr"," 북경남S/S #2M.Tr 증설공사"," #1BUS 도킹 후 시험 가압","2025-10-31 09:00","2025-11-01 18:00","취소","취소","연속"]
[]
[{"$nulls":5}," "]

{"sheet":"345설비","index":1,"n_rows":381,"n_cols":11,"rows_kept":381,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2025년도 10월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr","2025 성동전력지사 변전협력회사 공사","- 효성제 170kV GIS 노후 전자변 교체","2025-10-17 09:00","2025-10-17 18:00","2025-10-17 09:00","2025-10-17 18:00","연속"]
[2,"서울","성동","성동S/S #1 M.Tr","2025 성동전력지사 변전협력회사 공사","- 효성제 170kV GIS 노후 전자변 교체","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[3,"서울","중부","중부S/S #2 BUS","2025년 중부전력지사 변전협력회사 공사","CT 집합반 교체","2025-10-21 10:00","2025-10-22 10:00","2025-10-21 10:00","2025-10-22 10:00","연속"]
[4,"서울","중부","중부S/S #1 M.Tr","2025년 중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV #65BUS 모선 무부하가압용","2025-10-16 17:00","2025-10-17 09:00","2025-10-17 17:00","2025-10-20 09:00","연속"]
[5,"서울","중부","중부S/S #2 M.Tr","2025년 중부전력지사 변전협력회사 공사","- 1차 GIS 보통점검(7252,7262,7222,7228) - 3차 PT 위치 조정","2025-10-28 10:00","2025-10-28 18:00","2025-10-28 10:00","2025-10-28 18:00","연속"]
[6,"서울","중부","중부S/S #1 BUS","2025년 중부전력지사 변전협력회사 공사","CT 집합반 교체","2025-10-22 10:00","2025-10-22 18:00","2025-10-22 10:00","2025-10-22 18:00","연속"]
[7,"서울","중부","중부S/S #1 M.Tr","2025년 중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV #60BUS 모선 무부하가압용","2025-10-24 17:00","2025-10-27 09:00","2025-10-24 17:00","2025-10-27 09:00","연속"]
[8,"서울","중부","중부S/S #1 BUS","2025년 중부전력지사 변전협력회사 공사","CT 집합반 교체","2025-10-20 17:00","2025-10-21 10:00","2025-10-20 17:00","2025-10-21 10:00","연속"]
[9,"남서울","강남","신성남신양재#2 T/L","24-25년도 강남전력지사 변전협력회사 총액공사"," GIS 및 154kV GIS 조작시험, 전자변 교체","2025-10-24 09:00","2025-10-24 18:00","2025-10-24 09:00","2025-10-24 18:00","연속"]
[10,"남서울","동서울","동서울S/S CB 7800","362kV GIS Line PT 철거공사","362kV GIS Line PT 철거공사(불량설비 교체용 자재확보)","2025-10-27 09:00","2025-10-30 18:00","2025-10-27 09:00","2025-10-30 18:00","연속"]
[11,"남서울","동서울","동서울S/S #3 M.Tr","24-25년도 동서울전력지사 변전협력회사 총액공사","동서울S/S #3M.Tr 부싱절연유 채유","2025-10-22 09:00","2025-10-22 18:00","2025-10-22 09:00","2025-10-22 18:00","연속"]
[12,"남서울","동서울","동서울S/S CB 7872","362kV GIS Line PT 철거공사","362kV GIS Line PT 철거공사(불량설비 교체용 자재확보)","2025-10-27 09:00","2025-10-30 18:00","2025-10-27 09:00","2025-10-30 18:00","연속"]
[13,"남서울","영등포","신광명S/S #3 M.Tr","신광명S/S #3M.Tr 과열개소 보수","신광명S/S #3M.Tr 과열개소 보수","2025-10-13 09:00","2025-10-15 18:00","2025-10-13 09:00","2025-10-15 18:00","연속"]
[14,"남서울","직할","신문래S/S #2 M.Tr","170kV GIS 정밀점검 공사(#2M.Tr 2차 GIS)","170kV GIS 정밀점검 공사(#2M.Tr 2차 GIS)","2025-10-27 09:00","2025-10-29 18:00","2025-10-27 09:00","2025-10-29 18:00","연속"]
[15,"남서울","직할","신문래S/S #1 M.Tr","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS)","170kV GIS 정밀점검 공사(#1M.Tr 2차 GIS)","2025-10-16 09:00","2025-10-18 18:00","2025-10-16 09:00","2025-10-18 18:00","연속"]
[16,"남서울","직할","신문래S/S #3 M.Tr","170kV GIS 정밀점검 공사(#3M.Tr 2차 GIS)","170kV GIS 정밀점검 공사(#3M.Tr 2차 GIS)","2025-10-23 09:00","2025-10-25 18:00","2025-10-23 09:00","2025-10-25 18:00","연속"]
[17,"남서울","영등포","신광명S/S #1 M.Tr"," 신광명S/S #1M.Tr 주변압기 하자점검"," 신광명S/S #1M.Tr 주변압기 하자점검","2025-10-27 09:00","2025-10-29 18:00","2025-10-27 09:00","2025-10-29 18:00","연속"]
[18,"남서울","영등포","신광명S/S #4 M.Tr"," 신광명S/S #4M.Tr 누기 보수"," 신광명S/S #4M.Tr 누기 보수","2025-10-30 09:00","2025-10-31 18:00","2025-10-30 09:00","2025-10-31 18:00","연속"]
[19,"인천","김포","신김포신파주#2 T/L","신김포S/S  신김포-신파주#2T/L 보호배전반 대체공사","신김포S/S  신김포-신파주#2T/L 보호배전반 대체공사","2025-10-27 10:00","2025-10-31 18:00","취소","취소","연속"]
[20,"인천","김포","신김포서인천CC T/L","신김포S/S  신김포-신파주#2T/L 보호배전반 대체관련 휴전","신김포S/S  신김포-신파주#2T/L 보호배전반 대체공사관련 휴전 - 혼촉 및 오동작등에 의한 고장방지 - 작업자 안전 및 인적실수 방지","2025-10-27 10:00","2025-10-31 18:00","취소","취소","연속"]
[21,"인천","김포","신김포신파주#1 T/L","신김포S/S  신김포-신파주#1T/L 보호배전반 대체공사","신김포S/S  신김포-신파주#1T/L 보호배전반 대체공사","2025-10-20 10:00","2025-10-24 18:00","2025-10-20 10:00","2025-10-24 18:00","연속"]
[22,"인천","김포","신김포S/S #1 M.Tr","신김포S/S  신김포-신파주#1T/L 보호배전반 대체관련 휴전","신김포S/S  신김포-신파주#1T/L 보호배전반 대체공사관련 휴전 - 혼촉 및 오동작등에 의한 고장방지 - 작업자 안전 및 인적실수 방지","2025-10-20 10:00","2025-10-24 18:00","2025-10-20 10:00","2025-10-24 18:00","연속"]
[23,"인천","부평","서인천C/C CB 7577","서인천C/C  #75-77 CLR #7577 GIS 조작","서인천C/C  #75-77 CLR #7577 GIS 조작","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[24,"인천","부평","서인천C/C #4 M.Tr","서인천복합S/Y  #4M.Tr 염해방지 코팅","서인천복합S/Y  #4M.Tr 염해방지 코팅","2025-10-10 09:00","2025-10-11 18:00","2025-10-10 09:00","2025-10-11 18:00","연속"]
[25,"인천","부평","서인천C/C #3 M.Tr"," #3M.Tr 부싱유 채유"," #3M.Tr 부싱유 채유","2025-10-18 09:00","2025-10-18 18:00","2025-10-18 09:00","2025-10-18 18:00","연속"]
[26,"인천","부평","서인천C/C CB 7777","서인천C/C  #75-77 CLR #7777 GIS 조작","서인천C/C  #75-77 CLR #7777 GIS 조작","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[27,"인천","부평","서인천C/C #1 M.Tr"," #1M.Tr 부싱유 채유"," #1M.Tr 부싱유 채유","2025-10-21 09:00","2025-10-21 18:00","2025-10-21 09:00","2025-10-21 18:00","연속"]
[28,"인천","부평","서인천C/C #2 M.Tr"," #2M.Tr 부싱유 채유"," #2M.Tr 부싱유 채유","2025-10-20 09:00","2025-10-20 18:00","2025-10-20 09:00","2025-10-20 18:00","연속"]
[29,"인천","부평","신경서서인천CC T/L","서인천복합S/Y  신경서서인천CCT/L CLR DS조작함 보수","서인천복합S/Y  신경서서인천CCT/L CLR DS조작함 보수","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[30,"인천","부평","신가좌S/S CB 7271"," 신가좌-가정#1T/L 7271 GIS 조작"," 신가좌-가정#1T/L 7271 GIS 조작","2025-10-29 09:00","2025-10-29 18:00","2025-10-29 09:00","2025-10-29 18:00","연속"]
[31,"인천","부평","신가좌S/S CB 7200","신가좌가정#1-신가좌신시흥#1T/L TIE 7200 GIS 조작"," 신가좌가정#1-신가좌신시흥#1T/L TIE 7200 GIS 조작","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[32,"인천","부평","신가좌S/S CB 7371"," 신가좌-신시흥#1T/L 7272 GIS 조작","(구)신가좌S/S  신가좌-신시흥#1T/L 7272 GIS 조작","2025-10-31 09:00","2025-10-31 18:00","2025-10-31 09:00","2025-10-31 18:00","연속"]
[33,"인천","부평","신가좌S/S CB 7472","신가좌  #3 M.Tr 1차 7472 GIS 보통점검","신가좌  #3 M.Tr 1차 7472 GIS 보통점검","2025-10-04 09:00","2025-10-04 18:00","2025-10-04 09:00","2025-10-04 18:00","연속"]
[34,"인천","부평","신가좌S/S CB 7600"," #4 M.Tr 1차 TIE 7600 GIS보통점검,열화(오후)"," #4 M.Tr 1차 TIE 7600 GIS 보통점검, 절연열화","2025-10-03 11:00","2025-10-03 18:00","2025-10-03 11:00","2025-10-03 18:00","연속"]
[35,"인천","부평","신가좌S/S #2 M.Tr","신가좌S/S #2M.Tr 하자점검","신가좌S/S #2M.Tr 하자점검","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[36,"인천","부평","신가좌신시흥#1 T/L"," 신가좌-신시흥T/L No.15 태풍취약철탑 보강공사 등 3건","15호 인클로징 보강(태풍취약) 2~13호 상부재 보강(철탑보강)  피뢰기 설치(가공협력)","2025-10-21 07:00","2025-11-01 18:00","취소","취소","연속"]
[37,"인천","부평","신가좌신시흥#2 T/L"," 신가좌-신시흥T/L No.15 태풍취약철탑 보강공사","인클로징 공법 충전부 방호장치 설치","2025-10-20 07:00","2025-10-20 18:00","취소","취소","연속"]
[38,"인천","부평","신가좌S/S CB 7400","신가좌신시흥#2T/L-#3 M.Tr 1차 TIE 7400 GIS 조작"," 신가좌신시흥#2T/L-#3 M.Tr 1차 TIE 7400 GIS 조작","2025-10-18 09:00","2025-10-18 18:00","취소","취소","연속"]
[39,"인천","부평","신가좌S/S CB 7471"," 신가좌-신시흥#2T/L 7471 GIS 조작"," 신가좌-신시흥#2T/L 7471 GIS 조작","2025-10-11 09:00","2025-10-11 18:00","2025-10-11 09:00","2025-10-11 18:00","연속"]
[40,"인천","부평","신가좌S/S CB 7672"," #4 M.Tr 1차 7672 GIS 보통점검, 절연열화(오전)"," #4 M.Tr 1차 7672 GIS 보통점검, 절연열화(오전)","2025-10-03 07:00","2025-10-03 11:00","2025-10-03 07:00","2025-10-03 11:00","연속"]
[41,"인천","부평","신가좌S/S #4 M.Tr"," #4M.Tr 보통점검, 2차 6444 GIS 보통점검"," #4M.Tr 보통점검, 2차 6444 GIS 보통점검, 부싱유 채유, 베어링 발청 유사고장 보수","2025-10-06 09:00","2025-10-08 18:00","취소","취소","연속"]
[42,"인천","부평","신경서S/S #1 M.Tr"," #1M.Tr 부싱유 채유"," #1M.Tr 부싱유 채유","2025-10-16 09:00","2025-10-16 18:00","취소","취소","연속"]
[43,"인천","부평","신경서S/S #2 M.Tr","신경서S/S  #2M.Tr 부싱유 채유","신경서S/S  #2M.Tr 부싱유 채유","2025-10-17 09:00","2025-10-17 18:00","2025-10-17 09:00","2025-10-17 18:00","연속"]
[44,"인천","부평","신경서S/S #3 M.Tr"," #3M.Tr 2차 피뢰기 A,B,C 교체"," #3M.Tr 2차 피뢰기 A,B,C 교체","2025-10-22 09:00","2025-10-22 18:00","취소","취소","연속"]
[45,"인천","부평","신인천C/C CB 7572","신인천C/C  3MT101 7572 GIS 조작시험","신인천C/C  3MT101 GIS 조작시험 및 전자변교체","2025-10-28 09:00","2025-10-28 18:00","2025-10-28 09:00","2025-10-28 18:00","연속"]
[46,"인천","부평","인천C/C SEC CB 75760","인천CC S/Y  #75-#76 SEC GIS 정밀점검","인천CC S/Y  #75-#76 SEC GIS 정밀점검","2025-10-13 07:30","2025-10-16 18:00","2025-10-13 07:30","2025-10-16 18:00","연속"]
[47,"인천","부평","인천C/C #76 BUS","인천CC  #75-#76 SEC GIS 정밀점검 무부하가압","인천CC S/Y  #75-#76 SEC GIS 정밀점검 무부하가압","2025-10-16 16:00","2025-10-16 18:00","2025-10-16 16:00","2025-10-16 18:00","연속"]
[48,"인천","부평","가정인천CC#1 T/L","인천복합S/Y 가정-인천CC#1T/L 염해방지 코팅공사","인천복합S/Y 가정-인천CC#1T/L 염해방지 코팅공사","2025-10-18 07:00","2025-10-18 20:00","2025-10-18 07:00","2025-10-18 20:00","연속"]
[49,"인천","부평","인천C/C CB 7571"," 인천복합 #3,4 G/T 7571 GIS 조작"," 인천복합 #3,4 G/T 7571 GIS 조작","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[50,"인천","부평","가정인천CC#2 T/L","인천C/C  가정인천CC#2T/L 염해방지 코팅공사","인천C/C  가정인천CC#2T/L 염해방지 코팅공사 - CLR 인출 부싱","2025-10-19 07:00","2025-10-19 20:00","2025-10-19 07:00","2025-10-19 20:00","연속"]
[51,"인천","부평","인천C/C #2 M.Tr"," #2 TIE Tr 보통점검, 기계적보호장치 교체"," #2 TIE Tr 보통점검, 기계적보호장치 교체, 2차 6244GIS 조작시험, 3차 4289 GIS 조작시험, 부싱유 채유","2025-10-20 09:00","2025-10-24 18:00","취소","취소","연속"]
[52,"인천","부평","인천C/C CB 7572"," 인천복합 #1,2 G/T 7572 GIS 조작"," 인천복합 #1,2 G/T 7572 GIS 조작","2025-10-28 09:00","2025-10-28 18:00","2025-10-28 09:00","2025-10-28 18:00","연속"]
[53,"인천","부평","인천C/C CB 7500","인천CC#3,4G/T-인천CC#1,2G/T TIE 7500 GIS 조작","인천CC#3,4G/T-인천CC#1,2G/T TIE 7500 GIS 조작","2025-10-29 09:00","2025-10-29 18:00","2025-10-29 09:00","2025-10-29 18:00","연속"]
[54,"인천","부평","가정인천CC#1 T/L"," #1SH.R 부싱 누기 보수관련 크레인 이격거리 확보"," #1SH.R 부싱 누기 보수관련 크레인 이격거리 확보","2025-10-02 09:00","2025-10-03 18:00","취소","취소","연속"]
[55,"인천","부평","인천C/C CB 7672"," 인천복합 #1 S/T 7672 GIS 조작, 공압 게이지 교체"," 인천복합 #1 S/T 7672 GIS 조작 및 공기압게이지 교체","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[56,"인천","부평","인천C/C CB 7671"," 인천복합 #2 S/T 7671 GIS 조작"," 인천복합 #2 S/T 7671 GIS 조작","2025-10-31 09:00","2025-10-31 18:00","2025-10-31 09:00","2025-10-31 18:00","연속"]
[57,"인천","부평","인천C/C #1 Sh.R CB"," #1SH.R 부싱 누기 보수, 추락방지장치 설치"," #1SH.R 누기 보수, 가정인천CC#1T/L 동시휴전 필요 / 추락방지장치 설치","2025-10-02 09:00","2025-10-04 18:00","취소","취소","연속"]
[58,"인천","부평","인천C/C #1 M.Tr"," #1Tie Tr 부싱유 채유"," #1Tie Tr 부싱유 채유","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[59,"인천","시흥","신시화S/S #1Sh.R CB","신시화S/S #1Sh.R 하자점검","신시화S/S #1Sh.R 하자점검+PNC성능개선 병행","2025-10-24 09:00","2025-10-24 14:00","2025-10-24 09:00","2025-10-24 14:00","연속"]
[60,"인천","시흥","신시화영흥TP#1 T/L","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(72BF반)","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[61,"인천","시흥","신시화S/S #4 M.Tr","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(75BF반)","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[62,"인천","시흥","신시흥신시화#2 T/L","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(75BF반)","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[63,"인천","시흥","신시흥신시화#1 T/L"," 영흥T/L 부식금구 아연도금 도막두께 측정"," 영흥T/L 공단지역 내 금구류 부식발생 개소 도막두께 측정 - 대상개소 : No.59,68 (2개소)","2025-10-14 09:00","2025-10-15 18:00","2025-10-14 09:00","2025-10-15 18:00","연속"]
[64,"인천","시흥","신시화S/S #2 M.Tr","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(63BF반)","2025-10-31 09:00","2025-10-31 14:00","2025-10-31 09:00","2025-10-31 14:00","연속"]
[65,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥#1S/S  #3 M.Tr 보통점검","신시흥#1S/S  #3 M.Tr 보통점검","2025-10-13 09:00","2025-10-17 18:00","취소","취소","연속"]
[66,"인천","시흥","신시흥영흥TP#1 T/L"," 영흥T/L 부식금구 아연도금 도막두께 측정"," 영흥T/L 공단지역 내 금구류 부식발생 개소 도막두께 측정 - 대상개소 : No.59,68 (2개소)","2025-10-14 09:00","2025-10-15 18:00","2025-10-14 09:00","2025-10-15 18:00","연속"]
[67,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥#1S/S  #1 M.Tr 보통점검","신시흥#1S/S  #1 M.Tr 보통점검","2025-10-20 09:00","2025-10-24 18:00","취소","취소","연속"]
[68,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥#1S/S  #2 M.Tr 보통점검","신시흥#1S/S  #2 M.Tr 보통점검-보호반대체 병행","2025-10-27 09:00","2025-10-31 18:00","취소","취소","연속"]
[69,"인천","시흥","신시흥#1S/S CB 7771","신시흥S/S 362kV GIS 정밀점검 공사(7771)","신시흥S/S 7771 CB 정밀점검 공사","2025-10-13 08:00","2025-10-17 18:00","2025-10-13 08:00","2025-10-17 18:00","연속"]
[70,"인천","시흥","신시흥#1S/S CB 7872","신시흥#1S/S  7872 GIS 보통점검","신시흥#1S/S  7872 GIS 보통점검","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[71,"인천","시흥","신시흥신안산#1 T/L","신시흥신안산#1T/L 보호반대체","신시흥신안산#1T/L 보호반대체","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[72,"인천","시흥","영흥T/P CB 7871","영흥#2 7871 GIS 보통점검","영흥#2T/P 영흥TP신시화#1T/L GIS(7871) 보통점검","2025-10-23 09:00","2025-10-23 18:00","취소","취소","연속"]
[73,"인천","시흥","영흥T/P CB 7800","영흥#2 7800 GIS 보통점검","영흥#2T/P 영흥TP신시화#1T/L - TIE GIS(7800) 보통점검","2025-10-22 09:00","2025-10-22 18:00","취소","취소","연속"]
[74,"인천","직할","갈산S/S CB 7500","갈산S/S 7500 GIS 보통점검","갈산S/S 7500 GIS 보통점검","2025-10-22 09:00","2025-10-22 18:00","2025-10-22 09:00","2025-10-22 18:00","연속"]
[75,"인천","직할","갈산S/S #1 M.Tr","갈산S/S #1M.Tr 보통점검 및 2차 GIS 보통점검","갈산S/S #1M.Tr 보통점검 및 2차 GIS 보통점검","2025-10-13 09:30","2025-10-14 18:00","2025-10-13 09:30","2025-10-14 18:00","연속"]
[76,"경기북부","고양","신김포신파주#2 T/L","신파주S/S 장기사용 노후 배전반 대체공사"," 신김포-신파주#2T/L 보호반 및 #75 Bay B/F 보호반 대체","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[77,"경기북부","고양","신파주신덕은#2 T/L","신파주S/S 장기사용 노후 배전반 대체공사","#75 Bay B/F 보호반 대체","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[78,"경기북부","고양","신김포신파주#1 T/L","신파주S/S 장기사용 노후 배전반 대체공사"," 신김포-신파주#1T/L 보호반 및 #71 Bay B/F 보호반 대체","2025-10-20 09:00","2025-10-24 18:00","2025-10-20 09:00","2025-10-24 18:00","연속"]
[79,"경기북부","고양","신파주S/S #2 M.Tr","24-25년 고양전력 변전협력회사 공사","신파주S/S  #2M.Tr 3차 LA 보통점검","2025-10-10 09:00","2025-10-10 18:00","2025-10-10 09:00","2025-10-10 18:00","연속"]
[80,"경기북부","고양","신파주신덕은#1 T/L","신파주S/S 장기사용 노후 배전반 대체공사","#71 Bay B/F 보호반 대체","2025-10-20 09:00","2025-10-24 18:00","2025-10-20 09:00","2025-10-24 18:00","연속"]
[81,"경기북부","구리","미금S/S #6 Sh.R CB","2025년 구리전력지사 154kV 이상 GIS 점검공사","관내변전소  GIS 점검(7472)","2025-10-24 09:00","2025-10-24 18:00","2025-10-24 09:00","2025-10-24 18:00","연속"]
[82,"경기북부","구리","미금S/S #2 M.Tr","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  M.Tr 보통점검","2025-10-20 09:00","2025-10-22 18:00","2025-10-20 09:00","2025-10-22 18:00","연속"]
[83,"경기북부","구리","미금S/S #3 VSR CB","미금 용량부족 차단기 대체공사(72bay)","용량부족 차단기 대체 25CB","2025-10-13 09:00","2025-12-30 18:00","2025-10-13 09:00","2025-12-30 18:00","연속"]
[84,"경기북부","구리","미금S/S #1 M.Tr","25년 구리전력지사  M.Tr, Sh.R 정밀점검공사","#1M.Tr B상, OLTC 정밀점검","2025-10-13 09:00","2025-10-17 18:00","2025-10-13 09:00","2025-10-17 18:00","연속"]
[85,"경기북부","구리","미금S/S #4 Sh.R CB","미금 용량부족 차단기 대체공사(72bay)","용량부족 차단기 대체 25CB","2025-10-13 09:00","2025-12-30 18:00","2025-10-15 09:00","2026-01-02 18:00","연속"]
[86,"경기북부","구리","미금성동#2 T/L","미금 용량부족 차단기 대체공사(72bay)","용량부족 차단기 대체 25CB","2025-10-13 09:00","2025-12-30 18:00","2025-10-13 09:00","2025-12-30 18:00","연속"]
[87,"경기북부","구리","미금S/S #3 M.Tr","#3M.Tr 2차 GIS #2DS 불량 가스압력계 교체","#3M.Tr 2차 GIS #2DS 불량 가스압력계 교체","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[88,"경기북부","구리","미금S/S #6 Sh.R CB","2025년 구리전력지사 154kV 이상 GIS 점검공사","관내변전소  GIS 점검(7679)","2025-10-30 09:00","2025-10-30 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[89,"경기북부","구리","미금S/S #5 Sh.R CB","2025년 구리전력지사 154kV 이상 GIS 점검공사","관내변전소  GIS 점검(7579)","2025-10-29 09:00","2025-10-29 18:00","2025-10-14 09:00","2025-10-14 18:00","연속"]
[90,"경기북부","구리","신가평S/S #2 Sh.R CB","`24-25년 구리전력지사 변전협력 총액공사","신가평S/S  73BAY B/F PNL 교체공사","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[91,"경기북부","구리","신가평포천LNGCC#2 T/L","신가평S/S  GIS 인출변경공사(#73, 76BAY)","신가평S/S  GIS 인출변경공사(#73, 76BAY)","2025-10-13 09:00","2025-12-05 18:00","2025-10-13 09:00","2025-12-05 18:00","연속"]
[92,"경기북부","구리","신가평S/S CB 7300","`24-25년 구리전력지사 변전협력 총액공사","신가평S/S  73BAY B/F PNL 교체공사(7300)","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[93,"경기북부","구리","신가평S/S CB 7371","`24-25년 구리전력지사 변전협력 총액공사","신가평S/S  73BAY B/F PNL 교체공사(7371)","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[94,"경기북부","구리","신포천S/S #1 Sh.R CB","25년 구리전력지사  M.Tr, Sh.R 정밀점검공사","#1Sh.R 정밀점검","2025-10-20 09:00","2025-10-22 18:00","2025-10-20 09:00","2025-10-22 18:00","연속"]
[95,"경기북부","직할","신의정부S/S #4 M.Tr","신의정부S/S #4M.Tr 교체공사","장기사용 변압기 교체공사","2025-10-13 09:00","2026-02-27 18:00","2025-10-13 09:00","2026-02-27 18:00","연속"]
[96,"경기북부","직할","신의정부양주#2 T/L"," 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-양주#2 T/L No.1~97","2025-10-21 07:00","2025-10-31 18:00","취소","취소","연속"]
[97,"경기북부","직할","신의정부미금#2 T/L"," 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-미금#2 T/L No.64~68 (子 :  신가평-신의정부#1 T/L No.139~143)","2025-10-17 07:00","2025-10-17 18:00","2025-10-19 09:00","2025-10-19 18:00","연속"]
[98,"경기북부","직할","양주S/S #4 Sh.R CB","양주S/S 동두천CC-양주T/L SW 및 CLR 설치공사(무부하용)"," GIS 증설 * 2CCT","2025-10-31 14:00","2025-10-31 18:00","2025-10-31 14:00","2025-10-31 18:00","연속"]
[99,"경기북부","직할","양주S/S #2 BUS","양주S/S 동두천CC-양주T/L SW 및 CLR 설치공사"," GIS 증설 * 2CCT","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[100,"경기북부","직할","양주S/S #3 M.Tr"," 변압기 보통점검 및 추락방지 장치 설치","변압기 보통점검, 추락방지 장치 설치","2025-10-20 09:00","2025-10-24 18:00","2025-10-20 09:00","2025-10-24 18:00","연속"]
[101,"경기북부","직할","양주중부#2 T/L","양주S/S 동두천CC-양주T/L SW 및 CLR 설치공사(무부하용)"," GIS 증설 * 2CCT","2025-10-31 14:00","2025-10-31 18:00","2025-10-31 14:00","2025-10-31 18:00","연속"]
[102,"경기","군포","서서울#2신성남#1 T/L","서서울2S/S 서서울2-신성남#1T/L 7A71GIS절연열화측정","서서울#2S/S  서서울2-신성남#1T/L 7A71 GIS 콘덴서 절연열화 측정","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[103,"경기","동부","곤지암S/S CB 7271","곤지암S/S 곤지암-여주복합#1,2T/L GIS 조작시험","[곤지암-여주복합#1T/L] 곤지암:7200(조작),7271(조작) [곤지암-여주복합#2T/L] 곤지암:7171(조작)","2025-10-02 07:00","2025-10-02 08:00","2025-10-02 07:00","2025-10-02 08:00","연속"]
[104,"경기","동부","곤지암S/S CB 7200","곤지암S/S 곤지암-여주복합#1,2T/L GIS 조작시험","[곤지암-여주복합#1T/L] 곤지암:7200(조작),7271(조작) [곤지암-여주복합#2T/L] 곤지암:7171(조작)","2025-10-02 08:00","2025-10-02 09:00","2025-10-02 08:00","2025-10-02 09:00","연속"]
[105,"경기","동부","여주C/C CB 7171","여주CC 362kV GIS 7171(하자),7100(하자)","여주CC 362kV GIS 7171(하자),7100(하자)","2025-10-27 09:00","2025-10-27 16:00","2025-10-27 09:00","2025-10-27 16:00","연속"]
[106,"경기","동부","여주C/C CB 7100","여주CC 362kV GIS 7171(하자),7100(하자)","여주CC 362kV GIS 7171(하자),7100(하자)","2025-10-28 09:00","2025-10-28 16:00","2025-10-28 09:00","2025-10-28 16:00","연속"]
[107,"경기","동부","신제천신충주T#1 T/L","추락방지장치 설치공사(신제천-여주CC)","신제천 여주CC 추락방지장치 설치 39기","2025-10-22 07:00","2025-10-24 18:00","취소","취소","연속"]
[108,"경기","동부","신충주여주복합#2 T/L","추락방지장치 설치공사(신충주여주복합#2T/L)","신충주여주복합#2T/L 추락방지장치 설치 39기","2025-10-27 07:00","2025-10-30 18:00","취소","취소","연속"]
[109,"경기","동부","여주C/C CB 7471","여주CC 362kV GIS 7471(하자)","여주CC 362kV GIS 7471(하자)","2025-10-29 09:00","2025-10-29 16:00","2025-10-29 09:00","2025-10-29 16:00","연속"]
[110,"경기","성남","신성남신양재#2 T/L","2024-2025년 성남전력지사 가공송전 협력회사 공사","○ 고정형폴리머 설치공사 - 대상구간 :  신성남-신양재#2T/L No.22 ※ 154kV 신성남-염곡T/L 4회선 구간 - 대상구간 : 154kV 신성남-염곡 #2T/L No.2,12 ※  신성남-신양재T/L 4회선 구간","2025-10-31 07:00","2025-10-31 18:00","2025-10-31 07:00","2025-10-31 18:00","연속"]
[111,"경기","성남","신성남신양재#1 T/L","2024-2025년 성남전력지사 가공송전 협력회사 공사","○ 피뢰기 설치공사 - 대상구간 :  신성남-신양재#1T/L No.1 ○ 고정형폴리머 설치공사 - 대상구간 : 154kV 신성남-염곡#1T/L No.17,20 ※  신성남-신양재T/L 4회선 구간","2025-10-30 07:00","2025-10-30 18:00","2025-10-30 07:00","2025-10-30 18:00","연속"]
[112,"경기","성남","신성남S/S #3 M.Tr","2025년 765kV M.Tr보통/ M.Tr 정밀점검공사","m.tr 정밀점검","2025-10-13 09:00","2025-10-24 18:00","2025-10-13 09:00","2025-10-24 18:00","연속"]
[113,"경기","성남","신성남동서울#2 T/L","2025년 성남전력 변전협력회사 총액공사","7300, 7371 GIS 조작시험, 절연열화","2025-10-14 09:00","2025-10-14 18:00","2025-10-14 09:00","2025-10-14 18:00","연속"]
[114,"경기","성남","신성남S/S #1 M.Tr","25년 성남전력 주변압기  보통, 154kV 정밀/보통점검공사","m.tr 보통점검","2025-10-28 09:00","2025-10-29 18:00","2025-10-28 09:00","2025-10-29 18:00","연속"]
[115,"경기","성남","신수원S/S #2 M.Tr","신수원S/S 154kV 계통조정공사(토목)"," #2M.Tr용 신규GIB 기초작업(토목) (작업시 안전이격용 휴전필요)","2025-10-13 09:00","2025-10-26 18:00","2025-10-13 09:00","2025-10-26 18:00","연속"]
[116,"경기","성남","신안성신수원#2 T/L","수평 추락방지장치 설치공사","24-25년 경기직할 송전협력회사 공사(수평 추락방지장치 설치공사)","2025-10-31 07:00","2025-11-11 18:00","2025-10-31 07:00","2025-11-11 18:00","연속"]
[117,"경기","성남","신안성S/S #75 BUS"," 동용인S/S  GIS 설치공사","○ 신안성S/S : GIS(362kV 63kA 8000A) X 5대 설치 ○ 동용인S/S : GIS(362kV 63kA 6300/4000A) X 12대 설치","2025-10-13 09:00","2025-10-17 18:00","2025-10-13 09:00","2025-10-17 18:00","연속"]
[118,"경기","성남","신안성S/S #70 BUS"," 동용인S/S  GIS 설치공사","○ 신안성S/S : GIS(362kV 63kA 8000A) X 5대 설치 ○ 동용인S/S : GIS(362kV 63kA 6300/4000A) X 12대 설치","2025-10-20 09:00","2025-10-24 18:00","2025-10-20 09:00","2025-10-24 18:00","연속"]
[119,"경기","성남","신용인삼성 T/L","2025년 성남전력 변전협력회사 총액공사","보호반 대체 cvt 하자점검","2025-10-27 07:00","2025-11-07 18:00","2025-10-27 07:00","2025-11-07 18:00","연속"]
[120,"경기","성남","신용인S/S #3 M.Tr","2025년 성남전력 변전협력회사 총액공사","부싱절연유 채유 부싱 절연열화","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[121,"경기","성남","신용인동서울#2 T/L","2025년 성남전력 362, 170kV GIS 보통점검공사","7271, 7200 gis 보통점검, 절연열화","2025-10-16 09:00","2025-10-17 18:00","2025-10-16 09:00","2025-10-17 18:00","연속"]
[122,"경기","직할","아산화성#2 T/L","2024-2025년 평택전력지사 송전정비 협릭회사"," 아산-화성 #2T/L No.122 SB댐퍼 교체 및 No. 129 접지단자 및 SB댐퍼 교체","2025-10-21 08:00","2025-10-23 18:00","2025-10-21 08:00","2025-10-23 18:00","연속"]
[123,"경기","직할","화성S/S #2 M.Tr","화성S/S #2M.Tr 1,2차 부싱 채유 및 절연열화진단","화성S/S #2M.Tr 1,2차 부싱 채유 및 절연열화진단 - 1,2차 A,B,C상","2025-10-22 09:00","2025-10-22 18:00","2025-10-22 09:00","2025-10-22 18:00","연속"]
[124,"경기","직할","화성S/S #1 M.Tr","화성S/S #1M.Tr 1,2차 부싱 채유 및 절연열화진단","화성S/S #1M.Tr 1,2차 부싱 채유 및 절연열화진단 - 1차 B,C상 / 2차 A,B,C상","2025-10-20 09:00","2025-10-20 18:00","2025-10-20 09:00","2025-10-20 18:00","연속"]
[125,"경기","직할","아산화성#1 T/L","화성S/S 아산-화성#1T/L LA, CVT 보통점검","화성 : 아산-화성#1T/L LA, CVT 보통점검","2025-10-20 09:00","2025-10-20 18:00","2025-10-20 09:00","2025-10-20 18:00","연속"]
[126,"경기","평택","고덕2#S/S CB 7500","PNC테크 성능개선(고덕#2-서안성#2T/L 7500)","PNC테크 성능개선(고덕#2-서안성#2T/L 7500)","2025-10-02 08:30","2025-10-02 09:00","2025-10-02 08:30","2025-10-02 09:00","연속"]
[127,"경기","평택","고덕2#S/S CB 7571","PNC테크 성능개선(고덕#2-서안성#2T/L 7571)","PNC테크 성능개선(고덕#2-서안성#2T/L 7571)","2025-10-02 08:00","2025-10-02 08:30","2025-10-02 08:00","2025-10-02 08:30","연속"]
[128,"경기","평택","고덕#2서안성#1 T/L","고덕#2S/S 고덕2-서안성#1T/L 7422 DS 불량조치","고덕#2S/S 고덕2-서안성#1T/L 7422 DS 불량조치","2025-10-14 09:00","2025-10-17 18:00","2025-10-14 09:00","2025-10-17 18:00","연속"]
[129,"경기","평택","고덕#2서안성#2 T/L"," 고덕2-서안성#2T/L 피뢰기 설치공사","No.1~29 피뢰기 설치","2025-10-20 08:00","2025-10-24 18:00","2025-10-20 08:00","2025-10-24 18:00","연속"]
[130,"경기","평택","서안성S/S #1 M.Tr","2025년 평택전력 변전협력회사 총액공사(서안성1)","서안성S/S  #1 M.Tr 보호배전반 대체, #1S.Tr 대체, 2차 GIS 보통점검 ,3차 GIS 보통점검","2025-10-27 09:00","2025-11-07 18:00","2025-10-27 09:00","2025-11-07 18:00","연속"]
[131,"경기","성남","신성남S/S #5 M.Tr","2025년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검(9월 취소, 2일 추가 신청)","2025-10-25 09:00","2025-10-26 18:00","2025-10-25 09:00","2025-10-26 18:00","연속"]
[132,"강원","강릉","신양양S/S CB 7171","2025년 강릉전력지사 변전협력회사 총액공사","362kV GIS 보통점검, 전자변 교체","2025-10-30 10:00","2025-10-30 18:00","2025-10-30 10:00","2025-10-30 18:00","연속"]
[133,"강원","강릉","신양양S/S CB 7100","2025년 강릉전력지사 변전협력회사 총액공사","362kV GIS 보통점검, 전자변 교체","2025-10-31 10:00","2025-10-31 18:00","2025-10-31 10:00","2025-10-31 18:00","연속"]
[134,"강원","강릉","신양양S/S STATCOM CB","신양양S/S STATCOM용  GIS 설치공사","○ 신양양 STATCOM 설비 개체시험 및 연동시험","2025-10-24 18:00","2025-10-31 23:59","2025-10-24 18:00","2025-10-31 23:59","연속"]
[135,"강원","강릉","신양양S/S #2 BUS","신양양S/S STATCOM용  GIS 설치공사","○ 신양양 STATCOM C.Tr 및 GIS(7572CB) 무부하가압","2025-10-23 09:00","2025-10-24 09:00","2025-10-23 09:00","2025-10-24 09:00","연속"]
[136,"강원","강릉","안인개폐소신양양 T/L","신양양S/S STATCOM용  GIS 설치공사","○ 신양양 STATCOM C.Tr 및 GIS 무부하가압","2025-10-22 09:00","2025-10-24 18:00","2025-10-22 09:00","2025-10-24 18:00","연속"]
[137,"강원","강릉","신양양S/S #1 BUS","신양양S/S STATCOM용  GIS 설치공사","○ 신양양 STATCOM C.Tr 및 GIS(7500CB) 무부하가압","2025-10-22 09:00","2025-10-23 09:00","2025-10-22 09:00","2025-10-23 09:00","연속"]
[138,"강원","강릉","신양양S/S #2 M.Tr","2025년 강릉전력지사 변전협력회사 총액공사","362kV COMP 대체 안전조치 휴전","2025-10-20 10:00","2025-10-21 18:00","2025-10-20 10:00","2025-10-21 18:00","매일"]
[139,"강원","강릉","안인개폐소강릉TP#1 T/L","25년 가공송전 순시점검 위탁공사","초기점검(승탑) : No. 15~17","2025-10-13 08:00","2025-10-13 17:00","2025-10-13 08:00","2025-10-13 17:00","연속"]
[140,"강원","강릉","안인개폐소강릉TP#2 T/L","25년 가공송전 순시점검 위탁공사","초기점검(승탑) : No. 15~17","2025-10-14 08:00","2025-10-14 17:00","2025-10-14 08:00","2025-10-14 17:00","연속"]
[141,"강원","강릉","안인개폐소양양PP T/L","2024~2025년 가공송전협력회사 총액공사","○ 추락방지장치 설치공사 안인개폐소양양PP T/L (35, 60, 63)","2025-10-02 08:00","2025-10-02 18:00","2025-10-02 08:00","2025-10-02 18:00","연속"]
[142,"강원","강릉","안인개폐소신양양 T/L","2024~2025년 가공송전협력회사 총액공사","○ 추락방지장치 설치공사 안인개폐소신양양 T/L (35, 60, 63)","2025-10-01 08:00","2025-10-01 18:00","2025-10-01 08:00","2025-10-01 18:00","연속"]
[143,"강원","동해","동해S/S #3 M.Tr","2024~25년 변전협력회사총액공사","붓싱유 채취","2025-10-31 09:00","2025-10-31 18:00","2025-10-31 09:00","2025-10-31 18:00","연속"]
[144,"강원","동해","신제천동해#2 T/L","2024~25년 동해전력지사 가공송전 협력회사 공사","전선접속개소 전선교체","2025-10-13 07:00","2025-10-20 18:00","2025-10-13 07:00","2025-10-20 18:00","연속"]
[145,"강원","태백","신태백한울NP#1 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 신태백-한울NP2 #1 T/L 수평추락방지장치 및 폴리머 점퍼지지애자 설치","2025-10-21 07:00","2025-10-27 18:00","취소","취소","매일"]
[146,"강원","태백","신태백한울NP#1 T/L","신태백S/S STATCOM  GIS 설치공사","- 신태백 STATCOM C.Tr 및 GIS 무부하가압(24hr)","2025-10-22 09:00","2025-10-23 18:00","취소","취소","연속"]
[147,"강원","태백","신태백삼척BP#2T/L","신태백S/S STATCOM  GIS 설치공사","- 신태백 STATCOM C.Tr 및 GIS 무부하가압(24hr)","2025-10-21 09:00","2025-10-23 18:00","취소","취소","연속"]
[148,"강원","태백","신태백S/S #1 BUS","신태백S/S STATCOM  GIS 설치공사","- 신태백 STATCOM C.Tr 및 GIS 무부하가압, 사용전검사","2025-10-21 09:00","2025-10-22 12:00","취소","취소","연속"]
[149,"강원","태백","신태백S/S STATCOM CB","신태백S/S STATCOM  GIS 설치공사","- 신태백 STATCOM 설비 개체시험 및 연동시험","2025-10-27 09:00","2025-11-15 18:00","2025-10-27 09:00","2025-11-15 18:00","연속"]
[150,"강원","태백","신태백한울NP#2 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 신태백-한울NP2 #2 T/L 수평추락방지장치 및 폴리머 점퍼지지애자 설치","2025-10-01 07:00","2025-10-02 18:00","2025-10-01 07:00","2025-10-02 18:00","매일"]
[151,"강원","태백","신태백S/S #2 BUS","신태백S/S STATCOM  GIS 설치공사","- 신태백 STATCOM C.Tr 및 GIS 무부하가압, 사용전검사","2025-10-22 12:00","2025-10-23 18:00","취소","취소","연속"]
[152,"충북","직할","신진천S/S #2 M.Tr","24~25 직할 변전협력회사공사(부싱절연유채유)","신진천S/S  #2 M.Tr 부싱절연유 채유","2025-10-17 10:00","2025-10-17 18:00","2025-10-17 10:00","2025-10-17 18:00","연속"]
[153,"충북","직할","서안성신진천#2 T/L","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  서안성-신진천#2T/L LA 보통점검","2025-10-28 10:00","2025-10-28 18:00","2025-10-28 10:00","2025-10-28 18:00","연속"]
[154,"충북","직할","서안성신진천#1 T/L","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  서안성-신진천#1T/L GIS 보통점검","2025-10-27 10:00","2025-10-27 18:00","2025-10-27 10:00","2025-10-27 18:00","연속"]
[155,"충북","청주","신옥천S/S #2 M.Tr","신옥천S/S  #2M.Tr OLTC 조작불량사항 점검","신옥천S/S  #2M.Tr OLTC 조작불량사항 점검","2025-10-01 08:00","2025-10-01 18:00","2025-10-01 08:00","2025-10-01 18:00","연속"]
[156,"충북","충주","신제천S/S SVC CB","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  신제천 SVC M.Tr 1차 GIS 보통점검","2025-10-10 14:00","2025-10-10 18:00","취소","취소","연속"]
[157,"충북","충주","신제천S/S #2 TCSC CB","2025년 신제천S/S  TCSC 보통점검공사","2025년 신제천S/S  TCSC 보통점검공사","2025-10-13 07:00","2025-10-20 18:00","취소","취소","연속"]
[158,"충북","충주","신제천신영주#2 T/L","2025년 가공송전 순시점검 위탁공사"," 신제천-신영주T/L 정밀점검","2025-10-13 07:00","2025-10-24 18:00","취소","취소","매일"]
[159,"충북","충주","신제천S/S CB 7200","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S 신제천 SVC M.Tr 1차- TIE GIS 보통점검","2025-10-13 10:00","2025-10-13 14:00","취소","취소","연속"]
[160,"충북","충주","신제천신영주#1 T/L","2025년 가공송전 순시점검 위탁공사"," 신제천-신영주T/L 정밀점검","2025-10-27 07:00","2025-11-07 18:00","취소","취소","매일"]
[161,"충북","충주","신제천S/S CB 7471","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  신제천-여주복합T/L GIS 보통점검","2025-10-02 14:00","2025-10-02 18:00","2025-10-02 14:00","2025-10-02 18:00","연속"]
[162,"충북","충주","신제천S/S CB 7A00","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  신제천동해 #2T/L - #4M.Tr 1차 GIS 보통점검","2025-10-02 10:00","2025-10-02 14:00","2025-10-02 10:00","2025-10-02 14:00","연속"]
[163,"충북","충주","신제천S/S CB 7A71","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  신제천-동해 #2TL GIS 보통점검","2025-10-01 14:00","2025-10-01 18:00","취소","취소","연속"]
[164,"충북","충주","신제천S/S CB 7A72","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  #4M.Tr 1차 GIS 보통점검","2025-10-01 09:00","2025-10-01 14:00","2025-10-01 09:00","2025-10-01 14:00","연속"]
[165,"충북","충주","신제천S/S CB 7400","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  신제천-여주복합T/L- TIE GIS 보통점검","2025-10-10 10:00","2025-10-10 14:00","2025-10-10 10:00","2025-10-10 14:00","연속"]
[166,"충북","충주","신충주S/S CB 7100","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  신충주-여주복합#2T/L-#1M.Tr 1차 GIS 보통점검","2025-10-14 10:00","2025-10-14 14:00","2025-10-14 10:00","2025-10-14 14:00","연속"]
[167,"충북","충주","신충주S/S CB 7171","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  신충주-여주복합#2T/L GIS 보통점검","2025-10-14 14:00","2025-10-14 18:00","취소","취소","연속"]
[168,"충북","충주","신충주S/S CB 7172","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  #1 M.Tr 1차 GIS 보통점검","2025-10-15 10:00","2025-10-15 14:00","2025-10-15 10:00","2025-10-15 14:00","연속"]
[169,"충북","충주","신충주S/S CB 7200","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  신충주 T분기T/L-TIE GIS 보통점검","2025-10-15 14:00","2025-10-15 18:00","취소","취소","연속"]
[170,"충북","충주","신충주S/S CB 7271","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  신충주S/S 신충주 T분기T/L GIS 보통점검","2025-10-16 10:00","2025-10-16 14:00","2025-10-16 10:00","2025-10-16 14:00","연속"]
[171,"충북","충주","신충주S/S CB 7400","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  신제천-신충주#2T/L-TIE GIS 보통점검","2025-10-20 10:00","2025-10-20 14:00","2025-10-20 10:00","2025-10-20 14:00","연속"]
[172,"충북","충주","신충주S/S CB 7371","신충주S/S  73BAY BF 보호반 대체","신충주S/S  73BAY BF 보호반 대체","2025-10-21 09:00","2025-10-24 18:00","2025-10-21 09:00","2025-10-24 18:00","연속"]
[173,"충북","충주","신충주S/S #2 M.Tr","신충주S/S  73BAY BF 보호반 대체","신충주S/S  73BAY BF 보호반 대체","2025-10-21 09:00","2025-10-24 18:00","2025-10-21 09:00","2025-10-24 18:00","연속"]
[174,"충북","충주","신충주S/S CB 7600","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  #4 M.Tr 1차 TIE GIS 보통점검","2025-10-21 10:00","2025-10-21 14:00","2025-10-21 10:00","2025-10-21 14:00","연속"]
[175,"충북","충주","신충주S/S CB 7672","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S #4 M.Tr 1차 GIS 보통점검","2025-10-21 14:00","2025-10-21 18:00","취소","취소","연속"]
[176,"충북","충주","신충주T신충주 T/L","2024~2025년 충주전력지사 송전협력회사 공사(병가)","2024~2025년 충주전력지사 송전협력회사 공사 스페이서 교체( 신제천-신충주#2 T/L No.175~176 병가선로 휴전)","2025-10-27 07:00","2025-10-30 18:00","취소","취소","매일"]
[177,"충북","충주","신제천신충주#2 T/L","신충주S/S  74BAY BF 보호반 대체","신충주S/S  74BAY BF 보호반 대체","2025-10-27 09:00","2025-10-30 18:00","취소","취소","연속"]
[178,"충북","충주","신충주S/S #3 M.Tr","신충주S/S  74BAY BF 보호반 대체","신충주S/S  74BAY BF 보호반 대체","2025-10-27 09:00","2025-10-30 18:00","취소","취소","연속"]
[179,"대전세종충남","대전","신계룡S/S CB 7171","[즉시가압O]신계룡S/S  신계룡-청양T/L GIS 보통점검","[즉시가압O]신계룡S/S  신계룡-청양T/L GIS 보통점검","2025-10-28 09:00","2025-10-28 18:00","2025-10-28 09:00","2025-10-28 18:00","연속"]
[180,"대전세종충남","대전","신계룡S/S CB 7100","[즉시가압o]신계룡S/S  신계룡-청양-TIE GIS 보통점검","[즉시가압o]신계룡S/S  신계룡-청양-TIE GIS 보통점검","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[181,"대전세종충남","대전","신계룡S/S CB 7271","[즉시가압O]신계룡S/S  신옥천-신계룡T/L GIS 보통점검","[즉시가압O]신계룡S/S  신옥천-신계룡T/L GIS 보통점검","2025-10-29 09:00","2025-10-29 18:00","2025-10-29 09:00","2025-10-29 18:00","연속"]
[182,"대전세종충남","대전","신계룡S/S #2 M.Tr","[즉시가압O]신계룡S/S 23kV #2S.Tr 초기점검 및 3차차단기점검","[즉시가압O]신계룡S/S 23kV #2S.Tr 초기점검 및 3차차단기점검","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[183,"대전세종충남","대전","신계룡S/S #1 M.Tr","[즉시가압O]신계룡S/S 23kV #1S.Tr 초기점검 및 3차차단기점검","[즉시가압O]신계룡S/S 23kV #1S.Tr 초기점검 및 3차차단기점검","2025-10-31 09:00","2025-10-31 18:00","2025-10-31 09:00","2025-10-31 18:00","연속"]
[184,"대전세종충남","서산","당진T/P #71 M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 당진화력S/S  #71TieTr 보호반 성능개선","2025-10-01 09:30","2025-10-01 18:00","2025-10-01 09:30","2025-10-01 18:00","연속"]
[185,"대전세종충남","서산","당진T/P CB 7271","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 당진화력S/S 765kV #1Ti-eTr 2차 7271 CB 전자변 교체","2025-10-15 09:30","2025-10-15 18:00","2025-10-15 09:30","2025-10-15 18:00","연속"]
[186,"대전세종충남","서산","당진T/P CB 7200","당진화력S/S  차단기 조작시험","(즉시가압 가능)당진화력S/S 765kV #1 Tie.Tr 2차-2호기 1차 TIE CB 개폐타임 측정","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[187,"대전세종충남","서산","당진T/P #72 M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 당진화력S/S  #72TieTr 보호반 성능개선","2025-10-02 09:30","2025-10-02 18:00","2025-10-02 09:30","2025-10-02 18:00","연속"]
[188,"대전세종충남","서산","북당진S/S #1 M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 북당진S/S  #1M.Tr 보호반 성능개선","2025-10-17 09:30","2025-10-17 18:00","2025-10-17 09:30","2025-10-17 18:00","연속"]
[189,"대전세종충남","서산","신당진개폐소 CB 7B71","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진개폐소 현대제철T/L 7B71, 7B00 GIS 균압콘덴서 절연열화 측정","2025-10-23 09:30","2025-10-23 14:00","2025-10-23 09:30","2025-10-23 16:00","연속"]
[190,"대전세종충남","서산","신당진개폐소 CB 7B00","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진개폐소 현대제철T/L 7B71, 7B00 GIS 균압콘덴서 절연열화 측정","2025-10-23 14:00","2025-10-23 18:00","2025-10-24 09:30","2025-10-24 16:00","연속"]
[191,"대전세종충남","서산","신당진개폐소 #7B BUS","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신당진개폐소  7B BUS PT ,ES부 가스누기 보수공사 - 7D71 GIS 이용 무부하가압 예정으로 추가 휴전신청","2025-10-27 09:30","2025-10-31 18:00","2025-10-27 09:30","2025-10-31 18:00","연속"]
[192,"대전세종충남","서산","신당진개폐소 CB 7D71","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진개폐소  7B BUS PT ,ES부 가스누기 보수공사 - 7D71 GIS 이용 무부하가압 예정으로 추가 휴전신청","2025-10-31 14:00","2025-10-31 15:00","2025-10-31 16:00","2025-10-31 17:00","연속"]
[193,"대전세종충남","서산","신당진S/S CB 7171","신당진S/S  차단기 조작시험","(즉시가압 가능)신당진S/S  7171T/L CB 개폐타임 측정","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[194,"대전세종충남","서산","신당진S/S CB 7772","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신당진S/S  7752 DS 가스누기보수공사 - #76BUS, 7872 GIS 이용하여 무부하가압 예정으로 추가 휴전신청","2025-10-20 09:30","2025-10-22 18:00","2025-10-20 09:30","2025-10-22 18:00","연속"]
[195,"대전세종충남","서산","신당진S/S #76 BUS","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진S/S  7752 DS 가스누기보수공사 - #76BUS, 7872 GIS 이용하여 무부하가압 예정으로 추가 휴전신청","2025-10-22 14:00","2025-10-22 15:00","2025-10-22 16:00","2025-10-22 17:00","연속"]
[196,"대전세종충남","서산","신당진S/S CB 7872","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진S/S  7752 DS 가스누기보수공사 - #76BUS, 7872 GIS 이용하여 무부하가압 예정으로 추가 휴전신청","2025-10-22 14:00","2025-10-22 15:00","2025-10-22 16:00","2025-10-22 17:00","연속"]
[197,"대전세종충남","서산","신서산S/S #4 Sh.R CB","신서산S/S  차단기 조작시험","(즉시가압 가능)신서산S/S  #4 Sh.R 7779CB 개페타임 측정","2025-10-23 09:00","2025-10-23 18:00","2025-10-23 09:00","2025-10-23 18:00","연속"]
[198,"대전세종충남","서산","신서산S/S CB 7700","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신서산S/S  7700 GIS 차단기 유압스위치 불량교체","2025-10-14 09:30","2025-10-14 18:00","2025-10-14 09:30","2025-10-14 18:00","연속"]
[199,"대전세종충남","서산","태안T/P SEC CB 70710","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 태안화력S/S  7151 DS 가스누기 보수공사 -  70-71-0 SEC GIS 이용 무부하가압 예정으로 추가 휴전 신청","2025-10-22 09:30","2025-10-24 18:00","2025-10-22 09:30","2025-10-24 18:00","연속"]
[200,"대전세종충남","서산","태안T/P CB 7100","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 태안화력S/S  7151 DS 가스누기 보수공사","2025-10-22 09:30","2025-10-24 18:00","2025-10-22 09:30","2025-10-24 18:00","연속"]
[201,"대전세종충남","서산","태안T/P #70 BUS","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 태안화력S/S  7151 DS 가스누기 보수공사","2025-10-22 09:30","2025-10-24 18:00","2025-10-22 09:30","2025-10-24 18:00","연속"]
[202,"대전세종충남","서산","태안T/P CB 7300","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안T/P 3호기 7372, 7300 GIS 균압콘덴서 절연열화 측정","2025-10-06 14:00","2025-10-06 18:00","2025-10-06 14:00","2025-10-06 18:00","연속"]
[203,"대전세종충남","서산","태안T/P CB 7372","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안T/P 3호기 7372, 7300 GIS 균압콘덴서 절연열화 측정","2025-10-06 09:30","2025-10-06 14:00","2025-10-06 09:30","2025-10-06 14:00","연속"]
[204,"대전세종충남","서산","태안T/P CB 7671","25년 서산P/O  GIS 보통점검공사","(즉시가압가능) 태안화력S/S 7671 GIS 보통점검","2025-10-01 09:30","2025-10-02 18:00","2025-10-01 09:30","2025-10-02 18:00","연속"]
[205,"대전세종충남","천안","신온양신탕정#2 T/L","(9월 취소시) 신온양S/S #78B/F 보호배전반 교체","(9월 취소시)(즉시가압불가)(장기미교체대상)신온양S/S #78B/F 보호배전반 교체","2025-10-15 09:00","2025-10-19 15:00","2025-10-15 09:00","2025-10-19 16:00","연속"]
[206,"대전세종충남","천안","신온양서서울#2 T/L","(협력)  신온양-서서울T/L 수평 추락방지장치 설치공사","(협력)  신온양-서서울T/L 수평 추락방지장치 설치공사 - No.1-25","2025-10-13 08:00","2025-10-17 18:00","2025-10-20 08:00","2025-10-24 18:00","매일"]
[207,"대전세종충남","천안","신온양서서울#1 T/L","(9월 취소시) 신온양S/S #78B/F 보호배전반 교체","(9월 취소시)(즉시가압불가)(장기미교체대상)신온양S/S #78B/F 보호배전반 교체","2025-10-15 09:00","2025-10-19 15:00","2025-10-15 09:00","2025-10-19 16:00","연속"]
[208,"대전세종충남","천안","신온양S/S  예비 M.Tr","25년 천안PO 주변압기 정밀 및 보통점검 공사","신온양S/S  예비M.Tr 보통점검","2025-10-21 09:00","2025-10-21 18:00","취소","취소","연속"]
[209,"대전세종충남","천안","신온양S/S #3 M.Tr","25년 천안PO 주변압기 정밀 및 보통점검 공사","신온양S/S  3M.Tr(A,C) 보통점검","2025-10-20 09:00","2025-10-21 18:00","2025-10-20 09:00","2025-10-21 18:00","연속"]
[210,"대전세종충남","천안","신온양신탕정#1 T/L","신탕정S/S  #72bay B/F 노후 보호배전반 대체","(9월 취소시)(즉시가압불가)(장기미교체대상)신탕정S/S  #72bay B/F 노후 보호배전반 대체","2025-10-10 09:00","2025-10-14 18:00","2025-10-10 09:00","2025-10-14 18:00","연속"]
[211,"대전세종충남","천안","신탕정S/S #2 M.Tr","신탕정S/S  #72bay B/F 노후 보호배전반 대체","(9월취소시)(즉시가압불가)(장기미교체대상)신탕정S/S  72bay B/F 노후 보호배전반 대체","2025-10-10 09:00","2025-10-14 18:00","2025-10-10 09:00","2025-10-14 18:00","연속"]
[212,"대전세종충남","천안","아산S/S #2 M.Tr","(9월 취소시)아산S/S  #2M.Tr 부싱절연유 채유","(9월 취소시)아산S/S  #2M.Tr 부싱절연유 채유","2025-10-17 09:00","2025-10-17 18:00","2025-10-17 09:00","2025-10-17 18:00","연속"]
[213,"대전세종충남","천안","아산S/S  #2 M.Tr 예비","25년 천안PO 주변압기 정밀 및 보통점검 공사","아산S/S  예비변압기 보통점검","2025-10-17 09:00","2025-10-17 18:00","취소","취소","연속"]
[214,"대전세종충남","천안","아산S/S #3 M.Tr","25년 천안PO 주변압기 정밀 및 보통점검 공사","아산S/S  #3M.Tr 보통점검","2025-10-15 09:00","2025-10-16 18:00","2025-10-15 09:00","2025-10-16 18:00","연속"]
[215,"대전세종충남","천안","아산S/S #1 M.Tr","25년 천안PO 주변압기 정밀 및 보통점검 공사","아산S/S  #1M.Tr 보통점검","2025-10-13 09:00","2025-10-14 18:00","2025-10-13 09:00","2025-10-14 18:00","연속"]
[216,"대전세종충남","천안","아산S/S #4 M.Tr","아산S/S  #4 M.Tr 부싱절연유 채유","아산S/S  #4 M.Tr 부싱절연유 채유","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[217,"대전세종충남","청양","보령T/P CB 7271","[GIS정밀점검공사]청양P/O 362kV GIS 정밀점검 공사","[GIS정밀점검공사]보령화력  7271 GIS","2025-10-13 09:00","2025-10-17 18:00","2025-10-13 09:00","2025-10-17 18:00","연속"]
[218,"대전세종충남","청양","청양보령TP#1 T/L","[송전][즉시가압O] 아산-보령 등 4개T/L 항공구 설치공사"," 청양-보령화력#1T/L 항공구 설치공사","2025-10-02 08:00","2025-10-02 18:00","2025-10-02 08:00","2025-10-02 18:00","매일"]
[219,"대전세종충남","청양","아산보령TP#1 T/L","[변전내장화공사]보령화력  GIS LA & PT 내장화 공사","[변전내장화공사]보령화력  GIS LA & PT 내장화 공사 대상 : 보령연락#1T/L, 아산-보령화력#1T/L","2025-10-26 16:00","2025-11-01 06:00","2025-10-26 16:00","2025-11-01 06:00","연속"]
[220,"대전세종충남","청양","보령T/P CB 7100","[GIS정밀점검공사]청양P/O 362kV GIS 정밀점검 공사","[GIS정밀점검공사]보령화력  7100GIS","2025-10-23 09:00","2025-10-31 18:00","2025-10-23 09:00","2025-10-31 18:00","연속"]
[221,"대전세종충남","청양","아산보령TP#2 T/L","[송전][즉시가압O] 아산-보령 등 4개T/L 항공구 설치공사"," 아산-보령화력#2T/L 항공구 설치공사","2025-10-01 08:00","2025-10-01 18:00","2025-10-01 08:00","2025-10-01 18:00","매일"]
[222,"대전세종충남","청양","보령TP보령CC#1 T/L","[변전내장화공사]보령화력  GIS LA & PT 내장화 공사","[변전내장화공사]보령화력  GIS LA & PT 내장화 공사 대상 : 보령연락#1T/L, 아산-보령화력#1T/L","2025-10-19 16:00","2025-10-25 06:00","2025-10-19 17:00","2025-10-25 06:00","연속"]
[223,"대전세종충남","청양","청양신온양#1 T/L","[변전총액] 청양P/O 변전협력 총액공사"," 73BAY BF PNL 교체작업","2025-10-20 09:00","2025-10-24 18:00","취소","취소","연속"]
[224,"대전세종충남","청양","청양S/S #2 M.Tr","청양S/S  #1M.Tr 교체 및 3차측 현대화공사","#2M.Tr 3차측 현대화 -옥외철구 설비 철거 - 3차측 GIS 설치(GPT 둥)","2025-10-20 09:00","2025-12-05 18:00","2025-10-20 09:00","2025-12-05 18:00","연속"]
[225,"대전세종충남","청양","청양군산#2 T/L","[변전총액] 청양P/O 변전협력 총액공사"," 73BAY BF PNL 교체작업","2025-10-20 09:00","2025-10-24 18:00","취소","취소","연속"]
[226,"대전세종충남","청양","신옥천청양 T/L","[송전][즉시가압O] 신옥천-청양등8개T/L 추락방지설치공사","[송전][즉시가압O] 신옥천-청양 등 8개T/L 추락방지 설치공사","2025-10-20 07:00","2025-10-24 18:00","취소","취소","매일"]
[227,"대전세종충남","청양","청양S/S SEC CB 75760","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  #75-#76 SEC GIS 차단기 조작시험 (75-76)","2025-10-01 08:30","2025-10-01 10:00","2025-10-01 08:30","2025-10-01 10:00","연속"]
[228,"대전세종충남","청양","청양S/S SEC CB 70710","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  #70-#71 SEC GIS 차단기 조작시험 (70-71)","2025-10-01 07:00","2025-10-01 08:30","2025-10-01 07:00","2025-10-01 08:30","연속"]
[229,"대전세종충남","청양","청양S/S CB 7172","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  7172 GIS 차단기 조작시험","2025-10-31 08:30","2025-10-31 10:00","2025-10-31 08:30","2025-10-31 10:00","연속"]
[230,"전북","직할","신남원한빛NP#2 T/L","154kV 고창-영광T/L No.45~142 선종교체공사","○ 154kV 고창-영광T/L 선종교체공사 - No.45~142 전력선 교체(ACSR 330㎟ -> ASCC 430㎟)","2025-10-27 06:00","2025-11-21 18:00","취소","취소","연속"]
[231,"광주전남","강진","신강진광양#1 T/L","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-10-20 08:00","2025-10-31 18:00","취소","취소","연속"]
[232,"광주전남","강진","신강진S/S #3 M.Tr","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-10-20 08:00","2025-10-31 18:00","취소","취소","연속"]
[233,"광주전남","강진","신강진S/S #1 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. 신강진S/S #1M.Tr,B,C상 보통점검 ※ 거래소 요청 시 휴전일정 협의 가능","2025-10-13 08:00","2025-10-14 18:00","2025-10-13 08:00","2025-10-14 18:00","연속"]
[234,"광주전남","강진","신화순신강진#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","수직,수평 추락방지장치 설치공사, 즉시가압 불가하나, 1시간 내 가압가능","2025-10-14 07:00","2025-11-10 18:00","2025-10-14 07:00","2025-11-10 18:00","매일"]
[235,"광주전남","광주","신남원신광주#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#2T/L 116~164호","2025-10-20 08:00","2025-10-24 18:00","취소","취소","매일"]
[236,"광주전남","광주","신남원신광주#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#1T/L 116~164호","2025-10-13 08:00","2025-10-17 18:00","취소","취소","매일"]
[237,"광주전남","광주","신광주한빛NP#2 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주변전소 72BAY B/F반 대체","2025-10-13 09:00","2025-10-17 18:00","취소","취소","연속"]
[238,"광주전남","광주","신광주S/S #3 M.Tr","3M.Tr 변압기보호반 장기사용 교체","3M.Tr 변압기보호반 장기사용 교체(9월 휴전 불가대비 신청)","2025-10-20 08:00","2025-10-24 18:00","2025-10-20 08:00","2025-10-24 18:00","연속"]
[239,"광주전남","광주","신광주S/S #1 M.Tr","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  #1M.Tr GIS 2차 보통점검","2025-10-20 09:00","2025-10-20 18:00","2025-10-20 09:00","2025-10-20 18:00","연속"]
[240,"광주전남","광주","신광주S/S CB 7271","2024~25년 광주전력지사 변전협력회사 공사","2024~25년 광주전력지사 변전협력회사 공사 1. 신광주S/S 7100CB, 7271CB, 7472CB 차단기 조작시험","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[241,"광주전남","광주","신광주S/S CB 7472","2024~25년 광주전력지사 변전협력회사 공사","2024~25년 광주전력지사 변전협력회사 공사 1. 신광주S/S 7100CB, 7271CB, 7472CB 차단기 조작시험","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[242,"광주전남","광주","신광주S/S CB 7100","2024~25년 광주전력지사 변전협력회사 공사","2024~25년 광주전력지사 변전협력회사 공사 1. 신광주S/S 7100CB, 7271CB, 7472CB 차단기 조작시험","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[243,"광주전남","광주","신화순S/S #3 M.Tr","2024-2025년도 광주전력지사 변전협력공사 총액공사","신화순변전소 75BAY B/F반 PNL 대체 - 7200, 7572, 6433, 4384, 4389-1,2CB 휴전 - (신)B/F PNL 설치 및 제어케이블 결선 - (주)PNL 철거 - 조작 및 연동시험 등","2025-10-20 08:00","2025-10-24 18:00","2025-10-20 08:00","2025-10-24 18:00","연속"]
[244,"광주전남","목포","한빛1NP한빛2NP#2 T/L","2025년 목포전력지사 변전협력회사 총액공사","리액터 및 LA 점검","2025-10-21 10:00","2025-10-21 18:00","2025-10-21 10:00","2025-10-21 18:00","연속"]
[245,"광주전남","목포","한빛1NP한빛2NP#1 T/L","2025년 목포전력지사 변전협력회사 총액공사","리액터 및 LA 점검","2025-10-20 10:00","2025-10-20 18:00","2025-10-20 10:00","2025-10-20 18:00","연속"]
[246,"광주전남","목포","한빛2N/P CB 7900","한빛4호기 계획예방정비(O/H) 휴전","한빛4호기 계획예방정비(O/H) 휴전","2025-10-26 09:00","2025-11-17 18:00","2025-10-26 09:00","2025-11-17 18:00","연속"]
[247,"광주전남","목포","한빛2N/P CB 7A00","한빛4호기 계획예방정비(O/H) 휴전","한빛4호기 계획예방정비(O/H) 휴전","2025-10-25 09:00","2025-12-21 18:00","2025-10-25 09:00","2025-12-21 18:00","연속"]
[248,"광주전남","목포","한빛2N/P CB 7A71","한빛4호기 계획예방정비(O/H) 휴전","한빛4호기 계획예방정비(O/H) 휴전","2025-10-25 09:00","2025-12-21 18:00","2025-10-25 09:00","2025-12-21 18:00","연속"]
[249,"광주전남","목포","한빛2N/P CB 7971","한빛4호기 계획예방정비(O/H) 휴전","한빛4호기 계획예방정비(O/H) 휴전","2025-10-26 09:00","2025-11-17 18:00","2025-10-26 09:00","2025-11-17 18:00","연속"]
[250,"광주전남","순천","광양CC여수TP#1 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #1T/L 폴리머점퍼지지애자 설치","2025-10-20 07:00","2025-10-22 18:00","2025-10-20 07:00","2025-10-22 18:00","매일"]
[251,"광주전남","순천","광양CC여수TP#2 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #2T/L 폴리머점퍼지지애자 설치","2025-10-23 07:00","2025-10-23 18:00","2025-10-23 07:00","2025-10-23 18:00","연속"]
[252,"광주전남","순천","광양C/C CB 7272","24-25년 순천전력지사 변전협력회사 공사","광양CC 7272 GIS 보통점검","2025-10-20 09:00","2025-10-20 18:00","2025-10-20 09:00","2025-10-20 18:00","연속"]
[253,"광주전남","순천","신남원광양#2 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가) ※주말 미작업","2025-10-23 07:00","2025-10-31 18:00","취소","취소","매일"]
[254,"광주전남","순천","광양하동TP#1 T/L","코타핀 교체(광양-하동#1)","코타핀 교체","2025-10-21 07:00","2025-10-21 12:00","취소","취소","연속"]
[255,"광주전남","순천","신강진광양#2 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치 ※주말미작업","2025-10-23 07:00","2025-10-31 18:00","2025-10-23 07:00","2025-10-31 18:00","매일"]
[256,"광주전남","순천","광양율촌CC T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가) ※주말 미작업","2025-10-23 07:00","2025-10-31 18:00","2025-10-23 07:00","2025-10-31 18:00","매일"]
[257,"광주전남","순천","광양S/S #2 M.Tr","광양변전소 #2M.Tr 부싱절연유 이상 관련 부싱 점검 후 교체","광양변전소 #2M.Tr 부싱절연유 이상 관련 부싱 점검 후 교체","2025-10-27 08:00","2025-10-31 19:00","2025-10-27 08:00","2025-10-31 19:00","연속"]
[258,"광주전남","순천","광양S/S CB 7571","24-25년 순천전력지사 변전협력회사 공사","광양S/S 신강진-광양#1T/L(7571) GIS 초기점검","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[259,"광주전남","순천","광양S/S CB 7500","24-25년 순천전력지사 변전협력회사 공사","광양S/S 신강진-광양#1T/L(7500) GIS 초기점검","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[260,"광주전남","순천","광양S/S CB 7771","24-25년 순천전력지사 변전협력회사 공사","광양S/S 광양-하동TP#2T/L(7771) GIS 보통점검","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[261,"광주전남","순천","광양여수TP T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가) ※주말 미작업","2025-10-14 07:00","2025-10-22 18:00","2025-10-14 07:00","2025-10-22 18:00","매일"]
[262,"광주전남","순천","신강진광양#1 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치 ※주말미작업","2025-10-14 07:00","2025-10-22 18:00","2025-10-14 07:00","2025-10-22 18:00","매일"]
[263,"광주전남","순천","신남원광양#1 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가) ※주말미작업","2025-10-14 07:00","2025-10-22 18:00","취소","취소","매일"]
[264,"광주전남","순천","여수T/P #3 M.Tr","2025년 순천전력지사  M.Tr 정밀점검공사","여수화력S/S  #3M.Tr 정밀점검","2025-10-13 09:00","2025-10-17 18:00","취소","취소","연속"]
[265,"광주전남","순천","여수T/P #1 M.Tr","24-25년 순천전력지사 변전협력회사 공사","여수화력S/S #1M.Tr,B상 1차부싱 대체","2025-10-20 09:00","2025-10-24 18:00","2025-10-20 09:00","2025-10-24 18:00","연속"]
[266,"광주전남","순천","여수T/P #2 M.Tr","24-25년 순천전력지사 변전협력회사 공사","3차 DS과열관련 조치","2025-10-27 09:00","2025-10-28 18:00","2025-10-27 09:00","2025-10-28 18:00","연속"]
[267,"광주전남","순천","율촌C/C CB 7271","24-25년 순천전력지사 변전협력회사 공사","율촌CC 7271 CB 조작시험","2025-10-14 09:00","2025-10-14 18:00","2025-10-14 09:00","2025-10-14 18:00","연속"]
[268,"광주전남","순천","율촌C/C CB 7200","24-25년 순천전력지사 변전협력회사 공사","율촌CC 7200 CB 조작시험","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[269,"광주전남","순천","율촌C/C CB 7272","24-25년 순천전력지사 변전협력회사 공사","율촌CC 7272 CB 조작시험","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[270,"광주전남","순천","율촌C/C CB 7172","24-25년 순천전력지사 변전협력회사 공사","율촌CC 7172 CB 조작시험","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[271,"대구","경산","신경산S/S #2 M.Tr","24~25년 경산P/O 변전협력회사 총액공사","- 기기점검 및 실비교체","2025-10-14 09:30","2025-10-15 18:00","2025-10-14 09:30","2025-10-15 18:00","연속"]
[272,"대구","경산","신경산S/S #4 M.Tr","24~25년 경산P/O 변전협력회사 총액공사","- 기기점검 및 실비교체","2025-10-21 09:30","2025-10-22 18:00","2025-10-21 09:30","2025-10-22 18:00","연속"]
[273,"대구","달성","서대구고령#2 T/L","[TEST] 고령S/S 서대구-고령#2T/L 무부하가압선로","[TEST] 고령S/S 서대구-고령#2T/L 무부하가압선로","2025-10-03 17:00","2025-10-03 18:00","2025-10-03 17:00","2025-10-03 18:00","연속"]
[274,"대구","달성","서대구고령#1 T/L","고령S/S 서대구-고령#1T/L PT 초기점검","고령S/S 서대구-고령#1T/L PT 초기점검","2025-10-20 09:00","2025-10-20 18:00","2025-10-20 09:00","2025-10-20 18:00","연속"]
[275,"대구","달성","북경남고령#1 T/L","2024~2025 달성전력지사 가공송전협력회사공사"," 북경남-고령 #1T/L 76호 점퍼선 교체(A,B,C상 전체)","2025-10-01 08:00","2025-10-01 18:00","2025-10-01 08:00","2025-10-01 18:00","연속"]
[276,"대구","달성","북경남고령#2 T/L","고령S/S 북경남-고령#2T/L 정밀점검","고령S/S 북경남-고령#2T/L 정밀점검","2025-10-13 09:00","2025-10-17 18:00","2025-10-13 09:00","2025-10-17 18:00","연속"]
[277,"대구","달성","북경남고령#2 T/L"," 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 북경남-대구#2T/L 피뢰기 및 조류착지방지장치 설치 - 작업자 안전확보차","2025-10-22 07:00","2025-10-23 18:00","2025-10-22 07:00","2025-10-23 18:00","연속"]
[278,"대구","달성","서대구고령#2 T/L","고령S/S 서대구-고령#2T/L PT,LA 초기점검","고령S/S 서대구-고령#2T/L PT,LA 초기점검","2025-10-21 09:00","2025-10-21 18:00","2025-10-21 09:00","2025-10-21 18:00","연속"]
[279,"대구","달성","북경남대구#2 T/L"," 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 북경남-대구#2T/L 피뢰기 및 조류착지방지장치 설치","2025-10-20 07:00","2025-10-23 18:00","2025-10-20 07:00","2025-10-23 18:00","연속"]
[280,"대구","달성","대구S/S #1 M.Tr","대구S/S #1M.Tr 정밀점검","대구S/S #1M.Tr 정밀점검","2025-10-13 09:00","2025-10-19 18:00","2025-10-13 09:00","2025-10-19 18:00","연속"]
[281,"대구","달성","신경산대구#1 T/L","[TEST] 대구S/S #1M.Tr 정밀점검 무부하가압선로","[TEST] 대구S/S #1M.Tr 정밀점검 무부하가압선로","2025-10-19 17:00","2025-10-19 18:00","2025-10-19 17:00","2025-10-19 18:00","연속"]
[282,"대구","칠곡","서대구S/S #1 M.Tr","서대구S/S  #1M.Tr, LA, 3차 SIS 초기점검","서대구S/S  #1M.Tr, LA, 3차 SIS 초기점검","2025-10-13 09:00","2025-10-15 18:00","2025-10-13 09:00","2025-10-15 18:00","연속"]
[283,"대구","포항","신포항신월성NP#3 T/L","154kV 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 울주-월성NP#1T/L 추락방지장치 설치[안전확보]","2025-10-01 08:00","2025-10-02 18:00","2025-10-01 08:00","2025-10-02 18:00","연속"]
[284,"대구","포항","신포항신영일 T/L","2024~25년도 포항전력지사 변전협력회사 공사","신포항S/S 7100,7171 GIS 조작시험 LA, PT 보통점검 신영일S/S 7771 GIS 조작시험, LA, PT 하자점검","2025-10-15 09:00","2025-10-16 18:00","2025-10-15 09:00","2025-10-16 18:00","연속"]
[285,"대구","포항","신포항면봉산풍력 T/L","2024~25년 포항전력지사 송전 협력회사 공사","스페이서댐퍼 교체 및 전력선 소손개소 보수","2025-10-09 07:00","2025-10-09 18:00","2025-10-22 07:00","2025-10-22 18:00","연속"]
[286,"대구","포항","신포항S/S CB 7672","신포항S/S #5M.Tr 증설공사(일반도급)","#5M.Tr 증설용  GCB 기초 공사 시행","2025-10-02 09:00","2025-10-24 18:00","2025-10-17 18:00","2025-11-07 18:00","연속"]
[287,"대구","포항","월성N/P CB 7672","2024~2025년 포항전력지사 변전협력회사 공사","월성S/Y 7671, 7600, 7672 GIS 보통점검","2025-10-14 09:00","2025-10-15 18:00","2025-10-14 09:00","2025-10-15 18:00","연속"]
[288,"대구","포항","월성N/P CB 7671","2024~2025년 포항전력지사 변전협력회사 공사","월성S/Y 7671, 7600, 7672 GIS 보통점검","2025-10-14 09:00","2025-10-15 18:00","2025-10-14 09:00","2025-10-15 18:00","연속"]
[289,"대구","포항","월성N/P SEC CB 75760","2024~25년도 포항전력지사 변전협력회사 공사","75-76 GIS 조작시험","2025-10-15 13:00","2025-10-15 18:00","2025-10-15 13:00","2025-10-15 18:00","연속"]
[290,"경북","구미","북대구선산 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 서대구-선산, 선산분기T/L 수직 및 수평추락방지장치 설치공사 -  서대구-선산T/L No.106~31 -  선산분기T/L No.107","2025-10-13 07:00","2025-10-24 18:00","2025-10-13 07:00","2025-10-24 18:00","연속"]
[291,"경북","구미","서대구선산#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 서대구-선산, 선산분기T/L 수직 및 수평추락방지장치 설치공사 -  서대구-선산T/L No.106~31 -  선산분기T/L No.107","2025-10-13 07:00","2025-10-24 18:00","2025-10-13 07:00","2025-10-24 18:00","연속"]
[292,"경북","구미","선산S/S #3 M.Tr","2025년 구미전력지사  주변압기 및 OLTC 정밀점검","- M.Tr 정밀점검 [발주] - OLTC 정밀점검 - 3차 LA 보통점검 - 1차 A상,B상 부싱절연유 채유 - 2차 부싱절연유 채유 - 변압기 상부추락방지장치 설치 [협력]","2025-10-13 09:00","2025-10-31 18:00","2025-10-13 09:00","2025-10-31 18:00","연속"]
[293,"경북","영주","신영주S/S CB 7371","2025년 영주전력지사  GIS 정밀점검","-7371CB GIS 정밀점검","2025-10-13 09:00","2025-10-15 19:00","2025-10-13 09:00","2025-10-15 19:00","연속"]
[294,"경북","영주","신영주S/S CB 7171","2025년 영주전력지사  GIS 정밀점검공사","-7171CB GIS 정밀점검","2025-10-01 09:00","2025-10-03 19:00","2025-10-01 09:00","2025-10-03 19:00","연속"]
[295,"경북","영주","신영주S/S #2 TCSC CB","24-25년 영주전력지사 변전협력회사 총액공사","- #2TCSC GIB 보통점검","2025-10-28 09:00","2025-10-28 18:00","취소","취소","연속"]
[296,"경북","영주","신영주S/S STATCOM CB","2025년 영주전력지사  GIS 정밀점검공사","-7952DS 누기개소 보수","2025-10-23 09:00","2025-10-24 18:00","취소","취소","연속"]
[297,"경북","영주","신영주S/S #1 TCSC CB","24-25년 영주전력지사 변전협력회사 총액공사","- #1TCSC GIB 보통점검","2025-10-27 09:00","2025-10-27 18:00","취소","취소","연속"]
[298,"경북","영주","신영주안동CC T/L","2025년 영주전력지사  GIS 정밀점검공사","-7400CB 정밀점검 후  신영주-안동CC T/L 이용 무부하가압(4시간)","2025-10-25 14:00","2025-10-25 18:30","2025-10-26 01:00","2025-10-26 05:00","연속"]
[299,"경북","영주","신영주S/S CB 7400","2025년 영주전력지사  GIS 정밀점검공사","-7400CB GIS 정밀점검","2025-10-23 09:00","2025-10-25 19:00","2025-10-23 09:00","2025-10-25 19:00","연속"]
[300,"경북","영주","신영주안동CC T/L","2025년 영주전력지사  GIS 정밀점검공사","-7471CB 정밀점검 후  신영주-안동CC T/L 이용 무부하가압(4시간)","2025-10-22 14:00","2025-10-22 18:30","취소","취소","연속"]
[301,"경북","영주","신영주S/S CB 7471","2025년 영주전력지사  GIS 정밀점검공사","-7471CB GIS 정밀점검","2025-10-20 09:00","2025-10-22 19:00","2025-10-20 09:00","2025-10-22 19:00","연속"]
[302,"경북","영주","신영주청송PP T/L","2025년 영주전력지사  GIS 정밀점검공사","-7300CB 정밀점검 후  신영주-청송PP T/L 이용 무부하가압","2025-10-18 14:00","2025-10-18 18:30","취소","취소","연속"]
[303,"경북","영주","신영주S/S CB 7300","2025년 영주전력지사  GIS 정밀점검공사","-7300CB GIS 정밀점검","2025-10-16 09:00","2025-10-18 19:00","2025-10-16 09:00","2025-10-18 19:00","연속"]
[304,"경북","영주","신영주청송PP T/L","2025년 영주전력지사  GIS 정밀점검","-7371CB 정밀점검 후  신영주-청송PP T/L 이용 무부하가압(4시간)","2025-10-15 14:00","2025-10-15 18:30","취소","취소","연속"]
[305,"경북","영주","한울#1N/P CB 7372","2025년 영주전력지사  GIS 정밀점검공사","-7372CB GIS 정밀점검","2025-10-30 09:00","2025-11-01 18:00","2025-10-30 09:00","2025-11-01 18:00","연속"]
[306,"경북","영주","삼척GP한울NP#1 T/L","2025년 영주전력지사  GIS 정밀점검공사","-7300CB 정밀점검 후 삼척GP-한울NP1 #1T/L 이용 무부하가압(4시간)","2025-10-29 14:00","2025-10-29 18:00","2025-10-29 18:00","2025-10-29 22:00","연속"]
[307,"경북","영주","한울#1N/P CB 7300","2025년 영주전력지사  GIS 정밀점검공사","-7300CB GIS 정밀점검","2025-10-27 09:00","2025-10-29 18:00","2025-10-27 09:00","2025-10-29 18:00","연속"]
[308,"경북","영주","한울2NP한울3NP#4 T/L","24~25년 영주전력지사 변전협력회사 공사","7G02DS ASSY 교체","2025-10-27 09:00","2025-10-31 18:00","취소","취소","연속"]
[309,"경북","영주","신영주한울NP#2 T/L","500kV HVDC 동해안-신가평 송전선로 건설사업(1공구)","No.4~5 발받침철탑 보호망 설치를 위한 휴전 신청","2025-10-15 09:00","2025-10-17 18:00","2025-10-22 09:00","2025-10-24 18:00","연속"]
[310,"경북","영주","신영주한울NP#1 T/L","500kV HVDC 동해안-신가평 송전선로 건설사업(1공구)","No.4~5 발받침철탑 보호망 설치를 위한 휴전 신청","2025-10-15 09:00","2025-10-17 18:00","2025-10-22 09:00","2025-10-24 18:00","연속"]
[311,"경북","직할","신영주청송PP T/L"," 청송분기 T/L 불량애자 교체공사","- 신영주-청송PP T/L 불량애자 교체","2025-10-27 09:00","2025-11-17 18:00","취소","취소","매일"]
[312,"경북","직할","청송P/P CB 7200","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[313,"경북","직할","청송P/P CB 7272","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2025-10-14 09:00","2025-10-14 18:00","2025-10-14 09:00","2025-10-14 18:00","연속"]
[314,"경북","직할","청송P/P CB 7172","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[315,"경북","영주","신영주S/S #1 BUS"," 2025년 영주전력지사  GIS 정밀점검공사","GIS 정밀점검(무부하 가압)","2025-10-03 14:00","2025-10-03 18:30","취소","취소","연속"]
[316,"경북","영주","신영주S/S #1 BUS"," 2025년 영주전력지사  GIS 정밀점검공사","GIS 정밀점검(무부하 가압)","2025-10-15 14:00","2025-10-15 18:30","취소","취소","연속"]
[317,"경북","영주","신영주S/S #1 BUS"," 2025년 영주전력지사  GIS 정밀점검공사","GIS 정밀점검(무부하 가압)","2025-10-22 14:00","2025-10-22 18:30","취소","취소","연속"]
[318,"경북","영주","신영주S/S #2 BUS"," 2025년 영주전력지사  GIS 정밀점검공사","GIS 정밀점검(무부하 가압)","2025-10-18 14:00","2025-10-18 18:30","취소","취소","연속"]
[319,"부산울산","동부산","고리N/P CB 7C71","고리NP S/Y 7C71 정밀점검 및 7CB/F 대체","고리NP S/Y 7C71 정밀점검 및 7CB/F 대체","2025-10-30 09:00","2025-11-13 18:00","2025-10-30 09:00","2025-11-13 18:00","연속"]
[320,"부산울산","동부산","고리N/P CB 7671","고리NP S/Y  GIS 7671 정밀점검","고리NP S/Y  GIS 7671 정밀점검","2025-10-14 09:00","2025-10-28 18:00","2025-10-14 09:00","2025-10-28 18:00","연속"]
[321,"부산울산","북부산","신김해북부산#1 T/L","24-25년 북부산전력지사 가공송전협력회사 공사","압축인류클램프 교체 No.4,22,40,43,50","2025-10-18 08:00","2025-10-19 18:00","2025-10-18 08:00","2025-10-19 18:00","연속"]
[322,"부산울산","북부산","북부산고리NP#1 T/L"," 울주-울산TP 22개TL 철탑 정비공사","폴리머점퍼지지애자 설치 ( 북부산-고리NP#1 No.13,25,36,54)","2025-10-20 07:00","2025-10-21 18:00","2025-10-20 07:00","2025-10-21 18:00","연속"]
[323,"부산울산","북부산","북부산고리NP#2 T/L"," 울주-울산TP 22개TL 철탑 정비공사","폴리머점퍼지지애자 설치 ( 북부산-고리NP#2 No.13,25,36,54)","2025-10-22 07:00","2025-10-24 18:00","2025-10-22 07:00","2025-10-24 18:00","연속"]
[324,"부산울산","서부산","서부산S/S #70 BUS","서부산S/S 모선측 ES 기계적 접점교체","서부산S/S 모선측 ES 기계적 접점교체 병행 : 모선보호반 계전기 교체","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[325,"부산울산","서부산","신녹산S/S #1 BUS","신녹산S/S  #1M.Tr 증설공사"," #1M.Tr 1차측 2CB 증설(#1BUS부 설치)","2025-10-13 09:00","2025-10-24 18:00","2025-10-13 09:00","2025-10-24 18:00","연속"]
[326,"부산울산","서부산","신김해신녹산#1 T/L","신녹산S/S  #1M.Tr 증설공사"," #1M.Tr 1차측 2CB 증설(#1BUS부 무부하시험가압, 7151DS 개방)","2025-10-23 08:00","2025-10-24 08:00","2025-10-23 08:00","2025-10-24 08:00","연속"]
[327,"부산울산","서부산","신녹산S/S #2 BUS","신녹산S/S  #1M.Tr 증설공사"," #1M.Tr 1차측 2CB 증설(#2BUS부 설치)","2025-10-27 09:00","2025-11-07 18:00","2025-10-27 09:00","2025-11-07 18:00","연속"]
[328,"부산울산","울산","남울산울산TP#1 T/L","2025년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 -  남울산-울산TP#1T/L 8~S/T","2025-10-24 08:00","2025-10-24 16:00","2025-10-24 08:00","2025-10-24 16:00","연속"]
[329,"부산울산","울산","동울산S/S CB 7200","'24~'25년 울산전력 변전협력회사 총액공사","7200 GIS 보통점검","2025-09-17 10:00","2025-09-17 16:00","2025-10-19 10:00","2025-10-19 16:00","연속"]
[330,"부산울산","울산","신온산S/S CB 7171","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-10-02 09:00","2025-10-02 16:00","2025-10-02 09:00","2025-10-02 16:00","연속"]
[331,"부산울산","울산","신온산S/S CB 7271","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-10-01 09:00","2025-10-01 16:00","2025-10-01 09:00","2025-10-01 16:00","연속"]
[332,"부산울산","울산","신온산S/S CB 7100","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-10-13 09:00","2025-10-13 16:00","2025-10-13 09:00","2025-10-13 16:00","연속"]
[333,"부산울산","울산","신온산S/S CB 7172","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-10-14 09:00","2025-10-14 16:00","2025-10-14 09:00","2025-10-14 16:00","연속"]
[334,"부산울산","울산","신온산S/S CB 7672","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-10-15 09:00","2025-10-15 16:00","2025-10-15 09:00","2025-10-15 16:00","연속"]
[335,"부산울산","울산","신온산S/S CB 7600","현대제  GIS 하자조치(유사고장 관련)","현대제 차단기 유압조작기 체크밸브 설치(하자)","2025-10-16 09:00","2025-10-16 16:00","2025-10-16 09:00","2025-10-16 16:00","연속"]
[336,"부산울산","울산","신온산S/S #2 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","1, 2차 부싱절연유 채유","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[337,"부산울산","울산","신울산S/S #5 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#5M.Tr) 1차측 개착식 관로(L=269m) 구간 굴착 및 가시설 설치","2025-10-13 09:00","2025-10-26 18:00","2025-10-13 09:00","2025-10-26 18:00","연속"]
[338,"부산울산","울산","신울산고리NP#1 T/L","2025년 가공송전 순시점검 위탁공사"," 신울산-고리NP#1T/L 정밀점검 1~63호","2025-10-13 09:00","2025-10-19 18:00","2025-10-13 09:00","2025-10-19 18:00","연속"]
[339,"부산울산","울산","신울산S/S #2 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#2M.Tr) 1차측 개착식 관로(L=269m) 구간 굴착 및 가시설 설치","2025-10-25 09:00","2025-10-31 18:00","2025-10-25 09:00","2025-10-31 18:00","연속"]
[340,"부산울산","울산","신울산고리NP#2 T/L","'24~'25년 울산전력 변전협력회사 총액공사","CVT 보통점검","2025-10-28 09:00","2025-10-28 18:00","2025-10-28 09:00","2025-10-28 18:00","연속"]
[341,"부산울산","울산","울산C/C #1 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","1,2차 부싱절연유 채유","2025-10-20 09:00","2025-10-20 16:00","2025-10-20 09:00","2025-10-20 16:00","연속"]
[342,"부산울산","울산","울산C/C #2 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","1,2차 부싱절연유 채유","2025-10-21 09:00","2025-10-21 16:00","2025-10-21 09:00","2025-10-21 16:00","연속"]
[343,"부산울산","울산","울주월성NP#2 T/L"," 울주S/S 장기사용 GIS 교체공사","울주S/S 7A Bay 장기사용 GIS 교체","2025-10-13 08:00","2025-12-23 18:00","2025-10-13 08:00","2025-12-23 18:00","연속"]
[344,"부산울산","울산","울주S/S #1 BUS"," 울주S/S 장기사용 GIS 교체공사","울주S/S 7A Bay 장기사용 GIS 교체","2025-10-13 08:00","2025-10-31 18:00","2025-10-13 08:00","2025-10-31 18:00","연속"]
[345,"부산울산","울산","울주울산TP#1 T/L"," 울주S/S 장기사용 GIS 교체공사","울주S/S 7A Bay 장기사용 GIS 교체(시험가압선로)","2025-10-30 08:00","2025-10-31 18:00","2025-10-30 08:00","2025-10-31 18:00","연속"]
[346,"부산울산","울산","울주신경산#1 T/L"," 울주S/S 장기사용 GIS 교체공사","울주S/S 7A Bay 장기사용 GIS 교체(시험가압선로)","2025-10-30 08:00","2025-10-31 18:00","2025-10-30 08:00","2025-10-31 18:00","연속"]
[347,"부산울산","울산","울주울산TP#1 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 및 금구류 설치","2025-10-17 07:00","2025-10-22 18:00","2025-10-17 07:00","2025-10-22 18:00","연속"]
[348,"부산울산","울산","울주S/S #3 M.Tr"," 울주S/S 장기사용 GIS 교체공사","집감반 실규설치 관련 6344 Bay 결선 및 시험작업","2025-10-01 08:00","2025-10-01 18:00","2025-10-01 08:00","2025-10-01 18:00","연속"]
[349,"경남","직할","창원신고성#1 T/L","2025년 직할  GIS 정밀점검 시험가압용","2025년 직할  GIS 정밀점검 시험가압용 - 창원S/S 7300 GIS 시험가압용","2025-10-03 09:00","2025-10-03 18:00","2025-10-03 09:00","2025-10-03 18:00","연속"]
[350,"경남","진주","신남원의령#2 T/L"," 신남원-의령T/L 추락방지장치 설치 공사"," 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2025-10-10 07:00","2025-10-14 18:00","취소","취소","매일"]
[351,"경남","김해송변전부","신김해신녹산#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사","154kV 신김해-주촌T/L 성능저하지지애자교체 안전이격","2025-10-12 08:00","2025-10-12 13:00","2025-10-12 08:00","2025-10-12 13:00","연속"]
[352,"경남","김해송변전부","신김해북부산#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사","154kV 신김해-주촌T/L 성능저하 지지애자 교체 안전이격","2025-10-12 13:00","2025-10-12 18:00","취소","취소","연속"]
[353,"경남","직할","창원신고성#1 T/L"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사","2025-10-13 07:00","2025-10-21 18:00","2025-10-13 07:00","2025-10-21 18:00","연속"]
[354,"경남","통영","창원신고성#2 T/L"," 창원신고성#2 T/L 추락방지장치 설치공사"," 창원신고성#2 T/L 추락방지장치 설치공사","2025-10-13 07:00","2025-10-14 18:00","취소","취소","매일"]
[355,"경남","직할","창원S/S CB 7371","2025년 직할  GIS 정밀점검(단독휴전)","2025년 직할  GIS 정밀점검 단독휴전 - 창원-신고성#1T/L 7371 GIS 선로휴전(시험가압 : 자단)","2025-10-13 09:00","2025-10-17 18:00","2025-10-13 09:00","2025-10-17 18:00","연속"]
[356,"경남","진주","신남원의령#1 T/L"," 신남원-의령T/L 추락방지장치 설치 공사"," 신남원-의령T/L 추락방지장치 설치 공사 1~136호(136기)","2025-10-15 07:00","2025-10-31 18:00","취소","취소","매일"]
[357,"경남","통영","신고성S/S #2 M.Tr","신고성S/S #2M.Tr 부싱 절연유 채유 및 도블 측정 등","신고성S/S #2M.Tr 부싱 절연유 채유 및 도블 측정, C상 누유개소 조치, #2S.Tr VCB 보통점검","2025-10-15 09:30","2025-10-16 18:00","2025-10-15 09:30","2025-10-16 18:00","연속"]
[358,"경남","진주","의령S/S CB 7771","의령S/S  신남원-의령#2T/L(7771) 유압접점 점검","의령S/S  신남원-의령#2T/L(7771) 유압접점 점검(A상)","2025-10-16 09:00","2025-10-16 14:00","2025-10-16 09:00","2025-10-16 14:00","연속"]
[359,"경남","진주","의령S/S #3 M.Tr","의령S/S  #3M.Tr OLTC 절연유 채유","의령S/S  #3M.Tr OLTC 절연유 채유","2025-10-16 14:00","2025-10-16 18:00","취소","취소","연속"]
[360,"경남","통영","창원신고성#1 T/L"," 창원신고성#1 T/L추락방지장치 설치공사"," 창원신고성#1 T/L 추락방지장치 설치공사","2025-10-17 07:00","2025-10-18 18:00","취소","취소","매일"]
[361,"경남","직할","창원신고성#1 T/L","2025년 직할  GIS 정밀점검 시험가압용","2025년 직할  GIS 정밀점검 시험가압용 - 창원-신고성#1T/L 7371 GIS 선로휴전(시험가압 : 자단)","2025-10-17 09:00","2025-10-17 18:00","2025-10-17 09:00","2025-10-17 18:00","매일"]
[362,"경남","함안","신마산신김해#1 T/L","항공장애구 설치공사","신마산-신김해T/L 50~51호 구간(2조 11개 설치) - 적색 6EA","2025-10-20 07:00","2025-10-20 12:00","2025-10-20 07:00","2025-10-20 12:00","연속"]
[363,"경남","함안","신마산신김해#2 T/L","항공장애구 설치공사","신마산-신김해T/L 50~51호 구간(2조 11개 설치) - 백색 5EA","2025-10-20 12:00","2025-10-20 18:00","취소","취소","연속"]
[364,"경남","진주","하동T/P CB 7300","하동T/P  7300 GIS 컨트롤블록 교체(A,B,C)","하동T/P  7300 GIS 컨트롤블록 교체(A,B,C) [병행] 7300 CB 조작시험","2025-10-22 09:00","2025-10-24 18:00","2025-10-22 09:00","2025-10-24 18:00","연속"]
[365,"경남","함안","신마산신고성#1 T/L","신마산S/S  신마산신고성#1 T/L B상 접지본드 과열 조치","신마산S/S  신마산신고성#1 T/L B상 접지본드 과열 조치","2025-10-22 09:30","2025-10-22 17:30","2025-10-22 09:30","2025-10-22 17:30","연속"]
[366,"경남","직할","창원신고성#2 T/L"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사","2025-10-23 07:00","2025-10-31 18:00","2025-10-23 07:00","2025-10-31 18:00","연속"]
[367,"경남","김해송변전부","신김해S/S #2 M.Tr","신김해S/S  #2M.Tr 3차측 현대화공사","신김해S/S  #2M.Tr 3차측 현대화공사","2025-10-27 09:00","2025-12-12 18:00","취소","취소","연속"]
[368,"경남","김해송변전부","신김해창원#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해-창원T/L 폴리머지지애자 설치","2025-10-28 08:00","2025-10-28 18:00","2025-10-28 08:00","2025-10-28 18:00","연속"]
[369,"경남","직할","창원신고성#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해-창원T/L 폴리머지지애자 설치 (안전이격)","2025-10-28 08:00","2025-10-28 18:00","2025-10-28 08:00","2025-10-28 18:00","연속"]
[370,"경남","통영","신고성S/S CB 7600","신고성SS  6호기 7600 GIS 보통점검","신고성SS  6호기 GIS(7600) 보통점검, CVT A~C상 보통점검","2025-10-28 09:30","2025-10-28 18:00","2025-10-28 09:30","2025-10-28 18:00","연속"]
[371,"경남","함안","신마산신김해#2 T/L","신마산S/S  신마산신김해#2 T/L B상 접지본드 과열 조치","신마산S/S  신마산신김해#2 T/L B상 접지본드 과열 조치","2025-10-29 09:30","2025-10-29 17:30","2025-10-29 09:30","2025-10-29 17:30","연속"]
[372,"경남","통영","신고성S/S CB 7671","신고성SS  6호기 7671 GIS 보통점검","신고성SS  #G6호기 1차 GIS(7671) 보통점검","2025-10-29 09:30","2025-10-29 18:00","2025-10-29 09:30","2025-10-29 18:00","연속"]
[373,"경남","함안","신마산S/S #2 M.Tr"," 신마산S/S #2M.Tr 교체공사","1.  M.Tr 철거 및 설치 x 1Bank 2. 기타 부대공사 x 1식","2025-10-30 09:00","2025-12-11 18:00","2025-10-30 09:00","2025-12-19 18:00","연속"]
[374,"경남","진주","하동T/P CB 7100","하동T/P 7100, 7172 GIS 조작시험","하동T/P 7100, 7172 GIS 조작시험","2025-10-30 10:00","2025-10-30 12:00","2025-10-30 10:00","2025-10-30 12:00","연속"]
[375,"경남","진주","하동T/P CB 7172","하동T/P 7100, 7172 GIS 조작시험","하동T/P 7100, 7172 GIS 조작시험","2025-10-30 12:00","2025-10-30 15:00","취소","취소","연속"]
[376,"경남","진주","하동T/P SEC CB 70710","하동T/P #70-71, #75-76 SEC GIS 조작시험","하동T/P #70-71, #75-76 SEC GIS 조작시험","2025-10-31 10:00","2025-10-31 12:00","2025-10-31 10:00","2025-10-31 12:00","연속"]
[377,"경남","진주","하동T/P SEC CB 75760","하동T/P #70-71, #75-76 SEC GIS 조작시험","하동T/P #70-71, #75-76 SEC GIS 조작시험","2025-10-31 12:00","2025-10-31 15:00","2025-10-31 12:00","2025-10-31 15:00","연속"]

{"sheet":"154설비","index":2,"n_rows":963,"n_cols":11,"rows_kept":963,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 10월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","광장S/S CB 6100","2025 성동전력지사 변전협력회사 공사","- 효성제 170kV GIS 노후 전자변 교체","2025-10-20 09:00","2025-10-20 18:00","2025-10-20 09:00","2025-10-20 18:00","연속"]
[2,"서울","성동","구의광장#2 T/L","2025 성동전력지사 변전협력회사 공사","- 효성제 170kV GIS 노후 전자변 교체","2025-10-21 09:00","2025-10-21 18:00","2025-10-21 09:00","2025-10-21 18:00","연속"]
[3,"서울","성동","미금광장 T/L","광장S/S 종합예방진단장치 설치공사","- GIS 부분방전 센서 설치 및 차폐테이프 부착","2025-10-27 10:00","2025-10-27 18:00","2025-10-27 10:00","2025-10-27 18:00","연속"]
[4,"서울","성동","천호구의#1 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 하자점검","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[5,"서울","성동","천호구의#2 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 하자점검","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[6,"서울","성동","성수뚝도#1 T/L","뚝도변전소 인출 OF케이블 선종교체공사","OF케이블 선종교체(→XLPE) : 뚝도EBG ∼ J/B#13(7) - 대상선로 : 광장뚝도#1, 광장뚝도#2, 성수뚝도#1T/L (3C×0.06㎞)","2025-10-13 09:00","2025-11-21 18:00","2025-10-13 09:00","2025-11-21 18:00","연속"]
[7,"서울","성동","방학창동#2 T/L","2025년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검(무부하가압용)","2025-10-01 14:00","2025-10-01 18:00","2025-10-01 14:00","2025-10-01 18:00","연속"]
[8,"서울","성동","금오상계#1 T/L","2025년 성동P/O 변전협력회사 공사","- LA 초기점검","2025-10-14 09:00","2025-10-14 18:00","2025-10-14 09:00","2025-10-14 18:00","연속"]
[9,"서울","성동","창동S/S #2 BUS","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○ 1차분 :  #3, #4M.Tr 1차, 창동쌍문#1T/L GIS 교체(3Bay) ○ 23kV #2Bank 일부, #3, #4M.Tr Bank GIS 교체(14Bay) ○ 제어케이블 포설 등 기타공사(1식)","2025-10-13 09:00","2025-10-15 18:00","2025-10-13 09:00","2025-10-15 18:00","연속"]
[10,"서울","성동","상계창동#2 T/L","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○ 1차분 :  #3, #4M.Tr 1차, 창동쌍문#1T/L GIS 교체(3Bay) ○ 23kV #2Bank 일부, #3, #4M.Tr Bank GIS 교체(14Bay) ○ 제어케이블 포설 등 기타공사(1식) ○ 시험가압선로 : 상계창동#2T/L","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[11,"서울","성동","창동S/S #1 BUS","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○ 1차분 :  #3, #4M.Tr 1차, 창동쌍문#1T/L GIS 교체(3Bay) ○ 23kV #2Bank 일부, #3, #4M.Tr Bank GIS 교체(14Bay) ○ 제어케이블 포설 등 기타공사(1식)","2025-10-16 09:00","2025-10-27 09:00","2025-10-16 09:00","2025-10-27 09:00","연속"]
[12,"서울","성동","상계창동#2 T/L","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○ 1차분 :  #3, #4M.Tr 1차, 창동쌍문#1T/L GIS 교체(3Bay) ○ 23kV #2Bank 일부, #3, #4M.Tr Bank GIS 교체(14Bay) ○ 제어케이블 포설 등 기타공사(1식) ○ 시험가압선로 : 상계창동#2T/L","2025-10-24 09:00","2025-10-27 09:00","2025-10-24 09:00","2025-10-27 09:00","연속"]
[13,"서울","성동","창동S/S #2 BUS","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○ 1차분 :  #3, #4M.Tr 1차, 창동쌍문#1T/L GIS 교체(3Bay) ○ 23kV #2Bank 일부, #3, #4M.Tr Bank GIS 교체(14Bay) ○ 제어케이블 포설 등 기타공사(1식)","2025-10-27 09:00","2025-11-06 18:00","2025-10-27 09:00","2025-11-06 18:00","연속"]
[14,"서울","성동","창동S/S #2 BUS","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○ 1차분 :  #3, #4M.Tr 1차, 창동쌍문#1T/L GIS 교체(3Bay) ○ 23kV #2Bank 일부, #3, #4M.Tr Bank GIS 교체(14Bay) ○ 제어케이블 포설 등 기타공사(1식)","2025-10-27 09:00","2025-11-06 18:00","2025-10-27 09:00","2025-11-06 18:00","연속"]
[15,"서울","성동","창동쌍문#1 T/L","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○ 1차분 :  #3, #4M.Tr 1차, 창동쌍문#1T/L GIS 교체(3Bay) ○ 23kV #2Bank 일부, #3, #4M.Tr Bank GIS 교체(14Bay) ○ 제어케이블 포설 등 기타공사(1식)","2025-10-13 09:00","2025-11-06 18:00","2025-10-13 09:00","2025-11-06 18:00","연속"]
[16,"서울","성동","상계창동#2 T/L","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○ 1차분 :  #3, #4M.Tr 1차, 창동쌍문#1T/L GIS 교체(3Bay) ○ 23kV #2Bank 일부, #3, #4M.Tr Bank GIS 교체(14Bay) ○ 제어케이블 포설 등 기타공사(1식) ○ 시험가압선로 : 상계창동#2T/L","2025-10-27 13:00","2025-10-27 18:00","2025-10-27 13:00","2025-10-27 18:00","연속"]
[17,"서울","성동","상계창동#2 T/L","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○ 1차분 :  #3, #4M.Tr 1차, 창동쌍문#1T/L GIS 교체(3Bay) ○ 23kV #2Bank 일부, #3, #4M.Tr Bank GIS 교체(14Bay) ○ 제어케이블 포설 등 기타공사(1식) ○ 시험가압선로 : 상계창동#2T/L","2025-10-17 09:00","2025-10-17 18:00","2025-10-17 09:00","2025-10-17 18:00","연속"]
[18,"서울","성동","화양광장 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 조작시험","2025-10-28 09:00","2025-10-28 18:00","2025-10-28 09:00","2025-10-28 18:00","연속"]
[19,"서울","성동","화양성수 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 조작시험","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[20,"서울","성동","미금화양 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 조작시험","2025-10-29 09:00","2025-10-29 18:00","2025-10-29 09:00","2025-10-29 18:00","연속"]
[21,"서울","중부","용산동빙고 T/L","동빙고S/S 23kV 장기사용 GIS 교체공사(병행)","운영시스템 및 Legacy 설비 제어케이블 이설","2025-10-13 09:00","2025-10-14 18:00","2025-10-13 09:00","2025-10-14 18:00","연속"]
[22,"서울","중부","동빙고반포#1 T/L","동빙고S/S 23kV 장기사용 GIS 교체공사(병행)","운영시스템 및 Legacy 설비 제어케이블 이설","2025-10-20 09:00","2025-10-21 18:00","2025-10-20 09:00","2025-10-21 18:00","연속"]
[23,"서울","중부","동빙고반포#2 T/L","동빙고S/S 23kV 장기사용 GIS 교체공사(병행)","운영시스템 및 Legacy 설비 제어케이블 이설","2025-10-22 09:00","2025-10-23 18:00","2025-10-22 09:00","2025-10-23 18:00","연속"]
[24,"서울","중부","순화동빙고 T/L","동빙고S/S 23kV 장기사용 GIS 교체공사(병행)","운영시스템 및 Legacy 설비 제어케이블 이설","2025-10-15 09:00","2025-10-16 18:00","2025-10-15 09:00","2025-10-16 18:00","연속"]
[25,"서울","중부","상암S/S #1 BUS","(선로시험가압)수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : 2025.2.25~2026.10.23","2025-10-23 09:00","2025-10-24 09:00","2025-10-23 09:00","2025-10-24 09:00","연속"]
[26,"서울","중부","상암등촌#1 T/L","(선로시험가압)수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : 2025.2.25~2026.10.23","2025-10-23 09:00","2025-10-24 09:00","2025-10-23 09:00","2025-10-24 09:00","연속"]
[27,"서울","중부","원흥상암 T/L"," 수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : 2025.2.25~2026.10.23","2025-10-13 09:00","2025-10-24 09:00","2025-10-13 09:00","2025-10-24 09:00","연속"]
[28,"서울","중부","수색은평#1 T/L"," 수색S/S 옥내화관련 수색-은평T/L 지중화 공사","선종 및 회선 수 : STACIR 330㎟, 2회선 (금회분) 철탑신설 1기, 전력선 가선 (1.2C-㎞) 철탑철거 2기, 전력선인하 (7.4C-㎞) 공사기간 : 2024. 2. 8. ~ 2027. 2.11. (착공후 1100일간)","2025-10-22 09:00","2025-12-03 18:00","2025-10-22 09:00","2025-12-03 18:00","연속"]
[29,"서울","중부","원흥수색#1 T/L"," 수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : 2025.2.25~2026.10.23","2025-10-24 09:00","2025-11-14 18:00","2025-10-24 09:00","2025-11-14 18:00","연속"]
[30,"서울","중부","수색상암 T/L"," 수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : 2025.2.25~2026.10.23","2025-10-24 09:00","2025-11-14 18:00","2025-10-24 09:00","2025-11-14 18:00","연속"]
[31,"서울","중부","순화S/S CB 6100","2025년 중부전력지사 변전협력회사 공사","모선보호반 교체","2025-10-13 10:00","2025-10-17 18:00","2025-10-13 10:00","2025-10-17 18:00","연속"]
[32,"서울","중부","용산동빙고 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-10-28 10:00","2025-10-28 18:00","2025-10-28 10:00","2025-10-28 18:00","연속"]
[33,"서울","중부","용산동빙고 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-10-14 10:00","2025-10-14 18:00","2025-10-14 10:00","2025-10-14 18:00","연속"]
[34,"서울","중부","용산동빙고 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-10-30 10:00","2025-10-30 18:00","2025-10-30 10:00","2025-10-30 18:00","연속"]
[35,"서울","중부","용산동빙고 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-10-21 10:00","2025-10-21 18:00","2025-10-21 10:00","2025-10-21 18:00","연속"]
[36,"서울","중부","용산동빙고 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-10-17 10:00","2025-10-17 18:00","2025-10-17 10:00","2025-10-17 18:00","연속"]
[37,"서울","중부","용산동빙고 T/L","2025년 중부P/O 관내S/S 170kV GIS 정밀점검공사","시험 가압","2025-10-24 10:00","2025-10-24 18:00","2025-10-24 10:00","2025-10-24 18:00","연속"]
[38,"서울","중부","중부S/S #65 BUS","2025년 중부S/S  장기사용 GIS 교체공사(3차)","-  GIS 교체(#6100BUS-TIE, #62M.Tr 1차) - 기타 부대공사","2025-10-27 09:00","2025-11-07 15:00","2025-10-27 09:00","2025-11-07 15:00","연속"]
[39,"서울","중부","중부S/S #65 BUS","2025년 중부S/S  장기사용 GIS 교체공사(3차)","-  GIS 교체(#6100BUS-TIE, #62M.Tr 1차) - 기타 부대공사","2025-10-14 09:00","2025-10-17 09:00","2025-10-14 09:00","2025-10-17 09:00","연속"]
[40,"서울","중부","중부S/S CB 6100","2025년 중부S/S  장기사용 GIS 교체공사(3차)","-  GIS 교체(#6100BUS-TIE, #62M.Tr 1차) - 기타 부대공사","2025-10-13 09:00","2025-11-07 15:00","2025-10-13 09:00","2025-11-07 15:00","연속"]
[41,"서울","중부","중부S/S #60 BUS","2025년 중부S/S  장기사용 GIS 교체공사(3차)","-  GIS 교체(#6100BUS-TIE, #62M.Tr 1차) - 기타 부대공사","2025-10-17 09:00","2025-10-27 09:00","2025-10-17 09:00","2025-10-27 09:00","연속"]
[42,"서울","직할","옥인운니#1 T/L","25년 직할 변전정비협력회사 총액공사"," GIS 보통점검","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[43,"서울","직할","옥인운니#2 T/L","25년 직할 변전정비협력회사 총액공사"," GIS 보통점검","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[44,"남서울","강남","신양재역삼#3 T/L","송전선로 OF 케이블 절연유 채유","OF 케이블 절연유 채유","2025-10-28 09:00","2025-10-28 16:00","2025-10-28 09:00","2025-10-28 16:00","연속"]
[45,"남서울","강남","신양재역삼#2 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검","2025-10-16 09:00","2025-10-18 18:00","취소","취소","연속"]
[46,"남서울","강남","신양재역삼#1 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검","2025-10-13 09:00","2025-10-15 18:00","취소","취소","연속"]
[47,"남서울","강남","신양재S/S #61 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #1DS 점검","2025-10-13 09:00","2025-10-14 16:00","취소","취소","연속"]
[48,"남서울","강남","신양재사당#1 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검 무부하가압","2025-10-14 14:00","2025-10-14 16:00","취소","취소","연속"]
[49,"남서울","강남","신양재S/S #66 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #2DS 점검","2025-10-14 16:00","2025-10-15 18:00","취소","취소","연속"]
[50,"남서울","강남","신양재S/S #61 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #1DS 점검","2025-10-16 09:00","2025-10-17 16:00","취소","취소","연속"]
[51,"남서울","강남","신양재사당#1 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검 무부하가압","2025-10-17 14:00","2025-10-17 16:00","취소","취소","연속"]
[52,"남서울","강남","신양재S/S #66 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #2DS 점검","2025-10-17 16:00","2025-10-18 18:00","취소","취소","연속"]
[53,"남서울","강남","신양재과천#2 T/L","강남전력지사  GIS 정밀점검"," GIS 정밀점검","2025-10-20 09:00","2025-10-22 18:00","2025-10-20 09:00","2025-10-22 18:00","연속"]
[54,"남서울","강남","신양재S/S #60 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #1DS 점검","2025-10-20 09:00","2025-10-21 16:00","2025-10-20 09:00","2025-10-21 16:00","연속"]
[55,"남서울","강남","신양재신사#3 T/L","강남전력지사  GIS 정밀점검","OF 케이블 절연유 채유 및  GIS 정밀점검 무부하가압","2025-10-21 09:00","2025-10-21 16:00","2025-10-21 09:00","2025-10-21 16:00","연속"]
[56,"남서울","강남","신양재S/S #65 BUS","강남전력지사  GIS 정밀점검"," GIS 정밀점검 #2DS 점검","2025-10-21 16:00","2025-10-22 18:00","2025-10-21 16:00","2025-10-22 18:00","연속"]
[57,"남서울","동서울","논현선릉#2 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","선릉S/S 논현-선릉#2T/L 조작시험","2025-10-22 14:00","2025-10-22 18:00","2025-10-22 14:00","2025-10-22 18:00","연속"]
[58,"남서울","동서울","논현선릉#1 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","선릉S/S 논현-선릉#1T/L 조작시험","2025-10-22 09:00","2025-10-22 14:00","2025-10-22 09:00","2025-10-22 14:00","연속"]
[59,"남서울","동서울","수서S/S #1 BUS","24-25년도 동서울전력지사 변전협력회사 총액공사","수서S/S  PT집합반 대체","2025-10-13 16:00","2025-10-13 18:00","2025-10-13 16:00","2025-10-13 18:00","연속"]
[60,"남서울","동서울","수서S/S #1 BUS"," 산성-수서T/L 지중화공사(2단계)"," 산성-수서#1T/L 지중화(2단계) - 발주처 : LH - 지중화공사에 따른 케이블 철거 및 포설, 접속","2025-10-14 15:00","2025-10-15 18:00","2025-10-14 15:00","2025-10-15 18:00","연속"]
[61,"남서울","동서울","수서S/S #1 BUS","24-25년도 동서울전력지사 변전협력회사 총액공사","수서S/S  PT집합반 대체","2025-10-13 09:00","2025-10-13 13:00","2025-10-13 09:00","2025-10-13 13:00","연속"]
[62,"남서울","동서울","수서S/S #2 BUS","24-25년도 동서울전력지사 변전협력회사 총액공사","수서S/S  PT집합반 대체","2025-10-13 13:00","2025-10-13 16:00","2025-10-13 13:00","2025-10-13 16:00","연속"]
[63,"남서울","동서울","잠실탄천#1 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","잠실S/S 잠실-탄천#1T/L GIS 보통점검 (탄천측 보통점검 병행)","2025-10-25 09:00","2025-10-25 18:00","취소","취소","연속"]
[64,"남서울","동서울","잠실탄천#2 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","잠실S/S 잠실-탄천#1T/L GIS 보통점검 (탄천측 보통점검 병행)","2025-10-26 09:00","2025-10-26 18:00","취소","취소","연속"]
[65,"남서울","영등포","광명구공#1 T/L","'25-'26년 영등포전력지사 지중송전 협력회사 공사","○ 광명-구공#1T/L 절연유 채유","2025-10-28 09:00","2025-10-28 18:00","2025-10-28 09:00","2025-10-28 18:00","연속"]
[66,"남서울","영등포","신문래구로#2 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 구로S/S 신문래-구로#2 T/L GIS","2025-10-29 14:00","2025-10-31 18:00","취소","취소","연속"]
[67,"남서울","영등포","신정목동#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 목동S/S 신정-목동#1T/L GIS","2025-10-13 09:00","2025-10-15 14:00","2025-10-13 09:00","2025-10-15 14:00","연속"]
[68,"남서울","영등포","오류목동 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 목동S/S 6100 GIS 정밀점검후 무부하가압","2025-10-22 09:00","2025-10-22 18:00","2025-10-22 09:00","2025-10-22 18:00","연속"]
[69,"남서울","영등포","목동S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 목동S/S 6100 GIS 정밀점검용 60BUS 휴전","2025-10-20 09:00","2025-10-22 18:00","2025-10-20 09:00","2025-10-22 18:00","연속"]
[70,"남서울","영등포","신문래목동#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 목동S/S 신문래-목동#1T/L GIS","2025-10-15 14:00","2025-10-17 18:00","2025-10-15 14:00","2025-10-17 18:00","연속"]
[71,"남서울","영등포","천왕오류#1 T/L","'25-'26년 영등포전력지사 지중송전 협력회사 공사","○ 천왕-오류#1T/L 절연유 채유","2025-10-29 09:00","2025-10-29 18:00","취소","취소","연속"]
[72,"남서울","영등포","등촌S/S #60 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 등촌S/S 6433 정밀점검 후 무부하 가압용","2025-10-14 16:00","2025-10-14 18:00","2025-10-27 16:00","2025-10-28 18:00","연속"]
[73,"남서울","영등포","상암등촌#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 등촌S/S 6433 정밀점검 후 무부하가압","2025-10-14 16:00","2025-10-14 18:00","2025-10-28 16:00","2025-10-28 18:00","연속"]
[74,"남서울","영등포","가양등촌#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","등촌S/S 611 내부 점검","2025-10-15 09:00","2025-10-16 18:00","2025-10-29 09:00","2025-10-30 18:00","연속"]
[75,"남서울","영등포","등촌S/S #60 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 등촌S/S 611 내부 점검","2025-10-15 09:00","2025-10-16 18:00","2025-10-29 09:00","2025-10-30 18:00","연속"]
[76,"남서울","직할","신문래노들 T/L","170kV GIS 조작시험, 전자변 교체","170kV GIS 조작시험, 전자변 교체","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[77,"남서울","직할","신림봉천 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2025-10-18 09:00","2025-10-18 18:00","2025-10-18 09:00","2025-10-18 18:00","연속"]
[78,"남서울","직할","사당봉천#1 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-10-15 09:00","2025-10-17 18:00","2025-10-15 09:00","2025-10-17 18:00","연속"]
[79,"남서울","직할","사당봉천#2 T/L","170kV GIS 보통점검","170kV GIS 보통점검","2025-10-14 09:00","2025-10-14 18:00","2025-10-14 09:00","2025-10-14 18:00","연속"]
[80,"남서울","직할","봉천신길#1 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-10-20 09:00","2025-10-21 18:00","2025-10-20 09:00","2025-10-21 18:00","연속"]
[81,"남서울","직할","봉천신길#2 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-10-27 09:00","2025-10-28 18:00","2025-10-27 09:00","2025-10-28 18:00","연속"]
[82,"남서울","직할","사당신림 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-10-22 09:00","2025-10-24 18:00","2025-10-22 09:00","2025-10-24 18:00","연속"]
[83,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(신문래-목동#1T/L, 무부하가압용)","170kV GIS 정밀점검공사(신문래-목동#1T/L, 무부하가압용)","2025-10-14 10:00","2025-10-14 14:00","2025-10-14 10:00","2025-10-14 14:00","연속"]
[84,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(6100BUS-TIE, 무부하가압용)","170kV GIS 정밀점검공사(6100BUS-TIE, 무부하가압용)","2025-10-01 14:00","2025-10-01 18:00","2025-10-01 14:00","2025-10-01 18:00","연속"]
[85,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검공사(신문래-목동#1T/L, #2DS 점검용)","170kV GIS 정밀점검공사(신문래-목동#1T/L, #2DS 점검용)","2025-10-14 14:00","2025-10-15 18:00","2025-10-14 14:00","2025-10-15 18:00","연속"]
[86,"남서울","직할","신문래S/S #60 BUS","170kV GIS 정밀점검공사(#1M.Tr 2차, #1DS 점검용)","170kV GIS 정밀점검공사(#1M.Tr 2차, #1DS 점검용)","2025-10-16 09:00","2025-10-17 14:00","2025-10-16 09:00","2025-10-17 14:00","연속"]
[87,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(#1M.Tr 2차, 무부하가압용)","170kV GIS 정밀점검공사(#1M.Tr 2차, 무부하가압용)","2025-10-17 10:00","2025-10-17 14:00","2025-10-17 10:00","2025-10-17 14:00","연속"]
[88,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검공사(#1M.Tr 2차, #2DS 점검용)","170kV GIS 정밀점검공사(#1M.Tr 2차, #2DS 점검용)","2025-10-17 14:00","2025-10-18 18:00","2025-10-17 14:00","2025-10-18 18:00","연속"]
[89,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(#1M.Tr 2차, 무부하가압용)","170kV GIS 정밀점검공사(#1M.Tr 2차, 무부하가압용)","2025-10-18 14:00","2025-10-18 18:00","2025-10-18 14:00","2025-10-18 18:00","연속"]
[90,"남서울","직할","신문래S/S #60 BUS","170kV GIS 정밀점검공사(신문래-구로#2T/L, #1DS 점검용)","170kV GIS 정밀점검공사(신문래-구로#2T/L, #1DS 점검용)","2025-10-20 09:00","2025-10-21 14:00","2025-10-20 09:00","2025-10-21 14:00","연속"]
[91,"남서울","직할","신문래구로#2 T/L","170kV GIS 정밀점검공사(신문래-구로#2T/L)","170kV GIS 정밀점검공사(신문래-구로#2T/L)","2025-10-20 09:00","2025-10-22 18:00","2025-10-20 09:00","2025-10-22 18:00","연속"]
[92,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(신문래-구로#2T/L, 무부하가압용)","170kV GIS 정밀점검공사(신문래-구로#2T/L, 무부하가압용)","2025-10-21 10:00","2025-10-21 14:00","2025-10-21 10:00","2025-10-21 14:00","연속"]
[93,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검공사(신문래-구로#2T/L, #2DS 점검용)","170kV GIS 정밀점검공사(신문래-구로#2T/L, #2DS 점검용)","2025-10-21 14:00","2025-10-22 18:00","2025-10-21 14:00","2025-10-22 18:00","연속"]
[94,"남서울","직할","신문래S/S #60 BUS","170kV GIS 정밀점검공사(#3M.Tr 2차, #1DS 점검용)","170kV GIS 정밀점검공사(#3M.Tr 2차, #1DS 점검용)","2025-10-23 09:00","2025-10-24 14:00","2025-10-23 09:00","2025-10-24 14:00","연속"]
[95,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(#3M.Tr 2차, 무부하가압용)","170kV GIS 정밀점검공사(#3M.Tr 2차, 무부하가압용)","2025-10-24 10:00","2025-10-24 14:00","2025-10-24 10:00","2025-10-24 14:00","연속"]
[96,"남서울","직할","신문래S/S #65 BUS","170kV GIS 정밀점검공사(#3M.Tr 2차, #2DS 점검용)","170kV GIS 정밀점검공사(#3M.Tr 2차, #2DS 점검용)","2025-10-24 14:00","2025-10-25 18:00","2025-10-24 14:00","2025-10-25 18:00","연속"]
[97,"남서울","직할","신문래영오#1 T/L","170kV GIS 정밀점검공사(#3M.Tr 2차, 무부하가압용)","170kV GIS 정밀점검공사(#3M.Tr 2차, 무부하가압용)","2025-10-25 14:00","2025-10-25 18:00","2025-10-25 14:00","2025-10-25 18:00","연속"]
[98,"남서울","직할","신문래S/S #61 BUS","170kV GIS 정밀점검공사(#2M.Tr 2차, #1DS 점검용)","170kV GIS 정밀점검공사(#2M.Tr 2차, #1DS 점검용)","2025-10-27 09:00","2025-10-28 14:00","2025-10-27 09:00","2025-10-28 14:00","연속"]
[99,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사(#2M.Tr 2차, 무부하가압용)","170kV GIS 정밀점검공사(#2M.Tr 2차, 무부하가압용)","2025-10-28 10:00","2025-10-28 14:00","2025-10-28 10:00","2025-10-28 14:00","연속"]
[100,"남서울","직할","신문래S/S #66 BUS","170kV GIS 정밀점검공사(#2M.Tr 2차, #2DS 점검용)","170kV GIS 정밀점검공사(#2M.Tr 2차, #2DS 점검용)","2025-10-28 14:00","2025-10-29 18:00","2025-10-28 14:00","2025-10-29 18:00","연속"]
[101,"남서울","직할","신문래영오#2 T/L","170kV GIS 정밀점검공사(#2M.Tr 2차, 무부하가압용)","170kV GIS 정밀점검공사(#2M.Tr 2차, 무부하가압용)","2025-10-29 14:00","2025-10-29 18:00","2025-10-29 14:00","2025-10-29 18:00","연속"]
[102,"남서울","직할","신문래S/S #60 BUS","170kV GIS 정밀점검공사(신문래-목동#1T/L, #1DS 점검용)","170kV GIS 정밀점검공사(신문래-목동#1T/L, #1DS 점검용)","2025-10-13 09:00","2025-10-14 14:00","2025-10-13 09:00","2025-10-14 14:00","연속"]
[103,"남서울","직할","신문래목동#1 T/L","170kV GIS 정밀점검공사(신문래-목동#1T/L)","170kV GIS 정밀점검공사(신문래-목동#1T/L)","2025-10-13 09:00","2025-10-15 18:00","2025-10-13 09:00","2025-10-15 18:00","연속"]
[104,"남서울","직할","신문래양평#1 T/L","170kV GIS 보통점검, 전자변 교체","170kV GIS 보통점검, 전자변 교체","2025-10-31 09:00","2025-10-31 18:00","2025-10-31 09:00","2025-10-31 18:00","연속"]
[105,"인천","김포","경서양촌#2 T/L","경서S/S  경서-양촌#2T/L GIS 조작시험","경서S/S  경서-양촌#2T/L GIS 조작시험","2025-10-24 10:00","2025-10-24 18:00","2025-10-24 10:00","2025-10-24 18:00","연속"]
[106,"인천","김포","김포불로#1 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-10-29 08:00","2025-10-30 14:00","취소","취소","연속"]
[107,"인천","김포","계양불로#1 T/L","불로S/S  계양-불로#1T/L GIS 하자점검","불로S/S  계양-불로#1T/L GIS 하자점검","2025-10-28 10:00","2025-10-28 18:00","2025-10-28 10:00","2025-10-28 18:00","연속"]
[108,"인천","김포","계양불로#2 T/L","불로S/S  계양-불로#2T/L GIS 하자점검","불로S/S  계양-불로#2T/L GIS 하자점검","2025-10-30 10:00","2025-10-30 18:00","2025-10-30 10:00","2025-10-30 18:00","연속"]
[109,"인천","김포","김포불로#2 T/L","불로S/S  불로-김포#2T/L GIS 하자점검","불로S/S  불로-김포#2T/L GIS 하자점검","2025-10-24 10:00","2025-10-24 18:00","취소","취소","연속"]
[110,"인천","김포","신김포양곡#2 T/L","양곡S/S  신김포-양곡#2T/L GIS 하자점검","양곡S/S  신김포-양곡#2T/L GIS 하자점검","2025-10-31 10:00","2025-10-31 18:00","2025-10-31 10:00","2025-10-31 18:00","연속"]
[111,"인천","김포","양곡연락 T/L","양곡S/S  양곡연락T/L GIS 조작시험","양곡S/S  양곡연락T/L GIS 조작시험","2025-10-28 10:00","2025-10-28 18:00","2025-10-28 10:00","2025-10-28 18:00","연속"]
[112,"인천","김포","양곡S/S #60 BUS","양곡S/S  GIS 교체공사(4차)","- 양촌양곡#1T/L GIS 교체 - 상체크 시험","2025-10-02 15:00","2025-10-02 18:00","2025-10-02 15:00","2025-10-02 18:00","연속"]
[113,"인천","김포","양촌양곡#2 T/L","24-25년 가공송전 협력회사 공사 (추락방지시설 설치)","수평 추락방지시설 설치, SB댐퍼 설치","2025-10-03 07:00","2025-10-05 18:00","2025-10-03 07:00","2025-10-05 18:00","연속"]
[114,"인천","김포","왕길양촌#2 T/L","'24~25년 부평,김포 가공송전 협력회사 공사"," 왕길-양촌T/L 폴리머지지애자 설치공사","2025-10-27 07:00","2025-10-27 18:00","2025-10-27 07:00","2025-10-27 18:00","연속"]
[115,"인천","부평","관교만수#1 T/L","관교S/S  관교만수#1T/L  혼용화","관교S/S  관교만수#1T/L  혼용화","2025-10-10 09:00","2025-10-10 18:00","2025-10-10 09:00","2025-10-10 18:00","연속"]
[116,"인천","부평","인천남인천#2 T/L","지중송전설비 협력회사공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[117,"인천","부평","관교만수#2 T/L"," 관교-만수#2T/L 637 GIS 보통점검(오후)"," 관교-만수#2T/L 637 GIS 보통점검(오후)","2025-10-18 11:00","2025-10-18 18:00","2025-10-18 11:00","2025-10-18 18:00","연속"]
[118,"인천","부평","주안만수#2 T/L"," 주안-만수#2T/L 647 GIS 보통점검(오전)"," 주안-만수#2T/L 647 GIS 보통점검(오전)","2025-10-18 07:00","2025-10-18 11:00","2025-10-18 07:00","2025-10-18 11:00","연속"]
[119,"인천","부평","송현포스코CC#1 T/L","지중송전설비 협력회사공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[120,"인천","부평","송현포스코CC#2 T/L"," 주안-관교등 4개T/L 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링 유니트점검 시행","2025-10-27 09:00","2025-10-29 18:00","2025-10-27 09:00","2025-10-29 18:00","연속"]
[121,"인천","부평","신가좌주안#2 T/L"," 신가좌-주안#2T/L 617 GIS 보통점검,피뢰기점검"," 신가좌-주안#2T/L 617 GIS 보통점검,피뢰기 점검","2025-10-24 08:00","2025-10-24 11:00","취소","취소","연속"]
[122,"인천","부평","신가좌부개#1 T/L","25~26년 지중송전 협력회사공사","절연유 채취","2025-10-27 09:00","2025-10-29 18:00","2025-10-27 09:00","2025-10-29 18:00","연속"]
[123,"인천","부평","신가좌S/S SEC CB 60610"," #60-61 SEC GIS (60-61-0) 보조계전기 교체"," #60-61 SEC GIS (60-61-0) 보조계전기 교체","2025-10-29 09:00","2025-10-29 18:00","취소","취소","연속"]
[124,"인천","부평","신가좌부개#2 T/L","25~26년 지중송전 협력회사공사","절연유 채취","2025-10-30 09:00","2025-10-31 18:00","2025-10-30 09:00","2025-10-31 18:00","연속"]
[125,"인천","부평","신가좌S/S SEC CB 65660"," #65-66 SEC GIS (65-66-0) 보조계전기 교체"," #65-66 SEC GIS (65-66-0) 보조계전기 교체","2025-10-30 09:00","2025-10-30 18:00","취소","취소","연속"]
[126,"인천","부평","신가좌주안#1 T/L"," 신가좌-주안#1T/L 647 GIS 보통점검,피뢰기보통점검"," 신가좌-주안#1T/L 647 GIS 보통점검, 피뢰기 보통점검, 주안S/S 점검 병행","2025-10-09 09:00","2025-10-09 18:00","취소","취소","연속"]
[127,"인천","부평","원창S/S #2 BUS","원창S/S  신규수용공사","- 아마존코퍼레이트서비시즈코리아(유)  신규 대용량고객 전력공급 2회선","2025-10-13 09:00","2025-10-15 13:00","2025-10-13 09:00","2025-10-15 13:00","연속"]
[128,"인천","부평","북인천원창 T/L","원창S/S  신규수용공사","- 아마존코퍼레이트서비시즈코리아(유)  신규 대용량고객 전력공급 2회선","2025-10-14 09:00","2025-10-15 13:00","2025-10-14 09:00","2025-10-15 13:00","연속"]
[129,"인천","부평","원창S/S #1 BUS","원창S/S  신규수용공사","- 아마존코퍼레이트서비시즈코리아(유)  신규 대용량고객 전력공급 2회선","2025-10-15 13:00","2025-10-22 10:00","2025-10-15 13:00","2025-10-22 10:00","연속"]
[130,"인천","부평","북인천원창 T/L","원창S/S  신규수용공사","- 아마존코퍼레이트서비시즈코리아(유)  신규 대용량고객 전력공급 2회선","2025-10-21 10:00","2025-10-22 10:00","2025-10-21 10:00","2025-10-22 10:00","연속"]
[131,"인천","부평","원창S/S #2 BUS","원창S/S  신규수용공사","- 아마존코퍼레이트서비시즈코리아(유)  신규 대용량고객 전력공급 2회선","2025-10-22 10:00","2025-10-22 14:00","2025-10-22 10:00","2025-10-22 14:00","연속"]
[132,"인천","부평","관교주안 T/L"," 주안-관교등 4개T/L 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링 유니트점검 시행","2025-10-24 11:00","2025-10-26 18:00","취소","취소","연속"]
[133,"인천","부평","주안만수#1 T/L"," 주안-만수#1T/L 667 GIS 보통점검"," 주안-만수#1T/L 667 GIS 보통점검","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[134,"인천","부평","주안S/S CB 6100","주안S/S  모선보호반 대체","주안S/S  모선보호반 대체","2025-10-11 09:00","2025-10-14 18:00","취소","취소","연속"]
[135,"인천","시흥","남동동춘 T/L","남동S/S 혼용화공사","남동S/S 혼용화공사 관련 휴전","2025-10-27 09:00","2025-10-28 18:00","2025-10-27 09:00","2025-10-28 18:00","연속"]
[136,"인천","시흥","신시흥남동#1 T/L","남동S/S 혼용화공사","남동S/S 혼용화공사 관련 휴전","2025-10-30 09:00","2025-10-31 18:00","취소","취소","연속"]
[137,"인천","시흥","남동연수#1 T/L","남동S/S 혼용화공사","남동S/S 혼용화공사 관련 휴전","2025-10-01 09:00","2025-10-02 18:00","2025-10-01 09:00","2025-10-02 18:00","연속"]
[138,"인천","시흥","남시화남정왕#2 T/L","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  남시화-남정왕#2T/L GIS 정밀점검 - 정밀점검 및 시험가압을 위한 휴전","2025-10-10 08:00","2025-10-11 18:00","2025-10-10 08:00","2025-10-11 18:00","연속"]
[139,"인천","시흥","남시화남정왕#1 T/L","2025년 시흥전력지사 170kV GIS 정밀점검 공사","남정왕S/S  남시화-남정왕#1T/L GIS 정밀점검 - 정밀점검 및 시험가압을 위한 휴전","2025-10-03 08:00","2025-10-04 18:00","2025-10-03 08:00","2025-10-04 18:00","연속"]
[140,"인천","시흥","도림오봉#2 T/L","피뢰기 교체공사 및 열화진단","- 피뢰기 교체공사 : 오봉C/T - 피뢰기 열화진단 : 도림C/T","2025-10-23 08:00","2025-10-23 18:00","2025-10-23 08:00","2025-10-23 18:00","연속"]
[141,"인천","시흥","도림오봉#1 T/L","피뢰기 교체공사 및 열화진단","- 피뢰기 교체공사 : 오봉C/T - 피뢰기 열화진단 : 도림C/T","2025-10-22 08:00","2025-10-22 18:00","2025-10-22 08:00","2025-10-22 18:00","연속"]
[142,"인천","시흥","신시흥도림#1 T/L","도림SS  신시흥도림#1T/L GIS 보통점검","도림SS  신시흥도림#1T/L GIS 보통점검","2025-10-03 09:00","2025-10-03 14:00","취소","취소","연속"]
[143,"인천","시흥","동시화서시화 T/L","동시화S/S  #6M.Tr 증설공사","- 동시화S/S  #6M.Tr 증설관련  GIS 설치 - #66BUS 무부하 가압","2025-10-20 15:00","2025-10-21 15:00","2025-10-20 15:00","2025-10-21 15:00","연속"]
[144,"인천","시흥","동시화S/S #61 BUS","동시화S/S  #6M.Tr 증설공사","- 동시화S/S  #6M.Tr 증설관련  GIS 설치","2025-10-14 09:00","2025-10-18 15:00","2025-10-14 09:00","2025-10-18 15:00","연속"]
[145,"인천","시흥","동시화서시화 T/L","동시화S/S  #6M.Tr 증설공사","- 동시화S/S  #6M.Tr 증설관련  GIS 설치 - #61BUS 무부하 가압","2025-10-17 15:00","2025-10-18 15:00","2025-10-17 15:00","2025-10-18 15:00","연속"]
[146,"인천","시흥","동시화S/S #66 BUS","동시화S/S  #6M.Tr 증설공사","- 동시화S/S  #6M.Tr 증설관련  GIS 설치","2025-10-18 15:00","2025-10-21 15:00","2025-10-18 15:00","2025-10-21 15:00","연속"]
[147,"인천","시흥","서서울#2소래 T/L","피뢰기 열화진단 및 EBA 가스채취","- 피뢰기 열화진단 : 목감#41C/T, 목감#45C/T - EBA 가스채취 : 소래C/T","2025-10-18 08:00","2025-10-19 18:00","취소","취소","연속"]
[148,"인천","시흥","온수소래 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기)","2025-10-10 07:00","2025-10-12 18:00","취소","취소","연속"]
[149,"인천","시흥","서안양소래 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기)","2025-10-10 07:00","2025-10-12 18:00","취소","취소","연속"]
[150,"인천","시흥","신광명소래 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기)","2025-10-18 07:00","2025-10-19 18:00","취소","취소","연속"]
[151,"인천","시흥","신시화S/S SEC CB 60610","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(BUS SECTION BF반)","2025-10-24 14:00","2025-10-24 16:30","2025-10-24 14:00","2025-10-24 16:30","연속"]
[152,"인천","시흥","신시화남정왕#1 T/L","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(64BF반)","2025-10-31 14:00","2025-10-31 18:00","2025-10-31 14:00","2025-10-31 18:00","연속"]
[153,"인천","시흥","신시화중시화#1 T/L","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(63BF반)","2025-10-31 09:00","2025-10-31 14:00","2025-10-31 09:00","2025-10-31 14:00","연속"]
[154,"인천","시흥","신시화S/S SEC CB 65660","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(BUS SECTION BF반)","2025-10-24 16:30","2025-10-24 18:00","2025-10-24 16:30","2025-10-24 18:00","연속"]
[155,"인천","시흥","신시흥도림#2 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","철탑 추락방지장치(수평) 및 조류착지방지장치 설치 No.0.5~34 (30기)","2025-10-04 07:00","2025-10-09 18:00","취소","취소","연속"]
[156,"인천","시흥","신시흥남동#2 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","철탑 추락방지장치(수평) 및 조류착지방지장치 설치 No.1~35 (35기)","2025-10-04 07:00","2025-10-09 18:00","취소","취소","연속"]
[157,"인천","시흥","신시흥시화#1 T/L","신시흥시화#1T/L 보호반 대체","신시흥시화#1T/L 보호반 대체","2025-10-22 09:00","2025-10-24 18:00","2025-10-22 09:00","2025-10-24 18:00","연속"]
[158,"인천","시흥","신시흥시화#2 T/L","신시흥시화#2T/L 보호반 대체","신시흥시화#2T/L 보호반 대체","2025-10-27 09:00","2025-10-30 18:00","2025-10-27 09:00","2025-10-30 18:00","연속"]
[159,"인천","시흥","학익연수#1 T/L","연수S/S  학익연수#1 T/L GIS 보통점검","연수S/S  학익연수#1 T/L GIS 보통점검","2025-10-03 14:00","2025-10-03 18:00","2025-10-03 14:00","2025-10-03 18:00","연속"]
[160,"인천","직할","갈산S/S SEC CB 65660","갈산S/S #65-#66 SEC GIS 보통점검","갈산S/S #65-#66 SEC GIS 보통점검","2025-10-30 09:30","2025-10-30 18:00","2025-10-30 09:30","2025-10-30 18:00","연속"]
[161,"인천","직할","갈산S/S CB 6200","갈산S/S #61-#66 BUS TIE GIS 보통점검","갈산S/S #61-#66 BUS TIE GIS 보통점검(6200)","2025-10-02 09:30","2025-10-02 18:00","2025-10-02 09:30","2025-10-02 18:00","연속"]
[162,"인천","직할","갈산부흥#1 T/L"," 갈산부흥#1T/L GIS 보통점검, 조작시험(양단)","갈산S/S GIS 보통점검, 부흥S/S GIS 조작시험","2025-10-23 09:30","2025-10-23 18:00","취소","취소","연속"]
[163,"인천","직할","갈산부흥#2 T/L"," 갈산부흥#2T/L GIS 보통점검, 조작시험(양단)","갈산S/S GIS 보통점검, 부흥S/S GIS 조작시험","2025-10-24 09:30","2025-10-24 18:00","취소","취소","연속"]
[164,"인천","직할","갈산부흥#3 T/L","갈산S/S 갈산부흥#3T/L GIS 보통점검","갈산S/S 갈산부흥#3T/L GIS 보통점검","2025-10-27 09:30","2025-10-27 18:00","취소","취소","연속"]
[165,"인천","직할","갈산도당#1 T/L","갈산S/S 갈산도당#1T/L GIS 보통점검","갈산S/S 갈산도당#1T/L GIS 보통점검","2025-10-28 09:30","2025-10-28 18:00","취소","취소","연속"]
[166,"인천","직할","갈산S/S SEC CB 60610","갈산S/S #60-#61 SEC GIS 보통점검","갈산S/S #60-#61 SEC GIS 보통점검","2025-10-29 09:30","2025-10-29 18:00","2025-10-29 09:30","2025-10-29 18:00","연속"]
[167,"인천","직할","갈산S/S CB 6100","갈산S/S #60-#65 BUS TIE GIS 보통점검","갈산S/S #60-#65 BUS TIE GIS 보통점검(6100)","2025-10-01 09:30","2025-10-01 18:00","2025-10-01 09:30","2025-10-01 18:00","연속"]
[168,"인천","직할","계양원창 T/L","25~26년 지중송전 협력회사공사","피뢰기 및 C/T점검","2025-10-23 09:00","2025-10-23 18:00","2025-10-23 09:00","2025-10-23 18:00","연속"]
[169,"인천","직할","계양북인천 T/L","25~26년 지중송전 협력회사공사","피뢰기 및 C/T점검","2025-10-24 09:00","2025-10-24 18:00","2025-10-24 09:00","2025-10-24 18:00","연속"]
[170,"인천","직할","계양불로#1 T/L","계양S/S 계양불로#1T/L GIS 정밀점검","계양S/S 계양불로#1T/L GIS 정밀점검","2025-10-27 09:00","2025-10-29 14:00","취소","취소","연속"]
[171,"인천","직할","계양불로#2 T/L","계양S/S 계양불로#2T/L GIS 정밀점검","계양S/S 계양불로#2T/L GIS 정밀점검","2025-10-29 14:00","2025-10-31 18:00","취소","취소","연속"]
[172,"인천","직할","부흥원미 T/L"," 부흥원미T/L GIS 초기점검(양단)"," 부흥원미T/L GIS 초기점검(양단)","2025-10-31 09:30","2025-10-31 18:00","2025-10-31 09:30","2025-10-31 18:00","연속"]
[173,"인천","직할","경서북인천#2 T/L","북인천S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","북인천S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","2025-10-25 15:00","2025-10-25 18:00","2025-10-25 15:00","2025-10-25 18:00","연속"]
[174,"인천","직할","북인천S/S #65 BUS","북인천S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","북인천S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","2025-10-25 15:00","2025-10-25 18:00","2025-10-25 15:00","2025-10-25 18:00","연속"]
[175,"인천","직할","신부평고강#2 T/L"," 신부평고강T/L 서울광명고속도로 지장이설공사(지중)","대상구간 :  신부평-고강T/L M/H#9∼10(294m) 공사내용 : 중간맨홀 및 관로 신설, 지중케이블 설치","2025-10-08 08:00","2025-10-12 18:00","2025-10-08 08:00","2025-10-12 18:00","연속"]
[176,"인천","직할","신부평고강#1 T/L"," 신부평고강T/L 서울광명고속도로 지장이설공사(지중)","대상구간 :  신부평-고강T/L M/H#9∼10(294m) 공사내용 : 중간맨홀 및 관로 신설, 지중케이블 설치","2025-10-03 08:00","2025-10-07 18:00","2025-10-03 08:00","2025-10-07 18:00","연속"]
[177,"경기북부","고양","지도능곡#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 보통점검","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[178,"경기북부","고양","백학남면#1 T/L","24~25년 경기북부 직할 가공송전협력회사 공사"," 백학남면T/L 피뢰기 설치","2025-10-13 10:00","2025-10-17 18:00","2025-10-13 10:00","2025-10-17 18:00","연속"]
[179,"경기북부","고양","신덕은금촌#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2025-10-01 07:00","2025-10-01 17:00","2025-10-01 07:00","2025-10-01 17:00","연속"]
[180,"경기북부","고양","신덕은금촌#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2025-10-29 07:00","2025-10-29 17:00","2025-10-29 07:00","2025-10-29 17:00","연속"]
[181,"경기북부","고양","신파주원흥#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2025-10-13 07:00","2025-10-17 17:00","2025-10-13 07:00","2025-10-17 17:00","연속"]
[182,"경기북부","고양","신파주원흥#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2025-10-20 07:00","2025-10-22 18:00","2025-10-20 07:00","2025-10-22 18:00","연속"]
[183,"경기북부","고양","신파주원흥#1 T/L","(선로시험가압)수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : 2025.2.25~2026.10.23","2025-10-23 09:00","2025-10-24 09:00","2025-10-23 09:00","2025-10-24 09:00","연속"]
[184,"경기북부","고양","월롱금촌#1 T/L","2025년 가공송전 순시점검 위탁공사(고양)","피뢰기 점검","2025-10-23 08:00","2025-10-23 18:00","2025-10-23 08:00","2025-10-23 18:00","연속"]
[185,"경기북부","고양","일산지도#2 T/L","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-10-22 09:00","2025-10-22 18:00","2025-10-22 09:00","2025-10-22 18:00","연속"]
[186,"경기북부","고양","고양일산#2 T/L","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[187,"경기북부","고양","일산송포#1 T/L","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-10-17 09:00","2025-10-17 18:00","2025-10-17 09:00","2025-10-17 18:00","연속"]
[188,"경기북부","고양","일산지도#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","불량애자, 점퍼선 교체","2025-10-31 07:00","2025-10-31 17:00","2025-10-31 07:00","2025-10-31 17:00","연속"]
[189,"경기북부","고양","고양일산#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","불량애자 교체","2025-10-31 07:00","2025-10-31 17:00","2025-10-31 07:00","2025-10-31 17:00","연속"]
[190,"경기북부","고양","일산지도#1 T/L","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-10-21 09:00","2025-10-21 18:00","2025-10-21 09:00","2025-10-21 18:00","연속"]
[191,"경기북부","고양","일산호수#2 T/L","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-10-24 09:00","2025-10-24 18:00","2025-10-24 09:00","2025-10-24 18:00","연속"]
[192,"경기북부","고양","일산호수#1 T/L","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-10-23 09:00","2025-10-23 18:00","2025-10-23 09:00","2025-10-23 18:00","연속"]
[193,"경기북부","고양","일산S/S SEC CB 60610","24-25 변전협력회사 총액공사","170kV GIS 보통점검","2025-10-14 09:00","2025-10-14 18:00","2025-10-14 09:00","2025-10-14 18:00","연속"]
[194,"경기북부","고양","일산S/S SEC CB 65660","24-25 변전협력회사 총액공사","170kV GIS 보통점검","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[195,"경기북부","고양","고양일산#1 T/L","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[196,"경기북부","고양","일산송포#2 T/L","2025-2026 지중송전 협력회사 공사","고양전력지사 관내 지중송전설비 점검","2025-10-20 09:00","2025-10-21 18:00","2025-10-20 09:00","2025-10-21 18:00","연속"]
[197,"경기북부","구리","가평화천HP T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[198,"경기북부","구리","내촌용정#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 유사고장 점검","2025-10-28 14:00","2025-10-28 18:00","2025-10-28 14:00","2025-10-28 18:00","연속"]
[199,"경기북부","구리","내촌용정#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 유사고장 점검","2025-10-28 09:00","2025-10-28 14:00","2025-10-28 09:00","2025-10-28 14:00","연속"]
[200,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사(No.6~8) (병가  동서울-서종 T/L No.61~63)","2025-10-23 07:00","2025-10-31 18:00","2025-10-23 07:00","2025-10-31 18:00","연속"]
[201,"경기북부","구리","신장덕소#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사(No.6~8) (병가  동서울-서종 T/L No.61~63)","2025-10-23 07:00","2025-10-31 18:00","2025-10-23 07:00","2025-10-31 18:00","연속"]
[202,"경기북부","구리","덕소마석#1 T/L","구리송전협력회사 공사_추락방지장치 설치"," 덕소-마석#1T/L No.20 관형주 레일형 수평 추락방지장치 설치  덕소-마석#1T/L 암 및 바디 길이 실측(No.17, 45, 46) 3개소","2025-10-30 07:00","2025-10-30 18:00","2025-10-30 07:00","2025-10-30 18:00","연속"]
[203,"경기북부","구리","덕소마석#2 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","C/T 피뢰기 점검 및 금구류 교체","2025-10-31 09:00","2025-10-31 18:00","2025-10-31 09:00","2025-10-31 18:00","연속"]
[204,"경기북부","구리","덕소진건#1 T/L","구리송전협력회사 공사_추락방지장치 설치"," 덕소-진건#1T/L 암 및 바디 길이 실측(No.1, 2) 2개소","2025-10-31 07:00","2025-10-31 12:00","2025-10-31 07:00","2025-10-31 12:00","연속"]
[205,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사(NO.6~8) (병가  동서울-서종 No.61~63)","2025-10-13 07:00","2025-10-22 18:00","2025-10-13 07:00","2025-10-22 18:00","연속"]
[206,"경기북부","구리","미금광장 T/L","구리송전협력회사 공사_추락방지장치 설치"," 미금-광장T/L 레일형 관형주 암 및 바디 길이 실측(No.7~19, 32) 14개소","2025-10-27 07:00","2025-10-28 18:00","2025-10-27 07:00","2025-10-28 18:00","연속"]
[207,"경기북부","구리","미금화양 T/L","구리송전협력회사 공사_추락방지장치 설치"," 미금-화양T/L 관형주 암 및 바디 길이 실측(No.7~19, 32) 14개소","2025-10-29 07:00","2025-10-29 18:00","2025-10-29 07:00","2025-10-29 18:00","연속"]
[208,"경기북부","구리","동서울서종#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사(No.6~8) (병가  동서울-서종 T/L No.61~63)","2025-10-23 07:00","2025-10-31 18:00","2025-10-23 07:00","2025-10-31 18:00","연속"]
[209,"경기북부","구리","동서울서종#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사(NO.6~8) (병가  동서울-서종 No.61~63)","2025-10-13 07:00","2025-10-22 18:00","2025-10-13 07:00","2025-10-22 18:00","연속"]
[210,"경기북부","구리","진건별내#1 T/L","구리갈매역세권 공공주택지구 지장송전선로 이설공사"," 진건-별내T/L M/H#3~M/H#5 구간 이설","2025-10-30 09:00","2025-12-12 18:00","취소","취소","연속"]
[211,"경기북부","구리","별내진접 T/L","남양주진접2 공공주택지구 송전선로 임시이설공사","남양주 진접2 공공주택지구 지중화 전 임시선로 구성(요청자 직접시행)","2025-10-22 07:00","2025-10-25 18:00","2025-10-22 07:00","2025-10-25 18:00","연속"]
[212,"경기북부","구리","장암진접#1 T/L","남양주진접2 공공주택지구 송전선로 임시이설공사","남양주 진접2 공공주택지구 지중화 전 임시선로 구성(요청자 직접시행)","2025-10-21 07:00","2025-10-21 18:00","2025-10-21 07:00","2025-10-21 18:00","연속"]
[213,"경기북부","구리","장암진접#1 T/L","남양주진접2 공공주택지구 송전선로 임시이설공사","남양주 진접2 공공주택지구 지중화 전 임시선로 구성(요청자 직접시행)","2025-10-26 07:00","2025-10-28 18:00","2025-10-26 07:00","2025-10-28 18:00","연속"]
[214,"경기북부","구리","마석청평HP#2 T/L","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 보통점검","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[215,"경기북부","구리","청평H/P #2 M.Tr CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-10-20 09:00","2025-10-20 18:00","2025-10-20 09:00","2025-10-20 18:00","연속"]
[216,"경기북부","구리","가평청평HP#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-10-21 09:00","2025-10-22 18:00","2025-10-21 09:00","2025-10-22 18:00","연속"]
[217,"경기북부","구리","가평청평HP#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-10-23 09:00","2025-10-24 18:00","2025-10-23 09:00","2025-10-24 18:00","연속"]
[218,"경기북부","구리","청평HP의암HP T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-10-31 09:00","2025-10-31 18:00","2025-10-31 09:00","2025-10-31 18:00","연속"]
[219,"경기북부","구리","마석청평HP#1 T/L","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 보통점검","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[220,"경기북부","구리","청평P/P #1 M.Tr 2차 CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-10-10 09:00","2025-10-10 14:00","2025-10-10 09:00","2025-10-10 14:00","연속"]
[221,"경기북부","구리","청평P/P #2 M.Tr 2차 CB","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-10-10 14:00","2025-10-10 18:00","2025-10-10 14:00","2025-10-10 18:00","연속"]
[222,"경기북부","직할","백석덕계#2 T/L","25년 양주전력TF 170kV GIS 점검공사","170kV GIS 정밀점검(#1M.Tr 1차) 시험가압용 선로","2025-10-31 09:00","2025-10-31 18:00","2025-10-31 09:00","2025-10-31 18:00","연속"]
[223,"경기북부","직할","옥정동두천#1 T/L","2024-25년 경기북부 직할 변전협력 총액공사","동두천S/S  옥정-동두천#1T/L GIS 조작시험","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[224,"경기북부","직할","신포천동두천#1 T/L","2024-25년 경기북부 직할 변전협력 총액공사","동두천S/S  신포천-동두천#1T/L GIS 조작시험","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[225,"경기북부","직할","신의정부용현#1 T/L","2025년 경기북부 직할 170kV GIS 점검공사","신의정부S/S 신의정부-용현 #1T/L 정밀점검공사","2025-10-13 09:00","2025-10-14 18:00","2025-10-13 09:00","2025-10-14 18:00","연속"]
[226,"경기북부","직할","신의정부내촌#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신가평-신의정부#1 T/L No.120~134,136,138 (子 :  신의정부-내촌#1 T/L No.23~9,7,5)","2025-10-15 07:00","2025-10-20 12:00","2025-10-15 07:00","2025-10-20 12:00","연속"]
[227,"경기북부","직할","신의정부용현#2 T/L","2025년 경기북부 직할 170kV GIS 점검공사","신의정부S/S 신의정부-용현 #2T/L 정밀점검공사","2025-10-15 09:00","2025-10-16 18:00","2025-10-15 09:00","2025-10-16 18:00","연속"]
[228,"경기북부","직할","신의정부송우#1 T/L","2025년 경기북부 직할 170kV GIS 점검공사","신의정부S/S 신의정부-송우#1T/L 정밀점검공사","2025-10-20 12:00","2025-10-22 18:00","2025-10-20 12:00","2025-10-22 18:00","연속"]
[229,"경기북부","직할","신의정부송우#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신의정부-내촌#1 T/L No.1~4 (子 :  신의정부-송우#2 T/L No.1~4)","2025-10-20 07:00","2025-10-20 12:00","2025-10-20 07:00","2025-10-20 12:00","연속"]
[230,"경기북부","직할","신의정부내촌#2 T/L","2025년 경기북부 직할 170kV GIS 점검공사","신의정부S/S 신의정부-내촌#2T/L 정밀점검공사","2025-10-20 12:00","2025-10-24 18:00","2025-10-20 12:00","2025-10-24 18:00","연속"]
[231,"경기북부","직할","양주금촌#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","압축인류크램프, 불량애자 교체","2025-10-30 07:00","2025-10-30 17:00","2025-10-30 07:00","2025-10-30 17:00","연속"]
[232,"경기북부","직할","양주지축#2 T/L","가공송전 순시점검 위탁공사(고양)","정밀점검(양주-은평T/L) 관련 병가선로 휴전","2025-10-20 08:00","2025-10-24 18:00","2025-10-20 08:00","2025-10-24 18:00","연속"]
[233,"경기북부","직할","양주은평#1 T/L","가공송전 순시점검 위탁공사(고양)","정밀점검","2025-10-20 08:00","2025-10-24 18:00","2025-10-20 08:00","2025-10-24 18:00","연속"]
[234,"경기북부","직할","양주금촌#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","점퍼선 교체","2025-10-31 07:00","2025-10-31 17:00","2025-10-31 07:00","2025-10-31 17:00","연속"]
[235,"경기북부","직할","양주지축#1 T/L","가공송전 순시점검 위탁공사(고양)","정밀점검","2025-10-13 08:00","2025-10-17 18:00","2025-10-13 08:00","2025-10-17 18:00","연속"]
[236,"경기북부","직할","양주은평#2 T/L","가공송전 순시점검 위탁공사(고양)","정밀점검","2025-10-13 08:00","2025-10-17 18:00","2025-10-13 08:00","2025-10-17 18:00","연속"]
[237,"경기북부","직할","양주고양#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","병가선로 휴전","2025-10-30 07:00","2025-10-30 17:00","2025-10-30 07:00","2025-10-30 17:00","연속"]
[238,"경기북부","직할","양주고양#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","병가선로 휴전","2025-10-31 07:00","2025-10-31 17:00","2025-10-31 07:00","2025-10-31 17:00","연속"]
[239,"경기북부","직할","옥정동두천#2 T/L"," 옥정S/S #4M.Tr용 개폐장치 설치공사"," 옥정S/S #4M.Tr용 개폐장치 설치공사","2025-10-13 09:00","2025-10-16 18:00","2025-10-13 09:00","2025-10-16 18:00","연속"]
[240,"경기북부","직할","옥정송우#1 T/L"," 옥정S/S #4M.Tr용 개폐장치 설치공사","무부하가압선로","2025-10-14 13:00","2025-10-15 13:00","2025-10-14 13:00","2025-10-15 13:00","연속"]
[241,"경기북부","직할","옥정송우#1 T/L"," 옥정S/S #4M.Tr용 개폐장치 설치공사","무부하가압선로","2025-10-16 18:00","2025-10-17 18:00","2025-10-16 18:00","2025-10-17 18:00","연속"]
[242,"경기","군포","사강남양#2 T/L","남양S/S  남양-사강#2T/L GIS 유사고장 점검","남양S/S  남양-사강#2T/L GIS 유사고장(효성제발청) 점검","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[243,"경기","군포","반월시화#1 T/L","반월S/S  반월-시화#1T/L LA 대체","반월S/S  반월-시화#1T/L LA 대체","2025-10-29 09:00","2025-10-29 18:00","2025-10-29 09:00","2025-10-29 18:00","연속"]
[244,"경기","군포","반월시화#2 T/L","반월S/S  반월-시화#2T/L LA 대체","반월S/S  반월-시화#2T/L LA 대체","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[245,"경기","군포","서서울#2S/S #68 BUS","[정밀무부하] 서서울2S/S #68-#69 SEC GIS 정밀점검","서서울2S/S  #68-#69 SEC GIS 정밀점검 무부하가압용","2025-10-28 15:00","2025-10-28 17:00","2025-10-28 15:00","2025-10-28 17:00","연속"]
[246,"경기","군포","서서울#2일동#1 T/L","[정밀무부하] 서서울2S/S #68-#69 SEC GIS 정밀점검","서서울2S/S  #68-#69 SEC GIS 정밀점검 무부하가압용","2025-10-28 15:00","2025-10-28 17:00","2025-10-28 15:00","2025-10-28 17:00","연속"]
[247,"경기","군포","서서울#2S/S SEC CB 68690","[정밀] 서서울2S/S #68-#69 SEC GIS 정밀점검","서서울2S/S  #68-#69 SEC GIS 정밀점검 시행","2025-10-27 09:00","2025-10-28 18:00","2025-10-27 09:00","2025-10-28 18:00","연속"]
[248,"경기","군포","서서울산본#2 T/L","서서울S/S  서서울-산본#2T/L LA 대체","서서울S/S  서서울-산본#2T/L LA 대체","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[249,"경기","군포","목내성곡#1 T/L","[정밀무부하] 성곡S/S #4M.Tr 1차 GIS 정밀점검","성곡S/S #4M.Tr 1차(6433) GIS 정밀점검 무부하가압용","2025-10-23 15:00","2025-10-23 17:00","2025-10-23 15:00","2025-10-23 17:00","연속"]
[250,"경기","군포","시화중시화 T/L","시화S/S  시화-중시화T/L GIS 보통점검","시화S/S  시화-중시화T/L GIS 보통점검","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[251,"경기","군포","성포안산#2 T/L","[정밀] 안산S/S 성포-안산#2T/L GIS 정밀점검","안산S/S 성포-안산#2T/L GIS 정밀점검 시행","2025-10-01 09:00","2025-10-02 18:00","2025-10-01 09:00","2025-10-02 18:00","연속"]
[252,"경기","군포","안산반월열병합 T/L CB","안산S/S  반열T/L GIS 보통점검","안산S/S  반열T/L GIS 보통점검","2025-10-04 09:00","2025-10-04 18:00","취소","취소","연속"]
[253,"경기","군포","화성장덕#1 T/L","장덕S/S 화성-장덕#1T/L GIS 유사고장(일진제볼스토퍼) 점검","장덕S/S 화성-장덕#1T/L GIS 유사고장(일진제볼스토퍼) 점검","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[254,"경기","군포","장덕마도#1 T/L","[정밀무부하] 장덕S/S 장덕-현대자동차#1T/L GIS 정밀점검","장덕S/S  장덕-현대자동차#1T/L GIS 정밀점검 무부하가압용","2025-10-26 14:00","2025-10-26 16:00","2025-10-26 14:00","2025-10-26 16:00","연속"]
[255,"경기","군포","조암구문천#1 T/L","조암S/S  조암-구문천#1T/L GIS 유사고장 점검","조암S/S  조암-구문천#1T/L GIS 유사고장(현대제 방압변) 점검","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[256,"경기","동부","감곡가남#2 T/L"," 이천-가남 등 2개T/L 용량증대 선종교체공사"," 감곡-가남T/L No.25~가남S/S 18.2km, 선종교체 ACSR240㎟→ASCC310㎟","2025-10-15 07:00","2025-11-06 18:00","2025-10-15 07:00","2025-11-06 18:00","연속"]
[257,"경기","동부","분당오포#2 T/L","분당S/S  장기사용 GIS 교체공사","분당S/S  장기사용 GIS 교체공사 안전이격확보 및 무부하가압용","2025-10-15 09:00","2025-11-05 18:00","2025-10-15 09:00","2025-11-05 18:00","연속"]
[258,"경기","동부","분당S/S CB 6713","효성제 GIS 발청 교체작업 분당#7G/T","효성제 GIS 발청 분당:#7G/T, (#7G/T O/H : 10.14~10.21)","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[259,"경기","동부","성현분당#1 T/L","성현-분당T/L 추락방지장치 및 폴리머애자 설치","수직, 수평추락방지 및 폴리머애자 설치(야탑-성현과 병가)","2025-10-13 07:30","2025-10-14 18:00","취소","취소","연속"]
[260,"경기","동부","성현분당#1 T/L","성현-분당T/L 추락방지장치 및 폴리머애자 설치","수직, 수평추락방지 및 폴리머애자 설치(야탑-성현과 병가, 10/13-10/14까지 작업)","2025-10-01 07:30","2025-10-02 18:00","취소","취소","연속"]
[261,"경기","성남","기흥신갈#1 T/L","2025년 성남전력 변전협력회사 총액공사","GIS 유면계 누유보수","2025-10-23 09:00","2025-10-23 14:00","2025-10-23 09:00","2025-10-23 14:00","연속"]
[262,"경기","성남","신봉이의#1 T/L"," 신봉S/S #3M.Tr 증설공사","#3M.Tr 1차 GIS 설치 - 모선부 가스 감압 및 무부하 가압용","2025-10-20 14:00","2025-11-05 14:00","2025-10-20 14:00","2025-11-05 14:00","연속"]
[263,"경기","성남","신성남S/S SEC CB 66670","2025년 성남전력 변전협력회사 총액공사","GIS 조작시험","2025-10-01 14:00","2025-10-01 18:00","2025-10-01 14:00","2025-10-01 18:00","연속"]
[264,"경기","성남","신성남S/S SEC CB 61620","2025년 성남전력 변전협력회사 총액공사","GIS 조작시험","2025-10-01 09:00","2025-10-01 14:00","2025-10-01 09:00","2025-10-01 14:00","연속"]
[265,"경기","성남","신성남S/S CB 6200","2025년 성남전력 변전협력회사 총액공사","GIS 조작시험","2025-10-02 09:00","2025-10-02 14:00","2025-10-02 09:00","2025-10-02 14:00","연속"]
[266,"경기","성남","신수원S/S #61 BUS","신수원S/S  계통조정 공사(1차분)","- #63M.Tr 1차 GIS, (구)#62M.Tr 1차 GIS(운휴Bay), 공GIB(1Bay) 철거 - (신)61-62, 66-67SEC 설치, #63M.Tr 1차 GIS 설치","2025-10-30 09:00","2025-11-13 18:00","취소","취소","연속"]
[267,"경기","성남","신수원S/S #66 BUS","신수원S/S  계통조정 공사(1차분)","- #63M.Tr 1차 GIS, (구)#62M.Tr 1차 GIS(운휴Bay), 공GIB(1Bay) 철거 - (신)61-62, 66-67SEC 설치, #63M.Tr 1차 GIS 설치","2025-10-27 09:00","2025-10-29 18:00","취소","취소","연속"]
[268,"경기","성남","신용인기흥#2 T/L","수평 추락방지장치 설치공사","24-25년 경기직할 송전협력회사 공사(수평 추락방지장치 설치공사)","2025-10-27 07:00","2025-10-28 18:00","2025-10-27 07:00","2025-10-28 18:00","연속"]
[269,"경기","직할","관양동안양#2 T/L","동안양,관양S/S 관양-동안양#2T/L GIS 초기점검","동안양, 관양 : 관양-동안양#2T/L GIS 초기점검","2025-10-22 09:00","2025-10-22 18:00","2025-10-22 09:00","2025-10-22 18:00","연속"]
[270,"경기","직할","관양동안양#1 T/L","동안양 관양-동안양#1T/L GIS 초기점검","동안양 : 관양-동안양#1T/L GIS 초기점검","2025-10-21 09:00","2025-10-21 18:00","2025-10-21 09:00","2025-10-21 18:00","연속"]
[271,"경기","직할","서서울서수원#2 T/L","서수원S/S 서서울-서수원#2T/L LA 보통점검","서수원 : 서서울-서수원#2T/L LA 보통점검","2025-10-17 14:00","2025-10-17 18:00","2025-10-17 14:00","2025-10-17 18:00","연속"]
[272,"경기","직할","서서울서수원#1 T/L","서수원S/S 서서울-서수원#1T/L LA 보통점검","서수원 : 서서울-서수원#1T/L LA 보통점검","2025-10-17 09:00","2025-10-17 14:00","2025-10-17 09:00","2025-10-17 14:00","연속"]
[273,"경기","직할","서수원율전#1 T/L","율전S/S 서수원-율전#1T/L 보통점검","율전 : 서수원-율전#1T/L GIS 보통점검","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[274,"경기","직할","화성수촌#2 T/L","화성S/S 화성-수촌#2T/L LA,CVT 보통점검","화성 : 화성-수촌#2T/L LA,CVT 보통점검","2025-10-02 14:00","2025-10-02 18:00","2025-10-02 14:00","2025-10-02 18:00","연속"]
[275,"경기","직할","화성수촌#1 T/L","화성S/S 화성-수촌#1T/L LA,CVT 보통점검","화성 : 화성-수촌#1T/L LA,CVT 보통점검","2025-10-02 09:00","2025-10-02 14:00","2025-10-02 09:00","2025-10-02 14:00","연속"]
[276,"경기","직할","화성남양#2 T/L","화성S/S 화성-남양#2T/L GIS 조작시험","화성 : 화성-남양#2T/L GIS 조작시험","2025-10-13 14:00","2025-10-13 18:00","2025-10-13 14:00","2025-10-13 18:00","연속"]
[277,"경기","직할","화성남양#1 T/L","화성S/S 화성-남양#1T/L GIS 조작시험","화성 : 화성-남양#1T/L GIS 조작시험","2025-10-13 09:00","2025-10-13 14:00","2025-10-13 09:00","2025-10-13 14:00","연속"]
[278,"경기","평택","고덕S/S CB 6200","2025년 평택전력 변전협력회사 총액공사(고덕S/S 6200)","고덕S/S  #61-#66 BUS TIE GIS(6200) GIS 보통점검","2025-10-27 09:00","2025-10-27 18:00","취소","취소","연속"]
[279,"경기","평택","포승만호 T/L"," 희곡분기 지중T/L 건설공사","1. 공사구간 -  희곡∼포승 지중T/L M/H#1 ,희곡∼청북 지중T/L M/H#1 -  희곡S/S ∼ 만호S/S 2. 선종/회선길이 -  XLPE 2,000㎟, 2C×4.33㎞[희곡 S/S ~ (포승/청북) 지중T/L M/H#1] -  XLPE 2,000㎟, 2C×3.95㎞[희곡 S/S ~ 만","2025-10-13 09:00","2025-12-05 18:00","2025-10-13 09:00","2025-12-05 18:00","연속"]
[280,"경기","평택","오산향남#1 T/L","2025년 변전협력회사 총액공사(오산향남1)","오산S/S 오산향남#1T/L GIS 보통점검","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[281,"경기","평택","오산향남#2 T/L","2025년 변전협력회사 총액공사(오산향남2)","오산S/S 오산향남#2T/L GIS 보통점검","2025-10-28 09:00","2025-10-28 18:00","2025-10-28 09:00","2025-10-28 18:00","연속"]
[282,"경기","평택","원정평택TP#1 T/L","2025 평택전력 변전협력 총액공사(원정평택TP1)","원정S/S 원정-평택T/P #1T/L GIS 조작시험, PT&LA 보통점검","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[283,"경기","평택","평택추팔#1 T/L","2025년 평택전력 변전협력회사 총액공사(평택추팔1)","평택S/S 평택추팔#1 T/L DS부 과열조치","2025-10-29 09:00","2025-10-29 18:00","2025-10-29 09:00","2025-10-29 18:00","연속"]
[284,"경기","평택","평택오성CC#2 T/L","2025년 평택전력 변전협력회사 총액공사(평택오성2)","평택S/S 평택-오성C/C #2T/L PT, LA 보통점검","2025-10-14 09:00","2025-10-14 18:00","2025-10-14 09:00","2025-10-14 18:00","연속"]
[285,"경기","평택","평택추팔#2 T/L","2025년 평택전력 변전협력회사 총액공사(평택추팔2)","평택S/S 평택추팔#2 T/L DS부 과열조치","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[286,"경기","평택","평택T/P CB 6100","2025년 평택전력 변전협력회사 총액공사","인터록 관련 보조계전기 불량 교체(차단기 트립불가 현상 조치)","2025-10-30 09:00","2025-10-30 14:00","2025-10-30 09:00","2025-10-30 14:00","연속"]
[287,"경기","평택","평택T/P CB 6200","2025년 평택전력 변전협력회사 총액공사","인터록 관련 보조계전기 불량 교체(차단기 트립불가 현상 조치)","2025-10-30 14:00","2025-10-30 18:00","2025-10-30 14:00","2025-10-30 18:00","연속"]
[288,"경기","평택","평택T/P SEC CB 60610","2025년 평택전력 변전협력회사 총액공사","인터록 관련 보조계전기 불량 교체(차단기 트립불가 현상 조치)","2025-10-31 09:00","2025-10-31 14:00","2025-10-31 09:00","2025-10-31 14:00","연속"]
[289,"경기","평택","평택T/P SEC CB 65660","2025년 평택전력 변전협력회사 총액공사","인터록 관련 보조계전기 불량 교체(차단기 트립불가 현상 조치)","2025-10-31 14:00","2025-10-31 18:00","2025-10-31 14:00","2025-10-31 18:00","연속"]
[290,"경기","평택","고덕진위#2 T/L","345kV 고덕2-서안성#2T/L 피뢰기 설치공사(병가선로 안전이격)","345kV 고덕2-서안성#2T/L 피뢰기 설치공사 4회선 병가구간 안전이격","2025-10-20 08:00","2025-10-20 18:00","2025-10-20 08:00","2025-10-20 18:00","연속"]
[291,"강원","강릉","간성인제#2 T/L","2025년 강릉전력지사 변전협력회사 총액공사","170kV GIS 초기점검","2025-10-14 10:00","2025-10-14 18:00","2025-10-14 10:00","2025-10-14 18:00","연속"]
[292,"강원","강릉","간성인제#1 T/L","2025년 강릉전력지사 변전협력회사 총액공사","170kV GIS 초기점검","2025-10-13 10:00","2025-10-13 18:00","2025-10-13 10:00","2025-10-13 18:00","연속"]
[293,"강원","강릉","강릉영동TP T/L","2024~2025년 가공송전협력회사 총액공사","○ 전선접속개소 해소공사 (40.1-41)","2025-10-14 08:00","2025-10-14 18:00","2025-10-14 08:00","2025-10-14 18:00","연속"]
[294,"강원","강릉","신양양인제#2 T/L","2025년 강릉전력지사 변전협력회사 총액공사","송전선로 LA 대체","2025-10-15 10:00","2025-10-15 18:00","2025-10-15 10:00","2025-10-15 18:00","연속"]
[295,"강원","강릉","신양양인제#1 T/L","신양양S/S 수리풍력TL 증설공사","수리풍력TL CB부 무부하 가압(24H)","2025-10-13 09:00","2025-10-14 12:00","2025-10-13 09:00","2025-10-14 12:00","연속"]
[296,"강원","강릉","신양양양양#2 T/L","2025년 강릉전력지사 변전협력회사 총액공사","송전선로 피뢰기 대체","2025-10-22 10:00","2025-10-22 18:00","2025-10-22 10:00","2025-10-22 18:00","연속"]
[297,"강원","강릉","횡계올림픽 T/L","25년 가공송전 순시점검 위탁공사","정밀점검(승탑) : No.2~96","2025-10-01 08:00","2025-10-01 17:00","2025-10-01 08:00","2025-10-01 17:00","연속"]
[298,"강원","강릉","평창올림픽 T/L","25년 가공송전 순시점검 위탁공사","정밀점검(승탑) : No.1~96","2025-10-15 08:00","2025-10-22 17:00","2025-10-15 08:00","2025-10-22 17:00","연속"]
[299,"강원","강릉","주진평창#1 T/L"," 신양양속초 등 3개T/L 추락방지장치설치공사","수직 및 수평 추락방지장치 설치","2025-10-27 07:00","2025-10-31 18:00","2025-10-27 07:00","2025-10-31 18:00","연속"]
[300,"강원","강릉","횡계평창 T/L","25년 가공송전 순시점검 위탁공사","정밀점검(승탑) : No. 2~96","2025-10-23 08:00","2025-10-31 17:00","2025-10-23 08:00","2025-10-31 17:00","연속"]
[301,"강원","동해","동해강릉 T/L"," 동해분기T/L 안전이격확보공사","동해분기T/L 안전이격확보공사","2025-10-18 13:00","2025-10-31 18:00","2025-10-18 13:00","2025-10-31 18:00","연속"]
[302,"강원","동해","동해영동TP T/L"," 동해분기T/L 안전이격확보공사","동해분기T/L 안전이격확보공사","2025-10-18 13:00","2025-10-31 18:00","2025-10-18 13:00","2025-10-31 18:00","연속"]
[303,"강원","동해","북평영동TP#1 T/L","2024~25년 동해전력지사 가공송전 협력회사 공사","SB댐퍼 철거","2025-10-18 09:00","2025-10-18 13:00","2025-10-18 09:00","2025-10-18 13:00","연속"]
[304,"강원","동해","이원삼척 T/L","2025년 동해전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-10-13 09:00","2025-10-15 13:00","2025-10-13 09:00","2025-10-15 13:00","연속"]
[305,"강원","동해","동해이원#1 T/L","2025년 동해전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-10-22 13:00","2025-10-24 18:00","2025-10-22 13:00","2025-10-24 18:00","연속"]
[306,"강원","동해","동해이원#2 T/L","2025년 동해전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-10-20 09:00","2025-10-22 13:00","2025-10-20 09:00","2025-10-22 13:00","연속"]
[307,"강원","동해","이원S/S CB 6100","2025년 동해전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-10-15 13:00","2025-10-17 18:00","2025-10-15 13:00","2025-10-17 18:00","연속"]
[308,"강원","원주","원주서원주#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","추락방지장치 설치","2025-10-27 07:00","2025-10-28 18:00","2025-10-27 07:00","2025-10-28 18:00","연속"]
[309,"강원","원주","신제천남원주#1 T/L","2025년 원주전력지사  GIS 정밀점검 공사"," GIS 정밀점검","2025-10-25 09:00","2025-10-26 18:00","2025-10-25 09:00","2025-10-26 18:00","연속"]
[310,"강원","원주","둔내횡성#2 T/L"," 북원주-횡성 등 3개T/L 피뢰기 설치공사","6회선 구간 안전확보","2025-10-13 07:00","2025-10-13 18:00","2025-10-13 07:00","2025-10-13 18:00","연속"]
[311,"강원","원주","문막지제#2 T/L","25년 원주전력지사 변전협력회사 총액공사","GIS 보통점검 전자변교체","2025-10-14 10:00","2025-10-14 18:00","2025-10-14 10:00","2025-10-14 18:00","연속"]
[312,"강원","원주","원주북원주#2 T/L"," 북원주-횡성 등 3개T/L 피뢰기 설치공사","4회선 병가구간 안전확보","2025-10-19 07:00","2025-10-22 18:00","2025-10-19 07:00","2025-10-22 18:00","연속"]
[313,"강원","원주","북원주횡성#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","관형지지물 수평레일 설치","2025-10-23 07:00","2025-10-26 18:00","2025-10-23 07:00","2025-10-26 18:00","연속"]
[314,"강원","원주","원주북원주#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","관형지지물 수평레일 설치","2025-10-24 07:00","2025-10-27 18:00","2025-10-24 07:00","2025-10-27 18:00","연속"]
[315,"강원","원주","북원주횡성#1 T/L"," 북원주-횡성 등 3개T/L 피뢰기 설치공사","송전선로용 피뢰기 설치","2025-10-13 07:00","2025-10-22 18:00","2025-10-13 07:00","2025-10-22 18:00","연속"]
[316,"강원","원주","상남인제#2 T/L","25년 원주전력지사 변전협력회사 총액공사","차단기 동작시험 피뢰기 하자점검","2025-10-16 10:00","2025-10-16 18:00","2025-10-16 10:00","2025-10-16 18:00","연속"]
[317,"강원","원주","상남인제#1 T/L","25년 원주전력지사 변전협력회사 총액공사","차단기 동작시험 피뢰기 하자점검","2025-10-15 10:00","2025-10-15 18:00","2025-10-15 10:00","2025-10-15 18:00","연속"]
[318,"강원","원주","서원주문막#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","추락방지장치 설치","2025-10-28 07:00","2025-10-31 18:00","2025-10-28 07:00","2025-10-31 18:00","연속"]
[319,"강원","원주","홍천S/S SEC CB 65660"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-16 14:00","2025-10-20 18:00","2025-10-16 14:00","2025-10-20 18:00","연속"]
[320,"강원","원주","홍천S/S #66 BUS"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-16 14:00","2025-10-20 18:00","2025-10-16 14:00","2025-10-20 18:00","연속"]
[321,"강원","원주","횡성홍천#2 T/L"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-15 09:00","2025-10-16 18:00","2025-10-15 09:00","2025-10-16 18:00","연속"]
[322,"강원","원주","홍천S/S SEC CB 60610"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-13 09:00","2025-10-16 14:00","2025-10-13 09:00","2025-10-16 14:00","연속"]
[323,"강원","원주","홍천S/S #61 BUS"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-13 09:00","2025-10-16 14:00","2025-10-13 09:00","2025-10-16 14:00","연속"]
[324,"강원","원주","홍천소양강HP T/L"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-13 09:00","2025-10-15 18:00","2025-10-13 09:00","2025-10-15 18:00","연속"]
[325,"강원","원주","홍천S/S SEC CB 65660"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[326,"강원","원주","홍천S/S #66 BUS"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[327,"강원","원주","홍천S/S SEC CB 60610"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-29 09:00","2025-10-29 18:00","2025-10-29 09:00","2025-10-29 18:00","연속"]
[328,"강원","원주","홍천S/S #61 BUS"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-29 09:00","2025-10-29 18:00","2025-10-29 09:00","2025-10-29 18:00","연속"]
[329,"강원","원주","홍천소양강HP T/L"," 소양T/L No.76, 77 안전이격 확보공사(협력회사공사)","- No.76, 77  2C 철탑 2기 교체(인클로징) - No.74~79, ASCC/TW 430㎟×S, 3.681C-㎞ 전선교체","2025-10-27 09:00","2025-11-03 18:00","2025-10-27 09:00","2025-11-03 18:00","연속"]
[330,"강원","원주","횡성홍천#2 T/L"," 홍천 STATCOM 건설사업"," GIS 1CCT 설치","2025-10-18 09:00","2025-10-20 18:00","2025-10-18 09:00","2025-10-20 18:00","연속"]
[331,"강원","원주","횡성홍천#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","불량애자 교체","2025-10-23 07:00","2025-10-23 18:00","2025-10-23 07:00","2025-10-23 18:00","연속"]
[332,"강원","원주","횡성홍천#2 T/L"," 북원주-횡성 등 3개T/L 피뢰기 설치공사","4회선 병가구간 안전확보","2025-10-13 07:00","2025-10-18 18:00","2025-10-13 07:00","2025-10-18 18:00","연속"]
[333,"강원","직할","남춘천춘천열병합#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","남춘천춘천열병합#2 T/L GIS 초기점검","2025-10-14 09:00","2025-10-14 18:00","2025-10-14 09:00","2025-10-14 18:00","연속"]
[334,"강원","직할","홍천남춘천 T/L","남춘천S/S  장기사용 GIS 대체공사","● 2차공정 -  홍천-남춘천T/L GIS -  #2M.Tr 1차 GIS","2025-10-27 09:00","2025-11-28 18:00","취소","취소","연속"]
[335,"강원","직할","남춘천S/S #2 BUS","남춘천S/S  장기사용 GIS 대체공사","● 2차공정 -  홍천-남춘천T/L GIS -  #2M.Tr 1차 GIS","2025-10-27 09:00","2025-11-07 18:00","취소","취소","연속"]
[336,"강원","직할","홍천남춘천 T/L"," 소양T/L No.76, 77 안전이격 확보공사(협력회사공사)","- No.76, 77  2C 철탑 2기 교체(인클로징) - No.74~79, ASCC/TW 430㎟×S, 3.681C-㎞ 전선교체","2025-10-16 08:00","2025-10-26 18:00","2025-10-16 08:00","2025-10-26 18:00","연속"]
[337,"강원","직할","가평춘천HP T/L"," 상제 등 3개 T/L 추락방지장치 설치공사"," 화천 T/L 수평추락방지장치 설치","2025-10-20 09:00","2025-10-20 18:00","2025-10-20 09:00","2025-10-20 18:00","연속"]
[338,"강원","직할","춘천S/S CB 6100","2025년 강원본부 직할  주변압기 및 OLTC 정밀점검 공사","춘천S/S  #4M.Tr 주변압기 정밀점검(무부하 가압용)","2025-10-24 09:00","2025-10-24 18:00","2025-10-24 09:00","2025-10-24 18:00","연속"]
[339,"강원","직할","춘천S/S CB 6100","2025년 강원본부 직할  주변압기 및 OLTC 정밀점검 공사","춘천S/S  #3M.Tr 주변압기 정밀점검(무부하 가압용)","2025-10-17 09:00","2025-10-17 18:00","2025-10-17 09:00","2025-10-17 18:00","연속"]
[340,"강원","직할","남춘천춘천열병합#2 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  STATION AUX Tr GIS 정밀점검 후 무부하 가압용","2025-10-29 09:00","2025-10-29 12:00","2025-10-29 09:00","2025-10-29 12:00","연속"]
[341,"강원","직할","춘천열병합 CB 6183","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  STATION AUX Tr GIS 정밀점검","2025-10-27 09:00","2025-10-29 18:00","2025-10-27 09:00","2025-10-29 18:00","연속"]
[342,"강원","직할","춘천열병합 #2 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  STATION AUX Tr GIS 정밀점검 후 무부하 가압용","2025-10-29 09:00","2025-10-29 12:00","2025-10-29 09:00","2025-10-29 12:00","연속"]
[343,"강원","직할","남춘천춘천열병합#1 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  남춘천-춘천열병합 #1T/L GIS 정밀점검","2025-10-29 13:00","2025-10-31 18:00","2025-10-29 13:00","2025-10-31 18:00","연속"]
[344,"강원","직할","춘천열병합 #1 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  서홍천-춘천열병합 T/L GIS 정밀점검 후 무부하 가압용","2025-10-31 14:00","2025-10-31 18:00","2025-10-31 14:00","2025-10-31 18:00","연속"]
[345,"강원","직할","화천H/P #1 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 화천H/P  #1M.Tr 2차 GCB 정밀점검 후 무부하 가압용","2025-10-17 10:00","2025-10-17 18:00","2025-10-17 10:00","2025-10-17 18:00","연속"]
[346,"강원","직할","북춘천화천HP T/L"," 상제 등 3개 T/L 추락방지장치 설치공사"," 화천 T/L 추락방지장치 설치","2025-10-13 09:00","2025-10-16 18:00","2025-10-13 09:00","2025-10-16 18:00","연속"]
[347,"강원","직할","화천H/P #2 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 화천H/P  #2M.Tr 2차 GCB 정밀점검 후 무부하 가압용","2025-10-23 10:00","2025-10-23 18:00","2025-10-23 10:00","2025-10-23 18:00","연속"]
[348,"강원","직할","화천화천HP#1 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 화천H/P  #1M.Tr 2차 GCB 정밀점검 후 무부하 가압용","2025-10-23 10:00","2025-10-23 18:00","2025-10-23 10:00","2025-10-23 18:00","연속"]
[349,"강원","직할","가평화천HP T/L"," 상제 등 3개 T/L 추락방지장치 설치공사"," 화천 T/L 수평추락방지장치 설치","2025-10-21 09:00","2025-10-21 18:00","2025-10-21 09:00","2025-10-21 18:00","연속"]
[350,"강원","직할","화천화천HP#2 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 화천H/P  #2M.Tr 2차 GCB 정밀점검 후 무부하 가압용","2025-10-17 10:00","2025-10-17 18:00","2025-10-17 10:00","2025-10-17 18:00","연속"]
[351,"강원","직할","화천H/P #2 M.Tr CB","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 화천H/P  #2M.Tr 2차 GCB 정밀점검","2025-10-20 10:00","2025-10-23 18:00","2025-10-20 10:00","2025-10-23 18:00","연속"]
[352,"강원","직할","화천H/P #1 M.Tr CB","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 화천H/P  #1M.Tr 2차 GCB 정밀점검","2025-10-14 10:00","2025-10-17 18:00","2025-10-14 10:00","2025-10-17 18:00","연속"]
[353,"강원","직할","화천화천HP#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 화천S/S  화천-화천HP#1 T/L GIS 보통점검","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[354,"강원","직할","화천화천HP#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 화천S/S  화천-화천HP#2 T/L GIS 보통점검","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[355,"강원","태백","고한영월에코윈드 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 고한-영월에코윈드T/L 빙설해 고장 이력개소 신전선 시범 보강 시행","2025-10-28 08:00","2025-10-31 18:00","2025-10-28 08:00","2025-10-31 18:00","연속"]
[356,"강원","태백","영월에코윈드S/S  #65 BUS"," 영월에코윈드S/Y 제작사 점검"," 영월에코윈드S/Y PT FAIL 경보 관련 점검 및 BUS PT FUSE 교체","2025-10-01 14:00","2025-10-01 18:00","2025-10-01 14:00","2025-10-01 18:00","연속"]
[357,"강원","태백","영월에코윈드S/S  #66 BUS"," 영월에코윈드S/Y 제작사 점검"," 영월에코윈드S/Y PT FAIL 경보 관련 점검 및 BUS PT FUSE 교체","2025-10-01 14:00","2025-10-01 18:00","2025-10-01 14:00","2025-10-01 18:00","연속"]
[358,"강원","태백","영월에코윈드S/S  #61 BUS"," 영월에코윈드S/Y 제작사 점검"," 영월에코윈드S/Y PT FAIL 경보 관련 점검 및 BUS PT FUSE 교체","2025-10-01 09:00","2025-10-01 14:00","2025-10-01 09:00","2025-10-01 14:00","연속"]
[359,"강원","태백","영월에코윈드S/S  #60 BUS"," 영월에코윈드S/Y 제작사 점검"," 영월에코윈드S/Y PT FAIL 경보 관련 점검 및 BUS PT FUSE 교체","2025-10-01 09:00","2025-10-01 14:00","2025-10-01 09:00","2025-10-01 14:00","연속"]
[360,"강원","태백","태백영월에코윈드 T/L","2025년 태백전력지사  GIS 정밀점검공사","태백영월에코윈드 T/L GIS 정밀점검","2025-10-14 08:00","2025-10-15 18:00","2025-10-14 08:00","2025-10-15 18:00","연속"]
[361,"강원","태백","태백고한 T/L","24~25년 태백전력지사 송전 협력회사 공사"," 태백-영월에코윈드T/L No.6 피뢰기 미설치 개소 조치 (25. 10. 14 ~ 15 태백-영월에코윈드T/L GIS 정밀점검 휴전 신청에 따라 양회선 동시휴전을 통한 피뢰기 미설치개소 조치)","2025-10-14 09:00","2025-10-14 18:00","2025-10-14 09:00","2025-10-14 18:00","연속"]
[362,"충북","직할","서운광혜원 T/L","24~25 충북직할 가공송전 협력회사 총액공사"," 진천-광혜원T/L 병가 전선교체공사","2025-10-13 07:00","2025-10-19 18:00","2025-10-13 07:00","2025-10-19 18:00","연속"]
[363,"충북","직할","광혜원대소#2 T/L","광혜원S/S 23kV 장기사용 GIS 교체공사(병행)","제어/감시/경보 제어케이블 RTU → LID 이설 및 보호반 엔지니어링","2025-10-22 10:00","2025-10-23 18:00","2025-10-22 10:00","2025-10-23 18:00","연속"]
[364,"충북","직할","광혜원대소#1 T/L","광혜원S/S 23kV 장기사용 GIS 교체공사(병행)","제어/감시/경보 제어케이블 RTU → LID 이설 및 보호반 엔지니어링","2025-10-27 10:00","2025-10-28 18:00","2025-10-27 10:00","2025-10-28 18:00","연속"]
[365,"충북","직할","진천덕산#2 T/L","25년 충북직할  GIS 정밀점검공사","덕산변전소  진천-덕산#2T/L GIS 정밀점검","2025-10-01 08:00","2025-10-02 18:00","취소","취소","연속"]
[366,"충북","직할","신진천문백#2 T/L"," 신진천-문백T/L 문백C/T EBA PD집합반 설치공사"," 신진천-문백T/L 문백C/T EBA PD집합반 설치공사","2025-10-29 13:00","2025-10-29 18:00","2025-10-29 13:00","2025-10-29 18:00","연속"]
[367,"충북","직할","신진천문백#1 T/L"," 신진천-문백T/L 문백C/T EBA PD집합반 설치공사"," 신진천-문백T/L 문백C/T EBA PD집합반 설치공사","2025-10-29 08:00","2025-10-29 13:00","2025-10-29 08:00","2025-10-29 13:00","연속"]
[368,"충북","직할","신진천S/S CB 6300","24~25 직할 변전협력회사공사(장기미동작)","신진천S/S  #62-#67 BUS TIE GIS 장기미동작 차단기 조작시험","2025-10-16 14:00","2025-10-16 18:00","2025-10-16 14:00","2025-10-16 18:00","연속"]
[369,"충북","직할","신진천S/S CB 6100","24~25 직할 변전협력회사공사(장기미동작)","신진천S/S  #60-#65 BUS TIE GIS 장기미동작 차단기 조작시험","2025-10-16 10:00","2025-10-16 14:00","2025-10-16 10:00","2025-10-16 14:00","연속"]
[370,"충북","직할","신진천진천#1 T/L","24~25 직할 변전협력회사공사(장기미동작)","신진천진천#1 T/L 장기미동작 차단기 조작시험","2025-10-18 10:00","2025-10-18 14:00","2025-10-18 10:00","2025-10-18 14:00","연속"]
[371,"충북","직할","신진천S/S SEC CB 60610","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #60-61 BUS SEC GIS 보통점검 및 전자변 교체","2025-10-20 10:00","2025-10-20 18:00","2025-10-20 10:00","2025-10-20 18:00","연속"]
[372,"충북","직할","신진천S/S SEC CB 61620","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #61-62 BUS SEC GIS 보통점검 및 전자변 교체","2025-10-21 10:00","2025-10-21 18:00","2025-10-21 10:00","2025-10-21 18:00","연속"]
[373,"충북","직할","신진천S/S SEC CB 65660","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #65-66 BUS SEC GIS 보통점검 및 전자변 교체","2025-10-22 10:00","2025-10-22 18:00","2025-10-22 10:00","2025-10-22 18:00","연속"]
[374,"충북","직할","신진천S/S SEC CB 66670","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #66-67 BUS SEC GIS 보통점검 및 전자변 교체","2025-10-23 10:00","2025-10-23 18:00","2025-10-23 10:00","2025-10-23 18:00","연속"]
[375,"충북","직할","신진천S/S CB 6200","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #61-66 BUS TIE GIS 전자변 교체","2025-10-24 10:00","2025-10-24 16:00","2025-10-24 10:00","2025-10-24 16:00","연속"]
[376,"충북","직할","진천광혜원#1 T/L","24~25 충북직할 가공송전 협력회사 총액공사"," 서운-광혜원T/L 병가 전선교체공사","2025-10-13 07:00","2025-10-19 18:00","2025-10-13 07:00","2025-10-19 18:00","연속"]
[377,"충북","청주","오창국사#2 T/L","'24-'25년 청주전력지사 송전정비 협력회사 총액공사","수직, 수평 추락방지장치 설치(No.1~4)","2025-10-29 08:00","2025-10-30 18:00","2025-10-29 08:00","2025-10-30 18:00","연속"]
[378,"충북","청주","오창국사#1 T/L","'24-'25년 청주전력지사 송전정비 협력회사 총액공사","수직, 수평 추락방지장치 설치(No.1~4)","2025-10-27 08:00","2025-10-28 18:00","2025-10-27 08:00","2025-10-28 18:00","연속"]
[379,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(10월)","2025-10-05 07:00","2025-10-06 14:00","취소","취소","연속"]
[380,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_10월)","2025-10-05 07:00","2025-10-06 14:00","취소","취소","연속"]
[381,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_10월)","2025-10-29 14:00","2025-10-30 18:00","취소","취소","연속"]
[382,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(10월)","2025-10-11 14:00","2025-10-16 18:00","취소","취소","연속"]
[383,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_10월)","2025-10-15 14:00","2025-10-16 18:00","취소","취소","연속"]
[384,"충북","청주","남청주S/S SEC CB 62610","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(10월)","2025-10-19 07:00","2025-10-30 18:00","취소","취소","연속"]
[385,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(10월)","2025-10-19 07:00","2025-10-20 14:00","취소","취소","연속"]
[386,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_10월)","2025-10-19 14:00","2025-10-20 14:00","취소","취소","연속"]
[387,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(안전이격확보/무부하가압용_10월)","2025-10-20 14:00","2025-10-25 14:00","취소","취소","연속"]
[388,"충북","청주","남청주S/S #62 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(10월)","2025-10-20 14:00","2025-10-25 14:00","취소","취소","연속"]
[389,"충북","청주","남청주S/S SEC CB 67660","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(10월)","2025-10-05 07:00","2025-10-16 18:00","취소","취소","연속"]
[390,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(10월)","2025-10-25 14:00","2025-10-30 18:00","취소","취소","연속"]
[391,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_10월)","2025-10-10 14:00","2025-10-11 14:00","취소","취소","연속"]
[392,"충북","청주","남청주S/S #67 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(10월)","2025-10-06 14:00","2025-10-11 14:00","취소","취소","연속"]
[393,"충북","청주","북청주봉명#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-10-28 10:00","2025-10-28 18:00","2025-10-28 10:00","2025-10-28 18:00","연속"]
[394,"충북","청주","북청주봉명#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-10-29 10:00","2025-10-29 18:00","2025-10-29 10:00","2025-10-29 18:00","연속"]
[395,"충북","청주","서청주사직#1 T/L","대한전선제 열경화공법 EBG 보강공사","서청주S/S, 사직S/S  서청주-사직 #1T/L EBG 보강공사","2025-10-27 09:00","2025-10-29 12:00","2025-10-27 09:00","2025-10-29 12:00","연속"]
[396,"충북","청주","옥천영동 T/L","2024~2025년 송전정비 협력회사 총액공사"," 옥천-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 옥천-영동T/L 수평 추락방지장치 설치 2. 구간 :  영동분기T/L 1~61호","2025-10-27 08:00","2025-11-07 18:00","취소","취소","연속"]
[397,"충북","청주","화동영동 T/L","2024~2025년 송전정비 협력회사 총액공사"," 화동-영동T/L 추락방지장치 설치(수평설치) 1. 내용 : 화동-영동T/L 수평 추락방지장치 설치 2. 구간 :  화동-영동T/L 60~110호  영동분기T/L 1~61호","2025-10-13 08:00","2025-10-24 18:00","취소","취소","연속"]
[398,"충북","청주","오송북청주#1 T/L"," 신청주-문백T/L 건설공사"," 오송-국사 #1T/L 본선로 구성","2025-10-13 07:00","2025-10-18 18:00","2025-10-13 07:00","2025-10-18 18:00","연속"]
[399,"충북","청주","옥천보은 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," 송전선로 보호반 교체 LA, CVT 교체","2025-10-13 10:00","2025-10-15 18:00","취소","취소","연속"]
[400,"충북","청주","죽림S/S CB 6100","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-10-22 09:00","2025-10-23 18:00","2025-10-22 09:00","2025-10-23 18:00","연속"]
[401,"충북","청주","죽림S/S #1 BUS","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-10-22 09:00","2025-10-23 18:00","2025-10-22 09:00","2025-10-23 18:00","연속"]
[402,"충북","청주","죽림서청주#1 T/L","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검 무부하가압용","2025-10-23 15:00","2025-10-23 18:00","2025-10-23 15:00","2025-10-23 18:00","연속"]
[403,"충북","충주","감곡가남#1 T/L"," 감곡-가남T/L 용량증대 전선교체공사","#1T/L No.4~8 선종교체 (ASCR 240 → ASCC/TW 290)","2025-10-12 07:00","2025-10-14 18:00","2025-10-12 07:00","2025-10-14 18:00","연속"]
[404,"충북","충주","감곡가남#2 T/L"," 감곡-가남T/L 용량증대 전선교체공사","철탑 안전이격확보 1기(5호), #1,2 동시휴전","2025-10-03 08:00","2025-10-05 18:00","2025-10-03 08:00","2025-10-05 18:00","연속"]
[405,"충북","충주","감곡가남#1 T/L"," 감곡-가남T/L 용량증대 전선교체공사","철탑 안전이격확보 1기(5호), #1,2 동시휴전","2025-10-03 08:00","2025-10-05 18:00","2025-10-03 08:00","2025-10-05 18:00","연속"]
[406,"충북","충주","금왕남음성#2 T/L"," 성본S/S 최초가압"," 성본S/S 최조 무부하 가압 및 앵글측정","2025-10-20 10:00","2025-10-24 10:00","2025-10-20 10:00","2025-10-24 10:00","연속"]
[407,"충북","충주","금왕남음성#1 T/L","24~25 충북직할 가공송전 협력회사 총액공사"," 음성-금왕#2T/L 병가구간 수평추락방지장치 설치","2025-10-20 07:00","2025-10-23 18:00","2025-10-20 07:00","2025-10-23 18:00","연속"]
[408,"충북","충주","금왕S/S #1 BUS"," 성본S/S 최초가압"," 성본S/S 최초 무부하가압 및 앵글측정","2025-10-20 10:00","2025-10-21 10:00","2025-10-20 10:00","2025-10-21 10:00","연속"]
[409,"충북","충주","금왕S/S #2 BUS"," 성본S/S 최초가압"," 성본S/S 최초 무부하가압 및 앵글측정","2025-10-21 10:00","2025-10-22 10:00","2025-10-21 10:00","2025-10-22 10:00","연속"]
[410,"충북","충주","남음성덕산#2 T/L","2025 가공송전선로 순시점검 위탁공사"," 남음성-덕산T/L 정밀점검","2025-10-17 07:00","2025-10-19 18:00","2025-10-17 07:00","2025-10-19 18:00","연속"]
[411,"충북","충주","남음성덕산#1 T/L","2025 가공송전선로 순시점검 위탁공사"," 남음성-덕산T/L 정밀점검","2025-10-09 07:00","2025-10-11 18:00","2025-10-09 07:00","2025-10-11 18:00","연속"]
[412,"충북","충주","단양S/S #66 BUS","단양S/S STATCOM 설치공사용 개폐장치 설치공사(전문)","○ 170kV GIS 중간BAY x 1CCT 설치 ○ 기타 부대공사 x 1식 설치","2025-10-20 09:00","2025-10-22 09:00","2025-10-20 09:00","2025-10-22 09:00","연속"]
[413,"충북","충주","단양영월CC#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","수평추락방지장치설치( 단양-영월#2 T/L No.1~9,제천영월#2 병가)","2025-10-15 07:00","2025-10-17 18:00","2025-10-15 07:00","2025-10-17 18:00","연속"]
[414,"충북","충주","문경단양 T/L","단양S/S STATCOM 설치공사용 개폐장치 설치공사(전문)","○ 170kV GIS 중간BAY x 1CCT 설치 관련 #61 BUS 무부하 가압 시 설비의 건전성 확보","2025-10-23 13:00","2025-10-24 10:00","2025-10-23 13:00","2025-10-24 10:00","연속"]
[415,"충북","충주","문경단양 T/L","단양S/S STATCOM 설치공사용 개폐장치 설치공사(전문)","○ 170kV GIS 중간BAY x 1CCT 설치 시 작업 안전거리 확보 ○ #66 BUS 무부하 가압 시 설비의 건전성 확보","2025-10-20 09:00","2025-10-22 09:00","2025-10-20 09:00","2025-10-22 09:00","연속"]
[416,"충북","충주","단양S/S #61 BUS","단양S/S STATCOM 설치공사용 개폐장치 설치공사(전문)","○ 170kV GIS 중간BAY x 1CCT 설치 ○ 기타 부대공사 x 1식 설치","2025-10-22 09:00","2025-10-24 10:00","2025-10-22 09:00","2025-10-24 10:00","연속"]
[417,"충북","충주","대소S/S #66 BUS"," 성본S/S 최초가압"," 성본S/S 최초 무부하가압 및 앵글측정","2025-10-22 10:00","2025-10-23 10:00","2025-10-22 10:00","2025-10-23 10:00","연속"]
[418,"충북","충주","대소S/S #61 BUS"," 성본S/S 최초가압"," 성본S/S 최초 무부하가압 및 앵글측정","2025-10-21 10:00","2025-10-22 10:00","2025-10-21 10:00","2025-10-22 10:00","연속"]
[419,"충북","충주","신제천남원주#2 T/L","'24-25년 충주전력지사 변전정비 총액공사","신제천S/S 154k신제천남원주#2 T/L LA 보통점검","2025-10-10 09:00","2025-10-10 18:00","2025-10-10 09:00","2025-10-10 18:00","연속"]
[420,"충북","충주","신제천남원주#1 T/L","'24-25년 충주전력지사 변전정비 총액공사","신제천남원주#1 T/L LA 보통점검","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[421,"충북","충주","신충주감곡#2 T/L","24~25 충북직할 가공송전 협력회사 총액공사","수평암측 사재불량개소 정비","2025-10-28 07:00","2025-10-28 18:00","2025-10-28 07:00","2025-10-28 18:00","연속"]
[422,"충북","충주","신충주감곡#1 T/L","24~25 충북직할 가공송전 협력회사 총액공사","절연저항값 불량애자교체","2025-10-27 07:00","2025-10-27 18:00","2025-10-27 07:00","2025-10-27 18:00","연속"]
[423,"충북","충주","왕암북충주 T/L","왕암S/S STATCOM 설치공사용 개폐장치 설치공사(전문)","○ #2 BUS 무부하 가압 시 설비의 건전성 확보","2025-10-21 13:00","2025-10-22 09:00","2025-10-21 13:00","2025-10-22 09:00","연속"]
[424,"충북","충주","왕암S/S #1 BUS","왕암S/S STATCOM용 개폐장치 설치공사(전문)","○ 170kV GIS x 1CCT 설치 ○ 기타 부대공사 x 1식 설치","2025-10-22 09:00","2025-10-24 10:00","2025-10-22 09:00","2025-10-24 10:00","연속"]
[425,"충북","충주","왕암북충주 T/L","왕암S/S STATCOM 설치공사용 개폐장치 설치공사(전문)","○ #1 BUS 무부하 가압 시 설비의 건전성 확보","2025-10-23 13:00","2025-10-24 10:00","2025-10-23 13:00","2025-10-24 10:00","연속"]
[426,"충북","충주","왕암S/S #2 BUS","왕암S/S STATCOM용 개폐장치 설치공사(전문)","○ 170kV GIS x 1CCT 설치 ○ 기타 부대공사 x 1식 설치","2025-10-20 09:00","2025-10-22 09:00","2025-10-20 09:00","2025-10-22 09:00","연속"]
[427,"충북","충주","음성금왕#2 T/L","24~25 충북직할 가공송전 협력회사 총액공사"," 금왕-남음성#1T/L 병가구간 수평추락방지장치 설치","2025-10-20 07:00","2025-10-23 18:00","2025-10-20 07:00","2025-10-23 18:00","연속"]
[428,"충북","충주","제천영월#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","피뢰기 설치( 제천-영월#2 T/L No.4~71)","2025-10-13 07:00","2025-10-21 18:00","2025-10-13 07:00","2025-10-21 18:00","연속"]
[429,"충북","충주","충주S/S #60 BUS","충주S/S  #60-65 PT 집합반 대체","충주S/S  #60-65 PT 집합반 대체","2025-10-27 09:00","2025-10-28 18:00","2025-10-27 09:00","2025-10-28 18:00","연속"]
[430,"충북","충주","충주S/S #65 BUS","충주S/S  #60-65 PT 집합반 대체","충주S/S  #60-65 PT 집합반 대체","2025-10-29 09:00","2025-10-30 18:00","2025-10-29 09:00","2025-10-30 18:00","연속"]
[431,"충북","충주","충주S/S SEC CB 65660","25년 충주전력지사 362,170kV GIS 보통점검공사","충주S/S  65-66-0 BUS-SEC GIS 보통점검","2025-10-22 14:00","2025-10-22 18:00","2025-10-22 14:00","2025-10-22 18:00","연속"]
[432,"충북","충주","충주풍동 T/L","충주S/S  충주풍동 T/L LA 보통점검","충주S/S  충주풍동 T/L LA 보통점검","2025-10-24 09:00","2025-10-24 18:00","2025-10-24 09:00","2025-10-24 18:00","연속"]
[433,"충북","충주","충주S/S CB 6200","25년 충주전력지사 362,170kV GIS 보통점검공사","충주S/S  61-66 B/T GIS 보통점검","2025-10-23 10:00","2025-10-23 14:00","2025-10-23 10:00","2025-10-23 14:00","연속"]
[434,"충북","충주","왕암충주 T/L","25년 충주전력지사 362,170kV GIS 보통점검공사","충주S/S  왕암-충주 T/L GIS 보통점검","2025-10-22 10:00","2025-10-22 14:00","2025-10-22 10:00","2025-10-22 14:00","연속"]
[435,"충북","충주","풍동음성#2 T/L"," 풍동S/S 외벽 리모델링 공사","공사 목적 : 화재에 취약한 외벽 드라이비트 마감재를 교체하여 화재 확산 방지 및 설비피해를 예방하고자 함. - 시스템비계 설치 및 해체 : 2,815m2 - 외벽드라이비트 마감재 철거 : 1,808m2 - 신설 마감재 설치 : 1,808m2","2025-10-13 09:00","2025-11-02 18:00","2025-10-13 09:00","2025-11-02 18:00","연속"]
[436,"충북","충주","풍동음성#1 T/L"," 풍동S/S 외벽 리모델링 공사","공사 목적 : 화재에 취약한 외벽 드라이비트 마감재를 교체하여 화재 확산 방지 및 설비피해를 예방하고자 함. - 시스템비계 설치 및 해체 : 2,815m2 - 외벽드라이비트 마감재 철거 : 1,808m2 - 신설 마감재 설치 : 1,808m2","2025-10-13 09:00","2025-11-02 18:00","2025-10-13 09:00","2025-11-02 18:00","연속"]
[437,"대전세종충남","대전","가수원대전서남부 T/L","[즉시가압X]가수원S/S  LH열병합T/L GIS 보통점검","[즉시가압X]가수원S/S  LH열병합T/L GIS 보통점검 및 전자변교체","2025-10-15 09:00","2025-10-15 18:00","취소","취소","연속"]
[438,"대전세종충남","대전","추부금산#1 T/L","[가압O]금산S/S  추부-금산#1T/L GIS 보통점검","[가압O]금산S/S  추부-금산#1T/L GIS 보통점검","2025-10-22 18:00","2025-10-23 00:00","2025-10-22 18:00","2025-10-23 00:00","연속"]
[439,"대전세종충남","대전","추부금산#2 T/L","[즉시가압O]금산S/S  추부-금산#2T/L GIS 보통점검","[즉시가압O]금산S/S  추부-금산#2T/L GIS 보통점검","2025-10-23 18:00","2025-10-24 00:00","2025-10-23 18:00","2025-10-24 00:00","연속"]
[440,"대전세종충남","대전","남대전신흥#2 T/L","[취소시][가압X]남대전S/S 남대전-신흥#2T/L 하자점검","[취소시][가압X]남대전S/S 남대전-신흥#2T/L 하자점검","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[441,"대전세종충남","대전","남대전신흥#1 T/L","[취소시][가압X]남대전S/S 남대전-신흥#1T/L GIS 하자점검","[취소시][가압X]남대전S/S 남대전-신흥#1T/L GIS 하자점검","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[442,"대전세종충남","대전","신옥천남대전#1 T/L","(9월취소시) 신옥천-남대전T/L 지장수목전지 및 벌채"," 신옥천-남대전T/L 지장수목전지 및 벌채","2025-10-29 09:00","2025-10-29 18:00","2025-10-29 09:00","2025-10-29 18:00","연속"]
[443,"대전세종충남","대전","신옥천남대전#2 T/L","(9월취소시) 신옥천-남대전T/L 지장수목전지 및 벌채"," 신옥천-남대전T/L 지장수목전지 및 벌채","2025-10-30 09:00","2025-10-30 18:00","2025-10-30 09:00","2025-10-30 18:00","연속"]
[444,"대전세종충남","대전","부여논산#1 T/L","[송전][즉시가압O] 논산-은진등2개T/L폴리머애자 설치공사","[송전][즉시가압O] 논산-은진 등 2개T/L 폴리머지지애자 설치공사","2025-10-27 07:00","2025-10-29 18:00","취소","취소","연속"]
[445,"대전세종충남","대전","논산은진#2 T/L","[송전][즉시가압O] 논산-은진등2개T/L폴리머애자 설치공사","[송전][즉시가압O] 논산-은진 등 2개T/L 폴리머애자 설치공사","2025-10-29 07:00","2025-10-31 18:00","취소","취소","연속"]
[446,"대전세종충남","대전","팔봉두마#1 T/L","[즉시가압X]두마S/S  팔봉-두마#1T/L 전자변교체","[즉시가압X]두마S/S  팔봉-두마#1T/L 전자변교체","2025-10-28 09:00","2025-10-28 18:00","취소","취소","연속"]
[447,"대전세종충남","대전","신계룡두마#1 T/L","[즉시가압X]두마S/S  신계룡-두마#1T/L GIS 보통점검","[즉시가압X]두마S/S  신계룡-두마#1T/L GIS 보통점검 - 두마S/S  신계룡-두마#1T/L GIS 전자변교체 - 신계룡S/S  신계룡-두마#1T/L GIS 보통점검","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[448,"대전세종충남","대전","신계룡두마#2 T/L","[즉시가압X]두마S/S  신계룡-두마#2T/L GIS 보통점검","[즉시가압X]두마S/S  신계룡-두마#2T/L GIS 보통점검 -두마S/S  신계룡-두마#1T/L GIS 전자변교체","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[449,"대전세종충남","대전","팔봉두마#2 T/L","[즉시가압X]두마S/S  팔봉-두마#2T/L 전자변교체","[즉시가압X]두마S/S  팔봉-두마#2T/L 전자변교체","2025-10-29 09:00","2025-10-29 18:00","취소","취소","연속"]
[450,"대전세종충남","대전","신계룡은진#2 T/L","[즉시가압O]신계룡S/S  신계룡-은진#2T/L GIS 보통점검","[즉시가압O]신계룡S/S  신계룡-은진#2T/L GIS 보통점검","2025-10-24 09:00","2025-10-24 18:00","취소","취소","연속"]
[451,"대전세종충남","대전","신계룡은진#1 T/L","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","2025-10-13 07:00","2025-10-17 11:00","취소","취소","연속"]
[452,"대전세종충남","대전","신흥동대전#2 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-10-20 09:00","2025-10-22 12:00","취소","취소","연속"]
[453,"대전세종충남","대전","신흥동대전#1 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-10-15 12:00","2025-10-17 18:00","취소","취소","연속"]
[454,"대전세종충남","대전","남대전신흥#3 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [대전전력 변전]","2025-10-13 09:00","2025-10-15 12:00","2025-10-13 09:00","2025-10-15 12:00","연속"]
[455,"대전세종충남","대전","신흥동대전#3 T/L","[송전]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-10-22 12:00","2025-10-24 18:00","취소","취소","연속"]
[456,"대전세종충남","대전","신옥천용운#1 T/L","(취소시)(가압O)용운S/S 신옥천-용운#1T/L ES 락핀 점검","(취소시)(가압O)용운S/S 신옥천-용운#1T/L ES 락핀 점검","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[457,"대전세종충남","대전","신계룡은진#1 T/L","[즉시가압O]신계룡S/S  신계룡-은진#1T/L GIS 보통점검","[즉시가압O]신계룡S/S  신계룡-은진#1T/L GIS 보통점검","2025-10-13 09:00","2025-10-13 18:00","취소","취소","연속"]
[458,"대전세종충남","서산","신당진당진#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(9월취소시) (즉시가압가능) 신당진S/S 신당진당진#2T/L GIS 보통점검","2025-10-23 09:30","2025-10-23 18:00","2025-10-23 09:30","2025-10-23 18:00","연속"]
[459,"대전세종충남","서산","석문당진화력#2 T/L"," 대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [서산송전] 철탑 정밀점검 (김성현대리)","2025-10-30 12:00","2025-11-01 18:00","취소","취소","연속"]
[460,"대전세종충남","서산","석문당진화력#1 T/L"," 대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치 [서산송전] 철탑 정밀점검 (김성현대리)","2025-10-28 08:00","2025-10-30 12:00","취소","취소","연속"]
[461,"대전세종충남","서산","대산석문#1 T/L","24-25년 서산P/O 변전협력회사 총액공사","(9월휴전취소시) (즉시가압가능) 대산S/S 대산석문#1T/L GIS, LA 보통점검","2025-10-11 09:30","2025-10-11 18:00","취소","취소","연속"]
[462,"대전세종충남","서산","서산대산#4 T/L"," 대산개폐소 건설공사","- 계통변경(서산대산#4T/L-&gt대산개폐소대산#2T/L, 서산대산개폐소#2T/L) - 대산,서산S/S 송전선로 보호반 대체 - 기타 부대공사 1식","2025-10-20 10:00","2025-10-24 18:00","2025-10-20 10:00","2025-10-24 18:00","연속"]
[463,"대전세종충남","서산","대산석문#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(9월휴전취소시) (즉시가압가능) 대산S/S 대산석문#2T/L GIS, LA 보통점검","2025-10-12 09:30","2025-10-12 18:00","취소","취소","연속"]
[464,"대전세종충남","서산","서산성연 T/L"," 신성연-태안T/L 계통변경 외 1개 T/L 건설공사"," 대산T/L 임시선로(No.14-1) 구성","2025-10-29 07:00","2025-10-31 18:00","2025-10-29 07:00","2025-10-31 18:00","연속"]
[465,"대전세종충남","서산","서산태안#2 T/L"," 신성연-태안T/L 계통변경 외 1개 T/L 건설공사"," 대산 T/L 임시선로(No.14-1) 구성 시 작업공간 간섭에 따른 이격거리 확보","2025-10-29 07:00","2025-10-31 18:00","2025-10-29 07:00","2025-10-31 18:00","연속"]
[466,"대전세종충남","서산","서산태안#2 T/L","25년 서산P/O  이하 GIS 정밀점검공사","(9월휴전취소시) (즉시가압가능) 서산, 태안S/S 서산태안#2T/L GIS, LA 보통점검","2025-10-18 09:30","2025-10-19 18:00","2025-10-18 09:30","2025-10-19 18:00","연속"]
[467,"대전세종충남","서산","신당진서산#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 서산S/S 신당진서산#2T/L CVT 초기점검","2025-10-07 09:30","2025-10-07 18:00","취소","취소","연속"]
[468,"대전세종충남","서산","신당진서산#1 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 서산S/S 신당진서산#1T/L GIS 보통점검","2025-10-06 09:30","2025-10-06 18:00","취소","취소","연속"]
[469,"대전세종충남","서산","서산대산#3 T/L"," 대산개폐소 건설공사","- 계통변경(서산대산#3T/L-&gt대산개폐소대산#1T/L, 서산대산개폐소#1T/L) - 대산,서산S/S 송전선로 보호반 대체 - 기타 부대공사 1식","2025-10-13 10:00","2025-10-17 18:00","2025-10-13 10:00","2025-10-17 18:00","연속"]
[470,"대전세종충남","서산","신당진당진#1 T/L","24-25년 서산P/O 변전협력회사 총액공사","(9월취소시) (즉시가압가능) 신당진S/S 신당진당진#1T/L CVT 대체","2025-10-22 09:30","2025-10-22 18:00","2025-10-22 09:30","2025-10-22 18:00","연속"]
[471,"대전세종충남","서산","태안태안화력#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(9월휴전취소시) (즉시가압가능) 태안S/S 태안태안화력#2T/L 차단기 리미트스위치 불량보수","2025-10-01 09:30","2025-10-01 18:00","2025-10-01 09:30","2025-10-01 18:00","연속"]
[472,"대전세종충남","서산","태안태안화력#1 T/L","24-25년 서산P/O 변전협력회사 총액공사","(9월 휴전 취소시) (즉시가압가능) 태안T/P 태안태안화력#1T/L LA 보통점검","2025-10-21 09:30","2025-10-21 18:00","2025-10-21 09:30","2025-10-21 18:00","연속"]
[473,"대전세종충남","세종","신풍공주#1 T/L","[즉시가압O][주말X]  신풍-공주T/L 점퍼지지애자 설치"," 신풍-공주T/L 폴리머 점퍼지지애자 설치 - 철탑 수평각도 중각도 개소에 대한 폴리머 점퍼지지애자 설치를 통해 횡진 고장 예방","2025-10-09 07:00","2025-10-17 18:00","2025-10-09 07:00","2025-10-17 18:00","연속"]
[474,"대전세종충남","세종","신풍공주#2 T/L","[즉시가압O] 신풍-공주T/L 점퍼지지애자 설치"," 신풍-공주T/L 폴리머 점퍼지지애자 설치 - 철탑 수평각도 중각도 개소에 대한 폴리머 점퍼지지애자 설치를 통해 횡진 고장 예방","2025-10-20 07:00","2025-10-24 18:00","2025-10-20 07:00","2025-10-24 18:00","연속"]
[475,"대전세종충남","세종","덕진대화#2 T/L","[변전]25년 세종전력지사 변전협력회사 공사","[즉시가압○] GIS 보통점검","2025-10-24 09:00","2025-10-24 18:00","2025-10-24 09:00","2025-10-24 18:00","연속"]
[476,"대전세종충남","세종","덕진대화#1 T/L","[변전]25년 세종전력지사 변전협력회사 공사","[즉시가압○] GIS 보통점검","2025-10-23 09:00","2025-10-23 18:00","2025-10-23 09:00","2025-10-23 18:00","연속"]
[477,"대전세종충남","세종","덕진공주#1 T/L"," 덕진-공주T/L 지장수목전지 및 벌채"," 덕진-공주T/L 지장수목전지 및 벌채","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[478,"대전세종충남","세종","덕진공주#2 T/L"," 덕진-공주T/L 지장수목전지 및 벌채"," 덕진-공주T/L 지장수목전지 및 벌채","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[479,"대전세종충남","세종","세종둔곡#2 T/L","[즉시가압O]  세종-둔곡T/L 추락방지 설치"," 세종-둔곡T/L 추락방지 설치 - 추락방지 장치 설치를 통한 작업자 안전능률 향상","2025-10-27 07:00","2025-10-31 18:00","2025-10-27 07:00","2025-10-31 18:00","연속"]
[480,"대전세종충남","세종","세종부강#2 T/L","[9월 취소시][즉시가압O]  세종-부강T/L 불량애자 교체"," 세종-부강#2T/L 불량애자 교체 시행 - 사유 : 동일 Lot 내 하자 발생으로 해당 애자 전량 교체 시행","2025-10-02 07:00","2025-10-03 18:00","2025-10-02 07:00","2025-10-03 18:00","연속"]
[481,"대전세종충남","세종","세종부강#1 T/L","[9월 취소시][즉시가압O]  세종-부강T/L 불량애자 교체"," 세종-월산#1T/L 불량애자 교체 시행 - 사유 : 동일 Lot 내 하자 발생으로 해당 애자 전량 교체 시행","2025-10-01 07:00","2025-10-01 18:00","2025-10-01 07:00","2025-10-01 18:00","연속"]
[482,"대전세종충남","세종","부강대청HP T/L","[안전목적][즉시가압O]  세종-부강T/L 불량애자 교체"," 세종-부강T/L 불량애자 교체 중 4회선 병가철탑으로 인한 안전목적상 휴전","2025-10-01 07:00","2025-10-01 18:00","2025-10-01 07:00","2025-10-01 18:00","연속"]
[483,"대전세종충남","세종","부강신탄진 T/L","[9월 취소시][즉시가압O]  부강-신탄진T/L 추락방지 설치"," 부강-신탄진T/L 추락방지 설치 - 추락방지장치 설치를 통한 작업자 안전능률 향상 및 안전의식 고취","2025-10-17 07:00","2025-10-17 18:00","2025-10-17 07:00","2025-10-17 18:00","연속"]
[484,"대전세종충남","세종","세종월산#1 T/L","[9월 취소시][즉시가압O]  세종-월산#1T/L 불량애자 교체"," 세종-월산#1T/L 불량애자 교체 시행 - 사유 : 동일 Lot 내 하자 발생으로 해당 애자 전량 교체 시행","2025-10-20 07:00","2025-10-21 18:00","취소","취소","연속"]
[485,"대전세종충남","세종","세종월산#2 T/L","[9월 취소시][즉시가압O]  세종-월산#2T/L 불량애자 교체"," 세종-월산#1T/L 불량애자 교체 시행 - 사유 : 동일 Lot 내 하자 발생으로 해당 애자 전량 교체 시행","2025-10-22 07:00","2025-10-23 18:00","취소","취소","연속"]
[486,"대전세종충남","세종","서세종조치원 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 서서종-조치원 (찰탑철거 및 설치 : No.20,21,22,23)","2025-09-04 07:00","2025-09-10 18:00","취소","취소","연속"]
[487,"대전세종충남","세종","조치원월산 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 조치원월산 No.20~23호 임시 가선로 구성 (찰탑교체 3기 : No.20,21,23)","2025-10-01 07:00","2025-10-03 18:00","취소","취소","연속"]
[488,"대전세종충남","세종","서세종조치원 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 서서종-조치원 (찰탑철거 및 설치 : No.20,21,22,23)","2025-10-04 07:00","2025-10-10 18:00","취소","취소","연속"]
[489,"대전세종충남","세종","조치원전의#1 T/L","[9월 취소시][즉시가압O]  조치원-전의T/L 추락방지 설치"," 조치원-전의T/L 추락방지 설치공사 - 추락방지 설치공사를 하여 작업자의 안전능률을 향상하고 안전의식 고취","2025-10-15 07:00","2025-10-16 18:00","2025-10-15 07:00","2025-10-16 18:00","연속"]
[490,"대전세종충남","세종","조치원월산 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 조치원-월산 본선로 구성 (가철탑 - 본철탑 : No.20,21,23)","2025-10-11 07:00","2025-10-14 18:00","취소","취소","연속"]
[491,"대전세종충남","세종","조치원월산 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보 - 조치원-월산 본선로 구성 (가철탑-&gt본철탑 : No.20,21,23)","2025-09-11 07:00","2025-09-14 18:00","취소","취소","연속"]
[492,"대전세종충남","직할","신탄진대청HP T/L","24-25년도 직할 변전협력회사 총액공사","○ 신탄진-대청H/P T/L GIS 초기점검","2025-10-24 09:00","2025-10-24 18:00","2025-10-24 09:00","2025-10-24 18:00","연속"]
[493,"대전세종충남","천안","불당서천안#1 T/L","(즉시가압가능)불당S/S 불당-서천안#1T/L CB 개폐타임 측정","불당S/S  불당-서천안#1T/L CB 개폐타임 측정","2025-10-01 09:00","2025-10-01 18:00","취소","취소","연속"]
[494,"대전세종충남","천안","신온양한샘#1 T/L","2025년 가공송전 순시점검 위탁공사"," 신온양-한샘T/L 정밀점검","2025-10-20 08:00","2025-10-22 18:00","취소","취소","연속"]
[495,"대전세종충남","천안","신온양한샘#2 T/L","2025년 가공송전 순시점검 위탁공사"," 신온양-한샘T/L 정밀점검","2025-10-27 08:00","2025-10-29 18:00","취소","취소","연속"]
[496,"대전세종충남","천안","아산온양#1 T/L"," 아산-온양T/L 안전이격확보공사"," 아산-온양T/L No. 40 안전이격확보공사","2025-10-24 07:00","2025-10-28 18:00","취소","취소","연속"]
[497,"대전세종충남","천안","아산온양#2 T/L"," 아산-온양T/L 안전이격확보공사"," 아산-온양T/L No. 40 안전이격확보공사","2025-10-29 07:00","2025-10-31 18:00","취소","취소","연속"]
[498,"대전세종충남","천안","아산온양#1 T/L","온양S/S  아산-온양#1T/L 하자점검","온양S/S  아산-온양#1T/L 하자점검","2025-10-27 09:00","2025-10-27 18:00","취소","취소","연속"]
[499,"대전세종충남","천안","아산온양#2 T/L","온양S/S  아산-온양#2T/L 하자점검","온양S/S  아산-온양#2T/L 하자점검","2025-10-30 09:00","2025-10-30 18:00","취소","취소","연속"]
[500,"대전세종충남","천안","아산인주#2 T/L","(즉시가압불가)인주S/S 아산-인주#2T/L CB 전자변 교체","인주S/S 아산-인주#2T/L CB 전자변 교체 및 개폐타임 측정","2025-10-23 09:00","2025-10-23 18:00","취소","취소","연속"]
[501,"대전세종충남","천안","신탕정탕정#1 T/L","(즉시가압가능)탕정S/S 신탕정-탕정#1T/L CB 개폐타임 측정","탕정S/S  신탕정-탕정#1T/L CB 개폐타임 측정","2025-10-15 09:00","2025-10-15 18:00","2025-10-15 09:00","2025-10-15 18:00","연속"]
[502,"대전세종충남","천안","신탕정탕정#2 T/L","(즉시가압가능)탕정S/S 신탕정-탕정#2T/L CB 개폐타임 측정","탕정S/S  신탕정-탕정#2T/L CB 개폐타임 측정","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[503,"대전세종충남","청양","옥산장항#1 T/L","[송전][주말작업X]  옥산-장항#1T/L 정밀점검공사"," 옥산-장항#1T/L 정밀점검공사","2025-10-13 08:00","2025-10-17 18:00","2025-10-13 08:00","2025-10-17 18:00","연속"]
[504,"대전세종충남","청양","신서천옥산#1 T/L","[송전][주말작업X]  옥산-장항#2T/L 정밀점검[안전이격]"," 옥산-장항#2T/L 정밀점검공사 [안전이격]","2025-10-20 08:00","2025-10-20 18:00","2025-10-20 08:00","2025-10-20 18:00","연속"]
[505,"대전세종충남","청양","옥산장항#2 T/L","[송전][주말작업X]  옥산-장항#2T/L 정밀점검공사"," 옥산-장항#2T/L 정밀점검공사","2025-10-20 08:00","2025-10-24 18:00","2025-10-20 08:00","2025-10-24 18:00","연속"]
[506,"대전세종충남","청양","신서천옥산#2 T/L","[송전][주말작업X]  옥산-장항#1T/L 정밀점검[안전이격]"," 옥산-장항#1T/L 정밀점검공사 [안전이격]","2025-10-13 08:00","2025-10-13 18:00","2025-10-13 08:00","2025-10-13 18:00","연속"]
[507,"대전세종충남","청양","은하홍성#2 T/L","[9월취소시][변전총액] 청양P/O 변전협력 총액공사","ㅁ은하-홍성#2T/L 보호배전반 교체(은하S/S , 홍성S/S)","2025-10-27 09:00","2025-10-29 18:00","취소","취소","연속"]
[508,"대전세종충남","청양","동군산장항#2 T/L","[송전][주말작업X]  옥산-장항#1T/L 정밀점검[안전이격]"," 옥산-장항#1T/L 정밀점검공사 [안전이격]","2025-10-16 08:00","2025-10-17 18:00","2025-10-16 08:00","2025-10-17 18:00","연속"]
[509,"대전세종충남","청양","동군산장항#1 T/L","[송전][주말작업X]  옥산-장항#2T/L 정밀점검[안전이격]"," 옥산-장항#2T/L 정밀점검공사 [안전이격]","2025-10-23 08:00","2025-10-24 18:00","2025-10-23 08:00","2025-10-24 18:00","연속"]
[510,"대전세종충남","청양","청양S/S SEC CB 65660","[변전총액] 청양P/O 변전협력 총액공사","청양SS  #61-#66모선보호반 교체공사","2025-10-13 09:00","2025-10-17 18:00","2025-10-13 09:00","2025-10-17 18:00","연속"]
[511,"대전세종충남","청양","청양S/S CB 6100","[9월취소시][변전총액] 청양P/O 변전협력 총액공사","청양SS  #60-#65모선보호반 교체공사","2025-10-20 09:00","2025-10-24 18:00","2025-10-20 09:00","2025-10-24 18:00","연속"]
[512,"대전세종충남","청양","청양S/S CB 6100","[9월취소시][변전총액] 청양P/O 변전협력 총액공사","청양SS  #60-#65모선보호반 교체공사","2025-10-20 09:00","2025-10-24 18:00","2025-10-20 09:00","2025-10-24 18:00","연속"]
[513,"대전세종충남","청양","청양S/S SEC CB 65660","[9월취소시][변전총액] 청양P/O 변전협력 총액공사","청양SS  #60-#65모선보호반 교체공사","2025-10-20 09:00","2025-10-24 18:00","2025-10-20 09:00","2025-10-24 18:00","연속"]
[514,"대전세종충남","청양","청양S/S SEC CB 60610","[변전총액] 청양P/O 변전협력 총액공사","청양SS  #61-#66모선보호반 교체공사","2025-10-13 09:00","2025-10-17 18:00","2025-10-13 09:00","2025-10-17 18:00","연속"]
[515,"대전세종충남","청양","청양S/S CB 6200","[변전총액] 청양P/O 변전협력 총액공사","청양SS  #61-#66모선보호반 교체공사","2025-10-13 09:00","2025-10-17 18:00","2025-10-13 09:00","2025-10-17 18:00","연속"]
[516,"전북","군산","군산이리#1 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#1 동시휴전 필요)"," 군산-영등T/L 스페이서 보수공사 ※  군산-영등, 군산-이리T/L 4회선 구간으로 동시휴전 필요","2025-10-27 07:00","2025-10-27 18:00","취소","취소","연속"]
[517,"전북","군산","군산이리#2 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#2 동시휴전 필요)"," 군산-영등T/L 스페이서 보수공사 ※  군산-영등, 군산-이리T/L 4회선 구간으로 동시휴전 필요","2025-10-28 07:00","2025-10-28 18:00","취소","취소","연속"]
[518,"전북","군산","동군산군산CC#1 T/L","#4M.Tr 증설관련 개폐장치 설치(154) 무부하가압","#4M.Tr 증설관련 개폐장치 설치공사 -  GIS 1CCT 설치","2025-10-23 09:00","2025-10-24 18:00","2025-10-23 09:00","2025-10-24 18:00","연속"]
[519,"전북","군산","군산동군산#2 T/L","#4M.Tr 증설관련 개폐장치 설치(154) 이격확보","#4M.Tr 증설관련 개폐장치 설치공사 -  GIS 1CCT 설치","2025-10-22 09:00","2025-10-24 18:00","2025-10-22 09:00","2025-10-24 18:00","연속"]
[520,"전북","군산","동군산군산CC#1 T/L","#4M.Tr 증설관련 개폐장치 설치(154) 무부하가압","#4M.Tr 증설관련 개폐장치 설치공사 -  GIS 1CCT 설치","2025-10-19 09:00","2025-10-20 18:00","2025-10-19 09:00","2025-10-20 18:00","연속"]
[521,"전북","군산","군공소룡#1 T/L","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","170kV GIS 정밀점검공사","2025-10-24 17:00","2025-10-24 18:00","2025-10-24 17:00","2025-10-24 18:00","연속"]
[522,"전북","군산","군산영등#1 T/L","'25년 군산전력지사 가공송전협력회사공사(영등-낭산#2 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 및 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-10-29 07:00","2025-10-29 18:00","취소","취소","연속"]
[523,"전북","군산","영등낭산#1 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#2 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-10-30 07:00","2025-10-30 18:00","취소","취소","연속"]
[524,"전북","군산","군산영등#2 T/L","'25년 군산전력지사 가공송전협력회사공사(영등-낭산#1 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-10-30 07:00","2025-10-30 18:00","취소","취소","연속"]
[525,"전북","군산","영등낭산#2 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#1 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-10-29 07:00","2025-10-29 18:00","취소","취소","연속"]
[526,"전북","군산","군산영등#1 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-이리#1 동시휴전 필요)"," 군산-영등T/L 스페이서 보수공사 ※  군산-영등, 군산-이리T/L 4회선 구간으로 동시휴전 필요","2025-10-27 07:00","2025-10-27 18:00","취소","취소","연속"]
[527,"전북","군산","군산영등#2 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-이리#2 동시휴전 필요)"," 군산-영등T/L 스페이서 보수공사 ※  군산-영등, 군산-이리T/L 4회선 구간으로 동시휴전 필요","2025-10-28 07:00","2025-10-28 18:00","취소","취소","연속"]
[528,"전북","군산","군산이리#1 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-10-01 09:00","2025-10-02 18:00","취소","취소","연속"]
[529,"전북","군산","팔봉왕궁#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-10-01 08:00","2025-10-01 18:00","취소","취소","연속"]
[530,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS T/R x 2CCT, T/L x 1CCT 교체","2025-10-10 16:00","2025-10-10 18:00","2025-10-10 16:00","2025-10-10 18:00","연속"]
[531,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS T/R x 2CCT, T/L x 1CCT 교체","2025-10-09 16:00","2025-10-10 16:00","2025-10-09 16:00","2025-10-10 16:00","연속"]
[532,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS T/R x 2CCT, T/L x 1CCT 교체","2025-10-06 15:00","2025-10-07 15:00","2025-10-06 15:00","2025-10-07 15:00","연속"]
[533,"전북","군산","팔봉왕궁#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-10-02 08:00","2025-10-02 18:00","취소","취소","연속"]
[534,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS T/R x 2CCT, T/L x 1CCT 교체","2025-10-04 14:00","2025-10-04 15:00","2025-10-04 14:00","2025-10-04 15:00","연속"]
[535,"전북","김제","고창홍농 T/L"," 고창-영광T/L No.45~142 선종교체공사","○  고창-영광T/L 선종교체공사 - No.45~142 전력선 교체(ACSR 330㎟ -> ASCC 430㎟)","2025-10-27 06:00","2025-11-25 18:00","2025-10-27 06:00","2025-11-25 18:00","연속"]
[536,"전북","김제","정주동부안#1 T/L","동부안S/S 170kV GIS 보통점검","차단기 보통점검","2025-10-10 10:00","2025-10-10 18:00","2025-10-10 10:00","2025-10-10 18:00","연속"]
[537,"전북","김제","부안동부안#1 T/L","동부안S/S 170kV GIS 보통점검","차단기 보통점검","2025-10-01 10:00","2025-10-01 18:00","2025-10-01 10:00","2025-10-01 18:00","연속"]
[538,"전북","김제","부안동부안#2 T/L","동부안S/S 170kV GIS 보통점검","차단기 보통점검","2025-10-02 10:00","2025-10-02 18:00","2025-10-02 10:00","2025-10-02 18:00","연속"]
[539,"전북","김제","정주동부안#2 T/L","동부안S/S 170kV GIS 보통점검","차단기 보통점검","2025-10-15 10:00","2025-10-15 18:00","2025-10-15 10:00","2025-10-15 18:00","연속"]
[540,"전북","김제","백산김제#1 T/L","김제전력지사 장기사용 배전반 대체","백산,김제S/S 백산-김제#1T/L 보호반 대체","2025-10-15 09:00","2025-10-17 18:00","취소","취소","연속"]
[541,"전북","김제","백산김제#2 T/L","김제전력지사 장기사용 배전반 대체","백산,김제S/S 백산-김제#2T/L 보호반 대체","2025-10-22 09:00","2025-10-24 18:00","취소","취소","연속"]
[542,"전북","김제","신김제동전주#1 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #1T/L 전선이동 (가선로 → 본선로), 케이블타워 조립 및 긴선 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-10-17 07:00","2025-10-25 18:00","취소","취소","연속"]
[543,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #2T/L 전선이동 (가선로 → 본선로) 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-10-13 07:00","2025-10-16 18:00","취소","취소","연속"]
[544,"전북","김제","신김제S/S #1 EM.Tr CB","신김제 FR-ESS 정밀점검","신김제 FR-ESS 정밀점검","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[545,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #2T/L 긴선(케이블타워) 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-10-26 07:00","2025-10-29 18:00","취소","취소","연속"]
[546,"전북","김제","남전주임실#2 T/L"," 북임실분기T/L 건설사업"," 남전주-임실T/L 2∏분기","2025-10-20 09:00","2025-10-24 18:00","취소","취소","연속"]
[547,"전북","김제","남전주임실#1 T/L"," 북임실분기T/L 건설사업"," 남전주-임실T/L 2∏분기","2025-10-27 09:00","2025-10-29 18:00","취소","취소","연속"]
[548,"전북","김제","정공칠보HP T/L","정공S/S 정공-칠보T/L ES 조작함 접지해소 공사","정공S/S 정공-칠보T/L ES 조작함 접지해소 공사","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[549,"전북","김제","정공정주#2 T/L","김제전력지사 기타설비 점검공사","정공S/S 정공-정주#2T/L CVT 초기점검","2025-10-14 15:00","2025-10-14 18:00","2025-10-14 15:00","2025-10-14 18:00","연속"]
[550,"전북","김제","정공정주#1 T/L","김제전력지사 기타설비 점검공사","정공S/S 정공-정주#1T/L CVT 하자점검","2025-10-13 15:00","2025-10-13 18:00","2025-10-13 15:00","2025-10-13 18:00","연속"]
[551,"전북","김제","소성고창#1 T/L","소성S/S 170kV GIS 보통점검","차단기 보통점검","2025-10-20 10:00","2025-10-20 18:00","2025-10-20 10:00","2025-10-20 18:00","연속"]
[552,"전북","김제","소성고창#2 T/L","소성S/S 170kV GIS 보통점검","차단기 보통점검","2025-10-21 10:00","2025-10-21 18:00","2025-10-21 10:00","2025-10-21 18:00","연속"]
[553,"전북","직할","동전주북전주#1 T/L","전주전철#2T/L GIS 정밀점검 무부하가압","전주전철#2T/L GIS 정밀점검 무부하가압","2025-10-28 15:00","2025-10-28 16:00","2025-10-28 15:00","2025-10-28 16:00","연속"]
[554,"전북","직할","신김제동전주#1 T/L","동전주-태평#1T/L GIS 정밀점검 관련 무부하가압","동전주-태평#1T/L GIS 정밀점검 관련 무부하가압","2025-10-16 15:00","2025-10-16 16:00","2025-10-16 15:00","2025-10-16 16:00","연속"]
[555,"전북","직할","동전주북전주#1 T/L","전주전철#1T/L GIS 정밀점검 무부하가압","전주전철#1T/L GIS 정밀점검 무부하가압","2025-10-21 15:00","2025-10-21 16:00","2025-10-21 15:00","2025-10-21 16:00","연속"]
[556,"전북","직할","신김제동전주#1 T/L","'25년도 변전분야 기타기기 정기점검","- LA, CVT 보통점검","2025-10-23 09:00","2025-10-23 18:00","취소","취소","연속"]
[557,"전북","직할","동전주북전주#1 T/L","전주전철#1T/L GIS 정밀점검 무부하가압","전주전철#1T/L GIS 정밀점검 무부하가압","2025-10-23 15:00","2025-10-23 16:00","2025-10-23 15:00","2025-10-23 16:00","연속"]
[558,"전북","직할","신김제동전주#2 T/L","'25년도 변전분야 기타기기 정기점검","- LA, CVT 보통점검","2025-10-24 09:00","2025-10-24 18:00","취소","취소","연속"]
[559,"전북","직할","동전주북전주#1 T/L","전주전철#2T/L GIS 정밀점검 무부하가압","전주전철#2T/L GIS 정밀점검 무부하가압","2025-10-30 15:00","2025-10-30 16:00","2025-10-30 15:00","2025-10-30 16:00","연속"]
[560,"전북","직할","신김제동전주#1 T/L","동전주-태평#1T/L GIS 정밀점검 관련 무부하가압","동전주-태평#1T/L GIS 정밀점검 관련 무부하가압","2025-10-14 15:00","2025-10-14 16:00","2025-10-14 15:00","2025-10-14 16:00","연속"]
[561,"전북","직할","왕궁봉동#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-10-13 08:00","2025-10-13 18:00","취소","취소","연속"]
[562,"전북","직할","왕궁봉동#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-10-14 08:00","2025-10-14 18:00","취소","취소","연속"]
[563,"전북","직할","북전주봉동#1 T/L","북전주-봉동#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-10-13 09:00","2025-10-16 18:00","취소","취소","연속"]
[564,"전북","직할","북전주봉동#1 T/L","6433 GIS 정밀점검 관련 무부하가압","6433 GIS 정밀점검 관련 무부하가압","2025-10-16 15:00","2025-10-16 16:00","2025-10-16 15:00","2025-10-16 16:00","연속"]
[565,"전북","직할","북전주진안 T/L","'25년도 변전분야 기타기기 정기점검","- LA 보통점검","2025-10-17 09:00","2025-10-17 18:00","취소","취소","연속"]
[566,"전북","직할","북전주S/S #2 BUS","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-10-22 09:00","2025-10-23 18:00","취소","취소","연속"]
[567,"전북","직할","북전주S/S #1 BUS","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-10-20 09:00","2025-10-21 18:00","취소","취소","연속"]
[568,"전북","직할","북전주봉동#2 T/L","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-10-20 09:00","2025-10-23 18:00","취소","취소","연속"]
[569,"전북","직할","북전주S/S #1 BUS","북전주-봉동#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-10-13 09:00","2025-10-14 18:00","취소","취소","연속"]
[570,"전북","직할","북전주봉동#1 T/L","6433 GIS 정밀점검 관련 무부하가압","6433 GIS 정밀점검 관련 무부하가압","2025-10-14 15:00","2025-10-14 16:00","2025-10-14 15:00","2025-10-14 16:00","연속"]
[571,"전북","직할","북전주S/S #2 BUS","북전주-봉동#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-10-15 09:00","2025-10-16 18:00","취소","취소","연속"]
[572,"전북","직할","신남원S/S #6 EM.Tr CB","'25년도 변전분야 기타기기 정기점검","- EM.Tr, EP.Tr, 154/23kV EGIS 보통점검","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[573,"전북","직할","전주서곡#1 T/L","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","2025-10-16 15:00","2025-10-16 16:00","2025-10-16 15:00","2025-10-16 16:00","연속"]
[574,"전북","직할","전주서곡#1 T/L","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","2025-10-14 15:00","2025-10-14 16:00","2025-10-14 15:00","2025-10-14 16:00","연속"]
[575,"전북","직할","전주서곡#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-10-01 08:00","2025-10-02 18:00","취소","취소","연속"]
[576,"전북","직할","전주서곡#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-10-27 08:00","2025-10-28 18:00","취소","취소","연속"]
[577,"전북","직할","태평S/S CB 6100"," 태평S/S  장기사용 GIS 교체공사","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-11 09:00","2025-10-29 18:00","2025-10-11 09:00","2025-10-29 18:00","연속"]
[578,"전북","직할","태평S/S  #1-#2 PT GIS"," 태평S/S  장기사용 GIS 교체공사","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-11 09:00","2025-10-29 18:00","취소","취소","연속"]
[579,"전북","직할","태평S/S #2 BUS"," 태평S/S  장기사용 GIS 교체공사","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-11 09:00","2025-10-12 18:00","2025-10-11 09:00","2025-10-12 18:00","연속"]
[580,"전북","직할","동전주태평#2 T/L"," 태평S/S  장기사용 GIS 교체공사 (무부하가압, 2H)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-12 16:00","2025-10-12 18:00","2025-10-12 16:00","2025-10-12 18:00","연속"]
[581,"전북","직할","태평S/S #1 BUS"," 태평S/S  장기사용 GIS 교체공사","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-13 09:00","2025-10-21 18:00","2025-10-13 09:00","2025-10-21 18:00","연속"]
[582,"전북","직할","동전주태평#2 T/L"," 태평S/S  장기사용 GIS 교체공사 (모선절체용 임시 TIE)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-13 09:00","2025-10-13 10:00","2025-10-13 09:00","2025-10-13 10:00","연속"]
[583,"전북","직할","동전주태평#2 T/L"," 태평S/S  장기사용 GIS 교체공사 (무부하가압)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-20 18:00","2025-10-21 18:00","2025-10-20 18:00","2025-10-21 18:00","연속"]
[584,"전북","직할","태평S/S #2 BUS"," 태평S/S  장기사용 GIS 교체공사","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-22 09:00","2025-10-29 15:00","2025-10-22 09:00","2025-10-29 15:00","연속"]
[585,"전북","직할","동전주태평#2 T/L"," 태평S/S  장기사용 GIS 교체공사 (모선절체용 임시 TIE)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-22 09:00","2025-10-22 10:00","2025-10-22 09:00","2025-10-22 10:00","연속"]
[586,"전북","직할","동전주태평#2 T/L"," 태평S/S  장기사용 GIS 교체공사 (무부하가압)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-28 14:00","2025-10-29 18:00","2025-10-28 14:00","2025-10-29 18:00","연속"]
[587,"전북","직할","태평S/S #1 BUS"," 태평S/S  장기사용 GIS 교체공사","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-29 15:00","2025-10-29 18:00","2025-10-29 15:00","2025-10-29 18:00","연속"]
[588,"전북","직할","서곡태평#1 T/L","[3차수]태평S/S  장기사용 GIS 교체공사 (무부하)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-24 17:00","2025-10-25 17:00","2025-10-24 17:00","2025-10-25 17:00","연속"]
[589,"전북","직할","동전주태평#2 T/L","[2차수]태평S/S  장기사용 GIS 교체공사(무부하)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-01 14:00","2025-10-02 18:00","2025-10-01 14:00","2025-10-02 18:00","연속"]
[590,"전북","직할","서곡태평#1 T/L","[3차수]태평S/S  장기사용 GIS 교체공사 (무부하, 2H)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-15 15:00","2025-10-15 17:00","2025-10-15 15:00","2025-10-15 17:00","연속"]
[591,"전북","직할","동전주태평#1 T/L","[3차수]태평S/S  장기사용 GIS 교체공사","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-10-10 09:00","2025-11-12 18:00","2025-10-10 09:00","2025-11-12 18:00","연속"]
[592,"광주전남","강진","신강진강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","신강진-강진#1T/L 38~42호 피뢰기 및 추락방지장치 설치 ※ 강진-남창#1T/L 병행휴전 (4회선 구간) ※ 1시간 이내 즉시가압 가능","2025-10-28 07:00","2025-10-28 18:00","취소","취소","연속"]
[593,"광주전남","강진","강진남창#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","신강진-강진#1T/L 38~42호 피뢰기 및 추락방지장치 설치 ※ 강진-남창#1T/L 병행휴전 (4회선 구간) ※ 1시간 이내 즉시가압 가능","2025-10-28 07:00","2025-10-28 18:00","취소","취소","연속"]
[594,"광주전남","강진","금정강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","금정-강진#1T/L 피뢰기 및 추락방지장치 설치 ※ 1시간 이내 즉시가압 가능","2025-10-13 07:00","2025-10-14 18:00","취소","취소","연속"]
[595,"광주전남","강진","강진장흥#2 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","강진장흥#2T/L 1~59호 피뢰기 및 추락방지장치 설치 ※ 1시간 이내 즉시가압 가능","2025-10-13 07:00","2025-10-17 18:00","취소","취소","연속"]
[596,"광주전남","강진","나주금천#2 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#1T/L 정밀점검(안전이격 확보) (나주-영암#1T/L 병가선로)(1시간 내 가압 가능)","2025-10-28 07:00","2025-10-31 18:00","2025-10-28 07:00","2025-10-31 18:00","연속"]
[597,"광주전남","강진","나주영암#1 T/L","2025년 가공송전 순시점검 위탁공사","나주-영암#1T/L 정밀점검 (영암-금정#2T/L, 나주-금천#2T/L 병가선로)(1시간 내 가압 가능)","2025-10-21 07:00","2025-10-31 18:00","2025-10-21 07:00","2025-10-31 18:00","연속"]
[598,"광주전남","강진","나주엄다#1 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.28(화) 08:00 ~ 25.10.29(수) 18:00 4. 작업구간 :  나주-엄다#1TL No.9~17 (母선로 :  왕곡-나주#1T/L No.6~14)","2025-10-28 08:00","2025-10-29 18:00","취소","취소","연속"]
[599,"광주전남","강진","나주영암#2 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","나주영암#2T/L 1~81호 피뢰기 및 추락방지장치 설치 ※ 나주-금천#1T/L, 금정-영암#1T/L 병행휴전 (4회선 구간) ※ 1시간 이내 즉시가압 가능","2025-10-30 07:00","2025-11-10 18:00","2025-10-30 07:00","2025-11-10 18:00","연속"]
[600,"광주전남","강진","나주금천#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","나주영암#2T/L 1~81호 피뢰기 및 추락방지장치 설치 ※ 나주-금천#1T/L, 영암-금정#1T/L 병행휴전 (4회선 구간) ※ 1시간 이내 즉시가압 가능","2025-10-30 07:00","2025-10-30 18:00","2025-10-30 07:00","2025-10-30 18:00","연속"]
[601,"광주전남","강진","나주엄다#2 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.30(목) 08:00 ~ 18:00 4. 작업구간 :  나주-엄다#2T/L No.9~17 (母선로 :  왕곡-나주#2T/L No.6~14)","2025-10-30 08:00","2025-10-30 18:00","취소","취소","연속"]
[602,"광주전남","강진","남창해남CS#1 T/L","남창S/S 남창-해남C/S #1,2T/L 인출변경 공사","남창-해남C/S #1,2T/L 인출변경 × 1식","2025-10-15 07:00","2025-10-19 15:00","취소","취소","연속"]
[603,"광주전남","강진","남창S/S 모선연계T/L CB","남창S/S 남창-해남C/S #1,2T/L 인출변경 공사","남창-해남C/S #1,2T/L 인출변경 × 1식","2025-10-15 07:00","2025-10-19 15:00","취소","취소","연속"]
[604,"광주전남","강진","남창해남CS#2 T/L","남창S/S 남창-해남C/S #1,2T/L 인출변경 공사","남창-해남C/S #1,2T/L 인출변경 × 1식","2025-10-13 09:00","2025-10-15 15:00","취소","취소","연속"]
[605,"광주전남","강진","대불남악#1 T/L","2024~2025년 강진전력지사 변전협력회사 공사","대불S/S 대불-남악#1T/L CVT 보통점검","2025-10-01 09:00","2025-10-01 13:00","2025-10-01 16:00","2025-10-01 20:00","연속"]
[606,"광주전남","강진","대불남악#2 T/L","2024~2025년 강진전력지사 변전협력회사 공사","대불S/S 대불-남악#2T/L LA A,B,C 보통점검","2025-10-01 13:00","2025-10-01 17:00","2025-10-01 20:00","2025-10-02 02:00","연속"]
[607,"광주전남","강진","보성벌교 T/L","2024-2025년 강진전력지사 변전협력회사 공사","- 170kV GIS 공기배출밸브 개선","2025-10-16 14:00","2025-10-16 18:00","취소","취소","연속"]
[608,"광주전남","강진","장흥보성 T/L","2024-2025년 강진전력지사 변전협력회사 공사","- 170kV GIS 공기배출밸브 개선","2025-10-16 10:00","2025-10-16 14:00","취소","취소","연속"]
[609,"광주전남","강진","삼호화원#1 T/L"," 삼호-화원 지중T/L(복도체화) 건설공사"," XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2025-10-01 09:00","2025-10-22 18:00","취소","취소","연속"]
[610,"광주전남","강진","삼호화원#2 T/L"," 삼호-화원 지중T/L(복도체화) 건설공사"," XLPE 2000㎟(S) × 6.8km → XLPE 2000㎟(D) × 6.8km","2025-10-23 09:00","2025-11-14 18:00","취소","취소","연속"]
[611,"광주전남","강진","신강진대불#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","신강진-대불#2 가공지선 교체공사","2025-10-30 07:00","2025-10-30 18:00","취소","취소","연속"]
[612,"광주전남","강진","영암금정#2 T/L","2025년 가공송전 순시점검 위탁공사","영암-금정#2T/L 정밀점검 (나주-영암#1T/L 병가선로)(1시간 내 가압 가능)","2025-10-20 07:00","2025-10-27 18:00","2025-10-20 07:00","2025-10-27 18:00","연속"]
[613,"광주전남","강진","영암금정#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","나주영암#2T/L 1~81호 피뢰기 및 추락방지장치 설치 ※ 나주-금천#1T/L, 영암-금정#1T/L 병행휴전 (4회선 구간) ※ 1시간 이내 즉시가압 가능","2025-10-31 07:00","2025-11-05 18:00","2025-10-31 07:00","2025-11-05 18:00","연속"]
[614,"광주전남","강진","남창완도 T/L","2024-2025년 강진전력지사 변전협력회사 공사","- 170kV GIS 차단기 조작시험 및 공기배출밸브 개선","2025-10-23 10:00","2025-10-23 14:00","2025-10-23 10:00","2025-10-23 14:00","연속"]
[615,"광주전남","강진","화원진도#2 T/L","2024-2025년 강진전력지사 변전협력회사 공사","- 170kV GIS 차단기 조작시험, 공기배출밸브 개선","2025-10-15 14:00","2025-10-15 18:00","취소","취소","연속"]
[616,"광주전남","강진","화원진도#1 T/L","2024-2025년 강진전력지사 변전협력회사 공사","- 170kV GIS 차단기 조작시험, 공기배출밸브 개선","2025-10-15 10:00","2025-10-15 14:00","취소","취소","연속"]
[617,"광주전남","강진","해남해남CS#2 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-10-15 16:00","2025-10-15 20:00","2025-10-15 16:00","2025-10-15 20:00","연속"]
[618,"광주전남","강진","해남진도#2 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-10-16 16:00","2025-10-16 20:00","2025-10-16 16:00","2025-10-16 20:00","연속"]
[619,"광주전남","강진","해남해남CS#1 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-10-14 16:00","2025-10-14 20:00","2025-10-14 16:00","2025-10-14 20:00","연속"]
[620,"광주전남","강진","화원진도#1 T/L","2024~2025년 강진전력지사 송전협력회사 공사","항공장애표시구 (강진전(송전)-1431)로 인한 철거분 재설치","2025-10-13 07:00","2025-10-13 18:00","취소","취소","연속"]
[621,"광주전남","강진","화원진도#2 T/L","2025년 가공송전 순시점검 위탁공사","화원-진도#2T/L 정밀점검 (1시간 내 가압 가능)","2025-10-14 07:00","2025-10-17 18:00","취소","취소","연속"]
[622,"광주전남","광주","신광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 신광주-계림#2T/L 170kV GIS 조작시험","2025-10-21 13:00","2025-10-21 16:00","취소","취소","연속"]
[623,"광주전남","광주","계림S/S SEC CB 61600","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S #60-61BUS-SEC 조작시험","2025-10-22 10:00","2025-10-22 13:00","2025-10-22 10:00","2025-10-22 13:00","연속"]
[624,"광주전남","광주","북광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#2T/L 조작시험","2025-10-20 13:00","2025-10-20 16:00","취소","취소","연속"]
[625,"광주전남","광주","북광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#1T/L 조작시험","2025-10-20 10:00","2025-10-20 13:00","취소","취소","연속"]
[626,"광주전남","광주","계림승주#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 계림-승주#2 T/L 피뢰기 설치 - 대상 : 1~3, 17~107호 (총 99기) - 병가구간 : 3호 (남광주-계림, 계림-소태 병가), 99~106호(순천-승주#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-10-13 07:00","2025-10-23 18:00","취소","취소","연속"]
[627,"광주전남","광주","계림S/S SEC CB 61600","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-10-06 09:00","2025-10-10 18:00","취소","취소","연속"]
[628,"광주전남","광주","계림S/S SEC CB 66650","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-10-06 09:00","2025-10-10 18:00","취소","취소","연속"]
[629,"광주전남","광주","계림S/S CB 6100","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-10-06 09:00","2025-10-10 18:00","취소","취소","연속"]
[630,"광주전남","광주","신광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 신광주-계림#1T/L 170kV GIS 조작시험","2025-10-21 10:00","2025-10-21 13:00","2025-10-21 10:00","2025-10-21 13:00","연속"]
[631,"광주전남","광주","계림S/S SEC CB 66650","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S #65-#66 BUS-SEC 조작시험","2025-10-22 13:00","2025-10-22 16:00","2025-10-22 13:00","2025-10-22 16:00","연속"]
[632,"광주전남","광주","계림S/S CB 6200","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 6200BUS-TIE 조작시험","2025-10-23 10:00","2025-10-23 16:00","2025-10-23 10:00","2025-10-23 16:00","연속"]
[633,"광주전남","광주","정공담양 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 (병가) - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-10-20 07:00","2025-10-21 18:00","취소","취소","연속"]
[634,"광주전남","광주","신광주일곡#1 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주-일곡#1,2T/L PT 보통점검","2025-10-15 10:00","2025-10-15 14:00","2025-10-15 10:00","2025-10-15 14:00","연속"]
[635,"광주전남","광주","신광주계림#2 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주-계림#2T/L LA A,B,C상 보통점검","2025-10-03 09:00","2025-10-03 18:00","취소","취소","연속"]
[636,"광주전남","광주","신광주S/S #3 Sh.C CB","2025년 광주전력지사 170kV GIS 점검공사","2025년 광주전력지사 170kV GIS 점검공사 - 신광주S/S #3Sh.C170kV GIS 정밀점검","2025-10-28 09:00","2025-10-30 18:00","취소","취소","연속"]
[637,"광주전남","광주","신광주계림#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  신광주-계림#2T/L GIS 보통점검","2025-10-24 09:00","2025-10-24 18:00","취소","취소","연속"]
[638,"광주전남","광주","신광주S/S CB 6100","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S #1 BUSTIE 보통점검","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[639,"광주전남","광주","신광주일곡#2 T/L","2024-2025년도 광주전력지사 변전협력회사 총액공사","신광주-일곡#1,2T/L PT 보통점검","2025-10-15 14:00","2025-10-15 18:00","2025-10-16 10:00","2025-10-16 14:00","연속"]
[640,"광주전남","광주","담양일곡#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-10-20 07:00","2025-10-24 18:00","취소","취소","연속"]
[641,"광주전남","광주","일곡S/S CB 6100","2025년 광주전력지사 170kV GIS 점검공사","2025년 광주전력지사 170kV GIS 점검공사 1. 일곡S/S BUSTIE 정밀점검","2025-10-21 09:00","2025-10-23 18:00","취소","취소","연속"]
[642,"광주전남","광주","하남장성#1 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치(병가) - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-10-27 07:00","2025-10-28 18:00","취소","취소","연속"]
[643,"광주전남","광주","장성영광#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","-장성-영광#1T/L 170kV GIS 조작시험","2025-10-24 15:00","2025-10-24 18:00","취소","취소","연속"]
[644,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  신광주-장성#2T/L GIS 보통점검","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[645,"광주전남","광주","장성영광#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치 - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-10-27 07:00","2025-10-31 18:00","취소","취소","연속"]
[646,"광주전남","광주","남광주화순#2 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.20(월) 08:00 ~ 25.10.20(월) 18:00 4. 작업구간 : 남광주-화순#2T/L No.2~8 5. 작업내용 : 정밀점검","2025-10-20 08:00","2025-10-20 18:00","2025-10-20 08:00","2025-10-20 18:00","연속"]
[647,"광주전남","광주","화순승주#1 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.20(월) 08:00 ~ 25.10.22(수) 18:00 4. 작업구간 :  화순-승주#1T/L No.1~4, 223~225, 260, 265, 277, 278~297 5. 작업내용 : 정밀점검","2025-10-20 08:00","2025-10-22 18:00","2025-10-20 08:00","2025-10-22 18:00","연속"]
[648,"광주전남","광주","남광주화순#1 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.23(목) 08:00 ~ 25.10.23(월) 18:00 4. 작업구간 : 남광주-화순#1T/L No.2~8 5. 작업내용 : 정밀점검","2025-10-23 08:00","2025-10-23 18:00","2025-10-23 08:00","2025-10-23 18:00","연속"]
[649,"광주전남","광주","화순승주#2 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.23(목) 08:00 ~ 25.10.27(월) 18:00 4. 작업구간 :  화순-승주#2T/L No. 1~4, 260, 265, 277, 278~297 5. 작업내용 : 정밀점검","2025-10-23 08:00","2025-10-27 18:00","2025-10-23 08:00","2025-10-27 18:00","연속"]
[650,"광주전남","광주","신화순화순#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#2T/L GIS 정밀점검","2025-10-13 09:00","2025-10-15 18:00","취소","취소","연속"]
[651,"광주전남","목포","신안읍동#2 T/L CB"," 운남-안좌개폐소T/L 건설공사(1공구)"," 운남-안좌개폐소T/L 건설공사(1공구) 전력선 가선작업 - No.70~74 가선(점퍼선 설치)작업 * No.74 : 운남-신안, 신안-읍동 분기철탑 * 주말, 휴일작업 시행 예정","2025-10-21 08:00","2025-10-21 18:00","2025-10-21 08:00","2025-10-21 18:00","연속"]
[652,"광주전남","목포","신안읍동#1 T/L CB"," 운남-안좌개폐소T/L 건설공사(1공구)"," 운남-안좌개폐소T/L 건설공사(1공구) 전력선 가선작업 - No.70~74 가선작업 * No.74 : 운남-신안, 신안-읍동 분기철탑 * 주말, 휴일작업 시행 예정","2025-10-13 08:00","2025-10-21 18:00","2025-10-13 08:00","2025-10-21 18:00","연속"]
[653,"광주전남","목포","남악북항#1 T/L","북항변전소 건축설비 보수 공사","변전소 외벽 마감재 고정 (일정 변경가능)","2025-10-22 16:00","2025-10-22 22:00","2025-10-22 16:00","2025-10-22 22:00","연속"]
[654,"광주전남","목포","목포북항#1 T/L","북항변전소 건축설비 보수 공사","변전소 외벽 마감재 고정 (일정 변경가능)","2025-10-22 16:00","2025-10-22 22:00","2025-10-24 16:00","2025-10-24 22:00","연속"]
[655,"광주전남","목포","목포북항#2 T/L","2025년 목포전력지사 변전협력회사 총액공사","GIS 점검","2025-10-22 10:00","2025-10-22 18:00","취소","취소","연속"]
[656,"광주전남","목포","남악북항#2 T/L","북항변전소 건축설비 보수 공사","변전소 외벽 마감재 고정 (일정 변경가능)","2025-10-21 16:00","2025-10-21 22:00","2025-10-21 16:00","2025-10-21 22:00","연속"]
[657,"광주전남","목포","목포북항#2 T/L","북항변전소 건축설비 보수 공사","변전소 외벽 마감재 고정 (일정 변경가능)","2025-10-21 16:00","2025-10-21 22:00","2025-10-23 16:00","2025-10-23 22:00","연속"]
[658,"광주전남","목포","화원안좌#1 T/L","2025년 목포전력지사 변전협력회사 총액공사","보호반대체","2025-10-20 10:00","2025-10-22 18:00","취소","취소","연속"]
[659,"광주전남","목포","안좌S/S 스마트팜#1T/L CB","2025년 목포전력지사 변전협력회사 총액공사","GIS 점검","2025-10-23 15:00","2025-10-23 18:00","2025-10-23 15:00","2025-10-23 18:00","연속"]
[660,"광주전남","목포","화원안좌#2 T/L","2025년 목포전력지사 변전협력회사 총액공사","보호반대체","2025-10-27 10:00","2025-10-29 18:00","취소","취소","연속"]
[661,"광주전남","목포","안좌S/S 스마트팜#2T/L CB","2025년 목포전력지사 변전협력회사 총액공사","GIS 점검","2025-10-23 18:00","2025-10-23 21:00","2025-10-23 18:00","2025-10-23 21:00","연속"]
[662,"광주전남","목포","엄다목포#2 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치 병가구간 휴전 및  엄다-목포T/L 피뢰기 설치","2025-10-06 08:00","2025-10-10 18:00","취소","취소","연속"]
[663,"광주전남","목포","엄다무안햇빛#1 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  엄다-무안햇빛T/L 고정형폴리머 점퍼지지애자 설치 3. 공사구간  엄다-무안햇빛#1 No.4~39(13기)","2025-10-13 07:30","2025-10-15 17:00","취소","취소","연속"]
[664,"광주전남","목포","엄다무안햇빛#2 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  엄다-무안햇빛T/L 고정형폴리머 점퍼지지애자 설치 3. 공사구간  엄다-무안햇빛#1 No.4~39(13기)","2025-10-16 07:30","2025-10-20 17:00","취소","취소","연속"]
[665,"광주전남","목포","나주엄다#2 T/L","2025년 목포전력지사 변전협력회사 총액공사","LA점검","2025-10-24 10:00","2025-10-24 18:00","취소","취소","연속"]
[666,"광주전남","목포","나주엄다#1 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치(116기)","2025-10-01 08:00","2025-10-08 18:00","취소","취소","연속"]
[667,"광주전남","순천","벌교고흥#2 T/L","24-25년 순천전력지사 변전협력회사 공사","고흥S/S 벌교-고흥#2T/L GIS 보통점검 및 벌교S/S 벌교-고흥#2T/L GIS 전자변대체","2025-10-02 09:00","2025-10-02 18:00","취소","취소","연속"]
[668,"광주전남","순천","벌교고흥#1 T/L","24-25년 순천전력지사 변전협력회사 공사","벌교,고흥S/S 벌교-고흥#1T/L GIS 보통점검 및 벌교S/S 벌교-고흥#1T/L GIS 전자변대체","2025-10-01 09:00","2025-10-01 18:00","취소","취소","연속"]
[669,"광주전남","순천","광양하동#2 T/L","코타핀 교체(광양-하동#2)","코타핀 교체","2025-10-21 13:00","2025-10-21 18:00","2025-10-21 13:00","2025-10-21 18:00","연속"]
[670,"광주전남","순천","광양백운#1 T/L","24-25년 순천전력지사 변전협력회사 공사","광양-백운#1T/L 보호배전반 대체","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[671,"광주전남","순천","벌교고흥#1 T/L","피뢰기 설치(벌교-고흥#1T/L)","피뢰기 설치","2025-10-20 07:00","2025-10-21 18:00","취소","취소","연속"]
[672,"광주전남","순천","장흥벌교 T/L","피뢰기 설치(장흥-벌교T/L)","피뢰기 설치","2025-10-20 07:00","2025-10-21 18:00","취소","취소","연속"]
[673,"광주전남","순천","장흥벌교 T/L","24-25년 순천전력지사 변전협력회사 공사","벌교S/S 장흥-벌교T/L GIS 전자변대체","2025-10-13 09:00","2025-10-13 18:00","취소","취소","연속"]
[674,"광주전남","순천","보성벌교 T/L","24-25년 순천전력지사 변전협력회사 공사","벌교S/S 보성-벌교T/L GIS 전자변대체","2025-10-14 09:00","2025-10-14 18:00","취소","취소","연속"]
[675,"광주전남","순천","장흥벌교 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","장흥-벌교T/L 1~50, 71~90호 피뢰기 및 추락방지장치 설치 [2~6호 강진-장흥#2T/L 병행휴전] ※ 1시간 이내 즉시가압 가능","2025-10-17 07:00","2025-10-27 18:00","취소","취소","연속"]
[676,"광주전남","순천","서순천벌교#2 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 서순천-벌교#2T/L GIS 정밀점검","2025-10-16 16:00","2025-10-17 10:00","취소","취소","연속"]
[677,"광주전남","순천","서순천벌교#1 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 서순천-벌교#1T/L GIS 정밀점검","2025-10-13 16:00","2025-10-14 10:00","취소","취소","연속"]
[678,"광주전남","순천","서순천벌교#2 T/L","피뢰기 설치(서순천-벌교#2T/L)","피뢰기 설치","2025-10-13 07:00","2025-10-17 18:00","취소","취소","연속"]
[679,"광주전남","순천","세풍율촌#2 T/L","세풍-율촌T/L 초기점검"," 세풍-율촌T/L 초기점검 시행 - 총 4기","2025-10-29 09:00","2025-10-30 18:00","2025-10-29 09:00","2025-10-30 18:00","연속"]
[680,"광주전남","순천","세풍율촌#1 T/L","세풍-율촌T/L 초기점검"," 세풍-율촌T/L 초기점검 시행 - 총 4기","2025-10-29 09:00","2025-10-30 18:00","2025-10-29 09:00","2025-10-30 18:00","연속"]
[681,"광주전남","순천","황금세풍#1 T/L","백운-세풍T/L 초기점검"," 백운-세풍T/L 초기점검 시행 - 총 4기","2025-10-27 09:00","2025-10-28 18:00","2025-10-27 09:00","2025-10-28 18:00","연속"]
[682,"광주전남","순천","황금세풍#2 T/L","백운-세풍T/L 초기점검"," 백운-세풍T/L 초기점검 시행 - 총 4기","2025-10-27 09:00","2025-10-28 18:00","2025-10-27 09:00","2025-10-28 18:00","연속"]
[683,"광주전남","순천","세풍율촌#2 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-10-21 14:00","2025-10-21 18:00","2025-10-21 14:00","2025-10-21 18:00","연속"]
[684,"광주전남","순천","세풍율촌#1 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-10-21 10:00","2025-10-21 14:00","2025-10-21 10:00","2025-10-21 14:00","연속"]
[685,"광주전남","순천","황금세풍#1 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-10-20 14:00","2025-10-20 18:00","2025-10-20 14:00","2025-10-20 18:00","연속"]
[686,"광주전남","순천","황금세풍#2 T/L","조작불량관련 기계적 접점 교체","조작불량관련 기계적 접점 교체","2025-10-20 10:00","2025-10-20 14:00","2025-10-20 10:00","2025-10-20 14:00","연속"]
[687,"광주전남","순천","소라서순천#1 T/L","애자련 보강(소라-서순천#1)","애자련 보강","2025-10-21 07:00","2025-10-21 12:00","취소","취소","연속"]
[688,"광주전남","순천","소라서순천#2 T/L","애자련 보강(소라-서순천#2)","애자련 보강","2025-10-21 13:00","2025-10-21 18:00","취소","취소","연속"]
[689,"광주전남","순천","순천율촌#2 T/L","애자련 보강(순천-율촌)","애자련 보강","2025-10-22 13:00","2025-10-22 18:00","2025-10-22 13:00","2025-10-22 18:00","연속"]
[690,"광주전남","순천","순천율촌#1 T/L","애자련 보강(순천-율촌)","애자련 보강","2025-10-22 07:00","2025-10-22 18:00","2025-10-23 07:00","2025-10-23 18:00","연속"]
[691,"광주전남","순천","승주주암HP T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.22(수) 08:00 ~ 18:00 4. 작업구간 :  승주-주암HP T/L No.1 93~95 5. 작업내용 : 정밀점검","2025-10-22 08:00","2025-10-22 18:00","취소","취소","연속"]
[692,"광주전남","순천","승주서순천 T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-서순천, 화순-승주2(통보분) 병가) ※주말 미작업","2025-10-23 07:00","2025-10-31 18:00","취소","취소","연속"]
[693,"광주전남","순천","순천승주#1 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.27(월) 08:00 ~ 18:00 4. 작업구간 : 순천-승주#1T/L No.1 5. 작업내용 : 정밀점검","2025-10-27 08:00","2025-10-27 18:00","취소","취소","연속"]
[694,"광주전남","순천","승주서순천 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.27(월) 08:00 ~ 18:00 4. 작업구간 :  승주-서순천 T/L No.1 93~95 5. 작업내용 : 정밀점검","2025-10-27 08:00","2025-10-27 18:00","취소","취소","연속"]
[695,"광주전남","순천","순천승주#1 T/L","24-25년 순천전력지사 변전협력회사 공사","승주S/S 순천-승주#1T/L LA(A,B,C) 보통점검","2025-10-13 09:00","2025-10-13 18:00","취소","취소","연속"]
[696,"광주전남","순천","순천승주#2 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.22(수) 08:00 ~ 18:00 4. 작업구간 : 순천-승주#2T/L No.1 5. 작업내용 : 정밀점검","2025-10-22 08:00","2025-10-22 18:00","취소","취소","연속"]
[697,"광주전남","순천","승주주암HP T/L","항공장애표시구 교체(승주-주암HP)","항공장애표시구 교체","2025-10-20 13:00","2025-10-20 18:00","취소","취소","연속"]
[698,"광주전남","순천","계림승주#2 T/L","24-25년 순천전력지사 변전협력회사 공사","승주S/S 계림-승주#2T/L LA(A,B,C) 보통점검","2025-10-14 09:00","2025-10-14 18:00","취소","취소","연속"]
[699,"광주전남","순천","승주주암HP T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-주암HP, 화순-승주1(통보분) 병가) ※주말 미작업","2025-10-14 07:00","2025-10-22 18:00","취소","취소","연속"]
[700,"광주전남","순천","순천승주#1 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 계림-승주#2 T/L 피뢰기 설치(병가) - 대상 : 1~3, 17~107호 (총 99기) - 병가구간 : 3호 (계림-남광주, 계림-소태 병가), 99~106호(순천-승주#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-10-23 07:00","2025-10-23 18:00","취소","취소","연속"]
[701,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-10-17 17:00","2025-10-17 21:00","2025-10-24 17:00","2025-10-24 21:00","연속"]
[702,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수-소라#1,2T/L 보호배전반 엔지니어링","2025-10-01 17:00","2025-10-02 10:00","2025-10-15 17:00","2025-10-16 10:00","연속"]
[703,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-10-10 09:00","2025-10-31 18:00","2025-10-30 17:00","2025-10-31 21:00","연속"]
[704,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-10-10 09:00","2025-10-15 09:00","2025-10-17 09:00","2025-10-22 09:00","연속"]
[705,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-10-10 09:00","2025-10-15 09:00","2025-10-17 09:00","2025-10-22 09:00","연속"]
[706,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-10-10 09:00","2025-10-31 18:00","2025-10-17 09:00","2025-11-07 18:00","연속"]
[707,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-10-15 09:00","2025-10-23 09:00","2025-10-22 09:00","2025-10-30 09:00","연속"]
[708,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-10-15 09:00","2025-10-23 09:00","2025-10-22 09:00","2025-10-30 09:00","연속"]
[709,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-10-16 17:00","2025-10-16 21:00","2025-10-23 17:00","2025-10-23 21:00","연속"]
[710,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체용 무부하가압","2025-10-22 17:00","2025-10-23 09:00","2025-10-29 17:00","2025-10-30 09:00","연속"]
[711,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체 무부하가압용","2025-10-22 17:00","2025-10-23 09:00","2025-10-28 17:00","2025-10-29 09:00","연속"]
[712,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-10-23 09:00","2025-10-31 09:00","2025-10-30 09:00","2025-11-07 09:00","연속"]
[713,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-10-23 09:00","2025-10-31 09:00","2025-10-30 09:00","2025-11-07 09:00","연속"]
[714,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-10-31 09:00","2025-10-31 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[715,"광주전남","순천","율촌여수산단#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수산단 율촌-여수산단#2T/L GIS 보통점검, 율촌S/S 율촌-여수산단#2T/L LA 보통점검","2025-10-15 09:00","2025-10-15 18:00","취소","취소","연속"]
[716,"광주전남","순천","여수TP여천#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여수TP-여천#1T/L GIS 조작시험","2025-10-21 09:00","2025-10-21 18:00","취소","취소","연속"]
[717,"광주전남","순천","여수TP여천#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP,여천S/S 여수TP-여천#2T/L GIS 보통점검","2025-10-20 09:00","2025-10-20 18:00","취소","취소","연속"]
[718,"광주전남","순천","호남TP여수TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가)","2025-10-17 07:00","2025-10-17 18:00","취소","취소","연속"]
[719,"광주전남","순천","호남TP여수TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP2, 여천-여수1 병가) (2호 : 여천-호남TP2, 호남TP-여수TP2 병가)","2025-10-30 07:00","2025-10-31 18:00","취소","취소","연속"]
[720,"광주전남","순천","여수TP용성#1 T/L","SB댐퍼 설치(여수TP-용성T/L)","SB댐퍼 설치","2025-10-27 07:00","2025-10-27 18:00","취소","취소","연속"]
[721,"광주전남","순천","여수TP화치#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP-화치#2T/L 보호배전반 대체","2025-10-27 09:00","2025-10-31 18:00","2025-10-27 09:00","2025-10-31 18:00","연속"]
[722,"광주전남","순천","여수TP용성#2 T/L","SB댐퍼 설치(여수TP-용성T/L)","SB댐퍼 설치","2025-10-28 07:00","2025-10-28 18:00","취소","취소","연속"]
[723,"광주전남","순천","여수TP화치#1 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","여수화력S/S 여수TP-화치#1T/L GIS 정밀점검","2025-10-23 09:00","2025-10-24 18:00","2025-10-23 09:00","2025-10-24 18:00","연속"]
[724,"광주전남","순천","여천여수#1 T/L","여천S/S  GIS 기기기초 공사","활선직하 기기기초 터파기를 위한 휴전 / 매일휴전 / 즉시가압 가능","2025-10-20 08:00","2025-10-24 17:00","취소","취소","연속"]
[725,"광주전남","순천","여천호남TP#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여천-호남TP#11T/L GIS 보통점검 및 전자변대체","2025-10-22 09:00","2025-10-22 18:00","취소","취소","연속"]
[726,"광주전남","순천","여천호남TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가) ※주말미작업","2025-10-14 07:00","2025-10-22 18:00","취소","취소","연속"]
[727,"광주전남","순천","여천여수산단#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여천-여수산단#2T/L GIS 보통점검 및 전자변대체","2025-10-29 09:00","2025-10-29 18:00","2025-10-29 09:00","2025-10-29 18:00","연속"]
[728,"광주전남","순천","여천여수산단#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여천-여수산단#1T/L GIS 보통점검 및 전자변대체","2025-10-28 09:00","2025-10-28 18:00","2025-10-28 09:00","2025-10-28 18:00","연속"]
[729,"광주전남","순천","여천여수#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여천-여수#2T/L GIS 조작시험","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[730,"광주전남","순천","여천호남TP#1 T/L","여천S/S  GIS 기기기초 공사","활선직하 기기기초 터파기를 위한 휴전 / 매일휴전 / 즉시가압 가능","2025-10-27 08:00","2025-10-31 17:00","취소","취소","연속"]
[731,"광주전남","순천","여천여수#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP2, 여천-여수1 병가) (2호 : 여천-호남TP2, 호남TP-여수TP2 병가)","2025-10-27 07:00","2025-10-29 18:00","취소","취소","연속"]
[732,"광주전남","순천","여천여수#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여천-여수#1T/L GIS 보통점검 및 전자변대체","2025-10-24 09:00","2025-10-24 18:00","취소","취소","연속"]
[733,"광주전남","순천","여천호남TP#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여천-호남TP#2T/L GIS 보통점검","2025-10-23 09:00","2025-10-23 18:00","취소","취소","연속"]
[734,"광주전남","순천","여천여수#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가) ※주말미작업","2025-10-14 07:00","2025-10-16 18:00","취소","취소","연속"]
[735,"광주전남","순천","여천호남TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP2, 여천-여수1 병가) (2호 : 여천-호남TP2, 호남TP-여수TP2 병가) ※주말 미작업","2025-10-23 07:00","2025-10-31 18:00","취소","취소","연속"]
[736,"광주전남","순천","여천여수#2 T/L","여천S/S  GIS 기기기초 공사","활선직하 기기기초 터파기를 위한 휴전 / 매일휴전 / 즉시가압 가능","2025-10-13 08:00","2025-10-17 17:00","취소","취소","연속"]
[737,"광주전남","순천","여수TP용성#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP,용성S/S 여수TP-용성#1T/L GIS 보통점검","2025-10-16 09:00","2025-10-16 18:00","취소","취소","연속"]
[738,"광주전남","순천","여수TP용성#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP,용성S/S 여수TP-용성#2T/L GIS 보통점검","2025-10-17 09:00","2025-10-17 18:00","취소","취소","연속"]
[739,"광주전남","순천","용성여수산단#1 T/L"," 용성-여수산단T/L 폴리머점퍼지지애자 설치공사","용성-여수산단#1T/L 폴리머점퍼지지애자 설치","2025-10-27 07:00","2025-10-29 18:00","2025-10-27 07:00","2025-10-29 18:00","연속"]
[740,"광주전남","순천","율촌여수산단#1 T/L","율촌-여수산단#1 T/L 정밀점검","율촌-여수산단#1 T/L 정밀점검 총 51기","2025-10-20 09:00","2025-10-24 18:00","취소","취소","연속"]
[741,"광주전남","순천","율촌여수산단#2 T/L","율촌-여수산단#2 T/L 정밀점검","율촌-여수산단#2 T/L 정밀점검 총 51기","2025-10-13 09:00","2025-10-17 18:00","취소","취소","연속"]
[742,"광주전남","순천","율촌화치#1 T/L","율촌-여수산단#2 T/L 정밀점검","율촌-여수산단#2 T/L 정밀점검 총 51기 - 병가선로 휴전신청","2025-10-13 09:00","2025-10-17 18:00","취소","취소","연속"]
[743,"광주전남","순천","율촌화치#2 T/L","율촌-여수산단#1 T/L 정밀점검","율촌-여수산단#1 T/L 정밀점검 총 51기 - 병가선로 휴전신청","2025-10-20 09:00","2025-10-24 18:00","취소","취소","연속"]
[744,"광주전남","직할","덕림평동#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 덕림-평동#1T/L 59~61호[평동-왕곡#2T/L 1~3호(병가)]","2025-10-13 07:00","2025-10-13 18:00","2025-10-13 07:00","2025-10-13 18:00","연속"]
[745,"광주전남","직할","덕림평동#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 덕림-평동#2T/L 59~61호[평동-왕곡#1T/L 1~3호(병가)]","2025-10-14 07:00","2025-10-14 18:00","2025-10-14 07:00","2025-10-14 18:00","연속"]
[746,"광주전남","직할","매월화정#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-10-20 09:00","2025-10-21 18:00","취소","취소","연속"]
[747,"광주전남","직할","매월화정#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-10-22 09:00","2025-10-23 18:00","취소","취소","연속"]
[748,"광주전남","직할","매월화정#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-10-13 09:00","2025-10-14 18:00","취소","취소","연속"]
[749,"광주전남","직할","매월화정#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검","2025-10-15 09:00","2025-10-16 18:00","취소","취소","연속"]
[750,"광주전남","직할","일곡비아#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검 및 상부모선 누기개소 조치","2025-10-13 09:00","2025-10-17 18:00","취소","취소","연속"]
[751,"광주전남","직할","일곡비아#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 정밀점검 및 상부모선 누기 조치","2025-10-20 09:00","2025-10-24 18:00","취소","취소","연속"]
[752,"광주전남","직할","수완S/S 수완열병합 ST CB","2024~2025년 광주전남본부 직할 변전협력회사 공사","수완S/S STG T/L  GIS 보통점검","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[753,"광주전남","직할","왕곡나주#2 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.30(목) 08:00 ~ 18:00 4. 작업구간 :  왕곡-나주#2T/L No.6~14 5. 작업내용 : 정밀점검","2025-10-30 08:00","2025-10-30 18:00","취소","취소","연속"]
[754,"광주전남","직할","왕곡나주#1 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.10.28(화) 08:00 ~ 25.10.29(수) 18:00 4. 작업구간 :  왕곡-나주#1T/L No.1~21 5. 작업내용 : 정밀점검","2025-10-28 08:00","2025-10-29 18:00","취소","취소","연속"]
[755,"광주전남","직할","평동왕곡#2 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 덕림-평동#1T/L 59~61호[평동-왕곡#2T/L 1~3호(병가)]","2025-10-13 07:00","2025-10-13 18:00","2025-10-13 07:00","2025-10-13 18:00","연속"]
[756,"광주전남","직할","평동왕곡#1 T/L","2024-2025 광주전남본부 직할 가공송전협력회사 공사","작업내용 : 수평 추락방지 장치 설치 작업구간 : 덕림-평동#2T/L 59~61호[평동-왕곡#1T/L 1~3호(병가)]","2025-10-14 07:00","2025-10-14 18:00","2025-10-14 07:00","2025-10-14 18:00","연속"]
[757,"광주전남","직할","하남장성#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[758,"광주전남","직할","하남장성#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2025-10-27 09:00","2025-10-27 18:00","취소","취소","연속"]
[759,"광주전남","직할","하남장성#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2025-10-28 09:00","2025-10-28 18:00","취소","취소","연속"]
[760,"광주전남","직할","비아하남#2 T/L"," 첨단분기 지중T/L 건설공사","구간 : (신설)C/T~(신설)첨단S/S~(기설)비아-하남M/H#12 규모 :  XLPE2,000㎟ 2C(D) × 2.2㎞ - 휴전작업 공정 : M/H#12 케이블철거. 토목관로 접속, 케이블 포설 및 접속","2025-10-13 09:00","2025-11-11 18:00","2025-10-20 09:00","2025-11-17 18:00","연속"]
[761,"광주전남","직할","하남장성#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","170kV GIS 보통점검","2025-10-24 09:00","2025-10-24 18:00","2025-10-24 09:00","2025-10-24 18:00","연속"]
[762,"대구","경산","경산S/S #1 EM.Tr CB","2025년 경산전력 GIS 정밀점검공사","GIS 정밀점검공사","2025-10-30 09:00","2025-10-31 18:00","2025-10-30 09:00","2025-10-31 18:00","연속"]
[763,"대구","경산","금호아화#2 T/L","[안전확보] 2025년 가공송전 순시점검 위탁공사","[안전확보]  신경산-금호#1T/L 정밀점검","2025-10-22 07:00","2025-10-24 18:00","2025-10-22 07:00","2025-10-24 18:00","연속"]
[764,"대구","경산","금호아화#1 T/L","[안전확보] 2025년 가공송전 순시점검 위탁공사","[안전확보]  신경산-금호#2T/L 정밀점검","2025-10-15 07:00","2025-10-17 18:00","2025-10-15 07:00","2025-10-17 18:00","연속"]
[765,"대구","경산","신경산노변 T/L","2024-2025년 경산전력지사 송전협력회사 공사"," 신경산-노변T/L No.6, 8, 10 고정형폴리머 설치","2025-10-29 07:00","2025-10-29 18:00","2025-10-29 07:00","2025-10-29 18:00","연속"]
[766,"대구","경산","신경산금호#2 T/L","2025년 가공송전 순시점검 위탁공사"," 신경산-금호#2T/L 정밀점검","2025-10-13 07:00","2025-10-17 18:00","2025-10-13 07:00","2025-10-17 18:00","연속"]
[767,"대구","경산","신경산금호#1 T/L","2025년 가공송전 순시점검 위탁공사"," 신경산-금호#1T/L 정밀점검","2025-10-20 07:00","2025-10-24 18:00","2025-10-20 07:00","2025-10-24 18:00","연속"]
[768,"대구","달성","고령쌍림#1 T/L","고령S/S 고령-쌍림#1T/L CVT 대체","고령S/S 고령-쌍림#1T/L CVT 대체","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[769,"대구","달성","고령서구지#2 T/L","고령S/S 고령-쌍림#1T/L CVT 대체 관련 안전확보휴전","고령S/S 고령-쌍림#1T/L CVT 대체 관련 안전확보휴전","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[770,"대구","달성","고령쌍림#1 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 고령-쌍림 #1T/L (정밀점검,1~63호) 10.13~10.24  고령-쌍림 #1T/L (쌍림-합천 작업관련 안전확보) 10.27","2025-10-13 06:00","2025-10-27 18:00","취소","취소","연속"]
[771,"대구","달성","다사달서 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 왜관-다사 (정밀점검 안전확보)(10/14~10/15)  다사-달서 T/L 정밀점검(10/16~10/21)","2025-10-14 06:00","2025-10-21 18:00","2025-10-14 06:00","2025-10-21 18:00","연속"]
[772,"대구","달성","왜관다사#1 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 왜관-다사 #1T/L 정밀점검(10/13~10/15)  다사-달서(정밀점검 안전확보)(10/16)","2025-10-13 06:00","2025-10-16 18:00","2025-10-13 06:00","2025-10-16 18:00","연속"]
[773,"대구","달성","고령다산#1 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사(안전확보)"," 고령-쌍림 #1T/L 정밀점검 관련 안전확보","2025-10-13 06:00","2025-10-14 18:00","취소","취소","연속"]
[774,"대구","달성","두류봉덕#2 T/L","지중송전 종단접속함(EBG) 가스채취 밸브 설치 공사","○ 지중송전 종단접속함(EBG)내 열화진단을 위한 가스채취 밸브 설치 -  두류-봉덕#2T/L 두류S/S, 봉덕S/S 종단접속함(EBG) 총 6개상","2025-10-22 09:00","2025-10-23 18:00","취소","취소","연속"]
[775,"대구","달성","두류봉덕#1 T/L","지중송전 종단접속함(EBG) 가스채취 밸브 설치 공사","○ 지중송전 종단접속함(EBG)내 열화진단을 위한 가스채취 밸브 설치 -  두류-봉덕#1T/L 두류S/S, 봉덕S/S 종단접속함(EBG) 총 6개상","2025-10-20 09:00","2025-10-21 18:00","취소","취소","연속"]
[776,"대구","달성","대구봉덕#1 T/L","봉덕S/S 대구-봉덕#1T/L GIS 조작시험","봉덕S/S 대구-봉덕#1T/L GIS 조작시험","2025-10-27 09:00","2025-10-27 14:00","2025-10-27 09:00","2025-10-27 14:00","연속"]
[777,"대구","달성","대구봉덕#2 T/L","봉덕S/S 대구-봉덕#2T/L GIS 조작시험","봉덕S/S 대구-봉덕#2T/L GIS 조작시험","2025-10-27 14:00","2025-10-27 18:00","2025-10-27 14:00","2025-10-27 18:00","연속"]
[778,"대구","달성","쌍림합천#2 T/L","쌍림S/S 쌍림-합천#2T/L GIS 조작시험","쌍림S/S 쌍림-합천#2T/L GIS 조작시험","2025-10-27 09:00","2025-10-27 18:00","2025-10-27 09:00","2025-10-27 18:00","연속"]
[779,"대구","달성","쌍림합천#2 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 쌍림-합천 #2T/L (정밀점검,1~22호) 10.27~10.29  쌍림-합천 #2T/L (고령-쌍림#1 작업관련 안전확보) 10.24","2025-10-24 06:00","2025-10-29 18:00","취소","취소","연속"]
[780,"대구","직할","시지효목#2 T/L","효목S/S 시지-효목#2T/L 차단기 동작특성 시험","효목S/S 시지-효목#2T/L 차단기 동작특성 시험","2025-10-23 14:00","2025-10-23 18:00","2025-10-23 14:00","2025-10-23 18:00","연속"]
[781,"대구","직할","시지효목#1 T/L","효목S/S 시지-효목#1T/L 차단기 동작특성 시험","효목S/S 시지-효목#1T/L 차단기 동작특성 시험","2025-10-23 09:00","2025-10-23 14:00","2025-10-23 09:00","2025-10-23 14:00","연속"]
[782,"대구","칠곡","어모김천#2 T/L","2025년 칠곡전력지사 가공송전 순시점검 위탁공사"," 어모-김천#2 정밀점검 - No.1~6","2025-10-22 09:00","2025-10-23 18:00","취소","취소","연속"]
[783,"대구","칠곡","김천금릉#2 T/L","2024~2025년 대구본부 칠곡전력지사 송전협력회사 공사"," 김천-금릉#2T/L 수직, 수평 추락방지장치 설치공사 (No.1~11호)","2025-10-17 07:00","2025-10-17 18:00","2025-10-17 07:00","2025-10-17 18:00","연속"]
[784,"대구","칠곡","김천금릉#1 T/L","2024~2025년 대구본부 칠곡전력지사 송전협력회사 공사"," 김천-금릉#1T/L 수직, 수평 추락방지장치 설치공사 (No.1~11호)","2025-10-16 07:00","2025-10-16 18:00","2025-10-16 07:00","2025-10-16 18:00","연속"]
[785,"대구","칠곡","남구미농소#2 T/L","농소S/S  627 GIS 정밀점검공사 (무부하가압)","농소S/S  627 GIS 정밀점검공사 (무부하가압)","2025-10-02 14:00","2025-10-02 18:00","2025-10-01 14:00","2025-10-01 18:00","연속"]
[786,"대구","칠곡","농소김천#1 T/L","농소S/S  617 GIS 정밀점검공사","농소S/S  617 GIS 정밀점검공사","2025-10-13 09:00","2025-10-14 18:00","2025-10-13 09:00","2025-10-14 18:00","연속"]
[787,"대구","칠곡","북대구구암#1 T/L"," 북대구-구암T/L No.50~51 안전이격확보공사"," 북대구-구암 #1 T/L No.50~51 안전이격확보공사","2025-10-13 07:00","2025-12-12 18:00","2025-10-13 07:00","2025-12-12 18:00","연속"]
[788,"대구","칠곡","북대구구암#2 T/L"," 북대구-구암T/L No.50~51 안전이격확보공사"," 북대구-구암 #2 T/L No.50~51 안전이격확보공사","2025-10-13 07:00","2025-12-12 18:00","2025-10-13 07:00","2025-12-12 18:00","연속"]
[789,"대구","포항","건천천북#2 T/L","2024-2025년 경산전력지사 송전협력회사 공사"," 건천-천북#2T/L No.1~4 피뢰기 설치","2025-10-27 07:00","2025-10-27 18:00","취소","취소","연속"]
[790,"대구","포항","아화건천#1 T/L","2024-2025년 경산전력지사 송전협력회사 공사(안전확보)"," 건천-천북#2T/L No.1~4 피뢰기 설치 안전확보","2025-10-24 07:00","2025-10-27 18:00","취소","취소","연속"]
[791,"대구","포항","아화건천#2 T/L","2024-2025년 경산전력지사 송전협력회사 공사(안전확보)"," 건천-천북#1T/L No.1~4 피뢰기 설치 안전확보","2025-10-28 07:00","2025-10-28 18:00","취소","취소","연속"]
[792,"대구","포항","건천천북#1 T/L","2024-2025년 경산전력지사 송전협력회사 공사"," 건천-천북#1T/L No.1~4 피뢰기 설치","2025-10-28 07:00","2025-10-28 18:00","취소","취소","연속"]
[793,"대구","포항","북포항남포항 T/L"," 영일-입실 등 11개 T/L 피뢰기 설치공사"," 북포항-남포항#1T/L 피뢰기 설치공사","2025-10-02 07:00","2025-10-02 18:00","2025-10-02 07:00","2025-10-02 18:00","연속"]
[794,"대구","포항","서포항흥해#2 T/L"," 영일-입실 등 11개 T/L 피뢰기 설치공사"," 서포항-흥해#2T/L 피뢰기 설치공사","2025-10-01 07:00","2025-10-02 18:00","2025-10-01 07:00","2025-10-02 18:00","연속"]
[795,"대구","포항","신영일청하#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","신영일-청하#2T/L LA, PT 하자점검","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[796,"대구","포항","흥해북포항#1 T/L"," 영일-입실 등 11개 T/L 피뢰기 설치공사"," 흥해-북포항#1T/L 피뢰기 설치공사","2025-10-01 07:00","2025-10-02 18:00","2025-10-01 07:00","2025-10-02 18:00","연속"]
[797,"경북","구미","남인동인동#1 T/L","2025년 구미전력지사  GIS 보통점검 및 정밀점검 공사","- 남인동S/S 6333 GIS 차단부 정밀점검[무부하가압용]","2025-10-22 08:00","2025-10-22 13:00","2025-10-22 08:00","2025-10-22 13:00","연속"]
[798,"경북","구미","청리상주#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 청리-상주T/L 관형지지물 수직/수평 레일 설치공사 No.58, 84","2025-10-27 07:00","2025-10-27 13:00","2025-10-27 07:00","2025-10-27 13:00","연속"]
[799,"경북","구미","상주화동#2 T/L","2025년 구미전력지사  GIS 보통점검 및 정밀점검 공사","- GIS 보통점검","2025-10-02 14:00","2025-10-02 18:00","2025-10-02 14:00","2025-10-02 18:00","연속"]
[800,"경북","구미","상주화동#1 T/L","2025년 구미전력지사  GIS 보통점검 및 정밀점검 공사","- GIS 보통점검","2025-10-02 09:00","2025-10-02 14:00","2025-10-02 09:00","2025-10-02 14:00","연속"]
[801,"경북","구미","청리상주#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 청리-상주T/L 관형지지물 수직/수평 레일 설치공사 No.58, 84","2025-10-27 13:00","2025-10-27 18:00","2025-10-27 13:00","2025-10-27 18:00","연속"]
[802,"경북","구미","남인동인동#1 T/L","2025년 구미전력지사  GIS 보통점검 및 정밀점검 공사","- 인동S/S 60-61 BUS SEC GIS 차단부 정밀점검[무부하가압용]","2025-10-15 08:00","2025-10-15 13:00","2025-10-15 08:00","2025-10-15 13:00","연속"]
[803,"경북","구미","남인동인동#2 T/L","2025년 구미전력지사  GIS 보통점검 및 정밀점검 공사","- 인동S/S 6100 BUS TIE 차단부 정밀점검[무부하가압용]","2025-10-17 14:00","2025-10-17 18:00","2025-10-17 14:00","2025-10-17 18:00","연속"]
[804,"경북","구미","남인동인동#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 남인동-인동T/L 관형지지물 일체형 레일 설치공사","2025-10-31 13:00","2025-10-31 18:00","2025-10-31 13:00","2025-10-31 18:00","연속"]
[805,"경북","구미","남인동인동#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 남인동-인동T/L 관형지지물 일체형 레일 설치공사","2025-10-31 07:00","2025-10-31 13:00","2025-10-31 07:00","2025-10-31 13:00","연속"]
[806,"경북","구미","상주화동#1 T/L","2025년 가공송전 순시점검 위탁공사 (정밀점검)"," 상주-화동#1T/L 정밀점검","2025-10-30 09:00","2025-11-07 18:00","취소","취소","연속"]
[807,"경북","영주","신영주영주#1 T/L"," 신영주-안동 T/L 정밀점검"," 신영주-안동 T/L 정밀점검","2025-10-13 08:00","2025-10-14 17:00","취소","취소","연속"]
[808,"경북","영주","신영주영주#2 T/L"," 신영주-안동 T/L 정밀점검"," 신영주-안동 T/L 정밀점검","2025-10-20 08:00","2025-10-21 17:00","취소","취소","연속"]
[809,"경북","영주","영주S/S #1 EM.Tr CB","2024-25년 영주전력지사 변전협력회사 공사","영주 ESS 성능시험평가","2025-10-13 09:00","2025-10-24 18:00","2025-10-13 09:00","2025-10-24 18:00","연속"]
[810,"경북","영주","예천점촌#2 T/L","2025년 영주전력지사  GIS 정밀점검공사"," GIS 정밀점검 및 무부하가압","2025-10-20 09:00","2025-10-22 18:00","2025-10-20 09:00","2025-10-22 18:00","연속"]
[811,"경북","영주","예천점촌#1 T/L","2025년 영주전력지사  GIS 정밀점검공사"," GIS 정밀점검 및 무부하가압","2025-10-15 14:00","2025-10-17 18:00","2025-10-15 14:00","2025-10-17 18:00","연속"]
[812,"경북","영주","동상주점촌#2 T/L","2025년 영주전력지사  GIS 정밀점검공사"," GIS 정밀점검 후 무부하가압","2025-10-15 09:00","2025-10-15 14:00","2025-10-15 09:00","2025-10-15 14:00","연속"]
[813,"경북","직할","울진현종산풍력 T/L","500kV HVDC 동해안-신가평 송전선로 건설사업(1공구)","No.4~5 발받침철탑 보호망 설치를 위한 휴전 신청","2025-10-22 09:00","2025-10-24 18:00","2025-10-22 09:00","2025-10-24 18:00","연속"]
[814,"경북","직할","봉화울진 T/L","500kV HVDC 동해안-신가평 송전선로 건설사업(1공구)","No.4~5 발받침철탑 보호망 설치를 위한 휴전 신청","2025-10-22 09:00","2025-10-24 18:00","2025-10-22 09:00","2025-10-24 18:00","연속"]
[815,"경북","직할","의성S/S CB 6200","24~25년 경북본부 직할 변전협력회사 공사","GIS 조작시험","2025-10-22 14:00","2025-10-22 18:00","2025-10-22 14:00","2025-10-22 18:00","연속"]
[816,"경북","직할","진보S/S #2 BUS","진보S/S  장기사용 GIS 교체공사(1차수)","진보S/S  장기사용 GIS 교체공사(1차수) -  GIS 3CCT 교체","2025-10-13 09:00","2025-10-25 18:00","2025-10-13 09:00","2025-10-25 13:00","연속"]
[817,"경북","직할","진보S/S CB 6100","진보S/S  장기사용 GIS 교체공사(1차수)","진보S/S  장기사용 GIS 교체공사(1차수) -  GIS 3CCT 교체","2025-10-13 09:00","2025-11-21 18:00","2025-10-13 09:00","2025-11-21 18:00","연속"]
[818,"경북","직할","진보S/S #2 M.Tr CB","진보S/S  장기사용 GIS 교체공사(1차수)","진보S/S  장기사용 GIS 교체공사 -  GIS 3CCT 교체","2025-10-13 09:00","2025-11-21 18:00","2025-10-13 09:00","2025-11-21 18:00","연속"]
[819,"경북","직할","영덕진보#1 T/L","진보S/S  장기사용 GIS 교체공사(1차수)","진보S/S  장기사용 GIS 교체공사(1차수) -  GIS 3CCT 교체","2025-10-13 09:00","2025-11-21 18:00","2025-10-13 09:00","2025-11-21 18:00","연속"]
[820,"경북","직할","진보S/S #1 BUS","진보S/S  장기사용 GIS 교체공사(1차수)","진보S/S  장기사용 GIS 교체공사(1차수) -  GIS 3CCT 교체","2025-10-25 13:00","2025-11-09 13:00","2025-10-25 13:00","2025-11-09 13:00","연속"]
[821,"경북","직할","풍산안동CC#2 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 조작시험","2025-10-22 13:00","2025-10-22 17:00","2025-10-22 13:00","2025-10-22 17:00","연속"]
[822,"경북","직할","풍산동상주개폐소 T/L"," 동상주-풍산T/L 지장이설공사"," 동상주-풍산T/L 기설19~21호 철거 및 임시선로 구성(임시19~임시21)","2025-10-20 07:00","2025-10-28 18:00","2025-10-20 08:00","2025-10-28 18:00","연속"]
[823,"경북","직할","현종산풍력평해#2 T/L","24-25년 경북 직할 송전협력회사 공사","철탑 암 이동용 안전발판 설치공사 현종산풍력-평해#2T/L 39,40,58,59,72,73호","2025-10-13 07:00","2025-10-14 18:00","2025-10-13 07:00","2025-10-14 18:00","연속"]
[824,"경북","직할","현종산풍력평해#1 T/L","24-25년 경북 직할 송전협력회사 공사","철탑 암 이동용 안전발판 설치공사 현종산풍력-평해#1T/L 39,40,58,59,72,73호","2025-10-20 07:00","2025-10-21 18:00","2025-10-20 07:00","2025-10-21 18:00","연속"]
[825,"경북","직할","봉화현종산풍력 T/L","24-25년 경북 직할 송전협력회사 공사","철탑 암 이동용 안전발판 설치공사 봉화-현종산풍력T/L 155,156,160,161,180,181호","2025-10-15 07:00","2025-10-16 18:00","취소","취소","연속"]
[826,"경북","직할","신영주안동#2 T/L"," 안동S/S #4M.Tr 및 모선보강용 GIS 증설공사"," GIS 설치","2025-10-30 09:00","2025-11-12 07:00","2025-10-30 09:00","2025-11-12 07:00","연속"]
[827,"부산울산","동부산","명례장안 T/L","명례S/S #3M.Tr 증설공사","명례S/S #3M.Tr 증설공사(#2BUS 무부하가압)","2025-10-17 14:00","2025-10-18 14:00","2025-10-18 10:00","2025-10-19 10:00","연속"]
[828,"부산울산","동부산","명례장안 T/L","명례S/S #3M.Tr 증설공사","명례S/S #3M.Tr 증설공사(#1BUS 무부하가압)","2025-10-15 10:00","2025-10-16 10:00","2025-10-14 10:00","2025-10-15 10:00","연속"]
[829,"부산울산","동부산","웅촌서창#2 T/L","2025년 가공송전 순시점검 위탁공사"," 웅촌-서창#2T/L 정밀점검","2025-10-21 09:00","2025-10-24 18:00","2025-10-21 09:00","2025-10-24 18:00","연속"]
[830,"부산울산","동부산","웅촌서창#1 T/L","2025년 가공송전 순시점검 위탁공사"," 웅촌-서창#1T/L 정밀점검","2025-10-27 09:00","2025-10-30 18:00","2025-10-27 09:00","2025-10-30 18:00","연속"]
[831,"부산울산","동부산","수영우동 T/L","우동S/S  수영-우동T/L 보호반 대체","우동S/S  수영-우동T/L 보호반 대체","2025-10-10 09:00","2025-10-12 18:00","2025-11-08 09:00","2025-11-09 18:00","연속"]
[832,"부산울산","동부산","우동대연 T/L","2025년 서부산전력지사 가공송전 순시점검 위탁공사","정보T/L 송전선로 정밀점검, 조류착지방지장치 설치","2025-10-19 08:00","2025-10-19 18:00","2025-10-19 08:00","2025-10-19 18:00","연속"]
[833,"부산울산","동부산","노포정관#2 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 서창-산막#1T/L 송전용피뢰기 설치(No.65~72) 안전이격확보","2025-10-26 08:00","2025-10-26 10:00","2025-10-26 08:00","2025-10-26 10:00","연속"]
[834,"부산울산","동부산","정보대연 T/L","2025년 서부산전력지사 가공송전 순시점검 위탁공사","정보T/L 송전선로 정밀점검, 조류착지방지장치 설치","2025-10-18 08:00","2025-10-18 18:00","2025-10-18 08:00","2025-10-18 18:00","연속"]
[835,"부산울산","동부산","좌동S/S #60 BUS","좌동S/S  GIS 교체공사","좌동S/S  GIS 교체공사(617,6133,#1PT)","2025-10-20 09:00","2025-11-07 18:00","2025-10-20 09:00","2025-11-04 18:00","연속"]
[836,"부산울산","동부산","시랑좌동#2 T/L","좌동S/S  GIS 교체공사","좌동S/S  617 GIS 철거 관련 안전이격 휴전","2025-10-18 08:00","2025-10-18 18:00","2025-10-18 08:00","2025-10-18 18:00","연속"]
[837,"부산울산","동부산","시랑좌동#1 T/L","좌동S/S  GIS 교체공사","좌동S/S  GIS 교체공사(617,6133,#1PT)","2025-10-13 09:00","2025-11-27 18:00","2025-10-13 09:00","2025-11-22 18:00","연속"]
[838,"부산울산","북부산","북부산물금 T/L","24-25년 북부산전력지사 가공송전협력회사 공사","압축인류클램프 교체 No.8 폴리머애자 설치 No.1,2","2025-10-31 08:00","2025-10-31 18:00","2025-10-31 08:00","2025-10-31 18:00","연속"]
[839,"부산울산","북부산","석계산막#2 T/L","25 산막S/S  장기사용 GIS 대체공사","산막S/S #3M.Tr 1차 6333GIS 대체 / #2BUS 시험가압선로","2025-10-28 14:00","2025-10-28 15:00","2025-10-28 17:00","2025-10-28 18:00","연속"]
[840,"부산울산","북부산","석계산막#2 T/L","25 산막S/S  장기사용 GIS 대체공사","산막S/S #3M.Tr 1차 6333GIS 대체 / #1BUS 시험가압선로","2025-10-19 18:00","2025-10-20 18:00","2025-10-19 18:00","2025-10-20 18:00","연속"]
[841,"부산울산","북부산","서창산막#1 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 서창-산막#1T/L 송전용피뢰기 설치 : No.25~44","2025-10-18 08:00","2025-10-19 18:00","2025-10-18 08:00","2025-10-19 18:00","연속"]
[842,"부산울산","북부산","석계산막#2 T/L","25 산막S/S  장기사용 GIS 대체공사","산막S/S #3M.Tr 1차 6333GIS 대체 / #2BUS 시험가압선로","2025-10-12 18:00","2025-10-12 19:00","취소","취소","연속"]
[843,"부산울산","북부산","서창산막#1 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 서창-산막#1T/L 송전용피뢰기 설치 : No.45~72","2025-10-25 08:00","2025-10-26 18:00","2025-10-25 08:00","2025-10-26 18:00","연속"]
[844,"부산울산","북부산","물금삼랑진PP#2 T/L","2025년 가공송전선로 순시점검 위탁공사 정밀점검"," 물금-삼랑진 #2T/L 정밀점검 -점검대상 : 총 60기(No.1 ~ 58호 58기 및 S/T 6기)","2025-10-14 07:00","2025-10-16 18:00","2025-10-14 07:00","2025-10-16 18:00","연속"]
[845,"부산울산","북부산","북부산삼랑진PP T/L","2025년 가공송전선로 순시점검 위탁공사 정밀점검"," 북부산-삼랑진T/L 정밀점검 -점검대상 : 총 58기(No.1~10, 37~40, 64 ~ 105호 56기 및 S/T 2기)","2025-10-21 07:00","2025-10-24 18:00","2025-10-21 07:00","2025-10-24 18:00","연속"]
[846,"부산울산","북부산","석계산막#1 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 석계-산막#1T/L 송전용피뢰기 설치 : No.6~29","2025-10-11 08:00","2025-10-12 18:00","취소","취소","연속"]
[847,"부산울산","북부산","언양석계#2 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 언양-석계#2T/L 송전용피뢰기 설치 No.32","2025-10-10 08:00","2025-10-10 18:00","취소","취소","연속"]
[848,"부산울산","북부산","양산산막#2 T/L","25 북부산전력  GIS 정밀점검공사"," 고려제강T/L GIS 정밀점검 시험가압선로","2025-10-08 17:00","2025-10-08 18:00","취소","취소","연속"]
[849,"부산울산","북부산","북부산양산 T/L","25 북부산전력  GIS 정밀점검공사","양산S/S #3M.Tr 1차 GIS 정밀점검 시험가압선로","2025-10-28 15:00","2025-10-28 16:00","2025-10-28 15:00","2025-10-28 16:00","연속"]
[850,"부산울산","북부산","양산산막#2 T/L","25 북부산전력  GIS 정밀점검공사"," 양산산막#2T/L GIS 정밀점검 및 시험가압","2025-10-01 09:00","2025-10-02 18:00","2025-10-01 09:00","2025-10-02 18:00","연속"]
[851,"부산울산","북부산","양산산막#2 T/L","25 북부산전력  GIS 정밀점검공사"," 넥센타이어T/L GIS 정밀점검 시험가압선로","2025-10-08 16:00","2025-10-08 17:00","취소","취소","연속"]
[852,"부산울산","북부산","북부산양산 T/L","24-25년 북부산전력지사 가공송전협력회사 공사","압축인류클램프 교체 No.46.99","2025-10-27 08:00","2025-10-27 18:00","2025-10-27 08:00","2025-10-27 18:00","연속"]
[853,"부산울산","북부산","양산산막#2 T/L","25 북부산전력  GIS 정밀점검공사","양산S/S #2M.Tr 1차 GIS 정밀점검 시험가압선로","2025-10-26 18:00","2025-10-26 19:00","취소","취소","연속"]
[854,"부산울산","북부산","북부산양산 T/L","25 북부산전력  GIS 정밀점검공사","양산S/S #4M.Tr 1차 GIS 정밀점검 시험가압선로","2025-10-30 18:00","2025-10-30 19:00","2025-10-30 18:00","2025-10-30 19:00","연속"]
[855,"부산울산","북부산","양산삼랑진PP T/L","24-25년 북부산전력지사 가공송전협력회사 공사","압축인류클램프 교체 No.6,12 폴리머애자 설치 No.1 SB댐퍼 설치 No.0.01","2025-10-29 08:00","2025-10-30 18:00","2025-10-29 08:00","2025-10-30 18:00","연속"]
[856,"부산울산","북부산","엄궁학장#1 T/L","'24-25 북부산전력 변전협력총액공사","엄궁학장#1TL GIS 보통점검 (법정 정기검사)","2025-10-01 09:00","2025-10-01 18:00","2025-10-01 09:00","2025-10-01 18:00","연속"]
[857,"부산울산","북부산","엄궁학장#2 T/L","'24-25 북부산전력 변전협력총액공사","엄궁학장#2TL GIS 보통점검 (법정 정기검사)","2025-10-02 09:00","2025-10-02 18:00","2025-10-02 09:00","2025-10-02 18:00","연속"]
[858,"부산울산","북부산","호포물금 T/L","24-25년 북부산전력지사 가공송전협력회사 공사","압축인류클램프 교체 No.3","2025-10-28 07:00","2025-10-28 14:00","취소","취소","연속"]
[859,"부산울산","북부산","북부산호포 T/L","24-25년 북부산전력지사 가공송전협력회사 공사","압축인류클램프 교체 No.3","2025-10-13 08:00","2025-10-13 18:00","취소","취소","연속"]
[860,"부산울산","서부산","지사미음#2 T/L"," 세산S/S 건설공사 및 세산분기 지중T/L 건설공사","지사-미음#2T/L 분기선로 신설(지사-세산#2T/L, 세산-미음#2T/L) 신설","2025-10-27 09:00","2025-11-26 18:00","2025-10-27 09:00","2025-11-26 18:00","연속"]
[861,"부산울산","울산","남울산성암#1 T/L","'24~'25년 울산전력 개폐장치 정밀점검 공사","한주#1T/L GIS 정밀점검 시험가압","2025-10-28 17:00","2025-10-28 18:00","2025-10-28 17:00","2025-10-28 18:00","연속"]
[862,"부산울산","울산","남울산성암#2 T/L","'24~'25년 울산전력 개폐장치 정밀점검 공사","한주#2T/L GIS 정밀점검 시험가압","2025-10-30 17:00","2025-10-30 18:00","2025-10-30 17:00","2025-10-30 18:00","연속"]
[863,"부산울산","울산","성암울산TP#1 T/L","'24~'25년 울산전력 변전협력회사 총액공사","양단 송전선로 보호배전반 대체","2025-10-27 09:00","2025-10-29 18:00","2025-10-27 09:00","2025-10-29 18:00","연속"]
[864,"부산울산","울산","남울산신온산#1 T/L","2025년 가공송전 순시점검 위탁공사(울산)","송전선로 초기점검 -  남울산-신온산#1T/L S/T~4호 - 고객사(한주#1T/L) 병가선로 및 병행작업 시행","2025-10-27 07:00","2025-10-29 18:00","2025-10-27 07:00","2025-10-29 18:00","연속"]
[865,"부산울산","울산","신울산웅촌#2 T/L","2025년 가공송전 순시점검 위탁공사"," 웅촌-서창#2T/L 정밀점검 안전이격","2025-10-21 09:00","2025-10-22 18:00","2025-10-21 09:00","2025-10-22 18:00","연속"]
[866,"부산울산","울산","신울산웅촌#1 T/L","2025년 가공송전 순시점검 위탁공사"," 웅촌-서창#1T/L 정밀점검 안전이격","2025-10-27 09:00","2025-10-28 18:00","2025-10-27 09:00","2025-10-28 18:00","연속"]
[867,"부산울산","울산","신울산언양#2 T/L"," 추락방지장치(수평) 및 폴리머지지애자 설치공사","ㅇ 추락방지장치(수평) 설치 1기 (No.44) ㅇ 폴리머지지애자 설치 21(No.1, 2, 7, 9, 14, 15, 16, 18, 27, 31, 34, 36, 38, 41, 44, 49, 56, 59, 64, 66, 66-1)","2025-10-10 07:00","2025-10-15 18:00","취소","취소","연속"]
[868,"부산울산","울산","반천언양#2 T/L","24-25년 북부산전력지사 가공송전협력회사 공사","애자련 교체 안전이격확보휴전","2025-10-17 08:00","2025-10-17 18:00","2025-10-17 08:00","2025-10-17 18:00","연속"]
[869,"부산울산","울산","울산영남TP#1 T/L","'24~'25년 울산전력 개폐장치 정밀점검 공사","양단 GIS 보통점검","2025-10-20 09:00","2025-10-21 18:00","2025-10-20 09:00","2025-10-21 18:00","연속"]
[870,"부산울산","울산","울산영남TP#2 T/L","'24~'25년 울산전력 개폐장치 정밀점검 공사","GIS 보통점검","2025-10-16 09:00","2025-10-16 18:00","2025-10-16 09:00","2025-10-16 18:00","연속"]
[871,"부산울산","울산","옥동외동#1 T/L"," 추락방지장치(수평) 및 폴리머지지애자 설치공사","총 53기 ●병가구간( 울주-외동 #2T/L 병가) 28기 폴리머 + 수평 7기[38, 43, 46, 49, 50 ,56, 61] 수평 21기[35~62] ●단독선로 25기 폴리머 + 수평 7기[3, 10, 13, 26, 28, 30, 32] 수평 18기[2, 4, 5, 8, 9, 11, 12, 20, 21~25, 27, 29, 31, 33, 34]","2025-10-30 07:00","2025-11-21 18:00","2025-10-30 07:00","2025-11-21 18:00","연속"]
[872,"부산울산","울산","옥동외동#2 T/L"," 폴리머지지애자 설치공사","폴리머지지애자 설치 총 7기(병가 7기, 단독 7기) ㅇ 병가구간 7기 ( 외동-옥동 #2T/L No.37, 40, 44, 46, 54, 59, 60) [ 울주-외동 #1T/L No.18, 21, 25, 27, 35, 40, 41 병가] ㅇ 단일선로 7기 [ 외동-옥동 #2 No.3, 10, 13, 22, 26, 28, 30]","2025-10-21 07:00","2025-10-24 18:00","2025-10-21 07:00","2025-10-24 18:00","연속"]
[873,"부산울산","울산","신온산온산#3 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-10-16 09:00","2025-11-07 18:00","2025-10-16 09:00","2025-11-07 18:00","연속"]
[874,"부산울산","울산","신온산온산#2 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-10-17 09:00","2025-10-17 18:00","2025-10-17 09:00","2025-10-17 18:00","연속"]
[875,"부산울산","울산","신온산온산#2 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-10-24 09:00","2025-10-25 18:00","2025-10-24 09:00","2025-10-25 18:00","연속"]
[876,"부산울산","울산","신온산온산#2 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-10-31 09:00","2025-11-01 18:00","2025-10-31 09:00","2025-11-01 18:00","연속"]
[877,"부산울산","울산","울주입실#2 T/L","345kV 울주S/S 장기사용 GIS 교체공사","집감반 실규설치 관련 697 Bay 결선 및 시험작업","2025-10-02 08:00","2025-10-02 18:00","취소","취소","연속"]
[878,"부산울산","울산","울주외동#2 T/L"," 추락방지장치(수평) 및 폴리머지지애자 설치공사","총 36기 폴리머지지애자 8기 설치(2, 3, 6~8, 11, 13, 14) 폴리머지지애자 + 수평추락방지장치 7기 설치(19, 24, 27, 30, 31, 37, 42) 수평추락방지장치 21기(16~18, 20~23, 25~26, 28~29, 32~36, 38~41, 43)","2025-10-27 07:00","2025-11-11 18:00","2025-10-27 07:00","2025-11-11 18:00","연속"]
[879,"부산울산","울산","울주입실#2 T/L"," 추락방지장치(수평) 및 폴리머지지애자 설치공사(안전이격)"," 울주-외동 #2T/L 추락방지장치(수평) 및 폴리머지지애자 설치공사 안전이격  울주-입실 #2T/L 2, 3호 [ 울주-외동 #2T/L 2, 3호 병가구간]","2025-10-27 07:00","2025-10-27 18:00","취소","취소","연속"]
[880,"부산울산","울산","울주직동#2 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 및 금구류 설치","2025-10-17 07:00","2025-10-22 18:00","취소","취소","연속"]
[881,"부산울산","울산","울주외동#1 T/L"," 폴리머지지애자 설치공사","-폴리머지지애자 설치 13기(병가 7기) / 4호는 병가이나 울주-외동#1에만 설치 [4, 6, 7, 8, 10, 13, 18, 21, 25, 27, 35, 40, 41]","2025-10-16 07:00","2025-10-22 18:00","2025-10-16 07:00","2025-10-22 18:00","연속"]
[882,"부산울산","울산","울주입실#1 T/L"," 폴리머지지애자 설치공사(안전이격확보)"," 울주-외동 #1T/L 폴리머지지애자 설치 -25.10.16 : 4호 병가선로(울주-입실 #1T/L) 안전이격 확보차","2025-10-16 07:00","2025-10-16 18:00","취소","취소","연속"]
[883,"부산울산","울산","울주직동#1 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 및 금구류 설치","2025-10-14 07:00","2025-10-16 18:00","2025-10-14 07:00","2025-10-16 18:00","연속"]
[884,"부산울산","울산","울주입실#1 T/L","345kV 울주S/S 장기사용 GIS 교체공사","집감반 실규설치 관련 6A7 Bay 결선 및 시험작업","2025-10-01 08:00","2025-10-01 18:00","취소","취소","연속"]
[885,"부산울산","울산","직동반천#2 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 설치","2025-10-29 07:00","2025-10-29 18:00","2025-10-29 12:00","2025-10-29 18:00","연속"]
[886,"부산울산","울산","직동반천#1 T/L","동부산전력 가공송전협력회사 공사","추락방지장치 설치","2025-10-28 07:00","2025-10-28 18:00","2025-10-29 07:00","2025-10-29 12:00","연속"]
[887,"부산울산","직할","신대연양정#1 T/L","24-25년 직할 변전협력회사공사","신대연S/S 신대연-양정#1T/L 보호반 대체","2025-10-13 09:00","2025-10-15 18:00","2025-10-13 09:00","2025-10-15 18:00","연속"]
[888,"부산울산","직할","명장연산#1 T/L","24~25년 직할 변전협력회사 총액공사","연산S/S 명장-연산#1T/L GIS CT TANK 교체공사","2025-10-13 09:00","2025-11-03 18:00","2025-10-13 09:00","2025-11-03 18:00","연속"]
[889,"경남","직할","안민천선#2 T/L","24~25년 경남본부 직할 송전협력회사 공사"," 안민-천선#2T/L 폴리머점퍼지지애자 설치 - 18호","2025-10-01 07:00","2025-10-01 18:00","2025-10-01 07:00","2025-10-01 18:00","연속"]
[890,"경남","진주","개양S/S CB 6100","개양S/S #60-65 BUS-TIE GIS 보통점검","개양S/S #60-65 BUS-TIE GIS 보통점검","2025-10-02 10:00","2025-10-02 14:00","2025-10-02 10:00","2025-10-02 14:00","연속"]
[891,"경남","통영","고성통영CC#1 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성분기T/L 추락방지장치 설치공사","2025-10-09 07:00","2025-10-10 18:00","취소","취소","매일"]
[892,"경남","통영","신고성고성 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성분기T/L 추락방지장치 설치공사","2025-10-09 07:00","2025-10-10 18:00","취소","취소","매일"]
[893,"경남","진주","정촌S/S CB 6500","정촌S/S 하동-정촌#2T/L 61DS 조치작업","정촌S/S 하동-정촌#2T/L 61DS 조치작업 [병행] 하동S/S 하동-정촌#2T/L GIS 보통점검 및 LA,PT 보통(10/10) [병행] 정촌S/S 6571,6500 GIS 초기점검(10/13)","2025-10-10 09:00","2025-10-13 18:00","2025-10-10 09:00","2025-10-13 18:00","연속"]
[894,"경남","진주","정촌S/S CB 6571","정촌S/S 하동-정촌#2T/L 61DS 조치작업","정촌S/S 하동-정촌#2T/L 61DS 조치작업 [병행] 하동S/S 하동-정촌#2T/L GIS 보통점검 및 LA,PT 보통(10/10) [병행] 정촌S/S 6571,6500 GIS 초기점검(10/13)","2025-10-10 09:00","2025-10-13 18:00","2025-10-10 09:00","2025-10-13 18:00","연속"]
[895,"경남","통영","고성통영CC#2 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성분기T/L 추락방지장치 설치공사","2025-10-11 07:00","2025-10-12 18:00","2025-10-11 07:00","2025-10-12 18:00","매일"]
[896,"경남","통영","고성거류 T/L"," 고성분기T/L 추락방지장치 설치공사"," 고성분기T/L 추락방지장치 설치공사","2025-10-11 07:00","2025-10-11 18:00","2025-10-11 07:00","2025-10-11 18:00","연속"]
[897,"경남","김해송변전부","신김해주촌#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#1 T/L 성능저하 지지애자 교체","2025-10-12 08:00","2025-10-12 13:00","2025-10-12 08:00","2025-10-12 13:00","연속"]
[898,"경남","김해송변전부","신김해주촌#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌T/L 성능저하 지지애자 교체","2025-10-12 13:00","2025-10-12 18:00","2025-10-12 13:00","2025-10-12 18:00","연속"]
[899,"경남","진주","사봉개양#1 T/L"," 사봉-개양 #1T/L 폴리머지지애자 신규설치"," 사봉-개양 #1T/L 폴리머지지애자 신규설치 (매일) -10기 설치","2025-10-13 07:00","2025-10-14 18:00","취소","취소","매일"]
[900,"경남","진주","가야사봉#2 T/L"," 사봉-개양 #1T/L 폴리머지지애자 신규설치"," 사봉-개양 #1T/L 폴리머지지애자 신규설치 (매일) -10기 설치 - 가야-사봉#2T/L No. 49~44 병가","2025-10-13 07:00","2025-10-14 18:00","취소","취소","매일"]
[901,"경남","함안","창녕초동#2 T/L"," 창녕-구지#1T/L 폴리머 점퍼지지애자 설치공사(안전이격거리)"," 창녕-구지#1T/L 고정형 폴리머 점퍼지지애자 설치[7호(1기) 시 4회선 병가철탑(수직배열)으로 동시휴전 필요","2025-10-13 07:00","2025-10-13 18:00","2025-10-13 07:00","2025-10-13 18:00","연속"]
[902,"경남","직할","창공월림#2 T/L","월림S/S  장기사용 대체공사(이격거리)","월림S/S  장기사용 대체공사(이격거리)","2025-10-13 08:00","2025-10-28 18:00","2025-10-13 08:00","2025-10-28 18:00","연속"]
[903,"경남","직할","창공월림#1 T/L","월림S/S  장기사용 대체공사(이격거리)","월림S/S  장기사용 대체공사(이격거리)","2025-10-13 08:00","2025-10-28 18:00","2025-10-13 08:00","2025-10-28 18:00","연속"]
[904,"경남","김해송변전부","주촌삼계#2 T/L","삼계S/S 주촌-삼계#2T/L GIS 보통점검","삼계S/S 주촌-삼계#2T/L GIS 보통점검","2025-10-13 09:00","2025-10-13 18:00","2025-10-13 09:00","2025-10-13 18:00","연속"]
[905,"경남","함안","창녕초동#1 T/L"," 창녕-초동#1T/L 정밀정검"," 창녕-초동#1T/L 정밀정검 1~56호 정밀점검(56기)","2025-10-14 08:00","2025-10-20 18:00","2025-10-14 08:00","2025-10-20 18:00","매일"]
[906,"경남","진주","광양하동#1 T/L","하동S/S 광양-하동#1T/L LA 초기, PT 하자점검","하동S/S 광양-하동#1T/L LA 초기, PT 하자점검","2025-10-14 10:00","2025-10-14 14:00","취소","취소","연속"]
[907,"경남","진주","광양하동#2 T/L","하동S/S 광양-하동#2T/L LA 초기, PT 하자점검","하동S/S 광양-하동#2T/L LA 초기, PT 하자점검","2025-10-14 14:00","2025-10-14 17:00","취소","취소","연속"]
[908,"경남","진주","하동하동화력 T/L","하동S/S 하동-하동화력T/L PT 초기점검","하동S/S 하동-하동화력T/L PT 초기점검","2025-10-14 17:00","2025-10-14 18:00","취소","취소","연속"]
[909,"경남","진주","가야사봉#1 T/L"," 사봉-개양 #2T/L 폴리머지지애자 신규설치"," 사봉-개양 #2T/L 폴리머지지애자 신규설치 (매일) -13기 설치 - 가야-사봉#1T/L 병가 - 진주-개양#1T/L 병가","2025-10-15 07:00","2025-10-15 18:00","취소","취소","매일"]
[910,"경남","진주","사봉개양#2 T/L"," 사봉-개양 #2T/L 폴리머지지애자 신규설치"," 사봉-개양 #2T/L 폴리머지지애자 신규설치 (매일) -13기 설치 - 가야-사봉#1T/L 병가","2025-10-15 07:00","2025-10-16 18:00","취소","취소","매일"]
[911,"경남","직할","안민천선#2 T/L","24~25년 경남본부 직할 송전협력회사 공사"," 안민-천선#2T/L 폴리머점퍼지지애자 설치 - 3,12,14호","2025-10-15 07:00","2025-10-15 18:00","2025-10-15 07:00","2025-10-15 18:00","연속"]
[912,"경남","진주","정촌S/S CB 6371","정촌S/S 정촌-개양#1T/L(6371) GIS 초기점검","정촌S/S 정촌-개양#1T/L(6371) GIS 초기점검","2025-10-15 10:00","2025-10-15 14:00","취소","취소","연속"]
[913,"경남","진주","정촌S/S CB 6300","정촌S/S 정촌-개양#1T/L-TIE(6300) GIS 초기점검","정촌S/S 정촌-개양#1T/L-TIE(6300) GIS 초기점검","2025-10-15 14:00","2025-10-15 17:00","취소","취소","연속"]
[914,"경남","직할","안민천선#1 T/L","24~25년 경남본부 직할 송전협력회사 공사"," 안민-천선#1T/L 폴리머점퍼지지애자 설치 - 2,5,16호","2025-10-16 07:00","2025-10-17 18:00","2025-10-16 07:00","2025-10-17 18:00","매일"]
[915,"경남","진주","진주개양#1 T/L"," 사봉-개양 #2T/L 폴리머지지애자 신규설치"," 사봉-개양 #2T/L 폴리머지지애자 신규설치 (매일) -13기 설치 - 가야-사봉#1T/L 병가 - 진주-개양#1T/L 병가","2025-10-16 07:00","2025-10-16 18:00","취소","취소","매일"]
[916,"경남","함안","가야사봉#1 T/L","가야S/S 가야-사봉#1T/L 피뢰기 대체작업","가야S/S  가야-사봉#1T/L 피뢰기 대체작업","2025-10-17 09:30","2025-10-17 13:30","취소","취소","연속"]
[917,"경남","진주","합천합천수력#1 T/L","합천S/S 합천수력#1,2T/L GIS 조작시험 및 PT 하자점검","합천S/S 합천수력#1,2T/L GIS 조작시험 및 PT 하자점검","2025-10-17 10:00","2025-10-17 12:00","2025-10-17 10:00","2025-10-17 12:00","연속"]
[918,"경남","진주","합천합천수력#2 T/L","합천S/S 합천수력#1,2T/L GIS 조작시험 및 PT 하자점검","합천S/S 합천수력#1,2T/L GIS 조작시험 및 PT 하자점검","2025-10-17 12:00","2025-10-17 15:00","2025-10-17 12:00","2025-10-17 15:00","연속"]
[919,"경남","함안","가야사봉#2 T/L","가야S/S 가야-사봉#2T/L 피뢰기 대체작업","가야S/S  가야-사봉#2T/L 피뢰기 대체작업","2025-10-17 13:30","2025-10-17 17:30","취소","취소","연속"]
[920,"경남","직할","신월동읍#1 T/L"," 신월-동읍#1T/L 지중케이블 절연유 채유"," 신월-동읍#1T/L 지중케이블 절연유 채유","2025-10-18 09:00","2025-10-18 12:00","2025-10-18 09:00","2025-10-18 12:00","연속"]
[921,"경남","직할","신월삼정#1 T/L"," 신월-삼정#1T/L 지중케이블 절연유 채유"," 신월-삼정#1T/L 지중케이블 절연유 채유","2025-10-18 09:00","2025-10-18 12:00","2025-10-18 09:00","2025-10-18 12:00","연속"]
[922,"경남","진주","진주개양#2 T/L","진주S/S 진주-개양#2T/L CB 메커니즘 교체","진주S/S 진주-개양#2T/L CB 메커니즘 교체","2025-10-18 10:00","2025-10-18 15:00","취소","취소","연속"]
[923,"경남","직할","신월동읍#2 T/L"," 신월-동읍#2T/L 지중케이블 절연유 채유"," 신월-동읍#2T/L 지중케이블 절연유 채유","2025-10-18 12:00","2025-10-18 18:00","2025-10-18 12:00","2025-10-18 18:00","연속"]
[924,"경남","직할","신월삼정#2 T/L"," 신월-삼정#2T/L 지중케이블 절연유 채유"," 신월-삼정#2T/L 지중케이블 절연유 채유","2025-10-18 12:00","2025-10-18 18:00","2025-10-18 12:00","2025-10-18 18:00","연속"]
[925,"경남","진주","의령동진주#2 T/L"," 의령-동진주 #2T/L 폴리머지지애자 신규설치"," 의령-동진주 #2T/L 폴리머지지애자 신규설치 (매일) -12기 설치 - 의령-산청1T/L 병가","2025-10-20 07:00","2025-10-21 18:00","취소","취소","매일"]
[926,"경남","통영","신고성거류#3 T/L"," 신고성-거류#3 T/L추락방지장치 설치공사"," 신고성-거류#3 T/L 추락방지장치 설치공사","2025-10-20 07:00","2025-10-26 18:00","취소","취소","매일"]
[927,"경남","김해송변전부","신김해지사#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 장유-마천T/L 성능저하 지지애자교체 안전이격","2025-10-20 08:00","2025-10-21 18:00","2025-10-20 08:00","2025-10-21 18:00","매일"]
[928,"경남","함안","초동밀양#2 T/L"," 창녕-초동#1T/L 정밀정검 안전거리 확보"," 창녕-초동#1T/L 정밀정검 1~56호 정밀점검(56기) 안전거리 확보","2025-10-20 08:00","2025-10-20 18:00","2025-10-20 08:00","2025-10-20 18:00","연속"]
[929,"경남","진주","하동S/S #60 BUS","하동S/S  GIS 6100B/T 설치","하동S/S  GIS 6100B/T 설치","2025-10-20 09:00","2025-10-26 18:00","2025-10-20 09:00","2025-10-26 18:00","연속"]
[930,"경남","진주","의령산청 T/L"," 의령-동진주 #2T/L 폴리머지지애자 신규설치"," 의령-동진주 #2T/L 폴리머지지애자 신규설치 (매일) -12기 설치 - 의령-산청1T/L 병가","2025-10-21 07:00","2025-10-21 18:00","취소","취소","매일"]
[931,"경남","함안","진영수산#2 T/L","항공장애구 설치공사","동읍-진영T/L 19~20호 구간(2조 9개 설치) - 적색 5EA","2025-10-21 07:00","2025-10-21 12:00","2025-10-21 07:00","2025-10-21 12:00","연속"]
[932,"경남","함안","창녕초동#2 T/L"," 창녕-초동#2T/L 정밀정검"," 창녕-초동#2T/L 정밀정검 1~56호 정밀점검(56기)","2025-10-21 08:00","2025-10-28 18:00","2025-10-21 08:00","2025-10-28 18:00","매일"]
[933,"경남","함안","진영수산#1 T/L","항공장애구 설치공사","동읍-진영T/L 19~20호 구간(2조 9개 설치) - 백색 4EA","2025-10-21 12:00","2025-10-21 18:00","2025-10-21 12:00","2025-10-21 18:00","연속"]
[934,"경남","진주","의령동진주#1 T/L"," 의령-동진주 #1T/L 폴리머지지애자 신규설치"," 의령-동진주 #1T/L 폴리머지지애자 신규설치 (매일) -11기 설치 - 의령-함양1T/L 병가","2025-10-22 07:00","2025-10-23 18:00","취소","취소","매일"]
[935,"경남","함안","신마산마산#1 T/L","항공장애구 설치공사","신마산-마산T/L 4~5호 구간(2조 9개 설치) - 적색 5EA","2025-10-23 07:00","2025-10-23 12:00","취소","취소","연속"]
[936,"경남","진주","의령함양 T/L"," 의령-동진주 #1T/L 폴리머지지애자 신규설치"," 의령-동진주 #1T/L 폴리머지지애자 신규설치 (매일) -11기 설치 - 의령-함양1T/L 병가 - 10.31 피뢰기 및 조류착지방지장치 설치작업 시행","2025-10-23 07:00","2025-10-24 18:00","취소","취소","매일"]
[937,"경남","함안","신마산마산#2 T/L","항공장애구 설치공사","신마산-마산T/L 4~5호 구간(2조 9개 설치) - 적색 5EA","2025-10-23 07:00","2025-10-23 12:00","취소","취소","연속"]
[938,"경남","함안","신마산중리#1 T/L","항공장애구 설치공사","신마산-마산T/L 4~5호 구간(2조 9개 설치) - 백색 4EA","2025-10-23 12:00","2025-10-23 18:00","취소","취소","연속"]
[939,"경남","함안","신마산중리#2 T/L","항공장애구 설치공사","신마산-마산T/L 4~5호 구간(2조 9개 설치) - 백색 4EA","2025-10-23 12:00","2025-10-23 18:00","취소","취소","연속"]
[940,"경남","김해송변전부","신김해지사#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 장유-마천T/L 성능저하 지지애자교체 안전이격","2025-10-24 08:00","2025-10-27 18:00","취소","취소","매일"]
[941,"경남","김해송변전부","진영한림정#2 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사"," 한림정-삼계#1T/L 피뢰기 설치 공사(1~5호) 안전거리확보","2025-10-25 08:00","2025-10-25 18:00","2025-10-25 08:00","2025-10-25 18:00","연속"]
[942,"경남","김해송변전부","한림정삼계#1 T/L","2024-2025년 경남본부 함안전력지사 가공송전협력회사 총액공사"," 한림정-삼계#1T/L 피뢰기 설치 공사(1~10호)","2025-10-25 08:00","2025-10-26 18:00","2025-10-25 08:00","2025-10-26 18:00","매일"]
[943,"경남","통영","거류통영#1 T/L","거류개폐소  거류-통영 #1T/L GIS 초기점검 등","거류개폐소  거류-통영 #1T/L GIS 초기점검 통영SS  거류-통영 #1T/L GIS 보통점검","2025-10-25 09:30","2025-10-25 18:00","2025-10-25 09:30","2025-10-25 18:00","연속"]
[944,"경남","통영","거류통영#2 T/L","거류개폐소  거류-통영 #2T/L GIS 초기점검 등","거류개폐소  거류-통영 #2T/L GIS 초기점검 통영SS  거류-통영 #2T/L GIS 보통점검","2025-10-26 09:30","2025-10-26 18:00","2025-10-26 09:30","2025-10-26 18:00","연속"]
[945,"경남","함안","중리가야#1 T/L"," 중리-가야#1T/L 피뢰기 설치공사"," 중리-가야#1T/L 40~51호(8기) 피뢰기 설치","2025-10-27 07:00","2025-10-28 18:00","취소","취소","매일"]
[946,"경남","통영","신고성고성 T/L"," 신고성고성 T/L추락방지장치 설치공사"," 신고성고성 T/L추락방지장치 설치공사","2025-10-27 07:00","2025-11-02 18:00","2025-10-27 07:00","2025-11-02 18:00","매일"]
[947,"경남","함안","신마산중리#2 T/L"," 신마산-중리#2T/L 피뢰기 설치공사"," 신마산-중리#2T/L 1,24~32호(10기) 피뢰기 설치","2025-10-27 07:00","2025-10-27 18:00","취소","취소","연속"]
[948,"경남","김해송변전부","한림정S/S #60 BUS"," 한림정 #4M.Tr 증설공사(모선구분 병행)","-  모선구분, #4M.Tr 증설 및 관련 154, 23kV GIS 증설 각 1식","2025-10-27 09:00","2025-11-02 18:00","취소","취소","연속"]
[949,"경남","진주","의령S/S #1 EM.Tr CB","2025년 의령S/S ESS 정기검사","2025년 의령S/S ESS 정기검사","2025-10-27 09:00","2025-11-07 18:00","2025-10-27 09:00","2025-11-07 18:00","연속"]
[950,"경남","진주","하동S/S #65 BUS","하동S/S  GIS 6100B/T 설치","하동S/S  GIS 6100B/T 설치","2025-10-27 09:00","2025-11-01 18:00","2025-10-27 09:00","2025-11-01 18:00","연속"]
[951,"경남","진주"," 정촌S/S CB 6671","정촌S/S 정촌-개양#2T/L(6671) GIS 초기점검","정촌S/S 정촌-개양#2T/L(6671) GIS 초기점검","2025-10-27 10:00","2025-10-27 14:00","취소","취소","연속"]
[952,"경남","진주"," 정촌S/S CB 6600","정촌S/S 정촌-개양#2T/L TIE(6600) GIS 초기점검","정촌S/S 정촌-개양#2T/L TIE(6600) GIS 초기점검","2025-10-27 14:00","2025-10-27 17:00","취소","취소","연속"]
[953,"경남","함안","중리가야#2 T/L"," 중리-가야#1T/L 피뢰기 설치공사(안전이격거리확보)"," 중리-가야#1T/L 40~51호 피뢰기 설치 시 4회선 병가철탑(수직배열)으로 동시휴전 필요","2025-10-28 07:00","2025-10-28 18:00","취소","취소","연속"]
[954,"경남","함안","초동밀양#1 T/L"," 창녕-초동#2T/L 정밀정검 안전거리 확보"," 창녕-초동#2T/L 정밀정검 1~56호 정밀점검(56기) 안전거리 확보","2025-10-28 08:00","2025-10-28 18:00","2025-10-28 08:00","2025-10-28 18:00","연속"]
[955,"경남","진주","정촌S/S CB 6471","정촌S/S 하동-정촌#1T/L(6471) GIS 초기점검","정촌S/S 하동-정촌#1T/L(6471) GIS 초기점검","2025-10-28 10:00","2025-10-28 14:00","취소","취소","연속"]
[956,"경남","진주","정촌S/S CB 6400","정촌S/S 하동-정촌#1T/L-#2M TIE(6400) GIS 초기점검","정촌S/S 하동-정촌#1T/L-#2M TIE(6400) GIS 초기점검","2025-10-28 14:00","2025-10-28 17:00","취소","취소","연속"]
[957,"경남","직할","신월삼정#1 T/L"," 삼정S/S 창원IDC클리스터T/L 신규수용공사(시험가압)"," 삼정S/S 창원IDC클리스터T/L 신규수용공사","2025-10-30 13:00","2025-10-31 18:00","취소","취소","연속"]
[958,"경남","김해송변전부","신김해지사#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해-지사T/L 성능저하 지지애자 교체","2025-10-31 08:00","2025-10-31 13:00","취소","취소","연속"]
[959,"경남","통영","사천S/S #1 Sh.C CB","사천S/S  #2 Sh.C GCB 등 보통점검","사천S/S  #2 Sh.C GCB, 공기압축기, SR A~C상 보통점검","2025-10-31 09:30","2025-10-31 18:00","2025-10-31 09:30","2025-10-31 18:00","연속"]