{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":21,"n_cols":12,"rows_kept":21,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 11월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기북부","구리","신가평S/S #2 M.Tr"," #2M.Tr 보통점검"," #2M.Tr 보통점검 (6TANK), 3차 케이블 교체","2025-11-17 09:00","2025-12-05 18:00","취소","취소","연속"]
[2,"경기","성남","신안성S/S #2 M.Tr","2025년 성남전력 변전협력회사 총액공사","m.tr 보호반대체 rcp pnl 대체 85bay b/f 대체","2025-11-24 09:00","2025-12-26 18:00","2025-11-24 09:00","2025-12-26 18:00","연속"]
[3,"충북","직할","신중부신안성#2 T/L","24~25 충북직할 가공송전 협력회사 총액공사","풍소음 항공장애표시구 교체","2025-11-21 07:00","2025-11-21 18:00","2025-11-21 07:00","2025-11-21 18:00","연속"]
[4,"충북","직할","신중부S/S #3 M.Tr","신중부S/S  #3M.Tr 보호배전반 성능개선","신중부S/S  #3M.Tr 보호배전반 성능개선","2025-11-24 10:00","2025-11-25 18:00","2025-11-24 10:00","2025-11-25 18:00","연속"]
[5,"충북","직할","신중부신안성#1 T/L","24~25 충북직할 가공송전 협력회사 총액공사","풍소음 항공장애표시구 교체","2025-11-20 07:00","2025-11-20 18:00","2025-11-20 07:00","2025-11-20 18:00","연속"]
[6,"경북","영주","신한울N/P #2 M.Tr","#2M.Tr 불량조치","○ 220V 역가압 관련 회로개선","2025-11-05 09:00","2025-11-06 18:00","2025-11-12 09:00","2025-11-13 18:00","연속"]
[7,"경북","영주","신한울N/P #1 M.Tr","24~25년 영주전력지사 변전협력회사공사","○ 권선온도계 불량 조치","2025-11-03 09:00","2025-11-04 18:00","2025-11-10 09:00","2025-11-11 18:00","연속"]
[8,"부산울산","동부산","북경남신고리NP#1 T/L","345kV 신양산-고리NP 등 6개T/L 송전정비공사","-  북경남-신고리T/L 8,9호 수평레일 설치","2025-11-08 07:00","2025-11-11 18:00","2025-11-08 07:00","2025-11-11 18:00","연속"]
[9,"부산울산","동부산","신고리N/P #1 M.Tr","25년 하반기 신고리S/S  GIS 정밀보통점검공사","신고리S/S  GIS 8471 CB 전자변 교체","2025-11-17 09:00","2025-11-19 18:00","2025-11-12 09:00","2025-11-14 18:00","연속"]
[10,"부산울산","동부산","북경남신고리NP#2 T/L","북경남-신고리#2T/L, 신고리S/S 83Bay B/F PNL 교체","북경남-신고리#2T/L, 신고리S/S 83Bay B/F PNL 교체","2025-10-10 09:00","2025-10-17 18:00","2025-10-27 09:00","2025-11-07 18:00","연속"]
[11,"경남","함안","북경남S/S #1 BUS"," 북경남S/S #2M.Tr 증설공사"," #1BUS 도킹작업","2025-11-03 09:00","2025-11-15 18:00","2025-11-03 09:00","2025-11-15 18:00","연속"]
[12,"경남","함안","북경남S/S #5 M.Tr"," 북경남S/S #2M.Tr 증설공사","#2BUS 시험가압","2025-11-14 09:00","2025-11-15 18:00","2025-11-14 09:00","2025-11-15 18:00","연속"]
[13,"경남","함안","북경남신고리NP#2 T/L"," 북경남S/S #2M.Tr 증설공사"," #1BUS 도킹작업에 따른 안전이격거리확보","2025-11-03 09:00","2025-11-05 18:00","2025-11-03 09:00","2025-11-05 18:00","연속"]
[]
[]
[]
[{"$nulls":5}," "]

{"sheet":"345설비","index":1,"n_rows":423,"n_cols":12,"rows_kept":423,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2025년도 11월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #2 M.Tr","2025년 성동P/O 변전협력회사 공사","- 72Bay B/F반 교체","2025-11-19 09:00","2025-11-27 18:00","2025-11-19 09:00","2025-11-27 18:00","연속"]
[2,"서울","중부","중부S/S #75 BUS","2025년 중부전력지사 변전협력회사 공사","CT 집합반 교체","2025-11-25 10:00","2025-11-26 10:00","2025-11-25 10:00","2025-11-26 10:00","연속"]
[3,"서울","중부","중부S/S #70 BUS","2025년 중부전력지사 변전협력회사 공사","CT 집합반 교체","2025-11-24 17:00","2025-11-25 10:00","2025-11-24 17:00","2025-11-25 10:00","연속"]
[4,"서울","중부","중부S/S #3 M.Tr","2025년 중부S/S 154kV 장기사용 GIS 교체공사(4차)","- 154kV #62-#67PT GIS 증설(#62BUS 무부하가압용) - 기타 부대공사","2025-11-17 17:00","2025-11-18 09:00","2025-11-17 17:00","2025-11-18 09:00","연속"]
[5,"서울","중부","중부S/S #1 M.Tr","2025년 중부S/S 154kV 장기사용 GIS 교체공사(3차)","- 154kV 신규 GIS 무부하가압용","2025-11-04 17:00","2025-11-05 17:00","2025-11-04 17:00","2025-11-05 17:00","연속"]
[6,"서울","중부","중부S/S #70 BUS","2025년 중부전력지사 변전협력회사 공사","CT 집합반 교체","2025-11-26 10:00","2025-11-26 18:00","2025-11-26 10:00","2025-11-26 18:00","연속"]
[7,"서울","중부","중부S/S #3 M.Tr","2025년 중부S/S 154kV 장기사용 GIS 교체공사(4차)","- 154kV #62-#67PT GIS 증설(#67BUS 무부하가압용) - 기타 부대공사","2025-11-21 17:00","2025-11-22 15:00","2025-11-21 17:00","2025-11-22 15:00","연속"]
[8,"남서울","강남","신성남신양재#1 T/L","24-25년도 강남전력지사 변전협력회사 총액공사"," GIS 및 154kV GIS 조작시험, 전자변 교체 송전선로 피뢰기 열화진단","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[9,"남서울","강남","신성남신양재#2 T/L","송전선로 피뢰기 열화진단","송전선로 피뢰기 열화진단","2025-11-11 09:00","2025-11-11 18:00","2025-11-11 09:00","2025-11-11 18:00","연속"]
[10,"남서울","강남","신양재S/S #1 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사","Sh.R 보통점검 및 GIS 조작시험","2025-11-24 09:00","2025-11-24 14:00","2025-11-24 09:00","2025-11-24 18:00","연속"]
[11,"남서울","강남","신양재S/S #2 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사","Sh.R 보통점검 및 GIS 조작시험","2025-11-24 14:00","2025-11-24 18:00","2025-11-25 09:00","2025-11-25 18:00","연속"]
[12,"남서울","강남","신양재S/S #3 Sh.R CB","24-25년도 강남전력지사 변전협력회사 총액공사","GIS 조작시험","2025-11-25 09:00","2025-11-25 14:00","2025-11-26 09:00","2025-11-26 18:00","연속"]
[13,"남서울","강남","신성남신양재#2 T/L","24-25년도 강남전력지사 변전협력회사 총액공사"," #2M.Tr 1차 GIS 인출 PT 불량교체 관련 무부하 가압","2025-11-26 09:00","2025-11-27 18:00","2025-11-26 09:00","2025-11-27 18:00","연속"]
[14,"남서울","강남","신양재S/S #3 M.Tr","24-25년도 강남전력지사 변전협력회사 총액공사"," GIS 및 154kV GIS 조작시험, 주변압기 보통점검","2025-11-04 09:00","2025-11-05 18:00","2025-11-04 09:00","2025-11-05 18:00","연속"]
[15,"남서울","강남","신양재S/S #1 M.Tr","24-25년도 강남전력지사 변전협력회사 총액공사"," GIS 및 154kV GIS 조작시험, 전자변 교체","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[16,"남서울","동서울","동서울S/S #6 M.Tr","동서울S/S 종합정비공사","23kV Sh.R (3Bank), MAIN CB 이설","2025-11-17 08:00","2025-11-21 18:00","2025-11-17 08:00","2025-11-21 18:00","연속"]
[17,"남서울","동서울","동서울S/S #3 M.Tr","동서울S/S 종합정비공사","23kV Sh.R (3Bank), MAIN CB 이설","2025-11-10 08:00","2025-11-14 18:00","2025-11-10 08:00","2025-11-14 18:00","연속"]
[18,"남서울","동서울","동서울S/S CB 7800","362kV GIS Line PT 철거공사","362kV GIS Line PT 철거공사(불량설비 교체용 자재확보)","2025-11-24 09:00","2025-11-27 18:00","2025-11-24 09:00","2025-11-27 18:00","연속"]
[19,"남서울","동서울","동서울S/S CB 7872","362kV GIS Line PT 철거공사","362kV GIS Line PT 철거공사(불량설비 교체용 자재확보)","2025-11-24 09:00","2025-11-27 18:00","2025-11-24 09:00","2025-11-27 18:00","연속"]
[20,"남서울","동서울","동서울S/S CB 7472","2024-2025년도 동서울전력지사 변전협력회사 총액공사","7472 차단기 보통점검(7400 같이 휴전), 콘덴서 절연열화 측정","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[21,"남서울","동서울","동서울S/S CB 7400","2024-2025년도 동서울전력지사 변전협력회사 총액공사","7472 차단기 보통점검(7400 같이 휴전), 콘덴서 절연열화 측정","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[22,"남서울","동서울","신성남동서울#1 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","7871 차단기 조작시험","2025-11-04 09:00","2025-11-04 14:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[23,"남서울","동서울","동서울S/S #1 M.Tr","동서울S/S 종합정비공사(2차)","154kV 제어케이블 이설","2025-11-24 08:00","2025-11-26 12:00","2025-11-24 08:00","2025-11-26 12:00","연속"]
[24,"남서울","동서울","동서울S/S #2 M.Tr","동서울S/S 종합정비공사(2차)","154kV 제어케이블 이설","2025-11-26 13:00","2025-11-28 18:00","2025-11-26 13:00","2025-11-28 18:00","연속"]
[25,"남서울","동서울","신용인동서울#2 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","7971 차단기 조작시험(7900도 휴전 필요)","2025-11-04 14:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[26,"남서울","동서울","신성남동서울#2 T/L","2024-2025년도 동서울전력지사 변전협력회사 총액공사","7700, 7771 차단기 조작시험(7772는 기 휴전된 상태로 병행작업 시행)","2025-11-05 09:00","2025-11-05 18:00","2025-11-05 09:00","2025-11-05 18:00","연속"]
[27,"남서울","영등포","서서울신광명#2 T/L"," 서서울-신광명T/L 임시철탑 이설 및 보강공사","No.25 철탑보강, No.26 임시이설, No.27 철탑 인클로징","2025-11-29 09:00","2025-12-07 18:00","2025-11-29 09:00","2025-12-07 18:00","연속"]
[28,"남서울","영등포","신광명S/S #75 BUS"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-11-10 09:00","2025-11-28 18:00","2025-11-10 09:00","2025-11-28 18:00","연속"]
[29,"남서울","영등포","신광명S/S SEC CB 75760"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-11-10 09:00","2025-11-28 18:00","2025-11-10 09:00","2025-11-28 18:00","연속"]
[30,"남서울","영등포","신광명S/S CB 신7200","24~25년 영등포전력지사 변전협력회사 공사"," GCB 초기점검(7200)","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[31,"남서울","영등포","신광명S/S #3 M.Tr","신광명S/S #3M.Tr 3차측 GPT 점검","신광명S/S #3M.Tr 3차측 GPT 점검","2025-11-29 09:00","2025-11-30 18:00","2025-11-29 09:00","2025-11-30 18:00","연속"]
[32,"남서울","영등포","신광명신문래#3 T/L"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사 1식","2025-11-05 09:00","2025-11-06 18:00","2025-11-05 09:00","2025-11-06 18:00","연속"]
[33,"남서울","영등포","신광명S/S CB 신7279","24~25년 영등포전력지사 변전협력회사 공사"," GCB 초기점검","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[34,"남서울","영등포","신광명S/S CB 신7079","24~25년 영등포전력지사 변전협력회사 공사"," GCB 초기점검","2025-11-11 09:00","2025-11-11 18:00","2025-11-11 09:00","2025-11-11 18:00","연속"]
[35,"남서울","영등포","신광명S/S #76 BUS"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-11-10 09:00","2025-11-28 18:00","2025-11-10 09:00","2025-11-28 18:00","연속"]
[36,"남서울","직할","신광명신문래#2 T/L","362kV GIS 보통점검(7271)","362kV GIS 보통점검(7271)","2025-11-07 09:00","2025-11-07 18:00","취소","취소","연속"]
[37,"남서울","직할","신광명신문래#1 T/L","362kV GIS 보통점검(7171)","362kV GIS 보통점검(7171)","2025-11-06 09:00","2025-11-06 18:00","취소","취소","연속"]
[38,"인천","김포","가정개폐소 CB 7671","가정개폐소  #1 Sh.R 1차 GIS 정밀점검","가정개폐소  #1 Sh.R 1차 GIS 정밀점검","2025-11-24 09:00","2025-11-27 18:00","취소","취소","연속"]
[39,"인천","김포","가정개폐소 SEC CB 75760","가정개폐소  #75-#76 SEC GIS 정밀점검","가정개폐소  #75-#76 SEC GIS 정밀점검","2025-11-17 09:00","2025-11-20 18:00","2025-11-17 09:00","2025-11-20 18:00","연속"]
[40,"인천","김포","가정개폐소 SEC CB 70710","가정개폐소  #70-#71 SEC GIS 정밀점검","가정개폐소  #70-#71 SEC GIS 정밀점검","2025-11-10 09:00","2025-11-13 18:00","2025-11-24 09:00","2025-11-27 18:00","연속"]
[41,"인천","김포","신김포S/S #2 M.Tr","신김포S/S  #2M.Tr 추락방지 안전장치 설치","신김포S/S  #2M.Tr 추락방지 안전장치 설치","2025-11-04 10:00","2025-11-04 18:00","2025-11-04 10:00","2025-11-04 18:00","연속"]
[42,"인천","김포","신김포S/S #3 M.Tr","신김포S/S  #3M.Tr 추락방지 안전장치 설치","신김포S/S  #3M.Tr 추락방지 안전장치 설치","2025-11-05 10:00","2025-11-05 18:00","2025-11-05 10:00","2025-11-05 18:00","연속"]
[43,"인천","김포","신김포S/S #2 Sh.R CB","신김포S/S  #2Sh.R 추락방지 안전장치 설치","신김포S/S  #2Sh.R 추락방지 안전장치 설치","2025-11-06 10:00","2025-11-06 18:00","2025-11-06 10:00","2025-11-06 18:00","연속"]
[44,"인천","김포","신김포S/S #4 Sh.R CB","신김포S/S  #4Sh.R 추락방지 안전장치 설치","신김포S/S  #4Sh.R 추락방지 안전장치 설치","2025-11-07 10:00","2025-11-07 18:00","2025-11-07 10:00","2025-11-07 18:00","연속"]
[45,"인천","김포","신김포S/S #1 Sh.R CB"," 신김포변전소 Sh.R실 배기팬 교체공사","#1Sh.R실 배기팬 2EA 교체","2025-11-13 08:00","2025-11-13 18:00","2025-11-12 08:00","2025-11-12 18:00","연속"]
[46,"인천","김포","신김포S/S #3 Sh.R CB"," 신김포변전소 Sh.R실 배기팬 교체공사","#3Sh.R실 배기팬 2EA 교체","2025-11-14 08:00","2025-11-14 18:00","2025-11-14 08:00","2025-11-14 18:00","연속"]
[47,"인천","부평","서인천C/C #1 CLR CB","#1BUS CLR TOP HAT 볼트교체공사","#1BUS CLR TOP HAT 볼트교체공사","2025-11-15 09:00","2025-11-15 18:00","2025-11-15 09:00","2025-11-15 18:00","연속"]
[48,"인천","부평","서인천C/C CB 7A72","서인천복합S/Y 7A72 보호IED 펌웨어 업데이트","서인천복합S/Y 7A72 보호IED 펌웨어 업데이트 - 피앤씨테크제 7A B/F 보호반(7A72측)","2025-11-05 09:00","2025-11-05 18:00","취소","취소","연속"]
[49,"인천","부평","서인천C/C #1 CLR CB","#1BUS CLR TOP HAT 볼트교체공사","#1BUS CLR TOP HAT 볼트교체공사","2025-11-15 09:00","2025-11-15 18:00","취소","취소","연속"]
[50,"인천","부평","서인천C/C #4 M.Tr"," #4M.Tr 염해방지 코팅, 부싱유 채유(NGK)"," #4M.Tr 염해방지 코팅, 부싱유 채유(NGK)","2025-11-08 09:00","2025-11-09 18:00","2025-11-08 09:00","2025-11-09 18:00","연속"]
[51,"인천","부평","서인천C/C #2 M.Tr"," #2M.Tr 부싱유 채유(NGK)"," #2M.Tr 부싱유 채유(NGK)","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[52,"인천","부평","서인천C/C #1 M.Tr"," #1M.Tr 부싱유 채유(NGK)"," #1M.Tr 부싱유 채유(NGK)","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[53,"인천","부평","신가좌S/S #4 M.Tr"," #4M.Tr 보통점검 /2S.Tr 보호반 교체"," #4M.Tr 보통점검 / 23kV #4-1, #4-2 #2S.Tr 보호반 교체공사","2025-11-17 09:00","2025-11-21 18:00","2025-11-17 09:00","2025-11-21 18:00","연속"]
[54,"인천","부평","신가좌S/S #2 M.Tr"," #2M.Tr 하자점검 / Sh.R 보호반 교체"," #2M.Tr 하자점검 / 23kV #2-1, #2-2 Sh.R 보호반 교체 공사","2025-11-10 09:00","2025-11-14 18:00","2025-11-03 09:00","2025-11-09 18:00","연속"]
[55,"인천","부평","신가좌S/S CB 7272","(구)신가좌S/S  신가좌-신시흥#1T/L 7272 GIS 조작","(구)신가좌S/S  신가좌-신시흥#1T/L 7272 GIS 조작","2025-11-01 09:00","2025-11-01 18:00","2025-11-01 09:00","2025-11-01 18:00","연속"]
[56,"인천","부평","신경서S/S CB 7400"," 신경서-서인천CCT/L TIE 7400 GIS 보통점검"," 신경서-서인천CCT/L TIE 7400 GIS 보통점검","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[57,"인천","부평","신경서S/S #1 M.Tr","신경서S/S #1M.Tr 부싱유 채유","신경서S/S #1M.Tr 부싱유 채유","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[58,"인천","부평","신경서S/S #3 M.Tr"," #3M.Tr 2차 피뢰기 A,B,C 교체"," #3M.Tr 2차 피뢰기 A,B,C 교체","2025-11-05 09:00","2025-11-05 18:00","2025-11-05 09:00","2025-11-05 18:00","연속"]
[59,"인천","부평","신경서S/S #2 M.Tr","신경서S/S #2M.Tr 부싱유 채유","신경서S/S #2M.Tr 부싱유 채유","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[60,"인천","부평","신인천C/C SEC CB 70710","신인천복합S/Y 70-71 / 71-72 SEC B/F 보호반 교체 공사","신인천복합S/Y 70-71 / 71-72 SEC B/F 보호반 교체 공사","2025-11-10 09:00","2025-11-14 18:00","2025-11-08 09:00","2025-11-12 18:00","연속"]
[61,"인천","부평","신인천C/C SEC CB 71720","신인천복합S/Y 70-71 / 71-72 SEC B/F 보호반 교체 공사","신인천복합S/Y 70-71 / 71-72 SEC B/F 보호반 교체 공사","2025-11-10 09:00","2025-11-14 18:00","2025-11-08 09:00","2025-11-12 18:00","연속"]
[62,"인천","부평","인천C/C CB 7600","인천복합#2S/T-인천복합#1S/T TIE 7600 GIS 조작","인천복합#2S/T-인천복합#1S/T TIE 7600 GIS 조작","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[63,"인천","부평","인천C/C SEC CB 75760","인천CC S/Y  #75-#76 SEC GIS 보통점검","인천CC S/Y  #75-#76 SEC GIS 보통점검","2025-11-08 09:00","2025-11-08 18:00","2025-11-08 09:00","2025-11-08 18:00","연속"]
[64,"인천","부평","인천C/C #1 M.Tr","#1Tie Tr 부싱유 채유","#1Tie Tr 부싱유 채유","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[65,"인천","부평","가정인천CC#1 T/L"," 가정인천CC#1T/L 염해방지 코팅"," 가정인천CC#1T/L 염해방지 코팅","2025-11-01 07:00","2025-11-01 20:00","2025-11-01 07:00","2025-11-01 20:00","연속"]
[66,"인천","부평","포스코C/C #70 BUS","포스코 #70BUS 모선보호반 교체 공사","포스코 #70BUS 모선보호반 교체 공사","2025-11-03 09:00","2025-11-07 18:00","2025-11-03 09:00","2025-11-07 18:00","연속"]
[67,"인천","시흥","신시화S/S #3 M.Tr","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(74BF반)","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[68,"인천","시흥","신시화S/S #2 M.Tr","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(73BF반)","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[69,"인천","시흥","신시화영흥TP#2 T/L","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(73BF반)","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[70,"인천","시흥","신시흥신시화#1 T/L","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(74BF반)","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[71,"인천","시흥","신시화S/S #3 M.Tr","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(65BF반)","2025-11-13 09:00","2025-11-13 14:00","2025-11-07 12:00","2025-11-07 15:00","연속"]
[72,"인천","시흥","신시흥#1S/S #2 M.Tr","신시흥#1S/S  #2 M.Tr 보통점검","신시흥#1S/S  #2 M.Tr 보통점검-보호반대체 병행","2025-11-11 09:00","2025-11-15 18:00","2025-11-11 09:00","2025-11-15 18:00","연속"]
[73,"인천","시흥","신시흥영흥TP#1 T/L","신시흥S/S 362kV GIS 정밀점검 공사(7771) 무부하가압","신시흥S/S  7771 CB 정밀점검 공사 무부하가압","2025-11-07 10:00","2025-11-07 14:00","취소","취소","연속"]
[74,"인천","시흥","신시흥#1S/S #1 M.Tr","신시흥#1S/S  #1 M.Tr 보통점검","신시흥#1S/S  #1 M.Tr 보통점검(#1S.Tr초기점검, S.Tr CB 대체 병행)","2025-11-03 09:00","2025-11-05 18:00","취소","취소","연속"]
[75,"인천","시흥","신시흥#1S/S #3 M.Tr","신시흥#1S/S  #3 M.Tr 보통점검","신시흥#1S/S  #3 M.Tr 보통점검(#2S.Tr 초기점검 병행)","2025-11-03 09:00","2025-11-07 18:00","2025-11-03 09:00","2025-11-07 18:00","연속"]
[76,"인천","시흥","신시흥#1S/S CB 7771","신시흥S/S 362kV GIS 정밀점검 공사(7771)","신시흥S/S 7771 CB 정밀점검 공사","2025-11-03 08:00","2025-11-07 18:00","취소","취소","연속"]
[77,"인천","시흥","신시흥영흥TP#1 T/L","신시흥S/S  신시흥영흥TP#1T/L 피뢰기 보통점검","신시흥S/S  신시흥영흥TP#1T/L 피뢰기 보통점검","2025-11-25 09:00","2025-11-25 18:00","취소","취소","연속"]
[78,"인천","시흥","신시흥#1S/S CB 7A71","신시흥S/S  신시흥신광명#2 T/L LA 보통점검","신시흥S/S  신시흥신광명#2 T/L LA 보통점검","2025-11-17 09:00","2025-11-17 18:00","취소","취소","연속"]
[79,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥#2S/S  #6 M.Tr 피뢰기 대체","신시흥#2S/S  #6 M.Tr 피뢰기 대체(1,2,3차)","2025-11-26 09:00","2025-11-28 18:00","2025-11-26 09:00","2025-11-28 18:00","연속"]
[80,"인천","시흥","신시흥#2S/S #4 M.Tr","신시흥#2S/S  #4 M.Tr 보호반대체","신시흥#2S/S  #4 M.Tr 보호반대체","2025-11-17 09:00","2025-11-21 18:00","2025-11-17 09:00","2025-11-21 18:00","연속"]
[81,"인천","시흥","신시흥신안산#1 T/L","신시흥신안산#1T/L 피뢰기보통점검","신시흥신안산#1T/L 피뢰기보통점검","2025-11-12 09:00","2025-11-12 18:00","취소","취소","연속"]
[82,"인천","직할","갈산S/S #4 M.Tr","갈산S/S 종합예방진단시스템 증설공사","#4M.Tr 부싱누설전류 진단장치 설치 및 관련 케이블 결선작업 등","2025-11-03 09:00","2025-11-07 18:00","2025-11-03 09:00","2025-11-07 18:00","연속"]
[83,"인천","직할","신부평S/S #4 Sh.R CB","신부평S/S #4Sh.R 초기점검","신부평S/S #4Sh.R 초기점검","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[84,"인천","직할","갈산가정#3 T/L","갈산S/S 가정갈산#3T/L 1st 21 RY 교체","갈산S/S 가정갈산#3T/L 1st 21 RY 교체","2025-11-14 09:00","2025-11-14 18:00","취소","취소","연속"]
[85,"인천","김포","신김포S/S #1 M.Tr"," 신김포S/S  신김포-신파주#1T/L 보호배전반 대체관련 휴전"," 신김포S/S  신김포-신파주#1T/L 보호배전반 대체관련 휴전","2025-11-17 09:00","2025-11-21 18:00","2025-11-17 09:00","2025-11-21 18:00","연속"]
[86,"인천","김포","신김포서인천CC T/L"," 신김포S/S  신김포-신파주#2T/L 보호배전반 대체관련 휴전"," 신김포S/S  신김포-신파주#2T/L 보호배전반 대체관련 휴전","2025-11-24 09:00","2025-11-28 18:00","취소","취소","연속"]
[87,"인천","부평","신가좌신시흥#2 T/L"," 신가좌-신시흥T/L No.15 태풍취약철탑 보강공사","인클로징 공법 충전부 방호장치 설치","2025-11-09 07:00","2025-11-09 18:00","취소","취소","연속"]
[88,"인천","부평","신가좌신시흥#1 T/L"," 신가좌-신시흥T/L No.15 태풍취약철탑 보강공사 등 3건","15호 인클로징 보강(태풍취약) 2~13호 상부재 보강(철탑보강)  피뢰기 설치(가공협력)","2025-11-10 07:00","2025-11-21 18:00","취소","취소","연속"]
[89,"인천","부평","신가좌신시흥#2 T/L"," 신가좌-신시흥T/L No.15 태풍취약철탑 보강공사 등 3건","15호 인클로징 보강(태풍취약) 2~13호 상부재 보강(철탑보강)  피뢰기 설치(가공협력)","2025-11-22 07:00","2025-11-28 18:00","취소","취소","연속"]
[90,"인천","부평","신가좌S/S CB 7400","신가좌신시흥#2T/L-#3 M.Tr 1차 TIE 7400 GIS 조작"," 신가좌신시흥#2T/L-#3 M.Tr 1차 TIE 7400 GIS 조작","2025-11-04 09:00","2025-11-04 18:00","취소","취소","연속"]
[91,"경기북부","고양","신덕은동두천CC#2 T/L"," 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신덕은-동두천CC#2 T/L No.18~19, 32~50 (子 : 154kV 신의정부-백학#1 T/L No.7~8,21~39)","2025-11-20 07:00","2025-11-24 18:00","2025-11-20 07:00","2025-11-24 18:00","연속"]
[92,"경기북부","고양","신덕은동두천CC#1 T/L"," 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 :  신덕은-동두천CC#1 T/L No.18~19 (子 : 154kV 신의정부-백학#2 T/L No.7~8)","2025-11-25 07:00","2025-11-25 18:00","2025-11-25 07:00","2025-11-25 18:00","연속"]
[93,"경기북부","고양","신파주신덕은#1 T/L","신파주S/S 장기사용 노후 배전반 대체공사","#71 Bay B/F 보호반 대체 *10월 휴전일정 취소 대비 신청","2025-11-17 09:00","2025-11-21 18:00","2025-11-17 09:00","2025-11-21 18:00","연속"]
[94,"경기북부","고양","신김포신파주#1 T/L","신파주S/S 장기사용 노후 배전반 대체공사"," 신김포-신파주#1T/L 보호반 및 #71 Bay B/F 보호반 대체 *10월 휴전일정 취소 대비 신청","2025-11-17 09:00","2025-11-21 18:00","2025-11-17 09:00","2025-11-21 18:00","연속"]
[95,"경기북부","고양","신파주신덕은#2 T/L","신파주S/S 장기사용 노후 배전반 대체공사","#75 Bay B/F 보호반 대체 *10월 휴전일정 취소 대비 신청","2025-11-24 09:00","2025-11-28 18:00","2025-11-24 09:00","2025-11-28 18:00","연속"]
[96,"경기북부","고양","신김포신파주#2 T/L","신파주S/S 장기사용 노후 배전반 대체공사"," 신김포-신파주#2T/L 보호반 및 #75 Bay B/F 보호반 대체 *10월 휴전일정 취소 대비 신청","2025-11-24 09:00","2025-11-28 18:00","2025-11-24 09:00","2025-11-28 18:00","연속"]
[97,"경기북부","고양","신파주양주#1 T/L","24~25년 고양전력지사 변전협력회사 공사","362kV GIS 보통점검(7371,7300)","2025-11-17 09:00","2025-11-18 18:00","2025-11-17 09:00","2025-11-18 18:00","연속"]
[98,"경기북부","구리","미금S/S CB 7079","2025년 구리전력지사 154kV 이상 GIS 점검공사","관내변전소  GIS 점검(7079)","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[99,"경기북부","구리","미금S/S #1 M.Tr","24-25년 구리전력지사 변전협력회사 총액공사"," M.Tr 송유펌프 교체","2025-11-17 09:00","2025-11-19 18:00","2025-11-17 09:00","2025-11-19 18:00","연속"]
[100,"경기북부","구리","신가평S/S CB 7679","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험(7679)","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[101,"경기북부","구리","신가평S/S CB 7671","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 점검(7671)","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[102,"경기북부","구리","신포천S/S CB 7600","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험(7600)","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[103,"경기북부","구리","신포천S/S CB 7671","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험(7671)","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[104,"경기북부","구리","신포천S/S CB 7500","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험(7500)","2025-11-11 09:00","2025-11-11 18:00","2025-11-11 09:00","2025-11-11 18:00","연속"]
[105,"경기북부","구리","신포천S/S CB 7571","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험(7571)","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[106,"경기북부","구리","신포천포천LNGCC#1 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","신포천-포천LNG#1T/L 철탑추락방지장치 설치(수직:5기,수평:5기) No.1~5","2025-11-26 07:00","2025-12-05 18:00","2025-11-26 07:00","2025-12-05 18:00","연속"]
[107,"경기북부","직할","신의정부S/S  #1CLR GIS 선로측 DS","2024-25년 경기북부 직할 변전협력 총액공사","신의정부-양주#1 CLR 하자점검(7321-2)","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[108,"경기북부","직할","신의정부S/S #4 M.Tr","신의정부S/S #4M.Tr 교체공사","장기사용 변압기 교체공사","2025-11-05 09:00","2026-02-27 18:00","2025-11-05 09:00","2026-02-27 18:00","연속"]
[109,"경기북부","직할","신의정부S/S #1 M.Tr","24-25 직할 변전협력 총액공사","23kV GIS 보통점검(3차측)","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[110,"경기북부","직할","신의정부S/S #2 M.Tr","24-25 직할 변전협력 총액공사","23kV GIS 보통점검(3차측)","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[111,"경기북부","직할","신의정부S/S CB 7872","24-25년 변전협력회사 총액공사","신의정부SS 7872 GIS 개폐타임 측정","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[112,"경기북부","직할","신의정부S/S CB 7771","24-24년 변전협력회사 총액공사","신의정부SS 7771 GIS 보통점검 및 전자변 교체","2025-11-27 09:00","2025-11-28 18:00","2025-11-27 09:00","2025-11-28 18:00","연속"]
[113,"경기북부","직할","신의정부S/S  #2CLR GIS 선로측 DS","2024-25년 경기북부 직할 변전협력 총액공사","신의정부-양주#2 CLR 하자점검(7421-2)","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[114,"경기북부","직할","신의정부S/S  #2CLR GIS 모선측 DS","2024-25년 경기북부 직할 변전협력 총액공사","신의정부-양주#2 CLR 하자점검(7421-1)","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[115,"경기북부","직할","신의정부S/S  #1CLR GIS 모선측 DS","2024-25년 경기북부 직할 변전협력 총액공사","신의정부-양주#1 CLR 하자점검 (7321-1)","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[116,"경기북부","직할","신의정부양주#1 T/L","24-25년도 변전 협력회사 총액공사","개폐타임 측정 및 피뢰기 보통점검","2025-11-24 09:00","2025-11-24 18:00","2025-11-24 09:00","2025-11-24 18:00","연속"]
[117,"경기북부","직할","신의정부양주#2 T/L","24-25년도 변전 협력회사 총액공사","개폐타임 측정 및 피뢰기 보통점검","2025-11-19 09:00","2025-11-19 18:00","2025-11-19 09:00","2025-11-19 18:00","연속"]
[118,"경기북부","직할","양주S/S #1 M.Tr","'24-25 변전 협력회사 총액공사","A상 부싱 채유","2025-11-03 09:00","2025-11-05 18:00","2025-11-03 09:00","2025-11-05 18:00","연속"]
[119,"경기북부","직할","양주S/S #2 M.Tr","'24-25 변전 협력회사 총액공사","A,B,C상 부싱 채유, C상 OLTC 하부 플레이트 교체","2025-11-06 09:00","2025-11-07 18:00","2025-11-06 09:00","2025-11-07 18:00","연속"]
[120,"경기북부","직할","양주S/S #4 M.Tr"," 변압기 정밀점검 공사","A,B 보통점검 및 채유 C상 정밀점검","2025-11-10 09:00","2025-11-19 18:00","2025-11-10 09:00","2025-11-19 18:00","연속"]
[121,"경기","군포","서서울#2신시흥#2 T/L","서서울2S/S 서서울2-신시흥#2T/L 7C72,7C00GIS 보통점검등","서서울#2S/S  서서울2-신시흥#2T/L 7C72,7C00 GIS 보통점검, 절연열화측정","2025-11-10 09:00","2025-11-11 18:00","2025-11-10 09:00","2025-11-11 18:00","연속"]
[122,"경기","군포","서서울#2신시흥#1 T/L","서서울2S/S 서서울2-신시흥#1T/L 7D72,7D00GIS 보통점검등","서서울#2S/S  서서울2-신시흥#1T/L 7D72,7D00 GIS 보통점검, 절연열화측정","2025-11-26 09:00","2025-11-27 18:00","2025-11-26 09:00","2025-11-27 18:00","연속"]
[123,"경기","군포","서서울#2S/S #5 M.Tr","서서울#2S/S  #5M.Tr상 부싱유 채유","서서울#2S/S  #5M.Tr상 부싱유 채유","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[124,"경기","군포","신온양서서울#2 T/L","서서울S/S 신온양-서서울#2T/L 7772,7700GIS 보통점검 등","서서울S/S  신온양-서서울#2T/L 7772,7700 GIS 보통점검, CVT 대체","2025-11-05 09:00","2025-11-06 18:00","2025-11-05 09:00","2025-11-06 18:00","연속"]
[125,"경기","군포","서서울S/S #4 M.Tr","서서울S/S  #4M.Tr1차 7872,7800GIS 보통점검등","(10월취소시)서서울S/S  #4M.Tr 1차 7872,7800 GIS 보통점검,1차 CVT 대체,3차 GPT 대체,본체 부싱유채유,추락방지설치,방호벽사다리 철거","2025-11-24 09:00","2025-11-25 18:00","2025-11-24 09:00","2025-11-25 18:00","연속"]
[126,"경기","군포","신온양서서울#1 T/L","서서울S/S 신온양-서서울#1T/L 7400 GIS 조작시험 등","서서울S/S  신온양-서서울#1T/L 7400 GIS 조작시험,유사고장(송전선로 결상회로 개선) 점검,CVT 대체","2025-11-03 09:00","2025-11-04 18:00","2025-11-03 09:00","2025-11-04 18:00","연속"]
[127,"경기","군포","서서울S/S #2 M.Tr","서서울S/S  #2M.Tr 1차 7572GIS 보통점검 등","(10월취소시)서서울S/S  #2M.Tr 1차 7572GIS 보통,1,2,3차 LA 대체,1차CVT 대체,3차 GPT 초기점검","2025-11-17 09:00","2025-11-18 18:00","2025-11-17 09:00","2025-11-18 18:00","연속"]
[128,"경기","군포","서서울S/S #3 M.Tr","서서울S/S  #3M.Tr1차 7672,7600GIS 보통점검등","(10월취소시)서서울S/S  #3M.Tr 1차 7672,7600 GIS 보통점검,1차 CVT 대체,3차 GPT 초기점검,추락방지설치","2025-11-19 09:00","2025-11-20 18:00","2025-11-19 09:00","2025-11-20 18:00","연속"]
[129,"경기","동부","곤지암여주복합#1 T/L","2024-2025년 성남전력지사 가공송전 협력회사 공사","□ 전력선 정비 ○ 소도체 이도조정 : 곤지암-여주복합#1,2T/L No.63~69, 85~88호 ○ 가공지선 교체 : 곤지암-여주복합#1T/L No. 33~36호","2025-11-25 09:00","2025-11-28 18:00","취소","취소","연속"]
[130,"경기","동부","곤지암S/S #3 M.Tr","곤지암S/S  #3M.Tr 절연열화 측정 탭 설치","곤지암: #3M.Tr(1,2차) *[20↑]부싱절연유 채유(A,B,C) *절연열화 탭 제작사 설치(박성규)","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","연속"]
[131,"경기","동부","곤지암S/S #1 M.Tr","곤지암S/S  #1M.Tr 절연열화 측정 탭 설치","곤지암: #1M.Tr(1,2차) *[20↑]부싱절연유 채유(A,B,C) *곤지암S/S  #1M.Tr 절연열화 측정 탭 설치(박성규)","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[132,"경기","동부","곤지암S/S #4 M.Tr","곤지암S/S  #4M.Tr 절연열화 측정 탭 설치","곤지암: #4M.Tr *절연열화 탭 제작사 설치(박성규)","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[133,"경기","동부","곤지암S/S #2 M.Tr","곤지암S/S  #2M.Tr 절연열화측정 탭 설치","곤지암: #2M.Tr(1,2차) *[20↑]부싱절연유 채유(A,B,C) *6244 누유조치(테프론 와셔) *절연열화 탭 제작사 설치(박성규)","2025-11-05 09:00","2025-11-05 18:00","2025-11-05 09:00","2025-11-05 18:00","연속"]
[134,"경기","동부","곤지암여주복합#2 T/L","2024-2025년 성남전력지사 가공송전 협력회사 공사","□ 전력선 정비 ○ 소도체 이도조정 : 곤지암-여주복합#1,2T/L No.63~69, 85~88호","2025-11-24 09:00","2025-11-24 18:00","취소","취소","연속"]
[135,"경기","동부","여주C/C CB 7371","여주C/C  곤지암-여주복합#2T/L GIS 하자점검","여주C/C  곤지암-여주복합#2T/L GIS 하자점검","2025-11-27 09:00","2025-11-27 18:00","2025-11-27 09:00","2025-11-27 18:00","연속"]
[136,"경기","동부","여주C/C CB 7271","여주CC 신충주-여주복합#2T/L 하자점검","여주CC 신충주-여주복합#2T/L 하자점검","2025-11-11 09:00","2025-11-11 18:00","2025-11-11 09:00","2025-11-11 18:00","연속"]
[137,"경기","성남","신성남S/S #6 M.Tr","2025년 성남전력 변전협력회사 총액공사","7872 조작시험, 절연열화,2차 LA 하자점검,2차 GIS 조작시험,3차 4679 보통점검,3차 467-1,2 보통점검,#6-1,2 Sh.R 하자점검,부싱절연유 채유 4675DS 조류방지커버 설치","2025-11-05 09:00","2025-11-07 18:00","2025-11-05 09:00","2025-11-07 18:00","연속"]
[138,"경기","성남","신성남S/S #2 M.Tr","25년 성남전력 주변압기  보통, 154kV 정밀/보통점검공사","m.tr 보통점검","2025-11-03 09:00","2025-11-04 18:00","2025-11-03 09:00","2025-11-04 18:00","연속"]
[139,"경기","성남","서서울#2신성남#2 T/L","2025년 성남전력 변전협력회사 총액공사","7171 조작시험, 절연열화 7171 CVT A,B상 하자점검","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[140,"경기","성남","신수원S/S #2 M.Tr","신수원S/S 154kV 계통조정공사(토목)"," #2M.Tr용 신규GIB 기초작업(토목) (작업시 안전이격용 휴전필요)","2025-11-17 09:00","2025-11-30 18:00","2025-11-17 09:00","2025-11-30 18:00","연속"]
[141,"경기","성남","신수원S/S #4 M.Tr","신수원S/S 154kV 계통조정공사(토목)"," #2M.Tr용 신규GIB 기초작업(토목) (자재반입 안전이격용 휴전필요)","2025-11-03 09:00","2025-11-16 18:00","2025-11-03 09:00","2025-11-16 18:00","연속"]
[142,"경기","성남","신안성신성남#2 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사 - 대상구간 :  신안성-신성남#2T/L No.4~66 - 사전작업 : 추락방지장치 설치시행(수평) ※  신안성-신용인T/L 4회선 구간","2025-11-09 07:00","2025-11-23 18:00","2025-11-09 07:00","2025-11-23 18:00","연속"]
[143,"경기","성남","신안성신용인#2 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사 - 대상구간 :  신안성-신용인#2T/L No.4~66 - 사전작업 : 추락방지장치 설치시행(수평) ※  신안성-신성남T/L 4회선 구간","2025-11-09 07:00","2025-11-23 18:00","2025-11-09 07:00","2025-11-23 18:00","연속"]
[144,"경기","성남","신안성신성남#1 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사 - 대상구간 :  신안성-신성남#1T/L No.49~66 ※  신안성-신용인T/L 4회선 구간","2025-11-06 07:00","2025-11-08 18:00","2025-11-06 07:00","2025-11-08 18:00","연속"]
[145,"경기","성남","신안성신용인#1 T/L","24-25년 가공송전 정비공사(스페이서 댐퍼 교체)","○ 스페이서 댐퍼 불량관련 교체공사 - 대상구간 :  신안성-신용인#1T/L No.49~66 ※  신안성-신성남T/L 4회선 구간","2025-11-06 07:00","2025-11-08 18:00","2025-11-06 07:00","2025-11-08 18:00","연속"]
[146,"경기","성남","신용인S/S #2 M.Tr","25년 성남전력 주변압기  보통, 154kV 정밀/보통점검공사","m.tr 보통점검","2025-11-01 09:00","2025-11-02 18:00","2025-11-01 09:00","2025-11-02 18:00","연속"]
[147,"경기","평택","서안성S/S #2 M.Tr","2025년 평택전력 변전협력회사 총액공사(서안성2)","서안성S/S  #2 M.Tr 보호배전반 대체, #2S.Tr 대체, 2차 GIS 보통점검 ,3차 GIS 보통점검","2025-11-17 09:00","2025-11-28 18:00","2025-11-17 09:00","2025-11-28 18:00","연속"]
[148,"경기","평택","평택T/P #1 M.Tr","2025 평택전력 변전협력 총액공사(평택TP#1)","#1TIE-Tr A상 부싱 질소충진작업","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","연속"]
[149,"경기","평택","평택T/P CB 7600","평택T/P  발전소 트립라인 분리작업(7600)","#2T/P 트립라인 분리작업(7600)","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[150,"경기","평택","평택T/P CB 7672","평택T/P  발전소 트립라인 분리작업(7672)","#2T/P 트립라인 분리작업(7672)","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[151,"경기","평택","평택T/P CB 7472","평택T/P  발전소 트립라인 분리작업(7472)","#1T/P 트립라인 분리작업(7472)","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[152,"경기","평택","평택T/P CB 7200","평택T/P 발전소 트립라인 분리작업(7200)","#4T/P 트립라인 분리작업(7200)","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[153,"경기","평택","평택T/P CB 7100","평택T/P  발전소 트립라인 분리작업(7100)","#3T/P 트립라인 분리작업(7100)","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[154,"경기","평택","평택T/P CB 7400","평택T/P  발전소 트립라인 분리작업","#1T/P 트립라인 분리작업(7400)","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[155,"경기","평택","평택T/P CB 7271","평택T/P 발전소 트립라인 분리작업(7271)","#4T/P 트립라인 분리작업(7271)","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[156,"경기","평택","평택T/P CB 7172","평택T/P  발전소 트립라인 분리작업(7172)","#3T/P 트립라인 분리작업(7172)","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[157,"경기","평택","평택T/P #3 M.Tr","154kV 평택T/L SW 증설공사(기아)","- 인접BAY 감압 시행","2025-11-03 09:00","2025-11-20 18:00","2025-11-03 09:00","2025-11-20 18:00","연속"]
[158,"경기","성남","신용인S/S #1 M.Tr","2025년 성남전력 변전협력회사 총액공사","부싱절연유 채유","2025-11-12 09:00","2025-11-14 18:00","2025-10-30 09:00","2025-10-31 18:00","연속"]
[159,"경기","평택","고덕#2S/S CB 7572","PNC테크 성능개선(7572)","PNC테크 성능개선(7572)","2025-11-06 09:00","2025-11-06 09:30","2025-11-06 09:00","2025-11-06 09:30","연속"]
[160,"경기","평택","고덕#2S/S CB 7500","PNC테크 성능개선(7500)","PNC테크 성능개선(7500)","2025-11-06 08:30","2025-11-06 09:00","2025-11-06 08:30","2025-11-06 09:00","연속"]
[161,"경기","평택","고덕#2S/S CB 7571","PNC테크 성능개선(7571)","PNC테크 성능개선(7571)","2025-11-06 08:00","2025-11-06 08:30","2025-11-06 08:00","2025-11-06 08:30","연속"]
[162,"강원","강릉","신양양S/S #1 M.Tr","2025년 강릉전력  주변압기 정밀점검"," 주변압기 정밀점검","2025-11-10 09:00","2025-11-21 18:00","2025-11-10 09:00","2025-11-21 18:00","연속"]
[163,"강원","강릉","신양양양양PP T/L","2025년 강릉전력  주변압기 정밀점검"," 주변압기 정밀점검(무부하 가압용)","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","연속"]
[164,"강원","강릉","안인개폐소신양양 T/L","신양양S/S STATCOM용  GIS 설치공사","신양양 STATCOM C.Tr 및 GIS(7500CB, 7572CB) 무부하가압","2025-11-26 09:00","2025-11-28 09:00","2025-11-26 09:00","2025-11-28 09:00","연속"]
[165,"강원","강릉","신양양S/S #1 BUS","신양양S/S STATCOM용  GIS 설치공사","신양양 STATCOM C.Tr 및 GIS(7500CB) 무부하가압","2025-11-26 09:00","2025-11-27 09:00","2025-11-26 09:00","2025-11-27 09:00","연속"]
[166,"강원","강릉","신양양S/S #2 BUS","신양양S/S STATCOM용  GIS 설치공사","신양양 STATCOM C.Tr 및 GIS(7572CB) 무부하가압","2025-11-27 09:00","2025-11-28 09:00","2025-11-27 09:00","2025-11-28 09:00","연속"]
[167,"강원","강릉","양양P/P #2 BUS","2025년 강릉전력 변전협력 총액공사"," 75BUS 모선보호반 대체","2025-11-17 10:00","2025-11-21 18:00","2025-11-17 10:00","2025-11-21 18:00","연속"]
[168,"강원","동해","동해S/S  예비 M.Tr","2024∼2025년 동해전력지사 변전협력회사 공사","○ PCBs 절연유 세척제거","2025-11-24 09:00","2025-11-28 18:00","취소","취소","연속"]
[169,"강원","동해","동해S/S #2 M.Tr","동해전력지사 주변압기 정밀점검공사","○ #2M.Tr 정밀점검 ○ #2M,Tr AC,DC 옥외분전반 대체 ○ 부싱유채취","2025-11-17 09:00","2025-11-28 18:00","2025-11-17 09:00","2025-11-28 18:00","연속"]
[170,"강원","동해","동해S/S STATCOM CB","동해STATCOM 보통점검 및 성능개선","동해STATCOM 보통점검 및 SMPS 개선","2025-11-01 09:00","2025-11-12 18:00","취소","취소","연속"]
[171,"강원","동해","북평T/P CB 7272","2024∼2025년 동해전력지사 변전협력회사 공사","GIS 보통점검","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[172,"강원","태백","신태백S/S STATCOM CB","신태백S/S  STATCOM 부하시험","-  STATCOM 부하시험(11/5~28)","2025-11-05 09:00","2025-11-28 18:00","2025-11-05 09:00","2025-11-28 18:00","연속"]
[173,"강원","태백","신태백한울NP#1 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 신태백-한울NP2 #1 T/L 수평추락방지장치 및 폴리머 점퍼지지애자 설치","2025-11-10 07:00","2025-11-17 18:00","취소","취소","매일"]
[174,"강원","태백","신태백S/S STATCOM CB","신태백S/S  GIS 사용전검사","-  GIS 사용전검사(11/3~4)","2025-11-03 09:00","2025-11-04 18:00","2025-11-03 09:00","2025-11-04 18:00","연속"]
[175,"충북","직할","신중부신진천#1 T/L","'24-'25년 청주전력지사 송전정비 협력회사 총액공사","수직, 수평 추락방지장치 설치(No.1~27)","2025-11-03 08:00","2025-11-10 18:00","2025-11-03 08:00","2025-11-10 18:00","매일"]
[176,"충북","직할","신중부신진천#2 T/L","'24-'25년 청주전력지사 송전정비 협력회사 총액공사","수직, 수평 추락방지장치 설치(No.1~27)","2025-11-11 08:00","2025-11-14 18:00","2025-11-11 08:00","2025-11-14 18:00","매일"]
[177,"충북","직할","서안성신진천#2 T/L","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  서안성-신진천#2T/L LA 보통점검","2025-11-19 10:00","2025-11-19 18:00","2025-11-19 10:00","2025-11-19 18:00","연속"]
[178,"충북","직할","신진천S/S CB 7471","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  서안성-신진천#1T/L GIS 보통점검(7400)","2025-11-18 10:00","2025-11-18 18:00","2025-11-18 10:00","2025-11-18 18:00","연속"]
[179,"충북","청주","남청주S/S #2 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사","#2M.Tr 보호반 대체","2025-11-24 09:00","2025-11-27 18:00","2025-11-24 09:00","2025-11-27 18:00","연속"]
[180,"충북","청주","남청주S/S #3 M.Tr","남청주S/S 154kV 장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_11월)","2025-11-07 14:00","2025-11-08 14:00","2025-11-07 14:00","2025-11-08 14:00","연속"]
[181,"충북","청주","신옥천세종#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","LA, CVT 교체","2025-11-14 08:00","2025-11-14 18:00","취소","취소","연속"]
[182,"충북","청주","신옥천S/S #3 M.Tr","2024~2025년 청주전력지사 변전협력회사 공사","M.Tr 3차측 점검","2025-11-05 08:00","2025-11-05 18:00","2025-11-05 08:00","2025-11-05 18:00","연속"]
[183,"충북","충주","신제천신영주#1 T/L","2025년 가공송전 순시점검 위탁공사"," 신제천-신영주T/L No.1~165 정밀점검","2025-11-03 07:00","2025-11-14 18:00","취소","취소","매일"]
[184,"충북","충주","신제천신충주#2 T/L","신제천S/S 362KV GIS PD 제작사 하자보수/가공송전 위탁공사","신제천S/S 신제천신충주#2T/L DS(7361,7301) PD 하자보수 및 선로 과열개소 정비","2025-11-10 07:00","2025-11-12 18:00","취소","취소","연속"]
[185,"충북","충주","신제천신영주#2 T/L","가공송전 순시점검 위탁공사/신제천S/S 362KV GIS PD 하자보수"," 신제천-신영주T/L No.1~165 정밀점검 및 신제천S/S  신제천신영주#2T/L DS(7761,7701) PD 하자보수","2025-11-17 07:00","2025-11-28 18:00","취소","취소","연속"]
[186,"충북","충주","신제천신충주T#1 T/L","신제천S/S 362KV GIS PD 제작사 하자보수공사","신제천S/S  신제천여주복합T/L DS(7461,7401) PD 하자보수","2025-11-13 09:00","2025-11-15 18:00","취소","취소","연속"]
[187,"충북","충주","신충주S/S STATCOM CB","2025년 신충주S/S  STATCOM 보통점검공사","신충주S/S  STATCOM 보통점검","2025-11-17 09:00","2025-11-28 18:00","취소","취소","연속"]
[188,"충북","충주","신충주S/S CB 7372","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  #2 M.Tr 1차 GIS 보통점검(7372단독)","2025-11-06 09:00","2025-11-06 17:00","2025-11-06 09:00","2025-11-06 17:00","연속"]
[189,"충북","충주","신충주S/S CB 7471","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  신제천-신충주#2 T/L GIS 보통점검(7471단독)","2025-11-05 09:00","2025-11-05 17:00","2025-11-05 09:00","2025-11-05 17:00","연속"]
[190,"충북","충주","신충주S/S CB 7300","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  신제천-신충주#1T/L-#2M.Tr 1차 GIS 보통점검(7300단독)","2025-11-04 09:00","2025-11-04 17:00","2025-11-04 09:00","2025-11-04 17:00","연속"]
[191,"충북","충주","신충주S/S CB 7371","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S  신제천-신충주#1 T/L GIS 보통점검(7371단독)","2025-11-03 09:00","2025-11-03 17:00","2025-11-03 09:00","2025-11-03 17:00","연속"]
[192,"충북","충주","신충주S/S #1 BUS","신충주S/S  #70BUS 모선보호반 대체","신충주S/S  #70BUS 모선보호반 대체","2025-11-24 09:00","2025-11-27 18:00","취소","취소","연속"]
[193,"충북","충주","신제천신충주T#1 T/L","2025년 가공송전 순시점검 위탁공사"," 신제천-신충주#2T/L 과열개소 정비작업 간 작업자 안전을 위한 병가선로(하단) 휴전","2025-11-10 07:00","2025-11-10 18:00","취소","취소","연속"]
[194,"대전세종충남","대전","신계룡S/S #3 M.Tr","[취소시][가압X]신계룡S/S  #3M.Tr 보통점검","[취소시][가압X]신계룡S/S  #3M.Tr 보통점검","2025-11-17 09:00","2025-11-19 18:00","2025-11-17 09:00","2025-11-19 18:00","연속"]
[195,"대전세종충남","대전","신계룡S/S CB 7100","[취소시][가압X] 신계룡S/S 신계룡-청양T/L TIE GIS 보통점검","[취소시][가압X] 신계룡S/S 신계룡-청양T/L TIE GIS 보통점검","2025-11-19 09:00","2025-11-19 18:00","2025-11-19 09:00","2025-11-19 18:00","연속"]
[196,"대전세종충남","대전","신계룡S/S CB 7171","[취소시][가압X]신계룡S/S 신계룡-청양T/L GIS 보통점검","[취소시][가압X]신계룡S/S 신계룡-청양T/L GIS 보통점검","2025-11-20 09:00","2025-11-20 18:00","2025-11-20 09:00","2025-11-20 18:00","연속"]
[197,"대전세종충남","대전","신계룡S/S CB 7271","[취소시][가압X]신계룡S/S 신옥천-신계룡T/L GIS 보통점검","[취소시][가압X]신계룡S/S 신옥천-신계룡T/L GIS 보통점검","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","연속"]
[198,"대전세종충남","서산","당진T/P CB 7200","당진화력S/S  차단기 조작시험","(10월 휴전 취소시)(즉시가압 가능) 당진화력S/S #1 Tie.Tr 2차-2호기 1차 TIE CB 개폐타임 측정 및 조작시험","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[199,"대전세종충남","서산","신당진개폐소 CB 7D71","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진개폐소  7B BUS PT ,ES부 가스누기 보수공사 - 7D71 GIS 이용 무부하가압 예정으로 추가 휴전신청","2025-11-21 13:00","2025-11-21 14:00","2025-11-21 13:00","2025-11-21 14:00","연속"]
[200,"대전세종충남","서산","신당진개폐소 #7B BUS","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신당진개폐소  7B BUS PT ,ES부 가스누기 보수공사 - 7D71 GIS 이용 무부하가압 예정으로 추가 휴전신청","2025-11-17 09:30","2025-11-21 18:00","2025-11-17 09:30","2025-11-21 18:00","연속"]
[201,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~126(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 교차선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청 * 10월 휴전 승인시 취소 요청","2025-11-09 16:00","2025-11-09 20:00","취소","취소","연속"]
[202,"대전세종충남","서산","신당진개폐소북당진 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.126~127(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 병가선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청 * 10월 휴전 승인시 취소 요청","2025-11-09 08:00","2025-11-09 16:00","취소","취소","연속"]
[203,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-북당진T/L 병가 및  신당진개폐소-현대제철 교차구간,  신당진개폐소-북당진T/L 및 신당진개폐소-현대제철 모두 휴전 미승인시 휴전 취소 요청 * 10월 휴전 승인시 취소 요청","2025-11-09 08:00","2025-11-09 20:00","취소","취소","연속"]
[204,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","24~25 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-현대제철T/L 병가선로,  신당진개폐소-현대제철T/L 휴전 미승인시 휴전 취소 요청 * 10월 휴전 승인시 취소 요청","2025-11-08 08:00","2025-11-08 18:00","취소","취소","연속"]
[205,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#1T/L 병가선로,  신당진개폐소-태안화력#1T/L 휴전 미승인시 휴전 취소 요청 * 10월 휴전 승인시 취소 요청","2025-11-08 08:00","2025-11-08 18:00","취소","취소","연속"]
[206,"대전세종충남","서산","신당진S/S SEC CB 75760","신당진S/S  차단기 조작시험","(즉시가압 가능)신당진S/S  #75-#76 SEC CB 개폐타임 측정 및 조작시험","2025-11-20 09:00","2025-11-20 18:00","2025-11-20 09:00","2025-11-20 18:00","연속"]
[207,"대전세종충남","서산","신당진S/S CB 7771","신당진S/S  차단기 조작시험","(즉시가압 가능) 신당진S/S  신당진연락#2T/L CB 개폐타임 측정 및 조작시험","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[208,"대전세종충남","서산","신당진S/S CB 7171","신당진S/S  차단기 조작시험","(10월 휴전 취소시)(즉시가압 가능) 신당진S/S  7171T/L CB 개폐타임 측정 및 조작시험","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[209,"대전세종충남","서산","신당진S/S CB 7700","신당진S/S  차단기 조작시험","(즉시가압 가능) 신당진S/S  신당진연락#2-신서산#2T/L TIE CB 개폐타임 측정 및 조작시험","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[210,"대전세종충남","서산","신당진S/S CB 7471","신당진S/S  차단기 조작시험","(즉시가압 가능) 신당진S/S  신당진연락#1T/L CB 개폐타임 측정 및 조작시험","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[211,"대전세종충남","서산","신당진S/S SEC CB 70710","신당진S/S  차단기 조작시험","(즉시가압 가능)신당진S/S  #70-#71 SEC CB 개폐타임 측정 및 조작시험","2025-11-13 09:00","2025-11-13 18:00","2025-11-13 09:00","2025-11-13 18:00","연속"]
[212,"대전세종충남","서산","신서산S/S #4 Sh.R CB","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신서산S/S  7779 차단기 균압콘덴서 절연열화 진단","2025-11-12 09:30","2025-11-12 18:00","2025-11-12 09:30","2025-11-12 18:00","연속"]
[213,"대전세종충남","서산","신서산S/S #1 BUS","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신서산  7861 DS B상 가스누기 보수","2025-11-17 09:30","2025-11-21 18:00","취소","취소","연속"]
[214,"대전세종충남","서산","신서산S/S CB 7979","신서산S/S  차단기 조작시험","(즉시가압 가능) 신서산S/S  #5 Sh.R 7979CB 개폐타임 측정 및 조작시험","2025-11-26 09:00","2025-11-26 18:00","2025-11-26 09:00","2025-11-26 18:00","연속"]
[215,"대전세종충남","서산","태안T/P #1 M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 태안화력S/S  #1M.Tr 보호반 교체","2025-11-24 09:30","2025-11-28 18:00","2025-11-24 09:30","2025-11-28 18:00","연속"]
[216,"대전세종충남","서산","태안T/P CB 7300","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안T/P 3호기 7372, 7300 GIS 균압콘덴서 절연열화 측정","2025-11-05 09:30","2025-11-05 16:00","2025-11-05 09:30","2025-11-05 16:00","연속"]
[217,"대전세종충남","서산","태안T/P CB 7372","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안T/P 3호기 7372, 7300 GIS 균압콘덴서 절연열화 측정","2025-11-04 09:30","2025-11-04 16:00","2025-11-04 09:30","2025-11-04 16:00","연속"]
[218,"대전세종충남","서산","신서산태안TP#2 T/L","태안화력S/S  옥외 기타설비 내장화공사","(10월휴전취소시) (즉시가압불가) 태안화력S/S  신서산-태안화력#2T/L CVT 내장화공사","2025-11-10 09:00","2025-11-18 18:00","2025-11-10 09:00","2025-11-18 18:00","연속"]
[219,"대전세종충남","세종","세종S/S #2 M.Tr","[변전]25년 세종전력지사 변전협력회사 공사"," 변압기 F60제 보호계전기 64V 보호로직 개선","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[220,"대전세종충남","세종","세종S/S #3 M.Tr","[변전]25년 세종전력지사 변전협력회사 공사"," 변압기 F60제 보호계전기 64V 보호로직 개선","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[221,"대전세종충남","천안","신온양S/S CB 7971","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능_B/F PNL 대체 취소시)신온양S/S  신온양-신탕정#1T/L GIS 보통점검","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[222,"대전세종충남","천안","신온양신탕정#1 T/L","(10월 취소시)신온양S/S  신온양신탕정#1 T/L LA 교체","(10월 취소시)신온양S/S  신온양-신탕정#1 T/L LA 교체","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[223,"대전세종충남","천안","신온양신탕정#2 T/L","(10월 취소시) 신온양S/S #78B/F 보호배전반 교체","(10월 취소시)(즉시가압불가)(장기미교체대상)신온양S/S #78B/F 보호배전반 교체","2025-11-17 09:00","2025-11-20 18:00","취소","취소","연속"]
[224,"대전세종충남","천안","신온양서서울#1 T/L","(10월 취소시) 신온양S/S #78B/F 보호배전반 교체","(10월 취소시)(즉시가압불가)(장기미교체대상)신온양S/S #78B/F 보호배전반 교체","2025-11-17 09:00","2025-11-20 18:00","취소","취소","연속"]
[225,"대전세종충남","천안","신온양S/S CB 7871","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능_B/F PNL 대체 취소시)신온양S/S  신온양-서서울#1T/L GIS 보통점검","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[226,"대전세종충남","천안","신온양S/S #3 M.Tr","(10월취소시)25년 천안P/O 주변압기 정밀 및 보통점검공사","신온양S/S  #3M.Tr(A,C상) 보통점검","2025-11-21 09:00","2025-11-22 18:00","2025-11-21 09:00","2025-11-22 18:00","연속"]
[227,"대전세종충남","천안","신온양S/S #2 M.Tr","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능)신온양S/S 154kV #4Sh.C 1차 GIS 정밀점검(신온양S/S  #2M.Tr 안전이격 확보)","2025-11-10 09:00","2025-11-12 18:00","2025-11-10 09:00","2025-11-12 18:00","매일"]
[228,"대전세종충남","천안","신온양S/S CB 7671","(즉시가압가능)신온양S/S 청양-신온양#2T/L GIS 보통점검","(즉시가압가능)신온양S/S  청양-신온양#2T/L 7671 GIS 보통점검","2025-11-13 09:00","2025-11-13 18:00","2025-11-13 09:00","2025-11-13 18:00","연속"]
[229,"대전세종충남","천안","신온양S/S CB 7600","(즉시가압가능)신온양S/S 청양-신온양#2T/L-TIE GIS 보통점검","(즉시가압가능)신온양S/S  청양-신온양#2T/L -TIE 7600 GIS 보통점검","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[230,"대전세종충남","천안","신온양S/S CB 7700","(즉시가압가능)신온양S/S  7700 CB 개폐타임 측정","(즉시가압가능)신온양S/S 신온양-서서울#2T/L - #4M.Tr 1차 7700 CB 개폐타임 측정","2025-11-24 09:00","2025-11-24 18:00","2025-11-24 09:00","2025-11-24 18:00","연속"]
[231,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S  #77Bay B/F PNL 대체","(즉시가압불가)(장기미교체 대상)신온양S/S  #77Bay 노후 B/F PNL 대체","2025-11-23 09:00","2025-11-26 18:00","2025-11-23 09:00","2025-11-26 18:00","연속"]
[232,"대전세종충남","천안","신온양서서울#2 T/L","신온양S/S  #77Bay B/F PNL 대체","(즉시가압불가)(장기미교체 대상)신온양S/S  #77Bay 노후 B/F PNL 대체","2025-11-23 09:00","2025-11-26 18:00","2025-11-23 09:00","2025-11-26 18:00","연속"]
[233,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S  #4M.Tr 보통점검 및 불량 PT 교체공사","(77bay B/F반 휴전 취소시)신온양S/S  #4M.Tr 보통점검, #4M.Tr LA 보통점검, 부싱절연유 채유, 3차 PT GIS 교체","2025-11-24 09:00","2025-11-26 18:00","2025-11-24 09:00","2025-11-26 18:00","연속"]
[234,"대전세종충남","천안","신온양S/S CB 7771","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능_B/F PNL대체 취소시)신온양S/S  신온양-서서울#2T/L GIS 보통점검","2025-11-28 09:00","2025-11-28 18:00","2025-11-28 09:00","2025-11-28 18:00","연속"]
[235,"대전세종충남","천안","신탕정S/S #2 M.Tr","신탕정S/S  #72Bay B/F반 교체, #2M.Tr 정밀점검","(즉시가압불가)(장기미교체대상)신탕정S/S  72bay B/F 노후 보호배전반 대체 및 #2M.Tr B상 절연유 불량 관련 정밀점검","2025-11-06 09:00","2025-11-09 18:00","2025-11-06 09:00","2025-11-09 18:00","연속"]
[236,"대전세종충남","천안","신온양신탕정#1 T/L","신탕정S/S  #72bay B/F 노후 보호배전반 대체","(즉시가압불가)(장기미교체대상)신탕정S/S  #72bay B/F 노후 보호배전반 대체","2025-11-06 09:00","2025-11-09 18:00","2025-11-06 09:00","2025-11-09 18:00","연속"]
[237,"대전세종충남","천안","신탕정S/S #1 M.Tr","신탕정S/S  #71bay B/F반 교체, #1M.Tr 정밀점검","(즉시가압불가)(장기미교체대상)신탕정S/S  71B/F 보호반 교체공사+신탕정S/S  #1M.Tr 절연유 불량 관련 정밀점검","2025-11-13 09:00","2025-11-16 18:00","2025-11-13 09:00","2025-11-16 18:00","연속"]
[238,"대전세종충남","천안","북당진신탕정#1 T/L","신탕정S/S  #71bay B/F 노후 보호배전반 교체","신탕정S/S  #71bay B/F 노후 보호배전반 교체","2025-11-13 09:00","2025-11-16 18:00","취소","취소","연속"]
[239,"대전세종충남","천안","아산S/S #4 M.Tr","(10월 취소시)아산S/S  #4 M.Tr 부싱절연유 채유","(10월 취소시)아산S/S  #4 M.Tr 부싱절연유 채유","2025-11-27 09:00","2025-11-27 18:00","2025-11-27 09:00","2025-11-27 18:00","연속"]
[240,"대전세종충남","천안","아산S/S CB 7172","(즉시가압가능)아산S/S  7172 CB 개폐타임 측정","(9월 취소시)(즉시가압가능)아산S/S  아산-보령화력#2T/L 7172 CB 개폐타임측정","2025-11-04 08:00","2025-11-04 10:00","2025-11-04 08:00","2025-11-04 10:00","연속"]
[241,"대전세종충남","천안","아산S/S CB 7200","(9월취소시)(즉시가압가능)아산S/S 7200 CB 개폐타임 측정","(9월 취소시)(즉시가압가능)아산S/S 아산-화성 #2T/L - 아산-보령화력#1T/L TIE 7200 CB 개폐타임측정","2025-11-04 16:00","2025-11-04 18:00","2025-11-04 16:00","2025-11-04 18:00","연속"]
[242,"대전세종충남","천안","아산S/S #3 M.Tr","(10월취소시)25년 천안P/O 주변압기 정밀 및 보통점검공사","아산S/S  #3M.Tr(A,B,C상) 보통점검","2025-11-24 09:00","2025-11-26 18:00","2025-11-24 09:00","2025-11-26 18:00","연속"]
[243,"대전세종충남","천안","아산S/S #1 M.Tr","(10월취소시)25년 천안P/O 주변압기 정밀 및 보통점검공사","아산S/S  #1M.Tr(A,B,C상) 보통점검","2025-11-17 09:00","2025-11-19 18:00","2025-11-17 09:00","2025-11-19 18:00","연속"]
[244,"대전세종충남","천안","아산S/S CB 7400","(즉시가압가능)아산S/S  7400 CB 개폐타임 측정","아산S/S  아산-화성#1T/L-TIE 7400 CB 개폐타임 측정","2025-11-05 16:00","2025-11-05 18:00","2025-11-05 16:00","2025-11-05 18:00","연속"]
[245,"대전세종충남","천안","아산S/S CB 7271","(즉시가압가능)아산S/S  7271 CB 개폐타임 측정","아산S/S 아산-화성 #2T/L 7271 CB 개폐타임측정","2025-11-05 08:00","2025-11-05 10:00","2025-11-05 08:00","2025-11-05 10:00","연속"]
[246,"대전세종충남","청양","보령C/C CB 7171","[변전총액] 청양P/O 변전협력 총액공사","362kV 차단기 조작시험","2025-11-19 07:00","2025-11-19 08:30","취소","취소","연속"]
[247,"대전세종충남","청양","보령C/C CB 7200","[변전총액] 청양P/O 변전협력 총액공사","362kV 차단기 조작시험","2025-11-19 08:30","2025-11-19 10:00","취소","취소","연속"]
[248,"대전세종충남","청양","보령C/C CB 7172","[변전총액] 청양P/O 변전협력 총액공사","362kV GIS 보통점검","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[249,"대전세종충남","청양","보령C/C CB 7100","[변전총액] 청양P/O 변전협력 총액공사","362kV GIS 보통점검","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[250,"대전세종충남","청양","보령C/C CB 7272","[변전총액] 청양P/O 변전협력 총액공사","362kV 차단기 조작시험","2025-11-20 07:00","2025-11-20 08:30","2025-11-20 07:00","2025-11-20 08:30","연속"]
[251,"대전세종충남","청양","보령C/C CB 7271","[변전총액] 청양P/O 변전협력 총액공사","362kV 차단기 조작시험","2025-11-20 08:30","2025-11-20 10:00","2025-11-20 08:30","2025-11-20 10:00","연속"]
[252,"대전세종충남","청양","아산보령TP#2 T/L","[송전][즉시가압O] 아산-보령 등 4개T/L 항공구 설치공사"," 아산-보령화력#2T/L 항공구 설치공사","2025-11-03 08:00","2025-11-05 18:00","취소","취소","매일"]
[253,"대전세종충남","청양","보령T/P CB 7672","[변전총액] 청양P/O 변전협력 총액공사","362kV GIS 보통점검","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","연속"]
[254,"대전세종충남","청양","보령TP보령CC#1 T/L","[송전][즉시가압O] 장기사용 송전전선 건정성 점검","옥산-서천#2 등 6개T/L","2025-11-27 08:00","2025-11-07 18:00","취소","취소","연속"]
[255,"대전세종충남","청양","신옥천청양 T/L","[송전][즉시가압O] 신옥천-청양등8개T/L추락방지설치공사","[즉시가압O] 신옥천-청양 등 8개T/L 추락방지 설치공사","2025-11-03 07:00","2025-11-07 18:00","취소","취소","매일"]
[256,"대전세종충남","청양","청양보령TP#2 T/L","[변전총액] 청양P/O 변전협력 총액공사","362kV GIS 차단기 전자변 교체 및 CVT 보통점검","2025-11-28 09:00","2025-11-28 18:00","취소","취소","연속"]
[257,"대전세종충남","청양","청양S/S CB 7571","[변전총액] 청양P/O 변전협력 총액공사","362kV 차단기 조작시험","2025-11-24 08:30","2025-11-24 10:00","2025-11-24 08:30","2025-11-24 10:00","연속"]
[258,"전북","군산","군산S/S #1 M.Tr","군산P/O 주변압기 보통점검(중복)","주변압기 보통점검","2025-11-28 09:00","2025-11-28 18:00","2025-11-28 09:00","2025-11-28 18:00","연속"]
[259,"전북","군산","군산S/S #2 M.Tr","군산P/O 주변압기 정밀점검공사","주변압기 정밀점검공사","2025-11-17 09:00","2025-11-21 18:00","2025-11-17 09:00","2025-11-21 18:00","연속"]
[260,"전북","군산","군산S/S CB 7400","군산P/O  차단기 보통점검","○ 7400 CB 보통점검","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[261,"전북","군산","군산S/S CB 7500","군산P/O  차단기 보통점검","○ 7500 CB 보통점검","2025-11-05 09:00","2025-11-05 18:00","2025-11-05 09:00","2025-11-05 18:00","연속"]
[262,"전북","군산","새만금S/S CB 7271","24~25년 군산P/O 변전협력회사 총액공사","7271 CB A,B,C상 전자변 교체","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","연속"]
[263,"전북","군산","새만금S/S #2 M.Tr","주변압기 추락방지장치 설치공사(중복)","추락방지장치 설치공사","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[264,"전북","군산","새만금S/S CB 7372","군산P/O  차단기 보통점검","○ 7372 CB 보통점검","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[265,"전북","군산","새만금S/S CB 7200","24~25년 군산P/O 변전협력회사 총액공사","7200 CB A,B,C상 전자변 교체","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[266,"전북","군산","새만금S/S #1 Sh.R CB","새만금S/S #1Sh.R 고장복구공사(가압)","새만금S/S #1Sh.R 고장에 따른 복구공사 - Sh.R × 1대 철거, 설치 - GIB A상 × 1대 철거, 설치","2025-11-10 10:00","2025-11-11 10:00","2025-11-10 10:00","2025-11-11 10:00","연속"]
[267,"전북","김제","신김제S/S #1 M.Tr"," 신김제S/S  #1M.Tr OLTC 정밀점검"," 신김제S/S  #1M.Tr OLTC 정밀점검","2025-11-03 09:00","2025-11-05 18:00","2025-11-03 09:00","2025-11-05 18:00","연속"]
[268,"전북","김제","신김제S/S #3 M.Tr"," 김제전력지사 기타설비 점검공사"," 김제전력지사 기타설비 점검공사","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[269,"전북","김제","신김제S/S #2 M.Tr"," 신김제S/S  #2M.Tr 3차 GPT 교체공사"," 신김제S/S  #2M.Tr 3차 GPT 교체공사","2025-11-11 09:00","2025-11-11 18:00","2025-11-11 09:00","2025-11-11 18:00","연속"]
[270,"전북","김제","신김제S/S #4 M.Tr"," 신김제S/S  #4M.Tr 1차 피뢰기 대체공사"," 신김제S/S  #4M.Tr 1차 피뢰기 대체공사","2025-11-13 09:00","2025-11-13 18:00","2025-11-13 09:00","2025-11-13 18:00","연속"]
[271,"전북","직할","신남원한빛NP#2 T/L","  154kV 고창-영광T/L No.45~142 선종교체공사","  154kV 고창-영광T/L No.45~142 선종교체공사","2025-10-27 06:00","2025-11-21 18:00","취소","취소","연속"]
[272,"광주전남","강진","신강진S/S #3 M.Tr","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-11-03 08:00","2025-11-14 18:00","취소","취소","연속"]
[273,"광주전남","강진","신강진S/S #4 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","가. C상 가스검출계전기(96G) 수분 침투 관련 계전기 교체(경보 해소) ※ 거래소 요청 시 1시간 이내 가압 가능","2025-11-03 08:00","2025-11-03 18:00","2025-11-03 08:00","2025-11-03 18:00","연속"]
[274,"광주전남","강진","신강진광양#1 T/L","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-11-03 08:00","2025-11-14 18:00","취소","취소","연속"]
[275,"광주전남","강진","신화순신강진#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","신화순-신강진 수평추락방지장치 설치공사","2025-11-10 07:00","2025-12-12 18:00","취소","취소","매일"]
[276,"광주전남","강진","신강진S/S #3 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","1. 신강진S/S #3M.Tr  A,B,C OLTC 절연유 채유 ※ 거래소 요청 시 휴전일정 협의 가능","2025-11-11 08:00","2025-11-11 14:00","2025-11-11 08:00","2025-11-11 14:00","연속"]
[277,"광주전남","강진","신강진광양#2 T/L","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  75Bay B/F반 교체","2025-11-17 08:00","2025-11-28 18:00","취소","취소","연속"]
[278,"광주전남","강진","신강진S/S #4 M.Tr","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  75Bay B/F반 교체","2025-11-17 08:00","2025-11-28 18:00","취소","취소","연속"]
[279,"광주전남","광주","신광주한빛NP#2 T/L","신광주변전소 72BAY BF반 대체","신광주변전소 72BAY BF반 대체","2025-11-03 09:00","2025-11-07 18:00","취소","취소","연속"]
[280,"광주전남","광주","신남원신광주#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#1T/L 116~164호","2025-11-17 08:00","2025-11-21 18:00","취소","취소","매일"]
[281,"광주전남","광주","신광주S/S #1 M.Tr","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  #1M.Tr GIS 2차 보통점검","2025-11-20 09:00","2025-11-20 18:00","2025-11-20 09:00","2025-11-20 18:00","연속"]
[282,"광주전남","광주","신광주S/S #3 M.Tr","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  #3M.Tr GIS 2차 보통점검","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","연속"]
[283,"광주전남","광주","신남원신광주#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#2T/L 116~164호","2025-11-24 08:00","2025-11-28 18:00","취소","취소","매일"]
[284,"광주전남","광주","신광주S/S #2 M.Tr","'25년 광주전력지사 변전협력회사 공사","신광주S/S #2M.Tr 초기점검, 1차 GIS 조작시험, 2차 GIS 보통점검 1,3차 PT 초기점검, 1,2,3차 LA 보통점검, 2-1,2 Sh.R 보통점검","2025-11-24 09:00","2025-11-27 18:00","2025-11-24 09:00","2025-11-27 18:00","연속"]
[285,"광주전남","광주","신광주한빛NP#2 T/L","광주전력지사 변전협력회사 총액공사"," 신광주-한빛 #2T/L LA, CVT 보통점검","2025-11-27 08:00","2025-11-27 18:00","취소","취소","연속"]
[286,"광주전남","광주","신화순S/S #3 M.Tr","신화순변전소 75BAY BF반 대체","신화순변전소 75BAY BF반 대체","2025-11-17 09:00","2025-11-21 18:00","취소","취소","연속"]
[287,"광주전남","목포","한빛2N/P CB 7871","한빛4호기 계획예방정비(O/H) 휴전","한빛4호기 계획예방정비(O/H) 휴전","2025-11-20 09:00","2025-12-12 18:00","2025-11-20 09:00","2025-12-12 18:00","연속"]
[288,"광주전남","목포","한빛2N/P CB 7800","한빛4호기 계획예방정비(O/H) 휴전","한빛4호기 계획예방정비(O/H) 휴전","2025-11-20 09:00","2025-12-12 18:00","2025-11-20 09:00","2025-12-12 18:00","연속"]
[289,"광주전남","순천","광양C/C CB 7271","24-25년 순천전력지사 변전협력회사 공사","광양C/C 7271CB 조작시험","2025-11-24 09:00","2025-11-24 18:00","2025-11-24 09:00","2025-11-24 18:00","연속"]
[290,"광주전남","순천","광양C/C CB 7200","2025년 순천전력지사 362kV GIS 정밀점검","광양CC 7200CB 정밀점검","2025-11-17 09:00","2025-11-19 18:00","2025-11-17 09:00","2025-11-19 18:00","연속"]
[291,"광주전남","순천","광양C/C CB 7272","24-25년 순천전력지사 변전협력회사 공사","광양CC 7272 GIS 보통점검","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[292,"광주전남","순천","광양CC여수TP#2 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #2T/L 폴리머점퍼지지애자 설치","2025-11-07 07:00","2025-11-07 18:00","2025-11-07 07:00","2025-11-07 18:00","연속"]
[293,"광주전남","순천","광양CC여수TP#1 T/L"," 광양CC-여수TP T/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #1T/L 폴리머점퍼지지애자 설치","2025-11-03 07:00","2025-11-06 18:00","2025-11-03 07:00","2025-11-06 18:00","매일"]
[294,"광주전남","순천","광양광양CC#2 T/L"," 광양-광양CC T/L 폴리머점퍼지지애자 설치공사","광양-광양CC #2T/L 폴리머점퍼지지애자 설치","2025-11-24 07:00","2025-11-28 18:00","2025-11-24 07:00","2025-11-28 18:00","매일"]
[295,"광주전남","순천","광양S/S CB 7500","24-25년 순천전력지사 변전협력회사 공사","광양S/S 신강진-광양#2T/L(7500) GIS 초기점검","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[296,"광주전남","순천","광양여수TP T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가) ※휴일(8,9일) 미작업","2025-11-03 07:00","2025-11-14 18:00","2025-11-03 07:00","2025-11-14 18:00","매일"]
[297,"광주전남","순천","신강진광양#1 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치 ※주말(8,9일) 미작업","2025-11-03 07:00","2025-11-14 18:00","취소","취소","매일"]
[298,"광주전남","순천","신남원광양#1 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가) ※휴일(8,9일) 미작업","2025-11-03 07:00","2025-11-14 18:00","취소","취소","매일"]
[299,"광주전남","순천","광양S/S CB 7871","2025년 순천전력지사 362kV GIS 정밀점검","광양S/S 7871CB 정밀점검","2025-11-05 09:00","2025-11-07 18:00","2025-11-05 09:00","2025-11-07 18:00","연속"]
[300,"광주전남","순천","광양하동TP#2 T/L"," 광양-하동TP T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-11-10 07:00","2025-11-14 18:00","취소","취소","매일"]
[301,"광주전남","순천","광양S/S CB 7800","2025년 순천전력지사 362kV GIS 정밀점검","광양S/S 7800CB 정밀점검","2025-11-10 09:00","2025-11-12 18:00","2025-11-10 09:00","2025-11-12 18:00","연속"]
[302,"광주전남","순천","광양S/S CB 7771","24-25년 순천전력지사 변전협력회사 공사","광양S/S 광양-하동TP#2T/L(7771) GIS 보통점검","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[303,"광주전남","순천","광양S/S #2 M.Tr","광양S/S  #2M.Tr 부싱절연유 이상 관련 추적분석","광양S/S  #2M.Tr 부싱절연유 이상 관련 추적분석","2025-11-11 09:00","2025-11-11 18:00","2025-11-11 09:00","2025-11-11 18:00","연속"]
[304,"광주전남","순천","신남원광양#1 T/L","항공장애표시구 교체(신남원-광양#1)","항공장애표시구 교체","2025-11-12 09:00","2025-11-12 12:00","취소","취소","연속"]
[305,"광주전남","순천","광양S/S CB 7571","24-25년 순천전력지사 변전협력회사 공사","광양S/S 신강진-광양#2T/L(7571) GIS 초기점검","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[306,"광주전남","순천","신강진광양#2 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지시설 설치 ※주말(22,23일) 미작업","2025-11-17 07:00","2025-11-28 18:00","2025-11-17 07:00","2025-11-28 18:00","매일"]
[307,"광주전남","순천","신남원광양#2 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가) ※휴일(22,23일) 미작업","2025-11-17 07:00","2025-11-28 18:00","취소","취소","매일"]
[308,"광주전남","순천","광양광양CC#1 T/L"," 광양-광양CC T/L 폴리머점퍼지지애자 설치공사","광양-광양CC #1T/L 폴리머점퍼지지애자 설치","2025-11-17 07:00","2025-11-21 18:00","취소","취소","매일"]
[309,"광주전남","순천","광양율촌CC T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가) ※휴일(22,23일) 미작업","2025-11-17 07:00","2025-11-28 18:00","취소","취소","매일"]
[310,"광주전남","순천","여수T/P #3 M.Tr","2025년 순천전력지사  M.Tr 정밀점검공사","여수화력S/S  #3M.Tr 정밀점검","2025-11-17 09:00","2025-11-21 18:00","취소","취소","연속"]
[311,"광주전남","순천","여수T/P #2 M.Tr","24-25년 순천전력지사 변전협력회사 공사","3차 DS과열관련 조치","2025-11-12 09:00","2025-11-13 18:00","2025-11-12 09:00","2025-11-13 18:00","연속"]
[312,"광주전남","순천","여수T/P CB 7200","24-25년 순천전력지사 변전협력회사 공사","여수화력S/S 7200CB 조작시험","2025-11-26 09:00","2025-11-26 18:00","2025-11-26 09:00","2025-11-26 18:00","연속"]
[313,"광주전남","순천","여수T/P CB 7272","24-25년 순천전력지사 변전협력회사 공사","여수화력S/S 7272CB 조작시험","2025-11-27 09:00","2025-11-27 18:00","2025-11-27 09:00","2025-11-27 18:00","연속"]
[314,"광주전남","순천","여수T/P CB 7171","24-25년 순천전력지사 변전협력회사 공사","여수화력S/S 7171CB 조작시험","2025-11-24 09:00","2025-11-24 18:00","2025-11-24 09:00","2025-11-24 18:00","연속"]
[315,"광주전남","순천","여수T/P CB 7271","24-25년 순천전력지사 변전협력회사 공사","여수화력S/S 7271CB 조작시험","2025-11-25 09:00","2025-11-25 18:00","2025-11-25 09:00","2025-11-25 18:00","연속"]
[316,"광주전남","순천","여수T/P #1 M.Tr","24-25년 순천전력지사 변전협력회사 공사","여수화력S/S #1M.Tr,B상 1차부싱 대체","2025-11-03 09:00","2025-11-07 18:00","2025-11-03 09:00","2025-11-07 18:00","연속"]
[317,"광주전남","순천","율촌C/C CB 7272","24-25년 순천전력지사 변전협력회사 공사","율촌CC 7272 CB 조작시험","2025-11-05 09:00","2025-11-05 18:00","2025-11-05 09:00","2025-11-05 18:00","연속"]
[318,"광주전남","순천","율촌C/C CB 7271","24-25년 순천전력지사 변전협력회사 공사","율촌CC 7271 CB 조작시험","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[319,"광주전남","순천","율촌C/C CB 7200","24-25년 순천전력지사 변전협력회사 공사","율촌CC 7200 CB 조작시험","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[320,"대구","달성","고령의령#1 T/L"," 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 고령-의령#1T/L 피뢰기 및 조류착지방지장치 설치 - 주말간 환원(11/29~30)","2025-11-24 07:00","2025-12-02 18:00","취소","취소","연속"]
[321,"대구","달성","서대구고령#2 T/L","24~25년 달성전력지사 가공송전 협력회사공사(안전확보)"," 고령-의령#1T/L 소도체 이도조정(155~156호) 작업관련 안전확보","2025-11-25 07:00","2025-11-25 18:00","2025-11-25 07:00","2025-11-25 18:00","연속"]
[322,"대구","달성","고령의령#1 T/L","24~25년 달성전력지사 가공송전 협력회사공사"," 고령-의령#1T/L 소도체 이도조정(155~156호)","2025-11-25 07:00","2025-11-25 18:00","2025-11-25 07:00","2025-11-25 18:00","연속"]
[323,"대구","달성","북경남대구#2 T/L","대구SS 북경남-대구#2T/L PT,LA하자점검","대구SS 북경남-대구#2T/L PT,LA하자점검","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[324,"대구","칠곡","서대구S/S #2 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2025-11-03 08:00","2025-11-11 18:00","2025-11-03 08:00","2025-11-11 18:00","연속"]
[325,"대구","칠곡","서대구S/S #3 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2025-11-17 08:00","2025-11-25 18:00","2025-11-17 08:00","2025-11-25 18:00","연속"]
[326,"대구","포항","신영일S/S #3 M.Tr","2024~25년도 포항전력지사 변전협력회사 공사","신영일S/S #3M.Tr 7572, 7500 GIS 조작시험, 1차 LA, 2차 LA, 3차 LA 하자점검, 3차 GIS 조작시험","2025-11-24 09:00","2025-11-25 18:00","2025-11-24 09:00","2025-11-25 18:00","연속"]
[327,"대구","포항","울주월성NP#2 T/L","154kV 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 울주-월성NP#2T/L 추락방지장치 설치","2025-11-25 07:00","2025-12-09 18:00","2025-11-25 07:00","2025-12-09 18:00","연속"]
[328,"대구","포항","동울산월성NP T/L","2024~2025년 포항전력지사 변전협력회사 공사","7371 GIS 조작시험, PT 보통점검","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[329,"경북","영주","신영주S/S #2 BUS","2025년 영주전력지사  GIS 정밀점검공사","-7200CB 정밀점검 후 #2BUS 이용 무부하가압","2025-11-27 09:00","2025-11-27 18:00","취소","취소","연속"]
[330,"경북","영주","신영주S/S CB 7300","2025년 영주전력지사  GIS 정밀점검공사","-7300CB GIS 정밀점검","2025-11-24 09:00","2025-11-27 18:00","2025-11-24 09:00","2025-11-27 18:00","연속"]
[331,"경북","영주","신영주S/S #2 M.Tr","2024-25년 영주전력지사 변전협력회사 총액공사","보호반 대체","2025-11-03 09:00","2025-11-08 18:00","2025-11-03 09:00","2025-11-08 18:00","연속"]
[332,"경북","영주","신영주S/S CB 7371","2025년 영주전력지사  GIS 정밀점검공사","-7371CB 정밀점검","2025-11-10 09:00","2025-11-13 18:00","2025-11-10 09:00","2025-11-13 18:00","연속"]
[333,"경북","영주","신영주S/S CB 7271","2025년 영주전력지사  GIS 정밀점검","-7271CB GIS 정밀점검","2025-11-10 09:00","2025-11-13 18:00","2025-11-10 09:00","2025-11-13 18:00","연속"]
[334,"경북","영주","신영주S/S CB 7900","2025년 영주전력지사  GIS 정밀점검공사","-7952DS 누기 개소 보수(추가공사)","2025-11-10 09:00","2025-11-11 18:00","2025-11-10 09:00","2025-11-11 18:00","연속"]
[335,"경북","영주","신영주S/S #3 M.Tr","24~25년 영주전력지사 변전협력회사공사","- #3M.Tr 보호반대체","2025-11-10 09:00","2025-11-15 18:00","2025-11-10 09:00","2025-11-15 18:00","연속"]
[336,"경북","영주","신영주S/S #1 BUS","2025년 영주전력지사  GIS 정밀점검","-7271CB 정밀점검 후 #1BUS 이용 무부하가압","2025-11-13 14:00","2025-11-13 18:00","취소","취소","연속"]
[337,"경북","영주","신영주S/S #1 M.Tr","24~25년 영주전력지사 변전협력회사공사","- CB 조작시험 - 3차 CB 조작시험 - 2차 LA 하자점검(A,B,C) - Sh.R 1-1 보통점검 및 CB, DS 보통점검 - Sh.R 1-2 보통점검 및 CB 조작시험 및 DS 보통점검","2025-11-17 09:00","2025-11-20 18:00","2025-11-17 09:00","2025-11-20 18:00","연속"]
[338,"경북","영주","신영주S/S CB 7200","2025년 영주전력지사  GIS 정밀점검공사","-7200CB 정밀점검","2025-11-24 09:00","2025-11-27 18:00","2025-11-24 09:00","2025-11-27 18:00","연속"]
[339,"경북","영주","한울#1N/P CB 7372","2025년 영주전력지사  GIS 정밀점검","-7372CB GIS 정밀점검","2025-11-24 09:00","2025-11-26 18:00","2025-11-24 09:00","2025-11-26 18:00","연속"]
[340,"경북","영주","삼척GP한울NP#1 T/L","2025년 영주전력지사  GIS 정밀점검공사","-7300CB 정밀점검 후 #1BUS 이용 무부하가압시 T/L 정전고장 방지","2025-11-29 14:00","2025-11-29 18:00","2025-11-29 14:00","2025-11-29 18:00","연속"]
[341,"경북","영주","한울#1N/P #1 BUS","2025년 영주전력지사  GIS 정밀점검공사","-7300CB 정밀점검 후 #1BUS 이용 무부하가압","2025-11-29 14:00","2025-11-29 18:00","2025-11-29 14:00","2025-11-29 18:00","연속"]
[342,"경북","영주","한울#1N/P CB 7300","2025년 영주전력지사  GIS 정밀점검공사","-7300CB GIS 정밀점검","2025-11-27 09:00","2025-11-29 18:00","2025-11-27 09:00","2025-11-29 18:00","연속"]
[343,"경북","영주","삼척GP한울NP#1 T/L","2025년 영주전력지사  GIS 정밀점검공사","-7372CB 정밀점검 후 삼척GP-한울NP#1 #1T/L 이용 무부하가압(4시간)","2025-11-01 14:00","2025-11-01 18:00","취소","취소","연속"]
[344,"경북","영주","한울#1N/P #2 BUS","2025년 영주전력지사  GIS 정밀점검","-7372CB 정밀점검 후 #2BUS 이용 무부하가압","2025-11-26 14:00","2025-11-26 18:00","2025-11-26 14:00","2025-11-26 18:00","연속"]
[345,"경북","영주","한울2NP한울3NP#4 T/L","24~25년 영주전력지사 변전협력회사 공사","7G02,62DS ASSY 교체","2025-11-10 09:00","2025-11-14 18:00","취소","취소","연속"]
[346,"경북","직할","청송PP면봉산풍력 T/L"," 청송분기T/L 불량애자 교체공사","-  청송PP면봉산풍력T/L 불량애자 교체","2025-11-26 09:00","2025-12-16 18:00","2025-11-26 09:00","2025-12-16 18:00","매일"]
[347,"경북","직할","청송P/P CB 7172","24~25년 경북본부 직할 변전협력회사 공사","GIS 보통점검(7172) 및 7122 모터 불량 조치","2025-11-24 09:00","2025-11-24 18:00","2025-11-24 09:00","2025-11-24 18:00","연속"]
[348,"경북","직할","청송P/P CB 7100","24~25년 경북본부 직할 변전협력회사 공사","7122 모터 불량 조치","2025-11-24 09:00","2025-11-24 18:00","2025-11-24 09:00","2025-11-24 18:00","연속"]
[349,"부산울산","동부산","고리N/P CB 7B72","고리NP S/Y  7B B/F PNL 대체","고리NP S/Y  7B B/F PNL 대체","2025-11-29 09:00","2025-12-03 18:00","2025-11-29 09:00","2025-12-03 18:00","연속"]
[350,"부산울산","동부산","신양산고리NP#2 T/L"," 신양산-고리NP 등 6개T/L 송전정비공사","-  신양산-고리NPT/L 스페이서댐퍼교체공사","2025-11-24 07:00","2025-11-29 18:00","취소","취소","연속"]
[351,"부산울산","동부산","신양산S/S #2 BUS","신양산S/S  용량부족 차단기 교체공사","#2BUS 철거, #75-76BUS SEC 설치","2025-11-24 08:00","2026-03-31 18:00","2025-11-24 08:00","2026-03-31 18:00","연속"]
[352,"부산울산","동부산","신양산신대연#2 T/L","동부산전력 가공송전협력회사 공사","금구류 설치","2025-11-21 07:00","2025-11-21 18:00","2025-11-21 07:00","2025-11-21 18:00","연속"]
[353,"부산울산","동부산","신양산신대연#1 T/L","동부산전력 가공송전협력회사 공사","금구류 설치","2025-11-19 07:00","2025-11-20 18:00","2025-11-19 07:00","2025-11-20 18:00","연속"]
[354,"부산울산","북부산","신김해북부산#1 T/L","24-25 북부산 변전협력회사 총액공사","북부산 73BAY B/F PNL 대체","2025-11-22 08:00","2025-11-26 18:00","취소","취소","연속"]
[355,"부산울산","북부산","북부산신울산#1 T/L"," 북부산-고리NP 등 7개T/L 송전보강공사"," 북부산-신울산#1T/L 85~87호 항공장애표시구 설치","2025-11-27 07:30","2025-11-27 18:00","2025-11-11 07:30","2025-11-11 18:00","연속"]
[356,"부산울산","북부산","북부산신울산#2 T/L"," 북부산-고리NP 등 7개T/L 송전보강공사"," 북부산-신울산#2T/L 85~87호 항공장애표시구 설치","2025-11-28 07:30","2025-11-28 18:00","2025-11-12 07:30","2025-11-12 18:00","연속"]
[357,"부산울산","북부산","북부산고리NP#2 T/L","24-25 북부산 변전협력회사 총액공사","1. 북부산 73BAY B/F PNL 대체 2. (송전병행) 상부재보강, SD댐퍼설치철거, 애자증결, 이도장력조절 등 - 최지수 3. (송전병행) 폴리머점퍼지지애자 설치( 북부산-고리NP#2 No.13,22,25,36,54) - 홍지완","2025-11-22 08:00","2025-11-26 18:00","2025-11-24 08:00","2025-11-28 18:00","연속"]
[358,"부산울산","북부산","북부산S/S #3 M.Tr","24-25 북부산 변전협력회사 총액공사","북부산  77BAY B/F PNL 대체 (신양산-북부산#2T/L 기휴전중 ~11/18)","2025-11-03 08:00","2025-11-07 18:00","취소","취소","연속"]
[359,"부산울산","북부산","북부산S/S #4 M.Tr","24-25 북부산 변전협력회사 총액공사","북부산  #4M.Tr 부싱 절연유 채유(추적관찰), 추락방지장치설치","2025-11-20 09:00","2025-11-20 18:00","2025-11-03 08:00","2025-11-03 18:00","연속"]
[360,"부산울산","북부산","북부산고리NP#1 T/L","24-25 북부산 변전협력회사 총액공사","1. 북부산 75BAY B/F PNL 대체 2. (송전병행) 상부재보강, SD댐퍼설치철거, 애자증결, 이도장력조절 등 - 최지수 3. (송전병행) 폴리머점퍼지지애자 설치( 북부산-고리NP#1 No.13,25,36,54) - 홍지완","2025-11-30 08:00","2025-12-04 18:00","2025-11-19 08:00","2025-11-23 18:00","연속"]
[361,"부산울산","북부산","북부산S/S #2 M.Tr","24-25 북부산 변전협력회사 총액공사","북부산 75BAY B/F PNL 대체","2025-11-30 08:00","2025-12-04 18:00","2025-11-19 08:00","2025-11-23 18:00","연속"]
[362,"부산울산","서부산","서부산S/S #2 M.Tr","서부산S/S  #2 M.Tr 3차 현대화공사","서부산S/S  #2 M.Tr 3차 현대화공사","2025-11-24 09:00","2025-11-24 18:00","2025-11-24 09:00","2025-11-24 18:00","연속"]
[363,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S  7300,7372 GIS 동작시험","신녹산S/S  7300,7372 GIS 동작시험 병행 : 3차 피뢰기 보통점검","2025-11-19 09:00","2025-11-19 18:00","2025-11-19 09:00","2025-11-19 18:00","연속"]
[364,"부산울산","서부산","신녹산S/S CB 7371","신녹산S/S  7371 GIS 동작시험","신녹산S/S  7371 GIS 동작시험","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[365,"부산울산","서부산","신녹산S/S CB 7271","신녹산S/S  7271 GIS 동작시험","신녹산S/S  7271 GIS 동작시험","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[366,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S  #1M.Tr 증설공사"," #1M.Tr 1차측 2CB 증설(#2BUS부 무부하시험가압, 7152DS 개방)","2025-11-06 08:00","2025-11-07 08:00","2025-11-06 08:00","2025-11-07 08:00","연속"]
[367,"부산울산","서부산","신녹산S/S #2 BUS","신녹산S/S  #1M.Tr 증설공사"," #1M.Tr 1차측 2CB 무부하 시험가압(1H) / 7152DS 투입","2025-11-28 08:00","2025-11-28 09:00","2025-11-28 08:00","2025-11-28 09:00","연속"]
[368,"부산울산","서부산","신김해신녹산#1 T/L","신녹산S/S  #1M.Tr 증설공사"," #1M.Tr 1차측 2CB, #1M.Tr, 6144GIS 무부하 시험가압(26H) / 7151DS 투입","2025-11-27 07:00","2025-11-28 09:00","2025-11-27 07:00","2025-11-28 09:00","연속"]
[369,"부산울산","서부산","신녹산S/S #3 M.Tr","신녹산S/S  #1M.Tr 증설공사"," #1M.Tr 1차측 2CB 무부하 시험가압(1H) / 7152DS 투입","2025-11-28 08:00","2025-11-28 09:00","2025-11-28 08:00","2025-11-28 09:00","연속"]
[370,"부산울산","서부산","신녹산S/S #2 M.Tr","신녹산S/S  #2 M.Tr 2차 GIS 보통점검","신녹산S/S  #2 M.Tr 2차 GIS 보통점검 병행 : 7200,7272 GIS 동작시험, 3차 피뢰기 보통점검","2025-11-20 09:00","2025-11-21 18:00","2025-11-20 09:00","2025-11-21 18:00","연속"]
[371,"부산울산","서부산","신녹산S/S #1 BUS","신녹산S/S  #1M.Tr 증설공사"," #1M.Tr 1차측 2CB, #1M.Tr, 6144GIS 무부하시험가압(26H)","2025-11-27 07:00","2025-11-28 09:00","2025-11-27 07:00","2025-11-28 09:00","연속"]
[372,"부산울산","울산","남울산S/S #2 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","B상 누설전류 진단","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[373,"부산울산","울산","동울산S/S #3 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","- 부싱절연유 채유, 변압기 추락방지 장치 설치","2025-11-20 09:00","2025-11-20 18:00","2025-11-20 09:00","2025-11-20 18:00","연속"]
[374,"부산울산","울산","동울산S/S #2 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","- 부싱절연유 채유, 변압기 추락방지 장치 설치","2025-11-19 09:00","2025-11-19 18:00","2025-11-19 09:00","2025-11-19 18:00","연속"]
[375,"부산울산","울산","신울산고리NP#2 T/L","2025년 가공송전 순시점검 위탁공사"," 신울산-고리NP#2T/L 정밀점검 1~63호","2025-11-03 09:00","2025-11-07 18:00","2025-11-03 09:00","2025-11-07 18:00","연속"]
[376,"부산울산","울산","신울산S/S #1 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","- A상 1, 2차 부싱절연유 채유 - 2차 피뢰기 대체","2025-11-17 09:00","2025-11-17 18:00","2025-11-10 09:00","2025-11-22 18:00","연속"]
[377,"부산울산","울산","신울산S/S #5 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#5M.Tr) 2회선구간 개착식 관로 굴착 및 가시설 설치, 메사쉴드 발진구 굴착 및 가시설, 발진대 설치","2025-11-18 09:00","2025-11-29 18:00","2025-11-08 08:00","2025-11-08 18:00","연속"]
[378,"부산울산","울산","신울산고리NP#1 T/L"," 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치( 신울산-고리NP#1 No.10,14,35,42,54,55)","2025-11-19 07:00","2025-11-20 18:00","취소","취소","연속"]
[379,"부산울산","울산","신울산S/S #2 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#2M.Tr) 2회선구간 개착식 관로 가시설 설치 그라우팅","2025-11-03 09:00","2025-11-14 18:00","2025-11-03 09:00","2025-11-08 18:00","연속"]
[380,"부산울산","울산","울주S/S #2 BUS"," 울주S/S 장기사용 GIS 교체공사","울주S/S 7A Bay 장기사용 GIS 교체","2025-11-03 08:00","2025-11-18 18:00","2025-11-03 08:00","2025-11-18 18:00","연속"]
[381,"부산울산","울산","울주울산TP#2 T/L"," 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치( 울주-울산TP#2)","2025-11-24 07:00","2025-11-27 18:00","2025-11-24 07:00","2025-11-27 18:00","연속"]
[382,"부산울산","울산","울주S/S #2 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","2차 GIS 부분방전관련 조치작업","2025-11-20 09:00","2025-11-21 18:00","2025-11-20 09:00","2025-11-21 18:00","연속"]
[383,"부산울산","울산","울주신경산#1 T/L"," 울주S/S 장기사용 GIS 교체공사","울주S/S 7A Bay 장기사용 GIS 교체(시험가압선로)","2025-11-17 08:00","2025-11-18 18:00","2025-11-17 08:00","2025-11-18 18:00","연속"]
[384,"부산울산","울산","울주울산TP#1 T/L"," 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치( 울주-울산TP#1)","2025-11-19 07:00","2025-11-22 18:00","2025-11-19 07:00","2025-11-22 18:00","연속"]
[385,"부산울산","직할","신대연S/S #1 M.Tr","25년 신대연S/S  GIS 정밀점검공사(7172)","신대연S/S  7172 GIS 정밀점검(시험가압용)","2025-11-12 17:00","2025-11-12 18:00","2025-11-12 17:00","2025-11-12 18:00","연속"]
[386,"부산울산","직할","신양산신대연#1 T/L","25년 신대연S/S  GIS 정밀점검공사(7172)","신대연S/S  7172 GIS 정밀점검(시험가압용)","2025-11-12 17:00","2025-11-12 18:00","2025-11-12 17:00","2025-11-12 18:00","연속"]
[387,"부산울산","직할","신대연S/S #2 BUS","24-25년 직할 변전협력회사공사","신대연S/S #75BUS 모선보호반 대체","2025-11-27 09:00","2025-12-01 18:00","2025-11-27 09:00","2025-12-01 18:00","연속"]
[388,"부산울산","직할","신대연S/S CB 7172","25년 신대연S/S  GIS 정밀점검공사(7172)","신대연S/S  7172 GIS 정밀점검","2025-11-09 09:00","2025-11-12 18:00","2025-11-09 09:00","2025-11-12 18:00","연속"]
[389,"경남","김해송변전부","신김해신녹산#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사","수평추락방지장치 설치","2025-11-01 07:00","2025-11-02 18:00","2025-11-01 07:00","2025-11-02 18:00","매일"]
[390,"경남","김해송변전부","신김해S/S #2 M.Tr","신김해S/S  #2M.Tr 3차측 현대화공사","신김해S/S  #2M.Tr 3차측 현대화공사","2025-11-03 09:00","2025-12-05 18:00","취소","취소","연속"]
[391,"경남","김해송변전부","신김해북부산#2 T/L","25년도 OPGW 취약개소 금구류 정비공사","OPGW 금구류 정비 23기","2025-11-08 07:00","2025-11-09 18:00","2025-11-08 07:00","2025-11-09 18:00","매일"]
[392,"경남","김해송변전부","신김해북부산#2 T/L","25년도 OPGW 취약개소 금구류 정비공사","OPGW 금구류 정비 : 23개소","2025-11-15 07:00","2025-11-16 18:00","2025-11-15 07:00","2025-11-16 18:00","매일"]
[393,"경남","직할","창원신고성#1 T/L"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사","2025-11-03 07:00","2025-11-11 18:00","취소","취소","연속"]
[394,"경남","직할","창원신고성#2 T/L"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사","2025-11-12 07:00","2025-11-20 18:00","취소","취소","연속"]
[395,"경남","직할","창원신고성#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해-창원T/L 폴리머지지애자 설치 (안전이격)","2025-11-23 07:00","2025-11-23 18:00","2025-11-23 07:00","2025-11-23 18:00","매일"]
[396,"경남","직할","신김해창원#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해-창원T/L 폴리머지지애자 설치","2025-11-23 07:00","2025-11-23 18:00","2025-11-23 07:00","2025-11-23 18:00","매일"]
[397,"경남","진주","고령의령#2 T/L"," 고령-의령#2T/L 철탑 수평 추락방지장치 설치공사"," 고령-의령#2T/L 39호 등 48기 와이어형 수평 추락방지장치 설치공사","2025-11-08 07:00","2025-11-14 18:00","취소","취소","매일"]
[398,"경남","진주","고령의령#1 T/L"," 고령-의령#1T/L 철탑 수평 추락방지장치 설치공사"," 고령-의령#1T/L 39호 등 48기 와이어형 수평 추락방지장치 설치공사","2025-11-01 07:00","2025-11-07 18:00","취소","취소","매일"]
[399,"경남","진주","고령의령#1 T/L"," 고령-의령#1T/L 철탑 수평 추락방지장치 설치공사"," 고령-의령#1T/L 39호 등 48기 와이어형 수평 추락방지장치 설치공사","2025-11-15 07:00","2025-11-16 18:00","취소","취소","매일"]
[400,"경남","진주","고령의령#2 T/L","의령S/S  고령-의령#2T/L LA 보통점검 등","의령S/S  고령-의령#2T/L LA 보통점검 유압저하경보(B,C상) 확인","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[401,"경남","진주","고령의령#1 T/L","의령S/S  고령-의령#1T/L LA,PT 보통점검","의령S/S  고령-의령#1T/L LA(A,B,C),PT(A,B,C) 보통점검","2025-11-21 09:00","2025-11-21 15:00","2025-11-21 09:00","2025-11-21 15:00","연속"]
[402,"경남","진주","고령의령#2 T/L"," 고령-의령#2T/L 철탑 수평 추락방지장치 설치공사"," 고령-의령#2T/L 39호 등 48기 와이어형 수평 추락방지장치 설치공사","2025-11-22 07:00","2025-11-23 18:00","취소","취소","매일"]
[403,"경남","진주","고령의령#1 T/L"," 고령-의령#1T/L 철탑 수평 추락방지장치 설치공사"," 고령-의령#1T/L 39호 등 48기 와이어형 수평 추락방지장치 설치공사","2025-11-29 07:00","2025-11-30 18:00","취소","취소","매일"]
[404,"경남","진주","하동T/P CB 7600","하동T/P 7472, 7600, 7672 GIS 조작시험","하동T/P 7472, 7600, 7672 GIS 조작시험","2025-11-14 13:00","2025-11-14 15:00","2025-11-14 13:00","2025-11-14 15:00","연속"]
[405,"경남","진주","하동T/P CB 7672","하동T/P 7472, 7600, 7672 GIS 조작시험","하동T/P 7472, 7600, 7672 GIS 조작시험","2025-11-14 15:00","2025-11-14 17:00","2025-11-14 15:00","2025-11-14 17:00","연속"]
[406,"경남","진주","하동T/P CB 7472","하동T/P 7472, 7600, 7672 GIS 조작시험","하동T/P 7472, 7600, 7672 GIS 조작시험","2025-11-14 10:00","2025-11-14 13:00","2025-11-14 10:00","2025-11-14 13:00","연속"]
[407,"경남","통영","창원신고성#1 T/L"," 창원-신고성#1T/L 추락방지장치 설치공사"," 창원-신고성#1T/L 추락방지장치 설치공사","2025-11-03 07:00","2025-11-07 18:00","취소","취소","매일"]
[408,"경남","통영","신고성S/S  예비 M.Tr","신고성SS  예비M.Tr 부싱 절연유 채유","신고성SS  예비M.Tr 부싱 절연유 채유","2025-11-07 09:30","2025-11-07 18:00","취소","취소","연속"]
[409,"경남","통영","창원신고성#2 T/L"," 창원-신고성#2T/L 추락방지장치 설치공사"," 창원-신고성#2T/L 추락방지장치 설치공사","2025-11-10 07:00","2025-11-14 18:00","취소","취소","매일"]
[410,"경남","통영","신고성S/S #1 M.Tr","신고성SS  #1M.Tr 2차 GIS 조작시험 등","1. #1M.Tr 2차 GIS 조작시험 2. 부싱 절연유 채유 및 도블 측정(H1,X1) 3. 3차 BUS 보통점검(예비용 금구류 철거) 4. 3차 VCB, Sh.R 보통점검 5. 염해방지 애자절연 코팅","2025-11-18 09:30","2025-11-21 18:00","2025-11-18 09:30","2025-11-21 18:00","연속"]
[411,"경남","통영","신고성S/S #4 M.Tr","신고성SS  #4M.Tr 보통점검 등","1. #4M.Tr 보통점검 2. 2차 GIS 조작시험 3. 1,2차 LA A~C상 초기점검 4. 3차 BUS 보통점검(예비용 금구류 철거) 5. 3차 PT A~C상 보통점검 6. 부싱절연유 채유 및 도블 측정(H1, X1) 7. 염해방지 애자절연 코팅","2025-11-24 09:30","2025-11-27 18:00","2025-11-24 09:30","2025-11-27 18:00","연속"]
[412,"경남","함안","북경남서대구#2 T/L","765kV 북경남S/S #2M.Tr 증설공사","증설 #2M.Tr 시험 가압","2025-11-27 09:00","2025-11-28 18:00","2025-11-27 09:00","2025-11-28 18:00","연속"]
[413,"경남","함안","신마산신고성#1 T/L"," 신마산-신고성#1T/L 철탑추락방지장치 설치공사"," 신마산-신고성#1T/L 수직 및 수평 추락방지장치 설치(1~82호,132호)","2025-11-03 07:00","2025-11-16 18:00","2025-11-03 07:00","2025-11-16 18:00","매일"]
[414,"경남","함안","신마산신고성#2 T/L"," 신마산-신고성#2T/L 철탑추락방지장치 설치공사"," 신마산-신고성#2T/L 수직 및 수평 추락방지장치 설치(1~82호,132호)","2025-11-17 07:00","2025-11-30 18:00","2025-11-17 07:00","2025-11-30 18:00","매일"]
[415,"경남","함안","신마산신김해#1 T/L","신마산S/S  신마산-신김해#1 T/L B상 접지본드 과열 조치","신마산S/S  신마산신김해#1 T/L B상 접지본드 과열 조치","2025-11-04 09:30","2025-11-04 17:30","2025-11-04 09:30","2025-11-04 17:30","연속"]
[416,"경남","함안","신마산신고성#2 T/L","신마산S/S  신마산-신고성#2 T/L B상 접지본드 과열 조치","신마산S/S  신마산신고성#2 T/L B상 접지본드 과열 조치","2025-11-05 09:30","2025-11-05 17:30","취소","취소","연속"]
[417,"경남","함안","의령신마산#2 T/L","신마산S/S  의령-신마산#2 T/L B상 접지본드 과열 조치","신마산S/S  의령-신마산#2 T/L B상 접지본드 과열 조치","2025-11-06 16:30","2025-11-06 18:30","2025-11-06 16:30","2025-11-06 18:30","연속"]
[418,"경남","함안","의령신마산#1 T/L","신마산S/S  의령-신마산#1 T/L B상 접지본드 과열 조치등","신마산S/S  의령-신마산#1 T/L B상 접지본드 과열 조치 등","2025-11-07 16:30","2025-11-07 18:30","2025-11-07 16:30","2025-11-07 18:30","연속"]
[419,"경남","함안","신마산신김해#1 T/L","25년도 OPGW 취약개소 금구류 정비공사","OPGW 금구류 정비 : 23개소","2025-11-15 14:00","2025-11-15 18:00","2025-11-15 14:00","2025-11-15 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":928,"n_cols":12,"rows_kept":928,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2025년도 11월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","광장S/S CB 6100","2025 성동전력지사 변전협력회사 공사","- 효성제 170kV GIS 노후 전자변 교체","2025-11-05 09:00","2025-11-05 18:00","2025-11-05 09:00","2025-11-05 18:00","연속"]
[2,"서울","성동","구의광장#2 T/L","2025 성동전력지사 변전협력회사 공사","- 효성제 170kV GIS 노후 전자변 교체","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[3,"서울","성동","미금광장 T/L"," 광장S/S 종합예방진단장치 설치공사","차폐테이프 부착 및 부분방전 진단 센서 설치","2025-11-17 10:00","2025-11-17 18:00","2025-11-17 10:00","2025-11-17 18:00","연속"]
[4,"서울","성동","화양광장 T/L"," 광장S/S 종합예방진단장치 설치공사","차폐테이프 부착 및 부분방전 진단 센서 설치","2025-11-18 10:00","2025-11-18 18:00","2025-11-18 10:00","2025-11-18 18:00","연속"]
[5,"서울","성동","성수뚝도#2 T/L","뚝도S/S 성수뚝도#2T/L 21계전기 수리품으로 교체","25.2.17 성수뚝도#2T/L 21 계전기 불량으로 예비품으로 임시교체 탈거된 기존 계전기 수리 완료에 따른 수리품으로 다시 교체","2025-11-28 09:00","2025-11-28 18:00","2025-11-28 09:00","2025-11-28 18:00","연속"]
[6,"서울","성동","뚝도S/S #1 BUS","송전선로 상시험을 위한 BUS 휴전 및 무부하가압","1.대상선로 : 154㎸ 성수-뚝도 #1T/L 2.공사내용 : OF케이블 및 급유설비 철거, XLPE 케이블 설치 ○ XLPE 1200㎟ 1C-0.06km / 접속 2개소[중간 1개 종단 1개]","2025-11-11 10:00","2025-11-11 12:00","2025-11-11 10:00","2025-11-11 12:00","연속"]
[7,"서울","성동","금오상계#2 T/L","'25~'26년 서울본부 성동전력지사 지중송전 협력회사 공사","기중종단접속함(EBA) 가공-지중 인출선로 연결 금구류 TYPE 변경 기중종단접속함(EBA) 절연유 채유","2025-11-17 08:00","2025-11-21 18:00","2025-11-17 08:00","2025-11-21 18:00","연속"]
[8,"서울","성동","금오상계#1 T/L","'25~'26년 서울본부 성동전력지사 지중송전 협력회사 공사","기중종단접속함(EBA) 가공-지중 인출선로 연결 금구류 TYPE 변경 기중종단접속함(EBA) 절연유 채유","2025-11-17 08:00","2025-11-21 18:00","2025-11-17 08:00","2025-11-21 18:00","연속"]
[9,"서울","성동","성동S/S #1 Sh.R CB","2025 성동전력지사 변전협력회사 공사","- #61SH.R 초기점검(A, B, C상) - 170kV GIS 초기점검","2025-11-03 09:00","2025-11-04 18:00","2025-11-03 09:00","2025-11-04 18:00","연속"]
[10,"서울","성동","성동S/S #2 Sh.R CB","2025 성동전력지사 변전협력회사 공사","- #62SH.R 초기점검(A, B, C상) - 170kV GIS 초기점검","2025-11-05 09:00","2025-11-06 18:00","2025-11-05 09:00","2025-11-06 18:00","연속"]
[11,"서울","성동","창동쌍문#1 T/L","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○  창동쌍문#1T/L GIS 교체(1Bay) ○ 제어케이블 포설 등 기타공사(1식)","2025-11-19 08:00","2025-12-03 18:00","2025-11-19 08:00","2025-12-03 18:00","연속"]
[12,"서울","성동","화양성수 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 조작시험","2025-11-20 09:00","2025-11-20 18:00","2025-11-20 09:00","2025-11-20 18:00","연속"]
[13,"서울","성동","미금화양 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 조작시험","2025-11-19 09:00","2025-11-19 18:00","2025-11-19 09:00","2025-11-19 18:00","연속"]
[14,"서울","중부","동빙고반포#1 T/L","'25~'26년 서울본부 성동전력지사 지중송전 협력회사 공사(인력지원)","OF 케이블 급유관 미세누유 연공작업(OF전문사업소 인력지원)","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[15,"서울","중부","상암등촌#1 T/L","(선로시험가압)수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : 2025.2.25~2026.10.23","2025-11-12 15:00","2025-11-14 18:00","2025-11-12 15:00","2025-11-14 18:00","연속"]
[16,"서울","중부","상암S/S #1 BUS","(선로시험가압)수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : 2025.2.25~2026.10.23","2025-11-12 15:00","2025-11-14 18:00","2025-11-12 15:00","2025-11-14 18:00","연속"]
[17,"서울","중부","수색은평#2 T/L"," 수색S/S 옥내화관련 수색-은평T/L 지중화 공사","선종 및 회선 수 : STACIR 330㎟, 2회선 (금회분) 철탑신설 1기, 전력선 가선 (1.2C-㎞) 철탑철거 2기, 전력선인하 (7.4C-㎞) 공사기간 : 2024. 2. 8. ~ 2027. 2.11. (착공후 1100일간)","2025-11-07 08:00","2025-12-12 18:00","2025-11-07 08:00","2025-12-12 18:00","연속"]
[18,"서울","중부","중부S/S #67 BUS","2025년 중부S/S  장기사용 GIS 교체공사(4차)","-  #62-#67PT GIS 증설 - 기타 부대공사","2025-11-18 09:00","2025-11-22 15:00","2025-11-18 09:00","2025-11-22 15:00","연속"]
[19,"서울","중부","중부S/S #62 BUS","2025년 중부S/S  장기사용 GIS 교체공사(4차)","-  #62-#67PT GIS 증설 - 기타 부대공사","2025-11-10 09:00","2025-11-18 09:00","2025-11-10 09:00","2025-11-18 09:00","연속"]
[20,"서울","직할","서소문S/S #1 BUS","25년 직할 변전정비협력회사 총액공사","PT GIS 보통점검","2025-11-05 10:00","2025-11-05 12:00","2025-11-05 10:00","2025-11-05 12:00","연속"]
[21,"서울","직할","서소문S/S #2 BUS","25년 직할 변전정비협력회사 총액공사","PT GIS 보통점검","2025-11-05 13:00","2025-11-05 15:00","2025-11-05 13:00","2025-11-05 15:00","연속"]
[22,"서울","직할","서소문S/S CB 6100","25년 직할 변전정비협력회사 총액공사","PT GIS 보통점검","2025-11-05 10:00","2025-11-05 15:00","2025-11-05 10:00","2025-11-05 15:00","연속"]
[23,"서울","직할","중앙S/S #2 BUS","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 중앙서소문T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/26)","2025-11-15 09:00","2025-11-16 18:00","2025-11-15 09:00","2025-11-16 18:00","연속"]
[24,"서울","직할","중앙S/S #1 BUS","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 중앙서소문T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/26)","2025-11-17 09:00","2025-11-21 18:00","2025-11-17 09:00","2025-11-21 18:00","연속"]
[25,"서울","직할","중앙서소문 T/L","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 중앙서소문T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/26)","2025-11-15 09:00","2025-12-05 18:00","2025-11-15 09:00","2025-12-05 18:00","연속"]
[26,"서울","직할","중앙S/S #2 BUS","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 중앙서소문T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/26)","2025-11-24 09:00","2025-12-05 18:00","2025-11-24 09:00","2025-12-05 18:00","연속"]
[27,"남서울","강남","신사반포#2 T/L","24-25년도 강남전력 변전협력회사 총액공사","170kV GIS 전자변교체, 조작시험 포함","2025-11-24 14:00","2025-11-24 18:00","2025-11-24 14:00","2025-11-24 18:00","연속"]
[28,"남서울","강남","신사반포#1 T/L","24-25년도 강남전력 변전협력회사 총액공사","170kV GIS 전자변 교체공사 및 조작시험","2025-11-23 09:00","2025-11-24 14:00","2025-11-23 09:00","2025-11-24 14:00","연속"]
[29,"남서울","동서울","동서울위례#2 T/L","동서울S/S 종합정비공사"," 제어케이블 이설","2025-11-12 13:00","2025-11-14 18:00","2025-11-12 13:00","2025-11-14 18:00","연속"]
[30,"남서울","동서울","동서울위례#1 T/L","동서울S/S 종합정비공사"," 제어케이블 이설","2025-11-12 13:00","2025-11-14 18:00","2025-11-12 13:00","2025-11-14 18:00","연속"]
[31,"남서울","동서울","동서울S/S #67 BUS(신)","동서울S/S 종합정비공사(2차)"," 제어케이블 이설","2025-11-26 13:00","2025-11-28 18:00","취소","취소","연속"]
[32,"남서울","동서울","동서울송파#1 T/L","동서울S/S 종합정비공사"," 제어케이블 이설","2025-11-03 08:00","2025-11-05 12:00","2025-11-03 08:00","2025-11-05 12:00","연속"]
[33,"남서울","동서울","동서울강동#1 T/L","동서울S/S 종합정비공사"," 제어케이블 이설","2025-11-05 13:00","2025-11-07 18:00","2025-11-05 13:00","2025-11-07 18:00","연속"]
[34,"남서울","동서울","동서울S/S #65 BUS(신)","동서울S/S 종합정비공사(2차)"," 제어케이블 이설","2025-11-19 13:00","2025-11-21 18:00","취소","취소","연속"]
[35,"남서울","동서울","동서울S/S #66 BUS(신)","동서울S/S 종합정비공사(2차)"," 제어케이블 이설","2025-11-19 13:00","2025-11-21 18:00","취소","취소","연속"]
[36,"남서울","동서울","동서울S/S #60 BUS(신)","동서울S/S 종합정비공사(2차)"," 제어케이블 이설","2025-11-24 08:00","2025-11-26 12:00","취소","취소","연속"]
[37,"남서울","동서울","동서울송파#2 T/L","동서울S/S 종합정비공사"," 제어케이블 이설","2025-11-03 08:00","2025-11-05 12:00","2025-11-03 08:00","2025-11-05 12:00","연속"]
[38,"남서울","동서울","동서울신장#1 T/L","동서울S/S 종합정비공사"," 제어케이블 이설","2025-11-10 08:00","2025-11-12 12:00","2025-11-10 08:00","2025-11-12 12:00","연속"]
[39,"남서울","동서울","동서울신장#2 T/L","동서울S/S 종합정비공사"," 제어케이블 이설","2025-11-10 08:00","2025-11-12 12:00","2025-11-10 08:00","2025-11-12 12:00","연속"]
[40,"남서울","동서울","동서울강동#2 T/L","동서울S/S 종합정비공사"," 제어케이블 이설","2025-11-05 13:00","2025-11-07 18:00","2025-11-05 13:00","2025-11-07 18:00","연속"]
[41,"남서울","영등포","신문래구로#2 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 구로S/S 신문래-구로#2T/L","2025-11-24 09:00","2025-11-26 18:00","2025-11-24 09:00","2025-11-26 18:00","연속"]
[42,"남서울","영등포","천왕구로#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 구로S/S 전철T/L 정밀점검 무부하가압용(고객선로)","2025-11-20 09:00","2025-11-20 18:00","취소","취소","연속"]
[43,"남서울","영등포","구로구로전철 T/L CB","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 구로S/S 전철T/L","2025-11-18 09:00","2025-11-20 18:00","2025-11-18 09:00","2025-11-20 18:00","연속"]
[44,"남서울","영등포","상암등촌#2 T/L","'25-'26년 영등포전력지사 지중송전 협력회사 공사","○ 상암-등촌#2T/L 절연유 채유","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[45,"남서울","영등포","상암등촌#1 T/L","'25-'26년 영등포전력지사 지중송전 협력회사 공사","○ 상암-등촌#1T/L 절연유 채유","2025-11-11 09:00","2025-11-11 18:00","2025-11-11 09:00","2025-11-11 18:00","연속"]
[46,"남서울","영등포","신문래목동#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 목동S/S 신문래-목동#1","2025-11-12 14:00","2025-11-14 18:00","2025-11-12 14:00","2025-11-14 18:00","연속"]
[47,"남서울","영등포","목동S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 목동S/S 6100 정밀점검에 따른 60BUS 휴전","2025-11-03 09:00","2025-11-05 14:00","2025-11-03 09:00","2025-11-05 14:00","연속"]
[48,"남서울","영등포","오류목동 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 목동S/S 오류-목동T/L 및 6100 무부하가압용","2025-11-05 09:00","2025-11-07 18:00","2025-11-05 09:00","2025-11-07 18:00","연속"]
[49,"남서울","영등포","신정목동#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 목동S/S 신정-목동#1","2025-11-10 09:00","2025-11-12 14:00","2025-11-10 09:00","2025-11-12 14:00","연속"]
[50,"남서울","영등포","신정S/S #1 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6133(1DS 점검)","2025-11-27 09:00","2025-11-27 18:00","취소","취소","연속"]
[51,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6133(1DS 점검 후 무부하가압)","2025-11-27 15:00","2025-11-27 18:00","취소","취소","연속"]
[52,"남서울","영등포","신정S/S #2 BUS","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6133(2DS 점검)","2025-11-28 09:00","2025-11-28 18:00","취소","취소","연속"]
[53,"남서울","영등포","부천신정#1 T/L","25년도 영등포전력지사  GIS 정밀점검공사","25년도 영등포전력지사  GIS 정밀점검공사 대상 : 신정S/S 6133(2DS 점검 후 무부하가압)","2025-11-28 15:00","2025-11-28 18:00","취소","취소","연속"]
[54,"남서울","영등포","온수소래 T/L","24~25년 영등포전력지사 변전협력회사 총액공사"," GIS 조작시험","2025-11-08 09:00","2025-11-08 18:00","취소","취소","연속"]
[55,"남서울","영등포","천왕구로#2 T/L","'25-'26년 영등포전력지사 지중송전 협력회사 공사","○ 천왕-구로#2T/L 절연유 보충","2025-11-25 09:00","2025-11-27 18:00","취소","취소","연속"]
[56,"남서울","영등포","고강화곡#3 T/L","24~25년 영등포전력지사 변전협력회사 총액공사"," GIS 조작시험","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[57,"남서울","영등포","중동화곡#1 T/L"," 중동-화곡#1 T/L 과열개소 보수","접지선 과열개소 보수","2025-11-15 09:00","2025-11-16 18:00","취소","취소","연속"]
[58,"남서울","직할","신문래노들 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-11-05 09:00","2025-11-07 18:00","2025-11-05 09:00","2025-11-07 18:00","연속"]
[59,"남서울","직할","신문래노량진 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-11-10 09:00","2025-11-13 18:00","2025-11-10 09:00","2025-11-12T18:00:00","연속"]
[60,"남서울","직할","노들노량진 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-11-20 09:00","2025-11-21 18:00","2025-11-20 09:00","2025-11-21 18:00","연속"]
[61,"남서울","직할","사당봉천#2 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-11-03 09:00","2025-11-04 18:00","2025-11-03 09:00","2025-11-04 18:00","연속"]
[62,"남서울","직할","대방신길#1 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-11-14 09:00","2025-11-17 18:00","2025-11-14 09:00","2025-11-17 18:00","연속"]
[63,"남서울","직할","대방신길#2 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-11-18 09:00","2025-11-19 18:00","2025-11-18 09:00","2025-11-19 18:00","연속"]
[64,"남서울","직할","신문래여의 T/L"," 신문래-여의T/L 선종교체공사"," 신문래-여의T/L 전구간 선종교체","2025-11-21 09:00","2026-07-17 18:00","취소","취소","연속"]
[65,"남서울","직할","신문래구로#2 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-11-26 09:00","2025-11-27 18:00","2025-11-26 09:00","2025-11-27 18:00","연속"]
[66,"남서울","직할","신문래구로#1 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-11-24 09:00","2025-11-25 18:00","2025-11-24 09:00","2025-11-25 18:00","연속"]
[67,"남서울","직할","신문래양평#2 T/L","170kV GIS 보통점검, 전자변 교체","170kV GIS 보통점검, 전자변 교체","2025-11-03 09:00","2025-11-03 18:00","취소","취소","연속"]
[68,"인천","김포","신경서경서#2 T/L","경서S/S  신경서-경서#2T/L GIS 조작시험","경서S/S  신경서-경서#2T/L GIS 조작시험","2025-11-10 10:00","2025-11-10 18:00","2025-11-10 10:00","2025-11-10 18:00","연속"]
[69,"인천","김포","신경서경서#3 T/L","경서S/S  신경서-경서#3T/L GIS 조작시험","경서S/S  신경서-경서#3T/L GIS 조작시험","2025-11-11 10:00","2025-11-11 18:00","2025-11-11 10:00","2025-11-11 18:00","연속"]
[70,"인천","김포","김포불로#2 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-11-05 08:00","2025-11-06 18:00","취소","취소","연속"]
[71,"인천","김포","김포불로#1 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-11-03 08:00","2025-11-04 18:00","취소","취소","연속"]
[72,"인천","김포","계양불로#2 T/L","불로S/S  계양-불로#2T/L GIS 하자점검","불로S/S  계양-불로#2T/L GIS 하자점검","2025-11-02 10:00","2025-11-02 18:00","2025-11-02 10:00","2025-11-02 18:00","연속"]
[73,"인천","김포","계양불로#1 T/L","불로S/S  계양-불로#1T/L GIS 하자점검","불로S/S  계양-불로#1T/L GIS 하자점검","2025-11-01 10:00","2025-11-01 18:00","2025-11-01 10:00","2025-11-01 18:00","연속"]
[74,"인천","김포","신김포양곡#1 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-11-10 08:00","2025-11-12 18:00","2025-11-10 08:00","2025-11-12 18:00","연속"]
[75,"인천","김포","신김포양곡#2 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2025-11-13 08:00","2025-11-14 18:00","2025-11-14 08:00","2025-11-15 18:00","연속"]
[76,"인천","부평","관교만수#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[77,"인천","부평","관교만수#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[78,"인천","부평","주안만수#1 T/L"," 주안-만수 #1T/L 이상개소 복구공사 및 절연유 채유","- J/B #26 C상 발열개소 보수 - J/B #20 B상 누유개소 보수 - 주안 TJ 등 9개소 절연유 채유","2025-11-03 09:00","2025-11-05 18:00","2025-11-03 09:00","2025-11-05 18:00","연속"]
[79,"인천","부평","송현포스코CC#2 T/L"," 주안-관교등 4개T/L 열경화공법 EBG 보강공사","EBG 가스채취밸브 설치 및 스프링 유니트점검 시행","2025-11-10 09:00","2025-11-12 18:00","2025-11-10 09:00","2025-11-12 18:00","연속"]
[80,"인천","부평","송현포스코CC#1 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2025-11-13 09:00","2025-11-13 18:00","2025-11-13 09:00","2025-11-13 18:00","연속"]
[81,"인천","부평","원창포스코CC#2 T/L","원창-포스코#2T/L 보호반 교체 공사","원창-포스코#2T/L 보호반 교체 공사","2025-11-24 09:00","2025-11-28 18:00","2025-11-24 09:00","2025-11-28 18:00","연속"]
[82,"인천","부평","원창포스코CC#1 T/L","원창-포스코#1T/L 보호반 교체 공사","원창-포스코#1T/L 보호반 교체 공사","2025-11-17 09:00","2025-11-21 18:00","2025-11-17 09:00","2025-11-21 18:00","연속"]
[83,"인천","부평","북인천원창 T/L"," 북인천-원창T/L 6B7 GIS 보통점검"," 북인천-원창T/L 6B7 GIS 보통점검","2025-11-01 09:00","2025-11-01 18:00","2025-11-01 09:00","2025-11-01 18:00","연속"]
[84,"인천","부평","학익S/S CB 6100","학익S/S  #60-#65 BUS TIE GIS 조작","학익S/S  #60-#65 BUS TIE GIS 조작","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[85,"인천","부평","학익연수#1 T/L"," 남인천-학익 등 2개T/L 지장이설 및 선종교체공사","케이블 선종교체(OF 2,000㎟ → XLPE 2,000㎟, 2.7km)","2025-11-17 08:00","2026-01-30 18:00","2025-11-17 08:00","2026-01-30 18:00","연속"]
[86,"인천","시흥","신시흥남동#1 T/L","남동S/S 혼용화공사","남동S/S 혼용화공사 관련 휴전","2025-11-01 09:00","2025-11-01 18:00","2025-11-01 09:00","2025-11-01 18:00","연속"]
[87,"인천","시흥","신시흥남동#2 T/L","남동S/S 혼용화공사","남동S/S 혼용화공사 관련 휴전","2025-11-02 09:00","2025-11-02 18:00","2025-11-02 09:00","2025-11-02 18:00","연속"]
[88,"인천","시흥","도림오봉#1 T/L","피뢰기 교체공사 및 열화진단","- 피뢰기 교체공사 : 오봉C/T - 피뢰기 열화진단 : 도림C/T","2025-11-09 09:00","2025-11-09 18:00","2025-11-09 09:00","2025-11-09 18:00","매일"]
[89,"인천","시흥","도림오봉#2 T/L","피뢰기 교체공사 및 열화진단","- 피뢰기 교체공사 : 오봉C/T - 피뢰기 열화진단 : 도림C/T","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","매일"]
[90,"인천","시흥","북시화서시화#1 T/L","북시화S/S 북시화서시화#1T/L 보호반대체","북시화S/S 북시화서시화#1T/L 보호반대체-서시화S/S 보호반대체 병행","2025-11-03 09:00","2025-11-06 18:00","2025-11-03 09:00","2025-11-06 18:00","연속"]
[91,"인천","시흥","북시화서시화#2 T/L","북시화S/S 북시화서시화#2T/L 보호반대체","북시화S/S 북시화서시화#2T/L 보호반대체 -서시화S/S 보호반대체 병행","2025-11-10 09:00","2025-11-12 18:00","2025-11-10 09:00","2025-11-12 18:00","연속"]
[92,"인천","시흥","신광명소래 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기) 고정형 폴리머 점퍼지지애자 설치 No.80~91(7기)","2025-11-21 07:00","2025-11-23 18:00","취소","취소","매일"]
[93,"인천","시흥","서서울#2소래 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기) 고정형 폴리머 점퍼지지애자 설치 No.80~91(7기)","2025-11-21 07:00","2025-11-23 18:00","취소","취소","매일"]
[94,"인천","시흥","서안양소래 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기) 추락방지장치(수평) 설치 No.76~82(7기)","2025-11-28 07:00","2025-11-30 18:00","취소","취소","매일"]
[95,"인천","시흥","온수소래 T/L","'24~25 시흥전력지사 가공송전 협력회사 공사","조류착지방지장치 설치 No.76~92 (17기) 추락방지장치(수평) 설치 No.76~82(7기)","2025-11-28 07:00","2025-11-30 18:00","취소","취소","매일"]
[96,"인천","시흥","신시화남정왕#2 T/L","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(66BF반)","2025-11-13 14:00","2025-11-13 18:00","2025-11-07 15:00","2025-11-07 18:00","연속"]
[97,"인천","시흥","신시화중시화#2 T/L","피앤씨테크 보호 IED 성능개선","피앤씨테크 보호 IED 성능개선 F/W 업데이트 및 연동시험(65BF반)","2025-11-13 09:00","2025-11-13 14:00","2025-11-07 12:00","2025-11-07 15:00","연속"]
[98,"인천","시흥","신시흥S/S CB 6100","신시흥S/S  6100 B/T GIS 조작시험","신시흥S/S  6100(60-65) B/T GIS 조작시험","2025-11-06 09:00","2025-11-06 14:00","취소","취소","연속"]
[99,"인천","시흥","신시흥도림#2 T/L","신시흥S/S  신시흥도림#2T/L GIS 조작시험","신시흥S/S  신시흥도림#2T/L GIS 조작시험","2025-11-18 09:00","2025-11-18 14:00","취소","취소","연속"]
[100,"인천","시흥","신시흥시화#2 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","고정형 폴리머 점퍼지지애자 설치 No.8, 10(2기)","2025-11-26 07:30","2025-11-26 18:00","2025-11-26 07:30","2025-11-26 18:00","매일"]
[101,"인천","시흥","신시흥시화#1 T/L","24~25 시흥전력지사 가공송전 협력회사 공사","고정형 폴리머 점퍼지지애자 설치 No.8, 10(2기)","2025-11-25 07:30","2025-11-25 18:00","2025-11-25 07:30","2025-11-25 18:00","매일"]
[102,"인천","김포","양촌양곡#2 T/L"," 양곡S/S  양촌-양곡#2T/L GIS 보통점검"," 양곡S/S  양촌-양곡#2T/L GIS 보통점검","2025-11-06 10:00","2025-11-06 18:00","2025-11-06 10:00","2025-11-06 18:00","연속"]
[103,"인천","부평","신가좌주안#2 T/L","신가좌S/S  신가좌-주안#2T/L 617 GIS 보통점검","신가좌S/S  신가좌-주안#2T/L 617 GIS 보통점검,피뢰기점검","2025-11-08 12:00","2025-11-08 18:00","취소","취소","연속"]
[104,"인천","부평","신가좌주안#1 T/L","신가좌S/S  신가좌-주안#1T/L 647 GIS 보통점검","신가좌S/S  신가좌-주안#1T/L 647 GIS 보통점검,피뢰기점검","2025-11-08 07:00","2025-11-08 12:00","취소","취소","연속"]
[105,"인천","부평","영종공항열병합#2 T/L","영종S/S  공항열병합#2T/L 휴전(고객요청)","영종S/S  공항열병합#2T/L 휴전(고객요청)","2025-11-03 09:00","2025-11-07 18:00","2025-11-03 09:00","2025-11-07 18:00","연속"]
[106,"인천","부평","주안S/S CB 6100","주안S/S  BUS TIE 6100 GIS 보통점검","주안S/S  #60-#65 BUS TIE 6100 GIS 보통점검","2025-11-15 09:00","2025-11-15 18:00","2025-11-15 09:00","2025-11-15 18:00","연속"]
[107,"인천","직할","북인천원창 T/L","북인천S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","북인천S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","2025-11-08 15:00","2025-11-08 18:00","2025-11-08 15:00","2025-11-08 18:00","연속"]
[108,"인천","직할","북인천S/S #65 BUS","북인천S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","북인천S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","2025-11-08 15:00","2025-11-08 18:00","2025-11-08 15:00","2025-11-08 18:00","연속"]
[109,"인천","직할","갈산부흥#1 T/L"," 갈산부흥#1T/L GIS 보통점검, 조작시험(양단)","갈산S/S 갈산부흥#1T/L GIS 보통점검, 부흥S/S 갈산부흥#1T/L GIS 조작시험","2025-11-10 09:30","2025-11-10 18:00","2025-11-10 09:30","2025-11-10 18:00","연속"]
[110,"인천","직할","갈산부흥#2 T/L"," 갈산부흥#2T/L GIS 보통점검, 조작시험(양단)","갈산S/S 갈산부흥#2T/L GIS 보통점검, 부흥S/S 갈산부흥#2T/L GIS 조작시험","2025-11-11 09:30","2025-11-11 18:00","2025-11-11 09:30","2025-11-11 18:00","연속"]
[111,"인천","직할","갈산부흥#3 T/L","갈산S/S 갈산부흥#3T/L GIS 보통점검","갈산S/S 갈산부흥#3T/L GIS 보통점검","2025-11-12 09:30","2025-11-12 18:00","2025-11-12 09:30","2025-11-12 18:00","연속"]
[112,"인천","직할","고강화곡#3 T/L"," 고강S/S #4M.Tr 증설공사","고강S/S  GIS(#4M.Tr 1차) 설치 및 무부하가압","2025-11-15 07:00","2025-11-17 07:00","취소","취소","연속"]
[113,"인천","직할","고강S/S #60 BUS"," 고강S/S #4M.Tr 증설공사","고강S/S  GIS(#4M.Tr 1차) 설치 및 무부하가압","2025-11-15 07:00","2025-11-16 07:00","취소","취소","연속"]
[114,"인천","직할","고강S/S #65 BUS"," 고강S/S #4M.Tr 증설공사","고강S/S  GIS(#4M.Tr 1차) 설치 및 무부하가압","2025-11-16 07:00","2025-11-17 07:00","취소","취소","연속"]
[115,"인천","직할","계양원창 T/L","24~25년 부평, 김포 가공송전 협력회사 공사"," 계양-원창T/L 수평추락방지 및 폴리머 점퍼 지지애자 설치공사","2025-11-17 07:00","2025-11-20 18:00","취소","취소","매일"]
[116,"인천","직할","임학계양#1 T/L","24~25년 부평, 김포 가공송전 협력회사 공사"," 임학-계양T/L 수평추락방지 설치공사","2025-11-17 07:00","2025-11-21 18:00","취소","취소","매일"]
[117,"인천","직할","계양북인천 T/L","24~25년 부평, 김포 가공송전 협력회사 공사"," 계양-원창T/L 수평추락방지 및 폴리머 점퍼 지지애자 설치공사","2025-11-22 07:00","2025-11-25 18:00","취소","취소","매일"]
[118,"인천","직할","임학계양#2 T/L","24~25년 부평, 김포 가공송전 협력회사 공사"," 임학-계양T/L 수평추락방지 설치공사","2025-11-22 07:00","2025-11-26 18:00","취소","취소","매일"]
[119,"경기북부","고양","남면백석#1 T/L","24~25 고양전력지사 변전협력회사 총액공사","170kV GIS 계측 CT 케이블 교체","2025-11-25 09:00","2025-11-25 18:00","2025-11-25 09:00","2025-11-25 18:00","연속"]
[120,"경기북부","고양","신파주S/S SEC CB 65660","24-25 변전협력회사 총액공사","170kV GIS 보통점검","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[121,"경기북부","고양","신파주원흥#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2025-11-03 07:30","2025-11-07 17:00","취소","취소","연속"]
[122,"경기북부","고양","신파주S/S SEC CB 60610","24-25 변전협력회사 총액공사","170kV GIS 보통점검","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[123,"경기북부","고양","신파주원흥#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2025-11-17 07:30","2025-11-21 17:00","2025-11-17 07:30","2025-11-21 17:00","연속"]
[124,"경기북부","고양","신파주원흥#1 T/L","(선로시험가압)수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : 2025.2.25~2026.10.23","2025-11-12 15:00","2025-11-14 18:00","취소","취소","연속"]
[125,"경기북부","고양","원흥S/S #1 BUS","(선로시험가압)수색 및 증산S/S 건설에 따른 지중T/L 공사","선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 공사기간 : 2025.2.25~2026.10.23","2025-11-12 15:00","2025-11-14 18:00","취소","취소","연속"]
[126,"경기북부","고양","일산S/S CB 6200","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-11-03 08:00","2025-11-03 18:00","2025-11-03 08:00","2025-11-03 18:00","연속"]
[127,"경기북부","고양","일산S/S CB 6100","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-11-03 08:00","2025-11-03 18:00","2025-11-03 08:00","2025-11-03 18:00","연속"]
[128,"경기북부","고양","일산S/S SEC CB 60610","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-11-05 08:00","2025-11-05 18:00","2025-11-05 08:00","2025-11-05 18:00","연속"]
[129,"경기북부","고양","일산S/S SEC CB 65660","일산S/S 장기사용 23kV GIS 교체 일반도급공사","디지털화 공사 관련 제어케이블 이설","2025-11-06 08:00","2025-11-06 18:00","2025-11-06 08:00","2025-11-06 18:00","연속"]
[130,"경기북부","구리","가평춘천HP T/L"," 운천-철원 등 2개T/L 용량증대 전력선 교체공사"," 가평-춘천HPT/L 용량증대 전력선 교체 미작업구간 시행 ※ 25년 11월 휴전승인시, 해당선로 전력선 교체 전구간 완성","2025-11-17 09:00","2025-11-21 18:00","2025-11-17 09:00","2025-11-21 18:00","연속"]
[131,"경기북부","구리","가평청평HP#1 T/L"," 운천-철원 등 2개T/L 용량증대 전력선 교체공사"," 가평-춘천HPT/L 용량증대 전력선 교체 4회선 철탑 시공을 위한 하단선로 휴전","2025-11-17 09:00","2025-11-21 18:00","2025-11-17 09:00","2025-11-21 18:00","연속"]
[132,"경기북부","구리","가평청평HP#1 T/L"," 운천-철원 등 2개T/L 용량증대 전력선 교체공사"," 가평-춘천HPT/L 용량증대 전력선 교체 4회선 철탑 시공을 위한 하단선로 휴전","2025-11-24 09:00","2025-11-28 18:00","2025-11-24 09:00","2025-11-28 18:00","연속"]
[133,"경기북부","구리","가평춘천HP T/L"," 운천-철원 등 2개T/L 용량증대 전력선 교체공사"," 가평-춘천HPT/L No.127~135.99 용량증대 전력선 교체","2025-11-24 09:00","2025-11-28 18:00","2025-11-24 09:00","2025-11-28 18:00","연속"]
[134,"경기북부","구리","미금구리#3 T/L","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 초기점검","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[135,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 동서울서종#1T/L 전력선 가선 공정","2025-11-17 07:00","2025-12-03 18:00","2025-11-17 07:00","2025-12-03 18:00","연속"]
[136,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 동서울서종#2T/L 가선공정","2025-11-27 07:00","2025-12-03 18:00","2025-11-27 07:00","2025-12-03 18:00","연속"]
[137,"경기북부","구리","덕소진건#1 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","C/T 피뢰기 점검 및 금구류 교체","2025-11-27 09:00","2025-11-27 18:00","2025-11-27 09:00","2025-11-27 18:00","연속"]
[138,"경기북부","구리","덕소진건#2 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","C/T 피뢰기 점검 및 금구류 교체","2025-11-28 09:00","2025-11-28 18:00","2025-11-28 09:00","2025-11-28 18:00","연속"]
[139,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신장-덕소#2T/L 전력선 가선 공정","2025-11-03 07:00","2025-11-07 18:00","2025-11-03 07:00","2025-11-07 18:00","연속"]
[140,"경기북부","구리","덕소마석#1 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","C/T 피뢰기 점검 및 금구류 교체","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[141,"경기북부","구리","신장덕소#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 동서울서종#2T/L 가선공정","2025-11-27 07:00","2025-12-03 18:00","2025-11-27 07:00","2025-12-03 18:00","연속"]
[142,"경기북부","구리","덕소마석#2 T/L","25~26년 지중송전 협력회사 공사(경기북부본부 직할)","C/T 피뢰기 점검 및 금구류 교체","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[143,"경기북부","구리","미금광장 T/L","구리송전협력회사 공사_추락방지장치 설치"," 미금-광장T/L No.1,2,4,20 관형주 레일형 수평 추락방지장치 설치","2025-11-25 07:00","2025-11-25 17:00","2025-11-25 07:00","2025-11-25 17:00","연속"]
[144,"경기북부","구리","미금화양 T/L","구리송전협력회사 공사_추락방지장치 설치"," 미금-화양T/L No.1,2,4,20 관형주 레일형 수평 추락방지장치 설치","2025-11-24 07:00","2025-11-24 17:00","2025-11-24 07:00","2025-11-24 17:00","연속"]
[145,"경기북부","구리","별내별내열병합#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-11-05 09:00","2025-11-05 18:00","2025-11-05 09:00","2025-11-05 18:00","연속"]
[146,"경기북부","구리","별내별내열병합#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[147,"경기북부","구리","별내장암 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-11-19 09:00","2025-11-19 18:00","2025-11-19 09:00","2025-11-19 18:00","연속"]
[148,"경기북부","구리","동서울서종#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 동서울서종2T/L 전력선 가선 공정","2025-11-27 07:00","2025-12-03 18:00","2025-11-27 07:00","2025-12-03 18:00","연속"]
[149,"경기북부","구리","동서울서종#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신장-덕소#2T/L 전력선 가선 공정","2025-11-03 07:00","2025-11-07 18:00","2025-11-03 07:00","2025-11-07 18:00","연속"]
[150,"경기북부","구리","동서울서종#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 동서울서종#1T/L 전력선 가선 공정","2025-11-17 07:00","2025-11-26 18:00","2025-11-17 07:00","2025-11-26 18:00","연속"]
[151,"경기북부","구리","신포천S/S CB 6100","24-25년 구리전력지사 변전협력회사 총액공사"," #60-65 모선보호반 대체","2025-11-10 10:00","2025-11-14 18:00","2025-11-10 10:00","2025-11-14 18:00","연속"]
[152,"경기북부","구리","신포천S/S SEC CB 65660","24-25년 구리전력지사 변전협력회사 총액공사"," #61-66 모선보호반 대체","2025-11-24 10:00","2025-11-28 18:00","2025-11-24 10:00","2025-11-28 18:00","연속"]
[153,"경기북부","구리","신포천S/S CB 6200","24-25년 구리전력지사 변전협력회사 총액공사"," #61-66 모선보호반 대체","2025-11-24 10:00","2025-11-28 18:00","2025-11-24 10:00","2025-11-28 18:00","연속"]
[154,"경기북부","구리","신포천덕계#1 T/L","25년 구리전력 장기노후배전반 교체공사","신포천S/S 신포천-덕계#1T/L GIS : 송전선로 보호반 대체","2025-11-03 09:00","2025-11-06 18:00","2025-11-03 09:00","2025-11-06 18:00","연속"]
[155,"경기북부","구리","신포천백학#2 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신덕은-동두천CC#1 T/L No.18~19 (子 :  신의정부-백학#2 T/L No.7~8)","2025-11-25 07:00","2025-11-25 18:00","2025-11-25 07:00","2025-11-25 18:00","연속"]
[156,"경기북부","구리","신포천백학#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신덕은-동두천CC#2 T/L No.18~19, 32~50 (子 :  신의정부-백학#1 T/L No.7~8,21~39)","2025-11-20 07:00","2025-11-24 18:00","2025-11-20 07:00","2025-11-24 18:00","연속"]
[157,"경기북부","구리","신포천덕계#2 T/L","25년 구리전력 장기노후배전반 교체공사","신포천S/S 신포천-덕계#2T/L GIS : 송전선로 보호반 대체","2025-11-10 09:00","2025-11-12 18:00","2025-11-10 09:00","2025-11-12 18:00","연속"]
[158,"경기북부","구리","신포천S/S SEC CB 60610","24-25년 구리전력지사 변전협력회사 총액공사"," #60-65 모선보호반 대체","2025-11-10 10:00","2025-11-14 18:00","2025-11-10 10:00","2025-11-14 18:00","연속"]
[159,"경기북부","구리","신포천S/S SEC CB 65660","24-25년 구리전력지사 변전협력회사 총액공사"," #60-65 모선보호반 대체","2025-11-10 10:00","2025-11-14 18:00","2025-11-10 10:00","2025-11-14 18:00","연속"]
[160,"경기북부","구리","신포천S/S SEC CB 60610","24-25년 구리전력지사 변전협력회사 총액공사"," #61-66 모선보호반 대체","2025-11-24 10:00","2025-11-28 18:00","2025-11-24 10:00","2025-11-28 18:00","연속"]
[161,"경기북부","구리","운천철원#2 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 조작시험","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[162,"경기북부","구리","운천철원#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 전자변 교체","2025-11-11 09:00","2025-11-11 18:00","2025-11-11 09:00","2025-11-11 18:00","연속"]
[163,"경기북부","구리","지제용문#2 T/L","구리송전협력회사 공사_추락방지장치 설치"," 지제-용문#2T/L No.49,50 관형주 레일형 수평 추락방지장치 설치","2025-11-26 12:00","2025-11-26 18:00","2025-11-26 12:00","2025-11-26 18:00","연속"]
[164,"경기북부","구리","지제용문#1 T/L","구리송전협력회사 공사_추락방지장치 설치"," 지제-용문#1T/L No.49,50 관형주 레일형 수평 추락방지장치 설치","2025-11-26 07:00","2025-11-26 12:00","2025-11-26 07:00","2025-11-26 12:00","연속"]
[165,"경기북부","구리","진건별내#1 T/L","구리갈매역세권 공공주택지구 지장송전선로 이설공사"," 진건-별내T/L M/H#3~M/H#5 구간 이설","2025-11-19 09:00","2025-12-22 18:00","2025-11-19 09:00","2025-12-22 18:00","연속"]
[166,"경기북부","구리","장암진접#1 T/L","남양주진접2 공공주택지구 송전선로 임시이설공사","남양주 진접2 공공주택지구 지중화 전 임시선로 구성(요청자 직접시행)","2025-11-04 07:00","2025-11-06 18:00","2025-11-04 07:00","2025-11-06 18:00","연속"]
[167,"경기북부","구리","서홍천청평PP T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","345kV 신가평-포천LNG#1T/L(상),  서홍천-청평양수T/L(하) 4회선 병가구간(No.26~41)철탑추락방지시설 설치","2025-11-26 07:00","2025-12-05 18:00","2025-11-26 07:00","2025-12-05 18:00","연속"]
[168,"경기북부","구리","신포천포천#1 T/L","포천변전소  옥외철구 변전설비 철거공사","인출 POST 인근  DS 및 모선재 철거간 안전 이격거리 확보","2025-11-18 07:00","2025-11-18 12:00","2025-11-18 07:00","2025-11-18 12:00","연속"]
[169,"경기북부","구리","포천운천#2 T/L","포천변전소  옥외철구 변전설비 철거공사","인출 POST 인근  DS 및 모선재 철거간 안전 이격거리 확보","2025-11-18 07:00","2025-11-18 12:00","2025-11-18 07:00","2025-11-18 12:00","연속"]
[170,"경기북부","구리","신포천포천#2 T/L","포천변전소  옥외철구 변전설비 철거공사","인출 POST 인근  DS 및 모선재 철거간 안전 이격거리 확보","2025-11-17 12:00","2025-11-17 18:00","2025-11-17 12:00","2025-11-17 18:00","연속"]
[171,"경기북부","구리","용정포천#1 T/L","포천변전소  옥외철구 변전설비 철거공사","인출 POST 인근  DS 및 모선재 철거간 안전 이격거리 확보","2025-11-17 12:00","2025-11-17 18:00","2025-11-17 12:00","2025-11-17 18:00","연속"]
[172,"경기북부","구리","용정포천#2 T/L","포천변전소  옥외철구 변전설비 철거공사","인출 POST 인근  DS 및 모선재 철거간 안전 이격거리 확보","2025-11-17 07:00","2025-11-17 12:00","2025-11-17 07:00","2025-11-17 12:00","연속"]
[173,"경기북부","구리","포천운천#1 T/L","포천변전소  옥외철구 변전설비 철거공사","인출 POST 인근  DS 및 모선재 철거간 안전 이격거리 확보","2025-11-18 12:00","2025-11-19 18:00","2025-11-18 12:00","2025-11-19 18:00","매일"]
[174,"경기북부","직할","녹양백석#1 T/L","녹양S/S 170kV GIS 장기사용 대체공사","장기사용 GIS 철거 및 설치","2025-11-23 09:00","2025-11-23 18:00","2025-11-23 09:00","2025-11-23 18:00","연속"]
[175,"경기북부","직할","녹양S/S #1 BUS","녹양S/S 170kV GIS 장기사용 대체공사","장기사용 GIS 철거 및 설치","2025-11-24 09:00","2025-11-28 18:00","2025-11-24 09:00","2025-11-28 18:00","연속"]
[176,"경기북부","직할","녹양백석#1 T/L","녹양S/S 170kV GIS 장기사용 대체공사","장기사용 GIS 철거 및 설치","2025-11-09 09:00","2025-11-09 18:00","2025-11-09 09:00","2025-11-09 18:00","연속"]
[177,"경기북부","직할","녹양S/S #2 BUS","녹양S/S 170kV GIS 장기사용 대체공사","장기사용 GIS 철거 및 설치","2025-11-06 09:00","2025-11-09 09:00","2025-11-06 09:00","2025-11-09 09:00","연속"]
[178,"경기북부","직할","녹양백석#2 T/L","녹양S/S 170kV GIS 장기사용 대체공사","장기사용 GIS 철거 및 설치","2025-11-03 09:00","2025-12-05 18:00","2025-11-03 09:00","2025-12-05 18:00","연속"]
[179,"경기북부","직할","녹양S/S #1 BUS","녹양S/S 170kV GIS 장기사용 대체공사","장기사용 GIS 철거 및 설치","2025-11-03 09:00","2025-11-06 09:00","2025-11-03 09:00","2025-11-06 09:00","연속"]
[180,"경기북부","직할","백석덕계#1 T/L","25년 양주전력TF 170kV GIS 점검공사","덕계S/S 백석-덕계#1T/L GIS : 정밀점검","2025-11-17 09:00","2025-11-18 18:00","2025-11-17 09:00","2025-11-18 18:00","연속"]
[181,"경기북부","직할","신포천덕계#1 T/L","25년 양주전력TF 170kV GIS 점검공사","170kV GIS 정밀점검(백석-덕계#1TL) 시험가압용 선로","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[182,"경기북부","직할","백석덕계#2 T/L","25년 양주전력TF 170kV GIS 점검공사","170kV GIS 정밀점검(신포천-덕계#2TL) 시험가압용 선로","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[183,"경기북부","직할","백석덕계#1 T/L","25년 양주전력TF 170kV GIS 점검공사","170kV GIS 정밀점검(신포천-덕계#1TL) 시험가압용 선로","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[184,"경기북부","직할","신의정부내촌#1 T/L","345kV 신의정부-미금 등 19개 T/L 철탑추락방지시설 설치공사","ㅇ 수평 추락방지장치 설치 - 대상 : 345kV 신가평-신의정부#1 T/L No.120~134,136,138 (子 :  신의정부-내촌#1 T/L No.23~9,7,5)","2025-11-03 07:00","2025-11-05 18:00","2025-11-03 07:00","2025-11-05 18:00","연속"]
[185,"경기북부","직할","신의정부금오#1 T/L","24-25년 변전협력회사 총액공사","신의정부-금오 #1T/L 보호반 대체","2025-11-17 09:00","2025-11-19 18:00","2025-11-17 09:00","2025-11-19 18:00","연속"]
[186,"경기북부","직할","신의정부금오#2 T/L","24-25년 변전협력회사 총액공사","신의정부-금오 #2T/L 보호반 대체","2025-11-24 09:00","2025-11-26 18:00","2025-11-24 09:00","2025-11-26 18:00","연속"]
[187,"경기북부","직할","양주지축#2 T/L","가공송전 순시점검 위탁공사(고양)","정밀점검(양주-은평T/L) 관련 병가선로 휴전","2025-11-03 08:00","2025-11-07 18:00","2025-11-03 08:00","2025-11-07 18:00","연속"]
[188,"경기북부","직할","양주은평#1 T/L","가공송전 순시점검 위탁공사(고양)","정밀점검","2025-11-03 08:00","2025-11-07 18:00","2025-11-03 08:00","2025-11-07 18:00","연속"]
[189,"경기북부","직할","양주은평#2 T/L","가공송전 순시점검 위탁공사(고양)","정밀점검","2025-11-17 08:00","2025-11-21 18:00","2025-11-17 08:00","2025-11-21 18:00","연속"]
[190,"경기북부","직할","양주지축#1 T/L","가공송전 순시점검 위탁공사(고양)","정밀점검 관련 병가선로 휴전","2025-11-17 08:00","2025-11-21 18:00","2025-11-17 08:00","2025-11-21 18:00","연속"]
[191,"경기북부","직할","양주쌍문#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2025-11-10 07:30","2025-11-14 17:00","2025-11-10 07:30","2025-11-14 17:00","연속"]
[192,"경기북부","직할","양주쌍문#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2025-11-26 07:30","2025-11-28 17:00","2025-11-26 07:30","2025-11-28 17:00","연속"]
[193,"경기북부","직할","양주녹양#2 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2025-11-12 07:30","2025-11-19 17:00","2025-11-12 07:30","2025-11-19 17:00","연속"]
[194,"경기북부","직할","양주녹양#1 T/L","24~25년 고양전력 가공송전협력회사 총액공사","추락방지장치 설치","2025-11-03 07:30","2025-11-11 17:00","2025-11-03 07:30","2025-11-11 17:00","연속"]
[195,"경기북부","직할","옥정송우#1 T/L","옥정S/S  #4M.Tr 증설공사","옥정S/S  #4M.Tr 증설공사- 무부하가압 선로","2025-11-17 09:00","2025-11-19 18:00","2025-11-17 09:00","2025-11-19 18:00","연속"]
[196,"경기","군포","사강남양#2 T/L"," 남양-사강T/L 지중화공사_가공 본이설공사"," 남양-사강T/L 지중화공사_가공 본이설공사","2025-11-19 07:00","2025-12-03 13:00","2025-11-19 07:00","2025-12-03 13:00","연속"]
[197,"경기","군포","서서울#2S/S CB 6600","서서울#2S/S  6600 BUS-TIE GIS 보통점검","서서울#2S/S  #64-#69(6600) BUS-TIE GIS 보통점검","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[198,"경기","군포","서안양소래 T/L","광명-시흥지역 전기공급시설 전력구공사(남광명분기 1단계)","남광명변전소 신설로 기설 서안양#11맨홀 구조물 일부를 털어내고 확장하기 위한 공사로 활선에 인접하여 구조물 깨기공사 시행으로 휴전 신청","2025-11-24 09:00","2025-11-30 18:00","취소","취소","연속"]
[199,"경기","동부","감곡가남#1 T/L"," 이천-가남 등 2개T/L 용량증대 선종교체공사"," 감곡-가남T/L No.25~가남S/S 18.2km, 선종교체 ACSR240㎟→ASCC310㎟, 이천-가남#1 동시휴전(11/7~26), 이천-가남#2 동시휴전(11/27~29)","2025-11-11 07:00","2025-12-03 18:00","2025-11-11 07:00","2025-12-03 18:00","연속"]
[200,"경기","동부","이천가남#1 T/L"," 이천-가남 등 2개T/L 용량증대 선종교체공사"," 이천-가남T/L 이천S/S~가남S/S 12.9km, 선종교체 ACSR240㎟→ASCC310㎟, 감곡-가남#1 동시휴전(11/7~26)","2025-11-11 07:00","2025-11-30 18:00","2025-11-11 07:00","2025-11-30 18:00","연속"]
[201,"경기","동부","곤지암S/S SEC CB 61620","곤지암S/S #61-66 모선보호반 대체작업","곤지암S/S 61-66 모선보호반 대체작업","2025-11-17 09:00","2025-11-21 18:00","취소","취소","연속"]
[202,"경기","동부","곤지암S/S CB 6200","곤지암S/S #61-66 모선보호반 대체작업","곤지암S/S 61-66 모선보호반 대체작업","2025-11-17 09:00","2025-11-21 18:00","취소","취소","연속"]
[203,"경기","동부","곤지암S/S SEC CB 65660","곤지암S/S #61-66 모선보호반 대체작업","곤지암S/S 61-66 모선보호반 대체작업","2025-11-17 09:00","2025-11-21 18:00","취소","취소","연속"]
[204,"경기","동부","곤지암S/S SEC CB 60610","곤지암S/S #61-66 모선보호반 대체작업","곤지암S/S 61-66 모선보호반 대체작업","2025-11-17 09:00","2025-11-21 18:00","취소","취소","연속"]
[205,"경기","동부","곤지암S/S SEC CB 66670","곤지암S/S #61-66 모선보호반 대체작업","곤지암S/S 61-66 모선보호반 대체작업","2025-11-17 09:00","2025-11-21 18:00","취소","취소","연속"]
[206,"경기","동부","곤지암초월#1 T/L","곤지암-초월T/L 추락방지장치 설치","수평추락방지 설치(2회선 32기)","2025-11-24 07:30","2025-11-27 18:00","2025-11-24 07:30","2025-11-27 18:00","연속"]
[207,"경기","동부","정자동판교#1 T/L"," 동판교S/S #4M.Tr용 GIS 설치공사"," 동판교S/S #4M.Tr용 GIS 설치공사(무부하가압)","2025-11-26 15:00","2025-11-27 15:00","2025-11-26 15:00","2025-11-27 15:00","연속"]
[208,"경기","동부","오포모현#1 T/L"," 모현S/S #4M.Tr 증설공사 무부하 가압","#1BUS측 24시간 무부하 가압","2025-11-07 15:00","2025-11-08 18:00","2025-11-20T15:00:00","2025-11-21T18:00:00","연속"]
[209,"경기","동부","오포모현#1 T/L"," 모현S/S #4M.Tr 증설공사 무부하 가압","#2BUS측 24시간 무부하 가압","2025-11-14 15:00","2025-11-15 18:00","2025-11-26T15:00:00","2025-11-27T18:00:00","연속"]
[210,"경기","동부","동판교야탑 T/L","야탑S/S  동판교-야탑T/L(보통)","야탑:동판교-야탑T/L(보통)","2025-11-20 09:00","2025-11-20 18:00","2025-11-20 09:00","2025-11-20 18:00","연속"]
[211,"경기","동부","왕암여주#2 T/L","여주S/S  왕암-여주#1,2T/L GIS 메커니즘 대체작업","여주S/S  왕암-여주#1,2T/L GIS 메커니즘 대체작업","2025-11-19 14:00","2025-11-19 18:00","2025-11-19 14:00","2025-11-19 18:00","연속"]
[212,"경기","동부","왕암여주#1 T/L","여주S/S  왕암-여주#1,2T/L GIS 메커니즘 대체작업","여주S/S  왕암-여주#1,2T/L GIS 메커니즘 대체작업","2025-11-19 09:00","2025-11-19 14:00","2025-11-19 09:00","2025-11-19 14:00","연속"]
[213,"경기","동부","오천율현#1 T/L","2025년 가공송전 순시점검 위탁공사(정밀점검)"," 오천-율현#1T/L 정밀점검 대상 : No.1~25(총 25기)","2025-11-17 09:00","2025-11-18 18:00","2025-11-17 09:00","2025-11-18 18:00","연속"]
[214,"경기","동부","오천율현#2 T/L","2025년 가공송전 순시점검 위탁공사(정밀점검)"," 오천-율현#2T/L 정밀점검 대상 : No.1~25(총 25기)","2025-11-19 09:00","2025-11-20 18:00","2025-11-19 09:00","2025-11-20 18:00","연속"]
[215,"경기","동부","곤지암율현#2 T/L","2025년 가공송전 순시점검 위탁공사(정밀점검 안전이격확보)"," 오천-율현#1T/L 정밀점검(안전이격확보) 대상 : No.1~25(총 25기)","2025-11-17 09:00","2025-11-18 18:00","취소","취소","연속"]
[216,"경기","동부","곤지암율현#1 T/L","2025년 가공송전 순시점검 위탁공사(정밀점검 안전이격확보)"," 오천-율현#2T/L 정밀점검(안전이격확보) 대상 : No.1~25(총 25기)","2025-11-19 09:00","2025-11-20 18:00","취소","취소","연속"]
[217,"경기","동부","중원야탑 T/L","중원S/S 중원-야탑T/L 2DS 링크교체 외","야탑:중원-야탑T/L(보통) 중원:중원-야탑T/L(보통) * 중원-야탑 2DS 링크교체 * 중모 2DS 링크교체","2025-11-03 09:00","2025-11-04 18:00","2025-11-03 09:00","2025-11-04 18:00","연속"]
[218,"경기","성남","신용인S/S #65 BUS","2025년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검","2025-11-09 09:00","2025-11-09 18:00","취소","취소","연속"]
[219,"경기","성남","신용인S/S SEC CB 65660","2025년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검","2025-11-08 09:00","2025-11-09 18:00","취소","취소","연속"]
[220,"경기","성남","신용인S/S #60 BUS","2025년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검 무부하가압용","2025-11-02 09:00","2025-11-02 18:00","취소","취소","연속"]
[221,"경기","성남","신용인S/S SEC CB 60610","2025년 성남전력 170kV GIS 정밀점검공사","GIS 정밀점검","2025-11-01 09:00","2025-11-02 18:00","취소","취소","연속"]
[222,"경기","직할","과천동안양#2 T/L","24-25년 군포전력지사 가공송전협력회사 공사","의왕-동안양#1T/L 병가구간 안전이격거리확보","2025-11-14 07:00","2025-11-14 17:00","2025-11-14 07:00","2025-11-14 17:00","연속"]
[223,"경기","직할","율전의왕#2 T/L","24-25년 군포전력지사 가공송전협력회사 공사","송전선로용 피뢰기 설치 (39SET)","2025-11-03 07:00","2025-11-09 17:00","2025-11-03 07:00","2025-11-09 17:00","연속"]
[224,"경기","직할","의왕동안양#2 T/L"," 의왕S/S 디지털화공사","전력설비 감시·제어·계측 디지털화","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[225,"경기","직할","의왕동안양#1 T/L","24-25년 군포전력지사 가공송전협력회사 공사","송전선로용 피뢰기 설치 (123SET)","2025-11-01 07:00","2025-11-14 17:00","2025-11-01 07:00","2025-11-14 17:00","연속"]
[226,"경기","평택","고덕#2평택#2 T/L","2025-2026년 경기본부 평택전력지사 지중송전 협력회사 공사","케이블타워 및 피뢰기 점검(피뢰기 절연열화 측정)","2025-11-05 08:00","2025-11-05 18:00","2025-11-05 08:00","2025-11-05 18:00","연속"]
[227,"경기","평택","고덕진위#2 T/L"," 방여울분기 지중T/L 건설공사","평택 브레인시티 신규부하 전력공급능력 확보","2025-11-21 09:00","2025-12-21 18:00","2025-11-21 09:00","2025-12-21 18:00","연속"]
[228,"경기","평택","송탄안성 T/L","2025년 평택전력 변전협력회사 총액공사(송탄안성)","보호반 대체 / GIS 보통점검 / LA 보통점검 / CVT 대체","2025-11-27 09:00","2025-11-30 18:00","2025-11-27 09:00","2025-11-30 18:00","연속"]
[229,"경기","평택","송탄오성CC#1 T/L"," 평택-추팔 등 2개T/L 지중화공사_가공(LH요청)"," 평택추팔 13호(송탄오성6호) 현장실측 및 도면작성용역","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[230,"경기","평택","진위동탄#1 T/L","보호반 보호계전기 모듈교체","보호반 보호계전기 모듈교체","2025-11-27 09:00","2025-11-27 18:00","취소","취소","연속"]
[231,"경기","평택","평택추팔#2 T/L"," 평택-추팔T/L 용량증대 선종교체공사","작업구간 : No.26~27(철도횡단), 43~추팔S/S 작업내용 : ACSR 330sq -> ASCC/TW(탄소-금속) 410sq","2025-11-17 08:00","2025-11-26 18:00","2025-11-17 08:00","2025-11-26 18:00","연속"]
[232,"경기","평택","둔포추팔#1 T/L"," 평택-추팔T/L 용량증대 선종교체공사(안전거리 확보)","작업구간 : No.47~추팔S/S 작업내용 : ACSR 330sq -> ASCC/TW(탄소-금속) 410sq","2025-11-30 08:00","2025-11-30 18:00","취소","취소","연속"]
[233,"경기","평택","둔포추팔#2 T/L"," 평택-추팔T/L 용량증대 선종교체공사(안전거리 확보)","작업구간 : No.47~추팔S/S 작업내용 : ACSR 330sq -> ASCC/TW(탄소-금속) 410sq","2025-11-29 08:00","2025-11-30 18:00","취소","취소","연속"]
[234,"경기","평택","둔포추팔#1 T/L"," 평택-추팔T/L 용량증대 선종교체공사(안전거리 확보)","작업구간 : No.47~추팔S/S 작업내용 : ACSR 330sq -> ASCC/TW(탄소-금속) 410sq","2025-11-22 08:00","2025-11-23 18:00","취소","취소","연속"]
[235,"경기","평택","포승평택TP#2 T/L"," 평택T/L SW 증설공사(기아)","- 무부하가압 선로","2025-11-19 09:00","2025-11-20 18:00","2025-11-19 09:00","2025-11-20 18:00","연속"]
[236,"경기","평택","포승평택TP#2 T/L"," 평택T/L SW 증설공사(기아)","- 무부하가압 선로","2025-11-05 09:00","2025-11-06 18:00","2025-11-05 09:00","2025-11-06 18:00","연속"]
[237,"경기","군포","시화중시화 T/L","시화S/S  시화-중시화T/L GIS 보통점검","시화S/S  시화-중시화T/L GIS 보통점검","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[238,"강원","강릉","속초간성#1 T/L","2025년 강릉전력지사 변전협력회사 총액공사","속초간성#1 SPS 준공시험","2025-11-27 09:00","2025-11-27 18:00","2025-11-27 09:00","2025-11-27 18:00","연속"]
[239,"강원","강릉","속초간성#2 T/L","2025년 강릉전력지사 변전협력회사 총액공사","속초간성#2 SPS 준공시험","2025-11-28 09:00","2025-11-28 18:00","2025-11-28 09:00","2025-11-28 18:00","연속"]
[240,"강원","강릉","신양양양양#2 T/L"," 신양양속초 등 3개T/L 추락방지장치설치공사"," 신양양양양 #2T/L : 수직 및 수평 추락방지장치 설치","2025-11-17 07:00","2025-11-21 17:00","2025-11-17 07:00","2025-11-21 17:00","매일"]
[241,"강원","강릉","신양양속초#1 T/L"," 신양양속초 등 3개T/L 추락방지장치설치공사"," 신양양속초 #1T/L : 수직 및 수평 추락방지장치 설치","2025-11-17 07:00","2025-11-28 17:00","2025-11-17 07:00","2025-11-28 17:00","매일"]
[242,"강원","강릉","횡계올림픽 T/L","2025년 강릉전력지사 변전협력회사 총액공사","170kV GIS,LA 보통점검","2025-11-24 10:00","2025-11-24 18:00","2025-11-24 10:00","2025-11-24 18:00","연속"]
[243,"강원","강릉","주진평창#2 T/L"," 신양양속초 등 3개T/L 추락방지장치 설치공사"," 주진평창 #2 T/L : 수직 및 수평 추락방지장치 설치","2025-11-03 07:00","2025-11-07 18:00","2025-11-03 07:00","2025-11-07 18:00","매일"]
[244,"강원","강릉","평창올림픽 T/L","평창S/S 디지털화 공사","평창올림픽T/L 디지털화 결선 변경","2025-11-17 10:00","2025-11-18 18:00","2025-11-17 10:00","2025-11-18 18:00","연속"]
[245,"강원","동해","북평영동TP#1 T/L","진동저감댐퍼 실 선로 현장실증","新진동저감댐퍼 실선로 현장실증","2025-11-29 13:00","2025-11-29 18:00","2025-11-29 13:00","2025-11-29 18:00","연속"]
[246,"강원","동해","이원도계 T/L","66kV 동해전철#1,#2T/L 철거공사","66kV 동해전철#2T/L(이원S/S) 철거시, 안전이격거리 확보를 위한 휴전신청","2025-11-04 08:00","2025-11-04 18:00","2025-11-04 08:00","2025-11-04 18:00","연속"]
[247,"강원","동해","이원태백 T/L","66kV 동해전철#1,#2T/L 철거공사","66kV 동해전철#2T/L(이원S/S) 철거시, 안전이격거리 확보를 위한 휴전신청","2025-11-03 08:00","2025-11-03 18:00","2025-11-03 08:00","2025-11-03 18:00","연속"]
[248,"강원","동해","이원삼척 T/L"," 이원-도계 1파이분기T/L 건설공사","□ 공 사 명 :  이원-도계 1파이분기 T/L건설공사 □ 공사목적 : 삼척변전소 단일계통 보강을 통한 안정적 전력공급 □ 공사구간 : 기설  이원-태백T/L No.111~신설No.14(2C) 기설  삼척분기T/L No.22~삼척S/S(4C 하단)","2025-11-03 09:00","2025-11-27 18:00","2025-11-03 09:00","2025-11-27 18:00","연속"]
[249,"강원","원주","원주북원주#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","추락방지장치 설치","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[250,"강원","원주","원주서원주#1 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","추락방지장치 설치","2025-11-03 09:00","2025-11-04 18:00","2025-11-03 09:00","2025-11-04 18:00","매일"]
[251,"강원","원주","서원주문막#2 T/L","2024-25년 원주전력지사 가공송전 협력회사 공사","추락방지장치 설치","2025-11-04 09:00","2025-11-08 18:00","2025-11-04 09:00","2025-11-08 18:00","매일"]
[252,"강원","원주","홍천상남#1 T/L","2025년 원주전력지사 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2025-11-17 09:00","2025-11-22 18:00","2025-11-17 09:00","2025-11-22 18:00","매일"]
[253,"강원","원주","홍천상남#2 T/L","2025년 원주전력지사 가공송전선로 순시점검 위탁공사","송전선로 정밀점검","2025-11-24 09:00","2025-11-29 18:00","2025-11-24 09:00","2025-11-29 18:00","매일"]
[254,"강원","직할","남춘천춘천 T/L","2024~2025년 강원본부 직할 송전협력회사 공사","항공장애표시구 설치 및 조류착지방지장치 설치","2025-11-10 07:00","2025-11-11 18:00","2025-11-10 07:00","2025-11-11 18:00","매일"]
[255,"강원","직할","서홍천춘천열병합 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  서홍천-춘천열병합 T/L GIS 정밀점검 □ 서홍천S/S  서홍천-춘천열병합 T/L GIS 정밀점검","2025-11-24 09:00","2025-11-28 18:00","2025-11-24 09:00","2025-11-28 18:00","연속"]
[256,"강원","직할","서홍천S/S CB 6100","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 서홍천S/S  서홍천-춘천열병합T/L GIS 정밀점검 후 무부하 가압용","2025-11-28 14:00","2025-11-28 18:00","2025-11-28 14:00","2025-11-28 18:00","연속"]
[257,"강원","직할","서홍천S/S #1 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 서홍천S/S  서홍천-춘천열병합T/L GIS 정밀점검 후 무부하 가압용","2025-11-28 14:00","2025-11-28 18:00","2025-11-28 14:00","2025-11-28 18:00","연속"]
[258,"강원","직할","인제양구#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","인제양구#1 T/L 디지털화 공사","2025-11-17 09:00","2025-11-19 13:00","2025-11-17 09:00","2025-11-19 13:00","연속"]
[259,"강원","직할","상남인제#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","상남-인제#2T/L 디지털화 공사","2025-11-05 13:00","2025-11-07 18:00","2025-11-05 13:00","2025-11-07 18:00","연속"]
[260,"강원","직할","상남인제#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","상남-인제#1T/L 디지털화 공사","2025-11-03 09:00","2025-11-05 13:00","2025-11-03 09:00","2025-11-05 13:00","연속"]
[261,"강원","직할","인제양구#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","인제양구#2 T/L 디지털화 공사","2025-11-19 13:00","2025-11-21 18:00","2025-11-19 13:00","2025-11-21 18:00","연속"]
[262,"강원","직할","간성인제#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","간성인제#1 T/L 디지털화 공사","2025-11-24 09:00","2025-11-26 13:00","2025-11-24 09:00","2025-11-26 13:00","연속"]
[263,"강원","직할","간성인제#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","간성인제#2T/L 디지털화 공사","2025-11-26 13:00","2025-11-28 18:00","2025-11-26 13:00","2025-11-28 18:00","연속"]
[264,"강원","직할","춘천S/S #2 BUS","2024~2025년 강원본부 직할 변전협력회사 공사","□ 춘천S/S  PT GIS 보통점검","2025-11-10 13:00","2025-11-10 15:00","2025-11-10 13:00","2025-11-10 15:00","연속"]
[265,"강원","직할","춘천S/S #1 BUS","2024~2025년 강원본부 직할 변전협력회사 공사","□ 춘천S/S  PT GIS 보통점검","2025-11-10 10:00","2025-11-10 12:00","2025-11-10 10:00","2025-11-10 12:00","연속"]
[266,"강원","직할","춘천S/S #1 BUS","2024~2025년 강원본부 직할 변전협력회사 공사","□ 춘천S/S  #1BUS PT 보통점검","2025-11-25 10:00","2025-11-25 12:00","2025-11-25 10:00","2025-11-25 12:00","연속"]
[267,"강원","직할","남춘천춘천열병합#1 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  서홍천-춘천열병합 T/L GIS 정밀점검 후 무부하 가압용","2025-11-26 09:00","2025-11-26 12:00","2025-11-26 09:00","2025-11-26 12:00","연속"]
[268,"강원","직할","춘천열병합 CB 6100","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  STATION AUX Tr GIS 정밀점검 후 무부하 가압용","2025-11-12 13:00","2025-11-12 18:00","2025-11-12 13:00","2025-11-12 18:00","연속"]
[269,"강원","직할","청평PP춘천열병합 T/L","2025년 가공송전 순시점검 위탁공사","청평PP 인출  청평PP-춘천열병합T/L 회선 절연저항 측정","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[270,"강원","직할","춘천열병합 #1 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  서홍천-춘천열병합T/L GIS 정밀점검 후 무부하 가압용","2025-11-26 09:00","2025-11-26 12:00","2025-11-26 09:00","2025-11-26 12:00","연속"]
[271,"강원","직할","화천화천HP#2 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 화천S/S  화천-화천HP#2 T/L GIS 보통점검","2025-11-11 10:00","2025-11-11 18:00","2025-11-11 10:00","2025-11-11 18:00","연속"]
[272,"강원","직할","화천화천HP#1 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 화천S/S  화천-화천HP#1 T/L GIS 보통점검","2025-11-10 10:00","2025-11-10 18:00","2025-11-10 10:00","2025-11-10 18:00","연속"]
[273,"강원","태백","동해동영월 T/L","24~25년 태백전력지사 송전 협력회사 공사"," 동영월 분기 T/L 수평추락방지장치 설치","2025-11-06 09:00","2025-11-07 18:00","2025-11-06 09:00","2025-11-07 18:00","매일"]
[274,"강원","태백","동영월영월CC T/L","24~25년 태백전력지사 송전 협력회사 공사"," 동영월 분기 T/L 수평추락방지장치 설치","2025-11-03 09:00","2025-11-05 18:00","2025-11-03 09:00","2025-11-05 18:00","매일"]
[275,"강원","태백","정선영월CC T/L","24~25년 태백전력지사 송전 협력회사 공사"," 영월화력T/L 수평추락방지장치 설치","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[276,"강원","태백","신제천영월CC#2 T/L","24~25년 태백전력지사 송전 협력회사 공사"," 영월화력 T/L 수평추락방지장치 설치","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[277,"강원","태백","신제천영월CC#1 T/L","24~25년 태백전력지사 송전 협력회사 공사"," 영월화력 T/L 수평추락방지장치 설치","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[278,"강원","태백","태백삼척GP#2 T/L","2024-2025 태백전력지사 변전협력회사 공사","태백S/S 태백삼척GP#2 T/L 1차 GIS 보통점검","2025-11-10 09:00","2025-11-10 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[279,"강원","태백","태백S/S CB 6200","2024-2025 태백전력지사 변전협력회사 공사","태백S/S  #61-#66 BUS TIE GIS 보통점검","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[280,"강원","태백","태백영월에코윈드 T/L","2025년 태백전력지사  GIS 정밀점검공사","태백S/S  태백영월에코윈드 T/L GIS 정밀점검","2025-11-24 09:00","2025-11-25 18:00","2025-11-24 09:00","2025-11-25 18:00","연속"]
[281,"강원","강릉","강릉영동TP T/L","345kV 동해-북평T/P 등 3개 T/L 온라인PD 진단시스템 설치공사"," 영동T/P-강릉T/L ON-LINE PD 진단시스템 설치","2025-11-29 08:00","2025-11-29 12:00","2025-11-29 08:00","2025-11-29 12:00","연속"]
[282,"충북","직할","광혜원대소#2 T/L","광혜원S/S 23kV 장기사용 GIS 교체공사(병행)","제어/감시/경보 제어케이블 RTU → LID 이설 및 보호반 엔지니어링","2025-11-03 10:00","2025-11-04 18:00","2025-11-03 10:00","2025-11-04 18:00","연속"]
[283,"충북","직할","광혜원대소#1 T/L","광혜원S/S 23kV 장기사용 GIS 교체공사(병행)","제어/감시/경보 제어케이블 RTU → LID 이설 및 보호반 엔지니어링","2025-11-05 10:00","2025-11-06 18:00","2025-11-05 10:00","2025-11-06 18:00","연속"]
[284,"충북","직할","서운광혜원 T/L","24~25 충북직할 가공송전 협력회사 총액공사","전선접속개소 전선교체공사","2025-11-17 07:00","2025-11-24 18:00","2025-11-17 07:00","2025-11-24 18:00","연속"]
[285,"충북","직할","신진천S/S SEC CB 65660","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #65-66 BUS SEC GIS 보통점검 및 전자변 교체","2025-11-19 10:00","2025-11-19 18:00","2025-11-19 10:00","2025-11-19 18:00","연속"]
[286,"충북","직할","신진천S/S SEC CB 66670","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #66-67 BUS SEC GIS 보통점검 및 전자변 교체","2025-11-20 10:00","2025-11-20 18:00","2025-11-20 10:00","2025-11-20 18:00","연속"]
[287,"충북","직할","신진천S/S SEC CB 61620","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #61-62 BUS SEC GIS 보통점검 및 전자변 교체","2025-11-18 10:00","2025-11-18 18:00","2025-11-18 10:00","2025-11-18 18:00","연속"]
[288,"충북","직할","신진천S/S SEC CB 60610","'24-25년 충북본부 직할 변전협력회사 공사","신진천S/S  #60-61 BUS SEC GIS 보통점검 및 전자변 교체","2025-11-17 10:00","2025-11-17 18:00","2025-11-17 10:00","2025-11-17 18:00","연속"]
[289,"충북","직할","진천광혜원#1 T/L","24~25 충북직할 가공송전 협력회사 총액공사","전선접속개소 전선교체공사","2025-11-17 07:00","2025-11-24 18:00","2025-11-17 07:00","2025-11-24 18:00","연속"]
[290,"충북","청주","남청주오송#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 전자변교체 LA, CVT 점검","2025-11-04 10:00","2025-11-04 18:00","2025-11-04 10:00","2025-11-04 18:00","연속"]
[291,"충북","청주","남청주S/S #67 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(11월)","2025-11-03 14:00","2025-11-08 14:00","2025-11-03 14:00","2025-11-08 14:00","연속"]
[292,"충북","청주","남청주오송#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 전자변교체 LA, CVT 점검","2025-11-03 10:00","2025-11-03 18:00","2025-11-03 10:00","2025-11-03 18:00","연속"]
[293,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(11월)","2025-11-01 07:00","2025-11-03 14:00","2025-11-01 07:00","2025-11-03 14:00","연속"]
[294,"충북","청주","남청주S/S SEC CB 67660","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(11월)","2025-11-01 07:00","2025-11-12 18:00","2025-11-01 07:00","2025-11-12 18:00","연속"]
[295,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_11월)","2025-11-01 07:00","2025-11-03 14:00","2025-11-01 07:00","2025-11-03 14:00","연속"]
[296,"충북","청주","남청주S/S #66 BUS","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(11월)","2025-11-08 14:00","2025-11-12 18:00","2025-11-08 14:00","2025-11-12 18:00","연속"]
[297,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(2차)","#66-67 SEC GIS 대체(무부하가압용_11월)","2025-11-11 14:00","2025-11-12 18:00","2025-11-11 14:00","2025-11-12 18:00","연속"]
[298,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(안전이격확보/무부하가압용_11월)","2025-11-14 07:00","2025-11-16 14:00","취소","취소","매일"]
[299,"충북","청주","남청주S/S SEC CB 62610","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(11월)","2025-11-14 07:00","2025-11-30 18:00","취소","취소","연속"]
[300,"충북","청주","남청주S/S #62 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(11월)","2025-11-14 14:00","2025-11-16 14:00","취소","취소","연속"]
[301,"충북","청주","남청주S/S #61 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(11월)","2025-11-16 14:00","2025-11-20 14:00","취소","취소","연속"]
[302,"충북","청주","남청주청주#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체(무부하가압용_11월)","2025-11-19 14:00","2025-11-20 14:00","취소","취소","연속"]
[303,"충북","청주","남청주S/S #62 BUS","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC 대체 (11월)","2025-11-20 14:00","2025-11-30 18:00","취소","취소","연속"]
[304,"충북","청주","남청주오송#1 T/L","남청주S/S  장기사용 GIS 대체공사(3차)","#61-62 SEC GIS 대체 (안전이격확보/무부하가압용_11월)","2025-11-20 14:00","2025-11-30 18:00","취소","취소","매일"]
[305,"충북","청주","화동보은 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검 및 LA,CVT 교체","2025-11-21 10:00","2025-11-21 18:00","2025-11-21 10:00","2025-11-21 18:00","연속"]
[306,"충북","청주","율량봉명#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 조작시험","2025-11-05 15:00","2025-11-05 18:00","2025-11-05 15:00","2025-11-05 18:00","연속"]
[307,"충북","청주","율량봉명#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 조작시험","2025-11-05 12:00","2025-11-05 15:00","2025-11-05 12:00","2025-11-05 15:00","연속"]
[308,"충북","청주","서청주사직#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사","170kV GIS 조작시험","2025-11-06 13:00","2025-11-06 18:00","2025-11-06 13:00","2025-11-06 18:00","연속"]
[309,"충북","청주","서청주사직#2 T/L","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-11-26 09:00","2025-11-27 18:00","2025-11-26 09:00","2025-11-27 18:00","연속"]
[310,"충북","청주","신옥천S/S SEC CB 66670","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-11-07 10:00","2025-11-07 18:00","2025-11-07 10:00","2025-11-07 18:00","연속"]
[311,"충북","청주","신옥천S/S SEC CB 61620","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검","2025-11-06 10:00","2025-11-06 18:00","2025-11-06 10:00","2025-11-06 18:00","연속"]
[312,"충북","청주","옥천영동 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검 및 LA,CVT 교체(양단)","2025-11-24 10:00","2025-11-25 18:00","2025-11-24 10:00","2025-11-25 18:00","연속"]
[313,"충북","청주","화동영동 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검 및 LA,CVT 교체","2025-11-20 10:00","2025-11-20 18:00","2025-11-20 10:00","2025-11-20 18:00","연속"]
[314,"충북","청주","오송국사#1 T/L"," 신청주-문백T/L 건설공사","안전이격 확보 4회선구간 하단 병행휴전","2025-11-04 07:00","2025-11-10 18:00","2025-11-04 07:00","2025-11-10 18:00","매일"]
[315,"충북","청주","오송국사#1 T/L"," 신청주-문백T/L 건설공사","안전이격 확보 4회선구간 하단 병행휴전","2025-11-17 07:00","2025-11-23 18:00","2025-11-17 07:00","2025-11-23 18:00","매일"]
[316,"충북","청주","오창국사#2 T/L"," 신청주-문백T/L 건설공사"," 오창-국사 #2T/L 4회선 병가선로 구성","2025-11-17 07:00","2025-11-23 18:00","2025-11-17 07:00","2025-11-23 18:00","연속"]
[317,"충북","청주","오창국사#1 T/L"," 신청주-문백T/L 건설공사"," 오창-국사 #1T/L 4회선 병가선로 구성","2025-11-10 07:00","2025-11-16 18:00","2025-11-10 07:00","2025-11-16 18:00","연속"]
[318,"충북","청주","옥천보은 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," 송전선로 보호반교체 LA,CVT 교체(양단)","2025-11-10 10:00","2025-11-12 18:00","2025-11-10 10:00","2025-11-12 18:00","연속"]
[319,"충북","청주","죽림S/S CB 6100","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-11-17 09:00","2025-11-18 18:00","2025-11-17 09:00","2025-11-18 18:00","연속"]
[320,"충북","청주","죽림S/S #1 BUS","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검(BUS TIE 정밀 관련 모선절체용)","2025-11-17 09:00","2025-11-18 18:00","2025-11-17 09:00","2025-11-18 18:00","연속"]
[321,"충북","청주","남청주죽림#1 T/L","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-11-10 09:00","2025-11-11 18:00","2025-11-10 09:00","2025-11-11 18:00","연속"]
[322,"충북","청주","죽림서청주#1 T/L","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검 무부하가압용(BUS TIE 정밀점검)","2025-11-18 15:00","2025-11-18 18:00","2025-11-18 15:00","2025-11-18 18:00","연속"]
[323,"충북","충주","감곡가남#1 T/L"," 감곡-가남T/L 용량증대 전선교체공사","감곡가남 5호 안전이격확보 (롱암설치)","2025-11-02 08:00","2025-11-03 18:00","2025-11-02 08:00","2025-11-03 18:00","연속"]
[324,"충북","충주","감곡가남#2 T/L"," 감곡-가남T/L 용량증대 전선교체공사","감곡가남 5호 안전이격확보 (신설조립)","2025-11-04 08:00","2025-11-06 18:00","2025-11-04 08:00","2025-11-06 18:00","연속"]
[325,"충북","충주","음성금왕#2 T/L","24~25 충북직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치","2025-11-25 07:00","2025-11-28 18:00","2025-11-25 07:00","2025-11-28 18:00","매일"]
[326,"충북","충주","금왕남음성#1 T/L","24~25 충북직할 가공송전 협력회사 총액공사","수평 추락방지장치 설치","2025-11-25 07:00","2025-11-28 18:00","2025-11-25 07:00","2025-11-28 18:00","매일"]
[327,"충북","충주","단양영월CC#1 T/L","단양S/S 단양영월CC#1T/L LA 대체","단양S/S 단양영월CC#1T/L LA 대체","2025-11-05 10:00","2025-11-05 18:00","2025-11-05 10:00","2025-11-05 18:00","연속"]
[328,"충북","충주","단양S/S #66 BUS","단양S/S STATCOM 설치공사용 개폐장치 설치공사(전문)","C/H 커버 구간 및 1차 전력케이블 무부하 가압","2025-11-26 14:00","2025-11-27 14:00","2025-11-26 14:00","2025-11-27 14:00","연속"]
[329,"충북","충주","점촌단양 T/L","단양S/S STATCOM 설치공사용 개폐장치 설치공사(전문)","C/H 커버 구간 및 1차 전력케이블 무부하 가압","2025-11-26 14:00","2025-11-27 14:00","2025-11-26 14:00","2025-11-27 14:00","연속"]
[330,"충북","충주","신충주북충주#1 T/L","2024~2025년 충주전력지사 송전협력회사 공사","상간스페이서 설치( 신충주-북충주T/L No.71~72)","2025-11-18 07:00","2025-11-18 18:00","2025-11-18 07:00","2025-11-18 18:00","연속"]
[331,"충북","충주","신충주북충주#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","상간스페이서 설치( 신충주-북충주T/L No.71~72)","2025-11-17 07:00","2025-11-17 18:00","2025-11-17 07:00","2025-11-17 18:00","연속"]
[332,"충북","충주","신제천S/S #67 BUS","신제천S/S  #4Sh.C GIS 가스누기 보수공사(무부하)","-#4Sh.C GIS 가스누기 보수 공사 후 무부하 가압용","2025-11-19 09:00","2025-11-19 13:00","2025-11-19 09:00","2025-11-19 13:00","연속"]
[333,"충북","충주","신제천S/S SEC CB 65660","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  65-66 BUS-SEC GIS 보통점검","2025-11-07 09:00","2025-11-07 14:00","2025-11-07 09:00","2025-11-07 14:00","연속"]
[334,"충북","충주","신제천S/S CB 6200","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  61-66 BUS-TIE GIS 보통점검","2025-11-07 14:00","2025-11-07 18:00","2025-11-07 14:00","2025-11-07 18:00","연속"]
[335,"충북","충주","신제천S/S SEC CB 61620","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  61-62 BUS-SEC GIS 보통점검","2025-11-14 14:00","2025-11-14 18:00","2025-11-14 14:00","2025-11-14 18:00","연속"]
[336,"충북","충주","신제천S/S SEC CB 60610","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  60-61 BUS-SEC GIS 보통점검","2025-11-12 09:00","2025-11-12 14:00","2025-11-12 09:00","2025-11-12 14:00","연속"]
[337,"충북","충주","신제천S/S CB 6100","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  60-65 BUS-TIE GIS 보통점검","2025-11-11 09:00","2025-11-11 14:00","2025-11-11 09:00","2025-11-11 14:00","연속"]
[338,"충북","충주","신제천S/S CB 6300","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S  #62-67 BUS-TIE GIS 보통점검","2025-11-12 14:00","2025-11-12 18:00","2025-11-12 14:00","2025-11-12 18:00","연속"]
[339,"충북","충주","신제천제천#1 T/L","2024~2025년 충주전력지사 송전협력회사 공사","애자교체( 신제천-제천#1 T/L No.27-8)","2025-11-20 07:00","2025-11-21 18:00","취소","취소","매일"]
[340,"충북","충주","신제천왕암#1 T/L","2024~2025년 충주전력지사 송전협력회사 공사","국산지지애자교체( 신제천-왕암#1 T/L No.23) /  신제천-제천#1T/L 병가선로","2025-11-20 07:00","2025-11-20 18:00","취소","취소","연속"]
[341,"충북","충주","신제천S/S CB 6300","신제천S/S  #4Sh.C 가스누기 보수","신제천S/S  #4Sh.C 가스누기 보수 공사(무부하가압용)","2025-11-19 09:00","2025-11-19 13:00","2025-11-19 09:00","2025-11-19 13:00","연속"]
[342,"충북","충주","신제천S/S SEC CB 66670","신제천S/S  #4Sh.C 가스누기 보수공사(무부하가압용)","신제천S/S  #4Sh.C 가스누기 보수공사(무부하가압용)","2025-11-19 09:00","2025-11-19 13:00","2025-11-19 09:00","2025-11-19 13:00","연속"]
[343,"충북","충주","신충주음성#1 T/L","신충주,음성S/S 신충주음성#1 T/L 보호반 대체","신충주,음성S/S 신충주음성#1 T/L 보호반 대체(양단),음성S/S CVT 보통점검","2025-11-03 09:00","2025-11-06 18:00","2025-11-03 09:00","2025-11-06 18:00","연속"]
[344,"충북","충주","신충주음성#2 T/L","신충주,음성S/S 신충주음성#2 T/L 보호반 대체","신충주,음성S/S 신충주음성#2 T/L 보호반 대체,CVT 대체","2025-11-10 10:00","2025-11-12 18:00","2025-11-10 10:00","2025-11-12 18:00","연속"]
[345,"충북","충주","왕암북충주 T/L","왕암S/S STATCOM용 개폐장치 설치공사(전문)","C/H 커버구간 및 1차 전력케이블 무부하 가압","2025-11-27 14:00","2025-11-28 14:00","2025-11-27 14:00","2025-11-28 14:00","연속"]
[346,"충북","충주","왕암S/S #1 BUS","왕암S/S STATCOM용 개폐장치 설치공사(전문)","C/H 커버구간 및 1차 전력케이블 무부하 가압","2025-11-27 14:00","2025-11-28 14:00","2025-11-27 14:00","2025-11-28 14:00","연속"]
[347,"충북","충주","음성금왕#1 T/L","충주전력 효성제 170㎸ GIS 메커니즘 부품교체공사","음성S/S  음성-금왕#1TL 발청베어링 교체공사","2025-11-14 10:00","2025-11-14 14:00","2025-11-14 10:00","2025-11-14 14:00","연속"]
[348,"충북","충주","제천영월#1 T/L","25-26년 충북본부 직할 지중송전협력회사공사"," 제천-영월 #1T/L 피뢰기 열화진단","2025-11-12 10:00","2025-11-12 18:00","2025-11-12 10:00","2025-11-12 18:00","연속"]
[349,"충북","충주","충주풍동 T/L","2024~2025년 충주전력지사 송전협력회사 공사","피뢰기 설치( 충주-풍동T/L No.1~75)+풍동변전소 외벽공사","2025-11-03 07:00","2025-11-08 18:00","2025-11-03 07:00","2025-11-08 18:00","연속"]
[350,"충북","충주","충주충주HP#2 T/L","25년 충주전력지사 362,170kV GIS 보통점검공사","충주S/S  충주-충주HP#2T/L GIS 보통점검","2025-11-18 09:00","2025-11-18 14:00","2025-11-18 09:00","2025-11-18 14:00","연속"]
[351,"충북","충주","충주충주HP#1 T/L","25년 충주전력지사 362,170kV GIS 보통점검공사","충주S/S  충주-충주HP#1T/L GIS 보통점검","2025-11-17 09:00","2025-11-17 14:00","2025-11-17 09:00","2025-11-17 14:00","연속"]
[352,"충북","충주","왕암충주 T/L","25년 충주전력지사 362,170kV GIS 보통점검공사","충주S/S  왕암-충주 T/L GIS 보통점검","2025-11-25 09:00","2025-11-25 14:00","2025-11-25 09:00","2025-11-25 14:00","연속"]
[353,"충북","충주","풍동음성#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","피뢰기 설치( 충주-풍동T/L No.1~75) -병가구간 안전을 위한 휴전(풍동음성#2 실작업 없음)","2025-11-07 07:00","2025-11-08 18:00","2025-11-07 07:00","2025-11-08 18:00","매일"]
[354,"대전세종충남","대전","추부금산#1 T/L","[취소시][가압X]금산S/S  추부-금산#1T/L 보통점검","[취소시][가압X]금산S/S  추부-금산#1T/L 보통점검","2025-11-06 09:00","2025-11-06 18:00","취소","취소","연속"]
[355,"대전세종충남","대전","금산무주#1 T/L","[송전][즉시가압O]345kV신옥천-청양등8개TL 추락방지 설치공사","[즉시가압O]345kV신옥천-청양등8개TL 추락방지 설치공사","2025-11-17 07:00","2025-11-21 11:00","취소","취소","매일"]
[356,"대전세종충남","대전","추부금산#2 T/L","[취소시][가압X]금산S/S  추부-금산#2T/L 보통점검","[취소시][가압X]금산S/S  추부-금산#2T/L 보통점검","2025-11-07 09:00","2025-11-07 18:00","취소","취소","연속"]
[357,"대전세종충남","대전","남대전신흥#1 T/L","[취소시][가압O]남대전S/S 남대전-신흥#1T/L 하자점검","[취소시][가압O]남대전S/S 남대전-신흥#1T/L 하자점검","2025-11-03 09:00","2025-11-03 18:00","취소","취소","연속"]
[358,"대전세종충남","대전","남대전신흥#2 T/L","[취소시][가압O]남대전S/S 남대전-신흥#2T/L 하자점검","[취소시][가압O]남대전S/S 남대전-신흥#2T/L 하자점검","2025-11-04 09:00","2025-11-04 18:00","취소","취소","연속"]
[359,"대전세종충남","대전","신옥천남대전#1 T/L","[취소시][가압O]남대전S/S 신옥천-남대전#1T/L 하자점검","[취소시][가압O]남대전S/S 신옥천-남대전#1T/L 하자점검","2025-11-17 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[360,"대전세종충남","대전","신옥천남대전#2 T/L","(10월 취소시) 신옥천-남대전T/L 지장수목전지 및 벌채","(10월 취소시) 신옥천-남대전T/L 지장수목전지 및 벌채","2025-11-19 09:00","2025-11-20 18:00","2025-11-19 09:00","2025-11-20 18:00","매일"]
[361,"대전세종충남","대전","신옥천남대전#4 T/L","[취소시][가압O]남대전S/S 신옥천-남대전#4T/L 하자점검","[취소시][가압O]남대전S/S 신옥천-남대전#4T/L 하자점검","2025-11-26 09:00","2025-11-26 18:00","2025-11-26 09:00","2025-11-26 18:00","연속"]
[362,"대전세종충남","대전","신옥천남대전#3 T/L"," 신옥천-남대전삼사T/L 지장수목전지 및 벌채"," 신옥천-남대전삼사T/L 지장수목전지 및 벌채","2025-11-24 09:00","2025-11-25 18:00","2025-11-24 09:00","2025-11-25 18:00","매일"]
[363,"대전세종충남","대전","신옥천남대전#4 T/L"," 신옥천-남대전삼사T/L 지장수목전지 및 벌채"," 신옥천-남대전삼사T/L 지장수목전지 및 벌채","2025-11-26 09:00","2025-11-27 18:00","2025-11-26 09:00","2025-11-27 18:00","매일"]
[364,"대전세종충남","대전","신옥천남대전#1 T/L","(10월 취소시) 신옥천-남대전T/L 지장수목전지 및 벌채","(10월 취소시) 신옥천-남대전T/L 지장수목전지 및 벌채","2025-11-17 09:00","2025-11-18 18:00","2025-11-17 09:00","2025-11-18 18:00","매일"]
[365,"대전세종충남","대전","부여논산#1 T/L","[취소시][가압X]논산S/S 부여-논산#1T/L GIS 보통점검","[취소시][가압X]논산S/S 부여-논산#1T/L GIS 보통점검","2025-11-20 09:00","2025-11-20 18:00","2025-11-20 09:00","2025-11-20 18:00","연속"]
[366,"대전세종충남","대전","부여논산#2 T/L","[취소시][가압X]논산S/S 부여-논산#2T/L GIS 보통점검","[취소시][가압X]논산S/S 부여-논산#2T/L GIS 보통점검","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","연속"]
[367,"대전세종충남","대전","논산은진#1 T/L","[송전][즉시가압O]345kV신옥천-청양등8개TL 추락방지설치공사","[즉시가압O]345kV신옥천-청양등8개TL 추락방지설치공사","2025-11-10 07:00","2025-11-12 18:00","2025-11-10 07:00","2025-11-12 18:00","매일"]
[368,"대전세종충남","대전","팔봉두마#1 T/L","[즉시가압X]두마S/S  팔봉-두마#1T/L GIS 전자변교체","[즉시가압X]두마S/S  팔봉-두마#1T/L GIS 전자변교체","2025-11-03 09:00","2025-11-03 18:00","취소","취소","연속"]
[369,"대전세종충남","대전","팔봉두마#2 T/L","[즉시가압X]두마S/S  팔봉-두마#2T/L GIS 전자변교체","[즉시가압X]두마S/S  팔봉-두마#2T/L GIS 전자변교체","2025-11-04 09:00","2025-11-04 18:00","취소","취소","연속"]
[370,"대전세종충남","대전","신옥천서대전 T/L","[즉시가압O]서대전S/S 신옥천-서대전T/L GIS 보통점검","[즉시가압O]서대전S/S 신옥천-서대전T/L GIS 보통점검","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[371,"대전세종충남","대전","신계룡은진#1 T/L","[송전][즉시가압]345kV신옥천-청양등8개TL 추락방지 설치공사","[즉시가압]345kV신옥천-청양등8개TL 추락방지 설치공사","2025-11-24 07:00","2025-11-28 10:00","2025-11-24 07:00","2025-11-28 10:00","매일"]
[372,"대전세종충남","대전","신계룡은진#2 T/L","[취소시][가압O]신계룡S/S 신계룡-은진#2T/L 보통점검","[취소시][가압O]신계룡S/S 신계룡-은진#2T/L 보통점검","2025-11-13 16:00","2025-11-13 22:00","2025-11-13 16:00","2025-11-13 22:00","연속"]
[373,"대전세종충남","대전","신계룡두마#1 T/L","[취소시][가압X]신계룡S/S 신계룡-두마#1T/L GIS 보통점검","[취소시][가압X]신계룡S/S 신계룡-두마#1T/L GIS 보통점검","2025-11-10 16:00","2025-11-10 22:00","취소","취소","연속"]
[374,"대전세종충남","대전","신계룡두마#2 T/L","[취소시][가압X]신계룡S/S 신계룡-두마#2T/L 보통점검","[취소시][가압X]신계룡S/S 신계룡-두마#2T/L 보통점검","2025-11-11 16:00","2025-11-11 22:00","취소","취소","연속"]
[375,"대전세종충남","대전","신계룡은진#1 T/L","[취소시][가압O]신계룡S/S 신계룡-은진#1T/L 보통점검","[취소시][가압O]신계룡S/S 신계룡-은진#1T/L 보통점검","2025-11-12 16:00","2025-11-12 22:00","2025-11-12 16:00","2025-11-12 22:00","연속"]
[376,"대전세종충남","대전","남대전신흥#3 T/L","[10월취소시]  대한전선제 EBG 가스채취밸브 설치공사","[송전] 보호동관 해체 및 스프링유닛점검, 가스채취밸브 설치","2025-11-10 09:00","2025-11-11 18:00","취소","취소","연속"]
[377,"대전세종충남","대전","신옥천용운#1 T/L"," 신옥천-용운T/L 지장수목전지 및 벌채"," 신옥천-용운T/L 지장수목전지 및 벌채","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","매일"]
[378,"대전세종충남","대전","신옥천용운#2 T/L"," 신옥천-용운T/L 지장수목전지 및 벌채"," 신옥천-용운T/L 지장수목전지 및 벌채","2025-11-28 09:00","2025-11-28 18:00","2025-11-28 09:00","2025-11-28 18:00","매일"]
[379,"대전세종충남","대전","신옥천추부#2 T/L","[즉시가압O] 추부S/S 신옥천-추부#2T/L GIS 차단기 부동작시험","[즉시가압O] 추부S/S 신옥천-추부#2T/L GIS 차단기 부동작시험","2025-11-05 17:00","2025-11-05 18:00","2025-11-05 17:00","2025-11-05 18:00","연속"]
[380,"대전세종충남","대전","신옥천추부#1 T/L","[즉시가압O] 추부S/S 신옥천-추부#1T/L GIS 차단기 부동작시험","[즉시가압O] 추부S/S 신옥천-추부#1T/L GIS 차단기 부동작시험","2025-11-05 16:00","2025-11-05 17:00","2025-11-05 16:00","2025-11-05 17:00","연속"]
[381,"대전세종충남","서산","신당진당진#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(10월취소시) (즉시가압가능) 신당진S/S 신당진당진#2T/L GIS 보통점검","2025-11-10 09:30","2025-11-10 18:00","2025-11-10 09:30","2025-11-10 18:00","연속"]
[382,"대전세종충남","서산","대산석문#2 T/L"," 대산-석문#2T/L 피뢰기 설치공사"," 대산-석문#2T/L 피뢰기 설치공사 No.1~48(39기) *즉시가압가능(20분이내)","2025-11-08 08:00","2025-11-09 18:00","취소","취소","매일"]
[383,"대전세종충남","서산","서산대산 T/L"," 신성연-태안T/L 계통변경 외 1개 T/L 건설공사"," 대산T/L No.14(신설) 조립 및 본선로 구성","2025-11-03 07:00","2025-11-07 18:00","2025-11-03 07:00","2025-11-07 18:00","연속"]
[384,"대전세종충남","서산","서산태안#2 T/L"," 신성연-태안T/L 계통변경 외 1개 T/L 건설공사"," 대산T/L No.14(신설) 조립 및 본선로 구성(임시 직결)시 작업공간 간섭에 따른 4회선 병가철탑 안전 확보","2025-11-03 09:00","2025-11-07 16:00","2025-11-03 09:00","2025-11-07 16:00","매일"]
[385,"대전세종충남","서산","서산태안#1 T/L"," 신성연-태안T/L 계통변경 외 1개 T/L 건설공사"," 대산T/L No.14(신설) 조립 및 본선로 구성(임시 직결)시 작업공간 간섭에 따른 4회선 병가철탑 안전 확보","2025-11-07 16:00","2025-11-07 18:00","2025-11-07 16:00","2025-11-07 18:00","연속"]
[386,"대전세종충남","서산","서산태안#2 T/L"," 신성연-태안T/L 계통변경 외 1개 T/L 건설공사"," 대산T/L No.14(신설) 조립 및 본선로 구성(임시 직결)시 작업공간 간섭에 따른 4회선 병가철탑 안전 확보","2025-11-10 07:00","2025-11-14 18:00","2025-11-10 07:00","2025-11-14 18:00","매일"]
[387,"대전세종충남","서산","서산성연 T/L"," 신성연-태안T/L 계통변경 외 1개 T/L 건설공사"," 대산T/L 본선로 (신설No.14) 구성 (임시직결)","2025-11-10 09:00","2025-11-14 18:00","2025-11-10 09:00","2025-11-14 18:00","연속"]
[388,"대전세종충남","서산","신당진서산#1 T/L","24-25년 서산P/O 변전협력회사 총액공사","(10월취소시) (즉시가압가능) 서산S/S 신당진서산#1T/L GIS 보통점검","2025-11-17 09:30","2025-11-17 18:00","2025-11-17 09:30","2025-11-17 18:00","연속"]
[389,"대전세종충남","서산","신당진서산#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(10월취소시) (즉시가압가능) 서산S/S 신당진서산#2T/L CVT 초기점검","2025-11-18 09:30","2025-11-18 18:00","2025-11-18 09:30","2025-11-18 18:00","연속"]
[390,"대전세종충남","서산","서산태안#1 T/L"," 신성연-태안T/L 계통변경 외 1개 T/L 건설공사"," 대산T/L No.14(신설) 조립 및 본선로 구성(임시 직결)시 작업공간 간섭에 따른 4회선 병가철탑 안전 확보","2025-11-03 07:00","2025-11-03 09:00","2025-11-03 07:00","2025-11-03 09:00","연속"]
[391,"대전세종충남","서산","신당진당진#1 T/L","24-25년 서산P/O 변전협력회사 총액공사","(10월취소시) (즉시가압가능) 신당진S/S 신당진당진#1T/L CVT 대체","2025-11-11 09:30","2025-11-11 18:00","2025-11-11 09:30","2025-11-11 18:00","연속"]
[392,"대전세종충남","서산","태안태안화력#1 T/L","24-25년 서산P/O 변전협력회사 총액공사","(10월 휴전 취소시) (즉시가압가능) 태안T/P 태안태안화력#1T/L LA 보통점검","2025-11-17 09:30","2025-11-17 18:00","2025-11-17 09:30","2025-11-17 18:00","연속"]
[393,"대전세종충남","서산","서산태안#1 T/L","태안S/S  차단기 조작시험","(즉시가압 가능)태안S/S 서산-태안 #1 T/L CB(647) 개폐타임 측정 및 조작시험","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","연속"]
[394,"대전세종충남","서산","태안태안화력#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안T/P 태안태안화력#2T/L LA 보통점검","2025-11-18 09:30","2025-11-18 18:00","2025-11-18 09:30","2025-11-18 18:00","연속"]
[395,"대전세종충남","서산","합덕송악#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 합덕-송악#1T/L No.29~51, 98 총 24기) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-11-05 08:00","2025-11-07 18:00","2025-11-05 08:00","2025-11-07 18:00","매일"]
[396,"대전세종충남","세종","신풍공주#1 T/L","(10월 취소시)  신풍-공주T/L 폴리머 점퍼지지애자 설치","(10월 취소시)  신풍-공주T/L 폴리머 점퍼지지애자 설치","2025-11-17 07:00","2025-11-21 18:00","2025-11-17 07:00","2025-11-21 18:00","매일"]
[397,"대전세종충남","세종","신풍공주#2 T/L","(10월 취소시)  신풍-공주T/L 폴리머 점퍼지지애자 설치","(10월 취소시)  신풍-공주T/L 폴리머 점퍼지지애자 설치","2025-11-24 07:00","2025-11-28 18:00","2025-11-24 07:00","2025-11-28 18:00","매일"]
[398,"대전세종충남","세종","덕진공주#2 T/L"," 덕진-공주TL 지장수목 전지 및 벌채"," 덕진-공주TL 지장수목 전지 및 벌채","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","매일"]
[399,"대전세종충남","세종","덕진공주#1 T/L"," 덕진-공주TL 지장수목 전지 및 벌채"," 덕진-공주TL 지장수목 전지 및 벌채","2025-11-13 09:00","2025-11-13 18:00","2025-11-13 09:00","2025-11-13 18:00","매일"]
[400,"대전세종충남","세종","세종둔곡#2 T/L","(10월 취소시)  세종-둔곡#2T/L 추락방지장치 설치공사","(10월 취소시)  세종-둔곡#2T/L 추락방지장치 설치공사","2025-11-17 07:00","2025-11-20 18:00","2025-11-17 07:00","2025-11-20 18:00","매일"]
[401,"대전세종충남","세종","둔곡송강#2 T/L","[변전]25년 세종전력지사 변전협력회사 공사","○  GIS 보통점검 -즉시가압 가능","2025-11-08 09:00","2025-11-08 18:00","2025-11-08 09:00","2025-11-08 18:00","연속"]
[402,"대전세종충남","세종","둔곡송강#1 T/L","[변전]25년 세종전력지사 변전협력회사 공사","○  GIS 보통점검 -즉시가압 가능","2025-11-06 09:00","2025-11-06 18:00","2025-11-10 09:00","2025-11-10 18:00","연속"]
[403,"대전세종충남","세종","부강대청HP T/L","(10월 취소시)  세종-부강T/L 불량애자 교체공사"," 세종-부강T/L 불량애자 교체공사를 위한 안전목적상 휴전","2025-11-03 07:00","2025-11-03 18:00","2025-11-03 07:00","2025-11-03 18:00","연속"]
[404,"대전세종충남","세종","세종부강#1 T/L","(10월 취소시)  세종-부강T/L 불량애자 교체공사"," 세종-부강T/L 불량애자 교체공사","2025-11-03 07:00","2025-11-03 18:00","2025-11-03 07:00","2025-11-03 18:00","연속"]
[405,"대전세종충남","세종","세종부강#2 T/L","(10월 취소시)  세종-부강T/L 불량애자 교체공사"," 세종-부강T/L 불량애자 교체공사","2025-11-04 07:00","2025-11-05 18:00","2025-11-04 07:00","2025-11-05 18:00","매일"]
[406,"대전세종충남","세종","부강신탄진 T/L","(10월 취소시)  부강-신탄진T/L 추락방지장치 설치공사","(10월 취소시)  부강-신탄진T/L 추락방지장치 설치공사","2025-11-14 07:00","2025-11-14 18:00","2025-11-14 07:00","2025-11-14 18:00","연속"]
[407,"대전세종충남","세종","세종월산#2 T/L","(10월 취소시)  세종-월산T/L 불량애자 교체공사","(10월 취소시)  세종-월산T/L 불량애자 교체공사","2025-11-10 07:00","2025-11-11 18:00","2025-11-10 07:00","2025-11-11 18:00","매일"]
[408,"대전세종충남","세종","세종월산#1 T/L","(10월 취소시)  세종-월산T/L 불량애자 교체공사","(10월 취소시)  세종-월산T/L 불량애자 교체공사","2025-11-06 07:00","2025-11-07 18:00","2025-11-06 07:00","2025-11-07 18:00","매일"]
[409,"대전세종충남","세종","월산서세종 T/L","[변전]25년 세종전력지사 변전협력회사 공사","[즉시가압○] 차단기 조작시험 - 전자변 교체 병행","2025-11-05 09:00","2025-11-05 12:00","2025-11-05 09:00","2025-11-05 12:00","연속"]
[410,"대전세종충남","직할","신탄진대청HP T/L","24-25년도 직할 변전협력회사 총액공사","○ 신탄진-대청H/P T/L GIS 초기점검","2025-11-21 09:00","2025-11-21 18:00","2025-11-21 09:00","2025-11-21 18:00","연속"]
[411,"대전세종충남","직할","동대전신탄진#1 T/L","24-25년도 직할 변전협력회사 총액공사","○ 동대전-신탄진#1 T/L GIS 초기점검","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[412,"대전세종충남","직할","부강신탄진 T/L","24-25년도 직할 변전협력회사 총액공사","○ 부강-신탄진T/L GIS 초기점검","2025-11-11 09:00","2025-11-11 18:00","2025-11-11 09:00","2025-11-11 18:00","연속"]
[413,"대전세종충남","직할","동대전신탄진#2 T/L","24-25년도 직할 변전협력회사 총액공사","○ 동대전-신탄진#2 T/L GIS 초기점검","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[414,"대전세종충남","천안","신온양석곡#1 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능)석곡S/S  신온양-석곡#1T/L GIS 보통점검","2025-11-04 09:00","2025-11-04 18:00","취소","취소","연속"]
[415,"대전세종충남","천안","신온양석곡#2 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능)석곡S/S  신온양-석곡#2T/L GIS 보통점검","2025-11-05 09:00","2025-11-05 18:00","취소","취소","연속"]
[416,"대전세종충남","천안","아산예산#1 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능)아산S/S  아산-예산#1T/L GIS 보통점검","2025-11-17 09:00","2025-11-17 18:00","취소","취소","연속"]
[417,"대전세종충남","천안","온양풍세#1 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능)온양,풍세S/S  온양-풍세#1T/L GIS 보통점검","2025-11-20 09:00","2025-11-21 18:00","2025-11-20 09:00","2025-11-21 18:00","매일"]
[418,"대전세종충남","천안","아산온양#1 T/L","(10월 취소시)온양S/S  아산-온양#1T/L 하자점검","(10월 취소시)(즉시가압가능)온양S/S  아산-온양#1T/L 하자점검","2025-11-08 09:00","2025-11-08 18:00","2025-11-08 09:00","2025-11-08 18:00","연속"]
[419,"대전세종충남","천안","아산온양#2 T/L","(10월 취소시)온양S/S  아산-온양#2T/L 하자점검","(10월 취소시)온양S/S  아산-온양#2T/L 하자점검","2025-11-09 09:00","2025-11-09 18:00","2025-11-09 09:00","2025-11-09 18:00","연속"]
[420,"대전세종충남","천안","온양풍세#1 T/L","온양S/S  장기사용 #1M.Tr 교체공사","#1M.Tr 1차 모선 교체 관련 안전이격 확보","2025-11-27 09:00","2025-11-27 14:00","2025-11-27 09:00","2025-11-27 14:00","연속"]
[421,"대전세종충남","천안","서천안탕정#2 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능)탕정S/S  서천안-탕정#2T/L GIS 보통점검","2025-11-19 09:00","2025-11-19 18:00","2025-11-19 09:00","2025-11-19 18:00","연속"]
[422,"대전세종충남","청양","관창보령CC T/L","[송전][즉시가압O] 장기사용 송전전선 건정성 점검","옥산-서천#2 등 6개T/L","2025-11-14 08:00","2025-11-14 18:00","취소","취소","매일"]
[423,"대전세종충남","청양","관창대천#2 T/L","['25년 청양P/O 170kV GIS 정밀점검 공사]","관창S/S 관창-대천#2T/L GIS 정밀점검","2025-11-03 09:00","2025-11-05 18:00","2025-11-03 09:00","2025-11-05 18:00","연속"]
[424,"대전세종충남","청양","보령TP보령CC T/L","[송전][즉시가압O] 장기사용 송전전선 건정성 점검","옥산-서천#2 등 6개T/L","2025-11-17 08:00","2025-11-17 18:00","취소","취소","매일"]
[425,"대전세종충남","청양","관창보령TP T/L","[송전][즉시가압O] 장기사용 송전전선 건정성 점검","옥산-서천#2 등 6개T/L","2025-11-13 08:00","2025-11-13 18:00","취소","취소","매일"]
[426,"대전세종충남","청양","신서천대천#1 T/L","[송전][즉시가압O] 장기사용 송전전선 건정성 점검[안전이격]","옥산-서천#1T/L 하단 [안전이격]","2025-11-10 08:00","2025-11-10 18:00","취소","취소","매일"]
[427,"대전세종충남","청양","신서천대천#2 T/L","[송전][즉시가압O] 장기사용 송전전선 건정성 점검[안전이격]","옥산-서천#2T/L 하단 [안전이격]","2025-11-11 08:00","2025-11-11 18:00","취소","취소","매일"]
[428,"대전세종충남","청양","청양신풍#1 T/L"," 청양-신풍T/L 폴리머 점퍼지지애자 설치"," 청양-신풍T/L 폴리머 점퍼지지애자 설치","2025-11-17 07:00","2025-11-18 18:00","2025-11-17 07:00","2025-11-18 18:00","매일"]
[429,"대전세종충남","청양","옥산장항#1 T/L","[송전][주말작업X] 옥산-장항#1T/L 수평추락방지장치 설치","우상단 : 옥산-장항#1 우하단 : 동군산-장항#2 병가구간 수평추락방지장치 설치","2025-11-10 07:30","2025-11-11 18:00","취소","취소","매일"]
[430,"대전세종충남","청양","옥산장항#2 T/L","['25년 청양P/O 170kV GIS 정밀점검 공사]","옥산S/S 옥산-장항#2T/L GIS 정밀점검","2025-11-17 09:00","2025-11-19 18:00","2025-11-17 09:00","2025-11-19 18:00","연속"]
[431,"대전세종충남","청양","신서천옥산#2 T/L","['25년 청양P/O 170kV GIS 정밀점검 공사]","옥산S/S 옥산-서천#2T/L GIS 정밀점검","2025-11-10 09:00","2025-11-12 18:00","2025-11-10 09:00","2025-11-12 18:00","연속"]
[432,"대전세종충남","청양","신서천옥산#2 T/L","[송전][즉시가압O] 장기사용 송전전선 건정성 점검","옥산-서천#2 등 6개T/L","2025-11-11 08:00","2025-11-11 18:00","취소","취소","매일"]
[433,"대전세종충남","청양","옥산장항#2 T/L","[송전][주말작업X] 옥산-장항#2T/L 수평추락방지장치 설치","우상단 : 옥산-장항#2 우하단 : 동군산-장항#1 병가구간 수평추락방지장치 설치","2025-11-12 07:30","2025-11-13 18:00","취소","취소","매일"]
[434,"대전세종충남","청양","신서천옥산#1 T/L","[송전][즉시가압O] 장기사용 송전전선 건정성 점검","옥산-서천#2 등 6개T/L","2025-11-10 08:00","2025-11-10 18:00","취소","취소","매일"]
[435,"대전세종충남","청양","동군산장항#1 T/L","[송전][주말작업X] 동군산-장항#1T/L 수평추락방지장치 설치","우상단 : 옥산-장항#2 우하단 : 동군산-장항#1 병가구간 수평추락방지장치 설치","2025-11-12 07:30","2025-11-13 18:00","취소","취소","매일"]
[436,"대전세종충남","청양","동군산장항#2 T/L","[송전][주말작업X] 동군산-장항#2T/L 수평추락방지장치 설치","우상단 : 옥산-장항#1 우하단 : 동군산-장항#2 병가구간 수평추락방지장치 설치","2025-11-10 07:30","2025-11-11 18:00","취소","취소","매일"]
[437,"대전세종충남","청양","청양S/S CB 6100","[10월취소시][변전총액] 청양P/O 변전협력 총액공사","청양SS  #60-#65모선보호반 교체공사","2025-11-24 09:00","2025-11-28 18:00","취소","취소","연속"]
[438,"대전세종충남","청양","청양S/S SEC CB 60610","[10월취소시][변전총액] 청양P/O 변전협력 총액공사","청양SS  #60-#65모선보호반 교체공사","2025-11-24 09:00","2025-11-28 18:00","취소","취소","연속"]
[439,"대전세종충남","청양","청양S/S SEC CB 65660","[10월취소시][변전총액] 청양P/O 변전협력 총액공사","청양SS  #60-#65모선보호반 교체공사","2025-11-24 09:00","2025-11-28 18:00","취소","취소","연속"]
[440,"대전세종충남","청양","청양S/S SEC CB 60610","[10월취소시][변전총액] 청양P/O 변전협력 총액공사","청양SS  #61-#66모선보호반 교체공사","2025-11-17 09:00","2025-11-21 18:00","취소","취소","연속"]
[441,"대전세종충남","청양","청양S/S SEC CB 65660","[10월취소시][변전총액] 청양P/O 변전협력 총액공사","청양SS  #61-#66모선보호반 교체공사","2025-11-17 09:00","2025-11-21 18:00","취소","취소","연속"]
[442,"대전세종충남","청양","청양S/S CB 6200","[10월취소시][변전총액] 청양P/O 변전협력 총액공사","청양SS  #61-#66모선보호반 교체공사","2025-11-17 09:00","2025-11-21 18:00","취소","취소","연속"]
[443,"전북","군산","군산C/C CB 6100","군산P/O 노후배전반 대체공사","-모선보호반 대체","2025-11-04 09:00","2025-11-07 18:00","2025-11-04 09:00","2025-11-07 18:00","연속"]
[444,"전북","군산","동군산군산CC#2 T/L","군산P/O 노후배전반 대체공사","-동군산-군산CC#2T/L 송전선로보호반 대체","2025-11-12 09:00","2025-11-14 18:00","2025-11-12 09:00","2025-11-14 18:00","연속"]
[445,"전북","군산","동군산군산CC#1 T/L","군산P/O 노후배전반 대체공사","-동군산-군산CC#1T/L 송전선로보호반 대체","2025-11-17 09:00","2025-11-19 18:00","2025-11-17 09:00","2025-11-19 18:00","연속"]
[446,"전북","군산","군산이리#2 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-11-17 07:00","2025-11-21 18:00","취소","취소","연속"]
[447,"전북","군산","군산영등#2 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-11-17 07:00","2025-11-23 18:00","취소","취소","연속"]
[448,"전북","군산","군산이리#1 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-11-22 07:00","2025-11-23 18:00","취소","취소","연속"]
[449,"전북","군산","군산이리#1 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#1 동시휴전 필요)"," 군산-영등T/L 스페이서 보수공사 ※  군산-영등, 군산-이리T/L 4회선 구간으로 동시휴전 필요","2025-11-03 07:00","2025-11-03 18:00","취소","취소","연속"]
[450,"전북","군산","군산이리#2 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#2 동시휴전 필요)"," 군산-영등T/L 스페이서 보수공사 ※  군산-영등, 군산-이리T/L 4회선 구간으로 동시휴전 필요","2025-11-04 07:00","2025-11-04 18:00","취소","취소","연속"]
[451,"전북","군산","군산서군산#1 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-11-10 09:00","2025-11-11 18:00","취소","취소","연속"]
[452,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-11-12 09:00","2025-11-13 18:00","취소","취소","연속"]
[453,"전북","군산","군산S/S SEC CB 61620","군산P/O 이상 차단기 조작시험","군산P/O 이상 차단기 조작시험","2025-11-10 09:00","2025-11-10 14:00","2025-11-10 09:00","2025-11-10 14:00","연속"]
[454,"전북","군산","군산S/S SEC CB 66670","군산P/O 이상 차단기 조작시험","군산P/O 이상 차단기 조작시험","2025-11-10 14:00","2025-11-10 18:00","2025-11-10 14:00","2025-11-10 18:00","연속"]
[455,"전북","군산","내초SE열병합#1 T/L","군산P/O 이상 차단기 점검공사","군산P/O 이상 차단기 점검공사","2025-11-18 09:00","2025-11-18 18:00","2025-11-18 09:00","2025-11-18 18:00","연속"]
[456,"전북","군산","내초군장#2 T/L","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","170kV GIS 정밀점검공사(무부하가압용)","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[457,"전북","군산","내초군장#2 T/L","군산P/O 170kV GIS 정밀점검공사(무부하가압용)","170kV GIS 정밀점검공사(무부하가압용)","2025-11-19 09:00","2025-11-19 18:00","2025-11-19 09:00","2025-11-19 18:00","연속"]
[458,"전북","군산","군산동군산#1 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-11-05 09:00","2025-11-06 18:00","취소","취소","연속"]
[459,"전북","군산","동군산군산CC#3 T/L","군산P/O 이상 차단기 점검공사(중복)","군산P/O 이상 차단기 점검공사(중복)","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[460,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사(중복)","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2025-11-25 09:00","2025-11-27 18:00","취소","취소","연속"]
[461,"전북","군산","동군산장항#2 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-11-03 09:00","2025-11-04 18:00","취소","취소","연속"]
[462,"전북","군산","동군산군산CC#1 T/L","동군산S/S #4M.Tr 증설 관련 앵글측정 및 무부하가압","동군산S/S  #4M.Tr 증설공사 -  M.Tr 1Bank 설치","2025-11-20 09:00","2025-11-21 18:00","2025-11-20 09:00","2025-11-21 18:00","연속"]
[463,"전북","군산","군산동군산#2 T/L","#4M.Tr 증설관련 개폐장치 설치(154) 이격확보","#4M.Tr 증설관련 개폐장치 설치공사 -  GIS, M.Tr간 모선 연결","2025-11-12 09:00","2025-11-13 18:00","2025-11-12 09:00","2025-11-13 18:00","연속"]
[464,"전북","군산","군산동군산#2 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-11-10 09:00","2025-11-11 18:00","취소","취소","연속"]
[465,"전북","군산","군산영등#2 T/L","'25년 군산전력지사 가공송전협력회사공사(영등-낭산#1 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-11-06 07:00","2025-11-06 18:00","취소","취소","연속"]
[466,"전북","군산","군산영등#1 T/L","'25년 군산전력지사 가공송전협력회사공사(영등-낭산#2 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 및 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-11-05 07:00","2025-11-05 18:00","취소","취소","연속"]
[467,"전북","군산","영등낭산#2 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#1 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-11-05 07:00","2025-11-05 18:00","취소","취소","연속"]
[468,"전북","군산","군산영등#2 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-이리#2 동시휴전 필요)"," 군산-영등T/L 스페이서 보수공사 ※  군산-영등, 군산-이리T/L 4회선 구간으로 동시휴전 필요","2025-11-04 07:00","2025-11-04 18:00","취소","취소","연속"]
[469,"전북","군산","군산영등#1 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-이리#1 동시휴전 필요)"," 군산-영등T/L 스페이서 보수공사 ※  군산-영등, 군산-이리T/L 4회선 구간으로 동시휴전 필요","2025-11-03 07:00","2025-11-03 18:00","취소","취소","연속"]
[470,"전북","군산","영등팔봉#2 T/L","군산P/O 이상 차단기 보통점검","영등S/S  영등-팔봉#2T/L 차단기 보통점검","2025-11-28 09:00","2025-11-28 18:00","2025-11-28 09:00","2025-11-28 18:00","연속"]
[471,"전북","군산","영등팔봉#1 T/L","군산P/O 이상 차단기 보통점검","영등S/S  영등-팔봉#1T/L 차단기 보통점검","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[472,"전북","군산","영등낭산#1 T/L","'25년 군산전력지사 가공송전협력회사공사(군산-영등#2 동시휴전 필요)"," 군산-영등T/L 소도체 이도조정공사 ※ 영등-낭산T/L, 군산-영등T/L 4회선 구간으로 동시휴전 필요","2025-11-06 07:00","2025-11-06 18:00","취소","취소","연속"]
[473,"전북","군산","이리백산#1 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","170kV GIS 정밀점검공사(중복)","2025-11-20 09:00","2025-11-21 18:00","취소","취소","연속"]
[474,"전북","군산","군산이리#2 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","170kV GIS 정밀점검공사(중복)","2025-11-26 09:00","2025-11-27 18:00","취소","취소","연속"]
[475,"전북","군산","이리백산#2 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","170kV GIS 정밀점검공사(중복)","2025-11-24 09:00","2025-11-25 18:00","취소","취소","연속"]
[476,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS X 3CCT 교체","2025-11-02 09:00","2025-11-03 18:00","2025-11-02 09:00","2025-11-03 18:00","연속"]
[477,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS X 3CCT 교체","2025-11-03 09:00","2025-11-04 18:00","2025-11-03 09:00","2025-11-04 18:00","연속"]
[478,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS X 3CCT 교체","2025-11-06 09:00","2025-11-07 18:00","2025-11-06 09:00","2025-11-07 18:00","연속"]
[479,"전북","군산","팔봉왕궁#1 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-11-17 09:00","2025-11-18 18:00","취소","취소","연속"]
[480,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS X 3CCT 교체","2025-11-07 09:00","2025-11-08 18:00","2025-11-07 09:00","2025-11-08 18:00","연속"]
[481,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS X 3CCT 교체","2025-11-11 09:00","2025-11-12 18:00","2025-11-11 09:00","2025-11-12 18:00","연속"]
[482,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS X 3CCT 교체","2025-11-14 09:00","2025-11-15 18:00","2025-11-14 09:00","2025-11-15 18:00","연속"]
[483,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS T/R x 2CCT, T/L x 1CCT 교체","2025-11-17 17:00","2025-11-17 18:00","2025-11-17 17:00","2025-11-17 18:00","연속"]
[484,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS X 3CCT 교체","2025-11-18 17:00","2025-11-18 18:00","2025-11-18 17:00","2025-11-18 18:00","연속"]
[485,"전북","군산","팔봉왕궁#2 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-11-19 09:00","2025-11-20 18:00","취소","취소","연속"]
[486,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS X 3CCT 교체","2025-11-27 11:00","2025-11-27 13:00","2025-11-27 11:00","2025-11-27 13:00","연속"]
[487,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS X 3CCT 교체","2025-11-28 14:00","2025-11-28 16:00","2025-11-28 14:00","2025-11-28 16:00","연속"]
[488,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사"," GIS T/R x 2CCT, T/L x 1CCT 교체","2025-11-28 16:00","2025-11-28 17:00","2025-11-28 16:00","2025-11-28 17:00","연속"]
[489,"전북","군산","은진함열#1 T/L","'25년 가공송전 순시점검 위탁공사"," 은진-함열T/L 14기 조류착지방지장치 설치","2025-11-24 07:00","2025-11-25 18:00","2025-11-24 07:00","2025-11-25 18:00","연속"]
[490,"전북","군산","은진함열#2 T/L","'25년 가공송전 순시점검 위탁공사"," 은진-함열T/L 14기 조류착지방지장치 설치","2025-11-26 07:00","2025-11-27 18:00","2025-11-26 07:00","2025-11-27 18:00","연속"]
[491,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #2T/L 긴선(케이블타워) 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-11-23 07:00","2025-11-26 18:00","취소","취소","연속"]
[492,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #2T/L 전선이동 (가선로 → 본선로) 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-11-10 07:00","2025-11-13 18:00","취소","취소","연속"]
[493,"전북","직할","동전주북전주#1 T/L","전주전철#2T/L GIS 정밀점검 무부하가압","전주전철#2T/L GIS 정밀점검 무부하가압","2025-11-20 15:00","2025-11-20 16:00","2025-11-20 15:00","2025-11-20 16:00","연속"]
[494,"전북","직할","동전주북전주#1 T/L","전주전철#2T/L GIS 정밀점검 무부하가압","전주전철#2T/L GIS 정밀점검 무부하가압","2025-11-18 15:00","2025-11-18 16:00","2025-11-18 15:00","2025-11-18 16:00","연속"]
[495,"전북","직할","동전주북전주#1 T/L","전주전철#1T/L GIS 정밀점검 무부하가압","전주전철#1T/L GIS 정밀점검 무부하가압","2025-11-14 15:00","2025-11-14 16:00","2025-11-14 15:00","2025-11-14 16:00","연속"]
[496,"전북","직할","동전주북전주#1 T/L","전주전철#1T/L GIS 정밀점검 무부하가압","전주전철#1T/L GIS 정밀점검 무부하가압","2025-11-12 15:00","2025-11-12 16:00","2025-11-12 15:00","2025-11-12 16:00","연속"]
[497,"전북","직할","북전주S/S CB 6100","북전주S/S 장기사용 모선 보호반 대체 공사","- 북전주S/S 모선보호반 대체","2025-11-03 09:00","2025-11-07 18:00","2025-11-03 09:00","2025-11-07 18:00","연속"]
[498,"전북","직할","전주서곡#1 T/L","전주S/S 6333 GIS 정밀점검관련 무부하가압","전주S/S 6333 GIS 정밀점검관련 무부하가압","2025-11-07 15:00","2025-11-07 16:00","2025-11-07 15:00","2025-11-07 16:00","연속"]
[499,"전북","직할","전주서곡#1 T/L","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","2025-11-20 15:00","2025-11-20 16:00","2025-11-20 15:00","2025-11-20 16:00","연속"]
[500,"전북","직할","전주서곡#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-11-05 08:00","2025-11-06 18:00","2025-11-05 08:00","2025-11-06 18:00","매일"]
[501,"전북","직할","전주서곡#1 T/L","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","전주S/S 6100 TIE GIS 정밀점검관련 무부하가압","2025-11-18 15:00","2025-11-18 16:00","2025-11-18 15:00","2025-11-18 16:00","연속"]
[502,"전북","직할","전주서곡#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-11-03 08:00","2025-11-04 18:00","2025-11-03 08:00","2025-11-04 18:00","매일"]
[503,"전북","직할","전주서곡#1 T/L","전주S/S 6333 GIS 정밀점검관련 무부하가압","전주S/S 6333 GIS 정밀점검관련 무부하가압","2025-11-05 15:00","2025-11-05 16:00","2025-11-05 15:00","2025-11-05 16:00","연속"]
[504,"전북","직할","진안장수#2 T/L","345kV 신옥천-신남원 등 3개T/L 수평 추락방지시설 설치공사(계속)","345kV 신옥천-신남원#2T/L 1~178호 = 신옥천-신남원#2T/L No.73, 진안-장수#1,2T/L No.46 병가구간 작업자 안전확보차 휴전","2025-11-20 07:30","2025-11-21 17:00","취소","취소","매일"]
[505,"전북","직할","진안장수#1 T/L","345kV 신옥천-신남원 등 3개T/L 수평 추락방지시설 설치공사(계속)","345kV 신옥천-신남원#1T/L 1~178호 = 신옥천-신남원#1T/L No.73, 진안-장수#1,2T/L No.46 병가구간 작업자 안전확보차 휴전","2025-11-06 07:30","2025-11-07 17:00","취소","취소","매일"]
[506,"전북","직할","동전주태평#1 T/L","[3차수]태평S/S  장기사용 GIS 교체공사","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-11-05 09:00","2025-12-05 18:00","2025-11-05 09:00","2025-12-05 18:00","연속"]
[507,"전북","직할","서곡태평#1 T/L","[3차수]태평S/S  장기사용 GIS 교체공사(무부하, 2H)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-11-08 15:00","2025-11-08 17:00","2025-11-08 15:00","2025-11-08 17:00","연속"]
[508,"전북","직할","서곡태평#1 T/L","[3차수]태평S/S  장기사용 GIS 교체공사 (무부하)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-11-21 09:00","2025-11-21 10:00","2025-11-21 09:00","2025-11-21 10:00","연속"]
[509,"전북","직할","서곡태평#1 T/L","[3차수]태평S/S  장기사용 GIS 교체공사(무부하, 1H)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-11-11 09:00","2025-11-11 10:00","2025-11-11 09:00","2025-11-11 10:00","연속"]
[510,"전북","직할","서곡태평#1 T/L","[4차수]태평S/S  장기사용 GIS 교체공사(무부하)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-11-18 18:00","2025-11-19 18:00","2025-11-18 18:00","2025-11-19 18:00","연속"]
[511,"전북","김제","백산김제#1 T/L","백산김제#1 T/L"," '25년 가공송전 순시점검 위탁공사","2025-11-25 09:00","2025-11-26 18:00","취소","취소","매일"]
[512,"전북","김제","김제칠보HP T/L"," '25년 가공송전 순시점검 위탁공사"," '25년 가공송전 순시점검 위탁공사","2025-11-26 09:00","2025-11-26 18:00","취소","취소","연속"]
[513,"전북","김제","정주동부안#1 T/L"," 정주S/S 정주-동부안#1T/L GIS 정밀점검(연속)"," 정주S/S 정주-동부안#1T/L GIS 정밀점검(연속)","2025-11-26 09:00","2025-11-27 18:00","취소","취소","연속"]
[514,"전북","김제","담양김제 T/L"," '25년 가공송전 순시점검 위탁공사"," '25년 가공송전 순시점검 위탁공사","2025-11-27 09:00","2025-11-27 18:00","취소","취소","연속"]
[515,"전북","김제","백산김제#2 T/L","백산김제#2 T/L"," '25년 가공송전 순시점검 위탁공사","2025-11-27 09:00","2025-11-28 18:00","취소","취소","매일"]
[516,"전북","김제","정주소성#1 T/L"," 소성S/S 170kV GIS 보통점검공사"," 소성S/S 170kV GIS 보통점검공사","2025-11-27 09:00","2025-11-27 18:00","2025-11-27 09:00","2025-11-27 18:00","연속"]
[517,"전북","김제","정주소성#2 T/L"," 소성S/S 170kV GIS 보통점검공사"," 소성S/S 170kV GIS 보통점검공사","2025-11-28 09:00","2025-11-28 18:00","2025-11-28 09:00","2025-11-28 18:00","연속"]
[518,"광주전남","강진","금정강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","①  금정-강진#1T/L 피뢰기 설치 (16~21, 50, 51호) ② 강진-장흥#2T/L 피뢰기 설치 시 4회선 병행휴전","2025-11-10 07:00","2025-11-11 18:00","취소","취소","매일"]
[519,"광주전남","강진","강진장흥#2 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 강진-장흥#2T/L 피뢰기 및 추락방지장치 설치 (1~59호) - 4회선 구간 안전이격휴전 병행 (금정-강진#1, 장흥-벌교)","2025-11-10 07:00","2025-11-14 18:00","취소","취소","매일"]
[520,"광주전남","강진","강진장흥#2 T/L"," 금정-강진T/L OPGW 불량구간 교체공사","금정-강진T/L OPGW 불량구간 교체(강진-장흥 병가구간 포함)","2025-11-24 01:00","2025-11-30 11:00","취소","취소","연속"]
[521,"광주전남","강진","금정강진#1 T/L"," 금정-강진T/L OPGW 불량구간 교체공사","금정-강진T/L OPGW 불량구간 교체(강진-장흥 병가구간 포함)","2025-11-24 07:00","2025-11-30 18:00","취소","취소","매일"]
[522,"광주전남","강진","신강진강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 신강진-강진#2T/L 피뢰기 설치 - 강진-남창#1T/L 4회선 구간 안전이격휴전 병행","2025-11-25 07:00","2025-11-25 18:00","취소","취소","연속"]
[523,"광주전남","강진","강진남창#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 신강진-강진#2T/L 피뢰기 설치 - 강진-남창#1T/L 4회선 구간 안전이격휴전 병행","2025-11-25 07:00","2025-11-25 18:00","취소","취소","연속"]
[524,"광주전남","강진","나주영암#2 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","①  나주-영암#2T/L 피뢰기 및 추락방지장치 설치 (1~81호) ② 4회선 구간 작업 시 병가선로 휴전 병행(나주-금천#1, 영암-금정#1T/L)","2025-11-27 07:00","2025-12-08 18:00","2025-11-27 07:00","2025-12-08 18:00","매일"]
[525,"광주전남","강진","나주금천#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 나주-영암#2T/L 작업 시 4회선 구간 안전이격 휴전","2025-11-27 07:00","2025-11-27 18:00","취소","취소","연속"]
[526,"광주전남","강진","남창완도 T/L","'24~25년 강진전력지사 변전협력회사 공사","- 170kV GIS 보통점검","2025-11-04 10:00","2025-11-04 14:00","2025-11-04 10:00","2025-11-04 14:00","연속"]
[527,"광주전남","강진","남창해남CS#1 T/L","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-11-26 07:00","2025-11-30 15:00","취소","취소","연속"]
[528,"광주전남","강진","남창해남CS#2 T/L","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-11-24 09:00","2025-11-26 15:00","취소","취소","연속"]
[529,"광주전남","강진","남창 모선연계T/L CB","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-11-26 07:00","2025-11-30 15:00","취소","취소","연속"]
[530,"광주전남","강진","신강진대불#1 T/L","신강진-대불#1T/L 피뢰기 절연열화측정","신강진-대불#1T/L 피뢰기 절연열화측정","2025-11-05 09:00","2025-11-05 18:00","취소","취소","연속"]
[531,"광주전남","강진","대불남악#2 T/L","2024~2025년 강진전력지사 변전협력회사 공사","대불S/S 대불-남악#2T/L LA A,B,C 보통점검","2025-11-03 13:00","2025-11-03 17:00","취소","취소","연속"]
[532,"광주전남","강진","대불남악#1 T/L","2024~2025년 강진전력지사 변전협력회사 공사","대불S/S 대불-남악#1T/L CVT 보통점검","2025-11-03 09:00","2025-11-03 13:00","취소","취소","연속"]
[533,"광주전남","강진","장흥보성 T/L","'24~25년 강진전력지사 변전협력회사 공사","- 170kV GIS 공기배출밸브 개선","2025-11-03 10:00","2025-11-03 14:00","2025-11-03 16:00","2025-11-03 20:00","연속"]
[534,"광주전남","강진","보성벌교 T/L"," 보성-벌교T/L 안전이격확보 휴전","ㅇ 대상선로 :  보성-벌교T/L 1~2호 ㅇ 공사내용 : 송전선로 직하 보성군 생활폐기물 소각시설 설치사업 관련으로 시스템비계 설치 및 크레인 사용을 위한 안전이격확보 휴전","2025-11-17 07:00","2025-11-21 18:00","2025-11-17 07:00","2025-11-21 11:00","매일"]
[535,"광주전남","강진","보성벌교 T/L"," 보성-벌교T/L 안전이격확보 휴전","ㅇ 대상선로 :  보성-벌교T/L 1~2호 ㅇ 공사내용 : 송전선로 직하 보성군 생활폐기물 소각시설 설치사업 관련으로 시스템비계 설치 및 크레인 사용을 위한 안전이격확보 휴전","2025-11-03 07:00","2025-11-07 18:00","2025-11-03 07:00","2025-11-07 11:00","매일"]
[536,"광주전남","강진","신강진대불#2 T/L","2024~2025년 강진전력지사 송전협력회사 공사","신강진-대불#2 가공지선 교체공사","2025-11-27 07:00","2025-11-27 18:00","취소","취소","매일"]
[537,"광주전남","강진","영암금정#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사"," 나주-영암#2T/L 작업 시 4회선 구간 안전이격 휴전","2025-11-28 07:00","2025-12-03 18:00","취소","취소","매일"]
[538,"광주전남","강진","장흥벌교 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","①  장흥-벌교T/L 피뢰기 설치 (1~50, 71~90호) ② 강진-장흥#2 휴전작업 시 안전이격휴전 병행","2025-11-14 07:00","2025-11-24 18:00","취소","취소","매일"]
[539,"광주전남","강진","진도진도CS#2 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검","2025-11-18 14:00","2025-11-18 18:00","2025-11-18 14:00","2025-11-18 18:00","연속"]
[540,"광주전남","강진","진도진도CS#1 T/L","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","- 170kV GIS 보통점검","2025-11-18 10:00","2025-11-18 14:00","2025-11-18 10:00","2025-11-18 14:00","연속"]
[541,"광주전남","강진","해남해남CS#1 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-11-11 16:00","2025-11-11 20:00","2025-11-11 16:00","2025-11-11 20:00","매일"]
[542,"광주전남","강진","해남진도#2 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-11-13 16:00","2025-11-13 20:00","2025-11-13 16:00","2025-11-13 20:00","매일"]
[543,"광주전남","강진","해남해남CS#2 T/L","25년 강진전력지사 효성제 170kV GIS 개선공사","-효성제 170kV GIS 개선공사(2단래치 및 베어링)","2025-11-12 16:00","2025-11-12 20:00","2025-11-12 16:00","2025-11-12 20:00","매일"]
[544,"광주전남","강진","화원안좌#1 T/L","25년 강진전력지사 변전협력회사 공사","- 화원-안좌#1T/L 보호반 대체","2025-11-17 09:00","2025-11-19 18:00","취소","취소","연속"]
[545,"광주전남","강진","화원진도#2 T/L","'24~25년 강진전력지사 변전협력회사 공사","- 170kV GIS 차단기 조작시험","2025-11-05 14:00","2025-11-05 18:00","2025-11-05 20:00","2025-11-06 00:00","연속"]
[546,"광주전남","강진","화원진도#1 T/L","'24~25년 강진전력지사 변전협력회사 공사","- 170kV GIS 차단기 조작시험","2025-11-05 10:00","2025-11-05 14:00","2025-11-05 16:00","2025-11-05 20:00","연속"]
[547,"광주전남","강진","화원안좌#2 T/L","25년 강진전력지사 변전협력회사 공사","- 화원-안좌#1T/L 보호반 대체","2025-11-24 09:00","2025-11-26 18:00","취소","취소","연속"]
[548,"광주전남","광주","계림남광주 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.11.10(월) 08:00 ~ 25.11.13(목) 18:00 4. 작업구간 : 계림-남광주T/L No.28~58 5. 작업내용 : 정밀점검","2025-11-10 08:00","2025-11-13 18:00","2025-11-10 08:00","2025-11-13 18:00","매일"]
[549,"광주전남","광주","계림S/S CB 6100","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-11-10 09:00","2025-11-14 18:00","2025-11-10 09:00","2025-11-14 18:00","연속"]
[550,"광주전남","광주","계림S/S SEC CB 61600","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-11-10 09:00","2025-11-12 18:00","2025-11-10 09:00","2025-11-12 18:00","연속"]
[551,"광주전남","광주","신광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 신광주-계림#1T/L 170kV GIS 조작시험","2025-11-11 10:00","2025-11-11 13:00","2025-11-11 10:00","2025-11-11 13:00","연속"]
[552,"광주전남","광주","신광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 신광주-계림#2T/L 170kV GIS 조작시험","2025-11-11 13:00","2025-11-11 16:00","취소","취소","연속"]
[553,"광주전남","광주","북광주계림#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#1T/L 조작시험","2025-11-12 10:00","2025-11-12 13:00","2025-11-12 10:00","2025-11-12 13:00","연속"]
[554,"광주전남","광주","계림S/S CB 6200","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 6200BUS-TIE 조작시험","2025-11-12 10:00","2025-11-14 16:00","취소","취소","연속"]
[555,"광주전남","광주","북광주계림#2 T/L","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 북광주-계림#2T/L 조작시험","2025-11-12 13:00","2025-11-12 16:00","2025-11-12 13:00","2025-11-12 16:00","연속"]
[556,"광주전남","광주","계림S/S SEC CB 61600","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S #60-61BUS-SEC 조작시험","2025-11-13 10:00","2025-11-13 13:00","2025-11-13 10:00","2025-11-13 13:00","연속"]
[557,"광주전남","광주","계림S/S SEC CB 66650","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S #65-#66 BUS-SEC 조작시험","2025-11-13 13:00","2025-11-13 16:00","2025-11-13 13:00","2025-11-13 16:00","연속"]
[558,"광주전남","광주","계림S/S CB 6200","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 6200BUS-TIE 조작시험","2025-11-14 10:00","2025-11-14 16:00","취소","취소","연속"]
[559,"광주전남","광주","계림소태 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.11.17(월) 08:00 ~ 25.11.19(수) 18:00 4. 작업구간 : 계림-소태T/L No.28~47 5. 작업내용 : 정밀점검","2025-11-17 08:00","2025-11-19 18:00","취소","취소","매일"]
[560,"광주전남","광주","남광주화순#1 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.11.20(목) 08:00 ~ 18:00 4. 작업구간 : 남광주-소태T/L No.48~58(병가선로 : 남광주-화순#1T/L) 5. 작업내용 : 정밀점검","2025-11-20 08:00","2025-11-20 18:00","2025-11-20 08:00","2025-11-20 18:00","연속"]
[561,"광주전남","광주","남광주화순#2 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.11.13(목) 08:00 ~ 18:00 4. 작업구간 : 계림-남광주T/L No.57~58(병가선로 : 남광주-화순#2) 5. 작업내용 : 정밀점검","2025-11-13 08:00","2025-11-13 18:00","2025-11-13 08:00","2025-11-13 18:00","연속"]
[562,"광주전남","광주","남광주소태 T/L","2025년 가공송전 순시점검 위탁공사 (직할)","1. 공사명 : 2025년 가공송전 순시점검 위탁공사 (직할) 2. 시공사 : 한전KPS (시공관리책임자 : 김길창(010-4570-2339)) 3. 작업일정 : 25.11.20(목) 08:00 ~ 18:00 4. 작업구간 : 남광주-소태T/L No.48~58 5. 작업내용 : 정밀점검","2025-11-20 08:00","2025-11-20 18:00","2025-11-20 08:00","2025-11-20 18:00","연속"]
[563,"광주전남","광주","정공담양 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 (병가) - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가)","2025-11-03 07:00","2025-11-07 18:00","취소","취소","매일"]
[564,"광주전남","광주","담양김제 T/L","2024~25년 광주 송전협력회사공사(피뢰기)"," 담양-김제T/L 피뢰기설치공사 33기","2025-11-03 09:00","2025-11-06 18:00","취소","취소","매일"]
[565,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  신광주-장성#2T/L GIS 정밀점검","2025-11-17 09:00","2025-11-19 18:00","취소","취소","연속"]
[566,"광주전남","광주","신광주계림#2 T/L","광주전력지사 변전협력회사 총액공사"," 신광주-계림 #2T/L LA, CVT 보통점검","2025-11-12 09:00","2025-11-12 18:00","취소","취소","연속"]
[567,"광주전남","광주","신광주장성#2 T/L"," 신광주-장성T/L 가공지선교체공사"," 신광주-장성T/L 63~66호 가공지선교체공사","2025-11-10 07:00","2025-11-11 18:00","취소","취소","연속"]
[568,"광주전남","광주","신광주계림#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  신광주-계림#2T/L GIS 보통점검","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[569,"광주전남","광주","신광주S/S CB 6100","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S #1 BUSTIE 보통점검","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[570,"광주전남","광주","신광주장성#2 T/L","신광주-장성#2T/L 피뢰기 절연열화측정","신광주-장성#2T/L 피뢰기 절연열화측정","2025-11-07 09:00","2025-11-07 18:00","취소","취소","연속"]
[571,"광주전남","광주","신화순화순#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 피뢰기 갭혼 교체 -  신화순-화순#1T/L 1~5, 10~57호","2025-11-10 08:00","2025-11-14 18:00","취소","취소","매일"]
[572,"광주전남","광주","신화순화순#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 -  신화순-화순#1T/L 1~5, 10~57호","2025-11-03 08:00","2025-11-07 18:00","취소","취소","매일"]
[573,"광주전남","광주","담양일곡#2 T/L","담양-일곡#2T/L 피뢰기 절연열화측정","담양-일곡#2T/L 피뢰기 절연열화측정","2025-11-06 14:00","2025-11-06 18:00","취소","취소","연속"]
[574,"광주전남","광주","담양일곡#1 T/L","담양-일곡#1T/L 피뢰기 절연열화측정","담양-일곡#1T/L 피뢰기 절연열화측정","2025-11-06 09:00","2025-11-06 14:00","취소","취소","연속"]
[575,"광주전남","광주","담양일곡#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가)","2025-11-03 07:00","2025-11-07 18:00","취소","취소","매일"]
[576,"광주전남","광주","일곡S/S CB 6100","2025년 광주전력지사 170kV GIS 점검공사","2025년 광주전력지사 170kV GIS 점검공사 1. 일곡S/S BUSTIE 정밀점검","2025-11-24 09:00","2025-11-26 18:00","2025-11-24 09:00","2025-11-26 18:00","연속"]
[577,"광주전남","광주","하남장성#1 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치(병가) - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-11-10 07:00","2025-11-11 18:00","취소","취소","매일"]
[578,"광주전남","광주","장성영광#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치 - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-11-10 07:00","2025-11-14 18:00","취소","취소","매일"]
[579,"광주전남","광주","장성영광#1 T/L"," 장성-영광 #1T/L OPGW 불량구간 교체공사","가. 공사구간 :  장성-영광 #1T/L No.157-163호 나. 공사내역 1) 장성-영광 #1T/L No.157-163호 OPGW 1.797km 포설 2) 장성-영광 #1T/L 긴선 철거 및 긴선 7기 3) 접속함체 1식 철거, 2식 시설 및 접속","2025-11-02 09:00","2025-11-08 18:00","취소","취소","연속"]
[580,"광주전남","광주","장성영광#1 T/L","2024~2025년 광주전력지사 변전협력회사 공사","-장성-영광#1T/L 170kV GIS 조작시험","2025-11-17 15:00","2025-11-17 18:00","2025-11-17 15:00","2025-11-17 18:00","연속"]
[581,"광주전남","광주","신광주장성#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 장성S/S  신광주-장성#2T/L GIS보통점검","2025-11-19 09:00","2025-11-19 18:00","취소","취소","연속"]
[582,"광주전남","광주","신화순화순#1 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#1T/L GIS 정밀점검","2025-11-03 09:00","2025-11-05 18:00","취소","취소","연속"]
[583,"광주전남","광주","신화순화순#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#2T/L GIS 정밀점검","2025-11-10 09:00","2025-11-12 18:00","취소","취소","연속"]
[584,"광주전남","목포","남악북항#2 T/L","북항S/S #4M.Tr 증설공사(170kV GIS 증설)","#1BUS 무부하가압용","2025-11-04 13:00","2025-11-05 09:00","2025-11-04 16:00","2025-11-05 09:00","연속"]
[585,"광주전남","목포","남악북항#2 T/L","북항S/S #4M.Tr 증설공사(170kV GIS 증설)","#2BUS 무부하가압용","2025-11-06 13:00","2025-11-07 09:00","2025-11-06 16:00","2025-11-07 09:00","연속"]
[586,"광주전남","목포","남악북항#2 T/L","25년 목포전력지사 변전협력회사 총액공사","gis pt 점검","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 16:00","2025-11-04 09:00","연속"]
[587,"광주전남","목포","화원안좌#1 T/L","2025년 목포전력지사 송전협력회사 공사","고정형폴리머 점퍼지지애자(1~47호) 9기","2025-11-24 10:00","2025-11-26 18:00","취소","취소","매일"]
[588,"광주전남","목포","화원안좌#2 T/L","2025년 목포전력지사 송전협력회사 공사","고정형폴리머 점퍼지지애자(1~47호) 9기","2025-11-27 10:00","2025-11-28 18:00","취소","취소","매일"]
[589,"광주전남","목포","화원안좌#2 T/L","화원-안좌 #2T/L OPGW 신설 공사","가. OPGW 교체구간 : 화원-안좌 T/L No.24-47호 나. 공사내역 1) OPGW 연선 : 2.781km(200SQ, 48C), 6.801km(200SQ, 48C) 2) OPGW 긴선 긴선 철거 : 현수 철탑 14기, 내장 12기 3) 접속함체 교체 : 5개소 4) 항공장애표시구 시설 : 25조 다. 기타 사항","2025-11-12 09:00","2025-11-21 18:00","취소","취소","연속"]
[590,"광주전남","목포","엄다무안햇빛#2 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  엄다-무안햇빛T/L 고정형폴리머 점퍼지지애자 설치 3. 공사구간  엄다-무안햇빛#1 No.4~39(13기)","2025-11-20 07:30","2025-11-21 17:00","취소","취소","매일"]
[591,"광주전남","목포","엄다무안햇빛#1 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  엄다-무안햇빛T/L 고정형폴리머 점퍼지지애자 설치 3. 공사구간  엄다-무안햇빛#1 No.4~39(13기)","2025-11-17 07:30","2025-11-19 17:00","취소","취소","매일"]
[592,"광주전남","목포","엄다목포#2 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치 병가구간 휴전 및  엄다-목포T/L 피뢰기 설치","2025-11-06 08:00","2025-11-14 18:00","취소","취소","매일"]
[593,"광주전남","목포","나주엄다#2 T/L","나주엄다#2T/L 피뢰기 절연열화측정","나주엄다#2T/L 피뢰기 절연열화측정","2025-11-04 14:00","2025-11-04 18:00","취소","취소","연속"]
[594,"광주전남","목포","나주엄다#1 T/L","나주엄다#1T/L 피뢰기 절연열화측정","나주엄다#1T/L 피뢰기 절연열화측정","2025-11-04 09:00","2025-11-04 14:00","취소","취소","연속"]
[595,"광주전남","목포","나주엄다#1 T/L","24~25년 목포전력지사 송전협력회사 공사(피뢰기 설치)"," 나주-엄다T/L 피뢰기 설치(116기)","2025-11-03 08:00","2025-11-07 18:00","취소","취소","매일"]
[596,"광주전남","목포","영광서홍농개폐소 T/L"," 서홍농개폐소 건설공사(낙월해상풍력#1,2T/L 무부하가압)","○ 내용 :  낙월해상풍력#1,2T/L 송전선로 무부하가압, 실부하가압","2025-11-20 15:00","2025-11-21 15:00","취소","취소","연속"]
[597,"광주전남","목포","영광홍농 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  영광-홍농T/L 고정형폴리머점퍼지지애자 설치 3. 공사구간  영광-홍농 No.7~68(17기) ( 장성-영광T/L 병가구간 포함)","2025-11-13 07:30","2025-11-14 17:00","취소","취소","매일"]
[598,"광주전남","목포","영광서홍농개폐소 T/L"," 장성-영광 #1T/L OPGW 불량구간 교체공사","가. 공사구간 :  장성-영광 #1T/L No.157-163호 나. 공사내역 1) 장성-영광 #1T/L No.157-163호 OPGW 1.797km 포설 2) 장성-영광 #1T/L 긴선 철거 및 긴선 7기 3) 접속함체 1식 철거, 2식 시설 및 접속","2025-11-02 09:00","2025-11-08 18:00","취소","취소","연속"]
[599,"광주전남","목포","고창홍농 T/L","24~25년 목포전력지사 송전협력회사 공사","1. 공사명 : 고정형 폴리머 점퍼지지애자 설치 2. 공사내용  고창-홍농T/L 고정형폴리머점퍼지지애자 설치 3. 공사구간  고창-홍농 No.42~66(6기)","2025-11-10 07:30","2025-11-12 17:00","취소","취소","매일"]
[600,"광주전남","순천","광양하동#1 T/L","코타핀 교체(광양-하동#1)","코타핀 교체","2025-11-26 07:00","2025-11-26 12:00","2025-11-26 07:00","2025-11-26 12:00","연속"]
[601,"광주전남","순천","광양하동#2 T/L","코타핀 교체(광양-하동#2)","코타핀 교체","2025-11-26 13:00","2025-11-26 18:00","2025-11-26 13:00","2025-11-26 18:00","연속"]
[602,"광주전남","순천","광양백운#1 T/L","24-25년 순천전력지사 변전협력회사 공사","광양-백운#1T/L 보호배전반 대체","2025-11-03 09:00","2025-11-07 18:00","취소","취소","연속"]
[603,"광주전남","순천","백운황금#1 T/L"," 광양항분기 지중T/L 건설공사"," XLPE 2,500SQ 4C × 0.47km - 케이블 포설 : 4구간 / 케이블 접속 : 8개소(종단4개소, 중간4개소)","2025-11-24 09:00","2025-12-10 18:00","2025-11-24 09:00","2025-12-10 18:00","연속"]
[604,"광주전남","순천","장흥벌교 T/L","24-25년 순천전력지사 변전협력회사 공사","벌교S/S 장흥-벌교T/L GIS 전자변대체","2025-11-03 09:00","2025-11-03 18:00","취소","취소","연속"]
[605,"광주전남","순천","벌교고흥#1 T/L","피뢰기 설치(벌교-고흥#1T/L)","피뢰기 설치","2025-11-10 07:00","2025-11-11 18:00","취소","취소","매일"]
[606,"광주전남","순천","장흥벌교 T/L","피뢰기 설치(장흥-벌교T/L)","피뢰기 설치","2025-11-10 07:00","2025-11-11 18:00","취소","취소","매일"]
[607,"광주전남","순천","소라서순천#2 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 소라-서순천#2T/L GIS 정밀점검","2025-11-12 16:00","2025-11-13 10:00","취소","취소","연속"]
[608,"광주전남","순천","소라서순천#1 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 소라-서순천#1T/L GIS 정밀점검","2025-11-10 16:00","2025-11-11 10:00","취소","취소","연속"]
[609,"광주전남","순천","서순천주암HP T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 서순천-주암HP T/L GIS 정밀점검","2025-11-05 16:00","2025-11-06 10:00","취소","취소","연속"]
[610,"광주전남","순천","서순천벌교#1 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 서순천-벌교#1T/L GIS 정밀점검","2025-11-03 16:00","2025-11-04 10:00","취소","취소","연속"]
[611,"광주전남","순천","서순천벌교#2 T/L","피뢰기 설치(서순천-벌교#2T/L)","피뢰기 설치","2025-11-03 07:00","2025-11-07 18:00","취소","취소","매일"]
[612,"광주전남","순천","서순천벌교#2 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 서순천-벌교#2T/L GIS 정밀점검","2025-11-19 16:00","2025-11-20 10:00","취소","취소","연속"]
[613,"광주전남","순천","승주서순천 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 승주-서순천T/L GIS 정밀점검","2025-11-17 16:00","2025-11-18 10:00","취소","취소","연속"]
[614,"광주전남","순천","소라서순천#2 T/L","애자련 보강(소라-서순천#2)","애자련 보강","2025-11-21 13:00","2025-11-21 18:00","취소","취소","연속"]
[615,"광주전남","순천","소라서순천#1 T/L","애자련 보강(소라-서순천#1)","애자련 보강","2025-11-20 07:00","2025-11-20 12:00","취소","취소","연속"]
[616,"광주전남","순천","순천율촌#2 T/L","애자련 보강(순천-율촌)","애자련 보강","2025-11-24 13:00","2025-11-24 18:00","2025-11-24 13:00","2025-11-24 18:00","연속"]
[617,"광주전남","순천","순천율촌#1 T/L","애자련 보강(순천-율촌)","애자련 보강","2025-11-24 07:00","2025-11-24 18:00","2025-11-24 07:00","2025-11-24 18:00","연속"]
[618,"광주전남","순천","승주서순천 T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-서순천, 화순-승주2(통보분) 병가) ※휴일(22,23일) 미작업","2025-11-17 07:00","2025-11-28 18:00","취소","취소","매일"]
[619,"광주전남","순천","승주주암HP T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-주암HP, 화순-승주1(통보분) 병가) ※휴일(8,9일) 미작업","2025-11-03 07:00","2025-11-14 18:00","취소","취소","매일"]
[620,"광주전남","순천","승주주암HP T/L","항공장애표시구 교체(승주-주암HP)","항공장애표시구 교체","2025-11-12 13:00","2025-11-12 18:00","취소","취소","연속"]
[621,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-11-13 17:00","2025-11-13 21:00","2025-11-13 17:00","2025-11-13 21:00","연속"]
[622,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-11-07 09:00","2025-11-12 09:00","2025-11-07 09:00","2025-11-12 09:00","연속"]
[623,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-11-28 09:00","2025-11-28 18:00","2025-11-28 09:00","2025-11-28 18:00","연속"]
[624,"광주전남","순천","여수소라#1 T/L"," 여수-소라 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (2,3호 : 여수-소라1, 여천-여수1 병가)","2025-11-21 07:00","2025-11-21 18:00","2025-11-21 07:00","2025-11-21 18:00","연속"]
[625,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-11-20 09:00","2025-11-28 09:00","2025-11-20 09:00","2025-11-28 09:00","연속"]
[626,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-11-20 09:00","2025-11-28 09:00","2025-11-20 09:00","2025-11-28 09:00","연속"]
[627,"광주전남","순천","여수소라#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체 무부하가압용","2025-11-19 17:00","2025-11-20 09:00","2025-11-19 17:00","2025-11-20 09:00","연속"]
[628,"광주전남","순천","여수소라#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체용 무부하가압","2025-11-19 17:00","2025-11-20 09:00","2025-11-19 17:00","2025-11-20 09:00","연속"]
[629,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-11-14 17:00","2025-11-14 21:00","2025-11-14 17:00","2025-11-14 21:00","연속"]
[630,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-11-07 09:00","2025-11-28 18:00","2025-11-07 09:00","2025-11-28 18:00","연속"]
[631,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-11-12 09:00","2025-11-20 09:00","2025-11-12 09:00","2025-11-20 09:00","연속"]
[632,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-11-12 09:00","2025-11-20 09:00","2025-11-12 09:00","2025-11-20 09:00","연속"]
[633,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-11-07 09:00","2025-11-28 18:00","2025-11-07 09:00","2025-11-28 18:00","연속"]
[634,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-11-07 09:00","2025-11-12 09:00","2025-11-07 09:00","2025-11-12 09:00","연속"]
[635,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-10-31 09:00","2025-10-31 18:00","2025-10-31 09:00","2025-10-31 18:00","연속"]
[636,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수-소라#1,2T/L 보호배전반 엔지니어링","2025-11-05 17:00","2025-11-06 10:00","2025-11-05 17:00","2025-11-06 10:00","연속"]
[637,"광주전남","순천","여수소라#2 T/L"," 여수-소라 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (2,3호 : 여수-소라2, 여천-여수2 병가)","2025-11-07 07:00","2025-11-07 18:00","취소","취소","연속"]
[638,"광주전남","순천","율촌여수산단#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수산단 율촌-여수산단#2T/L GIS 보통점검, 율촌S/S 율촌-여수산단#2T/L LA 보통점검","2025-11-06 09:00","2025-11-06 18:00","취소","취소","연속"]
[639,"광주전남","순천","용성여수산단#2 T/L","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-11-27 09:00","2025-11-28 18:00","2025-11-27 09:00","2025-11-28 18:00","연속"]
[640,"광주전남","순천","여수T/P #65 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-11-03 09:00","2025-11-04 18:00","2025-11-03 09:00","2025-11-04 18:00","연속"]
[641,"광주전남","순천","호남TP여수TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가)","2025-11-14 07:00","2025-11-14 18:00","취소","취소","연속"]
[642,"광주전남","순천","여수T/P #61 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-11-17 09:00","2025-11-18 14:00","2025-11-17 09:00","2025-11-18 14:00","연속"]
[643,"광주전남","순천","여수TP여천#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여수TP-여천#1T/L GIS 조작시험","2025-11-17 09:00","2025-11-17 18:00","취소","취소","연속"]
[644,"광주전남","순천","여수T/P CB 6183","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-11-17 09:00","2025-11-19 18:00","2025-11-17 09:00","2025-11-19 18:00","연속"]
[645,"광주전남","순천","여수TP여천#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP,여천S/S 여수TP-여천#2T/L GIS 보통점검","2025-11-18 09:00","2025-11-18 18:00","취소","취소","연속"]
[646,"광주전남","순천","여수T/P #66 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-11-18 14:00","2025-11-19 18:00","2025-11-18 14:00","2025-11-19 18:00","연속"]
[647,"광주전남","순천","여수TP화치#1 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","여수화력S/S 여수TP-화치#1T/L GIS 정밀점검","2025-11-19 09:00","2025-11-20 18:00","취소","취소","연속"]
[648,"광주전남","순천","여수TP용성#2 T/L","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-11-20 09:00","2025-11-21 18:00","2025-11-20 09:00","2025-11-21 18:00","연속"]
[649,"광주전남","순천","호남TP여수TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP2, 여천-여수1 병가) (2호 : 여천-호남TP2, 호남TP-여수TP2 병가)","2025-11-24 07:00","2025-11-24 18:00","취소","취소","연속"]
[650,"광주전남","순천","여수TP화치#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP-화치#2T/L 보호배전반 대체","2025-11-24 09:00","2025-11-28 18:00","취소","취소","연속"]
[651,"광주전남","순천","여수TP화치#2 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","여수화력S/S 여수TP-화치#2T/L GIS 정밀점검","2025-11-24 09:00","2025-11-25 18:00","취소","취소","연속"]
[652,"광주전남","순천","호남TP여수TP#2 T/L","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-11-25 09:00","2025-11-26 18:00","2025-11-25 09:00","2025-11-26 18:00","연속"]
[653,"광주전남","순천","여수TP용성#2 T/L","SB댐퍼 설치(여수TP-용성T/L)","SB댐퍼 설치","2025-11-28 07:00","2025-11-28 18:00","취소","취소","연속"]
[654,"광주전남","순천","여수TP용성#1 T/L","SB댐퍼 설치(여수TP-용성T/L)","SB댐퍼 설치","2025-11-27 07:00","2025-11-27 18:00","취소","취소","연속"]
[655,"광주전남","순천","여천호남TP#1 T/L","여천S/S  GIS 기기기초 공사","활선직하 기기기초 안전이격 휴전 / 매일휴전 / 즉시가압 가능 / 동시휴전 없음","2025-11-03 09:00","2025-11-28 18:00","2025-11-03 09:00","2025-11-28 18:00","매일"]
[656,"광주전남","순천","여천여수#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여천-여수#2T/L GIS 조작시험","2025-11-24 09:00","2025-11-24 18:00","취소","취소","연속"]
[657,"광주전남","순천","여천여수#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여천-여수#1T/L GIS 보통점검 및 전자변대체","2025-11-21 09:00","2025-11-21 18:00","취소","취소","연속"]
[658,"광주전남","순천","여천호남TP#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여천-호남TP#2T/L GIS 보통점검","2025-11-20 09:00","2025-11-20 18:00","취소","취소","연속"]
[659,"광주전남","순천","여천호남TP#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여천S/S 여천-호남TP#11T/L GIS 보통점검 및 전자변대체","2025-11-19 09:00","2025-11-19 18:00","취소","취소","연속"]
[660,"광주전남","순천","여천호남TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP2, 여천-여수1 병가) (2호 : 여천-호남TP2, 호남TP-여수TP2 병가) ※휴일(22,23일) 미작업","2025-11-17 07:00","2025-11-28 18:00","취소","취소","매일"]
[661,"광주전남","순천","여천여수#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP2, 여천-여수1 병가) (2호 : 여천-호남TP2, 호남TP-여수TP2 병가)","2025-11-17 07:00","2025-11-21 18:00","취소","취소","매일"]
[662,"광주전남","순천","여수TP여천#1 T/L","여천S/S  GIS 기기기초 공사","활선직하 기기기초 안전이격 휴전 / 매일휴전 / 즉시가압 가능 / 동시휴전 없음","2025-11-03 09:00","2025-11-28 18:00","2025-11-03 09:00","2025-11-28 18:00","매일"]
[663,"광주전남","순천","여수TP여천#2 T/L","여천S/S  GIS 기기기초 공사","활선직하 기기기초 안전이격 휴전 / 매일휴전 / 즉시가압 가능 / 동시휴전 없음","2025-11-03 09:00","2025-11-28 18:00","2025-11-03 09:00","2025-11-28 18:00","매일"]
[664,"광주전남","순천","여천호남TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가) ※휴일(8,9일) 미작업","2025-11-03 07:00","2025-11-14 18:00","취소","취소","매일"]
[665,"광주전남","순천","여천여수#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가)","2025-11-03 07:00","2025-11-07 18:00","취소","취소","매일"]
[666,"광주전남","순천","여천호남TP#2 T/L","여천S/S  GIS 기기기초 공사","활선직하 기기기초 안전이격 휴전 / 매일휴전 / 즉시가압 가능 / 동시휴전 없음","2025-11-03 09:00","2025-11-28 18:00","2025-11-03 09:00","2025-11-28 18:00","매일"]
[667,"광주전남","순천","여천여수#2 T/L","여천S/S  GIS 기기기초 공사","활선직하 기기기초 안전이격 휴전 / 매일휴전 / 즉시가압 가능 / 동시휴전 없음","2025-11-03 09:00","2025-11-28 18:00","2025-11-03 09:00","2025-11-28 18:00","매일"]
[668,"광주전남","순천","여천여수#1 T/L","여천S/S  GIS 기기기초 공사","활선직하 기기기초 안전이격 휴전 / 매일휴전 / 즉시가압 가능 / 동시휴전 없음","2025-11-03 09:00","2025-11-28 18:00","2025-11-03 09:00","2025-11-28 18:00","매일"]
[669,"광주전남","순천","용성여수산단#2 T/L"," 용성-여수산단T/L 폴리머점퍼지지애자 설치공사","용성-여수산단#2T/L 폴리머점퍼지지애자 설치","2025-11-13 07:00","2025-11-14 18:00","2025-11-13 07:00","2025-11-14 18:00","매일"]
[670,"광주전남","순천","용성여수산단#2 T/L","SB댐퍼 설치(여수TP-용성T/L)","SB댐퍼 설치","2025-11-28 07:00","2025-11-28 18:00","취소","취소","연속"]
[671,"광주전남","순천","용성여수산단#1 T/L","SB댐퍼 설치(여수TP-용성T/L)","SB댐퍼 설치","2025-11-27 07:00","2025-11-27 18:00","취소","취소","연속"]
[672,"광주전남","순천","여수TP용성#1 T/L","가스압력계 불량 조치","가스압력계 불량 조치","2025-11-13 09:00","2025-11-14 18:00","2025-11-13 09:00","2025-11-14 18:00","연속"]
[673,"광주전남","순천","여수TP용성#1 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","여수TP-용성 #1T/L 수평 추락방지시설 설치 (1,3호 : 여수TP-용성1 2회선/ 2,2.1호 : 여수TP-용성1, 용성-여수산단1 병가)","2025-11-12 07:00","2025-11-12 18:00","취소","취소","연속"]
[674,"광주전남","순천","용성여수산단#1 T/L"," 용성-여수산단T/L 폴리머점퍼지지애자 설치공사","용성-여수산단#1T/L 폴리머점퍼지지애자 설치","2025-11-10 07:00","2025-11-12 18:00","2025-11-10 07:00","2025-11-12 18:00","매일"]
[675,"광주전남","순천","여수TP용성#1 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP,용성S/S 여수TP-용성#1T/L GIS 보통점검","2025-11-10 09:00","2025-11-10 18:00","취소","취소","연속"]
[676,"광주전남","순천","여수TP용성#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP,용성S/S 여수TP-용성#2T/L GIS 보통점검","2025-11-11 09:00","2025-11-11 18:00","취소","취소","연속"]
[677,"광주전남","순천","여수TP용성#2 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","여수TP-용성 #2T/L 수평 추락방지시설 설치 (1,3호 : 여수TP-용성2 2회선/ 2,2.1호 : 여수TP-용성2, 용성-여수산단2 병가)","2025-11-13 07:00","2025-11-13 18:00","취소","취소","연속"]
[678,"광주전남","순천","율촌민자#2 T/L"," 율촌민자 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-11-17 07:00","2025-11-21 18:00","2025-11-17 07:00","2025-11-21 18:00","매일"]
[679,"광주전남","순천","율촌화치#1 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (45~67호 : 율촌-화치1, 율촌-여수산단2 병가 68호 : 율촌-화치1, 순천-율촌2 병가)","2025-11-17 07:00","2025-11-21 18:00","취소","취소","매일"]
[680,"광주전남","순천","순천율촌#2 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (45~67호 : 율촌-화치1, 율촌-여수산단2 병가 68호 : 율촌-화치1, 순천-율촌2 병가)","2025-11-17 07:00","2025-11-17 18:00","취소","취소","연속"]
[681,"광주전남","순천","율촌여수산단#1 T/L"," 율촌-여수산단 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-11-03 07:00","2025-11-14 18:00","취소","취소","매일"]
[682,"광주전남","순천","순천율촌#1 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (45~67호 : 율촌-화치2, 율촌-여수산단1 병가 68호 : 율촌-화치2, 순천-율촌1 병가)","2025-11-14 07:00","2025-11-14 18:00","취소","취소","연속"]
[683,"광주전남","순천","율촌민자#1 T/L"," 율촌민자 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-11-10 07:00","2025-11-14 18:00","2025-11-10 07:00","2025-11-14 18:00","매일"]
[684,"광주전남","순천","율촌화치#2 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (45~67호 : 율촌-화치2, 율촌-여수산단1 병가 68호 : 율촌-화치2, 순천-율촌1 병가)","2025-11-10 07:00","2025-11-14 18:00","취소","취소","매일"]
[685,"광주전남","순천","율촌여수산단#2 T/L"," 율촌-여수산단 T/L 추락방지시설 설치공사","수평추락방지시설 설치","2025-11-17 07:00","2025-11-28 18:00","취소","취소","매일"]
[686,"광주전남","순천","태금하동화력 T/L","효성제 170kV GIS 메커니즘 교체공사","효성제 170kV GIS 메커니즘 교체공사","2025-11-27 09:00","2025-11-27 18:00","취소","취소","연속"]
[687,"광주전남","순천","여수TP화치#2 T/L","345kV 여수TP-화치 T/L 폴리머점퍼지지애자 설치공사","여수TP-화치 #2T/L 폴리머점퍼지지애자 설치","2025-11-24 07:00","2025-11-28 18:00","취소","취소","매일"]
[688,"광주전남","순천","율촌화치#1 T/L","24-25년 순천전력지사 변전협력회사 공사","화치S/S 율촌-화치#1T/L GIS 조작시험","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[689,"광주전남","순천","율촌화치#2 T/L","24-25년 순천전력지사 변전협력회사 공사","화치S/S 율촌-화치#2T/L GIS 조작시험","2025-11-07 09:00","2025-11-07 18:00","2025-11-07 09:00","2025-11-07 18:00","연속"]
[690,"광주전남","순천","여수TP화치#1 T/L","345kV 여수TP-화치 T/L 폴리머점퍼지지애자 설치공사","여수TP-화치 #1T/L 폴리머점퍼지지애자 설치","2025-11-17 07:00","2025-11-21 18:00","2025-11-17 07:00","2025-11-21 18:00","매일"]
[691,"광주전남","직할","매월화정#2 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","- 170kV GIS 정밀점검 ※ 2일 연속휴전 불가 시 1일 보통점검 대체 예정","2025-11-05 09:00","2025-11-06 18:00","취소","취소","연속"]
[692,"광주전남","직할","매월화정#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","- 170kV GIS 정밀점검 ※ 2일 연속휴전 불가 시 1일 보통점검 대체 예정","2025-11-03 09:00","2025-11-04 18:00","취소","취소","연속"]
[693,"광주전남","직할","일곡비아#1 T/L","'25년 직할 170kV GIS 정밀 및 보통점검 공사","- 170kV GIS 정밀점검 ※ 2일 연속휴전 불가 시 1일 보통점검 대체 예정","2025-11-10 09:00","2025-11-14 18:00","취소","취소","연속"]
[694,"광주전남","직할","비아하남#2 T/L"," 첨단분기 지중T/L 건설공사","구간 : (신설)C/T~(신설)첨단S/S~(기설)비아-하남M/H#12 규모 :  XLPE2,000㎟ 2C(D) × 2.2㎞ - 휴전작업 공정 : M/H#12 케이블철거. 토목관로 접속, 케이블 포설 및 접속","2025-11-19 09:00","2025-12-17 18:00","2025-11-19 09:00","2025-12-17 18:00","연속"]
[695,"대구","경산","신서열병합S/Y  G.TR CB","24~25년 경산P/O 변전협력회사 총액공사","보통점검","2025-11-20 09:30","2025-11-20 14:00","취소","취소","연속"]
[696,"대구","경산","신서열병합S/Y  .TR CB","24~25년 경산P/O 변전협력회사 총액공사","보통점검","2025-11-20 14:00","2025-11-20 18:00","취소","취소","연속"]
[697,"대구","경산","안심신서열병합#2 T/L","24~25년 경산P/O 변전협력회사 총액공사","조작시험","2025-11-19 14:00","2025-11-19 18:00","취소","취소","연속"]
[698,"대구","경산","안심신서열병합#1 T/L","24~25년 경산P/O 변전협력회사 총액공사","조작시험","2025-11-19 09:30","2025-11-19 12:00","취소","취소","연속"]
[699,"대구","경산","청통영천#2 T/L","2025년 가공송전 순시점검 위탁공사"," 청통-영천#2T/L 정밀점검","2025-11-03 08:30","2025-11-06 18:00","2025-11-03 08:30","2025-11-06 18:00","연속"]
[700,"대구","경산","아화영천#2 T/L","(안전확보)2025년 가공송전 순시점검 위탁공사"," 청통-영천#2T/L 정밀점검 안전확보차 -  청통-영천#2T/L No.40~43 병가철탑","2025-11-06 08:30","2025-11-06 18:00","2025-11-06 08:30","2025-11-06 18:00","연속"]
[701,"대구","달성","왜관다사#1 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 왜관-다사 #1T/L 정밀점검(11/03~11/05)  다사-달서(정밀점검 안전확보)(11/06)","2025-11-03 09:00","2025-11-06 18:00","2025-11-03 09:00","2025-11-06 18:00","연속"]
[702,"대구","달성","다사달서 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 왜관-다사 (정밀점검 안전확보)(11/04~11/05)  다사-달서 T/L 정밀점검(11/06~11/11)","2025-11-04 09:00","2025-11-11 18:00","2025-11-04 09:00","2025-11-11 18:00","연속"]
[703,"대구","달성","왜관다사#2 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 왜관-다사 #2T/L 정밀점검(11/17~11/19)  강창-다사(정밀점검 안전확보)(11/20)","2025-11-17 09:00","2025-11-20 18:00","2025-11-17 09:00","2025-11-20 18:00","연속"]
[704,"대구","달성","고령다산#2 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 고령-다산 #2T/L 정밀점검 관련 안전확보","2025-11-03 09:00","2025-11-04 18:00","2025-11-03 09:00","2025-11-04 18:00","연속"]
[705,"대구","달성","달성상인#1 T/L","달성SS 모선보호반 대체 준공시험","달성SS 모선보호반 대체 준공시험","2025-11-06 13:00","2025-11-06 13:30","2025-11-06 13:00","2025-11-06 13:30","연속"]
[706,"대구","달성","달성월배#2 T/L","달성SS 모선보호반 대체 준공시험","달성SS 모선보호반 대체 준공시험","2025-11-06 14:30","2025-11-06 15:00","2025-11-06 14:30","2025-11-06 15:00","연속"]
[707,"대구","달성","달성월배#1 T/L","달성SS 모선보호반 대체 준공시험","달성SS 모선보호반 대체 준공시험","2025-11-06 14:00","2025-11-06 14:30","2025-11-06 14:00","2025-11-06 14:30","연속"]
[708,"대구","달성","성서달성#2 T/L","달성SS 모선보호반 대체 준공시험","달성SS 모선보호반 대체 준공시험","2025-11-06 11:30","2025-11-06 12:00","2025-11-06 11:30","2025-11-06 12:00","연속"]
[709,"대구","달성","달성S/S CB 6100","달성SS 모선보호반 대체 관련 6100 BUS TIE 휴전","달성SS 모선보호반 대체 관련 6100 BUS TIE 휴전","2025-11-04 09:00","2025-11-06 18:00","2025-11-04 09:00","2025-11-06 18:00","연속"]
[710,"대구","달성","성서달성#1 T/L","달성SS 모선보호반 대체 준공시험","달성SS 모선보호반 대체 준공시험","2025-11-06 11:00","2025-11-06 11:30","2025-11-06 11:00","2025-11-06 11:30","연속"]
[711,"대구","달성","논공달성#2 T/L","달성SS 모선보호반 대체 준공시험","달성SS 모선보호반 대체 준공시험","2025-11-06 10:30","2025-11-06 11:00","2025-11-06 10:30","2025-11-06 11:00","연속"]
[712,"대구","달성","논공달성#1 T/L","달성SS 모선보호반 대체 준공시험","달성SS 모선보호반 대체 준공시험","2025-11-06 10:00","2025-11-06 10:30","2025-11-06 10:00","2025-11-06 10:30","연속"]
[713,"대구","달성","달성상인#2 T/L","달성SS 모선보호반 대체 준공시험","달성SS 모선보호반 대체 준공시험","2025-11-06 13:30","2025-11-06 14:00","2025-11-06 13:30","2025-11-06 14:00","연속"]
[714,"대구","달성","대구범물#1 T/L","2024~25년 대구직할 가공송전 협력회사 공사"," 대구-범물T/L 수평 추락방지장치 및 조류착지방지장치 설치","2025-11-03 07:00","2025-11-05 18:00","2025-11-03 07:00","2025-11-05 18:00","연속"]
[715,"대구","달성","강창성서#2 T/L","강창-성서#2T/L GIS 조작시험","강창-성서#2T/L GIS 조작시험","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[716,"대구","달성","쌍림합천#1 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 쌍림-합천 #1T/L (정밀점검,1~22호) 11.17~11.19  쌍림-합천 #1T/L (고령-쌍림#1 작업관련 안전확보) 11.14","2025-11-14 09:00","2025-11-19 18:00","취소","취소","연속"]
[717,"대구","달성","고령쌍림#2 T/L","2025년 달성전력지사 가공송전 순시점검 위탁공사"," 고령-쌍림 #2T/L (정밀점검,1~63호) 11.03~11.14  고령-쌍림 #2T/L (쌍림-합천 작업관련 안전확보) 11.17","2025-11-03 09:00","2025-11-17 18:00","2025-11-17 09:00","2025-11-17 18:00","연속"]
[718,"대구","직할","공평서침산 T/L","25-26년도 대구본부 직할 지중송전 협력회사 공사","OF케이블 절연유 열화진단","2025-11-21 09:00","2025-11-21 18:00","취소","취소","연속"]
[719,"대구","직할","공평침산 T/L","25-26년도 대구본부 직할 지중송전 협력회사 공사","절연유 열화진단(3개소), SVL보강(3상), EBG 가스채취밸브 설치","2025-11-07 09:00","2025-11-07 18:00","취소","취소","연속"]
[720,"대구","직할","산격S/S #1 BUS","산격S/S  GIS 교체공사(1차수, 6233,647 대체)","산격S/S  GIS 교체공사(1차수, 6233,647 대체)","2025-11-20 09:00","2025-11-29 18:00","2025-11-21 09:00","2025-11-29 18:00","연속"]
[721,"대구","직할","산격S/S #2 BUS","산격S/S  GIS 교체공사(1차수, 6233,647 대체)","산격S/S  GIS 교체공사(1차수, 6233,647 대체)","2025-11-30 09:00","2025-12-11 18:00","2025-11-30 09:00","2025-12-07 18:00","연속"]
[722,"대구","직할","검단산격#2 T/L","산격S/S  GIS 교체공사(1차수, 6233,647 대체)","산격S/S  GIS 교체공사(1차수, 6233,647 대체)","2025-11-17 09:00","2025-12-12 18:00","2025-11-17 09:00","2025-12-30 18:00","연속"]
[723,"대구","직할","시지효목#1 T/L"," 시지-효목#1T/L 손상 케이블 교체공사","C상 J/B#2-1 ~ J/B#2-1-1 케이블 철거, 포설 및 접속","2025-11-15 09:00","2025-12-03 18:00","취소","취소","연속"]
[724,"대구","직할","시지효목#2 T/L","25-26년도 대구본부 직할 지중송전 협력회사 공사","EBG 가스채취밸브 설치 및 피뢰기점검","2025-11-14 09:00","2025-11-14 18:00","2025-11-15 09:00","2025-11-15 18:00","연속"]
[725,"대구","칠곡","구미광평#1 T/L","광평S/S  667 GIS 정밀점검공사","광평S/S  667 GIS 정밀점검공사","2025-11-05 09:00","2025-11-06 18:00","취소","취소","연속"]
[726,"대구","칠곡","어모김천#2 T/L","2025년 칠곡전력지사 가공송전 순시점검 위탁공사"," 어모-김천#2 정밀점검 - No.1~6","2025-11-06 09:00","2025-11-07 18:00","취소","취소","연속"]
[727,"대구","칠곡","남구미S/S #2 Sh.C CB","남구미S/S  GIS 교체공사","170kV GIS * 17CCT 교체","2025-11-17 09:00","2026-12-31 18:00","2025-11-17 09:00","2026-12-31 18:00","연속"]
[728,"대구","칠곡","남구미S/S #1 Sh.C CB","남구미S/S  GIS 교체공사","170kV GIS * 17CCT 교체","2025-11-17 09:00","2026-12-31 18:00","2025-11-17 09:00","2026-12-31 18:00","연속"]
[729,"대구","칠곡","남구미S/S 사곡전철#2 T/L CB","남구미S/S  GIS 교체공사","170kV GIS * 17CCT 교체","2025-11-17 09:00","2026-04-30 18:00","2025-11-17 09:00","2026-04-30 18:00","연속"]
[730,"대구","칠곡","서대구남구미#2 T/L","남구미S/S  장기사용 #1,2M.Tr 교체공사","#2M.Tr 무부하 가압","2025-11-07 16:00","2025-11-08 16:00","2025-11-07 16:00","2025-11-08 16:00","연속"]
[731,"대구","칠곡","북대구왜관#2 T/L","24~25년 칠곡전력지사 변전협력회사 공사","북대구S/S 북대구-왜관#2T/L 조작유 상승관련 점검","2025-11-17 09:30","2025-11-17 18:00","취소","취소","연속"]
[732,"대구","칠곡","고아어모#1 T/L"," 고아-어모T/L No.64 안전이격확보공사"," 고아-어모T/L No.64 본선로 구성에 따른 전선 공중이동","2025-11-03 07:00","2025-11-05 18:00","2025-11-03 07:00","2025-11-05 18:00","연속"]
[733,"대구","칠곡","고아어모#2 T/L"," 고아-어모T/L No.64 안전이격확보공사"," 고아-어모T/L No.64 본선로 구성에 따른 전선 공중이동","2025-11-05 07:00","2025-11-14 18:00","2025-11-05 07:00","2025-11-14 18:00","연속"]
[734,"대구","포항","아화건천#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","아화-건천#1T/L GIS 보통점검","2025-11-10 09:00","2025-11-10 14:00","2025-11-10 09:00","2025-11-10 14:00","연속"]
[735,"대구","포항","아화건천#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","아화-건천#2T/L GIS 보통점검","2025-11-10 14:00","2025-11-10 18:00","2025-11-10 14:00","2025-11-10 18:00","연속"]
[736,"대구","포항","건천천북#2 T/L"," 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 건천-천북#2T/L 추락방지장치 설치","2025-11-04 07:00","2025-11-14 18:00","2025-11-04 07:00","2025-11-14 18:00","연속"]
[737,"대구","포항","북포항남포항#2 T/L","남포항S/S  #4M.Tr 증설공사","무부하가압 선로","2025-11-20 16:00","2025-11-21 16:00","2025-11-20 16:00","2025-11-21 16:00","연속"]
[738,"대구","포항","신영일청하#1 T/L"," 영일-입실 등 11개 T/L 피뢰기 설치공사"," 신영일-청하#1T/L 피뢰기 설치공사","2025-11-10 07:00","2025-11-14 18:00","2025-11-10 07:00","2025-11-14 18:00","연속"]
[739,"대구","포항","신영일서포항#2 T/L"," 영일-입실 등 11개 T/L 피뢰기 설치공사"," 신영일-서포항#2T/L 피뢰기 설치공사(병가선로)","2025-11-10 07:00","2025-11-14 18:00","2025-11-10 07:00","2025-11-14 18:00","연속"]
[740,"대구","포항","옥동외동#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","외동S/S 687 GIS, LA 보통점검","2025-11-14 09:00","2025-11-14 14:00","2025-11-14 09:00","2025-11-14 14:00","연속"]
[741,"대구","포항","천북경주 T/L"," 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 천북-경주T/L 추락방지장치 설치 안전확보","2025-11-24 07:00","2025-11-24 18:00","2025-11-24 07:00","2025-11-24 18:00","연속"]
[742,"대구","포항","포항경주 T/L"," 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 포항-경주T/L 추락방지장치 설치 안전확보","2025-11-21 07:00","2025-11-24 18:00","2025-11-21 07:00","2025-11-24 18:00","연속"]
[743,"대구","포항","아화건천#1 T/L","2024-2025년 경산전력지사 송전협력회사 공사(안전확보)"," 건천-천북#2T/L No.1~4 피뢰기 설치 안전확보","2025-11-17 07:00","2025-11-17 18:00","취소","취소","연속"]
[744,"대구","포항","건천천북#1 T/L"," 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 건천-천북#1T/L 추락방지장치 설치","2025-11-17 07:00","2025-11-25 18:00","취소","취소","연속"]
[745,"대구","포항","아화건천#2 T/L","2024-2025년 경산전력지사 송전협력회사 공사(안전확보)"," 건천-천북#1T/L No.1~4 피뢰기 설치 안전확보","2025-11-18 07:00","2025-11-18 18:00","취소","취소","연속"]
[746,"대구","포항","신포항상정#1 T/L"," 죽정분기T/L 건설공사 안전이격확보"," 죽정분기T/L 건설공사 안전이격확보","2025-11-17 08:00","2025-11-28 18:00","2025-11-17 08:00","2025-11-28 18:00","연속"]
[747,"대구","포항","신포항상정#2 T/L"," 죽정분기T/L 건설공사 안전이격확보"," 죽정분기T/L 건설공사 안전이격확보","2025-11-17 08:00","2025-11-21 18:00","2025-11-17 08:00","2025-11-21 18:00","연속"]
[748,"대구","포항","상정영일 T/L"," 죽정S/S 건설공사 및 죽정분기T/L 건설공사"," 죽정S/S 건설공사 및 죽정분기T/L 건설공사","2025-11-17 08:00","2025-11-28 18:00","2025-11-17 08:00","2025-11-28 18:00","연속"]
[749,"대구","포항","신포항상정#2 T/L"," 죽정분기T/L 건설공사 안전이격확보"," 죽정분기T/L 건설공사 안전이격확보","2025-11-29 08:00","2025-12-10 18:00","2025-11-29 08:00","2025-12-10 18:00","연속"]
[750,"대구","포항","상정양북 T/L"," 죽정S/S 건설공사 및 죽정분기T/L 건설공사"," 죽정S/S 건설공사 및 죽정분기T/L 건설공사","2025-11-29 08:00","2025-12-10 18:00","2025-11-29 08:00","2025-12-10 18:00","연속"]
[751,"경북","구미","동상주점촌#1 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 동상주-점촌T/L No.8,12,67 수직,수평레일 설치공사","2025-11-06 07:00","2025-11-06 18:00","2025-11-06 07:00","2025-11-06 13:00","연속"]
[752,"경북","구미","동상주점촌#2 T/L","2024-2025년 구미전력지사 송전협력회사 공사"," 동상주-점촌T/L No.8,12,67 수직,수평레일 설치공사","2025-11-07 07:00","2025-11-07 18:00","2025-11-06 13:00","2025-11-06 18:00","연속"]
[753,"경북","구미","화동영동 T/L","2025년 가공송전 순시점검 위탁공사 (정밀점검)"," 화동-영동T/L 정밀점검","2025-11-14 09:00","2025-11-21 18:00","2025-11-14 09:00","2025-11-21 18:00","매일"]
[754,"경북","구미","화동보은 T/L","2025년 가공송전 순시점검 위탁공사 (정밀점검)"," 화동-보은T/L 정밀점검","2025-11-07 09:00","2025-11-14 18:00","취소","취소","연속"]
[755,"경북","구미","상주화동#2 T/L","2025년 가공송전 순시점검 위탁공사 (정밀점검)"," 상주-화동#2T/L 정밀점검","2025-11-21 09:00","2025-11-28 18:00","2025-11-21 09:00","2025-11-28 18:00","매일"]
[756,"경북","영주","점촌문경 T/L","2024-2025년 영주전력지사 변전협력회사 총액공사","문경S/S  점촌-문경T/L 디지털 유압력계 교체","2025-11-29 10:00","2025-11-29 16:00","2025-11-29 10:00","2025-11-29 16:00","연속"]
[757,"경북","영주","봉화S/S 춘양전철#2T/L CB"," 봉화S/S 리모델링 공사","○ 외벽 마감재 교체(드라이비트 -> AL복합판넬, 화강석, 징크판넬)","2025-11-03 08:00","2025-11-14 17:00","2025-11-03 08:00","2025-11-14 17:00","연속"]
[758,"경북","영주","신영주영주#1 T/L","2024-25년 영주전력지사 변전협력회사 공사","피뢰기 하자점검","2025-11-28 09:00","2025-11-28 13:00","2025-11-28 09:00","2025-11-28 13:00","연속"]
[759,"경북","영주","신영주영주#2 T/L","2024-25년 영주전력지사 변전협력회사 공사","피뢰기 하자점검","2025-11-28 13:00","2025-11-28 18:00","2025-11-28 13:00","2025-11-28 18:00","연속"]
[760,"경북","영주","예천점촌#1 T/L","2025년 영주전력지사  GIS 정밀점검공사"," GIS 정밀점검 및 무부하가압","2025-11-03 09:00","2025-11-05 18:00","취소","취소","연속"]
[761,"경북","영주","예천점촌#2 T/L","2025년 영주전력지사  GIS 정밀점검공사"," GIS 정밀점검 및 무부하가압","2025-11-06 09:00","2025-11-08 18:00","취소","취소","연속"]
[762,"경북","영주","예천점촌#2 T/L"," 예천-점촌T/L No.66호 지장철탑이설공사"," 예천-점촌T/L No.66호 지장철탑이설공사","2025-11-17 08:00","2025-11-21 17:00","취소","취소","연속"]
[763,"경북","영주","예천점촌#1 T/L"," 예천-점촌T/L No.66호 지장철탑이설공사"," 예천-점촌T/L No.66호 지장철탑이설공사","2025-11-24 08:00","2025-11-28 17:00","취소","취소","연속"]
[764,"경북","영주","동상주점촌#2 T/L","2025년 영주전력지사  GIS 정밀점검공사"," GIS 정밀점검 후 무부하가압","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[765,"경북","직할","신영주안동#2 T/L","안동S/S #4M.Tr 및 모선보강용 GIS 증설공사"," GIS 설치","2025-11-13 08:00","2025-11-25 18:00","2025-11-13 08:00","2025-11-25 18:00","연속"]
[766,"경북","직할","안동동안동#2 T/L","2025~2026년도 지중송전 협력회사 공사","-  안동-동안동#2T/L 지중피뢰기 3상 열화진단 및 단자조임, 애관청소","2025-11-06 13:00","2025-11-06 18:00","2025-11-06 13:00","2025-11-06 18:00","연속"]
[767,"경북","직할","안동안동HP T/L","24-25년 경북직할 송전협력회사 공사","수평 추락방지장치 설치공사(안전확보차)","2025-11-11 08:00","2025-11-11 18:00","2025-11-11 08:00","2025-11-11 18:00","연속"]
[768,"경북","직할","안동풍산 T/L","24-25년 경북직할 송전협력회사 공사","수평 추락방지장치 설치공사","2025-11-06 08:00","2025-11-11 18:00","2025-11-06 08:00","2025-11-11 18:00","연속"]
[769,"경북","직할","영덕해맞이풍력 T/L CB","영덕S/S 디지털화 공사","영덕S/S 디지털화 공사","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[770,"경북","직할","진보S/S #1 M.Tr CB","진보S/S  장기사용 GIS 교체공사(2차수)","진보S/S  장기사용 GIS 교체공사(2차수) -  GIS 2CCT 교체","2025-11-24 09:00","2025-12-19 18:00","2025-11-24 09:00","2025-12-19 18:00","연속"]
[771,"경북","직할","진보S/S #2 BUS","진보S/S  장기사용 GIS 교체공사(1차수)","진보S/S  장기사용 GIS 교체공사(1차수) -  GIS 3CCT 교체","2025-11-06 09:00","2025-11-21 18:00","2025-11-06 09:00","2025-11-21 18:00","연속"]
[772,"경북","직할","영덕진보#2 T/L","진보S/S  장기사용 GIS 교체공사(2차수)","진보S/S  장기사용 GIS 교체공사(2차수) -  GIS 2CCT 교체","2025-11-24 09:00","2025-12-19 18:00","2025-11-24 09:00","2025-12-19 18:00","연속"]
[773,"경북","직할","현종산풍력평해#1 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 조작시험","2025-11-19 09:00","2025-11-19 14:00","2025-11-11 09:00","2025-11-11 14:00","연속"]
[774,"경북","직할","현종산풍력평해#1 T/L","24~25년 경북본부 직할 변전협력회사 공사","GIS 조작시험","2025-11-19 14:00","2025-11-19 18:00","2025-11-11 14:00","2025-11-11 18:00","연속"]
[775,"부산울산","동부산","구서노포#1 T/L","345kV 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치( 구서-노포#1)","2025-11-20 07:00","2025-11-22 18:00","2025-11-20 07:00","2025-11-22 18:00","연속"]
[776,"부산울산","동부산","노포정관#2 T/L","345kV 울주-고리NP 등 22개TL 송전철탑 정비공사","수평추락방지장치,폴리머점퍼지지애자 설치( 노포-정관#2)","2025-11-20 07:00","2025-11-22 18:00","2025-11-20 07:00","2025-11-22 18:00","연속"]
[777,"부산울산","동부산","노포정관#2 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 서창-산막#1T/L 송전용피뢰기 설치(No.37~72) No.37호 상단  노포-정관#2T/L 안전이격","2025-11-09 08:00","2025-11-09 10:00","2025-11-09 08:00","2025-11-09 10:00","연속"]
[778,"부산울산","동부산","웅촌서창#1 T/L","2025년 가공송전 순시점검 위탁공사"," 웅촌-서창#1T/L 정밀점검","2025-11-10 09:00","2025-11-12 18:00","2025-11-10 09:00","2025-11-12 18:00","연속"]
[779,"부산울산","동부산","서창산막#2 T/L","345kV 울주-고리NP 등 22개TL 송전철탑 정비공사","수평추락방지장치 설치( 서창-산막#2)","2025-11-22 07:00","2025-11-22 18:00","2025-11-22 07:00","2025-11-22 18:00","연속"]
[780,"부산울산","동부산","웅촌서창#2 T/L","2025년 가공송전 순시점검 위탁공사"," 웅촌-서창#2T/L 정밀점검","2025-11-17 09:00","2025-11-20 18:00","2025-11-17 09:00","2025-11-20 18:00","연속"]
[781,"부산울산","동부산","수영우동 T/L","우동S/S  수영-우동T/L 보호반 대체","우동S/S  수영-우동T/L 보호반 대체","2025-11-08 09:00","2025-11-09 18:00","2025-11-08 09:00","2025-11-09 18:00","연속"]
[782,"부산울산","동부산","우동대연 T/L","2025년 서부산전력지사 가공송전 순시점검 위탁공사","정보T/L 송전선로 정밀점검, 조류착지방지장치 설치","2025-11-02 08:00","2025-11-02 18:00","취소","취소","연속"]
[783,"부산울산","동부산","정보대연 T/L","2025년 서부산전력지사 가공송전 순시점검 위탁공사","정보T/L 송전선로 정밀점검, 조류착지방지장치 설치","2025-11-01 08:00","2025-11-01 18:00","취소","취소","연속"]
[784,"부산울산","동부산","정보S/S CB 6100","정보S/S 61000 차단기 동작시험","정보S/S 61000 차단기 동작시험","2025-11-15 09:00","2025-11-15 18:00","2025-11-15 09:00","2025-11-15 18:00","연속"]
[785,"부산울산","동부산","시랑좌동#2 T/L","좌동S/S  장기사용 GIS 교체공사","시랑좌동#1T/L 월부싱 설치 관련 안전이격 휴전","2025-11-01 08:00","2025-11-02 17:00","2025-11-01 08:00","2025-11-02 17:00","연속"]
[786,"부산울산","동부산","좌동우동#1 T/L","좌동S/S  장기사용 GIS 교체공사","60BUS 및 1DS 설치부 시험가압(617,6133)","2025-11-03 17:00","2025-11-04 17:00","2025-11-03 17:00","2025-11-04 17:00","연속"]
[787,"부산울산","북부산","학장개금#1 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","1. 대 상 :  학장-개금#1T/L 2. 작업내용 : 접속함 절연유채취 3. 업체명 : 공영전력","2025-11-05 09:00","2025-11-05 18:00","2025-11-05 09:00","2025-11-05 18:00","연속"]
[788,"부산울산","북부산","학장개금#2 T/L","지중송전 OF케이블 절연유 열화진단용 시료 채취","1. 대 상 :  학장-개금#2T/L 2. 작업내용 : 접속함 절연유채취 3. 업체명 : 공영전력","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[789,"부산울산","북부산","개금범천#1 T/L","개금S/S  장기사용 GIS 교체공사"," 개금-범천#1T/L 교체 시행","2025-11-25 09:00","2025-12-15 18:00","2025-11-25 09:00","2025-12-15 18:00","연속"]
[790,"부산울산","북부산","북부산구포#3 T/L","24-25 북부산 변전협력회사 총액공사","구포S/S 북부산-구포#3T/L GIS 조작시험","2025-11-06 09:00","2025-11-06 14:00","2025-11-06 09:00","2025-11-06 14:00","연속"]
[791,"부산울산","북부산","모라엄궁#1 T/L","24-25 북부산 변전협력회사 총액공사","엄궁,모라S/S 모라-엄궁#1T/L GIS 조작시험","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[792,"부산울산","북부산","북부산미남#2 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 미남-덕포#2T/L 송전용피뢰기 설치(No.1~10) 하단  북부산-미남#2T/L 안전이격","2025-11-10 08:00","2025-11-10 10:00","취소","취소","연속"]
[793,"부산울산","북부산","북부산미남#2 T/L","대동 등 5개 C/T PD 집합반 설치공사","북부산미남#2 T/L PD 집합반 설치공사","2025-11-20 09:00","2025-11-20 18:00","2025-11-20 09:00","2025-11-20 18:00","연속"]
[794,"부산울산","북부산","북부산미남#1 T/L","대동 등 5개 C/T PD 집합반 설치공사","북부산미남#1 T/L PD 집합반 설치공사","2025-11-19 09:00","2025-11-19 18:00","2025-11-19 09:00","2025-11-19 18:00","연속"]
[795,"부산울산","북부산","북부산삼랑진PP T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","고정형폴리머애자 설치 공사 안전이격","2025-11-10 08:00","2025-11-10 12:00","취소","취소","연속"]
[796,"부산울산","북부산","북부산물금 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 북부산-물금T/L 송전용피뢰기 설치 : No.24.1호(1기)","2025-11-23 07:00","2025-11-23 09:00","2025-11-23 07:00","2025-11-23 09:00","연속"]
[797,"부산울산","북부산","북부산양산 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","고정형폴리머애자 설치 공사 : No.43(1개)","2025-11-10 08:00","2025-11-10 12:00","취소","취소","연속"]
[798,"부산울산","북부산","서창산막#2 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","고정형폴리머애자 설치 : No.16 / SB댐퍼 설치 : No.2,9,47","2025-11-08 08:00","2025-11-08 17:00","2025-11-08 08:00","2025-11-08 17:00","연속"]
[799,"부산울산","북부산","서창산막#1 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 서창-산막#1T/L 송전용피뢰기 설치 : No.37~72(14기)","2025-11-09 08:00","2025-11-09 18:00","2025-11-09 08:00","2025-11-09 18:00","연속"]
[800,"부산울산","북부산","서창산막#2 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","고정형폴리머애자설치 안전이격","2025-11-29 08:00","2025-11-29 17:00","2025-11-29 08:00","2025-11-29 17:00","연속"]
[801,"부산울산","북부산","석계산막#2 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","고정형폴리머애자설치 : No.34,35","2025-11-29 08:00","2025-11-29 17:00","2025-11-29 08:00","2025-11-29 17:00","연속"]
[802,"부산울산","북부산","북부산삼랑진PP T/L","2025년 가공송전선로 순시점검 위탁공사 정밀점검"," 북부산-삼랑진T/L 정밀점검 -점검구간 : 총 No.1~10,37~40,64~105호)","2025-11-28 07:00","2025-11-29 18:00","2025-11-28 07:00","2025-11-29 18:00","연속"]
[803,"부산울산","북부산","양산삼랑진PP T/L","25 북부산  GIS 정밀점검공사","양산-삼랑진T/L GIS 정밀점검 및 시험가압","2025-11-26 08:00","2025-11-27 18:00","취소","취소","연속"]
[804,"부산울산","북부산","언양석계#1 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 언양-석계#1T/L 송전용피뢰기 설치 : No.36~41(6기)","2025-11-14 08:00","2025-11-14 18:00","2025-11-14 08:00","2025-11-14 18:00","연속"]
[805,"부산울산","북부산","석계산막#1 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 석계-산막#1T/L 송전용피뢰기 설치 : No.6~29(23기)","2025-11-15 08:00","2025-11-15 18:00","2025-11-15 08:00","2025-11-15 18:00","연속"]
[806,"부산울산","북부산","북부산양산 T/L","2025년 가공송전선로 순시점검 위탁공사 정밀점검"," 북부산-양산T/L 정밀점검 -점검구간 : 총 No.1~10,37~40","2025-11-21 07:00","2025-11-21 18:00","2025-11-21 07:00","2025-11-21 18:00","연속"]
[807,"부산울산","북부산","양산삼랑진PP T/L","25 북부산  GIS 정밀점검공사","양산-삼랑진T/L GIS 정밀점검 및 시험가압","2025-11-24 08:00","2025-11-25 18:00","2025-11-24 08:00","2025-11-25 18:00","연속"]
[808,"부산울산","북부산","양산산막#1 T/L","25 북부산  GIS 정밀점검공사","양산 6100 GIS 정밀점검 시험가압 선로","2025-11-20 17:00","2025-11-20 18:00","취소","취소","연속"]
[809,"부산울산","북부산","양산산막#1 T/L","25 북부산  GIS 정밀점검공사","양산 #1-1, #1-2Sh.C GCB 정밀점검 시험가압선로","2025-11-09 17:00","2025-11-09 18:00","2025-11-09 17:00","2025-11-09 18:00","연속"]
[810,"부산울산","북부산","양산산막#1 T/L","25 북부산  GIS 정밀점검공사","양산-산막#1T/L GIS 정밀점검 및 시험가압","2025-11-06 08:00","2025-11-07 18:00","취소","취소","연속"]
[811,"부산울산","북부산","양산산막#1 T/L","25년 북부산전력지사  GIS 정밀점검","양산S/S #1M.Tr 1차 GIS 정밀점검 관련 시험가압선로","2025-11-05 17:00","2025-11-05 18:00","취소","취소","연속"]
[812,"부산울산","북부산","양산산막#1 T/L","25 북부산  GIS 정밀점검공사","양산 Sh.C Main GIS 정밀점검 시험가압선로","2025-11-16 17:00","2025-11-16 18:00","2025-11-16 17:00","2025-11-16 18:00","연속"]
[813,"부산울산","북부산","서부산엄궁#1 T/L","24-25 북부산 변전협력회사 총액공사","엄궁S/S 서부산-엄궁#1T/L GIS 조작시험","2025-11-03 09:00","2025-11-03 14:00","2025-11-03 09:00","2025-11-03 14:00","연속"]
[814,"부산울산","북부산","서부산엄궁#2 T/L","24-25 북부산 변전협력회사 총액공사","엄궁S/S 서부산-엄궁#2T/L GIS 조작시험","2025-11-03 14:00","2025-11-03 18:00","2025-11-03 14:00","2025-11-03 18:00","연속"]
[815,"부산울산","북부산","호포대동#1 T/L","대동 등 5개 C/T PD 집합반 설치공사","호포대동#1 T/L PD 집합반 설치공사","2025-11-22 08:00","2025-11-22 13:00","취소","취소","연속"]
[816,"부산울산","북부산","호포물금 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 호포-물금T/L 송전용피뢰기 설치 : No.37~39(3기)","2025-11-30 07:00","2025-11-30 11:00","취소","취소","연속"]
[817,"부산울산","북부산","북부산호포 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 북부산-호포T/L 송전용피뢰기 설치 : No.6~9(4기)","2025-11-02 07:00","2025-11-02 12:00","2025-11-02 07:00","2025-11-02 12:00","연속"]
[818,"부산울산","북부산","호포대동#2 T/L","대동 등 5개 C/T PD 집합반 설치공사","호포대동#2 T/L PD 집합반 설치공사","2025-11-22 13:00","2025-11-22 18:00","취소","취소","연속"]
[819,"부산울산","서부산","서부산S/S CB 6344","서부산S/S 345kV #1 M.Tr 2차 GIS 동작시험","서부산S/S 345kV #1 M.Tr 2차 GIS 동작시험","2025-11-04 09:00","2025-11-04 18:00","2025-11-04 09:00","2025-11-04 18:00","연속"]
[820,"부산울산","서부산","서부산S/S CB 6344","서부산S/S 345kV #3 M.Tr 2차 GIS 동작시험","서부산S/S 345kV #3 M.Tr 2차 GIS 동작시험","2025-11-05 09:00","2025-11-05 18:00","2025-11-05 09:00","2025-11-05 18:00","연속"]
[821,"부산울산","서부산","신녹산S/S CB 6100","신녹산S/S  #60-#65 BUS TIE GIS 보통점검","신녹산S/S  #60-#65 BUS TIE GIS 보통점검","2025-11-12 09:00","2025-11-12 18:00","2025-11-12 09:00","2025-11-12 18:00","연속"]
[822,"부산울산","서부산","신녹산순아#2 T/L","신녹산S/S  신녹산-순아 #2T/L GIS 보통점검","신녹산S/S  신녹산-순아 #2T/L GIS 보통점검","2025-11-06 09:00","2025-11-06 18:00","2025-11-06 09:00","2025-11-06 18:00","연속"]
[823,"부산울산","서부산","신녹산순아#1 T/L","신녹산S/S  신녹산-순아 #1T/L GIS 보통점검","신녹산S/S  신녹산-순아 #1T/L GIS 보통점검","2025-11-05 09:00","2025-11-05 18:00","2025-11-05 09:00","2025-11-05 18:00","연속"]
[824,"부산울산","울산","남울산처용#2 T/L"," 폴리머지지애자 설치공사","폴리머지지애자 설치 4기 : [8, 13, 14, 18]","2025-11-17 07:00","2025-11-18 18:00","2025-11-17 07:00","2025-11-18 18:00","연속"]
[825,"부산울산","울산","남울산처용#1 T/L"," 폴리머지지애자 설치공사","폴리머지지애자 설치공사 : [6]","2025-11-12 07:00","2025-11-12 18:00","2025-11-12 07:00","2025-11-12 18:00","연속"]
[826,"부산울산","울산","산하방어진#1 T/L"," 폴리머지지애자 및 추락방지장치(수평레일) 설치","ㅇ 폴리머지지애자 설치 4기 (No. 1, 6, 8, 16) 16은 병가구간(동울산-산하#2) ㅇ 수평레일 2기 (17, 18) 17, 18 는 병가구간(동울산-산하 #2)","2025-11-03 07:00","2025-11-04 18:00","2025-11-03 07:00","2025-11-04 18:00","연속"]
[827,"부산울산","울산","남울산성암#2 T/L","'24~'25년 울산전력 개폐장치 정밀점검공사","GIS 정밀점검 시험가압 1HR","2025-11-19 17:00","2025-11-19 18:00","2025-11-19 17:00","2025-11-19 18:00","연속"]
[828,"부산울산","울산","신울산웅촌#2 T/L","2025년 가공송전 순시점검 위탁공사"," 웅촌-서창#2T/L 정밀점검 안전이격","2025-11-17 09:00","2025-11-18 18:00","2025-11-17 09:00","2025-11-18 18:00","연속"]
[829,"부산울산","울산","신울산웅촌#1 T/L","2025년 가공송전 순시점검 위탁공사"," 웅촌-서창#1T/L 정밀점검 안전이격","2025-11-10 09:00","2025-11-11 18:00","2025-11-10 09:00","2025-11-11 18:00","연속"]
[830,"부산울산","울산","신울산언양#1 T/L","대동 등 5개 C/T PD 집합반 설치공사","신울산언양#1 T/L PD 집합반 설치공사","2025-11-19 09:00","2025-11-19 18:00","2025-11-19 09:00","2025-11-19 18:00","연속"]
[831,"부산울산","울산","신울산언양#2 T/L","대동 등 5개 C/T PD 집합반 설치공사","신울산언양#2 T/L PD 집합반 설치공사","2025-11-20 09:00","2025-11-20 18:00","2025-11-20 09:00","2025-11-20 18:00","연속"]
[832,"부산울산","울산","반천언양#1 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","애자교체 안전이격","2025-11-03 08:00","2025-11-03 17:00","2025-11-03 08:00","2025-11-03 17:00","연속"]
[833,"부산울산","울산","언양석계#2 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","애자교체 : No4","2025-11-03 08:00","2025-11-03 17:00","2025-11-03 08:00","2025-11-03 17:00","연속"]
[834,"부산울산","울산","옥동외동#1 T/L","옥동S/S  모선구분차단기 설치공사","GIS 설치 관련 감압 및 시험가압","2025-11-24 09:00","2025-11-29 18:00","2025-11-24 09:00","2025-11-29 18:00","연속"]
[835,"부산울산","울산","신온산온산#3 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-11-25 13:00","2025-11-25 16:00","2025-11-25 13:00","2025-11-25 16:00","연속"]
[836,"부산울산","울산","신온산온산#2 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-11-19 09:00","2025-11-19 13:00","2025-11-19 09:00","2025-11-19 13:00","연속"]
[837,"부산울산","울산","신온산온산#3 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-11-19 13:00","2025-11-19 16:00","2025-11-19 13:00","2025-11-19 16:00","연속"]
[838,"부산울산","울산","온산처용#2 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-11-14 16:00","2025-11-14 17:00","2025-11-14 16:00","2025-11-14 17:00","연속"]
[839,"부산울산","울산","신온산온산#1 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-11-11 08:30","2025-12-12 18:00","2025-11-11 08:30","2025-12-12 18:00","연속"]
[840,"부산울산","울산","온산처용#2 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-11-28 16:00","2025-11-29 16:00","2025-11-28 16:00","2025-11-29 16:00","연속"]
[841,"부산울산","울산","신온산온산#2 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-11-25 09:00","2025-11-25 13:00","2025-11-25 09:00","2025-11-25 13:00","연속"]
[842,"부산울산","울산","온산처용#2 T/L","온산S/S  장기사용 GIS 교체공사","신온산-온산#3T/L GIS 교체","2025-11-21 16:00","2025-11-22 16:00","2025-11-21 16:00","2025-11-22 16:00","연속"]
[843,"부산울산","울산","남울산용연#2 T/L"," 폴리머지지애자 설치공사","폴리머지지애자 1기 : [3]","2025-11-20 07:00","2025-11-20 18:00","2025-11-20 07:00","2025-11-20 18:00","연속"]
[844,"부산울산","울산","용연울산TP#3 T/L"," 폴리머지지애자 및 추락방지장치(수직) 설치","폴리머지지애자 2기 설치 : [2, 3] 추락방지장치(수직) 3기 설치 : [1, 2, 3]","2025-11-07 07:00","2025-11-07 18:00","2025-11-07 07:00","2025-11-07 18:00","연속"]
[845,"부산울산","울산","남울산용연#1 T/L"," 폴리머지지애자 설치공사","폴리머지지애자 1기 설치 (No.2)","2025-11-14 07:00","2025-11-14 18:00","2025-11-14 07:00","2025-11-14 18:00","연속"]
[846,"부산울산","울산","용연울산TP#1 T/L"," 폴리머지지애자 및 추락방지장치(수직) 설치공사","ㅇ 추락방지장치(수직) 설치 11기 [1, 2, 3, 4, 5, 6, 7, 8, 9, 9-1, 9-2] ㅇ 폴리머지지애자 설치 4기 (No. 2, 3, 6, 8, 9-1) 9-1은 병가구간","2025-11-10 07:00","2025-11-11 18:00","2025-11-10 07:00","2025-11-11 18:00","연속"]
[847,"부산울산","울산","용연울산TP#2 T/L"," 폴리머지지애자 및 추락방지장치(수직) 설치","ㅇ 추락방지장치(수직) 설치 11기 [1, 2, 3, 4, 5, 6, 7, 8, 9, 9-1, 9-2] ㅇ 폴리머지지애자 설치 4기 (No. 2, 9-1) 9-1은 병가구간","2025-11-10 07:00","2025-11-10 18:00","2025-11-10 07:00","2025-11-10 18:00","연속"]
[848,"부산울산","울산","울주S/S #1 EM.Tr CB","'24~'25년 울산전력 변전협력회사 총액공사","변압기 보통점검, 추락방지장치 설치. 보호반 DTCR 교체","2025-11-17 09:00","2025-11-18 18:00","2025-11-17 09:00","2025-11-18 18:00","연속"]
[849,"부산울산","울산","울주직동#1 T/L","345kV 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치( 울주-직동#1)","2025-11-25 07:00","2025-11-27 18:00","2025-11-25 07:00","2025-11-27 18:00","연속"]
[850,"부산울산","울산","울주직동#2 T/L","345kV 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치( 울주-직동#2)","2025-11-19 07:00","2025-11-22 18:00","2025-11-19 07:00","2025-11-22 18:00","연속"]
[851,"부산울산","울산","울주S/S #1 EM.Tr CB","'24~'25년 울산전력 변전협력회사 총액공사","1,2차 부싱절연유 채유","2025-11-14 09:00","2025-11-14 18:00","2025-11-14 09:00","2025-11-14 18:00","연속"]
[852,"부산울산","울산","신울산웅촌#2 T/L"," 폴리머지지애자 설치공사","ㅇ 폴리머지지애자 설치 3기 : [16, 17, 23]","2025-11-06 07:00","2025-11-06 18:00","2025-11-06 07:00","2025-11-06 18:00","연속"]
[853,"부산울산","울산","신울산웅촌#1 T/L"," 폴리머지지애자 설치공사","ㅇ 폴리머지지애자 설치 5기[2, 5, 17, 23, 28]","2025-11-04 07:00","2025-11-05 18:00","2025-11-04 07:00","2025-11-05 18:00","연속"]
[854,"부산울산","울산","직동반천#1 T/L","345kV 울주-고리NP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치( 직동-반천#1)","2025-11-24 07:00","2025-11-24 18:00","2025-11-24 07:00","2025-11-24 18:00","연속"]
[855,"부산울산","직할","수정범일#1 T/L","25년 하반기  GIS 정밀점검","범일S/S 6133 GIS 정밀점검","2025-11-05 16:00","2025-11-05 18:00","2025-11-05 16:00","2025-11-05 18:00","연속"]
[856,"부산울산","직할","수정범일#1 T/L","25년 하반기  GIS 정밀점검","범일S/S 6233 GIS 정밀점검","2025-11-07 16:00","2025-11-07 18:00","2025-11-07 16:00","2025-11-07 18:00","연속"]
[857,"부산울산","직할","수정범일#1 T/L","25년 하반기  GIS 정밀점검","범일S/S 6100 GIS 정밀점검","2025-11-11 16:00","2025-11-11 18:00","2025-11-11 16:00","2025-11-11 18:00","연속"]
[858,"경남","김해송변전부","김해어방#2 T/L","김해S/S 김해-어방#2T/L 혼용화공사","김해S/S 김해-어방#2T/L 혼용화공사","2025-11-29 09:00","2025-11-30 18:00","2025-11-29 09:00","2025-11-30 18:00","연속"]
[859,"경남","김해송변전부","대동매리#2 T/L","2024-2025년 북부산전력지사 가공송전협력회사 공사","SB댐퍼 설치 : No.9","2025-11-01 08:00","2025-11-01 17:00","2025-11-01 08:00","2025-11-01 17:00","연속"]
[860,"경남","김해송변전부","대동매리#1 T/L","2025년도 가공송전 순시점검 위탁회사","초기점검(No.19,20)","2025-11-08 08:00","2025-11-08 18:00","취소","취소","연속"]
[861,"경남","김해송변전부","매리김해#1 T/L","2025년도 가공송전 순시점검 위탁회사","초기점검(No.19,20)","2025-11-08 08:00","2025-11-08 18:00","취소","취소","연속"]
[862,"경남","김해송변전부","신김해주촌#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#2 T/L 항공구 설치공사","2025-11-29 07:00","2025-11-30 18:00","취소","취소","매일"]
[863,"경남","김해송변전부","신김해주촌#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#2 T/L 항공구 설치공사","2025-11-23 07:00","2025-11-23 18:00","취소","취소","매일"]
[864,"경남","김해송변전부","신김해주촌#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#2 T/L 항공구 설치공사","2025-11-16 07:00","2025-11-16 18:00","2025-11-16 07:00","2025-11-16 18:00","연속"]
[865,"경남","김해송변전부","신김해주촌#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#1 T/L 항공구 설치공사","2025-11-15 07:00","2025-11-15 18:00","2025-11-15 07:00","2025-11-15 18:00","연속"]
[866,"경남","김해송변전부","신김해주촌#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#1 T/L 항공구 설치공사","2025-11-09 07:00","2025-11-09 18:00","취소","취소","매일"]
[867,"경남","김해송변전부","신김해삼정#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사","수평추락방지장치 설치","2025-11-01 07:00","2025-11-02 18:00","2025-11-01 07:00","2025-11-02 18:00","매일"]
[868,"경남","김해송변전부","신김해주촌#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#1 T/L 항공구 설치공사","2025-11-01 07:00","2025-11-02 18:00","2025-11-01 07:00","2025-11-02 18:00","매일"]
[869,"경남","김해송변전부","주촌삼계#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#2 T/L 항공구 설치공사(안전이격)","2025-11-23 07:00","2025-11-23 18:00","취소","취소","매일"]
[870,"경남","김해송변전부","주촌삼계#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#1 T/L 항공구 설치공사(안전이격)","2025-11-15 07:00","2025-11-15 18:00","2025-11-15 07:00","2025-11-15 18:00","연속"]
[871,"경남","김해송변전부","주촌삼계#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#1 T/L 항공구 설치공사(안전이격)","2025-11-09 07:00","2025-11-09 18:00","취소","취소","매일"]
[872,"경남","김해송변전부","주촌삼계#2 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#1 T/L 항공구 설치공사(안전이격)","2025-11-02 07:00","2025-11-02 18:00","2025-11-02 07:00","2025-11-02 18:00","연속"]
[873,"경남","김해송변전부","주촌삼계#1 T/L","24~25년 경남본부 직할 송전협력회사 총액공사"," 신김해주촌#2 T/L 항공구 설치공사(안전이격)","2025-11-29 07:00","2025-11-30 18:00","취소","취소","매일"]
[874,"경남","김해송변전부","신김해진례#1 T/L"," 진례S/S #1M.Tr 증설공사"," 진례S/S #1M.Tr 증설공사","2025-11-29 11:00","2025-11-30 17:00","2025-11-29 11:00","2025-11-30 17:00","연속"]
[875,"경남","김해송변전부","신김해진례#1 T/L"," 진례S/S #1M.Tr 증설공사"," 진례S/S #1M.Tr 증설공사","2025-11-22 11:00","2025-11-23 14:00","2025-11-22 11:00","2025-11-23 14:00","연속"]
[876,"경남","김해송변전부","진영한림정#2 T/L"," 한림정 #4M.Tr 증설공사(모선구분 병행)","-  모선구분, #4M.Tr 증설 및 관련 154, 23kV GIS 증설 각 1식","2025-11-15 15:00","2025-11-15 17:00","취소","취소","연속"]
[877,"경남","김해송변전부","진영한림정#1 T/L"," 한림정 #4M.Tr 증설공사(모선구분 병행)","-  모선구분, #4M.Tr 증설 및 관련 154, 23kV GIS 증설 각 1식","2025-11-15 13:00","2025-11-15 15:00","취소","취소","연속"]
[878,"경남","김해송변전부","한림정S/S #60 BUS"," 한림정 #4M.Tr 증설공사(모선구분 병행)","-  모선구분, #4M.Tr 증설 및 관련 154, 23kV GIS 증설 각 1식","2025-11-09 18:00","2025-11-09 20:00","2025-11-09 18:00","2025-11-09 20:00","연속"]
[879,"경남","김해송변전부","한림정삼계#2 T/L"," 한림정 #4M.Tr 증설공사(모선구분 병행)","-  모선구분, #4M.Tr 증설 및 관련 154, 23kV GIS 증설 각 1식","2025-11-08 18:00","2025-11-09 20:00","2025-11-08 18:00","2025-11-09 20:00","연속"]
[880,"경남","김해송변전부","한림정삼계#2 T/L"," 한림정 #4M.Tr 증설공사(모선구분 병행)","-  모선구분, #4M.Tr 증설 및 관련 154, 23kV GIS 증설 각 1식","2025-11-02 18:00","2025-11-03 09:00","2025-11-02 18:00","2025-11-03 08:00","연속"]
[881,"경남","김해송변전부","한림정S/S #65 BUS"," 한림정 #4M.Tr 증설공사(모선구분 병행)","-  모선구분, #4M.Tr 증설 및 관련 154, 23kV GIS 증설 각 1식","2025-11-03 09:00","2025-11-09 18:00","2025-11-03 09:00","2025-11-09 18:00","연속"]
[882,"경남","김해송변전부","한림정삼계#2 T/L"," 한림정 #4M.Tr 증설공사(시험가압[1H])","단모선 운전 최소화용 엔드커버 시험가압(1H)","2025-11-03 09:00","2025-11-03 18:00","2025-11-03 09:00","2025-11-03 18:00","연속"]
[883,"경남","직할","녹공마천#2 T/L"," 녹공-마천#2T/L 지중송전 피뢰기 열화진단"," 녹공-마천#2T/L 지중송전 피뢰기 열화진단","2025-11-11 09:00","2025-11-11 18:00","2025-11-11 09:00","2025-11-11 18:00","연속"]
[884,"경남","직할","신마산의창#2 T/L"," 신마산-의창#2T/L 지중선로용 피뢰기 교체"," 신마산-의창#1, 2T/L 지중송전선로용 노후 피뢰기 교체 시행","2025-11-25 08:00","2025-11-25 18:00","취소","취소","연속"]
[885,"경남","직할","신마산의창#1 T/L"," 신마산-의창#1T/L 지중선로용 피뢰기 교체"," 신마산-의창#1, 2T/L 지중송전선로용 노후 피뢰기 교체 시행","2025-11-25 08:00","2025-11-25 18:00","취소","취소","연속"]
[886,"경남","진주","진주개양#2 T/L"," 진주-개양#2T/L 지중송전 EBA절연유 진단"," 진주-개양#2T/L 지중송전 EBA절연유 진단","2025-11-29 12:00","2025-11-30 18:00","취소","취소","매일"]
[887,"경남","진주","진주개양#1 T/L"," 진주-개양#1T/L 지중송전 EBA절연유 진단"," 진주-개양#1T/L 지중송전 EBA절연유 진단","2025-11-29 09:00","2025-11-30 12:00","취소","취소","매일"]
[888,"경남","진주","의령S/S SEC CB 60610","의령S/S #60-61, #65-66 SEC GIS 조작시험","의령S/S #60-61, #65-66 SEC GIS 조작시험","2025-11-03 10:00","2025-11-03 13:00","2025-11-03 10:00","2025-11-03 13:00","연속"]
[889,"경남","진주","의령동진주#1 T/L","의령S/S 의령-동진주#1,2T/L GIS 조작시험","의령S/S 의령-동진주#1,2T/L GIS 조작시험","2025-11-04 10:00","2025-11-04 13:00","취소","취소","연속"]
[890,"경남","진주","의령동진주#2 T/L","의령S/S 의령-동진주#1,2T/L GIS 조작시험","의령S/S 의령-동진주#1,2T/L GIS 조작시험","2025-11-04 13:00","2025-11-04 15:00","취소","취소","연속"]
[891,"경남","진주","의령S/S SEC CB 65660","의령S/S #60-61, #65-66 SEC GIS 조작시험","의령S/S #60-61, #65-66 SEC GIS 조작시험","2025-11-03 13:00","2025-11-03 15:00","2025-11-03 13:00","2025-11-03 15:00","연속"]
[892,"경남","진주","하동하동화력 T/L"," 하동-남해#2T/L 항공장애표시구 설치 관련 안전거리 확보"," 하동-남해#2T/L 항공장애표시구 설치 관련 안전거리 확보","2025-11-17 07:00","2025-11-19 18:00","2025-11-17 07:00","2025-11-19 18:00","매일"]
[893,"경남","진주","광양하동#1 T/L"," 광양-하동T/L 항공장애표시구 설치"," 광양-하동T/L 항공장애표시구 설치","2025-11-10 07:00","2025-11-12 18:00","취소","취소","매일"]
[894,"경남","진주","광양하동#2 T/L"," 광양-하동T/L 항공장애표시구 설치"," 광양-하동T/L 항공장애표시구 설치","2025-11-10 07:00","2025-11-12 18:00","취소","취소","매일"]
[895,"경남","진주","하동정촌#1 T/L"," 하동-개양#1T/L 항공장애표시구 설치"," 하동-개양#1T/L 항공장애표시구 설치","2025-11-22 07:00","2025-11-23 18:00","취소","취소","매일"]
[896,"경남","진주","하동정촌#2 T/L"," 하동-개양#2T/L 항공장애표시구 설치"," 하동-개양#2T/L 항공장애표시구 설치","2025-11-22 07:00","2025-11-23 18:00","취소","취소","매일"]
[897,"경남","진주","하동하동화력 T/L"," 하동-하동화력T/L 보호반 대체(하동,하동화력)"," 하동-하동화력T/L 보호반 대체(하동,하동화력)","2025-11-25 10:00","2025-11-27 18:00","2025-11-25 10:00","2025-11-27 18:00","연속"]
[898,"경남","진주","산청함양 T/L"," 산청-함양T/L 지중송전 피뢰기 열화진단"," 산청-함양T/L 지중송전 피뢰기 열화진단","2025-11-16 12:00","2025-11-16 18:00","취소","취소","연속"]
[899,"경남","진주","의령함양 T/L"," 의령-함양T/L 지중송전 피뢰기 열화진단"," 의령-함양T/L 지중송전 피뢰기 열화진단","2025-11-16 09:00","2025-11-16 12:00","취소","취소","연속"]
[900,"경남","진주","거창합천#1 T/L","합천S/S 거창-합천#1T/L GIS 보통점검 등","합천S/S 거창-합천#1T/L GIS 보통 및 LA(A,B,C) 보통, PT 하자 [병행, 거창] 거창-합천#1T/L GIS 조작시험 및 하자점검","2025-11-12 11:00","2025-11-12 18:00","2025-11-12 11:00","2025-11-12 18:00","연속"]
[901,"경남","진주","쌍림합천#1 T/L","합천S/S 쌍림-합천#1T/L GIS 조작, LA 하자, PT 대체","합천S/S 쌍림-합천#1T/L GIS 조작, LA(A,B,C) 하자, PT 대체","2025-11-24 10:00","2025-11-24 17:00","2025-11-24 10:00","2025-11-24 17:00","연속"]
[902,"경남","통영","신고성거류#3 T/L"," 신고성-거류#3T/L 추락방지장치 설치공사"," 신고성-거류#3T/L 추락방지장치 설치공사","2025-11-17 07:00","2025-11-21 18:00","2025-11-17 07:00","2025-11-21 18:00","매일"]
[903,"경남","통영","거류통영#2 T/L"," 거류-통영#2T/L 추락방지장치 설치공사"," 거류-통영#2T/L 추락방지장치 설치공사","2025-11-29 07:00","2025-11-30 18:00","2025-11-29 07:00","2025-11-30 18:00","매일"]
[904,"경남","통영","거류통영#1 T/L"," 거류-통영#1T/L 추락방지장치 설치공사"," 거류-통영#1T/L 추락방지장치 설치공사","2025-11-22 07:00","2025-11-23 18:00","2025-11-22 07:00","2025-11-23 18:00","매일"]
[905,"경남","통영","거류거제#2 T/L"," 거류-거제#2T/L 추락방지장치 설치공사"," 거류-거제#2T/L 추락방지장치 설치공사","2025-11-01 07:00","2025-11-02 18:00","2025-11-01 07:00","2025-11-02 18:00","매일"]
[906,"경남","통영","통영거제#1 T/L"," 통영-거제#1T/L 지중송전 피뢰기 열화진단"," 통영-거제#1T/L 지중송전 피뢰기 열화진단","2025-11-15 09:00","2025-11-15 12:00","2025-11-15 09:00","2025-11-15 12:00","연속"]
[907,"경남","통영","통영거제#2 T/L"," 통영-거제#2T/L 지중송전 피뢰기 열화진단"," 통영-거제#2T/L 지중송전 피뢰기 열화진단","2025-11-15 12:00","2025-11-15 18:00","2025-11-15 12:00","2025-11-15 18:00","연속"]
[908,"경남","통영","거류거제#1 T/L"," 거류-거제#1T/L 추락방지장치 설치공사"," 거류-거제#1T/L 추락방지장치 설치공사","2025-11-08 07:00","2025-11-09 18:00","2025-11-08 07:00","2025-11-09 18:00","매일"]
[909,"경남","통영","사천개양#1 T/L"," 사천-개양T/L 애자세정작업"," 사천-개양T/L 애자세정작업(74~86호 회선 수평배열로 휴전 필요)","2025-11-09 07:00","2025-11-09 18:00","2025-11-09 07:00","2025-11-09 18:00","연속"]
[910,"경남","통영","삼천포사천#2 T/L"," 삼천포-사천T/L 애자세정작업 및 성능저하지지애자 교체","13일 :  삼천포-사천T/L 애자세정작업 14일 :  삼천포-사천#2T/L 성능저하지지애자 교체","2025-11-08 07:00","2025-11-09 18:00","2025-11-08 07:00","2025-11-09 18:00","매일"]
[911,"경남","통영","삼천포사천#2 T/L","삼천포SS 등  삼천포-사천#2T/L 송전선로 보호반 교체","삼천포SS, 사천SS  삼천포-사천#2T/L 송전선로 보호반 교체","2025-11-29 09:30","2025-11-30 18:00","2025-11-29 09:30","2025-11-30 18:00","연속"]
[912,"경남","통영","신고성고성 T/L"," 신고성고성 T/L추락방지장치 설치공사"," 신고성고성 T/L추락방지장치 설치공사","2025-11-24 07:00","2025-11-28 18:00","2025-11-24 07:00","2025-11-28 18:00","매일"]
[913,"경남","통영","진동안정#2 T/L","진동SS, 안정SS  진동-안정#2T/L 송전선로 보호반 교체","진동SS, 안정SS  진동-안정#2T/L 송전선로 보호반 교체","2025-11-22 09:30","2025-11-23 18:00","2025-11-22 09:30","2025-11-23 18:00","연속"]
[914,"경남","통영","진동안정#1 T/L","진동SS, 안정SS  진동-안정#1T/L 송전선로 보호반 교체","진동SS, 안정SS  진동-안정#1T/L 송전선로 보호반 교체","2025-11-15 09:30","2025-11-16 18:00","취소","취소","연속"]
[915,"경남","함안","서마산진동#2 T/L","항공장애구 설치공사","서마산-진동T/L 17~18호 구간(2조 7개 설치) - 백색 3EA","2025-11-16 12:00","2025-11-16 18:00","취소","취소","연속"]
[916,"경남","함안","서마산진동#1 T/L","항공장애구 설치공사","서마산-진동T/L 17~18호 구간(2조 7개 설치) - 적색 4EA","2025-11-16 07:00","2025-11-16 12:00","취소","취소","연속"]
[917,"경남","함안","신마산중리#1 T/L","항공장애구 설치공사","신마산-마산T/L 4~5호 구간(2조 9개 설치) - 백색 4EA","2025-11-15 12:00","2025-11-15 18:00","2025-11-15 12:00","2025-11-15 18:00","연속"]
[918,"경남","함안","신마산마산#1 T/L","항공장애구 설치공사","신마산-마산T/L 4~5호 구간(2조 9개 설치) - 적색 5EA","2025-11-15 07:00","2025-11-15 12:00","취소","취소","연속"]
[919,"경남","함안","신마산마산#2 T/L","항공장애구 설치공사","신마산-마산T/L 4~5호 구간(2조 9개 설치) - 적색 5EA","2025-11-15 07:00","2025-11-15 12:00","취소","취소","연속"]
[920,"경남","함안","신마산중리#2 T/L","항공장애구 설치공사","신마산-마산T/L 4~5호 구간(2조 9개 설치) - 백색 4EA","2025-11-15 12:00","2025-11-15 18:00","2025-11-15 12:00","2025-11-15 18:00","연속"]
[921,"경남","함안","중리가야#2 T/L"," 중리-가야T/L 철탑 현장실측용역"," 중리-가야T/L 8호 등 6기 안전도 기술검토 이후 부재보강 공사를 위한 현장 실측용역 시행","2025-11-04 07:00","2025-11-04 18:00","2025-11-04 07:00","2025-11-04 18:00","연속"]
[922,"경남","함안","중리가야#1 T/L"," 중리-가야T/L 철탑 현장실측용역"," 중리-가야T/L 8호 등 6기 안전도 기술검토 이후 부재보강 공사를 위한 현장 실측용역 시행","2025-11-03 07:00","2025-11-03 18:00","2025-11-03 07:00","2025-11-03 18:00","연속"]
[923,"경남","함안","초동밀양#1 T/L"," 초동-밀양T/L 항공구 설치 철탑 보강 및 OPGW 교체공사"," 초동-밀양T/L 9호 등 5기 철탑보강[함안전력] 및 6-2호~16호 OPGW 교체공사[직할 전자제어]","2025-11-22 07:00","2025-11-25 18:00","2025-11-22 07:00","2025-11-25 18:00","연속"]
[924,"경남","함안","초동밀양#2 T/L"," 초동-밀양T/L 항공구 설치 철탑 보강 및 OPGW 교체공사"," 초동-밀양T/L 9호 등 5기 철탑보강[함안전력] 및 6-2호~16호 OPGW 교체공사[직할 전자제어]","2025-11-19 07:00","2025-11-23 18:00","2025-11-19 07:00","2025-11-23 18:00","연속"]