{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":21,"n_cols":12,"rows_kept":21,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2025년도 12월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"대전세종충남","서산","당진T/P CB 8971","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 당진화력S/S 765kV 8971(B) CB 유압력계 교체","2025-12-10 09:30","2025-12-10 18:00","2025-12-10 09:30","2025-12-10 18:00","연속"]
[2,"대전세종충남","서산","당진T/P CB 8900","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 당진화력S/S 765kV 8900(C) CB 유압력계 교체","2025-12-09 09:30","2025-12-09 18:00","2025-12-09 09:30","2025-12-09 18:00","연속"]
{"$rows_empty":14}
[{"$nulls":5}," "]

{"sheet":"345설비","index":1,"n_rows":218,"n_cols":12,"rows_kept":218,"cut":false,"hidden":false,"merged":[[2,2,3,2],[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9]]}
["2025년도 12월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","동서울","동서울S/S #1 Sh.R CB","24-25년도 동서울전력지사 변전협력회사 총액공사","동서울S/S #1Sh.R 정밀점검","2025-12-08 09:00","2025-12-19 18:00","2025-12-01 09:00","2025-12-12 18:00","연속"]
[2,"남서울","동서울","동서울S/S #2 Sh.R CB","24-25년도 동서울전력지사 변전협력회사 총액공사","동서울S/S #2Sh.R 인출CB(7079) 정밀점검","2025-12-03 09:00","2025-12-05 18:00","2025-12-18 09:00","2025-12-20 18:00","연속"]
[3,"남서울","영등포","신광명S/S #70 BUS"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-12-07 09:00","2025-12-30 18:00","2025-12-07 09:00","2025-12-30 18:00","연속"]
[4,"남서울","영등포","서서울신광명#1 T/L"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사","2025-12-07 09:00","2026-01-31 18:00","2025-12-07 09:00","2026-01-31 18:00","연속"]
[5,"남서울","영등포","신광명S/S SEC CB 70710"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사 1식","2025-12-07 09:00","2025-12-30 18:00","2025-12-07 09:00","2025-12-30 18:00","연속"]
[6,"남서울","영등포","신광명S/S #71 BUS"," 신광명S/S GIS 대체 및 S/W 증설공사","-  63kA GIS 27CB 설치 - 기타 부대공사 1식","2025-12-07 09:00","2025-12-30 18:00","2025-12-31 09:00","2025-01-31 18:00","연속"]
[7,"남서울","직할","신문래S/S CB 7271","362kV GIS 보통점검(7271)","362kV GIS 보통점검(7271)","2025-12-04 09:00","2025-12-04 18:00","2025-12-04 09:00","2025-12-04 18:00","연속"]
[8,"남서울","직할","신문래S/S CB 7171","362kV GIS 보통점검(7171)","362kV GIS 보통점검(7171)","2025-12-03 09:00","2025-12-03 18:00","2025-12-03 09:00","2025-12-03 18:00","연속"]
[9,"남서울","직할","신문래S/S CB 7100","362kV GIS 보통점검 공사(7100)","362kV GIS 보통점검 공사(7100)","2025-12-05 09:00","2025-12-05 18:00","2025-12-05 09:00","2025-12-05 18:00","연속"]
[10,"남서울","직할","신문래S/S #3 Sh.R CB"," 다빈도 개폐장치 정밀점검공사"," 다빈도 개폐장치 정밀점검공사","2025-12-15 09:00","2025-12-19 18:00","2025-12-15 09:00","2025-12-19 18:00","연속"]
[11,"인천","김포","가정개폐소 #1 Sh.R CB","가정개폐소  #1 Sh.R 1차 GIS 정밀점검","가정개폐소  #1 Sh.R 1차 GIS 정밀점검","2025-12-15 09:00","2025-12-19 18:00","2025-12-15 09:00","2025-12-19 18:00","연속"]
[12,"인천","김포","가정개폐소 SEC CB 75760","가정개폐소  #75-#76 SEC GIS 정밀점검","가정개폐소  #75-#76 SEC GIS 정밀점검","2025-12-08 09:00","2025-12-12 18:00","취소","취소","연속"]
[13,"인천","김포","가정개폐소 SEC CB 70710","가정개폐소  #70-#71 SEC GIS 정밀점검","가정개폐소  #70-#71 SEC GIS 정밀점검","2025-12-01 09:00","2025-12-05 18:00","취소","취소","연속"]
[14,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S #4M.Tr 보통점검","신가좌S/S #4M.Tr 보통점검","2025-12-08 09:00","2025-12-12 18:00","취소","취소","연속"]
[15,"인천","부평","신경서S/S #3 M.Tr","신경서S/S  #3 M.Tr 1차 7572 GIS 보통점검","신경서S/S  #3 M.Tr 1차 7572 GIS 보통점검","2025-12-02 09:00","2025-12-02 18:00","취소","취소","연속"]
[16,"인천","부평","신경서S/S #2 M.Tr","신경서S/S  #2 M.Tr 1차 7272 GIS 보통점검","신경서S/S  #2 M.Tr 1차 7272 GIS 보통점검","2025-12-01 09:00","2025-12-01 18:00","취소","취소","연속"]
[17,"인천","김포","가정개폐소 #3 Sh.R CB","2025년 가정개폐소 노후 무인보안 시스템 교체공사","○ 2025년 가정개폐소 노후 무인보안 시스템 교체공사 - 근거 : 김포전(전자)-1225(2025.8.19) - 내용 : #3 Sh.R실 카메라 및 카메라 리프트 장치 시설 교체","2025-12-08 09:00","2025-12-08 18:00","2025-12-08 09:00","2025-12-08 18:00","연속"]
[18,"인천","김포","가정개폐소 #2 Sh.R CB","2025년 가정개폐소 노후 무인보안 시스템 교체공사","○ 2025년 가정개폐소 노후 무인보안 시스템 교체공사 - 근거 : 김포전(전자)-1225(2025.8.19) - 내용 : #2 Sh.R실 카메라 및 카메라 리프트 장치 시설 교체","2025-12-05 09:00","2025-12-05 18:00","2025-12-05 09:00","2025-12-05 18:00","연속"]
[19,"인천","김포","신김포S/S #2 M.Tr","신김포S/S  #2M.Tr 추락방지 안전장치 설치","신김포S/S  #2M.Tr 추락방지 안전장치 설치","2025-12-02 10:00","2025-12-02 18:00","취소","취소","연속"]
[20,"인천","김포","신김포S/S #3 M.Tr","신김포S/S  #3M.Tr 추락방지 안전장치 설치","신김포S/S  #3M.Tr 추락방지 안전장치 설치","2025-12-03 10:00","2025-12-03 18:00","취소","취소","연속"]
[21,"인천","김포","신김포S/S #2 Sh.R CB","신김포S/S  #2Sh.R 추락방지 안전장치 설치","신김포S/S  #2Sh.R 추락방지 안전장치 설치","2025-12-04 10:00","2025-12-04 18:00","취소","취소","연속"]
[22,"인천","김포","신김포S/S #4 Sh.R CB","신김포S/S  #4Sh.R 추락방지 안전장치 설치","신김포S/S  #4Sh.R 추락방지 안전장치 설치","2025-12-05 10:00","2025-12-05 18:00","취소","취소","연속"]
[23,"인천","김포","신김포S/S #1 M.Tr","신김포S/S  #1M.Tr 추락방지 안전장치 설치","신김포S/S  #1M.Tr 추락방지 안전장치 설치","2025-12-01 10:00","2025-12-01 18:00","취소","취소","연속"]
[24,"경기북부","고양","신파주S/S SVC TR CB","신파주 SVC 냉각설비 보통점검","□ 신파주 SVC 냉각설비 보통점검 ○ 점검대상 : 냉각 SKID 2식 ○ 점검내용 - 열교환기 점검 - 냉각설비 SKID 외관점검 - 냉각설비 소모품 교체","2025-12-01 09:00","2025-12-03 18:00","2025-12-01 09:00","2025-12-03 18:00","연속"]
[25,"경기북부","구리","신가평S/S #70 BUS","신가평S/S  #70BUS 벨로우즈 교체","신가평S/S  #70BUS 벨로우즈 교체(4EA)","2025-12-22 09:00","2026-01-09 18:00","2025-12-22 09:00","2026-01-09 18:00","연속"]
[26,"경기북부","직할","양주중부#1 T/L"," 양주S/S 동두천CC-양주T/L SW 및 CLR 설치공사"," 스위치 증설 2대","2025-12-19 09:00","2025-12-19 18:00","2025-12-19 09:00","2025-12-19 18:00","연속"]
[27,"경기북부","직할","신파주양주#1 T/L"," 양주S/S 동두천CC-양주T/L SW 및 CLR 설치공사"," 스위치 증설 2대","2025-12-18 09:00","2025-12-18 18:00","2025-12-18 09:00","2025-12-18 18:00","연속"]
[28,"경기북부","직할","양주S/S CB 7700","양주S/S OPGW 연계 광케이블 교체공사"," STACOM 감시실~ ICT실 1조 및 OPGW 연계 광케이블 6조 교체","2025-12-16 09:00","2025-12-18 18:00","2025-12-16 09:00","2025-12-18 18:00","연속"]
[29,"경기북부","직할","양주S/S CB 7771","양주S/S OPGW 연계 광케이블 교체공사"," STACOM 감시실~ ICT실 1조 및 OPGW 연계 광케이블 6조 교체","2025-12-16 09:00","2025-12-18 18:00","2025-12-16 09:00","2025-12-18 18:00","연속"]
[30,"경기","군포","신안산S/S #4 M.Tr","신안산S/S #4M.Tr 7322DS부 Gas 누기개소 점검 및 보수","신안산S/S #4M.Tr 7322DS부 Gas 누기개소 점검 및 보수","2025-12-01 09:00","2025-12-05 18:00","2025-12-01 09:00","2025-12-05 18:00","연속"]
[31,"경기","동부","곤지암여주복합#1 T/L","곤지암S/S 곤지암-여주복합#1,2T/L GIS 조작시험","[곤지암-여주복합#1T/L] 곤지암:7200(조작),7271(조작) [곤지암-여주복합#2T/L] 곤지암:7171(조작)","2025-12-02 07:00","2025-12-02 08:00","2025-12-02 07:00","2025-12-02 08:00","연속"]
[32,"경기","동부","곤지암S/S CB 7171","곤지암S/S 곤지암-여주복합#2T/L GIS 조작시험","[곤지암-여주복합#2T/L] 곤지암:7171(조작)","2025-12-03 07:00","2025-12-03 09:00","2025-12-03 07:00","2025-12-03 09:00","연속"]
[33,"경기","동부","곤지암S/S CB 7200","곤지암S/S 곤지암-여주복합#1,2T/L GIS 조작시험","[곤지암-여주복합#1T/L] 곤지암:7200(조작),7271(조작) [곤지암-여주복합#2T/L] 곤지암:7171(조작)","2025-12-02 08:00","2025-12-02 09:00","2025-12-02 08:00","2025-12-02 09:00","연속"]
[34,"경기","동부","여주C/C CB 7171","여주CC 362kV GIS 7171","여주CC 362kV GIS 7171 * 조작함 히터설치","2025-12-09 09:00","2025-12-09 18:00","2025-12-09 09:00","2025-12-09 18:00","연속"]
[35,"경기","동부","신충주여주복합#2 T/L","추락방지장치 설치공사(신충주여주복합#2T/L)","신충주여주복합#2T/L 추락방지장치 설치 39기","2025-12-02 07:00","2025-12-05 18:00","2025-12-03 07:00","2025-12-05 18:00","연속"]
[36,"경기","동부","여주C/C CB 7100","여주CC 362kV GIS 7100","여주CC 362kV GIS 7100 * 조작함 히터설치","2025-12-08 09:00","2025-12-08 18:00","2025-12-08 09:00","2025-12-08 18:00","연속"]
[37,"경기","성남","신수원S/S #2 M.Tr","신수원S/S 154kV 계통조정공사(토목)"," #2M.Tr용 신규GIB 기초작업(토목) (작업시 안전이격용 휴전필요)","2025-12-01 09:00","2025-12-14 18:00","2025-12-01 09:00","2025-12-14 18:00","연속"]
[38,"경기","평택","신안성서안성#1 T/L","T/L PT저전압 경보용 MCB 교체","T/L PT저전압 경보용 MCB 교체","2025-12-08 09:00","2025-12-08 18:00","2025-12-08 09:00","2025-12-08 18:00","연속"]
[39,"경기","평택","고덕#2S/S #4 M.Tr","고덕#2S/S #4M.Tr 예방진단시스템 설치","예방진단시스템 설치","2025-12-18 09:00","2025-12-18 18:00","2025-12-18 09:00","2025-12-18 18:00","연속"]
[40,"경기","평택","고덕#2S/S #3 M.Tr","고덕#2S/S #3M.Tr 추락방지장치 시공","#3M.Tr 추락방지장치 시공","2025-12-02 09:00","2025-12-02 18:00","2025-12-02 09:00","2025-12-02 18:00","연속"]
[41,"경기","평택","서안성S/S CB 7600","M.Tr 보통, 정밀점검 공사(서안성S/S 7600)","서안성S/S  7600 GIS 코일, 히터교체","2025-12-03 09:00","2025-12-03 18:00","2025-12-03 09:00","2025-12-03 18:00","연속"]
[42,"경기","평택","평택T/P CB 7871","2025년 평택변전협력 총액공사(평택화력 7871)","7871 CB 유압조작기(C상) 점검","2025-12-04 09:00","2025-12-04 18:00","2025-12-04 09:00","2025-12-04 18:00","연속"]
[43,"강원","강릉","신양양S/S CB 7500","신양양S/S STATCOM 변환설비 설치공사","신양양 STATCOM 부하시험","2025-12-08 10:00","2025-12-31 18:00","2025-12-08 10:00","2025-12-31 18:00","연속"]
[44,"강원","강릉","신양양S/S CB 7572","신양양S/S STATCOM용  GIS 설치공사","신양양 STATCOM용 C.Tr 및 GIS 사용전검사","2025-12-03 13:00","2025-12-05 18:00","2025-12-03 13:00","2025-12-05 18:00","연속"]
[45,"강원","강릉","신양양S/S CB 7500","신양양S/S STATCOM용  GIS 설치공사","신양양 STATCOM용 C.Tr 및 GIS 사용전검사","2025-12-03 13:00","2025-12-05 18:00","2025-12-03 13:00","2025-12-05 18:00","연속"]
[46,"강원","강릉","신양양S/S CB 7572","신양양S/S STATCOM 변환설비 설치공사","신양양 STATCOM 부하시험","2025-12-08 10:00","2025-12-31 18:00","2025-12-08 10:00","2025-12-31 18:00","연속"]
[47,"강원","동해","동해S/S CB 7671","2024∼2025년 동해전력지사 변전협력회사 공사","차단기 공압탱크 드레인밸브 위치조정","2025-12-04 09:00","2025-12-04 13:00","2025-12-04 09:00","2025-12-04 13:00","연속"]
[48,"강원","동해","동해S/S CB 7672","2024∼2025년 동해전력지사 변전협력회사 공사","차단기 공압탱크 드레인밸브 위치조정","2025-12-03 09:00","2025-12-03 13:00","2025-12-03 09:00","2025-12-03 13:00","연속"]
[49,"강원","동해","동해S/S CB 7600","2024∼2025년 동해전력지사 변전협력회사 공사","차단기 공압탱크 드레인밸브 위치조정","2025-12-03 13:00","2025-12-03 18:00","2025-12-03 13:00","2025-12-03 18:00","연속"]
[50,"강원","동해","동해S/S #1 M.Tr","2024~25년 동해전력지사 변전협력회사 총액공사","변압기 보호반 대체","2025-12-03 09:00","2025-12-05 18:00","2025-12-03 09:00","2025-12-05 18:00","연속"]
[51,"강원","태백","신태백한울NP#1 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 신태백-한울NP2 #1 T/L 수평추락방지장치 및 폴리머 점퍼지지애자 설치","2025-12-01 09:00","2025-12-07 18:00","취소","취소","매일"]
[52,"충북","충주","신제천S/S #4 M.Tr","25년 충주전력지사 362,170kV GIS 보통점검공사","신제천S/S 154kV #4M.Tr 2차 GIS 보통점검","2025-12-01 09:00","2025-12-01 17:00","2025-12-01 09:00","2025-12-01 17:00","연속"]
[53,"충북","충주","신충주S/S #2 BUS","신충주S/S  #75BUS 모선보호반 대체","신충주S/S  #75BUS 모선보호반 대체","2025-12-01 09:00","2025-12-05 18:00","2025-12-01 09:00","2025-12-05 18:00","연속"]
[54,"충북","충주","신충주S/S #2 M.Tr","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S 154kV #2M.Tr 2차 GIS 보통점검","2025-12-04 09:00","2025-12-04 17:00","2025-12-04 09:00","2025-12-04 17:00","연속"]
[55,"충북","충주","신충주S/S #1 M.Tr","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S 154kV #1M.Tr 2차 GIS 보통점검","2025-12-03 09:00","2025-12-03 17:00","2025-12-03 09:00","2025-12-03 17:00","연속"]
[56,"충북","충주","신충주T신충주 T/L"," 신용인-동서울 등 16개 T/L 추락방지장치 설치공사"," 신제천-여주CC T/L 추락방지장치 설치공사 - 신제천-여주CC 연계선로로 인한 휴전(신충주 T분기 실작업 없음)","2025-12-08 07:00","2025-12-10 18:00","취소","취소","연속"]
[57,"충북","충주","신충주S/S #4 M.Tr","25년 충주전력지사 362,170kV GIS 보통점검공사","신충주S/S 154kV #4M.Tr 2차 GIS 보통점검","2025-12-05 09:00","2025-12-05 17:00","2025-12-05 09:00","2025-12-05 17:00","연속"]
[58,"대전세종충남","대전","신옥천신계룡 T/L"," 신옥천-신계룡T/L 지장수목전지 및 벌채"," 신옥천-신계룡T/L 지장수목전지 및 벌채","2025-12-22 09:00","2025-12-23 18:00","취소","취소","매일"]
[59,"대전세종충남","서산","당진T/P CB 7171","당진화력S/S  차단기 조작시험","(즉시가압 가능)당진T/P #71 M.Tr 1차 7171 CB 개폐타임 측정 및 조작시험","2025-12-04 16:00","2025-12-04 18:00","2025-12-04 16:00","2025-12-04 18:00","연속"]
[60,"대전세종충남","서산","당진T/P CB 7100","당진화력S/S  차단기 조작시험","(즉시가압 가능)당진T/P #71 M.Tr 1차-1호기 1차 7100 CB 개폐타임 측정 및 조작시험","2025-12-05 16:00","2025-12-05 18:00","2025-12-05 16:00","2025-12-05 18:00","연속"]
[61,"대전세종충남","서산","당진T/P CB 7300","당진화력S/S  차단기 조작시험","(12월 12일 #72 변압기 휴전 취소시)당진T/P #72M.Tr 1차 - TIE 7300 CB 개폐타임 측정 및 조작시험","2025-12-12 16:00","2025-12-12 18:00","2025-12-12 16:00","2025-12-12 18:00","연속"]
[62,"대전세종충남","서산","당진T/P CB 7371","당진화력S/S  차단기 조작시험","(12월 12일 #72 변압기 휴전 취소시)당진T/P #72M.Tr 1차 7371 CB 개폐타임 측정 및 조작시험","2025-12-11 16:00","2025-12-11 18:00","2025-12-11 16:00","2025-12-11 18:00","연속"]
[63,"대전세종충남","서산","북당진현대제철 T/L"," 신송산분기T/L 건설공사","No.70 전선 이동(가철탑→본철탑) No.69∼No.71 전선 교체","2025-12-13 07:00","2025-12-24 18:00","취소","취소","연속"]
[64,"대전세종충남","서산","신당진개폐소북당진 T/L"," 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 신당진개폐소-북당진T/L No.49~65 총 17기) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-12-22 08:00","2025-12-23 18:00","취소","취소","매일"]
[65,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~126(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 교차선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청 * 11월 휴전 승인시 취소 요청","2025-12-07 05:00","2025-12-07 10:00","취소","취소","연속"]
[66,"대전세종충남","서산","신당진개폐소현대제철 T/L"," 신송산분기T/L 건설공사","No.70 전선 이동(가철탑→본철탑) No.69∼No.71 전선 교체","2025-12-01 07:00","2025-12-12 18:00","취소","취소","연속"]
[67,"대전세종충남","서산","신당진개폐소태안TP#1 T/L","24~25 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-현대제철T/L 병가선로,  신당진개폐소-현대제철T/L 휴전 미승인시 휴전 취소 요청 * 11월 휴전 승인시 취소 요청","2025-12-06 08:00","2025-12-06 18:00","2025-12-06 08:00","2025-12-06 18:00","연속"]
[68,"대전세종충남","서산","신당진개폐소북당진 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.126~127(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 병가선로,  신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청 * 11월 휴전 승인시 취소 요청","2025-12-07 10:00","2025-12-07 18:00","취소","취소","연속"]
[69,"대전세종충남","서산","신당진개폐소현대제철 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#1T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#1T/L 병가선로,  신당진개폐소-태안화력#1T/L 휴전 미승인시 휴전 취소 요청 * 11월 휴전 승인시 취소 요청","2025-12-06 08:00","2025-12-06 18:00","취소","취소","연속"]
[70,"대전세종충남","서산","신당진개폐소태안TP#2 T/L","24~25년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.125~127(2경간) *즉시가압가능(20분이내) * 신당진개폐소-북당진T/L 병가 및  신당진개폐소-현대제철 교차구간,  신당진개폐소-북당진T/L 및 신당진개폐소-현대제철 모두 휴전 미승인시 휴전 취소 요청 * 11월 휴전 승인시 취소 요청","2025-12-07 05:00","2025-12-07 18:00","2025-12-07 05:00","2025-12-07 18:00","연속"]
[71,"대전세종충남","서산","신당진S/S #2 M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신당진S/S  #2M.Tr 보호반 교체","2025-12-08 09:00","2025-12-12 18:00","2025-12-08 09:00","2025-12-12 18:00","연속"]
[72,"대전세종충남","서산","신당진S/S SEC CB 75760","신당진S/S  차단기 조작시험","(11월 휴전 취소시)(즉시가압 가능)신당진S/S  #75-#76 SEC 75-76-0CB 개폐타임 측정 및 조작시험","2025-12-15 09:00","2025-12-15 18:00","2025-12-15 09:00","2025-12-15 18:00","연속"]
[73,"대전세종충남","서산","신당진S/S SEC CB 70710","신당진S/S  차단기 조작시험","(11월 휴전 취소시)(즉시가압 가능)신당진S/S  #70-#71 SEC 70-71-0CB 개폐타임 측정 및 조작시험","2025-12-15 09:00","2025-12-15 18:00","2025-12-15 09:00","2025-12-15 18:00","연속"]
[74,"대전세종충남","서산","신당진S/S CB 7771","신당진S/S  차단기 조작시험","(11월 취소시)(즉시가압 가능)신당진S/S  신당진-연락#2T/L 7771CB 개폐타임 측정 및 조작시험","2025-12-09 09:00","2025-12-09 18:00","2025-12-09 09:00","2025-12-09 18:00","연속"]
[75,"대전세종충남","서산","신당진S/S CB 7700","신당진S/S  차단기 조작시험","(11월 휴전 취소시)(즉시가압 가능)신당진S/S  신당진연락#2-신서산#2T/L 7700CB 개폐타임 측정 및 조작시험","2025-12-09 09:00","2025-12-09 18:00","2025-12-09 09:00","2025-12-09 18:00","연속"]
[76,"대전세종충남","서산","신당진S/S CB 7471","신당진S/S  차단기 조작시험","(즉시가압 가능)신당진S/S  신당진-연락#1T/L 7471CB 개폐타임 측정 및 조작시험","2025-12-05 09:00","2025-12-05 18:00","2025-12-05 09:00","2025-12-05 18:00","연속"]
[77,"대전세종충남","서산","신당진S/S #3 M.Tr","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 신당진S/S  #3M.Tr B상 1차 LA 보수 및 96P 오동작 방지Ry 교체","2025-12-03 09:30","2025-12-03 18:00","2025-12-03 09:30","2025-12-03 18:00","연속"]
[78,"대전세종충남","서산","신서산아산#1 T/L"," 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 신서산-아산#1T/L No.1~5, 32~46 총 20기) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-12-15 08:00","2025-12-16 18:00","2025-12-15 08:00","2025-12-16 18:00","매일"]
[79,"대전세종충남","서산","신서산S/S #5 Sh.R CB","신서산S/S  차단기 조작시험","(11월 휴전 취소시)(즉시가압 가능)신서산S/S  #5Sh.R 7979CB 개폐타임 측정 및 조작시험","2025-12-08 09:00","2025-12-08 18:00","2025-12-08 09:00","2025-12-08 18:00","연속"]
[80,"대전세종충남","서산","신서산태안TP#1 T/L"," 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 신서산-태안화력#1T/L No.2~59,61~70, 72~83 총 80기) , 즉시가압(20분 이내) 가능","2025-12-22 08:00","2025-12-27 18:00","2025-12-22 08:00","2025-12-27 18:00","매일"]
[81,"대전세종충남","서산","신서산아산#2 T/L"," 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 신서산-아산#2T/L No.1~5, 32~46 총 20기) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-12-17 08:00","2025-12-18 18:00","2025-12-17 08:00","2025-12-18 18:00","매일"]
[82,"대전세종충남","서산","신서산신당진#2 T/L","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신서산S/S #77Bay B/F반, #4Sh.R 보호반 교체","2025-12-01 09:00","2025-12-05 18:00","취소","취소","연속"]
[83,"대전세종충남","서산","신서산S/S #4 Sh.R CB","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압불가) 신서산S/S #77Bay B/F반, #4Sh.R 보호반 교체","2025-12-01 09:00","2025-12-05 18:00","취소","취소","연속"]
[84,"대전세종충남","서산","신서산태안TP#2 T/L"," 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 신서산-태안화력#2T/L No.2~59, 61~70, 72~83 총 80기) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-12-01 08:00","2025-12-05 18:00","2025-12-01 08:00","2025-12-05 18:00","매일"]
[85,"대전세종충남","서산","태안T/P CB 7572","24-25년 서산P/O 변전협력회사 총액공사","(즉시가압가능) 태안화력S/S  7572(A) CB 유압력계 교체","2025-12-02 09:30","2025-12-02 18:00","2025-12-02 09:30","2025-12-02 18:00","연속"]
[86,"대전세종충남","천안","신온양S/S #3 M.Tr","(10,11월 취소시) 25년 천안PO 주변압기 정밀 및 보통점검 공사","신온양S/S  #3M.Tr 보통점검","2025-12-01 09:00","2025-12-03 18:00","취소","취소","연속"]
[87,"대전세종충남","천안","신온양S/S #2 M.Tr","'25년 천안P/O GIS 정밀 및 보통점검 공사","(11월 취소시) 신온양S/S 154kV #4Sh.C 1차 GIS 정밀점검 진행 시 이격거리 관련 병행 휴전 필요","2025-12-08 09:00","2025-12-10 18:00","취소","취소","연속"]
[88,"대전세종충남","천안","신온양S/S CB 7971","'25년 천안P/O GIS 정밀 및 보통점검 공사","(B/F보호반대체 취소시_즉시가압가능) 신온양S/S  신온양-신탕정#1T/L GIS 보통점검","2025-12-18 09:00","2025-12-18 18:00","2025-12-18 09:00","2025-12-18 18:00","연속"]
[89,"대전세종충남","천안","신온양S/S #2 M.Tr","신온양S/S  #2M.Tr 부싱절연유 채유","(11월 취소시)(즉시가압가능)신온양S/S  #2M.Tr 부싱절연유 채유","2025-12-01 09:00","2025-12-01 18:00","취소","취소","연속"]
[90,"대전세종충남","천안","신온양S/S #4 M.Tr","신온양S/S  #4M.Tr 부싱절연유 채유","(11월 취소시)(즉시가압가능)신온양S/S  #4M.Tr 부싱절연유 채유","2025-12-03 09:00","2025-12-03 18:00","취소","취소","연속"]
[91,"대전세종충남","천안","신온양S/S CB 7671","'25년 천안P/O GIS 정밀 및 보통점검 공사","(B/F보호반대체 취소시_즉시가압가능) 신온양S/S  신온양-서서울#1T/L GIS 보통점검","2025-12-16 09:00","2025-12-16 18:00","2025-12-16 09:00","2025-12-16 18:00","연속"]
[92,"대전세종충남","천안","신온양S/S CB 7771","'25년 천안P/O GIS 정밀 및 보통점검 공사","(B/F보호반대체 취소시_즉시가압가능) 신온양S/S  신온양-서서울#2T/L GIS 보통점검","2025-12-17 09:00","2025-12-17 18:00","2025-12-17 09:00","2025-12-17 18:00","연속"]
[93,"대전세종충남","천안","아산S/S CB 7172","(즉시가압가능)아산S/S  7172 CB 개폐타임 측정","(11월 취소시)(즉시가압가능)아산S/S  아산-보령화력#2T/L 7172 CB 개폐타임측정","2025-12-01 09:00","2025-12-01 14:00","취소","취소","연속"]
[94,"대전세종충남","천안","아산S/S #1 M.Tr","(10,11월 취소시) 25년 천안PO 주변압기 정밀 및 보통점검 공사","아산S/S  #1M.Tr 보통점검","2025-12-01 09:00","2025-12-03 18:00","취소","취소","연속"]
[95,"대전세종충남","천안","아산S/S CB 7271","(즉시가압가능)아산S/S  7271 CB 개폐타임 측정","(11월 취소시)아산S/S 아산-화성 #2T/L 7271 CB 개폐타임측정","2025-12-01 14:00","2025-12-01 18:00","취소","취소","연속"]
[96,"대전세종충남","천안","아산S/S #3 M.Tr","(10,11월 취소시) 25년 천안PO 주변압기 정밀 및 보통점검 공사","아산S/S  #3M.Tr 보통점검","2025-12-04 09:00","2025-12-05 18:00","취소","취소","연속"]
[97,"대전세종충남","천안","아산S/S CB 7400","(즉시가압가능)아산S/S  7400 CB 개폐타임 측정","(11월 취소시)아산S/S  아산-화성#1T/L-TIE 7400 CB 개폐타임 측정","2025-12-02 09:00","2025-12-02 18:00","취소","취소","연속"]
[98,"대전세종충남","청양","보령C/C CB 7100","[11월취소시][변전총액] 청양P/O 변전협력 총액공사","362kV GIS 보통점검","2025-12-09 09:00","2025-12-09 18:00","취소","취소","연속"]
[99,"대전세종충남","청양","보령C/C CB 7172","[11월취소시][변전총액] 청양P/O 변전협력 총액공사","362kV GIS 보통점검","2025-12-10 09:00","2025-12-10 18:00","취소","취소","연속"]
[100,"대전세종충남","청양","청양보령TP#1 T/L","[송전][즉시가압O] 아산-보령 등 4개T/L 항공구 설치공사"," 청양-보령화력#1T/L 항공구 설치공사","2025-12-11 08:00","2025-12-12 18:00","취소","취소","매일"]
[101,"대전세종충남","청양","보령T/P CB 7672","[11월취소시][변전총액] 청양P/O 변전협력 총액공사","362kV GIS 보통점검","2025-12-11 09:00","2025-12-11 18:00","2025-12-11 09:00","2025-12-11 18:00","연속"]
[102,"대전세종충남","청양","아산보령TP#2 T/L","[송전][즉시가압O] 아산-보령 등 4개T/L 항공구 설치공사"," 아산-보령화력#2T/L 항공구 설치공사","2025-12-08 08:00","2025-12-10 18:00","취소","취소","매일"]
[103,"대전세종충남","청양","신옥천청양 T/L","[송전][즉시가압O] 신옥천-청양T/L SB댐퍼 교체공사","[즉시가압O] 신옥천-청양T/L SB댐퍼 교체공사","2025-12-08 07:00","2025-12-12 18:00","취소","취소","매일"]
[104,"대전세종충남","청양","청양보령TP#2 T/L","[11월취소시][변전총액] 청양P/O 변전협력 총액공사"," GIS 차단기 전자변 교체 및 CVT 보통점검","2025-12-15 09:00","2025-12-15 18:00","취소","취소","연속"]
[105,"대전세종충남","청양","청양S/S #1 M.Tr","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  #1M.Tr 1,2차 부싱 절연유 채유","2025-12-09 09:00","2025-12-09 18:00","2025-12-09 09:00","2025-12-09 18:00","연속"]
[106,"대전세종충남","청양","청양S/S CB 7571","[11월취소시][변전총액] 청양P/O 변전협력 총액공사","362kV GIS 차단기 조작시험","2025-12-12 08:30","2025-12-12 10:00","2025-12-12 08:30","2025-12-12 10:00","연속"]
[107,"대전세종충남","청양","청양보령CC T/L","[11월취소시][변전총액] 청양P/O 변전협력 총액공사"," LA, CVT 보통점검","2025-12-04 09:00","2025-12-04 18:00","취소","취소","연속"]
[108,"대전세종충남","청양","청양신보령TP T/L","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  청양-신보령화력 T/L 차단기(7271) 조작시험 및 CVT 교체","2025-12-03 09:00","2025-12-03 18:00","취소","취소","연속"]
[109,"대전세종충남","청양","청양S/S SEC CB 75760","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  #75-#76 SEC GIS 차단기 조작시험 (75-76-0)","2025-12-16 08:30","2025-12-16 10:00","2025-12-16 08:30","2025-12-16 10:00","연속"]
[110,"대전세종충남","청양","청양S/S SEC CB 70710","[변전총액] 청양P/O 변전협력 총액공사","청양S/S  #70-#71 SEC GIS 차단기 조작시험 (70-71-0)","2025-12-16 07:00","2025-12-16 08:30","2025-12-16 07:00","2025-12-16 08:30","연속"]
[111,"대전세종충남","청양","신옥천청양 T/L"," 신옥천-청양T/L 지장수목전지 및 벌채"," 신옥천-청양T/L 지장수목전지 및 벌채","2025-12-01 09:00","2025-12-02 18:00","취소","취소","매일"]
[112,"대전세종충남","청양","신옥천청양 T/L","[송전][즉시가압O] 신옥천-청양등8개T/L 추락방지설치공사","[송전][즉시가압O] 신옥천-청양 등 8개T/L 추락방지 설치공사","2025-12-01 07:00","2025-12-05 18:00","취소","취소","매일"]
[113,"전북","군산","군산신김제#2 T/L","'25년 군산전력지사 가공송전협력회사공사","1.  군산-신김제T/L No.55~56 항공장애표시구 교체공사 ※ 바람에 의한 항공장애표시구 소음으로 인한 민원 해결 필요 2.  군산-신김제#2T/L 조류착지 방지장치 설치(68기)","2025-12-26 07:00","2025-12-26 18:00","2025-12-26 07:00","2025-12-26 18:00","매일"]
[114,"전북","군산","군산S/S CB 7500","군산P/O  차단기 보통점검 (중복)","○ 7500 CB 보통점검","2025-12-08 09:00","2025-12-08 18:00","2025-12-08 09:00","2025-12-08 18:00","연속"]
[115,"전북","군산","군산S/S CB 7600","25년 유사고장 재발방지관련 절연열화 측정"," 2점절 균압콘덴서 차단기","2025-12-19 09:00","2025-12-19 15:00","2025-12-19 09:00","2025-12-19 15:00","연속"]
[116,"전북","군산","군산S/S CB 7672","25년 유사고장 재발방지관련 절연열화 측정"," 2점절 균압콘덴서 차단기","2025-12-19 09:00","2025-12-19 15:00","2025-12-19 09:00","2025-12-19 15:00","연속"]
[117,"전북","군산","군산S/S #3 M.Tr","군산P/O 154kV 이상 주변압기 부싱유 채유공사","주변압기 부싱유 채유공사","2025-12-05 09:00","2025-12-05 18:00","2025-12-05 09:00","2025-12-05 18:00","연속"]
[118,"전북","군산","새만금S/S CB 7300","24~25년 군산P/O 변전협력회사 총액공사","전자변 교체공사(7300)","2025-12-15 09:00","2025-12-15 18:00","2025-12-15 09:00","2025-12-15 18:00","연속"]
[119,"전북","군산","새만금S/S CB 7371","24~25년 군산P/O 변전협력회사 총액공사","전자변 교체공사(7371)","2025-12-26 09:00","2025-12-26 18:00","2025-12-26 09:00","2025-12-26 18:00","연속"]
[120,"전북","직할","신남원한빛NP#1 T/L"," 신남원-한빛T/L 전선접속개소 전력선교체공사(계속)","○ 전력선 및 가공지선 교체 : No.198~199, 217~218","2025-12-15 08:00","2025-12-19 18:00","2025-12-15 08:00","2025-12-19 18:00","연속"]
[121,"전북","직할","신옥천신남원#1 T/L"," 신옥천-신남원 등 3개T/L 수평 추락방지시설 설치공사(계속)"," 신옥천-신남원#1T/L 1~178호","2025-12-22 07:30","2026-01-04 17:00","취소","취소","매일"]
[122,"광주전남","강진","신강진광양#1 T/L","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-12-01 08:00","2025-12-12 18:00","취소","취소","연속"]
[123,"광주전남","강진","신강진S/S #3 M.Tr","'24~25년 강진전력지사 변전협력회사 공사","신강진S/S  74Bay B/F반 교체","2025-12-01 08:00","2025-12-12 18:00","취소","취소","연속"]
[124,"광주전남","강진","신강진S/S #2 M.Tr","2024-2025년 강진전력지사 변전협력회사 공사","-신강진S/S #2M.Tr 1차,2차 NGK 부싱절연유 채유 (가스 분석 결과 수치초과로 인한 추적분석) ※ 거래소 요청 시 휴전일정 협의 가능","2025-12-02 08:00","2025-12-02 18:00","2025-12-02 08:00","2025-12-02 18:00","연속"]
[125,"광주전남","광주","신광주S/S #2 M.Tr","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  #2M.Tr GIS 2차 보통점검","2025-12-19 09:00","2025-12-19 18:00","취소","취소","연속"]
[126,"광주전남","광주","신광주S/S CB 7171","'24~25년 광주전력지사 변전협력회사 공사","신광주S/S 7171 CB 조작시험","2025-12-03 09:00","2025-12-03 18:00","2025-12-03 09:00","2025-12-03 18:00","연속"]
[127,"광주전남","광주","신광주S/S #3 M.Tr","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  #3M.Tr GIS 2차 보통점검","2025-12-17 09:00","2025-12-17 18:00","취소","취소","연속"]
[128,"광주전남","광주","신광주한빛NP#2 T/L","신광주변전소 72BAY BF반 대체","신광주변전소 72BAY BF반 대체","2025-12-15 09:00","2025-12-19 18:00","취소","취소","연속"]
[129,"광주전남","광주","신광주S/S CB 7600","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-12-15 08:00","2025-12-15 18:00","취소","취소","연속"]
[130,"광주전남","광주","신광주S/S CB 7672","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-12-15 08:00","2025-12-15 18:00","취소","취소","연속"]
[131,"광주전남","광주","신광주S/S CB 7600","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2025-12-15 08:00","2025-12-15 18:00","취소","취소","연속"]
[132,"광주전남","광주","신남원신광주#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#1T/L 116~164호","2025-12-15 08:00","2025-12-19 18:00","취소","취소","매일"]
[133,"광주전남","광주","신남원신광주#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 조류착지방지장치 설치 시행 - 신남원-신광주#2T/L 116~164호","2025-12-22 08:00","2025-12-26 18:00","취소","취소","매일"]
[134,"광주전남","광주","신광주S/S CB 7471","'24~25년 광주전력지사 변전협력회사 공사","7471 CB 조작시험","2025-12-02 09:00","2025-12-02 18:00","2025-12-02 09:00","2025-12-02 18:00","연속"]
[135,"광주전남","광주","신광주S/S #2 M.Tr","'25년 광주전력지사 변전협력회사 공사","신광주S/S #2M.Tr 초기점검, 1차 GIS 조작시험, 2차 GIS 보통점검 1,3차 PT 초기점검, 1,2,3차 LA 보통점검, 2-1,2 Sh.R 보통점검","2025-12-02 09:00","2025-12-05 18:00","취소","취소","연속"]
[136,"광주전남","광주","신광주S/S #1 M.Tr","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 신광주S/S  #1M.Tr GIS 2차 보통점검","2025-12-18 09:00","2025-12-18 18:00","취소","취소","연속"]
[137,"광주전남","광주","신화순S/S CB 7971","24~25년 광주전력지사 변전협력회사 공사","7971CB 차단기 조작시험","2025-12-11 09:00","2025-12-11 18:00","2025-12-11 09:00","2025-12-11 18:00","연속"]
[138,"광주전남","광주","신화순S/S #3 M.Tr","신화순변전소 75BAY BF반 대체","신화순변전소 75BAY BF반 대체","2025-12-15 09:00","2025-12-19 18:00","취소","취소","연속"]
[139,"광주전남","광주","신화순S/S #1 M.Tr","주변압기 부싱 절연유 채유","주변압기 부싱 절연유 채유 - 1,2차 A,B,C상","2025-12-01 09:00","2025-12-01 18:00","취소","취소","연속"]
[140,"광주전남","광주","신화순S/S CB 7900","24~25년 광주전력지사 변전협력회사 공사","7900CB 차단기 조작시험","2025-12-10 09:00","2025-12-10 18:00","2025-12-10 09:00","2025-12-10 18:00","연속"]
[141,"광주전남","광주","신화순S/S #2 M.Tr","주변압기 부싱 절연유 채유","주변압기 부싱 절연유 채유 - 1,2차 A,B,C상","2025-12-02 09:00","2025-12-02 18:00","취소","취소","연속"]
[142,"광주전남","광주","신화순S/S CB 7972","'24~25년도 광주전력지사 변전협력회사 공사","#1M.Tr 1차 7972CB 차단기 동작특성시험","2025-12-01 09:00","2025-12-01 18:00","2025-12-01 09:00","2025-12-01 18:00","연속"]
[143,"광주전남","순천","광양CC여수TP#2 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #2T/L 폴리머점퍼지지애자 설치","2025-12-15 07:00","2025-12-19 18:00","취소","취소","매일"]
[144,"광주전남","순천","광양CC여수TP#1 T/L"," 광양CC-여수TP T/L 폴리머점퍼지지애자 설치공사","광양CC-여수TP #1T/L 폴리머점퍼지지애자 설치","2025-12-02 07:00","2025-12-12 18:00","취소","취소","매일"]
[145,"광주전남","순천","광양광양CC#2 T/L"," 광양-광양CC T/L 폴리머점퍼지지애자 설치공사","광양-광양CC #2T/L 폴리머점퍼지지애자 설치(휴일작업포함)","2025-12-22 07:00","2025-12-26 18:00","2025-12-22 07:00","2025-12-26 18:00","매일"]
[146,"광주전남","순천","광양율촌CC T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가) (휴일작업포함, 1시간내 가압가능)","2025-12-17 07:00","2025-12-31 18:00","취소","취소","매일"]
[147,"광주전남","순천","신강진광양#2 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","#2T/L 수평추락방지시설 설치 (휴일작업포함, 1시간내 가압가능)","2025-12-17 07:00","2025-12-31 18:00","취소","취소","매일"]
[148,"광주전남","순천","신남원광양#2 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양2, 광양-율촌CC 병가) (휴일작업포함, 1시간내 가압가능)","2025-12-17 07:00","2025-12-31 18:00","취소","취소","매일"]
[149,"광주전남","순천","광양광양CC#1 T/L"," 광양-광양CC T/L 폴리머점퍼지지애자 설치공사","광양-광양CC #1T/L 폴리머점퍼지지애자 설치","2025-12-15 07:00","2025-12-19 18:00","2025-12-15 07:00","2025-12-19 18:00","매일"]
[150,"광주전남","순천","광양하동TP#1 T/L"," 광양-하동TP T/L 폴리머점퍼지지애자 설치공사","#1T/L 폴리머점퍼지지애자 설치","2025-12-15 07:00","2025-12-19 18:00","취소","취소","매일"]
[151,"광주전남","순천","광양S/S #1 M.Tr","#1M.Tr 3차 DS 과열조치","#1M.Tr 3차 DS 과열조치","2025-12-09 08:30","2025-12-09 18:30","2025-12-09 08:30","2025-12-09 18:30","연속"]
[152,"광주전남","순천","신강진광양#1 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","#1T/L 수평추락방지시설 설치 (휴일작업포함, 1시간내 가압가능)","2025-12-02 07:00","2025-12-16 18:00","취소","취소","매일"]
[153,"광주전남","순천","광양S/S #1 M.Tr","25년 순천전력지사 부싱절연유 채유","25년 순천전력지사 부싱절연유 채유","2025-12-08 08:00","2025-12-08 18:00","2025-12-08 08:00","2025-12-08 18:00","연속"]
[154,"광주전남","순천","광양하동TP#2 T/L"," 광양-하동TP T/L 추락방지시설 설치공사","수평추락방지시설 설치 (1시간내 가압가능)","2025-12-08 07:00","2025-12-12 18:00","취소","취소","매일"]
[155,"광주전남","순천","신남원광양#1 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가) (휴일작업포함, 1시간내 가압가능)","2025-12-02 07:00","2025-12-16 18:00","취소","취소","매일"]
[156,"광주전남","순천","광양여수TP T/L"," 신남원-광양 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (신남원-광양1, 광양-여수TP 병가) (휴일작업포함, 1시간내 가압가능)","2025-12-02 07:00","2025-12-16 18:00","취소","취소","매일"]
[157,"광주전남","순천","여수T/P #2 M.Tr","#2M.Tr 3차 DS 과열조치","#2M.Tr 3차 DS 과열조치","2025-12-08 09:00","2025-12-09 18:00","2025-12-08 09:00","2025-12-09 18:00","연속"]
[158,"광주전남","순천","여수T/P #1 M.Tr","#1M.Tr 1차 부싱 대체","#1M.Tr 1차 부싱 대체","2025-12-01 09:00","2025-12-05 18:00","2025-12-01 09:00","2025-12-05 18:00","연속"]
[159,"대구","달성","고령의령#2 T/L","24~25년 달성전력지사 송전협력회사공사","24~25년 달성전력지사 송전협력회사공사 12.01 고령-의령#2T/L 148호 2번선 점퍼선 및 스페이서 교체 12.02 155~156호 소도체 이도조정","2025-12-10 08:00","2025-12-11 18:00","취소","취소","연속"]
[160,"대구","달성","고령의령#1 T/L"," 고령-의령 등 4개T/L 피뢰기 및 조류착지방지장치 설치공사"," 고령-의령#1T/L 피뢰기 및 조류착지방지장치 설치 - 주말간 환원(12/06~07)","2025-12-01 07:00","2025-12-05 18:00","취소","취소","연속"]
[161,"대구","달성","고령의령#1 T/L","고령SS 고령-의령#1T/L PT,LA 보통점검","고령SS 고령-의령#1T/L PT,LA 보통점검","2025-12-08 09:00","2025-12-08 18:00","취소","취소","연속"]
[162,"대구","달성","서대구고령#1 T/L","24~25년 달성전력지사 송전협력회사공사(안전확보)","24~25년 달성전력지사 송전협력회사공사 고령-의령#2T/L 155~156호 소도체 이도조정 관련 안전확보","2025-12-02 08:00","2025-12-02 18:00","2025-12-11 08:00","2025-12-11 18:00","연속"]
[163,"대구","포항","신포항신월성NP#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","신월성S/Y 보호반 계전기 정정","2025-12-03 14:00","2025-12-03 18:00","2025-12-03 14:00","2025-12-03 18:00","연속"]
[164,"대구","포항","신포항신월성NP#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","신월성S/Y 보호반 계전기 정정","2025-12-03 09:00","2025-12-03 14:00","2025-12-03 09:00","2025-12-03 14:00","연속"]
[165,"대구","포항","신포항S/S #1 M.Tr","신포항S/S #5M.Tr 증설공사(일반도급)","#5M.Tr 증설관련 모선 및 가공지선 설치","2025-12-17 09:00","2025-12-19 18:00","2025-12-17 09:00","2025-12-19 18:00","연속"]
[166,"대구","포항","신포항S/S #2 M.Tr","신포항S/S #5M.Tr 증설공사(일반도급)","#5M.Tr 증설공사관련 안전이격거리 확보","2025-12-07 09:00","2025-12-08 18:00","2025-12-07 09:00","2025-12-08 18:00","연속"]
[167,"대구","포항","신포항신월성NP#4 T/L","154kV 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 신포항-신월성NP#4T/L 추락방지장치 설치","2025-12-02 07:00","2025-12-09 18:00","취소","취소","연속"]
[168,"경북","영주","신영주S/S CB 7271","2025년 영주전력지사  GIS 정밀점검공사","-7271CB GIS 정밀점검","2025-12-08 09:00","2025-12-10 19:00","2025-12-08 09:00","2025-12-10 19:00","연속"]
[169,"경북","영주","신영주S/S #1 BUS","2025년 영주전력지사  GIS 정밀점검공사","-7271CB 정밀점검 후 #1BUS 이용 무부하가압","2025-12-10 15:00","2025-12-10 18:00","2025-12-10 15:00","2025-12-10 18:00","연속"]
[170,"경북","영주","신영주S/S CB 7171","2025년 영주전력지사  GIS 정밀점검공사","7171CB GIS 정밀점검","2025-12-11 09:00","2025-12-13 19:00","2025-12-11 09:00","2025-12-13 19:00","연속"]
[171,"경북","영주","신영주S/S #1 BUS","2025년 영주전력지사  GIS 정밀점검공사","-7171CB 정밀점검 후 #1BUS 이용 무부하가압","2025-12-13 09:00","2025-12-13 18:00","2025-12-13 09:00","2025-12-13 18:00","연속"]
[172,"경북","영주","신영주S/S CB 7200","2025년 영주전력지사  GIS 정밀점검공사","-7200CB GIS 정밀점검","2025-12-15 09:00","2025-12-17 19:00","2025-12-15 09:00","2025-12-17 19:00","연속"]
[173,"경북","영주","신영주S/S #2 BUS","2025년 영주전력지사  GIS 정밀점검공사","-7200CB 정밀점검 후 #2BUS 이용 무부하가압","2025-12-17 09:00","2025-12-17 18:00","2025-12-17 09:00","2025-12-17 18:00","연속"]
[174,"경북","영주","신영주S/S CB 7371","2025년 영주전력지사  GIS 정밀점검공사","-7371CB GIS 정밀점검","2025-12-18 09:00","2025-12-21 18:00","2025-12-18 09:00","2025-12-21 18:00","연속"]
[175,"경북","영주","신영주청송PP T/L","2025년 영주전력지사  GIS 정밀점검공사","-7371CB 정밀점검 후 신영주-청송PP TL 이용 무부하가압","2025-12-21 14:00","2025-12-21 18:00","2025-12-21 14:00","2025-12-21 18:00","연속"]
[176,"경북","영주","신영주S/S CB 7300","2025년 영주전력지사  GIS 정밀점검공사","-7300CB GIS 정밀점검","2025-12-24 09:00","2025-12-27 18:00","2025-12-24 09:00","2025-12-27 18:00","연속"]
[177,"경북","영주","신영주청송PP T/L","2025년 영주전력지사  GIS 정밀점검공사","-7300CB 정밀점검 후 신영주-청송PP TL 이용 무부하가압","2025-12-27 14:00","2025-12-27 18:00","2025-12-27 14:00","2025-12-27 18:00","연속"]
[178,"경북","직할","신영주청송PP T/L"," 청송분기T/L 불량애자 교체공사","-  신영주-청송PP T/L 불량애자 교체","2025-12-29 09:00","2026-01-19 18:00","2025-12-29 09:00","2026-01-19 18:00","연속"]
[179,"부산울산","동부산","신양산S/S #1 M.Tr","신양산S/S #1M.Tr 부싱절연유 채유","신양산S/S #1M.Tr 부싱절연유 채유","2025-12-06 09:00","2025-12-06 12:00","취소","취소","연속"]
[180,"부산울산","동부산","신양산S/S #3 M.Tr","신양산S/S #3M.Tr 1차 GIS 초기점검 및 부싱절연유 채유","신양산S/S #3M.Tr 1차 GIS 초기점검 및 부싱절연유 채유","2025-12-06 13:00","2025-12-06 18:00","취소","취소","연속"]
[181,"부산울산","동부산","신양산S/S #4 M.Tr","신양산S/S #4M.Tr 1차 GIS 초기점검","신양산S/S #4M.Tr 1차 GIS 초기점검","2025-12-07 09:00","2025-12-07 18:00","취소","취소","연속"]
[182,"부산울산","북부산","북부산S/S #76 BUS","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S  76BUS PRO 대체공사","2025-12-01 09:00","2025-12-04 18:00","2025-12-01 09:00","2025-12-04 18:00","연속"]
[183,"부산울산","북부산","북부산S/S SEC CB 70710","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S  70-71,75-76 B/F PNL 대체","2025-12-01 09:00","2025-12-04 18:00","2025-12-01 09:00","2025-12-04 18:00","연속"]
[184,"부산울산","북부산","북부산S/S #3 M.Tr","24-25 북부산 변전협력회사 총액공사","북부산S/S #3M.Tr 변압기 부싱절연유채유","2025-12-05 09:00","2025-12-05 18:00","2025-12-05 09:00","2025-12-05 18:00","연속"]
[185,"부산울산","북부산","북부산S/S CB 7A00","북부산 STATCOM 초기점검","북부산 STATCOM 초기점검","2025-12-02 09:00","2025-12-31 18:00","취소","취소","연속"]
[186,"부산울산","북부산","북부산S/S #1 M.Tr","24-25 북부산 변전협력회사 총액공사","북부산S/S #1M.Tr 변압기 추락방지 장치 설치","2025-12-08 09:00","2025-12-08 18:00","2025-12-08 09:00","2025-12-08 18:00","연속"]
[187,"부산울산","북부산","북부산S/S SEC CB 75760","24-25년 북부산전력지사 변전협력회사 공사","북부산S/S  70-71,75-76 B/F PNL 대체","2025-12-01 09:00","2025-12-04 18:00","2025-12-01 09:00","2025-12-04 18:00","연속"]
[188,"부산울산","북부산","북부산S/S CB 7A71","북부산 STATCOM 초기점검","북부산 STATCOM 초기점검","2025-12-02 09:00","2025-12-31 18:00","취소","취소","연속"]
[189,"부산울산","서부산","신김해신녹산#2 T/L","2024~2025년 서부산전력지사 가공송전협력회사 공사","고정형 폴리머 지지애자 설치","2025-12-03 08:00","2025-12-04 18:00","2025-12-03 08:00","2025-12-04 18:00","연속"]
[190,"부산울산","서부산","신김해신녹산#1 T/L","2024~2025년 서부산전력지사 가공송전협력회사 공사","고정형 폴리머 지지애자 설치","2025-12-01 08:00","2025-12-02 18:00","2025-12-01 08:00","2025-12-02 18:00","연속"]
[191,"부산울산","울산","동울산신울산 T/L","2024-2025년 울산전력지사 가공송전협력회사 공사","1.  동울산-신울산T/L 가공지선 및 금구류 교체 ○ 구간 : No.116~118 ○ 감독 : 송전부 배형석(18107520) 2.  동울산-신울산T/L 지반변위 감시용 CCTV 가공지선 보조 전원설치 ○ 구간 : No.29 ○ 감독 : 북울산전력부 송전팀 김대우(15104091)","2025-12-01 08:00","2025-12-05 18:00","2025-12-01 08:00","2025-12-05 18:00","연속"]
[192,"부산울산","울산","신온산S/S #3 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","- 1, 2차 부싱절연유 채유 - 변압기 추락방지장치 설치 - 보호반 DTCR 교체 - 현대제 차단기 유압조작기 체크밸브 설치(하자)(7500,7572)","2025-12-01 09:00","2025-12-01 18:00","2025-12-01 09:00","2025-12-01 18:00","연속"]
[193,"부산울산","울산","신온산남울산#2 T/L"," 신온산-남울산 #2T/L 폴리머지지애자 설치공사","○ 폴리머지지애자 6기 병가(온산-처용 #1) : 22, 25, 29 병가X : 3, 5, 7","2025-12-22 07:00","2025-12-24 18:00","2025-12-22 07:00","2025-12-24 18:00","연속"]
[194,"부산울산","울산","신온산S/S #1 M.Tr","'24~'25년 울산전력 변전협력회사 총액공사","- 현대제 차단기 유압조작기 체크밸브 설치(하자)(7200, 7272)","2025-12-02 09:00","2025-12-02 18:00","2025-12-02 09:00","2025-12-02 18:00","연속"]
[195,"부산울산","울산","신온산남울산#1 T/L"," 신온산-남울산 #1T/L 폴리머지지애자 설치공사","○폴리머지지애자 설치 7기 병가 : (남울산-신울산 #2 : 19, 21) / (온산-처용 #2 : 23, 24, 28) 병가 X : 2, 16","2025-12-17 07:00","2025-12-19 18:00","2025-12-17 07:00","2025-12-19 18:00","연속"]
[196,"부산울산","울산","신울산S/S CB 7A72","신울산S/S STATCOM 설치사업","-. STATCOM HMI 수정 작업","2025-12-01 09:00","2025-12-05 18:00","취소","취소","연속"]
[197,"부산울산","울산","신울산S/S #4 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#4M.Tr) 3회선구간 관로 1차 터파기 및 가시설","2025-12-20 09:00","2025-12-31 18:00","2025-12-20 09:00","2025-12-31 18:00","연속"]
[198,"부산울산","울산","신울산S/S #3 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#3M.Tr) 3회선구간 관로 가시설 및 그라우팅","2025-12-06 09:00","2025-12-20 18:00","2025-12-06 09:00","2025-12-20 18:00","연속"]
[199,"부산울산","울산","울주S/S #2 BUS"," 울주S/S 장기사용 GIS 교체공사","울주S/S 7A Bay 장기사용 GIS 교체","2025-12-19 08:00","2025-12-19 13:00","2025-12-19 08:00","2025-12-19 14:00","연속"]
[200,"부산울산","울산","울주신경산#1 T/L"," 울주S/S 장기사용 GIS 교체공사","울주S/S 7A Bay 장기사용 GIS 교체(시험가압선로)","2025-12-19 08:00","2025-12-20 18:00","2025-12-19 08:00","2025-12-20 19:00","연속"]
[201,"부산울산","울산","울주S/S #1 BUS"," 울주S/S 장기사용 GIS 교체공사","울주S/S 7A Bay 장기사용 GIS 교체","2025-12-19 13:00","2025-12-20 18:00","2025-12-19 14:00","2025-12-20 19:00","연속"]
[202,"경남","김해송변전부","신김해S/S #4 M.Tr","신김해S/S 154kV Sh.C 대체공사 (안전이격)","신김해S/S 154kV Sh.C 대체공사 (안전이격) - 대상선로 : 신김해S/S 신김해-신녹산#2T/L, #4M.Tr","2025-12-13 07:00","2025-12-14 20:00","2025-12-13 07:00","2025-12-14 20:00","연속"]
[203,"경남","김해송변전부","신김해신녹산#2 T/L","신김해S/S 154kV Sh.C 대체공사 (안전이격)","신김해S/S 154kV Sh.C 대체공사 (안전이격) - 대상선로 : 신김해S/S 신김해-신녹산#2T/L","2025-12-06 07:00","2025-12-07 20:00","2025-12-06 07:00","2025-12-07 20:00","연속"]
[204,"경남","김해송변전부","신김해신녹산#2 T/L","신김해S/S 154kV Sh.C 대체공사 (안전이격)","신김해S/S 154kV Sh.C 대체공사 (안전이격) - 대상선로 : 신김해S/S 신김해-신녹산#2T/L, #4M.Tr","2025-12-13 07:00","2025-12-14 20:00","2025-12-13 07:00","2025-12-14 20:00","연속"]
[205,"경남","진주","의령신마산#2 T/L","의령S/S 의령-신마산#2T/L LA 하자 및 PT 보통","의령S/S 의령-신마산#2T/L LA(A,B,C) 하자 및 PT(A,B,C) 보통","2025-12-04 09:00","2025-12-04 16:00","2025-12-04 09:00","2025-12-04 16:00","연속"]
[206,"경남","진주","의령신마산#1 T/L","의령S/S 의령-신마산#1T/L LA 하자","의령S/S 의령-신마산#2T/L LA(A,B,C) 하자","2025-12-04 16:00","2025-12-04 18:00","2025-12-04 16:00","2025-12-04 18:00","연속"]
[207,"경남","진주","고령의령#2 T/L"," 고령-의령#1T/L 철탑 수평 추락방지장치 설치공사"," 고령-의령#1T/L 39호 등 48기 와이어형 수평 추락방지장치 설치공사","2025-12-08 07:00","2025-12-14 18:00","취소","취소","매일"]
[208,"경남","진주","신남원의령#1 T/L","의령S/S 신남원-의령#1T/L LA 하자 및 PT 하자","의령S/S 신남원-의령#1T/L LA(A,B,C) 하자 및 PT(A,B,C) 하자","2025-12-08 09:00","2025-12-08 16:00","취소","취소","연속"]
[209,"경남","진주","고령의령#2 T/L","의령S/S 고령-의령#2T/L LA 보통점검 등","의령S/S 고령-의령#2T/L LA(A,B,C) 보통점검 7571 유압저하 경보(B,C상) 오동작 점검 87/21 주보호,후비보호 이벤트 경보 시험 필요(계통시험팀 확인예정) 7500 히터용 케이블 재포설 후 결선","2025-12-09 09:00","2025-12-09 18:00","취소","취소","연속"]
[210,"경남","진주","고령의령#1 T/L","의령S/S 고령-의령#1T/L LA 보통 및 PT 보통","의령S/S 고령-의령#1T/L LA(A,B,C) 보통 및 PT(A,B,C) 보통","2025-12-10 09:00","2025-12-10 16:00","취소","취소","연속"]
[211,"경남","진주","고령의령#1 T/L"," 고령-의령#1T/L 철탑 수평 추락방지장치 설치공사"," 고령-의령#1T/L 39호 등 48기 와이어형 수평 추락방지장치 설치공사","2025-12-01 07:00","2025-12-07 18:00","취소","취소","매일"]
[212,"경남","진주","광양하동TP#2 T/L","하동T/P 광양-하동화력#2T/L LA 보통점검","하동T/P 광양-하동화력#2T/L LA(A,B,C) 보통점검","2025-12-11 09:00","2025-12-11 16:00","취소","취소","연속"]
[213,"경남","함안","신마산신고성#1 T/L","항공번호찰 교체공사","신마산-신고성T/L 155호 항공번호찰 교체(설치 1, 철거 1)","2025-12-04 07:00","2025-12-04 18:00","2025-12-04 07:00","2025-12-04 18:00","연속"]
[214,"경남","함안","신마산신김해#1 T/L"," 신마산S/S #2M.Tr 교체공사","1.  M.Tr 철거 및 설치 x 1Bank 2. 기타 부대공사 x 1식 3. 해당공사 시험가압선로","2025-12-09 09:00","2025-12-10 18:00","2025-12-09 09:00","2025-12-10 18:00","연속"]

{"sheet":"154설비","index":2,"n_rows":438,"n_cols":12,"rows_kept":438,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2025년도 12월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","창동쌍문#2 T/L","2025년 성동P/O 변전협력회사 공사","- 170kV GIS 보통점검","2025-12-09 09:00","2025-12-09 18:00","2025-12-09 09:00","2025-12-09 18:00","연속"]
[2,"서울","성동","창동S/S #1 BUS","창동S/S 23kV 및 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154, 23kV 장기사용 GIS 교체공사 ○ 3차분 :  창동쌍문#2T/L GIS 교체(1Bay) ○ 제어케이블 포설 등 기타공사(1식)","2025-12-03 14:00","2025-12-03 18:00","2025-12-03 14:00","2025-12-03 18:00","연속"]
[3,"서울","중부","증산S/S #61 BUS","(선로시험가압)수색 및 증산S/S 건설에 따른 지중T/L 공사","(지중)선종 및 회선수 :  XLPE 2,000㎟ 10회선 케이블 포설 : 24경간( XLPE 2,000㎟, 8.73 c-km) 케이블 접속 : 중간접속 20개소, 종단접속 24개소 (가공) 선종 및 회선 수 : STACIR 330㎟, 2회선 철탑신설 1기, 전력선 가선 (1.2C-㎞) 철탑철거 2기, 전력선인하 (7.4C-㎞)","2025-12-08 09:00","2025-12-09 09:00","2025-12-08 09:00","2025-12-09 09:00","연속"]
[4,"서울","직할","중앙서소문 T/L","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 방산-중앙#2T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/24)","2025-12-11 18:00","2025-12-12 18:00","2025-12-11 18:00","2025-12-12 18:00","연속"]
[5,"서울","직할","중앙S/S #1 BUS","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 방산-중앙#2T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/24)","2025-12-08 09:00","2025-12-12 18:00","2025-12-08 09:00","2025-12-12 18:00","연속"]
[6,"서울","직할","방산중앙#2 T/L","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 방산-중앙#2T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/24)","2025-12-06 09:00","2025-12-24 19:00","2025-12-06 09:00","2025-12-24 19:00","연속"]
[7,"서울","직할","중앙S/S #2 BUS","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 방산-중앙#2T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/24)","2025-12-06 09:00","2025-12-07 18:00","2025-12-06 09:00","2025-12-07 18:00","연속"]
[8,"서울","직할","중앙S/S #1 BUS","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 중앙서소문T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/26)","2025-12-05 18:00","2025-12-05 19:00","2025-12-05 18:00","2025-12-05 19:00","연속"]
[9,"서울","직할","방산중앙#1 T/L","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 중앙서소문T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/26)","2025-12-04 16:00","2025-12-05 19:00","2025-12-04 16:00","2025-12-05 19:00","연속"]
[10,"서울","직할","중앙S/S #2 BUS","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 방산-중앙#2T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/24)","2025-12-22 09:00","2025-12-24 18:00","2025-12-22 09:00","2025-12-24 18:00","연속"]
[11,"서울","직할","중앙서소문 T/L","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 방산-중앙#2T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/24)","2025-12-23 18:00","2025-12-24 19:00","2025-12-23 18:00","2025-12-24 19:00","연속"]
[12,"서울","직할","중앙S/S #1 BUS","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 방산-중앙#2T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/24)","2025-12-24 18:00","2025-12-24 19:00","2025-12-24 18:00","2025-12-24 19:00","연속"]
[13,"서울","직할","중앙서소문 T/L","중앙S/S  장기사용 GIS 교체공사","○ 중앙S/S  장기사용 GIS 교체공사 - 대상1 : 방산-중앙#2T/L(11/15~12/05) - 대상2 : 방산중앙#2T/L(12/06~12/24)","2025-12-07 16:00","2025-12-07 18:00","2025-12-07 16:00","2025-12-07 18:00","연속"]
[14,"남서울","동서울","강동천호#1 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","강동S/S 강동-천호#1T/L 조작시험","2025-12-02 10:00","2025-12-02 12:00","취소","취소","연속"]
[15,"남서울","동서울","강동천호#2 T/L","24-25년도 동서울전력지사 변전협력회사 총액공사","강동S/S 강동-천호#2T/L 조작시험","2025-12-02 12:00","2025-12-02 14:00","취소","취소","연속"]
[16,"남서울","동서울","동서울#2S/S #5 Sh.C CB","동서울S/S 종합정비공사(2차)"," Sh.C 이설 및 토목기초 변경  제어케이블 이설","2025-12-22 09:00","2026-02-28 18:00","2025-12-22 09:00","2026-02-28 18:00","연속"]
[17,"남서울","동서울","동서울S/S #4 Sh.C CB","동서울S/S 종합정비공사(2차)"," Sh.C 이설 및 토목기초 변경  제어케이블 이설","2025-12-22 09:00","2026-02-28 18:00","2025-12-22 09:00","2026-02-28 18:00","연속"]
[18,"남서울","동서울","동서울S/S #2 Sh.C CB","동서울S/S 종합정비공사(2차)"," Sh.C 이설 및 토목기초 변경  제어케이블 이설","2025-12-22 09:00","2026-02-28 18:00","2025-12-22 09:00","2026-02-28 18:00","연속"]
[19,"남서울","동서울","동서울S/S #1 Sh.C CB","동서울S/S 종합정비공사(2차)"," Sh.C 이설 및 토목기초 변경  제어케이블 이설","2025-12-22 09:00","2026-02-28 18:00","2025-12-22 09:00","2026-02-28 18:00","연속"]
[20,"남서울","동서울","동서울S/S #3 Sh.C CB","동서울S/S 종합정비공사(2차)"," Sh.C 이설 및 토목기초 변경  제어케이블 이설","2025-12-22 09:00","2026-02-28 18:00","2025-12-22 09:00","2026-02-28 18:00","연속"]
[21,"남서울","영등포","마곡가양#2 T/L","24~25년 영등포전력지사 변전협력회사 총액공사"," GIS 조작시험","2025-12-06 09:00","2025-12-06 14:00","취소","취소","연속"]
[22,"남서울","영등포","마곡가양#1 T/L","24~25년 영등포전력지사 변전협력회사 총액공사"," GIS 조작시험","2025-12-06 14:00","2025-12-06 18:00","취소","취소","연속"]
[23,"남서울","영등포","화곡마곡#1 T/L","24~25년 영등포전력지사 변전협력회사 총액공사"," GIS 정밀점검 및 보통점검","2025-12-01 09:00","2025-12-03 14:00","취소","취소","연속"]
[24,"남서울","영등포","화곡마곡#2 T/L","24~25년 영등포전력지사 변전협력회사 총액공사"," GIS 정밀점검 및 보통점검","2025-12-03 14:00","2025-12-05 18:00","취소","취소","연속"]
[25,"남서울","직할","봉천신길#1 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-12-01 09:00","2025-12-02 18:00","2025-12-01 09:00","2025-12-02 18:00","연속"]
[26,"남서울","직할","봉천신길#2 T/L","OF케이블 절연유 채유 및 채취밸브 설치","OF케이블 열화진단용 절연유 채유 및 채취밸브 설치","2025-12-01 09:00","2025-12-02 18:00","2025-12-01 09:00","2025-12-02 18:00","연속"]
[27,"인천","부평","신가좌주안#2 T/L","신가좌S/S 신가좌-주안#1T/L 보통점검(오후)","신가좌S/S 신가좌-주안#1T/L 보통점검(오후)","2025-12-06 12:00","2025-12-06 18:00","취소","취소","연속"]
[28,"인천","부평","신가좌주안#1 T/L","신가좌S/S 신가좌-주안#1T/L 보통점검(오전)","신가좌S/S 신가좌-주안#1T/L 보통점검(오전)","2025-12-06 07:00","2025-12-06 12:00","취소","취소","연속"]
[29,"인천","부평","주안S/S CB 6100","주안S/S  #60-#65 BUS TIE GIS 보통점검","주안S/S  #60-#65 BUS TIE GIS 보통점검","2025-12-02 09:00","2025-12-02 18:00","취소","취소","연속"]
[30,"인천","시흥","동시화서시화 T/L","동시화S/S  #6M.Tr 증설공사(최종무부하 가압)","- 동시화S/S #6M.Tr 최종무부하 가압","2025-12-04 18:00","2025-12-05 18:00","취소","취소","연속"]
[31,"인천","김포","신김포S/S CB 6100","신김포S/S  #60-#65 모선보호반 대체공사","신김포S/S  #60-#65 모선보호반 대체공사","2025-12-01 10:00","2025-12-05 18:00","취소","취소","연속"]
[32,"인천","김포","신김포S/S SEC CB 65660","신김포S/S  #60-#65 모선보호반 대체공사","신김포S/S  #60-#65 모선보호반 대체공사","2025-12-01 10:00","2025-12-05 18:00","취소","취소","연속"]
[33,"인천","김포","신김포S/S SEC CB 60610","신김포S/S  #60-#65 모선보호반 대체공사","신김포S/S  #60-#65 모선보호반 대체공사","2025-12-01 10:00","2025-12-05 18:00","취소","취소","연속"]
[34,"인천","김포","김포불로#1 T/L","불로S/S 170kV 불로-김포 #1T/L GIS 하자점검","불로S/S 170kV 불로-김포 #1T/L GIS 하자점검 - 김포S/S 170kV 불로-김포 #1T/L GIS 보통점검(상시Ry교체)","2025-12-06 09:00","2025-12-06 18:00","2025-12-06 09:00","2025-12-06 18:00","연속"]
[35,"인천","김포","김포불로#2 T/L","불로S/S 170kV 불로-김포 #2T/L GIS 하자점검","불로S/S 170kV 불로-김포 #2T/L GIS 하자점검","2025-12-07 09:00","2025-12-07 18:00","2025-12-07 09:00","2025-12-07 18:00","연속"]
[36,"경기북부","구리","신장덕소#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신장-덕소#1 가선공정","2025-12-11 07:00","2025-12-17 17:00","2025-12-11 07:00","2025-12-17 17:00","연속"]
[37,"경기북부","구리","신장덕소#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신장-덕소#2 가선공정","2025-12-04 07:00","2025-12-10 17:00","2025-12-04 07:00","2025-12-10 17:00","연속"]
[38,"경기북부","구리","동서울서종#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신장-덕소#2 가선공정","2025-12-04 07:00","2025-12-10 17:00","2025-12-04 07:00","2025-12-10 17:00","연속"]
[39,"경기북부","구리","동서울서종#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신장-덕소#1 가선공정","2025-12-11 07:00","2025-12-17 17:00","2025-12-11 07:00","2025-12-17 17:00","연속"]
[40,"경기북부","구리","신포천전곡#1 T/L","2025년 구리전력지사  GIS 이상 점검공사","관내변전소  GIS 보통점검","2025-12-01 09:00","2025-12-01 18:00","2025-12-01 09:00","2025-12-01 18:00","연속"]
[41,"경기북부","구리","문막지제#1 T/L","24-25년 구리전력지사 변전협력회사 총액공사","관내변전소  GIS 보통점검","2025-12-03 09:00","2025-12-03 18:00","2025-12-03 09:00","2025-12-03 18:00","연속"]
[42,"경기북부","직할","녹양S/S #2 BUS","녹양S/S 170kV GIS 장기사용 대체공사","장기사용 GIS 철거 및 설치 (분리된 모선 연결 및 무부하 가압)","2025-12-15 08:00","2025-12-19 09:00","2025-12-15 08:00","2025-12-19 09:00","연속"]
[43,"경기북부","직할","녹양S/S #1 BUS","녹양S/S 170kV GIS 장기사용 대체공사","장기사용 GIS 철거 및 설치 (분리된 모선 연결 및 무부하 가압)","2025-12-08 08:00","2025-12-12 09:00","2025-12-08 08:00","2025-12-12 09:00","연속"]
[44,"경기","군포","사강남양#1 T/L","사강S/S 남양-사강#1T/L 인출ES 레버 취부","사강S/S 남양-사강#1T/L 인출ES 레버 취부","2025-12-07 09:00","2025-12-07 18:00","2025-12-07 09:00","2025-12-07 18:00","연속"]
[45,"경기","군포","서서울#2봉담#1 T/L","2025년 가공송전 순시점검 위탁공사(초기점검)"," 서서울2-봉담#1T/L 초기점검 대상 : No.31~34 (총4기)","2025-12-08 08:00","2025-12-08 17:00","취소","취소","연속"]
[46,"경기","군포","서서울#2봉담#2 T/L","2025년 가공송전 순시점검 위탁공사(초기점검)"," 서서울2-봉담#2T/L 초기점검 대상 : No.31~34 (총4기)","2025-12-09 08:00","2025-12-09 17:00","취소","취소","연속"]
[47,"경기","군포","서서울율전#1 T/L","2025년 가공송전 순시점검 위탁공사(초기점검)"," 서서울-율전#1T/L 초기점검 대상 : No.4~8 (총 5기)","2025-12-15 08:00","2025-12-15 17:00","2025-12-15 08:00","2025-12-15 17:00","연속"]
[48,"경기","군포","서서울율전#2 T/L","2025년 가공송전 순시점검 위탁공사(초기점검)"," 서서울-율전#2T/L 초기점검 대상 : No.4~8 (총 5기)","2025-12-16 08:00","2025-12-16 17:00","2025-12-16 08:00","2025-12-16 17:00","연속"]
[49,"경기","동부","곤지암이천#1 T/L","곤지암S/S  LA7, LD7 대체작업","곤지암: ,LA7,LD7 대체 * 안전이격 휴전 : 곤지암-이천#1T/L","2025-12-18 09:00","2025-12-18 18:00","취소","취소","연속"]
[50,"경기","동부","곤지암초월#1 T/L","곤지암S/S  LA6, LA7 대체작업","곤지암: ,LA6,LD6 대체 *안전이격 휴전 : 곤지암-초월#1T/L","2025-12-16 09:00","2025-12-16 18:00","취소","취소","연속"]
[51,"경기","동부","정자동판교#1 T/L"," 동판교S/S #4M.Tr 설치공사"," 동판교S/S #4M.Tr 설치공사(무부하가압)","2025-12-19 09:00","2025-12-20 18:00","2025-12-19 09:00","2025-12-20 18:00","연속"]
[52,"경기","동부","정자동판교#1 T/L"," 동판교S/S #4M.Tr용 GIS 설치공사"," 동판교S/S #4M.Tr용 GIS 설치공사(무부하가압)","2025-12-05 14:00","2025-12-06 18:00","2025-12-05 14:00","2025-12-06 18:00","연속"]
[53,"경기","동부","오포모현#1 T/L"," 모현S/S #4M.Tr 증설공사 무부하 가압","#4M.Tr 24시간 무부하 가압","2025-12-17 11:00","2025-12-18 12:00","2025-12-17 11:00","2025-12-18 12:00","연속"]
[54,"경기","동부","성현분당#1 T/L","분당S/S 성현-분당#1T/L 효성제 발청점검","분당S/S 성현-분당#1T/L 효성제 발청점검","2025-12-08 09:00","2025-12-08 18:00","취소","취소","연속"]
[55,"경기","동부","분당오포#2 T/L","(시급) 분당S/S 분당-오포#2T/L 보호반 대체","분당S/S 분당-오포#2T/L 보호반 대체 - 24년부터 지속연기되어 시행필요","2025-12-10 09:00","2025-12-12 18:00","취소","취소","연속"]
[56,"경기","동부","이천S/S CB 6100","이천S/S 6100 GIS 보통점검","이천:6100(보통) *감곡-가남 선종교체로 25년 시행불가 예상","2025-12-09 09:00","2025-12-09 14:00","2025-12-09 09:00","2025-12-09 14:00","연속"]
[57,"경기","동부","이천S/S SEC CB 65660","이천S/S 65-66 GIS 보통점검","이천S/S 65-66 GIS 보통점검 *가남 선종교체로 25년 시행불가 예상","2025-12-09 14:00","2025-12-09 18:00","2025-12-09 14:00","2025-12-09 18:00","연속"]
[58,"경기","성남","신수원S/S CB 6100","2025년 성남전력 변전협력회사 총액공사","gis 보통점검","2025-12-02 09:00","2025-12-02 14:00","취소","취소","연속"]
[59,"경기","성남","신수원S/S CB 6300","2025년 성남전력 변전협력회사 총액공사","gis 조작시험","2025-12-02 14:00","2025-12-02 18:00","취소","취소","연속"]
[60,"경기","성남","오천용인#2 T/L","2025년 성남전력 변전협력회사 총액공사","LA 보통점검","2025-12-10 09:00","2025-12-10 18:00","2025-12-10 09:00","2025-12-10 18:00","연속"]
[61,"경기","직할","봉담남수원#1 T/L","2025년 가공송전 순시점검 위탁공사(초기점검)"," 봉담-남수원#1T/L 초기점검 대상 : No.1~3, 6~11 (총 9기)","2025-12-02 08:00","2025-12-03 17:00","2025-12-02 08:00","2025-12-03 17:00","연속"]
[62,"경기","직할","봉담남수원#2 T/L","2025년 가공송전 순시점검 위탁공사(초기점검)"," 봉담-남수원#2T/L 초기점검 대상 : No.1~3, 6~11 (총 9기)","2025-12-04 08:00","2025-12-05 17:00","2025-12-04 08:00","2025-12-05 17:00","연속"]
[63,"경기","평택","고덕S/S CB 6200","2025년 평택전력 변전협력회사 총액공사(고덕S/S 6200)","고덕S/S  #61-#66 BUS TIE GIS(6200) GIS 보통점검","2025-12-10 09:00","2025-12-10 18:00","취소","취소","연속"]
[64,"경기","평택","원정평택TP#2 T/L","2025 평택전력 변전협력 총액공사(원정평택2)","원정S/S 원정-평택T/P #2T/L GIS 조작시험, PT&LA 보통점검","2025-12-09 09:00","2025-12-09 18:00","취소","취소","연속"]
[65,"경기","평택","진위동탄#1 T/L"," 방여울S/S 건설공사","[방여울S/S] -  M.Tr(45/60) x 2Bank 신설 - 170kV EGIS x 10CCT 신설 - 25.8kV EGIS x 19CCT(PT Bay 별도) 신설","2025-12-15 09:00","2025-12-16 18:00","2025-12-15 09:00","2025-12-16 18:00","연속"]
[66,"경기","평택","포승평택TP#2 T/L"," 평택T/L SW 증설공사(기아)","- 무부하가압 선로","2025-12-18 09:00","2025-12-19 18:00","2025-12-18 09:00","2025-12-19 18:00","연속"]
[67,"경기","동부","중원야탑 T/L","중원S/S 중원-야탑T/L 2DS 링크교체공사","중원S/S 중원-야탑T/L 2DS 링크교체공사","2025-12-02 09:00","2025-12-03 18:00","2025-12-02 09:00","2025-12-03 18:00","연속"]
[68,"강원","강릉","강릉북강릉#2 T/L","2025년 강릉 주변압기 대체 공사","#4M.Tr 무부하 가압","2025-12-15 09:00","2025-12-16 18:00","2025-12-15 09:00","2025-12-16 18:00","연속"]
[69,"강원","강릉","강릉영동TP T/L","345kV 동해-북평T/P 등 3개T/L 온라인PD 진단시스템 설치공사","작업내용 :  영동T/P-강릉T/L ON-LINE PD 진단시스템 설치 작업기간 - `25.12.12 13:00 ~ 18:00","2025-12-12 13:00","2025-12-12 18:00","2025-12-12 13:00","2025-12-12 18:00","연속"]
[70,"강원","강릉","신양양양양#1 T/L"," 신양양속초 등 3개T/L 추락방지장치설치공사"," 신양양양양#1 T/L : 수직 및 수평 추락방지장치 설치","2025-12-01 07:00","2025-12-04 17:00","2025-12-01 07:00","2025-12-04 17:00","매일"]
[71,"강원","강릉","주문진양양#2 T/L","2024-2025년 강릉전력지사 송전협력회사 공사","○ 추락방지장치 설치 :  주문진-양양#2 T/L No.1~6","2025-12-15 07:00","2025-12-16 18:00","2025-12-15 07:00","2025-12-16 18:00","매일"]
[72,"강원","강릉","북강릉주문진#1 T/L","2024-2025년 강릉전력지사 송전협력회사 공사","○ 추락방지장치 설치 :  북강릉-주문진#1 T/L No.50~55","2025-12-15 07:00","2025-12-16 18:00","2025-12-15 07:00","2025-12-16 18:00","매일"]
[73,"강원","강릉","강릉횡계#1 T/L","2025년 횡계S/S 주변압기 증설 공사","#1M.Tr 무부하 가압","2025-12-16 10:00","2025-12-17 10:00","2025-12-16 10:00","2025-12-17 10:00","연속"]
[74,"강원","강릉","횡계강원풍력 T/L CB","2025년 강릉전력지사 변전협력 총액공사","강원풍력TL 송전선로 보호반 대체(고객협의 완료)","2025-12-15 10:00","2025-12-19 18:00","2025-12-15 10:00","2025-12-19 18:00","연속"]
[75,"강원","동해","북평영동TP#1 T/L","진동저감댐퍼 실 선로 현장실증","新진동저감댐퍼 실선로 현장실증(연구원요청)","2025-12-12 13:00","2025-12-12 18:00","2025-12-12 13:00","2025-12-12 18:00","연속"]
[76,"강원","직할","북춘천화천HP T/L"," 상제 등 3개 T/L 추락방지장치 설치공사"," 화천 T/L 추락방지장치 설치공사","2025-12-01 09:00","2025-12-04 18:00","2025-12-01 09:00","2025-12-04 18:00","연속"]
[77,"강원","직할","서홍천춘천열병합 T/L","2024~2025년 강원본부 직할 변전협력회사 공사","□ 서홍천S/S  서홍천-춘천열병합T/L 보호반 교체 □ 춘천열병합  서홍천-춘천열병합T/L 보호반 교체","2025-12-02 09:00","2025-12-05 18:00","2025-12-02 09:00","2025-12-05 18:00","연속"]
[78,"강원","직할","춘천열병합 #1 BUS","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  남춘천-춘천열병합 #1T/L GIS 정밀점검 후 무부하 가압용","2025-12-03 14:00","2025-12-03 18:00","2025-12-03 14:00","2025-12-03 18:00","연속"]
[79,"강원","직할","남춘천춘천열병합#1 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  남춘천-춘천열병합 #1T/L GIS 정밀점검","2025-12-01 10:00","2025-12-03 18:00","2025-12-01 10:00","2025-12-03 18:00","연속"]
[80,"강원","직할","서홍천춘천열병합 T/L","2025년 강원본부 직할  GIS, GCB 정밀점검 공사","□ 춘천열병합S/Y  남춘천-춘천열병합 #1T/L GIS 정밀점검 후 무부하 가압용","2025-12-03 14:00","2025-12-03 18:00","2025-12-03 14:00","2025-12-03 18:00","연속"]
[81,"강원","직할","가평화천HP T/L"," 상제 등 3개 T/L 추락방지장치 설치공사"," 화천 T/L 추락방지장치 설치","2025-12-05 09:00","2025-12-05 18:00","2025-12-05 09:00","2025-12-05 18:00","연속"]
[82,"강원","직할","북춘천화천HP T/L","2024~2025년 강원본부 직할 변전협력회사 공사"," 북춘천-화천H/PT/L LA,DS,PT 보통점검, 차단기 조작시험","2025-12-02 09:00","2025-12-02 18:00","취소","취소","연속"]
[83,"강원","직할","화천H/P #2 BUS","2024~2025년 강원본부 직할 변전협력회사 공사","화천H/P  #2 BUS PT 하자점검","2025-12-01 14:00","2025-12-01 18:00","2025-12-01 14:00","2025-12-01 18:00","연속"]
[84,"강원","직할","화천H/P #1 BUS","2024~2025년 강원본부 직할 변전협력회사 공사","화천H/P  #1 BUS PT 하자점검","2025-12-01 09:00","2025-12-01 14:00","2025-12-01 09:00","2025-12-01 14:00","연속"]
[85,"강원","직할","화천S/S CB 6100","2024~2025년 강원본부 직할 변전협력회사 공사"," #1-#2 BUS TIE 차단기 조작시험","2025-12-03 09:00","2025-12-03 14:00","2025-12-03 09:00","2025-12-03 14:00","연속"]
[86,"강원","태백","고한영월에코윈드 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 고한-영월에코윈드T/L 빙설해 고장 이력개소 신전선 시범 보강 시행","2025-12-01 08:00","2025-12-05 18:00","2025-12-01 08:00","2025-12-05 18:00","연속"]
[87,"강원","태백","이원태백 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 태원T/L 조류착지방지장치 설치","2025-12-04 09:00","2025-12-05 18:00","2025-12-04 09:00","2025-12-05 18:00","매일"]
[88,"강원","태백","도계태백 T/L","2024~2025년 태백전력지사 송전 협력회사 공사"," 태원T/L 조류착지방지장치 설치","2025-12-01 09:00","2025-12-03 18:00","2025-12-01 09:00","2025-12-03 18:00","매일"]
[89,"강원","태백","태백S/S SEC CB 65660","2024-2025년 태백전력지사 변전협력회사 공사","태백S/S  #65-#66 SEC GIS 보통점검","2025-12-01 09:00","2025-12-01 18:00","2025-12-01 09:00","2025-12-01 18:00","연속"]
[90,"강원","태백","태백S/S CB 6200","2024-2025년 태백전력지사 변전협력회사 공사","태백S/S  #61-#66 BUS TIE GIS 보통점검","2025-12-02 09:00","2025-12-02 18:00","2025-12-02 09:00","2025-12-02 18:00","연속"]
[91,"충북","직할","광혜원대소#2 T/L"," 광혜원-대소 지중T/L접속함 교체","#1T/L : M/H#2(A상) #2T/L : M/H#2(A,B상), M/H#3(A상),M/H#4(A,B,C상),M/H#5(A,C상)","2025-12-15 08:00","2025-12-21 18:00","2025-12-15 08:00","2025-12-21 18:00","연속"]
[92,"충북","직할","광혜원대소#1 T/L"," 광혜원-대소 지중T/L접속함 교체","#1T/L : M/H#2(A상) #2T/L : M/H#2(A,B상), M/H#3(A상),M/H#4(A,B,C상),M/H#5(A,C상)","2025-12-22 08:00","2025-12-24 18:00","2025-12-22 08:00","2025-12-24 18:00","연속"]
[93,"충북","직할","남음성덕산#2 T/L","25년 충북직할  GIS 정밀점검공사","덕산변전소  남음성-덕산#2T/L GIS 정밀점검","2025-12-22 08:00","2025-12-23 18:00","2025-12-22 08:00","2025-12-23 18:00","연속"]
[94,"충북","직할","진천덕산#1 T/L","25년 충북직할  GIS 정밀점검공사","덕산변전소  진천-덕산#1T/L GIS 정밀점검","2025-12-15 08:00","2025-12-16 18:00","2025-12-15 08:00","2025-12-16 18:00","연속"]
[95,"충북","직할","남음성덕산#1 T/L","25년 충북직할  GIS 정밀점검공사","덕산변전소  남음성-덕산#1T/L GIS 정밀점검","2025-12-19 08:00","2025-12-20 18:00","2025-12-19 08:00","2025-12-20 18:00","연속"]
[96,"충북","직할","진천덕산#2 T/L","25년 충북직할  GIS 정밀점검공사","덕산변전소  진천-덕산#2T/L GIS 정밀점검","2025-12-17 08:00","2025-12-18 18:00","2025-12-17 08:00","2025-12-18 18:00","연속"]
[97,"충북","직할","진천S/S CB 6200","진천S/S  #4, 5M.Tr 교체공사","○ 진천S/S  #4, 5M.Tr 교체공사 - 무부하가압 시 공급 중 변압기 모선변경을 위한 BUS-TIE 휴전조작","2025-12-01 09:00","2025-12-02 18:00","2025-12-01 09:00","2025-12-02 18:00","연속"]
[98,"충북","청주","남청주오송#2 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 전자변교체 LA, CVT 점검","2025-12-02 10:00","2025-12-02 18:00","2025-12-02 10:00","2025-12-02 18:00","연속"]
[99,"충북","청주","남청주오송#1 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 전자변교체 LA, CVT 점검","2025-12-01 10:00","2025-12-01 18:00","2025-12-01 10:00","2025-12-01 18:00","연속"]
[100,"충북","청주","화동보은 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검 및 LA,CVT 교체","2025-12-04 10:00","2025-12-04 18:00","2025-12-04 10:00","2025-12-04 18:00","연속"]
[101,"충북","청주","서청주사직#2 T/L","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-12-04 09:00","2025-12-05 18:00","2025-12-04 09:00","2025-12-05 18:00","연속"]
[102,"충북","청주","화동영동 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검 및 LA,CVT 교체","2025-12-03 10:00","2025-12-03 18:00","2025-12-03 10:00","2025-12-03 18:00","연속"]
[103,"충북","청주","옥천영동 T/L","2024~2025년 청주전력지사 변전협력회사 공사"," GIS 보통점검 및 LA,CVT 교체","2025-12-08 10:00","2025-12-09 18:00","2025-12-08 10:00","2025-12-09 18:00","연속"]
[104,"충북","청주","죽림S/S #1 BUS","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-12-11 09:00","2025-12-12 18:00","2025-12-11 09:00","2025-12-12 18:00","연속"]
[105,"충북","청주","죽림S/S CB 6100","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-12-11 09:00","2025-12-12 18:00","2025-12-11 09:00","2025-12-12 18:00","연속"]
[106,"충북","청주","남청주죽림#1 T/L","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검","2025-12-09 09:00","2025-12-10 18:00","2025-12-09 09:00","2025-12-10 18:00","연속"]
[107,"충북","청주","남청주죽림#1 T/L","25년 청주전력지사 170kV GIS 정밀점검공사","170kV GIS 정밀점검 무부하가압용(죽림 BUS TIE)","2025-12-12 15:00","2025-12-12 18:00","2025-12-12 15:00","2025-12-12 18:00","연속"]
[108,"충북","충주","금왕남음성#2 T/L"," 성본S/S 및 지중 T/L 최초가압","금왕-성본#1T/L 무부하가압 및 성본S/S 실부하가압 시행","2025-12-09 14:00","2025-12-12 10:00","2025-12-09 14:00","2025-12-12 10:00","연속"]
[109,"충북","충주","금왕S/S #1 BUS"," 성본S/S 및 지중 T/L 최초가압","금왕-성본#1T/L 무부하가압 및 성본S/S 실부하가압 시행","2025-12-11 14:00","2025-12-12 10:00","2025-12-11 14:00","2025-12-12 10:00","연속"]
[110,"충북","충주","금왕S/S #2 BUS"," 성본S/S 및 지중 T/L 최초가압","금왕-성본#1T/L 무부하가압 및 성본S/S 실부하가압 시행","2025-12-09 14:00","2025-12-10 14:00","2025-12-09 14:00","2025-12-10 14:00","연속"]
[111,"충북","충주","점촌단양 T/L","단양S/S STATCOM 설치공사","STATCOM C.Tr 무부하 가압","2025-12-27 14:00","2025-12-28 14:00","2025-12-27 14:00","2025-12-28 14:00","연속"]
[112,"충북","충주","단양S/S #66 BUS","단양S/S STATCOM 설치공사","STATCOM C.Tr 무부하 가압","2025-12-27 14:00","2025-12-28 14:00","2025-12-27 14:00","2025-12-28 14:00","연속"]
[113,"충북","충주","대소S/S #66 BUS"," 성본S/S 및 지중 T/L 최초가압","금왕-성본#1T/L 무부하가압 및 성본S/S 실부하가압 시행","2025-12-09 14:00","2025-12-10 14:00","2025-12-09 14:00","2025-12-10 14:00","연속"]
[114,"충북","충주","신충주북충주#2 T/L","2024~2025년 충주전력지사 송전협력회사 공사","상간스페이서 설치( 신충주-북충주#2T/L No.71~72)","2025-12-02 07:00","2025-12-02 18:00","2025-12-02 07:00","2025-12-02 18:00","연속"]
[115,"충북","충주","왕암북충주 T/L","왕암S/S STATCOM 설치공사","STATCOM C.Tr 무부하 가압","2025-12-27 14:00","2025-12-28 14:00","2025-12-27 14:00","2025-12-28 14:00","연속"]
[116,"충북","충주","왕암S/S #1 BUS","왕암S/S STATCOM 설치공사","STATCOM C.Tr 무부하가압","2025-12-27 14:00","2025-12-28 14:00","2025-12-27 14:00","2025-12-28 14:00","연속"]
[117,"대전세종충남","대전","신옥천남대전#2 T/L","[가압X]남대전S/S 신옥천-남대전#2T/L GIS 내부 흡습제교체","[가압X]남대전S/S 신옥천-남대전#2T/L GIS 내부 흡습제교체","2025-12-15 09:00","2025-12-16 14:00","취소","취소","연속"]
[118,"대전세종충남","대전","신옥천남대전#1 T/L","[가압X]남대전S/S 신옥천-남대전#2T/L GIS 내부 흡습제교체","[가압X]남대전S/S 신옥천-남대전#2T/L GIS 내부 흡습제교체","2025-12-11 09:00","2025-12-12 18:00","취소","취소","연속"]
[119,"대전세종충남","대전","신옥천남대전#3 T/L","[가압X]남대전S/S 신옥천-남대전#3T/L GIS 내부 흡습제교체","[가압X]남대전S/S 신옥천-남대전#3T/L GIS 내부 흡습제교체","2025-12-16 14:00","2025-12-17 18:00","취소","취소","연속"]
[120,"대전세종충남","대전","신옥천남대전#4 T/L","[가압X]남대전S/S 신옥천-남대전#4T/L GIS 내부흡습제 교체","[가압X]남대전S/S 신옥천-남대전#4T/L GIS 내부흡습제 교체","2025-12-18 09:00","2025-12-19 18:00","취소","취소","연속"]
[121,"대전세종충남","대전","남대전신흥#1 T/L","[가압X]남대전S/S 남대전-신흥#1T/L GIS 내부 흡습제 교체","[가압X]남대전S/S 남대전-신흥#1T/L GIS 내부 흡습제 교체","2025-12-08 09:00","2025-12-09 14:00","취소","취소","연속"]
[122,"대전세종충남","대전","남대전신흥#2 T/L","[가압X]남대전S/S 남대전-신흥#2T/L GIS 내부 흡습제 교체","[가압X]남대전S/S 남대전-신흥#2T/L GIS 내부 흡습제 교체","2025-12-09 14:00","2025-12-10 18:00","취소","취소","연속"]
[123,"대전세종충남","대전","신옥천서대전 T/L","[가압X][취소시]서대전S/S 신옥천-서대전T/L GIS 보통점검","[가압X][취소시]서대전S/S 신옥천-서대전T/L GIS 보통점검","2025-12-05 09:00","2025-12-05 18:00","취소","취소","연속"]
[124,"대전세종충남","대전","신계룡은진#1 T/L","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","[송전][오전만][즉시가압O]345kV 신옥천-청양 등 추락방지설치공사","2025-12-08 07:00","2025-12-12 10:00","취소","취소","매일"]
[125,"대전세종충남","대전","신옥천용운#2 T/L"," 신옥천-용운T/L 지장수목전지 및 벌채"," 신옥천-용운T/L 지장수목전지 및 벌채","2025-12-04 09:00","2025-12-05 18:00","취소","취소","매일"]
[126,"대전세종충남","서산","석문당진화력#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 석문-당진화력#1T/L No.2~23 총 22기) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-12-29 08:00","2025-12-30 18:00","취소","취소","매일"]
[127,"대전세종충남","서산","서산홍성 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 서산-홍성T/L No.1~135 총 83기) , 즉시가압(20분 이내) 가능","2025-12-08 08:00","2025-12-14 18:00","2025-12-08 08:00","2025-12-14 18:00","매일"]
[128,"대전세종충남","서산","서산태안#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 서산-태안#1T/L No.15~56, 58~59, 62~80 총 63기) , 즉시가압(20분 이내) 가능","2025-12-15 08:00","2025-12-20 18:00","취소","취소","매일"]
[129,"대전세종충남","서산","서산태안#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 서산-태안#2T/L No.15~56, 58~59, 62~80 총 63기) , 즉시가압(20분 이내) 가능, 주말 및 휴일작업 없음, 10월 작업시 작업 일수 2일로 축소 가능","2025-12-22 08:00","2025-12-26 18:00","취소","취소","매일"]
[130,"대전세종충남","서산","당진송악#1 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (345kV 당진송악#1T/L No.40 총 1기) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-12-19 08:00","2025-12-19 13:00","2025-12-19 08:00","2025-12-19 13:00","매일"]
[131,"대전세종충남","서산","당진송악#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 (345kV 당진송악#2T/L No.40 총 1기) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-12-19 13:00","2025-12-19 18:00","2025-12-19 13:00","2025-12-19 18:00","매일"]
[132,"대전세종충남","서산","태안태안화력#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 태안-태안화력#2T/L No.1, 28~50 총 24기) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-12-29 08:00","2025-12-30 18:00","2025-12-29 08:00","2025-12-30 18:00","매일"]
[133,"대전세종충남","서산","합덕송악#2 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 합덕-송악#2T/L No.29~51, 98 총 24기) , 즉시가압(20분 이내) 가능,주말 및 휴일작업 없음","2025-12-04 08:00","2025-12-05 18:00","2025-12-04 08:00","2025-12-05 18:00","매일"]
[134,"대전세종충남","서산","해미홍성 T/L","345kV 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 해미-홍성T/L No.1~30 총 30기) , 즉시가압(20분 이내) 가능, 주말 및 휴일작업 없음","2025-12-15 08:00","2025-12-17 18:00","2025-12-15 08:00","2025-12-17 18:00","매일"]
[135,"대전세종충남","세종","덕진공주#1 T/L","(11월 취소시) 덕진-공주T/L 지장수목 벌채"," 덕진-공주T/L 지장수목 벌채","2025-12-08 09:00","2025-12-09 18:00","취소","취소","매일"]
[136,"대전세종충남","세종","덕진공주#2 T/L","(11월 취소시) 덕진-공주T/L 지장수목 벌채"," 덕진-공주T/L 지장수목 벌채","2025-12-10 09:00","2025-12-11 18:00","취소","취소","매일"]
[137,"대전세종충남","세종","둔곡송강#1 T/L"," 둔곡-송강T/L 지장수목 전지 및 벌채"," 둔곡-송강T/L 지장수목 전지 및 벌채","2025-12-01 07:00","2025-12-01 13:00","취소","취소","연속"]
[138,"대전세종충남","세종","둔곡송강#2 T/L"," 둔곡-송강T/L 지장수목 전지 및 벌채"," 둔곡-송강T/L 지장수목 전지 및 벌채","2025-12-01 13:00","2025-12-01 18:00","취소","취소","연속"]
[139,"대전세종충남","직할","대덕둔산 T/L","대덕대교 교량첨가 구간 지장송전선로 이설공사","○ 공사구간 :  대덕-둔산T/L M/H#2 ~ M/H#3 ○ 지장이설 : M/H#2 ~ M/H#3  XLPE 2000SQ (0.4km)","2025-12-01 09:00","2025-12-17 18:00","2025-12-01 09:00","2025-12-17 18:00","연속"]
[140,"대전세종충남","직할","대덕둔지 T/L","대덕대교 교량첨가 구간 지장송전선로 이설공사","○ 공사구간 :  대덕-둔산T/L M/H#2 ~ M/H#3 ○ 지장이설 : M/H#2 ~ M/H#3  XLPE 2000SQ (0.4km)","2025-12-01 09:00","2025-12-17 18:00","2025-12-01 09:00","2025-12-17 18:00","매일"]
[141,"대전세종충남","직할","동대전신탄진#1 T/L","24-25년도 직할 변전협력회사 총액공사 (11월 승인취소시)","○ 동대전-신탄진#1 T/L GIS 초기점검","2025-12-02 09:00","2025-12-02 18:00","취소","취소","연속"]
[142,"대전세종충남","직할","동대전신탄진#2 T/L","24-25년도 직할 변전협력회사 총액공사(11월 승인취소시)","○ 동대전-신탄진#2 T/L GIS 초기점검","2025-12-03 09:00","2025-12-03 18:00","취소","취소","연속"]
[143,"대전세종충남","천안","둔포직산#1 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능) 둔포S/S  직산-둔포#1T/L GIS 보통점검","2025-12-01 09:00","2025-12-01 18:00","취소","취소","연속"]
[144,"대전세종충남","천안","둔포직산#2 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(즉시가압가능) 둔포S/S  직산-둔포#2T/L GIS 보통점검","2025-12-02 09:00","2025-12-02 18:00","취소","취소","연속"]
[145,"대전세종충남","천안","장재불당#2 T/L","(즉시가압가능)불당S/S 장재-불당#2T/L CB 전자변 교체","불당S/S 장재-불당#2T/L CB 전자변 교체 및 개폐타임 측정","2025-12-01 09:00","2025-12-01 18:00","2025-12-01 09:00","2025-12-01 18:00","연속"]
[146,"대전세종충남","천안","신온양석곡#2 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(11월취소시_즉시가압가능) 석곡S/S  신온양-석곡#2T/L GIS 보통점검","2025-12-12 09:00","2025-12-12 18:00","취소","취소","연속"]
[147,"대전세종충남","천안","신온양석곡#1 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(11월취소시_즉시가압가능) 석곡S/S  신온양-석곡#1T/L GIS 보통점검","2025-12-11 09:00","2025-12-11 18:00","취소","취소","연속"]
[148,"대전세종충남","천안","신탕정탕정#3 T/L"," 신탕정-탕정#3 지중T/L 건설공사"," XLPE 2000SQ 1회선 케이블 가압(신탕정SS ~ 탕정SS)","2025-12-10 09:00","2025-12-10 18:00","2025-12-10 09:00","2025-12-10 18:00","연속"]
[149,"대전세종충남","천안","아산예산#1 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(11월 취소시_즉시가압가능) 아산S/S  아산-예산#1T/L GIS 보통점검","2025-12-03 09:00","2025-12-03 18:00","취소","취소","연속"]
[150,"대전세종충남","천안","아산예산#1 T/L"," 아산-예산#1T/L 노후 보호배전반 대체","(즉시가압불가)(장기미교체 대상) 아산-예산#1T/L 노후 보호배전반 대체","2025-12-01 09:00","2025-12-03 18:00","취소","취소","연속"]
[151,"대전세종충남","천안","온양풍세#1 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(11월취소시_즉시가압가능) 온양,풍세S/S  온양-풍세#1T/L GIS 보통점검","2025-12-04 09:00","2025-12-05 18:00","취소","취소","매일"]
[152,"대전세종충남","천안","온양풍세#1 T/L","온양S/S  장기사용 #1M.Tr 교체공사"," #1M.Tr 교체 후 무부하 가압(24H)","2025-12-04 15:00","2025-12-05 15:00","2025-12-04 15:00","2025-12-05 15:00","연속"]
[153,"대전세종충남","천안","아산인주#2 T/L","인주S/S 아산-인주#2T/L CB 전자변 교체","인주S/S 아산-인주#2T/L CB 전자변 교체 및 개폐타임 측정","2025-12-02 09:00","2025-12-02 18:00","취소","취소","연속"]
[154,"대전세종충남","천안","서천안탕정#2 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(11월 취소시_즉시가압가능) 탕정S/S  서천안-탕정#2T/L GIS 보통점검","2025-12-15 09:00","2025-12-15 18:00","취소","취소","연속"]
[155,"대전세종충남","청양","관창대천#1 T/L","[변전총액] 청양P/O 변전협력 총액공사","관창S/S 170kV 관창-대천#1T/L 조작시험 및 피뢰기 보통점검","2025-12-19 09:00","2025-12-19 18:00","취소","취소","연속"]
[156,"대전세종충남","청양","관창대천#2 T/L","[11월취소시]['25년 청양P/O 170kV GIS 정밀점검 공사]","관창S/S 관창-대천#2T/L GIS 정밀점검","2025-12-22 09:00","2025-12-24 18:00","취소","취소","연속"]
[157,"대전세종충남","청양","옥산장항#2 T/L","[11월취소시]['25년 청양P/O 170kV GIS 정밀점검 공사]","옥산S/S 옥산-장항#2T/L GIS 정밀점검","2025-12-15 09:00","2025-12-17 18:00","취소","취소","연속"]
[158,"대전세종충남","청양","옥산장항#1 T/L","[송전][주말작업X] 옥산-장항#1T/L 수평추락방지장치 설치","우상단 : 옥산-장항#1 우하단 : 동군산-장항#2 병가구간 수평추락방지장치 설치","2025-12-01 07:30","2025-12-02 18:00","취소","취소","매일"]
[159,"대전세종충남","청양","신서천옥산#2 T/L","[11월취소시]['25년 청양P/O 170kV GIS 정밀점검 공사]","옥산S/S 옥산-서천#2T/L GIS 정밀점검","2025-12-08 09:00","2025-12-10 18:00","취소","취소","연속"]
[160,"대전세종충남","청양","옥산장항#2 T/L","[송전][주말작업X] 옥산-장항#2T/L 수평추락방지장치 설치","우상단 : 옥산-장항#2 우하단 : 동군산-장항#1 병가구간 수평추락방지장치 설치","2025-12-03 07:30","2025-12-04 18:00","취소","취소","매일"]
[161,"대전세종충남","청양","동군산장항#1 T/L","[송전][주말작업X] 동군산-장항#1T/L 수평추락방지장치 설치","우상단 : 옥산-장항#2 우하단 : 동군산-장항#1 병가구간 수평추락방지장치 설치","2025-12-03 07:30","2025-12-04 18:00","취소","취소","매일"]
[162,"대전세종충남","청양","동군산장항#2 T/L","[송전][주말작업X] 동군산-장항#2T/L 수평추락방지장치 설치","우상단 : 옥산-장항#1 우하단 : 동군산-장항#2 병가구간 수평추락방지장치 설치","2025-12-01 07:30","2025-12-02 18:00","취소","취소","매일"]
[163,"전북","군산","군공소룡#1 T/L","군산P/O 노후배전반 대체공사","군산P/O 노후배전반 대체공사","2025-12-17 09:00","2025-12-19 18:00","2025-12-17 09:00","2025-12-19 18:00","연속"]
[164,"전북","군산","군공S/S #60 BUS","군공S/S PT집합반 대체공사","군공S/S PT집합반 대체공사","2025-12-30 09:00","2025-12-30 18:00","취소","취소","연속"]
[165,"전북","군산","군공S/S #60 BUS","군공S/S PT집합반 대체공사","군공S/S PT집합반 대체공사","2025-12-29 09:00","2025-12-29 15:00","취소","취소","연속"]
[166,"전북","군산","군공소룡#2 T/L","군산P/O 노후배전반 대체공사","군산P/O 노후배전반 대체공사","2025-12-22 09:00","2025-12-24 18:00","2025-12-22 09:00","2025-12-24 18:00","연속"]
[167,"전북","군산","군공S/S #65 BUS","군공S/S PT집합반 대체공사","군공S/S PT집합반 대체공사","2025-12-29 15:00","2025-12-29 18:00","취소","취소","연속"]
[168,"전북","군산","군산C/C #3 M.Tr CB","일진제 유사고장 재발관련 DS확인","일진제 유사고장 재발관련 DS확인","2025-12-02 09:00","2025-12-02 18:00","취소","취소","연속"]
[169,"전북","군산","군산C/C #2 M.Tr CB","일진제 유사고장 재발관련 DS확인","일진제 유사고장 재발관련 DS확인","2025-12-01 09:00","2025-12-01 18:00","취소","취소","연속"]
[170,"전북","군산","군산영등#2 T/L","군산-영등 휴전작업","- 피뢰기 보통점검 - CVT 보통점검 - 차단기 제작사 점검 - 차단기 보통점검","2025-12-04 09:00","2025-12-05 18:00","2025-12-04 09:00","2025-12-05 18:00","연속"]
[171,"전북","군산","군산영등#1 T/L","군산-영등 휴전작업","- 피뢰기 보통점검 - CVT 보통점검 - 차단기 제작사 점검","2025-12-02 09:00","2025-12-03 18:00","2025-12-02 09:00","2025-12-03 18:00","연속"]
[172,"전북","군산","군산영등#2 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-12-15 07:00","2025-12-21 18:00","취소","취소","연속"]
[173,"전북","군산","군산서군산#1 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-12-09 09:00","2025-12-10 18:00","취소","취소","연속"]
[174,"전북","군산","군산서군산#2 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-12-11 09:00","2025-12-12 18:00","취소","취소","연속"]
[175,"전북","군산","군산이리#2 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-12-15 07:00","2025-12-19 18:00","취소","취소","연속"]
[176,"전북","군산","군산이리#1 T/L"," 군산-이리 등 4개T/L OPGW 증설공사","- OPGW교체(24C→48C) : 20.4km - 가공지선(ACSR 97㎟) 철거후 OPGW(48C) 시설 : 17.2km","2025-12-20 07:00","2025-12-21 18:00","취소","취소","연속"]
[177,"전북","군산","내초군장#2 T/L","군산P/O 노후배전반 대체공사","군산P/O 노후배전반 대체공사","2025-12-29 09:00","2025-12-31 18:00","취소","취소","연속"]
[178,"전북","군산","동군산장항#2 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-12-29 09:00","2025-12-30 18:00","2025-12-29 09:00","2025-12-30 18:00","연속"]
[179,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사(중복)","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2025-12-15 09:00","2025-12-17 18:00","2025-12-15 09:00","2025-12-17 18:00","연속"]
[180,"전북","군산","군산동군산#1 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-12-22 09:00","2025-12-23 18:00","2025-12-22 09:00","2025-12-23 18:00","연속"]
[181,"전북","군산","군산동군산#2 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-12-24 09:00","2025-12-25 18:00","2025-12-24 09:00","2025-12-25 18:00","연속"]
[182,"전북","군산","새만금비응#1 T/L"," 동비응S/S 건설공사","○  M.Tr × 2Bank ○ 170kV GIS × 9CCT, 25.8kV E-GIS × 12CCT ○ 운영시스템 등 부대설비 공사 × 1식","2025-12-30 09:00","2025-12-31 09:00","2025-12-30 09:00","2025-12-31 09:00","연속"]
[183,"전북","군산","서군산소룡#2 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-12-03 09:00","2025-12-04 18:00","취소","취소","연속"]
[184,"전북","군산","서군산소룡#1 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-12-01 09:00","2025-12-02 18:00","취소","취소","연속"]
[185,"전북","군산","영등낭산#2 T/L","군산P/O 이상 차단기 보통점검","영등S/S  영등-낭산#2T/L 차단기 보통점검","2025-12-16 09:00","2025-12-16 18:00","2025-12-16 09:00","2025-12-16 18:00","연속"]
[186,"전북","군산","영등낭산#1 T/L","군산P/O 이상 차단기 보통점검","영등S/S  영등-낭산#1T/L 차단기 보통점검","2025-12-31 09:00","2025-12-31 18:00","2025-12-31 09:00","2025-12-31 18:00","연속"]
[187,"전북","군산","이리백산#1 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-12-08 09:00","2025-12-09 18:00","취소","취소","연속"]
[188,"전북","군산","군산이리#2 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-12-03 09:00","2025-12-04 18:00","취소","취소","연속"]
[189,"전북","군산","탄소이리#1 T/L","'24~25년 군산전력 가공송전협력업체 공사"," 이리-탄소T/L 피뢰기 설치공사 No.58~63","2025-12-18 07:00","2025-12-19 18:00","2025-12-18 07:00","2025-12-19 18:00","연속"]
[190,"전북","군산","군산이리#1 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-12-01 09:00","2025-12-02 18:00","2025-12-01 09:00","2025-12-02 18:00","연속"]
[191,"전북","군산","이리백산#2 T/L","군산P/O 170kV GIS 정밀점검공사","170kV GIS 정밀점검공사","2025-12-10 09:00","2025-12-11 18:00","취소","취소","연속"]
[192,"전북","군산","팔봉왕궁#1 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-12-02 09:00","2025-12-03 18:00","취소","취소","연속"]
[193,"전북","군산","팔봉왕궁#2 T/L","군산P/O 170kV GIS 정밀점검공사(중복)","군산P/O 170kV GIS 정밀점검공사","2025-12-04 09:00","2025-12-05 18:00","취소","취소","연속"]
[194,"전북","군산","팔봉왕궁#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-12-05 08:00","2025-12-05 18:00","취소","취소","매일"]
[195,"전북","군산","팔봉왕궁#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2025-12-12 08:00","2025-12-12 18:00","취소","취소","매일"]
[196,"전북","군산","팔봉두마#2 T/L","팔봉S/S  장기사용 GIS 교체공사","#3M.Tr 1차 GIS 교체","2025-12-01 09:00","2025-12-01 18:00","취소","취소","연속"]
[197,"전북","김제","부안동부안#1 T/L","모선구분차단기 설치공사(6200 무부하가압)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-12-31 15:00","2026-01-01 15:00","취소","취소","연속"]
[198,"전북","김제","백산김제#1 T/L","김제전력지사 장기사용 배전반 대체","백산,김제S/S 백산-김제#1T/L 보호반 대체","2025-12-17 09:00","2025-12-19 18:00","취소","취소","연속"]
[199,"전북","김제","백산김제#2 T/L","김제전력지사 장기사용 배전반 대체","백산,김제S/S 백산-김제#2T/L 보호반 대체","2025-12-22 09:00","2025-12-24 18:00","취소","취소","연속"]
[200,"전북","김제","김제부안#2 T/L","모선구분차단기 설치(6200)","부안S/S  모선구분차단기 설치공사 -  BUS SEC 2CCT 설치 -  BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2025-12-29 09:00","2026-01-06 18:00","취소","취소","연속"]
[201,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #2T/L 긴선(케이블타워) 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-12-21 07:00","2025-12-24 18:00","취소","취소","연속"]
[202,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #2T/L 전선이동 (가선로 → 본선로) 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-12-08 07:00","2025-12-11 18:00","취소","취소","연속"]
[203,"전북","김제","신김제동전주#1 T/L"," 완산분기T/L 건설공사","1. 작업내용 : #1T/L 전선이동 (가선로 → 본선로), 케이블타워 조립 및 긴선 2. 위치 : 전주시 완산구 석구동 일원 3. 규모 : ACSR 410㎟×2B×4C (0.81㎞, 지지물 4기)","2025-12-12 07:00","2025-12-20 18:00","취소","취소","연속"]
[204,"전북","김제","신김제전주#1 T/L","김제전력지사 기타설비 점검공사","신김제S/S  신김제-전주#1T/L CVT 보통점검","2025-12-17 09:00","2025-12-17 12:00","취소","취소","연속"]
[205,"전북","김제","신김제동전주#1 T/L","김제전력지사 기타설비 점검공사","신김제S/S  신김제-동전주#1T/L CVT 보통점검","2025-12-18 15:00","2025-12-18 18:00","취소","취소","연속"]
[206,"전북","직할","동전주태평#2 T/L","동전주-태평#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-12-29 09:00","2025-01-01 18:00","2025-12-29 09:00","2025-01-01 18:00","연속"]
[207,"전북","직할","신김제동전주#2 T/L","'25년도 변전설비 기타기기 점검공사","- LA, CVT 보통점검","2025-12-02 16:00","2025-12-02 22:00","취소","취소","연속"]
[208,"전북","직할","무주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치(북전주-진안T/L No.50~104, 무주분기T/L No.1~45) -  북전주-진안T/L No.50~104 -  무주분기T/L No.1~45","2025-12-05 07:30","2025-12-11 18:00","취소","취소","연속"]
[209,"전북","직할","북전주S/S #1 BUS","북전주S/S 6433 GIS 정밀점검","CB, DS 정밀점검","2025-12-15 09:00","2025-12-16 18:00","취소","취소","연속"]
[210,"전북","직할","북전주S/S #1 BUS","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-12-08 09:00","2025-12-09 18:00","취소","취소","연속"]
[211,"전북","직할","북전주진안 T/L","'25년도 변전설비 기타기기 점검공사","- LA 보통점검","2025-12-12 16:00","2025-12-12 22:00","취소","취소","연속"]
[212,"전북","직할","북전주S/S #2 BUS","북전주-봉동#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-12-24 09:00","2025-12-25 18:00","취소","취소","연속"]
[213,"전북","직할","북전주S/S #1 BUS","북전주-봉동#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-12-22 09:00","2025-12-23 18:00","취소","취소","연속"]
[214,"전북","직할","북전주봉동#1 T/L","북전주-봉동#1T/L GIS 정밀점검","CB, DS 정밀점검","2025-12-22 09:00","2025-12-25 18:00","취소","취소","연속"]
[215,"전북","직할","북전주용담수력 T/L","345kV 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.1~50","2025-12-01 07:30","2025-12-04 18:00","취소","취소","연속"]
[216,"전북","직할","북전주S/S #2 BUS","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-12-10 09:00","2025-12-11 18:00","취소","취소","연속"]
[217,"전북","직할","북전주봉동#2 T/L","북전주-봉동#2T/L GIS 정밀점검","CB, DS 정밀점검","2025-12-08 09:00","2025-12-11 18:00","취소","취소","연속"]
[218,"전북","직할","북전주봉동#1 T/L","6433 GIS 정밀점검 관련 무부하가압","6433 GIS 정밀점검 관련 무부하가압","2025-12-18 15:00","2025-12-18 16:00","취소","취소","연속"]
[219,"전북","직할","북전주S/S #2 BUS","북전주S/S 6433 GIS 정밀점검","CB, DS 정밀점검","2025-12-17 09:00","2025-12-18 18:00","취소","취소","연속"]
[220,"전북","직할","북전주봉동#1 T/L","6433 GIS 정밀점검 관련 무부하가압","6433 GIS 정밀점검 관련 무부하가압","2025-12-16 15:00","2025-12-16 16:00","취소","취소","연속"]
[221,"전북","직할","서곡태평#1 T/L","[4차수]태평S/S  장기사용 GIS 교체공사(최종무부하)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2025-12-04 14:00","2025-12-05 17:00","2025-12-04 14:00","2025-12-05 17:00","연속"]
[222,"광주전남","강진","남창해남CS#2 T/L","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-12-05 09:00","2025-12-07 15:00","취소","취소","연속"]
[223,"광주전남","강진","남창 모선연계T/L CB","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-12-07 07:00","2025-12-10 15:00","취소","취소","연속"]
[224,"광주전남","강진","남창해남CS#1 T/L","남창S/S 남창-해남C/S 인출변경 공사","남창-해남C/S 인출변경 × 1식","2025-12-07 07:00","2025-12-10 15:00","취소","취소","연속"]
[225,"광주전남","강진","보성벌교 T/L"," 보성-벌교T/L 안전이격확보 휴전","ㅇ 대상선로 :  보성-벌교T/L 1~2호 ㅇ 공사내용 : 송전선로 직하 보성군 생활폐기물 소각시설 설치사업 관련으로 작업자 안전, 비계 및 크레인 사용을 위한 안전이격확보 휴전","2025-12-22 07:00","2025-12-26 18:00","2025-12-22 07:00","2025-12-26 11:00","매일"]
[226,"광주전남","강진","보성벌교 T/L"," 보성-벌교T/L 안전이격확보 휴전","ㅇ 대상선로 :  보성-벌교T/L 1~2호 ㅇ 공사내용 : 송전선로 직하 보성군 생활폐기물 소각시설 설치사업 관련으로 작업자 안전, 비계 및 크레인 사용을 위한 안전이격확보 휴전","2025-12-01 07:00","2025-12-05 18:00","2025-12-01 07:00","2025-12-05 11:00","매일"]
[227,"광주전남","강진","삼호솔라시도 T/L CB","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","-170kV GIS 보통점검","2025-12-03 09:00","2025-12-03 14:00","2025-12-03 09:00","2025-12-03 14:00","연속"]
[228,"광주전남","강진","완도동제주HVDC(3연계선) CB","2024-2025년 #3HVDC 변환설비 위탁정비공사","완도-동제주 #3HVDC 연차점검","2025-12-08 09:00","2025-12-21 18:00","2025-12-08 09:00","2025-12-21 18:00","연속"]
[229,"광주전남","강진","완도완도CS T/L","인수점검 미비사항 조치(완도-완도CS T/L Line ES 투입관련)","완도변환소 연차점검(12/8~21) 시 Line ES 점검","2025-12-10 09:00","2025-12-10 18:00","2025-12-10 09:00","2025-12-10 18:00","연속"]
[230,"광주전남","강진","남창완도 T/L","'24-25년 강진전력지사 변전협력회사 공사","-170kV GIS 보통점검","2025-12-04 10:00","2025-12-04 18:00","2025-12-04 10:00","2025-12-04 18:00","연속"]
[231,"광주전남","강진","장흥보성 T/L","'24-25년 강진전력지사 변전협력회사 공사","-170kV GIS 공기배출밸브 개선","2025-12-01 09:00","2025-12-01 14:00","2025-12-06 16:00","2025-12-06 21:00","연속"]
[232,"광주전남","강진","해남금오에너지 T/L CB","'25년 강진전력지사 170kV 이상 GIS 정밀 및 보통점검 공사","-170kV GIS 보통점검","2025-12-02 09:00","2025-12-02 14:00","2025-12-02 09:00","2025-12-02 14:00","연속"]
[233,"광주전남","강진","화원진도#2 T/L","'24-25년 강진전력지사 변전협력회사 공사","-170kV GIS 차단기 조작시험","2025-12-03 14:00","2025-12-03 18:00","취소","취소","연속"]
[234,"광주전남","강진","화원진도#1 T/L","'24-25년 강진전력지사 변전협력회사 공사","-170kV GIS 차단기 조작시험","2025-12-03 10:00","2025-12-03 14:00","취소","취소","연속"]
[235,"광주전남","광주","신광주계림#1 T/L","2024~2025년 광주전력지사 송전 협력회사공사(추락방지)"," 신광주-계림T/L 수평추락방지장치 설치 8기","2025-12-15 07:00","2025-12-15 18:00","취소","취소","연속"]
[236,"광주전남","광주","계림S/S SEC CB 61600","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-12-08 09:00","2025-12-12 18:00","취소","취소","연속"]
[237,"광주전남","광주","계림S/S CB 6100","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-12-08 09:00","2025-12-12 18:00","취소","취소","연속"]
[238,"광주전남","광주","계림S/S SEC CB 66650","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2025-12-08 09:00","2025-12-12 18:00","취소","취소","연속"]
[239,"광주전남","광주","신광주계림#2 T/L","2024~2025년 광주전력지사 송전 협력회사공사(추락방지)"," 신광주-계림T/L 수평추락방지장치 설치 8기","2025-12-16 07:00","2025-12-16 18:00","취소","취소","연속"]
[240,"광주전남","광주","계림남광주 T/L"," 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2025-12-16 09:00","2025-12-23 18:00","2025-12-16 09:00","2025-12-23 18:00","연속"]
[241,"광주전남","광주","남광주화순#1 T/L"," 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2025-12-24 09:00","2025-12-31 18:00","취소","취소","연속"]
[242,"광주전남","광주","남광주화순#2 T/L","(안전거리휴전) 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2025-12-29 09:00","2025-12-31 18:00","취소","취소","연속"]
[243,"광주전남","광주","남광주소태 T/L","(안전거리 휴전) 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2025-12-16 09:00","2025-12-18 18:00","2025-12-16 09:00","2025-12-18 18:00","연속"]
[244,"광주전남","광주","계림남광주 T/L","(안전거리 휴전) 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2025-12-13 09:00","2025-12-15 18:00","2025-12-13 09:00","2025-12-15 18:00","연속"]
[245,"광주전남","광주","남광주소태 T/L"," 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2025-12-08 09:00","2025-12-15 18:00","2025-12-08 09:00","2025-12-15 18:00","연속"]
[246,"광주전남","광주","정공담양 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 (병가) - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가)","2025-12-01 07:00","2025-12-02 18:00","취소","취소","매일"]
[247,"광주전남","광주","담양김제 T/L","2024~25년 광주전력지사 송전 협력회사공사(피뢰기)"," 담양-김제T/L 피뢰기설치공사 33기","2025-12-01 07:00","2025-12-04 18:00","취소","취소","매일"]
[248,"광주전남","광주","신화순화순#1 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 -  신화순-화순#1T/L 1~5, 10~57호","2025-12-01 08:00","2025-12-05 18:00","취소","취소","매일"]
[249,"광주전남","광주","신화순화순#2 T/L","2025년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 피뢰기 갭혼 교체 -  신화순-화순#2T/L 1~5, 10~57호","2025-12-08 08:00","2025-12-12 18:00","취소","취소","매일"]
[250,"광주전남","광주","신화순화순#2 T/L","2024~25년 광주전력지사 송전 협력회사공사(추락방지)"," 신화순-화순#2T/L 추락방지 설치공사 17기","2025-12-08 07:00","2025-12-10 18:00","취소","취소","매일"]
[251,"광주전남","광주","담양일곡#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 담양-일곡#2 T/L 피뢰기 설치 - 대상 : 1~16, 173~189, 193~228호 (총 71기) - 병가구간 : 2~15호 (담양-정공 병가)","2025-12-01 07:00","2025-12-05 18:00","취소","취소","매일"]
[252,"광주전남","광주","하남장성#1 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치(병가) - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-12-08 07:00","2025-12-09 18:00","취소","취소","매일"]
[253,"광주전남","광주","장성영광#2 T/L"," 계림-승주 등 3개 T/L 피뢰기 설치공사"," 장성-영광#2 T/L 피뢰기 설치 - 대상 : 1~15, 21~68호 (총 64기) - 병가구간 : 2~15호 (하남-장성#1 병가) ※즉시가압(20분이내) 불가하나, 가압 요청 시 1시간 이내 가압 가능","2025-12-08 07:00","2025-12-12 18:00","취소","취소","매일"]
[254,"광주전남","광주","신광주장성#2 T/L","2024~25년 광주전력지사 송전 협력회사공사(가공지선)"," 신광주-장성 #2T/L 측 가공지선 교체공사 63~66호 3경간","2025-12-11 07:00","2025-12-10 18:00","취소","취소","매일"]
[255,"광주전남","광주","신화순화순#1 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#1T/L GIS 정밀점검","2025-12-08 09:00","2025-12-10 18:00","취소","취소","연속"]
[256,"광주전남","광주","신화순화순#2 T/L","2025년 광주전력지사 170kV GIS 점검 공사","2025년 광주전력지사 170kV GIS 점검 공사 - 화순S/S  신화순-화순#2T/L GIS 정밀점검","2025-12-15 09:00","2025-12-17 18:00","취소","취소","연속"]
[257,"광주전남","목포","남악북항#2 T/L","북항S/S  #4M.Tr 증설공사","무부하가압용","2025-12-18 10:00","2025-12-19 18:00","2025-12-18 18:00","2025-12-19 20:00","연속"]
[258,"광주전남","순천","광양하동#2 T/L","코타핀 교체(광양-하동#2)","코타핀 교체","2025-12-19 07:00","2025-12-19 18:00","2025-12-19 07:00","2025-12-19 18:00","연속"]
[259,"광주전남","순천","광양하동#1 T/L","코타핀 교체(광양-하동#1)","코타핀 교체","2025-12-18 07:00","2025-12-18 18:00","2025-12-18 07:00","2025-12-18 18:00","연속"]
[260,"광주전남","순천","광양순천#1 T/L"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#6(기설) ∼ J/B#10(신설)  XLPE 1,200(D)㎟ × 2C × 1.402km","2025-12-15 07:00","2025-12-28 18:00","취소","취소","연속"]
[261,"광주전남","순천","광양백운#2 T/L","SB댐퍼설치(광양-백운#2)","SB댐퍼설치","2025-12-10 13:00","2025-12-10 18:00","2025-12-10 13:00","2025-12-10 18:00","연속"]
[262,"광주전남","순천","광양백운#1 T/L","SB댐퍼설치(광양-백운#1)","SB댐퍼설치","2025-12-10 07:00","2025-12-10 13:00","2025-12-10 07:00","2025-12-10 13:00","연속"]
[263,"광주전남","순천","광양순천#2 T/L"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#6(기설) ∼ J/B#10(신설)  XLPE 1,200(D)㎟ × 2C × 1.402km","2025-12-01 07:00","2025-12-14 18:00","취소","취소","연속"]
[264,"광주전남","순천","장흥벌교 T/L","피뢰기 설치(장흥-벌교)","피뢰기 설치","2025-12-08 07:00","2025-12-09 18:00","취소","취소","매일"]
[265,"광주전남","순천","서순천벌교#2 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 서순천-벌교#2T/L GIS 정밀점검","2025-12-17 16:00","2025-12-18 10:00","2025-12-17 16:00","2025-12-18 10:00","연속"]
[266,"광주전남","순천","소라서순천#1 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 소라-서순천#1T/L GIS 정밀점검","2025-12-01 16:00","2025-12-02 10:00","2025-12-01 16:00","2025-12-02 10:00","연속"]
[267,"광주전남","순천","소라서순천#2 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 소라-서순천#2T/L GIS 정밀점검","2025-12-03 16:00","2025-12-04 10:00","2025-12-03 16:00","2025-12-04 10:00","연속"]
[268,"광주전남","순천","승주서순천 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 승주-서순천T/L GIS 정밀점검","2025-12-08 16:00","2025-12-09 10:00","2025-12-08 16:00","2025-12-09 10:00","연속"]
[269,"광주전남","순천","서순천주암HP T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 서순천-주암HP T/L GIS 정밀점검","2025-12-10 16:00","2025-12-11 10:00","2025-12-10 16:00","2025-12-11 10:00","연속"]
[270,"광주전남","순천","서순천벌교#1 T/L","2025년 순천전력지사 170kV GIS 정밀점검공사","서순천S/S 서순천-벌교#1T/L GIS 정밀점검","2025-12-15 16:00","2025-12-16 10:00","2025-12-15 16:00","2025-12-16 10:00","연속"]
[271,"광주전남","순천","서순천벌교#2 T/L","피뢰기 설치(서순천-벌교#2)","피뢰기 설치","2025-12-01 07:00","2025-12-05 18:00","취소","취소","매일"]
[272,"광주전남","순천","황금세풍#2 T/L","조작불량관련 기계적 인터록 점검","조작불량관련 기계적 인터록 점검","2025-12-04 10:00","2025-12-04 14:00","취소","취소","연속"]
[273,"광주전남","순천","황금세풍#1 T/L","조작불량관련 기계적 인터록 점검","조작불량관련 기계적 인터록 점검","2025-12-04 14:00","2025-12-04 18:00","취소","취소","연속"]
[274,"광주전남","순천","세풍율촌#1 T/L","조작불량관련 기계적 인터록 점검","조작불량관련 기계적 인터록 점검","2025-12-05 10:00","2025-12-05 14:00","취소","취소","연속"]
[275,"광주전남","순천","세풍율촌#2 T/L","조작불량관련 기계적 인터록 점검","조작불량관련 기계적 인터록 점검","2025-12-05 14:00","2025-12-05 18:00","취소","취소","연속"]
[276,"광주전남","순천","소라서순천#1 T/L","애자련 보강(소라-서순천#1)","애자련 보강","2025-12-11 07:00","2025-12-11 18:00","취소","취소","연속"]
[277,"광주전남","순천","소라서순천#2 T/L","애자련 보강(소라-서순천#2)","애자련 보강","2025-12-12 07:00","2025-12-12 18:00","취소","취소","연속"]
[278,"광주전남","순천","승주서순천 T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-서순천, 화순-승주2(통보분) 병가) (휴일작업포함, 1시간내 가압가능)","2025-12-17 07:00","2025-12-31 18:00","취소","취소","매일"]
[279,"광주전남","순천","승주S/S #2 BUS","승주S/S  #4M.Tr 증설공사","170kV GIS 1CCT 설치","2025-12-15 09:00","2025-12-17 14:00","취소","취소","연속"]
[280,"광주전남","순천","승주주암HP T/L"," 승주-서순천 T/L 추락방지시설 설치공사","4회선 수평추락방지 설치 (승주-주암HP, 화순-승주1(통보분) 병가) (휴일작업포함, 1시간내 가압가능)","2025-12-02 07:00","2025-12-16 18:00","취소","취소","매일"]
[281,"광주전남","순천","승주S/S #1 BUS","승주S/S  #4M.Tr 증설공사","170kV GIS 1CCT 설치","2025-12-08 09:00","2025-12-12 14:00","취소","취소","연속"]
[282,"광주전남","순천","승주주암HP T/L","항공장애구 교체(승주-주암HP)","항공장애구 교체","2025-12-15 07:00","2025-12-15 18:00","취소","취소","연속"]
[283,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체용 무부하가압","2025-12-17 17:00","2025-12-18 09:00","취소","취소","연속"]
[284,"광주전남","순천","여수소라#2 T/L"," 여수-소라 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (2,3호 : 여수-소라2, 여천-여수2 병가) (1시간내 가압가능)","2025-12-12 07:00","2025-12-12 18:00","취소","취소","연속"]
[285,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-12-18 09:00","2025-12-26 09:00","취소","취소","연속"]
[286,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-12-18 09:00","2025-12-26 09:00","취소","취소","연속"]
[287,"광주전남","순천","여수소라#1 T/L"," 여수-소라 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (2,3호 : 여수-소라1, 여천-여수1 병가) (1시간내 가압가능)","2025-12-22 07:00","2025-12-22 18:00","취소","취소","연속"]
[288,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-12-26 09:00","2025-12-26 18:00","취소","취소","연속"]
[289,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-12-05 09:00","2025-12-26 18:00","취소","취소","연속"]
[290,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-12-05 09:00","2025-12-10 09:00","취소","취소","연속"]
[291,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-12-05 09:00","2025-12-10 09:00","취소","취소","연속"]
[292,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-12-05 09:00","2025-12-26 18:00","취소","취소","연속"]
[293,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2025-12-10 09:00","2025-12-18 09:00","취소","취소","연속"]
[294,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2025-12-10 09:00","2025-12-18 09:00","취소","취소","연속"]
[295,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-12-11 17:00","2025-12-11 21:00","취소","취소","연속"]
[296,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2025-12-12 17:00","2025-12-12 21:00","취소","취소","연속"]
[297,"광주전남","순천","여수소라#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체 무부하가압용","2025-12-17 17:00","2025-12-18 09:00","취소","취소","연속"]
[298,"광주전남","순천","여수TP용성#2 T/L","SB댐퍼 설치(여수TP-용성)","SB댐퍼 설치","2025-12-17 07:00","2025-12-17 18:00","취소","취소","연속"]
[299,"광주전남","순천","여수T/P #66 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-12-17 09:00","2025-12-18 18:00","취소","취소","연속"]
[300,"광주전남","순천","GS CALTEX여수TP# 1T/L CB","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-12-17 09:00","2025-12-18 18:00","취소","취소","연속"]
[301,"광주전남","순천","호남TP여수TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP2, 여천-여수1 병가) (2호 : 여천-호남TP2, 호남TP-여수TP2 병가) (1시간내 가압가능)","2025-12-19 07:00","2025-12-19 18:00","취소","취소","연속"]
[302,"광주전남","순천","GS CALTEX여수TP# 2T/L CB","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-12-22 09:00","2025-12-23 18:00","취소","취소","연속"]
[303,"광주전남","순천","여수T/P #65 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-12-22 09:00","2025-12-23 18:00","취소","취소","연속"]
[304,"광주전남","순천","호남TP여수TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가) (1시간내 가압가능)","2025-12-15 07:00","2025-12-15 18:00","취소","취소","연속"]
[305,"광주전남","순천","호남TP여수TP#2 T/L","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-12-09 14:00","2025-12-10 18:00","취소","취소","연속"]
[306,"광주전남","순천","여수T/P #66 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-12-09 09:00","2025-12-10 18:00","취소","취소","연속"]
[307,"광주전남","순천","여수T/P CB 6183","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-12-08 09:00","2025-12-10 18:00","취소","취소","연속"]
[308,"광주전남","순천","여수TP용성#2 T/L","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-12-08 09:00","2025-12-09 14:00","취소","취소","연속"]
[309,"광주전남","순천","여수TP용성#1 T/L","SB댐퍼 설치(여수TP-용성)","SB댐퍼 설치","2025-12-16 07:00","2025-12-16 18:00","취소","취소","연속"]
[310,"광주전남","순천","여수T/P #61 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2025-12-08 09:00","2025-12-09 14:00","취소","취소","연속"]
[311,"광주전남","순천","여수TP화치#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP-화치#2T/L 보호배전반 대체","2025-12-08 09:00","2025-12-10 18:00","취소","취소","연속"]
[312,"광주전남","순천","여수TP여천#1 T/L"," 여수TP-여천 T/L 폴리머점퍼지지애자 설치공사","#1T/L 폴리머점퍼지지애자 설치","2025-12-22 07:00","2025-12-26 18:00","취소","취소","매일"]
[313,"광주전남","순천","여천호남TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP2, 여천-여수1 병가) (2호 : 여천-호남TP2, 호남TP-여수TP2 병가) (휴일작업포함, 1시간내 가압가능)","2025-12-17 07:00","2025-12-31 18:00","취소","취소","매일"]
[314,"광주전남","순천","여천여수#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP2, 여천-여수1 병가) (2호 : 여천-호남TP2, 호남TP-여수TP2 병가) (휴일작업포함, 1시간내 가압가능)","2025-12-22 07:00","2025-12-31 18:00","취소","취소","매일"]
[315,"광주전남","순천","여천여수#2 T/L","바스프여천T/L 송전선로 선종교체공사(바스프여천T/L 무부하 가압)","바스프여천T/L 고객측 송전선로 선종교체공사(바스프여천T/L 무부하 가압)","2025-12-24 09:00","2025-12-25 09:00","2025-12-24 09:00","2025-12-25 09:00","연속"]
[316,"광주전남","순천","여천여수산단#1 T/L","바스프여천T/L 송전선로 선종교체공사(바스프여천T/L 무부하 가압)","바스프여천T/L 고객측 송전선로 선종교체공사(바스프여천T/L 무부하 가압)","2025-12-24 09:00","2025-12-25 09:00","2025-12-24 09:00","2025-12-25 09:00","연속"]
[317,"광주전남","순천","여수TP여천#2 T/L"," 여수TP-여천 T/L 폴리머점퍼지지애자 설치공사","#2T/L 폴리머점퍼지지애자 설치","2025-12-29 07:00","2025-12-31 18:00","취소","취소","매일"]
[318,"광주전남","순천","여천여수#1 T/L","여천S/S  기기기초 공사","여천S/S  기기기초 공사","2025-12-01 09:00","2025-12-31 18:00","취소","취소","매일"]
[319,"광주전남","순천","여천여수#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가)","2025-12-08 07:00","2025-12-12 18:00","취소","취소","매일"]
[320,"광주전남","순천","여천호남TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가) (휴일작업포함, 1시간내 가압가능)","2025-12-02 07:00","2025-12-16 18:00","취소","취소","매일"]
[321,"광주전남","순천","여천호남TP#1 T/L","여천S/S  기기기초 공사","여천S/S  기기기초 공사","2025-12-01 09:00","2025-12-31 18:00","취소","취소","매일"]
[322,"광주전남","순천","여수TP여천#2 T/L","여천S/S  기기기초 공사","여천S/S  기기기초 공사","2025-12-01 09:00","2025-12-31 18:00","취소","취소","매일"]
[323,"광주전남","순천","여수TP여천#1 T/L","여천S/S  기기기초 공사","여천S/S  기기기초 공사","2025-12-01 09:00","2025-12-31 18:00","취소","취소","매일"]
[324,"광주전남","순천","여천호남TP#2 T/L","여천S/S  기기기초 공사","여천S/S  기기기초 공사","2025-12-01 09:00","2025-12-31 18:00","취소","취소","매일"]
[325,"광주전남","순천","여천여수#2 T/L","여천S/S  기기기초 공사","여천S/S  기기기초 공사","2025-12-01 09:00","2025-12-31 18:00","취소","취소","매일"]
[326,"광주전남","순천","여수TP용성#2 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","여수TP-용성 #2T/L 수평 추락방지시설 설치 (1,3호 : 여수TP-용성2 2회선/ 2,2.1호 : 여수TP-용성2, 용성-여수산단2 병가) (1시간내 가압가능)","2025-12-17 07:00","2025-12-18 18:00","취소","취소","매일"]
[327,"광주전남","순천","용성여수산단#1 T/L","SB댐퍼 설치(여수TP-용성)","SB댐퍼 설치","2025-12-17 07:00","2025-12-17 18:00","취소","취소","연속"]
[328,"광주전남","순천","용성여수산단#2 T/L","SB댐퍼 설치(여수TP-용성)","SB댐퍼 설치","2025-12-16 07:00","2025-12-16 18:00","취소","취소","연속"]
[329,"광주전남","순천","여수TP용성#1 T/L","불량 유압압력계 교체","불량 유압압력계 교체","2025-12-15 09:00","2025-12-16 18:00","취소","취소","연속"]
[330,"광주전남","순천","용성여수산단#2 T/L"," 용성-여수산단T/L 폴리머점퍼지지애자 설치공사","용성-여수산단#2T/L 폴리머점퍼지지애자 설치","2025-12-15 07:00","2025-12-19 18:00","취소","취소","매일"]
[331,"광주전남","순천","여수TP용성#1 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","여수TP-용성 #1T/L 수평 추락방지시설 설치 (1,3호 : 여수TP-용성1 2회선/ 2,2.1호 : 여수TP-용성1, 용성-여수산단1 병가) (1시간내 가압가능)","2025-12-10 07:00","2025-12-11 18:00","취소","취소","매일"]
[332,"광주전남","순천","용성여수산단#1 T/L"," 용성-여수산단T/L 폴리머점퍼지지애자 설치공사","용성-여수산단#1T/L 폴리머점퍼지지애자 설치","2025-12-08 07:00","2025-12-12 18:00","취소","취소","매일"]
[333,"광주전남","순천","율촌민자#1 T/L"," 율촌민자 T/L 추락방지시설 설치공사","#1T/L 수평추락방지시설 설치(1시간내 가압가능)","2025-12-15 07:00","2025-12-19 18:00","취소","취소","매일"]
[334,"광주전남","순천","율촌화치#1 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (45~67호 : 율촌-화치1, 율촌-여수산단2 병가 68호 : 율촌-화치1, 순천-율촌2 병가) (1시간내 가압가능)","2025-12-15 07:00","2025-12-19 18:00","취소","취소","매일"]
[335,"광주전남","순천","율촌여수산단#2 T/L"," 율촌-여수산단 T/L 추락방지시설 설치공사","#2T/L 수평추락방지시설 설치 (1시간내 가압가능)","2025-12-15 07:00","2025-12-26 18:00","취소","취소","매일"]
[336,"광주전남","순천","순천율촌#1 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (45~67호 : 율촌-화치2, 율촌-여수산단1 병가 68호 : 율촌-화치2, 순천-율촌1 병가) (1시간내 가압가능)","2025-12-12 07:00","2025-12-12 18:00","2025-12-12 07:00","2025-12-12 18:00","연속"]
[337,"광주전남","순천","율촌화치#2 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (45~67호 : 율촌-화치2, 율촌-여수산단1 병가 68호 : 율촌-화치2, 순천-율촌1 병가) (1시간내 가압가능)","2025-12-08 07:00","2025-12-12 18:00","취소","취소","매일"]
[338,"광주전남","순천","세풍율촌#2 T/L","조작불량관련 메커니즘 점검","조작불량관련 메커니즘 점검","2025-12-05 10:00","2025-12-05 18:00","2025-12-05 10:00","2025-12-05 18:00","연속"]
[339,"광주전남","순천","세풍율촌#1 T/L","조작불량관련 메커니즘 점검","조작불량관련 메커니즘 점검","2025-12-04 10:00","2025-12-04 18:00","2025-12-04 10:00","2025-12-04 18:00","연속"]
[340,"광주전남","순천","율촌여수산단#1 T/L"," 율촌-여수산단 T/L 추락방지시설 설치공사","#1T/L 수평추락방지시설 설치 (1시간내 가압가능)","2025-12-02 07:00","2025-12-12 18:00","취소","취소","매일"]
[341,"광주전남","순천","율촌민자#2 T/L"," 율촌민자 T/L 추락방지시설 설치공사","#2T/L 수평추락방지시설 설치(1시간내 가압가능)","2025-12-22 07:00","2025-12-26 18:00","취소","취소","매일"]
[342,"광주전남","순천","순천율촌#2 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","4회선 수평추락방지시설 설치 (45~67호 : 율촌-화치1, 율촌-여수산단2 병가 68호 : 율촌-화치1, 순천-율촌2 병가) (1시간내 가압가능)","2025-12-19 07:00","2025-12-19 18:00","2025-12-19 07:00","2025-12-19 18:00","연속"]
[343,"광주전남","순천","여수TP화치#2 T/L","345kV 여수TP-화치 T/L 폴리머점퍼지지애자 설치공사","여수TP-화치 #2T/L 폴리머점퍼지지애자 설치","2025-12-15 07:00","2025-12-19 18:00","취소","취소","매일"]
[344,"광주전남","순천","여수TP화치#1 T/L","345kV 여수TP-화치 T/L 폴리머점퍼지지애자 설치공사","여수TP-화치 #1T/L 폴리머점퍼지지애자 설치","2025-12-08 07:00","2025-12-12 18:00","취소","취소","매일"]
[345,"광주전남","직할","남광주금천#2 T/L","금천S/S  #4M.Tr 설치공사"," GIS 1CCT 설치(무부하가압용)","2025-12-04 09:00","2025-12-05 09:00","취소","취소","연속"]
[346,"광주전남","직할","남광주금천#2 T/L","금천S/S  #4M.Tr 설치공사"," GIS 1CCT 설치(무부하가압용)","2025-12-10 09:00","2025-12-11 09:00","취소","취소","연속"]
[347,"광주전남","직할","덕림평동#2 T/L","2024~2025년 광주전남본부 직할 변전협력회사 공사","덕림-평동#2 T/L L A,B,C 대체","2025-12-01 09:00","2025-12-01 18:00","2025-12-01 09:00","2025-12-01 18:00","연속"]
[348,"광주전남","직할","덕림평동#1 T/L","2024~2025년 광주전남본부 직할 변전협력회사 공사","덕림-평동#1 T/L L A,B,C 대체","2025-12-02 09:00","2025-12-02 18:00","2025-12-02 09:00","2025-12-02 18:00","연속"]
[349,"대구","달성","고령쌍림#2 T/L","고령SS 고령-쌍림#2T/L LA 보통점검","고령SS 고령-쌍림#2T/L LA 보통점검","2025-12-09 09:00","2025-12-09 18:00","취소","취소","연속"]
[350,"대구","달성","논공S/S #1 EM.Tr CB","논공S/S FR-ESS 정기점검","논공S/S FR-ESS 정기점검","2025-12-01 09:00","2025-12-05 18:00","2025-12-01 09:00","2025-12-05 18:00","연속"]
[351,"대구","달성","쌍림합천#1 T/L","쌍림S/S 쌍림-합천#1/TL GIS 차단기시험","쌍림S/S 쌍림-합천#1/TL GIS 차단기시험","2025-12-10 09:00","2025-12-10 18:00","취소","취소","연속"]
[352,"대구","직할","동인내당#1 T/L","동인S/S 동인-내당 #1T/L GIS 보통점검","동인S/S 동인-내당 #1T/L GIS 보통점검","2025-12-06 09:00","2025-12-06 14:00","2025-12-06 09:00","2025-12-06 14:00","연속"]
[353,"대구","직할","동인내당#2 T/L","동인S/S 동인-내당 #2T/L GIS 보통점검","동인S/S 동인-내당 #2T/L GIS 보통점검","2025-12-06 14:00","2025-12-06 18:00","2025-12-06 14:00","2025-12-06 18:00","연속"]
[354,"대구","직할","산격침산#2 T/L","산격S/S  GIS 교체공사(1차수)","산격S/S  GIS 교체공사(1차수) - 무부하가압","2025-12-30 15:00","2025-12-30 17:00","취소","취소","연속"]
[355,"대구","직할","산격침산#2 T/L","산격S/S  GIS 교체공사(무부하가압용)","산격S/S  GIS 교체공사(1차수,6233,647 교체)","2025-12-30 13:00","2025-12-30 15:00","취소","취소","연속"]
[356,"대구","직할","산격침산#2 T/L","산격S/S  GIS 교체공사(무부하 가압용)","산격S/S  GIS 교체공사(1차수, 6233,647 대체)","2025-12-06 18:00","2025-12-07 18:00","2025-12-06 18:00","2025-12-07 18:00","연속"]
[357,"대구","직할","서침산침산 T/L","침산S/S 서침산-침산T/L GIS 보통점검","침산S/S 서침산-침산T/L GIS 보통점검","2025-12-13 09:00","2025-12-13 18:00","2025-12-13 09:00","2025-12-13 18:00","연속"]
[358,"대구","포항","건천천북#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","모선보호반 대체","2025-12-05 14:00","2025-12-05 14:30","취소","취소","연속"]
[359,"대구","포항","건천천북#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","모선보호반 대체","2025-12-05 13:00","2025-12-05 13:30","취소","취소","연속"]
[360,"대구","포항","아화건천#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","모선보호반 대체","2025-12-05 16:30","2025-12-05 17:00","취소","취소","연속"]
[361,"대구","포항","아화건천#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","모선보호반 대체","2025-12-05 15:00","2025-12-05 15:30","취소","취소","연속"]
[362,"대구","포항","신영일청하#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","신영일-청하#2T/L LA, PT 하자점검","2025-12-04 09:00","2025-12-04 18:00","취소","취소","연속"]
[363,"대구","포항","영일죽정#1 T/L CB"," 죽정S/S 건설공사 및 죽정분기T/L 건설공사"," 죽정S/S 건설공사 및 죽정분기T/L 건설공사","2025-12-02 08:00","2025-12-04 18:00","취소","취소","연속"]
[364,"대구","포항","울주외동#2 T/L"," 영일-입실 등 11개 T/L 피뢰기 설치공사"," 울주-외동#2T/L 피뢰기 설치공사(안전확보)","2025-12-02 07:00","2025-12-02 18:00","취소","취소","연속"]
[365,"대구","포항","울주입실#2 T/L","2024~25년도 포항전력지사 변전협력회사 공사","송전선로보호반 대체","2025-12-16 09:00","2025-12-18 18:00","취소","취소","연속"]
[366,"대구","포항","울주입실#1 T/L","2024~25년도 포항전력지사 변전협력회사 공사","송전선로보호반 대체","2025-12-09 09:00","2025-12-11 18:00","취소","취소","연속"]
[367,"대구","포항","울주입실#1 T/L"," 신영일-천북 등 19개 T/L 추락방지장치 설치공사"," 울주-입실T/L 추락방지장치 설치","2025-12-01 07:00","2025-12-01 18:00","취소","취소","연속"]
[368,"경북","영주","봉화S/S 춘양전철#1T/L CB"," 봉화S/S 리모델링 공사","○ 외벽 마감재 교체(드라이비트 -> AL복합판넬, 화강석, 징크판넬)","2025-12-01 00:00","2025-12-05 04:00","2025-12-01 00:00","2025-12-05 04:00","매일"]
[369,"경북","영주","봉화S/S 춘양전철#2T/L CB"," 봉화S/S 리모델링 공사","○ 외벽 마감재 교체(드라이비트 -> AL복합판넬, 화강석, 징크판넬)","2025-12-01 00:00","2025-12-05 04:00","2025-12-01 00:00","2025-12-05 04:00","매일"]
[370,"경북","영주","영주S/S #1 EM.Tr CB","2024-25년 영주전력지사 변전협력회사 공사","6133GIS 하자점검. 조작기구부 점검","2025-12-15 09:00","2025-12-15 18:00","2025-12-15 09:00","2025-12-15 18:00","연속"]
[371,"경북","직할","안동풍산 T/L","24~25년 경북본부 직할 변전협력회사 공사","풍산S/S #60-#65 모선보호반 교체공사","2025-12-11 09:00","2025-12-11 12:00","취소","취소","연속"]
[372,"경북","직할","진보S/S #2 BUS","진보S/S  장기사용 GIS 교체공사(2차수)","진보S/S  장기사용 GIS 교체공사(2차수) -  GIS 2CCT 교체","2025-12-12 09:00","2025-12-13 09:00","2025-12-12 09:00","2025-12-13 09:00","연속"]
[373,"경북","직할","진보S/S #1 BUS","진보S/S  장기사용 GIS 교체공사(2차수)","진보S/S  장기사용 GIS 교체공사(2차수) -  GIS 2CCT 교체","2025-12-13 09:00","2025-12-17 18:00","2025-12-13 09:00","2025-12-17 18:00","연속"]
[374,"경북","직할","동안동진보#2 T/L","진보S/S  장기사용 GIS 교체공사(2차수)","진보S/S  장기사용 GIS 교체공사(2차수) -  GIS 2CCT 교체","2025-12-12 18:00","2025-12-17 18:00","2025-12-12 18:00","2025-12-17 18:00","연속"]
[375,"경북","구미","화동보은 T/L","24~25년 경북본부 구미전력지사 변전협력회사 공사","24~25년 경북본부 구미전력지사 변전협력회사 공사","2025-12-03 09:00","2025-12-03 14:00","취소","취소","연속"]
[376,"부산울산","동부산","노포정관#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","금구류 및 추락방지장치 설치","2025-12-11 07:00","2025-12-13 18:00","취소","취소","연속"]
[377,"부산울산","동부산","명례장안 T/L"," 명례S/S #3M.Tr 증설공사"," 명례S/S #3M.Tr 증설공사 - 6332 DS, 6333 CB 투입 후 무부하가압 - 6331 DS 투입 후 무부하가압","2025-12-18 10:00","2025-12-19 18:00","2025-12-18 10:00","2025-12-19 18:00","연속"]
[378,"부산울산","동부산","명례고리NP T/L","2025년 가공송전 순시점검 위탁공사","송전선로 인근 수목 정비","2025-12-15 07:00","2025-12-16 18:00","2025-12-15 07:00","2025-12-16 18:00","연속"]
[379,"부산울산","동부산","신울산명례#2 T/L","2024-2025년 동부산 가공송전협력회사 공사","금구류 및 추락방지장치 설치","2025-12-10 07:00","2025-12-10 18:00","취소","취소","연속"]
[380,"부산울산","동부산","신울산명례#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","금구류 및 추락방지장치 설치","2025-12-08 07:00","2025-12-09 18:00","취소","취소","연속"]
[381,"부산울산","동부산","명례장안 T/L","345kV 울주-울산TP 등 22개TL 송전철탑 정비공사","폴리머점퍼지지애자 설치","2025-12-22 07:00","2025-12-23 18:00","2025-12-22 07:00","2025-12-23 18:00","연속"]
[382,"부산울산","동부산","서창산막#1 T/L","345kV 울주-울산TP 등 22개TL 송전철탑 정비공사","수평 추락방지장치 설치( 노포-정관#1T/L No.23 휴전작업 안전확보차)","2025-12-13 07:00","2025-12-13 18:00","취소","취소","연속"]
[383,"부산울산","동부산","신양산구서#1 T/L","2025년 가공송전 순시점검 위탁공사","송전선로 인근 수목 정비","2025-12-01 07:00","2025-12-02 18:00","2025-12-01 07:00","2025-12-02 18:00","연속"]
[384,"부산울산","동부산","정관장안#2 T/L","2024-2025년 동부산 가공송전협력회사 공사","금구류 및 추락방지장치 설치","2025-12-04 07:00","2025-12-06 18:00","취소","취소","연속"]
[385,"부산울산","동부산","정관장안#1 T/L","2024-2025년 동부산 가공송전협력회사 공사","금구류 및 추락방지장치 설치","2025-12-01 07:00","2025-12-03 18:00","취소","취소","연속"]
[386,"부산울산","동부산","정보대연 T/L","25-26년 직할 지중송전 협력회사 공사","정보-대연T/L 지중송전 OF케이블 점검 및 지유 작업","2025-12-06 09:00","2025-12-06 18:00","2025-12-06 09:00","2025-12-06 18:00","연속"]
[387,"부산울산","동부산","좌동S/S CB 6200","좌동S/S  모선보호반 설치","좌동S/S  모선보호반 설치(60-65BUS PRO, 61-66BUS PRO)","2025-12-08 09:00","2025-12-12 18:00","2025-12-08 09:00","2025-12-12 18:00","연속"]
[388,"부산울산","동부산","좌동S/S SEC CB 65660","좌동S/S  모선보호반 설치","좌동S/S  모선보호반 설치(60-65BUS PRO, 61-66BUS PRO)","2025-12-08 09:00","2025-12-12 18:00","2025-12-08 09:00","2025-12-12 18:00","연속"]
[389,"부산울산","동부산","좌동S/S SEC CB 60610","좌동S/S  모선보호반 설치","좌동S/S  모선보호반 설치(60-65BUS PRO, 61-66BUS PRO)","2025-12-08 09:00","2025-12-12 18:00","2025-12-08 09:00","2025-12-12 18:00","연속"]
[390,"부산울산","북부산","북부산S/S #67 BUS","24-25 북부산 변전협력회사 총액공사","북부산S/S  #67 BUS 가스누기 조치","2025-12-22 08:00","2025-12-23 18:00","2025-12-22 08:00","2025-12-23 18:00","연속"]
[391,"부산울산","북부산","북부산물금 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 북부산-물금T/L 송전용피뢰기 설치 : No.24.1호(1기)","2025-12-07 08:00","2025-12-07 12:00","2025-12-07 08:00","2025-12-07 12:00","연속"]
[392,"부산울산","북부산","북부산물금 T/L","24-25 북부산 변전협력회사 총액공사","북부산S/S  #67 BUS 가스누기 조치관련 시험가압선로","2025-12-23 17:00","2025-12-23 18:00","2025-12-23 17:00","2025-12-23 18:00","연속"]
[393,"부산울산","북부산","북부산삼랑진PP T/L","25 북부산전력  GIS 정밀점검공사","삼랑진S/Y 북부산-삼랑진GIS 보통점검","2025-12-02 09:00","2025-12-02 18:00","2025-12-02 09:00","2025-12-02 18:00","연속"]
[394,"부산울산","북부산","언양석계#1 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 언양-석계#1T/L 송전용피뢰기 설치 No.36~41(6기)","2025-12-05 08:00","2025-12-05 18:00","2025-12-05 08:00","2025-12-05 18:00","연속"]
[395,"부산울산","북부산","언양석계#2 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 언양-석계#2T/L 송전용피뢰기 설치 No.32","2025-12-04 08:00","2025-12-04 10:00","2025-12-04 08:00","2025-12-04 10:00","연속"]
[396,"부산울산","북부산","양산산막#1 T/L","25 북부산전력  GIS 정밀점검공사"," 양산산막#1T/L GIS 보통점검","2025-12-01 09:00","2025-12-01 18:00","취소","취소","연속"]
[397,"부산울산","북부산","양산삼랑진PP T/L"," 양산분기T/L 고정형 폴리머애자 설치"," 양산분기T/L(회선명 : 양산-삼랑진T/L) 고정형 폴리머지지애자 설치(3~16호, 11기)","2025-12-09 07:30","2025-12-12 18:00","취소","취소","매일"]
[398,"부산울산","북부산","엄궁학장#1 T/L"," 엄궁-학장#1T/L 절연유 보충","1. 공사내용 : 엄궁EBG~J/B#14-1 급유구간 절연유 보충 2. 시공사 : 지중송전 협력회사(공영전력)","2025-12-12 09:00","2025-12-12 18:00","2025-12-12 09:00","2025-12-12 18:00","연속"]
[399,"부산울산","북부산","호포물금 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 호포-물금T/L 송전용피뢰기 설치 : No.37~39(3기)","2025-12-07 08:00","2025-12-07 12:00","2025-12-07 08:00","2025-12-07 11:00","연속"]
[400,"부산울산","북부산","북부산호포 T/L","345kV 북부산-고리NP T/L 상부재보강 및  피뢰기설치공사"," 북부산-호포T/L 송전용피뢰기 설치 : No.6~9(4기)","2025-12-07 13:00","2025-12-07 18:00","2025-12-07 14:00","2025-12-07 18:00","연속"]
[401,"부산울산","서부산","신김해지사#1 T/L","지사S/S  신김해-지사#1 GIS 정밀점검","지사S/S  신김해-지사#1 GIS 정밀점검","2025-12-08 08:00","2025-12-09 18:00","2025-12-08 08:00","2025-12-09 18:00","연속"]
[402,"부산울산","서부산","신김해지사#2 T/L","지사S/S  신김해-지사#2 GIS 정밀점검","지사S/S  신김해-지사#2 GIS 정밀점검","2025-12-10 09:00","2025-12-11 18:00","2025-12-10 09:00","2025-12-11 18:00","연속"]
[403,"부산울산","울산","남울산신온산#2 T/L"," 남울산-신온산 #2T/L 폴리머지지애자 설치공사","○폴리머지지애자 설치 2기 병가(345kV 신온산-남울산) : 19, 21[모선로 지지물 번호 기준]","2025-12-18 07:00","2025-12-18 18:00","2025-12-18 07:00","2025-12-18 18:00","연속"]
[404,"부산울산","울산","산하방어진#1 T/L"," 효문-방어진(산하-방어진)T/L 폴리머지지애자 설치공사","○폴리머지지애자 설치 5기 -병가(현대#2) : 23, 29 -병가 X : 11, 13, 16","2025-12-06 07:00","2025-12-07 18:00","2025-12-06 07:00","2025-12-07 18:00","연속"]
[405,"부산울산","울산","신울산두왕#2 T/L"," 폴리머지지애자 및 추락방지장치(수직) 설치공사","폴리머지지애자 설치 6기 : [1, 2, 7, 10, 11, 12] 2는 병가구간(신울산-울산#2) 수직추락방지장치 2기(1, 7)","2025-12-11 07:00","2025-12-15 18:00","취소","취소","연속"]
[406,"부산울산","울산","신울산울산#1 T/L"," 신울산-울산 #1T/L 폴리머지지애자 설치공사","ㅇ 폴리머지지애자 설치 5기 -병가(신울산-두왕 #1) : 3, 4 -병가X : 7, 11, 12 ㅇ 수직추락방지장치 설치 12기 - 1, 4, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15","2025-12-08 07:00","2025-12-10 18:00","취소","취소","연속"]
[407,"부산울산","울산","신울산두왕#1 T/L"," 폴리머지지애자 및 추락방지장치 설치공사","폴리머지지애자 설치공사 2기 [3, 4] 3는 병가구간(신울산-울산 #1, 석지), 4는 병가구간(신울산-울산 #1) 수직 추락방지장치 2기(1, 7 신울산-두왕 #1)","2025-12-08 07:00","2025-12-10 18:00","취소","취소","연속"]
[408,"부산울산","울산","신울산울산#2 T/L"," 폴리머지지애자 및 추락방지장치(수직) 설치공사","폴리머지지애자 설치 6기 : [1, 2, 7, 10, 11, 12] 2는 병가구간(신울산-두왕 #2) 수직추락방지장치 14기(신울산-울산 #2 12기 / 신울산-두왕 #2 2기)","2025-12-11 07:00","2025-12-15 18:00","취소","취소","연속"]
[409,"부산울산","울산","신울산언양#2 T/L"," 신울산-언양 #2T/L 폴리머지지애자 및 추락방지장치 설치공사","○추락방지장치 설치(수평) : 44 ○폴리머지지애자 설치 : 44","2025-12-01 07:00","2025-12-01 18:00","2025-12-01 07:00","2025-12-01 18:00","연속"]
[410,"부산울산","울산","옥동외동#1 T/L","옥동S/S  모선구분차단기 설치공사","GIS 설치 관련 감압 및 시험가압","2025-12-08 09:00","2025-12-13 18:00","취소","취소","연속"]
[411,"부산울산","울산","온산처용#2 T/L"," 온산-처용 #2T/L 폴리머지지애자 설치공사","○폴리머지지애자 설치공사 병가(신온산-남울산) : 3, 7, 8 [온산-처용 기준 지지물 번호]","2025-12-19 07:00","2025-12-19 18:00","2025-12-19 07:00","2025-12-19 18:00","연속"]
[412,"부산울산","울산","온산처용#2 T/L"," 온산-처용 #2T/L 폴리머지지애자 설치공사","○폴리머지지애자 설치공사 5기 : [15, 16, 17, 18, 19]","2025-12-02 07:00","2025-12-03 18:00","2025-12-02 07:00","2025-12-03 18:00","연속"]
[413,"부산울산","울산","온산처용#1 T/L"," 온산-처용 #1T/L 폴리머지지애자 설치공사","○폴리머지지애자 설치 3기 병가(신온산-남울산) : 22, 25, 29 [모선로 지지물번호기준]","2025-12-23 07:00","2025-12-24 18:00","2025-12-23 07:00","2025-12-24 18:00","연속"]
[414,"부산울산","울산","울주외동#1 T/L","345kV 울주S/S 장기사용 GIS 교체공사","집감반 실규설치 관련 6C7 Bay 결선 및 시험작업","2025-12-01 08:00","2025-12-01 18:00","2025-12-01 08:00","2025-12-01 18:00","연속"]
[415,"부산울산","울산","울주외동#2 T/L","345kV 울주S/S 장기사용 GIS 교체공사","집감반 실규설치 관련 6B7 Bay 결선 및 시험작업","2025-12-02 08:00","2025-12-02 18:00","2025-12-02 08:00","2025-12-02 18:00","연속"]
[416,"부산울산","울산","신울산웅촌#1 T/L"," 신울산-웅촌 #1T/L 폴리머지지애자 설치공사","○폴리머지지애자 설치 2기 : [3, 4]","2025-12-04 07:00","2025-12-04 18:00","2025-12-04 07:00","2025-12-04 18:00","연속"]
[417,"부산울산","울산","신울산웅촌#1 T/L"," 신울산-웅촌 #1 T/L폴리머지지애자 설치공사","○ 폴리머지지애자 설치 : 3, 4","2025-12-15 07:00","2025-12-15 18:00","취소","취소","연속"]
[418,"부산울산","울산","효문방어진 T/L"," 효문-방어진T/L 폴리머지지애자 설치공사","○폴리머지지애자 설치 5기 - 병가(현대 #1) : 21, 22, 23, 28 - 병가 X : 18","2025-12-13 07:00","2025-12-14 18:00","2025-12-13 07:00","2025-12-14 18:00","연속"]
[419,"부산울산","직할","부산수정#2 T/L","25-26년 서부산전력지사 지중송전설비 협력회사 공사","OF케이블 접속함 절연유 채유작업","2025-12-06 09:00","2025-12-07 16:00","2025-12-06 09:00","2025-12-07 16:00","연속"]
[420,"부산울산","직할","부산수정#1 T/L","25-26년 서부산전력지사 지중송전설비 협력회사 공사","OF케이블 접속함 절연유 채유작업","2025-12-06 09:00","2025-12-07 16:00","2025-12-06 09:00","2025-12-07 16:00","연속"]
[421,"경남","김해송변전부","신김해진례#1 T/L"," 진례S/S #1M.Tr 증설공사(최초가압)"," 진례S/S #1M.Tr 증설공사(최초가압)","2025-12-13 09:00","2025-12-14 18:00","2025-12-13 09:00","2025-12-14 18:00","연속"]
[422,"경남","진주","하동정촌#2 T/L","하동S/S 하동-정촌#2T/L GIS 보통 및 LA 보통, PT 보통","하동S/S 하동-정촌#2T/L GIS 보통 및 LA 보통, PT 보통","2025-12-05 09:00","2025-12-05 16:00","2025-12-05 09:00","2025-12-05 16:00","연속"]
[423,"경남","진주","하동하동화력 T/L","하동-하동화력T/L 보호배전반 대체(하동측,하동화력측)","하동-하동화력T/L 보호배전반 대체(하동,하동화력측)","2025-12-01 09:00","2025-12-03 18:00","2025-12-01 09:00","2025-12-03 18:00","연속"]
[424,"경남","통영","거류통영#1 T/L","거류개폐소  거류-통영 #1T/L GIS 초기점검 등","거류개폐소  거류-통영 #1T/L GIS 초기점검 통영SS  거류-통영 #1T/L GIS 보통점검","2025-12-13 09:30","2025-12-13 18:00","취소","취소","연속"]
[425,"경남","통영","거류통영#2 T/L","거류개폐소  거류-통영 #2T/L GIS 초기점검 등","거류개폐소  거류-통영 #2T/L GIS 초기점검 통영SS  거류-통영 #2T/L GIS 보통점검","2025-12-14 09:30","2025-12-14 18:00","취소","취소","연속"]
[426,"경남","통영","고성통영CC#1 T/L","고성SS 등  고성-통영복합#1T/L GIS 초기점검 등","고성SS  고성-통영복합#1T/L LA A~C상 보통점검 통영복합SS  고성-통영복합#1T/L GIS 초기점검","2025-12-07 09:30","2025-12-07 18:00","취소","취소","연속"]
[427,"경남","함안","신마산칠서#1 T/L","항공번호찰 교체공사","신마산-칠서T/L 10, 40호 항공번호찰 교체(설치 각1, 철거 각1)","2025-12-02 07:00","2025-12-02 18:00","취소","취소","연속"]
[428,"경남","함안","신마산중리#2 T/L"," 신마산-중리#2T/L 피뢰기 설치공사"," 신마산-중리#2T/L 1,24~32호(10기) 피뢰기 설치","2025-12-06 07:00","2025-12-06 18:00","2025-12-06 07:00","2025-12-06 18:00","연속"]
[429,"경남","함안","중리가야#2 T/L"," 중리-가야#1T/L 피뢰기 설치공사(안전이격거리)"," 중리-가야#1T/L 40~51호 피뢰기 설치공사 안전이격거리 확보_4회선 병가철탑(수직배열) 동시휴전 필요","2025-12-07 07:00","2025-12-07 18:00","2025-12-07 07:00","2025-12-07 18:00","연속"]
[430,"경남","함안","중리가야#1 T/L"," 중리-가야#1T/L 피뢰기 설치공사"," 중리-가야#1T/L 40~51호(8기) 피뢰기 설치","2025-12-06 07:00","2025-12-07 18:00","2025-12-06 07:00","2025-12-07 18:00","매일"]
[431,"경남","함안","창녕초동#1 T/L","항공번호찰 교체공사","창녕-초동T/L 10호 항공번호찰 교체(설치2, 철거 2)","2025-12-01 07:00","2025-12-01 12:00","취소","취소","연속"]
[432,"경남","함안","창녕초동#1 T/L","초동-밀양T/L OPGW 교체공사","OPGW 6km 교체 및 항공장애표시구 87개 설치","2025-12-04 07:00","2025-12-05 18:00","취소","취소","연속"]
[433,"경남","함안","초동밀양#1 T/L"," 초동-밀양T/L 항공구 설치 철탑 보강 및 OPGW 교체공사"," 초동-밀양T/L 9호 등 5기 철탑보강[함안전력] 및 6-2호~16호 OPGW 교체공사[직할 전자제어]","2025-12-06 07:00","2025-12-09 18:00","취소","취소","연속"]
[434,"경남","함안","초동밀양#2 T/L"," 초동-밀양T/L 항공구 설치 철탑 보강 및 OPGW 교체공사"," 초동-밀양T/L 9호 등 5기 철탑보강[함안전력] 및 6-2호~16호 OPGW 교체공사[직할 전자제어]","2025-12-03 07:00","2025-12-07 18:00","취소","취소","연속"]