{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":9,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"345설비","index":0,"n_rows":63,"n_cols":12,"rows_kept":63,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2026년도 1월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"남서울","직할","신문래S/S #3 Sh.R CB","신문래S/S  다빈도 개폐장치 정밀점검","신문래S/S  다빈도 개폐장치 정밀점검","2026-01-26 09:00","2026-01-30 18:00","2026-01-26 09:00","2026-01-30 18:00","연속"]
[2,"강원","강릉","신양양S/S CB 7572","신양양S/S STATCOM 변환설비 설치공사","신양양 STATCOM 부하시험","2026-01-02 09:00","2026-01-31 18:00","2026-01-02 09:00","2026-01-31 18:00","연속"]
[3,"강원","강릉","신양양S/S CB 7500","신양양S/S STATCOM 변환설비 설치공사","신양양 STATCOM 부하시험","2026-01-02 09:00","2026-01-31 18:00","2026-01-02 09:00","2026-01-31 18:00","연속"]
[4,"충북","직할","신청주S/S #3 M.Tr"," 신청주S/S 종합예방진단시스템 설치공사"," 신청주S/S 종합예방진단시스템 설치","2026-01-29 09:00","2026-01-29 18:00","2026-01-29 09:00","2026-01-29 18:00","연속"]
[5,"충북","직할","신청주S/S #2 M.Tr"," 신청주S/S 종합예방진단시스템 설치공사"," 신청주S/S 종합예방진단시스템 설치","2026-01-28 09:00","2026-01-28 18:00","2026-01-28 09:00","2026-01-28 18:00","연속"]
[6,"충북","직할","신청주S/S #1 M.Tr"," 신청주S/S 종합예방진단시스템 설치공사"," 신청주S/S 종합예방진단시스템 설치","2026-01-27 09:00","2026-01-27 18:00","2026-01-27 09:00","2026-01-27 18:00","연속"]
[7,"대전세종충남","청양","청양신온양#1 T/L","[변전총액] 청양P/O 변전협력 총액공사"," 73BAY BF PNL 교체작업","2026-01-12 09:00","2026-01-16 18:00","취소","취소","연속"]
[8,"대전세종충남","청양","신옥천청양 T/L"," 신옥천청양 T/L 지장수목벌채"," 신옥천청양 T/L 지장수목벌채","2026-01-06 09:00","2026-01-07 18:00","취소","취소","매일"]
[9,"대전세종충남","청양","신계룡청양 T/L"," 신계룡청양 T/L 지장수목벌채"," 신계룡청양 T/L 지장수목벌채","2026-01-08 09:00","2026-01-09 18:00","취소","취소","매일"]
[10,"대전세종충남","청양","청양군산#2 T/L","[변전총액] 청양P/O 변전협력 총액공사"," 73BAY BF PNL 교체작업","2026-01-12 09:00","2026-01-16 18:00","취소","취소","연속"]
[11,"전북","직할","신남원광양#1 T/L","신남원S/S  #2M.Tr 설치공사 BF PNL 개조","75BAY B/F PNL 개조작업","2026-01-26 09:00","2026-01-30 18:00","취소","취소","연속"]
[12,"광주전남","광주","신광주S/S #2 M.Tr","광주전력지사 변전협력회사 공사","신광주S/S #2M.Tr 초기점검, 1차 GIS 조작시험, 2차 GIS 보통점검 1,3차 PT 초기점검, 1,2,3차 LA 보통점검, 2-1,2 Sh.R 보통점검","2026-01-26 09:00","2026-01-29 18:00","취소","취소","연속"]
[13,"광주전남","광주","신광주S/S CB 7171","신광주S/S 7171 CB 조작시험","신광주S/S 7171 CB 조작시험","2026-01-22 09:00","2026-01-22 18:00","취소","취소","연속"]
[14,"광주전남","광주","신광주S/S CB 7600","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2026-01-20 08:00","2026-01-20 18:00","취소","취소","연속"]
[15,"광주전남","광주","신광주S/S CB 7672","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2026-01-20 08:00","2026-01-20 18:00","취소","취소","연속"]
[16,"광주전남","광주","신광주S/S CB 7600","피앤씨테크 보호반 성능개선","신광주S/S  76Bay B/F PNL 보호반 성능개선","2026-01-20 08:00","2026-01-20 18:00","취소","취소","연속"]
[17,"광주전남","광주","신광주S/S CB 7471","7471 CB 조작시험","7471 CB 조작시험","2026-01-20 09:00","2026-02-02 18:00","취소","취소","연속"]
[18,"광주전남","광주","신광주한빛NP#2 T/L","신광주변전소 72BAY BF반 대체","신광주변전소 72BAY BF반 대체","2026-01-19 09:00","2026-01-23 18:00","취소","취소","연속"]
[19,"광주전남","광주","신화순S/S CB 7971","7971CB 차단기 조작시험","7971CB 차단기 조작시험","2026-01-26 09:00","2026-01-26 18:00","2026-01-26 09:00","2026-01-26 18:00","연속"]
[20,"광주전남","광주","신화순S/S #3 M.Tr","신화순변전소 75BAY BF반 대체","신화순변전소 75BAY BF반 대체","2026-01-26 09:00","2026-01-30 18:00","취소","취소","연속"]
[21,"광주전남","목포","신광주한빛NP#2 T/L","2026~2027년 목포전력지사 변전협력회사 공사","한빛#1S/Y 72BAY B/F 보호반 교체","2026-01-19 08:00","2026-01-23 18:00","취소","취소","연속"]
[22,"광주전남","목포","신광주한빛NP#1 T/L","2026~2027년 목포전력지사 변전협력회사 공사","한빛#1S/Y 71BAY B/F 보호반 교체","2026-01-26 08:00","2026-01-30 18:00","취소","취소","연속"]
[23,"광주전남","순천","광양CC여수TP#2 T/L"," 광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-12 07:00","2026-01-13 18:00","2026-01-12 07:00","2026-01-13 18:00","매일"]
[24,"광주전남","순천","광양CC여수TP#1 T/L"," 광양CC-여수TP T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-05 07:00","2026-01-09 18:00","2026-01-05 07:00","2026-01-09 18:00","매일"]
[25,"광주전남","순천","광양여수TP T/L"," 신남원-광양 T/L 추락방지시설 설치공사","수평추락방지설치 (신남원-광양1, 광양-여수TP 병가) (1시간내 가압가능, 휴일작업없음) (단독 승인시 폴리머공사 시행)","2026-01-05 07:00","2026-01-16 18:00","취소","취소","매일"]
[26,"광주전남","순천","신남원광양#1 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","수평추락방지설치 (신남원-광양1, 광양-여수TP 병가) (1시간내 가압가능, 휴일작업없음) (신남원-광양만 승인시 폴리머공사 시행)","2026-01-05 07:00","2026-01-16 18:00","취소","취소","매일"]
[27,"광주전남","순천","광양하동TP#1 T/L"," 광양-하동TP T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-14 07:00","2026-01-15 18:00","취소","취소","매일"]
[28,"광주전남","순천","광양광양CC#1 T/L"," 광양-광양CC T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-19 07:00","2026-01-30 18:00","취소","취소","매일"]
[29,"광주전남","순천","신강진광양#2 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지설치(2회선 구간)(휴일작업없음, 1시간내 가압가능)","2026-01-19 07:00","2026-01-30 18:00","취소","취소","매일"]
[30,"광주전남","순천","광양율촌CC T/L"," 신남원-광양 T/L 추락방지시설 설치공사","수평추락방지설치 (신남원-광양2, 광양-율촌CC 병가) (1시간내 가압가능, 휴일작업없음)","2026-01-19 07:00","2026-01-30 18:00","취소","취소","매일"]
[31,"광주전남","순천","신남원광양#2 T/L"," 신남원-광양 T/L 추락방지시설 설치공사","수평추락방지 설치 (신남원-광양2, 광양-율촌CC 병가) (1시간내 가압가능, 휴일작업없음) (단독 승인시 폴리머공사 시행)","2026-01-19 07:00","2026-01-30 18:00","취소","취소","매일"]
[32,"광주전남","순천","광양하동TP#2 T/L"," 광양-하동TP T/L 추락방지시설 설치공사","수평추락방지시설치 (1시간내 가압가능)","2026-01-26 07:00","2026-01-30 18:00","취소","취소","매일"]
[33,"광주전남","순천","광양광양CC#2 T/L"," 광양-광양CC T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-26 07:00","2026-01-30 18:00","취소","취소","매일"]
[34,"광주전남","순천","신강진광양#1 T/L"," 신강진-광양 T/L 추락방지시설 설치공사","수평추락방지설치(2회선 구간)(휴일작업없음, 1시간내 가압가능)","2026-01-05 07:00","2026-01-16 18:00","취소","취소","매일"]
[35,"대구","칠곡","서대구S/S #4 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2026-01-30 08:00","2026-01-30 18:00","2026-01-30 08:00","2026-01-30 18:00","연속"]
[36,"대구","칠곡","서대구S/S #2 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2026-01-28 08:00","2026-01-29 18:00","2026-01-28 08:00","2026-01-29 18:00","연속"]
[37,"대구","칠곡","서대구S/S #1 M.Tr"," 서대구S/S 현대화 관련 전력구공사","(안전확보) 8회선 전력구 1,025m 설치, 환기구 12개소 등","2026-01-26 08:00","2026-01-27 18:00","2026-01-26 08:00","2026-01-27 18:00","연속"]
[38,"대구","포항","신포항신월성NP#3 T/L","2026~27년도 포항전력지사 변전협력회사 공사","신포항-신월성#3T/L 7471 정밀점검, 신월성S/Y 보호반 계전기 정정","2026-01-13 09:00","2026-01-15 18:00","2026-01-20 09:00","2026-01-22 18:00","연속"]
[39,"대구","포항","신월성N/P #1호기 주변압기 (CB 7400, 7472)","2026~27년도 포항전력지사 변전협력회사 공사","신월성 #1M.Tr 1차 7400, 7472 점검","2026-01-14 09:00","2026-01-14 18:00","2026-01-20 09:00","2026-01-20 18:00","연속"]
[40,"대구","포항","신포항S/S #1 M.Tr","신포항S/S #5M.Tr 증설공사(일반도급)","#5M.Tr 증설관련 안전이격거리 확보","2026-01-05 09:00","2026-01-07 18:00","2026-01-05 09:00","2026-01-07 18:00","연속"]
[41,"대구","포항","신포항S/S #2 M.Tr","신포항S/S #5M.Tr 증설공사(일반도급)","#5M.Tr 증설공사관련 안전이격거리 확보","2026-01-12 09:00","2026-01-14 18:00","2026-01-12 09:00","2026-01-14 18:00","연속"]
[42,"경북","영주","신영주S/S CB 7271","2025년 영주전력지사  GIS 정밀점검공사","7271CB 정밀점검","2026-01-15 09:00","2026-01-17 18:00","2026-01-15 09:00","2026-01-17 18:00","연속"]
[43,"경북","영주","신영주S/S #1 BUS","2025년 영주전력지사  GIS 정밀점검공사","7171CB 정밀점검 후 무부하가압","2026-01-14 16:00","2026-01-14 18:00","취소","취소","연속"]
[44,"경북","영주","신영주S/S CB 7200","2025년 영주전력지사  GIS 정밀점검공사","7200CB 정밀점검","2026-01-19 09:00","2026-01-21 18:00","2026-01-19 09:00","2026-01-21 18:00","연속"]
[45,"경북","영주","신영주S/S CB 7171","2025년 영주전력지사  GIS 정밀점검공사","7171CB 정밀점검","2026-01-12 09:00","2026-01-14 18:00","2026-01-12 09:00","2026-01-14 18:00","연속"]
[46,"경북","영주","신영주S/S #2 BUS","2025년 영주전력지사  GIS 정밀점검공사","7200CB 정밀점검 후 무부하가압","2026-01-21 16:00","2026-01-21 18:00","취소","취소","연속"]
[47,"경북","영주","신영주S/S CB 7371","2025년 영주전력지사  GIS 정밀점검공사","7371CB 정밀점검","2026-01-26 09:00","2026-01-28 18:00","2026-01-26 09:00","2026-01-28 18:00","연속"]
[48,"경북","영주","신영주청송PP T/L","2025년 영주전력지사  GIS 정밀점검공사","7371CB 정밀점검 후 무부하가압","2026-01-28 14:00","2026-01-28 18:00","2026-01-29 01:00","2026-01-29 05:00","연속"]
[49,"경북","영주","신영주S/S CB 7300","2025년 영주전력지사  GIS 정밀점검공사","7300CB 정밀점검","2026-01-29 09:00","2026-01-31 18:00","2026-01-29 09:00","2026-01-31 18:00","연속"]
[50,"경북","영주","신영주청송PP T/L","2025년 영주전력지사  GIS 정밀점검공사","7300CB 정밀점검 후 무부하가압","2026-01-31 14:00","2026-01-31 18:00","2026-02-01 01:00","2026-02-01 05:00","연속"]
[51,"경북","영주","신영주S/S #1 BUS","2025년 영주전력지사  GIS 정밀점검공사","7271CB 정밀점검 후 무부하가압","2026-01-17 16:00","2026-01-17 18:00","취소","취소","연속"]
[52,"경북","직할","청송PP면봉산풍력 T/L"," 청송분기T/L 불량애자 교체공사","-  청송PP면봉산풍력T/L 불량애자 교체","2026-01-26 09:00","2026-02-13 18:00","2026-01-26 09:00","2026-02-13 18:00","연속"]
[53,"부산울산","동부산","신양산S/S #4 M.Tr","신양산S/S  용량부족 차단기 교체공사","(안전이격)#2BUS 교체 및 75-76BUS-SEC 설치","2026-01-03 08:00","2026-01-04 18:00","2026-01-03 08:00","2026-01-04 18:00","연속"]
[54,"부산울산","동부산","신양산S/S #3 M.Tr","신양산S/S  용량부족 차단기 교체공사","(안전이격)#2BUS 교체 및 75-76BUS-SEC 설치","2026-01-10 08:00","2026-01-11 18:00","취소","취소","연속"]
[55,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S  용량부족 차단기 교체공사","(안전이격)#2BUS 교체 및 75-76BUS-SEC 설치","2026-01-24 08:00","2026-01-25 18:00","2026-01-24 08:00","2026-01-25 18:00","연속"]
[56,"부산울산","서부산","서부산S/S #1 M.Tr","서부산S/S  차단기 용량부족 대체공사","서부산S/S 74BAY 차단기 용량부족 대체 및 인출변경공사(#1M.Tr <-> #3,4G/T) ○  GIS 40kA 4,000A×3CB 철거 ○  GIS 63kA 6,300A×3CB 설치 ○  GIS 63kA 6,300A×3CB 설치 ○ 인출변경 ( #1M.Tr <->  #3,4GT)","2026-01-26 09:00","2026-06-10 18:00","2026-01-26 09:00","2026-06-10 18:00","연속"]
[57,"부산울산","울산","신울산S/S #5 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#5M.Tr) 1차측 개착식 관로(L=257m) 구간 굴착 및 가시설 설치","2026-01-17 09:00","2026-01-30 18:00","2026-01-17 09:00","2026-02-06 18:00","연속"]
[58,"부산울산","울산","신울산S/S #2 M.Tr","신울산S/S  변압기 인출변경 전력구공사","신울산S/S  변압기(#2M.Tr) 1차측 개착식 관로(L=257m) 구간 굴착 및 가시설 설치","2026-01-02 09:00","2026-01-17 18:00","취소","취소","연속"]
[59,"부산울산","울산","울주S/S #4 M.Tr","울주S/S  #4M.Tr 3차 현대화 공사","- 울주S/S  #4M.Tr 3차 현대화 공사","2026-01-05 09:00","2026-02-27 18:00","2026-01-05 09:00","2026-02-27 18:00","연속"]

{"sheet":"154설비","index":1,"n_rows":150,"n_cols":12,"rows_kept":150,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2],[2,11,3,11]]}
["2026년도 1월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"인천","부평","학익S/S #1 BUS"," 남인천-학익 등 2개T/L 지장이설 및 선종교체공사","학익-연수#1T/L 무부하 가압용","2026-01-29 09:00","2026-01-29 12:00","2026-01-29 09:00","2026-01-29 12:00","당일"]
[2,"인천","시흥","연수S/S #1 BUS"," 남인천-학익 등 2개T/L 지장이설 및 선종교체공사","학익-연수#1T/L 무부하 가압용","2026-01-29 09:00","2026-01-30 09:00","2026-01-29 09:00","2026-01-30 09:00","연속"]
[3,"인천","시흥","북송도연수#1 T/L"," 남인천-학익 등 2개T/L 지장이설 및 선종교체공사","학익-연수#1T/L 무부하 가압용","2026-01-29 09:00","2026-01-30 09:00","2026-01-29 09:00","2026-01-30 09:00","연속"]
[4,"경기북부","구리","동서울서종#2 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신장-덕소#1 T/L 가선공정","2026-01-12 07:00","2026-01-17 18:00","2026-01-12 07:00","2026-01-17 18:00","연속"]
[5,"경기북부","구리","동서울서종#1 T/L"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사"," 신장-덕소 등 2개 T/L 지장송전선로 이설공사 신장-덕소#2 T/L 가선공정","2026-01-05 07:00","2026-01-10 18:00","2026-01-05 07:00","2026-01-10 18:00","연속"]
[6,"강원","원주","원주S/S STATCOM CB"," 원주S/S STATCOM 변환설비 설치공사","원주 STATCOM 부하시험","2026-01-12 09:00","2026-01-23 18:00","2026-01-12 09:00","2026-01-23 18:00","연속"]
[7,"강원","원주","홍천S/S #66 BUS","홍천S/S  C.Tr 최초가압"," C.Tr(A,B,C) 및 예비 Tr(상절체)","2026-01-13 10:00","2026-01-16 10:00","2026-01-13 10:00","2026-01-16 10:00","연속"]
[8,"강원","원주","홍천S/S SEC CB 65660","홍천S/S  C.Tr 최초가압"," C.Tr(A,B,C) 및 예비 Tr(상절체)","2026-01-13 10:00","2026-01-16 10:00","2026-01-13 10:00","2026-01-16 10:00","연속"]
[9,"강원","원주","홍천S/S #61 BUS","홍천S/S  C.Tr 최초가압"," C.Tr(A,B,C) 및 예비 Tr(상절체)","2026-01-12 10:00","2026-01-13 10:00","2026-01-12 10:00","2026-01-13 10:00","연속"]
[10,"강원","원주","홍천S/S SEC CB 60610","홍천S/S  C.Tr 최초가압"," C.Tr(A,B,C) 및 예비 Tr(상절체)","2026-01-12 10:00","2026-01-13 10:00","2026-01-12 10:00","2026-01-13 10:00","연속"]
[11,"강원","원주","횡성홍천#2 T/L","홍천S/S  C.Tr 최초가압"," C.Tr(A,B,C) 및 예비 Tr(상절체)","2026-01-12 10:00","2026-01-16 10:00","2026-01-12 10:00","2026-01-16 10:00","연속"]
[12,"충북","충주","점촌단양 T/L","단양S/S STATCOM 설치공사","○ STATCOM용 C.Tr 무부하가압","2026-01-22 13:00","2026-01-23 13:00","2026-01-22 13:00","2026-01-23 13:00","연속"]
[13,"충북","충주","단양S/S #66 BUS","단양S/S STATCOM 설치공사","○ STATCOM용 C.Tr 무부하가압","2026-01-22 13:00","2026-01-23 13:00","2026-01-22 13:00","2026-01-23 13:00","연속"]
[14,"충북","충주","왕암북충주 T/L","왕암S/S STATCOM 설치공사","○ STATCOM용 C.Tr 무부하가압","2026-01-31 13:00","2026-02-01 13:00","2026-01-31 13:00","2026-02-01 13:00","연속"]
[15,"충북","충주","왕암S/S #2 BUS","왕암S/S STATCOM 설치공사","○ STATCOM용 C.Tr 무부하가압","2026-01-31 13:00","2026-02-01 13:00","2026-01-31 13:00","2026-02-01 13:00","연속"]
[16,"대전세종충남","천안","둔포석곡#1 T/L","둔포S/S  둔포-석곡#1,2T/L 러버히터 설치공사","둔포S/S  둔포-석곡#1,2T/L 러버히터 설치공사","2026-01-13 09:00","2026-01-13 18:00","취소","취소","당일"]
[17,"대전세종충남","천안","둔포석곡#2 T/L","둔포S/S  둔포-석곡#1,2T/L 러버히터 설치공사","둔포S/S  둔포-석곡#1,2T/L 러버히터 설치공사","2026-01-13 09:00","2026-01-13 18:00","취소","취소","당일"]
[18,"대전세종충남","천안","신온양석곡#1 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(12월취소시_즉시가압가능) 석곡S/S  신온양-석곡#1T/L GIS 보통점검","2026-01-03 09:00","2026-01-03 18:00","취소","취소","당일"]
[19,"대전세종충남","천안","신온양석곡#2 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(12월취소시_즉시가압가능) 석곡S/S  신온양-석곡#2T/L GIS 보통점검","2026-01-03 09:00","2026-01-03 18:00","취소","취소","당일"]
[20,"대전세종충남","천안","신탕정탕정#1 T/L","(즉시가압 불가) 신탕정-탕정 #1T/L 보호배전반 교체"," 신탕정-탕정 #1T/L 보호배전반 교체","2026-01-20 09:00","2026-01-22 18:00","취소","취소","당일"]
[21,"대전세종충남","천안","신탕정탕정#2 T/L","(즉시가압 불가) 신탕정-탕정 #2T/L 보호배전반 교체"," 신탕정-탕정 #2T/L 보호배전반 교체","2026-01-25 09:00","2026-01-27 18:00","취소","취소","당일"]
[22,"대전세종충남","천안","아산예산#1 T/L","'25년 천안P/O GIS 정밀 및 보통점검 공사","(12월 취소시_즉시가압가능) 아산S/S  아산-예산#1T/L GIS 보통점검","2026-01-04 09:00","2026-01-04 18:00","취소","취소","당일"]
[23,"전북","군산","군공S/S CB 6100","군산P/O  GIS 보통점검","군공  6100 BUS-TIE GIS 보통점검","2026-01-06 09:00","2026-01-06 14:00","2026-01-06 09:00","2026-01-06 14:00","당일"]
[24,"전북","군산","군공소룡#1 T/L","군산P/O  GIS 보통점검","군산P/O  GIS 보통점검","2026-01-07 09:00","2026-01-07 14:00","2026-01-07 09:00","2026-01-07 14:00","당일"]
[25,"전북","군산","군산서군산#2 T/L","'26년 가공송전 순시점검 위탁공사"," 군산-서군산T/L 7기 조류착지방지장치 설치","2026-01-05 07:00","2026-01-05 18:00","취소","취소","당일"]
[26,"전북","군산","군산서군산#1 T/L","'26년 가공송전 순시점검 위탁공사"," 군산-서군산T/L 7기 조류착지방지장치 설치","2026-01-02 07:00","2026-01-02 18:00","취소","취소","당일"]
[27,"전북","군산","동군산장항#1 T/L","효성제 170kV GIS 차단기 주접점 교체공사(중복)","동군산S/S 동군산-장항#1T/L 효성제 170kV GIS 차단기 주접점 교체공사","2026-01-27 09:00","2026-01-29 18:00","취소","취소","연속"]
[28,"전북","군산","새만금소룡#2 T/L","군산P/O  GIS 보통점검","군산P/O  GIS 보통점검","2026-01-09 09:00","2026-01-09 14:00","2026-01-09 09:00","2026-01-09 14:00","당일"]
[29,"전북","군산","새만금비응#2 T/L","군산P/O  GIS 보통점검","군산P/O  GIS 보통점검","2026-01-15 09:00","2026-01-15 14:00","2026-01-15 09:00","2026-01-15 14:00","당일"]
[30,"전북","군산","새만금비응#1 T/L","군산P/O  GIS 보통점검","군산P/O  GIS 보통점검","2026-01-14 09:00","2026-01-14 14:00","2026-01-14 09:00","2026-01-14 14:00","당일"]
[31,"전북","군산","새만금소룡#1 T/L","군산P/O  GIS 보통점검","군산P/O  GIS 보통점검","2026-01-08 09:00","2026-01-08 14:00","2026-01-08 09:00","2026-01-08 14:00","당일"]
[32,"전북","군산","팔봉두마#2 T/L","팔봉S/S 혼용운영시스템 설치공사","RTU → LID 제어케이블 이설 작업개소 : 팔봉S/S","2026-01-22 09:00","2026-01-23 18:00","취소","취소","연속"]
[33,"전북","군산","영등팔봉#1 T/L","팔봉S/S 혼용운영시스템 설치공사","RTU → LID 제어케이블 이설 작업개소 : 팔봉, 영등S/S 양단","2026-01-12 09:00","2026-01-14 18:00","취소","취소","연속"]
[34,"전북","군산","영등팔봉#2 T/L","팔봉S/S 혼용운영시스템 설치공사","RTU → LID 제어케이블 이설 작업개소 : 팔봉, 영등S/S 양단","2026-01-19 09:00","2026-01-21 18:00","취소","취소","연속"]
[35,"전북","군산","팔봉두마#1 T/L","팔봉S/S 혼용운영시스템 설치공사","RTU → LID 제어케이블 이설 작업개소 : 팔봉S/S","2026-01-15 09:00","2026-01-16 18:00","취소","취소","연속"]
[36,"전북","군산","은진함열#1 T/L","'26년 가공송전 순시점검 위탁공사"," 은진-함열T/L 14기 조류착지방지장치 설치","2026-01-06 07:00","2026-01-07 18:00","2026-01-06 07:00","2026-01-07 18:00","매일"]
[37,"전북","군산","은진함열#2 T/L","'26년 가공송전 순시점검 위탁공사"," 은진-함열T/L 14기 조류착지방지장치 설치","2026-01-08 07:00","2026-01-09 18:00","2026-01-08 07:00","2026-01-09 18:00","매일"]
[38,"전북","김제","고창영광 T/L"," 고창S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2026-01-20 09:00","2026-01-20 18:00","취소","취소","당일"]
[39,"전북","김제","소성고창#2 T/L"," 고창S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2026-01-23 09:00","2026-01-23 18:00","취소","취소","당일"]
[40,"전북","김제","소성고창#1 T/L"," 고창S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2026-01-22 09:00","2026-01-22 18:00","취소","취소","당일"]
[41,"전북","김제","고창홍농 T/L"," 고창S/S 혼용운영시스템 설치공사","- 혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] - 이설 후 SCADA 연동시험 시행","2026-01-21 09:00","2026-01-21 18:00","취소","취소","당일"]
[42,"전북","김제","백산김제#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-01-13 08:00","2026-01-13 18:00","취소","취소","매일"]
[43,"전북","김제","백산김제#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-01-12 08:00","2026-01-12 18:00","취소","취소","매일"]
[44,"전북","김제","신김제동전주#2 T/L"," 완산분기T/L 건설공사","[송전] #2T/L 전선이동 (가선로 → 기존선로)","2026-01-22 07:00","2026-01-25 18:00","취소","취소","연속"]
[45,"전북","김제","신김제동전주#1 T/L"," 완산S/S 및 분기T/L 건설사업","[송전] 1. #1T/L 전선이동(가선로 → 기존선로) 2. C/T 조립 3. 본선로 구성 및 인하선 연결(EBA, EBG) [변전] 1. 보호반 이설 및 무부하 가압 2. 계통시험 및 사용전검사(실부하 가압)","2026-01-26 07:00","2026-02-13 18:00","취소","취소","연속"]
[46,"전북","직할","동전주북전주#1 T/L","전주전철#2T/L GIS 정밀점검 무부하가압","전주전철#2T/L GIS 정밀점검 무부하가압","2026-01-15 17:00","2026-01-15 18:00","2026-01-15 17:00","2026-01-15 18:00","당일"]
[47,"전북","직할","동전주북전주#1 T/L","전주전철#2T/L GIS 정밀점검 무부하가압","전주전철#2T/L GIS 정밀점검 무부하가압","2026-01-16 15:00","2026-01-16 18:00","2026-01-16 15:00","2026-01-16 18:00","당일"]
[48,"전북","직할","동전주북전주#1 T/L","전주전철#1T/L GIS 정밀점검 무부하가압","전주전철#1T/L GIS 정밀점검 무부하가압 12월 기신청(12월 진행시 1월 필요X)","2026-01-13 17:00","2026-01-13 18:00","2026-01-13 17:00","2026-01-13 18:00","당일"]
[49,"전북","직할","왕궁봉동#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-01-08 08:00","2026-01-08 18:00","취소","취소","당일"]
[50,"전북","직할","북전주봉동#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-01-05 08:00","2026-01-05 18:00","취소","취소","매일"]
[51,"전북","직할","왕궁봉동#1 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-01-02 08:00","2026-01-02 18:00","취소","취소","매일"]
[52,"전북","직할","북전주봉동#2 T/L"," 동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-01-06 08:00","2026-01-06 18:00","취소","취소","매일"]
[53,"전북","직할","북전주봉동#1 T/L","6433 GIS 정밀점검 관련 무부하가압","6433 GIS 정밀점검 관련 무부하가압","2026-01-08 15:00","2026-01-08 16:00","2026-01-08 15:00","2026-01-08 16:00","연속"]
[54,"전북","직할","북전주S/S #2 BUS","북전주S/S 6433 GIS 정밀점검","CB, DS 정밀점검","2026-01-07 09:00","2026-01-08 18:00","취소","취소","연속"]
[55,"전북","직할","북전주S/S #1 BUS","북전주S/S 6433 GIS 정밀점검","CB, DS 정밀점검","2026-01-05 09:00","2026-01-06 18:00","취소","취소","연속"]
[56,"전북","직할","북전주봉동#1 T/L","6433 GIS 정밀점검 관련 무부하가압","6433 GIS 정밀점검 관련 무부하가압","2026-01-06 15:00","2026-01-06 16:00","2026-01-06 15:00","2026-01-06 16:00","연속"]
[57,"전북","직할","동전주태평#1 T/L","[4차수]태평S/S  장기사용 GIS 교체공사 (무부하)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2026-01-14 17:00","2026-01-15 17:00","2026-01-14 17:00","2026-01-15 17:00","연속"]
[58,"전북","직할","동전주태평#1 T/L","[4차수]태평S/S  장기사용 GIS 교체공사 (무부하)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2026-01-28 14:00","2026-01-29 17:00","2026-01-28 14:00","2026-01-29 17:00","연속"]
[59,"전북","직할","동전주태평#1 T/L","[4차수]태평S/S  장기사용 GIS 교체공사 (1H, 무부하)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2026-01-13 16:00","2026-01-13 17:00","2026-01-13 16:00","2026-01-13 17:00","연속"]
[60,"전북","직할","동전주태평#1 T/L","[4차수]태평S/S  장기사용 GIS 교체공사 (1H, 무부하)","170kV GIS × 6CCT 교체[T/L 2CCT, T/R 3CCT, B/T 1CCT(PT 포함)]","2026-01-10 16:00","2026-01-10 17:00","2026-01-10 16:00","2026-01-10 17:00","연속"]
[61,"광주전남","강진","보성벌교 T/L"," 보성-벌교T/L 안전이격확보 휴전","ㅇ 대상선로 :  보성-벌교T/L 1~2호 ㅇ 공사내용 : 송전선로 직하 보성군 생활폐기물 소각시설 설치사업 관련으로 중장비(크레인 등) 사용을 위한 안전이격확보 휴전","2026-01-26 07:00","2026-01-30 11:00","2026-01-26 07:00","2026-01-30 11:00","매일"]
[62,"광주전남","강진","보성벌교 T/L"," 보성-벌교T/L 안전이격확보 휴전","ㅇ 대상선로 :  보성-벌교T/L 1~2호 ㅇ 공사내용 : 송전선로 직하 보성군 생활폐기물 소각시설 설치사업 관련으로 중장비(크레인 등) 사용을 위한 안전이격확보 휴전","2026-01-12 07:00","2026-01-16 11:00","2026-01-12 07:00","2026-01-16 11:00","매일"]
[63,"광주전남","광주","계림S/S SEC CB 61600","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2026-01-12 09:00","2026-01-14 18:00","취소","취소","연속"]
[64,"광주전남","광주","계림S/S CB 6100","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2026-01-12 09:00","2026-01-16 18:00","취소","취소","연속"]
[65,"광주전남","광주","계림S/S CB 6200","2024~2025년 광주전력지사 변전협력회사 공사","계림S/S 6200BUS-TIE 조작시험","2026-01-14 10:00","2026-01-16 16:00","취소","취소","당일"]
[66,"광주전남","광주","남광주소태 T/L"," 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2026-01-26 09:00","2026-01-31 18:00","취소","취소","연속"]
[67,"광주전남","광주","남광주화순#2 T/L"," 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2026-01-01 09:00","2026-01-08 18:00","취소","취소","연속"]
[68,"광주전남","광주","남광주화순#1 T/L","(안전거리휴전) 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2026-01-01 09:00","2026-01-03 18:00","취소","취소","연속"]
[69,"광주전남","광주","계림남광주 T/L","(안전거리 휴전) 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2026-01-29 09:00","2026-01-31 18:00","취소","취소","연속"]
[70,"광주전남","광주","북광주일곡#2 T/L","북광주S/S  #4M.Tr 증설공사","- #2BUS 무부하가압용","2026-01-29 16:00","2026-01-30 09:00","2026-01-29 16:00","2026-01-30 09:00","연속"]
[71,"광주전남","광주","북광주일곡#2 T/L","북광주S/S  #4M.Tr 증설공사","- #1BUS 무부하가압용","2026-01-27 16:00","2026-01-28 09:00","2026-01-27 16:00","2026-01-28 09:00","연속"]
[72,"광주전남","광주","담양일곡#2 T/L","일곡S/S  담양-일곡#2T/L GIS 보통점검","일곡S/S  담양-일곡#2T/L GIS 보통점검","2026-01-14 09:00","2026-01-14 18:00","취소","취소","당일"]
[73,"광주전남","광주","담양일곡#1 T/L","- 담양S/S  담양-일곡#1T/L GIS 보통점검","- 담양S/S  담양-일곡#1T/L GIS 보통점검","2026-01-13 09:00","2026-01-13 18:00","취소","취소","당일"]
[74,"광주전남","광주","신광주일곡#2 T/L","일곡S/S 신광주-일곡#2T/L GIS 보통점검","일곡S/S 신광주-일곡#2T/L GIS 보통점검","2026-01-30 09:00","2026-01-30 18:00","취소","취소","당일"]
[75,"광주전남","광주","신광주일곡#1 T/L","일곡S/S 신광주-일곡#1T/L GIS 보통점검","일곡S/S 신광주-일곡#1T/L GIS 보통점검","2026-01-29 09:00","2026-01-29 18:00","취소","취소","당일"]
[76,"광주전남","순천","고옥S/S CB 6100"," 고옥S/S 득량-고옥#1,2T/L GIS증설공사","득량-고옥#1,2T/L GIS 2BAY 증설 (휴일 작업 없음)","2026-01-12 09:00","2026-01-24 18:00","취소","취소","연속"]
[77,"광주전남","순천","광양순천#1 T/L"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#6(기설) ∼ J/B#10(신설)  XLPE 1,200(D)㎟ × 2C × 1.402km","2026-01-19 07:00","2026-02-14 18:00","취소","취소","계통안정"]
[78,"광주전남","순천","광양백운#1 T/L","24-25년 순천전력지사 변전협력회사 공사","광양-백운#1T/L 보호배전반 대체","2026-01-21 09:00","2026-01-23 18:00","취소","취소","연속"]
[79,"광주전남","순천","광양순천#2 T/L"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#6(기설) ∼ J/B#10(신설)  XLPE 1,200(D)㎟ × 2C × 1.402km","2026-01-19 07:00","2026-01-30 18:00","취소","취소","연속"]
[80,"광주전남","순천","벌교고흥#2 T/L"," 벌교-고흥T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(10일이상 승인분)(휴일작업없음)","2026-01-19 07:00","2026-01-30 18:00","취소","취소","매일"]
[81,"광주전남","순천","벌교고흥#1 T/L"," 벌교-고흥T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(10일이상 승인분)(휴일작업없음)","2026-01-05 07:00","2026-01-16 18:00","취소","취소","매일"]
[82,"광주전남","순천","장흥벌교 T/L"," 벌교-고흥T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(벌교고흥 일부병가, 단독시행가능)","2026-01-12 07:00","2026-01-16 18:00","취소","취소","매일"]
[83,"광주전남","순천","보성벌교 T/L"," 벌교-고흥T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(벌교고흥 일부병가, 단독작업가능)","2026-01-19 07:00","2026-01-23 18:00","취소","취소","매일"]
[84,"광주전남","순천","승주서순천 T/L"," 승주-서순천 T/L 추락방지시설 설치공사","수평추락방지설치 (승주-서순천, 화순-승주2(통보분) 병가) (1시간내 가압가능)","2026-01-19 07:00","2026-01-30 18:00","취소","취소","매일"]
[85,"광주전남","순천","승주주암HP T/L"," 승주-서순천 T/L 추락방지시설 설치공사","수평추락방지설치 (승주-주암HP, 화순-승주1(통보분) 병가) (1시간내 가압가능)","2026-01-05 07:00","2026-01-16 18:00","취소","취소","매일"]
[86,"광주전남","순천","여수소라#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체용 무부하가압","2026-01-14 17:00","2026-01-15 09:00","취소","취소","연속"]
[87,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-01-02 09:00","2026-01-07 09:00","취소","취소","연속"]
[88,"광주전남","순천","여천여수#1 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-01-02 09:00","2026-01-23 18:00","취소","취소","연속"]
[89,"광주전남","순천","여수소라#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수-소라#1,2T/L 보호배전반 엔지니어링","2026-01-05 17:00","2026-01-06 10:00","취소","취소","연속"]
[90,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-01-07 09:00","2026-01-15 09:00","취소","취소","연속"]
[91,"광주전남","순천","여수소라#2 T/L"," 여수-소라 T/L 추락방지시설 설치공사","수평추락방지설치(2,3호 : 여수-소라2, 여천-여수2 병가)(1시간내 가압가능)(단독승인시 폴리머설치공사 시행)","2026-01-13 07:00","2026-01-15 18:00","취소","취소","매일"]
[92,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2026-01-09 17:00","2026-01-09 21:00","취소","취소","당일"]
[93,"광주전남","순천","여천여수#2 T/L","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - 안전이격휴전","2026-01-08 17:00","2026-01-08 21:00","취소","취소","당일"]
[94,"광주전남","순천","여수소라#1 T/L"," 여수-소라 T/L 추락방지시설 설치공사","수평추락방지설치(2,3호 : 여수-소라1, 여천-여수1 병가)(1시간내 가압가능)(단독승인시 폴리머설치공사 시행)","2026-01-27 07:00","2026-01-29 18:00","취소","취소","매일"]
[95,"광주전남","순천","여수S/S #1 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-01-23 09:00","2026-01-23 18:00","취소","취소","연속"]
[96,"광주전남","순천","여수S/S #2 BUS","여수S/S  이하 장기사용 GIS 교체공사","○ 여수S/S  장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-01-15 09:00","2026-01-23 09:00","취소","취소","연속"]
[97,"광주전남","순천","여수T/P #60 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2026-01-12 09:00","2026-01-13 18:00","취소","취소","연속"]
[98,"광주전남","순천","호남TP여수TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","수평추락방지설치(32~41호 : 여천-호남TP1, 여천-여수2 병가/2호 : 여천-호남TP1, 호남TP-여수TP1 병가)(1시간내 가압가능)(단독승인시 폴리머설치공사 시행)","2026-01-12 07:00","2026-01-13 18:00","취소","취소","매일"]
[99,"광주전남","순천","호남TP여수TP#2 T/L","스페이서 가스누기 보수","스페이서 가스누기 보수","2026-01-21 09:00","2026-01-22 18:00","취소","취소","연속"]
[100,"광주전남","순천","여수TP화치#2 T/L","24-25년 순천전력지사 변전협력회사 공사","여수TP-화치#2T/L 보호배전반 대체","2026-01-28 09:00","2026-01-30 18:00","취소","취소","연속"]
[101,"광주전남","순천","여수T/P #65 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2026-01-14 09:00","2026-01-15 18:00","취소","취소","연속"]
[102,"광주전남","순천","호남TP여수TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","수평추락방지설치(32~41호 : 여천-호남TP2, 여천-여수1 병가)(2호 : 여천-호남TP2, 호남TP-여수TP2 병가)(1시간내 가압가능)(단독승인시 폴리머설치공사 시행)","2026-01-19 07:00","2026-01-23 18:00","취소","취소","매일"]
[103,"광주전남","순천","여수T/P #61 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2026-01-19 09:00","2026-01-20 18:00","취소","취소","연속"]
[104,"광주전남","순천","여수T/P #66 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2026-01-21 09:00","2026-01-22 18:00","취소","취소","연속"]
[105,"광주전남","순천","여천여수#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","수평추락방지설치(32~41호 : 여천-호남TP2, 여천-여수1 병가)(2호 : 여천-호남TP2, 호남TP-여수TP2 병가)(나머지 2회선)(1시간내 가압가능)(단독승인시 폴리머공사 시행)","2026-01-26 07:00","2026-01-30 18:00","취소","취소","매일"]
[106,"광주전남","순천","여수TP여천#2 T/L"," 여수TP-여천 T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-22 07:00","2026-01-23 18:00","취소","취소","매일"]
[107,"광주전남","순천","여수TP여천#1 T/L"," 여수TP-여천 T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-19 07:00","2026-01-21 18:00","취소","취소","매일"]
[108,"광주전남","순천","여천호남TP#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","수평추락방지설치(32~41호 : 여천-호남TP2, 여천-여수1 병가)(2호 : 여천-호남TP2, 호남TP-여수TP2 병가)(나머지2회선)(휴일작업없음, 1시간내 가압가능)","2026-01-19 07:00","2026-01-30 18:00","취소","취소","매일"]
[109,"광주전남","순천","여천여수#2 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","수평추락방지설치(32~41호 : 여천-호남TP1, 여천-여수2 병가/2호 : 여천-호남TP1, 호남TP-여수TP1 병가) (단독승인시 폴리머공사시행)","2026-01-12 07:00","2026-01-16 18:00","취소","취소","매일"]
[110,"광주전남","순천","여천호남TP#1 T/L"," 여천-호남TP T/L 추락방지시설 설치공사","수평추락방지설치(32~41호 : 여천-호남TP1, 여천-여수2 병가) (2호 : 여천-호남TP1, 호남TP-여수TP1 병가) (나머지 2회선) (1시간내 가압가능) (단독승인시 폴리머공사 시행)","2026-01-05 07:00","2026-01-16 18:00","취소","취소","매일"]
[111,"광주전남","순천","여천호남TP#1 T/L","여천S/S  GIS 기기기초 공사","기기기초공사 중장비 사용 관련 안전이격휴전 / 매일휴전 / 휴일작업 없음","2026-01-01 09:00","2026-01-30 18:00","취소","취소","매일"]
[112,"광주전남","순천","여천여수#1 T/L","여천S/S  GIS 기기기초 공사","기기기초공사 중장비 사용 관련 안전이격휴전 / 매일휴전 / 휴일작업 없음","2026-01-01 09:00","2026-01-30 18:00","취소","취소","매일"]
[113,"광주전남","순천","여수TP여천#1 T/L","여천S/S  GIS 기기기초 공사","기기기초공사 중장비 사용 관련 안전이격휴전 / 매일휴전 / 휴일작업 없음","2026-01-01 09:00","2026-01-30 18:00","취소","취소","매일"]
[114,"광주전남","순천","여천호남TP#2 T/L","여천S/S  GIS 기기기초 공사","기기기초공사 중장비 사용 관련 안전이격휴전 / 매일휴전 / 휴일작업 없음","2026-01-01 09:00","2026-01-30 18:00","취소","취소","매일"]
[115,"광주전남","순천","여수TP여천#2 T/L","여천S/S  GIS 기기기초 공사","기기기초공사 중장비 사용 관련 안전이격휴전 / 매일휴전 / 휴일작업 없음","2026-01-01 09:00","2026-01-30 18:00","취소","취소","매일"]
[116,"광주전남","순천","여천여수#2 T/L","여천S/S  GIS 기기기초 공사","기기기초공사 중장비 사용 관련 안전이격휴전 / 매일휴전 / 휴일작업 없음","2026-01-01 09:00","2026-01-30 18:00","취소","취소","매일"]
[117,"광주전남","순천","여수TP용성#1 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","수평추락방지설치(1,3호 : 2회선 / 2,2.1호 : 여수TP-용성1, 용성-여수산단1 병가)(1시간내 가압가능)","2026-01-12 07:00","2026-01-13 18:00","취소","취소","매일"]
[118,"광주전남","순천","용성여수산단#2 T/L"," 용성-여수산단T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-19 07:00","2026-01-20 18:00","취소","취소","매일"]
[119,"광주전남","순천","여수TP용성#2 T/L"," 여수TP-용성 T/L 추락방지시설 설치공사","수평추락방지설치(1,3호 : 2회선 / 2,2.1호 : 여수TP-용성2, 용성-여수산단2 병가)(1시간내 가압가능)","2026-01-19 07:00","2026-01-20 18:00","취소","취소","매일"]
[120,"광주전남","순천","용성여수산단#1 T/L"," 용성-여수산단T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-12 07:00","2026-01-16 18:00","취소","취소","매일"]
[121,"광주전남","순천","율촌화치#1 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","수평추락방지설치(45~67호 : 율촌-화치1, 율촌-여수산단2 병가, 68호 : 율촌-화치1, 순천-율촌2 병가)(1시간내 가압가능)(단독승인시 폴리머설치공사 시행)","2026-01-19 07:00","2026-01-23 18:00","취소","취소","매일"]
[122,"광주전남","순천","율촌여수산단#2 T/L"," 율촌-여수산단 T/L 추락방지시설 설치공사","수평추락방지설치 (1시간내 가압가능, 휴일작업없음) (병가구간있으나 단일 작업도 가능)","2026-01-19 07:00","2026-01-30 18:00","취소","취소","매일"]
[123,"광주전남","순천","순천율촌#1 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","수평추락방지설치(45~67호 : 율촌-화치2, 율촌-여수산단1 병가/68호 : 율촌-화치2, 순천-율촌1 병가) (1시간내 가압가능) (단독승인시 폴리머공사 시행)","2026-01-15 07:00","2026-01-16 18:00","취소","취소","매일"]
[124,"광주전남","순천","율촌화치#2 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","수평추락방지설치(45~67호 : 율촌-화치2, 율촌-여수산단1 병가 / 68호 : 율촌-화치2, 순천-율촌1 병가) (1시간내 가압가능) (단독승인시 폴리머공사 시행)","2026-01-12 07:00","2026-01-16 18:00","취소","취소","매일"]
[125,"광주전남","순천","순천율촌#2 T/L"," 율촌-화치 T/L 추락방지시설 설치공사","수평추락방지설치(45~67호 : 율촌-화치1, 율촌-여수산단2 병가)(68호 : 율촌-화치1, 순천-율촌2 병가)(1시간내 가압가능)(단독승인시 폴리머공사시행)","2026-01-22 07:00","2026-01-23 18:00","취소","취소","매일"]
[126,"광주전남","순천","율촌여수산단#1 T/L"," 율촌-여수산단 T/L 추락방지시설 설치공사","수평추락방지설치 (1시간내 가압가능, 휴일작업없음) (병가구간있으나 단일 작업도 가능)","2026-01-05 07:00","2026-01-16 18:00","취소","취소","매일"]
[127,"광주전남","순천","여수TP화치#2 T/L","345kV 여수TP-화치 T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-26 07:00","2026-01-30 18:00","취소","취소","매일"]
[128,"광주전남","순천","여수TP화치#1 T/L","345kV 여수TP-화치 T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치","2026-01-12 07:00","2026-01-16 18:00","취소","취소","매일"]
[129,"광주전남","순천","백운황금#1 T/L","현대제 170kV EGIS 정밀점검 시행","현대제 170kV EGIS 정밀점검 시행 - 170kV EGIS 10CCT 및 PT&ES 동작부","2026-01-12 09:00","2026-01-17 18:00","취소","취소","연속"]
[130,"광주전남","순천","백운황금#2 T/L","현대제 170kV EGIS 정밀점검 시행","현대제 170kV EGIS 정밀점검 시행 - 170kV EGIS 10CCT 및 PT&ES 동작부","2026-01-05 09:00","2026-01-10 18:00","취소","취소","연속"]
[131,"광주전남","순천","황금세풍#2 T/L","현대제 170kV EGIS 정밀점검 시행","현대제 170kV EGIS 정밀점검 시행 - 170kV EGIS 10CCT 및 PT&ES 동작부","2026-01-19 09:00","2026-01-24 18:00","취소","취소","연속"]
[132,"광주전남","직할","나주금천#1 T/L","나주-금천#1T/L 피뢰기 절연열화측정","나주-금천#1T/L 피뢰기 절연열화측정","2026-01-07 09:00","2026-01-06 14:00","취소","취소","당일"]
[133,"광주전남","직할","남광주금천#2 T/L","남광주-금천#2T/L 피뢰기 절연열화측정","남광주-금천#2T/L 피뢰기 절연열화측정","2026-01-06 14:00","2026-01-06 18:00","취소","취소","당일"]
[134,"광주전남","직할","남광주금천#1 T/L","남광주-금천#1T/L 피뢰기 절연열화측정","남광주-금천#1T/L 피뢰기 절연열화측정","2026-01-06 09:00","2026-01-06 14:00","취소","취소","당일"]
[135,"광주전남","직할","나주금천#2 T/L","나주-금천#2T/L 피뢰기 절연열화측정","나주-금천#2T/L 피뢰기 절연열화측정","2026-01-07 14:00","2026-01-07 18:00","취소","취소","당일"]
[136,"광주전남","직할","하남장성#1 T/L","하남장성#1T/L 피뢰기 절연열화측정","하남장성#1T/L 피뢰기 절연열화측정","2026-01-05 09:00","2026-01-05 14:00","취소","취소","당일"]
[137,"광주전남","직할","하남장성#1 T/L","하남장성#2T/L 피뢰기 절연열화측정","하남장성#2T/L 피뢰기 절연열화측정","2026-01-05 14:00","2026-01-05 18:00","취소","취소","당일"]
[138,"대구","칠곡","남구미S/S #1 Sh.C CB","남구미S/S  GIS 교체공사","170kV GIS * 17CCT 교체","2026-01-05 09:00","2027-02-12 18:00","2026-01-05 09:00","2027-02-12 18:00","연속"]
[139,"대구","칠곡","남구미S/S #2 Sh.C CB","남구미S/S  GIS 교체공사","170kV GIS * 17CCT 교체","2026-01-05 09:00","2027-02-12 18:00","2026-01-05 09:00","2027-02-12 18:00","연속"]
[140,"대구","칠곡","남구미S/S 사곡전철#2 T/L CB","남구미S/S  GIS 교체공사","170kV GIS * 17CCT 교체","2026-01-12 09:00","2026-04-30 18:00","2026-01-12 09:00","2026-04-30 18:00","연속"]
[141,"대구","포항","청하영덕#2 T/L","천전개폐소 연계송전선로 건설공사(GS풍력)","임시선로 구성을 위한 선로이설 -  청하-영덕 T/L 115호 →영덕제1풍력발전 T/L 19호 - #2T/L OPGW 및 전력선 이설","2026-01-23 09:00","2026-01-26 18:00","취소","취소","연속"]
[142,"대구","포항","청하영덕#1 T/L","천전개폐소 연계송전선로 건설공사(GS풍력)","임시선로 구성을 위한 선로이설 -  청하-영덕 T/L 115호 →영덕제1풍력발전 T/L 19호 - #1T/L OPGW 및 전력선 이설","2026-01-27 09:00","2026-01-30 18:00","취소","취소","연속"]
[143,"경북","구미","화동보은 T/L","2025-26년 구미전력지사 변전협력회사 공사","- GIS 하자점검","2026-01-13 14:00","2026-01-13 18:00","2026-01-13 11:00","2026-01-13 14:00","당일"]
[144,"경북","구미","화동영동 T/L","2025-26년 구미전력지사 변전협력회사 공사","- GIS 하자점검","2026-01-13 09:00","2026-01-13 14:00","2026-01-12 11:00","2026-01-12 14:00","당일"]
[145,"경북","구미","상주화동#2 T/L","2025-26년 구미전력지사 변전협력회사 공사","- GIS 하자점검","2026-01-14 09:00","2026-01-14 18:00","2026-01-14 11:00","2026-01-14 14:00","당일"]
[146,"경북","직할","안동동안동#2 T/L","26~27년 경북본부 직할 변전협력회사 공사","GIS 하자점검","2026-01-21 09:00","2026-01-21 14:00","2026-01-21 09:00","2026-01-21 14:00","당일"]