{"text_format":"2","workbook":"xlsx","n_sheets":3,"sheets":["765설비","345설비","154설비"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":12,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"765설비","index":0,"n_rows":21,"n_cols":12,"rows_kept":21,"cut":false,"hidden":false,"merged":[[2,11,3,11],[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2026년도 4월 휴전계획서"]
["765kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분","연간반영\n(Y/N)"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"경기","성남","신안성S/S #3 M.Tr","26년 성남전력 765,345kV M.Tr 정밀,보통점검 공사","M.Tr 보통점검 추락방지시설 설치 B-1 TANK 본체유 여과 7871 보통점검, 절연열화 7800 보통점검, 절연열화","2026-05-18 09:00","2026-05-29 18:00","2026-05-18 09:00","2026-05-29 18:00","연속"]
[2,"경기","성남","신안성신가평 T/L","2026-2027년 성남전력지사 가공송전 협력회사 공사","□ 항공장애표시도장(5기) 33~37호","2026-04-13 09:00","2026-04-17 18:00","취소","취소","연속"]
[3,"대전세종충남","서산","당진T/P CB 8371","'26년 서산P/O 변전협력회사 총액공사","(당진화력S/S 8101DS 복구시) 8351DS B,C상 가스누기 보수공사","2026-04-27 09:30","2026-05-01 18:00","2026-04-27 09:30","2026-05-01 18:00","연속"]
[4,"대전세종충남","서산","당진T/P #1 BUS","'26년 서산P/O 변전협력회사 총액공사","(당진화력S/S 8101DS 복구시) 8351DS B,C상 가스누기 보수공사","2026-04-27 09:30","2026-05-01 18:00","2026-04-27 09:30","2026-05-01 18:00","연속"]
[5,"대전세종충남","서산","당진T/P M.Tr","당진화력S/S 8101 DS A상 고장복구공사","(즉시가압불가) 당진화력S/S 8101 DS A상 고장복구공사","2026-04-20 09:30","2026-04-23 18:00","2026-04-20 09:30","2026-04-23 18:00","연속"]
[6,"대전세종충남","서산","신서산신중부#1 T/L"," 신서산-신중부 No.48-49 항공장애표시구 정비공사"," 신서산-신중부 No.48-49 항공장애표시구 GW1번 파손 정비공사","2026-04-27 09:00","2026-04-27 18:00","취소","취소","연속"]
[7,"대전세종충남","서산","신서산신중부#1 T/L","'26년 서산P/O 변전협력회사 총액공사","신서산S/S 신서산-신중부#1T/L 차단실패보호반 대체(85BAY)","2026-04-03 09:30","2026-04-12 18:00","2026-04-03 09:30","2026-04-12 18:00","연속"]
[8,"대전세종충남","서산","신서산S/S #4 M.Tr","[변전운영부]신서산S/S #4M.Tr 및 OLTC 정밀점검공사","○ 신서산S/S #4M.Tr 및 OLTC 정밀점검공사(즉시가압 불가) - 점검전후 시험, OLTC 점검, 졀연유 배유, 내부점검, 절연유 여과 등 - 보조계전기, 냉각팬 베어링, 기계적 보호장치, OFU, 온도계 교체 등 - 본체 유면계, 컨서베이터용 공기주머니 교체 등 ○ 병행작업 - #4M.Tr 2차 7871 GIS 보통점검,","2026-04-03 09:00","2026-06-05 18:00","취소","취소","연속"]
[9,"부산울산","동부산","신고리N/P #3 M.Tr","주변압기 종합예방진단 부싱 누설전류 어댑터 및 센서 교체공사","주변압기 종합예방진단 부싱 누설전류 어댑터 및 센서 교체공사","2026-04-20 09:00","2026-04-20 18:00","취소","취소","당일"]
{"$rows_empty":7}
[{"$nulls":5}," "]

{"sheet":"345설비","index":1,"n_rows":403,"n_cols":11,"rows_kept":403,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2026년도 4월 휴전계획서"]
["345kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성동S/S #4 M.Tr","성동변전소 노후 조명설비 대체공사","#4M.Tr실 노후 조명설비 대체 형광등, 방전등 ---> 고효율 LED 등기구","2026-04-23 13:00","2026-04-23 18:00","2026-04-23 13:00","2026-04-23 18:00","당일"]
[2,"서울","성동","성동S/S #2 M.Tr","성동변전소 노후 조명설비 대체공사","#2M.Tr실 노후 조명설비 대체 형광등, 방전등 ---> 고효율 LED 등기구","2026-04-23 08:00","2026-04-23 13:00","2026-04-23 08:00","2026-04-23 13:00","당일"]
[3,"서울","성동","성동S/S #1 Sh.R CB","성동변전소 노후 조명설비 대체공사","#1Sh.R실 노후 조명설비 대체 형광등, 방전등 --> LED","2026-04-21 08:00","2026-04-21 13:00","2026-04-21 08:00","2026-04-21 13:00","당일"]
[4,"서울","성동","성동S/S #1 M.Tr","성동변전소 노후 조명설비 대체공사","#1M.Tr실 노후 조명설비 대체 형광등, 방전등 ---> 고효율 LED 등기구","2026-04-22 09:00","2026-04-22 13:00","2026-04-22 09:00","2026-04-22 13:00","당일"]
[5,"서울","성동","성동S/S #2 Sh.R CB","성동변전소 노후 조명설비 대체공사","#2Sh.R실 노후 조명설비 대체 형광등, 방전등 --> LED","2026-04-21 13:00","2026-04-21 18:00","2026-04-21 13:00","2026-04-21 18:00","당일"]
[6,"서울","성동","성동S/S #3 M.Tr","성동변전소 노후 조명설비 대체공사","#3M.Tr실 노후 조명설비 대체 형광등, 방전등 ---> 고효율 LED 등기구","2026-04-22 13:00","2026-04-22 18:00","2026-04-22 13:00","2026-04-22 18:00","당일"]
[7,"서울","중부","중부S/S #1 M.Tr","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-06 10:00","2026-04-06 12:00","취소","취소","당일"]
[8,"서울","중부","중부S/S #75 BUS","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-06 10:00","2026-04-06 18:00","취소","취소","당일"]
[9,"서울","중부","중부S/S #2 M.Tr","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-06 12:00","2026-04-06 14:00","취소","취소","당일"]
[10,"서울","중부","중부S/S #3 M.Tr","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-06 14:00","2026-04-06 16:00","취소","취소","당일"]
[11,"서울","중부","중부S/S #4 M.Tr","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-06 16:00","2026-04-06 18:00","취소","취소","당일"]
[12,"서울","중부","중부S/S #70 BUS","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-07 10:00","2026-04-07 18:00","취소","취소","당일"]
[13,"서울","중부","중부S/S #1 M.Tr","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-08 10:00","2026-04-08 12:00","취소","취소","당일"]
[14,"서울","중부","중부S/S #75 BUS","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-08 10:00","2026-04-08 18:00","취소","취소","당일"]
[15,"서울","중부","중부S/S #2 M.Tr","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-08 12:00","2026-04-08 14:00","취소","취소","당일"]
[16,"서울","중부","중부S/S #3 M.Tr","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-08 14:00","2026-04-08 16:00","취소","취소","당일"]
[17,"서울","중부","중부S/S #4 M.Tr","2026~2027년 중부전력지사 변전협력회사 공사","CT집합반 대체","2026-04-08 16:00","2026-04-08 18:00","취소","취소","당일"]
[18,"남서울","동서울","신용인동서울#2 T/L"," 동서울변전소 옥내화 전력구공사","동서울변전소 옥내화에 따른 구내 전력구공사 - 활선간섭 구간 : 약 180m","2026-04-16 09:00","2026-06-30 18:00","2026-04-28 09:00","2026-07-17 18:00","연속"]
[19,"남서울","강남","신성남신양재#1 T/L","신양재S/S 노후불량 PT 교체공사"," #1M.Tr 1차 GIS 불량PT 교체관련 무부하 가압선로 7171 GIS 보통점검","2026-04-30 09:00","2026-05-03 18:00","취소","취소","연속"]
[20,"남서울","동서울","동서울S/S #2 M.Tr","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-20 09:00","2026-04-22 18:00","2026-04-20 09:00","2026-04-22 18:00","연속"]
[21,"남서울","동서울","동서울S/S #1 M.Tr","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-13 09:00","2026-04-15 18:00","2026-04-13 09:00","2026-04-15 18:00","연속"]
[22,"남서울","동서울","동서울S/S CB 7800","동서울S/S GIS PT 철거공사","신양재S/S 노후불량 PT 교체용 자재전용 철거","2026-04-27 09:00","2026-04-28 18:00","취소","취소","연속"]
[23,"남서울","동서울","동서울S/S CB 7400","동서울S/S GIS PT 철거공사","신양재S/S 노후불량 PT 교체용 자재전용 철거","2026-04-28 09:00","2026-04-30 18:00","취소","취소","연속"]
[24,"남서울","동서울","동서울미금#2 T/L","2026년 가공송전 순시점검 위탁공사","- 공 사 명 : 동서울-미금#2T/L 초기점검 및 정밀점검 - 점검내용 : 초기점검(No.5~8) 및 지지물, 전선,금구류 정밀점검","2026-04-27 09:00","2026-04-30 18:00","취소","취소","연속"]
[25,"남서울","동서울","동서울S/S CB 7872","동서울S/S GIS PT 철거공사","신양재S/S 노후불량 PT 교체용 자재전용 철거","2026-04-27 09:00","2026-04-28 18:00","취소","취소","연속"]
[26,"남서울","동서울","동서울미금#1 T/L","2026년 가공송전 순시점검 위탁공사","- 공 사 명 : 동서울-미금#1T/L 초기점검 및 정밀점검 - 점검내용 : 초기점검(No.5~8) 및 지지물, 전선,금구류 정밀점검","2026-04-21 09:00","2026-04-24 18:00","취소","취소","연속"]
[27,"남서울","동서울","동서울S/S CB 7472","동서울S/S GIS PT 철거공사","신양재S/S 노후불량 PT 교체용 자재전용 철거","2026-04-28 09:00","2026-04-30 18:00","취소","취소","연속"]
[28,"남서울","영등포","서서울신광명#2 T/L"," 서서울-신광명#2T/L 지장송전선로 이설공사","No.38, 42 보강, No.39,41 인클로징, No.40 신규이설","2026-04-01 09:00","2026-04-12 18:00","취소","취소","연속"]
[29,"남서울","영등포","신광명신문래#1 T/L"," 광명-서울 고속도로 지장송전선로 이설공사","ㅇ 공사목적 : 광명-서울 고속도로 건설에 따른 지장송전선로 이설 ㅇ 공사구간 : J/B#3~J/B#4","2026-04-01 09:00","2026-05-08 18:00","2026-04-01 09:00","2026-05-08 18:00","연속"]
[30,"남서울","영등포","신시흥신광명#2 T/L"," 신광명S/S GIS 대체 및 S/W 증설공사","- 63kA GIS 28CB 설치 - 기타 부대공사","2026-04-01 09:00","2026-04-30 18:00","취소","취소","연속"]
[31,"남서울","영등포","신광명S/S #2 M.Tr","신광명S/S #2M.Tr 3차측 GPT 점검","신광명S/S #2M.Tr 3차측 GPT 점검","2026-04-20 09:00","2026-04-24 18:00","취소","취소","당일"]
[32,"남서울","영등포","서서울신광명#1 T/L"," 서서울-신광명#1T/L 지장송전선로 이설공사","No.38, 42 보강, No.39,41 인클로징, No.40 신규이설","2026-04-13 09:00","2026-04-22 18:00","취소","취소","연속"]
[33,"남서울","직할","신문래S/S #1 M.Tr","현대제 170kV GIS 단로기 링크교체","현대제 170kV GIS 단로기 링크교체","2026-04-20 09:00","2026-04-22 18:00","2026-04-23 15:00","2026-04-25 08:00","연속"]
[34,"남서울","직할","신문래S/S #1 M.Tr","현대제 170kV GIS 단로기 링크교체","현대제 170kV GIS 단로기 링크교체","2026-04-01 09:00","2026-04-03 18:00","취소","취소","연속"]
[35,"인천","김포","가정개폐소 CB 7272","가정개폐소 가정-갈산#3T/L(7272) GIS 보통점검","가정개폐소 가정-갈산#3T/L(7272) GIS 보통점검 - 상시 보조계전기 교체","2026-04-01 09:00","2026-04-01 18:00","2026-04-01 09:00","2026-04-01 18:00","당일"]
[36,"인천","부평","신경서포스코CC#1 T/L","포스코S/Y #3 CLR 보통점검(신경서-포스코#1)","포스코S/Y #3 CLR 보통점검(신경서-포스코#1)","2026-04-01 09:00","2026-04-01 18:00","2026-04-01 09:00","2026-04-01 18:00","당일"]
[37,"인천","직할","신부평S/S #2 Sh.R CB","신부평S/S #2Sh.R 7279 GIS 조작시험","신부평S/S #2Sh.R 7279 GIS 조작시험 및 #2Sh.R 방열판 청소","2026-04-01 09:30","2026-04-01 18:00","2026-04-01 09:30","2026-04-01 18:00","당일"]
[38,"인천","김포","가정개폐소 CB 7300","가정 신가좌가정#2T/L TIE(7300) GIS 보통점검","가정개폐소 신가좌-가정#2T/L TIE(7300) GIS 보통점검 - 상시보조계전기 교체","2026-04-02 09:00","2026-04-02 18:00","취소","취소","당일"]
[39,"인천","부평","포스코CC인천CC#2 T/L","포스코S/Y #2 CLR 보통점검(포스코-인천CC#2T/L)","포스코S/Y #2 CLR 보통점검(포스코-인천CC#2T/L)","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[40,"인천","김포","가정개폐소 #1 Sh.R CB","가정개폐소 #1Sh.R 누유보수","가정개폐소 #1Sh.R 누유보수","2026-04-02 10:00","2026-04-02 18:00","2026-04-02 10:00","2026-04-02 18:00","당일"]
[41,"인천","김포","가정개폐소 CB 7371","가정개폐소 신가좌-가정#2T/L(7371) GIS 보통점검","가정개폐소 신가좌-가정#2T/L(7371) GIS 보통점검 - 보조계전기 교체","2026-04-03 09:00","2026-04-03 18:00","2026-04-03 09:00","2026-04-03 18:00","당일"]
[42,"인천","김포","신김포S/S CB 7471","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험(7471)","2026-04-03 12:00","2026-04-03 12:30","취소","취소","당일"]
[43,"인천","김포","신김포S/S CB 7400","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험(7400)","2026-04-03 12:30","2026-04-03 13:00","취소","취소","당일"]
[44,"인천","김포","신김포S/S CB 7500","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험(7500)","2026-04-03 13:00","2026-04-03 13:30","취소","취소","당일"]
[45,"인천","김포","신김포S/S CB 7572","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험(7572)","2026-04-03 13:30","2026-04-03 14:00","취소","취소","당일"]
[46,"인천","김포","신김포S/S CB 7571","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험(7571)","2026-04-03 14:00","2026-04-03 14:30","취소","취소","당일"]
[47,"인천","김포","신김포S/S CB 7371","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험(7371)","2026-04-03 14:30","2026-04-03 15:00","취소","취소","당일"]
[48,"인천","김포","신김포S/S CB 7300","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험","신김포S/S SPS PNL 대체 관련 차단기 접점 동작 시험(7300)","2026-04-03 15:00","2026-04-03 15:30","취소","취소","당일"]
[49,"인천","김포","신김포서인천CC T/L","’25∼26년 인천본부 김포전력지사 지중송전 협력회사 공사","피뢰기 열화진단","2026-04-06 08:00","2026-04-06 18:00","취소","취소","당일"]
[50,"인천","부평","가정인천CC#2 T/L"," 가정-인천CC #2T/L EBG 해체점검","EBG B상 아세틸렌 가스 검출에 따른 해체점검 시행","2026-04-06 09:00","2026-04-10 18:00","취소","취소","연속"]
[51,"인천","직할","신부평S/S #4 M.Tr","신부평S/S 노후 보호배전반 교체공사","신부평S/S 74 Bay 차단실패보호반 교체, 서인천CC신부평#4T/L 보호배전반 교체 및 GIS 조작시험(7471, 7400, 7472)","2026-04-06 09:00","2026-04-10 18:00","2026-04-06 09:00","2026-04-10 18:00","연속"]
[52,"인천","부평","서인천C/C #2 M.Tr","서인천C/C #2 M.Tr 보통점검 및 금구류 교체","서인천C/C #2 M.Tr 보통점검 및 금구류 교체","2026-04-07 09:00","2026-04-10 18:00","2026-04-07 09:00","2026-04-10 18:00","당일"]
[53,"인천","부평","신인천C/C CB 7600","3MT001-3MT201 TIE 7600 GIS 보통점검(오버홀병행)","신인천C/C 3MT001-3MT201 TIE 7600 GIS 보통점검(오버홀병행)(7600)","2026-04-08 09:00","2026-04-08 13:00","2026-04-08 09:00","2026-04-08 13:00","연속"]
[54,"인천","부평","신인천C/C CB 7672","신인천 3MT201 7672 GIS 보통점검(오버홀병행)","신인천C/C 3MT201 7672 GIS 보통점검(오버홀병행)(7672)","2026-04-08 09:00","2026-04-08 18:00","2026-04-08 09:00","2026-04-08 18:00","연속"]
[55,"인천","직할","갈산S/S #1 Sh.R CB","갈산S/S #1Sh.R 방열판 청소 및 GIS 보통점검","갈산S/S #1Sh.R 방열판 청소 및 7671, 7600 GIS 보통점검","2026-04-08 09:30","2026-04-08 18:00","2026-04-08 09:30","2026-04-08 18:00","당일"]
[56,"인천","시흥","신가좌신시흥#1 T/L","신시흥S/S 154kV Sh.R 증설공사","#65BUS 무부하 가압 및 상체크","2026-04-08 18:00","2026-04-09 18:00","2026-04-08 18:00","2026-04-09 18:00","연속"]
[57,"인천","직할","갈산S/S #2 Sh.R CB","갈산S/S #1Sh.R 방열판 청소 및 GIS 보통점검","갈산S/S #1Sh.R 방열판 청소 및 7672 GIS 보통점검","2026-04-09 09:30","2026-04-09 18:00","2026-04-09 09:30","2026-04-09 18:00","당일"]
[58,"인천","부평","포스코CC인천CC#1 T/L","포스코S/Y #1 CLR 보통점검(포스코-인천CC#1T/L)","포스코S/Y #1 CLR 보통점검(포스코-인천CC#1T/L)","2026-04-11 09:00","2026-04-11 18:00","2026-04-11 09:00","2026-04-11 18:00","당일"]
[59,"인천","시흥","신가좌신시흥#1 T/L","신시흥S/S 154kV Sh.R 증설공사","#60BUS 무부하 가압 및 상체크","2026-04-11 18:00","2026-04-12 18:00","취소","취소","연속"]
[60,"인천","시흥","신시흥영흥TP#1 T/L","신시흥S/S 7701,7761 DS 누기보수","신시흥S/S 7701,7761 DS 누기보수 (신시흥영흥TP#1T/L 휴전)","2026-04-13 08:00","2026-04-17 18:00","취소","취소","연속"]
[61,"인천","직할","서인천CC신부평#4 T/L","’25∼26년 인천본부 김포전력지사 지중송전 협력회사 공사","절연유 채유","2026-04-13 08:00","2026-04-14 18:00","2026-04-13 08:00","2026-04-14 18:00","연속"]
[62,"인천","시흥","신시흥S/S #71 BUS","신시흥S/S 7761 DS 누기보수","신시흥S/S 7761 DS 누기보수 (#71 BUS 휴전)","2026-04-13 08:00","2026-04-17 18:00","취소","취소","연속"]
[63,"인천","김포","신김포S/S #1 M.Tr","신김포S/S 73BAY B/F반 대체공사","신김포S/S 73BAY B/F반 대체공사","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[64,"인천","김포","신김포신파주#1 T/L","신김포S/S 신김포-신파주#1T/L 보호배전반 대체공사","신김포S/S 신김포-신파주#1T/L 보호배전반 대체공사","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[65,"인천","부평","서인천C/C CB 7171","서인천C/C 신김포-서인천CC T/L 7171 GIS 정밀점검","서인천C/C 신김포-서인천CC T/L 7171 GIS 정밀점검(7171)","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[66,"인천","부평","신가좌S/S #3 M.Tr","신가좌S/S #3M.Tr 보통점검, 2차피뢰기 교체","신가좌S/S #3M.Tr 보통점검, 2차피뢰기 교체","2026-04-13 09:00","2026-04-17 18:00","취소","취소","연속"]
[67,"인천","시흥","신시흥S/S #75 BUS","신시흥S/S #70-#75 모선보호반 대체","신시흥S/S #70-#75 모선보호반 대체관련 75BUS휴전","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[68,"인천","시흥","신시흥#2S/S #4 M.Tr","시흥 인천지역 전기공급시설 전력구공사(신시흥-신송도 1차)","○ 휴전구간 : 신시흥변전소 #4M.Tr ○ 전력구 가시설, 차수그라우팅, 구조물공사","2026-04-13 09:00","2026-04-30 18:00","취소","취소","연속"]
[69,"인천","시흥","신시화영흥TP#1 T/L","2026년 시흥전력지사 가공송전 순시점검 위탁공사(초기점검)","신시화분기 C/T 초기점검 2기 No.55~CT#1, CT#2~No.58","2026-04-14 07:30","2026-04-14 18:00","취소","취소","연속"]
[70,"인천","시흥","신시흥신시화#1 T/L","2026년 시흥전력지사 가공송전 순시점검 위탁공사(초기점검)","신시화분기 C/T 초기점검 2기 No.55~CT#1, CT#2~No.58","2026-04-15 07:30","2026-04-15 18:00","취소","취소","연속"]
[71,"인천","부평","서인천C/C #1 M.Tr","서인천복합S/Y #1M.Tr 부싱유채유, 금구류 교체","서인천복합S/Y #1M.Tr 부싱유채유, 금구류 교체","2026-04-15 09:00","2026-04-15 18:00","2026-04-15 09:00","2026-04-15 18:00","연속"]
[72,"인천","부평","인천C/C #2 Sh.R CB","인천CC S/Y #2 Sh.R 보통점검 및 누유보수","인천CC S/Y #2 Sh.R 보통점검 및 누유보수","2026-04-15 09:00","2026-04-17 18:00","취소","취소","연속"]
[73,"인천","시흥","신시화영흥TP#2 T/L","2026년 시흥전력지사 가공송전 순시점검 위탁공사(초기점검)","신시화분기 C/T 초기점검 2기 No.55~CT#1, CT#2~No.58","2026-04-16 07:30","2026-04-16 18:00","취소","취소","연속"]
[74,"인천","시흥","신시흥영흥TP#2 T/L","2026년 시흥전력지사 가공송전 순시점검 위탁공사(초기점검)","신시화분기 C/T 초기점검 2기 No.55~CT#1, CT#2~No.58","2026-04-16 07:30","2026-04-17 18:00","취소","취소","연속"]
[75,"인천","부평","서인천C/C CB 7777","서인천C/C #75-77 CLR 보통점검","서인천C/C #75-77 CLR 보통점검(7777)","2026-04-16 09:00","2026-04-16 18:00","2026-04-16 09:00","2026-04-16 18:00","당일"]
[76,"인천","부평","서인천C/C CB 7577","서인천C/C #75-77 CLR 보통점검","서인천C/C #75-77 CLR 보통점검(7577)","2026-04-16 09:00","2026-04-16 18:00","2026-04-16 09:00","2026-04-16 18:00","당일"]
[77,"인천","시흥","신시흥신시화#2 T/L","2026년 시흥전력지사 가공송전 순시점검 위탁공사(초기점검)","신시화분기 C/T 초기점검 2기 No.55~CT#1, CT#2~No.58","2026-04-17 07:30","2026-04-17 18:00","취소","취소","연속"]
[78,"인천","부평","서인천C/C CB 7077","서인천C/C #70-72 CLR 보통점검","서인천C/C #70-72 CLR 보통점검(7077)","2026-04-17 09:00","2026-04-17 18:00","2026-04-17 09:00","2026-04-17 18:00","당일"]
[79,"인천","부평","서인천C/C CB 7277","서인천C/C #70-72 CLR 보통점검","서인천C/C #70-72 CLR 보통점검(7277)","2026-04-17 09:00","2026-04-17 18:00","2026-04-17 09:00","2026-04-17 18:00","당일"]
[80,"인천","부평","신가좌가정#1 T/L","신가좌S/S #2 CLR 보통점검(신가좌-가정#1T/L)","신가좌S/S #2 CLR 보통점검(신가좌-가정#1T/L)","2026-04-18 09:00","2026-04-18 18:00","취소","취소","연속"]
[81,"인천","시흥","신가좌신시흥#1 T/L","신시흥S/S 7B01 DS 누기보수","신시흥S/S 7B01 DS 누기보수 (신가좌신시흥#1T/L 휴전)","2026-04-20 08:00","2026-04-24 18:00","취소","취소","연속"]
[82,"인천","직할","서인천CC신부평#2 T/L","’25∼26년 인천본부 김포전력지사 지중송전 협력회사 공사","절연유 채유","2026-04-20 08:00","2026-04-21 18:00","2026-04-20 08:00","2026-04-21 18:00","연속"]
[83,"인천","부평","서인천C/C CB 7172","서인천C/C #1M.Tr 1차 GIS 7172 GIS 정밀점검","서인천C/C #1M.Tr 1차 GIS 7172 GIS 정밀점검(7172)","2026-04-20 09:00","2026-04-24 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[84,"인천","부평","신가좌S/S #4 M.Tr","신가좌S/S #4M.Tr 보호반 대체, 보통점검","신가좌S/S #4M.Tr 보호반 대체, 보통점검","2026-04-20 09:00","2026-04-24 18:00","취소","취소","연속"]
[85,"인천","부평","인천C/C CB 7400","인천CC 신경서인천CC#2-가정인천CC#1T/L TIE 7400 정밀","인천CC S/Y 신경서인천CC#2-가정인천CC#1T/L TIE 7400 정밀 (7400)","2026-04-20 09:00","2026-04-24 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[86,"인천","시흥","신시흥S/S #70 BUS","신시흥S/S #70-#75 모선보호반 대체","신시흥S/S #70-#75 모선보호반 대체관련 70BUS휴전","2026-04-20 09:00","2026-04-24 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[87,"인천","직할","신부평S/S #1 Sh.R CB","신부평S/S #1Sh.R 7179 GIS 정밀점검","신부평S/S #1Sh.R 7179 GIS 정밀점검 및 방열판 청소","2026-04-20 09:30","2026-04-23 18:00","취소","취소","당일"]
[88,"인천","시흥","신시흥신안산#2 T/L","신시흥S/S 신시흥신안산#2T/L GIS 보통점검","신시흥S/S 신시흥신안산#2T/L GIS 보통점검(7471,7400)","2026-04-21 09:00","2026-04-21 18:00","취소","취소","당일"]
[89,"인천","직할","서인천CC신부평#3 T/L","’25∼26년 인천본부 김포전력지사 지중송전 협력회사 공사","절연유 채유","2026-04-22 08:00","2026-04-23 18:00","2026-04-22 08:00","2026-04-23 18:00","연속"]
[90,"인천","부평","서인천C/C #75 BUS","서인천C/C 7172 GIS 정밀점검 무부하 가압","서인천C/C 7172 GIS 정밀점검 무부하 가압","2026-04-24 14:00","2026-04-24 16:00","취소","취소","연속"]
[91,"인천","부평","서인천CC신부평#4 T/L","서인천C/C 7172 GIS 정밀점검 무부하 가압","서인천C/C 7172 GIS 정밀점검 무부하 가압","2026-04-24 14:00","2026-04-24 16:00","2026-04-24 14:00","2026-04-24 16:00","연속"]
[92,"인천","부평","신경서인천CC#2 T/L","신경서인천CC#2-가정인천CC#1T/L TIE 7400 GIS 무부하가압","신경서인천CC#2-가정인천CC#1T/L TIE 7400 GIS 무부하가압","2026-04-24 14:00","2026-04-24 15:00","2026-04-24 14:00","2026-04-24 15:00","연속"]
[93,"인천","부평","신가좌가정#2 T/L","신가좌S/S #1 CLR 보통점검(신가좌-가정#2T/L)","신가좌S/S #1 CLR 보통점검(신가좌-가정#2T/L)","2026-04-25 09:00","2026-04-25 18:00","취소","취소","연속"]
[94,"인천","부평","서인천C/C CB 7100","신김포서인천T/L-#1M.Tr 1차 TIE GIS 7100 GIS 정밀"," 신김포서인천CCT/L-#1M.Tr 1차 TIE GIS 7100 GIS 정밀점검","2026-04-26 09:00","2026-04-30 18:00","2026-04-26 09:00","2026-04-30 18:00","연속"]
[95,"인천","부평","인천C/C CB 7472","인천CC S/Y 가정-인천CC#1T/L 7472 GIS 정밀","인천CC S/Y 가정-인천CC#1T/L 7472 GIS 정밀점검","2026-04-26 09:00","2026-04-26 18:00","2026-04-26 09:00","2026-04-26 18:00","연속"]
[96,"인천","시흥","신시흥신광명#1 T/L","신시흥-신광명#1T/L 시흥장현 변전설비 정기검사","시흥장현 변전설비 정기검사(신시흥-신광명#1T/L ) - ES, DS 및 소내전원","2026-04-27 08:00","2026-04-27 18:00","취소","취소","당일"]
[97,"인천","김포","신김포신파주#2 T/L","신김포S/S 신김포-신파주#2T/L 보호배전반 대체공사","신김포S/S 신김포-신파주#2T/L 보호배전반 대체공사","2026-04-27 09:00","2026-05-01 18:00","2026-04-27 09:00","2026-05-01 18:00","연속"]
[98,"인천","부평","신경서S/S #3 M.Tr","신경서SS #3 M.Tr 보통점검, 피뢰기 보통점검","신경서S/S #3 M.Tr 보통점검, 1차피뢰기(A,B,C) 보통점검","2026-04-27 09:00","2026-05-01 18:00","2026-04-27 09:00","2026-05-01 18:00","연속"]
[99,"인천","시흥","신시흥#2S/S #6 M.Tr","신시흥S/S #6 M.Tr 보통점검","신시흥S/S #6 M.Tr 보통점검 - OLTC 보통점검 - 1,2,3차 LA 보통점검 - 1차 GIS 보통점검, 2차 GIS 보통점검 - #4S.Tr 하자점검 및 #4S.Tr VCB(4689) 대체, DS(4685) 보통점검 - 3차 PT 보통점검","2026-04-27 09:00","2026-05-01 18:00","2026-04-27 09:00","2026-05-01 18:00","연속"]
[100,"인천","직할","신부평S/S #3 Sh.R CB","신부평S/S #3Sh.R 7379 GIS 정밀점검","신부평S/S #3Sh.R 7379 GIS 정밀점검 및 방열판 청소","2026-04-27 09:30","2026-04-30 18:00","취소","취소","당일"]
[101,"인천","시흥","신시흥신광명#2 T/L","신시흥-신광명#2T/L 시흥장현 변전설비 정기검사","시흥장현 변전설비 정기검사(신시흥-신광명#2T/L ) - ES, DS 및 소내전원","2026-04-28 08:00","2026-04-28 18:00","취소","취소","당일"]
[102,"인천","시흥","신가좌신시흥#2 T/L","신가좌-신시흥#2T/L 시흥장현 변전설비 정기검사","시흥장현 변전설비 정기검사(신가좌-신시흥#2T/L ) - ES, DS 및 소내전원","2026-04-30 08:00","2026-04-30 18:00","취소","취소","당일"]
[103,"인천","부평","신김포서인천CC T/L","서인천C/C 7100 GIS 정밀점검 무부하 가압","서인천C/C 7100 GIS 정밀점검 무부하 가압","2026-04-30 14:00","2026-04-30 16:00","2026-04-30 14:00","2026-04-30 16:00","연속"]
[104,"인천","부평","가정인천CC#1 T/L"," 가정-인천CC#1T/L 7472 GIS 무부하가압"," 가정-인천CC#1T/L 7472 GIS 무부하가압","2026-04-30 14:00","2026-04-30 15:00","2026-04-30 14:00","2026-04-30 15:00","연속"]
[105,"경기북부","고양","신파주신덕은#1 T/L","김포-파주간 도로 건설공사","김포-파주간 도로 건설공사(한국도로공사)","2026-04-03 10:00","2026-04-03 12:00","취소","취소","당일"]
[106,"경기북부","고양","신덕은S/S LG디스플레이2T/L CB","2026년도 고양전력지사 362kV GIS 정밀점검공사","7072 GIS 정밀점검","2026-04-22 13:00","2026-04-24 18:00","2026-04-22 13:00","2026-04-24 18:00","연속"]
[107,"경기북부","고양","신파주신덕은#2 T/L","김포-파주간 도로 건설공사","김포-파주간 도로 건설공사(한국도로공사)","2026-04-22 08:00","2026-04-22 18:00","취소","취소","당일"]
[108,"경기북부","고양","신덕은동두천CC#2 T/L","26~27년 고양전력 가공송전협력회사 공사","추락방지장치(수평) 설치, 폴리머점퍼지지애자 설치","2026-04-27 07:30","2026-05-07 17:30","2026-04-27 07:30","2026-05-07 17:30","연속"]
[109,"경기북부","고양","신덕은S/S LG디스플레이1T/L CB","2026년도 고양전력지사 362kV GIS 정밀점검공사","7071 GIS 정밀점검","2026-04-20 09:00","2026-04-22 12:00","2026-04-20 09:00","2026-04-22 12:00","연속"]
[110,"경기북부","고양","신파주신덕은#2 T/L","김포-파주간 도로 건설공사","김포-파주간 도로 건설공사(한국도로공사)","2026-04-16 08:00","2026-04-17 18:00","취소","취소","당일"]
[111,"경기북부","고양","신파주신덕은#1 T/L","김포-파주간 도로 건설공사","김포-파주간 도로 건설공사(한국도로공사)","2026-04-09 10:00","2026-04-09 12:00","취소","취소","당일"]
[112,"경기북부","고양","신파주신덕은#1 T/L","김포-파주간 도로 건설공사","김포-파주간 도로 건설공사(한국도로공사)","2026-04-07 10:00","2026-04-07 12:00","취소","취소","당일"]
[113,"경기북부","고양","신덕은S/S #1 M.Tr","26~27년 경기북부본부 고양전력지사 변전정비회사 총액공사(변압기 점검)","신덕은S/S #1M.Tr 부싱 N2가스 보충 및 변압기 정밀점검 대상 관련 설비 파악","2026-04-01 09:00","2026-04-02 18:00","2026-04-01 09:00","2026-04-02 18:00","연속"]
[114,"경기북부","고양","신김포신파주#1 T/L","신파주S/S 장기사용 노후 배전반 대체공사"," 신김포-신파주#1T/L 보호반 및 #71 Bay B/F 보호반 대체","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[115,"경기북부","고양","신김포신파주#2 T/L","신파주S/S 장기사용 노후 배전반 대체공사"," 신김포-신파주#2T/L 보호반 및 #75 Bay B/F 보호반 대체","2026-04-27 09:00","2026-05-01 18:00","2026-04-27 09:00","2026-05-01 18:00","연속"]
[116,"경기북부","고양","신파주S/S #3 M.Tr","26~27년 경기북부본부 고양전력지사 변전정비회사 총액공사(변압기 점검)","신파주S/S #3M.Tr 본체 및 3차 GPT 보통점검, N2 압력계 점검","2026-04-20 09:00","2026-04-24 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[117,"경기북부","직할","동두천C/C CB 7472","동두천CC 동두천CC-양주 T/L SW 증설공사","동두천CC 74Bay B/F반 교체 및 74Bay GIS LCP 교체작업","2026-04-28 09:00","2026-05-14 18:00","2026-04-28 09:00","2026-05-14 18:00","연속"]
[118,"경기북부","직할","신의정부S/S #1 M.Tr","신의정부S/S 154kV 신의정부-금오, 용현#3T/L SW 증설공사","신의정부S/S 154kV 신의정부-용현#3T/L GIS 설치시 #1M.Tr 2차측 가공모선 근접","2026-04-13 09:00","2026-04-24 18:00","2026-04-13 09:00","2026-04-24 18:00","연속"]
[119,"경기북부","직할","신의정부S/S #3 M.Tr","26년 경기북부 직할 M.Tr 보통, 정밀점검 공사","신의정부S/S #3M.Tr 및 OLTC 정밀점검","2026-04-27 09:00","2026-05-08 18:00","2026-04-27 09:00","2026-05-08 18:00","연속"]
[120,"경기북부","직할","신의정부미금#2 T/L","2026년 가공송전 순시점검 위탁공사","정밀점검 신의정부-미금#2T/L No.1~69 (4.24~5.7) 병가선로 신의정부-송우#2T/L No.5~12 (4.27~28) 신가평-신의정부#1T/L No.139~143 (4.24)","2026-04-13 07:00","2026-04-23 18:00","2026-04-13 07:00","2026-04-23 18:00","연속"]
[121,"경기북부","직할","신파주양주#1 T/L","양주SS 동두천CC-양주T/L SW 및 CLR 설치공사","7300, 7500CB METER CT 증설","2026-04-27 09:00","2026-05-01 18:00","2026-04-27 09:00","2026-05-01 18:00","연속"]
[122,"경기북부","구리","미금S/S #1 M.Tr","안전한국훈련 1차 리허설","안전한국훈련 1차 리허설","2026-04-22 09:00","2026-04-22 18:00","2026-04-22 09:00","2026-04-22 18:00","당일"]
[123,"경기북부","구리","미금S/S #1 M.Tr","안전한국훈련 2차 리허설","안전한국훈련 2차 리허설","2026-04-29 09:00","2026-04-29 18:00","2026-04-29 09:00","2026-04-29 18:00","당일"]
[124,"경기북부","구리","미금S/S #3 M.Tr","‘26∼27년 구리전력지사 변전협력회사 총액공사","주변압기 부싱 절연유 채유","2026-04-16 09:00","2026-04-17 18:00","2026-04-16 09:00","2026-04-17 18:00","연속"]
[125,"경기북부","구리","미금S/S #2 M.Tr","‘26∼27년 구리전력지사 변전협력회사 총액공사","주변압기 부싱 절연유 채유","2026-04-06 09:00","2026-04-07 18:00","2026-04-06 09:00","2026-04-07 18:00","연속"]
[126,"경기북부","구리","미금S/S CB 7371","26-27년 구리전력지사 변전협력회사 공사"," GIS 하자점검(7371)","2026-04-03 09:00","2026-04-03 18:00","2026-04-03 09:00","2026-04-03 18:00","당일"]
[127,"경기북부","구리","신가평신의정부#1 T/L","구리송전협력회사 공사_추락방지장치 설치"," 신가평-신의정부#1T/L No.2~7 추락방지장치 설치 ( 신가평-미금#2T/L No.2~7 병가구간)","2026-04-01 07:00","2026-04-03 17:00","2026-04-01 07:00","2026-04-03 17:00","연속"]
[128,"경기북부","구리","신가평미금#2 T/L","구리송전협력회사 공사_추락방지장치 설치"," 신가평-미금#2T/L No.2~7 추락방지장치 설치 ( 신가평-신의정부#1T/L No.2~7 병가구간)","2026-04-01 07:00","2026-04-03 17:00","2026-04-01 07:00","2026-04-03 17:00","연속"]
[129,"경기북부","구리","신가평신의정부#2 T/L","구리송전협력회사 공사_추락방지장치 설치"," 신가평-신의정부#2T/L No.2~7 추락방지장치 설치 ( 신가평-미금#1T/L No.2~7 병가구간)","2026-04-06 07:00","2026-04-08 17:00","2026-04-06 07:00","2026-04-08 17:00","연속"]
[130,"경기북부","구리","신가평미금#1 T/L","구리송전협력회사 공사_추락방지장치 설치"," 신가평-미금#1T/L No.2~7 추락방지장치 설치 ( 신가평-신의정부#2T/L No.2~7 병가구간)","2026-04-06 07:00","2026-04-08 17:00","2026-04-06 07:00","2026-04-08 17:00","연속"]
[131,"경기북부","구리","신가평S/S #4 Sh.R CB","신가평S/S #4Sh.R 노후대체공사","신가평S/S #4Sh.R 노후대체공사","2026-04-06 09:00","2026-05-08 18:00","2026-04-06 09:00","2026-05-08 18:00","연속"]
[132,"경기북부","구리","신가평S/S CB 7600","신가평S/S #4Sh.R 노후대체공사","신가평S/S #4Sh.R 노후대체공사","2026-04-06 09:00","2026-05-08 18:00","2026-04-06 09:00","2026-05-08 18:00","연속"]
[133,"경기북부","구리","신가평S/S CB 7671","신가평S/S #4Sh.R 노후대체공사","신가평S/S #4Sh.R 노후대체공사","2026-04-06 09:00","2026-05-08 18:00","2026-04-06 09:00","2026-05-08 18:00","연속"]
[134,"경기북부","구리","신가평신의정부#1 T/L","2026년 가공송전 순시점검 위탁공사","정밀점검 신의정부-미금#2T/L No.1~69 (4.24~5.7) 병가선로 신의정부-송우#2T/L No.5~12 (4.27~28) 신가평-신의정부#1T/L No.139~143 (4.24)","2026-04-13 07:00","2026-04-13 18:00","2026-04-13 07:00","2026-04-13 18:00","당일"]
[135,"경기북부","구리","신가평S/S CB 7771","2026년도 구리전력지사 154kV 이상 GIS 보통점검"," GIS 보통점검(7771)","2026-04-28 09:00","2026-04-28 18:00","2026-04-28 09:00","2026-04-28 18:00","당일"]
[136,"경기북부","구리","신가평S/S CB 7571","2026년도 구리전력지사 154kV 이상 GIS 보통점검"," GIS 보통점검(7571)","2026-04-29 09:00","2026-04-29 18:00","2026-04-29 09:00","2026-04-29 18:00","당일"]
[137,"경기북부","구리","신가평S/S CB 7500","2026년도 구리전력지사 154kV 이상 GIS 보통점검"," GIS 보통점검(7500)","2026-04-30 09:00","2026-04-30 18:00","2026-04-30 09:00","2026-04-30 18:00","당일"]
[138,"경기북부","구리","신포천S/S #2 M.Tr","26-27년 구리전력지사 변전협력회사 총액공사"," M.Tr 순환여과","2026-04-23 09:00","2026-04-29 18:00","2026-04-23 09:00","2026-04-29 18:00","연속"]
[139,"경기북부","구리","신포천S/S #1 M.Tr","26-27년 구리전력지사 변전협력회사 총액공사"," M.Tr 순환여과","2026-04-20 09:00","2026-04-22 18:00","2026-04-20 09:00","2026-04-22 18:00","연속"]
[140,"경기북부","구리","신포천S/S #3 M.Tr","26-27년 구리전력지사 변전협력회사 총액공사"," M.Tr 순환여과","2026-04-08 09:00","2026-04-10 18:00","2026-04-08 09:00","2026-04-10 18:00","연속"]
[141,"경기북부","구리","신포천S/S CB 7171","26-27년 구리전력지사 변전협력회사 공사"," GIS 조작시험(7171)","2026-04-23 09:00","2026-04-23 18:00","2026-04-23 09:00","2026-04-23 18:00","당일"]
[142,"경기북부","구리","신가평포천LNGCC#1 T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","신가평-포천LNGCC T/L(수직설치:104기,수평:151기) : No.1~177","2026-04-09 07:00","2026-05-20 18:00","2026-04-09 07:00","2026-05-20 18:00","연속"]
[143,"경기","군포","서서울신광명#1 T/L","서서울S/S 서서울-신광명#1T/L 7500, 7571 GIS 조작시험","서서울S/S 서서울-신광명#1T/L 7500, 7571 GIS 조작시험, LA 초기점검","2026-04-01 09:00","2026-04-01 18:00","취소","취소","당일"]
[144,"경기","성남","신용인S/S #2 M.Tr","2026년 성남전력지사 변전협력회사 공사","- 2차 GIS 조작시험 - LA, CVT 보통점검 - 3차 Main 4289CB 초기점검 - 3차 Main 4285DS 보통점검 - 부싱절연유 채유(1,2차 A,B,C) - 부싱 절연열화 측정","2026-04-01 09:00","2026-04-01 18:00","2026-04-01 09:00","2026-04-01 18:00","당일"]
[145,"경기","평택","고덕S/S #3 M.Tr","2026년 평택 변전협력 총액공사(고덕#3MTr)","고덕S/S #3M.Tr 보통점검, 추락방지 설치 7571,7500,6344,4389 보통점검, 콘덴서 절연열화 측정","2026-04-01 09:00","2026-04-03 18:00","2026-04-01 09:00","2026-04-03 18:00","연속"]
[146,"경기","평택","평택T/P #3 M.Tr","2026년 평택 변전협력 총액공사(평택T/P #3Tie-Tr)","평택T/P #3Tie-Tr 1차 GIB 누기점검","2026-04-01 09:00","2026-04-01 18:00","2026-04-01 09:00","2026-04-01 18:00","당일"]
[147,"경기","군포","서서울신광명#2 T/L","서서울S/S 서서울-신광명#2T/L 7671 GIS 조작시험","서서울S/S 서서울-신광명#2T/L 7671 GIS 조작시험, PT 보통점검, LA 초기점검","2026-04-02 09:00","2026-04-02 18:00","취소","취소","당일"]
[148,"경기","성남","신성남S/S #2 M.Tr","2026년 성남전력지사 변전협력회사 공사","- 7272 보통점검, 절연열화 - 부싱절연유 채유 (1차 A,B,C / 2차 B,C) - 부싱 절연열화 - 3차 Main 4287 SIS보통점검 - #1S.Tr 보통점검 - #1S.Tr 4289-1 SIS보통점검","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[149,"경기","성남","신성남S/S #3 M.Tr","2026년 성남전력지사 변전협력회사 공사","- 7372 보통점검, 절연열화 - 부싱절연유 채유 (1차 A,B / 2차 A,B,C) - 부싱 절연열화 측정","2026-04-03 09:00","2026-04-03 18:00","2026-04-03 09:00","2026-04-03 18:00","당일"]
[150,"경기","군포","화성신안산#1 T/L","2026년 가공송전 순시점검 위탁공사(정밀점검)"," 화성-신안산 #1T/L 정밀점검 -대상 : No.1~30호","2026-04-06 09:00","2026-04-10 18:00","2026-04-06 09:00","2026-04-10 18:00","연속"]
[151,"경기","동부","곤지암S/S CB 7471","곤지암S/S 곤지암-동서울#2T/L 7471 GIS 보통점검 외","곤지암:곤지암-동서울#2T/L 7471(보통, 전자변 교체) *7471 전자변 교체(A,B상) *7461(C) 전자변 O-ring 교체","2026-04-06 09:00","2026-04-06 18:00","2026-04-06 09:00","2026-04-06 18:00","당일"]
[152,"경기","성남","신수원S/S #4 M.Tr","26년 성남전력 345,154kV M.Tr 정밀,보통점검 공사","M.Tr 보통점검 2차 GIS 조작시험 154kV LA 초기점검 부싱누설전류 진단장치 보수 (C상 2차부싱)","2026-04-06 09:00","2026-04-07 18:00","2026-04-06 09:00","2026-04-07 18:00","연속"]
[153,"경기","평택","고덕S/S #4 M.Tr","2026년 평택 변전협력 총액공사(고덕#4MTr)","고덕S/S #4M.Tr 보통점검, 추락방지 설치 7672,7600,6444,4489 보통점검, 콘덴서 절연열화 측정","2026-04-06 09:00","2026-04-08 18:00","2026-04-06 09:00","2026-04-08 18:00","연속"]
[154,"경기","동부","곤지암S/S CB 7271","곤지암S/S 곤지암-여주복합#1T/L 7271 GIS 보통점검 외","곤지암:곤지암-여주복합#1T/L 7271(보통, 전자변 교체) *7271 전자변 교체(A,B,C상) *7251(A) 전자변 O-ring 교체","2026-04-07 09:00","2026-04-07 18:00","2026-04-07 09:00","2026-04-07 18:00","당일"]
[155,"경기","직할","화성S/S #2 M.Tr","화성S/S #2M.Tr 2차 GIS 보통점검","- 화성S/S #2M.Tr 2차 GIS 보통점검 - #2M.Tr 부싱 절연유 채유(1차 BC, 2차 ABC)","2026-04-07 09:00","2026-04-07 18:00","2026-04-05 09:00","2026-04-05 18:00","당일"]
[156,"경기","동부","곤지암S/S CB 7400","곤지암S/S 곤지암-동서울#2T/L-TIE 7400 GIS 보통점검 외","곤지암:곤지암-동서울#2T/L-TIE 7400(보통,전자변 교체) *7400 전자변 교체(A,B상)","2026-04-08 09:00","2026-04-08 18:00","2026-04-08 09:00","2026-04-08 18:00","당일"]
[157,"경기","성남","신안성신용인#1 T/L","2026-2027년 성남전력지사 가공송전 협력회사 공사(피뢰기)","○ 피뢰기 설치공사 - 대상구간 : 신안성-신용인T/L No.2~60 ※ 신안성-신성남T/L 4회선 구간","2026-04-09 07:00","2026-04-16 18:00","2026-04-09 07:00","2026-04-16 18:00","연속"]
[158,"경기","성남","신안성신성남#1 T/L","2026-2027년 성남전력지사 가공송전 협력회사 공사(피뢰기)","○ 피뢰기 설치공사 - 대상구간 : 신안성-신성남T/L No.1~60 ※ 신안성-신용인T/L 4회선 구간(No.2~60)","2026-04-09 07:00","2026-04-16 18:00","취소","취소","연속"]
[159,"경기","동부","곤지암S/S #1 M.Tr","곤지암S/S #1M.Tr 보통점검 등","곤지암:#1M.Tr(보통), 7100(보통), 7172(보통, 전자변 교체), 6144(보통), 4189(보통), #1S.Tr(하자, 유입) *[20↑]#1M.Tr 부싱절연유 채유(A,B,C상) *2차 LA(보통), 3차 LA(대체) *7172 전자변 교체(A,B,C상)","2026-04-09 09:00","2026-04-10 18:00","2026-04-09 09:00","2026-04-10 18:00","연속"]
[160,"경기","평택","고덕#2S/S #4 M.Tr","2026년 평택 변전협력 총액공사(고덕2#4MTr)","고덕2S/S #4M.Tr 보통점검 7572,6A72보통점검, 콘덴서 절연열화 측정","2026-04-09 09:00","2026-04-10 18:00","2026-04-09 09:00","2026-04-10 18:00","연속"]
[161,"경기","군포","화성신안산#2 T/L","2026년 가공송전 순시점검 위탁공사(정밀점검)"," 화성-신안산 #2T/L 정밀점검 -대상 : No.1~30호","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[162,"경기","성남","신수원S/S #3 M.Tr","26년 성남전력 345,154kV M.Tr 정밀,보통점검 공사","M.Tr 보통점검(A,B상) 2차 GIS 보통점검 1차 CVT 보통점검 부싱절연유 채유(1,2차 A,B)","2026-04-13 09:00","2026-04-14 18:00","2026-04-13 09:00","2026-04-14 18:00","연속"]
[163,"경기","평택","서안성S/S #1 M.Tr","2026년 평택 변전협력 총액공사(서안성#1MTr)","서안성S/S #1M.Tr 보호반 대체 #1M.Tr 보통점검, 4189 조작시험, 부싱절연유채유","2026-04-13 09:00","2026-04-22 18:00","2026-04-13 09:00","2026-04-22 18:00","연속"]
[164,"경기","직할","화성S/S #1 M.Tr","화성S/S #1M.Tr 2차 GIS 보통점검","- 화성S/S #1M.Tr 2차 GIS 보통점검 - #1M.Tr 부싱 절연유 채유(1차 BC, 2차 ABC)","2026-04-14 09:00","2026-04-14 18:00","2026-04-12 09:00","2026-04-12 18:00","당일"]
[165,"경기","동부","곤지암S/S #2 M.Tr","곤지암S/S #2M.Tr 보통점검 등","곤지암:#2M.Tr(보통), 7300(보통, 전자변 교체), 7372(보통), 6244(보통), 4289(보통), #2S.Tr(초기, 유입) *[20↑]#2M.Tr 부싱절연유 채유(A,B,C상) *2차 LA(보통), 3차 LA(대체) *7300 전자변 교체(A,B,C상)","2026-04-16 09:00","2026-04-17 18:00","2026-04-16 09:00","2026-04-17 18:00","연속"]
[166,"경기","성남","신안성신수원#2 T/L"," 신안성-신수원#2T/L B상 방식층 해체점검"," 신안성-신수원#2T/L B상 접속함 좌측 연공부 발열로 인한 해체점검","2026-04-17 09:00","2026-04-17 18:00","2026-04-17 09:00","2026-04-17 18:00","당일"]
[167,"경기","평택","서안성S/S CB 7500","2026년 평택 변전협력 총액공사(고덕2-서안성#1T/L TIE)","서안성S/S 고덕2-서안성#1T/L TIE GIS[7500] 하이드로오일 충유 및 에어벤팅","2026-04-17 09:00","2026-04-17 18:00","2026-04-17 09:00","2026-04-17 18:00","연속"]
[168,"경기","군포","서서울#2신시흥#2 T/L"," 서서울2-신시흥T/L 16~17호 전력선 이도조정"," 서서울2-신시흥T/L 16~17호 전력선 이도조정","2026-04-20 07:00","2026-04-21 18:00","2026-04-20 07:00","2026-04-21 18:00","연속"]
[169,"경기","직할","화성S/S #4 M.Tr","화성S/S #4 M.Tr 2차 GIS 조작시험","- 화성S/S #4M.Tr 2차 GIS 조작시험 - #2M.Tr 부싱 절연유 채유(1차 ABC, 2차 ABC)","2026-04-21 09:00","2026-04-21 18:00","2026-04-19 09:00","2026-04-19 18:00","당일"]
[170,"경기","군포","화성서서울#1 T/L"," 화성-서서울T/L 26~28호 전력선 이도조정"," 화성-서서울T/L 26~28호 전력선 이도조정","2026-04-22 07:00","2026-04-23 18:00","2026-04-22 07:00","2026-04-23 18:00","연속"]
[171,"경기","성남","신용인S/S #3 M.Tr","26년 성남전력 345,154kV M.Tr 정밀,보통점검 공사","M.Tr 보통점검 2차 GIS 조작시험 1차 LA 보통점검 1,3차 CVT 보통점검 3차 BUS 보통점검 부싱절연유 채유(1,2차 A,B,C)","2026-04-22 09:00","2026-04-23 18:00","2026-04-22 09:00","2026-04-23 18:00","연속"]
[172,"경기","성남","신성남신양재#1 T/L","2026-2027년 성남전력지사 가공송전 협력회사 공사(고정형폴리머)","○ 고정형폴리머 설치공사(안전이격확보) - 대상구간 : 154kV 신성남-염곡#1T/L No.17,20 ※ 신성남-신양재T/L 4회선 구간","2026-04-23 07:00","2026-04-23 18:00","2026-04-23 07:00","2026-04-23 18:00","당일"]
[173,"경기","동부","곤지암S/S #3 M.Tr","곤지암S/S #3M.Tr 보통점검 등","곤지암:#3M.Tr(보통), 7500(보통, 전자변 교체), 7572(보통, 전자변 교체), 6344(보통) *[20↑]#3M.Tr 부싱절연유 채유(A,B,C상) *2차 LA(보통), 3차 LA(보통) *7500 전자변 교체(A,B,C상) │ 7572 전자변 교체(A,B,C상) *7562(B) 전자변 O-ring 교체","2026-04-23 09:00","2026-04-24 18:00","2026-04-23 09:00","2026-04-24 18:00","연속"]
[174,"경기","성남","신성남신양재#2 T/L","2026-2027년 성남전력지사 가공송전 협력회사 공사(고정형폴리머)","○ 고정형폴리머 설치공사 - 대상구간 : 신성남-신양재#2T/L No.22 ※ 154kV 신성남-염곡T/L 4회선 구간","2026-04-24 07:00","2026-04-24 18:00","2026-04-24 07:00","2026-04-24 18:00","당일"]
[175,"경기","성남","신성남S/S STATCOM CB","26년 성남전력 345,154kV M.Tr 정밀,보통점검 공사","M.Tr 보통점검 STATCOM 냉각설비 보통점검 1차 LA 보통점검 7000 보통점검, 절연열화 7072 보통점검, 절연열화 #1,2S.Tr SIS 보통점검 (4189, 4289-2)","2026-04-27 09:00","2026-04-29 18:00","2026-04-27 09:00","2026-04-29 18:00","연속"]
[176,"경기","동부","곤지암S/S #4 M.Tr","곤지암S/S #4M.Tr 보통점검 등","곤지암:#4M.Tr(보통), 7600(보통), 7672(보통), 6444(보통) *#4M.Tr 부싱절연유 채유(A,B,C상) [ABB} *2차 LA(보통), 3차 LA(보통)","2026-04-28 09:00","2026-04-29 18:00","2026-04-28 09:00","2026-04-29 18:00","연속"]
[177,"경기","동부","곤지암S/S CB 7179","곤지암S/S #1Sh.R 7179 GIS 조작시험 등","곤지암:7179(조작) *7179 전자변 교체(A,B,C상)","2026-04-30 09:00","2026-04-30 18:00","2026-04-30 09:00","2026-04-30 18:00","당일"]
[178,"경기","성남","신성남동서울#1 T/L","성남지역 전기공급시설 전력구공사(동서울-신성남 용량증대) "," 동서울-신성남 용량증대 사업 관련 전력구 공사(비상시 즉시가압 가능) ","2026-04-16 09:00","2026-07-31 18:00","2026-04-28 09:00","2026-07-31 18:00","연속"]
[179,"경기","성남","신용인S/S #1 M.Tr","2026년 성남전력지사 변전협력회사 공사","M.Tr 정밀점검","2026-04-06 09:00","2026-04-17 18:00","2026-04-30 09:00","2026-04-30 18:00","연속"]
[180,"강원","강릉","양양P/P CB 7272","2026~2027년 변전협력회사 총액공사","362kV GIS 보통점검","2026-04-01 10:00","2026-04-01 18:00","2026-04-01 10:00","2026-04-01 18:00","당일"]
[181,"강원","강릉","양양P/P CB 7372","2026~2027년 변전협력회사 총액공사","362kV GIS 보통점검","2026-04-03 10:00","2026-04-03 18:00","2026-04-03 10:00","2026-04-03 18:00","당일"]
[182,"강원","강릉","양양P/P CB 7200","2026~2027년 변전협력회사 총액공사","362kV GIS 보통점검","2026-04-02 10:00","2026-04-02 18:00","2026-04-02 10:00","2026-04-02 18:00","당일"]
[183,"강원","동해","동해S/S CB 7171","2026~27년 변전정비팀 총액공사","동해S/S 7171 GIS 보통점검","2026-04-13 09:00","2026-04-13 18:00","2026-04-13 09:00","2026-04-13 18:00","당일"]
[184,"강원","동해","신제천동해#1 T/L","500kV HVDC 동해안-신가평 송전선로 건설사업(5공구)","발받침철탑 보호망 설치를 위한 휴전신청","2026-04-08 09:00","2026-04-10 18:00","2026-04-15 09:00","2026-04-17 18:00","연속"]
[185,"강원","동해","신제천동해#2 T/L","500kV HVDC 동해안-신가평 송전선로 건설사업(5공구)","발받침철탑 보호망 설치를 위한 휴전신청","2026-04-08 09:00","2026-04-10 18:00","2026-04-15 09:00","2026-04-17 18:00","연속"]
[186,"강원","동해","동해S/S CB 7100","2026~27년 변전정비팀 총액공사","동해S/S 7100 GIS 보통점검","2026-04-06 09:00","2026-04-06 18:00","2026-04-06 09:00","2026-04-06 18:00","당일"]
[187,"충북","직할","신청주S/S #3 M.Tr","신청주S/S 154kV 신규수용 SW 증설공사","69, 6A Bay 66BUS 측 설치 후 무부하가압","2026-04-14 09:00","2026-04-15 18:00","2026-04-14 09:00","2026-04-15 18:00","연속"]
[188,"충북","직할","신청주S/S #3 M.Tr","신청주S/S 154kV 신규수용 SW 증설공사","69, 6A Bay 61BUS 측 설치 후 무부하 가압","2026-04-24 09:00","2026-04-25 18:00","2026-04-24 09:00","2026-04-25 18:00","연속"]
[189,"충북","직할","신청주S/S #3 M.Tr","신청주S/S 건설공사","#3M.TR C상 2차측 GIB 가스누기 개소점검","2026-04-01 09:00","2026-04-03 18:00","2026-04-01 09:00","2026-04-03 18:00","연속"]
[190,"충북","청주","남청주S/S #5 M.Tr","'26~27 청주전력지사 변전협력회사 공사","하자점검(#5M.Tr, 1,2,3차 LA, 3차 GPT)","2026-04-15 09:00","2026-04-16 18:00","2026-04-15 09:00","2026-04-16 18:00","연속"]
[191,"충북","청주","남청주S/S #4 M.Tr","'26~27 청주전력지사 변전협력회사 공사","보통점검(2차 GIS, 3차 LA,PT,BUS, #2S.Tr VCB, DS), 하자점검(1,2차 LA)","2026-04-27 09:00","2026-04-29 18:00","2026-04-27 09:00","2026-04-29 18:00","연속"]
[192,"충북","청주","세종남청주#2 T/L","2026~2027년도 청주전력지사 송전협력회사 총액공사","2026~2027년도 청주전력지사 송전협력회사 총액공사 고정형폴리머지지애자 설치 등","2026-04-01 07:00","2026-04-01 18:00","2026-04-01 07:00","2026-04-01 18:00","연속"]
[193,"충북","청주","신옥천S/S #3 M.Tr","26~27 청주전력지사 변전협력회사 공사","보통점검(#3M.Tr 1차 GIS, #2S.Tr VCB,DS, #3-1Sh.R VCB,DS), 하자점검(2차 LA)","2026-04-01 08:00","2026-04-02 18:00","2026-04-01 08:00","2026-04-02 18:00","연속"]
[194,"충북","청주","신옥천S/S #1 M.Tr","26-27 청주전력지사 변전부 총액공사","1, 2차 부싱 절연유 채유(20년 이상 사용 부싱)","2026-04-09 09:00","2026-04-09 18:00","취소","취소","연속"]
[195,"충북","청주","신옥천세종#2 T/L","'26~27 청주전력지사 변전협력회사 공사","신옥천-세종#1T/L 초기점검(LA)","2026-04-17 08:00","2026-04-17 18:00","2026-04-17 08:00","2026-04-17 18:00","연속"]
[196,"충북","청주","신옥천신계룡 T/L","'26~27 청주전력지사 변전협력회사 공사","신옥천-신계룡T/L 보통점검(1차 GIS, TIE GIS, CVT), 초기점검(LA)","2026-04-20 08:00","2026-04-21 18:00","취소","취소","연속"]
[197,"충북","청주","신옥천청양 T/L","'26~27 청주전력지사 변전협력회사 공사","신옥천-청양T/L 보통점검(1차 GIS, TIE GIS, CVT), 초기점검(LA)","2026-04-22 08:00","2026-04-23 18:00","2026-04-22 08:00","2026-04-23 18:00","연속"]
[198,"충북","청주","신옥천S/S #2 M.Tr","'26~27 청주전력지사 변전협력회사 공사","보통점검(#2M.Tr 1차 GIS, TIE GIS, #1S.Tr VCB,DS), 하자점검(2차 LA, #2-1,2Sh.R VCB,DS)","2026-04-13 08:00","2026-04-14 18:00","2026-04-13 08:00","2026-04-14 18:00","연속"]
[199,"충북","충주","신제천신충주#2 T/L","신충주S/S #74BAY BF 보호반 대체","신충주S/S #74BAY BF 보호반 대체","2026-04-27 09:00","2026-04-30 18:00","2026-04-27 09:00","2026-04-30 18:00","연속"]
[200,"충북","충주","신충주S/S #3 M.Tr","신충주S/S #74BAY BF 보호반 대체","신충주S/S #74BAY BF 보호반 대체","2026-04-27 09:00","2026-04-30 18:00","2026-04-27 09:00","2026-04-30 18:00","연속"]
[201,"대전세종충남","대전","신계룡S/S #1 M.Tr","[가압X]신계룡S/S #1M.Tr 방열기 누유보수 및 병행작업","[가압X]신계룡S/S #1M.Tr 방열기 누유보수 및 병행작업","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[202,"대전세종충남","대전","신계룡S/S #3 M.Tr","[가압X]신계룡S/S #3M.Tr 송유펌프 교체 및 병행작업","[가압X]신계룡S/S #3M.Tr 송유펌프 교체 및 병행작업","2026-04-20 09:00","2026-04-24 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[203,"대전세종충남","서산","당진T/P #72 M.Tr","26-27 서산P/O 변전협력회사 총액공사","(3월 휴전 미승인시)당진화력S/S #72 Tie.Tr 부싱 절연유 채유 및 절연열화 진단","2026-04-09 09:00","2026-04-09 18:00","2026-04-09 09:00","2026-04-09 18:00","연속"]
[204,"대전세종충남","서산","당진T/P #71 M.Tr","26-27 서산P/O 변전협력회사 총액공사","(3월 휴전 미승인시)당진화력S/S #71 Tie.Tr 부싱 절연유 채유 및 절연열화 진단","2026-04-07 09:00","2026-04-07 18:00","2026-04-07 09:00","2026-04-07 18:00","연속"]
[205,"대전세종충남","서산","북당진고덕HVDC#1 Pole CB","26-27년 북당진-고덕 변환설비 위탁정비공사","1. 공사명 : 26-27년 북당진-고덕 HVDC 변환설비 위탁정비공사 2. 휴전설비 : 북당진-고덕#1T/L(#1Pole) 3. 작업내용 : #1Pole 변환설비 연차점검 - #1Pole C.Tr, Valve, 냉각, 공조설비 , 제어기 등","2026-04-13 09:00","2026-05-15 18:00","취소","취소","연속"]
[206,"대전세종충남","서산","북당진고덕HVDC#2 Pole CB","26-27년 북당진-고덕 변환설비 위탁정비공사","1. 공사명 : 26-27년 북당진-고덕 HVDC 변환설비 위탁정비공사 2. 휴전설비 : 북당진-고덕#2T/L(#2Pole) 3. 작업내용 : #2Pole 변환설비 연차점검 - #2Pole C.Tr, Valve, 냉각, 공조설비, 제어기 등","2026-04-13 09:00","2026-05-08 18:00","취소","취소","연속"]
[207,"대전세종충남","서산","북당진S/S CB 7872","26년 서산P/O GIS 보통,정밀점검공사","북당진S/S #4-1M.Tr 1차 7872 GIS 보통점검","2026-04-29 09:00","2026-04-30 18:00","2026-04-29 09:00","2026-04-30 18:00","연속"]
[208,"대전세종충남","서산","북당진S/S CB 7500","26년 서산P/O GIS 보통,정밀점검공사","북당진S/S #2Tie-Tr 1차 TIE 7500 GIS 보통점검","2026-04-09 09:00","2026-04-10 18:00","2026-04-09 09:00","2026-04-10 18:00","연속"]
[209,"대전세종충남","서산","신당진개폐소 SEC CB 7C7D0","26년 서산P/O GIS 보통,정밀점검공사","(3월휴전취소시) 신당진개폐소 #7C-7D BUS SEC GIS 보통점검","2026-04-15 09:00","2026-04-16 18:00","2026-04-15 09:00","2026-04-16 18:00","연속"]
[210,"대전세종충남","서산","신당진개폐소 CB 7A72","26년 서산P/O GIS 보통,정밀점검공사","(3월휴전취소시)신당진개폐소 신당진연락#1T/L 7A72 GIS 보통점검","2026-04-27 09:00","2026-04-28 18:00","2026-04-27 09:00","2026-04-28 18:00","연속"]
[211,"대전세종충남","서산","신당진개폐소북당진 T/L","26~27년도 서산전력지사 송전협력회사 공사"," 신당진개폐소-태안화력#2T/L 항공장애표시구 설치공사 No.126~127(1경간) *즉시가압가능(20분이내) * 신당진개폐소-태안화력#2T/L 병가구간, 신당진개폐소-태안화력#2T/L 휴전 미승인시 휴전 취소 요청","2026-04-24 08:00","2026-04-24 18:00","2026-04-24 08:00","2026-04-24 18:00","연속"]
[212,"대전세종충남","서산","신당진개폐소 SEC CB 7A7B0","26년 서산P/O GIS 보통,정밀점검공사","(3월휴전취소시)신당진개폐소 7A-7B-0 BUS SEC GIS 보통점검","2026-04-13 09:00","2026-04-14 18:00","2026-04-13 09:00","2026-04-14 18:00","연속"]
[213,"대전세종충남","서산","신당진S/S #2 M.Tr","'26년 서산P/O 변전협력회사 총액공사","신당진S/S #2M.Tr 차단실패 보호반대체(76BAY)","2026-04-13 09:30","2026-04-17 18:00","2026-04-13 09:30","2026-04-17 18:00","연속"]
[214,"대전세종충남","서산","신당진S/S #1 M.Tr","26-27 서산P/O 변전협력회사 총액공사","(3월 휴전 미승인시) 신당진S/S #1M.Tr 부싱 절연유 채유 및 절연열화 진단","2026-04-21 09:00","2026-04-21 18:00","2026-04-21 09:00","2026-04-21 18:00","연속"]
[215,"대전세종충남","서산","신당진S/S #2 M.Tr","26-27 서산P/O 변전협력회사 총액공사","(3월 휴전 미승인시) 신당진S/S #2M.Tr 부싱 절연유 채유 및 절연열화 진단","2026-04-23 09:00","2026-04-23 18:00","2026-04-23 09:00","2026-04-23 18:00","연속"]
[216,"대전세종충남","서산","신서산아산#1 T/L"," 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 신서산-아산#1 T/L No. 1~5, 32~46, 총 20기) , 즉시가압(20분 이내) 가능,주말 작업 없음.","2026-04-01 07:00","2026-04-02 18:00","2026-04-01 07:00","2026-04-02 18:00","매일"]
[217,"대전세종충남","서산","신당진개폐소태안TP#1 T/L"," 신성연분기T/L 건설공사"," 신성연분기T/L 건설공사 임시철탑(No.78-1) 구성","2026-04-28 07:00","2026-05-05 18:00","2026-04-28 07:00","2026-05-05 18:00","연속"]
[218,"대전세종충남","서산","신당진개폐소태안TP#2 T/L"," 신성연분기T/L 건설공사"," 신성연분기T/L 건설공사 임시철탑(No.78-1) 구성","2026-04-20 07:00","2026-04-27 18:00","2026-04-20 07:00","2026-04-27 18:00","연속"]
[219,"대전세종충남","서산","신당진개폐소태안TP#2 T/L"," 신서산-태안화력 등 19개T/L 수평 추락방지 설치공사","수평 추락방지장치 설치공사 ( 신당진-태안화력#2 T/L No. 0.1, 28~76,총 50기) , 즉시가압(20분 이내) 가능,주말 작업 없음.","2026-04-20 07:00","2026-04-24 18:00","취소","취소","매일"]
[220,"대전세종충남","세종","세종S/S #1 M.Tr","[변전]26년 세종전력지사 변전협력회사 총액공사","○ M.Tr 하자점검 - 1/2/3차 GIS, 3차 LA 하자점검 병행","2026-04-15 09:00","2026-04-17 18:00","2026-04-15 09:00","2026-04-17 18:00","연속"]
[221,"대전세종충남","천안","신온양S/S CB 7500","신온양S/S 7500 TIE CB 개폐타임 측정","신온양S/S 청양-신온양#1T/L-#3M.Tr 1차 7500CB 개폐타임측정","2026-04-03 07:00","2026-04-03 20:00","2026-04-03 07:00","2026-04-03 20:00","연속"]
[222,"대전세종충남","천안","신온양S/S CB 7571","신온양S/S 청양-신온양#1T/L 7571CB 개폐타임측정","신온양S/S 청양-신온양#1T/L 7571CB 개폐타임측정","2026-04-04 07:00","2026-04-04 20:00","2026-04-04 07:00","2026-04-04 20:00","연속"]
[223,"대전세종충남","천안","신온양S/S #4 M.Tr","(즉시가압불가)신온양S/S #4M.Tr 부싱절연유 채유","신온양S/S #4M.Tr 부싱절연유 채유(1/2회)","2026-04-07 09:00","2026-04-07 18:00","취소","취소","연속"]
[224,"대전세종충남","천안","신온양S/S #3 M.Tr","(즉시가압불가)신온양S/S #3M.Tr 보통점검","신온양S/S #3M.Tr 보통점검 (병행)신온양S/S #3M.Tr 1차,2차 GIS 보통 점검","2026-04-17 09:00","2026-04-18 18:00","2026-04-17 09:00","2026-04-18 18:00","연속"]
[225,"대전세종충남","천안","신탕정S/S CB 7271","26년 천안PO GIS 정밀 및 보통점검공사","신탕정S/S 신온양-신탕정#1T/L GIS(7271) 보통점검","2026-04-27 09:00","2026-04-27 18:00","2026-04-27 09:00","2026-04-27 18:00","연속"]
[226,"대전세종충남","천안","신탕정S/S CB 7571","26년 천안PO GIS 정밀 및 보통점검공사","신탕정S/S 북당진-신탕정#2T/L GIS(7571) 보통점검","2026-04-21 09:00","2026-04-21 18:00","2026-04-21 09:00","2026-04-21 18:00","연속"]
[227,"대전세종충남","천안","신탕정S/S #1 M.Tr","(즉시가압불가)신탕정S/S #1M.Tr 여과","신탕정S/S #1M.Tr 여과","2026-04-20 09:00","2026-04-30 18:00","2026-04-20 09:00","2026-04-30 18:00","연속"]
[228,"대전세종충남","천안","신탕정S/S #3 M.Tr","(즉시가압불가)신탕정S/S #3M.Tr 누유개소 보수","신탕정S/S #3M.Tr 콘서베이터 공기주머니, 누유개소 보수","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[229,"대전세종충남","천안","신탕정S/S CB 7471","26년 천안PO GIS 정밀 및 보통점검공사","신탕정S/S 신온양-신탕정#2T/L GIS(7471) 보통점검","2026-04-28 09:00","2026-04-28 18:00","2026-04-28 09:00","2026-04-28 18:00","연속"]
[230,"대전세종충남","천안","신탕정S/S CB 7500","26년 천안PO GIS 정밀 및 보통점검공사","신탕정S/S 북당진-신탕정#2T/L-TIE GIS(7500) 보통점검","2026-04-22 09:00","2026-04-22 18:00","2026-04-22 09:00","2026-04-22 18:00","연속"]
[231,"대전세종충남","천안","신탕정S/S CB 7171","26년 천안PO GIS 정밀 및 보통점검공사","신탕정S/S 북당진-신탕정#1T/L GIS(7171) 보통점검","2026-04-23 09:00","2026-04-23 18:00","2026-04-23 09:00","2026-04-23 18:00","연속"]
[232,"대전세종충남","천안","아산S/S CB 7272","아산S/S 아산-보령화력#1T/L 7272CB 개폐타임측정","아산S/S 아산-보령화력#1T/L 7272CB 개폐타임측정","2026-04-01 07:00","2026-04-01 20:00","2026-04-01 07:00","2026-04-01 20:00","연속"]
[233,"대전세종충남","천안","아산S/S #2 M.Tr","(즉시가압불가)아산SS #2M.Tr 부싱절연유 채유","아산S/S #2M.Tr 부싱절연유 채유(1차 B,C / 2차 A,B,C)","2026-04-26 09:00","2026-04-26 18:00","2026-04-26 09:00","2026-04-26 18:00","연속"]
[234,"대전세종충남","천안","아산S/S #4 M.Tr","(즉시가압불가)아산SS #4M.Tr 부싱절연유 채유","아산S/S #4M.Tr 부싱절연유 채유(1차 A,B,C / 2차 A,B,C)","2026-04-10 09:00","2026-04-10 18:00","취소","취소","연속"]
[235,"대전세종충남","천안","아산S/S CB 7371","아산S/S 신서산-아산#2T/L 7371CB 개폐타임측정","아산S/S 신서산-아산#2T/L 7371CB 개폐타임측정","2026-04-02 07:00","2026-04-02 20:00","2026-04-02 07:00","2026-04-02 20:00","연속"]
[236,"대전세종충남","천안","아산S/S CB 7471","아산S/S 아산-화성#1T/L 7471CB 개폐타임측정","아산S/S 아산-화성#1T/L 7471CB 개폐타임측정","2026-04-02 07:00","2026-04-02 20:00","2026-04-02 07:00","2026-04-02 20:00","연속"]
[237,"대전세종충남","천안","아산S/S #1 M.Tr","(즉시가압불가)아산S/S #1M.Tr 부싱절연유 채유","아산S/S #1M.Tr 부싱절연유 채유(1/2회)","2026-04-25 09:00","2026-04-25 18:00","취소","취소","연속"]
[238,"대전세종충남","천안","아산S/S CB 7100","아산S/S 7100 TIE CB 개폐타임측정","아산S/S 신서산아산#1-아산보령화력#2T/L 7100 TIE CB 개폐타임측정","2026-04-01 07:00","2026-04-01 20:00","2026-04-01 07:00","2026-04-01 20:00","연속"]
[239,"대전세종충남","천안","아산보령TP#1 T/L","[송전] 아산-보령화력#1T/L 정밀점검","[송전] 아산-보령화력#1T/L 정밀점검 No.123~190","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","매일"]
[240,"대전세종충남","천안","아산S/S #3 M.Tr","(즉시가압불가)아산S/S #3M.Tr 부싱절연유 채유","아산S/S #3M.Tr 부싱절연유 채유(1/1회)","2026-04-24 09:00","2026-04-24 18:00","취소","취소","연속"]
[241,"대전세종충남","청양","아산보령TP#2 T/L","[송전][즉시가압O] 아산-보령화력#2T/L 항공구 설치공사"," 아산-보령화력#2T/L 항공구 설치공사","2026-04-20 08:00","2026-04-24 18:00","취소","취소","매일"]
[242,"대전세종충남","청양","청양보령TP#1 T/L","[송전][즉시가압O] 청양-보령화력#1T/L 항공구 설치공사"," 청양-보령화력#1T/L 항공구 설치공사","2026-04-27 09:00","2026-04-30 18:00","2026-04-27 09:00","2026-04-30 18:00","매일"]
[243,"대전세종충남","청양","청양S/S CB 7400","[변전총액] 청양P/O 변전협력 총액공사","[변전총액] 청양S/S GIS(7400) 보통점검","2026-04-07 09:00","2026-04-07 18:00","2026-04-07 09:00","2026-04-07 18:00","연속"]
[244,"대전세종충남","청양","청양S/S CB 7700","[변전총액] 청양P/O 변전협력 총액공사","[변전총액] 청양S/S GIS(7700) 보통점검","2026-04-09 09:00","2026-04-09 18:00","2026-04-09 09:00","2026-04-09 18:00","연속"]
[245,"대전세종충남","청양","청양S/S CB 7500","[변전총액] 청양P/O 변전협력 총액공사","[변전총액] 청양S/S GIS(7500) 보통점검","2026-04-08 09:00","2026-04-08 18:00","2026-04-08 09:00","2026-04-08 18:00","연속"]
[246,"대전세종충남","청양","신옥천청양 T/L","[송전] 신옥천-청양 등T/L 추락방지장치 설치공사","[송전] 신옥천-청양T/L 추락방지장치 설치공사","2026-04-06 07:00","2026-04-10 11:00","2026-04-06 07:00","2026-04-10 11:00","매일"]
[247,"대전세종충남","청양","청양S/S CB 7300","[변전총액] 청양P/O 변전협력 총액공사","[변전총액] 청양S/S GIS(7300) 보통점검","2026-04-06 09:00","2026-04-06 18:00","2026-04-06 09:00","2026-04-06 18:00","연속"]
[248,"전북","직할","북경남무주양수 T/L","무주양수 7272 차단기 누기점검(무부하가압용 30분)","무주양수 7272 차단기 누기점검(무부하가압용 30분)","2026-04-14 15:00","2026-04-14 15:30","2026-04-14 15:00","2026-04-14 15:30","연속"]
[249,"전북","직할","무주P/P CB 7272","무주양수 7272 차단기 누기점검","무주양수 7272 차단기 누기점검","2026-04-13 09:00","2026-04-14 18:00","2026-04-13 09:00","2026-04-14 18:00","연속"]
[250,"전북","군산","군산S/S #2 M.Tr","#2 S.Tr 대체 및 #2M.Tr 기타 설비 점검","#2M.Tr 3차측 DS, PT 점검 및 장기사용 S.Tr 대체","2026-04-13 09:00","2026-04-15 18:00","2026-04-13 09:00","2026-04-15 18:00","연속"]
[251,"전북","군산","군산S/S #4 M.Tr","군산P/O 주변압기 정밀점검공사","주변압기 정밀점검공사","2026-04-01 09:00","2026-04-12 18:00","2026-04-01 09:00","2026-04-12 18:00","연속"]
[252,"전북","김제","신김제S/S #3 M.Tr","김제P/O 154kV 차단기 보통점검","- 신김제S/S #3M.Tr 1차 차단기 보통점검","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","연속"]
[253,"전북","직할","신남원한빛NP#2 T/L"," 신남원-한빛T/L 전선접속개소 전력선교체공사(전월신청분)","○ 전력선 및 가공지선 교체 : No.198~199, 217~218","2026-04-13 07:00","2026-04-17 18:00","취소","취소","연속"]
[254,"전북","직할","신옥천신남원#1 T/L"," 신옥천-신남원 등 3개T/L 추락방지시설 설치공사(전월신청분)"," 신옥천-신남원#1T/L 1~178호","2026-04-06 07:30","2026-04-17 17:00","취소","취소","매일"]
[255,"전북","직할","신남원한빛NP#1 T/L"," 신남원-한빛T/L 전선접속개소 전력선교체공사(전월신청분)","○ 전력선 및 가공지선 교체 : No.198~199, 217~218","2026-04-06 07:00","2026-04-10 18:00","취소","취소","연속"]
[256,"전북","직할","신옥천신남원#2 T/L"," 신옥천-신남원 등 3개T/L 추락방지시설 설치공사(전월신청분)"," 신옥천-신남원#2T/L 1~178호","2026-04-20 07:00","2026-04-30 17:00","취소","취소","매일"]
[257,"전북","직할","신남원신광주#1 T/L","'26년 전북 직할 가공송전 순시점검 위탁공사(전월신청분)","○ 정밀점검 : #1T/L No.1~115","2026-04-13 07:00","2026-04-17 17:00","2026-04-13 07:00","2026-04-17 17:00","연속"]
[258,"전북","직할","신남원신광주#2 T/L","'26년 전북 직할 가공송전 순시점검 위탁공사(전월신청분)","○ 정밀점검 : #2T/L No.1~115","2026-04-20 07:00","2026-04-23 17:00","2026-04-20 07:00","2026-04-23 17:00","연속"]
[259,"전북","직할","신남원광양#1 T/L","26~27년 전북직할 가공송전 협력회사 공사"," 신남원-광양T/L 피뢰기 설치(34기)","2026-04-06 09:00","2026-04-10 18:00","2026-04-06 09:00","2026-04-10 18:00","매일"]
[260,"광주전남","강진","신강진광양#2 T/L","2026~2027년 강진전력지사 송전협력회사 공사","민원으로 인한 저소음 항공장애구 교체 (#2 가공지선 기존 항공구 철거 후 저소음 설치)","2026-04-23 07:00","2026-04-23 18:00","취소","취소","연속"]
[261,"광주전남","강진","신강진광양#1 T/L","2026~2027년 강진전력지사 송전협력회사 공사","민원으로 인한 저소음 항공장애구 교체 (#1 OPGW 기존 항공구 철거 후 저소음 설치)","2026-04-22 07:00","2026-04-22 18:00","취소","취소","연속"]
[262,"광주전남","강진","신강진광양#1 T/L","'26~27년 강진전력지사 변전협력회사 공사","신강진S/S 74Bay B/F반 교체","2026-04-06 08:00","2026-04-17 18:00","취소","취소","연속"]
[263,"광주전남","강진","신강진S/S #3 M.Tr","'26~27년 강진전력지사 변전협력회사 공사","신강진S/S 74Bay B/F반 교체","2026-04-06 08:00","2026-04-17 18:00","취소","취소","연속"]
[264,"광주전남","강진","신강진광양#2 T/L","'26~27년 강진전력지사 변전협력회사 공사","신강진S/S 75Bay B/F반 교체","2026-04-20 08:00","2026-04-30 18:00","취소","취소","연속"]
[265,"광주전남","강진","신강진S/S #4 M.Tr","'26~27년 강진전력지사 변전협력회사 공사","신강진S/S 75Bay B/F반 교체","2026-04-20 08:00","2026-04-30 18:00","취소","취소","연속"]
[266,"광주전남","광주","신광주S/S CB 7172","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험","2026-04-14 08:00","2026-04-14 18:00","취소","취소","연속"]
[267,"광주전남","광주","신광주S/S CB 7800","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험","2026-04-09 08:00","2026-04-09 18:00","2026-04-09 08:00","2026-04-09 18:00","연속"]
[268,"광주전남","광주","신광주S/S #4 M.Tr","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험","2026-04-09 08:00","2026-04-09 18:00","2026-04-09 08:00","2026-04-09 18:00","연속"]
[269,"광주전남","광주","신광주S/S CB 7400","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험","2026-04-09 08:00","2026-04-09 18:00","2026-04-09 08:00","2026-04-09 18:00","연속"]
[270,"광주전남","광주","신광주S/S CB 7171","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험","2026-04-02 08:00","2026-04-02 18:00","2026-04-02 08:00","2026-04-02 18:00","연속"]
[271,"광주전남","광주","신남원신광주#2 T/L","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험","2026-04-08 08:00","2026-04-08 18:00","취소","취소","연속"]
[272,"광주전남","광주","신광주신화순#1 T/L","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험, LA점검","2026-04-02 08:00","2026-04-02 18:00","취소","취소","연속"]
[273,"광주전남","광주","신광주S/S CB 7471","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험","2026-04-01 08:00","2026-04-01 18:00","취소","취소","연속"]
[274,"광주전남","광주","신광주신화순#2 T/L","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험,","2026-04-16 08:00","2026-04-16 18:00","취소","취소","연속"]
[275,"광주전남","광주","신광주신화순#1 T/L","피앤씨테크 보호반 성능개선","신광주S/S 76Bay B/F PNL 보호반 성능개선","2026-04-29 08:00","2026-04-29 18:00","취소","취소","연속"]
[276,"광주전남","광주","신광주S/S #3 M.Tr","피앤씨테크 보호반 성능개선","신광주S/S 76Bay B/F PNL 보호반 성능개선","2026-04-29 08:00","2026-04-29 18:00","취소","취소","연속"]
[277,"광주전남","광주","신광주신화순#1 T/L","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험, LA점검","2026-04-15 08:00","2026-04-15 18:00","취소","취소","연속"]
[278,"광주전남","광주","신화순S/S #2 M.Tr","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험 LA 점검","2026-04-07 08:00","2026-04-07 18:00","2026-04-07 08:00","2026-04-07 18:00","연속"]
[279,"광주전남","광주","신화순S/S #1 M.Tr","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험 LA 점검","2026-04-06 08:00","2026-04-06 18:00","2026-04-06 08:00","2026-04-06 18:00","연속"]
[280,"광주전남","목포","신광주한빛NP#2 T/L"," 한빛연락T/L 철탑 추락방지장치 설치 등 3개 공사","고정형 중간클램프 및 폴리머 점퍼지지애자 설치 O 구간 - 고정형 클램프 설치 : 신광주-한빛 #1,2T/L No.1~69호(69기) - 폴리머 점퍼지지애자 설치 : 신광주-한빛 #1,2T/L No.1,16,35,47,65호(5기)","2026-04-07 08:00","2026-04-13 18:00","2026-04-07 08:00","2026-04-13 18:00","매일"]
[281,"광주전남","순천","광양CC여수TP#1 T/L","광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","#1T/L 폴리머점퍼지지애자 설치(1시간내가압가능)","2026-04-20 07:00","2026-04-23 18:00","2026-04-20 07:00","2026-04-23 18:00","매일"]
[282,"광주전남","순천","광양CC여수TP#2 T/L","광양CC-여수TPT/L 폴리머점퍼지지애자 설치공사","#2T/L폴리머점퍼지지애자 설치(1시간내가압가능)","2026-04-24 07:00","2026-04-24 18:00","2026-04-24 07:00","2026-04-24 18:00","연속"]
[283,"광주전남","순천","신남원광양#2 T/L","2026-2027년 순천전력지사 변전협력회사 공사","광양S/S 신남원-광양#2T/L CVT(C) 대체","2026-04-06 08:00","2026-04-06 18:00","취소","취소","연속"]
[284,"광주전남","순천","광양여수TP T/L","왕지2지구 일부지중화 관련 2개 T/L 철거공사","◎ 공사개요 : 광양-여수 TP 85~91호, 10기 철거 ◎ 휴전기간 : 신설 지중선로 EBA 접속작업 시행 및 인하선 접속작업. ◎ 휴일 작업 없음.","2026-04-07 08:00","2026-04-13 18:00","2026-04-07 08:00","2026-04-13 18:00","연속"]
[285,"광주전남","순천","광양S/S #3 M.Tr","26-27년 순천전력지사 변전협력회사 공사","광양S/S #3M.Tr 보호배전반 대체","2026-04-20 09:00","2026-04-24 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[286,"광주전남","순천","신남원광양#2 T/L","신남원-광양T/L 추락방지시설 설치공사","2T/L 수평추락방지 설치 (신남원-광양2, 광양-율촌CC 병가) (1시간내 가압가능)","2026-04-20 07:00","2026-04-23 18:00","취소","취소","매일"]
[287,"광주전남","순천","광양율촌CC T/L","신남원-광양T/L 추락방지시설 설치공사","2T/L 수평추락방지설치 (신남원-광양2, 광양-율촌CC 병가) (1시간내 가압가능)","2026-04-24 07:00","2026-04-24 18:00","취소","취소","매일"]
[288,"광주전남","순천","신강진광양#2 T/L","신강진-광양T/L 추락방지시설 설치공사","2T/L 수평추락방지설치 (2회선 구간) (1시간내 가압가능)","2026-04-20 07:00","2026-04-30 18:00","취소","취소","매일"]
[289,"광주전남","순천","광양하동TP#2 T/L","광양-하동TPT/L 추락방지시설 설치공사","#2T/L 수평추락방지시설치 (1시간내 가압가능)","2026-04-20 09:00","2026-04-24 18:00","취소","취소","매일"]
[290,"광주전남","순천","광양하동TP#1 T/L","광양-하동TP T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(1시간내가압가능)","2026-04-20 09:00","2026-04-24 18:00","취소","취소","매일"]
[291,"광주전남","순천","광양여수TP T/L","2026-2027년 순천전력지사 변전협력회사 공사","광양S/S 광양-여수TP T/L CVT(C) 대체 여수화력 광양-여수T/P T/L GIS 보통점검","2026-04-07 08:00","2026-04-07 18:00","취소","취소","연속"]
[292,"광주전남","순천","광양S/S #1 M.Tr","2026~2027년 순천전력지사 변전협력회사 공사","광양S/S #1M.Tr 2차 부싱 절연유 채유, 3차 MAIN VCB 조작시험","2026-04-06 09:00","2026-04-06 16:00","2026-04-06 09:00","2026-04-06 16:00","연속"]
[293,"광주전남","순천","신남원광양#1 T/L","신남원-광양T/L 추락방지시설 설치공사","1T/L 수평추락방지설치 (신남원-광양1, 광양-여수TP 병가) (1시간내 가압가능)","2026-04-06 07:00","2026-04-17 18:00","취소","취소","매일"]
[294,"광주전남","순천","광양여수TP T/L","신남원-광양T/L 추락방지시설 설치공사","#1T/L 수평추락방지설치 (신남원-광양1, 광양-여수TP 병가) (1시간내 가압가능)","2026-04-06 07:00","2026-04-17 18:00","취소","취소","매일"]
[295,"광주전남","순천","신강진광양#1 T/L","신강진-광양T/L 추락방지시설 설치공사","1T/L 수평추락방지설치 (2회선 구간) (1시간내 가압가능)","2026-04-06 07:00","2026-04-17 18:00","취소","취소","매일"]
[296,"광주전남","순천","광양광양제철#1 T/L","광양-광양CCT/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(광양-광양CC1, 광양제철1 병가)(1시간내가압가능)","2026-04-27 07:00","2026-04-30 18:00","2026-04-27 07:00","2026-04-30 18:00","매일"]
[297,"광주전남","순천","광양광양CC#1 T/L","광양-광양CCT/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(1시간내가압가능)","2026-04-27 07:00","2026-04-30 18:00","2026-04-27 07:00","2026-04-30 18:00","매일"]
[298,"광주전남","순천","광양율촌CC T/L","2026-2027년 순천전력지사 변전협력회사 공사","광양S/S 광양-율촌CC T/L LA 보통점검, CVT 대체 율촌CC 광양-율촌CC T/L(7171,7100) GIS 조작시험","2026-04-27 09:00","2026-04-28 18:00","취소","취소","연속"]
[299,"광주전남","순천","광양광양CC#1 T/L","2026-2027년 순천전력지사 변전협력회사 공사","광양CC 광양광양CC#1T/L LA,CVT(A,V,C) 대체, 7271CB 조작시험","2026-04-29 09:00","2026-04-30 18:00","2026-04-29 09:00","2026-04-30 18:00","연속"]
[300,"광주전남","순천","광양율촌CC T/L","왕지2지구 일부지중화 관련 2개 T/L 철거공사","◎ 공사개요 : 광양-여수 TP 85~91호, 10기 철거 ◎ 휴전기간 : 84~85호 전선 철거 및 신설 지중선로 EBA 접속작업 시행. ◎ 휴일 작업 없음.","2026-04-27 09:00","2026-05-01 18:00","2026-04-27 09:00","2026-05-01 18:00","연속"]
[301,"광주전남","순천","여수T/P #1 M.Tr","2026~2027년 순천전력지사 변전협력회사 공사","여수화력S/S #1M.Tr 2차 부싱 절연유 채유, 1차 GIS(7100,7172) 조작시험, 2차 GIS 보통점검, 3차 VCB 초기점검, 1차 LA(A) 초기점검","2026-04-08 09:00","2026-04-09 18:00","2026-04-08 09:00","2026-04-09 18:00","연속"]
[302,"광주전남","순천","여수T/P #4 M.Tr","2026~2027년 순천전력지사 변전협력회사 공사","여수화력S/S #4M.Tr, 1,2차 GIS, 3차 SIS, 2차 LA(A,B,C) 보통점검","2026-04-13 09:00","2026-04-15 18:00","2026-04-13 09:00","2026-04-15 18:00","연속"]
[303,"대구","경산","신경산S/S #1 M.Tr","26~27년 경산 변전협력 기기점검공사","- 7000 7072 조작시험","2026-04-13 09:30","2026-04-13 18:00","2026-04-13 09:30","2026-04-13 18:00","당일"]
[304,"대구","달성","고령의령#2 T/L","24~25년 달성전력지사 송전협력회사공사","24~25년 달성전력지사 송전협력회사공사 04.07(화) 고령-의령#2T/L 148호 2번선 점퍼선 및 스페이서 교체 02.18 155~156호 소도체 이도조정","2026-04-07 08:00","2026-04-07 18:00","취소","취소","당일"]
[305,"대구","달성","고령의령#1 T/L","26~27년 달성전력지사 가공송전 협력회사공사"," 고령-의령#1T/L 피뢰기 설치공사","2026-04-13 07:00","2026-04-17 18:00","취소","취소","연속"]
[306,"대구","달성","서대구고령#2 T/L","26~27년 달성전력지사 가공송전 협력회사공사(안전확보)"," 고령-의령#1T/L 피뢰기 설치공사 관련 안전확보","2026-04-13 07:00","2026-04-17 18:00","취소","취소","연속"]
[307,"대구","칠곡","북경남서대구#2 T/L","26~27년 달성전력지사 가공송전 협력회사공사","4.6(월) : 북경남-서대구#2 4호 스페이서 교체 및 스플라이스 시공 4.7(화) : 북경남-서대구#2 35호 스페이서 교체 및 스플라이스 시공 4.8(수) : 북경남-서대구#2 106호 스페이서 교체 및 스플라이스 시공 4.9(목) : 북경남-서대구#2 17호 스페이서 교체 및 스플라이스 시공","2026-04-06 07:00","2026-04-09 18:00","2026-04-06 07:00","2026-04-09 18:00","연속"]
[308,"대구","칠곡","서대구S/S CB 7472","서대구S/S GCB 공기조작부 정밀점검공사","서대구S/S 1차 7472 GCB 공기조작부 정밀점검","2026-04-08 09:00","2026-04-09 18:00","2026-04-08 09:00","2026-04-09 18:00","연속"]
[309,"대구","칠곡","서대구S/S CB 7871","26~27년 칠곡전력지사 변전협력회사 공사","서대구S/S 북대구-서대구#1T/L 7871 GCB 보통점검","2026-04-15 09:30","2026-04-15 18:00","2026-04-14 09:30","2026-04-14 18:00","당일"]
[310,"대구","칠곡","북대구서대구#2 T/L","26~27년 칠곡전력지사 변전협력회사 공사","서대구S/S 북대구-서대구#2T/L PT보통점검, 7772 GCB 보통점검","2026-04-16 09:30","2026-04-16 18:00","2026-04-16 09:30","2026-04-16 18:00","당일"]
[311,"대구","포항","신포항S/S #2 M.Tr","신포항S/S #5M.Tr 증설공사(일반도급)","#5M.Tr 증설공사관련 안전이격거리 확보","2026-04-20 09:00","2026-04-24 18:00","취소","취소","연속"]
[312,"대구","포항","신포항S/S #1 M.Tr","신포항S/S #5M.Tr 증설공사(일반도급)","#5M.Tr 증설관련 안전이격거리 확보","2026-04-13 09:00","2026-04-17 18:00","취소","취소","연속"]
[313,"경북","영주","한울#3N/P #2 BUS","동해안변환소 AC배후계통건설공사(변전)","- 362kV GIS 50kA -> 63kA 12CB 대체 - 362kV GIS 63kA 6CB 증설 - 기타 부대공사","2026-04-21 08:00","2026-04-23 10:00","2026-04-21 08:00","2026-04-23 10:00","연속"]
[314,"경북","영주","한울#3N/P #1 BUS","동해안변환소 AC배후계통건설공사(변전)","- 362kV GIS 50kA -> 63kA 12CB 대체 - 362kV GIS 63kA 6CB 증설 - 기타 부대공사","2026-04-19 08:00","2026-04-21 10:00","2026-04-19 08:00","2026-04-21 10:00","연속"]
[315,"경북","영주","신한울한울#2 T/L","동해안변환소 AC배후계통건설공사(변전)","- 362kV GIS 50kA -> 63kA 12CB 대체 - 362kV GIS 63kA 6CB 증설 - 기타 부대공사","2026-04-19 08:00","2026-06-05 18:00","2026-04-19 08:00","2026-06-05 18:00","연속"]
[316,"경북","영주","한울2NP한울3NP#3 T/L","동해안변환소 AC배후계통건설공사(변전)","- 362kV GIS 50kA -> 63kA 12CB 대체 - 362kV GIS 63kA 6CB 증설 - 기타 부대공사","2026-04-07 10:00","2026-04-08 12:00","2026-04-07 10:00","2026-04-08 12:00","연속"]
[317,"경북","직할","안동C/C #1 M.Tr","안동복합S/S 계통연계용 GIS 증설공사","7172GIS 전력케이블 연결 후 무부하 가압","2026-04-23 09:00","2026-04-24 11:00","2026-04-23 09:00","2026-04-24 11:00","연속"]
[318,"경북","직할","안동C/C CB 7100","안동복합S/S 계통연계용 GIS 증설공사","7172GIS 전력케이블 연결 후 무부하 가압","2026-04-23 09:00","2026-04-24 11:00","2026-04-23 09:00","2026-04-24 11:00","연속"]
[319,"경북","직할","안동C/C #75 BUS","안동복합S/S 계통연계용 GIS 증설공사","7172GIS 전력케이블 연결 후 무부하 가압","2026-04-23 09:00","2026-04-24 11:00","2026-04-23 09:00","2026-04-24 11:00","연속"]
[320,"경북","직할","신영주청송PP T/L"," 청송분기T/L 불량애자 교체공사","- 신영주-청송PPT/L 불량애자 교체","2026-04-08 09:00","2026-05-06 18:00","2026-04-08 09:00","2026-05-06 18:00","연속"]
[321,"부산울산","동부산","고리N/P CB 7500","고리NP S/Y GIS 정밀점검공사","고리NP S/Y GIS 정밀점검공사(7500)","2026-04-20 09:00","2026-04-26 18:00","2026-04-20 09:00","2026-04-26 18:00","연속"]
[322,"부산울산","동부산","고리N/P #76 BUS","고리NP S/Y GIS 정밀점검공사","고리NP S/Y GIS 정밀점검공사(7677) 시험가압","2026-04-17 16:00","2026-04-17 17:00","2026-04-17 16:00","2026-04-17 17:00","당일"]
[323,"부산울산","동부산","고리N/P CB 7677","고리NP S/Y GIS 정밀점검공사","고리NP S/Y GIS 정밀점검공사(7677)","2026-04-13 09:30","2026-04-19 18:00","2026-04-13 09:00","2026-04-19 18:00","연속"]
[324,"부산울산","동부산","고리N/P #71 BUS","고리NP S/Y GIS 정밀점검공사","고리NP S/Y GIS 정밀점검공사(7177) 시험가압","2026-04-10 16:00","2026-04-10 17:00","2026-04-10 16:00","2026-04-10 17:00","당일"]
[325,"부산울산","동부산","고리N/P CB 7677","고리NP S/Y GIS 정밀점검공사","고리NP S/Y GIS 정밀점검공사(7677)","2026-04-30 16:00","2026-04-30 17:00","2026-04-30 16:00","2026-04-30 17:00","연속"]
[326,"부산울산","동부산","고리N/P CB 7177","고리NP S/Y GIS 정밀점검공사","고리NP S/Y GIS 정밀점검공사(7177)","2026-04-24 16:00","2026-04-24 17:00","2026-04-24 16:00","2026-04-24 17:00","연속"]
[327,"부산울산","동부산","고리N/P #71 BUS","고리NP S/Y GIS 정밀점검공사","고리NP S/Y GIS 정밀점검공사(7500) 시험가압","2026-04-24 16:00","2026-04-24 17:00","2026-04-24 16:00","2026-04-24 17:00","당일"]
[328,"부산울산","동부산","고리N/P CB 7572","고리NP S/Y GIS 정밀점검공사","고리NP S/Y GIS 정밀점검공사(7572)","2026-04-27 09:00","2026-05-03 18:00","2026-04-27 09:00","2026-05-03 18:00","연속"]
[329,"부산울산","동부산","고리N/P #76 BUS","고리NP S/Y GIS 정밀점검공사","고리NP S/Y GIS 정밀점검공사(7572) 시험가압","2026-04-30 16:00","2026-04-30 17:00","2026-04-30 16:00","2026-04-30 17:00","연속"]
[330,"부산울산","동부산","고리N/P CB 7177","고리NP S/Y GIS 정밀점검공사","고리NP S/Y GIS 정밀점검공사(7177)","2026-04-06 09:00","2026-04-12 18:00","2026-04-06 09:00","2026-04-12 18:00","연속"]
[331,"부산울산","동부산","신양산북부산#1 T/L","신양산S/S 용량부족 차단기 교체공사(8차)","#1BUS 철거 안전이격","2026-04-20 08:00","2026-04-21 18:00","2026-04-19 08:00","2026-04-20 18:00","연속"]
[332,"부산울산","동부산","신양산고리NP#2 T/L","신양산S/S 용량부족 차단기 교체공사(8차)","#1BUS 철거 안전이격","2026-04-15 08:00","2026-04-16 18:00","2026-04-17 08:00","2026-04-18 18:00","연속"]
[333,"부산울산","동부산","신양산고리NP#1 T/L","신양산S/S 용량부족 차단기 교체공사(8차)","#1BUS 철거 안전이격","2026-04-13 08:00","2026-04-14 18:00","2026-04-15 08:00","2026-04-16 18:00","연속"]
[334,"부산울산","동부산","신양산북부산#2 T/L","신양산S/S 용량부족 차단기 교체공사(8차)","#1BUS 철거 안전이격","2026-04-22 08:00","2026-04-24 18:00","2026-04-21 08:00","2026-04-23 18:00","연속"]
[335,"부산울산","동부산","신양산S/S #2 M.Tr","신양산S/S #2M.Tr C상 부싱절연유 채유","신양산S/S #2M.Tr C상 부싱절연유 채유","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[336,"부산울산","동부산","신양산북부산#2 T/L"," 신양산-고리NP 등 6개 T/L 송전정비공사","상부재 보강 및 항공구 설치 ( 신양산-북부산 #2T/L 15,16,43~46,48,49,54,55,60,61호)","2026-04-02 07:00","2026-04-10 18:00","2026-04-01 07:00","2026-04-09 18:00","연속"]
[337,"부산울산","북부산","북부산S/S CB 7A77","2026년 북부산전력지사 GIS 정밀점검공사","#4Sh.R 1차 선로측 GIS 7A77 정밀점검","2026-04-22 09:00","2026-04-24 18:00","2026-04-22 09:00","2026-04-24 18:00","연속"]
[338,"부산울산","북부산","북부산고리NP#2 T/L"," 북부산-신울산 등 7개T/L 송전보강공사(고정형 폴리머설치)"," 북부산-고리NP#2T/L 고정형 폴리머애자 설치공사(24기)","2026-04-25 07:00","2026-05-01 18:00","2026-05-10 09:00","2026-05-16 18:00","연속"]
[339,"부산울산","북부산","신김해북부산#1 T/L","26-27 북부산전력 변전협력회사 총액공사","73B/F 보호반 대체, 7300,7371GIS 정밀점검","2026-04-25 09:00","2026-04-30 18:00","2026-05-11 09:00","2026-05-16 18:00","연속"]
[340,"부산울산","북부산","북부산고리NP#1 T/L"," 북부산-신울산 등 7개T/L 송전보강공사(고정형 폴리머설치)"," 북부산-고리NP#1T/L 고정형 폴리머애자 설치공사(26기)","2026-04-18 07:00","2026-04-24 18:00","2026-04-24 07:00","2026-04-30 18:00","연속"]
[341,"부산울산","북부산","북부산신울산#2 T/L","2026년 북부산전력지사 GIS 정밀점검공사","7271, 7200GIS 정밀점검","2026-04-13 09:00","2026-04-17 18:00","2026-04-12 09:00","2026-04-16 18:00","연속"]
[342,"부산울산","북부산","북부산S/S #3 M.Tr","26-27 북부산전력 변전협력회사 총액공사","77B/F PNL 대체, 부싱절연유채유, 부싱절연열화측정, 2차 6333GIS 보통점검, 7771GIS 전자변교체","2026-04-06 09:00","2026-04-10 18:00","2026-04-05 09:00","2026-04-09 18:00","연속"]
[343,"부산울산","북부산","북부산신울산#2 T/L","2026년 가공송전선로 순시점검 위탁공사 송전선로 정비"," 북부산-신울산#2T/L 애자 금구류 정비 -정비대상 : 총 1기(No.97호)","2026-03-31 07:00","2026-03-31 18:00","2026-03-31 07:00","2026-03-31 18:00","연속"]
[344,"부산울산","북부산","서부산북부산#2 T/L","2026년 북부산전력지사 GIS 정밀점검공사","(시험가압선로) #4Sh.R 1차 선로측 GIS 7A77 정밀점검","2026-04-24 17:00","2026-04-24 18:00","2026-04-24 21:00","2026-04-24 22:00","당일"]
[345,"부산울산","서부산","신김해신녹산#2 T/L","2026년 서부산전력지사 가공송전 순시점검 위탁공사","정밀점검, 조류착지방지장치 설치 : 23~52호","2026-04-13 08:00","2026-04-17 18:00","2026-04-13 08:00","2026-04-17 18:00","연속"]
[346,"부산울산","서부산","신김해신녹산#1 T/L","2026년 서부산전력지사 가공송전 순시점검 위탁공사","정밀점검, 조류착지방지장치 설치 : 23~52호","2026-04-06 08:00","2026-04-10 18:00","2026-04-06 08:00","2026-04-10 18:00","연속"]
[347,"부산울산","서부산","신녹산S/S #2 M.Tr","2026년 상반기 M.TR 및 OLTC 정밀점검공사","신녹산S/S #2M.Tr 본체 보통점검/OLTC 정밀점검","2026-04-27 09:00","2026-05-08 18:00","2026-04-27 09:00","2026-05-08 18:00","연속"]
[348,"부산울산","울산","동울산S/S CB 7100","'26~'27년 북울산전력 변전협력회사 공사","7171,7100 GIS 보통점검","2026-04-13 09:00","2026-04-13 13:00","취소","취소","당일"]
[349,"부산울산","울산","신온산S/S #4 M.Tr","26년~27년 울산전력지사 변전협력회사 공사","- 1,2차 부싱절연유 채유 - 피뢰기 보통점검","2026-04-07 09:00","2026-04-07 18:00","2026-04-07 09:00","2026-04-07 18:00","당일"]
[350,"부산울산","울산","신온산S/S #3 M.Tr","26년~27년 울산전력지사 변전협력회사 공사","- 1,2차 부싱절연유 채유","2026-04-06 09:00","2026-04-06 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[351,"부산울산","울산","신울산S/S #3 M.Tr","신울산S/S 변압기 인출변경 전력구공사","신울산S/S 변압기(#3M.Tr) 3회선구간(#3M.Tr~#1M.Tr) 관로 포설 및 되메우기","2026-04-27 09:00","2026-05-15 18:00","2026-04-27 09:00","2026-05-15 18:00","연속"]
[352,"부산울산","울산","신울산S/S #1 M.Tr","신울산S/S 변압기 인출변경 전력구공사","신울산S/S 변압기(#1M.Tr) 3회선구간 관로 1차 터파기 및 가시설","2026-04-06 09:00","2026-04-24 18:00","2026-04-06 09:00","2026-04-24 18:00","연속"]
[353,"부산울산","울산","울산C/C #2 M.Tr","26년~27년 울산전력지사 변전협력회사 공사","- 1,2차 부싱절연유 채유","2026-04-16 09:00","2026-04-16 18:00","2026-04-29 09:00","2026-04-30 18:00","연속"]
[354,"부산울산","울산","울산C/C #1 M.Tr","26년~27년 울산전력지사 변전협력회사 공사","- 1,2차 부싱절연유 채유","2026-04-15 09:00","2026-04-15 18:00","2026-04-27 09:00","2026-04-28 18:00","연속"]
[355,"부산울산","울산","울주S/S #1 BUS"," 울주S/S 장기사용 GIS 교체공사","울주S/S 79Bay GIS 교체작업 무부하 시험가압","2026-04-27 08:00","2026-04-27 18:00","2026-04-27 08:00","2026-04-27 18:00","연속"]
[356,"부산울산","울산","울주울산TP#1 T/L"," 울주S/S 장기사용 GIS 교체공사","울주S/S 79Bay 장기사용 GIS 교체(시험가압)","2026-04-27 08:00","2026-04-28 18:00","2026-04-27 08:00","2026-04-28 18:00","연속"]
[357,"부산울산","울산","울주울산TP#1 T/L"," 울주S/S 장기사용 GIS 교체공사","울주S/S 79Bay 장기사용 GIS 교체(시험가압)","2026-04-13 08:00","2026-04-14 18:00","2026-04-13 08:00","2026-04-14 18:00","연속"]
[358,"부산울산","울산","울주신경산#1 T/L"," 울주S/S 장기사용 GIS 교체공사","울주S/S 79Bay 장기사용 GIS 교체(시험가압)","2026-04-13 08:00","2026-04-14 18:00","2026-04-13 08:00","2026-04-14 18:00","연속"]
[359,"부산울산","울산","울주S/S #2 BUS"," 울주S/S 장기사용 GIS 교체공사","울주S/S 79Bay GIS 교체작업 무부하 시험가압","2026-04-28 08:00","2026-04-28 18:00","2026-04-28 08:00","2026-04-28 18:00","당일"]
[360,"부산울산","울산","울주신경산#1 T/L"," 울주S/S 장기사용 GIS 교체공사","울주S/S 79Bay 장기사용 GIS 교체(시험가압)","2026-04-27 08:00","2026-04-28 18:00","2026-04-27 08:00","2026-04-28 18:00","연속"]
[361,"부산울산","직할","신대연S/S #1 M.Tr","26~27년 직할 변전협력회사 총액공사","신대연S/S #1M.Tr 보통점검, 3차 GIS(4189) 조작시험","2026-04-27 09:30","2026-04-28 18:00","취소","취소","연속"]
[362,"부산울산","직할","신대연S/S #2 M.Tr","26~27년 직할 변전협력회사 총액공사","신대연S/S #2M.Tr, 3차 GIS(4289) 보통점검","2026-04-29 09:30","2026-04-30 18:00","취소","취소","연속"]
[363,"경남","김해송변전부","신마산신김해#1 T/L","2026년도 가공송전 순시점검 위탁회사","신김해-진례 정밀점검(No.1~28) 안전이격","2026-04-25 08:00","2026-04-25 18:00","2026-04-25 08:00","2026-04-25 18:00","연속"]
[364,"경남","김해송변전부","신김해북부산#2 T/L","2026년도 가공송전 순시점검 위탁회사","신김해-진례 정밀점검(No.1~28) 안전이격","2026-04-18 08:00","2026-04-18 18:00","취소","취소","연속"]
[365,"경남","김해송변전부","신마산신김해#1 T/L","2026년도 가공송전 순시점검 위탁회사","신김해-진례 정밀점검(No.1~28) 안전이격","2026-04-18 08:00","2026-04-18 18:00","2026-04-18 08:00","2026-04-18 18:00","연속"]
[366,"경남","김해송변전부","신김해S/S CB 7500","신김해S/S 신김해-북부산 #2 7500 GIS 보통점검","신김해S/S 신김해-북부산 #2 7500 GIS 보통점검","2026-04-12 09:00","2026-04-12 18:00","2026-04-12 09:00","2026-04-12 18:00","연속"]
[367,"경남","김해송변전부","신마산신김해#1 T/L","2026년도 가공송전 순시점검 위탁회사","진례-진영 정밀점검(No.1~7) 안전이격","2026-04-04 08:00","2026-04-04 18:00","2026-04-04 08:00","2026-04-04 18:00","연속"]
[368,"경남","김해송변전부","신김해S/S CB 7871","신김해S/S 신김해-신녹산 #2T/L GIS 보통점검","신김해S/S 신김해-신녹산 #2T/L GIS 보통점검 + 전자변 교체","2026-04-25 09:30","2026-04-25 18:00","2026-04-25 09:30","2026-04-25 18:00","연속"]
[369,"경남","김해송변전부","신김해북부산#2 T/L","2026년도 가공송전 순시점검 위탁회사","신김해-진례 정밀점검(No.1~28) 안전이격","2026-04-25 08:00","2026-04-25 18:00","취소","취소","연속"]
[370,"경남","김해송변전부","신마산신김해#2 T/L","2026년도 가공송전 순시점검 위탁회사","진례-진영 정밀점검(No.1~7) 안전이격","2026-04-05 08:00","2026-04-05 18:00","2026-04-05 08:00","2026-04-05 18:00","연속"]
[371,"경남","직할","창원S/S CB 7272","창원S/S #2M.Tr 1차 7272 GIS 정밀점검","창원S/S #2M.Tr 1차 7272 GIS 정밀점검","2026-04-06 09:00","2026-04-10 18:00","2026-04-06 09:00","2026-04-10 18:00","연속"]
[372,"경남","직할","창원신고성#2 T/L"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사","2026-04-22 07:00","2026-04-30 18:00","취소","취소","연속"]
[373,"경남","직할","창원신고성#1 T/L","창원S/S #3M.Tr 1차 7372 GIS 정밀점검 시험가압","창원S/S #3M.Tr 1차 7372 GIS 정밀점검 시험가압","2026-04-17 16:00","2026-04-17 18:00","2026-04-17 16:00","2026-04-17 18:00","연속"]
[374,"경남","직할","창원S/S #3 M.Tr","창원S/S #3M.Tr 병행작업 및 시험가압","창원S/S #3M.Tr 병행작업 및 시험가압","2026-04-16 09:00","2026-04-17 18:00","2026-04-16 09:00","2026-04-17 18:00","연속"]
[375,"경남","직할","창원S/S CB 7372","창원S/S #3M.Tr 1차 7372 GIS 정밀점검","창원S/S #3M.Tr 1차 7372 GIS 정밀점검","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[376,"경남","직할","창원신고성#1 T/L"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사"," 창원-신고성T/L 155~158호 등 3개구간 전력선 교체공사","2026-04-13 07:00","2026-04-21 18:00","2026-04-13 07:00","2026-04-21 18:00","연속"]
[377,"경남","직할","창원S/S #2 M.Tr","창원S/S #2M.Tr 병행작업 및 시험가압","창원S/S #2M.Tr 병행작업 및 시험가압 (병행)2,3차 GIS 보통점검","2026-04-09 09:00","2026-04-10 18:00","2026-04-09 09:00","2026-04-10 18:00","연속"]
[378,"경남","진주","신남원의령#2 T/L","2026년도 가공송전 순시점검 위탁공사","송전선로 정밀점검","2026-04-20 08:00","2026-04-30 18:00","취소","취소","매일"]
[379,"경남","진주","의령S/S CB 7900","의령S/S 의령-신마산#1T/L 휴전작업","의령S/S 의령-신마산#1T/L 휴전작업_CB단독 - 7952 DS 가스압력 이상 관련 현상확인","2026-04-06 09:00","2026-04-06 18:00","취소","취소","연속"]
[380,"경남","진주","신남원의령#1 T/L","2026년도 가공송전 순시점검 위탁공사","송전선로 정밀점검","2026-04-07 08:00","2026-04-17 18:00","취소","취소","매일"]
[381,"경남","진주","고령의령#1 T/L","2026년도 가공송전 순시점검 위탁공사","송전선로 정밀점검 안전이격거리 확보","2026-04-07 08:00","2026-04-07 18:00","2026-04-07 08:00","2026-04-07 18:00","매일"]
[382,"경남","진주","고령의령#2 T/L","2026년도 가공송전 순시점검 위탁공사","송전선로 정밀점검 안전이격거리 확보","2026-04-20 08:00","2026-04-20 18:00","2026-04-20 08:00","2026-04-20 18:00","매일"]
[383,"경남","진주","하동T/P CB 7672","하동T/P 7672 GIS 조작시험","하동T/P 7672 GIS 조작시험","2026-04-09 14:00","2026-04-09 17:00","2026-04-09 14:00","2026-04-09 17:00","연속"]
[384,"경남","진주","하동T/P CB 7400","하동T/P 7400 GIS 보통점검","하동T/P 7400 GIS 보통점검","2026-04-01 10:00","2026-04-01 17:00","2026-04-01 10:00","2026-04-01 17:00","연속"]
[385,"경남","진주","하동T/P CB 7600","하동T/P 7600 GIS 조작시험","하동T/P 7600 GIS 조작시험","2026-04-09 10:00","2026-04-09 14:00","2026-04-09 10:00","2026-04-09 14:00","연속"]
[386,"경남","진주","하동T/P CB 7172","하동T/P 7172 GIS 보통점검","하동T/P 7172 GIS 보통점검","2026-04-08 10:00","2026-04-08 17:00","취소","취소","연속"]
[387,"경남","진주","하동T/P CB 7472","하동T/P 7472 GIS 보통점검","하동T/P 7472 GIS 보통점검","2026-04-02 10:00","2026-04-02 17:00","2026-04-02 10:00","2026-04-02 17:00","연속"]
[388,"경남","통영","신고성S/S SEC CB 70710","신고성S/S #70-#71 SEC GIS 보통점검","신고성S/S #70-#71 SEC GIS 보통점검","2026-04-06 09:00","2026-04-06 18:00","2026-04-06 09:00","2026-04-06 18:00","연속"]
[389,"경남","통영","창원신고성#1 T/L"," 창원신고성#1 T/L 추락방지장치 설치공사"," 창원신고성#1 T/L 추락방지장치 설치공사","2026-04-13 07:00","2026-04-14 18:00","2026-04-13 07:00","2026-04-14 18:00","매일"]
[390,"경남","통영","신고성S/S SEC CB 75760","신고성S/S #75-#76 SEC GIS 보통점검","신고성S/S #75-#76 SEC GIS 보통점검","2026-04-07 09:00","2026-04-07 18:00","2026-04-07 09:00","2026-04-07 18:00","연속"]
[391,"경남","통영","창원신고성#2 T/L"," 창원신고성#2 T/L 추락방지장치 설치공사"," 창원신고성#2 T/L 추락방지장치 설치공사","2026-04-08 07:00","2026-04-10 18:00","2026-04-08 07:00","2026-04-10 18:00","매일"]
[392,"경남","통영","신고성S/S #4 M.Tr","신고성S/S #4 M.Tr 1차 7672 GIS 보통점검 등","신고성S/S #4 M.Tr 1차 7672, 7600 GIS 보통점검 신고성S/S #4 M.Tr 2차 GIS 보통점검","2026-04-27 09:00","2026-04-30 18:00","2026-04-27 09:00","2026-04-30 18:00","연속"]
[393,"경남","통영","신고성S/S CB 7200","신고성S/S 신마산#2T/L-#G2 TIE GIS 보통점검","신고성S/S 신마산#2T/L-#G2 TIE GIS 보통점검","2026-04-16 09:00","2026-04-16 18:00","2026-04-16 09:00","2026-04-16 18:00","연속"]
[394,"경남","통영","신고성고성하이TP#1 T/L"," 신고성고성하이발전#1 T/L 추락방지장치 설치공사"," 신고성고성하이발전#1 T/L 추락방지장치 설치공사","2026-04-15 07:00","2026-04-15 18:00","2026-04-15 07:00","2026-04-15 18:00","매일"]
[395,"경남","통영","신고성S/S CB 7271","신고성S/S #G2호기 1차 GIS(7271) 보통점검","신고성S/S #G2호기 1차 GIS(7271) 보통점검","2026-04-14 09:00","2026-04-14 18:00","2026-04-14 09:00","2026-04-14 18:00","연속"]
[396,"경남","함안","북경남무주양수 T/L","26~27년 달성전력지사 가공송전 협력회사공사","4.10(금) : 북경남-무주양수T/L 17호 스페이서 교체 및 스플라이스 시공","2026-04-10 07:00","2026-04-10 18:00","취소","취소","연속"]
[397,"경남","함안","의령신마산#1 T/L"," 의령-신마산T/L 정밀점검"," 의령-신마산T/L 정밀점검 1~115호","2026-04-02 08:00","2026-04-10 18:00","2026-04-02 08:00","2026-04-10 18:00","매일"]
[398,"경남","함안","의령신마산#2 T/L"," 의령-신마산T/L 정밀점검"," 의령-신마산T/L 정밀점검 1~115호","2026-04-13 08:00","2026-04-21 18:00","2026-04-13 08:00","2026-04-21 18:00","매일"]
[399,"경남","함안","신마산S/S #1 M.Tr","신마산S/S #1M.Tr 보통점검 등","신마산S/S #1M.Tr 보통점검 등","2026-04-06 09:30","2026-04-08 17:30","2026-04-06 09:30","2026-04-08 17:30","연속"]

{"sheet":"154설비","index":2,"n_rows":881,"n_cols":11,"rows_kept":881,"cut":false,"hidden":false,"merged":[[2,0,3,0],[2,1,3,1],[2,3,3,3],[2,10,3,10],[2,4,3,4],[2,5,3,5],[2,6,2,7],[2,8,2,9],[2,2,3,2]]}
["2026년도 4월 휴전계획서"]
["154kV"]
["번호","1차사업소","사업소","설비명","공사명","공사개요","신청일시",null,"조정일시",null,"작업구분"]
[{"$nulls":6},"시작","종료","시작","종료"]
[1,"서울","성동","성수뚝도#1 T/L","43PDA 교체","- 43PDA 교체","2026-04-03 09:00","2026-04-03 14:00","취소","취소","당일"]
[2,"서울","성동","광장뚝도#1 T/L","43PDA 교체","- 43PDA 교체","2026-04-03 14:00","2026-04-03 18:00","취소","취소","당일"]
[3,"서울","성동","금오상계#1 T/L","170kV GIS 조작시험","- GIS 조작시험 - 전자변 교체","2026-04-06 09:00","2026-04-06 18:00","2026-04-06 09:00","2026-04-06 18:00","당일"]
[4,"서울","성동","금오상계#2 T/L","170kV GIS 조작시험","- GIS 조작시험","2026-04-07 09:00","2026-04-07 18:00","2026-04-07 09:00","2026-04-07 18:00","당일"]
[5,"서울","성동","성동휘경#1 T/L","170kV GIS 조작시험","- GIS 조작시험 - 전자변 교체","2026-04-15 09:00","2026-04-15 18:00","2026-04-15 09:00","2026-04-15 18:00","당일"]
[6,"서울","성동","성동휘경#2 T/L","170kV GIS 조작시험","- GIS 조작시험","2026-04-16 09:00","2026-04-16 18:00","2026-04-16 09:00","2026-04-16 18:00","당일"]
[7,"서울","성동","왕십리용두 T/L","2026년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검 * 24Bay","2026-04-21 14:00","2026-04-21 18:00","2026-04-21 14:00","2026-04-21 18:00","연속"]
[8,"서울","성동","왕십리용두 T/L","2026년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검 * 24Bay","2026-04-08 09:00","2026-04-10 18:00","2026-04-08 09:00","2026-04-10 18:00","연속"]
[9,"서울","성동","왕십리용두 T/L","2026년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검 * 24Bay","2026-04-22 14:00","2026-04-22 18:00","2026-04-22 14:00","2026-04-22 18:00","연속"]
[10,"서울","성동","휘경종암#2 T/L","2026년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검 * 24Bay","2026-04-29 09:00","2026-04-30 18:00","취소","취소","연속"]
[11,"서울","성동","휘경종암#1 T/L","2026년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검 * 24Bay","2026-04-27 09:00","2026-04-28 18:00","취소","취소","연속"]
[12,"서울","성동","휘경종암#1 T/L","2026년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검 * 24Bay","2026-04-30 14:00","2026-04-30 18:00","취소","취소","연속"]
[13,"서울","성동","창동쌍문#2 T/L","창동S/S 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154kV 장기사용 GIS 교체공사 ○ 154kV 창동쌍문#2T/L GIS 교체(1Bay) ○ 제어케이블 포설 등 기타공사(1식)","2026-04-13 08:00","2026-04-30 18:00","취소","취소","연속"]
[14,"서울","성동","창동S/S #2 BUS","창동S/S 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154kV 장기사용 GIS 교체공사 ○ 3차분 : 154kV 창동쌍문#2T/L GIS 교체(1Bay) ○ 제어케이블 포설 등 기타공사(1식)","2026-04-13 08:00","2026-04-15 09:00","취소","취소","연속"]
[15,"서울","성동","창동S/S #1 BUS","창동S/S 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154kV 장기사용 GIS 교체공사 ○ 3차분 : 154kV 창동쌍문#2T/L GIS 교체(1Bay) ○ 제어케이블 포설 등 기타공사(1식)","2026-04-15 09:00","2026-04-22 09:00","취소","취소","연속"]
[16,"서울","성동","상계창동#2 T/L","창동S/S 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154kV 장기사용 GIS 교체공사 ○ 2차분 : 154kV 창동쌍문#2T/L GIS 교체(1Bay) ○ 제어케이블 포설 등 기타공사(1식) ○ 시험가압선로 : 상계창동#2T/L","2026-04-21 16:00","2026-04-22 09:00","취소","취소","연속"]
[17,"서울","성동","창동S/S #2 BUS","창동S/S 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154kV 장기사용 GIS 교체공사 ○ 3차분 : 154kV 창동쌍문#2T/L GIS 교체(1Bay) ○ 제어케이블 포설 등 기타공사(1식)","2026-04-22 09:00","2026-04-30 09:00","취소","취소","연속"]
[18,"서울","성동","창동S/S #1 BUS","창동S/S 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154kV 장기사용 GIS 교체공사 ○ 3차분 : 154kV 창동쌍문#2T/L GIS 교체(1Bay) ○ 제어케이블 포설 등 기타공사(1식)","2026-04-30 09:00","2026-04-30 18:00","취소","취소","연속"]
[19,"서울","성동","상계창동#2 T/L","창동S/S 170kV 장기사용 GIS 대체공사","■ 공사명 : 창동S/S 154kV 장기사용 GIS 교체공사 ○ 2차분 : 154kV 창동쌍문#2T/L GIS 교체(1Bay) ○ 제어케이블 포설 등 기타공사(1식) ○ 시험가압선로 : 상계창동#2T/L","2026-04-14 16:00","2026-04-15 09:00","취소","취소","연속"]
[20,"서울","성동","휘경종암#2 T/L","2026년 성동P/O 170kV GIS 정밀점검 공사","170kV GIS 정밀점검 * 24Bay","2026-04-28 14:00","2026-04-28 18:00","취소","취소","연속"]
[21,"서울","중부","중부당인리#1 T/L","2026～2027년 중부전력지사 변전협력회사 공사","GIS 초기점검","2026-04-08 10:00","2026-04-08 18:00","2026-04-08 10:00","2026-04-08 18:00","당일"]
[22,"서울","중부","중부당인리#2 T/L","2026～2027년 중부전력지사 변전협력회사 공사","GIS 초기점검","2026-04-09 10:00","2026-04-09 18:00","2026-04-09 10:00","2026-04-09 18:00","당일"]
[23,"서울","중부","중부용산#1 T/L","2026～2027년 중부전력지사 변전협력회사 공사","GIS 초기점검","2026-04-07 10:00","2026-04-07 18:00","2026-04-07 10:00","2026-04-07 18:00","당일"]
[24,"서울","직할","현저서대문#1 T/L","2026년 서울본부 직할 154kV GIS 정밀점검 공사","#3M.Tr 1차 GIS(CB+DS)","2026-04-02 09:00","2026-04-03 18:00","취소","취소","연속"]
[25,"서울","직할","현저서대문#2 T/L","2026년 서울본부 직할 154kV GIS 정밀점검 공사","현저-서대문#2T/L 정밀점검(CB+DS)","2026-04-08 09:00","2026-04-10 18:00","취소","취소","연속"]
[26,"서울","직할","현저서대문#1 T/L","2026년 서울본부 직할 154kV GIS 정밀점검 공사","현저-서대문#1T/L 정밀점검(CB+DS)","2026-04-06 09:00","2026-04-08 18:00","취소","취소","연속"]
[27,"서울","직할","옥인운니#1 T/L","(직할총액) 운니S/S 옥인운니#1TL GIS 조작시험","운니S/S 옥인운니#1TL GIS 조작시험 및 전자변교체","2026-04-27 09:00","2026-04-27 18:00","2026-04-27 09:00","2026-04-27 18:00","당일"]
[28,"서울","직할","옥인운니#2 T/L","(직할총액) 운니S/S 옥인운니#2TL GIS 조작시험","운니S/S 옥인운니#2TL GIS 조작시험 및 전자변교체","2026-04-28 09:00","2026-04-28 18:00","2026-04-28 09:00","2026-04-28 18:00","당일"]
[29,"서울","직할","종로서소문 T/L","2026년 서울본부 직할 154kV GIS 정밀점검 공사","종로-서소문T/L(CB+DS)","2026-04-29 09:00","2026-05-01 18:00","2026-04-29 09:00","2026-05-01 18:00","연속"]
[30,"서울","직할","중앙S/S #1 BUS","중앙S/S 154kV 장기사용 GIS 교체공사","○ 중앙S/S 154kV 장기사용 GIS 교체공사 - 대상 : 방산중앙#2T/L(3/3~4/10)","2026-04-06 09:00","2026-04-08 11:00","2026-04-06 09:00","2026-04-08 11:00","연속"]
[31,"서울","직할","중앙S/S #2 BUS","중앙S/S 154kV 장기사용 GIS 교체공사","○ 중앙S/S 154kV 장기사용 GIS 교체공사 - 대상 : 방산중앙#2T/L(3/3~4/10)","2026-04-08 11:00","2026-04-10 18:00","2026-04-08 11:00","2026-04-10 18:00","연속"]
[32,"서울","중부","중부연대 T/L","2026~2027년 중부전력지사 변전협력회사 공사","GIS 점검","2026-04-01 10:00","2026-04-01 18:00","취소","취소","당일"]
[33,"서울","중부","중부용산#2 T/L","2026년 중부전력지사 170kV GIS 정밀점검공사","무부하가압 시험가압 선로","2026-04-02 10:00","2026-04-02 11:00","2026-04-02 10:00","2026-04-02 11:00","당일"]
[34,"서울","중부","은평녹번#2 T/L","2026~2027년 중부전력지사 변전협력회사 공사","GIS 점검","2026-04-03 10:00","2026-04-03 18:00","2026-04-03 10:00","2026-04-03 18:00","당일"]
[35,"서울","중부","중부용산#2 T/L","2026년 중부전력지사 170kV GIS 정밀점검공사","무부하가압 시험가압 선로","2026-04-03 14:00","2026-04-03 18:00","2026-04-03 14:00","2026-04-03 18:00","당일"]
[36,"서울","중부","상암등촌#1 T/L","2026년 중부전력지사 170kV GIS 정밀점검공사","무부하가압 시험가압 선로","2026-04-07 10:00","2026-04-07 11:00","2026-04-07 10:00","2026-04-07 11:00","당일"]
[37,"서울","중부","상암등촌#1 T/L","2026년 중부전력지사 170kV GIS 정밀점검공사","무부하가압 시험가압 선로","2026-04-09 14:00","2026-04-09 18:00","2026-04-09 14:00","2026-04-09 18:00","당일"]
[38,"서울","중부","녹번세종로 T/L","2026~2027년 중부전력지사 변전협력회사 공사","GIS 점검","2026-04-10 10:00","2026-04-10 18:00","2026-04-10 10:00","2026-04-10 18:00","당일"]
[39,"서울","중부","중부S/S #61 BUS","중부S/S 154kV 장기사용 GIS 교체공사(5차)","154kV #61M.Tr GIS 설치 및 기타 부대공사","2026-04-13 09:00","2026-04-23 14:00","2026-04-13 09:00","2026-04-23 14:00","연속"]
[40,"서울","중부","수색상암#2 T/L","2026~2027년 중부전력지사 변전협력회사 공사","GIS 점검","2026-04-14 10:00","2026-04-14 18:00","2026-04-14 10:00","2026-04-14 18:00","당일"]
[41,"서울","중부","양주은평#1 T/L","2026~2027년 중부전력지사 변전협력회사 공사","GIS 점검","2026-04-17 10:00","2026-04-17 18:00","2026-04-17 10:00","2026-04-17 18:00","당일"]
[42,"서울","중부","중부S/S #66 BUS","중부S/S 154kV 장기사용 GIS 교체공사(5차)","154kV #61M.Tr GIS 설치 및 기타 부대공사","2026-04-23 14:00","2026-05-07 10:00","2026-04-23 14:00","2026-05-07 10:00","연속"]
[43,"서울","중부","양주은평#2 T/L","2026~2027년 중부전력지사 변전협력회사 공사","GIS 점검","2026-04-24 10:00","2026-04-24 18:00","2026-04-24 10:00","2026-04-24 18:00","당일"]
[44,"남서울","강남","과천동안양#1 T/L","과천S/S 154kV #1,2Sh.R 및 #4M.Tr 증설공사","1701kV GIS 증설분 무부하 가압(#1BUS)","2026-04-02 09:00","2026-04-10 18:00","2026-04-02 09:00","2026-04-10 18:00","연속"]
[45,"남서울","강남","동빙고반포#2 T/L","154kV GIS 정밀점검","154kV GIS 정밀점검","2026-04-08 09:00","2026-04-10 18:00","2026-04-08 09:00","2026-04-10 18:00","연속"]
[46,"남서울","강남","동빙고반포#1 T/L","154kV GIS 정밀점검","154kV GIS 정밀점검","2026-04-05 09:00","2026-04-07 18:00","2026-04-05 09:00","2026-04-07 18:00","연속"]
[47,"남서울","강남","신사반포#2 T/L","26-27년도 강남전력지사 변전협력회사 총액공사","170kV GIS 조작시험 및 전자변교체 신사(이정배), 반포(양성철)","2026-04-12 09:00","2026-04-12 18:00","2026-04-12 09:00","2026-04-12 18:00","당일"]
[48,"남서울","강남","반포S/S CB 6100","26-27년도 강남전력지사 변전협력회사 총액공사","154kV GIS 조작시험","2026-04-27 09:00","2026-04-27 18:00","2026-04-27 09:00","2026-04-27 18:00","당일"]
[49,"남서울","강남","동빙고반포#1 T/L","154kV GIS 정밀점검","154kV GIS 정밀점검 무부하가압","2026-04-09 09:00","2026-04-09 16:00","2026-04-09 09:00","2026-04-09 16:00","당일"]
[50,"남서울","강남","반포S/S #1 BUS","154kV GIS 정밀점검","154kV GIS 정밀점검 #1DS점검","2026-04-08 09:00","2026-04-09 16:00","2026-04-08 09:00","2026-04-09 16:00","연속"]
[51,"남서울","강남","반포S/S #2 BUS","154kV GIS 정밀점검","154kV GIS 정밀점검 #2DS점검","2026-04-06 16:00","2026-04-07 18:00","2026-04-06 16:00","2026-04-07 18:00","연속"]
[52,"남서울","강남","동빙고반포#2 T/L","154kV GIS 정밀점검","154kV GIS 정밀점검 무부하가압","2026-04-06 09:00","2026-04-06 16:00","2026-04-06 09:00","2026-04-06 16:00","당일"]
[53,"남서울","강남","반포S/S #1 BUS","154kV GIS 정밀점검","154kV GIS 정밀점검 #1DS 점검","2026-04-05 09:00","2026-04-06 16:00","2026-04-05 09:00","2026-04-06 16:00","연속"]
[54,"남서울","강남","신사반포#1 T/L","26-27년도 강남전력지사 변전협력회사 총액공사","반포S/S 154kV GIS 조작시험(김재연) 신사S/S 154kV GIS 조작시험(이정배)","2026-04-11 09:00","2026-04-11 18:00","2026-04-11 09:00","2026-04-11 18:00","당일"]
[55,"남서울","강남","반포S/S #2 BUS","154kV GIS 정밀점검","154kV GIS 정밀점검 #2DS점검","2026-04-09 16:00","2026-04-10 18:00","2026-04-09 16:00","2026-04-10 18:00","연속"]
[56,"남서울","강남","신사S/S #2 BUS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사 #2DS 점검","2026-04-28 16:00","2026-04-29 16:00","2026-04-28 16:00","2026-04-29 16:00","연속"]
[57,"남서울","강남","신사S/S #1 BUS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사 #1DS 점검","2026-04-22 09:00","2026-04-23 16:00","2026-04-22 09:00","2026-04-23 16:00","연속"]
[58,"남서울","강남","신사S/S #2 BUS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사 #2DS점검","2026-04-23 16:00","2026-04-24 18:00","2026-04-23 16:00","2026-04-24 18:00","연속"]
[59,"남서울","강남","신사S/S #1 BUS","154kV GIS 정밀점검공사","154kV GIS 정밀점검공사 #1DS 점검","2026-04-27 09:00","2026-04-28 16:00","2026-04-27 09:00","2026-04-28 16:00","연속"]
[60,"남서울","강남","신양재역삼#2 T/L","154kV GIS 정밀점검","154kV GIS 정밀점검 역삼S/S GIS 보통점검(정규성)","2026-04-25 09:00","2026-04-26 18:00","2026-04-25 09:00","2026-04-26 18:00","연속"]
[61,"남서울","강남","신양재역삼#1 T/L","154kV GIS 정밀점검","154kV GIS 정밀점검 역삼S/S GIS 보통점검(정규성)","2026-04-18 09:00","2026-04-19 18:00","2026-04-18 09:00","2026-04-19 18:00","연속"]
[62,"남서울","강남","신양재역삼#3 T/L","26-27년도 강남전력지사 변전협력회사 총액공사","154kV GIS 조작시험","2026-04-04 09:00","2026-04-04 14:00","2026-04-04 09:00","2026-04-04 14:00","당일"]
[63,"남서울","강남","신양재S/S #66 BUS","154kV GIS 정밀점검","154kV GIS 정밀점검 #2DS점검","2026-04-17 16:00","2026-04-18 18:00","2026-04-17 16:00","2026-04-18 18:00","연속"]
[64,"남서울","강남","신양재과천#2 T/L","26-27년도 강남전력지사 변전협력회사 총액공사","154kV GIS 조작시험","2026-04-02 14:00","2026-04-02 18:00","2026-04-02 14:00","2026-04-02 18:00","당일"]
[65,"남서울","강남","신양재S/S #61 BUS","154kV GIS 정밀점검","154kV GIS 정밀점검 #1DS 점검","2026-04-16 09:00","2026-04-17 16:00","2026-04-16 09:00","2026-04-17 16:00","연속"]
[66,"남서울","강남","신양재S/S #61 BUS","154kV GIS 정밀점검","154kV GIS 정밀점검 #1DS 점검","2026-04-13 09:00","2026-04-14 16:00","2026-04-13 09:00","2026-04-14 16:00","연속"]
[67,"남서울","강남","신양재사당#1 T/L","154kV GIS 정밀점검","154kV GIS 정밀점검 무부하가압 신양재측 조작시험(이정배), 사당측 보통점검(이종호))","2026-04-14 09:00","2026-04-14 16:00","2026-04-14 09:00","2026-04-14 16:00","당일"]
[68,"남서울","강남","신양재S/S #66 BUS","154kV GIS 정밀점검","154kV GIS 정밀점검 #2DS점검","2026-04-14 16:00","2026-04-15 18:00","2026-04-14 16:00","2026-04-15 18:00","연속"]
[69,"남서울","강남","신양재사당#1 T/L","154kV GIS 정밀점검","154kV GIS 정밀점검 무부하가압용","2026-04-17 09:00","2026-04-17 16:00","2026-04-17 09:00","2026-04-17 16:00","당일"]
[70,"남서울","동서울","동서울#2S/S #69 BUS","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-08 09:00","2026-04-10 18:00","2026-04-08 09:00","2026-04-10 18:00","연속"]
[71,"남서울","동서울","동서울#2S/S #64 BUS","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-06 09:00","2026-04-08 18:00","2026-04-06 09:00","2026-04-08 18:00","연속"]
[72,"남서울","동서울","동서울S/S CB 6500","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-06 09:00","2026-04-08 18:00","2026-04-06 09:00","2026-04-08 18:00","연속"]
[73,"남서울","동서울","동서울#2S/S #68 BUS","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-01 09:00","2026-04-03 18:00","2026-04-01 09:00","2026-04-03 18:00","연속"]
[74,"남서울","동서울","동서울S/S SEC CB 68690","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-01 09:00","2026-04-03 18:00","2026-04-01 09:00","2026-04-03 18:00","연속"]
[75,"남서울","동서울","동서울S/S SEC CB 65660","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-13 09:00","2026-04-15 18:00","2026-04-13 09:00","2026-04-15 18:00","연속"]
[76,"남서울","동서울","동서울S/S SEC CB 66670","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-15 09:00","2026-04-17 18:00","2026-04-15 09:00","2026-04-17 18:00","연속"]
[77,"남서울","동서울","동서울S/S #67 BUS(신)","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-20 09:00","2026-04-22 18:00","2026-04-20 09:00","2026-04-22 18:00","연속"]
[78,"남서울","동서울","동서울S/S #65 BUS(신)","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-13 09:00","2026-04-15 18:00","2026-04-13 09:00","2026-04-15 18:00","연속"]
[79,"남서울","동서울","동서울S/S SEC CB 67680","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-20 09:00","2026-04-22 18:00","2026-04-20 09:00","2026-04-22 18:00","연속"]
[80,"남서울","동서울","동서울S/S #66 BUS(신)","동서울S/S 종합정비공사(2차)","-154kV 제어케이블 이설","2026-04-15 09:00","2026-04-17 18:00","2026-04-15 09:00","2026-04-17 18:00","연속"]
[81,"남서울","동서울","가락수서#1 T/L","26~27년 동서울전력지사 변전협력회사공사","170kV GIS 보통점검(수서)","2026-04-23 09:00","2026-04-23 18:00","2026-04-23 09:00","2026-04-23 18:00","당일"]
[82,"남서울","동서울","가락수서#2 T/L","26~27년 동서울전력지사 변전협력회사공사","170kV GIS 보통점검(수서)","2026-04-24 09:00","2026-04-24 18:00","2026-04-24 09:00","2026-04-24 18:00","당일"]
[83,"남서울","동서울","송파잠실#1 T/L","26-27년도 동서울전력지사 변전협력회사 총액공사","170kV GIS 보통점검(잠실)","2026-04-09 09:00","2026-04-09 18:00","2026-04-09 09:00","2026-04-09 18:00","당일"]
[84,"남서울","동서울","송파잠실#4 T/L","26-27년도 동서울전력지사 변전협력회사 총액공사","170kV GIS 보통점검(잠실)","2026-04-08 09:00","2026-04-08 18:00","2026-04-08 09:00","2026-04-08 18:00","당일"]
[85,"남서울","동서울","잠실탄천#1 T/L","26-27년도 동서울전력지사 변전협력회사 총액공사","170kV GIS 보통점검(잠실)","2026-04-18 09:00","2026-04-18 18:00","2026-04-18 09:00","2026-04-18 18:00","당일"]
[86,"남서울","동서울","잠실탄천#2 T/L","26-27년도 동서울전력지사 변전협력회사 총액공사","170kV GIS 보통점검(잠실)","2026-04-19 09:00","2026-04-19 18:00","2026-04-19 09:00","2026-04-19 18:00","당일"]
[87,"남서울","영등포","마곡가양#2 T/L","’25~’26년 남서울본부 영등포전력지사 지중송전 협력회사 공사","154kV 마곡-가양#2T/L 가양EBG 가스채취밸브 설치","2026-04-08 09:00","2026-04-09 18:00","2026-04-08 09:00","2026-04-09 18:00","연속"]
[88,"남서울","영등포","마곡가양#1 T/L","’25~’26년 남서울본부 영등포전력지사 지중송전 협력회사 공사","154kV 마곡-가양#1T/L 가양EBG 가스채취밸브 설치","2026-04-06 09:00","2026-04-07 18:00","2026-04-06 09:00","2026-04-07 18:00","연속"]
[89,"남서울","영등포","독산대방#1 T/L","'26년 영등포전력지사 170kV GIS 정밀점검 공사","'26년 영등포전력지사 170kV GIS 정밀점검 공사 - 대상 : 독산-대방#1T/L GIS","2026-04-01 09:00","2026-04-03 18:00","취소","취소","연속"]
[90,"남서울","영등포","독산대방#2 T/L","'26년 영등포전력지사 170kV GIS 정밀점검 공사","'26년 영등포전력지사 170kV GIS 정밀점검 공사 - 대상 : 독산-대방#2T/L GIS","2026-04-06 09:00","2026-04-08 18:00","취소","취소","연속"]
[91,"남서울","영등포","구공독산 T/L","154kV GIS 조작시험","독산S/S 구공-독산T/L 조작시험","2026-04-14 09:00","2026-04-14 18:00","2026-04-14 09:00","2026-04-14 18:00","연속"]
[92,"남서울","영등포","화곡마곡#1 T/L","'26년 영등포전력지사 170kV GIS 정밀점검 공사","'26년 영등포전력지사 170kV GIS 정밀점검 공사 - 대상 : 화곡-마곡#1T/L GIS","2026-04-11 09:00","2026-04-12 18:00","2026-04-11 09:00","2026-04-12 18:00","연속"]
[93,"남서울","영등포","화곡마곡#2 T/L","'26년 영등포전력지사 170kV GIS 정밀점검 공사","'26년 영등포전력지사 170kV GIS 정밀점검 공사 - 대상 : 화곡-마곡#2T/L GIS","2026-04-18 09:00","2026-04-19 18:00","2026-04-18 09:00","2026-04-19 18:00","연속"]
[94,"남서울","영등포","신문래목동#1 T/L","154kV GIS 조작시험","목동S/S 신문래-목동#1,2T/L 조작시험","2026-04-16 09:00","2026-04-16 14:00","2026-04-16 09:00","2026-04-16 14:00","연속"]
[95,"남서울","영등포","신문래목동#2 T/L","154kV GIS 조작시험","목동S/S 신문래-목동#1,2T/L 조작시험","2026-04-16 14:00","2026-04-16 18:00","2026-04-16 14:00","2026-04-16 18:00","연속"]
[96,"남서울","영등포","시흥독산#1 T/L","'26년 영등포전력지사 170kV GIS 정밀점검 공사","'26년 영등포전력지사 170kV GIS 정밀점검 공사 - 대상 : 시흥-독산#1T/L GIS","2026-04-27 09:00","2026-04-29 18:00","2026-04-27 09:00","2026-04-29 18:00","연속"]
[97,"남서울","영등포","시흥S/S #60 BUS","'26년 영등포전력지사 170kV GIS 정밀점검 공사","'26년 영등포전력지사 170kV GIS 정밀점검 공사 - 내용 : 시흥S/S #1M.Tr 1차 GIS 정밀점검 관련 무부하가압용(#60BUS, 시흥-독산#2T/L)","2026-04-24 16:00","2026-04-24 18:00","2026-04-24 16:00","2026-04-24 18:00","연속"]
[98,"남서울","영등포","시흥독산#2 T/L","'26년 영등포전력지사 170kV GIS 정밀점검 공사","'26년 영등포전력지사 170kV GIS 정밀점검 공사 - 내용 : 시흥S/S #1M.Tr 1차 GIS 정밀점검 관련 무부하가압용(#60BUS, 시흥-독산#2T/L)","2026-04-24 16:00","2026-04-24 18:00","2026-04-24 16:00","2026-04-24 18:00","연속"]
[99,"남서울","영등포","온수소래 T/L","’25~’26년 남서울본부 영등포전력지사 지중송전 협력회사 공사","154kV 온수-소래T/L 온수EBG 가스채취밸브 설치","2026-04-15 09:00","2026-04-16 18:00","취소","취소","연속"]
[100,"남서울","영등포","고강화곡#2 T/L","’25~’26년 남서울본부 영등포전력지사 지중송전 협력회사 공사","154kV 고강-화곡#2T/L 고강EBG 가스채취밸브 설치","2026-04-29 09:00","2026-04-30 18:00","2026-04-29 09:00","2026-04-30 18:00","연속"]
[101,"남서울","영등포","고강화곡#1 T/L","’25~’26년 남서울본부 영등포전력지사 지중송전 협력회사 공사","154kV 고강-화곡#1T/L 고강EBG 가스채취밸브 설치","2026-04-27 09:00","2026-04-28 18:00","2026-04-27 09:00","2026-04-28 18:00","연속"]
[102,"남서울","영등포","고강화곡#3 T/L","'26년 영등포전력지사 170kV GIS 정밀점검 공사","'26년 영등포전력지사 170kV GIS 정밀점검 공사 - 대상 : 고강-화곡#3T/L GIS","2026-04-14 09:00","2026-04-16 18:00","2026-04-14 09:00","2026-04-16 18:00","연속"]
[103,"남서울","직할","신문래S/S #60 BUS","현대제 170kV GIS 단로기 링크교체","현대제 170kV GIS 단로기 링크교체","2026-04-01 09:00","2026-04-15 18:00","취소","취소","연속"]
[104,"남서울","직할","신문래구로#2 T/L","현대제 170kV GIS 단로기 링크교체(무부하가압용)","현대제 170kV GIS 단로기 링크교체(무부하가압용)","2026-04-28 09:00","2026-04-28 18:00","취소","취소","연속"]
[105,"남서울","직할","신문래양평#1 T/L","현대제 170kV GIS 단로기 링크교체","현대제 170kV GIS 단로기 링크교체","2026-04-23 09:00","2026-04-25 18:00","취소","취소","연속"]
[106,"남서울","직할","신문래S/S #65 BUS","현대제 170kV GIS 단로기 링크교체(모선용)","현대제 170kV GIS 단로기 링크교체(모선용)","2026-04-20 09:00","2026-04-28 18:00","취소","취소","연속"]
[107,"남서울","직할","신문래목동#1 T/L","현대제 170kV GIS 단로기 링크교체","현대제 170kV GIS 단로기 링크교체","2026-04-20 09:00","2026-04-22 18:00","취소","취소","연속"]
[108,"남서울","직할","신문래구로#2 T/L","현대제 170kV GIS 단로기 링크교체(무부하가압용)","현대제 170kV GIS 단로기 링크교체(무부하가압용)","2026-04-15 09:00","2026-04-15 18:00","취소","취소","연속"]
[109,"남서울","직할","신문래구로#2 T/L","현대제 170kV GIS 단로기 링크교체(무부하가압용)","현대제 170kV GIS 단로기 링크교체(무부하가압용)","2026-04-08 09:00","2026-04-08 18:00","취소","취소","연속"]
[110,"남서울","직할","신문래양평#1 T/L","현대제 170kV GIS 단로기 링크교체","현대제 170kV GIS 단로기 링크교체","2026-04-06 09:00","2026-04-08 18:00","취소","취소","연속"]
[111,"남서울","직할","신문래목동#1 T/L","현대제 170kV GIS 단로기 링크교체(부스절체용)","현대제 170kV GIS 단로기 링크교체(부스절체용)","2026-04-01 09:00","2026-04-01 18:00","취소","취소","당일"]
[112,"남서울","직할","신문래구로#2 T/L","현대제 170kV GIS 단로기 링크교체","현대제 170kV GIS 단로기 링크교체","2026-04-01 09:00","2026-04-03 18:00","취소","취소","연속"]
[113,"남서울","직할","신문래구로#2 T/L","현대제 170kV GIS 단로기 링크교체(무부하가압용)","현대제 170kV GIS 단로기 링크교체(무부하가압용)","2026-04-04 09:00","2026-04-04 18:00","취소","취소","연속"]
[114,"인천","김포","계양불로#1 T/L","검단신도시 송전선로 지중화공사","일부구간 케이블 선종교체[XLPE 2,000㎟ → XLPE 2,000㎟(D)]","2026-04-01 08:00","2026-04-22 18:00","2026-04-01 08:00","2026-04-22 18:00","연속"]
[115,"인천","시흥","신시흥남동#2 T/L","인천남동 첨단산업단지 신시흥-남동T/L 지중화공사","1. 공사구간 : 신시흥-남동T/L No.35～신동C/T 2. 선로길이 : ACSR/AW 410㎟ × 2B × 2C, 0.364km XLPE 2000㎟ / 2C(D) x 0.6km (M/H#7 ~ 신설C/T) 3. 지 지 물 : C/T 신설 1기, 임시철탑 2기, 철탑철거 2기","2026-04-01 08:00","2026-05-09 18:00","취소","취소","연속"]
[116,"인천","시흥","도림오봉#1 T/L","피뢰기 교체공사, 절연유 채유 및 열화진단","- 피뢰기 교체공사 및 절연유 채유 : 오봉C/T - 피뢰기 열화 진단 : 도림C/T","2026-04-01 08:00","2026-04-02 18:00","2026-04-01 08:00","2026-04-02 18:00","매일"]
[117,"인천","김포","장기S/S #1 BUS","장기S/S 신김포-장기#2T/L GIS 정밀점검 무부하가압","장기S/S 신김포-장기#2T/L GIS 정밀점검 무부하가압용","2026-04-01 09:00","2026-04-01 18:00","취소","취소","당일"]
[118,"인천","직할","갈산부흥#3 T/L","부흥S/S #3M.Tr 1차 GIS 정밀점검 무부하가압","부흥S/S #3M.Tr 1차 GIS 정밀점검 무부하가압","2026-04-01 16:00","2026-04-01 18:00","2026-04-01 16:00","2026-04-01 18:00","당일"]
[119,"인천","직할","부흥S/S #65 BUS","부흥S/S #3M.Tr 1차 GIS 정밀점검 무부하가압","부흥S/S #3M.Tr 1차 GIS 정밀점검 무부하가압","2026-04-01 16:00","2026-04-01 18:00","2026-04-01 16:00","2026-04-01 18:00","당일"]
[120,"인천","김포","신김포장기#1 T/L","장기S/S 신김포-장기#1T/L GIS 정밀점검","장기S/S 신김포-장기#1T/L GIS 정밀점검","2026-04-02 09:00","2026-04-04 18:00","취소","취소","당일"]
[121,"인천","김포","장기S/S #2 BUS","장기S/S 신김포-장기#1T/L GIS 정밀점검 무부하가압","장기S/S 신김포-장기#1T/L GIS 정밀점검 무부하가압용","2026-04-02 09:00","2026-04-04 18:00","취소","취소","당일"]
[122,"인천","부평","인천CC포스코CC#1 T/L"," 인천CC-포스코CC#1T/L 637 GIS 보통점검"," 인천CC-포스코CC#1T/L 637 GIS 보통점검","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[123,"인천","시흥","도림오봉#2 T/L","절연유 채유 및 피뢰기 열화진단","- 절연유 채유 : 오봉C/T - 피뢰기 열화 진단 : 도림C/T","2026-04-03 08:00","2026-04-03 18:00","2026-04-03 09:00","2026-04-03 18:00","당일"]
[124,"인천","부평","인천CC포스코CC#2 T/L"," 인천CC-포스코CC#2T/L 677 GIS 보통점검"," 인천CC-포스코CC#2T/L 677 GIS 보통점검","2026-04-03 09:00","2026-04-03 18:00","2026-04-03 09:00","2026-04-03 18:00","당일"]
[125,"인천","시흥","온수소래 T/L","26~27 가공협력 공사(추락방지)","추락방지장치 설치(수평, 4회선 구간) - 온수-소래T/L 76~82, 서안양-소래T/L 76~82","2026-04-04 07:30","2026-04-05 18:00","2026-04-04 07:30","2026-04-05 18:00","매일"]
[126,"인천","시흥","서안양소래 T/L","26~27 가공협력 공사(추락방지)","추락방지장치 설치(수평, 4회선 구간) - 온수-소래T/L 76~82, 서안양-소래T/L 76~82","2026-04-04 07:30","2026-04-05 18:00","2026-04-04 07:30","2026-04-05 18:00","매일"]
[127,"인천","직할","신부평고강#1 T/L"," 신부평-고강#1T/L EBA 비표준형 자기애관 교체공사","비표준형 자기애관을 폴리머애관으로 교체","2026-04-04 08:00","2026-04-05 22:00","2026-04-04 09:00","2026-04-04 14:00","연속"]
[128,"인천","시흥","오봉고잔#1 T/L","오봉S/S 오봉고잔#1T/L GIS 보통점검","오봉S/S 오봉고잔#1T/L GIS 보통점검","2026-04-04 09:00","2026-04-04 14:00","2026-04-04 14:00","2026-04-04 18:00","당일"]
[129,"인천","시흥","오봉고잔#2 T/L","오봉S/S 오봉고잔#2T/L GIS 보통점검","오봉S/S 오봉고잔#2T/L GIS 보통점검","2026-04-04 14:00","2026-04-04 18:00","2026-04-05 09:00","2026-04-05 18:00","당일"]
[130,"인천","직할","갈산부흥#3 T/L","부흥S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","부흥S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","2026-04-04 16:00","2026-04-04 18:00","2026-04-04 16:00","2026-04-04 18:00","당일"]
[131,"인천","직할","부흥S/S #65 BUS","부흥S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","부흥S/S #4M.Tr 1차 GIS 정밀점검 무부하가압","2026-04-04 16:00","2026-04-04 18:00","2026-04-04 16:00","2026-04-04 18:00","당일"]
[132,"인천","부평","송현송월#2 T/L"," 송현-송월#2T/L 657 GIS 보통점검"," 송현-송월#2T/L 657 GIS 보통점검","2026-04-05 09:00","2026-04-05 18:00","취소","취소","연속"]
[133,"인천","시흥","남동동춘 T/L","남동S/S 남동동춘T/L GIS 보통점검","남동S/S 남동동춘T/L GIS 보통점검","2026-04-05 09:00","2026-04-05 18:00","2026-04-05 09:00","2026-04-05 18:00","당일"]
[134,"인천","직할","계양원창 T/L","2026-27년 부평, 김포전력지사 가공송전협력회사 총액공사","수평추락설치, 수직추락정비","2026-04-06 07:00","2026-04-11 18:00","취소","취소","연속"]
[135,"인천","직할","임학계양#1 T/L","2026-27년 부평, 김포전력지사 가공송전협력회사 총액공사","수평추락설치, 수직추락정비","2026-04-06 07:00","2026-04-11 18:00","취소","취소","연속"]
[136,"인천","시흥","신시흥도림#1 T/L","26~27 가공협력 공사(추락방지, 조류착지)","추락방지장치 설치(수평, 4회선 구간) - 신시흥남동#1 No.1~35, 신시흥-도림#1 No,0.5, No.1~25, 도림-오봉#1 No.27~31, No26.9 C/T 2기, No.32 C/T 2기","2026-04-06 07:30","2026-04-13 18:00","취소","취소","매일"]
[137,"인천","김포","경서양촌#2 T/L","검암 플라시아 지장송전선로 지중화공사(2단계)","① (임시선로) 임시철탑 1기 설치 / HSTACIR 330㎟×2C, 0.582km ② (지 중 화) C/T 1기 설치, 철탑 2기 철거 / 지중케이블 0.28㎞(터널)","2026-04-06 08:00","2026-04-11 18:00","취소","취소","연속"]
[138,"인천","김포","신김포S/S SEC CB 60610","신김포S/S #60-#65 모선보호반 대체공사","신김포S/S #60-#65 모선보호반 대체공사","2026-04-06 09:00","2026-04-10 18:00","취소","취소","당일"]
[139,"인천","김포","신김포S/S CB 6100","신김포S/S #60-#65 모선보호반 대체공사","신김포S/S #60-#65 모선보호반 대체공사","2026-04-06 09:00","2026-04-10 18:00","취소","취소","당일"]
[140,"인천","김포","김포장기#1 T/L","장기S/S 김포-장기#1T/L GIS 정밀점검","장기S/S 김포-장기#1T/L GIS 정밀점검","2026-04-06 09:00","2026-04-08 18:00","취소","취소","당일"]
[141,"인천","부평","서인천C/C CB 6133","서인천 #1 G.Tr 1차 6133 GIS 조작(오버홀병행)","서인천C/C #1 G.Tr 1차 6133 GIS 조작(오버홀병행)","2026-04-06 09:00","2026-04-06 18:00","2026-04-06 09:00","2026-04-06 18:00","연속"]
[142,"인천","부평","영종공항열병합#1 T/L","영종S/S 고객측 공항열병합#1T/L GIS 정밀점검(고객요청)","영종S/S 고객측 공항열병합#1T/L GIS 정밀점검(고객요청)","2026-04-06 09:00","2026-04-10 18:00","2026-04-06 09:00","2026-04-10 18:00","연속"]
[143,"인천","부평","주안S/S CB 6100","주안S/S 모선보호반 대체 및 GIS 보통점검 공사","주안S/S 모선보호반 대체 및 GIS 보통점검 공사","2026-04-06 09:00","2026-04-10 18:00","취소","취소","연속"]
[144,"인천","시흥","시화동시화#1 T/L","동시화S/S 시화동시화#1T/L GIS 보통점검","동시화S/S 시화동시화#1T/L GIS 보통점검","2026-04-06 09:00","2026-04-06 14:00","2026-04-06 09:00","2026-04-06 14:00","당일"]
[145,"인천","시흥","오봉남동#1 T/L","오봉S/S 오봉남동#1T/L GIS 보통점검","오봉S/S 오봉남동#1T/L GIS 보통점검 남동S/S 오봉남동#1T/L GIS 보통점검 병행","2026-04-06 09:00","2026-04-06 14:00","2026-04-06 09:00","2026-04-06 14:00","당일"]
[146,"인천","시흥","시화동시화#2 T/L","동시화S/S 시화동시화#2T/L GIS 보통점검","동시화S/S 시화동시화#2T/L GIS 보통점검","2026-04-06 14:00","2026-04-06 18:00","2026-04-06 14:00","2026-04-06 18:00","당일"]
[147,"인천","시흥","오봉남동#2 T/L","오봉S/S 오봉남동#2T/L GIS 보통점검","오봉S/S 오봉남동#2T/L GIS 보통점검 남동S/S 오봉남동#2T/L GIS 조작시험","2026-04-06 14:00","2026-04-06 18:00","2026-04-06 14:00","2026-04-06 18:00","당일"]
[148,"인천","시흥","신시흥#1S/S #65 BUS","신시흥S/S Sh.R 증설공사","- #65BUS endcover 철거 및 모선도킹","2026-04-07 08:00","2026-04-09 18:00","2026-04-07 08:00","2026-04-09 18:00","연속"]
[149,"인천","부평","인천남인천#2 T/L","지중송전설비 위탁정비공사 OF케이블 절연유 열화진단","OF 케이블 절연유의 열화정도 확인","2026-04-07 09:00","2026-04-07 18:00","취소","취소","당일"]
[150,"인천","부평","원창포스코CC#1 T/L","원창S/S 원창-포스코CC#1T/L 617 GIS 보통점검","원창S/S 원창-포스코CC#1T/L 617 GIS 보통점검","2026-04-07 09:00","2026-04-07 18:00","2026-04-09 09:00","2026-04-09 14:00","당일"]
[151,"인천","시흥","북시화서시화#3 T/L","북시화,서시화S/S 북시화서시화#3T/L GIS 조작시험","북시화,서시화S/S 북시화서시화#3T/L GIS 조작시험","2026-04-07 09:00","2026-04-07 14:00","2026-04-09 14:00","2026-04-09 18:00","당일"]
[152,"인천","김포","김포불로#1 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2026-04-08 08:00","2026-04-09 18:00","취소","취소","연속"]
[153,"인천","김포","장기S/S #1 BUS","장기S/S 김포-장기#1T/L GIS 정밀점검 무부하가압","장기S/S 김포-장기#1T/L GIS 정밀점검 무부하가압용","2026-04-08 09:00","2026-04-08 18:00","취소","취소","당일"]
[154,"인천","부평","원창포스코CC#2 T/L","원창S/S 원창-포스코CC#2T/L 647 GIS 보통점검","원창S/S 원창-포스코CC#2T/L 647 GIS 보통점검","2026-04-08 09:00","2026-04-08 18:00","2026-04-11 07:30","2026-04-12 18:00","당일"]
[155,"인천","김포","김포장기#2 T/L","장기S/S 김포-장기#2T/L GIS 정밀점검","장기S/S 김포-장기#2T/L GIS 정밀점검","2026-04-09 09:00","2026-04-11 18:00","취소","취소","당일"]
[156,"인천","부평","송현포스코CC#2 T/L"," 송현-포스코CC#2T/L 657 GIS 보통점검"," 송현-포스코CC#2T/L 657 GIS 보통점검","2026-04-09 09:00","2026-04-09 18:00","2026-04-09 09:00","2026-04-09 18:00","당일"]
[157,"인천","시흥","신시흥S/S CB 6300","신시흥#2S/S #62-#67 BUS TIE GIS 조작시험","신시흥#2S/S #62-#67 BUS TIE GIS 조작시험(6300)","2026-04-09 09:00","2026-04-09 14:00","2026-04-09 09:00","2026-04-09 14:00","당일"]
[158,"인천","시흥","신시흥S/S CB 6400","신시흥#2S/S #63-#68 BUS TIE GIS 조작시험","신시흥#2S/S #63-#68 BUS TIE GIS 조작시험(6400)","2026-04-09 14:00","2026-04-09 18:00","2026-04-09 14:00","2026-04-09 18:00","당일"]
[159,"인천","시흥","신시흥#1S/S #60 BUS","신시흥S/S Sh.R 증설공사","- #60BUS endcover 철거 및 모선도킹","2026-04-10 08:00","2026-04-12 18:00","2026-04-10 08:00","2026-04-12 18:00","연속"]
[160,"인천","부평","신경서경서#3 T/L","신경서S/S 신경서-경서#3T/L 637 GIS 보통점검","신경서S/S 신경서-경서#3T/L 637 GIS 보통점검","2026-04-10 09:00","2026-04-10 18:00","2026-04-10 09:00","2026-04-10 18:00","연속"]
[161,"인천","시흥","신시흥시화#1 T/L","신시흥S/S 신시흥시화#1T/L GIS 보통점검","신시흥S/S 신시흥시화#1T/L GIS 보통점검","2026-04-10 09:00","2026-04-10 18:00","2026-04-10 09:00","2026-04-10 18:00","당일"]
[162,"인천","직할","부흥원미 T/L"," 부흥원미T/L GIS 초기점검(양단)"," 부흥원미T/L GIS 초기점검(양단)","2026-04-10 09:30","2026-04-10 18:00","2026-04-10 09:30","2026-04-10 18:00","당일"]
[163,"인천","시흥","신광명소래 T/L","26~27 가공협력 공사(조류착지)","조류착지방지장치 설치 서서울2-소래T/L No.76~92","2026-04-11 07:30","2026-04-12 18:00","2026-04-11 07:30","2026-04-12 18:00","매일"]
[164,"인천","시흥","서서울#2소래 T/L","26~27 가공협력 공사(조류착지)","조류착지방지장치 설치 서서울2-소래T/L No.76~92","2026-04-11 07:30","2026-04-12 18:00","2026-04-11 07:30","2026-04-12 18:00","매일"]
[165,"인천","김포","장기S/S #2 BUS","장기S/S 김포-장기#2T/L GIS 정밀점검 무부하가압","장기S/S 김포-장기#2T/L GIS 정밀점검 무부하가압용","2026-04-11 09:00","2026-04-11 18:00","취소","취소","당일"]
[166,"인천","부평","신가좌신현#1 T/L"," 신가좌-신현#1T/L 657 GIS 보통점검"," 신가좌-신현#1T/L 657 GIS 보통점검, 피뢰기 교체","2026-04-11 09:00","2026-04-11 18:00","2026-04-11 09:00","2026-04-11 18:00","연속"]
[167,"인천","부평","신가좌신현#2 T/L"," 신가좌-신현#2T/L 687 GIS 보통점검"," 신가좌-신현#2T/L 687 GIS 보통점검","2026-04-12 09:00","2026-04-12 18:00","2026-04-12 09:00","2026-04-12 18:00","연속"]
[168,"인천","직할","임학계양#2 T/L","2026-27년 부평, 김포전력지사 가공송전협력회사 총액공사","수평추락설치, 수직추락정비","2026-04-13 07:00","2026-04-18 18:00","취소","취소","연속"]
[169,"인천","직할","계양북인천 T/L","2026-27년 부평, 김포전력지사 가공송전협력회사 총액공사","수평추락설치, 수직추락정비","2026-04-13 07:00","2026-04-18 18:00","취소","취소","연속"]
[170,"인천","김포","경서양촌#1 T/L","검암 플라시아 지장송전선로 지중화공사(2단계)","① (임시선로) 임시철탑 1기 설치 / HSTACIR 330㎟×2C, 0.582km ② (지 중 화) C/T 1기 설치, 철탑 2기 철거 / 지중케이블 0.28㎞(터널)","2026-04-13 08:00","2026-04-18 18:00","취소","취소","연속"]
[171,"인천","김포","김포불로#2 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2026-04-13 08:00","2026-04-14 18:00","취소","취소","연속"]
[172,"인천","부평","송현포스코CC#1 T/L"," 송현-포스코CC#1T/L OF 케이블 선종교체공사","* 대상구간 : 송현-포스코CC#1T/L 송현EBG∼송포C/T EBA (0.9㎞) * 공사내용 : (선종교체) OF1,200㎟(D) ⇒ XLPE1,200㎟(D), 0.9C-km","2026-04-13 08:00","2026-06-05 18:00","2026-04-13 08:00","2026-06-05 18:00","연속"]
[173,"인천","부평","영종공항열병합#2 T/L","영종S/S 고객측 공항열병합#2T/L GIS 정밀점검(고객요청)","영종S/S 고객측 공항열병합#2T/L GIS 정밀점검(고객요청)","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[174,"인천","직할","부개원미#1 T/L","원미S/S 부개원미#1T/L GIS 조작시험","원미S/S 부개원미#1T/L GIS 조작시험","2026-04-13 09:30","2026-04-13 14:00","2026-04-13 09:30","2026-04-13 14:00","당일"]
[175,"인천","직할","부개원미#2 T/L","원미S/S 부개원미#2T/L GIS 조작시험","원미S/S 부개원미#2T/L GIS 조작시험","2026-04-13 14:00","2026-04-13 18:00","2026-04-13 14:00","2026-04-13 18:00","당일"]
[176,"인천","부평","관교만수#2 T/L","관교S/S 관교-만수#2T/L 627 GIS 보통점검","관교S/S 관교-만수#2T/L 627 GIS 보통점검","2026-04-14 09:00","2026-04-14 18:00","2026-04-14 09:30","2026-04-14 18:00","연속"]
[177,"인천","직할","신부평중동#2 T/L","중동S/S 신부평중동#2T/L GIS 보통점검","중동S/S 신부평중동#2T/L GIS 보통점검","2026-04-14 09:30","2026-04-14 18:00","2026-04-15 09:30","2026-04-15 18:00","당일"]
[178,"인천","김포","신김포양곡#2 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2026-04-15 08:00","2026-04-16 18:00","취소","취소","연속"]
[179,"인천","김포","경서S/S #2 BUS","경서S/S 신경서-경서#3T/L GIS 정밀점검 무부하가압","경서S/S 신경서-경서#3T/L GIS 정밀점검 무부하가압용","2026-04-15 09:00","2026-04-15 18:00","취소","취소","당일"]
[180,"인천","부평","인천S/S CB 6100","인천SS #60-#65 BUS TIE 6100 GIS 보통점검","인천S/S #60-#65 BUS TIE 6100 GIS 보통점검","2026-04-15 09:00","2026-04-15 18:00","취소","취소","연속"]
[181,"인천","직할","신부평중동#3 T/L","중동S/S 신부평중동#3T/L GIS 보통점검","중동S/S 신부평중동#3T/L GIS 보통점검","2026-04-15 09:30","2026-04-15 18:00","2026-04-15 09:30","2026-04-15 18:00","당일"]
[182,"인천","시흥","신시흥도림#2 T/L","26~27 가공협력 공사(추락방지, 조류착지)","추락방지장치 설치(수평, 4회선 구간) - 신시흥남동#2 No.1~35, 신시흥-도림#2 No,0.5, No.1~25, 도림-오봉#2 No.27~31, No.26.9 C/T 2기, No.32 C/T 1기","2026-04-16 07:30","2026-04-22 18:00","취소","취소","매일"]
[183,"인천","부평","중산S/S #1 BUS"," 중산S/S #3M.Tr, Sh.R 증설공사","중산S/S GIS(#3M.Tr 1차, #1Sh.R 1차) 설치 및 무부하가압","2026-04-16 08:00","2026-04-18 08:00","2026-04-16 08:00","2026-04-18 08:00","연속"]
[184,"인천","부평","남인천학익#2 T/L","남인천S/S 남인천-학익#2T/L 667 GIS 보통점검","남인천S/S 남인천-학익#2T/L 667 GIS 보통점검","2026-04-16 09:00","2026-04-16 18:00","취소","취소","연속"]
[185,"인천","김포","신김포장기#2 T/L","장기S/S 신김포-장기#2T/L GIS 정밀점검","장기S/S 신김포-장기#2T/L GIS 정밀점검","2026-04-16 09:00","2026-04-18 18:00","취소","취소","연속"]
[186,"인천","부평","관교만수#1 T/L","관교S/S 관교-만수#1T/L 657 GIS 보통점검","관교S/S 관교-만수#1T/L 657 GIS 보통점검","2026-04-17 07:00","2026-04-17 18:00","2026-04-17 07:00","2026-04-17 18:00","연속"]
[187,"인천","부평","신경서중산 T/L"," 중산S/S #3M.Tr, Sh.R 증설공사","중산S/S GIS( #3M.Tr 1차, #1Sh.R 1차) 무부하가압","2026-04-17 08:00","2026-04-18 08:00","2026-04-17 08:00","2026-04-18 08:00","연속"]
[188,"인천","부평","중산S/S #2 BUS"," 중산S/S #3M.Tr, Sh.R 증설공사","중산S/S GIS(#3M.Tr 1차, #1Sh.R 1차) 설치 및 무부하가압","2026-04-18 08:00","2026-04-20 08:00","2026-04-18 08:00","2026-04-20 08:00","연속"]
[189,"인천","부평","신가좌주안#1 T/L"," 주안-관교 등 4개 T/L EBG 가스채취밸브 교체공사","가스채취밸브 교체공사 (6상)","2026-04-18 08:30","2026-04-20 18:00","취소","취소","연속"]
[190,"인천","직할","중동화곡#1 T/L","중동S/S 중동화곡#1T/L GIS 보통점검","중동S/S 중동화곡#1T/L GIS 보통점검","2026-04-18 09:30","2026-04-18 18:00","취소","취소","당일"]
[191,"인천","부평","신경서중산 T/L"," 중산S/S #3M.Tr, Sh.R 증설공사","중산S/S GIS( #3M.Tr 1차, #1Sh.R 1차) 무부하가압","2026-04-19 08:00","2026-04-20 08:00","2026-04-19 09:30","2026-04-19 18:00","연속"]
[192,"인천","직할","중동화곡#2 T/L","중동S/S 중동화곡#2T/L GIS 보통점검","중동S/S 중동화곡#2T/L GIS 보통점검","2026-04-19 09:30","2026-04-19 18:00","취소","취소","당일"]
[193,"인천","김포","신김포양곡#1 T/L","EBG 가스 채취밸브 설치 및 해체점검 공사","- EBG 보호동관 가스 채취밸브 미 설치개소 보강","2026-04-20 08:00","2026-04-23 18:00","취소","취소","연속"]
[194,"인천","김포","신경서왕길#1 T/L","왕길S/S 신경서-왕길#1T/L 송전선로 보호반 대체","왕길S/S 신경서-왕길#1T/L 송전선로 보호반 대체","2026-04-20 10:00","2026-04-24 18:00","2026-04-20 10:00","2026-04-24 18:00","당일"]
[195,"인천","부평","부흥부개#1 T/L","부개S/S 부흥-부개#1T/L 637 GIS 보통점검","부개S/S 부흥-부개#1T/L 637 GIS 보통점검","2026-04-21 09:00","2026-04-21 18:00","2026-04-23 08:00","2026-05-15 18:00","연속"]
[196,"인천","부평","신가좌S/S CB 6200"," #61-#66 BUS TIE 6200 GIS 보통점검"," #61-#66 BUS TIE 6200 GIS 보통점검","2026-04-21 09:00","2026-04-21 18:00","2026-04-21 09:00","2026-04-21 18:00","연속"]
[197,"인천","부평","부흥부개#2 T/L","부개S/S 부흥-부개#2T/L 647 GIS 보통점검","부개S/S 부흥-부개#2T/L 647 GIS 보통점검","2026-04-22 09:00","2026-04-22 18:00","2026-04-22 09:00","2026-04-22 18:00","연속"]
[198,"인천","부평","신가좌S/S CB 6100"," #60-#65 BUS TIE 6100 GIS 보통점검"," #60-#65 BUS TIE 6100 GIS 보통점검","2026-04-22 09:00","2026-04-22 18:00","2026-04-22 09:00","2026-04-22 18:00","연속"]
[199,"인천","김포","계양불로#2 T/L","검단신도시 송전선로 지중화공사","일부구간 케이블 선종교체[XLPE 2,000㎟ → XLPE 2,000㎟(D)]","2026-04-23 08:00","2026-05-15 18:00","2026-04-23 08:00","2026-05-15 18:00","연속"]
[200,"인천","부평","주안만수#1 T/L","만수S/S 주안-만수#1T/L 617 GIS 보통점검","만수S/S 주안-만수#1T/L 617 GIS 보통점검","2026-04-23 09:00","2026-04-23 18:00","2026-04-23 09:00","2026-04-23 18:00","연속"]
[201,"인천","부평","송현송월#1 T/L","송현S/S 송현-송월#1T/L 677 GIS 보통점검","송현S/S 송현-송월#1T/L 677 GIS 보통점검","2026-04-23 09:00","2026-04-23 18:00","취소","취소","연속"]
[202,"인천","부평","송현남인천 T/L","송현S/S 송현-남인천T/L 637 GIS 보통점검(오전)","송현S/S 송현-남인천T/L 637 GIS 보통점검(오전)","2026-04-24 07:00","2026-04-24 12:00","취소","취소","연속"]
[203,"인천","시흥","신시흥남동#1 T/L","인천남동 첨단산업단지 신시흥-남동T/L 지중화공사","1. 공사구간 : 신시흥-남동T/L No.35～신동C/T 2. 선로길이 : ACSR/AW 410㎟ × 2B × 2C, 0.364km XLPE 2000㎟ / 2C(D) x 0.6km (M/H#7 ~ 신설C/T) 3. 지 지 물 : C/T 신설 1기, 임시철탑 2기, 철탑철거 2기","2026-04-24 08:00","2026-06-01 18:00","취소","취소","연속"]
[204,"인천","부평","신현송현#2 T/L","송현S/S 신현-송현#2T/L 627 GIS 보통점검(오후)","송현S/S 신현-송현#2T/L 627 GIS 보통점검(오후)","2026-04-24 12:00","2026-04-24 18:00","취소","취소","연속"]
[205,"인천","부평","신가좌주안#2 T/L"," 주안-관교 등 4개 T/L EBG 가스채취밸브 교체공사","가스채취밸브 교체공사 (6상)","2026-04-25 08:30","2026-04-27 18:00","취소","취소","연속"]
[206,"인천","부평","관교주안 T/L","주안-관교#1T/L 보호반 대체","주안-관교#1T/L 보호반 대체","2026-04-27 07:00","2026-04-30 18:00","2026-04-27 07:00","2026-04-30 18:00","연속"]
[207,"인천","부평","인천CC현대제철#1 T/L"," 신김포-선인천CC 등 4개T/L 접속설비 보강공사","- 수평추락방지 설치, - 송현-포스코 전선교체 관련 병가구간 휴전","2026-04-27 08:00","2026-04-29 17:00","취소","취소","연속"]
[208,"인천","부평","신경서왕길#1 T/L","신경서-왕길#1T/L 보호반 대체 공사","신경서-왕길#1T/L 보호반 대체 공사","2026-04-27 09:00","2026-05-01 18:00","2026-04-27 09:00","2026-05-01 18:00","연속"]
[209,"인천","부평","신가좌S/S CB 6300","신가좌 #62-#67 BUS TIE 6300 GIS 보통점검","신가좌S/S #62-#67 BUS TIE 6300 GIS 보통점검","2026-04-28 09:00","2026-04-28 18:00","2026-04-28 09:00","2026-04-28 18:00","연속"]
[210,"인천","부평","신가좌인천#3 T/L","신가좌S/S 신가좌-인천#3T/L 637 GIS 보통점검","신가좌S/S 신가좌-인천#3T/L 637 GIS 보통점검","2026-04-29 07:00","2026-04-29 18:00","취소","취소","연속"]
[211,"인천","부평","인천CC현대제철#2 T/L"," 신김포-선인천CC 등 4개T/L 접속설비 보강공사","- 수평추락방지 설치, - 송현-포스코 전선교체 관련 병가구간 휴전","2026-04-30 08:00","2026-04-30 17:00","취소","취소","당일"]
[212,"경기북부","고양","남면백석#2 T/L","26~27년 고양전력 가공송전협력회사 공사","추락방지장치(수평) 설치","2026-04-27 07:30","2026-04-30 17:30","취소","취소","연속"]
[213,"경기북부","고양","문산선유#2 T/L","2026년 고양전력지사 170kV GIS 정밀점검공사","문산-선유#2T/L GIS 정밀점검","2026-04-20 09:00","2026-04-23 18:00","2026-04-20 09:00","2026-04-23 18:00","연속"]
[214,"경기북부","고양","문산선유#1 T/L","2026년 고양전력지사 170kV GIS 정밀점검공사","문산-선유#1T/L GIS 정밀점검","2026-04-13 09:00","2026-04-16 18:00","2026-04-13 09:00","2026-04-16 18:00","연속"]
[215,"경기북부","고양","신파주S/S #66 BUS","신파주S/S GS건설 신규수용공사"," 신파주-GS건설#2T/L GIS 설치(#2DS부)","2026-04-02 09:00","2026-04-10 18:00","2026-04-06 09:00","2026-04-10 18:00","연속"]
[216,"경기북부","고양","신파주송포#2 T/L","25-26 고양전력지사 지중송전 협력회사공사","OF케이블 절연유채유","2026-04-16 09:00","2026-04-16 18:00","2026-04-16 09:00","2026-04-16 18:00","당일"]
[217,"경기북부","고양","신파주송포#1 T/L","25-26 고양전력지사 지중송전 협력회사공사","OF케이블 절연유 채유","2026-04-15 09:00","2026-04-15 18:00","2026-04-15 09:00","2026-04-15 18:00","당일"]
[218,"경기북부","고양","신파주송포#1 T/L","신파주S/S GS건설 신규수용공사"," 66BUS 무부하가압","2026-04-09 09:00","2026-04-10 18:00","2026-04-09 09:00","2026-04-10 18:00","연속"]
[219,"경기북부","고양","신파주원흥#1 T/L","25-26 고양전력지사 지중송전 협력회사공사","EBA 절연유 채유","2026-04-28 09:00","2026-04-28 18:00","2026-04-28 09:00","2026-04-28 18:00","당일"]
[220,"경기북부","고양","일산송포#2 T/L","25-26 고양전력지사 지중송전 협력회사공사","OF케이블 절연유 채유","2026-04-14 09:00","2026-04-14 18:00","2026-04-14 09:00","2026-04-14 18:00","당일"]
[221,"경기북부","고양","일산호수#1 T/L","26~27 고양전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2026-04-01 09:00","2026-04-01 18:00","2026-04-01 09:00","2026-04-01 18:00","연속"]
[222,"경기북부","고양","일산호수#2 T/L","26~27 고양전력지사 변전협력회사 총액공사","170kV GIS 조작시험","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","연속"]
[223,"경기북부","고양","일산송포#1 T/L","25-26 고양전력지사 지중송전 협력회사공사","OF케이블 절연유 채유","2026-04-13 09:00","2026-04-13 18:00","2026-04-13 09:00","2026-04-13 18:00","당일"]
[224,"경기북부","고양","지도능곡#1 T/L","25-26 고양전력지사 지중송전 협력회사공사","OF케이블 절연유 채유","2026-04-21 09:00","2026-04-21 18:00","2026-04-21 09:00","2026-04-21 18:00","당일"]
[225,"경기북부","고양","지도능곡#2 T/L","25-26 고양전력지사 지중송전 협력회사공사","OF케이블 절연유 채유","2026-04-22 09:00","2026-04-22 18:00","2026-04-22 09:00","2026-04-22 18:00","당일"]
[226,"경기북부","고양","지축S/S #66 BUS"," 지축S/S #4M.Tr 증설공사"," #4M.Tr 1차 GIS 설치 (#66BUS)","2026-04-20 09:00","2026-04-24 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[227,"경기북부","고양","양주지축#2 T/L"," 지축S/S #4M.Tr 증설공사"," #61BUS 무부하 가압","2026-04-30 18:00","2026-05-01 18:00","2026-04-30 18:00","2026-05-01 18:00","연속"]
[228,"경기북부","고양","지축S/S #61 BUS"," 지축S/S #4M.Tr 증설공사"," #4M.Tr 1차 GIS 설치 (#61BUS)","2026-04-27 09:00","2026-05-01 18:00","2026-04-27 09:00","2026-05-01 18:00","연속"]
[229,"경기북부","고양","양주지축#2 T/L"," 지축S/S #4M.Tr 증설공사"," #66BUS 무부하 가압","2026-04-23 18:00","2026-04-24 18:00","2026-04-23 18:00","2026-04-24 18:00","연속"]
[230,"경기북부","직할","양주녹양#2 T/L","(계획변경분)녹양S/S 장기사용 170kV GIS 대체공사(2차분)","1. 무부하가압용 선로(#60BUS 모선단말공법 시행 후 1,2Bank무부하가압)","2026-04-26 13:00","2026-04-26 18:00","2026-04-26 13:00","2026-04-26 18:00","당일"]
[231,"경기북부","직할","양주녹양#2 T/L","(계획변경분)녹양S/S 장기사용 170kV GIS 대체공사(2차분)","1. 안전이격거리 휴전(녹양백석#1T/L 월부싱 철거)","2026-04-19 08:00","2026-04-19 18:00","2026-04-19 08:00","2026-04-19 18:00","당일"]
[232,"경기북부","직할","양주녹양#2 T/L","(계획변경분)녹양S/S 장기사용 170kV GIS 대체공사(2차분)","1. #65BUS 무부하가압용 선로","2026-04-18 13:00","2026-04-18 18:00","2026-04-18 13:00","2026-04-18 18:00","당일"]
[233,"경기북부","직할","녹양백석#1 T/L","(계획변경분)녹양S/S 장기사용 170kV GIS 대체공사(2차분)","1. 녹양백석#1TL, #3M.Tr 1차 대체 2. 60-61SEC, 65-66SEC, 61-66TIE, 61BUSPT, 66BUS PT 설치 3. 61-66모선보호반 신설","2026-04-17 08:00","2026-06-15 18:00","2026-04-17 08:00","2026-06-15 18:00","연속"]
[234,"경기북부","직할","신의정부S/S CB 6100","신의정부S/S 신의정부-금오, 용현#3T/L SW 증설공사","신의정부S/S 신의정부-금오#3T/L GIS #60BUS 측 설치","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[235,"경기북부","직할","신의정부S/S #60 BUS","신의정부S/S 신의정부-금오, 용현#3T/L SW 증설공사","신의정부S/S 신의정부-금오#3T/L GIS #60BUS 측 설치","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[236,"경기북부","직할","신의정부용현#2 T/L","신의정부S/S 신의정부-금오, 용현#3T/L SW 증설공사","신의정부S/S 신의정부-용현#3T/L GIS 설치 (인접Bay 가스감압 및 무부하가압용 선로)","2026-04-13 09:00","2026-04-24 18:00","2026-04-13 09:00","2026-04-24 18:00","연속"]
[237,"경기북부","직할","신의정부S/S SEC CB 60610","신의정부S/S 신의정부-금오, 용현#3T/L SW 증설공사","신의정부S/S 신의정부-금오#3T/L GIS #60BUS 측 설치","2026-04-13 09:00","2026-04-17 18:00","2026-04-13 09:00","2026-04-17 18:00","연속"]
[238,"경기북부","직할","신의정부S/S SEC CB 65660","신의정부S/S 신의정부-금오, 용현#3T/L SW 증설공사","신의정부S/S 신의정부-금오#3T/L GIS #65BUS 측 설치","2026-04-20 09:00","2026-04-24 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[239,"경기북부","직할","신의정부S/S #65 BUS","신의정부S/S 신의정부-금오, 용현#3T/L SW 증설공사","신의정부S/S 신의정부-금오#3T/L GIS #65BUS 측 설치","2026-04-20 09:00","2026-04-24 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[240,"경기북부","직할","신의정부S/S CB 6100","신의정부S/S 신의정부-금오, 용현#3T/L SW 증설공사","신의정부S/S 신의정부-금오#3T/L GIS #65BUS 측 설치","2026-04-20 09:00","2026-04-24 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[241,"경기북부","직할","신의정부송우#2 T/L","2026년 가공송전 순시점검 위탁공사","정밀점검 신의정부-미금#2T/L No.1~69 (4.24~5.7) 병가선로 신의정부-송우#2T/L No.5~12 (4.27~28) 신가평-신의정부#1T/L No.139~143 (4.24)","2026-04-14 07:00","2026-04-15 18:00","취소","취소","연속"]
[242,"경기북부","직할","신의정부송우#1 T/L","26~27년 경기북부 직할 가공송전협력회사 공사"," 신의정부-송우#1 철탑추락방지장치 설치(수평) 및 애자련보강","2026-04-28 09:00","2026-04-29 18:00","2026-04-09 09:00","2026-04-10 18:00","연속"]
[243,"경기북부","직할","양주S/S #1 HVDC CB","양주 HVDC 연차점검","#1,2C/S HVDC 변환설비 연차점검","2026-04-01 10:00","2026-04-28 18:00","취소","취소","연속"]
[244,"경기북부","직할","양주지축#1 T/L","26~27년 고양전력 가공송전협력회사 공사","점퍼선, 압축인류크램프, SB댐퍼 교체","2026-04-03 07:30","2026-04-03 17:30","취소","취소","연속"]
[245,"경기북부","직할","양주은평#2 T/L","26~27년 고양전력 가공송전협력회사 공사","점퍼선, 압축인류크램프, SB댐퍼 교체","2026-04-03 07:30","2026-04-03 17:30","취소","취소","연속"]
[246,"경기북부","직할","양주은평#1 T/L","26~27년 고양전력 가공송전협력회사 공사","점퍼선, 압축인류크램프, SB댐퍼 교체","2026-04-01 07:30","2026-04-02 17:30","취소","취소","연속"]
[247,"경기북부","직할","양주쌍문#1 T/L","26~27년 고양전력 가공송전협력회사 공사","추락방지장치(수평) 설치","2026-04-06 07:30","2026-04-08 17:30","취소","취소","연속"]
[248,"경기북부","직할","양주쌍문#2 T/L","26~27년 고양전력 가공송전협력회사 공사","추락방지장치(수평) 설치","2026-04-09 07:30","2026-04-10 17:30","취소","취소","연속"]
[249,"경기북부","직할","양주S/S #2 HVDC CB","양주 HVDC 연차점검","#1,2C/S HVDC 변환설비 연차점검","2026-04-01 10:00","2026-04-28 18:00","취소","취소","연속"]
[250,"경기북부","직할","양주지축#2 T/L","26~27년 고양전력 가공송전협력회사 공사","점퍼선, 압축인류크램프, SB댐퍼 교체","2026-04-01 07:30","2026-04-02 17:30","취소","취소","연속"]
[251,"경기북부","직할","옥정동두천#1 T/L","2026년 가공송전 순시점검 위탁공사","정밀점검 옥정-동두천#1T/L 6일(4/1~8) 병가선로 신포천-동두천 #1T/L 2일(4/1~2) 옥정-송우#2T/L 1일(4/8)","2026-04-01 07:00","2026-04-08 18:00","2026-04-01 07:00","2026-04-08 18:00","연속"]
[252,"경기북부","직할","옥정송우#2 T/L","2026년 가공송전 순시점검 위탁공사","정밀점검 옥정-동두천#1T/L 6일(4/1~8) 병가선로 신포천-동두천 #1T/L 2일(4/1~2) 옥정-송우#2T/L 1일(4/8)","2026-04-08 07:00","2026-04-08 18:00","2026-04-08 07:00","2026-04-08 18:00","당일"]
[253,"경기북부","직할","옥정송우#1 T/L","26~27년 경기북부 직할 가공송전협력회사 공사"," 옥정-송우#1 피뢰기설치","2026-04-22 09:00","2026-04-22 18:00","2026-04-10 07:00","2026-04-10 18:00","연속"]
[254,"경기북부","직할","옥정동두천#2 T/L","26년 직할 및 양주TF GIS 보통점검 공사","(옥정) 옥정동두천#2T/L - GIS 보통점검 (동두천) 옥정동두천#2T/L - GIS 보통점검, 전자변교체","2026-04-27 09:00","2026-04-28 18:00","2026-04-27 09:00","2026-04-28 18:00","연속"]
[255,"경기북부","구리","가평청평HP#2 T/L"," 운천-철원 등 2개T/L 용량증대 전력선 교체공사"," 가평-화천HPT/L 용량증대 전력선 교체관련 병가선로 휴전","2026-04-13 07:00","2026-04-24 18:00","취소","취소","연속"]
[256,"경기북부","구리","가평청평HP#1 T/L"," 운천-철원 등 2개T/L 용량증대 전력선 교체공사"," 가평-화천HPT/L 용량증대 전력선 교체관련 병가선로 휴전","2026-04-13 07:00","2026-04-17 18:00","취소","취소","연속"]
[257,"경기북부","구리","미금구리#2 T/L","26-27년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 보통점검","2026-04-22 09:00","2026-04-22 18:00","2026-04-22 09:00","2026-04-22 18:00","당일"]
[258,"경기북부","구리","미금구리#1 T/L","26-27년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 보통점검","2026-04-21 09:00","2026-04-21 18:00","2026-04-21 09:00","2026-04-21 18:00","당일"]
[259,"경기북부","구리","내촌용정#1 T/L","26-27년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 유사고장 점검","2026-04-07 09:00","2026-04-07 10:30","2026-04-07 09:00","2026-04-07 10:30","당일"]
[260,"경기북부","구리","신의정부내촌#2 T/L","26-27년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 유사고장 점검","2026-04-07 14:30","2026-04-07 16:00","2026-04-07 14:30","2026-04-07 16:00","당일"]
[261,"경기북부","구리","신의정부내촌#1 T/L","26-27년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 유사고장 점검","2026-04-07 13:00","2026-04-07 14:30","2026-04-13 13:00","2026-04-29 18:00","당일"]
[262,"경기북부","구리","내촌용정#2 T/L","26-27년 구리전력지사 변전협력회사 총액공사","관내변전소 GIS 유사고장 점검","2026-04-07 10:30","2026-04-07 12:00","2026-04-07 10:30","2026-04-07 12:00","당일"]
[263,"경기북부","구리","덕소진건#1 T/L","구리송전협력회사 공사_추락방지장치 설치"," 덕소-진건#1T/L No.1,2,10,11,22 관형주 수평 추락방지장치 설치","2026-04-21 07:00","2026-04-22 17:00","2026-04-21 07:00","2026-04-22 17:00","연속"]
[264,"경기북부","구리","덕소진건#2 T/L","구리송전협력회사 공사_추락방지장치 설치"," 덕소-진건#2T/L No.1,2,10,11,22 관형주 수평 추락방지장치 설치","2026-04-23 07:00","2026-04-24 17:00","2026-04-23 07:00","2026-04-24 17:00","연속"]
[265,"경기북부","구리","미금광장 T/L","구리송전협력회사 공사_추락방지장치 설치"," 미금-광장T/L No.1,2,3,7,8~20,32 관형주 수평 추락방지장치 및 No.15,19,28,31 피뢰기 설치","2026-04-09 07:00","2026-04-20 17:00","2026-04-09 07:00","2026-04-20 17:00","연속"]
[266,"경기북부","구리","별내진접 T/L","구리송전협력회사 공사_추락방지장치 설치"," 별내-진접T/L No.2~9 와이어 수평 추락방지장치 설치","2026-04-27 07:00","2026-04-28 17:00","2026-04-27 07:00","2026-04-28 17:00","연속"]
[267,"경기북부","구리","신포천S/S SEC CB 60610","26-27년 구리전력지사 변전협력회사 총액공사"," #61-66 모선보호반 대체","2026-04-06 10:00","2026-04-10 18:00","2026-04-06 10:00","2026-04-10 18:00","연속"]
[268,"경기북부","구리","신포천S/S CB 6200","26-27년 구리전력지사 변전협력회사 총액공사"," #61-66 모선보호반 대체","2026-04-06 10:00","2026-04-10 18:00","2026-04-06 10:00","2026-04-10 18:00","연속"]
[269,"경기북부","구리","신포천S/S SEC CB 65660","26-27년 구리전력지사 변전협력회사 총액공사"," #61-66 모선보호반 대체","2026-04-06 10:00","2026-04-10 18:00","2026-04-06 10:00","2026-04-10 18:00","연속"]
[270,"경기북부","구리","신포천전곡#1 T/L","26~27년 경기북부 직할 가공송전협력회사 공사"," 신포천-전곡 #1 불량애자 교체","2026-04-24 09:00","2026-04-24 18:00","2026-04-24 07:00","2026-04-24 18:00","연속"]
[271,"경기북부","구리","신포천동두천#1 T/L","2026년 가공송전 순시점검 위탁공사","정밀점검 옥정-동두천#1T/L 6일(4/1~8) 병가선로 신포천-동두천 #1T/L 2일(4/1~2) 옥정-송우#2T/L 1일(4/8)","2026-04-01 07:00","2026-04-02 18:00","2026-04-01 07:00","2026-04-02 18:00","연속"]
[272,"경기북부","구리","신포천백학#1 T/L","26~27년 경기북부 직할 가공송전협력회사 공사"," 신포천-백학 철탑추락방지장치 설치","2026-04-27 09:00","2026-04-27 18:00","2026-04-27 09:00","2026-04-27 18:00","연속"]
[273,"경기북부","구리","신포천백학#2 T/L","26~27년 경기북부 직할 가공송전협력회사 공사"," 신포천-백학 철탑추락방지장치 설치","2026-04-28 09:00","2026-04-28 18:00","2026-04-28 09:00","2026-04-28 18:00","연속"]
[274,"경기북부","구리","운천전곡#2 T/L","26~27년 경기북부 직할 가공송전협력회사 공사"," 운천-전곡#2 불량애자교체","2026-04-08 09:00","2026-04-08 18:00","2026-04-24 07:00","2026-04-24 18:00","연속"]
[275,"경기북부","구리","서홍천청평PP T/L","765kV 신안성-신가평 등 12개T/L 추락방지시설 설치공사","신가평-포천LNGCC#1T/L 작업을 위한 하단 병가회선 휴전","2026-04-27 07:00","2026-05-01 18:00","2026-04-27 07:00","2026-05-01 18:00","연속"]
[276,"경기북부","구리","신포천포천#1 T/L","26~27년 경기북부 직할 가공송전협력회사 공사"," 신포천-포천 #1 가공지선 교체","2026-04-23 09:00","2026-04-23 18:00","2026-04-23 09:00","2026-04-23 18:00","연속"]
[277,"경기북부","구리","용정포천#2 T/L","26~27년 경기북부 직할 가공송전협력회사 공사"," 포천-용정#2 피뢰기설치","2026-04-20 09:00","2026-04-20 18:00","2026-04-20 09:00","2026-04-20 18:00","연속"]
[278,"경기","직할","동수원우만#2 T/L","동수원-우만#1 등 4개T/L 절연유 채유","동수원-우만#2T/L 2D A상 (EBG, J/B#1,3,4,6) [총5상]","2026-04-01 09:00","2026-04-03 18:00","2026-04-01 09:00","2026-04-03 18:00","연속"]
[279,"경기","직할","화성발안#1 T/L","화성S/S 화성발안#1 T/L 보통점검","화성S/S 화성발안#1 T/L보통점검","2026-04-01 09:00","2026-04-01 18:00","2026-04-01 09:00","2026-04-01 18:00","당일"]
[280,"경기","동부","감곡가남#1 T/L","154kV 이천-가남 등 2개T/L 용량증대 선종교체공사","154kV 이천-가남T/L 이천S/S~가남S/S 18.2km, 선종교체 ACSR240㎟→ASCC310㎟, 활선 안전이격","2026-05-01 12:00","2026-05-03 16:00","2026-05-01 12:00","2026-05-03 16:00","연속"]
[281,"경기","직할","과천동안양#1 T/L","154kV 의왕-동안양#1T/L 송전선로용 피뢰기 설치","의왕-동안양#1T/L 병가구간 안전이격거리 확보","2026-04-02 07:00","2026-04-04 17:00","2026-04-02 07:00","2026-04-04 17:00","연속"]
[282,"경기","동부","성현분당#1 T/L","성현S/S 성현-분당#1T/L GIS 하자점검 외","성현:성현-분당#1T/L(하자) 분당:성현-분당#1T/L(효성제 발청 조치)","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[283,"경기","직할","화성수촌#2 T/L","화성S/S 화성수촌#2 T/L 보통점검","화성S/S 화성수촌#2 T/L 보통점검","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[284,"경기","평택","서운안성#1 T/L","서운S/S 154kV 신규수용공사(현대차#1,2T/L)","서운S/S 154kV 신규수용공사(현대차#1,2T/L) 2DS,1DS 투입 무부하가압(24h)","2026-04-02 09:00","2026-04-03 18:00","2026-04-02 09:00","2026-04-03 18:00","연속"]
[285,"경기","직할","서수원율전#1 T/L","서수원S/S 서수원율전#1 T/L GIS 조작시험","서수원율전#1 T/L GIS 조작시험","2026-04-03 09:00","2026-04-03 12:00","2026-04-03 09:00","2026-04-03 12:00","당일"]
[286,"경기","직할","서수원율전#2 T/L","서수원S/S 서수원율전#2 T/L GIS 조작시험","서수원율전#2T/L GIS 조작시험","2026-04-03 13:00","2026-04-03 18:00","2026-04-03 13:00","2026-04-03 18:00","당일"]
[287,"경기","성남","신수원S/S #61 BUS","신수원S/S 154kV 계통조정 공사(1차분)","- (신)61-62, 66-67SEC, #63M.Tr 1차 GIS 설치분 인터록시험 및 앵글측정","2026-04-24 15:00","2026-04-24 18:00","취소","취소","연속"]
[288,"경기","평택","원정평택TP#1 T/L","2026-2027년 평택전력 가공송전협력회사 공사","추락방지장치(수평) 설치공사, 점퍼지지애자 설치공사 -작업구간: No.1~6","2026-04-06 08:00","2026-04-08 18:00","2026-04-06 08:00","2026-04-08 18:00","연속"]
[289,"경기","성남","기흥신갈#1 T/L","154kV 신용인-동백 등 3개T/L 노후 피뢰기 교체공사","154kV 신용인-동백#1,2, 신용인-기흥#1,2, 기흥-신갈#1,2 T/L 노후피뢰기 철거 및 신규 폴리머피뢰기 설치","2026-04-06 09:00","2026-04-06 18:00","2026-04-06 09:00","2026-04-06 18:00","당일"]
[290,"경기","성남","신수원S/S #60 BUS","신수원S/S 154kV 계통조정 공사(2차분)","- 공GIB(1Bay) 철거, (신)6200TIE 설치","2026-04-27 09:00","2026-05-06 15:00","취소","취소","연속"]
[291,"경기","성남","모현용인#1 T/L","2026년 가공송전선로 순시점검 위탁공사","154kV 모현-용인T/L 정밀점검","2026-04-06 09:00","2026-04-10 18:00","2026-04-06 09:00","2026-04-10 18:00","연속"]
[292,"경기","직할","관양동안양#1 T/L","25~26년 군포전력 지중송전 협력회사 공사","EBG 가스채취밸브 설치 공사","2026-04-06 09:00","2026-04-07 18:00","2026-04-06 09:00","2026-04-07 18:00","연속"]
[293,"경기","평택","원정만호#1 T/L","2026년도 가공송전선로 순시점검 위탁공사","154kV 원정만호T/L 정밀점검 시행","2026-04-06 09:00","2026-04-07 18:00","2026-04-06 09:00","2026-04-07 18:00","연속"]
[294,"경기","평택","평택S/S #1 BUS","154kV 평택S/S 옥내화 공사","옥내화 변전소 연결T/L용 모선 보강","2026-04-06 09:00","2026-04-08 18:00","2026-04-06 09:00","2026-04-08 18:00","연속"]
[295,"경기","성남","기흥신갈#2 T/L","154kV 신용인-동백 등 3개T/L 노후 피뢰기 교체공사","154kV 신용인-동백#1,2, 신용인-기흥#1,2, 기흥-신갈#1,2 T/L 노후피뢰기 철거 및 신규 폴리머피뢰기 설치","2026-04-07 09:00","2026-04-07 18:00","2026-04-07 09:00","2026-04-07 18:00","당일"]
[296,"경기","직할","관양동안양#2 T/L","25~26년 군포전력 지중송전 협력회사 공사","EBG 가스채취밸브 설치 공사","2026-04-08 09:00","2026-04-09 18:00","2026-04-08 09:00","2026-04-09 18:00","연속"]
[297,"경기","평택","원정만호#2 T/L","2026년도 가공송전선로 순시점검 위탁공사","154kV 원정만호T/L 정밀점검 시행","2026-04-08 09:00","2026-04-09 18:00","2026-04-08 09:00","2026-04-09 18:00","연속"]
[298,"경기","군포","사강남양#1 T/L","154kV 남양-사강T/L 지중화공사_가공 본이설공사","154kV 남양-사강T/L 지중화공사_가공 본이설공사","2026-04-09 07:00","2026-04-22 18:00","2026-04-09 07:00","2026-04-22 18:00","연속"]
[299,"경기","평택","원정평택TP#2 T/L","2026-2027년 평택전력 가공송전협력회사 공사","추락방지장치(수평) 설치공사, 점퍼지지애자 설치공사 -작업구간: No.1~6","2026-04-09 08:00","2026-04-10 18:00","2026-04-09 08:00","2026-04-10 18:00","연속"]
[300,"경기","동부","중원야탑 T/L","중원S/S 중모, 중원-야탑T/L 2DS 링크 교체 등","중원:중모T/L(2DS 링크 교체), 중원-야탑T/L(2DS 링크 교체, 전자변 교체) * 중모T/L 2DS 누기점검 * 65BUS 휴전","2026-04-09 09:00","2026-04-10 18:00","2026-04-09 09:00","2026-04-10 18:00","연속"]
[301,"경기","평택","평택S/S #2 BUS","154kV 평택S/S 옥내화 공사","옥내화 변전소 연결T/L용 모선 보강","2026-04-09 09:00","2026-04-11 18:00","2026-04-09 09:00","2026-04-11 18:00","연속"]
[302,"경기","군포","신안산남안산#1 T/L","남안산S/S 신안산-남안산#1T/L 인출 ES 투입불량 보수","남안산S/S 신안산-남안산#1T/L 인출 ES 투입불량 보수","2026-04-10 09:00","2026-04-10 18:00","2026-04-10 09:00","2026-04-10 18:00","당일"]
[303,"경기","직할","평촌안양2CC#1 T/L","평촌S/S 평촌안양CC#1 T/L GIS 보통점검","- 평촌S/S 평촌안양CC#1 T/L GIS 보통점검 - 안양C.C 평촌안양CC#1 T/L GIS 보통점검","2026-04-10 09:00","2026-04-10 18:00","2026-04-10 09:00","2026-04-10 18:00","당일"]
[304,"경기","군포","서안양소래 T/L","광명-시흥지역 전기공급시설 전력구공사(남광명분기 1단계)","남광명변전소 신설로 취약한 기설 설비(154kV 서안양-소래, 서서울2-서안양 T/L) 보강을 위해 기존 서안양#11맨홀 구조물 일부를 철거하고 확장하는 공사로 활선에 근접하여 구조물 깨기, 가시설설치, 신설 확장공사 등을 시행하여 설비고장 및 안전사고 위험이 높아 휴전 신청","2026-04-11 08:00","2026-04-11 18:00","2026-04-11 08:00","2026-04-11 18:00","연속"]
[305,"경기","평택","청북평택#1 T/L","2026년도 가공송전선로 순시점검 위탁공사","154kV 포승청북 및 청북평택T/L 정밀점검","2026-04-13 08:00","2026-04-14 18:00","2026-04-13 08:00","2026-04-14 18:00","연속"]
[306,"경기","평택","포승청북 T/L","2026년도 가공송전선로 순시점검 위탁공사","154kV 포승청북 및 청북평택T/L 정밀점검","2026-04-13 08:00","2026-04-17 18:00","2026-04-13 08:00","2026-04-17 18:00","연속"]
[307,"경기","성남","모현용인#2 T/L","2026년 가공송전선로 순시점검 위탁공사","154kV 모현-용인T/L 정밀점검","2026-04-13 09:00","2026-04-17 18:00","취소","취소","연속"]
[308,"경기","직할","동수원우만#1 T/L","동수원-우만#1 등 4개T/L 절연유 채유","동수원-우만#1T/L(D) A,B,C상 (EBG, J/B#1, 6), [총 18상]","2026-04-13 09:00","2026-04-15 18:00","2026-04-13 09:00","2026-04-15 18:00","연속"]
[309,"경기","직할","동안양안양CC#2 T/L","동안양-안양열병합#2T/L GIS 초기점검","동안양-안양열병합#2T/L GIS 초기점검","2026-04-13 09:00","2026-04-13 18:00","2026-04-13 09:00","2026-04-13 18:00","당일"]
[310,"경기","평택","서안성안성#1 T/L","154kV 추곡S/S 및 분기 송전선로 건설공사","○ 목적 : 안성지역 택지 및 산업단지 개발 신규부하 공급능력 확보 및 인근 변전소(154kV 안성, 서운S/S) 부하분담 ○ 사업구간 : 154kV 서안성-안성T/L No.21~25호 구간 ○ 경과지역 : 경기도 안성시 양성면 추곡리 산2 등 ○ 사업규모 - 변전 : 154kV M.Tr 60MVA × 2Bank - 송전 : 철탑5기(2회선 2기, 4회선 3기), ACSR 410*2B*2,4C, 1.7km","2026-04-13 09:00","2026-05-22 18:00","2026-04-13 09:00","2026-05-22 18:00","연속"]
[311,"경기","직할","동안양안양CC#1 T/L","동안양-안양열병합#1T/L GIS 초기점검","동안양-안양열병합#1T/L GIS 초기점검","2026-04-14 09:00","2026-04-14 18:00","2026-04-14 09:00","2026-04-14 18:00","당일"]
[312,"경기","평택","평택추팔#1 T/L","154kV 평택S/S 옥내화 공사","평택S/S 연결T/L용 기초보강 작업시 안전이격 확보","2026-04-14 09:00","2026-04-15 18:00","2026-04-14 09:00","2026-04-15 18:00","연속"]
[313,"경기","평택","포승평택TP#1 T/L","2026년도 가공송전선로 순시점검 위탁공사","154kV 포승청북 및 청북평택T/L 정밀점검","2026-04-15 08:00","2026-04-17 18:00","2026-04-15 08:00","2026-04-17 18:00","연속"]
[314,"경기","직할","평촌안양2CC#2 T/L","평촌S/S 평촌안양CC#2 T/L GIS 보통점검","- 평촌S/S 평촌안양CC#2 T/L GIS 보통점검 - 안양C.C 평촌안양CC#2 T/L GIS 보통점검","2026-04-15 09:00","2026-04-15 18:00","2026-04-15 09:00","2026-04-15 18:00","당일"]
[315,"경기","직할","평촌안양2CC#3 T/L","평촌S/S 평촌안양CC#3 T/L GIS 보통점검","- 평촌S/S 평촌안양CC#3 T/L GIS 보통점검 - 안양C.C 평촌안양CC#3 T/L GIS 보통점검","2026-04-16 09:00","2026-04-16 18:00","2026-04-16 09:00","2026-04-16 18:00","당일"]
[316,"경기","성남","용인덕성#1 T/L","26년 성남전력 170kV GIS 보통점검 공사","덕성: GIS 보통점검 용인: CVT 초기점검(협력)","2026-04-17 09:00","2026-04-17 14:00","2026-04-17 09:00","2026-04-17 14:00","당일"]
[317,"경기","성남","용인덕성#2 T/L","26년 성남전력 170kV GIS 보통점검 공사","GIS 보통점검","2026-04-17 14:00","2026-04-17 18:00","2026-04-17 14:00","2026-04-17 18:00","당일"]
[318,"경기","군포","서서울#2서안양 T/L","광명-시흥지역 전기공급시설 전력구공사(남광명분기 1단계)","남광명변전소 신설로 취약한 기설 설비(154kV 서안양-소래, 서서울2-서안양 T/L) 보강을 위해 기존 서안양#11맨홀 구조물 일부를 철거하고 확장하는 공사로 활선에 근접하여 구조물 깨기, 가시설설치, 신설 확장공사 등을 시행하여 설비고장 및 안전사고 위험이 높아 휴전 신청","2026-04-18 08:00","2026-04-18 18:00","2026-04-18 08:00","2026-04-18 18:00","연속"]
[319,"경기","성남","신용인용인#1 T/L","26-27년 경기직할 가공송전 협력회사 공사","상간스페이서 설치","2026-04-20 07:00","2026-04-22 18:00","2026-04-20 07:00","2026-04-22 18:00","연속"]
[320,"경기","평택","소사벌안성 T/L","154kV 소사벌-안성T/L 접속함 해체점검","154kV 소사벌-안성T/L PD발생 조치","2026-04-20 08:00","2026-04-24 18:00","2026-04-20 08:00","2026-04-24 18:00","연속"]
[321,"경기","군포","신안산성포#3 T/L","성포,안산S/S 154kV 성포-안산 1회선 증설공사","- 성포-안산T/L 앵글측정 - 성포-안산T/L 전체 무부하","2026-04-20 09:00","2026-04-21 18:00","2026-04-20 09:00","2026-04-21 18:00","연속"]
[322,"경기","동부","곤지암S/S CB 6100","곤지암S/S 170kV 6100, 6200 GIS 보통점검","곤지암:6100(보통), 6200(보통)","2026-04-20 09:00","2026-04-20 14:00","2026-04-20 09:00","2026-04-20 14:00","당일"]
[323,"경기","동부","성현분당#2 T/L","26-27년 동부전력지사 가공송전협력회사 공사","폴리머지지애자설치 : 4,7,9,15,25,26,31,36,38,39,40,41(12기)","2026-04-20 09:00","2026-04-23 18:00","취소","취소","연속"]
[324,"경기","동부","곤지암S/S CB 6200","곤지암S/S 170kV 6100, 6200 GIS 보통점검","곤지암:6100(보통), 6200(보통)","2026-04-20 14:00","2026-04-20 18:00","2026-04-20 14:00","2026-04-20 18:00","당일"]
[325,"경기","평택","포승평택TP#2 T/L","2026년도 가공송전선로 순시점검 위탁공사","154kV 희곡청북 및 청북평택T/L 정밀점검","2026-04-21 08:00","2026-04-24 18:00","2026-04-21 08:00","2026-04-24 18:00","연속"]
[326,"경기","군포","화성남양#1 T/L","154kV 동송산S/S 건설공사 사용전검사(3차)","동송산S/S 남양-동송산, 동송산-사강 #1T/L GIS 사용전검사","2026-04-21 09:00","2026-04-22 18:00","2026-04-21 09:00","2026-04-22 18:00","연속"]
[327,"경기","군포","마도사강#1 T/L","154kV 동송산S/S 건설공사 사용전검사(3차)","동송산S/S 남양-동송산, 동송산-사강 #1T/L GIS 사용전검사","2026-04-21 09:00","2026-04-22 18:00","2026-04-21 09:00","2026-04-22 18:00","연속"]
[328,"경기","성남","신수원북동탄#1 T/L","26년 성남전력 170kV GIS 보통점검 공사","GIS 보통점검","2026-04-21 09:00","2026-04-21 14:00","2026-04-21 09:00","2026-04-21 14:00","당일"]
[329,"경기","성남","신수원북동탄#2 T/L","26년 성남전력 170kV GIS 보통점검 공사","GIS 보통점검","2026-04-21 14:00","2026-04-21 18:00","2026-04-21 14:00","2026-04-21 18:00","당일"]
[330,"경기","성남","정자동판교#1 T/L","26년 성남전력 170kV GIS 정밀점검 공사","GIS 정밀점검 DS 방압변 점검","2026-04-22 09:00","2026-04-23 18:00","2026-04-22 09:00","2026-04-23 18:00","연속"]
[331,"경기","직할","화성남양#1 T/L","화성S/S 화성남양#1 T/L GIS 조작시험","화성S/S 화성남양#1 T/L GIS 조작시험","2026-04-24 09:00","2026-04-24 12:00","취소","취소","당일"]
[332,"경기","직할","화성남양#2 T/L","화성S/S 화성남양#2 T/L GIS 조작시험","화성S/S 화성남양#2 T/L GIS 조작시험","2026-04-24 13:00","2026-04-24 18:00","2026-04-24 13:00","2026-04-24 18:00","당일"]
[333,"경기","동부","이천가남#1 T/L","154kV 이천-가남 등 2개T/L 용량증대 선종교체공사","154kV 이천-가남T/L 이천S/S~가남S/S 12.9km, 선종교체 ACSR240㎟→ASCC310㎟","2026-05-24 16:00","2026-06-18 12:00","2026-05-24 16:00","2026-06-18 12:00","연속"]
[334,"경기","군포","서서울#2봉담#1 T/L","154kV 서서울2-봉담T/L No.23호 철탑 긴급 보강작업","154kV 서서울2-봉담T/L No.23호 철탑 긴급 보강작업","2026-04-25 07:00","2026-04-26 18:00","취소","취소","연속"]
[335,"경기","군포","서서울#2봉담#2 T/L","154kV 서서울2-봉담T/L No.23호 철탑 긴급 보강작업","154kV 서서울2-봉담T/L No.23호 철탑 긴급 보강작업","2026-04-25 07:00","2026-04-26 18:00","취소","취소","연속"]
[336,"경기","평택","오산평택#2 T/L","154kV 오산-평택T/L 용량증대전선교체 및 안전이격확보공사","- 용량증대 전선교체 : No.1 ~ 59(16.518km) - 안전이격 확보공사 : No.30, 32, 33, 36, 43, 48","2026-04-27 07:00","2026-05-31 18:00","2026-04-27 07:00","2026-05-31 18:00","연속"]
[337,"경기","평택","오산향남#2 T/L","154kV 오산-평택T/L 용량증대전선교체 및 안전이격확보공사","- 용량증대 전선교체공사 관련 작업안전확보","2026-04-27 07:00","2026-05-23 18:00","2026-04-27 07:00","2026-05-23 18:00","연속"]
[338,"경기","군포","반월시화#1 T/L","반월,시화S/S 반월-시화#1T/L GIS 보통점검","반월S/S 반월-시화#1T/L 667 GIS 보통점검, LA 보통점검 시화S/S 반월-시화#1T/L 617 GIS 보통점검, LA 보통점검","2026-04-27 09:00","2026-04-27 18:00","2026-04-27 09:00","2026-04-27 18:00","당일"]
[339,"경기","동부","곤지암S/S SEC CB 60610","곤지암S/S 170kV #60-61, #65-66 GIS 보통점검","곤지암:60-61(보통), 65-66(보통)","2026-04-27 09:00","2026-04-27 14:00","취소","취소","당일"]
[340,"경기","성남","정자동판교#2 T/L","26년 성남전력 170kV GIS 정밀점검 공사","GIS 정밀점검 DS 방압변 점검","2026-04-27 09:00","2026-04-28 18:00","2026-04-27 09:00","2026-04-28 18:00","연속"]
[341,"경기","직할","화성장덕#2 T/L","화성S/S 화성장덕#2 T/L 조작시험","화성S/S 화성장덕#2 T/L 조작시험","2026-04-27 09:00","2026-04-27 12:00","2026-04-27 09:00","2026-04-27 12:00","당일"]
[342,"경기","평택","서운안성#1 T/L","서운S/S 154kV 신규수용공사(현대차#1,2T/L)","서운S/S 154kV 신규수용공사(현대차#1,2T/L) 무부하가압(24h)","2026-04-27 09:00","2026-04-28 18:00","2026-04-27 09:00","2026-04-28 18:00","연속"]
[343,"경기","동부","곤지암S/S SEC CB 65660","곤지암S/S 170kV #60-61, #65-66 GIS 보통점검","곤지암:60-61(보통), 65-66(보통)","2026-04-27 14:00","2026-04-27 18:00","취소","취소","당일"]
[344,"경기","군포","반월시화#2 T/L","반월,시화S/S 반월-시화#2T/L GIS 보통점검","반월S/S 반월-시화#2T/L 687 GIS 보통점검, LA 보통점검 시화S/S 반월-시화#2T/L 627 GIS 보통점검, LA 보통점검","2026-04-28 09:00","2026-04-28 18:00","2026-04-28 09:00","2026-04-28 18:00","당일"]
[345,"경기","직할","안양평촌#1 T/L","평촌S/S 안양평촌T/L 조작시험","- 평촌S/S 안양평촌T/L 조작시험 - 평촌S/S 안양평촌T/L 전자변 교체","2026-04-28 09:00","2026-04-28 12:00","2026-04-28 09:00","2026-04-28 12:00","당일"]
[346,"경기","직할","화성발안#2 T/L","화성S/S 화성발안#2 T/L 보통점검","화성S/S 화성발안#2 T/L 보통점검","2026-04-28 09:00","2026-04-28 18:00","2026-04-28 09:00","2026-04-28 18:00","당일"]
[347,"경기","성남","신용인S/S CB 6100","26년 성남전력 170kV GIS 정밀점검 공사","GIS 정밀점검","2026-04-29 09:00","2026-04-30 18:00","취소","취소","연속"]
[348,"경기","직할","안양평촌#3 T/L","평촌S/S 안양평촌 3T/L 초기점검","평촌S/S 안양평촌 3T/L 초기점검","2026-04-29 09:00","2026-04-29 18:00","2026-04-29 09:00","2026-04-29 18:00","당일"]
[349,"경기","군포","장덕마도#2 T/L","마도S/S 장덕-마도#2T/L GIS 보통점검","마도S/S 장덕-마도#2T/L GIS 보통점검","2026-04-30 09:00","2026-04-30 18:00","2026-04-30 09:00","2026-04-30 18:00","당일"]
[350,"경기","직할","화성수촌#1 T/L","화성S/S 화성수촌#1 T/L 보통점검","화성S/S 화성수촌#1 T/L 보통점검","2026-04-30 09:00","2026-04-30 18:00","2026-04-30 09:00","2026-04-30 18:00","당일"]
[351,"경기","평택","서운안성#2 T/L","2026년 평택 변전협력 총액공사(서운-안성#2T/L)","서운S/S 서운-안성#2T/L GIS 보통점검","2026-04-30 09:00","2026-04-30 18:00","2026-04-30 09:00","2026-04-30 18:00","연속"]
[352,"경기","평택","평택S/S CB 6100","2026년 평택 변전협력 총액공사(평택S/S #6100)","평택S/S 6100B/T GCB보통점검","2026-04-30 09:00","2026-04-30 18:00","2026-04-30 09:00","2026-04-30 18:00","당일"]
[353,"경기","성남","신용인S/S #60 BUS","26년 성남전력 170kV GIS 정밀점검 공사","6100B/T 무부하 가압","2026-04-30 13:00","2026-04-30 16:00","취소","취소","당일"]
[354,"경기","성남","신수원S/S #61 BUS","신수원S/S 154kV 계통조정 공사(1차분)","#63M.Tr 1차 GIS, (구)#62M.Tr 1차 GIS(운휴Bay), 공GIB(1Bay) 철거 - (신)61-62, 66-67SEC 설치, #63M.Tr 1차 GIS 설치","2026-03-30 09:00","2026-04-10 18:00","취소","취소","연속"]
[355,"경기","성남","신수원S/S #66 BUS","신수원S/S 154kV 계통조정 공사(1차분)","#66BUS 모선철거 - (신)61-62, 66-67 SEC 설치, #63M.Tr 1차 GIS 설치","2026-04-13 09:00","2026-04-24 15:00","취소","취소","연속"]
[356,"강원","강릉","동해강릉 T/L","2026~2027년 가공송전협력회사 총액공사","○ 폴리머 점퍼 지지애자 설치 - 154kV 강릉(동해-강릉)T/L NO. 8.1, 10, 12.1, 17, 21, 26, 29, 32, 36, 37, 38, 40.1, 41, 42, 44, 45, 46, 51, 54, 57, 59 - 154kV 동해분기(동해-강릉)T/L NO.1, 3, 5, 9, 10, 11, 13, 26, 29, 30, 32, 33, 34, 35, 38, 41, 46, 48.1, 53.1","2026-04-24 08:00","2026-05-01 18:00","취소","취소","매일"]
[357,"강원","강릉","강릉영동TP T/L","2026~2027년 가공송전협력회사 총액공사","○ 폴리머 점퍼 지지애자 설치 - 154kV 영동TP-강릉 T/L No.5, 7.1, 8, 8.1, 12, 12.1, 21, 26, 28, 29, 37, 40.1, 44, 45, 51, 57, 59, 63, 65","2026-04-20 08:00","2026-04-23 18:00","취소","취소","매일"]
[358,"강원","강릉","평창올림픽 T/L","2026~2027년 강릉전력지사 변전협력회사 총액공사","170kV GIS, LA 보통점검","2026-04-14 10:00","2026-04-14 18:00","취소","취소","당일"]
[359,"강원","강릉","신제천주진#1 T/L","2026-27년 원주전력지사 가공송전 협력회사 공사","송전선로용 피뢰기 설치 및 전력선 이도조정","2026-04-13 07:00","2026-04-24 18:00","2026-04-13 07:00","2026-04-24 18:00","매일"]
[360,"강원","강릉","주진평창#2 T/L","500kV HVDC 동해안-신가평 송전선로 건설사업(6공구)","발받침철탑 보호망 설치를 위한 휴전신청","2026-04-15 07:00","2026-04-17 18:00","2026-04-15 07:00","2026-04-17 18:00","연속"]
[361,"강원","강릉","주진평창#1 T/L","500kV HVDC 동해안-신가평 송전선로 건설사업(6공구)","발받침철탑 보호망 설치를 위한 휴전신청","2026-04-15 07:00","2026-04-17 18:00","2026-04-15 07:00","2026-04-17 18:00","연속"]
[362,"강원","동해","삼척동해TP T/L","154kV 이원-도계 1파이분기T/L 건설공사","□ 공 사 명 : 154kV 이원-도계 1파이분기 T/L건설공사 □ 공사목적 : 삼척변전소 단일계통 보강을 통한 안정적 전력공급 □ 공사구간 : 기설 154kV 이원-태백T/L No.111~신설No.14(2C) 기설 154kV 삼척분기T/L No.22~삼척S/S(4C 하단)","2026-04-11 07:00","2026-05-07 18:00","2026-04-11 07:00","2026-05-07 18:00","연속"]
[363,"강원","동해","이원태백 T/L","345kV 동해 등 15개 T/L 추락방지장치 설치공사","안전이격공사","2026-04-13 08:00","2026-04-23 18:00","2026-04-13 08:00","2026-04-23 18:00","매일"]
[364,"강원","동해","이원도계 T/L","345kV 동해 등 15개 T/L 추락방지장치 설치공사","안전이격공사","2026-04-24 08:00","2026-05-06 18:00","2026-04-24 08:00","2026-05-06 18:00","매일"]
[365,"강원","동해","정선S/S CB 6100","2026~27년 변전정비팀 총액공사","정선S/S 6100 GIS 보통점검","2026-04-24 10:00","2026-04-24 18:00","2026-04-24 10:00","2026-04-24 18:00","당일"]
[366,"강원","동해","동해정선 T/L","2026~27년 변전정비팀 총액공사","정선S/S 154kV 동해-정선T/L GIS 보통점검","2026-04-23 10:00","2026-04-23 18:00","2026-04-23 10:00","2026-04-23 18:00","당일"]
[367,"강원","동해","정선영월CC T/L","2026~27년 변전정비팀 총액공사","정선S/S 154kV 정선-영월CC T/L GIS 보통점검","2026-04-22 10:00","2026-04-22 18:00","2026-04-22 10:00","2026-04-22 18:00","당일"]
[368,"강원","원주","원주북원주#1 T/L","2026-27년 원주전력지사 가공송전 협력회사 공사","154kV 원주-서원주#2T/L 송전선로용 피뢰기 설치구간 안전조치(4회선 하단)","2026-04-27 07:00","2026-04-27 18:00","취소","취소","당일"]
[369,"강원","원주","원주서원주#2 T/L","2026-27년 원주전력지사 가공송전 협력회사 공사","송전선로용 피뢰기 설치","2026-04-27 07:00","2026-04-28 18:00","취소","취소","매일"]
[370,"강원","원주","원주북원주#2 T/L","2026-27년 원주전력지사 가공송전 협력회사 공사","송전선로용 피뢰기 설치","2026-04-29 07:00","2026-04-29 18:00","취소","취소","당일"]
[371,"강원","원주","원주서원주#1 T/L","2026-27년 원주전력지사 가공송전 협력회사 공사","154kV 원주-북원주#2T/L 송전선로용 피뢰기 설치구간 안전조치(4회선 하단)","2026-04-29 07:00","2026-04-29 18:00","취소","취소","당일"]
[372,"강원","원주","서원주문막#1 T/L","2026-27년 원주전력지사 가공송전 협력회사 공사","154kV 원주-서원주#2T/L 송전선로용 피뢰기 설치구간 안전조치(4회선 하단)","2026-04-28 07:00","2026-04-28 18:00","취소","취소","당일"]
[373,"강원","직할","인제양구#1 T/L","2026년 가공송전 순시점검 위탁공사","154kV 인제-양구T/L 정밀점검 시행","2026-04-13 09:00","2026-04-20 18:00","2026-04-13 09:00","2026-04-20 18:00","매일"]
[374,"강원","직할","인제양구#2 T/L","2026년 가공송전 순시점검 위탁공사","154kV 인제-양구T/L 정밀점검 시행","2026-04-21 09:00","2026-04-28 18:00","2026-04-21 09:00","2026-04-28 18:00","매일"]
[375,"강원","직할","인제S/S CB 6100","2026~2027년 강원본부 직할 변전협력회사 공사","154kV #1-#2 BUS TIE CB 디지털화 공사","2026-04-01 09:00","2026-04-03 18:00","2026-04-01 09:00","2026-04-03 18:00","연속"]
[376,"강원","직할","북춘천화천HP T/L","화천HP 가평-화천HPTL GCB 대체공사 및 정밀점검","가평-화천HPTL GCB 대체공사로 인한 안전이격거리 확보(매일)","2026-04-06 10:00","2026-04-10 18:00","2026-04-06 10:00","2026-04-10 18:00","매일"]
[377,"강원","태백","영월영월CC T/L","2026년 태백전력지사 변전협력회사 공사","영월-영월CC T/L GIS 조작시험","2026-04-23 09:00","2026-04-23 18:00","2026-04-23 09:00","2026-04-23 18:00","당일"]
[378,"충북","직할","서운광혜원 T/L","26~27년 충북본부 직할 가공송전 협력회사 공사","26~27년 충북본부 직할 가공송전 협력회사 공사","2026-04-06 09:00","2026-04-12 18:00","취소","취소","연속"]
[379,"충북","직할","진천광혜원#1 T/L","26~27년 충북본부 직할 가공송전 협력회사 공사","26~27년 충북본부 직할 가공송전 협력회사 공사","2026-04-06 09:00","2026-04-12 18:00","취소","취소","연속"]
[380,"충북","직할","신진천문백#2 T/L","26-27년 충북직할 변전협력회사 공사","문백S/S 신진천-문백#2T/L GIS 하자점검","2026-04-20 10:00","2026-04-20 18:00","2026-04-20 10:00","2026-04-20 18:00","당일"]
[381,"충북","직할","문백오창#2 T/L","26-27년 충북직할 변전협력회사 공사","문백S/S 문백-오창#2T/L GIS 하자점검","2026-04-15 10:00","2026-04-15 18:00","2026-04-15 10:00","2026-04-15 18:00","당일"]
[382,"충북","직할","문백오창#1 T/L","26-27년 충북직할 변전협력회사 공사","문백S/S 문백-오창 #1T/L GIS 하자점검","2026-04-14 10:00","2026-04-14 18:00","2026-04-14 10:00","2026-04-14 18:00","당일"]
[383,"충북","직할","신진천진천#2 T/L","26-27년 충북직할 변전협력회사 공사","신진천S/S 신진천-진천 #2T/L GIS 전자변 교체","2026-04-24 14:00","2026-04-24 18:00","2026-04-24 14:00","2026-04-24 18:00","당일"]
[384,"충북","직할","신진천진천#1 T/L","26~27년 충북본부 직할 가공송전 협력회사 공사","26~27년 충북본부 직할 가공송전 협력회사 공사","2026-04-13 09:00","2026-04-15 18:00","2026-04-13 09:00","2026-04-13 18:00","매일"]
[385,"충북","직할","신진천문백#1 T/L","26-27년 충북직할 변전협력회사 공사","신진천S/S 신진천-문백#1T/L GIS 보통점검","2026-04-17 10:00","2026-04-17 18:00","2026-04-17 10:00","2026-04-17 18:00","당일"]
[386,"충북","직할","신진천S/S CB 6300","26-27년 충북직할 변전협력회사 공사","신진천S/S #62-67 BUSTIE GIS 보통점검","2026-04-23 10:00","2026-04-23 18:00","2026-04-23 10:00","2026-04-23 18:00","당일"]
[387,"충북","직할","신진천S/S SEC CB 61620","26-27년 충북직할 변전협력회사 공사","신진천S/S #61-62 SEC GIS 전자변 교체","2026-04-27 10:00","2026-04-27 18:00","2026-04-27 10:00","2026-04-27 18:00","당일"]
[388,"충북","직할","신진천S/S SEC CB 65660","26-27년 충북직할 변전협력회사 공사","신진천S/S #65-66SEC GIS 전자변 교체","2026-04-28 10:00","2026-04-28 14:00","2026-04-28 10:00","2026-04-28 14:00","당일"]
[389,"충북","직할","신진천S/S SEC CB 66670","26-27년 충북직할 변전협력회사 공사","신진천S/S #66-67 SEC GIS 전자변 교체","2026-04-28 14:00","2026-04-28 18:00","2026-04-28 14:00","2026-04-28 18:00","당일"]
[390,"충북","직할","신청주S/S #61 BUS","신청주S/S 신규수용 SW 증설공사","69, 6A Bay 61BUS 측 설치","2026-04-15 09:00","2026-04-25 18:00","2026-04-15 09:00","2026-04-25 18:00","연속"]
[391,"충북","직할","신청주S/S #60 BUS","신청주S/S 신규수용 SW 증설공사","64, 67Bay 60BUS 측 설치 공사","2026-04-27 09:00","2026-05-22 18:00","2026-04-27 09:00","2026-05-22 18:00","연속"]
[392,"충북","청주","남청주오송#1 T/L","2026~2027년도 청주전력지사 송전협력회사 총액공사","2026~2027년도 청주전력지사 송전협력회사 총액공사 고정형폴리머지지애자 설치 등","2026-04-01 07:00","2026-04-03 18:00","2026-04-01 07:00","2026-04-03 18:00","매일"]
[393,"충북","청주","남청주오송#2 T/L","'25-'26년 충북본부 지중송전 협력회사공사"," 남청주-오송 #2T/L 피뢰기 열화진단","2026-04-09 09:00","2026-04-09 18:00","취소","취소","당일"]
[394,"충북","충주","금왕남음성#2 T/L","26~27년 충북본부 직할 가공송전 협력회사 공사","26~27년 충북본부 직할 가공송전 협력회사 공사","2026-04-16 09:00","2026-04-17 18:00","취소","취소","매일"]
[395,"충북","충주","신제천영월CC#1 T/L","2026~2027년 충주전력지사 송전협력회사 공사"," 신제천-영월CC#1 T/L No.35-75 수평추락방지장치 설치","2026-04-27 07:00","2026-05-01 18:00","2026-04-27 07:00","2026-05-01 18:00","매일"]
[396,"충북","충주","제천영월#2 T/L","제천S/S 23kV GIS 장기사용 교체공사","제천S/S 제천-영월#2T/L GIS,보호반 제어케이블 이설(화)","2026-04-20 09:00","2026-04-21 18:00","2026-04-20 09:00","2026-04-21 18:00","연속"]
[397,"충북","충주","신제천제천#1 T/L","제천S/S 23kV GIS 교체공사","제천S/S 신제천-제천#1T/L 제어케이블 이설(화)","2026-04-01 09:00","2026-04-02 18:00","2026-04-01 09:00","2026-04-02 18:00","연속"]
[398,"충북","충주","신제천제천#2 T/L","제천S/S 23kV GIS 장기사용 교체공사","제천S/S 신제천-제천#2T/L GIS,보호반 제어케이블 이설","2026-04-06 09:00","2026-04-07 18:00","2026-04-06 09:00","2026-04-07 18:00","연속"]
[399,"충북","충주","제천영월#1 T/L","제천S/S 23kV 장기사용 GIS 교체공사","제천S/S 제천-영월#1T/L GIS,보호반 제어케이블 이설","2026-04-15 09:00","2026-04-16 18:00","취소","취소","연속"]
[400,"대전세종충남","대전","논산은진#1 T/L","[취소시][가압X]논산S/S 논산-은진#1T/L GIS 보통점검","[취소시][가압X]논산S/S 논산-은진#1T/L GIS 보통점검","2026-04-28 09:00","2026-04-28 18:00","2026-04-28 09:00","2026-04-28 18:00","당일"]
[401,"대전세종충남","대전","논산은진#2 T/L","[취소시][가압X]논산S/S 논산-은진#2T/L GIS 보통점검","[취소시][가압X]논산S/S 논산-은진#2T/L GIS 보통점검","2026-04-29 09:00","2026-04-29 18:00","2026-04-29 09:00","2026-04-29 18:00","당일"]
[402,"대전세종충남","대전","부여논산#1 T/L","[가압O]논산S/S 부여-논산#1T/L CB 개폐타임 측정","[가압O]논산S/S 부여-논산#1T/L CB 개폐타임 측정","2026-04-30 09:00","2026-04-30 14:00","2026-04-30 09:00","2026-04-30 14:00","당일"]
[403,"대전세종충남","대전","부여논산#2 T/L","[가압O]논산S/S 부여-논산#2T/L CB 개폐타임 측정","[가압O]논산S/S 부여-논산#2T/L CB 개폐타임 측정","2026-04-30 14:00","2026-04-30 18:00","2026-04-30 14:00","2026-04-30 18:00","당일"]
[404,"대전세종충남","대전","팔봉두마#2 T/L","[가압X]두마S/S 팔봉-두마#2T/L GIS 전자변 교체","[가압X]두마S/S 팔봉-두마#2T/L GIS 전자변 교체","2026-04-24 09:00","2026-04-24 18:00","취소","취소","당일"]
[405,"대전세종충남","대전","팔봉두마#1 T/L","[가압X]두마S/S 팔봉-두마#1T/L GIS 전자변 교체","[가압X]두마S/S 팔봉-두마#1T/L GIS 전자변 교체","2026-04-23 09:00","2026-04-23 18:00","취소","취소","당일"]
[406,"대전세종충남","대전","신옥천서대전 T/L","[송전] 신옥천-서대전T/L 정밀점검","[송전] 신옥천-서대전T/L 정밀점검","2026-04-06 07:00","2026-04-15 18:00","2026-04-06 07:00","2026-04-15 18:00","당일"]
[407,"대전세종충남","대전","신흥동대전#1 T/L","[가압X]신흥S/S 신흥-동대전#1T/L GIS 보통점검","[가압X]신흥S/S 신흥-동대전#1T/L GIS 보통점검","2026-04-08 09:00","2026-04-08 18:00","2026-04-08 09:00","2026-04-08 18:00","당일"]
[408,"대전세종충남","대전","신흥동대전#3 T/L","[가압O]신흥S/S 신흥-동대전#3T/L GIS 보통점검","[가압O]신흥S/S 신흥-동대전#3T/L GIS 보통점검","2026-04-10 09:00","2026-04-10 18:00","2026-04-10 09:00","2026-04-10 18:00","당일"]
[409,"대전세종충남","대전","신흥동대전#2 T/L","[가압X]신흥S/S 신흥-동대전#2T/L GIS 보통점검","[가압X]신흥S/S 신흥-동대전#2T/L GIS 보통점검","2026-04-09 09:00","2026-04-09 18:00","2026-04-09 09:00","2026-04-09 18:00","당일"]
[410,"대전세종충남","대전","신옥천유천 T/L","[가압O]유천S/S 신옥천-유천T/L GIS 보통점검","[가압O]유천S/S 신옥천-유천T/L GIS 보통점검","2026-04-17 09:00","2026-04-17 18:00","취소","취소","당일"]
[411,"대전세종충남","대전","신옥천유천 T/L","[송전] 신옥천-유천T/L 정밀점검","[송전] 신옥천-유천T/L 정밀점검","2026-04-16 07:00","2026-04-24 18:00","2026-04-16 07:00","2026-04-24 18:00","당일"]
[412,"대전세종충남","대전","신옥천추부#2 T/L","[가압X]추부S/S 신옥천-추부#2T/L GIS 보통점검","[가압X]추부S/S 신옥천-추부#2T/L GIS 보통점검","2026-04-07 09:00","2026-04-07 18:00","취소","취소","당일"]
[413,"대전세종충남","대전","신옥천추부#1 T/L","[가압X]추부S/S 신옥천-추부#1T/L GIS 보통점검","[가압X]추부S/S 신옥천-추부#1T/L GIS 보통점검","2026-04-06 09:00","2026-04-06 18:00","취소","취소","당일"]
[414,"대전세종충남","서산","당진T/P CB 6100","'26년 서산P/O 변전협력회사 총액공사","당진화력S/S 6100 GIS 보통점검","2026-04-16 09:00","2026-04-16 18:00","2026-04-16 09:00","2026-04-16 18:00","당일"]
[415,"대전세종충남","서산","대산대산복합#1 T/L","'26년 서산P/O 변전협력회사 총액공사","(고객일정협의완료) 대산S/S CGN대산전력#1T/L GIS 초기점검","2026-04-15 09:30","2026-04-15 18:00","2026-04-15 09:30","2026-04-15 18:00","당일"]
[416,"대전세종충남","서산","서산성연 T/L","26년 서산P/O GIS 보통, 정밀점검공사","(3월휴전 취소 시)서산S/S 서산-성연T/L GIS 보통점검 ※보조계전기 교체수량(60) - 휴전2일신청","2026-04-07 09:30","2026-04-08 18:00","2026-04-07 09:30","2026-04-08 18:00","연속"]
[417,"대전세종충남","서산","송악GSEPS#1 T/L","26년 서산P/O GIS 보통,정밀점검공사","(발전소일정협의완료) 송악S/S GSEPS#1T/L GIS 보통점검","2026-04-13 09:30","2026-04-13 18:00","2026-04-13 09:30","2026-04-13 18:00","당일"]
[418,"대전세종충남","서산","송악GSEPS#2 T/L","26년 서산P/O GIS 보통,정밀점검공사","(발전소일정협의완료) 송악S/S GSEPS#2T/L GIS 보통점검","2026-04-14 09:30","2026-04-14 18:00","2026-04-14 09:30","2026-04-14 18:00","당일"]
[419,"대전세종충남","서산","신당진S/S SEC CB 65660","'26-27년 서산P/O 변전협력회사 총액공사","(3월 휴전취소시)신당진S/S 65-66-0 SEC GIS 보통점검","2026-04-20 09:00","2026-04-20 18:00","2026-04-20 09:00","2026-04-20 18:00","당일"]
[420,"대전세종충남","서산","신당진S/S CB 6200","'26-27년 서산P/O 변전협력회사 총액공사","(3월휴전취소시)신당진S/S 6200 GIS 보통점검","2026-04-09 09:00","2026-04-09 18:00","2026-04-09 09:00","2026-04-09 18:00","당일"]
[421,"대전세종충남","서산","신당진서산#1 T/L"," 신당진-서산#1T/L OPGW 정비공사"," 신당진-서산#1T/L OPGW S/T~No.55 OPGW 교체","2026-04-14 09:00","2026-04-17 18:00","2026-04-14 09:00","2026-04-17 18:00","연속"]
[422,"대전세종충남","서산","신당진S/S SEC CB 60610","'26-27년 서산P/O 변전협력회사 총액공사","(3월휴전취소시)신당진S/S 60-61-0 SEC GIS 보통점검","2026-04-15 09:00","2026-04-15 18:00","2026-04-15 09:00","2026-04-15 18:00","당일"]
[423,"대전세종충남","서산","해미홍성 T/L","26년 서산P/O GIS 보통, 정밀점검공사","(3월휴전 취소 시)서산S/S 서산-홍성T/L GIS 정밀점검","2026-04-28 09:30","2026-04-30 18:00","2026-04-28 09:30","2026-04-30 18:00","연속"]
[424,"대전세종충남","세종","세종월산#1 T/L","[즉시가압O][주말작업X] 세종-월산T/L 불량애자 교체"," 세종-월산T/L 불량애자 교체","2026-04-06 07:00","2026-04-09 18:00","2026-04-06 07:00","2026-04-09 18:00","매일"]
[425,"대전세종충남","세종","세종월산#2 T/L","[즉시가압O][주말작업X] 세종-월산T/L 불량애자 교체"," 세종-월산T/L 불량애자 교체","2026-04-10 07:00","2026-04-14 18:00","2026-04-10 07:00","2026-04-14 18:00","매일"]
[426,"대전세종충남","세종","천안소정#1 T/L","[변전]26년 세종전력지사 변전협력회사 공사","소정S/S GIS 초기점검 - 천안-소정#1T/L GIS 초기점검","2026-04-02 10:00","2026-04-02 18:00","2026-04-02 10:00","2026-04-02 18:00","당일"]
[427,"대전세종충남","세종","소정전의#1 T/L","[즉시가압O][안전목적] 북오송-전의T/L 불량애자 교체"," 북오송-전의T/L 불량애자 교체","2026-04-15 07:00","2026-04-15 18:00","2026-04-15 07:00","2026-04-15 18:00","당일"]
[428,"대전세종충남","세종","소정전의#2 T/L","[즉시가압O][안전목적] 북오송-전의T/L 불량애자 교체"," 북오송-전의T/L 불량애자 교체","2026-04-28 07:00","2026-04-28 18:00","2026-04-28 07:00","2026-04-28 18:00","당일"]
[429,"대전세종충남","세종","서세종조치원 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보(No.14~16) - 서세종-조치원 (본선로 구성 : No.14~16)","2026-04-23 07:00","2026-04-27 18:00","2026-04-23 07:00","2026-04-27 18:00","연속"]
[430,"대전세종충남","세종","조치원월산 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보(No.14~16) - 조치원-월산 (본선로 구성 : No.14~16)","2026-04-18 07:00","2026-04-22 18:00","2026-04-18 07:00","2026-04-22 18:00","연속"]
[431,"대전세종충남","세종","조치원월산 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보(No.14~16) - 조치원-월산 (가선로 구성 : No.14~16)","2026-04-03 07:00","2026-04-04 18:00","2026-04-03 07:00","2026-04-04 18:00","연속"]
[432,"대전세종충남","세종","서세종조치원 T/L"," 조치원-월산T/L 안전이격거리확보공사","조치원-월산T/L 안전이격거리확보(No.14~16) - 서세종-조치원 (가선로 구성 : No.14~16)","2026-04-01 07:00","2026-04-02 18:00","2026-04-01 07:00","2026-04-02 18:00","연속"]
[433,"대전세종충남","직할","대덕둔산 T/L","26-27 직할 변전협력회사 총액공사","대덕S/S 대덕-둔산T/L 보통점검","2026-04-02 09:00","2026-04-02 18:00","취소","취소","당일"]
[434,"대전세종충남","직할","덕진대화#2 T/L","26년 직할 170kV GIS 정밀점검","대화S/S 덕진-대화#2 T/L GIS 정밀점검","2026-04-29 14:00","2026-05-01 18:00","2026-04-29 14:00","2026-05-01 18:00","연속"]
[435,"대전세종충남","직할","덕진대화#1 T/L","26년 직할 170kV GIS 정밀점검","대화S/S 덕진-대화#1 T/L GIS 정밀점검","2026-04-27 09:00","2026-04-29 14:00","2026-04-27 09:00","2026-04-29 14:00","연속"]
[436,"대전세종충남","직할","대덕둔지 T/L","26년 직할 170kV GIS 정밀점검","둔지S/S 대덕-둔지T/L GIS 정밀점검","2026-04-22 08:00","2026-04-24 14:00","2026-04-22 08:00","2026-04-24 14:00","연속"]
[437,"대전세종충남","직할","둔곡송강#2 T/L","(3월 취소시) 둔곡-송강#2T/L 추락방지장치 설치"," 둔곡-송강#2T/L 추락방지장치 설치공사","2026-04-06 09:00","2026-04-07 18:00","2026-04-06 09:00","2026-04-07 18:00","매일"]
[438,"대전세종충남","직할","둔곡송강#1 T/L","(3월 취소시) 둔곡-송강#1T/L 피뢰기 및 추락방지장치 설치"," 둔곡-송강#1T/L 피뢰기 설치 및 추락방지장치 설치공사","2026-04-01 09:00","2026-04-04 18:00","2026-04-01 09:00","2026-04-04 18:00","매일"]
[439,"대전세종충남","천안","둔포석곡#2 T/L","(즉시가압불가_3월취소시)둔포,석곡S/S 둔포-석곡#2T/L 보호반 교체","(즉시가압불가_3월취소시)둔포, 석곡S/S 둔포-석곡#2T/L 보호배전반 교체","2026-04-13 09:00","2026-04-16 18:00","취소","취소","연속"]
[440,"대전세종충남","천안","둔포석곡#1 T/L","(즉시가압불가_3월취소시)둔포,석곡S/S 둔포-석곡#1T/L 보호반 교체","(즉시가압불가_3월취소시)둔포, 석곡S/S 둔포-석곡#1T/L 보호배전반 교체","2026-04-20 09:00","2026-04-23 18:00","취소","취소","연속"]
[441,"대전세종충남","천안","장재불당#1 T/L","불당SS 장재불당#1TL 637CB 개폐타임측정,전자변 교체","불당S/S 장재-불당#1T/L 637CB 개폐타임측정 및 전자변 교체","2026-04-08 09:00","2026-04-08 18:00","2026-04-08 09:00","2026-04-08 18:00","당일"]
[442,"대전세종충남","천안","장재불당#2 T/L","불당SS 장재-불당#2TL 647CB 개폐타임측정,전자변 교체","불당SS 장재-불당#2TL 647CB 개폐타임측정, 전자변 교체","2026-04-09 09:00","2026-04-09 18:00","2026-04-09 09:00","2026-04-09 18:00","당일"]
[443,"대전세종충남","천안","서천안탕정#1 T/L","(즉시가압가능)서천안S/S 서천안-탕정#1TL DS 조작시험","서천안S/S 서천안-탕정#1T/L GIS DS 조작 시험","2026-04-07 09:00","2026-04-07 18:00","2026-04-07 09:00","2026-04-07 18:00","당일"]
[444,"대전세종충남","천안","신온양S/S #67 BUS"," 신온양S/S #1M.Tr 증설공사","- M.Tr(166.7MVA *3대) * 1Bank 설치 - GIS(362kV 6300A 63kA) * 2CB 설치 - GIS(170kV 2000A 50kA) * 1CCT 설치 - 기타 부대공사 * 1식","2026-04-27 09:00","2026-05-01 16:00","2026-04-27 09:00","2026-05-01 16:00","연속"]
[445,"대전세종충남","천안","신온양S/S #62 BUS"," 신온양S/S #1M.Tr 증설공사","- M.Tr(166.7MVA *3대) * 1Bank 설치 - GIS(362kV 6300A 63kA) * 2CB 설치 - GIS(170kV 2000A 50kA) * 1CCT 설치 - 기타 부대공사 * 1식","2026-04-20 09:00","2026-04-24 16:00","2026-04-20 09:00","2026-04-24 16:00","연속"]
[446,"대전세종충남","천안","신온양한샘#2 T/L"," 신온양S/S #1M.Tr 증설공사","- 모선 무부하 가압","2026-04-23 16:00","2026-04-24 16:00","2026-04-23 16:00","2026-04-24 16:00","연속"]
[447,"대전세종충남","천안","신온양한샘#2 T/L"," 신온양S/S #1M.Tr 증설공사","- 모선 무부하 가압","2026-04-30 16:00","2026-05-01 16:00","2026-04-30 16:00","2026-05-01 16:00","연속"]
[448,"대전세종충남","천안","신탕정탕정#1 T/L","(즉시가압불가_3월취소시)신탕정SS 신탕정탕정1TL 보호반대체","신탕정S/S 신탕정-탕정#1T/L 보호반대체","2026-04-01 09:00","2026-04-03 18:00","2026-04-01 09:00","2026-04-03 18:00","연속"]
[449,"대전세종충남","천안","신탕정탕정#2 T/L","(즉시가압X_3월취소시)신탕정SS 신탕정-탕정2TL 보호반대체","신탕정S/S 신탕정-탕정#2T/L 보호반대체","2026-04-06 09:00","2026-04-08 18:00","2026-04-06 09:00","2026-04-08 18:00","연속"]
[450,"대전세종충남","천안","아산온양#1 T/L","(즉시가압가능_3월취소시)아산SS 아산온양1TL GIS보통점검","아산S/S 아산-온양#1T/L GIS 보통점검","2026-04-01 09:00","2026-04-01 18:00","2026-04-01 09:00","2026-04-01 18:00","당일"]
[451,"대전세종충남","천안","아산온양#2 T/L","(즉시가압O_3월취소시)아산SS 아산온양2TL GIS보통점검","아산S/S 아산-온양#2T/L GIS 보통점검","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[452,"대전세종충남","천안","아산예산#2 T/L","(즉시가압불가)아산, 예산S/S #2T/L 보호배전반 교체","(즉시가압불가)아산, 예산S/S #2T/L 보호배전반 교체","2026-04-13 09:00","2026-04-16 18:00","취소","취소","연속"]
[453,"대전세종충남","천안","아산예산#1 T/L","(즉시가압불가)아산, 예산S/S #1T/L 보호배전반 교체","(즉시가압불가)아산, 예산S/S #1T/L 보호배전반 교체","2026-04-06 09:00","2026-04-09 18:00","취소","취소","연속"]
[454,"대전세종충남","천안","아산온양#2 T/L","[송전] 아산-온양T/L 안전이격확보공사","○ 철탑상향 인클로징 : 1기[No.40 (A2-24 → A2-35)] ○ 전선이동 : STACIR 410㎟ × 1S × 2C(전력선 재사용) ○ 가공지선 : OPGW 100㎟ × 1조(전자제어파트 시행) ○ 기타 부대공사","2026-04-04 07:00","2026-04-05 18:00","2026-04-04 07:00","2026-04-05 18:00","연속"]
[455,"대전세종충남","천안","아산온양#1 T/L","[송전] 아산-온양T/L 안전이격확보공사","○ 철탑상향 인클로징 : 1기[No.40 (A2-24 → A2-35) ○ 전선이동 : STACIR 410㎟ × 1S × 2C(전력선 재사용) ○ 가공지선 : OPGW 100㎟ × 1조(전자제어파트 시행) ○ 기타 부대공사","2026-04-11 07:00","2026-04-12 18:00","2026-04-11 07:00","2026-04-12 18:00","연속"]
[456,"대전세종충남","천안","아산인주#1 T/L","인주S/S 아산-인주#1T/L 617CB 개폐타임측정","인주S/S 아산-인주#1T/L 617CB 개폐타임측정","2026-04-17 09:00","2026-04-17 18:00","2026-04-17 09:00","2026-04-17 18:00","당일"]
[457,"대전세종충남","천안","장재천안#1 T/L","(즉시가압불가_3월취소시)장재, 천안S/S #1T/L 보호배전반 교체","(즉시가압불가_3월취소시)장재, 천안S/S #1T/L 보호배전반 교체","2026-04-27 09:00","2026-04-30 18:00","2026-04-27 09:00","2026-04-30 18:00","연속"]
[458,"대전세종충남","천안","서천안탕정#1 T/L","탕정S/S 서천안-탕정#1T/L 657CB 개폐타임측정","탕정S/S 서천안-탕정#1T/L 657CB 개폐타임측정","2026-04-10 09:00","2026-04-10 18:00","2026-04-10 09:00","2026-04-10 18:00","당일"]
[459,"대전세종충남","청양","관창대천#2 T/L","[3월취소시][변전총액] 청양P/O 변전협력 총액공사","[변전총액]관창SS : 170kV GIS 전자변교체","2026-04-28 09:00","2026-04-28 18:00","2026-04-28 09:00","2026-04-28 18:00","당일"]
[460,"대전세종충남","청양","신서천대천#1 T/L","[병가]상단 옥산-서천#1No2~44, 하단 대천-서천#1No2~44"," 대천-서천#1 T/L 정밀점검 병가구간 상단 옥산-서천 #1 T/L No2~44 하단 대천-서천 #1 T/L No2~44","2026-04-24 08:00","2026-05-06 18:00","2026-04-24 08:00","2026-05-06 18:00","매일"]
[461,"대전세종충남","청양","옥산장항#2 T/L","[병가]상단 옥산-서천#1T/L,하단 옥산-장항#2T/L 정밀"," 옥산-장항#2T/L 정밀점검 옥산-서천#1T/L No.90~91 옥산-장항#2T/L No.1~2","2026-04-17 08:00","2026-04-23 18:00","취소","취소","매일"]
[462,"대전세종충남","청양","옥산부여#1 T/L","[변전총액] 청양P/O 변전협력 총액공사","[변전총액] 옥산SS : 170kV GIS 전자변교체 부여SS : 170kV GIS 보통점검","2026-04-09 09:00","2026-04-09 18:00","2026-04-09 09:00","2026-04-09 18:00","당일"]
[463,"대전세종충남","청양","옥산부여#2 T/L","[변전총액] 청양P/O 변전협력 총액공사","[변전총액]옥산SS : 170kV GIS 전자변교체","2026-04-10 09:00","2026-04-10 18:00","2026-04-10 09:00","2026-04-10 18:00","당일"]
[464,"대전세종충남","청양","옥산장항#1 T/L","[송전][주말작업X] 옥산-장항#1T/L 수평추락방지장치 설치","우상단 : 옥산-장항#1 우하단 : 동군산-장항#2 병가구간 수평추락방지장치 설치","2026-04-01 07:30","2026-04-02 18:00","취소","취소","매일"]
[465,"대전세종충남","청양","신서천옥산#1 T/L","[변전총액] 청양P/O 변전협력 총액공사","[변전총액]옥산SS : 170kV GIS 보통점검, LA대체 서천SS : 170kV GIS 보통점검","2026-04-30 09:00","2026-04-30 18:00","2026-04-30 09:00","2026-04-30 18:00","당일"]
[466,"대전세종충남","청양","신서천옥산#1 T/L","[송전][즉시가압O] 옥산-서천#1T/L 정밀점검"," 옥산-서천#1T/L 정밀점검","2026-04-22 08:00","2026-05-01 18:00","2026-04-22 08:00","2026-05-01 18:00","매일"]
[467,"대전세종충남","청양","동군산장항#2 T/L","[송전][주말작업X] 동군산-장항#2T/L 수평추락방지장치 설치","우상단 : 옥산-장항#1 우하단 : 동군산-장항#2 병가구간 수평추락방지장치 설치","2026-04-01 07:30","2026-04-02 18:00","취소","취소","매일"]
[468,"대전세종충남","청양","동군산장항#1 T/L","[송전][주말작업X] 동군산-장항#1T/L 수평추락방지장치 설치","좌상단 : 옥산-장항#2 좌하단 : 동군산-장항#1 병가구간 수평추락방지장치 설치","2026-04-17 07:30","2026-04-21 18:00","취소","취소","매일"]
[469,"대전세종충남","청양","청양S/S #60 BUS","청양S/S #1M.Tr 교체 및 3차측 현대화공사","#1M.Tr 교체 및 3차측 현대화 -옥외철구 설비 철거 - #1M.Tr 교체(예비변압기 포함) - 3차측 GIS 설치(GPT 둥) - M.Tr 상시험","2026-04-27 14:00","2026-04-27 18:00","2026-04-27 14:00","2026-04-27 18:00","연속"]
[470,"전북","군산","군산영등#2 T/L","군산P/O 170kV 차단기 보통점검","군산S/S 군산-영등 #2T/L 170kV 차단기 보통점검","2026-04-17 16:00","2026-04-17 20:00","취소","취소","당일"]
[471,"전북","군산","함열낭산#2 T/L","군산P/O 170kV 차단기 보통점검","낭산S/S 낭산-함열 #2T/L 170kV 차단기 보통점검","2026-04-14 16:00","2026-04-14 20:00","2026-04-14 16:00","2026-04-14 20:00","당일"]
[472,"전북","군산","함열낭산#1 T/L","군산P/O 170kV 차단기 보통점검","낭산S/S 낭산-함열 #1T/L 170kV 차단기 보통점검","2026-04-13 16:00","2026-04-13 20:00","2026-04-13 16:00","2026-04-13 20:00","당일"]
[473,"전북","군산","영등낭산#1 T/L","군산P/O 170kV 차단기 보통점검","낭산S/S 영등-낭산 #1T/L 170kV 차단기 보통점검","2026-04-15 16:00","2026-04-15 20:00","2026-04-15 16:00","2026-04-15 20:00","당일"]
[474,"전북","군산","영등낭산#2 T/L","군산P/O 170kV 차단기 보통점검","낭산S/S 영등-낭산 #2T/L 170kV 차단기 보통점검","2026-04-16 16:00","2026-04-16 20:00","2026-04-16 16:00","2026-04-16 20:00","당일"]
[475,"전북","군산","비응동비응#1 T/L"," 동비응S/S 건설공사 사용전검사"," 동비응S/S 건설공사 사용전검사 관련 기기조작","2026-04-09 09:00","2026-04-15 18:00","2026-04-09 09:00","2026-04-15 18:00","연속"]
[476,"전북","군산","비응동비응#2 T/L"," 동비응S/S 건설공사 사용전검사"," 동비응S/S 건설공사 사용전검사 관련 기기조작","2026-04-09 09:00","2026-04-15 18:00","2026-04-09 09:00","2026-04-15 18:00","연속"]
[477,"전북","군산","서군산소룡#1 T/L","군산P/O 170kV 차단기 정밀점검","소룡S/S 서군산-소룡 #1T/L 170kV 차단기 정밀점검","2026-04-08 09:00","2026-04-09 18:00","취소","취소","연속"]
[478,"전북","군산","서군산소룡#2 T/L","군산P/O 170kV 차단기 정밀점검","소룡S/S 서군산-소룡 #2T/L 170kV 차단기 정밀점검","2026-04-13 09:00","2026-04-14 18:00","취소","취소","연속"]
[479,"전북","군산","군산이리#1 T/L","군산P/O 170kV 차단기 정밀점검","이리S/S 군산-이리 #1T/L 170kV 차단기 정밀점검","2026-04-15 09:00","2026-04-16 18:00","취소","취소","연속"]
[480,"전북","군산","군산이리#2 T/L","군산P/O 170kV 차단기 정밀점검","이리S/S 군산-이리 #2T/L 170kV 차단기 정밀점검","2026-04-20 09:00","2026-04-21 18:00","취소","취소","연속"]
[481,"전북","군산","팔봉왕궁#1 T/L","동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사(전월신청분)","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-04-29 16:00","2026-04-29 20:00","2026-04-29 16:00","2026-04-29 20:00","매일"]
[482,"전북","군산","팔봉왕궁#2 T/L","동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사(전월신청분)","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-04-30 16:00","2026-04-30 20:00","2026-04-30 16:00","2026-04-30 20:00","매일"]
[483,"전북","김제","소성고창#1 T/L"," 고창S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2026-04-06 16:00","2026-04-06 23:00","2026-04-06 16:00","2026-04-06 23:00","당일"]
[484,"전북","김제","소성고창#2 T/L"," 고창S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2026-04-07 16:00","2026-04-07 23:00","2026-04-07 16:00","2026-04-07 23:00","당일"]
[485,"전북","김제","고창서홍농개폐소 T/L"," 고창S/S 혼용운영시스템 설치공사","- 혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] - 이설 후 SCADA 연동시험 시행","2026-04-02 16:00","2026-04-02 23:00","2026-04-02 16:00","2026-04-02 23:00","당일"]
[486,"전북","김제","고창영광 T/L"," 고창S/S 혼용운영시스템 설치공사","혼용화 관련 제어케이블 이설 [RTU↔GIS]☞[LID↔GIS] 이설 후 SCADA 연동시험 시행","2026-04-03 16:00","2026-04-03 23:00","2026-04-03 16:00","2026-04-03 23:00","당일"]
[487,"전북","김제","백산김제#2 T/L","동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사(전월신청분)","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-04-28 16:00","2026-04-28 20:00","2026-04-28 16:00","2026-04-28 20:00","매일"]
[488,"전북","김제","백산김제#1 T/L","동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사(전월신청분)","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-04-27 16:00","2026-04-27 20:00","2026-04-27 16:00","2026-04-27 20:00","매일"]
[489,"전북","김제","남전주임실#2 T/L"," 북임실S/S 및 분기T/L 건설공사(재생e 변전소)","(변전) 보호반 이설, 대국시험, 무부하 가압, 실부하가압 (송전) 변전소 인입, 전선이동, 인수점검 등 (통신) OPGW 신설, 이설 및 광손실 시험 등","2026-04-20 09:00","2026-04-30 18:00","취소","취소","연속"]
[490,"전북","김제","김제부안#2 T/L","부안S/S 모선구분차단기 설치(6200)","부안S/S 모선구분차단기 설치공사 - BUS SEC 2CCT 설치 - BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2026-04-07 09:00","2026-04-15 18:00","취소","취소","연속"]
[491,"전북","김제","김제부안#1 T/L","부안S/S 모선구분차단기 설치(PT)","부안S/S 모선구분차단기 설치공사 - BUS SEC 2CCT 설치 - BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2026-04-16 09:00","2026-04-24 18:00","취소","취소","연속"]
[492,"전북","김제","김제부안#1 T/L","부안S/S 모선구분차단기 설치(B/S)-무부하가압","부안S/S 모선구분차단기 설치공사 - BUS SEC 2CCT 설치 - BUS-TIE 1CCT 설치 - #61-66 모선 보호IED반 설치 - 기타부대공사 1식","2026-04-30 16:00","2026-05-01 16:00","취소","취소","연속"]
[493,"전북","직할","무주용담수력 T/L"," 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치(북전주-진안T/L No.50~104, 무주분기T/L No.1~45) - 북전주-진안T/L No.50~104 - 무주분기T/L No.1~45","2026-04-01 07:30","2026-04-06 18:00","취소","취소","연속"]
[494,"전북","직할","왕궁봉동#1 T/L","동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사(전월신청분)","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-04-06 16:00","2026-04-06 20:00","2026-04-06 16:00","2026-04-06 20:00","매일"]
[495,"전북","직할","북전주봉동#1 T/L","동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사(전월신청분)","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-04-02 16:00","2026-04-02 20:00","2026-04-02 16:00","2026-04-02 20:00","매일"]
[496,"전북","직할","왕궁봉동#2 T/L","동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사(전월신청분)","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-04-07 16:00","2026-04-07 20:00","2026-04-07 16:00","2026-04-07 20:00","매일"]
[497,"전북","직할","북전주봉동#2 T/L","동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사(전월신청분)","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-04-03 16:00","2026-04-03 20:00","2026-04-03 16:00","2026-04-03 20:00","매일"]
[498,"전북","직할","북전주용담수력 T/L"," 신남원-신광주 등 5개T/L 수평 추락방지시설 설치공사(계속)","○ 수평 추락방지시설 설치 : No.1~50","2026-04-07 07:30","2026-04-10 18:00","취소","취소","연속"]
[499,"전북","직할","장수S/S #2 BUS","장수S/S 모선구분 차단기 및 신장수 연계 GIS 설치공사"," 65-66 BUS SEC, 6202 DS 설치","2026-04-06 09:00","2026-04-16 08:00","2026-04-06 09:00","2026-04-16 08:00","연속"]
[500,"전북","직할","장수S/S #66 BUS","장수S/S 모선구분 차단기 및 신장수 연계 GIS 설치공사","65-66 BUS SEC 무부하가압 환원 후 이어서 휴전 시행 신장수S/S #2M.Tr 2차 GIS 설치(6244)","2026-04-16 08:00","2026-04-19 18:00","2026-04-16 08:00","2026-04-19 18:00","연속"]
[501,"전북","직할","진안장수#2 T/L","장수S/S 모선구분차단기 및 신장수S/S 연계GIS 설치","장수S/S 65-66 BUS SEC 설치 완료 후 무부하가압 시행 (즉시가압가능)","2026-04-15 08:00","2026-04-16 08:00","2026-04-15 08:00","2026-04-16 08:00","연속"]
[502,"전북","직할","진안장수#2 T/L","장수S/S 모선구분차단기 및 신장수S/S 연계GIS 설치","신장수S/S #2M.Tr 2차 GIS의 [2DS,2BUS] 설치 후 무부하가압 시행 (즉시가압가능)","2026-04-18 13:00","2026-04-19 13:00","2026-04-18 13:00","2026-04-19 13:00","연속"]
[503,"전북","직할","장수S/S #1 BUS","장수S/S 모선구분 차단기 및 신장수 연계 GIS 설치공사"," 60-61 BUS SEC, 6200 BUS TIE 설치","2026-04-20 09:00","2026-05-02 08:00","2026-04-20 09:00","2026-05-02 08:00","연속"]
[504,"전북","직할","전주서곡#1 T/L","동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사(전월신청분)","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-04-20 08:00","2026-04-21 18:00","취소","취소","매일"]
[505,"전북","직할","신김제전주#2 T/L","전주S/S 신김제전주#2 T/L GIS 보통점검","전주S/S 신김제전주#2 T/L GIS 보통점검","2026-04-09 09:00","2026-04-09 18:00","취소","취소","당일"]
[506,"전북","직할","탄소전주#2 T/L","전주S/S 탄소-전주#2 T/L GIS 보통점검","전주S/S 탄소-전주#2 T/L GIS 보통점검","2026-04-08 16:00","2026-04-08 20:00","취소","취소","당일"]
[507,"전북","직할","전주서곡#2 T/L","동전주-태평 등 10개T/L EBG 가스채취밸브 설치공사(전월신청분)","□ 내용 : 대한전선제 열경화공법 적용 EBG 가스채취밸브 설치","2026-04-22 08:00","2026-04-23 18:00","취소","취소","매일"]
[508,"전북","직할","무주진안 T/L"," 무주분기T/L No.23~24 항공장애표시구 교체공사","○ 무주분기T/L No.23~24 항공장애표시구 교체공사","2026-04-01 16:00","2026-04-01 19:00","2026-04-01 16:00","2026-04-01 19:00","당일"]
[509,"전북","직할","동전주태평#1 T/L","26년 전북직할 이상 차단기 정기검사","태평S/S 동전주-태평 #1T/L 초기점검","2026-04-10 09:00","2026-04-10 18:00","2026-04-10 09:00","2026-04-10 18:00","당일"]
[510,"전북","직할","동전주태평#2 T/L","26년 전북직할 이상 차단기 정기검사","태평S/S 동전주-태평 #2T/L 초기점검","2026-04-17 09:00","2026-04-17 18:00","2026-04-17 09:00","2026-04-17 18:00","당일"]
[511,"광주전남","강진","강진장흥#2 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","① 강진장흥#2T/L 피뢰기 설치(1~59호) ② 금정-강진#1, 장흥-벌교 휴전작업에 따른 안전이격 병행휴전 ※ 1시간 이내 즉시가압 가능","2026-04-22 07:00","2026-04-30 18:00","2026-04-22 07:00","2026-04-30 18:00","매일"]
[512,"광주전남","강진","금정강진#1 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","① 금정-강진#1T/L 피뢰기 설치(16~21,50,51호) ② 강진-장흥#2 휴전작업에 따른 안전이격 병행휴전 ※ 1시간 이내 즉시가압 가능","2026-04-29 07:00","2026-04-30 18:00","취소","취소","매일"]
[513,"광주전남","강진","남창해남CS#1 T/L","2026년 가공송전 순시점검 위탁공사","남창-해남CS#1T/L 정밀점검","2026-04-13 09:00","2026-04-16 18:00","2026-04-13 09:00","2026-04-16 18:00","매일"]
[514,"광주전남","강진","남창해남CS#2 T/L","남창S/S 남창-해남C/S T/L 인출변경 공사","- 남창S/S 남창-해남C/S T/L 인출변경","2026-04-17 09:00","2026-04-19 15:00","2026-04-17 09:00","2026-04-19 15:00","연속"]
[515,"광주전남","강진","남창해남CS#1 T/L","남창S/S 남창-해남C/S T/L 인출변경 공사","- 남창S/S 남창-해남C/S T/L 인출변경","2026-04-19 07:00","2026-04-23 15:00","취소","취소","연속"]
[516,"광주전남","강진","남창해남CS#2 T/L","2026년 가공송전 순시점검 위탁공사","남창-해남CS#2T/L 정밀점검","2026-04-20 09:00","2026-04-23 18:00","취소","취소","매일"]
[517,"광주전남","강진","남창모선연계 T/L","남창S/S 남창-해남C/S T/L 인출변경 공사","- 남창S/S 남창-해남C/S T/L 인출변경","2026-04-19 07:00","2026-04-23 15:00","취소","취소","연속"]
[518,"광주전남","강진","대불삼호#2 T/L","'26~27 강진전력지사 변전협력회사 공사","1. 대불S/S 대불-삼호 #2T/L GIS CB 조작시험","2026-04-01 09:00","2026-04-01 18:00","2026-04-01 09:00","2026-04-01 18:00","당일"]
[519,"광주전남","강진","보성벌교 T/L"," 보성-벌교T/L 안전이격확보 휴전","ㅇ 대상선로 : 보성-벌교T/L 1~2호 ㅇ 공사내용 : 송전선로 직하 보성군 생활폐기물 소각시설 설치사업 관련으로 중장비(크레인 등) 사용을 위한 안전이격확보 휴전","2026-04-06 07:00","2026-04-10 11:00","2026-04-06 06:30","2026-04-10 09:30","매일"]
[520,"광주전남","강진","보성벌교 T/L","2026~2027년 강진전력지사 송전협력회사 공사","클램프, 점퍼소켓 교체","2026-04-24 07:00","2026-05-01 18:00","취소","취소","매일"]
[521,"광주전남","강진","장흥보성 T/L","2026~2027년 강진전력지사 송전협력회사 공사","클램프, 점퍼소켓 교체","2026-04-10 07:00","2026-04-14 18:00","취소","취소","매일"]
[522,"광주전남","강진","보성벌교 T/L"," 보성-벌교T/L 안전이격확보 휴전","ㅇ 대상선로 : 보성-벌교T/L 1~2호 ㅇ 공사내용 : 송전선로 직하 보성군 생활폐기물 소각시설 설치사업 관련으로 중장비(크레인 등) 사용을 위한 안전이격확보 휴전","2026-04-20 07:00","2026-04-24 11:00","2026-04-20 06:30","2026-04-24 09:30","매일"]
[523,"광주전남","강진","신강진대불#1 T/L","2026~2027년 강진전력지사 송전협력회사 공사","가공지선 교체","2026-04-22 07:00","2026-04-23 18:00","취소","취소","매일"]
[524,"광주전남","강진","남창완도CS T/L","2026년 가공송전 순시점검 위탁공사","남창-완도CST/L 초기점검","2026-04-16 09:00","2026-04-16 18:00","취소","취소","당일"]
[525,"광주전남","강진","완도완도CS T/L","2026년 가공송전 순시점검 위탁공사","완도-완도CST/L 초기점검","2026-04-17 09:00","2026-04-17 18:00","취소","취소","당일"]
[526,"광주전남","강진","장흥벌교 T/L"," 장흥-벌교 등 5개T/L 피뢰기 및 추락방지장치 설치공사","① 장흥-벌교T/L 피뢰기 설치 (1~50, 71~90호) ② 강진-장흥#2 휴전작업에 따른 안전이격 병행휴전 ※ 1시간 이내 즉시가압 가능","2026-04-15 07:00","2026-04-23 18:00","취소","취소","매일"]
[527,"광주전남","강진","화원진도#2 T/L","'26~27 강진전력지사 변전협력회사 공사","1. 진도S/S 화원-진도 #2T/L GIS CB 조작시험","2026-04-02 14:00","2026-04-02 18:00","취소","취소","당일"]
[528,"광주전남","강진","해남진도#1 T/L","'26~27 강진전력지사 변전협력회사 공사","1. 진도S/S 해남-진도 #1T/L GIS 보통점검","2026-04-08 10:00","2026-04-08 18:00","취소","취소","당일"]
[529,"광주전남","강진","해남진도#2 T/L","'26~27 강진전력지사 변전협력회사 공사","1. 진도S/S 해남-진도 #2T/L GIS 보통점검","2026-04-09 10:00","2026-04-09 18:00","취소","취소","당일"]
[530,"광주전남","강진","화원진도#1 T/L","2026~2027년 강진전력지사 송전협력회사 공사","민원으로 인한 저소음 항공장애구 설치","2026-04-20 07:00","2026-04-20 18:00","취소","취소","당일"]
[531,"광주전남","강진","화원진도#1 T/L","'26~27 강진전력지사 변전협력회사 공사","1. 진도S/S 화원-진도 #1T/L GIS CB 조작시험","2026-04-02 10:00","2026-04-02 14:00","취소","취소","당일"]
[532,"광주전남","강진","화원진도#2 T/L","2026~2027년 강진전력지사 송전협력회사 공사","민원으로 인한 저소음 항공장애구 교체 (#2 OPGW 기존 항공구 철거 후 저소음 설치)","2026-04-21 07:00","2026-04-21 18:00","취소","취소","당일"]
[533,"광주전남","강진","해남해남CS#1 T/L","2026년 가공송전 순시점검 위탁공사","해남-해남CS#1T/L 정밀점검","2026-04-06 09:00","2026-04-15 18:00","2026-04-06 09:00","2026-04-15 18:00","매일"]
[534,"광주전남","강진","신강진해남#1 T/L","'26~27 강진전력지사 변전협력회사 공사","1. 해남S/S 신강진-해남 #1T/L GIS CB 조작시험","2026-04-10 10:00","2026-04-10 14:00","취소","취소","당일"]
[535,"광주전남","강진","해남해남CS#2 T/L","2026년 가공송전 순시점검 위탁공사","해남-해남CS#2T/L 정밀점검","2026-04-20 09:00","2026-04-29 18:00","2026-04-20 09:00","2026-04-29 18:00","매일"]
[536,"광주전남","강진","신강진해남#2 T/L","'26~27 강진전력지사 변전협력회사 공사","1. 해남S/S 신강진-해남 #2T/L GIS CB 조작시험","2026-04-10 14:00","2026-04-10 18:00","취소","취소","당일"]
[537,"광주전남","강진","화원안좌#2 T/L","26~27년 강진전력지사 변전협력회사 공사","- 화원-안좌#2T/L 보호반 대체","2026-04-13 09:00","2026-04-15 18:00","2026-04-13 09:00","2026-04-15 18:00","연속"]
[538,"광주전남","강진","화원안좌#1 T/L","26~27년 강진전력지사 변전협력회사 공사","- 화원-안좌#1T/L 보호반 대체","2026-04-06 09:00","2026-04-08 18:00","2026-04-06 09:00","2026-04-08 18:00","연속"]
[539,"광주전남","광주","계림S/S CB 6100"," 남광주C/T 이설공사(남광주-계림T/L 상체크 무부하)","○ 남광주-계림T/L 이설 후 상체크 및 무부하 가압을 하기 위함 - 남광주S/S ,계림S/S #1 BUS 휴전(#1BUS 부하 전환) → 남광주S/S,계림S/S, 6100 TIE CB 개방 및 단로기 개방 - 남광주S/S 남광주-화순#1T/L #1BUS로 절체 및 가압 - 상체크 후 계림S/S 657 개방 및 부하 원복 후 24시간 무부하 가압","2026-04-23 12:00","2026-04-24 18:00","2026-04-23 12:00","2026-04-24 18:00","연속"]
[540,"광주전남","광주","계림S/S #66 BUS","계림S/S 장기사용 GIS 교체(Digital화)공사","○ 170kV GIS × 16CCT 교체","2026-04-17 18:00","2026-04-20 07:00","취소","취소","연속"]
[541,"광주전남","광주","계림S/S #66 BUS","계림S/S 장기사용 GIS 교체(Digital화)공사","○ 170kV GIS × 16CCT 교체","2026-04-10 18:00","2026-04-10 21:00","취소","취소","당일"]
[542,"광주전남","광주","계림S/S #61 BUS","계림S/S 장기사용 GIS 교체(Digital화)공사","○ 170kV GIS × 16CCT 교체","2026-04-10 21:00","2026-04-13 07:00","취소","취소","연속"]
[543,"광주전남","광주","북광주계림#2 T/L","계림S/S 장기사용 GIS 교체(Digital화)공사","○ 170kV GIS × 16CCT 교체","2026-04-19 19:00","2026-04-20 07:00","취소","취소","연속"]
[544,"광주전남","광주","계림S/S SEC CB 61600"," 남광주C/T 이설공사(남광주-계림T/L 상체크 무부하)","○ 남광주-계림T/L 이설 후 상체크 및 무부하 가압을 하기 위함 - 남광주S/S ,계림S/S #1 BUS 휴전(#1BUS 부하 전환) → 남광주S/S,계림S/S, 6100 TIE CB 개방 및 단로기 개방 - 남광주S/S 남광주-화순#1T/L #1BUS로 절체 및 가압 - 상체크 후 계림S/S 657 개방 및 부하 원복 후 24시간 무부하 가압","2026-04-23 12:00","2026-04-24 18:00","취소","취소","연속"]
[545,"광주전남","광주","계림S/S CB 6200","계림S/S 장기사용 GIS 교체(Digital화)공사","○ 170kV GIS × 16CCT 교체","2026-04-10 09:00","2026-04-26 18:00","취소","취소","연속"]
[546,"광주전남","광주","신광주계림#1 T/L","계림S/S 장기사용 GIS 교체(Digital화)공사","○ 170kV GIS × 16CCT 교체 안전이격거리","2026-04-10 18:00","2026-04-10 21:00","취소","취소","당일"]
[547,"광주전남","광주","북광주계림#2 T/L","계림S/S 장기사용 GIS 교체(Digital화)공사","○ 170kV GIS × 16CCT 교체","2026-04-12 19:00","2026-04-13 07:00","취소","취소","연속"]
[548,"광주전남","광주","계림S/S #60 BUS"," 남광주C/T 이설공사(남광주-계림T/L 상체크 무부하)","○ 남광주-계림T/L 이설 후 상체크 및 무부하 가압을 하기 위함 - 남광주S/S ,계림S/S #1 BUS 휴전(#1BUS 부하 전환) → 남광주S/S,계림S/S, 6100 TIE CB 개방 및 단로기 개방 - 남광주S/S 남광주-화순#1T/L #1BUS로 절체 및 가압 - 상체크 후 계림S/S 657 개방 및 부하 원복 후 24시간 무부하 가압","2026-04-23 12:00","2026-04-24 18:00","취소","취소","연속"]
[549,"광주전남","광주","계림S/S SEC CB 66650"," 남광주C/T 이설공사(남광주-계림T/L 상체크 무부하)","○ 남광주-계림T/L 이설 후 상체크 및 무부하 가압을 하기 위함 - 남광주S/S ,계림S/S #1 BUS 휴전(#1BUS 부하 전환) → 남광주S/S,계림S/S, 6100 TIE CB 개방 및 단로기 개방 - 남광주S/S 남광주-화순#1T/L #1BUS로 절체 및 가압 - 상체크 후 계림S/S 657 개방 및 부하 원복 후 24시간 무부하 가압","2026-04-23 12:00","2026-04-24 18:00","취소","취소","연속"]
[550,"광주전남","광주","계림S/S SEC CB 66650","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2026-04-15 09:00","2026-04-17 18:00","취소","취소","연속"]
[551,"광주전남","광주","계림S/S SEC CB 61600","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2026-04-13 09:00","2026-04-15 18:00","취소","취소","연속"]
[552,"광주전남","광주","계림S/S CB 6100","25년 광주전력지사 변전협력회사 총액공사","- 60-65 모선보호반 대체","2026-04-13 09:00","2026-04-17 18:00","취소","취소","연속"]
[553,"광주전남","광주","순창곡성#1 T/L","2026년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 시행 - 순창-곡성#1T/L 2~41호 (40기)","2026-04-20 08:00","2026-04-22 18:00","2026-04-20 08:00","2026-04-22 18:00","매일"]
[554,"광주전남","광주","곡성남원#1 T/L","2026년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 시행 - 곡성-남원 #1T/L 2~15호(순창-곡성 T/L 병가선로)","2026-04-22 08:00","2026-04-22 18:00","2026-04-22 08:00","2026-04-22 18:00","매일"]
[555,"광주전남","광주","순창곡성#2 T/L","2026년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 피뢰기 갭혼교체 시행 - 순창-곡성#2T/L 2~41호 (40기)","2026-04-23 08:00","2026-04-27 18:00","2026-04-23 08:00","2026-04-27 18:00","매일"]
[556,"광주전남","광주","곡성남원#2 T/L","2026년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 피뢰기 갭혼교체 시행 - 곡성-남원#2T/L 2~15호 ( 순창-곡성T/L 병가선로)","2026-04-27 08:00","2026-04-27 18:00","2026-04-27 08:00","2026-04-27 18:00","매일"]
[557,"광주전남","광주","남광주소태 T/L"," 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2026-04-07 09:00","2026-04-15 18:00","2026-04-07 09:00","2026-04-15 18:00","연속"]
[558,"광주전남","광주","남광주소태 T/L","(안전이격) 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2026-04-16 09:00","2026-04-19 18:00","2026-04-16 09:00","2026-04-19 18:00","매일"]
[559,"광주전남","광주","남광주화순#2 T/L","(안전이격) 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2026-04-26 09:00","2026-04-30 18:00","2026-04-26 09:00","2026-04-30 18:00","매일"]
[560,"광주전남","광주","계림남광주 T/L","(안전이격) 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2026-04-11 09:00","2026-04-14 18:00","2026-04-11 09:00","2026-04-14 18:00","매일"]
[561,"광주전남","광주","계림남광주 T/L"," 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2026-04-16 09:00","2026-04-24 18:00","2026-04-16 09:00","2026-04-24 18:00","연속"]
[562,"광주전남","광주","남광주화순#1 T/L"," 남광주CT 이설공사(지중케이블)"," 계림-남광주 58호 C/T 이설(약 0.1㎞) ○ 기설C/T 철거 및 신설C/T 가선 및 케이블 접속 ○ 아파트 인근 송전설비존치 관련 민원","2026-04-26 09:00","2026-04-30 18:00","2026-04-26 09:00","2026-04-30 18:00","연속"]
[563,"광주전남","광주","담양일곡#2 T/L"," 계림-승주 등 3개T/L 피뢰기설치공사"," 담양-일곡#2T/L 피뢰기 설치공사 1~228호, 71기","2026-04-13 07:00","2026-04-17 18:00","취소","취소","매일"]
[564,"광주전남","광주","정공담양 T/L"," 계림-승주 등 3개T/L 피뢰기설치공사"," 담양-일곡#2T/L 피뢰기 설치공사 4회선 구간 안전이격 확보 차 휴전","2026-04-13 07:00","2026-04-14 18:00","취소","취소","매일"]
[565,"광주전남","광주","북광주일곡#1 T/L","북광주S/S #3M.Tr 교체공사","#3M.Tr 무부하가압","2026-04-29 09:00","2026-04-30 18:00","2026-04-29 09:00","2026-04-30 18:00","연속"]
[566,"광주전남","광주","신광주순창#1 T/L","2026년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 시행 - 신광주-순창#1T/L 1~76호 (76기)","2026-04-06 08:00","2026-04-10 18:00","취소","취소","매일"]
[567,"광주전남","광주","신광주순창#2 T/L","2026년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 및 피뢰기갭혼 교체 시행 - 신광주-순창#2T/L 1~76호 (76기)","2026-04-13 08:00","2026-04-17 18:00","취소","취소","매일"]
[568,"광주전남","광주","신광주순창#1 T/L","2026년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 시행 - 신광주-순창#1T/L 76호 ( 순창-곡성T/L 병가선로)","2026-04-20 08:00","2026-04-20 18:00","2026-04-20 08:00","2026-04-20 18:00","매일"]
[569,"광주전남","광주","신광주순창#2 T/L","2026년 가공송전 순시점검 위탁공사(광주전력)","정밀점검 시행 - 신광주-순창#2T/L 76호 ( 순창-곡성T/L 병가선로)","2026-04-23 08:00","2026-04-23 18:00","2026-04-23 08:00","2026-04-23 18:00","매일"]
[570,"광주전남","광주","장성영광#2 T/L"," 계림-승주 등 3개T/L 피뢰기설치공사"," 장성-영광#2T/L 피뢰기 설치공사 1~15, 21~68호 64기","2026-04-06 07:00","2026-04-10 18:00","취소","취소","매일"]
[571,"광주전남","광주","신광주장성#2 T/L","'26~27 광주전력지사 변전협력회사 총액공사"," GIS 조작시험","2026-04-23 10:00","2026-04-23 18:00","취소","취소","당일"]
[572,"광주전남","광주","하남장성#1 T/L"," 계림-승주 등 3개T/L 피뢰기설치공사"," 장성-영광#2T/L 피뢰기 설치공사 4회선 구간 안전이격 확보 차 휴전","2026-04-06 07:00","2026-04-07 18:00","취소","취소","매일"]
[573,"광주전남","목포","영광서홍농개폐소 T/L","2026~2027년 목포전력지사 변전협력회사 공사","- 서홍농S/Y 영광-서홍농T/L GIS 초기시험","2026-04-09 10:00","2026-04-09 18:00","취소","취소","연속"]
[574,"광주전남","목포","영광홍농 T/L","2026~2027년 목포전력지사 변전협력회사 공사","- 영광S/S 영광-서홍농T/L GIS 조작시험, LA 보통점검","2026-04-09 10:00","2026-04-09 18:00","취소","취소","연속"]
[575,"광주전남","순천","광양S/S #60 BUS"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#7(기설) ∼ J/B#10(신설) XLPE 1,200(D)㎟ × 2C × 1.402km","2026-04-29 15:00","2026-04-29 17:00","2026-04-29 15:00","2026-04-29 17:00","당일"]
[576,"광주전남","순천","광양백운#1 T/L","26-27년 순천전력지사 변전협력회사 공사","광양-백운#1T/L 보호배전반 대체","2026-04-13 09:00","2026-04-15 18:00","2026-04-13 09:00","2026-04-15 18:00","연속"]
[577,"광주전남","순천","광양S/S SEC CB 60610","26-27년 순천전력지사 변전협력회사 공사","광양S/S #61-66 모선보호반 대체","2026-04-06 09:00","2026-04-10 18:00","2026-04-06 09:00","2026-04-10 18:00","연속"]
[578,"광주전남","순천","광양S/S CB 6200","26-27년 순천전력지사 변전협력회사 공사","광양S/S #61-66 모선보호반 대체","2026-04-06 09:00","2026-04-10 18:00","2026-04-06 09:00","2026-04-10 18:00","연속"]
[579,"광주전남","순천","광양S/S SEC CB 65660","26-27년 순천전력지사 변전협력회사 공사","광양S/S #61-66 모선보호반 대체","2026-04-06 09:00","2026-04-10 18:00","2026-04-06 09:00","2026-04-10 18:00","연속"]
[580,"광주전남","순천","광양S/S #60 BUS"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#7(기설) ∼ J/B#10(신설) XLPE 1,200(D)㎟ × 2C × 1.402km","2026-04-02 15:00","2026-04-02 17:00","취소","취소","당일"]
[581,"광주전남","순천","보성벌교 T/L","장흥-벌교T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(벌교고흥 일부병가, 단독작업가능)(1시간내가압가능)","2026-04-20 07:00","2026-04-22 18:00","취소","취소","매일"]
[582,"광주전남","순천","장흥벌교 T/L","장흥-벌교T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(벌교고흥 일부병가, 단독시행가능)(1시간내가압가능)","2026-04-13 07:00","2026-04-16 18:00","취소","취소","매일"]
[583,"광주전남","순천","소라서순천#1 T/L","2026~2027년 순천전력지사 변전협력회사 공사","서순천S/S 소라-서순천#1T/L GIS 조작시험 소라S/S 소라-서순천#1T/L GIS 조작시험","2026-04-22 16:00","2026-04-22 20:00","2026-04-22 16:00","2026-04-22 20:00","당일"]
[584,"광주전남","순천","순천S/S CB 6100"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#6(기설) ∼ J/B#10(신설) XLPE 1,200(D)㎟ × 2C × 1.402km","2026-04-29 17:00","2026-04-30 17:00","2026-04-29 17:00","2026-04-30 17:00","연속"]
[585,"광주전남","순천","순천율촌#1 T/L"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#6(기설) ∼ J/B#10(신설) XLPE 1,200(D)㎟ × 2C × 1.402km","2026-04-29 17:00","2026-04-30 17:00","2026-04-16 17:00","2026-04-17 17:00","연속"]
[586,"광주전남","순천","순천S/S #2 BUS"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#7(기설) ∼ J/B#10(신설) XLPE 1,200(D)㎟ × 2C × 1.402km","2026-04-29 15:00","2026-04-30 17:00","2026-04-29 15:00","2026-04-30 17:00","연속"]
[587,"광주전남","순천","광양순천#2 T/L"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#7(기설) ∼ J/B#10(신설) XLPE 1,200(D)㎟ × 2C × 1.402km","2026-04-06 07:00","2026-04-30 17:00","취소","취소","연속"]
[588,"광주전남","순천","순천율촌#1 T/L"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#6(기설) ∼ J/B#10(신설) XLPE 1,200(D)㎟ × 2C × 1.402km","2026-04-02 17:00","2026-04-03 17:00","취소","취소","연속"]
[589,"광주전남","순천","순천S/S CB 6100"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#6(기설) ∼ J/B#10(신설) XLPE 1,200(D)㎟ × 2C × 1.402km","2026-04-02 17:00","2026-04-03 17:00","취소","취소","연속"]
[590,"광주전남","순천","순천S/S #2 BUS"," 광양-순천T/L 지중화공사","154㎸ 광양-순천#1, 2T/L J/B#7(기설) ∼ J/B#10(신설) XLPE 1,200(D)㎟ × 2C × 1.402km","2026-04-02 15:00","2026-04-03 17:00","취소","취소","연속"]
[591,"광주전남","순천","승주주암HP T/L","승주-서순천T/L 추락방지시설 설치공사","수평추락방지설치 (승주-주암HP, 화순-승주1(통보분) 병가) (1시간내 가압가능)","2026-04-20 07:00","2026-04-30 18:00","취소","취소","매일"]
[592,"광주전남","순천","승주S/S #2 BUS","승주S/S #4M.Tr 증설공사","170kV GIS 증설용","2026-04-16 09:00","2026-04-18 18:00","취소","취소","연속"]
[593,"광주전남","순천","승주S/S #1 BUS","승주S/S #4M.Tr 증설공사","170kV GIS 증설용","2026-04-13 09:00","2026-04-16 09:00","취소","취소","연속"]
[594,"광주전남","순천","승주서순천 T/L","승주-서순천T/L 추락방지시설 설치공사","수평추락방지설치 (승주-서순천, 화순-승주2(통보분) 병가) (1시간내 가압가능)","2026-04-06 07:00","2026-04-17 18:00","취소","취소","매일"]
[595,"광주전남","순천","여수소라#2 T/L","2026~2027년 순천전력지사 변전협력회사 공사","여수S/S 여수-소라#2T/L GIS 보통점검, LA(B,C) 대체 소라S/S 여수-소라#2T/L GIS 조작시험","2026-04-07 09:00","2026-04-07 18:00","취소","취소","당일"]
[596,"광주전남","순천","여수S/S #2 BUS","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(3차) - 여천-여수#2T/L, #4M.Tr 1차 교체","2026-04-09 09:00","2026-04-15 09:00","취소","취소","연속"]
[597,"광주전남","순천","여천여수#2 T/L","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2026-04-09 09:00","2026-04-30 18:00","취소","취소","당일"]
[598,"광주전남","순천","여수S/S #1 BUS","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-04-09 09:00","2026-04-17 18:00","취소","취소","연속"]
[599,"광주전남","순천","여수소라#2 T/L","여수-소라T/L 추락방지시설 설치공사","수평추락방지설치(2,3호 : 여수-소라2, 여천-여수2 병가)(1시간내 가압가능)","2026-04-06 07:00","2026-04-07 18:00","2026-04-06 07:00","2026-04-07 18:00","매일"]
[600,"광주전남","순천","여천여수#2 T/L","여수-소라T/L 추락방지시설 설치공사","수평추락방지설치(2,3호 : 여수-소라2, 여천-여수2 병가)(1시간내 가압가능)","2026-04-06 07:00","2026-04-07 18:00","2026-04-06 07:00","2026-04-07 18:00","매일"]
[601,"광주전남","순천","여천여수#2 T/L","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(2차) - 안전이격휴전","2026-04-09 17:00","2026-04-09 21:00","취소","취소","당일"]
[602,"광주전남","순천","여수S/S #1 BUS","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-04-03 09:00","2026-04-03 18:00","취소","취소","연속"]
[603,"광주전남","순천","여천여수#1 T/L","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-04-03 09:00","2026-04-24 18:00","취소","취소","연속"]
[604,"광주전남","순천","여천여수#2 T/L","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(2차) - 안전이격휴전","2026-04-10 17:00","2026-04-10 21:00","취소","취소","당일"]
[605,"광주전남","순천","여수S/S #1 BUS","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2026-04-15 09:00","2026-04-23 09:00","취소","취소","당일"]
[606,"광주전남","순천","여수소라#1 T/L","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체용 무부하가압","2026-04-16 17:00","2026-04-17 09:00","취소","취소","연속"]
[607,"광주전남","순천","여수S/S #2 BUS","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-04-17 09:00","2026-04-24 09:00","취소","취소","연속"]
[608,"광주전남","순천","여수소라#1 T/L","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(3차) - #4M.Tr 1차, 여천-여수#1T/L 교체용 무부하가압","2026-04-22 17:00","2026-04-23 09:00","취소","취소","연속"]
[609,"광주전남","순천","여수S/S #2 BUS","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(3차) - #4M.Tr 1차 GIS, 여천-여수#2T/L 교체","2026-04-23 09:00","2026-04-30 09:00","취소","취소","당일"]
[610,"광주전남","순천","여수S/S #1 BUS","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-04-24 09:00","2026-04-24 18:00","취소","취소","연속"]
[611,"광주전남","순천","여수소라#1 T/L","여수-소라T/L 추락방지시설 설치공사","수평추락방지설치(2,3호 : 여수-소라1, 여천-여수1 병가)(1시간내 가압가능)","2026-04-02 07:00","2026-04-03 18:00","2026-04-02 07:00","2026-04-03 18:00","매일"]
[612,"광주전남","순천","여천여수#1 T/L","여수-소라T/L 추락방지시설 설치공사","수평추락방지설치(2,3호 : 여수-소라1, 여천-여수1 병가)(1시간내 가압가능)","2026-04-02 07:00","2026-04-03 18:00","2026-04-02 07:00","2026-04-03 18:00","매일"]
[613,"광주전남","순천","여수S/S #2 BUS","여수S/S 이하 장기사용 GIS 교체공사","○ 여수S/S 장기사용 GIS 교체공사(2차) - BUS-SEC 증설 및 여천-여수#1T/L 교체","2026-04-03 09:00","2026-04-09 09:00","취소","취소","연속"]
[614,"광주전남","순천","여수소라#1 T/L","2026~2027년 순천전력지사 변전협력회사 공사","여수S/S 여수-소라#1T/L GIS 보통점검, LA(A,B,C) 대체 소라S/S 여수-소라#1T/L GIS 조작시험","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[615,"광주전남","순천","여수T/P #66 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2026-04-09 09:00","2026-04-10 18:00","취소","취소","연속"]
[616,"광주전남","순천","호남TP여수TP#2 T/L","스페이서 가스누기 보수","스페이서 가스누기 보수","2026-04-09 09:00","2026-04-10 18:00","취소","취소","연속"]
[617,"광주전남","순천","여수TP여천#2 T/L","26년 송전선로 정밀점검","26년도 송전선로 정밀점검 ○ 여수TP-여천T/L No.1~15호","2026-04-09 08:00","2026-04-10 18:00","취소","취소","매일"]
[618,"광주전남","순천","여수TP여천#1 T/L","26년 송전선로 정밀점검","26년도 송전선로 정밀점검 ○ 여수TP-여천T/L No.1~15호","2026-04-07 08:00","2026-04-08 18:00","취소","취소","매일"]
[619,"광주전남","순천","호남TP여수TP#2 T/L","호남TP-여수TPT/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자설치(1시간내가압가능)","2026-04-06 07:00","2026-04-09 18:00","취소","취소","매일"]
[620,"광주전남","순천","여수T/P #65 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2026-04-23 09:00","2026-04-24 18:00","취소","취소","연속"]
[621,"광주전남","순천","여수TP화치#2 T/L","26-27년 순천전력지사 변전협력회사 공사","여수TP-화치#2T/L 보호배전반 대체","2026-04-27 09:00","2026-04-29 18:00","취소","취소","연속"]
[622,"광주전남","순천","여수T/P #61 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2026-04-02 09:00","2026-04-03 14:00","취소","취소","연속"]
[623,"광주전남","순천","호남TP여수TP#1 T/L","호남TP-여수TPT/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자설치(1시간내가압가능)","2026-04-03 07:00","2026-04-03 18:00","취소","취소","당일"]
[624,"광주전남","순천","여수T/P #60 BUS","스페이서 가스누기 보수","스페이서 가스누기 보수","2026-04-16 09:00","2026-04-17 18:00","취소","취소","연속"]
[625,"광주전남","순천","여천호남TP#2 T/L","여천S/S GIS 기기기초공사","안전이격, 매일휴전, 시간조정 가능, 즉시가압 가능","2026-04-01 09:00","2026-04-30 18:00","2026-04-01 09:00","2026-04-30 18:00","매일"]
[626,"광주전남","순천","여천여수#2 T/L","여천S/S GIS 기기기초공사","안전이격, 매일휴전, 시간조정 가능, 즉시가압 가능","2026-04-01 09:00","2026-04-30 18:00","2026-04-02 07:00","2026-04-03 18:00","매일"]
[627,"광주전남","순천","여수TP여천#2 T/L","여천S/S GIS 기기기초공사","안전이격, 매일휴전, 시간조정 가능, 즉시가압 가능","2026-04-01 09:00","2026-04-30 18:00","취소","취소","매일"]
[628,"광주전남","순천","여천호남TP#1 T/L","여천S/S GIS 기기기초공사","안전이격, 매일휴전, 시간조정 가능, 즉시가압 가능","2026-04-01 09:00","2026-04-30 18:00","2026-04-01 09:00","2026-04-30 18:00","매일"]
[629,"광주전남","순천","여수TP여천#1 T/L","여천S/S GIS 기기기초공사","안전이격, 매일휴전, 시간조정 가능, 즉시가압 가능","2026-04-01 09:00","2026-04-30 18:00","취소","취소","매일"]
[630,"광주전남","순천","여천여수#1 T/L","여천S/S GIS 기기기초공사","안전이격, 매일휴전, 시간조정 가능, 즉시가압 가능","2026-04-01 09:00","2026-04-30 18:00","2026-04-02 07:00","2026-04-03 18:00","매일"]
[631,"광주전남","순천","여수TP여천#1 T/L","2026~2027년 순천전력지사 변전협력회사 공사","여천S/S 여수TP-여천#1T/L GIS 보통점검, LA(B) 대체, LA(A,B) 보통점검","2026-04-16 09:00","2026-04-16 18:00","취소","취소","당일"]
[632,"광주전남","순천","여천여수#1 T/L","2026~2027년 순천전력지사 변전협력회사 공사","여천S/S 여천-여수 #1 T/L GIS 보통점검, 전자변 대체 여수S/S 여천-여수 #1 T/L LA 보통검검","2026-04-20 09:00","2026-04-20 18:00","2026-04-20 09:00","2026-04-20 18:00","당일"]
[633,"광주전남","순천","여수TP여천#2 T/L","여수TP-여천T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(1시간내가압가능)","2026-04-30 07:00","2026-04-30 18:00","취소","취소","당일"]
[634,"광주전남","순천","여천호남TP#2 T/L","2026~2027년 순천전력지사 변전협력회사 공사","여천S/S 여천-호남TP #2T/L GIS 보통점검 호남화력 여천-호남TP #2T/L LA(A,B,C) 대체","2026-04-29 09:00","2026-04-29 18:00","취소","취소","당일"]
[635,"광주전남","순천","여천호남TP#1 T/L","2026~2027년 순천전력지사 변전협력회사 공사","여천S/S 여천-호남TP #1T/L GIS 보통점검, 전자변 대체","2026-04-28 09:00","2026-04-28 18:00","취소","취소","당일"]
[636,"광주전남","순천","여천여수산단#1 T/L","2026~2027년 순천전력지사 변전협력회사 공사","여천S/S 여천-여수산단#1T/L GIS 조작시험","2026-04-27 10:00","2026-04-27 15:00","2026-04-27 10:00","2026-04-27 15:00","당일"]
[637,"광주전남","순천","여수TP여천#1 T/L","여수TP-여천T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(1시간내가압가능)","2026-04-27 07:00","2026-04-29 18:00","취소","취소","매일"]
[638,"광주전남","순천","여천여수#2 T/L","2026~2027년 순천전력지사 변전협력회사 공사","여천S/S 여천-여수 #2 T/L GIS 조작시험 여수S/S 여천-여수 #2 T/L LA 보통검검","2026-04-21 09:00","2026-04-21 18:00","2026-04-21 09:00","2026-04-21 18:00","당일"]
[639,"광주전남","순천","여수TP여천#2 T/L","2026~2027년 순천전력지사 변전협력회사 공사","여천S/S 여수TP-여천#2T/L GIS 보통점검","2026-04-17 09:00","2026-04-17 18:00","취소","취소","당일"]
[640,"광주전남","순천","용성여수산단#2 T/L","용성-여수산단T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(1시간내 가압가능)","2026-04-24 07:00","2026-04-24 18:00","취소","취소","당일"]
[641,"광주전남","순천","여수TP용성#2 T/L","여수TP-용성T/L 추락방지시설 설치공사","수평추락방지설치(1,3호 : 2회선 / 2,2.1호 : 여수TP-용성2, 용성-여수산단2 병가)(1시간내 가압가능)","2026-04-24 07:00","2026-04-24 18:00","취소","취소","당일"]
[642,"광주전남","순천","여수TP용성#1 T/L","여수TP-용성T/L 추락방지시설 설치공사","수평추락방지설치(1,3호 : 2회선 / 2,2.1호 : 여수TP-용성1, 용성-여수산단1 병가) (1시간내 가압가능)","2026-04-23 07:00","2026-04-23 18:00","취소","취소","당일"]
[643,"광주전남","순천","용성여수산단#1 T/L","용성-여수산단T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(1시간내 가압가능)","2026-04-20 07:00","2026-04-23 18:00","취소","취소","매일"]
[644,"광주전남","순천","용성여수산단#2 T/L","26년 송전선로 정밀점검","26년도 송전선로 정밀점검 ○ 용성-여수산단T/L No.1~3호","2026-04-15 08:00","2026-04-16 18:00","취소","취소","매일"]
[645,"광주전남","순천","여수TP용성#2 T/L","26년 송전선로 정밀점검","26년도 송전선로 정밀점검 ○ 여수TP-용성T/L No.1~3호","2026-04-15 08:00","2026-04-16 18:00","취소","취소","매일"]
[646,"광주전남","순천","여수TP용성#1 T/L","26년 송전선로 정밀점검","26년도 송전선로 정밀점검 ○ 여수TP-용성T/L No.1~3호","2026-04-13 08:00","2026-04-14 18:00","취소","취소","매일"]
[647,"광주전남","순천","용성여수산단#1 T/L","26년 송전선로 정밀점검","26년도 송전선로 정밀점검 ○ 용성-여수산단T/L No.1~3호","2026-04-13 08:00","2026-04-14 18:00","취소","취소","매일"]
[648,"광주전남","순천","순천율촌#1 T/L","율촌-화치T/L 추락방지시설 설치공사","수평추락방지설치(45~67호 : 율촌-화치2, 율촌-여수산단1 병가/68호 : 율촌-화치2, 순천-율촌1 병가)(1시간내 가압가능)","2026-04-24 07:00","2026-04-24 18:00","2026-04-24 07:00","2026-04-24 18:00","당일"]
[649,"광주전남","순천","순천율촌#2 T/L","2026~2027년 순천전력지사 변전협력회사 공사","율촌S/S 순천-율촌#2T/L GIS 보통점검, 유압시스템 교체","2026-04-23 09:00","2026-04-23 18:00","취소","취소","당일"]
[650,"광주전남","순천","율촌여수산단#1 T/L","율촌-여수산단T/L 추락방지시설 설치공사","수평추락방지설치 (2~27호 : 2회선 / 28~50호 : 율촌-화치2, 율촌-여수산단1 병가) (1시간내 가압가능)","2026-04-20 07:00","2026-04-30 18:00","취소","취소","매일"]
[651,"광주전남","순천","율촌화치#2 T/L","율촌-화치T/L 추락방지시설 설치공사","수평추락방지설치(45~67호 : 율촌-화치2, 율촌-여수산단1 병가 / 68호 : 율촌-화치2, 순천-율촌1 병가) (1시간내 가압가능)","2026-04-20 07:00","2026-04-24 18:00","2026-04-20 07:00","2026-04-24 18:00","매일"]
[652,"광주전남","순천","순천율촌#2 T/L","율촌-화치T/L 추락방지시설 설치공사","수평추락방지설치 (45~67호 : 율촌-화치1, 율촌-여수산단2 병가) (68호 : 율촌-화치1, 순천-율촌2 병가) (1시간내 가압가능)","2026-04-17 07:00","2026-04-17 18:00","2026-04-17 07:00","2026-04-17 18:00","당일"]
[653,"광주전남","순천","율촌화치#1 T/L","율촌-화치T/L 추락방지시설 설치공사","수평추락방지설치(45~67호 : 율촌-화치1, 율촌-여수산단2 병가, 68호 : 율촌-화치1, 순천-율촌2 병가)(1시간내 가압가능)","2026-04-13 07:00","2026-04-17 18:00","2026-04-13 07:00","2026-04-17 18:00","매일"]
[654,"광주전남","순천","율촌민자#2 T/L","율촌민자T/L 추락방지시설 설치공사","수평추락방지시설 설치","2026-04-09 07:00","2026-04-10 18:00","2026-04-09 07:00","2026-04-10 18:00","매일"]
[655,"광주전남","순천","율촌민자#1 T/L","율촌민자T/L 추락방지시설 설치공사","수평추락방지시설 설치","2026-04-07 07:00","2026-04-08 18:00","2026-04-07 07:00","2026-04-08 18:00","매일"]
[656,"광주전남","순천","율촌여수산단#2 T/L","율촌-여수산단T/L 추락방지시설 설치공사","수평추락방지설치 (2~27호 : 2회선구간 / 28~50호 : 율촌-화치1, 율촌-여수산단2 병가) (1시간내 가압가능)","2026-04-06 07:00","2026-04-17 18:00","취소","취소","매일"]
[657,"광주전남","순천","여수TP화치#2 T/L","여수TP-화치T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(1시간내 가압가능)","2026-04-13 07:00","2026-04-16 18:00","취소","취소","매일"]
[658,"광주전남","순천","여수TP화치#1 T/L","여수TP-화치T/L 폴리머점퍼지지애자 설치공사","폴리머점퍼지지애자 설치(1시간내가압가능)","2026-04-06 07:00","2026-04-08 18:00","취소","취소","매일"]
[659,"광주전남","순천","백운황금#2 T/L","현대제 170kV EGIS 정밀점검 시행","현대제 170kV EGIS 정밀점검 시행 - 170kV EGIS 10CCT 및 PT&ES 동작부","2026-04-13 09:00","2026-04-17 18:00","취소","취소","연속"]
[660,"광주전남","순천","황금세풍#1 T/L","현대제 170kV EGIS 정밀점검 시행","현대제 170kV EGIS 정밀점검 시행 - 170kV EGIS 10CCT 및 PT&ES 동작부","2026-04-20 09:00","2026-04-24 18:00","취소","취소","연속"]
[661,"광주전남","순천","백운황금#1 T/L","현대제 170kV EGIS 정밀점검 시행","현대제 170kV EGIS 정밀점검 시행 - 170kV EGIS 10CCT 및 PT&ES 동작부","2026-04-06 09:00","2026-04-10 18:00","취소","취소","연속"]
[662,"광주전남","순천","황금세풍#2 T/L","현대제 170kV EGIS 정밀점검 시행","현대제 170kV EGIS 정밀점검 시행 - 170kV EGIS 10CCT 및 PT&ES 동작부","2026-04-27 09:00","2026-05-01 18:00","취소","취소","연속"]
[663,"광주전남","직할","농성화정#1 T/L","2026~2027년 광주전남본부 직할 변전협력회사 공사","170kV GIS 조작시험 전자변 교체","2026-04-13 10:00","2026-04-13 18:00","취소","취소","당일"]
[664,"광주전남","직할","농성화정#2 T/L","2026~2027년 광주전남본부 직할 변전협력회사 공사","170kV GIS 조작시험 전자변 교체","2026-04-14 10:00","2026-04-14 18:00","취소","취소","당일"]
[665,"대구","경산","신경산노변 T/L","25~26년 대구본부 직할 지중송전 협력회사 공사","피뢰기 열화진단, 절연유 채유","2026-04-27 09:00","2026-04-29 16:00","2026-04-27 09:00","2026-04-29 16:00","연속"]
[666,"대구","경산","신서열병합(대구그린파워)S/Y 6100 CB","26~27년 경산전력 변전협력 총액공사","GIS 보통점검","2026-04-24 09:30","2026-04-24 18:00","2026-04-24 09:30","2026-04-24 18:00","당일"]
[667,"대구","경산","안심대구그린파워#1 T/L","26~27년 경산전력 변전협력 총액공사","GIS 보통점검","2026-04-22 09:30","2026-04-22 18:00","2026-04-22 09:30","2026-04-22 18:00","당일"]
[668,"대구","경산","안심대구그린파워#2 T/L","26~27년 경산전력 변전협력 총액공사","GIS 보통점검","2026-04-23 09:30","2026-04-23 18:00","2026-04-23 09:30","2026-04-23 18:00","당일"]
[669,"대구","경산","영천S/S #1 EM.Tr CB","26~27년 경산 변전협력 기기점검공사","- 변압기 보통점검 - GIS 보통점검 등","2026-04-06 09:30","2026-04-24 18:00","취소","취소","연속"]
[670,"대구","경산","영천S/S #2 EM.Tr CB","26~27년 경산 변전협력 기기점검공사","- 변압기 보통점검 - GIS 보통점검 등","2026-04-06 09:30","2026-04-24 18:00","취소","취소","연속"]
[671,"대구","경산","신경산진량 T/L","26년 경산전력지사 GIS 정밀점검 공사"," GIS 정밀점검","2026-04-29 16:00","2026-04-29 18:00","2026-04-30 16:00","2026-04-30 18:00","연속"]
[672,"대구","경산","신경산진량 T/L","[안전확보]진량S/S #1M.TR 부싱교체공사","1차측 부싱교체","2026-04-02 09:00","2026-04-03 18:00","2026-04-02 09:00","2026-04-03 18:00","연속"]
[673,"대구","달성","강창성서#2 T/L","GIS 정밀점검","GIS 정밀점검","2026-04-29 09:00","2026-04-30 18:00","2026-05-11 09:00","2026-05-12 18:00","당일"]
[674,"대구","달성","강창성서#1 T/L","GIS 정밀점검","GIS 정밀점검","2026-04-27 09:00","2026-04-28 18:00","2026-04-27 09:00","2026-04-28 18:00","당일"]
[675,"대구","달성","논공달성#2 T/L"," 명곡분기T/L 건설사업","○ 논공-명곡#2T/L, 명곡-달성#2T/L 신규 설치(철탑 2기 신설) ○ 논공-달성#2 No.13~18 금구류 교체 ○ 명곡변전소 무부하 가압 및 사용전 검사 ○ 논공 및 달성 변전소 송전선로 보호반 대체(#2T/L)","2026-04-10 08:00","2026-04-22 18:00","2026-04-11 08:00","2026-04-24 18:00","연속"]
[676,"대구","달성","논공달성#1 T/L"," 명곡분기T/L 건설사업","○ 명곡분기T/L 건설 전 가철탑 설치 ○ 논공달성#1 T/L의 가철탑으로 공중이동 ○ 논공달성#1 T/L 13~18호 금구류 교체","2026-04-06 08:00","2026-04-09 18:00","2026-04-06 08:00","2026-04-10 18:00","연속"]
[677,"대구","달성","논공달성#1 T/L"," 명곡분기T/L 건설사업","○ 논공-명곡#2T/L, 명곡-달성#1T/L 신규 설치 ○ 가철탑 철거 ○ 명곡변전소 무부하 가압 및 사용전 검사 ○ 논공 및 달성 변전소 송전선로 보호반 대체(#1T/L)","2026-04-24 08:00","2026-04-30 18:00","2026-04-25 08:00","2026-04-30 18:00","연속"]
[678,"대구","달성","다사달서 T/L","[TEST] GIS 정밀점검 관련 무부하선로","[TEST] GIS 정밀점검 관련 무부하선로","2026-04-21 17:00","2026-04-21 18:00","2026-04-21 17:00","2026-04-21 18:00","당일"]
[679,"대구","달성","달성S/S #2 BUS"," 명곡S/S 건설사업","○ 명곡S/S 무부하 가압","2026-04-20 09:00","2026-04-21 18:00","2026-04-22 09:00","2026-04-22 18:00","연속"]
[680,"대구","달성","달성S/S #1 BUS"," 명곡S/S 건설사업","○ 명곡S/S 무부하 가압","2026-04-28 09:00","2026-04-29 18:00","2026-04-29 09:00","2026-04-29 18:00","연속"]
[681,"대구","달성","성서달성#2 T/L","GIS 보통점검","GIS 보통점검","2026-04-07 09:00","2026-04-07 18:00","2026-04-07 09:00","2026-04-07 18:00","당일"]
[682,"대구","달성","성서달성#1 T/L","GIS 보통점검","GIS 보통점검","2026-04-06 09:00","2026-04-06 18:00","2026-04-06 09:00","2026-04-06 18:00","당일"]
[683,"대구","직할","남대구동인#2 T/L","25~26년 대구본부 직할 지중송전 협력회사 공사","절연유 채유","2026-04-13 09:00","2026-04-13 18:00","2026-04-13 09:00","2026-04-13 18:00","당일"]
[684,"대구","직할","남대구동인#1 T/L","25~26년 대구본부 직할 지중송전 협력회사 공사","절연유 채유","2026-04-10 09:00","2026-04-10 18:00","2026-04-10 09:00","2026-04-10 18:00","당일"]
[685,"대구","직할","동인내당#2 T/L","25~26년 대구본부 직할 지중송전 협력회사 공사","절연유 채유","2026-04-08 09:00","2026-04-09 18:00","2026-04-08 09:00","2026-04-09 18:00","연속"]
[686,"대구","직할","동인내당#1 T/L","25~26년 대구본부 직할 지중송전 협력회사 공사","절연유 채유","2026-04-16 09:00","2026-04-17 18:00","2026-04-16 09:00","2026-04-17 18:00","연속"]
[687,"대구","직할","효목안심#2 T/L","효목S/S 효목-안심#2T/L GIS 보통점검","효목S/S 효목-안심#2T/L GIS 보통점검","2026-04-15 09:30","2026-04-15 18:00","2026-04-15 09:30","2026-04-15 18:00","당일"]
[688,"대구","직할","효목안심#1 T/L","효목S/S 효목-안심#1T/L GIS 보통점검","효목S/S 효목-안심#1T/L GIS 보통점검","2026-04-14 09:30","2026-04-14 18:00","2026-04-14 09:30","2026-04-14 18:00","당일"]
[689,"대구","칠곡","관음구암#2 T/L","2026년 직할 가공송전 순시점검 위탁공사"," 관음-구암#2T/L 정밀점검 - No.1~45","2026-04-20 09:00","2026-04-30 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[690,"대구","칠곡","관음구암#1 T/L","2026년 직할 가공송전 순시점검 위탁공사"," 관음-구암#1T/L 정밀점검 - No.1~45","2026-04-20 09:00","2026-04-30 18:00","2026-04-20 09:00","2026-04-24 18:00","연속"]
[691,"대구","칠곡","봉무구암#2 T/L","2026년 직할 가공송전 순시점검 위탁공사"," 봉무-구암#2T/L 정밀점검 - No.1~25","2026-04-13 09:00","2026-04-24 18:00","취소","취소","연속"]
[692,"대구","칠곡","봉무구암#1 T/L","2026년 직할 가공송전 순시점검 위탁공사"," 봉무-구암#1T/L 정밀점검 - No.1~25","2026-04-13 09:00","2026-04-24 18:00","취소","취소","연속"]
[693,"대구","칠곡","김천금릉#1 T/L","금릉S/S #3M.Tr 증설공사(무부하 가압)","금릉S/S #3M.Tr 증설공사(무부하 가압)","2026-04-15 09:00","2026-04-15 18:00","2026-04-15 09:00","2026-04-15 18:00","연속"]
[694,"대구","칠곡","김천금릉#1 T/L","금릉S/S #3M.Tr 증설공사(무부하 가압)","금릉S/S #3M.Tr 증설공사(무부하 가압)","2026-04-17 09:00","2026-04-17 18:00","2026-04-17 09:00","2026-04-17 18:00","연속"]
[695,"대구","칠곡","어모김천#1 T/L","(안전확보) 2026~2027년 칠곡전력지사 가공송전협력회사 공사"," 고아-어모#1T/L 피뢰기 및 고정형 중간클램프, 회전방지금구 설치관련 안전확보차 (No.69, 4회선 구간 ; 상단 고아-어모#1, 하단 어모-김천#1)","2026-04-10 07:00","2026-04-10 18:00","2026-04-10 07:00","2026-04-10 18:00","당일"]
[696,"대구","칠곡","어모김천#1 T/L"," 김천S/S 현대화공사","○ LINE PT FUSE FAIL 경보수용","2026-04-28 09:00","2026-04-28 18:00","취소","취소","당일"]
[697,"대구","칠곡","어모김천#2 T/L"," 김천S/S 현대화공사","○ LINE PT FUSE FAIL 경보수용","2026-04-29 09:00","2026-04-29 18:00","취소","취소","당일"]
[698,"대구","칠곡","농소김천#2 T/L"," 김천S/S 현대화공사","○ LINE PT FUSE FAIL 경보수용","2026-04-30 09:00","2026-04-30 18:00","취소","취소","당일"]
[699,"대구","칠곡","남구미광평#1 T/L","남구미S/S 장기사용 GIS 교체공사(, 1.5CB)"," GIS 17CCT 철거, 22CCT 설치","2026-04-06 09:00","2026-06-16 18:00","2026-04-06 09:00","2026-06-16 18:00","연속"]
[700,"대구","칠곡","남구미농소#2 T/L","남구미S/S 장기사용 GIS 교체공사(, 1.5CB)"," GIS 17CCT 철거, 22CCT 설치","2026-04-06 09:00","2026-06-16 18:00","2026-04-06 09:00","2026-06-16 18:00","연속"]
[701,"대구","칠곡","어모김천#2 T/L","2026~2027년 칠곡전력지사 가공송전협력회사 공사","1. 고아-어모#2T/L 피뢰기 설치공사 안전확보차 (고아-어모#2T/L No.70~74, 4회선 구간) 2. 어모-김천#2T/L 피뢰기 설치공사차 (어모-김천#2T/L No.7~19)","2026-04-16 07:00","2026-04-17 18:00","2026-04-16 07:00","2026-04-17 18:00","연속"]
[702,"대구","칠곡","고아어모#1 T/L","2026~2027년 칠곡전력지사 가공송전협력회사 공사"," 고아-어모#1T/L 피뢰기 및 고정형 중간클램프, 회전방지금구 설치 (No.1~69)","2026-04-06 07:00","2026-04-10 18:00","2026-04-06 07:00","2026-04-10 18:00","연속"]
[703,"대구","칠곡","고아어모#2 T/L","2026~2027년 칠곡전력지사 가공송전협력회사 공사"," 고아-어모#2T/L 피뢰기 및 고정형 중간클램프, 회전방지금구 설치 (No.70~74)","2026-04-16 07:00","2026-04-16 18:00","2026-04-16 07:00","2026-04-16 18:00","당일"]
[704,"대구","포항","건천천북#2 T/L"," 건천-천북T/L 용량증대 선종교체공사","전력선 교체 40.3C-km","2026-04-14 07:00","2026-04-21 18:00","2026-04-18 07:00","2026-04-25 18:00","연속"]
[705,"대구","포항","아화건천#2 T/L","2026~27년 포항전력지사 변전협력회사 공사","건천S/S 모선보호반 대체","2026-04-30 15:00","2026-04-30 15:30","2026-04-30 15:00","2026-04-30 15:30","당일"]
[706,"대구","포항","건천천북#2 T/L","2026~27년 포항전력지사 변전협력회사 공사","건천S/S 모선보호반 대체","2026-04-30 13:30","2026-04-30 14:00","2026-04-30 13:30","2026-04-30 14:00","당일"]
[707,"대구","포항","건천천북#1 T/L","2026~27년 포항전력지사 변전협력회사 공사","건천S/S 모선보호반 대체","2026-04-30 13:00","2026-04-30 13:30","2026-04-30 13:00","2026-04-30 13:30","당일"]
[708,"대구","포항","아화건천#1 T/L","2026~27년 포항전력지사 변전협력회사 공사","건천S/S 모선보호반 대체","2026-04-30 14:30","2026-04-30 15:00","2026-04-30 14:30","2026-04-30 15:00","당일"]
[709,"경북","구미","동상주점촌#2 T/L","2026-2027년 구미전력지사 송전협력회사 공사"," 동상주-점촌T/L 관형지지물 일체형 레일 설치","2026-04-01 10:00","2026-04-01 18:00","2026-04-01 10:00","2026-04-01 18:00","연속"]
[710,"경북","구미","청리상주#1 T/L","2026-2027년 구미전력지사 송전협력회사 공사"," 청리-상주T/L 관형지지물 일체형 레일 설치","2026-04-03 08:00","2026-04-03 12:00","2026-04-03 08:00","2026-04-03 12:00","당일"]
[711,"경북","구미","청리상주#2 T/L","2026-2027년 구미전력지사 송전협력회사 공사"," 청리-상주T/L 관형지지물 일체형 레일 설치","2026-04-03 12:00","2026-04-03 18:00","2026-04-03 12:00","2026-04-03 18:00","당일"]
[712,"경북","구미","상주화동#1 T/L","2026-2027년 구미전력지사 송전협력회사 공사"," 상주-화동T/L 관형지지물 일체형 레일 설치","2026-04-03 08:00","2026-04-03 12:00","2026-04-03 08:00","2026-04-03 12:00","당일"]
[713,"경북","구미","상주화동#2 T/L","2026-2027년 구미전력지사 송전협력회사 공사"," 상주-화동T/L 관형지지물 일체형 레일 설치","2026-04-03 12:00","2026-04-03 18:00","2026-04-03 12:00","2026-04-03 18:00","당일"]
[714,"경북","영주","점촌문경 T/L","2026년 영주전력지사 가공송전 순시점검 위탁공사"," 예천-점촌T/L 정밀점검(점촌-문경 선로는 병가선로로 안전이격거리를 위한 휴전신청)","2026-04-27 08:00","2026-04-30 17:00","2026-04-27 08:00","2026-04-30 17:00","매일"]
[715,"경북","영주","문경단양 T/L","2026-27년 영주전력지사 변전협력회사공사","- LA A,B,C 히자점검","2026-04-03 10:00","2026-04-03 18:00","2026-04-03 10:00","2026-04-03 18:00","연속"]
[716,"경북","영주","문경S/S CB 6100","2026-2027년 영주전력지사 변전협력회사 총액공사","문경S/S 6100CB GIS 디지털 유압력계 교체","2026-04-03 09:00","2026-04-03 18:00","2026-04-03 09:00","2026-04-03 18:00","당일"]
[717,"경북","영주","봉화울진 T/L","26~27년 영주전력지사 변전협력회사공사","봉화-울진 T/L 조작시험","2026-04-07 09:00","2026-04-07 18:00","2026-04-07 09:00","2026-04-07 18:00","당일"]
[718,"경북","영주","예천점촌#2 T/L"," 예천-점촌T/L No.66호 지장철탑이설공사","- 지지물 : 철거 1기(66호), 설치 1기(66호), 가철탑 1기 - 전력선 : ACSR 410㎟*S*2C 0.766C-㎞ 교체 - 가공지선 : ACSR 97㎟ 1조, OPGW 100㎟ 1조(전자제어팀)","2026-04-20 08:00","2026-05-03 17:00","2026-04-20 08:00","2026-05-03 17:00","연속"]
[719,"경북","영주","예천점촌#1 T/L"," 예천-점촌T/L No.66호 지장철탑이설공사","- 지지물 : 철거 1기(66호), 설치 1기(66호), 가철탑 1기 - 전력선 : ACSR 410㎟*S*2C 0.766C-㎞ 교체 - 가공지선 : ACSR 97㎟ 1조, OPGW 100㎟ 1조(전자제어팀)","2026-04-13 08:00","2026-04-18 17:00","2026-04-13 08:00","2026-04-18 17:00","연속"]
[720,"경북","영주","점촌문경 T/L","2026-27년 영주전력지사 변전협력회사공사","- PT A 하자점검","2026-04-10 10:00","2026-04-10 18:00","2026-04-10 10:00","2026-04-10 18:00","연속"]
[721,"경북","영주","동상주점촌#2 T/L","2026년 영주전력지사 가공송전 순시점검 위탁공사"," 예천-점촌T/L 정밀점검(동상주-점촌#2T/L는 병가선로로 안전이격거리를 위한 휴전신청)","2026-04-30 08:00","2026-04-30 17:00","2026-04-30 08:00","2026-04-30 17:00","매일"]
[722,"경북","영주","점촌단양 T/L","2026-27년 영주전력지사 변전협력회사공사","- PT A 하자점검","2026-04-02 10:00","2026-04-02 18:00","2026-04-02 10:00","2026-04-02 18:00","연속"]
[723,"경북","직할","봉화울진 T/L","26~27년 경북본부 직할 변전협력회사 공사","GIS 하자점검","2026-04-28 10:00","2026-04-28 14:00","2026-04-28 10:00","2026-04-28 14:00","당일"]
[724,"경북","직할","진보GS영양풍력#2 T/L CB","2026년 경북본부 직할 GIS 정밀점검공사","진보 GS영양풍력#2T/L GIS 차단기 정밀점검","2026-04-20 09:00","2026-04-22 18:00","2026-04-20 09:00","2026-04-22 18:00","연속"]
[725,"부산울산","동부산","신울산명례#1 T/L","명례S/S #1M.Tr 1차(6133) GIS 정밀점검 관련 시험가압","명례S/S #1M.Tr 1차(6133) GIS 정밀점검 관련 시험가압","2026-04-03 17:00","2026-04-03 18:00","취소","취소","당일"]
[726,"부산울산","동부산","명례장안 T/L","명례S/S #1M.Tr 1차(6133) GIS 정밀점검 관련 시험가압","명례S/S #1M.Tr 1차(6133) GIS 정밀점검 관련 시험가압","2026-04-03 17:00","2026-04-03 18:00","2026-04-03 17:00","2026-04-03 18:00","당일"]
[727,"부산울산","동부산","신울산명례#1 T/L","명례S/S #1BUS-TIE(6100) GIS 정밀점검 관련 시험가압","명례S/S #1BUS-TIE(6100) GIS 정밀점검 관련 시험가압","2026-04-16 17:00","2026-04-16 18:00","취소","취소","당일"]
[728,"부산울산","동부산","명례장안 T/L","명례S/S #1BUS-TIE(6100) GIS 정밀점검 관련 시험가압","명례S/S #1BUS-TIE(6100) GIS 정밀점검 관련 시험가압","2026-04-16 17:00","2026-04-16 18:00","2026-04-16 17:00","2026-04-16 18:00","당일"]
[729,"부산울산","동부산","명례장안 T/L","명례S/S 명례-장안 T/L(647) GIS 정밀점검","명례S/S 명례-장안 T/L(647) GIS 정밀점검","2026-04-13 09:00","2026-04-14 18:00","2026-04-13 09:00","2026-04-14 18:00","연속"]
[730,"부산울산","동부산","명례고리NP T/L","명례S/S 명례-고리NP T/L(637) GIS 정밀점검","명례S/S 명례-고리NP T/L(637) GIS 정밀점검","2026-04-08 09:00","2026-04-09 18:00","2026-04-08 09:00","2026-04-09 18:00","연속"]
[731,"부산울산","동부산","명례장안 T/L","명례S/S #2M.Tr 1차(6233) GIS 정밀점검 관련 시험가압","명례S/S #2M.Tr 1차(6233) GIS 정밀점검 관련 시험가압","2026-04-07 17:00","2026-04-07 18:00","2026-04-07 17:00","2026-04-07 18:00","당일"]
[732,"부산울산","동부산","신울산명례#2 T/L","명례S/S #2M.Tr 1차(6233) GIS 정밀점검 관련 시험가압","명례S/S #2M.Tr 1차(6233) GIS 정밀점검 관련 시험가압","2026-04-07 17:00","2026-04-07 18:00","취소","취소","당일"]
[733,"부산울산","북부산","개금범천#2 T/L","개금S/S 장기사용 GIS 교체공사","개금S/S 장기사용 GIS 교체공사","2026-04-18 09:00","2026-05-05 18:00","2026-04-18 09:00","2026-05-05 18:00","연속"]
[734,"부산울산","북부산","개금범천#1 T/L","개금S/S 장기사용 GIS 교체공사","개금S/S 장기사용 GIS 교체공사","2026-04-03 09:00","2026-04-17 18:00","2026-04-03 09:00","2026-04-17 18:00","연속"]
[735,"부산울산","북부산","북부산구포#2 T/L","2026년 북부산전력 GIS 정밀/보통점검공사","북부산-구포#2T/L GIS 보통점검","2026-04-21 09:00","2026-04-21 18:00","2026-04-21 09:00","2026-04-21 18:00","당일"]
[736,"부산울산","북부산","북부산구포#1 T/L","2026년 북부산전력 GIS 정밀/보통점검공사","북부산-구포#1T/L GIS 보통점검","2026-04-20 09:00","2026-04-20 18:00","2026-04-20 09:00","2026-04-20 18:00","당일"]
[737,"부산울산","북부산","북부산S/S CB 6100","2026년 북부산전력 GIS 정밀/보통점검공사","6100B/T GIS 보통점검","2026-04-17 09:00","2026-04-17 18:00","2026-04-17 09:00","2026-04-17 18:00","당일"]
[738,"부산울산","북부산","북부산삼랑진PP T/L","2026년 북부산전력 GIS 정밀/보통점검공사 `","북부산-삼랑진T/L GIS 보통점검","2026-04-16 09:00","2026-04-16 18:00","2026-04-16 09:00","2026-04-16 18:00","당일"]
[739,"부산울산","북부산","북부산양산 T/L","2026년 북부산전력 GIS 정밀/보통점검공사","북부산-양산T/L GIS 보통점검","2026-04-15 09:00","2026-04-15 18:00","2026-04-15 09:00","2026-04-15 18:00","당일"]
[740,"부산울산","북부산","북부산물금 T/L","2026년 북부산전력 GIS 정밀/보통점검공사","북부산-물금T/L GIS 보통점검","2026-04-14 09:00","2026-04-14 18:00","2026-04-14 09:00","2026-04-14 18:00","당일"]
[741,"부산울산","북부산","북부산구포#3 T/L","2026년 북부산전력 GIS 정밀/보통점검공사","북부산-구포#3T/L GIS 보통점검","2026-04-30 09:00","2026-04-30 18:00","2026-04-30 09:00","2026-04-30 18:00","당일"]
[742,"부산울산","북부산","북부산S/S CB 6300","2026년 북부산전력 GIS 정밀/보통점검공사","6300B/T GIS 보통점검","2026-04-30 09:00","2026-04-30 18:00","2026-04-30 09:00","2026-04-30 18:00","당일"]
[743,"부산울산","북부산","북부산S/S CB 6200","2026년 북부산전력 GIS 정밀/보통점검공사","6200B/T GIS 보통점검","2026-04-24 09:00","2026-04-24 18:00","2026-04-24 09:00","2026-04-24 18:00","당일"]
[744,"부산울산","북부산","양산산막#1 T/L","2026년 가공송전선로 순시점검 위탁공사 초기점검"," 양산-산막T/L 초기점검 -점검대상 : 총 3기(No.1~3호)","2026-04-04 07:00","2026-04-04 18:00","2026-04-04 07:00","2026-04-04 18:00","당일"]
[745,"부산울산","북부산","양산산막#2 T/L","2026년 가공송전선로 순시점검 위탁공사 초기점검"," 양산-산막T/L 초기점검 -점검대상 : 총 3기(No.1~3호)","2026-04-05 07:00","2026-04-05 18:00","2026-04-05 07:00","2026-04-05 18:00","당일"]
[746,"부산울산","북부산","모라엄궁#2 T/L","26-27 북부산전력 변전협력회사 총액공사`","모라엄궁#2T/L GIS 보통점검","2026-04-03 09:00","2026-04-03 18:00","2026-04-03 09:00","2026-04-03 18:00","당일"]
[747,"부산울산","북부산","엄궁S/S CB 6100","26-27 북부산전력 변전협력회사 총액공사`","6100 BT GIS 보통점검","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[748,"부산울산","북부산","호포물금 T/L","2026~2027년 북부산서부산전력지사 가공송전 협력회사 공사"," 호포-물금T/L 보수용 압축인류클램프 시공 - 설치대상 : 1기(3호)","2026-04-25 13:00","2026-04-25 18:00","취소","취소","당일"]
[749,"부산울산","북부산","북부산호포 T/L","2026~2027년 북부산서부산전력지사 가공송전 협력회사 공사"," 북부산-호포T/L 보수용 압축인류클램프 시공 - 설치대상 : 1기(3호)","2026-04-25 07:00","2026-04-25 13:00","취소","취소","당일"]
[750,"부산울산","서부산","용원녹공#2 T/L","녹공S/S 용원-녹공#2T/L GIS 동작시험","녹공S/S 용원-녹공#2T/L GIS 동작시험","2026-04-13 14:00","2026-04-13 18:00","2026-04-13 14:00","2026-04-13 18:00","당일"]
[751,"부산울산","서부산","용원녹공#1 T/L","녹공S/S 용원-녹공#1T/L GIS 동작시험","녹공S/S 용원-녹공#1T/L GIS 동작시험","2026-04-13 09:00","2026-04-13 14:00","2026-04-13 09:00","2026-04-13 14:00","당일"]
[752,"부산울산","서부산","신녹산녹산#2 T/L","녹산S/S 신녹산-녹산#2T/L GIS 보통점검","녹산S/S 신녹산-녹산#2T/L GIS 보통점검","2026-04-15 09:00","2026-04-15 18:00","취소","취소","당일"]
[753,"부산울산","서부산","신녹산녹산#1 T/L","녹산S/S 신녹산-녹산#1T/L GIS 보통점검","녹산S/S 신녹산-녹산#1T/L GIS 보통점검","2026-04-14 09:00","2026-04-14 18:00","취소","취소","당일"]
[754,"부산울산","서부산","서부산다대#2 T/L","다대S/S 장기사용 GIS 교체공사(3차분)","다대S/S 장기사용 GIS 교체공사(3차분) - 서부산-다대#2T/L","2026-04-29 08:00","2026-05-15 18:00","2026-04-29 08:00","2026-05-15 18:00","연속"]
[755,"부산울산","서부산","신녹산용원#2 T/L","신녹산,용원S/S 신녹산-용원#2T/L 보호배전반 교체","신녹산,용원S/S 신녹산-용원#2T/L 보호배전반 교체","2026-04-25 09:00","2026-04-26 18:00","2026-04-25 09:00","2026-04-26 18:00","연속"]
[756,"부산울산","서부산","신녹산용원#1 T/L","신녹산,용원S/S 신녹산-용원#1 T/L 보호배전반 교체","신녹산,용원S/S 신녹산-용원#1 T/L 보호배전반 교체","2026-04-18 09:00","2026-04-19 18:00","2026-04-18 09:00","2026-04-19 18:00","연속"]
[757,"부산울산","서부산","신김해지사#2 T/L","지사S/S 신김해-지사#2T/L GIS 정밀점검","지사S/S 신김해-지사#2T/L GIS 정밀점검","2026-04-15 09:00","2026-04-16 18:00","2026-04-15 09:00","2026-04-16 18:00","연속"]
[758,"부산울산","서부산","신김해지사#1 T/L","지사S/S 신김해-지사#1T/L GIS 정밀점검","지사S/S 신김해-지사#1T/L GIS 정밀점검","2026-04-13 09:00","2026-04-14 18:00","2026-04-13 09:00","2026-04-14 18:00","연속"]
[759,"부산울산","울산","산하방어진#1 T/L","수평레일 추락방지장치 설치공사","동울산-산하 #2 병가 : 17, 18","2026-04-16 07:00","2026-04-16 18:00","2026-04-16 07:00","2026-04-16 18:00","당일"]
[760,"부산울산","울산","성암울산TP#2 T/L","폴리머지지애자 설치공사","성암-울산TP #2 병가 : 7 (4/20~4/21) 병가 X : 1, 1-1, 2, 3","2026-04-20 07:00","2026-04-21 18:00","2026-04-20 07:00","2026-04-21 18:00","연속"]
[761,"부산울산","울산","성암울산TP#2 T/L"," 성암개폐소 신규수용공사(디아이지)"," 성암개폐소 신규수용공사 시험가압선로","2026-04-01 09:00","2026-04-02 18:00","취소","취소","연속"]
[762,"부산울산","울산","남울산성암#1 T/L","성암S/Y 신규수용공사","디아이지 에어가스 신규수용공사 - 시험가압선로","2026-04-01 09:00","2026-04-02 18:00","취소","취소","연속"]
[763,"부산울산","울산","신울산S/S SEC CB 60610","26년~27년 울산전력지사 변전협력회사 공사","-GIS 보통점검 -Rubber Heater 설치","2026-04-07 09:00","2026-04-07 12:00","2026-04-07 09:00","2026-04-07 12:00","당일"]
[764,"부산울산","울산","신울산S/S CB 6200","26~27년 울산전력 변전협력회사공사","- GIS 보통점검","2026-04-23 13:00","2026-04-23 18:00","2026-04-23 13:00","2026-04-23 18:00","연속"]
[765,"부산울산","울산","신울산언양#1 T/L","26년~27년 울산전력지사 변전협력회사 공사","-GIS 보통점검","2026-04-06 09:00","2026-04-06 12:00","2026-04-06 09:00","2026-04-06 12:00","당일"]
[766,"부산울산","울산","신울산웅촌#2 T/L","26년~27년 울산전력지사 변전협력회사 공사","-GIS 보통점검","2026-04-01 13:00","2026-04-01 18:00","취소","취소","당일"]
[767,"부산울산","울산","신울산웅촌#1 T/L","26년~27년 울산전력지사 변전협력회사 공사","-GIS 보통점검","2026-04-01 09:00","2026-04-01 12:00","취소","취소","당일"]
[768,"부산울산","울산","신울산웅촌#1 T/L","신울산-웅촌-서창간 OPGW 증설공사","신울산-웅촌, 웅촌-서창간 OPGW 증설(12C→48C)","2026-04-20 07:00","2026-04-26 17:00","2026-04-20 07:00","2026-04-26 17:00","연속"]
[769,"부산울산","울산","신울산S/S SEC CB 61620","26~27년 울산전력 변전협력회사공사","- GIS 보통점검","2026-04-20 09:00","2026-04-20 12:00","2026-04-20 09:00","2026-04-20 12:00","연속"]
[770,"부산울산","울산","신울산S/S SEC CB 62630","26~27년 울산전력 변전협력회사공사","- GIS 보통점검","2026-04-21 09:00","2026-04-21 12:00","2026-04-21 09:00","2026-04-21 12:00","연속"]
[771,"부산울산","울산","신울산S/S CB 6100","26~27년 울산전력 변전협력회사공사","- GIS 보통점검","2026-04-23 09:00","2026-04-23 12:00","2026-04-23 09:00","2026-04-23 12:00","연속"]
[772,"부산울산","울산","신울산언양#2 T/L","26년~27년 울산전력지사 변전협력회사 공사","-GIS 보통점검 -Rubber Heater 설치","2026-04-06 13:00","2026-04-06 18:00","2026-04-06 13:00","2026-04-06 18:00","당일"]
[773,"부산울산","울산","신울산S/S SEC CB 65660","26~27년 울산전력 변전협력회사공사","- GIS 보통점검","2026-04-24 09:00","2026-04-24 12:00","2026-04-24 09:00","2026-04-24 12:00","연속"]
[774,"부산울산","울산","신울산S/S SEC CB 67680","26~27년 울산전력 변전협력회사공사","- GIS 보통점검","2026-04-07 13:00","2026-04-07 18:00","2026-04-07 13:00","2026-04-07 18:00","연속"]
[775,"부산울산","울산","신울산S/S SEC CB 66670","26~27년 울산전력 변전협력회사공사","- GIS 보통점검","2026-04-24 13:00","2026-04-24 18:00","2026-04-24 13:00","2026-04-24 18:00","연속"]
[776,"부산울산","울산","신울산언양#1 T/L","폴리머지지애자 설치공사","신울산-언양 #1 병가 : 4","2026-04-14 07:00","2026-04-14 18:00","2026-04-14 07:00","2026-04-14 18:00","당일"]
[777,"부산울산","울산","옥동외동#2 T/L","폴리머지지애자 설치공사","외동-옥동 #2 병가 : 25, 27 (4/22~4/23) 병가X : 13, 22, 32","2026-04-22 10:00","2026-04-23 18:00","2026-04-22 10:00","2026-04-23 18:00","연속"]
[778,"부산울산","울산","신온산온산#1 T/L","26년~27년 울산전력지사 변전협력회사 공사","-GIS 초기점검","2026-04-08 09:00","2026-04-08 18:00","2026-04-08 09:00","2026-04-08 18:00","당일"]
[779,"부산울산","울산","신온산온산#3 T/L","26년~27년 울산전력지사 변전협력회사 공사","-GIS 초기점검","2026-04-10 09:00","2026-04-10 18:00","2026-04-10 09:00","2026-04-10 18:00","당일"]
[780,"부산울산","울산","온산처용#1 T/L","26년~27년 울산전력지사 변전협력회사 공사","-GIS 초기점검","2026-04-13 09:00","2026-04-13 18:00","2026-04-13 09:00","2026-04-13 18:00","당일"]
[781,"부산울산","울산","온산처용#2 T/L","26년~27년 울산전력지사 변전협력회사 공사","-GIS 초기점검","2026-04-14 09:00","2026-04-14 18:00","2026-04-14 09:00","2026-04-14 18:00","당일"]
[782,"부산울산","울산","신온산온산#2 T/L","26년~27년 울산전력지사 변전협력회사 공사","-GIS 초기점검","2026-04-09 09:00","2026-04-09 18:00","2026-04-09 09:00","2026-04-09 18:00","당일"]
[783,"부산울산","울산","용연울산TP#3 T/L","26년~27년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2026-04-17 09:00","2026-04-17 18:00","2026-04-17 09:00","2026-04-17 18:00","당일"]
[784,"부산울산","울산","용연울산TP#3 T/L","26년~27년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2026-04-17 09:00","2026-04-17 18:00","취소","취소","당일"]
[785,"부산울산","울산","울주외동#2 T/L","폴리머지지애자 설치공사","울주-입실 #2 병가 : 2, 3 (4/24)","2026-04-24 07:00","2026-04-24 18:00","2026-04-24 07:00","2026-04-24 18:00","당일"]
[786,"부산울산","울산","울주외동#1 T/L","폴리머지지애자 설치공사","울주-입실 #1 병가 : 4 (4/22) 외동-옥동 #2 병가 : 25, 27 (4/22~4/23)","2026-04-22 07:00","2026-04-23 18:00","2026-04-22 07:00","2026-04-23 18:00","연속"]
[787,"부산울산","울산","울주입실#1 T/L","폴리머지지애자 설치공사","울주-입실 #1 병가 : 4 (4/22)","2026-04-22 07:00","2026-04-22 10:00","2026-04-22 07:00","2026-04-22 10:00","당일"]
[788,"부산울산","울산","울주입실#2 T/L","폴리머지지애자 설치공사","울주-입실 #2 병가 : 2, 3 (4/24)","2026-04-24 07:00","2026-04-24 18:00","2026-04-24 07:00","2026-04-24 18:00","당일"]
[789,"부산울산","울산","웅촌서창#2 T/L","26년~27년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2026-04-17 09:00","2026-04-17 12:00","2026-04-17 09:00","2026-04-17 12:00","당일"]
[790,"부산울산","울산","울주직동#1 T/L","26년~27년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2026-04-20 09:00","2026-04-20 18:00","2026-04-20 09:00","2026-04-20 18:00","당일"]
[791,"부산울산","울산","울주직동#2 T/L","26년~27년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2026-04-21 09:00","2026-04-21 18:00","2026-04-21 09:00","2026-04-21 18:00","당일"]
[792,"부산울산","울산","온산처용#1 T/L","26년~27년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2026-04-13 09:00","2026-04-13 18:00","2026-04-13 09:00","2026-04-13 18:00","당일"]
[793,"부산울산","울산","온산처용#2 T/L","26년~27년 울산전력지사 변전협력회사 공사","-차단기 동작시험","2026-04-14 09:00","2026-04-14 18:00","2026-04-14 09:00","2026-04-14 18:00","당일"]
[794,"부산울산","울산","태화북울산#1 T/L","수평레일 추락방지장치 설치 및 점퍼선 교체공사","[수평레일]병가X : 1 [점퍼선 교체] 병가 X : 2, 7","2026-04-14 07:00","2026-04-14 18:00","2026-04-14 07:00","2026-04-14 18:00","당일"]
[795,"부산울산","직할","우동대연 T/L","2026~2027년 북부산,서부산 가공협력회사 공사","고정형 폴리머 점퍼지지애자 설치공사","2026-04-18 08:00","2026-04-19 18:00","취소","취소","당일"]
[796,"부산울산","직할","정보대연 T/L","26~27년 직할 변전협력회사공사","대연S/S 정보-대연 T/L GIS 보통점검, 전자변 교체","2026-04-11 09:30","2026-04-11 18:00","취소","취소","연속"]
[797,"부산울산","직할","수정범일#1 T/L"," 수정-범일#1T/L 누유점 확인작업"," 수정-범일#1T/L 누유점 확인작업","2026-04-21 09:00","2026-04-21 18:00","2026-04-21 09:00","2026-04-21 18:00","당일"]
[798,"부산울산","직할","양정범천 T/L","26-27년 직할 변전협력회사공사","양정, 범천S/S 양정-범천T/L 보호반 교체","2026-04-13 09:30","2026-04-15 18:00","취소","취소","연속"]
[799,"부산울산","동부산","명례장안 T/L","명례S/S 명례-고리T/L GIS 정밀점검 관련 시험가압","명례S/S 명례-고리T/L GIS 정밀점검 관련 시험가압","2026-04-09 17:00","2026-04-09 18:00","2026-04-09 17:00","2026-04-09 18:00","당일"]
[800,"경남","김해송변전부","매리김해#2 T/L","김해S/S 매리-김해#2T/L 혼용화공사","김해S/S 매리-김해#2T/L 혼용화공사","2026-04-11 09:00","2026-04-12 18:00","2026-04-11 09:00","2026-04-12 18:00","연속"]
[801,"경남","김해송변전부","매리김해#1 T/L","김해S/S 매리-김해#1T/L 혼용화공사","김해S/S 매리-김해#1T/L 혼용화공사","2026-04-04 09:00","2026-04-05 18:00","2026-04-04 09:00","2026-04-05 18:00","연속"]
[802,"경남","김해송변전부","김해S/S CB 6100","김해S/S BUS TIE 6100 혼용화공사","김해S/S BUS TIE 6100 혼용화공사","2026-04-03 09:30","2026-04-03 18:00","2026-04-03 09:30","2026-04-03 18:00","당일"]
[803,"경남","김해송변전부","김해어방#1 T/L","김해S/S 김해-어방#1T/L 혼용화공사","김해S/S 김해-어방#1T/L 혼용화공사","2026-04-18 09:00","2026-04-19 18:00","2026-04-18 09:00","2026-04-19 18:00","연속"]
[804,"경남","김해송변전부","삼계어방#2 T/L","어방S/S 삼계-어방 #2T/L GIS 보통점검","어방S/S 삼계-어방 #2T/L GIS 보통점검","2026-04-26 09:30","2026-04-26 18:00","2026-04-26 09:30","2026-04-26 18:00","당일"]
[805,"경남","김해송변전부","삼계어방#1 T/L","어방S/S 삼계-어방 #1T/L GIS 보통점검","어방S/S 삼계-어방 #1T/L GIS 보통점검 + 전자변 교체","2026-04-25 09:30","2026-04-25 18:00","2026-04-25 09:30","2026-04-25 18:00","당일"]
[806,"경남","김해송변전부","신김해진례#1 T/L","2026년도 가공송전 순시점검 위탁회사","정밀점검(No.1~28)","2026-04-25 08:00","2026-04-25 18:00","2026-04-25 08:00","2026-04-25 18:00","당일"]
[807,"경남","김해송변전부","진례진영#2 T/L","2026년도 가공송전 순시점검 위탁회사","정밀점검(No.1~7)","2026-04-05 08:00","2026-04-05 18:00","2026-04-05 08:00","2026-04-05 18:00","당일"]
[808,"경남","김해송변전부","진례진영#1 T/L","2026년도 가공송전 순시점검 위탁회사","정밀점검(No.1~7)","2026-04-04 08:00","2026-04-04 18:00","2026-04-04 08:00","2026-04-04 18:00","당일"]
[809,"경남","김해송변전부","신김해진례#1 T/L","2026년도 가공송전 순시점검 위탁회사","정밀점검(No.1~28)","2026-04-18 08:00","2026-04-18 18:00","2026-04-18 08:00","2026-04-18 18:00","당일"]
[810,"경남","직할","신월동읍#1 T/L","신월S/S #3M.Tr 1차 GIS 정밀점검 시험가압","신월S/S #3M.Tr 1차 GIS 정밀점검 시험가압","2026-04-29 15:00","2026-04-29 18:00","2026-04-29 15:00","2026-04-29 18:00","당일"]
[811,"경남","직할","안민천선#2 T/L","천선 안민-천선#2T/L 보통점검","천선 안민-천선#2T/L 보통점검 (병행)안민S/S 안민-천선#2T/L GIS 조작","2026-04-08 09:00","2026-04-08 18:00","2026-04-08 09:00","2026-04-08 18:00","당일"]
[812,"경남","진주","사봉개양#1 T/L","개양S/S 사봉-개양#1T/L GIS 보통점검","개양S/S 사봉-개양#1T/L GIS 보통점검","2026-04-16 10:00","2026-04-16 17:00","2026-04-16 10:00","2026-04-16 17:00","당일"]
[813,"경남","진주","사천개양#2 T/L","개양S/S 사천-개양#2T/L GIS 보통점검","개양S/S 사천-개양#2T/L GIS 보통점검","2026-04-07 10:00","2026-04-07 17:00","2026-04-07 10:00","2026-04-07 17:00","당일"]
[814,"경남","진주","진주개양#2 T/L"," 진주-개양#2T/L 지중송전 EBA절연유 진단"," 진주-개양#2T/L 지중송전 EBA절연유 진단","2026-04-02 09:00","2026-04-02 18:00","2026-04-05 09:00","2026-04-05 18:00","당일"]
[815,"경남","진주","진주개양#1 T/L"," 진주-개양#1T/L 지중송전 EBA절연유 진단"," 진주-개양#1T/L 지중송전 EBA절연유 진단","2026-04-01 09:00","2026-04-01 18:00","취소","취소","당일"]
[816,"경남","진주","진주개양#2 T/L","개양S/S 진주-개양#2T/L GIS 보통점검","개양S/S 진주-개양#2T/L GIS 보통점검","2026-04-14 10:00","2026-04-14 17:00","취소","취소","당일"]
[817,"경남","진주","동진주S/S CB 6100","동진주S/S #60-#65 BUS TIE GIS 보통점검","동진주S/S #60-#65 BUS TIE GIS 보통점검","2026-04-03 10:00","2026-04-03 17:00","2026-04-03 10:00","2026-04-03 17:00","당일"]
[818,"경남","진주","동진주진주#1 T/L","동진주S/S 동진주-진주#1T/L GIS 보통점검","동진주S/S 동진주-진주#1T/L GIS 보통점검","2026-04-24 10:00","2026-04-24 17:00","2026-04-24 10:00","2026-04-24 17:00","당일"]
[819,"경남","진주","동진주진주#2 T/L","동진주S/S 동진주-진주#2T/L GIS 보통점검","동진주S/S 동진주-진주#2T/L GIS 보통점검","2026-04-23 10:00","2026-04-23 17:00","2026-04-23 10:00","2026-04-23 17:00","당일"]
[820,"경남","진주","하동정촌#2 T/L","정촌S/S 하동-정촌#2T/L GIS 제작사 하자점검","정촌S/S 하동-정촌#2T/L GIS 제작사 하자점검(선로 휴전)","2026-04-25 09:00","2026-04-28 18:00","2026-04-25 09:00","2026-04-28 18:00","연속"]
[821,"경남","진주","하동S/S CB 6100","하동S/S 장기사용 170kV GIS 교체공사(1차 공정)","하동S/S 장기사용 170kV GIS 교체공사(1차 공정)","2026-04-13 09:00","2026-04-25 18:00","2026-04-13 09:00","2026-04-25 18:00","연속"]
[822,"경남","진주","하동하동화력 T/L","하동S/S 지중 인출변경 관련 LA 임시 이설","하동S/S 지중 인출변경 관련 LA 임시 이설","2026-04-02 09:00","2026-04-02 18:00","2026-04-02 09:00","2026-04-02 18:00","당일"]
[823,"경남","진주","광양하동#2 T/L","하동S/S 장기사용 GIS 교체공사(1차 공정) 시험가압2","하동S/S 장기사용 GIS 교체공사(1차 공정) 시험가압2","2026-04-24 09:00","2026-04-25 18:00","취소","취소","연속"]
[824,"경남","진주","하동S/S #65 BUS","하동S/S 장기사용 170kV GIS 교체공사(1차 공정)","하동S/S 장기사용 170kV GIS 교체공사(1차 공정)","2026-04-20 09:00","2026-04-25 18:00","2026-04-20 09:00","2026-04-25 18:00","연속"]
[825,"경남","진주","광양하동#2 T/L","하동S/S 장기사용 GIS 교체공사(1차 공정) 시험가압","하동S/S 장기사용 GIS 교체공사(1차 공정) 시험가압","2026-04-18 09:00","2026-04-19 18:00","취소","취소","연속"]
[826,"경남","진주","하동S/S #60 BUS","하동S/S 장기사용 170kV GIS 교체공사(1차 공정)","하동S/S 장기사용 170kV GIS 교체공사(1차 공정)","2026-04-13 09:00","2026-04-19 18:00","2026-04-13 09:00","2026-04-19 18:00","연속"]
[827,"경남","진주","의령함양 T/L","함양S/S 의령-함양T/L GIS 보통점검","함양S/S 의령-함양T/L GIS 보통점검 [병행] 의령S/S 의령-함양T/L GIS 조작시험","2026-04-29 10:00","2026-04-29 17:00","2026-04-29 10:00","2026-04-29 17:00","당일"]
[828,"경남","진주","함양거창#2 T/L","2026년도 가공송전 순시점검 위탁공사","송전선로 정밀점검","2026-04-15 08:00","2026-04-23 18:00","2026-04-15 08:00","2026-04-23 18:00","매일"]
[829,"경남","진주","함양거창#1 T/L","2026년도 가공송전 순시점검 위탁공사","송전선로 정밀점검","2026-04-06 08:00","2026-04-14 18:00","2026-04-06 08:00","2026-04-14 18:00","매일"]
[830,"경남","진주","거창합천#1 T/L","2026년도 가공송전 순시점검 위탁공사","송전선로 정밀점검 안전이격거리 확보","2026-04-14 08:00","2026-04-14 18:00","2026-04-14 08:00","2026-04-14 18:00","매일"]
[831,"경남","진주","거창합천#2 T/L","2026년도 가공송전 순시점검 위탁공사","송전선로 정밀점검 안전이격거리 확보","2026-04-23 08:00","2026-04-23 18:00","2026-04-23 08:00","2026-04-23 18:00","매일"]
[832,"경남","통영","거류통영#1 T/L"," 거류-통영#1T/L 추락방지장치 설치공사"," 거류-통영#1T/L 추락방지장치 설치공사","2026-04-11 07:00","2026-04-12 18:00","2026-04-11 07:00","2026-04-12 18:00","매일"]
[833,"경남","통영","신고성삼천포#1 T/L"," 신고성-삼천포#1 T/L 정밀점검"," 신고성-삼천포#1 T/L 정밀점검, 1~22호 정밀점검","2026-04-27 07:00","2026-04-28 18:00","2026-04-27 07:00","2026-04-28 18:00","매일"]
[834,"경남","통영","신고성삼천포#2 T/L"," 신고성-삼천포#2 T/L 정밀점검"," 신고성-삼천포#2 T/L 정밀점검, 1~22호 정밀점검","2026-04-29 07:00","2026-04-30 18:00","2026-04-29 07:00","2026-04-30 18:00","매일"]
[835,"경남","통영","신고성거류#3 T/L"," 신고성-거류#3 T/L추락방지장치 설치공사"," 신고성-거류#3 T/L 추락방지장치 설치공사 레일형","2026-04-16 07:00","2026-04-16 18:00","취소","취소","매일"]
[836,"경남","통영","신고성거류#1 T/L"," 신고성-거류#1 T/L추락방지장치 설치공사"," 신고성-거류#1 T/L 추락방지장치 설치공사 레일형","2026-04-16 07:00","2026-04-16 18:00","취소","취소","매일"]
[837,"경남","통영","진동안정#2 T/L","진동-안정#2 T/L 폴리머지지애자 설치","진동-안정#2 T/L 폴리머지지애자 설치","2026-04-22 09:00","2026-04-26 18:00","2026-04-22 09:00","2026-04-26 18:00","연속"]
[838,"경남","통영","진동안정#1 T/L","안정S/S 진동-안정#1 T/L GIS 조작시험 등","안정S/S 진동-안정#1 T/L GIS 조작시험 진동S/S 진동-안정#1 T/L GIS LA 보통점검","2026-04-19 09:00","2026-04-19 18:00","2026-04-19 09:00","2026-04-19 18:00","당일"]
[839,"경남","통영","진동안정#1 T/L"," 서마산-진동#1T/L 폴리머 점퍼지지애자 설치관련 안전이격확보"," 서마산-진동#1T/L 고정형 폴리머 점퍼지지애자(9~42호,9기) 설치 관련 안전이격 확보","2026-04-20 07:00","2026-04-20 18:00","2026-04-20 07:00","2026-04-20 18:00","당일"]
[840,"경남","통영","통영거제#2 T/L"," 통영거제#2 T/L 추락방지장치 설치공사"," 통영거제#2 T/L 추락방지장치 설치공사","2026-04-11 07:00","2026-04-12 18:00","2026-04-11 07:00","2026-04-12 18:00","매일"]
[841,"경남","통영","통영거제#1 T/L","거제S/S #3M.Tr 1차 GIS 시험가압","거제S/S #3M.Tr 1차 GIS 시험가압","2026-04-25 09:30","2026-04-25 18:00","2026-04-25 09:30","2026-04-25 18:00","당일"]
[842,"경남","통영","거류통영복합#1 T/L","통영복합S/Y 거류-통영복합#1 T/L GIS 하자점검","통영복합S/Y 거류-통영복합#1 T/L GIS 하자점검","2026-04-22 09:00","2026-04-22 14:00","2026-04-22 09:00","2026-04-22 14:00","당일"]
[843,"경남","통영","고성통영CC#1 T/L","고성-통영복합#1,2T/L 항공구 설치","고성-통영복합#1,2T/L 항공구 설치","2026-04-20 07:00","2026-04-21 18:00","2026-04-20 07:00","2026-04-21 18:00","매일"]
[844,"경남","통영","거류통영복합#2 T/L","통영복합S/Y 거류-통영복합#2 T/L GIS 하자점검","통영복합S/Y 거류-통영복합#2 T/L GIS 하자점검","2026-04-22 14:00","2026-04-22 18:00","2026-04-22 14:00","2026-04-22 18:00","당일"]
[845,"경남","통영","고성통영CC#2 T/L","고성-통영복합#1,2T/L 항공구 설치","고성-통영복합#1,2T/L 항공구 설치","2026-04-20 07:00","2026-04-21 18:00","2026-04-20 07:00","2026-04-21 18:00","매일"]
[846,"경남","함안","중리가야#1 T/L","가야S/S 170kV 장기사용GIS 대체공사","대체 : 중리-가야#1T/L, #2M.Tr, 모선보호반 설치 : SEC CB,#2PT&ES","2026-04-08 17:00","2026-04-09 08:30","2026-04-08 17:00","2026-04-09 08:30","연속"]
[847,"경남","함안","가야S/S #65 BUS","가야S/S 170kV 장기사용GIS 대체공사","대체 : 중리-가야#1T/L, #2M.Tr, 모선보호반 설치 : SEC CB,#2PT&ES","2026-04-09 08:30","2026-04-18 15:00","2026-04-09 08:30","2026-04-18 15:00","연속"]
[848,"경남","함안","중리가야#1 T/L","가야S/S 170kV 장기사용GIS 대체공사","대체 : 중리-가야#1T/L, #2M.Tr, 모선보호반 설치 : SEC CB,#2PT&ES","2026-04-17 17:00","2026-04-18 23:00","2026-04-17 17:00","2026-04-18 23:00","연속"]
[849,"경남","함안","중리가야#2 T/L","가야S/S 170kV 장기사용GIS 대체공사","대체 : 중리-가야#2T/L, #3M.Tr 1차 GIS 설치 : 6200 GIS","2026-04-23 17:00","2026-04-23 19:00","2026-04-23 17:00","2026-04-23 19:00","당일"]
[850,"경남","함안","가야S/S #60 BUS","가야S/S 170kV 장기사용GIS 대체공사","대체 : 중리-가야#2T/L, #3M.Tr 1차 GIS 설치 : 6200 GIS","2026-04-24 08:30","2026-05-07 08:30","2026-04-24 08:30","2026-05-07 08:30","연속"]
[851,"경남","함안","중리가야#2 T/L","가야S/S 170kV 장기사용GIS 대체공사","대체 : 중리-가야#2T/L, #3M.Tr 1차 GIS 설치 : 6200 GIS","2026-04-20 17:00","2026-04-21 08:30","2026-04-20 17:00","2026-04-21 08:30","연속"]
[852,"경남","함안","신월동읍#2 T/L","동읍S/S 신월-동읍#2T/L GIS 보통점검","동읍S/S 신월-동읍#2T/L GIS 보통점검","2026-04-25 09:30","2026-04-25 17:30","2026-04-25 09:30","2026-04-25 17:30","당일"]
[853,"경남","함안","신월동읍#1 T/L","동읍S/S 신월-동읍#1T/L GIS 보통점검","동읍S/S 신월-동읍#1T/L GIS 보통점검","2026-04-18 09:30","2026-04-18 17:30","2026-04-18 09:30","2026-04-18 17:30","당일"]
[854,"경남","함안","부북밀양#2 T/L","밀양S/S 장기사용 170kV GIS 대체공사","#60-61-0 BUS SEC GIS 증설 및 시험가압","2026-04-13 09:00","2026-04-24 18:00","2026-04-13 09:00","2026-04-24 18:00","연속"]
[855,"경남","함안","밀양S/S #60 BUS","밀양S/S 장기사용 170kV GIS 대체공사","#60-61-0 BUS SEC GIS 증설","2026-04-13 09:00","2026-04-24 18:00","2026-04-13 09:00","2026-04-24 18:00","연속"]
[856,"경남","함안","밀양S/S #65 BUS","밀양S/S 장기사용 170kV GIS 대체공사","#65-66-0 BUS SEC GIS 증설","2026-04-27 09:00","2026-05-12 18:00","2026-04-27 09:00","2026-05-12 18:00","연속"]
[857,"경남","함안","부북밀양#2 T/L","밀양S/S 장기사용 170kV GIS 대체공사","#65-66-0 BUS SEC GIS 증설 및 시험가압","2026-04-27 09:00","2026-05-12 18:00","2026-04-27 09:00","2026-05-12 18:00","연속"]
[858,"경남","함안","부북밀양#1 T/L","부북 부북-밀양#1T/L GIS 하자점검","부북 부북-밀양#1T/L GIS 하자점검","2026-04-06 09:30","2026-04-06 17:30","2026-04-06 09:30","2026-04-06 17:30","당일"]
[859,"경남","함안","청도부북#2 T/L","부북 청도-부북#2T/L GIS 하자점검","부북 청도-부북#2T/L GIS 하자점검","2026-04-03 09:30","2026-04-03 17:30","2026-04-03 09:30","2026-04-03 17:30","당일"]
[860,"경남","함안","청도부북#1 T/L","부북 청도-부북#1T/L GIS 하자점검","부북 청도-부북#1T/L GIS 하자점검","2026-04-02 09:30","2026-04-02 17:30","2026-04-02 09:30","2026-04-02 17:30","당일"]
[861,"경남","함안","부북밀양#2 T/L","부북 부북-밀양#2T/L GIS 하자점검","부북 부북-밀양#2T/L GIS 하자점검","2026-04-07 09:30","2026-04-07 17:30","2026-04-07 09:30","2026-04-07 17:30","당일"]
[862,"경남","함안","서마산진동#1 T/L"," 서마산-진동#1T/L 폴리머 점퍼지지애자 설치"," 서마산-진동#1T/L -고정형 폴리머 점퍼지지애자(9~42호,9기) 설치 -상간스페이셔 설치(34~35호) 구간 설치 ※ 진동-안정#1T/L 병가로 동시휴전 필요","2026-04-20 07:00","2026-04-22 18:00","2026-04-20 07:00","2026-04-22 18:00","매일"]
[863,"경남","함안","서마산진동#2 T/L"," 서마산-진동#2T/L 폴리머 점퍼지지애자 설치"," 서마산-진동#2T/L -고정형 폴리머 점퍼지지애자(5~42호,12기) 설치 -상간스페이셔 설치(9~10호,15~16호,28~29호,30~31호) 구간 설치 ※ 진동-안정#2T/L 병가로 동시휴전 필요","2026-04-23 07:00","2026-04-27 18:00","2026-04-23 07:00","2026-04-27 18:00","매일"]
[864,"경남","함안","진영수산#2 T/L"," 진영-수산T/L 철탑 현장실측 및 도면작성 용역"," 진영-수산T/L 56~59호 철탑 현장실측 및 도면작성 용역","2026-04-02 07:00","2026-04-02 18:00","2026-04-02 07:00","2026-04-02 18:00","당일"]
[865,"경남","함안","진영수산#1 T/L"," 진영-수산T/L 철탑 현장실측 및 도면작성 용역"," 진영-수산T/L 56~59호 철탑 현장실측 및 도면작성 용역","2026-04-02 07:00","2026-04-02 18:00","2026-04-02 07:00","2026-04-02 18:00","당일"]
[866,"경남","함안","신마산의창#2 T/L"," 신마산S/S 옥외철구 GIS화 송전전력구공사"," 송전전력구 공사","2026-04-01 09:00","2026-04-04 18:00","2026-04-01 09:00","2026-04-04 18:00","연속"]
[867,"경남","함안","신마산중리#2 T/L","중리S/S 신마산-중리#2T/L GIS 보통점검","중리S/S 신마산-중리#2T/L GIS 보통점검","2026-04-11 09:30","2026-04-11 17:30","2026-04-11 09:30","2026-04-11 17:30","당일"]
[868,"경남","함안","신마산중리#1 T/L","중리S/S 신마산-중리#1T/L GIS 보통점검","중리S/S 신마산-중리#1T/L GIS 보통점검","2026-04-04 09:30","2026-04-04 17:30","2026-04-04 09:30","2026-04-04 17:30","당일"]
[869,"경남","함안","신마산칠서#1 T/L"," 신마산-칠서 등 2개T/L 철탑 현장실측 및 도면작성 용역"," 신마산-칠서T/L 34,35호 철탑 현장실측 및 도면작성 용역(34호 : 신마산-칠서#1T/L 및 칠서-창녕#1T/L 동시휴전 필요)","2026-04-01 07:00","2026-04-01 13:00","2026-04-01 07:00","2026-04-01 13:00","당일"]
{"$rows_empty":7}
[null,null,null," "]